## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation |  | WMP-GDOM-GH-01 | Program | See Column K | Reduce the risk of ignition from vegetation contact, wire slap during wind events, and wildlife interference. | 8.2.1 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 2.6 |  | In Progress
1010000001 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment |  | WMP-GDOM-GH-02 | Program | See Column K | Eliminate wildfire ignition risks. | 8.2.2 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | Quantitative | Circuit Miles | No |  | No target in 2026 | 2026 | 2
1010000002 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements |  | WMP-GDOM-GH-03 | Program | See Column K | Minimize the risk of faults due to pole and associated hardware failure and to maintain system reliability. | 8.2.3 | Equipment ignition likelihood | Quantitative | Poles | No |  |  | 2026 | 2 | 277 |  | In Progress
1010000003 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening |  | WMP-GDOM-GH-05 | Program | See Column K | Support both wildfire risk reduction and system reliability improvements. | 8.2.5 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000004 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids |  | WMP-GDOM-GH-07 | Program | See Column K | Reduce wildfire risk and eliminate the possibility of infrastructure ignition events on lines that are removed or taken out of service. | 8.2.7 | PSPS likelihood PSPS exposure potential | Quantitative | Microgrids | No |  | No target in 2026 | 2026 | 2
1010000005 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment |  | WMP-GDOM-GH-08 | Program | See Column K | Liberty installs reclosers to help with sectionalization, opportunities for distribution automation, and opportunities for grid topology improvement to reduce the size and number of customers affected by faults on the system. Reclosers also help Liberty more quickly identify and restore power to affected customers. | 8.2.8 | Equipment ignition likelihood | Quantitative | Automatic Reclosers | No |  | No target in 2026 | 2026 | 2
1010000006 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removal (in HFTD) |  | WMP-GDOM-GH-09 | Program | See Column K | Line removal eliminates the risk of infrastructure caused ignitions in the area where a line is removed. | 8.2.9 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  | No target in 2026 | 2026 | 2
1010000007 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Tree attachment removals |  | WMP-GDOM-GH-12a | Program | See Column K | Reduce wildfire ignition risk by eliminating the potential for conductor-tree contact, which can lead to faults, arcing, or fire during wind events or tree movement. | 8.2.12.1 | Equipment ignition likelihood | Quantitative | Tree Attachments | No |  |  | 2026 | 2 | 74 |  | In Progress
1010000008 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Expulsion fuse replacement |  | WMP-GDOM-GH-12b | Program | See Column K | Reduce risk of ignition by limiting energy release. | 8.2.12.2 | Equipment ignition likelihood | Quantitative | Expulsion Fuses | No |  |  | 2026 | 2 | 865 |  | In Progress
1010000009 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Animal guards |  | WMP-GDOM-GH-12c | Program | See Column K | Reduce risk of ignition by installing insulating animal guards on exposed substation equipment. | 8.2.12.3 | Equipment ignition likelihood Contact by object ignition likelihood | Quantitative | Animal Guards | No |  | No target in 2026 | 2026 | 2
1010000010 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Open wire/grey wire |  | WMP-GDOM-GH-12e | Program | See Column K | Reduces the risk of ignition and service interruptions, particularly in wildland-urban interface areas where homes and vegetation are in close proximity to overhead infrastructure. | 8.2.12.5 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 7.35 |  | In Progress
1010000011 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Detailed inspections of distribution electric lines and equipment |  | WMP-GDOM-AI-01 | Program | See Column K | Reduce the risk of equipment failure. | 8.3.1 | Equipment ignition likelihood | Quantitative | Circuit Miles | Yes |  |  | 2026 | 2 | 199.17 |  | In Progress
1010000012 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Intrusive pole inspections |  | WMP-GDOM-AI-02 | Program | See Column K | Reduce the risk of equipment failure. | 8.3.2 | Equipment ignition likelihood | Quantitative | Poles | Yes |  |  | 2026 | 2 | 0 |  | Planned
1010000013 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Patrol inspections of distribution electric lines and equipment |  | WMP-GDOM-AI-03 | Program | See Column K | Reduce the risk of equipment failure. | 8.3.3 | Equipment ignition likelihood | Quantitative | Circuit Miles | Yes |  |  | 2026 | 2 | 553.4 |  | Completed
1010000014 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Other discretionary inspections of distribution electric lines and equipment |  | WMP-GDOM-AI-04 | Program | See Column K | Reduce the risk of equipment failure. | 8.3.4 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 0 |  | Planned
1010000015 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Quality assurance / quality control of inspections |  | WMP-GDOM-AI-05 | Program | See Column K | Reduce the risk of equipment failure. | 8.5 | Equipment ignition likelihood | Quantitative | % of Detailed Inspections | Yes |  |  | 2026 | 2 | 0 |  | Planned
1010000016 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Substation inspections |  | WMP-GDOM-AI-06 | Program | See Column K | Reduce the risk of equipment failure. | 8.3.5 | Equipment ignition likelihood | Quantitative | Substations | Yes |  |  | 2026 | 2 | 28 |  | In Progress
1010000017 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair | Equipment maintenance and repair |  | WMP-GDOM-MR-01 | Program | See Column K | Reduce the risk of equipment failure. | 8.4 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | No update in Q2 | In Progress
1010000018 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment settings to reduce wildfire risk |  | WMP-GDOM-GO-01 | Program | See Column K | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | 8.7.1 | Equipment ignition likelihood | Quantitative | # Circuits with SRP | No |  | No target in 2026 | 2026 | 2
1010000019 | LU | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment settings to reduce wildfire risk |  | WMP-GDOM-GO-01 | Program | See Column K | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | 8.7.1 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | 9 out of 11 circuit reviews completed | Planned
1010000020 | LU | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Asset Management and Inspection Enterprise System |  | WMP-GDOM-GO-05 | Program | See Column K | Accept, store, retrieve, and update data for the production, management, and scheduling of related work. | 12 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | 22 open work orders remaining in 2021 Inspection Application | In Progress
1010000021 | LU | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Vegetation Management Inspection Program - Detailed |  | WMP-VM-INSP-01 | Program | See Column K | Prescribe pruning and removal of vegetation as a safeguard against grow‐ins or fall‐ins and to comply with required laws and regulations. | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | Yes |  |  | 2026 | 2 | 178.41 |  | In Progress
1010000022 | LU | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Vegetation Management Inspection Program - Patrol |  | WMP-VM-INSP-02 | Program | See Column K | Conduct as needed based on environmental conditions or other factors. | 9.2.2 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | No |  |  | 2026 | 2 | 28.75 |  | In Progress
1010000023 | LU | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Vegetation Management Inspection Program - LiDar |  | WMP-VM-INSP-03 | Program | See Column K | Measure vegetation to conductor distances, tree height, and proximity to overhead lines. | 9.2.3 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | Yes |  |  | 2026 | 2 | 0 |  | Planned
1010000024 | LU | 2026-08-01 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing - PRC 4292 Required |  | WMP-VM-VFM-01-R | Program | See Column K | Reduce wildfire risk by removing vegetation at base of poles. | 9.4 | Wildfire spread Wildfire hazard | Quantitative | Subject Poles | No |  |  | 2026 | 2 | 3992 |  | In Progress
1010000025 | LU | 2026-08-01 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing - Discretionary |  | WMP-VM-VFM-01-D | Program | See Column K | Reduce wildfire risk by removing vegetation at base of poles. | 9.4 | Wildfire spread Wildfire hazard | Quantitative | Subject Poles | No |  |  | 2026 | 2 | 377 |  | In Progress
1010000026 | LU | 2026-08-01 | Vegetation Management and Inspections | Wood and Slash Management | Wood and Slash Management |  | WMP-VM-VFM-02 | Program | See Column K | Reduce wildfire risks by removing wood and treating brush and slash after vegetation maintenance is performed. | 9.5 | Wildfire spread Wildfire hazard | Quantitative | Acres | No |  |  | 2026 | 2 | 68.1824 |  | In Progress
1010000027 | LU | 2026-08-01 | Vegetation Management and Inspections | Defensible Space | Substation Defensible Space |  | WMP-VM-VFM-03 | Program | See Column K | Maintain accessibility, safety, and adherence to all appropriate governmental regulations and Liberty policies. | 9.6 | Wildfire spread Wildfire hazard | Quantitative | Substation Treatments | No |  |  | 2026 | 2 | 12 |  | Completed
1010000028 | LU | 2026-08-01 | Vegetation Management and Inspections | Integrated Vegetation Management | Fire-Resilient Right-of-Ways |  | WMP-VM-VFM-04 | Program | See Column K | Reduce future maintenance entries, protect infrastructure, increase fire-resiliency and are the initial step of the integrated vegetation management (“IVM”) program. | 9.7 | Wildfire spread Wildfire hazard | Qualitative |  | No |  |  | 2026 | 2 |  | No update in Q2 | Completed
1010000029 | LU | 2026-08-01 | Vegetation Management and Inspections | Clearance | Clearance |  | WMP-VM-VFM-05 | Program | See Column K | Prescribe mitigation of vegetation encroachments. | 9.2 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | No |  |  | 2026 | 2 | 700 |  | Completed
1010000030 | LU | 2026-08-01 | Vegetation Management and Inspections | Fall-In Mitigation | Fall-In Mitigation |  | WMP-VM-VFM-06 | Program | See Column K | Identify trees that pose a high risk of failure. | 9.2 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | No |  |  | 2026 | 2 | 102.5 |  | In Progress
1010000031 | LU | 2026-08-01 | Vegetation Management and Inspections | High-Risk Species | High-Risk Species |  | WMP-VM-VFM-07 | Program | See Column K | Identify trees that pose a high risk of failure. | 9.2 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | No |  | No target in 2026 | 2026 | 2
1010000032 | LU | 2026-08-01 | Vegetation Management and Inspections | Emergency Response Vegetation Management | Emergency Response Vegetation Management |  | WMP-VM-VFM-08 | Program | See Column K | Identify and mitigate significantly damaged trees exhibiting 50% or more crown loss, severe trunk damage or scorching, and are an immediate or critical risk to restoration efforts or the repaired infrastructure. | 9.1 | Wildfire spread Wildfire hazard | Quantitative | Line Miles | No |  | No target in 2026 | 2026 | 2
1010000033 | LU | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Vegetation Management Enterprise System |  | WMP-VM-ESG-01 | Program | See Column K | Accept, store, retrieve, and update data for the production, management, and scheduling of related work. | 12 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | No update in Q2 | In Progress
1010000034 | LU | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control | Quality Assurance and Quality Control |  | WMP-VM-QAQC-01 | Program | See Column K | Provides VM program oversight to provide reasonable assurance that vegetation inspection and maintenance work is being effectively performed. | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Line Miles | No |  |  | 2026 | 2 | 232.9 |  | In Progress
1010000035 | LU | 2026-08-01 | Situational Awareness and Forecasting | Environmental monitoring systems | Environmental monitoring systems |  | WMP-SA-01 | Program | See Column K | Monitor environmental conditions within service territory. | 10.2 | Wildfire exposure potential PSPS exposure potential | Quantitative | Weather Stations | No |  | No target in 2026 | 2026 | 2
1010000036 | LU | 2026-08-01 | Situational Awareness and Forecasting | Grid monitoring systems | Grid monitoring systems |  | WMP-SA-02 | Program | See Column K | Expedite power restoration during an outage by helping line crews locate the fault. | 10.3 | Equipment ignition likelihood | Quantitative | Circuits With Fault Indicators | No |  | No target in 2026 | 2026 | 2
1010000037 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Collaboration and coordination with public safety partners | Collaboration and coordination with public safety partners |  | WMP-EP-02 | Program | See Column K | Inform external public safety partners and other interconnected electrical corporation partners of wildfire, PSPS, and re-energization events as required by G.O. 166 and Public Utilities Code Section 768.6. | 11.3.1 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty partipated in: 1. Colaboration Meetings with Tahoe Public Utilities District and NV Energy. 2. El Doroado County Project Coordination Group 3.South Tahoe Public Utility District and Lake Valley Fire Protection District Hazard Mitigation Planning 4. Placer County OES Coordination Meetings 5. El Dorado County OES Coordination Meetings 6. Cal OES Coordination Meetings 7. Utility Watch Coordination Group Meetings 8. Mono County Social Serices Meeting 9. Placer County Fire Safe Alliance Meetings 10. Participated in SDG&E TTX 11. Tahoe Fire and Fuels Team Coordination Meeting 12. University of Reno, NV Energy, and Bureau of Land Management Wildfire Camera meetings | In Progress
1010000038 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Customer support in wildfire and PSPS emergencies | Customer support in wildfire and PSPS emergencies |  | WMP-EP-05 | Program | See Column K | Increase awareness and community resiliency to wildfires and PSPS events. | 11.5 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty conducted a PSPS tabletop exercise and functional exercise in Q2. | In Progress
1010000039 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Learning after wildfire and PSPS events | Learning after wildfire and PSPS events |  | WMP-EP-06 | Program | See Column K | Increase awareness and community resiliency to wildfires and PSPS events. | 7 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty produced an After Action Report for the Functional Exercise June 25, 2026. | In Progress
1010000040 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | WMP-CO-01 | Program | See Column K | Increase awareness and community resiliency to wildfires and PSPS events. | 11.4.3 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty executed a pre-season wave of Wildfire Awareness Customer Surveys including interviews in Q2. Results are planned to be reviewed in Q3. Liberty participated in 6 community outreach events in Q2. | In Progress
1010000041 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Engagement with AFN populations, local governments, and tribal communities | Engagement with AFN populations, local governments, and tribal communities |  | WMP-CO-03 | Program | See Column K | Increase awareness and community resiliency to wildfires and PSPS events, including identification of AFN customers. | 11.4.4 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty participated in 7 engagements in Q2 reaching CBOs and 3 engagements with local government contacts. | In Progress
1010000042 | LU | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Best practice sharing with other electrical corporations | Best practice sharing with other electrical corporations |  | WMP-CO-05 | Program | See Column K | Share industry best practices | 11.4.4 | PSPS vulnerability Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Liberty participated in 13 working groups and councils in Q2. | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 1
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 20
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 2
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 8
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 2
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 10
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 33
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 10
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 2
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 4
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 15
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 1
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | LU | 2026 | 2 | 0
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | LU | 2026 | 2 | 58
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | LU | 2026 | 2 | 207
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | LU | 2026 | 2 | 127
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | LU | 2026 | 2 | 176
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | LU | 2026 | 2 | 60
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | LU | 2026 | 2 | 62
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | LU | 2026 | 2 | 230
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | LU | 2026 | 2 | 244
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | LU | 2026 | 2 | 212
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | LU | 2026 | 2 | 215
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | LU | 2026 | 2 | 64
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | LU | 2026 | 2 | 70
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 5016
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 10176
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 912
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 974
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 3480
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 3480
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 13152
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 39216
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 816
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 3067
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 26520
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | LU | 2026 | 2 | 35300
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | LU | 2026 | 2 | 0
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | LU | 2026 | 2 | 1805
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | LU | 2026 | 2 | 0
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | LU | 2026 | 2 | 3750
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | LU | 2026 | 2 | 3
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  | Liberty does not track this metric | LU | 2026 | 2
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | LU | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | LU | 2026 | 2 | 0
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | LU | 2026 | 2 | 0
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | LU | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | LU | 2026 | 2 | 0
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | LU | 2026 | 2 | 0
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | LU | 2026 | 2 | 0
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 2441
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 86.18
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 51
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 517
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 380
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 9.13
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 9
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 76
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 72
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 1.51
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 5
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 14
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | LU | 2026 | 2 | 0
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | LU | 2026 | 2 | 0
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 1
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 47
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 13
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 430
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 22
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 5
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 1
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 5
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 2
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 7
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | LU | 2026 | 2 | 0
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 2718
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 71
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 1
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 1
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 42
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 5
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 31
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 2
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 1
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 1
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | LU | 2026 | 2 | 0
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | LU | 2026 | 2 | 0
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Liberty did not experience a utility ignited wildfire in Q2 of 2026 | LU | 2026 | 2 | 0

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 1.665
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | LU | 2026 | 2 | 4.078
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 1.665
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | LU | 2026 | 2 | 4.078
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 504.352
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 1.577
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 23.116
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 12.631
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 0
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | LU | 2026 | 2 | 0

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 1
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 2
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 4
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 1
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 2
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 2
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 3
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 2
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 4
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 7
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 3
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 1
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 1
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 7
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 1
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 1
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 4
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 3
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 3
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 1
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 1
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 1
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 2
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 1
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 2
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 6
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 3
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | LU | 2026 | 2 | 0
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | LU | 2026 | 2 | 0
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | LU | 2026 | 2 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | LU | 2026 | 2 | 0
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | LU | 2026 | 2 | 0
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | LU | 2026 | 2 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 4.48
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.87
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 12.74
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 5.27
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 52.11
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 14.59
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 304.84
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 18.31
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 577.11
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 163.75
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 114.54
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 72.62
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.03
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 108.41
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 15.8
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.44
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.4
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.09
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.18
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.54
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.25
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 5.68
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 20.69
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.29
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.03
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 2.32
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 22.13
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.06
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 3.41
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.57
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 8.85
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.91
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 104.48
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 11.91
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 303.23
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 79.43
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 36.21
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 11.05
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 8.88
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.47
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.06
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.09
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.15
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 14
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 3
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 16
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 4
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 98
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 14
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 520
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 69
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 473
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 120
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 90
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 39
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 0
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 0
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 57
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 5
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 0
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | LU | 2026 | 2 | 0
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 1030
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 16
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 369
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 19
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 1443
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 39
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 14744
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 39
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 20088
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 1064
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 1757
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 209
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 1
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 0
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 2749
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 139
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | LU | 2026 | 2 | 0
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | LU | 2026 | 2 | 0
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 102
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 11
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 75
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 91
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 191
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 70
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 2198
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 249
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 1605
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 401
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 142
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 96
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 0
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 0
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 56
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 4
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 0
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | LU | 2026 | 2 | 0
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 344
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 6
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 130
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 7
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 688
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 28
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 5817
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 25
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 6280
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 358
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 766
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 100
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 0
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 0
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 887
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 44
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 0
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | LU | 2026 | 2 | 0
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 2
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 5
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 2
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 1
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 4
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 2
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 8
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 11
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 5
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 7
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 1
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.03
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.01
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.06
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.06
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.03
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.22
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.07
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.04
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.02
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.22
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.02
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.06
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.03
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.03
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.01
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.12
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | -0.09
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.41
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.16
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.22
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.1
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0.02
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.06
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 1.36
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | LU | 2026 | 2 | 0
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 1
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | LU | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | LU | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | LU | 2026 | 2 | 0
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | LU | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | LU | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | LU | 2026 | 2 | 0
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | LU | 2026 | 2 | 0
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | LU | 2026 | 2 | 0
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | LU | 2026 | 2 | 0
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | LU | 2026 | 2 | 0
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | LU | 2026 | 2 | 0
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | LU | 2026 | 2 | 0
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | LU | 2026 | 2 | 0
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | LU | 2026 | 2 | 0
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | LU | 2026 | 2 | 1
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | LU | 2026 | 2 | 0
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | LU | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | LU | 2026 | 2 | 0
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | LU | 2026 | 2 | 236.19
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | LU | 2026 | 2 | 0
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | LU | 2026 | 2 | 0
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | LU | 2026 | 2 | 0
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | LU | 2026 | 2 | 0
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | LU | 2026 | 2 | 0
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | LU | 2026 | 2 | 0
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | LU | 2026 | 2 | 0
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | LU | 2026 | 2 | 0
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | LU | 2026 | 2 | 0
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | LU | 2026 | 2 | 0
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | LU | 2026 | 2 | 0
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | LU | 2026 | 2 | 0
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | LU | 2026 | 2 | 0
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | LU | 2026 | 2 | 0
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | LU | 2026 | 2 | 0
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | LU | 2026 | 2 | 0
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | LU | 2026 | 2 | 0
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | LU | 2026 | 2 | 0
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | LU | 2026 | 2 | 0
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | LU | 2026 | 2 | 0
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | LU | 2026 | 2 | 0
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | LU | 2026 | 2 | 0

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1120000000 | a4f85bc5-1f59-4489-94b7-c6a19a5378c0 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2026-04-24, Work Order ID: 7051c15f-fd25-4897-b5bd-cee9cb34a598 |  | LU | 2026 | 2
1120000001 | a4f85bc5-1f59-4489-94b7-c6a19a5378c0 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: aeb026f0-5dbd-4c0c-81a8-ec84afc04aad |  | LU | 2026 | 2
1120000002 | 232b309f-2784-4aae-8380-606ef4a42e8a | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-30, Work Order ID: 4a7f65ad-2054-4c77-a306-c07ee85c919c |  | LU | 2026 | 2
1120000003 | 439f6388-e65e-4cb2-a22d-a74573f3a79f | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-30, Work Order ID: 8803daff-a46c-48d0-9db2-7813bc072bc2 |  | LU | 2026 | 2
1120000004 | 439f6388-e65e-4cb2-a22d-a74573f3a79f | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: a772a60c-edcd-4b32-a295-235300167d47 |  | LU | 2026 | 2
1120000005 | e0da3074-1c87-4223-81db-66a9a1a865d3 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: a6d4b552-f14e-4fc3-80f0-62eb53aba03f |  | LU | 2026 | 2
1120000006 | e0da3074-1c87-4223-81db-66a9a1a865d3 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: b4e4e4e7-a53b-45d6-93dd-0668bd8928ba |  | LU | 2026 | 2
1120000007 | eba9351e-8d73-40ce-8a12-a0a39cbb9931 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-30, Work Order ID: 30e8070b-d10f-4504-b319-6c852c74c99b |  | LU | 2026 | 2
1120000008 | eba9351e-8d73-40ce-8a12-a0a39cbb9931 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 8eab24ed-e009-4189-adae-e4b57332add7 |  | LU | 2026 | 2
1120000009 | eba9351e-8d73-40ce-8a12-a0a39cbb9931 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-30, Work Order ID: c2597446-5bbe-4f04-a34f-e53765533bff |  | LU | 2026 | 2
1120000010 | eba9351e-8d73-40ce-8a12-a0a39cbb9931 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: e3cca12a-9ebe-4c0d-8402-ae31adff5a3e |  | LU | 2026 | 2
1120000011 | eba9351e-8d73-40ce-8a12-a0a39cbb9931 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: e7b2a0ab-4957-4564-b0a3-5459d9809a2a |  | LU | 2026 | 2
1120000012 | f558a4e4-ed21-4278-a549-7c1417f9d3bf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 91013227-0264-43ea-b38e-5c5ba5c6a254 |  | LU | 2026 | 2
1120000013 | f558a4e4-ed21-4278-a549-7c1417f9d3bf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: b8d27b57-a227-47a2-a5a6-d4ccafe7912b |  | LU | 2026 | 2
1120000014 | 4c7235ed-4871-42e6-ac07-de3fb576f831 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 3de66dfa-b685-46a5-93cb-1a37e7c4e5cd |  | LU | 2026 | 2
1120000015 | 4c7235ed-4871-42e6-ac07-de3fb576f831 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 5dcfc4b5-532e-4721-8c62-2efad807c65d |  | LU | 2026 | 2
1120000016 | 4c7235ed-4871-42e6-ac07-de3fb576f831 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: de54c866-a072-4c63-9765-dc9ddbe58c3c |  | LU | 2026 | 2
1120000017 | 21da0b74-8d28-4796-b590-3f170e116975 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 0e07e82b-d4b9-46da-a455-1cf21add34fd |  | LU | 2026 | 2
1120000018 | 21da0b74-8d28-4796-b590-3f170e116975 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-28, Work Order ID: 64b0658a-7494-42bc-b2e1-b4e51655c59f |  | LU | 2026 | 2
1120000019 | 0d03a769-6559-4e54-884d-372fc35fda6d | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 26e54547-e160-44cd-a3ae-c3e778a49c56 |  | LU | 2026 | 2
1120000020 | 0d03a769-6559-4e54-884d-372fc35fda6d | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 7c527692-d633-4bee-81f6-a7d290ac065f |  | LU | 2026 | 2
1120000021 | 0d03a769-6559-4e54-884d-372fc35fda6d | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2026-07-29 | Level 2 |  | Reinspection Date: 2025-07-29, Work Order ID: f89db694-9f8d-496f-b313-3f71c242ee72 |  | LU | 2026 | 2
1120000022 | 67b3f4ee-226a-4599-9cce-72f34c173c83 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 20b8bfa3-f8b1-433f-a71a-711f0dc568a8 |  | LU | 2026 | 2
1120000023 | 67b3f4ee-226a-4599-9cce-72f34c173c83 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 3747eb8c-a0b1-4113-9218-b496a86e633d |  | LU | 2026 | 2
1120000024 | 67b3f4ee-226a-4599-9cce-72f34c173c83 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 6746aa56-cc68-4791-9d94-7ffb8f78b794 |  | LU | 2026 | 2
1120000025 | 67b3f4ee-226a-4599-9cce-72f34c173c83 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: cd14782e-f573-47b4-8de2-06601653b8a2 |  | LU | 2026 | 2
1120000026 | 8a7d97ca-60cf-403b-a156-046952460c45 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2026-07-29 | Level 2 |  | Reinspection Date: 2025-07-29, Work Order ID: 816d9bb7-b16a-49fc-94ae-e97fe36f9e4a |  | LU | 2026 | 2
1120000027 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 3437f5cd-164f-4b99-a11b-6c255be2ff18 |  | LU | 2026 | 2
1120000028 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 838ee497-52a0-4b4f-aadc-d019bee4c4db |  | LU | 2026 | 2
1120000029 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 8cfed7b7-6137-4e14-af2f-99074c547a9d |  | LU | 2026 | 2
1120000030 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 8d749907-874d-4fc3-9783-7b73fcd6db09 |  | LU | 2026 | 2
1120000031 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 91346a6e-e64e-4db1-b3b0-f23a6d7710a8 |  | LU | 2026 | 2
1120000032 | 8df06911-6842-4694-a653-7a60e44e0acf | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 |  | 2025-07-29 |  | 2026-07-29 | Level 2 |  | Reinspection Date: 2025-07-29, Work Order ID: be57ddfc-63e7-483f-b3b1-bf55e93bdb71 |  | LU | 2026 | 2
1120000033 | 5235e926-3345-4961-bf0a-47b3e040a97a | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 0a7051fd-f99a-4fc7-bcdb-6b22eb5caf49 |  | LU | 2026 | 2
1120000034 | 5235e926-3345-4961-bf0a-47b3e040a97a | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 4013781c-1e73-4a0d-a875-5a41098652d5 |  | LU | 2026 | 2
1120000035 | 5235e926-3345-4961-bf0a-47b3e040a97a | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 9e0184ea-f62b-4a77-a09a-07a6dc3d5880 |  | LU | 2026 | 2
1120000036 | e71b3b0b-6e25-4344-bd82-1411929f7eb6 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 707ef125-75ae-4c80-bb3a-065165100e96 |  | LU | 2026 | 2
1120000037 | e71b3b0b-6e25-4344-bd82-1411929f7eb6 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: fe83b31f-37e0-4e1f-b4ee-7d36175d7038 |  | LU | 2026 | 2
1120000038 | d37e823a-3bfe-401d-9c21-61bef80e8949 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 98aad18c-0221-4ad1-85aa-b7dca141d793 |  | LU | 2026 | 2
1120000039 | d37e823a-3bfe-401d-9c21-61bef80e8949 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: f3ad7e61-20c6-4d14-9f80-89da0466d0b1 |  | LU | 2026 | 2
1120000040 | 1538eac7-4b36-413b-a12b-0866d21a51a6 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 2025-12-12 |  | 2030-12-11 | Level 3 |  | Reinspection Date: 2025-12-12, Work Order ID: 87dd557a-b7e2-429b-8cb3-67388b4dbced |  | LU | 2026 | 2
1120000041 | e8e60c03-85b8-4584-8c9b-d935fbb65328 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 96e891e5-43fc-4c9d-9fa4-e3680955dcf2 |  | LU | 2026 | 2
1120000042 | 518d2ff7-6ee7-4d3a-a6af-9a7b1dd8eebb | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2025-11-18 |  | 2030-11-17 | Level 3 |  | Reinspection Date: 2025-11-18, Work Order ID: 9d634eeb-93ca-4720-bfc5-8dc868381e00 |  | LU | 2026 | 2
1120000043 | 9a98dac3-55d5-4e0f-9ef7-b2ecaa2a2c6a | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 175b06b4-6b4f-4b3a-a090-3303258b861f |  | LU | 2026 | 2
1120000044 | 9a98dac3-55d5-4e0f-9ef7-b2ecaa2a2c6a | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: d13ef683-e2dc-47cb-8b8a-789d662070fc |  | LU | 2026 | 2
1120000045 | 85944aeb-f3c2-4ed9-a0f0-ff2a0057faa6 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 8ebf6fd9-25f3-445e-b792-0e8bd4559234 |  | LU | 2026 | 2
1120000046 | 85944aeb-f3c2-4ed9-a0f0-ff2a0057faa6 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: dcb30b11-426b-48a9-abe2-a99612f49df9 |  | LU | 2026 | 2
1120000047 | 74572c8e-7d40-46b6-bd2f-cf080c3105e2 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 3d37f973-002f-4d00-bf37-ff777df73430 |  | LU | 2026 | 2
1120000048 | 74572c8e-7d40-46b6-bd2f-cf080c3105e2 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 95485a66-1077-4af7-a5f4-99f139ac057f |  | LU | 2026 | 2
1120000049 | 74572c8e-7d40-46b6-bd2f-cf080c3105e2 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: eddd8d2c-8f9c-495b-8a18-de23d77aad1f |  | LU | 2026 | 2
1120000050 | 6777086e-f51d-4f14-a648-4aae728dc556 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 313026f1-b250-49d3-8cc7-65f064189836 |  | LU | 2026 | 2
1120000051 | 6777086e-f51d-4f14-a648-4aae728dc556 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: ab99daaf-5e68-431e-8049-227a301d9876 |  | LU | 2026 | 2
1120000052 | 1aa8ceb4-0a04-4c59-9c7e-d7be039589ef | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 5e8a21f2-af10-4450-8dd6-01c42a4f86ac |  | LU | 2026 | 2
1120000053 | 1aa8ceb4-0a04-4c59-9c7e-d7be039589ef | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 707639f6-e33b-4430-95e4-59649dc3877d |  | LU | 2026 | 2
1120000054 | 0a0feab9-57ec-4c31-bf8d-4af6507767ae | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 0d67a575-89f0-4af2-ab58-80dbd35d6598 |  | LU | 2026 | 2
1120000055 | 0a0feab9-57ec-4c31-bf8d-4af6507767ae | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 5cb05bdc-f79b-41b5-b336-9f2233eb39c9 |  | LU | 2026 | 2
1120000056 | 431f01d3-8454-4f58-ac7f-720fdcc3802a | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 0cea5c04-5d6a-464e-b0b4-ee3186bd31d2 |  | LU | 2026 | 2
1120000057 | ef993ee2-6d32-4be8-aed5-68237e9b2224 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 2becc7bb-9ece-4a92-b4e2-2f418ef86c20 |  | LU | 2026 | 2
1120000058 | ef993ee2-6d32-4be8-aed5-68237e9b2224 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 637ff63b-e7cd-4501-88e4-bd0746bb3216 |  | LU | 2026 | 2
1120000059 | fcb199cc-6853-44d9-867a-8316e74174bc | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: e0dc7534-8713-49fb-8ac1-9e6ba7af0b61 |  | LU | 2026 | 2
1120000060 | fcb199cc-6853-44d9-867a-8316e74174bc | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: e5a4fa12-c84e-408a-a866-50f3c8906c07 |  | LU | 2026 | 2
1120000061 | d27a56e8-168d-44a8-8752-6b519630b191 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 7573a44f-a0e9-4e9c-b17d-34767b68f516 |  | LU | 2026 | 2
1120000062 | d27a56e8-168d-44a8-8752-6b519630b191 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 8eaf2e25-5656-4b2a-9278-ff9880566af3 |  | LU | 2026 | 2
1120000063 | d27a56e8-168d-44a8-8752-6b519630b191 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-12-09, Work Order ID: 909855db-5fba-4949-a1db-6b456848fbb3 |  | LU | 2026 | 2
1120000064 | a5084516-bb31-44fd-908f-aad9d554aacb | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 665af605-add2-4e37-aa50-4a665e20a735 |  | LU | 2026 | 2
1120000065 | a5084516-bb31-44fd-908f-aad9d554aacb | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 910794f4-1bdb-4823-afb6-b6204cf75339 |  | LU | 2026 | 2
1120000066 | a5084516-bb31-44fd-908f-aad9d554aacb | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 92b17315-6939-4fc1-acab-849710a1efed |  | LU | 2026 | 2
1120000067 | a58c5df8-ece2-4bdd-927f-4215ff050352 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 74ca4864-a3d3-4e9e-b7d3-e2b26d634e5d |  | LU | 2026 | 2
1120000068 | ac01ea06-fa29-4e08-8174-31d59f43e0ee | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: c9e68835-f23d-4727-a688-a25686b3e8ac |  | LU | 2026 | 2
1120000069 | bc8d2f58-b236-4b4a-96b1-88303770ef94 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: e79ca478-ad5f-4f51-bb1d-ad28baf8ae13 |  | LU | 2026 | 2
1120000070 | c1fc9ab8-47fe-43e7-b6d3-dd671c44889d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 8264ebc6-9030-44bf-bff6-a1282c6a8a78 |  | LU | 2026 | 2
1120000071 | c1fc9ab8-47fe-43e7-b6d3-dd671c44889d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: b185f5a6-4e0d-4e7f-8c73-be975480bdf3 |  | LU | 2026 | 2
1120000072 | d481e1ef-55cb-4f9d-b59f-c9bbeb4d4244 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 58b86c9d-6e6a-43cd-ad8c-305d9da377c8 |  | LU | 2026 | 2
1120000073 | ccc9829a-ade2-40fc-824d-430b937ed1e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 9fe660c9-19bc-4cbf-b499-e2b32944229f |  | LU | 2026 | 2
1120000074 | d8ddd7c7-97fb-4648-8d61-8dac6234f8d5 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 756cf75d-f8c5-4142-8bfe-4be3fd0cbe57 |  | LU | 2026 | 2
1120000075 | de2c86eb-9025-4158-a4b3-b2b895876829 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: bc45fbee-2967-47e7-beb6-48dc6961654a |  | LU | 2026 | 2
1120000076 | df3c6813-907e-4f09-96ab-b3dc3586a25c | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 7c054535-b167-4214-9235-495c3f09ff94 |  | LU | 2026 | 2
1120000077 | e1605807-986c-4051-b715-c2bd7254d94c | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 791b5866-0050-4f18-9640-709c39171fea |  | LU | 2026 | 2
1120000078 | fc296a43-2241-4719-a193-e003d4009a45 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: b854bf3d-674c-40b0-a5d7-6b845f7a4366 |  | LU | 2026 | 2
1120000079 | fc296a43-2241-4719-a193-e003d4009a45 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: f80450b9-a145-4480-88f9-9f19f37f6faf |  | LU | 2026 | 2
1120000080 | f97a3670-8864-4503-9b18-b9e4e00f6198 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 04f37541-fc39-40bf-a4e6-9f5c4487786c |  | LU | 2026 | 2
1120000081 | f97a3670-8864-4503-9b18-b9e4e00f6198 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 106e523f-ecb2-4d83-ad76-2c6d999c0e34 |  | LU | 2026 | 2
1120000082 | f97a3670-8864-4503-9b18-b9e4e00f6198 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 880e2a64-f39a-4c5f-9084-739b022caf27 |  | LU | 2026 | 2
1120000083 | f97a3670-8864-4503-9b18-b9e4e00f6198 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: b628689d-a979-469f-90f6-bba3bf0b49a4 |  | LU | 2026 | 2
1120000084 | ff5be9ef-a4e3-4bcc-90e2-b8d1fa6ec063 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 58343646-47ed-41c4-8fe3-d63cd5c085c8 |  | LU | 2026 | 2
1120000085 | 39aa3ddf-7aae-43af-8a0a-b2ffa61af7ec | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 4f57d86d-c82d-45c2-96ee-a2f06c9568fc |  | LU | 2026 | 2
1120000086 | 3ac8fb00-7608-4be2-abc3-e5e8db3bacb9 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 36cd5209-5ccc-4b61-8164-f01c7d5815cc |  | LU | 2026 | 2
1120000087 | 3ac8fb00-7608-4be2-abc3-e5e8db3bacb9 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: e5042c0f-cd36-4b6c-bc10-7b8161cbed83 |  | LU | 2026 | 2
1120000088 | 3baeeecd-1d29-4b42-bca1-d915017fe274 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 626bcd65-2a00-4138-87eb-d76664e4f92b |  | LU | 2026 | 2
1120000089 | 175ccc22-7e29-4628-9fd7-aa63a2d9c412 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: a2a16261-0e4d-47c4-9888-3bdcb59a0ac6 |  | LU | 2026 | 2
1120000090 | 17e4f2b0-365f-4ba5-bec3-f7825a71411a | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: adee4412-0122-47fd-a3a6-810c8940ae84 |  | LU | 2026 | 2
1120000091 | 1567d2d3-663b-4a7f-b096-c923873cfc8c | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 0c6fba0a-e293-4ca8-9394-8bf0037f532c |  | LU | 2026 | 2
1120000092 | 670f4f1a-5f72-4e45-a4cb-2af3dc11befd | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-07 |  | 2026-08-07 | Level 2 |  | Reinspection Date: 2025-08-07, Work Order ID: 83026beb-a268-4080-b952-415702abbec1 |  | LU | 2026 | 2
1120000093 | 6e288cdd-bdc2-4597-b76b-5620ee2aede5 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: ea419da6-6693-4b30-b871-80376b8343ce |  | LU | 2026 | 2
1120000094 | 5e2c463f-5dcc-4238-a904-4a1a72797669 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: ae699d78-35bd-449f-8778-5bd58009f3c4 |  | LU | 2026 | 2
1120000095 | 7607f6e6-7692-4d68-954f-2ef3be3e66dc | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 81c3a22e-afad-4ca8-8c86-843a8a338e5c |  | LU | 2026 | 2
1120000096 | 79b2b04c-d393-470d-8c5a-01c44c7d070e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 4bcab022-3e26-45e9-aac9-9b1f7aa9a2bb |  | LU | 2026 | 2
1120000097 | 868ae42a-48a4-4064-a21e-b35902cd98f1 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: b4b0b15b-7baf-4cee-9975-2e9176449e8d |  | LU | 2026 | 2
1120000098 | 88829276-80db-4919-a6c3-72e4f42f4a87 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 9494fb05-6a5c-44f8-bf6e-c5fe483add9d |  | LU | 2026 | 2
1120000099 | 8049d292-bfd3-468a-ba89-c446dfc6803b | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 3bfd5990-a735-466a-b572-18388002a171 |  | LU | 2026 | 2
1120000100 | 8e75595d-71fc-4ba9-ba8f-66e45f790905 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: c2c29c3f-5319-4cd6-bac8-73a2589128e5 |  | LU | 2026 | 2
1120000101 | 59eaba23-46cc-4b3a-bc04-25bfa32af22c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: d94df99e-8afc-42cc-a559-b0482046d852 |  | LU | 2026 | 2
1120000102 | 5230274b-16b2-483d-8657-fd4435190d13 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 20e5b016-8265-4650-a555-e08916583a13 |  | LU | 2026 | 2
1120000103 | 5230274b-16b2-483d-8657-fd4435190d13 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: a256d2d1-513a-460e-89b8-fe6fcb3a7bda |  | LU | 2026 | 2
1120000104 | 5230274b-16b2-483d-8657-fd4435190d13 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: c5ace1fa-aaab-45e4-a503-cb9b804d8a5a |  | LU | 2026 | 2
1120000105 | 71dd79d7-b55c-4b70-8604-fff2d50f34f1 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 700b5998-63b9-4cf4-9d94-ea5a7acd904b |  | LU | 2026 | 2
1120000106 | 65420298-0dd2-4e7d-aca0-3b25f97d5033 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: dba2307f-ee02-4bb6-b660-2ecbda4f7e31 |  | LU | 2026 | 2
1120000107 | 65420298-0dd2-4e7d-aca0-3b25f97d5033 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: dbbbecfb-4c8c-4c22-a1ff-fc926a71a2f9 |  | LU | 2026 | 2
1120000108 | 16272680-583a-4a1b-979d-c1a6f884900d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 2d168ea2-8caa-42eb-b69c-dac42e47005c |  | LU | 2026 | 2
1120000109 | 13a095ca-637f-41bd-8ee2-555e0be32d31 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 6a6b4ebd-0b03-405a-aab8-9bb15a7fad83 |  | LU | 2026 | 2
1120000110 | 13a095ca-637f-41bd-8ee2-555e0be32d31 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: b0a8af12-efab-4feb-b39d-34bfd78edeab |  | LU | 2026 | 2
1120000111 | 184d1fb2-c175-4be7-9515-e26f49bae50c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: e6be4e46-4b20-4be3-bda6-a25e840ee651 |  | LU | 2026 | 2
1120000112 | 1a8be819-edb2-4bec-8f70-f240db8a9cdf | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 22bff4d9-08f1-4825-80e8-327dfe31e1b8 |  | LU | 2026 | 2
1120000113 | 1a8be819-edb2-4bec-8f70-f240db8a9cdf | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: d61d38a2-4e45-405b-a269-473b7cf583e4 |  | LU | 2026 | 2
1120000114 | 25751c7c-c625-4567-b815-4cfe7e6c6e69 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 4fe688c7-f4ff-4bf9-ba96-7dbef89d9d60 |  | LU | 2026 | 2
1120000115 | 1afe05c3-1547-40d1-bf2c-8380bd41352f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 9dc49393-9fa9-4a4c-b991-a0280064fdc6 |  | LU | 2026 | 2
1120000116 | 1afe05c3-1547-40d1-bf2c-8380bd41352f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: af20cbe9-6274-4c58-b44f-36b4b76f40d5 |  | LU | 2026 | 2
1120000117 | 1197a233-3b93-40b8-abe8-d486f5aafa34 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 8a1c5891-7222-4e21-b910-95dcdfd8aec1 |  | LU | 2026 | 2
1120000118 | 044a5ad1-3ced-46f2-866a-16d28c93378e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: e6554712-44e0-474e-9b6b-ecaacdca5542 |  | LU | 2026 | 2
1120000119 | 05d7ab46-2553-4d9c-be8f-5161b4d899bc | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 1778589d-fc67-4a27-ba8a-80eec2dd8593 |  | LU | 2026 | 2
1120000120 | 05d7ab46-2553-4d9c-be8f-5161b4d899bc | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: d43bafdf-91fe-4925-92c4-dca59617919e |  | LU | 2026 | 2
1120000121 | 40ec92c2-2afe-4d8b-ab57-860989f4601d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 08b404e3-b845-4d95-a845-fda28bd0d8d2 |  | LU | 2026 | 2
1120000122 | 40ec92c2-2afe-4d8b-ab57-860989f4601d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: b78b43af-524e-4d43-8c40-30ee962b61a4 |  | LU | 2026 | 2
1120000123 | 416b7181-f6f9-46c1-b14f-30da575b5bfe | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 5033843e-473e-4441-bb2c-c3f26e062d00 |  | LU | 2026 | 2
1120000124 | 416b7181-f6f9-46c1-b14f-30da575b5bfe | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 9c892e38-b60f-4862-9d11-762ee83521d0 |  | LU | 2026 | 2
1120000125 | 2872a9a2-d8a8-416c-9bf2-f27310c15fd6 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: d5463140-fc0c-469c-9924-846295d2ba26 |  | LU | 2026 | 2
1120000126 | 2a4b09b8-6185-47e0-8b58-6431bbd2f597 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 483f9d7d-80e9-4583-a59d-da578de01b7a |  | LU | 2026 | 2
1120000127 | 2b5700c4-6167-49a1-8b91-356ffcf2cc44 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 0e6fbaa6-bddd-4d53-878d-b96453b0f971 |  | LU | 2026 | 2
1120000128 | 2b5700c4-6167-49a1-8b91-356ffcf2cc44 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: e6534008-8df4-48cf-ad50-d1ed8e0da14d |  | LU | 2026 | 2
1120000129 | 330387aa-a9b9-4bad-a21e-35f5919b1f8c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 06b2ef3d-641a-4e28-95d9-a1ba22f24ba2 |  | LU | 2026 | 2
1120000130 | 330387aa-a9b9-4bad-a21e-35f5919b1f8c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 1cb8e230-f6d2-459a-ac31-cd9a41b375dc |  | LU | 2026 | 2
1120000131 | f9c3b165-e3e5-4a1c-bdfd-31dbfa99326d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 90dcd9cb-3700-4d09-b16f-7977e5c5099f |  | LU | 2026 | 2
1120000132 | f780660b-2e33-4a5f-90df-cba27e463e8b | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 8be8de82-f38e-4430-b463-1c520d1cfa1f |  | LU | 2026 | 2
1120000133 | e84ba2f0-d2dd-49bc-a6ce-ff6616ff30f5 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 8abbe4d2-d6d2-4a0a-85e4-bf40e4592408 |  | LU | 2026 | 2
1120000134 | e84ba2f0-d2dd-49bc-a6ce-ff6616ff30f5 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: b40ab044-735d-40ce-83a2-c99708b6c030 |  | LU | 2026 | 2
1120000135 | e84ba2f0-d2dd-49bc-a6ce-ff6616ff30f5 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: cbebc24e-e258-43c5-9f00-fab3960a053a |  | LU | 2026 | 2
1120000136 | f2525204-6043-4d9d-beb7-22f31f5ce45d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 593572b1-2456-454a-912a-3549b9a47bae |  | LU | 2026 | 2
1120000137 | deaaafe6-3f4e-4e45-a48b-7a0e2d4333cf | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 069bc254-da8c-412b-8416-acd9e314db29 |  | LU | 2026 | 2
1120000138 | da37e51d-4818-4b2a-8833-332345a86fae | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 2702ea88-72ab-4c73-a694-654d4431272b |  | LU | 2026 | 2
1120000139 | da37e51d-4818-4b2a-8833-332345a86fae | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: a7f48c07-3f8b-47c9-91fa-54417eb7aaed |  | LU | 2026 | 2
1120000140 | d1e1c6b9-7b59-42a7-b67d-7927c6baf83e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 40722a50-7a98-42ec-962f-c20620e123f0 |  | LU | 2026 | 2
1120000141 | c1315c25-9277-437b-9c73-dc33ad12f705 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 69de0529-dfcf-4716-8dc7-e2012a3eb886 |  | LU | 2026 | 2
1120000142 | c787b691-22f6-4599-a686-8a283b3e1b58 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 34df7129-53e5-4ba4-8a32-8aeea929e3b3 |  | LU | 2026 | 2
1120000143 | c787b691-22f6-4599-a686-8a283b3e1b58 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: f462edc8-b09f-4c76-afc2-573df3f18661 |  | LU | 2026 | 2
1120000144 | be440b9a-aac4-4a55-af79-a9ca9c271392 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 7e2f2a1a-3773-43a8-9d56-fa14b04b6ef0 |  | LU | 2026 | 2
1120000145 | be4ce5d9-858c-4b44-b1cb-f92c8866a9df | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 02db293d-5dce-4543-afba-441ecb366942 |  | LU | 2026 | 2
1120000146 | be4ce5d9-858c-4b44-b1cb-f92c8866a9df | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: bf893033-5812-4d27-9aaa-94b77abb3a38 |  | LU | 2026 | 2
1120000147 | ac75c43a-1d93-41ae-bb90-67b69eb21c9d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 44daec8d-90c4-4c38-9019-d369feee7198 |  | LU | 2026 | 2
1120000148 | ad961985-5598-4780-9553-3caa6a2c62c7 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 1d6a6079-bbb8-4546-b4ea-0f14098e2519 |  | LU | 2026 | 2
1120000149 | ad961985-5598-4780-9553-3caa6a2c62c7 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 8774217f-1447-4785-a41a-5d0d2edc5313 |  | LU | 2026 | 2
1120000150 | b16d588f-c76a-4232-a662-bcb81951d1eb | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 8345a7f6-681f-4ddc-9e4b-0cd273300bce |  | LU | 2026 | 2
1120000151 | a8bba167-6456-4e54-899f-460abb21bf28 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: b4c73ca9-254f-4181-ba69-c9d5a55edd06 |  | LU | 2026 | 2
1120000152 | b0f70896-04f1-4f18-8fe7-7e488060422c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 0155617e-38ae-4e57-ba5b-5b78d98acc00 |  | LU | 2026 | 2
1120000153 | b0f70896-04f1-4f18-8fe7-7e488060422c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 01a19725-8b62-42a9-8626-c0ed38de3e95 |  | LU | 2026 | 2
1120000154 | b0f70896-04f1-4f18-8fe7-7e488060422c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: c611a9fc-d1c9-4910-8852-d74023838753 |  | LU | 2026 | 2
1120000155 | bd4fec66-9ef5-4631-a5ed-2304a04f20bb | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 9ebde163-889d-4f14-adbe-31a086c8fd04 |  | LU | 2026 | 2
1120000156 | bd4fec66-9ef5-4631-a5ed-2304a04f20bb | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: d0c30bda-6e59-43ae-8922-380904610087 |  | LU | 2026 | 2
1120000157 | bde5e268-1668-43c8-ba28-1915028411d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 4456aa5f-61f0-416c-9a8d-018988bdec19 |  | LU | 2026 | 2
1120000158 | bc558c78-0229-4e9c-81ad-9bc3f9326d5e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 21bd3014-dcdd-4ec2-b389-fb86068dfd0f |  | LU | 2026 | 2
1120000159 | bc558c78-0229-4e9c-81ad-9bc3f9326d5e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 728bc297-1575-420b-a33f-f3f120197b17 |  | LU | 2026 | 2
1120000160 | b82d1042-c5a1-43c3-847d-42e3ef1323b6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 2740cedd-6244-4a12-9df6-137e19fd65a1 |  | LU | 2026 | 2
1120000161 | c1e96192-ccfc-4a35-9a3f-956ca4bd0ed7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: a182c31c-0251-4af4-b060-9419ed76050c |  | LU | 2026 | 2
1120000162 | c4dddf69-bd68-499f-b9cd-f2329c56733f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 22bdf424-d053-41a7-b7f4-ba77c2bbe01a |  | LU | 2026 | 2
1120000163 | c4dddf69-bd68-499f-b9cd-f2329c56733f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: eb5d3720-1e56-42ff-a621-61a9acd53ea6 |  | LU | 2026 | 2
1120000164 | d4cd12d6-2387-4b66-84d4-c0917848a582 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 780f9ab6-ec65-47dd-a5a2-c4f85bbf24ad |  | LU | 2026 | 2
1120000165 | d4cd12d6-2387-4b66-84d4-c0917848a582 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: ac1cb0de-ae41-4663-9c75-c588ba723222 |  | LU | 2026 | 2
1120000166 | d4cd12d6-2387-4b66-84d4-c0917848a582 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: fcda0de1-9888-4641-990b-6ab5a8635f52 |  | LU | 2026 | 2
1120000167 | ef6999d8-dfdd-4c41-bcea-6bbb3a34871e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 6c2fb6d4-454f-4c99-a09f-6c12dca5d6ab |  | LU | 2026 | 2
1120000168 | ef6999d8-dfdd-4c41-bcea-6bbb3a34871e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: bdc3a909-6cee-483a-ab26-e69843e06cd6 |  | LU | 2026 | 2
1120000169 | ef6999d8-dfdd-4c41-bcea-6bbb3a34871e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: f061a51f-a3f9-45a8-a21f-0773885b217c |  | LU | 2026 | 2
1120000170 | e177849e-0aee-4454-8029-ec615094210d | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: ee6d47bc-1d70-4ed2-941b-6b1424f4cf96 |  | LU | 2026 | 2
1120000171 | 33a99f65-e15b-480d-aa0f-155fff4e752d | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 638d7f95-9a13-4ac5-996f-ca45a4482dc4 |  | LU | 2026 | 2
1120000172 | 2ef7df10-11a2-41c2-a373-df1b2120dff7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 3812d3f6-7589-4ac7-9eb8-985c1fa421b9 |  | LU | 2026 | 2
1120000173 | 3422ff06-79cd-4f04-a062-25ee9888fa33 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: b0fab020-b0f9-46d5-a661-d92ef415a3bb |  | LU | 2026 | 2
1120000174 | 2bff0f8b-b9d3-4901-a3df-c062bd703672 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2026-08-13 | Level 2 |  | Reinspection Date: 2025-08-13, Work Order ID: 219e3fbe-c0c7-4857-a602-3a1f16f49cf2 |  | LU | 2026 | 2
1120000175 | 2bff0f8b-b9d3-4901-a3df-c062bd703672 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2026-08-13 | Level 2 |  | Reinspection Date: 2025-08-13, Work Order ID: 2ed0980d-c0e3-423a-b140-a2fdeb0596fe |  | LU | 2026 | 2
1120000176 | 2bff0f8b-b9d3-4901-a3df-c062bd703672 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 46e61578-a63d-4c7c-a8e8-a05efd115ab9 |  | LU | 2026 | 2
1120000177 | 2bff0f8b-b9d3-4901-a3df-c062bd703672 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: e2b8a808-1b8e-4a4e-bc99-6815912311e6 |  | LU | 2026 | 2
1120000178 | 41981976-bf53-4d20-a4c5-32e479ebc29a | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 9466d417-8325-4fa5-86fb-a8ea2b11d4b7 |  | LU | 2026 | 2
1120000179 | 49e1829c-9a09-4e24-a8a5-8d8372026be5 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 002a8d35-a5df-481d-a1ff-867e52cd9bc9 |  | LU | 2026 | 2
1120000180 | 49e1829c-9a09-4e24-a8a5-8d8372026be5 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 03dedd12-0b41-4514-bb5c-5f85a3a4abf0 |  | LU | 2026 | 2
1120000181 | 4868a601-7e11-40c3-b65e-6244e27eaf41 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: fec60605-7865-4d1f-b571-21b863d36047 |  | LU | 2026 | 2
1120000182 | 07ff8117-9ff1-4642-bf07-c4f286b54946 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: cf4b9ae9-87e1-4620-a356-3afa9cc996dd |  | LU | 2026 | 2
1120000183 | 08217c68-054c-45dc-91c1-5b5c896effce | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: e5b91d06-5a01-4d20-a17b-9eb04507f6d8 |  | LU | 2026 | 2
1120000184 | 0cf88fec-ed5a-45bf-8c5c-eaaace7e13de | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 335dc112-cdf9-47ad-a8b5-23a5c8c2b12d |  | LU | 2026 | 2
1120000185 | 6e41f9f0-94e1-4f49-bd2b-b5fa19f28a82 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 25b9759a-4a7d-4184-9b7e-75f2132c9de1 |  | LU | 2026 | 2
1120000186 | 6e41f9f0-94e1-4f49-bd2b-b5fa19f28a82 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 663f76a0-561b-4946-a248-a7b51aa70a33 |  | LU | 2026 | 2
1120000187 | 6e41f9f0-94e1-4f49-bd2b-b5fa19f28a82 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: a4058d2d-2d1d-472a-9e94-de31d6f67d12 |  | LU | 2026 | 2
1120000188 | 4cc36078-4394-455c-9ffb-73b85818cb40 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: aca9d62b-13e7-4830-bae1-858b762bfca8 |  | LU | 2026 | 2
1120000189 | 5e9127ca-57e2-40bd-87d9-161c3784b7e8 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 27bd8c4d-0f87-4efd-9789-28e1508fffe9 |  | LU | 2026 | 2
1120000190 | 5e9127ca-57e2-40bd-87d9-161c3784b7e8 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 923e00b7-dbb6-41e1-a390-1f1599720cc5 |  | LU | 2026 | 2
1120000191 | 8f0d1bf9-5fd3-437d-bfee-ae886db9695f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 34522b53-5682-447f-8aa7-771fbfa8abac |  | LU | 2026 | 2
1120000192 | 8f0d1bf9-5fd3-437d-bfee-ae886db9695f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 3f6388d8-5fbc-4bfa-80cd-fd55bfddad6a |  | LU | 2026 | 2
1120000193 | 8f0d1bf9-5fd3-437d-bfee-ae886db9695f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 7515ae92-819f-4fee-aa88-a8c2d84ba982 |  | LU | 2026 | 2
1120000194 | 8f0d1bf9-5fd3-437d-bfee-ae886db9695f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: ba010afa-2813-42aa-84b7-d2c0b15db5c6 |  | LU | 2026 | 2
1120000195 | 83c5c5ac-bc92-4146-8963-efb6ebb8ecf6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: b5c08c4a-df8f-4857-8e58-09dee50a82c3 |  | LU | 2026 | 2
1120000196 | 83c5c5ac-bc92-4146-8963-efb6ebb8ecf6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: f1b36091-394e-4f73-9319-0ba8a94dfa52 |  | LU | 2026 | 2
1120000197 | 84e2e7ee-f290-4d6e-baf3-7fd1ce1e539a | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: bbdf462b-4863-48b5-ae6a-a5e3bd619420 |  | LU | 2026 | 2
1120000198 | 8520a8f1-05e5-441c-beb6-fbed25c7dd8c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 4b4217d1-2100-415f-a153-e2c13fa09ff8 |  | LU | 2026 | 2
1120000199 | 886b2dee-9710-4ef4-9c73-5f1e04e754de | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: a644ca54-c3e7-411d-8933-11c04dc85c3a |  | LU | 2026 | 2
1120000200 | 886b2dee-9710-4ef4-9c73-5f1e04e754de | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: a9bf6ea2-64ca-49d1-900d-cbb48f474aaf |  | LU | 2026 | 2
1120000201 | 7d6b8a03-1d1c-4b42-8feb-916c5088490e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 09ddbd36-0539-440e-abef-d26685f188bc |  | LU | 2026 | 2
1120000202 | 7ef5bee4-e532-48c1-b75e-8788fbfa11d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 292c0880-bcaf-4984-acda-5b04d2d0ef4d |  | LU | 2026 | 2
1120000203 | 7ef5bee4-e532-48c1-b75e-8788fbfa11d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 4db7dcbf-9775-4062-be82-ab58c445647d |  | LU | 2026 | 2
1120000204 | 7ef5bee4-e532-48c1-b75e-8788fbfa11d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 98883d55-c89d-48b8-b4c1-7291c50edeec |  | LU | 2026 | 2
1120000205 | 7ef5bee4-e532-48c1-b75e-8788fbfa11d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: a9ebf51f-ea27-41c0-8e16-ba96d818f042 |  | LU | 2026 | 2
1120000206 | 6faeffe7-fbf6-4f02-8a58-2327b1a56674 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: b6da3796-0941-4188-8ade-59fc9a1efad6 |  | LU | 2026 | 2
1120000207 | 67353876-3cb5-432a-90c2-5aaf3a8ef153 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: fe5033e6-f0a1-46db-b98b-3f4f2833852b |  | LU | 2026 | 2
1120000208 | 08cbc006-1d9a-4f7d-b474-6dac6ef08004 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 59bab7ee-1696-4d27-be8b-cbe25445c7cf |  | LU | 2026 | 2
1120000209 | 08cbc006-1d9a-4f7d-b474-6dac6ef08004 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: e1f7f440-5984-4199-84d7-684d1063e8c6 |  | LU | 2026 | 2
1120000210 | 2008c446-ca38-462c-84e4-69f0e0087104 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 8f1e84ed-1fbc-493e-b110-6064dc96fa34 |  | LU | 2026 | 2
1120000211 | 41e55f1f-5762-40d1-9f6e-9c632c4b85de | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 26958c82-764e-4c15-a356-4b1148223a37 |  | LU | 2026 | 2
1120000212 | d5213ff3-1a3c-4066-9758-682f2151f6d9 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: d7d7b3c1-7796-48c3-8e5f-bbd8e0e53c23 |  | LU | 2026 | 2
1120000213 | b320d06b-486f-40fb-90cf-f84c5cfaef86 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 68c1ebd9-6bb8-41a0-acc7-0252947e1d3e |  | LU | 2026 | 2
1120000214 | dac0e9f8-df3e-4c9d-a582-cad1d98af526 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: b3db4f8b-3268-490a-b69d-c3ed3310c07e |  | LU | 2026 | 2
1120000215 | dac0e9f8-df3e-4c9d-a582-cad1d98af526 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: f31b648e-0654-4a9b-98e3-3838c4c0f75d |  | LU | 2026 | 2
1120000216 | f0b0c09b-f539-4ba1-981f-f83d222f708d | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 6a424b28-dc23-4a5f-9164-bed1795081e4 |  | LU | 2026 | 2
1120000217 | f0b0c09b-f539-4ba1-981f-f83d222f708d | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: c9eab434-58dd-4747-8a4f-c0e979bb6de1 |  | LU | 2026 | 2
1120000218 | fcad9e4a-c877-4744-9e0f-c266c322ebbf | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: ed917354-ebcd-4b33-bebf-61c34bb8dbcb |  | LU | 2026 | 2
1120000219 | 21bbbbec-f506-4184-927a-094144aedac1 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 245a2135-bd05-40d4-9904-9857e106ad41 |  | LU | 2026 | 2
1120000220 | 7850f946-53ea-45fd-a4f1-a2ea94ee0f35 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 0b061c8c-700f-4e16-8649-c09fb4e77eec |  | LU | 2026 | 2
1120000221 | 7850f946-53ea-45fd-a4f1-a2ea94ee0f35 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: f996ee17-4612-4bf5-b471-d69e4799c1ec |  | LU | 2026 | 2
1120000222 | 98050b19-c725-472a-8317-fa9f7ecb3033 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: d87832c8-0c23-43ff-9366-26f3aa6a166e |  | LU | 2026 | 2
1120000223 | 87e74c20-c711-4516-83e6-4c3c6bbc4120 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 155c2369-b2f0-4921-bec3-5eceff0bd170 |  | LU | 2026 | 2
1120000224 | 87e74c20-c711-4516-83e6-4c3c6bbc4120 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: fc1fa41e-be03-4da0-9459-f8895dc821f5 |  | LU | 2026 | 2
1120000225 | 6c022555-c90b-45f0-815a-bd980c43dee7 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 6aebcd97-4987-4b6d-8075-99c57389b841 |  | LU | 2026 | 2
1120000226 | 6c022555-c90b-45f0-815a-bd980c43dee7 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: c9975744-2d51-46a6-be9f-0877e00070ce |  | LU | 2026 | 2
1120000227 | 35889e6b-9914-4c14-942b-e00bc02332b1 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 30c20277-47de-46bc-addb-acef72a77fc8 |  | LU | 2026 | 2
1120000228 | 35889e6b-9914-4c14-942b-e00bc02332b1 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: 8a3db67c-e067-4e28-80ff-84193cf90f7d |  | LU | 2026 | 2
1120000229 | f8984285-586e-4f1e-8450-3102d79d16e9 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 767b4eba-c6d8-47e9-b1c7-2311804de385 |  | LU | 2026 | 2
1120000230 | de0f106f-604c-4fdd-9373-b51552127767 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 7f134f48-527a-435e-959b-7c59b5b87d93 |  | LU | 2026 | 2
1120000231 | d6d0fd2b-718b-4db4-a45d-659531f1d04d | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 238d8094-85d0-4180-a435-16fdc0a88fdd |  | LU | 2026 | 2
1120000232 | cd0c772e-29e1-4e2e-92ee-8b6284a601e4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: b28bb2ed-e181-485c-94e6-4af47ea18acd |  | LU | 2026 | 2
1120000233 | cf56a0df-da17-4574-ab46-21f6310b5a69 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: abf67cda-60bd-4666-8eb6-ff54b5bc8089 |  | LU | 2026 | 2
1120000234 | bdc9a767-340b-4f74-8fdd-0b92c2b98de4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 40201664-c942-4d5c-a73f-377c97f4619f |  | LU | 2026 | 2
1120000235 | bc2a007b-d6da-4a47-98a1-ab45a905df3d | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 2ad7ea9e-e6c0-472e-b987-f85b1c0f92f9 |  | LU | 2026 | 2
1120000236 | bc2a007b-d6da-4a47-98a1-ab45a905df3d | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 6f0bb877-8ec0-4d7d-b5c3-0dfbf64a5763 |  | LU | 2026 | 2
1120000237 | ceb04037-ff1c-4167-94f2-59107a7a2a81 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 39079d4c-3b63-40c5-8abd-3ec743a529f5 |  | LU | 2026 | 2
1120000238 | f8e06d5c-2926-4613-bb68-c7a79f821a63 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 769763fd-3a2d-473f-a7e5-477a42efb826 |  | LU | 2026 | 2
1120000239 | 06a013fd-084a-473f-bcd1-c61f4139e66a | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 633afe6f-eb7f-4523-8809-1163596a5696 |  | LU | 2026 | 2
1120000240 | 61ddce5d-f641-4843-9c18-213e6a623c79 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: af6881ce-eb5c-4240-97e1-758346b18d34 |  | LU | 2026 | 2
1120000241 | 644f564c-0fd6-46cb-b7e9-46fb3fc31e4f | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: bd6a83bc-ddba-49a4-a7f8-df96afd67828 |  | LU | 2026 | 2
1120000242 | 819a5393-fa64-43f5-8903-6753f22f304d | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 4ec8775e-12cc-48e9-8e61-c700200eb06a |  | LU | 2026 | 2
1120000243 | 8f16b385-c43d-4e58-bda5-2bd49ea08dd4 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 862e7d2e-50f6-4d8b-84c0-ae326d4e974d |  | LU | 2026 | 2
1120000244 | 800c9611-3a30-4152-9e8a-189b02ce9dd2 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 42dbd52b-6bad-4688-881c-800af33356a0 |  | LU | 2026 | 2
1120000245 | 800c9611-3a30-4152-9e8a-189b02ce9dd2 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 512ad22d-e1dc-48d8-abcc-ce3ef0385d23 |  | LU | 2026 | 2
1120000246 | 84d3640b-c4d3-4641-86a4-f3af1768108d | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 11a322b6-eb11-43d8-8463-2b44a502fa61 |  | LU | 2026 | 2
1120000247 | 84d3640b-c4d3-4641-86a4-f3af1768108d | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: ac171219-f133-4e9f-b5b9-d11d4ad080a1 |  | LU | 2026 | 2
1120000248 | 79058894-c55e-4443-aaa7-326f6d91c561 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: e5f190e9-5a2a-4078-bd72-ef82d6719f71 |  | LU | 2026 | 2
1120000249 | 69279c48-82e2-415d-8545-a25d846577b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-11 |  | 2026-08-11 | Level 2 |  | Reinspection Date: 2025-08-11, Work Order ID: 2e4b130a-66b3-4d77-b98a-695af16b932f |  | LU | 2026 | 2
1120000250 | 2477a9df-9b11-4153-a00f-3208085627c7 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 13590942-0200-45ea-bca3-37a339bd1ede |  | LU | 2026 | 2
1120000251 | 3fb73251-51f0-45a2-8e6e-d48f3ebcef07 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 207fe6f7-2e38-426b-b6aa-1daa32fd5f0d |  | LU | 2026 | 2
1120000252 | 3fb73251-51f0-45a2-8e6e-d48f3ebcef07 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: dbaf79a9-5e8d-4c70-8717-f0043d90ffcd |  | LU | 2026 | 2
1120000253 | b9f08bc8-e7a0-4ca0-b188-777f2df05a3f | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 92c389d6-c779-4126-b08a-8697de042d27 |  | LU | 2026 | 2
1120000254 | cb973d42-3e60-45ee-accc-312d24f06de5 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: e82a4088-9794-4965-8a92-3fb900b29278 |  | LU | 2026 | 2
1120000255 | d0e0a3c9-7e4a-4bd0-b9b0-d20eddf79b1a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: c55d59a5-0e37-495e-a07a-5c2cec7060a4 |  | LU | 2026 | 2
1120000256 | ea54c31d-d1f7-4234-ae73-2ff8d7245d1c | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 531e881f-dc58-4d65-931e-6ed416adc941 |  | LU | 2026 | 2
1120000257 | ea54c31d-d1f7-4234-ae73-2ff8d7245d1c | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: e158d2fe-385a-4d9f-9d2a-8c279624efce |  | LU | 2026 | 2
1120000258 | df8e84bf-c492-4aa1-8536-650d68f61790 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 49d1364e-aa8b-42e5-9736-c984a3320d7f |  | LU | 2026 | 2
1120000259 | df8e84bf-c492-4aa1-8536-650d68f61790 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: a0aafa8a-8c84-44d7-b790-ad07b8e81c7c |  | LU | 2026 | 2
1120000260 | ff1468ce-b832-4fb0-99ac-0a2069d45d19 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 1b060e8a-4309-458b-b875-54530655eedb |  | LU | 2026 | 2
1120000261 | ff1468ce-b832-4fb0-99ac-0a2069d45d19 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: ece0cb49-8407-4b4e-9dd4-6c30e1c26093 |  | LU | 2026 | 2
1120000262 | 4c2e0bf4-3835-44e8-8117-e462e3864ac0 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 5eae247b-906f-42c0-8ca8-57e3fa5e4d9d |  | LU | 2026 | 2
1120000263 | 4c2e0bf4-3835-44e8-8117-e462e3864ac0 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: ec9bfe2d-94f6-41d1-a43b-c20eb0353d21 |  | LU | 2026 | 2
1120000264 | 23515b62-48c2-4556-bd45-12848900f152 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 1cedc43b-c2ad-458f-9a86-139622f34022 |  | LU | 2026 | 2
1120000265 | 1aa7e76a-7b2b-4e9b-bead-9a612a31f2a5 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 105cb5fe-7993-4ed9-94dd-a60e76033962 |  | LU | 2026 | 2
1120000266 | 1aa7e76a-7b2b-4e9b-bead-9a612a31f2a5 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 1b99a5df-d715-4f36-b5b8-f8c0a4948ad8 |  | LU | 2026 | 2
1120000267 | 6124871b-8728-4cfc-9f4d-1aab5ebbd569 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 12f492cf-8b75-4388-b137-23b707ed8d50 |  | LU | 2026 | 2
1120000268 | 613977df-c2f9-4bed-b8b5-b1f39f1feaf9 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 6b39f7ef-6b06-4797-9a30-d6f1ce2cafee |  | LU | 2026 | 2
1120000269 | 555534b5-c902-4af1-a764-1796fa2b9983 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 755b5689-c76e-4d9a-b83b-7aa809a21b1b |  | LU | 2026 | 2
1120000270 | 555534b5-c902-4af1-a764-1796fa2b9983 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: cd6cee5b-5738-4a79-a153-104ba63ba4e8 |  | LU | 2026 | 2
1120000271 | 555534b5-c902-4af1-a764-1796fa2b9983 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: cdc5b2a2-8b6c-485c-8393-ffbc2e35f9de |  | LU | 2026 | 2
1120000272 | 94413025-69b3-4e71-93f9-54326383cd81 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 8f46fef0-5835-47fd-8770-1891338613e1 |  | LU | 2026 | 2
1120000273 | 991677c6-91a5-429a-a254-495da23ea4a1 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 2025-08-07 |  | 2030-08-06 | Level 3 |  | Reinspection Date: 2025-08-07, Work Order ID: 1f8b6f71-3fdd-460e-9c26-be201589c1e3 |  | LU | 2026 | 2
1120000274 | 952d2ed9-1c96-4b4b-b146-fdd45464488d | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 3dce424a-d142-474f-8832-0a2146baf3af |  | LU | 2026 | 2
1120000275 | 952d2ed9-1c96-4b4b-b146-fdd45464488d | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 77314400-f883-4f85-ba19-93eb2c93cd63 |  | LU | 2026 | 2
1120000276 | 952d2ed9-1c96-4b4b-b146-fdd45464488d | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: b0edbfe9-4710-4a12-892e-a8ac70d8cc5e |  | LU | 2026 | 2
1120000277 | 952d2ed9-1c96-4b4b-b146-fdd45464488d | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: d153df49-e453-448e-ab14-f23401168667 |  | LU | 2026 | 2
1120000278 | 8c252ad4-62f5-41f3-bb8e-682b90b9fd36 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: 18d528dd-54dd-4629-8f3e-ae8acc748159 |  | LU | 2026 | 2
1120000279 | 5aeadcfd-8379-468e-8033-650626e03812 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 5035aef3-a2e7-455f-b518-eccbf60fcffe |  | LU | 2026 | 2
1120000280 | 5aeadcfd-8379-468e-8033-650626e03812 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: 58145df4-d57e-4ff5-85d8-e928a58b31cf |  | LU | 2026 | 2
1120000281 | 234da9c5-9676-43b4-bf32-4838687244a2 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-08 |  | 2030-08-07 | Level 3 |  | Reinspection Date: 2025-08-08, Work Order ID: 402b09b0-a520-4255-b3c1-bc5484d3ef25 |  | LU | 2026 | 2
1120000282 | 3a775075-343a-4a3b-84db-d95ebb7557ef | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 8349eb59-e62d-4428-8f0f-82cfcb9f2835 |  | LU | 2026 | 2
1120000283 | 360b7775-9160-435a-8abd-5af6ea5c119e | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: c7970265-0b62-41eb-ab5f-a45a0ebdf143 |  | LU | 2026 | 2
1120000284 | 31033ad3-009b-4c48-b627-05c471f6bd1c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 7a5471da-f7f8-452c-a503-afaf2c6e6a32 |  | LU | 2026 | 2
1120000285 | f58e93ff-43e9-40de-abf1-97d8d3d29c4c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-05 |  | 2030-08-04 | Level 3 |  | Reinspection Date: 2025-08-05, Work Order ID: f5f7d1f7-4736-4d97-a076-e5448879077f |  | LU | 2026 | 2
1120000286 | f9e9c534-04ad-4383-955d-0f38008c046a | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: ad99ce3a-3117-484f-9a56-fc93e966e222 |  | LU | 2026 | 2
1120000287 | e0505489-268f-4d4f-873f-53fd9e3936bb | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: f80bd25d-05e7-44da-8726-ed2b08e8e70b |  | LU | 2026 | 2
1120000288 | ece636f7-b196-4efd-9d79-9480a29b8f58 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 09b4bd26-24fd-4bbd-80e4-379464ab08bd |  | LU | 2026 | 2
1120000289 | ece636f7-b196-4efd-9d79-9480a29b8f58 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 33b74232-0359-44bf-87eb-fedb3c314c5b |  | LU | 2026 | 2
1120000290 | f1fdadd1-9560-4662-a018-1c2397ca079f | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: a02156e7-753e-4311-89a1-17922467d17c |  | LU | 2026 | 2
1120000291 | 30836850-7b60-4a98-b4ea-e6974bb22e0a | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 97fe0624-dbcf-4c72-aa94-0945bc2c0838 |  | LU | 2026 | 2
1120000292 | 2edeedf2-f282-45f9-bdce-ea4847c6b194 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-11 |  | 2026-08-11 | Level 2 |  | Reinspection Date: 2025-08-11, Work Order ID: fa6a880d-5f74-471f-ad7e-3677c2f7443d |  | LU | 2026 | 2
1120000293 | 2de0239c-744b-4200-92e5-a3117a3127db | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 37da252a-8588-44d2-95b3-03b2f1d13de5 |  | LU | 2026 | 2
1120000294 | 2de0239c-744b-4200-92e5-a3117a3127db | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: b4eefc0a-167a-4924-be6e-f7eec768b556 |  | LU | 2026 | 2
1120000295 | 254b623d-3104-4a9c-b851-130e8a6a62b8 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 92d9ec8d-230b-41e4-9d43-52cfa4d3f2d6 |  | LU | 2026 | 2
1120000296 | 1eb2c19b-2665-484d-9894-25d2791fd21a | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: d7eee044-3293-48db-a12a-210178376f2d |  | LU | 2026 | 2
1120000297 | 0f9e27c4-65ae-44cb-8584-21ca3ef26874 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: b16842d5-980a-4324-b68b-920b254eba9f |  | LU | 2026 | 2
1120000298 | 0f9e27c4-65ae-44cb-8584-21ca3ef26874 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: bac6b83d-7075-4ee3-be78-586b71d23f0b |  | LU | 2026 | 2
1120000299 | 0f9e27c4-65ae-44cb-8584-21ca3ef26874 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: dfe565c0-e47c-443f-94f3-bb0809b9a02b |  | LU | 2026 | 2
1120000300 | 5d19a928-079f-4b42-b7be-59e829b22412 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: f17331bf-850a-48a8-b216-479a087ddfe4 |  | LU | 2026 | 2
1120000301 | 5d3be5f0-9e2a-4449-b1d9-39694f0a258b | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-30 |  | 2026-07-30 | Level 2 |  | Reinspection Date: 2025-07-30, Work Order ID: d2696450-4daa-4ab2-a38e-ebe20da5378a |  | LU | 2026 | 2
1120000302 | 9d49a92e-d14c-4560-b073-77e9f1679f4a | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-08-04 |  | 2030-08-03 | Level 3 |  | Reinspection Date: 2025-08-04, Work Order ID: 1113ab74-783f-4e5f-a4bb-db5586424e75 |  | LU | 2026 | 2
1120000303 | 86acb40e-bdc3-4f17-8251-fb28a2b0975f | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: ea2544e6-6da6-4439-b334-ab9733843ef5 |  | LU | 2026 | 2
1120000304 | 881b6403-a267-431e-8d9d-1cf334681590 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: c5dd7a9f-14e6-4a14-9556-e8508002e9dc |  | LU | 2026 | 2
1120000305 | 1250c82b-0f8c-433c-92b2-dcfc65479d34 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 576e55e5-32ef-4fa4-9efd-f3dbc31c299c |  | LU | 2026 | 2
1120000306 | 1250c82b-0f8c-433c-92b2-dcfc65479d34 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 9f5ebec5-d238-4677-b6e5-c084714a62d1 |  | LU | 2026 | 2
1120000307 | 1250c82b-0f8c-433c-92b2-dcfc65479d34 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: c7c1c414-05be-4752-866f-27767bfa7a4f |  | LU | 2026 | 2
1120000308 | 4661651b-c17e-4438-b6b5-c79391e7712e | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: cd3a7fc8-f03e-4995-81fd-adadf6bddadb |  | LU | 2026 | 2
1120000309 | e5944243-89df-4e03-b71e-5e86fa8407f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 300bd60e-5340-474c-9cf6-fd0f1ba75f52 |  | LU | 2026 | 2
1120000310 | e5944243-89df-4e03-b71e-5e86fa8407f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: b9f5ca6b-ce85-4ab3-92cb-58bde7d75f74 |  | LU | 2026 | 2
1120000311 | a32495ad-d8c0-4f63-8a88-7db0995255e1 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 69754439-0c85-4a69-8914-740802af9e4a |  | LU | 2026 | 2
1120000312 | a32495ad-d8c0-4f63-8a88-7db0995255e1 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: aba5bf9a-528d-43d1-8518-f7fb47ee2789 |  | LU | 2026 | 2
1120000313 | fc33d93a-7305-4afd-b625-80e3d645144b | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 2025-08-11 |  | 2026-08-11 | Level 2 |  | Reinspection Date: 2025-08-11, Work Order ID: de1b099c-4585-4609-999f-82b35794a76e |  | LU | 2026 | 2
1120000314 | 44b62822-5bb0-473d-a2cd-d40f55fc4652 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: cfee4e67-f332-4374-b59f-0ffbcde36659 |  | LU | 2026 | 2
1120000315 | 4adccfab-42db-4b83-bafe-d82969335ef8 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 582e3741-4c3b-4b3f-b47f-2902006d2273 |  | LU | 2026 | 2
1120000316 | 4adccfab-42db-4b83-bafe-d82969335ef8 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: d9906fcb-7a18-43e2-8707-f55819dba313 |  | LU | 2026 | 2
1120000317 | 4c4a90ca-284a-4f26-8ef0-c5872100f298 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 02a25f9e-c435-4423-93b3-3d067f47b279 |  | LU | 2026 | 2
1120000318 | 0c27489e-4b6b-4ebc-a705-7a73e40e43da | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: ad1cacb0-9f9c-4c70-8afd-ecdb93697e92 |  | LU | 2026 | 2
1120000319 | 234d542b-2efe-47e0-afcc-4eb8a2b75639 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-08-11 |  | 2026-08-11 | Level 2 |  | Reinspection Date: 2025-08-11, Work Order ID: 6f386919-0b49-4a8c-aea5-fe18306b4cc3 |  | LU | 2026 | 2
1120000320 | 18d94671-f86f-4950-8f33-0f428281bcea | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 707d42ba-1c88-45bb-9546-00cff3956d67 |  | LU | 2026 | 2
1120000321 | 18d94671-f86f-4950-8f33-0f428281bcea | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 776ea007-7561-4fab-a7c4-3942b7e12c8e |  | LU | 2026 | 2
1120000322 | 18d94671-f86f-4950-8f33-0f428281bcea | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: a29504dc-f054-46d2-be7b-96428220422e |  | LU | 2026 | 2
1120000323 | 145ef01b-6e14-47e1-85c6-663034b8b02d | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 527b93b9-9390-4bf1-b27f-0f5eb8218216 |  | LU | 2026 | 2
1120000324 | 145ef01b-6e14-47e1-85c6-663034b8b02d | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: beb3dad4-c155-4608-b9e2-72f13febcb7e |  | LU | 2026 | 2
1120000325 | 74428a5d-f045-449c-8107-5242dc2c80d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 15e85d50-f8f8-4fcf-83ec-3f7dcdeb5b9b |  | LU | 2026 | 2
1120000326 | 74428a5d-f045-449c-8107-5242dc2c80d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 32e02a66-4c37-42ce-a065-fd6a6a7226c6 |  | LU | 2026 | 2
1120000327 | 8ba8eba4-dea1-419a-aa6c-c24644ced5d8 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 6331f285-68fe-4ac6-aeda-2ca84d948519 |  | LU | 2026 | 2
1120000328 | 62a5cb90-d3b1-413b-be86-8b8d736caa62 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 2022-10-21 |  | 2027-10-20 |  |  |  |  | LU | 2026 | 2
1120000329 | 64e3c616-c21b-4fef-b487-d66573da87a8 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 1f13c1c5-226f-4260-98a8-88979051d8bf |  | LU | 2026 | 2
1120000330 | 64e3c616-c21b-4fef-b487-d66573da87a8 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: afdeaae0-5158-47a8-8939-8d24b29acddc |  | LU | 2026 | 2
1120000331 | 5a092bd0-5fe3-4add-a900-de0b55d9e757 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | 2025-04-02 |  | 2030-04-01 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 5cb50c8d-1276-40a6-8119-feed0e442895 |  | LU | 2026 | 2
1120000332 | b580f6fb-4d7d-4a00-8e76-2dc6dec1f0cc | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 6568587b-3bce-46c0-bd2f-c0f06d975b88 |  | LU | 2026 | 2
1120000333 | be0f7b5e-f429-4d70-a727-33e874884c77 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-08-13 |  | 2030-08-12 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: b990e71f-95b1-4e0c-83da-5279345897e6 |  | LU | 2026 | 2
1120000334 | a651bed1-ac0a-4895-a893-f194f8cf0e7c | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 3b221bdd-ab4d-4b38-9a41-9af4f411affd |  | LU | 2026 | 2
1120000335 | f6ddd8d7-d754-4b0d-99aa-b3dd9edb3233 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: fc3c2a41-393e-43a8-8d2a-f5807a08baed |  | LU | 2026 | 2
1120000336 | 741e0979-0612-4b42-b0c1-3da06bee2f03 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: d27fe783-224a-4715-afe4-258693bddce8 |  | LU | 2026 | 2
1120000337 | 0494010c-daae-4729-a850-a35a2c1d7bf0 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 2641d4eb-b163-41ae-bc98-0bcb7991a69a |  | LU | 2026 | 2
1120000338 | 0494010c-daae-4729-a850-a35a2c1d7bf0 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 743ecc23-171f-4d63-b27d-9ef780d7397c |  | LU | 2026 | 2
1120000339 | 4cbb4c68-141f-48bc-8438-ed9b50b45e48 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 6809013d-f312-49b7-8508-ed2e8db7afa1 |  | LU | 2026 | 2
1120000340 | 3a9ca1cc-0b50-4fa4-8f60-cc7e0ff125d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2021-08-19 | Level 2 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 54fd9edb-ecca-4d85-abb5-4e309fddb309 |  | LU | 2026 | 2
1120000341 | 4a98a717-fa00-47b0-953e-103f8ebf9e61 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 9afd87df-993f-4490-848b-1a229c82bd78 |  | LU | 2026 | 2
1120000342 | 4a98a717-fa00-47b0-953e-103f8ebf9e61 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: e9684bf5-712f-48e9-b53e-3b52343450df |  | LU | 2026 | 2
1120000343 | 15f88cfe-98a2-4347-b382-b9d5ac39ed71 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: b7ee37f3-ad7c-47f1-8783-de2cb4308610 |  | LU | 2026 | 2
1120000344 | 5a7f204a-d655-47fd-9bd9-591581c86fd7 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 2349aaae-f42f-47f5-9e21-0c98ffa0ab9c |  | LU | 2026 | 2
1120000345 | 5a7f204a-d655-47fd-9bd9-591581c86fd7 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 59c10aab-fcf6-4198-a62c-a7981183d283 |  | LU | 2026 | 2
1120000346 | f1fae96d-ce3b-4d3e-ab67-3707b04f8d08 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 1f67133b-b0b1-4ac2-b707-c2ea1a92dd45 |  | LU | 2026 | 2
1120000347 | db7d20d8-4cea-4e1e-8138-c49a4fee7588 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: dde02a54-16f5-4beb-a0bb-a6e2f14e4059 |  | LU | 2026 | 2
1120000348 | ebe8b2fa-6eb5-456c-899b-2a6a8114f42c | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: ab28216e-0a56-4fe7-807b-2ce7a6132897 |  | LU | 2026 | 2
1120000349 | b27c5259-820f-41a4-93af-6913a0a526c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: e3bbd432-aa77-4cba-9bb1-4f0e4cd22e62 |  | LU | 2026 | 2
1120000350 | c30faa27-8ae1-4de2-af9f-b67afde00e26 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 7e982cb8-491d-4c78-881b-0207d7556558 |  | LU | 2026 | 2
1120000351 | f82210fb-ebce-4645-af4f-3f7f7ddc2a56 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 006c8cd1-fac1-493d-a58f-1ac5281debbf |  | LU | 2026 | 2
1120000352 | 59e29a5d-f2ba-4a50-9151-c044cec50d1d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 11903071-46ef-4d99-9a97-63e17522f99b |  | LU | 2026 | 2
1120000353 | 59e29a5d-f2ba-4a50-9151-c044cec50d1d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: c984d31a-e1e7-47d4-a6a8-bedbe59fb16c |  | LU | 2026 | 2
1120000354 | 989c7a10-7931-4a49-9475-21e21bf8bfb8 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 36f12645-3067-4b47-a855-70863584466c |  | LU | 2026 | 2
1120000355 | 989c7a10-7931-4a49-9475-21e21bf8bfb8 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: bd07c10f-0a68-479e-85a8-d1a081929f73 |  | LU | 2026 | 2
1120000356 | 16144fc7-3169-4de1-bd32-c182ad4ba4bd | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 8ce369e4-34dd-4ea9-aae1-776a6b720b64 |  | LU | 2026 | 2
1120000357 | 07235cd7-1ebf-4aad-930a-1e7096d46c02 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 8dc760ba-763f-440f-8255-8269d4629375 |  | LU | 2026 | 2
1120000358 | 07235cd7-1ebf-4aad-930a-1e7096d46c02 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 98d11738-f3ad-434d-8d1d-54a36803a045 |  | LU | 2026 | 2
1120000359 | 9547cb61-fbb0-4e10-91c1-5c65b8ee506d | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: 3425c193-4f09-4ca2-af29-41620d13cfb9 |  | LU | 2026 | 2
1120000360 | ca8e5df8-1194-4a42-b30d-f53f151aff6f | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 9dbe0799-1c1b-48ef-9391-a2100856f2f7 |  | LU | 2026 | 2
1120000361 | b5cc8584-f854-406f-a34a-a08cba154f0d | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2025-08-14 |  | 2026-08-14 | Level 2 |  | Reinspection Date: 2025-12-09, Work Order ID: d9059ec2-0303-4d5f-b339-18a76ac76a63 |  | LU | 2026 | 2
1120000362 | e38f98ce-c29b-4852-ab5e-44db2d3cd15c | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 487ab9be-c05a-4104-8975-4977dccd7817 |  | LU | 2026 | 2
1120000363 | 8c8d7d2c-5544-4267-9b09-721cbf89b861 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 590459df-a7e8-44d7-9779-75996ef49595 |  | LU | 2026 | 2
1120000364 | 0e3aaf35-1169-4adc-8167-c7d2a02aa6cc | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 40c4f633-2737-4216-9d14-c5ab151b6412 |  | LU | 2026 | 2
1120000365 | 0e3aaf35-1169-4adc-8167-c7d2a02aa6cc | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 |  | 2025-08-11 |  | 2030-08-10 | Level 3 |  | Reinspection Date: 2025-08-11, Work Order ID: 5a2f7df0-0371-49d7-9c8e-e2e580e61c30 |  | LU | 2026 | 2
1120000366 | 2080ab6e-687d-4b58-9524-379ac87453fa | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: d1728ac3-a253-4a51-a15b-ed9912aa6dc0 |  | LU | 2026 | 2
1120000367 | f7ad9557-4ba2-4382-ace6-6403f5529feb | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | 2024-06-14 |  | 2029-06-13 | Level 3 |  | Reinspection Date: 2024-06-14, Work Order ID: 7d4d7c1f-24e2-4e9d-a951-e7686d8f8435 |  | LU | 2026 | 2
1120000368 | fd700f41-28fb-4c6f-8b31-b591acc5ad9c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: 62a9bdad-f914-4e13-97d7-28558c32cc75 |  | LU | 2026 | 2
1120000369 | fd700f41-28fb-4c6f-8b31-b591acc5ad9c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: eb474ac3-1449-4f71-9b87-510554cbd130 |  | LU | 2026 | 2
1120000370 | 18350311-5e81-4e29-bd87-9ead83abf1a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 2025-03-07 |  | 2030-03-06 | Level 3 |  | Reinspection Date: 2025-03-07, Work Order ID: a354c1ad-b7be-4d12-9078-0e987d523083 |  | LU | 2026 | 2
1120000371 | 112f9edf-eb31-4afd-acbb-d12436d157cd | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 2ab45452-0210-42bd-8a61-028e35c31f46 |  | LU | 2026 | 2
1120000372 | 2a20769f-6e2d-4769-9b07-7c99ad1db00a | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 2025-07-31 |  | 2030-07-30 | Level 3 |  | Reinspection Date: 2025-07-31, Work Order ID: 109d1d8e-f240-414c-8b77-2e3385cdf8db |  | LU | 2026 | 2
1120000373 | 5eef24ed-730c-4ca0-94b9-731f8346d860 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: 473efdeb-c625-4437-ac03-fceda996cb83 |  | LU | 2026 | 2
1120000374 | f15a3089-e4e6-4d85-bae2-bcf947342c00 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: 6c206d96-fbb6-47fb-9b73-fd13d87b9878 |  | LU | 2026 | 2
1120000375 | 6c2b5f10-1d7f-436e-9ee6-f767876eec41 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: f496d764-c912-447f-a220-dda4be0440dd |  | LU | 2026 | 2
1120000376 | 0ccc8acf-3476-481d-b528-09cd4fc07d15 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 3da27a52-04cc-4776-bff5-22b83c99b98f |  | LU | 2026 | 2
1120000377 | 0ccc8acf-3476-481d-b528-09cd4fc07d15 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 570d00be-4481-4885-aabe-216ed3f1bc10 |  | LU | 2026 | 2
1120000378 | 50b39ec5-fa76-4bb5-8d7a-58a9094d7e18 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: abd90119-fcc0-446f-9a45-2934eabb6c84 |  | LU | 2026 | 2
1120000379 | ce5b4ac8-e431-46f8-886a-0c8ad53508bb | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 97a665b3-250a-4a90-9f59-edb083e886a7 |  | LU | 2026 | 2
1120000380 | e86e8a30-171f-4e1f-ae0c-b9aadabafecb | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-15 |  | 2030-05-14 | Level 3 |  | Reinspection Date: 2025-05-15, Work Order ID: cffe1888-6dab-475b-a00a-9f44e32c3fff |  | LU | 2026 | 2
1120000381 | b72c1dca-54d4-4289-987c-a3452ebd5569 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-23 |  | 2030-05-22 | Level 3 |  | Reinspection Date: 2025-05-23, Work Order ID: 9e0cdc4a-bd2d-4067-9a3c-b346f4870868 |  | LU | 2026 | 2
1120000382 | b72c1dca-54d4-4289-987c-a3452ebd5569 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-23 |  | 2030-05-22 | Level 3 |  | Reinspection Date: 2025-05-23, Work Order ID: c0de2fed-2152-4d00-85b9-d50b280fa518 |  | LU | 2026 | 2
1120000383 | bf56f6b4-1aea-4566-ae0e-3fcaa75ff939 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: e3c38211-0c18-4128-9df3-fa6d4bd5aa64 |  | LU | 2026 | 2
1120000384 | a84f887c-967e-446f-8652-822e6b9bcd4d | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-23 |  | 2030-05-22 | Level 3 |  | Reinspection Date: 2025-05-23, Work Order ID: 9aafa2e1-2693-44bb-b149-2b7ed59b5865 |  | LU | 2026 | 2
1120000385 | f6b3b5ca-e829-40b6-b541-fc1f0e52f468 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 4d40bc1c-51bb-475a-8804-565564df9caa |  | LU | 2026 | 2
1120000386 | f6b3b5ca-e829-40b6-b541-fc1f0e52f468 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 6b3d310f-9405-4c9e-b315-21873be66a83 |  | LU | 2026 | 2
1120000387 | f8d41791-7bd7-4237-bad5-354cb2bbca75 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 5cf2811b-f692-4007-8b6b-5dcba82e7290 |  | LU | 2026 | 2
1120000388 | f8d41791-7bd7-4237-bad5-354cb2bbca75 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: a27de6e2-9c1b-4917-afd0-9725af05303d |  | LU | 2026 | 2
1120000389 | 69996247-3e57-45dd-b47b-74c2e8a4f2dc | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 20f2a129-1e5a-45af-8448-58dcabd578fe |  | LU | 2026 | 2
1120000390 | 69996247-3e57-45dd-b47b-74c2e8a4f2dc | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 46ce2d58-6123-45b4-a3a0-641eb6b10bd2 |  | LU | 2026 | 2
1120000391 | 95f9d12c-80b1-4c70-9d83-89a07c36184a | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 066a5614-4dd8-4e61-99b7-3a6bcf8debf2 |  | LU | 2026 | 2
1120000392 | 95f9d12c-80b1-4c70-9d83-89a07c36184a | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: c761f0e0-1a17-46bf-b695-cc08e9c47402 |  | LU | 2026 | 2
1120000393 | 95f9d12c-80b1-4c70-9d83-89a07c36184a | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: dfd4a1a0-b04d-485b-8522-2ddd6740fd09 |  | LU | 2026 | 2
1120000394 | 0a7ef587-4897-49d1-a699-2eb2f7f40650 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-23 |  | 2030-05-22 | Level 3 |  | Reinspection Date: 2025-05-23, Work Order ID: 68ebe03b-12f8-4e56-8d3d-ae509694b411 |  | LU | 2026 | 2
1120000395 | 2ac1c80f-3003-4c94-a0d5-49e00729e7ec | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-05-23 |  | 2030-05-22 | Level 3 |  | Reinspection Date: 2025-05-23, Work Order ID: b8c72a3d-fb7d-4352-9795-a8727e0fd723 |  | LU | 2026 | 2
1120000396 | 358737be-845d-4cab-981f-c430b6b29280 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 5f997f1f-8f9c-4d6f-af64-c59d258898c6 |  | LU | 2026 | 2
1120000397 | 0984b54e-51bc-4cd2-8996-0a1e233f4fb3 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 9f984b70-348f-4a7e-9f55-cbc5ab89939a |  | LU | 2026 | 2
1120000398 | 0984b54e-51bc-4cd2-8996-0a1e233f4fb3 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: c81959cd-8823-44b3-82ea-84f061ecc350 |  | LU | 2026 | 2
1120000399 | 17e55a90-e563-454c-8561-b4fea81050e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-07-15 |  | 2030-07-14 | Level 3 |  | Reinspection Date: 2025-07-15, Work Order ID: 7a521559-e64f-450f-8b2e-8e240b607569 |  | LU | 2026 | 2
1120000400 | 143e37b3-5b0a-44dc-b4e6-4f11f6524c8c | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: bb86f081-2ddb-475a-a468-b7715fb22349 |  | LU | 2026 | 2
1120000401 | 97b788dd-0067-4a67-afa5-fc8c3851c7ba | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: 83f25e3c-dc44-4336-bf58-7f6c7c115acb |  | LU | 2026 | 2
1120000402 | 973afa36-f0a0-45b9-85ec-b697d61dac9a | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-28 |  | 2030-05-27 | Level 3 |  | Reinspection Date: 2025-05-28, Work Order ID: 264bdfaf-c3be-4115-832a-5855649a9740 |  | LU | 2026 | 2
1120000403 | 8e4ccc23-ae0a-42a4-b047-4a8c7ad13f9c | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: 755c62b7-8f46-4418-ac41-e82d36dd0769 |  | LU | 2026 | 2
1120000404 | 71deff71-dc87-474d-a88e-b554e5ec8735 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: eb1fecbf-3947-4627-ab1c-9b4a9db5547c |  | LU | 2026 | 2
1120000405 | 599c210c-f7b9-48d0-8a99-7dbc5d1d3c60 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-28 |  | 2030-05-27 | Level 3 |  | Reinspection Date: 2025-05-28, Work Order ID: d451c8c4-cf47-444a-9113-f5b4970bb805 |  | LU | 2026 | 2
1120000406 | b971e754-a7a1-4cfc-ac62-ac373c6b22e1 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 84297955-8161-42ac-b552-46511c8507c7 |  | LU | 2026 | 2
1120000407 | b971e754-a7a1-4cfc-ac62-ac373c6b22e1 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 846d52f2-0fba-469c-928f-0e44f865c487 |  | LU | 2026 | 2
1120000408 | f39ebcdc-e1cf-4321-ad97-aae41be4de40 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-05-27 |  | 2030-05-26 | Level 3 |  | Reinspection Date: 2025-05-27, Work Order ID: 3976bbb8-f66c-4012-8971-a86d26881bfe |  | LU | 2026 | 2
1120000409 | ebd43823-7e3e-4a64-8dcd-a365f4f4d688 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 8c6f1059-07a2-4f57-bca5-fa3af29b2752 |  | LU | 2026 | 2
1120000410 | cc282a12-28fc-427a-8ad0-90915688a5ec | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 7cfd013e-8cb8-4a93-8ce0-a5162e4cf68e |  | LU | 2026 | 2
1120000411 | d7361257-5d6b-4b70-8a83-14bcecbdea19 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: e6af7729-1f78-493b-852f-24818ec2f16a |  | LU | 2026 | 2
1120000412 | c05927a8-dfb9-4078-833e-bfbd9fe07717 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: 6ef70053-be09-4af9-8dc8-d8756d4da264 |  | LU | 2026 | 2
1120000413 | 6e97e484-4cc4-4e85-83f6-f369608e11f5 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-11 |  | 2030-04-10 | Level 3 |  | Reinspection Date: 2025-04-11, Work Order ID: 63903cbe-228b-40c2-994d-c716fbda8f3e |  | LU | 2026 | 2
1120000414 | 1da97d4a-433c-494a-934b-2c6393f1f033 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: 23d5ff0c-4ef6-4d34-bba8-d69bd50c4f30 |  | LU | 2026 | 2
1120000415 | 1fd57d67-f40a-42a5-a98e-141e397cd3a5 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: 3730e36e-f5de-4273-b0e9-e64e736dabe0 |  | LU | 2026 | 2
1120000416 | 48c545d7-05b7-4ffd-a478-7eb602a2ae92 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: 0be4526c-7dcb-4c87-92bd-08dc6633e7ec |  | LU | 2026 | 2
1120000417 | 1d953718-f9df-4ad4-a763-32ec470df896 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: 3174c2a5-1b6a-41ff-a495-f1e6cf24b035 |  | LU | 2026 | 2
1120000418 | 1d953718-f9df-4ad4-a763-32ec470df896 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: ae4ff0d3-10af-4e99-aa80-28fb3bc4fb64 |  | LU | 2026 | 2
1120000419 | 0fab8ec0-87ee-4d06-bcf9-c2069e62b261 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: 08c180dc-7287-4474-baa8-a8ab1f1a7e09 |  | LU | 2026 | 2
1120000420 | 025319f6-6b42-4694-b632-d2433105ca4a | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: e02b8b8e-272d-43d7-9e05-2f79e0ac89fd |  | LU | 2026 | 2
1120000421 | 02aaeb86-d9f5-4815-a2a1-73ac6d76ee7f | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 0e5b254b-1c76-4be0-863d-3ba82662b3a0 |  | LU | 2026 | 2
1120000422 | 6c5f0103-1a36-4ef9-b7a7-e0e3b212c5e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 5684dde6-928a-4426-aa55-946e68e335ad |  | LU | 2026 | 2
1120000423 | 57071b9b-29b4-44b4-8502-5a9f8dc12676 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 6a96544f-71c4-451a-bd08-354145da4248 |  | LU | 2026 | 2
1120000424 | 5cf0a10c-0545-41f8-8ff9-640352b224f5 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 3d645abe-bcd1-4612-9462-149cca178c47 |  | LU | 2026 | 2
1120000425 | 5cf0a10c-0545-41f8-8ff9-640352b224f5 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 8a49f25a-a785-4339-b7b4-4aad75dd4567 |  | LU | 2026 | 2
1120000426 | 5bc015a3-574b-480f-ac18-fc1db17145e2 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: d2deca4d-5a01-4410-a860-eef324695127 |  | LU | 2026 | 2
1120000427 | 544540b5-495f-4eb5-9081-a5a52d1cbbd1 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-07-16 |  | 2030-07-15 | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 8df62375-3c02-4970-84c1-72d089c1189e |  | LU | 2026 | 2
1120000428 | 7f77bc38-cfb0-4b50-bec3-f6b3eb27a1ce | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: b0c6c900-0be0-44b1-b65f-c53e5958b01f |  | LU | 2026 | 2
1120000429 | c4615a2b-e456-4a2f-a27c-dea97be2c056 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-05-14 |  | 2030-05-13 | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 491928f3-c7c4-4152-bfc6-f4209db30096 |  | LU | 2026 | 2
1120000430 | d841e89a-1a74-4475-a78e-89094d2da266 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-04-02 |  | 2030-04-01 | Level 3 |  | Reinspection Date: 2025-04-02, Work Order ID: ca643cbc-0da9-4a52-949e-baaf8d676a5e |  | LU | 2026 | 2
1120000431 | cb5376bc-02bc-4543-b454-fdb1c3a53691 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: d53725a6-2fae-4a90-b5ea-26dac6898f57 |  | LU | 2026 | 2
1120000432 | fb0c63ba-91f8-44a7-9157-735ffd31220d | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: d2f1b8f8-6a08-4b86-8d14-1d5d31369231 |  | LU | 2026 | 2
1120000433 | fffddd42-6a29-4925-b436-f66561081014 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 867191ad-c28f-48e9-9bd0-942930577009 |  | LU | 2026 | 2
1120000434 | fffddd42-6a29-4925-b436-f66561081014 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: e0b4cb53-1317-4eba-a582-83300c52800d |  | LU | 2026 | 2
1120000435 | d4fbd17d-2f58-4fc5-8e93-03f9a210bc97 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-07-15 |  | 2030-07-14 | Level 3 |  | Reinspection Date: 2025-07-15, Work Order ID: 4c69a945-f99f-43b6-8597-c369043e97ef |  | LU | 2026 | 2
1120000436 | d45978db-2ae5-4d40-af2e-48572f3f324b | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: cbc95617-4523-401b-8e2c-4d168c073b5e |  | LU | 2026 | 2
1120000437 | d9a7f516-ecd1-42bd-95fa-7d5f790e6612 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-11 |  | 2030-04-10 | Level 3 |  | Reinspection Date: 2025-04-11, Work Order ID: 90c0022a-2b2f-4932-96a3-095ef0c56bb8 |  | LU | 2026 | 2
1120000438 | ed69cff8-ff34-4f58-817b-d74d9877c01e | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-07-15 |  | 2030-07-14 | Level 3 |  | Reinspection Date: 2025-07-15, Work Order ID: 5d8f8864-3519-426f-9459-f4d688266efc |  | LU | 2026 | 2
1120000439 | ef6b2186-03f3-490a-9250-580743e3462a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: 1a13e0c8-2fe5-468b-b3e4-ad94985209d9 |  | LU | 2026 | 2
1120000440 | ef6b2186-03f3-490a-9250-580743e3462a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: bdcdfadb-a5f6-47ae-9ef6-3d5b73aa0e7a |  | LU | 2026 | 2
1120000441 | c8cbad51-dd29-4bd1-aae9-71bd4ce3a008 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-11 |  | 2030-04-10 | Level 3 |  | Reinspection Date: 2025-04-11, Work Order ID: e6d237df-ac16-4b7f-ae40-15c4546637b7 |  | LU | 2026 | 2
1120000442 | c8cbad51-dd29-4bd1-aae9-71bd4ce3a008 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-11 |  | 2030-04-10 | Level 3 |  | Reinspection Date: 2025-04-11, Work Order ID: fd2b5a02-2be0-47e9-a8a3-a9fff7e5bb94 |  | LU | 2026 | 2
1120000443 | 873b993e-4fe3-4f8b-8454-c9c80671730d | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: d31e98c0-3a73-4f2f-973c-d563f74563a0 |  | LU | 2026 | 2
1120000444 | 9417c87c-abf0-4ae1-9c9e-49a92873082a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: a8ec9869-d627-4b16-9f8e-851e3fd03b51 |  | LU | 2026 | 2
1120000445 | 9518665f-4856-4edb-aa6e-d9865d050d82 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 8a3f4b3b-0952-4251-9e7a-a31a878b7303 |  | LU | 2026 | 2
1120000446 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 4de48c62-f140-414b-9a24-53700941614d |  | LU | 2026 | 2
1120000447 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 5e66b018-2139-41c3-b646-cb10c3bfe49f |  | LU | 2026 | 2
1120000448 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 932118d8-b3e4-492d-917d-9a0835f42807 |  | LU | 2026 | 2
1120000449 | 54e38460-caac-4668-9de9-61c585fe6731 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: eab09b8b-be1a-4d7c-88ac-7d0fc4e204c5 |  | LU | 2026 | 2
1120000450 | 71875d7c-38a3-4a36-aeeb-9a1d7ab2ccf2 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 29382dc7-6263-4af5-9e1c-28182f527974 |  | LU | 2026 | 2
1120000451 | 71875d7c-38a3-4a36-aeeb-9a1d7ab2ccf2 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-02-28 |  | 2030-02-27 | Level 3 |  | Reinspection Date: 2025-02-28, Work Order ID: 9a4ccd82-2580-4164-85b3-45680d50ec4e |  | LU | 2026 | 2
1120000452 | 1c3eb035-255d-42ef-be59-8cee0541b29e | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-04-11 |  | 2030-04-10 | Level 3 |  | Reinspection Date: 2025-04-11, Work Order ID: 1bd28496-6b62-48bd-a9d7-acab4610b02d |  | LU | 2026 | 2
1120000453 | 425b5c88-914d-4f92-9cfa-ab55e7523096 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: 36f4ee47-950e-4c3a-a0a6-0ac775c91050 |  | LU | 2026 | 2
1120000454 | 425b5c88-914d-4f92-9cfa-ab55e7523096 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: 8af2c959-54c8-4518-8372-a42b4e4d8bd3 |  | LU | 2026 | 2
1120000455 | 425b5c88-914d-4f92-9cfa-ab55e7523096 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: d212d255-b364-4914-8a89-c4ed22fd2ba5 |  | LU | 2026 | 2
1120000456 | 2bfd054e-778e-4362-baf2-82c02c763ef4 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 |  | 2025-07-15 |  | 2030-07-14 | Level 3 |  | Reinspection Date: 2025-07-15, Work Order ID: 393a1ed9-82b3-4323-8bf7-ca0019891a62 |  | LU | 2026 | 2
1120000457 | 6e0e78df-02cb-4b0b-bcca-222d92558034 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: a77f6181-d1dd-497e-ba44-11e6766a2188 |  | LU | 2026 | 2
1120000458 | 6e0e78df-02cb-4b0b-bcca-222d92558034 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: cbe0f45a-ec7c-46f2-a5a1-610606859c27 |  | LU | 2026 | 2
1120000459 | 58776ba7-720a-4656-b257-6b15fa9640b9 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: 3c53f9fc-5230-4e1a-be7f-8a3b2720367c |  | LU | 2026 | 2
1120000460 | 8fb63efb-75d6-4178-934a-737853999df4 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: 18be5c59-933c-41d9-818b-374154002506 |  | LU | 2026 | 2
1120000461 | 878164e6-3b54-4524-a60f-dfdaac6d2999 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 00b7d37d-05ea-4a89-9be7-ea490602e450 |  | LU | 2026 | 2
1120000462 | 878164e6-3b54-4524-a60f-dfdaac6d2999 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: b2c22a7f-372b-4d15-9c6f-f794f6172dde |  | LU | 2026 | 2
1120000463 | baaf8b96-2dd2-4d35-b799-5d2a1a352b86 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 77305c10-5a7b-4cff-b2c6-b7c4adca8088 |  | LU | 2026 | 2
1120000464 | ed01b73c-e0c5-40f4-940e-02938e1ee2d2 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 8dafc7b0-96db-4eaf-943d-6d99daf6197f |  | LU | 2026 | 2
1120000465 | f22642d8-b035-4955-8b8a-f0a67fd249fc | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: 5622e734-65be-435c-beb6-2af81b53dc32 |  | LU | 2026 | 2
1120000466 | f22642d8-b035-4955-8b8a-f0a67fd249fc | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: a6fdc96a-ea57-466e-9c15-48da908242fd |  | LU | 2026 | 2
1120000467 | f22642d8-b035-4955-8b8a-f0a67fd249fc | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: b22a5692-7bd9-4231-af91-f892f3ae7a37 |  | LU | 2026 | 2
1120000468 | b2666ef3-01e2-4893-be1c-85ae2eed317f | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: 8cc4ca6c-2771-47af-ae33-694ead0eb26f |  | LU | 2026 | 2
1120000469 | b2666ef3-01e2-4893-be1c-85ae2eed317f | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: b9adf09e-0ff6-4c23-a8ba-87269c0b4f31 |  | LU | 2026 | 2
1120000470 | aff8e811-4da9-4a87-b347-756628be1ed4 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-03-27 |  | 2030-03-26 | Level 3 |  | Reinspection Date: 2025-03-27, Work Order ID: 67ad7ce8-6fe5-4447-8901-1e2adca731e1 |  | LU | 2026 | 2
1120000471 | 4a236246-274b-4c7a-ab5c-0f1d2a11f64e | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: 4f202774-c620-4966-b045-52cee3ed519f |  | LU | 2026 | 2
1120000472 | 43e67911-fc8e-4e53-83ab-8eeaadeaf9f0 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 2bc1939d-74a6-48af-8cb0-1083302b9a87 |  | LU | 2026 | 2
1120000473 | 1750facf-38ea-4b71-9d85-63f3cc3e392a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: 0083e3bb-d148-4c58-aec5-0989fd80e68e |  | LU | 2026 | 2
1120000474 | 1750facf-38ea-4b71-9d85-63f3cc3e392a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: 2aea63ee-4d7f-4ffe-8d87-d5a4932152d8 |  | LU | 2026 | 2
1120000475 | 1750facf-38ea-4b71-9d85-63f3cc3e392a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: a33a1bd7-5ccc-4a35-a039-deb409181233 |  | LU | 2026 | 2
1120000476 | 085e544e-9522-477a-9ede-7f7bd7148164 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-23 |  | 2030-04-22 | Level 3 |  | Reinspection Date: 2025-04-23, Work Order ID: 1dccbc93-6018-4515-9876-b53136330470 |  | LU | 2026 | 2
1120000477 | 96199d60-250b-47d7-8b8f-d6a620f0c370 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: 48bf90a2-fca8-41bd-a822-4fa1c616eab1 |  | LU | 2026 | 2
1120000478 | 97bb598a-b5a1-4d8a-8695-ad802b975edb | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: 06653353-a29c-4be9-85ce-d68a6093a670 |  | LU | 2026 | 2
1120000479 | 5c3926af-5029-4f91-b70a-da42d0d108c6 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-08 |  | 2030-04-07 | Level 3 |  | Reinspection Date: 2025-04-08, Work Order ID: e804bc13-f9fc-4cbe-b4c6-22be16d572b9 |  | LU | 2026 | 2
1120000480 | 6bab5585-e336-4f17-a49f-7945d2d2781e | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 047ca0d0-1a2c-4eec-b57f-a1a57e248a03 |  | LU | 2026 | 2
1120000481 | b3099126-a659-47ed-89f6-a14bc8a8cdad | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: 6fc5ba5a-f3d6-483e-aae1-06dbe628c6c4 |  | LU | 2026 | 2
1120000482 | ddeeebce-815f-432d-aa16-f76bd64a34e1 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 2025-04-30 |  | 2030-04-29 | Level 3 |  | Reinspection Date: 2025-04-30, Work Order ID: b0abf246-49e2-44b8-88d6-b26c7c869f85 |  | LU | 2026 | 2
1120000483 | d904e4e5-6795-4bed-a366-31333829c308 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-05-16 |  | 2030-05-15 | Level 3 |  | Reinspection Date: 2025-05-16, Work Order ID: f758b06c-7201-4b6a-953f-38c34278f8cc |  | LU | 2026 | 2
1120000484 | f9e32375-a6f0-4ee8-9551-70f813360abf | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: 43ee7a64-547e-48fb-bd9f-d9d99061cda8 |  | LU | 2026 | 2
1120000485 | f9e32375-a6f0-4ee8-9551-70f813360abf | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: bd42f0a0-c58d-4a3f-9c03-ee91fde08f94 |  | LU | 2026 | 2
1120000486 | 565e6c56-85ca-4ab7-a785-37e05ea27308 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: e1f1d074-c7b9-4cd8-bfd9-9b75cc1a2872 |  | LU | 2026 | 2
1120000487 | 83878f8a-b88c-47eb-8283-a14fb21cd1af | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: 280df545-5322-4c7e-9e53-5b15f2fb3a0a |  | LU | 2026 | 2
1120000488 | 83878f8a-b88c-47eb-8283-a14fb21cd1af | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-18 |  | 2030-04-17 | Level 3 |  | Reinspection Date: 2025-04-18, Work Order ID: cc15c5b5-9477-4c13-97c1-2c91be646d58 |  | LU | 2026 | 2
1120000489 | 7504fda9-54d3-454b-afc5-9f358efd5216 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-09-22 |  | 2026-09-22 | Level 2 |  | Reinspection Date: 2025-09-22, Work Order ID: 99a0fa42-455c-441e-bb25-af2bda4b519f |  | LU | 2026 | 2
1120000490 | 0cbdbae0-058e-41d4-949f-6f7547073aa3 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: fb93c3e6-2924-4cf5-89c1-06f3edd9c93c |  | LU | 2026 | 2
1120000491 | 3ad21ec0-6ed7-4c63-a7d4-f5cfd2d2bd0d | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: 0782f8cf-f9fa-4a96-a7f4-90296030cba9 |  | LU | 2026 | 2
1120000492 | 3ad21ec0-6ed7-4c63-a7d4-f5cfd2d2bd0d | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 2025-04-09 |  | 2030-04-08 | Level 3 |  | Reinspection Date: 2025-04-09, Work Order ID: e35240e8-223e-4be4-af1e-1c305a029e51 |  | LU | 2026 | 2
1120000493 | 45f7cea2-fc3a-4b19-bd91-cccac3f30e93 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: 6d2576cb-3edd-4e73-849b-7d341359ac2e |  | LU | 2026 | 2
1120000494 | 976812c3-549e-4459-8aaa-1014a57e85c2 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: 9ff7c8f6-7029-4b66-9d90-da98c3041195 |  | LU | 2026 | 2
1120000495 | 8c7a975b-05f7-449b-96f8-a8e31a0c14ce | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-03-27 |  | 2030-03-26 | Level 3 |  | Reinspection Date: 2025-03-27, Work Order ID: 9f4bfcde-0d87-4cf7-ae60-c42ae42d2b50 |  | LU | 2026 | 2
1120000496 | 701f10e0-2c97-4200-9cf5-eb1dbf3a911a | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: b5e30a75-9cb9-4af2-bd57-4c727a52a330 |  | LU | 2026 | 2
1120000497 | 701f10e0-2c97-4200-9cf5-eb1dbf3a911a | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: e8f5d6a0-5b98-4d23-9720-d136a95512fd |  | LU | 2026 | 2
1120000498 | fcf91658-272c-4f3b-afdd-2b0129da2f9c | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: dd4cf439-115b-490d-a792-b9fe5ee11dcd |  | LU | 2026 | 2
1120000499 | eb7ef2fe-be23-4b67-9e40-6cb772cde68e | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-04-29 |  | 2030-04-28 | Level 3 |  | Reinspection Date: 2025-04-29, Work Order ID: deaed856-1997-48fd-821d-2f89d14eba3b |  | LU | 2026 | 2
1120000500 | b9cbb2d2-b1db-4d39-abd0-be203d091c16 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: 66673030-4934-4ad3-ac78-cafe8840ae82 |  | LU | 2026 | 2
1120000501 | c86f2997-16d0-4a0f-b43b-f69bc14b81b7 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: 711f955d-0343-4422-af30-f0d0ba1d616c |  | LU | 2026 | 2
1120000502 | a94943af-7397-45f2-8b69-e4ca16a12d2f | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: da8f65a2-1522-4f75-8c0c-745888eac1a5 |  | LU | 2026 | 2
1120000503 | 8872a0c6-849c-4123-b8c5-81a8b5604ce7 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | 2025-04-03 |  | 2030-04-02 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: ba3be2cc-e52d-48f9-9f3f-4d67093b799b |  | LU | 2026 | 2
1120000504 | 3918925d-84fc-4a05-9982-ffdfd26057aa | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 |  | 2025-04-02 |  | 2030-04-01 | Level 3 |  | Reinspection Date: 2025-04-02, Work Order ID: 4dc888af-0cd7-4f0a-b138-bc70cbcebc93 |  | LU | 2026 | 2
1120000505 | 19ddd5a2-2b27-42d2-acb9-728a37443d61 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | 2025-02-20 |  | 2030-02-19 | Level 3 |  | Reinspection Date: 2025-02-20, Work Order ID: ab9f3a30-b041-4d5b-8dc7-30ebfb135faf |  | LU | 2026 | 2
1120000506 | b88d0870-45d2-434f-871a-0ecc054b9df8 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 |  | 2025-02-21 |  | 2030-02-20 | Level 3 |  | Reinspection Date: 2025-02-21, Work Order ID: 7a0ac46d-aa01-4fbb-8276-72b83535d112 |  | LU | 2026 | 2
1120000507 | 5ac125c4-f76c-4bf6-81a8-6023687c1e56 | Pole | HFTD Tier 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 |  | 2025-11-13 |  | 2026-11-13 | Level 2 |  | Reinspection Date: 2025-11-14, Work Order ID: f17646af-2a38-4a29-9489-9db3236e12c8 |  | LU | 2026 | 2
1120000508 | 2bdbc017-ebfe-4ff6-a4bb-a2b677c538e2 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | 2025-09-23 |  | 2026-09-23 | Level 2 |  | Reinspection Date: 2025-09-23, Work Order ID: e2c35efb-7811-4077-a443-63f469bdc816 |  | LU | 2026 | 2
1120000509 | e53ed73d-23f5-4039-bb8d-228db32ae57f | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-10-31, Work Order ID: 3fa46966-885b-42a3-9399-e703f29d45e0 |  | LU | 2026 | 2
1120000510 | f9fb7b28-a61f-4399-bdb9-9d2a8a5852d9 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 327d1616-d91e-4ae4-9261-b941c19f3e59 |  | LU | 2026 | 2
1120000511 | f9fb7b28-a61f-4399-bdb9-9d2a8a5852d9 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | 2025-09-23 |  | 2026-09-23 | Level 2 |  | Reinspection Date: 2025-09-23, Work Order ID: 44fb161a-090c-4e28-8960-891470169632 |  | LU | 2026 | 2
1120000512 | f9fb7b28-a61f-4399-bdb9-9d2a8a5852d9 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 |  | 2025-09-23 |  | 2026-09-23 | Level 2 |  | Reinspection Date: 2025-09-23, Work Order ID: 6a45b96a-26f1-4e6c-b423-45674ab0e900 |  | LU | 2026 | 2
1120000513 | 963136ec-ce64-4c53-a454-f33e483b9fae | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 |  | 2025-05-21 |  | 2030-05-20 | Level 3 |  | Reinspection Date: 2025-05-21, Work Order ID: 0f203214-8c47-4a19-9954-428bb3dff8d7 |  | LU | 2026 | 2
1120000514 | 5944863f-b5ee-40a5-9711-590f6d8b0d80 | Pole | HFTD Tier 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: 8654dd86-83ac-475b-bac7-b75a7427f2c5 |  | LU | 2026 | 2
1120000515 | 5944863f-b5ee-40a5-9711-590f6d8b0d80 | Pole | HFTD Tier 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: daa0d1d0-9d19-40af-8056-8d734bac7083 |  | LU | 2026 | 2
1120000516 | 951e2639-6d1d-43dc-b94a-90af4258816c | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-25 |  | 2030-04-24 | Level 3 |  | Reinspection Date: 2025-04-25, Work Order ID: a67d5fd3-c7ea-45ad-9488-0c680a2f9f16 |  | LU | 2026 | 2
1120000517 | 4456b3ce-1ab3-4760-8754-5998f6087cc2 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: 76d3dc67-622c-46a1-90c6-2eeafa8c5fdb |  | LU | 2026 | 2
1120000518 | 4456b3ce-1ab3-4760-8754-5998f6087cc2 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: deb65665-2347-4ccd-ad9f-4429a8fb2d75 |  | LU | 2026 | 2
1120000519 | 19adf6c5-be0d-4467-be4a-31f26d68874c | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-25 |  | 2030-04-24 | Level 3 |  | Reinspection Date: 2025-04-25, Work Order ID: c2d0972f-2ffa-4f0f-9434-35e3cc6fa3c3 |  | LU | 2026 | 2
1120000520 | cf6bbdf5-ecc2-42c3-a11f-21ecccc8bd6a | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-10 |  | 2030-04-09 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: ed84d48e-555a-4cd0-95e7-015bcf882372 |  | LU | 2026 | 2
1120000521 | bb0d463c-032a-4c3f-afba-5086f25a93c4 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: 8f1810b5-f180-4001-a555-3609b0d92a22 |  | LU | 2026 | 2
1120000522 | c8ffbe26-1d69-43ce-8e3a-c0c744fe3fa4 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 |  | 2025-04-22 |  | 2030-04-21 | Level 3 |  | Reinspection Date: 2025-04-22, Work Order ID: 94bfba77-ca1d-4380-a254-045872d6a963 |  | LU | 2026 | 2
1120000523 | b609f00c-e7b5-4af4-87c4-ea6ee277b1aa | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2025-04-02 |  | 2030-04-01 | Level 3 |  | Reinspection Date: 2025-04-02, Work Order ID: 6a9364e2-db72-4435-8d69-7a2c2240ce84 |  | LU | 2026 | 2
1120000524 | a49354e1-fa0a-4405-8003-26376cb3accd | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2024-03-08 |  | 2029-03-07 | Level 3 |  | Reinspection Date: 2026-01-27, Work Order ID: d7a0f6d8-8ef6-4733-bfbe-eb09bb9a5a68 |  | LU | 2026 | 2
1120000525 | a49354e1-fa0a-4405-8003-26376cb3accd | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2024-03-08 |  | 2029-03-07 | Level 3 |  | Reinspection Date: 2026-01-27, Work Order ID: f89c9c94-6bf3-4d84-a8ba-eee2f6c2085e |  | LU | 2026 | 2
1120000526 | 33e5b988-db42-4f18-9ddc-50cd8772e0b0 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2025-06-26 |  | 2030-06-25 | Level 3 |  | Reinspection Date: 2025-04-03, Work Order ID: ef79ba59-9e9e-4bc3-a5bc-7a5dbefc0e9b |  | LU | 2026 | 2
1120000527 | 997df984-f7a6-491c-b971-f9830dbf646b | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2025-06-26 |  | 2030-06-25 | Level 3 |  | Reinspection Date: 2025-04-10, Work Order ID: e398d313-d4f2-4a5f-b8aa-896ae60c3bef |  | LU | 2026 | 2
1120000528 | 6498c3a6-9d0d-4450-a7c0-5ca207606cda | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 |  | 2025-04-02 |  | 2030-04-01 | Level 3 |  | Reinspection Date: 2025-04-02, Work Order ID: 5fb3351e-e067-4e01-bfa0-7d9b4c4c56f5 |  | LU | 2026 | 2
1120000529 | 0234f723-55e7-4334-a6ef-a6815bb14a8b | Pole | HFTD Tier 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 |  | 2025-06-26 |  | 2030-06-25 | Level 3 |  | Reinspection Date: 2025-05-15, Work Order ID: 95506144-3311-4a5f-be7d-644b9fee3a21 |  | LU | 2026 | 2
1120000530 | 11492d1c-2efc-4170-99eb-b393e987786f | Pole | HFTD Tier 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 9823e89b-0920-4b1b-812a-a094f9973a9a |  | LU | 2026 | 2
1120000531 | 3dc3ba1f-7d9a-4fbe-b8e4-c7386a341c1f | Pole | HFTD Tier 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 73954d29-d4da-4857-aa0f-2982860ecc58 |  | LU | 2026 | 2
1120000532 | 22a2e0f7-8444-42e3-a99e-6be94498d001 | Pole | HFTD Tier 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 |  | 2025-12-10 |  | 2030-12-09 | Level 3 |  | Reinspection Date: 2025-12-10, Work Order ID: fd2e8f74-985e-48cf-a1b0-544868f49a97 |  | LU | 2026 | 2
1120000533 | 2dc42ec5-3264-478d-8207-5006cfaa9c49 | Pole | HFTD Tier 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 |  | 2024-06-17 |  | 2029-06-16 | Level 3 |  | Reinspection Date: 2024-06-17, Work Order ID: 2dc7d973-6c3b-41fb-a715-e30f08da69f1 |  | LU | 2026 | 2
1120000534 | 2dc42ec5-3264-478d-8207-5006cfaa9c49 | Pole | HFTD Tier 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 |  | 2024-06-17 |  | 2029-06-16 | Level 3 |  | Reinspection Date: 2024-06-17, Work Order ID: 9ccf235c-40ad-4d3b-9c89-cd75a39a4506 |  | LU | 2026 | 2
1120000535 | 67587120-ccb9-4817-a6b9-c3f76a5ae8bd | Pole | HFTD Tier 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3 |  | 2025-07-30 |  | 2030-07-29 | Level 3 |  | Reinspection Date: 2025-07-30, Work Order ID: a044038b-1eb0-4472-9b31-69a49195c42f |  | LU | 2026 | 2
1120000536 | 914e7e65-8498-48b0-832a-82725b95c796 | UG Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 708f0c23-afed-4660-8964-3f5e5f45e500 |  | LU | 2026 | 2
1120000537 | b53a1b1f-5715-4d3d-a8ba-b1ad9b65fe3f | UG Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 086e961a-85c2-4267-b614-c2437a579c6a |  | LU | 2026 | 2
1120000538 | d433971e-683d-4d41-ae5a-7e03c1550cd9 | UG Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2022-10-22 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: e7e34106-952e-4c52-8f25-b66b718298d9 |  | LU | 2026 | 2
1120000539 | a61caf01-5aa1-4845-a933-36462956d195 | UG Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: fd30e6ee-01c7-467a-9647-8c9f314a7933 |  | LU | 2026 | 2
1120000540 | 718a4f31-c825-4158-b0c4-dd89695d465f | UG Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 6120a213-99fd-48d5-b218-4dc24e7f6825 |  | LU | 2026 | 2
1120000541 | e163f1f1-8cba-48c5-83d2-75aa5efe2818 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-12-12, Work Order ID: c7db3202-e835-42b3-a817-1f98e6f07a85 |  | LU | 2026 | 2
1120000542 | e163f1f1-8cba-48c5-83d2-75aa5efe2818 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: fc1f7f14-f20d-4143-abea-5e5ef5f5e5e6 |  | LU | 2026 | 2
1120000543 | f1f8c7b1-1b6b-4604-8239-4c4dd6b4aa37 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | 2025-12-11 |  | 2030-12-10 | Level 3 |  | Reinspection Date: 2025-12-11, Work Order ID: d1feeaa7-41be-4988-bde3-7e3199cae912 |  | LU | 2026 | 2
1120000544 | b747a0d6-843b-4cba-9d37-6f5a966ae173 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 |  | 2026-04-16 |  | 2031-04-15 | Level 3 |  | Reinspection Date: 2026-04-16, Work Order ID: f7901ace-75aa-47fd-8b8c-2611c9060f0f |  | LU | 2026 | 2
1120000545 | d451f1f0-1222-4811-a268-06b6075a50ad | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 |  | 2026-04-16 |  | 2031-04-15 | Level 3 |  | Reinspection Date: 2026-04-16, Work Order ID: 31fe799e-b671-42d3-ae62-967462c84d31 |  | LU | 2026 | 2
1120000546 | d451f1f0-1222-4811-a268-06b6075a50ad | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 |  | 2026-04-16 |  | 2031-04-15 | Level 3 |  | Reinspection Date: 2026-04-16, Work Order ID: 5dd63b6c-bc36-47da-9a6d-365c7ce7df89 |  | LU | 2026 | 2
1120000547 | b56eb641-e8e6-4c5f-9c27-cafc6c74c257 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: ac83df51-d822-4bc8-a340-0c4de8062912 |  | LU | 2026 | 2
1120000548 | d5004bbc-f611-44c3-95ba-69ecbd2a4c1b | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | 2026-02-11 |  | 2031-02-10 | Level 3 |  | Reinspection Date: 2026-02-11, Work Order ID: 02061121-6193-4c3a-9e71-6890928f74c8 |  | LU | 2026 | 2
1120000549 | d5004bbc-f611-44c3-95ba-69ecbd2a4c1b | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | 2026-02-11 |  | 2031-02-10 | Level 3 |  | Reinspection Date: 2026-02-11, Work Order ID: 89acb19c-09ac-467d-8023-33a252a61c0d |  | LU | 2026 | 2
1120000550 | d064a8de-28dc-4db2-8041-ab59066c968d | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | 2026-02-11 |  | 2031-02-10 | Level 3 |  | Reinspection Date: 2026-02-11, Work Order ID: bc9049c2-5a90-42f8-b521-5995cef2cee0 |  | LU | 2026 | 2
1120000551 | 7ba60b31-707c-486e-ba96-97469ac5f305 | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | 2026-02-11 |  | 2031-02-10 | Level 3 |  | Reinspection Date: 2026-02-11, Work Order ID: 42bda79c-7ea2-49ed-b87b-d28786eff954 |  | LU | 2026 | 2
1120000552 | 24f578d1-36d7-4cbb-9433-0b3625b0e5dd | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 |  | 2026-02-11 |  | 2031-02-10 | Level 3 |  | Reinspection Date: 2026-02-11, Work Order ID: d5d3620c-5b7e-47cd-a8c1-be9864243688 |  | LU | 2026 | 2
1120000553 | 4a5d08a6-196f-41e2-83f5-e6eee3de49b4 | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: d36be3fc-c583-473b-aed7-a8b3571e96f5 |  | LU | 2026 | 2
1120000554 | a3b08b60-dd81-4c02-ab86-7fd324106d2c | UG Transformer | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 |  | 2026-02-12 |  | 2031-02-11 | Level 3 |  | Reinspection Date: 2026-02-12, Work Order ID: 971613aa-7f39-42d8-b6b8-ea74ae0a8ff5 |  | LU | 2026 | 2
1120000555 | c3ae04fc-0991-4061-8362-0af1e056442e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: b1fae584-61e5-48a5-90f8-6da3fd17d316 |  | LU | 2026 | 2
1120000556 | 9e79ef97-f876-443e-943e-204a55cd7b3c | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: c598820b-221e-496d-9e3e-df6e39da1888 |  | LU | 2026 | 2
1120000557 | 954534d2-b885-4cd5-a4b2-9e067e5a31a3 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: e1c130d6-db9a-41e5-ae67-6b62ada57c26 |  | LU | 2026 | 2
1120000558 | 0daf0ec8-3b81-4983-82a3-eed62a99ecb5 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: cb3d8341-05d0-4964-86a4-f638bb4b69fe |  | LU | 2026 | 2
1120000559 | 03eed663-4b09-45b1-ab7d-99cc4035d813 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: 10be8c01-d294-4e8f-bc78-ed83eedbf195 |  | LU | 2026 | 2
1120000560 | 3e699e09-eb38-44f7-9862-676830e6ff7f | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-03-16 |  | 2031-03-15 | Level 3 |  | Reinspection Date: 2026-03-16, Work Order ID: b255d19e-25b2-4a4c-a0a9-ce8ee697d23f |  | LU | 2026 | 2
1120000561 | 7b4f7d71-05ea-4576-9c62-33296534cc4e | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: e48db5de-532b-4651-87a0-a6b7d4a3efb3 |  | LU | 2026 | 2
1120000562 | 881313cb-605d-4122-b5f5-c1bb7108bd12 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: ff1935b5-7bf6-4e00-83c6-5971fe88b7dd |  | LU | 2026 | 2
1120000563 | 80707c2c-cee7-4dea-954b-4dfd66f60608 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: 8bfa0386-062f-4f4f-8a5d-bd938b85bf54 |  | LU | 2026 | 2
1120000564 | 51c76d6a-a2c1-4b0e-be1d-b4a9e38bb947 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: ebc8ac6a-a022-473b-8bd5-91868ade5777 |  | LU | 2026 | 2
1120000565 | c9927a47-4610-4e6e-aa9d-faa8e72d1dab | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 |  | 2026-02-09 |  | 2031-02-08 | Level 3 |  | Reinspection Date: 2026-02-09, Work Order ID: 4cd1f176-145b-4a67-9a10-9eb67f66ea07 |  | LU | 2026 | 2
1120000566 | 80b6278e-0ce2-4f55-9f45-5d1e08f5a743 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: 3bf9810d-4c3e-4ddc-b486-215ab9397126 |  | LU | 2026 | 2
1120000567 | 80b6278e-0ce2-4f55-9f45-5d1e08f5a743 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: daef6973-f719-4286-af2d-e90d6859c3ed |  | LU | 2026 | 2
1120000568 | 8a2e0ee2-9eb8-4eab-9a8d-a211a7251715 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: 7162774e-1230-43e4-a44b-06e4d9c2d5c1 |  | LU | 2026 | 2
1120000569 | 8a2e0ee2-9eb8-4eab-9a8d-a211a7251715 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: c96cfb41-9bf7-4ea3-bd63-0e44792a6de2 |  | LU | 2026 | 2
1120000570 | 8a2e0ee2-9eb8-4eab-9a8d-a211a7251715 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: fec1a332-1afc-4111-822a-b7ede05e5eb7 |  | LU | 2026 | 2
1120000571 | 05746d1c-75c1-4a69-aadd-a0725d36a9c5 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | 2026-02-12 |  | 2031-02-11 | Level 3 |  | Reinspection Date: 2026-02-12, Work Order ID: 751c9963-1ebf-4086-be66-91cb30c061ef |  | LU | 2026 | 2
1120000572 | 05746d1c-75c1-4a69-aadd-a0725d36a9c5 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | 2026-02-12 |  | 2031-02-11 | Level 3 |  | Reinspection Date: 2026-02-12, Work Order ID: af386f25-ded4-4bbc-9b74-9d411cf1948b |  | LU | 2026 | 2
1120000573 | bd1839ad-2fd9-4aef-85d2-7cd542bbf167 | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 |  | 2026-02-12 |  | 2031-02-11 | Level 3 |  | Reinspection Date: 2026-02-12, Work Order ID: 6d79332b-c47e-4f2b-aae0-ab38dd90436f |  | LU | 2026 | 2
1120000574 | cdb708ab-9057-43c3-acfe-9110862882fd | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | 2026-02-06 |  | 2031-02-05 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 9b045e72-4fad-43bd-81a3-aa91d3623289 |  | LU | 2026 | 2
1120000575 | cdb708ab-9057-43c3-acfe-9110862882fd | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | 2026-02-06 |  | 2031-02-05 | Level 3 |  | Reinspection Date: 2026-02-06, Work Order ID: d90b59e7-b621-4e00-9081-95ec028347e9 |  | LU | 2026 | 2
1120000576 | 897517da-e9b6-4354-bfa0-a9a8eea3ec3d | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 |  | 2026-02-06 |  | 2031-02-05 | Level 3 |  | Reinspection Date: 2026-02-06, Work Order ID: 7bab6a71-2c97-498a-a0b9-9225af6dbbb3 |  | LU | 2026 | 2
1120000577 | adabfe21-7c93-4cad-964d-afe95093b13c | UG Transformer | HFTD Tier 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 |  | 2026-02-06 |  | 2031-02-05 | Level 3 |  | Reinspection Date: 2026-02-06, Work Order ID: 699ffce3-5e53-49f7-b7c7-f336c3447110 |  | LU | 2026 | 2
1120000578 | 916065d9-7717-489c-97e8-09a487d70e56 | UG Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 0493db62-038f-4ece-8412-a69110ebd253 |  | LU | 2026 | 2
1120000579 | 916065d9-7717-489c-97e8-09a487d70e56 | UG Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-02-05, Work Order ID: cb43f278-fcd0-47f2-9712-25ee0dbe2609 |  | LU | 2026 | 2
1120000580 | 916065d9-7717-489c-97e8-09a487d70e56 | UG Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-02-05, Work Order ID: cda63dcc-c403-4bed-95bb-72c8c0672991 |  | LU | 2026 | 2
1120000581 | 0017805a-608c-4e88-9174-f66ed8562a13 | UG Transformer | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | 2025-11-20 |  | 2030-11-19 | Level 3 |  | Reinspection Date: 2025-11-20, Work Order ID: 1988173c-cbfd-4fac-a992-496df17016e7 |  | LU | 2026 | 2
1120000582 | 0017805a-608c-4e88-9174-f66ed8562a13 | UG Transformer | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 |  | 2025-11-20 |  | 2030-11-19 | Level 3 |  | Reinspection Date: 2026-02-05, Work Order ID: edc525df-9bb0-4c2c-81c1-b422e9b717f0 |  | LU | 2026 | 2
1120000583 | 1aa56628-a981-4cc2-9c27-8f81f0b0010e | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000584 | 7a8cc998-e2c9-46f8-acc3-c1ce1ebd65ce | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000585 | 79f94430-f7dd-4e43-b791-ac44b00b66bf | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000586 | 4d986c89-524b-49a6-9c18-2c77865ba0b1 | Pole | Non-HFTD | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000587 | b646a044-212a-4883-b835-05df3135e9be | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000588 | dd4c6a5b-6280-461a-9307-7810ce4d656a | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000589 | ffdb08e1-3cda-4d70-b378-a29db53c941b | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000590 | de0312a9-32dd-4e37-b7ea-5450062d4b14 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000591 | b07a6841-ec72-4547-80db-57b6fb1ba967 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000592 | 8bf623ee-ebef-4f63-a753-3af34c5f53f2 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000593 | 2de29661-84fd-42b7-9355-fdb668ede5d7 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000594 | 36db653b-49fa-4fff-a66e-f48cda801d8c | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000595 | 8c70cf5e-777d-4e6a-a0e3-216ed425c4a3 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000596 | 5957e772-71c6-475b-a7b0-6c0c4f54115e | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000597 | af3c60aa-0c35-43c4-b18b-54a6a678f88d | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000598 | c55ae154-c776-4d22-8c01-d3618e007b92 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000599 | 6dd8d446-3ba3-4675-81d8-13aadcafe105 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000600 | 30e9314b-3fc7-4ef3-8a8f-8672f6471c83 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000601 | 32ecb370-1fe2-4223-9aa3-b3b344016ad4 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000602 | 3e5aa20b-287f-4e65-8d89-20f2b57510ef | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000603 | 240dd5b0-bf4b-4d2b-9958-dd0349c52e71 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000604 | 14a55c3d-7228-478b-9c15-e17f4b3f3dcc | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000605 | 453370c9-9491-4498-89a4-34d078f014b2 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000606 | 79500704-6812-4c62-823b-ede8492e679d | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000607 | 8e910bc3-7b15-4540-9482-fe25885e484c | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120000608 | 3e971e2c-0a48-41eb-9119-d9a4c9ad543c | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 |  | 2025-09-12 |  | 2030-09-11 | Level 3 |  | Reinspection Date: 2025-09-12, Work Order ID: 940c3990-b160-49c5-9103-cd0d779d9a59 |  | LU | 2026 | 2
1120000609 | 3e971e2c-0a48-41eb-9119-d9a4c9ad543c | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 |  | 2025-09-12 |  | 2030-09-11 | Level 3 |  | Reinspection Date: 2025-09-12, Work Order ID: c3788bd3-7cf7-477e-91f8-7c7f6f9ff405 |  | LU | 2026 | 2
1120000610 | 3246d659-6d77-4831-90b6-cea9af7d79c8 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000611 | 7ae3c14f-2dbc-4e6d-bd76-be4e2ded08fb | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000612 | 5a44b1f9-daf3-47d2-9906-da650f080764 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000613 | 74d3db50-2958-4ea3-aae7-6ec687c6f7f3 | Pole | Non-HFTD | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000614 | 93088519-5600-44c8-b679-2de6d10b40fb | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000615 | 45d8b59e-b40d-437d-9a7c-2b9b922f4f0e | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000616 | 3a508812-be8d-4175-855e-66a8a93c1e9f | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000617 | 262258f9-4b4a-4482-ab78-5c5d251ff5d4 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000618 | 8fd2d194-0cc3-4236-b131-692a3f7afe6e | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000619 | 7867d964-1f89-4b8c-9e83-e87cc761370e | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000620 | 6e920e41-7726-4669-b859-7885e6e5d4ff | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000621 | c5a11c96-f73a-4aa4-a8e8-9b0f66fc6d10 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000622 | aab229c0-4d78-4d7d-ae92-e8778adf11b9 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000623 | a5cdc95e-52b2-4bbf-a91a-46e8ac3e68eb | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000624 | ad3fb623-0e83-4c5e-9c25-c81f37faa957 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000625 | bbb0feb7-c394-4e1f-b724-67b7a5aa828d | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000626 | 6536af10-b041-4d3c-a55a-301ae3dc30ed | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 |  | 2025-03-07 |  | 2030-03-06 | Level 3 |  | Reinspection Date: 2025-03-07, Work Order ID: c4ea4c6b-ca89-4d61-9886-5f4061e4634b |  | LU | 2026 | 2
1120000627 | 8ebbf735-2967-43ce-a524-164f20cfb254 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000628 | 8b77616c-e838-4a9d-9d19-43e258cce374 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000629 | 3a211bc7-0824-48e7-ab31-826154608772 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000630 | 1418d789-7bc6-4a55-93a4-632676a3455d | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000631 | 9076da6f-12b9-4222-ad8d-e9290db01fbe | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: b8155f4b-bb2b-4921-8029-67c7ebf7b52b |  | LU | 2026 | 2
1120000632 | 9076da6f-12b9-4222-ad8d-e9290db01fbe | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: bf51f6e0-1d32-4172-ab9e-755d82da1cf2 |  | LU | 2026 | 2
1120000633 | 936e8b1b-490b-4002-b316-5411274c4cad | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: c2f85c2d-8000-4138-ba15-4e5897958b9c |  | LU | 2026 | 2
1120000634 | 65991550-21b1-45c5-a9a5-9bd2175ba247 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 41cc1b12-bfe5-47a8-b06d-2b11b341978c |  | LU | 2026 | 2
1120000635 | 50da1809-f59e-46df-be74-d618534160f2 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 5737073a-207f-4e40-a2e8-7b9beb6205a3 |  | LU | 2026 | 2
1120000636 | 88e95113-b1ab-4d72-8e77-74cf55f30c45 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 745a3442-379e-4edc-85ec-bf1ea0496230 |  | LU | 2026 | 2
1120000637 | 08cb65df-922a-40b9-b1c5-50bd1b088ebe | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | 2025-07-09 |  | 2030-07-08 | Level 3 |  | Reinspection Date: 2025-07-09, Work Order ID: b2be7534-899c-4c77-ba84-46e00d1c188a |  | LU | 2026 | 2
1120000638 | 3dacab4f-4c4f-4c6d-bcbb-037d8a3fcb56 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 2c417d7f-a65b-4c20-b889-e7e99983ae19 |  | LU | 2026 | 2
1120000639 | 3ddbc701-4e5f-4d6c-8ef4-cbdb6cd7140a | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 77fc73e1-10b4-4c1d-957c-7a30d750e101 |  | LU | 2026 | 2
1120000640 | 2dafe234-c350-4a22-b05a-4618d50078c3 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120000641 | a4e7a99d-9f83-4044-9366-56aec6a275a9 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 |  | 2025-05-06 |  | 2030-05-05 | Level 3 |  | Reinspection Date: 2025-05-06, Work Order ID: d78c9365-7844-4c16-a92e-c7c344426901 |  | LU | 2026 | 2
1120000642 | c46eeda5-e1b1-4d5b-b74f-77cffee8366d | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000643 | e4f6610a-a221-4630-b8c5-720f7b9d4c31 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: 07ddea60-37b9-48cb-bae0-adb3e81844e3 |  | LU | 2026 | 2
1120000644 | fdd78893-be1b-449e-83ae-b9ceb8f7a3e8 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | 2025-05-20 |  | 2030-05-19 | Level 3 |  | Reinspection Date: 2025-05-20, Work Order ID: de5c2cae-41d3-4740-9941-3cf7dffa6722 |  | LU | 2026 | 2
1120000645 | f3cd9c1f-4c46-439e-8a76-2812b3465187 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000646 | 568e9093-4504-44be-a147-3f4c1e80e433 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 |  | 2025-05-21 |  | 2030-05-20 | Level 3 |  | Reinspection Date: 2025-05-21, Work Order ID: 10732f5b-d6b8-4de9-b02f-1722214ee963 |  | LU | 2026 | 2
1120000647 | 54f4a338-1b7a-4e1f-a3df-9f70fe166300 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000648 | 5ce7533d-3ee9-41e1-b22f-ae9f635c88b4 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000649 | e234c2b7-5a0f-487f-a649-9d28f00d1a91 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000650 | 5a4c2575-d784-4717-a5b9-5b04aecb63fb | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000651 | 8623e559-0d0a-4e71-a711-b09f3f779f4f | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000652 | 7f527968-df73-49cc-9f05-cee645222c12 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000653 | 3caf99d2-0abb-439c-9769-a4ff298a68f5 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000654 | 4b6d1296-b85e-48e6-a916-2b30cb4661b6 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000655 | 07c28662-ceac-4cd0-90ce-8232d672aabc | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000656 | 0140a406-6179-42b2-b2a0-71b36891e433 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000657 | 0d0ce0e9-ab78-4daf-89f7-b341bd58b579 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000658 | 16d8cd56-e13d-4341-9277-3a576765b208 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000659 | 4707987d-5239-43ec-a193-afa0d31cd8d0 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000660 | 8be489ac-8429-4a28-87ab-64885de3e9df | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000661 | 592a28d7-5d44-4ec4-9df9-d4a543d9502b | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000662 | 50ec66bd-cf4a-43bd-86e2-f06446bbfb0e | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000663 | 688af7c8-9566-4874-b32b-950521a06c76 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000664 | e7f729ce-ace2-4cd7-b676-9d4d161b25bd | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000665 | f1e8c6c2-4de8-412c-aa2b-e4963cdf9c0c | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000666 | d5049150-9b22-48c4-a7a7-a8b1ec4eb6b7 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000667 | bbef76b2-3d90-4a6b-b2a4-4a9c7b9a4934 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000668 | a8b4ab2a-eb29-4e16-9782-63034f4d0465 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000669 | bb82f9b8-e802-473f-8a06-6d61c026f351 | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000670 | e7b213d0-3779-4907-b2d9-3f148b7206f4 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000671 | cc3f70ec-68de-44a8-98b3-92e77f21ffec | Switch | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 4d7816c7-eb7b-413c-8950-b98798e44774 |  | LU | 2026 | 2
1120000672 | cc3f70ec-68de-44a8-98b3-92e77f21ffec | Switch | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: e325d7fe-0330-4047-82c7-4cbc1c099e39 |  | LU | 2026 | 2
1120000673 | cebd2c4f-fbf3-41aa-ba50-dbcdc601cc64 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 18309c27-8cec-4283-b37a-91836a36c197 |  | LU | 2026 | 2
1120000674 | cebd2c4f-fbf3-41aa-ba50-dbcdc601cc64 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 48f36ce2-ec01-4c0e-a5dd-1a85e0674d66 |  | LU | 2026 | 2
1120000675 | cebd2c4f-fbf3-41aa-ba50-dbcdc601cc64 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: c5504d36-f736-4109-9a7e-f5cb2cfa80be |  | LU | 2026 | 2
1120000676 | cebd2c4f-fbf3-41aa-ba50-dbcdc601cc64 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: e92ff104-0f44-486d-94f7-04657481299c |  | LU | 2026 | 2
1120000677 | c68d77a0-9ec9-42ce-81be-d8766018792f | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-03-20 |  | 2030-03-19 | Level 3 |  | Reinspection Date: 2025-03-20, Work Order ID: 65c5fd02-a452-4e6b-b43a-deb128f59e24 |  | LU | 2026 | 2
1120000678 | c68d77a0-9ec9-42ce-81be-d8766018792f | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-03-20 |  | 2030-03-19 | Level 3 |  | Reinspection Date: 2025-03-20, Work Order ID: f52c4485-70f3-475b-8b0d-bc9d65ceb744 |  | LU | 2026 | 2
1120000679 | fc7b9297-b8d3-4365-861d-cd5f9da1ebd0 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 3a25a3a1-3e20-4ae0-953d-6e7c62059424 |  | LU | 2026 | 2
1120000680 | 99152c7b-c3bb-4f24-9464-1e8b447796e7 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 3fda6f06-5913-4653-9909-1fa6e8b0bdf5 |  | LU | 2026 | 2
1120000681 | 99152c7b-c3bb-4f24-9464-1e8b447796e7 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 77c39b77-cf28-44ed-9cdf-6cf86f3151ab |  | LU | 2026 | 2
1120000682 | 99152c7b-c3bb-4f24-9464-1e8b447796e7 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: d0caeac0-5577-4e04-9102-65d129b54cd6 |  | LU | 2026 | 2
1120000683 | 750c55f3-2edf-4af5-b70b-3fe07a130cd8 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 923c8925-d4ea-4cf7-a79b-6b429868c36d |  | LU | 2026 | 2
1120000684 | 750c55f3-2edf-4af5-b70b-3fe07a130cd8 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: d17c579b-df9e-4ed2-b152-c95b076913ef |  | LU | 2026 | 2
1120000685 | 3db39618-9780-4192-b06f-ccd9efb2313d | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 52858e80-300d-4a50-b21d-f89b9fae7eb8 |  | LU | 2026 | 2
1120000686 | 3db39618-9780-4192-b06f-ccd9efb2313d | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 787c8611-fdac-46f4-8664-5779641552a3 |  | LU | 2026 | 2
1120000687 | 275db486-5fb1-4b68-8c90-b59e4e4c3977 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-31 |  | 2030-10-30 | Level 3 |  | Reinspection Date: 2025-10-31, Work Order ID: 7b0c32cb-b86f-4ec7-9566-10f1baa59db3 |  | LU | 2026 | 2
1120000688 | 32a69599-8ab4-4bc9-af4a-2992c004a64a | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 520548d7-1402-45a9-8298-55fd757b77bb |  | LU | 2026 | 2
1120000689 | 372b38ac-4489-4a29-ae5d-68c311ac2e7c | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 |  | 2025-10-31 |  | 2030-10-30 | Level 3 |  | Reinspection Date: 2025-10-31, Work Order ID: 441ab098-066b-441c-a72e-11c443553462 |  | LU | 2026 | 2
1120000690 | 316e3726-e6d3-4f0f-9d53-b3e401250bb3 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-03-20 |  | 2030-03-19 | Level 3 |  | Reinspection Date: 2025-03-20, Work Order ID: 34483887-107c-41f5-934b-3b45d8772afe |  | LU | 2026 | 2
1120000691 | 0504f15f-9bbe-497d-9d42-4061efaca3e3 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: b8d4159b-e60f-426b-b5b7-8b4b7e3d4d10 |  | LU | 2026 | 2
1120000692 | 61d0f50a-8eed-4b35-ab9e-95f9b7250cad | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 34f4b4c9-9a36-4bfc-af23-db967a7bf965 |  | LU | 2026 | 2
1120000693 | 6a8c90ec-f864-45c5-a42b-f80a92464239 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-10-02 |  | 2030-10-01 | Level 3 |  | Reinspection Date: 2025-10-02, Work Order ID: 29490024-362e-4ec9-aabf-0b45bbe22384 |  | LU | 2026 | 2
1120000694 | 6a8c90ec-f864-45c5-a42b-f80a92464239 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-10-02 |  | 2030-10-01 | Level 3 |  | Reinspection Date: 2025-10-02, Work Order ID: 4e18b4a8-27c8-4b2a-b959-ec4274ee3e81 |  | LU | 2026 | 2
1120000695 | c3e50670-932e-42fa-8a78-7b4c6b9fd501 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 20293c4c-4c01-4e5a-a39f-9b5664d33295 |  | LU | 2026 | 2
1120000696 | d04b9cb9-a155-4203-b95a-c4111bfebbd1 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: fe9aae75-fc68-4732-a0a5-7787b8da375e |  | LU | 2026 | 2
1120000697 | cba75e47-6f96-4558-9d85-e6d55a79ff4a | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000698 | b5417b2c-ffcb-4168-8363-e7046c6ab8d1 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-05-21 |  | 2030-05-20 | Level 3 |  | Reinspection Date: 2025-05-21, Work Order ID: 2288ec7f-32cf-4fe1-af9b-c5d4377118c6 |  | LU | 2026 | 2
1120000699 | af8dfd74-8f2c-4b62-9813-3fcb014ba1e9 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000700 | ffce0b2c-f625-452e-b352-208cbc4ae90e | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-31 |  | 2030-10-30 | Level 3 |  | Reinspection Date: 2025-10-31, Work Order ID: 2338d534-c195-40f9-910b-ef692e09749e |  | LU | 2026 | 2
1120000701 | ffce0b2c-f625-452e-b352-208cbc4ae90e | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-31 |  | 2030-10-30 | Level 3 |  | Reinspection Date: 2025-10-31, Work Order ID: 75a35594-0863-4efc-9c17-43f9fd119614 |  | LU | 2026 | 2
1120000702 | 67f30de6-2dfe-47f8-adf8-cfdf2c574940 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-28 |  | 2030-10-27 | Level 3 |  | Reinspection Date: 2025-10-28, Work Order ID: 5dbbb587-fbad-45a3-93e5-4235f68beaf1 |  | LU | 2026 | 2
1120000703 | 51396fed-485f-49e6-980d-509359a48aeb | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-30 |  | 2030-10-29 | Level 3 |  | Reinspection Date: 2025-10-30, Work Order ID: 7b938155-259b-4c85-a547-bd9465115857 |  | LU | 2026 | 2
1120000704 | 9602144c-b82e-4800-aa17-8d42a86d47e6 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-30 |  | 2030-10-29 | Level 3 |  | Reinspection Date: 2025-10-30, Work Order ID: 84cddf05-841e-4818-a148-7e8aa6373a40 |  | LU | 2026 | 2
1120000705 | 8bb2c126-9068-4690-ab94-4f64edd7f3ec | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000706 | 1a8c150c-cb0f-4073-84dc-16281aeeca13 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 |  | 2025-10-30 |  | 2030-10-29 | Level 3 |  | Reinspection Date: 2025-10-30, Work Order ID: 0f40888d-03f4-49f2-ae40-04725792ad9c |  | LU | 2026 | 2
1120000707 | 468e7a72-aac9-4875-b6c6-7ca17a809add | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000708 | 3bd7e6a3-8448-4505-ba5d-8afdba37f4b3 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | 2025-05-21 |  | 2030-05-20 | Level 3 |  | Reinspection Date: 2025-05-21, Work Order ID: 620bdaf2-e319-4d34-ac3c-60862a4c44fa |  | LU | 2026 | 2
1120000709 | 877e2245-f1f2-4e0a-998f-9f1ddef4f249 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 |  | 2025-06-12 |  | 2030-06-11 | Level 3 |  | Reinspection Date: 2025-06-12, Work Order ID: 5c362d2a-b902-4fbf-a2f1-5b8f67c8a3df |  | LU | 2026 | 2
1120000710 | 4e5364ad-f466-4420-85af-ccfcdfaa7346 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: bb4a6af8-51d2-432b-a98d-79fe2fbf7dab |  | LU | 2026 | 2
1120000711 | 6d4e04e6-91fd-44ad-922e-62012c0d31a8 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120000712 | 4b3e5fae-782d-47a1-89a6-d04cbdc741b2 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 52d3c17f-41b5-42ca-8f1c-31517e701df1 |  | LU | 2026 | 2
1120000713 | 26fd6453-11a5-42c2-b8aa-d56d697e6b87 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: c4b378ca-4ee1-45d1-90b4-ec05cb40146b |  | LU | 2026 | 2
1120000714 | 26fd6453-11a5-42c2-b8aa-d56d697e6b87 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: da319bd9-90d6-4ee6-aade-c763962a463c |  | LU | 2026 | 2
1120000715 | 2024979d-c021-487a-a2fa-a2e6d07a09c6 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120000716 | dea6c55b-5a7d-4ea9-8328-02f98cb4dd26 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: 4bb76178-0beb-45bb-9251-ca30c1b3e68b |  | LU | 2026 | 2
1120000717 | d7c4dcca-103b-4c46-b3df-6d74fe5e9197 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: f981b049-de8d-466a-b0f4-5cffbb63024e |  | LU | 2026 | 2
1120000718 | e7b1d051-16a0-401b-858e-4bb199fb7225 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: f4749d0b-90b8-47fe-9c13-2f9b92b07039 |  | LU | 2026 | 2
1120000719 | fac6a3a0-75c0-4c0e-ad42-252501c6f847 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000720 | 6863321c-b27f-49b7-9b9b-765881710f1b | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 |  | 2025-03-04 |  | 2030-03-03 | Level 3 |  | Reinspection Date: 2025-03-04, Work Order ID: 5bc725e4-30d9-4393-8d97-4951c6b6e988 |  | LU | 2026 | 2
1120000721 | 8eddc616-56e7-495f-bb7d-c5fe14e9b934 | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000722 | 92eebad6-5db7-4f90-8832-322969bc68eb | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 4041ac2d-a04b-46a4-a0e1-6d50dce50623 |  | LU | 2026 | 2
1120000723 | 843fc9b1-533a-46ca-876d-d2c69d8ca972 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: 655eea07-8d23-4438-8a50-8932fc66a0a8 |  | LU | 2026 | 2
1120000724 | 67e20d48-a27b-45aa-983f-f2f6a7205866 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 754f08d9-0085-481f-944e-7b31ad58d3c0 |  | LU | 2026 | 2
1120000725 | 65edb13a-6772-482d-917c-96e9d13661ab | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 35f13e01-fca9-46bc-a69d-e4f22745dafd |  | LU | 2026 | 2
1120000726 | 4d2db7f8-bc06-43ce-b5d2-4e329c4d053a | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: fc4cc117-ffbc-4670-b054-d537f7f11718 |  | LU | 2026 | 2
1120000727 | 52b3bb82-a148-4fe7-9809-3d3e3af5559a | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000728 | 5ea54344-9227-4726-b7bd-84551df8bf74 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: c4782b13-2895-43d2-a44b-c8237b064d69 |  | LU | 2026 | 2
1120000729 | 5ea54344-9227-4726-b7bd-84551df8bf74 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: db0890cd-f2b3-4e7c-a0d5-792ad6168e9f |  | LU | 2026 | 2
1120000730 | 061c8eba-3bb4-4ae2-b7f1-8549334a02f6 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000731 | 0ff71d5e-7acc-468e-8d48-3c954185ff1b | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 2530beed-ea55-43c0-947c-f99e633f50c4 |  | LU | 2026 | 2
1120000732 | 32aa8ed2-3a6e-4c77-bfba-98c0fdd454bb | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-26, Work Order ID: 128ebc0a-ed76-476f-99a7-de3e3abdeb2d |  | LU | 2026 | 2
1120000733 | 2f740d31-1fca-441f-972b-fc833b0459d1 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-30 |  | 2030-09-29 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 2eeebf1e-dd82-414c-978a-e17ef1983c9b |  | LU | 2026 | 2
1120000734 | 48944863-9355-455c-b31e-9e799dce7cac | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: 3a5a290e-0803-4d72-af7f-e88695304952 |  | LU | 2026 | 2
1120000735 | 48944863-9355-455c-b31e-9e799dce7cac | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 |  | 2025-09-26 |  | 2030-09-25 | Level 3 |  | Reinspection Date: 2025-09-30, Work Order ID: eb453c52-4074-4fa3-92bc-781309d0276a |  | LU | 2026 | 2
1120000736 | 399d295e-b8d1-4f71-a335-e7b2e9af42ed | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | 2025-10-17 |  | 2030-10-16 | Level 3 |  | Reinspection Date: 2025-10-17, Work Order ID: 9c4f944b-dfa7-449b-8d70-4754d9761540 |  | LU | 2026 | 2
1120000737 | 605e7139-bc15-4384-80a0-e9de124b5015 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000738 | f5523471-5f16-4f5e-b832-7c59917ca8fc | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 |  | 2025-10-17 |  | 2030-10-16 | Level 3 |  | Reinspection Date: 2025-10-17, Work Order ID: 404d1d7a-4302-4953-9acb-d35064e5f0cc |  | LU | 2026 | 2
1120000739 | a7b864e5-96ad-4fcb-8fe0-2a97a37e631c | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120000740 | 7d05c622-4a5e-4882-a671-a9fd262946b0 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120000741 | 279d1e14-2627-43da-8c7e-af99443f339f | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000742 | f13d4655-f3b0-47bb-82d5-09c840a3b9a3 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000743 | 2956fbb8-2b4d-4f3d-8950-2386873a3c59 | Pole | HFTD Tier 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000744 | 5ea6f806-94d2-45f8-afee-bfc21a9cbf00 | Pole | Non-HFTD | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000745 | a4681f11-8df9-4cab-9864-b15c560da8b8 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000746 | c4f945aa-aab0-4a0f-bc6f-4f279b5f19a3 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000747 | bd02502d-b6a7-4fc5-a3a0-615f40781bdb | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 97e4bae0-c622-4692-9880-db86b405daa6 |  | LU | 2026 | 2
1120000748 | 38b8cda4-4c09-4873-abd9-113c145665bb | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000749 | 0a7892d0-e1cc-49fb-88f8-147c3111999c | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000750 | 8ee6f7c2-e248-4b75-813a-f29ff833a560 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000751 | dae60379-6f06-412c-b840-9ea6044082c9 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120000752 | 54ccdac7-65e7-46aa-8772-7ac31e642101 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000753 | 011ec3be-637c-4c53-8455-19bd724131e2 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000754 | 3427a04e-af38-44c7-9dc0-03f25aea0c47 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000755 | 449a3fd9-6a15-4edb-adef-37eecac70186 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000756 | 57298da4-085e-4a72-9192-b84b02d621eb | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120000757 | 77a734b1-f825-4a0d-bfde-f8fef4f64205 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120000758 | b419a52d-bd16-45fa-92d9-24da7540126b | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120000759 | e707e466-721c-4732-9532-a9f6cc279846 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120000760 | c8d0333c-1ab8-4836-9766-032e21e4742d | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000761 | 0ca8a859-b5cb-4f82-b0c5-f891d553eb89 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000762 | 1357eced-8afd-4479-b82c-152944c3f572 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120000763 | 9dd4116d-078b-42f9-9b94-92ccf7f1ebd0 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000764 | ce61d46f-6e7f-4e8a-96ca-f5e12021aa28 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000765 | 7458865c-ccb2-4f54-82a2-011af5d3522b | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000766 | 46d1fafb-47ef-4b24-be4d-2d611d53b42f | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120000767 | d3e0b15a-ce35-4a71-811f-da58dc85a696 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000768 | c6a44c2d-b649-4509-ac88-16dff9f42731 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000769 | 6aecd5cc-ec4f-4005-8ec2-39d9fc3471cd | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 |  | 2026-04-30 |  | 2031-04-29 | Level 3 |  | Reinspection Date: 2026-04-30, Work Order ID: b47ec94b-f9e9-4827-a2ad-220665bcb918 |  | LU | 2026 | 2
1120000770 | 5f92a481-35f9-4857-b3f2-eb108755e8fc | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120000771 | c0342a13-3c7c-43a4-8cd9-4783348a622e | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | 2026-04-29 |  | 2031-04-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 81b98e17-4323-4943-8c07-18f5ec57baa5 |  | LU | 2026 | 2
1120000772 | c0342a13-3c7c-43a4-8cd9-4783348a622e | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 |  | 2026-04-29 |  | 2031-04-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: c3956cc8-add5-4ee4-8869-8966df2cfd73 |  | LU | 2026 | 2
1120000773 | 026d47dc-553a-4ff9-a20f-23e44e64751b | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000774 | 6174cbac-8fdb-4ae3-b78d-5f6eb97ec6c9 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 4e8314ac-156e-4881-b6d0-08243c38aef7 |  | LU | 2026 | 2
1120000775 | 6b877e8d-8acc-4e10-b718-5eb75c248112 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000776 | 23abc9ef-a407-4be2-88d6-da30e2bf142a | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 22669295-b6a7-4621-be14-41039abc9e3a |  | LU | 2026 | 2
1120000777 | 23abc9ef-a407-4be2-88d6-da30e2bf142a | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: a464ee6f-0a1b-45f4-9b6b-49fc4b01bcf9 |  | LU | 2026 | 2
1120000778 | e3ac7da8-07e2-4438-a951-c86442a73d84 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 6c175699-0755-4e17-91b0-5563961a7bfc |  | LU | 2026 | 2
1120000779 | d18c0f68-86ad-47d6-8ac3-25f67cb09a70 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: 34fcea4c-4ea9-42a5-aeef-ede60b87ef9a |  | LU | 2026 | 2
1120000780 | d18c0f68-86ad-47d6-8ac3-25f67cb09a70 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: 5edaa646-2d70-42fb-bd52-1a9a27114c45 |  | LU | 2026 | 2
1120000781 | d18c0f68-86ad-47d6-8ac3-25f67cb09a70 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-29, Work Order ID: cbd246ee-fa7a-467f-b457-0eb55575afe8 |  | LU | 2026 | 2
1120000782 | 1b926a1c-9239-4abc-8ee1-e5ab9e66a9a1 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: a80a1db3-46d1-451f-9985-1f066a4a8b1e |  | LU | 2026 | 2
1120000783 | 1b926a1c-9239-4abc-8ee1-e5ab9e66a9a1 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2025-07-29, Work Order ID: cf874bd9-cffa-40a9-95f1-9246045f9e49 |  | LU | 2026 | 2
1120000784 | 1b926a1c-9239-4abc-8ee1-e5ab9e66a9a1 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 |  | 2025-07-29 |  | 2030-07-28 | Level 3 |  | Reinspection Date: 2026-04-28, Work Order ID: f4cfb014-889f-4781-aaae-1ab313928af9 |  | LU | 2026 | 2
1120000785 | 5072ce8d-9834-4add-a63d-e52acb103917 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000786 | d62e6a75-c027-43cf-8050-942c0ec6b8dc | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | 2024-01-11 |  | 2029-01-09 | Level 3 |  | Reinspection Date: 2024-01-11, Work Order ID: |  | LU | 2026 | 2
1120000787 | d62e6a75-c027-43cf-8050-942c0ec6b8dc | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 |  | 2024-01-11 |  | 2029-01-09 | Level 3 |  | Reinspection Date: 2026-04-09, Work Order ID: 11baefb7-1f8d-46f8-9c33-485cbfff3d39 |  | LU | 2026 | 2
1120000788 | 0004ef32-55de-4796-a5d2-ef0815b5b4d5 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000789 | 1c1a3677-ba9b-49d0-a429-8e1417474d26 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000790 | 021d295e-4bc2-409a-8246-30dabaed4fac | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: 235b262e-7670-4ab2-9ebe-0274bf959891 |  | LU | 2026 | 2
1120000791 | 29943d00-6868-41ad-942d-a31600988523 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: cb40faa9-efa2-46f1-96c3-46e49c8bf1c0 |  | LU | 2026 | 2
1120000792 | 577dcb2e-c63d-495a-8fc5-68469d4ad6c6 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: 7375ce26-9779-441a-b6e4-9c174fec2630 |  | LU | 2026 | 2
1120000793 | 66808a8f-4e1f-46e2-a9e3-26cd1d56fa71 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: 6df77b10-adf0-401d-9f0f-b4871e2210c6 |  | LU | 2026 | 2
1120000794 | 66808a8f-4e1f-46e2-a9e3-26cd1d56fa71 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: 821afa30-abf8-4112-9bb6-8469229d75cf |  | LU | 2026 | 2
1120000795 | 2634a699-80f6-45d1-a784-f44573023fc4 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: ce8c1475-e2cc-4e82-84f5-1210c21be328 |  | LU | 2026 | 2
1120000796 | b8121adf-8c3f-4a33-8698-8fb206a9a718 | UG Transformer | Non-HFTD | Distribution | 2022-06-17 | 2027-06-16 | Level 3 |  | 2026-06-26 |  | 2031-06-25 | Level 3 |  | Reinspection Date: 2026-06-26, Work Order ID: e0378c5d-9c8c-4afb-a1f8-d5e0aa686f84 |  | LU | 2026 | 2
1120000797 | ced9162a-2b0c-4082-b796-2b678cbf2c06 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | 2026-06-26 |  | 2031-06-25 | Level 3 |  | Reinspection Date: 2026-06-26, Work Order ID: b4030c08-cfc5-489d-9581-13d6924fd73d |  | LU | 2026 | 2
1120000798 | edf775bc-9d7b-4a7c-b533-cec7cc2aeb91 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000799 | 2e010461-57e8-4e27-b212-0d7603dee877 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 |  | 2026-06-26 |  | 2031-06-25 | Level 3 |  | Reinspection Date: 2026-06-26, Work Order ID: 160e181f-ccc5-4c9d-8160-299b8c6035c0 |  | LU | 2026 | 2
1120000800 | 5ff51a71-1123-4167-a8f1-9b8cdb1bc2e2 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120000801 | eff15701-7c3c-4633-93f6-23987c2b383e | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | 2025-08-27 |  | 2030-08-26 | Level 3 |  | Reinspection Date: 2025-08-27, Work Order ID: 3a2bdb6d-8b05-469a-a1a8-bee5c7bc0ea6 |  | LU | 2026 | 2
1120000802 | eff15701-7c3c-4633-93f6-23987c2b383e | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 |  | 2025-08-27 |  | 2030-08-26 | Level 3 |  | Reinspection Date: 2025-08-18, Work Order ID: fecc38e0-3953-4d38-8192-4e0f3a3e9f0f |  | LU | 2026 | 2
1120000803 | f3a74b06-ca89-44fc-9aa2-970b8f01b5ab | Other (Describe) | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000804 | f2144e7c-b2f0-4a5b-b261-25ea32aa872d | Other (Describe) | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120000805 | ed42748d-cde4-4cea-8306-63913d379ec9 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000806 | a045f6a4-5a5f-4005-a009-1d3e74085d87 | Riser | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000807 | 0230ef7a-cff2-4bc8-839a-9dcf7772fa92 | UG Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2023-06-30 | Level 2 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: 1902e221-0adf-4d32-9764-ea82937c8c0a |  | LU | 2026 | 2
1120000808 | 75bebe98-40a9-4f8d-a4e4-e4f0ab6a6409 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 |  | 2025-08-20 |  | 2030-08-19 | Level 3 |  | Reinspection Date: 2025-08-20, Work Order ID: 6ee4f353-7a2b-470b-9788-a3100ec2394a |  | LU | 2026 | 2
1120000809 | 737883d5-c881-49dd-a4ba-11d018923726 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000810 | 65ba05e4-df32-4bd9-b04d-3fec4db659d2 | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | 2025-02-27 |  | 2030-02-26 | Level 3 |  | Reinspection Date: 2025-02-27, Work Order ID: b32bdcfc-08e1-4414-9187-c5a7ab5d081c |  | LU | 2026 | 2
1120000811 | 342f77b9-e2fd-4c57-ba57-5eb78637c108 | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | 2025-02-27 |  | 2030-02-26 | Level 3 |  | Reinspection Date: 2025-02-27, Work Order ID: c7348b36-4ac1-4c31-bdfd-7f1310426de6 |  | LU | 2026 | 2
1120000812 | 3ab6c00a-099a-413e-80c5-82d1f07d6d3c | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | 2025-02-27 |  | 2030-02-26 | Level 3 |  | Reinspection Date: 2025-02-27, Work Order ID: 2634f999-e8c8-4109-854c-f29d3c993017 |  | LU | 2026 | 2
1120000813 | f89d945a-9a47-41dc-af83-9bce8e9f70ca | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 |  | 2025-02-27 |  | 2030-02-26 | Level 3 |  | Reinspection Date: 2025-02-27, Work Order ID: 41a3aac3-2668-4a55-a3b4-e30d9f269fa8 |  | LU | 2026 | 2
1120000814 | e98435bf-aa05-43b3-9a33-d6085b5cd7f7 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: b971fd85-4fd6-47a3-82a9-d13e2c944615 |  | LU | 2026 | 2
1120000815 | 92530485-8c67-4892-827b-293d16760fab | Riser | HFTD Tier 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120000816 | 8d3dc34c-219c-4200-b6bf-bfcaf2aea6db | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2023-07-16 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 7168d06a-233e-4816-b9e7-ff7174d10e4b |  | LU | 2026 | 2
1120000817 | cf94f441-6ce3-4753-909f-b4d2526168e0 | UG Transformer | Non-HFTD | Distribution | 2022-07-16 | 2023-07-16 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 1d7a0288-fa19-4017-99d6-48a05d4980bd |  | LU | 2026 | 2
1120000818 | ba98a25d-f5f8-492a-abb7-8c54732f1ef8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000819 | 3982e6de-9c23-4af3-8ca5-c90f9d0cfee8 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: e1f8d977-8147-4e75-ac89-711d47479092 |  | LU | 2026 | 2
1120000820 | 4756537b-22c0-4779-8823-c7938b06c36d | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 |  | 2026-06-26 |  | 2031-06-25 | Level 3 |  | Reinspection Date: 2026-06-26, Work Order ID: ba786b36-9df7-4049-80f4-1bf820aea8b8 |  | LU | 2026 | 2
1120000821 | 3cbd90aa-9655-4e4f-a4ec-802bedc5e9d5 | Riser | HFTD Tier 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000822 | 5621a3df-f5c6-4921-9d74-96aaac526093 | Riser | HFTD Tier 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000823 | 9d1360b0-d78b-4956-b9a7-c3cff338b71e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120000824 | b4c00fa9-e2d6-467d-9da7-1477bf4ad733 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120000825 | 6395d381-8e2b-4d7e-8024-a8f960e4e55d | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: da701e90-945d-46ed-9640-b4320d3d3937 |  | LU | 2026 | 2
1120000826 | 3d079c3a-9636-4778-b33c-511362fa8161 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | 2025-11-06 |  | 2030-11-05 | Level 3 |  | Reinspection Date: 2025-11-06, Work Order ID: 0b498bc1-1f67-4028-95e6-7d6c72a72214 |  | LU | 2026 | 2
1120000827 | 3d079c3a-9636-4778-b33c-511362fa8161 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | 2025-11-06 |  | 2030-11-05 | Level 3 |  | Reinspection Date: 2025-11-06, Work Order ID: 1d3c8456-bab1-4b99-9af2-4bdc9c42cbd8 |  | LU | 2026 | 2
1120000828 | 2bf0c766-91ee-41c6-9908-761279414d53 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 |  | 2025-11-04 |  | 2030-11-03 | Level 3 |  | Reinspection Date: 2025-11-04, Work Order ID: ce826a00-eb1d-4117-9f7a-d039d35bb874 |  | LU | 2026 | 2
1120000829 | 36d50287-264a-485c-ac26-08922c80b25b | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | 2025-11-06 |  | 2030-11-05 | Level 3 |  | Reinspection Date: 2025-11-06, Work Order ID: 1de03acc-64c2-4aaa-b4c2-55ff0c58fb7e |  | LU | 2026 | 2
1120000830 | 602b9bb1-ccf4-4ad9-9434-5e3119dcb8aa | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-13, Work Order ID: abdec1b7-a22d-4c3e-abcb-315cbbddfdbc |  | LU | 2026 | 2
1120000831 | 67bd32c8-2519-4339-b8c9-ec74cf32d1d3 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: be564ec9-1b5a-41a7-a50f-3fa464a8eca3 |  | LU | 2026 | 2
1120000832 | fe3bc5e6-ca95-4956-888e-439034857f0a | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | 2025-11-06 |  | 2030-11-05 | Level 3 |  | Reinspection Date: 2025-11-06, Work Order ID: 140ae8fe-3534-4cdc-835f-8d3f7cfaabe1 |  | LU | 2026 | 2
1120000833 | d1ddb158-7958-4b45-accf-cf9486c494fe | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2023-07-27 | Level 2 |  | 2025-08-14 |  | 2026-08-14 | Level 2 |  | Reinspection Date: 2025-08-14, Work Order ID: 638cc35d-4039-4a5e-b778-b8224d13bb92 |  | LU | 2026 | 2
1120000834 | 9e7ecdf4-4653-42ac-ad6d-850829b6f1d6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120000835 | 9bf34abf-2bc5-4b69-970a-776399848125 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: bddcc2c0-d1f2-4448-9511-763c7d829bea |  | LU | 2026 | 2
1120000836 | 861b19f4-6d5c-4e9c-9ba3-2c6ccad098db | Riser | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120000837 | 2db13002-dcf5-4bb3-ae9c-5a869ca4f460 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2023-07-29 | Level 2 |  | 2025-08-14 |  | 2030-08-13 | Level 3 |  | Reinspection Date: 2025-08-14, Work Order ID: 56f24559-22eb-40c2-bbfe-3f2141be0b6c |  | LU | 2026 | 2
1120000838 | e5687798-66d1-40cd-91a7-d3da0ce5a4b4 | Riser | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120000839 | f05e702b-cd7b-4ea9-ab85-75f5ef776923 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: b497f530-8770-47e0-a21c-8eebde9fbb19 |  | LU | 2026 | 2
1120000840 | 2b88e9fb-eccd-419b-b6e7-1789a08f4201 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | 2025-09-22 |  | 2026-09-22 | Level 2 |  | Reinspection Date: 2025-09-22, Work Order ID: 3708313c-ece0-431e-b2fc-172af45873e9 |  | LU | 2026 | 2
1120000841 | 2b88e9fb-eccd-419b-b6e7-1789a08f4201 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | 2025-09-22 |  | 2030-09-21 | Level 3 |  | Reinspection Date: 2025-09-22, Work Order ID: 4fa5c225-3fef-49d3-b9f4-846a6533e0b0 |  | LU | 2026 | 2
1120000842 | 0cfbf23d-c2eb-4881-8ce6-44cbbc2125fa | UG Transformer | Non-HFTD | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 01591a62-29c8-488e-a597-fe70fc10656a |  | LU | 2026 | 2
1120000843 | 0cfbf23d-c2eb-4881-8ce6-44cbbc2125fa | UG Transformer | Non-HFTD | Distribution | 2022-07-30 | 2023-07-30 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-12-01, Work Order ID: a89c2d5f-99e4-44f4-8051-edc1287dedd0 |  | LU | 2026 | 2
1120000844 | 17ee48fa-7ff5-4904-b32b-48e0c78fe8b2 | UG Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 |  | 2025-08-12 |  | 2030-08-11 | Level 3 |  | Reinspection Date: 2025-08-12, Work Order ID: cd9d3755-cd7f-4ada-b7d4-2d59ee9e85d1 |  | LU | 2026 | 2
1120000845 | 730267e1-2afa-4ee9-b96f-a6aabc2f7b0d | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 |  | 2025-08-19 |  | 2030-08-18 | Level 3 |  | Reinspection Date: 2025-08-19, Work Order ID: 9ba3030c-0c44-48dc-ac9e-7f5ab49cb56d |  | LU | 2026 | 2
1120000846 | 6b3635c4-1fbe-46ba-a33c-a665b7199004 | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: aed627f1-7552-446c-bced-c1cd409d7ad7 |  | LU | 2026 | 2
1120000847 | fc590529-2aec-4a7c-b7cb-607001aecd1a | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-20 | 2023-08-20 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 8ee52c05-b58f-4e29-9da6-205b311927eb |  | LU | 2026 | 2
1120000848 | d85f0d19-5d87-4773-be35-31b72fa03195 | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 06bbada5-d95d-4349-9550-d0c5776c8e36 |  | LU | 2026 | 2
1120000849 | c3bbd04d-bb34-48a1-9663-6544270b056f | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 22c4f1e9-7465-447b-a946-a7c8855c670e |  | LU | 2026 | 2
1120000850 | 30cc459a-43eb-4c66-8671-c5a7f4f3bef3 | UG Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 |  | 2026-06-29 |  | 2031-06-28 | Level 3 |  | Reinspection Date: 2026-06-29, Work Order ID: 5810031f-1a91-4d8e-aa62-9f84cd4031df |  | LU | 2026 | 2
1120000851 | 58942f1a-5036-44b2-91b6-f30a3ef7760f | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000852 | 5bdf31cc-12ba-40bd-945b-df6d16365a4b | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000853 | 89926fbb-cae6-49c3-b81a-361100e2f151 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000854 | 0e390fe4-c150-4bb1-bd86-8ee5d6a963ca | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000855 | adef5ec6-94cb-4749-aa95-9a009b4f90c3 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000856 | e4d54697-90b4-4c0f-8054-564699302bad | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000857 | 1d870439-b07c-4d3b-bd87-e32e995d0f1d | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000858 | 6683fc71-8b48-4287-b7c9-05b6e14e884c | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000859 | 603c4036-e86a-4ab3-8508-2af5613496a9 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000860 | 7922db2e-c76c-48bf-a145-26f598dd418e | Pole | HFTD Tier 2 | Distribution | 2023-06-21 | 2028-06-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000861 | 7b8de552-de6b-423c-b17c-5399a2c3523a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 |  | 2025-10-01 |  | 2030-09-30 | Level 3 |  | Reinspection Date: 2025-10-01, Work Order ID: 0d0cb508-c5d5-49b1-8c90-9ca27b744857 |  | LU | 2026 | 2
1120000862 | 10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000863 | 10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120000864 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000865 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000866 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000867 | 880fb73d-b44a-4791-9c41-3ef1915f5d9a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 |  | 2023-12-18 |  | 2028-12-16 |  |  |  |  | LU | 2026 | 2
1120000868 | c618249e-bd23-42e3-9e22-24574206a77f | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 |  | 2025-10-20 |  | 2030-10-19 | Level 3 |  | Reinspection Date: 2025-10-20, Work Order ID: 81651a64-62b0-490d-93af-6c2b8d5cf626 |  | LU | 2026 | 2
1120000869 | f7e80e6f-2126-4172-9014-896e3736ba47 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2026-09-23 | Level 2 |  | Reinspection Date: 2025-09-23, Work Order ID: c1624f3d-a46a-4b39-a5ea-59d2c2af3018 |  | LU | 2026 | 2
1120000870 | f7e80e6f-2126-4172-9014-896e3736ba47 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: c6d57341-c0b0-4b73-a2a6-a077e14a80a9 |  | LU | 2026 | 2
1120000871 | 521935b7-65b2-4738-9fff-2d5f304797c8 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 161ad7e0-a25d-4cf9-9140-59ef7d41713f |  | LU | 2026 | 2
1120000872 | 521935b7-65b2-4738-9fff-2d5f304797c8 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: f48b54b7-af68-4f97-a16f-71a562ad95e4 |  | LU | 2026 | 2
1120000873 | 0f501815-6c4e-425f-9656-cbac6b9447ca | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 13dc9fa4-ab0a-4024-b343-69b51c036ed0 |  | LU | 2026 | 2
1120000874 | 0f501815-6c4e-425f-9656-cbac6b9447ca | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: daa2cc54-78ca-4fd9-bc3d-4cf4503641e7 |  | LU | 2026 | 2
1120000875 | 43d6cc09-8082-4d8c-9a76-526d681bfcd0 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 025d20e5-f409-48b0-b165-6f02fff11ef6 |  | LU | 2026 | 2
1120000876 | 43d6cc09-8082-4d8c-9a76-526d681bfcd0 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 3cc5c8d7-d7be-4488-bc3a-64d6632a39fc |  | LU | 2026 | 2
1120000877 | 43d6cc09-8082-4d8c-9a76-526d681bfcd0 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 |  | 2025-09-23 |  | 2030-09-22 | Level 3 |  | Reinspection Date: 2025-09-23, Work Order ID: 76ee8f6e-367f-4d5d-961f-bf7f4eabe24a |  | LU | 2026 | 2
1120000878 | 3e326912-ac6a-4eaa-b012-d6d799777bd5 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000879 | 48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000880 | 48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000881 | 2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | 2023-11-15 |  | 2028-11-13 |  |  |  |  | LU | 2026 | 2
1120000882 | 2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 |  | 2023-11-15 |  | 2028-11-13 |  |  |  |  | LU | 2026 | 2
1120000883 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [8 empty] | LU | 2026 | 2
1120000884 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [8 empty] | LU | 2026 | 2
1120000885 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2028-10-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000886 | be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120000887 | be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120000888 | ae9bc4da-b916-4258-952e-8a9000986684 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120000889 | beaeb331-4794-4c6b-afb2-3de498581578 | Pole | HFTD Tier 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2 |  | 2025-12-18 |  | 2030-12-17 | Level 3 |  | Reinspection Date: 2025-12-18, Work Order ID: 40c75c3b-20d4-43cf-956f-8d78e88ab487 |  | LU | 2026 | 2
1120000890 | 3f547d7f-c752-4412-8bc0-76c15d53d6e4 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000891 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000892 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000893 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000894 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000895 | 64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000896 | 6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000897 | ef0d7626-593c-4c4e-a005-4b0bcf7eb222 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000898 | c7efe317-ec09-4cf1-8df1-eba14aef8c92 | Pole | HFTD Tier 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000899 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000900 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000901 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000902 | 380fa61b-d30a-4c68-b4ea-e65dfb919c74 | Pole | HFTD Tier 2 | Distribution | 2024-02-29 | 2029-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000903 | b1ef0c83-bdc0-442a-87cb-9f2ed12dbefe | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120000904 | a3dc23c7-095b-4ea9-b2a4-e9f7df5d5cfd | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000905 | 1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000906 | 1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000907 | 613d0b2c-9d20-4454-8f55-e08ac74e678b | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000908 | f85c7d00-0b40-4291-bfe3-8fbb4ba7626c | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120000909 | 6c28ca20-e409-4a24-9e9a-5d008eb8b314 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120000910 | 85a994ee-218a-4a63-9a51-21ec1db3c9b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120000911 | 04f4d012-143b-4395-b60e-0b6101d9ddf7 | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120000912 | ec67a7ca-4c76-4298-a25d-7f99ec5d8a7b | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000913 | 4cdbca96-ad2f-4657-9032-934c15f6630a | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000914 | 076f89b7-7432-4a4f-8808-17afc7a7570a | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000915 | ef8f1f0e-243b-4436-9177-c42b499d58bf | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2029-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000916 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000917 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000918 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000919 | 7db8e149-37f6-428e-b892-a52c34ad2704 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000920 | eb2f4621-499f-4eb5-a075-ce7cc9297c24 | UG Transformer | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000921 | fbaff4c1-96e3-44c3-bb60-c466472bd1db | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000922 | fbaff4c1-96e3-44c3-bb60-c466472bd1db | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000923 | 178b60a9-1fca-41da-a4e8-4443065e0e9d | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000924 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120000925 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120000926 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120000927 | 24fbd4f8-4f61-4bd7-ae1a-90e1269a36fb | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120000928 | 6a8493a7-c56f-489d-8f87-84cfe96541c2 | Pole | HFTD Tier 3 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000929 | 525c4a88-5f5f-45fd-b63d-c146305815ee | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 0686b8df-53f1-47ed-82c7-19f395617d70 |  | LU | 2026 | 2
1120000930 | 525c4a88-5f5f-45fd-b63d-c146305815ee | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2024-11-07, Work Order ID: c728fa43-1c42-4ebe-b00f-dc3b1096e2bf |  | LU | 2026 | 2
1120000931 | 8864d6dd-5a66-49fa-9f57-74c13da15119 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000932 | 8864d6dd-5a66-49fa-9f57-74c13da15119 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000933 | 2d0254bf-5e99-4834-97bf-7e1339033db9 | Pole | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000934 | 4bb3f2dd-894f-4e59-942b-b542b708b705 | Pole | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000935 | cb48ad7b-0587-4e0c-851c-5220410f5e2b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: fb4c4398-0368-4429-8c26-4f8a91917001 |  | LU | 2026 | 2
1120000936 | c07ffae7-69a5-49d9-8480-dd336783993a | Padmount Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 32489429-4770-4c79-8279-161bb7c71ff2 |  | LU | 2026 | 2
1120000937 | c07ffae7-69a5-49d9-8480-dd336783993a | Padmount Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 409bbf2b-7e62-4070-86fe-5c9fe67a3b2b |  | LU | 2026 | 2
1120000938 | c07ffae7-69a5-49d9-8480-dd336783993a | Padmount Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 6adfa3bd-45cf-45a1-92fa-aac47d2de050 |  | LU | 2026 | 2
1120000939 | 49f88f71-c6fc-4d0d-993b-94a316a1401f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 99496d68-6c78-47d3-81e0-98eda5262608 |  | LU | 2026 | 2
1120000940 | 3697255f-ab0f-4275-acdc-40cc96afc2d4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 2ee4480a-7e99-42a6-aef6-07f147dde593 |  | LU | 2026 | 2
1120000941 | 9a206726-1e50-4c7c-bdc3-75f7a973eff7 | Padmount Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 5fbda450-46e3-4e8c-9844-e82f8045ca4c |  | LU | 2026 | 2
1120000942 | 6a87a042-dccc-47e2-8f53-7622ced9f689 | Padmount Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 482b1233-f7de-4acb-8fae-dd9166f18533 |  | LU | 2026 | 2
1120000943 | 50b35d34-8510-4508-b109-9ffb13c59a5e | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000944 | 50b35d34-8510-4508-b109-9ffb13c59a5e | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120000945 | 7748dd36-8aa6-4b87-9359-d958686326f6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: a91f1e85-73c9-475c-a239-58a8c59e0ca6 |  | LU | 2026 | 2
1120000946 | f765ed55-f6ea-4444-bffc-1b951ed17615 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 9f430503-dd16-4837-ad11-b9ab107866a9 |  | LU | 2026 | 2
1120000947 | 9221e35a-edc8-47ef-8ca4-9542949c6dbb | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-13 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: d6964d73-f98a-4f39-a075-2106a0f0a7e1 |  | LU | 2026 | 2
1120000948 | f870a5bb-0694-48a2-92bb-987697265c56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 1e53b880-e0fd-4216-ad4f-185d45d17b56 |  | LU | 2026 | 2
1120000949 | a74e66e9-af39-41e6-849b-6ffa0d714c1c | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000950 | 13242277-6dbf-4752-82bd-6d59fd7ab27f | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000951 | e53bbab2-7890-442d-932d-e000041df083 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120000952 | 21146fa0-6daf-47ce-8b15-b9096c6bf25b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000953 | 360e1296-4534-49df-8be2-9f5cc277893e | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000954 | 55273612-0cbd-4f37-833a-c6707443f248 | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120000955 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000956 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000957 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120000958 | bc2c6791-61e0-4bad-b496-95784c10e72e | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120000959 | ed809408-b368-4b57-9a21-6ff964711263 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120000960 | df810e4a-eca1-4bc4-95fc-671a5f467a95 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000961 | 7ed765a6-2774-4657-808d-a0129c45c337 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000962 | 87274764-f32f-4a23-9a4a-67a198ba980a | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000963 | 064e0681-ab18-4da5-9251-7b24d7e6cb09 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120000964 | 0d5d9b57-b55d-4208-b8b0-784773aa7ae0 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000965 | 1afd68f7-cc90-45bc-98ad-464051f54749 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120000966 | 889f4ac9-ae97-4196-9216-3411d3e839bb | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000967 | 889f4ac9-ae97-4196-9216-3411d3e839bb | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120000968 | 4cf15d2e-7662-45b2-9a58-f384041a280d | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000969 | 126f2e3a-d1e5-4dba-a1da-3d04dc46d94e | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120000970 | 7808dbc6-3d87-4738-a29e-057f952f2b5a | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000971 | f6321919-385c-4f4a-a65e-7611c8beb1ad | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120000972 | afb2fa38-c60c-4524-9ba1-c67a1015bcad | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120000973 | afb2fa38-c60c-4524-9ba1-c67a1015bcad | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120000974 | 818f16fc-3640-46ef-938b-6d848fe3f253 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000975 | 9b021d0f-8282-45a9-8bcb-d8260074ea3e | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000976 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000977 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000978 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000979 | 2750fb51-f4df-46fe-be2f-fada05ab70be | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000980 | 2a833ae7-dd6e-47da-bb72-61f050278a45 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000981 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000982 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000983 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000984 | 410c96b9-1d03-4557-ab41-c9de07bbf181 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000985 | 410c96b9-1d03-4557-ab41-c9de07bbf181 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120000986 | 101b3959-e140-46f1-8101-531a8ec78ea6 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000987 | 0b871fed-849f-4203-b08f-bf783be13cec | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000988 | 0b871fed-849f-4203-b08f-bf783be13cec | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000989 | 6a5aeed2-1a35-41ec-87dd-27480fe74f42 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000990 | 6a5aeed2-1a35-41ec-87dd-27480fe74f42 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000991 | 6d8a7834-7714-4d38-8da5-1e24dcf0f3ee | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000992 | e2e1b9b9-f4dd-497c-ab9d-0e42b0cd3e6d | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120000993 | efdf1269-fa47-4d02-8278-fd92c77252f7 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000994 | f5bf4487-9c26-4e8d-99c4-33485afbc426 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000995 | 5c0ec0d7-0e00-4336-851d-32f7d083c3f6 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000996 | 5fce6e63-3e8a-4c5b-b678-c103216964f0 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120000997 | 67d33fde-5979-4079-a0aa-d93dfb119ca2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120000998 | 67d33fde-5979-4079-a0aa-d93dfb119ca2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120000999 | e7e9720e-a30c-49d2-b560-fe06328484ce | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001000 | e7e9720e-a30c-49d2-b560-fe06328484ce | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001001 | 117eb034-d5c4-4a03-bbed-e177ea9a090d | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001002 | 117eb034-d5c4-4a03-bbed-e177ea9a090d | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001003 | 420f064d-37ee-437c-8837-3763579b0450 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001004 | 420f064d-37ee-437c-8837-3763579b0450 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001005 | 088eab05-d496-4cb6-8c66-d8942a174fb8 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001006 | 24d251a3-14f9-4853-9bfa-4c2737012fe1 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001007 | a41d8aae-a14b-456e-b147-408245a343e3 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001008 | a3b092ec-843b-493c-81f6-3bd457c3d50c | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001009 | cb043f54-c80f-47b7-abe2-f5c8e0888c7c | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001010 | 0597cc9e-7216-4cec-ba41-79209e7660f8 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120001011 | 047dd912-6c71-4cf8-b96f-e575ea777e56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: b60f6ca3-7bfc-4fe6-900b-d0721df60de2 |  | LU | 2026 | 2
1120001012 | 379941f4-71c5-447c-be67-c75837271cdb | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001013 | dc4dec6d-9add-4264-aab9-53aad72a83eb | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: a313fe0a-b913-447a-94bf-a447b96d302f |  | LU | 2026 | 2
1120001014 | 317de1bb-d14a-4785-8309-060ffaf40f04 | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001015 | 6c05f561-c5e7-4fa5-bbaa-6b8efab5a1a5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: f4748eff-2a2b-43e2-aea9-5d678d63d871 |  | LU | 2026 | 2
1120001016 | 9da3e9d9-022a-4a3f-9279-9a4a8f0e2272 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001017 | c40519e7-4395-41f5-9c87-b6b03b249249 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001018 | c40519e7-4395-41f5-9c87-b6b03b249249 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001019 | 477dce3b-f593-45d1-9c03-864a7beba9da | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001020 | 894dff3c-0490-4549-beb9-49039df01598 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2025-08-16 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 8cdccd50-62a6-4a74-bec7-0ab58ca6dbef |  | LU | 2026 | 2
1120001021 | 8dcf29db-3601-46c2-901b-e02c6e030791 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: b2fb0d53-ad22-4134-a244-9a8b8e0b7cb4 |  | LU | 2026 | 2
1120001022 | 02046b06-9a07-41d6-8eff-aa93f8e993a9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 011150c3-478a-419a-ac0a-c101bdc19ad4 |  | LU | 2026 | 2
1120001023 | f5b898b8-a6db-4efa-a622-fee4687acc2d | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001024 | 9b91fa0d-a7cf-49c3-9be7-fc46c86dd8c3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-27 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 7c2a7cfd-a628-4516-9976-a2dde7c6e0a8 |  | LU | 2026 | 2
1120001025 | 113d2d12-c28e-40c5-922c-35f57589739e | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001026 | 26887caf-d722-4a80-948f-dc947af8318e | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 435fe0a3-21ba-4947-bde2-2658b33a9c8b |  | LU | 2026 | 2
1120001027 | 6f7a17fd-0406-401a-9cc4-94bf8ab22874 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 68a99993-f8d4-41b7-baed-78bb207d1570 |  | LU | 2026 | 2
1120001028 | 70e5e648-2836-499a-96dc-1ce87c3d6ba9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2025-09-04 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 83231cde-f26d-4570-a0c2-37696d0c6293 |  | LU | 2026 | 2
1120001029 | 45179ca9-b8e7-4285-9f6c-6686ccc6c1fa | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: a3c19a52-3ca4-46a3-b17a-3fb5bf6cd153 |  | LU | 2026 | 2
1120001030 | 42706cf4-8db6-4a36-bac8-b0926dd77ca0 | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001031 | 42706cf4-8db6-4a36-bac8-b0926dd77ca0 | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001032 | 9eb5cc44-e521-4931-8b01-e7a96b8f0e71 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  | 2025-09-29 |  | 2030-09-28 | Level 3 |  | Reinspection Date: 2025-09-29, Work Order ID: 525150f0-ed5d-4f8f-b02b-d0706d568739 |  | LU | 2026 | 2
1120001033 | c679b097-ec2a-4273-90fe-fbb832bca1d9 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001034 | c679b097-ec2a-4273-90fe-fbb832bca1d9 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001035 | ec361fe0-dd2f-408c-866b-e347b13a04de | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001036 | f8fb9b64-176f-4c5f-82aa-b13c4f627146 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001037 | 430dd346-caa2-4f1d-93b7-1d5aafe993ce | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001038 | 4c633712-9df8-4347-9516-eca1bd47ff60 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001039 | 00bfb561-d849-477f-9b49-af7b63141875 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001040 | 00bfb561-d849-477f-9b49-af7b63141875 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001041 | 18824233-23ab-4de9-b882-60e331184aab | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001042 | 539d5fe6-e28a-4e83-b94f-b5a8737f1a15 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001043 | 539d5fe6-e28a-4e83-b94f-b5a8737f1a15 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001044 | 898ac8d5-697a-4a34-91b6-4ed5aac2f7ed | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001045 | 898ac8d5-697a-4a34-91b6-4ed5aac2f7ed | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001046 | 693d039e-a074-4638-8094-25ed5b3809d7 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001047 | 35a0559d-e418-405f-a50f-2664e38cc4c7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001048 | 35a0559d-e418-405f-a50f-2664e38cc4c7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001049 | d374c432-f55f-4f2b-99c5-d5efed76a500 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001050 | d374c432-f55f-4f2b-99c5-d5efed76a500 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001051 | 097412e0-3e53-4310-8900-9ef522481e03 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2025-09-09 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 6ce630ad-234d-4ac8-91ef-52ac0241db4a |  | LU | 2026 | 2
1120001052 | dc44779f-7b4e-4f16-baa8-39d59448a797 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001053 | e1953949-f163-4b67-8ff0-1507173ad872 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-10 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: 56fa6155-3f31-40c3-a733-e6189b19509f |  | LU | 2026 | 2
1120001054 | 4ee6c160-52a1-49aa-8e7a-68c0d6eeaab3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001055 | 031cd921-b172-4d56-b104-b8cfb8a57b22 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001056 | 031cd921-b172-4d56-b104-b8cfb8a57b22 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001057 | 1bc8f556-3ed8-4aac-a3d7-57dd81fbd252 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 45e555f6-e295-4dc0-aa8d-4c0949024ff5 |  | LU | 2026 | 2
1120001058 | a85812cc-7557-4bcc-9fd2-1e7ef2412009 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 7992702e-b5d9-4557-be7a-823b24b5c144 |  | LU | 2026 | 2
1120001059 | e217976e-cb6d-40d6-9dc9-a95420ff798b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: bd15f49c-4f1d-4341-9237-550cd5e06e88 |  | LU | 2026 | 2
1120001060 | 22c8646b-a4f2-4ed5-a41e-b824672bbc1f | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001061 | bb7e8be9-3e60-4ac9-8626-7bf59cb8c5eb | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001062 | ca121bbf-5e5c-4a9d-ad7e-684192195c36 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: d3ef2749-48da-45cd-b696-fd9e9c82ca9b |  | LU | 2026 | 2
1120001063 | 71894b0d-cb10-4460-8948-7680d703053b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: f5e8aba7-103e-43f7-9677-5840e30e678c |  | LU | 2026 | 2
1120001064 | 8339bf41-6dff-47a1-8d04-103fe99994ed | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001065 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001066 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001067 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001068 | dcf512a8-2350-4306-a999-8bda830d7a7a | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2025-09-25 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 82565f21-e14d-4ece-8174-f8612033a8e5 |  | LU | 2026 | 2
1120001069 | b6a24af7-d580-4a24-a63d-91388c185f68 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001070 | a8e07211-1b9f-466b-9785-89f05761ef5f | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001071 | b4d660c5-afd8-46cd-97e4-0cc1ec8e6065 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001072 | 45418583-7bf4-4b7c-b10b-4ab8e34cc158 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001073 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001074 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001075 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001076 | 5e562c17-ddf1-425a-970e-f34d2991642b | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001077 | ed1dce4a-7c61-4004-b689-6eea8bbc5c98 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001078 | 91ed88cf-0710-4d57-b19c-3ffcd1a2db34 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001079 | 508b450b-998b-4885-be47-df1849f218b1 | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001080 | 3f1fd076-4f1c-4280-96e9-1bea7bf1476a | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001081 | 3f1fd076-4f1c-4280-96e9-1bea7bf1476a | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001082 | 2e3b7b5b-a4b5-41ee-b5ad-afde14445424 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2025-10-09 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 2bac77a7-5ea1-45ae-bf84-056e3e4bbe75 |  | LU | 2026 | 2
1120001083 | 2e3b7b5b-a4b5-41ee-b5ad-afde14445424 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2025-10-09 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-03-17, Work Order ID: 30058404-242d-4aeb-99e4-f7335ce29b34 |  | LU | 2026 | 2
1120001084 | 189bcfca-b0c8-4985-a0e4-7645fbeb5892 | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001085 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 5e62fa0d-e719-4560-a3bb-2e14e526d2ac |  | LU | 2026 | 2
1120001086 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: f2c063d2-d017-47d1-9e23-52d23e5507ae |  | LU | 2026 | 2
1120001087 | 215cdeaf-d308-4755-94c3-1be7a4fd2af3 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001088 | 08110983-44fe-4dd1-929d-0a6495466891 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001089 | 08db2e62-6c88-4f03-9a40-91518b255098 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: b51ece6b-63b7-46b7-aeb9-87ee6929a156 |  | LU | 2026 | 2
1120001090 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 446944f5-73ad-4a26-8325-ed21c5e3f0d6 |  | LU | 2026 | 2
1120001091 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 917e2efe-82fd-446c-a7b6-0486ae323252 |  | LU | 2026 | 2
1120001092 | ba101026-bb63-4851-ab59-23e007003013 | Padmount Transformer | Non-HFTD | Distribution | 2024-10-16 | 2025-10-16 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 180702de-e7ab-475a-9a11-8af44c26359e |  | LU | 2026 | 2
1120001093 | d511cea1-8a7b-4d55-aaa9-7f2ad3328fc7 | Pole | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001094 | 82e1727c-9d9d-4216-9f5c-990ebcc913f0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001095 | 83417e27-3699-428f-89d8-6b6cbff9cd41 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001096 | 83417e27-3699-428f-89d8-6b6cbff9cd41 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001097 | 720605ba-8096-450b-a754-4dbcc95983dc | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 6b419299-187d-4621-9f58-21f762978c17 |  | LU | 2026 | 2
1120001098 | 06eb7792-a968-48f7-9f5f-9b7d0d8117ad | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001099 | 4967dfa4-464e-43cc-8f11-b861a3b6704a | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: d5a62a01-7502-4ead-813b-e0cd651eef3a |  | LU | 2026 | 2
1120001100 | 54181ace-95f2-48ab-9f09-9a22d354d8f7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2025-10-18 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 2b6d2b1a-0455-4c97-8590-344b2f2c9c41 |  | LU | 2026 | 2
1120001101 | 83d2e575-1471-4bf0-a0f8-3b55eecb367d | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001102 | 83d2e575-1471-4bf0-a0f8-3b55eecb367d | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001103 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001104 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001105 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001106 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001107 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001108 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001109 | 08435365-2b50-40ab-a6cf-3542a002ebd6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2025-10-21 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: ba242866-e54b-4a85-a9eb-234a0c75f3e0 |  | LU | 2026 | 2
1120001110 | b83181a3-e28a-4e9b-bca6-aebdc06a6854 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001111 | c019bea8-ced8-4e03-9b7c-7d6fd42db78d | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001112 | ad89eb61-6587-442a-b8bd-48df87fdc998 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001113 | ee195894-4408-441c-a1c4-84bc67982891 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001114 | ee195894-4408-441c-a1c4-84bc67982891 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001115 | fd763201-df6c-4631-ba1c-8bc67dfa49f9 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-03-16, Work Order ID: 2de7f3e4-2cf5-41c7-a79a-bba7516ca123 |  | LU | 2026 | 2
1120001116 | fd763201-df6c-4631-ba1c-8bc67dfa49f9 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 8769a960-18ac-47d7-b084-aa0ee1de5d6c |  | LU | 2026 | 2
1120001117 | 09db7738-a274-4426-9ae4-2f14f6f486a3 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001118 | 160e5a50-7301-4290-be5a-db17d12c84cf | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 405e31aa-1078-4470-939e-8f0de39ec3ec |  | LU | 2026 | 2
1120001119 | 160e5a50-7301-4290-be5a-db17d12c84cf | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-03-16, Work Order ID: e5955625-4857-4ab9-bf9a-333430f04a3e |  | LU | 2026 | 2
1120001120 | 3e88ae74-c096-427b-b161-e25b9c5e4d08 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2026-03-16, Work Order ID: 76fc8b7a-a0cc-4078-ac4b-cb9a70d7549b |  | LU | 2026 | 2
1120001121 | 3e88ae74-c096-427b-b161-e25b9c5e4d08 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  | 2025-09-24 |  | 2030-09-23 | Level 3 |  | Reinspection Date: 2025-09-24, Work Order ID: 9c027751-eda4-436d-a768-6466ca0e94de |  | LU | 2026 | 2
1120001122 | 1245648a-5fce-45e6-b498-e0d5a63c4217 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  | 2025-09-14 |  | 2030-09-13 | Level 3 |  | Reinspection Date: 2025-09-16, Work Order ID: 87f96807-9c55-465f-9b7c-b7753424e215 |  | LU | 2026 | 2
1120001123 | 0d6c76d7-9f2d-4d5e-87f7-dfbe881e94e3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  | 2025-09-14 |  | 2030-09-13 | Level 3 |  | Reinspection Date: 2026-02-05, Work Order ID: 6e213969-429e-4ef3-a782-7c7fab41ccb5 |  | LU | 2026 | 2
1120001124 | 0d6c76d7-9f2d-4d5e-87f7-dfbe881e94e3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  | 2025-09-14 |  | 2030-09-13 | Level 3 |  | Reinspection Date: 2025-09-16, Work Order ID: d7dbd9cf-fe60-4c09-889a-87ddb345ee52 |  | LU | 2026 | 2
1120001125 | 888aa292-e125-4af1-878e-a953702888d5 | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001126 | 258f1d89-dcaf-4929-a1b0-0ff981fed18a | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001127 | 0cdd6527-19a0-4173-8576-80e1957db301 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001128 | dd0c5051-34af-40ec-9000-5e28b73dabc0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001129 | 7b979fb4-eef9-43b3-90a0-f0d4dbcd24c5 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001130 | 03dbda9b-fbc2-4fe3-91a7-50ea14690a19 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001131 | 7b8736b5-64fb-436f-9511-7b76d27cf325 | Padmount Transformer | HFTD Tier 2 | Distribution | 2024-11-08 | 2025-11-08 | Level 2 |  | 2025-09-25 |  | 2030-09-24 | Level 3 |  | Reinspection Date: 2025-09-25, Work Order ID: f6ae833f-78e6-4620-af86-5dd8a2823fa0 |  | LU | 2026 | 2
1120001132 | e2fbb06f-cb34-4c7a-82fb-53ccb513461f | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001133 | 9983dfa2-d6a2-42f5-a8f0-decd21ac300b | Pole | Non-HFTD | Distribution | 2025-02-04 | 2030-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001134 | 8e4a4fe0-825a-45d6-8a7d-534134672cd6 | Pole | Non-HFTD | Distribution | 2025-02-05 | 2030-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001135 | dd98cc24-5a60-466e-b264-1ed94391468b | Pole | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001136 | 9d4cace1-db14-4802-bb78-d5b884187aad | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001137 | 4bc18ee2-07d4-4ab7-ac9a-9c8a0f4cd16d | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001138 | 3fb74fa6-dbf5-4525-8cb9-19eb3a77aa16 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001139 | 2b48e22f-e716-40fe-827d-c796a1d8bd87 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001140 | 033224a7-8eb3-4977-adbe-0ec6511c68e5 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001141 | 2291f61b-fa83-49b1-89fd-06ca292fa9f1 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001142 | 1f07c0e6-9e24-4812-a9e0-88e9e6f13b93 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001143 | 185844a8-b997-49ef-aed4-683186d9fcb9 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001144 | 1a2eec75-269a-4efb-8c2f-d1023f41bee7 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001145 | 7aad7942-d95f-4864-babe-20ea56721c75 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001146 | 849ea042-aa18-4837-8ed8-d1696bf2f440 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001147 | 6cceeafd-871f-4201-90c2-621d0c5fa9f0 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001148 | 6273718e-0dfd-4c12-94ba-c6c5ff068d5f | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001149 | dbe5c093-4843-4077-ae2f-8f8ec53c7159 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001150 | daf93d99-09a6-48fa-89d6-3b727688c798 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001151 | d10ba26e-9bb0-46e8-99b1-a35d3c0cb979 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001152 | ce38d17d-49f8-4f8a-bb7b-34fd89ba68f9 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001153 | c9819bc5-0af7-4fc0-baaf-c7afa51680ac | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001154 | c10f25b7-4181-485d-b8e8-aa39bc9c82bc | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001155 | d9c54737-42c2-4d91-936b-f67ec22f9337 | Pole | Non-HFTD | Distribution | 2025-02-25 | 2030-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001156 | 04463a67-6c24-433c-88ce-21208b881a0e | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001157 | 04463a67-6c24-433c-88ce-21208b881a0e | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001158 | 2626ed7c-d7e0-4452-b85e-715c5db7f70c | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001159 | 95ac786a-4538-464b-a6a1-92aed738d56e | Pole | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001160 | ac81c9bc-0d98-462b-ab08-76ed4f0d4493 | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001161 | 9f37860f-f3a7-4c4d-9f95-3a26b30fa09e | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001162 | c0276719-210d-4f71-84dd-d0b9f7d7f45e | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001163 | d673bacf-93fa-48cb-a381-dd13533dc77a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001164 | dbe19199-7160-43e8-a3e4-6927cf03d92c | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001165 | f1e773d7-6444-4fa5-9961-7cd2390bb2b5 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001166 | 4e799e20-0df3-4444-8801-9814566371eb | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001167 | 3a7f2649-80e1-4bd4-82dd-d04c403593e0 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001168 | 12542146-4753-4b98-85ff-1ca7f8e84a93 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001169 | 12542146-4753-4b98-85ff-1ca7f8e84a93 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001170 | 9ba038f1-bebf-4e62-8e3d-0b198487a54c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001171 | 8e8f78c1-523e-4374-919e-a3b36dece350 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001172 | a4a39f38-f6b6-4870-b3d4-75be1cea2cec | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001173 | fb7c0a78-8db0-45ec-a54a-2e48de6a544c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001174 | fb7c0a78-8db0-45ec-a54a-2e48de6a544c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001175 | fcce86c1-489b-4248-91a4-87d75a06fbff | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001176 | f4e5f669-9a06-4e8b-8f2d-8896839059f5 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001177 | daf8f2c2-eea0-413c-9aeb-93450134a0dc | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001178 | 8cfb2b9f-a10c-48be-a457-592293ed8c2d | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001179 | 6381231a-0638-42e0-a439-e66bcbbb6c06 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001180 | 6df31a44-ed9e-424e-9b1b-260c144ea2d1 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001181 | 6e15cd54-8aa6-41e1-833f-ed45fa386e68 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001182 | 34064f69-a35e-45ff-a16c-a35f17f23487 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001183 | 437e12d5-3064-4690-bc7c-164159bd7497 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001184 | 06fdf389-b75f-4377-8d68-461125aac99a | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001185 | 1c71911b-8a42-4e7b-b19d-3ed402303b69 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001186 | 8e2c822a-bd81-4ce1-bcfb-3472e3411321 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001187 | 79713613-ef4e-4c80-b9b3-d9fa73a67ce3 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001188 | a8b1b111-af47-4d28-878d-9cd80e682c66 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001189 | bcbbc8de-3b0e-4e8f-935e-3d1f2f9027c1 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001190 | f5856337-bcd1-42f6-aa36-495828066de9 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001191 | fe647549-10f2-4474-84c5-0954eca1ac7f | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001192 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001193 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001194 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001195 | fa5a3228-72fb-4188-83b9-38f1d6e35858 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001196 | 1afad64b-387f-46b0-99eb-df1f6a05c28c | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001197 | 36d4433a-50b9-4ad5-b010-94bb286218ee | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001198 | 36ab204a-dc7c-4fa7-b94e-bb595e22489e | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001199 | 333c0654-50a8-43c7-90fd-42236fa1cdd2 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001200 | 7862145a-b779-45fe-b478-1325d91a2ebd | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001201 | 8019d952-7a34-4a08-862a-3e08e4a04fb3 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001202 | 659b26a6-cb0f-4d9c-9484-ab52aeed8c41 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001203 | 5f896831-ddb7-403f-a93e-712bb13be540 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001204 | 4b6e7984-f3d3-417b-983b-78e12184f295 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001205 | 4b6e7984-f3d3-417b-983b-78e12184f295 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001206 | abb691fc-9ad8-4963-8652-6738bc94b260 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001207 | b2a4ebab-a57e-4432-8007-e8cdb11a6d2e | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001208 | b2a4ebab-a57e-4432-8007-e8cdb11a6d2e | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001209 | b1747cb0-ba87-4e2a-a3fc-3b939e1aa8da | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001210 | bc2444aa-8d8d-4660-8fc9-5a9e94cccfea | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001211 | e2b35f61-a1eb-450a-9047-323ff6f18f24 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001212 | e2b35f61-a1eb-450a-9047-323ff6f18f24 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001213 | d996106e-1802-47fa-8652-4e2ce34313fb | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001214 | d1889bd0-e2d2-4f20-85a8-e480ff0102d0 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001215 | 41636d54-73ba-435e-a397-9aea5eabb44f | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001216 | 2cb4e189-03a9-4f63-b83c-5c1aab3d523f | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001217 | 1e3463e7-4a90-474d-aafb-2bfdae40638c | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001218 | 1af27f97-abbe-4a3e-934f-bd045033c762 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001219 | 1af27f97-abbe-4a3e-934f-bd045033c762 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001220 | 05f2b8b7-4e98-4cab-91ea-2cd79c47bf17 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001221 | 108aed6f-ca0b-429f-802d-3d023916ad57 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001222 | 61ae2634-1497-47da-87e2-b8eb27f95922 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001223 | 6d6eb2bb-0441-46d7-9828-d16c11e58335 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001224 | 6d6eb2bb-0441-46d7-9828-d16c11e58335 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001225 | 58fe5e62-6e28-495e-9f22-1a7b5d67c366 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001226 | 83a32de5-653a-4454-a3a1-d6002381e2bd | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001227 | 8760f79a-1f2f-43b7-ae47-d40b56ae9a48 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120001228 | 51479c9b-e8db-4c09-8995-ada2676c290c | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001229 | 50e8b1d2-083b-41ea-ae71-3cf3c2769ddf | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001230 | 56070e5f-7872-45a8-a45b-830d5d60bbfc | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001231 | 6b8e391c-ec2e-4ee6-b14b-9ac880ace656 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001232 | 137eb83d-f799-4a28-b21f-132ba834a516 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001233 | 1c97c2ef-088d-472a-9624-5df55a873f2d | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001234 | 32ae75b5-dbad-4ee3-b8f0-61d2a0b3e34f | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001235 | 39208054-4b83-4df2-9cb6-fdb6ca10799f | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001236 | d3ab4bc2-9e15-4190-bdda-23ea760bc1ca | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001237 | dba105a0-a908-4081-b312-ac777642e4c3 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001238 | de1d0174-4ea8-41e6-ad0b-310eef9a7028 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001239 | e1126513-a6b2-42f3-84d2-f04495419947 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001240 | c5dd3944-4b93-440e-94ca-d9211f5f8dd4 | Pole | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001241 | eaa8fea1-84d5-42a7-b439-791b3aae6566 | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001242 | d13d79c8-61a9-49ec-b469-ac8346177fd7 | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001243 | fe0dea7e-f385-44ed-ac14-8ba066aea5cb | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001244 | 09b830e0-0075-41e1-a04d-43b6990f3c3b | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001245 | 78d8fa33-94d1-472c-b172-6f1d0fdcb091 | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001246 | 8feb128e-8b41-4ce1-a8a3-3d7a70804bd7 | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001247 | 679c3e5d-0260-425d-8588-499e2e33a22e | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001248 | 5c67672f-ac5d-4cb9-ad51-044be3289400 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001249 | 0ad5e369-ec5c-4dd7-bbe4-12ab68394cee | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001250 | 192d46c9-55ca-4adb-baee-d5d292fd29cf | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001251 | 3f81c71a-f06c-423a-9759-40a9f528682f | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001252 | 3f81c71a-f06c-423a-9759-40a9f528682f | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001253 | d3938a8a-89b9-4870-8095-66964785e538 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001254 | ed435593-a0a5-4aef-a703-230d9e152439 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001255 | e0537263-8c60-4dd2-bec9-07062f9dc1c7 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001256 | c4800bfd-9deb-484d-93c1-0eae6832f78d | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001257 | c4800bfd-9deb-484d-93c1-0eae6832f78d | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001258 | ba5763bb-3166-4096-9de8-dd4c08f16d3a | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001259 | ba5763bb-3166-4096-9de8-dd4c08f16d3a | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001260 | baedb812-12a0-4070-a1bf-0480f4ace7a9 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001261 | a1727b00-4820-4281-82a8-6e0288723a35 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001262 | a1727b00-4820-4281-82a8-6e0288723a35 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001263 | 9ee651c8-26ea-46df-be23-a884e6829ebf | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001264 | c4e0f42c-0cea-4612-bcaa-5f5ff06fe49c | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001265 | d783bb20-327d-4fbe-bda2-77b754584bf2 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001266 | f5ff6842-f7e8-4f43-bb09-6f7b7d78442b | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001267 | 40c7813f-8006-4f3d-8da6-806daef1aeb7 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001268 | 19d442c9-c218-4c67-909d-d9ce6706c59b | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001269 | 16cd4f3c-abf3-4c59-87ac-96353e4314d5 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001270 | 1ecedd8f-ca36-42a6-b9cd-1186dfdf7d14 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001271 | 09786829-04b6-448c-b311-a01a2459b0a0 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001272 | 0db936a3-12e8-4dd6-a522-1f5ea86110b7 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001273 | 0893a7f5-3d36-4ee8-9ab6-beeaebec3823 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001274 | 8e886ebb-5b6d-4181-9c48-9d8889530c35 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001275 | 4fcdfbf8-71a3-43b2-87ef-06d629336b85 | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001276 | 10c4b56c-27ef-404f-9eb0-7cc2e13cf060 | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001277 | 3d64a00e-4f0a-46e8-8f32-1c056e59dc94 | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001278 | 3d64a00e-4f0a-46e8-8f32-1c056e59dc94 | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001279 | fb09ce01-2fe4-45b2-996e-8fc4e260e36a | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001280 | c5574a40-dd25-4782-a196-409affb8937a | Pole | HFTD Tier 2 | Distribution | 2025-04-11 | 2030-04-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001281 | e2444b6c-5b6e-45df-8e3e-a870508ea7bb | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001282 | 039824f2-90b9-4626-a41c-fe058a8c577f | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001283 | 5b7f62f3-00e9-4b57-a01f-4561b9135ace | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001284 | 730d8253-a655-4ebf-9e6c-8b008e7e787b | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001285 | 7f68c182-84dc-452c-844f-a2d7bf4cd0c1 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001286 | 85ab0c3d-d6c4-4ed1-a188-be511996efb5 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001287 | 8b052735-a1ff-4398-8b51-4539bf73919e | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001288 | 8f208706-affd-4f0a-ae43-d7e5c443c274 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001289 | 8f287c34-c79d-4bbc-821e-9b76d55eda95 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001290 | 21a2a70d-2ba3-422a-b5f5-587c6325088c | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001291 | 2ab4bf8a-7713-4611-a59f-8e558fe17267 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001292 | d39f45e7-9cba-4cb9-9664-ab6cfb1b9b36 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001293 | cf3c1617-b668-4e42-a01b-c2733b45edd2 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001294 | afe87812-096c-4aee-ac04-99313ba44d37 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001295 | afe87812-096c-4aee-ac04-99313ba44d37 | Pole | HFTD Tier 2 | Distribution | 2025-04-18 | 2030-04-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001296 | c15675d6-ddb3-4b9d-876b-386d9cbe3ade | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001297 | b80cc6d2-0180-4d6b-ada1-5f43dda341b4 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001298 | ce3a060a-3e71-4ad1-8bd2-fa94f38566b7 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001299 | ce3a060a-3e71-4ad1-8bd2-fa94f38566b7 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001300 | d7873be0-1602-4030-973a-1aa2a668e90a | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001301 | e2846d61-8ccc-44af-90b3-35222a977a5a | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001302 | eda91b0c-76e4-4aa0-b341-d119b366f992 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001303 | 34a70689-c27a-4480-b02b-c463ab1229d7 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001304 | 02fe94fc-3c42-40ec-9014-e31a17f29746 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001305 | 024d1211-a14e-4d3c-a794-a73e1af8b2ae | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001306 | 05802cdc-d69c-4913-b183-ae25d86621a4 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001307 | 91c671fc-8625-4bad-a09e-ca7f1df0604c | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001308 | 7fb992a0-8f19-417a-9b7a-0e14740ec951 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001309 | 64631f1b-c52e-4814-84a5-9057c300fcd6 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001310 | 603c3f6e-8c78-4300-af4b-5495fcd82d58 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001311 | 5b03e747-4744-47a9-b86d-407c528316d2 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001312 | 4e4bc52b-2739-498e-8b7a-9704a7a711fe | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001313 | 6d2f01eb-0983-4303-b47d-17c12c9079c8 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001314 | 7bcbfcaf-43cd-412a-9813-fbe479fb507b | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001315 | 89634d76-4deb-44d0-9a09-8f22772367e0 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001316 | 97bedaac-a28a-4061-a195-76345be7c23c | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001317 | 2596a6a8-c3ba-4eb6-9e38-a1d1b70406a8 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001318 | 3171af79-748a-4f31-a7ca-b82ce6daf1e6 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001319 | 3171af79-748a-4f31-a7ca-b82ce6daf1e6 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001320 | 44065dde-dc65-4041-8d54-6945f265c25a | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001321 | e3536805-b590-4aa5-aa0f-74f1c1f408f9 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001322 | d5e31265-8ec2-4c53-95a3-26268fdf7c6e | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001323 | 9f27890c-21d6-4525-86e3-e47a1c571566 | Pole | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001324 | b2bc242c-2360-4f4f-8335-1620609b20b8 | Pole | HFTD Tier 2 | Distribution | 2025-04-25 | 2030-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001325 | b2bc242c-2360-4f4f-8335-1620609b20b8 | Pole | HFTD Tier 2 | Distribution | 2025-04-25 | 2030-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001326 | b2bc242c-2360-4f4f-8335-1620609b20b8 | Pole | HFTD Tier 2 | Distribution | 2025-04-25 | 2030-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001327 | c6584e04-dc10-4f2e-b4de-8cd9e5dba11c | Pole | HFTD Tier 2 | Distribution | 2025-04-25 | 2030-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001328 | 1eff70fc-a881-4f03-8ebe-2da62697cb7b | Pole | HFTD Tier 2 | Distribution | 2025-04-25 | 2030-04-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001329 | 1ed79d10-26bd-4df9-880b-9d4d2cc06607 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001330 | 83796199-d236-482a-aaf6-ad109fc1eb95 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001331 | 61b78a54-cce0-4cf5-af2a-563d870cb452 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001332 | 517909c6-1b31-4491-ae48-6c065f108dc8 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001333 | ee2aa289-04f7-42ca-9523-72825aa06bc5 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001334 | 764d222a-e747-4845-adc7-50e780053089 | Pole | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001335 | 0b8f003b-8367-40f7-9bf9-91e45146ffc1 | Pole | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001336 | 0b2f4a50-8742-4cdf-9714-0b3ca568b1a8 | Pole | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001337 | 2fd2b9dd-5033-414c-bc9c-3f8160b21831 | Pole | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001338 | 5043a10d-3ebf-48d7-b41f-87e58db7ed77 | Pole | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001339 | cbcffaec-ba0b-4edb-9b7b-3a88de34fc95 | UG Transformer | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001340 | e8ddbac8-16ef-4f09-8feb-60e122c22a7a | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001341 | e95b6bb7-84b6-4340-9a94-f047ed059c18 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001342 | c39d7380-9581-4390-9db9-652487e2f30d | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001343 | b1388294-571e-47a8-beb3-fe4091012b55 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001344 | f83d1ed1-40c2-4d99-9070-78a822a1c94d | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001345 | 674ebe03-8bc4-4b61-bf46-162aa9d0994a | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001346 | 6d0a4b8f-e1b1-4181-b588-e70c7e716f6e | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001347 | 6c5e450e-1b58-4b5e-aa68-c76fa2c6a73c | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001348 | 6c5e450e-1b58-4b5e-aa68-c76fa2c6a73c | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001349 | 6f91d746-3a2c-4356-b081-5de003e379c2 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001350 | 7c36908f-d783-48f3-ac9b-3a0d1642d18d | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001351 | 8e542bda-6a90-4e3a-869e-ffcddc798448 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001352 | 2ca8d9a4-b658-4c6e-a05b-197630bce054 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001353 | 3caf6afb-c786-445b-90e0-c1122e42bb59 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2025-05-14, Work Order ID: 541ae836-dabe-441c-ac92-e1016f3d6b1c |  | LU | 2026 | 2
1120001354 | 1f7ac2ab-e7ed-4ff2-8570-5a946cecb730 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001355 | 2504e716-0f05-4624-bbc1-8968243aa522 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001356 | 1a3d2ccf-2c0d-40bb-ab98-b28b27134e64 | Pole | HFTD Tier 2 | Distribution | 2025-05-14 | 2030-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001357 | 19876124-cfe1-4cd7-ba06-5ed8c2cc44f4 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001358 | 490061d4-b73b-4856-9ae4-10ea1c847a1e | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001359 | 85069df0-2b6f-487c-ae60-2948154c0c31 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001360 | 71c9536d-fe8c-4582-9cc8-3bb3750b5363 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001361 | 71c9536d-fe8c-4582-9cc8-3bb3750b5363 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001362 | 5a5623d8-943b-4747-aefa-eca059db642d | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001363 | 5c866140-5b7e-4055-b7b4-7d0276bdd4b6 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001364 | f922a6f5-3a15-4f93-a0fb-3beb5d2e169c | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001365 | f922a6f5-3a15-4f93-a0fb-3beb5d2e169c | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001366 | fa589c24-f1a8-4660-8324-b590c954f350 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001367 | a78c4e1d-d63f-4112-a072-08688ee46be9 | Pole | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001368 | 9feea989-271a-4904-8acb-e766c3c67940 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001369 | d3495eb0-16aa-4605-b8e3-0b2ae30da527 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001370 | dc504c41-00b9-47ec-b50d-5fa04bde4b58 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001371 | 611a43b3-6746-435f-a5cc-8069d45b337e | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001372 | 0b3f5afc-c9fb-470c-ad98-7a5e8007fc09 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001373 | 0b3f5afc-c9fb-470c-ad98-7a5e8007fc09 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001374 | 05aa8677-cccf-4383-ba48-ff0c31e29a02 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001375 | 05aa8677-cccf-4383-ba48-ff0c31e29a02 | Pole | HFTD Tier 2 | Distribution | 2025-05-16 | 2030-05-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001376 | e874f38d-ead0-4302-b40f-1d95b3e0f164 | Pole | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001377 | 9ee8e75a-ea2e-4522-a639-958b094d2c43 | Pole | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001378 | 0151c31d-b267-44b1-a79b-500f6973d493 | Pole | HFTD Tier 2 | Distribution | 2025-05-21 | 2030-05-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120001379 | 23ef32ec-4c4d-487c-928c-50be85a9443c | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001380 | 213ac7b7-a360-4e67-ac9a-0e9fa7da0f8d | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001381 | b727dda2-11d8-4d24-939a-feccca034b0c | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001382 | d558c986-1dd7-4882-99ab-563a13775707 | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001383 | d85fea13-988a-441d-aa68-4c89624f2bbe | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001384 | d85fea13-988a-441d-aa68-4c89624f2bbe | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001385 | fa5e6b30-2beb-4a95-a15e-2b7150ec69f0 | Pole | HFTD Tier 2 | Distribution | 2025-05-23 | 2030-05-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001386 | f2117dde-e0d6-472e-84ef-bc7d6819ffdb | Pole | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001387 | a10d7341-e8ef-4998-aa53-c726677b3ad1 | Pole | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001388 | 8130e468-2bf6-4c7d-b377-9d1b53cbedb3 | Pole | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001389 | 8a7f3a48-00e8-4b94-a394-55c48a66e35e | Pole | HFTD Tier 2 | Distribution | 2025-05-28 | 2030-05-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001390 | a2d10175-4b6e-46bb-9b9d-56b390c618e3 | Pole | HFTD Tier 2 | Distribution | 2025-05-28 | 2030-05-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001391 | dd9581e7-ad80-4bca-979c-9c888ceaebde | Pole | HFTD Tier 2 | Distribution | 2025-05-28 | 2030-05-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001392 | dd9581e7-ad80-4bca-979c-9c888ceaebde | Pole | HFTD Tier 2 | Distribution | 2025-05-28 | 2030-05-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001393 | cf06cb2b-68eb-4255-aa18-435a838f288c | Pole | HFTD Tier 2 | Distribution | 2025-05-28 | 2030-05-27 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2025-05-28, Work Order ID: 25091c1e-12d7-4867-a0d7-f7931a10c561 |  | LU | 2026 | 2
1120001394 | e5d03a1c-a6e6-4f32-ad13-91aded45b04c | Pole | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001395 | e5d03a1c-a6e6-4f32-ad13-91aded45b04c | Pole | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001396 | e119d30e-c9f9-4786-87b5-1c2110e3a305 | Pole | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001397 | 229bf03f-a045-418f-a7bb-cf01403858bd | Pole | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001398 | d21f2e58-f0be-40bc-a44c-aad237d7069f | Pole | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001399 | c262cf17-2bba-4e6f-a339-dd0c7b583f48 | Pole | HFTD Tier 2 | Distribution | 2025-06-20 | 2030-06-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001400 | ba3b0bd4-b79e-4555-a216-7123ac79221e | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001401 | bede6164-9e3d-4f32-b36f-a3ba99622be1 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001402 | a869d26e-f583-42d8-bcf3-15c710aee038 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001403 | dd3bb39e-c0e9-414a-9eae-21865868be49 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001404 | d5923406-b3c2-43c5-a801-1186403271a3 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001405 | e44b5181-7ad6-4c30-96b9-d55649e36036 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001406 | e44b5181-7ad6-4c30-96b9-d55649e36036 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001407 | 19cfacf6-372c-45a9-9a82-4ce775a2974e | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001408 | 0d359da1-5c18-482c-ba3d-eb3d3261c3d6 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2025-07-15, Work Order ID: c55c92f1-10c0-4fa1-bfae-6bf1cc0771e6 |  | LU | 2026 | 2
1120001409 | 10405bda-d3a3-41f0-ba40-28494f1319b3 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001410 | 4b743248-7e16-474b-b446-e888f6cf1395 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001411 | 2a584aa6-73f5-4eb3-8780-8db80e4ad7a8 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001412 | 2a584aa6-73f5-4eb3-8780-8db80e4ad7a8 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001413 | 90baa389-0b2f-4bac-aa9a-b3f579bd6876 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001414 | 99af481e-8427-413a-ac93-8856c349e311 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001415 | 9b3136fa-a9ef-4e38-914d-ba541a958e89 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001416 | 82fe4e27-c28d-4d23-8166-fbdc1d3c84dd | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001417 | 6958b938-378b-4372-a5f8-2b32bb9713c1 | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001418 | 57c4ca9a-8c83-4cf0-a13f-c9c4916b085e | Pole | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001419 | 5a97ca7d-a647-4550-bb94-a0dadeeb6813 | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001420 | 715cb9c3-857c-4635-b7f6-5a980115104c | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001421 | 34cd1cd8-ffaa-4206-abc2-5f9807142ded | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001422 | 34cd1cd8-ffaa-4206-abc2-5f9807142ded | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001423 | 1a9909d1-0a8c-4fa8-86d6-1eeb50adb831 | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001424 | ddb5c75a-101d-455e-a537-187e51c50533 | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2025-07-16, Work Order ID: 24a4ce00-8911-43c8-ae09-43d11d2d1032 |  | LU | 2026 | 2
1120001425 | d1f9317b-e261-437b-9f03-cd5f58b31468 | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001426 | 9f05000f-fd8b-45d2-9d62-4b9405b432eb | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001427 | c996ce40-d2c0-42ae-8c30-352441318e2f | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001428 | c996ce40-d2c0-42ae-8c30-352441318e2f | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001429 | fef60fc3-986b-4277-8e48-bc0266c1adf1 | Pole | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001430 | b573d0e7-83ec-4a3e-9840-4dc7e9d6e5e7 | Pole | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001431 | bf1d2d8d-b7ff-4a13-9da9-41d1a03ff08d | UG Transformer | Non-HFTD | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001432 | c4896390-42f8-4c68-9676-441d17adcf15 | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001433 | a065f829-39eb-45ea-ac71-542740c9b37e | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001434 | d292cf6c-4da3-434b-b067-b4f84bf69df9 | UG Transformer | HFTD Tier 3 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001435 | 37725e89-31c6-4af0-89bd-80c2a06ac599 | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001436 | 38287138-c427-4f10-a2aa-4b90fc0544a9 | UG Transformer | Non-HFTD | Distribution | 2025-07-23 | 2026-07-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120001437 | 29810a9e-d8b1-4eb7-a6d4-7f4a3afbafc5 | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001438 | 6b416dee-5084-4437-8b42-30b49156b87e | UG Transformer | HFTD Tier 3 | Distribution | 2025-07-23 | 2030-07-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120001439 | 6641315f-c041-4561-aa34-bb26ce546d64 | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2026-07-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120001440 | 5805acda-c904-43d1-97c8-e99ed509e7cb | UG Transformer | HFTD Tier 2 | Distribution | 2025-07-23 | 2026-07-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120001441 | c54a0e7d-293f-47d2-8c10-2c4584babf1f | Pole | HFTD Tier 2 | Distribution | 2025-07-25 | 2030-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001442 | c54a0e7d-293f-47d2-8c10-2c4584babf1f | Pole | HFTD Tier 2 | Distribution | 2025-07-25 | 2030-07-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001443 | bf261371-a31c-4e17-a968-dcb2bae1928f | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001444 | a4075d5d-d879-49ab-afd1-6ed54edafcbf | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001445 | a4a5c875-8ca6-42c9-a512-b523df764230 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001446 | ad25aacb-224f-4d60-86a1-747d2eb1c1ea | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001447 | d967b1e0-e6ad-495d-89d0-39a5ddadcf0f | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001448 | 993f54c1-40b9-45fb-a4bc-bd4d01b14db0 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001449 | 9e6ed887-5858-4415-a7e0-15a57a600a49 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001450 | 9771ca6f-82fa-47d3-8f96-586f226f6325 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001451 | 96fb9572-a26a-43bc-a740-05eca41b7182 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001452 | 33b0e8a1-f4ec-471c-92b6-8f6caf672a8e | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001453 | 3c64d72f-bb1f-4e4e-af40-eb4189be2993 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2026-07-29 | Level 2 | [8 empty] | LU | 2026 | 2
1120001454 | 176d0d30-3760-4dee-8949-2f953f0679fa | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001455 | 227ad3b7-61ae-4766-8a94-3a3ad1b1675a | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001456 | 12702f10-e828-47d9-8859-6d25ec10c659 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001457 | 0bcf4b7e-daa8-41be-b8f4-ffd9b5218a72 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001458 | 0bcf4b7e-daa8-41be-b8f4-ffd9b5218a72 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001459 | 0695a926-5600-4f66-9a06-32690049db9a | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001460 | 06a4f754-0d13-471f-bf9d-f54cad6c84b5 | Pole | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001461 | 056c70b9-fa39-4000-853b-8edb0847cd80 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001462 | 05b54041-540b-4b86-935f-3331147a95eb | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001463 | 0906765c-0431-446a-824f-1af0da5cb7cd | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001464 | 0489ba75-6a89-49e9-a601-da4d7da66f97 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001465 | 0ad0f67c-e1d6-4357-be4e-719f8d095b47 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001466 | 0ad0f67c-e1d6-4357-be4e-719f8d095b47 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001467 | 1709025f-6aaa-49a3-9e1a-67eccc77cfbf | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001468 | 1709025f-6aaa-49a3-9e1a-67eccc77cfbf | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001469 | 135b543a-1630-4c94-9b78-fe517ffb991d | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001470 | 4c418a99-04a5-4fd0-ad68-11379513de8f | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001471 | 4c418a99-04a5-4fd0-ad68-11379513de8f | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001472 | 2f9e8957-3283-44b4-b1f4-fcdf44bef21b | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001473 | 33877f09-9f17-431b-b2a2-54f92fe65bc5 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001474 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001475 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001476 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001477 | 2e862c2e-c69a-4a79-a4de-f76186a571ce | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001478 | 2e862c2e-c69a-4a79-a4de-f76186a571ce | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001479 | 2e862c2e-c69a-4a79-a4de-f76186a571ce | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001480 | 2c5f7539-d57d-442f-97de-1f0e08e23d27 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001481 | 8f94a17b-dc0d-49cf-aac4-39edf40980fb | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001482 | 92361389-ff3d-42e8-a52d-72c883ee6110 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001483 | 92661425-9867-4217-8089-6097094d730c | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001484 | 89d96d38-c4d7-4b77-8457-4ffea42d18a6 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001485 | 749afc30-d895-48a6-9f23-8e9f930f508b | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001486 | 53767d9e-8827-474e-b7a0-fc9a47b75430 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001487 | 684d8263-2e8a-4d19-b006-08499b8a4114 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001488 | 60290a43-7386-4321-967a-7c70c60842b1 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001489 | 7167eed5-9361-4f60-a4ff-88cb5d30ce74 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001490 | e14b9d4e-f3d7-4bff-bacf-0babd3b7b540 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001491 | e71e9ee5-0de8-4dd1-884c-e0ccc94fde0b | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001492 | e7cddbbc-1842-43fd-b6cd-08317e42ec8c | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001493 | ac4932d0-0a4c-4211-b5a8-46833a24377d | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001494 | a80974a9-21c5-4b7e-92f7-070a1a1478f2 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001495 | a80974a9-21c5-4b7e-92f7-070a1a1478f2 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001496 | a63f5a52-e1f7-49f4-873b-c7d7537308a1 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001497 | c6d8ea76-4bb3-4109-b83d-e507320156e7 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001498 | fe6c19e0-72b4-456d-9d82-1c91703b02b6 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001499 | faa5746c-e60e-46ea-a13e-4a532e778963 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001500 | f96c9d6a-c8fd-403f-9a57-c9a5eaf2f493 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001501 | f96c9d6a-c8fd-403f-9a57-c9a5eaf2f493 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001502 | fd09be2f-e47d-4b06-bae4-32752061f7b6 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001503 | c52a1e51-9b0e-43c1-afba-737979e168a2 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001504 | c539f850-4030-477d-adf5-ad24ed6b677d | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001505 | c539f850-4030-477d-adf5-ad24ed6b677d | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001506 | c539f850-4030-477d-adf5-ad24ed6b677d | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001507 | c539f850-4030-477d-adf5-ad24ed6b677d | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001508 | c2cfa5df-c3d2-4425-813e-b3808ea4aed4 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001509 | ac300326-a164-405e-ba63-8bfd444e3464 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001510 | b3697d1e-b3a8-450b-af43-5612f1f3d4d0 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001511 | f1635e5d-ea7c-46bc-9e2a-eccba6852124 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001512 | d931995f-7395-4d2e-947e-f4bebaf159fd | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001513 | d308f23b-a9f0-45bb-be88-d2cd5d4519f1 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001514 | 62bc31a4-cbb4-4ea6-a9aa-a737e93eb3bf | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001515 | 67ef52bd-e410-40dc-93e7-ba186236bc8a | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001516 | 56c75ede-dbf9-4ce8-bd2e-91c447e5b2f3 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001517 | 8a420dc6-f905-4fe1-81fe-448495383981 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001518 | 8f4cc076-4c6e-4dd5-a779-104828a525b1 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001519 | 8cfce043-09e0-40b8-ab36-1644c079b3d8 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001520 | 2fc3a715-db7d-4d22-b7ed-2b9ec41ca0dc | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001521 | 2fc3a715-db7d-4d22-b7ed-2b9ec41ca0dc | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001522 | 341fcf64-79c0-480b-abb9-24c3d451b6f5 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001523 | 3670d486-c6db-4ad8-a386-bab49190ecab | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001524 | 3670d486-c6db-4ad8-a386-bab49190ecab | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001525 | 458dde24-2fcb-4ee6-a2e4-4a93fa5262a2 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001526 | 468b684e-d7d6-478b-9fa2-96c4efca66cb | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001527 | 468b684e-d7d6-478b-9fa2-96c4efca66cb | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001528 | 3c4b363d-1b19-4a1d-b374-4b566dea9b06 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001529 | 3d958159-5af8-4095-96bc-d9f7ebacfc16 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001530 | 3d958159-5af8-4095-96bc-d9f7ebacfc16 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001531 | 1806016f-bcb7-4fa9-b7ec-e4aa44735e2c | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001532 | 24ded998-73e5-418c-9fe7-84cbcf8efb26 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001533 | 035bc920-3e51-4610-9b3d-11a5fd3250ba | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001534 | 00af3d91-d7b5-476b-be26-b1d381cefd20 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001535 | 0926e34b-df85-4db2-80c4-b1adfff50a07 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001536 | 169b9a58-ef31-4459-ab17-be7fe6e655fc | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2026-08-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120001537 | d17f1f80-5b65-4a07-a05c-a7e936c5c76c | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001538 | d0881784-3e5b-4efb-9206-180dbe01586b | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001539 | e926b8ac-ba69-4cd8-82d4-b4c77d89013e | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2026-08-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120001540 | e926b8ac-ba69-4cd8-82d4-b4c77d89013e | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-06 | 2026-08-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120001541 | 9b12a272-c96e-4d14-adcc-c7d73173f932 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-08 | 2026-08-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120001542 | 836f59c5-1fdc-49f8-82ad-6da2b1deb6d7 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001543 | 75da4b8f-d90e-4e90-87ce-9a1eecd457c1 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001544 | 7d0e266e-11ad-4c76-a97a-921833d08730 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001545 | 7d4e2f1c-cbe5-4a3d-b1a4-c91aafafa36f | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001546 | 7d4e2f1c-cbe5-4a3d-b1a4-c91aafafa36f | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001547 | 13e71b8b-7052-4f31-9b28-90e679dd0371 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001548 | 0078eefe-8d59-4bf0-934c-32bc6b25e64a | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001549 | 10de13b1-5339-4e6a-a021-bd40f5da019b | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001550 | 30331257-9544-458e-adb0-eea92f93e817 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001551 | f0a365b4-01ad-449c-9999-61c3616e150d | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001552 | eccef5ed-bd11-4dda-bf8e-aa092b5c0d15 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001553 | ed5f6e12-fa06-437d-9061-9ae38ed63704 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001554 | ed61270a-02f9-4f3c-a1c8-3c69e035998c | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001555 | c516a806-4eb5-4496-b72d-3fdfc9b5d693 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001556 | bc592bbb-1b18-43b1-8c99-b4eebe117c85 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2030-08-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001557 | 7f406429-8a86-4cbf-82f0-952be7244d9d | Pole | HFTD Tier 3 | Distribution | 2025-08-15 | 2030-08-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001558 | 7b04b277-7664-4f95-9d45-73e33464538b | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001559 | 8f990745-b1b3-4172-ae8d-7057bd843e13 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001560 | 8f990745-b1b3-4172-ae8d-7057bd843e13 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001561 | 925abee1-d13f-4240-9b32-7cb26df91458 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001562 | 5e94b845-b985-43fc-a47a-1fe6df37cdf3 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001563 | 678cea47-158e-49d1-a4f7-0260361a1e29 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001564 | 3247c883-2d32-4257-9fd5-1542daefa687 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001565 | 3a3585a3-dc46-410c-8b32-7af5c295de51 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-08-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001566 | 3a3585a3-dc46-410c-8b32-7af5c295de51 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-08-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001567 | a8d303fa-3219-4d91-ab95-62af5e3eec0a | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001568 | a8d303fa-3219-4d91-ab95-62af5e3eec0a | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001569 | e86536a1-9a3a-426e-98b2-7b30e1a0a00b | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001570 | e578f173-43b8-483b-98d1-a239f1c1a549 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001571 | cbd5b75f-f073-4ccf-99a0-e774876cbef2 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-08-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001572 | d85e70e0-1b5a-4413-953e-fe8f3c736ccb | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2030-08-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001573 | fb7e28ef-6239-42f5-8018-8ac2da6639f5 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-08-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001574 | fb7e28ef-6239-42f5-8018-8ac2da6639f5 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-08-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001575 | f6887a30-e151-43d3-88c5-c72132168b30 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001576 | f15aff36-3bc9-438c-a63c-ca645724f429 | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001577 | 33a36958-bf7b-40c8-98d1-f464ccbbc43c | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001578 | 0c3a972a-3dd5-4a06-8099-7a1d398d1808 | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001579 | 16ae9330-11ff-4094-803d-f39ccab1c3db | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001580 | 1f4a5a02-fdf0-470e-bad3-be9c6b6f6aa8 | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001581 | 57ea4f8e-1cb2-4386-8cf9-598398f8cf65 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001582 | 5b56064e-0263-40c4-a8db-34fa3eea4c67 | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2026-08-19 | Level 2 | [8 empty] | LU | 2026 | 2
1120001583 | 9e48c790-e2a7-413f-91b6-3354d38fb056 | Pole | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001584 | 7f646cc8-76cc-43bb-aae8-524a35983e00 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-19 | 2030-08-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120001585 | 7dd00c6b-c76b-4d6b-8601-b04bbd63053e | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001586 | 83ae888f-6377-4005-871b-e9efadb05f62 | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001587 | 8224d06f-2e9f-48cc-acf7-f8d273e1ffaa | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001588 | 53ea2cb4-0a4c-4258-a625-abdb5fdd8121 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001589 | 4f70394d-f821-4e7b-a97f-875bbe78b92e | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001590 | 68153528-5e2d-4cd1-98cf-3fcd5d6ddf7d | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001591 | 616db1b0-453b-4a43-8169-1978795a3f8a | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2026-08-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120001592 | 1680d299-6faa-468d-901b-22fecd4514f4 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001593 | 1680d299-6faa-468d-901b-22fecd4514f4 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001594 | 10e7a84d-7197-4ab6-8055-7f49f0201c88 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001595 | 10e7a84d-7197-4ab6-8055-7f49f0201c88 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001596 | 012a0515-5292-4757-bf75-914c56217e3f | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001597 | 31a85b93-0379-4c70-877b-abf6b60003c1 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001598 | 27c4a65e-7e63-4936-a872-e7258bfdbd79 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001599 | 3cf41d31-fba6-4bd8-a1d4-c2e75054acb6 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001600 | e193ed5c-9229-4815-a188-cb4fba598aaa | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001601 | e193ed5c-9229-4815-a188-cb4fba598aaa | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001602 | d7ac4724-6c26-4d55-a1c2-486b0f587c01 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001603 | d936b034-5b43-4928-a7f2-54a4789a1947 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001604 | d936b034-5b43-4928-a7f2-54a4789a1947 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001605 | d730670c-610c-4d5d-b52d-b24319e6017a | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2026-08-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120001606 | d730670c-610c-4d5d-b52d-b24319e6017a | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2026-08-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120001607 | d730670c-610c-4d5d-b52d-b24319e6017a | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001608 | d730670c-610c-4d5d-b52d-b24319e6017a | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001609 | dc50c11b-92f7-4b47-b454-8dc02f562d49 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001610 | cf7e8cfb-e716-4b57-8b5f-de8272420093 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001611 | ceae4666-f159-40ca-8243-a512b2fb1165 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001612 | bb3f7481-5842-4e39-b8af-11e0cd028d65 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001613 | bb3f7481-5842-4e39-b8af-11e0cd028d65 | Pole | HFTD Tier 2 | Distribution | 2025-08-20 | 2030-08-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001614 | cdad1cf8-aeb9-45ac-a508-1a918a4a5441 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001615 | db6ab74b-2978-480c-92d7-ad6af13604f9 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001616 | db6ab74b-2978-480c-92d7-ad6af13604f9 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001617 | dd3c3d8b-cb54-4b8f-b26e-163c12f29bcf | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001618 | dd3c3d8b-cb54-4b8f-b26e-163c12f29bcf | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001619 | 3f197e02-fa0b-4037-83a8-0ad086d93a5c | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001620 | 418d5b98-bc4a-4f91-85aa-32583074731f | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001621 | 3437a83f-2c67-4789-b3b7-ca4a8df573e6 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001622 | 01a6dc81-6f0b-4f80-a096-e5e6b8f3660f | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001623 | 01a6dc81-6f0b-4f80-a096-e5e6b8f3660f | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001624 | 04a1ba90-377f-42b8-a005-c5b0ce8b8cc1 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001625 | 04d7f947-897d-411a-80ad-ab13948e6f47 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001626 | 72522a2f-be9a-482a-8b40-2a8943879c7f | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001627 | 6ed58bfa-42f6-421a-ac84-ec7ccd9c544d | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001628 | 5f1166fe-5823-4ecb-8329-db1e0035e9cb | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001629 | 5f1166fe-5823-4ecb-8329-db1e0035e9cb | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001630 | 7fea6d9b-9c55-4c17-ba2c-532591a10e04 | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001631 | 7e954307-c52b-4c47-ad2c-2108f448685e | Pole | HFTD Tier 2 | Distribution | 2025-08-22 | 2030-08-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001632 | df002475-eced-45c4-9d5b-e0ebb49c827b | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001633 | 369b89bf-75c1-409a-a958-dda7bcdc05fc | UG Transformer | HFTD Tier 2 | Distribution | 2025-08-29 | 2030-08-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001634 | 36e1123a-a83e-4d41-9abf-e89a4ee5d328 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001635 | 302a518e-8f28-450e-8ea9-cacf8ebb309d | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001636 | 298c893a-12a3-45b0-9394-c05001b01bf8 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001637 | 066f4e35-a84d-480f-9511-6862df91c283 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001638 | 11372e47-713e-40e0-a18d-f85e133df038 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001639 | 7e3e910d-93e1-4e8d-a66e-6340410c6509 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001640 | 7e3e910d-93e1-4e8d-a66e-6340410c6509 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001641 | 94ce918f-2d09-4c96-8206-522325683f64 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001642 | 9843dacd-75f3-4aa1-95aa-4823a31d6b91 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001643 | 5155ea8a-07d1-4495-a869-7a98e42b2106 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001644 | 5155ea8a-07d1-4495-a869-7a98e42b2106 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001645 | dae6ca81-6c75-4744-8586-14c89174dafc | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001646 | d5e8fefd-20f8-4e5e-8663-27a45686ffa0 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001647 | d90f5c97-1698-42c7-83cc-371218a1d7f9 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001648 | d0233026-422f-4ffd-878a-030c8317957f | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001649 | e504b315-c201-412e-935e-1f2c6d3d6bb7 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001650 | f01b8cd6-db3d-4146-99aa-acd8ef9acda2 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001651 | f01b8cd6-db3d-4146-99aa-acd8ef9acda2 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001652 | f01b8cd6-db3d-4146-99aa-acd8ef9acda2 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001653 | f01b8cd6-db3d-4146-99aa-acd8ef9acda2 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001654 | f333a926-e0cf-45d8-bcf6-4923dced600c | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001655 | c625a7fc-a11f-4c39-8235-5fcd06b7aebf | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001656 | cb2f13dc-81c2-4739-8ebb-47eb5e9e54a2 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001657 | cabb334b-e1cd-439a-b6ef-dfd898d1fa6c | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001658 | fd6f938e-177f-4d13-b108-032b8cfac96c | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001659 | fd6f938e-177f-4d13-b108-032b8cfac96c | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001660 | ffac77cf-de5b-4bc1-beb3-2cbf17ded467 | Pole | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001661 | f9530593-2ff8-4b0f-8344-b3f679ea4b89 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001662 | f9567086-d847-4168-92bb-f05db61e4a71 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001663 | c91631a0-ad45-493f-b754-5513dabd4864 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001664 | b99c1ff4-6702-4c7e-9ba2-c97bd7d93172 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001665 | a2acd1e8-fb2c-474e-89bf-a90f4053806d | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001666 | a2acd1e8-fb2c-474e-89bf-a90f4053806d | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001667 | a1e4cb87-357c-4836-95a4-f80ba8ec3457 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001668 | b2af3a84-ddf3-4580-ab48-55f1239b91fb | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001669 | ed95a3a1-0464-4ee2-a9ff-1ba38f8bdd80 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001670 | eaf203c8-e7ee-4936-a053-39d3776e2da3 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001671 | d0839e35-5823-4ad6-bf3d-14c66a47a788 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001672 | d6a9eaf0-6160-4fb9-a54d-42ad002b2126 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001673 | d6a9eaf0-6160-4fb9-a54d-42ad002b2126 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001674 | dcc2b8a6-2d4a-47e3-bb1f-a2890c942c35 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001675 | 4e0caca7-1e97-4af4-9215-c79d1b9cac40 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001676 | 5a837cb1-fffa-4cfb-9126-581501234391 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001677 | 8bfd6478-fa6b-4ef6-8b6a-227df926b816 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001678 | 8ef3d771-a12d-4f9b-aafb-5676e6790d3f | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001679 | 7aff6bd6-6a89-4bf1-ad55-bf115e48c248 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001680 | 750911ff-f60f-41d7-b81a-a91f946ec219 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001681 | 82e9df84-6b84-4a0f-9add-5525683012ee | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001682 | 82e9df84-6b84-4a0f-9add-5525683012ee | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001683 | 82e9df84-6b84-4a0f-9add-5525683012ee | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001684 | 10b19b52-4b4f-4c9a-98b4-c26cf69bf285 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001685 | 00045e89-24fe-4543-89b6-f8aed3eea4c4 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001686 | 17fb15d0-7351-414a-a970-a3f352c2ca3a | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001687 | 2869fb61-2601-4713-8836-728e5fb24edc | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001688 | 2869fb61-2601-4713-8836-728e5fb24edc | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001689 | 2d413b51-f680-45c3-9796-a4a5a26493dc | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001690 | 31773053-96b3-4cef-a94c-bf2a625b4e2b | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001691 | 31773053-96b3-4cef-a94c-bf2a625b4e2b | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001692 | 413ebd38-84fd-4d7c-8438-4009abdd46e8 | Pole | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001693 | 138ff73f-2948-4d16-ac21-be8c0a5753c2 | Pole | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001694 | 126f2e3a-d1e5-4dba-a1da-3d04dc46d94e | Pole | HFTD Tier 3 | Transmission | 2025-09-09 | 2030-09-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001695 | 86e91040-aeb3-47ef-85f2-f6a8451bacd7 | Pole | HFTD Tier 3 | Transmission | 2025-09-09 | 2030-09-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001696 | 7682a06b-6de9-422c-bbd7-03cec228e957 | Pole | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001697 | 4e77e3d7-e9b5-47a7-aa4b-a161b6fcd1f3 | Pole | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120001698 | 6c9da36f-4613-433a-aa97-f76e50dd0c8f | Pole | HFTD Tier 2 | Distribution | 2025-09-11 | 2030-09-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001699 | 0ee1aa4f-b3d8-492d-b074-5bcf66825a2d | Pole | Non-HFTD | Distribution | 2025-09-11 | 2030-09-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120001700 | 67477f2c-39a6-4a01-b243-96bc98257b50 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001701 | 67477f2c-39a6-4a01-b243-96bc98257b50 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001702 | 592cd76d-10a8-4d58-aa9d-45428645ad4a | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001703 | 5c162ede-7f6f-43be-afce-6755d8850365 | Pole | HFTD Tier 2 | Transmission | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001704 | 796aba62-d72b-42d6-bcbb-fc3f977dd0da | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001705 | 7ef5e0a7-2aea-4c90-b787-e65d3e2af34b | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001706 | dd389563-3be6-4eab-8d8a-f86f99773c46 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001707 | a35ccdaf-6f9e-4705-92d3-66985fcf6edc | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | 2030-09-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120001708 | a574d1e5-c835-476c-8188-491cea7430f9 | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2030-09-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001709 | dbab60e2-81fa-4ab7-b208-6b3d6881b93a | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2030-09-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001710 | d71c5b2c-4450-4d71-ae6e-6c36d6113a39 | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2030-09-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001711 | 923d9a93-4fae-4f58-b380-f27243900f56 | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2026-09-15 | Level 2 | [8 empty] | LU | 2026 | 2
1120001712 | 923d9a93-4fae-4f58-b380-f27243900f56 | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2030-09-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001713 | 3289f116-f7b4-4aad-97a6-90512558992b | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | 2030-09-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001714 | 4e989edd-15fe-4be2-9a87-05158c6ae1cd | Pole | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001715 | 4e989edd-15fe-4be2-9a87-05158c6ae1cd | Pole | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001716 | 4e989edd-15fe-4be2-9a87-05158c6ae1cd | Pole | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001717 | e072c98b-dcf8-404d-a941-4cd8aa192e9c | Pole | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001718 | e072c98b-dcf8-404d-a941-4cd8aa192e9c | Pole | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001719 | e9c4993f-825e-4998-a60e-ea29eb0aecd9 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001720 | eba852d4-903b-49c4-9122-d7b02c550f25 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001721 | d74cc430-af5e-4271-ab0a-fee9b5256dc9 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001722 | d86ef25c-19f5-4058-ad44-37ea632b87ca | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001723 | a595274d-898d-4856-88e3-27582cbfac60 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001724 | a7eae2f1-e4e4-44f9-b89e-ce52a919a1b7 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001725 | 9ffaf604-409a-45aa-8dd0-866bfcb5f6a0 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001726 | ba6bca75-6b98-45e3-b19e-c0f642e8d702 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001727 | c5ab2b67-21f2-4367-99f1-1babaec6ddf1 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001728 | 4ec0f497-35b2-4aec-8d3c-2c1763a9b52f | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001729 | 583ab233-2602-4c29-a989-0ff85dec00c4 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001730 | 5727074a-1a91-4918-b2ee-3c2bc85f8535 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001731 | 63a98e68-053b-4cec-a775-ad13903c7913 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001732 | 6f3f485f-daa8-46cc-9e09-95fc0e7c42ff | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001733 | 702ad50f-6738-43b5-9eb7-43eda63e20bd | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001734 | 8e88916e-d961-4f21-b8a4-baa0a4a89bdc | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001735 | 8e88916e-d961-4f21-b8a4-baa0a4a89bdc | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001736 | 8e88916e-d961-4f21-b8a4-baa0a4a89bdc | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001737 | 8e88916e-d961-4f21-b8a4-baa0a4a89bdc | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001738 | 974d7aed-27e9-4272-8946-66ddac60feb3 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001739 | 974d7aed-27e9-4272-8946-66ddac60feb3 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001740 | 77aa778b-6517-4a39-8ff5-51b6f30e3d94 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001741 | 731e18e4-24d5-47c7-902e-5cd29a0a1048 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001742 | 2e7054c2-4bfc-4e3f-9c2c-43950778a0c4 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001743 | 2e7054c2-4bfc-4e3f-9c2c-43950778a0c4 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001744 | 2c134ada-3fdd-4652-8373-fcd3844a44c2 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001745 | 2c134ada-3fdd-4652-8373-fcd3844a44c2 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001746 | 3b5ab9c6-54b7-4790-b5a2-2c8e549483da | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001747 | 3b5ab9c6-54b7-4790-b5a2-2c8e549483da | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001748 | 11ac4ced-ad1f-4ec1-a683-786db41af045 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001749 | 024c7f16-c548-4f24-8ceb-91e5f64f770b | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001750 | 024c7f16-c548-4f24-8ceb-91e5f64f770b | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001751 | 06106e48-1873-4470-bfc4-65053430f2d1 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001752 | 13499523-8e85-4e35-b908-9746606e7ba6 | Pole | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001753 | 9e0fc55b-c5b4-4425-a438-2be37a636ee5 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | 2026-09-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120001754 | 624118eb-1425-4c1d-91af-6a28a873b0e5 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | 2030-09-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001755 | 670a8c26-d990-403a-83bb-08d416415d20 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | 2030-09-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120001756 | 531fc56c-60c5-4d84-a822-945ada4f1574 | Pole | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001757 | 531fc56c-60c5-4d84-a822-945ada4f1574 | Pole | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001758 | 531fc56c-60c5-4d84-a822-945ada4f1574 | Pole | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001759 | 531fc56c-60c5-4d84-a822-945ada4f1574 | Pole | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120001760 | 62a3b30b-7c1b-4e25-8dab-b77eb148c85d | Pole | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001761 | 6031b292-2f30-422f-9d52-035079bd685c | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001762 | 8deb43ac-9beb-4f9d-9014-81c024399c88 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001763 | 25bccd6b-91db-4d64-9070-6578e8a92155 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001764 | 015b8d58-93ec-4896-9c63-8917cf07aba6 | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001765 | a08b67bd-335a-4722-a505-280de4006def | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001766 | aae93739-f3de-4e7a-9617-a92df44218d9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120001767 | b462202b-79c5-491b-935f-2a8f210702ad | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001768 | b462202b-79c5-491b-935f-2a8f210702ad | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001769 | e394bd92-e238-40d5-b695-a9c430030a98 | Pole | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001770 | e394bd92-e238-40d5-b695-a9c430030a98 | Pole | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001771 | 49fe14e2-b714-4168-a265-44718c9efc02 | UG Transformer | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120001772 | 4833fc34-f7ef-4db4-ab1b-abb53efd1ab1 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | 2030-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001773 | 02f3f002-599e-4bb4-a799-89debda768a1 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | 2030-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001774 | 02f3f002-599e-4bb4-a799-89debda768a1 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | 2030-09-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120001775 | 1c9fc150-eb40-42f9-8605-9afb12316f20 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001776 | 47b37d37-9197-4364-8fe2-e293924fd6db | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001777 | 35c77219-2141-405c-9e6c-c37525c24658 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001778 | 35c77219-2141-405c-9e6c-c37525c24658 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001779 | 8dd6590e-668f-45fc-a6ab-4716d723b8de | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001780 | 8dd6590e-668f-45fc-a6ab-4716d723b8de | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001781 | 8dd6590e-668f-45fc-a6ab-4716d723b8de | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001782 | 9a0b3a57-fa19-4757-84fa-c908eaa50fba | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001783 | 73a92b12-9c4d-426d-9f7d-7d41b69e0378 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001784 | 83d252ea-0553-4d78-9a28-9f810e6a5e4a | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001785 | 659df533-b9c5-444b-b3f6-573daee9c6aa | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001786 | 6dbf3c46-f4bf-4310-ba86-3f9043b73677 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001787 | 55ced008-d80a-4318-98b7-f43ac33567e6 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001788 | 55ced008-d80a-4318-98b7-f43ac33567e6 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-09-29 | Level 2 | [8 empty] | LU | 2026 | 2
1120001789 | 55ced008-d80a-4318-98b7-f43ac33567e6 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001790 | b016b536-793a-4f89-9ce9-5ea4561b06d6 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001791 | b016b536-793a-4f89-9ce9-5ea4561b06d6 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001792 | afc63002-4385-491b-b268-cbee7f31e3b7 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001793 | c7976e1d-087c-49b2-b5c3-8049d21ce9f1 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001794 | fea75bc0-04d5-4b11-83e8-acbb671dd1d8 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120001795 | f34d7bf0-2849-4d73-81be-4ca53a83e41c | Pole | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001796 | 7d0775df-c7ae-41c0-b020-00018db149d1 | Pole | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001797 | 23f881a2-dd7a-40ef-aabf-664702428c46 | Pole | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120001798 | 72161296-480c-4c49-adf5-6262fbdee639 | UG Transformer | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-09-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001799 | d2a81cc6-de29-421b-a6be-d47da88ceecc | UG Transformer | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-09-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001800 | f3d146e8-a23d-4f83-8d65-421f300a0d02 | Pole | HFTD Tier 2 | Distribution | 2025-10-03 | 2030-10-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001801 | f3d146e8-a23d-4f83-8d65-421f300a0d02 | Pole | HFTD Tier 2 | Distribution | 2025-10-03 | 2030-10-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001802 | dbf8b04f-46a0-4ec1-90d8-dcb215fb594a | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001803 | b766982b-67f0-480d-895b-33aea3758019 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001804 | b766982b-67f0-480d-895b-33aea3758019 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001805 | a50d4956-b655-4748-ab92-87aacd3a0313 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001806 | a50d4956-b655-4748-ab92-87aacd3a0313 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001807 | 5d8b50b2-c396-41b9-b546-41dfb9de0dc5 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001808 | 5d8b50b2-c396-41b9-b546-41dfb9de0dc5 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001809 | 5d8b50b2-c396-41b9-b546-41dfb9de0dc5 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001810 | 2042311d-fbd5-4d5a-a08d-2b3be4c9b4c3 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001811 | 141e2e2d-1ac4-4b8d-8d1a-61f44ca97d39 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001812 | 141e2e2d-1ac4-4b8d-8d1a-61f44ca97d39 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001813 | 141e2e2d-1ac4-4b8d-8d1a-61f44ca97d39 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001814 | 028e3536-2d54-4e54-9c79-b4d9ed505639 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001815 | 028e3536-2d54-4e54-9c79-b4d9ed505639 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001816 | 0920f0d8-cad6-4237-9ae5-e2d5a35d18b8 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001817 | 35ab9523-01d6-4c22-8002-a1fd283c0a92 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001818 | 3f562c53-5b53-435f-bd0a-b684a284dda6 | Pole | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001819 | 30315833-7973-4469-b64b-2962157a8650 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001820 | 30315833-7973-4469-b64b-2962157a8650 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001821 | 280ba639-7bff-4349-9408-0d3b1e4c32b5 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001822 | 106a774d-f407-48a9-aa32-adde9de80e5a | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001823 | 106a774d-f407-48a9-aa32-adde9de80e5a | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001824 | 53710a2f-657e-4e3f-9686-2c23b43c45de | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001825 | 4e350f4f-ec1c-48c3-9917-cc73a97c7661 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001826 | 667938b3-b9cb-4d1e-ac8a-9f14a8e8f872 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001827 | 667938b3-b9cb-4d1e-ac8a-9f14a8e8f872 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001828 | 99405cfd-82a1-4231-b5d7-03dbf5f89f0d | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001829 | 99405cfd-82a1-4231-b5d7-03dbf5f89f0d | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001830 | 99405cfd-82a1-4231-b5d7-03dbf5f89f0d | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001831 | a5851866-dd62-4a73-9f9e-2c10d5ddf55a | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001832 | a9a13771-5c1b-4bff-bfc3-f4793ad64528 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001833 | b08e15b6-c665-4803-996e-7b175c60b09b | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001834 | b08e15b6-c665-4803-996e-7b175c60b09b | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001835 | efc30f5f-6e38-4abf-bef4-fa6afa8ae233 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001836 | efc30f5f-6e38-4abf-bef4-fa6afa8ae233 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001837 | efc30f5f-6e38-4abf-bef4-fa6afa8ae233 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001838 | e47d36bf-d009-4e67-a81d-a5b506cf4aff | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001839 | e0bc45f2-3410-43f7-a8a3-41c8a76cfcb9 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001840 | e0bc45f2-3410-43f7-a8a3-41c8a76cfcb9 | Pole | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120001841 | e4cfdbce-c3ed-4b61-aeb7-dc4eeae00215 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001842 | f0f578ad-84b1-4bed-9301-311f964c5521 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001843 | f0f578ad-84b1-4bed-9301-311f964c5521 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001844 | db1a101d-37c7-4770-b8b8-d4e54a4ba486 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001845 | a238704a-7550-4538-846d-8686aa175a77 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001846 | c6897540-7efc-4b4d-bbad-cef57070e9bf | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001847 | f4d82712-00d1-464c-9856-d6f237868812 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001848 | f4d82712-00d1-464c-9856-d6f237868812 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2026-10-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120001849 | f4d82712-00d1-464c-9856-d6f237868812 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001850 | f4d82712-00d1-464c-9856-d6f237868812 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2026-10-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120001851 | f4d82712-00d1-464c-9856-d6f237868812 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001852 | 799dce0b-ad04-405d-a751-e00d30f7df42 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001853 | 760186a7-ae69-409e-b4f7-383369bd0ae8 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001854 | 81b7c103-e245-4e84-8055-b6dc03cd5d2b | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001855 | 81b7c103-e245-4e84-8055-b6dc03cd5d2b | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001856 | 81b7c103-e245-4e84-8055-b6dc03cd5d2b | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001857 | 85ed3587-bec7-4411-a794-d3cafff6f0ec | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001858 | 85ed3587-bec7-4411-a794-d3cafff6f0ec | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001859 | 85ed3587-bec7-4411-a794-d3cafff6f0ec | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001860 | 63cf5ce3-b73f-48b3-a97a-8289660051a1 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001861 | 5388548a-5157-411f-bd3b-69670671b792 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001862 | 5f3b5002-bd32-49a2-bb10-b1c473a861fe | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001863 | 5f3b5002-bd32-49a2-bb10-b1c473a861fe | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001864 | 02fcf98c-fc87-4f2c-b3e5-a35134f5bbed | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001865 | 13915d83-946d-46bf-8bdd-7293c3938631 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001866 | 19f14181-4868-4a48-abfb-45e9941b604c | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001867 | 1dd6b22c-175b-4c11-8349-8a92044d1626 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001868 | 1dd6b22c-175b-4c11-8349-8a92044d1626 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001869 | 1dd6b22c-175b-4c11-8349-8a92044d1626 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001870 | 487d7d86-c801-4a1f-b215-7f2e2e0f1e24 | Pole | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120001871 | 43b15b60-e4d7-43b7-b14e-4faaca677f9f | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001872 | 43b15b60-e4d7-43b7-b14e-4faaca677f9f | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001873 | 057fc16a-10b6-4c8a-9181-11724078692c | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001874 | 057fc16a-10b6-4c8a-9181-11724078692c | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001875 | 057fc16a-10b6-4c8a-9181-11724078692c | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001876 | 057fc16a-10b6-4c8a-9181-11724078692c | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001877 | 057fc16a-10b6-4c8a-9181-11724078692c | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001878 | 98c4efe0-51cb-4af6-8e43-7e64ec616e55 | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001879 | ef653620-ce16-4556-a8c0-c6ae4d0f82d3 | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001880 | ef653620-ce16-4556-a8c0-c6ae4d0f82d3 | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001881 | ef653620-ce16-4556-a8c0-c6ae4d0f82d3 | Pole | HFTD Tier 2 | Distribution | 2025-10-10 | 2030-10-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120001882 | a5b2ebc5-6518-4b41-8eea-831368a9dea9 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001883 | a7f500f0-7da6-4824-8ac6-91151558111b | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001884 | a7f500f0-7da6-4824-8ac6-91151558111b | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001885 | b13211d1-cfcc-4f53-82cf-095786cf39b6 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001886 | b310a77f-826c-4fef-a45c-17ca8ae9fa49 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001887 | aa23287b-89a2-4804-a219-6359d7fb783a | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001888 | aa23287b-89a2-4804-a219-6359d7fb783a | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001889 | f4b0403b-9f84-4bdc-b698-c0f39e850ed9 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001890 | fad8dc68-19de-4e0a-9ccc-54ab881ce7d8 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001891 | fad8dc68-19de-4e0a-9ccc-54ab881ce7d8 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001892 | 902aa66b-4bf5-4e4a-b970-40b2549cd546 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001893 | 58e3604d-a094-472e-bd73-26d2c41582d5 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001894 | 621bf7fd-5e18-4476-a34d-ca78d694c751 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001895 | 474e2204-10c3-4ff5-9a0e-2866d7e9d511 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001896 | 3ba0cc8f-f35f-4812-b2d8-f7f4c7d2e79b | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001897 | 3ba0cc8f-f35f-4812-b2d8-f7f4c7d2e79b | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001898 | 29bb8760-9a4f-48b7-a1e7-bbb71adfa112 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001899 | 29bb8760-9a4f-48b7-a1e7-bbb71adfa112 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001900 | 303e23a1-e895-4be2-8294-2196a0e6ee30 | Pole | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120001901 | 34c33e31-14f0-48a4-a83d-61255b3a8e69 | Pole | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001902 | 34c33e31-14f0-48a4-a83d-61255b3a8e69 | Pole | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120001903 | 137b8de2-a869-4e8a-acb0-48ff3e9db558 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001904 | 137b8de2-a869-4e8a-acb0-48ff3e9db558 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001905 | 53c50980-87a2-4ee7-acdf-900c552b7aaa | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001906 | 7ee24948-b6af-4df6-95f1-ea90d9c52b00 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120001907 | 96bf0877-a05e-42b5-9663-03d891c9a242 | Pole | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001908 | ef40babd-6159-483a-b0be-e16a9ab77671 | Pole | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120001909 | 974eeb98-f60f-4db0-9e79-7926317aa8f3 | UG Transformer | HFTD Tier 2 | Distribution | 2025-10-17 | 2030-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001910 | 063f8b1e-8c7c-4b43-96f9-ca3a3944c187 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-10-17 | 2030-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001911 | 304f3fb9-dca8-416a-99c9-cd598b4f99df | Pole | HFTD Tier 2 | Distribution | 2025-10-17 | 2030-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001912 | 3bfe34e1-19d4-4552-95a4-895a472aa3d0 | Pole | HFTD Tier 2 | Distribution | 2025-10-17 | 2030-10-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120001913 | 12762675-9a37-4718-afde-104bc5b8817d | Pole | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001914 | ede8fcd6-9479-49f3-b596-f62dcde4811e | Pole | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001915 | d10f1132-89ef-4285-bef7-42e3f8eab684 | Pole | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001916 | f40369eb-dfe3-4ba3-bff1-ea1d2ef23c31 | UG Transformer | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120001917 | 641ad85e-b788-41ff-be0c-8910897ce4d3 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | 2030-10-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001918 | 641ad85e-b788-41ff-be0c-8910897ce4d3 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | 2030-10-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120001919 | 6f6d024b-ea3c-4f81-a8b4-3aae27003e21 | Pole | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001920 | 98540507-fd97-4282-a6d1-d94b4eba4615 | Pole | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001921 | 98540507-fd97-4282-a6d1-d94b4eba4615 | Pole | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001922 | 0d2705dc-0f23-4d44-a47a-bd2f46e56641 | Pole | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001923 | f65cd8dc-70ef-4ec2-9d69-263628d62d43 | UG Transformer | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001924 | b7db79a4-fd1d-4dbe-96a5-224feb0dc156 | Pole | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120001925 | b4ec70cc-60e2-4a54-8d22-3319c93b4e8b | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001926 | b0b517db-6fbf-439b-80cc-c89af8b14c87 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001927 | a40280d5-c553-4270-88cd-af4f91cc4f34 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001928 | d51f8ab6-4e22-4177-a4cf-b75bd2b9282c | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001929 | e77efbe0-7842-4136-9072-2f00c7bebc55 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001930 | 1396aa7e-4e1d-40fa-a03b-50f9a4790386 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001931 | 159d7131-4479-41b2-8234-d3c8a5b5865f | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001932 | 159d7131-4479-41b2-8234-d3c8a5b5865f | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2026-10-31 | Level 2 | [8 empty] | LU | 2026 | 2
1120001933 | 159d7131-4479-41b2-8234-d3c8a5b5865f | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001934 | 328ba8a9-728f-46a8-8332-a2054c1a5916 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001935 | 381250aa-fd9a-487d-afeb-1ce9cb2077f2 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001936 | 9afdf25a-2a27-471f-913a-ef7211412561 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001937 | 9c591c77-bcfb-415d-89a3-70adec011812 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001938 | 9c591c77-bcfb-415d-89a3-70adec011812 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001939 | 80809253-ba44-485e-bf64-b08687a38c18 | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001940 | 6f9c73ca-2e04-4070-b878-72489734e45e | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001941 | 6f9c73ca-2e04-4070-b878-72489734e45e | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001942 | 55894b10-a300-42e3-a45b-bfe7d19b0e6b | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001943 | 55894b10-a300-42e3-a45b-bfe7d19b0e6b | Pole | HFTD Tier 2 | Distribution | 2025-10-31 | 2030-10-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120001944 | 5031afa2-6a43-43f7-901c-a333fde78fbe | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001945 | 6cd52cba-0adf-49d3-b4ac-87ed5d593e1c | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001946 | 6891f71a-1989-4a2d-92d8-25d75265e75f | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001947 | 6891f71a-1989-4a2d-92d8-25d75265e75f | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001948 | 7ffcae24-7eab-45e4-a498-87b6120651a6 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001949 | 7ffcae24-7eab-45e4-a498-87b6120651a6 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001950 | 304147bd-0aac-4a30-9528-c49940988eaa | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001951 | 302760cb-d279-4374-aea1-2c91c7b63605 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001952 | 3e2583c7-428a-4a74-a911-bac8bc644d9d | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001953 | 12d4eebe-4f59-404e-8b27-8db6bdd48354 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001954 | 12d4eebe-4f59-404e-8b27-8db6bdd48354 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001955 | 12d4eebe-4f59-404e-8b27-8db6bdd48354 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001956 | 1d17c299-0e58-4959-8621-60add5538869 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001957 | 1d17c299-0e58-4959-8621-60add5538869 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001958 | ee2884b5-bfa1-49c2-9a73-6a170266b959 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001959 | ccd54631-7b2f-4eb0-8d3d-ce9e979f2456 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001960 | a8dff7df-b82c-422e-b845-33fdc2ba8378 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001961 | a1084a3d-fc76-46a4-9177-2bc9d817af71 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001962 | a3e96086-5e97-4b09-8710-9818f4137a01 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001963 | 9fe039f5-83b3-409e-93ca-143a2529f31e | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001964 | b8d9dba3-79f5-40fe-8208-8d81cf868604 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001965 | c3643035-93c9-418c-ab7e-da7b72cdab97 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001966 | f501ee75-acc5-4dcb-aed8-be6609cc3c67 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001967 | febfec91-ed45-4195-9ac6-1b925ee2938f | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001968 | fed49d36-2afb-4127-934c-4196ec56d77e | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2030-11-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120001969 | fe93f4cc-b64c-49c0-9732-7dc8e8f34337 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001970 | c08eed45-bd87-418b-8ae2-52ba9d82d714 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001971 | a3692415-0e5f-4d6d-95cd-72b76992472b | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001972 | a2b07c75-6a97-45b0-bd03-93164139cf71 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001973 | b4dfb309-ecfd-4231-a91b-7acadde23aaf | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001974 | dd1bfe02-1df8-42b3-8509-5e72daa9a05a | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001975 | dea940e2-1b9b-4ed6-8798-55d02f3ec628 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001976 | f3e9b31c-a622-41f9-8d09-b57bf3e74b3e | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001977 | f3e9b31c-a622-41f9-8d09-b57bf3e74b3e | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001978 | 16eed5f1-221d-46d1-8769-cdf0a11f5783 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2026-11-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120001979 | 16eed5f1-221d-46d1-8769-cdf0a11f5783 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001980 | 0bc3c561-5dab-4a5f-80c9-06b1c2d1710a | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001981 | 002d0d7b-0bcc-4996-b77d-ca975073ad8c | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001982 | 3dbfbf38-3331-4fd2-a0c0-fa2580911fe3 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001983 | 3dbfbf38-3331-4fd2-a0c0-fa2580911fe3 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001984 | 3a2d2f50-06d8-4f25-85bb-b20ceca6e11f | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001985 | 3a2d2f50-06d8-4f25-85bb-b20ceca6e11f | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001986 | 29d534fb-22fd-448a-ad9d-3298344e860f | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001987 | 81bf7961-dc38-4a86-895b-f8b283171c3a | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001988 | 88f91c2e-5e4b-4e87-a2f7-6039dc0b383c | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001989 | 7e54b5b0-2729-4cb0-99dc-65c014e95fa6 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001990 | 9bd69555-f3a0-474f-b0d7-62b632da2eaf | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001991 | 6cb68a0c-7ef8-4780-b32a-d3c08a3e26bd | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | 2030-11-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120001992 | dbdcf664-ce56-47dc-909a-a7d85c18e1d8 | Pole | HFTD Tier 2 | Distribution | 2025-11-05 | 2030-11-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001993 | c5ebaed1-7dc7-4e4d-8f07-6e2b7711f076 | Pole | HFTD Tier 2 | Distribution | 2025-11-05 | 2030-11-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001994 | c5ebaed1-7dc7-4e4d-8f07-6e2b7711f076 | Pole | HFTD Tier 2 | Distribution | 2025-11-05 | 2030-11-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120001995 | c5ebaed1-7dc7-4e4d-8f07-6e2b7711f076 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001996 | c94a5a1a-8b0a-4f0f-b002-6868a96d6a2e | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001997 | c94a5a1a-8b0a-4f0f-b002-6868a96d6a2e | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001998 | c3a4f71a-5e69-4b8f-b809-f3cad502997c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120001999 | c3a4f71a-5e69-4b8f-b809-f3cad502997c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002000 | c3a4f71a-5e69-4b8f-b809-f3cad502997c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002001 | c3a4f71a-5e69-4b8f-b809-f3cad502997c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002002 | c3a4f71a-5e69-4b8f-b809-f3cad502997c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002003 | b176db59-1fed-40fe-9fd9-c55fcda261c8 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002004 | ac406e62-7582-425a-85b7-d49a9ceee622 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002005 | abd30dc8-77b4-4260-b26c-f56893f60661 | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002006 | aba0f13b-8ca2-4b49-ad8b-90ba34d6c3e4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002007 | dbdcf664-ce56-47dc-909a-a7d85c18e1d8 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002008 | d1f9646e-8c69-4053-9c4d-d41f575be6b6 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002009 | ee0fd98f-7b47-48db-a59e-876a3fa5adf3 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002010 | e107d11f-2d7c-4bc1-bcde-4e2779a6cee4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002011 | e107d11f-2d7c-4bc1-bcde-4e2779a6cee4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002012 | e107d11f-2d7c-4bc1-bcde-4e2779a6cee4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002013 | e107d11f-2d7c-4bc1-bcde-4e2779a6cee4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002014 | e371184c-17c0-456a-93dc-b0efc144c1a5 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002015 | f3f9a090-bc3e-45e1-b804-2e5e038b6716 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002016 | 6b49973d-eb0e-4748-aa27-c7241e08984c | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002017 | 6aeb3535-438f-43ca-a231-72fb3441ef27 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002018 | 6981f960-c5de-4bff-a6d5-b61dd2498429 | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002019 | 7048fae7-922b-4498-b02a-72c512e320a7 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002020 | 7048fae7-922b-4498-b02a-72c512e320a7 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002021 | 7048fae7-922b-4498-b02a-72c512e320a7 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002022 | 683f048a-08f7-4fdd-bffd-e1633641b11c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002023 | 683f048a-08f7-4fdd-bffd-e1633641b11c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002024 | 683f048a-08f7-4fdd-bffd-e1633641b11c | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002025 | 621536d0-1ae2-4047-b642-43f12c5177bd | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002026 | 621536d0-1ae2-4047-b642-43f12c5177bd | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002027 | 621536d0-1ae2-4047-b642-43f12c5177bd | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002028 | 60dbf92a-a75e-4b8e-9f76-b0c4dd2d176f | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002029 | 5ed4632c-a20f-439a-bda2-af2ba521efa3 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002030 | 90867ddb-f215-40bd-b7b1-b156292b3707 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002031 | 941af178-a813-4989-b33a-2823eeafdf94 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002032 | 941af178-a813-4989-b33a-2823eeafdf94 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2026-11-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002033 | 82ea74f5-d784-4fa9-bd8e-671304406e4d | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002034 | 82ea74f5-d784-4fa9-bd8e-671304406e4d | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002035 | 82ea74f5-d784-4fa9-bd8e-671304406e4d | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002036 | 37d322e2-d0d6-4b1a-be9e-49f8cff7b6c4 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002037 | 4603f377-7eec-4fae-a930-d8edd0466c51 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002038 | 4623b991-1426-45a8-9173-5af4412cba42 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002039 | 4ac4b25b-68d8-4163-812f-86f0b4747be9 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002040 | 0b53d028-876d-46ae-b60a-a17b8ce44207 | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002041 | 0a360ff1-dbdf-4da2-9eb2-78d1011bd955 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002042 | 1686bf7d-0194-4288-9d81-518c430a2590 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002043 | 1edba41f-32bd-44be-a16f-4ea49445ee9e | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002044 | 1db71ab3-a48c-4b6b-9cb7-26db00a06d70 | Pole | HFTD Tier 2 | Distribution | 2025-11-06 | 2030-11-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002045 | 01965cac-0935-457b-8605-028bf73790dc | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002046 | 880903d0-3d10-4773-8d53-e18f048da9c1 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002047 | 7f5b2ebc-5419-4cdf-8561-0f3ec14e54db | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002048 | 7f5b2ebc-5419-4cdf-8561-0f3ec14e54db | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002049 | f05ff20c-f4a6-44ee-a89a-95e920890708 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002050 | b3bbde73-88ca-4696-8a2f-93b15d6efd61 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002051 | b4c075e5-cb2c-4c05-bd5c-f9e6204136bb | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002052 | b4c075e5-cb2c-4c05-bd5c-f9e6204136bb | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002053 | b16426d4-358d-4d8b-9cfc-bc875839ce98 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002054 | a34af649-0e68-48a1-8354-594c99e2b8f5 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002055 | c4c72508-b9a3-4ed8-b561-ba3a76513e66 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002056 | c4c72508-b9a3-4ed8-b561-ba3a76513e66 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002057 | c4c72508-b9a3-4ed8-b561-ba3a76513e66 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002058 | c4c72508-b9a3-4ed8-b561-ba3a76513e66 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002059 | c6a78ebf-2333-4dc4-a10d-f8642490e7c5 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002060 | bd0cbbe3-896c-44d4-b84a-41aad5db6b01 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002061 | b8e961ab-d2e9-4004-8e2c-0acdc7903010 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002062 | baeec05e-f981-4e19-b5d4-e5d496702fab | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002063 | ee23ae9e-fb7f-48dc-b050-7a51cd2dc9c6 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002064 | ee23ae9e-fb7f-48dc-b050-7a51cd2dc9c6 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002065 | ebcf11f9-6be2-4880-8bfa-d2985d26eff6 | Pole | HFTD Tier 2 | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002066 | d39cdba5-91c0-45c5-b22e-34df0dba400f | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002067 | db48d087-96be-4a05-aec0-28c56f6862de | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002068 | de45b8fc-099f-4a52-afc7-70c2d66ae891 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002069 | d5fa17af-5d93-4823-aee1-483e68381e3a | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002070 | d5fa17af-5d93-4823-aee1-483e68381e3a | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002071 | fd07208d-fe9a-40b1-975a-b49e2701d47a | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002072 | fd07208d-fe9a-40b1-975a-b49e2701d47a | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002073 | fcd47ea7-5312-4ced-955b-0806697cae83 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002074 | 7a9d941b-a062-4d75-869c-9ab06abe363b | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002075 | 90f45e8f-ff00-4ae5-a2a1-8ffca3b203f6 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002076 | 8cbdcbb7-02cd-417b-9ba1-d5ff2938b522 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002077 | 8cbdcbb7-02cd-417b-9ba1-d5ff2938b522 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002078 | 9e4169ac-fadf-48d1-b5cc-2670b844a6fa | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002079 | 9d079cf3-7b04-4d87-abc3-26ba6aafbc57 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002080 | 9b646215-e019-4691-84cb-219974686f42 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002081 | 9b646215-e019-4691-84cb-219974686f42 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002082 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002083 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002084 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002085 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002086 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2026-11-14 | Level 2 | [8 empty] | LU | 2026 | 2
1120002087 | 990ce327-2f36-4b42-b8ab-880044e284b8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002088 | 9567cd21-2b33-493a-a6e6-264d749290a9 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002089 | 5b6a18c7-869f-454f-a55d-47d7acefa2e3 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002090 | 59a32802-f3d5-4ac0-8783-0d889cbf9ff8 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002091 | 4f88b4ab-8c0d-4317-a6c1-463f490313be | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002092 | 51ae6ee1-b8f5-42d9-90bb-a0ada0788a89 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002093 | 67666814-2f06-4438-8da4-596974c1ad80 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002094 | 673d31a6-cbd7-4ca7-83ec-e09f91a7f0c7 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002095 | 6eea3a2a-c127-483e-9efa-e727b8e8f993 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002096 | 0d4ec441-20e0-4539-a636-b1959a30a386 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002097 | 0f169a7f-646c-44ad-8198-31597196ea35 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002098 | 145b1bbf-a0af-4b8b-b043-d59277fe491c | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002099 | 4ad54612-ca4e-4ab0-ada5-8fbef8dd9456 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002100 | 4ad54612-ca4e-4ab0-ada5-8fbef8dd9456 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002101 | 4ad54612-ca4e-4ab0-ada5-8fbef8dd9456 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002102 | 4ad54612-ca4e-4ab0-ada5-8fbef8dd9456 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002103 | 4ca380a7-a23f-42d7-8520-380a62d917c4 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002104 | 49b91161-3ff6-40a7-a93a-32eeca129ee7 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002105 | 3960bbb3-deb6-4063-be0d-1e56e72db0d5 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002106 | 3cbcafa5-126c-436d-aec4-ad151ef9af48 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002107 | 3cbcafa5-126c-436d-aec4-ad151ef9af48 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002108 | 3528ccd9-6203-4a3d-920c-311206c4e199 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002109 | 2fa95917-fdb3-42a5-b6f8-242b4e840ce2 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002110 | 2fa95917-fdb3-42a5-b6f8-242b4e840ce2 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002111 | 2fa95917-fdb3-42a5-b6f8-242b4e840ce2 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002112 | 2f35aa13-d3cb-4cd7-a466-c6f645657a8d | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002113 | 299e2fda-d75d-4351-a717-4453726f0211 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002114 | 299e2fda-d75d-4351-a717-4453726f0211 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002115 | 299e2fda-d75d-4351-a717-4453726f0211 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002116 | 29a8161e-a0c5-409b-831b-bd89828adccd | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002117 | 29a8161e-a0c5-409b-831b-bd89828adccd | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002118 | 29a8161e-a0c5-409b-831b-bd89828adccd | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002119 | 29a8161e-a0c5-409b-831b-bd89828adccd | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002120 | 2bdf952a-300d-4f06-a24c-cd376f3494f2 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002121 | 2bdf952a-300d-4f06-a24c-cd376f3494f2 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002122 | 2d7d0503-0de2-40ba-a7c0-d26f32b82796 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002123 | 2dd276e9-ac75-4247-8104-0ededc57a218 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002124 | 2c9a692a-76cd-4046-83d4-944be1206e53 | Pole | Non-HFTD | Distribution | 2025-11-14 | 2030-11-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120002125 | 337a16dc-f099-4955-9a92-4b13bbdf4c28 | Junction Enclosure | HFTD Tier 2 | Distribution | 2025-11-15 | 2030-11-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002126 | 36a71fdf-c8c2-4d15-ae7e-8fd7d1c0dd44 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002127 | 2ae602d1-c5f4-4871-b38d-66f2640b7089 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002128 | 2bbb196d-7f9d-423f-a696-5ea7ca72df08 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002129 | 3cb72111-611f-470e-bec5-23ee2fbbb2e6 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002130 | 39074127-2c89-45ee-97fb-be3784bd4674 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002131 | 427cd8d4-8566-49b1-bd5e-3e899b08676a | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002132 | 13e4e0d7-1864-4ca7-9008-9eb618078636 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002133 | 196870e0-8e42-4aa6-ba8b-217798e5e4f7 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002134 | 1896a536-5832-42b4-aa27-af2a0dbc2b2d | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002135 | 118a425f-5868-47cd-93c3-91a9074179a5 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002136 | 033ff3bf-e488-4713-905b-85b53f70674b | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002137 | 0858a678-b631-4fa8-a7b2-f65a0b696c43 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002138 | 0858a678-b631-4fa8-a7b2-f65a0b696c43 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002139 | 0858a678-b631-4fa8-a7b2-f65a0b696c43 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002140 | 6ed0250e-67a0-4538-90dc-9e18bc322cb2 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002141 | 6cb9126d-fee3-40cd-87b7-63f351b3b011 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002142 | 62b4de4e-95f5-475a-93a0-f974f1355fe7 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002143 | 521debe2-b290-4793-ae06-819f8734ebf0 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002144 | 54427359-42ef-47ee-97cd-f7f05dd5558e | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002145 | 54427359-42ef-47ee-97cd-f7f05dd5558e | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002146 | 59e6aa8f-3745-40d9-ade1-c3ce896d8e86 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002147 | 5cdbc0b8-4c7c-4a43-8397-0069070c39c4 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002148 | 95421344-5e5f-42a6-8e09-14ed0d23707b | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002149 | 9102b48e-2153-42b8-b708-00227cb65ab5 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002150 | 8f3e4ade-a94a-420b-b00b-37bd97b159ae | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002151 | 92553cce-55d4-4a6c-a84d-84a0db94bbcd | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002152 | 91b9ab0b-86ec-48ab-a066-0935f12b5895 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002153 | 7f0aa5c5-ecf2-494d-846e-a18c3966197d | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002154 | 7f0aa5c5-ecf2-494d-846e-a18c3966197d | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002155 | 75c673ff-8ad2-4111-81b8-1c761c25b2ff | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002156 | 802c5337-c0e0-4dd7-a7cf-9fae9f6d913d | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002157 | 802c5337-c0e0-4dd7-a7cf-9fae9f6d913d | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002158 | fb7d0559-2133-4221-a42a-2887e17ad937 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002159 | fa60117a-0d99-46d7-8059-4924d287c023 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002160 | fd960c00-79a7-486d-a33a-18a228f70e94 | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002161 | f102c286-796c-43b0-a7be-4bf9eed0f72e | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002162 | e5ef51ef-2927-4869-b4e8-daab11c18337 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002163 | e5ef51ef-2927-4869-b4e8-daab11c18337 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002164 | e8ff3e87-31f3-4d9c-82a4-3ea3bcdd480e | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002165 | e8ff3e87-31f3-4d9c-82a4-3ea3bcdd480e | Pole | Non-HFTD | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002166 | bab61545-c770-4b08-b4e6-168007f8cc6e | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002167 | bab61545-c770-4b08-b4e6-168007f8cc6e | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002168 | b6a863f9-797c-4de2-a8fe-b9c642594477 | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002169 | a47ee31d-b9ea-4f7e-a148-fb45e1364320 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002170 | b44502c9-aabe-4fc1-b3ea-50f7fe4c7e6f | Pole | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002171 | b30100ad-9ab0-42c0-9824-186e219b9b4c | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002172 | b4407ef7-bfe3-41c8-8f91-4cefe27fb5c7 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002173 | aa4d5f2c-397b-4f2e-b8d7-e6c5f0b1213d | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002174 | aa94e8ab-4497-42cf-8e48-edcdd811ec05 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002175 | ad27d122-b02d-4555-8682-d567c4360282 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002176 | b841a884-3301-4c62-93c2-5aafdb928fd1 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002177 | bb8c08e2-f5a6-4f6e-9b79-d0cb9732c1a8 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002178 | bdc2a0f6-5fb6-4a13-a408-af66849da86a | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002179 | c8afaa2d-fbc3-4acb-aab5-da9c14fdb485 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002180 | e86aefb2-8c6f-4afc-bd2f-b734cc86387b | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002181 | f3aa9194-b422-4a72-8acc-e2ee11509fb0 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002182 | f3aa9194-b422-4a72-8acc-e2ee11509fb0 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002183 | ec1c4916-a08f-4771-85a4-d269ad5230bb | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002184 | d37e6dcb-5b0f-4995-8a1c-bab94c814d21 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002185 | ce5d2d58-b527-4c26-a997-2e3cf062d6fb | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002186 | f9e93aae-c2ad-491b-ba91-4c904afa012a | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002187 | fc0cf5b8-af76-4cb9-8e35-c2f4268ff8be | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002188 | fc3f6382-34ea-4ffa-8153-082f1c8360e6 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2026-11-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120002189 | fd6dcd55-c72b-4897-bee9-0c260597dc0c | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002190 | f835d2b1-34b1-4b8e-a595-08e8ab1d1c59 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002191 | 823b804c-0999-427f-b961-fd90cc08a80a | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002192 | 81ba6bd1-92cb-4956-a4a0-08f230a13263 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002193 | 8555868b-d753-4199-b1fa-35a6f8de722c | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002194 | 8954ebf2-d83f-4af5-a5d5-ebd4a8775a73 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002195 | 7e43d306-47ea-4788-9e1f-bbf0d5d800c6 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002196 | 921494aa-dc8a-41e7-a43d-31882a3fdf66 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002197 | 8c9676a1-f7a4-4008-bc06-d218df60dbda | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002198 | 8c9676a1-f7a4-4008-bc06-d218df60dbda | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002199 | 8b6e9461-3b62-4b3a-8566-45eb000fe4de | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002200 | 8ed7ea86-8669-41d3-a2a9-07b902f7a169 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002201 | 96f5a103-5abf-4211-99f8-ff62450891bb | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002202 | 96f5a103-5abf-4211-99f8-ff62450891bb | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002203 | 9e4cf41d-313d-4429-ae74-fc2647ad5e1d | Pole | Non-HFTD | Distribution | 2025-11-18 | 2026-11-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120002204 | 9c35ac34-d236-4667-b36b-781653bd8525 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002205 | 5e9851b6-3dbe-4383-b066-748e8041e3d6 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002206 | 5e301ef5-7907-46c4-9fa4-39aa0611ef93 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002207 | 5734abe3-3236-4587-9569-df004a0b709b | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002208 | 5585426d-1ee3-446d-bf5e-4cc37a86362e | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002209 | 5163d130-84bc-405d-b566-b7d7da8a2b99 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002210 | 621a43fb-6f5e-48cc-8336-39a9a6e2e61d | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2026-11-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120002211 | 60c7d90c-7a03-461c-8d08-75dd554d1519 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002212 | 7022212f-64d3-4c5f-a367-d9e71405b845 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002213 | 705f3846-fe0c-4f25-a1a3-fdc3bda57738 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002214 | 07303944-316c-41b6-81a5-1635dc4249d8 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002215 | 12a51c70-0c93-49a3-8673-5efa928e17cf | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002216 | 12a51c70-0c93-49a3-8673-5efa928e17cf | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002217 | 112d05e0-fdeb-4b80-b52f-4a0556251cec | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002218 | 11843979-0fc9-40f6-a13e-1f4ee55646fa | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002219 | 0f7dd7d4-b6d8-4a8b-b9eb-7651be749259 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002220 | 17989dd0-1dbe-4e3f-81d4-62dfe2e0b415 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002221 | 19ebf6a3-eb36-4b72-8fc5-b11a4b5154e8 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002222 | 1a74e4bd-f8be-4fd1-9937-cedb46ba91c3 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002223 | 1a93e455-3d16-4e8e-b207-15f46a69b3da | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002224 | 16c156f1-34b5-42d5-90aa-25078fee990a | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2026-11-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120002225 | 1742d97e-00df-4fd0-8829-ecf1ed3759d7 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002226 | 1b8d80a6-e54a-4814-a4a8-80ef5bd43c79 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002227 | 1b8d80a6-e54a-4814-a4a8-80ef5bd43c79 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002228 | 24b6b2fb-5232-4ec8-a6a8-f369924252d6 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002229 | 3ed84b32-9ed1-48ba-a7f5-3c1419de1320 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002230 | 4a0c2e0c-22fb-4265-88fa-f412e36dc482 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002231 | 4b4d3f37-d16c-42a5-aa3c-4cb098118130 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002232 | 46a7ea4a-6f6f-433d-b5d8-3760d9b489f0 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002233 | 2c356d5e-0192-4be4-8070-387813cfec6f | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2026-11-18 | Level 2 | [8 empty] | LU | 2026 | 2
1120002234 | 2d4f6a88-7470-4c3b-a97b-72b542e61910 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002235 | 284fd4ee-2387-489c-8a1a-795669b58078 | Pole | Non-HFTD | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002236 | 332f421b-421d-4f1d-b280-5a18da697f4f | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002237 | 3093d618-a3fe-4975-86ee-d1dc8d67a0f6 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120002238 | 17669aea-0903-46de-abee-5c61611ba062 | Pole | Non-HFTD | Distribution | 2025-11-19 | 2030-11-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002239 | e3c390e8-9933-4e00-8fcf-00426308a629 | Pole | Non-HFTD | Distribution | 2025-11-19 | 2030-11-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002240 | b41b101b-63d5-4d69-8c61-3ddba88b899d | Pole | Non-HFTD | Distribution | 2025-11-19 | 2030-11-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002241 | aead3865-0090-4826-9f84-8f22d3f0b243 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002242 | a4314ab4-c9c3-42e8-8258-75bab6108634 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002243 | a465a9e1-ad13-422f-b8b1-11fd281670cb | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002244 | 9f2e553b-3301-45f9-9596-af16441ca3e0 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002245 | c5a15310-fb07-4ea8-9584-e04eb3f62939 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002246 | c5cff97d-dc54-4286-bdd9-94638438e8d8 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002247 | c001c767-7643-4097-9886-daff3c0cd880 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002248 | e41d42ac-3b67-4d0d-a0ad-a201ed2c14aa | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002249 | f3ad4564-e268-4821-be81-82d460cacba7 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002250 | cfbf2eef-a46f-409a-9817-46cbffb60af0 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002251 | 1a34c5fd-4f84-4be0-a6b9-4dc9856a4cf5 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002252 | 13ec8c0a-989d-4dd7-8d19-f50e2aa29ea6 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002253 | 13a49834-f2ec-4960-9e11-50b253863be7 | Pole | Non-HFTD | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002254 | 25c02058-a726-4144-b9ce-64644b441672 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002255 | 0b7ad1fc-6e46-41a0-9d10-4ce1d647e1b3 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002256 | 0b7ad1fc-6e46-41a0-9d10-4ce1d647e1b3 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002257 | 00a483fe-a76c-42ab-ba76-bb4e20a9bb81 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002258 | 300ea9fa-9165-42b9-8aeb-e79f76c89ae5 | Pole | Non-HFTD | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002259 | 300ea9fa-9165-42b9-8aeb-e79f76c89ae5 | Pole | Non-HFTD | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002260 | 2ece344a-4af5-485b-860e-b8121a074d6f | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002261 | 32d91feb-fefd-480a-a90f-69427082cc66 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002262 | 3590c08d-9a0f-4cb6-9864-167cc77e1f98 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002263 | 26f5f852-a371-48af-ad15-fd9a46bdc540 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002264 | 2ce02870-b028-4090-8fac-493aaba3ba69 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002265 | 4a50c9a5-fb63-4ed7-9954-0e71e87c3fd2 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002266 | 49dbe4cb-c9f5-435e-8d40-b03f6d640f62 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002267 | 4955b8ec-2a24-41db-8504-982bc7b299e1 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002268 | 40260d3d-10cd-4a1e-bf92-4f4a90e1b8af | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002269 | 42f2f630-7626-43c4-af4e-bb6b90727ddb | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002270 | 42f69afa-ddaf-4cd0-8e54-a9e3708d80b3 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002271 | 71fba3b4-1756-428d-b13b-92ce88f1d522 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002272 | 6d614128-c13c-42e5-9627-65463318b543 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002273 | 6b0cb359-5a39-4cd0-aa37-b5d8550044ca | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002274 | 63e39fd1-a166-47f4-8653-1409667b5d06 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002275 | 4f9ebfcf-a009-44bc-8a34-42c1d5912b56 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002276 | 55cd4d3d-639e-401d-b891-d4d78a4e410b | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002277 | 5752fd83-4801-48ff-aa04-930480949a78 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002278 | 589f5cc3-a648-4907-b544-a1e0daed1a89 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002279 | 5ceaa0e7-f580-410e-88ed-869a1416245a | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002280 | 5dc31323-ba02-4f8d-9eb2-be6b93c03fdf | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002281 | 803dfc20-1953-4c95-bc30-78e1b20e14c0 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | 2030-11-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002282 | 88032cc4-ceb1-48e5-bc1b-0b7a0a6e7fe2 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002283 | 987c0c97-8afc-438c-bb75-0b48f4ce688d | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002284 | 614b102d-b44e-49d2-a317-58910693240d | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002285 | 66c1a4bc-8103-4606-91a1-ca72bde3f733 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002286 | 7315f5e9-09ea-421f-9f31-3150774d92ab | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002287 | 0c41f2e5-d947-4c20-9b63-8acefa35947c | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002288 | 22f15d3d-b9e6-4229-b397-e942f41dc668 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002289 | 1d1bc1e5-6543-4c4a-b015-6d8cf51eb069 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002290 | 1faff636-5abc-43eb-8568-c96db127a679 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002291 | 16fd1e3f-c065-409a-88f7-fc838c14e884 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002292 | c55bbc2e-11d8-443c-835b-3478e2d6b558 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002293 | f6ee6492-e15d-4579-a2e5-84fdf1ce62c0 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | 2030-11-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002294 | fe02eacc-e995-404b-b041-72cb1c5648c2 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002295 | c43c232b-6b0e-4cd2-a4bc-612a5b330ecc | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002296 | c43c232b-6b0e-4cd2-a4bc-612a5b330ecc | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002297 | c3510fc3-87ac-4b32-bfe3-a6a3c51d7b93 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002298 | c3510fc3-87ac-4b32-bfe3-a6a3c51d7b93 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002299 | c0f5a2f6-aca2-46d7-8f66-2daeb4833347 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002300 | cb0252e8-cef5-48d0-a025-7595b3ac8969 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002301 | bf57f910-f1c3-4986-a6ac-fb385e92ffa0 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002302 | bc42d6c3-8d41-438b-ba22-1d9fc3db60ca | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002303 | bc42d6c3-8d41-438b-ba22-1d9fc3db60ca | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002304 | ba6bc1f6-87ef-4d18-a0f1-39da5d6926f2 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002305 | ba6bc1f6-87ef-4d18-a0f1-39da5d6926f2 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002306 | b74537e4-8d0b-4175-876a-a1458cdd19f1 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002307 | a0fa1883-5d19-424d-aeeb-508486d29465 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002308 | a1fa11a9-6c6f-4660-a5b8-1185365adf4f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002309 | a1fa11a9-6c6f-4660-a5b8-1185365adf4f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002310 | a56d2fde-fc3f-4025-bf1d-5edd5a67ee41 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002311 | a78c74f9-ecc1-4a4d-856b-3c9d23c3716f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002312 | ad966af1-a640-4a22-81da-85dc88b1f847 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002313 | ad966af1-a640-4a22-81da-85dc88b1f847 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002314 | cd241c15-5e36-4edc-bfe4-0c52a0cb5016 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002315 | d24ab2e9-7ac5-47bb-976d-b749be38bc62 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002316 | d24ab2e9-7ac5-47bb-976d-b749be38bc62 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002317 | d24ab2e9-7ac5-47bb-976d-b749be38bc62 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002318 | d3ca4b05-42ab-4e1b-921c-289bf69bbc59 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002319 | d6906809-6fab-4b69-9c06-fba833cafebf | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002320 | d6906809-6fab-4b69-9c06-fba833cafebf | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002321 | d92ef85e-87c5-4b24-ace6-95582f7fdbff | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002322 | daf50f67-c666-4822-9373-2c906ebd185f | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002323 | daa2da85-2fe9-4af1-b5b8-1c26e720414e | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002324 | dca77c8c-f7ea-4b90-809a-ca5f0f8be69a | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002325 | dca77c8c-f7ea-4b90-809a-ca5f0f8be69a | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002326 | f363f094-95a6-45ae-87e6-34211d463c73 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002327 | f363f094-95a6-45ae-87e6-34211d463c73 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002328 | f363f094-95a6-45ae-87e6-34211d463c73 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002329 | f02924db-1f8e-4a96-b995-a8069aa94bfd | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002330 | eace499d-015f-49f4-8fa8-b6d9566764e4 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002331 | ea96ae1b-eadb-4c60-9cd2-7b4f4194322e | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002332 | edab72e4-a768-47a5-986d-3503c4511c39 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002333 | e32a398c-2cbe-4207-881e-5aef298bd571 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002334 | e1f83a1a-2790-4ce8-8c21-8a7ba5dacf8d | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002335 | e1f83a1a-2790-4ce8-8c21-8a7ba5dacf8d | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002336 | e15439bf-6526-451b-89d7-800b4539448f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002337 | e125aadb-fe8a-4e11-9eed-2a31634d4aa5 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002338 | 18aaf051-e1d8-4949-a7cb-cde2cebc8f16 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002339 | 1c5eb6c3-a5c9-4dce-a674-68613bc81a76 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002340 | 1b764b47-ed50-4daa-8c9a-e7af74d3cdc9 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002341 | 1bcb8402-3e41-411c-ba56-d980109f3427 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002342 | 0cfcda93-8cc8-46c8-921d-9199421c8d5e | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002343 | 0aa952f7-1d7a-4232-9a97-0f23096e6d41 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002344 | 0ee9d8ad-e3c4-476d-be9c-d569cb23d0b9 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002345 | 0ddf5258-2747-4fbd-a1b6-f89f3eb70153 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002346 | 113093dc-7ce3-4e80-826b-f671a486a377 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002347 | 016eedbc-80ac-4212-8d22-5918da28d38a | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002348 | 434c9ff1-e8c8-4fa9-a0e1-dabaff517be3 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002349 | 40a21620-f5af-4e37-b27f-c86ab6363f04 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002350 | 40c9b814-571b-4b27-b53c-ec1026fad20e | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002351 | 3a41e0b3-d337-4a95-9a18-35ff5561a269 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002352 | 39e4adf9-0e48-4736-b671-1f87f5c73460 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002353 | 46c8e653-0733-4f9c-b875-34ca734cdb11 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002354 | 44047331-0f15-4a6f-9ef9-c848f03d9e47 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2026-11-25 | Level 2 | [8 empty] | LU | 2026 | 2
1120002355 | 44ab9653-a9dd-4590-8d9c-b5831d25cdad | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002356 | 44ad6c44-15fb-4492-b43f-eb9744749ec4 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002357 | 44ad6c44-15fb-4492-b43f-eb9744749ec4 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002358 | 453547ce-da8c-4b33-ab43-0644ab0b27e8 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002359 | 2c830835-5cc4-486d-b6bb-5cc0bbcc6eeb | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002360 | 2e3c17ec-948e-4bb3-982a-a78f3c0cef15 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002361 | 2e3c17ec-948e-4bb3-982a-a78f3c0cef15 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002362 | 2b9f395b-a25d-4c0a-9f80-bb92d6fc19fd | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002363 | 28d8b1fe-2fe4-4a4f-ae75-8738c7d226cf | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002364 | 29d857b1-a119-40fd-8566-88f6e5ca94ba | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002365 | 3821e21d-ae93-4eed-8b1b-934c8437fa3f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002366 | 33a33d68-39fb-4be8-9128-add232576414 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002367 | 2fcabb06-b353-41bd-aa2e-92ab60c61c7f | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002368 | 2fe41936-def1-4ed6-8df5-1c06107c06da | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002369 | 3053d6ac-f3ca-4047-820a-6175e0a75b72 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002370 | 70c003df-3508-420f-b872-a8bddecc9a34 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002371 | 6eda2b2b-2921-4d8f-b4de-80760ecbf4ee | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002372 | 6e9f0bea-6646-4efc-8110-94c99f658d5c | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002373 | 697604be-3eb8-43a1-a52f-35a10fbefa4c | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002374 | 69b6b3e8-1ae0-4d7d-8ea8-1a844b7657f8 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002375 | 69b6b3e8-1ae0-4d7d-8ea8-1a844b7657f8 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002376 | 69b6b3e8-1ae0-4d7d-8ea8-1a844b7657f8 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002377 | 6835a7d7-9ea7-4df5-8420-54657db4d066 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002378 | 60e64520-d928-4999-a0fd-c370a404891e | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002379 | 63a03eca-e3c1-468f-a9dc-6fcd8b09eed5 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002380 | 573184e8-0471-452c-adc8-412eefc12301 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002381 | 5b264135-4709-4096-a2a6-b3ef86de452d | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002382 | 5b264135-4709-4096-a2a6-b3ef86de452d | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002383 | 5b264135-4709-4096-a2a6-b3ef86de452d | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002384 | 4deb6614-359a-4439-9150-59067bff4ff3 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002385 | 4deb6614-359a-4439-9150-59067bff4ff3 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002386 | 9745d591-ad72-45d6-a14b-08bd1576484b | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002387 | 95fc270a-96c3-4eff-8937-1916a6f79ab6 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002388 | 95fc270a-96c3-4eff-8937-1916a6f79ab6 | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002389 | 9563325a-e6ff-4e4e-8f04-f08bd2976683 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002390 | 9c3c2b89-a007-4da0-a4ff-6cfea7546f1f | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002391 | 9d26fc0e-54e2-4149-a9b0-8d04f7ef82cf | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002392 | 8be71f22-aa3a-4493-8eaa-0d983a090695 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002393 | 823b7ff6-65a6-4140-aa29-5e9fd1354c69 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002394 | 83164845-2e9d-4352-a4d7-a64c89b59d50 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002395 | 7c51b9b7-0221-42ad-9892-66ae088d5933 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002396 | 7c51b9b7-0221-42ad-9892-66ae088d5933 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002397 | 75de8e17-02f9-4a54-bf24-2fe50c1c828c | Pole | Non-HFTD | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002398 | 77294454-801d-41cf-8020-1aaf07cb0d64 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002399 | 79ea10bf-12b9-41d6-962e-4dd22aee42fd | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | 2030-11-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002400 | 8b115f82-8810-4829-a7af-f102ccba6178 | Pole | HFTD Tier 2 | Distribution | 2025-11-26 | 2030-11-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120002401 | 56a5ca69-9bba-442a-83e9-befabf1f6068 | Pole | HFTD Tier 2 | Distribution | 2025-11-26 | 2030-11-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120002402 | d44cec9f-138f-4573-8557-8c30f1d5f8af | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-26 | 2030-11-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120002403 | d44cec9f-138f-4573-8557-8c30f1d5f8af | UG Transformer | HFTD Tier 2 | Distribution | 2025-11-26 | 2026-11-26 | Level 2 | [8 empty] | LU | 2026 | 2
1120002404 | d79b47df-803f-4022-8c42-6d4c36bffade | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002405 | e88b54a7-2fb2-4b1e-9ec6-5a3e298bdbd9 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002406 | b2384e9c-8b61-49e5-9eed-bd71284b60ca | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002407 | b2384e9c-8b61-49e5-9eed-bd71284b60ca | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002408 | a7a969ad-810f-4c82-8e38-b17fcb77e52e | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002409 | c0d247e8-897b-47c5-8804-aeb07c19096d | Pole | Non-HFTD | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002410 | fda79173-642c-4af8-8db1-3e455ac1c908 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002411 | 5b56064e-0263-40c4-a8db-34fa3eea4c67 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002412 | 5b56064e-0263-40c4-a8db-34fa3eea4c67 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2026-12-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120002413 | 7404e446-2716-4675-b181-6a0b3171db2b | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002414 | 7e370971-ba74-4cb7-8d11-79381542db7e | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002415 | 7e370971-ba74-4cb7-8d11-79381542db7e | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002416 | 44ae8b43-868e-48c0-a815-daef0f142959 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002417 | 44ae8b43-868e-48c0-a815-daef0f142959 | Pole | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002418 | 08ba866b-2378-4f1d-b4bd-ffac04d7100e | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002419 | 08ba866b-2378-4f1d-b4bd-ffac04d7100e | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-01 | 2030-11-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120002420 | 1db33b00-ac3f-40d4-bbfe-593d9ede8b2c | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002421 | 84236670-9083-478c-a4e1-2553b93f522e | Pole | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002422 | fb7e28ef-6239-42f5-8018-8ac2da6639f5 | Pole | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002423 | fb7e28ef-6239-42f5-8018-8ac2da6639f5 | Pole | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002424 | c6a25b67-f408-4338-b60e-a28db7251ff5 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002425 | e827cb2b-0d84-4a67-a851-61ea4d7d905e | Pole | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002426 | e734676f-1aeb-457a-8900-8d7c8b0f3051 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002427 | e197eed9-0284-4c88-bdc3-46612201a908 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002428 | ea61ab68-3146-4292-8334-3747051b31a8 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-02 | 2030-12-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002429 | cbd5b75f-f073-4ccf-99a0-e774876cbef2 | Pole | HFTD Tier 2 | Distribution | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | LU | 2026 | 2
1120002430 | cdac5e4a-a088-4db4-8c15-b35167900886 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002431 | eb98b07f-7609-441d-957d-c20c9202c1fd | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002432 | e61acf18-6875-4c22-acfd-124fc14b8d07 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002433 | c82396a3-327b-4e7e-b509-9557b287e7b5 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002434 | ca44e609-820a-406f-9968-181f6eb1c4c7 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002435 | a418fcfb-2ab5-498e-aea8-01995a1be33f | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002436 | fda009fc-c85c-4f3b-ac68-306ffc9a1a49 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002437 | 941290aa-ebba-49a1-b07e-db2629890c6c | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002438 | 996241bd-9c3e-40ca-a33a-7cc61b7d4b26 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002439 | 96dd8a45-7ad9-4f05-9749-22ad210c12be | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002440 | 5b68afff-2f81-4e68-8ec9-92259de1e4df | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002441 | 55826d29-9fd5-4597-972a-a90407fb7d92 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002442 | 54effd0a-ed76-475c-aadc-89aae77e80b9 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002443 | 4f51a017-55ad-4b86-8b9d-024a205a504a | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002444 | 517a738a-a7f9-4e9b-971f-c5bf1cc3739f | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002445 | 517a738a-a7f9-4e9b-971f-c5bf1cc3739f | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002446 | 66c84cd0-fbc8-4594-ba00-76135ad48edc | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002447 | 6dd03596-cb88-434f-b0cb-a64670e3c519 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002448 | 6ee0b615-eab8-4f16-af4f-f77af61cf648 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002449 | 6ee0b615-eab8-4f16-af4f-f77af61cf648 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002450 | 6f6d024b-ea3c-4f81-a8b4-3aae27003e21 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002451 | 16ef188e-c565-4a1a-a98a-22644916bab3 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002452 | 079e8678-c755-458d-8a07-79d5effc079d | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002453 | 079e8678-c755-458d-8a07-79d5effc079d | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002454 | 0ea7171f-d2e4-4065-a7ed-66fcbf909a81 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002455 | 48727420-239c-44d7-bde4-11c5a351d9a6 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002456 | 4cb212d6-b247-4a0a-9108-a28dcb33ee8d | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002457 | 4cb212d6-b247-4a0a-9108-a28dcb33ee8d | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002458 | 3d958159-5af8-4095-96bc-d9f7ebacfc16 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002459 | 3f2ab252-b62d-41ed-99eb-0fafb7439d23 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002460 | 3f2ab252-b62d-41ed-99eb-0fafb7439d23 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002461 | 30f1dbf8-30b5-48af-aac8-777a1395f79c | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002462 | 33b0e8a1-f4ec-471c-92b6-8f6caf672a8e | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2026-12-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120002463 | 37eb6ca3-0228-456d-926f-a2ce1f229940 | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002464 | 33b0e8a1-f4ec-471c-92b6-8f6caf672a8e | Pole | HFTD Tier 2 | Distribution | 2025-12-04 | 2030-12-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002465 | 373dc011-d4e6-42a2-a1b5-d99157061a4a | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002466 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002467 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002468 | 3320a807-09cc-40b3-a839-d66f66b88795 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002469 | 2e862c2e-c69a-4a79-a4de-f76186a571ce | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002470 | 2e862c2e-c69a-4a79-a4de-f76186a571ce | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002471 | 39b82469-4fae-42b4-8827-51775e5b7c09 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002472 | 0687293c-973b-4567-8b2c-92219fd0c030 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002473 | 024fae4e-fe3c-4a41-bd26-d023bc670dd3 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002474 | 14e984a9-2095-4f50-92f0-c5c78f2ebfdb | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002475 | 711e2a2e-9b18-4850-b9a8-c5fc5e2eea6d | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002476 | 6dbf3c46-f4bf-4310-ba86-3f9043b73677 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002477 | 60354f10-4318-4f83-82b9-9d75a8f6dd1b | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002478 | 60354f10-4318-4f83-82b9-9d75a8f6dd1b | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002479 | 50d85ace-cbb3-42ef-a569-9a457f21cbe5 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002480 | 55ced008-d80a-4318-98b7-f43ac33567e6 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2026-12-05 | Level 2 | [8 empty] | LU | 2026 | 2
1120002481 | 55ced008-d80a-4318-98b7-f43ac33567e6 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002482 | 5429f1b2-80a7-4fe0-9239-8a7acb782897 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002483 | 573f23ae-133d-42f4-a43a-ff25f1fe8594 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002484 | 5bcbc3ee-8261-4c7a-822b-d6b66e22e41a | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002485 | 98fca2d1-ab14-4d62-a993-2fda97352385 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002486 | 9d834098-4630-4325-bc9c-83899c1749d2 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002487 | 85e3f735-456d-45c9-892e-66daef02a6cf | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002488 | 7bca3548-e781-4d83-8776-64f15d7df20e | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002489 | 79f86b4b-e91a-44aa-bc94-76638f9c6c5b | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002490 | 79f86b4b-e91a-44aa-bc94-76638f9c6c5b | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002491 | a4404ce4-e1fd-43bd-bc5e-2977ba90bd99 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002492 | a8bab12d-bc82-4f40-8e64-27139b52dc68 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002493 | a8bab12d-bc82-4f40-8e64-27139b52dc68 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002494 | b016b536-793a-4f89-9ce9-5ea4561b06d6 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002495 | c502cb9d-cf9c-4e19-a3c3-35825ef44e52 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002496 | bda52817-1dfa-44f7-a89d-5b70d11d1e02 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002497 | bdab00b5-9eef-4664-a2d1-05fd9bb0548f | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002498 | bdab00b5-9eef-4664-a2d1-05fd9bb0548f | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002499 | bedf1b76-2aac-4336-8080-103a7af16a59 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002500 | bedf1b76-2aac-4336-8080-103a7af16a59 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002501 | bedf1b76-2aac-4336-8080-103a7af16a59 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | 2030-12-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002502 | ba743f79-431f-47f3-b21e-32ce4cda7935 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002503 | c0f03cab-6c43-4831-94b0-23a679fa419c | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002504 | c37f4624-d39b-4af0-b68b-f97a1e455b13 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002505 | b1dd66f8-85e4-4376-825a-483e7fcddbb0 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002506 | e6a28845-096e-4df9-91d6-f3cc44fca78b | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002507 | eb0b23c5-4ba7-4ccc-b476-ec32e3968172 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002508 | da3fe191-1c5b-48a8-8460-4638052643fd | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002509 | 89eb9121-649f-4eee-9738-3eb3078bfd06 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002510 | 9bf68ea7-16d8-4c11-a020-03bfe5d79cb8 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002511 | 925dff6d-bd20-4605-bc7d-ca210c4225b8 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2026-12-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002512 | 925dff6d-bd20-4605-bc7d-ca210c4225b8 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2026-12-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002513 | 5a92ad67-e132-4869-aa41-5f46ae479d23 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002514 | 5a92ad67-e132-4869-aa41-5f46ae479d23 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002515 | 55c7839d-af2a-4da7-aeda-4d9465b1dc49 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002516 | 4cd9d274-983c-49a8-b18f-9129caf0d9ee | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002517 | 4cd9d274-983c-49a8-b18f-9129caf0d9ee | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002518 | 6df43266-d477-4863-9c51-a7d598d35c0e | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002519 | 6edbdf73-d867-4288-bc85-b834b93b1f59 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002520 | 16603c7f-6953-4581-a427-3c07bbb202df | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002521 | 1fb85b39-68b0-4d15-8d9b-e327d6e48172 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002522 | 1d14b840-1954-4b6b-9831-3c4f9c17cbeb | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002523 | 2042cf53-7aa5-49ce-88bd-e8e674a98c27 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002524 | 21439f1f-ea7f-4c14-b785-d5642a1c93a0 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002525 | 01728095-17ff-49c2-8bf9-dfd930bb9820 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002526 | 043a6bbf-23c3-47f4-9afb-4d32ae8d8ea9 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002527 | 093c8ab0-38d1-44b1-9bef-e073a45b4de7 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002528 | 0e5a887a-ff45-49ef-9a80-4aef6ef7ac46 | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002529 | 49359f9d-a9a5-4431-b700-3e2b33256c0d | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002530 | 49359f9d-a9a5-4431-b700-3e2b33256c0d | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002531 | 2bc8ffaa-41a1-495e-93e0-191fccc5771a | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002532 | 290b9611-2e57-41d5-9959-67cd6672459a | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2030-12-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002533 | 2f4650dd-4504-4c81-ad9f-56c361e8cbcf | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2026-12-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002534 | 2f4650dd-4504-4c81-ad9f-56c361e8cbcf | Pole | HFTD Tier 2 | Distribution | 2025-12-06 | 2026-12-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120002535 | 36175e83-ca61-4166-a31b-88407c312963 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002536 | 27a4da30-e196-4bd1-99de-0975c1588f3b | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002537 | 2bb85d5b-9a8f-46ce-8644-4676ba42e2ac | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002538 | 2c73a096-d5a4-4710-9c45-a77dedea62a8 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002539 | 2d2df3e6-b81e-4851-bb13-0ca2f88ce891 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002540 | 47893e44-4e78-4cd8-b609-b6f2e560be7a | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002541 | 47721a27-d941-4fa5-8d83-73c61b982728 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002542 | 38af38d7-d552-4832-9cb5-5802d2fe8fce | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002543 | 3d277964-1541-4bbb-a05d-2efa10f068b8 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002544 | 3df28765-0848-45d2-8a79-3932cbda964e | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002545 | 0f36ffdb-c1a7-4350-8580-3bac58e526a7 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002546 | 0fe175fc-290b-4294-ad57-3a53fd651280 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002547 | 0dd4eac5-3032-4655-a174-7d421dfed713 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002548 | 0233b73e-233b-4912-ae6c-6b6f7d3df95d | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002549 | 02faf5e9-5003-4147-b9cd-c5246721cf34 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002550 | 1a104b51-6bf3-4063-88aa-0719a69e0d1b | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002551 | 1a74ff66-7d6f-4dc0-8285-027a69a94fc9 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002552 | 6b1d4bb5-3c6e-436d-9465-fc335e327f23 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002553 | 6274edd0-5658-4b30-988c-e9c833d8c20e | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002554 | 6274edd0-5658-4b30-988c-e9c833d8c20e | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002555 | 4df9e95e-ebe4-4dc6-8396-0d824e65d3f2 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002556 | 4e4865b8-2a97-41cc-8ee0-9dfb6d09512c | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002557 | 55aa17bf-ebe3-4091-9a11-87c309d8e4e6 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002558 | 5c317253-e13b-4f1e-b740-f122fc99e154 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002559 | 5dd99682-6e70-4e85-8928-091717412ea5 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002560 | 908f6f9b-d192-412c-a125-7310275fc101 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002561 | 8c9455e2-5041-47cf-9ced-f709bd4d9bd4 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002562 | 880f5402-22ab-4744-bce9-a8a2341c3d02 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002563 | 82d590cc-af0f-4853-a877-ee193839e427 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002564 | 7412bd73-2a6c-4aad-b08c-bd37fc6e65fd | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002565 | 733f2170-ceea-4017-bfd2-dd112ddc5633 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002566 | 7b632f48-8452-4f27-8360-a2ab7fe65d2f | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002567 | 7cf48960-7892-4a4a-9d7d-70347fd12549 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002568 | 7ebf0b90-c18c-4669-bee1-b2e44772a7d2 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002569 | 7ebf0b90-c18c-4669-bee1-b2e44772a7d2 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002570 | 7f7593e6-e7d2-4508-bd73-0ac6ff98f88d | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002571 | da93881c-cb32-48c2-a4fa-98c1ec05c420 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002572 | d8a9de85-038a-4b7c-994c-0fbccfdea7d4 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002573 | d554f585-0e0d-4fe1-9f22-2ef0160f914e | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002574 | dc385c0a-28d7-45e7-b7ab-f5bcc29d5517 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002575 | d47a65b2-def5-4a16-ac84-44e4ead0e675 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002576 | ebf683f3-9e2c-4a5d-bc81-ba84704b0b15 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002577 | efd07ae8-957e-4f2c-8966-5177b9d0e2ed | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002578 | f3893a44-2dad-4f03-872a-9beba509d6b1 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002579 | e73658fa-f969-4ee1-a586-2d1c9b2505f2 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002580 | a790d10f-4fcd-4cd4-8139-28360469c504 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002581 | a74e14c1-0419-4bc3-a3c7-4b7e9ccf8881 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002582 | a74e14c1-0419-4bc3-a3c7-4b7e9ccf8881 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002583 | a2037844-e960-48c8-acb5-19f6f591d660 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002584 | 9f476284-9f05-48ad-8e1b-f5c22eacb640 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002585 | c3cfdb03-e19d-4270-8bbe-f18a06387160 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002586 | bbe10543-0ad9-4601-8219-d1843182826d | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002587 | fc9e9617-5170-47c9-877f-f8919f2648ed | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002588 | f943ac7b-af96-4ff3-8f67-2ab4c2366084 | Pole | HFTD Tier 2 | Distribution | 2025-12-08 | 2030-12-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120002589 | c08afc8a-cdbf-49bf-ad6b-8ec60cfb9af0 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002590 | a79872b5-bb90-4c46-8737-910bf320c79c | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002591 | a79872b5-bb90-4c46-8737-910bf320c79c | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002592 | e853211f-8ed9-4558-be07-757ff76c4d85 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002593 | d3ad132a-a0f2-482c-9686-aad1f6223868 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002594 | de467e1d-1754-4164-bab2-2fda3cd5934a | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002595 | 804a6f38-82e0-40e0-9212-b2e91aecaa00 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002596 | 8f775ea9-9bd5-40ce-aeb7-a6bfafb2e659 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002597 | 9bdd663f-c501-45c4-a855-a85a7b8ce525 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002598 | 5e925790-e5dd-4fba-8813-c8870fc63585 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002599 | 5e925790-e5dd-4fba-8813-c8870fc63585 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002600 | 02f9f54a-a7e0-4924-8f86-cbe71f1db836 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002601 | 3898025c-a6e6-45e3-8aab-15e247f82957 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002602 | 48877317-2ed9-40ec-ae90-62a93174a2c6 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | 2030-12-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002603 | 456eb02a-ddff-48ac-9189-89d419e36684 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002604 | 33cfa138-6b5f-4555-ba59-619b90d9a785 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2026-12-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120002605 | 003a7827-8e3b-4668-aa4e-0848d0c031ad | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002606 | 4d994cc5-ea2a-4e8f-9cae-bdd3c706a969 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002607 | 5096d704-e307-49e6-b80b-d387ee037907 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002608 | 70593cdc-60d4-4ff9-9bde-6b795164c816 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002609 | 7f7b83eb-a2a6-4be0-a12e-735b4f1157aa | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002610 | ddff36aa-f2b1-4c5a-8879-e8482857118d | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002611 | d7a74c28-b3a0-4c73-a1f3-995564602329 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2026-12-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120002612 | e19b92cf-dcd8-4c66-8f6b-3235a4a7832c | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002613 | ecb3c519-643b-4613-901b-9851b9f755ad | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2026-12-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120002614 | 9f9bb1d3-7f00-4ff0-a2b9-8e534e538197 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002615 | bf3b1bab-c7ea-4e1d-9df0-d28d3b0d3b6d | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002616 | c8ec1540-9d9f-471d-9e67-47cc9bafb276 | Pole | HFTD Tier 2 | Distribution | 2025-12-10 | 2030-12-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002617 | c87ec552-3ecb-4bab-9183-ef8efd94484a | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002618 | c3cdfe91-6484-440a-a063-11fc3f7072cb | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002619 | bf88eb0f-4f68-4608-b00f-db12396e4b44 | Switch | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002620 | b5a15a35-3e24-4067-9a79-2a18d89709e7 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002621 | 9f884b4c-b2d2-400d-830c-32d41596b5cb | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002622 | a08b67bd-335a-4722-a505-280de4006def | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002623 | b52c05e2-7b33-47c5-9295-2fa1b976688e | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002624 | aae93739-f3de-4e7a-9617-a92df44218d9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002625 | ed2ac25d-f801-46ac-b320-b6b6a2c23d51 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002626 | e23a7e9a-caa5-4b2d-93cd-fcafe32029cb | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002627 | d4c8501a-9dd3-405a-9753-e98b1b53fd91 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002628 | ce0e4626-77d5-45da-af15-45ac902b013f | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2026-12-11 | Level 2 | [8 empty] | LU | 2026 | 2
1120002629 | f79a80f7-bd8f-4ba7-8d35-8f2f8469003d | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002630 | fc7773b0-7b8d-4359-b85f-f0abfc0ca860 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002631 | fc7773b0-7b8d-4359-b85f-f0abfc0ca860 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002632 | ffb12e2b-0019-4be2-a1ac-5ca02b6c6e0f | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002633 | 7a826ef1-603a-4599-ab3e-b82f026dfa5c | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002634 | 7873bed6-ac36-4a81-9bf7-7f93179d9a88 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002635 | 99e5f575-0fba-45e9-97b2-1a2ccde1d1e3 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002636 | 8eae4e86-1172-4dd2-9490-bb128433bf33 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002637 | 91a4bb8b-f69e-44b6-accd-b184d53fc6e7 | Switch | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002638 | 6e2257e5-9c8c-4964-8c6c-312955d3a013 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002639 | 5eee29b9-842d-45fc-9fa2-48f67ac0f6b1 | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002640 | 55e5a204-d35d-40c0-991f-2dd07b74dfb4 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002641 | 5d8a16aa-d712-480a-968e-554edf51ac55 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002642 | 57ee7587-0fc1-42ce-916a-1a4055e7347a | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002643 | 015b8d58-93ec-4896-9c63-8917cf07aba6 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002644 | 19119ac7-0ded-4d9d-a430-d6d3839ec3d8 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002645 | 13156bc7-fc04-4835-93a7-257980f5314f | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002646 | 35800bcd-0a5f-4484-8068-197f4fccf99b | Pole | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002647 | 3cc53d2c-1f66-4d6e-b2d7-d034bc9652a1 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-11 | 2030-12-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002648 | 42e7f232-7d96-46b3-a3bd-7d3c8567c77b | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002649 | 49fe14e2-b714-4168-a265-44718c9efc02 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002650 | 3535cb7e-6ac0-41c4-9883-7f90db1d264b | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002651 | 34b85b11-7c04-4df5-84a6-b554831ac45d | Pole | HFTD Tier 3 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002652 | 2acb5a9b-d846-47b8-a4cd-6b006ee41e1f | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002653 | 1a8129d2-b221-433f-9bf3-3487ec4ff7fd | UG Transformer | Non-HFTD | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002654 | 119a6bdb-7564-48e4-87bd-c5733476ec71 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002655 | 5954717a-9071-4267-990c-f2a3e90afa54 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002656 | 5b30bbd0-e2b5-4e46-9056-9c2d370f6493 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002657 | 5636b6cc-92e4-4df6-9ed2-fc152e4747ce | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002658 | 9477968a-4632-4ba1-a7cd-3dec88cad1cd | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002659 | 76961911-548a-4596-8382-47fc1f6f6565 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002660 | 812c7e95-327f-429b-8163-ba7ff53b8dde | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002661 | 8938f448-3cf7-4bb0-b626-495731fd59ee | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002662 | fa48f9c3-9875-4a87-9381-bdbfe8834139 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002663 | e2e9ea62-ad90-4c09-9ede-b8c675173ccf | Pole | HFTD Tier 3 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002664 | e41fcb71-2d50-4517-976c-85a50905cd5c | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002665 | e12e36b2-6439-4a30-a7e5-3348e9740c0a | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002666 | f24e5303-929d-472b-9808-475397dd90ca | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002667 | aee0a5a4-3e02-485d-998f-bb52062c196c | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002668 | b4d7d386-a8a3-40ce-9d31-db4423ad5618 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002669 | b347c657-aeb2-4d49-9693-0b121d253adb | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002670 | b1a39047-9142-47fd-af62-d4a4be1afb5b | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2026-12-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002671 | b22564e9-81e5-4098-bfcf-6c191c98f8ef | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002672 | a0da7b88-9fe5-4485-b467-5ecb9291c1d9 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002673 | a56ead64-c3e1-42de-9e54-7ed27772c927 | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002674 | c2154f56-b8c8-4686-aa88-db10ffc3f74d | Pole | HFTD Tier 2 | Distribution | 2025-12-12 | 2030-12-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002675 | a4414fab-8fae-4852-be50-b429604041a3 | UG Transformer | Non-HFTD | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002676 | a15d3198-3468-4c12-8bb8-6162b2dbea4f | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002677 | a15d3198-3468-4c12-8bb8-6162b2dbea4f | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002678 | d2eedbf6-9dc3-4d30-90ad-b33c88ebf36e | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002679 | 8381d689-8610-4423-b283-64e74ddddba0 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002680 | 7ff0344a-da49-45b9-ab7d-765990068eb0 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002681 | 6473a912-9695-44fc-a1fe-7e701226970a | Pole | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002682 | 1ab632ea-619d-4cf9-ad5f-eb3f0189bc49 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002683 | 1b2eb8ab-b064-4241-8a1d-8b52d96c8bca | Pole | HFTD Tier 2 | Distribution | 2025-12-15 | 2030-12-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120002684 | 4a2102fc-e628-45dd-9f1f-6b2a130ab851 | UG Transformer | Non-HFTD | Distribution | 2025-12-15 | 2026-12-15 | Level 2 | [8 empty] | LU | 2026 | 2
1120002685 | 41176ee3-4a71-499b-acd8-d0c47d793afc | Pole | HFTD Tier 2 | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002686 | 2cf9add8-123f-4aec-94ce-a7efb5c32572 | UG Transformer | Non-HFTD | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002687 | 34f5c221-5726-4037-8adb-7e4cdccd1b0b | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002688 | 984cfb8e-102a-4ac2-a099-34ed8a97a8ec | UG Transformer | Non-HFTD | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002689 | 984cfb8e-102a-4ac2-a099-34ed8a97a8ec | UG Transformer | Non-HFTD | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002690 | 8a8724e7-4eab-432c-8912-482514767cf8 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002691 | dffee072-f3f0-442b-a51c-82166b77438a | UG Transformer | Non-HFTD | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002692 | a94223b1-5122-4564-9719-b269fedd8491 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-17 | 2030-12-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120002693 | d3b57d53-7f24-4211-8a30-141327d13e82 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-19 | 2030-12-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002694 | 79e7af93-053c-4c04-8557-8433dce5fd35 | Pole | HFTD Tier 2 | Distribution | 2025-12-19 | 2030-12-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002695 | 785578ac-b684-45df-b954-7bdf77d4f148 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002696 | 737872db-371c-46e1-a246-c6261b245689 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002697 | 84e202a0-f1b7-406c-adf1-c189cfad440b | Pole | Non-HFTD | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002698 | 84e202a0-f1b7-406c-adf1-c189cfad440b | Pole | Non-HFTD | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002699 | 84e202a0-f1b7-406c-adf1-c189cfad440b | Pole | Non-HFTD | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002700 | 9a2c217d-c78f-478e-a62f-233cd504c587 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002701 | 69864ae5-8b7d-4aae-94d1-1cb1afc9bad5 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002702 | 547cb55c-3aed-4297-99dc-50d288857866 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002703 | 5ba4f19c-7941-410b-95fb-d284fd382ee0 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002704 | 2f53066b-8f4a-4c39-bb9f-1bda86238b9f | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002705 | 40acbdf8-3fc8-40b5-b600-dc026a8706ab | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002706 | 409dbeaf-7580-4019-ac6d-662bd756298d | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002707 | 4816093f-c198-4d16-b603-1e691c5e2bd0 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002708 | 1ce3f919-7726-4827-b84a-32044ab31d3b | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002709 | 22015ee0-4bf0-4599-9b4a-d38cd8ba74b0 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002710 | 07609c0f-4b1d-4736-9ba6-20582dda431c | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002711 | d61829ea-c748-4a27-afd2-d2d4b24686d3 | Pole | Non-HFTD | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002712 | d61829ea-c748-4a27-afd2-d2d4b24686d3 | Pole | Non-HFTD | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002713 | d7ce3ac7-0e80-4938-a99a-5c80e96af080 | Padmount Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002714 | f1b1b1eb-dd56-403f-ab17-5d8b03c96f12 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002715 | ae32dad6-267f-4c42-8695-c39867400785 | UG Transformer | HFTD Tier 2 | Distribution | 2025-12-23 | 2030-12-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002716 | a487f6e8-59aa-431b-8ca7-328c5944b062 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002717 | fc3f6382-34ea-4ffa-8153-082f1c8360e6 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002718 | 25b1c45c-8329-41d1-8c93-68beae296696 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-01-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002719 | 9cf73608-750c-4976-ae01-a614a1841fac | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002720 | ac5b9627-6512-479d-b26f-ea99d432d77a | Pole | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-01-13 | Level 2 | [8 empty] | LU | 2026 | 2
1120002721 | d742ce4f-e93e-4f77-b42d-1e4e3e5d1171 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-01-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002722 | 36b5701c-c537-47ed-a55f-a5fb0db134ac | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-01-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002723 | 46032a24-bf5b-475a-b23f-c6e148b58891 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002724 | 9a5b7789-ebca-4d4d-837d-a43a90266684 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002725 | 8d38fdf7-8be6-4a06-a18a-9380155497d6 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002726 | 61b78a54-cce0-4cf5-af2a-563d870cb452 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002727 | d37d92bd-12d1-4171-9464-eb61bf53abdf | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002728 | e558ed9f-3444-45b5-b524-4d135f84d029 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002729 | b897c066-5000-46f3-8fa8-d46b4c1ce580 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002730 | b897c066-5000-46f3-8fa8-d46b4c1ce580 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002731 | bead03a8-fa0e-4228-9f8b-caef0faceedd | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002732 | ffb0a4c0-e755-4784-9fea-619310fe5447 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002733 | ffb0a4c0-e755-4784-9fea-619310fe5447 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-01-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120002734 | c9ccd6e0-3a01-43d4-bae8-532933317710 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002735 | a5853363-e0fd-4bdd-980c-fd6780f4d2d6 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002736 | cc80b732-e4f7-4933-8d03-33bb414abcd0 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002737 | 5ae2b141-0fdb-4019-8141-719b488a580e | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002738 | 557862a9-4373-4046-baec-b704ac7aab56 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002739 | 83796199-d236-482a-aaf6-ad109fc1eb95 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002740 | 4272f21a-a9a5-455a-a32e-f0ea4355dc81 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002741 | 2b06ae1d-4b8b-4149-b8c2-11bdf13c0834 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002742 | 07508cc9-bd04-4b5e-87bc-04bcc8442599 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-01-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120002743 | 8a77fb65-7816-4a9f-9d7c-43a96471c472 | Pole | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002744 | 5b7f62f3-00e9-4b57-a01f-4561b9135ace | Pole | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120002745 | e2444b6c-5b6e-45df-8e3e-a870508ea7bb | Pole | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-01-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120002746 | e2e5f3ed-0a51-4ab6-b683-f1b1d812588c | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002747 | e49a9249-f167-4428-ac39-c72e8ddb46f9 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002748 | e559833d-c8fe-43b7-a0ec-7f6ef2084314 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002749 | eab5c2c4-cb6a-44d9-a890-afcd5d2d0f86 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002750 | d25adbec-61e2-412c-b9ac-40c5dfd89db3 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002751 | d1621268-e8aa-4968-ad21-3a88a63b3e59 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002752 | df6c3a39-5549-4acf-805e-88e43edcc504 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002753 | a40d03ac-c4ae-4398-884b-d4ff06b4d029 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002754 | a40d03ac-c4ae-4398-884b-d4ff06b4d029 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002755 | a40d03ac-c4ae-4398-884b-d4ff06b4d029 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002756 | a40d03ac-c4ae-4398-884b-d4ff06b4d029 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002757 | b1a66e54-57be-48ae-844b-5d65717f6f33 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002758 | c0d0e8be-3c6e-4e46-b9c5-40e46d22ff2c | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002759 | be3c788b-c18f-46ec-9331-3a4f98cb10b5 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002760 | be3c788b-c18f-46ec-9331-3a4f98cb10b5 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002761 | fcdfbe99-1163-4383-9e04-d55b8c70b44b | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002762 | f8382f76-be46-4692-bfc6-21e3da49c47e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002763 | f619b8ae-6c01-4cc6-8a99-222bfd1fb8c2 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002764 | f619b8ae-6c01-4cc6-8a99-222bfd1fb8c2 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002765 | 5999acba-8b27-476e-a528-7e2061346121 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002766 | 56ba2d55-ee71-496e-85f6-b3987bf90951 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002767 | 642a38c8-f68b-4656-bff2-03c922d37419 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002768 | 6943c8d6-ab1b-4289-b8af-98a37a4ea180 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002769 | 72080ef2-9a33-4c85-b416-f091456d257e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002770 | 9a0a267b-8e5e-41b6-9474-272b64777bb7 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002771 | 9a0a267b-8e5e-41b6-9474-272b64777bb7 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002772 | 86bd71fc-7f6f-46ef-836f-b595ffdc1d4b | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002773 | 78fadfc2-3402-48e4-afe5-f635b6afcff6 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002774 | 02a44639-bda3-4f1d-8dfe-640f8a509d1e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002775 | 118ce14f-06e2-4419-91cc-3e0614aedc75 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002776 | 118ce14f-06e2-4419-91cc-3e0614aedc75 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002777 | 258309da-014c-4a37-8cda-0a369b7dae5d | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002778 | 1b795b68-a052-4abd-96a6-897fb1098e46 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002779 | 1eaae884-2b79-4a97-ba88-86d889445ba5 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002780 | 139d8b53-01d3-44f8-962b-e38928bc62ab | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002781 | 13490dc8-677a-461c-8f94-4ef1ba680a15 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002782 | 2d0d9bac-9db2-4107-8b41-6ce7a2476c80 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002783 | 33c2695f-197a-42c8-8cbc-5dcd9af8c62e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002784 | 33c2695f-197a-42c8-8cbc-5dcd9af8c62e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002785 | 33c2695f-197a-42c8-8cbc-5dcd9af8c62e | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2027-01-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120002786 | 3cef5965-d641-4197-b391-53665234c4ad | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002787 | 44df3996-aa43-4449-8be6-66b9a586bef3 | Pole | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120002788 | edcb10a6-2e9d-42f9-96e3-195e70aa70b7 | Pole | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120002789 | b8e77f87-73b9-417a-95da-b2eeff24df62 | Pole | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120002790 | abdb7528-8eb0-476b-b9cf-ff6f288a1bcd | Pole | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120002791 | 8ff27dbd-51f4-47aa-ab50-ea45fca322f0 | Pole | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120002792 | 6a9d5f29-c321-4adc-9316-fb678bdba9ae | Pole | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120002793 | 8df11829-400f-4111-ba8d-381495ef4096 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002794 | 424d54ef-b11e-43a5-bf19-a024c06c2ec7 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002795 | 3fd1aba8-d31b-477c-9303-8005428dadd0 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002796 | 13b3c4ba-52ed-4f44-bea3-fd93d42a8606 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002797 | 016e4804-50da-48a4-af10-1f14c75556b0 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002798 | a329a222-de99-4942-9f8f-dfb3712231e3 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2027-01-30 | Level 2 | [8 empty] | LU | 2026 | 2
1120002799 | cba22572-e14a-4660-ad9a-06d94a73be67 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-01-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120002800 | f1cb35a4-2e93-48ba-8fb4-9936a898fe25 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002801 | d6f83f73-582f-4424-be65-87e04bfbf396 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002802 | 0426ffa4-6237-4faf-b8b4-34a825e3d519 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002803 | 22376187-93fe-4af8-9527-993bf473517a | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002804 | 7252c10f-9d96-466d-8260-405f5dab8172 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002805 | 61da88d8-85b1-42b0-bae9-071908cbfbf0 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002806 | 5766bbba-0e91-40a5-abf6-3e588e3fcacc | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-02-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120002807 | 99b9354f-017e-4747-8a17-b89adf38b6c6 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002808 | 1fa86422-54e9-461d-95b0-d31e2f625963 | Pole | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002809 | 1a74e123-b6e4-43e5-bf58-cd1b8be2b932 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002810 | 101ed74b-5df8-4aac-ba99-5aa6d1b8ff65 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002811 | cce2b4c0-c10d-43be-887a-55a195cfa6b7 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002812 | c7f946b9-3edb-4e52-a82c-d3f24095d0e9 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002813 | c233fd13-de79-4150-a470-aa213b94c6e0 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002814 | ac709390-04f3-44ee-b26a-d86248d70b70 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120002815 | b1e621e1-7a99-4d34-a994-adad0ebee2fe | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002816 | a2c329a8-55e1-4a81-b41f-59b4fcd85bbd | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002817 | a43b84f8-e337-4814-ace7-71d2716ad5fb | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002818 | a8249540-c33b-46ce-acc8-2f290f56d4c3 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002819 | c23d7cbf-a4a1-4a2d-a141-072d20fda4af | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002820 | c43f4934-67a2-4cc4-8532-483ca15f1a4d | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002821 | c43f4934-67a2-4cc4-8532-483ca15f1a4d | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002822 | b5ed5504-922a-43be-943f-3e0ed058976a | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002823 | b5ed5504-922a-43be-943f-3e0ed058976a | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002824 | d5fb693a-f214-412f-a3b2-fba72bcd47cb | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002825 | d5fb693a-f214-412f-a3b2-fba72bcd47cb | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002826 | d93a72ad-1226-4dcc-9c15-1eec67e59a91 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002827 | ddf07066-4e30-4329-a4e7-60da0ffba0ca | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002828 | efc9a6eb-3dd6-4c6e-8059-574254bbdf27 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002829 | ec5d31e0-225e-43fc-bc09-2dec215167f7 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2027-02-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120002830 | e61c2e50-a3f0-43a3-b58c-440bab53bccc | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002831 | e7ff1bd8-ca85-43d3-8fa0-58dd43cedc18 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002832 | e7ff1bd8-ca85-43d3-8fa0-58dd43cedc18 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002833 | dfa9d969-a4de-46fa-92af-4c8251dbb505 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002834 | dfa9d969-a4de-46fa-92af-4c8251dbb505 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002835 | f5ba8435-2ce2-435b-9b2a-5e6cde52700b | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002836 | 0b5002c5-cb34-4ed1-a269-0a8b39feaf3e | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002837 | 0af8e67d-3b32-4ad1-a817-222509fb1848 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2027-02-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120002838 | 01cc5168-89d6-448d-a5b2-d5e470beca24 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002839 | 18eec926-4404-4492-9ca6-191f166c0c75 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002840 | 18eec926-4404-4492-9ca6-191f166c0c75 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002841 | 1bf43252-5cf1-4e8e-ab68-c1aa2e60ceae | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2027-02-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120002842 | 47f362f2-9d51-4eb8-8e9c-2358fa6a3262 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002843 | 4c2c5c16-4b83-452a-b003-faede3edafde | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002844 | 4b9f697b-0c5f-41f8-8a5f-13f050192ac8 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002845 | 33e2f352-0e93-4dba-b264-9251c88eac4b | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002846 | 2b536b53-68f6-40d5-88cd-3b970646e9c3 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002847 | 28eec98a-ad98-44a8-bb16-7499093de276 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002848 | 9502acd8-c654-4eb1-899a-088ce2428be2 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002849 | 956edfe7-1882-420d-a3a6-db9869386d5e | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002850 | 903a8f5b-269b-4d61-bbeb-1845431ec776 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002851 | 8fa10ff4-c932-4840-ab5f-e84293d21cfc | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002852 | 7d5e58e6-6c1b-4fa1-978a-ac9d3cfcc856 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002853 | 86655162-a98f-4c4d-8670-9f014813dbc6 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2027-02-04 | Level 2 | [8 empty] | LU | 2026 | 2
1120002854 | 891c2de3-0b41-4e25-bbc9-54fbeef13686 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002855 | 52bcf19e-16ac-4611-9336-41459db98c49 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002856 | 4d83d9bc-059f-424e-bdbc-867d645fc56f | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002857 | 4e38cfe0-cade-4f40-9c6e-73b7b87ca712 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002858 | 4ecdd626-aa2c-486d-b024-b0bd1c1fc0e4 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002859 | 5f621922-1ce1-43cc-816b-ebb33c67182a | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002860 | 6df8586e-b727-4edb-ad3a-19999c9eb4a1 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120002861 | 4970a61b-198f-4c24-8e9d-8f4d76b824e7 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002862 | 46fb7db6-48fa-4d80-8ded-6f5092f72dc4 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002863 | 3eac8ef6-53b4-46ba-888e-77e629bef738 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002864 | 1f5b3061-4b02-4be7-973f-45d35de20249 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2027-02-05 | Level 2 | [8 empty] | LU | 2026 | 2
1120002865 | 1e8738e4-8df4-428a-8f1c-c33d15d8bc8a | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002866 | 0f3f7bd4-ea79-4ed4-9439-346e08e5e7af | UG Transformer | Non-HFTD | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002867 | fff30e11-219f-4eb7-920c-73beb89de83e | UG Transformer | Non-HFTD | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002868 | e65bca41-0864-4201-9b79-1c6f1f9a737f | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002869 | a734e99b-e261-4e53-b624-471f76a5eba9 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002870 | a61339ec-0c88-454c-9fbc-a00fbe2d1806 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002871 | aeb681bd-9e1c-41e8-b509-768712534942 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120002872 | a1d615a8-94fa-4364-930c-e54d8d6c3a67 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-02-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002873 | 464fe159-84df-41dd-874c-5ef6f8d96704 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-02-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002874 | 53956147-bc65-4b7f-9b67-c3079aec7a48 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-02-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002875 | 5d33b72f-65a4-4960-b9c3-fd432e9afa6c | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-02-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002876 | 5ea62a95-29c4-46b3-82b8-1659dba188d4 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-02-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120002877 | 59c2c7cd-1859-47b3-92d0-fa40f30a86b8 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002878 | 7008329a-97f1-412b-95af-a7c3a01ee2c2 | Pole | Non-HFTD | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002879 | 600211f7-84a4-4c84-9e2b-9ccea0fab937 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002880 | 600211f7-84a4-4c84-9e2b-9ccea0fab937 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002881 | 83db1dc2-176d-44ac-9d12-ec35e839e4e4 | Pole | Non-HFTD | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002882 | 4ab8899b-33ae-4ac0-a5ee-a07110ecd2b8 | Pole | Non-HFTD | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002883 | 0afb53f1-81eb-4d33-b1c5-ea400b92ab94 | Pole | Non-HFTD | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002884 | 1bebcca9-675d-4d6b-a2bf-c91f92928b59 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002885 | ad3556ef-a006-431b-9bc2-082759e91541 | Pole | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002886 | c4543673-5cc2-4453-92fa-1ad3fc0fc9d5 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002887 | e477e878-c110-4c71-920a-18b52ccaef7e | Pole | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002888 | db783f71-073e-46c1-8dac-3eb0d33a9206 | Pole | Non-HFTD | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002889 | d6c9a4bf-57ca-4f0d-b8bb-9bff95e0811a | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120002890 | d09e11b2-abc7-4c68-8e50-3505b90e3809 | Pole | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002891 | e189ebd7-de43-458a-bc52-415c0b756b78 | Pole | Non-HFTD | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002892 | 228ee7a2-c9ec-4cff-af93-2394a2df4cd4 | Pole | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002893 | 076c5ea9-0b72-4c6a-b1c7-ec13300d288d | Pole | HFTD Tier 3 | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002894 | 26a31d33-82ba-4b87-823f-a352a1d1cdbd | Pole | HFTD Tier 2 | Distribution | 2026-02-10 | 2027-02-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120002895 | 3274861f-2f2a-4a28-bc85-8c8a5750da8d | Pole | HFTD Tier 3 | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002896 | 6cbc1ea9-33df-4c6f-825e-02474bba5062 | Pole | Non-HFTD | Distribution | 2026-02-10 | 2031-02-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120002897 | 5f07b1fe-5f4b-44f6-b998-5f963bed8da1 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002898 | 31116eb1-85cb-43bd-b1b9-1e216dab31f3 | Pole | Non-HFTD | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002899 | 2a3c8d8b-77d1-4fa0-9dfa-b7b9d42063fe | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002900 | 0bce1008-36c5-43ec-b60f-751fd0126239 | Pole | Non-HFTD | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002901 | 0f30984c-b447-499c-a1b8-3a0fbd930ea7 | Pole | HFTD Tier 3 | Distribution | 2026-02-11 | 2026-08-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120002902 | e23ae615-ef4f-4afc-8a99-9ff432c274fd | Pole | Non-HFTD | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002903 | d8cbb497-1718-4d27-b01f-b8946178a859 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2027-02-11 | Level 2 | [8 empty] | LU | 2026 | 2
1120002904 | ac8b23e8-1a30-4302-9c9c-5a2066505207 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002905 | a3ad1276-f50f-4f8e-8f84-dddb2d9abb93 | Pole | Non-HFTD | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002906 | 9fff6dbb-dd09-4e1e-9cd1-55bde8dd5694 | Pole | Non-HFTD | Distribution | 2026-02-11 | 2031-02-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120002907 | b4adabfb-9d6a-4a06-bd2d-5e44ea8c3437 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002908 | d536c0ba-0751-4684-bab1-849abbd88ded | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002909 | d472cb99-e61d-4bb0-9d37-2935855f1f18 | UG Transformer | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002910 | e29b81b6-988a-47a6-8379-6a07a137cb80 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002911 | 032570e8-7daf-4c6d-aea9-0c890d8d5d88 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002912 | 1f3c773f-5a34-4f2b-9760-6b53b8560be0 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002913 | 1811d649-deda-4df0-8691-793aaff2741c | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002914 | 133d6464-a59a-44b3-a652-0aac9abd56e6 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002915 | 495fcac5-e8ae-47cc-8e01-5433a0035ca0 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-02-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002916 | 48759a36-17b8-4b6e-97a7-60611b9ab72b | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-02-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120002917 | 42fe35e2-a11c-4695-9d9d-f173f1345ac2 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002918 | 6d91bd52-0e7e-422a-85d3-2b9b83e2151d | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002919 | 62cd3790-e154-4d89-acb4-faef6d7c29d7 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002920 | 8d57cf45-cfc4-4f5f-ad2f-1ad99d1f00f6 | Pole | HFTD Tier 3 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002921 | 9def7a3e-8704-4a3a-8fbd-96c6125e7a88 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120002922 | 907fe96f-cf25-4ab2-918f-5338de13d9ac | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002923 | 813e680c-cc58-4a3b-a2f6-c3fb9c937cd6 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002924 | 88cb80df-85f8-4b3d-8567-8efea11ac008 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002925 | 8721e292-546c-49f6-b272-d73dd7bbee08 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002926 | 87dd2471-d9e0-449f-bcb9-b2d939f654b9 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002927 | 5aa10f49-4629-4424-b74f-b9c7eb8a2375 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002928 | 3aa3b9ad-9781-4c91-9e87-b071b581d45b | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002929 | 2b2052f7-dc2c-465e-bfdd-6959bc6803c9 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002930 | 1ef72bb9-3aa6-4821-b3e6-a40e2e3108b4 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002931 | 1ddba277-3595-4889-80be-d5d63f9b784c | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002932 | 24f35ade-a910-4916-a354-2737be72161c | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002933 | e3dc6c0b-9158-4cac-bcfa-755070a97205 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002934 | d77d0da9-ba3e-43d1-a88f-22cef7dcaf71 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002935 | b0ba3530-280a-4093-a274-8e61ff21e95c | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002936 | b0ba3530-280a-4093-a274-8e61ff21e95c | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002937 | a6d841be-15ff-4cde-96c7-3e912b4a1ee5 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002938 | bb2a4ca6-13c0-4f0e-8d4f-b12eeda702b3 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002939 | bb47362b-e962-4bdc-bf12-07525f23cc54 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002940 | bdbc03b5-73df-4956-a4fb-d2c1e343a17a | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002941 | bdbc03b5-73df-4956-a4fb-d2c1e343a17a | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002942 | fe865be5-8abc-4e3f-95aa-eae62d22ed8c | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002943 | f4802fc6-8476-4295-a857-4192bb98c682 | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002944 | f92135e6-733f-47bc-bd15-129b1e9925ed | Pole | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-02-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120002945 | fa34b536-69b6-4bff-a427-45727992e087 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002946 | bbd69100-c569-4712-b262-162dd1051b9b | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002947 | a42a4de5-cc92-4250-91fb-4184d1c8a865 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002948 | 9ec8a37b-ebb8-4089-aab2-e5e1a89ceceb | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002949 | df5b97da-c6ba-4d72-99d2-394aed5c2761 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002950 | cfebbea0-9c23-4f9d-9413-68213f4c46e1 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002951 | ce097805-f6d7-4681-82c2-ec40399ddcb1 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002952 | e6e914a4-8e4a-48b3-9bbd-385545a1144f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002953 | 2414d4ec-fdf0-4ee8-8109-f98d7c848068 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002954 | 1e4adb5e-3a3f-41ae-9323-090f9f9700b3 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002955 | 1e4adb5e-3a3f-41ae-9323-090f9f9700b3 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002956 | 2e6dfac8-f509-4061-b61e-f7d59a450c3b | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002957 | 68e3774e-51b5-4720-9ed1-cccf2777789f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002958 | 6b2f575f-ec15-46ee-b3ca-c0c079fcfb3f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002959 | 6b2f575f-ec15-46ee-b3ca-c0c079fcfb3f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002960 | 6b2f575f-ec15-46ee-b3ca-c0c079fcfb3f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002961 | 6f4af95c-af17-4d50-9c3f-12aa019b7520 | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002962 | 8e2c6551-13d1-42b1-8e81-f90ac19a742f | Pole | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120002963 | 9389563c-36d8-435e-b50d-5fddb6a891d9 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002964 | 92ef99c7-55df-42ab-84a0-3f3be8c10942 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002965 | 92ef99c7-55df-42ab-84a0-3f3be8c10942 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002966 | 5e8045d9-c611-4821-a920-55b55003d1f5 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002967 | 5e8045d9-c611-4821-a920-55b55003d1f5 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002968 | 552aa873-ee86-43b8-a476-770474746fc5 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002969 | 4f446eb5-a3ac-4103-8376-3e82a1e6cbdc | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002970 | 238ab903-ef02-46c4-bcfc-56e4fd011949 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002971 | 1fdb31cd-dc14-49d7-8d19-2962b2d75831 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002972 | 15d1d0ea-6210-400a-863a-6fef35d4ddfe | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002973 | 182862e1-429f-4ca4-b6fa-6579c9fb5c5b | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002974 | 179dd238-db1b-4630-a5ed-4515dd94cf63 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002975 | 179dd238-db1b-4630-a5ed-4515dd94cf63 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002976 | 08a9d6b3-c26e-433d-b56a-e9e65f5be091 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002977 | 094b7649-9651-4538-97b9-bba59dbca75e | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002978 | e2ab6d2c-549d-4dbf-8ce1-73d1b8424b11 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002979 | cc6b43be-04e9-49d1-b71a-1100e1587615 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002980 | d0aafc8b-4416-465f-8b58-863a293ae233 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002981 | d199de1d-040c-42d9-833a-bed0d14e1321 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002982 | d199de1d-040c-42d9-833a-bed0d14e1321 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002983 | a601f0b7-8ff2-4317-a44e-f001b4d2ec69 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002984 | a601f0b7-8ff2-4317-a44e-f001b4d2ec69 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002985 | af7a0735-f475-41c9-b70f-0632252e9064 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002986 | ffc312ab-b223-440e-9fab-04414c14c115 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-02-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120002987 | b4c31695-72be-4646-97cc-52aa8fc281d4 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002988 | ca4a606c-72cf-48ad-a173-79c6118703ab | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002989 | d2d4cb61-2826-4bd1-8d9d-0b7e6cd3c971 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002990 | d3362d5e-1be2-4069-929c-1744f7372f87 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002991 | 506d8efd-9367-4738-a825-9cb139b9eb1f | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002992 | 5f505837-fa41-40f4-848e-e8b88ce929af | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002993 | 617937cc-82ab-44b3-85e1-6e157892dc43 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002994 | 7cbbf252-d462-4d4d-9a2d-e7a7a07e0576 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120002995 | b7e0a90a-5228-4048-b163-72de51a9c85a | Pole | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120002996 | be0f7d05-7b95-4b7a-866d-ac3cbde8b3c2 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002997 | ca08db1b-7e1f-4227-8ab3-d7fe80630354 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002998 | c84bb148-da9e-40fa-b430-4dc441781c64 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120002999 | c443b0ce-0399-4a7d-92aa-24b22bbd92ff | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003000 | ae784122-567e-4698-b6eb-cef9ccc3a598 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003001 | abe19756-4cc6-44c1-b6f0-a1d1b8a81454 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003002 | d39cbfba-41ee-4cd6-98f0-4ca67471a2de | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003003 | ccb1f3d5-1b58-46d3-b0fc-eb4feae4405d | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003004 | dbbfc0b1-4add-4c05-95c4-4c77c2705432 | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003005 | dbbfc0b1-4add-4c05-95c4-4c77c2705432 | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003006 | da54a50a-12eb-46c7-b116-50fbcb3ad993 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003007 | e27e6488-3d52-4129-868b-8bc0f1b389ed | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003008 | e27e6488-3d52-4129-868b-8bc0f1b389ed | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003009 | e5b8acd7-6dbf-4853-bfec-f516a6e99a3d | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003010 | eb7b0445-8e5c-4ec3-9858-ef634d800045 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003011 | f36dcf02-e002-4a0a-b273-5a6b79778be9 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003012 | 7b54731e-3d2f-4e0f-8194-24fd3e88562b | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003013 | 868cb5aa-a327-4131-be81-f94c3480b546 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003014 | 868cb5aa-a327-4131-be81-f94c3480b546 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003015 | 8593ea89-7eb3-40c3-9acd-73220895ddad | Pole | Non-HFTD | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003016 | 889f690a-d863-4a55-b9b2-860d68c63681 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003017 | 851c78dc-5788-4af8-9ca1-8d96c410bf1f | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003018 | 9865a1f1-8dcd-4289-a82c-f52f05e6b580 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003019 | 98b30946-fd28-4c33-8df6-307f28855256 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003020 | 67dbb38b-aa59-49d0-bc74-69a070886697 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003021 | 66a04103-f1ff-4ed6-89e6-d06bc2e8ee2b | Pole | Non-HFTD | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003022 | 59d8a487-c3e3-432b-9763-51e3e3ae04ea | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2027-02-25 | Level 2 | [8 empty] | LU | 2026 | 2
1120003023 | 561d15e1-a106-442d-9a2d-b51dc5ac5937 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003024 | 55c43c4c-f812-4a36-9020-1229b93d33c6 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003025 | 55c43c4c-f812-4a36-9020-1229b93d33c6 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003026 | 56001582-d6b5-40e3-8190-3fd215c6c129 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003027 | 0a56abb0-5d78-4624-b1fa-80312b7173f3 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003028 | 1fd7172c-ae4d-45bf-a6be-b3cd8cb7667a | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003029 | 2c66a317-4ff6-4b8a-af65-29fe1a181a2c | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003030 | 300c1818-6065-47c7-a2f0-d8fb15dd12cb | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003031 | 341386b8-78b9-4580-a017-f2dddd8f3f5a | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003032 | 41c71e84-e99b-4a98-8d0a-39e33789c0f8 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003033 | 2d293791-8db5-4d7f-a14d-cbad56ada21a | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003034 | 53810fb9-587a-4e38-8c8e-9ac2ff5dbc9a | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003035 | 659b55ed-5dcb-49f5-b078-69b657160be2 | Pole | Non-HFTD | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003036 | 88f43953-9713-49b9-b572-e3cf95b796ff | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003037 | dbbfc0b1-4add-4c05-95c4-4c77c2705432 | Pole | HFTD Tier 3 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003038 | a2fd1834-86e5-4fdd-bcd0-dcc8c00351be | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003039 | bed4265d-71c6-4f18-95fa-f1bbdad405a8 | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003040 | fcd55327-b14c-486a-9312-f2d791f4e23a | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-25 | Level 3 | [8 empty] | LU | 2026 | 2
1120003041 | 8bcb781f-d59b-4402-84b6-d99aff1a3176 | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2031-02-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003042 | 26d8b19a-697c-4d00-a06b-43a00d675534 | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2031-02-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003043 | 2ef2e202-9a86-4938-be75-5c89e41a874d | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2031-02-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003044 | 28cd1ccc-0e54-4ac7-8dee-9b7d765274ec | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003045 | 28cd1ccc-0e54-4ac7-8dee-9b7d765274ec | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003046 | 43c944f1-c01c-4d15-a194-8acef9e76763 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003047 | b9249598-8dbf-4827-b545-0f6d4678b374 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003048 | c526d70b-2cdf-4116-a6f9-7a0945d5563d | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003049 | c1075d10-3968-442f-8fb5-ba7134fc35d8 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003050 | c1075d10-3968-442f-8fb5-ba7134fc35d8 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003051 | e812ea55-7cc2-4031-a123-4683e29f25ed | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003052 | e698f617-ee4b-41ae-aa68-4c9b7a12e816 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003053 | db552461-f98d-47f9-8a33-72f242d1c58e | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003054 | aea9e280-2171-4e32-b482-918342b19109 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003055 | 2e36b6e3-bf22-4eef-95e9-9eb2a0e8bf9b | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003056 | 306c9c04-4685-489c-8938-8643088791f1 | Vault | Non-HFTD | Distribution | 2026-03-03 | 2027-03-03 | Level 2 | [8 empty] | LU | 2026 | 2
1120003057 | 1b0b18e5-d4c8-40ed-a493-4fd32480f151 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003058 | 13d8e024-ed68-4140-a5f2-d6c39f218459 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003059 | 0e884f3d-1176-4771-80ce-ec68962c43ba | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003060 | 67d3d39e-fb1b-4286-967c-041a57695d74 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-02 | Level 3 | [8 empty] | LU | 2026 | 2
1120003061 | 4199f51b-d009-4f39-af41-713cae74745c | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120003062 | aa674e39-28f0-45a8-90c0-2cdc76516c9f | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120003063 | aa674e39-28f0-45a8-90c0-2cdc76516c9f | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120003064 | ff802b44-208d-45ac-a6a4-4911dc1258e6 | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-03 | Level 3 | [8 empty] | LU | 2026 | 2
1120003065 | fad31da9-dd83-4664-a69e-60b23cedc1ce | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003066 | aa252841-0797-40b2-b086-27279815889d | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003067 | ae5205f4-d404-453c-8fd0-f7af9ab7e5b0 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003068 | b2d0e600-54c4-4472-a1e7-c8428c52f6d7 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003069 | a49ece12-c117-4b50-a9fd-4b07841bcbc7 | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: 1aae68eb-ef32-4d8c-b881-2a9ae8bc416d |  | LU | 2026 | 2
1120003070 | a4cf3a39-ebee-46e2-ad92-d68e13f49005 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003071 | a4e34aaf-6ed5-4b45-a8e6-58826f3f9394 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003072 | c572001d-8731-4c3a-a9fc-2fb9c12abc7e | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: 4ffd97ef-4741-4357-b2da-137d5c786147 |  | LU | 2026 | 2
1120003073 | d57b90f4-ea7b-4626-b2ba-f43c5337c893 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2027-03-05 | Level 2 | [8 empty] | LU | 2026 | 2
1120003074 | d10577bd-2f5c-4484-91fe-bd1329ec954b | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003075 | cf921062-d742-4d3b-9f5e-3d0e9dff6a55 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003076 | 3efdfa1a-076f-4e4e-9846-a84d99a30ac8 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003077 | 4617ae43-1c7e-4bb6-9813-3d4782e02dd5 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003078 | 4b1af944-e90a-4ced-b1ed-bc6092073112 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003079 | 2c73fbe0-6c0b-4f4e-9b3b-7c275dbf0150 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003080 | 2a98b9a6-1240-4f72-8a1e-2ae2bc821c2a | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003081 | 0e8b9d3c-997f-461e-9d1b-764b156455c1 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 |  |  |  |  | Level 3 |  | Reinspection Date: 2026-03-05, Work Order ID: df66dedc-dfcf-475b-86f6-52907593ac80 |  | LU | 2026 | 2
1120003082 | 05410693-afaf-4cd6-8094-6b661d63f9a2 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003083 | 1322b688-ca62-4600-8a12-0b0b12044945 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003084 | 17b57cf7-c9bf-43b1-a492-1ff13f37b870 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003085 | 53a3be32-d001-4626-a95a-2b801737c43e | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003086 | 5675bcf2-b180-43ed-8595-c008b7f91697 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003087 | 524bffc2-fe5a-40d1-a7d7-9c892520e910 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003088 | 5b058809-b719-4c18-99c9-3e9d4396002d | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003089 | 9e0f94ed-e29e-423b-9332-ac9bb4390e7a | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003090 | 8a1eb3d7-a9ae-4436-87c9-7cc0722399e3 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003091 | 79553c4b-bc35-4a59-89b5-cfeb0198004b | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003092 | 73dad1be-090b-4f0e-95a5-1839bacdd5e0 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2031-03-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003093 | 93863e6e-3540-4bd2-ba1b-fd2fc90b2279 | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003094 | 52faa6fc-6e4a-4b3c-8bb7-f38af472eeba | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003095 | 52faa6fc-6e4a-4b3c-8bb7-f38af472eeba | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003096 | 6a790db8-0086-4393-bfca-5b509af70c93 | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003097 | 0e2d467f-b9f4-4b13-b50f-dfb6bf855dba | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003098 | 0ffddd32-f23e-481c-a0e4-608424c34ca9 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003099 | 2294ccb9-ab40-4106-a01d-9013d65c9ec5 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003100 | 27b417b2-b586-4abc-afea-7856e9268a98 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2027-03-09 | Level 2 | [8 empty] | LU | 2026 | 2
1120003101 | 43c18895-1207-47e3-9919-e961bfd73edf | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003102 | 43c18895-1207-47e3-9919-e961bfd73edf | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003103 | 39cefbad-e975-4723-9166-27ca705e15ac | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003104 | 39cefbad-e975-4723-9166-27ca705e15ac | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003105 | 3c2cdf8a-fa88-439b-b4cc-d9fbc0844d7a | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003106 | 615259eb-3c42-4854-b67c-05074a6a516a | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003107 | 9ea6fbff-e542-4fc7-91d5-b3215327fa2e | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003108 | 99376bcd-a891-41cf-ae68-2f7e56041bc9 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003109 | 99036461-7e01-468a-ac28-9421b2ac2bec | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003110 | 7e72bb7b-7ed0-4587-b227-0bdbb2bf199c | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003111 | 888c7f90-5126-43af-a042-b506293b9ead | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003112 | dbd009f7-be7f-4cbc-91a6-966321a15537 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003113 | dfbbd831-a71a-41f5-bd2b-afa98c10cdbd | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003114 | f14b8ddf-48d8-4096-8b2f-0ca7dd68b8d2 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003115 | c7ce21a3-e2d0-4362-ad55-83b29cef7b6a | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003116 | bc6a569a-3d27-46a4-a597-e96c9f6b4c29 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003117 | b280594b-6492-42fa-837f-c9acefe22e6b | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003118 | f8bfc0dc-15a4-4ab2-ae1e-534470807f4d | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003119 | fe92dc9e-c8f6-4e5b-a9c5-3ca0df1851eb | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003120 | fd9a3caa-9f74-44d2-b6e0-af23e569ca39 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003121 | bf0f0c28-50a3-45e7-bc7f-9990c140a23e | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | LU | 2026 | 2
1120003122 | 783620c2-5020-4478-905b-57bf0d3a54c5 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120003123 | 783620c2-5020-4478-905b-57bf0d3a54c5 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120003124 | 74b36430-f74c-44e8-993d-9d495ab6eaf8 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003125 | 43cd406b-fa06-42c8-b572-4ee472f93257 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003126 | 47fb2594-2d2d-4721-ae7f-ac02f8cc11f8 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003127 | bd999830-c644-4afb-99b5-cd80b4313679 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003128 | b1b61ef0-f8b9-4a69-a366-9c5bba3bca86 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003129 | f011eed4-95ba-4634-8851-c559d65b0c12 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003130 | cf13eddd-18d9-47ad-955e-b46e0875855c | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2027-03-13 | Level 2 | [8 empty] | LU | 2026 | 2
1120003131 | cd8c40de-a0e2-436d-b41e-997ddb625c16 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003132 | ae32dad6-267f-4c42-8695-c39867400785 | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003133 | b6d4f3e4-d93c-41eb-a471-7d77bda12e8e | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003134 | 28ea2568-7530-4667-99ca-d77070bd2d2d | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003135 | 0cdd6527-19a0-4173-8576-80e1957db301 | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003136 | 3f1fd076-4f1c-4280-96e9-1bea7bf1476a | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-03-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003137 | 9541bea9-7b8f-43ec-9196-a2280c1f1d45 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003138 | 8cdc4718-e223-41c2-ad64-b2d6f418c7ff | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003139 | 6418aee6-738f-4947-9d77-7e31d18e4b01 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003140 | 6d0825f1-477f-4814-a513-c4ed238bd11e | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003141 | c79b9dee-4d89-4b3e-8922-460bdcc64b5c | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003142 | b04bc88d-9c41-498a-953b-61b211175f59 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003143 | ccb9d4ad-0198-4c09-8d64-83c117e55ec2 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003144 | df0e2f7f-c002-435c-9db0-3a52fcb21177 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003145 | a74e66e9-af39-41e6-849b-6ffa0d714c1c | Pole | Non-HFTD | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003146 | ba01e961-bdab-4707-86d0-d1c20f2666b5 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003147 | 56440470-c1eb-4aec-b1b7-bdda15661da1 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003148 | 9314f914-c0e3-42ce-9028-3bf21f2a3af2 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-03-19 | Level 2 | [8 empty] | LU | 2026 | 2
1120003149 | 3dc870ee-e97b-4290-8cc2-88f477cb9ae2 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003150 | 2298a983-4706-4acf-8cb7-55e7c02c993b | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003151 | 2298a983-4706-4acf-8cb7-55e7c02c993b | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-03-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003152 | 1c490569-793a-4948-b3c0-a5b5ffecf746 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003153 | 4b50930e-3d7d-4eb6-a78d-333a8e0afec9 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003154 | 9e4fe35d-e8e3-4e28-8867-505a5fa1fb71 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003155 | 8556f9fc-960d-4d70-bf82-aebe7b1dab5a | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003156 | 5590680e-90bf-422d-8828-15a359ec832b | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003157 | 52cabac1-2578-4cc6-85dd-e30c676838ed | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003158 | c6221b71-27c7-46d1-a3e5-59346665191e | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003159 | c1cd8f2a-e00e-454a-857b-4d897dc20473 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003160 | dd2e9d8d-1e2f-4cd8-ab09-9a5dfbe0dfe7 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003161 | fb1c1691-8df3-41c6-8842-35af48ce050e | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-03-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003162 | 1547c321-b75f-40c6-9f89-1600f7a142c0 | Pole | HFTD Tier 2 | Distribution | 2026-03-23 | 2027-03-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120003163 | 1afd68f7-cc90-45bc-98ad-464051f54749 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003164 | f0f761ec-8021-4353-90ab-bfe190d74476 | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-03-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003165 | ef70892f-0ee5-4207-8383-f02771bd1ec5 | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003166 | 2facf443-b30b-4bbf-a1e4-eaaa54ec489c | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003167 | 2facf443-b30b-4bbf-a1e4-eaaa54ec489c | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003168 | 4fe0a9b3-ff8a-4c80-9009-7c12711be5cd | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003169 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003170 | 600d654d-c1da-421d-8886-12324f699d37 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003171 | 7e7963bc-0b8a-4699-bb54-5f9389c6240f | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003172 | 93857e45-2ce0-41da-87b1-5dc54b484729 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003173 | 326d4ae7-f889-4068-a56b-675f6357bca3 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003174 | 294d60a2-3b00-4dc6-a240-6d0ca0950d9f | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003175 | 2b164907-2760-402b-81a8-bee79d08c6e7 | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003176 | 3cee9095-b717-417c-8626-cc17da4efeb5 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003177 | 1b9cb554-3e03-488d-a671-a7e38e6cc614 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003178 | cdb5d981-85c1-4475-a40c-40af2746d86d | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003179 | c604788b-42c9-4f4e-94c0-ba57c0329b22 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003180 | c935ccdb-240f-4ca0-8b17-e29732d1a7a0 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003181 | ca983c8d-de6f-40c1-94df-68c878c012da | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003182 | bd96d15b-d4e9-40c5-a87f-b06284ef6316 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003183 | a3e530bd-39fa-437a-be15-c67d9f937719 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003184 | 9ee6dfc2-ac7e-45ae-8787-d9bca0489ce5 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003185 | f4fd76f0-b052-49e6-8371-d51fa1700d0e | UG Transformer | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003186 | a01dc70c-a055-494b-8a2e-3e7f1cc2715c | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003187 | a021e634-48c2-48cb-9107-6a5d89b6d8f7 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003188 | ae785958-d02e-47fe-bf2a-d82cee78fed9 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003189 | c493cca2-8501-4530-9036-888f51a6669b | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120003190 | dc7ba9f0-d57f-4d56-b580-b6f295a5d75a | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003191 | ef2efcea-8316-4819-8dd7-98326d6019b2 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120003192 | f1ceb276-3daf-42cf-96c2-84546a80a373 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003193 | e21d4a80-708b-459d-9d3b-8178fbf1a5d5 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003194 | 219239de-50fc-4bd4-aa47-7e29a2fe9999 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120003195 | 23224399-d509-4d60-bd03-772ecd04b104 | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003196 | 0cebb401-d160-44f7-903b-11387612c657 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003197 | 27fbbc2b-972b-4fb0-b89d-c6340ba61951 | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003198 | 33055e9c-42fd-456f-bcbf-cb31ee8e139c | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003199 | 8f9a75c9-affe-4906-b238-7d3ff6a3a92f | Pole | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120003200 | 7c12b66b-8ab2-4e7b-870a-dddd029fae5e | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-03-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003201 | 9ae182f6-be86-495b-9bde-3e1ba579ebf9 | Pole | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-04-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003202 | 95e7f7b9-853b-4092-a7ae-04f2a04670e4 | Pole | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-04-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003203 | 297d28fc-3bc2-4fbb-908a-3561286f06e5 | Pole | HFTD Tier 2 | Distribution | 2026-04-06 | 2027-04-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120003204 | e891de79-ab11-48b9-a2ea-4252b9e56174 | Pole | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-04-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003205 | d4c0fc68-57a0-421a-819b-6543a0ac8c5a | Pole | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-04-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003206 | bb7e8be9-3e60-4ac9-8626-7bf59cb8c5eb | Padmount Transformer | HFTD Tier 2 | Distribution | 2026-04-06 | 2027-04-06 | Level 2 | [8 empty] | LU | 2026 | 2
1120003207 | ba352782-030b-44fd-9323-8d4c2cdb18e3 | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003208 | c4047395-99cb-4fb3-832f-7fafe8ea66fc | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003209 | 38760184-e09b-461c-9b50-31a6355c520e | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2027-04-07 | Level 2 | [8 empty] | LU | 2026 | 2
1120003210 | 45eedc66-0a68-4dc4-9659-b3d6a9c3811d | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003211 | 00af01f4-74d0-4f59-af37-6daabc6e2925 | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003212 | 57d5a8b6-c65f-4e6e-85d2-2278b67801f8 | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003213 | 56b304e4-bd89-4fe5-9260-0891c1a96d31 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003214 | 64676096-63b5-4953-9341-294b19cea183 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003215 | 9a59b358-1904-4fa1-a92a-1f2a01fc0fca | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003216 | 93da5939-a9f5-4e0a-a814-0ca0576b051a | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003217 | 1fc30080-eded-48f6-a5ad-d79d8c9cccb3 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003218 | 3771bdfd-6e02-4912-a3d8-c2eab2159119 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003219 | a9c6a73e-57dd-4094-a282-d0359ed8afa1 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003220 | b0ccc44a-2a90-473a-a9ec-be4fda8098f3 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003221 | d3fb1120-fe06-4cf4-9448-b136a513126f | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003222 | cdba5d11-4185-44f3-82c9-6e75b9604dd9 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003223 | e4f0a23b-77a9-4864-b2a3-5a9c2efaec28 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2027-04-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120003224 | ece4bff5-fa73-4b62-82d5-7988e876e611 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003225 | f8644ad8-e142-4329-bf3f-3f6dffcdea40 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003226 | fa31dda3-7047-460d-af97-cb83c2ec6223 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003227 | f9f02b2d-f8e3-454b-96cb-8a9c7d7bb1e1 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003228 | fc812491-720b-47e3-a887-c8c507c95e9b | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003229 | fc812491-720b-47e3-a887-c8c507c95e9b | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2027-04-09 | Level 2 | [8 empty] | LU | 2026 | 2
1120003230 | ab5712e8-a490-45d5-ba68-8c68d2156432 | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003231 | adb219c5-1da9-43d5-9f95-5968d3910dfe | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003232 | 29508bf3-b95b-445c-8027-af14cf4eb14a | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003233 | 3c5c6705-bcf3-42ac-a275-c8d042bc3fe7 | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003234 | 00ed3ae5-62fd-4918-b1fd-bf4313eab346 | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003235 | 0b9a6fc2-3a43-4c48-a08b-da2cbfbe676b | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003236 | 8f01139f-ac2b-42ea-b4b5-6024629d6848 | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003237 | 7667db2f-36e3-434a-b9bb-1c5699b3836c | Pole | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003238 | 99695dd6-72b8-4579-a107-86f4464cf1ad | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003239 | 5ede3db2-0541-40c2-b60c-286f66bf4b72 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003240 | 3cf41935-5f28-4720-b3fc-2baf687a1078 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003241 | 35ff738f-be54-43b5-a6d5-480aa36dadbd | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003242 | 38e8b4d3-fc5e-4448-9ab6-5f33c3908112 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003243 | 38e8b4d3-fc5e-4448-9ab6-5f33c3908112 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003244 | 9fd05fa4-c2c7-47cd-bd8a-790e3c64663d | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003245 | c312a9dd-7792-435f-af9b-f4fd1fe292a3 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003246 | c6263320-606e-473a-af85-087966bdbc68 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003247 | b934109f-6fae-42a0-b2ad-276d1bf1a009 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003248 | be21e767-90a6-4fd2-8f5b-13127380603e | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003249 | ad00393d-3ffc-49c2-a7b0-079ca4f95c1c | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003250 | f1612b86-2f0a-4e05-bb43-32a798d6c72b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003251 | f1612b86-2f0a-4e05-bb43-32a798d6c72b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003252 | d9c3e038-f946-43f7-a96e-544b7e759a7a | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003253 | f8bca6d0-c2ff-473c-9143-0878308fe3bd | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003254 | ff51648b-fc12-488d-83ea-5ab203d4e619 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003255 | 45f29243-a2cd-4384-a0e0-5a5c86387b40 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003256 | 45f29243-a2cd-4384-a0e0-5a5c86387b40 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003257 | 4738c4ad-858d-4d7b-b1bc-664fd29667ad | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003258 | 09564229-2826-4c91-8523-d7b85e1415cb | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003259 | 08bb290b-f55a-4d1b-bb5c-2020d5b53fa5 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003260 | 1b05e555-2d7c-4bee-8065-5c20a06d1911 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003261 | 5e3d2987-bdc9-4369-9385-588700ff3c51 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003262 | 561c11cd-bf9d-4a9d-b67c-cc1286394222 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003263 | 656e2901-2bac-4064-a499-de7ac2fe137f | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003264 | 6b4a3e70-70a1-4e71-9a77-f5de63977654 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003265 | 6f086351-3c78-4474-9dcc-e259e09aaef8 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003266 | 98eecab0-6eff-4704-9dee-164a8a09225f | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003267 | 8dc9f005-6664-4f6e-a258-9b98f78aa45b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003268 | 7989d43b-3de3-406b-a520-2f0b664b2bbb | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003269 | 882bad7d-7a0c-4be8-b300-fe98203ab968 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003270 | 8041357c-9c25-4535-8fc8-eaac37e8a4c5 | Pole | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003271 | 8280f439-2bcb-4ecf-a95d-c78df44d579f | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003272 | 8a5439ab-2bd2-4954-bcfa-a60150ce4467 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003273 | 7a0f4d2b-25d0-46b5-9c1d-f091c78503b3 | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003274 | 7c1733b7-5071-4fa2-ab69-92eeab61933c | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003275 | 8aefff77-4889-4c5d-b1f2-d00850b4e9e9 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003276 | 997b863f-947e-406c-acb9-f7da07ea7c6f | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003277 | 9cf28b5e-5bf1-4b0f-9dbb-57d6057dd21e | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003278 | 6e25d5aa-9d02-46c0-8bd9-c8326fd456a0 | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003279 | 68b59eaf-ab6e-491e-ba30-73d53b5e2141 | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003280 | 59867805-81db-4d19-a8f3-0440277c79b5 | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003281 | 12f07c4c-b2f0-45e7-ac8f-975d55150fa3 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003282 | 12f07c4c-b2f0-45e7-ac8f-975d55150fa3 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003283 | 0afca997-9de8-431e-a2cf-a5a47bf0d8b5 | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003284 | 40ceae1a-1193-43ee-8553-f4155fbb43a6 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003285 | 40ceae1a-1193-43ee-8553-f4155fbb43a6 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003286 | 40e95e0b-a0d8-4fda-9686-bb01c43a5ceb | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003287 | 37ab7a68-4151-4f27-8abe-1b93ee3aa3ba | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003288 | 36739454-ef9c-4a4e-a504-378541b87780 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003289 | 36739454-ef9c-4a4e-a504-378541b87780 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003290 | 368e4b75-4303-4630-a692-cb2d286e4434 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003291 | f81e0c86-876f-48ec-b016-43ff9602a9f4 | Switching Cabinet | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003292 | cd61eb8d-6818-4e3f-8ba9-0907dc12dc8f | Switching Cabinet | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003293 | e2d638ee-2863-42a4-84dc-208517627d46 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003294 | ab1beb0d-417b-42ab-9c99-9f23d19a7444 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003295 | c59c4e07-cb3e-493a-b73b-24a7d4afd0de | Pole | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003296 | c8f90f09-df49-497e-a797-8ce610dcb132 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003297 | b6b57c2f-0b68-444d-951e-e9b76abc8b1d | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003298 | b04e0318-5445-4615-9647-696628abeddc | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003299 | d0c311fd-5e9a-471e-adc9-ac31a251d37f | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003300 | d05cf1e0-9340-4ff0-8747-f06112224786 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003301 | db0c15dd-43df-4378-af14-3081abe77c8e | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003302 | f65704b7-4f9f-4aa8-b3a1-be206471f527 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003303 | fbb81eff-55e2-4af0-a988-e82ffd632e86 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003304 | 386fa99a-ff56-4815-beec-60794dfdf8a5 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003305 | 386fa99a-ff56-4815-beec-60794dfdf8a5 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003306 | 32870f9c-b57b-4262-a209-60ddfa64fd74 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003307 | 30cb231e-752c-460a-a9ae-541fe18ac450 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003308 | 43bafc81-f3a4-470f-8cae-bdb923133ccd | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003309 | 0be87ffa-30cf-4fab-9fc2-a07e4b747a89 | Switching Cabinet | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003310 | 5a0ad80c-1df4-4464-9c52-f12c77e5ee0b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003311 | 4ff81ea0-2373-4e83-8a6b-0720bd8d8343 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003312 | 4f1da416-4e3e-495d-918d-e09eeb90e990 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003313 | 632306d4-e0c6-43d6-a64b-68ee8ad6cfe5 | Pole | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003314 | 8c2342b0-da41-49e6-bcb7-8c7b6519a9a3 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-04-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003315 | 9d7e83fc-d343-4f8e-8bcf-609733b76af8 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003316 | 690d3354-f549-46e9-81f5-3ccaf1436495 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003317 | 690d3354-f549-46e9-81f5-3ccaf1436495 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003318 | 091823b3-5deb-4a04-ac7c-1b0eec7864c1 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2027-04-17 | Level 2 | [8 empty] | LU | 2026 | 2
1120003319 | 02495068-3802-4def-bf1e-32fe86291c6b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003320 | 02d18de3-4424-4fcb-b57b-759f02cac353 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003321 | 17ffd87b-2b36-43e4-af5f-a7a3a32ad236 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003322 | 17ffd87b-2b36-43e4-af5f-a7a3a32ad236 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2027-04-17 | Level 2 | [8 empty] | LU | 2026 | 2
1120003323 | 1c79d9a7-763e-46c0-85de-d12d3019ff5a | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003324 | 24a80b9e-6603-446f-8162-2a83a0f4bd17 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003325 | 469d061f-c78e-4331-be41-a263313d36fb | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003326 | 38ec5fd5-6549-4e74-8704-30fd4276f9a2 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003327 | 3726c607-ce75-4eee-85b4-dde76d417441 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003328 | 29ba06c6-6db9-4e03-be84-1ff5dbd5b580 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003329 | 288ff191-4d34-4021-bf67-4bc5306eb973 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003330 | cd620eae-eaa3-4b40-9266-6e554c2597de | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003331 | dfbcb82d-ac3f-4d22-b284-f83d62fb98cb | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003332 | dfbcb82d-ac3f-4d22-b284-f83d62fb98cb | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2027-04-17 | Level 2 | [8 empty] | LU | 2026 | 2
1120003333 | f25cf463-f0f2-4f40-b089-b0138a8e77bc | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003334 | a6c5030d-60fd-445e-ad3a-96fe542448fb | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003335 | bbd867d1-acbe-4458-927c-a3749d613b9a | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-04-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003336 | bc44b3fe-04b2-42c5-bbce-d5badfd3550f | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003337 | c0114b0a-ed3d-4ff4-9744-d151314bfd18 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003338 | c053c6b2-266f-4511-b241-d0fc13e34410 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003339 | b5bcea9d-9fe6-4ac0-bc1f-02415aadea75 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2027-04-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120003340 | b5bcea9d-9fe6-4ac0-bc1f-02415aadea75 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2027-04-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120003341 | b53f4622-55f5-48f8-8f7a-08dba9016083 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003342 | c7c4d421-0b59-4fef-bd0c-cf0d3aeda93a | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003343 | a8c68455-da44-43d4-9589-72a14a2745a5 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003344 | 9ff68b67-6654-4c2e-9dba-4859999bbeee | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003345 | ed3adf8c-5bd1-469c-b4f6-22cfa07a2dc6 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003346 | e1309afe-9521-4b6d-927c-084f36f8a1ae | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003347 | d4580350-33a6-428a-9265-ba134159f9cf | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003348 | d28f5010-0d82-4bc1-a643-1e8fa6569095 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003349 | 2a2daa4c-54a2-4f15-88d1-5d45a0b988d1 | Switching Cabinet | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003350 | 298079dd-0cfc-4443-a946-47bdf66db58a | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003351 | 2c819ada-efbf-410f-9eae-86222508d0f1 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003352 | 2c819ada-efbf-410f-9eae-86222508d0f1 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003353 | 2eacaefa-2556-4431-ae89-80bf6b0a3250 | Junction Enclosure | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003354 | 2130b8f7-0655-44fe-aa10-d9a02679c7bb | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003355 | 226c67aa-23a8-4222-acec-ceea4b4c61d1 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003356 | 0c734c45-4c9b-4f4b-b84d-91450cdcd462 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003357 | 0af06f75-9887-430a-9f68-2755eafc94e7 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003358 | 11f0aace-d4f3-4364-90e4-d97afe7f0e3a | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003359 | 6e8e3c65-edee-49d5-9f95-2e380d58f78a | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003360 | 635d1289-f36b-4a7d-8ad0-dd412fadd949 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003361 | 68e82b12-9d7e-468e-8389-995e500a3511 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003362 | 674515da-5792-460d-8d77-008a109aeb83 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003363 | 5b219c7e-9db9-455f-840c-837dfbfa3724 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003364 | 5c2a052b-2327-49cb-91f6-84ba35e704aa | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003365 | 9730ae7d-75be-4adb-8946-205a410b6564 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003366 | 9223dabe-e522-4fe6-a8b7-0b0074b6bc47 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003367 | 84bfb01b-b094-42db-9549-1ca0c59486b7 | Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2031-04-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003368 | 8537dad7-4d6d-4613-a706-fa5dcc32ef5b | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003369 | 8200201d-2c39-47e5-9fa2-9a6655fadde1 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003370 | 8200201d-2c39-47e5-9fa2-9a6655fadde1 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003371 | 9df904f9-3ad9-46d5-b2e3-39ddc897336c | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003372 | 60620b92-dd2e-4b38-adda-6966febfd7e8 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003373 | 6b9c2b19-70a0-4fcc-a585-61825f4cd7c9 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003374 | 0b481ede-34f3-491f-b422-09af748a0867 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003375 | 0b481ede-34f3-491f-b422-09af748a0867 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003376 | 0d8d8c33-f0c7-412f-b029-fd2cf472fbd7 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003377 | db3d3d50-0b37-4b28-aa12-506f069c3e46 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003378 | d70283ed-fb47-4785-82db-f8075ca4d106 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003379 | d70283ed-fb47-4785-82db-f8075ca4d106 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003380 | ee029dc3-c078-49d7-8cbb-0411f53c7774 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2027-04-21 | Level 2 | [8 empty] | LU | 2026 | 2
1120003381 | a26490e1-c6be-4596-9b66-14fbc88ab3f5 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003382 | a5d36743-a296-450c-88da-c42d342efe99 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003383 | c2ebb8ce-7499-42d5-bd6a-4cd6eea73cfb | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-04-20 | Level 3 | [8 empty] | LU | 2026 | 2
1120003384 | c0b211c0-6c69-4e1f-8a71-b503c33e2af1 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003385 | b0117c57-6cc2-43ab-8eaa-a1d3a650a263 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003386 | e009414f-4c74-438e-88f4-17808818162c | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003387 | d87b9281-509d-429a-8324-1206892f925d | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003388 | cea0ce91-130d-439d-9f07-6450267a20af | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003389 | cea0ce91-130d-439d-9f07-6450267a20af | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003390 | fb0fc3b9-a3ec-4c9f-9947-31e8b17e947a | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003391 | f471923a-215e-45e4-aff9-caf637ea89f2 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003392 | 058a3e9c-9e8f-4e7c-870b-e73c54b19584 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003393 | 235cb1c9-afe3-4473-9b92-aed9207015bd | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003394 | 2da1d6da-d1f7-477c-960e-d1a2ce5a0017 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003395 | 2da1d6da-d1f7-477c-960e-d1a2ce5a0017 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003396 | 2ae1676f-63c6-4a40-9904-e25da0d1b0fa | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003397 | 2ab9e32b-9493-435d-8d95-70dfc4cea9d1 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003398 | 288d7cf5-72d0-4a8a-b498-b907498bf1e2 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003399 | 46e6b5e9-9d10-4131-8293-7c3fe43bf102 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003400 | 49a7ba4d-a9db-4390-9487-d137c1547bb1 | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003401 | 3cf543fb-eae2-4ae0-8c10-7bd4ea8d2f8e | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003402 | 525d8013-1970-44a5-a9aa-4f035d0dc18a | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003403 | 525d8013-1970-44a5-a9aa-4f035d0dc18a | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003404 | 961008ef-e47f-4e7a-9870-6c85faf03dc9 | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003405 | 90a77652-3a3c-4609-bfb5-5f617833ddbf | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-04-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003406 | 925e20e7-963c-479e-a1d0-fafd268f2985 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003407 | 9179ed8d-1e32-4052-95f4-28e0c1bb3dd7 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003408 | 98c2009f-c06d-47a7-a1c4-00ef850b765b | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003409 | 98503488-1f55-4577-a752-9f6f6fc49644 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003410 | 98503488-1f55-4577-a752-9f6f6fc49644 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003411 | 9c54e1d8-aa2b-4cdd-9d0c-fd4ba4644a31 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003412 | 8628350b-f864-4b9b-98ef-fd6e5c826ab8 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003413 | 7d645ba5-465d-4d5d-9f47-671821481b96 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003414 | 507c3883-35cb-4499-8271-78d0c0f4a408 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003415 | 507c3883-35cb-4499-8271-78d0c0f4a408 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003416 | 507c3883-35cb-4499-8271-78d0c0f4a408 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003417 | 5bf22b51-d33a-4e79-be24-fbc93f32f9a4 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003418 | 6e1b75f8-9a82-49b3-8a63-78c956bd2ffc | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003419 | 3cf4a479-c430-4287-b53d-4ec56583ca0c | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2027-04-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120003420 | 3cf4a479-c430-4287-b53d-4ec56583ca0c | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003421 | 29011c9c-b920-463e-9002-34e6ba184976 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003422 | 2457b877-1e98-442d-b8f2-c191b5f3490d | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003423 | 05beac2a-acbe-489d-8238-ef8d3d75d1cc | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003424 | d0a15412-d3df-4a73-ad75-ed94c5657b4c | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003425 | a27326de-1893-4e01-8e46-c93c2c5e6d77 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003426 | a27326de-1893-4e01-8e46-c93c2c5e6d77 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003427 | bbbf976a-76db-4f53-9bdb-2d8e178f8161 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003428 | b65c2964-e18a-4996-a168-1615f5dd0e90 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003429 | c1fc8c9b-3d34-479e-a7e7-4fe3ff194c0a | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-04-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003430 | dd69da25-1a20-4887-a4e5-6061f4a435b9 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2027-04-24 | Level 2 | [8 empty] | LU | 2026 | 2
1120003431 | e4f3a2f1-6240-409d-90e5-f85e7ff5e13f | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003432 | 49556d8e-5ec5-42ed-a3bc-062ea31a91bf | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003433 | 6d56cb90-354f-4a72-892b-d6bacad50810 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003434 | 6491874d-e277-4ac3-ac66-15f62b0ffe14 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003435 | 6491874d-e277-4ac3-ac66-15f62b0ffe14 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003436 | 6491874d-e277-4ac3-ac66-15f62b0ffe14 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003437 | 5fdf5fd4-4027-4728-aacc-79ae83f290d5 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003438 | 5fdf5fd4-4027-4728-aacc-79ae83f290d5 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003439 | 5fdf5fd4-4027-4728-aacc-79ae83f290d5 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2027-04-24 | Level 2 | [8 empty] | LU | 2026 | 2
1120003440 | 7343984e-5cbb-44a6-a80f-68df46947911 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-04-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003441 | 7a85d9f3-9d2c-4021-9d94-85b324c09c27 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2027-04-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120003442 | 9919e319-ecdd-4062-b40d-684ef44c6bb6 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003443 | 5fc02464-6ed4-498b-861e-a5519fe33376 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003444 | 5fc02464-6ed4-498b-861e-a5519fe33376 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003445 | 5572a3e7-3416-4c95-815c-50c76f8cde17 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003446 | 6451b009-dc75-4685-83a5-b8f710a8fed2 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003447 | 6451b009-dc75-4685-83a5-b8f710a8fed2 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2027-04-27 | Level 2 | [8 empty] | LU | 2026 | 2
1120003448 | 6dc52f2b-6a09-4d85-9e5d-9f45fe043541 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003449 | 6d0a1bef-6ae1-48d6-ac04-4d87cd6e364d | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003450 | 6f13bb60-b4d5-4458-ace5-b96dea561f79 | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003451 | 33e6db0a-95a6-4bd9-9668-8f4f1cecd290 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003452 | ed8b03c7-fb82-4a82-bdf8-186e24876b03 | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003453 | b6df15b1-d7ec-4fd0-ade1-0cc1c7cc055b | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003454 | b354bb6a-336b-4151-bfdf-3b27d39b19ae | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003455 | b354bb6a-336b-4151-bfdf-3b27d39b19ae | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003456 | b354bb6a-336b-4151-bfdf-3b27d39b19ae | Pole | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003457 | abfe397d-8dd7-4ba2-8313-f55a0c4df78d | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003458 | fe00961b-b602-458b-9b0b-46516738a5cd | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-04-26 | Level 3 | [8 empty] | LU | 2026 | 2
1120003459 | aaa0800e-41f4-46f8-8abd-45ce639a4763 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003460 | f3f1a778-f3f8-4106-862d-82f222fb0223 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003461 | f19679cf-91e2-4d7c-8e77-9fb51650d323 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003462 | e61a4a30-5174-4ee9-b826-d14522c03151 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003463 | ced65380-49a2-4a2e-9d58-e08a487da98e | UG Transformer | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003464 | 2c2672c4-9b45-443c-9758-02017bf46637 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003465 | 393fca87-084c-4858-8e83-6b269d4a37de | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003466 | 393fca87-084c-4858-8e83-6b269d4a37de | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003467 | 41ca52d0-c83c-464c-bbda-92bf6a4e8551 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003468 | 60dad9fc-1bb7-4515-9a15-da7c909a0f97 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2027-04-28 | Level 2 | [8 empty] | LU | 2026 | 2
1120003469 | 9771ca6f-82fa-47d3-8f96-586f226f6325 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003470 | 96fb9572-a26a-43bc-a740-05eca41b7182 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-04-27 | Level 3 | [8 empty] | LU | 2026 | 2
1120003471 | 7f3d222e-19f8-4375-8d2c-6cab818e3142 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2027-04-28 | Level 2 | [8 empty] | LU | 2026 | 2
1120003472 | 86d55ebe-b83f-49f7-8d5a-bb08d0181027 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2027-04-28 | Level 2 | [8 empty] | LU | 2026 | 2
1120003473 | 86eee04f-d22f-42be-a46e-a9defaea26b7 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003474 | 8028f02e-62be-4306-b328-5a96686cb22e | Pole | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003475 | 74bce5c1-1e6e-4001-ba46-fe34f804e443 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003476 | 8fa8dc48-1cf0-4bbd-82ae-9e6d0636093f | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003477 | 8eabfa39-9980-4129-872b-33e79aae4056 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003478 | 43a325eb-a687-45bf-aabc-3ecd397987f5 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003479 | 056b77bd-1fe8-4f4d-b825-63a57b988083 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003480 | 08d8afb0-96c5-4dcb-a995-7471c00a89d7 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003481 | 07a83b4f-cfd5-4b39-bc4c-b56d6485677a | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003482 | 0ea126ea-e69c-4246-8446-b2aa8f06fc25 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003483 | 258ed5c5-d144-4beb-ba21-464bc5a86a2e | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003484 | 258ed5c5-d144-4beb-ba21-464bc5a86a2e | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003485 | 258ed5c5-d144-4beb-ba21-464bc5a86a2e | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003486 | 258ed5c5-d144-4beb-ba21-464bc5a86a2e | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003487 | 176d0d30-3760-4dee-8949-2f953f0679fa | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003488 | 15d8264b-b87c-4665-8e52-3172a24d71b1 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003489 | d2c37a62-3641-433c-b45a-2510593b75ff | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003490 | d2c37a62-3641-433c-b45a-2510593b75ff | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003491 | de71be26-4d5c-4b65-9e52-e1618bbee1f9 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003492 | e801c2cd-3270-435c-8b1f-eae825dc156e | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003493 | e13cfdff-5eee-45ab-a1e8-13413f5acdee | Pole | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003494 | e2a1784b-084f-4325-b061-b0cdb6d3131d | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003495 | ea689ca1-5f88-4837-8ac3-6ba037092831 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003496 | ab86db5c-ee6b-44ea-acc9-a3f7b477d595 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003497 | ad6a1012-93a2-4916-8e71-4311df020038 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003498 | aff0261c-2ae9-4bb9-b0c2-38f385215de9 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003499 | a3d9b12a-b265-479a-a6a5-ef119ca82dd2 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003500 | 9f0b38fe-399b-4cc0-8fe2-ad54d4151988 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003501 | 9f0b38fe-399b-4cc0-8fe2-ad54d4151988 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003502 | c8f45704-10c7-4de2-a5f6-da992993695a | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2027-04-29 | Level 2 | [8 empty] | LU | 2026 | 2
1120003503 | c8f45704-10c7-4de2-a5f6-da992993695a | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003504 | ca3e0a26-1eea-49b4-bcc3-3470fb1fb4d7 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003505 | f58ed45d-813a-44b2-8920-f45074b9b5cd | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003506 | f8b7b1a2-7f0c-4261-86e6-abe65ee387c8 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-04-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003507 | a4a5c875-8ca6-42c9-a512-b523df764230 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003508 | 1634e18b-f222-42e1-b7fa-adb5076c2343 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003509 | 02ea243c-e994-4d2a-85bb-f71b57515845 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003510 | 48cbb811-7b00-4a2b-9f65-d5bd8e449f67 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003511 | 4cb8d722-0155-496e-a184-31c18679f265 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003512 | 4dc55139-a709-4c9e-a586-a60a79d681c8 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003513 | 5bcf4825-d03e-43c4-aa62-262d8c7cf3e4 | Pole | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-04-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003514 | 5ed5dc63-6540-43cd-a992-e83f11d70f1a | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003515 | 6499309d-32af-4efd-8f55-e31f95f8857f | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003516 | 68bef8b8-2263-428f-84f1-fb6818f5e273 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003517 | 72fd6ee7-1057-401b-99f5-7ceb28a1596e | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003518 | 72fd6ee7-1057-401b-99f5-7ceb28a1596e | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003519 | 8b9261bd-52bc-4e05-94b2-e086fc03a58f | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003520 | 9138f4c7-b1ed-476f-8758-df9ca37a0740 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003521 | 892cb0e4-9cc8-4ea4-8237-555781be48ec | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003522 | 4830c007-1652-4cff-80df-a54a5546746b | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003523 | 40e56643-670a-407a-b6a2-e0b85dd48063 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003524 | 9fa096ce-7eb8-4c46-bc98-7adaa6d4178e | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003525 | afcc3422-cbe2-4afe-8f97-0574a5a44e89 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003526 | e70adf77-5032-461b-8fe3-c71232eb0944 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003527 | d4c3883e-7a45-4828-8a70-b477d37490c4 | Pole | HFTD Tier 2 | Distribution | 2026-05-01 | 2031-04-30 | Level 3 | [8 empty] | LU | 2026 | 2
1120003528 | d2587881-757a-405a-ba20-558a44112063 | Pole | HFTD Tier 3 | Distribution | 2026-05-05 | 2031-05-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003529 | db6179df-21bb-4270-90cd-3896d652b435 | Pole | HFTD Tier 3 | Distribution | 2026-05-05 | 2031-05-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003530 | 44e2cfed-8c57-4450-b736-b3a4c53c1bcf | Pole | HFTD Tier 3 | Distribution | 2026-05-05 | 2031-05-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003531 | 2190a921-5040-45a4-b6aa-b5f6c47989fe | Pole | HFTD Tier 3 | Distribution | 2026-05-05 | 2031-05-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003532 | 9834e0e9-0498-4171-9dae-ed28b601f96c | Pole | HFTD Tier 3 | Distribution | 2026-05-05 | 2031-05-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003533 | 663b96e7-da45-428c-9eb5-061093312bcd | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003534 | 0e6ca065-09d6-419e-8abc-c68ac24b8aeb | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003535 | b4b972cf-cab1-46cd-aa80-70648c683384 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003536 | f5c33f75-83f2-464b-8d3a-537997403946 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003537 | fa308327-a670-4ba1-91d7-1b98ddda5d2c | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003538 | fef9a6f2-b375-4685-ac65-2024647e8683 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003539 | fef9a6f2-b375-4685-ac65-2024647e8683 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-05-05 | Level 3 | [8 empty] | LU | 2026 | 2
1120003540 | fe9f69ac-f54a-469e-9aed-1b4a31acf235 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003541 | fe9f69ac-f54a-469e-9aed-1b4a31acf235 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003542 | ca327d33-4c72-4d95-b844-e08c6ef0ab68 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003543 | e025271d-168b-4438-8011-31475eb21a56 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003544 | 1596bca2-827a-42b3-a54d-f03543e455ad | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003545 | 18855d5c-aa41-4f72-8d30-d42e9f4be370 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003546 | 29b4f0b4-b363-4e7d-9e30-973724eca955 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003547 | 9964634d-2d83-454e-86ce-072150d35c7b | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003548 | 9964634d-2d83-454e-86ce-072150d35c7b | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003549 | 75bc2383-22a8-4b0f-94d5-dc7d2534bc27 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2026-11-03 | Level 2 | [8 empty] | LU | 2026 | 2
1120003550 | 75bc2383-22a8-4b0f-94d5-dc7d2534bc27 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-05-06 | Level 3 | [8 empty] | LU | 2026 | 2
1120003551 | 64f477eb-6b66-4636-b672-27618c57f0d7 | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003552 | 6f1c7336-04ae-4bec-9b09-25de961523f3 | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003553 | 6f2602c1-f26b-43bc-8df6-98de2795ae2d | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003554 | 6f4c3a33-fbe5-4f04-a814-aec97b361c3d | UG Transformer | HFTD Tier 2 | Distribution | 2026-05-08 | 2027-05-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120003555 | 2e00f399-9986-4d1d-b3ae-6b60f73e7b99 | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003556 | 4b58f3cc-01fc-4aa1-b12c-746090a4cee8 | UG Transformer | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003557 | e3621523-330e-4500-bdea-cf7ad24b4d0b | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003558 | ec0b3b36-86df-48a9-87bd-f1a6333bd9ab | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003559 | ec0b3b36-86df-48a9-87bd-f1a6333bd9ab | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003560 | cd7e103a-ac16-4115-b32e-0a338bc6510f | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003561 | c1cdb6e9-a1cc-4e7f-939a-71334b59e12e | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003562 | b7986f67-4d15-4563-8110-decb5aefc0f1 | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003563 | b76b37ca-0895-4bbe-8b9e-87f258239373 | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003564 | b76b37ca-0895-4bbe-8b9e-87f258239373 | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003565 | b76b37ca-0895-4bbe-8b9e-87f258239373 | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003566 | ac448e45-acc2-42bd-88d0-75d52d2bc9d8 | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003567 | f811c64c-a84b-4eb1-977f-dbe18df4c5fd | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-05-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003568 | 57aa1993-1196-4a0e-bcb2-0258331f7e8d | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-05-10 | Level 3 | [8 empty] | LU | 2026 | 2
1120003569 | 5fc5aa40-e5a2-4256-9b40-e17d762fe6b9 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003570 | 78b84beb-5535-4461-b432-6f2ecded748d | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003571 | 808138f2-6a66-4e11-9c1d-2b6840ebbf53 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003572 | 4a6ed4a5-b097-4115-918e-12371da9e572 | Pole | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003573 | 10c347cc-6f68-4898-bf99-4a1cca9918ea | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003574 | 10c347cc-6f68-4898-bf99-4a1cca9918ea | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003575 | f067df3e-2147-492c-bcf8-7e6b5f6b35b8 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003576 | f0f18e45-96d6-44c3-b654-6d876c672f33 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-05-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003577 | f1d7e5f9-91ed-432a-88d7-a64111a797a0 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003578 | c64afdc8-bc11-4b5c-be0f-1f0ebcd1f6cc | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003579 | 008b853e-71cf-4352-8e24-ca8298fc2241 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003580 | 008b853e-71cf-4352-8e24-ca8298fc2241 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003581 | 08bfced9-145b-4eae-80b2-b77d722c7577 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003582 | 165adb38-72dc-4776-b27c-cee490808d16 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003583 | 165adb38-72dc-4776-b27c-cee490808d16 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003584 | 4a4cb22c-6f98-4ce8-800e-ba4385d9bf25 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2027-05-13 | Level 2 | [8 empty] | LU | 2026 | 2
1120003585 | 277b6707-8a84-460f-beb8-8543aef2fa42 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003586 | 6c8ddbc8-506d-434f-ac15-61c8fc4695c8 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003587 | 6bc378f8-2be6-4f94-b98d-859a943551ec | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003588 | 65104381-0bb8-49fb-82be-f55b410989a2 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-05-12 | Level 3 | [8 empty] | LU | 2026 | 2
1120003589 | 6361f3a4-1cad-4929-9b48-78cf206b1b9d | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003590 | 4fecb113-0eb9-4761-b9ad-94671dfd291c | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003591 | 50a8367e-8b53-4c2b-919a-0b5024758437 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003592 | 8090833d-4896-4452-bcc4-efefa11f3588 | Pole | HFTD Tier 3 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003593 | 735a64df-67ef-4798-ab4a-6a32a26bf528 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003594 | 9b06985c-b97b-4722-98ad-b8f727af87a7 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003595 | 9db24c8c-c710-4e4b-8856-9f64ab1bf1e1 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003596 | 8d84e59f-5b75-4683-af5c-9a46034dea2c | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003597 | 28643aa4-b33e-4324-8c9e-4acc0de96e49 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003598 | 28643aa4-b33e-4324-8c9e-4acc0de96e49 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003599 | 294cfcd0-d79c-41f8-ada1-27ff92d2327c | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003600 | 2a210197-57bd-45c2-94bb-44a1c4ad101f | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003601 | 2bd0208e-6626-479e-91b3-26090e364fd4 | Pole | HFTD Tier 3 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003602 | 37ac9a00-19f4-494c-b240-db46651810f9 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003603 | 24d29c82-7201-4b2a-be70-847530ffb0af | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003604 | 118355d5-8349-4316-b14f-6476bb9100da | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003605 | 118355d5-8349-4316-b14f-6476bb9100da | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003606 | a7c4cba1-49ad-41b0-85cf-e708ae34feca | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003607 | ec0eae75-8cba-410d-8936-aae9f9e26fce | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003608 | cfd85aff-a971-4e29-9131-65bf33c99a1e | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2027-05-14 | Level 2 | [8 empty] | LU | 2026 | 2
1120003609 | f8071c8a-7ff0-4c2d-83cd-048aea81cc64 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003610 | f8071c8a-7ff0-4c2d-83cd-048aea81cc64 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-05-13 | Level 3 | [8 empty] | LU | 2026 | 2
1120003611 | d037b55a-ba29-40e0-a9e5-0e671b27bcf5 | Pole | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003612 | ee14ec79-1163-48a7-b510-32d7f394908d | Pole | HFTD Tier 2 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003613 | a4b4f54f-0c8c-4ec5-95af-b897eb91d643 | Pole | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003614 | 0edef941-65ab-4c2b-8604-1693469d1b88 | Pole | HFTD Tier 2 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003615 | 23029300-21df-4044-a1c0-e89c072f24f3 | Pole | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003616 | 2a38c170-b608-4677-9eaf-dfa090cc9c70 | Pole | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-05-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003617 | 32a41a3d-429b-4ecb-a51f-0ebcb521243d | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003618 | 0c5600c8-a6f8-4e7e-891c-f2aca8075324 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003619 | 9b8e95aa-d6b6-46fd-86c8-cb1f87937fb6 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003620 | 97e140ce-7451-4b98-92c7-fdce6ee640a0 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003621 | 8573aa22-307c-40f6-80a0-6832827b14f2 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003622 | f92f93cd-26ff-432e-af96-0685a275d544 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003623 | f92f93cd-26ff-432e-af96-0685a275d544 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-05-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003624 | b78d6e2d-d0fd-4537-8ded-ac91b7ae25af | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003625 | ec14fa7e-0aeb-4bc5-a16a-032ba15ee232 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003626 | e080689b-4234-47fd-8eba-c4481081f1aa | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003627 | 74eb4baa-0488-4353-af65-fa453c7a364c | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003628 | 7738951f-0d55-4067-917d-9c37054f7c76 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003629 | 98f7ca22-100e-4348-a5e3-d008475eaa6b | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003630 | 95db3ba0-b0a1-49e5-b855-6f67124ac04d | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003631 | 5da65cc2-3a2b-412b-9adb-0baeef19a6b2 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003632 | 5da65cc2-3a2b-412b-9adb-0baeef19a6b2 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003633 | 5da65cc2-3a2b-412b-9adb-0baeef19a6b2 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003634 | 6bf37c60-b054-4dcf-b3b3-c9991e9b3c37 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003635 | 6bf37c60-b054-4dcf-b3b3-c9991e9b3c37 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003636 | 0c3e9d3c-14ad-406e-b913-c8d8803128e6 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003637 | 1e91f33c-4dc7-4bc4-a3cd-519ccc8b5f8f | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003638 | 1aeae991-25a8-4ed0-857b-79060600ab09 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-05-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003639 | 08f291b6-eb43-49eb-a09f-d0afc4162fc9 | Pole | Non-HFTD | Distribution | 2026-05-20 | 2031-05-19 | Level 3 | [8 empty] | LU | 2026 | 2
1120003640 | 7ffdbf49-932a-4f36-97e4-97d3b1bb0410 | Pole | Non-HFTD | Distribution | 2026-05-20 | 2027-05-20 | Level 2 | [8 empty] | LU | 2026 | 2
1120003641 | 9071f0b2-5a4d-467d-8267-8afdb332feef | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003642 | 5a0b469d-5411-4e7f-9001-a663178489a9 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003643 | 4d17e1b8-6525-48db-9ed9-77a26be0312c | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2027-05-22 | Level 2 | [8 empty] | LU | 2026 | 2
1120003644 | 13cfdc2b-ed95-4a15-b17a-6f2d7d3b5bb9 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003645 | b7ea2d1a-e9f0-49b0-9998-8cafc2c9c779 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003646 | beaa0489-0b97-457f-967f-831b26981929 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003647 | a93b7748-622d-460f-90b6-7588d112359c | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003648 | f3d146e8-a23d-4f83-8d65-421f300a0d02 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-05-21 | Level 3 | [8 empty] | LU | 2026 | 2
1120003649 | fc30c6d3-82b5-48ec-959d-8c084f05a6a3 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003650 | a8f94d51-1f39-4945-adb4-1173ac063483 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003651 | b42487ce-477f-4269-8672-04f3e928f40d | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003652 | 17c65fbf-f0d3-4230-a806-7074d4dd3131 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003653 | 0490e346-46bf-46d9-b170-dbac3c7f48fb | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003654 | 099d6750-1d47-4264-bf01-db845e519c2f | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003655 | 364b4b52-d1ca-4487-b1df-31066d70cab2 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003656 | 939576cf-cd76-441d-ae11-09b0b3a675f1 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2027-05-29 | Level 2 | [8 empty] | LU | 2026 | 2
1120003657 | 939576cf-cd76-441d-ae11-09b0b3a675f1 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003658 | 7e9723fa-6e18-4636-9b41-64d4c8e956af | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003659 | 7f2522e7-6243-4559-ad07-f9b32f72ba72 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003660 | 7f2522e7-6243-4559-ad07-f9b32f72ba72 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-05-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003661 | 54584257-63bf-4dc5-8cc4-f533693bbbb5 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003662 | 66cefa32-745b-4a60-82c9-20bb196a9435 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003663 | 445ef60d-768a-4a0d-9eef-1b08afcabad2 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003664 | 47dcdeab-b9f7-4111-9f7b-a26a926355de | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2027-06-01 | Level 2 | [8 empty] | LU | 2026 | 2
1120003665 | a1f12dff-a5b1-44a1-8908-1b1f6f3d8c2a | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003666 | c1ba3fab-e5d7-4906-8dc1-68658919e8dc | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003667 | e4c9e60f-f037-4fd6-aa73-b741ac290576 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003668 | e6b7d90c-f89f-45dc-92c1-d1ffac6143cf | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003669 | e964d996-b55c-41f1-b557-91d1e2c12806 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-05-31 | Level 3 | [8 empty] | LU | 2026 | 2
1120003670 | a0cbb660-4883-4958-881a-3d5ab683f8f5 | Pole | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-06-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003671 | 71616dd2-7c5e-4ce7-9dfd-b9a29125ae3e | Pole | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-06-01 | Level 3 | [8 empty] | LU | 2026 | 2
1120003672 | 86741aa8-2ca2-422f-8057-0243c7813b54 | Pole | HFTD Tier 2 | Distribution | 2026-06-02 | 2027-06-02 | Level 2 | [8 empty] | LU | 2026 | 2
1120003673 | 7b939a1b-9b63-4862-90dc-a924082a3a70 | Pole | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-06-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003674 | 5cae375c-434d-4fee-ac35-f742dbc4b1be | Pole | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-06-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003675 | 5dd8eeb5-01b2-4cd4-9153-dfb599720035 | Pole | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-06-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003676 | e91dbf32-0062-4c8f-8977-53d24aa08a78 | Pole | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-06-04 | Level 3 | [8 empty] | LU | 2026 | 2
1120003677 | 4e6d76ba-90e4-4e52-b59d-c44e0ec2d840 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2027-06-08 | Level 2 | [8 empty] | LU | 2026 | 2
1120003678 | 9993b690-bf74-427c-8ad7-fed9633dbff0 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-06-07 | Level 3 | [8 empty] | LU | 2026 | 2
1120003679 | 97b3f1dd-a361-4821-bed3-f880d2826b99 | Pole | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-06-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003680 | 83fcb6b0-f108-4ef0-b285-35d050be9832 | Pole | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-06-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003681 | 65927b5f-f5c2-44fc-8ae5-15b240fea88e | Pole | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-06-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003682 | c475ad69-4e5e-4eb9-9fbd-fadee900779c | Pole | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-06-08 | Level 3 | [8 empty] | LU | 2026 | 2
1120003683 | d3fb54ae-ba62-4905-8e5c-373b7e611deb | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-06-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120003684 | 6bd9ae89-86ec-42dc-bd0a-2323c2ae0c3e | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2027-06-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120003685 | 5e9f2bff-70e3-4e09-a0f9-727d3d2d76ec | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-06-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120003686 | 8ab6b3ce-a2b5-4522-9b1d-6869a24d460a | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-06-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120003687 | 1f143ff5-fba4-473b-9b39-7ca010f80c8f | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-06-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120003688 | 1f143ff5-fba4-473b-9b39-7ca010f80c8f | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-06-09 | Level 3 | [8 empty] | LU | 2026 | 2
1120003689 | 224e489e-4d0a-4930-be29-a97ff52b4bca | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2027-06-10 | Level 2 | [8 empty] | LU | 2026 | 2
1120003690 | 26c744fb-d896-43a2-9622-279e68718579 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2027-06-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120003691 | 26c744fb-d896-43a2-9622-279e68718579 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003692 | 26c744fb-d896-43a2-9622-279e68718579 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003693 | 983fe981-1b30-4f8c-95c2-c4cc1d001d17 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2027-06-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120003694 | 983fe981-1b30-4f8c-95c2-c4cc1d001d17 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003695 | 983fe981-1b30-4f8c-95c2-c4cc1d001d17 | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003696 | 60d74ab0-e93f-46de-a3ce-d5c4dcea9f7f | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003697 | 60d74ab0-e93f-46de-a3ce-d5c4dcea9f7f | Pole | Non-HFTD | Distribution | 2026-06-12 | 2027-06-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120003698 | 60d74ab0-e93f-46de-a3ce-d5c4dcea9f7f | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003699 | f3303fad-f942-4d8a-b90b-a60c84cc700a | Pole | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003700 | f3303fad-f942-4d8a-b90b-a60c84cc700a | Pole | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003701 | a279321f-7b21-4eae-82ff-11bd087dabec | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003702 | a279321f-7b21-4eae-82ff-11bd087dabec | Pole | Non-HFTD | Distribution | 2026-06-12 | 2031-06-11 | Level 3 | [8 empty] | LU | 2026 | 2
1120003703 | a279321f-7b21-4eae-82ff-11bd087dabec | Pole | Non-HFTD | Distribution | 2026-06-12 | 2027-06-12 | Level 2 | [8 empty] | LU | 2026 | 2
1120003704 | 3813c8ff-b484-45a7-821b-e4cc5c866280 | Pole | HFTD Tier 2 | Distribution | 2026-06-15 | 2031-06-14 | Level 3 | [8 empty] | LU | 2026 | 2
1120003705 | 129e9dd4-508c-4322-b7cb-2c012ef093be | Pole | HFTD Tier 2 | Distribution | 2026-06-15 | 2027-06-15 | Level 2 | [8 empty] | LU | 2026 | 2
1120003706 | 22ae9cf3-6d7d-48f8-add9-c51a6de4e5e3 | Pole | Non-HFTD | Distribution | 2026-06-16 | 2031-06-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003707 | 45bd1dcd-90b1-43d7-a58f-45b4ebd77848 | Pole | Non-HFTD | Distribution | 2026-06-16 | 2031-06-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003708 | 8ca31df1-9eaf-453f-95da-df3bb4f9b651 | Pole | Non-HFTD | Distribution | 2026-06-16 | 2031-06-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003709 | 8ca31df1-9eaf-453f-95da-df3bb4f9b651 | Pole | Non-HFTD | Distribution | 2026-06-16 | 2031-06-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003710 | a39b17cf-89ad-4971-ba36-ca9cfefb7684 | Pole | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-06-15 | Level 3 | [8 empty] | LU | 2026 | 2
1120003711 | caa7d7c1-f669-4da5-ad12-6f24c24ede83 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003712 | e8ed90ac-82f2-46d8-9db3-772767c90dc9 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003713 | d455dbb6-9893-4b35-8dfd-fe6d023fa8cb | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003714 | d455dbb6-9893-4b35-8dfd-fe6d023fa8cb | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003715 | f6039501-9cf0-4217-8ef5-3f73ab8bff72 | Pole | HFTD Tier 3 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003716 | f68d0c5d-3817-48c0-9e9a-8780e23fa653 | Pole | HFTD Tier 3 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003717 | f68d0c5d-3817-48c0-9e9a-8780e23fa653 | Pole | HFTD Tier 3 | Distribution | 2026-06-17 | 2031-06-16 | Level 3 | [8 empty] | LU | 2026 | 2
1120003718 | e853b2e5-b395-4256-b463-376411eeef9d | Pole | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-06-17 | Level 3 | [8 empty] | LU | 2026 | 2
1120003719 | 2b6c63af-3ceb-4edc-9499-1ea3c845772e | Pole | HFTD Tier 3 | Distribution | 2026-06-18 | 2026-12-15 | Level 2 | [8 empty] | LU | 2026 | 2
1120003720 | 1000c106-955a-4cbf-84af-111ebf91d2f9 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-06-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003721 | 017041a0-cee9-4c98-ba3d-756a5e68ba6f | Pole | HFTD Tier 3 | Distribution | 2026-06-19 | 2031-06-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003722 | 8913b9dc-d463-4e2c-bd5a-b2969f9eadbc | Pole | HFTD Tier 3 | Distribution | 2026-06-19 | 2031-06-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003723 | 730bd819-4de6-4bdc-8f23-58959168a2cd | Pole | HFTD Tier 3 | Distribution | 2026-06-19 | 2031-06-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003724 | cce2fbf5-8bbc-44a0-a5d9-0d6b832bfc6e | Pole | HFTD Tier 3 | Distribution | 2026-06-19 | 2031-06-18 | Level 3 | [8 empty] | LU | 2026 | 2
1120003725 | 1ccd0150-33a4-4b94-9736-baa85bf477d3 | Pole | HFTD Tier 2 | Distribution | 2026-06-22 | 2027-06-22 | Level 2 | [8 empty] | LU | 2026 | 2
1120003726 | 794554f2-f368-443f-9443-da1d7d0abbce | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003727 | e37e57a8-6d89-4f3d-804d-bd116dade914 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003728 | ac650801-b126-41ed-bcbc-0ef837f05c31 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003729 | abd30dc8-77b4-4260-b26c-f56893f60661 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-23 | 2027-06-23 | Level 2 | [8 empty] | LU | 2026 | 2
1120003730 | abd30dc8-77b4-4260-b26c-f56893f60661 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-06-22 | Level 3 | [8 empty] | LU | 2026 | 2
1120003731 | f5d90a6e-4dcf-49e8-9b08-be12fced6798 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-06-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003732 | 188f2cea-c32d-4778-8cc9-b6df02489944 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-06-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003733 | 188f2cea-c32d-4778-8cc9-b6df02489944 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-06-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003734 | 0c2dd7ae-5a82-4bac-984d-028c0166df74 | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-06-23 | Level 3 | [8 empty] | LU | 2026 | 2
1120003735 | 1d07cecc-fa82-4a68-9390-537e1ff53860 | Pole | HFTD Tier 3 | Distribution | 2026-06-25 | 2031-06-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003736 | 1d07cecc-fa82-4a68-9390-537e1ff53860 | Pole | HFTD Tier 3 | Distribution | 2026-06-25 | 2026-12-22 | Level 2 | [8 empty] | LU | 2026 | 2
1120003737 | 6ff5f1e5-197b-49ea-ac58-2ad27160c1ab | Pole | HFTD Tier 2 | Distribution | 2026-06-25 | 2031-06-24 | Level 3 | [8 empty] | LU | 2026 | 2
1120003738 | d65cadf1-017a-4861-8ad3-f7c9ce24ac06 | Pole | HFTD Tier 2 | Distribution | 2026-06-25 | 2027-06-25 | Level 2 | [8 empty] | LU | 2026 | 2
1120003739 | cde01937-8986-4fea-9d6d-4ec6b87b276f | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003740 | cde01937-8986-4fea-9d6d-4ec6b87b276f | UG Transformer | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003741 | 7a7ce6b0-42ba-48a1-b404-6b6fff4d6071 | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003742 | 8f8fbb6d-20c8-40ef-a9ff-5334594d73be | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003743 | 1f2b6825-b553-4b5e-9811-3af9d10554f4 | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003744 | 1f2b6825-b553-4b5e-9811-3af9d10554f4 | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003745 | 1f2b6825-b553-4b5e-9811-3af9d10554f4 | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003746 | 0bd23199-6476-4c61-8d14-fbbd8f527f57 | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003747 | 2e72df23-372e-49bb-98f6-e4f4e474644e | Pole | HFTD Tier 2 | Distribution | 2026-06-29 | 2031-06-28 | Level 3 | [8 empty] | LU | 2026 | 2
1120003748 | a165ad08-a54b-44a2-a304-9fff5bcd78e2 | Pole | HFTD Tier 3 | Distribution | 2026-06-30 | 2031-06-29 | Level 3 | [8 empty] | LU | 2026 | 2
1120003749 | a165ad08-a54b-44a2-a304-9fff5bcd78e2 | Pole | HFTD Tier 3 | Distribution | 2026-06-30 | 2026-12-27 | Level 2 | [8 empty] | LU | 2026 | 2