## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | SCE
Report Year |  | 2020
Report Quarter |  | Q4
Submission Date |  | 2021-04-01
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1W1:Y20W1:Y18W1:Y20Z27W1:Y21 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 | N/A | N/A | SCE_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _N/A_2021 | 100 | N/A
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | Climate-driven risk map and modelling based on various relevant weather scenarios |  | 2 | N/A | N/A | SCE_Risk Assessment & Mapping_Climate-driven risk map and modelling based on various relevant weather scenarios _N/A_2021 | 100 | N/A
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | 3 | N/A | N/A | SCE_Risk Assessment & Mapping_Ignition probability mapping showing the probability of ignition along the electric lines and equipment _N/A_2021 | 100 | N/A
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | 4 | N/A | N/A | SCE_Risk Assessment & Mapping_Initiative mapping and estimation of wildfire and PSPS risk-reduction impact _N/A_2021 | 100 | N/A
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | 5 | N/A | N/A | SCE_Risk Assessment & Mapping_Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment _N/A_2021 | 101 | N/A
SCE | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. |  | Weather-driven risk map and modelling based on various relevant weather scenarios | 6 | N/A | N/A | SCE_Risk Assessment & Mapping_x_N/A_2021 | 101 | N/A
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Advanced weather monitoring and weather stations |  | 1 | Weather Stations | SA-1 | SCE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _SA-1_2021 | 104 | # of weather stations installed | Install 375 Weather Stations. SCE will strive for installation of 475 Weather Stations subject to resource constraints and other execution risks |  |  |  | 375 |  |  |  | ~590 of 375 weather stations installed. Exceeded WMP Program target and exceeded the strive target of 475 installations. | [5 empty] | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors |  | 2 | Transmission Open Phase Detection | SH-8 | SCE_Situational Awareness & Forecasting_Continuous monitoring sensors _SH-8_2021 | 106 | N/A | [9 empty] | Continue deployment of transmission open phase detection on six additional transmission/subtransmission circuits |  |  |  | All six circuits are in service and are under observation. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors |  | 2 | Distribution Fault Anticipation (DFA) | AT-2.1 | SCE_Situational Awareness & Forecasting_Continuous monitoring sensors _AT-2.1_2021 | 106 | N/A | [9 empty] | Evaluate technology performance on fault anticipation technology and future deployment |  |  |  | An evaluation report of the performance of the 60 installed Distribution Fault Anticipation (DFA) units was completed in Q4. SCE also developed a 2021 deployment plan for additional DFA units. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors |  | 2 | Early Fault Detection (EFD) Evaluation | AT-7 | SCE_Situational Awareness & Forecasting_Continuous monitoring sensors _AT-7_2021 | 106 | N/A | [9 empty] | Develop installation standards, install, and commission at least 10 EFD sensors. Gather data to determine requirements to support the potential for larger system deployments. SCE will strive to complete an additional 90 sensors for evaluation subject to resource constraints and other execution risks |  |  |  | Team developed installation standards and completed field installation of 33 EFD units. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Fault indicators for detecting faults on electric lines and equipment |  | 3 | N/A | N/A | SCE_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _N/A_2021 | 107 | N/A
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fire Potential Index (FPI) Phase II | SA-2 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-2_2021 | 107 | N/A | [9 empty] | Refine the current FPI by integrating historical weather and vegetation data into the index |  |  |  | Completed development of FPI 2.0 which factors in different fuel types (e.g. grass, timber, or brush) and historical weather data. Historical weather data was received in Q2. New fuel loading map and FPI 2.0 formulas were completed in Q4 | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fuel Sampling Program | SA-5 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-5_2021 | 108 | N/A | [9 empty] | Perform updated fuel sampling in HFRA in areas deemed appropriate once every two weeks (weather permitting) |  |  |  | Initiated fuel sampling in all four regions specified in the WMP (Inland Empire, North LA County, Eastern Sierra, Western Sierra). Fuel sampling continued in all four regions through year-end. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Surface and Canopy Fuels Mapping | SA-6 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-6_2021 | 108 | N/A | [9 empty] | Initiate surface and canopy fuels mapping across HFRA |  |  |  | Vendor began work to refresh the fuels/surface canopy dataset in SCE territory in Q4. The program will improve fire spread modeling capabilities. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Remote Sensing / Satellite Fuel Moisture | SA-7 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-7_2021 | 109 | N/A | [9 empty] | Initiate procurement process for remote sensing technology for future implementation |  |  |  | Procurement was initiated for a wind profiling pilot using LiDAR in the lower atmosphere of the Eastern Sierra. Contract was in the close to finalization by the end of 2020. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fire Science Enhancements | SA-8 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-8_2021 | 109 | N/A | [9 empty] | Implement enhanced forecasting capability and improved fuel modeling |  |  |  | Ensemble forecasting was implemented in Q3 and will increase the frequency of modeling to receive a range of outputs for forecasting. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 | N/A | N/A | SCE_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _N/A_2021 | 110 | N/A
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Weather forecasting and estimating impacts on electric lines and equipment |  | 6 | High-Performing Computer Cluster (HPCC) Weather Modeling System | SA-3 | SCE_Situational Awareness & Forecasting_Weather forecasting and estimating impacts on electric lines and equipment _SA-3_2021 | 110 | N/A | [9 empty] | Complete installation of second HPCC |  |  |  | Completed the installation of second HPCC weather modeling system—It is in operational use. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. |  | Asset and Reliability & Risk Analytics Capability | 7 | Expansion of Risk Analysis & Risk Analytics Capability | RA-1 | SCE_Situational Awareness & Forecasting_x_RA-1_2021 | 111 | N/A | [9 empty] | Implement Wildfire Risk Reduction Model (WRRM) module of Technosylva (software platform) |  |  |  | Technosylva delivered the WRRM software to SCE in Q4 2020. Following its quality review of the data and functionality of the WRRM software, SCE deemed that it met its requirements.SCE will continueworking with Technosylva to incorporate enhancements throughout 2021. | Complete
SCE | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. |  | Asset and Reliability & Risk Analytics Capability | 7 | Asset Reliability & Risk Analytics Capability | SA-4 | SCE_Situational Awareness & Forecasting_x_SA-4_2021 | 111 | N/A | [9 empty] | Implement FireCastand FireSimmodules of Technosylva |  |  |  | Completed implementation of FireCastand FireSimapplications and fire scientist training. Performed fire simulations in Q4. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Capacitor maintenance and replacement program |  | 1 | N/A | N/A | SCE_Grid Design & System Hardening_Capacitor maintenance and replacement program _N/A_2021 | 114 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Circuit Breaker Relay Hardware for Fast Curve | SH-6 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _SH-6_2021 | 118 | # of installations and place into service | Replace/upgrade 55 relay units in HFRA. SCE will strive to replace up to 110 relay units in HFRA. These targets are subject to resource constraints and other execution risks. |  |  |  | 55 |  |  |  | ~92 of 55 fast curve relay setting installed and placed into service* (see comment) | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Alternative Technology Pilots – Meter Alarming for Down Energized Conductor (MADEC) | AT-1 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-1_2021 | 115 | N/A | [9 empty] | Evaluating algorithm improvements specific to the detection of downed energized covered conductor, which may behave differently than bare conductor |  |  |  | SCE collected and analyzed meter alarm data to build an event database to enhance the MADEC algorithm. As of year-end, there were no meter alarms specific to downed, energized covered conductor to enhance the algorithm for this type of event. SCE anticipates it may take several years to collect enough datapoints for thorough analysis. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter - Ground Fault Neutralizer (GFN) | AT-3.1 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-3.1_2021 | 115 | N/A | [9 empty] | Initiate engineering design and order equipment for a GFN field installation |  |  |  | Final substation engineering and design for Ground Fault Neutralizers was released in December with construction scheduled to begin in Q1 2021. GFN equipment was received ahead of schedule in 2020. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter – Resonant Grounding with Arc Suppression Coil | AT-3.2 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-3.2_2021 | 116 | N/A | [9 empty] | Initiate engineering design to convert a typical substation to resonant grounding |  |  |  | Final substation engineering and design for resonant grounded substation was released in December with construction scheduled to begin in Q2 2021. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter - Isolation Transformer | AT-3.3 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-3.3_2021 | 116 | N/A | [9 empty] | Install one Rapid Earth Fault Current Limiter -Isolation Transformer |  |  |  | The Rapid Earth Fault Current Limiter -Isolation Transformer was successfully tested and commissioned in Q4. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Alternative Technology Evaluations – Distribution Open Phase Detection | AT-3.4 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-3.4_2021 | 117 | N/A | [9 empty] | Complete pilot installation for five circuit locations |  |  |  | Distribution open phase detection logic has been deployed at five pilot locations as of mid-Q3. These locations have been in-serviced and are now in observation mode for alarming to validate and test the logic. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | High Impedance Relay Evaluations | AT-8 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _AT-8_2021 | 117 | N/A | [9 empty] | Investigate and deploy two controllers/relays with a High Impedance (Hi-Z) element in HFRA |  |  |  | SCE installed high impedance elements at two distribution pilot locations in Q3. SCE is monitoring these installations in “alarm” mode to validate that the alarm logic is working as expected. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation |  | 3 | Covered Conductor | SH-1 | SCE_Grid Design & System Hardening_Covered conductor installation _SH-1_2021 | 118 | # of circuit miles in HFRA | Install 700 circuit miles of covered conductor in HFRA. While 700 circuit miles is SCE’s program target, SCE will strive to complete 1,000 circuit miles subject to resource constraints and other execution risks. |  |  |  | 700 |  |  |  | ~960 of 700 circuit miles installed. | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation |  | 3 | Tree Attachment Remediation | SH-10 | SCE_Grid Design & System Hardening_Covered conductor installation _SH-10_2021 | 120 | # of tree attachment remediations | Remediate 325 tree attachments. SCE will strive to complete 481 tree attachment remediations subject to resource constraints and other execution risks |  |  |  | 325 |  |  |  | ~400 tree attachments were remediated in 2020, exceeding the WMP target. The majority, 369, of these tree attachments were scoped for future years (e.g., 2021) but were removed as a result of wildfires in the second half of the year. Documentation for this methodology and rationale was captured in the 2021 WMP Update to the WSD. | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation |  | 3 | Alternative Technology Implementation – Vibration Dampers | AT-4 | SCE_Grid Design & System Hardening_Covered conductor installation _AT-4_2021 | 120 | N/A | [9 empty] | Evaluate damper technologies for both small and large diameter covered conductor applications and develop standards for small and large diameter covered conductors |  |  |  | completed the evaluation of damper technologies and published new standards incorporating vibration damper applications for both large and small diameter covered conductor in Q4. SCE’s analysis validated that dampers help prevent conductor strain. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor maintenance |  | 4 | N/A | N/A | SCE_Grid Design & System Hardening_Covered conductor maintenance _N/A_2021 | 121 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Crossarm maintenance, repair, and replacement |  | 5 | N/A | N/A | SCE_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement _N/A_2021 | 121 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Fire Resistant Poles | SH-3 | SCE_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _SH-3_2021 | 121 | # of poles in HFRA | Replace 5,200 poles with fire resistant poles in HFRA. SCE will strive to replace 11,700 poles with fire resistant poles in HFRA subject to pole loading assessment results, resource constraints and other execution risks |  |  |  | 5200 |  |  |  | ~6,090 of 5,200 poles installed. | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Expulsion fuse replacement |  | 7 | Branch Line Protection Strategy | SH-4 | SCE_Grid Design & System Hardening_Expulsion fuse replacement _SH-4_2021 | 123 | # of locations with installed / replaced fuses | Install/replace fuses at 3,025 locations |  |  |  | 3025 |  |  |  | 3,025 of 3,025 locations installed/replaced fuses. | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | PSPS-Driven Grid Hardening Work | SH-7 | SCE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _SH-7_2021 | 123 | N/A | [9 empty] | Review 50% of all distribution circuits within HFRA to determine if modifications may improve sectionalizing capability within HFRA |  |  |  | Review of all 550 in-scope distribution HFRA circuits was completed, and sectionalization and other grid-hardening (e.g. covered conductor) modifications were proposed. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | Microgrid Assessment | PSPS-8 | SCE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _PSPS-8_2021 | 124 | N/A | [9 empty] | 1) Execute requests for proposals (RFP) for six resiliency microgrid projects, 2) Depending on RFP results, implementation of up to 6 resiliency microgrid projects shown to be technically feasible and cost-effective. |  |  |  | The 2020 program target of issuing an RFP for six potential 2020 microgrid projects was completed. However, this RFP did not yield any cost-effective options. Learning from this experience, SCE evaluated alternative microgrid sites that could be safely and more economically islanded and issued a second microgrid RFP. SCE received a higher response rate than the RFP issued earlier in 2020, evaluated the submissions, and recommended proceeding with one vendor for a potential 2022 deployment. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Installation of system automation equipment |  | 9 | Installation of System Automation Equipment - RAR / RCS | SH-5 | SCE_Grid Design & System Hardening_Installation of system automation equipment _SH-5_2021 | 125 | # of RARs / RCSs installed and operationalized | Install 45 RARs/RCSs |  |  |  | 45 |  |  |  | 48 of 45 RARs/RCSs installed and operationalized* (see comment) | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Maintenance, repair, and replacement of connectors, including hotline clamps |  | 10 | N/A | N/A | SCE_Grid Design & System Hardening_Maintenance, repair, and replacement of connectors, including hotline clamps _N/A_2021 | 126 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | N/A | N/A | SCE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event _N/A_2021 | 126 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Other corrective action |  | 12 | Remediations - Distribution | SH-12.1 | SCE_Grid Design & System Hardening_Other corrective action _SH-12.1_2021 | 127 | % of notifications remediated | Remediate 100% of notifications with ignition risk in accordance with CPUC requirements, non-inclusive of notifications which meet the criteria of a valid exception |  |  |  | 100% |  |  |  | As of the end of December, Distribution Remediation finished at 97% complete, missing the WMP Program target of 100%. Prior to year-end Distribution Remediations were at risk of not meeting the goal due to resource diversion to restoration efforts from catastrophic fires and other precautions taken due to record dry fuel conditions. COVID related restrictions on outages, and PSPS activations also continually delayed and slowed work throughout the year. | [5 empty] | Behind Plan, Substantially Complete | Detailed line-by-line analysis of the outstanding 2020 notifications is being conducted to help all Regions clear remaining obstacles to completion
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Other corrective action |  | 12 | Remediations - Transmission | SH-12.2 | SCE_Grid Design & System Hardening_Other corrective action _SH-12.2_2021 | 128 | % of notifications remediated | Remediate 100% of notifications with ignition risk in accordance with CPUC requirements, non-inclusive of notifications which meet the criteria of a valid exception |  |  |  | 100% |  |  |  | As of the end of December, Transmission Remediation finished at 95% complete, missing the WMP Program target of 100%. Prior to year-end Transmission Remediations were at risk of not meeting the goal due to resource diversion to restoration efforts from catastrophic fires and other precautions taken due to record dry fuel conditions. COVID related restrictions on outages also continually delayed and slowed work throughout the year | [5 empty] | Behind Plan, Substantially Complete | Line-by-line analysis of the outstanding 2020 notifications is being done to help all Regions clear remaining obstacles to completion.
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Other corrective action |  | 12 | Remediations - Generation | SH-12.3 | SCE_Grid Design & System Hardening_Other corrective action _SH-12.3_2021 | 129 | % of notifications remediated | Remediate 100% of notifications with ignition risk in accordance with CPUC requirements, non-inclusive of notifications which meet the criteria of a valid exception |  |  |  | 100% |  |  |  | Remediated 100% of generation notifications with ignition risk in accordance with CPUC requirements | [5 empty] | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  | 13 | N/A | N/A | SCE_Grid Design & System Hardening_Pole loading infrastructure hardening and replacement program based on pole loading assessment program _N/A_2021 | 130 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Transformers maintenance and replacement |  | 14 | N/A | N/A | SCE_Grid Design & System Hardening_Transformers maintenance and replacement _N/A_2021 | 130 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Transmission tower maintenance and replacement |  | 15 | N/A | N/A | SCE_Grid Design & System Hardening_Transmission tower maintenance and replacement _N/A_2021 | 130 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Undergrounding of electric lines and/or equipment |  | 16 | Undergrounding Overhead Conductor | SH-2 | SCE_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _SH-2_2021 | 130 | N/A | [9 empty] | Refine evaluation methodology for targeted undergrounding as a wildfire mitigation activity |  |  |  | Team refined targeted undergrounding methodology and began scoping work for 2021. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | N/A | N/A | SCE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs _N/A_2021 | 131 | N/A
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. |  | TOH Review | 18 | Transmission Overhead Standards (TOH) Review | SH-9 | SCE_Grid Design & System Hardening_x_SH-9_2021 | 132 | N/A | [9 empty] | Review transmission standards to determine if there are any changes that can be made to help reduce wildfire threats, especially during extreme wind events |  |  |  | Completed review of historical transmission outage data and identified several recommended updates for TOH standards that will be adopted in 2021. | Complete
SCE | 2021-04-01 | Grid Design & System Hardening | 5.3.3. |  | Legacy Facilities | 19 | Legacy Facilities | SH-11 | SCE_Grid Design & System Hardening_x_SH-11_2021 | 132 | N/A | [9 empty] | Evaluate risk, scope, and alternatives for identified circuits; evaluation of additional system hardening mitigation for wildlife fault protection and grounding/lightning arresters |  |  |  | Risk evaluations on hydro control circuits and grounding study reports on two high priority sites were completed in December. Risk evaluations for low voltage sites were completed in November. Wildlife risk evaluation was completed in July. | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Detailed inspections of distribution electric lines and equipment |  | 1 | N/A | N/A | SCE_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _N/A_2021 | 135 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | N/A | N/A | SCE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _N/A_2021 | 136 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Improvement of inspections |  | 3 | N/A | N/A | SCE_Asset Management & Inspections_Improvement of inspections _N/A_2021 | 137 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Infrared inspections of distribution electric lines and equipment |  | 4 | Infrared Inspection of Energized Overhead Distribution Facilities and Equipment | IN-3 | SCE_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _IN-3_2021 | 137 | % of distribution circuit miles in HFRA | Inspect 50% of distribution circuits in HFRA |  |  |  | 50% |  |  |  | Completed goal of inspecting 50% of distribution circuit miles in HFRA in Q4. | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Infrared inspections of transmission electric lines and equipment |  | 5 | Infrared Inspection, Corona Scanning, and High-Definition Imagery of Energized Overhead Transmission facilitites and Equipment | IN-4 | SCE_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _IN-4_2021 | 138 | # of transmission circuit miles in HFRA | Inspect 1,000 transmission circuit miles in HFRA |  |  |  | 1000 |  |  |  | 1,000+ circuit miles inspected in HFRA. | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Intrusive pole inspections |  | 6 | N/A | N/A | SCE_Asset Management & Inspections_Intrusive pole inspections _N/A_2021 | 138 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | LiDAR inspections of distribution electric lines and equipment |  | 7 | N/A | N/A | SCE_Asset Management & Inspections_LiDAR inspections of distribution electric lines and equipment _N/A_2021 | 139 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | LiDAR inspections of transmission electric lines and equipment |  | 8 | N/A | N/A | SCE_Asset Management & Inspections_LiDAR inspections of transmission electric lines and equipment _N/A_2021 | 139 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Unmanned Aerial (UAS) Operations Traning | OP-3 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _OP-3_2021 | 143 | Increase the number of UAS operators | 50 crews |  |  |  | 50 |  |  |  | 42 crews The goal of training an additional 50 UAS operators was not met, however, 42 resources passed the FAA 107 exam despite the closure of FAA testing centers due to COVID from March through July* (see comment) | [5 empty] | Behind Plan, Substantially Complete | Planning for 2021 certifications and tracking an additional 8 resources to take and pass the FAA exam
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Distribution High Fire Risk Informed Inspections in HFRA | IN-1.1 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _IN-1.1_2021 | 139 | # of structures in HFRA | Inspect 105,000 structures in HFRA |  |  |  | 105000 |  |  |  | ~199,000 of 105,000 structures inspected in HFRA (see comment) | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Aerial Inspections - Distribution | IN-6.1 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _IN-6.1_2021 | 141 | # of structures in HFRA | Inspect 165,000 structures in HFRA |  |  |  | 165000 |  |  |  | ~168,000 of 165,000 structures inspected in HFRA. The start of 2020 aerial inspections were delayed due to COVID restrictions preventing aerial inspectors from accessing the on-site inspection room. Restarted inspections in Q2.Catastrophic fires and environmental factors (visibility, winds, heat) in the second half of the year caused inspection progress to slow, but the goal of 165,000 distribution structures in HFRA was met. | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Advanced Unmanned Aerial Systems Study | AT-2.2 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _AT-2.2_2021 | 142 | N/A | [9 empty] | Conduct additional Extended Visual Line of Sight (EVLOS) demonstration UAS flights using lessons learned from 2019 study and validate aerial patrol findings via truck, foot, or helicopter |  |  |  | Despite the UAS team being diverted to support fire restoration efforts in Q4, the second round of UAS demonstration flights were successfully conducted with multiple vendors and validated by inspectors along a 11.5-mile segment. | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Asset Defect Detection Using Machine Learning Object Detection | AT-5 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _AT-5_2021 | 140 | N/A | [9 empty] | Begin standardization of data collection for Machine Learning (ML) by cataloging and tagging inspection imagery metadata for ML. Investigate SCE use cases and evaluate feasibility of ML to support objective evaluation of assets |  |  |  | Documentation of 2020 machine learning findings began in December and is expected to be completed in Q1 2021. In 2020 SCE developed a process for collecting and tagging images to support machine learning model development and explored collaboration opportunities with a ML vendors. | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of transmission electric lines and |  | 10 | Transmission High Fire Risk Informed Inspections in HFRA | IN-1.2 | SCE_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and _IN-1.2_2021 | 143 | # of structures in HFRA | Inspect 22,500 structures in HFRA |  |  |  | 22500 |  |  |  | ~33,500 of 22,500 structures inspected in HFRA (see comment) | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of transmission electric lines and |  | 10 | Aerial Inspections - Transmission | IN-6.2 | SCE_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and _IN-6.2_2021 | 144 | # of structures in HFRA | Inspect 33,500 structures in HFRA |  |  |  | 33500 |  |  |  | Substantially complete. ~31,380 of 33,500 structures inspected in HFRA. The start of 2020 aerial inspections were delayed due to COVID restrictions preventing aerial inspectors from accessing the on-site inspection room. Restarted inspections in Q2. Catastrophic fires and environmental factors (visibility, winds, heat) in the second half of the year caused inspection progress to slow. FAA flight restrictions in sensitive areas (government, wildlife) prevented a portion of scope from being captured. | [5 empty] | Behind Plan, Substantially Complete | The aerial team is evaluating structures that were not completed or partially completed in 2020 to determine which structures can be rolled over for inspection in 2021 and which structures are unlikely to be captured from the air due to a permanent condition (e.g., geographical restrictions). In 2021 the aerial team is targeting inspections to start earlier in the year (e.g., Q1 2021) to make greater progress ahead of fire season.
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of transmission electric lines and |  | 10 | Assessment of Partial Discharge for Transmission Facilities | AT-6 | SCE_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and _AT-6_2021 | 144 | N/A | [9 empty] | Evaluate use of a Partial Discharge assessment technology to assess the health of in-service transmission assets |  |  |  | Team conducted a benchmark assessment for Transmission Partial Discharge based on survey data, industry research, and engineering analysis. Team developed an assessment report with its findings and recommendations. | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Patrol inspections of distribution electric lines and equipment |  | 11 | N/A | N/A | SCE_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _N/A_2021 | 144 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Patrol inspections of transmission electric lines and equipment |  | 12 | N/A | N/A | SCE_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _N/A_2021 | 145 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Pole loading assessment program to determine safety factor |  | 13 | N/A | N/A | SCE_Asset Management & Inspections_Pole loading assessment program to determine safety factor _N/A_2021 | 145 | N/A
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Quality assurance / quality control of inspections |  | 14 | Quality Oversight / Quality Control | IN-2 | SCE_Asset Management & Inspections_Quality assurance / quality control of inspections _IN-2_2021 | 146 | # of structures in HFRA | Perform quality control and oversight of inspections of 15,000 transmission, distribution, and generation structures in HFRA |  |  |  | 15000 |  |  |  | Performed quality control on ~17,400 of 15,000 structures in HFRA. | [5 empty] | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Substation inspections |  | 15 | Failure Modes and Effects Analysis (FMEA) | IN-7 | SCE_Asset Management & Inspections_Substation inspections _IN-7_2021 | 147 | N/A | [9 empty] | Complete FMEA study for substation assets in HFRA and prepare final report |  |  |  | The working group began developing FMEA risk identification in Q2 and completed it in Q3. The final assessment report, documenting the findings and recommendations, was completed in Q4. | Complete
SCE | 2021-04-01 | Asset Management & Inspections | 5.3.4. |  | Generation High Fire Risk Informed Inspections in HFRA | 16 | Generation High Fire Risk Informed Inspections in HFRA | IN-5 | SCE_Asset Management & Inspections_x_IN-5_2021 | 147 | # of structures in HFRA | Perform inspection of 200 generation-related assets |  |  |  | 200 |  |  |  | ~290 of 200 structures inspected in HFRA. | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Additional efforts to manage community and environmental impacts |  | 1 | N/A | N/A | SCE_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _N/A_2021 | 152 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | N/A | N/A | SCE_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 152 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around transmission electric lines and equipment |  | 3 | N/A | N/A | SCE_Vegetation Management & Inspections_Detailed inspections of vegetation around transmission electric lines and equipment _N/A_2021 | 152 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Emergency response vegetation management due to red flag warning or other urgent conditions |  | 4 | N/A | N/A | SCE_Vegetation Management & Inspections_Emergency response vegetation management due to red flag warning or other urgent conditions _N/A_2021 | 153 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Expanded Pole Brushing | VM-2 | SCE_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VM-2_2021 | 153 | # of poles cleared | Perform brush clearance of 200,000 poles SCE will strive to perform brush clearance for 300,000 poles subject to resource constraints and other execution risks |  |  |  | 200000 |  |  |  | Pole clearances exceeded the WMP Target of 200K in November and ended the year at ~231,000 pole clearances. (see comment) | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Expanded Clearances for Legacy Facilities | VM-3 | SCE_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VM-3_2021 | 153 | % of identified facilities where enhanced buffers were completed | Perform assessments of all identified facilities in HFRA. Establish enhanced buffers at 30% of identified facilities |  |  |  | 30% |  |  |  | The activity was completed in December as enhanced buffers were completed at 39% (61) identified facilities, surpassing the original goal of 30% (46). | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Improvement of inspections |  | 6 | N/A | N/A | SCE_Vegetation Management & Inspections_Improvement of inspections _N/A_2021 | 154 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 | N/A | N/A | SCE_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 154 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | LiDAR inspections of vegetation around transmission electric lines and equipment |  | 8 | N/A | N/A | SCE_Vegetation Management & Inspections_LiDAR inspections of vegetation around transmission electric lines and equipment _N/A_2021 | 154 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Other discretionary inspections of vegetation around distribution electric lines and equipment |  | 9 | N/A | N/A | SCE_Vegetation Management & Inspections_Other discretionary inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 154 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Other discretionary inspections of vegetation around transmission electric lines and equipment |  | 10 | N/A | N/A | SCE_Vegetation Management & Inspections_Other discretionary inspections of vegetation around transmission electric lines and equipment _N/A_2021 | 154 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 | N/A | N/A | SCE_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 155 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 | N/A | N/A | SCE_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 155 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Quality assurance / quality control of vegetation inspections |  | 13 | N/A | N/A | SCE_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections _N/A_2021 | 155 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Quality assurance / quality control of inspections |  | 14 | Vegetation Management Quality Control | VM-5 | SCE_Vegetation Management & Inspections_Quality assurance / quality control of inspections _VM-5_2021 | 155 | # of risk-based HFRA circuit miles | Perform 3,000 risk-based HFRA circuit mile vegetation management Quality Control inspections |  |  |  | 3000 |  |  |  | Performed ~6,100 of 3,000 of risk-based HFRA circuit mile quality control inspections. | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Substation inspections |  | 15 | N/A | N/A | SCE_Vegetation Management & Inspections_Substation inspections _N/A_2021 | 155 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Hazard Tree Management Program | VM-1 | SCE_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VM-1_2021 | 156 | # of trees assessed and % mitigated with 180 days | Assess 75,000 trees for hazardous conditions and perform prescribed mitigations in accordance with program guidelines and schedules |  |  |  | 75000 |  |  |  | Assessed ~99,500 of 75,000 trees through Q4 and mitigated 97% of trees within 180 days, which exceeded the WMP Program Target. | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Drought Relief Initiative (DRI) Inspections and Mitigations | VM-4 | SCE_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VM-4_2021 | 158 | % of active inventory aged less than 180 days | Perform DRI annual inspection scope and complete prescribed mitigations in accordance with internal DRI program guidelines |  |  |  | 94% |  |  |  | Drought Relief Initiative (DRI) inspections met year-end goal. 3rd (and final) cycle inspections completed mid-December. DRI mitigations exceeded year-end goal with 95% of active inventory aged less than 180 days, which exceeded the WMP target of 94%. | [5 empty] | Complete
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Substation inspection |  | 17 | N/A | N/A | SCE_Vegetation Management & Inspections_Substation inspection _N/A_2021 | 158 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Substation vegetation management |  | 18 | N/A | N/A | SCE_Vegetation Management & Inspections_Substation vegetation management _N/A_2021 | 158 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Vegetation inventory system |  | 19 | N/A | N/A | SCE_Vegetation Management & Inspections_Vegetation inventory system _N/A_2021 | 158 | N/A
SCE | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | N/A | N/A | SCE_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _N/A_2021 | 158 | N/A
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Automatic recloser operations |  | 1 | Annual SOB 322 Review | OP-1 | SCE_Grid Operations & Operating Protocols_Automatic recloser operations _OP-1_2021 | 161 | N/A | [9 empty] | Review and update SOB 322 to reflect lessons learned from past elevated fire weather threats/PSPS events and integrate, where applicable, new and improved situational awareness data, improved threat indicators, and applicable regulatory requirements in an effort toreduce wildfire risk and the impact of outages on customers. |  |  |  | Completed the annual SOB 322 bulletin, reflecting lessons learned from 2019, elevated threats, and PSPS events. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Crew-accompanying ignition prevention and suppression resources and services |  | 2 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Crew-accompanying ignition prevention and suppression resources and services _N/A_2021 | 163 | N/A
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Personnel work procedures and training in conditions of elevated fire risk |  | 3 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _N/A_2021 | 163 | N/A
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Protocols for PSPS re-energization |  | 4 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Protocols for PSPS re-energization _N/A_2021 | 163 | N/A
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Wildfire Infrastructure Protection Team Additional Staffing | OP-2 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _OP-2_2021 | 168 | N/A | [9 empty] | Hire additional resources including: a senior compliance manager, two compliance advisors, a project/program advisor, a data specialist and a fire-weather meteorologist. PSPS Operations will also be staffed to provide dedicated operational, project management, and compliance capabilities. |  |  |  | PSPS Operations hiring was completed in November. Consultants are bridging the gap in Project Management and Compliance competencies until full time SCE employees can be hired. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Community Resource Centers | PSPS-2 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-2_2021 | 165 | # of Community Resource Centers available across SCE service territory | Have 23 sites available across SCE service territory for customers impacted by a PSPS |  |  |  | 23 |  |  |  | 56 CRCs have been contracted across 9 counties. Of these 56, 43 can operate with extended hours (8am to 10pm) per PSPS Phase 2 D.20-05-051. | [5 empty] | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Customer Resiliency Equipment Incentives | PSPS-3 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-3_2021 | 166 | N/A | [9 empty] | Develop a customer resiliency equipment incentive pilot program that provides financial support to customers willing to increase resiliency within its HFRA. One customer will be implemented for this pilot in 2020. |  |  |  | The pilot program has been completed and the chosen location, a local high school, now has the ability to island itself from the grid and maintain emergency services during a power outage. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Income Qualified Critical Care (IQCC) Customer Battery Backup Incentive Program | PSPS-4 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-4_2021 | 166 | N/A | [9 empty] | Outreach to eligible customers (low income, critical care, Tier 2/3) to provide portable battery back-up solution. SCE has identified approximately 2,500 customers that it will target for the program in 2020, with efforts to begin in the second quarter. |  |  |  | The program launched on July 7th and by year end ~2,600 customers had been offered the program via direct outreach. Customer enrollments and battery deliveries started in Q3 and continued throughout Q4. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | MICOP Partnership | PSPS-5 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-5_2021 | 167 | N/A | [9 empty] | Enable communications with indigenous populations and measure the number of customers contacted |  |  |  | Mixteco/IndigenaCommunity Organizing Project (MICOP) has exceeded the year-end goal of conducting wildfire safety outreach to 600 customers. In June, MICOP started follow-up phone calls with customers who had received the initial outreach. The target of 100 follow-ups has also been exceeded. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Independent Living Centers Partnership | PSPS-6 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-6_2021 | 167 | N/A | [9 empty] | Conduct outreach activities and workshops/trainings to provide preparedness education and assistance in applying for the Medical Baseline Program and measure the number of customers contacted |  |  |  | The Independent Living Centers (ILCs) program exceeded the target holding 10 workshops/trainings for customers with disabilities and others with access and functional needs in June. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | Community Outreach | PSPS-7 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-7_2021 | 168 | N/A | [9 empty] | Minimum of five Community Crew Vehicles (CCVs) ready to be deployed during times when weather and fuel conditions are at critical levels. Communicate with customers in a local targeted way using a variety of channels to ensure timely delivery of notifications. |  |  |  | A minimum of five CCVs were ready for deployment during each of SCE’s PSPS activations in 2020. The CCV locator tool has featured on sce.com and been promoted during PSPS events. A virtual CCV website went live in Q3 offering customers wildfire safety resources and support. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Stationed and on-call ignition prevention and suppression resources and services |  | 6 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Stationed and on-call ignition prevention and suppression resources and services _N/A_2021 | 171 | N/A
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. |  | De-Energization Notifications | 7 | De-Energization Notifications - Public safety agencies and local governments | PSPS-1.1 | SCE_Grid Operations & Operating Protocols_x_PSPS-1.1_2021 | 171 | N/A | [9 empty] | Notify applicable public safety agencies and local governments of possible de-energization |  |  |  | Through the end of December the PSPS Incident Management Team (IMT) was activated for 12 events. Notifications were sent to stakeholders during each event. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. |  | De-Energization Notifications | 7 | De-Energization Notifications - Cal OES | PSPS-1.2 | SCE_Grid Operations & Operating Protocols_x_PSPS-1.2_2021 | 171 | N/A | [9 empty] | Notify Cal OES through the State Warning Center of possible de-energization |  |  |  | Through the end of December the PSPS Incident Management Team (IMT) was activated for 12 events. Notifications were sent out to stakeholders during each event. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. |  | De-Energization Notifications | 7 | De-Energization Notifications - CPUC | PSPS-1.3 | SCE_Grid Operations & Operating Protocols_x_PSPS-1.3_2021 | 171 | N/A | [9 empty] | Notify the CPUC of possible de-energization |  |  |  | Through the end of December the PSPS Incident Management Team (IMT) was activated for 12 events. Notifications were sent out to stakeholders during each event. | Complete
SCE | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. |  | De-Energization Notifications | 7 | De-Energization Notifications - Enhance Emergency Outage Notification system | PSPS-1.4 | SCE_Grid Operations & Operating Protocols_x_PSPS-1.4_2021 | 171 | N/A | [9 empty] | Enhance Emergency Outage Notification System (EONS) to include Zip Code level alerting to include in-language notifications to align with its existing notification abilities for SCE customers |  |  |  | Zip code level and in-language notification enhancements (in Spanish, Mandarin, Cantonese, Vietnamese, Korean, and Tagalog) were implemented and used during PSPS events in 2020. | Complete
SCE | 2021-04-01 | Data Governance | 5.3.7. | Centralized repository for data |  | 1 | N/A | N/A | SCE_Data Governance_Centralized repository for data _N/A_2021 | 174 | N/A
SCE | 2021-04-01 | Data Governance | 5.3.7. | Collaborative research on utility ignition and/or wildfire |  | 2 | N/A | N/A | SCE_Data Governance_Collaborative research on utility ignition and/or wildfire _N/A_2021 | 179 | N/A
SCE | 2021-04-01 | Data Governance | 5.3.7. | Documentation and disclosure of wildfire-related data and algorithms |  | 3 | N/A | N/A | SCE_Data Governance_Documentation and disclosure of wildfire-related data and algorithms _N/A_2021 | 179 | N/A
SCE | 2021-04-01 | Resource Allocation Methodology | 5.3.8. | Tracking and analysis of near miss data |  | 4 | N/A | N/A | SCE_Resource Allocation Methodology_Tracking and analysis of near miss data _N/A_2021 | 182 | N/A
SCE | 2021-04-01 | Resource Allocation Methodology | 5.3.8. | Allocation methodology development and application |  | 1 | N/A | N/A | SCE_Resource Allocation Methodology_Allocation methodology development and application _N/A_2021 | 184 | N/A
SCE | 2021-04-01 | Resource Allocation Methodology | 5.3.8. | Risk reduction scenario development and analysis |  | 2 | N/A | N/A | SCE_Resource Allocation Methodology_Risk reduction scenario development and analysis _N/A_2021 | 186 | N/A
SCE | 2021-04-01 | Resource Allocation Methodology | 5.3.8. | Risk spend efficiency analysis |  | 3 | N/A | N/A | SCE_Resource Allocation Methodology_Risk spend efficiency analysis_N/A_2021 | 187 | N/A
SCE | 2021-04-01 | Resource Allocation Methodology | 5.3.8. |  | Organizational Support - PMO and OCM | 4 | N/A | N/A | SCE_Resource Allocation Methodology_x_N/A_2021 | 188 | N/A
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Adequate and trained workforce for service restoration |  | 1 | SCE Emergency Response Training | DEP-2 | SCE_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _DEP-2_2021 | 194 | N/A | [9 empty] | Hold SCE IMT member training on de-energization protocols, determine additional staffing needs and train, exercise and qualify new staff |  |  |  | All annual trainings and exercises have been completed for 2020. The trainings and exercises were completed virtually as a result of COVID. Additional staffing for a permanent PSPS IMT have been hired. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Customer Education and Engagemente - Dear Neighbor Letter | DEP-1.1 | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _DEP-1.1_2021 | 196 | N/A | [9 empty] | Send ~915,000 letters with information about PSPS, emergency preparedness, and SCE’s wildfire mitigation plan to customer accounts in HFRA and ~3,200,000 letters to customer accounts in non-HFRA |  |  |  | Mailings have been completed to all customers (both HFRA and non-HFRA). COVID messaging was included in the newsletter along with contact information in 15 languages. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Customer Education and Engagemente - Community Meetings | DEP-1.2 | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _DEP-1.2_2021 | 196 | N/A | [9 empty] | Host 8-12 community meetings in areas impacted by 2019 PSPS plus other meetings including online as determined to share information about PSPS, emergency preparedness, and SCE’s wildfire mitigation plan |  |  |  | Nine virtual Community Meetings were held by the end of Q2. No additional Community Meetings were planned in 2020. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Customer Education and Engagemente - Marketing Campaign | DEP-1.3 | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _DEP-1.3_2021 | 196 | N/A | [9 empty] | Marketing campaign to reach 5,000,000 Customer Accounts (goal of 40% awareness about the purpose of PSPS, emergency preparedness, and SCE’s wildfire mitigation plan) |  |  |  | The 2020 marketing campaign was launched in May and SCE tracked PSPS and emergency awareness throughout the year. Average monthly awareness throughout 2020 was ~56%. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | IOU Customer Engagement | DEP-3 | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _DEP-3_2021 | 196 | N/A | [9 empty] | Participate in statewide multichannel and multi-lingual campaign using digital ads, social media ads, and radio ads to provide customers with important and consistent messaging about wildfire mitigation activities happening across the state |  |  |  | SCE has determined there is no need for a separate statewide customer engagement campaign in addition to SCE’s local market campaign and informed CalOESof this change in direction. SCE further described this change in its June 1, 2020 Off-Ramp and September 11th Change Report. SCE’s local PSPS education campaign launched in May 2020 across digital channels and continued throughout wildfire season. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Customer Research and Education | DEP-4 | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _DEP-4_2021 | 196 | N/A | [9 empty] | Develop/implement various research activities that gauge customer awareness, preparedness for, and satisfaction with outage experiences; to include but not be limited to: town hall meetings, online & telephone surveys, focus groups, and assessments of programs & services to prepare customers before and after PSPS outages |  |  |  | Town hall meetings were completed and a report summarizing findings was published. Online and telephone surveys were conducted on programs (e.g.,CRCs/CCVs). Assessments of customer preparations before and after PSPS outages were conducted through Voice of Customer surveys. | Complete
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. |  | Customer support in emergencies | 3 | N/A | N/A | SCE_Emergency Planning & Preparedness_x_N/A_2021 | 198 | N/A
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. |  | Disaster and emergency preparedness plan | 4 | N/A | N/A | SCE_Emergency Planning & Preparedness_x_N/A_2021 | 198 | N/A
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. |  | Preparedness and planning for service restoration | 5 | N/A | N/A | SCE_Emergency Planning & Preparedness_x_N/A_2021 | 200 | N/A
SCE | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. |  | Protocols in place to learn from wildfire events | 6 | N/A | N/A | SCE_Emergency Planning & Preparedness_x_N/A_2021 | 200 | N/A
Notes:
-At the time of submission of this QIU (4/1/2021), SCE is completing its data validation of 2020 WMP activities. As a result, some figures reported in Advice 4437-E (SCE QAL Q4 2020) have been slightly revised. These revisions do not impact the status of activities and have been incorporated and noted in this QIU. Reported 2020 figures are subject to further revision as SCE completes its data validation process.
-In this QIU, SCE reports on progress in the 69 2020 WMP activities which were initiated to primarily address wildfire risks and/or PSPS impacts and which have specific 2020 program targets. SCE considers Non-WMP programs to be programs which are not initiated to primarily address wildfire risks and/or PSPS impacts. These programs are implemented for purposes primarily outside of wildfire / PSPS impact mitigation (e.g., for reliability), though they may provide indirect wildfire / PSPS impact mitigation benefits. Therefore, these programs would continue even if wildfire and/or PSPS risk did not exist.
NOTE: To add more rows, highlight the current last row of the table, copy, and paste directly below the last row
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See notes at end of table below
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE focuses its QIU on reporting on WMP activities which are initiated to primarily address wildfire risks and/or PSPS impacts and have specific program targets. SCE considers Non-WMP programs to be programs which are not initiated to primarily address wildfire risks and/or PSPS impacts. These programs are implemented for purposes primarily outside of wildfire / PSPS impact mitigation (e.g., for reliability), though they may provide indirect wildfire / PSPS impact mitigation benefits. Therefore, these programs would continue even if wildfire and/or PSPS risk did not exist. These programs can also include work SCE is doing as part of standard operations. Discussion on these programs were included in SCE’s 2020-2022 WMP.
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on H20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We call it "Expansion of Risk Analysis and Wildfire Risk Reduction Model" in the WMP (p. 11) Reply: Thanks. Updated.
Note on G21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on U23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Following validation of records, 100 of 55 circuit breaker relays were impacted to allow for 92 fast curve settings installed and placed into service. This is a decrease of 8 from what was published in the WMP Progress Update 2020-12-31 on 3/8/2021.
Note on U39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Following validation of records, 42 persons completed UAS 107 training and FAA certification in 2020. This is a decrease of 1 from what was published in the WMP Progress Update 2020-12-31 on 3/8/2021.
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on U60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Following validation of records, 42 persons completed UAS 107 training and FAA certification in 2020. This is a decrease of 1 from what was published in the WMP Progress Update 2020-12-31 on 3/8/2021.
Note on U61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As noted in SCE's 2020 WMP First Change Orders Report filed September 11, 2020, SCE increased the scale of its Distribution HFRI inspections to 165,000.
Note on U65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As noted in SCE's 2020 WMP First Change Orders Report filed September 11, 2020, SCE increased the scale of its Transmission HFRI inspections to 33,500.
Note on G73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on U78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Following validation of records, SCE performed ~231,000 pole clearances in 2020. This is a decrease from the reported ~233,900 figure reported in the WMP Progress Update 2020-12-31 submitted on 3/8/2021.​
Note on G80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE noticed the formula mapping in the WSD's template was incorrect and hence coded in the value 6.
Note on G108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab
Note on G129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE had an additional section in the 2020 WMP that was not included in the Initiative Mapping tab

## Initiative mapping-DO NOT EDIT
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other