## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | LU
Report Year |  | 2020
Report Quarter |  | Q4
Submission Date |  | 2021-04-01
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
LU | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 |  | 001 | LU_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _001_2021 | 80 | N/A | [9 empty] | Complete risk model |  |  |  | Nearly Completed | Complete
LU | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Advanced weather monitoring and weather stations |  | 1 |  | 002 | LU_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _002_2021 | 81 | Weather Stations Installed | 20 |  |  |  | 20 | 0 | 1 | 10 | 19 | [5 empty] | In Progress
LU | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors |  | 2 |  | 003 | LU_Situational Awareness & Forecasting_Continuous monitoring sensors _003_2021 | 82 | DFA units installed | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Procurment of DFA untis and signed contract |  |  |  | Accomplished | In Progress
LU | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Fault indicators for detecting faults on electric lines and equipment |  | 3 |  | 004 | LU_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _004_2021 | 83 | Fault indicators installed | n/a | [13 empty] | In Progress
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation |  | 3 |  | 005 | LU_Grid Design & System Hardening_Covered conductor installation _005_2021 | 87 | Line miles | 5 |  |  |  | 5 |  |  |  | 6.8 | [5 empty] | Complete
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Crossarm maintenance, repair, and replacement |  | 5 |  | 006 | LU_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement _006_2021 | 90 | Tree attachments | n/a
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 |  | 007 | LU_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _007_2021 | 90 | Poles | n/a | [7 empty] | 62
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Expulsion fuse replacement |  | 7 |  | 008 | LU_Grid Design & System Hardening_Expulsion fuse replacement _008_2021 | 91 | Expulsion fuses replaced | 720 |  |  |  | 720 | 0 | 258 | 419 | 853 | [5 empty] | In Progress
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 |  | 009 | LU_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _009_2021 | 93 | Line miles | 4 |  |  |  | 4 |  |  |  | 4 | Microgrid |  |  |  | Accomplished | Complete
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Installation of system automation equipment |  | 9 |  | 010 | LU_Grid Design & System Hardening_Installation of system automation equipment _010_2021 | 93 | Reclosers installed | 4 | 0 | 0 | 2 | 4 | 0 | 0 | 2 | 4 | [5 empty] | In Progress
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Other corrective action |  | 12 |  | 011 | LU_Grid Design & System Hardening_Other corrective action _011_2021 | 94 | Tree attachment removals | n/a | [7 empty] | 60
LU | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Undergrounding of electric lines and/or equipment |  | 16 |  | 012 | LU_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _012_2021 | 96 | Line miles | 4 |  |  |  | 4 |  |  |  | 0.75
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.1 | Detailed inspections of distribution electric lines and equipment |  | 1 |  | 013 | LU_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _013_2021 | 81 | Asset Inspection (Line miles) | 1635 | 368 | 425 | 842 | 1635 |  | 368 | 425 | 842 | [5 empty] | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.2 | Detailed inspections of transmission electric lines and equipment |  | 2 |  | 014 | LU_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _014_2021 | 81 | N/A | [14 empty] | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.3 | Improvement of inspections |  | 3 |  | 015 | LU_Asset Management & Inspections_Improvement of inspections _015_2021 | 82 | N/A | [9 empty] | Enterprise GIS coming in 2022 |  |  |  |  | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.4 | Infrared inspections of distribution electric lines and equipment |  | 4 |  | 016 | LU_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _016_2021 | 82 | N/A | [9 empty] | RFP developed in 2021, bid in 2022 |  |  |  |  | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.5 | Infrared inspections of transmission electric lines and equipment |  | 5 |  | 017 | LU_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _017_2021 | 82 | N/A | [9 empty] | N/A |  |  |  |  | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.6 | Intrusive pole inspections |  | 6 |  | 018 | LU_Asset Management & Inspections_Intrusive pole inspections _018_2021 | 83 | Intrusive Pole Inspections | 3113 | 0 | 0 | 1600 | 3113 | 0 | 0 | 1600 | 3113 | [5 empty] | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.7 | LiDAR inspections of distribution electric lines and equipment |  | 7 |  | 019 | LU_Asset Management & Inspections_LiDAR inspections of distribution electric lines and equipment _019_2021 | 83 | N/A | [9 empty] | N/A |  |  |  |  | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.8 | LiDAR inspections of transmission electric lines and equipment |  | 8 |  | 020 | LU_Asset Management & Inspections_LiDAR inspections of transmission electric lines and equipment _020_2021 | 84 | N/A | [9 empty] | N/A |  |  |  |  | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 |  | 021 | LU_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _021_2021 | 84 | N/A | [9 empty] | N/A |  |  |  |  | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.10 | Other discretionary inspection of transmission electric lines and |  | 10 |  | 022 | LU_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and _022_2021 | 84 | N/A |  |  |  |  | 12 |  |  |  |  | N/A |  |  |  |  | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.11 | Patrol inspections of distribution electric lines and equipment |  | 11 |  | 023 | LU_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _023_2021 | 85 | Patrol Inspection (Line Miles) | 2050 | 0 | 500 | 800 | 2050 | 0 | 500 | 800 | 2050 | [5 empty] | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.12 | Patrol inspections of transmission electric lines and equipment |  | 12 |  | 024 | LU_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _024_2021 | 85 | N/A | [9 empty] | N/A |  |  |  |  | N/A
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.13 | Pole loading assessment program to determine safety factor |  | 13 |  | 025 | LU_Asset Management & Inspections_Pole loading assessment program to determine safety factor _025_2021 | 85 | N/A |  |  |  |  | … |  |  |  |  | N/A |  |  |  |  | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.14 | Quality assurance / quality control of inspections |  | 14 |  | 026 | LU_Asset Management & Inspections_Quality assurance / quality control of inspections _026_2021 | 86 | N/A |  |  |  |  | … |  |  |  |  | RFP developed in 2021, bid in 2022 |  |  |  |  | In Progress
LU | 2021-04-01 | Asset Management & Inspections | 5.3.4.15 | Substation inspections |  | 15 |  | 027 | LU_Asset Management & Inspections_Substation inspections _027_2021 | 88 | Substations Inspected | 46 | 11 | 11 | 11 | 46 | 11 | 11 | 11 | 46 | [5 empty] | In Progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Additional efforts to manage community and environmental impacts |  | 1 |  | 028 | LU_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _028_2021 | 104 | Number of line miles treated | 14 |  |  |  | 14 | 0 | 0 | 1 | 14 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 |  | 029 | LU_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _029_2021 | 107 | Number of line miles inspected | 230 |  |  |  | 230 | 30 | 98 | 168 | 233 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Fuel management and reduction of “slash” from vegetation management activities |  | 5 |  | 030 | LU_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _030_2021 | 109 | Tons of biomass removed | n/a |  |  |  |  | 0 | 0 | 247.8 | 376.4 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 |  | 031 | LU_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment _031_2021 | 112 | Number of line miles inspected | n/a |  |  |  |  | 0 | 0 | 0 | 328 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 |  | 032 | LU_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _032_2021 | 113 | Number of line miles inspected | n/a |  |  |  | 150 | 55 | 134 | 218 | 331.2 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Quality assurance / quality control of vegetation inspections |  | 13 |  | 033 | LU_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections _033_2021 | 114 | Number of line miles inspected | n/a |  |  |  |  | 0 | 0 | 0 | 57.1 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Remediation of at-risk species |  | 15 |  | 034 | LU_Vegetation Management & Inspections_Remediation of at-risk species _034_2021 | 117 | Number of line miles treated | n/a |  |  |  | 230 | 20 | 42 | 90 | 131.7 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 |  | 035 | LU_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _035_2021 | 118 | Number of line miles treated | n/a |  |  |  | 150 | 36 | 88 | 135 | 243.1 | [5 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 |  | 036 | LU_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _036_2021 | 119 | Number of line miles treated | n/a | [13 empty] | In progress
LU | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Other discretionary inspections of vegetation around transmission electric lines and equipment |  | 10 |  | 037 | LU_Vegetation Management & Inspections_Other discretionary inspections of vegetation around transmission electric lines and equipment _037_2021 | 113 | Number of line miles treated | n/a |  |  |  | 50 | 0 | 0 | 36 | 50 | [5 empty] | In progress
LU | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Personnel work procedures and training in conditions of elevated fire risk |  | 3 |  | 038 | LU_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _038_2021 | 121 | N/A | [9 empty] | Improve Fire Potential Index Operating Conditions |  |  |  | Completed | In Progress
LU | 2021-04-01 | Grid Operations & Operating Protocols | 5.3.6. | Stationed and on-call ignition prevention and suppression resources and services |  | 6 |  | 039 | LU_Grid Operations & Operating Protocols_Stationed and on-call ignition prevention and suppression resources and services _039_2021 | 124 | Number of vehicles | [8 empty] | 2
LU | 2021-04-01 | Data Governance | 5.3.7. | Centralized repository for data |  | 1 |  | 040 | LU_Data Governance_Centralized repository for data _040_2021 | 98 | Line Miles | 2055 | 0 | 0 | 0 | 2055 | 0 | 0 | 0 | 0 | Developing a centralized data lake by end of year | None | Request made for SQL Server, Reporting tools | Waiting for IT, Negotiations | Meetings held, request approved | In Progress
LU | 2021-04-01 | Data Governance | 5.3.7. | Collaborative research on utility ignition and/or wildfire |  | 2 |  | 041 | LU_Data Governance_Collaborative research on utility ignition and/or wildfire _041_2021 | 126 | N/A | [9 empty] | Data provided to University of Reno for High Impendence Fault Detection Study |  |  |  | Completed | In Progress
LU | 2021-04-01 | Emergency Planning & Preparedness | 5.3.9. | Adequate and trained workforce for service restoration |  | 1 |  | 042 | LU_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _042_2021 | 128 | N/A | [9 empty] | Update Corporate Emergency Management Plan |  |  |  | Completed | Complete
LU | 2021-04-01 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Community engagement |  | 1 |  | 043 | LU_Stakeholder Cooperation & Community Engagement_Community engagement _043_2021 | 135 | N/A | [9 empty] | Increase public awareness |  |  |  | Completed | In Progress

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other