## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | PC
Report Year |  | 2020
Report Quarter |  | Q4 (Revised)
Submission Date |  | 4/1/2021 02/25/2026
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PC | 2021-04-01 | Risk Assessment & Mapping | 5.3.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | RA-1 | 1 | Risk Modeling Platform | 001 | PC_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _001_2021 | 122107 | Financial Reporting ($)- | $186,000- | - | - | - | $186,000- | - | - | - | $186,000 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Advanced weather monitoring and weather stations | SA-1 | 1 | Installation of Weather Stations | 002 | PC_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _002_2021 | 123132 | Weather Stations | 10 | - | - | - | 2 | - | - | - | 2 | N/A | - | - | - | - | Delayed | Delays in siting and installation; Iterative and longer process to ensure quality data is received; All remaining weather stations from 2020 are purchased and in the process of being installed prior to fire season
PC | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors | SA-3 | 2 | Pilot 1: DFA | 003 | PC_Situational Awareness & Forecasting_Continuous monitoring sensors _003_2021 | 128132 | Devices / Projects | 4 | - | - | - | 10 | - | - | - | 10 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Situational Awareness & Forecasting | 5.3.2. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | PS-5 | 5 | Fire Risk Monitoring | 004 | PC_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _004_2021 | 128 | Financial Reporting ($)- | $975,913- | - | - | - | $975,913- | - | - | - | $975,913 - | N/APrepare operational and support teams to activation process; evaluate effectiveness of real‐time monitoring function, determine needed changes and inform stakeholders. | - | - | - | - | In Progress
PC | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Circuit Breaker Maintenance | 005 | PC_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _005_2021 | 129138 | Financial Reporting ($)- | $148- | - | - | - | $148- | - | - | - | $148 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation | AH-5 | 3 | Covered Conductor | 006 | PC_Grid Design & System Hardening_Covered conductor installation _006_2021 | 130139 | Line-Miles | 38 | - | - | - | 1.4 | - | - | - | 1.4 | N/A | - | - | - | - | Delayed | Significantly delays due to start up efforts and onboarding contractors to support the design and estimating phase of the projects
PC | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Crossarm maintenance, repair, and replacement |  | 5 | Crossarm Replacement | 007 | PC_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement _007_2021 | 131 144 | Financial Reporting ($)- | $272,000- | - | - | - | $272,000- | - | - | - | $272,000 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Distribution pole replacement and reinforcement, including with composite poles | AH-2 | 6 | Targeted Pole Replacement | 008 | PC_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _008_2021 | 131145 | Poles | 189 | - | - | - | 29 | - | - | - | 29 | N/A | - | - | - | - | In Progress | Scope of project fully defined and aligned with the targeted installation of covered conductor in 2020 resulting in a re-phasing of stand-alone pole replacements; Future delays not anticipated
PC | 2021-04-01 | Grid Design & System Hardening | 5.3.3. | Installation of system automation equipment | AH-4 | 9 | Relay/Recloser Replacement | 009 | PC_Grid Design & System Hardening_Installation of system automation equipment _009_2021 | 136153 | Devices / Projects | 2831 | - | - | - | 28 | - | - | - | 28 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Detailed inspections of distribution electric lines and equipment |  | 1 | Distribution Detailed Inspections | 010 | PC_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _010_2021 | 144208 | FacilitiesLine-Miles | 10,155605 | - | - | - | 10,155538 | - | - | - | 10,155538 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | Transmission Detailed Inspections | 011 | PC_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _011_2021 | 145208 | FacilitiesLine-Miles | 1,188122 | - | - | - | 1,188224 | - | - | - | 1,188224 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Infrared inspections of transmission electric lines and equipment | IN-5 | 5 | LiDAR/Infrared Transmission Lines | 012 | PC_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _012_2021 | 147209 | Line-Miles | 866232 | - | - | - | 866 | - | - | - | 866 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Intrusive pole inspections |  | 6 | Intrusive Pole Inspections | 013 | PC_Asset Management & Inspections_Intrusive pole inspections _013_2021 | 149209 | FacilitiesLine-Miles | 3,208150 | - | - | - | 3,208159 | - | - | - | 3,208159 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Patrol inspections of distribution electric lines and equipment |  | 11 | Distribution Patrol Inspections | 014 | PC_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _014_2021 | 151210 | FacilitiesLine-Miles | 46,2811,941 | - | - | - | 46,2811,724 | - | - | - | 46,2811,724 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Patrol inspections of transmission electric lines and equipment |  | 12 | Transmission Patrol Inspections | 015 | PC_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _015_2021 | 152210 | FacilitiesLine-Miles | 1,654657 | - | - | - | 1,654704 | - | - | - | 1,654704 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Quality assurance / quality control of inspections |  | 14 | Inspection QA/QC | 016 | PC_Asset Management & Inspections_Quality assurance / quality control of inspections _016_2021 | 152203 | Financial Reporting ($)- | $36- | - | - | - | $36- | - | - | - | $36 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Asset Management & Inspections | 5.3.4. | Substation inspections |  | 15 | Substation Inspections | 017 | PC_Asset Management & Inspections_Substation inspections _017_2021 | 155211 | Inspections | 444 | - | - | - | 444 | - | - | - | 444 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | Distribution Detailed Inspections of Vegetation | 018 | PC_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _018_2021 | 159251 | Line-Miles | 909825 | - | - | - | 9091,924 | - | - | - | 9091,924 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around transmission electric lines and equipment |  | 3 | Transmission Detailed Inspections of Vegetation | 019 | PC_Vegetation Management & Inspections_Detailed inspections of vegetation around transmission electric lines and equipment _019_2021 | 159251 | Line-Miles | 185345 | - | - | - | 185533 | - | - | - | 185533 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Expanded Pole Clearing | 020 | PC_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _020_2021 | 161248 | Poles | 2,1642,768 | - | - | - | 2164 | - | - | - | 2164 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of vegetation around distribution electric lines and equipment | VM-1 | 11 | WM Readiness Patrol: Dist | 021 | PC_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _021_2021 | 165233 | Line-Miles | 784- | - | - | - | 784- | - | - | - | 784 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of vegetation around transmission electric lines and equipment | VM-1 | 12 | WM Readiness Patrol: Trans | 022 | PC_Vegetation Management & Inspections_Patrol inspections of vegetation around transmission electric lines and equipment _022_2021 | 166234 | Line-Miles | 323- | - | - | - | 323- | - | - | - | 323 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Quality assurance / quality control of inspections |  | 1413 | Vegetation QA/QC | 023 | PC_Vegetation Management & Inspections_Quality assurance / quality control of inspections _023_2021 | 166235 | Line-Miles | 1,107- | - | - | - | 1,107- | - | - | - | 1,107 - | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Vegetation Management & Inspections | 5.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | Vegetation Cycle Clearing | 024 | PC_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _024_2021 | 170256 | Financial Reporting ($)Line-Miles | $6,699,3023,195 | - | - | - | $6,699,3022,457 | - | - | - | $6,699,302 2,457 | N/A | - | - | - | - | In Progress
PC | 2021-04-01 | Data Governance | 5.3.7. | Centralized repository for data |  | 1 | Data Governance | 025 | PC_Data Governance_Centralized repository for data _025_2021 | 175276 | Financial Reporting ($)- | $181,000- | - | - | - | $181,000- | - | - | - | $181,000 - | N/ADevelop methods to ensure programmatic associations among data sources; evaluate frequent refresh cycle for assessment on interim performance as compared to these data sources (i.e. outages and weather, ignitions and fire weather warnings, etc.) | - | - | - | - | In Progress
PC | 2021-04-01 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Community engagement |  | 1 | Community Engagement | 026 | PC_Stakeholder Cooperation & Community Engagement_Community engagement _026_2021 | 186317 | Financial Reporting ($)- | $36,474- | - | - | - | $36,474- | - | - | - | $36,474 - | N/A | - | - | - | - | In Progress