## Sheet1
Task Name | % Complete | Duration | Start | Finish | Predecessors
Discovery Phase | 100% | 124 days | Tue 2/9/21 | Fri 7/30/21
IT Kickoff meeting with Stakeholders | 100% | 1 day | Tue 2/9/21 | Tue 2/9/21
Finalize and Submit IT resource requirements | 100% | 6 days | Wed 2/10/21 | Wed 2/17/21
On-board IT Resources (preliminary scope & Requirements) | 100% | 32 days | Thu 2/18/21 | Fri 4/2/21
Finalize and Onboard Business Resources (preliminary scope & Requirements) | 100% | 58 days | Wed 2/10/21 | Fri 4/30/21
POC Prep - Cost Proposals & PO Processing (with 4 vendors) | 100% | 62 days | Mon 3/15/21 | Tue 6/8/21
Cyber Security Allignment | 100% | 8 days | Thu 4/1/21 | Mon 4/12/21
POC Scoring & Evaluations | 100% | 46 days | Mon 5/24/21 | Mon 7/26/21
Final Vendor Selection Complete | 100% | 1 day | Mon 7/26/21 | Mon 7/26/21
Sourcing and legal processing | 100% | 22 days | Thu 7/1/21 | Fri 7/30/21
Selected Vendor SOW finalized & Contract Created | 100% | 1 day | Fri 7/30/21 | Fri 7/30/21
Distribution Rountine / CEMA - Core processes | 100% | 33 days | Wed 5/5/21 | Fri 6/18/21
Solution Architecture | 100% | 57 days | Thu 4/1/21 | Fri 6/18/21
Change Management Preparation Phase | 100% | 32 days | Mon 5/3/21 | Tue 6/15/21
R1A (Pilot Release) | 100% | 169 days | Sun 8/1/21 | Wed 3/23/22
Prep, Plan & Architect (HLD Milestone 1) | 100% | 37 days | Sun 8/1/21 | Tue 9/21/21
Construct R1 | 100% | 60 days | Wed 9/22/21 | Tue 12/14/21
Validation R1A | 100% | 57 days | Wed 10/20/21 | Thu 1/6/22
Data Readiness & Mock Migration Run | 100% | 31 days | Tue 11/30/21 | Tue 1/11/22
PMO Deliverables and Approvals | 100% | 104 days | Sun 8/15/21 | Wed 1/5/22
R1A - Prod Deployment | 100% | 269 days | Tue 1/5/21 | Fri 1/14/22
Data Migration Production | 100% | 4 days | Wed 1/12/22 | Mon 1/17/22
SFDC Project Team Support R1A | 100% | 5 days | Mon 1/17/22 | Fri 1/21/22
Performance Test Run - R1A | 100% | 63 days | Wed 12/1/21 | Fri 2/25/22
Pilot Phase | 100% | 46 days | Wed 1/19/22 | Wed 3/23/22
R1B (Full Roll Out) | 100% | 99 days | Mon 1/17/22 | Wed 6/1/22
Mulesoft Integrations Design | 100% | 5 days | Mon 1/17/22 | Fri 1/21/22
Construct R1B | 100% | 44 days | Mon 1/24/22 | Thu 3/24/22
Initial product testing | 100% | 49 days | Mon 1/17/22 | Thu 3/24/22 | 101
QA & UAT | 100% | 27 days | Fri 3/25/22 | Fri 4/29/22 | 111
Performance Test - R1B | 100% | 46 days | Mon 3/14/22 | Fri 5/13/22
Key GIS & Miscellaneous Tasks | 100% | 80 days | Mon 1/17/22 | Thu 5/5/22
Migration Activities (Non-Prod) - in parallel with SIT | 100% | 14 days | Wed 3/23/22 | Fri 4/8/22
R1B Prod Deployment | 100% | 5 days | Mon 5/2/22 | Sun 5/8/22
SFDC Project Team Support R1B | 100% | 10 days | Mon 5/9/22 | Fri 5/20/22
R1B - Critical Reports in VMARS | 100% | 46 days | Mon 3/28/22 | Fri 5/27/22
IT Product Support Tasks | 100% | 75 days | Fri 2/18/22 | Wed 6/1/22
Change Management Key Tasks - R1B | 100% | 43 days | Wed 3/9/22 | Thu 5/5/22
On-Going Peer Training Sessions | 50% | 77 days | Fri 4/29/22 | Mon 8/15/22 | 183
RELEASE 2 | 18% | 116 days | Mon 5/23/22 | Sun 10/30/22
Construct | 39% | 62 days | Mon 5/23/22 | Tue 8/16/22
Initial product testing | 0% | 32 days | Wed 7/6/22 | Thu 8/18/22
QA Readiness Tasks | 0% | 6 days | Mon 8/15/22 | Mon 8/22/22
Final QA Validation | 0% | 16 days | Fri 8/19/22 | Fri 9/9/22
UAT Readiness Tasks | 0% | 5 days | Mon 9/5/22 | Fri 9/9/22
User Acceptance Testing (UAT) | 0% | 10 days | Mon 9/12/22 | Fri 9/23/22
Create and Configure new AGOL PROD org | 0% | 5 days | Thu 9/1/22 | Wed 9/7/22
Change the URL in SF/Lemur/MuleSoft + Validation | 0% | 2 days | Sun 9/4/22 | Mon 9/5/22
Performance Test - R2 | 0% | 35 days | Mon 8/15/22 | Fri 9/30/22
R2 Prod Deployment | 0% | 8 days | Mon 9/26/22 | Wed 10/5/22
SFDC Project Team Support R2 | 0% | 6 days | Mon 10/3/22 | Mon 10/10/22