## 2020_WV_SUMRY_All_Miles
REGION | DIVISION | CIRCUIT | 2020 Planned Mileage | WV_CLAIMED_MILES | NOTE
Bay Area | DI_Diablo | ALHAMBRA 1105 | 0.44
Bay Area | DI_Diablo | CLAYTON 2212 | 10 | 16.7396
Bay Area | DI_Diablo | MORAGA 1101 | 4 | 4.1377
Bay Area | DI_Diablo | MORAGA 1102 | 4.5 | 1.7925
Bay Area | DI_Diablo | MORAGA 1104 | 0.25
Bay Area | DI_Diablo | MORAGA 1105 | 4 | 4.0312
Bay Area | DI_Diablo | ORINDA 0401 | 9.75 | 5.4442
Bay Area | DI_Diablo | ROSSMOOR 1108 | 7 | 1.0224
Bay Area | EB_East Bay | OAKLAND K 1102 | 14.5 | 4.5919
Bay Area | EB_East Bay | OAKLAND K 1104 | 0.75 | 0.20479
Bay Area | EB_East Bay | OAKLAND X 1104 | 12.25 | 4.9445
Bay Area | EB_East Bay | VALLEY VIEW 1106 | 1 | 3.6215
Bay Area | MI_Mission | CASTRO VALLEY 1108 |  | 0.72582 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Bay Area | MI_Mission | SAN RAMON 2108 |  | 1.6348 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Bay Area | MI_Mission | SUNOL 1101 |  | 9.716 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Bay Area | NB_North Bay | CALISTOGA 1101 | 25 | 40.0153
Bay Area | NB_North Bay | CALISTOGA 1102 | 0 | 5.8994 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Bay Area | NB_North Bay | PUEBLO 2102 | 10 | 4.4071
Bay Area | NB_North Bay | PUEBLO 2103 | 2 | 0.86528
Bay Area | NB_North Bay | SILVERADO 2102 | 5 | 7.4244
Bay Area | NB_North Bay | SILVERADO 2103 | 5 | 1.9898
Bay Area | NB_North Bay | SILVERADO 2104 | 38 | 38.8934
Bay Area | NB_North Bay | SILVERADO 2105 | 10.5 | 6.1763
Bay Area | NB_North Bay | WOODACRE 1101 | 9 | 7.8461
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 10 | 27.8081
Bay Area | PE_Peninsula | WOODSIDE 1101 | 4.25 | 6.9832
Central Coast | CC_Central Coast | DEL MONTE 2103 | 12.83 | 3.5368
Central Coast | CC_Central Coast | DEL MONTE 2104 | 38 | 20.6488
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 1
Central Coast | CC_Central Coast | HATTON 1102 | 10.72 | 0.59094
Central Coast | CC_Central Coast | LAURELES 1111 | 52.2 | 41.6743
Central Coast | CC_Central Coast | LAURELES 1112 | 25.73
Central Coast | CC_Central Coast | RESERVATION ROAD 1101 | 7.3 | 6.7187
Central Coast | CC_Central Coast | ROB ROY 2104 | 1
Central Coast | CC_Central Coast | SAN BENITO 2104 | 1.7 | 0.7096
Central Coast | CC_Central Coast | VIEJO 2202 | 14.53 | 0.15962
Central Coast | DA_De Anza | LOS GATOS 1106 | 2.5
Central Coast | DA_De Anza | LOS GATOS 1107 | 5
Central Coast | LP_Los Padres | BUELLTON 1102 | 0.8 | 0.44073
Central Coast | LP_Los Padres | CAMBRIA 1101 | 0 | 1.1782 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Coast | LP_Los Padres | CHOLAME 2102 | 20 | 11.5476
Central Coast | LP_Los Padres | GOLDTREE 1105 | 7.1 | 7.2115
Central Coast | LP_Los Padres | GOLDTREE 1107 | 1.1 | 0.96746
Central Coast | LP_Los Padres | OCEANO 1104 | 7.2 | 5.3335
Central Coast | LP_Los Padres | OILFIELDS 1103 | 7.3 | 7.1437
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 39.5 | 40.0316
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 30 | 0.79717
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1108 | 1.2 | 2.1815
Central Coast | LP_Los Padres | SAN MIGUEL 1105 | 1 | 1.5204
Central Coast | LP_Los Padres | SANTA YNEZ 1101 | 6
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 6.6
Central Coast | LP_Los Padres | SISQUOC 1102 | 3.2 | 2.0977
Central Coast | LP_Los Padres | ZACA 1102 | 2.42
Central Valley | FR_Fresno | AUBERRY 1101 | 20 | 40.921
Central Valley | FR_Fresno | AUBERRY 1102 | 12
Central Valley | FR_Fresno | COPPERMINE 1104 | 8.15
Central Valley | FR_Fresno | DUNLAP 1102 | 14
Central Valley | FR_Fresno | DUNLAP 1103 | 17
Central Valley | FR_Fresno | KERCKHOFF 1101 | 17 | 5.2046
Central Valley | FR_Fresno | SAND CREEK 1103 | 10
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 5 | 56.8522
Central Valley | FR_Fresno | WISHON 1101 | 1.4833 | 1.5621
Central Valley | FR_Fresno | WOODWARD 2108 | 10 | 28.7831
Central Valley | KE_Kern | KERN OIL 1106 | 1 | 1.8063
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 1 | 49.4665
Central Valley | KE_Kern | TEJON 1102 | 1.6735 | 6.0767
Central Valley | ST_Stockton | CLAY 1101 | 13 | 22.488
Central Valley | ST_Stockton | CLAY 1102 | 1.17 | 0.54237
Central Valley | ST_Stockton | CORRAL 1101 | 9.7304 | 13.9008
Central Valley | ST_Stockton | ELECTRA 1101 | 11
Central Valley | ST_Stockton | ELECTRA 1102 | 21
Central Valley | ST_Stockton | FROGTOWN 1701 | 15 | 0.30954
Central Valley | ST_Stockton | IONE 1101 | 15.63 | 1.9748
Central Valley | ST_Stockton | MARTELL 1101 | 20 | 0.97768
Central Valley | ST_Stockton | MARTELL 1102 | 8.61
Central Valley | ST_Stockton | MARTELL 1103 | 10
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 20
Central Valley | ST_Stockton | OLETA 1101 | 15 | 66.3057
Central Valley | ST_Stockton | OLETA 1102 | 15
Central Valley | ST_Stockton | PINE GROVE 1102 |  | 0.44732 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Valley | ST_Stockton | STANISLAUS 1701 |  | 0.025048 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Valley | ST_Stockton | STANISLAUS 1702 | 2.3309 | 3.5956
Central Valley | ST_Stockton | TIGER CREEK 0201 | 0.39903 | 0.47901
Central Valley | ST_Stockton | WEST POINT 1102 | 9.6774 | 11.8572
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 15 | 18.3102
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 8
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 10 | 16.5673
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 10 | 134.4517
Central Valley | YO_Yosemite | CURTIS 1703 | 9.44 | 14.2716
Central Valley | YO_Yosemite | CURTIS 1704 | 10.4361 | 26.4115
Central Valley | YO_Yosemite | CURTIS 1705 | 4.5943 | 19.0887
Central Valley | YO_Yosemite | INDIAN FLAT 1104 | 16.74
Central Valley | YO_Yosemite | MARIPOSA 2101 | 17.8965 | 67.2647
Central Valley | YO_Yosemite | MARIPOSA 2102 | 15
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 0 | 14.2506 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Valley | YO_Yosemite | MIWUK 1701 | 0 | 0.65754 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Valley | YO_Yosemite | MIWUK 1702 | 1.3042 | 1.558
Central Valley | YO_Yosemite | OAKHURST 1101 | 7.7423 | 37.8084
Central Valley | YO_Yosemite | OAKHURST 1103 | 0 | 6.7102 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Central Valley | YO_Yosemite | PEORIA 1701 | 10
Central Valley | YO_Yosemite | PEORIA 1704 | 15 | 48.7393
Central Valley | YO_Yosemite | PEORIA 1705 | 5 | 2.0793
Central Valley | YO_Yosemite | RACETRACK 1703 | 5 | 0.083259
Central Valley | YO_Yosemite | RACETRACK 1704 | 5.7289 | 8.7955
Central Valley | YO_Yosemite | SAN JOAQUIN NO2 1103 | 1
Central Valley | YO_Yosemite | SO. CAL. EDISON NO3 1101 | 0 | 0.42465 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | BRIDGEVILLE 1101 | 8.679 | 9.7441
North Coast | HU_Humboldt | CLEAR LAKE 1101 |  | 0.29111 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | EEL RIVER 1102 | 26.82 | 16.7599
North Coast | HU_Humboldt | EEL RIVER 1103 | 3.23 | 2.2979
North Coast | HU_Humboldt | HIGHLANDS 1102 | 3.2064 | 3.377
North Coast | HU_Humboldt | HIGHLANDS 1103 | 0 | 10.4489 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | KONOCTI 1102 | 30 | 66.6108
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 25.5406 | 11.7109
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 20 | 19.6831
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 0 | 5.0146 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | NEWBURG 1131 | 8.33 | 0.085456
North Coast | HU_Humboldt | NEWBURG 1132 | 2.55 | 0.050611
North Coast | HU_Humboldt | NEWBURG 1133 | 4.59 | 0.016592
North Coast | HU_Humboldt | POTTER VALLEY P H 1105 | 12.305 | 16.3887
North Coast | HU_Humboldt | REDBUD 1101 | 0 | 2.3968 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | REDBUD 1102 |  | 0.24974 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | UPPER LAKE 1101 | 0 | 5.8053 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | HU_Humboldt | WILLITS 1104 | 22.19 | 37.6361
North Coast | SO_Sonoma | BELLEVUE 2103 | 1.5 | 1.3879
North Coast | SO_Sonoma | COTATI 1102 | 7 | 1.8667
North Coast | SO_Sonoma | COTATI 1105 | 2 | 3.9893
North Coast | SO_Sonoma | DUNBAR 1101 | 5 | 2.0381
North Coast | SO_Sonoma | DUNBAR 1102 | 7.174e-05 | 0.29845
North Coast | SO_Sonoma | DUNBAR 1103 |  | 7.174e-05 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 7.7 | 1.8984
North Coast | SO_Sonoma | FORT ROSS 1121 | 8
North Coast | SO_Sonoma | FULTON 1107 | 9 | 8.9718
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 0 | 4.1724 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Coast | SO_Sonoma | LAKEVILLE 1102 | 5 | 5.1898
North Coast | SO_Sonoma | MIRABEL 1101 | 3.1
North Coast | SO_Sonoma | MIRABEL 1102 | 3.8
North Coast | SO_Sonoma | MOLINO 1102 | 10 | 0.13878
North Coast | SO_Sonoma | MONTE RIO 1111 | 6 | 0.0018731
North Coast | SO_Sonoma | MONTE RIO 1112 | 2.1 | 0.17522
North Coast | SO_Sonoma | MONTE RIO 1113 | 6.2 | 0.64838
North Coast | SO_Sonoma | PENNGROVE 1101 | 4.5 | 1.7643
North Coast | SO_Sonoma | PETALUMA C 1108 | 7 | 5.1069
North Coast | SO_Sonoma | RINCON 1102 | 1
North Coast | SO_Sonoma | RINCON 1103 | 4.6 | 0.27729
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 1 | 1.8789
North Coast | SO_Sonoma | SANTA ROSA A 1111 | 1.5 | 0.60255
North Valley | NV_North Valley | BIG MEADOWS 2101 |  | 0.87556 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Valley | NV_North Valley | CLARK ROAD 1102 | 78.8 | 65.4292
North Valley | NV_North Valley | CORNING 1101 | 8.5 | 8.0317
North Valley | NV_North Valley | COTTONWOOD 1103 | 19.1 | 10.7165
North Valley | NV_North Valley | EAST QUINCY 1101 | 3.37 | 0.082427
North Valley | NV_North Valley | KESWICK 1101 | 25.4 | 19.5863
North Valley | NV_North Valley | OREGON TRAIL 1103 | 113 | 94.8094
North Valley | NV_North Valley | ORO FINO 1101 | 6.1 | 1.3178
North Valley | NV_North Valley | ORO FINO 1102 | 12 | 0.5739 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
North Valley | NV_North Valley | PANORAMA 1101 | 2.1 | 1.6814
North Valley | NV_North Valley | PARADISE 1101 | 0.54486 | 3.1943
North Valley | NV_North Valley | PARADISE 1102 | 0.39024 | 1.3999
North Valley | NV_North Valley | PARADISE 1103 | 4.6473 | 12.1154
North Valley | NV_North Valley | PARADISE 1104 | 6.2333 | 9.7948
North Valley | NV_North Valley | PARADISE 1105 | 0.24348 | 0.54488
North Valley | NV_North Valley | PARADISE 1106 | 2.3513 | 3.1502
North Valley | NV_North Valley | RED BLUFF 1104 | 9.6 | 2.7832
North Valley | NV_North Valley | SYCAMORE CREEK 1111 | 25 | 16.7412
North Valley | NV_North Valley | WYANDOTTE 1107 | 75.9 | 42.8986
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 0 | 3.6351 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SA_Sacramento | PUTAH CREEK 1103 | 0 | 0.33023 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SA_Sacramento | VACAVILLE 1111 | 5.35 | 7.2105
Sierra | SI_Sierra | APPLE HILL 1104 | 15.89 | 0.7072
Sierra | SI_Sierra | APPLE HILL 2102 | 127.12 | 28.9254
Sierra | SI_Sierra | BANGOR 1101 | 43.28 | 63.1661
Sierra | SI_Sierra | BELL 1107 | 31.4 | 16.5118
Sierra | SI_Sierra | BELL 1108 | 21.7 | 23.305
Sierra | SI_Sierra | BONNIE NOOK 1101 | 5.04
Sierra | SI_Sierra | BRUNSWICK 1102 |  | 1.6655 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | BRUNSWICK 1103 |  | 0.87489 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | BRUNSWICK 1105 | 4 | 1.4252
Sierra | SI_Sierra | BRUNSWICK 1106 | 7 | 7.2975
Sierra | SI_Sierra | BRUNSWICK 1110 |  | 0.0037881 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | CLARKSVILLE 2103 |  | 0.73658 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | CLARKSVILLE 2104 |  | 2.3348 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 4.4
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 |  | 0.90775 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 35.2 | 7.8351
Sierra | SI_Sierra | DIAMOND SPRINGS 1107 | 0 | 3.1844 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | EL DORADO PH 2101 | 18.78 | 4.5135
Sierra | SI_Sierra | FORESTHILL 1101 | 15.89
Sierra | SI_Sierra | FORESTHILL 1102 | 8.5 | 0.6021 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | GRASS VALLEY 1103 | 1.6 | 0.11888
Sierra | SI_Sierra | NARROWS 2102 | 24.43 | 31.9958
Sierra | SI_Sierra | PENRYN 1103 | 12.57 | 17.4794
Sierra | SI_Sierra | SHINGLE SPRINGS 1104 | 0 | 0.48725 | Work completed in 2020 and WV Claimed in 2020 on this circuit were along portions of the Circuit that were considered "Carry Over" from prior year work.
Sierra | SI_Sierra | WISE 1102 | 9.91 | 15.531
SELECT
CM.REGION
,CM.DIVISION
,CM.CIRCUITNAME AS CIRCUIT
,P20.[Planned 2020 Mileage__4/8/2020] AS [2020 Planned Mileage]
,SUM(C.NET_2020_WV_MILES) AS WV_CLAIMED_MILES
FROM EVM_CONDUCTORINSPECTION_MASTER_20210105 CM
LEFT JOIN [EVM_V8].[dbo].[DIM_2020EVMCircuitList] P20 ON CM.CIRCUITNAME = P20.Circuit
LEFT JOIN rpt_EVM_CLEAR_MILES_2020 C ON CM.UNIQUE_SEGMENT_ID = C.UNIQUE_SEGMENT_ID_V8
WHERE (C.UNIQUE_SEGMENT_ID_V8 IS NOT NULL OR P20.[Part of 2020 Plan] = 'Y')
GROUP BY CM.REGION
,CM.DIVISION
,CM.CIRCUITNAME
,P20.[Planned 2020 Mileage__4/8/2020]
ORDER BY 1,2,3