## Summary
PACIFICORP VEGETATION MANAGEMENT
2020 MAIN GRID TRANSMISSION PROGRESS REPORT
Through Jan 2, 2021
STATE SUMMARY
Cycle Work
| TOTAL | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Goal | Ahead/Behind
| 7633.64 | 51.4 | 51.65 | 51.4 | 0.25
State
California | 129.4 | 11.6 | 11.9 | 11.6 | 0.3
Idaho | 1149.55 | 0 | 0 | 0 | 0
Misc States | 70.05 | 0 | 0 | 0 | 0
Montana | 137.16 | 0 | 0 | 0 | 0
Oregon | 1168.58 | 25.6 | 25.5 | 25.6 | -0.1
Utah | 2621.08 | 14.2 | 14.25 | 14.2 | 0.05
Washington | 282.67 | 0 | 0 | 0 | 0
Wyoming | 2075.15 | 0 | 0 | 0 | 0
TOTAL | 7633.64 | 51.4 | 51.65 | 51.4 | 0.25
FORESTER SUMMARY
| TOTAL | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Goal | Ahead/Behind
| 7633.64 | 51.4 | 51.65 | 51.4 | 0.25
Forester
Housholder/Koetsier | 480.11 | 0 | 0 | 0 | 0
Evans/Spicer | 2114.91 | 9.2 | 9.25 | 9.2 | 0.05
Sorensen/O'Malley | 109.53 | 1 | 1 | 1 | 0
Hooley/Arritola | 281.59 | 0 | 0 | 0 | 0
Phillips/Russell | 481.88 | 37.2 | 37.4 | 37.2 | 0.2
Vanderhoof/Cherry | 3828.55 | 4 | 4 | 4 | 0
Feldman/Dudik | 337.07 | 0 | 0 | 0 | 0
Total | 7633.64 | 51.4 | 51.65 | 51.4 | 0.25
Weeks
52

## Pacific-Rocky
PACIFICORP VEGETATION MANAGEMENT
2020 MAIN GRID TRANSMISSION PROGRESS REPORT
Pacific Power - Rocky Mountain Power
Through Jan 2, 2021
STATE SUMMARY
Cycle Work
| TOTAL | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Goal | Ahead/Behind
| 7633.64 | 68.07 | 67.65 | 68.07 | -0.42
Pacific
California | 129.4 | 11.6 | 11.9 | 11.6 | 0.3
Oregon | 1168.58 | 25.6 | 25.5 | 25.6 | -0.1
Washington | 282.67 | 0 | 0 | 0 | 0
Total | 1580.65 | 37.2 | 37.4 | 37.2 | 0.2
State/Rocky Mt
Idaho | 1149.55 | 0 | 0 | 0 | 0
Misc States | 70.05 | 0 | 0 | 0 | 0
Montana | 137.16 | 0 | 0 | 0 | 0
Utah | 2621.08 | 14.2 | 14.25 | 14.2 | 0.05
Wyoming | 2075.15 | 16.67 | 16 | 16.67 | -0.67
Total | 6052.99 | 30.87 | 30.25 | 30.87 | -0.62
FORESTER SUMMARY
| TOTAL | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Goal | Ahead/Behind
| 7633.64 | 68.07 | 67.65 | 68.07 | -0.42
Forester/Pacific
Housholder/Koetsier | 480.11 | 0 | 0 | 0 | 0
Hooley/Arritola | 281.59 | 0 | 0 | 0 | 0
Phillips/Russell | 481.88 | 37.2 | 37.4 | 37.2 | 0.2
Feldman/Dudik | 337.07 | 0 | 0 | 0 | 0
Total | 1580.65 | 37.2 | 37.4 | 37.2 | 0.2
Forester/Rocky Mt
Evans/Spicer | 2114.91 | 9.2 | 9.25 | 9.2 | 0.05
Sorensen/O'Malley | 109.53 | 1 | 1 | 1 | 0
Vanderhoof/Cherry | 3828.55 | 20.67 | 20 | 20.67 | -0.67
Total | 6052.99 | 30.87 | 30.25 | 30.87 | -0.62

## California
California 2020 Main Grid Transmission Report
Through Jan 2, 2021
Cycle Work
Phillips/Russell |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 129.4 | 11.6 | 11.9 | 11.6 | 0.3
KFC668059 | Copco II 230kV Ln #59 (CA) (MG) | 4.92 |  |  | 0 | 0
KFC668064 | Malin-Indian Springs 500kV Ln#64(CA)(MG) | 46.92 | 7.9 | 7.9 | 7.9 | 0
YRE668014 | Copco 2-Delta 115kV Ln #14 (MG) | 77.56 | 3.7 | 4 | 3.7 | 0.3
| California Total | 129.4 | 11.6 | 11.9 | 11.6 | 0.3

## Idaho
Idaho 2020 Main Grid Transmission Report
Through Jan 2, 2021
IDAHO MAIN GRID WORK
Cycle Work
Vanderhoof/Cherry |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 1149.55 | 0 | 0 | 0 | 0
PRE065001 | Populus-Borah #2 345kV Ln (ID) (MG) | 47.12 |  |  | 0 | 0
PRE065002 | Bridger-Goshen Lp-3mile Knoll 345kV (MG) | 0.35 |  |  | 0 | 0
PRE065003 | Populus-Ben Lomond East 345kV (ID) (MG) | 23.22 |  |  | 0 | 0
PRE074001 | Grace-Goshen 161kV Ln (MG) | 57.22 |  |  | 0 | 0
PRE075001 | Grace-Ben Lomond 138kV 103-104Ln(ID)(MG) | 42.27 |  |  | 0 | 0
PRE076001 | Grace-Ben Lomond 138kV 105 Ln (ID) (MG) | 42.09 |  |  | 0 | 0
PRE076003 | Wheelon-American Falls 138kV Ln (ID)(MG) | 37.36 |  |  | 0 | 0
PRE076010 | Treasureton-Franklin 138kV Ln (MG) | 10.43 |  |  | 0 | 0
PRE076011 | Franklin-Smithfield 138kV Ln (ID) (MG) | 7.05 |  |  | 0 | 0
PRE076014 | Amer Falls-Malad Str#460 138kV (MG) | 28.27 |  |  | 0 | 0
PRE084001 | Populus-Ben Lomond West DC 345kV Ln (MG) | 23.22 |  |  | 0 | 0
PRE084002 | Populus-Kinport 345kV Ln (ID) (MG) | 40.26 |  |  | 0 | 0
PRE084003 | Populus-Borah #1 345kV Ln (ID) (MG) | 46.46 |  |  | 0 | 0
PRE092001 | Sunbeam-Treasureton 230kV Ln (MG) | 66.04 |  |  | 0 | 0
PRE092003 | Brady-Sunbeam 230kV Ln (MG) | 7 |  |  | 0 | 0
PRE096000 | Naughton-Treasureton 230kV Ln (ID) (MG) | 47.74 |  |  | 0 | 0
PRE335033 | Jim Bridger-Populus #2 345kV Ln (ID) (MG) | 68.3 |  |  | 0 | 0
PRE335034 | Jim Bridger-Populus #1 345kV Ln (ID) (MG) | 68.25 |  |  | 0 | 0
REX063000 | Antelope-Lost River 230kV Ln (MG) | 31.42 |  |  | 0 | 0
REX074002 | Goshen-Rigby 161kV Ln (MG) | 30.97 |  |  | 0 | 0
REX074004 | Goshen-Antelope 161kV Ln (MG) | 19.85 |  |  | 0 | 0
REX074005 | Goshen-Sugar Mill 161kV Ln (MG) | 16.55 |  |  | 0 | 0
REX074006 | Sugarmill-Rigby 161kV Ln (MG) | 16.69 |  |  | 0 | 0
REX074007 | Goshen-Bonneville 161kV Ln (MG) | 20.1 |  |  | 0 | 0
REX074008 | Goshen-Big Grassy 161kV Ln (MG) | 50.04 |  |  | 0 | 0
REX074015 | Rigby-Jefferson 161kV Ln (MG) | 17.51 |  |  | 0 | 0
REX074016 | Goshen-Antelope Str #174 161kV (MG) | 24.8 |  |  | 0 | 0
REX074017 | Big Grassy-Mt State 161kV (MG) | 40.54 |  |  | 0 | 0
REX084000 | Goshen-Kinport 345kV Ln (MG) | 41 |  |  | 0 | 0
REX084004 | Bridger-Goshen 345kV (ID)#802 (MG) | 101.71 |  |  | 0 | 0
REX089000 | Antelope-Bannack Pass 230kV Ln (MG) | 75.72 |  |  | 0 | 0
| Idaho Total | 1149.55 | 0 | 0 | 0 | 0

## Misc States
Misc States 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
Evans/Spicer |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 70.05 | 0 | 0 | 0 | 0
MAZ728003 | Sigurd-Glen Canyon 230kV Ln (AZ) (MG) | 10.37 |  |  | 0 | 0
MCO090001 | Camp Williams-Four Corners 345kV(CO)(MG) | 27.6 |  |  | 0 | 0
MNM091001 | Camp Williams-Four Corners 345kV(NM)(MG) | 32.08 |  |  | 0 | 0
| Misc States Total | 70.05 | 0 | 0 | 0 | 0

## Montana
Montana 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
Vanderhoof/Cherry |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 137.16 | 0 | 0 | 0 | 0
CAM437090 | Yellowtail-Casper 230kV Ln (MT) (MG) | 39.17 |  |  | 0 | 0
CAM437095 | Yellowtail-Thermopolis 230kV Ln (MT) (MG) | 52.46 |  |  | 0 | 0
CAM437098 | Rimrock-Yellowtail (MPC)161kV (MG) | 45.53 |  |  | 0 | 0
| Montana Total | 137.16 | 0 | 0 | 0 | 0

## Oregon
Oregon 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
|  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 1168.58 | 25.6 | 25.5 | 25.6 | -0.1
ALB067090 | Bethel-Fry 230kV MG Veg Mgt | 26.23 |  |  | 0 | 0
ALB067091 | Fry-Alvey 230kV MG Veg Mgt | 44.94 |  |  | 0 | 0
BEN063077 | Corral-Ochoco #1 230kV MG Veg Mgt | 11.2 |  |  | 0 | 0
BEN063080 | Corral-PAC Ponderosa 230kV MG Veg Mgt | 0.2 |  |  | 0 | 0
BEN063081 | Coral-BPA Ponderosa #2 230kV MG Veg Mgt | 0.23 |  |  | 0 | 0
BEN068219 | OR/ID-Summer Lake 500kV Ln#80 Veg Mgt | 217.67 |  |  | 0 | 0
ROS068063(shares w Josh) | Alvey-Dixonville 230kV #63 MG Veg Mgt | 18.4 |  |  | 0 | 0
ROS068090(shares w Tony) | Alvey-Dixonville 500kV #90 MG Veg Mgt | 18.2 |  |  | 0 | 0
Feldman/Dudik | Total | 337.07 | 0 | 0 | 0 | 0
COO062090 | Fairview-Isthmus 230kV MG Veg Mgt | 11.87 |  |  | 0 | 0
GRA068072 | GPass-Dixonville 230 #72 MG Veg Mgt(GRA) | 24.08 |  |  | 0 | 0
GRA068091 | Dixonville-Meridian500#91MG Veg Mgt(GRA) | 36.85 |  |  | 0 | 0
MED068071 | Meridian-Grants Pass 230 #71 MG Veg Mgt | 34.68 |  |  | 0 | 0
ROS068020 | Dixonville-Reston 230kV #20 MG Veg Mgt | 17.4 |  |  | 0 | 0
ROS068063(shares w Tony) | Alvey-Dixonville 230kV #63 MG Veg Mgt | 41 |  |  | 0 | 0
ROS068072 | GPass-Dixonville 230 #72 MG Veg Mgt(ROS) | 37.66 |  |  | 0 | 0
ROS068090(shares w Josh) | Alvey-Dixonville 500kV #90 MG Veg Mgt | 39.75 |  |  | 0 | 0
ROS068091 | Dixonville-Meridian500#91MG Veg Mgt(ROS) | 36.85 |  |  | 0 | 0
ROS068096 | Dixonvlle230-Dixonvlle500#96 MG Veg Mgt | 1.45 |  |  | 0 | 0
Hooley/Arritola | Total | 281.59 | 0 | 0 | 0 | 0
KLA068052 | Yamsay-K Falls 230kV #52 MG Veg Mgt | 62.5 | 4.3 | 4.3 | 4.3 | 0
KLA068059 | Lone Pine-K Falls 230kV #59 MG Veg Mgt | 71.1 | 3 | 3 | 3 | 0
KLA068064 | Malin-IndianSprngs500#64(OR) MG Veg Mgt | 0.49 |  |  | 0 | 0
KLA068070 | Klamath Falls-Malin230kV #70 MG Veg Mgt | 34.54 |  |  | 0 | 0
KLA068080 | Summer Lake-Malin 500kV #80 MG Veg Mgt | 75.12 | 10.1 | 10 | 10.1 | -0.1
KLA068081 | Capt Jack-Meridan 500kV #81 MG Veg Mgt | 91.22 | 6 | 6 | 6 | 0
KLA068097 | Malin-Captain Jack 500kV #97 MG Veg Mgt | 6.93 |  |  | 0 | 0
MED068054 | Lone Pine-Meridian 230kV #54 MG Veg Mgt | 5.23 |  |  | 0 | 0
MED068218 | Meridian-New Lone Pine230 #2 MG Veg Mgt | 5.35 | 2.2 | 2.2 | 2.2 | 0
Phillips/Russell | Total | 352.48 | 25.6 | 25.5 | 25.6 | -0.1
AST061084 | Tillamook-Astoria 115kV MG Veg Mgt | 58.13 |  |  | 0 | 0
POR067140 | Troutdale-PGE Gresham 230kV MG Veg Mgt | 6.94 |  |  | 0 | 0
POR067181 | Merwin-St Johns 115kV (OR) MG Veg Mgt | 1.61 |  |  | 0 | 0
POR067195 | Troutdale-Linneman 230kV MG Veg Mgt | 6.44 |  |  | 0 | 0
POR067202 | Columbia-Killingsworth 115kV MG Veg Mgt | 3.8 |  |  | 0 | 0
WWO0067391 | McNary-Wallula 230kV (OR) MG Veg Mgt | 22.22 |  |  | 0 | 0
WWO064061 | WallaWalla-Hells Cnyn230(OR) MG Veg Mgt | 74.25 |  |  | 0 | 0
WWO067382 | McNary-Walla Walla 230kV(OR) MG Veg Mgt | 23.98 |  |  | 0 | 0
WWO067384 | BPA Dalreed Tap 230kV MG Veg Mgt | 0.07 |  |  | 0 | 0
Housholder/Koetsier | Total | 197.44 | 0 | 0 | 0 | 0
| Oregon Total | 1168.58 | 25.6 | 25.5 | 25.6 | -0.1

## Utah
Utah 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
|  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 2621.08 | 14.2 | 14.25 | 14.2 | 0.05
AME067004 | Camp Williams-Spanish Fork 345kV Ln (MG) | 35 | 0.25 | 0.3 | 0.25 | 0.05
AME067006 | Huntington-Spanish Fork 345kV St Ln (MG) | 78.47 | 2.5 | 2.5 | 2.5 | 0
AME067009 | Camp Williams-Mona 345kV Ln #2 (MG) | 46.74 |  |  | 0 | 0
AME067012 | Emery-Camp Williams 345kV St Ln (MG) | 120.52 | 2.5 | 2.5 | 2.5 | 0
AME067077 | Current Creek SwYard-Mona 345kV Ln (MG) | 0.37 |  |  | 0 | 0
AME067078 | Clover-Limber 345kV Ln (MG) | 54 |  |  | 0 | 0
AME067079 | Camp Williams-Mona #4 345kV Ln (MG) | 46.54 |  |  | 0 | 0
AME067389 | Camp Williams-Steel Mill | 20.8 | 0.1 | 0.1 | 0.1 | 0
AME078005 | Spanish Fork-Carbon #1 138kV Ln (MG) | 54.22 |  |  | 0 | 0
AME078012 | Spanish Fork-Carbon #2 138kV Ln (MG) | 52.08 | 0.1 | 0.1 | 0.1 | 0
AME078017 | Carbon-Ashley 138kV Ln (MG) | 91.46 | 2 | 2 | 2 | 0
AME078019 | Ashley-Vernal USBR 138kV Ln (MG) | 11.7 |  |  | 0 | 0
AME099002 | Camp Williams-Mona 345kV Ln #1 (MG) | 46.26 |  |  | 0 | 0
AME099005 | Clover-Mona #1 345kV (MG) | 3 |  |  | 0 | 0
AME099006 | Clover-Mona #2 345kV (MG) | 3 |  |  | 0 | 0
PRC099001 | Camp Williams-Four Corners 345kV(UT)(MG) | 311.14 | 1 | 1 | 1 | 0
RIC067005 | Huntington-Sigurd 345kV St Ln (MG) | 94 |  |  | 0 | 0
RIC067008 | Emery-Sigurd 345kV Ln #2 (MG) | 74.74 | 0.25 | 0.25 | 0.25 | 0
RIC067015 | Sigurd-Red Butte 345kV Ln (MG) | 156.6 |  |  | 0 | 0
RIC067016 | Red Butte-Nevada 345kV Ln (MG) | 33.78 |  |  | 0 | 0
RIC067390 | Sigurd-Red Butte #2 345kV MG Veg Mgt | 169.6 |  |  | 0 | 0
RIC068000 | Sigurd-West Cedar 230kV Ln (MG) | 117.15 |  |  | 0 | 0
RIC069000 | Sigurd-Nevada State Line 230kV Ln (MG) | 140.66 |  |  | 0 | 0
RIC093003 | Sigurd-Glen Canyon 230kV Ln (UT) (MG) | 149.03 | 0.5 | 0.5 | 0.5 | 0
RIC099003 | Clover-Sigurd #1 345kV (MG) | 67 |  |  | 0 | 0
RIC099004 | Clover-Sigurd #2 345kV (MG) | 67 |  |  | 0 | 0
Evans/Spicer | Total | 2044.86 | 9.2 | 9.25 | 9.2 | 0.05
AME067388 | Limber-Oquirrh 345kV Ln (MG) | 46 |  |  | 0 | 0
MET067007 | Terminal-Ninety South 345kV DC St Ln(MG) | 15.79 |  |  | 0 | 0
MET067010 | Camp Williams-90th So #1 - #2 345kV Ln (MG) | 10.65 |  |  | 0 | 0
MET067011 | Terminal-Camp Williams 345kV DC St (MG) | 26.44 |  |  | 0 | 0
MET067201 | Camp Williams-90th So #3 - #4 345kV Ln (MG) | 10.65 | 1 | 1 | 1 | 0
Sorensen/O'Malley | Total | 109.53 | 1 | 1 | 1 | 0
AME888090 | Rock Springs-Flaming Gorge 230kV (UT) (MG) | 6.95 |  |  | 0 | 0
MET067002 | Ben Lomond-Terminal East DC 345kV Ln (MG) | 46.6 |  |  | 0 | 0
MET067013 | Populus-Ben Lomond 345kV Ln (UT) (MG) | 13.77 |  |  | 0 | 0
MET067198 | Populus-Ben Lomond West 345kV Ln (MG) | 85.72 |  |  | 0 | 0
MET067199 | Ben Lomond-Terminal W DC 345kV Ln (MG) | 46.6 |  |  | 0 | 0
MET078001 | Grace-Ben Lomond 138kV Ln 105 (UT) (MG) | 49.21 |  |  | 0 | 0
MET078002 | Grace-Ben Lomond 138kV Ln103-104(UT)(MG) | 48.67 |  |  | 0 | 0
MET078003 | Wheelon-American Falls 138kV Ln (UT)(MG) | 14.44 |  |  | 0 | 0
MET093001 | Naughton-Ben Lomond 230kV Ln #1(UT) (MG) | 58.85 | 2 | 2 | 2 | 0
MET093005 | Naughton-Ben Lomond 230kV Ln #2(UT) (MG) | 58.68 | 2 | 2 | 2 | 0
SMI078010 | Wheelon-Smithfield 138kV Ln (MG) | 12.49 |  |  | 0 | 0
SMI078041 | Franklin-Smithfield 138kV Ln (UT) (MG) | 11.6 |  |  | 0 | 0
SMI093004 | Naughton-Treasureton 230kV Ln (UT) (MG) | 0.95 |  |  | 0 | 0
SMI093006 | Birch Creek-Railroad 230kV Ln (UT) (MG) | 12.16 |  |  | 0 | 0
Vanderhoof/Cherry | Total | 466.69 | 4 | 4 | 4 | 0
| Utah Total | 2621.08 | 14.2 | 14.25 | 14.2 | 0.05

## Washington
Washington 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
Householder/Koetsier |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 282.67 | 0 | 0 | 0 | 0
POW238040 | Swift 1-Swift 2 230kV(Cougar)MG Veg Mgt | 3.06 |  |  | 0 | 0
POW238041 | Swift 2-BPA Wdland (Speelyai)MG Veg Mgt | 23 |  |  | 0 | 0
POW238080 | Merwin-Kalama-Cardwell 115kV MG Veg Mgt | 16.28 |  |  | 0 | 0
POW238081 | Merwin-St Johns 115kV (WA) MG Veg Mgt | 28.17 |  |  | 0 | 0
POW238088 | Merwin-Yale 115Kv (Lake) MG Veg Mgt | 10.8 |  |  | 0 | 0
WAL238043 | WallaWalla-Lewistn230(Alpowa)MG Veg Mgt | 44.88 |  |  | 0 | 0
WAL238044 | Walla Walla-Wanapum 230kV MG Veg Mgt | 33.33 |  |  | 0 | 0
WAL238076 | Walla Walla-Hells Cnyn230(WA)MG Veg Mgt | 5.4 |  |  | 0 | 0
WAL238094 | McNary-Walla Walla 230kV(WA) MG Veg Mgt | 32.32 |  |  | 0 | 0
WAL238110 | McNary-Wallula 230kV (WA) MG Veg Mgt | 6.92 |  |  | 0 | 0
YAK238042 | Union Gap-BPA Midway 230kV MG Veg Mgt | 40.11 |  |  | 0 | 0
YAK238096 | Pomona-Wanapum 230kV MG Veg Mgt | 38.4 |  |  | 0 | 0
YAK238103 | Pomona-Union Gap 230kV MG Veg Mgt | 8.56
| Washington Total | 282.67 | 0 | 0 | 0 | 0

## Wyoming
Wyoming 2020 Main Grid Transmission Report
Through Jan 2, 2021
MAIN GRID WORK
Cycle Work
Vanderhoof/Cherry |  | Total | Line Miles | Line Miles | Line Mile | Line Miles
|  | Line Miles | Scheduled | Completed | Goal | Ahead/Behind
Work Order | Description | 2075.15 | 16.67 | 16 | 16.67 | -0.67
CAS540080 | Hilltop-Worland(WAPA) 115kV Ln (MG) | 7.84 |  |  | 0 | 0
CAS540081 | DJ-Spence(WAPA) 230kV Ln (MG) | 31.1 |  |  | 0 | 0
CAS540082 | Dave Johnston-USBR 115kV East Ln-So (MG) | 1.41 |  |  | 0 | 0
CAS540083 | Windstar-Latigo 230kV Ln (MG) | 8.33 |  |  | 0 | 0
CAS540086 | Windstar-Dave Johnston 230kV Ln (MG) | 1.3 |  |  | 0 | 0
CAS540090 | Yellowtail-Casper 230kV Ln (WY) (MG) | 169.36 |  |  | 0 | 0
CAS540092 | Yellowtail-Thermopolis 230kV Ln (WY)(MG) | 123.1 |  |  | 0 | 0
CAS540095 | Thermopolis-Riverton 230kV Ln (MG) | 50.81 |  |  | 0 | 0
CAS540096 | Casper-Riverton 230kV Line (MG) | 110.42 |  |  | 0 | 0
CAS540097 | Dave Johnston-Miners 230kV Ln (MG) | 88.99 | 12 | 12 | 12 | 0
CAS540102 | Dave Johnston-USBR 115kV West Ln-No(MG) | 1.41 |  |  | 0 | 0
CAS540112 | Wyodak-Buffalo 230kV Ln (MG) | 69.14 |  |  | 0 | 0
CAS540115 | DJ-Yellowcake-Reno 230kV Ln (MG) | 68.55 |  |  | 0 | 0
CAS540120 | Wyodak Plant-Sub 230kV Tie Ln (MG) | 0.17 |  |  | 0 | 0
CAS540121 | Wyodak Plt-Sub 69kV Tie Line (MG) | 0.15 |  |  | 0 | 0
CAS540133 | (WAPA)Casper-Casper 115kV Line (MG) | 2.33 | 2.33 | 2 | 2.33 | -0.33
CAS540134 | Casper-Casper (WAPA) 69kV Tie Ln (MG) | 2.34 | 2.34 | 2 | 2.34 | -0.34
CAS540137 | Thermopolis-(USBR) 115kV Tie Ln #1 (MG) | 0.14 |  |  | 0 | 0
CAS540152 | Foote Creek-Miners 230kV Ln (MG) | 28.8 |  |  | 0 | 0
CAS540160 | Thermopolis-Hilltop 115kV Ln (MG) | 32.97 |  |  | 0 | 0
CAS540161 | Thermopolis-(WAPA)Thermop 115 Tie #2(MG) | 0.14 |  |  | 0 | 0
CAS540168 | Casper-Latigo 230kV (MG) | 21.33 |  |  | 0 | 0
EVA094001 | Naughton-Ben Lomond 230kV Ln #1 (WY)(MG) | 29.21 |  |  | 0 | 0
EVA094002 | Naughton-Ben Lomond 230kV Ln #2 (WY)(MG) | 29.18 |  |  | 0 | 0
EVA094004 | Birch Creek-Railroad 230kV Ln (WY) (MG) | 7.05 |  |  | 0 | 0
EVA094005 | Naughton-Chappel Creek 230kV Ln (MG) | 45.83 |  |  | 0 | 0
EVA094006 | Craven Creek-Pioneer 230kV Ln (MG) | 5 |  |  | 0 | 0
EVA094007 | Chappel Creek-Jonah Field 230kV Ln (MG) | 32.13 |  |  | 0 | 0
EVA097000 | Naughton-Treasureton 230kV Ln(WY) (MG) | 30.89 |  |  | 0 | 0
ROC094008 | Chappel-Chimney Butte 230kV Ln (MG) | 34.62 |  |  | 0 | 0
ROC094009 | Lima-Roberson 230kV Ln (MG) | 1.5 |  |  | 0 | 0
ROC094014 | Arrowhead-Fire Hole 230kV (MG) | 8.9 |  |  | 0 | 0
ROC094015 | Chimney-Butte-Riley Ridge 230kV (MG) | 16.01 |  |  | 0 | 0
ROC540089 | Monument-Craven Creek 230kV (MG) | 19.8 |  |  | 0 | 0
ROC540093 | Naughton-Rock Springs 230kV Ln (MG) | 71.39 |  |  | 0 | 0
ROC540094 | Rock Springs-Atlantic City 230kV Ln (MG) | 68.82 |  |  | 0 | 0
ROC540098 | Riverton-Atlantc Cty-Columbia Gen230(MG) | 50.14 |  |  | 0 | 0
ROC540099 | Rock Springs-Flaming Gorge 230kV(WY)(MG) | 47.68 |  |  | 0 | 0
ROC540101 | Point of Rocks-Rock Springs 230kV (MG) | 26.62 |  |  | 0 | 0
ROC540106 | Jim Bridger-Populus #2 345kV Ln (WY)(MG) | 125.25 |  |  | 0 | 0
ROC540107 | Jim Bridger-Populus #1 345kV Ln (WY) (MG) | 125.28 |  |  | 0 | 0
ROC540111 | Palisades SW Sta-Bridger Pump 230kV (MG) | 9.26 |  |  | 0 | 0
ROC540114 | Jim Bridger-Point of Rocks230kV Ln#1(MG) | 9.34 |  |  | 0 | 0
ROC540123 | Jim Bridger-Point of Rocks230kV Ln#2(MG) | 9.34 |  |  | 0 | 0
ROC540127 | Blue Rim-South Trona 230kV Line (MG) | 13.3 |  |  | 0 | 0
ROC540139 | Monument-Exxon 230kV Ln (MG) | 12.68 |  |  | 0 | 0
ROC540144 | Firehole-Mansface 230kV Ln (MG) | 11.99 |  |  | 0 | 0
ROC540145 | Monument-South Trona 230kV Ln (MG) | 19.39 |  |  | 0 | 0
ROC540148 | Jim Bridger-Mustang 230kV Ln (MG) | 72.96 |  |  | 0 | 0
ROC540150 | Mustang-Spence(WAPA) 230kV Ln (MG) | 76.57 |  |  | 0 | 0
ROC540175 | Point of Rocks-Standpipe 230kV (MG) | 120.7 |  |  | 0 | 0
ROC540176 | Bridger-Goshen 345kV (WY)#802 (MG) | 124.19 |  |  | 0 | 0
| Wyoming Total | 2075.15 | 16.67 | 16 | 16.67 | -0.67