## Summary
PACIFICORP VEGETATION MANAGEMENT 2020 LOCAL TRANSMISSION PROGRESS REPORT
Summary
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK | [5 empty] | INTERIM WORK
| Total | Total Miles | Line Miles | Line Mile | Miles | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Goal | Ahead/Behind
| 8190.88 | 1697.7 | 1601 | 1697.7 | -96.7 | 376.59 | 404.59 | 376.59 | 28
State
California | 571.82 | 9.7 | 6 | 9.7 | -3.7 | 50.59 | 50.59 | 50.59 | 0
Idaho | 818.4 | 261 | 261 | 261 | 0 | 0 | 0 | 0 | 0
Oregon | 1819.65 | 40 | 36 | 40 | -4 | 326 | 354 | 326 | 28
Utah | 3972.48 | 1262 | 1183 | 1262 | -79 | 0 | 0 | 0 | 0
Washington | 325.65 | 47 | 16 | 47 | -31 | 0 | 0 | 0 | 0
Wyoming | 682.88 | 78 | 99 | 78 | 21 | 0 | 0 | 0 | 0
Total | 8190.88 | 1697.7 | 1601 | 1697.7 | -96.7 | 376.59 | 404.59 | 376.59 | 28
SUMMARY OF WORK BY FORESTER
| Total | Total Miles | Line Miles | Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 8190.88 | 2074.29 | 1862.59 | 2074.29 | -211.7
Forester
Feldman/Dudik | 499.44 | 147 | 83 | 147 | -64
Evans/Spicer | 2759.16 | 725 | 723 | 725 | -2
Sorensen/O'Malley | 518.72 | 317 | 317 | 317 | 0
Hooley/Arritola | 775.54 | 181.59 | 197.59 | 181.59 | 16
Phillips/Russell | 851.35 | 13.7 | 7 | 13.7 | -6.7
Vanderhoof/Cherry | 2195.88 | 559 | 360 | 559 | -56
Housholder/Koetsier | 590.79 | 131 | 175 | 131 | 44
Total | 8190.88 | 2074.29 | 1862.59 | 2074.29 | -68.7
Weeks
52

## Pacific-Rocky
PACIFICORP VEGETATION MANAGEMENT 2020 LOCAL TRANSMISSION PROGRESS REPORT
Pacific Power - Rocky Mountain Power
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK | [5 empty] | INTERIM WORK
| Total | Total Miles | Line Miles | Line Mile | Miles | Line Miles | Line Miles | Line Miles | Line Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Goal | Ahead/Behind
| 8190.88 | 1697.7 | 1601 | 1697.7 | -96.7 | 376.59 | 404.59 | 376.59 | 28
Pacific
California | 571.82 | 9.7 | 6 | 9.7 | -3.7 | 50.59 | 50.59 | 50.59 | 0
Oregon | 1819.65 | 40 | 36 | 40 | -4 | 326 | 354 | 326 | 28
Washington | 325.65 | 47 | 16 | 47 | -31
Total | 2717.12 | 96.7 | 58 | 96.7 | -38.7 | 376.59 | 404.59 | 376.59 | 28
Rocky Mt
Idaho | 818.4 | 261 | 261 | 261 | 0
Utah | 3972.48 | 1262 | 1183 | 1262 | -79
Wyoming | 682.88 | 78 | 99 | 78 | 21
Total | 5473.76 | 1601 | 1543 | 1601 | -58 | 0 | 0 | 0 | 0
SUMMARY OF WORK BY FORESTER
| Total | Total Miles | Line Miles | Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 8190.88 | 2074.29 | 2005.59 | 2074.29 | -68.7
Forester/Pacific
Feldman/Dudik | 499.44 | 147 | 83 | 147 | -64
Hooley/Arritola | 775.54 | 181.59 | 197.59 | 181.59 | 16
Phillips/Russell | 851.35 | 13.7 | 7 | 13.7 | -6.7
Housholder/Koetsier | 590.79 | 131 | 175 | 131 | 44
Total | 2717.12 | 473.29 | 462.59 | 473.29 | -10.7
Forester/Rocky Mt
Evans/Spicer | 2759.16 | 725 | 723 | 725 | -2
Sorensen/O'Malley | 518.72 | 317 | 317 | 317 | 0
Vanderhoof/Cherry | 2195.88 | 559 | 503 | 559 | -56
Total | 5473.76 | 1601 | 1543 | 1601 | -58

## California
California Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK | [5 empty] | INTERIM WORK
| District | Total Miles | Line Miles | Line Mile | Miles | Line Miles | Line Miles | Line Miles | Line Miles
Total California | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Goal | Ahead/Behind
| 571.82 | 9.7 | 6 | 9.7 | -3.7 | 50.59 | 50.59 | 50.59 | 0
Hooley/Arritola
California | 102.05 |  |  | 0 | 0 | 50.59 | 50.59 | 50.59 | 0
Total | 102.05 | 0 | 0 | 0 | 0 | 50.59 | 50.59 | 50.59 | 0
Phillips/Russell
California | 469.77 | 9.7 | 6 | 9.7 | -3.7 |  |  | 0 | 0
Total | 469.77 | 9.7 | 6 | 9.7 | -3.7 | 0 | 0 | 0 | 0
Total California | 571.82 | 9.7 | 6 | 9.7 | -3.7 | 50.59 | 50.59 | 50.59 | 0

## Idaho
Idaho Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK
| District | Total Miles | Line Miles | Line Mile | Miles
Total Idaho | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
Vanderhoof/Cherry | 818.4 | 261 | 261 | 261 | 0
Idaho | 818.4 | 261 | 261 | 261 | 0
Total Idaho | 818.4 | 261 | 261 | 261 | 0

## Oregon
Oregon Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK | [5 empty] | INTERIM WORK
| District | Total Miles | Line Miles | Line Mile | Miles | Line Miles | Line Miles | Line Miles | Line Miles
Total Oregon | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Goal | Ahead/Behind
| 1819.65 | 40 | 36 | 40 | -4 | 326 | 354 | 326 | 28
Feldman/Dudik
Oregon | 499.44 |  |  | 0 | 0 | 147 | 83 | 147 | -64
Total | 499.44 | 0 | 0 | 0 | 0 | 147 | 83 | 147 | -64
Hooley/Arritola
Oregon | 673.49 | 0 |  | 0 | 0 | 131 | 147 | 131 | 16
Total | 673.49 | 0 | 0 | 0 | 0 | 131 | 147 | 131 | 16
Phillips/Russell
Oregon | 381.58 | 4 | 1 | 4 | -3 |  |  | 0 | 0
Total | 381.58 | 4 | 1 | 4 | -3 | 0 | 0 | 0 | 0
Housholder/Koetsier
Oregon | 265.14 | 36 | 35 | 36 | -1 | 48 | 124 | 48 | 76
Total | 265.14 | 36 | 35 | 36 | -1 | 48 | 124 | 48 | 76
Total Oregon | 1819.65 | 40 | 36 | 40 | -4 | 326 | 354 | 326 | 28
14804 | 15803
3417 | 6108
11387 | 9695
1.1745

## Utah
Utah Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
| District | Total Miles | Line Miles | Line Mile | Miles
Total Utah | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 3972.48 | 1262 | 1183 | 1262 | -79
Evans/Spicer
Utah | 2759.16 | 725 | 723 | 725 | -2
Total | 2759.16 | 725 | 723 | 725 | -2
Sorensen/O'Malley
Utah | 518.72 | 317 | 317 | 317 | 0
Total | 518.72 | 317 | 317 | 317 | 0
Vanderhoof/Cherry
Utah | 694.6 | 220 | 143 | 220 | -77
Total | 694.6 | 220 | 143 | 220 | -77
Total Utah | 3972.48 | 1262 | 1183 | 1262 | -79

## Washington
Washington Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK
| District | Total Miles | Line Miles | Line Mile | Miles
Total Washington | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
Housholder/Koetsier | 325.65 | 47 | 16 | 47 | -31
Washington | 325.65 | 47 | 16 | 47 | -31
Total Washington | 325.65 | 47 | 16 | 47 | -31

## Wyoming
Wyoming Vegetation Management 2020 Local Transmission Progress Report
Through Jan 2, 2021
LOCAL TRANSMISSION WORK
CYCLE WORK
| District | Total Miles | Line Miles | Line Mile | Miles
Total Wyoming | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
Vanderhoof/Cherry | 682.88 | 78 | 99 | 78 | 21
Wyoming | 682.88 | 78 | 99 | 78 | 21
Total Wyoming | 682.88 | 78 | 99 | 78 | 21