## Summary
PACIFICORP VEGETATION MANAGEMENT 2020 DISTRIBUTION PROGRESS REPORT
Summary
Through Jan 2, 2021
CYCLE WORK | [5 empty] | INTERIM WORK
| Total | Total Miles | Line Miles | Line Mile | Miles | Total Miles | Line Miles | Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 42362.89 | 12767.53 | 11223.15 | 12767.53 | -1544.38 | 3947.86 | 1839 | 3947.86 | -2108.86
State
California | 2554.8 | 630 | 602 | 630 | -28 | 527 | 307 | 527 | -220
Idaho | 4433.2 | 1466 | 1466.3 | 1466 | 0.3 | 0 | 0 | 0 | 0
Oregon | 13940.07 | 3884.11 | 2808 | 3884.11 | -1076.11 | 3420.86 | 1532 | 3420.86 | -1888.86
Utah | 10840.1 | 3871.42 | 3836.2 | 3871.42 | -35.22 | 0 | 0 | 0 | 0
Washington | 3381.24 | 1095 | 683 | 1095 | -412 | 0 | 0 | 0 | 0
Wyoming | 7213.48 | 1821 | 1827.65 | 1821 | 6.65 | 0 | 0 | 0 | 0
Total | 42362.89 | 12767.53 | 11223.15 | 12767.53 | -1544.38 | 3947.86 | 1839 | 3947.86 | -2108.86
SUMMARY OF SYSTEMATIC WORK* BY FORESTER
| Total | Total Miles | *Line Miles | *Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead/(Behind)
| 42362.89 | 16715.39 | 13062.15 | 16715.39 | -3653.24
Forester |  | * | * | * | *
Feldman/Dudik | 4106.87 | 2306.15 | 1552 | 2306.15 | -754.15
Evans/Spicer | 6079.7 | 1898.52 | 1863.8 | 1898.52 | -34.72
Sorensen/O'Malley | 2063 | 851.9 | 852 | 851.9 | 0.1
Hooley/Arritola | 4652.4 | 2461 | 1406 | 2461 | -1055
Phillips/Russell | 5156 | 2322 | 1516 | 2322 | -806
Vanderhoof/Cherry | 14344.08 | 4408 | 4414.35 | 4408 | 6.35
Housholder/Koetsier | 5960.84 | 2467.82 | 1458 | 2467.82 | -1009.82
Total | 42362.89 | 16715.39 | 13062.15 | 16715.39 | -3653.24
*Combines cycle and interim work.
Weeks | 52

## Pacific-Rocky
PACIFICORP VEGETATION MANAGEMENT 2020 DISTRIBUTION PROGRESS REPORT
Through Jan 2, 2021
CYCLE WORK | [5 empty] | INTERIM WORK
| Total | Total Miles | Line Miles | Line Mile | Miles | Total Miles | Line Miles | Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 42362.89 | 12767.53 | 11223.15 | 12767.53 | -1544.38 | 3947.86 | 1839 | 3947.86 | -2108.86
Pacific
California | 2554.8 | 630 | 602 | 630 | -28 | 527 | 307 | 527 | -220
Oregon | 13940.07 | 3884.11 | 2808 | 3884.11 | -1076.11 | 3420.86 | 1532 | 3420.86 | -1888.86
Washington | 3381.24 | 1095 | 683 | 1095 | -412 | 0 | 0 | 0 | 0
Total | 19876.11 | 5609.11 | 4093 | 5609.11 | -1516.11 | 3947.86 | 1839 | 3947.86 | -2108.86
Rocky Mt
Idaho | 4433.2 | 1466 | 1466.3 | 1466 | 0.3 | 0 | 0 | 0 | 0
Utah | 10840.1 | 3871.42 | 3836.2 | 3871.42 | -35.22 | 0 | 0 | 0 | 0
Wyoming | 7213.48 | 1821 | 1827.65 | 1821 | 6.65 | 0 | 0 | 0 | 0
Total | 22486.78 | 7158.42 | 7130.15 | 7158.42 | -28.27 | 0 | 0 | 0 | 0
SUMMARY OF SYSTEMATIC WORK* BY FORESTER
| Total | Total Miles | Line Miles | Line Mile | Miles
| Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 42362.89 | 16715.39 | 13062.15 | 16715.39 | -3653.24
Forester/Pacific
Feldman/Dudik | 4106.87 | 851.9 | 1552 | 2306.15 | -754.15
Hooley/Arritola | 4652.4 | 2322 | 1406 | 2461 | -1055
Phillips/Russell | 5156 | 2322 | 1516 | 2322 | -806
Housholder/Koetsier | 5960.84 | 2467.82 | 1458 | 2467.82 | -1009.82
Total | 19876.11 | 7963.72 | 5932 | 9556.97 | -3624.97
Forester/Rocky Mt
Evans/Spicer | 6079.7 | 1898.52 | 1863.8 | 1898.52 | -34.72
Sorensen/O'Malley | 2063 | 851.9 | 852 | 851.9 | 0.1
Vanderhoof/Cherry | 14344.08 | 4408 | 4414.35 | 4408 | 6.35
Total | 22486.78 | 7158.42 | 7130.15 | 7158.42 | -28.27
*Combines cycle and interim work.
Weeks | 52
w

## Comparison (hidden)
PACIFICORP VEGETATION MANAGEMENT 2017 DISTRIBUTION PROGRESS REPORT
AHEAD / BEHIND LINE MILE GOALS
CYCLE WORK BY STATE YTD
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles
| 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
State
California | bar: Jan
Idaho | Jan: 52
Oregon | Jan: 29
Utah | Jan: 46
Washington | Jan: -17
Wyoming | Jan: 20
YTD Total | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERIM WORK BY STATE YTD
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles
| -70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
State
California | Jan: -18
Idaho
Oregon | Jan: -52
Utah
Washington
Wyoming
YTD Total | -70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMBINED CYCLE AND INTERIM WORK BY STATE YTD
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles
| 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
State
California | -17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Idaho | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oregon | -23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utah | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Washington | -17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wyoming | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
YTD Total | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMBINED CYCLE AND INTERIM WORK BY FORESTER YTD
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles | Line Miles
| 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forester
Wolinski | Jan: 110
Evans | Jan: 9
Jones | Jan: 2
Hooley | Jan: -17
Phillips | Jan: -69
Vanderhoof | Jan: 107
Armstrong | Jan: -83
YTD Total | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## California
California Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK | [5 empty] | INTERIM WORK
| District | Total Miles | YTD Line Miles | YTD Line Mile | Miles | Total Miles | YTD Line Miles | YTD Line Miles | Miles
Total California | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 2554.8 | 630 | 602 | 630 | -28 | 527 | 307 | 527 | -220
Phillips/Russell
Alturas/Lakeview | 156 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0
Tulelake/KFC | 699.4 | 199 | 199 | 199 | 0 | 135 | 27 | 135 | -108
Yreka/Mt Shasta | 1412.7 | 338 | 311 | 338 | -27 | 330 | 280 | 330 | -50
Total | 2268.1 | 556 | 529 | 556 | -27 | 465 | 307 | 465 | -158
Hooley/Arritola
Crescent City | 286.7 | 74 | 73 | 74 | -1 | 62 |  | 62 | -62
Total | 286.7 | 74 | 73 | 74 | -1 | 62 | 0 | 62 | -62
Total California | 2554.8 | 630 | 602 | 630 | -28 | 527 | 307 | 527 | -220

## Idaho
Idaho Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK
Vanderhoof/Cherry | District | Total Miles | YTD Line Miles | YTD Line Mile | Miles
Total Idaho | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 4433.2 | 1466 | 1466.3 | 1466 | 0.3
Montpelier | 854.4 | 164 | 164.3 | 164 | 0.3
Preston | 740.5 | 121 | 121 | 121 | 0
Rexburg/Mudlake | 1927.1 | 693 | 693 | 693 | 0
Shelley | 911.2 | 488 | 488 | 488 | 0
Total Idaho | 4433.2 | 1466 | 1466.3 | 1466 | 0.3
`

## Oregon
Oregon Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK | [6 empty] | INTERIM WORK
| District | Total Miles | YTD Line Miles | YTD Line Mile | Miles |  | Total Miles | YTD Line Miles | YTD Line Miles | Miles
Total Oregon | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind) |  | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 13940.07 | 3884.11 | 2808 | 3884.11 | -1076.11 |  | 3420.86 | 1532 | 3420.86 | -1888.86
Feldman/Dudik
Albany | 537.1 | 323.8 | 324 | 323.8 | 0.2 |  | 213.33 | 85 | 213.33 | -128.33
Central Oregon (Bend, Madras, Prineville, Redmond) | 1345.3 | 475 | 360 | 475 | -115 |  | 433.18 | 182 | 433.18 | -251.18
Corvallis | 304.7 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0
Cottage Grove | 52.3 | 0 |  | 0 | 0 |  | 52.17 | 52 | 52.17 | -0.17
Dallas | 409.3 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0
Junction City | 154.7 | 0 |  | 0 | 0 |  | 155.07 | 134 | 155.07 | -21.07
Lebanon | 695.22 | 0 |  | 0 | 0 |  | 128.28 | 128 | 128.28 | -0.28
Lincoln City | 163.64 | 0 |  | 0 | 0 |  | 80.82 | 81 | 80.82 | 0.18
Stayton | 444.61 | 388.6 | 150 | 388.6 | -238.6 |  | 55.9 | 56 | 55.9 | 0.1
Total | 4106.87 | 1187.4 | 834 | 1187.4 | -353.4 |  | 1118.75 | 718 | 1118.75 | -400.75
Hooley/Arritola
Coos Bay | 644.4 | 185 | 185 | 185 | 0 |  | 171 | 61 | 171 | -110
Grants Pass | 1635.7 | 401 | 293 | 401 | -108 |  | 422 | 141 | 422 | -281
No Medford | 893 | 240 | 225 | 240 | -15 |  | 297 | 68 | 297 | -229
Roseburg | 1192.6 | 379 | 242 | 379 | -137 |  | 230 | 118 | 230 | -112
Total | 4365.7 | 1205 | 945 | 1205 | -260 |  | 1120 | 388 | 1120 | -732
Phillips/Russell
Klamath Falls | 1843.5 | 513 | 339 | 513 | -174 |  | 409 | 64 | 409 | -345
Lakeview/Or | 35.4 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0
Medford | 1009 | 224 | 192 | 224 | -32 |  | 155 | 85 | 155 | -70
Total | 2887.9 | 737 | 531 | 737 | -206 |  | 564 | 149 | 564 | -415
Housholder/Koetsier
Clatsop | 374.4 | 79.54 | 55 | 79.54 | -24.54 |  |  | 11 | 0 | 11
Enterprise | 433 | 76.17 | 65 | 76.17 | -11.17 |  | 116.05 |  | 116.05 | -116.05
Hermiston | 253.9 | 57.88 | 58 | 57.88 | 0.12 |  | 126.86 | 26 | 126.86 | -100.86
Hood River | 306.1 | 83.91 | 61 | 83.91 | -22.91 |  | 129.68 | 123 | 129.68 | -6.68
Milton-Freewater (Walla Walla, OR) | 154.5 | 82.96 | 83 | 82.96 | 0.04 |  | 41.28 | 41 | 41.28 | -0.28
Pendleton | 610.8 | 178.58 | 17 | 178.58 | -161.58 |  | 204.24 | 76 | 204.24 | -128.24
*Portland | 446.9 | 195.67 | 159 | 195.67 | -36.67 |  | 0 |  | 0 | 0
Total | 2579.6 | 754.71 | 498 | 754.71 | -256.71 | 0 | 618.11 | 277 | 618.11 | -341.11
TOTAL | [7 empty] | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total Oregon | 13940.07 | 3884.11 | 2808 | 3884.11 | -1076.11 |  | 3420.86 | 1532 | 3420.86 | -1888.86
* Portland is ½ line miles for cycle, but there is no interim work.

## Utah
Utah Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK
| District | Total Miles | YTD Line Miles | YTD Line Mile | Miles
Total Utah | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 10840.1 | 3871.42 | 3836.2 | 3871.42 | -35.22
Evans/Spicer
American Fork, Nebo | 942.3 | 174.7 | 154.18 | 174.7 | -20.52
Cedar City, Dixie, Milford | 1378.6 | 684.16 | 684.16 | 684.16 | 0
Moab (Canyonlands) | 625 | 165.91 | 165.9 | 165.91 | -0.01
Park City | 546.4 | 216.89 | 217 | 216.89 | 0.11
Price (Castle Country) | 594.5 | 318.06 | 318 | 318.06 | -0.06
Richfield, Delta | 1243.4 | 158 | 158 | 158 | 0
Vernal (Ashley) | 255.2 | 86.56 | 86.56 | 86.56 | 0
Tooele | 494.3 | 94.24 | 80 | 94.24 | -14.24
Total | 6079.7 | 1898.52 | 1863.8 | 1898.52 | -34.72
Sorensen/O'Malley
Jordan Valley | 802.4 | 515.5 | 516 | 515.5 | 0.5
Metro | 1260.6 | 336.4 | 336 | 336.4 | -0.4
Total | 2063 | 851.9 | 852 | 851.9 | 0.1
Vanderhoof/Cherry
Layton | 295.6 | 28 | 28 | 28 | 0
Mt Ogden | 957.6 | 357 | 356 | 357 | -1
Smithfield, Randolph, Laketown | 766.3 | 276 | 276.4 | 276 | 0.4
Tremonton/Bear River | 677.9 | 460 | 460 | 460 | 0
Total | 2697.4 | 1121 | 1120.4 | 1121 | -0.6
Total Utah | 10840.1 | 3871.42 | 3836.2 | 3871.42 | -35.22

## Washington
Washington Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK
Housholder/Koetsier | District | Total Miles | YTD Line Miles | YTD Line Mile | Miles
Total Washington | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 3381.24 | 1095 | 683 | 1095 | -412
Sunnyside | 789.6 | 251 | 68 | 251 | -183
Walla Walla | 681.3 | 242 | 23 | 242 | -219
Yakima | 1910.34 | 602 | 592 | 602 | -10
Total Washington | 3381.24 | 1095 | 683 | 1095 | -412

## Wyoming
Wyoming Vegetation Management 2020 Distribution Progress Report
Through Jan 2, 2021
CYCLE WORK
Vanderhoof/Cherry | District | Total Miles | YTD Line Miles | YTD Line Mile | Miles
Total Wyoming | Line Miles | Scheduled | Completed | Completed Goal | Ahead(Behind)
| 7213.48 | 1821 | 1827.65 | 1821 | 6.65
Casper/Douglas/Buffalo | 2273.9 | 615 | 615 | 615 | 0
Cody/Lovell | 1013.1 | 0 | 5.25 | 0 | 5.25
Evanston/Kemmerer | 512.5 | 52 | 52.3 | 52 | 0.3
Laramie | 180.78 | 139 | 139 | 139 | 0
Pinedale/Sublett | 743.5 | 375 | 375 | 375 | 0
Rawlins | 584.3 | 433 | 432.7 | 433 | -0.3
Riverton/Lander | 475.2 | 172 | 171 | 172 | -1
Rock Springs | 754.6 | 35 | 35 | 35 | 0
Worland | 675.6 | 0 | 2.4 | 0 | 2.4
Total Wyoming | 7213.48 | 1821 | 1827.65 | 1821 | 6.65

## Completion %
PACIFICORP VEGETATION MANAGEMENT 2020 DISTRIBUTION PROGRESS REPORT
Summary
Through Jan 2, 2021
DISTRIBUTION CYCLE WORK |  |  |  | DISTRIBUTION INTERIM WORK
State | Miles | Miles Competed | % Complete | State | Miles | Miles Competed | % Complete
California | 630 | 602 | 95.56% | California | 527 | 307 | 58.25%
Oregon | 3884.11 | 2808 | 72.29% | Oregon | 3420.86 | 1532 | 44.78%
Washington | 1095 | 683 | 62.37% | Washington
Total | 5609.11 | 4093 | 72.97% | Total | 3947.86 | 1839 | 46.58%

## Sheet1 (2) (hidden)
Cycle Mi.
Date | Diff | Achieved | Goal | Mo. Miles
Jan | 131 | 516 | 385 | 516
Feb | 0 |  |  | -516
Mar | 0 |  |  | 0
Apr | 0 |  |  | 0
May | 0 |  |  | 0
Jun | 0 |  |  | 0
Jul | 0 |  |  | 0
Aug | 0 |  |  | 0
Sep | 0 |  |  | 0
Oct | 0 |  |  | 0
Nov | 0 |  |  | 0
Dec | 0 |  |  | 0
| Miles | Goal
Jan | 516 | 1025
Feb |  | 1025
Mar | 0 | 1025
Apr | 0 | 1025
May | 0 | 1025
Jun | 0 | 1025
Jul | 0 | 1025
Aug | 0 | 1025
Sep | 0 | 1025
Oct | 0 | 1025
Nov | 0 | 1025
Dec | 0 | 1025