## Liberty Q2 2021 QIU
WMP Initiative Category | WMP Initiative Category# | WMP Initiative Activity | 2021 WMP Page Number | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 80 | N/A | - | - | - | - | - | - | - |  |  | Complete First Generation Risk Model | Completed | - |  |  | First Generation Risk Model Complete and in review in Liberty's GRC proceeding
Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations | 81 | Weather Stations Installed | 10 | 0 | 0 | 5 | 10 | 0 | 0 | [7 empty] | In progress
Situational Awareness & Forecasting | 7.3.2.2 | Continuous monitoring sensors | 82 | DFA Units Installed | 10 | 0 | 3 | 6 | 10 | 0 | 0 | [7 empty] | In progress
Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment | 83 | Fault Indicators Installed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | In progress
Situational Awareness & Forecasting | 7.3.2.4 | Forecast of a fire risk index, fire potential index, or similar | 84 | N/A | - | - | - | - | - | - | - | [7 empty] | Complete
Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 85 | N/A | - | - | - | - | - | - | - | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | 86 | N/A | - | - | - | - | - | - | -
Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation | 87 | Line Miles | 9.1 | 0 | 0 | 3.35 | 9.1 | 0 | 0 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles | 90 | Poles | 400 | 0 | 25 | 325 | 400 | 0 | 25 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement | 91 | Expulsion Fuses Replaced | 1500 | 0 | 500 | 1000 | 1500 | 0 | 0 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.8 | Grid topology improvements to mitigate or reduce PSPS events | 93 | Line Miles | 0.5 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment | 93 | Automatic Reclosers Installed | 3 | 0 | 0 | 3 | 3 | 0 | 0 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.12 | Other corrective action | 94 | Tree Attachment Removals | 60 | 0 | 10 | 35 | 60 | 0 | 10 | [7 empty] | In progress
Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment | 96 | Line Miles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | In progress
Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment | 81 | Line Miles Inspected | 52 | 0 | 0 | 52 | 52 | 0 | 0 | [7 empty] | In progress
Asset Management & Inspections | 7.3.4.3 | Improvement of inspections | 82 | N/A | - | - | - | - | - | - | - |  |  | Complete Enterprise GIS in 2022 |  |  |  |  | In progress
Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment | 82 | N/A | - | - | - | - | - | - | - |  |  | RFP developed in 2021, bid in 2022 |  |  |  |  | In progress
Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections | 83 | Poles Inspected | 3600 | 0 | 0 | 2000 | 3600 | 0 | 0 | [7 empty] | In progress
Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment | 85 | Line Miles Inspected | 2050 | 500 | 1550 | 1550 | 2050 | 500 | 2050 | [7 empty] | In progress
Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections | 86 | N/A | - | - | - | - | - | - | - |  |  | RFP developed in 2021, bid in 2022 |  |  | Scope of work developed 7/21 |  | In progress
Asset Management & Inspections | 7.3.4.15 | Substation inspections | 88 | Substations Inspected | 46 | 11 | 22 | 35 | 46 | 11 | 22 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts | 104 | Line Miles Treated | 13 | 0 | 0 | 0 | 13 | 0 | 0 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections of vegetation around distribution electric lines and equipment | 107 | Line Miles Inspected | 207 | 0 | 0 | 0 | 207 | 18 | 76.7 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.5 | Fuel management and reduction of “slash” from vegetation management activities | 109 | Tons of Biomass Removed | 2100 | 0 | 0 | 0 | 2100 | 0 | 106.8 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.7 | LiDAR inspections of vegetation around distribution electric lines and equipment | 112 | Line Miles Inspected | 730 | 0 | 0 | 730 | 730 | 0 | 0 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment | 113 | Line Miles Inspected | - | - | - | - | - | - | -
Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment | 113 | Line Miles Inspected | 150 | 0 | 0 | 0 | 150 | 41.5 | 59.1 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections | 114 | Line Miles Inspected | 136 | 0 | 0 | 32 | 117 | 0 | 0 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel | 116 | N/A | - | - | - | - | - | - | -
Vegetation Management & Inspections | 7.3.5.15 | Remediation of at-risk species | 117 | Line Miles Treated | 230 | 0 | 0 | 0 | 230 | 8.4 | 134.8 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment | 118 | Line Miles Treated | 150 | 0 | 0 | 0 | 150 | 76.4 | 116 | [7 empty] | In progress
Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment | 119 | Line Miles Treated | 328 | 0 | 0 | 0 | 328 | 131.6 | 298.5 | [7 empty] | In progress
Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations | 120 | N/A | - | - | - | - | - | - | - |  |  | Complete DA Pilot Program |  | DA Pilot Program kickoff |  |  | In progress
Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk | 121 | N/A | - | - | - | - | - | - | - |  |  | FPP plan training conducted in Q2 | - | Conducted training for field personnel on June 17, 2021 |  |  | Complete 6/17/2021
Grid Operations & Operating Protocols | 7.3.6.4 | Protocols for PSPS re-energization | 124 | N/A | - | - | - | - | - | - | - |  |  | Playbook developed and hold annual PSPS exercise. | - | PSPS exercise held June 25, 2021 |  |  | Complete 6/25/2021
Data Governance | 7.3.7.1 | Centralized repository for data | 98 | N/A | - | - | - | - | - | - | - |  |  | Develop a centralized data lake by end of 2021 | - | Data source testing and development |  |  | In progress
Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire | 126 | N/A | - | - | - | - | - | - | - |  |  | Provide data to University of Reno for HIFD study | Data provided to UNR | - |  |  | In progress
Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration | 128 | N/A | - | - | - | - | - | - | -
Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts | 130 | N/A | - | - | - | - | - | - | - |  |  | Increase public awareness |  | Social media posts; monthly customer emails; digital, print, radio and TV ads running all 3 months |  |  | In progress
Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies | 132 | N/A | - | - | - | - | - | - | -
Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement | 135 | N/A | - | - | - | - | - | - | - |  |  | Increase public awareness |  | 11 events hosted; 4 WMP and PSPS virtual workshops offered to all customers; ongoing PSP outreach |  |  | In progress
Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA | 141 | N/A | - | - | - | - | - | - | -

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other