## Slide 1
Wildfire Mitigation Plan
Quarterly Advice Letter
Initiative Report
Bear Valley Electric Service
Q2 2021

## Slide 2: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
5.3.4 - Asset Management & Inspections
LiDAR inspections of distribution electric lines and equipment
5.3.4.7
Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
5.3.4.9
Intrusive Pole Inspections
5.3.4.6
Quality assurance / quality control of inspections
5.3.4.14
Other discretionary inspection of transmission electric lines and
5.3.4.10
Not Currently Scheduled*
Infrared inspections of transmission electric lines and equipment
5.3.4.5
Infrared inspections of distribution electric lines and equipment
5.3.4.4
Detailed inspections of distribution electric lines and equipment
5.3.4.1
Detailed inspections of transmission electric lines and equipment
5.3.4.2
Patrol inspections of transmission electric lines and equipment
5.3.4.12
Substation inspections
5.3.4.15
LiDAR inspections of transmission electric lines and equipment
5.3.4.8
Patrol inspections of distribution electric lines and equipment
5.3.4.11
Pole loading assessment program to determine safety factor
5.3.4.13
5.3.7 - Data Governance
Tracking and Analysis of Near Miss Data
5.3.7.4
Collaborative Research on Utility Ignition and/or Wildfire
5.3.7.2
Centralized Repository for Data
5.3.7.1
Documentation and Disclosure of Wildfire-Related Data and Algorithms
5.3.7.3
5.3.6 - Grid Operations & Operating Protocols
Protocols for PSPS Re-Energization
5.3.6.4
Crew-Accompanying Ignition Prevention and Suppression Resources and Services
5.3.6.2
Automatic Recloser Operations
5.3.6.1
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
5.3.6.3
PSPS Events and Mitigation of PSPS Impacts
5.3.6.5
Stationed and On-Call Ignition Prevention and Suppression Resources and Services
5.3.6.6
5.3.1 - Risk Assessment & Mapping
Initiative Mapping and Estimation of Wildfire and PSPS Risk-Reduction Impact
5.3.1.4
Climate-Driven Risk Map and Modeling Based on Various Relevant Weather Scenarios
5.3.1.2
A Summarized Risk Map That Shows the Overall Ignition Probability and Estimated Wildfire Consequence Along the Electric Lines and Equipment
5.3.1.1
Ignition Probability Mapping Showing the Probability of Ignition Along the Electric Lines and Equipment
5.3.1.3
Match Drop Simulations Showing the Potential Wildfire Consequence of Ignitions that Occurs Along the Electric Lines and Equipment
5.3.1.5
Improvement of Inspections
5.3.4.3
5.3.10 - Stakeholder Cooperation & Community Outreach
Cooperation and best practice sharing with agencies outside CA
5.3.10.2
Community Engagement
5.3.10.1
Forest service and fuel reduction cooperation and joint roadmap
5.3.10.4
Cooperation with suppression agencies
5.3.10.3
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).

## Slide 3: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
5.3.9 - Emergency Planning & Preparedness
Protocols in Place to Learn from Wildfire Events
5.3.9.6
Customer Support in Emergencies
5.3.9.3
Preparedness and Planning for Service Restoration
5.3.9.5
Not Currently Scheduled
Community Outreach, Public Awareness, and Communications Efforts
5.3.9.2
Adequate and Trained Workforce for service Restoration
5.3.9.1
Disaster and Emergency Preparedness Plan
5.3.9.4
5.3.3 - Grid Design & System Hardening
Covered Conductor Maintenance
5.3.3.4
Circuit Breaker Maintenance and Installation to De-Energize Lines Upon Detecting a Fault
5.3.3.2
Capacitor Maintenance and Replacement Program
5.3.3.1
Covered Conductor Installation
5.3.3.3
Crossarm Maintenance, Repair, and Replacement
5.3.3.5
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
5.3.3.6
Expulsion Fuse Replacement
5.3.3.7
Grid Topology Improvement to Mitigate or Reduce PSPS events
5.3.3.8
Installation of System Automation Equipment
5.3.3.9
Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps
5.3.3.10
Mitigation of Impact on Customers and Other Residents Affected During PSPS Events
5.3.3.11
Other Corrective Action
5.3.3.12
Pole Loading Infrastructure Hardening and Replacement Program Based on Pole Loading Assessment Program
5.3.3.13
Transformers Maintenance and Replacement
5.3.3.14
Transmission Tower Maintenance and Replacement
5.3.3.15
Undergrounding of Electric Lines and/or Equipment
5.3.3.16
Updates to Grid Topology to Minimize Risk of Ignition in HFTDs
5.3.3.17
Risk Spend Efficiency Analysis
5.3.8.3
Risk Reduction Scenario Development and Analysis
5.3.8.2
Allocation Methodology Development and Application
5.3.8.1
5.3.8 - Resource Allocation Methodology
5.3.2 - Situational Awareness & Forecasting
Forecast of a Fire Risk Index, Fire Potential Index, or Similar
5.3.2.4
Fault Indicators for Detecting Faults on Electric Lines and Equipment
5.3.2.3
Personnel Monitoring Areas of Electric Lines and Equipment in Elevated Fire Risk Conditions
5.3.2.5
Continuous Monitoring Sensors
5.3.2.2
Advanced Weather Monitoring and Weather Stations
5.3.2.1
Weather Forecasting and Estimating Impacts on Electrical Lines and Equipment
5.3.2.6

## Slide 4: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Additional efforts to manage community and environmental impacts
5.3.5.1
5.3.5 - Vegetation Management & Inspections
Not Currently Scheduled
LiDAR inspections of vegetation around distribution electric lines and equipment
5.3.5.7
Other discretionary inspection of transmission electric lines and
5.3.5.10
Fuel management and reduction of “slash” from vegetation management activities
5.3.5.5
Removal and remediation of trees with strike potential to electric lines and equipment
5.3.5.16
Patrol inspections of vegetation around transmission electric lines and equipment
5.3.5.12
Detailed inspections of vegetation around distribution electric lines and equipment
5.3.5.2
Recruiting and training of vegetation management personnel
5.3.5.14
Quality assurance / quality control of vegetation inspections
5.3.5.13
Substation inspection
5.3.5.17
Remediation of at-risk species
5.3.5.15
Vegetation management to achieve clearances around electric lines and equipment
5.3.5.20
Other discretionary inspections of vegetation around distribution electric lines and equipment
5.3.5.9
Vegetation inventory system
5.3.5.19
Enhanced Vegetation Management Program
5.3.5.11
Improvement of inspections
5.3.5.6
Detailed inspections of vegetation around transmission electric lines and equipment
5.3.5.3
Emergency response vegetation management due to red flag warning or other urgent conditions
5.3.5.4
Substation vegetation management
5.3.5.18
LiDAR inspections of vegetation around transmission electric lines and equipment
5.3.5.8

## Slide 5: WMP Activities Status vs. WMP Activity Goals
5.3.1 - Risk Assessment & Mapping
Ignition Probability Mapping Showing the Probability of Ignition Along the Electric Lines and Equipment
5.3.1.3
Ignition Probability & Wildfire Consequence Mapping Project
Contracted Resources
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
A Summarized Risk Map That Shows the Overall Ignition Probability and Estimated Wildfire Consequence Along the Electric Lines and Equipment
5.3.1.1
Ignition Probability & Wildfire Consequence Mapping Project [Primary]
Contracted Resources
Climate-Driven Risk Map and Modeling Based on Various Relevant Weather Scenarios
5.3.1.2
Ignition Probability & Wildfire Consequence Mapping Project
Contracted Resources
Initiative Mapping and Estimation of Wildfire and PSPS Risk-Reduction Impact
5.3.1.4
Ignition Probability & Wildfire Consequence Mapping Project
Contracted Resources
Match Drop Simulations Showing the Potential Wildfire Consequence of Ignitions that Occurs Along the Electric Lines and Equipment
5.3.1.5
Ignition Probability & Wildfire Consequence Mapping Project
Contracted Resources
Contracting with Risk Mapping Resource
Q2 2021 Goal: Work with the contracted resource to develop a risk model toolkit.
Key Actions: In conjunction with the contractor developed a summarized risk map; climate-driven map; ignition probability mapping model; PSPS estimation reduction impact map; and a match drop simulation. These models will be refined in the next quarter.
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.1.1 (Primary)
    5.3.1.2
    5.3.1.3
    5.3.1.4
    5.3.1.5 Secondary Initiatives
    5.3.2.4
    5.3.8.2
    5.3.8.3
5.3.7 - Data Governance
Tracking and Analysis of Near Miss Data
5.3.7.4
WMP Metrics Tracking
Ongoing
Centralized Repository for Data
5.3.7.1
GIS Data Collection & Sharing [Primary]
On Track
GIS Data Collection & Sharing Improvements:
BVES continues to work towards a class leading Data Repository.
Key Actions: BVES continue to work with its contracted experts to update its GIS database as well as develop a more streamlines method for reporting and sharing of information
WMP Metrics Tracking:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q2 of 2021 there were no compliance issues identified.
Key Actions: BVES recorded necessary metrics for inclusion in quarterly reporting

## Slide 6
5.3.2 - Situational Awareness & Forecasting
Revised Schedule for 2021 Planned Deployment & Additional Installation:
Volume vs Q2 2021 Goal: BVES planned to install 2 weather stations in Q2 of 2021. All aspects of project are on track, however, BVES was unable to install the second unit due to external factors.
Key Actions: One weather station was installed in Q2. Plans are on schedule to install the weather station remaining form Q2 in Q3 to reach annual targets.
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
WMP Activities Status vs. WMP Activity Goals
Forecast of a Fire Risk Index, Fire Potential Index, or Similar
5.3.2.4
Weather Consultant / Risk Mapping
On Track
Fault Indicators for Detecting Faults on Electric Lines and Equipment
5.3.2.3
Situational Awareness Hardware Program
Planned
Personnel Monitoring Areas of Electric Lines and Equipment in Elevated Fire Risk Conditions
5.3.2.5
Grid Operations & Protocols
No High-Risk Events Occurred
Continuous Monitoring Sensors
5.3.2.2
Situational Awareness Hardware Program
Off Track
Advanced Weather Monitoring and Weather Stations
5.3.2.1
Situational Awareness Hardware Program [Primary]
Off Track
Weather Forecasting and Estimating Impacts on Electrical Lines and Equipment
5.3.2.6
Weather Consultant [Primary]
Support Requirement Met
Situational Awareness Hardware Program:
Volume vs Q2 2021 Goal: BVES planned to install 2 HD Cameras in Q2 of 2021. All aspects of project are on track for these cameras, however, BVES was not able to secure access in Q2 to install the devices. WMP Initiative 5.3.2.1 is the primary for the subtasks included in this category.
Key Actions: Zero HD cameras were installed in Q2 due to access issues.
Situational Awareness Hardware Program:
Volume vs Q2 2021 Goal: This is currently a planned program for BVES in 2022. WMP Initiative 5.3.2.1 is the primary for the subtasks included in this category.
Key Actions: Currently on track to begin work.
Grid Operations & Protocol:
Volume vs Q2 2021 Goal: BVES has established a resource allocation level for the instance where a high fire risk condition occurs.
Key Actions: BVES currently has the resource pool available to combat high fire risk conditions in its operating area.
Contracting with Risk Mapping Resource
Volume vs Q2 2021 Goal: Work with the contracted resource to develop a risk model toolkit.
Key Actions: In conjunction with the contractor developed a summarized risk map; climate-driven map; ignition probability mapping model; PSPS estimation reduction impact map; and a match drop simulation. These models will be refined in the next quarter.
Weather Consultant for Weekly Reporting:
Q2 2021 Goal: BVES currently has a weather consultant on payroll who supports the weather forecasting and analysis necessary.
Key Actions: Additional task for quarterly aggregation of High Wind Warning and Red Flag Warning accounts to support Quarterly Data Reports.
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.2.6 (Primary)
    5.3.2.4
Situational Awareness Hardware Program
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.2.1 (Primary)
    5.3.2.2
    5.3.2.3

## Slide 7: WMP Activities Status vs. WMP Activity Goals
5.3.3 - Grid Design & System Hardening Initiatives
2019-2020 Completed Pilot:
Volume vs Q2 2021 Goal: BVES has no outstanding goals for the pilot.
2.82 Circuit Miles Planned for 2021 Hardening:
Volume vs Q1 2021 Goal: BVES will begin construction in Q3 contingent with permitting approvals for completion by the end of the year
Key Actions: Currently on track to begin Q3 activities.
12.9 Circuit Miles Planned for 2021 Hardening:
Volume vs Q2 2021 Goal: BVES projected that they would complete 4.3 line miles in Q2 of 2021. BVES was able to complete 5.15 lines miles in Q2.
Key Actions: BVES is currently on track to complete the projected total of 12.9 by close of 2021
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Covered Conductor Installation
5.3.3.3
Covered Conductor Pilot
Radford Covered Conductor Replacement
Covered Conductor Replacement Program
On Track
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
5.3.3.6
Pole Loading & Replacement Program
113 Poles Replaced
Radford Covered Conductor Replacement
Evacuation Route Hardening Pilot
Evacuation Route Hardening Program
400 Poles Hardened in 2021
Other Corrective Action
5.3.3.12
Radford Line Covered Conductor
Evacuation Route Hardening
On Track
Tree Attachment Removal Program
33% Patrolled within the Service Area to Date:
Volume vs Q2 2021 Goal: The goal for Q2 was to have 65 poles replaced as part of the assessment process. BVES has currently replaced 113 poles in 2021. This initiative is secondary to 5.3.3.13.
Key Actions: Due to the work that was completed in Q1 & Q2 BVES is on track to meet its target of 200 poles for 2021.
2.82 Circuit Miles Planned for 2021 Hardening:
Volume vs Q1 2021 Goal: BVES will begin construction in Q3 contingent with permitting approvals for completion by the end of the year
Key Actions: Currently on track to begin Q3 activities.
2020 Completed Route Hardening Pilot:
Volume vs Q2 2021 Goal: The BVES does not have an established goal for this pilot as it was completed the year prior.
400 Poles Hardened on Route to Date:
Volume vs Q2 2021 Goal: BVES initiated a pilot program to test fire-resistant solutions to protect wood poles. 321 wood poles were hardening with a wire mesh protective coating.
Key Actions: Currently on track to begin Q3 activities.
2.82 Circuit Miles Planned for 2021 Hardening:
Volume vs Q1 2021 Goal: BVES will begin construction in Q3 contingent with permitting approvals for completion by the end of the year
Key Actions: Currently on track to begin Q3 activities.
Completion Toward 85 Attachment Removals for the Year:
Volume vs Q2 2021 Goal: BVES identified and removed 4 tree attachments, placing it behind schedule by 21 units.
Key Actions: BVES plans to expedite the schedule in Q3 and Q4 to meet targets.
400 Poles Hardened on Route to Date:
Volume vs Q2 2021 Goal: BVES initiated a pilot program to test fire-resistant solutions to protect wood poles. 321 wood poles were hardening with a wire mesh protective coating.
Key Actions: Currently on track to begin Q3 activities.
1
2
3
3
Covered Conductor Program - Pilot
1
2
1
2
4
Evacuation Route Hardening- Pilot
3

## Slide 8: WMP Activities Status vs. WMP Activity Goals
5.3.3 - Grid Design & System Hardening Initiatives
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Expulsive Fuse Replacement
5.3.3.7
Fuse Replacement Program
0 Remaining
Installation of System Automation Equipment
5.3.3.9
Grid Automation Program [Primary]
2.5% Reached
Mitigation of Impact on Customers and Other Residents Affected During PSPS Events
5.3.3.11
Energy Storage Project
Planned
0 Conventional Fuses Blown in Q2:
Volume vs Q2 2021 Goal: BVES replaced 3,114 conventional expulsion fuses with 2,578 current limiting fuses (non-expulsion fuses) and 536 electronic fuses. BVES replaced 375 in Q2.
Key Actions: BVES completed this initiative.
8 MW/ 4 MWh Energy Storage Facility Planned in 2023:
Q2 2021 Goal: BVES has began working to select the appropriate site and contracting needs to plan for construction/operation by mid-2023.
Key Actions: BVES is on track with this initiative.
10% Annual Target for Grid Automation:
Volume vs Q2 2021 Goal: BVES has reached 2.5% of the milestone for this initiative in Q2, which is on track with goals.
Key Actions: Currently on track to complete annual targets.
Pole Loading Infrastructure Hardening and Replacement Program Based on Pole Loading Assessment Program
5.3.3.13
Pole Loading & Replacement Program [Primary]
279 Poles Assessed
33% Patrolled within the Service Area to Date:
Volume vs Q2 2021 Goal: The goal for Q2 was to have 65 poles replaced as part of the assessment process. BVES has currently replaced 113 poles in 2021. This initiative is secondary to 5.3.3.13.
Key Actions: Due to the work that was completed in Q1 & Q2 BVES is on track to meet its target of 200 poles for 2021.
Grid Topology Improvement to Mitigate or Reduce PSPS events
5.3.3.8
Grid Topology Improvements
[Primary]
Completed
Updates to Grid Topology to Minimize Risk of Ignition in HFTDs 5.3.3.17
Grid Topology Improvements
Completed
Grid Topology Improvements - Completed:
Volume vs Q2 2021 Goal: BVES will install sectionalizing devices as the need is determined. Currently, zero are planned in 2021. WMP Initiative 5.3.3.8 is the primary for the subtasks included in this category.
Key Actions: BVES has completed the effort as identified within this WMP cycle.
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.3.8 (Primary)
    5.3.3.17

## Slide 9: WMP Activities Status vs. WMP Activity Goals
5.3.3 - Grid Design & System Hardening Initiatives
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Capacitor Maintenance and Replacement Program
5.3.3.1
Complete / Ongoing
Circuit Breaker Maintenance and Installation to De-Energize Lines Upon Detecting a Fault
5.3.3.2
Complete / Ongoing
Transformers Maintenance and Replacement
5.3.3.14
Complete / Ongoing
Covered Conductor Maintenance
5.3.3.4
Complete / Ongoing
Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps
5.3.3.10
Complete / Ongoing
Crossarm Maintenance, Repair, and Replacement
5.3.3.5
Complete / Ongoing
BVES Maintenance Best Practice:
The following Grid Design and System Hardening initiatives are covered under ongoing maintenance of subtransmission and distribution facilities and are not separated as unique WMP initiatives.
5.3.10 - Stakeholder Cooperation & Community Outreach
Community engagement
5.3.10.1
Community Outreach Program
In Progress
Cooperation and best practice sharing with agencies outside CA
5.3.10.2
Planned
Forest service and fuel reduction cooperation and joint roadmap
5.3.10.4
Planned
Cooperation with suppression agencies
5.3.10.3
Complete/Ongoing
Cooperation and sharing with agencies outside CA:
Volume vs Q2 2021 Goal: Currently BVES does not participate in cooperation and best practice sharing with agencies outside of CA. BVES plans to have discussion with other agencies within CA to determine how they are approaching this initiative.
Key Actions: No actions have currently been taken
Cooperation with suppression agencies:
Volume vs Q2 2021 Goal: Currently BVES does not participate in cooperation with suppression agencies currently. BVES plans to have discussion with suppression agencies and determine if there are additional actions that can be taken to improve their program.
Key Actions: No actions have currently been taken
Cooperation with forest service and fuel reduction:
Volume vs Q2 2021 Goal: Currently BVES does not participate in forest service and fuel reduction cooperation and joint roadmap programs. BVES plans to have discussion with their forest service contacts to determine the applicability of these programs to improve their overall program.
Key Actions: No actions have currently been taken
Community Outreach Program:
Volume vs Q2 2021 Goal: BVES had planned to conducted at minimum 90 outreach activities. BVES recorded 137 outreach activities 150% of target for Q2. See 5.3.9.2 as the primary WMP initiative.
Key Actions: Grizzly Newspaper advertisements are posted during the week (M-F) for either WMP or PSPS and BVES will have 1 advertisement broadcasted each month.

## Slide 10: WMP Activities Status vs. WMP Activity Goals
5.3.4 - Asset Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
LiDAR inspections of distribution electric lines and equipment
5.3.4.7
LiDAR Inspection Program [Primary]
On Track for Mid-Year Inspection
Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
5.3.4.9
Third Party Ground Patrol
On Track for Mid-Year Inspection
Third Party UAV Program
On Track
Intrusive Pole Inspections
5.3.4.6
Intrusive Pole Inspection Program
Ongoing
Infrared inspections of distribution electric lines and equipment
5.3.4.4
UAV Thermography Program
On Track for Mid-Year Inspection
Detailed inspections of distribution electric lines and equipment
5.3.4.1
Detailed Inspection Program [Primary]
On Track for Mid-Year Inspection
Mid-Year Detailed Inspection Activities
Volume vs Q1 2021 Goal: BVES did not have a quarterly target established for circuit miles inspected over the second quarter in 2021. Inspections will occur in Q3.
Key Actions: Currently on track to complete annual targets.
Performed Annually Across the Entire Service Area
Volume vs Q2 2021 Goal: BVES will begin LiDAR inspections across the service territory in Q3 of 2021.
Key Actions: Currently on track to complete annual targets.
Contracted Third Party Inspection
Volume vs Q2 2021 Goal: BVES will begin third party patrols across the service territory in Q3 of 2021.
Key Actions: Currently on track to complete annual targets.
UAV Thermography Program
Volume vs Q2 2021 Goal: BVES will begin UAV Thermography Inspection across the service territory in Q3 of 2021.
Key Actions: Currently on track to complete annual targets.
Mid-Year UAV Inspection Activities
Volume vs Q2 2021 Goal: BVES did not have a quarterly target established for circuit miles inspected over the second quarter in 2021. Inspections will occur in Q3.
Key Actions: Currently on track to complete annual targets.
Mid-Year Intrusive Pole Inspections
Volume vs Q2 2021 Goal: BVES did not schedule any inspections for intrusive poles for Q1 of 2021. 900 Poles are planned for assessment in 2021.
Key Actions: This programs efforts occur primarily in Q3 and Q4 . Updates will be provided at that time.
LiDAR Inspection Program
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.4.7 (Primary)
    5.3.5.7
Improvement of Inspections
5.3.4.3
Ongoing Effort
Improvement of Inspections:
Key Actions: BVES is always trying to optimize its inspections and is open to changes/adaptations leading to a better process.
Third Party UAV Program
On Track
1
2

## Slide 11: WMP Activities Status vs. WMP Activity Goals
5.3.4 - Asset Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Quality assurance / quality control of inspections
5.3.4.14
Quality Control of Inspections [Primary]
Planned
Substation inspections
5.3.4.15
GO-174 Substation Inspection Program [Primary]
72 Substations Inspected
Patrol inspections of distribution electric lines and equipment
5.3.4.11
Patrol Inspection Program [Primary]
85 Circuit Miles Inspected
Pole loading assessment program to determine safety factor
5.3.4.13
Pole Loading & Replacement Program
YTD Assessed 352 Poles
85 Circuit Miles Patrolled within the Service Area
Volume vs Q2 2021 Goal: BVES met Q2 targets given that there were no miles to be inspected in Q2 (overall progress of 85 miles by close of Q2) with inspections resuming in Q3.
Key Actions: Currently on track to complete annual targets.
Pole Loading & Replacement
Volume vs Q2 2021 Goal: BVES set a target of 500 poles assessed by the end of Q2 2021. BVES was only able to assess 73 poles bringing the annual total to 352. This initiative is secondary to 5.3.3.13.
Key Actions: Due to resourcing issues BVES was not able to meet its goal of 500 poles by the end of Q2 2021. BVES believes it will still be able to meet its annual target for this initiative.
Quality Control for Electrical Inspections Program
Volume vs Goal: BVES has not yet established quantitative or qualitative targets for the planned quality control program and therefore, have no quarterly units to report in the Quarterly Advice Letter.
Key Actions: Currently on track to discuss framework for formal controls development for internal and third-party inspection patrols.
25% of Substations Inspected
Volume vs Q2 2021 Goal: BVES has executed physical inspections of 36 additional substations within the service area bringing the annual total to 72 substations inspected.
Key Actions: Currently on track to meet annual targets.
Patrol Inspection Program
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.4.11 (Primary)
    5.3.5.11
Pole Loading & Replacement Program
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.3.13 (Primary)
    5.3.3.6
    5.3.4.13
GO-174 Substation Inspection Program
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.4.15 (Primary)
    5.3.5.17

## Slide 12: WMP Activities Status vs. WMP Activity Goals
5.3.5 - Vegetation Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
LiDAR inspections of vegetation around distribution electric lines and equipment
5.3.5.7
LiDAR Inspection Program
On Track for Mid-Year Inspection
Detailed inspections of vegetation around distribution electric lines and equipment
5.3.5.2
Detailed Inspection Program
On Track for Mid-Year Inspection
Other discretionary inspections of vegetation around distribution electric lines and equipment
5.3.5.9
UAV & Ground Patrol
Planned / On Track
Patrol inspections of vegetation around distribution electric lines and equipment
5.3.5.11
Patrol Inspection Program
85 Circuit Miles Inspected
Emergency response vegetation management due to red flag warning or other urgent conditions
5.3.5.4
Emergency Preparedness & Response Program
Completed
Mid-Year Detailed Inspection Activities
Volume vs Q2 2021 Goal: BVES did not have a quarterly target established for circuit miles inspected over the second quarter in 2021.
Key Actions: Currently on track to complete annual targets.
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.4.1 (Primary)
    5.3.5.2
85 Circuit Miles Patrolled within the Service Area
Volume vs Q2 2021 Goal: BVES met Q2 targets, inspecting 85 circuit miles across the territory. There were no circuit miles to be inspected in Q2 of 2021.
Key Actions: Currently on track to complete annual targets.
Performed Annually Across the Entire Service Area
Volume vs Q1 2021 Goal: BVES will begin LiDAR inspections across the service territory in Q3 of 2021.
Key Actions: Currently on track to complete annual targets.
Mid-Year UAV Inspection Activities
Volume vs Q2 2021 Goal: BVES did not have a quarterly target established for circuit miles inspected over the second quarter in 2021.
Key Actions: Currently on track to complete annual targets.
Emergency Preparedness and Response Program:
Volume vs Q2 2021 Goal: BVES did not record an emergency in Q2 of 2021. This means that the use of the Emergency Preparedness & Response Program was not required. See initiative 5.3.9.4 as the primary.
Remediation of at-risk species
5.3.5.15
Planned
Improvement of inspections
5.3.5.6
Ongoing
Improvement of Inspections:
Key Actions: BVES is always trying to optimize its inspections and is open to changes/adaptations leading to a better process.
Remediation of At-Risk Species:
Key Actions: BVES and its contractors account for at risk species when doing field work and evaluation. Cycle Breaker vegetation is are an example of what may be recorded.

## Slide 13: WMP Activities Status vs. WMP Activity Goals
5.3.5 - Vegetation Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Removal and remediation of trees with strike potential to electric lines and equipment
5.3.5.16
Enhanced Vegetation Management Program [Primary]
On Track
Recruiting and training of vegetation management personnel
5.3.5.14
Vegetation Management Program Staffing
Met Targets
Quality assurance / quality control of vegetation inspections
5.3.5.13
Quality Control of Inspections
24 of 36
Substation inspection
5.3.5.17
GO-174 Substation Inspection Program
Inspected & Cleared Vegetation
Vegetation inventory system
5.3.5.19
GIS Data Collection & Sharing
Trimmed Trees Logged
Substation vegetation management
5.3.5.18
Substation Vegetation Management Inspections & Corrections
Inspected & Cleared Vegetation
Mid-Year Detailed Inspection Activities
Volume vs Q2 2021 Goal: BVES did not have a quarterly target established for circuit miles inspected over the second quarter in 2021.
Key Actions: Currently on track to complete annual targets.
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.4.1 (Primary)
    5.3.5.2
    5.3.5.20
Fuel management and reduction of “slash” from vegetation management activities
5.3.5.5
Enhanced Vegetation Management Program
Contractor Meets Requirements
50% of Substations Inspected
Volume vs Q2 2021 Goal: BVES has executed physical inspections of 72 substations within the service area at the close of Q2. BVES has met its target of 36 inspections per quarter.
Key Actions: Currently on track to meet annual targets.
50% of Substations Inspected
Volume vs Q2 2021 Goal: BVES has executed physical inspections of 76 substations within the service area at the close of Q2. BVES has met its target of 36 inspections per quarter.
Key Actions: Currently on track to meet annual targets.
GIS Data Collection & Sharing:
Volume vs Q2 2021 Goals: BVES continues to work towards a class leading Data Repository. WMP Initiative 5.3.7.1 is the primary associated with this ongoing inventory scope.
Key Actions: BVES continue to work with its contracted experts to update its GIS database as well as develop a more streamlines method for reporting and sharing of information.
Quality Control for Electrical Inspections Program
Volume vs Q2 2021 Goal: BVES plans to execute 18 audit reviews of vegetation management work per quarter. 24 out of 36 were completed per established targets at the close of Q2.
Key Actions/Remediation: BVES conducted 15 of the 18 scheduled reviews. BVES will work to meet future quarterly goals for reviewing contractor vegetation management activities.
Resource Allocation & Training:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q2 of 2021 there were no compliance issues identified.
Key Actions: BVES reviewed staffing program and methodology
Vegetation management to achieve clearances around electric lines and equipment
5.3.5.20
Enhanced Vegetation Management Program
Targets Met

## Slide 14: WMP Activities Status vs. WMP Activity Goals
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
5.3.6.3
PSPS Program & Procedures
Ongoing
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Alternative & Advance Technologies
5.3.6 - Grid Operational & Protocols
Protocols for PSPS Re-Energization
5.3.6.4
PSPS Program & Procedures
Established
Crew-Accompanying Ignition Prevention and Suppression Resources and Services
5.3.6.2
Emergency Preparedness & Response Program
No Emergency Events
Automatic Recloser Operations
5.3.6.1
Grid Automation Program
Completed
PSPS Events and Mitigation of PSPS Impacts
5.3.6.5
PSPS Program & Procedures [Primary]
0 PSPS Events
Stationed and On-Call Ignition Prevention and Suppression Resources and Services
5.3.6.5
Emergency Preparedness & Response Program
Ongoing
PSPS Program & Procedure:
BVES has an established program and procedures in place. BVES continues to monitor all aspects of the program for compliance. During the period Q2 of 2021 there were no PSPS events that would require the use of said program.
Key Actions: There were no key actions related to the Program as there were no PSPS events
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.6.5 (Primary)
    5.3.6.3
    5.3.6.4
Emergency Preparedness & Response Program:
BVES has an established program in place. BVES continues to monitor all aspects of the program for compliance. During the period Q2 of 2021 there were no emergency events that would require the use of said program.
Key Actions: There were no key actions related to this program in Q2 of 2021
Primary & Secondary Initiative Relationships
Associated WMP initiatives that are mapped to a major initiative for cost recovery classification. Some Secondary initiatives may also have separated costs.
WMP Category Initiative Relationship:
  5.3.9.4 (Primary)
    5.3.5.4
    5.3.6.2
    5.3.6.6
    5.3.9.3
    5.3.9.5
    5.3.9.6
Fault Interrupters – IntelliRupters Pulsing Auto Reclosers – Completed Cycle Work:
Volume vs Q2 2021 Goal: BVES plans to install S&C’s Pulse Closer Fault Interrupters across its major 34 kV system auto-reclosers that was completed in 2020. BVES has installed Fault Indicators (FIs) at key locations to reduce the time it takes to locate faults; thereby, reducing the time to isolate faults from the system or correcting the damage. Prior to the start of the program, BVES had 110 FIs installed in its system at key locations. As part of the WMP, BVES will install an additional 117 FIs at 39 key locations to provide optimal FI coverage in the system in 2022. This initiative is secondary to 5.3.3.9.
Key Actions: BVES has completed the effort as identified within this WMP cycle.

## Slide 15: WMP Activities Status vs. WMP Activity Goals
5.3.9 - Emergency Planning & Preparedness
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Protocols in Place to Learn from Wildfire Events
5.3.9.6
Emergency Preparedness & Response Program
In Progress
Customer Support in Emergencies
5.3.9.3
Emergency Preparedness & Response Program
Established
Preparedness and Planning for Service Restoration
5.3.9.5
Emergency Preparedness & Response Program
Ongoing
Community Outreach, Public Awareness, and Communications Efforts
5.3.9.2
Community Outreach Program [Primary]
Ongoing
Adequate and Trained Workforce for Service Restoration
5.3.9.1
Resource Allocation Methodology
Completed
Disaster and Emergency Preparedness Plan
5.3.9.4
Emergency Preparedness & Response Program [Primary]
Established
5.3.8 - Resource Allocation Methodology
Risk Spend Efficiency Analysis
5.3.8.3
Ignition Probability & Wildfire Consequence Mapping
In Process
Risk Reduction Scenario Development and Analysis
5.3.8.2
Ignition Probability & Wildfire Consequence Mapping
Planned
Allocation Methodology Development and Application
5.3.8.1
Resource Allocation Methodology [Primary]
Program In Process
Resource Allocation Methodology [Primary]:
BVES has an established program in place and continues to monitor all aspects of the program for additional staff. During the period Q2 of 2021 there were no gap issues identified.
Key Actions: BVES routinely reviewed staffing program needs.
Contracting with Risk Mapping Resource
Volume vs Q2 2021 Goal: Developed request for support in producing a package of risk mapping products and match drop simulations to accurately identify BVES’s ignition risk potential under climate change forecasts. WMP Initiative 5.3.1.1 is the primary for the subtasks included in this category.
Key Actions: Developed plan to engage external resources to support BVES in developing these risk maps.
Contracting with Risk Mapping Resource
Volume vs Q2 2021 Goal: Developed request for support in producing a package of risk mapping products and match drop simulations to accurately identify BVES’s ignition risk potential under climate change forecasts. WMP Initiative 5.3.1.1 is the primary for the subtasks included in this category.
Key Actions: Developed plan to engage external resources to support BVES in developing these risk maps.
Emergency Preparedness and Response Program:
Volume vs Q2 2021 Goal: BVES did not record an emergency in Q2 of 2021. This means that the use of the Emergency Preparedness & Response Program was not required. See initiative 5.3.9.4 as the primary.
Resource Allocation Methodology:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q2 of 2021 there were no compliance issues identified. See WMP initiative 5.3.8.1 as the primary.
Key Actions: Staffing for service restoration was reviewed and declared adequate. In the instance of a service restoration event BVES will review the results and re-evaluate staffing if necessary.
Community Outreach Program:
Volume vs Q2 2021 Goal: BVES had planned to conducted at minimum 90 outreach activities. BVES recorded 137 outreach activities 150% of target for Q2. See 5.3.9.2 as the primary WMP initiative.
Key Actions: Grizzly Newspaper advertisements are posted during the week (M-F) for either WMP or PSPS and BVES will have 1 advertisement broadcasted each month.