## Slide 1: SDG&E’s 2021 Wildfire Mitigation Plan 4th Quarter Progress Update
(All data as of December 31, 2021)

## Slide 2: 2021 Wildfire Mitigation Plan Activities Q4 Summary
7.3.3.1
Capacitor maintenance and replacement program
7.3.3.3
Covered conductor installation
7.3.3.7
Expulsion fuse replacement
7.3.3.8.1
PSPS sectionalizing enhancements
7.3.3.8.2
Microgrids
7.3.3.9
Installation of system automation equipment
7.3.3.10
Maintenance, repair, and replacement of connectors, including hotline clamps
7.3.3.11.1
Resiliency grant programs
7.3.2.1
Advanced weather monitoring and weather stations
7.3.3.11.2
Standby power programs
7.3.3.11.3
Resiliency assistance programs
7.3.3.16
Undergrounding of electric lines and/or equipment
7.3.3.17.1
Distribution overhead system hardening
7.3.3.17.2
Transmission overhead system hardening
7.3.3.17.3
Cleveland National Forest distribution and transmission system hardening
7.3.3.18.1
Distribution communications reliability improvements
7.3.3.18.2
Lightning arrestor removal and replacement
7.3.4.1
Detailed inspections of distribution electric lines and equipment
7.3.4.2
Detailed inspections of transmission electric lines and equipment
7.3.4.4
Infrared inspections of distribution electric lines and equipment
7.3.4.5
Infrared inspections of transmission electric lines and equipment
7.3.4.6
Intrusive pole inspections
7.3.4.9.1
HFTD Tier 3 inspections
7.3.5.2
Detailed inspections of vegetation around distribution electric lines and equipment
7.3.5.5
Fuels management and reduction of "slash" from vegetation management activities
7.3.5.9
Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
7.3.5.20
Vegetation management to achieve clearances around electric lines and equipment
7.3.4.9.2
Drone assessments of distribution infrastructure
7.3.4.9.5
Additional transmission aerial 69kV tier 3 visual inspection
7.3.4.10
Patrol inspections of distribution electric lines and equipment
7.3.4.11
Patrol inspections of transmission electric lines and equipment
7.3.4.14
Substation inspections
7.3.2.3
Fault indicators for detecting faults on electric lines and equipment
7.3.2.4.1
Fire Science & Climate Adaptation Department
7.3.4.9.4
Drone assessments of transmission infrastructure

## Slide 3: Q4 Activity Status vs 2021 Goals
7.3.2.1
46
Weather station upgrades
172% Advanced weather monitoring & station upgrades
Volume vs 2021 Goal: 46 of 25 weather station upgrades (184%)
Key Actions: Goal exceeded due to available inventory and available work crews.
7.3.2.3
544
Wireless fault indicators
109% Fault indicators for detecting faults on electric lines and equipment
Volume vs 2021 Goal: 544 of 500 wireless fault indicators (109%)
Key Actions: Program achieved 2021 target.
7.3.2 – Situational Awareness and Forecasting
100% Fire Science & Climate Adaptation Department
Volume vs 2021 Goal: 17 of 17 cameras installed (100%)
Key Actions: Program achieved 2021 target.
7.3.2.4.1 17
Cameras installed

## Slide 4: Q4 Activity Status vs 2021 Goals
7.3.3.1
35
SCADA capacitors
109% Capacitor maintenance and replacement program
Volume vs 2021 Goal: 35 of 32 SCADA capacitors (109%)
Key Actions: Program achieved 2021 target.
7.3.3.7
3,976
Expulsion fuses
100% Expulsion fuse replacement
Volume vs 2021 Goal: 3,976 of 3,970 expulsion fuses (100%)
Key Actions: Program achieved 2021 target.
7.3.3.8.2
0
Microgrids
0% Microgrids
Volume vs 2021 Goal: 0 of 0 microgrids (N/A%)
Key Actions: Existing microgrids are being converted from generators to renewable generation and energy storage. Additional microgrids delayed and being assessed as reported in November 1 Change Order Report.
7.3.3.10
2,743
Hotline clamps
122% Maintenance, repair, and replacement of connectors, including hotline clamps
Volume vs 2021 Goal: 2,743 of 2,250 hotline clamps (122%)
Key Actions: Program ahead of target.
7.3.3.3
20.6
miles CC
100% Covered conductor installation
Volume vs 2021 Goal: 20.6 of 20 miles covered conductor (100%)
Key Actions: Program achieved 2021 target.
7.3.3.8.1
13
Sectionalizing devices
130% PSPS sectionalizing enhancements
Volume vs 2021 Goal: 13 of 10 sectionalizing devices (100%)
Key Actions: Program ahead of 2021 target.
7.3.3.9
4
Circuits enabled
50% Installation of system automation equipment
Volume vs 2021 Goal: 4 of 8 circuits enabled (50%)
Key Actions: Program did not meet 2021 target.
7.3.3.11.1
2,310
Generators
116% Resiliency grant programs
Volume vs 2021 Goal: 2,310 of 2,000 generators (116%)
Key Actions: Program ahead of 2021 target.
7.3.3 – Grid Design and System Hardening (1 of 2)

## Slide 5: Q4 Activity Status vs 2021 Goals
7.3.3.11.2
355
Generators
86% Standby power programs
Volume vs 2021 Goal: 357 of 413 generators (86%)
Key Actions: Program did not meet 2021 target.
7.3.3.16
25.9
Miles UG
104% Undergrounding of electric lines and/or equipment
Volume vs 2021 Goal: 25.92 of 25 miles UG (104%)
Key Actions: Program achieved 2021 target.
7.3.3.17.2
100% Transmission overhead system hardening
Volume vs 2021 Goal: 6.7 of 6.7 miles OH (100%), 3.4 of 2.7 miles DUB (125%)
Key Actions: Program achieved 2021 target.
7.3.3.18.1
10
Base stations
100% Distribution communications reliability improvements
Volume vs 2021 Goal: 10 of 10 base stations (100%)
Key Actions: Program achieved 2021 target.
7.3.3.11.3
735
Generators
123% Resiliency assistance programs
Volume vs 2021 Goal: 735 of 600 generators (123%)
Key Actions: Program ahead of 2021 Change Order target.
7.3.3.17.1
100
Miles hardened
100% Distribution overhead system hardening
Volume vs 2021 Goal: 100 of 100 miles hardened (100%)
Key Actions: Program achieved 2021 target.
7.3.3.9
6.9
Miles Distribution OH
100% Cleveland National Forest distribution and transmission system hardening
Volume vs 2021 Goal: 6.9 of 7 miles hardened (100%)
Key Actions: Program achieved 2021 target.
7.3.3.18.2
1,789
Lightning arrestors
128% Lightning arrestor removal and replacement
Volume vs 2021 Goal: 1,789 of 1,400 lightning arrestors replaced (128%)
Key Actions: Program exceeds 2021target.
7.3.3 – Grid Design and System Hardening (2 of 2)
3.4 DUB
6.7 OH

## Slide 6: Q4 Activity Status vs 2021 Goals
7.3.4.1
22,354
Inspections
100% Detailed inspections of distribution electric lines and equipment
Volume vs 2021 Goal: 22,354 of 22,269 inspections (100%)
Key Actions: Program achieved 2021 target.
95% Infrared inspections of distribution electric lines and equipment
Volume vs 2021 Goal: 17,068 of 18,000 inspections (95%)
Key Actions: Program achieved 2021 target.
89% Intrusive pole inspections
Volume vs 2021 Goal: 8,721 of 9,796 inspections (89%)
Key Actions: Program did not meet 2021 target.
97% Drone assessments of distribution infrastructure
Volume vs 2021 Goal: 21,420 of 22,000 inspections (97%)
Key Actions: Program achieved 2021 target.
116% Detailed inspections of transmission electric lines and equipment
Volume vs 2021 Goal: 1,957 of 1,680 inspections (116%)
Key Actions: Program exceeded 2021 target.
95% Infrared inspections of transmission electric lines and equipment
Volume vs 2021 Goal: 6,239 of 6,565 inspections (95%)
Key Actions: Program achieved 2021 target.
107% HFTD Tier 3 inspections
Volume vs 2021 Goal: 11,535 of 10,815 inspections (107%)
Key Actions: Program achieved 2021 target.
7.3.4 – Asset Management and Inspections (1 of 2)
7.3.4.2
1,957
Inspections
7.3.4.4
17,068
Inspections
7.3.4.6
8,721
Inspections
7.3.4.9.2
21,420
Inspections
7.3.4.5
6,239
Inspections
7.3.4.9.1
11,535
Inspections
120% Drone assessments of transmission infrastructure
Volume vs 2021 Goal: 1,440 of 1,200 inspections (8%)
Key Actions: Program ahead of November 1 Change Order target.
7.3.4.9.4
1,440
Inspections

## Slide 7: Q4 Activity Status vs 2021 Goals
7.3.4 – Asset Management and Inspections (2 of 2)
7.3.4.10
86,490
Inspections
101% Patrol inspections of distribution electric lines and equipment
Volume vs 2021 Goal: 86,490 of 86,000 inspections (101%)
Key Actions: Program achieved 2021 target.
7.3.4.11
6,423
Inspections
91% Patrol inspections of transmission electric lines and equipment
Volume vs 2021 Goal: 6,429 of 7,024 inspections (91%)
Key Actions: Program achieved 2021 target.
7.3.4.14
405
Inspections
123% Substation inspections
Volume vs 2021 Goal: 405 of 330 inspections (123%)
Key Actions: Program exceeded 2021 target.
7.3.4.9.5
1,652
Inspections
100% Additional transmission aerial 69kV tier 3 visual inspection
Volume vs 2021 Goal: 1,652 of 1,654 inspections (100%)
Key Actions: Program achieved 2021 target.

## Slide 8: Q4 Activity Status vs 2021 Goals
7.3.5 – Vegetation Management and Inspections
110% Detailed inspections of vegetation around distribution electric lines and equipment
Volume vs 2021 Goal: 502,132 of 455,000 trees inspected (110%)
Key Actions: Program achieved 2021 target.
74% Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Volume vs 2021 Goal: 12,579 of 17,000 trees trimmed/removed (74%)
Key Actions: Program did not achieve 2021 target.
99% Vegetation management to achieve clearances around electric lines and equipment
Volume vs 2021 Goal: 35,102 of 35,500 poles brushed (99%)
Key Actions: Program achieved 2021 target.
92% Fuels management and reduction of "slash" from vegetation management activities
Volume vs 2021 Goal: 203 of 500 poles cleared (92%)
Key Actions: Program achieved 2021 target.
7.3.5.2
502,132
Trees inspected
7.3.5.9
12,579
Trees trimmed/removed
7.3.5.20
35,102
Poles brushed
7.3.5.5
463
Poles cleared

## Slide 9: Appendix
Off Track Activity Details

## Slide 10: 2021 WMP Off Track Activities – Details
One circuit, C222, was delayed due to Caltrans permits, likely until Q4 2022. Two additional circuits, C974 and C221, were not completed due to timing and unfinished design scoping in coordination with traditional hardening programs.
Several other circuits were placed on design hold based on WINGS analysis and subsequent decision to rescope these traditional hardening projects with covered conductor and undergrounding, resulting in the removal of these circuits from the original target.
Covid-19 delays regarding supply chain management of generators and a high demand of generator orders during severe weather conditions throughout the country delayed generator deliveries.
County permitting proved to take much longer than expected for commercial customer installations. Air Pollution Permit process especially proved to extend commercial completion dates by 3-6 months. A handful of backup power systems had to be redesigned to comply with new rooftop safety standards.
Mobile Home Park Resilience efforts were also delayed due to system redesigns, redrafting of customer Equipment User Agreements, mobile home community board approvals delayed signing of agreements and County permitting took longer than expected.
Contracted installers and residential customers had difficulty coordinating date with County to perform Final Safety Inspections in a timely fashion for residential generator installations. County can only provide so many Final Safety Inspections per week.
86% fully complete, but important to acknowledge many installations were well along the pipeline of the installation process
(ie. 467 User Agreements signed and 406 generators in the ground requiring only safety inspections, propane tank installations or minor electrical updates).
7.3.3.9
4
Circuits Enabled
50% Installation of system automation equipment
Volume vs 2021 Goal: 4 of 8 circuits enabled (50%)
Key Actions: Program did not meet 2021 target.
7.3.3.11.2
355
Generators
86% Standby Power Programs
Volume vs 2021 Goal: 355 of 413 generators (86%)
Key Actions: Program did not meet 2021 target.

## Slide 11: 2021 WMP Off Track Activities – Details
SDG&E did not fully complete the initial target of 9,796 inspections due to planned intrusive inspections being completed early in 2020. Of the 14,450 intrusive inspections performed in 2020, 700 of those were planned for 2021, but completed in 2020 through our special request process. These inspections were canceled for 2021, resulting in a reduced target that was not discovered until after the Change Order deadline of November 1st had passed. Using the modified target of 9,096 intrusive inspections, SDG&E would be 96% complete with this initiative in 2021.
The initial 17,000 target used a simple methodology assumption that all 83,000 inventory trees within the HFTD would require enhanced clearances within 5 years. The reality is this is not the case. The determination of which trees require annual work depends on their proximity to the lines, hazards, expected growth rate, and the annual trim cycle. A more realistic methodology for determining the annual target number would consider actual trim frequency for forecasting. A revised target number based on trim frequency where the tree was trimmed at least 5 of the last 10 years, and the tree had no previous enhanced trim in last 10 years with a current line clearance < 8 feet will be used moving forward. This new methodology has the target set at 12,500 which then aligns with the work that actually needs to be completed and this updated methodology will be applied to future targets.
7.3.4.6
8,721
Inspections
89% Intrusive Pole Inspections
Volume vs 2021 Goal: 8,721 of 9,796 inspections (89%)
Key Actions: Program did not meet 2021 target.
7.3.5.9
12,578
Trees trimmed /removed
74% Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Volume vs 2021 Goal: 12,578 of 17,000 trees trimmed/removed (74%)
Key Actions: Program did not meet 2021 target.