## Crescent City 2020 (hidden)
Crescent City 2020 Pole Clearing
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Lines Miles Complete | Percentage Complete | Post Inspect (x) | Comments
5R151 | Roosevelt | 9.54 | 2020-01-13 | 2019-12-02 | 2019-12-17 | 9.54 | 100%
5R152 | Belmont | 38.86 | 2020-01-13 | 2019-12-14 | 2020-02-21 | 38.86 | 100%
5R153 | Dead Lake | 7.52 | 2020-02-24 | 2020-02-24 | 2020-02-26 | 7.52 | 100%
5R147 | Lake Earl | 13.48 | 2020-03-05 | 2020-03-02 | 2020-04-03 | 13.48 | 100%
5R195 | City | 21.53 | 2020-03-12 | 2020-03-26 | 2019-05-18 | 21.53 | 100%
5R194 | Industrial | 18.23 | 2020-04-02 | 2019-05-19 |  | 17.8654 | 98%
5R106C | Obrien (CA) | 3.39 | 2020-04-27 | 2020-05-25 | 2020-05-28 | 3.39 | 100%
6R3 | Patricks Creek | 6.89 | 2020-04-30 | 2020-05-25 | 2020-05-29 | 6.89 | 100%
5R96 | East West | 10.04 | 2020-05-09 | 2020-06-01 | 2020-06-19 | 10.04 | 100%
5R165 | Smith River | 20.68 | 2020-05-23 | 2020-06-17 | 2020-07-24 | 20.68 | 100%
5R170 | North | 18.95 | 2020-06-20 | 2020-07-21 | 2020-10-15 | 18.95 | 100%
5R171 | Sawmill | 20.07 | 2020-07-30 | 2020-07-28 | 2020-11-10 | 20.07 | 100%
5R370 | Lillie | 22.13 | 2020-08-28 | 2020-07-21 | 2020-09-17 | 22.13 | 100%
5R371 | Azalea | 11.04 | 2020-09-19 | 2020-07-28 | 2020-07-29 | 11.04 | 100%
5R166 | Southbank | 12.52 | 2020-09-26 | 2020-11-25 | 2020-12-03 | 12.52 | 100%
5R167 | Highway 101 | 30.33 | 2020-10-10 | 2020-12-04 | 2021-01-08 | 30.33 | 100%
5R160 | Crescent | 11.21 | 2020-11-28 |  |  | 11.21 | 100% |  | LRA
5R161 | Cooper Street | 11.44 | 2020-12-24 |  |  | 11.44 | 100% |  | LRA
5R156 |  | 0.006 | 2020-12-24 |  |  | 0.006 | 100% |  | LRA
5R154 |  | 0.008 | 2020-12-24 |  |  | 0.008 | 100% |  | LRA
| Totals : | 287.864 |  |  |  | 287.4994 | 99.87%

## Mt. Shasta 21- W (hidden)
Mt. Shasta 2021 Pole Clearing
Warranty Cycle
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete
5G93 | School Town | 38 |  |  |  | 0 | 0%
6G101 | Snowbrush | 4.14 |  |  |  | 0 | 0%
8G103 | Vollmers | 3.39 |  |  |  | 0 | 0%
5G99 | South | 15.09 |  |  |  | 0 | 0%
5G97 | North | 8.49 |  |  |  | 0 | 0%
8G65 | Castella | 6.23 |  |  |  | 0 | 0%
8G95 | Nutglade | 8.28 |  |  |  | 0 | 0%
7G75 | S' Dunsmuir | 3.66 |  |  |  | 0 | 0%
5G69 | Shasta Springs | 11.44 |  |  |  | 0 | 0%
7G73 | Sacramento | 1.99 |  |  |  | 0 | 0%
7G71 | Florance | 4.03 |  |  |  | 0 | 0%
5G79 | Pioneer | 34.28 |  |  |  | 0 | 0%
5G77 | BlackButte | 43.77 |  |  |  | 0 | 0%
5G45 | Shastina | 7.84 |  |  |  | 0 | 0%
5G83 | Belair | 78.91 |  |  |  | 0 | 0%
7G81 | Center Town | 2.3 |  |  |  | 0 | 0%
7G82 | N' Town | 3.01 |  |  |  | 0 | 0%
8G40 | Intl Paper | 0.02 |  |  |  | 0 | 0%
| Totals : | 274.87 |  |  |  | 0 | 0%

## Alturas 20 - W (hidden)
Alturas 2021 Pole Clearing
Warranty Cycle
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete
8L129 | Canby | 0.25 |  |  |  | 0 | 0%
5L86 | Industrial | 30.89 |  |  |  | 0 | 0%
5L87 | Hydro | 66.34 |  |  |  | 0 | 0%
5L97 | Cedarville | 18.54 |  |  |  | 0 | 0%
5L105 | New Pine Cr. | 13.73 |  |  |  | 0 | 0%
| Totals | 129.5 |  |  |  | 0 | 0%

## Crescent City 20- W (hidden)
Crescent City 2021 Pole Clearing
Warranty Cycle
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Lines Miles Complete | Percentage Complete | Post Inspect (x) | Comments
5R151 | Roosevelt | 9.54 |  |  |  | 0 | 0%
5R152 | Belmont | 38.86 |  |  |  | 0 | 0%
5R153 | Dead Lake | 7.52 |  |  |  | 0 | 0%
5R160 | Cresent | 11.21 |  |  |  | 0 | 0%
5R147 | Lake Earl | 13.48 |  |  |  | 0 | 0%
5R195 | City | 21.53 |  |  |  | 0 | 0%
5R194 | Industrial | 18.23 |  |  |  | 0 | 0%
5R106C | Obrien (CA) | 3.39 |  |  |  | 0 | 0%
6R3 | Patricks Creek | 6.89 |  |  |  | 0 | 0%
5R96 | East West | 10.04 |  |  |  | 0 | 0%
5R165 | Smith River | 20.68 |  |  |  | 0 | 0% |  | bee pole
5R170 | North | 18.95 |  |  |  | 0 | 0% |  | repelling
5R171 | Sawmill | 20.07 |  |  |  | 0 | 0%
5R370 | Lillie | 22.13 |  |  |  | 0 | 0%
5R371 | Azalea | 11.04 |  |  |  | 0 | 0%
5R166 | Southbank | 12.52 |  |  |  | 0 | 0%
5R167 | Highway 101 | 30.33 |  |  |  | 0 | 0%
5R161 | Cooper Street | 11.44 |  |  |  | 0 | 0% |  | LRA
5R156 |  | 0.006 |  |  |  | 0 | 0%
5R154 |  | 0.008 |  |  |  | 0 | 0%
| Totals : | 287.85 |  |  |  | 0 | 0%

## Tulelake 20- W (hidden)
Tulelake 2021 Pole Clearing
Warranty Cycle
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete
5L70 | Perez | 13.9 |  |  |  | 0 | 0%
5L66 | Clearlake | 7.57 |  |  |  | 0 | 0%
5L68 | Newell | 99.56 |  |  |  | 0 | 0%
5L20 | Malin City | 21.85 |  |  |  | 0 | 0%
5L82 | East | 93.61 |  |  |  | 0 | 0%
5L73 | Lava Beds | 27.1 |  |  |  | 0 | 0%
5L83 | Town | 62.43 |  |  |  | 0 | 0%
5L26 | Lake | 13.98 |  |  |  | 0 | 0%
5L64 | Cal-Ore | 22.9 |  |  |  | 0 | 0%
5L63 | Town | 37.24 |  |  |  | 0 | 0%
5L62 | Mill | 64.56 |  |  |  | 0 | 0%
4L3 | Red Rock | 106.18 |  |  |  | 0 | 0%
5L77 | South | 39.66 |  |  |  | 0 | 0%
5L78 | Sheep Mt. | 69.28 |  |  |  | 0 | 0%
| Totals : | 679.82 |  |  |  | 0 | 0%

## Yreka 20- W (hidden)
Yreka 2021 Pole Clearing
Warranty Cycle
Feeder # | Feeder Name | Line Miles | Planned Work Date | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete
5G5 | Main St. | 26.33 |  |  |  | 0 | 0%
5G149 | Highland | 52.96 |  |  |  | 0 | 0%
5G7 | Fairlane | 48.92 |  |  |  | 0 | 0%
5G21 | Grenada | 76.52 |  |  |  | 0 | 0%
5G31 | South | 24.45 |  |  |  | 0 | 0%
5G23 | White Mt. | 94.78 |  |  |  | 0 | 0%
4G1 | Lake | 24.95 |  |  |  | 0 | 0%
6G25 | Little Shasta | 52.08 |  |  |  | 0 | 0%
5G33 | Town -Ager | 39.36 |  |  |  | 0 | 0%
5G35 | Air Force | 77.82 |  |  |  | 0 | 0%
5G6 | Daggett | 37.61 |  |  |  | 0 | 0%
5G19 | Hornbrook | 95.12 |  |  |  | 0 | 0%
6G1 | Hydro | 0.045 |  |  |  | 0 | 0%
5G40 | Scott Bar | 59.19 |  |  |  | 0 | 0%
8G27 | Hamburg | 4.91 |  |  |  | 0 | 0%
5G39 | Seiad Cr | 24.61 |  |  |  | 0 | 0%
5G14 | Mill | 4.51 |  |  |  | 0 | 0%
5G16 | Town | 38.24 |  |  |  | 0 | 0%
5G63 | Callahan | 88.05 |  |  |  | 0 | 0%
5G41 | Etna Tie | 86.37 |  |  |  | 0 | 0%
5G2 | Peach Orchard | 85.69 |  |  |  | 0 | 0%
5G1 | Greenview | 52.61 |  |  |  | 0 | 0%
5G151 | Center Town | 10.25 | LRA |  |  | 0 | 0%
5G163 | Lennox | 11.11 | LRA |  |  | 0 | 0%
| Totals : | 1116.485 |  |  |  | 0 | 0%

## LRA 2021
LRA 2021 Pole Clearing
Clear and Treat
District | Feeder # | Feeder Name | Tier | Line Miles | Planned Work Date | Estimated Poles | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete | # Poles Complete
Yreka | 5G151 | Center Town | 2 | 9.7 | March | 142 | 2021-02-15 | 2021-03-04 | 9.7 | 100% | 147
| 5G163 | Lennox | 2 | 11.3 | March | 159 | 2021-03-05 | 2021-04-05 | 11.3 | 100% | 191
| 5G149 | Highland | 2 | 52.96 | April | 201 | 2021-04-06 | 2021-08-30 | 52.96 | 100% | 273
| 5G5 | Main St. | 2 | 10.4 | April | 95 | 2021-06-21 | 2021-07-07 | 10.4 | 100% | 107
| 5G7 | Fairlane | 2 | 66.4 | April | 75 | 2021-05-27 | 2021-06-17 | 66.4 | 100% | 88
| 5G21 | Grenada | 2 | 77.2 | May | 276 | 2021-07-07 | 2021-09-29 | 77.2 | 100% | 257
| 5G1 | Greenview | 2 | 53.7 | June | 147 | 2021-03-25 | 2021-04-22 | 53.7 | 100% | 155
| 5G2 | Peach Orchard | 2 | 87.6 | June | 126 | 2021-03-25 | 2021-08-12 | 87.6 | 100% | 113
| 5G63 | Callahan | 2 | 89.6 | July | 81 | 2021-08-04 | 2021-08-19 | 89.6 | 100% | 87
| 5G41 | Etna Tie | 2 | 88.2 | July | 333 | 2021-05-27 | 2021-08-03 | 88.2 | 100% | 323
|  | Totals : |  | 547.06 |  | 1635 |  |  | 547.06 | 100% | 1741
Clear and Treat
District | Feeder # | Feeder Name | Tier | Line Miles | Planned Work Date | Estimated Poles | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete | # Poles Complete
Shasta | 5G45 | Shastina | 3 | 8.3 | April | 105 | 2021-04-12 | 2021-04-26 | 8.3 | 100% | 101
| 5G83 | Bel-Air | 3 | 80 | April | 224 | 2021-04-19 | 2021-04-29 | 80 | 100% | 208
| 5G69 | Shasta Springs | 3 | 11.7 | May | 97 | 2021-04-22 | 2021-04-28 | 11.7 | 100% | 100
| 5G77 | Black Butte | 3 | 45.4 | May | 123 | 2021-04-28 | 2021-05-10 | 45.4 | 100% | 109
| 5G79 | Pioneer | 3 | 35 | June | 104 | 2021-05-03 | 2021-05-10 | 35 | 100% | 116
| 7G71 | Florence Ave | 3 | 4 | June | 65 | 2021-05-11 | 2021-05-13 | 4 | 100% | 66
| 7G73 | Sacramento Ave | 3 | 2 | June | 37 | 2021-05-17 | 2021-05-18 | 2 | 100% | 14
| 7G75 | S Dunsmuir | 2 | 3.5 | June | 27 | 2021-05-17 | 2021-05-18 | 3.5 | 100% | 19
| 7G81 | Center Town | 2 | 2.5 | July | 51 | 2021-05-26 | 2021-05-27 | 2.5 | 100% | 35
| 7G82 | North Town | 2 | 3.1 | July | 78 | 2021-05-19 | 2021-05-25 | 3.1 | 100% | 45
| 8G40 | International Paper | 2 | 0.1 | July | 4 | 2021-01-04 | 2021-01-04 | 0.1 | 100% | SRA poles
|  | Totals : |  | 195.6 |  | 915 |  |  | 195.6 | 100% | 813
Clear and Treat
District | Feeder # | Feeder Name | Tier | Line Miles | Planned Work Date | Estimated Poles | Clear/Treat Start Date | Clear/Treat Completion Date | Miles Complete | Percentage Complete | # Poles Complete
Alturas | 5L87 | Hydro | 2 | 66.1 | May/June | 353 | 2021-04-12 | 2021-08-24 | 65.439 | 99% | 411
| 5L97 | Cedarville | 2 | 18.6 | June/July | 154 | 2021-04-12 | 2021-06-01 | 18.6 | 100% | 151
|  | Totals : |  | 84.7 |  | 507 |  |  | 84.039 | 45% | 562
|  | Totals : |  | 827.36 |  | 3057 |  |  | 826.699 | 99.92% | 3116