## Updated Tables 8.3.1-8.3.3
1. By June 1 of current year
· Table PG&E-8.3-1: PSPS Impact Mitigation Commitments To Be Completed by June 1, 2021
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
| Situational Awareness and Forecasting | B.02 | 7.3.2.1.2 |  | 7.3.2.1.2 | Enhancements to Fuel Moisture Sampling and Modeling efforts | Expand the historical Dead Fuel Moisture (DFM) and LFM Live Fuel Moisture (LFM) climatology at 2 x 2 km resolution to back-fill all of 2020. | 0 | 0 | N/A | The moisture content in living and dead vegetation is a critical component of PG&E’s FPI model used in PSPS event scoping. This initiative has zero direct impacts to frequency and scope and the impact of duration is not readily quantifiable. This is not readily quantifiable because it will improve the accuracy of our PSPS scope and may add or remove areas from PSPS scope with this further analysis. | 2021-06-01
| Situational Awareness and Forecasting | B.03 | 7.3.2.1.2 |  | 7.3.2.1.2 | Enhancements to Fuel Moisture Forecasting | Evaluate extending the deterministic DFM and LFM forecast to provide another 24 hours of forecast data. | 0 | 0 | N/A | The moisture content in living and dead vegetation is a critical component of PG&E’s FPI model used in PSPS event scoping. This initiative has zero direct impacts to frequency and scope and the impact of duration is not readily quantifiable. This will not affect our final PSPS scope but will improve our forecasting accuracy in advance of a PSPS event. | 2021-06-01
| Situational Awareness and Forecasting | B.07 | 7.3.2.1.6 |  | 7.3.2.1.6 | Information Sharing | Adjust the public 7 day forecast to provide more granularity and clarity around the potential for a PSPS event. | N/A | N/A | N/A | This initiative is foundational, so it does not directly support the evolution of the PSPS program. However, this initiative indirectly supports the evolution of the PSPS program by enabling the meteorology tools and models that directly are used in event scoping. These enabling activities include high performance cloud computing, building Diablo seasonal wind forecasting capabilities, and addressing weather forecast model uncertainty. | 2021-06-01
2. By September 1 of current year
· Table PG&E-8.3-2: PSPS Impact Mitigation Commitments To Be Completed After June 1, 2021, and Prior to SEPTEMBER 1, 2021
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
| Situational Awareness and Forecasting | B.11 | 7.3.2.4 |  | 7.3.2.4 | Enhancements to Fire Potential Index (FPI) Model | Enhance the FPI Model by September 1, 2021 using additional data and an enhanced fire occurrence dataset. PG&E also plans to incorporate the new Technosylva fuel mapping layer into FPI calculations if it provides more predictive skill of large fires. | 0 | 0 | N/A | The FPI Model is used as an hourly input to PG&E's PSPS framework. Improvements to this model could directly impact PSPS scope and frequency. However, this work is not complete or approved so PG&E cannot quantify how this impacts models. | 2021-09-01
| Situational Awareness and Forecasting | B.13 | 7.3.2.6 |  | 7.3.2.6 | Enhancements to Outage Producing Wind (OPW) Model | Recalibrate the OPW Model using the 2 km climatology that will be extended to capture all events in 2020, including sustained and momentary outages, as well as damages found in PSPS events of 2020. | 0 | 0 | N/A | Improved granularity in forecasting wind events and its impact on electrical equipment can directly reduce the scope and frequency of PSPS events. In addition to SOPP, The OPW model that is part of the initiative is directly used in PSPS scoping. However, this work is not complete or approved so PG&E cannot quantify how this impacts models. | 2021-09-01
0 | Grid Design and System Hardening | C.03 | 7.3.3.11.1 | 7.3.3.11.1B | 7.3.3.11.1/ 7.3.3.11.1B | Generation for PSPS Mitigation (Substation Distribution Microgrids) | Prepare at least 8 substations to receive temporary generation for 2021 PSPS mitigation. | 0 | 477.3518 | 11504.2269 | Temporary distribution and substation generation can allow "safe-to-energize" customers to remain energized even while the assets that normally serve them are de-energized, supporting PSPS scope reduction. See quantified benefits. The incorporation of this mitigation is expected to have a non-zero impact on PSPS scope and duration. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-08-01
| Grid Design and System Hardening | C.07 | 7.3.3.8.2 |  | 7.3.3.8.2, | Transmission Switches | Install 29 SCADA transmission switches to provide switching flexibility and sectionalization for PSPS events. | N/A | 381.408 | 13373.483 | Transmission switches create flexibility in operating the grid by more precisely controlling where PSPS de-energizations occur. See quantified benefits. The incorporation of this mitigation is expected to have a non-zero impact on PSPS scope and duration. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-09-01
| Grid Design and System Hardening | C.10 | 7.3.3.17.4 |  | 7.3.3.17.4, | Rapid Earth Fault Current Limiter (REFCL) Pilot | PG&E plans to have the final results from this pilot project by September 2021 to inform the long term REFCL strategy. | N/A | 0 | 0 | This pilot technology could enable lines to remain energized during PSPS events, reducing the scope and frequency of event in the long-term. This technology is currently in pilot mode and not expected to be used to keep lines energized during PSPS events in 2021, so the impact has been quantified as 0. | 2021-09-01
3. Next Annual WMP Update
· table PG&E-8.3-3: PSPS: Mitigation Commitments To Be Completed After September 1, 2021 and Prior to the Next Annual Update
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
| Risk Assessment and Mapping | A.01 | 7.3.1.5 |  | 7.3.1.5 | Match drop simulations (24 additional hours of forecast data) | Enhance the wildfire spread project in 2021 by expanding the forecast horizon from three to four days. | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand the level of wildfire consequence given an ignition on our system. By understanding locations where the consequence of a wildfire is high, PG&E can target investments in minimizing wildfire risk, as well as understand locations that would be affected by PSPS due to the consequence of a wildfire. | 2021-12-31
| Risk Assessment and Mapping | A.02 | 7.3.1.5 |  | 7.3.1.5 | Match drop simulations (update fuel model layers) | Update the fuel model layers on annual basis (Technosylva). | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand the level of wildfire consequence given an ignition on our system. By understanding locations where the consequence of a wildfire is high, PG&E can target investments in minimizing wildfire risk, as well as understand locations that would be affected by PSPS due to the consequence of a wildfire. | 2021-12-31
| Risk Assessment and Mapping | A.03 | 7.3.1.3 |  | 7.3.1.3 | Re-Train Vegetation and Equipment Probability of Ignition Models | PG&E’s Vegetation Probability of Ignition and Equipment Probability of Ignition Models will see more improvements with another year of data (2020) incorporated. | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand which locations have higher ignition probabilities either from asset or vegetation failures. With this information, this presents PG&E the ability to target investments in those areas to minimize wildfire risk. | 2021-12-31
| Risk Assessment and Mapping | A.04 | 7.3.1.1 | 4.5.1 | 7.3.1.1/ 4.5.1 | Risk Mapping Improvements (Transmission) | Improve Transmission Risk Modeling to provide more standardized wildfire risk mapping/ranking between the various controls and mitigations. | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand the level of wildfire risk at various circuit segments of PG&E's system. In combination with the potential frequency of PSPS events in this location, this initiative presents PG&E the ability to selective apply mitigations that benefit both wildfire and the PSPS program. | 2021-12-31
| Risk Assessment and Mapping | A.05 | 7.3.1.1 | 7.3.1.4 | 7.3.1.1/ 7.3.1.4 | Risk Mapping Improvements (Distribution) | Improve Distribution Risk Modeling to include: 1) ability to compare wildfire risks for different risk drivers, 2) ability to measure the risk reduction of specific mitigations, 3) add wildfire risk values for distribution line locations beyond the HFTD and High Fire Risk Areas (HFRA) areas to include all of PG&E’s distribution lines. | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand the level of wildfire risk at various circuit segments of PG&E's system. In combination with the potential frequency of PSPS events in this location, this initiative presents PG&E the ability to selective apply mitigations that benefit both wildfire and the PSPS program. | 2021-12-31
| Risk Assessment and Mapping | A.06 | 4.5.1 | 4.1 | 4.5.1/ 4.1 | Model PSPS customer impacts at circuit level | Develop a more granular, circuit level model, to assess PSPS customer impacts. | N/A | N/A | N/A | This initiative is foundational, so it does not directly reduce PSPS scope, frequency or duration. However, this initiative indirectly supports the evolution of the PSPS program by helping PG&E understand the level of PSPS consequence at each circuit of PG&E's system, providing much more accuracy and granularity. With scope, frequency and duration of PSPS events at the circuit level, this initiative allows PG&E the ability to selectively apply mitigations to better target the need at the circuit level. | 2021-09-30
| Situational Awareness and Forecasting | B.01 | 7.3.2.1.1 |  | 7.3.2.1.1 | Numerical Weather Prediction | Make enhancements to numerical weather prediction program. | 0 | 0 | N/A | Improved granularity of weather forecasts can directly reduce footprint of PSPS events (i.e., scope, or frequency, or both) and is a significant contributor to the long-term PSPS vision. However, PG&E does not expect a significant improvement in granularity of weather forecasts so this, so we quantified the impact as 0. | 2021-12-31
· PG&E-8.3-3: PSPS: Mitigation Commitments To Be Completed After September 1, 2021 and Prior to the Next Annual Update (continued)
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
| Situational Awareness and Forecasting | B.04 | 7.3.2.1.3 |  | 7.3.2.1.3 | Enhancements to Weather Station Project (Installations and Optimization) | Install or optimize the location of 300 weather stations throughout PG&E’s territory. | 0 | 0 | N/A | Data from weather stations installed in PG&E’s service area are used to help forecast and monitor for high fire-risk weather conditions, which helps inform implementation of additional precautionary measures such as PSPS. These weather stations could indirectly impact PSPS thresholds, scope, and frequency. However, this work is not complete or approved so PG&E cannot quantify how this impacts models. | 2021-12-31
| Situational Awareness and Forecasting | B.05 | 7.3.2.1.3 |  | 7.3.2.1.3 | Enhancements to Weather Station Project (Wind Gust Model) | Develop a weather-station specific wind gust model based on machine-learning or statistical techniques. | 0 | 0 | N/A | Data from weather stations installed in PG&E’s service area are used to help forecast and monitor for high fire-risk weather conditions, which helps inform implementation of additional precautionary measures such as PSPS. These weather stations could indirectly impact PSPS thresholds, scope, and frequency. However, this work is not complete or approved so PG&E cannot quantify how this impacts models. | 2021-12-31
| Situational Awareness and Forecasting | B.06 | 7.3.2.1.6 |  | 7.3.2.1.6 | Medium- to Seasonal-Range Diablo Wind Forecasting | Develop and deploy a seasonal Diablo wind event forecasting system to obtain longer lead-times of upcoming Diablo wind events. | N/A | N/A | N/A | This initiative is foundational, so it does not directly influence scope, duration or frequency. However, this initiative indirectly supports the evolution of the PSPS program by enabling the meteorology tools and models that directly are used in event scoping. These enabling activities include high performance cloud computing, building Diablo seasonal wind forecasting capabilities, and addressing weather forecast model uncertainty. | 2021-12-31
| Grid Design and System Hardening | C.01 | 7.3.3.8.3 |  | 7.3.3.8.3 | Assess Motorized Switch Operator (MSO) switches | Assess various alternatives to address the ignition risk associated with MSO switches. Explore several pilot options to inform the best alternatives and select the appropriate corrective action for MSO’s for the next WMP update. | N/A | N/A | N/A | This initiative does not directly contribute to reducing PSPS scope, duration, or frequency. However, this initiative addresses the ignition risk associated with MSO switches, and thus represents a potential reduction in wildfire risk. | 2021-12-31
0 | Grid Design and System Hardening | C.02 | 7.3.3.11.1 | 7.3.3.11.1C | 7.3.3.11.1/ 7.3.3.11.1C | Generation for PSPS Mitigation (Temporary Distribution Microgrids) | Develop at least 5 additional distribution microgrid Pre-installed Interconnection Hubs (PIH). | 0 | 477.3518 | 11504.2269 | See quantified benefits. The incorporation of this mitigation is expected to have a non-zero impact on PSPS scope and duration. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of the 2021 WMP Revision Notice response for discussion). | 2021-12-31
| Grid Design and System Hardening | C.04 | 7.3.3.11.3 |  | 7.3.3.11.3 | Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers | Equip at least 23 PG&E Service Centers & Materials Distribution Centers to receive permanent or temporary generation. | N/A | N/A | N/A | Equipping PG&E Service Centers & Materials Distribution Centers to receive permanent or temporary generation will not have a direct impact on PSPS event characteristics, but enables PG&E employees supporting PSPS events and restoration efforts to complete their work, accessing fuel islands, gate operators, and buildings at these PG&E facilities. | 2021-12-31
0 | Grid Design and System Hardening | C.05 | 7.3.3.17.5 |  | 7.3.3.17.5 | Remote Grid | Begin operations of the first Remote Grid site by the end of 2021. | 0 | 0 | 0 | When a remote area is "safe to energize" but subject to PSPS events due to the upstream connection to the grid being in the weather scope, then a remote grid can reduce or eliminate customers in that area from PSPS scope. The benefits of Remote Grid are projected to be zero because of uncertainties associated with the timing of project execution and because site designs have not yet been evaluated for PSPS impacts. However, given that typically only a handful of customers are served by each remote grid location, the contribution of this initiative to PSPS scope reduction is expected to be relatively minor. Remote Grid is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-12-31
· Table PG&E-8.3-3: PSPS: Mitigation Commitments To Be Completed After September 1, 2021 and Prior to the Next Annual Update (continued)
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
0 | Grid Design and System Hardening | C.06 | 7.3.3.8.1 |  | 7.3.3.8.1 | Distribution Sectionalizing (automated devices) | Install at least 250 more distribution sectionalizing devices integrating learnings from 2020 PSPS events, 10-year historical look-back of previous severe weather events, and feedback from county leaders and critical customers. | 0 | 1289.2248 | 36597.0396 | Sectionalizing devices create flexibility to more precisely control which areas of the grid are impacted by a PSPS event. See quantified benefits. The incorporation of this mitigation is expected to have a non-zero impact on PSPS scope and duration. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-12-31
| Grid Design and System Hardening | C.08 | 7.3.3.9.1 |  | 7.3.3.9.1 | Distribution line legacy 4C controllers | Replace all remaining (~84) distribution line legacy 4C controllers that are in Tier 2 and Tier 3 HFTD areas. | N/A | N/A | N/A | This initiative does not directly contribute to reducing PSPS scope, duration, or frequency. However, the replacement of the legacy SCADA recloser controls protecting fire Tier 2 and 3 HFTD areas with new recloser controllers that enable the use of protective features designed to address high impedance fault conditions contributes to maintaining the health of existing assets, which may indirectly contribute to enabling these assets to stay energized during a PSPS event. Improved asset health may also indirectly decrease PSPS outage duration times by eliminating hazards that would otherwise increase the time needed to patrol and inspect after the weather "All Clear." | 2021-12-31
| Grid Design and System Hardening | C.09 | 7.3.3.9.2 |  | 7.3.3.9.2 | Fuse Savers (Single phase reclosers) | Install 70 sets of single phase reclosers. | N/A | N/A | N/A | Generally, single phase reclosers can be used as automatic sectionalizing devices where field conditions do not require a three phase recloser. However, this initiative does not directly contribute to reducing PSPS scope, duration, or frequency because the devices installed for this initiative are not targeted at lines likely to be impacted for PSPS. However, by eliminating the risk associated with wire down events where a downed wire remains energized by a back-feed condition, single phase reclosers indirectly contribute to enabling these assets to stay energized during a PSPS event. System automation contributes to further flexibility in operating the grid and indirectly contributes to the long term vision to reduce scope and duration of PSPS events. | 2021-12-31
0 | Grid Design and System Hardening | C.13 | 7.3.3.17.1 |  | 7.3.3.17.1 | System Hardening (line miles) | Harden 180 highest risk miles. | 0 | 168.2627 | 3582.8833 | System Hardening significantly reduces the potential of ignition from phase-to-phase contact and objects falling into the line. Subject to Wildfire Steering Governance Committee approval, PG&E plans to incorporate modified PSPS criteria for overhead hardened distribution lines into its PSPS scoping models. The incorporation of this mitigation is expected to have a non-zero impact on PSPS scope and duration. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-12-31
0 | Grid Design and System Hardening | C.14 | 7.3.3.17.6 |  | 7.3.3.17.6 | Butte County Rebuild | Underground 23 miles. | 0 | 0 | 0 | Over the course of several years, PG&E is rebuilding electric circuits in the towns of Paradise and Magalia by undergrounding close to 200 miles. Customers on fully undergrounded circuits (from customer to substation) will be removed from PSPS scope in events where the substation has transmission that is in service. The Butte Rebuild Program will reduce PSPS event scope over time and is incorporating PSPS mitigation into the work prioritization while working with the community to align with their rebuild plans. However, the underground work is being completed in a patchwork manner, so wholesale PSPS elimination in these two towns is not anticipated until the completion of the work, currently scheduled for the end of 2025. | 2021-12-31
0 | Grid Design and System Hardening | C.15 | 7.3.3.17.2 |  | 7.3.3.17.2 | System Hardening - Transmission Conductor | Replace approximately 92 miles of conductor on lines traversing HFTD, including associated asset hardware. | 0 | 0 | 0 | The main purpose of this WMP commitment is to demonstrate that line replacement work in HFTD has the effect of transmission system hardening. While conductor replacement will increase the likelihood that a transmission line meets transmission health requirements that are part of the OA model, this work is not targeted to address PSPS or lines likely to be in scope for PSPS. Even if these repairs do improve lines that may be in scope for PSPS, the repairs may not always enable transmission lines to remain energized if the weather is strong enough or customers may still be de-energized due to distribution impacts. For all of these reasons, PG&E quantifies the benefits of this activity as 0. | 2021-12-31
0 | Vegetation Management and Inspections | E.01 | 7.3.5.15 |  | 7.3.5.15 | EVM (line miles) | Complete 1,800 circuit miles and mitigate approximately 190,000 trees. | 0 | 0 | 0 | The main purpose of this WMP commitment is to demonstrate that line replacement work in HFTD has the effect of transmission system hardening. While conductor replacement will increase the likelihood that a transmission line meets transmission health requirements that are part of the OA model, this work is not targeted to address PSPS or lines likely to be in scope for PSPS. Even if these repairs do improve lines that may be in scope for PSPS, the repairs may not always enable transmission lines to remain energized if the weather is strong enough or customers may still be de-energized due to distribution impacts. For all of these reasons, PG&E quantifies the benefits of this activity as 0. | 2021-12-31
0 | Vegetation Management and Inspections | E.03 | 7.3.5.3 |  | 7.3.5.3 | VM Transmission Right of Way Expansion | Perform Transmission ROW expansion on approximately 200 miles within HFTD areas. | 0 | 5779.9094 | 131574.996 | Right of Way Expansion within “Detailed Inspections of Vegetation Around Transmission Electric Lines and Equipment” directly reduces the scope and duration of PSPS events. See quantified benefits. However, it is expected to have zero impact on event frequency because this mitigation does not have a footprint large enough to eliminate an entire PSPS event (please see discussion on question 3 of this Revision Notice response for discussion). | 2021-12-31
| Emergency Planning and Preparedness | I.01 | 7.3.9.1 |  | 7.3.9.1 | Staffing to Support Service Restoration | Hire approximately 40 Linemen and 100 Apprentices. | N/A | N/A | N/A | This initiative is foundational, so it does not directly support the evolution of the PSPS program. However, this initiative indirectly supports the evolution of the PSPS program because workforce training on PSPS tools and processes is essential to efficient execution of re-energization and supports the long term vision to reduce duration of PSPS events. | 2021-12-31
| Emergency Planning and Preparedness | I.02 | 7.3.9.1 |  | 7.3.9.1 | Trained Workforce for Service Restoration | All required personnel complete identified trainings to improve PSPS event execution (including SEMS, Access and Functional Needs and other critical training). | N/A | N/A | N/A | This initiative is foundational, so it does not directly support the evolution of the PSPS program. However, this initiative indirectly supports the evolution of the PSPS program because workforce training on PSPS tools and processes is essential to efficient execution of re-energization and supports the long term vision to reduce duration of PSPS events. | 2021-12-31
· Table PG&E-8.3-3: PSPS: Mitigation Commitments To Be Completed After September 1, 2021 and Prior to the Next Annual Update (continued)
| Plan Area | Unique ID | Section Reference |  | Section Reference | Activity | Commitment Description | Estimated quantitative reduction of frequency (Number of Events) | Estimated quantitative reduction of scope per event (Number of Customers) | Estimated quantitative reduction of duration per event (Customer Hours) | Explanation if values are zero / unobtainable | Commitment Date
| Stakeholder Cooperation and Community Engagement | J.01 | 7.3.10.1 | 8.4 | 7.3.10.1/ 8.4 | Community Based Organizations (CBOs) Coordination | Partner with CBOs in targeted communities to increase their capacity to serve AFN communities, such as medically sensitive customers, low-income, limited- English speaking and tribal customers. | N/A | N/A | N/A | While these activities do not directly reduce event frequency, scope or duration, they do support the long term vision of limiting negative impacts from PSPS events by improving the preparedness of the most vulnerable customers for PSPS events. | 2021-12-31
| Stakeholder Cooperation and Community Engagement | J.02 | 7.3.9.2 | 7.3.10.1 | 7.3.9.2/ 7.3.10.1 | Community Engagement | Engage community stakeholders through offering: Wildfire Safety Working Sessions, workshops that review PG&E’s PSPS Policies and Procedures document, listening sessions, and Energy and Communications Providers Coordination Group meetings. | N/A | N/A | N/A | While these activities do not directly reduce event frequency, scope or duration, they do support the long term vision of limiting negative impacts from PSPS events by ensuring that the voices of impacted communities are heard so that PG&E can continue to improve its PSPS program. | 2022-02-01
| Stakeholder Cooperation and Community Engagement | J.03 | 7.3.9.2 | 7.3.10.1 | 7.3.9.2/ 7.3.10.1 | Customer and Community Outreach | Continue to enhance communications and engagement efforts with a focus on wildfire safety and preparedness for PSPS events - including Webinars/Community Meetings, Direct-to-Customer Outreach, developing and delivering informational video resources. | N/A | N/A | N/A | While these activities do not directly reduce event frequency, scope or duration, they do support the long term vision of limiting negative impacts from PSPS events by improving customer preparedness for PSPS events. | 2021-12-31
| Protocols on Public Safety Power Shutoff | K.01 | 8.4 | 8.2.4 | 8.4/ 8.2.4 | Customer and Agency Outreach During PSPS Events | Improve Customer and Agency Outreach During PSPS Events by: developing opt-in address alerts, conducting new message testing, promoting enrollment, hosting briefings, hosting cooperator calls. | N/A | N/A | N/A | While these activities do not directly reduce event frequency, scope or duration, they do support the long term vision of limiting negative impacts from PSPS events by improving customer preparedness for PSPS events. | 2021-12-31
| Protocols on Public Safety Power Shutoff | K.02 | 8.2.1 |  | 8.2.1 | Mitigate Impacts on De-Energized Customers | Work with partner organizations to provide outreach and support to vulnerable customers through programs such as the Disability Disaster Access and Resources Program (DDAR) and the Portable Battery Program (PBP). | N/A | N/A | N/A | While these activities do not directly reduce event frequency, scope or duration, they do support the long term vision of limiting negative impacts from PSPS events by improving the preparedness of the most vulnerable customers for PSPS events. | 2021-12-31
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Oram, Kevin @Stamp, Gareth Table 8.3