## Inspection Report Data
# | Inspection Report | Date Inspection Report Received | Date of Inspection | Report Item Number | Brief Description of Defect | Defect Severity | Defect Status | Response Summary | Corrective Action | Defect Corrected Date
1 | ELZ_PGE_20211214-01 | 2022-03-11 | 2021-12-14 | 1 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | Vegetation was trimmed from guy wire on 3/17/22. | Vegetation was trimmed from guy wire. | 2022-03-17
2 | ELZ_PGE_20211214-01 | 2022-03-11 | 2021-12-14 | 2 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | Vegetation was trimmed from guy wire on 3/17/22. | Vegetation was trimmed from guy wire. | 2022-03-17
3 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 1 | Excessive splicing in single span | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | The CAL Fire Wildfire Prevention Field Guide recommends auditors notify utilities to inspect spans that are identified with 3 or more splices, but does not prohibit more than 3 splices, nor prescribe any specific remediation for these conditions. Energy Safety confirmed on 3/13/23 to Regulatory Relations that this NOD is closed and no further actions are necessary. | None required | N/A
4 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 2 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | Vegetation was trimmed from guy wire on 3/17/22. | Vegetation was trimmed from guy wire. | 2022-03-17
5 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 3 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
6 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 4 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
7 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 5 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
8 | MJ4_PGE_20211207_01 | 2022-03-11 | 2021-12-07 | 6 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
9 | MJ4_PGE_20211203_01 | 2022-03-11 | 2021-12-03 | 1 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
10 | MJ4_PGE_20211203_01 | 2022-03-11 | 2021-12-03 | 2 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A
11 | MJ4_PGE_20211203_01 | 2022-03-11 | 2021-12-03 | 3 | Vegetation contacting guy wire above insulator | Category 3 – Minor: 12 months or resolution schedule included in WMP update | Closed by OEIS | No vegetation contacting guy wire above insulator. | None required | N/A