## Cover Sheet Tables 1-12
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines Appendix D, Section 1.2
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | Pacific Gas and Electric Company
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2022
Reporting Period quarter |  | Q4
Date Modified |  | 2023-02-01

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitativieObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Distribution Modeling Enhancements - Equipment Failure and Contact From Object | Develop additional Distribution Equipment Failure (EFF) and Distribution Contact From Object (CFO) sub-models. Conduct assessment to determine whether newly developed sub-models should be included in the WDRM model. | This initiative will help further develop PG&E's risk modeling capabilities. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | A.01 | PG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_A.01_2022 | 358 | Equipment ignition likelihood | No | [10 empty] | Develop additional Distribution Equipment Failure (EFF) and Distribution Contact From Object (CFO) sub-models. Conduct assessment to determine whether newly developed sub-models should be included in the WDRM model. | First drafts of the Equipment Failure and Contact from Object models were included as part of the 2022 WDRM v3. Scoping work for improved models as outlined in the schedule will begin in Q2 2022. | Developed scope for Equipment Failure (EFF) and Contact from Object (CFO) version 4 model improvements. Initiated Exploratory Data Analysis on model data and initial model runs on a subset of models. | Data pipelines for Asset models, including Capacitor Banks, Switches, Conductors, and Voltage Regulators have been built and exploratory data analysis has been performed. Asset model prototype training has begun. EVM work history data has been obtained and is being incorporated into the Vegetation model. Analysis of SALO tree mortality data is in progress. EPSS device activation history data has been obtained and analyzed in preparation for draft development into the probability of ignition model. | Finished new model analysis and presented results to Wildfire Risk Governance Steering Committee (WRGSC). Modeling approach was approved by the WRGSC. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Transmission Modeling Enhancements - Threat and Hazard Risk Drivers | Develop Threat and Hazard (Risk drivers) sub-models that cover: Threats (e.g., Atmospheric corrosion, Underground corrosion, Fatigue, Mechanical Wear, Decay, Contamination, Vibration), and Hazards (primarily Wind). Conduct assessment to determine whether newly developed sub-models are to be included in the WTRM model. | This initiative will help further develop PG&E's risk modeling capabilities. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | A.02 | PG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_A.02_2022 | 358 | Equipment ignition likelihood | No | [10 empty] | Develop Threat and Hazard (Risk drivers) sub-models that cover: Threats (e.g., Atmospheric corrosion, Underground corrosion, Fatigue, Mechanical Wear, Decay, Contamination, Vibration), and Hazards (primarily Wind). Conduct assessment to determine whether newly developed sub-models are to be included in the WTRM model. | The first version of all committed Threat\Hazard models besides one (Insulator-Contamination) that have the greatest impact to the safety of PG&E’s Transmission line assets have been deployed. The last remaining model, Insulator-Contamination, is targeted to be completed by April 30, 2022. | The first version of all committed Threat\Hazard models that have the greatest impact to the safety of our Transmission line assets have been deployed. The one pending model as of Q1 2022 (Insulator-contamination) was deployed on May 31st. The models are undergoing validation with a targeted date of completion Aug 31, 2022. | The WTRM models were approved for use by the WF Risk Governance Steering committee on Sep 14th. | The WTRM models were approved for use by the WRGSC on September 14, 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-06-01 | PSPS Consequence Model | Conduct an assessment of the PSPS Consequence model to inform if it is fit for use to inform PSPS mitigation plans to minimize customer impact. | This initiative will help further develop PG&E's risk modeling capabilities. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | A.03 | PG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_A.03_2022 | 361 | PSPS exposure potential | No | [10 empty] | Conduct an assessment of the PSPS Consequence model to inform if it is fit for use to inform PSPS mitigation plans to minimize customer impact. | Soliciting stakeholder feedback and usage through meetings and review of results as part of the Undergrounding mileage selection framework. Delay due to resource focus on supporting Undergrounding Tool and Integrated Risk Spend Efficiency for System Hardening team which stems from lack of resources dedicated to workstream; divergence of priorities due to 2 members of the team resigning and 1 on emergency family leave. | The assessment of the PSPS Consequence model was submitted to the WRGSC on May 11, 2022 and approved, meeting the annual target. | This target was completed in Q2 2022. | This target was completed in Q2 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Wildfire Consequence Model Enhancements - Ingress/Egress | Develop an approach on how to incorporate ingress/egress into the Wildfire Consequence Model. | This initiative will help further develop PG&E's risk modeling capabilities. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | A.04 | PG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_A.04_2022 | 364 | Wildfire vulnerability | No | [10 empty] | Develop an approach on how to incorporate ingress/egress into the Wildfire Consequence Model. | Egress model has been delivered by UCLA and the RAVE model from Technosylva. Next step is to identify and assign resources to apply and explore models to identify preferred application to include Egress in the risk models. | The code for the Egress model was delivered to us on June 15, 2022 by UCLA. It was determined that the UCLA portion of the project is not practical as part of this year's model development. Thus, we are continuing to focus our resources on the use and development of the RAVE data for the Egress model. We developed an initial formulation of potential approaches to accounting for egress as part of the Wildfire Consequence model. | Team has evaluated several new potential variables that could be used to enhance our Consequence model for the complications of egress, including population demographic factors such as age, poverty, and disability levels, and additional engineering factors such as burnable area, fuel layer content, and wind characteristics. Exploratory data analysis has been performed and new consequence model training and evaluation is in progress. | Analysis for a modeling approach for adding the effect of egress to the Wildfire Consequence Model was completed and presented to the WRGSC. The approach for integrating egress was approved. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Wildfire Consequence Model Enhancements - Resistance to Control | Evaluate an approach to incorporate "Resistance to Control" (i.e., TDI) into the Wildfire Consequence Model. Resistance to Control is the relative difficulty of constructing and holding a control line as affected by resistance to line construction and by fire behavior. | This initiative will help further develop PG&E's risk modeling capabilities. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | A.05 | PG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_A.05_2022 | 364 | Wildfire hazard | No | [10 empty] | Evaluate an approach to incorporate "Resistance to Control" (i.e., TDI) into the Wildfire Consequence Model. Resistance to Control is the relative difficulty of constructing and holding a control line as affected by resistance to line construction and by fire behavior. | Contractual arrangements for the resistance to control model outputs from the Technosylva RAVE model were completed. | The RADA/PSPS teams have initiated review of the RAVE data. All team members have access to this data through ArcGIS Pro. We developed an initial formulation of potential approaches to accounting for suppression as part of the Wildfire Consequence model. | Team has evaluated several new potential variables that could be used to enhance our Consequence model for the complications related to fire suppression, including population demographic factors such as age, poverty, and disability levels, and additional engineering factors such as burnable area, fuel layer content, and wind characteristics. Exploratory data analysis has been performed and new consequence model training and evaluation is in progress. | Analysis for a modeling approach for adding resistance to control (ingress and suppression) to the Wildfire Consequence Model was completed and presented to the WRGSC. The approach for integrating resistance to control was approved. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-09-01 | FPI and IPW Modeling - Revision Evaluation | Evaluate running the FPI and IPW Models with the ensemble mean output of the POMMS-EPS. | This initiative will help further develop PG&E's risk modeling capabilities and weather-related situational awareness. | Situational Awareness and Forecasting | 8.3 | Weather forecasting |  | 8.3.5 | B.01 | PG&E_Situational Awareness and Forecasting_Weather forecasting_B.01_2022 | 367 | PSPS likelihood | No | [10 empty] | Evaluate running the FPI and IPW Models with the ensemble mean output of the POMMS-EPS. | External vendor and internal teams have built out ensemble mean versus deterministic verification tools so we can track forecast performance each quarter. In addition, external vendor is working on adjusting the dead fuel and live fuel moisture models to accept either deterministic or ensemble mean forecast data as input. | The program team has met all interim milestones, as of June 30, 2022. We continue to track ensemble mean forecast skill versus deterministic each quarter to determine which forecast provides more accurate forecast data. By mid-July we project to have deterministic and ensemble mean forecast skill scores available for Q2 from the external vendor. Overall, the team is on track to complete this work in late Q3, by which point we will have completed thorough evaluations of forecast skill. This involved comparing forecast output against over a thousand weather station observations each hour across two quarters. In addition to evaluating forecast skill, we have explored if our FPI and IPW forecasts (inputs to PSPS), can be generated using both the ensemble mean and deterministic forecasts. In Q2, we built and deployed our PSPS models in a separate data pipeline driven by the ensemble mean forecast in our lower computing environments to prove feasibility. The deterministic and ensemble mean-driven forecasts are now being compared side-by-side. To accomplish this, we worked with an external vendor to enhance their code which can now generate forecasts of Dead Fuel Moisture and Live Fuel Moisture with deterministic and ensemble mean data and internally developed a parallel data flow pipeline in our AWS environment. The next steps are to evaluate Q2 forecast skill reports once available and to promote the ensemble-mean generated PSPS forecasts into our production environment. | In Q2 we built and deployed our PSPS models in a separate data pipeline driven by the ensemble mean forecast in our lower computing environments to prove feasibility. After testing, we have now promoted the pipeline through our QA and production environments and are now running our PSPS models in parallel allowing for direct comparison of outputs. We’ve also integrated the outputs into our ArcGIS pro environments and have built a front-end dashboard using Tableau to compare results. Forecast skill between model inputs has been evaluated and we’ve evaluated and built the data pipelines needed to run the PSPS models using different inputs operationally. In addition, the new FPI model was presented and approved by the Wildfire Risk Governance Committee (WRGC). | This target was completed in Q3 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Weather Stations -Installations and Optimizations | Install or Optimize 100 weather stations. A unit is deemed "installed" when it is in service and verified as operating when initially installed. A unit is deemed "optimized" when a weather station is moved from an existing location to a new location for the purposes of improving our understanding of the weather conditions in the area. | This initiative will further PG&E's situational awareness by providing increased weather station density. | Situational Awareness and Forecasting | 8.3 | Environmental monitoring system |  | 8.3.2 | B.02 | PG&E_Situational Awareness and Forecasting_Environmental monitoring system_B.02_2022 | 374 | Wildfire hazard | No | # of Weather Stations | 100 | 5 | 40 | 85 | 100 | 5 | 34 | 88 | 111 |  | In Q1, PG&E installed 5 weather stations. | The program fell behind the YTD Target of 40 with 34 weather stations installed/optimized by June 30, 2022. In Q2, a combined 29 newly installed or optimized weather stations were completed. We are forecasting to complete the annual goal of 100 new or optimized weather stations in 2022. | In Q3 PG&E installed a combined 54 newly installed and optimized weather stations. YTD the project has 82 new installs and 6 Optimized weather stations. The project is on track. | As of the end of Q4, we installed 105 new weather stations and optimized 6 weather stations, bringing the total number of new and optimized sites to 111, and exceeding the annual target of 100. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | High-Definition Cameras - Installations | Install 98 new cameras that are facing HFTD Tier 2 or Tier 3 viewsheds. In the case a site is destroyed and a camera can be replaced / relocated nearby with a different visual coverage than the original, this will count as a new installation. | This initiative will further PG&E's situational awareness by providing increased high-definition camera density. | Situational Awareness and Forecasting | 8.3 | Environmental monitoring system |  | 8.3.2 | B.03 | PG&E_Situational Awareness and Forecasting_Environmental monitoring system_B.03_2022 | 378 | Wildfire hazard | No | # of HD Cameras | 98 | 8 | 51 | 90 | 98 | 21 | 47 | 91 | 100 |  | In Q1, PG&E installed 21 cameras. | The cameras installation program fell behind the YTD Target of 51 with 47 cameras installed by June 30, 2022. 10 cameras were installed in June, with 26 installs total in Q2. A contract issue with a vendor, Stantec, caused a delay of over two months in the USFS work. This has since been cleared and Stantec is once again moving to push our sites with the USFS. Continued efforts to catch up from this contract delay stands with pending finalized land contracts and permit issuance anticipated for approval in the next three weeks. Work has also been slowed due to our viewshed commitment. There is a stated goal for 90% of HFTD Tier 2 and 3 coverage by the end of the year. This requires additional work to ensure camera installations add as much viewshed as possible in order to meet that goal. | Surpassed quarterly target of 39 with 44 cameras installed. We have now surpassed our YTD target of 90 with 91 cameras installed. On track to complete remaining 7 camera installation targets by Q4. | PG&E installed 9 cameras in Q4 and exceeded our annual target of 98, with 100 cameras installed in 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Distribution Fault Anticipation (DFA) - Installations | Install 40 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor per circuit at initiating substation. | This initiative will help PG&E identify and address latent or incipient issues in their early stages and may remove conditions that cause wildfires. | Situational Awareness and Forecasting | 8.3 | Grid monitoring system |  | 8.3.3 | B.04 | PG&E_Situational Awareness and Forecasting_Grid monitoring system_B.04_2022 | 392 | Equipment ignition likelihood | No | # of DFA Sensors | 40 | 5 | 10 | 25 | 40 | 12 | 21 | 42 | 48 |  | In Q1, PG&E installed 12 sensors. | The DFA installations program surpassed the YTD Target of 10 with a total of 21 DFA Units online by June 30, 2022. A total of 9 DFA Units came on line in Q2. | The DFA installation program surpassed the 2023 WMP commit of 40 with a total installation count of 42. A total of 21 DFA units came online in Q3 2022 | PG&E completed an additional 6 circuits in Q4, bringing our annual total to 48 circuits, and exceeding our annual target of 40 circuits. In Q1 2022, we reported a DFA install on circuit PLACERVILLE 1110. This should be corrected to SHINGLE SPRINGS 2105. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Early Fault Detection (EFD) - Installations | Install Early Fault Detection (EFD) sensors on 2 circuits feeding into HFTD areas or HFRA. | This initiative will help PG&E identify and address latent or incipient issues in their early stages and may remove conditions that cause wildfires. | Situational Awareness and Forecasting | 8.3 | Grid monitoring system |  | 8.3.3 | B.05 | PG&E_Situational Awareness and Forecasting_Grid monitoring system_B.05_2022 | 395 | Equipment ignition likelihood | No | # of circuits | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 2 |  | No sensors were installed in Q1, but none were planned to be installed in Q1. Therefore, this initiative remains on track for completion by the end of the year. | There were no circuit completions in Q2, but none were planned for Q2. This initiative remains on track for completion by the end of the year. | Installation in progress on two circuits, with estimation and permitting in progress for two additional circuits. Expect one circuit completion in October, one in November and two in December. | We completed installs on 2 circuits in Q4, meeting our annual target of 2 circuits. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Line Sensor - Installations | Install Line Sensor devices on 40 circuits feeding into HFTD areas or HFRA to cover mainline and major tap lines in areas meeting minimum load requirements and within cellular coverage areas to provide visibility. | This initiative will help PG&E continuously measure current in real time and report events as they occur. | Situational Awareness and Forecasting | 8.3 | Grid monitoring systems |  | 8.3.3 | B.06 | PG&E_Situational Awareness and Forecasting_Grid monitoring systems_B.06_2022 | 401 | Equipment ignition likelihood | No | # of circuits | 40 | 0 | 10 | 40 | 40 | 0 | 10 | 62 | 63 |  | No sensors were installed in Q1, but none were planned to be installed in Q1. Therefore, this initiative remains on track for completion by the end of the year. | The line sensor device installation program met the YTD Target of 10 with 10 installations in HFTD areas completed by June 30, 2022. | The Line Sensor installation program surpassed the 2023 WMP commit of 40 circuits, completing installs on 62 circuits by end of Q3 2022. | Line sensor installs were completed on 1 additional circuit in Q4, bringing our annual total to 63 circuits completed, and exceeding our annual target of 40 circuits. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Non-Exempt Expulsion Fuses - Removal | Remove 3,000 non-exempt fuses/ cutouts identified on distribution poles in HFTD areas or HFRA. | This initiative will remove non-exempt equipment that may generate electrical arcs, sparks, or hot material during its normal operation. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | C.01 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_C.01_2022 | 446 | Equipment ignition likelihood | No | # of fuses | 3000 | 300 | 1360 | 2430 | 3000 | 949 | 2342 | 2894 | 3085 |  | In Q1, PG&E installed 949 non-exempt fuses. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | The program surpassed the YTD Target of 1,360 with the removal of 2,342 non-exempt fuses / cutouts as of June 30, 2022. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | The program is On Track with 2,894 units completed against the YTD target of 2,430. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | PG&E's WMP target was to remove 3,000 non-exempt fuses in 2022. We have exceeded this target by removing 3,085 units by 12/19/22. 191 units were completed in Q4 2022. Data for earlier quarters may have changed as a result of data verification. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-09-01 | Distribution Protective Devices | Install and SCADA commission 100 new PSPS SCADA enabled Distribution Sectionalizing devices. | This initiative installs sectionalizing devices which can support PG&E's ability the reduce the impact and scope of PSPS events by segmenting circuits. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | C.02 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_C.02_2022 | 450 | PSPS exposure potential | No | # of distribution sectionalizing devices | 100 | 0 | 70 | 100 | 100 | 6 | 22 | 117 | 124 |  | In Q1, PG&E installed 6 PSPS Distribution Sectionalizing devices, which includes construction and SCADA commissioning. Note that supply chain issues, as well as permitting, environmental and land dependencies may introduce potential risk to the plan in the future months. | The program fell behind the Original YTD Target of 70 with 22 units completed by June 30, 2022. The delay is due to material availability limitations and resources focused on the higher priority EPSS program implementation, and a recovery plan and catch-back targets have been implemented in Q2. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | The program met the WMP Commitment of 100 commissioned devices on August 19, 2022, with 117 devices commissioned September YTD. New PSPS SCADA enabled Distribution Sectionalizing devices include: 1) New automated SCADA devices intended to reduce the number of customers impacted during a PSPS/EPSS event. 2) Automated SCADA devices that replace existing manual devices and are intended to reduce PSPS/EPSS duration. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | PG&E’s WMP target was to install and SCADA commission 100 new PSPS Distribution Sectionalizing devices. PG&E installed and SCADA commissioned 124 new PSPS Distribution Sectionalizing devices in 2022. Data for earlier quarters may have changed as a result data verification. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-09-01 | Transmission Line Sectionalizing - Install and SCADA commission | Install and SCADA commission 15 transmission line switches on lines that traverse the HFTD areas. The switches themselves may not be located in the HFTD areas but can be used to support customer impact reduction. | This initiative installs sectionalizing devices which can support PG&E's ability the reduce the impact and scope of PSPS events by segmenting circuits. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | C.03 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_C.03_2022 | 454 | PSPS exposure potential | No | # of switches | 15 | 1 | 8 | 15 | 15 | 1 | 8 | 16 | 18 |  | In Q1, PG&E completed 1 transmission line switch on lines that traverse the HFTD areas was completed. | The program met the YTD Target of 8 with 8 SCADA commissioned transmission line switches by June 30, 2022. | One (1) PSPS T-Line SCADA switch was installed in July bringing the YTD total through July to 9. Another six (6) were installed in August bringing the YTD total through August to 15, meeting the 2022 WMP goal of installing 15 PSPS T-Line SCADA switches by 9/1. An additional one (1) switch was installed in September. A total of eight (8) switches were installed in Q3. | The program met the Target of 15 sectionalizing switches by the end of August. 3 additional PSPS switches were installed over the remainder of Q3 and Q4 bringing the total to 18 for 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Distribution Line Motorized Switch Operator (MSO) - Replacements | Replace at least 50 of the 104 remaining Motorized Switch Operators that are located within or are energizing line sections that feed into HFTD areas or HFRA. | This initiative is to replace Motorized Switch Operators, which have a potential to arc flash during operations, with other devices. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | C.04 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_C.04_2022 | 457 | Equipment ignition likelihood | No | # of MSOs | 50 | 0 | 23 | 39 | 50 | 1 | 14 | 21 | 57 |  | In Q1, PG&E completed installation of 1 MSO device, which includes construction and SCADA commissioning. Note that supply chain issues, as well as permitting, environmental and land dependencies may introduce potential risk to the plan in the future months. | The program fell behind the YTD target of 23 with 14 MSO replacements units completed by June 30, 2022. The delay was driven by material availability limitations and resources focused on the higher priority EPSS program implementation through the first half of 2022. | The program fell behind the Original YTD Target of 39 with 21 units completed September YTD. In Q3, 7 units were completed. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | PG&E's WMP target was to replace 50 Motorized Switch Operators in 2022. We have exceeded this target by replacing 57 units by December 19, 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | SCADA Recloser Equipment - Installations | Install 17 substation SCADA enabled reclosers on circuits serving line sections that feed into HFTD areas or HFRA, barring any exceptions due to connectivity issues necessary to SCADA-enable the recloser. Footnote: There may be connectivity issues for some SCADA reclosers that will require manual setting updates, but there is still benefit in installing the recloser to get the sectionalization on the circuit. | This initiative will install SCADA equipment which can be used to detect and address high impedence faults conditions. | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | C.05 | PG&E_Grid Design, Operations, and Maintenance_Installation of system automation equipment _C.05_2022 | 462 | Equipment ignition likelihood | No | # of reclosers | 17 | 0 | 6 | 13 | 17 | 0 | 3 | 8 | 17 |  | The program had no Q1 target, and no units were Commissioned. Work is expected to ramp up in Q2 as the program is targeting to complete 6 SCADA reclosers. | The program is behind the YTD target of 6 with 3 substation SCADA enabled reclosers installed by June 30, 2022. The delay was driven by material availability limitations and resources focused on the higher priority EPSS program implementation through the first half of 2022. | The program fell behind the Original YTD Target of 13 with 8 units completed September YTD. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | PG&E's WMP target was to install 17 units in 2022. We have completed this target by installing 17 units by December 21, 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Fuse Savers (Single Phase Reclosers) - Installations | Install 80 single phase recloser sets in HFTD areas or HFRA. | This initiative will install single phase reclosers with the capability to trip all phases reducing the risk associated with a wire down event. | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | C.06 | PG&E_Grid Design, Operations, and Maintenance_Installation of system automation equipment _C.06_2022 | 465 | Equipment ignition likelihood | No | # of fuse saver sets | 80 | 0 | 27 | 63 | 80 | 2 | 16 | 28 | 81 |  | In Q1, PG&E installed 2 single phase reclosers. | The program is behind the YTD target of 27 with 16 Fuse Savers installed by June 30, 2022. The delay is driven by skilled resource availability as the EPSS and PSPS devices have been prioritized over these fuse savers. | The program fell behind the Original Target of 63 with 28 units completed September YTD. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. | PG&E's WMP target was to install 80 units in 2022. We have completed this target by installing 81 units by December 21, 2022. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Temporary Distribution Microgrids | Make operationally ready at least four (4) additional Distribution Microgrid Pre-installed Interconnection Hubs (PIHs). This target will include 1 PIH that completed construction in December 2021 and will be made ready to operate in 2022. | This initiative will install Distribution Microgrid PIHs which can be used to keep commercial corridors and critical facilities online when distribution lines are de-energized as a result of a PSPS event. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | C.07 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_C.07_2022 | 470 | PSPS exposure potential | No | # of PIHs | 4 | 0 | 0 | 2 | 4 | 0 | 0 | 1 | 4 |  | The project management team made progress obtaining/extending permitting and securing major material and equipment needed for electrical construction, including Viper line reclosers that needed additional lead time for safety enhancement. Clearances have been submitted and scheduled for two sites to begin construction in Q2 (Lucerne and Arnold). To ensure temporary generation is available to energize these sites, PG&E issued a Temporary Generation Request for Proposals and began evaluation on competitive bids. Cross-functional alignment planning across engineering teams took place to ensure energization plans for constructed sites can be completed in a timely fashion once generators are available. | On April 29, 2022 the Lucerne Distribution Microgrid completed construction, including installation of pre-installed interconnection hub, ground grid, an underground connection to the mainline, and several isolation devices. Quality Assurance (QA) is in progress and EDGIS mapping has been requested. Work continued on three other Distribution Microgrids (Arnold, Clearlake North, and Groveland), scheduled to complete construction in Q3. Additionally, in June we executed contracts for temporary generation rentals to serve these microgrids. Generators will be inspected and released in Q3, after which energization plans will be completed to reach operational readiness. | Colfax Distribution Microgrid was made operationally ready in August, completing one out of the two units that were committed for Q3 and one of the four WMP 2022 commitment units. Construction for manual operation was completed on Arnold, Groveland, and Clearlake N. Go-backs will be completed on all sites in Q4 to install SCADA-enabling equipment. Energization plans will be completed for these sites as well as Lucerne in Q4, thereby meeting the full 2022 WMP commitment for this initiative. | Three additional temporary distribution microgrids with pre-installed interconnection hubs reached operational readiness in Q4 2022. Together with the unit completed in Q3, this brings the total units for 2022 to four, completing the 2022 WMP target for this initiative. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-06-01 | Rincon Transformer Fuse - Replacement | Replace the fuse with a circuit switcher on the Rincon Transformer Bank 1. | This initiative is replacing the fuse at Rincon Transformer Bank 1, which was not providing optimal low side protection and could cause additional impacts during PSPS events. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | C.08 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_C.08_2022 | 486 | PSPS exposure potential | No | # of fuses | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 |  | In-Service date on track for Q2. | The Rincon Transformer Fuse Replacement has been completed and went in-service in May 2022, meeting our Q2 initiative. This initiative has been completed. | This Initiative was completed in Q2. | This Initiative was completed in Q2. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Emergency Back-up Generation – Equip PG&E Service Centers & Materials Distribution Centers | Equip 15 PG&E Service Centers or Materials Distribution Centers sites with emergency back-up generation to allow the sites to operate with the same amount of functionality as they would if they were being fed from their normal utility power source. | This initiative will allow PG&E facilities to operate during PSPS events with the same functionality as they normally would operate so that restoration efforts can be carried out unimpeded. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | C.09 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_C.09_2022 | 489 | PSPS exposure potential | No | # of sites | 15 | 4 | 9 | 13 | 15 | 4 | 9 | 12 | 15 |  | In Q1, PG&E completed the cutovers on four 4 sites. Fortuna SC, Quincy SC, and Clearlake SC were completed in January. Woodland SC was successfully completed in February. | The program met the YTD Target of 9 with 9 sites equipped with emergency back-up generation by June 30, 2022. In Q2, we completed cutovers on five sites. Hayward SC and Willows SC were completed in April and Buellton SC, Oakland SC, and Santa Rosa SC were completed in June. | The program has fallen slightly behind the YTD Target of 13 sites by end of Q3 2022. Only 12 sites were equipped with emergency back-up generation by September 30, 2022. In Q3, we completed cutovers on three sites. Marysville SC was completed in August, followed by Hollister SC and Watsonville SC completions in September. | The program has been completed. In Q4, we completed cutovers on the remaining three sites. San Jose Edenvale SC was completed in October, Colma SC was completed in November, and Fort Bragg SC was completed in December. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | 10K Undergrounding | Complete at least 175 circuit miles of undergrounding work. The 175 circuit mile target includes undergrounding taking place as part of both System Hardening (Section 7.3.3.17.1), Butte County Rebuild efforts (Section 7.3.3.17.6) including a small volume of previously hardened overhead lines that are being placed underground, and any other undergrounding work performed in HFTD or fire rebuild areas. | This initiative will underground electrical facilities to reduce the risk of potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | C.10 | PG&E_Grid Design, Operations, and Maintenance_Undergrounding of electric lines and/or equipment _C.10_2022 | 523 | Equipment ignition likelihood | No | # of circuit miles | 175 | 23 | 70 | 131 | 175 | 35.2 | 72.2 | 99.5 | 179.7 |  | In Q1, PG&E completed 35.2 undergrounding miles (31.1 from the System Hardening Program and 4.1 from the Butte Rebuild effort). | The program has exceeded the YTD target of 70 miles with 72.2 undergrounding miles completed June 30, 2022. 51.1 miles were from System Hardening Undergrounding and 21.1 miles were from Butte Rebuild undergrounding. | The program fell behind the Original YTD target of 131 miles with 99.5 miles completed: 70.6 from System Hardening Undergrounding and 28.9 from Butte Rebuild undergrounding. | PG&E's WMP target was to complete 175 circuit miles of undergrounding in 2022. We have exceeded this target by undergrounding 179.7 circuit miles. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | System Hardening - Distribution | Complete at least 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding and removal of overhead lines in HFTD or buffer zone areas with the exception of any mileage being undergrounded and tracked separately as part of our Butte County Rebuild efforts (Section 7.3.3.17.6). | This initiative will harden distribution circuit miles through overhead system hardening, undergrounding, and the removal of overhead lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | C.11 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_C.11_2022 | 537 | Equipment ignition likelihood | No | # of circuit miles | 470 | 85 | 230 | 375 | 470 | 95.1 | 250.6 | 369.6 | 483 |  | In Q1, PG&E completed 95.1 miles of system hardening. | The program has exceeded the YTD target of 230 miles with 250.6 system hardening miles completed June 30, 2022. The program is on track to achieve the 470 mile EOY target with 147.3 miles currently in construction and another 83.4 miles ready for construction. | The program fell behind the Original YTD target of 375 miles with 369.6 miles completed September YTD. The program is on track to achieve the 470-mile EOY target with 130.9 miles currently in construction and another 4.3 miles ready for construction. | PG&E's WMP target was to harden 470 circuit miles in 2022. We have completed this commitment by completing 483.0 system hardening miles. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | System Hardening - Transmission | Remove or replace 32 circuit miles of transmission conductor on lines traversing the HFTD areas or HFRA. | This initiative will harden transmission circuit miles through removing or replacing conductor to reduce the risk of potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | C.12 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_C.12_2022 | 548 | Equipment ignition likelihood | No | # of circuit miles | 32.6 | 4.2 | 4.6 | 4.6 | 32.6 | 4.2 | 7.7 | 13.7 | 37.8 |  | In Q1, PG&E completed 4.2 miles of removing or replacing transmission conductor. | The program surpassed the YTD Target of 5 miles with 7.7 system hardening transmission miles completed by June 30, 2022. Drum Rio-Oso phase 2 project completed an additional 3.5 miles in Q2 due to clearance availability. On track to meet EOY target. | YTD actuals have increased to 13.7 for system hardening transmission miles by September 30, 2022. 6 miles have been completed from Caribou-Palermo removal project in September. On track to meet EOY target. | PG&E's WMP target was to remove or replace 32 circuit miles of transmission conductor on lines traversing HFTD or HFRA areas in 2022. We exceeded this target by removing or replacing 37.8 circuit miles by December 31, 2022, including completing 24.1 circuit miles in Q4. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Surge Arrestor - Removals | Remove all of the remaining non-exempt surge arrestors in HFTD areas (based on the known population of 4,590 surge arrestors as of January 1, 2022) through replacement with exempt equipment. | This initiative will remove non-exempt equipment with exempt equipment that has a lower propensity to cause a fire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | C.13 | PG&E_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_C.13_2022 | 552 | Equipment ignition likelihood | No | # of surge arrestors | 4590 | 220 | 1590 | 3270 | 4590 | 1193 | 2596 | 3545 | 4621 |  | In Q1, PG&E completed the removal of 1,193 surge arrestors. | The program has exceeded the YTD target of 1,590 units with 2,596 completed. The program is on track to meet the EOY target of 4,590 units. Note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled with our vendors. | The program is On Track with 3,545 units completed against the YTD target of 3,270. Note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled between vendors and PG&E. | PG&E had a target to replace 4,590 surge arrestors with known grounding issues in the HFTD based on the known population as of January 1, 2022. PG&E exceeded that target by replacing 4,621 units in 2022. Not all surge arresters with known grounding issues in the HFTD were replaced in 2022 because the target was created using an estimate based on the historical number of cancellations each year. In 2022, we experienced fewer cancellations than estimated. We also reviewed our data to ensure we were capturing all remaining surge arresters with known grounding issues in the HFTD. In total, 139 additional sites could not be completed in 2022 due to access issues, customer refusals, and poles that need replacement before surge arrester work can take place. These remaining surge arresters in the HFTD will be completed in 2023, barring external factors. In addition, in 2023 we are expanding the scope to include surge arresters with known grounding issues in the HFRA. Note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled between vendors and PG&E. As a result, quarterly completed units have been adjusted to reflect the most up-to-date data. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Remote Grid - Operate New SPS Units | Operate 2 new Remote Grid Standalone Power System (SPS) units | This initiative will allow for the operation of remote grids which can replace traditional wires to remote locations and reduce the risk of potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Microgrids |  | 8.1.2.7 | C.14 | PG&E_Grid Design, Operations, and Maintenance_Microgrids_C.14_2022 | 558 | Equipment ignition likelihood | No | # of Remote Grids | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 |  | The Remote Grid Program executed contracts for four Standalone Power Systems (SPS) units in the third week of February. Two of these four units are scheduled to be online by December 2022. For these projects the vendor has ordered the longest-lead major equipment (generator sets) and detailed engineering design is nearing 90% complete. PG&E has initiated line removal scoping, permitting outreach, and the Environmental Review process. Unexpected supply chain delays in major equipment delivery pose schedule risks so the team is working to expedite delivery. At conclusion of 30% design, our contractor notified us that the remainder of Engineer/Procure/Construct timelines will be longer than expected due to COVID related delays. Global supply chain issues delaying generator procurement, extended design and contracting durations, and incremental civil scopes identified on 2 projects were the primary causes of the delay. | The four SPS units under contract are progressing on track with two scheduled to be online by December 2022. The design/build contractor has completed final Issue-For Construction civil drawings. Further supply chain issues, as well as vendor product line updates, have led to a change in certain inverter models specified, so complete Design & Engineering and trailing items of Major Equipment Order are still in flight, yielding overall project schedule On Track for online target date. We completed preliminary designs for service facilities with complete Job Estimates expected in July. Environment Release To Construct has been completed for all 4 units, as well as local county permits received for 2 units. Aggressive management of supply chain delays has mitigated schedule impacts through escalations to key equipment vendors, with Major Equipment Delivery back on track for September for the 2 committed units. Mobilization and start of construction is planned for July for 2 units and August for the other 2 units. | The four SPS units are now in the Construction stage with two On Track to be online by December 2022 as planned. Major Equipment Orders were completed, and supply chain issues were actively managed with key long lead equipment (generator sets) shipped in late September for Oct delivery, on schedule for the two Commitment units. Service Facilities job estimates are complete for installation sequenced in parallel with the Standalone Power System scope. On site, PV panels have been installed for two units, and civil work including clearing, grading, foundations, access road improvements, as well as conduits and grounding systems have been installed across all four sites. Engineering focus is now on last technical submittals to prepare for commissioning and performance testing. Remaining major equipment including generators, energy storage systems, switchgear, and balance of plant are upcoming and on track. Required county permits were received. | Two SPS units, Corning Remote 0001 and 0002, were brought online in December after successful commissioning and cutover. Two other units completed commissioning but not cutover: these 2 units will be carried into 2023 to go online when weather permits access to these relatively remote sites. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Butte County Rebuild - Undergrounding | Complete 55 circuit miles of undergrounding work as part of the Butte County Rebuild program. | This initiative will underground electrical facilities to reduce the risk of potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | C.15 | PG&E_Grid Design, Operations, and Maintenance_Undergrounding of electric lines and/or equipment _C.15_2022 | 566 | Equipment ignition likelihood | No | # of primary circuit miles | 55 | 1 | 12 | 25 | 55 | 3.88 | 19.91 | 27.26 | 57.84 |  | In Q1, PG&E completed 3.9 miles of undergrounding work as a part of the Butte County Rebuild program. | The program surpassed the YTD Target of 12 miles with 19.9 undergrounding miles completed by June 30, 2022. The program is on track to meet or exceed the 55 mile commitment. | The program surpassed the YTD Target of 25 miles with 27.3 undergrounding miles completed by September 30, 2022. The program is on track to meet or exceed the 55 mile commitment. | PG&E exceeded WMP target of 55 circuit miles with 57.8 circuit miles undergrounding miles completed in 2022. | Completed
PG&E | 2023-02-01 | Program |  |  | Detailed Inspections - Distribution | Complete detailed inspections on a minimum of 396,000 distribution poles, which were identified in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any poles discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any poles discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | This initiative includes detailed inspections of distribution poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.01 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.01_2022 | 569 | Equipment ignition likelihood | No | # of poles | 396000 | 6235 | 311359 | 396000 | 396000 | 6212 | 250633 | 398119 | 398184 |  | In Q1, PG&E completed detailed ground inspections on 6,212 distribution poles. | The program fell behind the YTD Target with 250,633 poles inspected by June 30, 2022. | The program met and surpassed the WMP Target of 396,000 distribution ground inspections with 398,119 completed by the end of Q3. The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis. | PG&E exceeded the WMP target of 396,000 detailed distribution ground inspections by completing 398,184 detailed distribution ground inspections. Data for earlier quarters may have changed as a result data verification. | Completed
PG&E | 2023-02-01 | Program |  |  | Detailed Inspection Transmission – Ground | Complete detailed ground inspections on a minimum of 39,000 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | This initiative includes detailed inspections (ground) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.02 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.02_2022 | 574 | Equipment ignition likelihood | No | # of structures | 39000 | 2783 | 33758 | 39191 | 39191 | 2714 | 38610 | 39004 | 39005 |  | In Q1, PG&E completed detailed ground inspections on 2,714 transmission structures. | The program surpassed the YTD Target of 33,758 transmission ground inspections with 38,610 transmission ground inspections completed by June 30, 2022. | The program surpassed the WMP Target of 39,000 transmission ground inspections with 39,004 completed by the end of Q3. PG&E has met its WMP target for 2022. The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis. | PG&E exceeded the WMP target of 39,000 detailed transmission ground inspections by completing 39,005 detailed transmission ground inspections. Data for earlier quarters may have changed as a result data verification. | Completed
PG&E | 2023-02-01 | Program |  |  | Detailed Inspection Transmission – Climbing | Complete detailed climbing inspections on a minimum of 1,800 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | This initiative includes detailed inspections (climbing) of transmission poles which can reduce the potential for equipment failure which could case a potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.03 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.03_2022 | 574 | Equipment ignition likelihood | No | # of structures | 1800 | 661 | 1832 | 1832 | 1832 | 1177 | 1833 | 1835 | 1835 |  | In Q1, PG&E completed 1,177 climbing inspections. | The program has completed the annual Target with 1,833 Transmission climbing inspections completed by June 30, 2022. | The program surpassed the WMP Target of 1,800 transmission climb inspections with 1,835 completed by the end of Q3. PG&E has met its WMP target for 2022. The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis. | PG&E exceeded the WMP target of 1,800 transmission climb inspections by completing 1,835 detailed climbing inspections. Data for earlier quarters may have changed as a result data verification. | Completed
PG&E | 2023-02-01 | Program |  |  | Detailed Inspection Transmission – Aerial | Complete detailed aerial inspections on a minimum of 39,000 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | This initiative includes detailed inspections (aerial) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.04 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.04_2022 | 574 | Equipment ignition likelihood | No | # of structures | 39000 | 8202 | 35591 | 39191 | 39191 | 8117 | 36976 | 39004 | 39004 |  | In Q1, PG&E completed aerial inspections on 8,117 transmission structures. | The program surpassed the YTD Target of 35,591 transmission aerial inspections with 36,976 transmission aerial inspections completed by June 30, 2022. Transmission Aerial inspections are on track and we are committed to meet our target for 2022. | The program surpassed the WMP Target of 39,000 transmission aerial inspections with 39,004 completed by the end of Q3. PG&E has met its WMP target for 2022. The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis. | PG&E exceeded the WMP target of 39,000 detailed transmission aerial inspections by completing 39,004 detailed aerial inspections Data for earlier quarters may have changed as a result data verification. | Completed
PG&E | 2023-02-01 | Program |  |  | Infrared Inspections - Distribution | Complete infrared inspections on a minimum of 9,000 distribution circuit miles in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets identified after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets identified after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | This initiative includes infrared inspections which can detect potential distribution equipment failure that cannot be detected visually and thus reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.05 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.05_2022 | 582 | Equipment ignition likelihood | No | # of circuit miles | 9000 | 0 | 0 | 5500 | 9000 | 0 | 0 | 6360 | 9560 |  | In Q1, 0 miles were inspected. Infrared Inspections - Distributions plans to start inspections in Q3 and will complete by end of year 2022. | The program will begin the Infrared Inspections for Distribution in Q3 and will complete the inspections by end of year 2022. | For Q3 2022, 6,360 miles were completed scanned by Infrared in HFTD against the Q3 target of 5,500. The program is on track to complete by the end of the year as scheduled. | PG&E exceeded the WMP target of 9,000 circuit miles of infrared inspections by completing 9,560 circuit miles of infrared inspections. | Completed
PG&E | 2023-02-01 | Program |  |  | Supplemental Inspections - Substation Distribution | Complete supplemental inspections on 86 distribution substations in HFTD areas or HFRA, barring External Factors. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.06 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.06_2022 | 624 | Equipment ignition likelihood | No | # of Distribution Substations | 86 | 0 | 65 | 86 | 86 | 0 | 86 | 86 | 86 |  | In Q1, PG&E completed 10 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. PG&E is committed to meet its target for 2022. | In Q2, we completed all 86 inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. The last completed date of inspection for this work is June 20, 2022. We have met our target for 2022. | The program completed the WMP Target of 86 supplemental inspections on Substation Distribution with 86 completed on June 20, 2022. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. PG&E has met its target for 2022. No additional units completed in the 3rd Quarter. | PG&E completed the WMP target of 86 supplemental inspections on distribution substations with 86 completed on June 20, 2022. No additional units completed in the 3rd and 4th Quarters. | Completed
PG&E | 2023-02-01 | Program |  |  | Supplemental Inspections - Substation Transmission | Complete supplemental inspections on 43 transmission substations within HFTD areas or HFRA, barring External Factors. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.07 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.07_2022 | 624 | Equipment ignition likelihood | No | # of Transmission Substations | 43 | 0 | 33 | 43 | 43 | 0 | 43 | 43 | 43 |  | In Q1, PG&E had completed 3 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. | In Q2, we completed all 43 inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. The last completed date of inspection for this work is June 21, 2022. We have met our target for 2022. | The program completed the WMP Target of 43 supplemental inspections on Substation Transmission with 43 completed on June 21, 2022. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. PG&E has met its target for 2022. No additional units completed in the 3rd Quarter. | PG&E completed the WMP target of 43 supplemental inspections on transmission substations with 43 completed on June 21, 2022. No additional units completed in the 3rd and 4th Quarters. | Completed
PG&E | 2023-02-01 | Program |  |  | Supplemental Inspections - Hydroelectric Substations and Powerhouses | Complete supplemental inspections on 52 Hydroelectric Generation Substations and Powerhouses within HFTD areas or HFRA, barring External Factors. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations, and Maintenance | 8.1 | Asset inspections |  | 8.1.3.1 | D.08 | PG&E_Grid Design, Operations, and Maintenance_Asset inspections_D.08_2022 | 628 | Equipment ignition likelihood | No | # of Hydroelectric Substations and Powerhouses | 52 | 0 | 42 | 52 | 52 | 0 | 52 | 52 | 52 |  | In Q1, PG&E had completed 3 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. | In Q2, we completed all 52 inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. The last completed date of inspection for this work is June 6, 2022. We have met our target for 2022. | The program completed the WMP Target of 52 supplemental inspections on Hydroelectric Substations and Powerhouses with 52 completed on June 6, 2022. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. PG&E has met its target for 2022. No additional units were completed in the 3rd Quarter. | PG&E completed the WMP target of 52 supplemental inspections on hydroelectric substations and powerhouses with 52 completed on June 6, 2022. No additional units completed in the 3rd and 4th Quarters. | Completed
PG&E | 2023-02-01 | Program |  |  | Asset Inspections - Quality Assurance | Perform Transmission and Distribution system inspection quality audits prioritizing HFTD/HFRA areas. Statistically valid methodology parameters, such as a confidence level of 95%, will be utilized. | This initiative audits the quality of transmission and distribution system inspections, which can help identify gaps and implement improvements for inspections. | Grid Design, Operations, and Maintenance | 8.1 | Quality assurance / quality control |  | 8.1.6 | D.09 | PG&E_Grid Design, Operations, and Maintenance_Quality assurance / quality control_D.09_2022 | 619 | Equipment ignition likelihood | No | [10 empty] | Perform Transmission and Distribution system inspection quality audits prioritizing HFTD/HFRA areas. Statistically valid methodology parameters, such as a confidence level of 95%, will be utilized. | The Transmission System Inspections audit began in March and continues on track. The Distribution System Inspections audit was not scheduled to begin until April 4th and therefore no progress update for Q1 is available. | The Transmission System Inspections Audit continues to be on track through Q2. Approximately 92% of the forecasted locations to be audited have been completed through Q2 (1,417 locations audited through Q2). Though slightly behind schedule, Transmission System Inspections audit has seen an upward trend in the number of locations audited monthly with approximately 106% of the total forecasted locations completed in June alone (409 locations completed versus 385 estimated). The team will continue this trend to catch up to its original total forecasted audit locations for the audit. If the team has not completely caught up to the original planned number of total locations audited, the QV Transmission team plans to extend the audit to ensure the original plan is achieved. The Distribution System Inspections Audit is off track through Q2 for its YTD completed audit locations versus the original plan. Currently the audit has completed 59% of the original planned number of locations to audit (954 completed versus 1,620 planned through Q2). The main driver for this low completion rate is from resource constraints due to vacation and sick leave time taken in Q2. An additional driver for the low completion rate is due to the amount of time required to travel to many of the auditing locations. | The Quality Management Transmission System Inspections Audits continue to be on track through Q3. Approximately 99% of the forecasted locations to be audited have been completed through Q3 (2,659 out of 2,695 locations audited through Q3). The Quality Management Transmission SI Audit Auditees are also on track to meet its target. The Quality Management Distribution System Inspections Audits have reached and exceeded its target for completed audit locations versus the original plan (2,838 completed versus 2,835 planned through Q3). The Quality Management Distribution SI Audit Auditees will not meet its target. | The Quality Management Transmission System Inspection Audit, which followed a statistically valid sampling methodology using a 95% confidence level and was specifically concentrated in High Fire Threat District locations, is complete with a final total number of locations audited of 2,696 (versus a planned 2,695). The audit has achieved approximately 100% of its 2022 target. The Quality Management Distribution System Inspections Audit, which followed a statistically valid sampling methodology using a 95% confidence level and was specifically concentrated in High Fire Threat District locations, is complete with a final total number of locations audited of 3,041 (versus a planned 2,835). The audit has achieved approximately 107% of its 2022 target | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2002-12-31 | HFTD/HFRA Open Tag Reduction - Distribution | Close a minimum of 55,000 HFTD or HFRA distribution tags in PG&E's workplan as of June 30, 2022, barring External Factors. | This initiative is focused on closing out open E maintenance tags for distribution facilities in HFTD and HFRA areas. | Grid Design, Operations, and Maintenance | 8.1 | Open work orders |  | 8.1.7 | D.10 | PG&E_Grid Design, Operations, and Maintenance_Open work orders_D.10_2022 |  | Equipment ignition likelihood | No | # of closed Distribution tags | 55000 | N/A | N/A | 41250 | 55000 | N/A | N/A | 36658 | 45951 |  | This was not an initiative in Q1. | This was not an initiative in Q2. | In Q3, D.10 was created as a target as a result of the 2022 Revision Notice. The target for this work is to complete 55,000 HFRA/HFTD distribution tags by the end of the year and to complete 12,700 ignition risk HFRA/HFTD distribution tags in Q3. Please note that additional tags have been brought into the latest workplan as they are deemed essential due to a variety of reasons. In Q3, we completed 11,219 tags, resulting in an annual total of 36,658 distribution tags against the YTD Target of 41,250. While we were unable to achieve our Q3 goal of 12,700 tags, we will institute a catch back plan to meet our annual goal of 55,000 tags. Please note that the recording of completed tags may experience delays due to the work verification process and clerical updates, as well as target clarification, and we have updated our Q3 numbers from the numbers in the Q3 Quarterly Notification. | The WMP target was to close a minimum of 55,000 HFRA/HFTD distribution tags by the end of the year, barring external factors. After reviewing the distribution tags that have been completed this year, as well as the language of our 2022 WMP Revision Notice response, we determined that only E tags (or E tags that changed into another type of tag) should be counted for purposes of Target D.10 because they were part of the “workplan” discussed in the WMP submission. PG&E understands that the target was specific to completing category E tags, given that these tags constituted the largest percentage of risk in our distribution tag backlog. While we did not meet the target of a minimum of 55,000 HFRA/HFTD E tags, we exceeded 55,000 total tags. We had higher priority work come in after our Revision Notice submission pertaining to A and B tags. Addressing these A and B tags was appropriate given they are higher priority and pose a greater risk to our customers. In Q4, PG&E completed 9,293 E tags, with a total of 45,951 E tags completed in 2022. | Delayed | For 2022, we closed a total of 45,951 E tags in HFTD and HFRA areas, which was 16.5% lower than our target of 55,000 E maintenance tags. We were not able to meet this our target for E tags because more category A and B tags were created during 2022 than PG&E anticipated. A and B tags are prioritized over E tags because of shorter regulatory compliance requirements and A and B tags are generally greater higher risk than E tags. Thus, while we did not meet this target, we continued to prioritize our commitment to working the riskiest tags first and preventing A and B tags from being added to the backlog. Consistent with Energy Safety's guidance, we have prioritized resolving our asset tag backlog and will describe in detail our continued strategy for achieving this goal, including corrective actions to address the delay in resolving E tags, in our 2023 WMP. | [6 empty] | a. After reviewing the distribution tags that have been completed this year, as well as the language of our 2022 WMP Revision Notice response, we determined that only E tags (or E tags that changed into another type of tag) should be counted for purposes of Target D.10 because they were part of the “workplan” discussed in the WMP submission. While we won’t meet the volume target for E tags we have exceeded the 55,000 target holistically, we had much higher priority work come in after our revision notice submission pertaining to A and B tags. We felt addressing these tags was the right thing to do given they are higher priority and pose a greater risk to our customers.
PG&E | 2023-02-01 | Project | 2022-01-01 | 2002-12-31 | HFTD/HFRA Open Tag Reduction - Transmission | Close a minimum of 18,000 HFTD or HFRA transmission tags in PG&E's workplan as of June 30, 2022, barring External Factors. | This initiative is focused on closing out open maintenance tags for transmission facilities in HFTD and HFRA areas. | Grid Design, Operations, and Maintenance | 8.1 | Open work orders |  | 8.1.7 | D.11 | PG&E_Grid Design, Operations, and Maintenance_Open work orders_D.11_2022 |  | Equipment ignition likelihood | No | # of closed Transmission tags | 18000 | N/A | N/A | 14872 | 18000 | N/A | N/A | 19398 | 21145 |  | This was not an initiative in Q1. | This was not an initiative in Q2. | In Q3, we created Initiative Target D.11 as part of the 2022 Revision Notice. The target for this work is to complete 18,000 HFTD/HFRA transmission tags by the end of the year. Please note that additional tags have been brought into the latest workplan as they are deemed essential due to a variety of reasons. Due to the work verification process which delayed the tag status, 2,055 tags from the June 30, 2022 workplan have been completed, but will not be counted against the Q3 tag count as they were completed prior to July 2022. They have, however, been included in the YTD goal. In Q3, we completed 4,997 tags resulting in 19,398 transmission tags completed against the YTD Target of 14,872. We met the Q3 goal of 3,800 tags due to 20 tags being prevented from being completed as a result of External Factors. | The WMP target was to close a minimum of 18,000 HFRA/HFTD transmission tags by the end of the year, barring external factors. In Q4, we completed 1,747 tags, bringing our annual total to 21,145 and exceeding our annual target of 18,000 . Please note that, while we were able to exceed our annual target for this work, we did not meet the Q4 quarterly target of closing at least 3,500 tags because our Revision Notice response overestimated the total number of open tags and underestimated the number of tags completed in Q2 for which the paperwork had not been finalized. Because we were able to perform the majority of this work earlier in the year—prior to fire season—and were able to exceed the annual target, we do not view this as a missed target. | Completed
PG&E | 2023-02-01 | Program |  |  | Enhanced Vegetation Management | Complete EVM work on 1,800 risk ranked distribution circuit miles, barring External Factors. | This initiative implements our Enhanced Vegetation Management program to reduce the risk associated with vegetation contact causing a potential ignition. | Vegetation Management and Inspections | 8.2 | Clearance |  | 8.2.3.3 | E.01 | PG&E_Vegetation Management and Inspections_Clearance_E.01_2022 | 634 | Contact from vegetation ignition likelihood | No | # of circuit miles | 1800 | 217 | 757 | 1405 | 1800 | 291.9 | 933.86 | 1453.86 | 1923.81 |  | In Q1, PG&E completed 291.9 miles of EVM work. These amounts are subject to change based upon the completion of reviews by our VM and Internal Audit departments. | The EVM program surpassed the YTD Target of 757 miles with 933.9 circuit miles completed by June 30, 2022. These amounts are subject to change based upon the completion of reviews by our VM and Internal Audit departments. | The EVM program completed 1,453.9 miles YTD, exceeding the September YTD Target of 1,405 miles. The program is on track to meet the 1,800-mile commitment by end of year. These amounts are subject to change based upon the completion of reviews by our VM and Internal Audit departments. | The EVM program completed 1,923.81 circuit miles by the end of 2022, exceeding the WMP target of 1,800 miles. 98.7% of the EVM work performed in 2022 was performed on the highest 20% risk-ranked miles. | Completed
PG&E | 2023-02-01 | Program |  |  | Pole Clearing Program | Inspect and clear (where clearance is needed) all poles identified in PG&E's Vegetation Management Database as of October 1, 2021, in HFTD areas or HFRA, not required by PRC 4292 and barring External Factors. Any assets discovered between October 1, 2021 and August 31, 2022 will be inspected and cleared (where clearance is needed) by the target due date, barring External Factors. Any assets discovered after August 31, 2022 will be inspected and cleared (where clearance is needed) within 45 days of when added to the Vegetation Management Database, barring External Factors. | This initiative performs pole clearing inspections and work (where needed) for poles in HFTD and HFRA areas where clearance is not required by PRC Section 4292. Pole clearing can reduce the potential for a wildfire ignition. | Vegetation Management and Inspections | 8.2 | Pole Clearing |  | 8.2.3.1 | E.02 | PG&E_Vegetation Management and Inspections_Pole Clearing_E.02_2022 | 634 | Contact from vegetation ignition likelihood | No | # of distribution poles | 7000 | 6600 | 7000 | 7000 | 7000 | 5884 | 8299 | 8356 | 8356 |  | Since October 2021, PG&E inspected and cleared, as needed 9,511 Poles outside of compliance mandated areas. A subtotal of 5,884 poles were in HFTD or HFRA. Please note the Target description has been revised in an April 25, 2022 Errata submission. | The program surpassed the YTD target of 7,000 with 8,299 units in HFTD or HFRA completed YTD. This includes an revised number of 5,884 poles from Q1 and 2,415 poles from Q2 in HFTD or HFRA. Poles are only counted once regardless of whether they were inspected and/or cleared more than once. The program has met the 2022 target to inspect and clear (where clearance is necessary) all poles identified in our Vegetation Management Database as of October 1, 2021, in HFTD areas or HFRA, not required by PRC 4292 and barring External Factors. Note the assets could still be discovered until August 31, 2022 that could require inspection and cleared (where clearance is needed). | Our Pole Clearing program completed inspection and clearing, where clearing is needed, of 8,356 poles cumulatively within the current annual inspection cycle. The language in the initiative target focuses on all poles identified in PG&E's Vegetation Management Database as of October 1, 2021, in HFTD areas or HFRA, not required by PRC 4292 and barring External Factors. However, as a result of challenges in our legacy recordkeeping system, we were unable to establish a precise baseline pole population as of October 1, 2021. To validate the pole population and completion of initiative target E.02, our pole clearing team captured the data in the legacy system as of April 4, 2022 and reviewed the inspection records that had taken place from October 1, 2021 (the start of the program) to April 4, 2022. This created the baseline database of poles for validating completion of the initiative target. Based on this approach, we believe that we have completed initiative target E.02. We plan to make improvements to our legacy system to better track the number of poles in our database and that are inspected and cleared as a part of our Pole Clearing program. We are developing a process to address documentation gaps identified in 2022 until our legacy system and program has transitioned to the One Veg technology tool. | Commitment completed in Q3. | Completed
PG&E | 2023-02-01 | Program |  |  | LiDAR Ground Inspections - Distribution | Complete at least 2,000 circuit miles of Mobile LiDAR capture on HFTD road-access electric distribution lines, barring External Factors. If at any point PG&E determines this technology does not effectively support efforts to reduce wildfire risk when compared to other viable approaches or technology, PG&E will pause or discontinue Ground Based LiDAR efforts. | This initiative performs LiDAR ground inspections of distribution lines to help identify potential vegetation encroachments. | Vegetation Management and Inspections | 8.2 | Vegetation Inspections |  | 8.2.2.1 | E.03 | PG&E_Vegetation Management and Inspections_Vegetation Inspections_E.03_2022 | 655 | Contact from vegetation ignition likelihood | No | # of circuit miles | 2000 | 0 | 500 | 1000 | 2000 | 0 | 383.47 | 2507.35 | 3358.66 |  | The LiDAR Ground program is on track to both commence reporting completed inspections in June 2022 and complete the 2,000 mile commitment by end of year. | The program fell behind the YTD Target of 500 miles with 383 circuit miles completed by June 30, 2022. These amounts are subject to change based upon the completion of reviews by our VM and Internal Audit departments. | The LiDAR Ground program worked 2,507 miles YTD, exceeding the September YTD Target of 1,000 miles. The program is on track to complete the 2,000 mile commitment by end of year. | The LiDAR Ground program worked 3,358.66 circuit miles by the end of 2022, exceeding the WMP target of 2,000 circuit miles. | Completed
PG&E | 2023-02-01 | Program |  |  | LiDAR Routine Inspections - Transmission | Complete LiDAR inspection of approximately 18,000 circuit miles of transmission lines, barring External Factors. | This initiative performs LiDAR ground inspections of transmission lines to help identify potential vegetation encroachments. | Vegetation Management and Inspections | 8.2 | Vegetation Inspections |  | 8.2.2.1 | E.04 | PG&E_Vegetation Management and Inspections_Vegetation Inspections_E.04_2022 | 658 | Contact from vegetation ignition likelihood | No | # of circuit miles | 17867 | 11883 | 17867 | 17867 | 17867 | 13147 | 17867 | 17867 | 17867 |  | In Q1, PG&E completed 13,147 of LIDAR inspections of transmission facility miles. | The program has completed aerial LiDAR inspections of all transmission circuit miles resulting in 17,867 circuit miles completed. Note: We completed Transmission LiDAR inspection of 17,867 circuit miles. We informed Energy Safety of an error in the unit of measure used to define the 2022 WMP target for this initiative – at completion of initiative, we identified that our target of approximately 18,000 “circuit miles” was intended to have meant “line miles” per the Energy Safety definition (resulting in 17,867 circuit miles vs. 18,194 line miles). | This Target was completed in Q2, no additional inspections were performed in Q3. | WMP target completed in Q2 | Completed
PG&E | 2023-02-01 | Program |  |  | Vegetation Management - Quality Verification | Target revised per Revision Notice #10 1. Quality Assurance Audits Type of audits; Distribution - voltages less than 60kV in our Routine, Tree Mortality, EVM and Pole Clearing programs. (43 audits) Vegetation Pole Clearing (1 audit) Transmission - high voltage 60kV and greater and applies to maintaining high voltage transmission corridors to Minimum NERC clearance, PRC 4293 clearance, and GO 95 Rule 35 clearance (1 audit) Procedure audit of the following: Enhanced Vegetation Management, Record Keeping, Transmission and Distribution Line Verification, and Refusal Procedure (4 audits) Distribution and transmission audits include multiple trees and a 95% AQL would represent 95% of the total trees audited being in compliance with PG&E requirements. The vegetation pole clearing audit includes multiple poles and a 95% AQL would represent 95% of the total poles audited being in compliance with PG&E requirements. The procedure audit includes a review of PG&E’s vegetation standards and whether PG&E’s vegetation management team adhered to the process and procedures in the standard. 2. Quality Verification Reviews Type of Verification; Distribution - voltages less than 60kV in our Routine, Tree Mortality, EVM and Pole Clearing programs (1,522 Reviews). Vegetation Pole Clearing (3,421 Poles). Transmission - high voltage 60kV and greater and applies to maintaining high voltage transmission corridors to Minimum NERC clearance, PRC 4293 clearance, and GO 95 Rule 35 clearance (260 Reviews). Distribution and transmission reviews include multiple trees and a 95% AQL would represent 95% of the total trees reviewed being in compliance with PG&E requirements. The vegetation pole clearing reviews includes multiple poles and a 95% AQL would represent 95% of the total poles reviewed being in compliance with PG&E requirements. | This initiative performs Quality Assurance and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspections | 8.2 | Quality assurance / quality control |  | 8.2.5 | E.05 | PG&E_Vegetation Management and Inspections_Quality assurance / quality control_E.05_2022 | 670 | Contact from vegetation ignition likelihood | No | [10 empty] | Target revised per Revision Notice #10 1. Quality Assurance Audits Type of audits; Distribution - voltages less than 60kV in our Routine, Tree Mortality, EVM and Pole Clearing programs. (43 audits) Vegetation Pole Clearing (1 audit) Transmission - high voltage 60kV and greater and applies to maintaining high voltage transmission corridors to Minimum NERC clearance, PRC 4293 clearance, and GO 95 Rule 35 clearance (1 audit) Procedure audit of the following: Enhanced Vegetation Management, Record Keeping, Transmission and Distribution Line Verification, and Refusal Procedure (4 audits) Distribution and transmission audits include multiple trees and a 95% AQL would represent 95% of the total trees audited being in compliance with PG&E requirements. The vegetation pole clearing audit includes multiple poles and a 95% AQL would represent 95% of the total poles audited being in compliance with PG&E requirements. The procedure audit includes a review of PG&E’s vegetation standards and whether PG&E’s vegetation management team adhered to the process and procedures in the standard. 2. Quality Verification Reviews Type of Verification; Distribution - voltages less than 60kV in our Routine, Tree Mortality, EVM and Pole Clearing programs (1,522 Reviews). Vegetation Pole Clearing (3,421 Poles). Transmission - high voltage 60kV and greater and applies to maintaining high voltage transmission corridors to Minimum NERC clearance, PRC 4293 clearance, and GO 95 Rule 35 clearance (260 Reviews). Distribution and transmission reviews include multiple trees and a 95% AQL would represent 95% of the total trees reviewed being in compliance with PG&E requirements. The vegetation pole clearing reviews includes multiple poles and a 95% AQL would represent 95% of the total poles reviewed being in compliance with PG&E requirements. | In Q1, five QAVM audits were completed. QVVM performed: (1) 388 Distribution Reviews were completed; (2)104 Transmission Reviews were completed; (3) 596 Poles were audited under VC Pole Clearing; (4) Monthly Enhanced Vegetation Management audits began in February; and (5) 0 Quality CAP Closure Process audits were conducted. | The program fell behind the YTD Target of 95% pass rate in two areas. QVVM Distribution - Off Track with Pass Rate of 91.75% QVVM Pole Clearing - Off Track with Pass Rate of 89.90% We are in the process of developing a corrective action plan and will provide a description of this plan in our next quarterly update. QAVM: Through Q2, 14 audits have been completed YTD with 9 audits currently in progress QVVM: Through Q2, (1) 378 Distribution Reviews have been completed; (2) 174 Transmission Reviews have been completed; (3) 1,297 Poles have been audited under VC Pole Clearing; (4) 5 monthly Enhanced Vegetation Management audits have been completed amounting to 2,497 Line Segments; and (5) 6 Quality CAP Closure Process audits have been completed. Note: Prior to Q2 reporting, E.05 did not have published targets for the various QA and QV audit/review categories. Per Revision Notice 10, the OEIS has requested that targets be set for each of the work categories that are reported in E.05. The OEIS requested that these targets not be any lower than 95% “AQL”. Acceptable quality level (AQL) is defined as follows: When a continuing series of lots is considered, a quality level which for purposes of sampling inspection is the limit of satisfactory process average. (Juran, Joseph, and A. Blanton Godfrey. "Quality handbook." Republished McGraw-Hill 173, no. 8 (1999): 34-51. Page 46.7). In other terms, AQL is the worst quality level that is still considered satisfactory. In this case, we could set the AQL for Vegetation Pole Clearing as 95%, meaning if 95% of work audited is deemed compliant with pole clearing specifications and congruently 5% of that same work is considered non-compliant, we would consider this “acceptable." All QA and QV work categories in E.05 are now given a “AQL” / Pass Rate target of 95%. (Total items that passed the audit divided by the total items audited). Status of E.05 Sub-Components: QAVM Distribution - On Track with Pass Rate of 99.79%. QAVM Pole Clearing - On Track (no audits complete to date with first audit scheduled to complete in late July). QAVM Transmission - On Track (no audits complete to date with first audit scheduled to complete in early August). QAVM Process Audits - On Track (no audits complete to date with first audit scheduled to complete in July). QVVM Distribution - Off Track with Pass Rate of 91.75%. QVVM Pole Clearing - Off Track with Pass Rate of 89.90%. QVVM Transmission - On Track with Pass Rate of 95.20%. | In Q3, QVVM performed: (1) 457 out of 381 planned Distribution Reviews were completed. (2) 68 out of 66 planned Transmission Reviews were completed. (3) 1,537 out of 1014 planned VC Pole Clearing audits were completed. Status of E.05 Sub-Components (Target Pass Rate 95%): QVVM Distribution Audit Results- Off Track with Pass Rate of 91.40%. QVVM Pole Clearing Audit Results - Off Track with Pass Rate of 89.26%. QVVM Transmission Audit Results - Off Track with Pass Rate of 94.32%. For QVVM deficiencies, QV provides notifications of findings to the LOB, as well as AQL scores. The LOB is responsible for creating CAPs and developing action plans to mitigate findings. If there is a compliance issue, QVVM will create a CAP, otherwise, QV will follow up on corrective actions and CAPs to ensure they are being addressed and closed out timely. However, QV does not perform re-inspection on those corrective actions. In Q3, QAVM performed: (1) 8 out of 14 planned Distribution audits were completed. (2) 1 out of 1 planned Veg Pole Clearing audit was completed. (3) 1 out of 1 planned Transmission audit was completed. (4) 1 out of 3 planned Process audit was completed. Status of E.05 Sub-Components (Target Pass Rate 95%): QAVM Distribution Audit Results- On Track with Pass Rate of 99.82%. QAVM Pole Clearing Audit Results- Met target with Pass Rate of 98.20%. QAVM Transmission Audit Results- Met target with Pass Rate of 100.00% QAVM Process Audit Results - Off Track with Pass Rate of 88% - 39 CAPs were created from the 1 process audit to work on this deficiency. 19 out of the 39 CAPs have been completed, and the remainder are on track to be completed by the individual due dates associated with each CAP. | QAVM Q4/YTD Status: 1. All 43 planned Distribution Audits were completed with a FINAL 2022 PASS RATE of 99.78% resulting in meeting the AQL Target of 95% 2. 1 planned Vegetation Pole Clearing audit was complete with a FINAL 2022 PASS RATE of 98.20% resulting in meeting the AQL Target of 95% 3. 1 planned Transmission audit was completed with a FINAL 2022 PASS RATE of 100%, resulting in meeting the AQL Target of 95% 4. 4 Procedure Audits were completed with a FINAL 2022 PASS RATE of 76.00% which did not meet the AQL Target of 95% QVVM Q4/YTD Status: 1. A total of 1,640 Distribution Reviews were completed (versus a plan of 1,522) with a FINAL 2022 PASS RATE of 91.34% which did not meet the AQL Target of 95% 2. A total of 349 Transmission Reviews were completed (versus a plan of 260) with a FINAL 2022 PASS RATE of 94.21% which did not meet the AQL Target of 95% 3. A total of 3,469 Poles were audited in the Pole Clearing audit (versus a plan of 3,421) with a FINAL 2022 PASS RATE of 90.26% which did not meet the AQL Target of 95% As part of the Revision Notice, Energy Safety directed PG&E to establish a 95% AQL for audits/reviews for seven VM program. The initiative target has 14 different components; seven relate to the number of audits/reviews performed and seven relate to programs achieving a 95% AQL. In our Revision Notice response, we explained that we may not be able to meet this target given that we established it midway through the year and a lot of work had already taken place, especially for pole clearing. We were able to achieve the specified number of audits/reviews for the seven programs. However, we were unable achieve 95% AQL for four of the seven programs. Of these four programs, two of these programs (QVVM Distribution and QVVM Transmission) had 2021 AQL scores. These programs increased their AQL scores in 2022 (increases ranged from 3.41% - 6.25%). | Delayed | Corrective Actions Plans for QAVM include: 1. Process Audit: A CAP was created to memorialize this audit and give clarity into the corrective action. As a result, multiple procedures and standards are being revised and/or updated. These controls will go through the proper change management and communication to ensure compliance going forward. Corrective Actions for QVVM include: 2. Distribution: Findings were attributed to: (1) missed clearance; (2) overlist of trees; and (3) improper cut. In process QC and controls have been implemented which resulted in improvements in VM work execution when compared to 2021. These controls are expected to yield an AQL of 95% or higher in 2023. 3. Transmission: Findings were attributed to: (1) inconsistent use of Shape Tags; and (2) missed clearance at pole base. Shape tags represented a majority of all findings. This practice of shape tags was eliminated and communicated accordingly to establish standard work. Although we expect significant improvements when compared to 2021, this work was substantially complete when this commitment was established in July 2022. 4. Pole Clearing: Findings were attributed to: (1) missed clearance; (2) overlist of trees; and (3) missed tree marking. In process QC and controls have been implemented which resulted in improvements in VM work execution when compared to 2021. These controls are expected to yield an AQL of 95% or higher in 2023.
PG&E | 2023-02-01 | Program |  |  | Defensible Space Inspections - Distribution Substation | Complete defensible space inspections in alignment with the guidelines set forth in PRC 4291 at 132 distribution substations within HFTD areas or HFRA, barring External Factors. | This initiative clears defensible space areas around distribution substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspections | 8.2 | Substation defensible space |  | 8.2.3.5 | E.06 | PG&E_Vegetation Management and Inspections_Substation defensible space_E.06_2022 | 682 | Wildfire exposure potential | No | # of Distribution Substations | 132 | 109 | 132 | 132 | 132 | 116 | 132 | 132 | 132 |  | In Q1, PG&E completed Defensible Space Inspections at 116 Distribution Substations within either a Tier 2, Tier 3, or HFRA. | As of Q2, this initiative has been completed as planned. All 132 Distribution Substation inspections are complete and prescribed routine maintenance activities are being executed. | This Initiative was completed in Q2. | This initiative was completed in Q2. | Completed
PG&E | 2023-02-01 | Program |  |  | Defensible Space Inspections - Transmission Substation | Complete defensible space inspections in alignment with the guidelines set forth in PRC 4291 at 55 transmission substations within HFTD areas or HFRA, barring External Factors. | This initiative clears defensible space areas around transmission substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspections | 8.2 | Substation defensible space |  | 8.2.3.5 | E.07 | PG&E_Vegetation Management and Inspections_Substation defensible space_E.07_2022 | 684 | Wildfire exposure potential | No | # of Transmission Substations | 55 | 33 | 55 | 55 | 55 | 49 | 55 | 55 | 55 |  | In Q1, PG&E completed Defensible Space Inspections at 49 Substations within either a Tier 2, Tier 3, or HFRA. | As of Q2, this initiative has been completed as planned. All 55 Transmission Substation inspections are complete and prescribed routine maintenance activities are being executed. | This initiative was completed in Q2. | This initiative was completed in Q2. | Completed | [7 empty] | ii. Three of these programs had 2021 AQL scores, which are QVVM Distribution, QVVM Pole Clearing, and QVVM Transmission. These programs increased their scores in 2022 (increases ranged from 2.18% - 6.25%).
PG&E | 2023-02-01 | Program |  |  | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | Complete defensible space inspections at 61 Hydroelectric Generation Substations and Powerhouses within HTFD areas or HFRA, barring External Factors. Co-located hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around hydroelectric substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspections | 8.2 | Substation defensible space |  | 8.2.3.5 | E.08 | PG&E_Vegetation Management and Inspections_Substation defensible space_E.08_2022 | 686 | Wildfire exposure potential | No | # of Hydroelectric Substations and Powerhouses | 61 | 42 | 61 | 61 | 61 | 46 | 61 | 61 | 61 |  | In Q1, PG&E completed Defensible Space Inspections at 46 Hydroelectric Generation Substations and Powerhouses within either a Tier 2, Tier 3, or HFRA. | All 61 Power Generation powerhouses and switchyards have been inspected for Defensible Space. | This initiative was completed in Q2. | This initiative was completed in Q2. | Completed
PG&E | 2023-02-01 | Program |  |  | Utility Defensible Space - Distribution | Complete utility defensible space work on a minimum of 7,000 poles in the HFTD, barring External Factors. | This initiative clears defensible space around poles in HFTD areas to reduce the potential for wildfire ignition . | Vegetation Management and Inspections | 8.2 | Clearance |  | 8.2.3.3 | E.09 | PG&E_Vegetation Management and Inspections_Clearance_E.09_2022 | 699 | Contact from vegetation ignition likelihood | No | # of distribution poles | 7000 | 1750 | 3567 | 5359 | 7000 | 2320 | 4358 | 6252 | 7168 |  | In Q1, PG&E completed 2,320 pole clearings. | The program surpassed the YTD Target of 3,567 poles with 4,358 poles completed by June 30, 2022. | The UDS program completed clearing 6,252 poles YTD, exceeding the September YTD Target of 5,359 poles. The program on track to meet the 2022 commitment to clear a total of 7,000 poles by end of year. Note that completed units previously reported were revised based on review of the VM legacy database. | PG&E completed clearing 7,168 poles by the end of 2022, exceeding the WMP target of 7,000 poles. | Completed
PG&E | 2023-02-01 | Program |  |  | Pole Clearing in State Responsibility Areas | PG&E will inspect and clear, where clearance is needed, 80,258 distribution poles subject to PRC 4292 in State Responsibility Areas identified by PRC 4292, barring External Factors or poles that are exempt under Title 14 Cal. Code of Regulations 1255. This number may change as poles are added, removed, or have a change in status during the pole clearing program cycle. Any assets discovered between October 1, 2021 and August 31, 2022 will be inspected and cleared (where clearance is needed) by the target due date, barring External Factors. Any assets discovered after August 31, 2022 will be inspected and cleared (where clearance is needed) within 45 days of when added to the Vegetation Management Database, barring External Factors. Poles in fields that are plowed or cultivated, such as planted row crops, cultivated fields, vineyards, nonflammable summer fallow, irrigated pastureland, fruit, nut, citrus orchards, Christmas tree farms, swamp, marsh or bog land and where vegetation is maintained less than 30.48 cm in height, is fire resistant, and is planted and maintained for the specific purpose of preventing soil erosion and fire ignition. | This initiative performs pole clearing inspections and work (where needed) for poles in HFTD and HFRA areas where clearance is required by PRC Section 4292. Pole clearing can reduce the potential for a wildfire ignition. | Vegetation Management and Inspections | 8.2 | Pole Clearing |  | 8.2.3.1 | E.10 | PG&E_Vegetation Management and Inspections_Pole Clearing_E.10_2022 |  | Contact from vegetation ignition likelihood | No | # of distribution poles | 80258 | N/A | N/A | 80258 | 80258 | N/A | N/A | 80208 | 80208 |  | This was not an initiative in Q1 | As this new initiative was added as part of Revision Notice at the end of Q2, the VM program has identified the applicable poles for this initiative and will provide a progress update for the Q3 QIU report. | At the end of Q3, we reported this commitment as completed with 80,208 distribution poles inspected and cleared, where clearance was needed. E.10 pole Clearing program like E.02, is managed through a VM legacy database system. Due to the timing of the Revision Notice, the team was near the end of its inspection cycle and was able to use the pole population as the total and provide the database for our internal auditing teams to review and support it meet the spirit and intent, which is the next level down from full validation. To mature and support this program forward, the team has created a record of evidence process to address the documentation gaps identified in 2022 until this legacy system and program has transitioned to the One Veg technology tool. Despite the challenges in the legacy system, we believe that the current records are sufficient to demonstrate that the target was achieved. We have evidence that a base population of poles was inspected and cleared, meeting the spirit and intent of this target. Furthermore, to demonstrate the teams’ efforts to improve the data management challenges within the legacy system, towards the end of the two program cycles, the team reviewed and created a more deliberate administrative boundary and separation of poles in the LRA and SRA in initiatives E.02 and E.10, respectively. This resulted in 1,841 poles having their respective administrative boundaries changed, causing the pole count to be moved from E.10 to E.02. These poles are not doubled counted, but the result lowered the count for E.10 and raised the count for E.02, thus leaving the 50-pole deficit in E.10. These poles were originally part of the E.10 SRA inspection and clearing, but the data scrub and corresponding data file reflect the data clean-up effort and the movement of these poles to the E.02 LRA inspection count. | This initiative was completed in Q3. | 0
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-04-01 | EPSS - Settings Design and Test | Conduct laboratory testing to refine the circuit device design parameters for 2022 EPSS implementation. | This initiative tests the design parameters for EPSS implementation for PG&E's 2022 EPSS program. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk (Grid Ops) |  | 8.1.8.1 | F.01 | PG&E_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk (Grid Ops)_F.01_2022 | 730 | Equipment ignition likelihood | No | [10 empty] | Conduct laboratory testing to refine the circuit device design parameters for 2022 EPSS implementation. | In Q1, 174 tests were performed at the ATS High Current Test Yard. The testing results indicate the following: * The probability of ignition is higher on dried sod compared to other natural fuel media with higher moisture content. * As the fault current increases, the probability of sustained ignition increases. * As the clearing time increases, the probability of sustained ignition increases for all the fault current magnitudes used for testing. Based on the test results, the reduction in clearing time (fast relaying) for all faults will help reduce the ignition risk and is aligned with enhanced safety practices by other utilities and industry research. Faster relaying will also help limit the movement of faults/traveling arcs on circuits and flashover/arcing to adjacent phases. It was observed that for faster clearing times below 100ms, the risk of sustained ignition was minimal compared to conventional relay settings. Increasing EPSS relay clearing times beyond 100ms is not recommended at this time, as it may increase the ignition risk. | We completed the testing for this initiative on March 31, 2022 and an ATS EPSS Clearing Time Testing Final Report was provided as evidence of completion. | This target was completed in Q1. | This target was completed in Q1. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-08-01 | EPSS - Install Settings on Distribution Line devices | Load the engineered settings on protection devices (line reclosers and fuse savers) on the identified 1,018 circuits (as of March 10, 2022) on the following schedule, barring External Factors: (1) On 80 percent of line devices by 5/1/22 and, (2) On the remaining 20 percent of line devices by 8/1/22 | This initiative implements EPSS load settings on protection devices so that EPSS can be enabled to reduce the potential for wildfire ignition. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk (Grid Ops) |  | 8.1.8.1 | F.02 | PG&E_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk (Grid Ops)_F.02_2022 | 730 | Equipment ignition likelihood | No | # of line reclosers and fuse savers | 3580 | 1574 | 3580 | 3580 | 3580 | 1440 | 3568 | 3580 | 3580 |  | A total of 1,440 protection line devices (line reclosers and fuse savers) have had EPSS settings designed and installed through March 31, 2022. Please note the Target description has been revised in an April 29, 2022 Errata submission. | The program fell behind the YTD Target of 3,580 with 3,568 settings loaded on protective devices completed by June 30, 2022. EPPS was delayed in reaching the projected Q2 target of 3580; through Q2, 3,464 line devices (line reclosers and fuse savers) were made capable (3,568 total devices when including COE/approved external factors (i.e., scope change, access issues, etc.). While we did not make all 3,580 line devices capable as projected in Q2, we are still on track to meeting the EPSS line device capability target for completion by 8/1/2022. Protection Line Devices Made Capable prior to 2022 - Please note some line devices were made EPSS capable prior to 2022 as part of the 2021 pilot program and those line devices will be counted toward the 2022 target. Additionally, many Fuse Saver devices come programmed from the manufacturer with fast trip protection settings pre-loaded on the devices, and were installed on the system prior to and during 2022 . All devices have been reviewed to validate setting status and coordination with other devices on the corresponding circuit. Circuits with Circuit Breaker Only Protection – When examining protection across all 1,018 circuits in EPSS scope, some circuits are solely protected by a circuit breaker. This F.02 target initiative is specific to making line devices capable. Critical Operating Equipment – Due to equipment failure for some Critical Operating Equipment (COE), fast-trip settings could not be loaded and installed on all line devices identified in EPSS scope and therefore an exception for “COEs” have been established in F.02 target initiative. As a result of the COE exception, the EPSS program established an initiative in May to prioritize completion of COE repairs on those devices necessary for protection of the High Fire Risk Area. While repairs are completed, EPSS enablement procedure directs protection of identified circuit protection zones by an “upstream” device. The EPSS program is coordinating with the PG&E work execution teams that are responsible for COE repair work to ensure prioritized EPSS work is scheduled and completed timely to allow for EPSS settings to be installed. | We met the Target of 3,580 installed setting on distribution line devices in July with 3,467 devices made capable and 113 exclusions. Note “Exclusions” are defined as (1) protection devices that due to repair status cannot receive the engineered settings; (2) protection devices removed from service after March 10, 2022; and (3) circumstances arising from External Factors. At the time of validation, all exclusions were listed in the month of June. Since meeting the target there were 5 exclusion devices made capable in July and 4 more in August, bring the total exclusions listed in June down to 104 and total devices enabled to 3,476. In Q4, we will continue to work on making the 104 exclusion devices capable as equipment, access and other external factors are resolved. Also, in Q4 we will work to enable additional devices and will report those values in our Q4 QIU update. | We met the target of 3,580 installed setting on distribution line devices on the 1,018 circuits in Q3. Note “Exclusions” are defined as (1) protection devices that due to repair status cannot receive the engineered settings; (2) protection devices removed from service after March 10, 2022; and (3) circumstances arising from External Factors. At the time of validation, all exclusions were listed in the month of June. Since Q3, there were 6 additional exclusion devices were made capable, bringing the total exclusions down to 98 and total devices enabled to 3,482. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-05-01 | EPSS - Develop Enablement Standards and Procedures | Develop the procedure to govern the enablement of EPSS settings in 2022. | This initiative develops a procedure to govern when EPSS settings will be enabled in 2022. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk (Grid Ops) |  | 8.1.8.1 | F.03 | PG&E_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk (Grid Ops)_F.03_2022 | 730 | Equipment ignition likelihood | No | [10 empty] | Develop the procedure to govern the enablement of EPSS settings in 2022. | PG&E is on track to meet the 5/1 delivery date. | The work on this initiative was completed on April 30, 2022 and the TD-1470S EPSS Standard and supplemental documentation were provided as evidence of completion. | This Target was completed in Q2. | This Target was completed in Q2. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-08-01 | EPSS - Reliability Improvements | Initiate reliability mitigations on 50 EPSS capable circuits in the HFTD areas, HFRA and non-HFTD buffer zones based on highest projected Customer Experiencing Sustained Outage (CESO). | This initiative implemented reliability mitigations on EPSS-enabled circuits to reduce the impact of EPSS on customers. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk (Grid Ops) |  | 8.1.8.1 | F.04 | PG&E_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk (Grid Ops)_F.04_2022 | 730 | Equipment ignition likelihood | No | # of circuits | 50 | 0 | 42 | 50 | 50 | 48 | 49 | 50 | 50 |  | In Q1, PG&E initiated reliability mitigations on 48 of the 50 highest projected Customer Experiencing Sustained Outage (CESO) circuits. | The program surpassed the YTD Target of 42 with 49 circuits completed by June 30, 2022. The program has met all interim milestones, due to late reporting of notifications, which resulted in 7 additional circuits being completed in Q1 than initially reported in Q1. In Q1, we initiated reliability mitigations on 48 of the 50 highest projected CESO circuits. In Q2, we completed work on 1 of the remaining 2 circuits. | This Target was completed in Q3. | This Target was completed in Q3. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Data Governance - Identify and Centralize High Priority Data | 1. Document and implement a process to identify data gaps in Foundry for critical risk drivers 2. Identify and incorporate new high-priority datasets into Foundry in support of analytic products 3. Identify and incorporate 20 new, foundational ontology objects into Foundry | This initiative improves PG&E's data governance by identifying data gaps for critical risk drivers, includes new data sets in Foundry, and includes new objects in foundry. | Wildfire Mitigation Strategy Development | 7.1 | Approach |  | 7.1.1 | G.01 | PG&E_Wildfire Mitigation Strategy Development_ Approach_G.01_2022 | 740 | Wildfire exposure potential | No | [10 empty] | 1. Document and implement a process to identify data gaps in Foundry for critical risk drivers 2. Identify and incorporate new high-priority datasets into Foundry in support of analytic products 3. Identify and incorporate 20 new, foundational ontology objects into Foundry | PG&E's ontology team is progressing on 10 high priority ontology objects and is on track. | Two L2 Ontology objects (Dist. Support Structures, Dist. Primary Overhead Conductors) have been released; 11 additional objects are L2 "ready", 5 of which are targeted for release by July 22, 2022. The evolving standard for ontology object L2 maturity requires support from Business Data Stewards (BDS); the BDS program has encountered process and resource availability issues. | On track with WMP Plan / Target - 15 L2 Ontology objects have been released; 7 objects are L2 "ready" pending final BDS review and on track for November completion - this will bring us to 22, meeting the commitment of 20; 1 additional object is L2 ready but there are resource constraints in assigning a BDS | This annual target has been met as we have: (1) documented and implemented a process to identify data gaps in Foundry for critical risk drivers; (2) identified and incorporated new high-priority data sets into Foundry in support of analytic products; and (3) successfully completed the development and incorporation of 22 L2 Ontology objects in support of wildfire mitigation analytics. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-09-30 | Risk Spend Efficiency - Develop and Share Governance Process | Develop and share RSE Governance Process with Energy Safety. | This initiative develops and shares with Energy Safety a governance process for Risk-Spend Efficiency. | Wildfire Mitigation Strategy Development | 7.1 | Risk-Informed Prioritization |  | 7.1.3 | H.01 | PG&E_Wildfire Mitigation Strategy Development_Risk-Informed Prioritization_H.01_2022 | 783 | Wildfire exposure potential | No | [10 empty] | Develop and share RSE Governance Process with Energy Safety. | Mockup of Risk Spend Efficiency (RSE) Governance project timeline and process developed in draft. | In Q2, initial meetings with SMEs were held and a draft overall process was developed and shared internally for review. | RSE Governance team documented the Risk Spend Efficiency (RSE) Governance Process, including 3rd-party findings, to ensure continued improvements in the robustness of RSEs. The progress and findings are summarized in a PowerPoint presentation which was sent via email to OEIS on 9/22/2022, thereby completing this target. | This Target was completed in Q3. | Completed
PG&E | 2023-02-01 | Project | 2022-01-01 | 2022-12-31 | Community Engagement - Meetings | Host 22 customer and community focused virtual meetings (i.e., Safety Town Halls, CWSP Webinars) to further stakeholder and community awareness of PG&E's wildfire mitigation efforts. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | 8.5 | Public Outreach and education awareness program |  | 8.5.2 | J.01 | PG&E_Community Outreach and Engagement_Public Outreach and education awareness program_J.01_2022 | 812 | Wildfire vulnerability | No | # of meetings | 22 | 3 | 16 | 22 | 22 | 4 | 16 | 23 | 23 |  | In Q1, PG&E completed 4 Safety Town Halls and CWSP webinars completed. | The program met the YTD Target of 16 Safety Town Halls and CWSP webinars completed by June 30, 2022. | Completed target in Q3 on August 30. In Q3 PG&E completed 7 Safety Town Halls and CWSP webinars bringing total to date of 23 completed. | This Target was completed in Q3. | Completed
Notes:
1. For Column Q (RiskTargetReduction), PG&E has attempted to chose the risk components targeted listed in the Data Guidelines that most closely matches the Initiative Target.
2. For Column R (MidYear Target), PG&E has indicated "No" because it in the 2022 WMP, we did not have formal mid-year targets for initiatives. We did have quarterly targets for initiatives with quantitative targets. The quarterly targets are identified in Columns U-X.
3. For Columns Y-AA (Q1 - Q3 QuantActualProgress), where appropriate, PG&E has updated numbers from prior quarter QIUs to reflect data validation and QA.
4. For some quantitative initiative targets, numbers may change as data is validated, SAP transaction processing, and/or clerical work is performed to input data. Thus, some quarterly data in earlier submissions of the QIU or Quarterly Notification may have changed in this Q4 QIU.
5. For Column G (InitiativeDescription), some initiatives may have more than 500 characters. We have included in this Table 1 all of the language from the 2022 WMP describing each Initiative Description and therefore may exceed the 500 character limit.

## Table 2
| Utility | Pacific Gas and Electric Company | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | [15 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
| Table 2: Performance Metrics | [8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 8; Actuals 3: 229; Actuals 4: 76; Actuals 1: 7; Actuals 2: 31; Actuals 3: 68; Actuals 4: 29; Actuals 1: 0; Actuals 2: 18; Actuals 3: 3; Actuals 4: 0 | 21 | 21 | 21 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 323; Actuals 2: 0; Actuals 3: 194; Actuals 4: 8; Actuals 1: 7; Actuals 2: 0; Actuals 3: 0; Actuals 4: 5 | 12 | 12 | 12 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 3; Actuals 2: 0; Actuals 3: 59; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 1560; Actuals 2: 1288; Actuals 3: 1205; Actuals 4: 1114; Actuals 1: 2341; Actuals 2: 1498; Actuals 3: 1429; Actuals 4: 1644; Actuals 1: 953; Actuals 2: 1195; Actuals 3: 1107; Actuals 4: 1100 | 4355 | 4355 | 4355 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 3; Actuals 3: 369; Actuals 4: 49; Actuals 1: 2; Actuals 2: 19; Actuals 3: 39; Actuals 4: 16; Actuals 1: 0; Actuals 2: 8; Actuals 3: 0; Actuals 4: 0 | 8 | 8 | 8 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 382; Actuals 2: 0; Actuals 3: 80; Actuals 4: 1; Actuals 1: 17; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 17 | 17 | 17 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 36; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 1480; Actuals 2: 716; Actuals 3: 980; Actuals 4: 667; Actuals 1: 1589; Actuals 2: 696; Actuals 3: 615; Actuals 4: 1011; Actuals 1: 567; Actuals 2: 581; Actuals 3: 512; Actuals 4: 587 | 2247 | 2247 | 2247 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 56; Actuals 3: 980; Actuals 4: 449; Actuals 1: 14; Actuals 2: 221; Actuals 3: 210; Actuals 4: 646; Actuals 1: 0; Actuals 2: 232; Actuals 3: 1; Actuals 4: 0 | 233 | 233 | 233 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 31; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1108; Actuals 2: 3; Actuals 3: 877; Actuals 4: 55; Actuals 1: 13; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 13 | 13 | 13 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 196; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 6094; Actuals 2: 6687; Actuals 3: 7162; Actuals 4: 6804; Actuals 1: 9596; Actuals 2: 8001; Actuals 3: 6689; Actuals 4: 13017; Actuals 1: 7376; Actuals 2: 8964; Actuals 3: 8770; Actuals 4: 8034 | 33144 | 33144 | 33144 | Number of events
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 24; Actuals 4: 7; Actuals 1: 2; Actuals 2: 1; Actuals 3: 4; Actuals 4: 1; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 99; Actuals 2: 0; Actuals 3: 15; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 1 | 1 | 1 | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 4; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 256; Actuals 2: 135; Actuals 3: 85; Actuals 4: 76; Actuals 1: 365; Actuals 2: 105; Actuals 3: 104; Actuals 4: 174; Actuals 1: 63; Actuals 2: 84; Actuals 3: 45; Actuals 4: 104 | 296 | 296 | 296 | Number of events
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 49; Actuals 4: 8; Actuals 1: 1; Actuals 2: 3; Actuals 3: 2; Actuals 4: 2; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 207; Actuals 2: 0; Actuals 3: 6; Actuals 4: 0; Actuals 1: 4; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 4 | 4 | 4 | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 385; Actuals 2: 94; Actuals 3: 95; Actuals 4: 70; Actuals 1: 342; Actuals 2: 59; Actuals 3: 56; Actuals 4: 149; Actuals 1: 51; Actuals 2: 52; Actuals 3: 29; Actuals 4: 94 | 226 | 226 | 226 | Number of events
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 3; Actuals 3: 61; Actuals 4: 33; Actuals 1: 2; Actuals 2: 12; Actuals 3: 9; Actuals 4: 66; Actuals 1: 0; Actuals 2: 22; Actuals 3: 0; Actuals 4: 0 | 22 | 22 | 22 | Number of events
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 4; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 174; Actuals 2: 1; Actuals 3: 40; Actuals 4: 5; Actuals 1: 6; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 6 | 6 | 6 | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 9; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 576; Actuals 2: 492; Actuals 3: 525; Actuals 4: 486; Actuals 1: 861; Actuals 2: 506; Actuals 3: 480; Actuals 4: 2252; Actuals 1: 562; Actuals 2: 644; Actuals 3: 545; Actuals 4: 942 | 2693 | 2693 | 2693 | Number of events
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 1; Actuals 3: 33; Actuals 4: 13; Actuals 1: 2; Actuals 2: 1; Actuals 3: 10; Actuals 4: 6; Actuals 1: 0; Actuals 2: 3; Actuals 3: 0; Actuals 4: 0 | 3 | 3 | 3 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 123; Actuals 2: 0; Actuals 3: 26; Actuals 4: 2; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 2 | 2 | 2 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 10; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 1167; Actuals 2: 1096; Actuals 3: 1053; Actuals 4: 999; Actuals 1: 1775; Actuals 2: 1322; Actuals 3: 1269; Actuals 4: 1255; Actuals 1: 818; Actuals 2: 1033; Actuals 3: 990; Actuals 4: 901 | 3742 | 3742 | 3742 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 2; Actuals 3: 81; Actuals 4: 12; Actuals 1: 1; Actuals 2: 3; Actuals 3: 6; Actuals 4: 3; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0 | 1 | 1 | 1 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 211; Actuals 2: 0; Actuals 3: 12; Actuals 4: 0; Actuals 1: 4; Actuals 2: 0; Actuals 3: 0; Actuals 4: 4 | 8 | 8 | 8 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 6; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 714; Actuals 2: 505; Actuals 3: 834; Actuals 4: 508; Actuals 1: 956; Actuals 2: 565; Actuals 3: 516; Actuals 4: 646; Actuals 1: 406; Actuals 2: 420; Actuals 3: 413; Actuals 4: 358 | 1597 | 1597 | 1597 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 8; Actuals 3: 84; Actuals 4: 63; Actuals 1: 4; Actuals 2: 18; Actuals 3: 14; Actuals 4: 127; Actuals 1: 0; Actuals 2: 35; Actuals 3: 0; Actuals 4: 0 | 35 | 35 | 35 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 3; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 225; Actuals 2: 0; Actuals 3: 47; Actuals 4: 9; Actuals 1: 7; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 7 | 7 | 7 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 14; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 5594; Actuals 2: 6282; Actuals 3: 6800; Actuals 4: 6494; Actuals 1: 8711; Actuals 2: 7652; Actuals 3: 6385; Actuals 4: 10348; Actuals 1: 6909; Actuals 2: 8396; Actuals 3: 8322; Actuals 4: 7193 | 30820 | 30820 | 30820 | Number of events
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 1; Actuals 3: 33; Actuals 4: 13; Actuals 1: 2; Actuals 2: 1; Actuals 3: 10; Actuals 4: 6; Actuals 1: 0; Actuals 2: 3; Actuals 3: 0; Actuals 4: 0 | 3 | 3 | 3 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 123; Actuals 2: 0; Actuals 3: 26; Actuals 4: 2; Actuals 1: 2; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 2 | 2 | 2 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 10; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 393; Actuals 2: 192; Actuals 3: 152; Actuals 4: 115; Actuals 1: 566; Actuals 2: 176; Actuals 3: 160; Actuals 4: 389; Actuals 1: 135; Actuals 2: 162; Actuals 3: 117; Actuals 4: 199 | 613 | 613 | 613 | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 2; Actuals 3: 81; Actuals 4: 12; Actuals 1: 1; Actuals 2: 3; Actuals 3: 6; Actuals 4: 3; Actuals 1: 0; Actuals 2: 1; Actuals 3: 0; Actuals 4: 0 | 1 | 1 | 1 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 211; Actuals 2: 0; Actuals 3: 12; Actuals 4: 0; Actuals 1: 4; Actuals 2: 0; Actuals 3: 0; Actuals 4: 1 | 5 | 5 | 5 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 6; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 766; Actuals 2: 211; Actuals 3: 146; Actuals 4: 159; Actuals 1: 633; Actuals 2: 131; Actuals 3: 99; Actuals 4: 365; Actuals 1: 161; Actuals 2: 161; Actuals 3: 99; Actuals 4: 229 | 650 | 650 | 650 | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 8; Actuals 3: 84; Actuals 4: 63; Actuals 1: 4; Actuals 2: 18; Actuals 3: 14; Actuals 4: 127; Actuals 1: 0; Actuals 2: 35; Actuals 3: 0; Actuals 4: 0 | 35 | 35 | 35 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 3; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 225; Actuals 2: 0; Actuals 3: 47; Actuals 4: 9; Actuals 1: 7; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 7 | 7 | 7 | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 14; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 500; Actuals 2: 405; Actuals 3: 362; Actuals 4: 310; Actuals 1: 885; Actuals 2: 349; Actuals 3: 304; Actuals 4: 2669; Actuals 1: 467; Actuals 2: 568; Actuals 3: 448; Actuals 4: 841 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 11; Actuals 3: 6; Actuals 4: 1 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 167; Actuals 3: 443; Actuals 4: 216 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 3; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 71; Actuals 3: 153; Actuals 4: 50 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 17; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 4; Actuals 2: 306; Actuals 3: 726; Actuals 4: 201 |  |  |  | Number of events | This program started in 2022 and, therefore, we are unable to provide data for the period 2020 to 2021. | Historical Data is not applicable as this program started in 2022. Additionally, the projection fields are blank as the team is evaluating projection options with limited data.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 4: 1790 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 4: 7309 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 4: 1787 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 4: 6225 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | Actuals 4: 1334 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | Actuals 4: 5582 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 4: 3192 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 4: 5818 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 4: 3679.5 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 4: 7716 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | Actuals 4: 3059 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for the period 2023 to 2025.
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | Actuals 4: 10520 |  |  |  | hours | We are unable to provide projections for the period 2023 to 2025. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. PG&E is unable to provide projections for 2023 - 2025
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 4: 182058 |  |  |  | Number of orders | This data is accurate for open work orders on trees as of 1/25/23. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 4: 513 |  |  |  | Number of orders | Please note, these numbers are based off at P1/P2 data. As of the data pull on 1/25/23, there are no P1 tags included in the past due work orders. | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 4: 678058 |  |  |  | Number of orders |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Number of orders |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Hours
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 4; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of fatalities | Number of fatalities per year.
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 3; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 2; Actuals 4: 0 |  |  |  | Number of injuries | Number of OSHA-reportable injuries per year.
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 368.2M; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 44.3M; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 206; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 1334; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 78; Actuals 4: 0 |  |  |  | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 16; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 1530; Actuals 3: 57738; Actuals 4: 10; Actuals 1: 742; Actuals 2: 446; Actuals 3: 967629; Actuals 4: 517; Actuals 1: 0; Actuals 2: 300; Actuals 3: 76848; Actuals 4: 42 |  |  |  | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 3; Actuals 3: 5; Actuals 4: 0; Actuals 1: 1; Actuals 2: 3; Actuals 3: 2; Actuals 4: 0; Actuals 1: 0; Actuals 2: 3; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 1; Actuals 2: 0; Actuals 3: 1; Actuals 4: 0; Actuals 1: 0; Actuals 2: 1; Actuals 3: 1; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 3; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | Actuals 1: 0; Actuals 2: 12; Actuals 3: 7; Actuals 4: 1; Actuals 1: 1; Actuals 2: 2; Actuals 3: 1; Actuals 4: 1; Actuals 1: 0; Actuals 2: 5; Actuals 3: 1; Actuals 4: 1 |  |  |  | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 248708; Actuals 2: 71890; Actuals 3: 31515; Actuals 4: 86; Actuals 1: 97044; Actuals 2: 193114; Actuals 3: 51978; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | We are unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 10616; Actuals 2: 179858; Actuals 3: 55763; Actuals 4: 3107; Actuals 1: 5449; Actuals 2: 118700; Actuals 3: 65654; Actuals 4: 367 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | We are unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 1: 9611.47; Actuals 2: 2778.23; Actuals 3: 1217.92; Actuals 4: 3.32; Actuals 1: 3750.32; Actuals 2: 7463.01; Actuals 3: 2008.72; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 1: 410.26; Actuals 2: 6950.72; Actuals 3: 2154.99; Actuals 4: 120.07; Actuals 1: 210.58; Actuals 2: 4587.23; Actuals 3: 2537.24; Actuals 4: 14.18 |  |  |  | # of circuit miles inspected by the utility | Other Inspections Type = Detailed Ground Inspections | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 14 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 527 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 20 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 157 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 3 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 2 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 10972; Actuals 2: 161321; Actuals 3: 28300; Actuals 4: 710; Actuals 1: 740; Actuals 2: 122872; Actuals 3: 81486; Actuals 4: 135 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 0; Actuals 2: 0; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 1: 424.02; Actuals 2: 6234.35; Actuals 3: 1093.67; Actuals 4: 27.44; Actuals 1: 28.6; Actuals 2: 4748.46; Actuals 3: 3149.08; Actuals 4: 5.22 |  |  |  | # of circuit miles inspected by the utility | Other Inspections Type = Detailed Ground Inspections | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. | bar: Actuals 4
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 676 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 3123 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 2 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 15 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 2 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 2 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 137222; Actuals 2: 185915; Actuals 3: 275676; Actuals 4: 375500; Actuals 1: 137039; Actuals 2: 154168; Actuals 3: 276387; Actuals 4: 367926 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 5851; Actuals 2: 84262; Actuals 3: 193727; Actuals 4: 139870; Actuals 1: 16469; Actuals 2: 135659; Actuals 3: 184726; Actuals 4: 67766 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 1: 4493.59; Actuals 2: 6088.13; Actuals 3: 9027.52; Actuals 4: 12296.44; Actuals 1: 4487.59; Actuals 2: 5048.51; Actuals 3: 9050.8; Actuals 4: 12048.41 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 1: 191.6; Actuals 2: 2759.31; Actuals 3: 6343.95; Actuals 4: 4580.3; Actuals 1: 539.31; Actuals 2: 4442.4; Actuals 3: 6049.19; Actuals 4: 2219.12 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 4: 58 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 676 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 3125 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 4: 17 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 1743 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 407 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 224 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for distribution inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 7 |  |  |  | # of findings from these asset inspections |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 16892; Actuals 2: 19602; Actuals 3: 108; Actuals 4: 0; Actuals 1: 5150; Actuals 2: 22694; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 260; Actuals 2: 10820; Actuals 3: 3368; Actuals 4: 57; Actuals 1: 6398; Actuals 2: 19057; Actuals 3: 1512; Actuals 4: 42 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 2115; Actuals 2: 11869; Actuals 3: 117; Actuals 4: 44; Actuals 1: 1457; Actuals 2: 25023; Actuals 3: 307; Actuals 4: 36 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 1: 135636.07; Actuals 2: 157396.3; Actuals 3: 867.2; Actuals 4: 0; Actuals 1: 41352.46; Actuals 2: 182223.83; Actuals 3: 0; Actuals 4: 0 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 1: 2087.7; Actuals 2: 86880.32; Actuals 3: 27043.71; Actuals 4: 457.69; Actuals 1: 51373.41; Actuals 2: 153020.16; Actuals 3: 12140.76; Actuals 4: 337.24 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 1: 16982.61; Actuals 2: 95303.37; Actuals 3: 939.46; Actuals 4: 353.3; Actuals 1: 11699.13; Actuals 2: 200924.78; Actuals 3: 2465.09; Actuals 4: 289.07 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections | bar: Actuals 4
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 6 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 4: 5 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 4: 28 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 107 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 30 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 4: 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 67 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 18 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 11657; Actuals 2: 12465; Actuals 3: 2816; Actuals 4: 2136; Actuals 1: 3087; Actuals 2: 17578; Actuals 3: 248; Actuals 4: 1457 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 206; Actuals 2: 9538; Actuals 3: 1794; Actuals 4: 29; Actuals 1: 1705; Actuals 2: 9275; Actuals 3: 479; Actuals 4: 6 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 3149; Actuals 2: 8300; Actuals 3: 140; Actuals 4: 0; Actuals 1: 1128; Actuals 2: 10163; Actuals 3: 71; Actuals 4: 2 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 1: 93601.09; Actuals 2: 100089.01; Actuals 3: 22611.37; Actuals 4: 17151.23; Actuals 1: 24787.39; Actuals 2: 141144.38; Actuals 3: 1991.34; Actuals 4: 11699.13 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 1: 1654.1; Actuals 2: 76586.36; Actuals 3: 14405.11; Actuals 4: 232.86; Actuals 1: 13690.47; Actuals 2: 74474.58; Actuals 3: 3846.18; Actuals 4: 48.18 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 1: 25285.22; Actuals 2: 66645.71; Actuals 3: 1124.14; Actuals 4: 0; Actuals 1: 9057.39; Actuals 2: 81604.87; Actuals 3: 570.1; Actuals 4: 16.06 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | [27 empty] | # of findings from these asset inspections | bar: Actuals 4
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 87 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 21 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 4: 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 11 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 7 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 2926; Actuals 2: 19670; Actuals 3: 27029; Actuals 4: 15376; Actuals 1: 21; Actuals 2: 11840; Actuals 3: 20066; Actuals 4: 29065 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 285; Actuals 2: 7411; Actuals 3: 21311; Actuals 4: 11566; Actuals 1: 1633; Actuals 2: 4245; Actuals 3: 11612; Actuals 4: 3058 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 3075; Actuals 2: 25007; Actuals 3: 6720; Actuals 4: 4373; Actuals 1: 1024; Actuals 2: 7307; Actuals 3: 9076; Actuals 4: 3073 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections | PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | [27 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 1: 24121.34; Actuals 2: 162155.39; Actuals 3: 222821.46; Actuals 4: 126756.55; Actuals 1: 173.12; Actuals 2: 97606.5; Actuals 3: 165419.93; Actuals 4: 239605.82 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 1: 2349.48; Actuals 2: 61094.74; Actuals 3: 175683.45; Actuals 4: 95347.7; Actuals 1: 13462.11; Actuals 2: 34994.9; Actuals 3: 95726.91; Actuals 4: 25209.52 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 1: 25349.66; Actuals 2: 206152.51; Actuals 3: 55398.28; Actuals 4: 36050.1; Actuals 1: 8441.64; Actuals 2: 60237.39; Actuals 3: 74820.66; Actuals 4: 25333.17 |  |  |  | # of circuit miles inspected by the utility |  | PG&E does not track inspection data by circuit mile. Circuit miles shown are estimated based as a fraction of total circuit mileage and are assumed proportional to the percentage of structures inspected for each inspection category. PG&E is unable to provide historical data prior to 2021 with this level of granularity.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | [27 empty] | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 5 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 5 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 35 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 23 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 39 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 1557 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 858 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 209 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 12 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 658 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 262 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 26 |  |  |  | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 14 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 531 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | Actuals 4: 6 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 2757 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 1227 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | Actuals 4: 135 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | Actuals 4: 26 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. | bar: Actuals 4
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 3 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 319 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | Actuals 4: 5 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 2227 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 723 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | Actuals 4: 126 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | Actuals 4: 46 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 677 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 3145 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 4: 73 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 3969 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 1866 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | Actuals 4: 2 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | Actuals 4: 551 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | Actuals 4: 39 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. | bar: Actuals 4
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 3 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 6 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 4: 36 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 4: 6940 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 5540 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 47 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | Actuals 4: 4 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | Actuals 4: 3659 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | Actuals 4: 1262 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | Actuals 4: 23 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. | bar: Actuals 4
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 3 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 4 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | Actuals 4: 15 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 4: 1722 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 1848 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 24 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | [27 empty] | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. | bar: Actuals 4
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | Actuals 4: 895 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | Actuals 4: 332 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | Actuals 4: 12 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 6 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 5 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 46 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 23 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 175 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 8340 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 5580 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 359 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | Actuals 4: 20 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | Actuals 4: 2891 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | Actuals 4: 1400 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | [27 empty] | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | Actuals 4: 58 |  |  |  | # of asset inspection findings which have been fixed |  | Data is currently missing in this submission, PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting.
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | Actuals 4: 376 | 483 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | Actuals 4: 40694 | 409746 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | Actuals 4: 710 | 3033 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | Actuals 4: 4051 | 21611 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | Actuals 4: 11 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | Actuals 4: 120 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | Actuals 4: 2940 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | Actuals 4: 267 | 505 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | Actuals 4: 26977 | 285188 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | Actuals 4: 314 | 772 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | Actuals 4: 10380 | 27200 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | Actuals 4: 71 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | Actuals 4: 2131 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | Actuals 4: 117 | 35 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | Actuals 4: 143437 | 717468 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | Actuals 4: 231 | 766 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | Actuals 4: 1180 | 7118 |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | Actuals 4: 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | Actuals 4: 54 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | Actuals 4: 6919 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. The majority of Distribution is inspected on ground patrols
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | Actuals 1: 5849910; Actuals 1: 5839506; Actuals 1: 5933330 | >5,500,000 | >5,500,000 | >5,500,000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | Actuals 1: 6077; Actuals 2: 12013; Actuals 3: 16842; Actuals 4: 3707; Actuals 1: 6433; Actuals 2: 16799; Actuals 3: 7166; Actuals 4: 3287; Actuals 1: 6703; Actuals 2: 10376; Actuals 3: 6623; Actuals 4: 131 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in Non HFTD
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | Actuals 1: 253757; Actuals 1: 239066; Actuals 1: 212536 | <225,000 | <225,000 | <225,000 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Please note that these numbers are based on the project year and not calendar year.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | Actuals 1: 9; Actuals 2: 57; Actuals 3: 115; Actuals 4: 26; Actuals 1: 9; Actuals 2: 23; Actuals 3: 55; Actuals 4: 9; Actuals 1: 8; Actuals 2: 2; Actuals 3: 15; Actuals 4: 3 | 3 | 3 | 3 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | Actuals 1: 2440491; Actuals 1: 2407120; Actuals 1: 2398660 | >2,100,000 | >2,100,000 | >2,100,000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | Actuals 1: 4149; Actuals 2: 6397; Actuals 3: 6041; Actuals 4: 1095; Actuals 1: 3124; Actuals 2: 9981; Actuals 3: 6195; Actuals 4: 2381; Actuals 1: 4179; Actuals 2: 5498; Actuals 3: 2108; Actuals 4: 136 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in Non HFTD
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | Actuals 1: 126832; Actuals 1: 117043; Actuals 1: 105687 | <110,000 | <110,000 | <110,000 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Please note that these numbers are based on the project year and not calendar year.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | Actuals 1: 5; Actuals 2: 5; Actuals 3: 57; Actuals 4: 3; Actuals 1: 9; Actuals 2: 2; Actuals 3: 21; Actuals 4: 0; Actuals 1: 2; Actuals 2: 1; Actuals 3: 15; Actuals 4: 3 | 3 | 3 | 3 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | [24 empty] | >11,000,000 | >11,000,000 | >11,000,000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | Actuals 1: 11502631; Actuals 1: 12015596; Actuals 1: 12014276 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | Actuals 1: 9676; Actuals 2: 12072; Actuals 3: 14975; Actuals 4: 3150; Actuals 1: 10332; Actuals 2: 15410; Actuals 3: 10379; Actuals 4: 6167; Actuals 1: 9943; Actuals 2: 11571; Actuals 3: 6932; Actuals 4: 938 | 64550 | 64550 | 64550 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | These are forecasted numbers for all HFTD tiers. We are unable to pull forecasted data by HFTD tier.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect by drone
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | We do not inspect Non-Routine for compliance
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | Actuals 1: 95595; Actuals 1: 88286; Actuals 1: 79336 | <80,000 | <80,000 | <80,000 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | Actuals 1: 33; Actuals 2: 13; Actuals 3: 86; Actuals 4: 17; Actuals 1: 5; Actuals 2: 8; Actuals 3: 16; Actuals 4: 19; Actuals 1: 7; Actuals 2: 1; Actuals 3: 18; Actuals 4: 3 | 3 | 3 | 3 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Percentage of customers notified of evacuation |  | PG&E does not issue wildfire evacuation notices to customers and does not maintain metrics on the number of customers in an evacuation zone or the number of customers notified of evacuation orders. Because of this, PG&E is unable to report on evacuation related requirements in this table. PG&E anticipates this to be a recurring challenge going forward.

## Table 3
Utility | Pacific Gas and Electric Company
Table No. | 3
Date Modified | 2023-02-01
[5 empty] | Actual | [7 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
Table 3: List and description of additional metrics |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning

## Table 4
Utility | Pacific Gas and Electric Company
Table No. | 4
Date Modified | 2023-02-01
Note: These columns are placeholders for future QR submissions.
Table 4: Weather patterns |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 38182.28; 3: 2774.88; 4: 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 8339.14; 3: 749.27; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 65952.69; 3: 199.87; 4: 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 289.03; 3: 0; 4: 1430.19 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 337.23; 3: 0; 4: 752.14 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 2.22; 3: 0; 4: 423.82 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 38471.31; 3: 2774.88; 4: 1430.19 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 8676.37; 3: 749.27; 4: 752.14 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 1: 0; 2: 65954.91; 3: 199.87; 4: 423.82 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 1: 3859.7; 2: 503899; 3: 1333407.9; 4: 395757 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 1: 1181.6; 2: 161044; 3: 482998; 4: 135880 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 1: 555.8; 2: 99862.5; 3: 282488.4; 4: 76714.6 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)
Comments for Table 4: Table 4 shows the trends of National Weather Service (NWS) issued Red Flag Warnings (RFWs) and High Wind Warnings (HWWs) over the past year impacting PG&E circuits across the territory through the metrics RFW Circuit Mile Days and HWW Circuit Mile Days. NWS RFWs are a proxy for high fire danger conditions, while HWWs are issued for solely high wind threats, regardless of humidity values and fire danger. These values have changed from previous reports, which calculated RFW Day Circuit miles based on Fire Index Areas. For these metrics, circuit miles are now calculated by the NWS RFW and HWW polygons to give a more accurate and precise values for RFW Circuit Mile Days and HWW Circuit Mile Days.

## Table 5
| Utility | Pacific Gas and Electric Company | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[8 empty] | Actual number of risk events | [15 empty] | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 11; Actual number of risk events Q3: 8; Actual number of risk events Q4: 5 | 27 | 27 | 27 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 16; Actual number of risk events Q2: 27; Actual number of risk events Q3: 22; Actual number of risk events Q4: 22 | 87 | 87 | 87 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 16; Actual number of risk events Q3: 3; Actual number of risk events Q4: 4 | 26 | 26 | 26 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 28; Actual number of risk events Q2: 30; Actual number of risk events Q3: 33; Actual number of risk events Q4: 38 | 129 | 129 | 129 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 5; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 6 | 6 | 6 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 58; Actual number of risk events Q2: 91; Actual number of risk events Q3: 79; Actual number of risk events Q4: 83 | 311 | 311 | 311 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 7; Actual number of risk events Q3: 3; Actual number of risk events Q4: 3 | 16 | 16 | 16 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 0 | 8 | 8 | 8 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | Non-HFTD |  | Actual number of risk events Q1: 16; Actual number of risk events Q2: 11; Actual number of risk events Q3: 10; Actual number of risk events Q4: 10 | 47 | 47 | 47 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 141; Actual number of risk events Q2: 191; Actual number of risk events Q3: 127; Actual number of risk events Q4: 283 | 742 | 742 | 742 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 28; Actual number of risk events Q2: 47; Actual number of risk events Q3: 36; Actual number of risk events Q4: 60 | 171 | 171 | 171 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 35; Actual number of risk events Q2: 48; Actual number of risk events Q3: 32; Actual number of risk events Q4: 80 | 195 | 195 | 195 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD |  | Actual number of risk events Q1: 176; Actual number of risk events Q2: 277; Actual number of risk events Q3: 235; Actual number of risk events Q4: 270 | 958 | 958 | 958 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 9; Actual number of risk events Q2: 28; Actual number of risk events Q3: 18; Actual number of risk events Q4: 18 | 73 | 73 | 73 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 10; Actual number of risk events Q2: 11; Actual number of risk events Q3: 15; Actual number of risk events Q4: 8 | 44 | 44 | 44 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 2; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 6; Actual number of risk events Q2: 10; Actual number of risk events Q3: 11; Actual number of risk events Q4: 4 | 31 | 31 | 31 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 3; Actual number of risk events Q4: 5 | 11 | 11 | 11 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 5; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD |  | Actual number of risk events Q1: 11; Actual number of risk events Q2: 28; Actual number of risk events Q3: 28; Actual number of risk events Q4: 15 | 82 | 82 | 82 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2 | 6 | 6 | 6 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 6 | 6 | 6 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 63; Actual number of risk events Q2: 170; Actual number of risk events Q3: 200; Actual number of risk events Q4: 113 | 546 | 546 | 546 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 5; Actual number of risk events Q3: 13; Actual number of risk events Q4: 4 | 26 | 26 | 26 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 6; Actual number of risk events Q4: 2 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 4; Actual number of risk events Q4: 2 | 7 | 7 | 7 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 12; Actual number of risk events Q4: 0 | 14 | 14 | 14 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 6; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 237; Actual number of risk events Q2: 517; Actual number of risk events Q3: 465; Actual number of risk events Q4: 349 | 1411.2 | 1411.2 | 1411.2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 31; Actual number of risk events Q2: 94; Actual number of risk events Q3: 111; Actual number of risk events Q4: 47 | 254.7 | 254.7 | 254.7 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 19; Actual number of risk events Q2: 28; Actual number of risk events Q3: 33; Actual number of risk events Q4: 22 | 91.8 | 91.8 | 91.8 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 6; Actual number of risk events Q2: 10; Actual number of risk events Q3: 13; Actual number of risk events Q4: 3 | 32 | 32 | 32 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 94; Actual number of risk events Q2: 183; Actual number of risk events Q3: 98; Actual number of risk events Q4: 68 | 443 | 443 | 443 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 4; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 373; Actual number of risk events Q2: 467; Actual number of risk events Q3: 517; Actual number of risk events Q4: 397 | 1754 | 1754 | 1754 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 17; Actual number of risk events Q2: 30; Actual number of risk events Q3: 28; Actual number of risk events Q4: 20 | 95 | 95 | 95 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 7; Actual number of risk events Q2: 17; Actual number of risk events Q3: 8; Actual number of risk events Q4: 13 | 45 | 45 | 45 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 18; Actual number of risk events Q2: 9; Actual number of risk events Q3: 17; Actual number of risk events Q4: 10 | 54 | 54 | 54 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 65; Actual number of risk events Q2: 89; Actual number of risk events Q3: 75; Actual number of risk events Q4: 65 | 294 | 294 | 294 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 17; Actual number of risk events Q3: 12; Actual number of risk events Q4: 6 | 38 | 38 | 38 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 5; Actual number of risk events Q2: 3; Actual number of risk events Q3: 4; Actual number of risk events Q4: 3 | 15 | 15 | 15 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 31; Actual number of risk events Q2: 49; Actual number of risk events Q3: 55; Actual number of risk events Q4: 24 | 159 | 159 | 159 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 5; Actual number of risk events Q3: 5; Actual number of risk events Q4: 3 | 17 | 17 | 17 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 10; Actual number of risk events Q3: 4; Actual number of risk events Q4: 2 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 397; Actual number of risk events Q2: 601; Actual number of risk events Q3: 431; Actual number of risk events Q4: 834 | 2263 | 2263 | 2263 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 111; Actual number of risk events Q2: 159; Actual number of risk events Q3: 112; Actual number of risk events Q4: 198 | 580 | 580 | 580 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 134; Actual number of risk events Q2: 162; Actual number of risk events Q3: 96; Actual number of risk events Q4: 228 | 620 | 620 | 620 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 7 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 4 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD |  | Actual number of risk events Q1: 5; Actual number of risk events Q2: 10; Actual number of risk events Q3: 15; Actual number of risk events Q4: 17 | 47 | 47 | 47 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | [17 empty] | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible | bar: Actual number of risk events Q1 to Actual number of risk events Q4
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD |  | Actual number of risk events Q1: 13; Actual number of risk events Q2: 17; Actual number of risk events Q3: 11; Actual number of risk events Q4: 11 | 52 | 52 | 52 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD |  | Actual number of risk events Q1: 247; Actual number of risk events Q2: 412; Actual number of risk events Q3: 468; Actual number of risk events Q4: 440 | 1567 | 1567 | 1567 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 19; Actual number of risk events Q2: 39; Actual number of risk events Q3: 25; Actual number of risk events Q4: 26 | 109 | 109 | 109 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 10; Actual number of risk events Q2: 16; Actual number of risk events Q3: 18; Actual number of risk events Q4: 13 | 57 | 57 | 57 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | [17 empty] | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible | bar: Actual number of risk events Q1 to Actual number of risk events Q4
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD |  | Actual number of risk events Q1: 32; Actual number of risk events Q2: 46; Actual number of risk events Q3: 39; Actual number of risk events Q4: 67 | 184 | 184 | 184 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 4; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD |  | Actual number of risk events Q1: 123; Actual number of risk events Q2: 221; Actual number of risk events Q3: 175; Actual number of risk events Q4: 158 | 677 | 677 | 677 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 19; Actual number of risk events Q2: 21; Actual number of risk events Q3: 23; Actual number of risk events Q4: 11 | 74 | 74 | 74 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 20; Actual number of risk events Q3: 7; Actual number of risk events Q4: 3 | 38 | 38 | 38 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD |  | Actual number of risk events Q1: 111; Actual number of risk events Q2: 181; Actual number of risk events Q3: 282; Actual number of risk events Q4: 229 | 803 | 803 | 803 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 13; Actual number of risk events Q2: 19; Actual number of risk events Q3: 24; Actual number of risk events Q4: 16 | 72 | 72 | 72 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 14; Actual number of risk events Q2: 5; Actual number of risk events Q3: 18; Actual number of risk events Q4: 12 | 49 | 49 | 49 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD |  | Actual number of risk events Q1: 63; Actual number of risk events Q2: 87; Actual number of risk events Q3: 80; Actual number of risk events Q4: 92 | 322 | 322 | 322 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 14; Actual number of risk events Q3: 13; Actual number of risk events Q4: 12 | 47 | 47 | 47 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 5; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2 | 14 | 14 | 14 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD |  | Actual number of risk events Q1: 41; Actual number of risk events Q2: 65; Actual number of risk events Q3: 50; Actual number of risk events Q4: 68 | 224 | 224 | 224 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 23; Actual number of risk events Q3: 8; Actual number of risk events Q4: 11 | 50 | 50 | 50 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 12; Actual number of risk events Q2: 13; Actual number of risk events Q3: 5; Actual number of risk events Q4: 4 | 34 | 34 | 34 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 4; Actual number of risk events Q3: 6; Actual number of risk events Q4: 2 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrestor | Distribution | Non-HFTD |  | Actual number of risk events Q1: 19; Actual number of risk events Q2: 18; Actual number of risk events Q3: 26; Actual number of risk events Q4: 47 | 110 | 110 | 110 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 13 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 6 | 14 | 14 | 14 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrestor | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 8; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 8 | 8 | 8 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD |  | Actual number of risk events Q1: 136; Actual number of risk events Q2: 213; Actual number of risk events Q3: 191; Actual number of risk events Q4: 407 | 947 | 947 | 947 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 21; Actual number of risk events Q2: 46; Actual number of risk events Q3: 56; Actual number of risk events Q4: 47 | 170 | 170 | 170 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 18; Actual number of risk events Q2: 14; Actual number of risk events Q3: 18; Actual number of risk events Q4: 26 | 76 | 76 | 76 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 4; Actual number of risk events Q3: 2; Actual number of risk events Q4: 2 | 15 | 15 | 15 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD |  | Actual number of risk events Q1: 15; Actual number of risk events Q2: 13; Actual number of risk events Q3: 21; Actual number of risk events Q4: 31 | 80 | 80 | 80 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 8; Actual number of risk events Q3: 4; Actual number of risk events Q4: 7 | 21 | 21 | 21 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 10 | 13 | 13 | 13 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2 | 4 | 4 | 4 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD |  | Actual number of risk events Q1: 137; Actual number of risk events Q2: 218; Actual number of risk events Q3: 203; Actual number of risk events Q4: 165 | 723 | 723 | 723 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 13; Actual number of risk events Q2: 18; Actual number of risk events Q3: 15; Actual number of risk events Q4: 20 | 66 | 66 | 66 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 10; Actual number of risk events Q2: 7; Actual number of risk events Q3: 5; Actual number of risk events Q4: 4 | 26 | 26 | 26 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD |  | Actual number of risk events Q1: 30; Actual number of risk events Q2: 56; Actual number of risk events Q3: 57; Actual number of risk events Q4: 56 | 199 | 199 | 199 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 4 | 6 | 6 | 6 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 625; Actual number of risk events Q2: 1059; Actual number of risk events Q3: 1459; Actual number of risk events Q4: 745 | 3888 | 3888 | 3888 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 75; Actual number of risk events Q2: 122; Actual number of risk events Q3: 140; Actual number of risk events Q4: 93 | 430 | 430 | 430 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 36; Actual number of risk events Q2: 56; Actual number of risk events Q3: 61; Actual number of risk events Q4: 26 | 179 | 179 | 179 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD |  | Actual number of risk events Q1: 9; Actual number of risk events Q2: 12; Actual number of risk events Q3: 23; Actual number of risk events Q4: 12 | 56 | 56 | 56 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 6; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 12 | 12 | 12 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 17; Actual number of risk events Q2: 39; Actual number of risk events Q3: 30; Actual number of risk events Q4: 22 | 108 | 108 | 108 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 4; Actual number of risk events Q3: 2; Actual number of risk events Q4: 5 | 15 | 15 | 15 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 3; Actual number of risk events Q4: 1 | 6 | 6 | 6 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 27 | 34 | 34 | 34 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1627; Actual number of risk events Q2: 2193; Actual number of risk events Q3: 1865; Actual number of risk events Q4: 2156 | 7605.77 | 7605.77 | 7605.77 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 289; Actual number of risk events Q2: 377; Actual number of risk events Q3: 338; Actual number of risk events Q4: 402 | 1363.82 | 1363.82 | 1363.82 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 123; Actual number of risk events Q2: 169; Actual number of risk events Q3: 105; Actual number of risk events Q4: 182 | 561.63 | 561.63 | 561.63 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 11; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 17 | 17 | 17 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD |  | Actual number of risk events Q1: 16; Actual number of risk events Q2: 28; Actual number of risk events Q3: 23; Actual number of risk events Q4: 19 | 86 | 86 | 86 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 3; Actual number of risk events Q4: 7 | 11 | 11 | 11 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD |  | Actual number of risk events Q1: 35; Actual number of risk events Q2: 86; Actual number of risk events Q3: 20; Actual number of risk events Q4: 17 | 158 | 158 | 158 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 5; Actual number of risk events Q3: 3; Actual number of risk events Q4: 11 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 2; Actual number of risk events Q3: 5; Actual number of risk events Q4: 2 | 11 | 11 | 11 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 25; Actual number of risk events Q3: 2; Actual number of risk events Q4: 3 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 10; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2 | 10 | 10 | 10 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 2 | 2 | 2 | 2 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 3; Actual number of risk events Q3: 6; Actual number of risk events Q4: 8 | 20 | 20 | 20 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 5; Actual number of risk events Q4: 4 | 11 | 11 | 11 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 8 | 8 | 8 | 8 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 42 | 47.46 | 47.46 | 47.46 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3 | 3.39 | 3.39 | 3.39 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 1.13 | 1.13 | 1.13 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD |  | Actual number of risk events Q1: 27; Actual number of risk events Q2: 43; Actual number of risk events Q3: 40; Actual number of risk events Q4: 55 | 165 | 165 | 165 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 12; Actual number of risk events Q2: 24; Actual number of risk events Q3: 5; Actual number of risk events Q4: 9 | 50 | 50 | 50 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 10; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 16 | 16 | 16 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 2251; Actual number of risk events Q2: 3217; Actual number of risk events Q3: 2629; Actual number of risk events Q4: 2864 | 10632.17 | 10632.17 | 10632.17 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 291; Actual number of risk events Q2: 358; Actual number of risk events Q3: 316; Actual number of risk events Q4: 405 | 1328.9 | 1328.9 | 1328.9 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 114; Actual number of risk events Q2: 155; Actual number of risk events Q3: 129; Actual number of risk events Q4: 160 | 541.26 | 541.26 | 541.26 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 21; Actual number of risk events Q2: 30; Actual number of risk events Q3: 18; Actual number of risk events Q4: 21 | 90 | 90 | 90 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 3; Actual number of risk events Q3: 2; Actual number of risk events Q4: 13 | 26 | 26 | 26 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 12; Actual number of risk events Q3: 0; Actual number of risk events Q4: 3 | 18 | 18 | 18 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 21; Actual number of risk events Q2: 25; Actual number of risk events Q3: 20; Actual number of risk events Q4: 80 | 80 | 80 | 80 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 6; Actual number of risk events Q2: 6; Actual number of risk events Q3: 9; Actual number of risk events Q4: 49 | 60 | 60 | 60 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 8; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 3 | 14 | 14 | 14 | # risk events (excluding ignitions) |  | For column H, we are working on gathering this information and will provide this information to the extent possible
Comments for Table 5 Risk Event Drivers (Distribution System): To the extent available, PG&E’s Integrated Logging Information System – Operations Data Base (ILIS-ODB) was used to provide the level of detail contained in Table 7.1 (Distribution) that includes both sustained and momentary outages experienced on our distribution system. When reviewing this data, the following should be noted: Based on PG&E’s standard definition, a distribution wire down event results in a reportable outage event and occurs when a normally energized electric primary distribution conductor is broken, or stays intact, and falls from its intended position to rest on the ground or a foreign object. PG&E used this standard definition in this year’s report and thus it does not include any secondary related wire down events. However, it should also be noted that any primary or secondary wire down condition that resulted in an outage event is also reported in the distribution outage results. Due to their relatively small contribution, the Commission does not require transformer-only outages be reported in the annual electric system reliability metrics. However, transformer-only outages are reported within PG&E’s Field Automation System (FAS) and most were also reported in PG&E’s ILIS-ODB outage data base. PG&E is including these transformer-only outages in the WMP reporting to reflect the full picture of outage incidents which could have represented ignition potential. PG&E also further enhanced our reporting process/controls in September 2020 to ensure future transformer-only outages are fully reported in our ILIS-ODB outage data base and is working to improve outage cause reporting. In Table 5 (Distribution), columns under the category ‘Projected risk events’ depict the projections in the respective years. Projections are based off analysis of trends on data from 2017-2022 Comments for Table 5 Risk Event Drivers (Transmission System): PG&E’s Transmission Operations Tracking & Logging (TOTL) application was used as the primary data source for Table 5 (Transmission) which includes unplanned outages experienced on the transmission (i.e., >50 kV) system. Unplanned outages include those due to an “automatic” operation (i.e., the transmission line relayed automatically by a protective device (typically a circuit breaker) and either automatically tested OK, tested no good, or was set up not to test (e.g., automatics disabled or cut out for wildfire risk mitigation)). Unplanned outages also include those where the line was manually removed from service by Operations on an “emergency” basis, usually to repair or replace an imminent failure of an asset. Such emergency forced outages (EFOs) are taken without securing approval from the California Independent System Operator (CAISO). Planned or “scheduled” outages are not included. Scheduled outages differ from EFOs in that PG&E garnered CAISO approval prior to the line being removed from service. Based on PG&E’s standard definition, a transmission wire down event (similar to distribution) results in a reportable outage event (note: customers may or may not have been de-energized) and occurs when a normally energized electric transmission conductor fails in service and falls from its intended position to rest on the ground or a foreign object. In Table 5 (Transmission), columns under the category ‘Projected risk events’ depict the projections in the respective years. Projections are based off analysis of trends on data from 2017-2022

## Table 6
| Utility | Pacific Gas and Electric Company | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2023-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[7 empty] | Actual number of ignitions | [15 empty] | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 11; Actual number of ignitions Q3: 17; Actual number of ignitions Q4: 5 | 34 | 34 | 34 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 5; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 6.8747 | 6.7076 | 6.5406 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 2; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 3 | 3 | 3 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 2; Actual number of ignitions Q2: 9; Actual number of ignitions Q3: 5; Actual number of ignitions Q4: 4 | 20 | 20 | 20 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 2 | 2 | 2 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 4; Actual number of ignitions Q2: 16; Actual number of ignitions Q3: 11; Actual number of ignitions Q4: 5 | 36 | 36 | 36 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 2; Actual number of ignitions Q3: 3; Actual number of ignitions Q4: 0 | 6 | 6 | 6 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 1 | 2 | 2 | 2 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 7; Actual number of ignitions Q2: 8; Actual number of ignitions Q3: 7; Actual number of ignitions Q4: 1 | 23 | 23 | 23 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 4; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 4.9105 | 4.7912 | 4.6719 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 27; Actual number of ignitions Q3: 24; Actual number of ignitions Q4: 5 | 57 | 57 | 57 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 3; Actual number of ignitions Q2: 8; Actual number of ignitions Q3: 11; Actual number of ignitions Q4: 4 | 25.5346 | 24.9141 | 24.2937 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 2; Actual number of ignitions Q2: 9; Actual number of ignitions Q3: 5; Actual number of ignitions Q4: 1 | 16.6957 | 16.29 | 15.8844 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment/facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 2; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 2 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 2; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 4; Actual number of ignitions Q4: 2 | 9 | 9 | 9 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 4; Actual number of ignitions Q2: 12; Actual number of ignitions Q3: 22; Actual number of ignitions Q4: 5 | 43 | 43 | 43 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0 | 2.9463 | 2.8747 | 2.8031 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 13; Actual number of ignitions Q3: 13; Actual number of ignitions Q4: 3 | 30 | 30 | 30 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 1 | 2.9463 | 2.8747 | 2.8031 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 1 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 3; Actual number of ignitions Q3: 4; Actual number of ignitions Q4: 1 | 8 | 8 | 8 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and brushing | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0 | 3 | 3 | 3 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and brushing | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and brushing | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and brushing | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and brushing | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and brushing | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 2; Actual number of ignitions Q3: 3; Actual number of ignitions Q4: 1 | 6 | 6 | 6 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 8; Actual number of ignitions Q4: 0 | 8 | 8 | 8 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 1 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 5; Actual number of ignitions Q3: 6; Actual number of ignitions Q4: 1 | 13 | 13 | 13 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 2; Actual number of ignitions Q2: 6; Actual number of ignitions Q3: 9; Actual number of ignitions Q4: 3 | 20 | 20 | 20 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 3; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0 | 4.9105 | 4.7912 | 4.6719 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 3; Actual number of ignitions Q4: 0 | 3.9284 | 3.8329 | 3.7375 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 3; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 2 | 7 | 7 | 7 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 3; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 3 | 8 | 8 | 8 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 1.9642 | 1.9165 | 1.8687 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | No | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We don't track this data.
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0 | 2 | 2 | 2 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0 | 2 | 2 | 2 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 1 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions |  | We are working on gathering this information and will provide this information to the extent possible
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 3; Actual number of ignitions Q2: 20; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 28 | 28 | 28 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1.9642 | 1.9165 | 1.8687 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0.9821 | 0.95823 | 0.93437 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
Comments for Table 6: The fire ignition data provided in this table is based on fire incident reports filed with the CPUC annually in accordance with D.14-02-015. The ignition data provided in these tables was pulled from PG&E’s systems in January 2023 and reflects preliminary data for two reasons: first, PG&E’s final 2022 fire ignition report is due on April 1, 2023 and 2022 data will be further reviewed in advance of that filing. The System HFTD Tier metric is the sum of Non HFTD, HFTD Zone 1, HFTD Tier 2, and HFTD Tier 3. 2023 HFTD Distribution: Values show decreases as compared to 2022 HFTD distribution based on preliminary undergrounding modelling forecast.

## Table 7
| Utility | Pacific Gas and Electric Company
| Table No. | 7
| Date Modified | 2023-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 4348.5699; Actual Q2: 4345.3411; Actual Q3: 4631.3445; Actual Q4: 4628.6061 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 9716.6576; Actual Q2: 9715.6693; Actual Q3: 9428.8116; Actual Q4: 9427.7867 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 6957.1301; Actual Q2: 6954.6518; Actual Q3: 7029.7223; Actual Q4: 7025.8764 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 29022.6951; Actual Q2: 29025.4167; Actual Q3: 28947.5391; Actual Q4: 28936.0333 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 426.5629; Actual Q2: 424.3796; Actual Q3: 421.7475; Actual Q4: 421.3767 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 4852.2035; Actual Q2: 4853.0973; Actual Q3: 4858.1717; Actual Q4: 4859.0601 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 647.0469; Actual Q2: 646.9476; Actual Q3: 683.6973; Actual Q4: 683.2701 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 157.7631; Actual Q2: 156.3281; Actual Q3: 119.1924; Actual Q4: 118.5082 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 8693.1045; Actual Q2: 8692.5594; Actual Q3: 8638.5246; Actual Q4: 8623.0156 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 5374.1373; Actual Q2: 5369.9503; Actual Q3: 5417.8917; Actual Q4: 5411.1054 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 888.9491; Actual Q2: 882.6836; Actual Q3: 799.9587; Actual Q4: 797.8877 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 2360.5897; Actual Q2: 2341.8904; Actual Q3: 2415.2306; Actual Q4: 2404.0742 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 271.6586; Actual Q2: 270.8524; Actual Q3: 272.356; Actual Q4: 271.9752 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 35.7873; Actual Q2: 35.7585; Actual Q3: 33.5971; Actual Q4: 33.3088 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 4297.583; Actual Q2: 4282.2151; Actual Q3: 4207.4348; Actual Q4: 4187.6568 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 1662.7455; Actual Q2: 1653.3888; Actual Q3: 1720.2677; Actual Q4: 1707.5367 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 333.3048; Actual Q2: 332.1065; Actual Q3: 330.4929; Actual Q4: 329.3895 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 352.9192; Actual Q2: 350.5431; Actual Q3: 351.5567; Actual Q4: 343.7054 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 532.9372; Actual Q2: 534.6115; Actual Q3: 585.2357; Actual Q4: 588.3099 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 1654.3772; Actual Q2: 1653.3822; Actual Q3: 1593.5476; Actual Q4: 1594.5712 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 887.7087; Actual Q2: 887.7578; Actual Q3: 880.5545; Actual Q4: 882.4176 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 7928.1657; Actual Q2: 7927.0245; Actual Q3: 7949.1786; Actual Q4: 7952.5809 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 45.105; Actual Q2: 45.105; Actual Q3: 45.8319; Actual Q4: 45.8319 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 1541.7771; Actual Q2: 1541.7829; Actual Q3: 1541.0559; Actual Q4: 1541.0439 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 85.2227; Actual Q2: 86.0816; Actual Q3: 96.3273; Actual Q4: 99.8541 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 133.7272; Actual Q2: 134.3674; Actual Q3: 115.2935; Actual Q4: 119.926 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 835.8007; Actual Q2: 836.5236; Actual Q3: 858.8134; Actual Q4: 862.0742 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 2084.0941; Actual Q2: 2084.1624; Actual Q3: 2056.7798; Actual Q4: 2067.8761 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 79.0616; Actual Q2: 77.8902; Actual Q3: 72.8263; Actual Q4: 72.8263 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 1010.0679; Actual Q2: 999.3293; Actual Q3: 996.3023; Actual Q4: 996.3023 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 32.1786; Actual Q2: 32.1786; Actual Q3: 35.0025; Actual Q4: 35.0025 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 25.9505; Actual Q2: 25.9811; Actual Q3: 23.1582; Actual Q4: 23.1582 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 293.3891; Actual Q2: 293.3521; Actual Q3: 305.6531; Actual Q4: 305.6539 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 771.8024; Actual Q2: 769.9943; Actual Q3: 757.9361; Actual Q4: 757.9541 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 22.8332; Actual Q2: 22.8332; Actual Q3: 27.036; Actual Q4: 27.036 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 1. Overhead circuit miles | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 145.6196; Actual Q2: 145.6182; Actual Q3: 138.4021; Actual Q4: 138.4021 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 5796.4058; Actual Q2: 5807.8832; Actual Q3: 6458.6199; Actual Q4: 6474.3866 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 12680.6917; Actual Q2: 12706.4541; Actual Q3: 12079.1919; Actual Q4: 12097.9196 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 2486.9413; Actual Q2: 2496.8179; Actual Q3: 2733.4712; Actual Q4: 2743.782 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 3539.8856; Actual Q2: 3563.7755; Actual Q3: 3364.1547; Actual Q4: 3382.5812 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 53.6397; Actual Q2: 53.8587; Actual Q3: 57.3393; Actual Q4: 57.8976 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 154.1344; Actual Q2: 158.2163; Actual Q3: 156.421; Actual Q4: 157.7913 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 296.0595; Actual Q2: 296.2649; Actual Q3: 333.2007; Actual Q4: 333.5923 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 74.586; Actual Q2: 76.1494; Actual Q3: 39.9902; Actual Q4: 42.7733 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 997.8451; Actual Q2: 1000.4192; Actual Q3: 1035.0633; Actual Q4: 1057.1284 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 453.4979; Actual Q2: 454.9782; Actual Q3: 431.0027; Actual Q4: 441.6947 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 63.7808; Actual Q2: 63.788; Actual Q3: 64.2903; Actual Q4: 64.8714 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 135.8752; Actual Q2: 136.0232; Actual Q3: 136.4735; Actual Q4: 139.9058 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 111.1707; Actual Q2: 113.4251; Actual Q3: 115.5915; Actual Q4: 115.8151 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 8.5977; Actual Q2: 8.6831; Actual Q3: 7.7935; Actual Q4: 7.7861 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 460.4259; Actual Q2: 480.7232; Actual Q3: 482.618; Actual Q4: 503.4972 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 152.0049; Actual Q2: 160.7969; Actual Q3: 168.4299; Actual Q4: 175.9107 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 20.2613; Actual Q2: 20.1679; Actual Q3: 20.3196; Actual Q4: 20.5408 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 30.715; Actual Q2: 31.373; Actual Q3: 31.2229; Actual Q4: 31.9197 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 20.8916; Actual Q2: 20.8916; Actual Q3: 10.8741; Actual Q4: 10.8746 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 102.3832; Actual Q2: 102.3832; Actual Q3: 36.3202; Actual Q4: 36.3202 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 8.1396; Actual Q2: 8.1396; Actual Q3: 23.3964; Actual Q4: 23.3964 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 39.0546; Actual Q2: 39.0546; Actual Q3: 99.8783; Actual Q4: 99.8783 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 1.3204; Actual Q2: 1.3204; Actual Q3: 1.1211; Actual Q4: 1.1211 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0.48189; Actual Q2: 0.48189; Actual Q3: 7.8594; Actual Q4: 7.8594 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0.49677; Actual Q2: 0.49677; Actual Q3: 1.6534; Actual Q4: 1.6534 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 8.4837; Actual Q2: 8.4837; Actual Q3: 0.14894; Actual Q4: 0.14894 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0.548; Actual Q2: 0.548; Actual Q3: 0.58353; Actual Q4: 0.58353 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0.38604; Actual Q2: 0.38604; Actual Q3: 0.35051; Actual Q4: 0.35051 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 2. Underground circuit miles | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 14202; Actual Q2: 14194; Actual Q3: 15368; Actual Q4: 15539 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 38262; Actual Q2: 38251; Actual Q3: 37015; Actual Q4: 37488 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 7062; Actual Q2: 7059; Actual Q3: 7354; Actual Q4: 7423 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 12783; Actual Q2: 12765; Actual Q3: 12442; Actual Q4: 12596 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 231; Actual Q2: 229; Actual Q3: 240; Actual Q4: 241 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 804; Actual Q2: 804; Actual Q3: 793; Actual Q4: 796 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 1052; Actual Q2: 1052; Actual Q3: 1137; Actual Q4: 1141 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 306; Actual Q2: 305; Actual Q3: 217; Actual Q4: 221 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 3534; Actual Q2: 3530; Actual Q3: 3565; Actual Q4: 3578 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 1708; Actual Q2: 1707; Actual Q3: 1663; Actual Q4: 1690 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 365; Actual Q2: 362; Actual Q3: 355; Actual Q4: 352 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 469; Actual Q2: 467; Actual Q3: 472; Actual Q4: 473 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 422; Actual Q2: 421; Actual Q3: 427; Actual Q4: 426 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 61; Actual Q2: 61; Actual Q3: 56; Actual Q4: 56 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 1926; Actual Q2: 1929; Actual Q3: 1953; Actual Q4: 1960 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 726; Actual Q2: 720; Actual Q3: 697; Actual Q4: 697 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 210; Actual Q2: 209; Actual Q3: 212; Actual Q4: 213 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 3. Critical facilities | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 113; Actual Q2: 114; Actual Q3: 110; Actual Q4: 110 |  |  |  | Number of critical facilities |  | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 1228424 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 2546192 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 403265 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 312685 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 10408 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 10820 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 72042 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 3444 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 195912 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 27026 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 17101 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 8508 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 27234 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 1868 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 105782 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 9687 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 9558 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 4. Residential customers | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 1602 |  |  |  | Number of residential customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 107089 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 322682 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 60055 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 165601 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 1990 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 12653 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 3952 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 750 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 19648 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 10370 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 1921 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 3174 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 1717 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 200 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 8774 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 3252 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 786 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 5. Commercial customers | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 503 |  |  |  | Number of commercial customers | Unable to provide data for previous quarters due to system limitation of PG&E's GIS Real Time Database | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 57130; Actual Q2: 57517; Actual Q3: 62046; Actual Q4: 342839 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 116384; Actual Q2: 116958; Actual Q3: 115578; Actual Q4: 868502 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 23983; Actual Q2: 24103; Actual Q3: 25519; Actual Q4: 113761 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 19689; Actual Q2: 19819; Actual Q3: 19353; Actual Q4: 119491 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 472; Actual Q2: 472; Actual Q3: 516; Actual Q4: 3083 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 502; Actual Q2: 504; Actual Q3: 494; Actual Q4: 3324 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 3370; Actual Q2: 3389; Actual Q3: 3716; Actual Q4: 13473 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 387; Actual Q2: 386; Actual Q3: 167; Actual Q4: 634 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 14192; Actual Q2: 14307; Actual Q3: 14779; Actual Q4: 57174 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 1519; Actual Q2: 1539; Actual Q3: 1479; Actual Q4: 6113 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 955; Actual Q2: 944; Actual Q3: 942; Actual Q4: 4747 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 337; Actual Q2: 341; Actual Q3: 368; Actual Q4: 1995 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 1276; Actual Q2: 1303; Actual Q3: 1337; Actual Q4: 4563 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 90; Actual Q2: 91; Actual Q3: 89; Actual Q4: 399 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 7115; Actual Q2: 7171; Actual Q3: 7333; Actual Q4: 28288 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 394; Actual Q2: 400; Actual Q3: 456; Actual Q4: 2002 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 334; Actual Q2: 335; Actual Q3: 351; Actual Q4: 1906 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 6. AFN customers | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 70; Actual Q2: 72; Actual Q3: 73; Actual Q4: 348 |  |  |  | Number of customers belonging to access and functional needs populations | AFN Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Previous quarter's data were carried over from the previous QDR submissions. | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 87; Actual Q2: 87; Actual Q3: 98; Actual Q4: 87 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 216; Actual Q2: 216; Actual Q3: 205; Actual Q4: 216 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 67; Actual Q2: 67; Actual Q3: 69; Actual Q4: 67 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 305; Actual Q2: 305; Actual Q3: 303; Actual Q4: 305 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 6; Actual Q4: 4 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 61; Actual Q2: 61; Actual Q3: 59; Actual Q4: 61 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 11; Actual Q2: 11; Actual Q3: 12; Actual Q4: 11 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 5; Actual Q2: 5; Actual Q3: 4; Actual Q4: 5 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 35; Actual Q2: 35; Actual Q3: 35; Actual Q4: 34 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 64; Actual Q2: 64; Actual Q3: 64; Actual Q4: 65 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 17; Actual Q2: 17; Actual Q3: 15; Actual Q4: 17 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 54; Actual Q2: 54; Actual Q3: 56; Actual Q4: 52 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 18; Actual Q2: 18; Actual Q3: 22; Actual Q4: 18 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 28; Actual Q2: 28; Actual Q3: 24; Actual Q4: 28 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 4; Actual Q2: 4; Actual Q3: 5; Actual Q4: 4 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 7. Substations | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 16; Actual Q2: 16; Actual Q3: 15; Actual Q4: 17 |  |  |  | Number of substations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 15; Actual Q2: 18; Actual Q3: 18; Actual Q4: 20 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 7; Actual Q2: 8; Actual Q3: 11; Actual Q4: 20 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 57; Actual Q2: 58; Actual Q3: 64; Actual Q4: 61 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 141; Actual Q2: 136; Actual Q3: 139; Actual Q4: 150 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 7; Actual Q2: 9; Actual Q3: 8; Actual Q4: 10 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 43; Actual Q2: 49; Actual Q3: 53; Actual Q4: 53 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 10; Actual Q2: 9; Actual Q3: 9; Actual Q4: 9 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 8; Actual Q2: 7; Actual Q3: 7; Actual Q4: 7 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 174; Actual Q2: 179; Actual Q3: 180; Actual Q4: 182 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 355; Actual Q2: 339; Actual Q3: 354; Actual Q4: 355 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 31; Actual Q2: 31; Actual Q3: 30; Actual Q4: 33 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 177; Actual Q2: 203; Actual Q3: 228; Actual Q4: 221 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 6; Actual Q2: 7; Actual Q3: 7; Actual Q4: 7 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 3; Actual Q2: 4; Actual Q3: 2; Actual Q4: 5 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 114; Actual Q2: 113; Actual Q3: 111; Actual Q4: 115 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 139; Actual Q2: 136; Actual Q3: 147; Actual Q4: 138 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 13; Actual Q2: 12; Actual Q3: 12; Actual Q4: 12 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
| 8. Weather stations | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 23; Actual Q2: 30; Actual Q3: 33; Actual Q4: 34 |  |  |  | Number of weather stations |  | We are working on gathering this information and will provide this information to the extent possible
Updated comments for Table 7 (2/1/2023): AFN Data in Q4 2022 onward has been adjusted to reflect the AFN definition as stated in the 2022 WMP. Residental and Commerical Customer data has been provided starting with out Q4 2022 submsision. PG&E’s GIS system is a dynamic ‘real-time’ system that reflects the current assets in PG&E’s service territory, hence data will continue to change as our system evolves. Projected Data are missing inthis submission. PG&E plans to continue to work on providing this level of detail in future quarterly submissions as we enhance our backend reporting. Updated comments for Table 7 (11/1/2022): Updated WUI Dataset that was released in Sept 2022 for data as of 2020 provided by the University of Wisconsin-Madison SILVIS Lab, available here: http://silvis.forest.wisc.edu/data/wui-change/ and https://www.fs.usda.gov/rds/archive/catalog/RDS-2015-0012-3 Updated comments for Table 7 (5/2/2022): Please note that we added Undergrounding mileage starting with our Q1 2022 submission. PG&E is using 2020 Census data and which has impacted the Urban, Rural and Highly Rural layers starting with our Q1 2022 submission. Comments for Table 7: Table 7 seeks information regarding the current baseline state of HFTD and non-HFTD service territory, as located in urban versus rural versus highly rural areas, including a subset with the Wildland-Urban Interface (WUI). The WUI is defined as areas where homes are built near or among lands prone to wildland fires. PG&E identifies WUI areas within PG&E’s service territory based upon data provided by the University of Wisconsin-Madison SILVIS Lab, available here: http://silvis.forest.wisc.edu/data/wui-change/, shows the WUI areas within California as of 2020. Customers belonging to AFN (Access and Functional Needs) population dataset is based on Medical Baseline Customers only and does not reflect the revision of AFN definition in the 2022 WMP for data prior to Q3 2022. This is due to the system limitation of the data within the various systems that are not currently connected to the enterprise GIS database. Data in Q4 2022 onward has been adusted to reflect the AFN definition as stated in the 2022 WMP. Substation count includes facility type: Distribution Switching station, Junction, Power House, Power Plant, Substation & Transmission Switching Station. PG&E’s GIS system is a dynamic ‘real-time’ system that reflects the current assets in PG&E’s service territory, hence data will continue to change as our system evolves.

## Table 8
| Utility | Pacific Gas & Electric |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2023-02-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | [15 empty] | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 77.7539; Actual Q2: 216.7905; Actual Q3: 362.8445; Actual Q4: 364.3071 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: -122.7144; Actual Q2: 310.7988; Actual Q3: -402.6884; Actual Q4: -398.1833 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: -54.2679; Actual Q2: -136.4592; Actual Q3: 18.2223; Actual Q4: 15.4164 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 294.3551; Actual Q2: -152.1228; Actual Q3: 218.0391; Actual Q4: 208.1333 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: -31.7962; Actual Q2: -100.6808; Actual Q3: -38.6525; Actual Q4: -38.9735 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: -208.4805; Actual Q2: -191.771; Actual Q3: -203.7283; Actual Q4: -201.6449 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: -18.1806; Actual Q2: 4.8202; Actual Q3: 17.9973; Actual Q4: 17.5283 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: -12.8572; Actual Q2: 11.0539; Actual Q3: -50.4076; Actual Q4: -51.2465 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: -21.2125; Actual Q2: 34.6079; Actual Q3: -72.4754; Actual Q4: -85.7584 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -252.1787; Actual Q2: 16.0334; Actual Q3: -189.5083; Actual Q4: -193.0276 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 27.2217; Actual Q2: -54.1224; Actual Q3: -58.4413; Actual Q4: -60.0349 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 244.0487; Actual Q2: -46.8645; Actual Q3: 302.9306; Actual Q4: 291.7032 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: -8.2618; Actual Q2: -17.8923; Actual Q3: -5.344; Actual Q4: -5.5396 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: -2.5126; Actual Q2: -1.8301; Actual Q3: -4.5029; Actual Q4: -4.8021 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: -101.588; Actual Q2: -58.4767; Actual Q3: -187.0652; Actual Q4: -191.1782 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: -84.1945; Actual Q2: -22.7458; Actual Q3: -16.4323; Actual Q4: -22.5273 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 83.1338; Actual Q2: 36.7417; Actual Q3: 79.8929; Actual Q4: 79.4229 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 64.5528; Actual Q2: 1.1892; Actual Q3: 64.1567; Actual Q4: 56.439 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 20.0007; Actual Q2: 31.6373; Actual Q3: 72.8357; Actual Q4: 73.2506 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 3.3702; Actual Q2: 124.7566; Actual Q3: -58.0524; Actual Q4: -59.3888 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: -27.6167; Actual Q2: -25.2866; Actual Q3: -31.4455; Actual Q4: -27.5075 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 104.3117; Actual Q2: -22.103; Actual Q3: 128.0786; Actual Q4: 145.4369 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 4.2774; Actual Q2: -4.8176; Actual Q3: 5.0319; Actual Q4: 5.0048 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: -109.1609; Actual Q2: -132.2514; Actual Q3: -135.4441; Actual Q4: -122.2861 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: -3.328; Actual Q2: 1.8031; Actual Q3: 7.8273; Actual Q4: 10.4522 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: -4.5495; Actual Q2: 9.544; Actual Q3: -23.0065; Actual Q4: -18.6986 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 6.6771; Actual Q2: 22.427; Actual Q3: 31.1134; Actual Q4: 35.2134 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: -49.4159; Actual Q2: 23.3978; Actual Q3: -78.2202; Actual Q4: -65.2379 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: -4.7889; Actual Q2: -24.127; Actual Q3: -11.0737; Actual Q4: -11.0059 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 54.7943; Actual Q2: -42.7461; Actual Q3: 41.3023; Actual Q4: 41.1937 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: -4.6073; Actual Q2: -2.3899; Actual Q3: -1.1975; Actual Q4: -1.1521 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 1.1631; Actual Q2: 9.0251; Actual Q3: -1.5418; Actual Q4: -1.6292 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 2.6716; Actual Q2: 9.2725; Actual Q3: 16.6531; Actual Q4: 18.3112 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: -32.9284; Actual Q2: -16.0498; Actual Q3: -47.9639; Actual Q4: -44.928 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: -1.4016; Actual Q2: -8.4327; Actual Q3: 2.136; Actual Q4: 2.146 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 34.4729; Actual Q2: 1.3622; Actual Q3: 21.9021; Actual Q4: 21.9081 |  |  |  | Circuit miles |  | See note 1 for columns M - AA
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - L. See note 1 for columns M - AA.
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q3: 13; Actual Q4: 54 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q3: -7; Actual Q4: -48 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | [19 empty] | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA. | bar: Actual Q3 to Actual Q4
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q3: -3; Actual Q4: 7 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q3: 2; Actual Q4: -3 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA. | bar: Actual Q3 to Actual Q4
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA. | bar: Actual Q3 to Actual Q4
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q3: 0; Actual Q4: -1 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA. | bar: Actual Q3 to Actual Q4
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q3: -2; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q3: 8; Actual Q4: 4 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q3: 4; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA. | bar: Actual Q3 to Actual Q4
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q3: 3; Actual Q4: 5 |  |  |  | Number of substations |  | See note 4 for columns I - J. See note 1 for columns M - AA.
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 3; Actual Q2: 5; Actual Q3: 4; Actual Q4: 5 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: 4; Actual Q4: 13 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 15; Actual Q2: 12; Actual Q3: 10; Actual Q4: 4 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 36; Actual Q2: 18; Actual Q3: 0; Actual Q4: 10 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 2; Actual Q2: 3; Actual Q3: 1; Actual Q4: 3 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 9; Actual Q2: 10; Actual Q3: 11; Actual Q4: 10 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: -1; Actual Q3: -1; Actual Q4: -1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: -1; Actual Q4: -1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 45; Actual Q2: 26; Actual Q3: 9; Actual Q4: 8 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 77; Actual Q2: 22; Actual Q3: 10; Actual Q4: 2 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 2; Actual Q2: 0; Actual Q3: -1; Actual Q4: 2 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 39; Actual Q2: 47; Actual Q3: 63; Actual Q4: 46 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 1; Actual Q2: 2; Actual Q3: -1; Actual Q4: 2 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 22; Actual Q2: 11; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 23; Actual Q2: 6; Actual Q3: 11; Actual Q4: -1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 5; Actual Q2: 3; Actual Q3: 0; Actual Q4: -1 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 4; Actual Q2: 11; Actual Q3: 10; Actual Q4: 11 |  |  |  | Number of weather stations |  | See note 2 for columns M - AA
Comments for Table 8: The 2022 Actual data was derived by subtracting the 2021 data from the 2022 data in Table 8, and reflects the total net change in the system year-over-year. Data for net change for underground is not provided since PG&E did not provide underground data in 2021. The data presented for 2020 and 2021 Transmission and Distribution removals/additions represents the work for removal of idle facilities. There are many other reasons that conductor may be added or removed. The same layers used in Table 7 have been used to determine Population Density, HFTD, and WUI. Notes for Table 8: The data presented in this table are based on the best knowledge that PG&E has as of January 31, 2023. As better data becomes available, this will be updated in the quarterly updates. Note 1: For transmission & distribution line additions and removals for 2023 - 2025, project prioritization and timing have not been fully determined or mapped. Note 2: PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station additional and removals for 2023, project prioritization and timing have not been fully determined or mapped. Note 3: For substation additional and removals for 2023 - 2025, project prioritization and timing have not been fully determined or mapped. Note 4: The substation count was refined after the submission of our May 5, 2021 self-identification letter relating to substation inspections. Since substations are facilities in which significant amounts of equipment is installed, a single installation date for this field cannot be provided. As a result, PG&E is unable to provide year-over-year data for 2021 because the dataset used in 2021 is different than that from 2020 and would cause discrepancies in the data set. However, PG&E will be able to report the year-over-year data for 2022 and all future years since this standardized counting method will allow for an accurate comparison of annual substation data going forward. Note 5: PG&E’s GIS system is a dynamic ‘real-time’ system that reflects the current assets in PG&E’s service territory, therefore our GIS data does not reflect data from previous years that we had not report on / previously extracted.

## Table 9
| Utility | Pacific Gas and Electric Company
| Table No. | 9
| Date Modified | 2023-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 5 for columns I - X. See note 3 for columns Y - AA.
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | [19 empty] | Circuit miles |  | See note 1 for columns I - X. See note 4 for columns Y - AA.
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations |  | See note 6 for columns M -AA
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | [19 empty] | Number of weather stations |  | See note 2 for columns I - AA
Comments for Table 9: The data presented in this table are based on the best knowledge that PG&E has as of January 31, 2023. As better data becomes available, this will be updated in the quarterly updates. Note 1: PG&E replaced or removed approximately 38 miles of transmission conductor in 2022, but all jobs have not been mapped into the GIS system in order to break the data down as required by this table. Note 2: PG&E plans to do some power upgrades on some weather stations in 2023, but projects have not been mapped as of January 2023 therefore its' projection will not be included in this dataset. Note 3: PG&E is in the process of planning the Distribution system hardening work for 2023 - 2025. Note 4: PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table. Note 5: PG&E hardened 483 miles in 2022, but not all projects have been mapped as of January 2023 and therefore may not be included in this data. Note 6: PG&E is in the process of refining the substation upgrade plan for 2023 - 2025. Other comments: 1) The same layers used in Table 8 have been used to determine Population Density, HFTD, and WUI.

## Table 10
Utility | Pacific Gas and Electric Company |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2023-02-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | [15 empty] | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Wind Warning Status | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 1.2; Projected 4: 0.8; Projected 1: 0; Projected 2: 0; Projected 3: 1.2; Projected 4: 0.8; Projected 1: 0; Projected 2: 0; Projected 3: 1.2; Projected 4: 0.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1.8; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1.8; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | None | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.b. | RFW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 100.8; Projected 4: 33.6; Projected 1: 0; Projected 2: 0; Projected 3: 100.8; Projected 4: 33.6; Projected 1: 0; Projected 2: 0; Projected 3: 100.8; Projected 4: 33.6 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 324.6; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 324.6; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 324.6 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | None | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.c. | RFW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 2223318.871; Projected 4: 571834.955; Projected 1: 0; Projected 2: 0; Projected 3: 2198177.546; Projected 4: 565373.2201; Projected 1: 0; Projected 2: 0; Projected 3: 2167403.06; Projected 4: 557457.995 | Customer hours per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW & RFW | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 9526919.797; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 9419171.854; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 9287303.448 | Customer hours per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | None | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Customer hours per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
| 1.d. | RFW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 31; Actual Q3: 6; Actual Q4: 1 | Number of events |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | HWW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | HWW & RFW | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | Number of events |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | None | Frequency of fast-trip events (total) | Actual Q1: 4; Actual Q2: 548; Actual Q3: 1319; Actual Q4: 466 | Number of events |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 391; Actual Q3: 10091; Actual Q4: 104693 | Circuit mile days |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 20; Actual Q2: 16; Actual Q3: 0; Actual Q4: 75 | Circuit mile days |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 80 | Circuit mile days |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
|  | None | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 10239; Actual Q2: 1962929; Actual Q3: 3999301; Actual Q4: 1848540 | Circuit mile days |  | Per guidelines from OEIS on Jan 23rd, we are not providing projections for metric
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | Actual Q1: 801537; Actual Q2: 940,399; Actual Q3: 836,702; Actual Q4: 694908; Projected 1: 739424.8278; Projected 2: 740381.8722; Projected 3: 3831564.2389; Projected 4: 5954497.6111; Projected 1: 739424.8278; Projected 2: 740381.8722; Projected 3: 3831564.2389; Projected 4: 5954497.6111; Projected 1: 739424.8278; Projected 2: 740381.8722; Projected 3: 3831564.2389; Projected 4: 5954497.6111 | Total customer hours of planned outages per year | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | Actual Q1: 3,112,527; Actual Q2: 5755242; Actual Q3: 8446118; Actual Q4: 10463744; Projected 1: 8390455.45; Projected 2: 4131263.4111; Projected 3: 8724555.0111; Projected 4: 12558450.7444; Projected 1: 8390455.45; Projected 2: 4131263.4111; Projected 3: 8724555.0111; Projected 4: 12558450.7444; Projected 1: 8390455.45; Projected 2: 4131263.4111; Projected 3: 8724555.0111; Projected 4: 12558450.7444 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | Actual Q1: 4635.8167; Actual Q2: 1635480.3833; Actual Q3: 3639082.1167; Actual Q4: 836381.1333; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Total customer hours of outages due to fast-trip per year | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | Actual Q1: 0.7; Actual Q2: 1.2; Actual Q3: 1.6; Actual Q4: 1.9531; Projected 1: 1.6106; Projected 2: 0.85722; Projected 3: 2.2156; Projected 4: 3.2661; Projected 1: 1.6106; Projected 2: 0.85722; Projected 3: 2.2156; Projected 4: 3.2661; Projected 1: 1.6106; Projected 2: 0.85722; Projected 3: 2.2156; Projected 4: 3.2661 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | Actual Q1: 0.7; Actual Q2: 1.2; Actual Q3: 1.6; Actual Q4: 1.9531; Projected 1: 1.5928; Projected 2: 0.85722; Projected 3: 1.6689; Projected 4: 2.3389; Projected 1: 1.5928; Projected 2: 0.85722; Projected 3: 1.6689; Projected 4: 2.3389; Projected 1: 1.5928; Projected 2: 0.85722; Projected 3: 1.6689; Projected 4: 2.3389 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | Actual Q1: 0.3; Actual Q2: 0.5; Actual Q3: 0.6; Actual Q4: 0.464; Projected 1: 0.35367; Projected 2: 0.36867; Projected 3: 0.51833; Projected 4: 0.483; Projected 1: 0.35367; Projected 2: 0.36867; Projected 3: 0.51833; Projected 4: 0.483; Projected 1: 0.35367; Projected 2: 0.36867; Projected 3: 0.51833; Projected 4: 0.483 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | Actual Q1: 0.3; Actual Q2: 0.5; Actual Q3: 0.6; Actual Q4: 0.464; Projected 1: 0.35333; Projected 2: 0.36867; Projected 3: 0.50067; Projected 4: 0.45533; Projected 1: 0.35333; Projected 2: 0.36867; Projected 3: 0.50067; Projected 4: 0.45533; Projected 1: 0.35333; Projected 2: 0.36867; Projected 3: 0.50067; Projected 4: 0.45533 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | For Actual: Historical PSPS and non-PSPS outage data. For Projected: Based on 3-year historical average.
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 43453.2237; Projected 4: 188458.3244; Projected 1: 0; Projected 2: 0; Projected 3: 42961.6623; Projected 4: 186326.0451; Projected 1: 0; Projected 2: 0; Projected 3: 42360.199; Projected 4: 183717.4805 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 63562.2456; Projected 4: 253774.0015; Projected 1: 0; Projected 2: 0; Projected 3: 62808.35; Projected 4: 250718.8554; Projected 1: 0; Projected 2: 0; Projected 3: 61929.0331; Projected 4: 247208.7914 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
| 4.b. | N/A | # of medical baseline customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 5090.2058; Projected 4: 19503.7161; Projected 1: 0; Projected 2: 0; Projected 3: 5031.3903; Projected 4: 19276.4116; Projected 1: 0; Projected 2: 0; Projected 3: 4960.9509; Projected 4: 19006.5419 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Medical Baseline customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
| 4.c. | N/A | # of customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 91457.7688; Projected 4: 365147.6396; Projected 1: 0; Projected 2: 0; Projected 3: 90373.0115; Projected 4: 360751.6835; Projected 1: 0; Projected 2: 0; Projected 3: 89107.7893; Projected 4: 355701.1599 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. Consistent with past reporting, does not include events in which no customers were de-energized. For Projected: This is larger than the number of customers impacted (4a), because it includes additional customers who were notified but not de-energized.
| 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 7257.3283; Projected 4: 27807.2985; Projected 1: 0; Projected 2: 0; Projected 3: 7173.4726; Projected 4: 27483.2207; Projected 1: 0; Projected 2: 0; Projected 3: 7073.044; Projected 4: 27098.4556 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. Consistent with past reporting, does not include events in which no customers were de-energized. For Projected: This is larger than the number of Medical Baseline customers impacted (4b), because it includes additional customers who were notified but not de-energized.
| 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 63562.2456; Projected 4: 253774.0015; Projected 1: 0; Projected 2: 0; Projected 3: 62808.35; Projected 4: 250718.8554; Projected 1: 0; Projected 2: 0; Projected 3: 61929.0331; Projected 4: 247208.7914 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. Consistent with past reporting, does not include events in which no customers were de-energized. For Projected: PG&E plans to notify all customers prior to their de-energization in a PSPS event.
| 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 5090.2058; Projected 4: 19503.7161; Projected 1: 0; Projected 2: 0; Projected 3: 5031.3903; Projected 4: 19276.4116; Projected 1: 0; Projected 2: 0; Projected 3: 4960.9509; Projected 4: 19006.5419 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | For Actual: No PSPS events that required de-energization in 2022. Consistent with past reporting, does not include events in which no customers were de-energized. For Projected: PG&E plans to notify all Medical Baseline customers prior to their de-energization in a PSPS event.
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 1; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1 | Number of events | For Actual: Based on the October 22, 2022 Weather Event, which did not result in de-energization. For Projected: Based on the historical average of Weather Events which resulted in notifications but not de-energization, in the years 2020-2022.
| 5.b. | N/A | Average number of customers located on de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 1681.0345; Projected 4: 1844.5325; Projected 1: 0; Projected 2: 0; Projected 3: 1681.0345; Projected 4: 1844.5325; Projected 1: 0; Projected 2: 0; Projected 3: 1681.0345; Projected 4: 1844.5325 | Number of customers | For Actual: No PSPS events that required de-energization in 2022. For Projected: This was calculated by summing the total active customers on de-energized circuits for all events in a given quarter, divided by the number of de-energized circuit-events in the same quarter. The list of impacted circuits is based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 15.8437; Projected 4: 41.9761; Projected 1: 0; Projected 2: 0; Projected 3: 15.6645; Projected 4: 41.5014; Projected 1: 0; Projected 2: 0; Projected 3: 15.4452; Projected 4: 40.9204 | =1.c. / RFW OH circuit mile days in time period | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year historical average.
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1170.3017; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1157.0665; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 1140.8675 | =1.c. / HWW OH circuit mile days in time period | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year historical average.
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 1.0796; Projected 4: 10.0657; Projected 1: 0; Projected 2: 0; Projected 3: 1.0674; Projected 4: 9.9519; Projected 1: 0; Projected 2: 0; Projected 3: 1.0524; Projected 4: 9.8125 | =1.c. / FPI OH circuit mile days in time period | For Actual: No PSPS events that required de-energization in 2022. For Projected: Based on 5-year historical average.
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 21; Projected 4: 29; Projected 1: 0; Projected 2: 0; Projected 3: 21; Projected 4: 29; Projected 1: 0; Projected 2: 0; Projected 3: 21; Projected 4: 29 | Time between de-energization and inspection on a circuit-segment basis in hours | For Actual: No PSPS events that required de-energization in 2022. For Projected: This is calculated based on the time between the start of de-energization due to PSPS, and the start of inspection. Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 38; Projected 4: 50; Projected 1: 0; Projected 2: 0; Projected 3: 38; Projected 4: 50; Projected 1: 0; Projected 2: 0; Projected 3: 38; Projected 4: 50 | Time between de-energization and inspection on a circuit-segment basis in hours | For Actual: No PSPS events that required de-energization in 2022. For Projected: This is calculated based on the time between the start of de-energization due to PSPS, and the start of inspection. Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 1.3167; Actual Q2: 3.5333; Actual Q3: 3.2833; Actual Q4: 3.1167; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 4.6; Actual Q2: 15.6; Actual Q3: 15.2; Actual Q4: 16.9; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 0; Projected 4: 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Projected 1: 0; Projected 2: 0; Projected 3: 22.9216; Projected 4: 202.1068; Projected 1: 0; Projected 2: 0; Projected 3: 22.9216; Projected 4: 202.1068; Projected 1: 0; Projected 2: 0; Projected 3: 22.9216; Projected 4: 202.1068 | Number of risk events | For Actual: No PSPS events that required de-energization in 2022. For Projected: The number of risk events is based on the number of damages and hazards, as reported in post de-energization reports for past PSPS events. The list of events is based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. For lookback events which do not align with a past PSPS event, the number of risk events is approximated using the number of sustained outages which occurred during the hypothetical lookback event scope and duration, filtered to only include the types of outages which would have resulted in a damage or hazard (as reported in post de-energization reports).
Comments for Table 10: PG&E has outlined the past and forecasted PSPS metrics in Table 10, which is utilizing historic recorded data for actuals and an analysis of the past ten years of weather data to provide the forecasted metrics. Please see the Comments column of Table 10 for specific details regarding the actual and projected methodology for each metric.

## Table 11
Utility | Pacific Gas and Electric Company | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2023-02-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actual | [15 empty] | Projected
|  | The units for the spend data are thousands of dollars. | [9 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Community Outreach and Engagement | Public outreach and education awareness program |  | N/A - Foundational |  | 2019 | Denergization OIR – Phase 3 | n/a | In compliance | Denergization OIR – Phase 3, GO 166 |  |  | 0 | 0 | 1798.9138 | 1798.9138 | 255.1762 | 255.1762 | 24890.6211 | 24890.6211 | 36.4711 | 36.4711 | 25774.44 | 25774.44 | 5874.3394 | 5874.3394 | 30836.7581 | 30836.7581 | 4062.5 | 4062.5 | 23346.5806 | 23346.5806 | 4062.5 | 4062.5 | 15546.5806 | 15546.5806 | 4184.375 | 4184.375 | 16012.978 | 16012.978
Community Outreach and Engagement | Engagement with access and functional needs populations |  | N/A - Foundational |  | 2018 | Denergization OIR – Phase 3 | n/a | In compliance | Denergization OIR – Phase 3 |  |  | 0 | 0 | 7900.0555 | 7900.0555 | 0 | 0 | 9036.1912 | 9036.1912 | 0 | 0 | 10566.0131 | 10566.0131 | 0 | 0 | 10315.173 | 10315.173 | 0 | 0 | 11834.5776 | 11834.5776 | 0 | 0 | 12189.615 | 12189.615 | 0 | 0 | 12555.3034 | 12555.3034
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning |  | N/A - Foundational |  | 2021 | PSPS OII | n/a | In compliance | Customer Care portion: PSPS OII |  |  | 0 | 0 | 2346.6931 | 2346.6931 | 0 | 0 | 2716.4217 | 2716.4217 | 0 | 0 | 3112.9697 | 3112.9697 | 0 | 0 | 3033.6193 | 3033.6193 | 0 | 0 | 3496.1115 | 3496.1115 | 0 | 0 | 3600.9949 | 3600.9949 | 0 | 0 | 3709.0247 | 3709.0247
Community Outreach and Engagement | Best practice sharing with other utilities |  | All Consequences |  | <2018 | 2023 GRC | n/a | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  | 0 | 0 | 2390.613 | 2390.613 | 0 | 0 | 2988.3181 | 2988.3181 | 0 | 0 | 2964.0722 | 2964.0722 | 0 | 0 | 1621.8857 | 1621.8857 | 0 | 0 | 4119 | 4119 | 0 | 0 | 4242.57 | 4242.57 | 0 | 0 | 4369.8471 | 4369.8471
Emergency Preparedness | Emergency preparedness plan |  | All Consequences |  | 2018 | Denergization OIR – Phase 3 | n/a | In compliance | Denergization OIR – Phase 3 |  |  | 0 | 0 | 11389.1299 | 11389.1299 | 0 | 0 | 13050.336 | 13050.336 | 0 | 0 | 15197.7335 | 15197.7335 | 0 | 0 | 14815.7448 | 14815.7448 | 0 | 0 | 17043.1514 | 17043.1514 | 0 | 0 | 17554.4459 | 17554.4459 | 0 | 0 | 18081.0793 | 18081.0793
Emergency Preparedness | External collaboration and coordination |  | All Consequences |  | 2018 | Denergization OIR – Phase 3 | n/a | In compliance | Denergization OIR – Phase 3 |  |  | 0 | 0 | 3840.253 | 3840.253 | 0 | 0 | 7224.2167 | 7224.2167 | 0 | 0 | 6879.2394 | 6879.2394 | 0 | 0 | 5978.6615 | 5978.6615 | 0 | 0 | 8109.3037 | 8109.3037 | 0 | 0 | 8352.5828 | 8352.5828 | 0 | 0 | 8603.1603 | 8603.1603
Emergency Preparedness | Public emergency communication strategy |  | All Consequences |  | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 |  |  | 0 | 0 | 189.1269 | 189.1269 | 0 | 0 | 16156.1589 | 16156.1589 | 0 | 0 | 17796.4476 | 17796.4476 | 0 | 0 | 10351.3177 | 10351.3177 | 0 | 0 | 8700 | 8700 | 0 | 0 | 8961 | 8961 | 0 | 0 | 9229.83 | 9229.83
Emergency Preparedness | Preparedness and planning for service restoration |  | All Consequences |  | 2018 | Denergization OIR – Phase 3 | n/a | In compliance | Denergization OIR – Phase 3 |  |  | 0 | 0 | 2073.6491 | 2073.6491 | 765.5286 | 765.5286 | 14521.6002 | 14521.6002 | 109.4134 | 109.4134 | 11928.6446 | 11928.6446 | -12.0189 | -12.0189 | 9311.2938 | 9311.2938 | 187.5 | 187.5 | 14780.0164 | 14780.0164 | 193.125 | 193.125 | 15223.4169 | 15223.4169 | 198.9187 | 198.9187 | 15680.1194 | 15680.1194
Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC | n/a | In Compliance | TD-9001M CH 15 “Fire Area Design Guidance” in addition to all relevant standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 251136.0575 | 251136.0575 | 0 | 0 | 444029.9827 | 444029.9827 | 0 | 0 | 112596.2775 | 112596.2775 | 0 | 0 | 285543.7965 | 285543.7965 | 0 | 0 | 67504.2203 | 67504.2203 | 0 | 0 | 59301.8571 | 59301.8571 | 0 | 0 | 41432.3404 | 41432.3404 | 0 | 0
Grid Design, Operations, and Maintenance | Covered conductor installation |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | n/a | n/a |  |  | 100.2381 | 0 | 0 | 0 | 179.3827 | 0 | 0 | 0 | 6684.49 | 6727.4484 | 0 | 0 | 10660.7966 | 10596.8485 | 0 | 0 | 7621 | 7621 | 0 | 0 | 7849.63 | 7849.63 | 0 | 0 | 8085.1189 | 8085.1189 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions |  | Consequence - PSPS |  | - Distribution - 2019 - Transmission - 2019/2020 | -Distribution - 2023 GRC - Transmission - TO Rate Case | n/a | - Distribution - In compliance per WMP commitments for replacements - Transmission - n/a | n/a |  |  | 84293.1082 | 79674.4921 | 0 | 0 | 114864.0146 | 108432.0097 | 0 | 0 | 53976.5063 | 51079.406 | 0 | 0 | 48072.0123 | 45726.8419 | 0 | 0 | 17303.7399 | 15847.8377 | 0 | 0 | 17822.8521 | 16323.2728 | 0 | 0 | 18357.5376 | 16812.971 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events |  | Contact from object |  | checking with Kindra and Justin Flores for the Substation Animal Abatement portion | checking with Kindra and Justin Flores for the Substation Animal Abatement portion | checking with Kindra and Justin Flores for the Substation Animal Abatement portion | checking with Kindra and Justin Flores for the Substation Animal Abatement portion | checking with Kindra and Justin Flores for the Substation Animal Abatement portion |  |  | 1708.9731 | 1708.9731 | 0 | 0 | 5960.8386 | 5960.8386 | 0 | 0 | 6598.9343 | 6598.9343 | 0 | 0 | 3443.3024 | 3443.3024 | 261.04 | 261.04 | 0 | 0 | 835 | 835 | 0 | 0 | 860.05 | 860.05 | 0 | 0 | 885.8515 | 885.8515
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | In Compliance | UG Design and Construction Standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 66496.895 | 66331.5516 | 0 | 0 | 77562.1 | 72874.2798 | 0 | 0 | 262146.6108 | 252222.4578 | 0 | 0 | 558068.2384 | 550224.5857 | 0 | 0 | 1263230.7283 | 1233980.7283 | 0 | 0 | 1624232.6624 | 1594105.1624 | 0 | 0 | 1878931.225 | 1863415.5625 | 0 | 0
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment |  | Equipment / facility failure |  | <2018 | 2023 GRC | n/a | Not in compliance - due to the backlog of poles to be replaced and reinforced; but have plan to reduce backlog | GO 95 Rule 18 |  |  | 361157.977 | 105813.4526 | 3764.3247 | 0 | 248052.6956 | 127940.7329 | 4783.4683 | 0 | 413586.3039 | 338324.7705 | 2800.1469 | 104.771 | 506231.7091 | 408395.3636 | 3362.5204 | 543.7312 | 503834.5982 | 377875.9487 | 5809.3098 | 0 | 518949.6362 | 389212.2271 | 5983.5891 | 0 | 534518.1253 | 400888.594 | 6163.0968 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | Equipment / facility failure |  | <2018 | TO Rate Case | n/a | Refer to section 8.1.7.1 and assocated target 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. | GO 95 Rule 18 |  |  | 41694.6543 | 22950.0251 | 167411.8598 | 114551.4348 | 63740.489 | 14707.8029 | 93657.0663 | 49029.1608 | 81032.7963 | 12990.9465 | 105907.949 | 45196.9636 | 191547.5078 | 44643.1586 | 93770.5882 | 54595.9668 | 114621.0258 | 18628.0406 | 99279.8781 | 10184.1633 | 118059.6566 | 19186.8819 | 102258.2745 | 10489.6882 | 121601.4463 | 19762.4883 | 105326.0227 | 10804.3789
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - refer to Maintenance program in 8.1.4 Transmission before 2018 | Distribution - refer to Maintenance program in 8.1.4 Transmission - TO rate case | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution costs covered in the Maintenance programs, under 8.1.4 |  | 508.0346 | 508.0346 | 0 | 0 | 1060.154 | 1060.154 | 0 | 0 | 24817.0913 | 24817.0913 | 0 | 0 | 4865.1974 | 4865.1974 | 0 | 0 | 19134.1732 | 19134.1732 | 0 | 0 | 7799.5099 | 7799.5099 | 0 | 0 | 19143.2054 | 19143.2054 | 0 | 0
Grid Design, Operations, and Maintenance | Traditional overhead hardening |  | Equipment / facility failure |  | 2019 | 2023 GRC | n/a | not in compliance – we have non-exempt fuse equipment installed in fire areas. | Cal Fire Power Line Fire Prevention Field Guide establishes what is classified as non-exempt. TD-9100P-09 is the estimating standard for equipment in fire areas that references the above guide. |  |  | 30897.6865 | 30897.6865 | 0 | 0 | 71344.5464 | 71344.5464 | 0 | 0 | 85486.1036 | 85486.1036 | 0 | 0 | 60360.8595 | 60360.8595 | 0 | 0 | 31758.6216 | 31758.6216 | 0 | 0 | 28800.9562 | 28800.9562 | 0 | 0 | 29664.9849 | 29664.9849 | 0 | 0
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots |  | Consequence - PSPS |  | 2019 - Dist. Micro, CMEP, MIP, Clean Substation 2019 - Remote Grid | - Dist. Micro, CMEP, MIP, Clean Substation: Microgrid OIR, 2020 GRC, EPIC 3 - Remote Grid: 2023 GRC | - CMEP, MIP, Clean Substation: MGMA/MGBA - Remote Grid: n/a | - Dist. Micro, CMEP, MIP, Clean Substation: In compliance - Remote Grid: in compliance with required filing (Resolution E-5132) | n/a |  |  | 3283.1713 | 3283.1713 | 725.9452 | 725.9452 | 13901.6863 | 13901.6863 | 2149.9013 | 2149.9013 | 15570.9024 | 15570.9024 | 7219.1667 | 7219.1667 | 5548.8426 | 5548.8426 | 4731.4075 | 4731.4075 | 2038.5821 | 2038.5821 | 11544.9276 | 11544.9276 | 4742.361 | 4742.361 | 27935.7745 | 27935.7745 | 6008.213 | 6008.213 | 38299.4646 | 38299.4646
Grid Design, Operations, and Maintenance | Microgrids |  | N/A - Foundational | N/A - Foundational | 2019 | 2023 GRC | n/a | n/a | n/a |  |  | 6720.4368 | 6720.4368 | 0 | 0 | 1443.485 | 1443.485 | 0 | 0 | 7730.8492 | 7730.8492 | 0 | 0 | 4729.4877 | 4729.4877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - 2019 Transmission < 2018 | Distribution - 2023 GRC Transmission - Res.SED 6 | n/a | Distribution - In Compliance Transmission - In Compliance | Distribution: De-energization and removal of OH conductor in HFTD/HFRA; Utility Procedure: TD-2459P-01 “Idle Facility Program” Transmission: GO-95 rule 31.6 |  |  | 0 | 0 | 0 | 0 | 196.8593 | 196.8593 | 0 | 0 | 3209.2233 | 3209.2233 | 0 | 0 | 29546.6298 | 12842.9691 | 0 | 0 | 64023.161 | 21568.0233 | 0 | 0 | 2250 | 2250 | 0 | 0 | 2250 | 2250 | 0 | 0
Grid Design, Operations, and Maintenance | Line removals (in HFTD) |  | Equipment / facility failure |  | Distribution - 2016 (focused on WMP work) Transmission - 2020 Substation - 2022 | Distribution - 2023 GRC Transmission - TO Rate Case Substation - 2023 GRC | n/a | Distribution - In compliance with WMP and GO 165 regulations. (Missed Inspections will be tracked and reported to the CPUC) Transmission - Michelle Sakamoto Substation - Kindra Cooper-Okas, Justin Flores | Distribution - GO 95; GO 165 Transmission - GO95; GO165 (Michelle to confirm) Substation - GO 174 (Kindra/Justin to confirm) |  |  | 0 | 0 | 268481.7516 | 225769.2108 | 0 | 0 | 249830.2165 | 92716.8533 | 0 | 0 | 242600.4995 | 111499.9219 | 0 | 0 | 231948.0214 | 131151.0375 | 0 | 0 | 163953.2274 | 80138.8645 | 0 | 0 | 168871.8242 | 82543.0305 | 0 | 0 | 173937.9789 | 85019.3214
Grid Design, Operations, and Maintenance | Asset Inspections |  | Equipment / facility failure |  | - Distribution - Transmission < 2018 - Substation - Circuit Breaker Maintenance and Installation initiative was introduced in the 2020 WMP. | 2023 GRC, Transmission Owner Rate Case | n/a | - Distribution - - Transmission - Not currently in compliance. Refer to Section 8.1.7.1 and associated target in 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. - Substation - In Compliance with regulations | - Distribution - - Transmission - GO 95 Rule 18 - Substation – CPUC General Order 174; WECC-FAC-501 |  |  | 763889.6811 | 307279.7471 | 385147.2314 | 80620.4247 | 808345.32 | 302202.7919 | 188653.0883 | 86011.5952 | 858693.7914 | 350524.5386 | 195212.6444 | 91602.822 | 989094.7078 | 338978.6283 | 171288.515 | 77405.3249 | 992133.6365 | 484344.1103 | 200999.0601 | 77628.5672 | 1021897.6456 | 498874.4336 | 207029.0319 | 79957.4242 | 1052554.575 | 513840.6666 | 213239.9029 | 82356.1469
Grid Design, Operations, and Maintenance | Equipment inspections, maintenance, and repair |  | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | Wildfire technology costs are aggegated in financials for "Other - Wildfire" |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Grid Design, Operations, and Maintenance | Asset management and inspection enterprise system(s) |  | N/A - Foundational | N/A - Foundational | 2020 | 2023 GRC, 2022 WMP | n/a | In Compliance | GO 95 GO 128 GO 165 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4349 | 2467 | 0 | 0 | 4349 | 2467 | 0 | 0 | 4349 | 2467 | 0 | 0 | 10657.395 | 10657.395 | 0 | 0 | 10977.1169 | 10977.1169 | 0 | 0 | 11306.4304 | 11306.4304
Grid Design, Operations, and Maintenance | Quality assurance / quality control |  | Equipment / facility failure |  | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | Most of the costs related to "Open Work Orders" are mapped to Maintenance section 8.1.4 |  | 0 | 0 | 5256.9386 | 5256.9386 | 0 | 0 | 3106.4294 | 3106.4294 | 0 | 0 | 5058.2168 | 5058.2168 | 0 | 0 | 1972.9466 | 1972.9466 | 0 | 0 | 3180.6092 | 3180.6092 | 0 | 0 | 3276.0274 | 3276.0274 | 0 | 0 | 3374.3083 | 3374.3083
Grid Design, Operations, and Maintenance | Open work orders |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | n/a | n/a |  |  | 56.6213 | 56.6213 | 1835.4004 | 1835.4004 | 4798.2197 | 4798.2197 | 6425.3295 | 6425.3295 | 719.8351 | 719.8351 | 24027.2564 | 24027.2564 | 17597.1214 | 17597.1214 | 87916.0239 | 87916.0239 | 41608.7201 | 41608.7201 | 108428.794 | 108428.794 | 41617.9482 | 41617.9482 | 0 | 0 | 41627.4532 | 41627.4532 | 0 | 0
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops) |  | N/A - Foundational | N/A - Foundational | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | Refer to 8.1.8.1 where EPSS financials are aggregated, also 8.1.8.2 Inspections |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops) |  | N/A - Foundational | N/A - Foundational | <2018 | 2022 WMP | n/a | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 | General Operations |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | n/a - support function | n/a - support function | General Operations |  | 0 | 0 | 1384.7294 | 1384.7294 | 0 | 0 | 839.8231 | 839.8231 | 0 | 0 | 966.4419 | 966.4419 | 0 | 0 | 808.4113 | 808.4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Workforce Planning |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | In Compliance | n/a - governed by various state, federal, local legislation | General Operations - costs are allocated to projects across the company when mitigations happen; so costs are already embedded in various programs and MWCs/MATs |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Overview of the Service Territory | Environmental compliance and permitting | 5.4.5 | N/A - Foundational | N/A - Foundational | 2019 | 2022 WMP | n/a | Risk models - in compliance | n/a |  |  | 6250 | 1933.5264 | 0 | 0 | 6950 | 2150.0814 | 0 | 0 | 8550 | 2645.0641 | 0 | 0 | 10150 | 3140.0469 | 0 | 0 | 10750 | 3325.6654 | 0 | 0 | 11072.5 | 3425.4354 | 0 | 0 | 11404.675 | 3528.1984 | 0 | 0
Risk Methodology and Assessment | Risk Methodology and Assessment | 6 | N/A - Foundational | N/A - Foundational | 2018 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 6933.6763 | 6933.6763 | 606.9244 | 606.9244 | 8314.9397 | 8314.9397 | 111.2093 | 111.2093 | 7719.7701 | 7719.7701 | 145.2292 | 145.2292 | 5625.0762 | 5625.0762 | 99.0722 | 99.0722 | 3286.1036 | 3286.1036 | 3126.5414 | 3126.5414 | 3384.6867 | 3384.6867 | 3220.3377 | 3220.3377 | 3486.2274 | 3486.2274 | 3316.9478 | 3316.9478
Situational Awareness and Forecasting | Environmental monitoring systems |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | n/a | GO 95 |  |  | 3001.4941 | 3001.4941 | 2290.5578 | 2290.5578 | 7392.227 | 7392.227 | 7895.1714 | 7895.1714 | 6574.6406 | 6574.6406 | 6311.8401 | 6311.8401 | 11163.4167 | 11163.4167 | 2316.4249 | 2316.4249 | 10105.7631 | 10105.7631 | 3329.768 | 3329.768 | 316.8323 | 316.8323 | 0 | 0 | 326.3373 | 326.3373 | 0 | 0
Situational Awareness and Forecasting | Grid monitoring systems |  | N/A - Foundational | N/A - Foundational | 2017 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 198.2271 | 198.2271 | 6196.5384 | 6196.5384 | 898.8112 | 898.8112 | 12667.292 | 12667.292 | 14.032 | 14.032 | 13969.7842 | 13969.7842 | 3.5106 | 3.5106 | 18744.056 | 18744.056 | 0 | 0 | 15324.1795 | 15324.1795 | 0 | 0 | 15783.9049 | 15783.9049 | 0 | 0 | 16257.4221 | 16257.4221
Situational Awareness and Forecasting | Ignition detection systems |  | N/A - Foundational | N/A - Foundational | 2014 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1627.0829 | 1627.0829 | 0 | 0 | 1797.3967 | 1797.3967 | 0 | 0 | 2067.4111 | 2067.4111 | 0 | 0 | 1976.0114 | 1976.0114 | 0 | 0 | 2035.2918 | 2035.2918 | 0 | 0 | 2096.3505 | 2096.3505
Situational Awareness and Forecasting | Weather forecasting |  | N/A - Foundational | N/A - Foundational | 2015 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0 | 0 | 85.8259 | 85.8259 | 0 | 0 | 93.1869 | 93.1869 | 0 | 0 | 134.1519 | 134.1519 | 0 | 0 | 132.1787 | 132.1787 | 0 | 0 | 150.4722 | 150.4722 | 0 | 0 | 154.9864 | 154.9864 | 0 | 0 | 159.636 | 159.636
Situational Awareness and Forecasting | Fire potential index |  | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | "NERC Standard FAC-003-04; GO 95 Rule 35; PRC 4292; PRC 4293; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01)" |  |  | 0 | 0 | 21034.22 | 6394.7002 | 0 | 0 | 22860.655 | 6949.9623 | 0 | 0 | 23507.405 | 23507.405 | 0 | 0 | 24917.176 | 24917.176 | 0 | 0 | 32890.6 | 32890.6 | 0 | 0 | 32890.6 | 32890.6 | 0 | 0 | 32890.6 | 32890.6
Vegetation Management and Inspection | Vegetation Inspections - Transmission |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | GO 95 Rule 35; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23) |  |  | 0 | 0 | 811980 | 252178.4538 | 0 | 0 | 1110310 | 344831.4725 | 0 | 0 | 1371370 | 425909.4635 | 0 | 0 | 1330440 | 413197.7414 | 0 | 0 | 771980 | 239755.5639 | 0 | 0 | 752770 | 233789.471 | 0 | 0 | 716880 | 222643.033
Vegetation Management and Inspection | Vegetation Inspections - Distribution |  | Vegetation Contact |  | <2018, 2021 | 2023 GRC, 2022 WMP | n/a | In compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  | 0 | 0 | 24580 | 7633.8659 | 0 | 0 | 28250 | 8773.666 | 0 | 0 | 35080 | 10894.8745 | 0 | 0 | 52200 | 16211.8713 | 0 | 0 | 31000 | 9627.7397 | 0 | 0 | 30230 | 9388.5991 | 0 | 0 | 28790 | 8941.375
Vegetation Management and Inspection | Pole clearing |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Best Management Practices (BMP) for Vegetation Management Activities (TD-7102P-01-JA01); Wood Management (TD-7102P-26) |  |  | 0 | 0 | 69730 | 21656.2028 | 0 | 0 | 95660 | 29709.3412 | 0 | 0 | 61220 | 19013.233 | 0 | 0 | 160450 | 49831.3172 | 0 | 0 | 105200 | 32672.2005 | 0 | 0 | 102580 | 31858.5012 | 0 | 0 | 97690 | 30339.8029
Vegetation Management and Inspection | Wood and slash management |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | refer to 8.2.3.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Clearance |  | Vegetation Contact |  | 2023 | n/a | n/a | n/a | GO 95 Rule 35; PRC 4292; PRC 4293 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188610 | 58577.0317 | 0 | 0 | 183910 | 57117.3421 | 0 | 0 | 175140 | 54393.6235
Vegetation Management and Inspection | Fall-in mitigation |  | Vegetation Contact |  | checking with Justin Flores and kindra Cooper-Okas | checking with Justin Flores and kindra Cooper-Okas | checking with Justin Flores and kindra Cooper-Okas | checking with Justin Flores and kindra Cooper-Okas | checking with Justin Flores and kindra Cooper-Okas |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4327.6907 | 4327.6907 | 0 | 0 | 4002.1973 | 4002.1973 | 0 | 0 | 3530.1939 | 3530.1939 | 0 | 0 | 2521.7317 | 2521.7317 | 0 | 0 | 2597.3837 | 2597.3837 | 0 | 0 | 2675.3052 | 2675.3052
Vegetation Management and Inspection | Substation defensible space |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | check with April on if more language |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | High-risk species |  | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO); ANSI A300 (Part 7)-2018 Integrated Vegetation Management; State, county, and city weed abatement ordinances |  |  | 0 | 0 | 10156.145 | 3087.6116 | 0 | 0 | 13935.693 | 4236.6477 | 0 | 0 | 14566.504 | 14566.504 | 0 | 0 | 10557.411 | 10557.411 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680
Vegetation Management and Inspection | Fire-resilient rights-of-way (Transmission) |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP (checking with Dana if should be TO and not GRC) | n/a | In compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO); ANSI A300 (Part 7)-2018 Integrated Vegetation Management; State, county, and city weed abatement ordinances |  |  | 0 | 0 | 10156.145 | 3087.6116 | 0 | 0 | 13935.693 | 4236.6477 | 0 | 0 | 14566.504 | 14566.504 | 0 | 0 | 10557.411 | 10557.411 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680
Vegetation Management and Inspection | Fire-resilient rights-of-way (Distribution) |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP (checking with Dana if should be TO and not GRC) | n/a | In compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO); ANSI A300 (Part 7)-2018 Integrated Vegetation Management; State, county, and city weed abatement ordinances |  |  | 0 | 0 | 10156.145 | 3087.6116 | 0 | 0 | 13935.693 | 4236.6477 | 0 | 0 | 14566.504 | 14566.504 | 0 | 0 | 10557.411 | 10557.411 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680 | 0 | 0 | 12680 | 12680
Vegetation Management and Inspection | Fire-resilient rights-of-way |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Vegetation Management Priority Tag Procedure (TD-7102P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  | 0 | 0 | 3430 | 1065.2628 | 0 | 0 | 5050 | 1568.3899 | 0 | 0 | 8800 | 2733.0358 | 0 | 0 | 11310 | 3512.5721 | 0 | 0 | 13000 | 4037.4392 | 0 | 0 | 12680 | 3938.0561 | 0 | 0 | 12070 | 3748.607
Vegetation Management and Inspection | Emergency response vegetation management |  | N/A - Foundational | N/A - Foundational | 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8960 | 2782.7273 | 0 | 0 | 16930 | 5257.9882 | 0 | 0 | 18000 | 5590.3005 | 0 | 0 | 17550 | 5450.5429 | 0 | 0 | 16720 | 5192.768
Vegetation Management and Inspection | Vegetation management enterprise system |  | N/A - Foundational | N/A - Foundational | <2018, 2019, 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 9060 | 2813.7846 | 0 | 0 | 8080 | 2509.4238 | 0 | 0 | 8010 | 2487.6837 | 0 | 0 | 13540 | 4205.1482 | 0 | 0 | 19100 | 5931.9299 | 0 | 0 | 18630 | 5785.961 | 0 | 0 | 17740 | 5509.5517
Vegetation Management and Inspection | Quality assurance / quality control |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Open work orders |  | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Workforce Planning |  | N/A - Foundational | All Drivers, All Consequences | n/a | n/a | n/a | n/a | n/a | cost partially in Section 6 - Risk Methodology and Assessment |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | 7 | Consequence - PSPS | No other consequences reflected | 2018 – PSPS program initiated | 2023 GRC and 2022 WMCE | n/a | In compliance | R.18-12-005 |  |  | 1399.1783 | 1399.1783 | 209124.556 | 209124.556 | 9163.3797 | 9163.3797 | 249248.5438 | 249248.5438 | 5808.2114 | 5808.2114 | 196168.5894 | 196168.5894 | 1859.1013 | 1859.1013 | 41045.9537 | 41045.9537 | 3963.18 | 3963.18 | 93111.7094 | 93111.7094 | 4082.0754 | 4082.0754 | 95905.0607 | 95905.0607 | 4204.5377 | 4204.5377 | 98782.2125 | 98782.2125
PSPS | Other - PSPS |  | N/A - Foundational | N/A - Foundational | n/a - this section are support projects and programs | 2023 GRC for Wildfire Technology | n/a | n/a - this section are support projects and programs | n/a - this section are support projects and programs |  |  | 55637.8929 | 55637.8929 | 67387.3678 | 67387.3678 | 91783.9354 | 91783.9354 | 83307.342 | 83307.342 | 125786.5698 | 125786.5698 | 133300.285 | 133300.285 | 94900.2015 | 94900.2015 | 122933.5531 | 122933.5531 | 117392.5186 | 117392.5186 | 113084.2841 | 113084.2841 | 120914.2942 | 120914.2942 | 116476.8126 | 116476.8126 | 124541.723 | 124541.723 | 119971.117 | 119971.117

## Table 12
Utility | Pacific Gas and Electric Company | Notes: Quarterly Targets contained in table 12 are preliminary and subject to change to ensure they are align with PG&E's WMP filing on March 27, 2023.
Table No. | 12
Date Modified | 2023-02-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | Method of Verification | Comments
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Ground | 8.1.3.1.1 | Quantitative | Transmission Structures | 22417 | 27000 | 27000 | 14400 | 20000 | 20000 | 22000 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Climbing | 8.1.3.1.3 | Quantitative | Transmission Structures | 1429 | 1700 | 1700 | 960 | 1200 | 1200 | 1200 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Aerial | 8.1.3.1.2 | Quantitative | Transmission Structures | 19000 | 24000 | 24000 | 19000 | 20000 | 20000 | 19000 | Completed work orders
Grid Design, Operations and Maintenance | Perform transmission infrared inspections | 8.1.3.1.4 | Quantitative | Miles | 1650 | 3250 | 4000 | 1600 | 3100 | 4000 | 3500 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspections - Distribution | 8.1.3.2.1 | Quantitative | Distribution Poles | 190495 | 234648 | 234648 | 190805 | 233501 | 233501 | 244000 | Completed work orders
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Distribution | 8.1.3.3.1 | Quantitative | Distribution Substations | 46 | 52 | 52 | 68 | 76 | 76 | 78 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Transmission | 8.1.3.3.1 | Quantitative | Transmission Substations | 31 | 34 | 34 | 33 | 36 | 36 | 41 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 8.1.3.3.1 | Quantitative | Hydroelectric Substations and Powerhouses | 41 | 41 | 41 | 45 | 46 | 46 | 40 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Community Outreach and Engagement | Community Engagement - Surveys | 8.5.1.2 | Quantitative | Surveys | 1 | 1 | 2 | 1 | 1 | 2 | 2 | Survey results and analyses.
Vegetation Management and Inspection | LiDAR Routine Inspections - Transmission | 8.2.2.1 | Quantitative | Circuit Miles | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | LiDAR Contractor Work Complete Attestation - (Vegetation Management Project Management Database). Data is uploaded to VMPI2 mobile device for Pre-Inspectors
Vegetation Management and Inspection | Pole Clearing Program | 8.2.3.1 | Quantitative | Distribution poles | 57750 | 77000 | 77000 | 47250 | 63000 | 63000 | 52000 | List of all poles in VM database as of October 1, 2022. (PCD2 App) All exceptions must be accordingly documented in the system of record
Vegetation Management and Inspection | Defensible Space Inspections - Distribution Substation | 8.2.3.5 | Quantitative | Distribution Substations | 130 | 131 | 131 | 130 | 131 | 131 | 131 | Preventative Notification numbers for each defensible space inspection
Vegetation Management and Inspection | Defensible Space Inspections - Transmission Substation | 8.2.3.5 | Quantitative | Transmission Substations | 55 | 55 | 55 | 55 | 55 | 55 | 55 | Preventative Notification numbers for each defensible space inspection
Vegetation Management and Inspection | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 8.2.3.5 | Quantitative | Hydroelectric Substations and Powerhouses | 61 | 61 | 61 | 61 | 61 | 61 | 61 | Preventative Notification numbers for each defensible space inspection
Grid Design, Operations and Maintenance | Covered conductor installation | 8.1.2.1 | Quantitative | Circuit Miles |  |  | 420 |  |  | 470 | 580 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Undergrounding of electric lines and/or equipment | 8.1.2.2 | Quantitative | Circuit Miles |  |  | 350 |  |  | 450 | 550 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | 8.1.2.5.1 | Quantitative | Circuit Miles |  |  | 43 |  |  | 0 | 5 | As-built job package.
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | 8.1.2.5.1 | Quantitative | Transmission Lines |  |  | 20 |  |  | 22 | 25 | As-built job package
Grid Design, Operations and Maintenance | Motor Switch Operator (MSO) Switch Replacement | 8.1.2.10.3 | Quantitative | MSOs replacements |  |  | 20 |  |  | 47 | N/A | As-built job package
Grid Design, Operations and Maintenance | Other grid topology improvements to minimize risk of ignitions | 8.1.2.10 | Quantitative | Surge Arrestors |  |  | 663 |  |  | N/A | N/A | Completed work orders
Grid Design, Operations and Maintenance | Installation of System Automation Equipment – Distribution EPSS Protective Devices | 8.1.2.8.1 | Quantitative | Distribution Sectionalizing Devices |  |  | 75 |  |  | N/A | N/A | Completed work orders
Grid Design, Operations and Maintenance | Non-Exempt Expulsion Fuses | 8.1.2.10.5 | Quantitative | Fuses |  |  | 3000 |  |  | 3000 | 1500 | Completed work orders
Grid Design, Operations and Maintenance | Quality Assurance (QA) | 8.1.6.1 | Quantitative | % Confidence Level |  |  | 0.95 |  |  | 0.95 | 0.95 | Final reports and field guides for all audits.
Grid Design, Operations and Maintenance | Open Work Orders - Transmission | 8.1.7.1 | Quantitative | Transmission LC Tags |  |  | TBD |  |  | TBD | TBD | Completed notifications
Grid Design, Operations and Maintenance | Open Work Orders - Distribution | 8.1.7.2 | Quantitative | Distribution EC Tags |  |  | TBD |  |  | TBD | TBD | Completed notifications
Grid Design, Operations and Maintenance | Protective Equipment and Device Settings | 8.1.8.1.1 | Quantitative | Protective Device Controllers or Relays that are DCD capable |  |  | 500 |  |  | 400 | 250 | Report with the number of protective device controllers or relays that were DCD capable
Situational Awareness and Forecasting | Planned Improvements | 8.3.3.3 | Quantitative | Circuits |  |  | 40 |  |  | 40 | 40 | Completed job packages
Vegetation Management and Inspection | Fall-in Mitigation | 8.2.3.4 | Quantitative | Trees Removed |  |  | 15000 |  |  | 20000 | 25000 | Completed work orders
Vegetation Management and Inspection | Quality Assurance / Quality Control | 8.2.5 | Quantitative | % Pass Rate |  |  | 0.95 |  |  | 0.95 | 0.95 | QV VM final reports

## Table 14
Utility | Pacific Gas and Electric Company
Table No. | 14
Date Modified | 2023-02-01
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution | 855.524 | 656.744 | 198.7799 | 284.7828 | 163.0337 | 42.0053 | 79.7438 | n/a | 4.75 | 2.3061 | n/a | n/a | n/a | 41.8484 | n/a | n/a
HFTD Tier 2/3 Distribution | 24291.0179 | 22425.256 | 1865.7619 | 177.0372 | 74.7102 | 75.3981 | 26.9288 | n/a | 4.75 | 126.6698 | n/a | n/a | n/a | 392.792 | n/a | n/a
Non-HFTD Transmission | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
HFTD Tier 2/3 Transmission | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Comments for Table 14: The data presented in this table are based on the best knowledge that PG&E has as of January 31, 2023. As better data becomes available, this will be updated in the quarterly updates. Note 1: Ignition Likelihood Metric: Ignition likelihood scaled from WDRM v3 to historical CPUC reportable probabilities Note 2: Equipment Likelihood of Ignition: WTRM produces as probability of equipment failure, not a probability of ignition Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD

## Table 15
Utility | Pacific Gas and Electric Company
Table No. | 15
Date Modified | 2023-02-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
HFTD
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
INDIAN FLAT 1104CB | Circuit Segment | Distribution | 13.7984 | Top 5% Risk | HFTD T2/T3 | 118.4654 | 118.4654 | 0 | 0.092864 | 0.052375 | 0.023498 | 0.016991 | n/a | 0 | 1275.6892 | n/a | n/a | n/a | 0 | n/a | n/a
BONNIE NOOK 1101CB | Circuit Segment | Distribution | 17.8044 | Top 5% Risk | HFTD T2/T3 | 91.2757 | 85.7859 | 5.49 | 0.12592 | 0.049897 | 0.061604 | 0.014418 | n/a | 1.0833 | 681.277 | n/a | n/a | n/a | 5.0676 | n/a | n/a
ALLEGHANY 1102CB | Circuit Segment | Distribution | 18.911 | Top 5% Risk | HFTD T2/T3 | 88.6057 | 86.0352 | 2.57 | 0.13492 | 0.075839 | 0.047435 | 0.01165 | n/a | 0.91667 | 637.6545 | n/a | n/a | n/a | 2.8042 | n/a | n/a
OAKHURST 110310140 | Circuit Segment | Distribution | 18.7573 | Top 5% Risk | HFTD T2/T3 | 88.4072 | 87.6743 | 0.73 | 0.1444 | 0.067327 | 0.061028 | 0.016049 | n/a | 0.16667 | 607.1449 | n/a | n/a | n/a | 4.397 | n/a | n/a
SILVERADO 2104515946 | Circuit Segment | Distribution | 19.0559 | Top 5% Risk | HFTD T2/T3 | 85.6002 | 80.7385 | 4.86 | 0.1818 | 0.077638 | 0.086109 | 0.018052 | n/a | 1.6667 | 444.1088 | n/a | n/a | n/a | 2.917 | n/a | n/a
HIGHLANDS 1102628 | Circuit Segment | Distribution | 15.7833 | Top 5% Risk | HFTD T2/T3 | 75.5797 | 75.4228 | 0.16 | 0.054274 | 0.031724 | 0.0096317 | 0.012919 | n/a | 0.83333 | 1389.6546 | n/a | n/a | n/a | 0.18832 | n/a | n/a
UPPER LAKE 11011276 | Circuit Segment | Distribution | 12.2879 | Top 5% Risk | HFTD T2/T3 | 67.2154 | 67.2154 | 0 | 0.081244 | 0.040321 | 0.031675 | 0.0092482 | n/a | 0 | 827.3291 | n/a | n/a | n/a | 0 | n/a | n/a
MIDDLETOWN 110148212 | Circuit Segment | Distribution | 9.8342 | Top 5% Risk | HFTD T2/T3 | 58.8187 | 58.3023 | 0.52 | 0.061009 | 0.022972 | 0.03152 | 0.0065178 | n/a | 0.41667 | 955.6277 | n/a | n/a | n/a | 1.2392 | n/a | n/a
APPLE HILL 21026552 | Circuit Segment | Distribution | 13.0241 | Top 5% Risk | HFTD T2/T3 | 57.1112 | 55.7622 | 1.35 | 0.073447 | 0.030361 | 0.032036 | 0.01105 | n/a | 0.58333 | 759.2213 | n/a | n/a | n/a | 2.3126 | n/a | n/a
NOTRE DAME 11042028 | Circuit Segment | Distribution | 11.3904 | Top 5% Risk | HFTD T2/T3 | 50.0967 | 49.5273 | 0.57 | 0.055547 | 0.018694 | 0.030871 | 0.0059816 | n/a | 0.83333 | 891.6258 | n/a | n/a | n/a | 0.68325 | n/a | n/a
CLAYTON 221296224 | Circuit Segment | Distribution | 10.1751 | Top 5% Risk | HFTD T2/T3 | 47.284 | 46.8169 | 0.47 | 0.050286 | 0.02571 | 0.016527 | 0.008049 | n/a | 0.66667 | 931.0051 | n/a | n/a | n/a | 0.70065 | n/a | n/a
ANTLER 11011384 | Circuit Segment | Distribution | 10.3375 | Top 5% Risk | HFTD T2/T3 | 46.8765 | 46.4286 | 0.45 | 0.089103 | 0.033176 | 0.043007 | 0.012921 | n/a | 0.083333 | 521.0645 | n/a | n/a | n/a | 5.3748 | n/a | n/a
MONTICELLO 1101654 | Circuit Segment | Distribution | 8.302 | Top 5% Risk | HFTD T2/T3 | 43.061 | 42.0937 | 0.97 | 0.043932 | 0.021006 | 0.013379 | 0.0095464 | n/a | 0.91667 | 958.167 | n/a | n/a | n/a | 1.0552 | n/a | n/a
BALCH NO 1 1101105414 | Circuit Segment | Distribution | 7.471 | Top 5% Risk | HFTD T2/T3 | 42.1929 | 42.179 | 0.01 | 0.02666 | 0.014398 | 0.0047943 | 0.0074682 | n/a | 0.083333 | 1582.0883 | n/a | n/a | n/a | 0.16639 | n/a | n/a
CURTIS 170356972 | Circuit Segment | Distribution | 8.4156 | Top 5% Risk | HFTD T2/T3 | 41.0987 | 40.9418 | 0.16 | 0.032244 | 0.016023 | 0.0053831 | 0.010838 | n/a | 0.083333 | 1269.7508 | n/a | n/a | n/a | 1.8821 | n/a | n/a
MONTICELLO 1101630 | Circuit Segment | Distribution | 4.9383 | Top 5% Risk | HFTD T2/T3 | 41.0785 | 40.1799 | 0.9 | 0.041905 | 0.020098 | 0.013381 | 0.0084256 | n/a | 0.91667 | 958.8298 | n/a | n/a | n/a | 0.98028 | n/a | n/a
PINE GROVE 1101CB | Circuit Segment | Distribution | 5.0523 | Top 5% Risk | HFTD T2/T3 | 31.9963 | 30.9366 | 1.06 | 0.044131 | 0.020752 | 0.01559 | 0.0077891 | n/a | 0.41667 | 701.0238 | n/a | n/a | n/a | 2.5434 | n/a | n/a
BUCKS CREEK 1101CB | Circuit Segment | Distribution | 4.8133 | Top 5% Risk | HFTD T2/T3 | 28.5059 | 28.5059 | 0 | 0.030079 | 0.020746 | 0.006401 | 0.0029323 | n/a | 0 | 947.6914 | n/a | n/a | n/a | 0 | n/a | n/a
SILVERADO 2104646776 | Circuit Segment | Distribution | 5.6861 | Top 5% Risk | HFTD T2/T3 | 26.5899 | 22.9267 | 3.66 | 0.063662 | 0.022366 | 0.035897 | 0.0053984 | n/a | 1.5 | 360.1334 | n/a | n/a | n/a | 2.4421 | n/a | n/a
CALISTOGA 1102131531 | Circuit Segment | Distribution | 5.042 | Top 5% Risk | HFTD T2/T3 | 26.0276 | 25.3574 | 0.67 | 0.054215 | 0.016667 | 0.034367 | 0.0031813 | n/a | 0.83333 | 467.7204 | n/a | n/a | n/a | 0.8042 | n/a | n/a
APPLE HILL 1104CB | Circuit Segment | Distribution | 5.6478 | Top 5% Risk | HFTD T2/T3 | 16.8603 | 15.7803 | 1.08 | 0.042343 | 0.020006 | 0.015804 | 0.0065331 | n/a | 0.5 | 372.6777 | n/a | n/a | n/a | 2.16 | n/a | n/a
MIDDLETOWN 1101171414 | Circuit Segment | Distribution | 3.5913 | Top 5% Risk | HFTD T2/T3 | 16.553 | 16.5203 | 0.03 | 0.023449 | 0.011498 | 0.010033 | 0.0019176 | n/a | 1 | 704.5098 | n/a | n/a | n/a | 0.032703 | n/a | n/a
ELECTRA 1102CB | Circuit Segment | Distribution | 2.6041 | Top 5% Risk | HFTD T2/T3 | 13.9336 | 13.9321 | 0 | 0.021292 | 0.013965 | 0.0026691 | 0.0046577 | n/a | 0.25 | 654.3409 | n/a | n/a | n/a | 0.0061624 | n/a | n/a
ORO FINO 1102CB | Circuit Segment | Distribution | 2.7342 | Top 5% Risk | HFTD T2/T3 | 12.5973 | 12.3594 | 0.24 | 0.020689 | 0.0094052 | 0.009169 | 0.002115 | n/a | 0.91667 | 597.3859 | n/a | n/a | n/a | 0.25945 | n/a | n/a
FRENCH GULCH 1101CB | Circuit Segment | Distribution | 2.7103 | Top 5% Risk | HFTD T2/T3 | 12.2201 | 11.8723 | 0.35 | 0.016126 | 0.010391 | 0.0022013 | 0.0035338 | n/a | 0.16667 | 736.2099 | n/a | n/a | n/a | 2.0868 | n/a | n/a
PARADISE 1103283794 | Circuit Segment | Distribution | 2.5507 | Top 5% Risk | HFTD T2/T3 | 12.1216 | 11.7003 | 0.42 | 0.017189 | 0.0083857 | 0.0054943 | 0.003309 | n/a | 1.25 | 680.6834 | n/a | n/a | n/a | 0.33701 | n/a | n/a
PARADISE 11061212 | Circuit Segment | Distribution | 2.3681 | Top 5% Risk | HFTD T2/T3 | 12.042 | 8.9653 | 3.08 | 0.022286 | 0.010355 | 0.0083336 | 0.0035978 | n/a | 1.0833 | 402.2767 | n/a | n/a | n/a | 2.8401 | n/a | n/a
CRESTA 1101103126 | Circuit Segment | Distribution | 0.87202 | Top 5% Risk | HFTD T2/T3 | 4.9548 | 4.9123 | 0.04 | 0.006334 | 0.0035102 | 0.0022348 | 0.00058905 | n/a | 1.5833 | 775.5367 | n/a | n/a | n/a | 0.026835 | n/a | n/a
CRESTA 1101546650 | Circuit Segment | Distribution | 0.89675 | Top 5% Risk | HFTD T2/T3 | 4.3588 | 4.3447 | 0.01 | 0.0062118 | 0.0041788 | 0.0014636 | 0.0005694 | n/a | 1.5833 | 699.4236 | n/a | n/a | n/a | 0.0089451 | n/a | n/a
MONTICELLO 1101CB | Circuit Segment | Distribution | 0.53696 | Top 5% Risk | HFTD T2/T3 | 3.063 | 3.063 | 0 | 0.0031223 | 0.0018583 | 0.00066244 | 0.00060162 | n/a | 0 | 980.9878 | n/a | n/a | n/a | 0 | n/a | n/a
TIGER CREEK 0201CB | Circuit Segment | Distribution | 0.39611 | Top 5% Risk | HFTD T2/T3 | 2.3021 | 2.2984 | 0 | 0.0025515 | 0.0013444 | 0.001006 | 0.00020108 | n/a | 0.5 | 900.8369 | n/a | n/a | n/a | 0.0072479 | n/a | n/a
INDIAN FLAT 11044440 | Circuit Segment | Distribution | 0.23656 | Top 5% Risk | HFTD T2/T3 | 1.7414 | 1.7414 | 0 | 0.0017945 | 0.0010988 | 0.00037872 | 0.00031702 | n/a | 0 | 970.3859 | n/a | n/a | n/a | 0 | n/a | n/a
CALPINE 1144304 | Circuit Segment | Distribution | 0.046358 | Top 5% Risk | HFTD T2/T3 | 1.714 | 1.703 | 0.01 | 0.0021465 | 0.0016636 | 0.0002979 | 0.00018491 | n/a | 1.4167 | 793.4165 | n/a | n/a | n/a | 0.007736 | n/a | n/a
APPLE HILL 2102CB | Circuit Segment | Distribution | 0.16914 | Top 5% Risk | HFTD T2/T3 | 1.4303 | 1.3798 | 0.05 | 0.0017415 | 0.00083934 | 0.00057424 | 0.00032797 | n/a | 0.58333 | 792.2561 | n/a | n/a | n/a | 0.086734 | n/a | n/a
MIDDLETOWN 1103CB | Circuit Segment | Distribution | 0.052964 | Top 5% Risk | HFTD T2/T3 | 1.0905 | 1.0905 | 0 | 0.0025189 | 0.0016727 | 0.00038566 | 0.00046059 | n/a | 0 | 432.9305 | n/a | n/a | n/a | 0 | n/a | n/a
PLACERVILLE 210658118 | Circuit Segment | Distribution | 0.10823 | Top 5% Risk | HFTD T2/T3 | 0.90325 | 0.89064 | 0.01 | 0.0010404 | 0.00063595 | 0.00016606 | 0.00023836 | n/a | 0.58333 | 856.0784 | n/a | n/a | n/a | 0.021609 | n/a | n/a
BALCH NO 1 1101CB | Circuit Segment | Distribution | 0.0137 | Top 5% Risk | HFTD T2/T3 | 0.81633 | 0.81633 | 0 | 0.00049446 | 0.00023641 | 0.00016333 | 9.4717e-05 | n/a | 0 | 1650.9566 | n/a | n/a | n/a | 0 | n/a | n/a
ALLEGHANY 11021101/2 | Circuit Segment | Distribution | 0.014692 | Top 5% Risk | HFTD T2/T3 | 0.33724 | 0.33724 | 0 | 0.00046721 | 0.00028559 | 0.00013775 | 4.387e-05 | n/a | 0 | 721.8028 | n/a | n/a | n/a | 0 | n/a | n/a
CALPINE 1144962 | Circuit Segment | Distribution | 0.039372 | Top 5% Risk | HFTD T2/T3 | 0.20797 | 0.20797 | 0 | 0.00024846 | 0.00020162 | 1.8626e-05 | 2.8214e-05 | n/a | 0 | 837.0146 | n/a | n/a | n/a | 0 | n/a | n/a
CAMP EVERS 2105BL 2101 | Circuit Segment | Distribution | 0.0032255 | Top 5% Risk | HFTD T2/T3 | 0.091574 | 0.091574 | 0 | 0.006562 | 0.0010484 | 0.0054105 | 0.00010305 | n/a | 0 | 13.9552 | n/a | n/a | n/a | 0 | n/a | n/a
MARIPOSA 2101929360 | Circuit Segment | Distribution | 0.067118 | Top 5% Risk | HFTD T2/T3 | 0.085249 | 0.085249 | 0 | 0.00016024 | 0.00013154 | 5.7355e-06 | 2.2965e-05 | n/a | 0 | 531.9936 | n/a | n/a | n/a | 0 | n/a | n/a
Comments for Table 15: The data presented in this table are based on the best knowledge that PG&E has as of January 31, 2023. As better data becomes available, this will be updated in the quarterly updates. Note 1: Burn Probability Metric: As described in Section 6.2, Burn Probability is a preliminary step in wildfire ccalculation, PG&E does not break this apart separately. Note 2: Wildfire Hazard Intensity Metric: PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not in the current WDRM v3. Note 3: Wildfire Exposure Potential, Wildfire Vulnerability, PSPS Exposure Poential, & Vilnerability of Community to PSPS Metircs: PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v3 and PSPS. Note 4: Ignition likelihood Metric: Ignition likelihood scaled from WDRM v3 to historical CPUC reportable probabilities