## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | PGE
Report Year |  | 2022
Report Quarter |  | Q1
Submission Date |  | 2022-05-02
Definition of fields
6/23 WSD Notes | Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
Should tie to QDR Spatial ID, where applicable | I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
Populate all Quarter Targets (cummulative for Q2 submission) | N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail | Supporting File links
PGE | 2022-05-02 | Risk Assessment & Mapping | 7.3.1. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | 3 | A.01 - Distribution Modeling Enhancements - Equipment Failure and Contact From Object |  | PGE_Risk Assessment & Mapping_Ignition probability mapping showing the probability of ignition along the electric lines and equipment __2022 | 358 | [10 empty] | Develop additional Distribution Equipment Failure (EFF) and Distribution Contact From Object (CFO) sub-models. Conduct assessment to determine whether newly developed sub-models should be included in the WDRM model. | First drafts of the Equipment Failure and Contact from Object models were included as part of the 2022 WDRM v3. Scoping work for improved models as outlined in the schedule will begin in Q2 2022. |  |  |  | In Progress
PGE | 2022-05-02 | Risk Assessment & Mapping | 7.3.1. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | 3 | A.02 - Transmission Modeling Enhancements - Threat and Hazard Risk Drivers |  | PGE_Risk Assessment & Mapping_Ignition probability mapping showing the probability of ignition along the electric lines and equipment __2022 | 358 | [10 empty] | Develop Threat and Hazard (Risk drivers) sub-models that cover: Threats (e.g., Atmospheric corrosion, Underground corrosion, Fatigue, Mechanical Wear, Decay, Contamination, Vibration), and Hazards (primarily Wind). Conduct assessment to determine whether newly developed sub-models are to be included in the WTRM model. | The first version of all committed Threat\Hazard models besides one (Insulator-Contamination) that have the greatest impact to the safety of PG&E’s Transmission line assets have been deployed. The last remaining model, Insulator-Contamination, is targeted to be completed by April 30, 2022. |  |  |  | In Progress
PGE | 2022-05-02 | Risk Assessment & Mapping | 7.3.1. | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | 4 | A.03 - PSPS Consequence Model |  | PGE_Risk Assessment & Mapping_Initiative mapping and estimation of wildfire and PSPS risk-reduction impact __2022 | 361 | [10 empty] | Conduct an assessment of the PSPS Consequence model to inform if it is fit for use to inform PSPS mitigation plans to minimize customer impact. | Soliciting stakeholder feedback and usage through meetings and review of results as part of the Undergrounding mileage selection framework. Delay due to resource focus on supporting Undergrounding Tool and Integrated Risk Spend Efficiency for System Hardening team which stems from lack of resources dedicated to workstream; divergence of priorities due to 2 members of the team resigning and 1 on emergency family leave. |  |  |  | Delayed | PG&E will shift its resource priorities to correct this delay and ensure this target is timely completed.
PGE | 2022-05-02 | Risk Assessment & Mapping | 7.3.1. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | 5 | A.04 - Wildfire Consequence Model Enhancements - Ingress/Egress |  | PGE_Risk Assessment & Mapping_Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment __2022 | 364 | [10 empty] | Develop an approach on how to incorporate ingress/egress into the Wildfire Consequence Model. | Egress model has been delivered by UCLA and the RAVE model from Technosylva. Next step is to identify and assign resources to apply and explore models to identify preferred application to include Egress in the risk models. |  |  |  | Delayed | By 4/18/2022, discuss with Management to identify and make additional resources or approvals available.
PGE | 2022-05-02 | Risk Assessment & Mapping | 7.3.1. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | 5 | A.05 - Wildfire Consequence Model Enhancements - Resistance to Control |  | PGE_Risk Assessment & Mapping_Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment __2022 | 364 | [10 empty] | Evaluate an approach to incorporate "Resistance to Control" (i.e., TDI) into the Wildfire Consequence Model. Resistance to Control is the relative difficulty of constructing and holding a control line as affected by resistance to line construction and by fire behavior. | Contractual arrangements for the resistance to control model outputs from the Technosylva RAVE model were completed. |  |  |  | Delayed | By 4/18/2022 , discuss with Management to identify and make additional resources or approvals available.
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Advanced weather monitoring and weather stations |  | 1 | B.01 - FPI and IPW Modeling - Revision Evaluation |  | PGE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations __2022 | 367 | [10 empty] | Evaluate running the FPI and IPW Models with the ensemble mean output of the POMMS-EPS. | External vendor and internal teams have built out ensemble mean versus deterministic verification tools so we can track forecast performance each quarter. In addition, external vendor is working on adjusting the dead fuel and live fuel moisture models to accept either deterministic or ensemble mean forecast data as input. |  |  |  | In Progress
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Advanced weather monitoring and weather stations |  | 1 | B.02 - Weather Stations -Installations and Optimizations |  | PGE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations __2022 | 374 | # of Weather Stations | 100 | 5 | 40 | 85 | 100 | 5 |  |  |  | Install or Optimize 100 weather stations. A unit is deemed "installed" when it is in service and verified as operating when initially installed. A unit is deemed "optimized" when a weather station is moved from an existing location to a new location for the purposes of improving our understanding of the weather conditions in the area. | In Q1, PG&E installed 5 weather stations. |  |  |  | In Progress
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Advanced weather monitoring and weather stations |  | 1 | B.03 - High-Definition Cameras - Installations |  | PGE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations __2022 | 378 | # of HD Cameras | 98 | 8 | 51 | 90 | 98 | 21 |  |  |  | Install 98 new cameras that are facing HFTD Tier 2 or Tier 3 viewsheds. In the case a site is destroyed and a camera can be replaced / relocated nearby with a different visual coverage than the original, this will count as a new installation. | In Q1, PG&E installed 21 cameras. |  |  |  | In Progress
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Continuous monitoring sensors |  | 2 | B.04 - Distribution Fault Anticipation (DFA) - Installations |  | PGE_Situational Awareness & Forecasting_Continuous monitoring sensors __2022 | 392 | # of DFA Sensors | 40 | 5 | 10 | 25 | 40 | 12 |  |  |  | Install 40 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor per circuit at initiating substation. | In Q1, PG&E installed 12 sensors. |  |  |  | In Progress
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Continuous monitoring sensors |  | 2 | B.05 - Early Fault Detection (EFD) - Installations |  | PGE_Situational Awareness & Forecasting_Continuous monitoring sensors __2022 | 395 | # of circuits | 2 | 0 | 0 | 1 | 2 | 0 |  |  |  | Install Early Fault Detection (EFD) sensors on 2 circuits feeding into HFTD areas or HFRA. | No sensors were installed in Q1, but none were planned to be installed in Q1. Therefore, this initiative remains on track for completion by the end of the year. |  |  |  | In Progress
PGE | 2022-05-02 | Situational Awareness & Forecasting | 7.3.2. | Continuous monitoring sensors |  | 2 | B.06 - Line Sensor - Installations |  | PGE_Situational Awareness & Forecasting_Continuous monitoring sensors __2022 | 401 | # of circuits | 40 | 0 | 10 | 40 | 40 | 0 |  |  |  | Install Line Sensor devices on 40 circuits feeding into HFTD areas or HFRA to cover mainline and major tap lines in areas meeting minimum load requirements and within cellular coverage areas to provide visibility. | No sensors were installed in Q1, but none were planned to be installed in Q1. Therefore, this initiative remains on track for completion by the end of the year. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Expulsion fuse replacement |  | 7 | C.01 - Expulsion Fuse - Removal |  | PGE_Grid Design & System Hardening_Expulsion fuse replacement __2022 | 446 | # of fuses | 3000 | 300 | 1360 | 2430 | 3000 | 831 |  |  |  | Remove 3,000 non-exempt fuses/ cutouts identified on distribution poles in HFTD areas or HFRA. | In Q1, PG&E installed 831 non-exempt fuses. Note that completed units reported are subject to change due to lag time in QA validation/approval and SAP transaction processing. The Q1 actuals are based on data validated in SAP on April 8th and could change in future reporting based on further validation. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | C.02 - Distribution Sectionalizing Devices - Install and SCADA commission | GhLogID | PGE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _GhLogID_2022 | 450 | # of distribution sectionalizing devices | 100 | 0 | 70 | 100 | 100 | 4 |  |  |  | Install and SCADA commission 100 new PSPS SCADA enabled Distribution Sectionalizing devices. | In Q1, PG&E installed 4 PSPS Distribution Sectionalizing devices, which includes construction and SCADA commissioning. Note that supply chain issues, as well as permitting, environmental and land dependencies may introduce potential risk to the plan in the future months. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | C.03 - Transmission Line Sectionalizing - Install and SCADA commission | GhLogID | PGE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _GhLogID_2022 | 454 | # of switches | 15 | 1 | 8 | 15 | 15 | 1 |  |  |  | Install and SCADA commission 15 transmission line switches on lines that traverse the HFTD areas. The switches themselves may not be located in the HFTD areas but can be used to support customer impact reduction. | In Q1, PG&E completed 1 transmission line switch on lines that traverse the HFTD areas was completed. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | C.04 - Distribution Line Motorized Switch Operator (MSO) - Replacements | GhLogID | PGE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _GhLogID_2022 | 457 | # of MSOs | 50 | 0 | 23 | 39 | 50 | 1 |  |  |  | Replace at least 50 of the 104 remaining Motorized Switch Operators that are located within or are energizing line sections that feed into HFTD areas or HFRA. | In Q1, PG&E completed installation of 1 MSO device installation, which includes construction and SCADA commissioning. Note that supply chain issues, as well as permitting, environmental and land dependencies may introduce potential risk to the plan in the future months. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Installation of system automation equipment |  | 9 | C.05 - SCADA Recloser Equipment - Installations |  | PGE_Grid Design & System Hardening_Installation of system automation equipment __2022 | 462 | # of reclosers | 17 | 0 | 6 | 13 | 17 | 0 |  |  |  | Install 17 substation SCADA enabled reclosers on circuits serving line sections that feed into HFTD areas or HFRA, barring any exceptions due to connectivity issues necessary to SCADA-enable the recloser. Footnote: There may be connectivity issues for some SCADA reclosers that will require manual setting updates, but there is still benefit in installing the recloser to get the sectionalization on the circuit. | The program had no Q1 target, and no units were Commissioned. Work is expected to ramp up in Q2 as the program is targeting to complete 6 SCADA reclosers. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Installation of system automation equipment |  | 9 | C.06 - Fuse Savers (Single Phase Reclosers) - Installations |  | PGE_Grid Design & System Hardening_Installation of system automation equipment __2022 | 465 | # of fuse saver sets | 80 | 0 | 27 | 63 | 80 | 2 |  |  |  | Install 80 single phase recloser sets in HFTD areas or HFRA. | In Q1, PG&E installed 2 single phase reclosers. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | C.07 - Temporary Distribution Microgrids |  | PGE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event __2022 | 470 | # of PIHs | 4 | 0 | 0 | 2 | 4 | 0 |  |  |  | Make operationally ready at least four (4) additional Distribution Microgrid Pre-installed Interconnection Hubs (PIHs). This target will include 1 PIH that completed construction in December 2021 and will be made ready to operate in 2022. | The project management team made progress obtaining/extending permitting and securing major material and equipment needed for electrical construction, including Viper line reclosers that needed additional lead time for safety enhancement. Clearances have been submitted and scheduled for two sites to begin construction in Q2 (Lucerne and Arnold). To ensure temporary generation is available to energize these sites, PG&E issued a Temporary Generation Request for Proposals and began evaluation on competitive bids. Cross-functional alignment planning across engineering teams took place to ensure energization plans for constructed sites can be completed in a timely fashion once generators are available. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | C.08 - Rincon Transformer Fuse - Replacement |  | PGE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event __2022 | 486 | # of fuses | 1 | 0 | 1 | 1 | 1 | 0 |  |  |  | Replace the fuse with a circuit switcher on the Rincon Transformer Bank 1. | In-Service date on track for Q2. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | C.09 - Emergency Back-up Generation – Equip PG&E Service Centers & Materials Distribution Centers |  | PGE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event __2022 | 489 | # of sites | 15 | 4 | 9 | 13 | 15 | 4 |  |  |  | Equip 15 PG&E Service Centers or Materials Distribution Centers sites with emergency back-up generation to allow the sites to operate with the same amount of functionality as they would if they were being fed from their normal utility power source. | In Q1, PG&E completed the cutovers on four 4 sites. Fortuna SC, Quincy SC, and Clearlake SC were completed in January. Woodland SC was successfully completed in February. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Undergrounding of electric lines and/or equipment |  | 16 | C.10 - 10K Undergrounding | GhLogID | PGE_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _GhLogID_2022 | 523 | # of circuit miles | 175 | 23 | 70 | 131 | 175 | 35.2 |  |  |  | Complete at least 175 circuit miles of undergrounding work. The 175 circuit mile target includes undergrounding taking place as part of both System Hardening (Section 7.3.3.17.1), Butte County Rebuild efforts (Section 7.3.3.17.6) including a small volume of previously hardened overhead lines that are being placed underground, and any other undergrounding work performed in HFTD or fire rebuild areas. | In Q1, PG&E completed 35.2 undergrounding miles (31.1 from the System Hardening Program and 4.1 from the Butte Rebuild effort). |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | C.11 - System Hardening - Distribution |  | PGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2022 | 537 | # of circuit miles | 470 | 85 | 230 | 375 | 470 | 95.1 |  |  |  | Complete at least 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding and removal of overhead lines in HFTD or buffer zone areas with the exception of any mileage being undergrounded and tracked separately as part of our Butte County Rebuild efforts (Section 7.3.3.17.6). | In Q1, PG&E completed 95.1 miles of system hardening. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | C.12 - System Hardening - Transmission |  | PGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2022 | 548 | # of circuit miles | 32.6 | 4.2 | 4.6 | 4.6 | 32.6 | 4.2 |  |  |  | Remove or replace 32 circuit miles of transmission conductor on lines traversing the HFTD areas or HFRA. | In Q1, PG&E completed 4.2 miles of removing or replacing transmission conductor. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | C.13 - Surge Arrestor - Removals |  | PGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2022 | 552 | # of surge arrestors | 4590 | 220 | 1590 | 3270 | 4590 | 1202 |  |  |  | Remove all of the remaining non-exempt surge arrestors in HFTD areas (based on the known population of 4,590 surge arrestors as of January 1, 2022) through replacement with exempt equipment. | In Q1, PG&E completed the removal of 1,202 surge arrestors. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | C.14 - Remote Grid - Operate New SPS Units |  | PGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2022 | 558 | # of Remote Grids | 2 | 0 | 0 | 0 | 2 | 0 |  |  |  | Operate 2 new Remote Grid Standalone Power System (SPS) units | The Remote Grid Program executed contracts for four Standalone Power Systems (SPS) units in the third week of February. Two of these four units are scheduled to be online by December 2022. For these projects the vendor has ordered the longest-lead major equipment (generator sets) and detailed engineering design is nearing 90% complete. PG&E has initiated line removal scoping, permitting outreach, and the Environmental Review process. Unexpected supply chain delays in major equipment delivery pose schedule risks so the team is working to expedite delivery. At conclusion of 30% design, our contractor notified us that the remainder of Engineer/Procure/Construct timelines will be longer than expected due to COVID related delays. Global supply chain issues delaying generator procurement, extended design and contracting durations, and incremental civil scopes identified on 2 projects were the primary causes of the delay. |  |  |  | Delayed | The below actions are being taken to mitigate these delays: (1) Expedite internal approvals for contracts; (2) Civil work has been re-sequenced for earlier start; (3) Executive sponsor reaching out to key supplier to expedite long lead generator procurement; and (4) Contingency planning is in process for early commissioning and interim operations if generator sets are late as forecast.
PGE | 2022-05-02 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | C.15 - Butte County Rebuild - Undergrounding |  | PGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2022 | 566 | # of primary circuit miles | 55 | 1 | 12 | 25 | 55 | 3.88 |  |  |  | Complete 55 circuit miles of undergrounding work as part of the Butte County Rebuild program. | In Q1, PG&E completed 3.9 miles of undergrounding work as a part of the Butte County Rebuild program. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Detailed inspections of distribution electric lines and equipment |  | 1 | D.01 - Detailed Inspections - Distribution | AiLogID | PGE_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _AiLogID_2022 | 569 | # of poles | 396000 | 20379 | 305546 | 396000 | 396000 | 6235 |  |  |  | Complete detailed inspections on a minimum of 396,000 distribution poles, which were identified in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any poles discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any poles discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | In Q1, PG&E completed detailed ground inspections on 6,235 distribution poles. |  |  |  | Delayed | Delays with execution were driven by transitioning from three contractors to a single contractor. This resulted in delayed onboarding, required training and new skills assessment required to start work. Contractor has been secured and onboarding training and skills assessment has been completed. The Recovery Plan date to be back on track with the WMP Target is 6/4/2022.
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | D.02 - Detailed Inspection Transmission – Ground | AiLogID | PGE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _AiLogID_2022 | 574 | # of structures | 39191 | 7329 | 39191 | 39191 | 39191 | 2783 |  |  |  | Complete detailed ground inspections on a minimum of 39,000 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | In Q1, PG&E completed detailed ground inspections on 2,783 transmission structures. |  |  |  | Delayed | Delays with execution were driven by transitioning from three contractors to a single contractor. This resulted in delayed onboarding, required training and new skills assessment required to start work. Contractor has been secured and onboarding training and skills assessment has been completed. The Recovery Plan date to be back on track with the WMP Target is 6/25/2022.
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | D.03 - Detailed Inspection Transmission – Climbing | AiLogID | PGE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _AiLogID_2022 | 574 | # of structures | 2204 | 661 | 1984 | 2204 | 2204 | 1172 |  |  |  | Complete detailed climbing inspections on a minimum of 1,800 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | In Q1, PG&E completed 1,172 climbing inspections. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | D.04 - Detailed Inspection Transmission – Aerial | AiLogID | PGE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _AiLogID_2022 | 574 | # of structures | 39191 | 12485 | 39191 | 39191 | 39191 | 8202 |  |  |  | Complete detailed aerial inspections on a minimum of 39,000 transmission structures in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets discovered after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets discovered after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | In Q1, PG&E completed aerial inspections on 8,202 transmission structures. |  |  |  | Delayed | Delays with execution were driven by contract reviews as we transitioned from six contractors in 2021 down to three contractors in 2022. The Recovery Plan date to be back on track with the WMP Target is 6/25/2022.
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Infrared inspections of distribution electric lines and equipment |  | 4 | D.05 - Infrared Inspections - Distribution |  | PGE_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment __2022 | 582 | # of circuit miles | 9000 | 0 | 0 | 4000 | 9000 | 0 |  |  |  | Complete infrared inspections on a minimum of 9,000 distribution circuit miles in PG&E's asset registry as of January 1, 2022, in HFTD areas or HFRA, barring External Factors. Any assets identified after January 1, 2022 with a field installation date on or before 2020 will be inspected within 90 days of when added to the asset registry. Any assets identified after January 1, 2022 with a field installation date in 2021 or 2022 will not be in scope for inspection as part of this 2022 WMP target. | In Q1, 0 miles were inspected. Infrared Inspections - Distributions plans to start inspections in Q3 and will complete by end of year 2022. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Substation inspections |  | 15 | D.06 - Supplemental Inspections - Substation Distribution | AiLogID | PGE_Asset Management & Inspections_Substation inspections _AiLogID_2022 | 624 | # of Distribution Substations | 86 | 0 | 65 | 86 | 86 | 0 |  |  |  | Complete supplemental inspections on 86 distribution substations in HFTD areas or HFRA, barring External Factors. | In Q1, PG&E completed 10 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. PG&E is committed to meet its target for 2022. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Substation inspections |  | 15 | D.07 - Supplemental Inspections - Substation Transmission | AiLogID | PGE_Asset Management & Inspections_Substation inspections _AiLogID_2022 | 624 | # of Transmission Substations | 43 | 0 | 34 | 43 | 43 | 0 |  |  |  | Complete supplemental inspections on 43 transmission substations within HFTD areas or HFRA, barring External Factors. | In Q1, PG&E had completed 3 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Other Substation inspections Hydro Generation |  | 16 | D.08 - Supplemental Inspections - Hydroelectric Substations and Powerhouses |  | PGE_Asset Management & Inspections_Other Substation inspections Hydro Generation__2022 | 628 | # of Hydroelectric Substations and Powerhouses | 52 | 0 | 42 | 52 | 52 | 0 |  |  |  | Complete supplemental inspections on 52 Hydroelectric Generation Substations and Powerhouses within HFTD areas or HFRA, barring External Factors. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | In Q1, PG&E had completed 3 aerial inspections. Per the WMP, units are completed when all three components of inspections (Ground, Aerial and Infrared) are finished. |  |  |  | In Progress
PGE | 2022-05-02 | Asset Management & Inspections | 7.3.4. | Quality assurance / quality control of inspections |  | 14 | D.09 - Asset Inspections - Quality Assurance |  | PGE_Asset Management & Inspections_Quality assurance / quality control of inspections __2022 | 619 | [10 empty] | Perform Transmission and Distribution system inspection quality audits prioritizing HFTD/HFRA areas. Statistically valid methodology parameters, such as a confidence level of 95%, will be utilized. | The Transmission System Inspections audit began in March and continues on track. The Distribution System Inspections audit was not scheduled to begin until April 4th and therefore no progress update for Q1 is available. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | E.01 - Enhanced Vegetation Management | VMiLogID | PGE_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _VMiLogID_2022 | 634 | # of circuit miles | 1800 | 217 | 757 | 1405 | 1800 | 291.9 |  |  |  | Complete EVM work on 1,800 risk ranked distribution circuit miles, barring External Factors. | In Q1, PG&E completed 291.9 miles of EVM work. These amounts are subject to change based upon the completion of reviews by our VM and Internal Audit departments. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | E.02 - Pole Clearing Program | VMiLogID | PGE_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _VMiLogID_2022 | 634 | # of distribution poles | [5 empty] | 7737 |  |  |  | Inspect and clear (where clearance is needed) all poles identified in PG&E's Vegetation Management Database as of October 1, 2021, in HFTD areas or HFRA, not required by PRC 4292 and barring External Factors. Any assets discovered between October 1, 2021 and August 31, 2022 will be inspected and cleared (where clearance is needed) by the target due date, barring External Factors. Any assets discovered after August 31, 2022 will be inspected and cleared (where clearance is needed) within 45 days of when added to the Vegetation Management Database, barring External Factors. | Since October 2021, PG&E inspected and cleared, as needed 9,511 Poles outside of compliance mandated areas. A subtotal of 7,737 poles were in HFTD or HFRA. Please note the Target description has been revised in an April 25, 2022 Errata submission. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 | E.03 - LiDAR Ground Inspections - Distribution |  | PGE_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment __2022 | 655 | # of circuit miles | 2000 | 0 | 500 | 1000 | 2000 | 0 |  |  |  | Complete at least 2,000 circuit miles of Mobile LiDAR capture on HFTD road-access electric distribution lines, barring External Factors. If at any point PG&E determines this technology does not effectively support efforts to reduce wildfire risk when compared to other viable approaches or technology, PG&E will pause or discontinue Ground Based LiDAR efforts. | The LiDAR Ground program is on track to both commence reporting completed inspections in June 2022 and complete the 2,000 mile commitment by end of year. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | LiDAR inspections of vegetation around transmission electric lines and equipment |  | 8 | E,04 - LiDAR Routine Inspections - Transmission |  | PGE_Vegetation Management & Inspections_LiDAR inspections of vegetation around transmission electric lines and equipment __2022 | 658 | # of circuit miles | 17880 | 11883 | 17880 | 17880 | 17880 | 13147 |  |  |  | Complete LiDAR inspection of approximately 18,000 circuit miles of transmission lines, barring External Factors. | In Q1, PG&E completed 13,147 of LIDAR inspections of transmission facility miles. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Quality assurance / quality control of vegetation inspections |  | 13 | E.05 - Vegetation Management - Quality Assurance |  | PGE_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections __2022 | 670 | [10 empty] | Perform vegetation management program quality audits prioritizing HFTD/HFRA areas. Statistically valid methodology parameters, such as a confidence level of 95%, will be utilized. | In Q1, five QAVM audits were completed. QVVM performed: (1) 388 Distribution Reviews were completed; (2)104 Transmission Reviews were completed; (3) 596 Poles were audited under VC Pole Clearing; (4) Monthly Enhanced Vegetation Management audits began in February; and (5) 0 Quality CAP Closure Process audits were conducted. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Substation inspection |  | 17 | E.06 - Defensible Space Inspections - Distribution Substation |  | PGE_Vegetation Management & Inspections_Substation inspection __2022 | 682 | # of Distribution Substations | 132 | 109 | 132 | 132 | 132 | 116 |  |  |  | Complete defensible space inspections in alignment with the guidelines set forth in PRC 4291 at 132 distribution substations within HFTD areas or HFRA, barring External Factors. | In Q1, PG&E completed Defensible Space Inspections at 116 Distribution Substations within either a Tier 2, Tier 3, or HFRA. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Substation inspection |  | 17 | E.07 - Defensible Space Inspections - Transmission Substation |  | PGE_Vegetation Management & Inspections_Substation inspection __2022 | 684 | # of Transmission Substations | 55 | 33 | 55 | 55 | 55 | 49 |  |  |  | Complete defensible space inspections in alignment with the guidelines set forth in PRC 4291 at 55 transmission substations within HFTD areas or HFRA, barring External Factors. | In Q1, PG&E completed Defensible Space Inspections at 49 Substations within either a Tier 2, Tier 3, or HFRA. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Substation inspection |  | 17 | E.08 - Defensible Space Inspections - Hydroelectric Substations and Powerhouses |  | PGE_Vegetation Management & Inspections_Substation inspection __2022 | 686 | # of Hydroelectric Substations and Powerhouses | 61 | 42 | 61 | 61 | 61 | 46 |  |  |  | Complete defensible space inspections at 61 Hydroelectric Generation Substations and Powerhouses within HTFD areas or HFRA, barring External Factors. Co-located hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | In Q1, PG&E completed Defensible Space Inspections at 46 Hydroelectric Generation Substations and Powerhouses within either a Tier 2, Tier 3, or HFRA. |  |  |  | In Progress
PGE | 2022-05-02 | Vegetation Management & Inspections | 7.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | E.09 - Utility Defensible Space - Distribution |  | PGE_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment __2022 | 699 | # of distribution poles | 7000 | 1750 | 3567 | 5359 | 7000 | 2244 |  |  |  | Complete utility defensible space work on a minimum of 7,000 poles in the HFTD, barring External Factors. | In Q1, PG&E completed 2,244 pole clearings. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Operations & Operating Protocols | 7.3.6. | Protective equipment and device settings |  | 8 | F.01 - EPSS - Settings Design and Test |  | PGE_Grid Operations & Operating Protocols_Protective equipment and device settings__2022 | 730 | [10 empty] | Conduct laboratory testing to refine the circuit device design parameters for 2022 EPSS implementation. | In Q1, 174 tests were performed at the ATS High Current Test Yard. The testing results indicate the following: * The probability of ignition is higher on dried sod compared to other natural fuel media with higher moisture content. * As the fault current increases, the probability of sustained ignition increases. * As the clearing time increases, the probability of sustained ignition increases for all the fault current magnitudes used for testing. Based on the test results, the reduction in clearing time (fast relaying) for all faults will help reduce the ignition risk and is aligned with enhanced safety practices by other utilities and industry research. Faster relaying will also help limit the movement of faults/traveling arcs on circuits and flashover/arcing to adjacent phases. It was observed that for faster clearing times below 100ms, the risk of sustained ignition was minimal compared to conventional relay settings. Increasing EPSS relay clearing times beyond 100ms is not recommended at this time, as it may increase the ignition risk. |  |  |  | Completed
PGE | 2022-05-02 | Grid Operations & Operating Protocols | 7.3.6. | Protective equipment and device settings |  | 8 | F.02 - EPSS - Install Settings on Distribution Line devices |  | PGE_Grid Operations & Operating Protocols_Protective equipment and device settings__2022 | 730 | # of line reclosers and fuse savers | 3580 | 1574 | 3580 | 3580 | 3580 | 1577 |  |  |  | Load the engineered settings on protection devices (line reclosers and fuse savers) on the identified 1,018 circuits (as of March 10, 2022) on the following schedule, barring External Factors: (1) On 80 percent of line devices by 5/1/22 and, (2) On the remaining 20 percent of line devices by 8/1/22 | A total of 1,577 protection line devices (line reclosers and fuse savers) have had EPSS settings designed and installed through March 31, 2022. Please note the Target description has been revised in an April 29, 2022 Errata submission. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Operations & Operating Protocols | 7.3.6. | Protective equipment and device settings |  | 8 | F.03 - EPSS - Develop Enablement Standards and Procedures |  | PGE_Grid Operations & Operating Protocols_Protective equipment and device settings__2022 | 730 | [10 empty] | Develop the procedure to govern the enablement of EPSS settings in 2022. | PG&E is on track to meet the 5/1 delivery date. |  |  |  | In Progress
PGE | 2022-05-02 | Grid Operations & Operating Protocols | 7.3.6. | Protective equipment and device settings |  | 8 | F.04 - EPSS - Reliability Improvements |  | PGE_Grid Operations & Operating Protocols_Protective equipment and device settings__2022 | 730 | # of circuits | 50 | 0 | 42 | 50 | 50 | 41 |  |  |  | Initiate reliability mitigations on 50 EPSS capable circuits in the HFTD areas, HFRA and non-HFTD buffer zones based on highest projected Customer Experiencing Sustained Outage (CESO). | In Q1, PG&E initiated reliability mitigations on 41 of the 50 highest projected Customer Experiencing Sustained Outage (CESO) circuits. |  |  |  | In Progress
PGE | 2022-05-02 | Data Governance | 7.3.7. | Centralized repository for data |  | 1 | G.01 - Data Governance - Identify and Centralize High Priority Data |  | PGE_Data Governance_Centralized repository for data __2022 | 740 | Level 2 Ontology Objects | [9 empty] | 1. Document and implement a process to identify data gaps in Foundry for critical risk drivers 2. Identify and incorporate new high-priority datasets into Foundry in support of analytic products 3. Identify and incorporate 20 new, foundational ontology objects into Foundry | PG&E's ontology team is progressing on 10 high priority ontology objects and is on track. |  |  |  | In Progress
PGE | 2022-05-02 | Resource Allocation Methodology | 7.3.8. | Risk spend efficiency analysis |  | 3 | H.01 - Risk Spend Efficiency - Develop and Share Governance Process |  | PGE_Resource Allocation Methodology_Risk spend efficiency analysis__2022 | 783 | [10 empty] | Develop and share RSE Governance Process with Energy Safety. | Mockup of Risk Spend Efficiency (RSE) Governance project timeline and process developed in draft. |  |  |  | In Progress
PGE | 2022-05-02 | Stakeholder Cooperation & Community Engagement | 7.3.10. | Community engagement |  | 1 | J.01 - Community Engagement - Meetings |  | PGE_Stakeholder Cooperation & Community Engagement_Community engagement __2022 | 812 | # of meetings | 22 | 3 | 16 | 22 | 22 | 4 |  |  |  | Host 22 customer and community focused virtual meetings (i.e., Safety Town Halls, CWSP Webinars) to further stakeholder and community awareness of PG&E's wildfire mitigation efforts. | In Q1, PG&E completed 4 Safety Town Halls and CWSP webinars completed. |  |  |  | In Progress

## Initiative mapping-DO NOT EDIT
section / initiative # | WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | section / initiative # | Notes | WMP category | WMP code | Utility
7.3.1.1 | Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 7.3.1. | 7.3.1.1 |  | Risk Assessment & Mapping | 7.3.1. | PGE
7.3.1.2 | Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | 7.3.1. | 7.3.1.2 |  | Situational Awareness & Forecasting | 7.3.2. | SCE
7.3.1.3 | Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 7.3.1. | 7.3.1.3 |  | Grid Design & System Hardening | 7.3.3. | SDGE
7.3.1.4 | Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 7.3.1. | 7.3.1.4 |  | Asset Management & Inspections | 7.3.4. | BVES
7.3.1.5 | Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 7.3.1. | 7.3.1.5 |  | Vegetation Management & Inspections | 7.3.5. | LU
7.3.2.1 | Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | 7.3.2. | 7.3.2.1 |  | Grid Operations & Operating Protocols | 7.3.6. | PC
7.3.2.2 | Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | 7.3.2. | 7.3.2.2 |  | Data Governance | 7.3.7. | TBC
7.3.2.3 | Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | 7.3.2. | 7.3.2.3 |  | Resource Allocation Methodology | 7.3.8. | HWT
7.3.2.4 | Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | 7.3.2. | 7.3.2.4 |  | Emergency Planning & Preparedness | 7.3.9.
7.3.2.5 | Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 7.3.2. | 7.3.2.5 |  | Stakeholder Cooperation & Community Engagement | 7.3.10.
7.3.2.6 | Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment | 7.3.2. | 7.3.2.6 |  | Protocols on Public Safety Power Shutoff | 8.2.
7.3.2.7 | Situational Awareness & Forecasting | 7 | Other, Wildfire Safety Operations Center | 7.3.2. | 7.3.2.7 | Added for Q2 2021
7.3.2.8 | Situational Awareness & Forecasting | 8 | Other, Meteorology Analytics / Operations Center | 7.3.2. | 7.3.2.8 | Added for Q2 2021
7.3.3.1 | Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program | 7.3.3. | 7.3.3.1
7.3.3.2 | Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | 7.3.3. | 7.3.3.2
7.3.3.3 | Grid Design & System Hardening | 3 | Covered conductor installation | 7.3.3. | 7.3.3.3
7.3.3.4 | Grid Design & System Hardening | 4 | Covered conductor maintenance | 7.3.3. | 7.3.3.4
7.3.3.5 | Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement | 7.3.3. | 7.3.3.5
7.3.3.6 | Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles | 7.3.3. | 7.3.3.6
7.3.3.7 | Grid Design & System Hardening | 7 | Expulsion fuse replacement | 7.3.3. | 7.3.3.7
7.3.3.8 | Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events | 7.3.3. | 7.3.3.8
7.3.3.9 | Grid Design & System Hardening | 9 | Installation of system automation equipment | 7.3.3. | 7.3.3.9
7.3.3.10 | Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps | 7.3.3. | 7.3.3.10
7.3.3.11 | Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event | 7.3.3. | 7.3.3.11
7.3.3.12 | Grid Design & System Hardening | 12 | Other corrective action | 7.3.3. | 7.3.3.12 | Added in Q1 2021
7.3.3.13 | Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 7.3.3. | 7.3.3.13
7.3.3.14 | Grid Design & System Hardening | 14 | Transformers maintenance and replacement | 7.3.3. | 7.3.3.14
7.3.3.15 | Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement | 7.3.3. | 7.3.3.15
7.3.3.16 | Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment | 7.3.3. | 7.3.3.16
7.3.3.17 | Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs | 7.3.3. | 7.3.3.17
7.3.4.1 | Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment | 7.3.4. | 7.3.4.1
7.3.4.2 | Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment | 7.3.4. | 7.3.4.2
7.3.4.3 | Asset Management & Inspections | 3 | Improvement of inspections | 7.3.4. | 7.3.4.3 | Added in Q1 2021
7.3.4.4 | Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment | 7.3.4. | 7.3.4.4
7.3.4.5 | Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment | 7.3.4. | 7.3.4.5
7.3.4.6 | Asset Management & Inspections | 6 | Intrusive pole inspections | 7.3.4. | 7.3.4.6
7.3.4.7 | Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment | 7.3.4. | 7.3.4.7
7.3.4.8 | Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment | 7.3.4. | 7.3.4.8
7.3.4.9 | Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.4. | 7.3.4.9
7.3.4.10 | Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and | 7.3.4. | 7.3.4.10
7.3.4.11 | Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment | 7.3.4. | 7.3.4.11
7.3.4.12 | Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment | 7.3.4. | 7.3.4.12
7.3.4.13 | Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor | 7.3.4. | 7.3.4.13
7.3.4.14 | Asset Management & Inspections | 14 | Quality assurance / quality control of inspections | 7.3.4. | 7.3.4.14
7.3.4.15 | Asset Management & Inspections | 15 | Substation inspections | 7.3.4. | 7.3.4.15
7.3.4.16 | Asset Management & Inspections | 16 | Other Substation inspections Hydro Generation | 7.3.4. | 7.3.4.16 | Added in Q1 2022
7.3.5.1 | Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts | 7.3.5. | 7.3.5.1
7.3.5.2 | Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment | 7.3.5. | 7.3.5.2
7.3.5.3 | Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment | 7.3.5. | 7.3.5.3
7.3.5.4 | Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions | 7.3.5. | 7.3.5.4
7.3.5.5 | Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities | 7.3.5. | 7.3.5.5
7.3.5.6 | Vegetation Management & Inspections | 6 | Improvement of inspections | 7.3.5. | 7.3.5.6 | Added in Q1 2021
7.3.5.7 | Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment | 7.3.5. | 7.3.5.7
7.3.5.8 | Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment | 7.3.5. | 7.3.5.8
7.3.5.9 | Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment | 7.3.5. | 7.3.5.9 | Added in Q1 2021
7.3.5.10 | Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment | 7.3.5. | 7.3.5.10 | Added in Q1 2021
7.3.5.11 | Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment | 7.3.5. | 7.3.5.11
7.3.5.12 | Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment | 7.3.5. | 7.3.5.12
7.3.5.13 | Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections | 7.3.5. | 7.3.5.13
7.3.5.14 | Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel | 7.3.5. | 7.3.5.14
7.3.5.15 | Vegetation Management & Inspections | 15 | Remediation of at-risk species | 7.3.5. | 7.3.5.15
7.3.5.16 | Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment | 7.3.5. | 7.3.5.16
7.3.5.17 | Vegetation Management & Inspections | 17 | Substation inspection | 7.3.5. | 7.3.5.17
7.3.5.18 | Vegetation Management & Inspections | 18 | Substation vegetation management | 7.3.5. | 7.3.5.18
7.3.5.19 | Vegetation Management & Inspections | 19 | Vegetation inventory system | 7.3.5. | 7.3.5.19
7.3.5.20 | Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment | 7.3.5. | 7.3.5.20
7.3.6.1 | Grid Operations & Operating Protocols | 1 | Automatic recloser operations | 7.3.6. | 7.3.6.1
7.3.6.2 | Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services | 7.3.6. | 7.3.6.2
7.3.6.3 | Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk | 7.3.6. | 7.3.6.3
7.3.6.4 | Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization | 7.3.6. | 7.3.6.4
7.3.6.5 | Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts | 7.3.6. | 7.3.6.5
7.3.6.6 | Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services | 7.3.6. | 7.3.6.6
7.3.6.7 | Grid Operations & Operating Protocols | 7 | Other, Aviation Support | 7.3.6. | 7.3.6.7 | Added in Q2 2021
7.3.6.8 | Grid Operations & Operating Protocols | 8 | Protective equipment and device settings | 7.3.6. | 7.3.6.8 | Added in Q1 2022
7.3.7.1 | Data Governance | 1 | Centralized repository for data | 7.3.7. | 7.3.7.1
7.3.7.2 | Data Governance | 2 | Collaborative research on utility ignition and/or wildfire | 7.3.7. | 7.3.7.2
7.3.7.3 | Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms | 7.3.7. | 7.3.7.3
7.3.7.4 | Data Governance | 4 | Tracking and analysis of near miss data | 7.3.7. | 7.3.7.4
7.3.7.5 | Data Governance | 5 | Other, IT projects to support Wildfire Mitigation work | 7.3.7. | 7.3.7.5 | Added in Q2 2021
7.3.8.1 | Resource Allocation Methodology | 1 | Allocation methodology development and application | 7.3.8. | 7.3.8.1
7.3.8.2 | Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis | 7.3.8. | 7.3.8.2
7.3.8.3 | Resource Allocation Methodology | 3 | Risk spend efficiency analysis | 7.3.8. | 7.3.8.3
7.3.9.1 | Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration | 7.3.9. | 7.3.9.1
7.3.9.2 | Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts | 7.3.9. | 7.3.9.2
7.3.9.3 | Emergency Planning & Preparedness | 3 | Customer support in emergencies | 7.3.9. | 7.3.9.3
7.3.9.4 | Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan | 7.3.9. | 7.3.9.4
7.3.9.5 | Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration | 7.3.9. | 7.3.9.5
7.3.9.6 | Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events | 7.3.9. | 7.3.9.6
7.3.9.7 | Emergency Planning & Preparedness | 7 | Other, Mutual Assistance Support | 7.3.9. | 7.3.9.7 | Added in Q1 2021
7.3.10.1 | Stakeholder Cooperation & Community Engagement | 1 | Community engagement | 7.3.10. | 7.3.10.1
7.3.10.2 | Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA | 7.3.10. | 7.3.10.2
7.3.10.3 | Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies | 7.3.10. | 7.3.10.3
7.3.10.4 | Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap | 7.3.10. | 7.3.10.4
7.3.10.5 | Stakeholder Cooperation & Community Engagement | 5 | Other, PMO and General Wildfire Support | 7.3.10. | 7.3.10.5 | Added in Q2 2021, NOT used in Q1
8.2.1 | Protocols on Public Safety Power Shutoff | 1 | Strategy to Minimize Public Safety Risk During High Wildfire Risk Conditions | 8.2. | 8.2.1 | Added in Q1 2021, EXPANDED for Q3 to include 4 "Addressing Extreme Drought" initiatives
8.2.4 | Protocols on Public Safety Power Shutoff | 4 | Customer, Agency, and External Communications | 8.2. | 8.2.4 | Added in Q1 2021
|  |  | Other |  |  | Added in Q1 2021