## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | LU
Report Year |  | 2022
Report Quarter |  | Q1
Submission Date |  | 2022-08-01
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail | Notes
LU | 2022-08-01 | Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk_01 | LU_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _Risk_01_2022 | 80 | N/A | - | - | - | - | - | - | - | - | - | Enhance wildfire risk model and update data | In progress | In progress | - | - | In progress
LU | 2022-08-01 | Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations |  | 1 | Advanced weather monitoring and weather stations | SAF_01 | LU_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _SAF_01_2022 | 81 | Weather Stations Installed | 10 | 0 | 2 | 8 | 10 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Situational Awareness & Forecasting | 7.3.2.2 | Continuous monitoring sensors |  | 2 | Continuous monitoring sensors | SAF_02 | LU_Situational Awareness & Forecasting_Continuous monitoring sensors _SAF_02_2022 | 82 | DFA Units Installed | 10 | 0 | 5 | 5 | 10 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment |  | 3 | Fault indicators for detecting faults on electric lines and equipment | SAF_03 | LU_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _SAF_03_2022 | 83 | Fault Indicators Installed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Situational Awareness & Forecasting | 7.3.2.4 | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Forecast of a fire risk index, fire potential index, or similar | SAF_04 | LU_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SAF_04_2022 | 84 | N/A | - | - | - | - | - | - | - | - | - | Continue to integrate FPI into operational decision-making to mitigate wildfire potential | In progress | In progress | - | - | In progress
LU | 2022-08-01 | Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | SAF_05 | LU_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _SAF_05_2022 | 85 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | GDSH_02 | LU_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _GDSH_02_2022 | 86 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation |  | 3 | Covered conductor installation | GDSH_03 | LU_Grid Design & System Hardening_Covered conductor installation _GDSH_03_2022 | 87 | Circuit miles | 9.55 | 0.5 | 0.5 | 5 | 9.55 | 0.47 | 1.88 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Distribution pole replacement and reinforcement, including with composite poles | GDSH_06 | LU_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _GDSH_06_2022 | 90 | Poles | 231 | 23 | 75 | 150 | 231 | 29 | 88 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement |  | 7 | Expulsion fuse replacement | GDSH_07 | LU_Grid Design & System Hardening_Expulsion fuse replacement _GDSH_07_2022 | 91 | Expulsion Fuses Replaced | 1500 | 0 | 300 | 900 | 1500 | 124 | 755 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.8 | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | Grid topology improvements to mitigate or reduce PSPS events | GDSH_08 | LU_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _GDSH_08_2022 | 93 | Line Miles | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment |  | 9 | Installation of system automation equipment | GDSH_09 | LU_Grid Design & System Hardening_Installation of system automation equipment _GDSH_09_2022 | 93 | Automatic Reclosers Installed | 4 | 0 | 1 | 1 | 4 | 0 | 1 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.12 | Other corrective action |  | 12 | Other corrective action | GDSH_12 | LU_Grid Design & System Hardening_Other corrective action _GDSH_12_2022 | 94 | Tree Attachment Removals | 45 | 0 | 15 | 30 | 45 | 25 | 48 | - | - | - | - | - | - | - | In progress | [7 empty] | Q1 progress was revised from 0 tree attachment removals to 25 tree attachment removals
LU | 2022-08-01 | Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment |  | 16 | Undergrounding of electric lines and/or equipment | GDSH_16 | LU_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _GDSH_16_2022 | 96 | Line Miles | 0.36 | - | - | - | 0.4 | 0.24 | 0.24 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment |  | 1 | Detailed inspections of distribution electric lines and equipment | AMI_01 | LU_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _AMI_01_2022 | 81 | Line Miles Inspected | 307.8 | 50 | 175 | 250 | 307.8 | 43.97 | 274.74 |  | - | - | - | - | - | - | In progress | [7 empty] | Q1 progress was revised from 134.86 miles to 43.97 miles
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.3 | Improvement of inspections |  | 3 | Improvement of inspections | AMI_03 | LU_Asset Management & Inspections_Improvement of inspections _AMI_03_2022 | 82 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment |  | 4 | Infrared inspections of distribution electric lines and equipment | AMI_04 | LU_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _AMI_04_2022 | 82 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections |  | 6 | Intrusive pole inspections | AMI_06 | LU_Asset Management & Inspections_Intrusive pole inspections _AMI_06_2022 | 83 | Poles Inspected | 2598 | 0 | 0 | 1299 | 2598 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment |  | 11 | Patrol inspections of distribution electric lines and equipment | AMI_11 | LU_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _AMI_11_2022 | 85 | Line Miles Inspected | 706.28 | 100 | 250 | 400 | 706.3 | 152.3 | 466.7 |  | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections |  | 14 | Quality assurance / quality control of inspections | AMI_14 | LU_Asset Management & Inspections_Quality assurance / quality control of inspections _AMI_14_2022 | 86 | % of detailed inspections | 0.005 | 0 | 0.005 | 0.005 | 0.005 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Asset Management & Inspections | 7.3.4.15 | Substation inspections |  | 15 | Substation inspections | AMI_15 | LU_Asset Management & Inspections_Substation inspections _AMI_15_2022 | 88 | Substations Inspected | 42 | 10 | 20 | 32 | 42 | 11 | 22 | - | - | - | - | - | - | - | In progress | [7 empty] | Q1 progress was revised from 10 substations to 11 substations
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts |  | 1 | Additional efforts to manage community and environmental impacts | VMI_01 | LU_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _VMI_01_2022 | 104 | Line Miles Treated | 6 | 0 | 2 | 4 | 6 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | Detailed inspections of vegetation around distribution electric lines and equipment | VMI_02 | LU_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _VMI_02_2022 | 107 | Line Miles Inspected | 222 | 53 | 109 | 170 | 222 | 53.5 | 149.3 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.5 | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Fuel management and reduction of “slash” from vegetation management activities | VMI_05 | LU_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VMI_05_2022 | 109 | Acres | 280 | 0 | 95 | 190 | 280 | 0 | 56.7 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.7 | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment | VMI_07 | LU_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment _VMI_07_2022 | 112 | Line Miles Inspected | 701 | 0 | 0 | 701 | 701 | 0 | 0 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment |  | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment | VMI_10 | LU_Vegetation Management & Inspections_Other discretionary inspections of vegetation around transmission electric lines and equipment _VMI_10_2022 | 113 | Line Miles Inspected | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 | Patrol inspections of vegetation around distribution electric lines and equipment | VMI_11 | LU_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _VMI_11_2022 | 113 | Line Miles Inspected | 171 | 43 | 88 | 130 | 171 | 26.1 | 92.9 | - | - | - | - | - | - | - | In progress | [7 empty] | Q1 progress was revised from 43.4 miles to 26.1 miles
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections |  | 13 | Quality assurance / quality control of vegetation inspections | VMI_13 | LU_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections _VMI_13_2022 | 114 | Line Miles Inspected | 221 | 22 | 92 | 162 | 228 | 22.4 | 184.1 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel |  | 14 | Recruiting and training of vegetation management personnel | VMI_14 | LU_Vegetation Management & Inspections_Recruiting and training of vegetation management personnel _VMI_14_2022 | 116 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.15 | Remediation of at-risk species |  | 15 | Remediation of at-risk species | VMI_15 | LU_Vegetation Management & Inspections_Remediation of at-risk species _VMI_15_2022 | 117 | Line Miles Treated | 238 | 30 | 110 | 190 | 238 | 30.4 | 30.4 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Removal and remediation of trees with strike potential to electric lines and equipment | VMI_16 | LU_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VMI_16_2022 | 118 | Line Miles Treated | 171 | 8 | 63 | 120 | 171 | 8.6 | 8.6 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | Vegetation management to achieve clearances around electric lines and equipment | VMI_20 | LU_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _VMI_20_2022 | 119 | Line Miles Treated | 701 | 400 | 600 | 701 | 701 | 404.9 | 697 | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Vegetation Management & Inspections | 7.3.5.21 | Vegetation management activities post-fire |  | 21 | Vegetation management activities post-fire | VMI_21 | LU_Vegetation Management & Inspections_Vegetation management activities post-fire _VMI_21_2022 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2022-08-01 | Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations |  | 1 | Automatic recloser operations | GOOP_01 | LU_Grid Operations & Operating Protocols_Automatic recloser operations _GOOP_01_2022 | 120 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk |  | 3 | Personnel work procedures and training in conditions of elevated fire risk | GOOP_03 | LU_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _GOOP_03_2022 | 121 | N/A | - | - | - | - | - | - | - | - | - | Annual training; update procedures and incorporate feedback from training | In progress | In progress | - | - | In progress
LU | 2022-08-01 | Grid Operations & Operating Protocols | 7.3.6.4 | Protocols for PSPS re-energization |  | 4 | Protocols for PSPS re-energization | GOOP_04 | LU_Grid Operations & Operating Protocols_Protocols for PSPS re-energization _GOOP_04_2022 | 124 | N/A | - | - | - | - | - | - | - | - | - | Continue refining activities associated with reducing PSPS impacts on customers | In progress | In progress | - | - | In progress
LU | 2022-08-01 | Data Governance | 7.3.7.1 | Centralized repository for data |  | 1 | Centralized repository for data | DG_01 | LU_Data Governance_Centralized repository for data _DG_01_2022 | 98 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire |  | 2 | Collaborative research on utility ignition and/or wildfire | DG_02 | LU_Data Governance_Collaborative research on utility ignition and/or wildfire _DG_02_2022 | 126 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | In progress
LU | 2022-08-01 | Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration |  | 1 | Adequate and trained workforce for service restoration | EPP_01 | LU_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _EPP_01_2022 | 128 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
LU | 2022-08-01 | Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts |  | 2 | Community outreach, public awareness, and communications efforts | EPP_02 | LU_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _EPP_02_2022 | 130 | N/A | - | - | - | - | - | - | - | - | - | Continued engagement with local stakeholders to prepare for and respond to fire-related event; Meet with Community Advisory Boards | In progress | - | - | - | In progress
LU | 2022-08-01 | Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies |  | 3 | Customer support in emergencies | EPP_03 | LU_Emergency Planning & Preparedness_Customer support in emergencies _EPP_03_2022 | 132 | N/A | - | - | - | - | - | - | - | - | - | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. | In progress | ICS Training and PSPS Table Top Exercise held on June 15, 2022; PSPS Full Scale Exercise with Public Safety Partners held on June 23, 2022 | - | - | In progress
LU | 2022-08-01 | Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement |  | 1 | Community engagement | SCCE_01 | LU_Stakeholder Cooperation & Community Engagement_Community engagement _SCCE_01_2022 | 135 | N/A | - | - | - | - | - | - | - | - | - | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. | In progress | 15 in-person events, 12 virtual events, and two rounds of social media posts focused on PSPS education and wildfire awareness, AFN outreach, and CBO colalboration and one phone call meeting with elected official. | - | - | In progress
LU | 2022-08-01 | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA |  | 2 | Cooperation and best practice sharing with agencies outside CA | SCCE_02 | LU_Stakeholder Cooperation & Community Engagement_Cooperation and best practice sharing with agencies outside CA _SCCE_02_2022 | 141 | N/A | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other