## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | BVES
Report Year |  | 2022
Report Quarter |  | Q1
Submission Date |  | 2022-07-29
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
BVES | 2022-07-29 | Risk Assessment & Mapping | 7.3.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-1 | BVES_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment _BVRAM-001-1_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Risk Assessment & Mapping | 7.3.1. | Climate-driven risk map and modelling based on various relevant weather scenarios |  | 2 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-2 | BVES_Risk Assessment & Mapping_Climate-driven risk map and modelling based on various relevant weather scenarios _BVRAM-001-2_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Risk Assessment & Mapping | 7.3.1. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | 3 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-3 | BVES_Risk Assessment & Mapping_Ignition probability mapping showing the probability of ignition along the electric lines and equipment _BVRAM-001-3_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Risk Assessment & Mapping | 7.3.1. | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | 4 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-4 | BVES_Risk Assessment & Mapping_Initiative mapping and estimation of wildfire and PSPS risk-reduction impact _BVRAM-001-4_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Risk Assessment & Mapping | 7.3.1. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | 5 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-5 | BVES_Risk Assessment & Mapping_Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment _BVRAM-001-5_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Advanced weather monitoring and weather stations |  | 1 | Situational Awareness Hardware Program | BVSAF-001-1 | BVES_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _BVSAF-001-1_2022 | 103 | Number of Weather Stations Installed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Continuous monitoring sensors |  | 2 | Situational Awareness Hardware Program | BVSAF-001-2 | BVES_Situational Awareness & Forecasting_Continuous monitoring sensors _BVSAF-001-2_2022 | 104 | Number of HD Cameras Installed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Fault indicators for detecting faults on electric lines and equipment |  | 3 | Situational Awareness Hardware Program | BVSAF-001-3 | BVES_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _BVSAF-001-3_2022 | 130 | Number of Fault Indicators | 50 | 0 | 0 | 20 | 50 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Weather Consultant | BVSAF-003-2 | BVES_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _BVSAF-003-2_2022 | 99 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 | Grid Operations & Protocol | BVSAF-002 | BVES_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _BVSAF-002_2022 | 128 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Sufficient resources during high risk conditions | No high risk events occurred | No high risk events occurred |  |  | In Progress | NA
BVES | 2022-07-29 | Situational Awareness & Forecasting | 7.3.2. | Weather forecasting and estimating impacts on electric lines and equipment |  | 6 | Weather Consultant | BVSAF-003-1 | BVES_Situational Awareness & Forecasting_Weather forecasting and estimating impacts on electric lines and equipment _BVSAF-003-1_2022 | 130 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Consulting support for weather forecasting & analysis | Support requirement met | Support requirement met |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Capacitor maintenance and replacement program |  | 1 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-001 | BVES_Grid Design & System Hardening_Capacitor maintenance and replacement program _BVGDSH-001_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-002 | BVES_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _BVGDSH-002_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Covered conductor installation |  | 3 | Covered Conductor Replacement Program | BVGDSH-003-1 | BVES_Grid Design & System Hardening_Covered conductor installation _BVGDSH-003-1_2022 | 114 | Circuit Miles Hardened | 12.9 | 0 | 4.3 | 8.6 | 12.9 | 2.3 | 7.02 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Covered conductor installation |  | 3 | Covered Conductor Replacement Program - Radford | BVGDSH-003-2 | BVES_Grid Design & System Hardening_Covered conductor installation _BVGDSH-003-2_2022 |  | Circuit Miles Hardened | 2.7 | 0 | 0 | 1 | 2.7 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Covered conductor maintenance |  | 4 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-004 | BVES_Grid Design & System Hardening_Covered conductor maintenance _BVGDSH-004_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Crossarm maintenance, repair, and replacement |  | 5 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-005 | BVES_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement _BVGDSH-005_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Distribution Pole Repalcement and Reforcement – GO 95 Projects (7.3.3.6.1) | BVGDSH-015-2 | BVES_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _BVGDSH-015-2_2022 | 113 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Covered Conductor Project - Radford Line | BVGDSH-015-4 | BVES_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _BVGDSH-015-4_2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Evacuation Route Hardening Program - Pilot | BVGDSH-015-5 | BVES_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _BVGDSH-015-5_2022 |  | Poles Hardened | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Evacuation Route Hardening Program | BVGDSH-015-6 | BVES_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _BVGDSH-015-6_2022 |  | Poles Hardened | 412 | 350 | 412 | 412 | 412 | 412 | 412 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Expulsion fuse replacement |  | 7 | Fuse Replacement Program | BVGDSH-006 | BVES_Grid Design & System Hardening_Expulsion fuse replacement _BVGDSH-006_2022 | 110 | Number of Fuses Replaced | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | Grid Topology Improvements | BVGDSH-007-1 | BVES_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _BVGDSH-007-1_2022 | 59 | # of Sectional Devices Installed Divided by # of Sectional Devices Needed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Installation of system automation equipment |  | 9 | Grid Automation Program | BVGDSH-008-1 | BVES_Grid Design & System Hardening_Installation of system automation equipment _BVGDSH-008-1_2022 | 102 | Number of Subsations connected to SCADA | 2 | 0 | 0 | 1 | 2 | 0 | 1 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Installation of system automation equipment |  | 9 | Grid Automation Program // FLISR |  | BVES_Grid Design & System Hardening_Installation of system automation equipment __2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | System Instillation and Project Completion | Project effort continue | Project effort continue |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Installation of system automation equipment |  | 9 | Grid Automation Program // Fuse Trip Saver |  | BVES_Grid Design & System Hardening_Installation of system automation equipment __2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Maintenance, repair, and replacement of connectors, including hotline clamps |  | 10 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-009 | BVES_Grid Design & System Hardening_Maintenance, repair, and replacement of connectors, including hotline clamps _BVGDSH-009_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | Energy Storage Project | BVGDSH-010 | BVES_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event _BVGDSH-010_2022 | 60 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | BVES plans to install a 8MW/4MWh battery storage system in 2023 | Internal discussions for siting and permitting needs ahead of construction plan | Internal discussions for siting and permitting needs ahead of construction plan |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | BVPP Phase 4 Upgrade Project |  | BVES_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event __2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Other corrective action |  | 12 | Tree Attachment Removal Program | BVGDSH-013 | BVES_Grid Design & System Hardening_Other corrective action _BVGDSH-013_2022 | 68 | Tree Attachment Removal | 80 | 0 | 0 | 0 | 80 | 0 | 2 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Other corrective action |  | 12 | Evacuation Route Hardening | BVGDSH-014 | BVES_Grid Design & System Hardening_Other corrective action _BVGDSH-014_2022 | 69 | Poles Hardened | 412 | 350 | 412 | 412 | 412 | 412 | 412 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  | 13 | Pole Loading & Replacement Program | BVGDSH-015-1 | BVES_Grid Design & System Hardening_Pole loading infrastructure hardening and replacement program based on pole loading assessment program _BVGDSH-015-1_2022 | 113 | Number of Poles Replaced | 165 | 10 | 40 | 100 | 165 | 28 | 104 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Transformers maintenance and replacement |  | 14 | Program covered under ongoing maintenance of subtransmission and distribution facilities. There is not a separate WMP initiative. | BVGDSH-016 | BVES_Grid Design & System Hardening_Transformers maintenance and replacement _BVGDSH-016_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Transmission tower maintenance and replacement |  | 15 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVGDSH-017 | BVES_Grid Design & System Hardening_Transmission tower maintenance and replacement _BVGDSH-017_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Undergrounding of electric lines and/or equipment |  | 16 | Ongoing Routine Undergrounding Projects | BVGDSH-018 | BVES_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _BVGDSH-018_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Design & System Hardening | 7.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | Grid Topology Improvements | BVGDSH-007-2 | BVES_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs _BVGDSH-007-2_2022 | 59 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Detailed inspections of distribution electric lines and equipment |  | 1 | Detailed Inspection Program | BVAMI-001-1 | BVES_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _BVAMI-001-1_2022 | 61 | Circuit Miles Inspected | 29 | 0 | 5 | 11 | 29 | 0 | 29.58 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVAMI-002 | BVES_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _BVAMI-002_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Improvement of inspections |  | 3 | Improvement of Inspections | BVAMI-003 | BVES_Asset Management & Inspections_Improvement of inspections _BVAMI-003_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Infrared inspections of distribution electric lines and equipment |  | 4 | UAV Thermography Program | BVAMI-004 | BVES_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _BVAMI-004_2022 | 61 | Circuit Miles Inspected | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Infrared inspections of transmission electric lines and equipment |  | 5 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVAMI-005 | BVES_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _BVAMI-005_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Intrusive pole inspections |  | 6 | Intrusive Pole Inspection Program | BVAMI-006 | BVES_Asset Management & Inspections_Intrusive pole inspections _BVAMI-006_2022 | 120 | Number of Poles Assessed | 850 | 0 | 0 | 300 | 850 | 0 | 587 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | LiDAR inspections of distribution electric lines and equipment |  | 7 | LiDAR Inspection Program | BVAMI-007-1 | BVES_Asset Management & Inspections_LiDAR inspections of distribution electric lines and equipment _BVAMI-007-1_2022 | 120 | Circuit Miles Surveyed | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | LiDAR inspections of transmission electric lines and equipment |  | 8 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVAMI-008 | BVES_Asset Management & Inspections_LiDAR inspections of transmission electric lines and equipment _BVAMI-008_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Third Party Ground Patrol | BVAMI-009 | BVES_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _BVAMI-009_2022 | 119 | Circuit Miles Inspected | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | UAV HD Photography/Video Program | BVAMI-009-1 | BVES_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _BVAMI-009-1_2022 |  | Circuit Miles Inspected | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Other discretionary inspection of transmission electric lines and |  | 10 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVAMI-010 | BVES_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and _BVAMI-010_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Patrol inspections of distribution electric lines and equipment |  | 11 | Patrol Inspection Program | BVAMI-011-1 | BVES_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _BVAMI-011-1_2022 | 118 | Circuit Miles Inspected | 211 | 25 | 75 | 211 | 211 | 83.2 | 83.2 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Patrol inspections of transmission electric lines and equipment |  | 12 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVAMI-012 | BVES_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _BVAMI-012_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Pole loading assessment program to determine safety factor |  | 13 | Pole Loading & Replacement Program | BVGDSH-015-3 BVAMI-013 | BVES_Asset Management & Inspections_Pole loading assessment program to determine safety factor _BVGDSH-015-3 BVAMI-013_2022 | 113 | Number of Poles Assessed | 225 | 0 | 75 | 150 | 225 | 28 | 104 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Quality assurance / quality control of inspections |  | 14 | Quality Control of Inspections | BVAMI-014-1 | BVES_Asset Management & Inspections_Quality assurance / quality control of inspections _BVAMI-014-1_2022 | 63 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Planned | NA
BVES | 2022-07-29 | Asset Management & Inspections | 7.3.4. | Substation inspections |  | 15 | GO-174 Substation Inspection Program | BVAMI-015-1 | BVES_Asset Management & Inspections_Substation inspections _BVAMI-015-1_2022 | 63 | Number of Monthly Substations Inspected | 144 | 36 | 72 | 108 | 144 | 39 | 78 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Additional efforts to manage community and environmental impacts |  | 1 | BVES does not have a unique WMP initiative for this activity at this time. BVES currently has not encountered the need for additional efforts to manage community and environmental impacts. | BVVMI-001 | BVES_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _BVVMI-001_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment |  | 2 | Detailed Inspection Program | BVAMI-001-2 BVVMI-002 | BVES_Vegetation Management & Inspections_Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment_BVAMI-001-2 BVVMI-002_2022 | 119 | Circuit Miles Inspected | 29 | 0 | 5 | 11 | 29 | 0 | 29.58 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment |  | 3 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVVMI-003 | BVES_Vegetation Management & Inspections_Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment_BVVMI-003_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Emergency response vegetation management due to red flag warning or other urgent weather conditions |  | 4 | Emergency Preparedness & Response Program | BVEPP-004-7 BVVMI-004 | BVES_Vegetation Management & Inspections_Emergency response vegetation management due to red flag warning or other urgent weather conditions _BVEPP-004-7 BVVMI-004_2022 | 63 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Fuel management (including all wood management) and management of “slash” from vegetation management activities |  | 5 | Enhanced Vegetation Management Program | BVVMI-015-2 | BVES_Vegetation Management & Inspections_Fuel management (including all wood management) and management of “slash” from vegetation management activities _BVVMI-015-2_2022 | 63 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Contractor removes veg waste as part of contract on daily basis | Contractor meets requirements |  |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Improvement of inspections |  | 6 | Quality Control of Inspections | BVVMI-005 | BVES_Vegetation Management & Inspections_Improvement of inspections_BVVMI-005_2022 | NA | Number of Vegetation Management Audits | 4 | 1 | 2 | 3 | 4 | 2 | 3 |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Remote sensing inspections of vegetation around distribution electric lines and equipment |  | 7 | LiDAR Inspection Program | BVAMI-007-2 BVVMI-006 | BVES_Vegetation Management & Inspections_Remote sensing inspections of vegetation around distribution electric lines and equipment_BVAMI-007-2 BVVMI-006_2022 | 120 | Circuit Miles Surveyed | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Remote sensing inspections of vegetation around transmission electric lines and equipment |  | 8 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVVMI-007 | BVES_Vegetation Management & Inspections_Remote sensing inspections of vegetation around transmission electric lines and equipment_BVVMI-007_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Other discretionary inspections of vegetation around distribution electric lines and equipment |  | 9 | Third Party Ground Patrol | BVVMI-008 | BVES_Vegetation Management & Inspections_Other discretionary inspections of vegetation around distribution electric lines and equipment _BVVMI-008_2022 | 122 | Circuit Miles Inspected | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Other discretionary inspections of vegetation around distribution electric lines and equipment |  | 9 | UAV HD Photography/Video Program |  | BVES_Vegetation Management & Inspections_Other discretionary inspections of vegetation around distribution electric lines and equipment __2022 |  | Circuit Miles Inspected (UAV) | 211 | 0 | 0 | 211 | 211 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Other discretionary inspection of transmission electric lines and |  | 10 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVVMI-009 | BVES_Vegetation Management & Inspections_Other discretionary inspection of transmission electric lines and _BVVMI-009_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 | Patrol Inspection Program | BVAMI-011-2 BVVMI-010 | BVES_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment _BVAMI-011-2 BVVMI-010_2022 | 91 | Circuit Miles Inspected | 211 | 25 | 75 | 211 | 211 | 83.2 | 83.2 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Patrol inspections of vegetation around transmission electric lines and equipment |  | 12 | BVES does not have any transmission level assets and maintains a subtransmission line (34.5kV) that is treated as a higher voltage asset. | BVVMI-011 | BVES_Vegetation Management & Inspections_Patrol inspections of vegetation around transmission electric lines and equipment _BVVMI-011_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Quality assurance / quality control of vegetation management |  | 13 | Quality Control of Inspections | BVAMI-014-2 BVVMI-012 | BVES_Vegetation Management & Inspections_Quality assurance / quality control of vegetation management_BVAMI-014-2 BVVMI-012_2022 | 95 | Number of Quality Control Reviews Conducted | 72 | 18 | 36 | 54 | 72 | 16 | 42 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Recruiting and training of vegetation management personnel |  | 14 | Vegetation Management Program Staffing | BVVMI-013 | BVES_Vegetation Management & Inspections_Recruiting and training of vegetation management personnel _BVVMI-013_2022 | 72 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | No gaps in staffing for veg management | Met target | Met target |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Identification and remediation of “at-risk species” |  | 15 | Identification and remediation of “at-risk species” | BVVMI-014 | BVES_Vegetation Management & Inspections_Identification and remediation of “at-risk species” _BVVMI-014_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Enhanced Vegetation Management Program | BVVMI-015-1 | BVES_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _BVVMI-015-1_2022 | 64 | Hazard Trees Removed/Remediated | 88 | 18 | 36 | 66 | 88 | 20 | 67 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Substation inspection |  | 17 | GO-174 Substation Inspection Program | BVAMI-015-2 BVVMI-016 | BVES_Vegetation Management & Inspections_Substation inspection _BVAMI-015-2 BVVMI-016_2022 | 91 | Number of Substations Inspected | 144 | 36 | 72 | 108 | 144 | 39 | 78 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Substation vegetation management |  | 18 | Substation Vegetation Management Inspections & Corrections | BVVMI-017 | BVES_Vegetation Management & Inspections_Substation vegetation management _BVVMI-017_2022 | 64 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Contractor assess and removes vegetation per substation on an annual basis | inspected substations cleared of vegetation | inspected substations cleared of vegetation |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Vegetation management enterprise system |  | 19 | GIS Data Collection & Sharing | BVDG-001-2 BVVMI-018 | BVES_Vegetation Management & Inspections_Vegetation management enterprise system_BVDG-001-2 BVVMI-018_2022 | 64 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | System updates as necessary | Trimmed Trees were entered into GIS | Trimmed Trees were entered into GIS |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | Enhanced Vegetation Management Program | BVVMI-015-3 BVVMI-019 | BVES_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _BVVMI-015-3 BVVMI-019_2022 | 65 | Circuit Miles Cleared | 72 | 18 | 36 | 54 | 72 | 36.6 | 61.62 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Vegetation Management & Inspections | 7.3.5. | Vegetation management activities post-fire |  | 21 | BVES does not have a unique WMP initiative for this activity at this time. This is captured under normal business operations. |  | BVES_Vegetation Management & Inspections_Vegetation management activities post-fire __2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Automatic recloser operations |  | 1 | Grid Automation Program | BVGDSH-008-2 BVGOOP-001 | BVES_Grid Operations & Operating Protocols_Automatic recloser operations _BVGDSH-008-2 BVGOOP-001_2022 | 65 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Protective equipment and device settings |  | 2 | Protective Equipement and Device Settings |  | BVES_Grid Operations & Operating Protocols_Protective equipment and device settings__2022 |  | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Crew-accompanying ignition prevention and suppression resources and services |  | 3 | Emergency Preparedness & Response Program | BVEPP-004-5 BVGOOP-002-1 | BVES_Grid Operations & Operating Protocols_Crew-accompanying ignition prevention and suppression resources and services _BVEPP-004-5 BVGOOP-002-1_2022 | 65 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Ongoing compliance with plan | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Personnel work procedures and training in conditions of elevated fire risk |  | 4 | PSPS Program & Procedures | BVGOOP-003-2 | BVES_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _BVGOOP-003-2_2022 | 65 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Ongoing compliance with program and procedures | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Protocols for PSPS re-energization |  | 5 | PSPS Program & Procedures | BVGOOP-003-3 | BVES_Grid Operations & Operating Protocols_Protocols for PSPS re-energization _BVGOOP-003-3_2022 | 66 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Ongoing compliance with program and procedures | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | PSPS events and mitigation of PSPS impacts |  | 6 | PSPS Program & Procedures | BVGOOP-003-1 | BVES_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _BVGOOP-003-1_2022 | 66 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Ongoing compliance with program and procedures | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Grid Operations & Operating Protocols | 7.3.6. | Stationed and on-call ignition prevention and suppression resources and services |  | 7 | Emergency Preparedness & Response Program | BVEPP-004-6 BVGOOP-002-2 | BVES_Grid Operations & Operating Protocols_Stationed and on-call ignition prevention and suppression resources and services _BVEPP-004-6 BVGOOP-002-2_2022 | 65 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Ability to comply with plan and respond to emergencies | No emergency events occurred | No emergency events occurred |  |  | In Progress | NA
BVES | 2022-07-29 | Data Governance | 7.3.7. | Centralized repository for data |  | 1 | GIS Data Collection & Sharing | BVDG-001-1 | BVES_Data Governance_Centralized repository for data _BVDG-001-1_2022 | 66 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Continued development and storage of GIS Data | Continued refinement for GIS resources | Continued refinement for GIS resources |  |  | In Progress | NA
BVES | 2022-07-29 | Data Governance | 7.3.7. | Collaborative research on utility ignition and/or wildfire |  | 2 | BVES does not have a unique WMP initiative for this activity at this time. BVES is open to collaborative research on utility ignition and/or wildfire. | BVDG-002 | BVES_Data Governance_Collaborative research on utility ignition and/or wildfire _BVDG-002_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Data Governance | 7.3.7. | Documentation and disclosure of wildfire-related data and algorithms |  | 3 | BVES does not have a unique WMP initiative for this activity at this time. This is captured under normal business operations. | BVDG-003 | BVES_Data Governance_Documentation and disclosure of wildfire-related data and algorithms _BVDG-003_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Data Governance | 7.3.7. | Tracking and analysis of near miss data |  | 4 | WMP Metrics Tracking | BVDG-004 | BVES_Data Governance_Tracking and analysis of near miss data _BVDG-004_2022 | 66 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Program in place and continued compliance with program | Aligned recording mechanism to track near miss data with WSD/OEIS template | Aligned recording mechanism to track near miss data with WSD/OEIS template |  |  | In Progress | NA
BVES | 2022-07-29 | Resource Allocation Methodology | 7.3.8. | Allocation methodology development and application |  | 1 | Resource Allocation Methodology | BVRES-001-1 | BVES_Resource Allocation Methodology_Allocation methodology development and application _BVRES-001-1_2022 | 134 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | Program in place and continued compliance with program | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Resource Allocation Methodology | 7.3.8. | Risk reduction scenario development and analysis |  | 2 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-6 BVRES-002 | BVES_Resource Allocation Methodology_Risk reduction scenario development and analysis _BVRAM-001-6 BVRES-002_2022 | 19 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Completed | NA
BVES | 2022-07-29 | Resource Allocation Methodology | 7.3.8. | Risk spend efficiency analysis |  | 3 | Ignition Probability & Wildfire Consequence Mapping | BVRAM-001-7 BVRES-003 | BVES_Resource Allocation Methodology_Risk spend efficiency analysis_BVRAM-001-7 BVRES-003_2022 | 19 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Adequate and trained workforce for service restoration |  | 1 | Resource Allocation Methodology | BVRES-001-2 BVEPP-001 | BVES_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _BVRES-001-2 BVEPP-001_2022 | 138 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | BVES staffing contract and mutual aid adequate for service restoration | Adequate | Adequate |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Community Outreach Program | BVEPP-002-1 | BVES_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _BVEPP-002-1_2022 | 139 | Number of Engagements (Radio, Newspaper, Online, Mail) | 360 | 90 | 180 | 270 | 360 | 141 | 286 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Customer support in emergencies |  | 3 | Emergency Preparedness & Response Program | BVEPP-003-2 | BVES_Emergency Planning & Preparedness_Customer support in emergencies _BVEPP-003-2_2022 | 141 | Number of Emergencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Disaster and emergency preparedness plan |  | 4 | Emergency Preparedness & Response Program | BVEPP-003-1 | BVES_Emergency Planning & Preparedness_Disaster and emergency preparedness plan _BVEPP-003-1_2022 | 135 | Number of Emergencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Preparedness and planning for service restoration |  | 5 | Emergency Preparedness & Response Program | BVEPP-003-3 | BVES_Emergency Planning & Preparedness_Preparedness and planning for service restoration _BVEPP-003-3_2022 | 138 | Number of Emergencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Emergency Planning & Preparedness | 7.3.9. | Protocols in place to learn from wildfire events |  | 6 | Emergency Preparedness & Response Program | BVEPP-003-4 | BVES_Emergency Planning & Preparedness_Protocols in place to learn from wildfire events _BVEPP-003-4_2022 | 143 | Number of Emergencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Stakeholder Cooperation & Community Engagement | 7.3.10. | Community engagement |  | 1 | Community Outreach Program | BVEPP-002-2 BVSCCE-001 | BVES_Stakeholder Cooperation & Community Engagement_Community engagement _BVEPP-002-2 BVSCCE-001_2022 | 139 | Number of Engagements (Radio, Newspaper, Online, Mail) | 360 | 90 | 180 | 270 | 360 | 141 | 286 |  |  | NA | NA | NA |  |  | In Progress | NA
BVES | 2022-07-29 | Stakeholder Cooperation & Community Engagement | 7.3.10. | Cooperation and best practice sharing with agencies outside CA |  | 2 | Cooperation and best practice sharing with agencies outside CA | BVSCCE-002 | BVES_Stakeholder Cooperation & Community Engagement_Cooperation and best practice sharing with agencies outside CA _BVSCCE-002_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | Planned | NA
BVES | 2022-07-29 | Stakeholder Cooperation & Community Engagement | 7.3.10. | Cooperation with suppression agencies |  | 3 | Cooperation with suppression agencies | BVSCCE-003 | BVES_Stakeholder Cooperation & Community Engagement_Cooperation with suppression agencies _BVSCCE-003_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
BVES | 2022-07-29 | Stakeholder Cooperation & Community Engagement | 7.3.10. | Forest service and fuel reduction cooperation and joint roadmap |  | 4 | Forest service and fuel reduction cooperation and joint roadmap | BVSCCE-004 | BVES_Stakeholder Cooperation & Community Engagement_Forest service and fuel reduction cooperation and joint roadmap _BVSCCE-004_2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA |  |  | NA | NA
NOTE: To add more rows, highlight the current last row of the table, copy, and paste directly below the last row

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 7.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 7.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 7.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 7.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 7.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 7.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 7.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 7.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 7.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 7.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent weather conditions
Vegetation Management & Inspections | 5 | Fuel management (including all wood management) and management of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | Remote sensing inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | Remote sensing inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation management
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Identification and remediation of “at-risk species”
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation management enterprise system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation Management & Inspections | 21 | Vegetation management activities post-fire
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Protective equipment and device settings
Grid Operations & Operating Protocols | 3 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 4 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 5 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 6 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 7 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other