## Slide 1
Wildfire Mitigation Plan
Quarterly Advice Letter
(now an Information Only Report)
Initiatives Update
Bear Valley Electric Service, Inc.
Q1 2022

## Slide 2: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
7.3.4 - Asset Management & Inspections
LiDAR inspections of distribution electric lines and equipment
7.3.4.7
Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
7.3.4.9
Intrusive Pole Inspections
7.3.4.6
Quality assurance / quality control of inspections
7.3.4.14
Other discretionary inspection of transmission electric lines and
7.3.4.10
Not Currently Scheduled*
Infrared inspections of transmission electric lines and equipment
7.3.4.5
Infrared inspections of distribution electric lines and equipment
7.3.4.4
Detailed inspections of distribution electric lines and equipment
7.3.4.1
Detailed inspections of transmission electric lines and equipment
7.3.4.2
Patrol inspections of transmission electric lines and equipment
7.3.4.12
Substation inspections
7.3.4.15
LiDAR inspections of transmission electric lines and equipment
7.3.4.8
Patrol inspections of distribution electric lines and equipment
7.3.4.11
Pole loading assessment program to determine safety factor
7.3.4.13
7.3.7 - Data Governance
Tracking and Analysis of Near Miss Data
7.3.7.4
Collaborative Research on Utility Ignition and/or Wildfire
7.3.7.2
Centralized Repository for Data
7.3.7.1
Documentation and Disclosure of Wildfire-Related Data and Algorithms
7.3.7.3
7.3.6 - Grid Operations & Protocols
Protocols for PSPS Re-Energization
7.3.6.5
Crew-Accompanying Ignition Prevention and Suppression Resources and Services
7.3.6.3
Automatic Recloser Operations
7.3.6.1
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
7.3.6.4
PSPS Events and Mitigation of PSPS Impacts
7.3.6.6
Stationed and On-Call Ignition Prevention and Suppression Resources and Services
7.3.6.7
7.3.1 - Risk Assessment & Mapping
Initiative Mapping and Estimation of Wildfire and PSPS Risk-Reduction Impact
7.3.1.4
Climate-Driven Risk Map and Modeling Based on Various Relevant Weather Scenarios
7.3.1.2
A Summarized Risk Map That Shows the Overall Ignition Probability and Estimated Wildfire Consequence Along the Electric Lines and Equipment
7.3.1.1
Ignition Probability Mapping Showing the Probability of Ignition Along the Electric Lines and Equipment
7.3.1.3
Match Drop Simulations Showing the Potential Wildfire Consequence of Ignitions that Occurs Along the Electric Lines and Equipment
7.3.1.5
Improvement of Inspections
7.3.4.3
7.3.10 - Stakeholder Cooperation & Community Outreach
Cooperation and best practice sharing with agencies outside CA
7.3.10.2
Community Engagement
7.3.10.1
Forest service and fuel reduction cooperation and joint roadmap
7.3.10.4
Cooperation with suppression agencies
7.3.10.3
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).
Protective Equipment and Device Settings
7.3.6.2

## Slide 3: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
7.3.9 - Emergency Planning & Preparedness
Protocols in Place to Learn from Wildfire Events
7.3.9.6
Customer Support in Emergencies
7.3.9.3
Preparedness and Planning for Service Restoration
7.3.9.5
Not Currently Scheduled*
Community Outreach, Public Awareness, and Communications Efforts
7.3.9.2
Adequate and Trained Workforce for service Restoration
7.3.9.1
Disaster and Emergency Preparedness Plan
7.3.9.4
7.3.3 - Grid Design & System Hardening
Covered Conductor Maintenance
7.3.3.4
Circuit Breaker Maintenance and Installation to De-Energize Lines Upon Detecting a Fault
7.3.3.2
Capacitor Maintenance and Replacement Program
7.3.3.1
Covered Conductor Installation
7.3.3.3
Crossarm Maintenance, Repair, and Replacement
7.3.3.5
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
7.3.3.6
Expulsion Fuse Replacement
7.3.3.7
Grid Topology Improvement to Mitigate or Reduce PSPS events
7.3.3.8
Installation of System Automation Equipment
7.3.3.9
Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps
7.3.3.10
Mitigation of Impact on Customers and Other Residents Affected During PSPS Events
7.3.3.11
Other Corrective Action
7.3.3.12
Pole Loading Infrastructure Hardening and Replacement Program Based on Pole Loading Assessment Program
7.3.3.13
Transformers Maintenance and Replacement
7.3.3.14
Transmission Tower Maintenance and Replacement
7.3.3.15
Undergrounding of Electric Lines and/or Equipment
7.3.3.16
Updates to Grid Topology to Minimize Risk of Ignition in HFTDs
7.3.3.17
Risk Spend Efficiency Analysis
7.3.8.3
Risk Reduction Scenario Development and Analysis
7.3.8.2
Allocation Methodology Development and Application
7.3.8.1
7.3.8 - Resource Allocation Methodology
7.3.2 - Situational Awareness & Forecasting
Forecast of a Fire Risk Index, Fire Potential Index, or Similar
7.3.2.4
Fault Indicators for Detecting Faults on Electric Lines and Equipment
7.3.2.3
Personnel Monitoring Areas of Electric Lines and Equipment in Elevated Fire Risk Conditions
7.3.2.5
Continuous Monitoring Sensors
7.3.2.2
Advanced Weather Monitoring and Weather Stations
7.3.2.1
Weather Forecasting and Estimating Impacts on Electrical Lines and Equipment
7.3.2.6
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).

## Slide 4: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Additional efforts to manage community and environmental impacts
7.3.5.1
7.3.5 - Vegetation Management & Inspections
Not Currently Scheduled*
Remote sensing inspections of vegetation around distribution electric lines and equipment
7.3.5.7
Other discretionary inspection of transmission electric lines and
7.3.5.10
Fuel management (including all wood management) and management of “slash” from vegetation management activities
7.3.5.5
Removal and remediation of trees with strike potential to electric lines and equipment
7.3.5.16
Patrol inspections of vegetation around transmission electric lines and equipment
7.3.5.12
Detailed inspections of vegetation around distribution electric lines and equipment
7.3.5.2
Recruiting and training of vegetation management personnel
7.3.5.14
Quality assurance / quality control of vegetation inspections
7.3.5.13
Substation inspection
7.3.5.17
Identification and remediation of “at-risk species”
7.3.5.15
Vegetation management to achieve clearances around electric lines and equipment
7.3.5.20
Other discretionary inspections of vegetation around distribution electric lines and equipment
7.3.5.9
Vegetation management enterprise system
7.3.5.19
Patrol inspections of vegetation around distribution electric lines and equipment
7.3.5.11
Improvement of inspections
7.3.5.6
Detailed inspections of vegetation around transmission electric lines and equipment
7.3.5.3
Emergency response vegetation management due to red flag warning or other urgent conditions
7.3.5.4
Substation vegetation management
7.3.5.18
Remote sensing inspections of vegetation around transmission electric lines and equipment
7.3.5.8
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).
Vegetation management activities post-fire
7.3.5.21

## Slide 5: WMP Activities Status vs. WMP Activity Goals
7.3.1 - Risk Assessment & Mapping
Ignition Probability Mapping Showing the Probability of Ignition Along the Electric Lines and Equipment
7.3.1.3
Ignition Probability & Wildfire Consequence Mapping Project
Completed
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
A Summarized Risk Map That Shows the Overall Ignition Probability and Estimated Wildfire Consequence Along the Electric Lines and Equipment
7.3.1.1
Ignition Probability & Wildfire Consequence Mapping Project
Completed
Climate-Driven Risk Map and Modeling Based on Various Relevant Weather Scenarios
7.3.1.2
Ignition Probability & Wildfire Consequence Mapping Project
Completed
Initiative Mapping and Estimation of Wildfire and PSPS Risk-Reduction Impact
7.3.1.4
Ignition Probability & Wildfire Consequence Mapping Project
On Track
Match Drop Simulations Showing the Potential Wildfire Consequence of Ignitions that Occurs Along the Electric Lines and Equipment
7.3.1.5
Ignition Probability & Wildfire Consequence Mapping Project
Completed
Contracting with Risk Mapping Resource:
2022 Goal: During 2021 in conjunction with the contracted resource BVES completed its initial Risk Mapping. Due to a lack of historical data the PSPS risk reduction aspect was deferred. For 2022 BVES plans to evaluate the best course of action to add this tool to its Risk Assessment & Mapping program.
Key Actions: BVES continues to evaluate the best course of action to add PSPS Risk Reduction mapping to its Risk Assessment & Mapping program.
7.3.7 - Data Governance
Centralized Repository for Data
7.3.7.1
GIS Data Collection & Sharing
On Track
GIS Data Collection & Sharing Improvements:
BVES continues to work towards a class leading Data Repository.
Key Actions: BVES continue to work with its contracted experts to update its GIS database as well as develop a more streamlines method for reporting and sharing of information
Tracking and Analysis of Near Miss Data
7.3.7.4
WMP Metrics Tracking
Ongoing
WMP Metrics Tracking:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q1 of 2021 there were no compliance issues identified.
Key Actions: BVES recorded necessary metrics for inclusion in quarterly reporting
Not Currently Scheduled

## Slide 6
7.3.2 - Situational Awareness & Forecasting
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
WMP Activities Status vs. WMP Activity Goals
Revised Schedule for 2021 Planned Deployment & Additional Installation:
Volume vs 2022 Goal: BVES does not have any planned weather stations for 2022.
Key Actions: BVES continues to evaluate the needed for future weathers stations in its operating territory.
Advanced Weather Monitoring and Weather Stations
7.3.2.1
Situational Awareness Hardware Program
Completed
Continuous Monitoring Sensors
7.3.2.2
Situational Awareness Hardware Program
Completed
Situational Awareness Hardware Program:
Volume vs 2022 Goal: BVES does not have any planned HD Cameras for 2022.
Key Actions: BVES continues to evaluate the needed for future HD Cameras in its operating territory.
Fault Indicators for Detecting Faults on Electric Lines and Equipment
7.3.2.3
Situational Awareness Hardware Program
On Track
Situational Awareness Hardware Program:
Volume vs Q1 2022 Goal: BVES is scheduled to begin this program in Q3 with a target of 50 fault indicator instillations in 2022
Key Actions: Currently on track to begin work.
Personnel Monitoring Areas of Electric Lines and Equipment in Elevated Fire Risk Conditions
7.3.2.5
Grid Operations & Protocols
No High-Risk Events Occurred
Grid Operations & Protocol:
Volume vs 2022 Goal: BVES has established a resource allocation level for the instance where a high fire risk condition occurs.
Key Actions: BVES currently has the resource pool available to combat high fire risk conditions in its operating area.
Forecast of a Fire Risk Index, Fire Potential Index, or Similar
7.3.2.4
Weather Consultant / Risk Mapping
Completed
Contracting with Risk Mapping Resource:
Volume vs 2022 Goal: During 2021 in conjunction with the contracted resource BVES completed its initial Risk Mapping.
Key Actions: BVES continues to evaluate the need for future improvements to the designed system.
Weather Forecasting and Estimating Impacts on Electrical Lines and Equipment
7.3.2.6
Weather Consultant
Support Requirement Met
Weather Consultant for Weekly Reporting:
2022 Goal: BVES currently has a weather consultant on payroll who supports the weather forecasting and analysis necessary.
Key Actions: Additional task for quarterly aggregation of High Wind Warning and Red Flag Warning accounts to support Quarterly Data Reports.

## Slide 7: WMP Activities Status vs. WMP Activity Goals
7.3.3 - Grid Design & System Hardening Initiatives
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Covered Conductor Replacement Program:
Volume vs Q1 2022 Goal: BVES planned to complete 0 circuit miles in Q1. BVES was able to complete 2.3 circuit miles. The target for 2022 is 12.9 circuit miles.
Key Actions: BVES was able to complete 2.3 circuit miles of covered conductor instillation. This puts this initiative ahead of schedule.
Covered Conductor Installation
7.3.3.3.1
Covered Conductor Replacement Program
Ahead of Plan
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
7.3.3.6.1
Distribution Pole Replacement and Reinforcement – GO 95 Projects
Distribution Pole Replacement and Reinforcement – GO 95 Projects:
Volume vs 2022 Goal: There are no current targets for this initiative in 2022
Key Actions: Initiative targets will be evaluated for future calendar years
Other Corrective Action
7.3.3.12.1
Tree Attachment Removal Program
Completion Toward 80 Attachment Removals for the Year:
Volume vs Q1 2022 Goal: BVES planned to remove 0 tree attachments in Q1 of 2022. No tree attachments were removed in Q1 of 2022.
Key Actions: BVES plans to remove all 80 tree attachments planned for 2022 in Q4 due to a variety of constraints.
Covered Conductor Installation
7.3.3.3.2
Covered Conductor Replacement Program - Radford
On Track
Covered Conductor Replacement Program - Radford:
Volume vs Q1 2022 Goal: BVES planned to complete 0 circuit miles of covered conductor in Q1. The target for 2022 is 2.7 circuit miles.
Key Actions: The project is still on track to hit its target of 2.7 circuit miles in 2022
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
7.3.3.6.3
Evacuation Route Hardening- Pilot
2020 Completed Route Hardening Pilot:
Volume vs 2022 Goal: The BVES does not have an established goal for this pilot as it was completed in 2020.
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
7.3.3.6.2
Covered Conductor Project – Radford Line
Covered Conductor Project – Radford Line:
Volume vs 2022 Goal: There are no current targets for this initiative in 2022
Key Actions: Initiative targets will be evaluated for future calendar years
Distribution Pole Replacement and Reinforcement, Including with Composite Poles
7.3.3.6.4
Evacuation Route Hardening
Ahead of Plan
Evacuation Route Hardening:
Volume vs Q1 2022 Goal: BVES planned to harden 350 poles in Q1 as part of its Evacuation Route Hardening Program. 412 wood poles were hardening with a wire mesh protective coating.
Key Actions: BVES was able to meet its 2022 Goal of 412 poles hardened in Q1 of 2022.
Other Corrective Action
7.3.3.12.2
Evacuation Route Hardening
Ahead of Plan
Evacuation Route Hardening:
Volume vs Q1 2022 Goal: BVES planned to harden 350 poles in Q1 as part of its Evacuation Route Hardening Program. 412 wood poles were hardening with a wire mesh protective coating.
Key Actions: BVES was able to meet its 2022 Goal of 412 poles hardened in Q1 of 2022.

## Slide 8: WMP Activities Status vs. WMP Activity Goals
7.3.3 - Grid Design & System Hardening Initiatives
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Expulsive Fuse Replacement
7.3.3.7
Fuse Replacement Program
0 Remaining
0 Conventional Fuses Remaining:
Volume vs 2022 Goal: There are no current targets for this initiative in 2022
Key Actions: This initiative was completed in 2021.
Mitigation of Impact on Customers and Other Residents Affected During PSPS Events
7.3.3.11.1
Energy Storage Project
Planned
8 MW/ 4 MWh Energy Storage Facility Planned in 2023:
2022 Goal: Seek siting location and work on associated agreements
Key Actions: BVES is still in the process of siting the storage device
Installation of System Automation Equipment
7.3.3.9.1
Grid Automation Program
Grid Automation:
Volume vs Q1 2022 Goal: BVES planned to connect 0 substations to SCADA in Q1 of 2022. BVES plans to have 2 substations connected to SCADA by the end of 2022.
Key Actions: The initiative is on track to meet its target in 2022
Pole Loading Infrastructure Hardening and Replacement Program Based on Pole Loading Assessment Program
7.3.3.13
Pole Loading & Replacement Program
30 Poles Assessed
Pole Assessment Program:
Volume vs Q1 2022 Goal: The goal for Q1 was to assess an additional 30 poles as part of the assessment process. BVES has currently assessed 30 of its targeted 165 poles for 2022.
Key Actions: 30 poles were assessed in Q1. BVES met its goal of 10 poles assessed by assessing 30 poles in Q1 2022.
Grid Topology Improvement to Mitigate or Reduce PSPS events
7.3.3.8
Grid Topology Improvements
Completed
Grid Topology Improvements - Completed:
Volume vs Goal: BVES will install sectionalizing devices as the need is determined. Currently, zero are planned in 2022.
Key Actions: No actions were taken for this initiative in Q1 of 2022.
Installation of System Automation Equipment
7.3.3.9.2
Grid Automation Program // FLISR
Grid Automation FLISR Project:
Volume vs 2022 Goal: There are no activities planned for this initiative in 2022
Key Actions: This project/program will begin in 2023
Installation of System Automation Equipment
7.3.3.9.3
Grid Automation Program // Fuse Trip Saver
Grid Automation Fuse Trip Saver Project:
Volume vs 2022 Goal: There are no activities planned for this initiative in 2022
Key Actions: This project/program will begin in 2023
Updates to Grid Topology to Minimize Risk of Ignition in HFTDs
7.3.3.17
Grid Topology Improvements
Completed
Grid Topology Improvements - Completed:
Volume vs Goal: BVES will install sectionalizing devices as the need is determined. Currently, zero are planned in 2022.
Key Actions: No actions were taken for this initiative in Q1 of 2022.
Mitigation of Impact on Customers and Other Residents Affected During PSPS Events
7.3.3.11.2
BVPP Phase 4 Upgrade Project
Planned
8 MW/ 4 MWh Energy Storage Facility Planned in 2023:
2022 Goal: Seek siting location and work on associated agreements
Key Actions: BVES is still in the process of siting the storage device

## Slide 9: WMP Activities Status vs. WMP Activity Goals
7.3.3 - Grid Design & System Hardening Initiatives
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Capacitor Maintenance and Replacement Program
7.3.3.1
Complete / Ongoing
Circuit Breaker Maintenance and Installation to De-Energize Lines Upon Detecting a Fault
7.3.3.2
Complete / Ongoing
Transformers Maintenance and Replacement
7.3.3.14
Complete / Ongoing
Covered Conductor Maintenance
7.3.3.4
Complete / Ongoing
Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps
7.3.3.10
Complete / Ongoing
Crossarm Maintenance, Repair, and Replacement
7.3.3.5
Complete / Ongoing
BVES Maintenance Best Practice:
The following Grid Design and System Hardening initiatives are covered under ongoing maintenance of sub-transmission and distribution facilities and are not separated as unique WMP initiatives.
7.3.10 - Stakeholder Cooperation & Community Outreach
Cooperation and best practice sharing with agencies outside CA
7.3.10.2
Planned
Cooperation and sharing with agencies outside CA:
Volume vs 2022 Goal: Currently BVES does not participate in cooperation and best practice sharing with agencies outside of CA. BVES plans to have discussion with other agencies within CA to determine how they are approaching this initiative.
Key Actions: No actions have currently been taken
Cooperation with suppression agencies
7.3.10.3
Coordination On Track
Cooperation with suppression agencies:
Volume vs 2022 Goal: BVES does not currently participate in cooperation with suppression agencies. BVES plans to have discussion with suppression agencies and determine if there are additional actions that can be taken to improve their program.
Key Actions: BVES established plans to engage in coordination efforts based on PSPS activations, which will include suppression agencies.
Forest service and fuel reduction cooperation and joint roadmap
7.3.10.4
Planned
Cooperation with forest service and fuel reduction:
Volume vs 2022 Goal: Currently BVES does not participate in forest service and fuel reduction cooperation and joint roadmap programs. BVES plans to have discussions with their forest service contacts to determine the applicability of these programs to improve their overall program.
Key Actions: No actions have currently been taken
Community engagement
7.3.10.1
Community Outreach Program
Exceeded Targets
Community Outreach Program:
Volume vs Q1 2022 Goal: BVES had planned to conducted at minimum 90 outreach activities. BVES recorded 141 outreach activities 157% of target for Q1.
Key Actions: Grizzly Newspaper advertisements are posted during the week (M-F) for either WMP or PSPS and BVES will have 1 advertisement broadcasted each month.

## Slide 10: WMP Activities Status vs. WMP Activity Goals
7.3.4 - Asset Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Detailed inspections of distribution electric lines and equipment
7.3.4.1
Detailed Inspection Program
On Track
Detailed Inspection Activities
Volume vs Q1 2022 Goal: BVES set a target of 0 circuit miles by end of Q1. BVES plans to conduct 29 circuit miles of inspection in 2022.
Key Actions: No actions for this initiative were taken in Q1 of 2022.
Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
7.3.4.9.1
Third Party Ground Patrol
On Track
Contracted Third Party Inspection
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually
Infrared inspections of distribution electric lines and equipment
7.3.4.4
UAV Thermography Program
On Track
UAV Inspection Activities
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually
Intrusive Pole Inspections
7.3.4.6
Intrusive Pole Inspection Program
On Track
Intrusive Pole Inspections
Volume vs Q1 2022 Goal: Zero intrusive pole inspections were scheduled for Q1 of 2022. BVES plans to assess 850 poles in 2022.
Key Actions: No actions for this initiative were taken in Q1 of 2022.
Improvement of Inspections
7.3.4.3
Ongoing Effort
Improvement of Inspections:
Key Actions: BVES is always trying to optimize its inspections and is open to changes/adaptations leading to a better process.
LiDAR inspections of distribution electric lines and equipment
7.3.4.7
LiDAR Inspection Program
On Track
LiDAR Inspection Activities
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually
Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
7.3.4.9.2
UAV HD Photography/Video Program
On Track
UAV HD Photography/Video Program
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually

## Slide 11: WMP Activities Status vs. WMP Activity Goals
7.3.4 - Asset Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Patrol inspections of distribution electric lines and equipment
7.3.4.11
Patrol Inspection Program
Ahead of Plan
Patrol Inspection within the Service Area
Volume vs Q1 2022 Goal: BVES targeted 25 circuit miles inspected in Q1 2022. BVES was able to conduct 83.2 circuit miles of inspection in Q1 2022.
Key Actions: BVES plans to inspect 211 circuit miles in 2022.
Pole loading assessment program to determine safety factor
7.3.4.13
Pole Loading & Replacement Program
Ahead of Plan
Pole Loading & Replacement
Volume vs Q1 2022 Goal: BVES targeted 0 pole assessments in Q1 2022. BVES was able to conduct 27 pole assessments in Q1 2022.
Key Actions: BVES plans to conduct 225 pole assessments in 2022.
Quality assurance / quality control of inspections
7.3.4.14
Quality Control of Inspections
Planned
Quality Control for Electrical Inspections Program
Volume vs Goal: BVES has not yet established quantitative or qualitative targets for the planned quality control program and therefore, have no quarterly units to report in the Quarterly Advice Letter.
Key Actions: Currently on track to discuss framework for formal controls development for internal and third-party inspection patrols.
Substation inspections
7.3.4.15
GO-174 Substation Inspection Program
Ahead of Plan
Substations Inspected
Volume vs Q1 2022 Goal: BVES targeted 36 substation inspections in Q1 2022. BVES was able to complete 39 substation inspections in Q1 2022.
Key Actions: BVES plans to conduct 36 substation inspections per quarter with an annual target of 144 substation inspections.

## Slide 12: WMP Activities Status vs. WMP Activity Goals
7.3.5 - Vegetation Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment
7.3.5.2
Detailed Inspection Program
On Track
Detailed Inspection Activities:
Volume vs Q1 2022 Goal: BVES set a target of 0 circuit miles by end of Q1. BVES plans to conduct 29 circuit miles of inspection in 2022.
Key Actions: No actions for this initiative were taken in Q1 of 2022.
Patrol inspections of vegetation around distribution electric lines and equipment
7.3.5.11
Patrol Inspection Program
Patrol Inspection within the Service Area
Volume vs Q1 2022 Goal: BVES targeted 25 circuit miles inspected in Q1 2022. BVES was able to conduct 83.2 circuit miles of inspection in Q1 2022.
Key Actions: BVES plans to inspect 211 circuit miles in 2022.
Remote sensing inspections of vegetation around distribution electric lines and equipment
7.3.5.7
LiDAR Inspection Program
LiDAR Inspection Activities
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually
Other discretionary inspections of vegetation around distribution electric lines and equipment
7.3.5.9.1
Third Party Ground Patrol
Contracted Third Party Inspection
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually
Emergency response vegetation management due to red flag warning or other urgent conditions
7.3.5.4
Emergency Preparedness & Response Program
Emergency Preparedness and Response Program:
Volume vs Goal: BVES did not record an emergency in Q1 of 2022. This means that the use of the Emergency Preparedness & Response Program was not required.
Improvement of inspections
7.3.5.6
Quality Control of Inspections
Improvement of Inspections:
Volume vs Q1 2022 Goal: One vegetation management audit was planned for Q1 2022. BVES was able to complete 2 vegetation management audits in Q1 2022.
Key Actions: BVES plans to conduct one audit per quarter with an annual target of 4 vegetation management audits in 2022.
Identification and remediation of “at-risk species”
7.3.5.15
Planned
Remediation of At-Risk Species:
Key Actions: BVES and its contractors account for at risk species when doing field work and evaluation. Cycle Breaker vegetation is are an example of what may be recorded. Remediation as a separate initiative is considered for the future with no set program/project at this time.
Other discretionary inspections of vegetation around distribution electric lines and equipment
7.3.5.9.2
UAV HD Photography/Video Program
UAV HD Photography/Video Program
Volume vs Q1 2022 Goal: Zero circuit miles were scheduled for Q1 of 2022.
Key Actions: BVES plans to complete 211 circuit miles, which would fulfil the goal of conducting infrared inspections of the entire system annually

## Slide 13: WMP Activities Status vs. WMP Activity Goals
7.3.5 - Vegetation Management & Inspection
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Removal and remediation of trees with strike potential to electric lines and equipment
7.3.5.16
Enhanced Vegetation Management Program
Mid-Year Detailed Inspection Activities
Volume vs Q1 2022 Goal: BVES planned to remove/remediate 18 hazardous trees in Q1 2022. BVES was able to remove/remediate 20 hazardous trees in Q1 2022.
Key Actions: BVES plans to clear 18 circuit miles per quarter with an annual target of 72 circuit miles cleared in 2022.
Substation inspection
7.3.5.17
GO-174 Substation Inspection Program
Inspected & Cleared Vegetation
Substations Inspected
Volume vs Q1 2022 Goal: BVES planned to inspect 36 substations in Q1 2022. BVES was able to clear 39 substations in Q1 2022.
Key Actions: BVES plans to inspect 36 substations per quarter with an annual target of 144 circuit miles cleared in 2022.
Substation vegetation management
7.3.5.18
Substation Vegetation Management Inspections & Corrections
Substation Inspection
Key Actions: This is a contractor lead initiative. Following the monthly substation inspections identified vegetation concerns and their associated waste are removed by the contractor per the contract. At which point BVES is notified, and the inspection and removal is logged.
Vegetation management enterprise system
7.3.5.19
GIS Data Collection & Sharing
Trimmed Trees Logged
GIS Data Collection & Sharing:
Volume vs 2022 Goals: BVES continues to work towards a class leading Data Repository.
Key Actions: BVES continue to work with its contracted experts to update its GIS database as well as develop a more streamlines method for reporting and sharing of information.
Quality assurance / quality control of vegetation inspections
7.3.5.13
Quality Control of Inspections
16 QC Reviews
Quality Control for Electrical Inspections Program
Volume vs Q1 2022 Goal: BVES planned to conduct 18 quality controls reviews in Q1 2022. BVES was able to conduct 16 quality control reviews in Q1 2022.
Key Actions: BVES plans to conduct 18 quality control reviews per quarter with an annual target of 72 quality control reviews in 2022.
Recruiting and training of vegetation management personnel
7.3.5.14
Vegetation Management Program Staffing
Met Targets
Resource Allocation & Training:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q4 of 2021, there were no compliance issues identified.
Key Actions: BVES reviewed staffing program and methodology
Vegetation management to achieve clearances around electric lines and equipment
7.3.5.20
Enhanced Vegetation Management Program
Circuit Miles Cleared:
Volume vs Q1 2022 Goals: BVES planned to clear 18 circuit miles in Q1 2022. BVES was able to clear 36.6 circuit miles in Q1 2022.
Key Actions: BVES plans to clear 18 circuit miles per quarter with an annual target of 72 circuit miles cleared in 2022.
Fuel management (including all wood management) and management of “slash” from vegetation management activities
7.3.5.5
Enhanced Vegetation Management Program
Contractor Meets Requirements
Enhanced VM Program Inspection
Key Actions: This is a contractor lead initiative. Following the monthly substation inspections identified vegetation concerns and their associated waste are removed by the contractor per the contract. At which point BVES is notified, and the inspection and removal is logged.

## Slide 14: WMP Activities Status vs. WMP Activity Goals
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Alternative & Advance Technologies
7.3.6 - Grid Operations & Operating Protocols
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
7.3.6.4
PSPS Program & Procedures
Ongoing
Protocols for PSPS Re-Energization
7.3.6.5
PSPS Program & Procedures
Established
PSPS Events and Mitigation of PSPS Impacts
7.3.6.6
PSPS Program & Procedures
0 PSPS Events
PSPS Program & Procedure:
BVES has an established program and procedures in place. BVES continues to monitor all aspects of the program for compliance. During the period Q1 of 2022 there were no PSPS events that would require the use of said program.
Key Actions: There were no key actions related to the Program as there were no PSPS events.
Automatic Recloser Operations
7.3.6.1
Grid Automation Program
Completed
Fault Interrupters – IntelliRupters Pulsing Auto Reclosers – Completed Cycle Work:
Volume vs Goal: BVES plans to install S&C’s Pulse Closer Fault Interrupters across its major 34 kV system auto-reclosers that was completed in 2020. BVES has installed Fault Indicators (FIs) at key locations to reduce the time it takes to locate faults, thereby reducing the time to isolate faults from the system or correcting the damage. Prior to the start of the program, BVES had 110 FIs installed in its system at key locations. As part of the WMP, BVES will install an additional 117 FIs at 39 key locations to provide optimal FI coverage in the system in 2022.
Key Actions: BVES has completed the effort as identified within this WMP cycle.
Protective equipment and device settings
7.3.6.2
Protective Equipment and Device Settings
Protective Equipment and Device Settings:
Key Actions: All protective device settings are logged and controlled by Engineering. The settings are set based on coordination studies.
Crew-Accompanying Ignition Prevention and Suppression Resources and Services
7.3.6.3
Emergency Preparedness & Response Program
No Emergency Events
Stationed and On-Call Ignition Prevention and Suppression Resources and Services
7.3.6.7
Emergency Preparedness & Response Program
Ongoing
Emergency Preparedness & Response Program:
BVES has an established program in place. BVES continues to monitor all aspects of the program for compliance. During the period Q1 of 2022, there were no emergency events that would require the use of said program.
Key Actions: There were no key actions related to this program in Q1 of 2022.

## Slide 15: WMP Activities Status vs. WMP Activity Goals
7.3.9 - Emergency Planning & Preparedness
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
7.3.8 - Resource Allocation Methodology
Allocation Methodology Development and Application
7.3.8.1
Resource Allocation Methodology
Program In Process
Resource Allocation Methodology [Primary]:
BVES has an established program in place and continues to monitor all aspects of the program for additional staff. During the period Q1 of 2022, there were no gap issues identified.
Key Actions: BVES routinely reviewed staffing program needs.
Risk Reduction Scenario Development and Analysis
7.3.8.2
Ignition Probability & Wildfire Consequence Mapping
Completed
Contracting with Risk Mapping Resource
2022 Goal: During 2021 in conjunction with the contracted resource BVES completed its initial Risk Mapping. Due to a lack of historical data, the PSPS risk reduction aspect was deferred. For 2022, BVES plans to contract with Technosylva to develop real-time fire modeling capabilities.
Key Actions: BVES continues to evaluate the best course of action to add PSPS Risk Reduction mapping and has engaged a contractor for additional modeling support.
Risk Spend Efficiency Analysis
7.3.8.3
Ignition Probability & Wildfire Consequence Mapping
In Progress
Contracting with Risk Mapping Resource
2022 Goal: During 2021 in conjunction with the contracted resource BVES completed its initial Risk Mapping. Due to a lack of historical data the PSPS risk reduction aspect was deferred. For 2022 BVES plans to evaluate the best course of action to add this tool to its Risk Assessment & Mapping program.
Key Actions: BVES continues to evaluate the best course of action to add PSPS Risk Reduction mapping to its Risk Assessment & Mapping program.
Protocols in Place to Learn from Wildfire Events
7.3.9.6
Emergency Preparedness & Response Program
In Progress
Customer Support in Emergencies
7.3.9.3
Emergency Preparedness & Response Program
Established
Preparedness and Planning for Service Restoration
7.3.9.5
Emergency Preparedness & Response Program
Ongoing
Disaster and Emergency Preparedness Plan
7.3.9.4
Emergency Preparedness & Response Program
Established
Emergency Preparedness and Response Program:
Volume vs Q1 2022 Goal: BVES did not record an emergency in Q1 of 2022. This means that the use of the Emergency Preparedness & Response Program was not required.
Adequate and Trained Workforce for Service Restoration
7.3.9.1
Resource Allocation Methodology
Completed
Resource Allocation Methodology:
BVES has an established program in place and continues to monitor all aspects of the program for compliance. During the period Q1 of 2022, there were no compliance issues identified.
Key Actions: Staffing for service restoration was reviewed and declared adequate. In the instance of a service restoration event BVES will review the results and re-evaluate staffing if necessary.
Community Outreach, Public Awareness, and Communications Efforts
7.3.9.2
Community Outreach Program
Targets Exceeded
Community Outreach Program:
Volume vs Q1 2022 Goal: BVES had planned to conduct 90 outreach activities at minimum. BVES recorded 141 outreach activities 157% of target for Q1.
Key Actions: BVES exceeded its outreach targets in Q1 at 157% of the established target. BVES continues to establish coordination and communication events as pre-season PSPS planning takes place.