## Slide 1: SDG&E’s 2022 Wildfire Mitigation Plan 1st Quarter Progress Update
(All data as of March 31, 2022)

## Slide 2: 2022 Wildfire Mitigation Plan Activities Q1 Summary
7.3.3.1
Capacitor maintenance and replacement program
7.3.3.3
Covered conductor installation
7.3.3.7
Expulsion fuse replacement
7.3.3.8.1
PSPS sectionalizing enhancements
7.3.3.8.2
Microgrids
7.3.3.9
Installation of system automation equipment
7.3.3.10
Maintenance, repair, and replacement of connectors, including hotline clamps
7.3.3.11.1
Generator grant programs
7.3.2.1
Advanced weather monitoring and weather stations
7.3.3.11.2
Standby power programs
7.3.3.11.3
Generator assistance programs
7.3.3.16
Undergrounding of electric lines and/or equipment
7.3.3.17.1
Distribution overhead system hardening
7.3.3.17.2.1
Overhead transmission fire hardening
7.3.3.18.1
Distribution communications reliability improvements
7.3.3.18.2
Lightning arrestor removal and replacement
7.3.4.1
CMP HFTD Inspections
5 Year Detailed
7.3.4.2
Detailed inspections of transmission electric lines and equipment
7.3.4.4
Infrared inspections of distribution electric lines and equipment
7.3.4.5
Infrared inspections of transmission electric lines and equipment
7.3.4.6
CMP HFTD Inspections - Wood Pole Intrusive
7.3.4.9.1
HFTD Tier 3 distribution pole inspections
7.3.5.2
Detailed inspections of vegetation around distribution
7.3.5.5
Fuels management and reduction of "slash"
7.3.5.9
Other discretionary inspection of vegetation around distribution electric lines and equipment
7.3.5.20
Vegetation management to achieve clearances around electric lines and equipment
7.3.4.9.2
Drone assessments of distribution infrastructure
7.3.4.10.2
Additional transmission aerial 69kV tier 3 visual inspection
7.3.4.11
Patrol inspections of distribution electric lines and equipment
7.3.4.12
Patrol inspections of transmission electric lines and equipment
7.3.4.15
Substation inspections
7.3.2.3
Fault indicators for detecting faults on electric lines and equipment
7.3.4.10.1
Drone assessments of transmission infrastructure
7.3.2.2.1
Air Quality Index
7.3.2.2.2
Satellite-based remote sensing
7.3.3.17.2.2
Underground transmission fire hardening
7.3.3.17.2.3
Distribution overhead transmission fire hardening
7.3.3.18.3
Avian Mitigation
7.3.5.7
LiDAR inspections of vegetation around distribution
7.3.5.16
Removal and remediation of trees with strike potential to electric lines and equipment
7.3.5.13
QA/QC of inspections

## Slide 3: Q1 Activity Status vs 2022 Goals
7.3.2.1
4
Weather Station
Upgrades
20% Advanced weather monitoring & station upgrades
Volume vs 2022 Goal: 4 of 20 weather station upgrades (20%)
Key Actions: Program on time and on target.
7.3.2.3
12
Wireless fault
indicators
2% Fault indicators for detecting faults on electric lines and equipment
Volume vs 2022 Goal: 12 of 500 wireless fault indicators (2%)
Key Actions: Program on time and on target.
7.3.2.2.1
1
Sensors
16% Continuous monitoring sensors - Air Quality Index
Volume vs 2022 Goal: 1 of 6 air quality sensors installed (16%)
Key Actions: Program on time and on target.
7.3.2 – Situational Awareness and Forecasting
75% Satellite-based remote sensing
Volume vs 2022 Goal: 6 of 8 cameras installed (75%)
Key Actions: Program on time and on target.
7.3.2.2.2
6
Cameras

## Slide 4: Q1 Activity Status vs 2022 Goals
7.3.3.1
5
Capacitors
13% Capacitor maintenance and replacement program - SCADA capacitors
Volume vs 2022 Goal: 5 of 40 SCADA capacitors (13%)
Key Actions: Program on time and on target.
7.3.3.7
98
Fuses
35% Expulsion fuse replacement
Volume vs 2022 Goal: 98 of 277 expulsion fuses (35%)
Key Actions: Program on time and on target.
7.3.3.8.2
1
Microgrids
25% Microgrids
Volume vs 2022 Goal: 1 of 4 microgrids (25%)
Key Actions: Program on time and on target.
7.3.3.10
576
Hotline Camps
35% Maintenance, repair, and replacement of connectors, including hotline clamps
Volume vs 2022 Goal: 576 of 1,650 hotline clamps (35%)
Key Actions: Program on time and on target.
7.3.3.3
3
Miles
5% Covered conductor installation - Distribution OH Hardening
Volume vs 2022 Goal: 3 of 60 miles covered conductor (5%)
Key Actions: Program on time and on target.
7.3.3.8.1
3
Switches
30% PSPS sectionalizing enhancements
Volume vs 2022 Goal: 3 of 10 sectionalizing devices (30%)
Key Actions: Program on time and on target.
7.3.3.9
0
Circuits
0% Installation of system automation equipment
Volume vs 2022 Goal: 0 of 8 circuits enabled (0%)
Key Actions: Program on time and on target. 3 circuits planned for Q2.
7.3.3.11.1
8
Generators
0% Generator Grant Programs
Volume vs 2022 Goal: 8 of 3,000 generators (0%)
Key Actions: Program on time and on target.
7.3.3 – Grid Design and System Hardening (1 of 2)

## Slide 5: Q1 Activity Status vs 2022 Goals
7.3.3.11.2
46
Generators
11% Standby power programs
Volume vs 2022 Goal: 46 of 412 generators (11%)
Key Actions: Program on time and on target.
7.3.3.16
9.91
Miles
15% Undergrounding of electric lines and/or equipment
Volume vs 2022 Goal: 9.91 of 65 miles UG (15%)
Key Actions: Program on time and on target.
7.3.3.17.2.1
1.45
Miles
8% Overhead transmission fire hardening
Volume vs 2022 Goal: 1.45 of 18.5 miles of OH miles hardened (8%),
Key Actions: Program on time and on target.
7.3.3.18.1
2
Base stations
8% Distribution communications reliability improvements
Volume vs 2022 Goal: 2 of 25 base stations (8%)
Key Actions: Program on time and on target.
7.3.3.11.3
0
Generators
0% Generator assistance programs
Volume vs 2022 Goal: 0 of 1250 generators (0%)
Key Actions: Program on time and on target.
7.3.3.17.1
12.65
Miles
253% Distribution overhead system hardening
Volume vs 2022 Goal: 12.65 of 5 miles hardened (253%)
Key Actions: Program on time and on target.
7.3.3.17.2.3
0
Miles
0% Underground transmission fire hardening
Volume vs 2022 Goal: 0 of 5.5 miles hardened (0%)
Key Actions: Program on time and on target.
7.3.3.18.2
341
Arrestors
18% Lightning arrestor removal and replacement
Volume vs 2022 Goal: 341 of 1,848 lightning arrestors replaced (18%)
Key Actions: Program on time and on target.
7.3.3 – Grid Design and System Hardening (2 of 2)
7.3.3.17.2.2
0
Miles
0% Overhead transmission fire hardening (Distribution Underbuilt)
Volume vs 2022 Goal: 0 of 7.6 miles hardened (0%)
Key Actions: Program on time and on target.
7.3.3.18.3
205
Poles
24% Avian mitigation
Volume vs 2022 Goal: 205 of 874 poles (24%)
Key Actions: Program on time and on target.

## Slide 6: Q1 Activity Status vs 2022 Goals
7.3.4.1
9,639
Inspections
53% CMP HFTD Inspections - 5 Year Detailed
Volume vs 2022 Goal: 9,639 of 18,177 inspections (53%)
Key Actions: Program on time and on target.
38% CMP HFTD Inspections - Wood Pole Intrusive
Volume vs 2022 Goal: 135 of 350 inspections (38%)
Key Actions: Program on time and on target.
52% Drone assessments of distribution infrastructure
Volume vs 2022 Goal: 11,441 of 22,000 inspections (52%)
Key Actions: Program on time and on target.
0% Transmission Infrared Inspections
Volume vs 2022 Goal: 0 of 6,154 inspections (0%)
Key Actions: Program will begin in July per schedule.
101% HFTD Tier 3 distribution pole inspections
Volume vs 2022 Goal: 12,404 of 12,286 inspections (101%)
Key Actions: Program on time and on target.
7.3.4 – Asset Management and Inspections (1 of 2)
7.3.4.4
3,820
Inspections
7.3.4.9.2
11,441
Inspections
7.3.4.5
0
Inspections
7.3.4.9.1
12,404
Inspections
94% Drone assessment of transmission
Volume vs 2022 Goal: 468 of 500 inspections (94%)
Key Actions: Program on time and on target.
7.3.4.10.1
468
Inspections
7.3.4.2
531
Inspections
7.3.4.6
135
Inspections
25% Transmission Inspections – Detailed
Volume vs 2022 Goal: 531 of 2,087 inspections (25%)
Key Actions: Program on time and on target.
31% Distribution Infrared Inspections
Volume vs 2022 Goal: 3,820 of 12,000 inspections (31%)
Key Actions: Program on time and on target.

## Slide 7: Q1 Activity Status vs 2022 Goals
7.3.4 – Asset Management and Inspections (2 of 2)
7.3.4.15
91
Inspections
27% Substation inspections
Volume vs 2022 Goal: 91 of 330 inspections (27%)
Key Actions: Program on time and on target.
7
31% Patrol inspections of transmission electric lines and equipment
Volume vs 2022 Goal: 1,962 of 6,312 inspections (31%)
Key Actions: Program on time and on target.
7.3.4.11
37,567
Inspections
7.3.4.10.2
0
Inspections
0% Additional Transmission Aerial 69kV Tier 3 Visual Inspection
Volume vs 2022 Goal: 0 of 1,654 inspections (0%)
Key Actions: Program will begin in August per schedule.
7.3.4.12
1,962
Inspections
43% Patrol inspections of distribution electric lines and equipment
Volume vs 2022 Goal: 37,567 of 86,490 inspections (43%)
Key Actions: Program on time and on target.

## Slide 8: Q1 Activity Status vs 2022 Goals
7.3.5 – Vegetation Management and Inspections
25% Detailed inspections of vegetation around distribution electric lines and equipment
Volume vs 2022 Goal: 123,917 of 491,822 trees inspected (25%)
Key Actions: Program on time and on target.
16% Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Volume vs 2022 Goal: 2,110 of 12,500 trees trimmed/removed (16%)
Key Actions: Program on time and on target.
25% Quality assurance/quality control of inspections
Volume vs 2022 Goal: 3.75% of 15% of inspections (25%)
Key Actions: Program on time and on target.
18% Fuels management and reduction of "slash" from vegetation management activities
Volume vs 2022 Goal: 90 of 500 poles cleared (18%)
Key Actions: Program on time and on target. Work will resume in Q3.
7.3.5.2
123,917
Inspections
7.3.5.9
2,110
Trees
7.3.5.13
3.75
Inspections
7.3.5.5
90
Poles Cleared
7.3.5.7
56.2
Circuit Line Mile
8% LiDAR inspections of vegetation around distribution electric lines and equipment
Volume vs 2022 Goal: 56.2 of 730 miles inspected (8%)
Key Actions: Program on time and on target.
0% Removal and remediation of trees with strike potential to electric lines and equipment
Volume vs 2022 Goal: 0 of 106 Vegetation Management Areas Completed (0%)
Key Actions: VMAs in the HFTD scheduled for inspection beginning in Q2.
7.3.5.16
0
Vegetation Management Areas
39% Vegetation management to achieve clearances around electric lines and equipment
Volume vs 2022 Goal: 13,317 of 34,000 poles brushed (39%)
Key Actions: Program on time and on target.
7.3.5.20
13,317
Poles brushed