## Project List
Order | Order Description | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2020 Miles Installed | 2021 Miles Installed | 2022 Forecast Miles | 2023 Forecast Miles | 2024 Forecast Miles | Div | Region | City | County | Latitude | Longitude | Circuit Protection Zone | 2021 Risk Rank | Project Type (see 3rd tab for description) | HFTD Tier
35286103 |  | Base SH | 08W | UNSE | Scoping/Scoped | 13.9201 | 0 | 0 | 13.9201 | 0 | 0 | 0 | 13.9201 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012510 | 3328 | CWSP 2022-2023 | Tier 2
35294729 |  | Base SH | 08W | UNSE | Scoping/Scoped | 6.4 | 0 | 0 | 6.4 | 0 | 0 | 0 | 6.4 | 0 | NV | Region 2 - North East | Burney | Shasta |  |  | PIT NO 3 21011482 | 2320 | CWSP 2022-2023 | Tier 2
35294730 |  | Base SH | 08W | UNSE | Scoping/Scoped | 6.21 | 0.079924 | 0 | 6.29 | 0 | 0 | 0 | 6.29 | 0 | NV | Region 2 - North East | Burney | Shasta |  |  | PIT NO 3 21011482 | 2320 | CWSP 2022-2023 | Tier 2
35223060 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0 | 0 | 0.036553 | SI | Region 2 - North East | Downieville | SIERRA |  |  | ALLEGHANY 1101VR816 | 2010 | PSPS - Community Resiliency | Tier 3
35298571 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Anderson | SHASTA |  |  | ANDERSON 11031600 | 143 | CWSP 2022-2023 | Tier 2
35254242 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.9436 | 0 | 1.9436 | 0 | 0 | 0 | 1.9436 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 110149122 | 330 | CWSP 2022-2023 | Tier 2
35278889 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1968 | 0 | 2.1968 | 0 | 0 | 0 | 2.1968 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 110149122 | 330 | CWSP 2022-2023 | Tier 2
35279181 |  | Fire Rebuild | 08W | ESTS | Estimating | 5.589 | 0 | 0 | 5.589 | 0 | 0 | 5.589 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1102CB | 378 | FRRB - UG - 2021 | Tier 2 & 3
35277926 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.4417 | 0 | 3.4417 | 0 | 0 | 3.4417 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35277927 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8672 | 0 | 2.8672 | 0 | 0 | 0 | 2.8672 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35277929 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7939 | 0 | 2.7939 | 0 | 0 | 2.7939 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35277930 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.32936 | 0 | 0.32936 | 0 | 0 | 0 | 0.32936 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35277931 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.5072 | 0 | 3.5072 | 0 | 0 | 0 | 3.5072 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35254078 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.6199 | 0 | 2.6199 | 0 | 0 | 2.6199 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35254079 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.4011 | 0 | 2.4011 | 0 | 0 | 2.4011 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35254243 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.91 | 0 | 2.91 | 0 | 0 | 0 | 2.91 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35254244 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 2.66 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35254245 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 2.958 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35254246 |  | Base SH | 08W | ADER | Estimating | 0 | 2.6201 | 0 | 2.6201 | 0 | 0 | 2.6201 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35254247 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.95 | 0 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35277936 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.94 | 0 | 3.94 | 0 | 0 | 0 | 3.94 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35277937 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8701 | 0 | 2.8701 | 0 | 0 | 0 | 2.8701 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35235677 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 5.414 | 0 | 0 | 5.414 | 0 | 5.414 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35278091 |  | Base SH | 08W | ADER | Estimating | 0 | 2.839 | 0 | 2.839 | 0 | 0 | 0 | 2.839 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278092 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.8369 | 0 | 3.8369 | 0 | 0 | 0 | 3.8369 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35294728 |  | Base SH | 08W | UNSE | Scoping/Scoped | 5.3799 | 0 | 0 | 5.3799 | 0 | 0 | 0 | 5.3799 | 0 | NV | Region 2 - North East | Burney | Shasta |  |  | PIT NO 3 2101CB | 1816 | CWSP 2022-2023 | Tier 2
35278096 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.2299 | 0 | 1.2299 | 0 | 0 | 1.2299 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278097 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.2 | 0.29602 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278098 |  | Base SH | 08W | ADER | Estimating | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 1.54 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278890 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.75 | 0 | 1.75 | 0 | 0 | 0 | 1.75 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278891 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35278892 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 2.5299 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35277921 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 2.4 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35277922 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 1.76 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35277923 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 3.1701 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35256083 |  | Base SH | 08W | UNSE | Scoping/Scoped | 5.0909 | 2.467 | 0 | 7.558 | 0 | 0 | 0 | 7.558 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35278090 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8492 | 0.39583 | 3.2451 | 0 | 0 | 0 | 3.2451 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35277933 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1036 | 0 | 2.1036 | 0 | 0 | 0 | 2.1036 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35277934 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1415 | 0 | 2.1415 | 0 | 0 | 0 | 2.1415 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35297692 |  | Fire Rebuild | 08W | ESTS | Estimating | 4.6598 | 0 | 0 | 4.6598 | 0 | 0 | 4.6598 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35254240 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 0 | 2.1252 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35254241 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8248 | 0 | 2.8248 | 0 | 0 | 0 | 2.8248 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35226629 |  | Base SH | 08W | PEND | Permitting/Dependency | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 4.5 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35052731 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.5271 | 0 | 1.5271 | 0 | 0.57917 | 0.94792 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ |  |  | BIG BASIN 110110296 | 2456 | Pre | Tier 3
35113950 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.2451 | 0 | 3.2451 | 0 | 0 | 3.2451 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ |  |  | BIG BASIN 110110296 | 2456 | Pre | Tier 3
35113951 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.3443 | 0 | 2.3443 | 0 | 0 | 2.3443 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ |  |  | BIG BASIN 110110296 | 2456 | Pre | Tier 3
35219289 |  | Base SH | 08W | ESTS | Estimating | 4.3544 | 0 | 0 | 4.3544 | 0 | 0 | 4.3544 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35142826 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.5932 | 0 | 1.5932 | 0 | 1.5932 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada |  |  | BRUNSWICK 11032200 | 2521 | Pre | Tier 3
35117443 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 2.1347 | 0 | 2.1347 | 0 | 2.1347 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35115148 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.1331 | 0 | 2.1331 | 2.0127 | 0.12045 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35115151 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.9057 | 0 | 1.9057 | 0 | 1.9057 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35115152 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.7013 | 0 | 1.7013 | 0 | 0.80076 | 0.90057 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35115153 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7006 | 0 | 1.7006 | 0 | 1.7006 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35115154 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.6462 | 0 | 1.6462 | 0 | 1.6462 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35061206 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7348 | 0 | 1.7348 | 0 | 1.7348 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35061212 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.9985 | 0 | 1.9985 | 0 | 1.9985 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35061213 |  | Base SH | 08W | CLSD | Closed | 0 | 1.4511 | 0 | 1.4511 | 1.3445 | 0.10663 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | BRUNSWICK 110350070 | 2144 | Pre | Tier 3
35284364 |  | Base SH | 08W | UNSE | Scoping/Scoped | 4.3498 | 0.040341 | 0 | 4.3902 | 0 | 0 | 0 | 4.3902 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | STANISLAUS 1702CB | 235 | CWSP 2022-2023 | Tier 2 & 3
35223062 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0.13125 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA |  |  | CALISTOGA 1102184814 | 3098 | PSPS - Community Resiliency | Tier 2
35114100 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.95076 | 0 | 0.95076 | 0 | 0.95076 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ |  |  | CAMP EVERS 21065020 | 2464 | Pre | Tier 3
35114102 |  | Base SH | 08W | CLSD | Closed | 0 | 0.73428 | 0 | 0.73428 | 0.16004 | 0.57424 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ |  |  | CAMP EVERS 21065020 | 2464 | Pre | Tier 3
35114103 |  | Base SH | 08W | CLSD | Closed | 0 | 1.1294 | 0 | 1.1294 | 0 | 1.1294 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ |  |  | CAMP EVERS 21065020 | 2464 | Pre | Tier 3
35243441 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 2.3233 | 0 | NV | Region 2 - North East | Brownsville | YUBA |  |  | CHALLENGE 11025462 | 1428 | REMG 2022-2023 | Tier 2 & 3
35292754 |  | Fire Rebuild | 08W | ESTS | Estimating | 4.2299 | 0 | 0 | 4.2299 | 0 | 0 | 4.2299 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35145522 |  | Base SH | 08W | PEND | Permitting/Dependency | 4.0494 | 0 | 0 | 4.0494 | 0 | 0 | 4.0494 | 0 | 0 | SI | Region 2 - North East | El Dorado Hills | El Dorado |  |  | CLARKSVILLE 2104CB | 134 | PSPS - Community Resiliency | Tier 2
35223344 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 3.8902 | 0 | 0 | 3.8902 | 0 | 3.8902 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35223345 |  | Fire Rebuild | 08W | FICL | Post-Construction | 3.7676 | 0 | 0 | 3.7676 | 0 | 3.7676 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35062376 |  | Base SH | 08W | APPR | Estimating | 3.2866 | 0 | 0 | 3.2866 | 0 | 0 | 3.2866 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  | SHINGLE SPRINGS 210935598 | 159 | Top 20% MAVF CPZ | Tier 3
35278899 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.9449 | 0 | 0 | 2.9449 | 0 | 0 | 0 | 2.9449 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | STANISLAUS 1701CB | 56 | CWSP 2022-2023 | Tier 2 & 3
35225593 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.05 | 0 | 1.05 | 0 | 0 | 1.05 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | CLAYTON 221296224 | 377 | ECOP - Top 20% | Tier 3
35217275 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.9 | 0 | 0 | 2.9 | 0 | 0 | 2.9 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo |  |  | HALF MOON BAY 110369412 | 2055 | FRRB - UG - 2021 | Tier 2
35233950 |  | Base SH | 08W | ESTS | Estimating | 2.8943 | 0 | 0 | 2.8943 | 0 | 0 | 2.8943 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35243452 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.3625 | 0 | 3.3625 | 0 | 0 | 3.3625 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410030 | 144 | CWSP 2022-2023 | Tier 2
35249996 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.9536 | 0 | 1.9536 | 0 | 0 | 1.9536 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410030 | 144 | CWSP 2022-2023 | Tier 2
35249997 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.115 | 0 | 2.115 | 0 | 0 | 2.115 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410030 | 144 | CWSP 2022-2023 | Tier 2
35249998 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.6773 | 0 | 3.6773 | 0 | 0 | 3.6773 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410030 | 144 | CWSP 2022-2023 | Tier 2
35249999 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.0688 | 0 | 2.0688 | 0 | 0 | 2.0688 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410030 | 144 | CWSP 2022-2023 | Tier 2
35227260 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2362 | 0 | 2.2362 | 0 | 2.2362 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410335 | 66 | Top 250 Miles | Tier 2
35227261 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.729 | 0 | 1.729 | 0 | 1.729 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410335 | 66 | Top 250 Miles | Tier 2
35227262 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7343 | 0 | 1.7343 | 0 | 1.7343 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 210410335 | 66 | Top 250 Miles | Tier 2
35240160 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 4.3841 | 0 | 4.3841 | 0 | 0 | 4.3841 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35240162 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35240163 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.2153 | 0 | 2.2153 | 0 | 0 | 0 | 2.2153 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35249871 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.0186 | 0 | 2.0186 | 0 | 0 | 2.0186 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35249872 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.725 | 0 | 2.725 | 0 | 0 | 2.725 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35249873 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.8913 | 0 | 3.8913 | 0 | 0 | 0 | 3.8913 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35249874 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.7922 | 0 | 3.7922 | 0 | 0 | 0 | 3.7922 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35250737 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8564 | 0 | 2.8564 | 0 | 0 | 0 | 2.8564 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35250738 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.4856 | 0 | 3.4856 | 0 | 0 | 0 | 3.4856 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21045310 | 61 | CWSP 2022-2023 | Tier 2
35240164 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0979 | 0 | 2.0979 | 0 | 0 | 0 | 2.0979 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 2104570682 | 78 | CWSP 2022-2023 | Tier 2
35240165 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.8498 | 0 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21046210 | 132 | CWSP 2022-2023 | Tier 2
35249875 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.6394 | 0 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21046210 | 132 | CWSP 2022-2023 | Tier 2
35249876 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.6483 | 0 | 3.6483 | 0 | 0 | 3.6483 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21046210 | 132 | CWSP 2022-2023 | Tier 2
35249877 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 1.0299 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 21046210 | 132 | CWSP 2022-2023 | Tier 2
35219097 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.4794 | 0 | 2.4794 | 0 | 0 | 2.4794 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA |  |  | COARSEGOLD 2104CB | 22 | Top 250 Miles | Tier 2
35229051 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA |  |  | CORNING 110253184 | 413 | Remote Grid Pilot | Tier 3
35276100 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA |  |  | CORNING 110253184 | 413 | Remote Grid Pilot | Tier 3
35241072 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.6 | 0.21004 | 3.81 | 0 | 0 | 3.81 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35243447 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.64 | 0.032955 | 2.6729 | 0 | 0 | 2.6729 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35259511 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 2.77 | 0 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35235676 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.8788 | 0 | 0 | 2.8788 | 0 | 0.11231 | 2.7665 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35259515 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4752 | 0 | 2.4752 | 0 | 0 | 2.4752 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35227007 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.8756 | 0 | 0 | 2.8756 | 0 | 0 | 0 | 2.8756 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35259514 |  | Base SH | 08W | ADER | Estimating | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 3.61 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041582 | 301 | CWSP 2022-2023 | Tier 2
35241071 |  | Base SH | 08W | APPR | Estimating | 0 | 2.0356 | 0.325 | 2.3606 | 0 | 0 | 2.3606 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041582 | 301 | CWSP 2022-2023 | Tier 2
35243448 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.69 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 110449024 | 99 | CWSP 2022-2023 | Tier 2
35241073 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.8553 | 0 | 3.8553 | 0 | 0 | 3.8553 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 110449024 | 99 | CWSP 2022-2023 | Tier 2
35259517 |  | Base SH | 08W | ESTS | Estimating | 0 | 4.6008 | 0 | 4.6008 | 0 | 0 | 4.6008 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 110449024 | 99 | CWSP 2022-2023 | Tier 2
35259513 |  | Base SH | 08W | ESTS | Estimating | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 4.64 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | DESCHUTES 110449024 | 99 | CWSP 2022-2023 | Tier 2
35219286 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.361 | 0 | 3.361 | 0 | 0 | 3.361 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35232960 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.9078 | 0 | 2.9078 | 0 | 0 | 2.9078 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35232442 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.9127 | 0 | 2.9127 | 0 | 0 | 2.9127 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35232443 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0093 | 0 | 1.0093 | 0 | 1.0093 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35232444 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.4282 | 0 | 3.4282 | 0 | 1.2443 | 2.1839 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35232445 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.6036 | 0 | 2.6036 | 0 | 0.45246 | 2.1511 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35225825 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.5214 | 0 | 1.5214 | 0 | 1.5214 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48 | Top 250 Miles | Tier 2
35026643 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0089 | 0 | 1.0089 | 0 | 0 | 0 | 1.0089 | 0 | SI | Region 2 - North East | El Dorado | El Dorado |  |  | DIAMOND SPRINGS 11052102 | 666 | Top 20% MAVF CPZ | Tier 2
35192290 |  | Base SH | 08W | ESTS | Post-Construction | 0 | 5.0519 | 0 | 5.0519 | 0 | 2.8996 | 2.1523 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 11071402 | 811 | ECOP | Tier 3
35224856 |  | Other | 10Q | ESTS | Estimating | 2.803 | 0.10985 | 0 | 2.9129 | 0 | 0 | 1.1364 | 1.7765 | 0 | NV | Region 2 - North East
35226845 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.3184 | 0 | 2.3184 | 0 | 2.3184 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 11071402 | 811 | ECOP | Tier 3
31361965 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.4483 | 0 | 0.4483 | 0 | 0.4483 | 0 | 0 | 0 | SO | Region 1 - North Coast | Glen Ellen | SONOMA |  |  | DUNBAR 110147964 | 1794 | Pre | Tier 3
35234756 |  | Base SH | 08W | ESTS | Estimating | 2.782 | 0 | 0 | 2.782 | 0 | 0 | 0 | 2.782 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35274593 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | 0 | 0 | 2.756 | 0 | 0 | 0 | 2.756 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2
35292755 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.74 | 0 | 0 | 2.74 | 0 | 0 | 2.74 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35222235 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 2.6 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare |  |  | DUNLAP 1102778286 | 2738 | Remote Grid Pilot | Tier 3
35225824 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.6989 | 0 | 0 | 2.6989 | 0 | 2.2879 | 0.41098 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | WYANDOTTE 11031508 | 1176 | FRRB - UG - 2021 | Tier 2
35219276 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.69 | 0 | 0 | 2.69 | 0 | 0 | 2.69 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35231620 |  | Base SH | 08W | ADER | Estimating | 2.6782 | 0 | 0 | 2.6782 | 0 | 0 | 0 | 2.6782 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35280560 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.64 | 0 | 0 | 2.64 | 0 | 0 | 2.64 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1102CB | 378 | FRRB - UG - 2021 | Tier 2 & 3
35285249 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.593 | 0 | 0 | 2.593 | 0 | 0 | 0 | 2.593 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35282166 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.5902 | 0 | 0 | 2.5902 | 0 | 0 | 2.5902 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS |  |  | SPANISH CREEK 4401CB | 1322 | FRRB | Tier 2
35112435 |  | Base SH | 08W | CLSD | Closed | 0 | 1.3269 | 0 | 1.3269 | 1.1178 | 0.20909 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO |  |  | EL DORADO PH 210219562 | 3014 | Pre | Tier 3
35226625 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 8.9 | 0 | NV | Region 2 - North East | Elk Creek | GLENN |  |  | ELK CREEK 11012106 | 340 | FRRB - REMG - 2021 | Tier 2
74022384 |  | Base SH | 08W | FICL | Post-Construction | 0 | 5.1314 | 0 | 5.1314 | 0.96004 | 4.1714 | 0 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA |  |  | FITCH MOUNTAIN 111324918 | 481 | Pre | Tier 3
35226626 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0 | 4.15 | 4.15 | 0 | 4.15 | 0 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA |  |  | FITCH MOUNTAIN 11136751 | 945 | FRRB - REMG - 2021 | Tier 2
31334291 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0.51326 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino |  |  | FORT BRAGG A 11013113 | 2140 | Pre | Tier 3
35075103 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.63674 | 0 | 0.63674 | 0 | 0.63674 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | FROGTOWN 17011623 | 721 | Top 20% MAVF CPZ | Tier 3
35174085 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.095265 | 0 | 0.095265 | 0 | 0.095265 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | CALAVERAS |  |  | FROGTOWN 170236870 | 2139 | PSPS - Scoped | Tier 3
35233948 |  | Base SH | 08W | ESTS | Estimating | 2.5871 | 0 | 0 | 2.5871 | 0 | 0 | 2.5871 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35225595 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.83807 | 0 | 0.83807 | 0 | 0.11629 | 0.72178 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | FULTON 1107604 | 637 | ECOP - Top 20% | Tier 3
35225597 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.79356 | 0 | 0.79356 | 0 | 0 | 0.79356 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | FULTON 1107604 | 637 | ECOP - Top 20% | Tier 3
35225598 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.9053 | 0 | 0.9053 | 0 | 0 | 0.9053 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | FULTON 1107604 | 637 | ECOP - Top 20% | Tier 3
35246501 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 7.0994 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma |  |  | FULTON 1107604 | 637 | REMG 2022-2023 | Tier 3
35225828 |  | Base SH | 08W | ESTS | Estimating | 2.5314 | 0 | 0 | 2.5314 | 0 | 0 | 2.5314 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35250574 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 8.0701 | 0 | 8.0701 | 0 | 0 | 0 | 8.0701 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 11011306 | 593 | CWSP 2022-2023 | Tier 2
35250576 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.22992 | 0 | 0.22992 | 0 | 0 | 0 | 0.22992 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35283196 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0.66799 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35283197 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4381 | 0 | 2.4381 | 0 | 0 | 0 | 2.4381 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35283938 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | 0 | 0 | 2.4799 | 0 | 0 | 0 | 2.4799 | 0 | PN | Region 3 - Bay Area | Redwood City | SAN MATEO |  |  | WOODSIDE 11018974 | 1145 | CWSP 2022-2023 | Tier 3
35283199 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2701 | 0 | 1.2701 | 0 | 0 | 0 | 1.2701 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35283340 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35299133 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35299134 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35299135 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35299136 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35299137 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35299138 |  | Base SH | 08W | CLSD | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35250575 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.2299 | 0 | 3.2299 | 0 | 0 | 0 | 3.2299 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101980662 | 19 | CWSP 2022-2023 | Tier 2
35254072 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102623120 | 74 | CWSP 2022-2023 | Tier 2
35290511 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 1.2799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102623120 | 74 | CWSP 2022-2023 | Tier 2
35290512 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 2.06 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102623120 | 74 | CWSP 2022-2023 | Tier 2
35290513 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0201 | 0 | 2.0201 | 0 | 0 | 0 | 2.0201 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102623120 | 74 | CWSP 2022-2023 | Tier 2
35290514 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.060038 | 0 | 0.060038 | 0 | 0 | 0 | 0.060038 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102623120 | 74 | CWSP 2022-2023 | Tier 2
35219099 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7269 | 0 | 2.7269 | 0 | 0 | 2.7269 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35057018 |  | Base SH | 08W | CONS | In-Construction | 2.4557 | 0.19508 | 0 | 2.6508 | 0 | 0 | 2.6508 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210119752 | 1946 | PSS Approved | Tier 3
35233314 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.3701 | 0 | 0 | 2.3701 | 0 | 2.0169 | 0.35322 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35231622 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0.88996 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231623 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 1.3799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231624 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 4.2701 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231625 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231626 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0.68314 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231627 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.39867 | 0 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231628 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 1.8799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231629 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 2.7701 | 2.7701 | 0 | 0 | 0 | 2.7701 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231630 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.36326 | 0 | 0.36326 | 0 | 0 | 0.36326 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35231631 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0.46686 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35226627 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.31761 | 0 | 0.31761 | 0 | 0.31761 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35239098 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35236995 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - REMG - 2021 | Tier 3
35226630 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4 | 0.033523 | 1.4335 | 0 | 0 | 1.4335 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35226631 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.5402 | 0 | 1.5402 | 0 | 1.5402 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35279307 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.25 | 0 | 0 | 2.25 | 0 | 0 | 2.25 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas |  |  | GANSNER 11012424 | 1172 | FRRB | Tier 2 & 3
35223024 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.24 | 0 | 0 | 2.24 | 0 | 0 | 2.24 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35227655 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 3.2598 | 3.2598 | 0 | 0 | 0 | 3.2598 | 0 | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA |  |  | KIRKER 2104442850 | 21 | Top 250 Miles | Tier 2
35094397 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0646 | 0 | 1.0646 | 0 | 1.0646 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake |  |  | KONOCTI 1102532 | 1999 | Pre | Tier 3
35217270 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.55 | 0 | 0.55 | 0 | 0 | 0 | 0.55 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | KONOCTI 1102965078 | 9 | Top 50 Miles | Tier 3
35225589 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0.88996 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | KONOCTI 1102965078 | 9 | Top 50 Miles | Tier 3
35225591 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | KONOCTI 1102965078 | 9 | Top 50 Miles | Tier 3
35217274 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo |  |  | HALF MOON BAY 110369412 | 2055 | FRRB - UG - 2021 | Tier 2
35274589 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | 0 | 0 | 2.132 | 0 | 0 | 0 | 2.132 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2 & 3
35119965 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara |  |  | LOS GATOS 1106LB44 | 1864 | Pre | Tier 3
35113108 |  | Base SH | 08W | CLSD | Closed | 0 | 0.72102 | 0 | 0.72102 | 0 | 0.72102 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CRUZ |  |  | LOS GATOS 1106LB44 | 1864 | Pre | Tier 3
35250572 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.953 | 0 | 1.953 | 0 | 0 | 0 | 1.953 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101309438 | 605 | CWSP 2022-2023 | Tier 2
35274595 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0.057 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101309438 | 605 | CWSP 2022-2023 | Tier 2
35274596 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.214 | 0.172 | 1.386 | 0 | 0 | 0 | 1.386 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101309438 | 605 | CWSP 2022-2023 | Tier 2
35219281 |  | Base SH | 08W | CONS | In-Construction | 2.1025 | 0 | 0 | 2.1025 | 0 | 0 | 2.1025 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21016953 | 45 | Top 250 Miles | Tier 2
35274591 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.022 | 0 | 1.022 | 0 | 0 | 0 | 1.022 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2 & 3
35274592 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.963 | 0 | 1.963 | 0 | 0 | 0 | 1.963 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2
35237889 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35274594 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.078 | 0 | 3.078 | 0 | 0 | 0 | 3.078 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2
35250570 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4009 | 0 | 2.4009 | 0 | 0 | 0 | 2.4009 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2 & 3
35250571 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 4.595 | 0 | 4.595 | 0 | 0 | 0 | 4.595 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | CWSP 2022-2023 | Tier 2
35238088 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210135244 | 428 | Remote Grid Pilot | Tier 3
35161152 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.081439 | 0 | 0.081439 | 0 | 0.081439 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  |  |  | MARIPOSA 2101752630 | 700 | Remote Grid | Tier 2 & 3
35219268 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.972 | 0 | 1.972 | 0 | 1.972 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210197142 | 36 | Top 250 Miles | Tier 2
35238567 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0.10436 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210197142 | 36 | Top 250 Miles | Tier 2
35226240 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.2004 | 0 | 1.2004 | 0 | 1.2004 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210197142 | 36 | Top 250 Miles | Tier 2
35226241 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.2593 | 0 | 1.2593 | 0 | 1.2593 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210197142 | 36 | Top 250 Miles | Tier 2
35250573 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.759 | 0 | 1.759 | 0 | 0 | 0 | 1.759 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101CB | 57 | CWSP 2022-2023 | Tier 2
35274597 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.63295 | 0 | 0.63295 | 0 | 0 | 0 | 0.63295 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101CB | 57 | CWSP 2022-2023 | Tier 2
35217267 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.93977 | 0 | 0.93977 | 0 | 0.93977 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102241564 | 10 | Top 50 Miles | Tier 2 & 3
35219267 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6701 | 0 | 1.6701 | 0 | 0 | 1.6701 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102440236 | 50 | Top 250 Miles | Tier 2 & 3
35219587 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.0299 | 0 | 2.0299 | 0 | 0 | 2.0299 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102440236 | 50 | Top 250 Miles | Tier 2 & 3
35219588 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102440236 | 50 | Top 250 Miles | Tier 2 & 3
35192284 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35219266 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.9312 | 0 | 2.9312 | 0 | 0 | 2.9312 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102CB | 35 | Top 250 Miles | Tier 2
35227263 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 2.5125 | 0 | 2.5125 | 0 | 2.5125 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102CB | 35 | Top 250 Miles | Tier 2
35279182 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1102CB | 378 | FRRB - UG - 2021 | Tier 2 & 3
35234284 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.24053 | 0 | 0.24053 | 0 | 0 | 0.24053 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR |  |  | MARTELL 1101CB | 999 | PSPS - Community Resiliency | Tier 2
35236985 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 2.0655 | 0 | 0 | 2.0655 | 0 | 0 | 2.0655 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - REMG - 2021 | Tier 3
35219098 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.70265 | 0 | 0.70265 | 0 | 0 | 0.70265 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101118494 | 23 | Top 250 Miles | Tier 2 & 3
35062374 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.0513 | 0 | 0 | 2.0513 | 0 | 0 | 2.0513 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35137593 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.3786 | 0 | 1.3786 | 0 | 0 | 1.3786 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | MIDDLETOWN 11014646 | 328 | ECOP - Top 20% | Tier 3
35137596 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0116 | 0 | 1.0116 | 0 | 0 | 1.0116 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | MIDDLETOWN 11014646 | 328 | ECOP - Top 20% | Tier 3
35219272 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.92 | 0 | 0.92 | 0 | 0 | 0.92 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101481876 | 38 | Top 250 Miles | Tier 2 & 3
35227027 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35227028 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35227029 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 1.04 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35192282 |  | Base SH | 08W | ESTS | Estimating | 2.04 | 0 | 0 | 2.04 | 0 | 0 | 0 | 2.04 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35236984 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031508 | 1176 | FRRB - REMG - 2021 | Tier 3
35235702 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.9597 | 0 | 0 | 1.9597 | 0 | 0 | 1.9597 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35226622 |  | Base SH | 08W | ADER | Estimating | 0 | 0.76004 | 0 | 0.76004 | 0 | 0 | 0.76004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35226623 |  | Base SH | 08W | APPR | Estimating | 0 | 1.15 | 0 | 1.15 | 0 | 0 | 1.15 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35226624 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.74678 | 0 | 0.74678 | 0 | 0 | 0.74678 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35236437 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.37841 | 0 | 0.37841 | 0 | 0 | 0.37841 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35236438 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.5197 | 0 | 0.5197 | 0 | 0 | 0.5197 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35192281 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.27008 | 0 | 0.27008 | 0 | 0 | 0.27008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35220895 |  | Base SH | 08W | ESTS | Estimating | 1.9299 | 0 | 0 | 1.9299 | 0 | 0 | 0 | 1.9299 | 0 | HB | Region 1 - North Coast | Middletown | Lake |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35174501 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8598 | 0 | 0 | 1.8598 | 0 | 0 | 1.8598 | 0 | 0 | HB | Region 1 - North Coast | Glen Ellen | SONOMA |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35174479 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 3.96 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35145001 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8409 | 0.071023 | 0 | 1.9119 | 0 | 0 | 1.9119 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa |  |  | CLAYTON 2215184604 | 1739 | PSPS - Community Resiliency | Tier 2 & 3
35224713 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.8299 | 0 | 0 | 1.8299 | 0 | 0 | 1.8299 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1101CB | 11 | Top 50 Miles | Tier 2 & 3
35227167 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35223026 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35192292 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.7848 | 0.19489 | 0 | 1.9797 | 0 | 0 | 1.9797 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | FULTON 1107604 | 637 | ECOP - Top 20% | Tier 3
35226849 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.7799 | 0 | 0 | 1.7799 | 0 | 0 | 1.7799 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35224712 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.7299 | 0 | 0 | 1.7299 | 0 | 0 | 1.7299 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1101CB | 11 | Top 50 Miles | Tier 2 & 3
35235705 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.7104 | 0 | 0 | 1.7104 | 0 | 1.7104 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35226858 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37992 | 0 | 0.37992 | 0 | 0 | 0 | 0.37992 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226859 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.87992 | 0 | 0.87992 | 0 | 0 | 0 | 0.87992 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226861 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0.66004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226862 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.57992 | 0 | 0.57992 | 0 | 0 | 0.57992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226863 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.52765 | 0 | 0.52765 | 0 | 0 | 0.52765 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226864 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.32652 | 0 | 0.32652 | 0 | 0 | 0.32652 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226865 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.23542 | 0 | 0.23542 | 0 | 0 | 0.23542 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226866 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.51818 | 0 | 0.51818 | 0 | 0 | 0.51818 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226870 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.41951 | 0 | 0.41951 | 0 | 0 | 0.41951 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226871 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.39659 | 0 | 0.39659 | 0 | 0.39659 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226872 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.22121 | 0 | 0.22121 | 0 | 0 | 0.22121 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35219096 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.6701 | 0 | 0 | 1.6701 | 0 | 0 | 0 | 1.6701 | 0 | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA |  |  | KIRKER 2104442850 | 21 | Top 250 Miles | Tier 2
35227656 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.66 | 0 | 0 | 1.66 | 0 | 0 | 1.66 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35239095 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35223615 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5928 | 0 | 0 | 1.5928 | 0 | 0 | 1.5928 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | MARIN |  |  | LAS GALLINAS A 110599904 | 215 | ECOP - Top 20% | Tier 3
35227168 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35062375 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5646 | 0 | 0 | 1.5646 | 0 | 0 | 1.5646 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35227031 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 1.55 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35227010 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.15795 | 0 | 0.15795 | 0 | 0 | 0 | 0.15795 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35227013 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.031818 | 0 | 0.031818 | 0 | 0 | 0 | 0.031818 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35227015 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.96705 | 0 | 0.96705 | 0 | 0 | 0 | 0.96705 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35227018 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.1955 | 0 | 1.1955 | 0 | 0 | 0 | 1.1955 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35227021 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.34186 | 0 | 0.34186 | 0 | 0 | 0.34186 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226621 |  | Base SH | 08W | ESTS | Estimating | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 0 | 1.55 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35137590 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.39299 | 0 | 0.39299 | 0 | 0 | 0.39299 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake |  |  | MIDDLETOWN 1101CB | 86 | ECOP - Top 20% | Tier 3
35217271 |  | Base SH | 08W | ADER | Estimating | 1.54 | 0 | 0 | 1.54 | 0 | 0 | 0 | 1.54 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227161 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.73996 | 0 | 0.73996 | 0 | 0 | 0 | 0.73996 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35145524 |  | Base SH | 08W | CONS | In-Construction | 1.5216 | 0 | 0 | 1.5216 | 0 | 1.5216 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma |  |  | RINCON 1103CB | 1755 | PSPS - Scoped | Tier 3
35227163 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0.46004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35227164 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35226819 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.99 | 0 | 1.99 | 0 | 0 | 1.99 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35217269 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0.42992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35235139 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.5108 | 0 | 0 | 1.5108 | 0 | 1.2008 | 0.31004 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35228186 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227870 |  | Base SH | 08W | UNSC | Ready for Construction | 1.4848 | 0 | 0 | 1.4848 | 0 | 0 | 1.4848 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35222045 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0.88996 | 0 | 0 | HB | Region 1 - North Coast | Pope Valley | Napa |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35237896 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.4295 | 0 | 0 | 1.4295 | 0 | 0 | 1.4295 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35228187 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.57614 | 0 | 0.57614 | 0 | 0.57614 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35228188 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.45 | 0 | 3.45 | 0 | 0 | 0 | 3.45 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227860 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.19602 | 0 | 0.19602 | 0 | 0.19602 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227861 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5201 | 0 | 1.5201 | 0 | 0 | 1.5201 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227862 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227863 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35235700 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.4083 | 0 | 0 | 1.4083 | 0 | 0 | 1.4083 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35227866 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.53314 | 0 | 0.53314 | 0 | 0.53314 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227867 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.98239 | 0 | 0.98239 | 0 | 0.052652 | 0.92973 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35227868 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35281758 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | NV | Region 2 - North East | Twain | PLUMAS |  |  | GRAYS FLAT 0401CB | 1748 | FRRB | Tier 2
35227030 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3801 | 0 | 0 | 1.3801 | 0 | 0 | 1.3801 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 110148212 | 468 | ECOP - Top 20% | Tier 3
35231621 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3655 | 0 | 0 | 1.3655 | 0 | 0 | 1.3655 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1102628 | 27 | Top 250 Miles | Tier 2 & 3
35236661 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.22008 | 0 | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35116383 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3919 | 0 | 1.3919 | 0 | 1.0422 | 0.34962 | 0 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | MIWUK 1701953336 | 2267 | Pre | Tier 3
35116384 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7617 | 0 | 1.7617 | 0 | 1.7617 | 0 | 0 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | MIWUK 1701953336 | 2267 | Pre | Tier 3
35116385 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5161 | 0 | 1.5161 | 0 | 0 | 1.5161 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1701953336 | 2267 | Pre | Tier 3
35052737 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.6297 | 0 | 1.6297 | 0 | 0 | 1.6297 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne |  |  | MIWUK 1701953336 | 2267 | Pre | Tier 3
35052821 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.0911 | 0 | 2.0911 | 0 | 2.0911 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1701CB | 2353 | Pre | Tier 3
35056746 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.0278 | 0 | 2.0278 | 0 | 1.6869 | 0.34091 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE |  |  | MIWUK 1701CB | 2353 | Pre | Tier 3
35115050 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.6241 | 0 | 1.6241 | 0 | 1.6241 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1701CB | 2353 | Pre | Tier 3
35115053 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7411 | 0 | 1.7411 | 0 | 1.7411 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE |  |  | MIWUK 1701CB | 2353 | Pre | Tier 3
35115054 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3953 | 0 | 1.3953 | 0 | 1.3953 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE |  |  | MIWUK 1701CB | 2353 | Pre | Tier 3
35115055 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.1343 | 0 | 2.1343 | 0 | 2.1343 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE |  |  | MIWUK 1701CB | 2353 | Pre | Tier 2
35116442 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.3314 | 0 | 2.3314 | 1.7888 | 0.54261 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 170238218 | 2678 | Pre | Tier 3
35116444 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.065 | 0 | 2.065 | 0 | 0.38883 | 1.6761 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 170238218 | 2678 | Pre | Tier 3
35116800 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3864 | 0 | 1.3864 | 0.73996 | 0.6464 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702823548 | 2411 | Pre | Tier 3
35225823 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.3602 | 0 | 0 | 1.3602 | 0 | 1.3602 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35116802 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2237 | 0 | 2.2237 | 2.2167 | 0.0070076 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702823548 | 2411 | Pre | Tier 3
35116391 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.0902 | 0 | 2.0902 | 1.3841 | 0.70606 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702CB | 2369 | Pre | Tier 3
35116395 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.703 | 0 | 1.703 | 0 | 1.703 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702CB | 2369 | Pre | Tier 3
35052825 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0917 | 0 | 1.0917 | 0 | 1.0917 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702S2247 | 2737 | Pre | Tier 3
35232650 |  | Base SH | 08W | UNSC | Ready for Construction | 1.3447 | 0 | 0 | 1.3447 | 0 | 0 | 1.3447 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21016953 | 45 | Top 250 Miles | Tier 2
35254070 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35254071 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.65 | 0 | 2.65 | 0 | 0 | 0 | 2.65 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305303 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305304 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305305 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305306 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305307 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305308 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305309 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305310 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305311 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35305312 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35234526 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3426 | 0 | 0 | 1.3426 | 0 | 0 | 1.3426 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR |  |  | MARTELL 1101CB | 999 | PSPS - Community Resiliency | Tier 2
35192280 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.34 | 0 | 0 | 1.34 | 0 | 0 | 1.34 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa |  |  | CLAYTON 221296224 | 377 | ECOP - Top 20% | Tier 3
35293664 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35227160 |  | Base SH | 08W | ESTS | Estimating | 1.3201 | 0 | 0 | 1.3201 | 0 | 0 | 0 | 1.3201 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35293666 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.22992 | 0 | 0.22992 | 0 | 0 | 0 | 0.22992 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35293667 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.65 | 0 | 1.65 | 0 | 0 | 0 | 1.65 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35293668 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 1.44 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35293669 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.6299 | 0 | 1.6299 | 0 | 0 | 0 | 1.6299 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35293670 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35231543 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA |  |  | TIDEWATER 210614072 | 18 | Top 50 Miles | Tier 2
35145525 |  | Base SH | 08W | CONS | In-Construction | 1.283 | 0.2 | 0 | 1.483 | 0 | 1.1737 | 0.30928 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma |  |  | RINCON 1104CB | 3302 | PSPS - Scoped | Tier 2
35232651 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7445 | 0 | 1.7445 | 0 | 1.7445 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21016953 | 45 | Top 250 Miles | Tier 2
35191319 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.2816 | 0 | 0 | 1.2816 | 0 | 0 | 1.2816 | 0 | 0 | NB | Region 1 - North Coast | Nicasio | MARIN |  |  | LAS GALLINAS A 110599904 | 215 | ECOP - Top 20% | Tier 3
35293672 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 1.09 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293673 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 1.8799 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293674 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.61 | 0 | 1.61 | 0 | 0 | 0 | 1.61 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293675 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 2.11 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293676 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293677 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.72008 | 0 | 0.72008 | 0 | 0 | 0 | 0.72008 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293847 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0.33996 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293505 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.3799 | 0 | 1.3799 | 0 | 0 | 0 | 1.3799 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293506 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35293507 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35242421 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2674 | 0 | 0 | 1.2674 | 0 | 1.2674 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35293509 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 2.04 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35236991 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2616 | 0 | 0 | 1.2616 | 0 | 0 | 1.2616 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35300934 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35235678 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2422 | 0 | 0 | 1.2422 | 0 | 1.2422 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35301113 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35301114 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 1.01 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35237890 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35254068 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 1.81 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35254069 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 1.3701 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35241060 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | YO | Region 5 - Central Valley | Ahwahnee | MADERA |  |  | OAKHURST 110110090 | 421 | Remote Grid Pilot | Tier 3
35223037 |  | Base SH | 08W | CONS | In-Construction | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0 | 0.0079545 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | MADERA |  |  | OAKHURST 1101CB | 847 | PSPS - Community Resiliency | Tier 3
35227096 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1049 | 0 | 1.1049 | 0 | 1.1049 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | MARIPOSA |  |  | OAKHURST 11035120 | 1975 | Storm Rebuild | Tier 3
35227201 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.83523 | 0 | 0.83523 | 0 | 0.83523 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | MARIPOSA |  |  | OAKHURST 11035120 | 1975 | Storm Rebuild | Tier 3
35192053 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.143 | 0 | 2.143 | 0 | 2.143 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | Mariposa |  |  | OAKHURST 11035120 | 1975 | Storm Rebuild | Tier 3
35243446 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0.37 | 0 | NB | Region 1 - North Coast | Inverness | MARIN |  |  | OLEMA 110150396 | 2644 | REMG 2022-2023 | Tier 2
35243445 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 1.92 | 0 | NB | Region 1 - North Coast | Inverness | MARIN |  |  | OLEMA 1101602 | 2360 | REMG 2022-2023 | Tier 2
35219591 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.332 | 0.0077652 | 1.3398 | 0 | 0 | 0 | 1.3398 | 0 | ST | Region 5 - Central Valley | Plymouth | AMADOR |  |  | OLETA 1101754718 | 54 | Top 250 Miles | Tier 2
35236662 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6246 | 0 | 1.6246 | 0 | 1.6246 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | AMADOR |  |  | OLETA 1101754718 | 54 | Top 250 Miles | Tier 2
35233947 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.8436 | 0 | 1.8436 | 0 | 0 | 1.8436 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35254643 |  | Base SH | 08W | ESTS | Estimating | 1.21 | 0 | 1.0979 | 2.308 | 0 | 0 | 0 | 2.308 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35233949 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.9769 | 0 | 1.9769 | 0 | 0 | 1.9769 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35293665 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.2087 | 0 | 0 | 1.2087 | 0 | 0 | 0 | 1.2087 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35233951 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5648 | 0 | 1.5648 | 0 | 0 | 1.5648 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35233952 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.1616 | 0 | 2.1616 | 0 | 0 | 2.1616 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234383 |  | Base SH | 08W | ESTS | Estimating | 1.1985 | 0 | 0 | 1.1985 | 0 | 0 | 1.1985 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35233954 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.19451 | 0 | 0.19451 | 0 | 0 | 0.19451 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35237894 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.185 | 0 | 0 | 1.185 | 0 | 0 | 1.185 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35233956 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.26098 | 0 | 0.26098 | 0 | 0 | 0.26098 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35295186 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.1701 | 0 | 0 | 1.1701 | 0 | 0 | 1.1701 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35233958 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.18845 | 0 | 0.18845 | 0 | 0 | 0.18845 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35233959 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.34602 | 0 | 0.34602 | 0 | 0 | 0.34602 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234380 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.2419 | 0 | 2.2419 | 0 | 0 | 2.2419 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234381 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5468 | 0 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234382 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5875 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35284023 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | DUNBAR 1101416 | 1684 | FRRB - UG - 2021 | Tier 3
35234384 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0.050568 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234385 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.67443 | 0 | 0.67443 | 0 | 0 | 0.67443 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234386 |  | Base SH | 08W | ADER | Estimating | 0 | 0.85777 | 0 | 0.85777 | 0 | 0 | 0.85777 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234387 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.93996 | 0 | 0.93996 | 0 | 0 | 0.93996 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234388 |  | Base SH | 08W | ADER | Estimating | 0 | 2.0402 | 0 | 2.0402 | 0 | 0 | 2.0402 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234389 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234390 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234391 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 1.26 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234392 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.66 | 0 | 1.66 | 0 | 0 | 1.66 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234393 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.4201 | 0 | 2.4201 | 0 | 0 | 2.4201 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234394 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234395 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.71 | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234396 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 1.69 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234397 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.72008 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234398 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8525 | 0 | 2.8525 | 0 | 0 | 2.8525 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35239097 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.1566 | 0 | 0 | 1.1566 | 0 | 0 | 1.1566 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35234400 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35234401 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 1.85 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35225826 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5424 | 0 | 2.5424 | 0 | 0 | 2.5424 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35219093 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.14 | 0 | 0 | 1.14 | 0 | 0 | 1.14 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA |  |  | TIDEWATER 210614072 | 18 | Top 50 Miles | Tier 2
35236439 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35225829 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.19 | 0 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35219287 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.3962 | 0 | 2.3962 | 0 | 0 | 2.3962 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35297984 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 110148950 | 851 | FRRB | Tier 2
35292788 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012476 | 2342 | FRRB | Tier 2
35254254 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.46 | 0 | 1.46 | 0 | 0 | 0 | 1.46 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 11032731 | 260 | CWSP 2022-2023 | Tier 2
35279626 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0.17 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 11032731 | 260 | CWSP 2022-2023 | Tier 2
35279630 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 1.69 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 110359763 | 615 | CWSP 2022-2023 | Tier 2
35254251 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.13 | 0 | 1.13 | 0 | 0 | 1.13 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 110359763 | 615 | CWSP 2022-2023 | Tier 2
35260649 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.62992 | 0 | 0.62992 | 0 | 0 | 0 | 0.62992 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N04 | 510 | CWSP 2022-2023 | Tier 2
35254253 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N50 | 138 | CWSP 2022-2023 | Tier 2
35279627 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 1.47 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N50 | 138 | CWSP 2022-2023 | Tier 2
35279628 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 2.37 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N52 | 291 | CWSP 2022-2023 | Tier 2
35279629 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 1.71 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N52 | 291 | CWSP 2022-2023 | Tier 2
35254252 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.49 | 0.064962 | 2.5549 | 0 | 0 | 2.5549 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N52 | 291 | CWSP 2022-2023 | Tier 2
35254249 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 2.7 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35254250 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.11 | 0 | 1.11 | 0 | 0 | 0 | 1.11 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278880 |  | Base SH | 08W | ADER | Estimating | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 2.09 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278881 |  | Base SH | 08W | ADER | Estimating | 0 | 2.6799 | 0 | 2.6799 | 0 | 0 | 0 | 2.6799 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278882 |  | Base SH | 08W | ADER | Estimating | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 2.01 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278883 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278884 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 2.77 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278885 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 1.47 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278886 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278887 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 1.48 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35278888 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 1.39 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N54 | 69 | CWSP 2022-2023 | Tier 2
35254248 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.43 | 0 | 1.43 | 0 | 0 | 1.43 | 0 | 0 | LP | Region 4 - Central Coast | El Paso de Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N58 | 257 | CWSP 2022-2023 | Tier 2
35279631 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 3.07 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N58 | 257 | CWSP 2022-2023 | Tier 2
35243442 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 2.319 | SI | Region 2 - North East | North San Juan | SIERRA |  |  | PIKE CITY 1102CB | 1308 | REMG 2022-2023 | Tier 3
35295019 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35114042 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3352 | 0 | 1.3352 | 1.172 | 0.16326 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35114044 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0966 | 0 | 1.0966 | 0.081061 | 1.0155 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35114048 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3909 | 0 | 1.3909 | 0 | 1.3909 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35114049 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.5705 | 0 | 1.5705 | 0.70663 | 0.86383 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35114051 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4371 | 0 | 1.4371 | 0 | 1.4371 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35295009 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer |  |  | SHADY GLEN 11012768 | 1885 | FRRB
35233166 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0491 | 0 | 0 | 1.0491 | 0 | 0 | 1.0491 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35233308 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.047 | 0 | 0 | 1.047 | 0 | 1.047 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35174478 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.04 | 0 | 0 | 1.04 | 0 | 0 | 0 | 1.04 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35226873 |  | Base SH | 08W | ESTS | Estimating | 1.0394 | 0 | 0 | 1.0394 | 0 | 0 | 0 | 1.0394 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35235707 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0284 | 0 | 0 | 1.0284 | 0 | 0 | 1.0284 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - REMG - 2021 | Tier 3
35225821 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0252 | 0 | 0 | 1.0252 | 0 | 1.0252 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35297699 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0199 | 0 | 0 | 1.0199 | 0 | 0 | 1.0199 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35250579 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 6.14 | 0 | 6.14 | 0 | 0 | 0 | 6.14 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110495878 | 60 | CWSP 2022-2023 | Tier 2 & 3
35254073 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 1.01 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35254074 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.35 | 0 | 0.35 | 0 | 0 | 0 | 0.35 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35254075 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 1.8 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35254076 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0.92992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35293770 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.52992 | 0 | 0.52992 | 0 | 0 | 0 | 0.52992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293774 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 1.1799 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293775 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.39015 | 0 | 0.39015 | 0 | 0 | 0 | 0.39015 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293841 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293843 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.31 | 0 | 1.31 | 0 | 0 | 0 | 1.31 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293844 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0.92992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35293845 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 1.4201 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35227165 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.01 | 0 | 0 | 1.01 | 0 | 0 | 1.01 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35290807 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2259 | 0 | 1.2259 | 0 | 0 | 0 | 1.2259 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35279120 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.004 | 0 | 0 | 1.004 | 0 | 0 | 0 | 1.004 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | STANISLAUS 1701CB | 56 | CWSP 2022-2023 | Tier 2 & 3
35290295 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.197 | 0 | 1.197 | 0 | 0 | 0 | 1.197 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290296 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.93807 | 0 | 0.93807 | 0 | 0 | 0 | 0.93807 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290297 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0451 | 0 | 1.0451 | 0 | 0 | 0 | 1.0451 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290298 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 1.2799 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290299 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.4189 | 0 | 1.4189 | 0 | 0 | 0 | 1.4189 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290500 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0229 | 0 | 1.0229 | 0 | 0 | 0 | 1.0229 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290501 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.64 | 0 | 1.64 | 0 | 0 | 0 | 1.64 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290502 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 1.6299 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290503 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35228774 |  | Base SH | 08W | ESTS | Estimating | 1.0008 | 0 | 0 | 1.0008 | 0 | 0 | 0 | 1.0008 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | DUNBAR 1101CB | 2048 | PSPS - Community Resiliency | Tier 2
35290506 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 2.09 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290507 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77992 | 0 | 0.77992 | 0 | 0 | 0 | 0.77992 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35297693 |  | Fire Rebuild | 08W | ESTS | Estimating | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35290509 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 1.09 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35290510 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0.6 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35293663 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.98996 | 0 | 0 | 0.98996 | 0 | 0 | 0 | 0.98996 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35290544 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35285245 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.40398 | 0 | 0.40398 | 0 | 0 | 0 | 0.40398 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110537476 | 396 | CWSP 2022-2023 | Tier 2
35254077 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.6021 | 0 | 1.6021 | 0 | 0 | 0 | 1.6021 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110537476 | 396 | CWSP 2022-2023 | Tier 2
35219280 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5871 | 0 | 1.5871 | 0 | 0 | 1.5871 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110564118 | 43 | Top 250 Miles | Tier 2
35239096 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35191937 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4542 | 0 | 1.4542 | 0 | 1.4542 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA |  |  | PUEBLO 2102792 | 951 | ECOP | Tier 3
35227032 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.87121 | 0 | 0.87121 | 0 | 0.56269 | 0.30852 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA |  |  | PUEBLO 2102792 | 951 | ECOP | Tier 3
35227033 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3299 | 2.3299 | 0 | 0 | 0 | 0 | 2.3299 | NB | Region 1 - North Coast | Napa | NAPA |  |  | PUEBLO 2102792 | 951 | ECOP | Tier 3
35219275 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0231 | 0 | 1.0231 | 0 | 0 | 1.0231 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110246012 | 41 | Top 250 Miles | Tier 2
35240176 |  | Base SH | 08W | ADER | Estimating | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110264044 | 529 | CWSP 2022-2023 | Tier 2
35240177 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 3.3 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110264044 | 529 | CWSP 2022-2023 | Tier 2
35254177 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.31 | 0 | 0.31 | 0 | 0 | 0.31 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110264044 | 529 | CWSP 2022-2023 | Tier 2
35254178 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.253 | 0 | 1.253 | 0 | 0 | 1.253 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35240175 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.446 | 0 | 3.446 | 0 | 0 | 3.446 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35254560 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 1.211 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35223343 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.95473 | 0.0094697 | 0 | 0.9642 | 0 | 0.9642 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35254261 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.802 | 0 | 2.802 | 0 | 0 | 2.802 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35254262 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.104 | 0 | 2.104 | 0 | 0 | 2.104 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35254263 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.225 | 0 | 1.225 | 0 | 0 | 1.225 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 1102710384 | 418 | CWSP 2022-2023 | Tier 2
35240178 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.4229 | 0 | 3.4229 | 0 | 0 | 3.4229 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 1102710384 | 418 | CWSP 2022-2023 | Tier 2
35254264 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.33 | 0 | 1.33 | 0 | 0 | 1.33 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 11028352 | 171 | CWSP 2022-2023 | Tier 2
35254265 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 2.76 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 11028352 | 171 | CWSP 2022-2023 | Tier 2
35254266 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.13 | 0 | 0.13 | 0 | 0 | 0.13 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 11028352 | 171 | CWSP 2022-2023 | Tier 2
35240173 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.2201 | 0 | 1.2201 | 0 | 0 | 1.2201 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 11028352 | 171 | CWSP 2022-2023 | Tier 2
35240174 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.07 | 0 | 1.07 | 0 | 0 | 1.07 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO |  |  | PUTAH CREEK 11028352 | 171 | CWSP 2022-2023 | Tier 2
35297694 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35295195 |  | Fire Rebuild | 08W | ADER | Estimating | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35228449 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.829 | 0 | 2.829 | 0 | 2.829 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT |  |  | Rio Dell 11024230 | 585 | Storm Rebuild | Tier 2
35015704 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0038 | 0 | 1.0038 | 0 | 0 | 0 | 1.0038 | 0 | CC | Region 4 - Central Coast | Aptos | SANTA CRUZ |  |  | ROB ROY 210512474 | 3283 | Pre | Tier 3
35085847 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.84659 | 0 | 0.84659 | 0 | 0 | 0 | 0.84659 | 0 | CC | Region 4 - Central Coast | Aptos | SANTA CRUZ |  |  | ROB ROY 210512474 | 3283 | Pre | Tier 3
35228775 |  | Base SH | 08W | ESTS | Estimating | 0.90341 | 0 | 0 | 0.90341 | 0 | 0 | 0 | 0.90341 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | DUNBAR 1101CB | 2048 | PSPS - Community Resiliency | Tier 2
35115855 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.2456 | 0 | 1.2456 | 1.0847 | 0.16098 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | SALT SPRINGS 21023142 | 2659 | Pre | Tier 3
35264191 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 2.35 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35264192 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35264193 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.08 | 0 | 2.08 | 0 | 0 | 2.08 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35264194 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35271002 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.22 | 0 | 1.22 | 0 | 0 | 1.22 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35240224 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.8701 | 0 | 1.8701 | 0 | 0 | 1.8701 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 110477098 | 308 | CWSP 2022-2023 | Tier 2
35240179 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.25 | 0 | 0.25 | 0 | 0 | 0.25 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | SANTA YNEZ 1104CB | 137 | CWSP 2022-2023 | Tier 2
35240220 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.786 | 0 | 2.786 | 0 | 0 | 2.786 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35240221 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.93 | 0 | 2.93 | 0 | 0 | 2.93 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35264181 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5568 | 0 | 2.5568 | 0 | 0 | 2.5568 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35264182 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.3167 | 0 | 2.3167 | 0 | 0 | 2.3167 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35264183 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.44 | 0 | 2.44 | 0 | 0 | 2.44 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35264184 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y04 | 108 | CWSP 2022-2023 | Tier 2
35264185 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.52 | 0.18 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264186 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.43 | 0.43 | 0 | 0 | 0 | 0 | 0.43 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264187 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.07 | 0 | 2.07 | 0 | 0 | 0 | 2.07 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264188 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 1.14 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264189 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 2.66 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264190 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 2.37 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35240222 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 2.11 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35240223 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 2.61 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153 | CWSP 2022-2023 | Tier 2 & 3
35242423 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.88958 | 0 | 0 | 0.88958 | 0 | 0 | 0.88958 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35226852 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3718 | 0 | 2.3718 | 0 | 0 | 0 | 2.3718 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 210935598 | 159 | Top 20% MAVF CPZ | Tier 3
35226853 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.9174 | 0 | 1.9174 | 0 | 0 | 1.9174 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 210935598 | 159 | Top 20% MAVF CPZ | Tier 3
35226854 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.0076 | 0.36364 | 2.3712 | 0 | 0 | 2.3712 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 210935598 | 159 | Top 20% MAVF CPZ | Tier 3
35226856 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.0938 | 0 | 1.0938 | 0 | 0 | 1.0938 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 210935598 | 159 | Top 20% MAVF CPZ | Tier 3
35226846 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4795 | 0 | 1.4795 | 0 | 0 | 1.4795 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35226847 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.2939 | 0.22462 | 1.5186 | 0 | 0 | 1.5186 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35226848 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.8341 | 0 | 2.8341 | 0 | 0 | 2.8341 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35242427 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.87784 | 0 | 0 | 0.87784 | 0 | 0 | 0.87784 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35226850 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4674 | 0 | 1.4674 | 0 | 0.18542 | 1.282 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35226851 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.1157 | 0 | 2.1157 | 0 | 0 | 2.1157 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35231607 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4093 | 0 | 1.4093 | 0 | 0 | 1.4093 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35231608 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0.37121 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35231609 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.7477 | 0.15758 | 1.9053 | 0 | 0 | 1.9053 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35232280 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.61269 | 0 | 0.61269 | 0 | 0.61269 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227 | Top 20% MAVF CPZ | Tier 3
35270706 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.87102 | 0.10417 | 0 | 0.97519 | 0 | 0.97519 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011612 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35290517 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.86989 | 0 | 0 | 0.86989 | 0 | 0 | 0.86989 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS |  |  | SPANISH CREEK 4401CB | 1322 | FRRB | Tier 2
35191383 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.3337 | 0 | 1.3337 | 0 | 1.3337 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA |  |  | SILVERADO 210258626 | 663 | ECOP - Top 20% | Tier 3
35191318 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.2201 | 0 | 2.2201 | 0 | 0 | 2.2201 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA |  |  | SILVERADO 210258626 | 663 | ECOP - Top 20% | Tier 3
35220936 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo |  |  | HALF MOON BAY 11036012 | 2186 | FRRB - UG - 2021 | Tier 2
35293846 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.85985 | 0 | 0 | 0.85985 | 0 | 0 | 0 | 0.85985 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2 & 3
35284810 |  | Fire Rebuild | 08W | ADER | Estimating | 0.85814 | 0 | 0 | 0.85814 | 0 | 0 | 0 | 0.85814 | 0 | PN | Region 3 - Bay Area | Pescadero | SAN MATEO |  |  | HALF MOON BAY 11036012 | 2186 | FRRB
35223027 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6559 | 0 | 1.6559 | 0 | 0.35909 | 1.2968 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35223028 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1784 | 0 | 1.1784 | 0 | 1.1784 | 0 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35238098 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.47936 | 0 | 0.47936 | 0 | 0 | 0 | 0.47936 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA |  |  | SILVERADO 2104726 | 279 | ECOP - Top 20% | Tier 3
35226628 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.85511 | 0 | 0 | 0.85511 | 0 | 0 | 0.85511 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35242422 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.85398 | 0 | 0 | 0.85398 | 0 | 0 | 0.85398 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35283343 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0 | 0.85303 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35279121 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77235 | 0 | 0.77235 | 0 | 0 | 0 | 0.77235 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | STANISLAUS 1701CB | 56 | CWSP 2022-2023 | Tier 2 & 3
35279122 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.90909 | 0 | 0.90909 | 0 | 0 | 0 | 0.90909 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | STANISLAUS 1701CB | 56 | CWSP 2022-2023 | Tier 2 & 3
35250578 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4174 | 0 | 2.4174 | 0 | 0 | 0 | 2.4174 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | STANISLAUS 1701CB | 56 | CWSP 2022-2023 | Tier 2 & 3
35236990 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - REMG - 2021 | Tier 3
35250577 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.3513 | 0 | 3.3513 | 0 | 0 | 0 | 3.3513 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | STANISLAUS 1702CB | 235 | CWSP 2022-2023 | Tier 2 & 3
35226857 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35254259 |  | Base SH | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35284366 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0.60871 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE |  |  | STANISLAUS 1702CB | 235 | CWSP 2022-2023 | Tier 2 & 3
35280499 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1102CB | 378 | FRRB - UG - 2021 | Tier 2 & 3
35233996 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.84962 | 0 | 0.52121 | 1.3708 | 0 | 0 | 1.3708 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  | PLACERVILLE 21067522 | 1363 | PSPS - Community Resiliency | Tier 3
35231544 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1009 | 0 | 1.1009 | 0 | 1.1009 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA |  |  | TIDEWATER 210614072 | 18 | Top 50 Miles | Tier 2
35243443 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 11.215 | FR | Region 5 - Central Valley | Sanger | FRESNO |  |  | TIVY VALLEY 1107869946 | 491 | REMG 2022-2023 | Tier 2
35256082 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 0 | 1.211 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35223032 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.84924 | 0 | 0 | 0.84924 | 0 | 0 | 0.47045 | 0.37879 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | PSPS - Community Resiliency | Tier 2
35283341 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.07803 | 0 | 0.07803 | 0 | 0 | 0 | 0.07803 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35225827 |  | Base SH | 08W | ESTS | Estimating | 0.84564 | 0 | 0 | 0.84564 | 0 | 0 | 0.84564 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35283344 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.6561 | 0 | 1.6561 | 0 | 0 | 0 | 1.6561 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35233953 |  | Base SH | 08W | ESTS | Estimating | 0.84034 | 0 | 0 | 0.84034 | 0 | 0 | 0.84034 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35283347 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.478 | 0 | 1.478 | 0 | 0 | 0 | 1.478 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35283348 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.075 | 0 | 1.075 | 0 | 0 | 0 | 1.075 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35283349 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 1.0549 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35285247 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.48106 | 0 | 0.48106 | 0 | 0 | 0 | 0.48106 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35285248 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.461 | 0 | 1.461 | 0 | 0 | 0 | 1.461 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35280496 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35285250 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.51705 | 0 | 0.51705 | 0 | 0 | 0 | 0.51705 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35233315 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.80436 | 0 | 0 | 0.80436 | 0 | 0 | 0.80436 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35217273 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.0799 | 0 | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake |  |  | UPPER LAKE 1101CB | 6 | Top 50 Miles | Tier 2
35219291 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.35814 | 0 | 0.35814 | 0 | 0 | 0.35814 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 1101126774 | 20 | Top 250 Miles | Tier 2
35219269 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 2.14 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237258 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.15 | 0 | 2.15 | 0 | 0 | 2.15 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237259 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.5744 | 0 | 3.5744 | 0 | 0 | 3.5744 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237360 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 3.01 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237361 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3383 | 0 | 2.3383 | 0 | 0 | 2.3383 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237364 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.8307 | 0 | 2.8307 | 0 | 0 | 2.8307 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237365 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.5699 | 0 | 2.5699 | 0 | 0 | 2.5699 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237366 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237368 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 4.19 | 0 | 4.19 | 0 | 0 | 4.19 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237369 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.14 | 0 | 3.14 | 0 | 0 | 3.14 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237370 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.7799 | 0 | 3.7799 | 0 | 0 | 3.7799 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35237371 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0.33996 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 110540092 | 37 | Top 250 Miles | Tier 2
35219590 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6167 | 0 | 1.6167 | 0 | 0 | 1.6167 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACA DIXON 1105965390 | 53 | Top 250 Miles | Tier 2
35270705 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.79394 | 0 | 0 | 0.79394 | 0 | 0.79394 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011612 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35224378 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.8888 | 0.075947 | 2.9648 | 0 | 1.1445 | 1.8203 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35290540 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35227657 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.44186 | 0 | 0.44186 | 0 | 0.44186 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35227658 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.41307 | 0 | 0.41307 | 0 | 0 | 0.41307 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35227659 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.25568 | 0 | 0.25568 | 0 | 0.25568 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35297696 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35227651 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.6951 | 0 | 2.6951 | 0 | 0 | 2.6951 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35233312 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.78371 | 0 | 0 | 0.78371 | 0 | 0 | 0.78371 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35227653 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.646 | 0 | 2.646 | 0 | 0 | 2.646 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35227654 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.52992 | 0.52992 | 0 | 0 | 0.52992 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35271455 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.54034 | 0 | 0.54034 | 0 | 0 | 0.54034 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35254720 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254721 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.2049 | 0 | 2.2049 | 0 | 0 | 2.2049 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254738 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 1.018 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35300933 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0.77992 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35254657 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.16004 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254658 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.7561 | 0 | 1.7561 | 0 | 0 | 1.7561 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254659 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.6759 | 0 | 2.6759 | 0 | 0 | 2.6759 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254940 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0.64697 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35254941 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.178 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35254942 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.482 | 0 | 1.482 | 0 | 0 | 1.482 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35254943 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.93201 | 0 | 0.93201 | 0 | 0 | 0.93201 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35243444 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35240169 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.8951 | 0 | 1.8951 | 0 | 0 | 1.8951 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35240170 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.83731 | 0 | 0.83731 | 0 | 0 | 0.83731 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35240171 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.3409 | 0 | 1.3409 | 0 | 0 | 1.3409 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2
35243453 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.2042 | 0 | 1.2042 | 0 | 0 | 1.2042 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35254944 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.052841 | 0.12 | 0.17284 | 0 | 0 | 0.17284 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35283346 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.77803 | 0 | 0 | 0.77803 | 0 | 0 | 0 | 0.77803 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35254946 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88902 | 0 | 0.88902 | 0 | 0 | 0.88902 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35223039 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | WYANDOTTE 1109702710 | 218 | PSPS - Community Resiliency | Tier 2
35254948 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.97898 | 0 | 0.97898 | 0 | 0 | 0.97898 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35219273 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.1519 | 0 | 1.1519 | 0 | 0 | 1.1519 | 0 | 0 | NV | Region 2 - North East | Manton | TEHAMA |  |  | VOLTA 110149742 | 39 | Top 250 Miles | Tier 2
35240168 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35225822 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.75152 | 0 | 0 | 0.75152 | 0 | 0.75152 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35292756 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 0.75 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35254651 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4252 | 0 | 2.4252 | 0 | 0 | 2.4252 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35254652 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.9341 | 0 | 1.9341 | 0 | 0 | 1.9341 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35254653 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.028 | 0 | 2.028 | 0 | 0 | 2.028 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35254654 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.15511 | 0 | 0.15511 | 0 | 0 | 0.15511 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35254655 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.55227 | 0 | 0.55227 | 0 | 0 | 0.55227 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35254640 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0326 | 0 | 1.0326 | 0 | 0 | 1.0326 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35270755 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.74867 | 0 | 0 | 0.74867 | 0 | 0.74867 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011612 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35254642 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.81042 | 0 | 0.81042 | 0 | 0 | 0.81042 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35237893 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.74811 | 0 | 0 | 0.74811 | 0 | 0 | 0.74811 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35254644 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.41004 | 0 | 0.41004 | 0 | 0 | 0.41004 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35254645 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.75095 | 0 | 0.75095 | 0 | 0 | 0.75095 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2
35254646 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.34394 | 0.34394 | 0 | 0 | 0.34394 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2
35235706 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.7392 | 0 | 0 | 0.7392 | 0 | 0 | 0.7392 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35254648 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.48485 | 0 | 0.48485 | 0 | 0 | 0.48485 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2
35254258 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.45 | 0 | 1.45 | 0 | 0 | 0 | 1.45 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35242428 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35240166 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.47784 | 0 | 0.47784 | 0 | 0 | 0.47784 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35235679 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.72784 | 0 | 0 | 0.72784 | 0 | 0 | 0.72784 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35106331 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.49 | 0 | 2.49 | 2.3309 | 0.15909 | 0 | 0 | 0 | NV | Region 2 - North East | Shingletown | SHASTA |  |  | VOLTA 110253130 | 2314 | Pre | Tier 3
35113102 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2267 | 0 | 2.2267 | 2.1784 | 0.048295 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | AMADOR |  |  | WEST POINT 110113444 | 2293 | Pre | Tier 3
35219589 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.7958 | 0 | 2.7958 | 0 | 0 | 0 | 2.7958 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011454 | 52 | Top 250 Miles | Tier 2
35224321 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4055 | 0 | 2.4055 | 0 | 0 | 0 | 2.4055 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011454 | 52 | Top 250 Miles | Tier 2
35226900 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.6517 | 0 | 0.6517 | 0 | 0 | 0.6517 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011454 | 52 | Top 250 Miles | Tier 2
35226798 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.7034 | 0 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011454 | 52 | Top 250 Miles | Tier 2
35226799 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0.19223 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011454 | 52 | Top 250 Miles | Tier 2
35227001 |  | Base SH | 08W | ADER | Estimating | 0.7214 | 0 | 0 | 0.7214 | 0 | 0 | 0 | 0.7214 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35192291 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.70871 | 0 | 0 | 0.70871 | 0 | 0 | 0.70871 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 11071402 | 811 | ECOP | Tier 3
35219260 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.92822 | 0.86723 | 1.7955 | 0 | 0.87803 | 0.91742 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | WYANDOTTE 110932586 | 29 | Top 250 Miles | Tier 2
35234529 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | 0 | 0 | 0.70833 | 0 | 0 | 0 | 0 | 0.70833 | SI | Region 2 - North East | Downieville | SIERRA |  |  | ALLEGHANY 1101VR816 | 2010 | PSPS - Community Resiliency | Tier 3
31478906 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley
31534930 |  | Base SH | 08H | UNSC | Ready for Construction | 0 | 2.2805 | 0 | 2.2805 | 0 | 0 | 2.2805 | 0 | 0 | NV | Region 2 - North East
31540451 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East
31548160 |  | Base SH | 08H | ADER | Estimating | 0 | 2.135 | 0 | 2.135 | 0 | 0 | 2.135 | 0 | 0 | NV | Region 2 - North East
31554994 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East
35129944 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa
35294275 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA
35264250 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.15473 | 0 | 0.15473 | 0 | 0.15473 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011612 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35254649 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.70606 | 0 | 0 | 0.70606 | 0 | 0 | 0.70606 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35242424 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.69943 | 0 | 0 | 0.69943 | 0 | 0 | 0.69943 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35233995 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.69886 | 0 | 0 | 0.69886 | 0 | 0 | 0.69886 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  | PLACERVILLE 21067522 | 1363 | PSPS - Community Resiliency | Tier 3
35284826 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | APPLE HILL 21029722 | 1131 | FRRB | Tier 2 & 3
35284827 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 1.2553 | 0.087121 | 1.3424 | 0 | 1.3424 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | APPLE HILL 21029722 | 1131 | FRRB | Tier 2 & 3
35284569 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.68409 | 0 | 0 | 0.68409 | 0 | 0 | 0.68409 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 110248894 | 1378 | FRRB | Tier 2
35236992 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - REMG - 2021 | Tier 3
35242425 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.66155 | 0 | 0 | 0.66155 | 0 | 0 | 0.66155 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35285251 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.65303 | 0 | 0 | 0.65303 | 0 | 0 | 0 | 0.65303 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | UPPER LAKE 11011276 | 335 | CWSP 2022-2023 | Tier 2
35284567 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.64773 | 0 | 0 | 0.64773 | 0 | 0 | 0.64773 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 11012768 | 1885 | FRRB | Tier 2
35234865 |  | Base SH | 08W | ESTS | Estimating | 0.64754 | 0 | 0 | 0.64754 | 0 | 0 | 0 | 0.64754 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35233311 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0.64205 | 0 | 0 | 0.64205 | 0 | 0.64205 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35295010 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35295187 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35242426 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.63352 | 0 | 0 | 0.63352 | 0 | 0 | 0.63352 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35058026 |  | Base SH | 08W | ESTS | Estimating | 0.6267 | 0 | 0 | 0.6267 | 0 | 0 | 0 | 0.6267 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210163464 | 1138
35227864 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35290508 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0 | 0.62008 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35235671 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.6161 | 0 | 0 | 0.6161 | 0 | 0.6161 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35290504 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.61004 | 0 | 0 | 0.61004 | 0 | 0 | 0 | 0.61004 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35300884 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0.6 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ |  |  | POINT MORETTI 1101415734 |  | FRRB
35242429 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - UG - 2021 | Tier 3
35057010 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.59375 | 0.71572 | 0 | 1.3095 | 0 | 0 | 1.3095 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210119752 | 1946 | PSS Approved | Tier 3
35284568 |  | Fire Rebuild | 08W | ADER | Estimating | 0.59318 | 0 | 0 | 0.59318 | 0 | 0 | 0.59318 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 110132726 | 2201 | FRRB | Tier 2
35235674 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 1102CB | 865 | FRRB - UG - 2021 | Tier 3
35242420 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.094697 | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 1102CB | 865 | FRRB - UG - 2021 | Tier 3
35241078 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.18258 | 0 | 0.18258 | 0 | 0.18258 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 1102CB | 865 | FRRB - UG - 2021 | Tier 3
35241079 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.074621 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | BIG BEND 1102CB | 865 | FRRB - UG - 2021 | Tier 3
35226878 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.58883 | 0 | 0 | 0.58883 | 0 | 0 | 0 | 0.58883 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35285064 |  | Base SH | 08W | ESTS | Estimating | 0.58636 | 0 | 0 | 0.58636 | 0 | 0 | 0 | 0.58636 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110537476 | 396 | CWSP 2022-2023 | Tier 2
35229119 |  | Base SH | 08W | UNSC | Ready for Construction | 0.5858 | 0 | 0 | 0.5858 | 0 | 0 | 0.5858 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101118494 | 23 | Top 250 Miles | Tier 2 & 3
35292757 |  | Fire Rebuild | 08W | ADER | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35234758 |  | Base SH | 08W | ADER | Estimating | 0.58201 | 0 | 0 | 0.58201 | 0 | 0 | 0 | 0.58201 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35280492 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35280493 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.35 | 0 | 0.35 | 0 | 0 | 0.35 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35280495 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0.51004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35279985 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 2.19 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35145004 |  | Base SH | 08W | CONS | In-Construction | 0.58201 | 0.37216 | 0 | 0.95417 | 0 | 0 | 0.95417 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa |  |  | ROSSMOOR 1106CB | 3259 | PSPS - Community Resiliency | Tier 2 & 3
35290943 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35227003 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.58087 | 0 | 0 | 0.58087 | 0 | 0 | 0 | 0.58087 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35290945 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35223030 |  | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East | Bangor | BUTTE |  |  | BANGOR 1101CB | 355 | PSPS - Community Resiliency | Tier 2
35290947 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35226700 |  | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | WYANDOTTE 110932586 | 29 | Top 250 Miles | Tier 2
35290518 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35290519 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35295188 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35300885 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ |  |  | BIG BASIN 11022253 | 2246 | FRRB
35290545 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35292759 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35297464 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | 0 | 0.56818 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ |  |  | POINT MORETTI 110112122 | 2199 | FRRB
35292781 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35290542 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.56004 | 0 | 0 | 0.56004 | 0 | 0 | 0.56004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35292783 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35238840 |  | Fire Rebuild | 95F | CONS | In-Construction | 0.55152 | 0.012311 | 0 | 0.56383 | 0 | 0 | 0.56383 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ
35292785 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35233305 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.55114 | 0 | 0 | 0.55114 | 0 | 0.55114 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35292787 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.16004 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012476 | 2342 | FRRB | Tier 2
35227652 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.55 | 0 | 0 | 0.55 | 0 | 0 | 0.55 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11046542 | 42 | Top 250 Miles | Tier 3
35227025 |  | Base SH | 08W | ESTS | Estimating | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0 | 0.54924 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35290541 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.34223 | 0 | 0.34223 | 0 | 0.34223 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012586 | 1285 | FRRB | Tier 2
35292790 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012586 | 1285 | FRRB | Tier 2
35233955 |  | Base SH | 08W | ESTS | Estimating | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35302344 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.18939 | 0 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35286199 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.29167 | 0 | 0.29167 | 0 | 0.29167 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35145540 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.53902 | 0.73333 | 0 | 1.2723 | 0 | 0 | 1.2723 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras |  |  | FROGTOWN 1702CB | 1316 | PSPS - Scoped | Tier 3
35279603 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35279604 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.5146 | 0 | 1.5146 | 0 | 1.3017 | 0.21288 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35279605 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.72879 | 0 | 0.72879 | 0 | 0.72879 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35223038 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.53295 | 0 | 0 | 0.53295 | 0 | 0 | 0.53295 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR |  |  | MARTELL 1101CB | 999 | PSPS - Community Resiliency | Tier 2
35254641 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.52235 | 0.075947 | 0.47727 | 1.0756 | 0 | 0 | 1.0756 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2 & 3
35295184 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35277195 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1101CB | 11 | FRRB | Tier 2 & 3
35277565 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1102CB | 378 | FRRB | Tier 2 & 3
35293508 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.51004 | 0 | 0 | 0.51004 | 0 | 0 | 0 | 0.51004 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35254945 |  | Base SH | 08W | ESTS | Estimating | 0.51 | 0 | 0 | 0.51 | 0 | 0 | 0 | 0.51 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35254647 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.50606 | 0 | 0 | 0.50606 | 0 | 0 | 0 | 0.50606 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2
35293662 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 21011350 | 169 | CWSP 2022-2023 | Tier 2
35297232 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0.18939 | 0.18939 | 0 | 0 | 0 | 0.18939 | 0 | NV | Region 2 - North East | Twain | PLUMAS |  |  | BUCKS CREEK 1102CB | 378 | FRRB - REMG - 2021 | Tier 2 & 3
35295446 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Quincy | PLUMAS |  |  | BUCKS CREEK 1103CB | 1658 | FRRB | Tier 2 & 3
35279987 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.5227 | 0.087121 | 1.6098 | 0 | 1.6098 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas |  |  | CHESTER 11022564 | 2726 | FRRB | Tier 2
35292751 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35292753 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35235673 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.49356 | 0 | 0 | 0.49356 | 0 | 0.49356 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35280497 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35280498 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0.073295 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35286724 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.0837 | 0 | 1.0837 | 0 | 1.0485 | 0.035227 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | CRESCENT MILLS 21012056 | 895 | FRRB | Tier 2
35234399 |  | Base SH | 08W | ESTS | Estimating | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35285586 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.27216 | 0 | 0.27216 | 0 | 0.27216 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35285587 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.71136 | 0 | 0.71136 | 0 | 0.71136 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35285588 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.56307 | 0.046023 | 0.60909 | 0 | 0.60909 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35236993 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - REMG - 2021 | Tier 3
35285590 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.43674 | 0 | 0.43674 | 0 | 0.43674 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35285591 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.47595 | 0.032955 | 0.5089 | 0 | 0.5089 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35285592 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.76458 | 0 | 0.76458 | 0 | 0.76458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35285593 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.26458 | 0 | 0.26458 | 0 | 0.26458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101481660 | 2005 | FRRB | Tier 2
35236660 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.47992 | 0 | 0 | 0.47992 | 0 | 0 | 0.47992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35285352 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.13845 | 0 | 0.13845 | 0 | 0.13845 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101481660 | 2005 | FRRB | Tier 2
35285353 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.31856 | 0 | 0.31856 | 0 | 0.31856 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101481660 | 2005 | FRRB | Tier 2
35285354 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101481660 | 2005 | FRRB | Tier 2
35285585 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.63902 | 0 | 0.63902 | 0 | 0.63902 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 110155262 | 3355 | FRRB | Tier 2
35285741 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.26837 | 0.027273 | 0.29564 | 0 | 0.29564 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35285742 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.24432 | 0.027462 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35286483 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.0843 | 0 | 1.0843 | 0 | 1.0843 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284716 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.7589 | 0 | 0.7589 | 0 | 0.7589 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284717 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.89489 | 0 | 0.89489 | 0 | 0.89489 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35292144 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.139 | 0 | 1.139 | 0 | 1.139 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35292145 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 2.1585 | 0 | 2.1585 | 0 | 1.625 | 0.53352 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35292188 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.13542 | 0 | 0.13542 | 0 | 0.13542 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35292189 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.18125 | 0 | 0.18125 | 0 | 0.18125 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35282125 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35282126 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35282281 |  | Fire Rebuild | 08W | ESTS | Post-Construction | 0 | 0.47235 | 0 | 0.47235 | 0 | 0.47235 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284828 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.65606 | 0 | 0.65606 | 0 | 0.65606 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284829 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.57348 | 0 | 0.57348 | 0 | 0.57348 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284830 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.76515 | 0 | 0.76515 | 0 | 0.76515 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284831 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.96402 | 0 | 0.96402 | 0 | 0.96402 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284832 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.89299 | 0 | 0.89299 | 0 | 0.89299 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284833 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.91837 | 0 | 0.91837 | 0 | 0.91837 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284834 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.70587 | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284835 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.4661 | 0 | 0.4661 | 0 | 0.4661 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284836 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.88182 | 0 | 0.88182 | 0 | 0.88182 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284837 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.7884 | 0 | 1.7884 | 0 | 1.7884 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284838 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.60568 | 0 | 0.60568 | 0 | 0.60568 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35284839 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.47595 | 0 | 0.47595 | 0 | 0.47595 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35285048 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.41212 | 0 | 0.41212 | 0 | 0.41212 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35285049 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.18542 | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35285050 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 1.593 | 0 | 1.593 | 0 | 1.593 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | EL DORADO |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35237891 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.47197 | 0 | 0 | 0.47197 | 0 | 0 | 0.47197 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35295017 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.47008 | 0 | 0 | 0.47008 | 0 | 0 | 0.47008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35233038 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.46932 | 0 | 0 | 0.46932 | 0 | 0.46932 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35233039 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.46326 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35239937 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.46193 | 0 | 0 | 0.46193 | 0 | 0.46193 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35279313 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.45985 | 0 | 0 | 0.45985 | 0 | 0 | 0.45985 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas |  |  | GANSNER 11012424 | 1172 | FRRB | Tier 2 & 3
35301112 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.45 | 0.05 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35239099 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35254656 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.44205 | 0 | 0 | 0.44205 | 0 | 0 | 0.44205 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 11011568 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254067 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.43996 | 0.039962 | 0 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0 | SI | Region 2 - North East | Cool | EL DORADO |  |  | MOUNTAIN QUARRIES 2101CB | 68 | CWSP 2022-2023 | Tier 2
35297695 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.43996 | 0 | 0 | 0.43996 | 0 | 0 | 0.43996 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35227002 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.43295 | 0 | 0 | 0.43295 | 0 | 0 | 0 | 0.43295 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35243440 |  | Base SH | 08W | ESTS | Estimating | 0.42992 | 0 | 0 | 0.42992 | 0 | 0 | 0 | 0.42992 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 1103CB | 290 | PSPS | Tier 2
35295745 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.41913 | 0 | 0 | 0.41913 | 0 | 0 | 0.41913 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031508 | 1176 | FRRB
35278093 |  | Base SH | 08W | ESTS | Estimating | 0.41496 | 0 | 0.52008 | 0.93504 | 0 | 0 | 0 | 0.93504 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35240167 |  | Base SH | 08W | ESTS | Estimating | 0.41288 | 0.037879 | 0 | 0.45076 | 0 | 0 | 0 | 0.45076 | 0 | NV | Region 2 - North East | Manton | SHASTA |  |  | VOLTA 1101CB | 76 | CWSP 2022-2023 | Tier 2
35283874 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.40284 | 0 | 0.15057 | 0.55341 | 0 | 0 | 0.55341 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35254260 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO |  |  | PUTAH CREEK 110267858 | 92 | CWSP 2022-2023 | Tier 2
35295012 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35235669 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.39148 | 0 | 0 | 0.39148 | 0 | 0.39148 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35295191 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3911 | 0 | 0 | 0.3911 | 0 | 0 | 0.3911 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35277938 |  | Base SH | 08W | ESTS | Estimating | 0.38996 | 0 | 0.27973 | 0.6697 | 0 | 0 | 0 | 0.6697 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35233309 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.38295 | 0 | 0 | 0.38295 | 0 | 0.38295 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
31547582 |  | Fire Rebuild | 92F | UNSC | Ready for Construction | 0 | 1.0136 | 0 | 1.0136 | 0 | 0 | 1.0136 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas |  |  | GANSNER 11012424 | 1172 | FRRB | Tier 2 & 3
35282057 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas |  |  | GANSNER 11012424 | 1172 | FRRB | Tier 2 & 3
35233300 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.37879 | 0 | 0 | 0.37879 | 0 | 0 | 0.37879 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35232718 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.37652 | 0 | 0 | 0.37652 | 0 | 0.37652 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35295018 |  | Fire Rebuild | 08W | ADER | Estimating | 0.37008 | 0 | 0 | 0.37008 | 0 | 0 | 0.37008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35254650 |  | Base SH | 08W | ESTS | Estimating | 0.36402 | 0 | 0 | 0.36402 | 0 | 0 | 0 | 0.36402 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 110153118 | 157 | CWSP 2022-2023 | Tier 2
35233307 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.36402 | 0 | 0 | 0.36402 | 0 | 0.36402 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35233304 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.35644 | 0 | 0 | 0.35644 | 0 | 0.35644 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35233306 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.35398 | 0 | 0 | 0.35398 | 0 | 0.35398 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35236999 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.175 | 0 | 0.175 | 0 | 0.175 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35237020 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.50795 | 0 | 0.50795 | 0 | 0.50795 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - REMG - 2021 | Tier 3
35240542 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.90795 | 0 | 0.90795 | 0 | 0.90795 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35240543 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.2068 | 0 | 1.2068 | 0 | 1.2068 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35236982 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.95 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - REMG - 2021 | Tier 3
35235701 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0.10909 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35239522 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.34848 | 0 | 0 | 0.34848 | 0 | 0 | 0.34848 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35227004 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.3483 | 0 | 0 | 0.3483 | 0 | 0 | 0.3483 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35236986 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.8441 | 0 | 1.8441 | 0 | 1.8441 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - REMG - 2021 | Tier 3
35236989 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0 | 0.51326 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35236983 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.34072 | 0 | 0 | 0.34072 | 0 | 0 | 0.34072 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | BIG BEND 11021972 | 1288 | FRRB - REMG - 2021 | Tier 3
35235704 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.18902 | 0 | 0.18902 | 0 | 0 | 0 | 0.18902 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35294385 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35318074 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.33996 | 0 | 0 | 0.33996 | 0 | 0 | 0 | 0.33996 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ
35227162 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.32008 | 0 | 0 | 0.32008 | 0 | 0 | 0.32008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8 | Top 50 Miles | Tier 2
35253173 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.059848 | 0 | 0.059848 | 0 | 0.059848 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35253174 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.28826 | 0 | 0.28826 | 0 | 0.28826 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35223063 |  | Base SH | 08W | ESTS | Estimating | 0.3197 | 0 | 0 | 0.3197 | 0 | 0 | 0 | 0.3197 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | DUNBAR 1101CB | 2048 | PSPS - Community Resiliency | Tier 2
35244696 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.29678 | 0 | 0.29678 | 0 | 0.29678 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35244697 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.12405 | 0 | 0.12405 | 0 | 0.12405 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35244698 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.090341 | 0 | 0.090341 | 0 | 0 | 0 | 0.090341 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35244699 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.080114 | 0 | 0.080114 | 0 | 0 | 0 | 0.080114 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245140 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0.27178 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245141 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.054545 | 0 | 0.054545 | 0 | 0 | 0 | 0.054545 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245142 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245143 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.2589 | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245144 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.24886 | 0 | 0.24886 | 0 | 0.24886 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245145 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.095455 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245146 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.13731 | 0 | 0.13731 | 0 | 0 | 0 | 0.13731 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245147 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.39242 | 0 | 0.39242 | 0 | 0.39242 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245148 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.20492 | 0 | 0.20492 | 0 | 0 | 0 | 0.20492 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245149 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.26894 | 0 | 0.26894 | 0 | 0 | 0 | 0.26894 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245150 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.12557 | 0 | 0.12557 | 0 | 0 | 0 | 0.12557 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245151 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.15455 | 0 | 0.15455 | 0 | 0.15455 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35245152 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.48295 | 0 | 0.48295 | 0 | 0 | 0 | 0.48295 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - OH - 2021 | Tier 3
35109546 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.31515 | 2.4574 | 0 | 2.7725 | 0 | 0 | 2.7725 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210119752 | 1946 | PSS Approved | Tier 3
35295016 |  | Fire Rebuild | 08W | ADER | Estimating | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35241077 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | 0 | 0.31004 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35279508 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 11012768 | 1885 | FRRB | Tier 2
35279509 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.1801 | 0 | 1.1801 | 0 | 1.1801 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 11012768 | 1885 | FRRB | Tier 2
35235672 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | 0 | 0 | 0.30303 | 0 | 0 | 0 | 0.30303 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35284570 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.24564 | 0 | 0.24564 | 0 | 0.24564 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 11012768 | 1885 | FRRB | Tier 2
35233310 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.30246 | 0 | 0 | 0.30246 | 0 | 0 | 0.30246 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35217272 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011586 | 7 | Top 50 Miles | Tier 3
35290944 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35281759 |  | Fire Rebuild | 08W | ADER | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS |  |  | SPANISH CREEK 4401CB | 1322 | FRRB | Tier 2
35281815 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35250343 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.29432 | 0 | 0 | 0.29432 | 0 | 0 | 0.29432 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35291986 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.8223 | 0 | 1.8223 | 0 | 1.6958 | 0.12652 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 110148950 | 851 | FRRB | Tier 2
35236997 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | 0 | 0 | 0.28409 | 0 | 0 | 0 | 0.28409 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - REMG - 2021 | Tier 3
35293380 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 110148950 | 851 | FRRB | Tier 2
35291988 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 110148950 | 851 | FRRB | Tier 2
35291987 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35291895 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.18864 | 0 | 0.18864 | 0 | 0.18864 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35291982 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.15076 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35291983 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.25038 | 0 | 0.25038 | 0 | 0.25038 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35291984 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.4841 | 0 | 1.4841 | 0 | 1.4841 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35291985 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.8875 | 0 | 0.8875 | 0 | 0.8875 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 1102CB | 502 | FRRB | Tier 2
35285589 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.28295 | 0 | 0 | 0.28295 | 0 | 0 | 0.28295 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101344250 | 2461 | FRRB | Tier 2
35220896 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake |  |  | MIDDLETOWN 1103830 | 14 | Top 50 Miles | Tier 2 & 3
35295015 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35224377 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.2786 | 0 | 0 | 0.2786 | 0 | 0 | 0.2786 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  | PLACERVILLE 21067522 | 1363 | PSPS - Community Resiliency | Tier 3
35283198 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.27803 | 0 | 0 | 0.27803 | 0 | 0 | 0 | 0.27803 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101698 | 58 | CWSP 2022-2023 | Tier 2
35254947 |  | Base SH | 08W | ESTS | Estimating | 0.263 | 0 | 0 | 0.263 | 0 | 0 | 0 | 0.263 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966 | CWSP 2022-2023 | Tier 2
35056733 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.26193 | 1.2653 | 0 | 1.5273 | 0 | 0 | 1.5273 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210119752 | 1946 | PSS Approved | Tier 3
35281810 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35281813 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.046591 | 0 | 0.046591 | 0 | 0 | 0 | 0.046591 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35232298 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.26155 | 0 | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35295182 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.26004 | 0 | 0 | 0.26004 | 0 | 0 | 0.26004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35144944 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.2553 | 0 | 0 | 0.2553 | 0 | 0 | 0.2553 | 0 | 0 | PN | Region 3 - Bay Area | South San Francisco | SAN MATEO |  |  | SNEATH LANE 110748338 | 3550 | PSPS - Community Resiliency | Tier 2
35235320 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35290808 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.24508 | 0 | 0 | 0.24508 | 0 | 0 | 0 | 0.24508 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 11051904 | 75 | CWSP 2022-2023 | Tier 2
35109541 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.24223 | 2.4256 | 0 | 2.6678 | 0 | 0 | 2.6678 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | EL DORADO PH 210119752 | 1946 | PSS Approved | Tier 3
35285065 |  | Base SH | 08W | ESTS | Estimating | 0.24167 | 0.012311 | 0 | 0.25398 | 0 | 0 | 0 | 0.25398 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110537476 | 396 | CWSP 2022-2023 | Tier 2
35145003 |  | Base SH | 08W | CONS | In-Construction | 0.24015 | 0.079545 | 0 | 0.3197 | 0 | 0 | 0.3197 | 0 | 0 | DI | Region 3 - Bay Area | Orinda | Contra Costa |  |  | MORAGA 1103CB | 2631 | PSPS - Community Resiliency | Tier 2 & 3
35219543 |  | Base SH | 08W | ESTS | Estimating | 0.24 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0.24 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 1112CB | 2123 | PSPS - Community Resiliency | Tier 2
35292782 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.23011 | 0 | 0 | 0.23011 | 0 | 0 | 0.23011 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35239523 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.22917 | 0 | 0 | 0.22917 | 0 | 0.22917 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35295193 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35285594 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  | ECHO SUMMIT 1101481660 | 2005 | FRRB | Tier 2
35259516 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.21364 | 0 | 0 | 0.21364 | 0 | 0 | 0.21364 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35277925 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.21326 | 0 | 0 | 0.21326 | 0 | 0 | 0 | 0.21326 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101CB | 63 | CWSP 2022-2023 | Tier 2
35295190 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35279243 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.20511 | 0 | 0 | 0.20511 | 0 | 0.20511 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35249161 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0.19508 | 0 | 0 | 0.19508 | 0 | 0.19508 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35284365 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.19375 | 0.019508 | 0 | 0.21326 | 0 | 0 | 0 | 0.21326 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | STANISLAUS 1702CB | 235 | CWSP 2022-2023 | Tier 2 & 3
35237021 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.19318 | 0 | 0 | 0.19318 | 0 | 0 | 0.19318 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35295192 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.18996 | 0 | 0 | 0.18996 | 0 | 0 | 0.18996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35290946 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35295011 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35295189 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35292780 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17008 | 0 | 0 | 0.17008 | 0 | 0 | 0.17008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35219542 |  | Base SH | 08W | UNSC | Ready for Construction | 0.16629 | 0 | 0.048295 | 0.21458 | 0 | 0 | 0.21458 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 1112CB | 2123 | PSPS - Community Resiliency | Tier 2
35295014 |  | Fire Rebuild | 08W | ADER | Estimating | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35233302 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35259512 |  | Base SH | 08W | ADER | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA |  |  | DESCHUTES 11041370 | 100 | CWSP 2022-2023 | Tier 2
35292758 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012248 | 916 | FRRB | Tier 2
35290948 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35295013 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35295194 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35279512 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.13542 | 0 | 0 | 0.13542 | 0 | 0 | 0.13542 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | BRUNSWICK 11062790 | 715 | FRRB | Tier 3
35240545 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.13125 | 0 | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35240546 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.13087 | 0 | 0 | 0.13087 | 0 | 0 | 0.13087 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35233301 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.12917 | 0 | 0 | 0.12917 | 0 | 0.12917 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35318072 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.12784 | 0 | 0 | 0.12784 | 0 | 0 | 0.12784 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35292791 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012586 | 1285 | FRRB | Tier 2
35295185 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  | EL DORADO PH 210126000 | 2252 | FRRB | Tier 2 & 3
35235675 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | 0 | 0 | 0.11364 | 0 | 0 | 0 | 0.11364 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35241076 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35235670 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35277924 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | 0 | 0.12955 | 0.23864 | 0 | 0 | 0 | 0.23864 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2578 | 163 | CWSP 2022-2023 | Tier 2
35280362 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.1089 | 0 | 0 | 0.1089 | 0 | 0 | 0 | 0.1089 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2102440236 | 50 | Top 250 Miles | Tier 2 & 3
35248770 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.10814 | 0 | 0 | 0.10814 | 0 | 0.10814 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35226632 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.10606 | 0 | 0 | 0.10606 | 0 | 0 | 0.10606 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO |  |  | POTTER VALLEY P H 110564118 | 43 | Top 250 Miles | Tier 2
35116801 |  | Base SH | 08W | FICL | Post-Construction | 0.10417 | 1.1737 | 0 | 1.2778 | 0.37008 | 0.90777 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | MIWUK 1702823548 | 2411 | Pre | Tier 3
35233957 |  | Base SH | 08W | ESTS | Estimating | 0.10208 | 0 | 0 | 0.10208 | 0 | 0 | 0.10208 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49 | Top 250 Miles | Tier 2
35292784 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35292786 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012260 | 995 | FRRB | Tier 2
35292789 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas |  |  | BIG MEADOWS 21012476 | 2342 | FRRB | Tier 2
74008802 |  | Other | 06A | DOCC | Post-Construction | 0.099432 | 1.0496 | 0 | 1.1491 | 0 | 1.1491 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa |  |  | ROSSMOOR 1108CB | 2676
35299634 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 11022070 | 1033 | PSPS | Tier 2
35299633 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 11022094 | 1703 | PSPS | Tier 2
35299635 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Paradise | BUTTE |  |  | CLARK ROAD 110247006 | 1535 | PSPS | Tier 2
35299631 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 110281296 | 698 | PSPS | Tier 2
35299629 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 1102CB | 268 | PSPS | Tier 2
35282131 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35277935 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.092992 | 0 | 0 | 0.092992 | 0 | 0 | 0 | 0.092992 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | AUBERRY 1101R2839 | 274 | CWSP 2022-2023 | Tier 2
35279510 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.091856 | 0 | 0 | 0.091856 | 0 | 0.091856 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 110248894 | 1378 | FRRB | Tier 2
35114040 |  | Base SH | 08W | UNSC | Ready for Construction | 0.090341 | 1.3943 | 0 | 1.4847 | 0 | 0 | 1.4847 | 0 | 0 | ST | Region 5 - Central Valley | Kit Carson | Amador |  |  | PINE GROVE 11021222 | 2271 | Pre | Tier 3
35234862 |  | Base SH | 08W | ESTS | Estimating | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | 0 | 0.079924 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474 | ECOP - Top 20% | Tier 3
35281816 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2
35234527 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | 0 | 0 | 0.075947 | 0 | 0 | 0 | 0 | 0.075947 | SI | Region 2 - North East | Downieville | SIERRA |  |  | ALLEGHANY 1101VR816 | 2010 | PSPS - Community Resiliency | Tier 3
35223036 |  | Base SH | 08W | UNSC | Ready for Construction | 0.072159 | 0 | 0.018371 | 0.09053 | 0 | 0 | 0.072159 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | BRUNSWICK 1110CB | 2134 | PSPS - Community Resiliency | Tier 2
35241075 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | 0 | 0 | 0.070076 | 0 | 0 | 0 | 0.070076 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031976 | 1299 | FRRB - UG - 2021 | Tier 3
35254695 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte |  |  | KANAKA 1101CB | 1480 | FRRB - UG - 2021 | Tier 3
35233303 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.065909 | 0 | 0 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35199565 |  | Fire Rebuild | 95A | ESTS | Post-Construction | 0 | 28.8953 | 0 | 28.8953 | 26.7508 | 2.1445 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  |  | 1288
35222036 |  | Fire Rebuild | 95F | PEND | Permitting/Dependency | 0 | 0.52462 | 0 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35235158 |  | Fire Rebuild | 95F | MAPP | Post-Construction | 0 | 0.030871 | 0 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | CC | Region 4 - Central Coast | Felton | SANTA CRUZ
35237593 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.027462 | 0 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ
35237620 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.024621 | 0 | 0.024621 | 0 | 0.024621 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ
35238587 |  | Fire Rebuild | 95F | DOCC | Post-Construction | 0 | 0.36761 | 0 | 0.36761 | 0 | 0.36761 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Big sur | MONTEREY
35244330 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.057386 | 0 | 0 | 0.057386 | 0 | 0.057386 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte |  |  | WYANDOTTE 11031974 | 1849 | FRRB - UG - 2021 | Tier 3
35239462 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.28788 | 0 | 0.28788 | 0 | 0.22879 | 0.059091 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35239464 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.070265 | 0 | 0.070265 | 0 | 0 | 0.070265 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35242673 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.067235 | 0 | 0.067235 | 0 | 0.067235 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35245029 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.3125 | 0 | 0.3125 | 0 | 0 | 0.3125 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ
35250987 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.08447 | 0 | 0.08447 | 0 | 0 | 0.08447 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35259466 |  | Fire Rebuild | 95F | MAPP | Post-Construction | 0 | 0.045076 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ
35263364 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.38788 | 0 | 0.38788 | 0 | 0 | 0.38788 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ
35217268 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.039962 | 0.056818 | 0 | 0.09678 | 0 | 0 | 0.09678 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  | BUCKS CREEK 1101CB | 11 | Top 50 Miles | Tier 2 & 3
35234528 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | 0 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0.035985 | SI | Region 2 - North East | Downieville | SIERRA |  |  | ALLEGHANY 1101VR816 | 2010 | PSPS - Community Resiliency | Tier 3
35244158 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Goodyears Bar | SIERRA |  |  | ALLEGHANY 1101804 | 1753
35208064 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SI | Region 2 - North East | Goodyears Bar | SIERRA |  |  | ALLEGHANY 1101806 | 1446
35028500 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.65152 | 0.65152 | 0 | 0.65152 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | SIERRA |  |  | ALLEGHANY 1101806 | 1446
35264104 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10189 | 0.10189 | 0 | 0 | 0.10189 | 0 | 0 | SI | Region 2 - North East | Downieville | SIERRA |  |  | ALLEGHANY 1101806 | 1446
35244150 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | ALLEGHANY 1102CB | 1700
35121398 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.03447 | 0.03447 | 0 | 0.03447 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011378 | 1722
35121520 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0.65606 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA |  |  | ANTLER 11011378 | 1722
35185246 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.30701 | 0.30701 | 0 | 0.30701 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  | APPLE HILL 110413512 | 1284
35244148 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Camino | EL DORADO |  |  | APPLE HILL 110413512 | 1284
35148224 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Camino | EL DORADO |  |  | APPLE HILL 1104CB | 1422
35244146 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | APPLE HILL 2102186912 | 1035
35148039 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO |  |  | APPLE HILL 21028372 | 654
35148037 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.07822 | 0.07822 | 0 | 0 | 0.07822 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO |  |  | APPLE HILL 21029722 | 1131
35111037 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.030682 | 0.030682 | 0 | 0.030682 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Atascadero | SAN LUIS OBISPO |  |  | ATASCADERO 1103440856 | 1294
35083699 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101176050 | 1302
35154942 |  | Idle Facilities | 07D | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO |  |  | AUBERRY 1101R322 | 956
35221652 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Prather | FRESNO |  |  | AUBERRY 1102R902 | 213
35205112 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.095644 | 0.095644 | 0 | 0.095644 | 0 | 0 | 0 | NV | Region 2 - North East | Marysville | YUBA |  |  | BANGOR 11011958 | 785
35211755 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.10473 | 0.10473 | 0 | 0 | 0.10473 | 0 | 0 | NV | Region 2 - North East | Marysville | YUBA |  |  | BANGOR 11011958 | 785
35211757 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Marysville | YUBA |  |  | BANGOR 110131502 | 225
35277147 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | BEAR VALLEY 210521160 | 1019
35145458 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 1.6263 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | BEAR VALLEY 2105454432 | 882
35083878 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045644 | 0.045644 | 0 | 0 | 0.045644 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | BEAR VALLEY 21059560 | 1547
35211260 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | SI | Region 2 - North East | Auburn | PLACER |  |  | BELL 11082202 | 118
35211742 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.093561 | 0.093561 | 0 | 0 | 0.093561 | 0 | 0 | SI | Region 2 - North East | Auburn | PLACER |  |  | BELL 11082202 | 118
35078178 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ |  |  | BIG BASIN 11015028 | 2968
35240792 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.075189 | 0.075189 | 0 | 0.075189 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | BIG MEADOWS 21012260 | 995
35106411 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.038447 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | SI | Region 2 - North East | Dutch Flat | PLACER |  |  | BONNIE NOOK 1101CB | 1526
35149117 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.099621 | 0.099621 | 0 | 0.099621 | 0 | 0 | 0 | HB | Region 1 - North Coast | Carlotta | HUMBOLDT |  |  | BRIDGEVILLE 110237486 | 1315
35037613 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Carlotta | HUMBOLDT |  |  | BRIDGEVILLE 110237486 | 1315
35211230 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0.061174 | 0 | 0 | SA | Region 2 - North East | Browns Valley | YUBA |  |  | BROWNS VALLEY 110193870 | 774
35208071 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | BRUNSWICK 11062416 | 1638
35244185 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley |  |  |  | BRUNSWICK 1106CB | 1876
35211797 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | BRUNSWICK 11103907 | 2928
35224443 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.096402 | 0.096402 | 0 | 0.096402 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Buellton | SANTA BARBARA |  |  | BUELLTON 1101Y26 | 517
35224439 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15777 | 0.15777 | 0 | 0.15777 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA |  |  | BUELLTON 1102Y50 | 269
35122245 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA |  |  | CABRILLO 1103Y10 | 1278
35122244 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA |  |  | CABRILLO 1103Y46 | 998
35224451 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.013258 | 0.013258 | 0 | 0 | 0.013258 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA |  |  | CABRILLO 1104Y22 | 1500
35224444 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.32481 | 0.32481 | 0 | 0.32481 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA |  |  | CABRILLO 1104Y24 | 949
35224438 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0.017235 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA |  |  | CABRILLO 1104Y24 | 949
35222069 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.067045 | 0.067045 | 0 | 0.067045 | 0 | 0 | 0 | ST | Region 5 - Central Valley | San Andreas | CALAVERAS |  |  | CALAVERAS CEMENT 110111236 | 886
35221824 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.052652 | 0.052652 | 0 | 0 | 0.052652 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | CALAVERAS CEMENT 11012646 | 1889
35221747 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS |  |  | CALAVERAS CEMENT 11014786 | 804
35221748 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS |  |  | CALAVERAS CEMENT 11014786 | 804
35222073 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS |  |  | CALAVERAS CEMENT 11014786 | 804
35221818 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.071591 | 0.071591 | 0 | 0 | 0.071591 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS |  |  | CALAVERAS CEMENT 110180930 | 1652
35264103 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.13011 | 0.13011 | 0 | 0 | 0.13011 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA |  |  | CALISTOGA 110189150 | 1093
35243793 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA |  |  | CALISTOGA 1102634 | 1477
35211655 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | MENDOCINO |  |  | CALPELLA 1101619542 | 1432
35225015 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.030114 | 0.030114 | 0 | 0.030114 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Simeon | SAN LUIS OBISPO |  |  | CAMBRIA 1101858200 | 1620
35225253 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ |  |  | CAMP EVERS 21045096 | 2474
35206236 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.11212 | 0.11212 | 0 | 0 | 0.11212 | 0 | 0 | CC | Region 4 - Central Coast | Felton | SANTA CRUZ |  |  | CAMP EVERS 210510294 | 2167
35037588 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0.17216 | 0 | 0 | HB | Region 1 - North Coast | Fortuna | HUMBOLDT |  |  | CARLOTTA 112142896 | 1918
35083864 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | MI | Region 3 - Bay Area | Castro Valley | ALAMEDA |  |  | CASTRO VALLEY 1110MR243 | 1914
35204835 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.18636 | 0.18636 | 0 | 0.18636 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | SHASTA |  |  | CEDAR CREEK 11011664 | 281
35217691 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.083144 | 0.083144 | 0 | 0.083144 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | SHASTA |  |  | CEDAR CREEK 11011664 | 281
35207960 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10568 | 0.10568 | 0 | 0.10568 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | CEDAR CREEK 1101CB | 392
35038065 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.17973 | 0.17973 | 0 | 0.17973 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA |  |  | CHALLENGE 11021064 | 793
35122388 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA |  |  | CHALLENGE 11021064 | 793
35122390 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.031061 | 0.031061 | 0 | 0.031061 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA |  |  | CHALLENGE 11021064 | 793
35211211 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13352 | 0.13352 | 0 | 0.13352 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 110290548 | 1578
35221249 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | CLARK ROAD 110292622 | 771
35208045 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11155 | 0.11155 | 0 | 0.11155 | 0 | 0 | 0 | SI | Region 2 - North East | Rescue | El Dorado |  |  | CLARKSVILLE 210413352 | 586
35221659 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Ione | AMADOR |  |  | CLAY 110113442 | 744
35223265 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 1.2756 | 1.2756 | 0 | 1.2756 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Brentwood |  |  |  | CLAYTON 2213CB | 1367
35037880 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | CLEAR LAKE 11011302 | 2020
31255513 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Cloverdale | SONOMA |  |  | CLOVERDALE 1102674 | 680
35083755 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.059091 | 0.059091 | 0 | 0.059091 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera |  |  | COARSEGOLD 210410400 | 263
35211659 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | SI | Region 2 - North East | Camptonville | YUBA |  |  | COLUMBIA HILL 1101764 | 1590
35211656 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019318 | 0.019318 | 0 | 0.019318 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City |  |  |  | COLUMBIA HILL 1101CB | 1077
35149360 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065152 | 0.065152 | 0 | 0.065152 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA |  |  | CORNING 110253184 | 413
35223249 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN |  |  | COTATI 1103132 | 965
35208019 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.037121 | 0.037121 | 0 | 0 | 0.037121 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA |  |  | COTTONWOOD 11011610 | 470
35204801 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.27462 | 0.27462 | 0 | 0.27462 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA |  |  | COTTONWOOD 11011610 | 470
35204803 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.099621 | 0.099621 | 0 | 0 | 0.099621 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA |  |  | COTTONWOOD 11011610 | 470
35262345 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0.17803 | 0 | 0 | NV | Region 2 - North East | Cottonwood | SHASTA |  |  | COTTONWOOD 11021578 | 554
35038650 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037879 | 0.037879 | 0 | 0.037879 | 0 | 0 | 0 | HB | Region 1 - North Coast | Covelo | Mendocino |  |  | COVELO 1101516510 | 1591
35238953 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 4.2356 | 4.2356 | 0 | 0 | 4.2356 | 0 | 0 | NV | Region 2 - North East | Greenville | PLUMAS |  |  | CRESCENT MILLS 21012562 | 1078
35246795 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.09053 | 0.09053 | 0 | 0.09053 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora |  |  |  | CURTIS 17048140 | 1604
35221715 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | YO | Region 5 - Central Valley | Soulsbyville | TUOLUMNE |  |  | CURTIS 17058170 | 1770
35046236 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | CC | Region 4 - Central Coast | Salinas | MONTEREY |  |  | DEL MONTE 21042624 | 2367
35274991 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | DESCHUTES 11011580 | 375
35162302 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11629 | 0.11629 | 0 | 0.11629 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | Shasta |  |  | DESCHUTES 11011580 | 375
35204871 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | DESCHUTES 11011580 | 375
35204816 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050568 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | DESCHUTES 11011580 | 375
35275963 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Shingletown | SHASTA |  |  | DESCHUTES 11011654 | 1086
35204808 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0.015152 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta |  |  | DESCHUTES 11041370 | 100
35211254 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.030114 | 0.030114 | 0 | 0 | 0.030114 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11041370 | 100
35137767 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.032576 | 0.032576 | 0 | 0.032576 | 0 | 0 | 0 | NV | Region 2 - North East | Bella Vista |  |  |  | DESCHUTES 11041370 | 100
35237026 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.18769 | 0.18769 | 0 | 0 | 0.18769 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48
35144989 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0.073485 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48
35208066 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14205 | 0.14205 | 0 | 0 | 0.14205 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA |  |  | DESCHUTES 11049718 | 48
35205100 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.081818 | 0.081818 | 0 | 0.081818 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 11039432 | 1699
35211802 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0.055871 | 0 | 0 | SI | Region 2 - North East | Diamond Springs | EL DORADO |  |  | DIAMOND SPRINGS 1104CB | 2036
35211692 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | DIAMOND SPRINGS 110518935 | 1031
35244155 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 110610587 | 632
35244157 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 110610587 | 632
35244159 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | DIAMOND SPRINGS 11071402 | 811
35208046 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA |  |  | DOBBINS 11011264 | 650
35208012 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.1697 | 0.1697 | 0 | 0 | 0.1697 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA |  |  | DOBBINS 11011264 | 650
35208036 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.073485 | 0.073485 | 0 | 0.073485 | 0 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA |  |  | DOBBINS 11011264 | 650
35208044 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.20871 | 0.20871 | 0 | 0.20871 | 0 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA |  |  | DOBBINS 11011264 | 650
35208047 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0 | 0.02178 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA |  |  | DOBBINS 11011808 | 193
35244117 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Alta | PLACER |  |  | DRUM 11011602 | 2009
35083772 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15152 | 0.15152 | 0 | 0.15152 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Miramonte | Fresno |  |  | DUNLAP 11037220 | 364
35211354 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065909 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | EL DORADO |  |  | ECHO SUMMIT 1101344250 | 2461
35037596 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.20265 | 0.20265 | 0 | 0.20265 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ferndale | HUMBOLDT |  |  | EEL RIVER 11024814 | 1252
35208069 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO |  |  | EL DORADO PH 21026645 | 2469
35225016 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.32614 | 0.32614 | 0 | 0.32614 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO |  |  | FOOTHILL 110299432 | 2765
35150689 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.22045 | 0.22045 | 0 | 0.22045 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | MENDOCINO |  |  | FORT BRAGG A 11041316 | 2581
35159826 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0 | 0.015152 | 0 | 0 | SO | Region 1 - North Coast | Cazadero | SONOMA |  |  | FORT ROSS 1121124 | 1022
35037705 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.125 | 0.125 | 0 | 0.125 | 0 | 0 | 0 | HB | Region 1 - North Coast | Zenia | TRINITY |  |  | FORT SEWARD 11211602 | 1194
35149328 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Alderpoint | HUMBOLDT |  |  | FORT SEWARD 1121CB | 566
35149060 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0.020455 | 0 | 0 | HB | Region 1 - North Coast | Redcrest | HUMBOLDT |  |  | FRUITLAND 1141200856 | 1867
35045886 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.20587 | 0.20587 | 0 | 0.20587 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT |  |  | FRUITLAND 11422006 | 1426
35149232 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16098 | 0.16098 | 0 | 0.16098 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt |  |  | FRUITLAND 11426054 | 1295
35150991 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0.072159 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT |  |  | FRUITLAND 114263170 | 1429
35150549 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT |  |  | GARBERVILLE 11011604 | 522
35150686 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | HB | Region 1 - North Coast | Westport | MENDOCINO |  |  | GARBERVILLE 11012026 | 415
35037708 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13277 | 0.13277 | 0 | 0.13277 | 0 | 0 | 0 | HB | Region 1 - North Coast | Leggett | MENDOCINO |  |  | GARBERVILLE 110135706 | 928
35037707 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.21837 | 0.21837 | 0 | 0 | 0.21837 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT |  |  | GARBERVILLE 110139524 | 1245
35150103 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.038447 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT |  |  | GARBERVILLE 11021510 | 1476
35037706 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.024811 | 0.024811 | 0 | 0 | 0.024811 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT |  |  | GARBERVILLE 11022500 | 1149
35208094 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT |  |  | GARBERVILLE 110237054 | 1237
35208076 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.092235 | 0.092235 | 0 | 0 | 0.092235 | 0 | 0 | HB | Region 1 - North Coast | Piercy | MENDOCINO |  |  | GARBERVILLE 11026084 | 1777
35244151 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Piercy | MENDOCINO |  |  | GARBERVILLE 11026084 | 1777
35255487 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.21818 | 0.21818 | 0 | 0 | 0.21818 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA |  |  | GEYSERVILLE 1102274 | 940
35223270 |  | Idle Facilities | 2AF | APPR | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Geyserville | SONOMA |  |  | GEYSERVILLE 1102484 | 668
35224947 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO |  |  | GOLDTREE 1105CB | 1104
35211639 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | GRASS VALLEY 11012208 | 1973
35211212 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.073864 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada |  |  | GRASS VALLEY 11032180 | 524
35211204 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | GRASS VALLEY 11032180 | 524
35009378 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.60379 | 0.60379 | 0 | 0 | 0.60379 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | SAN MATEO |  |  | HALF MOON BAY 11036012 | 2186
35244167 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Meadow Vista | PLACER |  |  | HALSEY 11011704 | 2500
35037563 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Eureka | HUMBOLDT |  |  | HARRIS 11082062 | 3118
35205102 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0.10985 | 0 | 0 | HB | Region 1 - North Coast | Eureka | HUMBOLDT |  |  | HARRIS 1109355914 | 2462
35151050 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0041667 | 0.0041667 | 0 | 0.0041667 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101658 | 439
35151026 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.10152 | 0.10152 | 0 | 0 | 0.10152 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE |  |  | HARTLEY 1101658 | 439
35224893 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | CC | Region 4 - Central Coast | Carmel | MONTEREY |  |  | HATTON 110137088 | 2887
35211265 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16837 | 0.16837 | 0 | 0.16837 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | HIGGINS 1110166282 | 1259
35149235 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0.16515 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE |  |  | HIGHLANDS 11031282 | 626
35151074 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.2964 | 0.2964 | 0 | 0.2964 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE |  |  | HIGHLANDS 1103482 | 181
35208097 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0.017045 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE |  |  | HIGHLANDS 1103482 | 181
35149249 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake |  |  |  | HIGHLANDS 1103520 | 440
35150641 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1103568 | 212
35151070 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054924 | 0.054924 | 0 | 0.054924 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE |  |  | HIGHLANDS 1103CB | 461
35037377 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 1103CB | 461
35211257 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE |  |  | HIGHLANDS 110448262 | 3295
35224519 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Hollister | SAN BENITO |  |  | HOLLISTER 21054048 | 2382
35149246 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0.18277 | 0 | 0 | HB | Region 1 - North Coast | Hopland | MENDOCINO |  |  | HOPLAND 1101768 | 110
35151000 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.039773 | 0.039773 | 0 | 0.039773 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hopland | MENDOCINO |  |  | HOPLAND 1101CB | 1099
35078377 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Granite Bay | PLACER |  |  | HORSESHOE 110450142 | 2708
35275961 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.14148 | 0.14148 | 0 | 0 | 0.14148 | 0 | 0 | NV | Region 2 - North East | Igo | SHASTA |  |  | JESSUP 110141356 | 350
35211698 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.074811 | 0.074811 | 0 | 0.074811 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA |  |  | JESSUP 1102158468 | 3114
35204821 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10322 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta |  |  | JESSUP 11023105 | 89
35204826 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.083333 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA |  |  | JESSUP 110296554 | 267
35204796 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.018182 | 0.018182 | 0 | 0.018182 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville |  |  |  | KANAKA 11011034 | 1566
35211630 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.060038 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | NV | Region 2 - North East | Forbestown | YUBA |  |  | KANAKA 110165606 | 1201
35211753 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | KESWICK 11011590 | 848
35037854 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.086553 | 0.086553 | 0 | 0.086553 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | MONTEREY |  |  | KING CITY 11037038 | 1814
35205028 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | KONOCTI 110264664 | 168
35208093 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake |  |  | KONOCTI 110275382 | 728
35037896 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | KONOCTI 1102965078 | 9
35150135 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE |  |  | KONOCTI 1102CB | 407
35262342 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16193 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | MARIN |  |  | LAS GALLINAS A 1105532 | 359
35223248 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.052083 | 0.052083 | 0 | 0.052083 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda |  |  | LAS POSITAS 2108MR182 | 803
35255493 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.12614 | 0.12614 | 0 | 0 | 0.12614 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA |  |  | LAS POSITAS 2108MR182 | 803
35038684 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | MENDOCINO |  |  | LAYTONVILLE 1101402 | 1293
35038648 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.049811 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0 | HB | Region 1 - North Coast | Laytonville |  |  |  | LAYTONVILLE 110264908 | 1003
35149255 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.044508 | 0.044508 | 0 | 0.044508 | 0 | 0 | 0 | HB | Region 1 - North Coast | Branscomb |  |  |  | LAYTONVILLE 1102682 | 1508
35132573 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.068182 | 0.068182 | 0 | 0 | 0.068182 | 0 | 0 | HB | Region 1 - North Coast | Dos Rios | MENDOCINO |  |  | LAYTONVILLE 1102CB | 786
35208072 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Lincoln | PLACER |  |  | LINCOLN 11012310 | 1408
35244172 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.16326 | 0.16326 | 0 | 0 | 0.16326 | 0 | 0 | SI | Region 2 - North East | Lincoln | PLACER |  |  | LINCOLN 11042070 | 568
35221621 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.018939 | 0.018939 | 0 | 0.018939 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA |  |  | LOS GATOS 1106LA42 | 3015
35247031 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.14981 | 0.14981 | 0 | 0 | 0.14981 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA |  |  | LOS GATOS 1106LB44 | 1864
35126503 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.041667 | 0.041667 | 0 | 0 | 0.041667 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA |  |  | LOS GATOS 1107CB | 2606
35037897 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Nice | LAKE |  |  | LUCERNE 1106CB | 2687
35198772 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.27652 | 0.27652 | 0 | 0.27652 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | MARIPOSA 210110240 | 679
35198773 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.22064 | 0.22064 | 0 | 0.22064 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa |  |  | MARIPOSA 210110240 | 679
35198774 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.012311 | 0.012311 | 0 | 0.012311 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  |  |  | MARIPOSA 210110240 | 679
35198775 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.19223 | 0.19223 | 0 | 0.19223 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  |  |  | MARIPOSA 210110240 | 679
35198776 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.051136 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa |  |  | MARIPOSA 210110240 | 679
35198777 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa |  |  | MARIPOSA 210110240 | 679
35198778 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15625 | 0.15625 | 0 | 0.15625 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa |  |  | MARIPOSA 210110240 | 679
35198779 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019886 | 0.019886 | 0 | 0.019886 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa |  |  | MARIPOSA 210110240 | 679
35198780 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.19242 | 0.19242 | 0 | 0.19242 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  |  |  | MARIPOSA 210110240 | 679
35198781 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13068 | 0.13068 | 0 | 0.13068 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | MARIPOSA 210110240 | 679
35198782 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.035985 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | MARIPOSA 210110240 | 679
35277148 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 2101309438 | 605
35083807 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.014583 | 0.014583 | 0 | 0 | 0.014583 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | MARIPOSA 2101752630 | 700
35242663 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048295 | 0.048295 | 0 | 0.048295 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa |  |  |  | MARIPOSA 2101752630 | 700
35221744 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1447 | 0.1447 | 0 | 0.1447 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 21019400 | 655
35221710 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013636 | 0.013636 | 0 | 0.013636 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa |  |  |  | MARIPOSA 2101CB | 57
35083919 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.094886 | 0.094886 | 0 | 0.094886 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | MARIPOSA 210237288 | 379
35083888 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.072348 | 0.072348 | 0 | 0 | 0.072348 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | AMADOR |  |  | MARTELL 110292172 | 2054
35221764 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15473 | 0.15473 | 0 | 0.15473 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | AMADOR |  |  | MARTELL 110368192 | 1330
35211249 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Fall River Mills | SHASTA |  |  | MC ARTHUR 11011490 | 1181
35207802 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0625 | 0.0625 | 0 | 0.0625 | 0 | 0 | 0 | NV | Region 2 - North East | Fall River Mills |  |  |  | MC ARTHUR 11011490 | 1181
35038562 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0.054924 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | MENDOCINO |  |  | MENDOCINO 110148750 | 1073
35223241 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | Portola Valley | SAN MATEO |  |  | MENLO 11028896 | 1917
35155226 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042045 | 0.042045 | 0 | 0 | 0.042045 | 0 | 0 | PN | Region 3 - Bay Area | La Honda | SAN MATEO |  |  | MENLO 1102W80 | 620
35149134 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.098674 | 0.098674 | 0 | 0.098674 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE |  |  | MIDDLETOWN 11014646 | 328
35150566 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0.031629 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474
35151024 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1339 | 0.1339 | 0 | 0.1339 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474
35244105 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1101548 | 474
35149930 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.090341 | 0.090341 | 0 | 0.090341 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake |  |  | MIDDLETOWN 1101CB | 86
35150992 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.061932 | 0.061932 | 0 | 0.061932 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE |  |  | MIDDLETOWN 1102302610 | 8
35237664 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.47273 | 0.47273 | 0 | 0.47273 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hidden Valley Lake |  |  |  | MIDDLETOWN 1103830 | 14
31211614 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma |  |  | MOLINO 110241392 | 1468
35085362 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.026515 | 0.026515 | 0 | 0.026515 | 0 | 0 | 0 | SO | Region 1 - North Coast | Guerneville | SONOMA |  |  | MONTE RIO 1113346 | 2084
35243374 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.61667 | 0.61667 | 0 | 0 | 0.61667 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA |  |  | MONTICELLO 11014360 | 757
35221620 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SJ | Region 4 - Central Coast | Gilroy | SANTA CLARA |  |  | MORGAN HILL 2105XR176 | 854
35224941 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Morro Bay | SAN LUIS OBISPO |  |  | MORRO BAY 1102CB | 2399
35225009 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.08428 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | LP | Region 4 - Central Coast | Los Osos | SAN LUIS OBISPO |  |  | MORRO BAY 1102W34 | 2590
35217564 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Browns Valley | YUBA |  |  | NARROWS 21011202 | 758
35244154 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | NARROWS 21022220 | 505
35208024 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.049811 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0 | SI | Region 2 - North East | Penn Valley | NEVADA |  |  | NARROWS 21022718 | 1812
35211601 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.035606 | 0.035606 | 0 | 0 | 0.035606 | 0 | 0 | SI | Region 2 - North East | Rough and Ready | NEVADA |  |  | NARROWS 21052216 | 737
35208006 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.017614 | 0.017614 | 0 | 0 | 0.017614 | 0 | 0 | SI | Region 2 - North East | Rough and Ready | NEVADA |  |  | NARROWS 21052216 | 737
35211618 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Smartsville | NEVADA |  |  | NARROWS 210551582 | 582
35186134 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.060417 | 0.060417 | 0 | 0 | 0.060417 | 0 | 0 | SI | Region 2 - North East | Penn Valley | NEVADA |  |  | NARROWS 2105CB | 730
35083719 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.038636 | 0.038636 | 0 | 0.038636 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | Madera |  |  | OAKHURST 11035480 | 1903
35225441 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Bradley | MONTEREY |  |  | OILFIELDS 1103N48 | 508
35204811 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.125 | 0.125 | 0 | 0 | 0.125 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 11021584 | 1773
35211225 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110249144 | 968
35211643 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 11031500 | 981
35262346 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.1411 | 0.1411 | 0 | 0 | 0.1411 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 11031500 | 981
35262343 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0.05303 | 0 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA |  |  | OREGON TRAIL 110335002 | 49
35262344 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.049621 | 0.049621 | 0 | 0 | 0.049621 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49
35211263 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 110335002 | 49
35204806 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.044318 | 0.044318 | 0 | 0 | 0.044318 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | OREGON TRAIL 1104CB | 255
35225318 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | SANTA BARBARA |  |  | PALMER 1101M84 | 256
35225319 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.094697 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | SANTA BARBARA |  |  | PALMER 1101M84 | 256
35204902 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA |  |  | PANORAMA 1101CB | 1038
35119600 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.40947 | 0.40947 | 0 | 0.40947 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson |  |  |  | PANORAMA 1102508502 | 283
35109767 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054356 | 0.054356 | 0 | 0.054356 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise |  |  |  | PARADISE 11042034 | 1537
35254545 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.87273 | 0.87273 | 0 | 0.87273 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1103N50 | 138
35225437 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034659 | 0.034659 | 0 | 0.034659 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | PASO ROBLES 1104R56 | 251
35208010 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER |  |  | PENRYN 11051342 | 1016
35211210 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11364 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer |  |  | PENRYN 1106212772 | 385
35221768 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.19792 | 0.19792 | 0 | 0.19792 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | CALAVERAS |  |  | PEORIA 1704CB | 800
35083726 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048295 | 0.048295 | 0 | 0.048295 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne |  |  | PEORIA 170510580 | 835
35225011 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Cambria | SAN LUIS OBISPO |  |  | PERRY 1101V74 | 2433
35159821 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN |  |  | PETALUMA C 1108632 | 888
35223225 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.11269 | 0.11269 | 0 | 0 | 0.11269 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN |  |  | PETALUMA C 1108632 | 888
35221246 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Yorkville | MENDOCINO |  |  | PHILO 11013700 | 417
35244145 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 1109CB | 1761
35176816 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.14299 | 0.14299 | 0 | 0 | 0.14299 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 210611132 | 1666
35208054 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0.14867 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 210611132 | 1666
35135357 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.022348 | 0.022348 | 0 | 0.022348 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 210619732 | 2992
35148124 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 210623190 | 2430
35264102 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.10833 | 0.10833 | 0 | 0 | 0.10833 | 0 | 0 | SI | Region 2 - North East | Garden Valley | EL DORADO |  |  | PLACERVILLE 21067522 | 1363
35135355 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.057008 | 0.057008 | 0 | 0.057008 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | PLACERVILLE 2106935216 | 904
35244112 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Garden Valley | EL DORADO |  |  | PLACERVILLE 21069712 | 1646
35225543 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1858 | 0.1858 | 0 | 0.1858 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Bakersfield | KERN |  |  | POSO MOUNTAIN 210448268 | 402
35244086 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA |  |  | PUEBLO 2102792 | 951
35253133 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  |  | REDBUD 1101323962 | 423
35244102 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  |  | REDBUD 1101708166 | 345
35208096 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0.20663 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  |  | REDBUD 1101708166 | 345
35225467 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0.023674 | 0 | 0 | CC | Region 4 - Central Coast | Watsonville | SANTA CRUZ |  |  | ROB ROY 210410298 | 2387
35224942 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.010417 | 0.010417 | 0 | 0 | 0.010417 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO |  |  | SAN LUIS OBISPO 1101483444 | 2146
35225006 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050947 | 0.050947 | 0 | 0.050947 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO |  |  | SAN LUIS OBISPO 1107V02 | 1317
35225004 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO |  |  | SAN LUIS OBISPO 1107V02 | 1317
35225423 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.0058712 | 0.0058712 | 0 | 0 | 0.0058712 | 0 | 0 | LP | Region 4 - Central Coast | San Ardo | MONTEREY |  |  | SAN MIGUEL 1106605393 | 469
35120413 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Fairfax | MARIN |  |  | SAN RAFAEL 1108516 | 1837
35083913 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | MI | Region 3 - Bay Area | Castro Valley | ALAMEDA |  |  | SAN RAMON 2108CB | 1092
35215883 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0.10303 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | FRESNO |  |  | SAND CREEK 110345190 | 195
35262347 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0.069318 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | FRESNO |  |  | SAND CREEK 110345190 | 195
35221706 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.035795 | 0.035795 | 0 | 0.035795 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Badger | TULARE |  |  | SAND CREEK 11037110 | 636
35221671 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048864 | 0.048864 | 0 | 0.048864 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Woodlake | TULARE |  |  | SAND CREEK 11037110 | 636
35221646 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Woodlake | TULARE |  |  | SAND CREEK 11037110 | 636
35083879 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Orange Cove | TULARE |  |  | SAND CREEK 1103CB | 337
35225003 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.015909 | 0.015909 | 0 | 0.015909 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Arroyo Grande | SAN LUIS OBISPO |  |  | SANTA MARIA 1108M80 | 1109
31323810 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA |  |  | SANTA ROSA A 1104991788 | 3369
35224441 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.19697 | 0.19697 | 0 | 0.19697 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA |  |  | SANTA YNEZ 1104Y66 | 153
35275478 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0.15852 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | SANTA CLARA |  |  | SARATOGA 1107167792 | 2354
35150987 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara |  |  | SARATOGA 1107413816 | 2145
35221770 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | SANTA CLARA |  |  | SARATOGA 1107LC12 | 2627
35207979 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 110132726 | 2201
35205036 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.051326 | 0.051326 | 0 | 0.051326 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax |  |  |  | SHADY GLEN 110151696 | 1581
35273069 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.20947 | 0.20947 | 0 | 0 | 0.20947 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA |  |  | SHADY GLEN 11022232 | 2022
35205038 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.10227 | 0.10227 | 0 | 0 | 0.10227 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | SHADY GLEN 1102CB | 1829
35083743 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.039394 | 0.039394 | 0 | 0.039394 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Clovis | Fresno |  |  | SHEPHERD 2111707358 | 247
35205118 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Rescue | EL DORADO |  |  | SHINGLE SPRINGS 210519522 | 240
35250938 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.22557 | 0.22557 | 0 | 0 | 0.22557 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 210851476 | 424
35106410 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042803 | 0.042803 | 0 | 0.042803 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 2108CB | 2298
35208079 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0.15057 | 0 | 0 | SI | Region 2 - North East | Lotus | EL DORADO |  |  | SHINGLE SPRINGS 210911092 | 2116
35244173 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | SHINGLE SPRINGS 210911092 | 2116
35081139 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15246 | 0.15246 | 0 | 0.15246 | 0 | 0 | 0 | SI | Region 2 - North East | Rescue |  |  |  | SHINGLE SPRINGS 21092679 | 578
35207972 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO |  |  | SHINGLE SPRINGS 21099372 | 227
35211743 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO |  |  | SHINGLE SPRINGS 2109CB | 1240
35211237 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA |  |  | SILVERADO 210234959 | 579
35223207 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | San Bruno | SAN MATEO |  |  | SNEATH LANE 1106CB | 2588
35275477 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.043561 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soledad | MONTEREY |  |  | SOLEDAD 2102955138 | 623
35223204 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Sonoma | SONOMA |  |  | SONOMA 1105229588 | 720
35211234 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15928 | 0.15928 | 0 | 0.15928 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | PLACER |  |  | SPAULDING 1101578852 | 1563
35277146 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.13598 | 0.13598 | 0 | 0 | 0.13598 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | TUOLUMNE |  |  | SPRING GAP 17029690 | 2788
35221765 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | STANISLAUS 170237278 | 2810
35275962 |  | Idle Facilities | 2BF | PEND | Permitting/Dependency | 0 | 0 | 0.0056818 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 11011320 | 1828
35177215 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1892 | 0.1892 | 0 | 0.1892 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta |  |  | STILLWATER 11011320 | 1828
35204831 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16439 | 0.16439 | 0 | 0.16439 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta |  |  | STILLWATER 1101CB | 1737
35204830 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045833 | 0.045833 | 0 | 0 | 0.045833 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 11021466 | 1251
35211694 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA |  |  | STILLWATER 11021466 | 1251
35204820 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.058523 | 0.058523 | 0 | 0.058523 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta |  |  | STILLWATER 11021644 | 628
35199323 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.24072 | 0.24072 | 0 | 0.24072 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Mount Hamilton |  |  |  | SWIFT 2110XR254 | 1228
35207810 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.1678 | 0.1678 | 0 | 0 | 0.1678 | 0 | 0 | NV | Region 2 - North East | Chico | BUTTE |  |  | SYCAMORE CREEK 11112014 | 1137
35221199 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Chico | BUTTE |  |  | SYCAMORE CREEK 11112014 | 1137
35244018 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Norden | PLACER |  |  | TAMARACK 1101CB | 2630
35083773 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | TUOLUMNE |  |  | TAR FLAT 0401CB | 3142
35083737 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.80947 | 0.80947 | 0 | 0.80947 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN |  |  | TEJON 11023751 | 691
35083733 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN |  |  | TEJON 1102732836 | 583
35083812 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.045076 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN |  |  | TEJON 1102732836 | 583
35135297 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.098864 | 0.098864 | 0 | 0.098864 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Margarita | SAN LUIS OBISPO |  |  | TEMPLETON 2113A12 | 133
35225409 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1072 | 0.1072 | 0 | 0.1072 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Templeton | SAN LUIS OBISPO |  |  | TEMPLETON 2113A70 | 955
35079416 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.055492 | 0.055492 | 0 | 0.055492 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Creston | SAN LUIS OBISPO |  |  | TEMPLETON 2113R82 | 864
35217692 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA |  |  | TYLER 110585132 | 383
35204877 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | UKIAH 1113548420 | 1369
35038557 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | UKIAH 11151216 | 1030
35151005 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0.28636 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE |  |  | UPPER LAKE 1101412 | 259
31157088 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.24053 | 0.24053 | 0 | 0 | 0.24053 | 0 | 0 | SA | Region 2 - North East | Fairfield | SOLANO |  |  | VACAVILLE 11046542 | 42
35208021 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.20739 | 0.20739 | 0 | 0 | 0.20739 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 11088762 | 64
31156970 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO |  |  | VACAVILLE 111113652 | 190
35207931 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.042424 | 0.042424 | 0 | 0.042424 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano |  |  | VACAVILLE 1111CB | 500
35083893 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0.067424 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA |  |  | VASCO 1102MR176 | 324
35083687 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050189 | 0.050189 | 0 | 0.050189 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA |  |  | VASCO 1102MR176 | 324
35083695 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1661 | 0.1661 | 0 | 0.1661 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda |  |  | VASCO 1102MR176 | 324
35229381 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11477 | 0.11477 | 0 | 0.11477 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Pebble Beach | MONTEREY |  |  | VIEJO 2202CB | 3216
35143764 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023485 | 0.023485 | 0 | 0 | 0.023485 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA |  |  | VOLTA 11011596 | 966
35275479 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Manton | TEHAMA |  |  | VOLTA 110180454 | 532
35205037 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.082576 | 0.082576 | 0 | 0 | 0.082576 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | WEIMAR 11012058 | 1379
35211657 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | WEIMAR 11012058 | 1379
35211297 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15682 | 0.15682 | 0 | 0 | 0.15682 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | WEIMAR 11012084 | 1801
35211671 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER |  |  | WEIMAR 11022038 | 2536
35079380 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.21951 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS |  |  | WEST POINT 11024788 | 1206
35221997 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.043561 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | WEST POINT 11024790 | 1664
35221998 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10985 | 0.10985 | 0 | 0.10985 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | WEST POINT 11024790 | 1664
35221807 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | WEST POINT 11024790 | 1664
35207962 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA |  |  | WHITMORE 11011594 | 678
35204813 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.06875 | 0.06875 | 0 | 0 | 0.06875 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA |  |  | WHITMORE 11011598 | 820
35204814 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0.21023 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA |  |  | WHITMORE 11011598 | 820
35208023 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037311 | 0.037311 | 0 | 0.037311 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | WHITMORE 11011598 | 820
35275960 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA |  |  | WHITMORE 11011598 | 820
35217667 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.43371 | 0.43371 | 0 | 0 | 0.43371 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA |  |  | WHITMORE 110145262 | 685
35204810 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA |  |  | WHITMORE 110145262 | 685
35174308 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.069697 | 0.069697 | 0 | 0.069697 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta |  |  | WHITMORE 110145262 | 685
35207963 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042992 | 0.042992 | 0 | 0.042992 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta |  |  | WHITMORE 1101CB | 1481
35207965 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA |  |  | WILDWOOD 11011576 | 1125
35038672 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013826 | 0.013826 | 0 | 0.013826 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino |  |  | WILLITS 11032500 | 782
35038671 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino |  |  | WILLITS 110337506 | 1161
35132574 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019697 | 0.019697 | 0 | 0.019697 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | MENDOCINO |  |  | WILLITS 1103968 | 1264
35038668 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino |  |  | WILLITS 1104934 | 778
35151029 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | TRINITY |  |  | WILLOW CREEK 11032936 | 1474
35149294 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.082955 | 0.082955 | 0 | 0.082955 | 0 | 0 | 0 | HB | Region 1 - North Coast | Salyer | HUMBOLDT |  |  | WILLOW CREEK 11033090 | 1598
35078722 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER |  |  | WISE 11022234 | 430
35078723 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.074432 | 0.074432 | 0 | 0.074432 | 0 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER |  |  | WISE 11022234 | 430
35242865 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | SAN MATEO |  |  | WOODSIDE 11018972 | 1376
35078735 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.062879 | 0.062879 | 0 | 0 | 0.062879 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE |  |  | WYANDOTTE 11071510 | 905
35079389 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.14015 | 0.14015 | 0 | 0.14015 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst
35083712 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.13769 | 0.13769 | 0 | 0 | 0.13769 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE
35083923 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.079167 | 0.079167 | 0 | 0.079167 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN
35149472 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.080492 | 0.080492 | 0 | 0.080492 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE
35150617 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.022727 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willow Creek | HUMBOLDT
35204864 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.053977 | 0.053977 | 0 | 0.053977 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | TEHAMA
35205115 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | SI | Region 2 - North East | Lotus | EL DORADO
35208075 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.040341 | 0.040341 | 0 | 0.040341 | 0 | 0 | 0 | SI | Region 2 - North East | North San Juan | NEVADA
35208098 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.029356 | 0.029356 | 0 | 0.029356 | 0 | 0 | 0 | HB | Region 1 - North Coast | Redway | HUMBOLDT
35209864 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.036553 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO
35211232 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | NEVADA
35211241 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.074811 | 0.074811 | 0 | 0 | 0.074811 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO
35211277 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.014394 | 0.014394 | 0 | 0.014394 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley
35221635 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.082955 | 0.082955 | 0 | 0.082955 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Clovis
35225434 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.073295 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Margarita | SAN LUIS OBISPO
35185022 |  | Other | 06I | FICL | Post-Construction | 0 | 0.41705 | 0 | 0.41705 | 0 | 0.41705 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA |  |  | ALLEGHANY 1102CB | 1700
35080162 |  | Other | 06H | CONS | In-Construction | 0 | 1.4413 | 0 | 1.4413 | 0 | 1.2462 | 0.19508 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | Mendocino |  |  | Calpella 1101CB | 1256
35094513 |  | Base SH | 08W | UNSC | Ready for Construction | 0.032576 | 1.7771 | 0 | 1.8097 | 0 | 0 | 1.8097 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras |  |  | STANISLAUS 17021804 | 2712 | Pre | Tier 3
35146106 |  | Other | 06H | DOCC | Post-Construction | 0 | 3.621 | 0 | 3.621 | 0 | 3.621 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO |  |  | SAN MIGUEL 1104N60 | 229
35297697 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.014773 | 0 | 0 | 0.014773 | 0 | 0 | 0.014773 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity |  |  | WILLOW CREEK 11032936 | 1474 | FRRB | Tier 2

## Status
SAP Status | Status
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | In-Construction | *
DOCC | Post-Construction | *
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles

## ProjectType
ProjectType | Description
CWSP 2022-2023 | Community Wildfire Safety Program for projects aimed for 2022-2023
ECOP | EC Tag Optimization
ECOP - Top 20% | EC Tag Optimization in the top 20% of the 2021 risk model
FRRB - OH – 2021 | Fire Rebuild - Overhead Hardening
FRRB - REMG – 2021 | Fire Rebuild - Remote Grid Projects
FRRB - UG – 2021 | Fire Rebuild - Underground Hardening
PRE | Projects that had poles in the ground and construction had begun, based on 2018 risk model
PSPS - Community Resiliency | Public Safety Power Shutoff projects
PSPS – Scoped | Public Safety Power Shutoff projects that had been scoped, based on 2018 risk model
PSS Approved | Public Safety Specialists approved projects
Remote Grid | Remote Grid projects
Remote Grid Pilot | Remote Grid projects part of the Pilot program
Storm Rebuild | Storm Rebuild projects
Top 20% MAVF CPZ | Top 20% of Multi-Attribute Value Function Circuit Protection Zones based on the 2021 risk model
Top 250 miles | Top 250 miles based on the 2021 risk model
Top 50 Miles | Top 50 miles based on the 2021 risk model