## Table 12
Utility |  | Pacific Gas & Electric Company | Notes:
Table No. |  | 12 | Risk-Spend-Efficiency (RSE) is defined as "An estimate of the cost-effectiveness of initiative, calculated by dividing the mitigation risk reduction benefit by the mitigation cost estimate based on the full set of risk reduction benefits estimated from the incurred costs."
Date Modified |  | 2022-06-27 | CAPEX = Capital expenditure; OPEX = Operating expenditure. In future submissions update planned spend, line miles treated, RSE, etc. with updated projections and actuals. Additional instructions can be found in QR information.
[23 empty] | Actual | [35 empty] | Projected
[23 empty] | CAPEX ($ thousands) |  |  | OPEX ($ thousands) |  |  | Line miles treated / Units | [5 empty] | CAPEX ($ thousands) |  |  | OPEX ($ thousands) |  |  | Line miles treated / Units | [5 empty] | CAPEX ($ thousands) |  |  | OPEX ($ thousands) |  |  | Line miles to be treated / Units | [5 empty] | CAPEX ($ thousands) |  |  | OPEX ($ thousands) |  |  | Line miles to be treated / Units | [5 empty] | CAPEX ($ thousands) |  |  | OPEX ($ thousands) |  |  | Line miles to be treated / Units |  |  |  |  | Line miles to be treated
|  |  |  | 2021 ALIGNMENT (2021 WMP - Revised: June 3, 2021) |  | 2022 Alignment (2022 WMP: February 25, 2022) | [16 empty] | Territory | HFTD | HFRA | Territory | HFTD | HFRA | Line Miles - Territory | Line Miles - HFTD | Alternative units (unit of measure) | Units - Territory | Units - HFTD | 2019 Comments: Line Miles Treated / Units | Territory | HFTD | HFRA | Territory | HFTD | HFRA | Line Miles - Territory | Line Miles - HFTD | Alternative units (unit of measure) | Units - Territory | Units - HFTD | 2020 Comments Line Miles Treated / Units | Territory | HFTD | HFRA | Territory | HFTD | HFRA | Line Miles - Territory | Line Miles - HFTD | Alternative units (unit of measure) | Units - Territory | Units - HFTD | 2021 Comments Line Miles Treated / Units | Territory | HFTD | HFRA | Territory | HFTD | HFRA | Line Miles - Territory | Line Miles - HFTD | Alternative units (unit of measure) | Units - Territory | Units - HFTD | 2022 Comments Line Miles Treated / Units | Territory | HFTD | HFRA | Territory | HFTD | HFRA | Line Miles - Territory | Line Miles - HFTD | Alternative units (unit of measure) | Units - Territory | Units - HFTD | 2023 Comments Line Miles Treated / Units
Metric type | WMP Table # / Category | WMP Initiative # | Initative Activity | Initiative number | Initiative name | Initiative number | Initiative name | Change in Initiative scope from 2021 to 2022 | Primary driver targeted | Secondary driver targeted | Year initiated | Estimated RSE territory-wide | Estimated RSE in non-HFTD region | Estimated RSE in HFTD Zone 1 | Estimated RSE in HFTD Tier 2 | Estimated RSE in HFTD Tier 3 | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compliance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments on RSE | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Other | Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 7.3.1.1 | 7.3.1.1 A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 7.3.1.1 | 7.3.1.1 A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | All Drivers | All Drivers | 2018 | 2227.7163 | 0 | 42.3222 | 2600.8227 | 1271.2675 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 100.3542 | 31.3384 | 31.7915 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Program applies to all T&D assets in HFTD | 1039.5227 | 324.6196 | 329.3132 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | N/A - Risk Analysis activities generally performed by internal electric operations staff with costs not tracked separately | 1006.5347 | 314.3182 | 318.8629 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 909.8101 | 284.1132 | 288.2212 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 1061.1252 | 331.3655 | 336.1567 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Risk Assessment & Mapping | 7.3.1.2 | Climate-driven risk map and modeling based on various relevant weather scenarios | 7.3.1.2 | 7.3.1.2 Climate-driven risk map and modelling based on various relevant weather scenarios | 7.3.1.2 | 7.3.1.2 Climate-driven risk map and modeling based on various relevant weather scenarios |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 770 | 241.8156 | 245.312 | N/A | N/A |  | 0 | 0 | N/A - Climate driven risk mapping is an aspect of weather and fire modeling, captured in Table 22, Initiative 4-1, Forecast of a fire risk index, fire potential index, or similar | 0 | 0 | 0 | 1623 | 509.697 | 517.0667 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 1572 | 493.6807 | 500.8188 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 1297 | 407.3179 | 413.2073 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Risk Assessment & Mapping | 7.3.1.3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 7.3.1.3 | 7.3.1.3 Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 7.3.1.3 | 7.3.1.3 Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | All Drivers | All Drivers | 2018 | 2227.7163 | 0 | 42.3222 | 2600.8227 | 1271.2675 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 100.3542 | 31.3384 | 31.7915 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Program applies to all T&D assets in HFTD | 1039.5227 | 324.6196 | 329.3132 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | N/A - Circuit based ignition probabilities and risk analysis activities generally performed by internal electric operations staff with costs not tracked separately | 1006.5347 | 314.3182 | 318.8629 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 909.8101 | 284.1132 | 288.2212 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 1061.1252 | 331.3655 | 336.1567 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Risk Assessment & Mapping | 7.3.1.4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 7.3.1.4 | 7.3.1.4 Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 7.3.1.4 | 7.3.1.4 Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 23.1064 | 7.2156 | 7.3199 | N/A | N/A |  | 0 | 0 | Program applies to all T&D assets in HFTD | 0 | 0 | 0 | 15.5357 | 4.8514 | 4.9216 | N/A | N/A |  | 0 | 0 | N/A - Risk Analysis activities generally performed by internal electric operations staff with costs not tracked separately | 0 | 0 | 0 | 171.1056 | 53.432 | 54.2068 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 168.4643 | 52.608 | 53.3708 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 173.5182 | 54.186 | 54.9717 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Risk Assessment & Mapping | 7.3.1.5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 7.3.1.5 | 7.3.1.5 Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 7.3.1.5 | 7.3.1.5 Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | N/A - Foundational | N/A - Foundational | 2019 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2100 | 2100 | 2130.3638 | N/A | N/A |  | 0 | 0 | Program applies to all T&D assets in HFTD | 0 | 0 | 0 | 3000 | 3000 | 3043.3768 | N/A | N/A |  | 0 | 0 | N/A - 5.3.1.5 is an aspect of weather and fire modeling, captured in Table 22, Initiative 4-1, Forecast of a fire risk index, fire potential index, or similar | 1194 | 1194 | 1211.264 | 3800 | 3800 | 3854.9439 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 1194 | 1194 | 1211.264 | 3200 | 3200 | 3246.2686 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 1229.82 | 1229.82 | 1247.6019 | 3296 | 3296 | 3343.6566 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Risk Assessment & Mapping | 7.3.1.6 | Weather-Driven Risk Map and Modelling Based on Various Relevant Weather Scenarios | 7.3.1.6 | 7.3.1.6 Weather-Driven Risk Map and Modelling Based on Various Relevant Weather Scenarios | 7.3.1.6 - REMOVE | Removed in 2022 WMP: 7.3.1.6 Weather-Driven Risk Map and Modelling Based on Various Relevant Weather Scenarios | Removed from 2022 WMP | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | N/A - 7.3.1.6 Weather-Driven Risk Map and Modelling Based on Various Relevant Weather Scenarios not in Sept 9 2020 filing | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Mapping activities do not specifically address line miles
Other | Situational Awareness & Forecasting | 7.3.2.1.1 | Advanced weather monitoring and weather stations, Numerical Weather Prediction | 7.3.2.1.1 | 7.3.2.1.1 Advanced weather monitoring and weather stations, Numerical Weather Prediction | 7.3.2.1.1 | 7.3.2.1.1 Advanced weather monitoring and weather stations, Numerical Weather Prediction |  | Consequence - PSPS | No other consequences reflected | <2018 | 189.3603 | 0 | 189.3603 | 189.3603 | 189.3603 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 650.8331 | 650.8331 | 660.2435 | N/A | N/A |  | 0 | 0 | N/A - 7.3.2.1.1 Advanced weather monitoring and weather stations, Numerical Weather Prediction not in Sept 9 2020 filing | 0 | 0 | 0 | 718.9587 | 718.9587 | 729.354 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 789.075 | 789.075 | 800.4842 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 806.8874 | 806.8874 | 818.5541 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.1.2 | Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling | 7.3.2.1.2 | 7.3.2.1.2 Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling | 7.3.2.1.2 | 7.3.2.1.2 Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling |  | Consequence - PSPS | No other consequences reflected | 2018 | 74.9475 | 0 | 74.9475 | 74.9475 | 74.9475 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 413.3169 | 129.8006 | 131.6774 | N/A | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 571.1528 | 179.3684 | 181.9619 | N/A | N/A |  | 0 | 0 | N/A - 7.3.2.1.2 Advanced weather monitoring and weather stations, Fuel Moisture Sampling and Modeling not in Sept 9 2020 filing | 0 | 0 | 0 | 571.796 | 179.5704 | 182.1668 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 598.0965 | 187.8299 | 190.5458 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 616.6032 | 193.6419 | 196.4418 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.1.3 | Advanced weather monitoring and weather stations, Weather Stations | 7.3.2.1.3 | 7.3.2.1.3 Advanced weather monitoring and weather stations, Weather Stations | 7.3.2.1.3 | 7.3.2.1.3 Advanced weather monitoring and weather stations, Weather Stations |  | Consequence - PSPS | No other consequences reflected | 2018 | 21.6596 | 0 | 21.6596 | 21.6596 | 21.6596 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 6933.6763 | 5699.898 | 5782.3124 | 605.6783 | 497.9039 | 505.1031 | N/A | N/A | # of Weather Stations | 627 | 515.4316 | Assumption is that 1,300 weather stations will cover all of T2 and T3. Annual "miles treated" is calculated as # of weather stations/ 1,300 * total T2 and T3 circuit miles. Note that 200 weather stations were installed in 2018 as well. | 8314.9397 | 6835.3793 | 6934.2116 | 111.2093 | 91.4207 | 92.7425 | 9623.5908 | 9623.5908 | # of Weather Stations | 1005 | 826.1703 | Assumption that 1,300 for the entire program will cover all of T2 and T3. Equation is # of weather stations/ 1,300 * total T1 Z1 T2 and T3 circuit miles. We do have tier 1 weather stations so including all line miles in territory in formula. | 7719.7701 | 6346.1142 | 6437.8722 | 145.2292 | 119.3871 | 121.1133 | N/A | N/A | # of Weather Stations | 1313 | 1079.3648 | Specific units are a preferable way to report progress for this initiative | 6181.3442 | 5081.4358 | 5154.9079 | 1595.2679 | 1311.4059 | 1330.3674 | N/A | N/A | # of Weather Stations | 1650 | 1356.399 | Specific units are a preferable way to report progress for this initiative | 3156.22 | 2594.6022 | 2632.1174 | 1714.7949 | 1409.6643 | 1430.0466 | N/A | N/A | # of Weather Stations | 1550 | 1274.193 | Specific units are a preferable way to report progress for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.1.4 | Advanced weather monitoring and weather stations, Wildfire Cameras | 7.3.2.1.4 | 7.3.2.1.4 Advanced weather monitoring and weather stations, Wildfire Cameras | 7.3.2.1.4 | 7.3.2.1.4 Advanced weather monitoring and weather stations, Wildfire Cameras |  | All Drivers | All Drivers | 2018 | 122.8516 | 0 | 7.9164 | 140.5841 | 75.2795 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2063.3694 | 1748.5046 | 1773.7861 | N/A | N/A | # of HD Cameras | 124 | 105.0779 | Assumption is that 600 cameras for the entire program will cover all of Tier 2 and Tier 3. Therefore annual "miles treated" is calculated as # of cameras/600 * total T2 and T3 circuit miles. | 0 | 0 | 0 | 6955.7637 | 5894.3323 | 5979.558 | 11148.12 | 11148.12 | # of HD Cameras | 216 | 183.039 | Assumption is that 600 for the entire program will cover all HFTD. Equation is # of cameras/600 * total T+D HFTD circuit miles. | 0 | 0 | 0 | 8050.7839 | 6822.2552 | 6920.8977 | N/A | N/A | # of HD Cameras | 153 | 129.6526 | Specific units are a preferable way to report progress for this initiative | 0 | 0 | 0 | 11211.216 | 9500.4135 | 9637.7794 | N/A | N/A | # of HD Cameras | 133 | 112.7045 | Specific units are a preferable way to report progress for this initiative | 0 | 0 | 0 | 8002.0207 | 6780.9331 | 6878.9781 | N/A | N/A | # of HD Cameras | 10 | 8.474 | Specific units are a preferable way to report progress for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.1.5 | Advanced weather monitoring and weather stations, Fire Detection & Alerting | 7.3.2.1.5 | 7.3.2.1.5 Advanced weather monitoring and weather stations, Fire Detection & Alerting | 7.3.2.1.5 | 7.3.2.1.5 Advanced weather monitoring and weather stations, Fire Detection & Alerting |  | All Drivers | All Drivers | 2019 | 175.9289 | 2.5211 | 35.7727 | 635.3427 | 340.2102 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Program applies to all T&D assets in HFTD | 0 | 0 | 0 | 0 | 0 | 0 | 81004 | 25439 |  | 0 | 0 | Program applies to all tiers in Distribution. Assumption is this program treats all miles. | 0 | 0 | 0 | 195.207 | 61.304 | 62.1904 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 341.3279 | 107.1927 | 108.7426 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 351.8894 | 110.5095 | 112.1074 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.1.6 | Advanced weather monitoring and weather stations, Other Meteorology Tools and Upgrades | 7.3.2.1.6 | 7.3.2.1.6 Advanced weather monitoring and weather stations, Other Meteorology Tools and Upgrades | 7.3.2.1.6 | 7.3.2.1.6 Advanced weather monitoring and weather stations, Other Meteorology Tools and Upgrades |  | N/A - Foundational | N/A - Foundational | 2019 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 289.3218 | 90.8604 | 92.1742 | N/A | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 887.9318 | 278.8516 | 282.8835 | N/A | N/A |  | 0 | 0 | N/A - 7.3.2.1.6, Other Meteorology Tools and Upgrades not in Sept 9 2020 filing | 0 | 0 | 0 | 939.4762 | 295.039 | 299.3049 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 1020 | 320.3271 | 324.9587 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 1050.6 | 329.937 | 334.7075 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.2.1 | Continuous monitoring sensors, Electric Transmission SEL T400L | 7.3.2.2.1 | 7.3.2.2.1 Continuous monitoring sensors, Electric Transmission SEL T400L | No 2022 Activity- 7.3.2.2.1 | No 2022 Activity - 7.3.2.2.1 Continuous monitoring sensors, Electric Transmission SEL T400L | There are no activities in place for 2022, however, any available data (e.g. financials/line miles/units) is provided for previous years. | N/A - Pilot | N/A - Pilot | 2019 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 39627.9794 | 12062.3022 | 12509.2308 | 0 | 0 | 0 | N/A | N/A | Relays | 0 | 0 | UNITS SHOLD BE AVAILABLE FOR THIS PROGRAM | 47015.4914 | 14310.9761 | 14841.2219 | 0 | 0 | 0 | N/A | N/A | Relays | 0 | 0 | UNITS SHOLD BE AVAILABLE FOR THIS PROGRAM | 35312.5456 | 10748.7337 | 11146.9924 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | This program will not continue in 2022 and beyond | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | This program will not continue in 2022 and beyond
Other | Situational Awareness & Forecasting | 7.3.2.2.2 | Continuous monitoring sensors, SmartMeter™ Partial Voltage Detection (Formerly Known as Enhanced Wires Down Detection) | 7.3.2.2.2 | 7.3.2.2.2 Continuous monitoring sensors, SmartMeter™ Partial Voltage Detection (Formerly Known as Enhanced Wires Down Detection) | No 2022 Activity- 7.3.2.2.2 | No 2022 Activity - 7.3.2.2.2 Continuous monitoring sensors, SmartMeter™ Partial Voltage Detection (Formerly Known as Enhanced Wires Down Detection) | There are no activities in place for 2022, however, any available data (e.g. financials/line miles/units) is provided for previous years. | Equipment Failure | No other drivers addressed | 2019 | N/A | 3.9558 | 1602.038 | 1602.038 | 1602.038 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 390.5367 | 390.5367 | 396.1835 | 0.17818 | 0.17818 | 0.18076 | N/A | N/A | SmartMeters | 0 | 0 | UNITS SHOLD BE AVAILABLE FOR THIS PROGRAM | 1215.5724 | 1215.5724 | 1233.1483 | 3.6572 | 3.6572 | 3.7101 | N/A | N/A | SmartMeters | 0 | 0 | UNITS SHOLD BE AVAILABLE FOR THIS PROGRAM | 607.6568 | 607.6568 | 616.4428 | 2.1919 | 2.1919 | 2.2236 | N/A | N/A | SmartMeters enabled | 0 | 0 | UNITS SHOULD BE AVAILABLE FOR THIS PROGRAM | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Program is operational and no new units are planned | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Program is operational and no new units are planned
Other | Situational Awareness & Forecasting | 7.3.2.2.3 | Continuous monitoring sensors, Distribution Fault Anticipation Technology and Early Fault Detection | 7.3.2.2.3 | 7.3.2.2.3 Continuous monitoring sensors, Distribution Fault Anticipation Technology and Early Fault Detection | 7.3.2.2.3 | 7.3.2.2.3 Continuous monitoring sensors, Distribution Fault Anticipation Technology and Early Fault Detection |  | Equipment / facility failure, Vegetation Contact, Contact from object, Other, Vandalism / Theft, | No other drivers addressed | 2019 | 4.5183 | 0 | 0.14208 | 5.3571 | 2.3672 | WMCE | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 815.6914 | 815.6914 | 827.4854 | N/A | N/A | # of DFA Sensors | 7.5 | 7.5 | UNITS SHOLD BE AVAILABLE FOR THIS PROGRAM | 0 | 0 | 0 | 338.2566 | 338.2566 | 343.1475 | N/A | N/A | # of DFA Sensors | 1 | 1 | Actuals were for the two circuits completed in 2020 for the pilot | 5274.7005 | 5274.7005 | 5350.967 | 158.6605 | 158.6605 | 160.9545 | N/A | N/A | # of DFA Sensors | 16 | 16 | Units are the appropriate measure for this program | 14579.4178 | 14579.4178 | 14790.2206 | 2573.4993 | 2573.4993 | 2610.7094 | N/A | N/A | # of DFA Sensors | 42 | 42 | Narrative states 40 DFA sensors and 2 EFD circuits | 13965.4892 | 13965.4892 | 14167.4153 | 3425.8093 | 3425.8093 | 3475.3429 | N/A | N/A | # of DFA Sensors | 43 | 43 | DFA Sensors and EFD Circuits
Other | Situational Awareness & Forecasting | 7.3.2.2.4 | Continuous monitoring sensors, Sensor IQ | 7.3.2.2.4 | 7.3.2.2.4 Continuous monitoring sensors, Sensor IQ | 7.3.2.2.4 | 7.3.2.2.4 Continuous monitoring sensors, Sensor IQ |  | N/A - Foundational | N/A - Foundational | 2020 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | WMCE | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 29.212 | 9.2923 | 9.4267 | 23.5013 | 7.4758 | 7.5839 | N/A | N/A |  | 0 | 0 | No specific targets for this program | -30.0251 | -9.551 | -9.6891 | 1870.7814 | 595.0956 | 603.7 | N/A | N/A |  | 0 | 0 | No specific targets for this program | 0.01217 | 0.0038713 | 0.0039273 | 1247.9865 | 396.9845 | 402.7245 | N/A | N/A | SmartMeters enabled | 551 | 175.2731 | Not sure what these units are. Narrative describes SmartMeters as the units | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets | 10507 | 3342.2767 | 3390.6025 | 3676.2309 | 1169.4091 | 1186.3175 | N/A | N/A | N/A | 0 | 0 | No specific targets
Other | Situational Awareness & Forecasting | 7.3.2.2.5 | Continuous monitoring sensors, Line Sensor Devices | 7.3.2.2.5 | 7.3.2.2.5 Continuous monitoring sensors, Line Sensor Devices | 7.3.2.2.5 | 7.3.2.2.5 Continuous monitoring sensors, Line Sensor Devices |  | All Drivers, All Consequences | All Drivers, All Consequences | 2019 | 72.5033 | 0 | 1.4867 | 84.8118 | 40.9492 | N/A | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 2764.5835 | 2764.5835 | 2804.5565 | 455.1574 | 455.1574 | 461.7385 | N/A | N/A | # of Circuits | 14 | 14 | Units should be circuits | 2720.7288 | 2720.7288 | 2760.0676 | 924.254 | 924.254 | 937.6178 | N/A | N/A | # of Circuits | 38 | 38 | Units should be circuits | 3234.4113 | 3234.4113 | 3281.1774 | 1115.8787 | 1115.8787 | 1132.0131 | N/A | N/A | # of Circuits | 67 | 67 | Units should be circuits | 7812.786 | 7812.786 | 7925.7505 | 0 | 0 | 0 | N/A | N/A | # of Circuits | 40 | 40 | Units should be circuits | 8005.572 | 8005.572 | 8121.324 | 0 | 0 | 0 | N/A | N/A | # of Circuits | 40 | 40 | Units should be circuits
Other | Situational Awareness & Forecasting | 7.3.2.2.6 | Continuous monitoring sensors, Distribution Arcing Fault Signature Library | 7.3.2.2.6 | 7.3.2.2.6 Continuous monitoring sensors, Distribution Arcing Fault Signature Library | 7.3.2.2.6 | 7.3.2.2.6 Continuous monitoring sensors, Distribution Arcing Fault Signature Library |  | N/A - Pilot | N/A - Pilot | 2020 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | WMCE | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A |  | 0 | 0 | 2020 cost is anticipated to be 100% reimbursable as part of joint research project with national laboratories | 0 | 0 | 0 | 563.4847 | 563.4847 | 571.6321 | N/A | N/A | N/A | 0 | 0 | Since this is purely an R&D project, the initial scope of deployment will be on a single circuit that has a high occurrence of faults with a wide range of causes. The circuit includes sections that are within the Tier 2 and Tier 3 HFTD areas. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.2.7 | Continuous monitoring sensors, DTS FAST | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.2.2.7 | 7.3.2.2.6 Continuous monitoring sensors, DTS FAST | Added new sub-initiative in 2022 | N/A - Pilot | N/A - Pilot | 2020 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot |  |  | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 9.08 | 9.08 | 9.2113 |  |  |  | 0 | 0 |  | 4220.2594 | 4220.2594 | 4281.2798 | 137.1107 | 137.1107 | 139.0932 |  |  |  | 0 | 0 |  | 19452 | 19452 | 19733.2551 | 600 | 600 | 608.6754 |  |  |  | 0 | 0 |  | 20542.5 | 20542.5 | 20839.5226 | 800 | 800 | 811.5671 |  |  |  | 0 | 0
Other | Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment | 7.3.2.3 | 7.3.2.3 Fault indicators for detecting faults on electric lines and equipment | 7.3.2.3 | 7.3.2.3 Fault indicators for detecting faults on electric lines and equipment |  | All Drivers, All Consequences | All Drivers, All Consequences | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 84.5536 | 26.5537 | 26.9377 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Program applies to all Distribution lines in HFTD. | 52.5431 | 16.501 | 16.7395 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | We have not yet determined a long-term plan for fault indicators and their detection of faults on electrical lines and equipment. Long-term plan milestones are still under development with Electric Operations and Asset Management as we evaluate our current protection and automation standards/initiatives. | 19.6899 | 6.1835 | 6.2729 | 0 | 0 | 0 | N/A | N/A | Fault Indicators | 0 | 0 | Fault Indicators would be the appropriate measure. However | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Fault Indicators | 0 | 0 | Fault Indicators would be the appropriate measure. However | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Fault Indicators | 0 | 0 | Fault Indicators would be the appropriate measure. However
Other | Situational Awareness & Forecasting | 7.3.2.4 | Forecast of a fire risk index, fire potential index, or similar | 7.3.2.4 | 7.3.2.4 Forecast of a fire risk index, fire potential index, or similar | 7.3.2.4 | 7.3.2.4 Forecast of a fire risk index, fire potential index, or similar |  | Consequence - PSPS | No other consequences reflected | <2018 | 49.965 | 0 | 49.965 | 49.965 | 49.965 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 198.2271 | 198.2271 | 201.0932 | 1416.3562 | 1416.3562 | 1436.8352 | N/A | N/A | N/A | 0 | 0 | Program applies to all T&D assets in HFTD | 898.8112 | 898.8112 | 911.8071 | 1833.7554 | 1833.7554 | 1860.2695 | N/A | N/A | N/A | 0 | 0 | Program applies to HFTD | 14.032 | 14.032 | 14.2349 | 1080.0589 | 1080.0589 | 1095.6754 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 1867.1707 | 1867.1707 | 1894.168 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative | 0 | 0 | 0 | 1927.7466 | 1927.7466 | 1955.6198 | N/A | N/A | N/A | 0 | 0 | Line miles, nor units are appropriate measures for this initiative
Other | Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 7.3.2.5 | 7.3.2.5 Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 7.3.2.5 | 7.3.2.5 Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | N/A | N/A | 2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 128.4705 | 128.4705 | 130.3281 | 2583.6528 | 2583.6528 | 2621.0097 |  | N/A |  | 0 | 0 | Line miles is not an applicable metric | 250.785 | 250.785 | 254.4111 | 3068.3805 | 3068.3805 | 3112.746 | N/A | N/A |  | 0 | 0 | Line miles treated is not an appropriate metric to measure this initiative. | 11.7078 | 11.7078 | 11.877 | 3422.4025 | 3422.4025 | 3471.8868 |  |  |  | 0 | 0 |  | 230.0126 | 230.0126 | 233.3383 | 4841.3383 | 4841.3383 | 4911.3389 |  |  |  | 0 | 0 |  | 47.8332 | 47.8332 | 48.5248 | 5027.7593 | 5027.7593 | 5100.4553 |  |  |  | 0 | 0
Other | Situational Awareness & Forecasting | 7.3.2.6 | Weather forecasting and estimating impacts on electric lines and equipment | 7.3.2.6 | 7.3.2.6 Weather forecasting and estimating impacts on electric lines and equipment | 7.3.2.6 | 7.3.2.6 Weather forecasting and estimating impacts on electric lines and equipment |  | Consequence - PSPS | No other consequences reflected | <2018 | 140.251 | 0 | 140.251 | 140.251 | 140.251 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Not a unitized program - but rather personnel on hand | 0 | 0 | 0 | 488.1249 | 488.1249 | 495.1826 | N/A | N/A | N/A | 0 | 0 | Not a unitized program - but rather personnel on hand | 975.1272 | 975.1272 | 989.2265 | 718.7264 | 718.7264 | 729.1185 | N/A | N/A | N/A | 0 | 0 | Not a unitized program - but rather personnel on hand | 1022.9234 | 1022.9234 | 1037.7137 | 1107.8211 | 1107.8211 | 1123.839 | N/A | N/A | N/A | 0 | 0 | Not a unitized program - but rather personnel on hand | 1045.0294 | 1045.0294 | 1060.1394 | 1030.3787 | 1030.3787 | 1045.2769 | N/A | N/A | N/A | 0 | 0 | Not a unitized program - but rather personnel on hand
Other | Situational Awareness & Forecasting | 7.3.2.7 | Other, Wildfire Safety Operations Center (WSOC) | 7.3.2.7 | 7.3.2.7 Other, Wildfire Safety Operations Center (WSOC) | 7.3.2.7 | 7.3.2.7 Other, Wildfire Safety Operations Center (WSOC) |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 2120.9695 | 2120.9695 | 2151.6364 | 5678.2011 | 5678.2011 | 5760.3018 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | -34.0887 | -34.0887 | -34.5816 | 4117.327 | 4117.327 | 4176.8591 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 140.5808 | 140.5808 | 142.6135 | 4847.3841 | 4847.3841 | 4917.4721 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 124.6707 | 124.6707 | 126.4733 | 6981.0461 | 6981.0461 | 7081.9845 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 0 | 0 | 0 | 7138.6341 | 7138.6341 | 7241.8511 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized
Other | Situational Awareness & Forecasting | 7.3.2.8 | Other, Meteorology Analytics/Operations Center | 7.3.2.8 | 7.3.2.8 Other, Meteorology Analytics/Operations Center | No 2022 Activity - 7.3.2.8 | No 2022 Activity - 7.3.2.8 Other, Meteorology Analytics/Operations Center | There are no activities in place for 2022, however, any available data (e.g. financials/line miles/units) is provided for previous years. | N/A - Foundational | N/A - Foundational | 2020 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - to be removed, no financials after 2021 | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 0 | 0 | 0 | 920.104 | 920.104 | 933.4077 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 0 | 0 | 0 | 49.4055 | 49.4055 | 50.1198 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Analytical models do not directly address line miles and are not unitized
Grid hardening | Grid Design & System Hardening | 7.3.3.1 | Capacitor maintenance and replacement program | 7.3.3.1 | 7.3.3.1 Capacitor maintenance and replacement program | 7.3.3.1 | 7.3.3.1 Capacitor maintenance and replacement program |  | Equipment / facility failure | No other drivers addressed | <2018 | 238.1338 | 2.6423 |  | 1033.92 | 202.7749 | 2020 GRC | N/A | In Compliance | GO 95 |  | RSEs presented are for the year 2022. | 6426.3172 | 2018.1606 | 2047.3411 | 2034.6632 | 638.9783 | 648.2172 | 81004 | 25439 |  | 619.6637 | 194.603 | Maintained or reduced trend in equipment failures (outages or ignitions) associated with Capacitors for entire service territory annually | 8246.664 | 2589.8337 | 2627.2799 | 2383.3797 | 748.4914 | 759.3138 | 81004 | 25439 |  | 614.987 | 193.1343 | Maintained or reduced trend in equipment failures (outages or ignitions) associated with Capacitors for entire service territory annually | 10931.5542 | 3433.0133 | 3482.651 | 2959.1761 | 929.3181 | 942.755 | 81004 | 25439 |  | 937.9619 | 294.5634 | Maintained or reduced trend in equipment failures (outages or ignitions) associated with Capacitors for entire service territory annually | 10549.2358 | 3312.9476 | 3360.8493 | 2369.2363 | 744.0497 | 754.8079 | 81004 | 25439 |  | 789.5857 | 247.9664 | Maintained or reduced trend in equipment failures (outages or ignitions) associated with Capacitors for entire service territory annually | 11964.7222 | 3757.4758 | 3811.8049 | 2436.1597 | 765.0668 | 776.1288 | 81004 | 25439 |  | 789.5624 | 247.9591 | Maintained or reduced trend in equipment failures (outages or ignitions) associated with Capacitors for entire service territory annually
Grid hardening | Grid Design & System Hardening | 7.3.3.2-D | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Distribution | 7.3.3.2-Baseline-D and 7.3.3.2-Enhanced-D | 7.3.3.2-Baseline-D and 7.3.3.2-Enhanced-D are separate line items in June 3, 2021 - filing | 7.3.3.2-D | 7.3.3.2-D Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Distribution | Line items 7.3.3.2-Baseline-D and 7.3.3.2-Enhanced-D are consolidated to 7.3.3.2-D in 2022 | Equipment / facility failure |  | <2018 | 0 | 0 | 0 | 0 | 0 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1511.585 | 474.7076 | 481.5713 | N/A | N/A | Circuit Breakers | 1947 | 611.448 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2368.31 | 743.7588 | 754.5128 | N/A | N/A | Circuit Breakers | 2253 | 707.5461 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2638.202 | 828.5174 | 840.4968 | N/A | N/A | Circuit Breakers | 2067 | 649.1335 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2585.9803 | 812.1174 | 823.8597 | N/A | N/A | Circuit Breakers | 2817 | 884.6682 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2411.392 | 757.2885 | 768.2381 | N/A | N/A | Circuit Breakers | 2817 | 884.6682 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation
Grid hardening | Grid Design & System Hardening | 7.3.3.2-T | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Transmission | 7.3.3.2-Baseline-T and 7.3.3.2-Enhanced-T | 7.3.3.2-Baseline-T and 7.3.3.2-Enhanced-T are separate line items in June 3, 2021 - filing | 7.3.3.2-T | 7.3.3.2-T Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Maintenance Substation Transmission | Line items 7.3.3.2-Baseline-T and 7.3.3.2-Enhanced-T are consolidated to 7.3.3.2-D in 2022 | Equipment / facility failure |  | <2018 | 0 | 0 | 0 | 0 | 0 | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1772.44 | 539.5104 | 559.5002 | N/A | N/A | Circuit Breakers | 4095 | 1246.471 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2414.211 | 734.8581 | 762.0859 | N/A | N/A | Circuit Breakers | 4639 | 1412.0584 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2088.398 | 635.6844 | 659.2376 | N/A | N/A | Circuit Breakers | 3572 | 1087.2758 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2444.5316 | 744.0874 | 771.6571 | N/A | N/A | Circuit Breakers | 3416 | 1039.7912 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 0 | 0 | 0 | 2444.5316 | 744.0874 | 771.6571 | N/A | N/A | Circuit Breakers | 3687 | 1122.2805 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation
Grid hardening | Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation | 7.3.3.3 | 7.3.3.3 Covered conductor installation | 7.3.3.3 | 7.3.3.3 Covered conductor installation |  | See initiative 7.3.3.17.1 | See initiative 7.3.3.17.1 | 2018 | 7.55 | - | 7.55 | 7.55 | 7.55 | See 7.3.3.17.1 | N/A | Exceeds | GO 95 | 7.3.3.17.1 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution | RSEs presented are for the year 2022. | 251263.87 | 251263.87 | 254896.8772 | 0 | 0 | 0 | 131.751 | 131.751 | # of circuit miles | 131.751 | 131.751 | This is a portion of the overall system hardening program, costs are not tracked separately but have been estimated as a portion of the overall system hardening spend. | 446093.376 | 446093.376 | 452543.4098 | 0 | 0 | 0 | 334 | 334 | # of circuit miles | 334 | 334 | Covered conductor in this initiative is in HFTDs | 113595.776 | 113595.776 | 115238.2496 | 0 | 0 | 0 | 146.96 | 146.96 | # of circuit miles | 146.96 | 146.96 | See Section 7.3.3.17-1 for System hardening information | 366000 | 366000 | 371291.9692 | 0 | 0 | 0 | 305 | 305 | # of circuit miles | 305 | 305 |  | 265376.8 | 265376.8 | 269213.8651 | 0 | 0 | 0 | 170 | 170 | # of circuit miles | 170 | 170
Grid hardening | Grid Design & System Hardening | 7.3.3.4 | Covered conductor maintenance | 7.3.3.4 | 7.3.3.4 Covered conductor maintenance | 7.3.3.4 | 7.3.3.4 Covered conductor maintenance |  | Equipment / facility failure | No other drivers addressed | 2018 | 1670.0685 | 4.3235 | 6.6812 | 2903.9408 | 935.5143 | 2020 GRC | FRMMA / WMPMA | In Compliance | GO 95 |  | RSEs presented are for the year 2022. | 24674.9144 | 8110.2403 | 8227.5057 | 17159.8071 | 5983.6764 | 6070.194 | N/A | N/A | Tags | 6554.5715 | 2409.4104 | Actual units is a more accurate representation | 18576.5561 | 7135.1861 | 7238.3532 | 17027.1357 | 9990.2317 | 10134.6798 | N/A | N/A | Tags | 6183.0734 | 3514.6289 | Actual units is a more accurate representation | 29052.1113 | 8749.5237 | 8876.0324 | 15281.3978 | 9723.6746 | 9864.2685 | N/A | N/A | Tags | 6323 | 3564 | Actual units is a more accurate representation | 44386.3098 | 25367.0235 | 25733.8036 | 9013.3054 | 7470.0681 | 7578.0773 | N/A | N/A | Tags | 7829 | 5554 | Actual units is a more accurate representation | 44386.3098 | 25367.0235 | 25733.8036 | 9013.3054 | 7470.0681 | 7578.0773 | N/A | N/A | Tags | 7829 | 5554 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.5 | Crossarm maintenance, repair, and replacement | 7.3.3.5 | 7.3.3.5 Crossarm maintenance, repair, and replacement | 7.3.3.5 | 7.3.3.5 Crossarm maintenance, repair, and replacement |  | Equipment / facility failure | No other drivers addressed | <2018 | 102.684 | 0.67149 | 19.5661 | 291.1802 | 98.1179 | 2020 GRC, Transmission Owners | FRMMA / WMPMA | Exceeds | GO 95; GO 165; FERC TPL Standards |  | RSEs presented are for the year 2022. | 75781.991 | 37223.8565 | 38603.0632 | 1443.2985 | 845.1408 | 876.4547 | N/A | N/A | Tags | 6236.8444 | 2723.7009 | Actual units is a more accurate representation | 52085.7144 | 26213.3011 | 27184.5481 | 966.639 | 592.122 | 614.0611 | N/A | N/A | Tags | 4798.0915 | 2345.6171 | Actual units is a more accurate representation | 80299.6185 | 32933.4025 | 34153.6407 | 2820.1257 | 1843.5114 | 1911.8166 | N/A | N/A | Tags | 7043 | 2874 | Actual units is a more accurate representation | 71788.1646 | 32920.0287 | 34139.7713 | 2567.1658 | 1728.7875 | 1792.842 | N/A | N/A | Tags | 7326 | 3410 | Actual units is a more accurate representation | 68996.6128 | 31322.5064 | 32483.0581 | 2760.6981 | 1858.7698 | 1927.6403 | N/A | N/A | Tags | 7341 | 3420 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles | 7.3.3.6 | 7.3.3.6 Distribution pole replacement and reinforcement, including with composite poles | 7.3.3.6 | 7.3.3.6 Distribution pole replacement and reinforcement, including with composite poles |  | Equipment / facility failure | No other drivers addressed | <2018 | 140.7824 | 0.82055 | 1.7852 | 237.7257 | 66.6294 | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 347133.1356 | 105777.9113 | 107307.3469 | 3764.3247 | 1080.3612 | 1095.9821 | N/A | N/A | Tags | 17834 | 8157.432 | Actual units is a more accurate representation | 238929.563 | 129004.8389 | 130870.1111 | 4783.4683 | 1372.8554 | 1392.7054 | N/A | N/A | Tags | 14033 | 8605.374 | Actual units is a more accurate representation | 390886.8857 | 330359.7864 | 335136.4361 | 2800.1469 | 803.6422 | 815.262 | N/A | N/A | Tags | 19269 | 14705.477 | Actual units is a more accurate representation | 419170.185 | 337801.8772 | 342686.1316 | 3460.0221 | 993.0263 | 1007.3844 | N/A | N/A | Tags | 22345 | 16269.4 | Actual units is a more accurate representation | 434217.5427 | 368822.4335 | 374155.212 | 3911.4241 | 1122.5787 | 1138.81 | N/A | N/A | Tags | 20734 | 14602.5 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement | 7.3.3.7 | 7.3.3.7 Expulsion fuse replacement | 7.3.3.7 | 7.3.3.7 Expulsion fuse replacement |  | Equipment / facility failure | No other drivers addressed | <2018 | 24.7226 | 0 | 0 | 33.0214 | 12.6693 | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 9130.3359 | 9130.3359 | 9262.3508 | 0 | 0 | 0 | N/A | N/A | # of fuses | 405 | 405 | Actual units is a more accurate representation | 7846.551 | 7846.551 | 7960.0037 | 0 | 0 | 0 | N/A | N/A | # of fuses | 643 | 643 | Actual units is a more accurate representation | 11295.1645 | 11295.1645 | 11458.4805 | 0 | 0 | 0 | N/A | N/A | # of fuses | 1429 | 1429 | Actual units is a more accurate representation | 35000 | 35000 | 35506.0626 | 0 | 0 | 0 | N/A | N/A | # of fuses | 3000 | 3000 | Actual units is a more accurate representation | 35000 | 35000 | 35506.0626 | 0 | 0 | 0 | N/A | N/A | # of fuses | 3000 | 3000 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.8.1 | Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Sectionalizing | 7.3.3.8.1 | 7.3.3.8.1 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Sectionalizing | 7.3.3.8.1 | 7.3.3.8.1 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Sectionalizing | Maintenance of viper reclosers added as new activity in Initiative 7.3.3.8.1 | Consequence - PSPS | No other consequences reflected | 2019 | 4.2542 | 0 | 4.2542 | 4.2542 | 4.2542 | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 25591.6764 | 25591.6764 | 25961.7048 | 0 | 0 | 0 | N/A | N/A | # of distribution sectionalizing devices | 298 | 298 | Actual units is a more accurate representation | 34977.9909 | 34977.9909 | 35483.7353 | 0 | 0 | 0 | N/A | N/A | # of distribution sectionalizing devices | 603 | 603 | Focus of switches is to reduce PSPS event scope, not related to "line miles treated" [Prior comment: Based on WMP write up 10 year program with 603 in 2020, 250 in 2021, and 100 in 2022, with at total of 1653 over the 10 years if 100 per year starting in 2022. Multiplied % by total HFTD miles.] | 14912.7556 | 14912.7556 | 15128.3781 | 44.0336 | 44.0336 | 44.6703 | N/A | N/A | # of distribution sectionalizing devices | 269 | 269 | Actual units is a more accurate representation | 10452.1989 | 10452.1989 | 10603.3265 | 0 | 0 | 0 | N/A | N/A | # of distribution sectionalizing devices | 100 | 100 | Actual units is a more accurate representation | 5948.7598 | 5948.7598 | 6034.7726 | 0 | 0 | 0 | N/A | N/A | # of distribution sectionalizing devices | 100 | 100 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events, Transmission Line Sectionalizing | 7.3.3.8.2 | 7.3.3.8.2 Grid topology improvements to mitigate or reduce PSPS events, Transmission Line Sectionalizing | 7.3.3.8.2 | 7.3.3.8.2 Grid topology improvements to mitigate or reduce PSPS events, Transmission Line Sectionalizing |  | Consequence - PSPS | No other consequences reflected | 2020 | 3.4138 | 0 | 3.4138 | 3.4138 | 3.4138 | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 33100 | 28491.1392 | 29546.784 | 0 | 0 | 0 | N/A | N/A | # of switches | 54 | 46.481 | Actual units is a more accurate representation | 44700 | 38475.9494 | 39901.5482 | 0 | 0 | 0 | N/A | N/A | # of switches | 79 | 68 | Focus of switches is to reduce PSPS event scope, not related to "line miles treated" [Prior comment: Based on WMP write up 10 year program with 603 in 2020, 250 in 2021, and 100 in 2022, with at total of 1653 over the 10 years if 100 per year starting in 2022. Multiplied % by total HFTD miles.] | 24700 | 21260.7595 | 22048.5065 | 0 | 0 | 0 | N/A | N/A | # of switches | 43 | 37.0127 | Actual units is a more accurate representation | 54247.7608 | 49727.1141 | 51569.5875 | 0 | 0 | 0 | N/A | N/A | # of switches | 36 | 33 | Actual units is a more accurate representation | 55295.487 | 50687.5298 | 52565.5882 | 0 | 0 | 0 | N/A | N/A | # of switches | 36 | 33 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.8.3 | Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Motorized Switch Operator Pilot | 7.3.3.8.3 | 7.3.3.8.3 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Motorized Switch Operator Pilot | 7.3.3.8.3 | 7.3.3.8.3 Grid topology improvements to mitigate or reduce PSPS events, Distribution Line Motorized Switch Operator Pilot |  | N/A - Foundational | N/A - Foundational | 2020 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 25591.6764 | 25591.6764 | 25961.7048 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Actual units is a more accurate representation | 34977.9909 | 34977.9909 | 35483.7353 | 0 | 0 | 0 | N/A | N/A | # of MSOs | 0 | 0 | Focus of switches is to reduce PSPS event scope, not related to "line miles treated" [Prior note: 54 SCADA switches were installed in T2 and T3 in 2019. However focus of the program was on reliability improvement. Focus switched for 2020 on mitigating PSPS impacts.] | 14912.7556 | 14912.7556 | 15128.3781 | 0 | 0 | 0 | N/A | N/A | # of MSOs | 50 | 50 | Actual units is a more accurate representation | 10452.1989 | 10452.1989 | 10603.3265 | 0 | 0 | 0 | N/A | N/A | # of MSOs | 50 | 50 | Actual units is a more accurate representation | 5948.7598 | 5948.7598 | 6034.7726 | 0 | 0 | 0 | N/A | N/A | # of MSOs | 100 | 100 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.9.1 | Installation of system automation equipment | 7.3.3.9.1 | 7.3.3.9.1 Installation of system automation equipment, Installation of System Automation Equipment | 7.3.3.9.1 | 7.3.3.9.1 Installation of system automation equipment |  | Equipment Failure, All Consequence | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 47562.0695 | 19539.6813 | 19822.2043 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles Other costs forecast in this section are for lifecycle replacements for distribution line automation | 20215.7585 | 7328.4392 | 7434.4006 | 0 | 0 | 0 | N/A | N/A | # of reclosers | 20 | 20 | Line miles treated is not an appropriate metric for substation related investments | 17206.8303 | 10504.4378 | 10656.3208 | 0 | 0 | 0 | N/A | N/A | # of reclosers | 81 | 81 | Actual units is a more accurate representation | 15598.7243 | 6284.347 | 6375.212 | 0 | 0 | 0 | N/A | N/A | # of reclosers | 65 | 32.0742 | Actual units is a more accurate representation | 12710.0163 | 3991.5326 | 4049.2459 | 0 | 0 | 0 | N/A | N/A | # of reclosers | 18 | 5.6528 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.9.2 | Installation of system automation equipment, Single phase reclosers | 7.3.3.9.2 | 7.3.3.9.2 Installation of system automation equipment, Single phase reclosers | 7.3.3.9.2 | 7.3.3.9.2 Installation of system automation equipment, Single phase reclosers |  | Contact from object, Vegetation Contact, Equipment / facility failure, Vandalism / Theft | No other drivers addressed | 2019 | 34.5818 | 0 | 0.74089 | 39.7479 | 21.3439 | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | # of fuse saver sets | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | # of fuse saver sets | 0 | 0 | Line miles treated is not an appropriate metric for substation related investments | 6730.3359 | 6730.3359 | 6827.6493 | 0 | 0 | 0 | N/A | N/A | # of fuse saver sets | 71 | 71 | Actual units is a more accurate representation | 4400 | 4400 | 4463.6193 | 0 | 0 | 0 | N/A | N/A | # of fuse saver sets | 80 | 80 | Actual units is a more accurate representation | 4400 | 4400 | 4463.6193 | 0 | 0 | 0 | N/A | N/A | # of fuse saver sets | 80 | 80 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.10 | Maintenance, repair, and replacement of connectors, including hotline clamps | 7.3.3.10 | 7.3.3.10 Maintenance, repair, and replacement of connectors, including hotline clamps | 7.3.3.10 | 7.3.3.10 Maintenance, repair, and replacement of connectors, including hotline clamps |  | Equipment / facility failure | No other drivers addressed | <2018 | 2110.5075 | 4.761 | 170.4384 | 2768.9373 | 1064.0456 | 2020 GRC, Transmission Owners | FRMMA / WMPMA | Exceeds | GO 95; GO 165; PRC 4292; FERC TPL Standards |  | RSEs presented are for the year 2022. | 1483.4945 | 1263.9381 | 1310.7691 | 17568.445 | 13317.6256 | 13811.0661 | N/A | N/A | Tags | 6039.528 | 4698.5749 | This is a portion of both the overall system hardening program (where connectors are replaced) and the enhanced inspection and repair program where connectors are reviewed and identified if repairs are needed, costs for connector activity are not tracked separately but have been estimated as a portion of the overall spend in those programs. | 1223.835 | 1072.1854 | 1111.9117 | 24792.9007 | 22172.6126 | 22994.1453 | N/A | N/A | Tags | 8541.0148 | 7700.9728 | No particular line miles addressed, repairs are identified and managed through existing, other programs. [Prior note: Whole system, 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle] | 1583.8682 | 1314.7676 | 1363.4819 | 23651.4136 | 21507.2985 | 22304.1802 | N/A | N/A | Tags | 8216 | 7527 | Actual units is a more accurate representation | 3134.7231 | 2960.8996 | 3070.6059 | 14596.8005 | 13431.1838 | 13928.8318 | N/A | N/A | Tags | 6481 | 5975 | Actual units is a more accurate representation | 3134.7231 | 2960.8996 | 3070.6059 | 14597.6988 | 13431.7494 | 13929.4184 | N/A | N/A | Tags | 6481 | 5975 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.11.1 | Mitigation of impact on customers and other residents affected during PSPS event, Generation for PSPS Mitigation | 7.3.3.11.1 | 7.3.3.11.1 Mitigation of impact on customers and other residents affected during PSPS event, Generation for PSPS Mitigation | 7.3.3.11.1 | 7.3.3.11.1 Mitigation of impact on customers and other residents affected during PSPS event, Generation for PSPS Mitigation | Change in scope to include the following: Back up Transfer Power Meters (new in 2022) Other customer impact mitigations (previously covered in 7.3.6.4-D in 2021 WMP) | Consequence - PSPS | No other consequences reflected | 2019 | 0.37111 | 0 | 0.37111 | 0.37111 | 0.37111 | 2020 GRC | Microgrid Memo Account FRMMA, WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 3283.1713 | 3283.1713 | 3330.6424 | 210.7776 | 210.7776 | 213.8252 | N/A | N/A | # of PIHs | 1 | 1 | DGEMs activities for PSPS mitigation were proposed, revised and further discussed in the Microgrid and Resilience Strategies Rulemaking (R.19-09-009). Program is noted here for informational purposes only and is subject to change, based on that other proceeding. | 20800.889 | 20800.889 | 21101.6477 | 176496.497 | 176496.497 | 179048.4478 | N/A | N/A | # of PIHs | 2 | 2 | N/A 0 substation should not be calculated by circuit mile | 16661.6908 | 16661.6908 | 16902.601 | 160389.6555 | 160389.6555 | 162708.7187 | N/A | N/A | # of PIHs | 6 | 6 | Narrative describes setting up the organization as the initiative | 23324.9089 | 23324.9089 | 23662.1622 | 112689.5805 | 112689.5805 | 114318.9515 | N/A | N/A | # of PIHs | 5 | 5 | Narrative describes setting up the organization as the initiative | 5515 | 5515 | 5594.741 | 106552.3851 | 106552.3851 | 108093.0189 |  |  | # of PIHs | 0 | 0 | Narrative describes setting up the organization as the initiative
Grid hardening | Grid Design & System Hardening | 7.3.3.11.2 | Mitigation of impact on customers and other residents affected during PSPS event, Substation activities to enable reduction of PSPS impacts | 7.3.3.11.2 | 7.3.3.11.2 Mitigation of impact on customers and other residents affected during PSPS event, Substation activities to enable reduction of PSPS impacts | 7.3.3.11.2 | 7.3.3.11.2 Mitigation of impact on customers and other residents affected during PSPS event, Substation activities to enable reduction of PSPS impacts |  | Consequence - PSPS | No other consequences reflected | 2020 | 66.5629 | 0 | 66.5629 | 66.5629 | 66.5629 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 4086 | 1283.1929 | 1301.7465 | 0 | 0 | 0 | N/A | N/A | # of fuses | 18 | 5.6528 | Line Miles = N/A as this activity supports substation activity to support PSPS events and not a specific volume of line miles | 3845.8212 | 1207.7656 | 1225.2286 | 0 | 0 | 0 | N/A | N/A | # of fuses | 4 | 1.2562 | N/A 0 substation should not be calculated by circuit mile | 11630.0472 | 3652.3724 | 3705.1818 | 0 | 0 | 0 | N/A | N/A | # of fuses | 2 | 0.62809 | N/A 0 substation should not be calculated by circuit mile | 681 | 213.8655 | 216.9577 | 0 | 0 | 0 | N/A | N/A | # of fuses | 0 | 0 | N/A 0 substation should not be calculated by circuit mile | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | # of fuses | 0 | 0 | N/A 0 substation should not be calculated by circuit mile
Grid hardening | Grid Design & System Hardening | 7.3.3.11.3 | Mitigation of impact on customers and other residents affected during PSPS event, Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers | 7.3.3.11.3 | 7.3.3.11.3 Mitigation of impact on customers and other residents affected during PSPS event, Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers | 7.3.3.11.3 | 7.3.3.11.3 Mitigation of impact on customers and other residents affected during PSPS event, Emergency Back-up Generation – PG&E Service Centers & Materials Distribution Centers |  | N/A - Foundational | N/A - Foundational | 2021 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | WMCE | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 |  | 37100 | 37100 | 37636.4264 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | CRESS Project - line miles not applicable | 39600 | 39600 | 40172.5737 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate measure for the initiative | 18000 | 18000 | 18260.2608 | 0 | 0 | 0 | N/A | N/A | # of sites | 15 | 15 | Line miles is not an appropriate measure for the initiative | 3000 | 3000 | 3043.3768 | 0 | 0 | 0 | N/A | N/A | # of sites | 6 | 6 | Line miles is not an appropriate measure for the initiative
Grid hardening | Grid Design & System Hardening | 7.3.3.11.4 | Fixed Power Solutions | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.3.11.4 | 7.3.3.11.4 Fixed Power Solutions | Added new sub-initiative in 2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate measure for the initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate measure for the initiative | 0 | 0 | 0 | 7800 | 7800 | 7912.7797 | N/A | N/A | Customer Systems | 150 | 150 | Line miles is not an appropriate measure for the initiative | 0 | 0 | 0 | 12066.21 | 12066.21 | 12240.6745 | N/A | N/A | Customer systems | 500 | 500 | Line miles is not an appropriate measure for the initiative
Grid hardening | Grid Design & System Hardening | 7.3.3.12.1 | Other corrective action, Distribution Substation | 7.3.3.12.1 | 7.3.3.12.1 Other corrective action, Distribution Substation | 7.3.3.12.1 | 7.3.3.12.1 Other corrective action, Distribution Substation | Defensible space spend shifted from 7.3.3.12.1 to 7.3.5.20 | Contact from object | No other drivers addressed | <2018 | 0 | 0 | 0 | 0 | 0 | 2020 GRC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 1306.7098 | 410.3673 | 416.3007 | 5248.1172 | 5246.8212 | 5322.6846 | N/A | N/A | Corrective Notifications | 543 | 543 | Line Miles = N/A as substation assets are not associated with circuit miles | 4960.8901 | 1557.9488 | 1580.475 | 2445.1287 | 2085.6017 | 2115.7573 | N/A | N/A | Corrective Notifications | 532 | 308 | N/A 0 substation should not be calculated by circuit mile | 4739.2217 | 1488.3347 | 1509.8544 | 2792.2492 | 2792.2492 | 2832.6222 | N/A | N/A | Corrective Notifications | 1308 | 1308 | N/A 0 substation should not be calculated by circuit mile | 0 | 0 | 0 | 976.9113 | 976.9113 | 991.0364 | N/A | N/A | Corrective Notifications | 584 | 584 | N/A 0 substation should not be calculated by circuit mile | 0 | 0 | 0 | 4626.1392 | 4626.1392 | 4693.0282 | N/A | N/A | Corrective Notifications | 0 | 0 | N/A 0 substation should not be calculated by circuit mile
Grid hardening | Grid Design & System Hardening | 7.3.3.12.2 | Other corrective action, Transmission Substation | 7.3.3.12.2 | 7.3.3.12.2 Other corrective action, Transmission Substation | 7.3.3.12.2 | 7.3.3.12.2 Other corrective action, Transmission Substation | Defensible space spend shifted from 7.3.3.12.2 to 7.3.5.20 | Contact from object | No other drivers addressed | <2018 | 0 | 0 | 0 | 0 | 0 | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 402.2633 | 122.4443 | 126.9811 | 2830.6898 | 2824.2018 | 2928.8433 | N/A | N/A | Corrective Notifications | 261 | 261 | Line Miles = N/A as substation assets are not associated with circuit miles | 958.5485 | 291.7712 | 302.5818 | 2014.4506 | 1749.5156 | 1814.3381 | N/A | N/A | Corrective Notifications | 420 | 208 | N/A 0 substation should not be calculated by circuit mile | 1390.5826 | 423.2774 | 438.9605 | 2882.8844 | 2882.8844 | 2989.7001 | N/A | N/A | Corrective Notifications | 1294 | 1294 | N/A 0 substation should not be calculated by circuit mile | 0 | 0 | 0 | 504.1428 | 504.1428 | 522.8222 | N/A | N/A | Corrective Notifications | 300 | 300 | N/A 0 substation should not be calculated by circuit mile | 0 | 0 | 0 | 1186.6132 | 1186.6132 | 1230.5792 | N/A | N/A | Corrective Notifications | 0 | 0 | N/A 0 substation should not be calculated by circuit mile
Grid hardening | Grid Design & System Hardening | 7.3.3.12.3 | Other corrective action, Maintenance, Transmission | 7.3.3.12.3 | 7.3.3.12.3 Other corrective action, Maintenance, Transmission | 7.3.3.12.3 | 7.3.3.12.3 Other corrective action, Maintenance, Transmission |  | Equipment / facility failure | No other drivers addressed | <2018 | 8.6993 | 0.23923 | 26.8768 | 26.8768 | 31.8235 | Transmission Owner | N/A | In Compliance | GO 95; GO 165; FERC TPL Standards |  | RSEs presented are for the year 2022. | 365319.6504 | 111199.1095 | 115319.2241 | 347117.5879 | 105658.6105 | 109573.4403 | N/A | N/A | Corrective Notifications | 29322 | 8925.2803 | These remediations are tags / notifications resulting from inspections based on the new inspection cycle of 100% T3 and 33% T2 going forward. For 2019 100% of HFTD was inspected as part of WSIP | 449179.0138 | 136724.9374 | 141790.827 | 99945.9642 | 30422.4046 | 31549.606 | N/A | N/A | Corrective Notifications | 15877 | 4832.7766 | Transmission 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 360362.224 | 109690.1258 | 113754.33 | 89135.5812 | 27131.8481 | 28137.1288 | N/A | N/A | Corrective Notifications | 15001 | 4566.1323 | Actual units is a more accurate representation | 412054.6501 | 125424.7071 | 130071.9041 | 127975.5381 | 38954.2853 | 40397.6072 | N/A | N/A | Corrective Notifications | 15169 | 4617.2695 | Actual units is a more accurate representation | 381315.7334 | 116068.1336 | 120368.6538 | 139107.312 | 42342.6695 | 43911.5368 | N/A | N/A | Corrective Notifications | 19098 | 5813.212 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.12.4 | Other corrective action, Maintenance, Distribution | 7.3.3.12.4 | 7.3.3.12.4 Other corrective action, Maintenance, Distribution | 7.3.3.12.4 | 7.3.3.12.4 Other corrective action, Maintenance, Distribution |  | Equipment / facility failure | No other drivers addressed | <2018 | 395.5788 | 1.6005 | 2.6868 | 779.669 | 238.7884 | 2020 GRC | FRMMA / WMPMA | In Compliance | GO 95 |  | RSEs presented are for the year 2022. | 233861.3126 | 120626.7514 | 122370.8854 | 75112.7333 | 40250.6338 | 40832.615 | N/A | N/A | Corrective Notifications | 79416.7946 | 52993.8445 | These remediations are tags / notifications resulting from inspections based on the new inspection cycle of 100% T3 and 33% T2 going forward. For 2019 100% of HFTD was inspected as part of WSIP | 236372.8788 | 116324.8261 | 118006.7588 | 75248.474 | 49008.5383 | 49717.1494 | N/A | N/A | Corrective Notifications |  |  | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 295107.9589 | 149538.0917 | 151700.2529 | 74702.949 | 48599.3991 | 49302.0945 | N/A | N/A | Corrective Notifications | N/A | N/A | Actual units is a more accurate representation | 196540.8369 | 110480.7735 | 112078.2075 | 93704.4326 | 72464.987 | 73512.7534 | N/A | N/A | Corrective Notifications | N/A | N/A | Actual units is a more accurate representation | 329592.6125 | 194791.8113 | 197608.2929 | 73465.8102 | 47353.6213 | 48038.3041 | N/A | N/A | Corrective Notifications | N/A | N/A | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.12.5 | Other corrective action, Generation Substation | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.3.12.5 | 7.3.3.12.5 Other corrective action, Generation Substation | Added new sub-initiative in 2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | FRMMA / WMPMA | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Corrective Actions | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Corrective Actions | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 905.9398 | 905.9398 | 919.0388 | N/A | N/A | Corrective Actions | 53 | 53 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 2839.3903 | 2839.3903 | 2880.4449 | N/A | N/A | Corrective Actions | 51 | 51 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 516.6667 | 516.6667 | 524.1371 | N/A | N/A | Corrective Actions | 51 | 51 | Line Miles = N/A as substation assets are not associated with circuit miles
Grid hardening | Grid Design & System Hardening | 7.3.3.13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 7.3.3.13 | 7.3.3.13 Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 7.3.3.13 | 7.3.3.13 Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  | Equipment / facility failure | No other drivers addressed | <2018 | 61.6932 | 0.32153 | 0.69952 | 93.1517 | 26.1084 | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 8200.8693 | 6806.7215 | 6905.1395 | 228.0798 | 189.3062 | 192.0434 | N/A | N/A | Poles | 167.08 | 63.08 | Units in the table appear to be overloaded poles replaced | 13793.3459 | 11448.4771 | 11614.0099 | 61.0715 | 50.6893 | 51.4222 | N/A | N/A | Poles | 263.69 | 118.69 | Units in the table appear to be overloaded poles replaced | 19998.0899 | 16598.4146 | 16838.41 | 0.41075 | 0.34092 | 0.34585 | N/A | N/A | Poles | 492.53 | 324.53 | Units in the table appear to be overloaded poles replaced | 9236.196 | 7666.0427 | 7776.8855 | 154.455 | 128.1977 | 130.0513 | N/A | N/A | Poles | 269.27 | 223.27 | Units in the table appear to be overloaded poles replaced | 9220.919 | 7653.3628 | 7764.0222 | 158.91 | 131.8953 | 133.8024 | N/A | N/A | Poles | 262.46 | 217.46 | Units in the table appear to be overloaded poles replaced
Grid hardening | Grid Design & System Hardening | 7.3.3.14 | Transformers maintenance and replacement | 7.3.3.14 | 7.3.3.14 Transformers maintenance and replacement | 7.3.3.14 | 7.3.3.14 Transformers maintenance and replacement |  | Equipment / facility failure | No other drivers addressed | <2018 | 14.9196 | 0.13781 | 0 | 28.6747 | 8.3421 | 2020 GRC, Transmission Owner | FRMMA / WMPMA | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 41206.9431 | 22054.9637 | 22373.8549 | 170.8347 | 20.838 | 21.1393 | N/A | N/A | Tags | 2534.0569 | 1467.3339 | Actual units is a more accurate representation | 32920.1029 | 19691.6578 | 19976.3781 | 129.2342 | 34.7907 | 35.2937 | N/A | N/A | Tags | 2043.0982 | 1308.268 | Actual units is a more accurate representation | 48102.8368 | 24629.1037 | 24985.2142 | 108.4535 | 33.8624 | 34.352 | N/A | N/A | Tags | 2898 | 1614 | Actual units is a more accurate representation | 22485.2165 | 15708.2682 | 15935.393 | 1335.0436 | 1310.7454 | 1329.6974 | N/A | N/A | Tags | 1488 | 963 | Actual units is a more accurate representation | 27558.7165 | 20781.7682 | 21082.2504 | 1372.5436 | 1348.2454 | 1367.7396 | N/A | N/A | Tags | 1688 | 1163 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.15 | Transmission tower maintenance and replacement | 7.3.3.15 | 7.3.3.15 Transmission tower maintenance and replacement | 7.3.3.15 | 7.3.3.15 Transmission tower maintenance and replacement |  | Equipment / facility failure | No other drivers addressed | <2018 | 30.2769 | 0.39379 | 0 | 44.2413 | 54.5776 | Transmission Owner | N/A | Exceeds | GO95; GO165 |  | RSEs presented are for the year 2022. | 9135.9949 | 5800.8696 | 6015.8016 | 96300.0848 | 61145.4189 | 63410.9598 | N/A | N/A | Structures | 13241 | 8407.329 | Actual units is a more accurate representation | 40848.31 | 25936.4987 | 26897.4897 | 51008.4425 | 32387.6411 | 33587.6579 | N/A | N/A | Structures | 8066 | 5121.4799 | Actual units is a more accurate representation | 60006.7976 | 38101.1168 | 39512.8275 | 57675.5552 | 36620.9022 | 37977.7684 | N/A | N/A | Structures | 7466 | 4740.5119 | Actual units is a more accurate representation | 154981 | 98404.671 | 102050.7301 | 50261.2325 | 31913.2026 | 33095.6406 | N/A | N/A | Structures | 6220 | 3949.3683 | Actual units is a more accurate representation | 175000 | 111115.6686 | 115232.6916 | 53422.01 | 33920.1278 | 35176.9257 | N/A | N/A | Structures | 6512.9445 | 4135.3725 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment | 7.3.3.16 | 7.3.3.16 Undergrounding of electric lines and/or equipment | 7.3.3.16 | 7.3.3.16 Undergrounding of electric lines and/or equipment |  | See initiative 7.3.3.17.1 | See initiative 7.3.3.17.1 | <2018 | 4.4 | - | 4.4 | 4.4 | 4.4 | N/A | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 27826 | 27826 | 28228.3342 | 0 | 0 | 0 | 6.764 | 6.764 | # of circuit miles | 6.764 | 6.764 | See Section 7.3.3.17-1 for System hardening information | 10873.446 | 10873.446 | 11030.6644 | 0 | 0 | 0 | 4.61 | 4.61 | # of circuit miles | 4.61 | 4.61 | See Section 7.3.3.17-1 for System hardening information | 164358.394 | 164358.394 | 166734.8409 | 0 | 0 | 0 | 40.16 | 40.16 | # of circuit miles | 40.16 | 40.16 | See Section 7.3.3.17-1 for System hardening information | 611250 | 611250 | 620088.0223 | 0 | 0 | 0 | 163 | 163 | # of circuit miles | 163 | 163 |  | 1192578.075 | 1192578.075 | 1209821.4804 | 0 | 0 | 0 | 357.3 | 357.3 | # of circuit miles | 357.3 | 357.3
Grid hardening | Grid Design & System Hardening | 7.3.3.17.1 | Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution (Line Removal) | 7.3.3.17.1 | 7.3.3.17.1 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution | 7.3.3.17.1 | 7.3.3.17.1 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, Utility work / Operation, CC - Seismic Scenario | No other drivers addressed | 2018 | 5.5 (140) | 0 | 0.06 (140) | 5.8 (140) | 4.1 (140) | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. The Line Removal RSE is based on line removal mileage completed as of 6/21/22 using an average cost. | $281,066 ($3,455) | $281,066 ($3,455) | $285,130 ($3,455) | 0 | 0 | 0 | 171.11 (32.6) | 171.11 (32.6) | # of circuit miles (# of circuit miles removed) | 171.11 (32.6) | 171.11 (32.6) | This is the bulk of the overall system hardening program, some costs have been broken out for line items 3, 10 & 16 of this table. Estimated miles of undergrounding for 2021 & 2022 has also been broken out in line item 16 of this table. | $460,142 ($357) | $460,142 ($357) | $466,795 ($357) | 0 | 0 | 0 | 342 (3.4) | 342 (3.4) | # of circuit miles (# of circuit miles removed) | 342 (3.4) | 342 (3.4) | Metric is miles, based on narrative, 180 in 2021, 464 in 2022 (2021-2023 target is to complete 1127 miles) | $280,422 ($2,474) | $280,422 ($2,474) | $284,476 ($2,474) | 0 | 0 | 0 | 210.6 (23.3) | 210.6 (23.3) | # of circuit miles (# of circuit miles removed) | 210.6 (23.3) | 210.6 (23.3) | Miles is the metric for this initiative | $977,250 ($985) | $977,250 ($985) | $991,380 ($985) | 0 | 0 | 0 | 470 (9.3) | 470 (9.3) | # of circuit miles | 470 (9.3) | 470 (9.3) | Miles is the metric for this initiative | 1457954.875 | 1457954.875 | 1479035.3456 | 0 | 0 | 0 | 527.3 | 527.3 | # of circuit miles | 527.3 | 527.3 | Miles is the metric for this initiative
Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Transmission | 7.3.3.17.2 | 7.3.3.17.2 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Transmission | 7.3.3.17.2 | 7.3.3.17.2 Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Transmission |  | N/A | No other drivers addressed | 2019 | N/A | N/A | N/A | N/A | N/A | Transmission Owner | N/A | Exceeds | GO 95; GO 165; FERC TPL Standards |  | RSEs presented are for the year 2022. | 508.0346 | 508.0346 | 526.8582 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Variety of different units | 1060.154 | 1060.154 | 1099.4345 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Miles to be treated reference the 92 miles of Transmission Conductor to be replaced in HFTD areas in 2021. [Prior note: Only program in this section that miles could apply to is 71Z ROW clearing] | 24817.0913 | 24817.0913 | 25736.6064 | 0 | 0 | 0 | N/A | N/A | # of circuit miles | 0 | 0 | Variety of different units | 19050.876 | 19050.876 | 19756.743 | 0 | 0 | 0 | N/A | N/A | # of circuit miles | 32.58 | 32.58 | Variety of different units | 19622.4022 | 19622.4022 | 20349.4453 | 0 | 0 | 0 | N/A | N/A | # of circuit miles | 32.58 | 32.58 | Variety of different units
Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor | 7.3.3.17.3 | 7.3.3.17.3 Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor | 7.3.3.17.3 | 7.3.3.17.3 Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor |  | Equipment / facility failure | No other drivers addressed | <2018 | 4.4597 | 0.1445 | 0 | 7.427 | 1.9172 | 2020 GRC | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 21767.3506 | 16242.3826 | 16477.2301 | 0 | 0 | 0 | N/A | N/A | # of Surge Arrestors | 3404 | 2540 | Actual units is a more accurate representation | 63497.9953 | 45387.9005 | 46044.1611 | 0 | 0 | 0 | N/A | N/A | # of Surge Arrestors | 14372 | 10273 | Actual units is a more accurate representation | 74190.9391 | 74190.9391 | 75263.6608 | 0 | 0 | 0 | N/A | N/A | # of Surge Arrestors | 15477 | 15477 | Actual units is a more accurate representation | 33172.1158 | 21401.365 | 21710.8059 | 0 | 0 | 0 | N/A | N/A | # of Surge Arrestors | 7750 | 5000 | Actual units is a more accurate representation | 17706.3611 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | # of Surge Arrestors | 4396 | 0 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.17.4 | Updates to grid topology to minimize risk of ignition in HFTDs, Rapid Earth Current Fault Limiter | 7.3.3.17.4 | 7.3.3.17.4 Updates to grid topology to minimize risk of ignition in HFTDs, Rapid Earth Current Fault Limiter | No 2022 financial data - 7.3.3.17.4 | No 2022 financial data - 7.3.3.17.4 Updates to grid topology to minimize risk of ignition in HFTDs, Rapid Earth Current Fault Limiter | There is no financial spend allocated for 2022; any available data (e.g. financials/line miles/units) is provided for previous years. | N/A | No other drivers addressed | 2019 | N/A | N/A | N/A | N/A | N/A | EPIC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 56.6213 | 56.6213 | 57.44 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Program is an exploratory project, some details including line miles to be "treated" are still TBD. | 4798.2197 | 4798.2197 | 4867.5968 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | A long-term plan will be developed after successful completion of the pilot and identifications of lessons learned in 2021 | -2022.3511 | -2022.3511 | -2051.5921 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative
Grid hardening | Grid Design & System Hardening | 7.3.3.17.5 | Updates to grid topology to minimize risk of ignition in HFTDs, Remote Grid | 7.3.3.17.5 | 7.3.3.17.5 Updates to grid topology to minimize risk of ignition in HFTDs, Remote Grid | 7.3.3.17.5 | 7.3.3.17.5 Updates to grid topology to minimize risk of ignition in HFTDs, Remote Grid | Line Elimination Incentive Program and Operation and Maintenance of the Remote Grids have been included in this initiative in 2022. | N/A | No other drivers addressed | 2020 | 22.6 | N/A | 22.6 | 22.6 | 22.6 | WMCE | FRMMA / WMPMA | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 30.5914 | 30.5914 | 31.0337 | N/A | N/A | # of Remote Grids | N/A | N/A | Program is an exploratory project, some details including line miles to be "treated" are still TBD. | 183.8062 | 183.8062 | 186.4639 | 755.2311 | 755.2311 | 766.1509 | N/A | N/A | # of Remote Grids | N/A | N/A | PG&E has not determined a long-term plan yet for this initiative. Pending the success of initial Remote Grid projects, we will be evaluating the reduction in wildfire ignition risk and costs, engineering and execution feasibility, and overall service quality in order to determine the long-term path and program scalability | 1785.293 | 1785.293 | 1811.1065 | 4857.1281 | 4857.1281 | 4927.357 | N/A | N/A | # of Remote Grids | 1 | 1 | Actual units is a more accurate representation | 17000 | 17000 | 17245.8018 | 14824.2289 | 14824.2289 | 15038.5714 | N/A | N/A | # of Remote Grids | 2 | 2 | Actual units is a more accurate representation | 8500 | 8500 | 8622.9009 | 15166.0821 | 15166.0821 | 15385.3674 | N/A | N/A | # of Remote Grids | 1 | 1 | Actual units is a more accurate representation
Grid hardening | Grid Design & System Hardening | 7.3.3.17.6 | Updates to grid topology to minimize risk of ignition in HFTDs, Butte County Rebuild | 7.3.3.17.6 | 7.3.3.17.6 Updates to grid topology to minimize risk of ignition in HFTDs, Butte County Rebuild | 7.3.3.17.6 | 7.3.3.17.6 Updates to grid topology to minimize risk of ignition in HFTDs, Butte County Rebuild |  | All Drivers | All Drivers | 2019 | 1.1633 | 0.012507 | 0.031868 | 1.6293 | 1.5161 | N/A | N/A | Exceeds | GO 95 |  | RSEs presented are for the year 2022. | 38549.4114 | 28912.0586 | 29330.0961 | 0 | 0 | 0 | 0.4 | 0 | # of primary circuit miles | 0.4 | 0 | Miles is the metric for this initiative | 64587.0231 | 48440.2673 | 49140.6619 | 0 | 0 | 0 | 36.6 | 26.4 | # of primary circuit miles | 36.6 | 26.4 | Miles is the metric for this initiative | 98429.0159 | 73821.7619 | 74889.1458 | 0 | 0 | 0 | 31.5 | 22.4 | # of primary circuit miles | 31.5 | 22.4 | Miles is the metric for this initiative | 138750 | 104062.5 | 105567.1326 | 0 | 0 | 0 | 55 | 32.8 | # of primary circuit miles | 55 | 32.8 | Miles is the metric for this initiative | 142521.925 | 114017.54 | 115666.1119 | 0 | 0 | 0 | 70 | 56 | # of primary circuit miles | 70 | 56 | Miles is the metric for this initiative
Asset inspection | Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment | 7.3.4.1 | 7.3.4.1 Detailed inspections of distribution electric lines and equipment | 7.3.4.1 | 7.3.4.1 Detailed inspections of distribution electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 214.356 | 1.0272 | 1.6793 | 487.3024 | 149.2456 | 2020 GRC | FRMMA / WMPMA | In Compliance | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 143845.2604 | 135655.8362 | 137617.2747 |  | 25597 | # of poles | 486749 | 190383 | This item captures the minor volume of non-enhanced inspections in HFTD areas | 0 | 0 | 0 | 100485.3167 | 52079.6486 | 52832.6647 | 24263 | 13265.6667 | # of poles | 781555 | 447160 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 95920.6026 | 50048.7923 | 50772.4444 | 24263.94 | 13150.94 | # of poles | 960862 | 521194 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 100378.9799 | 51876.3511 | 52626.4278 | 24263.94 | 13150.94 | # of poles | 919294 | 446006 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 101781.9707 | 53372.639 | 54144.3504 | 24263.94 | 13150.94 | # of poles | 919294 | 446006 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle
Asset inspection | Asset Management & Inspections | 7.3.4.2 | Detailed inspections of transmission electric lines and equipment | 7.3.4.2 | 7.3.4.2 Detailed inspections of transmission electric lines and equipment | 7.3.4.2 | 7.3.4.2 Detailed inspections of transmission electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 9.1825 | 0.0079059 | 24.0528 | 3.9055 | 32.3295 | Transmission Owner | N/A | In Compliance | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 72520.882 | 67601.1067 | 1105.2611 |  | 5710 | # of structures | 333566 | 40145 | This item captures the minor volume of non-enhanced inspections in HFTD areas | 0 | 0 | 0 | 92826.651 | 9442.9715 | 154.3902 | 5234.6 | 2862 | # of structures | 392435 | 112955 | Transmission 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 85681.5605 | 28378.4479 | 463.9805 | 5473.07 | 2862.07 | # of structures | 278786 | 120320 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 86707.253 | 56022.0741 | 915.9468 | 5473.07 | 2862.07 | # of structures | 259271 | 136944 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle | 0 | 0 | 0 | 89308.4706 | 57702.7363 | 943.4252 | 5473.07 | 2862.07 | # of structures | 259271 | 136944 | 100% for 2019 based on WSIP and 100% T3, 33% T2, 20% T1 based on new inspection cycle
Asset inspection | Asset Management & Inspections | 7.3.4.3 | Improvement of inspections | 7.3.4.3 | 7.3.4.3 Improvement of inspections | 7.3.4.3 | 7.3.4.3 Improvement of inspections |  | N/A - Foundational | No other drivers addressed | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A |  | 0 | 0 | This item captures estimated costs associated with inspection process improvements in 2019 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Line miles treated is not an appropriate metric for a system/process improvement | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles treated is not an appropriate metric for a system/process improvement | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles treated is not an appropriate metric for a system/process improvement | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles treated is not an appropriate metric for a system/process improvement
Asset inspection | Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment | 7.3.4.4 | 7.3.4.4 Infrared inspections of distribution electric lines and equipment | 7.3.4.4 | 7.3.4.4 Infrared inspections of distribution electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 45.5994 | 0.19162 | 0.32167 | 93.3446 | 28.5885 | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1918.7773 | 952.1643 | 965.9316 | 14608 | 7249 | # of circuit miles | 14608 | 7249 | Miles is the metric for this initiative | 0 | 0 | 0 | 1561.3355 | 879.1485 | 891.86 | 5450 | 5450 | # of circuit miles | 9679 | 5450 | Miles is the metric for this initiative | 0 | 0 | 0 | 2118.1083 | 1651.2346 | 1675.1097 | 12948 | 10094 | # of circuit miles | 12948 | 10094 | Miles is the metric for this initiative | 0 | 0 | 0 | 2225.8927 | 2114.5981 | 2145.1729 | 10600 | 10070 | # of circuit miles | 10600 | 10070 | Miles is the metric for this initiative | 0 | 0 | 0 | 2290.0949 | 2175.5902 | 2207.0469 | 10600 | 10070 | # of circuit miles | 10600 | 10070 | Miles is the metric for this initiative
Asset inspection | Asset Management & Inspections | 7.3.4.5 | Infrared inspections of transmission electric lines and equipment | 7.3.4.5 | 7.3.4.5 Infrared inspections of transmission electric lines and equipment | 7.3.4.5 | 7.3.4.5 Infrared inspections of transmission electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 0.50745 | 0.0020873 | 0.78938 | 0.88523 | 1.0663 | Transmission Owner | N/A | In Compliance | GO 95; GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 222.5848 | 0 | 0 |  | N/A |  | 0 | 0 | Going forward, infrared inspections will be deployed as appropriate alongside the suite of other inspection tools and techniques include enhanced visual inspections, drones or helicopters and other emerging technologies. PG&E does not have a discrete plan for how many circuit miles will be inspected using IR systems in HFTD areas. | 0 | 0 | 0 | 1443.6 | 711.148 | 0 | 5280 | 2601.04 |  | 5280 | 2601.04 | Miles is the metric for this initiative | 0 | 0 | 0 | 2534.5113 | 1407.327 | 22.7769 | 7591.34 | 4215.21 |  | 7591.34 | 4215.21 | Miles is the metric for this initiative | 0 | 0 | 0 | 2220 | 912.418 | 14.767 | 7844.47 | 3224.07 | Miles | 7844.47 | 3224.07 | Miles is the metric for this initiative | 0 | 0 | 0 | 2220 | 912.418 | 14.767 | 7844.47 | 3224.07 |  | 7844.47 | 3224.07 | Miles is the metric for this initiative
Asset inspection | Asset Management & Inspections | 7.3.4.6.1 | Intrusive pole inspections, Distribution | 7.3.4.6 | 7.3.4.6 Intrusive pole inspections | 7.3.4.6.1 | 7.3.4.6.1 Intrusive pole inspections, Distribution | Initiative 7.3.4.6 has been split into sub-initiatives 7.3.4.6.1 + 7.3.4.6.2 in 2022 | Equipment / facility failure | No other drivers addressed | <2018 | 379.7853 | 5.7482 | 12.5058 | 1665.3441 | 466.7604 | 2020 GRC, Transmission Owner | FRMMA / WMPMA | Exceeds | GO 165; GO 95 rule 44.3 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 17848.7066 | 5122.5788 | 5196.6458 |  | 2559.7 |  | 224419 | 64408.253 | Based on a ten year cycle | 0 | 0 | 0 | 17446.6652 | 628.3732 | 637.4588 | 8100 | 2559.7 |  | 238000 | 8572 | Based on a ten year cycle | 0 | 0 | 0 | 17628.5321 | 3691.7164 | 3745.0947 | 8100 | 2544 |  | 217211 | 52296 | Based on a ten year cycle | 0 | 0 | 0 | 21239.442 | 6095.7199 | 6183.8575 | 8100 | 2544 |  | 295000 | 84665 | Based on a ten year cycle | 0 | 0 | 0 | 19247.0471 | 5523.9025 | 5603.7722 | 8100 | 2544 |  | 260000 | 74620 | Based on a ten year cycle
Asset inspection | Asset Management & Inspections | 7.3.4.6.2 | Intrusive pole inspections, Transmission | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.4.6.2 | 7.3.4.6.2 Intrusive pole inspections, Transmission | Initiative 7.3.4.6 has been split into sub-initiatives 7.3.4.6.1 + 7.3.4.6.2 in 2022 | N/A | N/A | <2018 | N/A | N/A | N/A | N/A | N/A |  |  | Exceeds | GO 165; GO 95 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1958.5373 | 312.1908 | 323.758 |  | 587 |  | 14331 | 2284.3614 | Based on a ten year cycle | 0 | 0 | 0 | 1450.5177 | 231.2125 | 239.7793 | 1892 | 587 |  | 0 | 0 | Based on a ten year cycle | 0 | 0 | 0 | 1323.8431 | 211.0206 | 218.8393 | 1892 | 587 |  | 7630 | 1216.222 | Based on a ten year cycle | 0 | 0 | 0 | 2150 | 342.71 | 355.408 | 1892 | 587 |  | 10000 | 1594 | Based on a ten year cycle | 0 | 0 | 0 | 2150 | 342.71 | 355.408 | 1892 | 587 |  | 10000 | 1594 | Based on a ten year cycle
Asset inspection | Asset Management & Inspections | 7.3.4.7 | LiDAR Inspections of Distribution Electric Lines and Equipment | 7.3.4.7 | 7.3.4.7 LiDAR Inspections of Distribution Electric Lines and Equipment | 7.3.4.7 | 7.3.4.7 LiDAR Inspections of Distribution Electric Lines and Equipment |  | N/A - Pilot | N/A - Pilot | <2018 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A | N/A | Exceeds | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 15061 | 3012.2 | 3055.7532 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 5404 | 1080.8 | 1096.4272 | 3000 | 3000 |  | 0 | 0 | Updated based on language in the 2021 WMP narrative. | 0 | 0 | 0 | 10312 | 2062.4 | 2092.2201 | N/A | N/A | N/A | 0 | 0 | Specific miles not available | 0 | 0 | 0 | 10500 | 2100 | 2130.3638 | N/A | 158 |  | 0 | 0 | Specific Non-HFTD miles not available | 0 | 0 | 0 | 10000 | 2000 | 2028.9179 | N/A | N/A |  | 0 | 0 | No specific targets associated with this initiative
Asset inspection | Asset Management & Inspections | 7.3.4.8 | LiDAR Inspections of Transmission Electric Lines and Equipment | 7.3.4.8 | 7.3.4.8 LiDAR Inspections of Transmission Electric Lines and Equipment | 7.3.4.8 | 7.3.4.8 LiDAR Inspections of Transmission Electric Lines and Equipment |  | N/A | N/A | See Initiative 7.3.5.8 | N/A | N/A | N/A | N/A | N/A | Transmission Owner | N/A | See Initiative 7.3.5.8 | See Initiative 7.3.5.8 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 398 | 358.2 | 371.4719 | N/A | N/A |  | 0 | 0 | PG&E does not have a long-term plan established for LiDAR inspections of electric transmission assets. As noted above, PG&E is exploring the use of this technology which may, or may not, result in the development of a program to leverage this technology for asset inspections in the future. | 0 | 0 | 0 | 355 | 319.5 | 331.338 | N/A | N/A | N/A | 0 | 0 | Specific miles not available | 11003 | 9902.7 | 10269.6117 | 5030 | 4527 | 4694.733 | N/A | 269 |  | 0 | 0 | Specific Non-HFTD miles not available | 3000 | 2700 | 2800.0396 | 3000 | 2700 | 2800.0396 | N/A | N/A |  | 0 | 0 | No specific targets associated with this initiative
Asset inspection | Asset Management & Inspections | 7.3.4.9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.4.9 | 7.3.4.9 Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.4.9 | 7.3.4.9 Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | N/A - Complementary | N/A - Complementary | See Initiatives 7.3.4.1 and 7.3.4.4 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2287.3577 | 718.336 | 728.7224 |  | 25597 |  | 24288 | 7627.5546 | 100% for 2019 based on WSIP and 100% T3 and 33% T2 based on new inspection cycle | 0 | 0 | 0 | 2729.9172 | 857.3202 | 869.7161 | N/A | N/A | Inspections | 24643 | 7739.041 | Inspections in this initiative are not based on line miles or even a percentage of the system | 0 | 0 | 0 | 2964.3061 | 930.9291 | 944.3894 | N/A | N/A | Inspections | 25007 | 7853.3538 | Inspections in this initiative are not based on line miles or even a percentage of the system | 0 | 0 | 0 | 3257.6179 | 1023.0426 | 1037.8347 | N/A | N/A | Inspections | 27884 | 8756.8648 | Inspections in this initiative are not based on line miles or even a percentage of the system | 0 | 0 | 0 | 3351.5785 | 1052.5505 | 1067.7693 | N/A | N/A | Inspections | 27884 | 8756.8648 | Inspections in this initiative are not based on line miles or even a percentage of the system
Asset inspection | Asset Management & Inspections | 7.3.4.10 | Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.4.10 | 7.3.4.10 Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.4.10 | 7.3.4.10 Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations |  | N/A - Pilot | N/A - Pilot | <2018 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | Transmission Owner | N/A | In Compliance | GO 95; GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 5710 |  | 0 | 0 | 100% for 2019 based on WSIP and 100% T3 and 33% T2 based on new inspection cycle | 0 | 0 | 0 | 131 | 39.8749 | 41.3523 | N/A | N/A | N/A | 0 | 0 | Inspections in this initiative are not based on line miles or even a percentage of the system | 579.433 | 176.3728 | 182.9077 | 1127 | 343.0459 | 355.7563 | N/A | N/A | Inspections | 318 | 96.7956 | Inspections in this initiative are not based on line miles or even a percentage of the system | 3700 | 1126.2375 | 1167.9665 | 4300 | 1308.8707 | 1357.3665 | N/A | N/A | Inspections | 1001 | 304.6929 | Inspections in this initiative are not based on line miles or even a percentage of the system | 4070 | 1238.8613 | 1284.7632 | 4429 | 1348.1368 | 1398.0875 | N/A | N/A | Inspections | 1101.1 | 335.1622 | Inspections in this initiative are not based on line miles or even a percentage of the system
Asset inspection | Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment | 7.3.4.11 | 7.3.4.11 Patrol inspections of distribution electric lines and equipment | 7.3.4.11 | 7.3.4.11 Patrol inspections of distribution electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 68.4054 | 0.63187 | 1.0607 | 307.8012 | 94.2699 | 2020 GRC | N/A | In Compliance | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 6151.5771 | 1931.8795 | 1959.8124 |  | 2238.5449 |  | 1601338 | 502894.1457 | Patrols completed for HFTD assets not covered by detailed overhead inspections. For 2019 actual, since all assets were detail inspected, no routine patrols were executed; For 2020-2022 plan to patrol 2/3rds of Tier 2 line miles each year. | 0 | 0 | 0 | 7737.2502 | 2429.8542 | 2464.9873 | 56541 | 12089 |  | 1657817 | 520631.1622 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 6097.237 | 1914.8142 | 1942.5004 | 56541 | 12089 |  | 1327910 | 417025.1159 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 6062.9179 | 1284.0581 | 1302.6242 | 56541 | 12089 |  | 1186480 | 261025 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 6237.7928 | 1321.0946 | 1340.1962 | 56541 | 12089 |  | 1186480 | 261025 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled)
Asset inspection | Asset Management & Inspections | 7.3.4.12 | Patrol inspections of transmission electric lines and equipment | 7.3.4.12 | 7.3.4.12 Patrol inspections of transmission electric lines and equipment | 7.3.4.12 | 7.3.4.12 Patrol inspections of transmission electric lines and equipment |  | Equipment / facility failure | No other drivers addressed | <2018 | 1092.8532 | 12.6633 | 4382.7663 | 4914.9156 | 0 | Transmission Owner | N/A | In Compliance | GO 95; GO 167 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 18.1944 | 0 | 0 |  | N/A |  | 683 | 0 | The costs in this section are for transmission patrols for facilities that cannot be patrolled by air; other transmission patrols are included in Table 24, line item 2. Detailed inspections of transmission electric lines and equipment. For 2019 all Tier 2 and Tier 3 were inspected, no patrols were conducted. For 2020-2022 plan to patrol 2/3rds of Tier 2 line miles each year. | 0 | 0 | 0 | 170.4886 | 0 | 0 | 13400 | 2956 |  | 4503 | 0 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 59.6549 | 0 | 0 | 13400 | 2956 |  | 1939 | 0 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 83.6831 | 24.6165 | 0 | 13400 | 2956 |  | 2570 | 756 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled) | 0 | 0 | 0 | 83.6831 | 24.6165 | 0 | 13400 | 2956 |  | 2570 | 756 | Based on 0% in T3, 66% T 2 and 80% Non-HFTD annually (all miles that are not inspected are patrolled)
Asset inspection | Asset Management & Inspections | 7.3.4.13 | Pole loading assessment program to determine safety factor | 7.3.4.13 | 7.3.4.13 Pole loading assessment program to determine safety factor | 7.3.4.13 | 7.3.4.13 Pole loading assessment program to determine safety factor |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | N/A | FRMMA / WMPMA | Exceeds | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 55 | 55 | 55.7952 |  | N/A |  | 0 | 0 | This line item relates to the actual pole loading calculations leveraging the tool implemented via initiative 5.3.3.13 on Table 23. | 0 | 0 | 0 | 13652 | 13652 | 13849.3933 | N/A | N/A | Calculations | 134899 | 134899 | Actual units is a more accurate representation | 0 | 0 | 0 | 10162 | 10162 | 10308.9317 | N/A | N/A | Calculations | 61723 | 61723 | Actual units is a more accurate representation | 0 | 0 | 0 | 9122.83 | 9122.83 | 9254.7364 | N/A | N/A | Calculations | 180000 | 180000 | Actual units is a more accurate representation | 0 | 0 | 0 | 10237.025 | 10237.025 | 10385.0414 | N/A | N/A | Calculations | 200000 | 200000 | Actual units is a more accurate representation
Asset inspection | Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections | 7.3.4.14 | 7.3.4.14 Quality assurance / quality control of inspections | 7.3.4.14 | 7.3.4.14 Quality assurance / quality control of inspections |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 165 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 38509.9606 | 32511.4787 | 32981.5599 |  | N/A |  | 0 | 0 | 100% for 2019 based on WSIP and 100% T3 and 33% T2 based on new inspection cycle | 0 | 0 | 0 | 40700.2842 | 33846.7053 | 34336.0926 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for these other initiatives | 0 | 0 | 0 | 27309.1184 | 14190.742 | 14395.9249 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for these other initiatives | 0 | 0 | 0 | 6015.9077 | 3214.3418 | 3260.8177 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for these other initiatives | 0 | 0 | 0 | 6189.4267 | 3307.0542 | 3354.8707 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for these other initiatives
Asset inspection | Asset Management & Inspections | 7.3.4.15-T | Substation inspections, Enhanced Transmission, Substation | 7.3.4.15-T | 7.3.4.15-T Substation inspections, Enhanced Transmission, Substation | 7.3.4.15-T | 7.3.4.15-T Substation inspections, Enhanced Transmission, Substation |  | Equipment / facility failure | All Drivers | 2018 | 0.55924 | 0.014362 | 0.83444 | 0.83444 | 0.83444 | Transmission Owner | N/A | Exceeds | GO 174 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 13495.198 | 5410.8105 | 5611.2902 | N/A | N/A | Substation Inspections | 212 | 85 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 9667.808 | 5012.9375 | 5198.6753 | N/A | N/A | Substation Inspections | 54 | 28 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 4164.357 | 4105.7041 | 4257.8273 | N/A | N/A | Substation Inspections | 71 | 70 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1757.465 | 1757.465 | 1822.582 | N/A | N/A | Substation Inspections | 43 | 43 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1757.465 | 1757.465 | 1822.582 | N/A | N/A | Substation Inspections | 43 | 43 | Line Miles = N/A as substation assets are not associated with circuit miles
Asset inspection | Asset Management & Inspections | 7.3.4.15-D | Substation inspections, Enhanced Distribution, Substation | 7.3.4.15-D | 7.3.4.15-D Substation inspections, Enhanced Distribution, Substation | 7.3.4.15-D | 7.3.4.15-D Substation inspections, Enhanced Distribution, Substation |  | Equipment / facility failure | All Drivers | 2018 | 73.5862 | 1.5544 | 174.634 | 174.634 | 174.634 | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 174 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 8147.582 | 2060.1743 | 0 | N/A | N/A | Substation Inspections | 700 | 177 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 6888.384 | 3308.2371 | 0 | N/A | N/A | Substation Inspections | 152 | 73 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 3251.776 | 3205.9763 | 45.7997 | N/A | N/A | Substation Inspections | 71 | 70 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 4397.3044 | 4397.3044 | 51.1314 | N/A | N/A | Substation Inspections | 86 | 86 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 4397.3044 | 4397.3044 | 51.1314 | N/A | N/A | Substation Inspections | 86 | 86 | Line Miles = N/A as substation assets are not associated with circuit miles
Asset inspection | Asset Management & Inspections | 7.3.4.16 | Other, Substation inspections, Generation | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.4.16 | 7.3.4.16, Other, Substation inspections, Generation | Added new Initiative in 2022 | N/A | N/A | 2019 | N/A | N/A | N/A | N/A | N/A | N/A | FRMMA / WMPMA | Exceeds | CAISO Transmission Control Agreement |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | # of Hydroelectric Substations and Powerhouses | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 0 | 0 | 0 |  |  | # of Hydroelectric Substations and Powerhouses | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1483.8958 | 1483.8958 | 1505.3513 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 53 | 53 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1141.3333 | 1141.3333 | 1157.8358 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 51 | 51 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 991.6667 | 991.6667 | 1006.0051 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 51 | 51 | Line Miles = N/A as substation assets are not associated with circuit miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts | 7.3.5.1 | 7.3.5.1 Additional efforts to manage community and environmental impacts | 7.3.5.1 | 7.3.5.1 Additional efforts to manage community and environmental impacts |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - no forecast | N/A - no forecast | In Compliance | GO 95 Rule 35; PRC 4293 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Initiative captures community engagement and environmental support of all vegetation management in T2/T3 areas (distribution, transmission, routine and Enhanced) | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | In 2020 WMP Initiative captures community engagement and environmental support of all vegetation management in T2/T3 areas (distribution, transmission, routine and Enhanced). In 2021 WMP this program was described as being applicable to the entire T&D system. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | In 2020 WMP Initiative captures community engagement and environmental support of all vegetation management in T2/T3 areas (distribution, transmission, routine and Enhanced). In 2021 WMP this program was described as being applicable to the entire T&D system. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | In 2020 WMP Initiative captures community engagement and environmental support of all vegetation management in T2/T3 areas (distribution, transmission, routine and Enhanced). In 2021 WMP this program was described as being applicable to the entire T&D system. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | In 2020 WMP Initiative captures community engagement and environmental support of all vegetation management in T2/T3 areas (distribution, transmission, routine and Enhanced). In 2021 WMP this program was described as being applicable to the entire T&D system.
Vegetation management project | Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | 7.3.5.2 | 7.3.5.2 Detailed inspections of vegetation around distribution electric lines and equipment | 7.3.5.2 | 7.3.5.2 Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | 2022 - 7.3.5.2 includes the following programs: Routine distribution Mid-Cycle (Tree Mortality) EVM Pole Clearing There are also changes to the description of this initiative from Energy Safety (see changes in red) 2021 - 7.3.5.2 included the following programs: Only EVM Patrol Routine distribution Mid-Cycle (Tree Mortality) | Vegetation Contact | No other drivers addressed | <2018 | 4763.5214 | 54.0791 |  | 11252.802 | 3506.954 | 2020 GRC | N/A | In Compliance | GO 95 Rule 35; PRC 4293 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 806068.9253 | 253142 | 256812.559 |  | 25597 | # of circuit miles | 1321894 | 415135.8139 | Initiative captures a portion of routine distribution vegetation management inspections in T2/T3 areas (Routine Distribution) | 0 | 0 | 0 | 1134778.924 | 356373 | 361540.4085 | 81004 | 25439 | # of circuit miles | 1627335 | 511058.4053 | Full Distribution System treated annually | 0 | 0 | 0 | 1379387.0157 | 433191 | 439472.2695 | 81004 | 25439 | # of circuit miles | 1503572 | 472191.103 | Full Distribution System treated annually | 0 | 0 | 0 | 1370788.1352 | 430490.8322 | 436715.2699 | 81004 | 25439 | # of circuit miles | 1648515 | 517709.9043 | Full Distribution System treated annually | 0 | 0 | 0 | 958671.3201 | 301067.1042 | 305420.2131 | 81004 | 25439 | # of circuit miles | 1613583 | 506739.6417 | Full Distribution System treated annually
Vegetation management project | Vegetation Management & Inspections | 7.3.5.3 | Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | 7.3.5.3 | 7.3.5.3 Detailed inspections of vegetation around transmission electric lines and equipment | 7.3.5.3 | 7.3.5.3 Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | 2022 - 7.3.5.3 includes the following programs: Routine NERC Routine Non-NERC ROW Expansion IVM There are also changes to the description of this initiative from Energy Safety (see changes in red) 2021 - 7.3.5.3 included the following programs: Routine NERC Routine Non-NERC ROW Expansion IVM LiDAR midcycle | See initiative 7.3.5.8 | See initiative 7.3.5.8 | <2018 | See initiative 7.3.5.8 | See initiative 7.3.5.8 | See initiative 7.3.5.8 | See initiative 7.3.5.8 | See initiative 7.3.5.8 | Transmission Owner | N/A | In Compliance | GO 95; PRC 4293 |  | RSEs presented are for the year 2022. | 39737.215 | 12095.5523 | 12543.7129 | 98910.881 | 30107.3372 | 31222.8648 |  | 5710 |  | 26828 | 8166.1353 | Initiative captures a portion of routine transmission vegetation management inspections in T2/T3 areas. (Routine Transmission) | 45622.191 | 13886.8714 | 14401.4034 | 114443.617 | 34835.3238 | 36126.0313 | 18161 | 5869 |  | 26322 | 8012.1148 | Applies to all transmission system miles annually | 36682.458 | 11165.7193 | 11579.428 | 157375.864 | 47903.4071 | 49678.3091 | 18161 | 5869 |  | 28218 | 8589.2354 | Applies to all transmission system miles annually | 78701 | 23955.6813 | 24843.2797 | 111609.484 | 33972.6462 | 35231.3901 | 18161 | 5869 |  | 28240 | 8595.9319 | Applies to all transmission system miles annually | 63180 | 19231.267 | 19943.8179 | 115556.208 | 35173.9837 | 36477.2391 | 18161 | 5869 |  | 28240 | 8595.9319 | Applies to all transmission system miles annually
Vegetation management project | Vegetation Management & Inspections | 7.3.5.4 | Emergency response vegetation management due to red flag warning or other urgent climate conditions | 7.3.5.4 | 7.3.5.4 Emergency response vegetation management due to red flag warning or other urgent conditions | 7.3.5.4 | 7.3.5.4 Emergency response vegetation management due to red flag warning or other urgent climate conditions | There are also changes to the description of this initiative from Energy Safety (see changes in red) | N/A | N/A | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | In Compliance | GO 95 Rule 35; PRC 4293 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 3097.6429 | 967.324 | 981.3502 |  | 31307 |  | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 4441.7621 | 1387.062 | 1407.1744 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 5880 | 1836.066 | 1862.689 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 3126.977 | 976.4846 | 990.6035 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 3382.4606 | 1056.2664 | 1071.5389 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile
Vegetation management project | Vegetation Management & Inspections | 7.3.5.5 | Fuel management (including all wood management) and reduction of “slash” from vegetation management activities | 7.3.5.5 | 7.3.5.5 Fuel management and reduction of “slash” from vegetation management activities | 7.3.5.5 | 7.3.5.5 Fuel management (including all wood management) and reduction of “slash” from vegetation management activities | 2022 - 7.3.5.5: Wood management There are also changes to the description of this initiative from Energy Safety (see changes in red) 2021 - 7.3.5.5: Fuel management | N/A - Pilot | N/A - Pilot | <2018 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | 2020 GRC | N/A | Exceeds | GO 95 Rule 35; PRC 4293; PRC 4292 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 69216.4957 | 69216.4957 | 70217.2923 |  | 25597 |  | 0 | 0 |  | 0 | 0 | 0 | 95380.2828 | 95380.2828 | 96759.3798 | N/A | N/A |  | 0 | 0 | PG&E is still in the process of building a framework for fuel reduction work. In 2020, different strategies were discussed and benchmarking with other utility companies was completed. | 0 | 0 | 0 | 61101.1196 | 61101.1196 | 61984.5765 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 92609.6675 | 92609.6675 | 93948.7044 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile | 0 | 0 | 0 | 14447.1723 | 14447.1723 | 14656.063 | N/A | N/A | N/A | 0 | 0 | Not unitized, and not planned by mile
Vegetation management project | Vegetation Management & Inspections | 7.3.5.6 | Improvement of inspections | 7.3.5.6 | 7.3.5.6 Improvement of inspections | 7.3.5.6 | 7.3.5.6 Improvement of inspections | 2022 - 7.3.5.6 includes the following programs: Work Verification Quality Control SVMI Group 2021 - 7.3.5.6: Referenced other sections in 2021 WMP Section 7.3.5.2, 7.3.5.3, 7.3.5.13 and 7.3.5.14 | N/A | N/A | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | In Compliance | GO 95 Rule 35; PRC 4293; PRC 4295 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 31307 |  | 0 | 0 | Initiative captures inspection improvement activities for routine distribution vegetation management in T2/T3 areas | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Determined the line miles are not applicable to this improvement initiative. Alternatively it could apply to all T&D system miles | 0 | 0 | 0 | 65429 | 20432.027 | 20728.2914 | N/A | N/A | N/A | 0 | 0 | Determined the line miles are not applicable to this improvement initiative. Alternatively it could apply to all T&D system miles | 0 | 0 | 0 | 143138.4921 | 44698.9329 | 45345.2318 | N/A | N/A | N/A | 0 | 0 | Determined the line miles are not applicable to this improvement initiative. Alternatively it could apply to all T&D system miles | 0 | 0 | 0 | 52133.0295 | 16279.973 | 16515.3641 | N/A | N/A | N/A | 0 | 0 | Determined the line miles are not applicable to this improvement initiative. Alternatively it could apply to all T&D system miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.7 | Remote sensing inspections of vegetation around distribution electric lines and equipment | 7.3.5.7 | 7.3.5.7 LiDAR inspections of vegetation around distribution electric lines and equipment | 7.3.5.7 | 7.3.5.7 Remote sensing inspections of vegetation around distribution electric lines and equipment | Energy Safety changed the name from "7.3.5.7 LiDAR inspections of vegetation around distribution electric lines and equipment" to "7.3.5.7 Remote sensing inspections of vegetation around distribution electric lines and equipment" See changes in red) | N/A - Pilot | N/A - Pilot | <2018 | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | N/A - Pilot | 2020 GRC | N/A | In Compliance | GO 95 Rule 35; PRC 4293; PRC 4295 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 27034.3666 | 27034.3666 | 27425.2547 |  | 2533 | # of circuit miles | 0 | 0 |  | 0 | 0 | 0 | 4775.2336 | 4775.2336 | 4844.2784 | 0 | 0 | # of circuit miles | 0 | 0 | TBD, per the2021 WMP narrative | 0 | 0 | 0 | 437.9922 | 437.9922 | 444.3251 |  |  | # of circuit miles | 0 | 0 |  | 0 | 0 | 0 | 37090.1758 | 37090.1758 | 37626.4601 | 2000 | 2000 | # of circuit miles | 0 | 0 | Description based on narrative | 0 | 0 | 0 | 14568.8925 | 14568.8925 | 14779.5432 | 4000 | 4000 | # of circuit miles | 0 | 0 | Description based on narrative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.8 | Remote sensing inspections of vegetation around transmission electric lines and equipment | 7.3.5.8 | 7.3.5.8 LiDAR inspections of vegetation around transmission electric lines and equipment | 7.3.5.8 | 7.3.5.8 Remote sensing inspections of vegetation around transmission electric lines and equipment | 2022 - 7.3.5.8 includes: LiDAR (transmission) In addition, Energy Safety changed initiative name from "7.3.5.8 LiDAR inspections of vegetation around transmission electric lines and equipment" to "7.3.5.8 Remote sensing inspections of vegetation around transmission electric lines and equipment". See changes in red. 2021 - 7.3.5.8 included: LiDAR Routine (transmission) LiDAR Mid-Cycle (transmission) | Vegetation Contact | No other drivers addressed | <2018 | 2164.8804 | 0 | 10324.0754 | 6321.644 | 9406.2576 | Transmission Owner | N/A | In Compliance | GO95; PRC 4293; FAC 003-4 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 7287.753 | 2218.3084 | 2300.5005 |  | 5710 | # of circuit miles | 0 | 0 |  | 0 | 0 | 0 | 9927.717 | 3021.8831 | 3133.849 | 18161 | 5869 | # of circuit miles | 0 | 0 | Applies to all transmission system miles annually | 0 | 0 | 0 | 10120.589 | 3080.5912 | 3194.7323 | 17759 | 5869 | # of circuit miles | 0 | 0 | applies to all transmission system miles annually. However, the narrative gives a total miles amount that is short of the total transmission system miles | 0 | 0 | 0 | 13000 | 3957.0508 | 4103.6662 | 17759 | 5869 | # of circuit miles | 0 | 0 | applies to all transmission system miles annually. However, the narrative gives a total miles amount that is short of the total transmission system miles | 0 | 0 | 0 | 13390 | 4075.7623 | 4226.7762 | 17759 | 5869 | # of circuit miles | 0 | 0 | applies to all transmission system miles annually. However, the narrative gives a total miles amount that is short of the total transmission system miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.9 | Other discretionary inspections of vegetation around distribution electric lines and equipment | 7.3.5.9 | 7.3.5.9 Other discretionary inspections of vegetation around distribution electric lines and equipment | 7.3.5.9 | 7.3.5.9 Other discretionary inspections of vegetation around distribution electric lines and equipment | 2022 - 7.3.5.9: CEMA is removed from scope. This initiative references 7.3.5.2. | Vegetation Contact | No other drivers addressed | <2018 See Initiative 7.3.5.3 | 2828.8503 | 0 | 0 | 3140.5168 | 2031.3959 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | Exceeds | GO 95 Rule 35; PRC 4292; PRC 4293; PRC 4295 | 7.3.5.2 Detailed inspections of vegetation around distribution electric lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 25597 |  | 0 | 0 | Represents inspection for dead and dying trees due to drought; all distribution HFTD miles inspected annually (CEMA program) | 0 | 0 | 0 | 0 | 0 | 0 | 81004 | 25439 |  | 0 | 0 | Applies to all distribution system miles annually | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0
Vegetation management project | Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment | 7.3.5.10 | 7.3.5.10 Other discretionary inspections of vegetation around transmission electric lines and equipment | 7.3.5.10 | 7.3.5.10 Other discretionary inspections of vegetation around transmission electric lines and equipment |  | N/A - Complementary | N/A - Complementary | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | 7.3.5.3 Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 5710 |  | 0 | 0 | Initiative captures the very limited volume of non-routine transmission vegetation management inspections in T2/T3 areas. | 0 | 0 | 0 | 0 | 0 | 0 | 18161 | 5869 |  | 0 | 0 | Applies to all transmission system miles annually | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3 for a description of PG&E’s additional vegetation management practices around transmission lines beyond regulatory requirements | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3 for a description of PG&E’s additional vegetation management practices around transmission lines beyond regulatory requirements | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3 for a description of PG&E’s additional vegetation management practices around transmission lines beyond regulatory requirements
Vegetation management project | Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment | 7.3.5.11 | 7.3.5.11 Patrol inspections of vegetation around distribution electric lines and equipment | 7.3.5.11 | 7.3.5.11 Patrol inspections of vegetation around distribution electric lines and equipment |  | N/A - Complementary | N/A - Complementary | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | 7.3.5.2 Detailed inspections of vegetation around distribution electric lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 25597 |  | 0 | 0 | Initiative captures direct vegetation management inspection costs for distribution lines in T2/T3 areas (Routine Distribution, Enhanced Vegetation Management, and CEMA / Tree Mortality) | 0 | 0 | 0 | 0 | 0 | 0 | 81004 | 25439 |  | 0 | 0 | Applies to all distribution system miles annually | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please see Section 7.3.5.2 (distribution inspections) above for a discussion of PG&E’s vegetation inspection programs for distribution facilities. There is no specific program to perform “patrols” around distribution lines unique from the inspections described in Section 7.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please see Section 7.3.5.2 (distribution inspections) above for a discussion of PG&E’s vegetation inspection programs for distribution facilities. There is no specific program to perform “patrols” around distribution lines unique from the inspections described in Section 7.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please see Section 7.3.5.2 (distribution inspections) above for a discussion of PG&E’s vegetation inspection programs for distribution facilities. There is no specific program to perform “patrols” around distribution lines unique from the inspections described in Section 7.3.5.2
Vegetation management project | Vegetation Management & Inspections | 7.3.5.12 | Patrol inspections of vegetation around transmission electric lines and equipment | 7.3.5.12 | 7.3.5.12 Patrol inspections of vegetation around transmission electric lines and equipment | 7.3.5.12 | 7.3.5.12 Patrol inspections of vegetation around transmission electric lines and equipment |  | N/A - Complementary | N/A - Complementary | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | See Initiative 7.3.5.3 | 7.3.5.3 Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 8243 |  | 0 | 0 | Initiative captures direct routine transmission vegetation management inspection costs for lines in T2/T3 areas. (Routine Transmission) | 0 | 0 | 0 | 0 | 0 | 0 | 20724 | 7510 |  | 0 | 0 | Applies to whole transmission system and Distribution EVM Line Miles | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3. There is no specific program to perform patrols around transmission lines unique from the inspections described in Section 7.3.5.3. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3. There is no specific program to perform patrols around transmission lines unique from the inspections described in Section 7.3.5.3. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Please refer to Section 7.3.5.3. There is no specific program to perform patrols around transmission lines unique from the inspections described in Section 7.3.5.3.
Vegetation management project | Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections | 7.3.5.13 | 7.3.5.13 Quality assurance / quality control of vegetation inspections | 7.3.5.13 | 7.3.5.13 Quality assurance / quality control of vegetation inspections | 2022 - 7.3.5.13: References Initiative 7.3.5.2 for financials | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | In Compliance | GO 95 Rule 35; PRC 4293 | 7.3.5.2 Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 31307 |  | 0 | 0 | Quality costs reflected here include quality efforts to support multiple programs: EVM, Routine & CEMA on both transmission and distribution Miles considered N/A as this program validates work on mileage from multiple programs. (Routine Distribution) | 0 | 0 | 0 | 0 | 0 | 0 | 99165 | 31307 |  | 0 | 0 | Line miles treated would apply to both T&D routine programs | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this audit initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this audit initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this audit initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel | 7.3.5.14 | 7.3.5.14 Recruiting and training of vegetation management personnel | 7.3.5.14 | 7.3.5.14 Recruiting and training of vegetation management personnel | 2022 - 7.3.5.14: References Initiative 7.3.5.2 for financials | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | N/A | N/A | 7.3.5.2 Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 31307 |  | 0 | 0 | Recruiting costs reflected here support all vegetation management programs. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | Determined the line miles are not applicable to this improvement initiative. Alternatively it could apply to all T&D system miles | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this training initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this training initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an appropriate metric for this training initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.15 | Identification and remediation of "at-risk species" | 7.3.5.15 | 7.3.5.15 Remediation of at-risk species | 7.3.5.15 | 7.3.5.15 Identification and remediation of "at-risk species" | 2022 - 7.3.5.15: Initiative references Initiatives 7.3.5.2 and 7.3.5.3. Energy Safety changed title of initiative from "7.3.5.15 Remediation of at-risk species" to "7.3.5.15 Identification and remediation of "at-risk species". See changes in red. 2021 - 7.3.5.15 included: EVM TAT | Vegetation Contact | No other drivers addressed | 2018 | 2.1828 | 0 | 1.7489e-05 | 2.3933 | 1.6446 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | Exceeds | GO 95 Rule 35; PRC 4293 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 2533 |  | 0 | 0 | Represents enhanced vegetation management tree trimming work in T2/T3 areas. | 0 | 0 | 0 | 0 | 0 | 0 | 1878 | 1878 |  | 1878 | 1878 | This programs is planned and tracked using miles as updated in the 2021 WMP | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 |  | 1800 | 1800 | Miles is the metric for this initiative | 0 | 0 | 0 | 0 | 0 | 0 | 1890 | 1890 |  | 1890 | 1890 | Miles is the metric for this initiative | 0 | 0 | 0 | 0 | 0 | 0 | 1890 | 1890 |  | 1890 | 1890 | Miles is the metric for this initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment | 7.3.5.16 | 7.3.5.16 Removal and remediation of trees with strike potential to electric lines and equipment | 7.3.5.16 | 7.3.5.16 Removal and remediation of trees with strike potential to electric lines and equipment | 2022 - 7.3.5.16 includes: Initiative references 7.3.5.2 and 7.3.5.3 2021 - 7.3.5.16 included: Referenced 7.3.5.2, 7.3.5.3, and 7.3.5.15 | N/A - Complementary | N/A - Complementary | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | See Initiatives 7.3.5.2 and 7.3.5.3 | 7.3.5.2 Detailed inspections of vegetation around distribution electric lines and equipment, and 7.3.5.3 Detailed inspections of vegetation around transmission electric lines and equipment | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 141 |  | 0 | 0 | Represents Transmission ROW clearing; for 2019 plan the actual miles is estimated | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A |  | 0 | 0 | PG&E does not perform a separate effort to identify, remove and remediate trees with strike potential. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | PG&E does not perform a separate effort to identify, remove and remediate trees with strike potential. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | PG&E does not perform a separate effort to identify, remove and remediate trees with strike potential. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | PG&E does not perform a separate effort to identify, remove and remediate trees with strike potential.
Vegetation management project | Vegetation Management & Inspections | 7.3.5.17.1 | Substation inspection , Distribution substation | 7.3.5.17.1 | 7.3.5.17.1 Substation inspection , Distribution substation | 7.3.5.17.1 | 7.3.5.17.1 Substation inspection , Distribution substation |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | Exceeds | GO 95 Rule 35; PRC 4293; NERC Standard FAC-003-4 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 211.8192 | 66.5479 | 0.039217 |  | N/A | # of Distribution Substations | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 207.8645 | 65.3055 | 0.038484 | N/A | N/A | # of Distribution Substations | 0 | 0 | Line miles treated is not an appropriate metric for substation related investments | 0 | 0 | 0 | 536.678 | 536.678 | 4.0657 | N/A | N/A | # of Distribution Substations | 0 | 0 | Should say 170 substations | 0 | 0 | 0 | 552.779 | 552.779 | 4.1877 | N/A | N/A | # of Distribution Substations | 133 | 132 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 569.363 | 569.363 | 4.3134 | N/A | N/A | # of Distribution Substations | 133 | 132 | Line Miles = N/A as substation assets are not associated with circuit miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.17.2 | Substation inspection, Transmission substation | 7.3.5.17.2 | 7.3.5.17.2 Substation inspection , Transmission substation | 7.3.5.17.2 | 7.3.5.17.2 Substation inspection, Transmission substation |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | Transmission Owner | N/A | Exceeds | GO 95 Rule 35; PRC 4293; NERC Standard FAC-003-4 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 104.68 | 31.8634 | 33.044 |  | N/A | # of Transmission Substations | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 147.654 | 44.9442 | 46.6094 | N/A | N/A | # of Transmission Substations | 0 | 0 | Line miles treated is not an appropriate metric for substation related investments | 0 | 0 | 0 | 226.153 | 226.153 | 234.5324 | N/A | N/A | # of Transmission Substations | 0 | 0 | Should say 79 substations | 0 | 0 | 0 | 232.938 | 232.938 | 241.5687 | N/A | N/A | # of Transmission Substations | 55 | 55 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 239.926 | 239.926 | 248.8157 | N/A | N/A | # of Transmission Substations | 55 | 55 | Line Miles = N/A as substation assets are not associated with circuit miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.17.3 | Substation inspection, Generation substation | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.5.17.3 | 7.3.5.17.3 Substation inspection, Generation substation | Added new Initiative in 2022 | N/A | N/A | 2019 | N/A | N/A | N/A | N/A | N/A | N/A | FRMMA / WMPMA | In Compliance | NERC Standard FAC-003-3 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | # of Hydroelectric Substations and Powerhouses | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | # of Hydroelectric Substations and Powerhouses | 0 | 0 |  | 0 | 0 | 0 | 2158.6661 | 2158.6661 | 2189.8781 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 62 | 62 | Should say 64 substations | 0 | 0 | 0 | 1766.3333 | 1766.3333 | 1791.8726 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 60 | 60 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1786.6667 | 1786.6667 | 1812.5 | N/A | N/A | # of Hydroelectric Substations and Powerhouses | 60 | 60 | Line Miles = N/A as substation assets are not associated with circuit miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.18.1 | Substation vegetation management, Maintenance substation distribution | 7.3.5.18.1 | 7.3.5.18.1 Substation vegetation management, Maintenance substation distribution | 7.3.5.18.1 | 7.3.5.18.1 Substation vegetation management, Maintenance substation distribution |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | FRMMA / WMPMA | Exceeds | GO 95 Rule 35; PRC 4293; NERC Standard FAC-003-4 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2727.533 | 1709.384 | 1734.0999 |  | N/A |  | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 2676.609 | 1677.469 | 1701.7234 | N/A | N/A |  | 0 | 0 | Line miles treated is not an appropriate metric for substation related investments | 0 | 0 | 0 | 2314.258 | 2314.258 | 2347.7197 | N/A | N/A | Tags | 0 | 0 | Should say 166 substations | 0 | 0 | 0 | 1265.501 | 1265.501 | 1283.7988 | N/A | N/A | Tags | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 1302.003 | 1302.003 | 1320.8286 | N/A | N/A | Tags | 0 | 0 | No specific targets associated with this initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.18.2 | Substation vegetation management, Maintenance substation transmission | 7.3.5.18.2 | 7.3.5.18.2 Substation vegetation management, Maintenance substation transmission | 7.3.5.18.2 | 7.3.5.18.2 Substation vegetation management, Maintenance substation transmission |  | N/A | No other drivers addressed | <2018 | N/A | N/A | N/A | N/A | N/A | Transmission Owner | N/A | In Compliance | GO 95 Rule 35; PRC 4293; NERC Standard FAC-003-3 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1217.6491 | 856.4361 | 888.1685 |  | N/A |  | 0 | 0 | Line Miles = N/A as substation assets are not associated with circuit miles | 0 | 0 | 0 | 1717.5268 | 1208.0268 | 1252.7862 | N/A | N/A |  | 0 | 0 | Line miles treated is not an appropriate metric for substation related investments | 0 | 0 | 0 | 1670.4913 | 1670.4913 | 1732.3859 | N/A | N/A | Tags | 0 | 0 | Should say 79 substations | 0 | 0 | 0 | 1252.9987 | 1252.9987 | 1299.4245 | N/A | N/A | Tags | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 1252.9987 | 1252.9987 | 1299.4245 | N/A | N/A | Tags | 0 | 0 | No specific targets associated with this initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.18.3 | Substation vegetation management, Maintenance substation Generation | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.5.18.3 | 7.3.5.18.3 Substation vegetation management, Maintenance substation Generation | Added new Initiative in 2022 | N/A | N/A | 2019 | N/A | N/A | N/A | N/A | N/A | See initiative 7.3.5.17.3 | See initiative 7.3.5.17.3 | In Compliance | GO 95 Rule 35; PRC 4293; NERC Standard FAC-003-3 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Tags | 62 | 62 | Should say 64 substations | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Tags | 61 | 61 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Tags | 61 | 61 | No specific targets associated with this initiative
Vegetation management project | Vegetation Management & Inspections | 7.3.5.19 | Vegetation management system | 7.3.5.19 | 7.3.5.19 Vegetation inventory system | 7.3.5.19 | 7.3.5.19 Vegetation management system | 2022 - 7.3.5.19: Energy Safety changed name of Initiative from "7.3.5.19 Vegetation inventory system" to "7.3.5.19 Vegetation management system". See changes in red. | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | 25597 |  | 0 | 0 | Initiative captures vegetation management IT support costs across multiple vegetation management programs | 0 | 0 | 0 | 0 | 0 | 0 | 99165 | 31307 |  | 0 | 0 | Line miles treated would apply to both T&D routine programs | 0 | 0 | 0 | 8962.0837 | 2814.5085 | 2855.2033 | N/A | N/A | N/A | 0 | 0 | This enterprise system would apply to the whole system, but line miles is not an appropriate metric | 0 | 0 | 0 | 92516.1157 | 29054.3364 | 29474.4311 | N/A | N/A | N/A | 0 | 0 | This enterprise system would apply to the whole system, but line miles is not an appropriate metric | 0 | 0 | 0 | 8792.936 | 2761.3883 | 2801.315 | N/A | N/A | N/A | 0 | 0 | This enterprise system would apply to the whole system, but line miles is not an appropriate metric
Vegetation management project | Vegetation Management & Inspections | 7.3.5.20 | Additional vegetation management practices beyond regulatory requirements and recommendations | 7.3.5.20 | 7.3.5.20 Vegetation management to achieve clearances around electric lines and equipment | 7.3.5.20 | 7.3.5.20 Additional vegetation management practices beyond regulatory requirements and recommendations | 2022 - 7.3.5.20: Utility defensible space spend shifted from 7.3.3.12.1 and 7.3.3.12.2 to 7.3.5.20. Energy Safety changed name of Initiative from "7.3.5.20 Vegetation management to achieve clearances around electric lines and equipment" to "7.3.5.20 Additional vegetation management practices beyond regulatory requirements and recommendations". See changes in red. | N/A | N/A | 2021 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 13363.3195 | 4173.0642 | 4233.4023 |  | 31307 | # of distribution poles | 0 | 0 | Initiative captures tree trimming activities within multiple vegetation management programs in T2/T3 areas (Routine Distribution, Transmission, Enhanced, Tree Mortality) | 0 | 0 | 0 | 7971.0423 | 2489.1773 | 2525.1681 | 99165 | 31307 | # of distribution poles | 0 | 0 | Line miles treated would apply to both T&D routine programs | 0 | 0 | 0 | 18784.8196 | 5866.0768 | 5950.894 | N/A | N/A | # of distribution poles | 0 | 0 | work under this initiative has variable activities and units of measure | 0 | 0 | 0 | 32353.9608 | 10103.4146 | 10249.4991 | N/A | N/A | # of distribution poles | 0 | 0 | work under this initiative has variable activities and units of measure | 0 | 0 | 0 | 7076.6439 | 2209.8768 | 2241.8293 | N/A | N/A | # of distribution poles | 0 | 0 | work under this initiative has variable activities and units of measure
Vegetation management project | Vegetation Management & Inspections | 7.3.5.21 | Vegetation management activities post-fire | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.5.21 | 7.3.5.21 Vegetation management activities post-fire | New initiative from Energy Safety in 2022. See change in red. | N/A | N/A | See Initiative 7.3.5.2 | N/A | N/A | N/A | N/A | N/A | See Initiative 7.3.5.2 | See Initiative 7.3.5.2 | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | No specific targets associated with this initiative
Other | Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations | 7.3.6.1 | 7.3.6.1 Automatic recloser operations | 7.3.6.1 | 7.3.6.1 Automatic recloser operations |  | N/A | N/A | 2018 | N/A | N/A | N/A | N/A | N/A | N/A - no forecast | N/A - no forecast | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Entire Distribution system enabled in 2020, work started in 2018 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.2 | Crew-accompanying ignition prevention and suppression resources and services | 7.3.6.2 | 7.3.6.2 Crew-accompanying ignition prevention and suppression resources and services | 7.3.6.2 | 7.3.6.2 Crew-accompanying ignition prevention and suppression resources and services |  | Consequence - Financial | No other consequences reflected | 2018 | 0.71408 | 0 | 0.066674 | 0.81573 | 0.44133 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 385.4115 | 385.4115 | 390.9842 | 7750.9584 | 7750.9584 | 7863.029 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 752.3551 | 752.3551 | 763.2334 | 9205.1416 | 9205.1416 | 9338.2381 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 35.1233 | 35.1233 | 35.6311 | 10267.2076 | 10267.2076 | 10415.6605 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 690.0377 | 690.0377 | 700.0149 | 14524.0149 | 14524.0149 | 14734.0167 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 143.4995 | 143.4995 | 145.5743 | 15083.2779 | 15083.2779 | 15301.366 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk | 7.3.6.3 | 7.3.6.3 Personnel work procedures and training in conditions of elevated fire risk | 7.3.6.3 | 7.3.6.3 Personnel work procedures and training in conditions of elevated fire risk |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1384.7294 | 1384.7294 | 1404.7511 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 839.8231 | 839.8231 | 851.966 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 966.4419 | 966.4419 | 980.4156 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1000 | 1000 | 1014.4589 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1030 | 1030 | 1044.8927 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.4-D | Protocols for PSPS re-energization, Distribution | 7.3.6.4-D | 7.3.6.4-D Protocols for PSPS re-energization, Distribution | 7.3.6.4-D | 7.3.6.4-D Protocols for PSPS re-energization, Distribution | 2022 - 7.3.6.4-D: Some of the customer impact mitigation programs moved to 7.3.3.11.1 to better align with the narrative. | Consequence - PSPS | No other consequences reflected | 2018 | 1.7858 | 0 | 1.7858 | 1.7858 | 1.7858 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 756.8257 | 756.8257 | 767.7686 | 739.8956 | 739.8956 | 750.5937 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1376.1542 | 1376.1542 | 1396.0519 | 7610.4654 | 7610.4654 | 7720.5046 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1215.9062 | 1215.9062 | 1233.4869 | 8794.8573 | 8794.8573 | 8922.0216 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 4940.315 | 4940.315 | 5011.7467 | 10093.2135 | 10093.2135 | 10239.1506 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 3250.143 | 3250.143 | 3297.1366 | 8620.9611 | 8620.9611 | 8745.611 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.4-T | Protocols for PSPS re-energization, Transmission | 7.3.6.4-T | 7.3.6.4-T Protocols for PSPS re-energization, Transmission | 7.3.6.4-T | 7.3.6.4-T Protocols for PSPS re-energization, Transmission |  | Consequence - PSPS | No other consequences reflected | 2018 | 3.1359 | 0 | 3.1359 | 3.1359 | 3.1359 | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1774.2242 | 1774.2242 | 1839.9622 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1208.096 | 1208.096 | 1252.858 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1349.7304 | 1349.7304 | 1399.7402 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 2000 | 2000 | 2074.1034 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 2000 | 2000 | 2074.1034 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.5-D | PSPS events and mitigation of PSPS impacts , Distribution | 7.3.6.5-D | 7.3.6.5-D PSPS events and mitigation of PSPS impacts , Distribution | 7.3.6.5-D | 7.3.6.5-D PSPS events and mitigation of PSPS impacts , Distribution |  | Equipment Failure, Vegetation | No other drivers addressed | 2018 | N/A | N/A | N/A | N/A | N/A | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 178868.2005 | 178868.2005 | 181454.4437 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 80703.3268 | 80703.3268 | 81870.2107 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 35313.6331 | 35313.6331 | 35824.2305 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 68814.333 | 68814.333 | 69809.3148 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 70943.6296 | 70943.6296 | 71969.3988 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.5-T | PSPS events and mitigation of PSPS impacts , Transmission | 7.3.6.5-T | 7.3.6.5-T PSPS events and mitigation of PSPS impacts , Transmission | 7.3.6.5-T | 7.3.6.5-T PSPS events and mitigation of PSPS impacts , Transmission |  | Equipment Failure, Vegetation | No other drivers addressed | 2018 | N/A | N/A | N/A | N/A | N/A | Transmission Owner | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 16255.2054 | 16255.2054 | 16857.4882 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 2406.708 | 2406.708 | 2495.8806 | N/A | N/A | N/A | 0 | 0 | Units provided are number of events “forecasted”. Number of miles impacted will be dependent on scope of events. Line miles provided are for the entire Z1 T2 T3 Transmission system. | 0 | 0 | 0 | 1209.142 | 1209.142 | 1253.9428 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1807.925 | 1807.925 | 1874.9117 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1807.925 | 1807.925 | 1874.9117 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.6 | Stationed and on-call ignition prevention and suppression resources and services | 7.3.6.6 | 7.3.6.6 Stationed and on-call ignition prevention and suppression resources and services | 7.3.6.6 | 7.3.6.6 Stationed and on-call ignition prevention and suppression resources and services |  | Consequence - Financial | No other consequences reflected | 2018 | 0.71408 | 0 | 0.066674 | 0.81573 | 0.44133 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 128.4705 | 128.4705 | 130.3281 | 2583.6528 | 2583.6528 | 2621.0097 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 250.785 | 250.785 | 254.4111 | 3068.3805 | 3068.3805 | 3112.746 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 11.7078 | 11.7078 | 11.877 | 3422.4025 | 3422.4025 | 3471.8868 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 230.0126 | 230.0126 | 233.3383 | 4841.3383 | 4841.3383 | 4911.3389 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 47.8332 | 47.8332 | 48.5248 | 5027.7593 | 5027.7593 | 5100.4553 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.7 | Other, Aviation Support | 7.3.6.7 | 7.3.6.7 Other, Aviation Support | 7.3.6.7 | 7.3.6.7 Other, Aviation Support |  | Consequence - PSPS | No other consequences reflected | <2018 | 32.2052 | 0 | 32.2052 | 32.2052 | 32.2052 | 2020 GRC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A |  | 0 | 0 |  | 0 | 0 | 0 | 5398 | 5398 | 5476.0493 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 285 | 285 | 289.1208 | 3349 | 3349 | 3397.423 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 325 | 325 | 329.6992 | 6142 | 6142 | 6230.8068 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 24500 | 24500 | 24854.2438 | 5723 | 5723 | 5805.7485 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Grid Operations & Operating Protocols | 7.3.6.8 | Protective equipment and device settings | N/A - Not in 2021 WMP | N/A - Not in 2021 WMP | 7.3.6.8 | 7.3.6.8 Protective equipment and device settings | New initiative from Energy Safety in 2022. See change in red. | All Drivers | No other drivers addressed | 2021 | 103.9514 | 0 | 2.3059 | 120.8047 | 60.7525 | N/A | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | Initiative had not begun | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | Initiative had not begun | 2742.1862 | 2742.1862 | 2781.8353 | 18211.1575 | 18211.1575 | 18474.4714 | 11500 | 11500 | N/A | 0 | 0 | Narrative describes line miles associated with the activated circuits | 0 | 0 | 0 | 142592.2 | 142592.2 | 144653.9309 | 25734 | 25734 | N/A | 0 | 0 | Narrative describes line miles associated with the activated circuits | 0 | 0 | 0 | 140510.67 | 140510.67 | 142542.3042 | 25734 | 25734 | N/A | 0 | 0 | Narrative describes line miles associated with the activated circuits
Other | Data Governance | 7.3.7.1 | Centralized repository for data | 7.3.7.1 | 7.3.7.1 Centralized repository for data | 7.3.7.1 | 7.3.7.1 Centralized repository for data |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 758.3188 | 758.3188 | 769.2833 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 666.2762 | 666.2762 | 675.9098 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 779.4454 | 779.4454 | 790.7154 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 857.7958 | 857.7958 | 870.1986 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 883.5297 | 883.5297 | 896.3046 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire | 7.3.7.2 | 7.3.7.2 Collaborative research on utility ignition and/or wildfire | 7.3.7.2 | 7.3.7.2 Collaborative research on utility ignition and/or wildfire |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC, EPIC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 695.354 | 695.354 | 705.4081 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 985.249 | 985.249 | 999.4946 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 994.427 | 994.427 | 1008.8054 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 866 | 866 | 878.5214 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Data Governance | 7.3.7.3 | Documentation and disclosure of wildfire-related data and algorithms | 7.3.7.3 | 7.3.7.3 Documentation and disclosure of wildfire-related data and algorithms | 7.3.7.3 | 7.3.7.3 Documentation and disclosure of wildfire-related data and algorithms |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 947.943 | 947.943 | 961.6493 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 931.0686 | 931.0686 | 944.5309 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 995.7826 | 995.7826 | 1010.1806 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1047.3536 | 1047.3536 | 1062.4972 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1078.7742 | 1078.7742 | 1094.3721 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Data Governance | 7.3.7.4 | Tracking and analysis of near miss data | 7.3.7.4 | 7.3.7.4 Tracking and analysis of near miss data | 7.3.7.4 | 7.3.7.4 Tracking and analysis of near miss data |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 153.3257 | 153.3257 | 155.5426 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 631.7019 | 631.7019 | 640.8356 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 650.6529 | 650.6529 | 660.0607 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 670.1725 | 670.1725 | 679.8625 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Data Governance | 7.3.7.5 | Other, IT projects to support wildfire mitigation work | 7.3.7.5 | 7.3.7.5 Other, IT projects to support wildfire mitigation work | 7.3.7.5 | 7.3.7.5 Other, IT projects to support wildfire mitigation work |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | WMCE and Transmission Owner | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 27283.5563 | 27283.5563 | 27678.0474 | 9316.7949 | 9316.7949 | 9451.5058 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 32178.3272 | 32178.3272 | 32643.5915 | 23179.6683 | 23179.6683 | 23514.8216 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 51741.0219 | 51741.0219 | 52489.1419 | 40129.2822 | 40129.2822 | 40709.5088 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 49300.0264 | 49300.0264 | 50012.8521 | 45100.0056 | 45100.0056 | 45752.1035 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 35300 | 35300 | 35810.4003 | 36700 | 36700 | 37230.6428 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Resource allocation methodology | 7.3.8.1 | Allocation methodology development and application | 7.3.8.1 | 7.3.8.1 Allocation methodology development and application | 7.3.8.1 | 7.3.8.1 Allocation methodology development and application |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 921.4123 | 287.7363 | 291.8967 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 5710.4034 | 1783.2306 | 1809.0142 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1776.0833 | 554.6309 | 562.6503 | 6208.3813 | 1938.7379 | 1966.77 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 4382.394 | 1368.5231 | 1388.3105 | 3485.7611 | 1088.5248 | 1104.2637 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 564.2835 | 176.213 | 178.7609 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Resource allocation methodology | 7.3.8.2 | Risk reduction scenario development and analysis | 7.3.8.2 | 7.3.8.2 Risk reduction scenario development and analysis | 7.3.8.2 | 7.3.8.2 Risk reduction scenario development and analysis |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 100.3542 | 31.3384 | 31.7915 | 53.729 | 16.7784 | 17.021 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1039.5227 | 324.6196 | 329.3132 | 77.5158 | 24.2064 | 24.5564 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1006.5347 | 314.3182 | 318.8629 | 53.3266 | 16.6527 | 16.8935 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 909.8101 | 284.1132 | 288.2212 | 62.1916 | 19.421 | 19.7019 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 1061.1252 | 331.3655 | 336.1567 | 64.0574 | 20.0037 | 20.2929 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Resource allocation methodology | 7.3.8.3 | Risk spend efficiency analysis (RSE) | 7.3.8.3 | 7.3.8.3 Risk spend efficiency analysis | 7.3.8.3 | 7.3.8.3 Risk spend efficiency analysis (RSE) |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 103.9062 | 32.4476 | 32.9167 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 263.9438 | 82.4237 | 83.6155 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 956.594 | 298.7228 | 303.042 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 933.7633 | 291.5933 | 295.8094 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 783.7633 | 244.7517 | 248.2905 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration | 7.3.9.1 | 7.3.9.1 Adequate and trained workforce for service restoration | 7.3.9.1 | 7.3.9.1 Adequate and trained workforce for service restoration |  | All Consequences | All Consequences | <2018 | 68.9708 | 0 | 4.6405 | 78.9126 | 42.2983 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 9204.2186 | 9204.2186 | 9337.3018 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 8674.0874 | 8674.0874 | 8799.5055 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 7947.3524 | 7947.3524 | 8062.2626 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 7666.0593 | 7666.0593 | 7776.9023 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 7896.041 | 7896.041 | 8010.2094 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts | 7.3.9.2 | 7.3.9.2 Community outreach, public awareness, and communications efforts | 7.3.9.2 | 7.3.9.2 Community outreach, public awareness, and communications efforts |  | All Consequences | All Consequences | <2018 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.2 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.3 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.4 | 2020 GRC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 20394.114 | 20394.114 | 20688.9911 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 22942.9399 | 22942.9399 | 23274.6703 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 20751.9809 | 20751.9809 | 21052.0324 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 21739.4284 | 21739.4284 | 22053.7573 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 21374.1553 | 21374.1553 | 21683.2028 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.3 | Customer support in emergencies | 7.3.9.3 | 7.3.9.3 Customer support in emergencies | 7.3.9.3 | 7.3.9.3 Customer support in emergencies |  | All Consequences | All Consequences | <2018 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.2 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.3 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.4 | Emergency Consumer Protections | ECPMA FRMMA / WMPMA | In Compliance | Gas & Electric Rule 1; Gas & Electric Rule 6; Gas & Electric Rule 11; Gas & Electric Rule 19.1; Gas & Electric Rule 19.2; Gas & Electric Rule 19.3; Electric Rule 12; Electric Rule 13; Electric Rule 15; Electric Rule 16; Electric Rule 21 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2578.7053 | 2578.7053 | 2615.9906 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 3938.9336 | 3938.9336 | 3995.8863 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 2442.1174 | 2442.1174 | 2477.4278 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 3413.3412 | 3413.3412 | 3462.6945 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 3582.8169 | 3582.8169 | 3634.6206 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.4 | Disaster and emergency preparedness plan | 7.3.9.4 | 7.3.9.4 Disaster and emergency preparedness plan | 7.3.9.4 | 7.3.9.4 Disaster and emergency preparedness plan |  | All Consequences | All Consequences | <2018 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.2 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.3 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.4 | 2020 GRC | FRMMA / WMPMA | In Compliance | GO 166 Standards 1-13 |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1289.0715 | 1289.0715 | 1307.7101 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1557.0173 | 1557.0173 | 1579.5301 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 5643.612 | 5643.612 | 5725.2126 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 6843.4437 | 6843.4437 | 6942.3926 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 7048.747 | 7048.747 | 7150.6644 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.5 | Preparedness and planning for service restoration | 7.3.9.5 | 7.3.9.5 Preparedness and planning for service restoration | 7.3.9.5 | 7.3.9.5 Preparedness and planning for service restoration |  | All Consequences | All Consequences | <2018 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.2 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.3 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.4 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 189.1269 | 189.1269 | 191.8615 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 16156.1589 | 16156.1589 | 16389.7597 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 16467.4266 | 16467.4266 | 16705.528 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 15794.469 | 15794.469 | 16022.8402 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 16716.448 | 16716.448 | 16958.15 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Emergency planning and preparedness | 7.3.9.6 | Protocols in place to learn from wildfire events | 7.3.9.6 | 7.3.9.6 Protocols in place to learn from wildfire events | 7.3.9.6 | 7.3.9.6 Protocols in place to learn from wildfire events |  | All Consequences | All Consequences | <2018 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.1 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.2 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.3 | See 7.3.9.1. All EP&R costs and risk reduction have been combined as one RSE reflected in 7.3.9.4 | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 552.4592 | 552.4592 | 560.4472 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 667.2931 | 667.2931 | 676.9415 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1148.3742 | 1148.3742 | 1164.9785 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1235.8906 | 1235.8906 | 1253.7602 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 1272.9673 | 1272.9673 | 1291.3731 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement | 7.3.10.1 | 7.3.10.1 Community engagement | 7.3.10.1 | 7.3.10.1 Community engagement |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 19980.6211 | 19980.6211 | 20269.5196 | N/A | N/A | # of meetings | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 21811.6767 | 21811.6767 | 22127.0503 | N/A | N/A | # of meetings | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 19643.3108 | 19643.3108 | 19927.332 | N/A | N/A | # of meetings | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 20615.9564 | 20615.9564 | 20914.0411 | N/A | N/A | # of meetings | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 20216.9795 | 20216.9795 | 20509.2955 | N/A | N/A | # of meetings | 0 | 0 | Line miles is not an applicable metric
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA | 7.3.10.2 | 7.3.10.2 Cooperation and best practice sharing with agencies outside CA | 7.3.10.2 | 7.3.10.2 Cooperation and best practice sharing with agencies outside CA |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 134.745 | 134.745 | 136.6933 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 225 | 225 | 228.2533 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 193.2407 | 193.2407 | 196.0347 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 204.6708 | 204.6708 | 207.6301 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.3 | Cooperation with suppression agencies | 7.3.10.3 | 7.3.10.3 Cooperation with suppression agencies | 7.3.10.3 | 7.3.10.3 Cooperation with suppression agencies |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | N/A | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 1337.9408 | 1337.9408 | 1357.286 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 3858.6212 | 3858.6212 | 3914.4128 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 4258.2642 | 4258.2642 | 4319.8341 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 4532.2125 | 4532.2125 | 4597.7434 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 4668.1789 | 4668.1789 | 4735.6757 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.4 | Forest service and fuel reduction cooperation and joint roadmap | 7.3.10.4 | 7.3.10.4 Forest service and fuel reduction cooperation and joint roadmap | 7.3.10.4 | 7.3.10.4 Forest service and fuel reduction cooperation and joint roadmap |  | N/A - Foundational | N/A - Foundational | <2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC, Transmission Owner | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 2357.4014 | 728.5419 | 755.5356 | N/A | N/A | N/A | 0 | 0 | The data in this section is for the USFS program described in 5.3.10.4. Other activities in Section 5.3.10.4 are not tracked as separate costs; these activities are generally performed by internal sources as an ancillary function to their regular tasks | 0 | 0 | 0 | 5114.9445 | 1581.0027 | 1639.5816 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 4420.1345 | 1366.2406 | 1416.8622 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 5132.6675 | 1586.4693 | 1645.2507 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 5136.6475 | 1587.6808 | 1646.5071 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.5 | Other, PMO and General Wildfire Support | 7.3.10.5 | 7.3.10.5 Other, PMO and General Wildfire Support | 7.3.10.5 | 7.3.10.5 Other, PMO and General Wildfire Support |  | N/A - Foundational | N/A - Foundational | 2018 | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | N/A - Foundational | 2020 GRC | FRMMA / WMPMA | N/A | N/A |  | RSEs presented are for the year 2022. | 0 | 0 | 0 | 21505.3579 | 21505.3579 | 21816.3024 | N/A | N/A | N/A | 0 | 0 | Represents the costs of the CWSP Program Management Office (PMO) which aggregates a number of other initiatives including public outreach, benchmarking, governance and other activities. | 0 | 0 | 0 | 24849.4976 | 24849.4976 | 25208.7948 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 26581.8864 | 26581.8864 | 26966.2321 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 24192.6411 | 24192.6411 | 24542.4409 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric | 0 | 0 | 0 | 17473.2686 | 17473.2686 | 17725.9134 | N/A | N/A | N/A | 0 | 0 | Line miles is not an applicable metric
Table 12 comments:
Initiatives showing "Line Miles Treated" measured in "Alternative Units" are derived from the annual forecasted budget for that initiative which can include the costs of new installations as well as the forecasted costs for ongoing Operations & Maintenance and Repairs. 7.3.3.3 and 7.3.3.16 - These initiatives have been disaggregated in response to Revision Notice 22-13. The mileages and costs included in these initiatives are provided as a directional view and are not meant to be targets for the WMP. The disaggregated mileage and costs are included in the totals for Section 7.3.3.17.1 and and therefore should not be added to the total WMP forecast for 2022 and 2023. 7.3.3.17.1 - This initiative represents the total total forecasted mileage and costs for the System Hardening Program. We have included disaggregated line removal information, where available, within this initiative in red in response to Revision Notice 22-13. Line removal is included in this section because line removal is not a separate 2022 WMP initiative. The 2022 line removal mileage and costs provided are year-to-date actuals as of 6/21/22 and not forecasts. 7.3.3.17.5 - The CAPEX costs and RSE values for this initiative has been disaggregated in response to Revision Notice 22-13. We have updated the 2022 forecasted units to align with our 2022 WMP Target of 2 stand alone power systems (SPS). For 2023 we have updated units and CAPEX forecasts to align with the 2023 GRC forecasts. The 2022 and 2023 forecasted costs were not explicitly budgeted for within 7.3.3.17.1 . These forecasted costs for 2022 and 2023 were only separated out for purposes of responding to Revision Notice 22-13 and other system hardening initiatives are planned to be offsets to complete this work. These forecasted costs should not be added to the total WMP SH forecast for 2022 and 2023.
Detailed notes on Table 12 data can be found in the Section 7.3.a in the 2022 Wildfire Mitigation Plan.