## Project List_Updated
Order | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2023 Forecast Miles | 2024-2026 Forecast Miles | Div | Region | City | County | Latitude | Longitude | Circuit Protection Zone (V2) | 2021-2023 Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | 2024-2026 Risk Rank (V3) | v3 Mean Risk | Measured Effectiveness | Project Type (see 3rd tab for description) | HFTD Tier | Unique ID
35117455 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.172 | - | - | 1.172 | 1.172 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.594 |  | 2141 | 0.0062243 |  | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 1
35118673 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.6064 | - | - | 2.6064 | 2.6064 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8005 | -121.6047 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 2
35118674 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5212 | - | - | 2.5212 | 2.5212 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.6017 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 3
35126752 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.5909 | - | - | 1.5909 | 1.5909 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7333 | -121.6353 |  | 817 | 0.090831 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 4
35127550 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.9189 | - | - | 2.9189 | 2.9189 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7858 | -121.6004 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 5
35144480 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.7155 | - | - | 3.7155 | 3.7155 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8116 | -121.5956 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 6
35227400 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.233 | - | - | 3.233 | 3.233 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7712 | -121.6031 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 7
35227401 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.7701 | - | - | 1.7701 | 1.7701 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7628 | -121.6233 |  | 2922 | 3.3375e-05 |  | 69 | 0.020609 | 99% | Butte Rebuild | Tier 2 | 8
35227402 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.404 | - | - | 1.404 | 1.404 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6071 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 9
35227404 | Community Rebuild | 95F | ESTS | ESTIMATING | 0.99697 | - | - | 0.99697 | 0.99697 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7538 | -121.6172 |  | 2941 | 2.9018e-05 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 10
35227405 | Community Rebuild | 95F | PEND | PERMITTING/DEPENDENCY | 0.41477 | - | - | 0.41477 | 0.41477 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7578 | -121.6071 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 11
35227406 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.8989 | - | - | 2.8989 | 2.8989 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7523 | -121.6185 |  | 2467 | 0.0021 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 12
35227408 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.1447 | - | - | 2.1447 | 2.1447 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7524 | -121.6126 |  | 2941 | 2.9018e-05 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | HFRA | 13
35227409 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.646 | - | - | 3.646 | 3.646 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7501 | -121.6242 |  | 2467 | 0.0021 |  | 1178 | 0.0017042 | 99% | Butte Rebuild | Tier 2 | 14
35227411 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.3665 | - | - | 3.3665 | 3.3665 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7595 | 121.6024 |  | 2912 | 4.1187e-05 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 15
35227412 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.2926 | - | - | 1.2926 | 1.2926 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.769 | -121.5786 |  | 2954 | 2.3677e-05 |  | 622 | 0.0042646 | 99% | Butte Rebuild | Tier 2 | 16
35227413 | Community Rebuild | 95F | ESTS | ESTIMATING | 4.1278 | - | - | 4.1278 | 4.1278 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7423 | -121.6423 |  | 734 | 0.10501 |  | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 17
35227415 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.2267 | - | - | 5.2267 | 5.2267 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7389 | -121.6402 |  | 2924 | 3.2259e-05 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 18
35227417 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.7458 | - | - | 5.7458 | 5.7458 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7323 | -121.6513 |  | 734 | 0.10501 |  | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 19
35246308 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.3438 | - | - | 2.3438 | 2.3438 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7572 | -121.5722 |  | 2126 | 0.0064968 |  | 1617 | 0.00084939 | 99% | Butte Rebuild | Tier 2 | 20
35246309 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.2898 | - | - | 1.2898 | 1.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7752 | -121.6093 |  | 2813 | 0.0002457 |  | 1546 | 0.00092573 | 99% | Butte Rebuild | Tier 2 | 21
35246316 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.5938 | - | - | 3.5938 | 3.5938 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7265 | -121.6374 |  | 817 | 0.090831 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 22
35246589 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.0511 | - | - | 1.0511 | 1.0511 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.764 | -121.5986 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 23
35246590 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.2388 | - | - | 2.2388 | 2.2388 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7696 | -121.579 |  | 2383 | 0.0027 |  | 2198 | 0.00043536 | 99% | Butte Rebuild | Tier 2 | 24
35246591 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.2898 | - | - | 4.2898 | 4.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7485 | -121.6086 |  | 2941 | 2.9018e-05 |  | 1563 | 0.00090699 | 99% | Butte Rebuild | Tier 2 | 25
35246598 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.4871 | - | - | 3.4871 | 3.4871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8149 | -121.5802 |  | 2211 | 0.0048412 |  | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 26
35352072 | Community Rebuild | 08W | ESTS | ESTIMATING | 0.56818 | - | - | 0.56818 | 0.56818 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6265 |  | 2910 | 4.2503e-05 |  | 26 | 0.026975 | 99% | Butte Rebuild | Tier 2 | 27
35353399 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.2386 | - | - | 3.2386 | 3.2386 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.5973 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 28
35353463 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.8871 | - | - | 4.8871 | 4.8871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8121 | -121.5914 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 29
35353466 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.4148 | - | - | 2.4148 | 2.4148 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8091 | -121.5998 |  | 2849 | 0.00016422 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 30
35353467 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5544 | - | - | 2.5544 | 2.5544 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8182 | -121.5952 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 31
35321894 | Fire Rebuild | 08W | ESTS | Estimating | 0.087121 | - | - | 0.087121 | 0.087121 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0773 | -122.2434 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 32
35334404 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.6 | - | - | 0.6 | 0.6 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0671 | -122.2231 |  | 1393 | 0.033758 |  | 2485 | 0.00031335 | 99% | FRRB | Tier 2 | 33
35298571 | Base SH | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.469 | -122.2542 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | 99% | CWSP 2022-2023 | Tier 2 | 34
35331305 | Base SH | 08W | UNSE | Scoping/Scoped | 0.445 | - | - | 0.445 | 0.445 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4699 | -122.2473 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | 99% | CWSP - 2023 ICUG | Tier 2 | 35
35311895 | Base SH | 08W | UNSE | Scoping/Scoped | 2.78 | - | - | 2.78 | 2.78 | - | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 36
35330815 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4792 | -122.2645 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 37
35277925 | Base SH | 08W | PEND | Permitting/Dependency | 0.21326 | - | - | 0.21326 | 0.21326 | - | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0746 | -119.4845 |  | 63 | 0.39206 |  | 2126 | 0.00047477 | 99% | CWSP 2022-2023 | Tier 2 | 38
35277924 | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | - | 0.12955 | 0.23864 | 0.23864 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0071 | -119.4086 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 39
35277938 | Base SH | 08W | ESTS | Estimating | 0.38996 | - | 0.27973 | 0.6697 | 0.6697 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0125 | -119.4038 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 40
35278093 | Base SH | 08W | ESTS | Estimating | 0.41496 | - | 0.52008 | 0.93504 | 0.93504 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9797 | -119.3677 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 41
35333501 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9851 | -121.1296 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 42
35333503 | Base SH | 08W | UNSE | Scoping/Scoped | 0.3 | 1.44 | - | 1.74 | 1.74 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9959 | -121.1355 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 43
35333504 | Base SH | 08W | UNSE | Scoping/Scoped | 0.45 | - | - | 0.45 | 0.45 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9992 | -121.1363 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 44
35311896 | Base SH | 08W | UNSE | Scoping/Scoped | 2.76 | - | - | 2.76 | 2.76 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9961 | -121.1091 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 45
35314415 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | 0.04 | - | 2.09 | 2.09 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9962 | -121.1167 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 46
35314416 | Base SH | 08W | UNSE | Scoping/Scoped | 1.1199 | 0.48011 | - | 1.6 | 1.6 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9981 | -121.1168 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 47
35334232 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9855 | -121.1087 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 48
35334234 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9781 | -121.1088 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 49
35318074 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.072 | -122.2298 |  | 2246 | 0.0041981 |  | 936 | 0.002497 | 99% | FRRB | Tier 2 | 50
35342335 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.5299 | - | - | 1.5299 | 1.5299 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1672 | -122.2131 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 51
35342336 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1699 | -122.2026 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 52
35342337 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.52008 | - | - | 0.52008 | 0.52008 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1657 | -122.2231 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 53
35342338 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.163 | -122.1902 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 54
35311924 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.08447 | - | - | 0.08447 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6747 | -121.3798 |  | 1288 | 0.040961 |  | 267 | 0.010152 | 99% | FRRB | Tier 3 | 55
35292784 | Fire Rebuild | 08W | ESTS | Estimating | 3.0644 | - | - | 3.0644 | 3.0644 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | 99% | FRRB | Tier 2 | 56
35292788 | Fire Rebuild | 08W | ESTS | Estimating | 1.1 | - | - | 1.1 | 1.1 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | 99% | FRRB | Tier 2 | 57
35286103 | Base SH | 08W | UNSE | Scoping/Scoped | 3.0701 | - | - | 3.0701 | 3.0701 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 58
35311596 | Base SH | 08W | UNSE | Scoping/Scoped | 3 | - | - | 3 | 3 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 59
35311626 | Base SH | 08W | UNSE | Scoping/Scoped | 3.64 | - | - | 3.64 | 3.64 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 60
35311627 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | - | - | 2.05 | 2.05 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 61
35279181 | Fire Rebuild | 08W | ESTS | Estimating | 5.589 | - | - | 5.589 | 5.589 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 62
35279182 | Fire Rebuild | 08W | ESTS | Estimating | 2.0701 | - | - | 2.0701 | 2.0701 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 63
35280560 | Fire Rebuild | 08W | ESTS | Estimating | 2.64 | - | - | 2.64 | 2.64 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 64
35320445 | Base SH | 08W | UNSE | Scoping/Scoped | 17.7201 | - | - | 17.7201 | 17.7201 | - | LP | Region 4 - Central Coast | Buellton | SANTA BARBARA | 34.6236 | -120.185 |  | 307 | 0.21085 |  | 2847 | 0.00018253 | 99% | CWSP - 2023 ICUG | Tier 2 | 65
35299634 | Base SH | 08W | UNSE | Scoping/Scoped | 2.61 | - | - | 2.61 | 2.61 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6568 | -121.5763 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 66
35329014 | Base SH | 08W | UNSE | Scoping/Scoped | 3.1701 | - | - | 3.1701 | 3.1701 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6666 | -121.5712 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 67
35329012 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6201 | - | - | 1.6201 | 1.6201 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6908 | -121.5733 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 68
35329013 | Base SH | 08W | UNSE | Scoping/Scoped | 1.85 | 0.039962 | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6805 | -121.5693 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 69
35299633 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | - | - | 2.14 | 2.14 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6766 | -121.5675 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 70
35299635 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6988 | -121.5743 |  | 1535 | 0.025936 |  | 47 | 0.022808 | 99% | PSPS | Tier 2 | 71
35329016 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.709 | -121.5757 |  | 1535 | 0.025936 |  | 47 | 0.022808 | 99% | PSPS | Tier 2 | 72
35329009 | Base SH | 08W | UNSE | Scoping/Scoped | 0.94091 | - | 0.020076 | 0.96098 | 0.96098 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.655 | -121.5839 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 73
35329010 | Base SH | 08W | UNSE | Scoping/Scoped | 2.814 | - | 0.020076 | 2.8341 | 2.8341 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6564 | -121.5838 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 74
35329011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3229 | - | - | 2.3229 | 2.3229 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6667 | -121.5826 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 75
35299631 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4299 | - | - | 3.4299 | 3.4299 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6474 | -121.6306 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 76
35299629 | Base SH | 08W | UNSE | Scoping/Scoped | 0.89091 | - | - | 0.89091 | 0.89091 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.654 | -121.6323 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 77
35329008 | Base SH | 08W | UNSE | Scoping/Scoped | 0.31307 | - | - | 0.31307 | 0.31307 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6413 | -121.6413 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 78
35334228 | Base SH | 08W | UNSE | Scoping/Scoped | 1.89 | - | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8468 | -122.589 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 79
35334229 | Base SH | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8493 | -122.6179 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 80
35334230 | Base SH | 08W | UNSE | Scoping/Scoped | 1.64 | - | - | 1.64 | 1.64 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8348 | -122.6319 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 81
35311897 | Base SH | 08W | UNSE | Scoping/Scoped | 2.11 | - | - | 2.11 | 2.11 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 82
35311898 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.9193 | -122.4369 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 83
35340270 | Base SH | 08W | UNSE | Scoping/Scoped | 1.84 | - | - | 1.84 | 1.84 | - | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 84
35340271 | Base SH | 08W | UNSE | Scoping/Scoped | 1.96 | - | - | 1.96 | 1.96 | - | NV | Region 2 - North East | Corning | Tehama | 39.9043 | -122.5022 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 85
35340272 | Base SH | 08W | UNSE | Scoping/Scoped | 1.56 | - | - | 1.56 | 1.56 | - | NV | Region 2 - North East | Corning | Tehama | 39.8887 | -122.5232 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 86
35340273 | Base SH | 08W | UNSE | Scoping/Scoped | 1.4299 | - | - | 1.4299 | 1.4299 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8831 | -122.5469 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 87
35340274 | Base SH | 08W | UNSE | Scoping/Scoped | 1.59 | - | - | 1.59 | 1.59 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 88
35311899 | Base SH | 08W | UNSE | Scoping/Scoped | 3.44 | - | - | 3.44 | 3.44 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 89
35316561 | Base SH | 08W | UNSE | Scoping/Scoped | 4.41 | - | - | 4.41 | 4.41 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 90
35332218 | Base SH | 08W | UNSE | Scoping/Scoped | 3.26 | - | - | 3.26 | 3.26 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3986 | -122.3143 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 91
35332213 | Base SH | 08W | UNSE | Scoping/Scoped | 2.37 | - | - | 2.37 | 2.37 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3892 | -122.3258 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 92
35332214 | Base SH | 08W | UNSE | Scoping/Scoped | 4.04 | - | - | 4.04 | 4.04 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3899 | -122.3499 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 93
35332215 | Base SH | 08W | UNSE | Scoping/Scoped | 2.26 | - | - | 2.26 | 2.26 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4149 | -122.3421 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 94
35332216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.4042 | -122.3264 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 95
35332217 | Base SH | 08W | UNSE | Scoping/Scoped | 3.03 | - | 0.053 | 3.083 | 3.083 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3886 | -122.3831 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 96
35316567 | Base SH | 08W | UNSE | Scoping/Scoped | 3.42 | - | - | 3.42 | 3.42 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 97
35316569 | Base SH | 08W | UNSE | Scoping/Scoped | 4.81 | - | 0.032 | 4.842 | 4.842 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 98
35312540 | Base SH | 08W | UNSE | Scoping/Scoped | 4.88 | - | - | 4.88 | 4.88 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 99
35312541 | Base SH | 08W | UNSE | Scoping/Scoped | 0.43 | - | - | 0.43 | 0.43 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9777 | -120.3274 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 100
35332868 | Base SH | 08W | UNSE | Scoping/Scoped | 2.53 | - | - | 2.53 | 2.53 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9803 | -120.337 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 101
74010582 | Other | 30A | PEND | Permitting/Dependency | 1.3299 | - | - | 1.3299 | 1.3299 | - | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 |  | 811 | 0.092281 |  | 1184 | 0.0016787 | 99% | Other | Tier 2 | 102
35284023 | Fire Rebuild | 08W | DCNL | CLOSED | 1.1699 | - | - | 1.1699 | 1.1699 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4361 | -122.5779 |  | 1684 | 0.019316 |  | 732 | 0.0035071 | 99% | FRRB - UG - 2021 | Tier 3 | 103
35228774 | Base SH | 08W | ESTS | Estimating | 1.0008 | - | - | 1.0008 | 1.0008 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1091 | 0.0019786 | 99% | PSPS - Community Resiliency | Tier 2 | 104
35228775 | Base SH | 08W | ESTS | Estimating | 0.90341 | - | - | 0.90341 | 0.90341 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1232 | 0.0015282 | 99% | PSPS - Community Resiliency | Tier 2 | 105
35223063 | Base SH | 08W | ESTS | Estimating | 0.3197 | - | - | 0.3197 | 0.3197 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1567 | 0.00090511 | 99% | PSPS - Community Resiliency | Tier 2 | 106
35312542 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | SO | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3791 | -122.5192 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 107
35343741 | Base SH | 08W | UNSE | Scoping/Scoped | 0.58 | - | - | 0.58 | 0.58 | - | SO | Region 1 - North Coast | Sonoma | SONOMA | 38.3371 | -122.4929 |  | 1827 | 0.01369 |  | 1080 | 0.0020136 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 108
35285594 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | SI | Region 2 - North East | Twin Bridges | EL DORADO | 38.8075 | -120.0935 |  | 2005 | 0.0089565 |  | 2299 | 0.00038767 | 99% | FRRB | Tier 2 | 109
74001486 | Other | 30A | ADER | Estimating | 1.4576 | - | - | 1.4576 | 1.4576 | - | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 |  | 2792 | 0.00031068 |  | 2633 | 0.00025777 | 99% | Other | Tier 2 & 3 | 110
35058026 | Base SH | 08W | PEND | Permitting/Dependency | 0.6267 | - | - | 0.6267 | 0.6267 | - | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7593 | -120.5087 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | 99% | CWSP 2022-2023 | Tier 3 | 111
35312543 | Base SH | 08W | UNSE | Scoping/Scoped | 3.71 | - | - | 3.71 | 3.71 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5896 | -122.5395 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 112
35332360 | Base SH | 08W | UNSE | Scoping/Scoped | 5.46 | - | - | 5.46 | 5.46 | - | NV | Region 2 - North East | Willows | GLENN | 39.456 | -122.5138 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 113
35332362 | Base SH | 08W | UNSE | Scoping/Scoped | 3.83 | - | - | 3.83 | 3.83 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4286 | -122.5052 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 114
35332363 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | - | 1.13 | 1.13 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4073 | -122.5471 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 115
35332364 | Base SH | 08W | UNSE | Scoping/Scoped | 0.085 | - | 0.6 | 0.685 | 0.685 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.3944 | -122.5518 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 116
35330812 | Base SH | 08W | UNSE | Scoping/Scoped | 2.49 | - | - | 2.49 | 2.49 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5561 | -122.5414 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 117
35316278 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4868 | -122.5188 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 118
35312544 | Base SH | 08W | UNSE | Scoping/Scoped | 0.44 | - | - | 0.44 | 0.44 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5927 | -122.5431 |  | 206 | 0.25426 |  | 1350 | 0.0012407 | 99% | PSPS - 2023 ICUG | Tier 2 | 119
35312545 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8586 | -121.0805 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 120
35325589 | Base SH | 08W | UNSE | Scoping/Scoped | 1.21 | - | - | 1.21 | 1.21 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8537 | -121.0803 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 121
35325590 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8575 | -121.0758 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 122
35326790 | Base SH | 08W | UNSE | Scoping/Scoped | 0.14792 | - | - | 0.14792 | 0.14792 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8934 | -121.0677 |  | 2980 | 1.7619e-05 |  | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 123
35312546 | Base SH | 08W | UNSE | Scoping/Scoped | 1.013 | - | - | 1.013 | 1.013 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8933 | -121.0676 |  | 2980 | 1.7619e-05 |  | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 124
35320444 | Base SH | 08W | UNSE | Scoping/Scoped | 7.4 | - | - | 7.4 | 7.4 | - | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.3203 | -120.6932 |  | 1104 | 0.056447 |  | 1903 | 0.00059698 | 99% | PSPS - 2023 ICUG | Tier 2 | 125
35284810 | Fire Rebuild | 08W | ESTS | Estimating | 0.85814 | - | - | 0.85814 | 0.85814 | - | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.2086 | -122.3251 |  | 2186 | 0.0054078 |  | 2174 | 0.00044555 | 99% | FRRB | Tier 2 | 126
35283198 | Base SH | 08W | ESTS | Estimating | 0.27803 | - | - | 0.27803 | 0.27803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.108 | -122.9558 |  | 58 | 0.39723 |  | 486 | 0.0056859 | 99% | CWSP 2022-2023 | Tier 2 | 127
35231620 | Base SH | 08W | PEND | Permitting/Dependency | 2.6782 | - | - | 2.6782 | 2.6782 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | 0.5487 |  | 29 | 0.026126 | 99% | Top 250 Miles | Tier 2 & 3 | 128
35329471 | Base SH | 08W | UNSE | Scoping/Scoped | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9373 | -122.6091 |  | 3243 | 5.4342e-06 |  | 1561 | 0.00090896 | 99% | PSPS - 2023 ICUG | Tier 2 | 129
35320447 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | 1.09 | - | 1.93 | 1.93 | - | SI | Region 2 - North East | Granite Bay | PLACER | 38.782 | -121.1456 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 130
35339664 | Base SH | 08W | UNSE | Scoping/Scoped | 0.17 | 0.75 | - | 0.92 | 0.92 | - | SI | Region 2 - North East | Loomis | PLACER | 38.7815 | -121.1632 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 131
35339665 | Base SH | 08W | UNSE | Scoping/Scoped | 0.69 | - | - | 0.69 | 0.69 | - | SI | Region 2 - North East | Loomis | PLACER | 38.767 | -121.1635 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 132
35342143 | Base SH | 08W | UNSE | Scoping/Scoped | 3.354 | - | 1.962 | 5.316 | 5.316 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2645 | -122.1722 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 133
35342144 | Base SH | 08W | UNSE | Scoping/Scoped | 1.802 | - | 1.046 | 2.848 | 2.848 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2553 | -122.1615 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 134
35342145 | Base SH | 08W | UNSE | Scoping/Scoped | 0.163 | - | 0.13 | 0.293 | 0.293 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2566 | -122.1697 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 135
35342146 | Base SH | 08W | UNSE | Scoping/Scoped | 2.386 | - | 1.875 | 4.261 | 4.261 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.262 | -122.1635 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 136
35342147 | Base SH | 08W | UNSE | Scoping/Scoped | 1.865 | - | 1.343 | 3.208 | 3.208 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2706 | -122.167 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 137
35342148 | Base SH | 08W | UNSE | Scoping/Scoped | 1.265 | - | 1.095 | 2.36 | 2.36 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2714 | -122.1672 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 138
35342151 | Base SH | 08W | UNSE | Scoping/Scoped | 0.08 | - | 0.085 | 0.165 | 0.165 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2491 | -122.1769 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 139
35320442 | Base SH | 08W | UNSE | Scoping/Scoped | 0.578 | - | 0.464 | 1.052 | 1.052 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2515 | -122.161 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 140
35320462 | Base SH | 08W | UNSE | Scoping/Scoped | 0.35 | - | - | 0.35 | 0.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2642 | -122.1295 |  | 1848 | 0.012819 |  | 8953 | 2.3644e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 141
35320460 | Base SH | 08W | UNSE | Scoping/Scoped | 1.78 | - | - | 1.78 | 1.78 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3063 | -122.1288 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 142
35320461 | Base SH | 08W | UNSE | Scoping/Scoped | 3.56 | - | - | 3.56 | 3.56 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.299 | -122.1519 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 143
35338404 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | 0.56 | 1.59 | 1.59 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3141 | -122.1263 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 144
35338405 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2972 | -122.1262 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 145
35338406 | Base SH | 08W | UNSE | Scoping/Scoped | 1.14 | - | - | 1.14 | 1.14 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2877 | -122.1043 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 146
35338407 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66 | - | 0.41 | 1.07 | 1.07 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3039 | -122.0964 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 147
35338408 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | 0.09 | 1.22 | 1.22 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3148 | -122.0962 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 148
35338409 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2968 | -122.1356 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 149
35338410 | Base SH | 08W | UNSE | Scoping/Scoped | 2.21 | - | - | 2.21 | 2.21 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2925 | -122.1292 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 150
35339293 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | NB | Region 2 - North East | Fairfield | SOLANO | 38.3158 | -122.1039 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 151
35320463 | Base SH | 08W | UNSE | Scoping/Scoped | 1.44 | - | - | 1.44 | 1.44 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.284 | -122.128 |  | 419 | 0.17457 |  | 987 | 0.0022992 | 99% | PSPS - 2023 ICUG | Tier 2 | 152
35337014 | Base SH | 08W | UNSE | Scoping/Scoped | 0.02 | 0.83 | - | 0.85 | 0.85 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2525 | -122.144 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 153
35337015 | Base SH | 08W | UNSE | Scoping/Scoped | 0.49 | - | - | 0.49 | 0.49 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2533 | -122.1356 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 154
35312548 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4517 | -122.3081 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 155
35339282 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4516 | -122.3245 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 156
35339283 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 157
35339285 | Base SH | 08W | UNSE | Scoping/Scoped | 2.32 | - | - | 2.32 | 2.32 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 158
35339286 | Base SH | 08W | UNSE | Scoping/Scoped | 2.54 | - | - | 2.54 | 2.54 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4362 | -122.3535 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 159
35339287 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4427 | -122.3927 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 160
35339288 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4403 | -122.4075 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 161
35339289 | Base SH | 08W | UNSE | Scoping/Scoped | 1.82 | - | - | 1.82 | 1.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4493 | -122.4078 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 162
35337008 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4409 | -122.3061 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 163
35337010 | Base SH | 08W | UNSE | Scoping/Scoped | 3.82 | - | - | 3.82 | 3.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4416 | -122.3258 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 164
35337011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.89 | - | - | 2.89 | 2.89 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4406 | -122.3414 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 165
35337012 | Base SH | 08W | UNSE | Scoping/Scoped | 4.92 | - | - | 4.92 | 4.92 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.443 | -122.3663 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 166
35317480 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4488 | -122.3179 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 167
35317887 | Base SH | 08W | UNSE | Scoping/Scoped | 0.8 | - | - | 0.8 | 0.8 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4377 | -122.3878 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 168
35312549 | Base SH | 08W | UNSE | Scoping/Scoped | 0.98 | - | - | 0.98 | 0.98 | - | NV | Region 2 - North East | Redding | SHASTA | 40.4913 | -122.2744 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 169
35332866 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4668 | -122.3357 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 170
35337163 | Base SH | 08W | ESTS | Estimating | 1.39 | 0.49 | - | 1.88 | 1.88 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.97 | -121.2606 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 171
35320449 | Base SH | 08W | ESTS | Estimating | 1.84 | - | - | 1.84 | 1.84 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9755 | -121.2772 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 172
35320312 | Base SH | 08W | ESTS | Estimating | 2.04 | - | - | 2.04 | 2.04 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9507 | -121.219 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 173
35332958 | Base SH | 08W | ESTS | Estimating | 1.37 | - | - | 1.37 | 1.37 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9431 | -121.219 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 174
35320450 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | 0.02 | - | 2.16 | 2.16 | - | SI | Region 2 - North East | Lincoln | PLACER | 39.0041 | -121.2605 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 175
35274589 | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | - | - | 2.132 | 2.132 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5186 | -119.9402 |  | 428 | 0.17286 |  | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 176
35274593 | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | - | - | 2.756 | 2.756 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5165 | -119.9716 |  | 428 | 0.17286 |  | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 | 177
35280362 | Base SH | 08W | ESTS | Estimating | 0.1089 | - | - | 0.1089 | 0.1089 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9483 |  | 50 | 0.4205 |  | 400 | 0.0069412 | 99% | Top 250 Miles | Tier 2 & 3 | 178
35226621 | Base SH | 08W | PEND | Permitting/Dependency | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 179
35192282 | Base SH | 08W | PEND | Permitting/Dependency | 2.04 | - | - | 2.04 | 2.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 180
35174478 | Base SH | 08W | PEND | Permitting/Dependency | 1.04 | - | - | 1.04 | 1.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 181
35226873 | Base SH | 08W | UNSE | Scoping/Scoped | 1.0394 | - | - | 1.0394 | 1.0394 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 182
35226878 | Base SH | 08W | PEND | Permitting/Dependency | 0.58883 | - | - | 0.58883 | 0.58883 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 183
35227001 | Base SH | 08W | PEND | Permitting/Dependency | 0.7214 | - | - | 0.7214 | 0.7214 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 184
35227002 | Base SH | 08W | PEND | Permitting/Dependency | 0.43295 | - | - | 0.43295 | 0.43295 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 185
35227003 | Base SH | 08W | PEND | Permitting/Dependency | 0.58087 | - | - | 0.58087 | 0.58087 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 186
35227007 | Base SH | 08W | PEND | Permitting/Dependency | 2.8756 | - | - | 2.8756 | 2.8756 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 187
35227015 | Base SH | 08W | CONS | In-Construction | 0.01572 | 0.80947 | - | 0.82519 | 0.82519 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 188
35227025 | Base SH | 08W | ESTS | Estimating | 1.1828 | - | - | 1.1828 | 1.1828 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 189
35234756 | Base SH | 08W | ESTS | Estimating | 2.782 | - | - | 2.782 | 2.782 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 190
35234758 | Base SH | 08W | PEND | Permitting/Dependency | 0.58201 | - | - | 0.58201 | 0.58201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 191
35234862 | Base SH | 08W | PEND | Permitting/Dependency | 0.079924 | - | - | 0.079924 | 0.079924 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 192
35234865 | Base SH | 08W | PEND | Permitting/Dependency | 0.64754 | - | - | 0.64754 | 0.64754 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 193
35227160 | Base SH | 08W | PEND | Permitting/Dependency | 1.3201 | - | - | 1.3201 | 1.3201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | 0.91632 |  | 392 | 0.007089 | 99% | Top 50 Miles | Tier 2 | 194
35217271 | Base SH | 08W | PEND | Permitting/Dependency | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 195
35220895 | Base SH | 08W | PEND | Permitting/Dependency | 1.9299 | - | - | 1.9299 | 1.9299 | - | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 196
35228186 | Base SH | 08W | APPR | Estimating | 1.49 | - | - | 1.49 | 1.49 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 197
35056808 | Other | 30A | PEND | Permitting/Dependency | 1.5138 | - | - | 1.5138 | 1.5138 | - | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 |  | 534 | 0.14747 |  | 1720 | 0.00074971 | 99% | Other | Tier 3 | 198
35305303 | Base SH | 08W | ESTS | Estimating | 1.065 | - | - | 1.065 | 1.065 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8972 | -120.989 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 199
35305308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66799 | - | - | 0.66799 | 0.66799 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8944 | -120.9647 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 200
35293662 | Base SH | 08W | ESTS | Estimating | 0.5 | - | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8956 | -120.9606 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 201
35293663 | Base SH | 08W | ESTS | Estimating | 0.98996 | - | - | 0.98996 | 0.98996 | - | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8964 | -120.922 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 202
35293665 | Base SH | 08W | ESTS | Estimating | 0.41572 | - | 0.070833 | 0.48655 | 0.48655 | - | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 203
35293670 | Base SH | 08W | UNSE | Scoping/Scoped | 0.54394 | - | - | 0.54394 | 0.54394 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8805 | -120.9418 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 204
35223032 | Base SH | 08W | ESTS | Estimating | 0.84924 | - | - | 0.84924 | 0.84924 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8855 | -121.0156 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | PSPS - Community Resiliency | Tier 2 | 205
35293508 | Base SH | 08W | ESTS | Estimating | 0.51004 | - | - | 0.51004 | 0.51004 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8729 | -120.991 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 206
35301112 | Base SH | 08W | ESTS | Estimating | 0.45 | 0.05 | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8641 | -120.9817 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 207
35300933 | Base SH | 08W | ESTS | Estimating | 0.77992 | - | - | 0.77992 | 0.77992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8775 | -120.993 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 208
35254067 | Base SH | 08W | ESTS | Estimating | 0.43996 | 0.039962 | - | 0.47992 | 0.47992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 209
35320464 | Base SH | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4267 | -122.2656 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 210
35338402 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4214 | -122.2578 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 211
35224856 | Other | 10K | APPR | Estimating | 2.803 | 0.10985 | - | 2.9129 | 1.7765 | - | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | 99% | Other | Tier 2 & 3 | 212
35219543 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24 | - | - | 0.24 | 0.24 | - | SI | Region 2 - North East | Placerville | EL DORADO | 38.7293 | -120.7998 |  | 2123 | 0.0065148 |  | 1979 | 0.00055552 | 99% | PSPS - Community Resiliency | Tier 2 | 213
35297464 | Fire Rebuild | 08W | ESTS | Estimating | 0.56818 | - | - | 0.56818 | 0.56818 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0777 | -122.2439 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 214
35293846 | Base SH | 08W | ESTS | Estimating | 0.85985 | - | - | 0.85985 | 0.85985 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3008 | -123.0524 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 215
35290504 | Base SH | 08W | ESTS | Estimating | 0.61004 | - | - | 0.61004 | 0.61004 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2145 | -123.0742 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 216
35290508 | Base SH | 08W | ESTS | Estimating | 0.62008 | - | - | 0.62008 | 0.62008 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1987 | -123.0496 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 217
35290808 | Base SH | 08W | ESTS | Estimating | 0.24508 | - | - | 0.24508 | 0.24508 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2815 | -123.1027 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 218
35285064 | Base SH | 08W | ADER | Estimating | 0.58636 | - | - | 0.58636 | 0.58636 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3076 | -123.1132 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | 99% | CWSP 2022-2023 | Tier 2 | 219
35312550 | Base SH | 08W | UNSE | Scoping/Scoped | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 220
35317399 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 221
35330211 | Base SH | 08W | UNSE | Scoping/Scoped | 1.97 | - | - | 1.97 | 1.97 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.5858 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 222
35330213 | Base SH | 08W | UNSE | Scoping/Scoped | 5.26 | - | - | 5.26 | 5.26 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.5887 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 223
35330215 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0669 | -122.5993 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 224
35330216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0696 | -122.585 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 225
35330217 | Base SH | 08W | UNSE | Scoping/Scoped | 0.28 | - | - | 0.28 | 0.28 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0506 | -122.5833 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 226
35330219 | Base SH | 08W | UNSE | Scoping/Scoped | 3.13 | - | - | 3.13 | 3.13 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0688 | -122.6043 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 227
35330241 | Base SH | 08W | UNSE | Scoping/Scoped | 2.855 | - | - | 2.855 | 2.855 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0823 | -122.6045 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 228
35329472 | Base SH | 08W | UNSE | Scoping/Scoped | 2.869 | - | - | 2.869 | 2.869 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0748 | -122.6503 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 229
35329473 | Base SH | 08W | UNSE | Scoping/Scoped | 4.761 | - | - | 4.761 | 4.761 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0654 | -122.6333 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 230
35312551 | Base SH | 08W | UNSE | Scoping/Scoped | 3.205 | - | - | 3.205 | 3.205 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0837 | -122.66 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 231
35312552 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.023 | -122.6779 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 232
35330244 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0531 | -122.6813 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 233
35330245 | Base SH | 08W | UNSE | Scoping/Scoped | 0.09 | - | - | 0.09 | 0.09 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0541 | -122.6767 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 234
35330246 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | - | 1.03 | 1.03 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.6814 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 235
35330247 | Base SH | 08W | UNSE | Scoping/Scoped | 0.75 | - | - | 0.75 | 0.75 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.04 | -122.6823 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 236
35330248 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4 | - | - | 2.4 | 2.4 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0296 | -122.6802 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 237
35330249 | Base SH | 08W | UNSE | Scoping/Scoped | 4 | 0.25 | - | 4.25 | 4.25 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.6799 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 238
35329474 | Base SH | 08W | UNSE | Scoping/Scoped | 0.11 | 1.16 | - | 1.27 | 1.27 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0932 | -122.6804 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 239
35317398 | Base SH | 08W | UNSE | Scoping/Scoped | 3.52 | - | - | 3.52 | 3.52 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0581 | -122.693 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 240
35312558 | Base SH | 08W | UNSE | Scoping/Scoped | 0.71004 | - | - | 0.71004 | 0.71004 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0269 | -122.663 |  | 371 | 0.18973 |  | 407 | 0.0068603 | 99% | PSPS - 2023 ICUG | Tier 2 | 241
35335235 | Base SH | 08W | UNSE | Scoping/Scoped | 3.15 | - | - | 3.15 | 3.15 | - | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5192 | -122.4719 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | 99% | PSPS - 2023 ICUG | Tier 3 | 242
35278899 | Base SH | 08W | ESTS | Estimating | 1.3449 | - | - | 1.3449 | 1.3449 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 243
35279120 | Base SH | 08W | ESTS | Estimating | 1.004 | - | - | 1.004 | 1.004 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 244
35338384 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 | 245
35284364 | Base SH | 08W | ESTS | Estimating | 0.64261 | 0.040341 | - | 0.68295 | 0.68295 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 246
35284365 | Base SH | 08W | ESTS | Estimating | 1.6292 | 0.019508 | - | 1.6487 | 1.6487 | - | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2399 | -120.3619 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 247
35337306 | Base SH | 08W | ESTS | Estimating | 2.1871 | - | - | 2.1871 | 2.1871 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 | 248
35297984 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | NV | Region 2 - North East | Redding | SHASTA | 40.6951 | -122.3174 |  | 851 | 0.085979 |  | 2266 | 0.00040165 | 99% | FRRB | Tier 2 | 249
35312553 | Base SH | 08W | UNSE | Scoping/Scoped | 2.39 | - | - | 2.39 | 2.39 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8582 | -118.8837 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 250
35335286 | Base SH | 08W | UNSE | Scoping/Scoped | 5.21 | - | - | 5.21 | 5.21 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8542 | -118.893 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 251
35335287 | Base SH | 08W | UNSE | Scoping/Scoped | 2.18 | - | - | 2.18 | 2.18 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8466 | -118.8987 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 252
35335288 | Base SH | 08W | UNSE | Scoping/Scoped | 3.6 | 1.38 | - | 4.98 | 4.98 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9158 | -118.9258 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 253
35321445 | Base SH | 08W | UNSE | Scoping/Scoped | 8.11 | - | - | 8.11 | 8.11 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8908 | -118.9154 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 254
35312554 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 255
35312555 | Base SH | 08W | UNSE | Scoping/Scoped | 7.41 | - | - | 7.41 | 7.41 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8814 | -118.9012 |  | 583 | 0.1353 |  | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 256
35320607 | Base SH | 08W | UNSE | Scoping/Scoped | 10 | - | - | 10 | 10 | - | KE | Region 5 - Central Valley | LEBEC | KERN | 34.846 | -118.872 |  | 583 | 0.1353 |  | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 257
35256083 | Base SH | 08W | ESTS | Estimating | 1.847 | 0.0075758 | - | 1.8545 | 1.8545 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1434 | -123.0023 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 258
35283343 | Base SH | 08W | ESTS | Estimating | 0.85303 | - | - | 0.85303 | 0.85303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1488 | -122.9992 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 259
35283346 | Base SH | 08W | ESTS | Estimating | 0.77803 | - | - | 0.77803 | 0.77803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.13 | -122.997 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 260
35285249 | Base SH | 08W | ESTS | Estimating | 2.593 | - | - | 2.593 | 2.593 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1673 | -123.0087 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 261
35285251 | Base SH | 08W | ESTS | Estimating | 0.65303 | - | - | 0.65303 | 0.65303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1758 | -123.0191 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 262
35334753 | Base SH | 08W | ESTS | Estimating | 5.69 | - | - | 5.69 | 5.69 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4313 | -122.05 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 263
35334754 | Base SH | 08W | UNSE | Scoping/Scoped | 3.93 | - | - | 3.93 | 3.93 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4024 | -122.0318 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 264
35334755 | Base SH | 08W | UNSE | Scoping/Scoped | 1.47 | - | - | 1.47 | 1.47 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3911 | -122.0367 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 265
35320336 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4365 | -122.0527 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 266
35320339 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4168 | -122.0381 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 267
35320333 | Base SH | 08W | UNSE | Scoping/Scoped | 2.95 | - | - | 2.95 | 2.95 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.344 | -122.0247 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 268
35320334 | Base SH | 08W | UNSE | Scoping/Scoped | 2.5 | - | - | 2.5 | 2.5 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3618 | -122.0219 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 269
35334750 | Base SH | 08W | UNSE | Scoping/Scoped | 1.49 | - | - | 1.49 | 1.49 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3588 | -122.0245 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 270
35334752 | Base SH | 08W | UNSE | Scoping/Scoped | 1.81 | - | - | 1.81 | 1.81 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3655 | -122.0233 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 271
35320440 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3783 | -122.0044 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 272
35335291 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3771 | -121.9968 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 273
35335292 | Base SH | 08W | UNSE | Scoping/Scoped | 1.88 | - | - | 1.88 | 1.88 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3772 | -121.9918 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 274
35335293 | Base SH | 08W | UNSE | Scoping/Scoped | 2.41 | - | - | 2.41 | 2.41 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3663 | -121.9916 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 275
35334466 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3386 | -122.1218 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 276
35334467 | Base SH | 08W | UNSE | Scoping/Scoped | 2.0271 | - | - | 2.0271 | 2.0271 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3305 | -122.0971 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 277
35334468 | Base SH | 08W | UNSE | Scoping/Scoped | 1.136 | 0.095076 | - | 1.2311 | 1.2311 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3139 | -122.0706 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 278
35254656 | Base SH | 08W | PEND | Permitting/Dependency | 0.44205 | - | - | 0.44205 | 0.44205 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | 0.36191 |  | 2428 | 0.00033385 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 279
35254259 | Base SH | 08W | UNSE | Scoping/Scoped | 0.85 | - | - | 0.85 | 0.85 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 280
35297692 | Fire Rebuild | 08W | ESTS | Estimating | 4.6598 | - | - | 4.6598 | 4.6598 | - | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 281
35334407 | Fire Rebuild | 08W | ESTS | Estimating | 0.089962 | - | - | 0.089962 | 0.089962 | - | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7875 | -123.4468 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 282
35320466 | Base SH | 08W | UNSE | Scoping/Scoped | 2 | - | - | 2 | 2 | - | HB | Region 1 - North Coast | Salyer | TRINITY | 40.8669 | -123.5148 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | CWSP - 2023 ICUG | Tier 2 | 283
35283938 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | - | - | 2.4799 | 2.4799 | - | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3845 | -122.2937 |  | 1145 | 0.05299 |  | 1026 | 0.0021738 | 99% | CWSP 2022-2023 | Tier 3 | 284
35341054 | Fire Rebuild | 08W | ESTS | Estimating | 0.088258 | - | - | 0.088258 | 0.088258 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6143 | -121.4029 |  | 1849 | 0.012814 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 285
35335712 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.0087121 | - | - | 0.0087121 | 0.0087121 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6333 | -121.4164 |  | 1849 | 0.012814 |  | 250 | 0.010796 | 99% | FRRB - UG - 2021 | Tier 3 | 286
35241075 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | - | - | 0.070076 | 0.070076 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 287
35241076 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | - | - | 0.11004 | 0.11004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 288
35241077 | Fire Rebuild | 08W | ADER | Estimating | 0.31004 | - | - | 0.31004 | 0.31004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 289
35236997 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | - | - | 0.28409 | 0.28409 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6827 | -121.3105 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - REMG - 2021 | Tier 3 | 290
35235672 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | - | - | 0.30303 | 0.30303 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 291
35235675 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | - | - | 0.11364 | 0.11364 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 292
35320807 | Fire Rebuild | 08W | ADER | Estimating | 0.085227 | - | - | 0.085227 | 0.085227 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6274 | -121.3727 |  | 1299 | 0.040282 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 293
35331458 | Fire Rebuild | 08W | ESTS | Estimating | 0.08428 | - | - | 0.08428 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6272 | -121.3969 |  | 1299 | 0.040282 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 294
35312560 | Base SH | 08W | UNSE | Scoping/Scoped | 1.98 | - | - | 1.98 | 1.98 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5054 | -121.4999 |  | 645 | 0.12006 |  | 1945 | 0.0005689 | 99% | PSPS - 2023 ICUG | Tier 2 | 295
35331306 | Base SH | 08W | UNSE | Scoping/Scoped | 2.67 | - | - | 2.67 | 2.67 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5178 | -121.4854 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 296
35331307 | Base SH | 08W | UNSE | Scoping/Scoped | 2.55 | - | - | 2.55 | 2.55 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5261 | -121.4815 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 297
35331308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.82 | - | - | 0.82 | 0.82 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5171 | -121.4825 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 298
35343394 | Base SH | 08W | UNSE | Scoping/Scoped | 1.17 | - | - | 1.17 | 1.17 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5152 | -121.4932 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 299
35343395 | Base SH | 08W | UNSE | Scoping/Scoped | 1.76 | - | - | 1.76 | 1.76 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5168 | -121.4943 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 300
35343396 | Base SH | 08W | UNSE | Scoping/Scoped | 1.08 | - | - | 1.08 | 1.08 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.52 | -121.4943 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 301
35343397 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | - | - | 0.84 | 0.84 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5082 | -121.5038 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 302
35320446 | Base SH | 08W | UNSE | Scoping/Scoped | 0.32 | 10.66 | - | 10.98 | 10.98 | - | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 35.6126 | -120.1756 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | 99% | CWSP - 2023 ICUG | Tier 2 | 303
35286270 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2428 | - | - | 1.2428 | - | 1.2428 | NV | Region 2 - North East | Paradise | BUTTE | 39.7573 | -121.6264 |  | 2257 | 0.0039747 |  | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 304
35144489 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.1733 | - | - | 2.1733 | - | 2.1733 | NV | Region 2 - North East | Magalia | BUTTE | 39.8201 | -121.6017 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 305
35112126 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.1095 | - | - | 2.1095 | - | 2.1095 | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.603 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 306
35246595 | Community Rebuild | 08W | ESTS | Estimating | 5.8735 | - | - | 5.8735 | - | 5.8735 | NV | Region 2 - North East | Paradise | BUTTE | 39.7778 | -121.6061 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 307
35127360 | Community Rebuild | 95F | UNSE | Scoping/Scoped | 1.3352 | - | - | 1.3352 | - | 1.3352 | NV | Region 2 - North East | Paradise | BUTTE | 39.7463 | -121.6437 |  | 2950 | 2.5314e-05 |  | 875 | 0.0027476 | 99% | Butte Rebuild | Tier 3 | 308
35144487 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4989 | - | - | 2.4989 | - | 2.4989 | NV | Region 2 - North East | Magalia | BUTTE | 39.8181 | -121.5952 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 309
35144488 | Community Rebuild | 95F | ESTS ERDY | Estimating | 3.5227 | - | - | 3.5227 | - | 3.5227 | NV | Region 2 - North East | Magalia | BUTTE | 39.8148 | -121.6065 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 310
35244220 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.5284 | - | - | 2.5284 | - | 2.5284 | NV | Region 2 - North East | Paradise | BUTTE | 39.7553 | -121.6287 |  | 2257 | 0.0039747 |  | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 311
35246594 | Community Rebuild | 08W | UNSE | Estimating | 3.7216 | - | - | 3.7216 | - | 3.7216 | NV | Region 2 - North East | Paradise | BUTTE | 39.741 | -121.6219 |  | 2906 | 4.4268e-05 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 312
35144490 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4928 | - | - | 2.4928 | - | 2.4928 | NV | Region 2 - North East | Magalia | BUTTE | 39.8242 | -121.5995 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 313
35144491 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.7557 | - | - | 2.7557 | - | 2.7557 | NV | Region 2 - North East | Magalia | BUTTE | 39.8259 | -121.5971 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 314
35144492 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2159 | - | - | 1.2159 | - | 1.2159 | NV | Region 2 - North East | Magalia | BUTTE | 39.8227 | -121.5947 |  | 2211 | 0.0048412 |  | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 315
35246592 | Community Rebuild | 08W | ESTS ERDY | Estimating | 6.2074 | - | - | 6.2074 | - | 6.2074 | NV | Region 2 - North East | Paradise | BUTTE | 39.7412 | -121.6079 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | 99% | Butte Rebuild | Tier 2 | 316
35244027 | Community Rebuild | 08W | ESTS ERDY | Estimating | 5.483 | - | - | 5.483 | - | 5.483 | NV | Region 2 - North East | Paradise | BUTTE | 39.8026 | -121.5798 |  | 2141 | 0.0062243 |  | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 317
35234527 | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | - | - | 0.075947 | - | 0.075947 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 318
35234528 | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | - | - | 0.035985 | - | 0.035985 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 319
35234529 | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | - | - | 0.70833 | - | 0.70833 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 320
35277935 | Base SH | 08W | ESTS | Estimating | 0.092992 | - | - | 0.092992 | - | 0.092992 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0313 | -119.4396 |  | 274 | 0.22501 |  | 614 | 0.0043344 | 99% | CWSP | Tier 2 | 321
35280505 | Other | 30A | ESTS | Estimating | 0.37879 | - | - | 0.37879 | - | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5947 | -122.4862 |  | 1614 | 0.022607 |  | 43 | 0.023649 | 99% | Other | Tier 3 | 322
35294729 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4089 | - | - | 3.4089 | - | 3.4089 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7479 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 323
35294730 | Base SH | 08W | UNSE | Scoping/Scoped | 2.8409 | - | - | 2.8409 | - | 2.8409 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9685 | -121.8246 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 324
35325224 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2799 | 0.05 | - | 3.3299 | - | 3.3299 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 41.0088 | -121.7129 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 325
35325225 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2449 | - | - | 3.2449 | - | 3.2449 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9729 | -121.7814 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 326
35325226 | Base SH | 08W | UNSE | Scoping/Scoped | 4.218 | - | - | 4.218 | - | 4.218 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9868 | -121.8481 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 327
35294728 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4201 | - | - | 2.4201 | - | 2.4201 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7478 |  | 1816 | 0.01407 |  | 326 | 0.0086689 | 99% | CWSP | Tier 2 | 328
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018365 | - | - | 0.018365 | - | 0.018365 | SI | Region 2 - North East | ALLEGHANY | Nevada | 39.364 | -120.7923 |  | 3054 | 1.0723e-05 |  | 4 | 0.066078 | 99% | V3 Tranche 1 | Tier 3 | 329
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.7026 | - | - | 21.7026 | - | 21.7026 | SI | Region 2 - North East | ALLEGHANY | Sierra | 39.4655 | -120.8449 |  | 1700 | 0.018204 |  | 41 | 0.023951 | 99% | V3 Tranche 1 | Tier 3 | 330
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4687 | - | - | 11.4687 | - | 11.4687 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8524 | -122.3324 |  | 1674 | 0.019836 |  | 210 | 0.012094 | 99% | V3 Tranche 1 | Tier 2 | 331
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.278 | - | - | 30.278 | - | 30.278 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8489 | -122.3313 |  | 1722 | 0.017574 |  | 247 | 0.010915 | 99% | V3 Tranche 1 | Tier 3 | 332
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.0657 | - | - | 11.0657 | - | 11.0657 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8937 | -122.382 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | 99% | V3 Tranche 1 | Tier 2 | 333
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.1874 | - | - | 11.1874 | - | 11.1874 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8995 | -122.3862 |  | 2407 | 0.002519 |  | 91 | 0.018782 | 99% | V3 Tranche 1 | Tier 2 | 334
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.622 | - | - | 9.622 | - | 9.622 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8916 | -122.3764 |  | 1791 | 0.014748 |  | 143 | 0.015772 | 99% | V3 Tranche 1 | Tier 3 | 335
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9879 | - | - | 1.9879 | - | 1.9879 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8945 | -122.3808 |  | 2207 | 0.0049349 |  | 94 | 0.0187 | 99% | V3 Tranche 1 | Tier 2 | 336
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.4383 | - | - | 34.4383 | - | 34.4383 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7391 | -120.6681 |  | 1284 | 0.041392 |  | 124 | 0.016427 | 99% | V3 Tranche 1 | Tier 3 | 337
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.021845 | - | - | 0.021845 | - | 0.021845 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7721 | -120.7002 |  | 1657 | 0.020643 |  | 386 | 0.0072633 | 99% | V3 Tranche 1 | Tier 3 | 338
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9275 | - | - | 31.9275 | - | 31.9275 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7652 | -120.7045 |  | 1934 | 0.010689 |  | 197 | 0.012828 | 99% | V3 Tranche 1 | Tier 3 | 339
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1021 | - | - | 5.1021 | - | 5.1021 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7396 | -120.6772 |  | 1422 | 0.032289 |  | 30 | 0.025967 | 99% | V3 Tranche 1 | Tier 2 | 340
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.136 | - | - | 15.136 | - | 15.136 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 |  | 178 | 0.2712 |  | 32 | 0.025831 | 99% | V3 Tranche 1 | Tier 3 | 341
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.5084 | - | - | 28.5084 | - | 28.5084 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6607 |  | 1505 | 0.027532 |  | 63 | 0.020812 | 99% | V3 Tranche 1 | Tier 3 | 342
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 51.0474 | - | - | 51.0474 | - | 51.0474 | SI | Region 2 - North East | Camino | El Dorado | 38.7371 | -120.6759 |  | 644 | 0.12006 |  | 132 | 0.01606 | 99% | V3 Tranche 1 | Tier 3 | 343
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.078916 | - | - | 0.078916 | - | 0.078916 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6765 |  | 644 | 0.12006 |  | 2 | 0.090117 | 99% | V3 Tranche 1 | Tier 2 | 344
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.2757 | - | - | 19.2757 | - | 19.2757 | NV | Region 2 - North East | BERRY CREEK | Butte | 39.6444 | -121.4314 |  | 1288 | 0.040961 |  | 267 | 0.010152 | 99% | V3 Tranche 1 | Tier 3 | 345
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.6217 | - | - | 13.6217 | - | 13.6217 | NV | Region 2 - North East | CONCOW | Butte | 39.6773 | -121.4916 |  | 865 | 0.084888 |  | 187 | 0.013302 | 99% | V3 Tranche 1 | Tier 3 | 346
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.0546 | - | - | 18.0546 | - | 18.0546 | SI | Region 2 - North East | ALTA | Placer | 39.2148 | -120.8091 |  | 1526 | 0.026396 |  | 20 | 0.02949 | 99% | V3 Tranche 1 | Tier 3 | 347
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.5031 | - | - | 42.5031 | - | 42.5031 | SI | Region 2 - North East | ALTA | Placer | 39.2147 | -120.8094 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | 99% | V3 Tranche 1 | Tier 3 | 348
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 55.3006 | - | - | 55.3006 | - | 55.3006 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.2129 | -121.0129 |  | 1649 | 0.021168 |  | 234 | 0.011407 | 99% | V3 Tranche 1 | Tier 3 | 349
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.0096 | - | - | 12.0096 | - | 12.0096 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1995 | -121.0171 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | 99% | V3 Tranche 1 | Tier 3 | 350
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.1704 | - | - | 28.1704 | - | 28.1704 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1909 | -120.9999 |  | 1154 | 0.052211 |  | 266 | 0.010208 | 99% | V3 Tranche 1 | Tier 3 | 351
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 70.6282 | - | - | 70.6282 | - | 70.6282 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1911 | -120.9965 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | 99% | V3 Tranche 1 | Tier 3 | 352
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.2781 | - | - | 33.2781 | - | 33.2781 | NV | Region 2 - North East | STORRIE | Plumas | 39.9109 | -121.3276 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | V3 Tranche 1 | Tier 3 | 353
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.9616 | - | - | 15.9616 | - | 15.9616 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6088 | -122.591 |  | 1093 | 0.057148 |  | 134 | 0.016019 | 99% | V3 Tranche 1 | Tier 3 | 354
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.64 | - | - | 1.64 | - | 1.64 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6222 | -122.679 |  | 565 | 0.14151 |  | 480 | 0.0057895 | 99% | V3 Tranche 1 | Tier 3 | 355
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.636 | - | - | 15.636 | - | 15.636 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5894 | -122.6079 |  | 683 | 0.11348 |  | 428 | 0.006597 | 99% | V3 Tranche 1 | Tier 3 | 356
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.5931 | - | - | 3.5931 | - | 3.5931 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6577 | -122.5951 |  | 614 | 0.12786 |  | 389 | 0.0071797 | 99% | V3 Tranche 1 | Tier 3 | 357
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3819 | - | - | 9.3819 | - | 9.3819 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5953 | -122.6022 |  | 1005 | 0.066852 |  | 105 | 0.017566 | 99% | V3 Tranche 1 | Tier 3 | 358
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9467 | - | - | 31.9467 | - | 31.9467 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5803 | -122.5979 |  | 833 | 0.088841 |  | 299 | 0.0094322 | 99% | V3 Tranche 1 | Tier 3 | 359
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.518 | - | - | 4.518 | - | 4.518 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6318 | -122.6741 |  | 406 | 0.17857 |  | 589 | 0.0045153 | 99% | V3 Tranche 1 | Tier 3 | 360
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8478 | - | - | 11.8478 | - | 11.8478 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.5599 | -122.6285 |  | 833 | 0.088841 |  | 411 | 0.006798 | 99% | V3 Tranche 1 | Tier 3 | 361
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.10844 | - | - | 0.10844 | - | 0.10844 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.592 | -122.5786 |  | 55 | 0.40561 |  | 1636 | 0.00082073 | 99% | V3 Tranche 1 | Tier 2 | 362
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.8011 | - | - | 5.8011 | - | 5.8011 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5637 | -122.5595 |  | 1477 | 0.029373 |  | 24 | 0.027222 | 99% | V3 Tranche 1 | Tier 3 | 363
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.052643 | - | - | 0.052643 | - | 0.052643 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5686 | -122.5417 |  | 1014 | 0.065722 |  | 78 | 0.019531 | 99% | V3 Tranche 1 | Tier 3 | 364
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.1129 | - | - | 0.1129 | - | 0.1129 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5762 | -122.5825 |  | 2828 | 0.00021298 |  | 382 | 0.0073271 | 99% | V3 Tranche 1 | Tier 2 | 365
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7313 | - | - | 0.7313 | - | 0.7313 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5787 | -122.5826 |  | 3098 | 8.707e-06 |  | 843 | 0.0029014 | 99% | V3 Tranche 1 | Tier 3 | 366
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9317 | - | - | 6.9317 | - | 6.9317 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5859 | -122.5714 |  | 1477 | 0.029373 |  | 769 | 0.0032407 | 99% | V3 Tranche 1 | Tier 3 | 367
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.0843 | - | - | 7.0843 | - | 7.0843 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5678 | -122.5383 |  | 1624 | 0.022338 |  | 534 | 0.0050695 | 99% | V3 Tranche 1 | Tier 3 | 368
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018445 | - | - | 0.018445 | - | 0.018445 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8059 | -122.8081 |  | 2 | 1.8786 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 369
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.057948 | - | - | 0.057948 | - | 0.057948 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7727 | -122.7295 |  | 2308 | 0.0033555 |  | 3 | 0.068443 | 99% | V3 Tranche 1 | Tier 3 | 370
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.0767 | - | - | 5.0767 | - | 5.0767 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7658 | -122.7076 |  | 1049 | 0.061428 |  | 238 | 0.011276 | 99% | V3 Tranche 1 | Tier 3 | 371
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3133 | - | - | 33.3133 | - | 33.3133 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8154 | -122.8003 |  | 334 | 0.19817 |  | 169 | 0.014299 | 99% | V3 Tranche 1 | Tier 3 | 372
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.010654 | - | - | 0.010654 | - | 0.010654 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8266 | -122.7997 |  | 31 | 0.50979 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 373
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.014112 | - | - | 0.014112 | - | 0.014112 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8264 | -122.7997 |  | 32 | 0.50979 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 374
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.3029 | - | - | 2.3029 | - | 2.3029 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8265 | -122.8041 |  | 97 | 0.34896 |  | 543 | 0.0049805 | 99% | V3 Tranche 1 | Tier 3 | 375
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.6798 | - | - | 4.6798 | - | 4.6798 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.815 | -122.8021 |  | 297 | 0.21399 |  | 79 | 0.019348 | 99% | V3 Tranche 1 | Tier 3 | 376
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.58901 | - | - | 0.58901 | - | 0.58901 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9412 | -121.9576 |  | 1321 | 0.038704 |  | 471 | 0.0058873 | 99% | V3 Tranche 1 | Tier 2 | 377
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.7558 | - | - | 14.7558 | - | 14.7558 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.8797 | -121.8678 |  | 377 | 0.18755 |  | 223 | 0.011731 | 99% | V3 Tranche 1 | Tier 3 | 378
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.79978 | - | - | 0.79978 | - | 0.79978 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9332 | -121.9419 |  | 2561 | 0.0014894 |  | 100 | 0.018211 | 99% | V3 Tranche 1 | Tier 3 | 379
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3146 | - | - | 33.3146 | - | 33.3146 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9245 | -121.9125 |  | 2561 | 0.0014894 |  | 115 | 0.016899 | 99% | V3 Tranche 1 | Tier 3 | 380
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.6045 | - | - | 9.6045 | - | 9.6045 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9039 | -121.8741 |  | 377 | 0.18755 |  | 15 | 0.034099 | 99% | V3 Tranche 1 | Tier 3 | 381
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.37986 | - | - | 0.37986 | - | 0.37986 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9439 | -121.9691 |  | 2561 | 0.0014894 |  | 1654 | 0.00080781 | 99% | V3 Tranche 1 | Tier 2 | 382
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6612 | - | - | 3.6612 | - | 3.6612 | HB | Region 1 - North Coast | LAKEPORT | Lake | 39.0183 | -122.917 |  | 239 | 0.23862 |  | 200 | 0.012549 | 99% | V3 Tranche 1 | Tier 2 | 383
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.052 | - | - | 17.052 | - | 17.052 | NV | Region 2 - North East | CORNING | Tehama | 39.9967 | -122.4058 |  | 549 | 0.1444 |  | 615 | 0.0043341 | 99% | V3 Tranche 1 | Tier 2 | 384
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.8387 | - | - | 28.8387 | - | 28.8387 | NV | Region 2 - North East | CORNING | Tehama | 40.0157 | -122.4005 |  | 986 | 0.068983 |  | 194 | 0.012991 | 99% | V3 Tranche 1 | Tier 2 | 385
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.96092 | - | - | 0.96092 | - | 0.96092 | NV | Region 2 - North East | OROVILLE | Butte | 39.8269 | -121.4092 |  | 2890 | 6.9083e-05 |  | 40 | 0.023964 | 99% | V3 Tranche 1 | Tier 3 | 386
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.54712 | - | - | 0.54712 | - | 0.54712 | NV | Region 2 - North East | OROVILLE | Butte | 39.8308 | -121.4091 |  | 33 | 0.50291 |  | 31 | 0.025946 | 99% | V3 Tranche 1 | Tier 3 | 387
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.7057 | - | - | 2.7057 | - | 2.7057 | SI | Region 2 - North East | ALTA | Placer | 39.2564 | -120.7671 |  | 942 | 0.074456 |  | 103 | 0.018102 | 99% | V3 Tranche 1 | Tier 3 | 388
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8641 | - | - | 11.8641 | - | 11.8641 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7617 | -120.5776 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | 99% | V3 Tranche 1 | Tier 3 | 389
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.31289 | - | - | 0.31289 | - | 0.31289 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7602 | -120.5769 |  | 3014 | 1.4503e-05 |  | 195 | 0.012963 | 99% | V3 Tranche 1 | Tier 3 | 390
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.077102 | - | - | 0.077102 | - | 0.077102 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7539 | -120.5747 |  | 2000 | 0.0090446 |  | 121 | 0.016629 | 99% | V3 Tranche 1 | Tier 3 | 391
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.9464 | - | - | 3.9464 | - | 3.9464 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7649 | -120.5894 |  | 2469 | 0.0020868 |  | 780 | 0.0031904 | 99% | V3 Tranche 1 | Tier 3 | 392
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.8959 | - | - | 6.8959 | - | 6.8959 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7935 | -120.6192 |  | 2732 | 0.00051722 |  | 278 | 0.0099516 | 99% | V3 Tranche 1 | Tier 3 | 393
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.2319 | - | - | 6.2319 | - | 6.2319 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3604 | -120.7525 |  | 1720 | 0.017625 |  | 288 | 0.0096899 | 99% | V3 Tranche 1 | Tier 2 | 394
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3872 | - | - | 29.3872 | - | 29.3872 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3633 | -120.6486 |  | 1571 | 0.0243 |  | 355 | 0.0078671 | 99% | V3 Tranche 1 | Tier 2 | 395
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.0949 | - | - | 15.0949 | - | 15.0949 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3639 | -120.6467 |  | 1548 | 0.025302 |  | 62 | 0.020861 | 99% | V3 Tranche 1 | Tier 2 | 396
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.1029 | - | - | 29.1029 | - | 29.1029 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3314 | -120.6731 |  | 1088 | 0.05741 |  | 251 | 0.010795 | 99% | V3 Tranche 1 | Tier 2 | 397
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.211 | - | - | 7.211 | - | 7.211 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3793 | -120.638 |  | 2349 | 0.0030208 |  | 118 | 0.016781 | 99% | V3 Tranche 1 | Tier 2 | 398
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7233 | - | - | 27.7233 | - | 27.7233 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0162 | -120.8351 |  | 1865 | 0.012496 |  | 179 | 0.013637 | 99% | V3 Tranche 1 | Tier 3 | 399
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.4919 | - | - | 14.4919 | - | 14.4919 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0474 | -120.7852 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | 99% | V3 Tranche 1 | Tier 3 | 400
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.6369 | - | - | 14.6369 | - | 14.6369 | SI | Region 2 - North East | FORESTHILL | Placer | 38.9929 | -120.8827 |  | 2270 | 0.0037623 |  | 114 | 0.01695 | 99% | V3 Tranche 1 | Tier 3 | 401
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.3473 | - | - | 11.3473 | - | 11.3473 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0193 | -120.8302 |  | 2058 | 0.0077431 |  | 232 | 0.011424 | 99% | V3 Tranche 1 | Tier 3 | 402
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.8558 | - | - | 34.8558 | - | 34.8558 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0198 | -120.8509 |  | 1301 | 0.040196 |  | 97 | 0.018495 | 99% | V3 Tranche 1 | Tier 3 | 403
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.25572 | - | - | 0.25572 | - | 0.25572 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.7004 | -122.9575 |  | 2170 | 0.0056711 |  | 1375 | 0.0011879 | 99% | V3 Tranche 1 | Tier 2 | 404
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.037341 | - | - | 0.037341 | - | 0.037341 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.937 | -122.609 |  | 3186 | 6.536e-06 |  | 163 | 0.014683 | 99% | V3 Tranche 1 | Tier 2 | 405
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.7877 | - | - | 17.7877 | - | 17.7877 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.9822 | -122.6031 |  | 27 | 0.5487 |  | 29 | 0.026126 | 99% | V3 Tranche 1 | Tier 3 | 406
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.6035 | - | - | 7.6035 | - | 7.6035 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8802 | -122.6125 |  | 626 | 0.12376 |  | 582 | 0.0045905 | 99% | V3 Tranche 1 | Tier 2 | 407
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.1732 | - | - | 21.1732 | - | 21.1732 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8967 | -122.5542 |  | 181 | 0.26975 |  | 156 | 0.015099 | 99% | V3 Tranche 1 | Tier 2 | 408
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.8369 | - | - | 9.8369 | - | 9.8369 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8705 | -122.6229 |  | 626 | 0.12376 |  | 144 | 0.015697 | 99% | V3 Tranche 1 | Tier 2 | 409
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.0855 | - | - | 9.0855 | - | 9.0855 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.9079 | -122.5968 |  | 461 | 0.16238 |  | 270 | 0.010079 | 99% | V3 Tranche 1 | Tier 2 | 410
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.29571 | - | - | 0.29571 | - | 0.29571 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.677 | -119.7768 |  | 16 | 0.68656 |  | 12 | 0.038638 | 99% | V3 Tranche 1 | Tier 2 | 411
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.8871 | - | - | 19.8871 | - | 19.8871 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.6649 | -119.8411 |  | 555 | 0.14347 |  | 10 | 0.039297 | 99% | V3 Tranche 1 | Tier 2 | 412
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3548 | - | - | 9.3548 | - | 9.3548 | SA | Region 2 - North East | GREEN VALLEY | Solano | 38.2496 | -122.1606 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | V3 Tranche 1 | Tier 2 | 413
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.8683 | - | - | 2.8683 | - | 2.8683 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.3482 | -121.3219 |  | 2006 | 0.0089147 |  | 462 | 0.0060529 | 99% | V3 Tranche 1 | Tier 2 | 414
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.4274 | - | - | 37.4274 | - | 37.4274 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2804 | -121.3064 |  | 1509 | 0.027281 |  | 178 | 0.013726 | 99% | V3 Tranche 1 | Tier 2 | 415
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 38.1684 | - | - | 38.1684 | - | 38.1684 | CC | Region 4 - Central Coast | BITTERWATER | San Benito | 36.3875 | -121.0045 |  | N/A (HFRA, not in v2) | - |  | 193 | 0.012994 | 99% | V3 Tranche 1 | HFRA | 416
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.182 | - | - | 15.182 | - | 15.182 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2789 | -121.3033 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | 99% | V3 Tranche 1 | Tier 2 | 417
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.6522 | - | - | 24.6522 | - | 24.6522 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5251 | -119.9181 |  | 679 | 0.11431 |  | 126 | 0.016323 | 99% | V3 Tranche 1 | Tier 3 | 418
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.4258 | - | - | 23.4258 | - | 23.4258 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5697 | -119.942 |  | 700 | 0.11205 |  | 199 | 0.012689 | 99% | V3 Tranche 1 | Tier 3 | 419
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.13992 | - | - | 0.13992 | - | 0.13992 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4872 | -119.9618 |  | 10 | 0.77248 |  | 515 | 0.0052627 | 99% | V3 Tranche 1 | Tier 2 | 420
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.070448 | - | - | 0.070448 | - | 0.070448 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4632 | -119.9482 |  | 3264 | 5.0408e-06 |  | 464 | 0.0059574 | 99% | V3 Tranche 1 | Tier 2 | 421
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65665 | - | - | 0.65665 | - | 0.65665 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4861 | -119.9697 |  | 587 | 0.13461 |  | 312 | 0.0089197 | 99% | V3 Tranche 1 | Tier 2 | 422
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0221 | - | - | 1.0221 | - | 1.0221 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.5044 | -120.0079 |  | 35 | 0.47165 |  | 77 | 0.019783 | 99% | V3 Tranche 1 | Tier 2 | 423
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76835 | - | - | 0.76835 | - | 0.76835 | HB | Region 1 - North Coast | COBB | Lake | 38.8237 | -122.7214 |  | 474 | 0.15935 |  | 258 | 0.010457 | 99% | V3 Tranche 1 | Tier 3 | 424
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.1567 | - | - | 1.1567 | - | 1.1567 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7312 | -122.6235 |  | 915 | 0.078235 |  | 56 | 0.021686 | 99% | V3 Tranche 1 | Tier 3 | 425
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3963 | - | - | 4.3963 | - | 4.3963 | HB | Region 1 - North Coast | COBB | Lake | 38.8481 | -122.7562 |  | 328 | 0.19983 |  | 38 | 0.024501 | 99% | V3 Tranche 1 | Tier 3 | 426
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.6615 | - | - | 2.6615 | - | 2.6615 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.695 | -122.5975 |  | 468 | 0.1603 |  | 175 | 0.013904 | 99% | V3 Tranche 1 | Tier 3 | 427
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3985 | - | - | 1.3985 | - | 1.3985 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7253 | -122.619 |  | 314 | 0.20636 |  | 99 | 0.018456 | 99% | V3 Tranche 1 | Tier 3 | 428
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.4605 | - | - | 1.4605 | - | 1.4605 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7522 | -122.6207 |  | 450 | 0.16479 |  | 174 | 0.013914 | 99% | V3 Tranche 1 | Tier 2 | 429
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.4241 | - | - | 26.4241 | - | 26.4241 | HB | Region 1 - North Coast | COBB | Lake | 38.8291 | -122.7295 |  | 328 | 0.19983 |  | 182 | 0.013549 | 99% | V3 Tranche 1 | Tier 3 | 430
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0487 | - | - | 1.0487 | - | 1.0487 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7628 | -122.6133 |  | 38 | 0.46769 |  | 673 | 0.0038943 | 99% | V3 Tranche 1 | Tier 3 | 431
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.9927 | - | - | 10.9927 | - | 10.9927 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7249 | -122.6186 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | V3 Tranche 1 | Tier 3 | 432
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.0007 | - | - | 26.0007 | - | 26.0007 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | V3 Tranche 1 | Tier 3 | 433
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.707 | - | - | 1.707 | - | 1.707 | HB | Region 1 - North Coast | COBB | Lake | 38.8266 | -122.727 |  | 2060 | 0.0076984 |  | 211 | 0.01209 | 99% | V3 Tranche 1 | Tier 3 | 434
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5662 | - | - | 18.5662 | - | 18.5662 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7462 | -122.6206 |  | 314 | 0.20636 |  | 185 | 0.013349 | 99% | V3 Tranche 1 | Tier 3 | 435
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9629 | - | - | 1.9629 | - | 1.9629 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7537 | -122.6111 |  | 86 | 0.36174 |  | 935 | 0.002498 | 99% | V3 Tranche 1 | Tier 3 | 436
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65224 | - | - | 0.65224 | - | 0.65224 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7523 | -122.6178 |  | 3073 | 9.669e-06 |  | 146 | 0.015654 | 99% | V3 Tranche 1 | Tier 2 | 437
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3099 | - | - | 4.3099 | - | 4.3099 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7722 | -122.6244 |  | 86 | 0.36174 |  | 160 | 0.014882 | 99% | V3 Tranche 1 | Tier 3 | 438
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.995 | - | - | 13.995 | - | 13.995 | SI | Region 2 - North East | GEOGETOWN | El Dorado | 38.8995 | -120.8545 |  | 2212 | 0.0048403 |  | 275 | 0.009997 | 99% | V3 Tranche 1 | Tier 3 | 439
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.104 | - | - | 27.104 | - | 27.104 | SI | Region 2 - North East | COOL | El Dorado | 38.8932 | -120.9965 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | V3 Tranche 1 | Tier 2 | 440
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6797 | - | - | 10.6797 | - | 10.6797 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.9 | -120.9074 |  | 1706 | 0.018043 |  | 165 | 0.014598 | 99% | V3 Tranche 1 | Tier 2 | 441
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.3111 | - | - | 18.3111 | - | 18.3111 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.8958 | -120.879 |  | 1212 | 0.046937 |  | 177 | 0.013764 | 99% | V3 Tranche 1 | Tier 3 | 442
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6043 | - | - | 10.6043 | - | 10.6043 | NV | Region 2 - North East | CHICO | Butte | 39.7784 | -121.7318 |  | 73 | 0.37815 |  | 155 | 0.015172 | 99% | V3 Tranche 1 | Tier 3 | 443
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5667 | - | - | 13.5667 | - | 13.5667 | NV | Region 2 - North East | FOREST RANCH | Butte | 39.839 | -121.7019 |  | 1043 | 0.062015 |  | 37 | 0.024521 | 99% | V3 Tranche 1 | Tier 3 | 444
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.8427 | - | - | 3.8427 | - | 3.8427 | NV | Region 2 - North East | CHICO | Butte | 39.7393 | -121.7854 |  | 73 | 0.37815 |  | 926 | 0.0025265 | 99% | V3 Tranche 1 | Tier 2 | 445
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.098 | - | - | 6.098 | - | 6.098 | NV | Region 2 - North East | CHICO | Butte | 39.7911 | -121.7217 |  | 1045 | 0.061762 |  | 290 | 0.0096296 | 99% | V3 Tranche 1 | Tier 3 | 446
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.7141 | - | - | 30.7141 | - | 30.7141 | YO | Region 5 - Central Valley | AHWAHNEE | Madera | 37.3399 | -119.6754 |  | 541 | 0.14657 |  | 172 | 0.014056 | 99% | V3 Tranche 1 | Tier 2 | 447
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.15233 | - | - | 0.15233 | - | 0.15233 | YO | Region 5 - Central Valley | OAKHURST | Madera | 37.3219 | -119.6344 |  | 847 | 0.086583 |  | 1208 | 0.0016106 | 99% | V3 Tranche 1 | Tier 3 | 448
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.4642 | - | - | 16.4642 | - | 16.4642 | NV | Region 2 - North East | SHASTA LAKE | Shasta | 40.6653 | -122.3866 |  | 1773 | 0.015387 |  | 64 | 0.0208 | 99% | V3 Tranche 1 | Tier 2 | 449
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1749 | - | - | 20.1749 | - | 20.1749 | NV | Region 2 - North East | MAGALIA | Butte | 39.8542 | -121.6058 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | 99% | V3 Tranche 1 | Tier 3 | 450
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.3261 | - | - | 20.3261 | - | 20.3261 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | 99% | V3 Tranche 1 | Tier 3 | 451
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5511 | - | - | 18.5511 | - | 18.5511 | NV | Region 2 - North East | MAGALIA | Butte | 39.8582 | -121.6134 |  | 2440 | 0.0022675 |  | 150 | 0.015441 | 99% | V3 Tranche 1 | Tier 3 | 452
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.1705 | - | - | 3.1705 | - | 3.1705 | NV | Region 2 - North East | MAGALIA | Butte | 39.872 | -121.612 |  | 1287 | 0.040994 |  | 129 | 0.016201 | 99% | V3 Tranche 1 | Tier 3 | 453
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.3248 | - | - | 8.3248 | - | 8.3248 | NV | Region 2 - North East | MAGALIA | Butte | 39.8901 | -121.5778 |  | 1441 | 0.031032 |  | 181 | 0.013572 | 99% | V3 Tranche 1 | Tier 3 | 454
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.8784 | - | - | 52.8784 | - | 52.8784 | NV | Region 2 - North East | MAGALIA | Butte | 39.8872 | -121.6653 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | 99% | V3 Tranche 1 | Tier 3 | 455
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.8338 | - | - | 13.8338 | - | 13.8338 | NV | Region 2 - North East | MAGALIA | Butte | 39.8705 | -121.6503 |  | 1667 | 0.020219 |  | 140 | 0.015891 | 99% | V3 Tranche 1 | Tier 3 | 456
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1864 | - | - | 20.1864 | - | 20.1864 | NV | Region 2 - North East | MAGALIA | Butte | 39.8877 | -121.6654 |  | 2763 | 0.000401 |  | 61 | 0.020869 | 99% | V3 Tranche 1 | Tier 3 | 457
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.714 | - | - | 2.714 | - | 2.714 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | 99% | V3 Tranche 1 | Tier 3 | 458
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9289 | - | - | 1.9289 | - | 1.9289 | NV | Region 2 - North East | PARADISE | Butte | 39.7704 | -121.6138 |  | 2910 | 4.2503e-05 |  | 26 | 0.026975 | 99% | V3 Tranche 1 | Tier 3 | 459
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.3679 | - | - | 7.3679 | - | 7.3679 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4553 | -121.053 |  | 1710 | 0.017864 |  | 52 | 0.02211 | 99% | V3 Tranche 1 | Tier 3 | 460
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.588 | - | - | 10.588 | - | 10.588 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4519 | -121.0542 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | 99% | V3 Tranche 1 | Tier 3 | 461
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.605 | - | - | 24.605 | - | 24.605 | SI | Region 2 - North East | NORTH SAN JUAN | Sierra | 39.4381 | -120.9961 |  | 1484 | 0.029034 |  | 116 | 0.016874 | 99% | V3 Tranche 1 | Tier 3 | 462
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.2062 | - | - | 5.2062 | - | 5.2062 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.414 | -120.6754 |  | 2455 | 0.0021716 |  | 310 | 0.0089413 | 99% | V3 Tranche 1 | Tier 2 | 463
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.187 | - | - | 15.187 | - | 15.187 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4069 | -120.6707 |  | 1764 | 0.015763 |  | 147 | 0.015597 | 99% | V3 Tranche 1 | Tier 2 | 464
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 49.4644 | - | - | 49.4644 | - | 49.4644 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4151 | -120.6853 |  | 1768 | 0.015534 |  | 410 | 0.0068091 | 99% | V3 Tranche 1 | Tier 2 | 465
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4439 | - | - | 11.4439 | - | 11.4439 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3852 | -120.6921 |  | 1943 | 0.010365 |  | 240 | 0.011105 | 99% | V3 Tranche 1 | Tier 2 | 466
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.3432 | - | - | 5.3432 | - | 5.3432 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | 99% | V3 Tranche 1 | Tier 2 | 467
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.6574 | - | - | 20.6574 | - | 20.6574 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4739 | -120.6268 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | 99% | V3 Tranche 1 | Tier 3 | 468
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.38 | - | - | 37.38 | - | 37.38 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4143 | -120.6541 |  | 1602 | 0.023045 |  | 303 | 0.0092748 | 99% | V3 Tranche 1 | Tier 3 | 469
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.82 | - | - | 11.82 | - | 11.82 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4102 | -120.6518 |  | 1592 | 0.023346 |  | 139 | 0.015893 | 99% | V3 Tranche 1 | Tier 3 | 470
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.4813 | - | - | 13.4813 | - | 13.4813 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4535 | -120.5298 |  | 2447 | 0.002235 |  | 233 | 0.011408 | 99% | V3 Tranche 1 | Tier 3 | 471
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.9356 | - | - | 42.9356 | - | 42.9356 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4612 | -120.6579 |  | 1271 | 0.042249 |  | 131 | 0.016072 | 99% | V3 Tranche 1 | Tier 2 | 472
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5197 | - | - | 13.5197 | - | 13.5197 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 |  | 1920 | 0.010952 |  | 161 | 0.014761 | 99% | V3 Tranche 1 | Tier 3 | 473
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.1028 | - | - | 16.1028 | - | 16.1028 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7219 | -120.7904 |  | 2135 | 0.0064118 |  | 148 | 0.015591 | 99% | V3 Tranche 1 | Tier 2 | 474
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.9958 | - | - | 52.9958 | - | 52.9958 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7716 | -120.8148 |  | 1666 | 0.020262 |  | 68 | 0.020612 | 99% | V3 Tranche 1 | Tier 3 | 475
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.066273 | - | - | 0.066273 | - | 0.066273 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7719 | -120.8138 |  | 1168 | 0.050873 |  | 1 | 0.10471 | 99% | V3 Tranche 1 | Tier 3 | 476
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 25.9329 | - | - | 25.9329 | - | 25.9329 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 |  | 904 | 0.079474 |  | 58 | 0.021398 | 99% | V3 Tranche 1 | Tier 3 | 477
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.8769 | - | - | 30.8769 | - | 30.8769 | SI | Region 2 - North East | SPANISH FLAT | El Dorado | 38.8328 | -120.8176 |  | 1646 | 0.021241 |  | 236 | 0.011373 | 99% | V3 Tranche 1 | Tier 3 | 478
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7465 | - | - | 7.7465 | - | 7.7465 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7308 | -120.7838 |  | 1168 | 0.050873 |  | 230 | 0.011469 | 99% | V3 Tranche 1 | Tier 3 | 479
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.2953 | - | - | 2.2953 | - | 2.2953 | NB | Region 1 - North Coast | ENCHANTED HILLS | Napa | 38.397 | -122.4504 |  | 1224 | 0.046077 |  | 264 | 0.010245 | 99% | V3 Tranche 1 | Tier 3 | 480
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 41.2147 | - | - | 41.2147 | - | 41.2147 | NB | Region 1 - North Coast | NAPA | Napa | 38.3155 | -122.3422 |  | 1224 | 0.046077 |  | 255 | 0.010549 | 99% | V3 Tranche 1 | Tier 3 | 481
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3813 | - | - | 9.3813 | - | 9.3813 | NB | Region 1 - North Coast | NAPA | Napa | 38.3469 | -122.3299 |  | 1630 | 0.022046 |  | 1000 | 0.0022679 | 99% | V3 Tranche 1 | Tier 3 | 482
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.7002 | - | - | 24.7002 | - | 24.7002 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0662 | -122.611 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | V3 Tranche 1 | Tier 3 | 483
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9186 | - | - | 6.9186 | - | 6.9186 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0836 | -122.6599 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | V3 Tranche 1 | Tier 3 | 484
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4951 | - | - | 5.4951 | - | 5.4951 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0231 | -122.678 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | V3 Tranche 1 | Tier 3 | 485
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1996 | - | - | 5.1996 | - | 5.1996 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0581 | -122.693 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | V3 Tranche 1 | Tier 3 | 486
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.0551 | - | - | 4.0551 | - | 4.0551 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0275 | -122.6625 |  | 2343 | 0.0030523 |  | 395 | 0.0070846 | 99% | V3 Tranche 1 | Tier 2 | 487
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.5016 | - | - | 6.5016 | - | 6.5016 | ST | Region 5 - Central Valley | DORRINGTON | Calaveras | 38.323 | -120.2534 |  | 2620 | 0.0010653 |  | 133 | 0.016045 | 99% | V3 Tranche 1 | Tier 3 | 488
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6822e-05 | - | - | 3.6822e-05 | - | 3.6822e-05 | NB | Region 1 - North Coast | SAN RAFAEL | Marin | 37.9807 | -122.5155 |  | 3129 | 7.8608e-06 |  | 5066 | 4.4996e-05 | 99% | V3 Tranche 1 | Tier 2 | 489
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | MI | Region 3 - Bay Area | DUBLIN | Alameda | 37.7029 | -121.9121 |  | 3206 | 6.0521e-06 |  | 1337 | 0.0012585 | 99% | V3 Tranche 1 | Tier 3 | 490
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.5259 | - | - | 7.5259 | - | 7.5259 | SI | Region 2 - North East | COLFAX | Placer | 39.103 | -120.9601 |  | 1885 | 0.011963 |  | 120 | 0.016673 | 99% | V3 Tranche 1 | Tier 3 | 491
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.5495 | - | - | 14.5495 | - | 14.5495 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 |  | 2201 | 0.00506 |  | 71 | 0.02023 | 99% | V3 Tranche 1 | Tier 2 | 492
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.986 | - | - | 0.986 | - | 0.986 | SI | Region 2 - North East | COLFAX | Placer | 39.0992 | -120.95 |  | 1581 | 0.023753 |  | 542 | 0.0049817 | 99% | V3 Tranche 1 | Tier 2 | 493
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32802 | - | - | 0.32802 | - | 0.32802 | SI | Region 2 - North East | COLFAX | Placer | 39.0994 | -120.9559 |  | 2622 | 0.0010502 |  | 869 | 0.0027704 | 99% | V3 Tranche 1 | Tier 2 | 494
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.2383 | - | - | 24.2383 | - | 24.2383 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | 99% | V3 Tranche 1 | Tier 3 | 495
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6883 | - | - | 12.6883 | - | 12.6883 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 |  | 1378 | 0.034658 |  | 89 | 0.018876 | 99% | V3 Tranche 1 | Tier 3 | 496
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.814 | - | - | 23.814 | - | 23.814 | SI | Region 2 - North East | COLFAX | Placer | 39.1153 | -120.953 |  | 1829 | 0.01359 |  | 180 | 0.01361 | 99% | V3 Tranche 1 | Tier 3 | 497
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.020723 | - | - | 0.020723 | - | 0.020723 | SI | Region 2 - North East | CAMERON PARK | El Dorado | 38.6795 | -120.9797 |  | 1047 | 0.061564 |  | 1953 | 0.00056455 | 99% | V3 Tranche 1 | Tier 2 | 498
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.73323 | - | - | 0.73323 | - | 0.73323 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5715 | -122.4451 |  | 1235 | 0.044601 |  | 873 | 0.0027563 | 99% | V3 Tranche 1 | Tier 3 | 499
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.5423 | - | - | 16.5423 | - | 16.5423 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5446 | -122.4781 |  | 1235 | 0.044601 |  | 33 | 0.025445 | 99% | V3 Tranche 1 | Tier 3 | 500
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.5752 | - | - | 22.5752 | - | 22.5752 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.574 | -122.4444 |  | 792 | 0.094959 |  | 59 | 0.021383 | 99% | V3 Tranche 1 | Tier 3 | 501
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3951 | - | - | 4.3951 | - | 4.3951 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5755 | -122.4443 |  | 1235 | 0.044601 |  | 14 | 0.034265 | 99% | V3 Tranche 1 | Tier 3 | 502
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.3167 | - | - | 3.3167 | - | 3.3167 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5146 | -122.4742 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | 99% | V3 Tranche 1 | Tier 3 | 503
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.946 | - | - | 0.946 | - | 0.946 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.545 | -122.4756 |  | 690 | 0.11274 |  | 435 | 0.0064165 | 99% | V3 Tranche 1 | Tier 3 | 504
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 32.9297 | - | - | 32.9297 | - | 32.9297 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.6152 | -122.4292 |  | 279 | 0.22347 |  | 203 | 0.012452 | 99% | V3 Tranche 1 | Tier 3 | 505
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.1027 | - | - | 14.1027 | - | 14.1027 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5533 | -122.4563 |  | 1254 | 0.043133 |  | 101 | 0.018153 | 99% | V3 Tranche 1 | Tier 3 | 506
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.9886 | - | - | 22.9886 | - | 22.9886 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.617 | -122.4242 |  | 309 | 0.21008 |  | 805 | 0.00309 | 99% | V3 Tranche 1 | Tier 3 | 507
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7133 | - | - | 0.7133 | - | 0.7133 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5099 | -122.4785 |  | 2341 | 0.0030939 |  | 419 | 0.0067032 | 99% | V3 Tranche 1 | Tier 3 | 508
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.16686 | - | - | 0.16686 | - | 0.16686 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.505 | -122.4747 |  | 3223 | 5.7874e-06 |  | 793 | 0.0031429 | 99% | V3 Tranche 1 | Tier 3 | 509
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3898 | - | - | 4.3898 | - | 4.3898 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5377 | -122.4954 |  | 1947 | 0.010281 |  | 556 | 0.0048458 | 99% | V3 Tranche 1 | Tier 3 | 510
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.2957 | - | - | 9.2957 | - | 9.2957 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4984 | -122.4795 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | 99% | V3 Tranche 1 | Tier 3 | 511
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.5635 | - | - | 2.5635 | - | 2.5635 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5286 | -122.5007 |  | 1901 | 0.011541 |  | 291 | 0.0096168 | 99% | V3 Tranche 1 | Tier 3 | 512
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0817 | - | - | 1.0817 | - | 1.0817 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5471 | -122.5102 |  | 2241 | 0.0043094 |  | 594 | 0.0044669 | 99% | V3 Tranche 1 | Tier 3 | 513
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.3847 | - | - | 0.3847 | - | 0.3847 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5057 | -122.4845 |  | 3085 | 9.3615e-06 |  | 416 | 0.0067497 | 99% | V3 Tranche 1 | Tier 3 | 514
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.1185 | - | - | 13.1185 | - | 13.1185 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5071 | -122.4907 |  | 1361 | 0.035763 |  | 87 | 0.018978 | 99% | V3 Tranche 1 | Tier 3 | 515
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.19139 | - | - | 0.19139 | - | 0.19139 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5206 | -122.4936 |  | 2341 | 0.0030939 |  | 1407 | 0.0011424 | 99% | V3 Tranche 1 | HFRA | 516
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.12596 | - | - | 0.12596 | - | 0.12596 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 |  | 2351 | 0.0030112 |  | 90 | 0.018786 | 99% | V3 Tranche 1 | Tier 3 | 517
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76549 | - | - | 0.76549 | - | 0.76549 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4943 | -122.4756 |  | 3201 | 6.2313e-06 |  | 117 | 0.016818 | 99% | V3 Tranche 1 | Tier 3 | 518
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4863 | - | - | 5.4863 | - | 5.4863 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2328 | -120.3655 |  | 2540 | 0.0015977 |  | 186 | 0.013343 | 99% | V3 Tranche 1 | Tier 3 | 519
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7986 | - | - | 23.7986 | - | 23.7986 | ST | Region 5 - Central Valley | AVERY | Calaveras | 38.1832 | -120.3754 |  | 1412 | 0.032657 |  | 66 | 0.02064 | 99% | V3 Tranche 1 | Tier 3 | 520
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.7987 | - | - | 5.7987 | - | 5.7987 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1743 | -120.3835 |  | 1661 | 0.020479 |  | 269 | 0.010091 | 99% | V3 Tranche 1 | Tier 2 | 521
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6801 | - | - | 12.6801 | - | 12.6801 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1699 | -120.4067 |  | 2142 | 0.0062159 |  | 231 | 0.011425 | 99% | V3 Tranche 1 | Tier 2 | 522
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 44.875 | - | - | 44.875 | - | 44.875 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | V3 Tranche 1 | Tier 2 | 523
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7229 | - | - | 23.7229 | - | 23.7229 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2366 | -120.3628 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | 99% | V3 Tranche 1 | Tier 3 | 524
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.4909 | - | - | 8.4909 | - | 8.4909 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2465 | -120.3642 |  | 2810 | 0.00026318 |  | 98 | 0.01848 | 99% | V3 Tranche 1 | Tier 3 | 525
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.3846 | - | - | 10.3846 | - | 10.3846 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2369 | -120.3646 |  | 2670 | 0.0008147 |  | 60 | 0.021109 | 99% | V3 Tranche 1 | Tier 3 | 526
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.2061 | - | - | 10.2061 | - | 10.2061 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | V3 Tranche 1 | Tier 3 | 527
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7453 | - | - | 27.7453 | - | 27.7453 | NV | Region 2 - North East | CHICO | Butte | 39.8318 | -121.8444 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | 99% | V3 Tranche 1 | Tier 3 | 528
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.1262 | - | - | 27.1262 | - | 27.1262 | NV | Region 2 - North East | COHASSET | Butte | 39.9034 | -121.742 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | 99% | V3 Tranche 1 | Tier 3 | 529
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3948 | - | - | 4.3948 | - | 4.3948 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4495 | -120.4908 |  | 1744 | 0.016801 |  | 151 | 0.015433 | 99% | V3 Tranche 1 | Tier 3 | 530
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32281 | - | - | 0.32281 | - | 0.32281 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4491 | -120.4927 |  | 1744 | 0.016801 |  | 8 | 0.040941 | 99% | V3 Tranche 1 | Tier 3 | 531
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.0017 | - | - | 16.0017 | - | 16.0017 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1583 | -122.9898 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | V3 Tranche 1 | Tier 2 | 532
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8763 | - | - | 11.8763 | - | 11.8763 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1825 | -122.9619 |  | 259 | 0.23008 |  | 327 | 0.0086415 | 99% | V3 Tranche 1 | Tier 2 | 533
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.4939 | - | - | 15.4939 | - | 15.4939 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1894 | -122.9009 |  | 705 | 0.11161 |  | 309 | 0.0089653 | 99% | V3 Tranche 1 | Tier 3 | 534
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3587 | - | - | 1.3587 | - | 1.3587 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1457 | -122.9167 |  | 6 | 1.2559 |  | 588 | 0.0045199 | 99% | V3 Tranche 1 | Tier 2 | 535
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.4554 | - | - | 29.4554 | - | 29.4554 | SI | Region 2 - North East | WEIMAR | Placer | 39.0443 | -120.9859 |  | 1379 | 0.034582 |  | 166 | 0.014596 | 99% | V3 Tranche 1 | Tier 2 | 536
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.2219 | - | - | 23.2219 | - | 23.2219 | SI | Region 2 - North East | WEIMAR | Placer | 39.0318 | -120.9741 |  | 1801 | 0.014579 |  | 142 | 0.015811 | 99% | V3 Tranche 1 | Tier 2 | 537
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.6912 | - | - | 19.6912 | - | 19.6912 | SI | Region 2 - North East | WEIMAR | Placer | 39.0342 | -120.9744 |  | 2258 | 0.003969 |  | 272 | 0.010047 | 99% | V3 Tranche 1 | Tier 2 | 538
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7753 | - | - | 7.7753 | - | 7.7753 | SI | Region 2 - North East | WEIMAR | Placer | 39.0352 | -120.9794 |  | 2599 | 0.0011906 |  | 268 | 0.010095 | 99% | V3 Tranche 1 | Tier 2 | 539
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.8119 | - | - | 10.8119 | - | 10.8119 | SI | Region 2 - North East | WEIMAR | Placer | 39.036 | -120.9881 |  | 2422 | 0.0023893 |  | 214 | 0.012028 | 99% | V3 Tranche 1 | Tier 2 | 540
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.1738 | - | - | 8.1738 | - | 8.1738 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4437 | -120.5088 |  | 2589 | 0.0012622 |  | 352 | 0.0079522 | 99% | V3 Tranche 1 | Tier 3 | 541
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3469 | - | - | 29.3469 | - | 29.3469 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.487 | -120.5231 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | 99% | V3 Tranche 1 | Tier 3 | 542
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.385 | - | - | 14.385 | - | 14.385 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4645 | -120.5292 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | 99% | V3 Tranche 1 | Tier 3 | 543
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0056 | - | - | 6.0056 | - | 6.0056 | ST | Region 5 - Central Valley | MOUNTAIN RANCH | Amador | 38.421 | -120.5497 |  | 1765 | 0.015736 |  | 218 | 0.011836 | 99% | V3 Tranche 1 | Tier 3 | 544
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.374 | - | - | 1.374 | - | 1.374 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4575 | -120.5238 |  | 2786 | 0.00032448 |  | 681 | 0.0038479 | 99% | V3 Tranche 1 | Tier 3 | 545
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.2384 | - | - | 12.2384 | - | 12.2384 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3174 | -120.5212 |  | 2247 | 0.0041901 |  | 80 | 0.019265 | 99% | V3 Tranche 1 | Tier 3 | 546
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 90.2567 | - | - | 90.2567 | - | 90.2567 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3314 | -120.5186 |  | 1206 | 0.047319 |  | 164 | 0.014654 | 99% | V3 Tranche 1 | Tier 3 | 547
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.7214 | - | - | 9.7214 | - | 9.7214 | NV | Region 2 - North East | PLATINA | Shasta | 40.3595 | -122.8928 |  | 52 | 0.41883 |  | 86 | 0.018983 | 99% | V3 Tranche 1 | Tier 2 | 548
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.0775 | - | - | 10.0775 | - | 10.0775 | NV | Region 2 - North East | WILDWOOD | Trinity | 40.3846 | -123.0286 |  | 1125 | 0.054922 |  | 191 | 0.013119 | 99% | V3 Tranche 1 | Tier 2 | 549
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.6734 | - | - | 5.6734 | - | 5.6734 | NV | Region 2 - North East | PLATINA | Shasta | 40.3606 | -122.8896 |  | 598 | 0.13184 |  | 111 | 0.017225 | 99% | V3 Tranche 1 | Tier 2 | 550
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.284 | - | - | 6.284 | - | 6.284 | NV | Region 2 - North East | PLATINA | Shasta | 40.3607 | -122.9513 |  | 454 | 0.16402 |  | 109 | 0.017355 | 99% | V3 Tranche 1 | Tier 2 | 551
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.023199 | - | - | 0.023199 | - | 0.023199 | NB | Region 1 - North Coast | Calistoga | Napa | 38.579 | -122.5144 |  | 1624 | 0.022 |  | 874 | 0.0027 | 99% | V3 Tranche 1 | Tier 3 | 552 | 0.01856 | 0.023199
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0166 | - | - | 6.0166 | - | 6.0166 | NV | Region 2 - North East | Belden | Plumas | 39.9114 | -121.327 |  | 11 | 0.735 |  | 21 | 0.029 | 99% | V3 Tranche 1 | Tier 2/3 | 553 | 4.8133 | 6.0166
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.2372 | - | - | 20.2372 | - | 20.2372 | SI | Region 2 - North East | COLFAX | Placer | 39.1003 | -120.9524 |  | 1581 | 0.0237 |  | 208 | 0.0122 | 99% | V3 Tranche 1 | Non Tier, Tier 2 | 554 | 16.1898 | 20.2372
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1681 | -120.1025 |  | 911 | 0.0788 |  | 335 | 0.0085 | 99% | V3 Tranche 1 | Tier 3 | 555 | 0.0028409 | 0.0035511
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035512 | - | - | 0.0035512 | - | 0.0035512 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 |  | 323 | 0.201 |  | 136 | 0.016 | 99% | V3 Tranche 1 | Tier 2 | 556 | 0.0028409 | 0.0035512
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.35 | - | - | 6.35 | - | 6.35 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 |  | 658 | 0.118 |  | 46 | 0.023 | 99% | V3 Tranche 1 | Tier 2 | 557 | 5.08 | 6.35

## Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | In-Construction | *
DOCC | Post-Construction | *
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles

## ProjectType
Category | Description | ProjectType | Description
Base SH | Planned projects in System Hardening program | CWSP 2022-2023 | Community Wildfire Safety Program for projects aimed for 2022-2023
|  | CWSP - 2023 ICUG | Incremental Undergrounding (ICUG) for 2023
|  | ECOP | EC Tag Optimization
|  | ECOP - Top 20% | EC Tag Optimization in the top 20% of the 2021 risk model
|  | PRE | Projects that had poles in the ground and construction had begun, based on 2018 risk model
|  | PSPS - Community Resiliency | Public Safety Power Shutoff projects
|  | PSPS - 2023 ICUG | Public Safety Power Shutoff projects - Incremental Undergrounding (ICUG) for 2023
|  | PSPS – Scoped | Public Safety Power Shutoff projects that had been scoped, based on 2018 risk model
|  | PSS Approved | Public Safety Specialists approved projects
|  | Remote Grid | Remote Grid projects
|  | Remote Grid Pilot | Remote Grid projects part of the Pilot program
|  | Storm Rebuild | Storm Rebuild projects
|  | Top 20% MAVF CPZ | Top 20% of Multi-Attribute Value Function Circuit Protection Zones based on the 2021 risk model
|  | Top 250 miles | Top 250 miles based on the 2021 risk model
|  | Top 50 Miles | Top 50 miles based on the 2021 risk model
Fire Rebuild | Hardening Scope as a result of fires in HFTD | FRRB - OH – 2021 | Fire Rebuild - Overhead Hardening
|  | FRRB - REMG – 2021 | Fire Rebuild - Remote Grid Projects
|  | FRRB - UG – 2021 | Fire Rebuild - Underground Hardening
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH | V3 Tranche 1 | Bundled Circuit Segments based on WFE (Wildfire Feasibility Efficiency) calculation
Other | Non-08W projects (New Busines, WRO, Capacity, Rule 20A, etc.) | Other | Non-08W projects (New Busines, WRO, Capacity, Rule 20A, etc.)
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds | Butte Rebuild | Paradise and Surrounding Areas