## Project List
Order | Order Description | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2020 Miles Installed | 2021 Miles Installed | 2022 Forecast Miles | 2023 Forecast Miles | 2024 Forecast Miles | Div | Region | City | County | Latitude | Longitude | Circuit Protection Zone | 2021 Risk Rank | Project Type (see 3rd tab for description) | HFTD Tier
35286103 |  | Base SH | 08W | UNSE | Scoping/Scoped | 13.9201 | 0 | 0 | 13.9201 | 0 | 0 | 0 | 13.9201 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 3328 | CWSP 2022-2023 | Tier 2
35294729 |  | Base SH | 08W | UNSE | Scoping/Scoped | 6.4 | 0 | 0 | 6.4 | 0 | 0 | 0 | 6.4 | 0 | NV | Region 2 - North East | Burney | Shasta | 40.9794 | -122.1091 |  | 2320 | CWSP 2022-2023 | Tier 2
35294730 |  | Base SH | 08W | UNSE | Scoping/Scoped | 6.21 | 0.079924 | 0 | 6.29 | 0 | 0 | 0 | 6.29 | 0 | NV | Region 2 - North East | Burney | Shasta | 40.9794 | -122.1091 |  | 2320 | CWSP 2022-2023 | Tier 2
35223060 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0 | 0 | 0.036553 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | PSPS - Community Resiliency | Tier 3
35298571 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Anderson | SHASTA | 40.469 | -122.2542 |  | 143 | CWSP 2022-2023 | Tier 2
35254242 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.9436 | 0 | 1.9436 | 0 | 0 | 0 | 1.9436 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0812 | -119.4864 |  | 330 | CWSP 2022-2023 | Tier 2
35278889 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1968 | 0 | 2.1968 | 0 | 0 | 0 | 2.1968 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0894 | -119.4783 |  | 330 | CWSP 2022-2023 | Tier 2
35279181 |  | Fire Rebuild | 08W | ESTS | Estimating | 5.589 | 0 | 0 | 5.589 | 0 | 0 | 5.589 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | FRRB - UG - 2021 | Tier 2 & 3
35277926 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.4417 | 0 | 3.4417 | 0 | 0 | 3.4417 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0749 | -119.4852 |  | 63 | CWSP 2022-2023 | Tier 2
35277927 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8672 | 0 | 2.8672 | 0 | 0 | 0 | 2.8672 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.067 | -119.4802 |  | 63 | CWSP 2022-2023 | Tier 2
35277929 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7939 | 0 | 2.7939 | 0 | 0 | 2.7939 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0578 | -119.4739 |  | 63 | CWSP 2022-2023 | Tier 2
35277930 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.32936 | 0 | 0.32936 | 0 | 0 | 0 | 0.32936 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0528 | -119.4629 |  | 63 | CWSP 2022-2023 | Tier 2
35277931 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.5072 | 0 | 3.5072 | 0 | 0 | 0 | 3.5072 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0503 | -119.4639 |  | 63 | CWSP 2022-2023 | Tier 2
35254078 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.6199 | 0 | 2.6199 | 0 | 0 | 2.6199 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0677 | -119.4958 |  | 63 | CWSP 2022-2023 | Tier 2
35254079 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.4011 | 0 | 2.4011 | 0 | 0 | 2.4011 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0677 | -119.4958 |  | 63 | CWSP 2022-2023 | Tier 2
35254243 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.91 | 0 | 2.91 | 0 | 0 | 0 | 2.91 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0173 | -119.427 |  | 163 | CWSP 2022-2023 | Tier 2
35254244 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 2.66 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0173 | -119.427 |  | 163 | CWSP 2022-2023 | Tier 2
35254245 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 2.958 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0173 | -119.427 |  | 163 | CWSP 2022-2023 | Tier 2
35254246 |  | Base SH | 08W | ADER | Estimating | 0 | 2.6201 | 0 | 2.6201 | 0 | 0 | 2.6201 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0173 | -119.427 |  | 163 | CWSP 2022-2023 | Tier 2
35254247 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.95 | 0 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0173 | -119.427 |  | 163 | CWSP 2022-2023 | Tier 2
35277936 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.94 | 0 | 3.94 | 0 | 0 | 0 | 3.94 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0143 | -119.4031 |  | 163 | CWSP 2022-2023 | Tier 2
35277937 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8701 | 0 | 2.8701 | 0 | 0 | 0 | 2.8701 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0129 | -119.3939 |  | 163 | CWSP 2022-2023 | Tier 2
35235677 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 5.414 | 0 | 0 | 5.414 | 0 | 5.414 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1288 | FRRB - UG - 2021 | Tier 3
35278091 |  | Base SH | 08W | ADER | Estimating | 0 | 2.839 | 0 | 2.839 | 0 | 0 | 0 | 2.839 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9796 | -119.3694 |  | 163 | CWSP 2022-2023 | Tier 2
35278092 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.8369 | 0 | 3.8369 | 0 | 0 | 0 | 3.8369 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.978 | -119.3677 |  | 163 | CWSP 2022-2023 | Tier 2
35294728 |  | Base SH | 08W | UNSE | Scoping/Scoped | 5.3799 | 0 | 0 | 5.3799 | 0 | 0 | 0 | 5.3799 | 0 | NV | Region 2 - North East | Burney | Shasta | 40.9794 | -122.1091 |  | 1816 | CWSP 2022-2023 | Tier 2
35278096 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.2299 | 0 | 1.2299 | 0 | 0 | 1.2299 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9806 | -119.3952 |  | 163 | CWSP 2022-2023 | Tier 2
35278097 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.2 | 0.29602 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.98 | -119.4029 |  | 163 | CWSP 2022-2023 | Tier 2
35278098 |  | Base SH | 08W | ADER | Estimating | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 1.54 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9796 | -119.4037 |  | 163 | CWSP 2022-2023 | Tier 2
35278890 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.75 | 0 | 1.75 | 0 | 0 | 0 | 1.75 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9737 | -119.3888 |  | 163 | CWSP 2022-2023 | Tier 2
35278891 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9752 | -119.3882 |  | 163 | CWSP 2022-2023 | Tier 2
35278892 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 2.5299 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9662 | -119.3834 |  | 163 | CWSP 2022-2023 | Tier 2
35277921 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 2.4 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0111 | -119.4175 |  | 163 | CWSP 2022-2023 | Tier 2
35277922 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 1.76 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.005 | -119.4055 |  | 163 | CWSP 2022-2023 | Tier 2
35277923 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 3.1701 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9916 | -119.4068 |  | 163 | CWSP 2022-2023 | Tier 2
35256083 |  | Base SH | 08W | UNSE | Scoping/Scoped | 5.0909 | 2.467 | 0 | 7.558 | 0 | 0 | 0 | 7.558 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1434 | -123.0023 |  | 335 | CWSP 2022-2023 | Tier 2
35278090 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8492 | 0.39583 | 3.2451 | 0 | 0 | 0 | 3.2451 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0201 | -119.4294 |  | 274 | CWSP 2022-2023 | Tier 2
35277933 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1036 | 0 | 2.1036 | 0 | 0 | 0 | 2.1036 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0335 | -119.4426 |  | 274 | CWSP 2022-2023 | Tier 2
35277934 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1415 | 0 | 2.1415 | 0 | 0 | 0 | 2.1415 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0314 | -119.4428 |  | 274 | CWSP 2022-2023 | Tier 2
35297692 |  | Fire Rebuild | 08W | ESTS | Estimating | 4.6598 | 0 | 0 | 4.6598 | 0 | 0 | 4.6598 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35254240 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 0 | 2.1252 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0362 | -119.452 |  | 274 | CWSP 2022-2023 | Tier 2
35254241 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8248 | 0 | 2.8248 | 0 | 0 | 0 | 2.8248 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0362 | -119.452 |  | 274 | CWSP 2022-2023 | Tier 2
35226629 |  | Base SH | 08W | PEND | Permitting/Dependency | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 4.5 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35052731 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.5271 | 0 | 1.5271 | 0 | 0.57917 | 0.94792 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1332 | -122.1257 |  | 2456 | Pre | Tier 3
35113950 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.2451 | 0 | 3.2451 | 0 | 0 | 3.2451 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1332 | -122.1257 |  | 2456 | Pre | Tier 3
35113951 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.3443 | 0 | 2.3443 | 0 | 0 | 2.3443 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1499 | -122.1363 |  | 2456 | Pre | Tier 3
35219289 |  | Base SH | 08W | ESTS | Estimating | 4.3544 | 0 | 0 | 4.3544 | 0 | 0 | 4.3544 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35142826 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.5932 | 0 | 1.5932 | 0 | 1.5932 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.2906 | -120.9978 |  | 2521 | Pre | Tier 3
35117443 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 2.1347 | 0 | 2.1347 | 0 | 2.1347 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.3003 | -121.0157 |  | 2144 | Pre | Tier 3
35115148 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.1331 | 0 | 2.1331 | 2.0127 | 0.12045 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.2957 | -121.0155 |  | 2144 | Pre | Tier 3
35115151 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.9057 | 0 | 1.9057 | 0 | 1.9057 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.3037 | -121.0396 |  | 2144 | Pre | Tier 3
35115152 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.7013 | 0 | 1.7013 | 0 | 0.80076 | 0.90057 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.3166 | -121.037 |  | 2144 | Pre | Tier 3
35115153 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7006 | 0 | 1.7006 | 0 | 1.7006 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.299 | -121.0391 |  | 2144 | Pre | Tier 3
35115154 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.6462 | 0 | 1.6462 | 0 | 1.6462 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.3103 | -121.0216 |  | 2144 | Pre | Tier 3
35061206 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7348 | 0 | 1.7348 | 0 | 1.7348 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.2755 | -121.0223 |  | 2144 | Pre | Tier 3
35061212 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.9985 | 0 | 1.9985 | 0 | 1.9985 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.291 | -121.0309 |  | 2144 | Pre | Tier 3
35061213 |  | Base SH | 08W | CLSD | Closed | 0 | 1.4511 | 0 | 1.4511 | 1.3445 | 0.10663 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.2907 | -121.0162 |  | 2144 | Pre | Tier 3
35284364 |  | Base SH | 08W | UNSE | Scoping/Scoped | 4.3498 | 0.040341 | 0 | 4.3902 | 0 | 0 | 0 | 4.3902 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | 235 | CWSP 2022-2023 | Tier 2 & 3
35223062 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0.13125 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5766 | -122.5839 |  | 3098 | PSPS - Community Resiliency | Tier 2
35114100 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.95076 | 0 | 0.95076 | 0 | 0.95076 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ | 37.1088 | -121.9868 |  | 2464 | Pre | Tier 3
35114102 |  | Base SH | 08W | CLSD | Closed | 0 | 0.73428 | 0 | 0.73428 | 0.16004 | 0.57424 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ | 37.0987 | -121.9895 |  | 2464 | Pre | Tier 3
35114103 |  | Base SH | 08W | CLSD | Closed | 0 | 1.1294 | 0 | 1.1294 | 0 | 1.1294 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ | 37.0997 | -121.9916 |  | 2464 | Pre | Tier 3
35243441 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 2.3233 | 0 | NV | Region 2 - North East | Brownsville | YUBA | 39.483 | -121.2466 |  | 1428 | REMG 2022-2023 | Tier 2 & 3
35292754 |  | Fire Rebuild | 08W | ESTS | Estimating | 4.2299 | 0 | 0 | 4.2299 | 0 | 0 | 4.2299 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35145522 |  | Base SH | 08W | PEND | Permitting/Dependency | 4.0494 | 0 | 0 | 4.0494 | 0 | 0 | 4.0494 | 0 | 0 | SI | Region 2 - North East | El Dorado Hills | El Dorado |  |  |  | 134 | PSPS - Community Resiliency | Tier 2
35223344 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 3.8902 | 0 | 0 | 3.8902 | 0 | 3.8902 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6394 | -121.4295 |  | 1849 | FRRB - UG - 2021 | Tier 3
35223345 |  | Fire Rebuild | 08W | FICL | Post-Construction | 3.7676 | 0 | 0 | 3.7676 | 0 | 3.7676 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35062376 |  | Base SH | 08W | APPR | Estimating | 3.2866 | 0 | 0 | 3.2866 | 0 | 0 | 3.2866 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  |  | 159 | Top 20% MAVF CPZ | Tier 3
35278899 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.9449 | 0 | 0 | 2.9449 | 0 | 0 | 0 | 2.9449 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | 56 | CWSP 2022-2023 | Tier 2 & 3
35225593 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.05 | 0 | 1.05 | 0 | 0 | 1.05 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.8879 | -121.8676 |  | 377 | ECOP - Top 20% | Tier 3
35217275 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.9 | 0 | 0 | 2.9 | 0 | 0 | 2.9 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 |  | 2055 | FRRB - UG - 2021 | Tier 2
35233950 |  | Base SH | 08W | ESTS | Estimating | 2.8943 | 0 | 0 | 2.8943 | 0 | 0 | 2.8943 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35243452 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.3625 | 0 | 3.3625 | 0 | 0 | 3.3625 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2234 | -119.7689 |  | 144 | CWSP 2022-2023 | Tier 2
35249996 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.9536 | 0 | 1.9536 | 0 | 0 | 1.9536 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2234 | -119.7689 |  | 144 | CWSP 2022-2023 | Tier 2
35249997 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.115 | 0 | 2.115 | 0 | 0 | 2.115 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2234 | -119.7689 |  | 144 | CWSP 2022-2023 | Tier 2
35249998 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.6773 | 0 | 3.6773 | 0 | 0 | 3.6773 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2234 | -119.7689 |  | 144 | CWSP 2022-2023 | Tier 2
35249999 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.0688 | 0 | 2.0688 | 0 | 0 | 2.0688 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2234 | -119.7689 |  | 144 | CWSP 2022-2023 | Tier 2
35227260 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2362 | 0 | 2.2362 | 0 | 2.2362 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2275 | -119.6896 |  | 66 | Top 250 Miles | Tier 2
35227261 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.729 | 0 | 1.729 | 0 | 1.729 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2275 | -119.6896 |  | 66 | Top 250 Miles | Tier 2
35227262 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7343 | 0 | 1.7343 | 0 | 1.7343 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2275 | -119.6896 |  | 66 | Top 250 Miles | Tier 2
35240160 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 4.3841 | 0 | 4.3841 | 0 | 0 | 4.3841 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35240162 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35240163 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.2153 | 0 | 2.2153 | 0 | 0 | 0 | 2.2153 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35249871 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.0186 | 0 | 2.0186 | 0 | 0 | 2.0186 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35249872 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.725 | 0 | 2.725 | 0 | 0 | 2.725 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35249873 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.8913 | 0 | 3.8913 | 0 | 0 | 0 | 3.8913 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35249874 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.7922 | 0 | 3.7922 | 0 | 0 | 0 | 3.7922 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35250737 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8564 | 0 | 2.8564 | 0 | 0 | 0 | 2.8564 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35250738 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.4856 | 0 | 3.4856 | 0 | 0 | 0 | 3.4856 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2285 | -119.7103 |  | 61 | CWSP 2022-2023 | Tier 2
35240164 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0979 | 0 | 2.0979 | 0 | 0 | 0 | 2.0979 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.264 | -119.7128 |  | 78 | CWSP 2022-2023 | Tier 2
35240165 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.8498 | 0 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.269 | -119.7126 |  | 132 | CWSP 2022-2023 | Tier 2
35249875 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.6394 | 0 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.269 | -119.7126 |  | 132 | CWSP 2022-2023 | Tier 2
35249876 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.6483 | 0 | 3.6483 | 0 | 0 | 3.6483 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.269 | -119.7126 |  | 132 | CWSP 2022-2023 | Tier 2
35249877 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 1.0299 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.269 | -119.7126 |  | 132 | CWSP 2022-2023 | Tier 2
35219097 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.4794 | 0 | 2.4794 | 0 | 0 | 2.4794 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | MADERA | 37.2276 | -119.6896 |  | 22 | Top 250 Miles | Tier 2
35229051 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.9003 | -122.5065 |  | 413 | Remote Grid Pilot | Tier 3
35276100 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.9108 | -122.493 |  | 413 | Remote Grid Pilot | Tier 3
35241072 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.6 | 0.21004 | 3.81 | 0 | 0 | 3.81 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.573 | -122.2386 |  | 100 | CWSP 2022-2023 | Tier 2
35243447 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.64 | 0.032955 | 2.6729 | 0 | 0 | 2.6729 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.573 | -122.2386 |  | 100 | CWSP 2022-2023 | Tier 2
35259511 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 2.77 | 0 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA | 40.6276 | -122.2347 |  | 100 | CWSP 2022-2023 | Tier 2
35235676 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.8788 | 0 | 0 | 2.8788 | 0 | 0.11231 | 2.7665 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1288 | FRRB - UG - 2021 | Tier 3
35259515 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4752 | 0 | 2.4752 | 0 | 0 | 2.4752 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5836 | -122.2422 |  | 100 | CWSP 2022-2023 | Tier 2
35227007 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.8756 | 0 | 0 | 2.8756 | 0 | 0 | 0 | 2.8756 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35259514 |  | Base SH | 08W | ADER | Estimating | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 3.61 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5894 | -122.2244 |  | 301 | CWSP 2022-2023 | Tier 2
35241071 |  | Base SH | 08W | APPR | Estimating | 0 | 2.0356 | 0.325 | 2.3606 | 0 | 0 | 2.3606 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5725 | -122.2381 |  | 301 | CWSP 2022-2023 | Tier 2
35243448 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.69 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5929 | -122.2396 |  | 99 | CWSP 2022-2023 | Tier 2
35241073 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.8553 | 0 | 3.8553 | 0 | 0 | 3.8553 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5929 | -122.2396 |  | 99 | CWSP 2022-2023 | Tier 2
35259517 |  | Base SH | 08W | ESTS | Estimating | 0 | 4.6008 | 0 | 4.6008 | 0 | 0 | 4.6008 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.593 | -122.2549 |  | 99 | CWSP 2022-2023 | Tier 2
35259513 |  | Base SH | 08W | ESTS | Estimating | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 4.64 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.5918 | -122.2743 |  | 99 | CWSP 2022-2023 | Tier 2
35219286 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 3.361 | 0 | 3.361 | 0 | 0 | 3.361 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35232960 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.9078 | 0 | 2.9078 | 0 | 0 | 2.9078 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35232442 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.9127 | 0 | 2.9127 | 0 | 0 | 2.9127 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35232443 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0093 | 0 | 1.0093 | 0 | 1.0093 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35232444 |  | Base SH | 08W | CONS | In-Construction | 0 | 3.4282 | 0 | 3.4282 | 0 | 1.2443 | 2.1839 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35232445 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.6036 | 0 | 2.6036 | 0 | 0.45246 | 2.1511 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35225825 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.5214 | 0 | 1.5214 | 0 | 1.5214 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.535 | -122.2392 |  | 48 | Top 250 Miles | Tier 2
35026643 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0089 | 0 | 1.0089 | 0 | 0 | 0 | 1.0089 | 0 | SI | Region 2 - North East | El Dorado | El Dorado |  |  |  | 666 | Top 20% MAVF CPZ | Tier 2
35192290 |  | Base SH | 08W | ESTS | Post-Construction | 0 | 5.0519 | 0 | 5.0519 | 0 | 2.8996 | 2.1523 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.739 | -120.9055 |  | 811 | ECOP | Tier 3
35224856 |  | Other | 10Q | ESTS | Estimating | 2.803 | 0.10985 | 0 | 2.9129 | 0 | 0 | 1.1364 | 1.7765 | 0 | NV | Region 2 - North East
35226845 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.3184 | 0 | 2.3184 | 0 | 2.3184 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7201 | -120.861 |  | 811 | ECOP | Tier 3
31361965 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.4483 | 0 | 0.4483 | 0 | 0.4483 | 0 | 0 | 0 | SO | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3919 | -122.53 |  | 1794 | Pre | Tier 3
35234756 |  | Base SH | 08W | ESTS | Estimating | 2.782 | 0 | 0 | 2.782 | 0 | 0 | 0 | 2.782 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35274593 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | 0 | 0 | 2.756 | 0 | 0 | 0 | 2.756 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5165 | -119.9716 |  | 428 | CWSP 2022-2023 | Tier 2
35292755 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.74 | 0 | 0 | 2.74 | 0 | 0 | 2.74 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35222235 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 2.6 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 |  | 2738 | Remote Grid Pilot | Tier 3
35225824 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.6989 | 0 | 0 | 2.6989 | 0 | 2.2879 | 0.41098 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5047 | -121.4524 |  | 1176 | FRRB - UG - 2021 | Tier 2
35219276 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.69 | 0 | 0 | 2.69 | 0 | 0 | 2.69 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35231620 |  | Base SH | 08W | ADER | Estimating | 2.6782 | 0 | 0 | 2.6782 | 0 | 0 | 0 | 2.6782 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35280560 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.64 | 0 | 0 | 2.64 | 0 | 0 | 2.64 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | FRRB - UG - 2021 | Tier 2 & 3
35285249 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.593 | 0 | 0 | 2.593 | 0 | 0 | 0 | 2.593 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1673 | -123.0087 |  | 335 | CWSP 2022-2023 | Tier 2
35282166 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.5902 | 0 | 0 | 2.5902 | 0 | 0 | 2.5902 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS | 40.0604 | -120.9643 |  | 1322 | FRRB | Tier 2
35112435 |  | Base SH | 08W | CLSD | Closed | 0 | 1.3269 | 0 | 1.3269 | 1.1178 | 0.20909 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7525 | -120.5747 |  | 3014 | Pre | Tier 3
35226625 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 8.9 | 0 | NV | Region 2 - North East | Elk Creek | GLENN | 39.6065 | -122.5419 |  | 340 | FRRB - REMG - 2021 | Tier 2
74022384 |  | Base SH | 08W | FICL | Post-Construction | 0 | 5.1314 | 0 | 5.1314 | 0.96004 | 4.1714 | 0 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA | 38.5912 | -122.9201 |  | 481 | Pre | Tier 3
35226626 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0 | 4.15 | 4.15 | 0 | 4.15 | 0 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA | 38.5919 | -122.9622 |  | 945 | FRRB - REMG - 2021 | Tier 2
31334291 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0.51326 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.5022 | -123.7717 |  | 2140 | Pre | Tier 3
35075103 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.63674 | 0 | 0.63674 | 0 | 0.63674 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1383 | -120.4132 |  | 721 | Top 20% MAVF CPZ | Tier 3
35174085 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.095265 | 0 | 0.095265 | 0 | 0.095265 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | CALAVERAS | 38.088 | -120.5696 |  | 2139 | PSPS - Scoped | Tier 3
35233948 |  | Base SH | 08W | ESTS | Estimating | 2.5871 | 0 | 0 | 2.5871 | 0 | 0 | 2.5871 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35225595 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.83807 | 0 | 0.83807 | 0 | 0.11629 | 0.72178 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.549 | -122.72 |  | 637 | ECOP - Top 20% | Tier 3
35225597 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.79356 | 0 | 0.79356 | 0 | 0 | 0.79356 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.549 | -122.72 |  | 637 | ECOP - Top 20% | Tier 3
35225598 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.9053 | 0 | 0.9053 | 0 | 0 | 0.9053 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.549 | -122.72 |  | 637 | ECOP - Top 20% | Tier 3
35246501 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 7.0994 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5702 | -122.6772 |  | 637 | REMG 2022-2023 | Tier 3
35225828 |  | Base SH | 08W | ESTS | Estimating | 2.5314 | 0 | 0 | 2.5314 | 0 | 0 | 2.5314 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35250574 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 8.0701 | 0 | 8.0701 | 0 | 0 | 0 | 8.0701 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0512 | -122.9384 |  | 593 | CWSP 2022-2023 | Tier 2
35250576 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.22992 | 0 | 0.22992 | 0 | 0 | 0 | 0.22992 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0803 | -122.9513 |  | 58 | CWSP 2022-2023 | Tier 2
35283196 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0.66799 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.095 | -122.9656 |  | 58 | CWSP 2022-2023 | Tier 2
35283197 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4381 | 0 | 2.4381 | 0 | 0 | 0 | 2.4381 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0946 | -122.9632 |  | 58 | CWSP 2022-2023 | Tier 2
35283938 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | 0 | 0 | 2.4799 | 0 | 0 | 0 | 2.4799 | 0 | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3845 | -122.2937 |  | 1145 | CWSP 2022-2023 | Tier 3
35283199 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2701 | 0 | 1.2701 | 0 | 0 | 0 | 1.2701 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0813 | -122.9625 |  | 58 | CWSP 2022-2023 | Tier 2
35283340 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.105 | -122.9581 |  | 58 | CWSP 2022-2023 | Tier 2
35299133 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0729 | -122.9569 |  | 19 | CWSP 2022-2023 | Tier 2
35299134 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0704 | -122.9571 |  | 19 | CWSP 2022-2023 | Tier 2
35299135 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0722 | -122.9571 |  | 19 | CWSP 2022-2023 | Tier 2
35299136 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0716 | -122.9638 |  | 19 | CWSP 2022-2023 | Tier 2
35299137 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.067 | -122.9672 |  | 19 | CWSP 2022-2023 | Tier 2
35299138 |  | Base SH | 08W | CLSD | Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.067 | -122.9672 |  | 19 | CWSP 2022-2023 | Tier 2
35250575 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.2299 | 0 | 3.2299 | 0 | 0 | 0 | 3.2299 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0636 | -122.9526 |  | 19 | CWSP 2022-2023 | Tier 2
35254072 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9544 | -122.6079 |  | 74 | CWSP 2022-2023 | Tier 2
35290511 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 1.2799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.979 | -122.6124 |  | 74 | CWSP 2022-2023 | Tier 2
35290512 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 2.06 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9543 | -122.6079 |  | 74 | CWSP 2022-2023 | Tier 2
35290513 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0201 | 0 | 2.0201 | 0 | 0 | 0 | 2.0201 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9769 | -122.6124 |  | 74 | CWSP 2022-2023 | Tier 2
35290514 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.060038 | 0 | 0.060038 | 0 | 0 | 0 | 0.060038 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9794 | -122.6125 |  | 74 | CWSP 2022-2023 | Tier 2
35219099 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7269 | 0 | 2.7269 | 0 | 0 | 2.7269 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35057018 |  | Base SH | 08W | CONS | In-Construction | 2.4557 | 0.19508 | 0 | 2.6508 | 0 | 0 | 2.6508 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 |  | 1946 | PSS Approved | Tier 3
35233314 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.3701 | 0 | 0 | 2.3701 | 0 | 2.0169 | 0.35322 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6254 | -121.398 |  | 1849 | FRRB - UG - 2021 | Tier 3
35231622 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0.88996 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231623 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 1.3799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231624 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 4.2701 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231625 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231626 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0.68314 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231627 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.39867 | 0 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231628 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 1.8799 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231629 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 2.7701 | 2.7701 | 0 | 0 | 0 | 2.7701 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231630 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.36326 | 0 | 0.36326 | 0 | 0 | 0.36326 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35231631 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0.46686 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35226627 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.31761 | 0 | 0.31761 | 0 | 0.31761 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35239098 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35236995 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - REMG - 2021 | Tier 3
35226630 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4 | 0.033523 | 1.4335 | 0 | 0 | 1.4335 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35226631 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.5402 | 0 | 1.5402 | 0 | 1.5402 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35279307 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.25 | 0 | 0 | 2.25 | 0 | 0 | 2.25 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 |  | 1172 | FRRB | Tier 2 & 3
35223024 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.24 | 0 | 0 | 2.24 | 0 | 0 | 2.24 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6152 | -122.4293 |  | 279 | ECOP - Top 20% | Tier 3
35227655 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 3.2598 | 3.2598 | 0 | 0 | 0 | 3.2598 | 0 | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA | 37.9907 | -121.896 |  | 21 | Top 250 Miles | Tier 2
35094397 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0646 | 0 | 1.0646 | 0 | 1.0646 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.9024 | -122.7519 |  | 1999 | Pre | Tier 3
35217270 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.55 | 0 | 0.55 | 0 | 0 | 0 | 0.55 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.93 | -122.7428 |  | 9 | Top 50 Miles | Tier 3
35225589 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0.88996 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.93 | -122.7428 |  | 9 | Top 50 Miles | Tier 3
35225591 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.93 | -122.7428 |  | 9 | Top 50 Miles | Tier 3
35217274 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 |  | 2055 | FRRB - UG - 2021 | Tier 2
35274589 |  | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | 0 | 0 | 2.132 | 0 | 0 | 0 | 2.132 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5186 | -119.9402 |  | 428 | CWSP 2022-2023 | Tier 2 & 3
35119965 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara |  |  |  | 1864 | Pre | Tier 3
35113108 |  | Base SH | 08W | CLSD | Closed | 0 | 0.72102 | 0 | 0.72102 | 0 | 0.72102 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CRUZ | 37.1912 | -122.0324 |  | 1864 | Pre | Tier 3
35250572 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.953 | 0 | 1.953 | 0 | 0 | 0 | 1.953 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5026 | -119.9886 |  | 605 | CWSP 2022-2023 | Tier 2
35274595 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0.057 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4983 | -119.9732 |  | 605 | CWSP 2022-2023 | Tier 2
35274596 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.214 | 0.172 | 1.386 | 0 | 0 | 0 | 1.386 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4889 | -119.9738 |  | 605 | CWSP 2022-2023 | Tier 2
35219281 |  | Base SH | 08W | CONS | In-Construction | 2.1025 | 0 | 0 | 2.1025 | 0 | 0 | 2.1025 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8982 | -120.9827 |  | 45 | Top 250 Miles | Tier 2
35274591 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.022 | 0 | 1.022 | 0 | 0 | 0 | 1.022 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5195 | -119.9397 |  | 428 | CWSP 2022-2023 | Tier 2 & 3
35274592 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.963 | 0 | 1.963 | 0 | 0 | 0 | 1.963 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5116 | -119.9647 |  | 428 | CWSP 2022-2023 | Tier 2
35237889 |  | Fire Rebuild | 08W | CONS | In-Construction | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35274594 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.078 | 0 | 3.078 | 0 | 0 | 0 | 3.078 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5353 | -119.9554 |  | 428 | CWSP 2022-2023 | Tier 2
35250570 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4009 | 0 | 2.4009 | 0 | 0 | 0 | 2.4009 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4927 | -119.9656 |  | 428 | CWSP 2022-2023 | Tier 2 & 3
35250571 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 4.595 | 0 | 4.595 | 0 | 0 | 0 | 4.595 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4927 | -119.9656 |  | 428 | CWSP 2022-2023 | Tier 2
35238088 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4927 | -119.9656 |  | 428 | Remote Grid Pilot | Tier 3
35161152 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.081439 | 0 | 0.081439 | 0 | 0.081439 | 0 | 0 | 0 | YO | Region 5 - Central Valley | [5 empty] | 700 | Remote Grid | Tier 2 & 3
35219268 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.972 | 0 | 1.972 | 0 | 1.972 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5065 | -120.0082 |  | 36 | Top 250 Miles | Tier 2
35238567 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0.10436 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5065 | -120.0082 |  | 36 | Top 250 Miles | Tier 2
35226240 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.2004 | 0 | 1.2004 | 0 | 1.2004 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5065 | -120.0082 |  | 36 | Top 250 Miles | Tier 2
35226241 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.2593 | 0 | 1.2593 | 0 | 1.2593 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5065 | -120.0082 |  | 36 | Top 250 Miles | Tier 2
35250573 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.759 | 0 | 1.759 | 0 | 0 | 0 | 1.759 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5046 | -120.0081 |  | 57 | CWSP 2022-2023 | Tier 2
35274597 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.63295 | 0 | 0.63295 | 0 | 0 | 0 | 0.63295 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5054 | -120.0067 |  | 57 | CWSP 2022-2023 | Tier 2
35217267 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.93977 | 0 | 0.93977 | 0 | 0.93977 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4872 | -119.9618 |  | 10 | Top 50 Miles | Tier 2 & 3
35219267 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6701 | 0 | 1.6701 | 0 | 0 | 1.6701 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4861 | -119.9697 |  | 50 | Top 250 Miles | Tier 2 & 3
35219587 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.0299 | 0 | 2.0299 | 0 | 0 | 2.0299 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4867 | -119.9603 |  | 50 | Top 250 Miles | Tier 2 & 3
35219588 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9482 |  | 50 | Top 250 Miles | Tier 2 & 3
35192284 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.6157 | -122.4315 |  | 279 | ECOP - Top 20% | Tier 3
35219266 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.9312 | 0 | 2.9312 | 0 | 0 | 2.9312 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5059 | -120.005 |  | 35 | Top 250 Miles | Tier 2
35227263 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 2.5125 | 0 | 2.5125 | 0 | 2.5125 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5059 | -120.005 |  | 35 | Top 250 Miles | Tier 2
35279182 |  | Fire Rebuild | 08W | ESTS | Estimating | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | FRRB - UG - 2021 | Tier 2 & 3
35234284 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.24053 | 0 | 0.24053 | 0 | 0 | 0.24053 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR | 38.3949 | -120.804 |  | 999 | PSPS - Community Resiliency | Tier 2
35236985 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 2.0655 | 0 | 0 | 2.0655 | 0 | 0 | 2.0655 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - REMG - 2021 | Tier 3
35219098 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.70265 | 0 | 0.70265 | 0 | 0 | 0.70265 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7513 | -122.6112 |  | 23 | Top 250 Miles | Tier 2 & 3
35062374 |  | Base SH | 08W | PEND | Permitting/Dependency | 2.0513 | 0 | 0 | 2.0513 | 0 | 0 | 2.0513 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  |  | 227 | Top 20% MAVF CPZ | Tier 3
35137593 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.3786 | 0 | 1.3786 | 0 | 0 | 1.3786 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.8654 | -122.7693 |  | 328 | ECOP - Top 20% | Tier 3
35137596 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0116 | 0 | 1.0116 | 0 | 0 | 1.0116 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.8546 | -122.7807 |  | 328 | ECOP - Top 20% | Tier 3
35219272 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.92 | 0 | 0.92 | 0 | 0 | 0.92 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7628 | -122.6133 |  | 38 | Top 250 Miles | Tier 2 & 3
35227027 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35227028 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35227029 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 1.04 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35192282 |  | Base SH | 08W | ESTS | Estimating | 2.04 | 0 | 0 | 2.04 | 0 | 0 | 0 | 2.04 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 |  | 468 | ECOP - Top 20% | Tier 3
35236984 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1176 | FRRB - REMG - 2021 | Tier 3
35235702 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.9597 | 0 | 0 | 1.9597 | 0 | 0 | 1.9597 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - UG - 2021 | Tier 3
35226622 |  | Base SH | 08W | ADER | Estimating | 0 | 0.76004 | 0 | 0.76004 | 0 | 0 | 0.76004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35226623 |  | Base SH | 08W | APPR | Estimating | 0 | 1.15 | 0 | 1.15 | 0 | 0 | 1.15 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35226624 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.74678 | 0 | 0.74678 | 0 | 0 | 0.74678 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35236437 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.37841 | 0 | 0.37841 | 0 | 0 | 0.37841 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35236438 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.5197 | 0 | 0.5197 | 0 | 0 | 0.5197 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35192281 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.27008 | 0 | 0.27008 | 0 | 0 | 0.27008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 |  | 468 | ECOP - Top 20% | Tier 3
35220895 |  | Base SH | 08W | ESTS | Estimating | 1.9299 | 0 | 0 | 1.9299 | 0 | 0 | 0 | 1.9299 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 |  | 14 | Top 50 Miles | Tier 2 & 3
35174501 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8598 | 0 | 0 | 1.8598 | 0 | 0 | 1.8598 | 0 | 0 | HB | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3526 | -122.5227 |  | 474 | ECOP - Top 20% | Tier 3
35174479 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 3.96 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35145001 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8409 | 0.071023 | 0 | 1.9119 | 0 | 0 | 1.9119 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa |  |  |  | 1739 | PSPS - Community Resiliency | Tier 2 & 3
35224713 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.8299 | 0 | 0 | 1.8299 | 0 | 0 | 1.8299 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  |  | 11 | Top 50 Miles | Tier 2 & 3
35227167 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35223026 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6152 | -122.4293 |  | 279 | ECOP - Top 20% | Tier 3
35192292 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.7848 | 0.19489 | 0 | 1.9797 | 0 | 0 | 1.9797 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.5527 | -122.7132 |  | 637 | ECOP - Top 20% | Tier 3
35226849 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.7799 | 0 | 0 | 1.7799 | 0 | 0 | 1.7799 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35224712 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.7299 | 0 | 0 | 1.7299 | 0 | 0 | 1.7299 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  |  | 11 | Top 50 Miles | Tier 2 & 3
35235705 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.7104 | 0 | 0 | 1.7104 | 0 | 1.7104 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1849 | FRRB - UG - 2021 | Tier 3
35226858 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37992 | 0 | 0.37992 | 0 | 0 | 0 | 0.37992 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226859 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.87992 | 0 | 0.87992 | 0 | 0 | 0 | 0.87992 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226861 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0.66004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226862 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.57992 | 0 | 0.57992 | 0 | 0 | 0.57992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226863 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.52765 | 0 | 0.52765 | 0 | 0 | 0.52765 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226864 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.32652 | 0 | 0.32652 | 0 | 0 | 0.32652 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226865 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.23542 | 0 | 0.23542 | 0 | 0 | 0.23542 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226866 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.51818 | 0 | 0.51818 | 0 | 0 | 0.51818 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226870 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.41951 | 0 | 0.41951 | 0 | 0 | 0.41951 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226871 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.39659 | 0 | 0.39659 | 0 | 0.39659 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226872 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.22121 | 0 | 0.22121 | 0 | 0 | 0.22121 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35219096 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.6701 | 0 | 0 | 1.6701 | 0 | 0 | 0 | 1.6701 | 0 | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA | 37.9907 | -121.896 |  | 21 | Top 250 Miles | Tier 2
35227656 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.66 | 0 | 0 | 1.66 | 0 | 0 | 1.66 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35239095 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35223615 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5928 | 0 | 0 | 1.5928 | 0 | 0 | 1.5928 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | MARIN | 38.0443 | -122.6155 |  | 215 | ECOP - Top 20% | Tier 3
35227168 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35062375 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.5646 | 0 | 0 | 1.5646 | 0 | 0 | 1.5646 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado |  |  |  | 227 | Top 20% MAVF CPZ | Tier 3
35227031 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 1.55 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35227010 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.15795 | 0 | 0.15795 | 0 | 0 | 0 | 0.15795 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35227013 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.031818 | 0 | 0.031818 | 0 | 0 | 0 | 0.031818 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35227015 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.96705 | 0 | 0.96705 | 0 | 0 | 0 | 0.96705 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35227018 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.1955 | 0 | 1.1955 | 0 | 0 | 0 | 1.1955 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35227021 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.34186 | 0 | 0.34186 | 0 | 0 | 0.34186 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35226621 |  | Base SH | 08W | ESTS | Estimating | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 0 | 1.55 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35137590 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.39299 | 0 | 0.39299 | 0 | 0 | 0.39299 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7927 | -122.6592 |  | 86 | ECOP - Top 20% | Tier 3
35217271 |  | Base SH | 08W | ADER | Estimating | 1.54 | 0 | 0 | 1.54 | 0 | 0 | 0 | 1.54 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227161 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.73996 | 0 | 0.73996 | 0 | 0 | 0 | 0.73996 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35145524 |  | Base SH | 08W | CONS | In-Construction | 1.5216 | 0 | 0 | 1.5216 | 0 | 1.5216 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4896 | -122.6662 |  | 1755 | PSPS - Scoped | Tier 3
35227163 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0.46004 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7673 | -122.5911 |  | 8 | Top 50 Miles | Tier 2
35227164 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35226819 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.99 | 0 | 1.99 | 0 | 0 | 1.99 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35217269 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0.42992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35235139 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.5108 | 0 | 0 | 1.5108 | 0 | 1.2008 | 0.31004 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6645 | -121.4316 |  | 1288 | FRRB - UG - 2021 | Tier 3
35228186 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227870 |  | Base SH | 08W | UNSC | Ready for Construction | 1.4848 | 0 | 0 | 1.4848 | 0 | 0 | 1.4848 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35222045 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0.88996 | 0 | 0 | HB | Region 1 - North Coast | Pope Valley | Napa | 38.7569 | -122.607 |  | 14 | Top 50 Miles | Tier 2 & 3
35237896 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.4295 | 0 | 0 | 1.4295 | 0 | 0 | 1.4295 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35228187 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.57614 | 0 | 0.57614 | 0 | 0.57614 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35228188 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.45 | 0 | 3.45 | 0 | 0 | 0 | 3.45 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227860 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.19602 | 0 | 0.19602 | 0 | 0.19602 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227861 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5201 | 0 | 1.5201 | 0 | 0 | 1.5201 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227862 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227863 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35235700 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.4083 | 0 | 0 | 1.4083 | 0 | 0 | 1.4083 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1299 | FRRB - UG - 2021 | Tier 3
35227866 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.53314 | 0 | 0.53314 | 0 | 0.53314 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227867 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.98239 | 0 | 0.98239 | 0 | 0.052652 | 0.92973 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35227868 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35281758 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | NV | Region 2 - North East | Twain | PLUMAS | 40.0222 | -121.0643 |  | 1748 | FRRB | Tier 2
35227030 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3801 | 0 | 0 | 1.3801 | 0 | 0 | 1.3801 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | ECOP - Top 20% | Tier 3
35231621 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3655 | 0 | 0 | 1.3655 | 0 | 0 | 1.3655 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | Top 250 Miles | Tier 2 & 3
35236661 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.22008 | 0 | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35116383 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3919 | 0 | 1.3919 | 0 | 1.0422 | 0.34962 | 0 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.0679 | -120.1868 |  | 2267 | Pre | Tier 3
35116384 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7617 | 0 | 1.7617 | 0 | 1.7617 | 0 | 0 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.0743 | -120.1731 |  | 2267 | Pre | Tier 3
35116385 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5161 | 0 | 1.5161 | 0 | 0 | 1.5161 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  |  | 2267 | Pre | Tier 3
35052737 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.6297 | 0 | 1.6297 | 0 | 0 | 1.6297 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne |  |  |  | 2267 | Pre | Tier 3
35052821 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.0911 | 0 | 2.0911 | 0 | 2.0911 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0571 | -120.2065 |  | 2353 | Pre | Tier 3
35056746 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.0278 | 0 | 2.0278 | 0 | 1.6869 | 0.34091 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE | 38.0885 | -120.1927 |  | 2353 | Pre | Tier 3
35115050 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.6241 | 0 | 1.6241 | 0 | 1.6241 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0571 | -120.2065 |  | 2353 | Pre | Tier 3
35115053 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.7411 | 0 | 1.7411 | 0 | 1.7411 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE | 38.0594 | -120.2227 |  | 2353 | Pre | Tier 3
35115054 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3953 | 0 | 1.3953 | 0 | 1.3953 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE | 38.0614 | -120.1982 |  | 2353 | Pre | Tier 3
35115055 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.1343 | 0 | 2.1343 | 0 | 2.1343 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE | 38.0615 | -120.1971 |  | 2353 | Pre | Tier 2
35116442 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.3314 | 0 | 2.3314 | 1.7888 | 0.54261 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0486 | -120.2438 |  | 2678 | Pre | Tier 3
35116444 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.065 | 0 | 2.065 | 0 | 0.38883 | 1.6761 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0486 | -120.2438 |  | 2678 | Pre | Tier 3
35116800 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3864 | 0 | 1.3864 | 0.73996 | 0.6464 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 |  | 2411 | Pre | Tier 3
35225823 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.3602 | 0 | 0 | 1.3602 | 0 | 1.3602 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35116802 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2237 | 0 | 2.2237 | 2.2167 | 0.0070076 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 |  | 2411 | Pre | Tier 3
35116391 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 2.0902 | 0 | 2.0902 | 1.3841 | 0.70606 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0494 | -120.261 |  | 2369 | Pre | Tier 3
35116395 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.703 | 0 | 1.703 | 0 | 1.703 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0596 | -120.2138 |  | 2369 | Pre | Tier 3
35052825 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0917 | 0 | 1.0917 | 0 | 1.0917 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0489 | -120.2345 |  | 2737 | Pre | Tier 3
35232650 |  | Base SH | 08W | UNSC | Ready for Construction | 1.3447 | 0 | 0 | 1.3447 | 0 | 0 | 1.3447 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8982 | -120.9827 |  | 45 | Top 250 Miles | Tier 2
35254070 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8931 | -120.9966 |  | 169 | CWSP 2022-2023 | Tier 2
35254071 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.65 | 0 | 2.65 | 0 | 0 | 0 | 2.65 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8932 | -120.9965 |  | 169 | CWSP 2022-2023 | Tier 2
35305303 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8972 | -120.989 |  | 169 | CWSP 2022-2023 | Tier 2
35305304 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8978 | -120.9866 |  | 169 | CWSP 2022-2023 | Tier 2
35305305 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8981 | -120.9738 |  | 169 | CWSP 2022-2023 | Tier 2
35305306 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8977 | -120.972 |  | 169 | CWSP 2022-2023 | Tier 2
35305307 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8962 | -120.9648 |  | 169 | CWSP 2022-2023 | Tier 2
35305308 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8944 | -120.9647 |  | 169 | CWSP 2022-2023 | Tier 2
35305309 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8962 | -120.9633 |  | 169 | CWSP 2022-2023 | Tier 2
35305310 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.899 | -120.9485 |  | 169 | CWSP 2022-2023 | Tier 2
35305311 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8965 | -120.9455 |  | 169 | CWSP 2022-2023 | Tier 2
35305312 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.98902 | 0 | 0.98902 | 0 | 0 | 0 | 0.98902 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8977 | -120.9674 |  | 169 | CWSP 2022-2023 | Tier 2
35234526 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3426 | 0 | 0 | 1.3426 | 0 | 0 | 1.3426 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR | 38.3949 | -120.804 |  | 999 | PSPS - Community Resiliency | Tier 2
35192280 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.34 | 0 | 0 | 1.34 | 0 | 0 | 1.34 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 |  | 377 | ECOP - Top 20% | Tier 3
35293664 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8981 | -120.914 |  | 169 | CWSP 2022-2023 | Tier 2
35227160 |  | Base SH | 08W | ESTS | Estimating | 1.3201 | 0 | 0 | 1.3201 | 0 | 0 | 0 | 1.3201 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35293666 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.22992 | 0 | 0.22992 | 0 | 0 | 0 | 0.22992 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.9012 | -120.9346 |  | 169 | CWSP 2022-2023 | Tier 2
35293667 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.65 | 0 | 1.65 | 0 | 0 | 0 | 1.65 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8974 | -120.9338 |  | 169 | CWSP 2022-2023 | Tier 2
35293668 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 1.44 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8894 | -120.9589 |  | 169 | CWSP 2022-2023 | Tier 2
35293669 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.6299 | 0 | 1.6299 | 0 | 0 | 0 | 1.6299 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8852 | -120.96 |  | 169 | CWSP 2022-2023 | Tier 2
35293670 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8805 | -120.9418 |  | 169 | CWSP 2022-2023 | Tier 2
35231543 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA | 37.9632 | -121.9407 |  | 18 | Top 50 Miles | Tier 2
35145525 |  | Base SH | 08W | CONS | In-Construction | 1.283 | 0.2 | 0 | 1.483 | 0 | 1.1737 | 0.30928 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.489 | -122.666 |  | 3302 | PSPS - Scoped | Tier 2
35232651 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7445 | 0 | 1.7445 | 0 | 1.7445 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8982 | -120.9827 |  | 45 | Top 250 Miles | Tier 2
35191319 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.2816 | 0 | 0 | 1.2816 | 0 | 0 | 1.2816 | 0 | 0 | NB | Region 1 - North Coast | Nicasio | MARIN | 38.046 | -122.646 |  | 215 | ECOP - Top 20% | Tier 3
35293672 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 1.09 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.9075 | -121.0168 |  | 68 | CWSP 2022-2023 | Tier 2
35293673 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 1.8799 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8939 | -121.0149 |  | 68 | CWSP 2022-2023 | Tier 2
35293674 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.61 | 0 | 1.61 | 0 | 0 | 0 | 1.61 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8882 | -121.0144 |  | 68 | CWSP 2022-2023 | Tier 2
35293675 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 2.11 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8795 | -121.0164 |  | 68 | CWSP 2022-2023 | Tier 2
35293676 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8745 | -121.0198 |  | 68 | CWSP 2022-2023 | Tier 2
35293677 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.72008 | 0 | 0.72008 | 0 | 0 | 0 | 0.72008 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8918 | -120.9988 |  | 68 | CWSP 2022-2023 | Tier 2
35293847 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0.33996 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8704 | -121.0217 |  | 68 | CWSP 2022-2023 | Tier 2
35293505 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.3799 | 0 | 1.3799 | 0 | 0 | 0 | 1.3799 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8782 | -120.9979 |  | 68 | CWSP 2022-2023 | Tier 2
35293506 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8803 | -121.0037 |  | 68 | CWSP 2022-2023 | Tier 2
35293507 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8774 | -120.9979 |  | 68 | CWSP 2022-2023 | Tier 2
35242421 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2674 | 0 | 0 | 1.2674 | 0 | 1.2674 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35293509 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 2.04 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8608 | -120.993 |  | 68 | CWSP 2022-2023 | Tier 2
35236991 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2616 | 0 | 0 | 1.2616 | 0 | 0 | 1.2616 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - UG - 2021 | Tier 3
35300934 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8708 | -120.9825 |  | 68 | CWSP 2022-2023 | Tier 2
35235678 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2422 | 0 | 0 | 1.2422 | 0 | 1.2422 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1288 | FRRB - UG - 2021 | Tier 3
35301113 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8632 | -120.9814 |  | 68 | CWSP 2022-2023 | Tier 2
35301114 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 1.01 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8694 | -120.979 |  | 68 | CWSP 2022-2023 | Tier 2
35237890 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35254068 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 1.81 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 |  | 68 | CWSP 2022-2023 | Tier 2
35254069 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 1.3701 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8777 | -120.9979 |  | 68 | CWSP 2022-2023 | Tier 2
35241060 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | YO | Region 5 - Central Valley | Ahwahnee | MADERA | 37.3642 | -119.7251 |  | 421 | Remote Grid Pilot | Tier 3
35223037 |  | Base SH | 08W | CONS | In-Construction | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0 | 0.0079545 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3227 | -119.6344 |  | 847 | PSPS - Community Resiliency | Tier 3
35227096 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1049 | 0 | 1.1049 | 0 | 1.1049 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | MARIPOSA | 37.4809 | -119.6371 |  | 1975 | Storm Rebuild | Tier 3
35227201 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.83523 | 0 | 0.83523 | 0 | 0.83523 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | MARIPOSA | 37.4809 | -119.6371 |  | 1975 | Storm Rebuild | Tier 3
35192053 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.143 | 0 | 2.143 | 0 | 2.143 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | Mariposa | 37.481 | -119.6374 |  | 1975 | Storm Rebuild | Tier 3
35243446 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0.37 | 0 | NB | Region 1 - North Coast | Inverness | MARIN | 38.1094 | -122.8698 |  | 2644 | REMG 2022-2023 | Tier 2
35243445 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 1.92 | 0 | NB | Region 1 - North Coast | Inverness | MARIN | 38.1094 | -122.8698 |  | 2360 | REMG 2022-2023 | Tier 2
35219591 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.332 | 0.0077652 | 1.3398 | 0 | 0 | 0 | 1.3398 | 0 | ST | Region 5 - Central Valley | Plymouth | AMADOR | 38.4692 | -120.8536 |  | 54 | Top 250 Miles | Tier 2
35236662 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6246 | 0 | 1.6246 | 0 | 1.6246 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | AMADOR | 38.4692 | -120.8536 |  | 54 | Top 250 Miles | Tier 2
35233947 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.8436 | 0 | 1.8436 | 0 | 0 | 1.8436 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35254643 |  | Base SH | 08W | ESTS | Estimating | 1.21 | 0 | 1.0979 | 2.308 | 0 | 0 | 0 | 2.308 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35233949 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.9769 | 0 | 1.9769 | 0 | 0 | 1.9769 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35293665 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.2087 | 0 | 0 | 1.2087 | 0 | 0 | 0 | 1.2087 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8973 | -120.9098 |  | 169 | CWSP 2022-2023 | Tier 2
35233951 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5648 | 0 | 1.5648 | 0 | 0 | 1.5648 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35233952 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.1616 | 0 | 2.1616 | 0 | 0 | 2.1616 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234383 |  | Base SH | 08W | ESTS | Estimating | 1.1985 | 0 | 0 | 1.1985 | 0 | 0 | 1.1985 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35233954 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.19451 | 0 | 0.19451 | 0 | 0 | 0.19451 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35237894 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.185 | 0 | 0 | 1.185 | 0 | 0 | 1.185 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35233956 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.26098 | 0 | 0.26098 | 0 | 0 | 0.26098 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35295186 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.1701 | 0 | 0 | 1.1701 | 0 | 0 | 1.1701 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35233958 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.18845 | 0 | 0.18845 | 0 | 0 | 0.18845 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35233959 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.34602 | 0 | 0.34602 | 0 | 0 | 0.34602 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234380 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.2419 | 0 | 2.2419 | 0 | 0 | 2.2419 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234381 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5468 | 0 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234382 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.5875 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35284023 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4361 | -122.5779 |  | 1684 | FRRB - UG - 2021 | Tier 3
35234384 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0.050568 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234385 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.67443 | 0 | 0.67443 | 0 | 0 | 0.67443 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234386 |  | Base SH | 08W | ADER | Estimating | 0 | 0.85777 | 0 | 0.85777 | 0 | 0 | 0.85777 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234387 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.93996 | 0 | 0.93996 | 0 | 0 | 0.93996 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234388 |  | Base SH | 08W | ADER | Estimating | 0 | 2.0402 | 0 | 2.0402 | 0 | 0 | 2.0402 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234389 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234390 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234391 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 1.26 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234392 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.66 | 0 | 1.66 | 0 | 0 | 1.66 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234393 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.4201 | 0 | 2.4201 | 0 | 0 | 2.4201 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234394 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234395 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.71 | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234396 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 1.69 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234397 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.72008 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234398 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.8525 | 0 | 2.8525 | 0 | 0 | 2.8525 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35239097 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.1566 | 0 | 0 | 1.1566 | 0 | 0 | 1.1566 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35234400 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35234401 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 1.85 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35225826 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5424 | 0 | 2.5424 | 0 | 0 | 2.5424 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35219093 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.14 | 0 | 0 | 1.14 | 0 | 0 | 1.14 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA | 37.9632 | -121.9407 |  | 18 | Top 50 Miles | Tier 2
35236439 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35225829 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.19 | 0 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35219287 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.3962 | 0 | 2.3962 | 0 | 0 | 2.3962 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6299 | -122.2445 |  | 49 | Top 250 Miles | Tier 2
35297984 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6951 | -122.3174 |  | 851 | FRRB | Tier 2
35292788 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 2342 | FRRB | Tier 2
35254254 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.46 | 0 | 1.46 | 0 | 0 | 0 | 1.46 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6844 | -120.7299 |  | 260 | CWSP 2022-2023 | Tier 2
35279626 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0.17 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6844 | -120.73 |  | 260 | CWSP 2022-2023 | Tier 2
35279630 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 1.69 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6401 | -120.7318 |  | 615 | CWSP 2022-2023 | Tier 2
35254251 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.13 | 0 | 1.13 | 0 | 0 | 1.13 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6415 | -120.7259 |  | 615 | CWSP 2022-2023 | Tier 2
35260649 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.62992 | 0 | 0.62992 | 0 | 0 | 0 | 0.62992 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.7334 | -120.8792 |  | 510 | CWSP 2022-2023 | Tier 2
35254253 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.714 | -120.8385 |  | 138 | CWSP 2022-2023 | Tier 2
35279627 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 1.47 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.7253 | -120.8701 |  | 138 | CWSP 2022-2023 | Tier 2
35279628 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 2.37 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.706 | -120.8189 |  | 291 | CWSP 2022-2023 | Tier 2
35279629 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 1.71 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.7141 | -120.8386 |  | 291 | CWSP 2022-2023 | Tier 2
35254252 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.49 | 0.064962 | 2.5549 | 0 | 0 | 2.5549 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6886 | -120.7649 |  | 291 | CWSP 2022-2023 | Tier 2
35254249 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 2.7 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6543 | -120.7258 |  | 69 | CWSP 2022-2023 | Tier 2
35254250 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.11 | 0 | 1.11 | 0 | 0 | 0 | 1.11 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6543 | -120.7258 |  | 69 | CWSP 2022-2023 | Tier 2
35278880 |  | Base SH | 08W | ADER | Estimating | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 2.09 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6698 | -120.7266 |  | 69 | CWSP 2022-2023 | Tier 2
35278881 |  | Base SH | 08W | ADER | Estimating | 0 | 2.6799 | 0 | 2.6799 | 0 | 0 | 0 | 2.6799 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6635 | -120.7259 |  | 69 | CWSP 2022-2023 | Tier 2
35278882 |  | Base SH | 08W | ADER | Estimating | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 2.01 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6747 | -120.7423 |  | 69 | CWSP 2022-2023 | Tier 2
35278883 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6795 | -120.745 |  | 69 | CWSP 2022-2023 | Tier 2
35278884 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 2.77 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6807 | -120.7554 |  | 69 | CWSP 2022-2023 | Tier 2
35278885 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 1.47 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6819 | -120.7391 |  | 69 | CWSP 2022-2023 | Tier 2
35278886 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6892 | -120.7391 |  | 69 | CWSP 2022-2023 | Tier 2
35278887 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 1.48 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6819 | -120.738 |  | 69 | CWSP 2022-2023 | Tier 2
35278888 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 1.39 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6847 | -120.73 |  | 69 | CWSP 2022-2023 | Tier 2
35254248 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.43 | 0 | 1.43 | 0 | 0 | 1.43 | 0 | 0 | LP | Region 4 - Central Coast | El Paso de Robles | SAN LUIS OBISPO | 35.6286 | -120.6955 |  | 257 | CWSP 2022-2023 | Tier 2
35279631 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 3.07 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6385 | -120.7157 |  | 257 | CWSP 2022-2023 | Tier 2
35243442 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 2.319 | SI | Region 2 - North East | North San Juan | SIERRA | 39.4385 | -120.9959 |  | 1308 | REMG 2022-2023 | Tier 3
35295019 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6425 | -120.5224 |  | 2252 | FRRB | Tier 2 & 3
35114042 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3352 | 0 | 1.3352 | 1.172 | 0.16326 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4356 | -120.5538 |  | 2271 | Pre | Tier 3
35114044 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.0966 | 0 | 1.0966 | 0.081061 | 1.0155 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4428 | -120.5433 |  | 2271 | Pre | Tier 3
35114048 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.3909 | 0 | 1.3909 | 0 | 1.3909 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.436 | -120.5559 |  | 2271 | Pre | Tier 3
35114049 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.5705 | 0 | 1.5705 | 0.70663 | 0.86383 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.436 | -120.5559 |  | 2271 | Pre | Tier 3
35114051 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4371 | 0 | 1.4371 | 0 | 1.4371 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4485 | -120.5393 |  | 2271 | Pre | Tier 3
35295009 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1166 | -120.967 |  | 1885 | FRRB
35233166 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0491 | 0 | 0 | 1.0491 | 0 | 0 | 1.0491 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35233308 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 1.047 | 0 | 0 | 1.047 | 0 | 1.047 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6333 | -121.4164 |  | 1849 | FRRB - UG - 2021 | Tier 3
35174478 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.04 | 0 | 0 | 1.04 | 0 | 0 | 0 | 1.04 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35226873 |  | Base SH | 08W | ESTS | Estimating | 1.0394 | 0 | 0 | 1.0394 | 0 | 0 | 0 | 1.0394 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35235707 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0284 | 0 | 0 | 1.0284 | 0 | 0 | 1.0284 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1849 | FRRB - REMG - 2021 | Tier 3
35225821 |  | Fire Rebuild | 08W | CONS | In-Construction | 1.0252 | 0 | 0 | 1.0252 | 0 | 1.0252 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35297699 |  | Fire Rebuild | 08W | ESTS | Estimating | 1.0199 | 0 | 0 | 1.0199 | 0 | 0 | 1.0199 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35250579 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 6.14 | 0 | 6.14 | 0 | 0 | 0 | 6.14 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3618 | -123.1272 |  | 60 | CWSP 2022-2023 | Tier 2 & 3
35254073 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 1.01 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3218 | -123.0951 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35254074 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.35 | 0 | 0.35 | 0 | 0 | 0 | 0.35 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3218 | -123.0951 |  | 75 | CWSP 2022-2023 | Tier 2
35254075 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 1.8 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3218 | -123.0951 |  | 75 | CWSP 2022-2023 | Tier 2
35254076 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0.92992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3218 | -123.0951 |  | 75 | CWSP 2022-2023 | Tier 2
35293770 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.52992 | 0 | 0.52992 | 0 | 0 | 0 | 0.52992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3146 | -123.0942 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293774 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 1.1799 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3095 | -123.0931 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293775 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.39015 | 0 | 0.39015 | 0 | 0 | 0 | 0.39015 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3018 | -123.0942 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293841 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2927 | -123.085 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293843 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.31 | 0 | 1.31 | 0 | 0 | 0 | 1.31 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2953 | -123.0616 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293844 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0.92992 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2984 | -123.0591 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35293845 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 1.4201 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3031 | -123.057 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35227165 |  | Base SH | 08W | PEND | Permitting/Dependency | 1.01 | 0 | 0 | 1.01 | 0 | 0 | 1.01 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35290807 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2259 | 0 | 1.2259 | 0 | 0 | 0 | 1.2259 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2457 | -123.1271 |  | 75 | CWSP 2022-2023 | Tier 2
35279120 |  | Base SH | 08W | UNSE | Scoping/Scoped | 1.004 | 0 | 0 | 1.004 | 0 | 0 | 0 | 1.004 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 |  | 56 | CWSP 2022-2023 | Tier 2 & 3
35290295 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.197 | 0 | 1.197 | 0 | 0 | 0 | 1.197 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2738 | -123.0944 |  | 75 | CWSP 2022-2023 | Tier 2
35290296 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.93807 | 0 | 0.93807 | 0 | 0 | 0 | 0.93807 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2715 | -123.097 |  | 75 | CWSP 2022-2023 | Tier 2
35290297 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0451 | 0 | 1.0451 | 0 | 0 | 0 | 1.0451 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2696 | -123.1053 |  | 75 | CWSP 2022-2023 | Tier 2
35290298 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 1.2799 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2619 | -123.1148 |  | 75 | CWSP 2022-2023 | Tier 2
35290299 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.4189 | 0 | 1.4189 | 0 | 0 | 0 | 1.4189 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2594 | -123.1172 |  | 75 | CWSP 2022-2023 | Tier 2
35290500 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0229 | 0 | 1.0229 | 0 | 0 | 0 | 1.0229 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2537 | -123.1188 |  | 75 | CWSP 2022-2023 | Tier 2
35290501 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.64 | 0 | 1.64 | 0 | 0 | 0 | 1.64 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2328 | -123.1053 |  | 75 | CWSP 2022-2023 | Tier 2
35290502 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 1.6299 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.228 | -123.0887 |  | 75 | CWSP 2022-2023 | Tier 2
35290503 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2248 | -123.0882 |  | 75 | CWSP 2022-2023 | Tier 2
35228774 |  | Base SH | 08W | ESTS | Estimating | 1.0008 | 0 | 0 | 1.0008 | 0 | 0 | 0 | 1.0008 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | PSPS - Community Resiliency | Tier 2
35290506 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 2.09 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2105 | -123.0641 |  | 75 | CWSP 2022-2023 | Tier 2
35290507 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77992 | 0 | 0.77992 | 0 | 0 | 0 | 0.77992 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1963 | -123.0435 |  | 75 | CWSP 2022-2023 | Tier 2
35297693 |  | Fire Rebuild | 08W | ESTS | Estimating | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35290509 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 1.09 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1918 | -123.0344 |  | 75 | CWSP 2022-2023 | Tier 2
35290510 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0.6 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1887 | -123.0323 |  | 75 | CWSP 2022-2023 | Tier 2
35293663 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.98996 | 0 | 0 | 0.98996 | 0 | 0 | 0 | 0.98996 | 0 | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8964 | -120.922 |  | 169 | CWSP 2022-2023 | Tier 2
35290544 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35285245 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.40398 | 0 | 0.40398 | 0 | 0 | 0 | 0.40398 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3022 | -123.1091 |  | 396 | CWSP 2022-2023 | Tier 2
35254077 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.6021 | 0 | 1.6021 | 0 | 0 | 0 | 1.6021 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3171 | -123.1131 |  | 396 | CWSP 2022-2023 | Tier 2
35219280 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5871 | 0 | 1.5871 | 0 | 0 | 1.5871 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.362 | -123.1283 |  | 43 | Top 250 Miles | Tier 2
35239096 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35191937 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4542 | 0 | 1.4542 | 0 | 1.4542 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA | 38.4109 | -122.4506 |  | 951 | ECOP | Tier 3
35227032 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 0.87121 | 0 | 0.87121 | 0 | 0.56269 | 0.30852 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA | 38.433 | -122.4021 |  | 951 | ECOP | Tier 3
35227033 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3299 | 2.3299 | 0 | 0 | 0 | 0 | 2.3299 | NB | Region 1 - North Coast | Napa | NAPA | 38.433 | -122.4021 |  | 951 | ECOP | Tier 3
35219275 |  | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0231 | 0 | 1.0231 | 0 | 0 | 1.0231 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.4831 | -122.0253 |  | 41 | Top 250 Miles | Tier 2
35240176 |  | Base SH | 08W | ADER | Estimating | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.4946 | -122.034 |  | 529 | CWSP 2022-2023 | Tier 2
35240177 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 3.3 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.4946 | -122.034 |  | 529 | CWSP 2022-2023 | Tier 2
35254177 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.31 | 0 | 0.31 | 0 | 0 | 0.31 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.4946 | -122.034 |  | 529 | CWSP 2022-2023 | Tier 2
35254178 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.253 | 0 | 1.253 | 0 | 0 | 1.253 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35240175 |  | Base SH | 08W | ESTS | Estimating | 0 | 3.446 | 0 | 3.446 | 0 | 0 | 3.446 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35254560 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 1.211 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35223343 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.95473 | 0.0094697 | 0 | 0.9642 | 0 | 0.9642 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35254261 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.802 | 0 | 2.802 | 0 | 0 | 2.802 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35254262 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.104 | 0 | 2.104 | 0 | 0 | 2.104 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35254263 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.225 | 0 | 1.225 | 0 | 0 | 1.225 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5142 | -122.0002 |  | 418 | CWSP 2022-2023 | Tier 2
35240178 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.4229 | 0 | 3.4229 | 0 | 0 | 3.4229 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5142 | -122.0002 |  | 418 | CWSP 2022-2023 | Tier 2
35254264 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.33 | 0 | 1.33 | 0 | 0 | 1.33 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5035 | -122.002 |  | 171 | CWSP 2022-2023 | Tier 2
35254265 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 2.76 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5035 | -122.002 |  | 171 | CWSP 2022-2023 | Tier 2
35254266 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.13 | 0 | 0.13 | 0 | 0 | 0.13 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5035 | -122.002 |  | 171 | CWSP 2022-2023 | Tier 2
35240173 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.2201 | 0 | 1.2201 | 0 | 0 | 1.2201 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5035 | -122.002 |  | 171 | CWSP 2022-2023 | Tier 2
35240174 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.07 | 0 | 1.07 | 0 | 0 | 1.07 | 0 | 0 | SA | Region 2 - North East | Winters | YOLO | 38.5035 | -122.002 |  | 171 | CWSP 2022-2023 | Tier 2
35297694 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35295195 |  | Fire Rebuild | 08W | ADER | Estimating | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6397 | -120.5229 |  | 2252 | FRRB | Tier 2 & 3
35228449 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.829 | 0 | 2.829 | 0 | 2.829 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT | 40.3679 | -124.0594 |  | 585 | Storm Rebuild | Tier 2
35015704 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0038 | 0 | 1.0038 | 0 | 0 | 0 | 1.0038 | 0 | CC | Region 4 - Central Coast | Aptos | SANTA CRUZ | 36.9718 | -121.8758 |  | 3283 | Pre | Tier 3
35085847 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.84659 | 0 | 0.84659 | 0 | 0 | 0 | 0.84659 | 0 | CC | Region 4 - Central Coast | Aptos | SANTA CRUZ | 36.9747 | -121.8839 |  | 3283 | Pre | Tier 3
35228775 |  | Base SH | 08W | ESTS | Estimating | 0.90341 | 0 | 0 | 0.90341 | 0 | 0 | 0 | 0.90341 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | PSPS - Community Resiliency | Tier 2
35115855 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.2456 | 0 | 1.2456 | 1.0847 | 0.16098 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.3017 | -120.2771 |  | 2659 | Pre | Tier 3
35264191 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 2.35 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6323 | -120.1426 |  | 308 | CWSP 2022-2023 | Tier 2
35264192 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6338 | -120.1419 |  | 308 | CWSP 2022-2023 | Tier 2
35264193 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.08 | 0 | 2.08 | 0 | 0 | 2.08 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6509 | -120.1422 |  | 308 | CWSP 2022-2023 | Tier 2
35264194 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.647 | -120.1323 |  | 308 | CWSP 2022-2023 | Tier 2
35271002 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.22 | 0 | 1.22 | 0 | 0 | 1.22 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.66 | -120.1339 |  | 308 | CWSP 2022-2023 | Tier 2
35240224 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.8701 | 0 | 1.8701 | 0 | 0 | 1.8701 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6323 | -120.1187 |  | 308 | CWSP 2022-2023 | Tier 2
35240179 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.25 | 0 | 0.25 | 0 | 0 | 0.25 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6254 | -120.1189 |  | 137 | CWSP 2022-2023 | Tier 2
35240220 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.786 | 0 | 2.786 | 0 | 0 | 2.786 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6354 | -120.0656 |  | 108 | CWSP 2022-2023 | Tier 2
35240221 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.93 | 0 | 2.93 | 0 | 0 | 2.93 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6354 | -120.0656 |  | 108 | CWSP 2022-2023 | Tier 2
35264181 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.5568 | 0 | 2.5568 | 0 | 0 | 2.5568 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6365 | -120.0218 |  | 108 | CWSP 2022-2023 | Tier 2
35264182 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.3167 | 0 | 2.3167 | 0 | 0 | 2.3167 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6278 | -120.0209 |  | 108 | CWSP 2022-2023 | Tier 2
35264183 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.44 | 0 | 2.44 | 0 | 0 | 2.44 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6273 | -120.0209 |  | 108 | CWSP 2022-2023 | Tier 2
35264184 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.5985 | -120.0297 |  | 108 | CWSP 2022-2023 | Tier 2
35264185 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.52 | 0.18 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6142 | -119.9878 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35264186 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.43 | 0.43 | 0 | 0 | 0 | 0 | 0.43 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6119 | -119.9908 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35264187 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.07 | 0 | 2.07 | 0 | 0 | 0 | 2.07 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6112 | -119.9786 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35264188 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 1.14 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6065 | -119.9509 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35264189 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 2.66 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6377 | -119.9713 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35264190 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 2.37 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6451 | -119.9634 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35240222 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 2.11 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6111 | -120.0203 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35240223 |  | Base SH | 08W | ESTS | Estimating | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 2.61 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6111 | -120.0203 |  | 153 | CWSP 2022-2023 | Tier 2 & 3
35242423 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.88958 | 0 | 0 | 0.88958 | 0 | 0 | 0.88958 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35226852 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3718 | 0 | 2.3718 | 0 | 0 | 0 | 2.3718 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 159 | Top 20% MAVF CPZ | Tier 3
35226853 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.9174 | 0 | 1.9174 | 0 | 0 | 1.9174 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 159 | Top 20% MAVF CPZ | Tier 3
35226854 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.0076 | 0.36364 | 2.3712 | 0 | 0 | 2.3712 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 159 | Top 20% MAVF CPZ | Tier 3
35226856 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.0938 | 0 | 1.0938 | 0 | 0 | 1.0938 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 159 | Top 20% MAVF CPZ | Tier 3
35226846 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4795 | 0 | 1.4795 | 0 | 0 | 1.4795 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35226847 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.2939 | 0.22462 | 1.5186 | 0 | 0 | 1.5186 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35226848 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.8341 | 0 | 2.8341 | 0 | 0 | 2.8341 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35242427 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.87784 | 0 | 0 | 0.87784 | 0 | 0 | 0.87784 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35226850 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4674 | 0 | 1.4674 | 0 | 0.18542 | 1.282 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35226851 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.1157 | 0 | 2.1157 | 0 | 0 | 2.1157 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35231607 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.4093 | 0 | 1.4093 | 0 | 0 | 1.4093 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35231608 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0.37121 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35231609 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.7477 | 0.15758 | 1.9053 | 0 | 0 | 1.9053 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35232280 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.61269 | 0 | 0.61269 | 0 | 0.61269 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7138 | -120.9394 |  | 227 | Top 20% MAVF CPZ | Tier 3
35270706 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.87102 | 0.10417 | 0 | 0.97519 | 0 | 0.97519 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.872 | -122.3592 |  | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35290517 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.86989 | 0 | 0 | 0.86989 | 0 | 0 | 0.86989 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS | 40.0553 | -120.9636 |  | 1322 | FRRB | Tier 2
35191383 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 1.3337 | 0 | 1.3337 | 0 | 1.3337 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5057 | -122.401 |  | 663 | ECOP - Top 20% | Tier 3
35191318 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.2201 | 0 | 2.2201 | 0 | 0 | 2.2201 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5095 | -122.386 |  | 663 | ECOP - Top 20% | Tier 3
35220936 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo |  |  |  | 2186 | FRRB - UG - 2021 | Tier 2
35293846 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.85985 | 0 | 0 | 0.85985 | 0 | 0 | 0 | 0.85985 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3008 | -123.0524 |  | 75 | CWSP 2022-2023 | Tier 2 & 3
35284810 |  | Fire Rebuild | 08W | ADER | Estimating | 0.85814 | 0 | 0 | 0.85814 | 0 | 0 | 0 | 0.85814 | 0 | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.2086 | -122.3251 |  | 2186 | FRRB
35223027 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6559 | 0 | 1.6559 | 0 | 0.35909 | 1.2968 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6152 | -122.4293 |  | 279 | ECOP - Top 20% | Tier 3
35223028 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1784 | 0 | 1.1784 | 0 | 1.1784 | 0 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6152 | -122.4293 |  | 279 | ECOP - Top 20% | Tier 3
35238098 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.47936 | 0 | 0.47936 | 0 | 0 | 0 | 0.47936 | 0 | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6152 | -122.4293 |  | 279 | ECOP - Top 20% | Tier 3
35226628 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.85511 | 0 | 0 | 0.85511 | 0 | 0 | 0.85511 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35242422 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.85398 | 0 | 0 | 0.85398 | 0 | 0 | 0.85398 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35283343 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0 | 0.85303 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1488 | -122.9992 |  | 335 | CWSP 2022-2023 | Tier 2
35279121 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77235 | 0 | 0.77235 | 0 | 0 | 0 | 0.77235 | 0 | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1797 | -120.3786 |  | 56 | CWSP 2022-2023 | Tier 2 & 3
35279122 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.90909 | 0 | 0.90909 | 0 | 0 | 0 | 0.90909 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.1379 | -120.3707 |  | 56 | CWSP 2022-2023 | Tier 2 & 3
35250578 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4174 | 0 | 2.4174 | 0 | 0 | 0 | 2.4174 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.1376 | -120.3702 |  | 56 | CWSP 2022-2023 | Tier 2 & 3
35236990 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - REMG - 2021 | Tier 3
35250577 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.3513 | 0 | 3.3513 | 0 | 0 | 0 | 3.3513 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.1377 | -120.3701 |  | 235 | CWSP 2022-2023 | Tier 2 & 3
35226857 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35254259 |  | Base SH | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35284366 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0.60871 | 0 | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | 38.1446 | -120.3574 |  | 235 | CWSP 2022-2023 | Tier 2 & 3
35280499 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | FRRB - UG - 2021 | Tier 2 & 3
35233996 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.84962 | 0 | 0.52121 | 1.3708 | 0 | 0 | 1.3708 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  |  | 1363 | PSPS - Community Resiliency | Tier 3
35231544 |  | Base SH | 08W | FICL | Post-Construction | 0 | 1.1009 | 0 | 1.1009 | 0 | 1.1009 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | CONTRA COSTA | 37.9632 | -121.9407 |  | 18 | Top 50 Miles | Tier 2
35243443 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 11.215 | FR | Region 5 - Central Valley | Sanger | FRESNO | 36.8168 | -119.3408 |  | 491 | REMG 2022-2023 | Tier 2
35256082 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 0 | 1.211 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1582 | -122.9898 |  | 335 | CWSP 2022-2023 | Tier 2
35223032 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.84924 | 0 | 0 | 0.84924 | 0 | 0 | 0.47045 | 0.37879 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8855 | -121.0156 |  | 68 | PSPS - Community Resiliency | Tier 2
35283341 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.07803 | 0 | 0.07803 | 0 | 0 | 0 | 0.07803 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.157 | -122.9917 |  | 335 | CWSP 2022-2023 | Tier 2
35225827 |  | Base SH | 08W | ESTS | Estimating | 0.84564 | 0 | 0 | 0.84564 | 0 | 0 | 0.84564 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35283344 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.6561 | 0 | 1.6561 | 0 | 0 | 0 | 1.6561 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1474 | -122.9995 |  | 335 | CWSP 2022-2023 | Tier 2
35233953 |  | Base SH | 08W | ESTS | Estimating | 0.84034 | 0 | 0 | 0.84034 | 0 | 0 | 0.84034 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35283347 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.478 | 0 | 1.478 | 0 | 0 | 0 | 1.478 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1253 | -122.9948 |  | 335 | CWSP 2022-2023 | Tier 2
35283348 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.075 | 0 | 1.075 | 0 | 0 | 0 | 1.075 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1213 | -122.9896 |  | 335 | CWSP 2022-2023 | Tier 2
35283349 |  | Base SH | 08W | ESTS | Estimating | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 1.0549 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.113 | -122.9818 |  | 335 | CWSP 2022-2023 | Tier 2
35285247 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.48106 | 0 | 0.48106 | 0 | 0 | 0 | 0.48106 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1668 | -123.0058 |  | 335 | CWSP 2022-2023 | Tier 2
35285248 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.461 | 0 | 1.461 | 0 | 0 | 0 | 1.461 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1679 | -123.0053 |  | 335 | CWSP 2022-2023 | Tier 2
35280496 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 895 | FRRB | Tier 2
35285250 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.51705 | 0 | 0.51705 | 0 | 0 | 0 | 0.51705 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1756 | -123.0186 |  | 335 | CWSP 2022-2023 | Tier 2
35233315 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.80436 | 0 | 0 | 0.80436 | 0 | 0 | 0.80436 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6234 | -121.4009 |  | 1849 | FRRB - UG - 2021 | Tier 3
35217273 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.0799 | 0 | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.353 | -122.7722 |  | 6 | Top 50 Miles | Tier 2
35219291 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.35814 | 0 | 0.35814 | 0 | 0 | 0.35814 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3973 | -121.9855 |  | 20 | Top 250 Miles | Tier 2
35219269 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 2.14 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237258 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.15 | 0 | 2.15 | 0 | 0 | 2.15 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237259 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.5744 | 0 | 3.5744 | 0 | 0 | 3.5744 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237360 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 3.01 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237361 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3383 | 0 | 2.3383 | 0 | 0 | 2.3383 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237364 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.8307 | 0 | 2.8307 | 0 | 0 | 2.8307 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237365 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.5699 | 0 | 2.5699 | 0 | 0 | 2.5699 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237366 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237368 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 4.19 | 0 | 4.19 | 0 | 0 | 4.19 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237369 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.14 | 0 | 3.14 | 0 | 0 | 3.14 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237370 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.7799 | 0 | 3.7799 | 0 | 0 | 3.7799 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35237371 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0.33996 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4159 | -121.9706 |  | 37 | Top 250 Miles | Tier 2
35219590 |  | Base SH | 08W | CONS | In-Construction | 0 | 1.6167 | 0 | 1.6167 | 0 | 0 | 1.6167 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.4341 | -121.9915 |  | 53 | Top 250 Miles | Tier 2
35270705 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.79394 | 0 | 0 | 0.79394 | 0 | 0.79394 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.8743 | -122.3575 |  | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35224378 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.8888 | 0.075947 | 2.9648 | 0 | 1.1445 | 1.8203 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35290540 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35227657 |  | Base SH | 08W | FICL | Post-Construction | 0 | 0.44186 | 0 | 0.44186 | 0 | 0.44186 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35227658 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.41307 | 0 | 0.41307 | 0 | 0 | 0.41307 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35227659 |  | Base SH | 08W | MAPP | Post-Construction | 0 | 0.25568 | 0 | 0.25568 | 0 | 0.25568 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35297696 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35227651 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.6951 | 0 | 2.6951 | 0 | 0 | 2.6951 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35233312 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.78371 | 0 | 0 | 0.78371 | 0 | 0 | 0.78371 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.633 | -121.388 |  | 1849 | FRRB - UG - 2021 | Tier 3
35227653 |  | Base SH | 08W | CONS | In-Construction | 0 | 2.646 | 0 | 2.646 | 0 | 0 | 2.646 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35227654 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.52992 | 0.52992 | 0 | 0 | 0.52992 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35271455 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.54034 | 0 | 0.54034 | 0 | 0 | 0.54034 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3373 | -122.0168 |  | 42 | Top 250 Miles | Tier 3
35254720 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254721 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.2049 | 0 | 2.2049 | 0 | 0 | 2.2049 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254738 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 1.018 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35300933 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0.77992 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8775 | -120.993 |  | 68 | CWSP 2022-2023 | Tier 2
35254657 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.16004 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254658 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.7561 | 0 | 1.7561 | 0 | 0 | 1.7561 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254659 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.6759 | 0 | 2.6759 | 0 | 0 | 2.6759 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254940 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0.64697 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35254941 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.178 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35254942 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.482 | 0 | 1.482 | 0 | 0 | 1.482 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35254943 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.93201 | 0 | 0.93201 | 0 | 0 | 0.93201 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35243444 |  | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35240169 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.8951 | 0 | 1.8951 | 0 | 0 | 1.8951 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35240170 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.83731 | 0 | 0.83731 | 0 | 0 | 0.83731 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35240171 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.3409 | 0 | 1.3409 | 0 | 0 | 1.3409 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2
35243453 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.2042 | 0 | 1.2042 | 0 | 0 | 1.2042 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35254944 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.052841 | 0.12 | 0.17284 | 0 | 0 | 0.17284 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35283346 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.77803 | 0 | 0 | 0.77803 | 0 | 0 | 0 | 0.77803 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.13 | -122.997 |  | 335 | CWSP 2022-2023 | Tier 2
35254946 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88902 | 0 | 0.88902 | 0 | 0 | 0.88902 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35223039 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 |  | 218 | PSPS - Community Resiliency | Tier 2
35254948 |  | Base SH | 08W | ESTS | Estimating | 0 | 0.97898 | 0 | 0.97898 | 0 | 0 | 0.97898 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35219273 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.1519 | 0 | 1.1519 | 0 | 0 | 1.1519 | 0 | 0 | NV | Region 2 - North East | Manton | TEHAMA | 40.4305 | -121.8716 |  | 39 | Top 250 Miles | Tier 2
35240168 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.5 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35225822 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.75152 | 0 | 0 | 0.75152 | 0 | 0.75152 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6394 | -121.4295 |  | 1849 | FRRB - UG - 2021 | Tier 3
35292756 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 0.75 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35254651 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4252 | 0 | 2.4252 | 0 | 0 | 2.4252 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35254652 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.9341 | 0 | 1.9341 | 0 | 0 | 1.9341 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35254653 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.028 | 0 | 2.028 | 0 | 0 | 2.028 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35254654 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.15511 | 0 | 0.15511 | 0 | 0 | 0.15511 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35254655 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.55227 | 0 | 0.55227 | 0 | 0 | 0.55227 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35254640 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0326 | 0 | 1.0326 | 0 | 0 | 1.0326 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35270755 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0.74867 | 0 | 0 | 0.74867 | 0 | 0.74867 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.8776 | -122.3623 |  | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35254642 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.81042 | 0 | 0.81042 | 0 | 0 | 0.81042 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35237893 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.74811 | 0 | 0 | 0.74811 | 0 | 0 | 0.74811 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35254644 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.41004 | 0 | 0.41004 | 0 | 0 | 0.41004 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35254645 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.75095 | 0 | 0.75095 | 0 | 0 | 0.75095 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4354 | -121.8725 |  | 76 | CWSP 2022-2023 | Tier 2
35254646 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.34394 | 0.34394 | 0 | 0 | 0.34394 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4354 | -121.8725 |  | 76 | CWSP 2022-2023 | Tier 2
35235706 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.7392 | 0 | 0 | 0.7392 | 0 | 0 | 0.7392 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1849 | FRRB - UG - 2021 | Tier 3
35254648 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.48485 | 0 | 0.48485 | 0 | 0 | 0.48485 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4354 | -121.8725 |  | 76 | CWSP 2022-2023 | Tier 2
35254258 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.45 | 0 | 1.45 | 0 | 0 | 0 | 1.45 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35242428 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35240166 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.47784 | 0 | 0.47784 | 0 | 0 | 0.47784 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4595 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35235679 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.72784 | 0 | 0 | 0.72784 | 0 | 0 | 0.72784 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1288 | FRRB - UG - 2021 | Tier 3
35106331 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.49 | 0 | 2.49 | 2.3309 | 0.15909 | 0 | 0 | 0 | NV | Region 2 - North East | Shingletown | SHASTA | 40.4974 | -121.8474 |  | 2314 | Pre | Tier 3
35113102 |  | Base SH | 08W | FICL | Post-Construction | 0 | 2.2267 | 0 | 2.2267 | 2.1784 | 0.048295 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | AMADOR | 38.4952 | -120.5721 |  | 2293 | Pre | Tier 3
35219589 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.7958 | 0 | 2.7958 | 0 | 0 | 0 | 2.7958 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | 52 | Top 250 Miles | Tier 2
35224321 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.4055 | 0 | 2.4055 | 0 | 0 | 0 | 2.4055 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | 52 | Top 250 Miles | Tier 2
35226900 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.6517 | 0 | 0.6517 | 0 | 0 | 0.6517 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | 52 | Top 250 Miles | Tier 2
35226798 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.7034 | 0 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | 52 | Top 250 Miles | Tier 2
35226799 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0.19223 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | 52 | Top 250 Miles | Tier 2
35227001 |  | Base SH | 08W | ADER | Estimating | 0.7214 | 0 | 0 | 0.7214 | 0 | 0 | 0 | 0.7214 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35192291 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.70871 | 0 | 0 | 0.70871 | 0 | 0 | 0.70871 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7215 | -120.8714 |  | 811 | ECOP | Tier 3
35219260 |  | Base SH | 08W | CONS | In-Construction | 0 | 0.92822 | 0.86723 | 1.7955 | 0 | 0.87803 | 0.91742 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.4631 | -121.5149 |  | 29 | Top 250 Miles | Tier 2
35234529 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | 0 | 0 | 0.70833 | 0 | 0 | 0 | 0 | 0.70833 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | PSPS - Community Resiliency | Tier 3
31478906 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley
31534930 |  | Base SH | 08H | UNSC | Ready for Construction | 0 | 2.2805 | 0 | 2.2805 | 0 | 0 | 2.2805 | 0 | 0 | NV | Region 2 - North East
31540451 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East
31548160 |  | Base SH | 08H | ADER | Estimating | 0 | 2.135 | 0 | 2.135 | 0 | 0 | 2.135 | 0 | 0 | NV | Region 2 - North East
31554994 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East
35129944 |  | Base SH | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa
35294275 |  | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA | 38.599 | -122.6197
35264250 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.15473 | 0 | 0.15473 | 0 | 0.15473 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.8915 | -122.3764 |  | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35254649 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.70606 | 0 | 0 | 0.70606 | 0 | 0 | 0.70606 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35242424 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.69943 | 0 | 0 | 0.69943 | 0 | 0 | 0.69943 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35233995 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.69886 | 0 | 0 | 0.69886 | 0 | 0 | 0.69886 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  |  | 1363 | PSPS - Community Resiliency | Tier 3
35284826 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6538 | -120.6215 |  | 1131 | FRRB | Tier 2 & 3
35284827 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 1.2553 | 0.087121 | 1.3424 | 0 | 1.3424 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6538 | -120.6215 |  | 1131 | FRRB | Tier 2 & 3
35284569 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.68409 | 0 | 0 | 0.68409 | 0 | 0 | 0.68409 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1166 | -120.967 |  | 1378 | FRRB | Tier 2
35236992 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5795 | -121.2969 |  | 1480 | FRRB - REMG - 2021 | Tier 3
35242425 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.66155 | 0 | 0 | 0.66155 | 0 | 0 | 0.66155 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35285251 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.65303 | 0 | 0 | 0.65303 | 0 | 0 | 0 | 0.65303 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1758 | -123.0191 |  | 335 | CWSP 2022-2023 | Tier 2
35284567 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.64773 | 0 | 0 | 0.64773 | 0 | 0 | 0.64773 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1039 | -120.976 |  | 1885 | FRRB | Tier 2
35234865 |  | Base SH | 08W | ESTS | Estimating | 0.64754 | 0 | 0 | 0.64754 | 0 | 0 | 0 | 0.64754 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35233311 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0.64205 | 0 | 0 | 0.64205 | 0 | 0.64205 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 36.6329 | -121.3979 |  | 1849 | FRRB - UG - 2021 | Tier 3
35295010 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6426 | -120.5235 |  | 2252 | FRRB | Tier 2 & 3
35295187 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35242426 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.63352 | 0 | 0 | 0.63352 | 0 | 0 | 0.63352 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35058026 |  | Base SH | 08W | ESTS | Estimating | 0.6267 | 0 | 0 | 0.6267 | 0 | 0 | 0 | 0.6267 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7593 | -120.5087 |  | 1138
35227864 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7561 | -122.6051 |  | 14 | Top 50 Miles | Tier 2 & 3
35290508 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0 | 0.62008 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1987 | -123.0496 |  | 75 | CWSP 2022-2023 | Tier 2
35235671 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.6161 | 0 | 0 | 0.6161 | 0 | 0.6161 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - UG - 2021 | Tier 3
35290504 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.61004 | 0 | 0 | 0.61004 | 0 | 0 | 0 | 0.61004 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2145 | -123.0742 |  | 75 | CWSP 2022-2023 | Tier 2
35300884 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0.6 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0671 | -122.2231 |  |  | FRRB
35242429 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6444 | -121.4314 |  | 1288 | FRRB - UG - 2021 | Tier 3
35057010 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.59375 | 0.71572 | 0 | 1.3095 | 0 | 0 | 1.3095 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 |  | 1946 | PSS Approved | Tier 3
35284568 |  | Fire Rebuild | 08W | ADER | Estimating | 0.59318 | 0 | 0 | 0.59318 | 0 | 0 | 0.59318 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.0914 | -120.9837 |  | 2201 | FRRB | Tier 2
35235674 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 865 | FRRB - UG - 2021 | Tier 3
35242420 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.094697 | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 865 | FRRB - UG - 2021 | Tier 3
35241078 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.18258 | 0 | 0.18258 | 0 | 0.18258 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 865 | FRRB - UG - 2021 | Tier 3
35241079 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.074621 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 865 | FRRB - UG - 2021 | Tier 3
35226878 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.58883 | 0 | 0 | 0.58883 | 0 | 0 | 0 | 0.58883 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35285064 |  | Base SH | 08W | ESTS | Estimating | 0.58636 | 0 | 0 | 0.58636 | 0 | 0 | 0 | 0.58636 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3076 | -123.1132 |  | 396 | CWSP 2022-2023 | Tier 2
35229119 |  | Base SH | 08W | UNSC | Ready for Construction | 0.5858 | 0 | 0 | 0.5858 | 0 | 0 | 0.5858 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7513 | -122.6112 |  | 23 | Top 250 Miles | Tier 2 & 3
35292757 |  | Fire Rebuild | 08W | ADER | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35234758 |  | Base SH | 08W | ADER | Estimating | 0.58201 | 0 | 0 | 0.58201 | 0 | 0 | 0 | 0.58201 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35280492 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35280493 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.35 | 0 | 0.35 | 0 | 0 | 0.35 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35280495 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0.51004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35279985 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 2.19 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 |  | 916 | FRRB | Tier 2
35145004 |  | Base SH | 08W | CONS | In-Construction | 0.58201 | 0.37216 | 0 | 0.95417 | 0 | 0 | 0.95417 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa | 37.8624 | -122.0862 |  | 3259 | PSPS - Community Resiliency | Tier 2 & 3
35290943 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35227003 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.58087 | 0 | 0 | 0.58087 | 0 | 0 | 0 | 0.58087 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35290945 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35223030 |  | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East | Bangor | BUTTE | 39.3878 | -121.4038 |  | 355 | PSPS - Community Resiliency | Tier 2
35290947 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35226700 |  | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 |  | 29 | Top 250 Miles | Tier 2
35290518 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35290519 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35295188 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35300885 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.174 | -122.1694 |  | 2246 | FRRB
35290545 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35292759 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35297464 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.56818 | 0 | 0 | 0.56818 | 0 | 0 | 0 | 0.56818 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0777 | -122.2439 |  | 2199 | FRRB
35292781 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35290542 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.56004 | 0 | 0 | 0.56004 | 0 | 0 | 0.56004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35292783 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35238840 |  | Fire Rebuild | 95F | CONS | In-Construction | 0.55152 | 0.012311 | 0 | 0.56383 | 0 | 0 | 0.56383 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0544 | -122.2256
35292785 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35233305 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.55114 | 0 | 0 | 0.55114 | 0 | 0.55114 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35292787 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.16004 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 2342 | FRRB | Tier 2
35227652 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.55 | 0 | 0 | 0.55 | 0 | 0 | 0.55 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | 42 | Top 250 Miles | Tier 3
35227025 |  | Base SH | 08W | ESTS | Estimating | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0 | 0.54924 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35290541 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.34223 | 0 | 0.34223 | 0 | 0.34223 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 1285 | FRRB | Tier 2
35292790 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 1285 | FRRB | Tier 2
35233955 |  | Base SH | 08W | ESTS | Estimating | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35302344 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.18939 | 0 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1227 | -120.9845 |  | 715 | FRRB | Tier 3
35286199 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.29167 | 0 | 0.29167 | 0 | 0.29167 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 |  | 715 | FRRB | Tier 3
35145540 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.53902 | 0.73333 | 0 | 1.2723 | 0 | 0 | 1.2723 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 |  | 1316 | PSPS - Scoped | Tier 3
35279603 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 |  | 715 | FRRB | Tier 3
35279604 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.5146 | 0 | 1.5146 | 0 | 1.3017 | 0.21288 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 |  | 715 | FRRB | Tier 3
35279605 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.72879 | 0 | 0.72879 | 0 | 0.72879 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 |  | 715 | FRRB | Tier 3
35223038 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.53295 | 0 | 0 | 0.53295 | 0 | 0 | 0.53295 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | AMADOR | 38.3949 | -120.804 |  | 999 | PSPS - Community Resiliency | Tier 2
35254641 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.52235 | 0.075947 | 0.47727 | 1.0756 | 0 | 0 | 1.0756 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2 & 3
35295184 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35277195 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.8656 | -121.3819 |  | 11 | FRRB | Tier 2 & 3
35277565 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | FRRB | Tier 2 & 3
35293508 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.51004 | 0 | 0 | 0.51004 | 0 | 0 | 0 | 0.51004 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8729 | -120.991 |  | 68 | CWSP 2022-2023 | Tier 2
35254945 |  | Base SH | 08W | ESTS | Estimating | 0.51 | 0 | 0 | 0.51 | 0 | 0 | 0 | 0.51 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35254647 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.50606 | 0 | 0 | 0.50606 | 0 | 0 | 0 | 0.50606 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4354 | -121.8725 |  | 76 | CWSP 2022-2023 | Tier 2
35293662 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8956 | -120.9606 |  | 169 | CWSP 2022-2023 | Tier 2
35297232 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0.18939 | 0.18939 | 0 | 0 | 0 | 0.18939 | 0 | NV | Region 2 - North East | Twain | PLUMAS | 40.0139 | -121.2232 |  | 378 | FRRB - REMG - 2021 | Tier 2 & 3
35295446 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Quincy | PLUMAS | 39.8957 | -121.2789 |  | 1658 | FRRB | Tier 2 & 3
35279987 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.5227 | 0.087121 | 1.6098 | 0 | 1.6098 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 |  | 2726 | FRRB | Tier 2
35292751 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 895 | FRRB | Tier 2
35292753 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 895 | FRRB | Tier 2
35235673 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.49356 | 0 | 0 | 0.49356 | 0 | 0.49356 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 |  | 1299 | FRRB - UG - 2021 | Tier 3
35280497 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 895 | FRRB | Tier 2
35280498 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0.073295 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 895 | FRRB | Tier 2
35286724 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.0837 | 0 | 1.0837 | 0 | 1.0485 | 0.035227 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1746 | -120.9945 |  | 895 | FRRB | Tier 2
35234399 |  | Base SH | 08W | ESTS | Estimating | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35285586 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.27216 | 0 | 0.27216 | 0 | 0.27216 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35285587 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.71136 | 0 | 0.71136 | 0 | 0.71136 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35285588 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.56307 | 0.046023 | 0.60909 | 0 | 0.60909 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35236993 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - REMG - 2021 | Tier 3
35285590 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.43674 | 0 | 0.43674 | 0 | 0.43674 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35285591 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.47595 | 0.032955 | 0.5089 | 0 | 0.5089 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35285592 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.76458 | 0 | 0.76458 | 0 | 0.76458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35285593 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.26458 | 0 | 0.26458 | 0 | 0.26458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2005 | FRRB | Tier 2
35236660 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.47992 | 0 | 0 | 0.47992 | 0 | 0 | 0.47992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35285352 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.13845 | 0 | 0.13845 | 0 | 0.13845 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2005 | FRRB | Tier 2
35285353 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.31856 | 0 | 0.31856 | 0 | 0.31856 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2005 | FRRB | Tier 2
35285354 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2005 | FRRB | Tier 2
35285585 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.63902 | 0 | 0.63902 | 0 | 0.63902 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 3355 | FRRB | Tier 2
35285741 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.26837 | 0.027273 | 0.29564 | 0 | 0.29564 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35285742 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.24432 | 0.027462 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35286483 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.0843 | 0 | 1.0843 | 0 | 1.0843 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35284716 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.7589 | 0 | 0.7589 | 0 | 0.7589 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6375 | -120.5393 |  | 2252 | FRRB | Tier 2 & 3
35284717 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.89489 | 0 | 0.89489 | 0 | 0.89489 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6325 | -120.5421 |  | 2252 | FRRB | Tier 2 & 3
35292144 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.139 | 0 | 1.139 | 0 | 1.139 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35292145 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 2.1585 | 0 | 2.1585 | 0 | 1.625 | 0.53352 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35292188 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.13542 | 0 | 0.13542 | 0 | 0.13542 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35292189 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.18125 | 0 | 0.18125 | 0 | 0.18125 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35282125 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6385 | -120.5319 |  | 2252 | FRRB | Tier 2 & 3
35282126 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6385 | -120.5319 |  | 2252 | FRRB | Tier 2 & 3
35282281 |  | Fire Rebuild | 08W | ESTS | Post-Construction | 0 | 0.47235 | 0 | 0.47235 | 0 | 0.47235 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6311 | -120.5678 |  | 2252 | FRRB | Tier 2 & 3
35284828 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.65606 | 0 | 0.65606 | 0 | 0.65606 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6335 | -120.5339 |  | 2252 | FRRB | Tier 2 & 3
35284829 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.57348 | 0 | 0.57348 | 0 | 0.57348 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6341 | -120.5354 |  | 2252 | FRRB | Tier 2 & 3
35284830 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.76515 | 0 | 0.76515 | 0 | 0.76515 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6455 | -120.5406 |  | 2252 | FRRB | Tier 2 & 3
35284831 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.96402 | 0 | 0.96402 | 0 | 0.96402 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6361 | -120.5283 |  | 2252 | FRRB | Tier 2 & 3
35284832 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.89299 | 0 | 0.89299 | 0 | 0.89299 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6421 | -120.5132 |  | 2252 | FRRB | Tier 2 & 3
35284833 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.91837 | 0 | 0.91837 | 0 | 0.91837 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6404 | -120.5146 |  | 2252 | FRRB | Tier 2 & 3
35284834 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.70587 | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6386 | -120.5215 |  | 2252 | FRRB | Tier 2 & 3
35284835 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.4661 | 0 | 0.4661 | 0 | 0.4661 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | EL DORADO | 38.6411 | -120.5234 |  | 2252 | FRRB | Tier 2 & 3
35284836 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 0.88182 | 0 | 0.88182 | 0 | 0.88182 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.643 | -120.526 |  | 2252 | FRRB | Tier 2 & 3
35284837 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 1.7884 | 0 | 1.7884 | 0 | 1.7884 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6544 | -120.5324 |  | 2252 | FRRB | Tier 2 & 3
35284838 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.60568 | 0 | 0.60568 | 0 | 0.60568 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6544 | -120.5324 |  | 2252 | FRRB | Tier 2 & 3
35284839 |  | Fire Rebuild | 08W | UNSC | Post-Construction | 0 | 0.47595 | 0 | 0.47595 | 0 | 0.47595 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.6533 | -120.5363 |  | 2252 | FRRB | Tier 2 & 3
35285048 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.41212 | 0 | 0.41212 | 0 | 0.41212 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | EL DORADO | 38.7868 | -120.2054 |  | 2252 | FRRB | Tier 2 & 3
35285049 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.18542 | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | EL DORADO | 38.7799 | -120.2508 |  | 2252 | FRRB | Tier 2 & 3
35285050 |  | Fire Rebuild | 08W | PEND | Post-Construction | 0 | 1.593 | 0 | 1.593 | 0 | 1.593 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | EL DORADO | 38.8096 | -120.1259 |  | 2252 | FRRB | Tier 2 & 3
35237891 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.47197 | 0 | 0 | 0.47197 | 0 | 0 | 0.47197 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1299 | FRRB - UG - 2021 | Tier 3
35295017 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.47008 | 0 | 0 | 0.47008 | 0 | 0 | 0.47008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6407 | -120.5097 |  | 2252 | FRRB | Tier 2 & 3
35233038 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.46932 | 0 | 0 | 0.46932 | 0 | 0.46932 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35233039 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.46326 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35239937 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.46193 | 0 | 0 | 0.46193 | 0 | 0.46193 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35279313 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.45985 | 0 | 0 | 0.45985 | 0 | 0 | 0.45985 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 |  | 1172 | FRRB | Tier 2 & 3
35301112 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.45 | 0.05 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.8641 | -120.9817 |  | 68 | CWSP 2022-2023 | Tier 2
35239099 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35254656 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.44205 | 0 | 0 | 0.44205 | 0 | 0 | 0.44205 | 0 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | CWSP 2022-2023 | Tier 2 & 3
35254067 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.43996 | 0.039962 | 0 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0 | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 |  | 68 | CWSP 2022-2023 | Tier 2
35297695 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.43996 | 0 | 0 | 0.43996 | 0 | 0 | 0.43996 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35227002 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.43295 | 0 | 0 | 0.43295 | 0 | 0 | 0 | 0.43295 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35243440 |  | Base SH | 08W | ESTS | Estimating | 0.42992 | 0 | 0 | 0.42992 | 0 | 0 | 0 | 0.42992 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 290 | PSPS | Tier 2
35295745 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.41913 | 0 | 0 | 0.41913 | 0 | 0 | 0.41913 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6008 | -121.4265 |  | 1176 | FRRB
35278093 |  | Base SH | 08W | ESTS | Estimating | 0.41496 | 0 | 0.52008 | 0.93504 | 0 | 0 | 0 | 0.93504 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9797 | -119.3677 |  | 163 | CWSP 2022-2023 | Tier 2
35240167 |  | Base SH | 08W | ESTS | Estimating | 0.41288 | 0.037879 | 0 | 0.45076 | 0 | 0 | 0 | 0.45076 | 0 | NV | Region 2 - North East | Manton | SHASTA | 40.4595 | -121.8662 |  | 76 | CWSP 2022-2023 | Tier 2
35283874 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.40284 | 0 | 0.15057 | 0.55341 | 0 | 0 | 0.55341 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35254260 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | SA | Region 2 - North East | Winters | SOLANO | 38.481 | -122.0272 |  | 92 | CWSP 2022-2023 | Tier 2
35295012 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6507 | -120.5314 |  | 2252 | FRRB | Tier 2 & 3
35235669 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.39148 | 0 | 0 | 0.39148 | 0 | 0.39148 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - UG - 2021 | Tier 3
35295191 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3911 | 0 | 0 | 0.3911 | 0 | 0 | 0.3911 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6384 | -120.5197 |  | 2252 | FRRB | Tier 2 & 3
35277938 |  | Base SH | 08W | ESTS | Estimating | 0.38996 | 0 | 0.27973 | 0.6697 | 0 | 0 | 0 | 0.6697 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0125 | -119.4038 |  | 163 | CWSP 2022-2023 | Tier 2
35233309 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.38295 | 0 | 0 | 0.38295 | 0 | 0.38295 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6321 | -121.4205 |  | 1849 | FRRB - UG - 2021 | Tier 3
31547582 |  | Fire Rebuild | 92F | UNSC | Ready for Construction | 0 | 1.0136 | 0 | 1.0136 | 0 | 0 | 1.0136 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.012 | -120.9667 |  | 1172 | FRRB | Tier 2 & 3
35282057 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas |  |  |  | 1172 | FRRB | Tier 2 & 3
35233300 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.37879 | 0 | 0 | 0.37879 | 0 | 0 | 0.37879 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35232718 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.37652 | 0 | 0 | 0.37652 | 0 | 0.37652 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35295018 |  | Fire Rebuild | 08W | ADER | Estimating | 0.37008 | 0 | 0 | 0.37008 | 0 | 0 | 0.37008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6462 | -120.5227 |  | 2252 | FRRB | Tier 2 & 3
35254650 |  | Base SH | 08W | ESTS | Estimating | 0.36402 | 0 | 0 | 0.36402 | 0 | 0 | 0 | 0.36402 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.4013 | -121.8752 |  | 157 | CWSP 2022-2023 | Tier 2
35233307 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.36402 | 0 | 0 | 0.36402 | 0 | 0.36402 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6305 | -121.4215 |  | 1849 | FRRB - UG - 2021 | Tier 3
35233304 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.35644 | 0 | 0 | 0.35644 | 0 | 0.35644 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35233306 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.35398 | 0 | 0 | 0.35398 | 0 | 0.35398 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.63 | -121.4206 |  | 1849 | FRRB - UG - 2021 | Tier 3
35236999 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.175 | 0 | 0.175 | 0 | 0.175 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 |  | 1480 | FRRB - UG - 2021 | Tier 3
35237020 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.50795 | 0 | 0.50795 | 0 | 0.50795 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5603 | -121.3467 |  | 1480 | FRRB - REMG - 2021 | Tier 3
35240542 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.90795 | 0 | 0.90795 | 0 | 0.90795 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 |  | 1480 | FRRB - OH - 2021 | Tier 3
35240543 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.2068 | 0 | 1.2068 | 0 | 1.2068 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 |  | 1480 | FRRB - OH - 2021 | Tier 3
35236982 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.95 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - REMG - 2021 | Tier 3
35235701 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0.10909 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - UG - 2021 | Tier 3
35239522 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.34848 | 0 | 0 | 0.34848 | 0 | 0 | 0.34848 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35227004 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.3483 | 0 | 0 | 0.3483 | 0 | 0 | 0.3483 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | ECOP - Top 20% | Tier 3
35236986 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.8441 | 0 | 1.8441 | 0 | 1.8441 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - REMG - 2021 | Tier 3
35236989 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0 | 0.51326 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - OH - 2021 | Tier 3
35236983 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.34072 | 0 | 0 | 0.34072 | 0 | 0 | 0.34072 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.6772 | -121.4917 |  | 1288 | FRRB - REMG - 2021 | Tier 3
35235704 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.18902 | 0 | 0.18902 | 0 | 0 | 0 | 0.18902 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | 1480 | FRRB - UG - 2021 | Tier 3
35294385 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.56 | -121.3289 |  | 1480 | FRRB - OH - 2021 | Tier 3
35318074 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.33996 | 0 | 0 | 0.33996 | 0 | 0 | 0 | 0.33996 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.072 | -122.2298
35227162 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.32008 | 0 | 0 | 0.32008 | 0 | 0 | 0.32008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | Top 50 Miles | Tier 2
35253173 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.059848 | 0 | 0.059848 | 0 | 0.059848 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5466 | -121.3552 |  | 1480 | FRRB - OH - 2021 | Tier 3
35253174 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.28826 | 0 | 0.28826 | 0 | 0.28826 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5462 | -121.3509 |  | 1480 | FRRB - OH - 2021 | Tier 3
35223063 |  | Base SH | 08W | ESTS | Estimating | 0.3197 | 0 | 0 | 0.3197 | 0 | 0 | 0 | 0.3197 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | PSPS - Community Resiliency | Tier 2
35244696 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.29678 | 0 | 0.29678 | 0 | 0.29678 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35244697 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.12405 | 0 | 0.12405 | 0 | 0.12405 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5618 | -121.3286 |  | 1480 | FRRB - OH - 2021 | Tier 3
35244698 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.090341 | 0 | 0.090341 | 0 | 0 | 0 | 0.090341 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35244699 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.080114 | 0 | 0.080114 | 0 | 0 | 0 | 0.080114 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245140 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0.27178 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245141 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.054545 | 0 | 0.054545 | 0 | 0 | 0 | 0.054545 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245142 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245143 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.2589 | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245144 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.24886 | 0 | 0.24886 | 0 | 0.24886 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245145 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.095455 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245146 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.13731 | 0 | 0.13731 | 0 | 0 | 0 | 0.13731 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245147 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0 | 0.39242 | 0 | 0.39242 | 0 | 0.39242 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245148 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.20492 | 0 | 0.20492 | 0 | 0 | 0 | 0.20492 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245149 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.26894 | 0 | 0.26894 | 0 | 0 | 0 | 0.26894 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245150 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.12557 | 0 | 0.12557 | 0 | 0 | 0 | 0.12557 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245151 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.15455 | 0 | 0.15455 | 0 | 0.15455 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35245152 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.48295 | 0 | 0.48295 | 0 | 0 | 0 | 0.48295 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 |  | 1480 | FRRB - OH - 2021 | Tier 3
35109546 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.31515 | 2.4574 | 0 | 2.7725 | 0 | 0 | 2.7725 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  |  | 1946 | PSS Approved | Tier 3
35295016 |  | Fire Rebuild | 08W | ADER | Estimating | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6425 | -120.5224 |  | 2252 | FRRB | Tier 2 & 3
35241077 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | 0 | 0.31004 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35279508 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1057 | -120.9742 |  | 1885 | FRRB | Tier 2
35279509 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.1801 | 0 | 1.1801 | 0 | 1.1801 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1057 | -120.9742 |  | 1885 | FRRB | Tier 2
35235672 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | 0 | 0 | 0.30303 | 0 | 0 | 0 | 0.30303 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 |  | 1299 | FRRB - UG - 2021 | Tier 3
35284570 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.24564 | 0 | 0.24564 | 0 | 0.24564 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1172 | -120.9705 |  | 1885 | FRRB | Tier 2
35233310 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.30246 | 0 | 0 | 0.30246 | 0 | 0 | 0.30246 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6338 | -121.4138 |  | 1849 | FRRB - UG - 2021 | Tier 3
35217272 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | 7 | Top 50 Miles | Tier 3
35290944 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35281759 |  | Fire Rebuild | 08W | ADER | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | PLUMAS | 40.0604 | -120.9643 |  | 1322 | FRRB | Tier 2
35281815 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35250343 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.29432 | 0 | 0 | 0.29432 | 0 | 0 | 0.29432 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5737 | -121.3129 |  | 1480 | FRRB - UG - 2021 | Tier 3
35291986 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.8223 | 0 | 1.8223 | 0 | 1.6958 | 0.12652 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6951 | -122.3174 |  | 851 | FRRB | Tier 2
35236997 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | 0 | 0 | 0.28409 | 0 | 0 | 0 | 0.28409 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6827 | -121.3105 |  | 1299 | FRRB - REMG - 2021 | Tier 3
35293380 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6915 | -122.318 |  | 851 | FRRB | Tier 2
35291988 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6957 | -122.3167 |  | 851 | FRRB | Tier 2
35291987 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6856 | -122.3196 |  | 502 | FRRB | Tier 2
35291895 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.18864 | 0 | 0.18864 | 0 | 0.18864 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.703 | -122.2836 |  | 502 | FRRB | Tier 2
35291982 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.15076 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6862 | -122.3124 |  | 502 | FRRB | Tier 2
35291983 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.25038 | 0 | 0.25038 | 0 | 0.25038 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6853 | -122.3097 |  | 502 | FRRB | Tier 2
35291984 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 1.4841 | 0 | 1.4841 | 0 | 1.4841 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6755 | -122.3215 |  | 502 | FRRB | Tier 2
35291985 |  | Fire Rebuild | 08W | CONS | In-Construction | 0 | 0.8875 | 0 | 0.8875 | 0 | 0.8875 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6857 | -122.3155 |  | 502 | FRRB | Tier 2
35285589 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.28295 | 0 | 0 | 0.28295 | 0 | 0 | 0.28295 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2461 | FRRB | Tier 2
35220896 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 |  | 14 | Top 50 Miles | Tier 2 & 3
35295015 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6426 | -120.5235 |  | 2252 | FRRB | Tier 2 & 3
35224377 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.2786 | 0 | 0 | 0.2786 | 0 | 0 | 0.2786 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado |  |  |  | 1363 | PSPS - Community Resiliency | Tier 3
35283198 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.27803 | 0 | 0 | 0.27803 | 0 | 0 | 0 | 0.27803 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.108 | -122.9558 |  | 58 | CWSP 2022-2023 | Tier 2
35254947 |  | Base SH | 08W | ESTS | Estimating | 0.263 | 0 | 0 | 0.263 | 0 | 0 | 0 | 0.263 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | 966 | CWSP 2022-2023 | Tier 2
35056733 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.26193 | 1.2653 | 0 | 1.5273 | 0 | 0 | 1.5273 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 |  | 1946 | PSS Approved | Tier 3
35281810 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35281813 |  | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.046591 | 0 | 0.046591 | 0 | 0 | 0 | 0.046591 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35232298 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.26155 | 0 | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35295182 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.26004 | 0 | 0 | 0.26004 | 0 | 0 | 0.26004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35144944 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.2553 | 0 | 0 | 0.2553 | 0 | 0 | 0.2553 | 0 | 0 | PN | Region 3 - Bay Area | South San Francisco | SAN MATEO | 37.6432 | -122.4679 |  | 3550 | PSPS - Community Resiliency | Tier 2
35235320 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6316 | -121.3793 |  | 1299 | FRRB - UG - 2021 | Tier 3
35290808 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.24508 | 0 | 0 | 0.24508 | 0 | 0 | 0 | 0.24508 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2815 | -123.1027 |  | 75 | CWSP 2022-2023 | Tier 2
35109541 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.24223 | 2.4256 | 0 | 2.6678 | 0 | 0 | 2.6678 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado |  |  |  | 1946 | PSS Approved | Tier 3
35285065 |  | Base SH | 08W | ESTS | Estimating | 0.24167 | 0.012311 | 0 | 0.25398 | 0 | 0 | 0 | 0.25398 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2968 | -123.1087 |  | 396 | CWSP 2022-2023 | Tier 2
35145003 |  | Base SH | 08W | CONS | In-Construction | 0.24015 | 0.079545 | 0 | 0.3197 | 0 | 0 | 0.3197 | 0 | 0 | DI | Region 3 - Bay Area | Orinda | Contra Costa |  |  |  | 2631 | PSPS - Community Resiliency | Tier 2 & 3
35219543 |  | Base SH | 08W | ESTS | Estimating | 0.24 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0.24 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7293 | -120.7998 |  | 2123 | PSPS - Community Resiliency | Tier 2
35292782 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.23011 | 0 | 0 | 0.23011 | 0 | 0 | 0.23011 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35239523 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.22917 | 0 | 0 | 0.22917 | 0 | 0.22917 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35295193 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6462 | -120.5227 |  | 2252 | FRRB | Tier 2 & 3
35285594 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado |  |  |  | 2005 | FRRB | Tier 2
35259516 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.21364 | 0 | 0 | 0.21364 | 0 | 0 | 0.21364 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.598 | -122.2382 |  | 100 | CWSP 2022-2023 | Tier 2
35277925 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.21326 | 0 | 0 | 0.21326 | 0 | 0 | 0 | 0.21326 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0746 | -119.4845 |  | 63 | CWSP 2022-2023 | Tier 2
35295190 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35279243 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.20511 | 0 | 0 | 0.20511 | 0 | 0.20511 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6287 | -121.3656 |  | 1849 | FRRB - UG - 2021 | Tier 3
35249161 |  | Fire Rebuild | 08W | MAPP | Post-Construction | 0.19508 | 0 | 0 | 0.19508 | 0 | 0.19508 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6397 | -121.3741 |  | 1849 | FRRB - UG - 2021 | Tier 3
35284365 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.19375 | 0.019508 | 0 | 0.21326 | 0 | 0 | 0 | 0.21326 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2399 | -120.3619 |  | 235 | CWSP 2022-2023 | Tier 2 & 3
35237021 |  | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.19318 | 0 | 0 | 0.19318 | 0 | 0 | 0.19318 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5614 | -121.4274 |  | 1299 | FRRB - UG - 2021 | Tier 3
35295192 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.18996 | 0 | 0 | 0.18996 | 0 | 0 | 0.18996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  |  | 2252 | FRRB | Tier 2 & 3
35290946 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35295011 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6507 | -120.5314 |  | 2252 | FRRB | Tier 2 & 3
35295189 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35292780 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.17008 | 0 | 0 | 0.17008 | 0 | 0 | 0.17008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35219542 |  | Base SH | 08W | UNSC | Ready for Construction | 0.16629 | 0 | 0.048295 | 0.21458 | 0 | 0 | 0.21458 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7307 | -120.7828 |  | 2123 | PSPS - Community Resiliency | Tier 2
35295014 |  | Fire Rebuild | 08W | ADER | Estimating | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6426 | -120.5235 |  | 2252 | FRRB | Tier 2 & 3
35233302 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35259512 |  | Base SH | 08W | ADER | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA | 40.6324 | -122.2376 |  | 100 | CWSP 2022-2023 | Tier 2
35292758 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 916 | FRRB | Tier 2
35290948 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35295013 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6507 | -120.5314 |  | 2252 | FRRB | Tier 2 & 3
35295194 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado |  |  |  | 2252 | FRRB | Tier 2 & 3
35279512 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.13542 | 0 | 0 | 0.13542 | 0 | 0 | 0.13542 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1174 | -120.9918 |  | 715 | FRRB | Tier 3
35240545 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.13125 | 0 | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35240546 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.13087 | 0 | 0 | 0.13087 | 0 | 0 | 0.13087 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | 1849 | FRRB - UG - 2021 | Tier 3
35233301 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.12917 | 0 | 0 | 0.12917 | 0 | 0.12917 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35318072 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.12784 | 0 | 0 | 0.12784 | 0 | 0 | 0.12784 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1291 | -122.1378
35292791 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 1285 | FRRB | Tier 2
35295185 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | 2252 | FRRB | Tier 2 & 3
35235675 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | 0 | 0 | 0.11364 | 0 | 0 | 0 | 0.11364 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1299 | FRRB - UG - 2021 | Tier 3
35241076 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35235670 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1299 | FRRB - UG - 2021 | Tier 3
35277924 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | 0 | 0.12955 | 0.23864 | 0 | 0 | 0 | 0.23864 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0071 | -119.4086 |  | 163 | CWSP 2022-2023 | Tier 2
35280362 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.1089 | 0 | 0 | 0.1089 | 0 | 0 | 0 | 0.1089 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9483 |  | 50 | Top 250 Miles | Tier 2 & 3
35248770 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.10814 | 0 | 0 | 0.10814 | 0 | 0.10814 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1849 | FRRB - UG - 2021 | Tier 3
35226632 |  | Base SH | 08W | PEND | Permitting/Dependency | 0.10606 | 0 | 0 | 0.10606 | 0 | 0 | 0.10606 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.362 | -123.1283 |  | 43 | Top 250 Miles | Tier 2
35116801 |  | Base SH | 08W | FICL | Post-Construction | 0.10417 | 1.1737 | 0 | 1.2778 | 0.37008 | 0.90777 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 |  | 2411 | Pre | Tier 3
35233957 |  | Base SH | 08W | ESTS | Estimating | 0.10208 | 0 | 0 | 0.10208 | 0 | 0 | 0.10208 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | 49 | Top 250 Miles | Tier 2
35292784 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35292786 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | FRRB | Tier 2
35292789 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 2342 | FRRB | Tier 2
74008802 |  | Other | 06A | DOCC | Post-Construction | 0.099432 | 1.0496 | 0 | 1.1491 | 0 | 1.1491 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa | 37.9561 | -122.0286 |  | 2676
35299634 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.6566 | -121.5763 |  | 1033 | PSPS | Tier 2
35299633 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.6569 | -121.5758 |  | 1703 | PSPS | Tier 2
35299635 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Paradise | BUTTE | 39.6988 | -121.5742 |  | 1535 | PSPS | Tier 2
35299631 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.6474 | -121.6306 |  | 698 | PSPS | Tier 2
35299629 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.6551 | -121.6343 |  | 268 | PSPS | Tier 2
35282131 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5804 | -121.2945 |  | 1480 | FRRB - UG - 2021 | Tier 3
35277935 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.092992 | 0 | 0 | 0.092992 | 0 | 0 | 0 | 0.092992 | 0 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0313 | -119.4396 |  | 274 | CWSP 2022-2023 | Tier 2
35279510 |  | Fire Rebuild | 08W | FICL | Post-Construction | 0.091856 | 0 | 0 | 0.091856 | 0 | 0.091856 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1057 | -120.9742 |  | 1378 | FRRB | Tier 2
35114040 |  | Base SH | 08W | UNSC | Ready for Construction | 0.090341 | 1.3943 | 0 | 1.4847 | 0 | 0 | 1.4847 | 0 | 0 | ST | Region 5 - Central Valley | Kit Carson | Amador |  |  |  | 2271 | Pre | Tier 3
35234862 |  | Base SH | 08W | ESTS | Estimating | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | 0 | 0.079924 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | ECOP - Top 20% | Tier 3
35281816 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2
35234527 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | 0 | 0 | 0.075947 | 0 | 0 | 0 | 0 | 0.075947 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | PSPS - Community Resiliency | Tier 3
35223036 |  | Base SH | 08W | UNSC | Ready for Construction | 0.072159 | 0 | 0.018371 | 0.09053 | 0 | 0 | 0.072159 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.2376 | -121.0592 |  | 2134 | PSPS - Community Resiliency | Tier 2
35241075 |  | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | 0 | 0 | 0.070076 | 0 | 0 | 0 | 0.070076 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1299 | FRRB - UG - 2021 | Tier 3
35254695 |  | Fire Rebuild | 08W | CONS | In-Construction | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.5752 | -121.3053 |  | 1480 | FRRB - UG - 2021 | Tier 3
35233303 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.065909 | 0 | 0 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6425 | -121.4237 |  | 1849 | FRRB - UG - 2021 | Tier 3
35199565 |  | Fire Rebuild | 95A | ESTS | Post-Construction | 0 | 28.8953 | 0 | 28.8953 | 26.7508 | 2.1445 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5439 | -121.4323 |  | 1288
35222036 |  | Fire Rebuild | 95F | PEND | Permitting/Dependency | 0 | 0.52462 | 0 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1676 | -122.2
35235158 |  | Fire Rebuild | 95F | MAPP | Post-Construction | 0 | 0.030871 | 0 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | CC | Region 4 - Central Coast | Felton | SANTA CRUZ | 37.0448 | -122.0673
35237593 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.027462 | 0 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ | 37.1011 | -122.1426
35237620 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.024621 | 0 | 0.024621 | 0 | 0.024621 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0742 | -122.2363
35238587 |  | Fire Rebuild | 95F | DOCC | Post-Construction | 0 | 0.36761 | 0 | 0.36761 | 0 | 0.36761 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Big sur | MONTEREY | 36.1136 | -121.6264
35244330 |  | Fire Rebuild | 08W | DOCC | Post-Construction | 0.057386 | 0 | 0 | 0.057386 | 0 | 0.057386 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 |  | 1849 | FRRB - UG - 2021 | Tier 3
35239462 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.28788 | 0 | 0.28788 | 0 | 0.22879 | 0.059091 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1797 | -122.1837
35239464 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.070265 | 0 | 0.070265 | 0 | 0 | 0.070265 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1297 | -122.1378
35242673 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.067235 | 0 | 0.067235 | 0 | 0.067235 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1701 | -122.1891
35245029 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.3125 | 0 | 0.3125 | 0 | 0 | 0.3125 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ | 37.0954 | -122.1479
35250987 |  | Fire Rebuild | 95F | CONS | In-Construction | 0 | 0.08447 | 0 | 0.08447 | 0 | 0 | 0.08447 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1376 | -122.1453
35259466 |  | Fire Rebuild | 95F | MAPP | Post-Construction | 0 | 0.045076 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | SANTA CRUZ | 37.093 | -122.1442
35263364 |  | Fire Rebuild | 95F | FICL | Post-Construction | 0 | 0.38788 | 0 | 0.38788 | 0 | 0 | 0.38788 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1636 | -122.1864
35217268 |  | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.039962 | 0.056818 | 0 | 0.09678 | 0 | 0 | 0.09678 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas |  |  |  | 11 | Top 50 Miles | Tier 2 & 3
35234528 |  | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | 0 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0.035985 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | PSPS - Community Resiliency | Tier 3
35244158 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Goodyears Bar | SIERRA | 39.5601 | -120.7512 |  | 1753
35208064 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SI | Region 2 - North East | Goodyears Bar | SIERRA | 39.5441 | -120.8676 |  | 1446
35028500 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.65152 | 0.65152 | 0 | 0.65152 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | SIERRA | 39.4782 | -120.8883 |  | 1446
35264104 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10189 | 0.10189 | 0 | 0 | 0.10189 | 0 | 0 | SI | Region 2 - North East | Downieville | SIERRA | 39.5593 | -120.8348 |  | 1446
35244150 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.437 | -120.8154 |  | 1700
35121398 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.03447 | 0.03447 | 0 | 0.03447 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.8413 | -122.3559 |  | 1722
35121520 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0.65606 | 0 | 0 | NV | Region 2 - North East | Lakehead | SHASTA | 40.8122 | -122.3073 |  | 1722
35185246 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.30701 | 0.30701 | 0 | 0.30701 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7458 | -120.599 |  | 1284
35244148 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Camino | EL DORADO | 38.7495 | -120.6168 |  | 1284
35148224 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Camino | EL DORADO | 38.7398 | -120.6765 |  | 1422
35244146 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.6211 | -120.7249 |  | 1035
35148039 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Somerset | EL DORADO | 38.5689 | -120.6488 |  | 654
35148037 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.07822 | 0.07822 | 0 | 0 | 0.07822 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.6783 | -120.5793 |  | 1131
35111037 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.030682 | 0.030682 | 0 | 0.030682 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Atascadero | SAN LUIS OBISPO | 35.461 | -120.7383 |  | 1294
35083699 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0361 | -119.3341 |  | 1302
35154942 |  | Idle Facilities | 07D | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.1162 | -119.4489 |  | 956
35221652 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Prather | FRESNO | 37.0335 | -119.5175 |  | 213
35205112 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.095644 | 0.095644 | 0 | 0.095644 | 0 | 0 | 0 | NV | Region 2 - North East | Marysville | YUBA | 39.3393 | -121.3618 |  | 785
35211755 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.10473 | 0.10473 | 0 | 0 | 0.10473 | 0 | 0 | NV | Region 2 - North East | Marysville | YUBA | 39.3521 | -121.3673 |  | 785
35211757 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Marysville | YUBA | 39.3562 | -121.3774 |  | 225
35277147 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | MARIPOSA | 37.7302 | -120.182 |  | 1019
35145458 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 1.6263 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.758 | -120.0408 |  | 882
35083878 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045644 | 0.045644 | 0 | 0 | 0.045644 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | MARIPOSA | 37.7096 | -120.1166 |  | 1547
35211260 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | SI | Region 2 - North East | Auburn | PLACER | 38.9957 | -121.1091 |  | 118
35211742 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.093561 | 0.093561 | 0 | 0 | 0.093561 | 0 | 0 | SI | Region 2 - North East | Auburn | PLACER | 39.0003 | -121.1186 |  | 118
35078178 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1304 | -122.1182 |  | 2968
35240792 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.075189 | 0.075189 | 0 | 0.075189 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6424 | -119.9642 |  | 995
35106411 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.038447 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | SI | Region 2 - North East | Dutch Flat | PLACER | 39.1967 | -120.8328 |  | 1526
35149117 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.099621 | 0.099621 | 0 | 0.099621 | 0 | 0 | 0 | HB | Region 1 - North Coast | Carlotta | HUMBOLDT | 40.4723 | -123.8654 |  | 1315
35037613 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Carlotta | HUMBOLDT | 40.4722 | -123.87 |  | 1315
35211230 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0.061174 | 0 | 0 | SA | Region 2 - North East | Browns Valley | YUBA | 39.2454 | -121.3989 |  | 774
35208071 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1654 | -121.0158 |  | 1638
35244185 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley |  | 39.2161 | -121.0312 |  | 1876
35211797 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.2206 | -121.0809 |  | 2928
35224443 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.096402 | 0.096402 | 0 | 0.096402 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Buellton | SANTA BARBARA | 34.6338 | -120.189 |  | 517
35224439 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15777 | 0.15777 | 0 | 0.15777 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 34.6171 | -120.1485 |  | 269
35122245 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA | 34.6736 | -120.4356 |  | 1278
35122244 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA | 34.613 | -120.3724 |  | 998
35224451 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.013258 | 0.013258 | 0 | 0 | 0.013258 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA | 34.6843 | -120.6038 |  | 1500
35224444 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.32481 | 0.32481 | 0 | 0.32481 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA | 34.6219 | -120.4538 |  | 949
35224438 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0.017235 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | SANTA BARBARA | 34.5386 | -120.5365 |  | 949
35222069 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.067045 | 0.067045 | 0 | 0.067045 | 0 | 0 | 0 | ST | Region 5 - Central Valley | San Andreas | CALAVERAS | 38.1699 | -120.6303 |  | 886
35221824 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.052652 | 0.052652 | 0 | 0 | 0.052652 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3042 | -120.672 |  | 1889
35221747 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS | 38.2342 | -120.5195 |  | 804
35221748 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS | 38.243 | -120.5166 |  | 804
35222073 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS | 38.2419 | -120.518 |  | 804
35221818 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.071591 | 0.071591 | 0 | 0 | 0.071591 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS | 38.2576 | -120.529 |  | 1652
35264103 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.13011 | 0.13011 | 0 | 0 | 0.13011 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA | 38.6206 | -122.5857 |  | 1093
35243793 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5693 | -122.5676 |  | 1477
35211655 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | MENDOCINO | 39.2495 | -123.2081 |  | 1432
35225015 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.030114 | 0.030114 | 0 | 0.030114 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Simeon | SAN LUIS OBISPO | 35.6442 | -121.1875 |  | 1620
35225253 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | SANTA CRUZ | 37.0631 | -122.0333 |  | 2474
35206236 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.11212 | 0.11212 | 0 | 0 | 0.11212 | 0 | 0 | CC | Region 4 - Central Coast | Felton | SANTA CRUZ | 37.1115 | -122.049 |  | 2167
35037588 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0.17216 | 0 | 0 | HB | Region 1 - North Coast | Fortuna | HUMBOLDT | 40.5516 | -124.1125 |  | 1918
35083864 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | MI | Region 3 - Bay Area | Castro Valley | ALAMEDA | 37.7215 | -122.003 |  | 1914
35204835 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.18636 | 0.18636 | 0 | 0.18636 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.8361 | -121.917 |  | 281
35217691 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.083144 | 0.083144 | 0 | 0.083144 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.8329 | -121.9285 |  | 281
35207960 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10568 | 0.10568 | 0 | 0.10568 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.7832 | -121.8958 |  | 392
35038065 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.17973 | 0.17973 | 0 | 0.17973 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA | 39.4687 | -121.2462 |  | 793
35122388 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA | 39.4185 | -121.2563 |  | 793
35122390 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.031061 | 0.031061 | 0 | 0.031061 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | YUBA | 39.4233 | -121.2597 |  | 793
35211211 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13352 | 0.13352 | 0 | 0.13352 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.7285 | -121.5403 |  | 1578
35221249 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.5519 | -121.5068 |  | 771
35208045 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11155 | 0.11155 | 0 | 0.11155 | 0 | 0 | 0 | SI | Region 2 - North East | Rescue | El Dorado | 38.7604 | -121.01 |  | 586
35221659 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Ione | AMADOR | 38.3665 | -120.9291 |  | 744
35223265 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 1.2756 | 1.2756 | 0 | 1.2756 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Brentwood |  | 37.9299 | -121.8703 |  | 1367
35037880 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 39.0032 | -122.8175 |  | 2020
31255513 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Cloverdale | SONOMA | 38.8315 | -123.0098 |  | 680
35083755 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.059091 | 0.059091 | 0 | 0.059091 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.1935 | -119.7917 |  | 263
35211659 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | SI | Region 2 - North East | Camptonville | YUBA | 39.3894 | -121.0978 |  | 1590
35211656 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019318 | 0.019318 | 0 | 0.019318 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City |  | 39.3516 | -121.061 |  | 1077
35149360 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065152 | 0.065152 | 0 | 0.065152 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.885 | -122.5436 |  | 413
35223249 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN | 38.2597 | -122.855 |  | 965
35208019 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.037121 | 0.037121 | 0 | 0 | 0.037121 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA | 40.2983 | -122.4258 |  | 470
35204801 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.27462 | 0.27462 | 0 | 0.27462 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA | 40.313 | -122.4579 |  | 470
35204803 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.099621 | 0.099621 | 0 | 0 | 0.099621 | 0 | 0 | NV | Region 2 - North East | Cottonwood | TEHAMA | 40.3251 | -122.4357 |  | 470
35262345 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0.17803 | 0 | 0 | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3774 | -122.4352 |  | 554
35038650 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037879 | 0.037879 | 0 | 0.037879 | 0 | 0 | 0 | HB | Region 1 - North Coast | Covelo | Mendocino | 39.738 | -123.1621 |  | 1591
35238953 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 4.2356 | 4.2356 | 0 | 0 | 4.2356 | 0 | 0 | NV | Region 2 - North East | Greenville | PLUMAS | 40.1311 | -120.8634 |  | 1078
35246795 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.09053 | 0.09053 | 0 | 0.09053 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora |  | 38.0479 | -120.3492 |  | 1604
35221715 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | YO | Region 5 - Central Valley | Soulsbyville | TUOLUMNE | 37.9965 | -120.2635 |  | 1770
35046236 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | CC | Region 4 - Central Coast | Salinas | MONTEREY | 36.6181 | -121.7543 |  | 2367
35274991 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.6935 | -122.042 |  | 375
35162302 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11629 | 0.11629 | 0 | 0.11629 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | Shasta | 40.5988 | -122.1677 |  | 375
35204871 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.6772 | -122.0243 |  | 375
35204816 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050568 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.7009 | -121.993 |  | 375
35275963 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Shingletown | SHASTA | 40.51 | -122.0382 |  | 1086
35204808 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0.015152 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.6074 | -122.2415 |  | 100
35211254 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.030114 | 0.030114 | 0 | 0 | 0.030114 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.6174 | -122.2347 |  | 100
35137767 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.032576 | 0.032576 | 0 | 0.032576 | 0 | 0 | 0 | NV | Region 2 - North East | Bella Vista |  | 40.6374 | -122.2152 |  | 100
35237026 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.18769 | 0.18769 | 0 | 0 | 0.18769 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5064 | -122.2232 |  | 48
35144989 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0.073485 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5951 | -122.2369 |  | 48
35208066 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14205 | 0.14205 | 0 | 0 | 0.14205 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | SHASTA | 40.5062 | -122.2412 |  | 48
35205100 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.081818 | 0.081818 | 0 | 0.081818 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7473 | -120.8611 |  | 1699
35211802 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0.055871 | 0 | 0 | SI | Region 2 - North East | Diamond Springs | EL DORADO | 38.687 | -120.8406 |  | 2036
35211692 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.6612 | -120.8935 |  | 1031
35244155 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.6644 | -120.7763 |  | 632
35244157 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.6647 | -120.7764 |  | 632
35244159 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7181 | -120.9127 |  | 811
35208046 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA | 39.3752 | -121.225 |  | 650
35208012 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.1697 | 0.1697 | 0 | 0 | 0.1697 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA | 39.3986 | -121.2356 |  | 650
35208036 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.073485 | 0.073485 | 0 | 0.073485 | 0 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA | 39.3813 | -121.2068 |  | 650
35208044 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.20871 | 0.20871 | 0 | 0.20871 | 0 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA | 39.4103 | -121.2229 |  | 650
35208047 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0 | 0.02178 | 0 | 0 | SA | Region 2 - North East | Dobbins | YUBA | 39.3777 | -121.2491 |  | 193
35244117 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Alta | PLACER | 39.286 | -120.6932 |  | 2009
35083772 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15152 | 0.15152 | 0 | 0.15152 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Miramonte | Fresno | 36.7321 | -119.112 |  | 364
35211354 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065909 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | EL DORADO | 38.8238 | -120.049 |  | 2461
35037596 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.20265 | 0.20265 | 0 | 0.20265 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ferndale | HUMBOLDT | 40.4395 | -124.4062 |  | 1252
35208069 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7709 | -120.5996 |  | 2469
35225016 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.32614 | 0.32614 | 0 | 0.32614 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.2563 | -120.7044 |  | 2765
35150689 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.22045 | 0.22045 | 0 | 0.22045 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | MENDOCINO | 39.4657 | -123.7875 |  | 2581
35159826 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0 | 0.015152 | 0 | 0 | SO | Region 1 - North Coast | Cazadero | SONOMA | 38.5929 | -123.3009 |  | 1022
35037705 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.125 | 0.125 | 0 | 0.125 | 0 | 0 | 0 | HB | Region 1 - North Coast | Zenia | TRINITY | 40.1619 | -123.4504 |  | 1194
35149328 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Alderpoint | HUMBOLDT | 40.1781 | -123.6143 |  | 566
35149060 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0.020455 | 0 | 0 | HB | Region 1 - North Coast | Redcrest | HUMBOLDT | 40.3238 | -123.9266 |  | 1867
35045886 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.20587 | 0.20587 | 0 | 0.20587 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT | 40.2486 | -123.8131 |  | 1426
35149232 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16098 | 0.16098 | 0 | 0.16098 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt | 40.2507 | -123.831 |  | 1295
35150991 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0.072159 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT | 40.2188 | -123.8212 |  | 1429
35150549 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT | 40.1031 | -123.792 |  | 522
35150686 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | HB | Region 1 - North Coast | Westport | MENDOCINO | 39.8181 | -123.7838 |  | 415
35037708 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13277 | 0.13277 | 0 | 0.13277 | 0 | 0 | 0 | HB | Region 1 - North Coast | Leggett | MENDOCINO | 39.8453 | -123.7041 |  | 928
35037707 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.21837 | 0.21837 | 0 | 0 | 0.21837 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT | 40.0598 | -123.7285 |  | 1245
35150103 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.038447 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | HUMBOLDT | 40.1302 | -123.8559 |  | 1476
35037706 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.024811 | 0.024811 | 0 | 0 | 0.024811 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT | 40.125 | -123.9784 |  | 1149
35208094 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Garberville | HUMBOLDT | 40.1679 | -124.0858 |  | 1237
35208076 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.092235 | 0.092235 | 0 | 0 | 0.092235 | 0 | 0 | HB | Region 1 - North Coast | Piercy | MENDOCINO | 39.9875 | -123.9267 |  | 1777
35244151 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Piercy | MENDOCINO | 39.9778 | -123.9405 |  | 1777
35255487 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.21818 | 0.21818 | 0 | 0 | 0.21818 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | SONOMA | 38.6491 | -122.8541 |  | 940
35223270 |  | Idle Facilities | 2AF | APPR | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Geyserville | SONOMA | 38.7534 | -122.8254 |  | 668
35224947 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.3288 | -120.6721 |  | 1104
35211639 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1898 | -121.0711 |  | 1973
35211212 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.073864 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1376 | -121.1011 |  | 524
35211204 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1417 | -121.082 |  | 524
35009378 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.60379 | 0.60379 | 0 | 0 | 0.60379 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.1979 | -122.3465 |  | 2186
35244167 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Meadow Vista | PLACER | 38.9969 | -121.0593 |  | 2500
35037563 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Eureka | HUMBOLDT | 40.7546 | -124.1484 |  | 3118
35205102 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0.10985 | 0 | 0 | HB | Region 1 - North Coast | Eureka | HUMBOLDT | 40.7699 | -124.075 |  | 2462
35151050 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0041667 | 0.0041667 | 0 | 0.0041667 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0734 | -122.9666 |  | 439
35151026 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.10152 | 0.10152 | 0 | 0 | 0.10152 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | LAKE | 39.0684 | -122.967 |  | 439
35224893 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | CC | Region 4 - Central Coast | Carmel | MONTEREY | 36.5433 | -121.8847 |  | 2887
35211265 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16837 | 0.16837 | 0 | 0.16837 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.058 | -121.0257 |  | 1259
35149235 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0.16515 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.8612 | -122.6264 |  | 626
35151074 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.2964 | 0.2964 | 0 | 0.2964 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.9014 | -122.5753 |  | 181
35208097 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0.017045 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.8926 | -122.5433 |  | 181
35149249 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake |  | 38.8324 | -122.5358 |  | 440
35150641 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9248 | -122.5972 |  | 212
35151070 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054924 | 0.054924 | 0 | 0.054924 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.9073 | -122.6071 |  | 461
35037377 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.936 | -122.6055 |  | 461
35211257 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9487 | -122.6208 |  | 3295
35224519 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Hollister | SAN BENITO | 36.7152 | -121.347 |  | 2382
35149246 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0.18277 | 0 | 0 | HB | Region 1 - North Coast | Hopland | MENDOCINO | 38.9503 | -123.0881 |  | 110
35151000 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.039773 | 0.039773 | 0 | 0.039773 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hopland | MENDOCINO | 38.9889 | -123.0588 |  | 1099
35078377 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Granite Bay | PLACER | 38.7653 | -121.1515 |  | 2708
35275961 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.14148 | 0.14148 | 0 | 0 | 0.14148 | 0 | 0 | NV | Region 2 - North East | Igo | SHASTA | 40.4427 | -122.5277 |  | 350
35211698 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.074811 | 0.074811 | 0 | 0.074811 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA | 40.4479 | -122.3165 |  | 3114
35204821 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10322 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4356 | -122.3978 |  | 89
35204826 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.083333 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA | 40.4283 | -122.4024 |  | 267
35204796 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.018182 | 0.018182 | 0 | 0.018182 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville |  | 39.5928 | -121.2637 |  | 1566
35211630 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.060038 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | NV | Region 2 - North East | Forbestown | YUBA | 39.5104 | -121.2737 |  | 1201
35211753 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6066 | -122.4625 |  | 848
35037854 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.086553 | 0.086553 | 0 | 0.086553 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | MONTEREY | 36.133 | -121.2302 |  | 1814
35205028 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.9521 | -122.8395 |  | 168
35208093 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.882 | -122.6934 |  | 728
35037896 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.9332 | -122.7583 |  | 9
35150135 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.9266 | -122.7231 |  | 407
35262342 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16193 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | MARIN | 38.0537 | -122.5964 |  | 359
35223248 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.052083 | 0.052083 | 0 | 0.052083 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6185 | -121.7511 |  | 803
35255493 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.12614 | 0.12614 | 0 | 0 | 0.12614 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA | 37.6294 | -121.7632 |  | 803
35038684 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | MENDOCINO | 39.7297 | -123.5078 |  | 1293
35038648 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.049811 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0 | HB | Region 1 - North Coast | Laytonville |  | 39.6762 | -123.5055 |  | 1003
35149255 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.044508 | 0.044508 | 0 | 0.044508 | 0 | 0 | 0 | HB | Region 1 - North Coast | Branscomb |  | 39.6572 | -123.6316 |  | 1508
35132573 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.068182 | 0.068182 | 0 | 0 | 0.068182 | 0 | 0 | HB | Region 1 - North Coast | Dos Rios | MENDOCINO | 39.6876 | -123.4485 |  | 786
35208072 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Lincoln | PLACER | 38.8754 | -121.2617 |  | 1408
35244172 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.16326 | 0.16326 | 0 | 0 | 0.16326 | 0 | 0 | SI | Region 2 - North East | Lincoln | PLACER | 38.9514 | -121.2285 |  | 568
35221621 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.018939 | 0.018939 | 0 | 0.018939 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA | 37.1533 | -121.9852 |  | 3015
35247031 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.14981 | 0.14981 | 0 | 0 | 0.14981 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA | 37.1967 | -122.0038 |  | 1864
35126503 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.041667 | 0.041667 | 0 | 0 | 0.041667 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | SANTA CLARA | 37.1906 | -121.9848 |  | 2606
35037897 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Nice | LAKE | 39.0997 | -122.7991 |  | 2687
35198772 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.27652 | 0.27652 | 0 | 0.27652 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA | 37.5926 | -119.9625 |  | 679
35198773 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.22064 | 0.22064 | 0 | 0.22064 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5958 | -119.9582 |  | 679
35198774 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.012311 | 0.012311 | 0 | 0.012311 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  | 37.5986 | -119.9564 |  | 679
35198775 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.19223 | 0.19223 | 0 | 0.19223 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  | 37.5987 | -119.9566 |  | 679
35198776 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.051136 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5951 | -119.9586 |  | 679
35198777 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6005 | -119.9592 |  | 679
35198778 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15625 | 0.15625 | 0 | 0.15625 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6009 | -119.9597 |  | 679
35198779 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019886 | 0.019886 | 0 | 0.019886 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6023 | -119.9619 |  | 679
35198780 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.19242 | 0.19242 | 0 | 0.19242 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines |  | 37.6025 | -119.9621 |  | 679
35198781 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.13068 | 0.13068 | 0 | 0.13068 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA | 37.6044 | -119.9647 |  | 679
35198782 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.035985 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA | 37.6035 | -119.9668 |  | 679
35277148 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4926 | -119.9792 |  | 605
35083807 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.014583 | 0.014583 | 0 | 0 | 0.014583 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | MARIPOSA | 37.562 | -119.9679 |  | 700
35242663 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048295 | 0.048295 | 0 | 0.048295 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa |  | 37.5507 | -119.9509 |  | 700
35221744 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1447 | 0.1447 | 0 | 0.1447 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4893 | -119.8378 |  | 655
35221710 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013636 | 0.013636 | 0 | 0.013636 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa |  | 37.5059 | -120.0008 |  | 57
35083919 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.094886 | 0.094886 | 0 | 0.094886 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.396 | -119.8287 |  | 379
35083888 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.072348 | 0.072348 | 0 | 0 | 0.072348 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | AMADOR | 38.3594 | -120.7799 |  | 2054
35221764 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15473 | 0.15473 | 0 | 0.15473 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | AMADOR | 38.3521 | -120.7924 |  | 1330
35211249 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Fall River Mills | SHASTA | 41.0968 | -121.5541 |  | 1181
35207802 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0625 | 0.0625 | 0 | 0.0625 | 0 | 0 | 0 | NV | Region 2 - North East | Fall River Mills |  | 41.114 | -121.5687 |  | 1181
35038562 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0.054924 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | MENDOCINO | 39.3397 | -123.2189 |  | 1073
35223241 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | Portola Valley | SAN MATEO | 37.3567 | -122.2181 |  | 1917
35155226 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042045 | 0.042045 | 0 | 0 | 0.042045 | 0 | 0 | PN | Region 3 - Bay Area | La Honda | SAN MATEO | 37.3555 | -122.2666 |  | 620
35149134 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.098674 | 0.098674 | 0 | 0.098674 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.8576 | -122.7617 |  | 328
35150566 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0.031629 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.8086 | -122.7072 |  | 474
35151024 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1339 | 0.1339 | 0 | 0.1339 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7812 | -122.7076 |  | 474
35244105 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7672 | -122.6631 |  | 474
35149930 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.090341 | 0.090341 | 0 | 0.090341 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7865 | -122.6517 |  | 86
35150992 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.061932 | 0.061932 | 0 | 0.061932 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | LAKE | 38.7687 | -122.5915 |  | 8
35237664 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.47273 | 0.47273 | 0 | 0.47273 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hidden Valley Lake |  | 38.7706 | -122.5157 |  | 14
31211614 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.4361 | -122.9103 |  | 1468
35085362 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.026515 | 0.026515 | 0 | 0.026515 | 0 | 0 | 0 | SO | Region 1 - North Coast | Guerneville | SONOMA | 38.5542 | -123.0043 |  | 2084
35243374 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.61667 | 0.61667 | 0 | 0 | 0.61667 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA | 38.3601 | -122.1971 |  | 757
35221620 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SJ | Region 4 - Central Coast | Gilroy | SANTA CLARA | 37.0533 | -121.6625 |  | 854
35224941 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Morro Bay | SAN LUIS OBISPO | 35.3583 | -120.8253 |  | 2399
35225009 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.08428 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | LP | Region 4 - Central Coast | Los Osos | SAN LUIS OBISPO | 35.325 | -120.8119 |  | 2590
35217564 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Browns Valley | YUBA | 39.2864 | -121.3535 |  | 758
35244154 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.2717 | -121.1799 |  | 505
35208024 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.049811 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0 | SI | Region 2 - North East | Penn Valley | NEVADA | 39.233 | -121.2206 |  | 1812
35211601 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.035606 | 0.035606 | 0 | 0 | 0.035606 | 0 | 0 | SI | Region 2 - North East | Rough and Ready | NEVADA | 39.2305 | -121.1566 |  | 737
35208006 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.017614 | 0.017614 | 0 | 0 | 0.017614 | 0 | 0 | SI | Region 2 - North East | Rough and Ready | NEVADA | 39.2362 | -121.155 |  | 737
35211618 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Smartsville | NEVADA | 39.2156 | -121.2722 |  | 582
35186134 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.060417 | 0.060417 | 0 | 0 | 0.060417 | 0 | 0 | SI | Region 2 - North East | Penn Valley | NEVADA | 39.2099 | -121.2251 |  | 730
35083719 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.038636 | 0.038636 | 0 | 0.038636 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | Madera | 37.3717 | -119.6102 |  | 1903
35225441 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Bradley | MONTEREY | 35.8643 | -121.026 |  | 508
35204811 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.125 | 0.125 | 0 | 0 | 0.125 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6562 | -122.4233 |  | 1773
35211225 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6285 | -122.3936 |  | 968
35211643 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6201 | -122.4409 |  | 981
35262346 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.1411 | 0.1411 | 0 | 0 | 0.1411 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6194 | -122.4272 |  | 981
35262343 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0.05303 | 0 | 0 | NV | Region 2 - North East | Bella Vista | SHASTA | 40.6447 | -122.2377 |  | 49
35262344 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.049621 | 0.049621 | 0 | 0 | 0.049621 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6219 | -122.2562 |  | 49
35211263 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6357 | -122.2643 |  | 49
35204806 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.044318 | 0.044318 | 0 | 0 | 0.044318 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.5828 | -122.3125 |  | 255
35225318 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | SANTA BARBARA | 34.8111 | -120.2748 |  | 256
35225319 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.094697 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | SANTA BARBARA | 34.814 | -120.2785 |  | 256
35204902 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Anderson | SHASTA | 40.42 | -122.2553 |  | 1038
35119600 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.40947 | 0.40947 | 0 | 0.40947 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson |  | 40.4714 | -122.1602 |  | 283
35109767 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054356 | 0.054356 | 0 | 0.054356 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise |  | 39.7387 | -121.6123 |  | 1537
35254545 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.87273 | 0.87273 | 0 | 0.87273 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.7214 | -120.8474 |  | 138
35225437 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034659 | 0.034659 | 0 | 0.034659 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6605 | -120.7647 |  | 251
35208010 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER | 38.8801 | -121.1685 |  | 1016
35211210 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11364 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.8276 | -121.2251 |  | 385
35221768 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.19792 | 0.19792 | 0 | 0.19792 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | CALAVERAS | 37.9039 | -120.566 |  | 800
35083726 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048295 | 0.048295 | 0 | 0.048295 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne | 37.934 | -120.4427 |  | 835
35225011 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | Cambria | SAN LUIS OBISPO | 35.5452 | -121.0718 |  | 2433
35159821 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN | 38.2553 | -122.8195 |  | 888
35223225 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.11269 | 0.11269 | 0 | 0 | 0.11269 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | MARIN | 38.2558 | -122.8151 |  | 888
35221246 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Yorkville | MENDOCINO | 38.9374 | -123.309 |  | 417
35244145 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7308 | -120.7551 |  | 1761
35176816 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.14299 | 0.14299 | 0 | 0 | 0.14299 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7988 | -120.8164 |  | 1666
35208054 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0.14867 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7975 | -120.8281 |  | 1666
35135357 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.022348 | 0.022348 | 0 | 0.022348 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7312 | -120.7962 |  | 2992
35148124 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7402 | -120.7772 |  | 2430
35264102 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.10833 | 0.10833 | 0 | 0 | 0.10833 | 0 | 0 | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8094 | -120.867 |  | 1363
35135355 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.057008 | 0.057008 | 0 | 0.057008 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7902 | -120.772 |  | 904
35244112 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8621 | -120.8033 |  | 1646
35225543 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1858 | 0.1858 | 0 | 0.1858 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Bakersfield | KERN | 35.5027 | -118.8761 |  | 402
35244086 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Napa | NAPA | 38.4176 | -122.4763 |  | 951
35253133 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0878 | -122.6097 |  | 423
35244102 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0238 | -122.6802 |  | 345
35208096 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0.20663 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.069 | -122.6909 |  | 345
35225467 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0.023674 | 0 | 0 | CC | Region 4 - Central Coast | Watsonville | SANTA CRUZ | 37.012 | -121.7958 |  | 2387
35224942 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.010417 | 0.010417 | 0 | 0 | 0.010417 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.2953 | -120.6389 |  | 2146
35225006 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050947 | 0.050947 | 0 | 0.050947 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.1868 | -120.6991 |  | 1317
35225004 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.1854 | -120.6998 |  | 1317
35225423 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.0058712 | 0.0058712 | 0 | 0 | 0.0058712 | 0 | 0 | LP | Region 4 - Central Coast | San Ardo | MONTEREY | 36.0015 | -120.6447 |  | 469
35120413 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Fairfax | MARIN | 37.9797 | -122.6039 |  | 1837
35083913 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | MI | Region 3 - Bay Area | Castro Valley | ALAMEDA | 37.7374 | -122.032 |  | 1092
35215883 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0.10303 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | FRESNO | 36.6914 | -119.1303 |  | 195
35262347 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0.069318 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | FRESNO | 36.6995 | -119.1257 |  | 195
35221706 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.035795 | 0.035795 | 0 | 0.035795 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Badger | TULARE | 36.6132 | -118.9938 |  | 636
35221671 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.048864 | 0.048864 | 0 | 0.048864 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Woodlake | TULARE | 36.5921 | -119.0181 |  | 636
35221646 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Woodlake | TULARE | 36.6571 | -118.9583 |  | 636
35083879 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | FR | Region 5 - Central Valley | Orange Cove | TULARE | 36.6365 | -119.1962 |  | 337
35225003 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.015909 | 0.015909 | 0 | 0.015909 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Arroyo Grande | SAN LUIS OBISPO | 35.1094 | -120.3815 |  | 1109
31323810 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4598 | -122.7023 |  | 3369
35224441 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.19697 | 0.19697 | 0 | 0.19697 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | SANTA BARBARA | 34.6248 | -119.9848 |  | 153
35275478 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0.15852 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | SANTA CLARA | 37.2476 | -122.0791 |  | 2354
35150987 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara | 37.239 | -122.0699 |  | 2145
35221770 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | SANTA CLARA | 37.2371 | -122.0373 |  | 2627
35207979 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.0948 | -120.9698 |  | 2201
35205036 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.051326 | 0.051326 | 0 | 0.051326 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax |  | 39.08 | -120.9599 |  | 1581
35273069 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.20947 | 0.20947 | 0 | 0 | 0.20947 | 0 | 0 | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1778 | -120.8918 |  | 2022
35205038 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.10227 | 0.10227 | 0 | 0 | 0.10227 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.1074 | -120.9492 |  | 1829
35083743 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.039394 | 0.039394 | 0 | 0.039394 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Clovis | Fresno | 36.9783 | -119.6277 |  | 247
35205118 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Rescue | EL DORADO | 38.6944 | -120.9795 |  | 240
35250938 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.22557 | 0.22557 | 0 | 0 | 0.22557 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.6385 | -120.9907 |  | 424
35106410 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042803 | 0.042803 | 0 | 0.042803 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.6592 | -120.9554 |  | 2298
35208079 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0.15057 | 0 | 0 | SI | Region 2 - North East | Lotus | EL DORADO | 38.8055 | -120.9274 |  | 2116
35244173 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7888 | -120.9206 |  | 2116
35081139 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15246 | 0.15246 | 0 | 0.15246 | 0 | 0 | 0 | SI | Region 2 - North East | Rescue |  | 38.7111 | -120.9793 |  | 578
35207972 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.7414 | -120.9326 |  | 227
35211743 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.6795 | -120.9469 |  | 1240
35211237 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5195 | -122.361 |  | 579
35223207 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | San Bruno | SAN MATEO | 37.6247 | -122.4471 |  | 2588
35275477 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.043561 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soledad | MONTEREY | 36.4295 | -121.2649 |  | 623
35223204 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SO | Region 1 - North Coast | Sonoma | SONOMA | 38.3002 | -122.4057 |  | 720
35211234 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15928 | 0.15928 | 0 | 0.15928 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | PLACER | 39.3061 | -120.6766 |  | 1563
35277146 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.13598 | 0.13598 | 0 | 0 | 0.13598 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | TUOLUMNE | 38.1406 | -120.0581 |  | 2788
35221765 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2531 | -120.3592 |  | 2810
35275962 |  | Idle Facilities | 2BF | PEND | Permitting/Dependency | 0 | 0 | 0.0056818 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.7096 | -122.3366 |  | 1828
35177215 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1892 | 0.1892 | 0 | 0.1892 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6969 | -122.3392 |  | 1828
35204831 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16439 | 0.16439 | 0 | 0.16439 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6952 | -122.3405 |  | 1737
35204830 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045833 | 0.045833 | 0 | 0 | 0.045833 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.7018 | -122.2322 |  | 1251
35211694 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Redding | SHASTA | 40.6992 | -122.23 |  | 1251
35204820 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.058523 | 0.058523 | 0 | 0.058523 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6835 | -122.2448 |  | 628
35199323 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.24072 | 0.24072 | 0 | 0.24072 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Mount Hamilton |  | 37.3476 | -121.7275 |  | 1228
35207810 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.1678 | 0.1678 | 0 | 0 | 0.1678 | 0 | 0 | NV | Region 2 - North East | Chico | BUTTE | 39.9088 | -121.7178 |  | 1137
35221199 |  | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Chico | BUTTE | 39.8868 | -121.7519 |  | 1137
35244018 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Norden | PLACER | 39.3149 | -120.4577 |  | 2630
35083773 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9912 | -120.3715 |  | 3142
35083737 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.80947 | 0.80947 | 0 | 0.80947 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN | 34.8884 | -118.9403 |  | 691
35083733 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN | 34.8446 | -118.8761 |  | 583
35083812 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.045076 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN | 34.8273 | -118.885 |  | 583
35135297 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.098864 | 0.098864 | 0 | 0.098864 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Margarita | SAN LUIS OBISPO | 35.3707 | -120.4072 |  | 133
35225409 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1072 | 0.1072 | 0 | 0.1072 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Templeton | SAN LUIS OBISPO | 35.5119 | -120.6445 |  | 955
35079416 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.055492 | 0.055492 | 0 | 0.055492 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Creston | SAN LUIS OBISPO | 35.4899 | -120.5388 |  | 864
35217692 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.0862 | -122.4538 |  | 383
35204877 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1167 | -123.2146 |  | 1369
35038557 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1731 | -123.1558 |  | 1030
35151005 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0.28636 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.185 | -122.9886 |  | 259
31157088 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.24053 | 0.24053 | 0 | 0 | 0.24053 | 0 | 0 | SA | Region 2 - North East | Fairfield | SOLANO | 38.3154 | -122.0016 |  | 42
35208021 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.20739 | 0.20739 | 0 | 0 | 0.20739 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3753 | -122.0359 |  | 64
31156970 |  | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SA | Region 2 - North East | Vacaville | SOLANO | 38.3868 | -122.0006 |  | 190
35207931 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.042424 | 0.042424 | 0 | 0.042424 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3791 | -121.9972 |  | 500
35083893 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0.067424 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA | 37.6459 | -121.7137 |  | 324
35083687 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050189 | 0.050189 | 0 | 0.050189 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | ALAMEDA | 37.5923 | -121.6813 |  | 324
35083695 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.1661 | 0.1661 | 0 | 0.1661 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.5742 | -121.6777 |  | 324
35229381 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.11477 | 0.11477 | 0 | 0.11477 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Pebble Beach | MONTEREY | 36.5936 | -121.9216 |  | 3216
35143764 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023485 | 0.023485 | 0 | 0 | 0.023485 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.3503 | -121.7728 |  | 966
35275479 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Manton | TEHAMA | 40.4236 | -121.8237 |  | 532
35205037 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.082576 | 0.082576 | 0 | 0 | 0.082576 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.07 | -120.9579 |  | 1379
35211657 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.0636 | -121.0002 |  | 1379
35211297 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15682 | 0.15682 | 0 | 0 | 0.15682 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.02 | -120.944 |  | 1801
35211671 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Colfax | PLACER | 39.0289 | -121.0036 |  | 2536
35079380 |  | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.21951 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | CALAVERAS | 38.2766 | -120.563 |  | 1206
35221997 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.043561 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3546 | -120.5022 |  | 1664
35221998 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.10985 | 0.10985 | 0 | 0.10985 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3545 | -120.504 |  | 1664
35221807 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3496 | -120.5094 |  | 1664
35207962 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA | 40.6587 | -121.8939 |  | 678
35204813 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.06875 | 0.06875 | 0 | 0 | 0.06875 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA | 40.6834 | -121.949 |  | 820
35204814 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0.21023 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA | 40.6759 | -121.971 |  | 820
35208023 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037311 | 0.037311 | 0 | 0.037311 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.7054 | -121.9102 |  | 820
35275960 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Oak Run | SHASTA | 40.7044 | -121.9215 |  | 820
35217667 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.43371 | 0.43371 | 0 | 0 | 0.43371 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA | 40.588 | -121.9245 |  | 685
35204810 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East | Whitmore | SHASTA | 40.6224 | -121.9955 |  | 685
35174308 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.069697 | 0.069697 | 0 | 0.069697 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.5867 | -121.935 |  | 685
35207963 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042992 | 0.042992 | 0 | 0.042992 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6302 | -121.9057 |  | 1481
35207965 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | SHASTA | 40.3884 | -122.9869 |  | 1125
35038672 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013826 | 0.013826 | 0 | 0.013826 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.493 | -123.1895 |  | 782
35038671 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.5498 | -123.381 |  | 1161
35132574 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019697 | 0.019697 | 0 | 0.019697 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | MENDOCINO | 39.3877 | -123.3241 |  | 1264
35038668 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.343 | -123.349 |  | 778
35151029 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.8113 | -123.4962 |  | 1474
35149294 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.082955 | 0.082955 | 0 | 0.082955 | 0 | 0 | 0 | HB | Region 1 - North Coast | Salyer | HUMBOLDT | 40.8032 | -123.5563 |  | 1598
35078722 |  | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER | 38.8908 | -121.1358 |  | 430
35078723 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.074432 | 0.074432 | 0 | 0.074432 | 0 | 0 | 0 | SI | Region 2 - North East | Newcastle | PLACER | 38.8921 | -121.1444 |  | 430
35242865 |  | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.4126 | -122.3299 |  | 1376
35078735 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.062879 | 0.062879 | 0 | 0 | 0.062879 | 0 | 0 | NV | Region 2 - North East | Oroville | BUTTE | 39.4969 | -121.3903 |  | 905
35079389 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.14015 | 0.14015 | 0 | 0.14015 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst |  | 37.2946 | -119.6252
35083712 |  | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.13769 | 0.13769 | 0 | 0 | 0.13769 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | TUOLUMNE | 38.0552 | -120.2327
35083923 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.079167 | 0.079167 | 0 | 0.079167 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | KERN | 34.8792 | -118.9008
35149472 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.080492 | 0.080492 | 0 | 0.080492 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.8811 | -122.6115
35150617 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.022727 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willow Creek | HUMBOLDT | 40.943 | -123.6884
35204864 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.053977 | 0.053977 | 0 | 0.053977 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | TEHAMA | 40.3344 | -122.8489
35205115 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | SI | Region 2 - North East | Lotus | EL DORADO | 38.802 | -120.9155
35208075 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.040341 | 0.040341 | 0 | 0.040341 | 0 | 0 | 0 | SI | Region 2 - North East | North San Juan | NEVADA | 39.3258 | -121.1483
35208098 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.029356 | 0.029356 | 0 | 0.029356 | 0 | 0 | 0 | HB | Region 1 - North Coast | Redway | HUMBOLDT | 40.1218 | -123.8347
35209864 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.036553 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.8083 | -120.8992
35211232 |  | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | NEVADA | 39.0129 | -121.1049
35211241 |  | Idle Facilities | 2AF | CONS | In-Construction | 0 | 0 | 0.074811 | 0.074811 | 0 | 0 | 0.074811 | 0 | 0 | SI | Region 2 - North East | Placerville | EL DORADO | 38.6841 | -120.7566
35211277 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.014394 | 0.014394 | 0 | 0.014394 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley |  | 39.0854 | -121.1369
35221635 |  | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.082955 | 0.082955 | 0 | 0.082955 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Clovis |  | 36.9298 | -119.4336
35225434 |  | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.073295 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Margarita | SAN LUIS OBISPO | 35.3516 | -120.4935
35185022 |  | Other | 06I | FICL | Post-Construction | 0 | 0.41705 | 0 | 0.41705 | 0 | 0.41705 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | NEVADA | 39.3633 | -120.7915 |  | 1700
35080162 |  | Other | 06H | CONS | In-Construction | 0 | 1.4413 | 0 | 1.4413 | 0 | 1.2462 | 0.19508 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | Mendocino | 39.2143 | -123.1889 |  | 1256
35094513 |  | Base SH | 08W | UNSC | Ready for Construction | 0.032576 | 1.7771 | 0 | 1.8097 | 0 | 0 | 1.8097 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras |  |  |  | 2712 | Pre | Tier 3
35146106 |  | Other | 06H | DOCC | Post-Construction | 0 | 3.621 | 0 | 3.621 | 0 | 3.621 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | SAN LUIS OBISPO | 35.6961 | -120.7404 |  | 229
35297697 |  | Fire Rebuild | 08W | ESTS | Estimating | 0.014773 | 0 | 0 | 0.014773 | 0 | 0 | 0.014773 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | FRRB | Tier 2

## Status
SAP Status | Status
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | In-Construction | *
DOCC | Post-Construction | *
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles

## ProjectType
ProjectType | Description
CWSP 2022-2023 | Community Wildfire Safety Program for projects aimed for 2022-2023
ECOP | EC Tag Optimization
ECOP - Top 20% | EC Tag Optimization in the top 20% of the 2021 risk model
FRRB - OH – 2021 | Fire Rebuild - Overhead Hardening
FRRB - REMG – 2021 | Fire Rebuild - Remote Grid Projects
FRRB - UG – 2021 | Fire Rebuild - Underground Hardening
PRE | Projects that had poles in the ground and construction had begun, based on 2018 risk model
PSPS - Community Resiliency | Public Safety Power Shutoff projects
PSPS – Scoped | Public Safety Power Shutoff projects that had been scoped, based on 2018 risk model
PSS Approved | Public Safety Specialists approved projects
Remote Grid | Remote Grid projects
Remote Grid Pilot | Remote Grid projects part of the Pilot program
Storm Rebuild | Storm Rebuild projects
Top 20% MAVF CPZ | Top 20% of Multi-Attribute Value Function Circuit Protection Zones based on the 2021 risk model
Top 250 miles | Top 250 miles based on the 2021 risk model
Top 50 Miles | Top 50 miles based on the 2021 risk model