## Summary
Substation LC Notifications - Open as of June 7, 2022
Notification Workdown Schedule
| 2022 |  |  | Total
Area | Q2 | Q3 | Q4
Bay Area | 23 | 54 | 54 | 131
Central Coast | 2 | 58 | 16 | 76
North Coast | 341 | 297 | 133 | 771
North Valley | 43 | 157 | 33 | 233
South Valley | 96 | 104 | 53 | 253
Total Notifications | 505 | 670 | 289 | 1464
Substation LC Notifications - Open as of June 7, 2022
Projected Resources for Workdown Schedule
| 2022 |  |  | Average
Area | Q2 | Q3 | Q4
Bay Area | 0.86132 | 2.3324 | 2.1372 | 1.777
Central Coast | 0.092809 | 3.0167 | 0.74247 | 1.284
North Coast | 14.6639 | 12.9257 | 5.749 | 11.1129
North Valley | 1.681 | 6.4941 | 1.347 | 3.174
South Valley | 4.9535 | 4.5876 | 2.6221 | 4.0544
Total Resources | 22.2526 | 29.3564 | 12.5978 | 21.4023

## Open HFTD Tags
[6 empty] | Total OPEN Notifications as of June 7, 2022 | 1464
Category | Notification | Priority | Notification Date | Notif Status | HFTD | Latitude | Longitude | Remediation Due Date
Sub | 123189325 | E | 2019-04-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2021-01-01
Sub | 117269300 | E | 2019-05-01 | OPEN | T2/3A | 37.9163 | -122.3031 | 2021-01-01
Sub | 117637881 | E | 2019-07-24 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2021-01-01
Sub | 119052229 | E | 2019-09-18 | OPEN | T2/3A | 40.6778 | -122.3498 | 2021-01-01
Sub | 117224616 | E | 2019-04-24 | OPEN | T2/3A | 35.0084 | -120.4532 | 2021-01-01
Sub | 119114121 | E | 2020-06-05 | OPEN | Tier 3 - Extreme | 39.2147 | -120.8093 | 2021-01-01
Sub | 119667038 | E | 2020-06-27 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2021-01-01
Sub | 114474703 | F | 2018-04-05 | OPEN | T2/3A | 37.5842 | -120.2712 | 2022-01-01
Sub | 119675853 | F | 2020-08-26 | OPEN | T2/3A | 37.9163 | -122.3031 | 2022-01-02
Sub | 119045299 | E | 2020-05-19 | OPEN | T2/3A | 40.718 | -122.9343 | 2022-01-01
Sub | 119052181 | F | 2020-05-21 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-01-02
Sub | 119531777 | E | 2020-05-27 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2022-01-01
Sub | 119530183 | E | 2020-05-30 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2022-01-01
Sub | 119530189 | E | 2020-05-30 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2022-01-01
Sub | 119114120 | E | 2020-06-05 | OPEN | T2/3A | 38.9035 | -121.0698 | 2022-01-01
Sub | 119753548 | E | 2020-06-08 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-01-01
Sub | 119753542 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-01-01
Sub | 119147095 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-01-01
Sub | 119753986 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-01-01
Sub | 119147735 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 35.5593 | -118.9576 | 2022-01-01
Sub | 119147545 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.9088 | -119.0877 | 2022-01-01
Sub | 119147290 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-01-01
Sub | 119147055 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-01-01
Sub | 119147215 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-01-01
Sub | 119147298 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.8882 | -119.1591 | 2022-01-01
Sub | 119718500 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.8882 | -119.1591 | 2022-01-01
Sub | 119147348 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-01-01
Sub | 119147592 | E | 2020-06-11 | OPEN | Tier 2 - Elevated | 36.9089 | -119.0884 | 2022-01-01
Sub | 119590767 | E | 2020-06-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590768 | E | 2020-06-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590766 | E | 2020-06-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590765 | E | 2020-06-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119591110 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119591579 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119591097 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119591233 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119591570 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590920 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590960 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590965 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590967 | E | 2020-06-19 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119550150 | E | 2020-06-24 | OPEN | T2/3A | 37.8266 | -122.2164 | 2022-01-01
Sub | 119590861 | E | 2020-06-25 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590863 | E | 2020-06-25 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119590769 | E | 2020-06-25 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119769633 | E | 2020-07-02 | OPEN | Tier 3 - Extreme | 38.4289 | -122.5933 | 2022-01-01
Sub | 119742911 | E | 2020-07-07 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119742989 | E | 2020-07-07 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119728478 | E | 2020-07-07 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119803616 | E | 2020-07-08 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119781937 | E | 2020-07-11 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119781938 | E | 2020-07-11 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119729272 | E | 2020-07-13 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2022-01-01
Sub | 119887609 | E | 2020-07-17 | OPEN | T2/3A | 40.3025 | -121.227 | 2022-01-01
Sub | 119896147 | E | 2020-07-17 | OPEN | T2/3A | 40.3025 | -121.227 | 2022-01-01
Sub | 119896091 | E | 2020-07-17 | OPEN | T2/3A | 40.3025 | -121.227 | 2022-01-01
Sub | 119832433 | E | 2020-07-25 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-01-01
Sub | 120041631 | E | 2020-08-03 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 120041144 | E | 2020-08-06 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 120041348 | E | 2020-08-06 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119968830 | E | 2020-08-08 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119968832 | E | 2020-08-08 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 121406611 | E | 2021-05-18 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2022-01-01
Sub | 121406612 | E | 2021-05-18 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2022-01-01
Sub | 119661221 | E | 2020-08-22 | OPEN | T2/3A | 35.0084 | -120.4532 | 2022-01-01
Sub | 119754582 | E | 2020-09-10 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2022-01-01
Sub | 119754710 | E | 2020-09-10 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2022-01-01
Sub | 119754714 | E | 2020-09-10 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2022-01-01
Sub | 119758248 | E | 2020-09-12 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2022-01-01
Sub | 121408603 | E | 2020-10-07 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119966934 | E | 2020-10-30 | OPEN | Tier 2 - Elevated | 38.7309 | -120.7836 | 2022-01-01
Sub | 119968809 | E | 2020-10-31 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 119968808 | E | 2020-10-31 | OPEN | T2/3A | 38.0768 | -122.5404 | 2022-01-01
Sub | 121837629 | E | 2021-08-03 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2022-01-01
Sub | 119979299 | E | 2020-11-03 | OPEN | T2/3A | 35.0084 | -120.4532 | 2022-01-01
Sub | 120191465 | E | 2020-12-14 | OPEN | Tier 2 - Elevated | 40.1028 | -123.793 | 2022-01-01
Sub | 117087069 | E | 2019-04-09 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-01-01
Sub | 117443033 | E | 2019-06-12 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-01-01
Sub | 117443967 | E | 2019-06-12 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2022-01-01
Sub | 117123811 | F | 2019-04-10 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 117613275 | F | 2019-07-17 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 112501828 | F | 2017-01-10 | OPEN | T2/3A | 41.0565 | -123.6823 | 2023-01-01
Sub | 118476828 | F | 2020-01-28 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 118476840 | F | 2020-01-28 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 118476829 | F | 2020-01-28 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 120491247 | E | 2021-02-01 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 120508322 | E | 2021-02-01 | OPEN | T2/3A | 39.7607 | -121.6189 | 2023-01-01
Sub | 120502630 | E | 2021-02-05 | OPEN | Tier 2 - Elevated | 40.1028 | -123.793 | 2023-01-01
Sub | 120536047 | E | 2021-02-08 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2023-01-01
Sub | 120536048 | E | 2021-02-11 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2023-01-01
Sub | 120585861 | E | 2021-02-27 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120594505 | E | 2021-03-02 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120594682 | E | 2021-03-02 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120627210 | E | 2021-03-09 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120628975 | E | 2021-03-09 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120636441 | E | 2021-03-06 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2023-01-01
Sub | 122920982 | B | 2022-01-12 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2022-05-01
Sub | 120657257 | E | 2021-03-14 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2023-01-01
Sub | 120653844 | E | 2021-03-17 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2023-01-01
Sub | 120659578 | E | 2021-03-17 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2023-01-01
Sub | 120659534 | E | 2021-03-17 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2023-01-01
Sub | 120655232 | E | 2021-03-17 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 120659731 | E | 2021-03-17 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2023-01-01
Sub | 123169817 | E | 2022-03-22 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2023-01-01
Sub | 120685687 | E | 2021-03-23 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 120732596 | E | 2021-03-29 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120732597 | E | 2021-03-29 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120747188 | E | 2021-03-30 | OPEN | Tier 3 - Extreme | 39.9053 | -121.3455 | 2023-01-01
Sub | 120756836 | E | 2021-03-30 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2023-01-01
Sub | 120743346 | E | 2021-03-31 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 121999448 | E | 2021-04-01 | OPEN | T2/3A | 39.5929 | -122.5429 | 2023-01-01
Sub | 120747763 | E | 2021-04-02 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120747495 | E | 2021-04-02 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120743024 | E | 2021-04-02 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120755278 | E | 2021-04-05 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2023-01-01
Sub | 120752210 | E | 2021-04-05 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120754712 | E | 2021-04-05 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2023-01-01
Sub | 120757847 | E | 2021-04-05 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120755344 | E | 2021-04-05 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2023-01-01
Sub | 120754404 | E | 2021-04-05 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120754379 | E | 2021-04-05 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120759031 | E | 2021-04-06 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120757721 | E | 2021-04-06 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120759102 | E | 2021-04-06 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 120765780 | E | 2021-04-06 | OPEN | Tier 3 - Extreme | 39.9053 | -121.3455 | 2023-01-01
Sub | 120893817 | E | 2021-04-07 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120762005 | E | 2021-04-07 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120814309 | E | 2021-04-08 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120857116 | E | 2021-04-08 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 120784627 | E | 2021-04-08 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120804703 | E | 2021-04-09 | OPEN | T2/3A | 35.4655 | -120.6715 | 2023-01-01
Sub | 120815822 | E | 2021-04-09 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120819054 | E | 2021-04-09 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120788049 | E | 2021-04-09 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120820774 | E | 2021-04-10 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120820826 | E | 2021-04-10 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120819431 | E | 2021-04-10 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 120808302 | E | 2021-04-10 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 120812637 | E | 2021-04-12 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 120862064 | E | 2021-04-12 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 121334298 | E | 2021-04-12 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 120808506 | E | 2021-04-12 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 122609084 | E | 2022-01-12 | OPEN | Tier 2 - Elevated | 40.0854 | -121.1479 | 2023-01-01
Sub | 120793464 | E | 2021-04-12 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120793967 | E | 2021-04-12 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120803771 | E | 2021-04-12 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120804185 | E | 2021-04-13 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120807782 | E | 2021-04-13 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120813783 | E | 2021-04-14 | OPEN | Tier 3 - Extreme | 39.9053 | -121.3455 | 2023-01-01
Sub | 120813711 | E | 2021-04-14 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120836785 | E | 2021-04-14 | OPEN | Tier 3 - Extreme | 39.8262 | -121.4096 | 2023-01-01
Sub | 120833379 | E | 2021-04-14 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120836786 | E | 2021-04-14 | OPEN | Tier 3 - Extreme | 39.8262 | -121.4096 | 2023-01-01
Sub | 120837470 | E | 2021-04-14 | OPEN | Tier 3 - Extreme | 39.8262 | -121.4096 | 2023-01-01
Sub | 120848137 | E | 2021-04-14 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120834286 | E | 2021-04-15 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120828519 | E | 2021-04-16 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2023-01-01
Sub | 120834138 | E | 2021-04-16 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120834135 | E | 2021-04-16 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120838031 | E | 2021-04-16 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120842393 | E | 2021-04-17 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 120837368 | E | 2021-04-18 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2023-01-01
Sub | 120838251 | E | 2021-04-18 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 120881280 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 39.6774 | -121.4916 | 2023-01-01
Sub | 120844327 | E | 2021-04-19 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2023-01-01
Sub | 120848778 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 39.7233 | -121.4697 | 2023-01-01
Sub | 120850008 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120850201 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120850355 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120848771 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 39.7233 | -121.4697 | 2023-01-01
Sub | 120881259 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 39.6774 | -121.4916 | 2023-01-01
Sub | 120881282 | E | 2021-04-19 | OPEN | Tier 3 - Extreme | 39.6774 | -121.4916 | 2023-01-01
Sub | 120990750 | E | 2021-04-19 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 120881258 | E | 2021-04-19 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 120859305 | E | 2021-04-20 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120872581 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120879983 | E | 2021-04-20 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120859308 | E | 2021-04-20 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120879984 | E | 2021-04-20 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120879985 | E | 2021-04-20 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120863462 | E | 2021-04-21 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120872288 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120872286 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120860410 | E | 2021-04-21 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120860412 | E | 2021-04-21 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 120865950 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120866667 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120879989 | E | 2021-04-21 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120879988 | E | 2021-04-21 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120861669 | E | 2021-04-21 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2023-01-01
Sub | 120871518 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120908386 | E | 2021-04-21 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120866035 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120866124 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120866741 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120871894 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120873220 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2023-01-01
Sub | 120871761 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120871914 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2023-01-01
Sub | 120875395 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120871517 | E | 2021-04-21 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120877324 | E | 2021-04-22 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120877325 | E | 2021-04-22 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2023-01-01
Sub | 120905370 | E | 2021-04-22 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120911849 | E | 2021-04-22 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120871760 | E | 2021-04-22 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2023-01-01
Sub | 120908383 | E | 2021-04-22 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120908632 | E | 2021-04-22 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120873221 | E | 2021-04-22 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120879568 | E | 2021-04-23 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120878867 | E | 2021-04-23 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120879567 | E | 2021-04-23 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120881079 | E | 2021-04-23 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120878986 | E | 2021-04-23 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120879986 | E | 2021-04-23 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120881406 | E | 2021-04-24 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120881420 | E | 2021-04-24 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 120887904 | E | 2021-04-24 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120905341 | E | 2021-04-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120939767 | E | 2021-04-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120904260 | E | 2021-04-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120911848 | E | 2021-04-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 120896525 | E | 2021-04-26 | OPEN | Tier 3 - Extreme | 39.5752 | -121.3057 | 2023-01-01
Sub | 120887909 | E | 2021-04-26 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120887972 | E | 2021-04-26 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120896521 | E | 2021-04-26 | OPEN | Tier 3 - Extreme | 39.5752 | -121.3057 | 2023-01-01
Sub | 120887976 | E | 2021-04-26 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120894871 | E | 2021-04-27 | OPEN | Tier 2 - Elevated | 35.3205 | -120.6931 | 2023-01-01
Sub | 120894636 | E | 2021-04-27 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120898726 | E | 2021-04-28 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120898728 | E | 2021-04-28 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120894639 | E | 2021-04-27 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120892965 | E | 2021-04-27 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 120899050 | E | 2021-04-28 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120937948 | E | 2021-04-28 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2023-01-01
Sub | 120905346 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120926611 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 36.1631 | -118.707 | 2023-01-01
Sub | 120903509 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120925677 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2023-01-01
Sub | 120926516 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 36.1631 | -118.707 | 2023-01-01
Sub | 120903442 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120903800 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120915297 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120925676 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2023-01-01
Sub | 120903343 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120914957 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120925002 | E | 2021-04-29 | OPEN | Tier 2 - Elevated | 36.1631 | -118.707 | 2023-01-01
Sub | 120911893 | E | 2021-04-30 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120911896 | E | 2021-04-30 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120908305 | E | 2021-04-30 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120908308 | E | 2021-04-30 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 120909827 | E | 2021-04-30 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120924872 | E | 2021-05-03 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120937302 | E | 2021-05-04 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 121324775 | E | 2021-05-04 | OPEN | Tier 2 - Elevated | 39.3309 | -121.1916 | 2023-01-01
Sub | 120974348 | E | 2021-05-04 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121187142 | E | 2021-05-04 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121319902 | E | 2021-05-10 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120939981 | E | 2021-05-05 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120939948 | E | 2021-05-05 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120941222 | E | 2021-05-05 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120941162 | E | 2021-05-05 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121187009 | E | 2021-05-05 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 120950008 | E | 2021-05-06 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120950334 | E | 2021-05-06 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121037880 | E | 2021-05-06 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 121325339 | E | 2021-05-06 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 121325443 | E | 2021-05-06 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 121325388 | E | 2021-05-06 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 120950337 | E | 2021-05-07 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 120952280 | E | 2021-05-07 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120952850 | E | 2021-05-07 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 120949705 | E | 2021-05-07 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 121315779 | E | 2021-05-07 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121337695 | E | 2021-05-07 | OPEN | T2/3A | 39.9392 | -120.9483 | 2023-01-01
Sub | 121337693 | E | 2021-05-07 | OPEN | T2/3A | 39.9392 | -120.9483 | 2023-01-01
Sub | 120949467 | E | 2021-05-07 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 120950853 | E | 2021-05-07 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 120952235 | E | 2021-05-07 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121337694 | E | 2021-05-07 | OPEN | T2/3A | 39.9392 | -120.9483 | 2023-01-01
Sub | 121317170 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121315978 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121315979 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121317008 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121317172 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121317178 | E | 2021-05-08 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121347895 | E | 2021-05-10 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121350262 | E | 2021-05-10 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 122498965 | E | 2021-05-10 | OPEN | Tier 2 - Elevated | 40.0854 | -121.1479 | 2023-01-01
Sub | 122498967 | E | 2021-05-10 | OPEN | Tier 2 - Elevated | 40.0854 | -121.1479 | 2023-01-01
Sub | 122498969 | E | 2021-05-10 | OPEN | Tier 2 - Elevated | 40.0854 | -121.1479 | 2023-01-01
Sub | 121325006 | E | 2021-05-11 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121332930 | E | 2021-05-11 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 121325053 | E | 2021-05-11 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121329767 | E | 2021-05-13 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121332733 | E | 2021-05-11 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 121336246 | E | 2021-05-11 | OPEN | T2/3A | 39.4056 | -123.3271 | 2023-01-01
Sub | 121357571 | E | 2021-05-14 | OPEN | Tier 3 - Extreme | 39.3318 | -121.1014 | 2023-01-01
Sub | 121357439 | E | 2021-05-14 | OPEN | Tier 3 - Extreme | 39.3318 | -121.1014 | 2023-01-01
Sub | 121367295 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121367440 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121367444 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121364861 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121364867 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121367640 | E | 2021-05-15 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121362183 | E | 2021-05-17 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121365514 | E | 2021-05-17 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121365949 | E | 2021-05-17 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121343239 | E | 2021-05-17 | OPEN | T2/3A | 38.9014 | -121.0879 | 2023-01-01
Sub | 121365946 | E | 2021-05-17 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121351683 | E | 2021-05-17 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2023-01-01
Sub | 121365518 | E | 2021-05-17 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121365940 | E | 2021-05-17 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 121362187 | E | 2021-05-18 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121373037 | E | 2021-05-18 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 121454344 | E | 2021-05-18 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2023-01-01
Sub | 121366506 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 121366589 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 121372706 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 121371484 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121371487 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121366469 | E | 2021-05-19 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 121369877 | E | 2021-05-19 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121374714 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121376166 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121384270 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385205 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385342 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379456 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121383257 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121384272 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121374596 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121384277 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385209 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121373132 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121374212 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121374711 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121383330 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121384872 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379514 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385344 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385996 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121386550 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121379459 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379499 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121385991 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379474 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379519 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121379641 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121384874 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 121386152 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121386336 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121386334 | E | 2021-05-21 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121386338 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121389018 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 123397385 | E | 2022-04-22 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2023-01-01
Sub | 121381410 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121386553 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121391150 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121398535 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121383254 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121386332 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121381627 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121389206 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121398533 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121398534 | E | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121408770 | E | 2021-05-22 | OPEN | T2/3A | 35.3822 | -120.0605 | 2023-01-01
Sub | 121395869 | E | 2021-05-24 | OPEN | Tier 3 - Extreme | 39.3318 | -121.1014 | 2023-01-01
Sub | 121391331 | E | 2021-05-24 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 121391383 | E | 2021-05-24 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 121432226 | E | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121434123 | E | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121398531 | E | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121398569 | E | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2023-01-01
Sub | 121446211 | E | 2021-05-24 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121431623 | E | 2021-05-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121437018 | E | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121419858 | E | 2021-05-25 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121421680 | E | 2021-05-25 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121427011 | E | 2021-05-25 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121436134 | E | 2021-05-26 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121425566 | E | 2021-05-26 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121444169 | E | 2021-05-26 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121419628 | E | 2021-05-26 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2023-01-01
Sub | 121419853 | E | 2021-05-26 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2023-01-01
Sub | 121432220 | E | 2021-05-26 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121442793 | E | 2021-05-27 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121435787 | E | 2021-05-27 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2023-01-01
Sub | 121445844 | E | 2021-05-27 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121445973 | E | 2021-05-27 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121420237 | E | 2021-05-27 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121445735 | E | 2021-05-27 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121445848 | E | 2021-05-27 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121432188 | E | 2021-05-28 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2023-01-01
Sub | 121438682 | E | 2021-05-28 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121439027 | E | 2021-05-28 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121432189 | E | 2021-05-28 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 121439221 | E | 2021-05-28 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121432184 | E | 2021-05-28 | OPEN | T2/3A | 40.718 | -122.9343 | 2023-01-01
Sub | 121432279 | E | 2021-05-28 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2023-01-01
Sub | 121430569 | E | 2021-05-28 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121439281 | E | 2021-05-29 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121439284 | E | 2021-05-29 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121437146 | E | 2021-05-29 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2023-01-01
Sub | 121437359 | E | 2021-05-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121437483 | E | 2021-05-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121439285 | E | 2021-05-29 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121437587 | E | 2021-05-29 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121430913 | E | 2021-05-29 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121431621 | E | 2021-05-29 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121432187 | E | 2021-05-29 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2023-01-01
Sub | 121437943 | E | 2021-05-31 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 123047654 | E | 2022-03-02 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2023-01-01
Sub | 121437354 | E | 2021-05-31 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121437942 | E | 2021-05-31 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121437793 | E | 2021-05-31 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121437797 | E | 2021-05-31 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2023-01-01
Sub | 121442717 | E | 2021-06-01 | OPEN | T2/3A | 41.0565 | -123.6823 | 2023-01-01
Sub | 122343999 | E | 2021-06-01 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2023-01-01
Sub | 122512479 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 122512475 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 122512558 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 122337254 | E | 2021-06-01 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2023-01-01
Sub | 122500854 | E | 2021-06-01 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2023-01-01
Sub | 122512552 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 122512555 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 121479247 | E | 2021-06-05 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 122337290 | E | 2021-06-01 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2023-01-01
Sub | 122337298 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.6774 | -121.4916 | 2023-01-01
Sub | 122512556 | E | 2021-06-01 | OPEN | Tier 3 - Extreme | 39.4655 | -120.8448 | 2023-01-01
Sub | 121451973 | E | 2021-06-02 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 122344320 | E | 2021-06-01 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2023-01-01
Sub | 121450852 | E | 2021-06-02 | OPEN | T2/3A | 40.4618 | -122.3278 | 2023-01-01
Sub | 121450858 | E | 2021-06-02 | OPEN | T2/3A | 40.4618 | -122.3278 | 2023-01-01
Sub | 121452136 | E | 2021-06-02 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121453293 | E | 2021-06-02 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121656659 | E | 2021-06-02 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 121452061 | E | 2021-06-02 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121452317 | E | 2021-06-02 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121453533 | E | 2021-06-02 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121445086 | E | 2021-06-02 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121452130 | E | 2021-06-02 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121451227 | E | 2021-06-03 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 121513486 | E | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121457775 | E | 2021-06-03 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121521235 | E | 2021-06-04 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121527362 | E | 2021-06-04 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121521304 | E | 2021-06-04 | OPEN | T2/3A | 39.0078 | -122.894 | 2023-01-01
Sub | 121482681 | E | 2021-06-05 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 123062723 | B | 2022-03-08 | OPEN | T2/3A | 40.3977 | -122.2649 | 2022-08-01
Sub | 122512741 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 122512744 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 122512745 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 122512615 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 122512618 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 122512743 | E | 2021-06-07 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2023-01-01
Sub | 121812999 | E | 2021-06-08 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2023-01-01
Sub | 121956706 | E | 2021-06-08 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 121490409 | E | 2021-06-08 | OPEN | Tier 2 - Elevated | 40.5624 | -122.3953 | 2023-01-01
Sub | 121492813 | E | 2021-06-08 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 121498182 | E | 2021-06-09 | OPEN | T2/3A | 40.718 | -122.9343 | 2023-01-01
Sub | 121520403 | E | 2021-06-10 | OPEN | T2/3A | 40.2999 | -121.0015 | 2023-01-01
Sub | 123597913 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.7385 | -121.7713 | 2022-08-01
Sub | 121531272 | E | 2021-06-13 | OPEN | T2/3A | 39.231 | -121.035 | 2023-01-01
Sub | 121531170 | E | 2021-06-13 | OPEN | T2/3A | 39.231 | -121.035 | 2023-01-01
Sub | 121541312 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121577833 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 123631278 | A | 2022-05-14 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-06-13
Sub | 121536517 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121539394 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121534957 | E | 2021-06-13 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121537266 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121535891 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121538824 | E | 2021-06-13 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121554568 | E | 2021-06-14 | OPEN | T2/3A | 39.231 | -121.035 | 2023-01-01
Sub | 122513772 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513791 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513830 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513771 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513797 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513835 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513776 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513790 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513795 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513774 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513778 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513793 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513796 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513799 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 122513831 | E | 2021-06-14 | OPEN | Tier 2 - Elevated | 39.331 | -121.1894 | 2023-01-01
Sub | 123723905 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-08-01
Sub | 123724023 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-08-01
Sub | 121553171 | E | 2021-06-15 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2023-01-01
Sub | 122513850 | E | 2021-06-15 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2023-01-01
Sub | 122513854 | E | 2021-06-15 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2023-01-01
Sub | 121554424 | E | 2021-06-16 | OPEN | Tier 3 - Extreme | 38.6593 | -120.9473 | 2023-01-01
Sub | 121546532 | E | 2021-06-16 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2023-01-01
Sub | 121546479 | E | 2021-06-16 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2023-01-01
Sub | 123663484 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-08-01
Sub | 121548688 | E | 2021-06-16 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121548798 | E | 2021-06-16 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2023-01-01
Sub | 121551472 | E | 2021-06-16 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121552294 | E | 2021-06-16 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121552137 | E | 2021-06-16 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121560760 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121560766 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121560769 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121561081 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121555409 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 40.8592 | -121.7529 | 2023-01-01
Sub | 121560107 | E | 2021-06-17 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121560108 | E | 2021-06-17 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121558798 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 40.8592 | -121.7529 | 2023-01-01
Sub | 121562934 | E | 2021-06-18 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 123648617 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-08-01
Sub | 123162866 | E | 2022-03-21 | OPEN | Tier 2 - Elevated | 40.7407 | -122.3096 | 2023-01-01
Sub | 123169816 | B | 2022-03-22 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2022-08-01
Sub | 123698754 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.3953 | -121.879 | 2022-08-01
Sub | 123176321 | B | 2022-03-23 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2022-08-01
Sub | 123691023 | A | 2022-05-23 | OPEN | Tier 3 - Extreme | 38.0121 | -122.6537 | 2022-06-22
Sub | 121579699 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 40.619 | -122.3221 | 2023-01-01
Sub | 121586427 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121586422 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121585601 | E | 2021-06-23 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 121586200 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121586429 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 123182684 | B | 2022-03-24 | OPEN | Tier 2 - Elevated | 38.957 | -121.0424 | 2022-08-01
Sub | 121626322 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121629797 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121629187 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121629570 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 121586728 | E | 2021-06-23 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121589188 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121630097 | E | 2021-06-23 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 123707678 | A | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.957 | -121.0424 | 2022-06-23
Sub | 121619804 | E | 2021-06-23 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 121588220 | E | 2021-06-23 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121587459 | E | 2021-06-23 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121587452 | E | 2021-06-23 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121587454 | E | 2021-06-23 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121591353 | E | 2021-06-23 | OPEN | T2/3A | 40.6778 | -122.3498 | 2023-01-01
Sub | 121601957 | E | 2021-06-25 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121601289 | E | 2021-06-25 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121602260 | E | 2021-06-25 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 123707464 | A | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-06-26
Sub | 121617321 | E | 2021-06-26 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121618763 | E | 2021-06-26 | OPEN | T2/3A | 38.3834 | -122.5279 | 2023-01-01
Sub | 121638704 | E | 2021-06-26 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 123752566 | A | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-06-27
Sub | 123752251 | A | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-06-27
Sub | 122894901 | B | 2022-01-27 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2022-08-01
Sub | 121661220 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121622580 | E | 2021-06-27 | OPEN | T2/3A | 36.9923 | -121.9822 | 2023-01-01
Sub | 121657695 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121661528 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 121661630 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 121661634 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121761183 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 121661425 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 121661526 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 37.9412 | -122.7062 | 2023-01-01
Sub | 121657968 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 121661361 | E | 2021-06-27 | OPEN | Tier 2 - Elevated | 38.0549 | -122.7599 | 2023-01-01
Sub | 123213776 | B | 2022-03-30 | OPEN | T2/3A | 40.5133 | -122.3788 | 2022-08-01
Sub | 121664210 | E | 2021-06-28 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664673 | E | 2021-06-28 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121653980 | E | 2021-06-28 | OPEN | Tier 3 - Extreme | 37.8479 | -122.1611 | 2023-01-01
Sub | 123222779 | B | 2022-03-31 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-08-01
Sub | 123223054 | B | 2022-03-31 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-08-01
Sub | 123208930 | B | 2022-03-29 | OPEN | Tier 2 - Elevated | 40.8945 | -122.3808 | 2022-08-01
Sub | 121663657 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121661740 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121997636 | E | 2021-06-29 | OPEN | T2/3A | 39.1431 | -123.1918 | 2023-01-01
Sub | 121661099 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121663700 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121661745 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121661749 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664360 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121671449 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121663654 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664214 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664215 | E | 2021-06-29 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121997637 | E | 2021-06-29 | OPEN | T2/3A | 39.1431 | -123.1918 | 2023-01-01
Sub | 121661091 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121663930 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121663933 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664520 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664526 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121663651 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121660999 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664363 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 121664524 | E | 2021-06-30 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 123231337 | B | 2022-04-01 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-08-01
Sub | 121642488 | E | 2021-06-30 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121642489 | E | 2021-06-30 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121642620 | E | 2021-06-30 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121657248 | E | 2021-07-01 | OPEN | T2/3A | 38.6934 | -120.8259 | 2023-01-01
Sub | 121655867 | E | 2021-07-01 | OPEN | Tier 2 - Elevated | 38.7309 | -120.7836 | 2023-01-01
Sub | 121715533 | E | 2021-07-01 | OPEN | Tier 2 - Elevated | 38.7309 | -120.7836 | 2023-01-01
Sub | 123731818 | A | 2022-06-01 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-07-01
Sub | 123732033 | A | 2022-06-01 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-07-01
Sub | 123731934 | A | 2022-06-01 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-07-01
Sub | 123235159 | B | 2022-04-02 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-09-01
Sub | 121653931 | E | 2021-07-02 | OPEN | T2/3A | 40.5133 | -122.3788 | 2023-01-01
Sub | 123236514 | B | 2022-04-02 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-09-01
Sub | 123245754 | B | 2022-04-04 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-09-01
Sub | 123244107 | B | 2022-04-04 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-09-01
Sub | 123254677 | B | 2022-04-05 | OPEN | Tier 2 - Elevated | 39.3309 | -121.1916 | 2022-09-01
Sub | 123253496 | B | 2022-04-05 | OPEN | T2/3A | 40.3977 | -122.2649 | 2022-09-01
Sub | 123258710 | B | 2022-04-06 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-09-01
Sub | 121690605 | E | 2021-07-07 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 121690844 | E | 2021-07-07 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 123279681 | E | 2022-04-09 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2023-01-01
Sub | 121719565 | E | 2021-07-08 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 123301548 | B | 2022-04-11 | OPEN | Tier 2 - Elevated | 39.2093 | -121.061 | 2022-09-01
Sub | 123299933 | B | 2022-04-11 | OPEN | Tier 2 - Elevated | 38.957 | -121.0424 | 2022-09-01
Sub | 123315894 | B | 2022-04-12 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-09-01
Sub | 123316083 | B | 2022-04-12 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-09-01
Sub | 123315626 | B | 2022-04-12 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-09-01
Sub | 123361655 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 38.3421 | -120.9351 | 2022-09-01
Sub | 121722729 | E | 2021-07-13 | OPEN | Tier 2 - Elevated | 38.1699 | -120.6673 | 2023-01-01
Sub | 123316182 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-09-01
Sub | 123365131 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-09-01
Sub | 123365456 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-09-01
Sub | 123320802 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-09-01
Sub | 123328122 | B | 2022-04-13 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123330216 | B | 2022-04-14 | OPEN | Tier 3 - Extreme | 39.2147 | -120.8093 | 2022-09-01
Sub | 121722281 | E | 2021-07-13 | OPEN | Tier 2 - Elevated | 38.3421 | -120.9351 | 2023-01-01
Sub | 121726943 | E | 2021-07-13 | OPEN | T2/3A | 34.6432 | -120.4372 | 2023-01-01
Sub | 123334993 | B | 2022-04-15 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-09-01
Sub | 121741811 | E | 2021-07-15 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2023-01-01
Sub | 121738060 | E | 2021-07-15 | OPEN | Tier 2 - Elevated | 38.3421 | -120.9351 | 2023-01-01
Sub | 121741921 | E | 2021-07-15 | OPEN | T2/3A | 38.2167 | -120.7647 | 2023-01-01
Sub | 123358405 | B | 2022-04-18 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2022-09-01
Sub | 123382687 | B | 2022-04-19 | OPEN | Tier 2 - Elevated | 38.4808 | -120.845 | 2022-09-01
Sub | 123387581 | B | 2022-04-19 | OPEN | Tier 2 - Elevated | 38.4808 | -120.845 | 2022-09-01
Sub | 123388373 | B | 2022-04-20 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123391597 | B | 2022-04-20 | OPEN | Tier 2 - Elevated | 36.9089 | -119.0884 | 2022-09-01
Sub | 123391469 | B | 2022-04-20 | OPEN | Tier 2 - Elevated | 36.9089 | -119.0884 | 2022-09-01
Sub | 123399724 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2022-09-01
Sub | 123399066 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123403890 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2022-09-01
Sub | 123409555 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2022-09-01
Sub | 123391176 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123398453 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123399067 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123399944 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123388429 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 40.0073 | -121.2494 | 2022-09-01
Sub | 123478279 | B | 2022-04-21 | OPEN | Tier 2 - Elevated | 40.0073 | -121.2494 | 2022-09-01
Sub | 123409012 | B | 2022-04-22 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-09-01
Sub | 123397389 | B | 2022-04-22 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-09-01
Sub | 123403688 | B | 2022-04-22 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2022-09-01
Sub | 123405086 | B | 2022-04-22 | OPEN | Tier 2 - Elevated | 39.3244 | -120.6448 | 2022-09-01
Sub | 123400611 | B | 2022-04-22 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2022-09-01
Sub | 123433903 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123434470 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123422617 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123422996 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123433902 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123409818 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.3244 | -120.6448 | 2022-09-01
Sub | 123422350 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123423073 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123422351 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123434207 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123410099 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.3244 | -120.6448 | 2022-09-01
Sub | 123412329 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123411587 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123423077 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 37.6648 | -119.8412 | 2022-09-01
Sub | 123433887 | B | 2022-04-23 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123437002 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123411692 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123437159 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123443538 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123437032 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123440102 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123450675 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123461674 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123473261 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123461673 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 37.7216 | -119.7029 | 2022-09-01
Sub | 123420680 | B | 2022-04-25 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2022-09-01
Sub | 123423700 | B | 2022-04-25 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-09-01
Sub | 123441344 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.1154 | -120.953 | 2022-09-01
Sub | 123441620 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.1154 | -120.953 | 2022-09-01
Sub | 123451436 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123434059 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123457883 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123473265 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123476587 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123447288 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123466553 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123446812 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123446818 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123449011 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.3399 | -121.195 | 2022-09-01
Sub | 123443179 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123473189 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123473584 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123473188 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123432399 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.1154 | -120.953 | 2022-09-01
Sub | 123442261 | B | 2022-04-26 | OPEN | Tier 2 - Elevated | 39.2351 | -121.2687 | 2022-09-01
Sub | 123457541 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123459500 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123475174 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123461677 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 35.5593 | -118.9576 | 2022-09-01
Sub | 123446496 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 35.5593 | -118.9576 | 2022-09-01
Sub | 123447115 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123447526 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123474789 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123475170 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123447886 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123460613 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 38.1998 | -120.7194 | 2022-09-01
Sub | 123474506 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123486422 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123437069 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 39.6846 | -123.4771 | 2022-09-01
Sub | 123490702 | B | 2022-04-27 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2022-09-01
Sub | 123479934 | B | 2022-04-27 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2022-09-01
Sub | 123477191 | B | 2022-04-28 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2022-09-01
Sub | 123480005 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123479582 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123486224 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 37.9798 | -120.4141 | 2022-09-01
Sub | 123486954 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123514998 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 37.9798 | -120.4141 | 2022-09-01
Sub | 123515835 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 37.9798 | -120.4141 | 2022-09-01
Sub | 123480113 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123486715 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123519594 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 37.9798 | -120.4141 | 2022-09-01
Sub | 123519597 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 37.9798 | -120.4141 | 2022-09-01
Sub | 121802458 | E | 2021-07-27 | OPEN | T2/3A | 34.6247 | -120.1861 | 2023-01-01
Sub | 123491131 | E | 2022-04-28 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2023-01-01
Sub | 123465756 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123465914 | B | 2022-04-28 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 121802451 | E | 2021-07-27 | OPEN | Tier 2 - Elevated | 34.648 | -120.1849 | 2023-01-01
Sub | 121808845 | E | 2021-07-27 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 123454290 | B | 2022-04-29 | OPEN | Tier 2 - Elevated | 38.7309 | -120.7836 | 2022-09-01
Sub | 123490980 | B | 2022-04-29 | OPEN | Tier 2 - Elevated | 35.5593 | -118.9576 | 2022-09-01
Sub | 123466240 | B | 2022-04-29 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-09-01
Sub | 123478324 | B | 2022-04-29 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-09-01
Sub | 123490985 | B | 2022-04-29 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123490981 | B | 2022-04-29 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-09-01
Sub | 123488894 | B | 2022-04-30 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2022-09-01
Sub | 123489174 | B | 2022-04-30 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2022-09-01
Sub | 123514794 | B | 2022-04-30 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2022-09-01
Sub | 123472818 | B | 2022-04-29 | OPEN | Tier 3 - Extreme | 39.9108 | -121.3277 | 2022-09-01
Sub | 121403885 | E | 2021-05-26 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2023-01-01
Sub | 123484196 | E | 2022-04-30 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2023-01-01
Sub | 123469522 | B | 2022-04-29 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-09-01
Sub | 123538277 | B | 2022-05-01 | OPEN | T2/3A | 38.9014 | -121.0879 | 2022-09-01
Sub | 123496686 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 39.1457 | -122.9167 | 2022-09-01
Sub | 123518425 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 39.1457 | -122.9167 | 2022-09-01
Sub | 123518151 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 39.1457 | -122.9167 | 2022-09-01
Sub | 123575910 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123536484 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123518420 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 39.1457 | -122.9167 | 2022-09-01
Sub | 123518700 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 39.1457 | -122.9167 | 2022-09-01
Sub | 123538556 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123538614 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123563946 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123588787 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123518000 | B | 2022-05-02 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-09-01
Sub | 123576965 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123581781 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123520545 | B | 2022-05-02 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2022-09-01
Sub | 123539363 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123576796 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123615569 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123525508 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 38.3311 | -120.67 | 2022-09-01
Sub | 123566170 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123576188 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123576785 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123585755 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-09-01
Sub | 123516254 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.9463 | -120.5278 | 2022-10-01
Sub | 123546171 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 38.9141 | -121.019 | 2022-10-01
Sub | 123546499 | B | 2022-05-03 | OPEN | T2/3A | 40.0938 | -120.9112 | 2022-10-01
Sub | 123546540 | B | 2022-05-03 | OPEN | T2/3A | 40.0938 | -120.9112 | 2022-10-01
Sub | 123575256 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123513790 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.068 | -119.4956 | 2022-10-01
Sub | 123515347 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 38.3421 | -120.9351 | 2022-10-01
Sub | 123575125 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123575253 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123603779 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 39.0275 | -122.6624 | 2022-10-01
Sub | 123513512 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.068 | -119.4956 | 2022-10-01
Sub | 123590225 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123590463 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123546542 | B | 2022-05-03 | OPEN | T2/3A | 40.0938 | -120.9112 | 2022-10-01
Sub | 123572632 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123586629 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123586825 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123590064 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123590460 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 122267603 | E | 2021-08-01 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2023-01-01
Sub | 123512717 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.9463 | -120.5278 | 2022-10-01
Sub | 123499313 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.9463 | -120.5278 | 2022-10-01
Sub | 123564372 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123564378 | B | 2022-05-03 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123576146 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123577550 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123586543 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123617356 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123515009 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123527748 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-10-01
Sub | 123563398 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123577551 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123585601 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123537594 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-10-01
Sub | 123541541 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.9037 | -120.4977 | 2022-10-01
Sub | 123577802 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123529303 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-10-01
Sub | 123542017 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123563399 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123564732 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123581298 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123581484 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123586365 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123588370 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123604319 | B | 2022-05-04 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 123604482 | B | 2022-05-04 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 121832539 | E | 2021-08-02 | OPEN | Tier 2 - Elevated | 40.619 | -122.3221 | 2023-01-01
Sub | 121832802 | E | 2021-08-02 | OPEN | Tier 2 - Elevated | 40.619 | -122.3221 | 2023-01-01
Sub | 123530973 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.6448 | -119.1605 | 2022-10-01
Sub | 123538093 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123563944 | B | 2022-05-02 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123535380 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123544886 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123567148 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123535389 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123564930 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123534066 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123540293 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123542133 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 39.0275 | -122.6624 | 2022-10-01
Sub | 123532897 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123540297 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123522453 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123533165 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 121841086 | E | 2021-08-03 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2023-01-01
Sub | 123538187 | E | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2023-01-01
Sub | 123538090 | E | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2023-01-01
Sub | 123538094 | E | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2023-01-01
Sub | 123537655 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 40.0854 | -121.1479 | 2022-10-01
Sub | 123566787 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123538139 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123538180 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123540291 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123560757 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2022-10-01
Sub | 123574502 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.3474 | -121.6349 | 2022-10-01
Sub | 123576560 | B | 2022-05-04 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123579778 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.3474 | -121.6349 | 2022-10-01
Sub | 123615908 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.3474 | -121.6349 | 2022-10-01
Sub | 123756491 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 36.7094 | -119.0291 | 2022-10-01
Sub | 123538185 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.3871 | -123.0441 | 2022-10-01
Sub | 123580400 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 37.9037 | -120.4977 | 2022-10-01
Sub | 123580001 | E | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.3474 | -121.6349 | 2023-01-01
Sub | 121846548 | E | 2021-08-04 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2023-01-01
Sub | 123543466 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123545701 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123545401 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123541061 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-10-01
Sub | 123571683 | B | 2022-05-06 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123545985 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2022-10-01
Sub | 123616089 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 40.5881 | -121.0916 | 2022-10-01
Sub | 123616201 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 40.5881 | -121.0916 | 2022-10-01
Sub | 123540779 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2022-10-01
Sub | 123540774 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123708923 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 34.6967 | -120.1515 | 2022-10-01
Sub | 123607390 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 34.648 | -120.1849 | 2022-10-01
Sub | 123525280 | B | 2022-05-05 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2022-10-01
Sub | 123604840 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 34.648 | -120.1849 | 2022-10-01
Sub | 123607394 | B | 2022-05-07 | OPEN | Tier 2 - Elevated | 34.648 | -120.1849 | 2022-10-01
Sub | 123580621 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 38.9107 | -122.6174 | 2022-10-01
Sub | 123657274 | B | 2022-05-09 | OPEN | Tier 3 - Extreme | 37.2035 | -119.4973 | 2022-10-01
Sub | 123541780 | E | 2022-05-09 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 123590824 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 37.7448 | -121.8579 | 2022-10-01
Sub | 123603445 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 38.9107 | -122.6174 | 2022-10-01
Sub | 123589599 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 37.7448 | -121.8579 | 2022-10-01
Sub | 123776252 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 34.7009 | -120.4356 | 2022-10-01
Sub | 123566420 | B | 2022-05-10 | OPEN | T2/3A | 38.9729 | -123.0812 | 2022-10-01
Sub | 123617737 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 123620320 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 123566422 | B | 2022-05-10 | OPEN | T2/3A | 38.9729 | -123.0812 | 2022-10-01
Sub | 123596123 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 123564301 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 37.7448 | -121.8579 | 2022-10-01
Sub | 123565160 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2022-10-01
Sub | 123566258 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 38.937 | -122.609 | 2022-10-01
Sub | 123595870 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 39.0193 | -120.8303 | 2022-10-01
Sub | 123596804 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 38.1866 | -120.112 | 2022-10-01
Sub | 123657270 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 34.7009 | -120.4356 | 2022-10-01
Sub | 121812731 | E | 2021-07-29 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 123607454 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 39.9053 | -121.3455 | 2022-10-01
Sub | 123607457 | B | 2022-05-10 | OPEN | Tier 3 - Extreme | 39.9053 | -121.3455 | 2022-10-01
Sub | 123568051 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123572394 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123598090 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2022-10-01
Sub | 123598093 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123598092 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123648336 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2022-10-01
Sub | 123575227 | B | 2022-05-11 | OPEN | T2/3A | 37.0419 | -122.0252 | 2022-10-01
Sub | 123579228 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123590509 | B | 2022-05-09 | OPEN | Tier 2 - Elevated | 37.7448 | -121.8579 | 2022-10-01
Sub | 123597911 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.7385 | -121.7713 | 2022-10-01
Sub | 123604224 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123598094 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123593296 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123666542 | B | 2022-05-11 | OPEN | Tier 3 - Extreme | 37.2035 | -119.4973 | 2022-10-01
Sub | 123594623 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123614192 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123618733 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 37.7385 | -121.7713 | 2022-10-01
Sub | 123542090 | B | 2022-05-09 | OPEN | T2/3A | 40.3977 | -122.2649 | 2022-10-01
Sub | 123589254 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2022-10-01
Sub | 123593590 | B | 2022-05-10 | OPEN | Tier 2 - Elevated | 38.4128 | -120.6602 | 2022-10-01
Sub | 123647928 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2022-10-01
Sub | 123648063 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2022-10-01
Sub | 123589468 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2022-10-01
Sub | 123589549 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2022-10-01
Sub | 123597786 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123618592 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2022-10-01
Sub | 123648173 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2022-10-01
Sub | 123596345 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123596349 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123603709 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123621567 | B | 2022-05-12 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2022-10-01
Sub | 123592372 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123614342 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123594626 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123593597 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2022-10-01
Sub | 123641936 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123612126 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123651886 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2022-10-01
Sub | 123607384 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2022-10-01
Sub | 123610339 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123642083 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123641719 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123606384 | B | 2022-05-13 | OPEN | Tier 3 - Extreme | 39.8262 | -121.4096 | 2022-10-01
Sub | 123606388 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2022-10-01
Sub | 123618925 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 40.9288 | -121.5444 | 2022-10-01
Sub | 123595227 | B | 2022-05-11 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123606386 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2022-10-01
Sub | 123624425 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123624476 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123640493 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2022-10-01
Sub | 123596617 | B | 2022-05-12 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2022-10-01
Sub | 123640499 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2022-10-01
Sub | 121889236 | E | 2021-08-12 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2023-01-01
Sub | 121890014 | E | 2021-08-12 | OPEN | Tier 3 - Extreme | 39.4853 | -121.2203 | 2023-01-01
Sub | 121889028 | E | 2021-08-12 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2023-01-01
Sub | 121889490 | E | 2021-08-12 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2023-01-01
Sub | 121889570 | E | 2021-08-12 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2023-01-01
Sub | 123582362 | B | 2022-05-12 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2022-10-01
Sub | 123632924 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123610735 | B | 2022-05-13 | OPEN | Tier 2 - Elevated | 38.0572 | -120.534 | 2022-10-01
Sub | 123624534 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123659064 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 35.32 | -120.6931 | 2022-10-01
Sub | 123610938 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2022-10-01
Sub | 123632333 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123647370 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123647375 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123647378 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2022-10-01
Sub | 123659062 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 35.32 | -120.6931 | 2022-10-01
Sub | 123616147 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 123641830 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 35.32 | -120.6931 | 2022-10-01
Sub | 123641312 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 35.32 | -120.6931 | 2022-10-01
Sub | 123629480 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2022-10-01
Sub | 123663481 | B | 2022-05-16 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2022-10-01
Sub | 123666943 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123712605 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 35.5709 | -121.0554 | 2022-10-01
Sub | 123666547 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123699394 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123629675 | B | 2022-05-16 | OPEN | Tier 3 - Extreme | 40.7912 | -121.9378 | 2022-10-01
Sub | 123635689 | B | 2022-05-16 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2022-10-01
Sub | 123666549 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123604372 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 38.3739 | -120.9576 | 2022-10-01
Sub | 123638941 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123657785 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123658013 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123635183 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 40.2693 | -121.0881 | 2022-10-01
Sub | 123620160 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-10-01
Sub | 123657788 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123687581 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123712601 | B | 2022-05-14 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123660328 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123626098 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.7912 | -121.9378 | 2022-10-01
Sub | 123629586 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.7912 | -121.9378 | 2022-10-01
Sub | 123726538 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2022-10-01
Sub | 123631519 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-10-01
Sub | 123632148 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-10-01
Sub | 123658843 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-10-01
Sub | 123672072 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123641076 | B | 2022-05-15 | OPEN | Tier 2 - Elevated | 35.32 | -120.6931 | 2022-10-01
Sub | 123671338 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123632409 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123632446 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123632493 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123638311 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123673187 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2022-10-01
Sub | 123726211 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123730701 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123636611 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123636733 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123636739 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123665666 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123673038 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2022-10-01
Sub | 123673324 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123725033 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123725905 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2022-10-01
Sub | 123756496 | B | 2022-05-17 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123712153 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 40.6291 | -121.9159 | 2022-10-01
Sub | 123627629 | B | 2022-05-16 | OPEN | Tier 3 - Extreme | 40.7912 | -121.9378 | 2022-10-01
Sub | 123719789 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 35.5709 | -121.0554 | 2022-10-01
Sub | 123701002 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 36.0132 | -121.1679 | 2022-10-01
Sub | 123717595 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 40.6291 | -121.9159 | 2022-10-01
Sub | 123725983 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 35.5709 | -121.0554 | 2022-10-01
Sub | 123694373 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123694466 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123694540 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 121906916 | E | 2021-08-16 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2023-01-01
Sub | 121924865 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 123730920 | B | 2022-05-16 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2022-10-01
Sub | 123631817 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2022-10-01
Sub | 123660326 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 40.2693 | -121.0881 | 2022-10-01
Sub | 123667299 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123673890 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123729452 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123698212 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123720234 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-10-01
Sub | 123658407 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123667294 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123677017 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123693121 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123696711 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2022-10-01
Sub | 123667035 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 37.9037 | -120.4977 | 2022-10-01
Sub | 123667487 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123669817 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123699005 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.9908 | -121.4978 | 2022-10-01
Sub | 123730705 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2022-10-01
Sub | 123761788 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-10-01
Sub | 123651466 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123653978 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123673130 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123676854 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123678240 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123699149 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123640851 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123653902 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123665872 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123699227 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123730966 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123642138 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123663482 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123663483 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123666224 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123671334 | B | 2022-05-17 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123676329 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123665669 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123668527 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123758260 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123648165 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123663480 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 38.4981 | -120.2184 | 2022-10-01
Sub | 123677726 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2022-10-01
Sub | 123678950 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2022-10-01
Sub | 123745610 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-10-01
Sub | 123662959 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 40.2693 | -121.0881 | 2022-10-01
Sub | 123677182 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123681279 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123691398 | B | 2022-05-18 | OPEN | Tier 2 - Elevated | 40.6291 | -121.9159 | 2022-10-01
Sub | 123744983 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-10-01
Sub | 123667291 | E | 2022-05-20 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2023-01-01
Sub | 123673981 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123674071 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123676324 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123694892 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 40.6523 | -122.3342 | 2022-10-01
Sub | 123719521 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2022-10-01
Sub | 123676326 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123667873 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123677335 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123722517 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123724367 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2022-10-01
Sub | 123741104 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123760094 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123760470 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123760567 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2022-10-01
Sub | 123761015 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2022-10-01
Sub | 123722267 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123722693 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123680776 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123710245 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123724362 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2022-10-01
Sub | 123760020 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123649243 | B | 2022-05-20 | OPEN | Tier 2 - Elevated | 38.8892 | -123.5509 | 2022-10-01
Sub | 123694544 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123710242 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 38.7862 | -123.5221 | 2022-10-01
Sub | 123722973 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123743664 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123760417 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 121921221 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121921220 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121924122 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121924171 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121924176 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121924120 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 121923931 | E | 2021-08-19 | OPEN | T2/3A | 40.888 | -121.6711 | 2023-01-01
Sub | 123694215 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123760142 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123686030 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123676542 | B | 2022-05-19 | OPEN | Tier 2 - Elevated | 39.2087 | -121.3031 | 2022-10-01
Sub | 123693815 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123693019 | B | 2022-05-22 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2022-10-01
Sub | 123731376 | B | 2022-05-22 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2022-10-01
Sub | 123741019 | B | 2022-05-22 | OPEN | Tier 2 - Elevated | 40.0269 | -120.9632 | 2022-10-01
Sub | 123692824 | B | 2022-05-22 | OPEN | Tier 2 - Elevated | 40.6869 | -122.6412 | 2022-10-01
Sub | 121926862 | E | 2021-08-20 | OPEN | Tier 2 - Elevated | 40.9288 | -121.5444 | 2023-01-01
Sub | 123681745 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 40.0222 | -121.0639 | 2022-10-01
Sub | 123695841 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123710612 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 37.0257 | -122.1548 | 2022-10-01
Sub | 123760133 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 40.8945 | -122.3808 | 2022-10-01
Sub | 123680655 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 39.2259 | -121.4228 | 2022-10-01
Sub | 123696523 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123760941 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 39.3877 | -121.4031 | 2022-10-01
Sub | 123712602 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 37.0257 | -122.1548 | 2022-10-01
Sub | 123714164 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 40.2859 | -123.8373 | 2022-10-01
Sub | 123760091 | B | 2022-05-22 | OPEN | Tier 2 - Elevated | 40.8945 | -122.3808 | 2022-10-01
Sub | 123760026 | E | 2022-05-23 | OPEN | Tier 2 - Elevated | 40.8945 | -122.3808 | 2023-01-01
Sub | 123681131 | B | 2021-05-22 | OPEN | Tier 2 - Elevated | 40.7118 | -122.808 | 2022-10-01
Sub | 123698397 | B | 2022-05-23 | OPEN | Tier 3 - Extreme | 39.6774 | -121.4916 | 2022-10-01
Sub | 123699186 | B | 2022-05-21 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2022-10-01
Sub | 123710593 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123758801 | B | 2022-05-24 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2022-10-01
Sub | 123759206 | B | 2022-05-24 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2022-10-01
Sub | 123761247 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123686291 | B | 2022-05-24 | OPEN | T2/3A | 37.604 | -122.4232 | 2022-10-01
Sub | 123689500 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.3877 | -121.4031 | 2022-10-01
Sub | 123682714 | B | 2022-05-24 | OPEN | T2/3A | 37.7273 | -122.1387 | 2022-10-01
Sub | 123696527 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123703139 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 40.9292 | -121.5444 | 2022-10-01
Sub | 123710672 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123711620 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 40.2859 | -123.8373 | 2022-10-01
Sub | 123760948 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123696520 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123710246 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123761245 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 39.6545 | -121.6356 | 2022-10-01
Sub | 123744085 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123708201 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.957 | -121.0424 | 2022-10-01
Sub | 123709680 | B | 2022-05-24 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2022-10-01
Sub | 123714074 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714093 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714209 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123715208 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123712373 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 40.2859 | -123.8373 | 2022-10-01
Sub | 123714040 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123730607 | B | 2022-05-24 | OPEN | Tier 3 - Extreme | 39.7888 | -121.6574 | 2022-10-01
Sub | 123744455 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123712015 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714263 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123723144 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123762549 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 40.4333 | -123.4727 | 2022-10-01
Sub | 123773710 | B | 2022-05-25 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2022-10-01
Sub | 123679491 | B | 2022-05-23 | OPEN | Tier 2 - Elevated | 40.8945 | -122.3808 | 2022-10-01
Sub | 123679786 | B | 2022-05-23 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2022-10-01
Sub | 123762457 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 40.4333 | -123.4727 | 2022-10-01
Sub | 123683364 | B | 2022-05-24 | OPEN | T2/3A | 37.5869 | -121.8697 | 2022-10-01
Sub | 123681444 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.6803 | -123.3118 | 2022-10-01
Sub | 123743689 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123761921 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 40.4333 | -123.4727 | 2022-10-01
Sub | 123773927 | B | 2022-05-25 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2022-10-01
Sub | 123699146 | B | 2022-05-23 | OPEN | Tier 3 - Extreme | 39.4381 | -120.9961 | 2022-10-01
Sub | 121942678 | E | 2021-08-23 | OPEN | Tier 3 - Extreme | 38.6593 | -120.9473 | 2023-01-01
Sub | 121942824 | E | 2021-08-23 | OPEN | Tier 3 - Extreme | 38.7934 | -120.6192 | 2023-01-01
Sub | 123714043 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123715224 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123744021 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714048 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714099 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123714132 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123715167 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123720379 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 121942617 | E | 2021-08-23 | OPEN | T2/3A | 38.6557 | -121.0595 | 2023-01-01
Sub | 123722071 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2022-10-01
Sub | 123688000 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.3313 | -120.6731 | 2022-10-01
Sub | 123714787 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 38.1199 | -122.614 | 2022-10-01
Sub | 123730618 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 123682512 | B | 2022-05-24 | OPEN | T2/3A | 37.7273 | -122.1387 | 2022-10-01
Sub | 123722169 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2022-10-01
Sub | 123730549 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 121948314 | E | 2021-08-24 | OPEN | Tier 3 - Extreme | 40.7912 | -121.9378 | 2023-01-01
Sub | 121952528 | E | 2021-08-24 | OPEN | T2/3A | 39.2506 | -123.1964 | 2023-01-01
Sub | 123719298 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123725834 | B | 2022-05-26 | OPEN | T2/3A | 37.9163 | -122.3031 | 2022-10-01
Sub | 123712377 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123720497 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 123714377 | B | 2022-05-24 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123711094 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-10-01
Sub | 123713965 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-10-01
Sub | 123723514 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 123740197 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-10-01
Sub | 123775195 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-10-01
Sub | 123694895 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-10-01
Sub | 123767649 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123715062 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 123745236 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 40.7679 | -123.8738 | 2022-10-01
Sub | 123762065 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-10-01
Sub | 123703130 | B | 2022-05-25 | OPEN | Tier 2 - Elevated | 38.957 | -121.0424 | 2022-10-01
Sub | 123750297 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123775190 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-10-01
Sub | 121952809 | E | 2021-08-25 | OPEN | Tier 2 - Elevated | 35.1016 | -120.5811 | 2023-01-01
Sub | 121959382 | E | 2021-08-25 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2023-01-01
Sub | 123758916 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123767571 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123774655 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123729779 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123744984 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123749147 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123758013 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123763202 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123763206 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123767578 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123732386 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123758530 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123758539 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123758912 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123763246 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123763266 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123767531 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123767538 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123729814 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123754095 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123758263 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123758642 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123762989 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123763268 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2022-10-01
Sub | 123767537 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123775658 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2022-10-01
Sub | 123776383 | B | 2022-05-27 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 121952894 | E | 2021-08-25 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 121955520 | E | 2021-08-25 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 123750053 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123758649 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123749962 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123758825 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123775911 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123696052 | B | 2022-05-26 | OPEN | Tier 2 - Elevated | 35.5593 | -118.9576 | 2022-10-01
Sub | 123750170 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 121962162 | E | 2021-08-26 | OPEN | T2/3A | 35.4655 | -120.6715 | 2023-01-01
Sub | 123714940 | B | 2022-05-28 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123729928 | B | 2022-05-28 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2022-10-01
Sub | 123749268 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.5396 | -123.2237 | 2022-10-01
Sub | 123714004 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.3114 | -123.7865 | 2022-10-01
Sub | 123740494 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 38.5087 | -122.2145 | 2022-10-01
Sub | 123723711 | B | 2022-05-27 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2022-10-01
Sub | 123758749 | B | 2022-05-28 | OPEN | Tier 2 - Elevated | 38.49 | -122.6661 | 2022-10-01
Sub | 123727735 | B | 2022-05-31 | OPEN | Tier 3 - Extreme | 40.6782 | -121.8731 | 2022-10-01
Sub | 123728128 | B | 2022-05-31 | OPEN | Tier 2 - Elevated | 37.2539 | -119.5192 | 2022-10-01
Sub | 121970846 | E | 2021-08-30 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2023-01-01
Sub | 121986092 | E | 2021-08-31 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2023-01-01
Sub | 121977869 | E | 2021-08-31 | OPEN | Tier 2 - Elevated | 40.7407 | -122.3096 | 2023-01-01
Sub | 121984405 | E | 2021-09-01 | OPEN | Tier 3 - Extreme | 39.5752 | -121.3057 | 2023-01-01
Sub | 121993147 | E | 2021-09-01 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 121996002 | E | 2021-09-01 | OPEN | T2/3A | 40.3977 | -122.2649 | 2023-01-01
Sub | 122012858 | E | 2021-09-08 | OPEN | Tier 3 - Extreme | 38.4714 | -123.0123 | 2023-01-01
Sub | 122018178 | E | 2021-09-09 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2023-01-01
Sub | 121996554 | E | 2021-06-17 | OPEN | Tier 3 - Extreme | 40.4595 | -121.8665 | 2023-01-01
Sub | 122414458 | E | 2021-09-20 | OPEN | Tier 2 - Elevated | 40.2138 | -123.5964 | 2023-01-01
Sub | 122094494 | E | 2021-09-23 | OPEN | T2/3A | 35.374 | -120.8552 | 2023-01-01
Sub | 122117905 | E | 2021-09-24 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122114028 | E | 2021-09-28 | OPEN | Tier 2 - Elevated | 38.7396 | -120.6772 | 2023-01-01
Sub | 122124130 | E | 2021-09-30 | OPEN | T2/3A | 39.231 | -121.035 | 2023-01-01
Sub | 122125906 | E | 2021-09-30 | OPEN | Tier 2 - Elevated | 38.3096 | -122.7316 | 2023-01-01
Sub | 122125901 | E | 2021-09-30 | OPEN | T2/3A | 38.0768 | -122.5404 | 2023-01-01
Sub | 122165983 | E | 2021-10-05 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 122153672 | E | 2021-10-05 | OPEN | T2/3A | 35.4655 | -120.6715 | 2023-01-01
Sub | 122169372 | E | 2021-10-06 | OPEN | Tier 3 - Extreme | 39.5752 | -121.3057 | 2023-01-01
Sub | 122189096 | E | 2021-10-07 | OPEN | T2/3A | 40.5553 | -122.2395 | 2023-01-01
Sub | 123358330 | E | 2022-04-18 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 122006976 | E | 2021-09-07 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2023-01-01
Sub | 123570053 | E | 2022-05-11 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 123570054 | E | 2022-05-11 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 122235423 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 121555726 | E | 2021-06-17 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122241253 | E | 2021-10-13 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 122197228 | E | 2021-10-13 | OPEN | Tier 3 - Extreme | 39.0193 | -120.8303 | 2023-01-01
Sub | 123701485 | E | 2021-10-14 | OPEN | Tier 2 - Elevated | 37.819 | -122.206 | 2023-01-01
Sub | 122057999 | F | 2021-09-16 | OPEN | Tier 2 - Elevated | 37.9055 | -122.2083 | 2024-01-01
Sub | 122048596 | E | 2021-09-14 | OPEN | T2/3A | 37.604 | -122.4232 | 2023-01-01
Sub | 122228641 | E | 2021-10-18 | OPEN | T2/3A | 38.9014 | -121.0879 | 2023-01-01
Sub | 122265411 | E | 2021-10-24 | OPEN | Tier 2 - Elevated | 37.5865 | -120.1256 | 2023-01-01
Sub | 122265410 | E | 2021-10-24 | OPEN | Tier 2 - Elevated | 37.5045 | -120.0079 | 2023-01-01
Sub | 122252793 | E | 2021-10-25 | OPEN | T2/3A | 39.2506 | -123.1964 | 2023-01-01
Sub | 122257425 | E | 2021-10-26 | OPEN | T2/3A | 39.231 | -121.035 | 2023-01-01
Sub | 122274095 | E | 2021-10-26 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122262037 | E | 2021-10-26 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122275363 | E | 2021-10-26 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 123716176 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716230 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123715963 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716045 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716119 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716233 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123715990 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716110 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716112 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716171 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123717922 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716238 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716040 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716043 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123716281 | E | 2021-10-29 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 122321191 | E | 2021-11-04 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2023-01-01
Sub | 123522771 | E | 2022-05-05 | OPEN | Tier 2 - Elevated | 35.2867 | -120.7059 | 2023-01-01
Sub | 122326254 | E | 2021-11-05 | OPEN | Tier 3 - Extreme | 39.2567 | -120.767 | 2023-01-01
Sub | 122166914 | E | 2021-10-06 | OPEN | Tier 3 - Extreme | 37.8479 | -122.1611 | 2023-01-01
Sub | 122338510 | E | 2021-11-08 | OPEN | T2/3A | 38.6934 | -120.8259 | 2023-01-01
Sub | 122341239 | E | 2021-11-08 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2023-01-01
Sub | 122340997 | E | 2021-11-08 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2023-01-01
Sub | 122341794 | E | 2021-11-08 | OPEN | Tier 2 - Elevated | 40.9977 | -121.7478 | 2023-01-01
Sub | 122358790 | E | 2021-11-09 | OPEN | Tier 2 - Elevated | 37.4617 | -122.2773 | 2023-01-01
Sub | 122381251 | E | 2021-11-09 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122374614 | E | 2021-11-09 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122358850 | E | 2021-11-10 | OPEN | Tier 2 - Elevated | 37.4617 | -122.2773 | 2023-01-01
Sub | 122358884 | E | 2021-11-10 | OPEN | Tier 2 - Elevated | 37.4617 | -122.2773 | 2023-01-01
Sub | 122393562 | E | 2021-11-14 | OPEN | T2/3A | 40.4497 | -122.3051 | 2023-01-01
Sub | 122377653 | E | 2021-11-15 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 122380129 | E | 2021-11-15 | OPEN | Tier 2 - Elevated | 37.5251 | -122.3563 | 2023-01-01
Sub | 122380321 | E | 2021-11-15 | OPEN | Tier 2 - Elevated | 37.5251 | -122.3563 | 2023-01-01
Sub | 122385961 | E | 2021-11-16 | OPEN | Tier 2 - Elevated | 37.4617 | -122.2773 | 2023-01-01
Sub | 122411097 | E | 2021-11-17 | OPEN | Tier 2 - Elevated | 39.1103 | -122.8129 | 2023-01-01
Sub | 122452215 | E | 2021-11-17 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2023-01-01
Sub | 122387381 | E | 2021-11-17 | OPEN | Tier 3 - Extreme | 38.6593 | -120.9473 | 2023-01-01
Sub | 122402894 | E | 2021-11-17 | OPEN | Tier 2 - Elevated | 38.3313 | -120.6731 | 2023-01-01
Sub | 122391716 | E | 2021-11-17 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2023-01-01
Sub | 122391627 | E | 2021-11-17 | OPEN | Tier 2 - Elevated | 38.1383 | -120.3703 | 2023-01-01
Sub | 123714557 | E | 2021-11-18 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 123714558 | E | 2021-11-18 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 123721239 | E | 2021-11-18 | OPEN | T2/3A | 37.8129 | -122.2188 | 2023-01-01
Sub | 123710237 | E | 2021-11-18 | OPEN | T2/3A | 37.8129 | -122.2188 | 2023-01-01
Sub | 123710491 | E | 2021-11-18 | OPEN | T2/3A | 37.8129 | -122.2188 | 2023-01-01
Sub | 123710498 | E | 2021-11-18 | OPEN | T2/3A | 37.8129 | -122.2188 | 2023-01-01
Sub | 123708787 | E | 2021-11-18 | OPEN | Tier 2 - Elevated | 37.9012 | -122.2865 | 2023-01-01
Sub | 123714553 | E | 2021-11-18 | OPEN | Tier 2 - Elevated | 37.885 | -122.2551 | 2023-01-01
Sub | 123720907 | E | 2021-11-18 | OPEN | T2/3A | 37.8129 | -122.2188 | 2023-01-01
Sub | 122407239 | E | 2021-11-22 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2023-01-01
Sub | 122407310 | E | 2021-11-22 | OPEN | Tier 2 - Elevated | 37.622 | -122.4467 | 2023-01-01
Sub | 122413481 | E | 2021-11-24 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 123724241 | E | 2022-05-25 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 122429393 | E | 2021-12-01 | OPEN | T2/3A | 37.9163 | -122.3031 | 2023-01-01
Sub | 121997067 | F | 2021-09-03 | OPEN | T2/3A | 37.0419 | -122.0252 | 2024-01-01
Sub | 123714502 | E | 2021-12-09 | OPEN | Tier 2 - Elevated | 37.8364 | -122.2202 | 2023-01-01
Sub | 122482733 | E | 2021-12-13 | OPEN | Tier 2 - Elevated | 38.9324 | -122.741 | 2023-01-01
Sub | 122484730 | E | 2021-12-13 | OPEN | Tier 2 - Elevated | 40.8592 | -121.7529 | 2023-01-01
Sub | 122496650 | E | 2021-12-14 | OPEN | T2/3A | 38.9729 | -123.0812 | 2023-01-01
Sub | 122548792 | E | 2021-12-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2023-01-01
Sub | 122548910 | E | 2021-12-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2023-01-01
Sub | 122495152 | E | 2021-12-16 | OPEN | Tier 2 - Elevated | 38.4808 | -120.845 | 2023-01-01
Sub | 122499489 | E | 2021-12-17 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 122499486 | E | 2021-12-17 | OPEN | T2/3A | 38.3691 | -120.7968 | 2023-01-01
Sub | 122511021 | E | 2021-12-21 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2023-01-01
Sub | 122510955 | E | 2021-12-21 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2023-01-01
Sub | 122510828 | E | 2021-12-21 | OPEN | Tier 3 - Extreme | 40.6238 | -122.4621 | 2023-01-01
Sub | 122507735 | E | 2021-12-21 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2023-01-01
Sub | 122512427 | E | 2021-12-22 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 122512482 | E | 2021-12-22 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 122512484 | E | 2021-12-22 | OPEN | T2/3A | 35.0084 | -120.4532 | 2023-01-01
Sub | 121582188 | E | 2021-06-22 | OPEN | Tier 2 - Elevated | 36.9274 | -119.0205 | 2023-01-01
Sub | 122518028 | E | 2021-12-23 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2023-01-01
Sub | 122513809 | E | 2021-12-23 | OPEN | Tier 2 - Elevated | 37.9055 | -122.2083 | 2023-01-01
Sub | 122522402 | E | 2021-12-17 | OPEN | Tier 3 - Extreme | 39.8716 | -121.6108 | 2023-01-01
Sub | 120842515 | F | 2021-04-17 | OPEN | T2/3A | 39.4056 | -123.3271 | 2024-01-01
Sub | 115787801 | F | 2019-02-05 | OPEN | Tier 2 - Elevated | 37.7448 | -121.8579 | 2024-01-01
Sub | 120858578 | F | 2021-04-17 | OPEN | T2/3A | 39.4056 | -123.3271 | 2024-01-01
Sub | 120899219 | F | 2021-04-17 | OPEN | T2/3A | 39.4056 | -123.3271 | 2024-01-01
Sub | 121362449 | E | 2021-05-18 | OPEN | Tier 2 - Elevated | 39.1293 | -123.7118 | 2023-01-01
Sub | 121373822 | E | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2023-01-01
Sub | 120845756 | F | 2021-04-19 | OPEN | T2/3A | 39.7607 | -121.6189 | 2024-01-01
Sub | 120862068 | F | 2021-04-07 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2024-01-01
Sub | 120897426 | F | 2021-04-28 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121352198 | F | 2021-05-18 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2024-01-01
Sub | 121385541 | F | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 121386556 | F | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 121525768 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121947978 | F | 2021-08-11 | OPEN | Tier 3 - Extreme | 36.3801 | -121.8993 | 2024-01-01
Sub | 120862067 | F | 2021-04-07 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2024-01-01
Sub | 120862173 | F | 2021-04-07 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2024-01-01
Sub | 120878369 | F | 2021-04-07 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2024-01-01
Sub | 121374026 | F | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 121374219 | F | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 121391156 | F | 2021-05-21 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 121391321 | F | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 121522726 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121530888 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121373828 | F | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 121379477 | F | 2021-05-21 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 120826111 | F | 2021-04-03 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2024-01-01
Sub | 120917911 | F | 2021-02-18 | OPEN | T2/3A | 39.4056 | -123.3271 | 2024-01-01
Sub | 121375322 | F | 2021-05-20 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 121389208 | F | 2021-05-22 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 121520621 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121521760 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121527551 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121756346 | F | 2021-07-19 | OPEN | Tier 2 - Elevated | 38.9123 | -123.6799 | 2024-01-01
Sub | 118723810 | F | 2019-05-02 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2024-01-01
Sub | 118723659 | F | 2019-05-02 | OPEN | Tier 2 - Elevated | 40.1714 | -121.0854 | 2024-01-01
Sub | 115054329 | F | 2018-10-11 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2024-01-01
Sub | 122544152 | E | 2021-12-31 | OPEN | T2/3A | 37.4572 | -122.2862 | 2023-01-01
Sub | 122544876 | E | 2021-12-31 | OPEN | T2/3A | 37.4572 | -122.2862 | 2023-01-01
Sub | 120827285 | F | 2021-04-01 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2024-01-01
Sub | 120926613 | F | 2021-04-17 | OPEN | T2/3A | 39.4056 | -123.3271 | 2024-01-01
Sub | 121521114 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 121521393 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 120867306 | F | 2021-04-22 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2024-01-01
Sub | 121437141 | F | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2024-01-01
Sub | 121521714 | F | 2021-06-03 | OPEN | T2/3A | 39.0078 | -122.894 | 2024-01-01
Sub | 120603692 | F | 2021-02-24 | OPEN | T2/3A | 39.4542 | -121.5178 | 2024-01-01
Sub | 120745310 | F | 2021-04-01 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2024-01-01
Sub | 120941971 | F | 2021-04-08 | OPEN | Tier 2 - Elevated | 38.9107 | -122.6174 | 2024-01-01
Sub | 121323469 | F | 2021-05-06 | OPEN | Tier 3 - Extreme | 37.1512 | -119.5048 | 2024-01-01
Sub | 121434125 | F | 2021-05-24 | OPEN | Tier 2 - Elevated | 39.0772 | -122.9325 | 2024-01-01
Sub | 119040254 | F | 2020-05-18 | OPEN | Tier 2 - Elevated | 40.086 | -121.149 | 2024-01-01
Sub | 121385686 | F | 2021-05-21 | OPEN | Tier 2 - Elevated | 39.0639 | -123.4377 | 2024-01-01
Sub | 118257492 | F | 2019-12-10 | OPEN | T2/3A | 39.4542 | -121.5178 | 2024-01-01
Sub | 114788051 | F | 2018-07-12 | OPEN | Tier 2 - Elevated | 40.8079 | -121.9358 | 2024-01-01
Sub | 122544014 | E | 2022-01-02 | OPEN | T2/3A | 40.3977 | -122.2649 | 2024-01-01
Sub | 122547417 | E | 2022-01-03 | OPEN | Tier 2 - Elevated | 37.4617 | -122.2773 | 2024-01-01
Sub | 122547728 | E | 2022-01-04 | OPEN | Tier 2 - Elevated | 39.036 | -120.988 | 2024-01-01
Sub | 122559584 | E | 2022-01-06 | OPEN | Tier 2 - Elevated | 38.4808 | -120.845 | 2024-01-01
Sub | 122551400 | E | 2021-01-05 | OPEN | Tier 3 - Extreme | 38.0121 | -122.6537 | 2024-01-01
Sub | 122603477 | E | 2022-01-07 | OPEN | T2/3A | 39.3138 | -120.4969 | 2024-01-01
Sub | 120430304 | F | 2021-01-12 | OPEN | T2/3A | 37.0419 | -122.0252 | 2025-01-01
Sub | 122621610 | E | 2022-01-15 | OPEN | T2/3A | 38.0768 | -122.5404 | 2024-01-01
Sub | 122748916 | E | 2022-01-18 | OPEN | T2/3A | 39.9392 | -120.9483 | 2024-01-01
Sub | 122774221 | E | 2022-01-20 | OPEN | Tier 3 - Extreme | 37.8479 | -122.1611 | 2024-01-01
Sub | 122886264 | E | 2022-01-25 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2024-01-01
Sub | 122882243 | E | 2022-01-26 | OPEN | Tier 2 - Elevated | 39.3193 | -120.3788 | 2024-01-01
Sub | 122886383 | E | 2022-01-26 | OPEN | T2/3A | 37.9939 | -122.1302 | 2024-01-01
Sub | 122895153 | E | 2022-01-27 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2024-01-01
Sub | 122895157 | E | 2022-01-27 | OPEN | Tier 3 - Extreme | 37.3219 | -119.6343 | 2024-01-01
Sub | 122893860 | E | 2022-01-28 | OPEN | Tier 2 - Elevated | 39.1154 | -120.953 | 2024-01-01
Sub | 122894709 | E | 2022-01-27 | OPEN | Tier 2 - Elevated | 37.2274 | -119.6908 | 2024-01-01
Sub | 122895274 | E | 2022-01-27 | OPEN | Tier 3 - Extreme | 37.3219 | -119.6343 | 2024-01-01
Sub | 122921426 | E | 2022-01-30 | OPEN | Tier 3 - Extreme | 39.3318 | -121.1014 | 2024-01-01
Sub | 122920221 | E | 2022-02-01 | OPEN | Tier 2 - Elevated | 39.3617 | -123.1277 | 2024-01-01
Sub | 122945526 | E | 2022-02-02 | OPEN | T2/3A | 39.1431 | -123.1918 | 2024-01-01
Sub | 122906340 | E | 2022-02-01 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2024-01-01
Sub | 122927131 | E | 2022-02-04 | OPEN | T2/3A | 38.3691 | -120.7968 | 2024-01-01
Sub | 122926598 | E | 2022-02-04 | OPEN | T2/3A | 35.0084 | -120.4532 | 2024-01-01
Sub | 122945120 | E | 2022-02-05 | OPEN | Tier 3 - Extreme | 35.2111 | -120.8541 | 2024-01-01
Sub | 122981337 | F | 2022-02-07 | OPEN | T2/3A | 35.374 | -120.8552 | 2025-01-01
Sub | 122945511 | E | 2022-02-08 | OPEN | Tier 2 - Elevated | 40.1028 | -123.793 | 2024-01-01
Sub | 122947634 | E | 2022-02-08 | OPEN | T2/3A | 38.3691 | -120.7968 | 2024-01-01
Sub | 122949742 | E | 2022-02-09 | OPEN | Tier 2 - Elevated | 37.0923 | -119.5526 | 2024-01-01
Sub | 122984680 | E | 2022-02-09 | OPEN | Tier 2 - Elevated | 38.7309 | -120.7836 | 2024-01-01
Sub | 122952283 | E | 2022-02-09 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2024-01-01
Sub | 122952281 | E | 2022-02-09 | OPEN | Tier 2 - Elevated | 37.0718 | -119.558 | 2024-01-01
Sub | 122980386 | E | 2022-02-10 | OPEN | Tier 2 - Elevated | 38.0027 | -122.2083 | 2024-01-01
Sub | 122969395 | E | 2022-02-11 | OPEN | Tier 2 - Elevated | 37.819 | -122.206 | 2024-01-01
Sub | 122980445 | E | 2022-02-11 | OPEN | Tier 3 - Extreme | 37.8479 | -122.1611 | 2024-01-01
Sub | 122978572 | E | 2022-02-12 | OPEN | Tier 2 - Elevated | 37.8475 | -122.2287 | 2024-01-01
Sub | 122983523 | E | 2022-02-14 | OPEN | Tier 2 - Elevated | 39.2093 | -121.061 | 2024-01-01
Sub | 122979947 | E | 2022-02-14 | OPEN | T2/3A | 40.3977 | -122.2649 | 2024-01-01
Sub | 122980572 | E | 2022-02-14 | OPEN | Tier 2 - Elevated | 37.9055 | -122.2083 | 2024-01-01
Sub | 122980570 | E | 2022-02-14 | OPEN | Tier 2 - Elevated | 37.9055 | -122.2083 | 2024-01-01
Sub | 122984425 | E | 2022-02-15 | OPEN | Tier 2 - Elevated | 39.0439 | -121.0907 | 2024-01-01
Sub | 122985144 | E | 2022-02-15 | OPEN | Tier 2 - Elevated | 37.0257 | -122.1548 | 2024-01-01
Sub | 122986003 | E | 2022-02-15 | OPEN | T2/3A | 36.9923 | -121.9822 | 2024-01-01
Sub | 122990320 | E | 2022-02-16 | OPEN | Tier 2 - Elevated | 36.5784 | -121.9085 | 2024-01-01
Sub | 123001844 | E | 2022-02-22 | OPEN | Tier 2 - Elevated | 40.2138 | -123.5964 | 2024-01-01
Sub | 118573798 | F | 2020-02-24 | OPEN | Tier 2 - Elevated | 38.7528 | -122.6087 | 2025-01-01
Sub | 123018936 | E | 2022-02-24 | OPEN | T2/3A | 35.0084 | -120.4532 | 2024-01-01
Sub | 123018931 | E | 2022-02-24 | OPEN | T2/3A | 35.374 | -120.8552 | 2024-01-01
Sub | 123032032 | E | 2022-02-25 | OPEN | T2/3A | 35.374 | -120.8552 | 2024-01-01
Sub | 123032035 | E | 2022-02-25 | OPEN | T2/3A | 35.374 | -120.8552 | 2024-01-01
Sub | 123032036 | E | 2022-02-25 | OPEN | T2/3A | 35.374 | -120.8552 | 2024-01-01
Sub | 118287059 | F | 2019-12-06 | OPEN | Tier 3 - Extreme | 38.829 | -122.8102 | 2025-01-01