## SH Workplan_2023-26_Conf
[13 empty] | 359.1663 | 956.7341 | 114.3591 | 1430.2596 | 2.7182 | 0 | 0 | 2.7182 | 44.9333 | 10.6458 | 0.8839 | 56.4631 | 184.1431 | 456.6398 | 55.6509 | 696.4338 | 127.3717 | 489.4485 | 57.8243 | 674.6445
Order | Order Description | MAT Code | Program | Circuit ID | Circuit Name | Applicable Risk Model | Circuit Protection Zone (V2) | Risk Rank (V2) | Circuit Protection Zone (CPZ) (V3) | Risk Rank (V3) | Actual or Planned Start Date | Expected End Date | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2022 Complete | UG - Pre-2022 Complete | Removal - Pre-2022 Complete | Pre-2022 Total Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles
35398090 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v3 |  | 995 | BIG MEADOWS 21012260 | 2135 | 2023-03-20 08:00 | 2023-04-24 08:00 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0
35379282 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v3 | EL DORADO PH 21026645 | 2252 | EL DORADO PH 210126000 | 1042 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35376306 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | Not Yet Available | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992
35376304 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | Not Yet Available | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45
35376303 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | Not Yet Available | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004
35374866 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | 2023-09-11 17:00 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0
35374865 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | 2023-09-12 17:00 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0
35374864 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-28 08:00 | 2023-12-27 17:00 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0
35374862 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-08-04 08:00 | 2023-11-28 17:00 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0
35374687 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-09-01 08:00 | 2023-10-16 17:00 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0
35374686 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-27 08:00 | 2023-11-21 17:00 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0
35374685 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-08-21 08:00 | 2023-12-06 17:00 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0
35374684 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-27 08:00 | 2023-11-13 17:00 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0
35374683 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-03 08:00 | 2023-10-02 17:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0
35374682 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | Not Yet Available | Not Yet Available | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0
35374559 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 21019400 | 655 | MARIPOSA 21019400 | 504 | 2023-07-03 08:00 | 2023-11-03 17:00 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0
35085847 |  | 08W | Base SH | 83692105 | ROB ROY 2105 | WDRM v2 | ROB ROY 210512474 | 3283 | ROB ROY 210512474 | 2739 | 2024-05-09 08:00 | 2024-05-24 17:00 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269
35015704 |  | 08W | Base SH | 83692105 | ROB ROY 2105 | WDRM v2 | ROB ROY 210512474 | 3283 | ROB ROY 210512474 | 2739 | 2024-05-27 08:00 | 2024-06-10 08:00 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038
35329471 |  | 08W | Base SH | 43361104 | HIGHLANDS 1104 | WDRM v2 | HIGHLANDS 1104CB | 3243 | HIGHLANDS 1104CB | 1561 | 2023-08-22 08:00 | 2024-04-17 08:00 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0
35396304 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 11062104 | 2157 | BRUNSWICK 11062104 | 429 | 2023-11-21 08:00 | 2024-04-12 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24
35373585 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 11062104 | 2157 | BRUNSWICK 11062104 | 429 | 2023-11-23 08:00 | 2024-05-15 08:00 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0
35396074 |  | 08W | Fire Rebuild | 102211103 | BUCKS CREEK 1103 | WDRM v3 |  | 1658 | BUCKS CREEK 1103CB | 404 | Not Yet Available | Not Yet Available | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0
35367518 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 | SILVERADO 2105167360 | 2174 | SILVERADO 2105167360 | 398 | 2024-02-28 08:00 | 2024-08-06 08:00 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201
35355173 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v3 | PIT NO 3 21011482 | 2320 | PIT NO 3 21011482 | 394 | 2024-04-02 08:00 | 2024-07-26 08:00 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917
35404753 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | Stanislaus 17021888 | 379 | 2023-12-11 08:00 | 2024-05-14 17:00 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74
35385890 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | STANISLAUS 17021888 | 379 | 2023-09-18 08:00 | 2024-01-23 17:00 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0
35385889 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | STANISLAUS 17021888 | 379 | 2023-10-16 08:00 | 2024-05-15 17:00 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453
35385888 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | STANISLAUS 17021888 | 379 | 2023-07-26 08:00 | 2024-01-04 17:00 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0
35373705 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | STANISLAUS 17021888 | 379 | 2023-11-08 08:00 | 2024-06-13 17:00 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517
35367520 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 | STANISLAUS 17021888 | 2386 | STANISLAUS 17021888 | 379 | 2023-07-11 08:00 | 2023-12-19 17:00 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0
35397454 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-09-14 08:00 | 2024-01-10 08:00 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778
35397453 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2024-04-09 08:00 | 2024-08-08 08:00 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302
35397452 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2024-04-09 08:00 | 2024-08-08 08:00 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074
35326790 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 | FLINT 1101958726 | 2980 | FLINT 1101958726 | 2071 | 2023-08-14 08:00 | 2023-12-18 17:00 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0
35396860 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-09-11 08:00 | 2024-01-09 08:00 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6
35396779 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-09-26 08:00 | 2024-01-10 08:00 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01
35396778 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-10-03 08:00 | 2024-01-05 08:00 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41
35396776 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-08-16 08:00 | 2024-04-11 08:00 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79
35373594 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-07-13 08:00 | 2023-11-15 08:00 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0
35373593 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-11-07 08:00 | 2024-03-25 08:00 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0
35373592 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2024-04-04 08:00 | 2024-09-03 08:00 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642
35373590 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2024-05-08 08:00 | 2024-09-06 08:00 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268
35373589 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-09-13 08:00 | 2024-01-08 08:00 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201
35367462 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 | BRUNSWICK 110651486 | 1788 | BRUNSWICK 110651486 | 315 | 2023-09-26 08:00 | 2024-04-16 08:00 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653
35396572 |  | 08W | Base SH | 083392110 | SWIFT 2110 | WDRM v3 |  | 1769 | SWIFT 2110XR332 | 276 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35374457 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 | ORO FINO 110239154 | 2575 | ORO FINO 110239154 | 273 | 2024-01-09 08:00 | 2024-08-30 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35374456 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 | ORO FINO 110239154 | 2575 | ORO FINO 110239154 | 273 | 2024-01-23 08:00 | 2025-01-16 08:00 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19
35350039 |  | 08W | Fire Rebuild | 103751102 | BIG BEND 1102 | WDRM v3 | BIG BEND 11021972 | 1288 | BIG BEND 1102884340 | 267 | Not Yet Available | Not Yet Available | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0
35396567 |  | 08W | Base SH | 103381102 | FRENCH GULCH 1102 | WDRM v3 |  | 2518 | FRENCH GULCH 11022902 | 262 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35397961 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-02-28 08:00 | 2024-07-19 08:00 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161
35397960 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-02-28 08:00 | 2024-07-15 08:00 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222
35396875 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-10 08:00 | 2024-08-27 08:00 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705
35396874 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-10 08:00 | 2024-09-11 08:00 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965
35396871 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-10 08:00 | 2024-08-06 08:00 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703
35396870 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-10 08:00 | 2024-08-21 08:00 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619
35396869 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-10 08:00 | 2024-09-03 08:00 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618
35373703 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-02-05 08:00 | 2024-06-27 08:00 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4
35373636 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 | PUEBLO 2103678 | 1224 | PUEBLO 2103678 | 255 | 2024-05-02 08:00 | 2024-12-13 08:00 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616
35373581 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 | BRUNSWICK 11021010 | 1649 | BRUNSWICK 11021010 | 234 | Not Yet Available | Not Yet Available | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598
35373536 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 | BRUNSWICK 11021010 | 1649 | BRUNSWICK 11021010 | 234 | Not Yet Available | Not Yet Available | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3
35367415 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 | BRUNSWICK 11021010 | 1649 | BRUNSWICK 11021010 | 234 | 2023-06-08 08:00 | 2024-01-25 08:00 | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01
35418371 |  | 3UG | Targeted UG | 162821701 | STANISLAUS 1701 | WDRM v3 | STANISLAUS 170179826 | 2142 | STANISLAUS 170179826 | 231 | Not Yet Available | Not Yet Available | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675
35312546 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 | FLINT 1101958726 | 2980 | FLINT 1101958726 | 2071 | 2023-09-05 08:00 | 2024-01-10 16:00 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131
35396073 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v3 |  | 1480 | KANAKA 1101CB | 212 | 2023-01-06 08:00 | 2023-03-27 08:00 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0
35373051 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v3 | KANAKA 1101CB | 1480 | KANAKA 1101CB | 212 | 2023-03-03 08:00 | 2023-04-21 08:00 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0
35402642 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 | PINE GROVE 110213438 | 204 | 2023-07-06 08:00 | Not Yet Available | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909
35402641 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 | PINE GROVE 110213438 | 2136 | PINE GROVE 110213438 | 204 | 2023-08-04 08:00 | Not Yet Available | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914
35373635 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 | PINE GROVE 110213438 | 2136 | PINE GROVE 110213438 | 204 | 2024-06-10 08:00 | 2024-11-15 08:00 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888
35367510 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 | PINE GROVE 110213438 | 2136 | PINE GROVE 110213438 | 204 | 2023-08-02 08:00 | 2024-02-07 08:00 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9
35078178 |  | 2AF | Idle Facilities | 82841101 | BIG BASIN 1101 | WDRM v2 | BIG BASIN 11015028 | 2968 | BIG BASIN 11015028 | 1102 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35221765 |  | 2AF | Idle Facilities | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 170237278 | 2810 | STANISLAUS 170237278 | 98 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
31383326 |  | 06E | Other | 43321103 | RINCON 1103 | WDRM v2 | RINCON 1103472 | 2799 | RINCON 1103472 | 7022 | 2021-06-15 | 2023-04-29 | 0.41856 | 0 | 0 | 0.41856 | 0 | 0 | 0 | 0 | 0.29867 | 0 | 0 | 0.29867 | 0.11989 | 0 | 0 | 0.11989 | 0 | 0 | 0 | 0
74001486 |  | 30A | Other | 12501105 | El Cerrito G 1105 | WDRM v2 | EL CERRITO G 1105BR160 | 2792 | El Cerrito G 1105BR160 | 2633 | 2023-04-04 08:00 | 2025-05-12 17:00 | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576
35277146 |  | 2AF | Idle Facilities | 162831702 | SPRING GAP 1702 | WDRM v2 | SPRING GAP 17029690 | 2788 | SPRING GAP 17029690 | 922 | Not Yet Available | Not Yet Available | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0
35222235 |  | 08W | Base SH | 254061102 | DUNLAP 1102 | WDRM v2 | DUNLAP 1102778286 | 2738 | DUNLAP 11027050 | 482 | 2023-09-05 08:00 | 2024-03-12 17:00 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0
35094513 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 17021804 | 2712 | STANISLAUS 17021804 | 1583 | 2022-03-14 | Not Yet Available | 1.7748 | 0.053977 | 0 | 1.8288 | 0 | 0 | 0 | 0 | 1.483 | 0.053977 | 0 | 1.5369 | 0.29186 | 0 | 0 | 0.29186 | 0 | 0 | 0 | 0
35342333 |  | 08W | Fire Rebuild | 82841101 | BIG BASIN 1101 | WDRM v2 | BIG BASIN 11015000 | 2579 | BIG BASIN 11015000 | 1120 | 2023-05-22 | 2023-07-27 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0
35237593 |  | 95F | Fire Rebuild | 82841101 | BIG BASIN 1101 | WDRM v2 | BIG BASIN 11015000 | 2579 | Big Basin 11015000 | 1120 | Not Yet Available | Not Yet Available | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0
35375180 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 193 | 2023-12-21 08:00 | 2024-06-19 08:00 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71
35376556 |  | 3UG | Targeted UG | 152301102 | BONNIE NOOK 1102 | WDRM v3 | BONNIE NOOK 1102CB | 2087 | BONNIE NOOK 1102CB | 192 | 2023-10-13 08:00 | 2024-03-14 08:00 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299
35368118 |  | 08W | Fire Rebuild | 103751102 | BIG BEND 1102 | WDRM v3 |  | 865 | BIG BEND 1102CB | 187 | 2023-03-31 08:00 | 2023-04-07 08:00 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0
35403556 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 11011802 | 1865 | FORESTHILL 11011802 | 179 | 2023-08-15 08:00 | Not Yet Available | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55
35403555 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 11011802 | 1865 | FORESTHILL 11011802 | 179 | 2023-10-10 08:00 | 2024-01-08 08:00 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172
35399834 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 11011802 | 1865 | FORESTHILL 11011802 | 179 | 2023-09-26 08:00 | 2024-02-21 08:00 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952
35373526 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 11011802 | 1865 | FORESTHILL 11011802 | 179 | 2023-10-12 08:00 | 2024-03-25 08:00 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695
35367476 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 11011802 | 1865 | FORESTHILL 11011802 | 179 | 2023-11-02 08:00 | 2024-03-01 08:00 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52
35382858 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 | LOS OSITOS 21033010 | 1509 | LOS OSITOS 21033010 | 178 | Not Yet Available | Not Yet Available | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701
35376305 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110170 | 1809 | MARIPOSA 210110170 | 137 | 2023-08-04 08:00 | 2023-09-27 17:00 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0
35374863 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110170 | 1809 | MARIPOSA 210110170 | 137 | 2023-09-01 08:00 | 2023-10-17 17:00 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0
35375511 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 | APPLE HILL 2102CB | 644 | APPLE HILL 2102836878 | 132 | 2024-01-18 08:00 | 2024-06-27 08:00 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35375510 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 | APPLE HILL 2102CB | 644 | APPLE HILL 2102836878 | 132 | 2024-01-18 08:00 | 2024-09-18 08:00 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35404716 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1102 | WDRM v3 | PINE GROVE 11026080 | 1271 | PINE GROVE 11026080 | 131 | 2023-12-15 08:00 | 2024-08-09 08:00 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96
35404715 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1102 | WDRM v3 | PINE GROVE 11026080 | 1271 | PINE GROVE 11026080 | 131 | 2023-12-15 08:00 | 2024-08-09 08:00 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65
35397963 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110240 | 679 | MARIPOSA 210110240 | 126 | 2023-10-04 08:00 | 2024-02-27 08:00 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88
35397962 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110240 | 679 | MARIPOSA 210110240 | 126 | 2023-10-04 08:00 | 2024-01-31 08:00 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2
35379383 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110240 | 679 | MARIPOSA 210110240 | 126 | 2023-09-29 08:00 | 2024-06-05 08:00 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74
35375721 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110240 | 679 | MARIPOSA 210110240 | 126 | 2023-07-28 08:00 | Not Yet Available | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004
35374681 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 | MARIPOSA 210110240 | 679 | MARIPOSA 210110240 | 126 | 2023-05-31 08:00 | 2023-09-18 17:00 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0
35373528 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 | APPLE HILL 110413512 | 1284 | APPLE HILL 110413512 | 124 | 2024-04-12 08:00 | 2024-11-06 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35373527 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 | APPLE HILL 110413512 | 1284 | APPLE HILL 110413512 | 124 | 2023-12-20 08:00 | 2024-07-25 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35396570 |  | 08W | Base SH | 163781701 | PEORIA 1701 | WDRM v3 |  | 780 | PEORIA 170190090 | 122 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35396911 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2024-03-19 08:00 | 2024-07-11 08:00 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13
35396910 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2024-03-19 08:00 | 2024-07-03 08:00 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97
35396909 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2023-09-26 08:00 | 2024-05-23 08:00 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01
35396908 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2024-02-29 08:00 | 2024-07-03 08:00 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32
35373533 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2023-08-25 08:00 | 2023-12-19 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0
35367478 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 | FORESTHILL 110150486 | 2270 | FORESTHILL 110150486 | 114 | 2024-08-07 08:00 | 2025-01-09 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04
35404726 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 | SILVERADO 210478268 | 1254 | SILVERADO 210478268 | 101 | 2023-09-26 08:00 | 2024-02-16 08:00 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88
35404352 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 | SILVERADO 210478268 | 1254 | SILVERADO 210478268 | 101 | 2023-09-21 08:00 | 2024-01-16 08:00 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029
35404351 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 | SILVERADO 210478268 | 1254 | SILVERADO 210478268 | 101 | 2023-09-21 08:00 | Not Yet Available | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632
35373704 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 | SILVERADO 210478268 | 1254 | SILVERADO 210478268 | 101 | 2024-07-03 08:00 | 2024-12-12 08:00 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648
35395931 |  | 08W | Base SH | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 | ANTLER 11011520 | 91 | 2023-08-15 08:00 | 2023-12-22 08:00 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0
35418356 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 | SILVERADO 2105616 | 2351 | SILVERADO 2105900104 | 90 | Not Yet Available | Not Yet Available | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4
35396569 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v3 |  | 1135 | KESWICK 11011588 | 83 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35396568 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v3 |  | 1135 | KESWICK 11011588 | 83 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0
35373620 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 | EL DORADO PH 2101CB | 2250 | EL DORADO PH 2101CB | 81 | 2023-12-22 08:00 | 2024-08-26 08:00 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41
35367468 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 | EL DORADO PH 2101CB | 2250 | EL DORADO PH 2101CB | 81 | 2023-12-22 08:00 | 2024-08-26 08:00 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65
35409211 |  | 3UG | Targeted UG | 152431101 | SHADY GLEN 1101 | WDRM v3 | SHADY GLEN 110132726 | 2201 | SHADY GLEN 110132726 | 71 | Not Yet Available | Not Yet Available | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3
35391472 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 | PLACERVILLE 210611132 | 1666 | PLACERVILLE 210611132 | 68 | 2023-11-30 08:00 | 2024-04-09 08:00 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799
35391471 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 | PLACERVILLE 210611132 | 1666 | PLACERVILLE 210611132 | 68 | 2023-11-30 08:00 | 2024-04-10 08:00 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201
35373532 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 | APPLE HILL 21027502 | 1505 | APPLE HILL 21027502 | 63 | 2024-06-26 08:00 | 2025-01-23 08:00 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701
35367414 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 | APPLE HILL 21027502 | 1505 | APPLE HILL 21027502 | 63 | 2024-02-09 08:00 | 2024-10-07 08:00 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75
TBD |  | 3UG | Targeted UG | 0 | 0 | WDRM v3 | APPLE HILL 21026552 | 178 | APPLE HILL 21026552 | 32 | Not Yet Available | Not Yet Available | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375
35409213 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 | APPLE HILL 1104CB | 1422 | APPLE HILL 1104CB | 30 | 2023-12-12 08:00 | 2024-04-19 08:00 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299
35235158 |  | 95F | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 | POINT MORETTI 110110726 | 2539 | Point Moretti 110110726 | 903 | Not Yet Available | Not Yet Available | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0
35211671 |  | 2AF | Idle Facilities | 152491102 | WEIMAR 1102 | WDRM v2 | WEIMAR 11022038 | 2536 | WEIMAR 11022038 | 1432 | Not Yet Available | Not Yet Available | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0
35244167 |  | 2AF | Idle Facilities | 152241101 | HALSEY 1101 | WDRM v2 | HALSEY 11011704 | 2500 | HALSEY 11011704 | 1766 | Not Yet Available | Not Yet Available | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0
35225253 |  | 2AF | Idle Facilities | 83622104 | CAMP EVERS 2104 | WDRM v2 | CAMP EVERS 21045096 | 2474 | CAMP EVERS 21045096 | 1225 | Not Yet Available | Not Yet Available | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0
35113950 |  | 08W | Base SH | 82841101 | BIG BASIN 1101 | WDRM v2 | BIG BASIN 110110296 | 2456 | BIG BASIN 110110296 | 1113 | 2022-02-05 | 2023-03-21 | 3.4441 | 0 | 0 | 3.4441 | 0 | 0 | 0 | 0 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538 | 0 | 0 | 0 | 0
35318072 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1101 | WDRM v2 | BIG BASIN 110110720 | 2435 | BIG BASIN 110110720 | 1105 | 2023-03-20 | 2023-04-10 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0
35225011 |  | 2AF | Idle Facilities | 183071101 | PERRY 1101 | WDRM v2 | PERRY 1101V74 | 2433 | PERRY 1101V74 | 2127 | Not Yet Available | Not Yet Available | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0
35224941 |  | 2AF | Idle Facilities | 183011102 | MORRO BAY 1102 | WDRM v2 | MORRO BAY 1102CB | 2399 | MORRO BAY 1102CB | 2247 | 2023-06-12 | 2023-06-12 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35225467 |  | 2AF | Idle Facilities | 83692104 | ROB ROY 2104 | WDRM v2 | ROB ROY 210410298 | 2387 | ROB ROY 210410298 | 1464 | Not Yet Available | Not Yet Available | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0
35342460 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 11025066 | 2359 | BIG BASIN 11025066 | 1314 | 2023-08-25 08:00 | 2023-11-10 08:00 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0
35372461 |  | 3UG | Targeted UG | 161380201 | TIGER CREEK 0201 | WDRM v3 | TIGER CREEK 0201CB | 1744 | TIGER CREEK 0201CB | 8 | 2024-04-02 08:00 | 2024-09-05 17:00 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42
35342336 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 11025066 | 2359 | BIG BASIN 11025066 | 1314 | 2023-08-07 | Not Yet Available | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201
35342335 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 11025066 | 2359 | BIG BASIN 11025066 | 1314 | 2023-08-07 | Not Yet Available | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299
35222036 |  | 95F | Fire Rebuild | 82841102 | Big Basin 1102 | WDRM v2 | BIG BASIN 11025066 | 2359 | Big Basin 11025066 | 1314 | Not Yet Available | Not Yet Available | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0
35334541 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 110212758 | 2358 | BIG BASIN 110212758 | 897 | 2023-03-02 | 2023-04-20 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0
35250987 |  | 95F | Fire Rebuild | 82841102 | Big Basin 1102 | WDRM v2 | BIG BASIN 110212758 | 2358 | Big Basin 110212758 | 897 | Not Yet Available | Not Yet Available | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0
35275478 |  | 2AF | Idle Facilities | 83371107 | SARATOGA 1107 | WDRM v2 | SARATOGA 1107167792 | 2354 | SARATOGA 1107167792 | 825 | Not Yet Available | Not Yet Available | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852
35292789 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012476 | 2342 | BIG MEADOWS 21012476 | 1533 | 2023-04-25 08:00 | 2023-05-30 17:00 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
35292788 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012476 | 2342 | BIG MEADOWS 21012476 | 1533 | Not Yet Available | Not Yet Available | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0
35292787 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012476 | 2342 | BIG MEADOWS 21012476 | 1533 | 2023-04-17 | 2024-02-09 16:00 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004
35294730 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 | PIT NO 3 21011482 | 2320 | PIT NO 3 21011482 | 394 | Not Yet Available | Not Yet Available | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066
35128962 |  | 08J | Other | 42761102 | FORT BRAGG A 1102 | WDRM v2 | FORT BRAGG A 110231304 | 2305 | FORT BRAGG A 110231304 | 2316 | 2024-01-08 08:00 | 2024-02-19 17:00 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288
35114040 |  | 08W | Base SH | 163751102 | PINE GROVE 1102 | WDRM v2 | PINE GROVE 11021222 | 2271 | PINE GROVE 11021222 | 558 | 2020-07-21 | 2023-03-24 | 1.3718 | 0.093561 | 0 | 1.4653 | 0 | 0 | 0 | 0 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.099242 | 0.052841 | 0 | 0.15208 | 0 | 0 | 0 | 0
35318074 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 11022253 | 2246 | BIG BASIN 11022253 | 936 | 2023-06-02 08:00 | 2023-07-20 17:00 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0
35321894 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 | POINT MORETTI 110112122 | 2199 | POINT MORETTI 110112122 | 2216 | 2023-08-31 08:00 | 2023-08-31 16:00 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0
35297464 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 | POINT MORETTI 110112122 | 2199 | POINT MORETTI 110112122 | 2216 | 2023-08-25 08:00 | 2023-09-26 17:00 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0
74028021 |  | 08W | Base SH | 42811113 | MONTE RIO 1113 | WDRM v2 | MONTE RIO 1113652 | 2192 | MONTE RIO 1113652 | 1383 | 2020-05-05 | Not Yet Available | 1.8559 | 0 | 0 | 1.8559 | 1.8402 | 0 | 0 | 1.8402 | 0 | 0 | 0 | 0 | 0.01572 | 0 | 0 | 0.01572 | 0 | 0 | 0 | 0
35284810 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 | HALF MOON BAY 11036012 | 2186 | HALF MOON BAY 11036012 | 2434 | 2023-09-25 08:00 | 2024-01-22 17:00 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602
35219543 |  | 08W | Base SH | 153081112 | PLACERVILLE 1112 | WDRM v2 | PLACERVILLE 1112CB | 2123 | PLACERVILLE 1112CB | 1979 | 2023-09-20 08:00 | 2023-10-18 08:00 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0
35244173 |  | 2AF | Idle Facilities | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 | SHINGLE SPRINGS 210911092 | 2116 | SHINGLE SPRINGS 210911092 | 237 | Not Yet Available | Not Yet Available | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0
35342339 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 | BIG BASIN 110296986 | 2070 | BIG BASIN 110296986 | 1413 | 2023-04-12 08:00 | 2023-04-19 08:00 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0
35217275 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 | HALF MOON BAY 110369412 | 2055 | HALF MOON BAY 110369412 | 2554 | 2022-11-02 | 2023-04-26 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0
35217274 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 | HALF MOON BAY 110369412 | 2055 | HALF MOON BAY 110369412 | 2554 | 2022-09-07 | Not Yet Available | 0 | 2.5239 | 0 | 2.5239 | 0 | 0 | 0 | 0 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0.88277
35228775 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1101CB | 2048 | DUNBAR 1101CB | 3020 | 2023-07-13 08:00 | Not Yet Available | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341
35228774 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1101CB | 2048 | DUNBAR 1101CB | 3020 | 2023-07-13 08:00 | Not Yet Available | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008
35223063 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1101CB | 2048 | DUNBAR 1101CB | 3020 | 2023-07-24 | 2023-08-18 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0
35285594 |  | 08W | Fire Rebuild | 158031101 | ECHO SUMMIT 1101 | WDRM v2 | ECHO SUMMIT 1101481660 | 2005 | ECHO SUMMIT 1101481660 | 2299 | 2024-04-26 08:00 | 2024-06-07 17:00 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989
35109546 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 | EL DORADO PH 210119752 | 1946 | EL DORADO PH 210119752 | 49 | 2022-08-29 | Not Yet Available | 2.3513 | 0.44621 | 0 | 2.7975 | 0 | 0 | 0 | 0 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0
35109541 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 | EL DORADO PH 210119752 | 1946 | EL DORADO PH 210119752 | 49 | 2022-08-22 | 2023-02-10 | 2.8136 | 0.37955 | 0 | 3.1932 | 0 | 0 | 0 | 0 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.61288 | 0.33883 | 0 | 0.9517 | 0 | 0 | 0 | 0
35057010 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 | EL DORADO PH 210119752 | 1946 | EL DORADO PH 210119752 | 49 | 2022-04-26 | 2023-03-31 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0
35056733 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 | EL DORADO PH 210119752 | 1946 | EL DORADO PH 210119752 | 49 | 2022-09-06 | Not Yet Available | 1.7455 | 0.57576 | 0 | 2.3212 | 0 | 0 | 0 | 0 | 1.6231 | 0 | 0 | 1.6231 | 0 | 0 | 0 | 0 | 0.12235 | 0.57576 | 0 | 0.69811
35223241 |  | 2AF | Idle Facilities | 24131102 | MENLO 1102 | WDRM v2 | MENLO 11028896 | 1917 | MENLO 11028896 | 630 | 2023-12-31 | 2023-12-31 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35320462 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105371694 | 1848 | JAMESON 1105371694 | 8953 | 2023-06-06 08:00 | Not Yet Available | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508
35120413 |  | 2AF | Idle Facilities | 42011108 | SAN RAFAEL 1108 | WDRM v2 | SAN RAFAEL 1108516 | 1837 | SAN RAFAEL 1108516 | 1001 | Not Yet Available | Not Yet Available | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0
35275962 |  | 2BF | Idle Facilities | 103561101 | STILLWATER 1101 | WDRM v2 | STILLWATER 11011320 | 1828 | STILLWATER 11011320 | 838 | 2023-06-26 | 2023-06-26 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0
35343741 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1103534 | 1827 | DUNBAR 1101534 | 440 | 2023-12-14 08:00 | 2024-01-25 08:00 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58
35312542 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1103534 | 1827 | DUNBAR 1101534 | 440 | 2023-11-21 08:00 | 2024-01-02 08:00 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77
35211297 |  | 2AF | Idle Facilities | 152491101 | WEIMAR 1101 | WDRM v2 | WEIMAR 11012084 | 1801 | WEIMAR 11012084 | 142 | Not Yet Available | Not Yet Available | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0
35221715 |  | 2AF | Idle Facilities | 163351705 | CURTIS 1705 | WDRM v2 | CURTIS 17058170 | 1770 | CURTIS 17058170 | 2025 | Not Yet Available | Not Yet Available | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0
35281758 |  | 08W | Fire Rebuild | 102530401 | GRAYS FLAT 0401 | WDRM v2 | GRAYS FLAT 0401CB | 1748 | GRAYS FLAT 0401CB | 521 | 2023-08-09 08:00 | 2023-10-06 17:00 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0
35145001 |  | 08W | Base SH | 12022215 | CLAYTON 2215 | WDRM v2 | CLAYTON 2215184604 | 1739 | CLAYTON 2215184604 | 1812 | 2022-05-06 | Not Yet Available | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756
35121520 |  | 2AF | Idle Facilities | 103271101 | ANTLER 1101 | WDRM v2 | ANTLER 11011378 | 1722 | ANTLER 11011378 | 247 | Not Yet Available | Not Yet Available | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0
35329013 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 11022094 | 1703 | CLARK ROAD 1102514690 | 933 | 2023-12-13 08:00 | 2024-04-03 08:00 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0
35329012 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 11022094 | 1703 | CLARK ROAD 1102407706 | 1009 | 2023-11-15 08:00 | 2024-02-22 08:00 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0
35299633 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 11022094 | 1703 | CLARK ROAD 1102407706 | 1009 | 2023-09-08 08:00 | 2024-01-16 08:00 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0
35244150 |  | 2AF | Idle Facilities | 152101102 | ALLEGHANY 1102 | WDRM v2 | ALLEGHANY 1102CB | 1700 | ALLEGHANY 1102CB | 41 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35284023 |  | 08W | Fire Rebuild | 43071101 | DUNBAR 1101 | WDRM v2 | DUNBAR 1101416 | 1684 | DUNBAR 1103416 | 732 | Not Yet Available | Not Yet Available | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699
35208054 |  | 2AF | Idle Facilities | 153082106 | PLACERVILLE 2106 | WDRM v2 | PLACERVILLE 210611132 | 1666 | PLACERVILLE 210611132 | 68 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0
35295446 |  | 08W | Fire Rebuild | 102211103 | BUCKS CREEK 1103 | WDRM v2 | BUCKS CREEK 1103CB | 1658 | BUCKS CREEK 1103CB | 404 | 2023-06-05 | 2023-09-30 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0
35335235 |  | 08W | Base SH | 43432104 | SILVERADO 2104 | WDRM v2 | SILVERADO 2104708 | 1648 | SILVERADO 2104708 | 619 | 2024-04-12 08:00 | 2024-07-29 17:00 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799
35211659 |  | 2AF | Idle Facilities | 152471101 | COLUMBIA HILL 1101 | WDRM v2 | COLUMBIA HILL 1101764 | 1590 | COLUMBIA HILL 1101764 | 149 | Not Yet Available | Not Yet Available | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0
35224856 |  | 10K | Other | 102831104 | Paradise 1104 | WDRM v2 | PARADISE 11042034 | 1537 | Paradise 11042034 | 362 | 2022-06-15 | Not Yet Available | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607
35329016 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110247006 | 1535 | CLARK ROAD 110247006 | 47 | 2023-09-27 08:00 | 2023-11-27 08:00 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0
35299635 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110247006 | 1535 | CLARK ROAD 110247006 | 47 | 2023-08-28 08:00 | 2023-10-13 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0
35236985 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 | KANAKA 1101CB | 1480 | KANAKA 1101CB | 212 | 2023-09-06 08:00 | 2023-10-19 10:00 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0
35334407 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-05-01 08:48 | 2023-06-07 10:00 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0
35297699 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-05-31 17:00 | 2023-07-31 17:00 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0
35297697 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-08-29 13:48 | 2023-11-10 08:48 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0
35297696 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-04-28 09:12 | 2023-10-19 09:36 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0
35297695 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-04-28 10:24 | 2023-08-04 17:00 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0
35297694 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-10-04 12:00 | 2023-12-18 12:00 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0
35297693 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-08-29 12:00 | 2023-11-01 17:00 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
35297692 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-06-19 12:00 | 2023-10-16 17:00 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0
35281816 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-05-13 08:24 | 2023-06-22 17:00 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0
35281815 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | WILLOW CREEK 11032936 | 938 | 2023-04-28 08:24 | 2023-05-31 08:24 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0
35264104 |  | 2AF | Idle Facilities | 152101101 | ALLEGHANY 1101 | WDRM v2 | ALLEGHANY 1101806 | 1446 | ALLEGHANY 1101806 | 254 | 2023-04-28 | 2023-04-28 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0
35150991 |  | 2AF | Idle Facilities | 192311142 | FRUITLAND 1142 | WDRM v2 | FRUITLAND 114263170 | 1429 | FRUITLAND 114263170 | 2354 | Not Yet Available | Not Yet Available | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0
35243441 |  | 08W | Base SH | 103201102 | CHALLENGE 1102 | WDRM v2 | CHALLENGE 11025462 | 1428 | CHALLENGE 11025462 | 408 | Not Yet Available | Not Yet Available | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233
35290901 |  | 16H | Other | 153701101 | LINCOLN 1101 | WDRM v2 | LINCOLN 11012310 | 1408 | Lincoln 1101875554 | 2686 | 2022-12-20 | 2023-04-12 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0
35242865 |  | 2AF | Idle Facilities | 24251101 | WOODSIDE 1101 | WDRM v2 | WOODSIDE 11018972 | 1376 | WOODSIDE 11018972 | 1131 | 2023-12-31 | 2023-12-31 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35353435 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 | PLACERVILLE 21067522 | 1363 | PLACERVILLE 21067522 | 277 | 2024-04-26 08:00 | 2024-08-12 17:00 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7
35233996 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 | PLACERVILLE 21067522 | 1363 | PLACERVILLE 21067522 | 277 | 2022-11-15 | 2023-04-06 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0
35233995 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 | PLACERVILLE 21067522 | 1363 | PLACERVILLE 21067522 | 277 | 2022-11-18 | 2023-04-03 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0
35290517 |  | 08W | Fire Rebuild | 103104401 | SPANISH CREEK 4401 | WDRM v2 | SPANISH CREEK 4401CB | 1322 | SPANISH CREEK 4401CB | 1064 | 2023-04-20 08:00 | 2023-05-25 08:00 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0
35282166 |  | 08W | Fire Rebuild | 103104401 | SPANISH CREEK 4401 | WDRM v2 | SPANISH CREEK 4401CB | 1322 | SPANISH CREEK 4401CB | 1064 | 2023-05-05 08:00 | 2023-09-04 08:00 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0
35145540 |  | 08W | Base SH | 163451702 | FROGTOWN 1702 | WDRM v2 | FROGTOWN 1702CB | 1316 | FROGTOWN 1702CB | 1205 | 2023-09-18 08:00 | 2023-11-27 08:00 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0
35251360 |  | 06E | Other | 42091101 | MIRABEL 1101 | WDRM v2 | MIRABEL 1101116 | 1313 | MIRABEL 1101116 | 1448 | 2023-11-01 | 2023-11-30 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0
35243442 |  | 08W | Base SH | 152201102 | PIKE CITY 1102 | WDRM v2 | PIKE CITY 1102CB | 1308 | PIKE CITY 1102CB | 162 | Not Yet Available | Not Yet Available | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319
35083699 |  | 2AF | Idle Facilities | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101176050 | 1302 | AUBERRY 1101176050 | 348 | Not Yet Available | Not Yet Available | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0
35241077 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2022-08-29 08:00 | Not Yet Available | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0
35241076 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2023-07-14 08:00 | 2023-09-18 17:00 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0
35241075 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2023-07-10 08:00 | 2023-09-13 17:00 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0
35237889 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 1103640652 | 250 | 2022-01-10 | Not Yet Available | 0 | 1.8256 | 0 | 1.8256 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0
35236997 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2023-07-05 08:00 | 2023-08-24 17:00 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0
35235675 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2023-07-05 08:00 | 2023-08-16 17:00 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0
35235672 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 | WYANDOTTE 11031976 | 1299 | WYANDOTTE 11031508 | 526 | 2023-07-05 08:00 | 2023-08-21 08:00 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0
35038684 |  | 2AF | Idle Facilities | 42681101 | LAYTONVILLE 1101 | WDRM v2 | LAYTONVILLE 1101402 | 1293 | LAYTONVILLE 1101402 | 992 | Not Yet Available | Not Yet Available | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0
35292791 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012586 | 1285 | BIG MEADOWS 21012586 | 2987 | 2022-08-08 | 2023-05-09 17:00 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0
35208094 |  | 2AF | Idle Facilities | 192221102 | GARBERVILLE 1102 | WDRM v2 | GARBERVILLE 110237054 | 1237 | GARBERVILLE 110237054 | 2057 | Not Yet Available | Not Yet Available | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0
35279307 |  | 08W | Fire Rebuild | 103021101 | GANSNER 1101 | WDRM v2 | GANSNER 11012424 | 1172 | GANSNER 11012424 | 785 | 2023-09-11 08:00 | 2023-12-13 08:00 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0
35332870 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 | CURTIS 1701CB | 1166 | CURTIS 1701CB | 1018 | 2023-06-27 08:00 | 2024-02-22 08:00 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0
35332868 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 | CURTIS 1701CB | 1166 | CURTIS 1701CB | 1018 | 2023-07-06 08:00 | 2024-03-01 08:00 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0
35312541 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 | CURTIS 1701CB | 1166 | CURTIS 1701CB | 1018 | 2023-06-07 08:00 | 2024-02-01 08:00 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0
35283938 |  | 08W | Base SH | 24251101 | WOODSIDE 1101 | WDRM v2 | WOODSIDE 11018974 | 1145 | WOODSIDE 11018974 | 1026 | 2023-12-31 | Not Yet Available | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939
35399833 |  | 08W | Base SH | 182581105 | GOLDTREE 1105 | WDRM v2 | GOLDTREE 1105CB | 1104 | GOLDTREE 1105CB | 1903 | 2023-11-03 | 2023-12-31 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0
35320444 |  | 08W | Base SH | 182581105 | GOLDTREE 1105 | WDRM v2 | GOLDTREE 1105CB | 1104 | GOLDTREE 1105CB | 1903 | 2023-09-01 | 2024-07-03 08:00 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15
35341551 |  | 08W | Base SH | 103501101 | PIT NO 7 1101 | WDRM v2 | PIT NO 7 1101CB | 1055 | PIT NO 7 1101CB | 549 | Not Yet Available | Not Yet Available | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098
35338402 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 | PANORAMA 1101CB | 1038 | PANORAMA 1101CB | 3890 | 2023-10-06 08:00 | 2023-10-27 08:00 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0
35320464 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 | PANORAMA 1101CB | 1038 | PANORAMA 1101CB | 3890 | 2023-09-15 08:00 | 2023-10-06 08:00 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0
35244146 |  | 2AF | Idle Facilities | 153662102 | APPLE HILL 2102 | WDRM v2 | APPLE HILL 2102186912 | 1035 | APPLE HILL 2102186912 | 436 | Not Yet Available | Not Yet Available | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0
35329014 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 11022070 | 1033 | CLARK ROAD 11022070 | 711 | 2023-12-18 08:00 | 2024-04-23 08:00 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0
35299634 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 11022070 | 1033 | CLARK ROAD 11022070 | 711 | 2023-07-07 08:00 | 2023-11-22 08:00 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0
35277147 |  | 2AF | Idle Facilities | 252192105 | BEAR VALLEY 2105 | WDRM v2 | BEAR VALLEY 210521160 | 1019 | BEAR VALLEY 210521160 | 433 | Not Yet Available | Not Yet Available | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0
35234526 |  | 08W | Base SH | 163541101 | MARTELL 1101 | WDRM v2 | MARTELL 1101CB | 999 | MARTELL 1101CB | 2578 | 2022-11-08 | Not Yet Available | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576
35292784 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012260 | 995 | BIG MEADOWS 21012260 | 2135 | 2023-06-07 | 2023-10-15 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0
35292780 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012260 | 995 | BIG MEADOWS 21012260 | 2135 | 2023-05-29 | 2023-06-06 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0
35290944 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012260 | 995 | BIG MEADOWS 21012260 | 2135 | 2023-04-17 | 2023-05-12 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0
35290544 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012260 | 995 | BIG MEADOWS 21012260 | 2135 | 2022-10-17 08:00 | 2023-07-10 08:00 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0
35290542 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012260 | 995 | BIG MEADOWS 21012260 | 2135 | 2023-04-19 | 2023-05-03 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0
35211643 |  | 2AF | Idle Facilities | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 11031500 | 981 | OREGON TRAIL 11031500 | 957 | Not Yet Available | Not Yet Available | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0
35343398 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-06-28 08:00 | Not Yet Available | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008
35343397 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-05-31 08:00 | Not Yet Available | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84
35343396 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-07-04 08:00 | 2023-09-29 16:00 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0
35343395 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-06-28 08:00 | 2023-08-23 08:00 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0
35343394 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-06-07 08:00 | 2023-07-17 08:00 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0
35331309 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | Not Yet Available | Not Yet Available | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992
35331308 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-06-07 08:00 | 2023-07-04 08:00 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0
35331307 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-06-12 08:00 | 2023-09-29 08:00 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0
35331306 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-05-01 08:00 | Not Yet Available | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67
35312560 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 | WYANDOTTE 1110980944 | 976 | WYANDOTTE 1110980944 | 1779 | 2023-07-12 08:00 | 2023-10-25 08:00 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0
35254948 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011596 | 966 | VOLTA 11011596 | 281 | 2023-01-23 | 2023-04-28 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0
35254947 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011596 | 966 | VOLTA 11011596 | 281 | 2023-03-27 | 2023-04-28 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0
35254946 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011596 | 966 | VOLTA 11011596 | 281 | 2023-01-23 | 2023-04-21 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0
35254945 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011596 | 966 | VOLTA 11011596 | 281 | 2023-05-01 | 2023-05-12 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0
35243453 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011596 | 966 | VOLTA 11011596 | 281 | 2022-08-29 | 2023-04-14 | 1.428 | 0 | 0 | 1.428 | 0 | 0 | 0 | 0 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205 | 0 | 0 | 0 | 0
35224438 |  | 2AF | Idle Facilities | 183101104 | CABRILLO 1104 | WDRM v2 | CABRILLO 1104Y24 | 949 | CABRILLO 1104Y24 | 2028 | Not Yet Available | Not Yet Available | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0
35292758 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2023-04-17 08:00 | 2023-04-21 17:00 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0
35292756 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2023-05-01 | 2023-06-26 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0
35292755 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2022-10-27 | 2023-06-10 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0
35292754 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2023-05-09 | 2023-06-08 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0
35290540 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2022-10-26 | 2023-05-09 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0
35280493 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2023-05-09 | 2023-06-09 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0
35279985 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 | BIG MEADOWS 21012248 | 916 | BIG MEADOWS 21012248 | 575 | 2023-05-01 | 2023-08-04 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0
35280498 |  | 08W | Fire Rebuild | 103132101 | CRESCENT MILLS 2101 | WDRM v2 | CRESCENT MILLS 21012056 | 895 | CRESCENT MILLS 21012056 | 854 | 2023-05-02 08:00 | 2023-05-10 17:00 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0
35280496 |  | 08W | Fire Rebuild | 103132101 | CRESCENT MILLS 2101 | WDRM v2 | CRESCENT MILLS 21012056 | 895 | CRESCENT MILLS 21012056 | 854 | 2023-06-06 08:00 | 2023-06-16 16:00 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0
35145458 |  | 2AF | Idle Facilities | 252192105 | BEAR VALLEY 2105 | WDRM v2 | BEAR VALLEY 2105454432 | 882 | BEAR VALLEY 2105454432 | 550 | 2023-03-27 | 2023-03-27 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0
35221620 |  | 2AF | Idle Facilities | 83242105 | MORGAN HILL 2105 | WDRM v2 | MORGAN HILL 2105XR176 | 854 | MORGAN HILL 2105XR176 | 1052 | 2023-06-30 | 2023-06-30 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0
35190945 |  | 10Q | Other | 163451702 | Frogtown 1702 | WDRM v2 | FROGTOWN 170275252 | 838 | Frogtown 170275252 | 1734 | 2022-08-22 | 2023-01-27 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0
35332718 |  | 06H | Other | 163781705 | PEORIA 1705 | WDRM v2 | PEORIA 170510580 | 835 | PEORIA 170510580 | 1778 | Not Yet Available | Not Yet Available | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015
35204814 |  | 2AF | Idle Facilities | 103601101 | WHITMORE 1101 | WDRM v2 | WHITMORE 11011598 | 820 | WHITMORE 11011598 | 1536 | Not Yet Available | Not Yet Available | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0
74010582 |  | 30A | Other | 152261107 | Diamond Springs 1107 | WDRM v2 | DIAMOND SPRINGS 11071402 | 811 | Diamond Springs 11071402 | 1184 | 2024-08-26 08:00 | 2024-12-27 17:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299
35173857 |  | 06E | Other | 43432104 | SILVERADO 2104 | WDRM v2 | SILVERADO 2104632 | 792 | SILVERADO 2104632 | 59 | 2022-10-29 | 2023-02-11 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0
35211230 |  | 2AF | Idle Facilities | 152921101 | BROWNS VALLEY 1101 | WDRM v2 | BROWNS VALLEY 110193870 | 774 | BROWNS VALLEY 110193870 | 3122 | Not Yet Available | Not Yet Available | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0
35221249 |  | 2AF | Idle Facilities | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110292622 | 771 | CLARK ROAD 110292622 | 1281 | Not Yet Available | Not Yet Available | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0
35217564 |  | 2AF | Idle Facilities | 153132101 | NARROWS 2101 | WDRM v2 | NARROWS 21011202 | 758 | NARROWS 21011202 | 2091 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35221659 |  | 2AF | Idle Facilities | 163341101 | CLAY 1101 | WDRM v2 | CLAY 110113442 | 744 | CLAY 110113442 | 2444 | 2022-09-07 | 2023-07-12 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0
35342151 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-11-06 08:00 | 2023-11-16 08:00 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0
35342148 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-10-19 08:00 | 2023-11-06 08:00 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0
35342147 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-06-14 08:00 | 2023-08-08 08:00 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0
35342146 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-06-14 08:00 | 2023-08-25 08:00 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0
35342145 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-06-14 08:00 | 2023-06-27 08:00 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0
35342144 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-10-19 08:00 | 2023-12-21 08:00 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0
35342143 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-10-19 08:00 | 2024-01-24 08:00 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0
35320442 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 | JAMESON 110265516 | 739 | JAMESON 110265516 | 313 | 2023-06-27 08:00 | 2023-07-13 08:00 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0
35337015 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 11059472 | 724 | JAMESON 11059472 | 1928 | 2023-06-13 08:00 | 2023-07-18 08:00 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0
35337014 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 11059472 | 724 | JAMESON 11059472 | 1928 | 2023-06-23 08:00 | 2023-07-28 08:00 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0
35329011 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110281296 | 698 | CLARK ROAD 110281296 | 1028 | 2023-05-09 08:00 | 2023-09-06 08:00 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0
35329010 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110281296 | 698 | CLARK ROAD 110281296 | 1028 | 2023-07-04 08:00 | 2023-08-22 08:00 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0
35329009 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110281296 | 698 | CLARK ROAD 110281296 | 1028 | 2023-04-12 08:00 | 2023-06-12 08:00 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0
35299631 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 110281296 | 698 | CLARK ROAD 110281296 | 1028 | 2023-04-24 08:00 | 2023-10-31 08:00 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0
35207962 |  | 2AF | Idle Facilities | 103601101 | WHITMORE 1101 | WDRM v2 | WHITMORE 11011594 | 678 | WHITMORE 11011594 | 1076 | Not Yet Available | Not Yet Available | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0
35026643 |  | 08W | Base SH | 152261105 | DIAMOND SPRINGS 1105 | WDRM v2 | DIAMOND SPRINGS 11052102 | 666 | DIAMOND SPRINGS 11052102 | 775 | 2022-11-04 | 2023-04-30 | 1.0733 | 0 | 0 | 1.0733 | 0 | 0 | 0 | 0 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049 | 0 | 0 | 0 | 0
35339665 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 | HORSESHOE 110150140 | 661 | HORSESHOE 110150140 | 2556 | 2023-07-10 | 2023-10-20 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0
35339664 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 | HORSESHOE 110150140 | 661 | HORSESHOE 110150140 | 2556 | 2023-07-10 | 2023-10-20 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0
35320447 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 | HORSESHOE 110150140 | 661 | HORSESHOE 110150140 | 2556 | 2023-07-10 | 2023-10-20 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0
35335287 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 11022455 | 642 | TEJON 11022455 | 72 | Not Yet Available | Not Yet Available | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799
35335286 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 11022455 | 642 | TEJON 11022455 | 72 | Not Yet Available | Not Yet Available | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21
35312553 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 11022455 | 642 | TEJON 11022455 | 72 | Not Yet Available | Not Yet Available | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39
35246501 |  | 08W | Base SH | 42561107 | FULTON 1107 | WDRM v2 | FULTON 1107604 | 637 | FULTON 1107604 | 1034 | 2023-08-09 08:00 | 2023-12-14 08:00 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0
35149235 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 | HIGHLANDS 11031282 | 626 | HIGHLANDS 11031282 | 582 | Not Yet Available | Not Yet Available | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0
35274595 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 2101309438 | 605 | MARIPOSA 2101309438 | 565 | 2023-05-08 | 2023-05-20 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0
35332866 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 | JESSUP 1103348657 | 590 | JESSUP 1103728460 | 2153 | 2023-06-29 08:00 | 2023-10-09 16:00 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0
35312549 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 | JESSUP 1103348657 | 590 | JESSUP 1103770356 | 2901 | 2023-06-19 08:00 | 2023-09-26 08:00 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0
35342313 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 1102732836 | 583 | TEJON 1102732836 | 219 | 2024-10-16 08:00 | 2025-02-03 17:00 | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902
35342312 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 1102732836 | 583 | TEJON 1102732836 | 219 | 2024-10-16 08:00 | 2025-02-03 17:00 | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591
35342311 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 1102732836 | 583 | TEJON 1102732836 | 219 | 2024-09-16 08:00 | 2025-01-02 17:00 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174
35320607 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 1102732836 | 583 | TEJON 1102732836 | 219 | Not Yet Available | Not Yet Available | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129
35312555 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 | TEJON 1102732836 | 583 | TEJON 1102732836 | 219 | 2024-09-12 08:00 | 2024-12-19 08:00 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979
35364450 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | Not Yet Available | Not Yet Available | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0
35364442 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-06-14 08:00 | 2024-09-30 17:00 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621
35364339 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-03-26 08:00 | 2024-07-10 17:00 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746
35364337 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-04-09 08:00 | 2024-07-24 17:00 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091
35364334 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-06-28 08:00 | 2024-10-14 17:00 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591
35334468 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2023-06-12 08:00 | 2024-01-29 08:00 | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77
35334467 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-03-21 08:00 | 2024-11-07 08:00 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847
35334466 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011516 | 580 | VOLTA 11011516 | 704 | 2024-07-25 08:00 | 2024-11-07 08:00 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902
35332958 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 11042070 | 568 | LINCOLN 11042070 | 3055 | 2023-06-21 08:00 | 2023-08-29 08:00 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0
35320312 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 11042070 | 568 | LINCOLN 11042070 | 3055 | 2023-05-26 08:00 | 2023-09-15 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0
35262345 |  | 2AF | Idle Facilities | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11021578 | 554 | COTTONWOOD 11021578 | 1152 | Not Yet Available | Not Yet Available | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0
35056808 |  | 30A | Other | 42571102 | Molino 1102 | WDRM v2 | MOLINO 110266006 | 534 | Molino 110266006 | 1720 | 2023-06-23 08:00 | Not Yet Available | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138
35275479 |  | 2AF | Idle Facilities | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 110180454 | 532 | VOLTA 110180454 | 1752 | 2023-05-15 | 2023-05-15 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0
35262812 |  | 06H | Other | 43351103 | LUCERNE 1103 | WDRM v2 | LUCERNE 11031280 | 512 | Lucerne 11031280 | 3737 | 2024-03-13 08:00 | 2024-06-04 17:00 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697
35260649 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N04 | 510 | OILFIELDS 1103N40 | 1729 | 2024-03-01 | 2024-05-30 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742
35335293 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 1111CB | 500 | VACAVILLE 1111CB | 1985 | 2023-10-16 08:00 | 2024-01-29 08:00 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0
35335292 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 1111CB | 500 | VACAVILLE 1111CB | 1985 | 2023-06-09 08:00 | 2023-08-14 08:00 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0
35335291 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 1111CB | 500 | VACAVILLE 1111CB | 1985 | 2023-06-09 08:00 | 2023-08-10 08:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0
35320440 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 1111CB | 500 | VACAVILLE 1111CB | 1985 | 2023-08-09 08:00 | Not Yet Available | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2
35243443 |  | 08W | Base SH | 252941107 | TIVY VALLEY 1107 | WDRM v2 | TIVY VALLEY 1107869946 | 491 | TIVY VALLEY 1107869946 | 1657 | Not Yet Available | Not Yet Available | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215
35244105 |  | 2AF | Idle Facilities | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35236439 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-08-08 | 2023-03-17 08:00 | 0.17614 | 1.2508 | 0 | 1.4269 | 0 | 0 | 0 | 0 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542 | 0 | 0 | 0 | 0
35234865 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-05-30 08:00 | 2024-01-17 17:00 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0
35234862 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-04-03 | 2023-06-22 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0
35234758 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-05-02 08:00 | 2023-03-17 08:00 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0
35234756 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-12-06 08:00 | 2024-03-13 08:00 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0
35227025 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-10-03 | 2023-02-22 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0
35227015 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-05-09 | Not Yet Available | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0
35227007 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-09-18 08:00 | 2024-01-04 08:00 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0
35227002 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-10-24 | Not Yet Available | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894
35227001 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-11-07 | 2023-04-15 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0
35226878 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-04-03 | 2023-06-24 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0
35226873 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | Not Yet Available | Not Yet Available | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0
35226862 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2022-07-27 | 2023-08-15 17:00 | 0.71326 | 0 | 0 | 0.71326 | 0 | 0 | 0 | 0 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746 | 0 | 0 | 0 | 0
35226857 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-08-15 08:00 | 2024-01-22 17:00 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0
35174501 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-05-17 08:00 | 2023-11-22 17:00 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0
35174479 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-06-06 08:00 | Not Yet Available | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96
35174478 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 1101548 | 474 | MIDDLETOWN 1101548 | 102 | 2023-03-31 | 2023-03-31 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0
35227031 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 110148212 | 468 | MIDDLETOWN 110148212 | 13 | 2023-01-30 | 2023-09-30 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0
35227030 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 110148212 | 468 | MIDDLETOWN 110148212 | 13 | 2022-08-15 | 2023-06-30 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0
35226621 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 110148212 | 468 | MIDDLETOWN 110148212 | 13 | 2024-02-20 08:00 | 2024-03-26 08:00 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107
35192282 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 | MIDDLETOWN 110148212 | 468 | MIDDLETOWN 110148212 | 13 | 2024-02-26 08:00 | 2024-04-08 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04
35340270 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 1102915324 | 457 | CORNING 1102915324 | 2905 | 2023-05-25 08:00 | 2024-01-11 08:00 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0
35311898 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 1102915324 | 457 | CORNING 1102915324 | 2905 | 2023-06-23 08:00 | 2024-02-09 08:00 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0
35274593 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 210135244 | 428 | MARIPOSA 2101151918 | 249 | 2023-07-05 | 2023-09-28 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0
35274589 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 210135244 | 428 | MARIPOSA 2101151918 | 249 | 2023-07-03 | 2023-08-04 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0
35238088 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 210135244 | 428 | MARIPOSA 2101151918 | 249 | 2022-10-31 | 2023-04-15 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
35250938 |  | 2AF | Idle Facilities | 153652108 | SHINGLE SPRINGS 2108 | WDRM v2 | SHINGLE SPRINGS 210851476 | 424 | SHINGLE SPRINGS 210851476 | 886 | Not Yet Available | Not Yet Available | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0
35330243 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-08-22 08:00 | Not Yet Available | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479
35330241 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-07-11 08:00 | 2023-10-25 16:00 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0
35330219 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-07-21 08:00 | 2023-11-06 16:00 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0
35330217 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-10-04 08:00 | 2023-11-08 08:00 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0
35330216 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-11-13 08:00 | 2024-01-16 08:00 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0
35330215 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | Not Yet Available | Not Yet Available | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0
35330213 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2024-05-13 08:00 | 2024-12-09 17:00 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26
35330211 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-10-25 08:00 | 2023-12-26 08:00 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0
35317399 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-07-04 08:00 | 2023-09-15 08:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0
35312550 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101323962 | 423 | REDBUD 1101323962 | 127 | 2023-08-04 08:00 | 2023-10-30 16:00 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0
35241060 |  | 08W | Base SH | 254421101 | OAKHURST 1101 | WDRM v2 | OAKHURST 110110090 | 421 | OAKHURST 110110090 | 913 | 2022-09-09 | 2023-03-31 17:00 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0
35320463 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105913400 | 419 | JAMESON 1105913400 | 987 | 2023-06-28 08:00 | 2023-08-02 08:00 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0
35221246 |  | 2AF | Idle Facilities | 42601101 | PHILO 1101 | WDRM v2 | PHILO 11013700 | 417 | PHILO 11013700 | 1638 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35380377 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0
35380376 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-11-01 08:00 | 2024-02-21 17:00 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0
35380375 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0
35380374 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0
35380373 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-11-06 08:00 | 2024-02-26 17:00 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0
35380372 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-11-13 08:00 | 2024-03-04 17:00 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0
35380371 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-12-22 08:00 | 2024-04-10 17:00 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0
35380370 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-10-16 08:00 | 2024-02-02 17:00 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0
35380369 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-09-05 08:00 | 2023-12-20 17:00 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0
35380368 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-09-21 08:00 | 2024-01-09 17:00 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0
35380365 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-09-27 08:00 | 2024-01-16 17:00 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0
35334230 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701
35334229 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-09-05 08:00 | 2023-12-20 17:00 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0
35311897 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2023-09-01 08:00 | 2024-04-19 08:00 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0
35276100 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008
35229051 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 | CORNING 110253184 | 413 | CORNING 110253184 | 694 | 2022-12-02 | 2023-04-15 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
35285065 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 110537476 | 396 | POTTER VALLEY P H 110537476 | 2321 | 2023-03-31 | 2023-03-31 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0
35285064 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 110537476 | 396 | POTTER VALLEY P H 110537476 | 2321 | 2023-03-31 | 2023-03-31 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0
35339293 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-05-30 08:00 | 2023-07-11 08:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0
35338410 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-06 08:00 | 2023-09-05 08:00 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0
35338409 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-27 08:00 | 2023-09-26 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0
35338408 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-21 08:00 | 2023-07-26 08:00 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0
35338407 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-09 08:00 | 2023-07-07 08:00 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0
35338406 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-30 08:00 | 2023-08-04 08:00 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0
35338405 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-23 08:00 | 2023-09-29 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0
35338404 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-23 08:00 | 2023-07-28 08:00 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0
35320461 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-16 08:00 | 2023-10-13 08:00 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0
35320460 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 | JAMESON 1105466348 | 393 | JAMESON 1105466348 | 728 | 2023-06-15 08:00 | 2023-08-31 08:00 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0
35339289 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-04-25 08:00 | 2023-06-26 08:00 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0
35339288 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-04-25 08:00 | 2023-08-01 08:00 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0
35339287 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-04-25 08:00 | 2023-08-01 08:00 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0
35339286 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-07-14 08:00 | 2023-07-14 08:00 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0
35339285 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-07-18 08:00 | 2023-09-13 08:00 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0
35339283 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-07-13 08:00 | 2023-09-25 08:00 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0
35339282 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-07-06 08:00 | 2023-07-20 08:00 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0
35337011 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-06-07 08:00 | 2023-09-27 08:00 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0
35337010 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-06-07 08:00 | 2023-09-13 08:00 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0
35337008 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-06-07 08:00 | 2023-08-16 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0
35317887 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-04-25 08:00 | 2023-07-25 08:00 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0
35317480 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-08-30 08:00 | 2023-10-19 08:00 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0
35312548 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 | JESSUP 11021550 | 389 | JESSUP 11021550 | 1853 | 2023-07-14 08:00 | 2023-11-07 08:00 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0
35280560 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 | BUCKS CREEK 1102CB | 378 | BUCKS CREEK 1102CB | 45 | 2023-03-16 | 2023-09-05 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0
35280499 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 | BUCKS CREEK 1102CB | 378 | BUCKS CREEK 1102CB | 45 | 2023-03-16 | 2023-09-05 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0
35279182 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 | BUCKS CREEK 1102CB | 378 | BUCKS CREEK 1102CB | 45 | 2023-03-16 | 2023-09-05 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0
35279181 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 | BUCKS CREEK 1102CB | 378 | BUCKS CREEK 1102CB | 45 | 2023-03-16 | 2023-09-05 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0
35192280 |  | 08W | Base SH | 12022212 | CLAYTON 2212 | WDRM v2 | CLAYTON 221296224 | 377 | CLAYTON 221296224 | 15 | 2023-03-20 | 2023-06-30 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0
35223030 |  | 08W | Base SH | 103191101 | BANGOR 1101 | WDRM v2 | BANGOR 1101CB | 355 | BANGOR 1101CB | 2768 | 2022-08-01 | Not Yet Available | 0.28352 | 1.1968 | 0 | 1.4803 | 0 | 0 | 0 | 0 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.060417 | 0 | 0.060417 | 0 | 0 | 0 | 0
35330249 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-04-03 | 2023-07-21 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0
35330248 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2024-01-25 08:00 | 2024-05-22 08:00 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4
35330247 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-04-10 | 2023-05-05 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0
35330246 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-05-08 | 2023-06-02 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0
35330245 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-04-03 | 2023-04-07 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0
35330244 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-06-05 | 2023-06-23 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0
35329474 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101754544 | 375 | 2023-10-25 08:00 | 2023-11-23 08:00 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0
35317398 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101754544 | 375 | 2023-10-24 08:00 | 2024-02-06 08:00 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201
35312552 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2023-05-23 08:00 | 2023-06-28 17:00 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0
35208096 |  | 2AF | Idle Facilities | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101708166 | 345 | REDBUD 1101708166 | 679 | 2021-11-05 | 2023-06-02 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0
35083879 |  | 2AF | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 | SAND CREEK 1103CB | 337 | SAND CREEK 1103CB | 2377 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35285251 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-06-30 | 2023-09-30 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0
35285249 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-05-08 | 2023-12-08 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0
35283346 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-05-01 | 2023-09-30 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0
35283343 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-06-05 | 2023-09-30 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0
35256083 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-01-30 | 2023-06-30 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0
35256082 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 11011276 | 335 | UPPER LAKE 11011276 | 35 | 2023-12-31 | 2023-12-31 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0
35083893 |  | 2AF | Idle Facilities | 13751102 | VASCO 1102 | WDRM v2 | VASCO 1102MR176 | 324 | VASCO 1102MR176 | 764 | 2023-03-17 | 2023-03-17 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0
35134959 |  | 06A | Other | 163231101 | NORTH BRANCH 1101 | WDRM v2 | NORTH BRANCH 1101CB | 322 | NORTH BRANCH 1101CB | 1048 | 2023-12-22 08:00 | 2024-03-28 17:00 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447
35332364 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-08-01 08:00 | 2023-08-29 08:00 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0
35332363 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-07-26 08:00 | 2023-10-26 16:00 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0
35332362 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-07-19 08:00 | 2024-03-29 16:00 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0
35332361 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | Not Yet Available | Not Yet Available | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2
35332360 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-07-13 08:00 | 2024-07-11 08:00 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0
35330813 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | Not Yet Available | Not Yet Available | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74
35330812 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-05-04 08:00 | 2023-08-24 08:00 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0
35316278 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-05-18 08:00 | 2023-12-21 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0
35312543 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 11012002 | 315 | ELK CREEK 11012002 | 1044 | 2023-06-02 08:00 | 2023-08-21 17:00 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0
35329473 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101454 | 312 | REDBUD 1101454 | 44 | 2024-01-12 08:00 | 2024-06-17 16:00 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761
35329472 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101454 | 312 | REDBUD 1101454 | 44 | 2023-11-29 08:00 | 2024-03-20 16:00 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0
35312551 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 | REDBUD 1101454 | 312 | REDBUD 1101454 | 44 | 2023-12-22 08:00 | 2024-04-15 16:00 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0
35349646 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102CB | 307 | BUELLTON 1102CB | 2847 | Not Yet Available | Not Yet Available | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95
35349645 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102CB | 307 | BUELLTON 1102CB | 2847 | Not Yet Available | Not Yet Available | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199
35349643 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102CB | 307 | BUELLTON 1102CB | 2847 | Not Yet Available | Not Yet Available | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59
35279629 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N52 | 291 | PASO ROBLES 1103N52 | 311 | 2024-03-01 | 2024-05-30 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534
35279628 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N52 | 291 | PASO ROBLES 1103N52 | 311 | 2024-04-01 | 2024-06-30 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023
35254252 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N52 | 291 | PASO ROBLES 1103N52 | 311 | 2023-05-09 | 2023-07-30 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0
35277935 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2839 | 274 | AUBERRY 1101R2839 | 614 | 2023-05-15 | 2023-06-09 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0
35332217 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-05-01 08:00 | 2023-08-01 08:00 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0
35332216 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-04-24 08:00 | 2023-06-05 08:00 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0
35332215 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-04-24 08:00 | 2023-07-03 08:00 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0
35332214 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-05-08 08:00 | 2023-09-05 08:00 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0
35316569 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-04-19 08:00 | 2023-09-27 08:00 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0
35316567 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-03-27 | 2023-09-08 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0
35312540 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 11029026 | 271 | COTTONWOOD 11029026 | 2723 | 2023-04-17 | 2023-09-15 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0
35349651 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102Y50 | 269 | BUELLTON 1102Y50 | 2607 | Not Yet Available | Not Yet Available | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951
35349650 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102Y50 | 269 | BUELLTON 1102Y50 | 2607 | 2024-04-09 08:00 | 2024-07-02 17:00 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843
35349649 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102Y50 | 269 | BUELLTON 1102Y50 | 2607 | 2024-05-13 08:00 | 2024-07-16 17:00 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108
35349648 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102Y50 | 269 | BUELLTON 1102Y50 | 2607 | 2024-04-24 08:00 | 2024-06-06 08:00 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962
35349647 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 | BUELLTON 1102Y50 | 269 | BUELLTON 1102Y50 | 2607 | 2024-04-11 08:00 | 2024-05-08 17:00 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398
35329008 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 1102CB | 268 | CLARK ROAD 1102CB | 2491 | 2023-07-25 08:00 | 2023-09-11 08:00 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0
35299629 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 | CLARK ROAD 1102CB | 268 | CLARK ROAD 1102CB | 2491 | 2024-05-07 08:00 | 2024-06-24 08:00 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091
35330815 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 | ANDERSON 1103226050 | 262 | ANDERSON 1103226050 | 3263 | 2023-07-10 | 2023-09-01 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0
35311895 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 | ANDERSON 1103226050 | 262 | ANDERSON 1103226050 | 3263 | 2023-05-22 | 2023-09-22 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0
35279626 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 11032731 | 260 | PASO ROBLES 1103N54 | 940 | 2023-04-21 | 2023-05-16 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0
35254254 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 11032731 | 260 | PASO ROBLES 1103N54 | 940 | 2023-03-28 | 2023-06-02 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0
35151005 |  | 2AF | Idle Facilities | 42871101 | UPPER LAKE 1101 | WDRM v2 | UPPER LAKE 1101412 | 259 | UPPER LAKE 1101412 | 327 | Not Yet Available | Not Yet Available | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0
35279631 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N58 | 257 | PASO ROBLES 1103N58 | 771 | 2022-06-14 | 2023-05-05 | 3.064 | 0 | 0 | 3.064 | 0 | 0 | 0 | 0 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417 | 0 | 0 | 0 | 0
35254248 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N58 | 257 | PASO ROBLES 1103N58 | 771 | 2024-08-01 | 2024-09-30 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299
35225318 |  | 2AF | Idle Facilities | 183031101 | PALMER 1101 | WDRM v2 | PALMER 1101M84 | 256 | PALMER 1101M84 | 2229 | 2023-07-24 | 2023-07-24 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0
35337306 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 1702CB | 235 | STANISLAUS 1702CB | 54 | 2023-03-27 | 2023-07-31 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0
35284366 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 1702CB | 235 | STANISLAUS 1702CB | 54 | Not Yet Available | Not Yet Available | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0
35284365 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 1702CB | 235 | STANISLAUS 1702CB | 54 | 2023-06-27 08:00 | 2023-12-25 17:00 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0
35284364 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 1702CB | 235 | STANISLAUS 1702CB | 54 | 2023-03-27 | 2023-06-30 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0
35250577 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 | STANISLAUS 1702CB | 235 | STANISLAUS 1702CB | 54 | 2023-01-23 | 2023-06-30 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0
35349244 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104685276 | 230 | LINCOLN 1104685276 | 4147 | 2023-06-26 08:00 | 2023-09-22 16:00 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0
35339292 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104685276 | 230 | LINCOLN 1104685276 | 4147 | Not Yet Available | Not Yet Available | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0
35339291 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104685276 | 230 | LINCOLN 1104685276 | 4147 | Not Yet Available | Not Yet Available | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29
35339290 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104685276 | 230 | LINCOLN 1104685276 | 4147 | Not Yet Available | Not Yet Available | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65
35320450 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104685276 | 230 | LINCOLN 1104685276 | 4147 | 2023-06-30 08:00 | 2023-10-06 08:00 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0
35211757 |  | 2AF | Idle Facilities | 103191101 | BANGOR 1101 | WDRM v2 | BANGOR 110131502 | 225 | BANGOR 110131502 | 2534 | Not Yet Available | Not Yet Available | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0
35223039 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 | WYANDOTTE 1109702710 | 218 | WYANDOTTE 1109702710 | 2461 | 2022-06-06 | Not Yet Available | 0.076705 | 0.53561 | 0 | 0.61231 | 0 | 0 | 0 | 0 | 0.062879 | 0.40985 | 0 | 0.47273 | 0 | 0 | 0 | 0 | 0.013826 | 0.12576 | 0 | 0.13958
35223615 |  | 08W | Base SH | 42991105 | LAS GALLINAS A 1105 | WDRM v2 | LAS GALLINAS A 110599904 | 215 | LAS GALLINAS A 110599904 | 1267 | 2023-05-26 08:00 | 2023-09-14 17:00 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0
35150641 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 | HIGHLANDS 1103568 | 212 | HIGHLANDS 1103568 | 847 | Not Yet Available | Not Yet Available | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0
35312544 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 | ELK CREEK 110193504 | 206 | ELK CREEK 110193504 | 1350 | 2023-04-24 | 2023-05-19 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0
35262347 |  | 2AF | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 | SAND CREEK 110345190 | 195 | SAND CREEK 110345190 | 1266 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0
35215883 |  | 2AA | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 | SAND CREEK 110345190 | 195 | SAND CREEK 110345190 | 1266 | Not Yet Available | Not Yet Available | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0
35335290 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 111113652 | 190 | VACAVILLE 111113652 | 1722 | 2023-08-08 08:00 | 2024-01-02 08:00 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0
35320441 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 | VACAVILLE 111113652 | 190 | VACAVILLE 111113652 | 1722 | 2023-08-08 08:00 | 2023-11-17 08:00 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0
35337164 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104275986 | 185 | LINCOLN 1104275986 | 2971 | 2024-05-13 08:00 | 2024-09-16 17:00 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301
35337163 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104275986 | 185 | LINCOLN 1104275986 | 2971 | 2023-05-17 08:00 | 2023-09-11 16:00 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0
35320449 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 1104275986 | 185 | LINCOLN 1104275986 | 2971 | 2023-04-27 08:00 | 2023-07-28 08:00 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0
35208097 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 | HIGHLANDS 1103482 | 181 | HIGHLANDS 1103482 | 270 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0
35254266 |  | 08W | Base SH | 63681102 | PUTAH CREEK 1102 | WDRM v2 | PUTAH CREEK 11028352 | 171 | PUTAH CREEK 11028352 | 712 | 2023-03-27 | 2023-03-31 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0
35240173 |  | 08W | Base SH | 63681102 | PUTAH CREEK 1102 | WDRM v2 | PUTAH CREEK 11028352 | 171 | PUTAH CREEK 11028352 | 712 | 2023-04-10 | 2023-05-01 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0
35310704 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-05-25 08:00 | Not Yet Available | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196
35305312 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-08 08:00 | 2024-04-19 16:00 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792
35305311 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201
35305310 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771
35305309 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-12 08:00 | 2024-06-17 17:00 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229
35305308 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-07-17 08:00 | Not Yet Available | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799
35305307 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-09 08:00 | 2024-05-06 16:00 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741
35305306 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-09 08:00 | 2024-05-13 16:00 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398
35305305 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522
35305304 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-02-08 08:00 | 2024-06-14 16:00 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205
35305303 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-05-09 08:00 | 2023-08-16 16:00 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0
35293670 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-05-13 | 2023-05-28 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0
35293669 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-11 08:00 | 2024-07-22 17:00 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299
35293668 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44
35293667 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65
35293666 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992
35293665 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-02-13 | 2023-04-26 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0
35293664 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-01 08:00 | 2024-07-12 17:00 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8
35293663 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-05-01 | Not Yet Available | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996
35293662 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2023-03-16 | 2023-05-12 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0
35254071 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65
35254070 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | MOUNTAIN QUARRIES 21011350 | 401 | 2024-03-08 08:00 | 2024-07-08 17:00 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701
35278892 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-12-03 | 2024-12-31 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299
35278891 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-12-03 | 2024-12-31 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5
35278890 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-12-03 | 2024-12-31 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75
35278097 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2022-08-30 | 2023-05-12 | 1.286 | 0 | 0.20095 | 1.4869 | 0 | 0 | 0 | 0 | 0.66345 | 0 | 0 | 0.66345 | 0.62254 | 0 | 0.20095 | 0.82348 | 0 | 0 | 0 | 0
35278092 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-04-01 | 2024-06-30 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369
35278091 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-03-01 | 2024-05-31 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839
35277938 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-06-05 | 2023-08-18 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0
35277937 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-01-02 | 2024-03-15 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004
35277936 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-06-06 | 2023-11-30 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0
35277924 |  | 08W | Base SH | 254151105 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-05-22 | 2023-08-25 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0
35277923 |  | 08W | Base SH | 254151104 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-06-06 | 2023-11-30 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0
35277922 |  | 08W | Base SH | 254151103 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-04-01 | 2024-06-30 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76
35277921 |  | 08W | Base SH | 254151102 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-03-01 | 2024-05-30 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994
35254247 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-11-05 | 2024-12-31 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95
35254245 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-09-05 | 2023-12-29 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0
35254244 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2023-05-12 | 2023-06-30 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0
35254243 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101R2578 | 163 | AUBERRY 1101R2578 | 569 | 2024-02-01 | 2024-04-28 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083
35226852 |  | 08W | Base SH | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 | SHINGLE SPRINGS 210935598 | 159 | SHINGLE SPRINGS 210935598 | 241 | 2023-01-24 | 2023-05-30 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0
35062376 |  | 08W | Base SH | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 | SHINGLE SPRINGS 210935598 | 159 | SHINGLE SPRINGS 210935598 | 241 | 2022-08-10 | 2023-06-02 | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0
35254651 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 110153118 | 157 | VOLTA 110153118 | 280 | 2022-05-23 | 2023-04-05 | 2.4038 | 0 | 0 | 2.4038 | 0 | 0 | 0 | 0 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0 | 0 | 0
35254650 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 110153118 | 157 | VOLTA 110153118 | 280 | 2022-10-10 | Not Yet Available | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.30436 | 0 | 0.30436 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | 0 | 0
35264190 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-03-27 | 2023-05-22 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0
35264189 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-01-23 | 2023-05-22 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0
35264188 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2022-12-05 | 2023-04-01 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0
35264187 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-05-31 08:00 | 2023-07-31 17:00 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0
35264185 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-02-13 | 2023-02-17 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0
35240223 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-01-23 | 2023-05-22 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0
35240222 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y66 | 153 | SANTA YNEZ 1104Y66 | 1417 | 2023-03-07 08:00 | 2023-04-18 08:00 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0
35325590 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 | FLINT 1101750 | 152 | FLINT 1101750 | 1508 | 2023-10-02 08:00 | 2023-12-18 08:00 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0
35325589 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 | FLINT 1101750 | 152 | FLINT 1101750 | 1508 | 2023-09-01 08:00 | 2023-11-20 16:00 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0
35312545 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 | FLINT 1101750 | 152 | FLINT 1101750 | 1508 | 2023-08-01 08:00 | 2023-09-06 16:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0
35249999 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 210410030 | 144 | COARSEGOLD 210410030 | 2787 | 2022-08-02 | 2023-03-31 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0
35249998 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 210410030 | 144 | COARSEGOLD 210410030 | 2787 | 2022-05-01 | Not Yet Available | 3.4638 | 0 | 0 | 3.4638 | 0 | 0 | 0 | 0 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572 | 0 | 0 | 0 | 0
35331305 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 | ANDERSON 11031600 | 143 | ANDERSON 11031600 | 3058 | 2023-05-29 | 2023-07-21 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0
35298571 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 | ANDERSON 11031600 | 143 | ANDERSON 11031600 | 3058 | 2023-06-26 | 2023-07-21 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0
35279627 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N50 | 138 | PASO ROBLES 1103N50 | 742 | 2024-02-07 | 2024-04-30 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269
35249877 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21046210 | 132 | COARSEGOLD 21046210 | 1380 | 2023-10-03 08:00 | 2024-04-10 17:00 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0
35249876 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21046210 | 132 | COARSEGOLD 21046210 | 1380 | 2022-09-05 | 2023-04-28 | 3.7142 | 0 | 0 | 3.7142 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693 | 0 | 0 | 0 | 0
35249875 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21046210 | 132 | COARSEGOLD 21046210 | 1380 | 2022-09-05 | 2023-05-26 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0
35240165 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21046210 | 132 | COARSEGOLD 21046210 | 1380 | 2022-09-30 | 2023-05-26 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0
35332218 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 1102544790 | 123 | COTTONWOOD 1102544790 | 1675 | 2023-06-09 08:00 | 2023-09-29 08:00 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0
35332213 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 1102544790 | 123 | COTTONWOOD 1102544790 | 1675 | 2023-07-21 08:00 | 2023-11-23 16:00 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0
35316561 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 1102544790 | 123 | COTTONWOOD 1102544790 | 1675 | 2023-07-17 | 2023-09-08 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0
35311899 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 | COTTONWOOD 1102544790 | 123 | COTTONWOOD 1102544790 | 1675 | 2023-06-06 08:00 | 2023-10-03 08:00 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0
35334755 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 110838316 | 122 | VACAVILLE 110838316 | 491 | 2023-10-27 08:00 | 2023-12-19 08:00 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0
35334754 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 110838316 | 122 | VACAVILLE 110838316 | 491 | 2023-10-10 08:00 | 2024-02-28 08:00 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0
35334753 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 110838316 | 122 | VACAVILLE 110838316 | 491 | 2023-06-12 | 2023-09-29 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0
35320339 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 110838316 | 122 | VACAVILLE 110838316 | 491 | 2023-10-10 08:00 | 2024-01-31 08:00 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0
35320336 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 110838316 | 122 | VACAVILLE 110838316 | 491 | 2023-06-12 | 2024-05-09 17:00 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3
35334234 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-25 08:00 | 2024-07-25 08:00 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3
35334233 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-06-03 08:00 | 2024-10-07 17:00 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49
35334232 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-05-01 08:00 | 2024-06-19 08:00 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01
35334231 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-05-08 08:00 | 2024-09-12 16:00 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3
35333510 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-29 08:00 | 2024-09-02 17:00 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996
35333509 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-02 08:00 | 2024-08-12 17:00 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41
35333508 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51
35333507 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4
35333506 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76
35333505 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | Not Yet Available | Not Yet Available | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0
35333504 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2023-09-05 08:00 | 2023-09-26 08:00 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0
35333503 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2023-09-05 08:00 | 2023-11-02 08:00 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0
35333502 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | Not Yet Available | Not Yet Available | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0
35333501 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2023-10-18 08:00 | 2024-01-26 08:00 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96
35333500 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | Not Yet Available | Not Yet Available | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0
35314416 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-05-20 08:00 | 2024-07-22 08:00 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002
35314415 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2023-09-29 08:00 | Not Yet Available | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09
35311896 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 | BELL 11082202 | 118 | BELL 11082202 | 2685 | 2024-05-01 08:00 | 2024-08-07 08:00 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76
35149246 |  | 2AF | Idle Facilities | 42251101 | HOPLAND 1101 | WDRM v2 | HOPLAND 1101768 | 110 | HOPLAND 1101768 | 519 | 2022-12-20 | Not Yet Available | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0
35264182 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y04 | 108 | SANTA YNEZ 1104Y04 | 2888 | 2022-10-04 | 2023-03-03 08:00 | 2.6348 | 0 | 0 | 2.6348 | 0 | 0 | 0 | 0 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765 | 0 | 0 | 0 | 0
35264181 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 | SANTA YNEZ 1104Y04 | 108 | SANTA YNEZ 1104Y04 | 2888 | 2022-10-29 | 2023-02-16 | 2.7506 | 0 | 0 | 2.7506 | 0 | 0 | 0 | 0 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585 | 0 | 0 | 0 | 0
35259512 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 | DESCHUTES 11041370 | 100 | DESCHUTES 11041370 | 2704 | 2023-01-16 | 2023-01-31 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0
35254940 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011568 | 85 | VOLTA 11011568 | 2428 | Not Yet Available | Not Yet Available | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0
35254738 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011568 | 85 | VOLTA 11011568 | 2428 | Not Yet Available | Not Yet Available | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0
35254658 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011568 | 85 | VOLTA 11011568 | 2428 | 2022-06-22 08:00 | Not Yet Available | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | 0 | 0
35243444 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 11011568 | 85 | VOLTA 11011568 | 2428 | 2022-10-31 08:00 | 2024-04-02 17:00 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
35240164 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 2104570682 | 78 | COARSEGOLD 2104570682 | 1728 | 2023-03-22 | 2023-06-23 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0
35254259 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 1101CB | 76 | VOLTA 1101CB | 2202 | 2023-02-06 | 2023-03-31 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0
35254258 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 1101CB | 76 | VOLTA 1101CB | 2202 | 2022-09-05 | 2023-04-07 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0
35240166 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 | VOLTA 1101CB | 76 | VOLTA 1101CB | 2202 | 2022-03-28 | 2023-01-27 | 0.46326 | 0.015341 | 0 | 0.4786 | 0 | 0 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0
35293846 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-24 | 2023-05-19 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0
35293845 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-02-13 | 2023-04-28 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0
35293844 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-01-24 | 2023-04-28 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0
35293843 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-06 08:00 | 2023-06-13 17:00 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0
35293841 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-04-02 08:00 | 2024-06-20 17:00 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5
35293775 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-01-23 | 2023-04-10 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0
35293774 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-01-15 08:00 | 2024-03-07 17:00 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699
35293770 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-09-04 08:00 | Not Yet Available | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9
35290808 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-10 | 2023-04-28 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0
35290807 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-05-09 08:00 | 2024-07-04 17:00 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699
35290509 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-09-18 08:00 | 2024-11-05 17:00 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09
35290508 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-09-18 08:00 | 2023-11-20 17:00 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0
35290507 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-02-26 08:00 | 2024-03-22 17:00 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992
35290506 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-06-14 08:00 | 2024-07-25 17:00 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09
35290504 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-06-26 08:00 | 2023-07-31 08:00 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0
35290503 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-09-10 08:00 | 2024-10-22 08:00 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157
35290502 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | Not Yet Available | Not Yet Available | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299
35290501 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-07-02 08:00 | 2024-09-10 17:00 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64
35290500 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-10 | 2023-04-10 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0
35290299 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-01-24 | 2023-04-28 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0
35290298 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-01-24 | 2023-04-28 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0
35290297 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-17 08:00 | 2023-09-07 17:00 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0
35290296 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-06-05 08:00 | 2023-08-15 17:00 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0
35290295 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-06-05 08:00 | 2023-07-28 17:00 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0
35254076 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2024-09-18 08:00 | 2024-10-23 17:00 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992
35254075 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | Not Yet Available | Not Yet Available | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0
35254074 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-05 08:00 | 2023-05-09 17:00 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0
35254073 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | POTTER VALLEY P H 11051904 | 573 | 2023-04-17 08:00 | 2023-07-13 08:00 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0
35278888 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2024-02-11 | 2024-04-30 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39
35278887 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2022-12-27 | 2023-04-14 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0
35278884 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2023-05-09 | 2023-07-30 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0
35278883 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2023-03-28 | 2023-07-01 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0
35278882 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2022-08-16 | 2023-05-05 | 2.6322 | 0 | 0 | 2.6322 | 0 | 0 | 0 | 0 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701 | 0 | 0 | 0 | 0
35278881 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2023-03-28 | 2023-07-10 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0
35254249 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 | PASO ROBLES 1103N54 | 69 | PASO ROBLES 1103N54 | 940 | 2022-09-06 | 2023-04-07 | 2.6725 | 0 | 0 | 2.6725 | 0 | 0 | 0 | 0 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267 | 0 | 0 | 0 | 0
35301114 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-05-22 08:00 | 2024-10-02 17:00 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695
35301113 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-18 08:00 | 2024-08-29 17:00 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7
35301112 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2023-04-10 | 2023-06-23 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0
35300934 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-22 08:00 | 2024-09-02 17:00 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409
35300933 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2023-03-06 | 2023-05-12 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0
35293847 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-24 08:00 | 2024-08-13 17:00 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636
35293677 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-05-07 08:00 | 2024-08-26 17:00 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989
35293676 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-04 08:00 | 2024-08-15 17:00 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201
35293675 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-06-20 08:00 | 2024-10-02 17:00 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528
35293674 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-17 08:00 | 2024-08-28 17:00 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61
35293673 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-06-06 08:00 | 2024-10-17 17:00 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534
35293672 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-02-27 08:00 | 2024-06-11 17:00 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322
35293509 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-24 08:00 | 2024-09-04 17:00 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441
35293508 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2023-05-01 | 2023-05-26 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0
35293507 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-05-08 08:00 | 2024-10-28 17:00 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201
35293506 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-24 08:00 | 2024-09-04 17:00 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083
35293505 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-05-01 08:00 | 2024-09-11 17:00 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019
35254069 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-12 08:00 | 2024-08-23 17:00 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778
35254068 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2024-04-18 08:00 | 2024-08-29 17:00 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595
35254067 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2023-09-13 08:00 | 2023-10-18 08:00 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0
35223032 |  | 08W | Base SH | 152282102 | MOUNTAIN QUARRIES 2101 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | MOUNTAIN QUARRIES 2101CB | 106 | 2023-05-15 | 2023-08-15 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0
35334752 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 11088762 | 64 | VACAVILLE 11088762 | 768 | Not Yet Available | Not Yet Available | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0
35334750 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 11088762 | 64 | VACAVILLE 11088762 | 768 | 2023-11-16 08:00 | 2024-01-05 08:00 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0
35320334 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 11088762 | 64 | VACAVILLE 11088762 | 768 | 2023-06-29 08:00 | 2023-10-02 08:00 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0
35320333 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 | VACAVILLE 11088762 | 64 | VACAVILLE 11088762 | 768 | Not Yet Available | Not Yet Available | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0
35277930 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101CB | 63 | AUBERRY 1101CB | 2126 | 2023-06-06 | 2023-06-23 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0
35277929 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101CB | 63 | AUBERRY 1101CB | 2126 | 2023-05-02 | 2023-08-31 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0
35277926 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101CB | 63 | AUBERRY 1101CB | 2126 | 2022-08-16 | 2023-05-26 | 3.4381 | 0 | 0 | 3.4381 | 0 | 0 | 0 | 0 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0
35277925 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101CB | 63 | AUBERRY 1101CB | 2126 | 2023-04-28 | 2023-04-28 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0
35254079 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 | AUBERRY 1101CB | 63 | AUBERRY 1101CB | 2126 | 2023-05-02 | 2023-06-09 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0
35250738 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21045310 | 61 | COARSEGOLD 21045310 | 1416 | 2023-11-20 | 2024-02-09 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0
35250737 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21045310 | 61 | COARSEGOLD 21045310 | 1416 | 2023-06-27 | 2023-09-01 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0
35240162 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 | COARSEGOLD 21045310 | 61 | COARSEGOLD 21045310 | 1416 | 2023-11-01 | 2023-12-31 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0
35283340 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-03-06 | 2023-06-30 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0
35283199 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-03-06 | 2023-06-30 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0
35283198 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-07-03 | 2023-07-21 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0
35283197 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-03-06 | 2023-06-30 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0
35283196 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-03-06 | 2023-06-30 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0
35250576 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101698 | 58 | HARTLEY 1101698 | 486 | 2023-03-06 | 2023-06-30 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0
35274597 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 2101CB | 57 | MARIPOSA 2101CB | 82 | 2023-10-27 08:00 | 2024-03-08 17:00 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0
35250573 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 | MARIPOSA 2101CB | 57 | MARIPOSA 2101CB | 82 | 2023-04-10 | 2023-05-05 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0
35338384 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-06-06 08:00 | 2023-09-29 08:00 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0
35279122 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-05-01 | 2023-06-02 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0
35279121 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-01-23 | 2023-02-15 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0
35279120 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-05-17 08:00 | 2023-08-16 08:00 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0
35278899 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-03-27 | 2023-06-30 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0
35250578 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 | STANISLAUS 1701CB | 56 | STANISLAUS 1701CB | 95 | 2023-03-07 | 2023-05-31 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0
35219591 |  | 08W | Base SH | 163541101 | OLETA 1101 | WDRM v2 | OLETA 1101754718 | 54 | OLETA 1101754718 | 2197 | 2023-06-06 | 2023-08-11 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0
35226799 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 | WILDWOOD 11011454 | 52 | WILDWOOD 11011454 | 86 | 2023-06-02 08:00 | 2023-06-12 17:00 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0
35226798 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 | WILDWOOD 11011454 | 52 | WILDWOOD 11011454 | 86 | 2023-04-03 08:00 | 2023-07-24 17:00 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0
35224321 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 | WILDWOOD 11011454 | 52 | WILDWOOD 11011454 | 86 | 2023-04-17 08:00 | 2023-07-31 17:00 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0
35280362 |  | 08W | Base SH | 254452102 | MARIPOSA 2102 | WDRM v2 | MARIPOSA 2102440236 | 50 | MARIPOSA 2102440236 | 400 | 2023-05-15 | 2023-09-28 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0
35219588 |  | 08W | Base SH | 254452102 | MARIPOSA 2102 | WDRM v2 | MARIPOSA 2102440236 | 50 | MARIPOSA 2102440236 | 400 | 2022-05-31 | Not Yet Available | 0.88182 | 0 | 0.27973 | 1.1616 | 0 | 0 | 0 | 0 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0
35316537 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | Not Yet Available | Not Yet Available | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152
35234400 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-08-10 | Not Yet Available | 1.2771 | 0 | 0 | 1.2771 | 0 | 0 | 0 | 0 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432 | 0 | 0 | 0 | 0
35234399 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-10-31 | Not Yet Available | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246
35234398 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-01-16 | 2023-04-12 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0
35234397 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-12-12 | 2023-06-27 17:00 | 0.71345 | 0 | 0 | 0.71345 | 0 | 0 | 0 | 0 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489 | 0 | 0 | 0 | 0
35234396 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-08-17 | 2023-09-26 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0
35234395 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-07-20 | 2023-08-24 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0
35234394 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-06-20 | 2023-07-25 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0
35234393 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-05-23 | 2023-06-27 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0
35234382 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-04-01 | 2023-04-18 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0
35234381 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-01-23 | 2023-03-31 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0
35233951 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-09-07 | 2023-04-28 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0
35233950 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-10-06 08:00 | 2024-05-24 17:00 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701
35233949 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-04-28 | 2023-03-03 17:00 | 1.7706 | 0 | 0 | 1.7706 | 0 | 0 | 0 | 0 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411 | 0 | 0 | 0 | 0
35233948 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-10-24 08:00 | 2024-03-01 08:00 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722
35225829 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2022-10-10 | 2023-05-30 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0
35219289 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-09-04 08:00 | 2024-01-04 17:00 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973
35219287 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 | OREGON TRAIL 110335002 | 49 | OREGON TRAIL 110335002 | 2405 | 2023-01-16 | 2023-04-03 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0
35219280 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 | POTTER VALLEY P H 110564118 | 43 | POTTER VALLEY P H 110564118 | 1733 | 2022-04-05 | 2023-01-28 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | 0 | 0
35227654 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 | VACAVILLE 11046542 | 42 | VACAVILLE 11046542 | 383 | 2023-06-26 08:00 | 2023-06-26 08:00 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0
35227652 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 | VACAVILLE 11046542 | 42 | VACAVILLE 11046542 | 383 | 2022-11-14 | 2023-03-31 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0
35219276 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 | VACAVILLE 11046542 | 42 | VACAVILLE 11046542 | 383 | 2023-03-15 | 2023-05-07 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0
35237370 |  | 08W | Base SH | 63591105 | VACA DIXON 1105 | WDRM v2 | VACA DIXON 110540092 | 37 | VACA DIXON 110540092 | 1554 | 2022-04-25 | Not Yet Available | 3.6491 | 0 | 0 | 3.6491 | 0 | 0 | 0 | 0 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | 0 | 0
35226700 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 | WYANDOTTE 110932586 | 29 | WYANDOTTE 110932586 | 2717 | 2022-08-01 | 2023-02-15 | 0 | 0.4214 | 0 | 0.4214 | 0 | 0 | 0 | 0 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0 | 0
35219260 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 | WYANDOTTE 110932586 | 29 | WYANDOTTE 110932586 | 2717 | 2021-09-15 | 2023-02-17 | 0.92822 | 0 | 0.86723 | 1.7955 | 0.87803 | 0 | 0 | 0.87803 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.86723 | 0.91742 | 0 | 0 | 0 | 0
35231631 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2022-04-28 | Not Yet Available | 0.44867 | 0 | 0 | 0.44867 | 0 | 0 | 0 | 0 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | 0 | 0
35231629 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-05-30 08:00 | 2023-07-24 17:00 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0
35231628 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799
35231627 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-06-30 | 2023-09-30 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0
35231626 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2022-11-03 | Not Yet Available | 0.78295 | 0 | 0.64962 | 1.4326 | 0 | 0 | 0 | 0 | 0.78295 | 0 | 0.60417 | 1.3871 | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0
35231625 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-09-01 08:00 | 2023-10-26 17:00 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0
35231624 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701
35231623 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2022-11-03 08:00 | Not Yet Available | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799
35231621 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-06-30 | 2023-09-30 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0
35231620 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-06-30 | 2023-09-30 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0
35219099 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 | HIGHLANDS 1102628 | 27 | HIGHLANDS 1102628 | 29 | 2023-06-30 | 2023-09-30 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0
35227655 |  | 08W | Base SH | 14452104 | KIRKER 2104 | WDRM v2 | KIRKER 2104442850 | 21 | KIRKER 2104442850 | 571 | Not Yet Available | Not Yet Available | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0
35219096 |  | 08W | Base SH | 14452104 | KIRKER 2104 | WDRM v2 | KIRKER 2104442850 | 21 | KIRKER 2104442850 | 571 | 2022-06-13 | 2023-03-15 | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0 | 0 | 0 | 0 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.028409 | 0.028409 | 0.056818 | 0 | 0 | 0 | 0
35299137 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101789752 | 595 | 2023-07-28 08:00 | 2023-09-12 08:00 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0
35299136 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101789752 | 595 | 2023-06-23 08:00 | 2023-08-11 08:00 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0
35299135 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101789752 | 595 | 2023-07-17 08:00 | 2023-09-15 08:00 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0
35299134 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101789752 | 595 | 2023-07-28 08:00 | 2023-09-11 08:00 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0
35299133 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101789752 | 595 | 2023-03-31 | 2023-05-01 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0
35250575 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 | HARTLEY 1101980662 | 19 | HARTLEY 1101658 | 2963 | 2023-03-31 | 2023-05-01 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0
35219093 |  | 08W | Base SH | 14652106 | TIDEWATER 2106 | WDRM v2 | TIDEWATER 210614072 | 18 | TIDEWATER 210614072 | 448 | 2023-04-03 | 2023-04-03 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0
35228188 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 | MIDDLETOWN 1103830 | 14 | MIDDLETOWN 1103830 | 443 | 2022-08-25 | 2023-03-31 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0
35228186 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 | MIDDLETOWN 1103830 | 14 | MIDDLETOWN 1103830 | 443 | 2023-06-30 | 2023-11-24 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0
35227868 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 | MIDDLETOWN 1103830 | 14 | MIDDLETOWN 1103830 | 443 | 2022-07-06 | 2023-03-31 | 0.57727 | 0 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939 | 0 | 0 | 0 | 0
35227864 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 | MIDDLETOWN 1103830 | 14 | MIDDLETOWN 1103830 | 443 | 2022-09-19 | 2023-04-14 | 0 | 1.3212 | 0 | 1.3212 | 0 | 0 | 0 | 0 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985 | 0 | 0 | 0 | 0
35220895 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 | MIDDLETOWN 1103830 | 14 | MIDDLETOWN 1103830 | 443 | 2022-10-17 | 2023-04-14 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0
35224713 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 | BUCKS CREEK 1101CB | 11 | BUCKS CREEK 1101CB | 21 | 2022-12-06 | 2023-04-28 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0
35224712 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 | BUCKS CREEK 1101CB | 11 | BUCKS CREEK 1101CB | 21 | 2022-12-06 | 2023-04-28 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0
35217268 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 | BUCKS CREEK 1101CB | 11 | BUCKS CREEK 1101CB | 21 | 2022-07-27 | 2023-09-15 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0
35227161 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 | MIDDLETOWN 1102302610 | 8 | MIDDLETOWN 1102302610 | 392 | 2023-12-31 | 2023-12-31 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0
35227160 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 | MIDDLETOWN 1102302610 | 8 | MIDDLETOWN 1102302610 | 392 | 2023-12-31 | 2024-09-20 17:00 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534
35226819 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 | MIDDLETOWN 1102302610 | 8 | MIDDLETOWN 1102302610 | 392 | 2023-12-31 | 2024-04-11 17:00 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321
35226629 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v2 | KESWICK 11011586 | 7 | KESWICK 11011586 | 48 | 2023-06-19 08:00 | 2023-11-27 08:00 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0
35226628 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v2 | KESWICK 11011586 | 7 | KESWICK 11011586 | 48 | 2023-06-19 08:00 | 2023-07-31 08:00 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0
35058839 |  | 07D | Other | 24251101 | WOODSIDE 1101 | WDRM v2 | WOODSIDE 11018974 | 1145 | WOODSIDE 11018974 | 1026 | 2022-09-17 | 2023-03-22 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0
35334404 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 | POINT MORETTI 11015076 | 1393 | POINT MORETTI 1101415734 | 2485 | 2023-08-01 08:00 | 2023-08-14 17:00 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0
35332872 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 110451756 | 693 | LINCOLN 1104997576 | 3098 | Not Yet Available | Not Yet Available | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61
35320453 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 | LINCOLN 110451756 | 693 | LINCOLN 1104997576 | 3098 | 2023-08-16 08:00 | 2023-12-21 16:00 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0
Note on E125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tekeste, Merih - do we have the circuit name / iD even though this isn't scoped?

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Idle Facilities | Removal of Primary Conductor in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
MAT Code
MAT Code | Description
06A | Feeder Projects Associated with Substation Capacity
08W | System Hardening Wildfire Resiliency Projects
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
95F | Electric Distribution Major Emergency
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Division
Division Acronym | Division Name
CC | Central Coast
CV | Central Valley
DA | De Anza
DI | Diablo
EB | East Bay
FR | Fresno
HB | Humboldt
KE | Kern
LP | Los Padres
NB | North Bay
NV | North Valley
PN | Peninsula
SA | Sacramento
SF | San Francisco
SI | Sierra
SJ | San Jose
SO | Sonoma
ST | Stockton
YO | Yosemite
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Mean Risk | Summation of the total risk of all pixels (100-meter x 100-meter cell) linked to a circuit segment, divided by the total number of pixels.
Feasibility score by CPZ | Cost multiplier indicating the difficulty of undergrounding the circuit segment (Circuit Protection Zone (CPZ)) based on presence of hard rock, water crossing, and gradient. The scale ranges from 1 to 3, with 3 being most challenging.