## Sheet2
Order | Order Description | Circuit ID | Circuit Name | Circuit Protection Zone | Rule 20 Project (Y/N) | WMP Project (Y/N) | Post-Wildfire Rebuild Project (Y/N) | County | Construction Start | Construction End | Planned OH Miles | Planned UG Miles | Planned Removal Miles | Total Miles | OH - 2021 Complete | UG - 2021 Complete | Removal - 2021 Complete | 2021 Miles Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Miles Complete | Total Life-cycle Costs
35334406 |  | 82841102 | BIG BASIN 1102 | BIG BASIN 11022253 | N | Y | Y | Santa Cruz | 2022-10-25 | 2022-11-23 | 0.041477 | 0.44318 | 0 | 0.48466 | 0 | 0 | 0 | 0 | 0.041477 | 0.44318 | 0 | 0.48466 | 1121624.42
35311924 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-08-31 | 2022-08-31 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 197062.13
35225821 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-08-02 | 2022-05-13 | 0 | 1.1314 | 0 | 1.1314 | 0 | 1.0252 | 0 | 1.0252 | 0 | 0.10625 | 0 | 0.10625 | 2337070.46
35242422 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-10-02 | 2022-05-11 | 0 | 0.85398 | 0 | 0.85398 | 0 | 0 | 0 | 0 | 0 | 0.85398 | 0 | 0.85398 | 1121509.24
35242423 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-09-30 | 2022-05-11 | 0 | 0.88958 | 0 | 0.88958 | 0 | 0 | 0 | 0 | 0 | 0.88958 | 0 | 0.88958 | 1173498.39
35242424 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-09-30 | 2022-05-11 | 0 | 0.69943 | 0 | 0.69943 | 0 | 0 | 0 | 0 | 0 | 0.69943 | 0 | 0.69943 | 997694.15
35242425 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-09-27 | 2022-05-11 | 0 | 0.66155 | 0 | 0.66155 | 0 | 0 | 0 | 0 | 0 | 0.66155 | 0 | 0.66155 | 1533598.25
35242426 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-02-14 | 2022-05-11 | 0 | 0.58864 | 0 | 0.58864 | 0 | 0 | 0 | 0 | 0 | 0.58864 | 0 | 0.58864 | 682476.45
35242427 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-03-26 | 2022-05-11 | 0 | 0.82822 | 0 | 0.82822 | 0 | 0 | 0 | 0 | 0 | 0.82822 | 0 | 0.82822 | 1362892.57
35242428 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-11-30 | 2022-04-08 | 0 | 0.73598 | 0 | 0.73598 | 0 | 0 | 0 | 0 | 0 | 0.73598 | 0 | 0.73598 | 944074.9
35242429 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-11-29 | 2022-04-06 | 0 | 0.59792 | 0 | 0.59792 | 0 | 0 | 0 | 0 | 0 | 0.59792 | 0 | 0.59792 | 936086.48
35236983 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-03-16 | 2022-04-15 | 0 | 0.31989 | 0 | 0.31989 | 0 | 0 | 0 | 0 | 0 | 0.31989 | 0 | 0.31989 | 732332.44
35235139 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-10-12 | 2022-03-18 | 0 | 1.5297 | 0 | 1.5297 | 0 | 1.2008 | 0 | 1.2008 | 0 | 0.32898 | 0 | 0.32898 | 5091101.89
35235676 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-02-25 | 2022-03-18 | 0 | 2.6394 | 0 | 2.6394 | 0 | 0.11231 | 0 | 0.11231 | 0 | 2.5271 | 0 | 2.5271 | 4176252.46
35235679 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2021-08-04 | 2022-05-11 | 0 | 0.72784 | 0 | 0.72784 | 0 | 0 | 0 | 0 | 0 | 0.72784 | 0 | 0.72784 | 2798738.8
35233166 |  | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | N | Y | Y | Butte | 2022-03-29 | 2022-04-13 | 0 | 0.88542 | 0 | 0.88542 | 0 | 0 | 0 | 0 | 0 | 0.88542 | 0 | 0.88542 | 1210497.91
35290946 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | N | Y | Y | Plumas | 2022-08-22 | 2022-09-23 | 0 | 0.19924 | 0 | 0.19924 | 0 | 0 | 0 | 0 | 0 | 0.19924 | 0 | 0.19924 | 474955.25
35290948 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | N | Y | Y | Plumas | 2022-08-11 | 2022-09-23 | 0 | 0.10966 | 0 | 0.10966 | 0 | 0 | 0 | 0 | 0 | 0.10966 | 0 | 0.10966 | 444968.61
35292782 |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | N | Y | Y | Plumas | 2022-09-26 | 2022-11-07 | 0.077462 | 0.11288 | 0 | 0.19034 | 0 | 0 | 0 | 0 | 0.077462 | 0.11288 | 0 | 0.19034 | 817608.68
35279512 |  | 152461106 | BRUNSWICK 1106 | BRUNSWICK 11062790 | N | Y | Y | Nevada | 2022-01-18 | 2022-08-06 | 0 | 0.17708 | 0 | 0.17708 | 0 | 0 | 0 | 0 | 0 | 0.17708 | 0 | 0.17708 | 821858.97
35295010 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-24 | 2022-10-07 | 0 | 0.3608 | 0 | 0.3608 | 0 | 0 | 0 | 0 | 0 | 0.3608 | 0 | 0.3608 | 840364.42
35295011 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-05-31 | 2022-08-22 | 0 | 0.12765 | 0 | 0.12765 | 0 | 0 | 0 | 0 | 0 | 0.12765 | 0 | 0.12765 | 415920.14
35295012 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-21 | 2022-08-26 | 0 | 0.89792 | 0 | 0.89792 | 0 | 0 | 0 | 0 | 0 | 0.89792 | 0 | 0.89792 | 1276280.39
35295013 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-21 | 2022-08-24 | 0 | 0.25814 | 0 | 0.25814 | 0 | 0 | 0 | 0 | 0 | 0.25814 | 0 | 0.25814 | 577020.83
35295014 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-06 | 2022-08-05 | 0 | 0.15758 | 0 | 0.15758 | 0 | 0 | 0 | 0 | 0 | 0.15758 | 0 | 0.15758 | 451378.46
35295015 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-16 | 2022-07-22 | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | 0 | 0 | 0.26155 | 0 | 0.26155 | 446112.74
35295016 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-22 | 2022-08-06 | 0 | 0.22481 | 0 | 0.22481 | 0 | 0 | 0 | 0 | 0 | 0.22481 | 0 | 0.22481 | 452275.47
35295017 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-05-09 | 2022-08-31 | 0.086364 | 0.33352 | 0 | 0.41989 | 0 | 0 | 0 | 0 | 0.086364 | 0.33352 | 0 | 0.41989 | 1629946.49
35295018 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-08 | 2022-08-13 | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0 | 0 | 0.37121 | 0 | 0.37121 | 1454204.91
35295019 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-22 | 2022-09-21 | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 1.0549 | 3474526.3
35295184 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-07-27 | 2022-10-07 | 0 | 0.54205 | 0 | 0.54205 | 0 | 0 | 0 | 0 | 0 | 0.54205 | 0 | 0.54205 | 1498040.01
35295185 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-21 | 2022-08-11 | 0 | 0.050379 | 0 | 0.050379 | 0 | 0 | 0 | 0 | 0 | 0.050379 | 0 | 0.050379 | 657063.26
35295186 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-27 | 2022-11-19 | 0 | 1.0076 | 0 | 1.0076 | 0 | 0 | 0 | 0 | 0 | 1.0076 | 0 | 1.0076 | 5113153.17
35295187 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-07-25 | 2022-10-14 | 0 | 0.50644 | 0 | 0.50644 | 0 | 0 | 0 | 0 | 0 | 0.50644 | 0 | 0.50644 | 2344638.3
35295188 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-24 | 2022-10-07 | 0 | 0.4733 | 0 | 0.4733 | 0 | 0 | 0 | 0 | 0 | 0.4733 | 0 | 0.4733 | 2050607.68
35295189 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-06-18 | 2022-08-26 | 0 | 0.17936 | 0 | 0.17936 | 0 | 0 | 0 | 0 | 0 | 0.17936 | 0 | 0.17936 | 378726.73
35295190 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-08-09 | 2022-08-29 | 0 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0 | 0.083333 | 273758.91
35295191 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-07-20 | 2022-08-09 | 0 | 0.22595 | 0 | 0.22595 | 0 | 0 | 0 | 0 | 0 | 0.22595 | 0 | 0.22595 | 567393.11
35295192 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-05-31 | 2022-07-13 | 0 | 0.05303 | 0 | 0.05303 | 0 | 0 | 0 | 0 | 0 | 0.05303 | 0 | 0.05303 | 420442.64
35295193 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-05-09 | 2022-10-03 | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | 0 | 0 | 0.18542 | 0 | 0.18542 | 1780110.06
35295194 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-09-15 | 2022-10-14 | 0 | 0.17102 | 0 | 0.17102 | 0 | 0 | 0 | 0 | 0 | 0.17102 | 0 | 0.17102 | 474165.27
35295195 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-05-09 | 2022-08-01 | 0 | 0.78447 | 0 | 0.78447 | 0 | 0 | 0 | 0 | 0 | 0.78447 | 0 | 0.78447 | 3114258.35
35295182 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | N | Y | Y | El Dorado | 2022-08-22 | 2022-10-16 | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | 0 | 0 | 0.2589 | 0 | 0.2589 | 974841.5
35285589 |  | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101344250 | N | Y | Y | El Dorado | 2022-08-22 | 2022-10-09 | 0 | 0.26326 | 0 | 0.26326 | 0 | 0 | 0 | 0 | 0 | 0.26326 | 0 | 0.26326 | 1169358.23
35279313 |  | 103021101 | GANSNER 1101 | GANSNER 11012424 | N | Y | Y | Plumas | 2022-10-03 | 2022-12-01 | 0.10227 | 0.46345 | 0 | 0.56572 | 0 | 0 | 0 | 0 | 0.10227 | 0.46345 | 0 | 0.56572 | 1464913.43
35220936 |  | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | N | Y | Y | San Mateo | 2022-08-01 | 2022-10-04 | 0 | 0.86269 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0.86269 | 1710074.48
35282131 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | N | Y | Y | Butte | 2021-12-10 | 2022-01-26 | 0 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0.038447 | 0 | 0.038447 | 202479.58
35250343 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | N | Y | Y | Butte | 2021-11-01 | 2022-01-26 | 0 | 0.29432 | 0 | 0.29432 | 0 | 0 | 0 | 0 | 0 | 0.29432 | 0 | 0.29432 | 295938.39
35254695 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | N | Y | Y | Butte | 2021-12-04 | 2022-01-26 | 0 | 0.055303 | 0 | 0.055303 | 0 | 0 | 0 | 0 | 0 | 0.055303 | 0 | 0.055303 | 194406.87
35236992 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | N | Y | Y | Butte | 2022-02-26 | 2022-05-04 | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | 0 | 0 | 0.70587 | 0 | 0.70587 | 1207251.83
35235702 |  | 103221101 | KANAKA 1101 | KANAKA 1101CB | N | Y | Y | Butte | 2022-03-02 | 2022-04-27 | 0 | 1.8371 | 0 | 1.8371 | 0 | 0 | 0 | 0 | 0 | 1.8371 | 0 | 1.8371 | 3108949.22
35238840 |  | 82931101 | POINT MORETTI 1101 | Point Moretti 110135874 | N | Y | Y | Santa Cruz |  |  | 0.14962 | 0.46117 | 0 | 0.6108 | 0 | 0 | 0 | 0 | 0.14962 | 0.46117 | 0 | 0.6108 | 35764.63
35284568 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | N | Y | Y | Placer | 2022-01-31 | 2022-06-30 | 0 | 0.92045 | 0 | 0.92045 | 0 | 0 | 0 | 0 | 0 | 0.92045 | 0 | 0.92045 | 3029365.27
35284567 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | N | Y | Y | Placer |  |  | 0 | 0.60701 | 0 | 0.60701 | 0 | 0 | 0 | 0 | 0 | 0.60701 | 0 | 0.60701 | 3515029.93
35295009 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | N | Y | Y | Placer | 2022-04-25 | 2022-07-22 | 0 | 1.0794 | 0 | 1.0794 | 0 | 0 | 0 | 0 | 0 | 1.0794 | 0 | 1.0794 | 2432135.88
35284569 |  | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110248894 | N | Y | Y | Placer | 2021-10-25 | 2022-03-30 | 0 | 0.62311 | 0 | 0.62311 | 0 | 0 | 0 | 0 | 0 | 0.62311 | 0 | 0.62311 | 2306374.43
35295745 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | N | Y | Y | Butte | 2022-01-13 | 2022-04-13 | 0 | 0.40038 | 0 | 0.40038 | 0 | 0 | 0 | 0 | 0 | 0.40038 | 0 | 0.40038 | 490644.17
35236984 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | N | Y | Y | Butte | 2022-01-14 | 2022-04-13 | 0 | 1.5852 | 0 | 1.5852 | 0 | 0 | 0 | 0 | 0 | 1.5852 | 0 | 1.5852 | 2001564.28
35341054 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031941 | N | Y | Y | Butte |  |  | 0 | 0.18333 | 0 | 0.18333 | 0 | 0 | 0 | 0 | 0 | 0.18333 | 0 | 0.18333 | 171950.59
35331458 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031941 | N | Y | Y | Butte | 2022-12-05 | 2022-12-05 | 0 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | 0 | 0 | 0.050568 | 0 | 0.050568 | 188815.63
35335712 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2022-08-26 | 2022-08-26 | 0 | 0.0087121 | 0 | 0.0087121 | 0 | 0 | 0 | 0 | 0 | 0.0087121 | 0 | 0.0087121 | 83719.5
35320807 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte |  |  | 0 | 0.09375 | 0 | 0.09375 | 0 | 0 | 0 | 0 | 0 | 0.09375 | 0 | 0.09375 | 179438.81
35302356 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2022-04-27 | 2022-05-10 | 0 | 0.24962 | 0 | 0.24962 | 0 | 0 | 0 | 0 | 0 | 0.24962 | 0 | 0.24962 | 211964.43
35233039 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-11-15 | 2022-02-17 | 0 | 0.42216 | 0 | 0.42216 | 0 | 0 | 0 | 0 | 0 | 0.42216 | 0 | 0.42216 | 655635.51
35235706 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-08-31 | 2022-01-31 | 0 | 0.7108 | 0 | 0.7108 | 0 | 0 | 0 | 0 | 0 | 0.7108 | 0 | 0.7108 | 722397.51
35235707 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-11-21 | 2022-03-04 | 0 | 0.94451 | 0 | 0.94451 | 0 | 0 | 0 | 0 | 0 | 0.94451 | 0 | 0.94451 | 1370318.82
35233300 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-01-06 | 2022-01-27 | 0 | 0.36117 | 0 | 0.36117 | 0 | 0 | 0 | 0 | 0 | 0.36117 | 0 | 0.36117 | 1027329.34
35233302 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-11-08 | 2022-02-16 | 0 | 0.14205 | 0 | 0.14205 | 0 | 0 | 0 | 0 | 0 | 0.14205 | 0 | 0.14205 | 322450.55
35233310 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2022-03-16 | 2022-03-24 | 0 | 0.28617 | 0 | 0.28617 | 0 | 0 | 0 | 0 | 0 | 0.28617 | 0 | 0.28617 | 678875.55
35233312 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-09-20 | 2022-03-24 | 0 | 0.78371 | 0 | 0.78371 | 0 | 0 | 0 | 0 | 0 | 0.78371 | 0 | 0.78371 | 1749417.6
35233314 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-06-28 | 2022-03-29 | 0 | 2.3701 | 0 | 2.3701 | 0 | 1.9703 | 0 | 1.9703 | 0 | 0.39981 | 0 | 0.39981 | 4025348.94
35233315 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2022-02-25 | 2022-03-10 | 0 | 0.70758 | 0 | 0.70758 | 0 | 0 | 0 | 0 | 0 | 0.70758 | 0 | 0.70758 | 960445.71
35239522 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-11-13 | 2022-01-28 | 0 | 0.24564 | 0 | 0.24564 | 0 | 0 | 0 | 0 | 0 | 0.24564 | 0 | 0.24564 | 449957.44
35240546 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2022-01-18 | 2022-03-11 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 220188.07
35283874 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | N | Y | Y | Butte | 2021-11-06 | 2022-01-10 | 0 | 0.40284 | 0.15057 | 0.55341 | 0 | 0 | 0 | 0 | 0 | 0.40284 | 0.15057 | 0.55341 | 583551.38
35239095 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-09-01 | 2022-03-10 | 0 | 1.5373 | 0 | 1.5373 | 0 | 0 | 0 | 0 | 0 | 1.5373 | 0 | 1.5373 | 2981889.23
35239096 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-10-21 | 2022-03-30 | 0 | 0.78504 | 0 | 0.78504 | 0 | 0 | 0 | 0 | 0 | 0.78504 | 0 | 0.78504 | 1889754.53
35239097 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-10-19 | 2022-04-08 | 0 | 1.2205 | 0 | 1.2205 | 0 | 0 | 0 | 0 | 0 | 1.2205 | 0 | 1.2205 | 1566096.2
35239098 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-10-15 | 2022-05-04 | 0 | 2.1644 | 0 | 2.1644 | 0 | 0 | 0 | 0 | 0 | 2.1644 | 0 | 2.1644 | 3047849.26
35239099 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-10-04 | 2022-04-19 | 0 | 0.41042 | 0 | 0.41042 | 0 | 0 | 0 | 0 | 0 | 0.41042 | 0 | 0.41042 | 672515.95
35235700 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-11-18 | 2022-05-11 | 0 | 0.96761 | 0 | 0.96761 | 0 | 0 | 0 | 0 | 0 | 0.96761 | 0 | 0.96761 | 1522631.94
35235320 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2022-01-27 | 2022-03-18 | 0 | 0.2267 | 0 | 0.2267 | 0 | 0 | 0 | 0 | 0 | 0.2267 | 0 | 0.2267 | 590083.78
35236990 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-09-13 | 2022-05-13 | 0 | 0.85303 | 0 | 0.85303 | 0 | 0 | 0 | 0 | 0 | 0.85303 | 0 | 0.85303 | 2807886.05
35236991 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-11-21 | 2022-05-11 | 0 | 1.0731 | 0 | 1.0731 | 0 | 0 | 0 | 0 | 0 | 1.0731 | 0 | 1.0731 | 1127983.51
35237021 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte |  |  | 0 | 0.17386 | 0 | 0.17386 | 0 | 0 | 0 | 0 | 0 | 0.17386 | 0 | 0.17386 | 392245.26
35236993 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2022-05-04 | 2022-05-04 | 0 | 0.36837 | 0 | 0.36837 | 0 | 0 | 0 | 0 | 0 | 0.36837 | 0 | 0.36837 | 745000.44
35236995 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-12-06 | 2022-03-11 | 0 | 2.2905 | 0 | 2.2905 | 0 | 0 | 0 | 0 | 0 | 2.2905 | 0 | 2.2905 | 3288368.34
35237896 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-01-03 | 2022-05-13 | 0 | 1.3059 | 0 | 1.3059 | 0 | 0 | 0 | 0 | 0 | 1.3059 | 0 | 1.3059 | 2034672.77
35237889 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2022-01-10 | 2022-02-28 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 2568786.91
35237890 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-09-20 | 2022-02-23 | 0 | 1.2174 | 0 | 1.2174 | 0 | 0 | 0 | 0 | 0 | 1.2174 | 0 | 1.2174 | 1996520.61
35237891 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2022-01-31 | 2022-04-22 | 0 | 0.43352 | 0 | 0.43352 | 0 | 0 | 0 | 0 | 0 | 0.43352 | 0 | 0.43352 | 1405992.28
35237893 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-09-10 | 2022-04-12 | 0 | 0.74811 | 0 | 0.74811 | 0 | 0 | 0 | 0 | 0 | 0.74811 | 0 | 0.74811 | 1186500.61
35237894 |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | N | Y | Y | Butte | 2021-09-10 | 2022-05-13 | 0 | 1.1083 | 0 | 1.1083 | 0 | 0 | 0 | 0 | 0 | 1.1083 | 0 | 1.1083 | 2326881.76
74013926 |  | 152481103 | Brunswick 1103 | Brunswick 1103CB | Y | Y | N | Nevada | 2022-07-22 | 2022-07-22 | 0 | 0.14583 | 0 | 0.14583 | 0 | 0 | 0 | 0 | 0 | 0.14583 | 0 | 0.14583 | 940049.91
31066255 |  | 152261106 | Diamond Springs 1106 | Diamond Springs 1106930190 | Y | Y | N | El Dorado | 2021-11-30 | 2022-01-21 | 0.11269 | 1.3144 | 0 | 1.4271 | 0 | 0 | 0 | 0 | 0.11269 | 1.3144 | 0 | 1.4271 | 4740691.69
35112572 |  | 192221102 | GARBERVILLE 1102 | GARBERVILLE 1102CB | N | Y | N | Humboldt | 2022-03-08 | 2022-09-30 | 0.59527 | 0.57311 | 0 | 1.1684 | 0 | 0 | 0 | 0 | 0.59527 | 0.57311 | 0 | 1.1684 | 4363560.67
31546316 |  | 152691109 | Higgins 1109 | Higgins 110950072 | N | Y | N | Nevada | 2022-05-24 | 2022-06-21 | 0 | 0.13049 | 0 | 0.13049 | 0 | 0 | 0 | 0 | 0 | 0.13049 | 0 | 0.13049 | 29867.85
35236002 |  | 42091102 | Mirabel 1102 | Mirabel 11021139 | N | Y | N | Sonoma | 2022-02-18 | 2022-02-25 | 0 | 0.18163 | 0 | 0.18163 | 0 | 0 | 0 | 0 | 0 | 0.18163 | 0 | 0.18163 | 86812.53
35384430 |  | 102541101 | VOLTA 1101 | VOLTA 11011596 | N | Y | N | Tehama | 2022-10-05 | 2022-12-16 | 0 | 0.012879 | 0 | 0.012879 | 0 | 0 | 0 | 0 | 0 | 0.012879 | 0 | 0.012879 | 1719651.37
35254649 |  | 102541101 | VOLTA 1101 | VOLTA 110153118 | N | Y | N | Tehama | 2022-08-16 | 2022-10-14 | 0.14773 | 0.46686 | 0 | 0.61458 | 0 | 0 | 0 | 0 | 0.14773 | 0.46686 | 0 | 0.61458 | 1594010.26
35254641 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | N | Y | N | Shasta | 2022-06-13 | 2022-08-19 | 0.088068 | 0.33598 | 0.72008 | 1.1441 | 0 | 0 | 0 | 0 | 0.088068 | 0.33598 | 0.72008 | 1.1441 | 854925.69
35254643 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | N | Y | N | Shasta | 2022-05-18 | 2022-12-09 | 0 | 1.2705 | 1.0356 | 2.3061 | 0 | 0 | 0 | 0 | 0 | 1.2705 | 1.0356 | 2.3061 | 3042261.27
35254647 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | N | Y | N | Tehama | 2022-07-07 | 2022-10-07 | 0 | 0.50928 | 0 | 0.50928 | 0 | 0 | 0 | 0 | 0 | 0.50928 | 0 | 0.50928 | 1218903.66
35240167 |  | 102541101 | VOLTA 1101 | VOLTA 1101CB | N | Y | N | Shasta | 2022-08-15 | 2022-12-16 | 0.02803 | 0.40909 | 0 | 0.43712 | 0 | 0 | 0 | 0 | 0.02803 | 0.40909 | 0 | 0.43712 | 1363845.37
35144944 |  | 22721107 | SNEATH LANE 1107 | SNEATH LANE 110748338 | N | Y | N | San Mateo | 2022-10-03 | 2022-11-17 | 0 | 0.20398 | 0 | 0.20398 | 0 | 0 | 0 | 0 | 0 | 0.20398 | 0 | 0.20398 | 1375518
35192284 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | N | Y | N | Napa | 2022-06-20 | 2022-10-01 | 0 | 1.9475 | 0 | 1.9475 | 0 | 0 | 0 | 0 | 0 | 1.9475 | 0 | 1.9475 | 4874305.86
35223024 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | N | Y | N | Napa | 2022-05-23 | 2022-10-01 | 0 | 2.0195 | 0 | 2.0195 | 0 | 0 | 0 | 0 | 0 | 2.0195 | 0 | 2.0195 | 3995851.19
35223026 |  | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | N | Y | N | Napa | 2022-06-23 | 2022-11-14 | 0.079545 | 1.329 | 0 | 1.4085 | 0 | 0 | 0 | 0 | 0.079545 | 1.329 | 0 | 1.4085 | 3124910.25
35226849 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | N | Y | N | El Dorado | 2022-06-20 | 2022-12-02 | 0 | 2.0458 | 0 | 2.0458 | 0 | 0 | 0 | 0 | 0 | 2.0458 | 0 | 2.0458 | 6337437.51
35062374 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | N | Y | N | El Dorado | 2022-03-28 | 2022-09-30 | 0.037311 | 2.0536 | 0 | 2.0909 | 0 | 0 | 0 | 0 | 0.037311 | 2.0536 | 0 | 2.0909 | 8376284.13
35062375 |  | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | N | Y | N | El Dorado | 2022-04-25 | 2022-12-17 | 0 | 1.4892 | 0 | 1.4892 | 0 | 0 | 0 | 0 | 0 | 1.4892 | 0 | 1.4892 | 6627030.08
35254656 |  | 102541101 | VOLTA 1101 | VOLTA 11011568 | N | Y | N | Shasta | 2022-08-01 | 2022-10-19 | 0.0028409 | 0.44545 | 0 | 0.4483 | 0 | 0 | 0 | 0 | 0.0028409 | 0.44545 | 0 | 0.4483 | 1084320.48
35227656 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | N | Y | N | Solano | 2022-06-06 | 2022-09-30 | 0.049432 | 1.0758 | 0 | 1.1252 | 0 | 0 | 0 | 0 | 0.049432 | 1.0758 | 0 | 1.1252 | 4176905.76
35227659 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | N | Y | N | Solano |  |  | 0.25568 | 0.056818 | 0 | 0.3125 | 0.25568 | 0 | 0 | 0.25568 | 0 | 0.056818 | 0 | 0.056818 | 475640.77
35227870 |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | N | Y | N | Solano | 2022-01-24 | 2022-05-25 | 0 | 1.5928 | 0 | 1.5928 | 0 | 0 | 0 | 0 | 0 | 1.5928 | 0 | 1.5928 | 4021510.05
35231543 |  | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | N | Y | N | Contra Costa | 2022-08-08 | 2022-12-09 | 0.13371 | 1.2386 | 0 | 1.3723 | 0 | 0 | 0 | 0 | 0.13371 | 1.2386 | 0 | 1.3723 | 4108580.75
35145004 |  | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | N | Y | N | Contra Costa | 2021-10-04 | 2022-06-24 | 0 | 0.69489 | 0 | 0.69489 | 0 | 0 | 0 | 0 | 0 | 0.69489 | 0 | 0.69489 | 3673644.5
35324156 |  | 14161108 | ROSSMOOR 1108 | ROSSMOOR 1108CB | N | Y | N | Contra Costa | 2022-06-22 | 2022-09-30 | 0.38864 | 0.55341 | 0.092614 | 1.0347 | 0 | 0 | 0 | 0 | 0.38864 | 0.55341 | 0.092614 | 1.0347 | 62844
35226632 |  | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | N | Y | N | Mendocino | 2022-04-25 | 2022-10-07 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 382077.4
35254260 |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | N | Y | N | Solano | 2022-10-10 | 2022-12-03 | 0.1036 | 0.37822 | 0 | 0.48182 | 0 | 0 | 0 | 0 | 0.1036 | 0.37822 | 0 | 0.48182 | 821095.36
35224377 |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | N | Y | N | El Dorado | 2022-08-01 | 2022-10-30 | 0 | 0.21799 | 0 | 0.21799 | 0 | 0 | 0 | 0 | 0 | 0.21799 | 0 | 0.21799 | 1749860.67
35219542 |  | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | N | Y | N | El Dorado | 2022-04-07 | 2022-09-29 | 0 | 0.12879 | 0 | 0.12879 | 0 | 0 | 0 | 0 | 0 | 0.12879 | 0 | 0.12879 | 1445005.36
35278886 |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | N | Y | N | San Luis Obispo | 2022-08-12 | 2022-10-28 | 1.379 | 0.024621 | 0 | 1.4036 | 0 | 0 | 0 | 0 | 1.379 | 0.024621 | 0 | 1.4036 | 1042522.36
35233953 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-10-27 | 2022-12-07 | 0 | 0.81761 | 0 | 0.81761 | 0 | 0 | 0 | 0 | 0 | 0.81761 | 0 | 0.81761 | 2003644.92
35233955 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-08-30 | 2022-11-18 | 0 | 0.55928 | 0 | 0.55928 | 0 | 0 | 0 | 0 | 0 | 0.55928 | 0 | 0.55928 | 1118292.36
35233957 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-08-29 | 2022-11-16 | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0 | 0 | 0 | 0.10436 | 0 | 0.10436 | 393625.8
35234383 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-09-06 | 2022-10-15 | 0 | 1.2502 | 0 | 1.2502 | 0 | 0 | 0 | 0 | 0 | 1.2502 | 0 | 1.2502 | 2676824.92
35223037 |  | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | N | Y | N | Madera | 2021-09-16 | 2022-01-06 | 0 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 0 | 0.0079545 | 258960.02
35243440 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 1103CB | N | Y | N | Shasta | 2022-07-05 | 2022-11-05 | 0 | 1.0214 | 0 | 1.0214 | 0 | 0 | 0 | 0 | 0 | 1.0214 | 0 | 1.0214 | 2803476.39
35225827 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-11-28 | 2022-12-02 | 0 | 1.1182 | 0 | 1.1182 | 0 | 0 | 0 | 0 | 0 | 1.1182 | 0 | 1.1182 | 3161373.66
35225828 |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | N | Y | N | Shasta | 2022-08-23 | 2022-11-25 | 0 | 2.7928 | 0 | 2.7928 | 0 | 0 | 0 | 0 | 0 | 2.7928 | 0 | 2.7928 | 5856900.72
35232650 |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | N | Y | N | El Dorado | 2022-03-21 | 2022-12-23 | 0 | 1.3269 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 1.3269 | 5136592.7
35219281 |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | N | Y | N | El Dorado | 2022-01-12 | 2022-12-23 | 0.0083333 | 1.8222 | 0 | 1.8305 | 0 | 0 | 0 | 0 | 0.0083333 | 1.8222 | 0 | 1.8305 | 8254669.19
35236660 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | N | Y | N | Lake | 2022-07-18 | 2022-12-01 | 0 | 0.42557 | 0 | 0.42557 | 0 | 0 | 0 | 0 | 0 | 0.42557 | 0 | 0.42557 | 838240.25
35223038 |  | 163541101 | MARTELL 1101 | MARTELL 1101CB | N | Y | N | Amador | 2022-06-20 | 2022-08-29 | 0 | 0.51155 | 0 | 0.51155 | 0 | 0 | 0 | 0 | 0 | 0.51155 | 0 | 0.51155 | 2564932.51
35227162 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | N | Y | N | Lake | 2022-05-24 | 2022-09-02 | 0.10227 | 0.22064 | 0 | 0.32292 | 0 | 0 | 0 | 0 | 0.10227 | 0.22064 | 0 | 0.32292 | 565147.81
35217269 |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | N | Y | N | Lake | 2022-06-20 | 2022-12-04 | 0.15587 | 0.34261 | 0 | 0.49848 | 0 | 0 | 0 | 0 | 0.15587 | 0.34261 | 0 | 0.49848 | 1542486
35217271 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | N | Y | N | Lake |  |  | 0 | 2.3784 | 0 | 2.3784 | 0 | 0 | 0 | 0 | 0 | 2.3784 | 0 | 2.3784 | 7108449.67
35227165 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | N | Y | N | Lake | 2022-07-25 | 2022-11-30 | 0 | 0.89394 | 0 | 0.89394 | 0 | 0 | 0 | 0 | 0 | 0.89394 | 0 | 0.89394 | 1951710.96
35227167 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | N | Y | N | Lake | 2022-08-02 | 2022-11-30 | 0 | 1.653 | 0 | 1.653 | 0 | 0 | 0 | 0 | 0 | 1.653 | 0 | 1.653 | 2534963.27
35227168 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | N | Y | N | Lake | 2022-08-01 | 2022-11-30 | 0 | 1.2121 | 0 | 1.2121 | 0 | 0 | 0 | 0 | 0 | 1.2121 | 0 | 1.2121 | 2252868.85
35220896 |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | N | Y | N | Lake | 2022-07-25 | 2022-11-30 | 0 | 0.31686 | 0 | 0.31686 | 0 | 0 | 0 | 0 | 0 | 0.31686 | 0 | 0.31686 | 1025534.17
35227003 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | N | Y | N | Lake | 2022-08-29 | 2022-12-09 | 0 | 0.53864 | 0 | 0.53864 | 0 | 0 | 0 | 0 | 0 | 0.53864 | 0 | 0.53864 | 2693357.88
35227004 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | N | Y | N | Lake | 2022-08-22 | 2022-11-18 | 0 | 0.35758 | 0 | 0.35758 | 0 | 0 | 0 | 0 | 0 | 0.35758 | 0 | 0.35758 | 2711740.97
35145003 |  | 13801103 | MORAGA 1103 | MORAGA 1103CB | N | Y | N | Contra Costa | 2021-11-05 | 2022-07-01 | 0.11742 | 0.12178 | 0.24356 | 0.48277 | 0 | 0 | 0 | 0 | 0.11742 | 0.12178 | 0.24356 | 0.48277 | 1631298.47
35229119 |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | N | Y | N | Lake | 2022-03-28 | 2022-05-24 | 0.0054924 | 0.64167 | 0.28333 | 0.93049 | 0 | 0 | 0 | 0 | 0.0054924 | 0.64167 | 0.28333 | 0.93049 | 1418543.53
35191319 |  | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | N | Y | N | Marin | 2022-05-03 | 2022-08-14 | 0 | 1.1354 | 0 | 1.1354 | 0 | 0 | 0 | 0 | 0 | 1.1354 | 0 | 1.1354 | 4320300.73
35217272 |  | 103451101 | KESWICK 1101 | KESWICK 11011586 | N | Y | N | Shasta | 2022-04-25 | 2022-05-24 | 0.014773 | 0.28466 | 0 | 0.29943 | 0 | 0 | 0 | 0 | 0.014773 | 0.28466 | 0 | 0.29943 | 1024187.05
35192292 |  | 42561107 | FULTON 1107 | FULTON 1107604 | N | Y | N | Sonoma | 2022-05-09 | 2022-12-09 | 0.19489 | 1.7848 | 0 | 1.9797 | 0 | 0 | 0 | 0 | 0.19489 | 1.7848 | 0 | 1.9797 | 8604645.53
35057018 |  | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | N | Y | N | El Dorado | 2022-03-01 | 2022-11-30 | 0.22367 | 4.1256 | 0 | 4.3492 | 0 | 0 | 0 | 0 | 0.22367 | 4.1256 | 0 | 4.3492 | 13499562.48
35192291 |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | N | Y | N | El Dorado | 2022-06-13 | 2022-12-02 | 0.029167 | 1.0148 | 0 | 1.0439 | 0 | 0 | 0 | 0 | 0.029167 | 1.0148 | 0 | 1.0439 | 3380339.76
35259516 |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | N | Y | N | Shasta | 2022-06-20 | 2022-07-24 | 0 | 0.19489 | 0 | 0.19489 | 0 | 0 | 0 | 0 | 0 | 0.19489 | 0 | 0.19489 | 433411.77
35145522 |  | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | N | Y | N | El Dorado | 2022-04-04 | 2022-12-11 | 0 | 2.7455 | 0 | 2.7455 | 0 | 0 | 0 | 0 | 0 | 2.7455 | 0 | 2.7455 | 12630865.71
35223036 |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | N | Y | N | Nevada | 2022-06-21 | 2022-11-18 | 0 | 0.027841 | 0.018371 | 0.046212 | 0 | 0 | 0 | 0 | 0 | 0.027841 | 0.018371 | 0.046212 | 1046381.34