## Table 8.1.2-3
TABLE PG&E-8.1.2-3: PG&E UNDERGROUNDING WORKPLAN 2023-2026 [As Filed in the WMP]
V2 Top Risk: V2 Risk Rank <=727 V3 Top Risk: V3 Risk Rank <=720
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534.3408 |  |  |  | 588.4057 |  |  |  | 682.9839 |  |  |  | 880.9464 |  |  |  | 2686.6767
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | V2 | V3 | Total
Top 20% Risk-Ranked Circuit Segments |  | 360.9624 |  | 360.9624 | 67.55% | 458.4166 |  | 458.4166 | 77.93% | 647.1972 |  | 647.1972 | 94.76% | 879.1076 |  | 879.1076 | 99.79% | 2345.6839 | 0 | 2345.6839 | 87.31% | 469.8149 | 1875.869 | 2345.6839
Other High Risk | Fire Rebuild | 45.2025 | 77.7009 | 122.9034 | 23% | 5.7807 | 98.7981 | 104.5788 | 17.78% | 1.76 |  | 1.76 | 0.2577% | 1.1201 |  | 1.1201 | 0.1271% | 53.8633 | 176.4991 | 230.3623 | 8.575% | 230.3623 |  | 230.3623
| PSPS | 47.0589 |  | 47.0589 | 8.807% | 18.1983 |  | 18.1983 | 3.094% | 15.9613 |  | 15.9613 | 2.337% |  |  | 0 | 0% | 81.2186 |  | 81.2186 | 3.023% | 81.2186 |  | 81.2186
| PSS Identified | 2.5902 |  | 2.5902 | 0.4847% | 0.57576 |  | 0.57576 | 0.09788% |  |  | 0 | 0% |  |  | 0 | 0% | 3.1659 |  | 3.1659 | 0.1178% | 3.1659 |  | 3.1659
| UG System Hardening | 0.82584 |  | 0.82584 | 0.1546% | 1.1939 |  | 1.1939 | 0.203% | 18.05 |  | 18.05 | 2.643% | 0.33996 |  | 0.33996 | 0.03859% | 20.4097 |  | 20.4097 | 0.7597% | 15.7798 | 4.6299 | 20.4097
Other UG Programs |  |  |  | 0 | 0% | 5.2831 |  | 5.2831 | 0.8981% | 0.015341 |  | 0.015341 | 0.002246% | 0.37879 |  | 0.37879 | 0.043% | 5.6773 |  | 5.6773 | 0.2113% | 5.6773 |  | 5.6773
Total |  | 456.6398 | 77.7009 | 534.3408 | 100% | 489.4485 | 98.7981 | 588.2466 | 100% | 682.9839 | 0 | 682.9839 | 100% | 880.9464 | 0 | 880.9464 | 100% | 2510.0186 | 176.4991 | 2686.5176 | 100% | 806.0188 | 1880.4989 | 2686.5176
Note: The 2023 risk rank for segments is based on the 2021 WDRM v2. The 2024-2026 risk rank for segments is based on the 2022 WDRM v3. Numbers may vary due to rounding. (a) Fire Rebuild miles are based on current, known rebuild needs. These miles may change due to future wildfire activity, which may affect other mileage goals in the 2022-2026 workplan. (b) Other underground projects that are not in the top risk ranked circuits (e.g., Rule 20, WRO, Capacity). | [21 empty] | 30% | 70% | 100%
"Top 20% Risk-Ranked Circuit Segments" miles can come from either the WDRM V2 or V3 Risk Rank Models: The "V3 Top 20% Risk-Ranked Circuit Segments" are miles selected from the WDRM V3 risk model with a V3 Risk Rank of <= 720. Any miles with a V3 Risk Rank above 720 that are completed as part of the program would be considered outside “the top 20 percent of risk-ranked circuit segments”. The "V2 Top 20% Risk-Ranked Circuit Segments" are miles selected from the WDRM V2 risk model with a V2 Risk Rank of <=727. Any miles with a V2 Risk Rank above 727 that are completed as part of the program would be considered outside “the top 20 percent of risk-ranked circuit segments”. Sources: - 2023-26 System Hardening Workplan_2023-01-03_Confidential - 'PG&E 2023-26_SH_UGWorkplan_Conf' Sheet
Projects Selected from WDRM V2 ONLY
TABLE PG&E-8.1.2-3: PG&E UNDERGROUNDING WORKPLAN 2023-2026
V2 Top Risk: V2 Risk Rank <=727 V2 ONLY
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534.3408 |  |  |  | 588.4057 |  |  |  | 682.9839 |  |  |  | 880.9464 |  |  |  | 2686.6767
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio
Top 20% Risk-Ranked Circuit Segments |  | 321.2528 |  | 321.2528 | 60.12% | 96.5386 |  | 96.5386 | 16.41% | 33.349 |  | 33.349 | 4.883% | 18.6746 |  | 18.6746 | 2.12% | 469.8149 |  | 469.8149 | 17.49%
Other High Risk | Fire Rebuild | 45.2025 |  | 45.2025 | 8.459% | 5.7807 |  | 5.7807 | 0.9827% | 1.76 |  | 1.76 | 0.2577% | 1.1201 |  | 1.1201 | 0.1271% | 53.8633 |  | 53.8633 | 2.005%
| PSPS | 47.0589 |  | 47.0589 | 8.807% | 18.1983 |  | 18.1983 | 3.094% | 15.9613 |  | 15.9613 | 2.337% |  |  | 0 | 0% | 81.2186 |  | 81.2186 | 3.023%
| PSS Identified | 2.5902 |  | 2.5902 | 0.4847% | 0.57576 |  | 0.57576 | 0.09788% |  |  | 0 | 0% |  |  | 0 | 0% | 3.1659 |  | 3.1659 | 0.1178%
| UG System Hardening | 0.82584 |  | 0.82584 | 0.1546% | 1.1939 |  | 1.1939 | 0.203% | 13.76 |  | 13.76 | 2.015% |  |  | 0 | 0% | 15.7798 |  | 15.7798 | 0.5874%
Other UG Programs |  |  |  | 0 | 0% | 5.2831 |  | 5.2831 | 0.8981% | 0.015341 |  | 0.015341 | 0.002246% | 0.37879 |  | 0.37879 | 0.043% | 5.6773 |  | 5.6773 | 0.2113%
Total |  | 416.9302 | 0 | 416.9302 | 78.03% | 127.5704 | 0 | 127.5704 | 21.69% | 64.8457 | 0 | 64.8457 | 9.494% | 20.1734 | 0 | 20.1734 | 2.29% | 629.5197 | 0 | 629.5197 | 23.43%
Projects Selected from WDRM V3 ONLY
TABLE PG&E-8.1.2-3: PG&E UNDERGROUNDING WORKPLAN 2023-2026
V3 Top Risk: V3 Risk Rank <=720 V3 ONLY
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534.3408 |  |  |  | 588.4057 |  |  |  | 682.9839 |  |  |  | 880.9464 |  |  |  | 2686.6767
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio
Top 20% Risk-Ranked Circuit Segments |  | 39.7097 |  | 39.7097 | 7.432% | 361.878 |  | 361.878 | 61.52% | 613.8482 |  | 613.8482 | 89.88% | 860.433 |  | 860.433 | 97.67% | 1875.869 |  | 1875.869 | 69.83%
Other High Risk | Fire Rebuild |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  | 0 | 0%
| PSPS |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  | 0 | 0%
| PSS Identified |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  | 0 | 0%
| UG System Hardening |  |  | 0 | 0% |  |  | 0 | 0% | 4.29 |  | 4.29 | 0.6281% | 0.33996 |  | 0.33996 | 0.03859% | 4.6299 |  | 4.6299 | 0.1723%
Other UG Programs |  |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  | 0 | 0%
Total |  | 39.7097 | 0 | 39.7097 | 7.432% | 361.878 | 0 | 361.878 | 61.52% | 618.1382 | 0 | 618.1382 | 90.51% | 860.773 | 0 | 860.773 | 97.71% | 1880.4989 | 0 | 1880.4989 | 70%
Community/Butte Rebuild
TABLE PG&E-8.1.2-3: PG&E UNDERGROUNDING WORKPLAN 2023-2026
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534.3408 |  |  |  | 588.4057 |  |  |  | 682.9839 |  |  |  | 880.9464 |  |  |  | 2686.6767
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio
Top 20% Risk-Ranked Circuit Segments |  |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0%
Other High Risk | Fire Rebuild |  | 77.7009 | 77.7009 | 14.54% |  | 98.7981 | 98.7981 | 16.8% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 176.4991 | 6.57%
| PSPS |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0%
| PSS Identified |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0%
| UG System Hardening |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0%
Other UG Programs |  |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0%
Total |  | 0 | 77.7009 | 77.7009 | 14.54% | 0 | 98.7981 | 98.7981 | 16.8% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 176.4991 | 176.4991 | 6.57%

## PG&E 2023-26_SH_UGWorkplan_Conf
PG&E 2023-2026 System Hardening and Undergrounding Workplan
Data as of January 3, 2023
[27 empty] | check | 0 | [15 empty] | check | 0
[13 empty] | 502.9049 | 2697.1635 | 139.8031 | 3339.8715 | 2.7182 | 0 | 0 | 2.7182 | 44.9333 | 10.6458 | 0.8839 | 56.4631 | 455.2534 | 2686.5176 | 138.9192 | 3280.6902 |  | 184.1431 | 534.3408 | 55.6509 | 774.1348 | 127.3717 | 588.2466 | 57.8243 | 773.4426 | 143.1446 | 682.9839 | 23.454 | 849.5824 | 0.59405 | 880.9464 | 1.99 | 883.5304
Order | Order Description | Applicable Risk Model | Progam | Project Type | Risk Rank | Top 20% Risk/Not Top Risk | Category | MAT | SAP Status | Status (see 2nd tab) | WMP GH-03 SH (Y/N) | WMP GH-05 10k UG (Y/N) | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2022 Complete | UG - Pre-2022 Complete | Removal - Pre-2022 Complete | Pre-2022 Total Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - Remaining | UG - Remaining | Removal - Remaining | Total Remaining | Years Assigned (for completion) | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles | OH - 2025 Forecast | UG - 2025 Forecast | Removal - 2025 Forecast | 2025 Total Miles | OH - 2026 Forecast | UG - 2026 Forecast | Removal - 2026 Forecast | 2026 Total Miles | Div | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (V2) | Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | Risk Rank (V3) | 2022 Risk Tranches v3 | v3 Mean Risk | HFTD Tier | Project Type 2
35311627 | CWSP BIG MEADOWS 2101 2510 PH1.4 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35398090 | FRRB -BIG MEADOWS 21012260 OH TL 1.14 | WDRM v3 | FRRB | 0 | 2135 | V3 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57027 | 0 | 0 | 0.57027 | 2023 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1356 | -120.9468 | WDRM v3 |  | 995 |  |  | 2135 | 0 |  | Tier 2 | 0
35374057 | CWSP - GEYSERVILLE - 1101482 | WDRM v3 | SH | CWSP | 1375 | V3 Not Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 |  | 2170 | 0.0056711 |  | 1375 | 1 | 0.0011879 | Tier 2 | CWSP 2024
35379282 | REMG - EL DORADO PH 21016852 PH 5 | WDRM v3 | SH | 0 | 1042 | V3 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7271 | -120.5477 | WDRM v3 |  | 2252 |  |  | 1042 | 0 |  | Tier 3 | 0
35367472 | CWSP_0780_EL DORADO 21026645 1.1 | WDRM v3 | SH | CWSP | 780 | V3 Not Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 |  | 780 | 1 | 0.0031904 | Tier 3 | CWSP 2024
35373630 | CWSP - ORO FINO 11012022 PH 3 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35373629 | CWSP - ORO FINO 11012022 PH 2 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.76 | 0 | 5.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76 | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35367501 | CWSP - ORO FINO 11012022 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.54 | 0 | 4.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54 | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35373626 | CWSP - EL DORADO PH 21016852 PH 4.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.2701 | 0 | 6.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35373625 | CWSP - EL DORADO PH 21016852 PH 3.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.2201 | 0 | 6.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35311626 | CWSP BIG MEADOWS 2101 2510 PH1.3 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35311596 | CWSP BIG MEADOWS 2101 2510 PH1.2 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35286103 | CWSP BIG MEADOWS 2101 2510 PH1.1 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35373624 | CWSP - EL DORADO 21016852 PH 2.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35367473 | CWSP - EL DORADO 21016852 - PH 1.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35390389 | CWSP - MARIPOSA 210110070 PH 1 | WDRM v3 | SH | CWSP | 531 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 |  | 187 | 0.2644 |  | 531 | 1 | 0.0051015 | Tier 2 | CWSP 2024
35375091 | CWSP - LOS OSITOS 21037062 PH 2 | WDRM v3 | SH | CWSP | 516 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.6799 | 0 | 7.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 1 | 0.0052285 | Tier 2 | CWSP 2024
35364020 | CWSP - LOS OSITOS 21037062 | WDRM v3 | SH | CWSP | 516 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 1 | 0.0052285 | Tier 2 | CWSP 2024
35376306 | FRRB - MARIPOSA 21019400 TL-11 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35376304 | FRRB - MARIPOSA 21019400 TL-8 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35376303 | FRRB - MARIPOSA 21019400 TL-9 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374866 | FRRB - MARIPOSA 21019400 TL-7 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2023 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374865 | FRRB - MARIPOSA 21019400 TL-6 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47008 | 0 | 0.47008 | 2023 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374864 | FRRB - MARIPOSA 21019400 TL-5 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0799 | 0 | 2.0799 | 2023 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374862 | FRRB - MARIPOSA 21029590 TL-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2023 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374687 | FRRB - MARIPOSA 21019400 TL-3 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2023 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 | FRRB - 2022
35374686 | FRRB - MARIPOSA 21019400 TL-2 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 2023 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374685 | FRRB - MARIPOSA 210110240 TL-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374684 | FRRB - MARIPOSA 210110170 ML-5 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4201 | 0 | 1.4201 | 2023 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374683 | FRRB - MARIPOSA 21019400 ML-4 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374682 | FRRB - MARIPOSA 210110240 ML-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45 | 2023 | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374559 | FRRB - MARIPOSA 21019400 ML-3 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 1.7 | 2023 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35364022 | CWSP - LOS COCHES 1101625902 | WDRM v3 | SH | CWSP | 462 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 |  | 2006 | 0.0089147 |  | 462 | 1 | 0.0060529 | Tier 2 | CWSP 2024
35374455 | CWSP - SYCAMORE CREEK 11112014 PH 3 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 & 3 | CWSP 2024
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | WDRM v2 | SH | WDDB | 3283 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 2024 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9747 | -121.8839 | WDRM v2 |  | 3283 | 4.6505e-06 |  | 2739 | 0 | 0.00021707 | Tier 3 | Pre
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | WDRM v2 | SH | WDDB | 3283 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 2024 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9718 | -121.8758 | WDRM v2 |  | 3283 | 4.6505e-06 |  | 2739 | 0 | 0.00021707 | Tier 3 | Pre
35329471 | PSPS HIGHLANDS 1104 CB PH 1.2 | WDRM v2 | SH | PSPS | 3243 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 2023 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 |  | 3243 | 5.43e-06 |  | 1561 | 0 | 0.00090896 | Tier 2 | PSPS - 2023 ICUG
35374454 | CWSP - SYCAMORE CREEK 11112014 PH 2 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 | CWSP 2024
35374444 | CWSP - SYCAMORE CREEK 11112014 PH 1 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 | CWSP 2024
35396304 | CWSP - BRUNSWICK 11062104 PH2.2 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35392779 | CWSP - BRUNSWICK 11062104 PH 1.3 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35392778 | CWSP - BRUNSWICK 11062104 PH 1.2 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35373585 | CWSP - BRUNSWICK 11062104 PH 2.1 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 1.44 | 2023 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35367418 | CWSP - BRUNSWICK 11062104 PH1.1 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35396074 | FRRB - BUCKS CREEK 1103CB PH1 | WDRM v3 | FRRB | 0 | 404 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 1.1932 | 2023 | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.8984 | -121.3203 | WDRM v3 |  | 1658 |  |  | 404 | 2 |  | Tier 3 | 0
35403554 | CWSP-SILVERADO 2105 167360&990552 PH1.5 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403553 | CWSP-SILVERADO 2105 167360&990552 PH1.4 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403552 | CWSP-SILVERADO 2105 167360&990552 PH1.3 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403551 | CWSP-SILVERADO 2105 167360&990552 PH1.2 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.25 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35367518 | CWSP-SILVERADO 2105 167360&990552 PH1.1 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35392114 | FRRB PLACERVILLE 21061104 UG TL5 | WDRM v3 | FRRB | 0 | 397 | V3 Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 |  | 2131 | 0.0064469 |  | 397 | 2 | 0.0070659 | Tier 3 | FRRB - UG - 2022
35355173 | PSPS PIT NO 3 2101CB PH 1.3 | WDRM v3 | SH | CWSP | 394 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS - 2023 ICUG
35355171 | PSPS PIT NO 3 21011482 PH 2.3 | WDRM v3 | SH | CWSP | 394 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS - 2023 ICUG
35404753 | CWSP - STANISLAUS 17021888 PH 2.2 | WDRM v3 | SH | 0 | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0 | 0.0073524 | Tier 3 | V3 Tranche 1
35385890 | CWSP - STANISLAUS 1702 LR1888 PH1.4 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.383 | 0 | 1.383 | 2023 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35385889 | CWSP - STANISLAUS 1702 LR1888 PH1.3 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35385888 | CWSP - STANISLAUS 1702 LR1888 PH1.2 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5439 | 0 | 1.5439 | 2023 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35376888 | CWSP - STANISLAUS 17021888 PH 3 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35373705 | CWSP - STANISLAUS 1702 LR1888 PH 2 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35367520 | CWSP - STANISLAUS 1702 LR1888 PH1.1 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2869 | 0 | 2.2869 | 2023 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35373599 | CWSP - EL DORADO PH 2101 LR 63464 PH 2.1 | WDRM v3 | SH | CWSP | 370 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 1 | 0.0074889 | Tier 2 & 3 | CWSP 2024
35367467 | CWSP - EL DORADO PH 2101 LR 63464 PH 1.1 | WDRM v3 | SH | CWSP | 370 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 1 | 0.0074889 | Tier 2 | CWSP 2024
35392113 | FRRB FORESTHILL 110137238 UG TL4 | WDRM v3 | FRRB | 0 | 322 | V3 Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 1 | 0.0088134 | Tier 3 | FRRB - UG - 2022
35387916 | CWSP - FORESTHILL 110137238 PH 1 | WDRM v3 | SH | CWSP | 322 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 1 | 0.0088134 | Tier 2 & 3 | CWSP 2024
35397456 | CWSP - BRUNSWICK 110651486 PH 7.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397455 | CWSP - BRUNSWICK 110651486 PH 7.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397454 | CWSP - BRUNSWICK 110651486 PH 4.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397453 | CWSP - BRUNSWICK 110651486 PH 3.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35397452 | CWSP - BRUNSWICK 110651486 PH 3.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35326790 | PSPS - FLINT1101 CB & 40666 PH1.2 | WDRM v2 | SH | PSPS | 2980 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0.14792 | 2023 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0 | 0.00050684 | Tier 2 | PSPS - 2023 ICUG
35396863 | CWSP - BRUNSWICK 110651486 PH 5.4 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396862 | CWSP - BRUNSWICK 110651486 PH 5.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396861 | CWSP - BRUNSWICK 110651486 PH 5.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396860 | CWSP - BRUNSWICK 110651486 PH 2.4 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396779 | CWSP - BRUNSWICK 110651486 PH 2.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396778 | CWSP - BRUNSWICK 110651486 PH 2.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396776 | CWSP - BRUNSWICK 110651486 PH 1.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396775 | CWSP - BRUNSWICK 110651486 PH 1.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35390288 | CWSP - BRUNSWICK 110651486 - 13993 SEVEN | WDRM v3 | SH | 0 | 315 | V3 Top Risk | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | Y | 0 | 0.12973 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | V3 Tranche 1
35373596 | CWSP - BRUNSWICK 110651486 PH 8 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.09 | 0 | 8.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373595 | CWSP - BRUNSWICK 110651486 PH 7.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373594 | CWSP - BRUNSWICK 110651486 PH 6.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.76 | 0 | 10.76 | 2023 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373593 | CWSP - BRUNSWICK 110651486 PH 5.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.081 | 0 | 3.081 | 2023 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373592 | CWSP - BRUNSWICK 110651486 PH 4.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373590 | CWSP - BRUNSWICK 110651486 PH 3.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35373589 | CWSP - BRUNSWICK 110651486 PH 2.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35367462 | CWSP - BRUNSWICK 110651486 PH 1.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35382936 | CWSP - UPPER LAKE 1101 LR 75370 PH 2 | WDRM v3 | SH | CWSP | 309 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 1 | 0.0089653 | Tier 2 & 3 | CWSP 2024
35382934 | CWSP - UPPER LAKE 1101 LR 75370 PH 1 | WDRM v3 | SH | CWSP | 309 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 1 | 0.0089653 | Tier 2 | CWSP 2024
35379289 | CWSP - PIKE CITY 11011730 PH 2 | WDRM v3 | SH | CWSP | 301 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.74 | 0 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74 | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 1 | 0.0093855 | Tier 3 | CWSP 2024
35375453 | CWSP - PIKE CITY 11011730 PH 1 | WDRM v3 | SH | CWSP | 301 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 1 | 0.0093855 | Tier 3 | CWSP 2024
35385801 | CWSP - NOTRE DAME 11042537 | WDRM v3 | SH | CWSP | 290 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 |  | 1045 | 0.061762 |  | 290 | 1 | 0.0096296 | Tier 2 & 3 | CWSP 2024
35401222 | CWSP - EL DORADO PH 210119612 PH 2.3 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.3201 | 0 | 4.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35401221 | CWSP - EL DORADO PH 210119612 PH 2.2 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35401220 | CWSP - EL DORADO PH 210119612 PH 1.2 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35373598 | CWSP - EL DORADO PH 2101 19612 PH 2.1 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.91 | 0 | 9.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35367466 | CWSP - EL DORADO PH 2101 19612 PH 1.1 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.1 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35367475 | CWSP - EL DORADO 2102CB PH 1.1 | WDRM v3 | SH | CWSP | 278 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.8875 | 0 | 6.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 |  | 2732 | 0.00051722 |  | 278 | 1 | 0.0099516 | Tier 3 | CWSP 2024
35396572 | REMG 339, SWIFT 2110 | WDRM v3 | SH | REMG | 276 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Livermore | Santa Clara | 37.3643 | -121.5789 | WDRM v3 |  | 1769 | 0.015532 |  | 276 | 1 |  | Tier 2 | CWSP 2024
35374562 | CWSP - ORO FINO 110239154 PH 6 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374561 | REMG 36 - ORO FINO 1102 PH 5 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374459 | CWSP - ORO FINO 110239154 PH 4 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374458 | REMG 510 - ORO FINO 1102 PH 3 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 & 3 | CWSP 2024
35374457 | CWSP - ORO FINO 110239154 PH 2 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 3 | CWSP 2024
35374456 | REMG 508 - ORO FINO 1102 PH 1 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 3 | CWSP 2024
35350039 | FRRB - BIG BEND 1102 884340 - B4 SM2 | WDRM v3 | FRRB | FRRB | 267 | V3 Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2023 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 |  | 1288 | 0.040961 |  | 267 | 1 | 0.010152 | Tier 3 | FRRB - UG – 2021
35373588 | CWSP - BRUNSWICK 110651484 PH 3 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35373587 | CWSP - BRUNSWICK 110651484 PH 2 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35367460 | CWSP - BRUNSWICK 110651484 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.41 | 0 | 12.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35396567 | REMG 823 - FRENCHGULCH 1102,SHASTA BALLY | WDRM v3 | SH | REMG | 262 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Igo | Shasta | 40.6068 | -122.6544 | WDRM v3 |  | 2518 | 0.0016954 |  | 262 | 1 |  | Tier 2 | CWSP 2024
35373706 | CWSP - WEST POINT 110113444 PH 2 | WDRM v3 | SH | CWSP | 256 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.45 | 0 | 12.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 1 | 0.01053 | Tier 3 | CWSP 2024
35367522 | CWSP - WEST POINT 110113444 | WDRM v3 | SH | CWSP | 256 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 1 | 0.01053 | Tier 3 | CWSP 2024
35397961 | CWSP - PUEBLO 2103678 PH 4.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35397960 | CWSP - PUEBLO 2103678 PH 4.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396905 | CWSP - PUEBLO 2103678 PH 3.9 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396904 | CWSP - PUEBLO 2103678 PH 3.8 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396903 | CWSP - PUEBLO 2103678 PH 3.7 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396902 | CWSP - PUEBLO 2103678 PH 3.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396900 | CWSP - PUEBLO 2103678 PH 3.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396878 | CWSP - PUEBLO 2103678 PH 3.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396877 | CWSP - PUEBLO 2103678 PH 3.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396876 | CWSP - PUEBLO 2103678 PH 3.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396875 | CWSP - PUEBLO 2103678 PH 2.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396874 | CWSP - PUEBLO 2103678 PH 2.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396871 | CWSP - PUEBLO 2103678 PH 2.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396870 | CWSP - PUEBLO 2103678 PH 2.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396869 | CWSP - PUEBLO 2103678 PH 2.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392777 | CWSP - PUEBLO 2103678 PH 1.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 & 3 | CWSP 2024
35392776 | CWSP - PUEBLO 2103678 PH 1.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392775 | CWSP - PUEBLO 2103678 PH 1.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392774 | CWSP - PUEBLO 2103678 PH 1.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392773 | CWSP - PUEBLO 2103678 PH 1.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 & 3 | CWSP 2024
35373703 | CWSP - PUEBLO 2103678 PH 4.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35373637 | CWSP - PUEBLO 2103678 PH 3.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35373636 | CWSP - PUEBLO 2103678 PH 2.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35367513 | CWSP - PUEBLO 2103678 PH 1.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 | CWSP 2024
35373581 | CWSP - BRUNSWICK 11021010 PH 7 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 2024 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373580 | CWSP - BRUNSWICK 11021010 PH 6 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.3799 | 0 | 8.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799 | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373539 | CWSP - BRUNSWICK 11021010 PH 5 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373538 | CWSP - BRUNSWICK 11021010 PH 4 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373537 | CWSP - BRUNSWICK 11021010 PH 3 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373536 | CWSP - BRUNSWICK 11021010 PH 2 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35367415 | CWSP - BRUNSWICK 11021010 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35396760 | CWSP - PINE GROVE 110245292 PH 1.5 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35396699 | CWSP - PINE GROVE 110245292 PH 1.4 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.3701 | 0 | 3.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35396698 | CWSP - PINE GROVE 110245292 PH 1.3 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35367511 | CWSP - PINE GROVE 110245292 PH 1.1 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 2 & 3 | CWSP 2024
35418371 | CWSP - STANISLAUS 170179826 | WDRM v3 | SH | CWSP | 231 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 2024 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 |  | 2142 | 0.0062159 |  | 231 | 1 | 0.011425 | Tier 2 | V3 Tranche 1
35376889 | CWSP - WEST POINT 1101 CB & 12256 PH2 | WDRM v3 | SH | CWSP | 218 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 1 | 0.011836 | Tier 3 | CWSP 2024
35367526 | CWSP - WEST POINT 1101 CB & 12256 PH 1.1 | WDRM v3 | SH | CWSP | 218 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 13.5701 | 0 | 13.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 1 | 0.011836 | Tier 3 | CWSP 2024
35312546 | PSPS - FLINT1101 CB & 40666 PH1.1 | WDRM v2 | SH | PSPS | 2980 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8933 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0 | 0.00050684 | Tier 2 | PSPS - 2023 ICUG
35396073 | FRRB - KANAKA 1101CB - K4 SM5 | WDRM v3 | FRRB | 0 | 212 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0 | 0.16098 | 2023 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5468 | -121.3424 | WDRM v3 |  | 1480 |  |  | 212 | 2 |  | Tier 2 | 0
35373051 | FRRB - KANAKA 1101CB - K2 SM3 | WDRM v3 | FRRB | 0 | 212 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13864 | 0 | 0.13864 | 2023 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG – 2021
35367500 | CWSP - MIDDLETOWN 1101614 | WDRM v3 | SH | CWSP | 211 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 |  | 2060 | 0.0076984 |  | 211 | 1 | 0.01209 | Tier 3 | CWSP 2024
35404267 | CWSP - PINE GROVE 110213438 PH 2.2 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35402642 | CWSP - PINE GROVE 110213438 1.3 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | N | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 2024 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 |  | Tier 2 & 3 | CWSP 2024
35402641 | CWSP - PINE GROVE 110213438 PH 1.2 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35373635 | CWSP - PINE GROVE 110213438 PH 2.1 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35367510 | CWSP - PINE GROVE 110213438 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 2024 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35403850 | CWSP - MARIPOSA 2101752630 PH 2.3 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403849 | CWSP - MARIPOSA 2101752630 PH 2.2 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.31 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403848 | CWSP - MARIPOSA 2101752630 PH 1.3 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403847 | CWSP - MARIPOSA 2101752630 PH 1.2 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35078178 | STS-COND_IDLE_REMV-295 EAST RD | WDRM v2 | IF | 0 | 2968 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1304 | -122.1182 | WDRM v2 |  | 2968 | 1.8516e-05 |  | 1102 | 0 | 0.0019468 | Tier 3 | Idle Facilities
35221765 | STS-COND_IDLE_REMV - 1504 PINE DR ARNOLD | WDRM v2 | IF | 0 | 2810 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2531 | -120.3592 | WDRM v2 |  | 2810 | 0.00026318 |  | 98 | 1 | 0.01848 | Tier 3 | Idle Facilities
31383326 | E CAP - SR 1107 & 1110 RECONFIGURE | WDRM v2 | Other | 0 | 2799 | V2 Not Top Risk | Other | 06E | CONS | In-Construction | Y | N | 0.41856 | 0 | 0 | 0.41856 | 0 | 0 | 0 | 0 | 0.29867 | 0 | 0 | 0.29867 | 0.11989 | 0 | 0 | 0.11989 | 2023 | 0.11989 | 0 | 0 | 0.11989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4388 | -122.6868 | WDRM v2 |  | 2799 | 0.00029462 |  | 7022 | 0 | 3.4973e-05 | Tier 2 | 0
74001486 | GRIZZLY PEAK BLVD BERKELEY R20A | WDRM v2 | Other | 0 | 2792 | V2 Not Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | WDRM v2 |  | 2792 | 0.00031068 |  | 2633 | 0 | 0.00025777 | Tier 2 & 3 | Other
35277146 | STS-COND_IDLE_REMV-29040 SNOWHITE RD | WDRM v2 | IF | 0 | 2788 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0.13617 | 2023 | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne | 38.1406 | -120.0581 | WDRM v2 |  | 2788 | 0.00031402 |  | 922 | 0 | 0.0025407 | Tier 3 | Idle Facilities
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | WDRM v2 | SH | REMG | 2738 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 2023 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 | WDRM v2 |  | 2738 | 0.0004909 |  | 482 | 0 | 0.0057466 | Tier 3 | Remote Grid Pilot
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | WDRM v2 | SH | CWSP | 2712 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.7748 | 0.053977 | 0 | 1.8288 | 0 | 0 | 0 | 0 | 1.483 | 0.053977 | 0 | 1.5369 | 0.29186 | 0 | 0 | 0.29186 | 2023 | 0.29186 | 0 | 0 | 0.29186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 |  | 2712 | 0.00058985 |  | 1583 | 0 | 0.00088659 | Tier 3 | Pre
35243446 | REMG 665 - OLEMA 1101, MT VISIONS PRNS | WDRM v2 | SH | REMG | 2644 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 |  | 2644 | 0.00096084 |  | 2439 | 0 | 0.00032912 | Tier 2 | REMG 2022-2023
35237937 | EQUIP ACCESS ISSUE 1025 HIDDEN VALLEY RD | WDRM v2 | Other | 0 | 2595 | V2 Not Top Risk | Other | 2BP | UNSC | Ready for Construction | Y | Y | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soquel | Santa Cruz | 37.0341 | -121.9738 | WDRM v2 |  | 2595 | 0.0012326 |  | 1319 | 0 | 0.0013011 | Tier 3 | Other
35342333 | FRRB-BIG BASIN 1101 UG1 SAN VICENTE | WDRM v2 | FRRB | FRRB | 2579 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42576 | 0 | 0.42576 | 2023 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0 | 0.0018854 | Tier 3 | FRRB
35237593 | #CZUSCRUZ 425 SAN VICENTE TERRACE, SCRUZ | WDRM v2 | FRRB | 0 | 2579 | V2 Not Top Risk | Fire Rebuild | 95F | CONS | In-Construction | Y | N | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027462 | 0 | 0 | 0.027462 | 2023 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.1011 | -122.1426 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0 | 0.0018854 | Tier 3 | 0
35382933 | CWSP - MARIPOSA 2101752630 PH 2.1 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.24 | 0 | 5.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35379382 | CWSP - MARIPOSA 2101752630 PH 1.1 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35375184 | CWSP - LOS OSITOS 21037014 PH 5 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375183 | CWSP - LOS OSITOS 21037014 PH 4 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375182 | CWSP - LOS OSITOS 21037014 PH 3 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375181 | CWSP - LOS OSITOS 21037014 PH 2 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375180 | CWSP - LOS OSITOS 21037014 PH 1 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 2024 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35376642 | CWSP - BONNIE NOOK 1102CB PH 4 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.06 | 0 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06 | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35378609 | PLUCODIXIE-COMMERCIAL-Z2 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 2023 | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35376641 | CWSP - BONNIE NOOK 1102CB PH 3 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35376640 | CWSP - BONNIE NOOK 1102CB PH 2 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35376556 | CWSP - BONNIE NOOK 1102CB & 1103CB PH 1 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35368118 | FRRB - BIG BEND 1102 CB - B1 SM1 | WDRM v3 | FRRB | 0 | 187 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0 | 0 | 0.030303 | 2023 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6347 | -121.4543 | WDRM v3 |  | 865 |  |  | 187 | 1 |  | Tier 3 | 0
35378690 | CWSP - MIDDLETOWN 11014646 -PH 4 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.46 | 0 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46 | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35378688 | CWSP - MIDDLETOWN 11014646 -PH 3 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.89 | 0 | 10.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89 | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35378687 | CWSP - MIDDLETOWN 11014646 -PH 2 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35377437 | CWSP - MIDDLETOWN 11014646 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35403556 | CWSP - FORESTHILL 11011802 PH 3.3 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35403555 | CWSP - FORESTHILL 11011802 PH 3.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399836 | CWSP - FORESTHILL 1101 1802 PH 2.3 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.387 | 0 | 5.387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387 | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399835 | CWSP - FORESTHILL 1101 1802 PH 2.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.342 | 0 | 2.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342 | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399834 | CWSP - FORESTHILL 1101 1802 PH 1.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35373526 | CWSP - FORESTHILL 11011802 PH 3.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35373525 | CWSP - FORESTHILL 1101 1802 PH 2.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35367476 | CWSP - FORESTHILL 1101 1802 PH 1.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35382858 | CWSP - LOS OSITOS 21033010 PH 5 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375099 | CWSP - LOS OSITOS 21033010 PH 4 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375096 | CWSP - LOS OSITOS 21033010 PH 3 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375095 | CWSP - LOS OSITOS 21033010 PH 2 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375094 | CWSP - LOS OSITOS 21033010 PH 1 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35373621 | CWSP - EL DORADO 210219542 PH 2.1 | WDRM v3 | SH | CWSP | 176 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.31 | 0 | 7.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 1 | 0.013848 | Tier 3 | CWSP 2024
35367470 | CWSP - EL DORADO 210219542 PH 1.1 | WDRM v3 | SH | CWSP | 176 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.71 | 0 | 6.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 1 | 0.013848 | Tier 3 | CWSP 2024
35383757 | CWSP - WEST POINT 11024788 PH5 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383756 | CWSP - WEST POINT 11024788 PH4 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383755 | CWSP - WEST POINT 11024788 PH3 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383754 | CWSP - WEST POINT 11024788 PH2 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383753 | CWSP - WEST POINT 11024788 PH 1 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 | CWSP 2024
35373535 | CWSP - ORO FINO 1101CB PH 3 | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35373534 | CWSP - ORO FINO 1101CB PH 2 | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35367503 | CWSP - ORO FINO 1101CB | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35374203 | CWSP - NOTRE DAME 1104176446 | WDRM v3 | SH | CWSP | 155 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 |  | 73 | 0.37815 |  | 155 | 1 | 0.015172 | Tier 2 & 3 | CWSP 2024
35402643 | CWSP - PINE GROVE 11013166 PH 1.2 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4561 | 0 | 2.4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35396761 | CWSP - PINE GROVE 11013166 PH 2.2 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35373707 | CWSP - PINE GROVE 11013166 PH 2.1 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35372460 | CWSP - PINE GROVE 11013166 PH 1.1 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.4299 | 0 | 7.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35376305 | FRRB - MARIPOSA 210110170 TL-10 | WDRM v3 | FRRB | FRRB | 137 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0.61004 | 2023 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 2 | 0.015939 | Tier 3 | FRRB - 2022
35374863 | FRRB - MARIPOSA 21019400 TL-4 INSTALL | WDRM v3 | FRRB | FRRB | 137 | V3 Top Risk | Fire Rebuild | 08W | ADER | Estimating | Y | Y | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0.46004 | 2023 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 2 | 0.015939 | Tier 2 | FRRB - 2022
35367515 | CWSP - SALT SPRINGS 210297924 | WDRM v3 | SH | CWSP | 133 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.6799 | 0 | 6.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 |  | 2620 | 0.0010653 |  | 133 | 1 | 0.016045 | Tier 3 | CWSP 2024
35375515 | CWSP - APPLE HILL 2102836878 PH 7 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 | CWSP 2024
35375514 | CWSP - APPLE HILL 2102836878 PH 6 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375513 | CWSP - APPLE HILL 2102836878 PH 5 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375512 | CWSP - APPLE HILL 2102836878 PH 4 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375511 | CWSP - APPLE HILL 2102836878 PH 3 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 3 | CWSP 2024
35375510 | CWSP - APPLE HILL 2102836878 PH 2 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375509 | CWSP - APPLE HILL 2102836878 PH 1 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35404716 | CWSP - PINE GROVE 11026080 PH 4 | WDRM v3 | SH | CWSP | 131 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 1 | 0.016072 | Tier 2 | V3 Tranche 1
35404715 | CWSP - PINE GROVE 11026080 PH 3 | WDRM v3 | SH | CWSP | 131 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 1 | 0.016072 | Tier 2 | V3 Tranche 1
35401013 | CWSP MARIPOSA 210110240 PH 1.4 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35401012 | CWSP MARIPOSA 210110240 PH 1.3 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35401011 | CWSP MARIPOSA 210110240 PH 1.2 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35397963 | CWSP MARIPOSA 210110240 PH 2.3 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35397962 | CWSP MARIPOSA 210110240 PH 2.2 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35382932 | CWSP MARIPOSA 210110240 PH 2.1 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35379383 | CWSP MARIPOSA 210110240 PH 1.1 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35375721 | FRRB - MARIPOSA 21019400 ML-6 | WDRM v3 | FRRB | FRRB | 126 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 3 | FRRB - 2022
35374681 | FRRB - MARIPOSA 21019400 ML-2 | WDRM v3 | FRRB | FRRB | 126 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96004 | 0 | 0.96004 | 2023 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | FRRB - 2022
35373529 | CWSP - APPLE HILL 110413512 PH 4 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 3 | CWSP 2024
35373528 | CWSP - APPLE HILL 110413512 PH 3 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 3 | CWSP 2024
35373527 | CWSP - APPLE HILL 110413512 PH 2 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 2 & 3 | CWSP 2024
35367412 | CWSP - APPLE HILL 110413512 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 2 & 3 | CWSP 2024
35396570 | REMG 432 - PEORIA 1701, TBD | WDRM v3 | SH | REMG | 122 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | La Grange | Tuolumne | 37.7952 | -120.2836 | WDRM v3 |  | 780 | 0.09692 |  | 122 | 1 |  | Tier 2 | CWSP 2024
35374059 | CWSP - ELECTRA 1101L1697 | WDRM v3 | SH | CWSP | 118 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 |  | 2349 | 0.0030208 |  | 118 | 1 | 0.016781 | Tier 2 | CWSP 2024
35377525 | CWSP - PIKE CITY 1101CB PH 3 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.9701 | 0 | 6.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701 | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35375450 | CWSP - PIKE CITY 1101CB PH 2 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.66 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66 | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35375449 | CWSP - PIKE CITY 1101CB PH 1 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.85 | 0 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85 | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35379381 | CWSP - CLAYTON 2212681608 | WDRM v3 | SH | CWSP | 115 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.4 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 |  | 400 | 0.18021 |  | 115 | 1 | 0.016899 | Tier 2 & 3 | CWSP 2024
35396911 | CWSP - FORESTHILL 110150486 - PH 1.5 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396910 | CWSP - FORESTHILL 110150486 - PH 1.4 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396909 | CWSP - FORESTHILL 110150486 - PH 1.3 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396908 | CWSP - FORESTHILL 110150486 - PH 1.2 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35373533 | CWSP - FORESTHILL 110150486 PH 2 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35367478 | CWSP - FORESTHILL 110150486 - PH 1.1 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35383305 | CWSP - WEST POINT 11014706 PH2 | WDRM v3 | SH | CWSP | 107 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.99 | 0 | 4.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 1 | 0.017455 | Tier 3 | CWSP 2024
35367524 | CWSP WEST POINT 1101 LR4706 PH1.1 | WDRM v3 | SH | CWSP | 107 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 14.3201 | 0 | 14.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 1 | 0.017455 | Tier 3 | CWSP 2024
35373597 | CWSP - CALISTOGA 110143924 PH 2 | WDRM v3 | SH | CWSP | 105 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.0201 | 0 | 5.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 1 | 0.017566 | Tier 3 | CWSP 2024
35367464 | CWSP - CALISTOGA 110143924 PH 1.1 | WDRM v3 | SH | CWSP | 105 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.0299 | 0 | 9.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 1 | 0.017566 | Tier 3 | CWSP 2024
35404726 | CWSP - SILVERADO 210478268 PH 2.2 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404355 | CWSP - SILVERADO 210478268 PH 1.6 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404354 | CWSP - SILVERADO 210478268 PH 1.5 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404353 | CWSP - SILVERADO 210478268 PH 1.4 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404352 | CWSP - SILVERADO 210478268 PH 1.3 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404351 | CWSP - SILVERADO 210478268 PH 1.2 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35373704 | CWSP - SILVERADO 210478268 PH 2.1 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35367516 | CWSP - SILVERADO 210478268 PH 1.1 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35362666 | CWSP - CLAYTON 2212614950 | WDRM v3 | SH | CWSP | 100 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 |  | 2561 | 0.0014894 |  | 100 | 1 | 0.018211 | Tier 2 & 3 | CWSP 2024
35409203 | CWSP - MIDDLETOWN 1101433160 | WDRM v3 | SH | CWSP | 99 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 |  | 314 | 0.20636 |  | 99 | 1 | 0.018456 | Tier 2 & 3 | CWSP 2024
35418379 | CWSP - STANISLAUS 170237278 | WDRM v3 | SH | CWSP | 98 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 |  | 2810 | 0.00026318 |  | 98 | 1 | 0.01848 | Tier 3 | V3 Tranche 1
35417148 | CWSP - Foresthill 1102 2106 PH 4 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.56 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417144 | CWSP - Foresthill 1102 2106 PH 3 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.7 | 0 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417117 | CWSP - Foresthill 1102 2106 PH 2 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417110 | CWSP - Foresthill 1102 2106 PH 1 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
35362685 | CWSP - STANISLAUS 1701 CB PH1.7 | WDRM v3 | SH | 0 | 95 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.42708 | 0 | 0 | 0.42708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.178 | -120.3801 | WDRM v3 |  | 56 |  |  | 95 | 1 |  | Tier 2 | 0
35372463 | CWSP - ANTLER 1101CB | WDRM v3 | SH | CWSP | 94 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.020076 | 1.99 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01 | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 |  | 2207 | 0.0049349 |  | 94 | 1 | 0.0187 | Tier 2 | CWSP 2024
TBD |  | WDRM v3 |  |  | 93 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9 | 0 | 10.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0 | 0.018723 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 93 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0 | 0.018723 | Tier 3 | V3 Tranche 1
35395931 | REMG - ANTLER 11011520 PH 1.5 | WDRM v3 | SH | REMG | 91 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377 | 2023 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.9225 | -122.4132 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 |  | Tier 2 | CWSP 2024
35395930 | CWSP - ANTLER 11011520 PH 1.4 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.369 | 0 | 0.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369 | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35395929 | CWSP - ANTLER 11011520 PH 1.3 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.057 | 0 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057 | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35395928 | CWSP - ANTLER 11011520 PH 1.2 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.937 | 0 | 1.937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937 | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35372464 | CWSP - ANTLER 11011520 PH1.1 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.553 | 0 | 6.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553 | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35418356 | CWSP - SILVERADO 2105900104 | WDRM v3 | SH | CWSP | 90 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 |  | 2351 | 0.0030112 |  | 90 | 1 | 0.018786 | Tier 3 | V3 Tranche 1
35418366 | CWSP - SHADY GLEN 110248894 PH2 | WDRM v3 | SH | CWSP | 89 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 1 | 0.018876 | Tier 3 | V3 Tranche 1
35418361 | CWSP - SHADY GLEN 110248894 PH1 | WDRM v3 | SH | CWSP | 89 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.601 | 0 | 6.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 1 | 0.018876 | Tier 3 | V3 Tranche 1
35376559 | CWSP - SILVERADO 2105658898 PH 2 | WDRM v3 | SH | CWSP | 87 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 1 | 0.018978 | Tier 3 | CWSP 2024
35376558 | CWSP - SILVERADO 2105658898 PH 1 | WDRM v3 | SH | CWSP | 87 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.25 | 0 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 1 | 0.018978 | Tier 3 | CWSP 2024
35396569 | REMG 841 - KESWICK 1101, WSKYTWN ENV SCH | WDRM v3 | SH | REMG | 83 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.5822 | -122.5413 | WDRM v3 |  | 1135 | 0.053968 |  | 83 | 1 |  | Tier 2 | CWSP 2024
35396568 | REMG 840 - KESWICK 1101, BRANDY CRK BEAC | WDRM v3 | SH | REMG | 83 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.616 | -122.5718 | WDRM v3 |  | 1135 | 0.053968 |  | 83 | 1 |  | Tier 2 | CWSP 2024
35373620 | PSPS - EL DORADO PH 2101 LR 668674 PH2.1 | WDRM v3 | SH | CWSP | 81 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 1 | 0.019264 | Tier 3 | PSPS
35367468 | PSPS - EL DORADO PH 2101 LR 668674 PH1 | WDRM v3 | SH | CWSP | 81 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 1 | 0.019264 | Tier 3 | PSPS
35383758 | CWSP - WEST POINT 11021341 PH1 | WDRM v3 | SH | CWSP | 80 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 |  | 2247 | 0.0041901 |  | 80 | 1 | 0.019265 | Tier 3 | CWSP 2024
35409211 | CWSP - SHADY GLEN 110132726 PH 2 | WDRM v3 | SH | CWSP | 71 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 1 | 0.02023 | Tier 2 | V3 Tranche 1
35409205 | CWSP - SHADY GLEN 110132726 PH 1 | WDRM v3 | SH | CWSP | 71 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 15.2 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2 | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 1 | 0.02023 | Tier 2 | CWSP 2024
35391723 | CWSP - PLACERVILLE 210611132 PH 6 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391722 | CWSP - PLACERVILLE 210611132 PH 5 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391721 | CWSP - PLACERVILLE 210611132 PH 4 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391473 | CWSP - PLACERVILLE 210611132 PH 3 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 | CWSP 2024
35391472 | CWSP - PLACERVILLE 210611132 PH 2.1 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 & 3 | CWSP 2024
35391471 | CWSP - PLACERVILLE 210611132 PH 1.1 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 & 3 | CWSP 2024
TBD |  | WDRM v3 |  |  | 66 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.788 | 0 | 8.788 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0 | 0.02064 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 66 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0 | 0.02064 | Tier 3 | V3 Tranche 1
35409217 | CWSP - OREGON TRAIL 11021584 PH 2 | WDRM v3 | SH | CWSP | 64 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 1 | 0.0208 | Tier 2 | CWSP 2024
35409215 | CWSP - OREGON TRAIL 11021584 PH 1 | WDRM v3 | SH | CWSP | 64 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.1 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 1 | 0.0208 | Tier 2 | CWSP 2024
35373532 | CWSP - APPLE HILL 21027502 PH 3 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 3 | CWSP 2024
35373530 | CWSP - APPLE HILL 21027502 PH 2 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 15.51 | 0 | 15.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51 | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 3 | CWSP 2024
35367414 | CWSP - APPLE HILL 21027502 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 2 & 3 | CWSP 2024
35404349 | CWSP - ELECTRA 1101 LR7104 PH 1.2 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.47 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35376890 | CWSP - ELECTRA 11017104 PH2 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.09 | 0 | 7.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35372462 | CWSP - ELECTRA 1101 LR7104 PH 1.1 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.019886 | 4.85 | 0 | 4.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35373628 | CWSP - ORO FINO 110276008 PH 2 | WDRM v3 | SH | CWSP | 61 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.7299 | 0 | 8.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 1 | 0.020869 | Tier 3 | CWSP 2024
35367504 | CWSP - ORO FINO 110276008 | WDRM v3 | SH | CWSP | 61 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.35 | 0 | 9.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 1 | 0.020869 | Tier 3 | CWSP 2024
35418375 | CWSP - STANISLAUS 17026028 | WDRM v3 | SH | CWSP | 60 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 |  | 2670 | 0.0008147 |  | 60 | 1 | 0.021109 | Tier 3 | V3 Tranche 1
35385804 | CWSP - SILVERADO 2104 LR 632 PH 2 | WDRM v3 | SH | CWSP | 59 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | CWSP 2024
35385803 | CWSP - SILVERADO 2104 LR 632 PH 1 | WDRM v3 | SH | CWSP | 59 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | CWSP 2024
35418305 | CWSP - PLACERVILLE 2106935216 PH 3 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35418255 | CWSP - PLACERVILLE 2106935216 PH 2 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35417127 | CWSP - PLACERVILLE 2106935216 PH 1 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35364784 | CWSP - SYCAMORE CREEK 11112268 PH 3 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.1701 | 0 | 7.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35363720 | CWSP - SYCAMORE CREEK 11112268 PH 2 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35363559 | CWSP - SYCAMORE CREEK 11112268 PH 1 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35409202 | CWSP - MIDDLETOWN 11011314 PH1 | WDRM v3 | SH | CWSP | 56 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 |  | 915 | 0.078235 |  | 56 | 1 | 0.021686 | Tier 2 & 3 | CWSP 2024
35375452 | CWSP - PIKE CITY 11011720 | WDRM v3 | SH | CWSP | 52 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 |  | 1710 | 0.017864 |  | 52 | 1 | 0.02211 | Tier 3 | CWSP 2024
35374570 | CWSP - NARROWS 2102CB | WDRM v3 | SH | CWSP | 46 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2799 | 0 | 7.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799 | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 |  | 658 | 0.11807 |  | 46 | 1 | 0.022999 | Tier 2 | CWSP 2024
35374569 | CWSP - BUCKS CREEK 1102CB - BELDEN | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | CWSP 2024
35374567 | CWSP - BUCKS CREEK 1102CB - RODGERS FLAT | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | CWSP 2024
35374566 | CWSP - BUCKS CREEK 1102CB - ROCK CREST | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374564 | CWSP - BUCKS CREEK 1102CB PH 2 N/O HWY 7 | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.79 | 1.76 | 8.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55 | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374563 | CWSP - BUCKS CREEK 1102CB PH 1 N/O HWY 7 | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374443 | CWSP - ALLEGHANY 1102CB NEVADA PH 5 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.7701 | 0 | 6.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701 | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374208 | CWSP - ALLEGHANY 1102CB NEVADA PH 4 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.89 | 0 | 4.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89 | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374206 | CWSP - ALLEGHANY 1102CB NEVADA PH 3 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374205 | CWSP - ALLEGHANY 1102CB SIERRA PH 2 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.24 | 0 | 6.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24 | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374204 | CWSP - ALLEGHANY 1102CB SIERRA PH 1 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.7201 | 0 | 6.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201 | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35377520 | CWSP - MIDDLETOWN 1101171414 | WDRM v3 | SH | CWSP | 38 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 |  | 328 | 0.19983 |  | 38 | 1 | 0.024501 | Tier 3 | CWSP 2024
35374202 | CWSP - NOTRE DAME 11042028 PH 2 | WDRM v3 | SH | CWSP | 37 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.6701 | 0 | 4.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701 | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 1 | 0.024521 | Tier 3 | CWSP 2024
35374200 | CWSP - NOTRE DAME 11042028 PH 1 | WDRM v3 | SH | CWSP | 37 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.04 | 0 | 8.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 1 | 0.024521 | Tier 3 | CWSP 2024
35385806 | CWSP - SILVERADO 2104 LR 515946 PH 2 | WDRM v3 | SH | CWSP | 33 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.69 | 0 | 6.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 1 | 0.025445 | Tier 3 | CWSP 2024
35385805 | CWSP - SILVERADO 2104 LR 515946 PH 1 | WDRM v3 | SH | CWSP | 33 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.74 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 1 | 0.025445 | Tier 3 | CWSP 2024
TBD |  | WDRM v3 |  |  | 32 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 2024 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 |  | 178 | 0.2712 |  | 32 | 0 | 0.025831 | Tier 3 | V3 Tranche 1
35409213 | CWSP - APPLE HILL 1104CB | WDRM v3 | SH | CWSP | 30 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 |  | 1422 | 0.032289 |  | 30 | 1 | 0.025967 | Tier 2 | CWSP 2024
35367335 | CWSP - BONNIE NOOK 1101CB PH 1 | WDRM v3 | SH | CWSP | 20 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 1 | 0.02949 | Tier 3 | CWSP 2024
35365064 | CWSP - BONNIE NOOK 1101CB PH 2 | WDRM v3 | SH | CWSP | 20 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.34 | 0.22992 | 10.5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699 | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 1 | 0.02949 | Tier 3 | CWSP 2024
35373634 | CWSP - ORO FINO 11022090 PH 3 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.4299 | 0 | 4.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299 | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35373632 | CWSP - ORO FINO 11022090 PH 2 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.2299 | 0 | 10.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299 | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35367508 | CWSP - ORO FINO 11022090 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.94 | 0 | 5.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94 | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35367507 | CWSP - ORO FINO 1102CB | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35235158 | #CZUSCRUZ 2151 PINE FLAT RD, SCRUZ | WDRM v2 | FRRB | 0 | 2539 | V2 Not Top Risk | Fire Rebuild | 95F | FICL | In-Construction | Y | N | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030871 | 0 | 0 | 0.030871 | 2023 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Felton | Santa Cruz | 37.0448 | -122.0673 | WDRM v2 |  | 2539 | 0.0016007 |  | 903 | 3 | 0.0026122 | Tier 3 | 0
35211671 | DR~STS-COND_IDLE_REMV-1120 NATUREWOOD DR | WDRM v2 | IF | 0 | 2536 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83769 | 0.83769 | 2023 | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0289 | -121.0036 | WDRM v2 |  | 2536 | 0.0016155 |  | 1432 | 0 | 0.0011018 | Tier 2 | Idle Facilities
35244167 | DR-COND_IDLE_REMV-WINCHESTER DR | WDRM v2 | IF | 0 | 2500 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22519 | 0.22519 | 2023 | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Meadow Vista | Placer | 38.9969 | -121.0593 | WDRM v2 |  | 2500 | 0.001823 |  | 1766 | 0 | 0.00071024 | Tier 2 | Idle Facilities
35225253 | STS-COND_IDLE_REMV-214 TABERNACLE DRIVE | WDRM v2 | IF | 0 | 2474 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028409 | 0.028409 | 2023 | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 37.0631 | -122.0333 | WDRM v2 |  | 2474 | 0.0020379 |  | 1225 | 0 | 0.0015415 | Tier 3 | Idle Facilities
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | WDRM v2 | SH | CWSP | 2456 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4441 | 0 | 0 | 3.4441 | 0 | 0 | 0 | 0 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538 | 2023 | 0.12538 | 0 | 0 | 0.12538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1332 | -122.1257 | WDRM v2 |  | 2456 | 0.0021702 |  | 1113 | 0 | 0.0019056 | Tier 3 | Pre
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | WDRM v2 | FRRB | FRRB | 2435 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20114 | 0 | 0.20114 | 2023 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 |  | 2435 | 0.002283 |  | 1105 | 0 | 0.0019396 | Tier 3 | FRRB
35225011 | STS-COND_IDLE_REMV - AT 1580 PRESTON ST | WDRM v2 | IF | 0 | 2433 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 2023 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Cambria | San Luis Obispo | 35.5452 | -121.0718 | WDRM v2 |  | 2433 | 0.0023119 |  | 2127 | 0 | 0.00047475 | Tier 2 | Idle Facilities
35224941 | +STS-COND_IDLE_REMV-R/O 2PE 1PS/O #67 BL | WDRM v2 | IF | 0 | 2399 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Morro Bay | San Luis Obispo | 35.3583 | -120.8253 | WDRM v2 |  | 2399 | 0.0025799 |  | 2247 | 0 | 0.00041125 | Tier 2 | Idle Facilities
35225467 | STS-COND_IDLE_REMV - 1/P/S/O/587 AVOCADO | WDRM v2 | IF | 0 | 2387 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023674 | 0.023674 | 2023 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Watsonville | Santa Cruz | 37.012 | -121.7958 | WDRM v2 |  | 2387 | 0.0026825 |  | 1464 | 0 | 0.0010495 | Tier 2 | Idle Facilities
35243445 | REMG 49 - OLEMA 1101, HOME RANCH PRNS | WDRM v2 | SH | REMG | 2360 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 |  | 2360 | 0.0028981 |  | 3015 | 0 | 0.00012995 | Tier 2 | REMG 2022-2023
35342460 | FRRB - BIG BASIN 1102 OH1 LODGE RD | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | N | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 2023 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1741 | -122.1812 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35385802 | CWSP - CLAYTON 2212 LR 96224 | WDRM v3 | SH | CWSP | 15 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.6 | 0 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | CWSP 2024
35376891 | CWSP - SILVERADO 2104646776 | WDRM v3 | SH | CWSP | 14 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.4 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4 | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 |  | 1235 | 0.044601 |  | 14 | 1 | 0.034265 | Tier 3 | CWSP 2024
35373708 | CWSP - ANTLER 11011384 PH 2 | WDRM v3 | SH | CWSP | 11 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.73 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73 | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 1 | 0.038738 | Tier 2 | CWSP 2024
35372465 | CWSP - ANTLER 11011384 | WDRM v3 | SH | CWSP | 11 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.84 | 0 | 11.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84 | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 1 | 0.038738 | Tier 2 | CWSP 2024
35372258 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2 | WDRM v3 | SH | CWSP | 10 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.892 | 0 | 8.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 1 | 0.039297 | Tier 2 | CWSP 2024
35372257 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1 | WDRM v3 | SH | CWSP | 10 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.808 | 0 | 9.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 1 | 0.039297 | Tier 2 | CWSP 2024
35372461 | CWSP - TIGER CREEK 201 CB & 320746 | WDRM v3 | SH | CWSP | 8 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 |  | 1744 | 0.016801 |  | 8 | 1 | 0.040941 | Tier 2 & 3 | CWSP 2024
35396763 | CWSP - PINE GROVE 1101CB PH 1.3 | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35353527 | CITADEL WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8221 | -121.5955 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353525 | SHERWOOD CIR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8243 | -121.5994 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353479 | CRESTON DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8211 | -121.6013 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353477 | WYCLIFF WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8192 | -121.6024 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353470 | JOPLIN CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8146 | -121.6066 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353468 | PONDEROSA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8167 | -121.598 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353467 | DREXEL DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8182 | -121.5952 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353466 | W PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8091 | -121.5998 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353463 | ANDOVER DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8121 | -121.5914 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35342338 | FRRB - BIG BASIN 1102 UG5 LITTLEBASIN CG | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.163 | -122.1902 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35353399 | EUREKA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.5973 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35352075 | BILLE WAGSTAFF | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | 2023 | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7777 | -121.6077 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35350874 | NORWOOD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2023 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7637 | -121.5732 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35350582 | PLUCODIXIE-HIDEAWAY Z7 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | 2023 | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35350519 | PLUCODIXIE-ALTA CAMP Z6 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47348 | 0 | 0.47348 | 2023 | 0 | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35396762 | CWSP - PINE GROVE 1101CB PH 1.2 | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0.07 | 2.91 | 0 | 2.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35342337 | FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1657 | -122.2231 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35342336 | FRRB - BIG BASIN 1102 UG2 CAMPGROUND | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1699 | -122.2026 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35342335 | FRRB - BIG BASIN 1102 UG3 HWY 236 | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1672 | -122.2131 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35222036 | CZUSCRUZ 21600 BIG BASIN, BOULDER CRK | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 95F | PEND | Permitting/Dependency | Y | N | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52462 | 0 | 0 | 0.52462 | 2023 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1676 | -122.2 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | 0
35334541 | FRRB -BIG BASIN 1102 12758 P1S2 CYPRESS | WDRM v2 | FRRB | FRRB | 2358 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16629 | 0 | 0.16629 | 2023 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 3 | 0.0026407 | Tier 3 | FRRB
35250987 | X22: XCZUSCRUZ 185 KNOB HILL DR, BOULDER | WDRM v2 | FRRB | 0 | 2358 | V2 Not Top Risk | Fire Rebuild | 95F | UNSC | Ready for Construction | Y | N | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088258 | 0 | 0 | 0.088258 | 2023 | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1376 | -122.1453 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 3 | 0.0026407 | Tier 3 | 0
35275478 | STS-POLE_IDLE_REMV-23600 STATE HWY 9 | WDRM v2 | IF | 0 | 2354 | V2 Not Top Risk | Idle Facilities | 2AF | DCNL | In-Construction | Y | N | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara | 37.2476 | -122.0791 | WDRM v2 |  | 2354 | 0.0029842 |  | 825 | 0 | 0.0029655 | Tier 3 | Idle Facilities
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 2023 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 2023 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35372259 | CWSP - PINE GROVE 1101CB | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 2024 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35325226 | PSPS PIT NO 3 21011482 PH 2.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9868 | -121.8481 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35325225 | PSPS PIT NO 3 21011482 PH 1.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9729 | -121.7814 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35325224 | PSPS PIT NO 3 2101CB PH 1.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 41.0088 | -121.7129 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35294730 | PSPS - PIT NO 3 21011482 PH 2.1 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9685 | -121.8246 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35294729 | PSPS - PIT NO 3 21011482 PH 1.1 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7479 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35128962 | RECOND HWY 20 - FTBRAGG 1102 | WDRM v2 | Other | 0 | 2305 | V2 Not Top Risk | Other | 08J | UNSE | Scoping/Scoped | Y | N | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 2024 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.4154 | -123.7771 | WDRM v2 |  | 2305 | 0.0033857 |  | 2316 | 0 | 0.00037958 | Tier 2 | 0
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | WDRM v2 | SH | PRE | 2271 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.3718 | 0.093561 | 0 | 1.4653 | 0 | 0 | 0 | 0 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.099242 | 0.052841 | 0 | 0.15208 | 2023 | 0.099242 | 0.052841 | 0 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 |  | 2271 | 0.0037571 |  | 558 | 0 | 0.0048336 | Tier 3 | Pre
35318074 | FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | WDRM v2 | FRRB | FRRB | 2246 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29356 | 0 | 0.29356 | 2023 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 |  | 2246 | 0.0041981 |  | 936 | 3 | 0.002497 | Tier 2 | FRRB
35321894 | FRRB - PT MORETTI 1101 12122 PH1 SM4 | WDRM v2 | FRRB | FRRB | 2199 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13826 | 0 | 0.13826 | 2023 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0 | 0.00042654 | Tier 2 | FRRB
35297464 | FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | WDRM v2 | FRRB | FRRB | 2199 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021 | 2023 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0 | 0.00042654 | Tier 2 | FRRB
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | WDRM v2 | SH | 0 | 2192 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.8559 | 0 | 0 | 1.8559 | 1.8402 | 0 | 0 | 1.8402 | 0 | 0 | 0 | 0 | 0.01572 | 0 | 0 | 0.01572 | 2023 | 0.01572 | 0 | 0 | 0.01572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.5056 | -122.9307 | WDRM v2 |  | 2192 | 0.0053427 |  | 1383 | 0 | 0.0011714 | Tier 3 | 0
35284810 | FRRB - HMB 1103 SM CO LR6012 PUMP HOUSE | WDRM v2 | FRRB | FRRB | 2186 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 2024 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2086 | -122.3251 | WDRM v2 |  | 2186 | 0.0054078 |  | 2434 | 0 | 0.00033154 | Tier 2 | FRRB
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | WDRM v2 | SH | PSPS | 2123 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.24 | 2023 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 |  | 2123 | 0.0065148 |  | 1979 | 0 | 0.00055552 | Tier 2 | PSPS - Community Resiliency
35244173 | DR-COND_IDLE_REMV-5260 GRANITE CREEK RD | WDRM v2 | IF | 0 | 2116 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 2023 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7888 | -120.9206 | WDRM v2 |  | 2116 | 0.0066099 |  | 237 | 3 | 0.011346 | Tier 2 | Idle Facilities
35342339 | FRRB - BIG BASIN 1102 UG6 BB VINEYARD | WDRM v2 | FRRB | FRRB | 2070 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0 | 0.16193 | 2023 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 |  | 2070 | 0.0075562 |  | 1413 | 0 | 0.0011281 | Tier 3 | FRRB
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | WDRM v2 | FRRB | FRRB | 2055 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 2023 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0 | 0.0002898 | Tier 2 | FRRB - UG - 2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | WDRM v2 | FRRB | FRRB | 2055 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.5239 | 0 | 2.5239 | 0 | 0 | 0 | 0 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0.88277 | 0 | 0.88277 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0 | 0.0002898 | Tier 2 | FRRB - UG - 2021
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35223063 | PSPS - DUNBAR 1101 - OAKMONT | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0.3197 | 2023 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 | WDRM v2 | FRRB | FRRB | 2005 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8075 | -120.0935 | WDRM v2 |  | 2005 | 0.0089565 |  | 2299 | 0 | 0.00038767 | Tier 2 | FRRB
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | DOCC | In-Construction | Y | Y | 2.3513 | 0.44621 | 0 | 2.7975 | 0 | 0 | 0 | 0 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 2023 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 2.8136 | 0.37955 | 0 | 3.1932 | 0 | 0 | 0 | 0 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.61288 | 0.33883 | 0 | 0.9517 | 2023 | 0.61288 | 0.33883 | 0 | 0.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62519 | 2.2513 | 0 | 2.8765 | 2023 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.7455 | 0.57576 | 0 | 2.3212 | 0 | 0 | 0 | 0 | 1.6231 | 0 | 0 | 1.6231 | 0.12235 | 0.57576 | 0 | 0.69811 | 2024 | 0 | 0 | 0 | 0 | 0.12235 | 0.57576 | 0 | 0.69811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35223241 | DR~STS-COND_IDLE_REMV-R/O 5500 ALPINE R | WDRM v2 | IF | 0 | 1917 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Portola Valley | San Mateo | 37.3567 | -122.2181 | WDRM v2 |  | 1917 | 0.011065 |  | 630 | 2 | 0.0042054 | Tier 2 | Idle Facilities
35320462 | PSPS - JAMESON 1105371694 | WDRM v2 | SH | PSPS | 1848 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2642 | -122.1295 | WDRM v2 |  | 1848 | 0.012819 |  | 8953 | 0 |  | Tier 2 | PSPS - 2023 ICUG
35120413 | DR-STS-COND_IDLE_REMV78TOYONDRIVE | WDRM v2 | IF | 0 | 1837 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020455 | 0.020455 | 2023 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Fairfax | Marin | 37.9797 | -122.6039 | WDRM v2 |  | 1837 | 0.013281 |  | 1001 | 0 | 0.0022627 | Tier 3 | Idle Facilities
35275962 | STS-COND_IDLE_REMV-1W/O 14508 WONDERLAND | WDRM v2 | IF | 0 | 1828 | V2 Not Top Risk | Idle Facilities | 2BF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 2023 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.7096 | -122.3366 | WDRM v2 |  | 1828 | 0.013687 |  | 838 | 0 | 0.002921 | Tier 2 | Idle Facilities
35343741 | PSPS - DUNBAR 1101 440 PH 1.3 | WDRM v2 | SH | PSPS | 1827 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3371 | -122.4929 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0 | 0.0063584 | Tier 2 & 3 | PSPS - 2023 ICUG
35312542 | PSPS - DUNBAR 1101 440 PH 1.1 | WDRM v2 | SH | PSPS | 1827 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Glen Ellen | Sonoma | 38.3791 | -122.5192 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0 | 0.0063584 | Tier 2 & 3 | PSPS - 2023 ICUG
35294728 | PSPS - PIT NO 3 2101CB PH 1.1 | WDRM v2 | SH | CWSP | 1816 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7478 | WDRM v2 |  | 1816 | 0.01407 |  | 326 | 2 | 0.0086689 | Tier 2 | PSPS
35211297 | DR~STS-COND_IDLE_REMV-2000 PONDEROSA WY | WDRM v2 | IF | 0 | 1801 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21326 | 0.21326 | 2023 | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.02 | -120.944 | WDRM v2 |  | 1801 | 0.014579 |  | 142 | 1 | 0.015811 | Tier 2 | Idle Facilities
35221715 | STS-COND_IDLE_REMV-20599 KINGS CT | WDRM v2 | IF | 0 | 1770 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0.041288 | 2023 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Soulsbyville | Tuolumne | 37.9965 | -120.2635 | WDRM v2 |  | 1770 | 0.015509 |  | 2025 | 0 | 0.00052763 | Tier 2 | Idle Facilities
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | WDRM v2 | FRRB | FRRB | 1748 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 |  | 1748 | 0.016728 |  | 521 | 3 | 0.0051671 | Tier 2 | FRRB
35145001 | PSPS - CLAYTON 2215 - CB | WDRM v2 | SH | PSPS | 1739 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 2024 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.931 | -121.9736 | WDRM v2 |  | 1739 | 0.016935 |  | 1812 | 0 | 0.0006705 | Tier 2 & 3 | PSPS - Community Resiliency
35121520 | NR7 OFAC_IDLE_REMV-LAKEVIEW RD-14LOC | WDRM v2 | IF | 0 | 1722 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65606 | 0.65606 | 2023 | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8122 | -122.3073 | WDRM v2 |  | 1722 | 0.017574 |  | 247 | 1 | 0.010915 | Tier 2 | Idle Facilities
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 1.85 | 2023 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 |  | 1703 | 0.018088 |  | 933 | 0 | 0.0025042 | Tier 2 | PSPS
35329012 | PSPS CLARK ROAD 1102 LR514690 PH 2.2 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 2023 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0 | 0.0022353 | Tier 2 | PSPS
35299633 | PSPS CLARK ROAD 1102 LR514690 PH 2.1 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 2023 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0 | 0.0022353 | Tier 2 | PSPS
35244150 | FT-COND_IDLE_REMV-D/P R/O 19182 GERMAN | WDRM v2 | IF | 0 | 1700 | V2 Not Top Risk | Idle Facilities | 2AF | ESTS | Estimating | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.437 | -120.8154 | WDRM v2 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | Idle Facilities
35284023 | FRRB - DUNBAR 1101416 | WDRM v2 | FRRB | FRRB | 1684 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 | WDRM v2 |  | 1684 | 0.019316 |  | 732 | 0 | 0.0035071 | Tier 3 | FRRB - UG - 2021
35208054 | STS-COND_IDLE_REMV-BAYNE RD | WDRM v2 | IF | 0 | 1666 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14867 | 0.14867 | 2023 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7975 | -120.8281 | WDRM v2 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 | Idle Facilities
35295446 | FRRB - BUCKS CREEK 1103 CB PH2 | WDRM v2 | FRRB | FRRB | 1658 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 2023 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 39.8957 | -121.2789 | WDRM v2 |  | 1658 | 0.020623 |  | 404 | 2 | 0.0069107 | Tier 2 & 3 | FRRB
35335235 | PSPS - SILVERADO 2104708 | WDRM v2 | SH | PSPS | 1648 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5192 | -122.4719 | WDRM v2 |  | 1648 | 0.02118 |  | 619 | 1 | 0.0043024 | Tier 3 | PSPS - 2023 ICUG
35280505 | HWY 299 SHASTA R20A | WDRM v2 | Other | 0 | 1614 | V2 Not Top Risk | Other | 30A | ESTS | Estimating | Y | Y | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5923 | -122.4836 | WDRM v2 |  | 1614 | 0.022607 |  | 43 | 2 | 0.023649 | Tier 3 | Other
35211659 | DR-COND_IDLE_REMV-14932 MOONSHINE RD | WDRM v2 | IF | 0 | 1590 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0.030303 | 2023 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.3894 | -121.0978 | WDRM v2 |  | 1590 | 0.023389 |  | 149 | 2 | 0.015567 | Tier 3 | Idle Facilities
35224856 | BR-12-5A HWY 191 RELOCATION, PARB | WDRM v2 | Other | 0 | 1537 | V2 Not Top Risk | Other | 10K | CONS | In-Construction | Y | Y | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 2024 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | WDRM v2 |  | 1537 | 0.025842 |  | 362 | 2 | 0.0076725 | Tier 2 & 3 | Other
35329016 | PSPS CLARK ROAD 1102 LR47006 PH 1.2 | WDRM v2 | SH | PSPS | 1535 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 2023 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 2 | 0.022808 | Tier 2 | PSPS
35299635 | PSPS CLARK ROAD 1102 LR47006 PH 1.1 | WDRM v2 | SH | PSPS | 1535 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 2 | 0.022808 | Tier 2 | PSPS
35245152 | FRRB - KANAKA 1101 - K4 PH 4.17 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35245141 | FRRB - KANAKA 1101 - K4 PH 4.6 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35244699 | FRRB - KANAKA 1101 - K4 PH 4.4 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35244698 | FRRB - KANAKA 1101 - K4 PH 4.3 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35236989 | FRRB - KANAKA 1101 - K2 PH2.2 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655 | 2023 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - REMG - 2021
35235704 | FRRB - KANAKA 1101 - K5 PH5.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG - 2021
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG - 2021
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 2023 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35320466 | CWSP - WILLOW CREEK 11032936 | WDRM v2 | SH | CWSP | 1474 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Salyer | Trinity | 40.8669 | -123.5148 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | CWSP - 2023 ICUG
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0199 | 0 | 1.0199 | 2023 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297697 | FRRB - WILLOW CREEK 11032936 UG TL3 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014773 | 0 | 0.014773 | 2023 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996 | 2023 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2023 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 2023 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2023 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6598 | 0 | 4.6598 | 2023 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35281816 | FRRB - WILLOW CREEK 11032936 ML2OHBRIDGE | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046591 | 0 | 0 | 0.046591 | 2023 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45985 | 0 | 0.45985 | 2023 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35264104 | DRSTS-OFAC_IDLE_REMV-7NE/O 15921 STATE H | WDRM v2 | IF | 0 | 1446 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0.10549 | 2023 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5593 | -120.8348 | WDRM v2 |  | 1446 | 0.030867 |  | 254 | 2 | 0.010591 | Tier 3 | Idle Facilities
35150991 | T2-POLE_IDLE_REMV - GIBNEY DR MIRANDA*RM | WDRM v2 | IF | 0 | 1429 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072159 | 0.072159 | 2023 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt | 40.2188 | -123.8212 | WDRM v2 |  | 1429 | 0.031951 |  | 2354 | 0 | 0.00036401 | Tier 2 | Idle Facilities
35243441 | REMG 17 - CHALLENGE 1102, PONDEROSA WAY | WDRM v2 | SH | REMG | 1428 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.483 | -121.2466 | WDRM v2 |  | 1428 | 0.032082 |  | 408 | 2 | 0.0068437 | Tier 2 & 3 | REMG 2022-2023
35290901 | EP BICKFORD RANCH RD WATER TANK LINCOLN | WDRM v2 | Other | 0 | 1408 | V2 Not Top Risk | Other | 16H | CONS | In-Construction | Y | N | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64432 | 0 | 0 | 0.64432 | 2023 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer |  |  | WDRM v2 |  | 1408 | 0.032911 |  | 2686 | 0 | 0.0002367 | Tier 2 | 0
35242865 | DR~STS-COND_IDLE_REMV-410 STAR HILL RD | WDRM v2 | IF | 0 | 1376 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.4126 | -122.3299 | WDRM v2 |  | 1376 | 0.034933 |  | 1131 | 0 | 0.0018648 | Tier 3 | Idle Facilities
35353435 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.4 | WDRM v2 | SH | REMG | 1363 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9081 | -120.8468 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | WDRM v2 | SH | PSPS | 1363 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84962 | 0.52121 | 1.3708 | 2023 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | WDRM v2 | SH | PSPS | 1363 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73144 | 0 | 0.73144 | 2023 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | WDRM v2 | FRRB | FRRB | 1322 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86989 | 0 | 0.86989 | 2023 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0 | 0.0020497 | Tier 2 | FRRB
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | WDRM v2 | FRRB | FRRB | 1322 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5902 | 0 | 2.5902 | 2023 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0 | 0.0020497 | Tier 2 | FRRB
35145540 | PSPS - FROGTOWN 1702 - CB | WDRM v2 | SH | PSPS | 1316 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61212 | 0.53447 | 0 | 1.1466 | 2023 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 |  | 1316 | 0.039234 |  | 1205 | 0 | 0.0016222 | Tier 3 | PSPS - Scoped
35251360 | MIRABEL 1101 - RECONDUCTOR 3,338 FT | WDRM v2 | Other | 0 | 1313 | V2 Not Top Risk | Other | 06E | PEND | Permitting/Dependency | Y | N | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34261 | 0 | 0 | 0.34261 | 2023 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.4736 | -122.8979 | WDRM v2 |  | 1313 | 0.039363 |  | 1448 | 0 | 0.001078 | Tier 2 | 0
35243442 | REMG 130 - PIKE CITY 1102, TAHOE NF | WDRM v2 | SH | REMG | 1308 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | North San Juan | Sierra | 39.4385 | -120.9959 | WDRM v2 |  | 1308 | 0.03956 |  | 162 | 2 | 0.0147 | Tier 3 | REMG 2022-2023
35083699 | *CANC*STS-COND_IDLE_REMV-38113 PETERSON | WDRM v2 | IF | 0 | 1302 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 2023 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0361 | -119.3341 | WDRM v2 |  | 1302 | 0.040157 |  | 348 | 3 | 0.0080497 | Tier 3 | Idle Facilities
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 0 | 0.31004 | 2023 | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 2023 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.070076 | 0 | 0.070076 | 2023 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | DOCC | In-Construction | Y | Y | 0 | 1.8256 | 0 | 1.8256 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0.00625 | 0 | 0.00625 | 2023 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 |  | 1299 | 0.040282 |  | 250 | 0 | 0.010796 | Tier 3 | FRRB - UG - 2021
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 0 | 0.28409 | 2023 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - REMG - 2021
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 2023 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0 | 0.30303 | 2023 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35038684 | REMV IDLE 4 LOCS 48600 VALLEY DR LAY | WDRM v2 | IF | 0 | 1293 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16818 | 0.16818 | 2023 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | Mendocino | 39.7297 | -123.5078 | WDRM v2 |  | 1293 | 0.040695 |  | 992 | 0 | 0.0022826 | Tier 2 | Idle Facilities
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | WDRM v2 | FRRB | FRRB | 1285 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 2023 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 1285 | 0.041237 |  | 2987 | 0 | 0.00013567 | Tier 2 | FRRB
35208094 | FT STS-TRAN_IDLE_REMV-2W/O6NW/O 7251 WIL | WDRM v2 | IF | 0 | 1237 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079735 | 0.079735 | 2023 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.1679 | -124.0858 | WDRM v2 |  | 1237 | 0.044439 |  | 2057 | 0 | 0.00051421 | Tier 2 | Idle Facilities
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | WDRM v2 | FRRB | FRRB | 1172 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 2023 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 |  | 1172 | 0.050559 |  | 785 | 0 | 0.0031715 | Tier 2 & 3 | FRRB
35332870 | PSPS - CURTIS 1701 CB PH 1.3 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38674 | 0 | 0.38674 | 2023 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35332868 | PSPS - CURTIS 1701 CB PH 1.2 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 2.5299 | 2023 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35312541 | PSPS - CURTIS 1701 CB PH 1.1 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0.42992 | 2023 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35283938 | CWSP - WOODSIDE 1101 FS 775939 PH 1.1 | WDRM v2 | SH | CWSP | 1145 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3845 | -122.2937 | WDRM v2 |  | 1145 | 0.05299 |  | 1026 | 0 | 0.0021738 | Tier 3 | CWSP 2022-2023
35399833 | PSPS - SAN LUIS OBISPO 1101 PH 1.2 | WDRM v2 | SH | PSPS | 1104 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.33 | 1.33 | 2023 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2752 | -120.6435 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0 | 0.00059698 | Tier 2 | PSPS - 2023 ICUG
35320444 | PSPS - SAN LUIS OBISPO 1101 PH 1.1 | WDRM v2 | SH | PSPS | 1104 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 2024 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2683 | -120.6383 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0 | 0.00059698 | Tier 2 | PSPS - 2023 ICUG
35341551 | REMG 499 - PIT NO 7 1101 | WDRM v2 | SH | 0 | 1055 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.8417 | -122.0114 | WDRM v2 |  | 1055 | 0.060819 |  | 549 | 0 | 0.0049268 | Tier 2 | 0
35338402 | PSPS - PANORAMA 1101 CB PH 1.2 | WDRM v2 | SH | PSPS | 1038 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 2023 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | PSPS - 2023 ICUG
35320464 | PSPS - PANORAMA 1101 CB PH 1.1 | WDRM v2 | SH | PSPS | 1038 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 2023 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | PSPS - 2023 ICUG
35244146 | FT-COND_IDLE_REMV-6935-6963 MORNING CAN | WDRM v2 | IF | 0 | 1035 | V2 Not Top Risk | Idle Facilities | 2AF | MAPP | In-Construction | Y | N | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04072 | 0.04072 | 2023 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6211 | -120.7249 | WDRM v2 |  | 1035 | 0.06292 |  | 436 | 2 | 0.0063805 | Tier 2 | Idle Facilities
35384087 | PSPS - CLARK ROAD 1102 LR514690 PH 1.4 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6578 | -121.5657 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35329015 | REMG 794 - CLARK ROAD 1102 | WDRM v2 | SH | REMG | 1033 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6575 | -121.5646 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35329014 | PSPS CLARK ROAD 1102 LR514690 PH 1.2 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701 | 2023 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35299634 | PSPS CLARK ROAD 1102 LR514690 PH 1.1 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799 | 2023 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35277147 | STS-POLE_IDLE_REMV-GREELY HILL RD CO#423 | WDRM v2 | IF | 0 | 1019 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40871 | 0.40871 | 2023 | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | Mariposa | 37.7302 | -120.182 | WDRM v2 |  | 1019 | 0.065187 |  | 433 | 0 | 0.0064317 | Tier 2 | Idle Facilities
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | WDRM v2 | SH | PSPS | 999 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | WDRM v2 |  | 999 | 0.067405 |  | 2578 | 0 | 0.0002828 | Tier 2 | PSPS - Community Resiliency
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0644 | 0 | 3.0644 | 2023 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17159 | 0 | 0.17159 | 2023 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49451 | 0 | 0.49451 | 2023 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0.97992 | 2023 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 2023 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35211643 | DR-STS-COND_IDLE_REMV-6 PLS W/O 11554 ON | WDRM v2 | IF | 0 | 981 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24489 | 0.24489 | 2023 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6201 | -122.4409 | WDRM v2 |  | 981 | 0.069495 |  | 957 | 0 | 0.0024201 | Tier 2 | Idle Facilities
35343398 | PSPS - WYANDOTTE 1110 LR980944 PH1.10 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5169 | -121.5161 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343397 | PSPS - WYANDOTTE 1110 LR980944 PH1.9 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5082 | -121.5038 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343396 | PSPS - WYANDOTTE 1110 LR980944 PH1.8 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0822 | 0 | 1.0822 | 2023 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343395 | PSPS - WYANDOTTE 1110 LR980944 PH1.7 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 2023 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343394 | PSPS - WYANDOTTE 1110 LR980944 PH1.6 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 1.17 | 2023 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331309 | REMG 801 - WYANDOTTE 1110, OROVILLE DAM | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5255 | -121.4817 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | 2023 ICUG
35331308 | PSPS WYANDOTTE 1110 LR980944 PH1.4 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0.82 | 2023 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331307 | PSPS WYANDOTTE 1110 LR980944 PH1.3 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 2023 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331306 | PSPS WYANDOTTE 1110 LR980944 PH1.2 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5178 | -121.4854 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35312560 | PSPS WYANDOTTE 1110 LR980944 PH1.1 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 3.61 | 2023 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35254948 | X22: CWSP - VOLTA 11011596 - PH1.6 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9803 | 0 | 0 | 0.9803 | 2023 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254947 | CWSP - VOLTA 11011596 - PH1.5 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.263 | 0 | 0.263 | 2023 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254946 | X22: CWSP - VOLTA 11011596 - PH1.4 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 2023 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254945 | CWSP - VOLTA 11011596 - PH1.3 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 2023 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35243453 | X22: CWSP-VOLTA-11011596-PH1 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.428 | 0 | 0 | 1.428 | 0 | 0 | 0 | 0 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205 | 2023 | 0.34205 | 0 | 0 | 0.34205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35227033 | PUEBLO 2102, DRY CREEK | WDRM v2 | SH | ECOP | 951 | V2 Not Top Risk | Base SH | 08W | APPR | Estimating | Y | N | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.433 | -122.4021 | WDRM v2 |  | 951 | 0.073389 |  | 338 | 0 | 0.0083787 | Tier 3 | ECOP
35224438 | #+STS-COND_IDLE_REMV-SUDDEN RANCH AT RR | WDRM v2 | IF | 0 | 949 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017235 | 0.017235 | 2023 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | Santa Barbara | 34.5386 | -120.5365 | WDRM v2 |  | 949 | 0.073569 |  | 2028 | 0 | 0.00052681 | Tier 2 | Idle Facilities
35292758 | FRRB BIG MEADOWS 2101 CB PH1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 2023 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2786 | 0 | 1.2786 | 2023 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 2023 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 2023 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 2023 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35280493 | FRRB -BIG MEADOWS 21012260 UG TL 1.13 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12008 | 0.35 | 0 | 0.47008 | 2023 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0 | 0.0046735 | Tier 2 | FRRB
35279985 | FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.115 | 0 | 3.115 | 2023 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0 | 0.0046735 | Tier 2 | FRRB
35280498 | FRRB - CRESCENT MILLS 21012056 OH TL 1.1 | WDRM v2 | FRRB | FRRB | 895 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 2023 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 3 | 0.0028532 | Tier 2 | FRRB
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | WDRM v2 | FRRB | FRRB | 895 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008 | 2023 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 3 | 0.0028532 | Tier 2 | FRRB
35145458 | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS | WDRM v2 | IF | 0 | 882 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6263 | 1.6263 | 2023 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.758 | -120.0408 | WDRM v2 |  | 882 | 0.08233 |  | 550 | 0 | 0.0049103 | Tier 2 | Idle Facilities
35235674 | FRRB - BIG BEND 1102 - B1 PH1.1 | WDRM v2 | FRRB | FRRB | 865 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 865 | 0.084888 |  | 187 | 1 | 0.013302 | Tier 3 | FRRB - UG - 2021
35221620 | STS-COND_IDLE_REMV-12345 HERITAGE WAY | WDRM v2 | IF | 0 | 854 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 2023 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Gilroy | Santa Clara | 37.0533 | -121.6625 | WDRM v2 |  | 854 | 0.085689 |  | 1052 | 0 | 0.0020756 | Tier 2 | Idle Facilities
35297984 | REMG 368 - STILLWATER 1101 | WDRM v2 | FRRB | FRRB | 851 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 | WDRM v2 |  | 851 | 0.085979 |  | 2266 | 0 | 0.00040165 | Tier 2 | FRRB
35190945 | EP 2951 HIGHWAY 4 MURPHYS WAGON TRAIL | WDRM v2 | Other | 0 | 838 | V2 Not Top Risk | Other | 10Q | CONS | In-Construction | Y | N | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1169 | 0 | 0 | 1.1169 | 2023 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | Calaveras |  |  | WDRM v2 |  | 838 | 0.088153 |  | 1734 | 0 | 0.00073728 | Tier 2 | 0
35332718 | PEORIA 1705 RECONDUCTORING | WDRM v2 | Other | 0 | 835 | V2 Not Top Risk | Other | 06H | ESTS | Estimating | Y | N | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 2024 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne | 37.8663 | -120.4293 | WDRM v2 |  | 835 | 0.088489 |  | 1778 | 0 | 0.00070132 | Tier 2 | 0
35204814 | DR-COND_IDLE_REMV-14820 FERN RD | WDRM v2 | IF | 0 | 820 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21023 | 0.21023 | 2023 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6759 | -121.971 | WDRM v2 |  | 820 | 0.09042 |  | 1536 | 0 | 0.00093567 | Tier 2 & 3 | Idle Facilities
74010582 | GREEN VALLEY RD EL DORADO CNTY R20A | WDRM v2 | Other | 0 | 811 | V2 Not Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | WDRM v2 |  | 811 | 0.092281 |  | 1184 | 0 | 0.0016787 | Tier 2 | Other
35173857 | SILVERADO 2104_RECONDUCTOR NEAR FUSE 797 | WDRM v2 | Other | 0 | 792 | V2 Not Top Risk | Other | 06E | CONS | In-Construction | Y | N | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 | 0.18939 | 2023 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5866 | -122.4424 | WDRM v2 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | 0
35211230 | DRCOND_IDLE_REMV-5726 EVERGLADE | WDRM v2 | IF | 0 | 774 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061174 | 0.061174 | 2023 | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2454 | -121.3989 | WDRM v2 |  | 774 | 0.098287 |  | 3122 | 0 | 0.00010395 | Tier 2 | Idle Facilities
35221249 | DR~STS-OFAC_IDLE_REMV - 1/N/O/AT 908 ORE | WDRM v2 | IF | 0 | 771 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 2023 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5519 | -121.5068 | WDRM v2 |  | 771 | 0.098498 |  | 1281 | 0 | 0.0013786 | Tier 2 | Idle Facilities
35217564 | DR-COND_IDLE_REMV - 1PWO 11188 TOWNSHIP | WDRM v2 | IF | 0 | 758 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2864 | -121.3535 | WDRM v2 |  | 758 | 0.10087 |  | 2091 | 0 | 0.00049399 | Tier 2 | Idle Facilities
35221659 | STS-COND_IDLE_REMV-1N/O 2W/O 10835 WATER | WDRM v2 | IF | 0 | 744 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15076 | 0.15076 | 2023 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Ione | Amador | 38.3665 | -120.9291 | WDRM v2 |  | 744 | 0.10338 |  | 2444 | 0 | 0.00032629 | Tier 2 | Idle Facilities
35342151 | PSPS - JAMESON 1102 LR65516 1.9 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 2023 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342150 | PSPS - JAMESON 1102 LR65516 1.8 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2623 | -122.1638 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342148 | PSPS - JAMESON 1102 LR65516 1.7 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 1.19 | 2023 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342147 | PSPS - JAMESON 1102 LR65516 1.6 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8259 | 0 | 1.8259 | 2023 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342146 | PSPS - JAMESON 1102 LR65516 1.5 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.397 | 0 | 2.397 | 2023 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342145 | PSPS - JAMESON 1102 LR65516 1.4 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16307 | 0 | 0.16307 | 2023 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342144 | PSPS - JAMESON 1102 LR65516 1.3 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.617 | 0 | 1.617 | 2023 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342143 | PSPS - JAMESON 1102 LR65516 1.2 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 2023 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35320442 | PSPS - JAMESON 1102 LR65516 1.1 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38693 | 0 | 0.38693 | 2023 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35337015 | CWSP - JAMESON 1105 LR9472 PH 1.4 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 0 | 0.48996 | 2023 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | CWSP - 2023 ICUG
35337014 | CWSP - JAMESON 1105 LR9472 PH 1.3 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.020076 | 0 | 0.85 | 2023 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | CWSP - 2023 ICUG
35337013 | CWSP - JAMESON 1105 LR9472 PH 1.2 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1517 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | 2023 ICUG
35320459 | CWSP - JAMESON 1105 LR9472 PH 1.1 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.157 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | 2023 ICUG
35329011 | PSPS CLARK ROAD 1102 LR81296 PH 1.4 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3229 | 0 | 2.3229 | 2023 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35329010 | PSPS CLARK ROAD 1102 LR81296 PH 1.3 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.814 | 0.020076 | 2.8341 | 2023 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35329009 | PSPS CLARK ROAD 1102 LR81296 PH 1.2 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94091 | 0.020076 | 0.96098 | 2023 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35299631 | PSPS CLARK ROAD 1102 LR81296 PH 1.1 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4299 | 0 | 3.4299 | 2023 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35342310 | PSPS - TEJON 11023751 PH 2.4 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.357 | 0 | 1.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35342308 | PSPS - TEJON 11023751 PH 2.3 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.997 | 0 | 2.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8868 | -118.9361 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35342307 | PSPS - TEJON 11023751 PH 2.2 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.252 | 0 | 2.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8833 | -118.9271 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35335289 | PSPS - TEJON 1102 LR3751 PH 1.3 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.5775 | 0 | 1.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35335288 | PSPS - TEJON 1102 LR3751 PH 1.2 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9158 | -118.9258 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35321445 | PSPS - TEJON 11023751 PH 2.1 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35312554 | PSPS - TEJON 1102 LR3751 PH 1.1 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9321 | -118.9283 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35207962 | FT-COND_IDLE_REMV-13080 FERN RD EAST | WDRM v2 | IF | 0 | 678 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 2023 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6587 | -121.8939 | WDRM v2 |  | 678 | 0.11449 |  | 1076 | 0 | 0.0020262 | Tier 2 | Idle Facilities
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | WDRM v2 | SH | WDDB | 666 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.0733 | 0 | 0 | 1.0733 | 0 | 0 | 0 | 0 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049 | 2023 | 0.78049 | 0 | 0 | 0.78049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6824 | -120.8551 | WDRM v2 |  | 666 | 0.11621 |  | 775 | 0 | 0.0032085 | Tier 2 | Top 20% MAVF CPZ
35339665 | CWSP - HORSESHOE 1101 LR50140 PH 1.4 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75909 | 0 | 0.75909 | 2023 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35339664 | CWSP - HORSESHOE 1101 LR50140 PH 1.3 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75208 | 0.17008 | 0 | 0.92216 | 2023 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35339663 | CWSP - HORSESHOE 1101 LR50140 PH 1.2 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | 2023 ICUG
35320447 | CWSP - HORSESHOE 1101 LR50140 PH 1.1 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0.83996 | 0 | 1.9299 | 2023 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35335287 | PSPS - TEJON 1102 LR2455 PH 1.3 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8466 | -118.8987 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35335286 | PSPS - TEJON 1102 LR2455 PH 1.2 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8542 | -118.893 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35312553 | PSPS - TEJON 1102 LR2455 PH 1.1 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8837 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35246501 | REMG 44-FULTON 1107, PEPPERWOOD PRESERVE | WDRM v2 | SH | REMG | 637 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0994 | 7.0994 | 2023 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5702 | -122.6772 | WDRM v2 |  | 637 | 0.12169 |  | 1034 | 0 | 0.0021304 | Tier 3 | REMG 2022-2023
35149235 | 8/31-REMV IDLE 6 LOCS 13311 HWY 29 | WDRM v2 | IF | 0 | 626 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16515 | 0.16515 | 2023 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8612 | -122.6264 | WDRM v2 |  | 626 | 0.12376 |  | 582 | 1 | 0.0045905 | Tier 2 | Idle Facilities
35274596 | CWSP MARIPOSA 2101 LR 309438 PH 1.3 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4889 | -119.9738 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35274595 | CWSP MARIPOSA 2101 LR 309438 PH 1.2 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0.057 | 2023 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4983 | -119.9732 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35250572 | CWSP - MARIPOSA 2101 LR 309438 PH1.1 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5026 | -119.9886 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35317937 | CWSP HARTLEY 1101 LR336932 1.10 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0436 | -122.9704 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317936 | CWSP HARTLEY 1101 LR336932 1.9 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0402 | -122.9674 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317935 | CWSP HARTLEY 1101 LR336932 1.8 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0405 | -122.9316 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317934 | CWSP HARTLEY 1101 LR336932 1.7 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.041 | -122.9443 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317932 | CWSP HARTLEY 1101 LR336932 1.6 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.044 | -122.9654 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317931 | CWSP HARTLEY 1101 LR336932 1.5 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0439 | -122.9625 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317930 | CWSP HARTLEY 1101 LR336932 1.4 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317929 | CWSP HARTLEY 1101 LR336932 1.3 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317928 | CWSP HARTLEY 1101 LR336932 1.2 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0406 | -122.9405 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35250574 | CWSP HARTLEY 1101 LR336932 1.1 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0512 | -122.9379 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35332866 | PSPS - JESSUP 1103 LR348657 PH 1.4 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 2023 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 |  | 590 | 0.13388 |  | 2153 | 0 | 0.00046034 | Tier 2 | PSPS - 2023 ICUG
35332864 | PSPS - JESSUP 1103 LR348657 PH 1.3 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5058 | -122.2644 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35332863 | PSPS - JESSUP 1103 LR348657 PH 1.2 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4921 | -122.2838 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35312549 | PSPS - JESSUP 1103 LR348657 PH 1.1 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 2023 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35342318 | PSPS - TEJON 1102 LR732836 PH 2.5 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8363 | -118.8637 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342317 | PSPS - TEJON 1102 LR732836 PH 2.4 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8295 | -118.8723 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342316 | PSPS - TEJON 1102 LR732836 PH 2.3 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.837 | -118.8663 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342315 | PSPS - TEJON 1102 LR732836 PH 2.2 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8407 | -118.8677 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342314 | PSPS - TEJON 1102 LR732836 PH 1.5 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8594 | -118.8797 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342313 | PSPS - TEJON 1102 LR732836 PH 1.4 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8835 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342312 | PSPS - TEJON 1102 LR732836 PH 1.3 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8726 | -118.8905 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342311 | PSPS - TEJON 1102 LR732836 PH 1.2 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8765 | -118.8926 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35320607 | PSPS - TEJON 1102 LR732836 PH 2.1 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.846 | -118.872 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35312555 | PSPS - TEJON 1102 LR732836 PH 1.1 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35364450 | PSPS - VOLTA 11011516 PH 1.17 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.496 | 0 | 0 | 1.496 | 2023 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364448 | PSPS - VOLTA 11011516 PH 1.16 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364446 | PSPS - VOLTA 11011516 PH 1.15 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.057008 | 2.5381 | 0 | 2.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364442 | PSPS - VOLTA 11011516 PH 1.14 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364440 | PSPS - VOLTA 11011516 PH 1.13 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364339 | PSPS - VOLTA 11011516 PH 1.12 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364337 | PSPS - VOLTA 11011516 PH 1.11 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364336 | PSPS - VOLTA 11011516 PH 1.10 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8561 | 0 | 1.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364334 | PSPS - VOLTA 11011516 PH 1.9 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364333 | PSPS - VOLTA 11011516 PH 1.8 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8131 | 0 | 2.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364332 | PSPS - VOLTA 11011516 PH 1.7 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334468 | REMG 465 - VOLTA 1101 1.6 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3139 | -122.0706 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | 2023 ICUG
35316201 | PLUCODIXIE-HOT SPRINGS RD Z5 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68314 | 0 | 0.68314 | 2023 | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1397 | -120.9389 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316200 | PLUCODIXIE-KINDER AVE Z4 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 1.0417 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0417 | 0 | 1.0417 | 2023 | 0 | 1.0417 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1413 | -120.957 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316019 | PLUCODIXIE-FORGAY AVE Z3 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 1.017 | 0 | 1.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.017 | 0 | 1.017 | 2023 | 0 | 1.017 | 0 | 1.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1435 | -120.9581 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316018 | PLUCODIXIE-BIDWELL ST Z2 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 0.7197 | 0 | 0.7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7197 | 0 | 0.7197 | 2023 | 0 | 0.7197 | 0 | 0.7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35334467 | PSPS - VOLTA 11011516 PH 1.5 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3305 | -122.0971 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334466 | PSPS - VOLTA 11011516 PH 1.4 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3386 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35313249 | PLUCODIXIE-BUSH ST Z1 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 1.2871 | 0 | 1.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2871 | 0 | 1.2871 | 2023 | 0 | 1.2871 | 0 | 1.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35334465 | PSPS - VOLTA 11011516 PH 1.3 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3507 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334464 | PSPS - VOLTA 11011516 PH 1.2 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3748 | -122.1217 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35312556 | CWSP - VOLTA 11011516 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3453 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | 2023 ICUG
35335283 | CWSP - LINCOLN 1104 LR2070 PH 1.4 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9566 | -121.2286 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35335282 | CWSP - LINCOLN 1104 LR2070 PH 1.3 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35335281 | CWSP - LINCOLN 1104 LR2070 PH 1.2 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35332959 | CWSP LINCOLN 1104 LR2070 PH 2.3 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.8975 | -121.2471 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35332958 | CWSP LINCOLN 1104 LR2070 PH 2.2 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3701 | 0 | 1.3701 | 2023 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | CWSP - 2023 ICUG
35320454 | CWSP - LINCOLN 1104 LR2070 PH 1.1 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.952 | -121.2551 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35320312 | CWSP LINCOLN 1104 LR2070 PH 2.1 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2023 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | CWSP - 2023 ICUG
35262345 | DR-STS-POLE_IDLE_REMV-4S/OR/O3235MEADOW | WDRM v2 | IF | 0 | 554 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17803 | 0.17803 | 2023 | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3774 | -122.4352 | WDRM v2 |  | 554 | 0.14355 |  | 1152 | 0 | 0.0017959 | Tier 2 | Idle Facilities
35056808 | R20A - FREESTONE SONOMA COUNTY | WDRM v2 | Other | 0 | 534 | V2 Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | WDRM v2 |  | 534 | 0.14747 |  | 1720 | 0 | 0.00074971 | Tier 3 | Other
35275479 | FT-OFAC_IDLE_REMV - #7 ON LINE S/O CO#5 | WDRM v2 | IF | 0 | 532 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26705 | 0.26705 | 2023 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4236 | -121.8237 | WDRM v2 |  | 532 | 0.14786 |  | 1752 | 0 | 0.00072124 | Tier 2 | Idle Facilities
35262812 | LUCERNE 1103 - DIST LINE WORK | WDRM v2 | Other | 0 | 512 | V2 Top Risk | Other | 06H | ESTS | Estimating | Y | N | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 2024 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lucerne | Lake |  |  | WDRM v2 |  | 512 | 0.1512 |  | 3737 | 0 | 5.9361e-05 | Tier 2 | 0
35260649 | X22: CWSP - PASO ROBLES 1103N04 PH 1 | WDRM v2 | SH | CWSP | 510 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 2024 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7334 | -120.8792 | WDRM v2 |  | 510 | 0.1516 |  | 1729 | 0 | 0.00074213 | Tier 2 | CWSP 2022-2023
35335293 | PSPS - VACAVILLE 1111 CB PH 1.4 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 0 | 2.41 | 2023 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35335292 | PSPS - VACAVILLE 1111 CB PH 1.3 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 0 | 1.8799 | 2023 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35335291 | PSPS - VACAVILLE 1111 CB PH 1.2 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2023 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35320440 | PSPS - VACAVILLE 1111 CB PH 1.1 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3783 | -122.0044 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35243443 | REMG 188 - TIVY VALLEY 1107 | WDRM v2 | SH | REMG | 491 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Sanger | Fresno | 36.8168 | -119.3407 | WDRM v2 |  | 491 | 0.15534 |  | 1657 | 0 | 0.00080485 | Tier 2 | REMG 2022-2023
35244105 | DR-COND_IDLE_REMV-20095 HWY 175 | WDRM v2 | IF | 0 | 474 | V2 Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7672 | -122.6631 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | Idle Facilities
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | Y | 0.17614 | 1.2508 | 0 | 1.4269 | 0 | 0 | 0 | 0 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542 | 2023 | 0.088068 | 0.047348 | 0 | 0.13542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0684 | 0 | 1.0684 | 2023 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 2023 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0267 | 0 | 1.0267 | 2023 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782 | 2023 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79413 | 0 | 0.79413 | 2023 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79375 | 0 | 0 | 0.79375 | 2023 | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756 | 2023 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85246 | 0 | 0.85246 | 2023 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0.58883 | 2023 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 1.0394 | 2023 | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.71326 | 0 | 0 | 0.71326 | 0 | 0 | 0 | 0 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746 | 2023 | 0.17746 | 0 | 0 | 0.17746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449 | 2023 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303 | 2023 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174479 | REMG 749-MIDDLETOWN 1101,ANDERSON SPRNGS | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04 | 2023 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35301110 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.6 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 2023 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0037879 | 1.3765 | 0 | 1.3803 | 2023 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 2024 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7241 | -122.619 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35340270 | PSPS - CORNING 1102 LR915324 PH 1.2 | WDRM v2 | SH | PSPS | 457 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 2.34 | 2023 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0 | 0.0001615 | Tier 2 | PSPS - 2023 ICUG
35311898 | PSPS - CORNING 1102 LR915324 PH 1.1 | WDRM v2 | SH | PSPS | 457 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2023 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0 | 0.0001615 | Tier 2 | PSPS - 2023 ICUG
35274594 | CWSP MARIPOSA 2101 LR 35244 PH 2.4 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5353 | -119.9554 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.756 | 0 | 2.756 | 2023 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274592 | CWSP MARIPOSA 2101 LR 35244 PH 2.2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5116 | -119.9647 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274591 | CWSP MARIPOSA 2101 LR 35244 PH1.3 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5195 | -119.9397 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.132 | 0 | 2.132 | 2023 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | WDRM v2 | SH | REMG | 428 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2023 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 3 | Remote Grid Pilot
35250938 | STS-POLE_IDLE_REMV-4/S/O 1/N/O 4511 BROO | WDRM v2 | IF | 0 | 424 | V2 Top Risk | Idle Facilities | 2AF | ESTS | Estimating | Y | N | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24432 | 0.24432 | 2023 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.6385 | -120.9907 | WDRM v2 |  | 424 | 0.1736 |  | 886 | 0 | 0.0026967 | Tier 3 | Idle Facilities
35330243 | CWSP - REDBUD 1101 LR323962 PH1.5 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0621 | -122.5786 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | 2023 ICUG
35330242 | CWSP - REDBUD 1101 LR323962 PH1.4 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0671 | -122.5853 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | 2023 ICUG
35330241 | CWSP - REDBUD 1101 LR323962 PH1.3 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8549 | 0 | 2.8549 | 2023 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35330219 | CWSP - REDBUD 1101 LR323962 PH1.2 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299 | 2023 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35330217 | CWSP - REDBUD 1101323962 PH 2.6 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 2023 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330216 | CWSP - REDBUD 1101323962 PH 2.5 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330215 | CWSP - REDBUD 1101323962 PH 2.4 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 2023 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330213 | CWSP - REDBUD 1101323962 PH 2.3 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.5887 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330211 | CWSP - REDBUD 1101323962 PH 2.2 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 1.9701 | 2023 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35317399 | CWSP - REDBUD 1101323962 PH 2.1 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35312550 | CWSP - REDBUD 1101 LR323962 PH1.1 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54 | 2023 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | WDRM v2 | SH | REMG | 421 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 2023 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Ahwahnee | Madera | 37.3642 | -119.7251 | WDRM v2 |  | 421 | 0.17437 |  | 913 | 0 | 0.0025801 | Tier 3 | Remote Grid Pilot
35320463 | PSPS - JAMESON 1105913400 | WDRM v2 | SH | PSPS | 419 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56004 | 0 | 0.56004 | 2023 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 |  | 419 | 0.17457 |  | 987 | 0 | 0.0022992 | Tier 2 | PSPS - 2023 ICUG
35221246 | DR~T2 REMV IDLE POLE 6 N/O #1 E/0 ENT | WDRM v2 | IF | 0 | 417 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Yorkville | Mendocino | 38.9374 | -123.309 | WDRM v2 |  | 417 | 0.17472 |  | 1638 | 0 | 0.0008197 | Tier 2 | Idle Facilities
35380377 | REMG 301 - CORNING 1102, NEWVILLE | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 2023 | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8303 | -122.5775 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380376 | PSPS - CORNING 1102 LR53184 PH 1.15 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799 | 2023 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380375 | REMG 797 - CORNING 1102 PH 1.14 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 2023 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8374 | -122.6306 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380374 | REMG 818 - CORNING 1102 PH 1.13 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299 | 2023 | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8507 | -122.6133 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380373 | PSPS - CORNING 1102 LR53184 PH 1.12 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79 | 2023 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380372 | PSPS - CORNING 1102 LR53184 PH 1.11 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 2023 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380371 | PSPS - CORNING 1102 LR53184 PH 1.10 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8299 | 0 | 2.8299 | 2023 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380370 | PSPS - CORNING 1102 LR53184 PH 1.9 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1799 | 0 | 3.1799 | 2023 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380369 | PSPS - CORNING 1102 LR53184 PH 1.8 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1299 | 0 | 2.1299 | 2023 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380368 | PSPS - CORNING 1102 LR53184 PH 1.7 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 2.2299 | 2023 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380365 | PSPS - CORNING 1102 LR53184 PH 1.5 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2023 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35334230 | REMG 817 - CORNING 1102 PH 1.4 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8348 | -122.6319 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35334229 | PSPS - CORNING 1102 LR53184 PH 1.3 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2023 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35311897 | PSPS - CORNING 1102 LR53184 PH 1.1 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.84 | 0 | 4.84 | 2023 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35276100 | REMG 300 - CORNING 1102, TURRI MAIN | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 3 | Remote Grid Pilot
35229051 | REMG 299 - CORNING 1102, TURRI ELLIS | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2023 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9003 | -122.5065 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 3 | Remote Grid Pilot
35285245 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.4 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3019 | -123.109 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012311 | 0.25398 | 0 | 0.26629 | 2023 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35285064 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79848 | 0 | 0.79848 | 2023 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35254077 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.1 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3171 | -123.1131 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35339293 | PSPS - JAMESON 1105 LR466348 PH 1.7 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338410 | PSPS - JAMESON 1105 LR466348 PH 2.3 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21 | 2023 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338409 | PSPS - JAMESON 1105 LR466348 PH 2.2 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338408 | PSPS - JAMESON 1105 LR466348 PH 1.6 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 2023 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338407 | PSPS - JAMESON 1105 LR466348 PH 1.5 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 2023 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 2023 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338405 | PSPS - JAMESON 1105 LR466348 PH 1.3 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338404 | PSPS - JAMESON 1105 LR466348 PH 1.2 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 2023 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35320461 | PSPS - JAMESON 1105 LR466348 PH 2.1 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56 | 2023 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35320460 | PSPS - JAMESON 1105 LR466348 PH 1.1 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 1.7799 | 2023 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35339289 | CWSP - JESSUP 1102 LR1550 PH 3.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.82 | 0 | 1.82 | 2023 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339288 | CWSP - JESSUP 1102 LR1550 PH 3.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 2023 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339287 | CWSP - JESSUP 1102 LR1550 PH 3.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339286 | CWSP - JESSUP 1102 LR1550 PH 2.5 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.54 | 0 | 2.54 | 2023 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339285 | CWSP - JESSUP 1102 LR1550 PH 2.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 2023 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339283 | CWSP - JESSUP 1102 LR1550 PH 2.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 2023 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339282 | CWSP - JESSUP 1102 LR1550 PH 2.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 2023 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337012 | CWSP - JESSUP 1102 LR1550 PH 1.5 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.443 | -122.3663 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337011 | CWSP - JESSUP 1102 LR1550 PH 1.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.89 | 0 | 2.89 | 2023 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337010 | CWSP - JESSUP 1102 LR1550 PH 1.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.82 | 0 | 3.82 | 2023 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35317887 | CWSP - JESSUP 1102 LR1550 PH 3.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 2023 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35317480 | CWSP - JESSUP 1102 LR1550 PH 2.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 2023 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35312548 | CWSP - JESSUP 1102 LR1550 PH 1.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35338403 | CWSP - PANORAMA 1101 LR885215 PH 1.2 | WDRM v2 | SH | PSPS | 380 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4063 | -122.2482 | WDRM v2 |  | 380 | 0.18705 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | 2023 ICUG
35320465 | CWSP - PANORAMA 1101 LR885215 PH 1.1 | WDRM v2 | SH | PSPS | 380 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4073 | -122.2444 | WDRM v2 |  | 380 | 0.18705 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | 2023 ICUG
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 2023 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 2023 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 2023 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.589 | 0 | 5.589 | 2023 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | WDRM v2 | SH | ECOP | 377 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8879 | -121.8676 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | ECOP - Top 20%
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | WDRM v2 | SH | ECOP | 377 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34 | 2023 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | ECOP - Top 20%
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | WDRM v2 | SH | PSPS | 355 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.28352 | 1.1968 | 0 | 1.4803 | 0 | 0 | 0 | 0 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.060417 | 0 | 0.060417 | 2023 | 0 | 0.060417 | 0 | 0.060417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 |  | 355 | 0.19378 |  | 2768 | 0 | 0.00020951 | Tier 2 | PSPS - Community Resiliency
35330249 | CWSP REDBUD 1101 708166 PH 1.7 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 4 | 0 | 4.25 | 2023 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330248 | CWSP REDBUD 1101 708166 PH 1.6 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0296 | -122.6802 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330247 | CWSP REDBUD 1101 708166 PH 1.5 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 2023 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330246 | CWSP REDBUD 1101 708166 PH 1.4 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 2023 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330245 | CWSP REDBUD 1101 708166 PH 1.3 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 2023 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330244 | CWSP REDBUD 1101 708166 PH 1.2 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 2023 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35329474 | CWSP REDBUD 1101 754544 PH 1.2 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0.11004 | 0 | 1.2701 | 2023 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 1 | 0.007396 | Tier 2 & 3 | CWSP - 2023 ICUG
35317398 | CWSP REDBUD 1101 754544 PH 1.1 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0581 | -122.693 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 1 | 0.007396 | Tier 2 & 3 | CWSP - 2023 ICUG
35312552 | CWSP REDBUD 1101 708166 PH 1.1 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0.77008 | 2023 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35208096 | 8/31-HOLD REMV IDLE FAC -LONGVALLEY *KS | WDRM v2 | IF | 0 | 345 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20663 | 0.20663 | 2023 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.069 | -122.6909 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 3 | Idle Facilities
35226625 | REMG 670 - ELK CREEK 1101, VALLEY VIEW | WDRM v2 | SH | FRRB | 340 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.6065 | -122.5419 | WDRM v2 |  | 340 | 0.1961 |  | 308 | 2 | 0.0090072 | Tier 2 | FRRB - REMG - 2021
35083879 | STS-POLE_IDLE_REMV - NEGRO CK RD/RD 152 | WDRM v2 | IF | 0 | 337 | V2 Top Risk | Idle Facilities | 2AF | ADER | Estimating | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Orange Cove | Tulare | 36.6365 | -119.1962 | WDRM v2 |  | 337 | 0.19768 |  | 2377 | 0 | 0.00035672 | Tier 2 | Idle Facilities
35349642 | CWSP - UPPER LAKE 1101 1276 PH 2.7 | WDRM v2 | SH | 0 | 335 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1699 | -123.006 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65303 | 0 | 0.65303 | 2023 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285250 | CWSP - UPPER LAKE 1101 1276 PH 2.5 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1756 | -123.0186 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35286270 | BOQUEST | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7583 | -121.6291 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35285249 | CWSP - UPPER LAKE 1101 1276 PH 2.4 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6288 | 0 | 2.6288 | 2023 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285248 | CWSP - UPPER LAKE 1101 1276 PH 2.3 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1679 | -123.0053 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285247 | CWSP - UPPER LAKE 1101 1276 PH 2.2 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1668 | -123.0058 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283349 | CWSP UPPER LAKE 1101 1276 PH 1.8 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.113 | -122.9818 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283348 | CWSP UPPER LAKE 1101 1276 PH 1.7 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1213 | -122.9896 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1253 | -122.9948 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6591 | 0 | 1.6591 | 2023 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283344 | CWSP UPPER LAKE 1101 1276 PH 1.4 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1474 | -122.9995 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283343 | CWSP UPPER LAKE 1101 1276 PH 1.3 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18447 | 0.72614 | 0 | 0.91061 | 2023 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35256083 | CWSP - UPPER LAKE 11011276 PH 2 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 1.847 | 0 | 1.8549 | 2023 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35256082 | CWSP - UPPER LAKE 11011276 PH 1 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1477 | 0 | 0 | 1.1477 | 2023 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1583 | -122.9898 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35278889 | CWSP - AUBERRY 1101 LR49122 PH1.2 | WDRM v2 | SH | CWSP | 330 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0894 | -119.4783 | WDRM v2 |  | 330 | 0.19907 |  | 734 | 0 | 0.0034999 | Tier 2 | CWSP 2022-2023
35254242 | CWSP - AUBERRY 1101 LR 49122 | WDRM v2 | SH | CWSP | 330 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0812 | -119.4864 | WDRM v2 |  | 330 | 0.19907 |  | 734 | 0 | 0.0034999 | Tier 2 | CWSP 2022-2023
35083893 | STS-COND_IDLE_REMV-5282 MINES RD | WDRM v2 | IF | 0 | 324 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067424 | 0.067424 | 2023 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6459 | -121.7137 | WDRM v2 |  | 324 | 0.20121 |  | 764 | 0 | 0.0032627 | Tier 2 | Idle Facilities
35134959 | VALLEY SPRINGS 1102 FEEDER OUTLET | WDRM v2 | Other | 0 | 322 | V2 Top Risk | Other | 06A | PEND | Permitting/Dependency | Y | Y | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 2024 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Valley Springs | Calaveras | 38.2131 | -120.7638 | WDRM v2 |  | 322 | 0.20132 |  | 1048 | 0 | 0.0020877 | Tier 2 | Other
35332364 | CWSP ELK CREEK 1101 LR2002 PH 2.6 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.085038 | 0 | 0.085038 | 2023 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332363 | CWSP ELK CREEK 1101 LR2002 PH 2.5 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 2023 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332362 | CWSP ELK CREEK 1101 LR2002 PH 2.4 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8299 | 0 | 3.8299 | 2023 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332361 | REMG 255 - ELK CREEK 1101, BRAVO | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4277 | -122.5067 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | 2023 ICUG
35332360 | CWSP ELK CREEK 1101 LR2002 PH 2.2 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.46 | 0 | 5.46 | 2023 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35330813 | REMG 256 - ELK CREEK 1101, MILANO | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5331 | -122.5377 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | 2023 ICUG
35330812 | PSPS ELK CREEK 1101 LR2002 PH 1.2 | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.49 | 0 | 2.49 | 2023 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | PSPS - 2023 ICUG
35316278 | CWSP ELK CREEK 1101 LR2002 PH 2.1 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35312543 | PSPS ELK CREEK 1101 LR2002 PH 1.1 | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.71 | 0 | 3.71 | 2023 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | PSPS - 2023 ICUG
35329473 | CWSP - REDBUD 1101 LR454 PH 1.3 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0654 | -122.6333 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35329472 | CWSP - REDBUD 1101 LR454 PH 1.2 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 2023 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35312551 | CWSP - REDBUD 1101 LR454 PH 1.1 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2049 | 0 | 3.2049 | 2023 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35349646 | CWSP - BUELLTON 1102 CB PH 1.4 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 2024 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.5925 | -120.1558 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35349645 | CWSP - BUELLTON 1102 CB PH 1.3 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 2024 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6005 | -120.1908 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35349643 | CWSP - BUELLTON 1102 CB PH 1.2 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 2024 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1576 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35320445 | CWSP - BUELLTON 1102 CB PH 1.1 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Buellton | Santa Barbara | 34.6236 | -120.185 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35259514 | CWSP - DESCHUTES 11041582 PH1.2 | WDRM v2 | SH | CWSP | 301 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5894 | -122.2244 | WDRM v2 |  | 301 | 0.21327 |  | 3101 | 0 | 0.0001094 | Tier 2 | CWSP 2022-2023
35279629 | CWSP PASO ROBLES 1103 LRN52 PH1.3 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 2024 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7141 | -120.8386 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35279628 | CWSP PASO ROBLES 1103 LRN52 PH1.2 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 2024 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.706 | -120.8189 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35254252 | +CWSP - PASO ROBLES 1103 LR N52 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.414 | 0 | 0 | 2.414 | 2023 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6886 | -120.7649 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35278090 | CWSP - AUBERRY 1101R2839 PH2.2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0201 | -119.4294 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35277935 | CWSP AUBERRY 1101 R2839 PH1.4 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089394 | 0 | 0.089394 | 2023 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP
35277934 | CWSP AUBERRY 1101 R2839 PH1.3 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0314 | -119.4428 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35277933 | CWSP AUBERRY 1101 R2839 PH1.2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0335 | -119.4426 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35254241 | CWSP - AUBERRY 1101 LR R2839 PH2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35254240 | CWSP - AUBERRY 1101 LR R2839 PH1 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35332217 | PSPS COTTONWOOD 1102 LR9026 PH 3.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0.05303 | 3.083 | 2023 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332216 | PSPS COTTONWOOD 1102 LR9026 PH 2.3 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332215 | PSPS COTTONWOOD 1102 LR9026 PH 2.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26 | 2023 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332214 | PSPS COTTONWOOD 1102 LR9026 PH 1.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.04 | 0 | 4.04 | 2023 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35316569 | PSPS - COTTONWOOD 11029026 PH3 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0.032008 | 4.842 | 2023 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35316567 | PSPS - COTTONWOOD 11029026 PH2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4201 | 0 | 3.4201 | 2023 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35312540 | PSPS - COTTONWOOD 11029026 PH1 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8799 | 0 | 4.8799 | 2023 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35349651 | CWSP - BUELLTON 1102 Y50 PH 1.6 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 2024 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6136 | -120.1365 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349650 | CWSP - BUELLTON 1102 Y50 PH 1.5 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 2024 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349649 | CWSP - BUELLTON 1102 Y50 PH 1.4 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 2024 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349648 | CWSP - BUELLTON 1102 Y50 PH 1.3 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 2024 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349647 | CWSP - BUELLTON 1102 Y50 PH 1.2 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 2024 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6129 | -120.1624 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35320446 | CWSP - BUELLTON 1102 Y50 PH 1.1 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.613 | -120.1749 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35329008 | PSPS CLARK ROAD 1102 CB PH 1.2 | WDRM v2 | SH | PSPS | 268 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31307 | 0 | 0.31307 | 2023 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0 | 0.00031072 | Tier 2 | PSPS
35299629 | PSPS CLARK ROAD 1102 CB PH 1.1 | WDRM v2 | SH | PSPS | 268 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.654 | -121.6323 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0 | 0.00031072 | Tier 2 | PSPS
35331302 | CWSP ANDERSON 1103 LR226050 PH 1.5 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4766 | -122.2926 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35331301 | CWSP ANDERSON 1103 LR226050 PH 1.4 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4791 | -122.2929 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35330816 | CWSP ANDERSON 1103 LR226050 PH 1.3 UPDAT | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.5058 | -122.2574 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35330815 | CWSP ANDERSON 1103 LR226050 PH 1.2 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2023 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | CWSP - 2023 ICUG
35311895 | CWSP ANDERSON 1103 LR226050 PH 1.1 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7799 | 0 | 2.7799 | 2023 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | CWSP - 2023 ICUG
35279626 | +X22: CWSP -PASO ROBLES 1103 LR 2731 PH1 | WDRM v2 | SH | CWSP | 260 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16364 | 0 | 0 | 0.16364 | 2023 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.73 | WDRM v2 |  | 260 | 0.2296 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35254254 | +X22: CWSP - PASO ROBLES 1103 LR 2731 | WDRM v2 | SH | CWSP | 260 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 | 1.3972 | 2023 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.7299 | WDRM v2 |  | 260 | 0.2296 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35151005 | 8/31 REMV IDLE 4 LOCS OLD WITTER SP*RA | WDRM v2 | IF | 0 | 259 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28636 | 0.28636 | 2023 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.185 | -122.9886 | WDRM v2 |  | 259 | 0.23008 |  | 327 | 1 | 0.0086415 | Tier 2 | Idle Facilities
35279631 | CWSP - PASO ROBLES 1103 LRN58 PH1.2 | WDRM v2 | SH | CWSP | 257 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.064 | 0 | 0 | 3.064 | 0 | 0 | 0 | 0 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417 | 2023 | 1.6417 | 0 | 0 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6385 | -120.7157 | WDRM v2 |  | 257 | 0.23099 |  | 771 | 0 | 0.0032279 | Tier 2 | CWSP 2022-2023
35254248 | CWSP - PASO ROBLES 1103 LR N58 | WDRM v2 | SH | CWSP | 257 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 2024 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | El Paso De Robles | San Luis Obispo | 35.6286 | -120.6955 | WDRM v2 |  | 257 | 0.23099 |  | 771 | 0 | 0.0032279 | Tier 2 | CWSP 2022-2023
35225318 | +STS-COND_IDLE_REMV-CAT CANYON RD | WDRM v2 | IF | 0 | 256 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094697 | 0.094697 | 2023 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | Santa Barbara | 34.8111 | -120.2748 | WDRM v2 |  | 256 | 0.23169 |  | 2229 | 0 | 0.00042166 | Tier 2 | Idle Facilities
35337306 | CWSP STANISLAUS 1702 CB PH 1.5 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0094697 | 2.2667 | 0 | 2.2761 | 2023 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284366 | REMG 512 - STANISLAUS 1702, FOREBAY | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871 | 2023 | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1446 | -120.3574 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284365 | CWSP STANISLAUS 1702 CB PH 1.3 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 2.7547 | 0 | 2.7797 | 2023 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0047348 | 0.91742 | 0 | 0.92216 | 2023 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35250577 | CWSP - STANISLAUS 1702 CB | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5777 | 0 | 0 | 3.5777 | 2023 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1377 | -120.3701 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35349244 | CWSP - LINCOLN 1104 LR685276 PH 1.5 | WDRM v2 | SH | 0 | 230 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2023 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | CWSP 2022-2023
35339292 | CWSP - LINCOLN 1104 LR685276 PH 1.4 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 2023 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9969 | -121.2718 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35339291 | CWSP - LINCOLN 1104 LR685276 PH 1.3 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 2024 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9964 | -121.2681 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35339290 | CWSP - LINCOLN 1104 LR685276 PH 1.2 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 2024 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35320450 | CWSP - LINCOLN 1104 LR685276 PH 1.1 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 2023 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | CWSP - 2023 ICUG
35211757 | DR-COND_IDLE_REMV-13716 LOS VERJELES | WDRM v2 | IF | 0 | 225 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15057 | 0.15057 | 2023 | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Marysville | Yuba | 39.3562 | -121.3774 | WDRM v2 |  | 225 | 0.24429 |  | 2534 | 0 | 0.00029638 | Tier 2 | Idle Facilities
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | WDRM v2 | SH | PSPS | 218 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.076705 | 0.53561 | 0 | 0.61231 | 0 | 0 | 0 | 0 | 0.062879 | 0.40985 | 0 | 0.47273 | 0.013826 | 0.12576 | 0 | 0.13958 | 2024 | 0 | 0 | 0 | 0 | 0.013826 | 0.12576 | 0 | 0.13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WDRM v2 |  | 218 | 0.24845 |  | 2461 | 0 | 0.00032066 | Tier 2 | PSPS - Community Resiliency
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | WDRM v2 | SH | ECOP | 215 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3843 | 0 | 1.3843 | 2023 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 |  | 215 | 0.25006 |  | 1267 | 0 | 0.0014262 | Tier 3 | ECOP - Top 20%
35150641 | T2-COND_IDLE_REMV-16853 DAM RD *KS | WDRM v2 | IF | 0 | 212 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 2023 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9248 | -122.5972 | WDRM v2 |  | 212 | 0.25222 |  | 847 | 0 | 0.0028915 | Tier 2 | Idle Facilities
35332219 | PSPS ELK CREEK 1101 LR93504 PH 1.2 | WDRM v2 | SH | PSPS | 206 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.593 | -122.5412 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0 | 0.0012407 | Tier 2 | PSPS - 2023 ICUG
35312544 | CWSP ELK CREEK 1101 LR93504 PH 1.1 | WDRM v2 | SH | PSPS | 206 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 2023 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0 | 0.0012407 | Tier 2 | PSPS - 2023 ICUG
35262347 | STS-POLE_IDLE_REMV - A/F 45771 BUTTERNUT | WDRM v2 | IF | 0 | 195 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.069318 | 0.069318 | 2023 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6995 | -119.1257 | WDRM v2 |  | 195 | 0.26095 |  | 1266 | 0 | 0.0014269 | Tier 2 | Idle Facilities
35215883 | STS-TRAN_CORR_REPL - 45886 CHUCKWAGON RD | WDRM v2 | IF | 0 | 195 | V2 Top Risk | Idle Facilities | 2AA | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10303 | 0.10303 | 2023 | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6914 | -119.1303 | WDRM v2 |  | 195 | 0.26095 |  | 1266 | 0 | 0.0014269 | Tier 2 | Idle Facilities
35335290 | PSPS - VACAVILLE 1111 LR13652 PH 1.2 | WDRM v2 | SH | PSPS | 190 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61 | 2023 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0 | 0.00074783 | Tier 2 | PSPS - 2023 ICUG
35320441 | PSPS - VACAVILLE 1111 LR13652 PH 1.1 | WDRM v2 | SH | PSPS | 190 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 2023 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0 | 0.00074783 | Tier 2 | PSPS - 2023 ICUG
35337164 | CWSP LINCOLN 1104 51756 & 275986 PH 1.3 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 2024 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9708 | -121.2498 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | 2023 ICUG
35337163 | CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 2023 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | CWSP - 2023 ICUG
35320449 | CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2375 | 1.5472 | 4.7847 | 2023 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | CWSP - 2023 ICUG
35208097 | 8/31-REMV IDLE 19824 MORGAN HOLD FOR 10J | WDRM v2 | IF | 0 | 181 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017045 | 0.017045 | 2023 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8926 | -122.5433 | WDRM v2 |  | 181 | 0.26975 |  | 270 | 1 | 0.010079 | Tier 2 | Idle Facilities
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 | WDRM v2 | SH | CWSP | 171 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0 | 0.15814 | 2023 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 |  | 171 | 0.27308 |  | 712 | 2 | 0.0036194 | Tier 2 | CWSP 2022-2023
35240173 | CWSP - PUTAH CREEK 11028352 PH 1.1 | WDRM v2 | SH | CWSP | 171 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.567 | 0 | 0 | 1.567 | 2023 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 |  | 171 | 0.27308 |  | 712 | 2 | 0.0036194 | Tier 2 | CWSP 2022-2023
35310704 | CWSP MOUNTAIN QUARRIES 2101 1350 PH1.12 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 2024 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305312 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.11 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 2024 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.9674 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305311 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.10 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 2024 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8965 | -120.9455 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305310 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.9 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 2024 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.899 | -120.9485 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305309 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.8 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 2024 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9633 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305308 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8944 | -120.9647 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305307 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.6 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 2024 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9648 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305306 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.5 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 2024 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.972 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305305 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.4 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 2024 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8981 | -120.9738 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305304 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.3 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 2024 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8978 | -120.9866 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.065 | 0 | 1.065 | 2023 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293670 | CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54394 | 0 | 0.54394 | 2023 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293669 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.9 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 2024 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8852 | -120.96 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293668 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.8 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 2024 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8894 | -120.9589 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293667 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.7 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 2024 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8974 | -120.9338 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293666 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.6 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 2024 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9012 | -120.9346 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43655 | 0 | 0.43655 | 2023 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293664 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.4 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2024 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8981 | -120.914 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68788 | 0 | 0.68788 | 2023 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH2. | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 2024 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8932 | -120.9965 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35254070 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH1 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 2024 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8931 | -120.9966 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35278892 | CWSP - AUBERRY 1101R2578 PH5.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 2024 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9662 | -119.3834 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278891 | CWSP - AUBERRY 1101R2578 PH5.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9752 | -119.3882 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278890 | CWSP - AUBERRY 1101R2578 PH5.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 2024 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9737 | -119.3888 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278097 | CWSP - AUBERRY 1101R2578 PH4.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.286 | 0 | 0.20095 | 1.4869 | 0 | 0 | 0 | 0 | 0.66345 | 0 | 0 | 0.66345 | 0.62254 | 0 | 0.20095 | 0.82348 | 2023 | 0.62254 | 0 | 0.20095 | 0.82348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.98 | -119.4029 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278093 | CWSP - AUBERRY 1101R2578 PH3.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.41496 | 0 | 0.41496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278092 | CWSP - AUBERRY 1101R2578 PH3.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 2024 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.978 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254346 | PBS-5552 CLARK RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6087 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35254345 | PBS-NUTMEG WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7874 | -121.601 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254344 | PBS-360 OAK SPRING RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.12027 | 0 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12027 | 0 | 0.12027 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.12027 | 0 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7414 | -121.6432 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254275 | PBS-BURKE LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7704 | -121.6012 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254274 | PBS-NOTTONGHAM PARK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | UNSC | Ready for Construction | N | Y | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088447 | 0 | 0.088447 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7598 | -121.6341 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35278091 | CWSP - AUBERRY 1101R2578 PH3.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 2024 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9796 | -119.3694 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277938 | CWSP AUBERRY 1101 R2578 PH2.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42822 | 0.31742 | 0.74564 | 2023 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277937 | CWSP AUBERRY 1101 R2578 PH2.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 2024 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0129 | -119.3939 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277936 | CWSP AUBERRY 1101 R2578 PH2.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5307 | 0 | 0 | 3.5307 | 2023 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0143 | -119.4031 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277924 | CWSP AUBERRY 1101 R2578 PH1.5 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0.10909 | 2023 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277923 | CWSP AUBERRY 1101 R2578 PH1.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1777 | 0 | 0 | 3.1777 | 2023 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9916 | -119.4068 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277922 | CWSP AUBERRY 1101 R2578 PH1.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 2024 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.005 | -119.4055 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277921 | CWSP AUBERRY 1101 R2578 PH1.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 2024 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0111 | -119.4175 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254247 | CWSP - AUBERRY 1101 LR R2578 PH5 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 2024 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9581 | 0 | 0 | 2.9581 | 2023 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254244 | CWSP - AUBERRY 1101 LR R2578 PH2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4244 | 0 | 0 | 2.4244 | 2023 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254243 | CWSP - AUBERRY 1101 LR R2578 PH1 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 2024 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35226852 | X22: CWSP-SHINGLE SPRINGS 2109-LR 9372-P | WDRM v2 | SH | PRE | 159 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 | 2.4932 | 2023 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 3 | 0.011098 | Tier 3 | Top 20% MAVF CPZ
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | WDRM v2 | SH | PRE | 159 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 2023 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 3 | 0.011098 | Tier 3 | Top 20% MAVF CPZ
35254651 | CWSP - VOLTA 110153118 PH 1.4 | WDRM v2 | SH | CWSP | 157 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.4038 | 0 | 0 | 2.4038 | 0 | 0 | 0 | 0 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045 | 2023 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 2 | 0.0099281 | Tier 2 | CWSP 2022-2023
35254650 | CWSP - VOLTA 110153118 PH 1.3 | WDRM v2 | SH | CWSP | 157 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.30436 | 0 | 0.30436 | 0.0056818 | 0 | 0 | 0.0056818 | 2023 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 2 | 0.0099281 | Tier 2 | CWSP 2022-2023
35264190 | CWSP - SANTA YNEZ 1104 Y66 PH 2.3 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3576 | 0 | 0 | 2.3576 | 2023 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6451 | -119.9634 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264189 | CWSP - SANTA YNEZ 1104Y66 PH 2.2 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6055 | 0 | 0 | 2.6055 | 2023 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6377 | -119.9713 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264188 | CWSP - SANTA YNEZ 1104Y66 PH 1.5 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1292 | 0 | 0 | 1.1292 | 2023 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6065 | -119.9508 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264187 | CWSP - SANTA YNEZ 1104Y66 PH 1.4 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6919 | 0 | 0 | 1.6919 | 2023 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6112 | -119.9786 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264185 | CWSP - SANTA YNEZ 1104Y66 PH 1.2 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4926 | 0 | 0 | 1.4926 | 2023 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6142 | -119.9878 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2.1 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.589 | 0 | 0 | 2.589 | 2023 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1.1 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1089 | 0 | 0 | 2.1089 | 2023 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35325590 | CWSP FLINT 1101 750 PH 1.3 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 2023 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35325589 | CWSP FLINT 1101 750 PH 1.2 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 2023 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35312545 | CWSP - FLINT 1101750 PH 1.1 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2023 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 | WDRM v2 | SH | CWSP | 144 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.218 | 0 | 0 | 2.218 | 2023 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 |  | 144 | 0.28655 |  | 2787 | 0 | 0.00020217 | Tier 2 | CWSP 2022-2023
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 | WDRM v2 | SH | CWSP | 144 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4638 | 0 | 0 | 3.4638 | 0 | 0 | 0 | 0 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572 | 2023 | 0.06572 | 0 | 0 | 0.06572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 |  | 144 | 0.28655 |  | 2787 | 0 | 0.00020217 | Tier 2 | CWSP 2022-2023
35331305 | CWSP ANDERSON 1103 LR1600 PH2.4 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 2023 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | CWSP - 2023 ICUG
35331304 | CWSP ANDERSON 1103 LR1600 PH2.3 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4829 | -122.2057 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35331303 | CWSP ANDERSON 1103 LR1600 PH2.2 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4832 | -122.214 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35311894 | CWSP ANDERSON 1103 LR1600 PH2.1 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4768 | -122.2276 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35298571 | CWSP ANDERSON 1103 LR1600 PH1 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 2023 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | CWSP 2022-2023
35279627 | X22: CWSP - PASO ROBLES 1103 LRN50 PH 1. | WDRM v2 | SH | CWSP | 138 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 2024 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7253 | -120.8701 | WDRM v2 |  | 138 | 0.30039 |  | 742 | 0 | 0.0034276 | Tier 2 | CWSP 2022-2023
35249877 | REMG 755 - COARSEGOLD 2104, MELVIN | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 1.0299 | 2023 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.7142 | 0 | 0 | 3.7142 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693 | 2023 | 2.7693 | 0 | 0 | 2.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35249875 | X22: CWSP - COARSEGOLD 21046210 PH 1.2 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6394 | 0 | 0 | 2.6394 | 2023 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35240165 | X22: CWSP - COARSEGOLD 21046210 PH 1.1 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8498 | 0 | 0 | 3.8498 | 2023 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35332218 | PSPS COTTONWOOD 1102 LR544790 PH 1.2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26 | 2023 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35332213 | PSPS COTTONWOOD 1102 LR544790 PH 2.2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3701 | 0 | 2.3701 | 2023 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35316561 | PSPS - COTTONWOOD 1102544790 PH 2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 2023 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35311899 | PSPS - COTTONWOOD 1102544790 PH 1 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 3.44 | 2023 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35404729 | PSPS - VACAVILLE 1108 LR38316 PH 1.5 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4295 | -122.0489 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35404728 | PSPS - VACAVILLE 1108 LR38316 PH 1.4 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4201 | -122.0443 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35404727 | PSPS - VACAVILLE 1108 LR38316 PH 1.3 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4267 | -122.0475 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334755 | PSPS - VACAVILLE 1108 LR38316 PH 2.3 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.47 | 0 | 1.47 | 2023 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334754 | PSPS - VACAVILLE 1108 LR38316 PH 2.2 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | 0 | 3.93 | 2023 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334753 | PSPS - VACAVILLE 1108 LR38316 PH 1.2 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 2023 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35246598 | DOG TOWN & MAGALIA DAM | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8149 | -121.5802 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246595 | SKYWAY PH5 (Wagstaff to Pentz) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 5.9 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9 | 0 | 5.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.9 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7842 | -121.5991 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246594 | ROSEHILL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.7 | 0 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 0 | 3.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.7 | 0 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7382 | -121.6208 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246592 | AMERICAN (elec only) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 6.2 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 6.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7367 | -121.6125 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246591 | OAK KNOLL (Caltrans) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 4.3 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 4.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7485 | -121.6086 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246590 | ALEXANDER CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7696 | -121.579 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246589 | KLING CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.764 | -121.5986 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35320339 | PSPS - VACAVILLE 1108 LR38316 PH 2.1 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35246316 | WAYLAND (elec only) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7265 | -121.6374 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246309 | SKYWAY PH4 (Bille to Wagstaff) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7752 | -121.6093 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35246308 | HOSPITAL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7572 | -121.5722 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35320336 | PSPS - VACAVILLE 1108 LR38316 PH 1.1 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4365 | -122.0527 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334234 | CWSP - BELL 1108 LR2202 PH 1.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1088 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35334233 | CWSP - BELL 1108 LR2202 PH 1.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 2024 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1075 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35334232 | CWSP - BELL 1108 LR2202 PH 1.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9855 | -121.1087 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35244220 | HONEY RUN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7717 | -121.6118 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35334231 | CWSP - BELL 1108 LR2202 PH 1.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9856 | -121.1102 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333510 | CWSP - BELL 1108 LR2202 PH 3.6 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 2024 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0081 | -121.1482 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333509 | CWSP - BELL 1108 LR2202 PH 3.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 2024 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0145 | -121.1236 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333508 | CWSP - BELL 1108 LR2202 PH 3.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 2024 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0083 | -121.1247 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333507 | CWSP - BELL 1108 LR2202 PH 3.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 2024 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0003 | -121.1276 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35244027 | SKYWAY PH6 (Old Magalia) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 5.5 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 5.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7285 | -121.6363 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35333506 | CWSP - BELL 1108 LR2202 PH 3.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 2024 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9995 | -121.122 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333505 | CWSP - BELL 1108 LR2202 PH 2.7 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 2023 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.143 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333504 | CWSP - BELL 1108 LR2202 PH 2.6 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2023 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333503 | CWSP - BELL 1108 LR2202 PH 2.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0.3 | 0 | 1.74 | 2023 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333502 | CWSP - BELL 1108 LR2202 PH 2.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 | 1.74 | 2023 | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9891 | -121.1353 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333501 | CWSP - BELL 1108 LR2202 PH 2.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9851 | -121.1296 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333500 | CWSP - BELL 1108 LR2202 PH 2.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 2023 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1268 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35314416 | CWSP - BELL 1108 LR2202 PH 3.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 2024 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9981 | -121.1168 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35314415 | CWSP - BELL 1108 LR2202 PH 2.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 2024 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35311896 | CWSP - BELL 1108 LR2202 PH 1.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1091 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35149246 | STS-COND_IDLE_REMV-16251 HWY 101*JM | WDRM v2 | IF | 0 | 110 | V2 Top Risk | Idle Facilities | 2AF | MAPP | In-Construction | Y | N | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18277 | 0.18277 | 2023 | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hopland | Mendocino | 38.9503 | -123.0881 | WDRM v2 |  | 110 | 0.32431 |  | 519 | 2 | 0.0051934 | Tier 2 | Idle Facilities
35264182 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.3 | WDRM v2 | SH | CWSP | 108 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6348 | 0 | 0 | 2.6348 | 0 | 0 | 0 | 0 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765 | 2023 | 0.17765 | 0 | 0 | 0.17765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6278 | -120.0209 | WDRM v2 |  | 108 | 0.32463 |  | 2888 | 0 | 0.0001675 | Tier 2 | CWSP 2022-2023
35264181 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.2 | WDRM v2 | SH | CWSP | 108 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.7506 | 0 | 0 | 2.7506 | 0 | 0 | 0 | 0 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585 | 2023 | 1.8585 | 0 | 0 | 1.8585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6365 | -120.0218 | WDRM v2 |  | 108 | 0.32463 |  | 2888 | 0 | 0.0001675 | Tier 2 | CWSP 2022-2023
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | WDRM v2 | SH | CWSP | 100 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25871 | 0 | 0.25871 | 2023 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0 | 0.00022756 | Tier 2 | CWSP 2022-2023
35243447 | CWSP - DESCHUTES 11041370 PH 2.1 | WDRM v2 | SH | CWSP | 100 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.573 | -122.2386 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0 | 0.00022756 | Tier 2 | CWSP 2022-2023
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 | WDRM v2 | SH | CWSP | 99 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.5917 | -122.2743 | WDRM v2 |  | 99 | 0.34786 |  | 2481 | 0 | 0.00031475 | Tier 2 | CWSP 2022-2023
35243448 | CWSP - DESCHUTES 110449024 PH 2.1 | WDRM v2 | SH | CWSP | 99 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5929 | -122.2396 | WDRM v2 |  | 99 | 0.34786 |  | 2481 | 0 | 0.00031475 | Tier 2 | CWSP 2022-2023
35254940 | REMG 761 - VOLTA 1101, BATTLE CREEK | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64697 | 0.64697 | 2023 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35254738 | REMG 760 - VOLTA 1101, WILDCAT | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.018 | 1.018 | 2023 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35254658 | CWSP - VOLTA 11011568 PH 1.4 | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447 | 2023 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 & 3 | CWSP 2022-2023
35243444 | REMG 757 - VOLTA 1101, PRESLEIGH | WDRM v2 | SH | REMG | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 | WDRM v2 | SH | CWSP | 78 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0985 | 0 | 0 | 2.0985 | 2023 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2635 | -119.7123 | WDRM v2 |  | 78 | 0.37306 |  | 1728 | 0 | 0.00074257 | Tier 2 | CWSP 2022-2023
35254259 | CWSP - VOLTA 1101CB PH 1.3 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22803 | 0.275 | 0 | 0.50303 | 2023 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35254258 | X22: CWSP - VOLTA 1101CB PH 1.2 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3525 | 0 | 0 | 1.3525 | 2023 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35240166 | CWSP - VOLTA 1101CB PH 1.1 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.46326 | 0.015341 | 0 | 0.4786 | 0 | 0 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 2023 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35293846 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.9 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85985 | 0 | 0.85985 | 2023 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293845 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 0 | 1.3799 | 2023 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3031 | -123.057 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293844 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 | 0.95985 | 2023 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2984 | -123.0591 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293843 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.31 | 0 | 0 | 1.31 | 2023 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2953 | -123.0616 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293841 | CWSP - POTTER VALLEY PH 11051904 PH1.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 2024 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2927 | -123.085 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293775 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0 | 0.82992 | 2023 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3018 | -123.0942 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293774 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 2024 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3095 | -123.0931 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293770 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 2024 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3146 | -123.0942 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35290808 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 2023 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290807 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 2024 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2457 | -123.1271 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290510 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1887 | -123.0323 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290509 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 2024 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1918 | -123.0344 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008 | 2023 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290507 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 2024 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1963 | -123.0435 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290506 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 2024 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2105 | -123.0641 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436 | 2023 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290503 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 2024 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2248 | -123.0882 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290502 | REMG 436 - POTTER VALLEY 1105, CCA-SCP | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.228 | -123.0887 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290501 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 2024 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2328 | -123.1053 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290500 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 | 1.0098 | 2023 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2537 | -123.1188 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290299 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 2023 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2594 | -123.1172 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290298 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 2023 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2619 | -123.1148 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290297 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 2023 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2696 | -123.1053 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290296 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 2023 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2715 | -123.097 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290295 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 2023 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2738 | -123.0944 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 2024 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 2023 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254074 | CWSP POTTER VALLEY PH 1105 LR1904 PH2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56989 | 0 | 0 | 0.56989 | 2023 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254073 | CWSP POTTER VALLEY PH 1105 LR1904 PH1 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0676 | 0 | 0 | 1.0676 | 2023 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35290514 | CWSP - HIGHLANDS 1102 LR623120 PH1.5 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9794 | -122.6125 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290513 | CWSP - HIGHLANDS 1102 LR623120 PH1.4 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9769 | -122.6124 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290512 | CWSP - HIGHLANDS 1102 LR623120 PH1.3 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9612 | -122.6089 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290511 | CWSP - HIGHLANDS 1102 LR623120 PH1.2 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.979 | -122.6124 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35254072 | CWSP - HIGHLANDS 1102 LR 623120 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9544 | -122.6079 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35278888 | +X22: CWSP - PASO ROBLES 1103 LRN54 PH2. | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 2024 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6848 | -120.73 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278887 | +X22: CWSP -PASO ROBLES 1103 LRN54 PH2.6 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4799 | 0 | 0 | 1.4799 | 2023 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6819 | -120.738 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278884 | +CWSP - PASO ROBLES 1103 LRN54 PH2.3 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7701 | 0 | 0 | 2.7701 | 2023 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6807 | -120.7554 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278883 | +CWSP - PASO ROBLES 1103 LRN54 PH2.2 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 0 | 1.81 | 2023 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6795 | -120.745 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278882 | +CWSP - PASO ROBLES 1103 LRN54 PH1.4 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6322 | 0 | 0 | 2.6322 | 0 | 0 | 0 | 0 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701 | 2023 | 0.90701 | 0 | 0 | 0.90701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6747 | -120.7423 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278881 | +CWSP - PASO ROBLES 1103 LRN54 PH1.3 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6799 | 0 | 0 | 2.6799 | 2023 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6635 | -120.7259 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1.1 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6725 | 0 | 0 | 2.6725 | 0 | 0 | 0 | 0 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267 | 2023 | 0.1267 | 0 | 0 | 0.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6543 | -120.7258 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35301114 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 2024 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8694 | -120.979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35301113 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 2024 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8632 | -120.9814 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35301112 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067235 | 0.52576 | 0 | 0.59299 | 2023 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35300934 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 2024 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8708 | -120.9825 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35300933 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59489 | 0 | 0.59489 | 2023 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293847 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.8 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 2024 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8704 | -121.0217 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293677 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.7 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 2024 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8918 | -120.9988 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293676 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 2024 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8745 | -121.0198 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293675 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 2024 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8795 | -121.0164 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293674 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 2024 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8882 | -121.0144 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293673 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 2024 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8939 | -121.0149 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293672 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 2024 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9075 | -121.0168 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293509 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 2024 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8608 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35227481 | HILLPARK LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 2023 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7392 | -121.5724 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227417 | CHAPARRAL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7323 | -121.6513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35227415 | JARVIS LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 5.2 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | 5.2 | 2023 | 0 | 5.2 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7389 | -121.6402 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227413 | STARLIGHT CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 5.6 | 0 | 5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 5.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7423 | -121.6423 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35227412 | PENTZ PH1 (Arrowhead to Fickett) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.769 | -121.5786 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227411 | COPELAND RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7595 | -121.6024 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227409 | SIERRA PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7501 | -121.6242 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227408 | PEARSON RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2023 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7524 | -121.6126 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227406 | COLLEGE HILL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ADER | Estimating | N | Y | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 4.5 | 2023 | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7523 | -121.6185 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227405 | SHADOWBROOK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0.3 | 2023 | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7578 | -121.6071 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227404 | ACADEMY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2023 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7538 | -121.6172 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227403 | MAPLE PARK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7616 | -121.6079 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227402 | STINSON LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2023 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7703 | -121.6071 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227401 | CAMELLIA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7628 | -121.6233 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227400 | OAK WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7712 | -121.6031 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2023 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293507 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 2024 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8774 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293506 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 2024 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8803 | -121.0037 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293505 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 2024 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8782 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254069 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 2024 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8777 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254068 | CWSP - MOUNTAIN QUARRIES 2101 CB PH2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 2024 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 0.43996 | 0 | 0.47992 | 2023 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | WDRM v2 | SH | PSPS | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84924 | 0 | 0.84924 | 2023 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | PSPS - Community Resiliency
35320443 | CWSP - JAMESON 1102865502 | WDRM v2 | SH | CWSP | 67 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.236 | -122.1528 | WDRM v2 |  | 67 | 0.38957 |  | 1581 | 0 | 0.00088788 | Tier 2 | 2023 ICUG
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 1.81 | 2023 | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35334750 | PSPS - VACAVILLE 1108 LR8762 PH 1.2 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 2023 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35320334 | PSPS - VACAVILLE 1108 LR8762 PH 2.0 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2023 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35320333 | PSPS - VACAVILLE 1108 LR8762 PH 1.1 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 2023 | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35277931 | CWSP - AUBERRY 1101CB PH2.4 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0503 | -119.4639 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277930 | CWSP - AUBERRY 1101CB PH2.3 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 | 0.33 | 2023 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0528 | -119.4629 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277929 | CWSP - AUBERRY 1101CB PH2.2 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5536 | 0 | 0 | 2.5536 | 2023 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0578 | -119.4739 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277926 | AUBERRY 1101CB PH1.3 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4381 | 0 | 0 | 3.4381 | 0 | 0 | 0 | 0 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843 | 2023 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0749 | -119.4852 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277925 | CWSP - AUBERRY 1101CB PH1.2 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 2023 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35254079 | X22: CWSP - AUBERRY 1101 CB PH2.1 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 2.4 | 2023 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0677 | -119.4958 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35250738 | CWSP - COARSEGOLD 21045310 PH 2.3 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4856 | 0 | 0 | 3.4856 | 2023 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35250737 | CWSP - COARSEGOLD 21045310 PH 2.2 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8564 | 0 | 0 | 2.8564 | 2023 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35249874 | CWSP - COARSEGOLD 21045310 PH 3.3 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35249873 | CWSP - COARSEGOLD 21045310 PH 3.2 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35240163 | CWSP - COARSEGOLD 21045310 PH 3.1 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 2023 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35311135 | CWSP - POTTER VALLEY PH 1104 95878 PH1.9 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311134 | CWSP - POTTER VALLEY PH 1104 95878 PH1.8 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311133 | CWSP - POTTER VALLEY PH 1104 95878 PH1.7 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311132 | CWSP - POTTER VALLEY PH 1104 95878 PH1.6 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311131 | CWSP - POTTER VALLEY PH 1104 95878 PH1.5 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310715 | CWSP - POTTER VALLEY PH 1104 95878 PH1.4 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310714 | CWSP - POTTER VALLEY PH 1104 95878 PH1.3 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310713 | CWSP - POTTER VALLEY PH 1104 95878 PH1.2 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35250579 | CWSP - POTTER VALLEY PH 1104 95878 PH1.1 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35283340 | CWSP HARTLEY 1101 LR698 PH 1.6 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 2023 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.105 | -122.9581 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283199 | CWSP HARTLEY 1101 LR698 PH 1.5 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2701 | 0 | 0 | 1.2701 | 2023 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0813 | -122.9625 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283198 | CWSP HARTLEY 1101 LR698 PH 1.4 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27803 | 0 | 0.27803 | 2023 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283197 | CWSP HARTLEY 1101 LR698 PH 1.3 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4381 | 0 | 0 | 2.4381 | 2023 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0946 | -122.9632 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283196 | CWSP HARTLEY 1101 LR698 PH 1.2 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3345 | 0 | 0 | 1.3345 | 2023 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.095 | -122.9656 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35250576 | CWSP - HARTLEY 1101 LR 698 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.217 | 0 | 0 | 1.217 | 2023 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0803 | -122.9513 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35274597 | CWSP MARIPOSA 2101 CB PH 1.2 | WDRM v2 | SH | CWSP | 57 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63295 | 0 | 0 | 0.63295 | 2023 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5054 | -120.0067 | WDRM v2 |  | 57 | 0.39837 |  | 82 | 2 | 0.019246 | Tier 2 | CWSP 2022-2023
35250573 | CWSP - MARIPOSA 2101 CB | WDRM v2 | SH | CWSP | 57 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7591 | 0 | 0 | 1.7591 | 2023 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5046 | -120.0081 | WDRM v2 |  | 57 | 0.39837 |  | 82 | 2 | 0.019246 | Tier 2 | CWSP 2022-2023
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 2023 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279122 | CWSP - STANISLAUS 1701 CB PH1.5 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90909 | 0 | 0 | 0.90909 | 2023 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1379 | -120.3707 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279121 | CWSP - STANISLAUS 1701 CB PH1.4 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77235 | 0 | 0 | 0.77235 | 2023 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1797 | -120.3786 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.004 | 0 | 1.004 | 2023 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3449 | 0 | 1.3449 | 2023 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35250578 | CWSP - STANISLAUS 1701 CB PH1.1 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4174 | 0 | 0 | 2.4174 | 2023 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1376 | -120.3702 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35219591 | CWSP - OLETA 1101754718 PH1.1 | WDRM v2 | SH | CWSP | 54 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 1.25 | 2023 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | Amador | 38.4692 | -120.8536 | WDRM v2 |  | 54 | 0.40712 |  | 2197 | 0 | 0.00043538 | Tier 2 | Top 250 Miles
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0.14489 | 2023 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7034 | 0 | 0 | 1.7034 | 2023 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4055 | 0 | 0 | 2.4055 | 2023 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35280362 | CWSP - MARIPOSA 2102440236 PH1.4 | WDRM v2 | SH | CWSP | 50 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047348 | 0.13258 | 0 | 0.17992 | 2023 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0 | 0.0069412 | Tier 2 & 3 | Top 250 Miles
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | WDRM v2 | SH | CWSP | 50 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 0.88182 | 0 | 0.27973 | 1.1616 | 0 | 0 | 0 | 0 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364 | 2023 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9482 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0 | 0.0069412 | Tier 2 & 3 | Top 250 Miles
35316537 | CWSP - OREGON TRAIL 110335002 PH1.7 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.624 | -122.3049 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 miles
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.2771 | 0 | 0 | 1.2771 | 0 | 0 | 0 | 0 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432 | 2023 | 0.049432 | 0 | 0 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 2024 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8206 | 0 | 0 | 2.8206 | 2023 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.71345 | 0 | 0 | 0.71345 | 0 | 0 | 0 | 0 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489 | 2023 | 0.14489 | 0 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234396 | X22: CWSP - OREGON TRAIL 110335002 PH5.5 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5604 | 0 | 0 | 1.5604 | 2023 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.71 | 0 | 0 | 2.71 | 2023 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 0 | 1.79 | 2023 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 0 | 0 | 2.42 | 2023 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 2023 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5468 | 0 | 0 | 1.5468 | 2023 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233951 | X22: CWSP - OREGON TRAIL 110335002 PH1.6 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6214 | 0 | 0 | 1.6214 | 2023 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233949 | X22: CWSP - OREGON TRAIL 110335002 PH1.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.7706 | 0 | 0 | 1.7706 | 0 | 0 | 0 | 0 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411 | 2023 | 1.6411 | 0 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 | 2.19 | 2023 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 | 2.31 | 2023 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6299 | -122.2445 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | WDRM v2 | SH | CWSP | 43 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636 | 2023 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.362 | -123.1283 | WDRM v2 |  | 43 | 0.44262 |  | 1733 | 0 | 0.00073797 | Tier 2 | Top 250 Miles
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87216 | 0.87216 | 2023 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53996 | 0 | 0.53996 | 2023 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7282 | 0 | 3.7282 | 2023 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | WDRM v2 | SH | CWSP | 37 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 3.6491 | 0 | 0 | 3.6491 | 0 | 0 | 0 | 0 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758 | 2023 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | WDRM v2 |  | 37 | 0.46772 |  | 1554 | 0 | 0.00091401 | Tier 2 | Top 250 Miles
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | WDRM v2 | SH | CWSP | 29 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.4214 | 0 | 0.4214 | 0 | 0 | 0 | 0 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288 | 2023 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0 | 0.0002242 | Tier 2 | Top 250 Miles
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | WDRM v2 | SH | CWSP | 29 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.92822 | 0 | 0.86723 | 1.7955 | 0.87803 | 0 | 0 | 0.87803 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.86723 | 0.91742 | 2023 | 0.050189 | 0 | 0.86723 | 0.91742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4631 | -121.5149 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0 | 0.0002242 | Tier 2 | Top 250 Miles
35231631 | OCGC-CWSP-HIGHLANDS 1102628 PH 1.13 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | FICL | In-Construction | Y | N | 0.44867 | 0 | 0 | 0.44867 | 0 | 0 | 0 | 0 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428 | 2023 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2165 | 0 | 0 | 1.2165 | 2023 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231628 | REMG 729 - HIGHLANDS 1102, WATERTROUGH | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 | 0.39867 | 2023 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231626 | OCGC_X22: CWSP-HIGHLANDS 1102628 PH 1.8 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | MAPP | In-Construction | Y | N | 0.78295 | 0 | 0.64962 | 1.4326 | 0 | 0 | 0 | 0 | 0.78295 | 0 | 0.60417 | 1.3871 | 0 | 0 | 0.045455 | 0.045455 | 2023 | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2023 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231624 | REMG 728 - HIGHLANDS 1102, BUCKSKIN WAY | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231623 | REMG 205 - HIGHLANDS 1102, OASIS | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35189987 | WHATEVER LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 2023 | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7404 | -121.5939 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35189984 | PALOMA AVE | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2023 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7471 | -121.6129 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189983 | FOSTER RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6266 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35189853 | HAPPY WOODS | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7681 | -121.5891 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189792 | CYPRESS LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.9 | 0 | 3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9 | 0 | 3.9 | 2023 | 0 | 3.9 | 0 | 3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.784 | -121.5864 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189791 | WARREN RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2023 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5873 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35175548 | HIGH SCHOOL MAXWELL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2023 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7619 | -121.6125 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35175547 | PENTZ & WAGSTAFF | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 4.8 | 0 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 0 | 4.8 | 2023 | 0 | 4.8 | 0 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5797 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35231622 | REMG 706 - HIGHLANDS 1102, INDIAN CREEK | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943 | 2023 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782 | 2023 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7275 | 0 | 0 | 2.7275 | 2023 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | WDRM v2 | SH | CWSP | 21 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2598 | 0 | 0 | 3.2598 | 2023 | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 2 | 0.00471 | Tier 2 | Top 250 Miles
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | WDRM v2 | SH | CWSP | 21 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0 | 0 | 0 | 0 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.028409 | 0.028409 | 0.056818 | 2023 | 0 | 0.028409 | 0.028409 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 2 | 0.00471 | Tier 2 | Top 250 Miles
35299137 | CWSP HARTLEY 1101 LR789752 PH 1.6 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57292 | 0 | 0 | 0.57292 | 2023 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.067 | -122.9672 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299136 | CWSP HARTLEY 1101 LR789752 PH 1.5 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67197 | 0 | 0 | 0.67197 | 2023 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0716 | -122.9638 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299135 | CWSP HARTLEY 1101 LR789752 PH 1.4 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92102 | 0 | 0 | 0.92102 | 2023 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0722 | -122.9571 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299134 | CWSP HARTLEY 1101 LR789752 PH 1.3 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40303 | 0 | 0 | 0.40303 | 2023 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0704 | -122.9571 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299133 | CWSP HARTLEY 1101 LR789752 PH 1.2 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28144 | 0 | 0 | 0.28144 | 2023 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0729 | -122.9569 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35250575 | CWSP HARTLEY 1101 LR789752 PH 1.1 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2428 | 0 | 0 | 0.2428 | 2023 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0636 | -122.9526 | WDRM v2 |  | 19 | 0.64187 |  | 2963 | 0 | 0.00014245 | Tier 2 | CWSP 2022-2023
35144480 | SHAW CIR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2023 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8116 | -121.5956 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | WDRM v2 | SH | CWSP | 18 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 2023 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 |  | 18 | 0.65331 |  | 448 | 2 | 0.0062529 | Tier 2 | Top 50 Miles
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0 | 0 | 3.45 | 2023 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35127550 | MYRTLE WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F CEMA | ESTS | Estimating | N | Y | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7858 | -121.6004 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35127360 | PRINCETON WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7461 | -121.6435 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35126752 | APPLE | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ADER | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7333 | -121.6353 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35126750 | JERRYS WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7741 | -121.5895 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35126645 | CRESTVIEW | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7612 | -121.6342 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 2023 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.57727 | 0 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939 | 2023 | 0.43939 | 0 | 0 | 0.43939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35118676 | REDBUD DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2023 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7551 | -121.6455 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35118674 | GLENDALE DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.6017 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35118673 | S PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.1 | 0 | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 3.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8005 | -121.6047 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35117455 | HERMAN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ADER | Estimating | N | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7813 | -121.594 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.3212 | 0 | 1.3212 | 0 | 0 | 0 | 0 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985 | 2023 | 0 | 0.95985 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0494 | 0 | 2.0494 | 2023 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35112126 | PARAGALIA | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.78 | -121.6092 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9095 | 0 | 1.9095 | 2023 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2.1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2729 | 0 | 2.2729 | 2023 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | ADER | Estimating | Y | N | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 2023 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9107 | -121.3275 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | WDRM v2 | SH | CWSP | 9 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.93 | -122.7428 | WDRM v2 |  | 9 | 0.87629 |  | 735 | 0 | 0.0034918 | Tier 3 | Top 50 Miles
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73068 | 0 | 0 | 0.73068 | 2023 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 2024 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 2024 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | WDRM v2 | SH | CWSP | 7 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8061 | 0 | 4.8061 | 2023 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 2 | 0.022602 | Tier 3 | Top 50 Miles
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | WDRM v2 | SH | CWSP | 7 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85511 | 0 | 0.85511 | 2023 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 2 | 0.022602 | Tier 3 | Top 50 Miles
35058839 | STS-POLE_BROK_REPL - 17 STARWOOD DR REDW | 0 | Other | 0 | FALSE | No Risk Vintage | Other | 07D | DOCC | In-Construction | Y | N | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1625 | 0 | 0 | 0.1625 | 2023 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3801 | -122.2699 | [6 empty] | 0 |  |  | 0
35342302 | CWSP - LINCOLN 1104 LR997576 PH 1.2 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0278 | -121.2938 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35334404 | FRRB - PT MORETTI 1101 P1S2 310SWAN | WDRM v2 | FRRB | FRRB | 1393 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2023 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0671 | -122.2231 | WDRM v2 |  | 1393 | 0.033758 |  | 2485 | 0 | 0.00031335 | Tier 2 | FRRB
35332878 | CWSP - LINCOLN 1104 LR997576 PH 1.6 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0128 | -121.263 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332876 | CWSP - LINCOLN 1104 LR997576 PH 1.5 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0181 | -121.2717 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332874 | CWSP - LINCOLN 1104 LR997576 PH 1.4 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0224 | -121.2874 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332872 | CWSP - LINCOLN 1104 LR997576 PH 1.3 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 2024 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0337 | -121.3086 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35320453 | CWSP - LINCOLN 1104 LR997576 PH 1.1 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 2023 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0371 | -121.3366 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG

## Pivot
Top 20% Risk/Not Top Risk | Progam | Project Type 2 | Sum of UG - 2023 Forecast | Sum of UG - 2024 Forecast | Sum of UG - 2025 Forecast | Sum of UG - 2026 Forecast
No Risk Vintage |  | Butte Rebuild | 71.4 | 98.7981 | 0 | 0
| Community Rebuild | Greenville Rebuild | 6.3009 | 0 | 0 | 0
| Other |  | 0 | 0 | 0 | 0
No Risk Vintage Total |  |  | 77.7009 | 98.7981 | 0 | 0
V2 Not Top Risk | FRRB |  | 45.2025 | 5.7807 | 1.76 | 1.1201
| IF |  | 0 | 0 | 0 | 0
| Other |  | 0 | 5.2831 | 0.015341 | 0.37879
| SH | 0 | 0 | 0 | 0 | 0
|  | 2023 ICUG | 0 | 0 | 0 | 0
|  | CWSP - 2023 ICUG | 0 | 0 | 2 | 0
|  | CWSP 2022-2023 | 0.773 | 1.1939 | 11.76 | 0
|  | ECOP | 0 | 0 | 0 | 0
|  | Pre | 0.052841 | 0 | 0 | 0
|  | PSPS | 16.84 | 2.9066 | 15.9613 | 0
|  | PSPS - 2023 ICUG | 27.5437 | 10.2781 | 0 | 0
|  | PSPS - Community Resiliency | 2.1408 | 5.0136 | 0 | 0
|  | PSPS - Scoped | 0.53447 | 0 | 0 | 0
|  | PSS Approved | 2.5902 | 0.57576 | 0 | 0
|  | REMG 2022-2023 | 0 | 0 | 0 | 0
|  | Remote Grid Pilot | 0 | 0 | 0 | 0
V2 Not Top Risk Total |  |  | 95.6774 | 31.0319 | 31.4967 | 1.4989
V2 Top Risk | FRRB |  | 15.3314 | 0 | 0 | 0
| IF |  | 0 | 0 | 0 | 0
| Other |  | 0 | 1.7032 | 0 | 0
| SH | 2023 ICUG | 0 | 0.50644 | 0 | 0
|  | CWSP | 0.089394 | 0 | 0 | 0
|  | CWSP - 2023 ICUG | 90.2153 | 28.1413 | 4.92 | 0
|  | CWSP 2022-2023 | 33.4753 | 1.658 | 0.035985 | 0.41496
|  | ECOP - Top 20% | 22.8638 | 4.0089 | 0 | 0
|  | FRRB - REMG - 2021 | 0 | 0 | 0 | 0
|  | PSPS | 9.8208 | 0.89091 | 0 | 0
|  | PSPS - 2023 ICUG | 123.179 | 41.3831 | 28.393 | 18.2596
|  | PSPS - Community Resiliency | 0.90966 | 0.12576 | 0 | 0
|  | REMG 2022-2023 | 0 | 0 | 0 | 0
|  | Remote Grid Pilot | 0 | 0 | 0 | 0
|  | Top 20% MAVF CPZ | 4.0593 | 0 | 0 | 0
|  | Top 250 Miles | 10.0083 | 16.8009 | 0 | 0
|  | Top 50 Miles | 11.3004 | 1.3201 | 0 | 0
V2 Top Risk Total |  |  | 321.2528 | 96.5386 | 33.349 | 18.6746
V3 Not Top Risk | FRRB |  | 0 | 0 | 0 | 0
| SH | 0 | 0 | 0 | 0 | 0
|  | CWSP 2024 | 0 | 0 | 4.29 | 0.33996
V3 Not Top Risk Total |  |  | 0 | 0 | 4.29 | 0.33996
V3 Top Risk |  | V3 Tranche 1 | 0 | 15.1375 | 53.248 | 76.185
| FRRB |  | 16.9748 | 2.05 | 1.2197 | 0.84905
| SH | 0 | 0 | 0 | 0 | 0
|  | CWSP 2024 | 22.7349 | 297.3763 | 520.3354 | 768.0183
|  | PSPS | 0 | 11.06 | 0 | 0
|  | PSPS - 2023 ICUG | 0 | 0.52917 | 0.55814 | 0
|  | V3 Tranche 1 | 0 | 35.725 | 38.487 | 15.3807
V3 Top Risk Total |  |  | 39.7097 | 361.878 | 613.8482 | 860.433
Grand Total |  |  | 534.3408 | 588.2466 | 682.9839 | 880.9464