## Table 8-3 modified
SCE WMP Table 8-3 (modified)
Note that values for SH-1 and SH-2 reflect corrections submitted to OEIS on April 6 and 26, 2023.
Initiative Activity | Tracking ID | 2023 Target & Unit | x% Risk | % in SRA/HCA 2023 | 2024 Target & Unit | x% Risk | % in SRA/HCA 2024 | 2025 Target & Unit | x% Risk | % in SRA/HCA 2025 | Method of Verification | "Top 20" value (see Word doc for N/A explanations and additional detail on these values)
|  |  | Impact 2023 |  |  | Impact 2024 |  |  | Impact 2025
|  |  | (Unit /HFRA) |  |  | (Unit /HFRA) |  |  | (Unit /HFRA)
Covered Conductor | SH-1 | Install 1,100 circuit miles of covered conductor in SCE’s HFRA | 51% / 20% | 91% | Install 1,050 circuit miles of covered conductor in SCE’s HFRA | 53%/6% | 91% | Install 700 circuit miles of covered conductor in SCE’s HFRA | 51%/4% | 80% | Listing of completed Work Orders | 22.2%
|  | SCE will strive to install up to as many as 1,200 circuit miles of covered conductor in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to install up to as many as 1,200 circuit miles of covered conductor in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to install up to as many as 850 circuit miles of covered conductor in SCE’s HFRA, subject to resource constraints and other execution risks
Undergrounding Overhead Conductor | SH-2 | Convert 11 circuit miles of overhead to underground in SCE's HFRA | 98%/.22% | 100% | Convert 16 circuit miles of overhead to underground in SCE's HFRA | 98%/.64% | 100% | Convert 48 circuit miles of overhead to underground in SCE's HFRA | 98%/.9% | 100% | Listing of completed Work Orders | 90.1%
[5 empty] | SCE will strive to convert up to 20 miles of overhead to underground in SCE's HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to convert up to 60 miles of overhead to underground in SCE's HFRA, subject to resource constraints and other execution risks
Branch Line Protection strategy | SH-4 | Install or replace fusing at 500 fuse locations that serve HFRA circuitry | 7%/.31% | 97% | N/A – Sunsetting in 2023, further fuse replacements will be completed via opportunity work | N/A | N/A | N/A – Sunsetting in 2023, further fuse replacements will be completed via opportunity work | N/A | N/A | Listing of completed Work Orders | N/A
SCE will strive to install or replace fusing at up to 570 locations that serve HFRA circuitry, subject to resource constraints and other execution risks
Remote Controlled Automatic Reclosers Settings Update | SH-5 | SCE will install 6 RAR/RCS sectionalizing devices subject to 2022 PSPS analysis and subject to change | 29%/.04% | 7% | SCE will install 5 RAR/RCS sectionalizing devices subject to 2023 PSPS analysis and subject to change | 34%/.24% | 67% | SCE will install 5 RAR/RCS sectionalizing devices subject to 2024 PSPS analysis and subject to change | 33%/.19% | 95% | Listing of completed Work Orders | N/A
|  | SCE will strive to install up to 17 RAR/RCS sectionalizing devices subject to 2022 PSPS analysis, resource constraints and other execution risks |  |  | SCE will strive to install 17 RAR/RCS sectionalizing devices subject to 2023 PSPS analysis, resource constraints and other execution risks |  |  | SCE will strive to install 17 RAR/RCS sectionalizing devices subject to 2024 PSPS analysis, resource constraints and other execution risks
Circuit Breaker Relay Hardware for Fast Curve | SH-6 | Replace/upgrade 75 CB relay units with fast curve settings in SCE’s HFRA | 32%/.15% | 95% | Replace/ upgrade remaining 10 CB relay units with fast curve settings in SCE’s HFRA, subject to resource constraints and other execution risks | 32%/.004% | 92% | N/A - Activity Sunsetting in 2024 | N/A | N/A | Listing of completed Work Orders | N/A
SCE will strive to replace/upgrade up to 88 relay units with fast curve settings in SCE’s HFRA, subject to resource constraints and other execution risks
Transmission Open Phase Detection | SH-8 | Install TOPD at 5 locations that serve HFRA circuitry with both alarm and trip functionality | 1%/.01% | 100% | Retrofit TOPD at 5 locations with trip capabilities where alarm mode was previously deployed and that serve HFRA circuitry | 1%/.01% | 100% | Target to be determined based on further evaluation | N/A | N/A | Listing of completed Work Orders | N/A
%
Tree Attachments Remediation | SH-10 | Remediate 400 tree attachments in SCE’s HFRA | 21%/.02% | 42% | Remediate 500 tree attachments in SCE’s HFRA | 21%/.03% | 42% | Remediate the balance of tree attachments in SCE’s HFRA, subject to change based on scope completed in previous years | 22%/.03% | 52% | Listing of completed Work Orders | N/A
|  | SCE will strive to complete up to 500 tree attachment remediations in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to complete up to 600 tree attachment remediations in SCE’s HFRA, subject to resource constraints and other execution risks
Long Span Initiative (LSI) | SH-14 | Remediate 400 spans in SCE’s HFRA | 5%/.01% | 92% | Remediate 1,000 spans in SCE’s HFRA | 5%/.04% | 82% | Remediate 1,000 spans in SCE’s HFRA | 4%/.02% | 98% | Listing of completed Work Orders | 61.52%
|  | SCE will strive to remediate up to 500 spans in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to remediate up to 1,200 spans in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to remediate up to 1,200 spans in SCE’s HFRA, subject to resource constraints and other execution risks |  | SRA%: 38%
HCA%: 60%
Vertical Switches | SH-15 | Install 9 vertical switches in SCE’s HFRA | 44%/.01% | 67% | N/A – Sunsetting in 2023 | N/A | N/A | N/A – Sunsetting in 2023 | N/A | N/A | Listing of completed Work Orders | N/A
SCE will strive to install 11 vertical switches in SCE’s HFRA, subject to resource constraints and other execution risks
Vibration Damper Retrofit | SH-16 | Retrofit vibration dampers on 300 structures where covered conductor is already installed in SCE’s HFRA | 19%/.04% | 100% | Retrofit vibration dampers on 500 structures where covered conductor is already installed in SCE’s HFRA | 11%/.01% | 99% | Retrofit vibration dampers on 600 structures where covered conductor is already installed in SCE’s HFRA | 20%/.09% | 100% | Listing of completed Work Orders | 24.65%
|  | SCE will strive to retrofit vibration dampers on up to 400 structures where covered conductor is already installed in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to retrofit vibration dampers on up to 600 structures where covered conductor is already installed in SCE’s HFRA, subject to resource constraints and other execution risks |  |  | SCE will strive to retrofit vibration dampers on up to 800 structures where covered conductor is already installed in SCE’s HFRA, subject to resource constraints and other execution risks
Rapid Earth Fault Current Limiters (REFCL) (Ground Fault Neutralizer (GFN)) | SH-17 | SCE will complete construction of GFN at two substations (Acton and Phelan) | 47%/3.6% | 94% | SCE will complete construction of GFN at one substation (Banducci) | 45%/.54% | 88% | SCE will complete construction of GFN at four substations | 49%/1.8% | 89% | Listing of completed Work Orders | 91.7%
Rapid Earth Fault Current Limiters (REFCL) - Grounding Conversion | SH-18 | SCE will complete grounding conversion at one location, subject to land availability. | 45%/.06% | 91% | SCE will target four locations for grounding conversion, subject to land availability | N/A scope not determined yet | N/A scope not determined yet | SCE will target four locations for grounding conversion, subject to land availability | N/A scope not determined yet | N/A scope not determined yet | Listing of completed Work Orders | N/A
[5 empty] | SCE will strive to target up to 6 locations for grounding conversion, subject to land availability |  |  | SCE will strive to target up to 6 locations for grounding conversion, subject to land availability