## SH Workplan_2023-26_Conf
[13 empty] | 500.8748 | 2426.6715 | 139.8732 | 3067.4195 | 2.7182 | 0 | 0 | 2.7182 | 44.9333 | 10.6458 | 0.8839 | 56.4631 | 184.1431 | 457.2099 | 55.721 | 697.074 | 127.3717 | 489.4485 | 57.8243 | 674.6445 | 143.1446 | 645.3459 | 23.454 | 811.9444 | 0.59405 | 832.9964 | 1.99 | 835.5804
Order | Order Description | MAT Code | Program | Circuit ID | Circuit Name | Applicable Risk Model | Circuit Protection Zone (V2) | Risk Rank (V2) | Circuit Protection Zone (CPZ) (V3) | Risk Rank (V3) | Actual or Planned Start Date | Expected End Date | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2022 Complete | UG - Pre-2022 Complete | Removal - Pre-2022 Complete | Pre-2022 Total Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles | OH - 2025 Forecast | UG - 2025 Forecast | Removal - 2025 Forecast | 2025 Total Miles | OH - 2026 Forecast | UG - 2026 Forecast | Removal - 2026 Forecast | 2026 Total Miles
35398090 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v3 |  | 995 |  | 2135 | 2023-03-20 08:00 | 2023-04-24 08:00 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35379282 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2252 |  | 1042 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35376306 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | Not Yet Available | Not Yet Available | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35376304 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | Not Yet Available | Not Yet Available | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35376303 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | Not Yet Available | Not Yet Available | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374866 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-28 08:00 | 2023-09-11 17:00 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374865 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-28 08:00 | 2023-09-12 17:00 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374864 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-28 08:00 | 2023-12-27 17:00 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374862 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-08-04 08:00 | 2023-11-28 17:00 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374687 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-09-01 08:00 | 2023-10-16 17:00 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374686 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-27 08:00 | 2023-11-21 17:00 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374685 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-08-21 08:00 | 2023-12-06 17:00 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374684 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-27 08:00 | 2023-11-13 17:00 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374683 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-03 08:00 | 2023-10-02 17:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374682 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | Not Yet Available | Not Yet Available | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374559 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 655 |  | 504 | 2023-07-03 08:00 | 2023-11-03 17:00 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35085847 |  | 08W | Base SH | 83692105 | ROB ROY 2105 | WDRM v2 |  | 3283 |  | 2739 | 2024-05-09 08:00 | 2024-05-24 17:00 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35015704 |  | 08W | Base SH | 83692105 | ROB ROY 2105 | WDRM v2 |  | 3283 |  | 2739 | 2024-05-27 08:00 | 2024-06-10 08:00 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329471 |  | 08W | Base SH | 43361104 | HIGHLANDS 1104 | WDRM v2 |  | 3243 |  | 1561 | 2023-08-22 08:00 | 2024-04-17 08:00 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396304 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 2157 |  | 429 | 2023-11-21 08:00 | 2024-04-12 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373585 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 2157 |  | 429 | Not Yet Available | Not Yet Available | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396074 |  | 08W | Fire Rebuild | 102211103 | BUCKS CREEK 1103 | WDRM v3 |  | 1658 |  | 404 | Not Yet Available | Not Yet Available | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367518 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2174 |  | 398 | 2024-02-28 08:00 | 2024-08-06 08:00 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35355173 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v3 |  | 2320 |  | 394 | 2024-04-02 08:00 | 2024-07-26 08:00 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404753 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-12-11 08:00 | 2024-05-14 17:00 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35385890 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-09-18 08:00 | 2024-01-23 17:00 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35385889 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-10-16 08:00 | 2024-05-15 17:00 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35385888 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-07-26 08:00 | 2024-01-04 17:00 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373705 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-11-08 08:00 | 2024-06-13 17:00 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367520 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | 2023-07-11 08:00 | 2023-12-19 17:00 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397454 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-09-14 08:00 | 2024-01-10 08:00 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397453 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2024-04-09 08:00 | 2024-08-08 08:00 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397452 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2024-04-09 08:00 | 2024-08-08 08:00 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35326790 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 |  | 2980 |  | 2071 | 2023-08-14 08:00 | 2023-12-18 17:00 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396860 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-09-11 08:00 | 2024-01-09 08:00 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396779 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-09-26 08:00 | 2024-01-10 08:00 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396778 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-10-03 08:00 | 2024-01-05 08:00 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396776 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-08-16 08:00 | 2024-04-11 08:00 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373594 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-07-13 08:00 | 2023-11-15 08:00 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373593 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373592 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2024-04-04 08:00 | 2024-09-03 08:00 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373590 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2024-05-08 08:00 | 2024-09-06 08:00 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373589 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-09-13 08:00 | 2024-01-08 08:00 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367462 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | 2023-09-26 08:00 | 2024-04-16 08:00 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396572 |  | 08W | Base SH | 083392110 | SWIFT 2110 | WDRM v3 |  | 1769 |  | 276 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374457 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | 2024-01-09 08:00 | 2024-08-30 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374456 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | 2024-01-23 08:00 | 2025-01-16 08:00 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35350039 |  | 08W | Fire Rebuild | 103751102 | BIG BEND 1102 | WDRM v3 |  | 1288 |  | 267 | Not Yet Available | Not Yet Available | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396567 |  | 08W | Base SH | 103381102 | FRENCH GULCH 1102 | WDRM v3 |  | 2518 |  | 262 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397961 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-02-28 08:00 | 2024-07-19 08:00 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397960 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-02-28 08:00 | 2024-07-15 08:00 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396875 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-10 08:00 | 2024-08-27 08:00 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396874 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-10 08:00 | 2024-09-11 08:00 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396871 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-10 08:00 | 2024-08-06 08:00 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396870 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-10 08:00 | 2024-08-21 08:00 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396869 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-10 08:00 | 2024-09-03 08:00 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373703 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-02-05 08:00 | 2024-06-27 08:00 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373636 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2024-05-02 08:00 | 2024-12-13 08:00 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373581 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373536 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367415 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35418371 |  | 3UG | Targeted UG | 162821701 | STANISLAUS 1701 | WDRM v3 |  | 2142 |  | 231 | Not Yet Available | Not Yet Available | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312546 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 |  | 2980 |  | 2071 | 2023-09-05 08:00 | 2024-01-10 16:00 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396073 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v3 |  | 1480 |  | 212 | 2023-01-06 08:00 | 2023-03-27 08:00 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373051 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v3 |  | 1480 |  | 212 | 2023-03-03 08:00 | 2023-04-21 08:00 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35402642 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 |  | 204 | Not Yet Available | Not Yet Available | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35402641 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 |  | 204 | 2023-08-04 08:00 | Not Yet Available | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373635 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 |  | 204 | 2024-06-10 08:00 | 2024-11-15 08:00 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367510 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 |  | 204 | 2023-08-02 08:00 | 2024-02-07 08:00 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35078178 |  | 2AF | Idle Facilities | 82841101 | BIG BASIN 1101 | WDRM v2 |  | 2968 |  | 1102 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221765 |  | 2AF | Idle Facilities | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 2810 |  | 98 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31383326 |  | 06E | Other | 43321103 | RINCON 1103 | WDRM v2 |  | 2799 |  | 7022 | 2021-06-15 | 2023-04-29 | 0.41856 | 0 | 0 | 0.41856 | 0 | 0 | 0 | 0 | 0.29867 | 0 | 0 | 0.29867 | 0.11989 | 0 | 0 | 0.11989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74001486 |  | 30A | Other | 12501105 | El Cerrito G 1105 | WDRM v2 |  | 2792 |  | 2633 | Not Yet Available | Not Yet Available | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277146 |  | 2AF | Idle Facilities | 162831702 | SPRING GAP 1702 | WDRM v2 |  | 2788 |  | 922 | Not Yet Available | Not Yet Available | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35222235 |  | 08W | Base SH | 254061102 | DUNLAP 1102 | WDRM v2 |  | 2738 |  | 482 | 2023-09-05 08:00 | Not Yet Available | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094513 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 2712 |  | 1583 | 2022-03-14 | Not Yet Available | 1.7748 | 0.053977 | 0 | 1.8288 | 0 | 0 | 0 | 0 | 1.483 | 0.053977 | 0 | 1.5369 | 0.29186 | 0 | 0 | 0.29186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342333 |  | 08W | Fire Rebuild | 82841101 | BIG BASIN 1101 | WDRM v2 |  | 2579 |  | 1120 | 2023-05-22 | 2023-07-27 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237593 |  | 95F | Fire Rebuild | 82841101 | BIG BASIN 1101 | WDRM v2 |  | 2579 |  | 1120 | Not Yet Available | Not Yet Available | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35375180 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | N/A |  | 193 | 2023-12-21 08:00 | 2024-06-19 08:00 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35376556 |  | 3UG | Targeted UG | 152301102 | BONNIE NOOK 1102 | WDRM v3 |  | 2087 |  | 192 | 2023-10-13 08:00 | 2024-03-14 08:00 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35368118 |  | 08W | Fire Rebuild | 103751102 | BIG BEND 1102 | WDRM v3 |  | 865 |  | 187 | 2023-03-31 08:00 | 2023-04-07 08:00 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35403556 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | 2023-08-15 08:00 | Not Yet Available | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35403555 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | 2023-10-10 08:00 | 2024-01-08 08:00 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35399834 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | 2023-09-26 08:00 | 2024-02-21 08:00 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373526 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | 2023-10-12 08:00 | 2024-03-25 08:00 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367476 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | 2023-11-02 08:00 | 2024-03-01 08:00 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35382858 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1509 |  | 178 | Not Yet Available | Not Yet Available | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35376305 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 1809 |  | 137 | 2023-08-04 08:00 | 2023-09-27 17:00 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374863 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 1809 |  | 137 | 2023-09-01 08:00 | 2023-10-17 17:00 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35375511 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | 2024-01-18 08:00 | 2024-06-27 08:00 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35375510 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | 2024-01-18 08:00 | 2024-09-18 08:00 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404716 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1102 | WDRM v3 |  | 1271 |  | 131 | 2023-12-15 08:00 | 2024-08-09 08:00 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404715 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1102 | WDRM v3 |  | 1271 |  | 131 | 2023-12-15 08:00 | 2024-08-09 08:00 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397963 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | 2023-10-04 08:00 | 2024-02-27 08:00 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35397962 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | 2023-10-04 08:00 | 2024-01-31 08:00 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35379383 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | 2023-09-29 08:00 | 2024-06-05 08:00 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35375721 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | Not Yet Available | Not Yet Available | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35374681 |  | 08W | Fire Rebuild | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | 2023-05-31 08:00 | 2023-09-18 17:00 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373528 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 |  | 1284 |  | 124 | 2024-04-12 08:00 | 2024-11-06 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373527 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 |  | 1284 |  | 124 | 2023-12-20 08:00 | 2024-07-25 08:00 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396570 |  | 08W | Base SH | 163781701 | PEORIA 1701 | WDRM v3 |  | 780 |  | 122 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396911 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2024-03-19 08:00 | 2024-07-11 08:00 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396910 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2024-03-19 08:00 | 2024-07-03 08:00 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396909 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2023-09-26 08:00 | 2024-05-23 08:00 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396908 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2024-02-29 08:00 | 2024-07-03 08:00 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373533 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2023-08-25 08:00 | 2023-12-19 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367478 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 2270 |  | 114 | 2024-08-07 08:00 | 2025-01-09 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404726 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | 2023-09-26 08:00 | 2024-02-16 08:00 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404352 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | 2023-09-21 08:00 | 2024-01-16 08:00 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35404351 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | 2023-09-21 08:00 | Not Yet Available | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373704 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | 2024-07-03 08:00 | 2024-12-12 08:00 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35395931 |  | 08W | Base SH | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 |  | 91 | 2023-08-15 08:00 | 2023-12-22 08:00 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35418356 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2351 |  | 90 | Not Yet Available | Not Yet Available | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396569 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v3 |  | 1135 |  | 83 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35396568 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v3 |  | 1135 |  | 83 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373620 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2250 |  | 81 | 2023-12-22 08:00 | 2024-08-26 08:00 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367468 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2250 |  | 81 | 2023-12-22 08:00 | 2024-08-26 08:00 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35409211 |  | 3UG | Targeted UG | 152431101 | SHADY GLEN 1101 | WDRM v3 |  | 2201 |  | 71 | Not Yet Available | Not Yet Available | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35391472 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | 2023-11-30 08:00 | 2024-04-09 08:00 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35391471 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | 2023-11-30 08:00 | 2024-04-10 08:00 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35373532 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 1505 |  | 63 | 2024-06-26 08:00 | 2025-01-23 08:00 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35367414 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 1505 |  | 63 | 2024-02-09 08:00 | 2024-10-07 08:00 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TBD |  | 3UG | Targeted UG | 0 | 0 | WDRM v3 |  | 178 |  | 32 | Not Yet Available | Not Yet Available | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975
35409213 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 |  | 1422 |  | 30 | 2023-12-12 08:00 | 2024-04-19 08:00 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35235158 |  | 95F | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 |  | 2539 |  | 903 | Not Yet Available | Not Yet Available | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211671 |  | 2AF | Idle Facilities | 152491102 | WEIMAR 1102 | WDRM v2 |  | 2536 |  | 1432 | Not Yet Available | Not Yet Available | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35244167 |  | 2AF | Idle Facilities | 152241101 | HALSEY 1101 | WDRM v2 |  | 2500 |  | 1766 | Not Yet Available | Not Yet Available | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225253 |  | 2AF | Idle Facilities | 83622104 | CAMP EVERS 2104 | WDRM v2 |  | 2474 |  | 1225 | Not Yet Available | Not Yet Available | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113950 |  | 08W | Base SH | 82841101 | BIG BASIN 1101 | WDRM v2 |  | 2456 |  | 1113 | 2022-02-05 | 2023-03-21 | 3.4441 | 0 | 0 | 3.4441 | 0 | 0 | 0 | 0 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35318072 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1101 | WDRM v2 |  | 2435 |  | 1105 | 2023-03-20 | 2023-04-10 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225011 |  | 2AF | Idle Facilities | 183071101 | PERRY 1101 | WDRM v2 |  | 2433 |  | 2127 | Not Yet Available | Not Yet Available | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224941 |  | 2AF | Idle Facilities | 183011102 | MORRO BAY 1102 | WDRM v2 |  | 2399 |  | 2247 | 2023-06-12 | 2023-06-12 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225467 |  | 2AF | Idle Facilities | 83692104 | ROB ROY 2104 | WDRM v2 |  | 2387 |  | 1464 | Not Yet Available | Not Yet Available | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342460 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2359 |  | 1314 | 2023-08-25 08:00 | 2023-11-10 08:00 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35372461 |  | 3UG | Targeted UG | 161380201 | TIGER CREEK 0201 | WDRM v3 |  | 1744 |  | 8 | 2024-04-02 08:00 | 2024-09-05 17:00 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342336 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2359 |  | 1314 | 2023-08-07 | Not Yet Available | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342335 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2359 |  | 1314 | 2023-08-07 | Not Yet Available | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35222036 |  | 95F | Fire Rebuild | 82841102 | Big Basin 1102 | WDRM v2 |  | 2359 |  | 1314 | Not Yet Available | Not Yet Available | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334541 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2358 |  | 897 | 2023-03-02 | 2023-04-20 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250987 |  | 95F | Fire Rebuild | 82841102 | Big Basin 1102 | WDRM v2 |  | 2358 |  | 897 | Not Yet Available | Not Yet Available | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35275478 |  | 2AF | Idle Facilities | 83371107 | SARATOGA 1107 | WDRM v2 |  | 2354 |  | 825 | Not Yet Available | Not Yet Available | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292789 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 2342 |  | 1533 | 2023-04-25 08:00 | 2023-05-30 17:00 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292788 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 2342 |  | 1533 | Not Yet Available | Not Yet Available | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292787 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 2342 |  | 1533 | Not Yet Available | Not Yet Available | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35294730 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 2320 |  | 394 | Not Yet Available | Not Yet Available | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35128962 |  | 08J | Other | 42761102 | FORT BRAGG A 1102 | WDRM v2 |  | 2305 |  | 2316 | 2024-01-08 08:00 | 2024-02-19 17:00 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35114040 |  | 08W | Base SH | 163751102 | PINE GROVE 1102 | WDRM v2 |  | 2271 |  | 558 | Not Yet Available | 2023-03-24 | 1.3718 | 0.093561 | 0 | 1.4653 | 0 | 0 | 0 | 0 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.099242 | 0.052841 | 0 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35318074 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2246 |  | 936 | 2023-06-02 08:00 | 2023-07-20 17:00 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35321894 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 |  | 2199 |  | 2216 | 2023-08-31 08:00 | 2023-08-31 16:00 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297464 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 |  | 2199 |  | 2216 | 2023-08-25 08:00 | 2023-09-26 17:00 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74028021 |  | 08W | Base SH | 42811113 | MONTE RIO 1113 | WDRM v2 |  | 2192 |  | 1383 | 2020-05-05 | Not Yet Available | 1.8559 | 0 | 0 | 1.8559 | 1.8402 | 0 | 0 | 1.8402 | 0 | 0 | 0 | 0 | 0.01572 | 0 | 0 | 0.01572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35284810 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 |  | 2186 |  | 2434 | 2023-09-25 08:00 | 2024-01-22 17:00 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219543 |  | 08W | Base SH | 153081112 | PLACERVILLE 1112 | WDRM v2 |  | 2123 |  | 1979 | 2023-09-20 08:00 | 2023-10-18 08:00 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35244173 |  | 2AF | Idle Facilities | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 |  | 2116 |  | 237 | Not Yet Available | Not Yet Available | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342339 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2070 |  | 1413 | 2023-04-12 08:00 | 2023-04-19 08:00 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35217275 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 |  | 2055 |  | 2554 | 2022-11-02 | 2023-04-26 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35217274 |  | 08W | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | WDRM v2 |  | 2055 |  | 2554 | Not Yet Available | Not Yet Available | 0 | 2.5239 | 0 | 2.5239 | 0 | 0 | 0 | 0 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228775 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 |  | 2048 |  | 3020 | Not Yet Available | Not Yet Available | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228774 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 |  | 2048 |  | 3020 | Not Yet Available | Not Yet Available | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223063 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 |  | 2048 |  | 3020 | 2023-07-24 | 2023-08-18 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35285594 |  | 08W | Fire Rebuild | 158031101 | ECHO SUMMIT 1101 | WDRM v2 |  | 2005 |  | 2299 | 2024-04-26 08:00 | 2024-06-07 17:00 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109546 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 |  | 1946 |  | 49 | 2022-08-29 | Not Yet Available | 2.3513 | 0.44621 | 0 | 2.7975 | 0 | 0 | 0 | 0 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109541 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 |  | 1946 |  | 49 | 2022-08-22 | 2023-02-10 | 2.8136 | 0.37955 | 0 | 3.1932 | 0 | 0 | 0 | 0 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.61288 | 0.33883 | 0 | 0.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35057010 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 |  | 1946 |  | 49 | 2022-04-26 | 2023-03-31 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056733 |  | 08W | Base SH | 152762101 | EL DORADO PH 2101 | WDRM v2 |  | 1946 |  | 49 | Not Yet Available | Not Yet Available | 1.7455 | 0.57576 | 0 | 2.3212 | 0 | 0 | 0 | 0 | 1.6231 | 0 | 0 | 1.6231 | 0 | 0 | 0 | 0 | 0.12235 | 0.57576 | 0 | 0.69811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223241 |  | 2AF | Idle Facilities | 24131102 | MENLO 1102 | WDRM v2 |  | 1917 |  | 630 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320462 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 1848 |  | 8953 | Not Yet Available | Not Yet Available | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35120413 |  | 2AF | Idle Facilities | 42011108 | SAN RAFAEL 1108 | WDRM v2 |  | 1837 |  | 1001 | Not Yet Available | Not Yet Available | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35275962 |  | 2BF | Idle Facilities | 103561101 | STILLWATER 1101 | WDRM v2 |  | 1828 |  | 838 | 2023-06-26 | 2023-06-26 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343741 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 |  | 1827 |  | 440 | 2023-12-14 08:00 | 2024-01-25 08:00 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312542 |  | 08W | Base SH | 43071101 | DUNBAR 1101 | WDRM v2 |  | 1827 |  | 440 | 2023-11-21 08:00 | 2024-01-02 08:00 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211297 |  | 2AF | Idle Facilities | 152491101 | WEIMAR 1101 | WDRM v2 |  | 1801 |  | 142 | Not Yet Available | Not Yet Available | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221715 |  | 2AF | Idle Facilities | 163351705 | CURTIS 1705 | WDRM v2 |  | 1770 |  | 2025 | Not Yet Available | Not Yet Available | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35281758 |  | 08W | Fire Rebuild | 102530401 | GRAYS FLAT 0401 | WDRM v2 |  | 1748 |  | 521 | 2023-08-09 08:00 | 2023-10-06 17:00 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35145001 |  | 08W | Base SH | 12022215 | CLAYTON 2215 | WDRM v2 |  | 1739 |  | 1812 | Not Yet Available | Not Yet Available | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35121520 |  | 2AF | Idle Facilities | 103271101 | ANTLER 1101 | WDRM v2 |  | 1722 |  | 247 | Not Yet Available | Not Yet Available | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329013 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1703 |  | 933 | Not Yet Available | Not Yet Available | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329012 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1703 |  | 1009 | Not Yet Available | Not Yet Available | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299633 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1703 |  | 1009 | 2023-09-08 08:00 | 2024-01-16 08:00 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35244150 |  | 2AF | Idle Facilities | 152101102 | ALLEGHANY 1102 | WDRM v2 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35284023 |  | 08W | Fire Rebuild | 43071101 | DUNBAR 1101 | WDRM v2 |  | 1684 |  | 732 | Not Yet Available | Not Yet Available | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35208054 |  | 2AF | Idle Facilities | 153082106 | PLACERVILLE 2106 | WDRM v2 |  | 1666 |  | 68 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35295446 |  | 08W | Fire Rebuild | 102211103 | BUCKS CREEK 1103 | WDRM v2 |  | 1658 |  | 404 | 2023-06-05 | 2023-09-30 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335235 |  | 08W | Base SH | 43432104 | SILVERADO 2104 | WDRM v2 |  | 1648 |  | 619 | 2024-04-12 08:00 | 2024-07-29 17:00 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211659 |  | 2AF | Idle Facilities | 152471101 | COLUMBIA HILL 1101 | WDRM v2 |  | 1590 |  | 149 | Not Yet Available | Not Yet Available | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224856 |  | 10K | Other | 102831104 | Paradise 1104 | WDRM v2 |  | 1537 |  | 362 | Not Yet Available | Not Yet Available | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329016 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1535 |  | 47 | 2023-09-27 08:00 | 2023-11-27 08:00 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299635 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1535 |  | 47 | 2023-08-28 08:00 | 2023-10-13 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236985 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2023-09-06 08:00 | 2023-10-19 10:00 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334407 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-05-01 08:48 | 2023-06-07 10:00 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297699 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-05-31 17:00 | 2023-07-31 17:00 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297697 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-08-29 13:48 | 2023-11-10 08:48 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297696 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-04-28 09:12 | 2023-10-19 09:36 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297695 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-04-28 10:24 | 2023-08-04 17:00 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297694 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-10-04 12:00 | 2023-12-18 12:00 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297693 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-08-29 12:00 | 2023-11-01 17:00 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35297692 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-06-19 12:00 | 2023-10-16 17:00 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35281816 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-05-13 08:24 | 2023-06-22 17:00 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35281815 |  | 08W | Fire Rebuild | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | 2023-04-28 08:24 | 2023-05-31 08:24 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264104 |  | 2AF | Idle Facilities | 152101101 | ALLEGHANY 1101 | WDRM v2 |  | 1446 |  | 254 | 2023-04-28 | 2023-04-28 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35150991 |  | 2AF | Idle Facilities | 192311142 | FRUITLAND 1142 | WDRM v2 |  | 1429 |  | 2354 | Not Yet Available | Not Yet Available | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243441 |  | 08W | Base SH | 103201102 | CHALLENGE 1102 | WDRM v2 |  | 1428 |  | 408 | Not Yet Available | Not Yet Available | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290901 |  | 16H | Other | 153701101 | LINCOLN 1101 | WDRM v2 |  | 1408 |  | 2686 | 2022-12-20 | 2023-04-12 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35242865 |  | 2AF | Idle Facilities | 24251101 | WOODSIDE 1101 | WDRM v2 |  | 1376 |  | 1131 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35353435 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 |  | 1363 |  | 277 | 2024-04-26 08:00 | 2024-08-12 17:00 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233996 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 |  | 1363 |  | 277 | 2022-11-15 | 2023-04-06 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233995 |  | 08W | Base SH | 153082106 | PLACERVILLE 2106 | WDRM v2 |  | 1363 |  | 277 | 2022-11-18 | 2023-04-03 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290517 |  | 08W | Fire Rebuild | 103104401 | SPANISH CREEK 4401 | WDRM v2 |  | 1322 |  | 1064 | 2023-04-20 08:00 | 2023-05-25 08:00 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35282166 |  | 08W | Fire Rebuild | 103104401 | SPANISH CREEK 4401 | WDRM v2 |  | 1322 |  | 1064 | 2023-05-05 08:00 | 2023-09-04 08:00 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35145540 |  | 08W | Base SH | 163451702 | FROGTOWN 1702 | WDRM v2 |  | 1316 |  | 1205 | 2023-09-18 08:00 | 2023-11-27 08:00 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35251360 |  | 06E | Other | 42091101 | MIRABEL 1101 | WDRM v2 |  | 1313 |  | 1448 | Not Yet Available | Not Yet Available | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243442 |  | 08W | Base SH | 152201102 | PIKE CITY 1102 | WDRM v2 |  | 1308 |  | 162 | Not Yet Available | Not Yet Available | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35083699 |  | 2AF | Idle Facilities | 254151101 | AUBERRY 1101 | WDRM v2 |  | 1302 |  | 348 | Not Yet Available | Not Yet Available | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241077 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2022-08-29 08:00 | Not Yet Available | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241076 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2023-07-14 08:00 | 2023-09-18 17:00 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241075 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2023-07-10 08:00 | 2023-09-13 17:00 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237889 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 250 | 2022-01-10 | Not Yet Available | 0 | 1.8256 | 0 | 1.8256 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236997 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2023-07-05 08:00 | 2023-08-24 17:00 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35235675 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2023-07-05 08:00 | 2023-08-16 17:00 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35235672 |  | 08W | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WDRM v2 |  | 1299 |  | 526 | 2023-07-05 08:00 | 2023-08-21 08:00 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35038684 |  | 2AF | Idle Facilities | 42681101 | LAYTONVILLE 1101 | WDRM v2 |  | 1293 |  | 992 | Not Yet Available | Not Yet Available | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292791 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 1285 |  | 2987 | 2022-08-08 | 2023-05-09 17:00 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35208094 |  | 2AF | Idle Facilities | 192221102 | GARBERVILLE 1102 | WDRM v2 |  | 1237 |  | 2057 | Not Yet Available | Not Yet Available | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279307 |  | 08W | Fire Rebuild | 103021101 | GANSNER 1101 | WDRM v2 |  | 1172 |  | 785 | 2023-09-11 08:00 | 2023-12-13 08:00 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332870 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 |  | 1166 |  | 1018 | 2023-06-27 08:00 | Not Yet Available | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332868 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 |  | 1166 |  | 1018 | 2023-07-06 08:00 | Not Yet Available | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312541 |  | 08W | Base SH | 163351701 | CURTIS 1701 | WDRM v2 |  | 1166 |  | 1018 | 2023-06-07 08:00 | Not Yet Available | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283938 |  | 08W | Base SH | 24251101 | WOODSIDE 1101 | WDRM v2 |  | 1145 |  | 1026 | 2023-12-31 | Not Yet Available | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35399833 |  | 08W | Base SH | 182581105 | GOLDTREE 1105 | WDRM v2 |  | 1104 |  | 1903 | Not Yet Available | Not Yet Available | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320444 |  | 08W | Base SH | 182581105 | GOLDTREE 1105 | WDRM v2 |  | 1104 |  | 1903 | 2023-09-01 | 2024-07-03 08:00 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35341551 |  | 08W | Base SH | 103501101 | PIT NO 7 1101 | WDRM v2 |  | 1055 |  | 549 | Not Yet Available | Not Yet Available | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338402 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 |  | 1038 |  | 3890 | Not Yet Available | Not Yet Available | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0
35320464 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 |  | 1038 |  | 3890 | Not Yet Available | Not Yet Available | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0
35244146 |  | 2AF | Idle Facilities | 153662102 | APPLE HILL 2102 | WDRM v2 |  | 1035 |  | 436 | Not Yet Available | Not Yet Available | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329014 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1033 |  | 711 | Not Yet Available | Not Yet Available | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299634 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1033 |  | 711 | 2023-07-07 08:00 | 2023-11-22 08:00 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277147 |  | 2AF | Idle Facilities | 252192105 | BEAR VALLEY 2105 | WDRM v2 |  | 1019 |  | 433 | Not Yet Available | Not Yet Available | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234526 |  | 08W | Base SH | 163541101 | MARTELL 1101 | WDRM v2 |  | 999 |  | 2578 | Not Yet Available | Not Yet Available | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292784 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 995 |  | 2135 | 2023-06-07 | 2023-10-15 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292780 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 995 |  | 2135 | 2023-05-29 | 2023-06-06 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290944 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 995 |  | 2135 | 2023-04-17 | 2023-05-12 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290544 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 995 |  | 2135 | 2022-10-17 08:00 | 2023-07-10 08:00 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290542 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 995 |  | 2135 | 2023-04-19 | 2023-05-03 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211643 |  | 2AF | Idle Facilities | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 981 |  | 957 | Not Yet Available | Not Yet Available | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343398 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | Not Yet Available | Not Yet Available | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343397 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | Not Yet Available | Not Yet Available | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343396 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-07-04 08:00 | 2023-09-29 16:00 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343395 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-06-28 08:00 | 2023-08-23 08:00 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35343394 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-06-07 08:00 | 2023-07-17 08:00 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35331309 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | Not Yet Available | Not Yet Available | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35331308 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-06-07 08:00 | 2023-07-04 08:00 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35331307 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-06-12 08:00 | 2023-09-29 08:00 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35331306 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | Not Yet Available | Not Yet Available | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312560 |  | 08W | Base SH | 102911110 | WYANDOTTE 1110 | WDRM v2 |  | 976 |  | 1779 | 2023-07-12 08:00 | 2023-10-25 08:00 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254948 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 966 |  | 281 | 2023-01-23 | 2023-04-28 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254947 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 966 |  | 281 | 2023-03-27 | 2023-04-28 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254946 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 966 |  | 281 | 2023-01-23 | 2023-04-21 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254945 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 966 |  | 281 | 2023-05-01 | 2023-05-12 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243453 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 966 |  | 281 | 2022-08-29 | 2023-04-14 | 1.428 | 0 | 0 | 1.428 | 0 | 0 | 0 | 0 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224438 |  | 2AF | Idle Facilities | 183101104 | CABRILLO 1104 | WDRM v2 |  | 949 |  | 2028 | Not Yet Available | Not Yet Available | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292758 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2023-04-17 08:00 | 2023-04-21 17:00 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292756 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2023-05-01 | 2023-06-26 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292755 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2022-10-27 | 2023-06-10 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35292754 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2023-05-09 | 2023-06-08 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290540 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2022-10-26 | 2023-05-09 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280493 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2023-05-09 | 2023-06-09 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279985 |  | 08W | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 916 |  | 575 | 2023-05-01 | 2023-08-04 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280498 |  | 08W | Fire Rebuild | 103132101 | CRESCENT MILLS 2101 | WDRM v2 |  | 895 |  | 854 | 2023-05-02 08:00 | 2023-05-10 17:00 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280496 |  | 08W | Fire Rebuild | 103132101 | CRESCENT MILLS 2101 | WDRM v2 |  | 895 |  | 854 | 2023-06-06 08:00 | 2023-06-16 16:00 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35145458 |  | 2AF | Idle Facilities | 252192105 | BEAR VALLEY 2105 | WDRM v2 |  | 882 |  | 550 | 2023-03-27 | 2023-03-27 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221620 |  | 2AF | Idle Facilities | 83242105 | MORGAN HILL 2105 | WDRM v2 |  | 854 |  | 1052 | 2023-06-30 | 2023-06-30 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35190945 |  | 10Q | Other | 163451702 | Frogtown 1702 | WDRM v2 |  | 838 |  | 1734 | 2022-08-22 | 2023-01-27 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332718 |  | 06H | Other | 163781705 | PEORIA 1705 | WDRM v2 |  | 835 |  | 1778 | Not Yet Available | Not Yet Available | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35204814 |  | 2AF | Idle Facilities | 103601101 | WHITMORE 1101 | WDRM v2 |  | 820 |  | 1536 | Not Yet Available | Not Yet Available | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74010582 |  | 30A | Other | 152261107 | Diamond Springs 1107 | WDRM v2 |  | 811 |  | 1184 | 2024-08-26 08:00 | 2024-12-27 17:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173857 |  | 06E | Other | 43432104 | SILVERADO 2104 | WDRM v2 |  | 792 |  | 59 | 2022-10-29 | 2023-02-11 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211230 |  | 2AF | Idle Facilities | 152921101 | BROWNS VALLEY 1101 | WDRM v2 |  | 774 |  | 3122 | Not Yet Available | Not Yet Available | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221249 |  | 2AF | Idle Facilities | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 771 |  | 1281 | Not Yet Available | Not Yet Available | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35217564 |  | 2AF | Idle Facilities | 153132101 | NARROWS 2101 | WDRM v2 |  | 758 |  | 2091 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221659 |  | 2AF | Idle Facilities | 163341101 | CLAY 1101 | WDRM v2 |  | 744 |  | 2444 | 2022-09-07 | 2023-07-12 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342151 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | Not Yet Available | Not Yet Available | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342148 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-10-19 08:00 | 2023-11-06 08:00 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342147 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-06-14 08:00 | 2023-08-08 08:00 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342146 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-06-14 08:00 | 2023-08-25 08:00 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342145 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-06-14 08:00 | 2023-06-27 08:00 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342144 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-10-19 08:00 | 2023-12-21 08:00 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342143 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-10-19 08:00 | 2024-01-24 08:00 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320442 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | 2023-06-27 08:00 | 2023-07-13 08:00 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337015 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 724 |  | 1928 | 2023-06-13 08:00 | 2023-07-18 08:00 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337014 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 724 |  | 1928 | 2023-06-23 08:00 | 2023-07-28 08:00 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329011 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 698 |  | 1028 | 2023-05-09 08:00 | 2023-09-06 08:00 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329010 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 698 |  | 1028 | 2023-07-04 08:00 | 2023-08-22 08:00 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329009 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 698 |  | 1028 | 2023-04-12 08:00 | 2023-06-12 08:00 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299631 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 698 |  | 1028 | 2023-04-24 08:00 | 2023-10-31 08:00 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35207962 |  | 2AF | Idle Facilities | 103601101 | WHITMORE 1101 | WDRM v2 |  | 678 |  | 1076 | Not Yet Available | Not Yet Available | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35026643 |  | 08W | Base SH | 152261105 | DIAMOND SPRINGS 1105 | WDRM v2 |  | 666 |  | 775 | 2022-11-04 | 2023-04-30 | 1.0733 | 0 | 0 | 1.0733 | 0 | 0 | 0 | 0 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339665 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 |  | 661 |  | 2556 | 2023-07-10 | 2023-10-20 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339664 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 |  | 661 |  | 2556 | 2023-07-10 | 2023-10-20 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320447 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 |  | 661 |  | 2556 | 2023-07-10 | 2023-10-20 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335287 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 642 |  | 72 | Not Yet Available | Not Yet Available | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335286 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 642 |  | 72 | Not Yet Available | Not Yet Available | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312553 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 642 |  | 72 | Not Yet Available | Not Yet Available | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246501 |  | 08W | Base SH | 42561107 | FULTON 1107 | WDRM v2 |  | 637 |  | 1034 | 2023-08-09 08:00 | 2023-12-14 08:00 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35149235 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 |  | 626 |  | 582 | Not Yet Available | Not Yet Available | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35274595 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 605 |  | 565 | 2023-05-08 | 2023-05-20 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332866 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 |  | 590 |  | 2153 | 2023-06-29 08:00 | 2023-10-09 16:00 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312549 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 |  | 590 |  | 2901 | 2023-06-19 08:00 | 2023-09-26 08:00 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342313 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2024-10-16 08:00 | Not Yet Available | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342312 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2024-10-16 08:00 | Not Yet Available | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342311 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2024-09-16 08:00 | 2025-01-02 17:00 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320607 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | Not Yet Available | Not Yet Available | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312555 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2024-09-12 08:00 | 2024-12-19 08:00 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35364450 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35364442 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-06-14 08:00 | 2024-09-30 17:00 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35364339 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-03-26 08:00 | 2024-07-10 17:00 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35364337 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-04-09 08:00 | 2024-07-24 17:00 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35364334 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-06-28 08:00 | 2024-10-14 17:00 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334468 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334467 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-03-21 08:00 | 2024-11-07 08:00 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334466 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2024-07-25 08:00 | 2024-11-07 08:00 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332958 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2023-06-21 08:00 | 2023-08-29 08:00 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320312 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2023-05-26 08:00 | 2023-09-15 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35262345 |  | 2AF | Idle Facilities | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 554 |  | 1152 | Not Yet Available | Not Yet Available | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056808 |  | 30A | Other | 42571102 | Molino 1102 | WDRM v2 |  | 534 |  | 1720 | Not Yet Available | Not Yet Available | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35275479 |  | 2AF | Idle Facilities | 102541101 | VOLTA 1101 | WDRM v2 |  | 532 |  | 1752 | 2023-05-15 | 2023-05-15 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35262812 |  | 06H | Other | 43351103 | LUCERNE 1103 | WDRM v2 |  | 512 |  | 3737 | 2024-03-13 08:00 | 2024-06-04 17:00 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35260649 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 510 |  | 1729 | 2024-03-01 | 2024-05-30 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335293 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 500 |  | 1985 | 2023-10-16 08:00 | 2024-01-29 08:00 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335292 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 500 |  | 1985 | 2023-06-09 08:00 | 2023-08-14 08:00 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335291 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 500 |  | 1985 | 2023-06-09 08:00 | 2023-08-10 08:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320440 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 500 |  | 1985 | 2023-08-09 08:00 | Not Yet Available | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243443 |  | 08W | Base SH | 252941107 | TIVY VALLEY 1107 | WDRM v2 |  | 491 |  | 1657 | Not Yet Available | Not Yet Available | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35244105 |  | 2AF | Idle Facilities | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236439 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2022-08-08 | 2023-03-17 08:00 | 0.17614 | 1.2508 | 0 | 1.4269 | 0 | 0 | 0 | 0 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234865 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-05-30 08:00 | 2024-01-17 17:00 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234862 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-04-03 | 2023-06-22 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234758 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-05-02 08:00 | 2023-03-17 08:00 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234756 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | Not Yet Available | Not Yet Available | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227025 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2022-10-03 | 2023-02-22 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227015 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2022-05-09 | Not Yet Available | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227007 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-09-18 08:00 | 2024-01-04 08:00 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227002 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | Not Yet Available | Not Yet Available | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227001 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2022-11-07 | 2023-04-15 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226878 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-04-03 | 2023-06-24 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226873 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | Not Yet Available | Not Yet Available | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226862 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2022-07-27 | 2023-08-15 17:00 | 0.71326 | 0 | 0 | 0.71326 | 0 | 0 | 0 | 0 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226857 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-08-15 08:00 | 2024-01-22 17:00 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174501 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-05-17 08:00 | 2023-11-22 17:00 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174479 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | Not Yet Available | Not Yet Available | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174478 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2023-03-31 | 2023-03-31 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227031 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2023-01-30 | 2023-09-30 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227030 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2022-08-15 | 2023-06-30 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226621 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2024-02-20 08:00 | 2024-03-26 08:00 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192282 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2024-02-26 08:00 | 2024-04-08 08:00 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35340270 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 457 |  | 2905 | 2023-05-25 08:00 | 2024-01-11 08:00 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311898 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 457 |  | 2905 | 2023-06-23 08:00 | Not Yet Available | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35274593 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2023-07-05 | 2023-09-28 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35274589 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2023-07-03 | 2023-08-04 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35238088 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2022-10-31 | 2023-04-15 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250938 |  | 2AF | Idle Facilities | 153652108 | SHINGLE SPRINGS 2108 | WDRM v2 |  | 424 |  | 886 | Not Yet Available | Not Yet Available | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330243 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-08-22 08:00 | Not Yet Available | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330241 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-07-11 08:00 | 2023-10-25 16:00 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330219 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-07-21 08:00 | 2023-11-06 16:00 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330217 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-10-04 08:00 | 2023-11-08 08:00 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330216 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | Not Yet Available | Not Yet Available | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330215 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | Not Yet Available | Not Yet Available | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330213 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2024-05-13 08:00 | 2024-12-09 17:00 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330211 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-10-25 08:00 | 2023-12-26 08:00 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35317399 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-07-04 08:00 | 2023-09-15 08:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312550 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | 2023-08-04 08:00 | 2023-10-30 16:00 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241060 |  | 08W | Base SH | 254421101 | OAKHURST 1101 | WDRM v2 |  | 421 |  | 913 | 2022-09-09 | 2023-03-31 17:00 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320463 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 419 |  | 987 | 2023-06-28 08:00 | 2023-08-02 08:00 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35221246 |  | 2AF | Idle Facilities | 42601101 | PHILO 1101 | WDRM v2 |  | 417 |  | 1638 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380377 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380376 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380375 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380374 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380373 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380372 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380371 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380370 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-10-16 08:00 | Not Yet Available | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380369 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-09-05 08:00 | 2023-12-20 17:00 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380368 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-09-21 08:00 | 2024-01-09 17:00 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35380365 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-09-27 08:00 | 2024-01-16 17:00 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334230 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334229 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-09-05 08:00 | 2023-12-20 17:00 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311897 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2023-09-01 08:00 | Not Yet Available | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35276100 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | Not Yet Available | Not Yet Available | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35229051 |  | 08W | Base SH | 103331102 | CORNING 1102 | WDRM v2 |  | 413 |  | 694 | 2022-12-02 | 2023-04-15 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35285065 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 396 |  | 2321 | 2023-03-31 | 2023-03-31 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35285064 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 396 |  | 2321 | 2023-03-31 | 2023-03-31 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339293 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-05-30 08:00 | 2023-07-11 08:00 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338410 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-06 08:00 | 2023-09-05 08:00 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338409 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-27 08:00 | 2023-09-26 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338408 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-21 08:00 | 2023-07-26 08:00 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338407 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-09 08:00 | 2023-07-07 08:00 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338406 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-30 08:00 | 2023-08-04 08:00 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338405 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-23 08:00 | 2023-09-29 08:00 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338404 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-23 08:00 | 2023-07-28 08:00 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320461 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-16 08:00 | 2023-10-13 08:00 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320460 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 393 |  | 728 | 2023-06-15 08:00 | 2023-08-31 08:00 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339289 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-04-25 08:00 | 2023-06-26 08:00 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339288 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-04-25 08:00 | 2023-08-01 08:00 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339287 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-04-25 08:00 | 2023-08-01 08:00 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339286 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-07-14 08:00 | 2023-07-14 08:00 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339285 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-07-18 08:00 | 2023-09-13 08:00 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339283 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-07-13 08:00 | 2023-09-25 08:00 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339282 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-07-06 08:00 | 2023-07-20 08:00 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337011 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-06-07 08:00 | 2023-09-27 08:00 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337010 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-06-07 08:00 | 2023-09-13 08:00 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337008 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-06-07 08:00 | 2023-08-16 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35317887 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-04-25 08:00 | 2023-07-25 08:00 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35317480 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-08-30 08:00 | 2023-10-19 08:00 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312548 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | 2023-07-14 08:00 | 2023-11-07 08:00 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280560 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 |  | 378 |  | 45 | 2023-03-16 | 2023-09-05 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280499 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 |  | 378 |  | 45 | 2023-03-16 | 2023-09-05 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279182 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 |  | 378 |  | 45 | 2023-03-16 | 2023-09-05 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279181 |  | 08W | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | WDRM v2 |  | 378 |  | 45 | 2023-03-16 | 2023-09-05 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192280 |  | 08W | Base SH | 12022212 | CLAYTON 2212 | WDRM v2 |  | 377 |  | 15 | 2023-03-20 | 2023-06-30 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223030 |  | 08W | Base SH | 103191101 | BANGOR 1101 | WDRM v2 |  | 355 |  | 2768 | 2022-08-01 | Not Yet Available | 0.28352 | 1.1968 | 0 | 1.4803 | 0 | 0 | 0 | 0 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.060417 | 0 | 0.060417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330249 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-04-03 | 2023-07-21 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330248 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2024-01-25 08:00 | 2024-05-22 08:00 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330247 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-04-10 | 2023-05-05 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330246 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-05-08 | 2023-06-02 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330245 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-04-03 | 2023-04-07 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330244 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-06-05 | 2023-06-23 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329474 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 375 | 2023-10-25 08:00 | 2023-11-23 08:00 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35317398 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 375 | 2023-10-24 08:00 | 2024-02-06 08:00 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312552 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | 2023-05-23 08:00 | 2023-06-28 17:00 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35208096 |  | 2AF | Idle Facilities | 43191101 | REDBUD 1101 | WDRM v2 |  | 345 |  | 679 | Not Yet Available | 2023-06-02 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35083879 |  | 2AF | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 |  | 337 |  | 2377 | Not Yet Available | Not Yet Available | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35285251 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2023-06-30 | 2023-09-30 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35285249 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2023-05-08 | 2023-12-08 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283346 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2023-05-01 | 2023-09-30 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283343 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2023-06-05 | 2023-09-30 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35256083 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2023-01-30 | 2023-06-30 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35256082 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | Not Yet Available | Not Yet Available | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35083893 |  | 2AF | Idle Facilities | 13751102 | VASCO 1102 | WDRM v2 |  | 324 |  | 764 | 2023-03-17 | 2023-03-17 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35134959 |  | 06A | Other | 163231101 | NORTH BRANCH 1101 | WDRM v2 |  | 322 |  | 1048 | 2023-12-22 08:00 | 2024-03-28 17:00 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332364 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-08-01 08:00 | 2023-08-29 08:00 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332363 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-07-26 08:00 | 2023-10-26 16:00 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332362 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-07-19 08:00 | Not Yet Available | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332361 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | Not Yet Available | Not Yet Available | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332360 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-07-13 08:00 | Not Yet Available | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330813 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | Not Yet Available | Not Yet Available | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330812 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-05-04 08:00 | 2023-08-24 08:00 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35316278 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-05-18 08:00 | 2023-12-21 08:00 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312543 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 315 |  | 1044 | 2023-06-02 08:00 | 2023-08-21 17:00 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329473 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 312 |  | 44 | 2024-01-12 08:00 | 2024-06-17 16:00 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329472 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 312 |  | 44 | Not Yet Available | Not Yet Available | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312551 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 312 |  | 44 | Not Yet Available | Not Yet Available | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349646 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 307 |  | 2847 | Not Yet Available | Not Yet Available | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349645 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 307 |  | 2847 | Not Yet Available | Not Yet Available | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349643 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 307 |  | 2847 | Not Yet Available | Not Yet Available | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279629 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 291 |  | 311 | 2024-03-01 | 2024-05-30 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279628 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 291 |  | 311 | 2024-04-01 | 2024-06-30 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254252 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 291 |  | 311 | 2023-05-09 | 2023-07-30 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277935 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2023-05-15 | 2023-06-09 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332217 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-05-01 08:00 | 2023-08-01 08:00 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332216 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-04-24 08:00 | 2023-06-05 08:00 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332215 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-04-24 08:00 | 2023-07-03 08:00 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332214 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-05-08 08:00 | 2023-09-05 08:00 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35316569 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-04-19 08:00 | 2023-09-27 08:00 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35316567 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-03-27 | 2023-09-08 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312540 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 271 |  | 2723 | 2023-04-17 | 2023-09-15 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349651 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | Not Yet Available | Not Yet Available | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349650 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | 2024-04-09 08:00 | 2024-07-02 17:00 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349649 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | 2024-05-13 08:00 | 2024-07-16 17:00 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349648 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | 2024-04-24 08:00 | 2024-06-06 08:00 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349647 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | 2024-04-11 08:00 | 2024-05-08 17:00 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35329008 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 268 |  | 2491 | 2023-07-25 08:00 | 2023-09-11 08:00 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299629 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 268 |  | 2491 | 2024-05-07 08:00 | 2024-06-24 08:00 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35330815 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 262 |  | 3263 | 2023-07-10 | 2023-09-01 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311895 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 262 |  | 3263 | 2023-05-22 | 2023-09-22 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279626 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 260 |  | 940 | 2023-04-21 | 2023-05-16 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254254 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 260 |  | 940 | 2023-03-28 | 2023-06-02 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35151005 |  | 2AF | Idle Facilities | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 259 |  | 327 | Not Yet Available | Not Yet Available | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279631 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 257 |  | 771 | 2022-06-14 | 2023-05-05 | 3.064 | 0 | 0 | 3.064 | 0 | 0 | 0 | 0 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254248 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 257 |  | 771 | 2024-08-01 | 2024-09-30 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225318 |  | 2AF | Idle Facilities | 183031101 | PALMER 1101 | WDRM v2 |  | 256 |  | 2229 | 2023-07-24 | 2023-07-24 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337306 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 235 |  | 54 | 2023-03-27 | 2023-07-31 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35284366 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 235 |  | 54 | Not Yet Available | Not Yet Available | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35284365 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 235 |  | 54 | 2023-06-27 08:00 | 2023-12-25 17:00 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35284364 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 235 |  | 54 | 2023-03-27 | 2023-06-30 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250577 |  | 08W | Base SH | 162821702 | STANISLAUS 1702 | WDRM v2 |  | 235 |  | 54 | 2023-01-23 | 2023-06-30 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35349244 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 230 |  | 4147 | 2023-06-26 08:00 | 2023-09-22 16:00 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339292 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 230 |  | 4147 | Not Yet Available | Not Yet Available | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339291 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 230 |  | 4147 | Not Yet Available | Not Yet Available | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35339290 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 230 |  | 4147 | Not Yet Available | Not Yet Available | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320450 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 230 |  | 4147 | 2023-06-30 08:00 | 2023-10-06 08:00 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35211757 |  | 2AF | Idle Facilities | 103191101 | BANGOR 1101 | WDRM v2 |  | 225 |  | 2534 | Not Yet Available | Not Yet Available | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223039 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 |  | 218 |  | 2461 | Not Yet Available | Not Yet Available | 0.076705 | 0.53561 | 0 | 0.61231 | 0 | 0 | 0 | 0 | 0.062879 | 0.40985 | 0 | 0.47273 | 0 | 0 | 0 | 0 | 0.013826 | 0.12576 | 0 | 0.13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223615 |  | 08W | Base SH | 42991105 | LAS GALLINAS A 1105 | WDRM v2 |  | 215 |  | 1267 | 2023-05-26 08:00 | 2023-09-14 17:00 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35150641 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 |  | 212 |  | 847 | Not Yet Available | Not Yet Available | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312544 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 206 |  | 1350 | 2023-04-24 | 2023-05-19 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35262347 |  | 2AF | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 |  | 195 |  | 1266 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35215883 |  | 2AA | Idle Facilities | 254601103 | SAND CREEK 1103 | WDRM v2 |  | 195 |  | 1266 | Not Yet Available | Not Yet Available | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35335290 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 190 |  | 1722 | 2023-08-08 08:00 | 2024-01-02 08:00 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320441 |  | 08W | Base SH | 63601111 | VACAVILLE 1111 | WDRM v2 |  | 190 |  | 1722 | 2023-08-08 08:00 | 2023-11-17 08:00 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337164 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 185 |  | 2971 | 2024-05-13 08:00 | 2024-09-16 17:00 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35337163 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 185 |  | 2971 | 2023-05-17 08:00 | 2023-09-11 16:00 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320449 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 185 |  | 2971 | 2023-04-27 08:00 | 2023-07-28 08:00 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35208097 |  | 2AF | Idle Facilities | 43361103 | HIGHLANDS 1103 | WDRM v2 |  | 181 |  | 270 | 2023-04-26 | 2023-04-26 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254266 |  | 08W | Base SH | 63681102 | PUTAH CREEK 1102 | WDRM v2 |  | 171 |  | 712 | 2023-03-27 | 2023-03-31 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240173 |  | 08W | Base SH | 63681102 | PUTAH CREEK 1102 | WDRM v2 |  | 171 |  | 712 | 2023-04-10 | 2023-05-01 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35310704 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | Not Yet Available | Not Yet Available | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305312 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-08 08:00 | 2024-04-19 16:00 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305311 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305310 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305309 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-12 08:00 | 2024-06-17 17:00 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305308 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | Not Yet Available | Not Yet Available | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305307 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-09 08:00 | 2024-05-06 16:00 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305306 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-09 08:00 | 2024-05-13 16:00 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305305 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-09 08:00 | 2024-06-17 16:00 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305304 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-02-08 08:00 | 2024-06-14 16:00 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35305303 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2023-05-09 08:00 | 2023-08-16 16:00 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293670 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2023-05-13 | 2023-05-28 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293669 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-11 08:00 | 2024-07-22 17:00 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293668 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293667 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293666 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293665 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2023-02-13 | 2023-04-26 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293664 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-01 08:00 | 2024-07-12 17:00 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293663 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | Not Yet Available | Not Yet Available | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293662 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2023-03-16 | 2023-05-12 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254071 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-04 08:00 | 2024-07-15 17:00 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254070 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 169 |  | 401 | 2024-03-08 08:00 | 2024-07-08 17:00 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278892 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-12-03 | 2024-12-31 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278891 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-12-03 | 2024-12-31 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278890 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-12-03 | 2024-12-31 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278097 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2022-08-30 | 2023-05-12 | 1.286 | 0 | 0.20095 | 1.4869 | 0 | 0 | 0 | 0 | 0.66345 | 0 | 0 | 0.66345 | 0.62254 | 0 | 0.20095 | 0.82348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278092 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-04-01 | 2024-06-30 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278091 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-03-01 | 2024-05-31 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277938 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-06-05 | 2023-08-18 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277937 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-01-02 | 2024-03-15 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277936 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-06-06 | 2023-11-30 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277924 |  | 08W | Base SH | 254151105 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-05-22 | 2023-08-25 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277923 |  | 08W | Base SH | 254151104 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-06-06 | 2023-11-30 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277922 |  | 08W | Base SH | 254151103 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-04-01 | 2024-06-30 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277921 |  | 08W | Base SH | 254151102 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-03-01 | 2024-05-30 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254247 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-11-05 | 2024-12-31 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254245 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-09-05 | 2023-12-29 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254244 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2023-05-12 | 2023-06-30 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254243 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | 2024-02-01 | 2024-04-28 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226852 |  | 08W | Base SH | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 |  | 159 |  | 241 | 2023-01-24 | 2023-05-30 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35062376 |  | 08W | Base SH | 153652109 | SHINGLE SPRINGS 2109 | WDRM v2 |  | 159 |  | 241 | 2022-08-10 | 2023-06-02 | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254651 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 157 |  | 280 | 2022-05-23 | 2023-04-05 | 2.4038 | 0 | 0 | 2.4038 | 0 | 0 | 0 | 0 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254650 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 157 |  | 280 | 2022-10-10 | Not Yet Available | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.30436 | 0 | 0.30436 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264190 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-03-27 | 2023-05-22 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264189 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-01-23 | 2023-05-22 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264188 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2022-12-05 | 2023-04-01 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264187 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-05-31 08:00 | 2023-07-31 17:00 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264185 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-02-13 | 2023-02-17 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240223 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-01-23 | 2023-05-22 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240222 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 153 |  | 1417 | 2023-03-07 08:00 | 2023-04-18 08:00 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35325590 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 |  | 152 |  | 1508 | 2023-10-02 08:00 | 2023-12-18 08:00 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35325589 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 |  | 152 |  | 1508 | 2023-09-01 08:00 | 2023-11-20 16:00 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35312545 |  | 08W | Base SH | 152531101 | FLINT 1101 | WDRM v2 |  | 152 |  | 1508 | 2023-08-01 08:00 | 2023-09-06 16:00 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249999 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 144 |  | 2787 | 2022-08-02 | 2023-03-31 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249998 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 144 |  | 2787 | 2022-05-01 | Not Yet Available | 3.4638 | 0 | 0 | 3.4638 | 0 | 0 | 0 | 0 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35331305 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 143 |  | 3058 | 2023-05-29 | 2023-07-21 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35298571 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 143 |  | 3058 | 2023-06-26 | 2023-07-21 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279627 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 138 |  | 742 | 2024-02-07 | 2024-04-30 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249877 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 132 |  | 1380 | 2023-10-03 08:00 | Not Yet Available | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249876 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 132 |  | 1380 | 2022-09-05 | 2023-04-28 | 3.7142 | 0 | 0 | 3.7142 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249875 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 132 |  | 1380 | 2022-09-05 | 2023-05-26 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240165 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 132 |  | 1380 | 2022-09-30 | 2023-05-26 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332218 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 123 |  | 1675 | 2023-06-09 08:00 | 2023-09-29 08:00 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332213 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 123 |  | 1675 | 2023-07-21 08:00 | 2023-11-23 16:00 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35316561 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 123 |  | 1675 | 2023-07-17 | 2023-09-08 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311899 |  | 08W | Base SH | 102931102 | COTTONWOOD 1102 | WDRM v2 |  | 123 |  | 1675 | 2023-06-06 08:00 | 2023-10-03 08:00 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334755 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | 2023-10-27 08:00 | 2023-12-19 08:00 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334754 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | 2023-10-10 08:00 | Not Yet Available | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334753 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | 2023-06-12 | 2023-09-29 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320339 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | 2023-10-10 08:00 | 2024-01-31 08:00 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320336 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | Not Yet Available | Not Yet Available | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334234 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-25 08:00 | 2024-07-25 08:00 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334233 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-06-03 08:00 | 2024-10-07 17:00 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334232 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-05-01 08:00 | 2024-06-19 08:00 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334231 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-05-08 08:00 | 2024-09-12 16:00 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333510 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-29 08:00 | 2024-09-02 17:00 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333509 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-02 08:00 | 2024-08-12 17:00 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333508 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333507 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333506 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-04-02 08:00 | 2024-08-07 16:00 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333505 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | Not Yet Available | Not Yet Available | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333504 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2023-09-05 08:00 | 2023-09-26 08:00 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333503 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2023-09-05 08:00 | 2023-11-02 08:00 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333502 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | Not Yet Available | Not Yet Available | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333501 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2023-10-18 08:00 | 2024-01-26 08:00 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35333500 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | Not Yet Available | Not Yet Available | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35314416 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-05-20 08:00 | 2024-07-22 08:00 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35314415 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2023-09-29 08:00 | Not Yet Available | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311896 |  | 08W | Base SH | 152701108 | BELL 1108 | WDRM v2 |  | 118 |  | 2685 | 2024-05-01 08:00 | 2024-08-07 08:00 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35149246 |  | 2AF | Idle Facilities | 42251101 | HOPLAND 1101 | WDRM v2 |  | 110 |  | 519 | 2022-12-20 | Not Yet Available | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264182 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 108 |  | 2888 | 2022-10-04 | 2023-03-03 08:00 | 2.6348 | 0 | 0 | 2.6348 | 0 | 0 | 0 | 0 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35264181 |  | 08W | Base SH | 182721104 | SANTA YNEZ 1104 | WDRM v2 |  | 108 |  | 2888 | 2022-10-29 | 2023-02-16 | 2.7506 | 0 | 0 | 2.7506 | 0 | 0 | 0 | 0 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35259512 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 |  | 100 |  | 2704 | 2023-01-16 | 2023-01-31 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254940 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 85 |  | 2428 | Not Yet Available | Not Yet Available | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254738 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 85 |  | 2428 | Not Yet Available | Not Yet Available | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254658 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 85 |  | 2428 | 2022-06-22 08:00 | Not Yet Available | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243444 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 85 |  | 2428 | Not Yet Available | Not Yet Available | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240164 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 78 |  | 1728 | 2023-03-22 | 2023-06-23 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254259 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 76 |  | 2202 | 2023-02-06 | 2023-03-31 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254258 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 76 |  | 2202 | 2022-09-05 | 2023-04-07 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240166 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 76 |  | 2202 | 2022-03-28 | 2023-01-27 | 0.46326 | 0.015341 | 0 | 0.4786 | 0 | 0 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293846 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-24 | 2023-05-19 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293845 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-02-13 | 2023-04-28 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293844 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-01-24 | 2023-04-28 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293843 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-06 08:00 | 2023-06-13 17:00 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293841 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-04-02 08:00 | 2024-06-20 17:00 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293775 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-01-23 | 2023-04-10 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293774 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-01-15 08:00 | 2024-03-07 17:00 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293770 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-09-04 08:00 | Not Yet Available | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290808 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-10 | 2023-04-28 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290807 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-05-09 08:00 | 2024-07-04 17:00 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290509 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-09-18 08:00 | 2024-11-05 17:00 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290508 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-09-18 08:00 | 2023-11-20 17:00 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290507 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-02-26 08:00 | 2024-03-22 17:00 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290506 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-06-14 08:00 | 2024-07-25 17:00 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290504 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-06-26 08:00 | 2023-07-31 08:00 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290503 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-09-10 08:00 | 2024-10-22 08:00 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290502 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | Not Yet Available | Not Yet Available | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290501 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-07-02 08:00 | 2024-09-10 17:00 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290500 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-10 | 2023-04-10 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290299 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-01-24 | 2023-04-28 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290298 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-01-24 | 2023-04-28 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290297 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-17 08:00 | 2023-09-07 17:00 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290296 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-06-05 08:00 | 2023-08-15 17:00 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35290295 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-06-05 08:00 | 2023-07-28 17:00 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254076 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2024-09-18 08:00 | 2024-10-23 17:00 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254075 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | Not Yet Available | Not Yet Available | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254074 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-05 08:00 | 2023-05-09 17:00 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254073 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2023-04-17 08:00 | 2023-07-13 08:00 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278888 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2024-02-11 | 2024-04-30 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278887 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2022-12-27 | 2023-04-14 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278884 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2023-05-09 | 2023-07-30 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278883 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2023-03-28 | 2023-07-01 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278882 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2022-08-16 | 2023-05-05 | 2.6322 | 0 | 0 | 2.6322 | 0 | 0 | 0 | 0 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278881 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2023-03-28 | 2023-07-10 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254249 |  | 08W | Base SH | 182611103 | PASO ROBLES 1103 | WDRM v2 |  | 69 |  | 940 | 2022-09-06 | 2023-04-07 | 2.6725 | 0 | 0 | 2.6725 | 0 | 0 | 0 | 0 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35301114 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-05-22 08:00 | 2024-10-02 17:00 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35301113 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-18 08:00 | 2024-08-29 17:00 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35301112 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2023-04-10 | 2023-06-23 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35300934 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-22 08:00 | 2024-09-02 17:00 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35300933 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2023-03-06 | 2023-05-12 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293847 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-24 08:00 | 2024-08-13 17:00 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293677 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-05-07 08:00 | 2024-08-26 17:00 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293676 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-04 08:00 | 2024-08-15 17:00 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293675 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-06-20 08:00 | 2024-10-02 17:00 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293674 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-17 08:00 | 2024-08-28 17:00 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293673 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-06-06 08:00 | 2024-10-17 17:00 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293672 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-02-27 08:00 | 2024-06-11 17:00 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293509 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-24 08:00 | 2024-09-04 17:00 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293508 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2023-05-01 | 2023-05-26 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293507 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-05-08 08:00 | 2024-10-28 17:00 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293506 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-24 08:00 | 2024-09-04 17:00 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35293505 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-05-01 08:00 | 2024-09-11 17:00 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254069 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-12 08:00 | 2024-08-23 17:00 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254068 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2024-04-18 08:00 | 2024-08-29 17:00 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254067 |  | 08W | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2023-09-13 08:00 | 2023-10-18 08:00 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223032 |  | 08W | Base SH | 152282102 | MOUNTAIN QUARRIES 2101 | WDRM v2 |  | 68 |  | 106 | 2023-05-15 | 2023-08-15 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334752 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 64 |  | 768 | Not Yet Available | Not Yet Available | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334750 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 64 |  | 768 | Not Yet Available | Not Yet Available | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320334 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 64 |  | 768 | 2023-06-29 08:00 | 2023-10-02 08:00 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320333 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 64 |  | 768 | Not Yet Available | Not Yet Available | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277930 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2023-06-06 | 2023-06-23 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277929 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2023-05-02 | 2023-08-31 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277926 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2022-08-16 | 2023-05-26 | 3.4381 | 0 | 0 | 3.4381 | 0 | 0 | 0 | 0 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35277925 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2023-04-28 | 2023-04-28 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254079 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2023-05-02 | 2023-06-09 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250738 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | Not Yet Available | Not Yet Available | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250737 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | 2023-06-27 | 2023-09-01 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240162 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | Not Yet Available | Not Yet Available | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283340 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-03-06 | 2023-06-30 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283199 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-03-06 | 2023-06-30 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283198 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-07-03 | 2023-07-21 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283197 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-03-06 | 2023-06-30 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35283196 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-03-06 | 2023-06-30 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250576 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 58 |  | 486 | 2023-03-06 | 2023-06-30 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35274597 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 57 |  | 82 | 2023-10-27 08:00 | Not Yet Available | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250573 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 57 |  | 82 | 2023-04-10 | 2023-05-05 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35338384 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-06-06 08:00 | 2023-09-29 08:00 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279122 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-05-01 | 2023-06-02 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279121 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-01-23 | 2023-02-15 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35279120 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-05-17 08:00 | 2023-08-16 08:00 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35278899 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-03-27 | 2023-06-30 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250578 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v2 |  | 56 |  | 95 | 2023-03-07 | 2023-05-31 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219591 |  | 08W | Base SH | 163541101 | OLETA 1101 | WDRM v2 |  | 54 |  | 2197 | 2023-06-06 | 2023-08-11 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226799 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 |  | 52 |  | 86 | 2023-06-02 08:00 | 2023-06-12 17:00 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226798 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 |  | 52 |  | 86 | 2023-04-03 08:00 | 2023-07-24 17:00 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224321 |  | 08W | Base SH | 103611101 | WILDWOOD 1101 | WDRM v2 |  | 52 |  | 86 | 2023-04-17 08:00 | 2023-07-31 17:00 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35280362 |  | 08W | Base SH | 254452102 | MARIPOSA 2102 | WDRM v2 |  | 50 |  | 400 | 2023-05-15 | 2023-09-28 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219588 |  | 08W | Base SH | 254452102 | MARIPOSA 2102 | WDRM v2 |  | 50 |  | 400 | 2022-05-31 | Not Yet Available | 0.88182 | 0 | 0.27973 | 1.1616 | 0 | 0 | 0 | 0 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35316537 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | Not Yet Available | Not Yet Available | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234400 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2022-08-10 | Not Yet Available | 1.2771 | 0 | 0 | 1.2771 | 0 | 0 | 0 | 0 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234399 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | Not Yet Available | Not Yet Available | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234398 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-01-16 | 2023-04-12 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234397 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2022-12-12 | 2023-06-27 17:00 | 0.71345 | 0 | 0 | 0.71345 | 0 | 0 | 0 | 0 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234396 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-08-17 | 2023-09-26 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234395 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-07-20 | 2023-08-24 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234394 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-06-20 | 2023-07-25 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234393 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-05-23 | 2023-06-27 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234382 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-04-01 | 2023-04-18 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234381 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-01-23 | 2023-03-31 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233951 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2022-09-07 | 2023-04-28 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233950 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-10-06 08:00 | 2024-05-24 17:00 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233949 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2022-04-28 | 2023-03-03 17:00 | 1.7706 | 0 | 0 | 1.7706 | 0 | 0 | 0 | 0 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233948 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-10-24 08:00 | 2024-03-01 08:00 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225829 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2022-10-10 | 2023-05-30 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219289 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-09-04 08:00 | 2024-01-04 17:00 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219287 |  | 08W | Base SH | 103521103 | OREGON TRAIL 1103 | WDRM v2 |  | 49 |  | 2405 | 2023-01-16 | 2023-04-03 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219280 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 43 |  | 1733 | 2022-04-05 | 2023-01-28 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227654 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 |  | 42 |  | 383 | 2023-06-26 08:00 | 2023-06-26 08:00 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227652 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 |  | 42 |  | 383 | 2022-11-14 | 2023-03-31 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219276 |  | 08W | Base SH | 63601104 | VACAVILLE 1104 | WDRM v2 |  | 42 |  | 383 | 2023-03-15 | 2023-05-07 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237370 |  | 08W | Base SH | 63591105 | VACA DIXON 1105 | WDRM v2 |  | 37 |  | 1554 | 2022-04-25 | Not Yet Available | 3.6491 | 0 | 0 | 3.6491 | 0 | 0 | 0 | 0 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226700 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 |  | 29 |  | 2717 | 2022-08-01 | 2023-02-15 | 0 | 0.4214 | 0 | 0.4214 | 0 | 0 | 0 | 0 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219260 |  | 08W | Base SH | 102911109 | WYANDOTTE 1109 | WDRM v2 |  | 29 |  | 2717 | 2021-09-15 | 2023-02-17 | 0.92822 | 0 | 0.86723 | 1.7955 | 0.87803 | 0 | 0 | 0.87803 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.86723 | 0.91742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231631 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2022-04-28 | Not Yet Available | 0.44867 | 0 | 0 | 0.44867 | 0 | 0 | 0 | 0 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231629 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-05-30 08:00 | 2023-07-24 17:00 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231628 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231627 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-06-30 | 2023-09-30 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231626 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2022-11-03 | Not Yet Available | 0.78295 | 0 | 0.64962 | 1.4326 | 0 | 0 | 0 | 0 | 0.78295 | 0 | 0.60417 | 1.3871 | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231625 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-09-01 08:00 | 2023-10-26 17:00 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231624 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231623 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231621 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-06-30 | 2023-09-30 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35231620 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-06-30 | 2023-09-30 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219099 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | 2023-06-30 | 2023-09-30 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227655 |  | 08W | Base SH | 14452104 | KIRKER 2104 | WDRM v2 |  | 21 |  | 571 | Not Yet Available | Not Yet Available | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219096 |  | 08W | Base SH | 14452104 | KIRKER 2104 | WDRM v2 |  | 21 |  | 571 | 2022-06-13 | 2023-03-15 | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0 | 0 | 0 | 0 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.028409 | 0.028409 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299137 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 595 | 2023-07-28 08:00 | 2023-09-12 08:00 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299136 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 595 | 2023-06-23 08:00 | 2023-08-11 08:00 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299135 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 595 | 2023-07-17 08:00 | 2023-09-15 08:00 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299134 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 595 | 2023-07-28 08:00 | 2023-09-11 08:00 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35299133 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 595 | 2023-03-31 | 2023-05-01 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250575 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 19 |  | 2963 | 2023-03-31 | 2023-05-01 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219093 |  | 08W | Base SH | 14652106 | TIDEWATER 2106 | WDRM v2 |  | 18 |  | 448 | 2023-04-03 | 2023-04-03 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228188 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 |  | 14 |  | 443 | 2022-08-25 | 2023-03-31 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228186 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 |  | 14 |  | 443 | 2023-06-30 | 2023-11-24 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227868 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 |  | 14 |  | 443 | 2022-07-06 | 2023-03-31 | 0.57727 | 0 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227864 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 |  | 14 |  | 443 | 2022-09-19 | 2023-04-14 | 0 | 1.3212 | 0 | 1.3212 | 0 | 0 | 0 | 0 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35220895 |  | 08W | Base SH | 43141103 | MIDDLETOWN 1103 | WDRM v2 |  | 14 |  | 443 | 2022-10-17 | 2023-04-14 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224713 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 |  | 11 |  | 21 | 2022-12-06 | 2023-04-28 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224712 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 |  | 11 |  | 21 | 2022-12-06 | 2023-04-28 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35217268 |  | 08W | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | WDRM v2 |  | 11 |  | 21 | 2022-07-27 | 2023-09-15 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227161 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 |  | 8 |  | 392 | Not Yet Available | Not Yet Available | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227160 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 |  | 8 |  | 392 | 2023-12-31 | 2024-09-20 17:00 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226819 |  | 08W | Base SH | 43141102 | MIDDLETOWN 1102 | WDRM v2 |  | 8 |  | 392 | 2023-12-31 | 2024-04-11 17:00 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226629 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v2 |  | 7 |  | 48 | 2023-06-19 08:00 | 2023-11-27 08:00 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226628 |  | 08W | Base SH | 103451101 | KESWICK 1101 | WDRM v2 |  | 7 |  | 48 | 2023-06-19 08:00 | 2023-07-31 08:00 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058839 |  | 07D | Other | 24251101 | WOODSIDE 1101 | WDRM v2 |  | 1145 |  | 1026 | 2022-09-17 | 2023-03-22 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35334404 |  | 08W | Fire Rebuild | 82931101 | POINT MORETTI 1101 | WDRM v2 |  | 1393 |  | 2485 | 2023-08-01 08:00 | 2023-08-14 17:00 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35332872 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | Not Yet Available | Not Yet Available | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320453 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | 2023-08-16 08:00 | 2023-12-21 16:00 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35311627 |  | 08W | Base SH | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 3328 |  | 969 | 2024-12-18 08:00 | 2025-03-19 08:00 | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0
35374057 |  | 3UG | Targeted UG | 42891101 | GEYSERVILLE 1101 | WDRM v3 |  | 2170 |  | 1375 | Not Yet Available | Not Yet Available | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996
35367472 |  | 3UG | Targeted UG | 152762102 | EL DORADO PH 2102 | WDRM v3 |  | 2469 |  | 780 | Not Yet Available | Not Yet Available | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0
35373630 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2420 |  | 657 | Not Yet Available | Not Yet Available | 0 | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5
35373629 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2420 |  | 657 | Not Yet Available | Not Yet Available | 0 | 5.76 | 0 | 5.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76
35367501 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2420 |  | 657 | Not Yet Available | Not Yet Available | 0 | 4.54 | 0 | 4.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54
35373626 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2028 |  | 625 | Not Yet Available | Not Yet Available | 0 | 6.2701 | 0 | 6.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701
35373625 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2028 |  | 625 | Not Yet Available | Not Yet Available | 0 | 6.2201 | 0 | 6.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201
35311626 |  | 08W | Base SH | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 3328 |  | 969 | 2024-12-18 08:00 | 2025-04-23 08:00 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0
35311596 |  | 08W | Base SH | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 3328 |  | 969 | Not Yet Available | Not Yet Available | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0
35286103 |  | 08W | Base SH | 102812101 | BIG MEADOWS 2101 | WDRM v2 |  | 3328 |  | 969 | 2024-09-24 08:00 | 2025-02-18 08:00 | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0
35373624 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2028 |  | 625 | Not Yet Available | Not Yet Available | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0
35367473 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2028 |  | 625 | Not Yet Available | Not Yet Available | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0
35390389 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 187 |  | 531 | Not Yet Available | Not Yet Available | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0
35375091 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1359 |  | 516 | Not Yet Available | Not Yet Available | 0 | 7.6799 | 0 | 7.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799
35364020 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1359 |  | 516 | Not Yet Available | Not Yet Available | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35364022 |  | 3UG | Targeted UG | 182151101 | LOS COCHES 1101 | WDRM v3 |  | 2006 |  | 462 | Not Yet Available | Not Yet Available | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0
35374455 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 1137 |  | 434 | Not Yet Available | Not Yet Available | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10
35374454 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 1137 |  | 434 | Not Yet Available | Not Yet Available | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0
35374444 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 1137 |  | 434 | Not Yet Available | Not Yet Available | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0
35392779 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 2157 |  | 429 | Not Yet Available | Not Yet Available | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0
35392778 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 2157 |  | 429 | Not Yet Available | Not Yet Available | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0
35367418 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 2157 |  | 429 | Not Yet Available | Not Yet Available | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0
35403554 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2174 |  | 398 | Not Yet Available | Not Yet Available | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95
35403553 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2174 |  | 398 | Not Yet Available | Not Yet Available | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299
35403552 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2174 |  | 398 | Not Yet Available | Not Yet Available | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31
35403551 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 2174 |  | 398 | Not Yet Available | Not Yet Available | 0 | 1.25 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25
35392114 |  | 08W | Fire Rebuild | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 2131 |  | 397 | Not Yet Available | Not Yet Available | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905
35355171 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v3 |  | 2320 |  | 394 | 2025-04-01 08:00 | 2025-08-01 08:00 | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0
35376888 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2386 |  | 379 | Not Yet Available | Not Yet Available | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701
35373599 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 1138 |  | 370 | Not Yet Available | Not Yet Available | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0
35367467 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 1138 |  | 370 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35392113 |  | 08W | Fire Rebuild | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1434 |  | 322 | Not Yet Available | Not Yet Available | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0
35387916 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1434 |  | 322 | Not Yet Available | Not Yet Available | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0
35397456 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0
35397455 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0
35396863 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0
35396862 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0
35396861 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0
35396775 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0
35390288 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 0.12973 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973
35373596 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 8.09 | 0 | 8.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09
35373595 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1788 |  | 315 | Not Yet Available | Not Yet Available | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0
35382936 |  | 3UG | Targeted UG | 42871101 | UPPER LAKE 1101 | WDRM v3 |  | 705 |  | 309 | 2025-05-12 08:00 | 2025-12-25 17:00 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0
35382934 |  | 3UG | Targeted UG | 42871101 | UPPER LAKE 1101 | WDRM v3 |  | 705 |  | 309 | 2025-04-15 08:00 | 2025-12-22 17:00 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0
35379289 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1400 |  | 301 | Not Yet Available | Not Yet Available | 0 | 6.74 | 0 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74
35375453 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1400 |  | 301 | Not Yet Available | Not Yet Available | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0
35385801 |  | 3UG | Targeted UG | 102041104 | NOTRE DAME 1104 | WDRM v3 |  | 1045 |  | 290 | Not Yet Available | Not Yet Available | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1
35401222 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2037 |  | 287 | Not Yet Available | Not Yet Available | 0 | 4.3201 | 0 | 4.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201
35401221 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2037 |  | 287 | Not Yet Available | Not Yet Available | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0
35401220 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2037 |  | 287 | Not Yet Available | Not Yet Available | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0
35373598 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2037 |  | 287 | Not Yet Available | Not Yet Available | 0 | 9.91 | 0 | 9.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91
35367466 |  | 3UG | Targeted UG | 152762101 | EL DORADO PH 2101 | WDRM v3 |  | 2037 |  | 287 | Not Yet Available | Not Yet Available | 0 | 4.1 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1
35367475 |  | 3UG | Targeted UG | 152762102 | EL DORADO PH 2102 | WDRM v3 |  | 2732 |  | 278 | Not Yet Available | Not Yet Available | 0 | 6.8875 | 0 | 6.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875
35374562 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35374561 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35374459 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35374458 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2575 |  | 273 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35373588 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1154 |  | 266 | Not Yet Available | Not Yet Available | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31
35373587 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1154 |  | 266 | Not Yet Available | Not Yet Available | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0
35367460 |  | 3UG | Targeted UG | 152481106 | BRUNSWICK 1106 | WDRM v3 |  | 1154 |  | 266 | Not Yet Available | Not Yet Available | 0 | 12.41 | 0 | 12.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41
35373706 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 2293 |  | 256 | Not Yet Available | Not Yet Available | 0 | 12.45 | 0 | 12.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45
35367522 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 2293 |  | 256 | Not Yet Available | Not Yet Available | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0
35396905 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-06-03 17:00 | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0
35396904 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-16 17:00 | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0
35396903 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-30 17:00 | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0
35396902 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-17 17:00 | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0
35396900 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-09-23 17:00 | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0
35396878 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-17 17:00 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0
35396877 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-08-11 17:00 | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0
35396876 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-17 17:00 | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0
35392777 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-17 17:00 | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0
35392776 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-21 17:00 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0
35392775 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-18 17:00 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0
35392774 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-07-16 17:00 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0
35392773 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-08-29 17:00 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0
35373637 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-10-21 17:00 | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0
35367513 |  | 3UG | Targeted UG | 43292103 | PUEBLO 2103 | WDRM v3 |  | 1224 |  | 255 | 2025-02-03 08:00 | 2025-10-22 17:00 | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0
35373580 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 8.3799 | 0 | 8.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799
35373539 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31
35373538 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0
35373537 |  | 3UG | Targeted UG | 152481102 | BRUNSWICK 1102 | WDRM v3 |  | 1649 |  | 234 | Not Yet Available | Not Yet Available | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0
35396760 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2447 |  | 233 | Not Yet Available | Not Yet Available | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992
35396699 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2447 |  | 233 | Not Yet Available | Not Yet Available | 0 | 3.3701 | 0 | 3.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701
35396698 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2447 |  | 233 | Not Yet Available | Not Yet Available | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0
35367511 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2447 |  | 233 | Not Yet Available | Not Yet Available | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0
35376889 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 1765 |  | 218 | Not Yet Available | Not Yet Available | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0
35367526 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 1765 |  | 218 | Not Yet Available | Not Yet Available | 0 | 13.5701 | 0 | 13.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701
35367500 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 2060 |  | 211 | Not Yet Available | Not Yet Available | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299
35404267 |  | 3UG | Targeted UG | 167351102 | PINE GROVE 1102 | WDRM v3 |  | 2136 |  | 204 | Not Yet Available | Not Yet Available | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0
35403850 |  | 3UG | Targeted UG | 25442101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13
35403849 |  | 3UG | Targeted UG | 25442101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 4.31 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31
35403848 |  | 3UG | Targeted UG | 25442101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0
35403847 |  | 3UG | Targeted UG | 25442101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0
35243446 |  | 08W | Base SH | 42291101 | OLEMA 1101 | WDRM v2 |  | 2644 |  | 2439 | Not Yet Available | Not Yet Available | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0
35237937 |  | 2BP | Other | 83622103 | CAMP EVERS 2103 | WDRM v2 |  | 2595 |  | 1319 | Not Yet Available | Not Yet Available | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0
35382933 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 5.24 | 0 | 5.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24
35379382 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 700 |  | 199 | Not Yet Available | Not Yet Available | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0
35375184 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | N/A |  | 193 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35375183 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | N/A |  | 193 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35375182 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | N/A |  | 193 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35375181 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | N/A |  | 193 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35376642 |  | 3UG | Targeted UG | 152301102 | BONNIE NOOK 1102 | WDRM v3 |  | 2087 |  | 192 | Not Yet Available | Not Yet Available | 0 | 9.06 | 0 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06
35376641 |  | 3UG | Targeted UG | 152301102 | BONNIE NOOK 1102 | WDRM v3 |  | 2087 |  | 192 | Not Yet Available | Not Yet Available | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0
35376640 |  | 3UG | Targeted UG | 152301102 | BONNIE NOOK 1102 | WDRM v3 |  | 2087 |  | 192 | Not Yet Available | Not Yet Available | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0
35378690 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 328 |  | 182 | 2026-02-02 08:00 | 2026-12-04 17:00 | 0 | 4.46 | 0 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46
35378688 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 328 |  | 182 | 2026-02-02 08:00 | 2026-12-04 17:00 | 0 | 10.89 | 0 | 10.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89
35378687 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 328 |  | 182 | 2025-02-03 08:00 | 2025-11-27 17:00 | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0
35377437 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 328 |  | 182 | 2025-02-03 08:00 | 2025-11-27 17:00 | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0
35399836 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | Not Yet Available | Not Yet Available | 0 | 5.387 | 0 | 5.387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387
35399835 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | Not Yet Available | Not Yet Available | 0 | 2.342 | 0 | 2.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342
35373525 |  | 3UG | Targeted UG | 152181101 | FORESTHILL 1101 | WDRM v3 |  | 1865 |  | 179 | Not Yet Available | Not Yet Available | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84
35375099 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1509 |  | 178 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35375096 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1509 |  | 178 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75
35375095 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1509 |  | 178 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35375094 |  | 3UG | Targeted UG | 182082103 | LOS OSITOS 2103 | WDRM v3 |  | 1509 |  | 178 | Not Yet Available | Not Yet Available | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0
35373621 |  | 3UG | Targeted UG | 152762102 | EL DORADO PH 2102 | WDRM v3 |  | 2512 |  | 176 | Not Yet Available | Not Yet Available | 0 | 7.31 | 0 | 7.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31
35367470 |  | 3UG | Targeted UG | 152762102 | EL DORADO PH 2102 | WDRM v3 |  | 2512 |  | 176 | Not Yet Available | Not Yet Available | 0 | 6.71 | 0 | 6.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71
35383757 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 1206 |  | 164 | Not Yet Available | Not Yet Available | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1
35383756 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 1206 |  | 164 | Not Yet Available | Not Yet Available | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1
35383755 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 1206 |  | 164 | Not Yet Available | Not Yet Available | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0
35383754 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 1206 |  | 164 | Not Yet Available | Not Yet Available | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0
35383753 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 1206 |  | 164 | Not Yet Available | Not Yet Available | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1
35373535 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2289 |  | 158 | Not Yet Available | Not Yet Available | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04
35373534 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2289 |  | 158 | Not Yet Available | Not Yet Available | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0
35367503 |  | 3UG | Targeted UG | 103031101 | ORO FINO 1101 | WDRM v3 |  | 2289 |  | 158 | Not Yet Available | Not Yet Available | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0
35374203 |  | 3UG | Targeted UG | 102041104 | NOTRE DAME 1104 | WDRM v3 |  | 73 |  | 155 | Not Yet Available | Not Yet Available | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0
35402643 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 1764 |  | 147 | Not Yet Available | Not Yet Available | 0 | 2.4561 | 0 | 2.4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561
35396761 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 1764 |  | 147 | Not Yet Available | Not Yet Available | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64
35373707 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 1764 |  | 147 | Not Yet Available | Not Yet Available | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0
35372460 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 1764 |  | 147 | Not Yet Available | Not Yet Available | 0 | 7.4299 | 0 | 7.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299
35367515 |  | 3UG | Targeted UG | 163692102 | SALT SPRINGS 2102 | WDRM v3 |  | 2620 |  | 133 | Not Yet Available | Not Yet Available | 0 | 6.6799 | 0 | 6.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799
35375515 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | Not Yet Available | Not Yet Available | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35375514 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | Not Yet Available | Not Yet Available | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35375513 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | Not Yet Available | Not Yet Available | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0
35375512 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | Not Yet Available | Not Yet Available | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0
35375509 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 644 |  | 132 | Not Yet Available | Not Yet Available | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0
35401013 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | Not Yet Available | Not Yet Available | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0
35401012 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | Not Yet Available | Not Yet Available | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0
35401011 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | Not Yet Available | Not Yet Available | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0
35382932 |  | 3UG | Targeted UG | 254452101 | MARIPOSA 2101 | WDRM v3 |  | 679 |  | 126 | Not Yet Available | Not Yet Available | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0
35373529 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 |  | 1284 |  | 124 | Not Yet Available | Not Yet Available | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0
35367412 |  | 3UG | Targeted UG | 153661104 | APPLE HILL 1104 | WDRM v3 |  | 1284 |  | 124 | Not Yet Available | Not Yet Available | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0
35374059 |  | 3UG | Targeted UG | 162161101 | ELECTRA 1101 | WDRM v3 |  | 2349 |  | 118 | Not Yet Available | Not Yet Available | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0
35377525 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1484 |  | 116 | Not Yet Available | Not Yet Available | 0 | 6.9701 | 0 | 6.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701
35375450 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1484 |  | 116 | Not Yet Available | Not Yet Available | 0 | 10.66 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66
35375449 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1484 |  | 116 | Not Yet Available | Not Yet Available | 0 | 10.85 | 0 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85
35379381 |  | 3UG | Targeted UG | 12022212 | CLAYTON 2212 | WDRM v3 |  | 400 |  | 115 | Not Yet Available | Not Yet Available | 0 | 10.4 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4
35383305 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 2468 |  | 107 | Not Yet Available | Not Yet Available | 0 | 4.99 | 0 | 4.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99
35367524 |  | 3UG | Targeted UG | 163201101 | WEST POINT 1101 | WDRM v3 |  | 2468 |  | 107 | Not Yet Available | Not Yet Available | 0 | 14.3201 | 0 | 14.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201
35373597 |  | 3UG | Targeted UG | 42711101 | CALISTOGA 1101 | WDRM v3 |  | 1005 |  | 105 | Not Yet Available | Not Yet Available | 0 | 5.0201 | 0 | 5.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201
35367464 |  | 3UG | Targeted UG | 42711101 | CALISTOGA 1101 | WDRM v3 |  | 1005 |  | 105 | Not Yet Available | Not Yet Available | 0 | 9.0299 | 0 | 9.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299
35404355 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | Not Yet Available | Not Yet Available | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0
35404354 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | Not Yet Available | Not Yet Available | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0
35404353 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | Not Yet Available | Not Yet Available | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0
35367516 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1254 |  | 101 | Not Yet Available | Not Yet Available | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0
35362666 |  | 3UG | Targeted UG | 12022212 | CLAYTON 2212 | WDRM v3 |  | 2561 |  | 100 | Not Yet Available | Not Yet Available | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992
35409203 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 314 |  | 99 | Not Yet Available | Not Yet Available | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4
35418379 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2810 |  | 98 | Not Yet Available | Not Yet Available | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0
35417148 |  | 3UG | Targeted UG |  |  | WDRM v3 |  | 1301 |  | 97 | Not Yet Available | Not Yet Available | 0 | 8.56 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56
35417144 |  | 3UG | Targeted UG |  |  | WDRM v3 |  | 1301 |  | 97 | Not Yet Available | Not Yet Available | 0 | 10.7 | 0 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7
35417117 |  | 3UG | Targeted UG |  |  | WDRM v3 |  | 1301 |  | 97 | Not Yet Available | Not Yet Available | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0
35417110 |  | 3UG | Targeted UG |  |  | WDRM v3 |  | 1301 |  | 97 | Not Yet Available | Not Yet Available | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0
35362685 |  | 08W | Base SH | 162821701 | STANISLAUS 1701 | WDRM v3 |  | 56 |  | 95 | Not Yet Available | Not Yet Available | 0.42708 | 0 | 0 | 0.42708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708
35372463 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2207 |  | 94 | 2026-01-08 08:00 | 2026-07-20 17:00 | 0.020076 | 1.99 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01
35395930 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 |  | 91 | Not Yet Available | Not Yet Available | 0 | 0.369 | 0 | 0.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369
35395929 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 |  | 91 | Not Yet Available | Not Yet Available | 0 | 0.057 | 0 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057
35395928 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 |  | 91 | Not Yet Available | Not Yet Available | 0 | 1.937 | 0 | 1.937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937
35372464 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2407 |  | 91 | Not Yet Available | Not Yet Available | 0 | 6.553 | 0 | 6.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553
35418366 |  | 3UG | Targeted UG | 152431102 | SHADY GLEN 1102 | WDRM v3 |  | 1378 |  | 89 | Not Yet Available | Not Yet Available | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0
35418361 |  | 3UG | Targeted UG | 152431102 | SHADY GLEN 1102 | WDRM v3 |  | 1378 |  | 89 | Not Yet Available | Not Yet Available | 0 | 6.601 | 0 | 6.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601
35376559 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 1361 |  | 87 | Not Yet Available | Not Yet Available | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21
35376558 |  | 3UG | Targeted UG | 43432105 | SILVERADO 2105 | WDRM v3 |  | 1361 |  | 87 | Not Yet Available | Not Yet Available | 0 | 10.25 | 0 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25
35383758 |  | 3UG | Targeted UG | 163201102 | WEST POINT 1102 | WDRM v3 |  | 2247 |  | 80 | Not Yet Available | Not Yet Available | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0
35409205 |  | 3UG | Targeted UG | 152431101 | SHADY GLEN 1101 | WDRM v3 |  | 2201 |  | 71 | Not Yet Available | Not Yet Available | 0 | 15.2 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2
35391723 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | Not Yet Available | Not Yet Available | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799
35391722 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | Not Yet Available | Not Yet Available | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799
35391721 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | Not Yet Available | Not Yet Available | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0
35391473 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 1666 |  | 68 | Not Yet Available | Not Yet Available | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0
35409217 |  | 3UG | Targeted UG | 103521102 | OREGON TRAIL 1102 | WDRM v3 |  | 1773 |  | 64 | Not Yet Available | Not Yet Available | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7
35409215 |  | 3UG | Targeted UG | 103521102 | OREGON TRAIL 1102 | WDRM v3 |  | 1773 |  | 64 | Not Yet Available | Not Yet Available | 0 | 5.1 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1
35373530 |  | 3UG | Targeted UG | 153662102 | APPLE HILL 2102 | WDRM v3 |  | 1505 |  | 63 | Not Yet Available | Not Yet Available | 0 | 15.51 | 0 | 15.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51
35404349 |  | 3UG | Targeted UG | 162161101 | ELECTRA 1101 | WDRM v3 |  | 1548 |  | 62 | Not Yet Available | Not Yet Available | 0 | 4.47 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47
35376890 |  | 3UG | Targeted UG | 162161101 | ELECTRA 1101 | WDRM v3 |  | 1548 |  | 62 | Not Yet Available | Not Yet Available | 0 | 7.09 | 0 | 7.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09
35372462 |  | 3UG | Targeted UG | 162161101 | ELECTRA 1101 | WDRM v3 |  | 1548 |  | 62 | Not Yet Available | Not Yet Available | 0.019886 | 4.85 | 0 | 4.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699
35373628 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2763 |  | 61 | Not Yet Available | Not Yet Available | 0 | 8.7299 | 0 | 8.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299
35367504 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2763 |  | 61 | Not Yet Available | Not Yet Available | 0 | 9.35 | 0 | 9.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35
35418375 |  | 3UG | Targeted UG | 162821702 | STANISLAUS 1702 | WDRM v3 |  | 2670 |  | 60 | Not Yet Available | Not Yet Available | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0
35385804 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 792 |  | 59 | Not Yet Available | Not Yet Available | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29
35385803 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 792 |  | 59 | Not Yet Available | Not Yet Available | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0
35418305 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 904 |  | 58 | Not Yet Available | Not Yet Available | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65
35418255 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 904 |  | 58 | Not Yet Available | Not Yet Available | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0
35417127 |  | 3UG | Targeted UG | 153082106 | PLACERVILLE 2106 | WDRM v3 |  | 904 |  | 58 | Not Yet Available | Not Yet Available | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0
35364784 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 2537 |  | 57 | Not Yet Available | Not Yet Available | 0 | 7.1701 | 0 | 7.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701
35363720 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 2537 |  | 57 | Not Yet Available | Not Yet Available | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0
35363559 |  | 3UG | Targeted UG | 102971111 | SYCAMORE CREEK 1111 | WDRM v3 |  | 2537 |  | 57 | Not Yet Available | Not Yet Available | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0
35409202 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 915 |  | 56 | Not Yet Available | Not Yet Available | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2
35375452 |  | 3UG | Targeted UG | 152201101 | PIKE CITY 1101 | WDRM v3 |  | 1710 |  | 52 | Not Yet Available | Not Yet Available | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0
35374570 |  | 3UG | Targeted UG | 153132102 | NARROWS 2102 | WDRM v3 |  | 658 |  | 46 | Not Yet Available | Not Yet Available | 0 | 7.2799 | 0 | 7.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799
35374569 |  | 3UG | Targeted UG | 102211102 | BUCKS CREEK 1102 | WDRM v3 |  | 378 |  | 45 | Not Yet Available | Not Yet Available | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004
35374567 |  | 3UG | Targeted UG | 102211102 | BUCKS CREEK 1102 | WDRM v3 |  | 378 |  | 45 | Not Yet Available | Not Yet Available | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996
35374566 |  | 3UG | Targeted UG | 102211102 | BUCKS CREEK 1102 | WDRM v3 |  | 378 |  | 45 | Not Yet Available | Not Yet Available | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004
35374564 |  | 3UG | Targeted UG | 102211102 | BUCKS CREEK 1102 | WDRM v3 |  | 378 |  | 45 | Not Yet Available | Not Yet Available | 0 | 6.79 | 1.76 | 8.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55
35374563 |  | 3UG | Targeted UG | 102211102 | BUCKS CREEK 1102 | WDRM v3 |  | 378 |  | 45 | Not Yet Available | Not Yet Available | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21
35374443 |  | 3UG | Targeted UG | 152101102 | ALLEGHANY 1102 | WDRM v3 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 6.7701 | 0 | 6.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701
35374208 |  | 3UG | Targeted UG | 152101102 | ALLEGHANY 1102 | WDRM v3 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 4.89 | 0 | 4.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89
35374206 |  | 3UG | Targeted UG | 152101102 | ALLEGHANY 1102 | WDRM v3 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0
35374205 |  | 3UG | Targeted UG | 152101102 | ALLEGHANY 1102 | WDRM v3 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 6.24 | 0 | 6.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24
35374204 |  | 3UG | Targeted UG | 152101102 | ALLEGHANY 1102 | WDRM v3 |  | 1700 |  | 41 | Not Yet Available | Not Yet Available | 0 | 6.7201 | 0 | 6.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201
35377520 |  | 3UG | Targeted UG | 43141101 | MIDDLETOWN 1101 | WDRM v3 |  | 328 |  | 38 | 2026-02-02 08:00 | 2026-12-04 17:00 | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701
35374202 |  | 3UG | Targeted UG | 102041104 | NOTRE DAME 1104 | WDRM v3 |  | 1043 |  | 37 | Not Yet Available | Not Yet Available | 0 | 4.6701 | 0 | 4.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701
35374200 |  | 3UG | Targeted UG | 102041104 | NOTRE DAME 1104 | WDRM v3 |  | 1043 |  | 37 | Not Yet Available | Not Yet Available | 0 | 8.04 | 0 | 8.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04
35385806 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1235 |  | 33 | Not Yet Available | Not Yet Available | 0 | 6.69 | 0 | 6.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69
35385805 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1235 |  | 33 | 2026-03-17 08:00 | 2026-09-14 17:00 | 0 | 10.74 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74
35367335 |  | 3UG | Targeted UG | 152301101 | BONNIE NOOK 1101 | WDRM v3 |  | 1526 |  | 20 | Not Yet Available | Not Yet Available | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0
35365064 |  | 3UG | Targeted UG | 152301101 | BONNIE NOOK 1101 | WDRM v3 |  | 1526 |  | 20 | Not Yet Available | Not Yet Available | 0 | 10.34 | 0.22992 | 10.5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699
35373634 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2451 |  | 17 | Not Yet Available | Not Yet Available | 0 | 4.4299 | 0 | 4.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299
35373632 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2451 |  | 17 | Not Yet Available | Not Yet Available | 0 | 10.2299 | 0 | 10.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299
35367508 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2451 |  | 17 | Not Yet Available | Not Yet Available | 0 | 5.94 | 0 | 5.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94
35367507 |  | 3UG | Targeted UG | 103031102 | ORO FINO 1102 | WDRM v3 |  | 2451 |  | 17 | Not Yet Available | Not Yet Available | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04
35243445 |  | 08W | Base SH | 42291101 | OLEMA 1101 | WDRM v2 |  | 2360 |  | 3015 | Not Yet Available | Not Yet Available | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0
35385802 |  | 3UG | Targeted UG | 12022212 | CLAYTON 2212 | WDRM v3 |  | 377 |  | 15 | Not Yet Available | Not Yet Available | 0 | 9.6 | 0 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6
35376891 |  | 3UG | Targeted UG | 43432104 | SILVERADO 2104 | WDRM v3 |  | 1235 |  | 14 | Not Yet Available | Not Yet Available | 0 | 4.4 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4
35373708 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2361 |  | 11 | Not Yet Available | Not Yet Available | 0 | 3.73 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73
35372465 |  | 3UG | Targeted UG | 103271101 | ANTLER 1101 | WDRM v3 |  | 2361 |  | 11 | Not Yet Available | Not Yet Available | 0 | 11.84 | 0 | 11.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84
35372258 |  | 3UG | Targeted UG | 252691104 | INDIAN FLAT 1104 | WDRM v3 |  | 555 |  | 10 | Not Yet Available | Not Yet Available | 0 | 8.892 | 0 | 8.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892
35372257 |  | 3UG | Targeted UG | 252691104 | INDIAN FLAT 1104 | WDRM v3 |  | 555 |  | 10 | Not Yet Available | Not Yet Available | 0 | 9.808 | 0 | 9.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808
35396763 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 2334 |  | 6 | Not Yet Available | Not Yet Available | 0 | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88
35342338 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2359 |  | 1314 | Not Yet Available | Not Yet Available | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0
35396762 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 2334 |  | 6 | Not Yet Available | Not Yet Available | 0.07 | 2.91 | 0 | 2.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98
35342337 |  | 08W | Fire Rebuild | 82841102 | BIG BASIN 1102 | WDRM v2 |  | 2359 |  | 1314 | Not Yet Available | Not Yet Available | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0
35372259 |  | 3UG | Targeted UG | 167351101 | PINE GROVE 1101 | WDRM v3 |  | 2334 |  | 6 | Not Yet Available | Not Yet Available | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84
35325226 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 2320 |  | 394 | 2025-06-11 08:00 | 2025-10-15 08:00 | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0
35325225 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 2320 |  | 394 | Not Yet Available | Not Yet Available | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0
35325224 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 2320 |  | 394 | Not Yet Available | Not Yet Available | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0
35294729 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 2320 |  | 394 | Not Yet Available | Not Yet Available | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0
35294728 |  | 08W | Base SH | 103732101 | PIT NO 3 2101 | WDRM v2 |  | 1816 |  | 326 | Not Yet Available | Not Yet Available | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0
35280505 |  | 30A | Other | 103451101 | Keswick 1101 | WDRM v2 |  | 1614 |  | 43 | Not Yet Available | Not Yet Available | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879
35245152 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-02 08:00 | 2025-06-23 17:00 | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0
35245141 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-02 08:00 | 2025-06-12 17:00 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0
35244699 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-02 08:00 | 2025-05-26 17:00 | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0
35244698 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-02 08:00 | 2025-06-12 17:00 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0
35236989 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-03 08:00 | 2025-07-01 17:00 | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0
35235704 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-03 08:00 | 2025-06-13 17:00 | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0
35235701 |  | 08W | Fire Rebuild | 103221101 | KANAKA 1101 | WDRM v2 |  | 1480 |  | 212 | 2025-04-03 08:00 | 2025-07-11 17:00 | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0
35320466 |  | 08W | Base SH | 192171103 | WILLOW CREEK 1103 | WDRM v2 |  | 1474 |  | 938 | Not Yet Available | Not Yet Available | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0
35338403 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 |  | 380 |  | 3890 | Not Yet Available | Not Yet Available | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35320465 |  | 08W | Base SH | 103461101 | PANORAMA 1101 | WDRM v2 |  | 380 |  | 3890 | Not Yet Available | Not Yet Available | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35384087 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1033 |  | 711 | Not Yet Available | Not Yet Available | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0
35329015 |  | 08W | Base SH | 103091102 | CLARK ROAD 1102 | WDRM v2 |  | 1033 |  | 711 | Not Yet Available | Not Yet Available | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0
35227033 |  | 08W | Base SH | 43292102 | PUEBLO 2102 | WDRM v2 |  | 951 |  | 338 | Not Yet Available | Not Yet Available | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0
35235674 |  | 08W | Fire Rebuild | 103751102 | BIG BEND 1102 | WDRM v2 |  | 865 |  | 187 | 2025-04-02 08:00 | 2025-05-23 17:00 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0
35297984 |  | 08W | Fire Rebuild | 103561101 | STILLWATER 1101 | WDRM v2 |  | 851 |  | 2266 | Not Yet Available | Not Yet Available | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201
35342150 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 739 |  | 313 | Not Yet Available | Not Yet Available | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0
35337013 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 724 |  | 1928 | 2025-06-13 08:00 | 2025-12-19 16:00 | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0
35320459 |  | 08W | Base SH | 63801105 | JAMESON 1105 | WDRM v2 |  | 724 |  | 1928 | Not Yet Available | Not Yet Available | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0
35342310 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 0 | 1.357 | 0 | 1.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357
35342308 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 0 | 2.997 | 0 | 2.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997
35342307 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 0 | 2.252 | 0 | 2.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252
35335289 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 0 | 1.5775 | 0 | 1.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775
35335288 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0
35321445 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | 2024-12-06 08:00 | 2025-02-27 08:00 | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0
35312554 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 691 |  | 368 | Not Yet Available | Not Yet Available | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0
35339663 |  | 08W | Base SH | 152571101 | HORSESHOE 1101 | WDRM v2 |  | 661 |  | 2556 | 2025-06-10 08:00 | 2025-12-16 16:00 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0
35274596 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 605 |  | 565 | 2024-12-06 08:00 | 2025-06-16 17:00 | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0
35250572 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 605 |  | 565 | 2025-05-26 08:00 | 2025-12-04 17:00 | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0
35317937 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-02-28 08:00 | 2025-08-13 17:00 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
35317936 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-05-01 08:00 | 2025-10-16 16:00 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0
35317935 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-05-16 08:00 | 2025-10-21 16:00 | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0
35317934 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-03-17 08:00 | 2025-08-20 16:00 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0
35317932 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | Not Yet Available | Not Yet Available | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0
35317931 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-07-16 08:00 | 2025-12-19 17:00 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0
35317930 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-05-16 08:00 | 2025-10-21 16:00 | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0
35317929 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-05-16 08:00 | 2025-10-21 16:00 | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0
35317928 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-04-29 08:00 | 2025-10-03 17:00 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0
35250574 |  | 08W | Base SH | 43211101 | HARTLEY 1101 | WDRM v2 |  | 593 |  | 1213 | 2025-07-16 08:00 | 2025-12-19 17:00 | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0
35332864 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 |  | 590 |  | 2901 | 2025-04-09 07:00 | 2025-05-16 15:00 | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0
35332863 |  | 08W | Base SH | 103441103 | JESSUP 1103 | WDRM v2 |  | 590 |  | 2901 | 2025-05-23 08:00 | 2025-08-13 17:00 | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0
35342318 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | Not Yet Available | Not Yet Available | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0
35342317 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | Not Yet Available | Not Yet Available | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0
35342316 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | Not Yet Available | Not Yet Available | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0
35342315 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2025-04-15 08:00 | 2025-09-26 17:00 | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0
35342314 |  | 08W | Base SH | 252931102 | TEJON 1102 | WDRM v2 |  | 583 |  | 219 | 2024-10-16 08:00 | 2025-04-04 17:00 | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0
35364448 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0
35364446 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0.057008 | 2.5381 | 0 | 2.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951
35364440 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689
35364336 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 1.8561 | 0 | 1.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561
35364333 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 2.8131 | 0 | 2.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131
35364332 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0
35334465 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2025-05-23 08:00 | 2025-11-05 17:00 | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0
35334464 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | 2025-04-23 08:00 | 2025-10-06 17:00 | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0
35312556 |  | 08W | Base SH | 102541101 | VOLTA 1101 | WDRM v2 |  | 580 |  | 704 | Not Yet Available | Not Yet Available | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0
35335283 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2025-05-13 08:00 | 2025-07-17 16:00 | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0
35335282 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2025-04-15 08:00 | 2025-07-17 16:00 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0
35335281 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2025-06-11 08:00 | 2025-06-19 16:00 | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0
35332959 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2025-06-24 08:00 | 2025-10-08 16:00 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0
35320454 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 568 |  | 3055 | 2025-05-14 08:00 | 2025-07-24 16:00 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0
35226859 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2025-02-24 08:00 | 2025-07-14 17:00 | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0
35226858 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 474 |  | 102 | 2025-02-10 08:00 | 2025-06-30 17:00 | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0
35301110 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2025-07-14 08:00 | 2025-10-31 17:00 | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0
35227027 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | Not Yet Available | Not Yet Available | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0
35226623 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2025-03-19 08:00 | 2025-04-30 08:00 | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0
35226622 |  | 08W | Base SH | 43141101 | MIDDLETOWN 1101 | WDRM v2 |  | 468 |  | 13 | 2025-03-19 08:00 | 2025-07-15 17:00 | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0
35274594 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | Not Yet Available | Not Yet Available | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0
35274592 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2025-04-30 08:00 | 2025-11-11 17:00 | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0
35274591 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | Not Yet Available | Not Yet Available | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0
35250571 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2025-04-30 08:00 | 2025-10-28 17:00 | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0
35250570 |  | 08W | Base SH | 254452101 | MARIPOSA 2101 | WDRM v2 |  | 428 |  | 249 | 2025-05-15 08:00 | 2025-11-19 17:00 | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0
35330242 |  | 08W | Base SH | 43191101 | REDBUD 1101 | WDRM v2 |  | 423 |  | 127 | Not Yet Available | Not Yet Available | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0
35285245 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 396 |  | 2321 | 2025-02-18 08:00 | 2025-04-30 08:00 | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0
35254077 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 396 |  | 2321 | 2025-06-11 08:00 | 2025-08-21 08:00 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0
35337012 |  | 08W | Base SH | 103441102 | JESSUP 1102 | WDRM v2 |  | 389 |  | 1853 | Not Yet Available | Not Yet Available | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0
35225593 |  | 08W | Base SH | 12022212 | CLAYTON 2212 | WDRM v2 |  | 377 |  | 15 | 2025-01-23 08:00 | 2025-05-13 17:00 | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0
35226625 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 340 |  | 308 | Not Yet Available | Not Yet Available | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0
35349642 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | Not Yet Available | Not Yet Available | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0
35285250 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-02-17 08:00 | 2025-08-29 17:00 | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0
35285248 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-02-10 08:00 | 2025-08-22 17:00 | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0
35285247 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-01-01 | 2025-02-27 | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0
35283349 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-04-08 08:00 | 2025-08-07 17:00 | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0
35283348 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-04-04 08:00 | 2025-09-17 17:00 | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0
35283347 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-03-04 08:00 | 2025-08-15 17:00 | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0
35283344 |  | 08W | Base SH | 42871101 | UPPER LAKE 1101 | WDRM v2 |  | 335 |  | 35 | 2025-05-13 08:00 | 2025-08-14 17:00 | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0
35278889 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 330 |  | 734 | 2025-07-10 08:00 | 2025-12-02 17:00 | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0
35254242 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 330 |  | 734 | 2025-07-04 08:00 | 2025-12-10 17:00 | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0
35320445 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 307 |  | 2847 | 2025-06-05 08:00 | 2025-10-01 17:00 | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0
35259514 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 |  | 301 |  | 3101 | Not Yet Available | Not Yet Available | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0
35278090 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2025-07-31 08:00 | 2025-12-23 17:00 | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0
35277934 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2025-07-17 08:00 | 2025-12-02 17:00 | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0
35277933 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2025-07-17 08:00 | 2025-12-02 17:00 | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0
35254241 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2025-07-03 08:00 | 2025-12-30 17:00 | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0
35254240 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 274 |  | 614 | 2024-10-02 08:00 | 2025-03-25 17:00 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0
35320446 |  | 08W | Base SH | 183041102 | BUELLTON 1102 | WDRM v2 |  | 269 |  | 2607 | Not Yet Available | Not Yet Available | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0
35331302 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 262 |  | 3263 | 2025-03-05 08:00 | 2025-04-02 08:00 | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0
35331301 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 262 |  | 3263 | 2025-04-16 08:00 | 2025-05-13 08:00 | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0
35330816 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 262 |  | 3263 | 2025-09-08 08:00 | 2025-09-15 08:00 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0
35332219 |  | 08W | Base SH | 102781101 | ELK CREEK 1101 | WDRM v2 |  | 206 |  | 1350 | Not Yet Available | Not Yet Available | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0
35278093 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 163 |  | 569 | Not Yet Available | Not Yet Available | 0 | 0.41496 | 0 | 0.41496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496
35331304 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 143 |  | 3058 | 2025-06-23 08:00 | 2025-08-12 08:00 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0
35331303 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 143 |  | 3058 | 2025-05-05 08:00 | 2025-06-19 16:00 | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0
35311894 |  | 08W | Base SH | 103261103 | ANDERSON 1103 | WDRM v2 |  | 143 |  | 3058 | 2025-03-04 08:00 | 2025-03-27 16:00 | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0
35404729 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | Not Yet Available | Not Yet Available | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0
35404728 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | Not Yet Available | Not Yet Available | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0
35404727 |  | 08W | Base SH | 63601108 | VACAVILLE 1108 | WDRM v2 |  | 122 |  | 491 | Not Yet Available | Not Yet Available | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0
35243447 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 |  | 100 |  | 2704 | Not Yet Available | Not Yet Available | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0
35259513 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 |  | 99 |  | 2481 | Not Yet Available | Not Yet Available | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0
35243448 |  | 08W | Base SH | 103351104 | DESCHUTES 1104 | WDRM v2 |  | 99 |  | 2481 | Not Yet Available | Not Yet Available | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0
35290510 |  | 08W | Base SH | 42281105 | POTTER VALLEY P H 1105 | WDRM v2 |  | 75 |  | 573 | 2025-05-05 08:00 | 2025-08-21 17:00 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0
35290514 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 74 |  | 1256 | 2025-02-10 08:00 | 2025-08-22 17:00 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0
35290513 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 74 |  | 1256 | 2025-02-10 08:00 | 2025-08-22 17:00 | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0
35290512 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 74 |  | 1256 | 2025-02-11 08:00 | 2025-08-25 17:00 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0
35290511 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 74 |  | 1256 | 2025-02-11 08:00 | 2025-07-18 17:00 | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0
35254072 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 74 |  | 1256 | 2025-03-03 08:00 | 2025-07-10 17:00 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0
35320443 |  | 08W | Base SH | 63801102 | JAMESON 1102 | WDRM v2 |  | 67 |  | 1581 | Not Yet Available | Not Yet Available | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
35277931 |  | 08W | Base SH | 254151101 | AUBERRY 1101 | WDRM v2 |  | 63 |  | 2126 | 2025-07-15 08:00 | 2025-12-30 17:00 | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0
35249874 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | 2025-03-11 08:00 | 2025-08-27 17:00 | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0
35249873 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | 2025-01-01 08:00 | 2025-08-18 17:00 | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0
35240163 |  | 08W | Base SH | 254432104 | COARSEGOLD 2104 | WDRM v2 |  | 61 |  | 1416 | Not Yet Available | Not Yet Available | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0
35311135 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-06-03 08:00 | 2025-10-23 17:00 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0
35311134 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-06-02 08:00 | 2025-10-22 17:00 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0
35311133 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-04-22 08:00 | 2025-09-11 17:00 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0
35311132 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-08-05 08:00 | 2025-12-25 17:00 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0
35311131 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-08-05 08:00 | 2025-12-25 17:00 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0
35310715 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-05-27 08:00 | 2025-10-16 17:00 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0
35310714 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-05-14 08:00 | 2025-10-03 17:00 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0
35310713 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-06-06 08:00 | 2025-10-28 17:00 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0
35250579 |  | 08W | Base SH | 42281104 | POTTER VALLEY P H 1104 | WDRM v2 |  | 60 |  | 2459 | 2025-08-05 08:00 | 2025-12-25 17:00 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0
35231622 |  | 08W | Base SH | 43361102 | HIGHLANDS 1102 | WDRM v2 |  | 27 |  | 29 | Not Yet Available | Not Yet Available | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0
35217270 |  | 08W | Base SH | 43311101 | KONOCTI 1102 | WDRM v2 |  | 9 |  | 735 | 2025-03-17 08:00 | 2025-06-09 17:00 | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0
35342302 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | 2025-06-23 08:00 | 2025-09-09 08:00 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0
35332878 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | 2025-05-26 08:00 | 2025-08-12 17:00 | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0
35332876 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | 2025-06-02 08:00 | 2025-08-12 16:00 | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0
35332874 |  | 08W | Base SH | 153701104 | LINCOLN 1104 | WDRM v2 |  | 693 |  | 3098 | 2025-01-31 08:00 | 2025-09-09 16:00 | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0
Note on E125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tekeste, Merih - do we have the circuit name / iD even though this isn't scoped?

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Idle Facilities | Removal of Primary Conductor in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
MAT Code
MAT Code | Description
06A | Feeder Projects Associated with Substation Capacity
08W | System Hardening Wildfire Resiliency Projects
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
95F | Electric Distribution Major Emergency
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Division
Division Acronym | Division Name
CC | Central Coast
CV | Central Valley
DA | De Anza
DI | Diablo
EB | East Bay
FR | Fresno
HB | Humboldt
KE | Kern
LP | Los Padres
NB | North Bay
NV | North Valley
PN | Peninsula
SA | Sacramento
SF | San Francisco
SI | Sierra
SJ | San Jose
SO | Sonoma
ST | Stockton
YO | Yosemite
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Mean Risk | Summation of the total risk of all pixels (100-meter x 100-meter cell) linked to a circuit segment, divided by the total number of pixels.
Feasibility score by CPZ | Cost multiplier indicating the difficulty of undergrounding the circuit segment (Circuit Protection Zone (CPZ)) based on presence of hard rock, water crossing, and gradient. The scale ranges from 1 to 3, with 3 being most challenging.