## Summary Risk Rank table (hidden)
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534 |  |  |  | 588 |  |  |  | 683 |  |  |  | 881 |  |  |  | 2686
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio
Top Risk-Ranked Circuit Segments |  | 345.014 |  | 345.014 | 64.57% | 456.5475 |  | 456.5475 | 77.61% | 650.929 |  | 650.929 | 95.31% | 878.5985 |  | 878.5985 | 99.73% | 2331.089 | 0 | 2331.089 | 86.77%
Other High Risk | Fire Rebuild | 61.1509 | 77.7009 | 138.8519 | 25.99% | 7.1206 | 98.7981 | 105.9187 | 18.01% | 1.76 |  | 1.76 | 0.2577% | 1.9691 |  | 1.9691 | 0.2235% | 72.0008 | 176.4991 | 248.4998 | 9.25%
| PSPS | 46.6722 |  | 46.6722 | 8.735% | 15.8209 |  | 15.8209 | 2.689% | 1.0381 |  | 1.0381 | 0.152% |  |  | 0 | 0% | 63.5311 | 0 | 63.5311 | 2.365%
| PSS Identified | 2.5902 |  | 2.5902 | 0.4847% | 0.57576 |  | 0.57576 | 0.09788% |  |  | 0 | 0% |  |  | 0 | 0% | 3.1659 | 0 | 3.1659 | 0.1178%
| UG System Hardening | 1.2126 |  | 1.2126 | 0.2269% | 4.1006 |  | 4.1006 | 0.6971% | 29.2414 |  | 29.2414 | 4.281% |  |  | 0 | 0% | 34.5545 | 0 | 34.5545 | 1.286%
Other |  |  |  | 0 | 0% | 5.2831 |  | 5.2831 | 0.8981% | 0.015341 |  | 0.015341 | 0.002246% | 0.37879 |  | 0.37879 | 0.043% | 5.6773 | 0 | 5.6773 | 0.2113%
Total |  | 456.6398 | 77.7009 | 534.3408 | 100% | 489.4485 | 98.7981 | 588.2466 | 100% | 682.9839 | 0 | 682.9839 | 100% | 880.9464 | 0 | 880.9464 | 100% | 2510.0186 | 176.4991 | 2686.5176 | 100%
DO NOT INCLUDE: *LTIP Model Application V2 miles are categorized using '2021-2023 Risk Rank (V2)' from Master 01-23_workplan_conf *LTIP Model Application V3 miles are categorized using columns "2022 Risk Tranches V3" form the WSHP Project Log unless otherwise stated in "Project Type (see 3rd tab for description)" in the Master 01-23_workplan_conf
Assumptions, Filters and Sources: - WSHP Project Log (1.13.23 v2) - Master 01-23_workplan_conf - The Program rows of the table below (Fire Rebuild, PSPS, PSS, UG System Hardening) were pulled from the ‘Project type’ column of the ‘Master 01-23_workplan_conf’. In some circumstances this differs to the data from the ‘WSHP Project Log (1.13.23 v2). - Risk Model Application V2 miles are categorized using '2021-2023 Risk Rank (V2)' from Master 01-23_workplan_conf. - Risk Model Application V3 miles are categorized using column ‘2022 Risk Tranches V3’ form the WSHP Project Log (1.13.23 v2) unless conflicted data is provided in ‘Project Type (see 3rd tab for description)’ in ‘Master 01-23_workplan_conf’. - V3 Miles categorized as Tranche 1 are ‘Top Risk’, all others are ‘Not Top Risk’. - V2 Miles with a risk rank <= 727 are categorized as ‘Top Risk’, V2 miles with a risk rank >727 are ‘Not Top Risk’.
Draft: Narrative on Impact of Activity of Wildfire Risk
Impact of the Activity on Wildfire Risk By replacing existing overhead lines with underground assets, ignition risk is reduced by approximately 99 percent . PG&E is focusing on undergrounding in areas where it can be most beneficial in reducing the risk of wildfires and PSPS and EPSS outages that affect customers and critical facilities. As stated in PG&E’s GRC Reply Brief, we have updated our 2023-2026 undergrounding mileage targets and have subsequently updated our workplan. As a result, 85% of our undergrounding work between 2023 and 2026 will be performed in the highest 20% of risk-ranked circuits before additional PSPS, PSS-identified, and/or fire rebuild miles are added. With this updated workplan, PG&E’s annual undergrounding portfolio increasingly addresses the top risk-ranked circuits so that by 2026, 97% of the targeted annual undergrounding miles are focused on the top 20% risk-ranked circuits.

## Table 8.1.2-3
TABLE PG&E-8.1.2-3: PG&E UNDERGROUNDING WORKPLAN 2023-2026
V2 Top Risk: V2 Risk Rank <=727 V3 Top Risk: V3 Risk Rank <=720
Portfolio Year |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2023 - 2026
# of Portfolio Miles |  | 534.3408 |  |  |  | 588.4057 |  |  |  | 682.9839 |  |  |  | 880.9464 |  |  |  | 2686.6767
Program Category |  | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | SH | Butte | Total Miles | % of Portfolio | V2 | V3 | Total
Top 20% Risk-Ranked Circuit Segments |  | 360.9624 |  | 360.9624 | 67.55% | 458.4166 |  | 458.4166 | 77.93% | 647.1972 |  | 647.1972 | 94.76% | 879.1076 |  | 879.1076 | 99.79% | 2345.6839 | 0 | 2345.6839 | 87.31% | 469.8149 | 1875.869 | 2345.6839
Other High Risk | Fire Rebuild | 45.2025 | 77.7009 | 122.9034 | 23% | 5.7807 | 98.7981 | 104.5788 | 17.78% | 1.76 |  | 1.76 | 0.2577% | 1.1201 |  | 1.1201 | 0.1271% | 53.8633 | 176.4991 | 230.3623 | 8.575% | 230.3623 |  | 230.3623
| PSPS | 47.0589 |  | 47.0589 | 8.807% | 18.1983 |  | 18.1983 | 3.094% | 15.9613 |  | 15.9613 | 2.337% |  |  | 0 | 0% | 81.2186 |  | 81.2186 | 3.023% | 81.2186 |  | 81.2186
| PSS Identified | 2.5902 |  | 2.5902 | 0.4847% | 0.57576 |  | 0.57576 | 0.09788% |  |  | 0 | 0% |  |  | 0 | 0% | 3.1659 |  | 3.1659 | 0.1178% | 3.1659 |  | 3.1659
| UG System Hardening | 0.82584 |  | 0.82584 | 0.1546% | 1.1939 |  | 1.1939 | 0.203% | 18.05 |  | 18.05 | 2.643% | 0.33996 |  | 0.33996 | 0.03859% | 20.4097 |  | 20.4097 | 0.7597% | 20.4097 |  | 20.4097
Other UG Programs |  |  |  | 0 | 0% | 5.2831 |  | 5.2831 | 0.8981% | 0.015341 |  | 0.015341 | 0.002246% | 0.37879 |  | 0.37879 | 0.043% | 5.6773 |  | 5.6773 | 0.2113% | 5.6773 |  | 5.6773
Total |  | 456.6398 | 77.7009 | 534.3408 | 100% | 489.4485 | 98.7981 | 588.2466 | 100% | 682.9839 | 0 | 682.9839 | 100% | 880.9464 | 0 | 880.9464 | 100% | 2510.0186 | 176.4991 | 2686.5176 | 100% | 810.6487 | 1875.869 | 2686.5176
Note: The 2023 risk rank for segments is based on the 2021 WDRM v2. The 2024-2026 risk rank for segments is based on the 2022 WDRM v3. Numbers may vary due to rounding. (a) Fire Rebuild miles are based on current, known rebuild needs. These miles may change due to future wildfire activity, which may affect other mileage goals in the 2022-2026 workplan. (b) Other underground projects that are not in the top risk ranked circuits (e.g., Rule 20, WRO, Capacity).
"Top 20% Risk-Ranked Circuit Segments" miles can come from either the WDRM V2 or V3 Risk Rank Models: The "V3 Top 20% Risk-Ranked Circuit Segments" are miles selected from the WDRM V3 risk model with a V3 Risk Rank of <= 720. Any miles with a V3 Risk Rank above 720 that are completed as part of the program would be considered outside “the top 20 percent of risk-ranked circuit segments”. The "V2 Top 20% Risk-Ranked Circuit Segments" are miles selected from the WDRM V2 risk model with a V2 Risk Rank of <=727. Any miles with a V2 Risk Rank above 727 that are completed as part of the program would be considered outside “the top 20 percent of risk-ranked circuit segments”. Sources: - 2023-26 System Hardening Workplan_2023-01-03_Confidential - 'PG&E 2023-26_SH_UGWorkplan_Conf' Sheet | [21 empty] | 30.17% | 69.83% | 100%

## PG&E 2023-26_SH_UGWorkplan_Conf
PG&E 2023-2026 System Hardening and Undergrounding Workplan
Data as of January 3, 2023
[27 empty] | check | 0 | [15 empty] | check | 0
[13 empty] | 502.9049 | 2697.1635 | 139.8031 | 3339.8715 | 2.7182 | 0 | 0 | 2.7182 | 44.9333 | 10.6458 | 0.8839 | 56.4631 | 455.2534 | 2686.5176 | 138.9192 | 3280.6902 |  | 184.1431 | 534.3408 | 55.6509 | 774.1348 | 127.3717 | 588.2466 | 57.8243 | 773.4426 | 143.1446 | 682.9839 | 23.454 | 849.5824 | 0.59405 | 880.9464 | 1.99 | 883.5304
Order | Order Description | Applicable Risk Model | Progam | Project Type | Risk Rank | Top 20% Risk/Not Top Risk | Category | MAT | SAP Status | Status (see 2nd tab) | WMP GH-03 SH (Y/N) | WMP GH-05 10k UG (Y/N) | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2022 Complete | UG - Pre-2022 Complete | Removal - Pre-2022 Complete | Pre-2022 Total Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - Remaining | UG - Remaining | Removal - Remaining | Total Remaining | Years Assigned (for completion) | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles | OH - 2025 Forecast | UG - 2025 Forecast | Removal - 2025 Forecast | 2025 Total Miles | OH - 2026 Forecast | UG - 2026 Forecast | Removal - 2026 Forecast | 2026 Total Miles | Div | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (V2) | Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | Risk Rank (V3) | 2022 Risk Tranches v3 | v3 Mean Risk | HFTD Tier | Project Type 2
35311627 | CWSP BIG MEADOWS 2101 2510 PH1.4 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35398090 | FRRB -BIG MEADOWS 21012260 OH TL 1.14 | WDRM v3 | FRRB | 0 | 2135 | V3 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57027 | 0 | 0 | 0.57027 | 2023 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1356 | -120.9468 | WDRM v3 |  | 995 |  |  | 2135 | 0 |  | Tier 2 | 0
35374057 | CWSP - GEYSERVILLE - 1101482 | WDRM v3 | SH | CWSP | 1375 | V3 Not Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 |  | 2170 | 0.0056711 |  | 1375 | 1 | 0.0011879 | Tier 2 | CWSP 2024
35379282 | REMG - EL DORADO PH 21016852 PH 5 | WDRM v3 | SH | 0 | 1042 | V3 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7271 | -120.5477 | WDRM v3 |  | 2252 |  |  | 1042 | 0 |  | Tier 3 | 0
35367472 | CWSP_0780_EL DORADO 21026645 1.1 | WDRM v3 | SH | CWSP | 780 | V3 Not Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 |  | 780 | 1 | 0.0031904 | Tier 3 | CWSP 2024
35373630 | CWSP - ORO FINO 11012022 PH 3 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35373629 | CWSP - ORO FINO 11012022 PH 2 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.76 | 0 | 5.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76 | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35367501 | CWSP - ORO FINO 11012022 | WDRM v3 | SH | CWSP | 657 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.54 | 0 | 4.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54 | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 1 | 0.003959 | Tier 3 | CWSP 2024
35373626 | CWSP - EL DORADO PH 21016852 PH 4.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.2701 | 0 | 6.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35373625 | CWSP - EL DORADO PH 21016852 PH 3.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.2201 | 0 | 6.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35311626 | CWSP BIG MEADOWS 2101 2510 PH1.3 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35311596 | CWSP BIG MEADOWS 2101 2510 PH1.2 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35286103 | CWSP BIG MEADOWS 2101 2510 PH1.1 | WDRM v2 | SH | CWSP | 3328 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0 | 0.0023864 | Tier 2 | CWSP 2022-2023
35373624 | CWSP - EL DORADO 21016852 PH 2.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35367473 | CWSP - EL DORADO 21016852 - PH 1.1 | WDRM v3 | SH | CWSP | 625 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 1 | 0.0042306 | Tier 3 | CWSP 2024
35390389 | CWSP - MARIPOSA 210110070 PH 1 | WDRM v3 | SH | CWSP | 531 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 |  | 187 | 0.2644 |  | 531 | 1 | 0.0051015 | Tier 2 | CWSP 2024
35375091 | CWSP - LOS OSITOS 21037062 PH 2 | WDRM v3 | SH | CWSP | 516 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.6799 | 0 | 7.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 1 | 0.0052285 | Tier 2 | CWSP 2024
35364020 | CWSP - LOS OSITOS 21037062 | WDRM v3 | SH | CWSP | 516 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 1 | 0.0052285 | Tier 2 | CWSP 2024
35376306 | FRRB - MARIPOSA 21019400 TL-11 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35376304 | FRRB - MARIPOSA 21019400 TL-8 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35376303 | FRRB - MARIPOSA 21019400 TL-9 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374866 | FRRB - MARIPOSA 21019400 TL-7 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2023 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374865 | FRRB - MARIPOSA 21019400 TL-6 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47008 | 0 | 0.47008 | 2023 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374864 | FRRB - MARIPOSA 21019400 TL-5 INSTALL | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0799 | 0 | 2.0799 | 2023 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374862 | FRRB - MARIPOSA 21029590 TL-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2023 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374687 | FRRB - MARIPOSA 21019400 TL-3 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2023 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 | FRRB - 2022
35374686 | FRRB - MARIPOSA 21019400 TL-2 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 2023 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374685 | FRRB - MARIPOSA 210110240 TL-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 3 | FRRB - 2022
35374684 | FRRB - MARIPOSA 210110170 ML-5 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4201 | 0 | 1.4201 | 2023 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374683 | FRRB - MARIPOSA 21019400 ML-4 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374682 | FRRB - MARIPOSA 210110240 ML-1 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45 | 2023 | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35374559 | FRRB - MARIPOSA 21019400 ML-3 | WDRM v3 | FRRB | FRRB | 504 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 1.7 | 2023 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 2 | 0.00537 | Tier 2 & 3 | FRRB - 2022
35364022 | CWSP - LOS COCHES 1101625902 | WDRM v3 | SH | CWSP | 462 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 |  | 2006 | 0.0089147 |  | 462 | 1 | 0.0060529 | Tier 2 | CWSP 2024
35374455 | CWSP - SYCAMORE CREEK 11112014 PH 3 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 & 3 | CWSP 2024
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | WDRM v2 | SH | WDDB | 3283 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 2024 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9747 | -121.8839 | WDRM v2 |  | 3283 | 4.6505e-06 |  | 2739 | 0 | 0.00021707 | Tier 3 | Pre
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | WDRM v2 | SH | WDDB | 3283 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 2024 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9718 | -121.8758 | WDRM v2 |  | 3283 | 4.6505e-06 |  | 2739 | 0 | 0.00021707 | Tier 3 | Pre
35329471 | PSPS HIGHLANDS 1104 CB PH 1.2 | WDRM v2 | SH | PSPS | 3243 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 2023 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 |  | 3243 | 5.43e-06 |  | 1561 | 0 | 0.00090896 | Tier 2 | PSPS - 2023 ICUG
35374454 | CWSP - SYCAMORE CREEK 11112014 PH 2 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 | CWSP 2024
35374444 | CWSP - SYCAMORE CREEK 11112014 PH 1 | WDRM v3 | SH | CWSP | 434 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 1 | 0.0064305 | Tier 2 | CWSP 2024
35396304 | CWSP - BRUNSWICK 11062104 PH2.2 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35392779 | CWSP - BRUNSWICK 11062104 PH 1.3 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35392778 | CWSP - BRUNSWICK 11062104 PH 1.2 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35373585 | CWSP - BRUNSWICK 11062104 PH 2.1 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 1.44 | 2023 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35367418 | CWSP - BRUNSWICK 11062104 PH1.1 | WDRM v3 | SH | CWSP | 429 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 1 | 0.0065825 | Tier 3 | CWSP 2024
35396074 | FRRB - BUCKS CREEK 1103CB PH1 | WDRM v3 | FRRB | 0 | 404 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 1.1932 | 2023 | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.8984 | -121.3203 | WDRM v3 |  | 1658 |  |  | 404 | 2 |  | Tier 3 | 0
35403554 | CWSP-SILVERADO 2105 167360&990552 PH1.5 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403553 | CWSP-SILVERADO 2105 167360&990552 PH1.4 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403552 | CWSP-SILVERADO 2105 167360&990552 PH1.3 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35403551 | CWSP-SILVERADO 2105 167360&990552 PH1.2 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.25 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35367518 | CWSP-SILVERADO 2105 167360&990552 PH1.1 | WDRM v3 | SH | CWSP | 398 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 1 | 0.0070204 | Tier 3 | CWSP 2024
35392114 | FRRB PLACERVILLE 21061104 UG TL5 | WDRM v3 | FRRB | 0 | 397 | V3 Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 |  | 2131 | 0.0064469 |  | 397 | 2 | 0.0070659 | Tier 3 | FRRB - UG - 2022
35355173 | PSPS PIT NO 3 2101CB PH 1.3 | WDRM v3 | SH | CWSP | 394 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS - 2023 ICUG
35355171 | PSPS PIT NO 3 21011482 PH 2.3 | WDRM v3 | SH | CWSP | 394 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS - 2023 ICUG
35404753 | CWSP - STANISLAUS 17021888 PH 2.2 | WDRM v3 | SH | 0 | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0 | 0.0073524 | Tier 3 | V3 Tranche 1
35385890 | CWSP - STANISLAUS 1702 LR1888 PH1.4 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.383 | 0 | 1.383 | 2023 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35385889 | CWSP - STANISLAUS 1702 LR1888 PH1.3 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35385888 | CWSP - STANISLAUS 1702 LR1888 PH1.2 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5439 | 0 | 1.5439 | 2023 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35376888 | CWSP - STANISLAUS 17021888 PH 3 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35373705 | CWSP - STANISLAUS 1702 LR1888 PH 2 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35367520 | CWSP - STANISLAUS 1702 LR1888 PH1.1 | WDRM v3 | SH | CWSP | 379 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2869 | 0 | 2.2869 | 2023 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 1 | 0.0073524 | Tier 3 | CWSP 2024
35373599 | CWSP - EL DORADO PH 2101 LR 63464 PH 2.1 | WDRM v3 | SH | CWSP | 370 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 1 | 0.0074889 | Tier 2 & 3 | CWSP 2024
35367467 | CWSP - EL DORADO PH 2101 LR 63464 PH 1.1 | WDRM v3 | SH | CWSP | 370 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 1 | 0.0074889 | Tier 2 | CWSP 2024
35392113 | FRRB FORESTHILL 110137238 UG TL4 | WDRM v3 | FRRB | 0 | 322 | V3 Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 1 | 0.0088134 | Tier 3 | FRRB - UG - 2022
35387916 | CWSP - FORESTHILL 110137238 PH 1 | WDRM v3 | SH | CWSP | 322 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 1 | 0.0088134 | Tier 2 & 3 | CWSP 2024
35397456 | CWSP - BRUNSWICK 110651486 PH 7.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397455 | CWSP - BRUNSWICK 110651486 PH 7.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397454 | CWSP - BRUNSWICK 110651486 PH 4.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35397453 | CWSP - BRUNSWICK 110651486 PH 3.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35397452 | CWSP - BRUNSWICK 110651486 PH 3.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35326790 | PSPS - FLINT1101 CB & 40666 PH1.2 | WDRM v2 | SH | PSPS | 2980 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0.14792 | 2023 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0 | 0.00050684 | Tier 2 | PSPS - 2023 ICUG
35396863 | CWSP - BRUNSWICK 110651486 PH 5.4 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396862 | CWSP - BRUNSWICK 110651486 PH 5.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396861 | CWSP - BRUNSWICK 110651486 PH 5.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396860 | CWSP - BRUNSWICK 110651486 PH 2.4 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396779 | CWSP - BRUNSWICK 110651486 PH 2.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396778 | CWSP - BRUNSWICK 110651486 PH 2.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396776 | CWSP - BRUNSWICK 110651486 PH 1.3 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35396775 | CWSP - BRUNSWICK 110651486 PH 1.2 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35390288 | CWSP - BRUNSWICK 110651486 - 13993 SEVEN | WDRM v3 | SH | 0 | 315 | V3 Top Risk | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | Y | 0 | 0.12973 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | V3 Tranche 1
35373596 | CWSP - BRUNSWICK 110651486 PH 8 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.09 | 0 | 8.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373595 | CWSP - BRUNSWICK 110651486 PH 7.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373594 | CWSP - BRUNSWICK 110651486 PH 6.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.76 | 0 | 10.76 | 2023 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373593 | CWSP - BRUNSWICK 110651486 PH 5.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.081 | 0 | 3.081 | 2023 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373592 | CWSP - BRUNSWICK 110651486 PH 4.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35373590 | CWSP - BRUNSWICK 110651486 PH 3.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 2 & 3 | CWSP 2024
35373589 | CWSP - BRUNSWICK 110651486 PH 2.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35367462 | CWSP - BRUNSWICK 110651486 PH 1.1 | WDRM v3 | SH | CWSP | 315 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 1 | 0.0088799 | Tier 3 | CWSP 2024
35382936 | CWSP - UPPER LAKE 1101 LR 75370 PH 2 | WDRM v3 | SH | CWSP | 309 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 1 | 0.0089653 | Tier 2 & 3 | CWSP 2024
35382934 | CWSP - UPPER LAKE 1101 LR 75370 PH 1 | WDRM v3 | SH | CWSP | 309 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 1 | 0.0089653 | Tier 2 | CWSP 2024
35379289 | CWSP - PIKE CITY 11011730 PH 2 | WDRM v3 | SH | CWSP | 301 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.74 | 0 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74 | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 1 | 0.0093855 | Tier 3 | CWSP 2024
35375453 | CWSP - PIKE CITY 11011730 PH 1 | WDRM v3 | SH | CWSP | 301 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 1 | 0.0093855 | Tier 3 | CWSP 2024
35385801 | CWSP - NOTRE DAME 11042537 | WDRM v3 | SH | CWSP | 290 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 |  | 1045 | 0.061762 |  | 290 | 1 | 0.0096296 | Tier 2 & 3 | CWSP 2024
35401222 | CWSP - EL DORADO PH 210119612 PH 2.3 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.3201 | 0 | 4.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35401221 | CWSP - EL DORADO PH 210119612 PH 2.2 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35401220 | CWSP - EL DORADO PH 210119612 PH 1.2 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35373598 | CWSP - EL DORADO PH 2101 19612 PH 2.1 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.91 | 0 | 9.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35367466 | CWSP - EL DORADO PH 2101 19612 PH 1.1 | WDRM v3 | SH | CWSP | 287 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.1 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 1 | 0.0097168 | Tier 3 | CWSP 2024
35367475 | CWSP - EL DORADO 2102CB PH 1.1 | WDRM v3 | SH | CWSP | 278 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.8875 | 0 | 6.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 |  | 2732 | 0.00051722 |  | 278 | 1 | 0.0099516 | Tier 3 | CWSP 2024
35396572 | REMG 339, SWIFT 2110 | WDRM v3 | SH | REMG | 276 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Livermore | Santa Clara | 37.3643 | -121.5789 | WDRM v3 |  | 1769 | 0.015532 |  | 276 | 1 |  | Tier 2 | CWSP 2024
35374562 | CWSP - ORO FINO 110239154 PH 6 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374561 | REMG 36 - ORO FINO 1102 PH 5 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374459 | CWSP - ORO FINO 110239154 PH 4 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 | CWSP 2024
35374458 | REMG 510 - ORO FINO 1102 PH 3 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 2 & 3 | CWSP 2024
35374457 | CWSP - ORO FINO 110239154 PH 2 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 3 | CWSP 2024
35374456 | REMG 508 - ORO FINO 1102 PH 1 | WDRM v3 | SH | CWSP | 273 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 1 | 0.010009 | Tier 3 | CWSP 2024
35350039 | FRRB - BIG BEND 1102 884340 - B4 SM2 | WDRM v3 | FRRB | FRRB | 267 | V3 Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2023 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 |  | 1288 | 0.040961 |  | 267 | 1 | 0.010152 | Tier 3 | FRRB - UG – 2021
35373588 | CWSP - BRUNSWICK 110651484 PH 3 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35373587 | CWSP - BRUNSWICK 110651484 PH 2 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35367460 | CWSP - BRUNSWICK 110651484 | WDRM v3 | SH | CWSP | 266 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.41 | 0 | 12.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 1 | 0.010208 | Tier 2 & 3 | CWSP 2024
35396567 | REMG 823 - FRENCHGULCH 1102,SHASTA BALLY | WDRM v3 | SH | REMG | 262 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Igo | Shasta | 40.6068 | -122.6544 | WDRM v3 |  | 2518 | 0.0016954 |  | 262 | 1 |  | Tier 2 | CWSP 2024
35373706 | CWSP - WEST POINT 110113444 PH 2 | WDRM v3 | SH | CWSP | 256 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.45 | 0 | 12.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 1 | 0.01053 | Tier 3 | CWSP 2024
35367522 | CWSP - WEST POINT 110113444 | WDRM v3 | SH | CWSP | 256 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 1 | 0.01053 | Tier 3 | CWSP 2024
35397961 | CWSP - PUEBLO 2103678 PH 4.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35397960 | CWSP - PUEBLO 2103678 PH 4.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396905 | CWSP - PUEBLO 2103678 PH 3.9 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396904 | CWSP - PUEBLO 2103678 PH 3.8 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396903 | CWSP - PUEBLO 2103678 PH 3.7 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396902 | CWSP - PUEBLO 2103678 PH 3.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396900 | CWSP - PUEBLO 2103678 PH 3.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396878 | CWSP - PUEBLO 2103678 PH 3.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396877 | CWSP - PUEBLO 2103678 PH 3.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396876 | CWSP - PUEBLO 2103678 PH 3.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396875 | CWSP - PUEBLO 2103678 PH 2.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396874 | CWSP - PUEBLO 2103678 PH 2.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396871 | CWSP - PUEBLO 2103678 PH 2.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396870 | CWSP - PUEBLO 2103678 PH 2.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35396869 | CWSP - PUEBLO 2103678 PH 2.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392777 | CWSP - PUEBLO 2103678 PH 1.6 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 & 3 | CWSP 2024
35392776 | CWSP - PUEBLO 2103678 PH 1.5 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392775 | CWSP - PUEBLO 2103678 PH 1.4 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392774 | CWSP - PUEBLO 2103678 PH 1.3 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35392773 | CWSP - PUEBLO 2103678 PH 1.2 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 & 3 | CWSP 2024
35373703 | CWSP - PUEBLO 2103678 PH 4.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35373637 | CWSP - PUEBLO 2103678 PH 3.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35373636 | CWSP - PUEBLO 2103678 PH 2.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 3 | CWSP 2024
35367513 | CWSP - PUEBLO 2103678 PH 1.1 | WDRM v3 | SH | CWSP | 255 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 1 | 0.010549 | Tier 2 | CWSP 2024
35373581 | CWSP - BRUNSWICK 11021010 PH 7 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 2024 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373580 | CWSP - BRUNSWICK 11021010 PH 6 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.3799 | 0 | 8.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799 | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373539 | CWSP - BRUNSWICK 11021010 PH 5 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373538 | CWSP - BRUNSWICK 11021010 PH 4 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373537 | CWSP - BRUNSWICK 11021010 PH 3 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35373536 | CWSP - BRUNSWICK 11021010 PH 2 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35367415 | CWSP - BRUNSWICK 11021010 | WDRM v3 | SH | CWSP | 234 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 1 | 0.011407 | Tier 3 | CWSP 2024
35396760 | CWSP - PINE GROVE 110245292 PH 1.5 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35396699 | CWSP - PINE GROVE 110245292 PH 1.4 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.3701 | 0 | 3.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35396698 | CWSP - PINE GROVE 110245292 PH 1.3 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 3 | CWSP 2024
35367511 | CWSP - PINE GROVE 110245292 PH 1.1 | WDRM v3 | SH | CWSP | 233 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 1 | 0.011408 | Tier 2 & 3 | CWSP 2024
35418371 | CWSP - STANISLAUS 170179826 | WDRM v3 | SH | CWSP | 231 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 2024 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 |  | 2142 | 0.0062159 |  | 231 | 1 | 0.011425 | Tier 2 | V3 Tranche 1
35376889 | CWSP - WEST POINT 1101 CB & 12256 PH2 | WDRM v3 | SH | CWSP | 218 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 1 | 0.011836 | Tier 3 | CWSP 2024
35367526 | CWSP - WEST POINT 1101 CB & 12256 PH 1.1 | WDRM v3 | SH | CWSP | 218 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 13.5701 | 0 | 13.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 1 | 0.011836 | Tier 3 | CWSP 2024
35312546 | PSPS - FLINT1101 CB & 40666 PH1.1 | WDRM v2 | SH | PSPS | 2980 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8933 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0 | 0.00050684 | Tier 2 | PSPS - 2023 ICUG
35396073 | FRRB - KANAKA 1101CB - K4 SM5 | WDRM v3 | FRRB | 0 | 212 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0 | 0.16098 | 2023 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5468 | -121.3424 | WDRM v3 |  | 1480 |  |  | 212 | 2 |  | Tier 2 | 0
35373051 | FRRB - KANAKA 1101CB - K2 SM3 | WDRM v3 | FRRB | 0 | 212 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13864 | 0 | 0.13864 | 2023 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG – 2021
35367500 | CWSP - MIDDLETOWN 1101614 | WDRM v3 | SH | CWSP | 211 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 |  | 2060 | 0.0076984 |  | 211 | 1 | 0.01209 | Tier 3 | CWSP 2024
35404267 | CWSP - PINE GROVE 110213438 PH 2.2 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35402642 | CWSP - PINE GROVE 110213438 1.3 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | N | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 2024 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 |  | Tier 2 & 3 | CWSP 2024
35402641 | CWSP - PINE GROVE 110213438 PH 1.2 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35373635 | CWSP - PINE GROVE 110213438 PH 2.1 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35367510 | CWSP - PINE GROVE 110213438 | WDRM v3 | SH | CWSP | 204 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 2024 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 1 | 0.012447 | Tier 2 & 3 | CWSP 2024
35403850 | CWSP - MARIPOSA 2101752630 PH 2.3 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403849 | CWSP - MARIPOSA 2101752630 PH 2.2 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.31 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403848 | CWSP - MARIPOSA 2101752630 PH 1.3 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35403847 | CWSP - MARIPOSA 2101752630 PH 1.2 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35078178 | STS-COND_IDLE_REMV-295 EAST RD | WDRM v2 | IF | 0 | 2968 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1304 | -122.1182 | WDRM v2 |  | 2968 | 1.8516e-05 |  | 1102 | 0 | 0.0019468 | Tier 3 | Idle Facilities
35221765 | STS-COND_IDLE_REMV - 1504 PINE DR ARNOLD | WDRM v2 | IF | 0 | 2810 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2531 | -120.3592 | WDRM v2 |  | 2810 | 0.00026318 |  | 98 | 1 | 0.01848 | Tier 3 | Idle Facilities
31383326 | E CAP - SR 1107 & 1110 RECONFIGURE | WDRM v2 | Other | 0 | 2799 | V2 Not Top Risk | Other | 06E | CONS | In-Construction | Y | N | 0.41856 | 0 | 0 | 0.41856 | 0 | 0 | 0 | 0 | 0.29867 | 0 | 0 | 0.29867 | 0.11989 | 0 | 0 | 0.11989 | 2023 | 0.11989 | 0 | 0 | 0.11989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4388 | -122.6868 | WDRM v2 |  | 2799 | 0.00029462 |  | 7022 | 0 | 3.4973e-05 | Tier 2 | 0
74001486 | GRIZZLY PEAK BLVD BERKELEY R20A | WDRM v2 | Other | 0 | 2792 | V2 Not Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | WDRM v2 |  | 2792 | 0.00031068 |  | 2633 | 0 | 0.00025777 | Tier 2 & 3 | Other
35277146 | STS-COND_IDLE_REMV-29040 SNOWHITE RD | WDRM v2 | IF | 0 | 2788 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0.13617 | 2023 | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne | 38.1406 | -120.0581 | WDRM v2 |  | 2788 | 0.00031402 |  | 922 | 0 | 0.0025407 | Tier 3 | Idle Facilities
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | WDRM v2 | SH | REMG | 2738 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 2023 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 | WDRM v2 |  | 2738 | 0.0004909 |  | 482 | 0 | 0.0057466 | Tier 3 | Remote Grid Pilot
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | WDRM v2 | SH | CWSP | 2712 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.7748 | 0.053977 | 0 | 1.8288 | 0 | 0 | 0 | 0 | 1.483 | 0.053977 | 0 | 1.5369 | 0.29186 | 0 | 0 | 0.29186 | 2023 | 0.29186 | 0 | 0 | 0.29186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 |  | 2712 | 0.00058985 |  | 1583 | 0 | 0.00088659 | Tier 3 | Pre
35243446 | REMG 665 - OLEMA 1101, MT VISIONS PRNS | WDRM v2 | SH | REMG | 2644 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 |  | 2644 | 0.00096084 |  | 2439 | 0 | 0.00032912 | Tier 2 | REMG 2022-2023
35237937 | EQUIP ACCESS ISSUE 1025 HIDDEN VALLEY RD | WDRM v2 | Other | 0 | 2595 | V2 Not Top Risk | Other | 2BP | UNSC | Ready for Construction | Y | Y | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soquel | Santa Cruz | 37.0341 | -121.9738 | WDRM v2 |  | 2595 | 0.0012326 |  | 1319 | 0 | 0.0013011 | Tier 3 | Other
35342333 | FRRB-BIG BASIN 1101 UG1 SAN VICENTE | WDRM v2 | FRRB | FRRB | 2579 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42576 | 0 | 0.42576 | 2023 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0 | 0.0018854 | Tier 3 | FRRB
35237593 | #CZUSCRUZ 425 SAN VICENTE TERRACE, SCRUZ | WDRM v2 | FRRB | 0 | 2579 | V2 Not Top Risk | Fire Rebuild | 95F | CONS | In-Construction | Y | N | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027462 | 0 | 0 | 0.027462 | 2023 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.1011 | -122.1426 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0 | 0.0018854 | Tier 3 | 0
35382933 | CWSP - MARIPOSA 2101752630 PH 2.1 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.24 | 0 | 5.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35379382 | CWSP - MARIPOSA 2101752630 PH 1.1 | WDRM v3 | SH | CWSP | 199 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 1 | 0.012689 | Tier 2 | CWSP 2024
35375184 | CWSP - LOS OSITOS 21037014 PH 5 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375183 | CWSP - LOS OSITOS 21037014 PH 4 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375182 | CWSP - LOS OSITOS 21037014 PH 3 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375181 | CWSP - LOS OSITOS 21037014 PH 2 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35375180 | CWSP - LOS OSITOS 21037014 PH 1 | WDRM v3 | SH | CWSP | 193 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 2024 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 |  | N/A | N/A |  | 193 | 1 | 0.012994 | HFRA | CWSP 2024
35376642 | CWSP - BONNIE NOOK 1102CB PH 4 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.06 | 0 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06 | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35378609 | PLUCODIXIE-COMMERCIAL-Z2 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 2023 | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35376641 | CWSP - BONNIE NOOK 1102CB PH 3 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35376640 | CWSP - BONNIE NOOK 1102CB PH 2 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35376556 | CWSP - BONNIE NOOK 1102CB & 1103CB PH 1 | WDRM v3 | SH | CWSP | 192 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 1 | 0.013013 | Tier 3 | CWSP 2024
35368118 | FRRB - BIG BEND 1102 CB - B1 SM1 | WDRM v3 | FRRB | 0 | 187 | V3 Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0 | 0 | 0.030303 | 2023 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6347 | -121.4543 | WDRM v3 |  | 865 |  |  | 187 | 1 |  | Tier 3 | 0
35378690 | CWSP - MIDDLETOWN 11014646 -PH 4 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.46 | 0 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46 | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35378688 | CWSP - MIDDLETOWN 11014646 -PH 3 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.89 | 0 | 10.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89 | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35378687 | CWSP - MIDDLETOWN 11014646 -PH 2 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35377437 | CWSP - MIDDLETOWN 11014646 | WDRM v3 | SH | CWSP | 182 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 1 | 0.013549 | Tier 3 | CWSP 2024
35403556 | CWSP - FORESTHILL 11011802 PH 3.3 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35403555 | CWSP - FORESTHILL 11011802 PH 3.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399836 | CWSP - FORESTHILL 1101 1802 PH 2.3 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.387 | 0 | 5.387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387 | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399835 | CWSP - FORESTHILL 1101 1802 PH 2.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.342 | 0 | 2.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342 | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35399834 | CWSP - FORESTHILL 1101 1802 PH 1.2 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35373526 | CWSP - FORESTHILL 11011802 PH 3.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35373525 | CWSP - FORESTHILL 1101 1802 PH 2.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35367476 | CWSP - FORESTHILL 1101 1802 PH 1.1 | WDRM v3 | SH | CWSP | 179 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 1 | 0.013637 | Tier 3 | CWSP 2024
35382858 | CWSP - LOS OSITOS 21033010 PH 5 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375099 | CWSP - LOS OSITOS 21033010 PH 4 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375096 | CWSP - LOS OSITOS 21033010 PH 3 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375095 | CWSP - LOS OSITOS 21033010 PH 2 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35375094 | CWSP - LOS OSITOS 21033010 PH 1 | WDRM v3 | SH | CWSP | 178 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 1 | 0.013726 | Tier 2 | CWSP 2024
35373621 | CWSP - EL DORADO 210219542 PH 2.1 | WDRM v3 | SH | CWSP | 176 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.31 | 0 | 7.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 1 | 0.013848 | Tier 3 | CWSP 2024
35367470 | CWSP - EL DORADO 210219542 PH 1.1 | WDRM v3 | SH | CWSP | 176 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.71 | 0 | 6.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 1 | 0.013848 | Tier 3 | CWSP 2024
35383757 | CWSP - WEST POINT 11024788 PH5 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383756 | CWSP - WEST POINT 11024788 PH4 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383755 | CWSP - WEST POINT 11024788 PH3 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383754 | CWSP - WEST POINT 11024788 PH2 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 & 3 | CWSP 2024
35383753 | CWSP - WEST POINT 11024788 PH 1 | WDRM v3 | SH | CWSP | 164 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 1 | 0.014654 | Tier 2 | CWSP 2024
35373535 | CWSP - ORO FINO 1101CB PH 3 | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35373534 | CWSP - ORO FINO 1101CB PH 2 | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35367503 | CWSP - ORO FINO 1101CB | WDRM v3 | SH | CWSP | 158 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 1 | 0.015008 | Tier 3 | CWSP 2024
35374203 | CWSP - NOTRE DAME 1104176446 | WDRM v3 | SH | CWSP | 155 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 |  | 73 | 0.37815 |  | 155 | 1 | 0.015172 | Tier 2 & 3 | CWSP 2024
35402643 | CWSP - PINE GROVE 11013166 PH 1.2 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.4561 | 0 | 2.4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35396761 | CWSP - PINE GROVE 11013166 PH 2.2 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35373707 | CWSP - PINE GROVE 11013166 PH 2.1 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35372460 | CWSP - PINE GROVE 11013166 PH 1.1 | WDRM v3 | SH | CWSP | 147 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.4299 | 0 | 7.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 1 | 0.015597 | Tier 2 | CWSP 2024
35376305 | FRRB - MARIPOSA 210110170 TL-10 | WDRM v3 | FRRB | FRRB | 137 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0.61004 | 2023 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 2 | 0.015939 | Tier 3 | FRRB - 2022
35374863 | FRRB - MARIPOSA 21019400 TL-4 INSTALL | WDRM v3 | FRRB | FRRB | 137 | V3 Top Risk | Fire Rebuild | 08W | ADER | Estimating | Y | Y | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0.46004 | 2023 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 2 | 0.015939 | Tier 2 | FRRB - 2022
35367515 | CWSP - SALT SPRINGS 210297924 | WDRM v3 | SH | CWSP | 133 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.6799 | 0 | 6.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 |  | 2620 | 0.0010653 |  | 133 | 1 | 0.016045 | Tier 3 | CWSP 2024
35375515 | CWSP - APPLE HILL 2102836878 PH 7 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 | CWSP 2024
35375514 | CWSP - APPLE HILL 2102836878 PH 6 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375513 | CWSP - APPLE HILL 2102836878 PH 5 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375512 | CWSP - APPLE HILL 2102836878 PH 4 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375511 | CWSP - APPLE HILL 2102836878 PH 3 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 3 | CWSP 2024
35375510 | CWSP - APPLE HILL 2102836878 PH 2 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35375509 | CWSP - APPLE HILL 2102836878 PH 1 | WDRM v3 | SH | CWSP | 132 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 1 | 0.01606 | Tier 2 & 3 | CWSP 2024
35404716 | CWSP - PINE GROVE 11026080 PH 4 | WDRM v3 | SH | CWSP | 131 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 1 | 0.016072 | Tier 2 | V3 Tranche 1
35404715 | CWSP - PINE GROVE 11026080 PH 3 | WDRM v3 | SH | CWSP | 131 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 1 | 0.016072 | Tier 2 | V3 Tranche 1
35401013 | CWSP MARIPOSA 210110240 PH 1.4 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35401012 | CWSP MARIPOSA 210110240 PH 1.3 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35401011 | CWSP MARIPOSA 210110240 PH 1.2 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35397963 | CWSP MARIPOSA 210110240 PH 2.3 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35397962 | CWSP MARIPOSA 210110240 PH 2.2 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35382932 | CWSP MARIPOSA 210110240 PH 2.1 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35379383 | CWSP MARIPOSA 210110240 PH 1.1 | WDRM v3 | SH | CWSP | 126 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | CWSP 2024
35375721 | FRRB - MARIPOSA 21019400 ML-6 | WDRM v3 | FRRB | FRRB | 126 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 3 | FRRB - 2022
35374681 | FRRB - MARIPOSA 21019400 ML-2 | WDRM v3 | FRRB | FRRB | 126 | V3 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96004 | 0 | 0.96004 | 2023 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 1 | 0.016323 | Tier 2 & 3 | FRRB - 2022
35373529 | CWSP - APPLE HILL 110413512 PH 4 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 3 | CWSP 2024
35373528 | CWSP - APPLE HILL 110413512 PH 3 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 3 | CWSP 2024
35373527 | CWSP - APPLE HILL 110413512 PH 2 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 2 & 3 | CWSP 2024
35367412 | CWSP - APPLE HILL 110413512 | WDRM v3 | SH | CWSP | 124 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 1 | 0.016427 | Tier 2 & 3 | CWSP 2024
35396570 | REMG 432 - PEORIA 1701, TBD | WDRM v3 | SH | REMG | 122 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | La Grange | Tuolumne | 37.7952 | -120.2836 | WDRM v3 |  | 780 | 0.09692 |  | 122 | 1 |  | Tier 2 | CWSP 2024
35374059 | CWSP - ELECTRA 1101L1697 | WDRM v3 | SH | CWSP | 118 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 |  | 2349 | 0.0030208 |  | 118 | 1 | 0.016781 | Tier 2 | CWSP 2024
35377525 | CWSP - PIKE CITY 1101CB PH 3 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.9701 | 0 | 6.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701 | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35375450 | CWSP - PIKE CITY 1101CB PH 2 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.66 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66 | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35375449 | CWSP - PIKE CITY 1101CB PH 1 | WDRM v3 | SH | CWSP | 116 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.85 | 0 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85 | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 1 | 0.016874 | Tier 3 | CWSP 2024
35379381 | CWSP - CLAYTON 2212681608 | WDRM v3 | SH | CWSP | 115 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.4 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 |  | 400 | 0.18021 |  | 115 | 1 | 0.016899 | Tier 2 & 3 | CWSP 2024
35396911 | CWSP - FORESTHILL 110150486 - PH 1.5 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396910 | CWSP - FORESTHILL 110150486 - PH 1.4 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396909 | CWSP - FORESTHILL 110150486 - PH 1.3 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35396908 | CWSP - FORESTHILL 110150486 - PH 1.2 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35373533 | CWSP - FORESTHILL 110150486 PH 2 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35367478 | CWSP - FORESTHILL 110150486 - PH 1.1 | WDRM v3 | SH | CWSP | 114 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 1 | 0.01695 | Tier 3 | CWSP 2024
35383305 | CWSP - WEST POINT 11014706 PH2 | WDRM v3 | SH | CWSP | 107 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.99 | 0 | 4.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 1 | 0.017455 | Tier 3 | CWSP 2024
35367524 | CWSP WEST POINT 1101 LR4706 PH1.1 | WDRM v3 | SH | CWSP | 107 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 14.3201 | 0 | 14.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 1 | 0.017455 | Tier 3 | CWSP 2024
35373597 | CWSP - CALISTOGA 110143924 PH 2 | WDRM v3 | SH | CWSP | 105 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.0201 | 0 | 5.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 1 | 0.017566 | Tier 3 | CWSP 2024
35367464 | CWSP - CALISTOGA 110143924 PH 1.1 | WDRM v3 | SH | CWSP | 105 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.0299 | 0 | 9.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 1 | 0.017566 | Tier 3 | CWSP 2024
35404726 | CWSP - SILVERADO 210478268 PH 2.2 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404355 | CWSP - SILVERADO 210478268 PH 1.6 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404354 | CWSP - SILVERADO 210478268 PH 1.5 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404353 | CWSP - SILVERADO 210478268 PH 1.4 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404352 | CWSP - SILVERADO 210478268 PH 1.3 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35404351 | CWSP - SILVERADO 210478268 PH 1.2 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35373704 | CWSP - SILVERADO 210478268 PH 2.1 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35367516 | CWSP - SILVERADO 210478268 PH 1.1 | WDRM v3 | SH | CWSP | 101 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 1 | 0.018153 | Tier 3 | CWSP 2024
35362666 | CWSP - CLAYTON 2212614950 | WDRM v3 | SH | CWSP | 100 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 |  | 2561 | 0.0014894 |  | 100 | 1 | 0.018211 | Tier 2 & 3 | CWSP 2024
35409203 | CWSP - MIDDLETOWN 1101433160 | WDRM v3 | SH | CWSP | 99 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 |  | 314 | 0.20636 |  | 99 | 1 | 0.018456 | Tier 2 & 3 | CWSP 2024
35418379 | CWSP - STANISLAUS 170237278 | WDRM v3 | SH | CWSP | 98 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 |  | 2810 | 0.00026318 |  | 98 | 1 | 0.01848 | Tier 3 | V3 Tranche 1
35417148 | CWSP - Foresthill 1102 2106 PH 4 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.56 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417144 | CWSP - Foresthill 1102 2106 PH 3 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.7 | 0 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417117 | CWSP - Foresthill 1102 2106 PH 2 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
35417110 | CWSP - Foresthill 1102 2106 PH 1 | WDRM v3 |  |  | 97 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0 | 0.018495 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 95 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0 | 0.018647 | Tier 2 & 3 | V3 Tranche 1
35362685 | CWSP - STANISLAUS 1701 CB PH1.7 | WDRM v3 | SH | 0 | 95 | V3 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.42708 | 0 | 0 | 0.42708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.178 | -120.3801 | WDRM v3 |  | 56 |  |  | 95 | 1 |  | Tier 2 | 0
35372463 | CWSP - ANTLER 1101CB | WDRM v3 | SH | CWSP | 94 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.020076 | 1.99 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01 | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 |  | 2207 | 0.0049349 |  | 94 | 1 | 0.0187 | Tier 2 | CWSP 2024
TBD |  | WDRM v3 |  |  | 93 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9 | 0 | 10.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0 | 0.018723 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 93 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0 | 0.018723 | Tier 3 | V3 Tranche 1
35395931 | REMG - ANTLER 11011520 PH 1.5 | WDRM v3 | SH | REMG | 91 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377 | 2023 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.9225 | -122.4132 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 |  | Tier 2 | CWSP 2024
35395930 | CWSP - ANTLER 11011520 PH 1.4 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.369 | 0 | 0.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369 | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35395929 | CWSP - ANTLER 11011520 PH 1.3 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.057 | 0 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057 | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35395928 | CWSP - ANTLER 11011520 PH 1.2 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.937 | 0 | 1.937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937 | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35372464 | CWSP - ANTLER 11011520 PH1.1 | WDRM v3 | SH | CWSP | 91 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.553 | 0 | 6.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553 | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 1 | 0.018782 | Tier 2 | CWSP 2024
35418356 | CWSP - SILVERADO 2105900104 | WDRM v3 | SH | CWSP | 90 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 |  | 2351 | 0.0030112 |  | 90 | 1 | 0.018786 | Tier 3 | V3 Tranche 1
35418366 | CWSP - SHADY GLEN 110248894 PH2 | WDRM v3 | SH | CWSP | 89 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 1 | 0.018876 | Tier 3 | V3 Tranche 1
35418361 | CWSP - SHADY GLEN 110248894 PH1 | WDRM v3 | SH | CWSP | 89 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.601 | 0 | 6.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 1 | 0.018876 | Tier 3 | V3 Tranche 1
35376559 | CWSP - SILVERADO 2105658898 PH 2 | WDRM v3 | SH | CWSP | 87 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 1 | 0.018978 | Tier 3 | CWSP 2024
35376558 | CWSP - SILVERADO 2105658898 PH 1 | WDRM v3 | SH | CWSP | 87 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.25 | 0 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 1 | 0.018978 | Tier 3 | CWSP 2024
35396569 | REMG 841 - KESWICK 1101, WSKYTWN ENV SCH | WDRM v3 | SH | REMG | 83 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.5822 | -122.5413 | WDRM v3 |  | 1135 | 0.053968 |  | 83 | 1 |  | Tier 2 | CWSP 2024
35396568 | REMG 840 - KESWICK 1101, BRANDY CRK BEAC | WDRM v3 | SH | REMG | 83 | V3 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 2023 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.616 | -122.5718 | WDRM v3 |  | 1135 | 0.053968 |  | 83 | 1 |  | Tier 2 | CWSP 2024
35373620 | PSPS - EL DORADO PH 2101 LR 668674 PH2.1 | WDRM v3 | SH | CWSP | 81 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 1 | 0.019264 | Tier 3 | PSPS
35367468 | PSPS - EL DORADO PH 2101 LR 668674 PH1 | WDRM v3 | SH | CWSP | 81 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 1 | 0.019264 | Tier 3 | PSPS
35383758 | CWSP - WEST POINT 11021341 PH1 | WDRM v3 | SH | CWSP | 80 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 |  | 2247 | 0.0041901 |  | 80 | 1 | 0.019265 | Tier 3 | CWSP 2024
35409211 | CWSP - SHADY GLEN 110132726 PH 2 | WDRM v3 | SH | CWSP | 71 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 1 | 0.02023 | Tier 2 | V3 Tranche 1
35409205 | CWSP - SHADY GLEN 110132726 PH 1 | WDRM v3 | SH | CWSP | 71 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 15.2 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2 | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 1 | 0.02023 | Tier 2 | CWSP 2024
35391723 | CWSP - PLACERVILLE 210611132 PH 6 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391722 | CWSP - PLACERVILLE 210611132 PH 5 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391721 | CWSP - PLACERVILLE 210611132 PH 4 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 3 | CWSP 2024
35391473 | CWSP - PLACERVILLE 210611132 PH 3 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 | CWSP 2024
35391472 | CWSP - PLACERVILLE 210611132 PH 2.1 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 & 3 | CWSP 2024
35391471 | CWSP - PLACERVILLE 210611132 PH 1.1 | WDRM v3 | SH | CWSP | 68 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 2024 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 & 3 | CWSP 2024
TBD |  | WDRM v3 |  |  | 66 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.788 | 0 | 8.788 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0 | 0.02064 | Tier 3 | V3 Tranche 1
TBD |  | WDRM v3 |  |  | 66 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0 | 0.02064 | Tier 3 | V3 Tranche 1
35409217 | CWSP - OREGON TRAIL 11021584 PH 2 | WDRM v3 | SH | CWSP | 64 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 1 | 0.0208 | Tier 2 | CWSP 2024
35409215 | CWSP - OREGON TRAIL 11021584 PH 1 | WDRM v3 | SH | CWSP | 64 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.1 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 1 | 0.0208 | Tier 2 | CWSP 2024
35373532 | CWSP - APPLE HILL 21027502 PH 3 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 2024 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 3 | CWSP 2024
35373530 | CWSP - APPLE HILL 21027502 PH 2 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 15.51 | 0 | 15.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51 | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 3 | CWSP 2024
35367414 | CWSP - APPLE HILL 21027502 | WDRM v3 | SH | CWSP | 63 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 2024 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 1 | 0.020812 | Tier 2 & 3 | CWSP 2024
35404349 | CWSP - ELECTRA 1101 LR7104 PH 1.2 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.47 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35376890 | CWSP - ELECTRA 11017104 PH2 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.09 | 0 | 7.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35372462 | CWSP - ELECTRA 1101 LR7104 PH 1.1 | WDRM v3 | SH | CWSP | 62 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0.019886 | 4.85 | 0 | 4.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 1 | 0.020861 | Tier 2 | CWSP 2024
35373628 | CWSP - ORO FINO 110276008 PH 2 | WDRM v3 | SH | CWSP | 61 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.7299 | 0 | 8.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 1 | 0.020869 | Tier 3 | CWSP 2024
35367504 | CWSP - ORO FINO 110276008 | WDRM v3 | SH | CWSP | 61 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.35 | 0 | 9.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 1 | 0.020869 | Tier 3 | CWSP 2024
35418375 | CWSP - STANISLAUS 17026028 | WDRM v3 | SH | CWSP | 60 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 |  | 2670 | 0.0008147 |  | 60 | 1 | 0.021109 | Tier 3 | V3 Tranche 1
35385804 | CWSP - SILVERADO 2104 LR 632 PH 2 | WDRM v3 | SH | CWSP | 59 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | CWSP 2024
35385803 | CWSP - SILVERADO 2104 LR 632 PH 1 | WDRM v3 | SH | CWSP | 59 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | CWSP 2024
35418305 | CWSP - PLACERVILLE 2106935216 PH 3 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35418255 | CWSP - PLACERVILLE 2106935216 PH 2 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35417127 | CWSP - PLACERVILLE 2106935216 PH 1 | WDRM v3 | SH | CWSP | 58 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 1 | 0.021398 | Tier 3 | V3 Tranche 1
35364784 | CWSP - SYCAMORE CREEK 11112268 PH 3 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.1701 | 0 | 7.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35363720 | CWSP - SYCAMORE CREEK 11112268 PH 2 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35363559 | CWSP - SYCAMORE CREEK 11112268 PH 1 | WDRM v3 | SH | CWSP | 57 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 1 | 0.021521 | Tier 3 | CWSP 2024
35409202 | CWSP - MIDDLETOWN 11011314 PH1 | WDRM v3 | SH | CWSP | 56 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 |  | 915 | 0.078235 |  | 56 | 1 | 0.021686 | Tier 2 & 3 | CWSP 2024
35375452 | CWSP - PIKE CITY 11011720 | WDRM v3 | SH | CWSP | 52 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 |  | 1710 | 0.017864 |  | 52 | 1 | 0.02211 | Tier 3 | CWSP 2024
35374570 | CWSP - NARROWS 2102CB | WDRM v3 | SH | CWSP | 46 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.2799 | 0 | 7.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799 | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 |  | 658 | 0.11807 |  | 46 | 1 | 0.022999 | Tier 2 | CWSP 2024
35374569 | CWSP - BUCKS CREEK 1102CB - BELDEN | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | CWSP 2024
35374567 | CWSP - BUCKS CREEK 1102CB - RODGERS FLAT | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | CWSP 2024
35374566 | CWSP - BUCKS CREEK 1102CB - ROCK CREST | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374564 | CWSP - BUCKS CREEK 1102CB PH 2 N/O HWY 7 | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.79 | 1.76 | 8.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55 | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374563 | CWSP - BUCKS CREEK 1102CB PH 1 N/O HWY 7 | WDRM v3 | SH | CWSP | 45 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 | CWSP 2024
35374443 | CWSP - ALLEGHANY 1102CB NEVADA PH 5 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.7701 | 0 | 6.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701 | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374208 | CWSP - ALLEGHANY 1102CB NEVADA PH 4 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.89 | 0 | 4.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89 | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374206 | CWSP - ALLEGHANY 1102CB NEVADA PH 3 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374205 | CWSP - ALLEGHANY 1102CB SIERRA PH 2 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.24 | 0 | 6.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24 | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35374204 | CWSP - ALLEGHANY 1102CB SIERRA PH 1 | WDRM v3 | SH | CWSP | 41 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.7201 | 0 | 6.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201 | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | CWSP 2024
35377520 | CWSP - MIDDLETOWN 1101171414 | WDRM v3 | SH | CWSP | 38 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 |  | 328 | 0.19983 |  | 38 | 1 | 0.024501 | Tier 3 | CWSP 2024
35374202 | CWSP - NOTRE DAME 11042028 PH 2 | WDRM v3 | SH | CWSP | 37 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.6701 | 0 | 4.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701 | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 1 | 0.024521 | Tier 3 | CWSP 2024
35374200 | CWSP - NOTRE DAME 11042028 PH 1 | WDRM v3 | SH | CWSP | 37 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.04 | 0 | 8.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 1 | 0.024521 | Tier 3 | CWSP 2024
35385806 | CWSP - SILVERADO 2104 LR 515946 PH 2 | WDRM v3 | SH | CWSP | 33 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 6.69 | 0 | 6.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 1 | 0.025445 | Tier 3 | CWSP 2024
35385805 | CWSP - SILVERADO 2104 LR 515946 PH 1 | WDRM v3 | SH | CWSP | 33 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.74 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 1 | 0.025445 | Tier 3 | CWSP 2024
TBD |  | WDRM v3 |  |  | 32 | V3 Top Risk | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | Y | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 2024 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 |  | 178 | 0.2712 |  | 32 | 0 | 0.025831 | Tier 3 | V3 Tranche 1
35409213 | CWSP - APPLE HILL 1104CB | WDRM v3 | SH | CWSP | 30 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 |  | 1422 | 0.032289 |  | 30 | 1 | 0.025967 | Tier 2 | CWSP 2024
35367335 | CWSP - BONNIE NOOK 1101CB PH 1 | WDRM v3 | SH | CWSP | 20 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 1 | 0.02949 | Tier 3 | CWSP 2024
35365064 | CWSP - BONNIE NOOK 1101CB PH 2 | WDRM v3 | SH | CWSP | 20 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.34 | 0.22992 | 10.5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699 | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 1 | 0.02949 | Tier 3 | CWSP 2024
35373634 | CWSP - ORO FINO 11022090 PH 3 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.4299 | 0 | 4.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299 | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35373632 | CWSP - ORO FINO 11022090 PH 2 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 10.2299 | 0 | 10.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299 | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35367508 | CWSP - ORO FINO 11022090 | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 5.94 | 0 | 5.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94 | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35367507 | CWSP - ORO FINO 1102CB | WDRM v3 | SH | CWSP | 17 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 1 | 0.031702 | Tier 3 | CWSP 2024
35235158 | #CZUSCRUZ 2151 PINE FLAT RD, SCRUZ | WDRM v2 | FRRB | 0 | 2539 | V2 Not Top Risk | Fire Rebuild | 95F | FICL | In-Construction | Y | N | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030871 | 0 | 0 | 0.030871 | 2023 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Felton | Santa Cruz | 37.0448 | -122.0673 | WDRM v2 |  | 2539 | 0.0016007 |  | 903 | 3 | 0.0026122 | Tier 3 | 0
35211671 | DR~STS-COND_IDLE_REMV-1120 NATUREWOOD DR | WDRM v2 | IF | 0 | 2536 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83769 | 0.83769 | 2023 | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0289 | -121.0036 | WDRM v2 |  | 2536 | 0.0016155 |  | 1432 | 0 | 0.0011018 | Tier 2 | Idle Facilities
35244167 | DR-COND_IDLE_REMV-WINCHESTER DR | WDRM v2 | IF | 0 | 2500 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22519 | 0.22519 | 2023 | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Meadow Vista | Placer | 38.9969 | -121.0593 | WDRM v2 |  | 2500 | 0.001823 |  | 1766 | 0 | 0.00071024 | Tier 2 | Idle Facilities
35225253 | STS-COND_IDLE_REMV-214 TABERNACLE DRIVE | WDRM v2 | IF | 0 | 2474 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028409 | 0.028409 | 2023 | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 37.0631 | -122.0333 | WDRM v2 |  | 2474 | 0.0020379 |  | 1225 | 0 | 0.0015415 | Tier 3 | Idle Facilities
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | WDRM v2 | SH | CWSP | 2456 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4441 | 0 | 0 | 3.4441 | 0 | 0 | 0 | 0 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538 | 2023 | 0.12538 | 0 | 0 | 0.12538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1332 | -122.1257 | WDRM v2 |  | 2456 | 0.0021702 |  | 1113 | 0 | 0.0019056 | Tier 3 | Pre
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | WDRM v2 | FRRB | FRRB | 2435 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20114 | 0 | 0.20114 | 2023 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 |  | 2435 | 0.002283 |  | 1105 | 0 | 0.0019396 | Tier 3 | FRRB
35225011 | STS-COND_IDLE_REMV - AT 1580 PRESTON ST | WDRM v2 | IF | 0 | 2433 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 2023 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Cambria | San Luis Obispo | 35.5452 | -121.0718 | WDRM v2 |  | 2433 | 0.0023119 |  | 2127 | 0 | 0.00047475 | Tier 2 | Idle Facilities
35224941 | +STS-COND_IDLE_REMV-R/O 2PE 1PS/O #67 BL | WDRM v2 | IF | 0 | 2399 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Morro Bay | San Luis Obispo | 35.3583 | -120.8253 | WDRM v2 |  | 2399 | 0.0025799 |  | 2247 | 0 | 0.00041125 | Tier 2 | Idle Facilities
35225467 | STS-COND_IDLE_REMV - 1/P/S/O/587 AVOCADO | WDRM v2 | IF | 0 | 2387 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023674 | 0.023674 | 2023 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Watsonville | Santa Cruz | 37.012 | -121.7958 | WDRM v2 |  | 2387 | 0.0026825 |  | 1464 | 0 | 0.0010495 | Tier 2 | Idle Facilities
35243445 | REMG 49 - OLEMA 1101, HOME RANCH PRNS | WDRM v2 | SH | REMG | 2360 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 |  | 2360 | 0.0028981 |  | 3015 | 0 | 0.00012995 | Tier 2 | REMG 2022-2023
35342460 | FRRB - BIG BASIN 1102 OH1 LODGE RD | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | N | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 2023 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1741 | -122.1812 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35385802 | CWSP - CLAYTON 2212 LR 96224 | WDRM v3 | SH | CWSP | 15 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.6 | 0 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | CWSP 2024
35376891 | CWSP - SILVERADO 2104646776 | WDRM v3 | SH | CWSP | 14 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.4 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4 | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 |  | 1235 | 0.044601 |  | 14 | 1 | 0.034265 | Tier 3 | CWSP 2024
35373708 | CWSP - ANTLER 11011384 PH 2 | WDRM v3 | SH | CWSP | 11 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 3.73 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73 | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 1 | 0.038738 | Tier 2 | CWSP 2024
35372465 | CWSP - ANTLER 11011384 | WDRM v3 | SH | CWSP | 11 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 11.84 | 0 | 11.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84 | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 1 | 0.038738 | Tier 2 | CWSP 2024
35372258 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2 | WDRM v3 | SH | CWSP | 10 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 8.892 | 0 | 8.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 1 | 0.039297 | Tier 2 | CWSP 2024
35372257 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1 | WDRM v3 | SH | CWSP | 10 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 9.808 | 0 | 9.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 1 | 0.039297 | Tier 2 | CWSP 2024
35372461 | CWSP - TIGER CREEK 201 CB & 320746 | WDRM v3 | SH | CWSP | 8 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 |  | 1744 | 0.016801 |  | 8 | 1 | 0.040941 | Tier 2 & 3 | CWSP 2024
35396763 | CWSP - PINE GROVE 1101CB PH 1.3 | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0 | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35353527 | CITADEL WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8221 | -121.5955 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353525 | SHERWOOD CIR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8243 | -121.5994 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353479 | CRESTON DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8211 | -121.6013 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353477 | WYCLIFF WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8192 | -121.6024 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353470 | JOPLIN CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8146 | -121.6066 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353468 | PONDEROSA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8167 | -121.598 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353467 | DREXEL DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8182 | -121.5952 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353466 | W PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8091 | -121.5998 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35353463 | ANDOVER DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8121 | -121.5914 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35342338 | FRRB - BIG BASIN 1102 UG5 LITTLEBASIN CG | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.163 | -122.1902 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35353399 | EUREKA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | PEND | Permitting/Dependency | N | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.5973 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35352075 | BILLE WAGSTAFF | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | 2023 | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7777 | -121.6077 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35350874 | NORWOOD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2023 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7637 | -121.5732 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35350582 | PLUCODIXIE-HIDEAWAY Z7 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | 2023 | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35350519 | PLUCODIXIE-ALTA CAMP Z6 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47348 | 0 | 0.47348 | 2023 | 0 | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35396762 | CWSP - PINE GROVE 1101CB PH 1.2 | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | ESTS | Estimating | Y | Y | 0.07 | 2.91 | 0 | 2.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35342337 | FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1657 | -122.2231 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35342336 | FRRB - BIG BASIN 1102 UG2 CAMPGROUND | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1699 | -122.2026 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35342335 | FRRB - BIG BASIN 1102 UG3 HWY 236 | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1672 | -122.2131 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | FRRB
35222036 | CZUSCRUZ 21600 BIG BASIN, BOULDER CRK | WDRM v2 | FRRB | FRRB | 2359 | V2 Not Top Risk | Fire Rebuild | 95F | PEND | Permitting/Dependency | Y | N | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52462 | 0 | 0 | 0.52462 | 2023 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1676 | -122.2 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0 | 0.0013052 | Tier 3 | 0
35334541 | FRRB -BIG BASIN 1102 12758 P1S2 CYPRESS | WDRM v2 | FRRB | FRRB | 2358 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16629 | 0 | 0.16629 | 2023 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 3 | 0.0026407 | Tier 3 | FRRB
35250987 | X22: XCZUSCRUZ 185 KNOB HILL DR, BOULDER | WDRM v2 | FRRB | 0 | 2358 | V2 Not Top Risk | Fire Rebuild | 95F | UNSC | Ready for Construction | Y | N | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088258 | 0 | 0 | 0.088258 | 2023 | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1376 | -122.1453 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 3 | 0.0026407 | Tier 3 | 0
35275478 | STS-POLE_IDLE_REMV-23600 STATE HWY 9 | WDRM v2 | IF | 0 | 2354 | V2 Not Top Risk | Idle Facilities | 2AF | DCNL | In-Construction | Y | N | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara | 37.2476 | -122.0791 | WDRM v2 |  | 2354 | 0.0029842 |  | 825 | 0 | 0.0029655 | Tier 3 | Idle Facilities
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 2023 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 2023 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35372259 | CWSP - PINE GROVE 1101CB | WDRM v3 | SH | CWSP | 6 | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 1 | 0.047261 | Tier 2 | CWSP 2024
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | WDRM v2 | FRRB | FRRB | 2342 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 2024 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0 | 0.00093756 | Tier 2 | FRRB
35325226 | PSPS PIT NO 3 21011482 PH 2.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9868 | -121.8481 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35325225 | PSPS PIT NO 3 21011482 PH 1.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9729 | -121.7814 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35325224 | PSPS PIT NO 3 2101CB PH 1.2 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 41.0088 | -121.7129 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35294730 | PSPS - PIT NO 3 21011482 PH 2.1 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9685 | -121.8246 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35294729 | PSPS - PIT NO 3 21011482 PH 1.1 | WDRM v2 | SH | CWSP | 2320 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7479 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 2 | 0.0070854 | Tier 2 | PSPS
35128962 | RECOND HWY 20 - FTBRAGG 1102 | WDRM v2 | Other | 0 | 2305 | V2 Not Top Risk | Other | 08J | UNSE | Scoping/Scoped | Y | N | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 2024 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.4154 | -123.7771 | WDRM v2 |  | 2305 | 0.0033857 |  | 2316 | 0 | 0.00037958 | Tier 2 | 0
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | WDRM v2 | SH | PRE | 2271 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.3718 | 0.093561 | 0 | 1.4653 | 0 | 0 | 0 | 0 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.099242 | 0.052841 | 0 | 0.15208 | 2023 | 0.099242 | 0.052841 | 0 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 |  | 2271 | 0.0037571 |  | 558 | 0 | 0.0048336 | Tier 3 | Pre
35318074 | FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | WDRM v2 | FRRB | FRRB | 2246 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29356 | 0 | 0.29356 | 2023 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 |  | 2246 | 0.0041981 |  | 936 | 3 | 0.002497 | Tier 2 | FRRB
35321894 | FRRB - PT MORETTI 1101 12122 PH1 SM4 | WDRM v2 | FRRB | FRRB | 2199 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13826 | 0 | 0.13826 | 2023 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0 | 0.00042654 | Tier 2 | FRRB
35297464 | FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | WDRM v2 | FRRB | FRRB | 2199 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021 | 2023 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0 | 0.00042654 | Tier 2 | FRRB
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | WDRM v2 | SH | 0 | 2192 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.8559 | 0 | 0 | 1.8559 | 1.8402 | 0 | 0 | 1.8402 | 0 | 0 | 0 | 0 | 0.01572 | 0 | 0 | 0.01572 | 2023 | 0.01572 | 0 | 0 | 0.01572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.5056 | -122.9307 | WDRM v2 |  | 2192 | 0.0053427 |  | 1383 | 0 | 0.0011714 | Tier 3 | 0
35284810 | FRRB - HMB 1103 SM CO LR6012 PUMP HOUSE | WDRM v2 | FRRB | FRRB | 2186 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 2024 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2086 | -122.3251 | WDRM v2 |  | 2186 | 0.0054078 |  | 2434 | 0 | 0.00033154 | Tier 2 | FRRB
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | WDRM v2 | SH | PSPS | 2123 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.24 | 2023 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 |  | 2123 | 0.0065148 |  | 1979 | 0 | 0.00055552 | Tier 2 | PSPS - Community Resiliency
35244173 | DR-COND_IDLE_REMV-5260 GRANITE CREEK RD | WDRM v2 | IF | 0 | 2116 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 2023 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7888 | -120.9206 | WDRM v2 |  | 2116 | 0.0066099 |  | 237 | 3 | 0.011346 | Tier 2 | Idle Facilities
35342339 | FRRB - BIG BASIN 1102 UG6 BB VINEYARD | WDRM v2 | FRRB | FRRB | 2070 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0 | 0.16193 | 2023 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 |  | 2070 | 0.0075562 |  | 1413 | 0 | 0.0011281 | Tier 3 | FRRB
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | WDRM v2 | FRRB | FRRB | 2055 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 2023 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0 | 0.0002898 | Tier 2 | FRRB - UG - 2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | WDRM v2 | FRRB | FRRB | 2055 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.5239 | 0 | 2.5239 | 0 | 0 | 0 | 0 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0.88277 | 0 | 0.88277 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0 | 0.0002898 | Tier 2 | FRRB - UG - 2021
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35223063 | PSPS - DUNBAR 1101 - OAKMONT | WDRM v2 | SH | PSPS | 2048 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0.3197 | 2023 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0 | 0.00012812 | Tier 2 | PSPS - Community Resiliency
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 | WDRM v2 | FRRB | FRRB | 2005 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8075 | -120.0935 | WDRM v2 |  | 2005 | 0.0089565 |  | 2299 | 0 | 0.00038767 | Tier 2 | FRRB
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | DOCC | In-Construction | Y | Y | 2.3513 | 0.44621 | 0 | 2.7975 | 0 | 0 | 0 | 0 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 2023 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 2.8136 | 0.37955 | 0 | 3.1932 | 0 | 0 | 0 | 0 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.61288 | 0.33883 | 0 | 0.9517 | 2023 | 0.61288 | 0.33883 | 0 | 0.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62519 | 2.2513 | 0 | 2.8765 | 2023 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | WDRM v2 | SH | PSS | 1946 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 1.7455 | 0.57576 | 0 | 2.3212 | 0 | 0 | 0 | 0 | 1.6231 | 0 | 0 | 1.6231 | 0.12235 | 0.57576 | 0 | 0.69811 | 2024 | 0 | 0 | 0 | 0 | 0.12235 | 0.57576 | 0 | 0.69811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 1 | 0.022482 | Tier 3 | PSS Approved
35223241 | DR~STS-COND_IDLE_REMV-R/O 5500 ALPINE R | WDRM v2 | IF | 0 | 1917 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Portola Valley | San Mateo | 37.3567 | -122.2181 | WDRM v2 |  | 1917 | 0.011065 |  | 630 | 2 | 0.0042054 | Tier 2 | Idle Facilities
35320462 | PSPS - JAMESON 1105371694 | WDRM v2 | SH | PSPS | 1848 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2642 | -122.1295 | WDRM v2 |  | 1848 | 0.012819 |  | 8953 | 0 |  | Tier 2 | PSPS - 2023 ICUG
35120413 | DR-STS-COND_IDLE_REMV78TOYONDRIVE | WDRM v2 | IF | 0 | 1837 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020455 | 0.020455 | 2023 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Fairfax | Marin | 37.9797 | -122.6039 | WDRM v2 |  | 1837 | 0.013281 |  | 1001 | 0 | 0.0022627 | Tier 3 | Idle Facilities
35275962 | STS-COND_IDLE_REMV-1W/O 14508 WONDERLAND | WDRM v2 | IF | 0 | 1828 | V2 Not Top Risk | Idle Facilities | 2BF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 2023 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.7096 | -122.3366 | WDRM v2 |  | 1828 | 0.013687 |  | 838 | 0 | 0.002921 | Tier 2 | Idle Facilities
35343741 | PSPS - DUNBAR 1101 440 PH 1.3 | WDRM v2 | SH | PSPS | 1827 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3371 | -122.4929 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0 | 0.0063584 | Tier 2 & 3 | PSPS - 2023 ICUG
35312542 | PSPS - DUNBAR 1101 440 PH 1.1 | WDRM v2 | SH | PSPS | 1827 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Glen Ellen | Sonoma | 38.3791 | -122.5192 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0 | 0.0063584 | Tier 2 & 3 | PSPS - 2023 ICUG
35294728 | PSPS - PIT NO 3 2101CB PH 1.1 | WDRM v2 | SH | CWSP | 1816 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7478 | WDRM v2 |  | 1816 | 0.01407 |  | 326 | 2 | 0.0086689 | Tier 2 | PSPS
35211297 | DR~STS-COND_IDLE_REMV-2000 PONDEROSA WY | WDRM v2 | IF | 0 | 1801 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21326 | 0.21326 | 2023 | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.02 | -120.944 | WDRM v2 |  | 1801 | 0.014579 |  | 142 | 1 | 0.015811 | Tier 2 | Idle Facilities
35221715 | STS-COND_IDLE_REMV-20599 KINGS CT | WDRM v2 | IF | 0 | 1770 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0.041288 | 2023 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Soulsbyville | Tuolumne | 37.9965 | -120.2635 | WDRM v2 |  | 1770 | 0.015509 |  | 2025 | 0 | 0.00052763 | Tier 2 | Idle Facilities
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | WDRM v2 | FRRB | FRRB | 1748 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 |  | 1748 | 0.016728 |  | 521 | 3 | 0.0051671 | Tier 2 | FRRB
35145001 | PSPS - CLAYTON 2215 - CB | WDRM v2 | SH | PSPS | 1739 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 2024 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.931 | -121.9736 | WDRM v2 |  | 1739 | 0.016935 |  | 1812 | 0 | 0.0006705 | Tier 2 & 3 | PSPS - Community Resiliency
35121520 | NR7 OFAC_IDLE_REMV-LAKEVIEW RD-14LOC | WDRM v2 | IF | 0 | 1722 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65606 | 0.65606 | 2023 | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8122 | -122.3073 | WDRM v2 |  | 1722 | 0.017574 |  | 247 | 1 | 0.010915 | Tier 2 | Idle Facilities
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 1.85 | 2023 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 |  | 1703 | 0.018088 |  | 933 | 0 | 0.0025042 | Tier 2 | PSPS
35329012 | PSPS CLARK ROAD 1102 LR514690 PH 2.2 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 2023 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0 | 0.0022353 | Tier 2 | PSPS
35299633 | PSPS CLARK ROAD 1102 LR514690 PH 2.1 | WDRM v2 | SH | PSPS | 1703 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 2023 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0 | 0.0022353 | Tier 2 | PSPS
35244150 | FT-COND_IDLE_REMV-D/P R/O 19182 GERMAN | WDRM v2 | IF | 0 | 1700 | V2 Not Top Risk | Idle Facilities | 2AF | ESTS | Estimating | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.437 | -120.8154 | WDRM v2 |  | 1700 | 0.018204 |  | 41 | 1 | 0.023951 | Tier 3 | Idle Facilities
35284023 | FRRB - DUNBAR 1101416 | WDRM v2 | FRRB | FRRB | 1684 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 | WDRM v2 |  | 1684 | 0.019316 |  | 732 | 0 | 0.0035071 | Tier 3 | FRRB - UG - 2021
35208054 | STS-COND_IDLE_REMV-BAYNE RD | WDRM v2 | IF | 0 | 1666 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14867 | 0.14867 | 2023 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7975 | -120.8281 | WDRM v2 |  | 1666 | 0.020262 |  | 68 | 1 | 0.020612 | Tier 2 | Idle Facilities
35295446 | FRRB - BUCKS CREEK 1103 CB PH2 | WDRM v2 | FRRB | FRRB | 1658 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 2023 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 39.8957 | -121.2789 | WDRM v2 |  | 1658 | 0.020623 |  | 404 | 2 | 0.0069107 | Tier 2 & 3 | FRRB
35335235 | PSPS - SILVERADO 2104708 | WDRM v2 | SH | PSPS | 1648 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5192 | -122.4719 | WDRM v2 |  | 1648 | 0.02118 |  | 619 | 1 | 0.0043024 | Tier 3 | PSPS - 2023 ICUG
35280505 | HWY 299 SHASTA R20A | WDRM v2 | Other | 0 | 1614 | V2 Not Top Risk | Other | 30A | ESTS | Estimating | Y | Y | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5923 | -122.4836 | WDRM v2 |  | 1614 | 0.022607 |  | 43 | 2 | 0.023649 | Tier 3 | Other
35211659 | DR-COND_IDLE_REMV-14932 MOONSHINE RD | WDRM v2 | IF | 0 | 1590 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0.030303 | 2023 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.3894 | -121.0978 | WDRM v2 |  | 1590 | 0.023389 |  | 149 | 2 | 0.015567 | Tier 3 | Idle Facilities
35224856 | BR-12-5A HWY 191 RELOCATION, PARB | WDRM v2 | Other | 0 | 1537 | V2 Not Top Risk | Other | 10K | CONS | In-Construction | Y | Y | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 2024 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | WDRM v2 |  | 1537 | 0.025842 |  | 362 | 2 | 0.0076725 | Tier 2 & 3 | Other
35329016 | PSPS CLARK ROAD 1102 LR47006 PH 1.2 | WDRM v2 | SH | PSPS | 1535 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 2023 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 2 | 0.022808 | Tier 2 | PSPS
35299635 | PSPS CLARK ROAD 1102 LR47006 PH 1.1 | WDRM v2 | SH | PSPS | 1535 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 2 | 0.022808 | Tier 2 | PSPS
35245152 | FRRB - KANAKA 1101 - K4 PH 4.17 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35245141 | FRRB - KANAKA 1101 - K4 PH 4.6 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35244699 | FRRB - KANAKA 1101 - K4 PH 4.4 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35244698 | FRRB - KANAKA 1101 - K4 PH 4.3 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35236989 | FRRB - KANAKA 1101 - K2 PH2.2 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - OH - 2021
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655 | 2023 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - REMG - 2021
35235704 | FRRB - KANAKA 1101 - K5 PH5.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG - 2021
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | WDRM v2 | FRRB | FRRB | 1480 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 2 | 0.01209 | Tier 3 | FRRB - UG - 2021
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 2023 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35320466 | CWSP - WILLOW CREEK 11032936 | WDRM v2 | SH | CWSP | 1474 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Salyer | Trinity | 40.8669 | -123.5148 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | CWSP - 2023 ICUG
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0199 | 0 | 1.0199 | 2023 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297697 | FRRB - WILLOW CREEK 11032936 UG TL3 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014773 | 0 | 0.014773 | 2023 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996 | 2023 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 2023 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 2023 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2023 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6598 | 0 | 4.6598 | 2023 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35281816 | FRRB - WILLOW CREEK 11032936 ML2OHBRIDGE | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046591 | 0 | 0 | 0.046591 | 2023 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | WDRM v2 | FRRB | FRRB | 1474 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45985 | 0 | 0.45985 | 2023 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0 | 0.0024804 | Tier 2 | FRRB
35264104 | DRSTS-OFAC_IDLE_REMV-7NE/O 15921 STATE H | WDRM v2 | IF | 0 | 1446 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0.10549 | 2023 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5593 | -120.8348 | WDRM v2 |  | 1446 | 0.030867 |  | 254 | 2 | 0.010591 | Tier 3 | Idle Facilities
35150991 | T2-POLE_IDLE_REMV - GIBNEY DR MIRANDA*RM | WDRM v2 | IF | 0 | 1429 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072159 | 0.072159 | 2023 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt | 40.2188 | -123.8212 | WDRM v2 |  | 1429 | 0.031951 |  | 2354 | 0 | 0.00036401 | Tier 2 | Idle Facilities
35243441 | REMG 17 - CHALLENGE 1102, PONDEROSA WAY | WDRM v2 | SH | REMG | 1428 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.483 | -121.2466 | WDRM v2 |  | 1428 | 0.032082 |  | 408 | 2 | 0.0068437 | Tier 2 & 3 | REMG 2022-2023
35290901 | EP BICKFORD RANCH RD WATER TANK LINCOLN | WDRM v2 | Other | 0 | 1408 | V2 Not Top Risk | Other | 16H | CONS | In-Construction | Y | N | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64432 | 0 | 0 | 0.64432 | 2023 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer |  |  | WDRM v2 |  | 1408 | 0.032911 |  | 2686 | 0 | 0.0002367 | Tier 2 | 0
35242865 | DR~STS-COND_IDLE_REMV-410 STAR HILL RD | WDRM v2 | IF | 0 | 1376 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.4126 | -122.3299 | WDRM v2 |  | 1376 | 0.034933 |  | 1131 | 0 | 0.0018648 | Tier 3 | Idle Facilities
35353435 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.4 | WDRM v2 | SH | REMG | 1363 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9081 | -120.8468 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | WDRM v2 | SH | PSPS | 1363 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84962 | 0.52121 | 1.3708 | 2023 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | WDRM v2 | SH | PSPS | 1363 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73144 | 0 | 0.73144 | 2023 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 2 | 0.0099544 | Tier 3 | PSPS - Community Resiliency
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | WDRM v2 | FRRB | FRRB | 1322 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86989 | 0 | 0.86989 | 2023 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0 | 0.0020497 | Tier 2 | FRRB
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | WDRM v2 | FRRB | FRRB | 1322 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5902 | 0 | 2.5902 | 2023 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0 | 0.0020497 | Tier 2 | FRRB
35145540 | PSPS - FROGTOWN 1702 - CB | WDRM v2 | SH | PSPS | 1316 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61212 | 0.53447 | 0 | 1.1466 | 2023 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 |  | 1316 | 0.039234 |  | 1205 | 0 | 0.0016222 | Tier 3 | PSPS - Scoped
35251360 | MIRABEL 1101 - RECONDUCTOR 3,338 FT | WDRM v2 | Other | 0 | 1313 | V2 Not Top Risk | Other | 06E | PEND | Permitting/Dependency | Y | N | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34261 | 0 | 0 | 0.34261 | 2023 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.4736 | -122.8979 | WDRM v2 |  | 1313 | 0.039363 |  | 1448 | 0 | 0.001078 | Tier 2 | 0
35243442 | REMG 130 - PIKE CITY 1102, TAHOE NF | WDRM v2 | SH | REMG | 1308 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | North San Juan | Sierra | 39.4385 | -120.9959 | WDRM v2 |  | 1308 | 0.03956 |  | 162 | 2 | 0.0147 | Tier 3 | REMG 2022-2023
35083699 | *CANC*STS-COND_IDLE_REMV-38113 PETERSON | WDRM v2 | IF | 0 | 1302 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 2023 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0361 | -119.3341 | WDRM v2 |  | 1302 | 0.040157 |  | 348 | 3 | 0.0080497 | Tier 3 | Idle Facilities
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 0 | 0.31004 | 2023 | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 2023 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.070076 | 0 | 0.070076 | 2023 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | DOCC | In-Construction | Y | Y | 0 | 1.8256 | 0 | 1.8256 | 0 | 0 | 0 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0.00625 | 0 | 0.00625 | 2023 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 |  | 1299 | 0.040282 |  | 250 | 0 | 0.010796 | Tier 3 | FRRB - UG - 2021
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 0 | 0.28409 | 2023 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - REMG - 2021
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 2023 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | WDRM v2 | FRRB | FRRB | 1299 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0 | 0.30303 | 2023 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0 | 0.0051219 | Tier 3 | FRRB - UG - 2021
35038684 | REMV IDLE 4 LOCS 48600 VALLEY DR LAY | WDRM v2 | IF | 0 | 1293 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16818 | 0.16818 | 2023 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | Mendocino | 39.7297 | -123.5078 | WDRM v2 |  | 1293 | 0.040695 |  | 992 | 0 | 0.0022826 | Tier 2 | Idle Facilities
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | WDRM v2 | FRRB | FRRB | 1285 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 2023 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 1285 | 0.041237 |  | 2987 | 0 | 0.00013567 | Tier 2 | FRRB
35208094 | FT STS-TRAN_IDLE_REMV-2W/O6NW/O 7251 WIL | WDRM v2 | IF | 0 | 1237 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079735 | 0.079735 | 2023 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.1679 | -124.0858 | WDRM v2 |  | 1237 | 0.044439 |  | 2057 | 0 | 0.00051421 | Tier 2 | Idle Facilities
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | WDRM v2 | FRRB | FRRB | 1172 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 2023 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 |  | 1172 | 0.050559 |  | 785 | 0 | 0.0031715 | Tier 2 & 3 | FRRB
35332870 | PSPS - CURTIS 1701 CB PH 1.3 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38674 | 0 | 0.38674 | 2023 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35332868 | PSPS - CURTIS 1701 CB PH 1.2 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 2.5299 | 2023 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35312541 | PSPS - CURTIS 1701 CB PH 1.1 | WDRM v2 | SH | PSPS | 1166 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0.42992 | 2023 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0 | 0.0021952 | Tier 2 | PSPS - 2023 ICUG
35283938 | CWSP - WOODSIDE 1101 FS 775939 PH 1.1 | WDRM v2 | SH | CWSP | 1145 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3845 | -122.2937 | WDRM v2 |  | 1145 | 0.05299 |  | 1026 | 0 | 0.0021738 | Tier 3 | CWSP 2022-2023
35399833 | PSPS - SAN LUIS OBISPO 1101 PH 1.2 | WDRM v2 | SH | PSPS | 1104 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.33 | 1.33 | 2023 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2752 | -120.6435 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0 | 0.00059698 | Tier 2 | PSPS - 2023 ICUG
35320444 | PSPS - SAN LUIS OBISPO 1101 PH 1.1 | WDRM v2 | SH | PSPS | 1104 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 2024 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2683 | -120.6383 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0 | 0.00059698 | Tier 2 | PSPS - 2023 ICUG
35341551 | REMG 499 - PIT NO 7 1101 | WDRM v2 | SH | 0 | 1055 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.8417 | -122.0114 | WDRM v2 |  | 1055 | 0.060819 |  | 549 | 0 | 0.0049268 | Tier 2 | 0
35338402 | PSPS - PANORAMA 1101 CB PH 1.2 | WDRM v2 | SH | PSPS | 1038 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 2023 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | PSPS - 2023 ICUG
35320464 | PSPS - PANORAMA 1101 CB PH 1.1 | WDRM v2 | SH | PSPS | 1038 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 2023 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | PSPS - 2023 ICUG
35244146 | FT-COND_IDLE_REMV-6935-6963 MORNING CAN | WDRM v2 | IF | 0 | 1035 | V2 Not Top Risk | Idle Facilities | 2AF | MAPP | In-Construction | Y | N | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04072 | 0.04072 | 2023 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6211 | -120.7249 | WDRM v2 |  | 1035 | 0.06292 |  | 436 | 2 | 0.0063805 | Tier 2 | Idle Facilities
35384087 | PSPS - CLARK ROAD 1102 LR514690 PH 1.4 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6578 | -121.5657 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35329015 | REMG 794 - CLARK ROAD 1102 | WDRM v2 | SH | REMG | 1033 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6575 | -121.5646 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35329014 | PSPS CLARK ROAD 1102 LR514690 PH 1.2 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701 | 2023 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35299634 | PSPS CLARK ROAD 1102 LR514690 PH 1.1 | WDRM v2 | SH | PSPS | 1033 | V2 Not Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799 | 2023 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0 | 0.0036217 | Tier 2 | PSPS
35277147 | STS-POLE_IDLE_REMV-GREELY HILL RD CO#423 | WDRM v2 | IF | 0 | 1019 | V2 Not Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40871 | 0.40871 | 2023 | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | Mariposa | 37.7302 | -120.182 | WDRM v2 |  | 1019 | 0.065187 |  | 433 | 0 | 0.0064317 | Tier 2 | Idle Facilities
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | WDRM v2 | SH | PSPS | 999 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | WDRM v2 |  | 999 | 0.067405 |  | 2578 | 0 | 0.0002828 | Tier 2 | PSPS - Community Resiliency
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0644 | 0 | 3.0644 | 2023 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17159 | 0 | 0.17159 | 2023 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49451 | 0 | 0.49451 | 2023 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0.97992 | 2023 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | WDRM v2 | FRRB | FRRB | 995 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 2023 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0 | 0.00047036 | Tier 2 | FRRB
35211643 | DR-STS-COND_IDLE_REMV-6 PLS W/O 11554 ON | WDRM v2 | IF | 0 | 981 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24489 | 0.24489 | 2023 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6201 | -122.4409 | WDRM v2 |  | 981 | 0.069495 |  | 957 | 0 | 0.0024201 | Tier 2 | Idle Facilities
35343398 | PSPS - WYANDOTTE 1110 LR980944 PH1.10 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5169 | -121.5161 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343397 | PSPS - WYANDOTTE 1110 LR980944 PH1.9 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5082 | -121.5038 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343396 | PSPS - WYANDOTTE 1110 LR980944 PH1.8 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0822 | 0 | 1.0822 | 2023 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343395 | PSPS - WYANDOTTE 1110 LR980944 PH1.7 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 2023 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35343394 | PSPS - WYANDOTTE 1110 LR980944 PH1.6 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 1.17 | 2023 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331309 | REMG 801 - WYANDOTTE 1110, OROVILLE DAM | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5255 | -121.4817 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | 2023 ICUG
35331308 | PSPS WYANDOTTE 1110 LR980944 PH1.4 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0.82 | 2023 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331307 | PSPS WYANDOTTE 1110 LR980944 PH1.3 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 2023 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35331306 | PSPS WYANDOTTE 1110 LR980944 PH1.2 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5178 | -121.4854 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35312560 | PSPS WYANDOTTE 1110 LR980944 PH1.1 | WDRM v2 | SH | PSPS | 976 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 3.61 | 2023 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0 | 0.00070123 | Tier 2 | PSPS - 2023 ICUG
35254948 | X22: CWSP - VOLTA 11011596 - PH1.6 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9803 | 0 | 0 | 0.9803 | 2023 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254947 | CWSP - VOLTA 11011596 - PH1.5 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.263 | 0 | 0.263 | 2023 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254946 | X22: CWSP - VOLTA 11011596 - PH1.4 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 2023 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35254945 | CWSP - VOLTA 11011596 - PH1.3 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 2023 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35243453 | X22: CWSP-VOLTA-11011596-PH1 | WDRM v2 | SH | CWSP | 966 | V2 Not Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.428 | 0 | 0 | 1.428 | 0 | 0 | 0 | 0 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205 | 2023 | 0.34205 | 0 | 0 | 0.34205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 2 | 0.0099219 | Tier 2 | CWSP 2022-2023
35227033 | PUEBLO 2102, DRY CREEK | WDRM v2 | SH | ECOP | 951 | V2 Not Top Risk | Base SH | 08W | APPR | Estimating | Y | N | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.433 | -122.4021 | WDRM v2 |  | 951 | 0.073389 |  | 338 | 0 | 0.0083787 | Tier 3 | ECOP
35224438 | #+STS-COND_IDLE_REMV-SUDDEN RANCH AT RR | WDRM v2 | IF | 0 | 949 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017235 | 0.017235 | 2023 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | Santa Barbara | 34.5386 | -120.5365 | WDRM v2 |  | 949 | 0.073569 |  | 2028 | 0 | 0.00052681 | Tier 2 | Idle Facilities
35292758 | FRRB BIG MEADOWS 2101 CB PH1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | N | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 2023 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2786 | 0 | 1.2786 | 2023 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 2023 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 2023 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | CONS | In-Construction | Y | Y | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 2023 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 3 | 0.0046735 | Tier 2 | FRRB
35280493 | FRRB -BIG MEADOWS 21012260 UG TL 1.13 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12008 | 0.35 | 0 | 0.47008 | 2023 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0 | 0.0046735 | Tier 2 | FRRB
35279985 | FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | WDRM v2 | FRRB | FRRB | 916 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.115 | 0 | 3.115 | 2023 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0 | 0.0046735 | Tier 2 | FRRB
35280498 | FRRB - CRESCENT MILLS 21012056 OH TL 1.1 | WDRM v2 | FRRB | FRRB | 895 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 2023 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 3 | 0.0028532 | Tier 2 | FRRB
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | WDRM v2 | FRRB | FRRB | 895 | V2 Not Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008 | 2023 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 3 | 0.0028532 | Tier 2 | FRRB
35145458 | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS | WDRM v2 | IF | 0 | 882 | V2 Not Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6263 | 1.6263 | 2023 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.758 | -120.0408 | WDRM v2 |  | 882 | 0.08233 |  | 550 | 0 | 0.0049103 | Tier 2 | Idle Facilities
35235674 | FRRB - BIG BEND 1102 - B1 PH1.1 | WDRM v2 | FRRB | FRRB | 865 | V2 Not Top Risk | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | N | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 865 | 0.084888 |  | 187 | 1 | 0.013302 | Tier 3 | FRRB - UG - 2021
35221620 | STS-COND_IDLE_REMV-12345 HERITAGE WAY | WDRM v2 | IF | 0 | 854 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 2023 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Gilroy | Santa Clara | 37.0533 | -121.6625 | WDRM v2 |  | 854 | 0.085689 |  | 1052 | 0 | 0.0020756 | Tier 2 | Idle Facilities
35297984 | REMG 368 - STILLWATER 1101 | WDRM v2 | FRRB | FRRB | 851 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 | WDRM v2 |  | 851 | 0.085979 |  | 2266 | 0 | 0.00040165 | Tier 2 | FRRB
35190945 | EP 2951 HIGHWAY 4 MURPHYS WAGON TRAIL | WDRM v2 | Other | 0 | 838 | V2 Not Top Risk | Other | 10Q | CONS | In-Construction | Y | N | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1169 | 0 | 0 | 1.1169 | 2023 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | Calaveras |  |  | WDRM v2 |  | 838 | 0.088153 |  | 1734 | 0 | 0.00073728 | Tier 2 | 0
35332718 | PEORIA 1705 RECONDUCTORING | WDRM v2 | Other | 0 | 835 | V2 Not Top Risk | Other | 06H | ESTS | Estimating | Y | N | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 2024 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne | 37.8663 | -120.4293 | WDRM v2 |  | 835 | 0.088489 |  | 1778 | 0 | 0.00070132 | Tier 2 | 0
35204814 | DR-COND_IDLE_REMV-14820 FERN RD | WDRM v2 | IF | 0 | 820 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21023 | 0.21023 | 2023 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6759 | -121.971 | WDRM v2 |  | 820 | 0.09042 |  | 1536 | 0 | 0.00093567 | Tier 2 & 3 | Idle Facilities
74010582 | GREEN VALLEY RD EL DORADO CNTY R20A | WDRM v2 | Other | 0 | 811 | V2 Not Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | WDRM v2 |  | 811 | 0.092281 |  | 1184 | 0 | 0.0016787 | Tier 2 | Other
35173857 | SILVERADO 2104_RECONDUCTOR NEAR FUSE 797 | WDRM v2 | Other | 0 | 792 | V2 Not Top Risk | Other | 06E | CONS | In-Construction | Y | N | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 | 0.18939 | 2023 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5866 | -122.4424 | WDRM v2 |  | 792 | 0.094959 |  | 59 | 1 | 0.021383 | Tier 3 | 0
35211230 | DRCOND_IDLE_REMV-5726 EVERGLADE | WDRM v2 | IF | 0 | 774 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061174 | 0.061174 | 2023 | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2454 | -121.3989 | WDRM v2 |  | 774 | 0.098287 |  | 3122 | 0 | 0.00010395 | Tier 2 | Idle Facilities
35221249 | DR~STS-OFAC_IDLE_REMV - 1/N/O/AT 908 ORE | WDRM v2 | IF | 0 | 771 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 2023 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5519 | -121.5068 | WDRM v2 |  | 771 | 0.098498 |  | 1281 | 0 | 0.0013786 | Tier 2 | Idle Facilities
35217564 | DR-COND_IDLE_REMV - 1PWO 11188 TOWNSHIP | WDRM v2 | IF | 0 | 758 | V2 Not Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2864 | -121.3535 | WDRM v2 |  | 758 | 0.10087 |  | 2091 | 0 | 0.00049399 | Tier 2 | Idle Facilities
35221659 | STS-COND_IDLE_REMV-1N/O 2W/O 10835 WATER | WDRM v2 | IF | 0 | 744 | V2 Not Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15076 | 0.15076 | 2023 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Ione | Amador | 38.3665 | -120.9291 | WDRM v2 |  | 744 | 0.10338 |  | 2444 | 0 | 0.00032629 | Tier 2 | Idle Facilities
35342151 | PSPS - JAMESON 1102 LR65516 1.9 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 2023 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342150 | PSPS - JAMESON 1102 LR65516 1.8 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2623 | -122.1638 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342148 | PSPS - JAMESON 1102 LR65516 1.7 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 1.19 | 2023 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342147 | PSPS - JAMESON 1102 LR65516 1.6 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8259 | 0 | 1.8259 | 2023 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342146 | PSPS - JAMESON 1102 LR65516 1.5 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.397 | 0 | 2.397 | 2023 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342145 | PSPS - JAMESON 1102 LR65516 1.4 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16307 | 0 | 0.16307 | 2023 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342144 | PSPS - JAMESON 1102 LR65516 1.3 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.617 | 0 | 1.617 | 2023 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35342143 | PSPS - JAMESON 1102 LR65516 1.2 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 2023 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35320442 | PSPS - JAMESON 1102 LR65516 1.1 | WDRM v2 | SH | PSPS | 739 | V2 Not Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38693 | 0 | 0.38693 | 2023 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 |  | 739 | 0.104 |  | 313 | 1 | 0.0089196 | Tier 2 | PSPS - 2023 ICUG
35337015 | CWSP - JAMESON 1105 LR9472 PH 1.4 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 0 | 0.48996 | 2023 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | CWSP - 2023 ICUG
35337014 | CWSP - JAMESON 1105 LR9472 PH 1.3 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.020076 | 0 | 0.85 | 2023 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | CWSP - 2023 ICUG
35337013 | CWSP - JAMESON 1105 LR9472 PH 1.2 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1517 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | 2023 ICUG
35320459 | CWSP - JAMESON 1105 LR9472 PH 1.1 | WDRM v2 | SH | CWSP | 724 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.157 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0 | 0.00057842 | Tier 2 | 2023 ICUG
35329011 | PSPS CLARK ROAD 1102 LR81296 PH 1.4 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3229 | 0 | 2.3229 | 2023 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35329010 | PSPS CLARK ROAD 1102 LR81296 PH 1.3 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.814 | 0.020076 | 2.8341 | 2023 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35329009 | PSPS CLARK ROAD 1102 LR81296 PH 1.2 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94091 | 0.020076 | 0.96098 | 2023 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35299631 | PSPS CLARK ROAD 1102 LR81296 PH 1.1 | WDRM v2 | SH | PSPS | 698 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4299 | 0 | 3.4299 | 2023 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 2 | 0.0021691 | Tier 2 | PSPS
35342310 | PSPS - TEJON 11023751 PH 2.4 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.357 | 0 | 1.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35342308 | PSPS - TEJON 11023751 PH 2.3 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.997 | 0 | 2.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8868 | -118.9361 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35342307 | PSPS - TEJON 11023751 PH 2.2 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.252 | 0 | 2.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8833 | -118.9271 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35335289 | PSPS - TEJON 1102 LR3751 PH 1.3 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.5775 | 0 | 1.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35335288 | PSPS - TEJON 1102 LR3751 PH 1.2 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9158 | -118.9258 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35321445 | PSPS - TEJON 11023751 PH 2.1 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35312554 | PSPS - TEJON 1102 LR3751 PH 1.1 | WDRM v2 | SH | PSPS | 691 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9321 | -118.9283 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 2 | 0.0075263 | Tier 2 | PSPS - 2023 ICUG
35207962 | FT-COND_IDLE_REMV-13080 FERN RD EAST | WDRM v2 | IF | 0 | 678 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 2023 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6587 | -121.8939 | WDRM v2 |  | 678 | 0.11449 |  | 1076 | 0 | 0.0020262 | Tier 2 | Idle Facilities
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | WDRM v2 | SH | WDDB | 666 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.0733 | 0 | 0 | 1.0733 | 0 | 0 | 0 | 0 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049 | 2023 | 0.78049 | 0 | 0 | 0.78049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6824 | -120.8551 | WDRM v2 |  | 666 | 0.11621 |  | 775 | 0 | 0.0032085 | Tier 2 | Top 20% MAVF CPZ
35339665 | CWSP - HORSESHOE 1101 LR50140 PH 1.4 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75909 | 0 | 0.75909 | 2023 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35339664 | CWSP - HORSESHOE 1101 LR50140 PH 1.3 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75208 | 0.17008 | 0 | 0.92216 | 2023 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35339663 | CWSP - HORSESHOE 1101 LR50140 PH 1.2 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | 2023 ICUG
35320447 | CWSP - HORSESHOE 1101 LR50140 PH 1.1 | WDRM v2 | SH | CWSP | 661 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0.83996 | 0 | 1.9299 | 2023 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0 | 0.00028839 | Tier 2 | CWSP - 2023 ICUG
35335287 | PSPS - TEJON 1102 LR2455 PH 1.3 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8466 | -118.8987 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35335286 | PSPS - TEJON 1102 LR2455 PH 1.2 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8542 | -118.893 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35312553 | PSPS - TEJON 1102 LR2455 PH 1.1 | WDRM v2 | SH | PSPS | 642 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8837 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 2 | 0.020158 | Tier 2 | PSPS - 2023 ICUG
35246501 | REMG 44-FULTON 1107, PEPPERWOOD PRESERVE | WDRM v2 | SH | REMG | 637 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0994 | 7.0994 | 2023 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5702 | -122.6772 | WDRM v2 |  | 637 | 0.12169 |  | 1034 | 0 | 0.0021304 | Tier 3 | REMG 2022-2023
35149235 | 8/31-REMV IDLE 6 LOCS 13311 HWY 29 | WDRM v2 | IF | 0 | 626 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16515 | 0.16515 | 2023 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8612 | -122.6264 | WDRM v2 |  | 626 | 0.12376 |  | 582 | 1 | 0.0045905 | Tier 2 | Idle Facilities
35274596 | CWSP MARIPOSA 2101 LR 309438 PH 1.3 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4889 | -119.9738 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35274595 | CWSP MARIPOSA 2101 LR 309438 PH 1.2 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0.057 | 2023 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4983 | -119.9732 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35250572 | CWSP - MARIPOSA 2101 LR 309438 PH1.1 | WDRM v2 | SH | CWSP | 605 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5026 | -119.9886 | WDRM v2 |  | 605 | 0.12966 |  | 565 | 2 | 0.0047998 | Tier 2 | CWSP 2022-2023
35317937 | CWSP HARTLEY 1101 LR336932 1.10 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0436 | -122.9704 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317936 | CWSP HARTLEY 1101 LR336932 1.9 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0402 | -122.9674 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317935 | CWSP HARTLEY 1101 LR336932 1.8 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0405 | -122.9316 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317934 | CWSP HARTLEY 1101 LR336932 1.7 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.041 | -122.9443 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317932 | CWSP HARTLEY 1101 LR336932 1.6 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.044 | -122.9654 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317931 | CWSP HARTLEY 1101 LR336932 1.5 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0439 | -122.9625 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317930 | CWSP HARTLEY 1101 LR336932 1.4 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317929 | CWSP HARTLEY 1101 LR336932 1.3 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35317928 | CWSP HARTLEY 1101 LR336932 1.2 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0406 | -122.9405 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35250574 | CWSP HARTLEY 1101 LR336932 1.1 | WDRM v2 | SH | CWSP | 593 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0512 | -122.9379 | WDRM v2 |  | 593 | 0.13303 |  | 1213 | 2 | 0.0015984 | Tier 2 | CWSP 2022-2023
35332866 | PSPS - JESSUP 1103 LR348657 PH 1.4 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 2023 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 |  | 590 | 0.13388 |  | 2153 | 0 | 0.00046034 | Tier 2 | PSPS - 2023 ICUG
35332864 | PSPS - JESSUP 1103 LR348657 PH 1.3 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5058 | -122.2644 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35332863 | PSPS - JESSUP 1103 LR348657 PH 1.2 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4921 | -122.2838 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35312549 | PSPS - JESSUP 1103 LR348657 PH 1.1 | WDRM v2 | SH | PSPS | 590 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 2023 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0 | 0.00016206 | Tier 2 | PSPS - 2023 ICUG
35342318 | PSPS - TEJON 1102 LR732836 PH 2.5 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8363 | -118.8637 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342317 | PSPS - TEJON 1102 LR732836 PH 2.4 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8295 | -118.8723 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342316 | PSPS - TEJON 1102 LR732836 PH 2.3 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.837 | -118.8663 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342315 | PSPS - TEJON 1102 LR732836 PH 2.2 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8407 | -118.8677 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342314 | PSPS - TEJON 1102 LR732836 PH 1.5 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8594 | -118.8797 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342313 | PSPS - TEJON 1102 LR732836 PH 1.4 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8835 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342312 | PSPS - TEJON 1102 LR732836 PH 1.3 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8726 | -118.8905 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35342311 | PSPS - TEJON 1102 LR732836 PH 1.2 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8765 | -118.8926 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35320607 | PSPS - TEJON 1102 LR732836 PH 2.1 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.846 | -118.872 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35312555 | PSPS - TEJON 1102 LR732836 PH 1.1 | WDRM v2 | SH | PSPS | 583 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 2 | 0.011818 | Tier 2 | PSPS - 2023 ICUG
35364450 | PSPS - VOLTA 11011516 PH 1.17 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.496 | 0 | 0 | 1.496 | 2023 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364448 | PSPS - VOLTA 11011516 PH 1.16 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364446 | PSPS - VOLTA 11011516 PH 1.15 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.057008 | 2.5381 | 0 | 2.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364442 | PSPS - VOLTA 11011516 PH 1.14 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364440 | PSPS - VOLTA 11011516 PH 1.13 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364339 | PSPS - VOLTA 11011516 PH 1.12 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364337 | PSPS - VOLTA 11011516 PH 1.11 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364336 | PSPS - VOLTA 11011516 PH 1.10 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8561 | 0 | 1.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364334 | PSPS - VOLTA 11011516 PH 1.9 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364333 | PSPS - VOLTA 11011516 PH 1.8 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8131 | 0 | 2.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35364332 | PSPS - VOLTA 11011516 PH 1.7 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334468 | REMG 465 - VOLTA 1101 1.6 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3139 | -122.0706 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | 2023 ICUG
35316201 | PLUCODIXIE-HOT SPRINGS RD Z5 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68314 | 0 | 0.68314 | 2023 | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1397 | -120.9389 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316200 | PLUCODIXIE-KINDER AVE Z4 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 1.0417 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0417 | 0 | 1.0417 | 2023 | 0 | 1.0417 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1413 | -120.957 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316019 | PLUCODIXIE-FORGAY AVE Z3 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 1.017 | 0 | 1.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.017 | 0 | 1.017 | 2023 | 0 | 1.017 | 0 | 1.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1435 | -120.9581 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35316018 | PLUCODIXIE-BIDWELL ST Z2 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 0.7197 | 0 | 0.7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7197 | 0 | 0.7197 | 2023 | 0 | 0.7197 | 0 | 0.7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35334467 | PSPS - VOLTA 11011516 PH 1.5 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3305 | -122.0971 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334466 | PSPS - VOLTA 11011516 PH 1.4 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3386 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35313249 | PLUCODIXIE-BUSH ST Z1 GREENVILLE | 0 | Community Rebuild | 0 | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 1.2871 | 0 | 1.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2871 | 0 | 1.2871 | 2023 | 0 | 1.2871 | 0 | 1.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Greenville Rebuild
35334465 | PSPS - VOLTA 11011516 PH 1.3 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3507 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35334464 | PSPS - VOLTA 11011516 PH 1.2 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3748 | -122.1217 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | PSPS - 2023 ICUG
35312556 | CWSP - VOLTA 11011516 | WDRM v2 | SH | PSPS | 580 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3453 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0 | 0.0036607 | Tier 2 | 2023 ICUG
35335283 | CWSP - LINCOLN 1104 LR2070 PH 1.4 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9566 | -121.2286 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35335282 | CWSP - LINCOLN 1104 LR2070 PH 1.3 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35335281 | CWSP - LINCOLN 1104 LR2070 PH 1.2 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35332959 | CWSP LINCOLN 1104 LR2070 PH 2.3 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.8975 | -121.2471 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35332958 | CWSP LINCOLN 1104 LR2070 PH 2.2 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3701 | 0 | 1.3701 | 2023 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | CWSP - 2023 ICUG
35320454 | CWSP - LINCOLN 1104 LR2070 PH 1.1 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.952 | -121.2551 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | 2023 ICUG
35320312 | CWSP LINCOLN 1104 LR2070 PH 2.1 | WDRM v2 | SH | CWSP | 568 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2023 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0 | 0.00011911 | Tier 2 | CWSP - 2023 ICUG
35262345 | DR-STS-POLE_IDLE_REMV-4S/OR/O3235MEADOW | WDRM v2 | IF | 0 | 554 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17803 | 0.17803 | 2023 | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3774 | -122.4352 | WDRM v2 |  | 554 | 0.14355 |  | 1152 | 0 | 0.0017959 | Tier 2 | Idle Facilities
35056808 | R20A - FREESTONE SONOMA COUNTY | WDRM v2 | Other | 0 | 534 | V2 Top Risk | Other | 30A | PEND | Permitting/Dependency | Y | Y | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | WDRM v2 |  | 534 | 0.14747 |  | 1720 | 0 | 0.00074971 | Tier 3 | Other
35275479 | FT-OFAC_IDLE_REMV - #7 ON LINE S/O CO#5 | WDRM v2 | IF | 0 | 532 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26705 | 0.26705 | 2023 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4236 | -121.8237 | WDRM v2 |  | 532 | 0.14786 |  | 1752 | 0 | 0.00072124 | Tier 2 | Idle Facilities
35262812 | LUCERNE 1103 - DIST LINE WORK | WDRM v2 | Other | 0 | 512 | V2 Top Risk | Other | 06H | ESTS | Estimating | Y | N | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 2024 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lucerne | Lake |  |  | WDRM v2 |  | 512 | 0.1512 |  | 3737 | 0 | 5.9361e-05 | Tier 2 | 0
35260649 | X22: CWSP - PASO ROBLES 1103N04 PH 1 | WDRM v2 | SH | CWSP | 510 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 2024 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7334 | -120.8792 | WDRM v2 |  | 510 | 0.1516 |  | 1729 | 0 | 0.00074213 | Tier 2 | CWSP 2022-2023
35335293 | PSPS - VACAVILLE 1111 CB PH 1.4 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 0 | 2.41 | 2023 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35335292 | PSPS - VACAVILLE 1111 CB PH 1.3 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 0 | 1.8799 | 2023 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35335291 | PSPS - VACAVILLE 1111 CB PH 1.2 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2023 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35320440 | PSPS - VACAVILLE 1111 CB PH 1.1 | WDRM v2 | SH | PSPS | 500 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3783 | -122.0044 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0 | 0.00055328 | Tier 2 | PSPS - 2023 ICUG
35243443 | REMG 188 - TIVY VALLEY 1107 | WDRM v2 | SH | REMG | 491 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Sanger | Fresno | 36.8168 | -119.3407 | WDRM v2 |  | 491 | 0.15534 |  | 1657 | 0 | 0.00080485 | Tier 2 | REMG 2022-2023
35244105 | DR-COND_IDLE_REMV-20095 HWY 175 | WDRM v2 | IF | 0 | 474 | V2 Top Risk | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7672 | -122.6631 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | Idle Facilities
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | Y | 0.17614 | 1.2508 | 0 | 1.4269 | 0 | 0 | 0 | 0 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542 | 2023 | 0.088068 | 0.047348 | 0 | 0.13542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0684 | 0 | 1.0684 | 2023 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 2023 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0267 | 0 | 1.0267 | 2023 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782 | 2023 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79413 | 0 | 0.79413 | 2023 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79375 | 0 | 0 | 0.79375 | 2023 | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756 | 2023 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85246 | 0 | 0.85246 | 2023 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0.58883 | 2023 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 1.0394 | 2023 | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.71326 | 0 | 0 | 0.71326 | 0 | 0 | 0 | 0 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746 | 2023 | 0.17746 | 0 | 0 | 0.17746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449 | 2023 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303 | 2023 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174479 | REMG 749-MIDDLETOWN 1101,ANDERSON SPRNGS | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | WDRM v2 | SH | ECOP | 474 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04 | 2023 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 1 | 0.018129 | Tier 3 | ECOP - Top 20%
35301110 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.6 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 2023 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0037879 | 1.3765 | 0 | 1.3803 | 2023 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 2024 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | WDRM v2 | SH | ECOP | 468 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7241 | -122.619 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 1 | 0.035184 | Tier 3 | ECOP - Top 20%
35340270 | PSPS - CORNING 1102 LR915324 PH 1.2 | WDRM v2 | SH | PSPS | 457 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 2.34 | 2023 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0 | 0.0001615 | Tier 2 | PSPS - 2023 ICUG
35311898 | PSPS - CORNING 1102 LR915324 PH 1.1 | WDRM v2 | SH | PSPS | 457 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2023 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0 | 0.0001615 | Tier 2 | PSPS - 2023 ICUG
35274594 | CWSP MARIPOSA 2101 LR 35244 PH 2.4 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5353 | -119.9554 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.756 | 0 | 2.756 | 2023 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274592 | CWSP MARIPOSA 2101 LR 35244 PH 2.2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5116 | -119.9647 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35274591 | CWSP MARIPOSA 2101 LR 35244 PH1.3 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5195 | -119.9397 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.132 | 0 | 2.132 | 2023 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 | CWSP 2022-2023
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 | WDRM v2 | SH | CWSP | 428 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 2 & 3 | CWSP 2022-2023
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | WDRM v2 | SH | REMG | 428 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2023 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0 | 0.010861 | Tier 3 | Remote Grid Pilot
35250938 | STS-POLE_IDLE_REMV-4/S/O 1/N/O 4511 BROO | WDRM v2 | IF | 0 | 424 | V2 Top Risk | Idle Facilities | 2AF | ESTS | Estimating | Y | N | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24432 | 0.24432 | 2023 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.6385 | -120.9907 | WDRM v2 |  | 424 | 0.1736 |  | 886 | 0 | 0.0026967 | Tier 3 | Idle Facilities
35330243 | CWSP - REDBUD 1101 LR323962 PH1.5 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0621 | -122.5786 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | 2023 ICUG
35330242 | CWSP - REDBUD 1101 LR323962 PH1.4 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0671 | -122.5853 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | 2023 ICUG
35330241 | CWSP - REDBUD 1101 LR323962 PH1.3 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8549 | 0 | 2.8549 | 2023 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35330219 | CWSP - REDBUD 1101 LR323962 PH1.2 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299 | 2023 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35330217 | CWSP - REDBUD 1101323962 PH 2.6 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 2023 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330216 | CWSP - REDBUD 1101323962 PH 2.5 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330215 | CWSP - REDBUD 1101323962 PH 2.4 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 2023 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330213 | CWSP - REDBUD 1101323962 PH 2.3 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.5887 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35330211 | CWSP - REDBUD 1101323962 PH 2.2 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 1.9701 | 2023 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35317399 | CWSP - REDBUD 1101323962 PH 2.1 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 2 & 3 | CWSP - 2023 ICUG
35312550 | CWSP - REDBUD 1101 LR323962 PH1.1 | WDRM v2 | SH | CWSP | 423 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54 | 2023 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 1 | 0.016255 | Tier 3 | CWSP - 2023 ICUG
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | WDRM v2 | SH | REMG | 421 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 2023 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Ahwahnee | Madera | 37.3642 | -119.7251 | WDRM v2 |  | 421 | 0.17437 |  | 913 | 0 | 0.0025801 | Tier 3 | Remote Grid Pilot
35320463 | PSPS - JAMESON 1105913400 | WDRM v2 | SH | PSPS | 419 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56004 | 0 | 0.56004 | 2023 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 |  | 419 | 0.17457 |  | 987 | 0 | 0.0022992 | Tier 2 | PSPS - 2023 ICUG
35221246 | DR~T2 REMV IDLE POLE 6 N/O #1 E/0 ENT | WDRM v2 | IF | 0 | 417 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Yorkville | Mendocino | 38.9374 | -123.309 | WDRM v2 |  | 417 | 0.17472 |  | 1638 | 0 | 0.0008197 | Tier 2 | Idle Facilities
35380377 | REMG 301 - CORNING 1102, NEWVILLE | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 2023 | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8303 | -122.5775 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380376 | PSPS - CORNING 1102 LR53184 PH 1.15 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799 | 2023 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380375 | REMG 797 - CORNING 1102 PH 1.14 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 2023 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8374 | -122.6306 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380374 | REMG 818 - CORNING 1102 PH 1.13 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299 | 2023 | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8507 | -122.6133 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35380373 | PSPS - CORNING 1102 LR53184 PH 1.12 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79 | 2023 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380372 | PSPS - CORNING 1102 LR53184 PH 1.11 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 2023 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380371 | PSPS - CORNING 1102 LR53184 PH 1.10 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8299 | 0 | 2.8299 | 2023 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380370 | PSPS - CORNING 1102 LR53184 PH 1.9 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1799 | 0 | 3.1799 | 2023 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380369 | PSPS - CORNING 1102 LR53184 PH 1.8 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1299 | 0 | 2.1299 | 2023 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380368 | PSPS - CORNING 1102 LR53184 PH 1.7 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 2.2299 | 2023 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35380365 | PSPS - CORNING 1102 LR53184 PH 1.5 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2023 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35334230 | REMG 817 - CORNING 1102 PH 1.4 | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8348 | -122.6319 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | 2023 ICUG
35334229 | PSPS - CORNING 1102 LR53184 PH 1.3 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 2023 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35311897 | PSPS - CORNING 1102 LR53184 PH 1.1 | WDRM v2 | SH | PSPS | 413 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.84 | 0 | 4.84 | 2023 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 2 | PSPS - 2023 ICUG
35276100 | REMG 300 - CORNING 1102, TURRI MAIN | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 3 | Remote Grid Pilot
35229051 | REMG 299 - CORNING 1102, TURRI ELLIS | WDRM v2 | SH | REMG | 413 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2023 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9003 | -122.5065 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0 | 0.0037456 | Tier 3 | Remote Grid Pilot
35285245 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.4 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3019 | -123.109 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012311 | 0.25398 | 0 | 0.26629 | 2023 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35285064 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79848 | 0 | 0.79848 | 2023 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35254077 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.1 | WDRM v2 | SH | CWSP | 396 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3171 | -123.1131 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0 | 0.00037714 | Tier 2 | CWSP 2022-2023
35339293 | PSPS - JAMESON 1105 LR466348 PH 1.7 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 2023 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338410 | PSPS - JAMESON 1105 LR466348 PH 2.3 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21 | 2023 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338409 | PSPS - JAMESON 1105 LR466348 PH 2.2 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338408 | PSPS - JAMESON 1105 LR466348 PH 1.6 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 2023 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338407 | PSPS - JAMESON 1105 LR466348 PH 1.5 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 2023 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 2023 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338405 | PSPS - JAMESON 1105 LR466348 PH 1.3 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 2023 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35338404 | PSPS - JAMESON 1105 LR466348 PH 1.2 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 2023 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35320461 | PSPS - JAMESON 1105 LR466348 PH 2.1 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56 | 2023 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35320460 | PSPS - JAMESON 1105 LR466348 PH 1.1 | WDRM v2 | SH | PSPS | 393 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 1.7799 | 2023 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 2 | 0.0035256 | Tier 2 | PSPS - 2023 ICUG
35339289 | CWSP - JESSUP 1102 LR1550 PH 3.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.82 | 0 | 1.82 | 2023 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339288 | CWSP - JESSUP 1102 LR1550 PH 3.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 2023 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339287 | CWSP - JESSUP 1102 LR1550 PH 3.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339286 | CWSP - JESSUP 1102 LR1550 PH 2.5 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.54 | 0 | 2.54 | 2023 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339285 | CWSP - JESSUP 1102 LR1550 PH 2.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 2023 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339283 | CWSP - JESSUP 1102 LR1550 PH 2.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 2023 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35339282 | CWSP - JESSUP 1102 LR1550 PH 2.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 2023 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337012 | CWSP - JESSUP 1102 LR1550 PH 1.5 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.443 | -122.3663 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337011 | CWSP - JESSUP 1102 LR1550 PH 1.4 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.89 | 0 | 2.89 | 2023 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337010 | CWSP - JESSUP 1102 LR1550 PH 1.3 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.82 | 0 | 3.82 | 2023 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35317887 | CWSP - JESSUP 1102 LR1550 PH 3.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 2023 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35317480 | CWSP - JESSUP 1102 LR1550 PH 2.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 2023 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35312548 | CWSP - JESSUP 1102 LR1550 PH 1.1 | WDRM v2 | SH | CWSP | 389 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0 | 0.00063997 | Tier 2 | CWSP - 2023 ICUG
35338403 | CWSP - PANORAMA 1101 LR885215 PH 1.2 | WDRM v2 | SH | PSPS | 380 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4063 | -122.2482 | WDRM v2 |  | 380 | 0.18705 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | 2023 ICUG
35320465 | CWSP - PANORAMA 1101 LR885215 PH 1.1 | WDRM v2 | SH | PSPS | 380 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4073 | -122.2444 | WDRM v2 |  | 380 | 0.18705 |  | 3890 | 0 | 5.6461e-05 | Tier 2 | 2023 ICUG
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 2023 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 2023 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 2023 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | WDRM v2 | FRRB | FRRB | 378 | V2 Top Risk | Fire Rebuild | 08W | ESTS | Estimating | Y | Y | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.589 | 0 | 5.589 | 2023 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 1 | 0.023178 | Tier 2 & 3 | FRRB - UG - 2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | WDRM v2 | SH | ECOP | 377 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8879 | -121.8676 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | ECOP - Top 20%
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | WDRM v2 | SH | ECOP | 377 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34 | 2023 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 1 | 0.034099 | Tier 3 | ECOP - Top 20%
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | WDRM v2 | SH | PSPS | 355 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.28352 | 1.1968 | 0 | 1.4803 | 0 | 0 | 0 | 0 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.060417 | 0 | 0.060417 | 2023 | 0 | 0.060417 | 0 | 0.060417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 |  | 355 | 0.19378 |  | 2768 | 0 | 0.00020951 | Tier 2 | PSPS - Community Resiliency
35330249 | CWSP REDBUD 1101 708166 PH 1.7 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 4 | 0 | 4.25 | 2023 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330248 | CWSP REDBUD 1101 708166 PH 1.6 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0296 | -122.6802 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330247 | CWSP REDBUD 1101 708166 PH 1.5 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 2023 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330246 | CWSP REDBUD 1101 708166 PH 1.4 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 2023 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330245 | CWSP REDBUD 1101 708166 PH 1.3 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 2023 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35330244 | CWSP REDBUD 1101 708166 PH 1.2 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 2023 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35329474 | CWSP REDBUD 1101 754544 PH 1.2 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0.11004 | 0 | 1.2701 | 2023 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 1 | 0.007396 | Tier 2 & 3 | CWSP - 2023 ICUG
35317398 | CWSP REDBUD 1101 754544 PH 1.1 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0581 | -122.693 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 1 | 0.007396 | Tier 2 & 3 | CWSP - 2023 ICUG
35312552 | CWSP REDBUD 1101 708166 PH 1.1 | WDRM v2 | SH | CWSP | 345 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0.77008 | 2023 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 2 & 3 | CWSP - 2023 ICUG
35208096 | 8/31-HOLD REMV IDLE FAC -LONGVALLEY *KS | WDRM v2 | IF | 0 | 345 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20663 | 0.20663 | 2023 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.069 | -122.6909 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 1 | 0.0038601 | Tier 3 | Idle Facilities
35226625 | REMG 670 - ELK CREEK 1101, VALLEY VIEW | WDRM v2 | SH | FRRB | 340 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.6065 | -122.5419 | WDRM v2 |  | 340 | 0.1961 |  | 308 | 2 | 0.0090072 | Tier 2 | FRRB - REMG - 2021
35083879 | STS-POLE_IDLE_REMV - NEGRO CK RD/RD 152 | WDRM v2 | IF | 0 | 337 | V2 Top Risk | Idle Facilities | 2AF | ADER | Estimating | Y | N | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 2023 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Orange Cove | Tulare | 36.6365 | -119.1962 | WDRM v2 |  | 337 | 0.19768 |  | 2377 | 0 | 0.00035672 | Tier 2 | Idle Facilities
35349642 | CWSP - UPPER LAKE 1101 1276 PH 2.7 | WDRM v2 | SH | 0 | 335 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1699 | -123.006 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65303 | 0 | 0.65303 | 2023 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285250 | CWSP - UPPER LAKE 1101 1276 PH 2.5 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1756 | -123.0186 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35286270 | BOQUEST | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7583 | -121.6291 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35285249 | CWSP - UPPER LAKE 1101 1276 PH 2.4 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6288 | 0 | 2.6288 | 2023 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285248 | CWSP - UPPER LAKE 1101 1276 PH 2.3 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1679 | -123.0053 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35285247 | CWSP - UPPER LAKE 1101 1276 PH 2.2 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1668 | -123.0058 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283349 | CWSP UPPER LAKE 1101 1276 PH 1.8 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.113 | -122.9818 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283348 | CWSP UPPER LAKE 1101 1276 PH 1.7 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1213 | -122.9896 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1253 | -122.9948 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6591 | 0 | 1.6591 | 2023 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283344 | CWSP UPPER LAKE 1101 1276 PH 1.4 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1474 | -122.9995 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35283343 | CWSP UPPER LAKE 1101 1276 PH 1.3 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18447 | 0.72614 | 0 | 0.91061 | 2023 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35256083 | CWSP - UPPER LAKE 11011276 PH 2 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0079545 | 1.847 | 0 | 1.8549 | 2023 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35256082 | CWSP - UPPER LAKE 11011276 PH 1 | WDRM v2 | SH | CWSP | 335 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1477 | 0 | 0 | 1.1477 | 2023 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1583 | -122.9898 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 1 | 0.024971 | Tier 2 | CWSP 2022-2023
35278889 | CWSP - AUBERRY 1101 LR49122 PH1.2 | WDRM v2 | SH | CWSP | 330 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0894 | -119.4783 | WDRM v2 |  | 330 | 0.19907 |  | 734 | 0 | 0.0034999 | Tier 2 | CWSP 2022-2023
35254242 | CWSP - AUBERRY 1101 LR 49122 | WDRM v2 | SH | CWSP | 330 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0812 | -119.4864 | WDRM v2 |  | 330 | 0.19907 |  | 734 | 0 | 0.0034999 | Tier 2 | CWSP 2022-2023
35083893 | STS-COND_IDLE_REMV-5282 MINES RD | WDRM v2 | IF | 0 | 324 | V2 Top Risk | Idle Facilities | 2AF | CONS | In-Construction | Y | N | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067424 | 0.067424 | 2023 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6459 | -121.7137 | WDRM v2 |  | 324 | 0.20121 |  | 764 | 0 | 0.0032627 | Tier 2 | Idle Facilities
35134959 | VALLEY SPRINGS 1102 FEEDER OUTLET | WDRM v2 | Other | 0 | 322 | V2 Top Risk | Other | 06A | PEND | Permitting/Dependency | Y | Y | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 2024 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Valley Springs | Calaveras | 38.2131 | -120.7638 | WDRM v2 |  | 322 | 0.20132 |  | 1048 | 0 | 0.0020877 | Tier 2 | Other
35332364 | CWSP ELK CREEK 1101 LR2002 PH 2.6 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.085038 | 0 | 0.085038 | 2023 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332363 | CWSP ELK CREEK 1101 LR2002 PH 2.5 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 2023 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332362 | CWSP ELK CREEK 1101 LR2002 PH 2.4 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8299 | 0 | 3.8299 | 2023 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35332361 | REMG 255 - ELK CREEK 1101, BRAVO | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4277 | -122.5067 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | 2023 ICUG
35332360 | CWSP ELK CREEK 1101 LR2002 PH 2.2 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.46 | 0 | 5.46 | 2023 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35330813 | REMG 256 - ELK CREEK 1101, MILANO | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5331 | -122.5377 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | 2023 ICUG
35330812 | PSPS ELK CREEK 1101 LR2002 PH 1.2 | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.49 | 0 | 2.49 | 2023 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | PSPS - 2023 ICUG
35316278 | CWSP ELK CREEK 1101 LR2002 PH 2.1 | WDRM v2 | SH | CWSP | 315 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 2023 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | CWSP - 2023 ICUG
35312543 | PSPS ELK CREEK 1101 LR2002 PH 1.1 | WDRM v2 | SH | PSPS | 315 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.71 | 0 | 3.71 | 2023 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0 | 0.0021026 | Tier 2 | PSPS - 2023 ICUG
35329473 | CWSP - REDBUD 1101 LR454 PH 1.3 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0654 | -122.6333 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35329472 | CWSP - REDBUD 1101 LR454 PH 1.2 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 2023 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35312551 | CWSP - REDBUD 1101 LR454 PH 1.1 | WDRM v2 | SH | CWSP | 312 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2049 | 0 | 3.2049 | 2023 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 1 | 0.023647 | Tier 3 | CWSP - 2023 ICUG
35349646 | CWSP - BUELLTON 1102 CB PH 1.4 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 2024 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.5925 | -120.1558 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35349645 | CWSP - BUELLTON 1102 CB PH 1.3 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 2024 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6005 | -120.1908 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35349643 | CWSP - BUELLTON 1102 CB PH 1.2 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 2024 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1576 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35320445 | CWSP - BUELLTON 1102 CB PH 1.1 | WDRM v2 | SH | CWSP | 307 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Buellton | Santa Barbara | 34.6236 | -120.185 | WDRM v2 |  | 307 | 0.21085 |  | 2847 | 0 | 0.00018253 | Tier 2 | 2023 ICUG
35259514 | CWSP - DESCHUTES 11041582 PH1.2 | WDRM v2 | SH | CWSP | 301 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5894 | -122.2244 | WDRM v2 |  | 301 | 0.21327 |  | 3101 | 0 | 0.0001094 | Tier 2 | CWSP 2022-2023
35279629 | CWSP PASO ROBLES 1103 LRN52 PH1.3 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 2024 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7141 | -120.8386 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35279628 | CWSP PASO ROBLES 1103 LRN52 PH1.2 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 2024 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.706 | -120.8189 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35254252 | +CWSP - PASO ROBLES 1103 LR N52 | WDRM v2 | SH | CWSP | 291 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.414 | 0 | 0 | 2.414 | 2023 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6886 | -120.7649 | WDRM v2 |  | 291 | 0.21643 |  | 311 | 2 | 0.0089389 | Tier 2 | CWSP 2022-2023
35278090 | CWSP - AUBERRY 1101R2839 PH2.2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0201 | -119.4294 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35277935 | CWSP AUBERRY 1101 R2839 PH1.4 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089394 | 0 | 0.089394 | 2023 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP
35277934 | CWSP AUBERRY 1101 R2839 PH1.3 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0314 | -119.4428 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35277933 | CWSP AUBERRY 1101 R2839 PH1.2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0335 | -119.4426 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35254241 | CWSP - AUBERRY 1101 LR R2839 PH2 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35254240 | CWSP - AUBERRY 1101 LR R2839 PH1 | WDRM v2 | SH | CWSP | 274 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0 | 0.0043344 | Tier 2 | CWSP 2022-2023
35332217 | PSPS COTTONWOOD 1102 LR9026 PH 3.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0.05303 | 3.083 | 2023 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332216 | PSPS COTTONWOOD 1102 LR9026 PH 2.3 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 2023 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332215 | PSPS COTTONWOOD 1102 LR9026 PH 2.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26 | 2023 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35332214 | PSPS COTTONWOOD 1102 LR9026 PH 1.2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.04 | 0 | 4.04 | 2023 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35316569 | PSPS - COTTONWOOD 11029026 PH3 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0.032008 | 4.842 | 2023 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35316567 | PSPS - COTTONWOOD 11029026 PH2 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4201 | 0 | 3.4201 | 2023 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35312540 | PSPS - COTTONWOOD 11029026 PH1 | WDRM v2 | SH | PSPS | 271 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8799 | 0 | 4.8799 | 2023 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0 | 0.0002216 | Tier 2 | PSPS - 2023 ICUG
35349651 | CWSP - BUELLTON 1102 Y50 PH 1.6 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 2024 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6136 | -120.1365 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349650 | CWSP - BUELLTON 1102 Y50 PH 1.5 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 2024 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349649 | CWSP - BUELLTON 1102 Y50 PH 1.4 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 2024 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349648 | CWSP - BUELLTON 1102 Y50 PH 1.3 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 2024 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35349647 | CWSP - BUELLTON 1102 Y50 PH 1.2 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 2024 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6129 | -120.1624 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35320446 | CWSP - BUELLTON 1102 Y50 PH 1.1 | WDRM v2 | SH | CWSP | 269 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.613 | -120.1749 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0 | 0.00026962 | Tier 2 | 2023 ICUG
35329008 | PSPS CLARK ROAD 1102 CB PH 1.2 | WDRM v2 | SH | PSPS | 268 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31307 | 0 | 0.31307 | 2023 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0 | 0.00031072 | Tier 2 | PSPS
35299629 | PSPS CLARK ROAD 1102 CB PH 1.1 | WDRM v2 | SH | PSPS | 268 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.654 | -121.6323 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0 | 0.00031072 | Tier 2 | PSPS
35331302 | CWSP ANDERSON 1103 LR226050 PH 1.5 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4766 | -122.2926 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35331301 | CWSP ANDERSON 1103 LR226050 PH 1.4 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4791 | -122.2929 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35330816 | CWSP ANDERSON 1103 LR226050 PH 1.3 UPDAT | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.5058 | -122.2574 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | 2023 ICUG
35330815 | CWSP ANDERSON 1103 LR226050 PH 1.2 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2023 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | CWSP - 2023 ICUG
35311895 | CWSP ANDERSON 1103 LR226050 PH 1.1 | WDRM v2 | SH | CWSP | 262 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7799 | 0 | 2.7799 | 2023 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 0 | 8.0345e-05 | Tier 2 | CWSP - 2023 ICUG
35279626 | +X22: CWSP -PASO ROBLES 1103 LR 2731 PH1 | WDRM v2 | SH | CWSP | 260 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16364 | 0 | 0 | 0.16364 | 2023 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.73 | WDRM v2 |  | 260 | 0.2296 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35254254 | +X22: CWSP - PASO ROBLES 1103 LR 2731 | WDRM v2 | SH | CWSP | 260 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 | 1.3972 | 2023 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.7299 | WDRM v2 |  | 260 | 0.2296 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35151005 | 8/31 REMV IDLE 4 LOCS OLD WITTER SP*RA | WDRM v2 | IF | 0 | 259 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28636 | 0.28636 | 2023 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.185 | -122.9886 | WDRM v2 |  | 259 | 0.23008 |  | 327 | 1 | 0.0086415 | Tier 2 | Idle Facilities
35279631 | CWSP - PASO ROBLES 1103 LRN58 PH1.2 | WDRM v2 | SH | CWSP | 257 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.064 | 0 | 0 | 3.064 | 0 | 0 | 0 | 0 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417 | 2023 | 1.6417 | 0 | 0 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6385 | -120.7157 | WDRM v2 |  | 257 | 0.23099 |  | 771 | 0 | 0.0032279 | Tier 2 | CWSP 2022-2023
35254248 | CWSP - PASO ROBLES 1103 LR N58 | WDRM v2 | SH | CWSP | 257 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 2024 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | El Paso De Robles | San Luis Obispo | 35.6286 | -120.6955 | WDRM v2 |  | 257 | 0.23099 |  | 771 | 0 | 0.0032279 | Tier 2 | CWSP 2022-2023
35225318 | +STS-COND_IDLE_REMV-CAT CANYON RD | WDRM v2 | IF | 0 | 256 | V2 Top Risk | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094697 | 0.094697 | 2023 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | Santa Barbara | 34.8111 | -120.2748 | WDRM v2 |  | 256 | 0.23169 |  | 2229 | 0 | 0.00042166 | Tier 2 | Idle Facilities
35337306 | CWSP STANISLAUS 1702 CB PH 1.5 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0094697 | 2.2667 | 0 | 2.2761 | 2023 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284366 | REMG 512 - STANISLAUS 1702, FOREBAY | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871 | 2023 | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1446 | -120.3574 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284365 | CWSP STANISLAUS 1702 CB PH 1.3 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 2.7547 | 0 | 2.7797 | 2023 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0047348 | 0.91742 | 0 | 0.92216 | 2023 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35250577 | CWSP - STANISLAUS 1702 CB | WDRM v2 | SH | CWSP | 235 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5777 | 0 | 0 | 3.5777 | 2023 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1377 | -120.3701 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 1 | 0.022026 | Tier 2 & 3 | CWSP 2022-2023
35349244 | CWSP - LINCOLN 1104 LR685276 PH 1.5 | WDRM v2 | SH | 0 | 230 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 2023 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | CWSP 2022-2023
35339292 | CWSP - LINCOLN 1104 LR685276 PH 1.4 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 2023 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9969 | -121.2718 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35339291 | CWSP - LINCOLN 1104 LR685276 PH 1.3 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 2024 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9964 | -121.2681 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35339290 | CWSP - LINCOLN 1104 LR685276 PH 1.2 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 2024 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | 2023 ICUG
35320450 | CWSP - LINCOLN 1104 LR685276 PH 1.1 | WDRM v2 | SH | CWSP | 230 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 2023 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 0 | 5.2842e-05 | Tier 2 | CWSP - 2023 ICUG
35211757 | DR-COND_IDLE_REMV-13716 LOS VERJELES | WDRM v2 | IF | 0 | 225 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15057 | 0.15057 | 2023 | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Marysville | Yuba | 39.3562 | -121.3774 | WDRM v2 |  | 225 | 0.24429 |  | 2534 | 0 | 0.00029638 | Tier 2 | Idle Facilities
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | WDRM v2 | SH | PSPS | 218 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.076705 | 0.53561 | 0 | 0.61231 | 0 | 0 | 0 | 0 | 0.062879 | 0.40985 | 0 | 0.47273 | 0.013826 | 0.12576 | 0 | 0.13958 | 2024 | 0 | 0 | 0 | 0 | 0.013826 | 0.12576 | 0 | 0.13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WDRM v2 |  | 218 | 0.24845 |  | 2461 | 0 | 0.00032066 | Tier 2 | PSPS - Community Resiliency
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | WDRM v2 | SH | ECOP | 215 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3843 | 0 | 1.3843 | 2023 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 |  | 215 | 0.25006 |  | 1267 | 0 | 0.0014262 | Tier 3 | ECOP - Top 20%
35150641 | T2-COND_IDLE_REMV-16853 DAM RD *KS | WDRM v2 | IF | 0 | 212 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 2023 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9248 | -122.5972 | WDRM v2 |  | 212 | 0.25222 |  | 847 | 0 | 0.0028915 | Tier 2 | Idle Facilities
35332219 | PSPS ELK CREEK 1101 LR93504 PH 1.2 | WDRM v2 | SH | PSPS | 206 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.593 | -122.5412 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0 | 0.0012407 | Tier 2 | PSPS - 2023 ICUG
35312544 | CWSP ELK CREEK 1101 LR93504 PH 1.1 | WDRM v2 | SH | PSPS | 206 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 2023 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0 | 0.0012407 | Tier 2 | PSPS - 2023 ICUG
35262347 | STS-POLE_IDLE_REMV - A/F 45771 BUTTERNUT | WDRM v2 | IF | 0 | 195 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.069318 | 0.069318 | 2023 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6995 | -119.1257 | WDRM v2 |  | 195 | 0.26095 |  | 1266 | 0 | 0.0014269 | Tier 2 | Idle Facilities
35215883 | STS-TRAN_CORR_REPL - 45886 CHUCKWAGON RD | WDRM v2 | IF | 0 | 195 | V2 Top Risk | Idle Facilities | 2AA | PEND | Permitting/Dependency | Y | N | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10303 | 0.10303 | 2023 | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6914 | -119.1303 | WDRM v2 |  | 195 | 0.26095 |  | 1266 | 0 | 0.0014269 | Tier 2 | Idle Facilities
35335290 | PSPS - VACAVILLE 1111 LR13652 PH 1.2 | WDRM v2 | SH | PSPS | 190 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61 | 2023 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0 | 0.00074783 | Tier 2 | PSPS - 2023 ICUG
35320441 | PSPS - VACAVILLE 1111 LR13652 PH 1.1 | WDRM v2 | SH | PSPS | 190 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 2023 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0 | 0.00074783 | Tier 2 | PSPS - 2023 ICUG
35337164 | CWSP LINCOLN 1104 51756 & 275986 PH 1.3 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 2024 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9708 | -121.2498 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | 2023 ICUG
35337163 | CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 2023 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | CWSP - 2023 ICUG
35320449 | CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | WDRM v2 | SH | CWSP | 185 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2375 | 1.5472 | 4.7847 | 2023 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0 | 0.0001399 | Tier 2 | CWSP - 2023 ICUG
35208097 | 8/31-REMV IDLE 19824 MORGAN HOLD FOR 10J | WDRM v2 | IF | 0 | 181 | V2 Top Risk | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017045 | 0.017045 | 2023 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8926 | -122.5433 | WDRM v2 |  | 181 | 0.26975 |  | 270 | 1 | 0.010079 | Tier 2 | Idle Facilities
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 | WDRM v2 | SH | CWSP | 171 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0 | 0.15814 | 2023 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 |  | 171 | 0.27308 |  | 712 | 2 | 0.0036194 | Tier 2 | CWSP 2022-2023
35240173 | CWSP - PUTAH CREEK 11028352 PH 1.1 | WDRM v2 | SH | CWSP | 171 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.567 | 0 | 0 | 1.567 | 2023 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 |  | 171 | 0.27308 |  | 712 | 2 | 0.0036194 | Tier 2 | CWSP 2022-2023
35310704 | CWSP MOUNTAIN QUARRIES 2101 1350 PH1.12 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 2024 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305312 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.11 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 2024 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.9674 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305311 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.10 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 2024 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8965 | -120.9455 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305310 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.9 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 2024 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.899 | -120.9485 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305309 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.8 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 2024 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9633 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305308 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8944 | -120.9647 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305307 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.6 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 2024 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9648 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305306 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.5 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 2024 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.972 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305305 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.4 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 2024 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8981 | -120.9738 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305304 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.3 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 2024 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8978 | -120.9866 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.065 | 0 | 1.065 | 2023 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293670 | CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54394 | 0 | 0.54394 | 2023 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293669 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.9 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 2024 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8852 | -120.96 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293668 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.8 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 2024 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8894 | -120.9589 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293667 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.7 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 2024 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8974 | -120.9338 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293666 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.6 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 2024 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9012 | -120.9346 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43655 | 0 | 0.43655 | 2023 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293664 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.4 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2024 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8981 | -120.914 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68788 | 0 | 0.68788 | 2023 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH2. | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 2024 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8932 | -120.9965 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35254070 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH1 | WDRM v2 | SH | CWSP | 169 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 2024 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8931 | -120.9966 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 1 | 0.0069368 | Tier 2 | CWSP 2022-2023
35278892 | CWSP - AUBERRY 1101R2578 PH5.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 2024 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9662 | -119.3834 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278891 | CWSP - AUBERRY 1101R2578 PH5.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9752 | -119.3882 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278890 | CWSP - AUBERRY 1101R2578 PH5.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 2024 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9737 | -119.3888 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278097 | CWSP - AUBERRY 1101R2578 PH4.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.286 | 0 | 0.20095 | 1.4869 | 0 | 0 | 0 | 0 | 0.66345 | 0 | 0 | 0.66345 | 0.62254 | 0 | 0.20095 | 0.82348 | 2023 | 0.62254 | 0 | 0.20095 | 0.82348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.98 | -119.4029 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278093 | CWSP - AUBERRY 1101R2578 PH3.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.41496 | 0 | 0.41496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35278092 | CWSP - AUBERRY 1101R2578 PH3.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 2024 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.978 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254346 | PBS-5552 CLARK RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6087 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35254345 | PBS-NUTMEG WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7874 | -121.601 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254344 | PBS-360 OAK SPRING RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | ESTS | Estimating | N | Y | 0 | 0.12027 | 0 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12027 | 0 | 0.12027 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.12027 | 0 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7414 | -121.6432 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254275 | PBS-BURKE LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | PEND | Permitting/Dependency | N | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7704 | -121.6012 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35254274 | PBS-NOTTONGHAM PARK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F | UNSC | Ready for Construction | N | Y | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.088447 | 0 | 0.088447 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7598 | -121.6341 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35278091 | CWSP - AUBERRY 1101R2578 PH3.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 2024 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9796 | -119.3694 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277938 | CWSP AUBERRY 1101 R2578 PH2.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42822 | 0.31742 | 0.74564 | 2023 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277937 | CWSP AUBERRY 1101 R2578 PH2.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 2024 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0129 | -119.3939 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277936 | CWSP AUBERRY 1101 R2578 PH2.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5307 | 0 | 0 | 3.5307 | 2023 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0143 | -119.4031 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277924 | CWSP AUBERRY 1101 R2578 PH1.5 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0.10909 | 2023 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277923 | CWSP AUBERRY 1101 R2578 PH1.4 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1777 | 0 | 0 | 3.1777 | 2023 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9916 | -119.4068 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277922 | CWSP AUBERRY 1101 R2578 PH1.3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 2024 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.005 | -119.4055 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35277921 | CWSP AUBERRY 1101 R2578 PH1.2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 2024 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0111 | -119.4175 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254247 | CWSP - AUBERRY 1101 LR R2578 PH5 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 2024 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9581 | 0 | 0 | 2.9581 | 2023 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254244 | CWSP - AUBERRY 1101 LR R2578 PH2 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4244 | 0 | 0 | 2.4244 | 2023 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35254243 | CWSP - AUBERRY 1101 LR R2578 PH1 | WDRM v2 | SH | CWSP | 163 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 2024 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0 | 0.0047219 | Tier 2 | CWSP 2022-2023
35226852 | X22: CWSP-SHINGLE SPRINGS 2109-LR 9372-P | WDRM v2 | SH | PRE | 159 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 | 2.4932 | 2023 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 3 | 0.011098 | Tier 3 | Top 20% MAVF CPZ
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | WDRM v2 | SH | PRE | 159 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 2023 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 3 | 0.011098 | Tier 3 | Top 20% MAVF CPZ
35254651 | CWSP - VOLTA 110153118 PH 1.4 | WDRM v2 | SH | CWSP | 157 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.4038 | 0 | 0 | 2.4038 | 0 | 0 | 0 | 0 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045 | 2023 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 2 | 0.0099281 | Tier 2 | CWSP 2022-2023
35254650 | CWSP - VOLTA 110153118 PH 1.3 | WDRM v2 | SH | CWSP | 157 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.30436 | 0 | 0.30436 | 0.0056818 | 0 | 0 | 0.0056818 | 2023 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 2 | 0.0099281 | Tier 2 | CWSP 2022-2023
35264190 | CWSP - SANTA YNEZ 1104 Y66 PH 2.3 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3576 | 0 | 0 | 2.3576 | 2023 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6451 | -119.9634 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264189 | CWSP - SANTA YNEZ 1104Y66 PH 2.2 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6055 | 0 | 0 | 2.6055 | 2023 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6377 | -119.9713 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264188 | CWSP - SANTA YNEZ 1104Y66 PH 1.5 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1292 | 0 | 0 | 1.1292 | 2023 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6065 | -119.9508 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264187 | CWSP - SANTA YNEZ 1104Y66 PH 1.4 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6919 | 0 | 0 | 1.6919 | 2023 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6112 | -119.9786 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35264185 | CWSP - SANTA YNEZ 1104Y66 PH 1.2 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4926 | 0 | 0 | 1.4926 | 2023 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6142 | -119.9878 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2.1 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.589 | 0 | 0 | 2.589 | 2023 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1.1 | WDRM v2 | SH | CWSP | 153 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1089 | 0 | 0 | 2.1089 | 2023 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 |  | 153 | 0.28279 |  | 1417 | 0 | 0.0011255 | Tier 2 & 3 | CWSP 2022-2023
35325590 | CWSP FLINT 1101 750 PH 1.3 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 2023 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35325589 | CWSP FLINT 1101 750 PH 1.2 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 2023 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35312545 | CWSP - FLINT 1101750 PH 1.1 | WDRM v2 | SH | CWSP | 152 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 2023 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0 | 0.00097924 | Tier 2 | CWSP - 2023 ICUG
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 | WDRM v2 | SH | CWSP | 144 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.218 | 0 | 0 | 2.218 | 2023 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 |  | 144 | 0.28655 |  | 2787 | 0 | 0.00020217 | Tier 2 | CWSP 2022-2023
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 | WDRM v2 | SH | CWSP | 144 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4638 | 0 | 0 | 3.4638 | 0 | 0 | 0 | 0 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572 | 2023 | 0.06572 | 0 | 0 | 0.06572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 |  | 144 | 0.28655 |  | 2787 | 0 | 0.00020217 | Tier 2 | CWSP 2022-2023
35331305 | CWSP ANDERSON 1103 LR1600 PH2.4 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 2023 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | CWSP - 2023 ICUG
35331304 | CWSP ANDERSON 1103 LR1600 PH2.3 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4829 | -122.2057 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35331303 | CWSP ANDERSON 1103 LR1600 PH2.2 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4832 | -122.214 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35311894 | CWSP ANDERSON 1103 LR1600 PH2.1 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4768 | -122.2276 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | 2023 ICUG
35298571 | CWSP ANDERSON 1103 LR1600 PH1 | WDRM v2 | SH | CWSP | 143 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 2023 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0 | 0.00011858 | Tier 2 | CWSP 2022-2023
35279627 | X22: CWSP - PASO ROBLES 1103 LRN50 PH 1. | WDRM v2 | SH | CWSP | 138 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 2024 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7253 | -120.8701 | WDRM v2 |  | 138 | 0.30039 |  | 742 | 0 | 0.0034276 | Tier 2 | CWSP 2022-2023
35249877 | REMG 755 - COARSEGOLD 2104, MELVIN | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 1.0299 | 2023 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.7142 | 0 | 0 | 3.7142 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693 | 2023 | 2.7693 | 0 | 0 | 2.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35249875 | X22: CWSP - COARSEGOLD 21046210 PH 1.2 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6394 | 0 | 0 | 2.6394 | 2023 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35240165 | X22: CWSP - COARSEGOLD 21046210 PH 1.1 | WDRM v2 | SH | CWSP | 132 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8498 | 0 | 0 | 3.8498 | 2023 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 |  | 132 | 0.30465 |  | 1380 | 0 | 0.0011778 | Tier 2 | CWSP 2022-2023
35332218 | PSPS COTTONWOOD 1102 LR544790 PH 1.2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26 | 2023 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35332213 | PSPS COTTONWOOD 1102 LR544790 PH 2.2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3701 | 0 | 2.3701 | 2023 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35316561 | PSPS - COTTONWOOD 1102544790 PH 2 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 2023 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35311899 | PSPS - COTTONWOOD 1102544790 PH 1 | WDRM v2 | SH | PSPS | 123 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 3.44 | 2023 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0 | 0.0007912 | Tier 2 | PSPS - 2023 ICUG
35404729 | PSPS - VACAVILLE 1108 LR38316 PH 1.5 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4295 | -122.0489 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35404728 | PSPS - VACAVILLE 1108 LR38316 PH 1.4 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4201 | -122.0443 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35404727 | PSPS - VACAVILLE 1108 LR38316 PH 1.3 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4267 | -122.0475 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334755 | PSPS - VACAVILLE 1108 LR38316 PH 2.3 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.47 | 0 | 1.47 | 2023 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334754 | PSPS - VACAVILLE 1108 LR38316 PH 2.2 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | 0 | 3.93 | 2023 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334753 | PSPS - VACAVILLE 1108 LR38316 PH 1.2 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 2023 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35246598 | DOG TOWN & MAGALIA DAM | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8149 | -121.5802 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246595 | SKYWAY PH5 (Wagstaff to Pentz) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 5.9 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9 | 0 | 5.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.9 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7842 | -121.5991 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246594 | ROSEHILL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.7 | 0 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 0 | 3.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.7 | 0 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7382 | -121.6208 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246592 | AMERICAN (elec only) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 6.2 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 6.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7367 | -121.6125 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246591 | OAK KNOLL (Caltrans) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 4.3 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 4.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7485 | -121.6086 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246590 | ALEXANDER CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7696 | -121.579 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246589 | KLING CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.764 | -121.5986 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35320339 | PSPS - VACAVILLE 1108 LR38316 PH 2.1 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35246316 | WAYLAND (elec only) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7265 | -121.6374 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35246309 | SKYWAY PH4 (Bille to Wagstaff) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7752 | -121.6093 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35246308 | HOSPITAL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7572 | -121.5722 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35320336 | PSPS - VACAVILLE 1108 LR38316 PH 1.1 | WDRM v2 | SH | PSPS | 122 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4365 | -122.0527 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 2 | 0.0056058 | Tier 2 | PSPS - 2023 ICUG
35334234 | CWSP - BELL 1108 LR2202 PH 1.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1088 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35334233 | CWSP - BELL 1108 LR2202 PH 1.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 2024 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1075 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35334232 | CWSP - BELL 1108 LR2202 PH 1.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9855 | -121.1087 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35244220 | HONEY RUN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7717 | -121.6118 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35334231 | CWSP - BELL 1108 LR2202 PH 1.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9856 | -121.1102 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333510 | CWSP - BELL 1108 LR2202 PH 3.6 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 2024 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0081 | -121.1482 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333509 | CWSP - BELL 1108 LR2202 PH 3.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 2024 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0145 | -121.1236 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333508 | CWSP - BELL 1108 LR2202 PH 3.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 2024 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0083 | -121.1247 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333507 | CWSP - BELL 1108 LR2202 PH 3.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 2024 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0003 | -121.1276 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35244027 | SKYWAY PH6 (Old Magalia) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 5.5 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 5.5 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7285 | -121.6363 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35333506 | CWSP - BELL 1108 LR2202 PH 3.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 2024 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9995 | -121.122 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333505 | CWSP - BELL 1108 LR2202 PH 2.7 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 2023 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.143 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333504 | CWSP - BELL 1108 LR2202 PH 2.6 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 2023 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333503 | CWSP - BELL 1108 LR2202 PH 2.5 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0.3 | 0 | 1.74 | 2023 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333502 | CWSP - BELL 1108 LR2202 PH 2.4 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 | 1.74 | 2023 | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9891 | -121.1353 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35333501 | CWSP - BELL 1108 LR2202 PH 2.3 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9851 | -121.1296 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35333500 | CWSP - BELL 1108 LR2202 PH 2.2 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 2023 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1268 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | 2023 ICUG
35314416 | CWSP - BELL 1108 LR2202 PH 3.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 2024 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9981 | -121.1168 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35314415 | CWSP - BELL 1108 LR2202 PH 2.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 2024 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35311896 | CWSP - BELL 1108 LR2202 PH 1.1 | WDRM v2 | SH | CWSP | 118 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | Y | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1091 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0 | 0.00023693 | Tier 2 | CWSP - 2023 ICUG
35149246 | STS-COND_IDLE_REMV-16251 HWY 101*JM | WDRM v2 | IF | 0 | 110 | V2 Top Risk | Idle Facilities | 2AF | MAPP | In-Construction | Y | N | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18277 | 0.18277 | 2023 | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hopland | Mendocino | 38.9503 | -123.0881 | WDRM v2 |  | 110 | 0.32431 |  | 519 | 2 | 0.0051934 | Tier 2 | Idle Facilities
35264182 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.3 | WDRM v2 | SH | CWSP | 108 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6348 | 0 | 0 | 2.6348 | 0 | 0 | 0 | 0 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765 | 2023 | 0.17765 | 0 | 0 | 0.17765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6278 | -120.0209 | WDRM v2 |  | 108 | 0.32463 |  | 2888 | 0 | 0.0001675 | Tier 2 | CWSP 2022-2023
35264181 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.2 | WDRM v2 | SH | CWSP | 108 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.7506 | 0 | 0 | 2.7506 | 0 | 0 | 0 | 0 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585 | 2023 | 1.8585 | 0 | 0 | 1.8585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6365 | -120.0218 | WDRM v2 |  | 108 | 0.32463 |  | 2888 | 0 | 0.0001675 | Tier 2 | CWSP 2022-2023
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | WDRM v2 | SH | CWSP | 100 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25871 | 0 | 0.25871 | 2023 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0 | 0.00022756 | Tier 2 | CWSP 2022-2023
35243447 | CWSP - DESCHUTES 11041370 PH 2.1 | WDRM v2 | SH | CWSP | 100 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.573 | -122.2386 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0 | 0.00022756 | Tier 2 | CWSP 2022-2023
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 | WDRM v2 | SH | CWSP | 99 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.5917 | -122.2743 | WDRM v2 |  | 99 | 0.34786 |  | 2481 | 0 | 0.00031475 | Tier 2 | CWSP 2022-2023
35243448 | CWSP - DESCHUTES 110449024 PH 2.1 | WDRM v2 | SH | CWSP | 99 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5929 | -122.2396 | WDRM v2 |  | 99 | 0.34786 |  | 2481 | 0 | 0.00031475 | Tier 2 | CWSP 2022-2023
35254940 | REMG 761 - VOLTA 1101, BATTLE CREEK | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64697 | 0.64697 | 2023 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35254738 | REMG 760 - VOLTA 1101, WILDCAT | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.018 | 1.018 | 2023 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35254658 | CWSP - VOLTA 11011568 PH 1.4 | WDRM v2 | SH | CWSP | 85 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447 | 2023 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 & 3 | CWSP 2022-2023
35243444 | REMG 757 - VOLTA 1101, PRESLEIGH | WDRM v2 | SH | REMG | 85 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 |  | 85 | 0.36191 |  | 2428 | 0 | 0.00033385 | Tier 2 | CWSP 2022-2023
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 | WDRM v2 | SH | CWSP | 78 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0985 | 0 | 0 | 2.0985 | 2023 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2635 | -119.7123 | WDRM v2 |  | 78 | 0.37306 |  | 1728 | 0 | 0.00074257 | Tier 2 | CWSP 2022-2023
35254259 | CWSP - VOLTA 1101CB PH 1.3 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22803 | 0.275 | 0 | 0.50303 | 2023 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35254258 | X22: CWSP - VOLTA 1101CB PH 1.2 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3525 | 0 | 0 | 1.3525 | 2023 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35240166 | CWSP - VOLTA 1101CB PH 1.1 | WDRM v2 | SH | CWSP | 76 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.46326 | 0.015341 | 0 | 0.4786 | 0 | 0 | 0 | 0 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 2023 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0 | 0.00043332 | Tier 2 & 3 | CWSP 2022-2023
35293846 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.9 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85985 | 0 | 0.85985 | 2023 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293845 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 0 | 1.3799 | 2023 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3031 | -123.057 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293844 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 | 0.95985 | 2023 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2984 | -123.0591 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293843 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.31 | 0 | 0 | 1.31 | 2023 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2953 | -123.0616 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293841 | CWSP - POTTER VALLEY PH 11051904 PH1.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 2024 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2927 | -123.085 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293775 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0 | 0.82992 | 2023 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3018 | -123.0942 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293774 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 2024 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3095 | -123.0931 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35293770 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 2024 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3146 | -123.0942 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35290808 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 2023 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290807 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 2024 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2457 | -123.1271 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290510 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1887 | -123.0323 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290509 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 2024 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1918 | -123.0344 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008 | 2023 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290507 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 2024 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1963 | -123.0435 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290506 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 2024 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2105 | -123.0641 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436 | 2023 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290503 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 2024 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2248 | -123.0882 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290502 | REMG 436 - POTTER VALLEY 1105, CCA-SCP | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.228 | -123.0887 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290501 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 2024 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2328 | -123.1053 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290500 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.7 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 | 1.0098 | 2023 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2537 | -123.1188 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290299 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.6 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 2023 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2594 | -123.1172 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290298 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.5 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 2023 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2619 | -123.1148 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290297 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 2023 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2696 | -123.1053 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290296 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 2023 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2715 | -123.097 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35290295 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 2023 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2738 | -123.0944 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 2024 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 2023 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254074 | CWSP POTTER VALLEY PH 1105 LR1904 PH2 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56989 | 0 | 0 | 0.56989 | 2023 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 | CWSP 2022-2023
35254073 | CWSP POTTER VALLEY PH 1105 LR1904 PH1 | WDRM v2 | SH | CWSP | 75 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0676 | 0 | 0 | 1.0676 | 2023 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 2 | 0.0046795 | Tier 2 & 3 | CWSP 2022-2023
35290514 | CWSP - HIGHLANDS 1102 LR623120 PH1.5 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9794 | -122.6125 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290513 | CWSP - HIGHLANDS 1102 LR623120 PH1.4 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9769 | -122.6124 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290512 | CWSP - HIGHLANDS 1102 LR623120 PH1.3 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9612 | -122.6089 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35290511 | CWSP - HIGHLANDS 1102 LR623120 PH1.2 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.979 | -122.6124 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35254072 | CWSP - HIGHLANDS 1102 LR 623120 | WDRM v2 | SH | CWSP | 74 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9544 | -122.6079 | WDRM v2 |  | 74 | 0.3774 |  | 1256 | 0 | 0.00146 | Tier 2 | CWSP 2022-2023
35278888 | +X22: CWSP - PASO ROBLES 1103 LRN54 PH2. | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 2024 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6848 | -120.73 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278887 | +X22: CWSP -PASO ROBLES 1103 LRN54 PH2.6 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4799 | 0 | 0 | 1.4799 | 2023 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6819 | -120.738 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278884 | +CWSP - PASO ROBLES 1103 LRN54 PH2.3 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7701 | 0 | 0 | 2.7701 | 2023 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6807 | -120.7554 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278883 | +CWSP - PASO ROBLES 1103 LRN54 PH2.2 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 0 | 1.81 | 2023 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6795 | -120.745 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278882 | +CWSP - PASO ROBLES 1103 LRN54 PH1.4 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6322 | 0 | 0 | 2.6322 | 0 | 0 | 0 | 0 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701 | 2023 | 0.90701 | 0 | 0 | 0.90701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6747 | -120.7423 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35278881 | +CWSP - PASO ROBLES 1103 LRN54 PH1.3 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6799 | 0 | 0 | 2.6799 | 2023 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6635 | -120.7259 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1.1 | WDRM v2 | SH | CWSP | 69 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.6725 | 0 | 0 | 2.6725 | 0 | 0 | 0 | 0 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267 | 2023 | 0.1267 | 0 | 0 | 0.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6543 | -120.7258 | WDRM v2 |  | 69 | 0.38568 |  | 940 | 0 | 0.0024787 | Tier 2 | CWSP 2022-2023
35301114 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 2024 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8694 | -120.979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35301113 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 2024 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8632 | -120.9814 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35301112 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067235 | 0.52576 | 0 | 0.59299 | 2023 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35300934 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 2024 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8708 | -120.9825 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35300933 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | Y | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59489 | 0 | 0.59489 | 2023 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293847 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.8 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 2024 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8704 | -121.0217 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293677 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.7 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 2024 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8918 | -120.9988 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293676 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 2024 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8745 | -121.0198 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293675 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 2024 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8795 | -121.0164 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293674 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 2024 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8882 | -121.0144 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293673 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 2024 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8939 | -121.0149 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293672 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 2024 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9075 | -121.0168 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293509 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.6 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 2024 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8608 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35227481 | HILLPARK LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 2023 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7392 | -121.5724 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227417 | CHAPARRAL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7323 | -121.6513 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35227415 | JARVIS LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 5.2 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | 5.2 | 2023 | 0 | 5.2 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7389 | -121.6402 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227413 | STARLIGHT CT | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 5.6 | 0 | 5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 5.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7423 | -121.6423 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35227412 | PENTZ PH1 (Arrowhead to Fickett) | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2024 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.769 | -121.5786 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227411 | COPELAND RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7595 | -121.6024 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227409 | SIERRA PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7501 | -121.6242 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227408 | PEARSON RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2023 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7524 | -121.6126 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227406 | COLLEGE HILL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ADER | Estimating | N | Y | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 4.5 | 2023 | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7523 | -121.6185 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227405 | SHADOWBROOK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0.3 | 2023 | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7578 | -121.6071 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227404 | ACADEMY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2023 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7538 | -121.6172 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227403 | MAPLE PARK | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7616 | -121.6079 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35227402 | STINSON LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2023 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7703 | -121.6071 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227401 | CAMELLIA DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 2023 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7628 | -121.6233 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227400 | OAK WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7712 | -121.6031 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 2023 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293507 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.4 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 2024 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8774 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293506 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 2024 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8803 | -121.0037 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35293505 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 2024 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8782 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254069 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 2024 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8777 | -120.9979 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254068 | CWSP - MOUNTAIN QUARRIES 2101 CB PH2 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 2024 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | WDRM v2 | SH | CWSP | 68 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 0.43996 | 0 | 0.47992 | 2023 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | CWSP 2022-2023
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | WDRM v2 | SH | PSPS | 68 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84924 | 0 | 0.84924 | 2023 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 2 | 0.017565 | Tier 2 | PSPS - Community Resiliency
35320443 | CWSP - JAMESON 1102865502 | WDRM v2 | SH | CWSP | 67 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.236 | -122.1528 | WDRM v2 |  | 67 | 0.38957 |  | 1581 | 0 | 0.00088788 | Tier 2 | 2023 ICUG
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 1.81 | 2023 | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35334750 | PSPS - VACAVILLE 1108 LR8762 PH 1.2 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 2023 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35320334 | PSPS - VACAVILLE 1108 LR8762 PH 2.0 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2023 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35320333 | PSPS - VACAVILLE 1108 LR8762 PH 1.1 | WDRM v2 | SH | PSPS | 64 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 2023 | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0 | 0.0032459 | Tier 2 | PSPS - 2023 ICUG
35277931 | CWSP - AUBERRY 1101CB PH2.4 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0503 | -119.4639 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277930 | CWSP - AUBERRY 1101CB PH2.3 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 | 0.33 | 2023 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0528 | -119.4629 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277929 | CWSP - AUBERRY 1101CB PH2.2 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5536 | 0 | 0 | 2.5536 | 2023 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0578 | -119.4739 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277926 | AUBERRY 1101CB PH1.3 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.4381 | 0 | 0 | 3.4381 | 0 | 0 | 0 | 0 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843 | 2023 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0749 | -119.4852 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35277925 | CWSP - AUBERRY 1101CB PH1.2 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 2023 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35254079 | X22: CWSP - AUBERRY 1101 CB PH2.1 | WDRM v2 | SH | CWSP | 63 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 2.4 | 2023 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0677 | -119.4958 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0 | 0.00047477 | Tier 2 | CWSP 2022-2023
35250738 | CWSP - COARSEGOLD 21045310 PH 2.3 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4856 | 0 | 0 | 3.4856 | 2023 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35250737 | CWSP - COARSEGOLD 21045310 PH 2.2 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8564 | 0 | 0 | 2.8564 | 2023 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35249874 | CWSP - COARSEGOLD 21045310 PH 3.3 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35249873 | CWSP - COARSEGOLD 21045310 PH 3.2 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35240163 | CWSP - COARSEGOLD 21045310 PH 3.1 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | WDRM v2 | SH | CWSP | 61 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 2023 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 |  | 61 | 0.39401 |  | 1416 | 0 | 0.001126 | Tier 2 | CWSP 2022-2023
35311135 | CWSP - POTTER VALLEY PH 1104 95878 PH1.9 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311134 | CWSP - POTTER VALLEY PH 1104 95878 PH1.8 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311133 | CWSP - POTTER VALLEY PH 1104 95878 PH1.7 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311132 | CWSP - POTTER VALLEY PH 1104 95878 PH1.6 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35311131 | CWSP - POTTER VALLEY PH 1104 95878 PH1.5 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310715 | CWSP - POTTER VALLEY PH 1104 95878 PH1.4 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310714 | CWSP - POTTER VALLEY PH 1104 95878 PH1.3 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35310713 | CWSP - POTTER VALLEY PH 1104 95878 PH1.2 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35250579 | CWSP - POTTER VALLEY PH 1104 95878 PH1.1 | WDRM v2 | SH | CWSP | 60 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 |  | 60 | 0.3965 |  | 2459 | 0 | 0.00032085 | Tier 2 & 3 | CWSP 2022-2023
35283340 | CWSP HARTLEY 1101 LR698 PH 1.6 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 2023 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.105 | -122.9581 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283199 | CWSP HARTLEY 1101 LR698 PH 1.5 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2701 | 0 | 0 | 1.2701 | 2023 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0813 | -122.9625 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283198 | CWSP HARTLEY 1101 LR698 PH 1.4 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27803 | 0 | 0.27803 | 2023 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283197 | CWSP HARTLEY 1101 LR698 PH 1.3 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4381 | 0 | 0 | 2.4381 | 2023 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0946 | -122.9632 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35283196 | CWSP HARTLEY 1101 LR698 PH 1.2 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3345 | 0 | 0 | 1.3345 | 2023 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.095 | -122.9656 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35250576 | CWSP - HARTLEY 1101 LR 698 | WDRM v2 | SH | CWSP | 58 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.217 | 0 | 0 | 1.217 | 2023 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0803 | -122.9513 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 2 | 0.0056859 | Tier 2 | CWSP 2022-2023
35274597 | CWSP MARIPOSA 2101 CB PH 1.2 | WDRM v2 | SH | CWSP | 57 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63295 | 0 | 0 | 0.63295 | 2023 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5054 | -120.0067 | WDRM v2 |  | 57 | 0.39837 |  | 82 | 2 | 0.019246 | Tier 2 | CWSP 2022-2023
35250573 | CWSP - MARIPOSA 2101 CB | WDRM v2 | SH | CWSP | 57 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7591 | 0 | 0 | 1.7591 | 2023 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5046 | -120.0081 | WDRM v2 |  | 57 | 0.39837 |  | 82 | 2 | 0.019246 | Tier 2 | CWSP 2022-2023
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 2023 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279122 | CWSP - STANISLAUS 1701 CB PH1.5 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90909 | 0 | 0 | 0.90909 | 2023 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1379 | -120.3707 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279121 | CWSP - STANISLAUS 1701 CB PH1.4 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77235 | 0 | 0 | 0.77235 | 2023 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1797 | -120.3786 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.004 | 0 | 1.004 | 2023 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3449 | 0 | 1.3449 | 2023 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35250578 | CWSP - STANISLAUS 1701 CB PH1.1 | WDRM v2 | SH | CWSP | 56 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4174 | 0 | 0 | 2.4174 | 2023 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1376 | -120.3702 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 1 | 0.018647 | Tier 2 & 3 | CWSP 2022-2023
35219591 | CWSP - OLETA 1101754718 PH1.1 | WDRM v2 | SH | CWSP | 54 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 1.25 | 2023 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | Amador | 38.4692 | -120.8536 | WDRM v2 |  | 54 | 0.40712 |  | 2197 | 0 | 0.00043538 | Tier 2 | Top 250 Miles
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0.14489 | 2023 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7034 | 0 | 0 | 1.7034 | 2023 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | WDRM v2 | SH | CWSP | 52 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4055 | 0 | 0 | 2.4055 | 2023 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 |  | 52 | 0.41883 |  | 86 | 1 | 0.018983 | Tier 2 | Top 250 Miles
35280362 | CWSP - MARIPOSA 2102440236 PH1.4 | WDRM v2 | SH | CWSP | 50 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047348 | 0.13258 | 0 | 0.17992 | 2023 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0 | 0.0069412 | Tier 2 & 3 | Top 250 Miles
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | WDRM v2 | SH | CWSP | 50 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 0.88182 | 0 | 0.27973 | 1.1616 | 0 | 0 | 0 | 0 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364 | 2023 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9482 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0 | 0.0069412 | Tier 2 & 3 | Top 250 Miles
35316537 | CWSP - OREGON TRAIL 110335002 PH1.7 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 2024 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.624 | -122.3049 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 miles
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.2771 | 0 | 0 | 1.2771 | 0 | 0 | 0 | 0 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432 | 2023 | 0.049432 | 0 | 0 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 2024 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8206 | 0 | 0 | 2.8206 | 2023 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.71345 | 0 | 0 | 0.71345 | 0 | 0 | 0 | 0 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489 | 2023 | 0.14489 | 0 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234396 | X22: CWSP - OREGON TRAIL 110335002 PH5.5 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5604 | 0 | 0 | 1.5604 | 2023 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.71 | 0 | 0 | 2.71 | 2023 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 0 | 1.79 | 2023 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 0 | 0 | 2.42 | 2023 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 2023 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5468 | 0 | 0 | 1.5468 | 2023 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233951 | X22: CWSP - OREGON TRAIL 110335002 PH1.6 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6214 | 0 | 0 | 1.6214 | 2023 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233949 | X22: CWSP - OREGON TRAIL 110335002 PH1.4 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.7706 | 0 | 0 | 1.7706 | 0 | 0 | 0 | 0 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411 | 2023 | 1.6411 | 0 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 2024 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 | 2.19 | 2023 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 2024 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | WDRM v2 | SH | CWSP | 49 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 | 2.31 | 2023 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6299 | -122.2445 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0 | 0.00034131 | Tier 2 | Top 250 Miles
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | WDRM v2 | SH | CWSP | 43 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636 | 2023 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.362 | -123.1283 | WDRM v2 |  | 43 | 0.44262 |  | 1733 | 0 | 0.00073797 | Tier 2 | Top 250 Miles
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | UNSC | Ready for Construction | Y | N | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87216 | 0.87216 | 2023 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53996 | 0 | 0.53996 | 2023 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | WDRM v2 | SH | CWSP | 42 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7282 | 0 | 3.7282 | 2023 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 3 | 0.0073117 | Tier 3 | Top 250 Miles
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | WDRM v2 | SH | CWSP | 37 | V2 Top Risk | Base SH | 08W | DOCC | In-Construction | Y | N | 3.6491 | 0 | 0 | 3.6491 | 0 | 0 | 0 | 0 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758 | 2023 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | WDRM v2 |  | 37 | 0.46772 |  | 1554 | 0 | 0.00091401 | Tier 2 | Top 250 Miles
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | WDRM v2 | SH | CWSP | 29 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 0.4214 | 0 | 0.4214 | 0 | 0 | 0 | 0 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288 | 2023 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0 | 0.0002242 | Tier 2 | Top 250 Miles
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | WDRM v2 | SH | CWSP | 29 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.92822 | 0 | 0.86723 | 1.7955 | 0.87803 | 0 | 0 | 0.87803 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.86723 | 0.91742 | 2023 | 0.050189 | 0 | 0.86723 | 0.91742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4631 | -121.5149 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0 | 0.0002242 | Tier 2 | Top 250 Miles
35231631 | OCGC-CWSP-HIGHLANDS 1102628 PH 1.13 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | FICL | In-Construction | Y | N | 0.44867 | 0 | 0 | 0.44867 | 0 | 0 | 0 | 0 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428 | 2023 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2165 | 0 | 0 | 1.2165 | 2023 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231628 | REMG 729 - HIGHLANDS 1102, WATERTROUGH | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 | 0.39867 | 2023 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231626 | OCGC_X22: CWSP-HIGHLANDS 1102628 PH 1.8 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | MAPP | In-Construction | Y | N | 0.78295 | 0 | 0.64962 | 1.4326 | 0 | 0 | 0 | 0 | 0.78295 | 0 | 0.60417 | 1.3871 | 0 | 0 | 0.045455 | 0.045455 | 2023 | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 2023 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231624 | REMG 728 - HIGHLANDS 1102, BUCKSKIN WAY | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231623 | REMG 205 - HIGHLANDS 1102, OASIS | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35189987 | WHATEVER LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 2.7 | 2023 | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7404 | -121.5939 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35189984 | PALOMA AVE | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 2023 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7471 | -121.6129 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189983 | FOSTER RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6266 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35189853 | HAPPY WOODS | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7681 | -121.5891 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189792 | CYPRESS LN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.9 | 0 | 3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9 | 0 | 3.9 | 2023 | 0 | 3.9 | 0 | 3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.784 | -121.5864 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35189791 | WARREN RD | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2023 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5873 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35175548 | HIGH SCHOOL MAXWELL | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2023 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7619 | -121.6125 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35175547 | PENTZ & WAGSTAFF | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 4.8 | 0 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 0 | 4.8 | 2023 | 0 | 4.8 | 0 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5797 |  |  | N/A | N/A |  | N/A | 0 | N/A | Non-HFTD | Butte Rebuild
35231622 | REMG 706 - HIGHLANDS 1102, INDIAN CREEK | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943 | 2023 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782 | 2023 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | WDRM v2 | SH | CWSP | 27 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7275 | 0 | 0 | 2.7275 | 2023 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 1 | 0.026126 | Tier 2 & 3 | Top 250 Miles
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | WDRM v2 | SH | CWSP | 21 | V2 Top Risk | Base SH | 08W | UNSE | Scoping/Scoped | Y | N | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2598 | 0 | 0 | 3.2598 | 2023 | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 2 | 0.00471 | Tier 2 | Top 250 Miles
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | WDRM v2 | SH | CWSP | 21 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0 | 0 | 0 | 0 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.028409 | 0.028409 | 0.056818 | 2023 | 0 | 0.028409 | 0.028409 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 2 | 0.00471 | Tier 2 | Top 250 Miles
35299137 | CWSP HARTLEY 1101 LR789752 PH 1.6 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57292 | 0 | 0 | 0.57292 | 2023 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.067 | -122.9672 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299136 | CWSP HARTLEY 1101 LR789752 PH 1.5 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67197 | 0 | 0 | 0.67197 | 2023 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0716 | -122.9638 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299135 | CWSP HARTLEY 1101 LR789752 PH 1.4 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92102 | 0 | 0 | 0.92102 | 2023 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0722 | -122.9571 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299134 | CWSP HARTLEY 1101 LR789752 PH 1.3 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40303 | 0 | 0 | 0.40303 | 2023 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0704 | -122.9571 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35299133 | CWSP HARTLEY 1101 LR789752 PH 1.2 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28144 | 0 | 0 | 0.28144 | 2023 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0729 | -122.9569 | WDRM v2 |  | 19 | 0.64187 |  | 595 | 0 | 0.0044545 | Tier 2 | CWSP 2022-2023
35250575 | CWSP HARTLEY 1101 LR789752 PH 1.1 | WDRM v2 | SH | CWSP | 19 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2428 | 0 | 0 | 0.2428 | 2023 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0636 | -122.9526 | WDRM v2 |  | 19 | 0.64187 |  | 2963 | 0 | 0.00014245 | Tier 2 | CWSP 2022-2023
35144480 | SHAW CIR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | PEND | Permitting/Dependency | N | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 2023 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8116 | -121.5956 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | WDRM v2 | SH | CWSP | 18 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 2023 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 |  | 18 | 0.65331 |  | 448 | 2 | 0.0062529 | Tier 2 | Top 50 Miles
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0 | 0 | 3.45 | 2023 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35127550 | MYRTLE WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F CEMA | ESTS | Estimating | N | Y | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7858 | -121.6004 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35127360 | PRINCETON WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ESTS | Estimating | N | Y | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7461 | -121.6435 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 2 | Butte Rebuild
35126752 | APPLE | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | ADER | Estimating | N | Y | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 2024 | 0 | 0 | 0 | 0 | 0 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7333 | -121.6353 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35126750 | JERRYS WAY | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | CONS | In-Construction | N | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 2023 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7741 | -121.5895 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35126645 | CRESTVIEW | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 2023 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7612 | -121.6342 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 2023 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | N | 0.57727 | 0 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939 | 2023 | 0.43939 | 0 | 0 | 0.43939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35118676 | REDBUD DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 95F O | UNSC | Ready for Construction | N | Y | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 3.2 | 2023 | 0 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7551 | -121.6455 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35118674 | GLENDALE DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.6017 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35118673 | S PARK DR | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 3.1 | 0 | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 3.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8005 | -121.6047 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35117455 | HERMAN | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ADER | Estimating | N | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 2023 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7813 | -121.594 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 1.3212 | 0 | 1.3212 | 0 | 0 | 0 | 0 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985 | 2023 | 0 | 0.95985 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | WDRM v2 | SH | CWSP | 14 | V2 Top Risk | Base SH | 08W | CONS | In-Construction | Y | Y | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0494 | 0 | 2.0494 | 2023 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 2 | 0.006302 | Tier 2 & 3 | Top 50 Miles
35112126 | PARAGALIA | 0 |  |  | FALSE | No Risk Vintage | Community Rebuild | 08W | ESTS | Estimating | N | Y | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2024 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.78 | -121.6092 |  |  | N/A | N/A |  | N/A | 0 | N/A | Tier 3 | Butte Rebuild
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9095 | 0 | 1.9095 | 2023 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2.1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | Y | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2729 | 0 | 2.2729 | 2023 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1 | WDRM v2 | FRRB | CWSP | 11 | V2 Top Risk | Fire Rebuild | 08W | ADER | Estimating | Y | N | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 2023 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9107 | -121.3275 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0 | 0.029234 | Tier 2 & 3 | Top 50 Miles
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | WDRM v2 | SH | CWSP | 9 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.93 | -122.7428 | WDRM v2 |  | 9 | 0.87629 |  | 735 | 0 | 0.0034918 | Tier 3 | Top 50 Miles
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73068 | 0 | 0 | 0.73068 | 2023 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | Y | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 2024 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | WDRM v2 | SH | CWSP | 8 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 2024 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 3 | 0.007089 | Tier 2 | Top 50 Miles
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | WDRM v2 | SH | CWSP | 7 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8061 | 0 | 4.8061 | 2023 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 2 | 0.022602 | Tier 3 | Top 50 Miles
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | WDRM v2 | SH | CWSP | 7 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | Y | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85511 | 0 | 0.85511 | 2023 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 2 | 0.022602 | Tier 3 | Top 50 Miles
35058839 | STS-POLE_BROK_REPL - 17 STARWOOD DR REDW | 0 | Other | 0 | FALSE | No Risk Vintage | Other | 07D | DOCC | In-Construction | Y | N | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1625 | 0 | 0 | 0.1625 | 2023 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3801 | -122.2699 | [6 empty] | 0 |  |  | 0
35342302 | CWSP - LINCOLN 1104 LR997576 PH 1.2 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0278 | -121.2938 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35334404 | FRRB - PT MORETTI 1101 P1S2 310SWAN | WDRM v2 | FRRB | FRRB | 1393 | V2 Not Top Risk | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | N | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 2023 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0671 | -122.2231 | WDRM v2 |  | 1393 | 0.033758 |  | 2485 | 0 | 0.00031335 | Tier 2 | FRRB
35332878 | CWSP - LINCOLN 1104 LR997576 PH 1.6 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0128 | -121.263 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332876 | CWSP - LINCOLN 1104 LR997576 PH 1.5 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0181 | -121.2717 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332874 | CWSP - LINCOLN 1104 LR997576 PH 1.4 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | PEND | Permitting/Dependency | Y | N | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0224 | -121.2874 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35332872 | CWSP - LINCOLN 1104 LR997576 PH 1.3 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ESTS | Estimating | Y | N | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 2024 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0337 | -121.3086 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG
35320453 | CWSP - LINCOLN 1104 LR997576 PH 1.1 | WDRM v2 | SH | CWSP | 693 | V2 Top Risk | Base SH | 08W | ADER | Estimating | Y | N | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 2023 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0371 | -121.3366 | WDRM v2 |  | 693 | 0.11252 |  | 3098 | 0 | 0.00010977 | Tier 2 | 2023 ICUG

## WMP Workplan_Pivot (hidden)
WMP GH-05 10k UG (Y/N) | Y
Order Description | Category | MAT | SAP Status | Div | Region | City | County | Applicable Risk Model | Circuit Protection Zone (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | v3 Mean Risk | HFTD Tier | Sum of Total Planned UG Miles | Sum of UG - 2022 Complete | Sum of UG - 2023 Forecast | Sum of UG - 2024 Forecast | Sum of UG - 2025 Forecast | Sum of UG - 2026 Forecast | Sum of Latitude | Sum of Longitude
ACADEMY | Community Rebuild | 95F O | PEND | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 39.7538 | -121.6172
ALEXANDER CT | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.3 | 0 | 0 | 3.3 | 0 | 0 | 39.7696 | -121.579
AMERICAN (elec only) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 6.2 | 0 | 0 | 6.2 | 0 | 0 | 39.7367 | -121.6125
ANDOVER DR | Community Rebuild | 08W | PEND | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.6 | 0 | 0 | 2.6 | 0 | 0 | 39.8121 | -121.5914
APPLE | Community Rebuild | 95F O | ADER | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.9 | 0 | 0 | 1.9 | 0 | 0 | 39.7333 | -121.6353
BILLE WAGSTAFF | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 39.7777 | -121.6077
BOQUEST | Community Rebuild | 95F O | PEND | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 39.7583 | -121.6291
BR-12-5A HWY 191 RELOCATION, PARB | Other | 10K | CONS | NV | Region 2 - North East | Paradise | Butte | WDRM v2 | PARADISE 11042034 | 0.025842 | Paradise 11042034 | 0.0076725 | Tier 2 & 3 | 2.4956 | 0 | 0 | 2.4956 | 0 | 0 | 39.7352 | -121.6113
CAMELLIA DR | Community Rebuild | 95F O | PEND | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 39.7628 | -121.6233
CHAPARRAL | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 2 | 2.8 | 0 | 0 | 2.8 | 0 | 0 | 39.7323 | -121.6513
CITADEL WAY | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 39.8221 | -121.5955
COLLEGE HILL | Community Rebuild | 95F O | ADER | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 39.7523 | -121.6185
COPELAND RD | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.7 | 0 | 0 | 2.7 | 0 | 0 | 39.7595 | -121.6024
CRESTON DR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 39.8211 | -121.6013
CRESTVIEW | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 39.7612 | -121.6342
CWSP - ALLEGHANY 1102CB NEVADA PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Nevada City | Nevada | WDRM v3 | ALLEGHANY 1102CB | 0.018204 | ALLEGHANY 1102CB | 0.023951 | Tier 3 | 9.69 | 0 | 0 | 0 | 9.69 | 0 | 39.4393 | -120.8173
CWSP - ALLEGHANY 1102CB NEVADA PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Nevada City | Nevada | WDRM v3 | ALLEGHANY 1102CB | 0.018204 | ALLEGHANY 1102CB | 0.023951 | Tier 3 | 4.89 | 0 | 0 | 0 | 0 | 4.89 | 39.439 | -120.8169
CWSP - ALLEGHANY 1102CB NEVADA PH 5 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Nevada City | Nevada | WDRM v3 | ALLEGHANY 1102CB | 0.018204 | ALLEGHANY 1102CB | 0.023951 | Tier 3 | 6.7701 | 0 | 0 | 0 | 0 | 6.7701 | 39.4367 | -120.815
CWSP - ALLEGHANY 1102CB SIERRA PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Alleghany | Sierra | WDRM v3 | ALLEGHANY 1102CB | 0.018204 | ALLEGHANY 1102CB | 0.023951 | Tier 3 | 6.7201 | 0 | 0 | 0 | 0 | 6.7201 | 39.4637 | -120.8433
CWSP - ALLEGHANY 1102CB SIERRA PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Alleghany | Sierra | WDRM v3 | ALLEGHANY 1102CB | 0.018204 | ALLEGHANY 1102CB | 0.023951 | Tier 3 | 6.24 | 0 | 0 | 0 | 0 | 6.24 | 39.4634 | -120.843
CWSP - ANTLER 11011384 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011384 | 0.0028857 | ANTLER 11011384 | 0.038738 | Tier 2 | 11.84 | 0 | 0 | 0 | 0 | 11.84 | 40.8936 | -122.3819
CWSP - ANTLER 11011384 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011384 | 0.0028857 | ANTLER 11011384 | 0.038738 | Tier 2 | 3.73 | 0 | 0 | 0 | 0 | 3.73 | 40.8928 | -122.3816
CWSP - ANTLER 11011520 PH 1.2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011520 | 0.002519 | ANTLER 11011520 | 0.018782 | Tier 2 | 1.937 | 0 | 0 | 0 | 0 | 1.937 | 40.9066 | -122.3834
CWSP - ANTLER 11011520 PH 1.3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011520 | 0.002519 | ANTLER 11011520 | 0.018782 | Tier 2 | 0.057 | 0 | 0 | 0 | 0 | 0.057 | 40.905 | -122.3847
CWSP - ANTLER 11011520 PH 1.4 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011520 | 0.002519 | ANTLER 11011520 | 0.018782 | Tier 2 | 0.369 | 0 | 0 | 0 | 0 | 0.369 | 40.9052 | -122.3826
CWSP - ANTLER 11011520 PH1.1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 11011520 | 0.002519 | ANTLER 11011520 | 0.018782 | Tier 2 | 6.553 | 0 | 0 | 0 | 0 | 6.553 | 40.8994 | -122.3862
CWSP - ANTLER 1101CB | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Lakehead | Shasta | WDRM v3 | ANTLER 1101CB | 0.0049349 | ANTLER 1101CB | 0.0187 | Tier 2 | 1.99 | 0 | 0 | 0 | 0 | 1.99 | 40.8947 | -122.3807
CWSP - APPLE HILL 110413512 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 110413512 | 0.041392 | APPLE HILL 110413512 | 0.016427 | Tier 2 & 3 | 8.19 | 0 | 0 | 0 | 8.19 | 0 | 38.7391 | -120.668
CWSP - APPLE HILL 110413512 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 110413512 | 0.041392 | APPLE HILL 110413512 | 0.016427 | Tier 2 & 3 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 38.7442 | -120.6585
CWSP - APPLE HILL 110413512 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 110413512 | 0.041392 | APPLE HILL 110413512 | 0.016427 | Tier 3 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 38.7443 | -120.6579
CWSP - APPLE HILL 110413512 PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 110413512 | 0.041392 | APPLE HILL 110413512 | 0.016427 | Tier 3 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 38.7444 | -120.6569
CWSP - APPLE HILL 1104CB | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 1104CB | 0.032289 | APPLE HILL 1104CB | 0.025967 | Tier 2 | 4.7299 | 0 | 0 | 4.7299 | 0 | 0 | 38.7395 | -120.6766
CWSP - APPLE HILL 21027502 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | APPLE HILL 21027502 | 0.027532 | APPLE HILL 21027502 | 0.020812 | Tier 2 & 3 | 9.75 | 0 | 0 | 9.75 | 0 | 0 | 38.6829 | -120.6611
CWSP - APPLE HILL 21027502 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | APPLE HILL 21027502 | 0.027532 | APPLE HILL 21027502 | 0.020812 | Tier 3 | 15.51 | 0 | 0 | 0 | 0 | 15.51 | 38.683 | -120.6604
CWSP - APPLE HILL 21027502 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | APPLE HILL 21027502 | 0.027532 | APPLE HILL 21027502 | 0.020812 | Tier 3 | 8.4701 | 0 | 0 | 8.4701 | 0 | 0 | 38.6833 | -120.6598
CWSP - APPLE HILL 2102836878 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 & 3 | 6.04 | 0 | 0 | 0 | 6.04 | 0 | 38.7372 | -120.6759
CWSP - APPLE HILL 2102836878 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 & 3 | 7.5 | 0 | 0 | 7.5 | 0 | 0 | 38.737 | -120.6759
CWSP - APPLE HILL 2102836878 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 3 | 7.5 | 0 | 0 | 7.5 | 0 | 0 | 38.7361 | -120.6759
CWSP - APPLE HILL 2102836878 PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 & 3 | 7.5 | 0 | 0 | 0 | 7.5 | 0 | 38.7357 | -120.6759
CWSP - APPLE HILL 2102836878 PH 5 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 & 3 | 7.5 | 0 | 0 | 0 | 7.5 | 0 | 38.7349 | -120.6759
CWSP - APPLE HILL 2102836878 PH 6 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 & 3 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 38.7343 | -120.6759
CWSP - APPLE HILL 2102836878 PH 7 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camino | El Dorado | WDRM v3 | APPLE HILL 2102CB | 0.12006 | APPLE HILL 2102836878 | 0.01606 | Tier 2 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 38.7338 | -120.6759
CWSP - AUBERRY 1101CB PH1.2 | Base SH | 08W | CONS | FR | Region 5 - Central Valley | Auberry | Fresno | WDRM v2 | AUBERRY 1101CB | 0.39206 | AUBERRY 1101CB | 0.00047477 | Tier 2 | 0.14148 | 0 | 0.14148 | 0 | 0 | 0 | 37.0746 | -119.4845
CWSP - AUBERRY 1101R2578 PH3.4 | Base SH | 08W | PEND | FR | Region 5 - Central Valley | Tollhouse | Fresno | WDRM v2 | AUBERRY 1101R2578 | 0.27714 | AUBERRY 1101R2578 | 0.0047219 | Tier 2 | 0.41496 | 0 | 0 | 0 | 0 | 0.41496 | 36.9797 | -119.3677
CWSP - BELL 1108 LR2202 PH 1.1 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 2.76 | 0 | 0 | 2.76 | 0 | 0 | 38.9961 | -121.1091
CWSP - BELL 1108 LR2202 PH 1.3 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 1.01 | 0 | 0 | 1.01 | 0 | 0 | 38.9855 | -121.1087
CWSP - BELL 1108 LR2202 PH 1.5 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 2.3 | 0 | 0 | 2.3 | 0 | 0 | 38.9781 | -121.1088
CWSP - BELL 1108 LR2202 PH 2.1 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 2.05 | 0 | 0 | 2.05 | 0 | 0 | 38.9962 | -121.1167
CWSP - BELL 1108 LR2202 PH 2.3 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 2.96 | 0 | 0 | 2.96 | 0 | 0 | 38.9851 | -121.1296
CWSP - BELL 1108 LR2202 PH 2.5 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 38.9959 | -121.1355
CWSP - BELL 1108 LR2202 PH 2.6 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 38.9992 | -121.1363
CWSP - BELL 1108 LR2202 PH 3.1 | Base SH | 08W | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | BELL 11082202 | 0.32016 | BELL 11082202 | 0.00023693 | Tier 2 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 38.9981 | -121.1168
CWSP - BONNIE NOOK 1101CB PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Alta | Placer | WDRM v3 | BONNIE NOOK 1101CB | 0.026396 | BONNIE NOOK 1101CB | 0.02949 | Tier 3 | 9.7201 | 0 | 0 | 0 | 9.7201 | 0 | 39.2148 | -120.8091
CWSP - BONNIE NOOK 1101CB PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Dutch Flat | Placer | WDRM v3 | BONNIE NOOK 1101CB | 0.026396 | BONNIE NOOK 1101CB | 0.02949 | Tier 3 | 10.34 | 0 | 0 | 0 | 0 | 10.34 | 39.202 | -120.8364
CWSP - BONNIE NOOK 1102CB & 1103CB PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Alta | Placer | WDRM v3 | BONNIE NOOK 1102CB | 0.0071702 | BONNIE NOOK 1102CB | 0.013013 | Tier 3 | 4.7 | 0 | 0 | 4.7 | 0 | 0 | 39.2147 | -120.8091
CWSP - BONNIE NOOK 1102CB PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Alta | Placer | WDRM v3 | BONNIE NOOK 1102CB | 0.0071702 | BONNIE NOOK 1102CB | 0.013013 | Tier 3 | 9.5 | 0 | 0 | 0 | 9.5 | 0 | 39.2159 | -120.8055
CWSP - BONNIE NOOK 1102CB PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Dutch Flat | Placer | WDRM v3 | BONNIE NOOK 1102CB | 0.0071702 | BONNIE NOOK 1102CB | 0.013013 | Tier 3 | 8.2 | 0 | 0 | 0 | 8.2 | 0 | 39.2009 | -120.8105
CWSP - BONNIE NOOK 1102CB PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Dutch Flat | Placer | WDRM v3 | BONNIE NOOK 1102CB | 0.0071702 | BONNIE NOOK 1102CB | 0.013013 | Tier 3 | 9.06 | 0 | 0 | 0 | 0 | 9.06 | 39.1906 | -120.809
CWSP - BRUNSWICK 11021010 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 7.01 | 0 | 0 | 7.01 | 0 | 0 | 39.2129 | -121.0128
CWSP - BRUNSWICK 11021010 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 10.3 | 0 | 0 | 10.3 | 0 | 0 | 39.2127 | -121.0123
CWSP - BRUNSWICK 11021010 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 9.7 | 0 | 0 | 0 | 9.7 | 0 | 39.2127 | -121.0121
CWSP - BRUNSWICK 11021010 PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 8.24 | 0 | 0 | 0 | 8.24 | 0 | 39.2125 | -121.0114
CWSP - BRUNSWICK 11021010 PH 5 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 9.31 | 0 | 0 | 0 | 0 | 9.31 | 39.2123 | -121.0107
CWSP - BRUNSWICK 11021010 PH 6 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 8.3799 | 0 | 0 | 0 | 0 | 8.3799 | 39.212 | -121.0099
CWSP - BRUNSWICK 11021010 PH 7 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11021010 | 0.021168 | BRUNSWICK 11021010 | 0.011407 | Tier 3 | 6.7299 | 0 | 0 | 6.7299 | 0 | 0 | 39.2118 | -121.0092
CWSP - BRUNSWICK 11062104 PH 1.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11062104 | 0.0059169 | BRUNSWICK 11062104 | 0.0065825 | Tier 3 | 1.48 | 0 | 0 | 0 | 1.48 | 0 | 39.1989 | -121.0106
CWSP - BRUNSWICK 11062104 PH 1.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11062104 | 0.0059169 | BRUNSWICK 11062104 | 0.0065825 | Tier 3 | 3.07 | 0 | 0 | 0 | 3.07 | 0 | 39.1985 | -121.0106
CWSP - BRUNSWICK 11062104 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11062104 | 0.0059169 | BRUNSWICK 11062104 | 0.0065825 | Tier 3 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 39.1953 | -121.0108
CWSP - BRUNSWICK 11062104 PH1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11062104 | 0.0059169 | BRUNSWICK 11062104 | 0.0065825 | Tier 3 | 4.02 | 0 | 0 | 0 | 4.02 | 0 | 39.1994 | -121.0172
CWSP - BRUNSWICK 11062104 PH2.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 11062104 | 0.0059169 | BRUNSWICK 11062104 | 0.0065825 | Tier 3 | 2.24 | 0 | 0 | 2.24 | 0 | 0 | 39.1904 | -121.0028
CWSP - BRUNSWICK 110651484 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651484 | 0.052212 | BRUNSWICK 110651484 | 0.010208 | Tier 2 & 3 | 12.41 | 0 | 0 | 0 | 0 | 12.41 | 39.1909 | -120.9998
CWSP - BRUNSWICK 110651484 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651484 | 0.052212 | BRUNSWICK 110651484 | 0.010208 | Tier 2 & 3 | 9.7799 | 0 | 0 | 0 | 9.7799 | 0 | 39.1651 | -120.988
CWSP - BRUNSWICK 110651484 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651484 | 0.052212 | BRUNSWICK 110651484 | 0.010208 | Tier 2 & 3 | 9.31 | 0 | 0 | 0 | 0 | 9.31 | 39.1696 | -120.993
CWSP - BRUNSWICK 110651486 - 13993 SEVEN | Targeted UG | 3UG | PEND | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 0.12973 | 0 | 0 | 0 | 0 | 0.12973 | 39.1766 | -120.9772
CWSP - BRUNSWICK 110651486 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 4.653 | 0 | 0 | 4.653 | 0 | 0 | 39.1912 | -120.9936
CWSP - BRUNSWICK 110651486 PH 1.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 1.71 | 0 | 0 | 0 | 1.71 | 0 | 39.1911 | -120.9964
CWSP - BRUNSWICK 110651486 PH 1.3 | Targeted UG | 3UG | ESTS | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.79 | 0 | 0 | 2.79 | 0 | 0 | 39.1909 | -120.9933
CWSP - BRUNSWICK 110651486 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 8.1201 | 0 | 0 | 8.1201 | 0 | 0 | 39.1905 | -120.9887
CWSP - BRUNSWICK 110651486 PH 2.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 39.1908 | -120.984
CWSP - BRUNSWICK 110651486 PH 2.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.01 | 0 | 0 | 2.01 | 0 | 0 | 39.1902 | -120.9767
CWSP - BRUNSWICK 110651486 PH 2.4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.6 | 0 | 0 | 2.6 | 0 | 0 | 39.1857 | -120.9735
CWSP - BRUNSWICK 110651486 PH 3.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 2 & 3 | 2.268 | 0 | 0 | 2.268 | 0 | 0 | 39.1715 | -120.9736
CWSP - BRUNSWICK 110651486 PH 3.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 2 & 3 | 2.074 | 0 | 0 | 2.074 | 0 | 0 | 39.1702 | -120.972
CWSP - BRUNSWICK 110651486 PH 3.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 2 & 3 | 4.302 | 0 | 0 | 4.302 | 0 | 0 | 39.1675 | -120.969
CWSP - BRUNSWICK 110651486 PH 4.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 5.642 | 0 | 0 | 5.642 | 0 | 0 | 39.1919 | -120.9748
CWSP - BRUNSWICK 110651486 PH 4.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.778 | 0 | 0 | 2.778 | 0 | 0 | 39.1914 | -120.9614
CWSP - BRUNSWICK 110651486 PH 5.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 39.1871 | -120.9543
CWSP - BRUNSWICK 110651486 PH 5.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.134 | 0 | 0 | 0 | 2.134 | 0 | 39.1881 | -120.9474
CWSP - BRUNSWICK 110651486 PH 5.3 | Targeted UG | 3UG | ESTS | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 1.798 | 0 | 0 | 0 | 1.798 | 0 | 39.188 | -120.959
CWSP - BRUNSWICK 110651486 PH 5.4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 2.487 | 0 | 0 | 0 | 2.487 | 0 | 39.1779 | -120.9564
CWSP - BRUNSWICK 110651486 PH 6.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 39.1841 | -120.9421
CWSP - BRUNSWICK 110651486 PH 7.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 3.061 | 0 | 0 | 0 | 3.061 | 0 | 39.1851 | -120.9719
CWSP - BRUNSWICK 110651486 PH 7.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 1.312 | 0 | 0 | 0 | 1.312 | 0 | 39.1806 | -120.9751
CWSP - BRUNSWICK 110651486 PH 7.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 3.529 | 0 | 0 | 0 | 3.529 | 0 | 39.174 | -120.9729
CWSP - BRUNSWICK 110651486 PH 8 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Grass Valley | Nevada | WDRM v3 | BRUNSWICK 110651486 | 0.014797 | BRUNSWICK 110651486 | 0.0088799 | Tier 3 | 8.09 | 0 | 0 | 0 | 0 | 8.09 | 39.1907 | -120.9917
CWSP - BUCKS CREEK 1102CB - BELDEN | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Twain | Plumas | WDRM v3 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 0.51004 | 0 | 0 | 0 | 0 | 0.51004 | 40.0055 | -121.249
CWSP - BUCKS CREEK 1102CB - ROCK CREST | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Belden | Plumas | WDRM v3 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 | 0.11004 | 0 | 0 | 0 | 0 | 0.11004 | 39.9272 | -121.3169
CWSP - BUCKS CREEK 1102CB - RODGERS FLAT | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Twain | Plumas | WDRM v3 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 0.43996 | 0 | 0 | 0 | 0 | 0.43996 | 39.9591 | -121.2804
CWSP - BUCKS CREEK 1102CB PH 1 N/O HWY 7 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Twain | Plumas | WDRM v3 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 | 7.21 | 0 | 0 | 0 | 0 | 7.21 | 40.0153 | -121.2245
CWSP - BUCKS CREEK 1102CB PH 2 N/O HWY 7 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Twain | Plumas | WDRM v3 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 | 6.79 | 0 | 0 | 0 | 0 | 6.79 | 40.0158 | -121.2239
CWSP - BUELLTON 1102 Y50 PH 1.3 | Base SH | 08W | UNSE | LP | Region 4 - Central Coast | Solvang | Santa Barbara | WDRM v2 | BUELLTON 1102Y50 | 0.22624 | BUELLTON 1102Y50 | 0.00026962 | Tier 2 | 0.25625 | 0 | 0 | 0.25625 | 0 | 0 | 34.6137 | -120.1537
CWSP - BUELLTON 1102 Y50 PH 1.4 | Base SH | 08W | UNSE | LP | Region 4 - Central Coast | Solvang | Santa Barbara | WDRM v2 | BUELLTON 1102Y50 | 0.22624 | BUELLTON 1102Y50 | 0.00026962 | Tier 2 | 0.25019 | 0 | 0 | 0.25019 | 0 | 0 | 34.6137 | -120.1537
CWSP - CALISTOGA 110143924 PH 1.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Calistoga | Napa | WDRM v3 | CALISTOGA 110143924 | 0.066852 | CALISTOGA 110143924 | 0.017566 | Tier 3 | 9.0299 | 0 | 0 | 0 | 0 | 9.0299 | 38.5891 | -122.6068
CWSP - CALISTOGA 110143924 PH 2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Calistoga | Napa | WDRM v3 | CALISTOGA 110143924 | 0.066852 | CALISTOGA 110143924 | 0.017566 | Tier 3 | 5.0201 | 0 | 0 | 0 | 0 | 5.0201 | 38.5951 | -122.6024
CWSP - CLAYTON 2212 LR 96224 | Targeted UG | 3UG | UNSE | DI | Region 3 - Bay Area | Clayton | Contra Costa | WDRM v3 | CLAYTON 221296224 | 0.18755 | CLAYTON 221296224 | 0.034099 | Tier 3 | 9.6 | 0 | 0 | 0 | 0 | 9.6 | 37.9038 | -121.8741
CWSP - CLAYTON 2212614950 | Targeted UG | 3UG | UNSE | DI | Region 3 - Bay Area | Clayton | Contra Costa | WDRM v3 | CLAYTON 2212CB | 0.0014894 | CLAYTON 2212614950 | 0.018211 | Tier 2 & 3 | 0.67992 | 0 | 0 | 0 | 0 | 0.67992 | 37.9331 | -121.942
CWSP - CLAYTON 2212681608 | Targeted UG | 3UG | UNSE | DI | Region 3 - Bay Area | Clayton | Contra Costa | WDRM v3 | CLAYTON 2212Y504R | 0.18021 | CLAYTON 2212681608 | 0.016899 | Tier 2 & 3 | 10.4 | 0 | 0 | 0 | 0 | 10.4 | 37.9245 | -121.9124
CWSP - DESCHUTES 11041370 PH 2.3 | Base SH | 08W | CONS | NV | Region 2 - North East | Bella Vista | Shasta | WDRM v2 | DESCHUTES 11041370 | 0.34561 | DESCHUTES 11041370 | 0.00022756 | Tier 2 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 40.6324 | -122.2376
CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Base SH | 08W | CONS | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v2 | EL DORADO PH 210119752 | 0.0103 | EL DORADO PH 210119752 | 0.022482 | Tier 3 | 0.57576 | 0 | 0 | 0.57576 | 0 | 0 | 38.7821 | -120.6094
CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Base SH | 08W | PEND | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v2 | EL DORADO PH 210119752 | 0.0103 | EL DORADO PH 210119752 | 0.022482 | Tier 3 | 2.2513 | 0 | 2.2513 | 0 | 0 | 0 | 38.7821 | -120.6094
CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Base SH | 08W | DOCC | SI | Region 2 - North East | Placerville | El Dorado | WDRM v2 | EL DORADO PH 210119752 | 0.0103 | EL DORADO PH 210119752 | 0.022482 | Tier 3 | 0.44621 | 0.44621 | 0 | 0 | 0 | 0 | 38.692 | -120.6132
CWSP - EL DORADO 2101- 19752 - PH 1.3 | Base SH | 08W | CONS | SI | Region 2 - North East | Placerville | El Dorado | WDRM v2 | EL DORADO PH 210119752 | 0.0103 | EL DORADO PH 210119752 | 0.022482 | Tier 3 | 0.37955 | 0.04072 | 0.33883 | 0 | 0 | 0 | 38.6839 | -120.6354
CWSP - EL DORADO 21016852 - PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 21016852 | 0.0085289 | EL DORADO PH 21016852 | 0.0042306 | Tier 3 | 7.2701 | 0 | 0 | 0 | 7.2701 | 0 | 38.7467 | -120.5634
CWSP - EL DORADO 21016852 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 21016852 | 0.0085289 | EL DORADO PH 21016852 | 0.0042306 | Tier 3 | 11.9201 | 0 | 0 | 0 | 11.9201 | 0 | 38.7597 | -120.5587
CWSP - EL DORADO 210219542 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210219542 | 0.0017374 | EL DORADO PH 210219542 | 0.013848 | Tier 3 | 6.71 | 0 | 0 | 0 | 0 | 6.71 | 38.7583 | -120.5864
CWSP - EL DORADO 210219542 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210219542 | 0.0017374 | EL DORADO PH 210219542 | 0.013848 | Tier 3 | 7.31 | 0 | 0 | 0 | 0 | 7.31 | 38.7563 | -120.5981
CWSP - EL DORADO 2102CB PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 2102CB | 0.00051722 | EL DORADO PH 2102CB | 0.0099516 | Tier 3 | 6.8875 | 0 | 0 | 0 | 0 | 6.8875 | 38.7932 | -120.6192
CWSP - EL DORADO PH 2101 19612 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210119612 | 0.0083743 | EL DORADO PH 210119612 | 0.0097168 | Tier 3 | 4.1 | 0 | 0 | 0 | 0 | 4.1 | 38.7619 | -120.5592
CWSP - EL DORADO PH 2101 19612 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210119612 | 0.0083743 | EL DORADO PH 210119612 | 0.0097168 | Tier 3 | 9.91 | 0 | 0 | 0 | 0 | 9.91 | 38.7632 | -120.5442
CWSP - EL DORADO PH 2101 LR 63464 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210163464 | 0.05356 | EL DORADO PH 210163464 | 0.0074889 | Tier 2 | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 38.7606 | -120.505
CWSP - EL DORADO PH 2101 LR 63464 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210163464 | 0.05356 | EL DORADO PH 210163464 | 0.0074889 | Tier 2 & 3 | 8.44 | 0 | 0 | 0 | 8.44 | 0 | 38.7688 | -120.4471
CWSP - EL DORADO PH 210119612 PH 1.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210119612 | 0.0083743 | EL DORADO PH 210119612 | 0.0097168 | Tier 3 | 2.64 | 0 | 0 | 0 | 2.64 | 0 | 38.7643 | -120.5577
CWSP - EL DORADO PH 210119612 PH 2.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210119612 | 0.0083743 | EL DORADO PH 210119612 | 0.0097168 | Tier 3 | 3.1201 | 0 | 0 | 0 | 3.1201 | 0 | 38.7616 | -120.5345
CWSP - EL DORADO PH 210119612 PH 2.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 210119612 | 0.0083743 | EL DORADO PH 210119612 | 0.0097168 | Tier 3 | 4.3201 | 0 | 0 | 0 | 0 | 4.3201 | 38.7583 | -120.5159
CWSP - EL DORADO PH 21016852 PH 3.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 21016852 | 0.0085289 | EL DORADO PH 21016852 | 0.0042306 | Tier 3 | 6.2201 | 0 | 0 | 0 | 0 | 6.2201 | 38.7594 | -120.5587
CWSP - EL DORADO PH 21016852 PH 4.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 21016852 | 0.0085289 | EL DORADO PH 21016852 | 0.0042306 | Tier 3 | 6.2701 | 0 | 0 | 0 | 0 | 6.2701 | 38.7585 | -120.5585
CWSP - ELECTRA 1101 LR7104 PH 1.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | ELECTRA 11017104 | 0.025302 | ELECTRA 11017104 | 0.020861 | Tier 2 | 4.85 | 0 | 0 | 0 | 0 | 4.85 | 38.4053 | -120.6461
CWSP - ELECTRA 1101 LR7104 PH 1.2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | ELECTRA 11017104 | 0.025302 | ELECTRA 11017104 | 0.020861 | Tier 2 | 4.47 | 0 | 0 | 0 | 0 | 4.47 | 38.395 | -120.645
CWSP - ELECTRA 11017104 PH2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | ELECTRA 11017104 | 0.025302 | ELECTRA 11017104 | 0.020861 | Tier 2 | 7.09 | 0 | 0 | 0 | 0 | 7.09 | 38.364 | -120.6467
CWSP - ELECTRA 1101L1697 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | ELECTRA 1101L1697 | 0.0030208 | ELECTRA 1101L1697 | 0.016781 | Tier 2 | 5.6701 | 0 | 0 | 0 | 5.6701 | 0 | 38.3794 | -120.6379
CWSP - FLINT 1101750 PH 1.1 | Base SH | 08W | ESTS | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | FLINT 1101750 | 0.28318 | FLINT 1101750 | 0.00097924 | Tier 2 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 38.8586 | -121.0805
CWSP - FORESTHILL 1101 1802 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 4.52 | 0 | 0 | 4.52 | 0 | 0 | 39.0163 | -120.835
CWSP - FORESTHILL 1101 1802 PH 1.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 3.952 | 0 | 0 | 3.952 | 0 | 0 | 39.01 | -120.8465
CWSP - FORESTHILL 1101 1802 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 2.84 | 0 | 0 | 0 | 0 | 2.84 | 39.0065 | -120.853
CWSP - FORESTHILL 1101 1802 PH 2.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 2.342 | 0 | 0 | 0 | 0 | 2.342 | 38.9997 | -120.8545
CWSP - FORESTHILL 1101 1802 PH 2.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Auburn | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 5.387 | 0 | 0 | 0 | 0 | 5.387 | 38.9768 | -121.1313
CWSP - FORESTHILL 11011802 PH 3.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 2.785 | 0 | 0 | 2.785 | 0 | 0 | 38.9828 | -120.8824
CWSP - FORESTHILL 11011802 PH 3.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 3.172 | 0 | 0 | 3.172 | 0 | 0 | 38.9898 | -120.8728
CWSP - FORESTHILL 11011802 PH 3.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11011802 | 0.012496 | FORESTHILL 11011802 | 0.013637 | Tier 3 | 2.55 | 0 | 0 | 2.55 | 0 | 0 | 38.9826 | -120.8755
CWSP - FORESTHILL 110137238 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110137238 | 0.031693 | FORESTHILL 110137238 | 0.0088134 | Tier 2 & 3 | 7.21 | 0 | 0 | 0 | 7.21 | 0 | 39.0473 | -120.7853
CWSP - FORESTHILL 110150486 - PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 2.04 | 0 | 0 | 2.04 | 0 | 0 | 39.0016 | -120.8905
CWSP - FORESTHILL 110150486 - PH 1.2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 2.32 | 0 | 0 | 2.32 | 0 | 0 | 38.9994 | -120.8896
CWSP - FORESTHILL 110150486 - PH 1.3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 3.01 | 0 | 0 | 3.01 | 0 | 0 | 38.9917 | -120.8912
CWSP - FORESTHILL 110150486 - PH 1.4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 2.97 | 0 | 0 | 2.97 | 0 | 0 | 38.9928 | -120.8828
CWSP - FORESTHILL 110150486 - PH 1.5 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 3.13 | 0 | 0 | 3.13 | 0 | 0 | 38.9913 | -120.8827
CWSP - FORESTHILL 110150486 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110150486 | 0.0037622 | FORESTHILL 110150486 | 0.01695 | Tier 3 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 38.9918 | -120.883
CWSP - Foresthill 1102 2106 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11022106 | 0.040196 | FORESTHILL 11022106 | 0.018495 | Tier 3 | 9.57 | 0 | 0 | 0 | 9.57 | 0 | 39.0198 | -120.8509
CWSP - Foresthill 1102 2106 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11022106 | 0.040196 | FORESTHILL 11022106 | 0.018495 | Tier 3 | 6.04 | 0 | 0 | 0 | 6.04 | 0 | 39.0198 | -120.8509
CWSP - Foresthill 1102 2106 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11022106 | 0.040196 | FORESTHILL 11022106 | 0.018495 | Tier 3 | 10.7 | 0 | 0 | 0 | 0 | 10.7 | 39.0198 | -120.8509
CWSP - Foresthill 1102 2106 PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 11022106 | 0.040196 | FORESTHILL 11022106 | 0.018495 | Tier 3 | 8.56 | 0 | 0 | 0 | 0 | 8.56 | 39.0198 | -120.8509
CWSP - GEYSERVILLE - 1101482 | Targeted UG | 3UG | UNSE | SO | Region 1 - North Coast | Geyserville | Sonoma | WDRM v3 | GEYSERVILLE 1101482 | 0.0056711 | GEYSERVILLE 1101482 | 0.0011879 | Tier 2 | 0.33996 | 0 | 0 | 0 | 0 | 0.33996 | 38.7005 | -122.9574
CWSP - HIGHLANDS 1102628 PH 1.2 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Clearlake | Lake | WDRM v2 | HIGHLANDS 1102628 | 0.5487 | HIGHLANDS 1102628 | 0.026126 | Tier 2 & 3 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 38.9822 | -122.6031
CWSP - HIGHLANDS 1102628 PH 1.3 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Clearlake | Lake | WDRM v2 | HIGHLANDS 1102628 | 0.5487 | HIGHLANDS 1102628 | 0.026126 | Tier 2 & 3 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 38.9822 | -122.6031
CWSP - HORSESHOE 1101 LR50140 PH 1.1 | Base SH | 08W | ESTS | SI | Region 2 - North East | Granite Bay | Placer | WDRM v2 | HORSESHOE 110150140 | 0.11734 | HORSESHOE 110150140 | 0.00028839 | Tier 2 | 0.83996 | 0 | 0.83996 | 0 | 0 | 0 | 38.782 | -121.1456
CWSP - HORSESHOE 1101 LR50140 PH 1.3 | Base SH | 08W | ESTS | SI | Region 2 - North East | Loomis | Placer | WDRM v2 | HORSESHOE 110150140 | 0.11734 | HORSESHOE 110150140 | 0.00028839 | Tier 2 | 0.17008 | 0 | 0.17008 | 0 | 0 | 0 | 38.7815 | -121.1632
CWSP - HORSESHOE 1101 LR50140 PH 1.4 | Base SH | 08W | ESTS | SI | Region 2 - North East | Loomis | Placer | WDRM v2 | HORSESHOE 110150140 | 0.11734 | HORSESHOE 110150140 | 0.00028839 | Tier 2 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 38.767 | -121.1634
CWSP - INDIAN FLAT 1104 CB & 4440 PH 1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | El Portal | Mariposa | WDRM v3 | INDIAN FLAT 1104CB | 0.14347 | INDIAN FLAT 1104CB | 0.039297 | Tier 2 | 9.808 | 0 | 0 | 0 | 0 | 9.808 | 37.6651 | -119.8416
CWSP - INDIAN FLAT 1104 CB & 4440 PH 2 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | El Portal | Mariposa | WDRM v3 | INDIAN FLAT 1104CB | 0.14347 | INDIAN FLAT 1104CB | 0.039297 | Tier 2 | 8.892 | 0 | 0 | 0 | 0 | 8.892 | 37.6771 | -119.7769
CWSP - JAMESON 1105 LR9472 PH 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 11059472 | 0.10731 | JAMESON 11059472 | 0.00057842 | Tier 2 | 0.020076 | 0 | 0.020076 | 0 | 0 | 0 | 38.2525 | -122.144
CWSP - JAMESON 1105 LR9472 PH 1.4 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 11059472 | 0.10731 | JAMESON 11059472 | 0.00057842 | Tier 2 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 38.2533 | -122.1356
CWSP - JESSUP 1102 LR1550 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 40.4517 | -122.3081
CWSP - JESSUP 1102 LR1550 PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 40.4409 | -122.3061
CWSP - JESSUP 1102 LR1550 PH 1.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 40.4416 | -122.3258
CWSP - JESSUP 1102 LR1550 PH 1.4 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 40.4406 | -122.3414
CWSP - JESSUP 1102 LR1550 PH 1.5 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 4.92 | 0 | 0 | 0 | 4.92 | 0 | 40.443 | -122.3663
CWSP - JESSUP 1102 LR1550 PH 2.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 40.4488 | -122.3179
CWSP - JESSUP 1102 LR1550 PH 2.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 40.4516 | -122.3245
CWSP - JESSUP 1102 LR1550 PH 2.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 40.4359 | -122.3689
CWSP - JESSUP 1102 LR1550 PH 2.4 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 40.4359 | -122.3689
CWSP - JESSUP 1102 LR1550 PH 2.5 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 40.4362 | -122.3535
CWSP - JESSUP 1102 LR1550 PH 3.1 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 40.4377 | -122.3878
CWSP - JESSUP 1102 LR1550 PH 3.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 40.4427 | -122.3927
CWSP - JESSUP 1102 LR1550 PH 3.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 40.4403 | -122.4075
CWSP - JESSUP 1102 LR1550 PH 3.4 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 11021550 | 0.18396 | JESSUP 11021550 | 0.00063997 | Tier 2 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 40.4493 | -122.4078
CWSP - KESWICK 1101 LR 1586 PH 1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | KESWICK 11011586 | 1.2524 | KESWICK 11011586 | 0.022602 | Tier 3 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 40.6253 | -122.4633
CWSP - KESWICK 1101 LR 1586 PH 1.4 | Base SH | 08W | PEND | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | KESWICK 11011586 | 1.2524 | KESWICK 11011586 | 0.022602 | Tier 3 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 40.6253 | -122.4633
CWSP - KIRKER 2104442850 PH 1.1 | Base SH | 08W | CONS | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | WDRM v2 | KIRKER 2104442850 | 0.61454 | KIRKER 2104442850 | 0.00471 | Tier 2 | 1.8303 | 1.8019 | 0.028409 | 0 | 0 | 0 | 37.9907 | -121.896
CWSP - LINCOLN 1104 LR685276 PH 1.1 | Base SH | 08W | ADER | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 1104685276 | 0.24208 | LINCOLN 1104685276 | 5.2842e-05 | Tier 2 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 39.0041 | -121.2605
CWSP - LINCOLN 1104 LR685276 PH 1.5 | Base SH | 08W | ADER | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 1104685276 | 0.24208 | LINCOLN 1104685276 | 5.2842e-05 | Tier 2 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 38.9873 | -121.2542
CWSP - LOS COCHES 1101625902 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Soledad | Monterey | WDRM v3 | LOS COCHES 1101625902 | 0.0089147 | LOS COCHES 1101625902 | 0.0060529 | Tier 2 | 2.4 | 0 | 0 | 0 | 2.4 | 0 | 36.3482 | -121.322
CWSP - LOS OSITOS 21033010 PH 1 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21033010 | 0.027281 | LOS OSITOS 21033010 | 0.013726 | Tier 2 | 8.9799 | 0 | 0 | 0 | 8.9799 | 0 | 36.2799 | -121.3079
CWSP - LOS OSITOS 21033010 PH 2 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21033010 | 0.027281 | LOS OSITOS 21033010 | 0.013726 | Tier 2 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 36.2609 | -121.3708
CWSP - LOS OSITOS 21033010 PH 3 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21033010 | 0.027281 | LOS OSITOS 21033010 | 0.013726 | Tier 2 | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 36.2618 | -121.4162
CWSP - LOS OSITOS 21033010 PH 4 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21033010 | 0.027281 | LOS OSITOS 21033010 | 0.013726 | Tier 2 | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 36.2703 | -121.439
CWSP - LOS OSITOS 21033010 PH 5 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21033010 | 0.027281 | LOS OSITOS 21033010 | 0.013726 | Tier 2 | 7.9701 | 0 | 0 | 7.9701 | 0 | 0 | 36.2698 | -121.4424
CWSP - LOS OSITOS 21037014 PH 1 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Paicines | San Benito | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 0.012994 | HFRA | 12.71 | 0 | 0 | 12.71 | 0 | 0 | 36.3874 | -121.0046
CWSP - LOS OSITOS 21037014 PH 2 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Paicines | San Benito | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 0.012994 | HFRA | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 36.4052 | -120.9534
CWSP - LOS OSITOS 21037014 PH 3 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Paicines | San Benito | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 0.012994 | HFRA | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 36.3871 | -120.9253
CWSP - LOS OSITOS 21037014 PH 4 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Paicines | San Benito | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 0.012994 | HFRA | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 36.3616 | -120.8504
CWSP - LOS OSITOS 21037014 PH 5 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Paicines | San Benito | WDRM v3 | N/A | N/A | LOS OSITOS 21037014 | 0.012994 | HFRA | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 36.34 | -120.7484
CWSP - LOS OSITOS 21037062 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21037062 | 0.035805 | LOS OSITOS 21037062 | 0.0052285 | Tier 2 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 36.2791 | -121.3034
CWSP - LOS OSITOS 21037062 PH 2 | Targeted UG | 3UG | UNSE | CC | Region 4 - Central Coast | Greenfield | Monterey | WDRM v3 | LOS OSITOS 21037062 | 0.035805 | LOS OSITOS 21037062 | 0.0052285 | Tier 2 | 7.6799 | 0 | 0 | 0 | 0 | 7.6799 | 36.2786 | -121.3033
CWSP - MARIPOSA 210110070 PH 1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110070 | 0.2644 | MARIPOSA 210110070 | 0.0051015 | Tier 2 | 5.51 | 0 | 0 | 0 | 5.51 | 0 | 37.508 | -119.9962
CWSP - MARIPOSA 2101752630 PH 1.1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 5.28 | 0 | 0 | 0 | 5.28 | 0 | 37.5641 | -119.9403
CWSP - MARIPOSA 2101752630 PH 1.2 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 4.39 | 0 | 0 | 0 | 4.39 | 0 | 37.5685 | -119.9677
CWSP - MARIPOSA 2101752630 PH 1.3 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 3.81 | 0 | 0 | 0 | 3.81 | 0 | 37.5677 | -119.9692
CWSP - MARIPOSA 2101752630 PH 2.1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 5.24 | 0 | 0 | 0 | 0 | 5.24 | 37.5664 | -119.9692
CWSP - MARIPOSA 2101752630 PH 2.2 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 4.31 | 0 | 0 | 0 | 0 | 4.31 | 37.5736 | -119.9769
CWSP - MARIPOSA 2101752630 PH 2.3 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 2101752630 | 0.11205 | MARIPOSA 2101752630 | 0.012689 | Tier 2 | 3.13 | 0 | 0 | 0 | 0 | 3.13 | 37.5728 | -119.9924
CWSP - MARIPOSA 2102440236 PH1.4 | Base SH | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v2 | MARIPOSA 2102440236 | 0.4205 | MARIPOSA 2102440236 | 0.0069412 | Tier 2 & 3 | 0.13258 | 0 | 0.13258 | 0 | 0 | 0 | 37.4632 | -119.9483
CWSP - MIDDLETOWN 11011314 PH1 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 11011314 | 0.078235 | MIDDLETOWN 11011314 | 0.021686 | Tier 2 & 3 | 1.2 | 0 | 0 | 0 | 0 | 1.2 | 38.7313 | -122.6233
CWSP - MIDDLETOWN 1101171414 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Kelseyville | Lake | WDRM v3 | MIDDLETOWN 11014646 | 0.19983 | MIDDLETOWN 1101171414 | 0.024501 | Tier 3 | 3.9701 | 0 | 0 | 0 | 0 | 3.9701 | 38.8481 | -122.7562
CWSP - MIDDLETOWN 1101433160 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 1101644756 | 0.20636 | MIDDLETOWN 1101433160 | 0.018456 | Tier 2 & 3 | 1.4 | 0 | 0 | 0 | 0 | 1.4 | 38.7253 | -122.6191
CWSP - MIDDLETOWN 11014646 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 11014646 | 0.19983 | MIDDLETOWN 11014646 | 0.013549 | Tier 3 | 7.19 | 0 | 0 | 0 | 7.19 | 0 | 38.829 | -122.7294
CWSP - MIDDLETOWN 11014646 -PH 2 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 11014646 | 0.19983 | MIDDLETOWN 11014646 | 0.013549 | Tier 3 | 8.84 | 0 | 0 | 0 | 8.84 | 0 | 38.8292 | -122.7295
CWSP - MIDDLETOWN 11014646 -PH 3 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 11014646 | 0.19983 | MIDDLETOWN 11014646 | 0.013549 | Tier 3 | 10.89 | 0 | 0 | 0 | 0 | 10.89 | 38.8296 | -122.7299
CWSP - MIDDLETOWN 11014646 -PH 4 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v3 | MIDDLETOWN 11014646 | 0.19983 | MIDDLETOWN 11014646 | 0.013549 | Tier 3 | 4.46 | 0 | 0 | 0 | 0 | 4.46 | 38.8301 | -122.73
CWSP - MIDDLETOWN 1101614 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Kelseyville | Lake | WDRM v3 | MIDDLETOWN 1101614 | 0.0076984 | MIDDLETOWN 1101614 | 0.01209 | Tier 3 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299 | 38.8267 | -122.7271
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1102302610 | 0.91632 | MIDDLETOWN 1102302610 | 0.007089 | Tier 2 | 1.3201 | 0 | 0 | 1.3201 | 0 | 0 | 38.7573 | -122.606
CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1103830 | 0.71618 | MIDDLETOWN 1103830 | 0.006302 | Tier 2 & 3 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 38.7569 | -122.607
CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1103830 | 0.71618 | MIDDLETOWN 1103830 | 0.006302 | Tier 2 & 3 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 38.7564 | -122.6056
CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1103830 | 0.71618 | MIDDLETOWN 1103830 | 0.006302 | Tier 2 & 3 | 1.3212 | 0.36136 | 0.95985 | 0 | 0 | 0 | 38.7564 | -122.6056
CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | Base SH | 08W | ESTS | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 0.38665 | MOUNTAIN QUARRIES 2101CB | 0.017565 | Tier 2 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 38.9141 | -121.0189
CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | Base SH | 08W | UNSC | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 0.38665 | MOUNTAIN QUARRIES 2101CB | 0.017565 | Tier 2 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 38.8775 | -120.993
CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | Base SH | 08W | PEND | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 0.38665 | MOUNTAIN QUARRIES 2101CB | 0.017565 | Tier 2 | 0.52576 | 0 | 0.52576 | 0 | 0 | 0 | 38.8641 | -120.9817
CWSP - NARROWS 2102CB | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Smartsville | Nevada | WDRM v3 | NARROWS 2102CB | 0.11807 | NARROWS 2102CB | 0.022999 | Tier 2 | 7.2799 | 0 | 0 | 0 | 0 | 7.2799 | 39.2362 | -121.2665
CWSP - NOTRE DAME 1104176446 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | NOTRE DAME 11042408 | 0.37815 | NOTRE DAME 1104176446 | 0.015172 | Tier 2 & 3 | 10.6299 | 0 | 0 | 0 | 10.6299 | 0 | 39.7783 | -121.7319
CWSP - NOTRE DAME 11042028 PH 1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | NOTRE DAME 11042028 | 0.062015 | NOTRE DAME 11042028 | 0.024521 | Tier 3 | 8.04 | 0 | 0 | 0 | 0 | 8.04 | 39.8389 | -121.702
CWSP - NOTRE DAME 11042028 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | NOTRE DAME 11042028 | 0.062015 | NOTRE DAME 11042028 | 0.024521 | Tier 3 | 4.6701 | 0 | 0 | 0 | 0 | 4.6701 | 39.839 | -121.7019
CWSP - NOTRE DAME 11042537 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | NOTRE DAME 11042537 | 0.061762 | NOTRE DAME 11042537 | 0.0096296 | Tier 2 & 3 | 6.1 | 0 | 0 | 0 | 0 | 6.1 | 39.7911 | -121.7218
CWSP - OREGON TRAIL 11021584 PH 1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Shasta Lake | Shasta | WDRM v3 | OREGON TRAIL 11021584 | 0.015387 | OREGON TRAIL 11021584 | 0.0208 | Tier 2 | 5.1 | 0 | 0 | 0 | 0 | 5.1 | 40.6654 | -122.3865
CWSP - OREGON TRAIL 11021584 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Shasta Lake | Shasta | WDRM v3 | OREGON TRAIL 11021584 | 0.015387 | OREGON TRAIL 11021584 | 0.0208 | Tier 2 | 9.7 | 0 | 0 | 0 | 0 | 9.7 | 40.665 | -122.3871
CWSP - OREGON TRAIL 110335002 PH1.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | OREGON TRAIL 110335002 | 0.42185 | OREGON TRAIL 110335002 | 0.00034131 | Tier 2 | 6.7973 | 0 | 0 | 6.7973 | 0 | 0 | 40.6242 | -122.3039
CWSP - OREGON TRAIL 110335002 PH1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | OREGON TRAIL 110335002 | 0.42185 | OREGON TRAIL 110335002 | 0.00034131 | Tier 2 | 4.6722 | 0 | 0 | 4.6722 | 0 | 0 | 40.6242 | -122.3039
CWSP - OREGON TRAIL 110335002 PH1.5 | Base SH | 08W | PEND | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | OREGON TRAIL 110335002 | 0.42185 | OREGON TRAIL 110335002 | 0.00034131 | Tier 2 | 4.5701 | 0 | 0 | 4.5701 | 0 | 0 | 40.6242 | -122.3039
CWSP - OREGON TRAIL 110335002 PH1.7 | Base SH | 08W | ESTS | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | OREGON TRAIL 110335002 | 0.42185 | OREGON TRAIL 110335002 | 0.00034131 | Tier 2 | 0.20152 | 0 | 0 | 0.20152 | 0 | 0 | 40.624 | -122.3049
CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Base SH | 08W | CONS | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | OREGON TRAIL 110335002 | 0.42185 | OREGON TRAIL 110335002 | 0.00034131 | Tier 2 | 0.55985 | 0 | 0 | 0.55985 | 0 | 0 | 40.6242 | -122.3039
CWSP - ORO FINO 11012022 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 11012022 | 0.0024209 | ORO FINO 11012022 | 0.003959 | Tier 3 | 4.54 | 0 | 0 | 0 | 0 | 4.54 | 39.8541 | -121.6059
CWSP - ORO FINO 11012022 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 11012022 | 0.0024209 | ORO FINO 11012022 | 0.003959 | Tier 3 | 5.76 | 0 | 0 | 0 | 0 | 5.76 | 39.8536 | -121.6057
CWSP - ORO FINO 11012022 PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 11012022 | 0.0024209 | ORO FINO 11012022 | 0.003959 | Tier 3 | 8.5 | 0 | 0 | 0 | 0 | 8.5 | 39.8531 | -121.6056
CWSP - ORO FINO 1101CB | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1101CB | 0.0035789 | ORO FINO 1101CB | 0.015008 | Tier 3 | 7.75 | 0 | 0 | 0 | 7.75 | 0 | 39.8717 | -121.6106
CWSP - ORO FINO 1101CB PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1101CB | 0.0035789 | ORO FINO 1101CB | 0.015008 | Tier 3 | 5.5701 | 0 | 0 | 0 | 5.5701 | 0 | 39.8701 | -121.6102
CWSP - ORO FINO 1101CB PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1101CB | 0.0035789 | ORO FINO 1101CB | 0.015008 | Tier 3 | 6.04 | 0 | 0 | 0 | 0 | 6.04 | 39.8695 | -121.6115
CWSP - ORO FINO 11022090 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1102CB | 0.0021922 | ORO FINO 1102CB | 0.031702 | Tier 3 | 5.94 | 0 | 0 | 0 | 0 | 5.94 | 39.8583 | -121.6133
CWSP - ORO FINO 11022090 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1102CB | 0.0021922 | ORO FINO 1102CB | 0.031702 | Tier 3 | 10.2299 | 0 | 0 | 0 | 0 | 10.2299 | 39.8576 | -121.6133
CWSP - ORO FINO 11022090 PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1102CB | 0.0021922 | ORO FINO 1102CB | 0.031702 | Tier 3 | 4.4299 | 0 | 0 | 0 | 0 | 4.4299 | 39.8569 | -121.6134
CWSP - ORO FINO 110239154 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 3 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 39.887 | -121.6654
CWSP - ORO FINO 110239154 PH 4 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 2 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 39.8864 | -121.6657
CWSP - ORO FINO 110239154 PH 6 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 2 | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 39.8847 | -121.6661
CWSP - ORO FINO 110276008 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110276008 | 0.000401 | ORO FINO 110276008 | 0.020869 | Tier 3 | 9.35 | 0 | 0 | 0 | 0 | 9.35 | 39.8877 | -121.6655
CWSP - ORO FINO 110276008 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110276008 | 0.000401 | ORO FINO 110276008 | 0.020869 | Tier 3 | 8.7299 | 0 | 0 | 0 | 0 | 8.7299 | 39.8877 | -121.666
CWSP - ORO FINO 1102CB | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Magalia | Butte | WDRM v3 | ORO FINO 1102CB | 0.0021922 | ORO FINO 1102CB | 0.031702 | Tier 3 | 3.04 | 0 | 0 | 0 | 0 | 3.04 | 39.8718 | -121.6107
CWSP - PIKE CITY 11011720 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camptonville | Yuba | WDRM v3 | PIKE CITY 11011720 | 0.017864 | PIKE CITY 11011720 | 0.02211 | Tier 3 | 6.9201 | 0 | 0 | 0 | 6.9201 | 0 | 39.4556 | -121.0536
CWSP - PIKE CITY 11011730 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camptonville | Yuba | WDRM v3 | PIKE CITY 11011730 | 0.033438 | PIKE CITY 11011730 | 0.0093855 | Tier 3 | 10.5875 | 0 | 0 | 0 | 10.5875 | 0 | 39.452 | -121.0541
CWSP - PIKE CITY 11011730 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | North San Juan | Yuba | WDRM v3 | PIKE CITY 11011730 | 0.033438 | PIKE CITY 11011730 | 0.0093855 | Tier 3 | 6.74 | 0 | 0 | 0 | 0 | 6.74 | 39.4332 | -121.0753
CWSP - PIKE CITY 1101CB PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | North San Juan | Sierra | WDRM v3 | PIKE CITY 1101CB | 0.029034 | PIKE CITY 1101CB | 0.016874 | Tier 3 | 10.85 | 0 | 0 | 0 | 0 | 10.85 | 39.4388 | -120.9968
CWSP - PIKE CITY 1101CB PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camptonville | Yuba | WDRM v3 | PIKE CITY 1101CB | 0.029034 | PIKE CITY 1101CB | 0.016874 | Tier 3 | 10.66 | 0 | 0 | 0 | 0 | 10.66 | 39.4528 | -121.0297
CWSP - PIKE CITY 1101CB PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Camptonville | Yuba | WDRM v3 | PIKE CITY 1101CB | 0.029034 | PIKE CITY 1101CB | 0.016874 | Tier 3 | 6.9701 | 0 | 0 | 0 | 0 | 6.9701 | 39.454 | -121.0327
CWSP - PINE GROVE 11013166 PH 1.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 11013166 | 0.015763 | PINE GROVE 11013166 | 0.015597 | Tier 2 | 7.4299 | 0 | 0 | 0 | 0 | 7.4299 | 38.4069 | -120.6707
CWSP - PINE GROVE 11013166 PH 1.2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 11013166 | 0.015763 | PINE GROVE 11013166 | 0.015597 | Tier 2 | 2.4561 | 0 | 0 | 0 | 0 | 2.4561 | 38.4069 | -120.6707
CWSP - PINE GROVE 11013166 PH 2.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 11013166 | 0.015763 | PINE GROVE 11013166 | 0.015597 | Tier 2 | 7.3299 | 0 | 0 | 0 | 7.3299 | 0 | 38.4067 | -120.6708
CWSP - PINE GROVE 11013166 PH 2.2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 11013166 | 0.015763 | PINE GROVE 11013166 | 0.015597 | Tier 2 | 4.64 | 0 | 0 | 0 | 0 | 4.64 | 38.4067 | -120.6708
CWSP - PINE GROVE 1101CB | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 1101CB | 0.0031502 | PINE GROVE 1101CB | 0.047261 | Tier 2 | 2.84 | 0 | 0 | 0 | 0 | 2.84 | 38.4129 | -120.6605
CWSP - PINE GROVE 1101CB PH 1.2 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 1101CB | 0.0031502 | PINE GROVE 1101CB | 0.047261 | Tier 2 | 2.91 | 0 | 0 | 0 | 0 | 2.91 | 38.4129 | -120.6605
CWSP - PINE GROVE 1101CB PH 1.3 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Pine Grove | Amador | WDRM v3 | PINE GROVE 1101CB | 0.0031502 | PINE GROVE 1101CB | 0.047261 | Tier 2 | 0.88 | 0 | 0 | 0 | 0 | 0.88 | 38.4129 | -120.6605
CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Base SH | 08W | CONS | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v2 | PINE GROVE 11021222 | 0.0037571 | PINE GROVE 11021222 | 0.0048336 | Tier 3 | 0.093561 | 0.04072 | 0.052841 | 0 | 0 | 0 | 38.436 | -120.5559
CWSP - PINE GROVE 110213438 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 110213438 | 0.0063999 | PINE GROVE 110213438 | 0.012447 | Tier 2 & 3 | 9 | 0 | 0 | 9 | 0 | 0 | 38.4738 | -120.6267
CWSP - PINE GROVE 110213438 PH 1.2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 110213438 | 0.0063999 | PINE GROVE 110213438 | 0.012447 | Tier 2 & 3 | 4.914 | 0 | 0 | 4.914 | 0 | 0 | 38.4738 | -120.6267
CWSP - PINE GROVE 110213438 PH 2.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 110213438 | 0.0063999 | PINE GROVE 110213438 | 0.012447 | Tier 2 & 3 | 4.888 | 0 | 0 | 4.888 | 0 | 0 | 38.4858 | -120.6021
CWSP - PINE GROVE 110213438 PH 2.2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 110213438 | 0.0063999 | PINE GROVE 110213438 | 0.012447 | Tier 2 & 3 | 6.192 | 0 | 0 | 0 | 6.192 | 0 | 38.489 | -120.5889
CWSP - PINE GROVE 110245292 PH 1.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | PINE GROVE 110245292 | 0.002235 | PINE GROVE 110245292 | 0.011408 | Tier 2 & 3 | 12.7701 | 0 | 0 | 0 | 12.7701 | 0 | 38.4536 | -120.5299
CWSP - PINE GROVE 110245292 PH 1.3 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | PINE GROVE 110245292 | 0.002235 | PINE GROVE 110245292 | 0.011408 | Tier 3 | 3.64 | 0 | 0 | 0 | 3.64 | 0 | 38.4536 | -120.5299
CWSP - PINE GROVE 110245292 PH 1.4 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | PINE GROVE 110245292 | 0.002235 | PINE GROVE 110245292 | 0.011408 | Tier 3 | 3.3701 | 0 | 0 | 0 | 0 | 3.3701 | 38.4536 | -120.5299
CWSP - PINE GROVE 110245292 PH 1.5 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | PINE GROVE 110245292 | 0.002235 | PINE GROVE 110245292 | 0.011408 | Tier 3 | 0.92992 | 0 | 0 | 0 | 0 | 0.92992 | 38.4536 | -120.5299
CWSP - PINE GROVE 11026080 PH 3 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 11026080 | 0.042249 | PINE GROVE 11026080 | 0.016072 | Tier 2 | 8.65 | 0 | 0 | 8.65 | 0 | 0 | 38.4612 | -120.6579
CWSP - PINE GROVE 11026080 PH 4 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Volcano | Amador | WDRM v3 | PINE GROVE 11026080 | 0.042249 | PINE GROVE 11026080 | 0.016072 | Tier 2 | 6.96 | 0 | 0 | 6.96 | 0 | 0 | 38.4612 | -120.6579
CWSP - PLACERVILLE 210611132 PH 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 2 & 3 | 10.7201 | 0 | 0 | 10.7201 | 0 | 0 | 38.7716 | -120.8149
CWSP - PLACERVILLE 210611132 PH 2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 2 & 3 | 10.0799 | 0 | 0 | 10.0799 | 0 | 0 | 38.7794 | -120.8161
CWSP - PLACERVILLE 210611132 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 2 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0 | 38.7837 | -120.8168
CWSP - PLACERVILLE 210611132 PH 4 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 3 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0 | 38.7978 | -120.8203
CWSP - PLACERVILLE 210611132 PH 5 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 3 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799 | 38.8089 | -120.8175
CWSP - PLACERVILLE 210611132 PH 6 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 210611132 | 0.020262 | PLACERVILLE 210611132 | 0.020612 | Tier 3 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799 | 38.811 | -120.8055
CWSP - PLACERVILLE 2106935216 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 2106935216 | 0.079474 | PLACERVILLE 2106935216 | 0.021398 | Tier 3 | 4.9 | 0 | 0 | 0 | 4.9 | 0 | 38.7571 | -120.7681
CWSP - PLACERVILLE 2106935216 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 2106935216 | 0.079474 | PLACERVILLE 2106935216 | 0.021398 | Tier 3 | 8.65 | 0 | 0 | 0 | 8.65 | 0 | 38.7571 | -120.7681
CWSP - PLACERVILLE 2106935216 PH 3 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v3 | PLACERVILLE 2106935216 | 0.079474 | PLACERVILLE 2106935216 | 0.021398 | Tier 3 | 8.65 | 0 | 0 | 0 | 0 | 8.65 | 38.7571 | -120.7681
CWSP - PUEBLO 2103678 PH 1.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 2 | 2.27 | 0 | 0 | 0 | 2.27 | 0 | 38.3155 | -122.342
CWSP - PUEBLO 2103678 PH 1.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 2 & 3 | 4.9 | 0 | 0 | 0 | 4.9 | 0 | 38.3284 | -122.3536
CWSP - PUEBLO 2103678 PH 1.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.59 | 0 | 0 | 0 | 1.59 | 0 | 38.3337 | -122.3742
CWSP - PUEBLO 2103678 PH 1.4 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.76 | 0 | 0 | 0 | 1.76 | 0 | 38.3365 | -122.3839
CWSP - PUEBLO 2103678 PH 1.5 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0 | 38.3391 | -122.3909
CWSP - PUEBLO 2103678 PH 1.6 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 2 & 3 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 | 38.3326 | -122.398
CWSP - PUEBLO 2103678 PH 2.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 0.616 | 0 | 0 | 0.616 | 0 | 0 | 38.3338 | -122.3727
CWSP - PUEBLO 2103678 PH 2.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 3.618 | 0 | 0 | 3.618 | 0 | 0 | 38.3395 | -122.3757
CWSP - PUEBLO 2103678 PH 2.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.619 | 0 | 0 | 1.619 | 0 | 0 | 38.3512 | -122.3815
CWSP - PUEBLO 2103678 PH 2.4 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 0.703 | 0 | 0 | 0.703 | 0 | 0 | 38.3624 | -122.4047
CWSP - PUEBLO 2103678 PH 2.5 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 2.965 | 0 | 0 | 2.965 | 0 | 0 | 38.3471 | -122.3949
CWSP - PUEBLO 2103678 PH 2.6 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 2.705 | 0 | 0 | 2.705 | 0 | 0 | 38.363 | -122.4052
CWSP - PUEBLO 2103678 PH 3.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.87 | 0 | 0 | 0 | 1.87 | 0 | 38.3704 | -122.4132
CWSP - PUEBLO 2103678 PH 3.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.725 | 0 | 0 | 0 | 1.725 | 0 | 38.3753 | -122.4221
CWSP - PUEBLO 2103678 PH 3.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 4.262 | 0 | 0 | 0 | 4.262 | 0 | 38.3723 | -122.4178
CWSP - PUEBLO 2103678 PH 3.4 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.74 | 0 | 0 | 0 | 1.74 | 0 | 38.3757 | -122.4227
CWSP - PUEBLO 2103678 PH 3.5 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.418 | 0 | 0 | 0 | 1.418 | 0 | 38.382 | -122.4321
CWSP - PUEBLO 2103678 PH 3.6 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 2.575 | 0 | 0 | 0 | 2.575 | 0 | 38.3857 | -122.4324
CWSP - PUEBLO 2103678 PH 3.7 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.957 | 0 | 0 | 0 | 1.957 | 0 | 38.3905 | -122.438
CWSP - PUEBLO 2103678 PH 3.8 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 0.848 | 0 | 0 | 0 | 0.848 | 0 | 38.3909 | -122.4387
CWSP - PUEBLO 2103678 PH 3.9 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 0.481 | 0 | 0 | 0 | 0.481 | 0 | 38.393 | -122.4421
CWSP - PUEBLO 2103678 PH 4.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 38.3419 | -122.3942
CWSP - PUEBLO 2103678 PH 4.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 2.222 | 0 | 0 | 2.222 | 0 | 0 | 38.3441 | -122.41
CWSP - PUEBLO 2103678 PH 4.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Napa | Napa | WDRM v3 | PUEBLO 2103678 | 0.046077 | PUEBLO 2103678 | 0.010549 | Tier 3 | 1.161 | 0 | 0 | 1.161 | 0 | 0 | 38.3465 | -122.4193
CWSP - REDBUD 1101 LR323962 PH1.1 | Base SH | 08W | ADER | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 3 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 39.0662 | -122.6111
CWSP - REDBUD 1101 LR323962 PH1.2 | Base SH | 08W | ADER | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 3 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 39.0688 | -122.6043
CWSP - REDBUD 1101 LR323962 PH1.3 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 3 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 39.0823 | -122.6045
CWSP - REDBUD 1101 LR454 PH 1.1 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101454 | 0.20738 | REDBUD 1101454 | 0.023647 | Tier 3 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 39.0837 | -122.66
CWSP - REDBUD 1101 LR454 PH 1.2 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101454 | 0.20738 | REDBUD 1101454 | 0.023647 | Tier 3 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 39.0748 | -122.6503
CWSP - REDBUD 1101 LR454 PH 1.3 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101454 | 0.20738 | REDBUD 1101454 | 0.023647 | Tier 3 | 4.761 | 0 | 0 | 4.761 | 0 | 0 | 39.0654 | -122.6333
CWSP - REDBUD 1101323962 PH 2.1 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 39.0662 | -122.6111
CWSP - REDBUD 1101323962 PH 2.2 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 39.0287 | -122.5858
CWSP - REDBUD 1101323962 PH 2.3 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 5.26 | 0 | 0 | 5.26 | 0 | 0 | 39.0448 | -122.5887
CWSP - REDBUD 1101323962 PH 2.4 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 39.0669 | -122.5993
CWSP - REDBUD 1101323962 PH 2.5 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 39.0696 | -122.585
CWSP - REDBUD 1101323962 PH 2.6 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101323962 | 0.17389 | REDBUD 1101323962 | 0.016255 | Tier 2 & 3 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 39.0506 | -122.5833
CWSP - SALT SPRINGS 210297924 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | SALT SPRINGS 210297924 | 0.0010653 | SALT SPRINGS 210297924 | 0.016045 | Tier 3 | 6.6799 | 0 | 0 | 0 | 0 | 6.6799 | 38.323 | -120.2535
CWSP - SHADY GLEN 110132726 PH 1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | COLFAX | Placer | WDRM v3 | SHADY GLEN 110132726 | 0.00506 | SHADY GLEN 110132726 | 0.02023 | Tier 2 | 15.2 | 0 | 0 | 0 | 0 | 15.2 | 39.1011 | -120.9596
CWSP - SHADY GLEN 110132726 PH 2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | COLFAX | Placer | WDRM v3 | SHADY GLEN 110132726 | 0.00506 | SHADY GLEN 110132726 | 0.02023 | Tier 2 | 3.3 | 0 | 0 | 3.3 | 0 | 0 | 39.101 | -120.9597
CWSP - SHADY GLEN 110248894 PH1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | COLFAX | Placer | WDRM v3 | SHADY GLEN 110248894 | 0.034658 | SHADY GLEN 110248894 | 0.018876 | Tier 3 | 6.601 | 0 | 0 | 0 | 0 | 6.601 | 39.1191 | -120.9513
CWSP - SHADY GLEN 110248894 PH2 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | COLFAX | Placer | WDRM v3 | SHADY GLEN 110248894 | 0.034658 | SHADY GLEN 110248894 | 0.018876 | Tier 3 | 6.062 | 0 | 0 | 0 | 6.062 | 0 | 39.1191 | -120.9513
CWSP - SILVERADO 2104 LR 515946 PH 1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | DEER PARK | Napa | WDRM v3 | SILVERADO 210437632 | 0.044601 | SILVERADO 2104515946 | 0.025445 | Tier 3 | 10.74 | 0 | 0 | 0 | 0 | 10.74 | 38.5447 | -122.4782
CWSP - SILVERADO 2104 LR 515946 PH 2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | DEER PARK | Napa | WDRM v3 | SILVERADO 210437632 | 0.044601 | SILVERADO 2104515946 | 0.025445 | Tier 3 | 6.69 | 0 | 0 | 0 | 0 | 6.69 | 38.5447 | -122.4782
CWSP - SILVERADO 2104 LR 632 PH 1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 2104632 | 0.094959 | SILVERADO 2104632 | 0.021383 | Tier 3 | 11.29 | 0 | 0 | 0 | 11.29 | 0 | 38.5742 | -122.4441
CWSP - SILVERADO 2104 LR 632 PH 2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 2104632 | 0.094959 | SILVERADO 2104632 | 0.021383 | Tier 3 | 11.29 | 0 | 0 | 0 | 0 | 11.29 | 38.5742 | -122.4441
CWSP - SILVERADO 2104646776 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210437632 | 0.044601 | SILVERADO 2104646776 | 0.034265 | Tier 3 | 4.4 | 0 | 0 | 0 | 0 | 4.4 | 38.5754 | -122.4443
CWSP - SILVERADO 210478268 PH 1.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 1.358 | 0 | 0 | 0 | 1.358 | 0 | 38.5613 | -122.4612
CWSP - SILVERADO 210478268 PH 1.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 1.632 | 0 | 0 | 1.632 | 0 | 0 | 38.5575 | -122.452
CWSP - SILVERADO 210478268 PH 1.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 2.029 | 0 | 0 | 2.029 | 0 | 0 | 38.5578 | -122.4566
CWSP - SILVERADO 210478268 PH 1.4 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 2.096 | 0 | 0 | 0 | 2.096 | 0 | 38.5587 | -122.4577
CWSP - SILVERADO 210478268 PH 1.5 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 0.862 | 0 | 0 | 0 | 0.862 | 0 | 38.5582 | -122.4502
CWSP - SILVERADO 210478268 PH 1.6 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 1.113 | 0 | 0 | 0 | 1.113 | 0 | 38.5532 | -122.4564
CWSP - SILVERADO 210478268 PH 2.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 3.648 | 0 | 0 | 3.648 | 0 | 0 | 38.5653 | -122.4415
CWSP - SILVERADO 210478268 PH 2.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Angwin | Napa | WDRM v3 | SILVERADO 210478268 | 0.043133 | SILVERADO 210478268 | 0.018153 | Tier 3 | 3.88 | 0 | 0 | 3.88 | 0 | 0 | 38.5572 | -122.4315
CWSP - SILVERADO 2105658898 PH 1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105658898 | 0.035763 | SILVERADO 2105658898 | 0.018978 | Tier 3 | 10.25 | 0 | 0 | 0 | 0 | 10.25 | 38.5071 | -122.4907
CWSP - SILVERADO 2105658898 PH 2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105658898 | 0.035763 | SILVERADO 2105658898 | 0.018978 | Tier 3 | 1.21 | 0 | 0 | 0 | 0 | 1.21 | 38.5201 | -122.5433
CWSP - SILVERADO 2105900104 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | DEER PARK | Napa | WDRM v3 | SILVERADO 2105616 | 0.0030112 | SILVERADO 2105900104 | 0.018786 | Tier 3 | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 38.5431 | -122.4978
CWSP - STANISLAUS 1701 CB PH1.2 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Murphys | Calaveras | WDRM v2 | STANISLAUS 1701CB | 0.40353 | STANISLAUS 1701CB | 0.018647 | Tier 2 & 3 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 38.1735 | -120.3833
CWSP - STANISLAUS 1701 CB PH1.3 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Murphys | Calaveras | WDRM v2 | STANISLAUS 1701CB | 0.40353 | STANISLAUS 1701CB | 0.018647 | Tier 2 & 3 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 38.1831 | -120.3755
CWSP - STANISLAUS 1701 CB PH1.6 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Murphys | Calaveras | WDRM v2 | STANISLAUS 1701CB | 0.40353 | STANISLAUS 1701CB | 0.018647 | Tier 2 & 3 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 38.1735 | -120.3833
CWSP - STANISLAUS 170179826 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | WDRM v3 | STANISLAUS 170179826 | 0.0062159 | STANISLAUS 170179826 | 0.011425 | Tier 2 | 12.675 | 0 | 0 | 12.675 | 0 | 0 | 38.1699 | -120.4067
CWSP - STANISLAUS 1702 LR1888 PH 2 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 5.517 | 0 | 0 | 5.517 | 0 | 0 | 38.2364 | -120.3626
CWSP - STANISLAUS 1702 LR1888 PH1.1 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 38.2367 | -120.3629
CWSP - STANISLAUS 1702 LR1888 PH1.2 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 38.2367 | -120.3629
CWSP - STANISLAUS 1702 LR1888 PH1.3 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 2.453 | 0 | 0 | 2.453 | 0 | 0 | 38.2367 | -120.3629
CWSP - STANISLAUS 1702 LR1888 PH1.4 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 38.2367 | -120.3629
CWSP - STANISLAUS 17021888 PH 2.2 | Targeted UG | 3UG | ESTS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 3.74 | 0 | 0 | 3.74 | 0 | 0 | 38.2364 | -120.3626
CWSP - STANISLAUS 17021888 PH 3 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17021888 | 0.0026855 | Stanislaus 17021888 | 0.0073524 | Tier 3 | 7.2701 | 0 | 0 | 0 | 0 | 7.2701 | 38.2364 | -120.3626
CWSP - STANISLAUS 170237278 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 170237278 | 0.00026318 | STANISLAUS 170237278 | 0.01848 | Tier 3 | 8.4875 | 0 | 0 | 0 | 8.4875 | 0 | 38.2465 | -120.3642
CWSP - STANISLAUS 17026028 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v3 | STANISLAUS 17026028 | 0.0008147 | STANISLAUS 17026028 | 0.021109 | Tier 3 | 10.3875 | 0 | 0 | 0 | 10.3875 | 0 | 38.2369 | -120.3646
CWSP - SYCAMORE CREEK 11112014 PH 1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112014 | 0.053762 | SYCAMORE CREEK 11112014 | 0.0064305 | Tier 2 | 8.66 | 0 | 0 | 0 | 8.66 | 0 | 39.8316 | -121.8443
CWSP - SYCAMORE CREEK 11112014 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112014 | 0.053762 | SYCAMORE CREEK 11112014 | 0.0064305 | Tier 2 | 10 | 0 | 0 | 0 | 10 | 0 | 39.833 | -121.8444
CWSP - SYCAMORE CREEK 11112014 PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112014 | 0.053762 | SYCAMORE CREEK 11112014 | 0.0064305 | Tier 2 & 3 | 10 | 0 | 0 | 0 | 0 | 10 | 39.8337 | -121.8445
CWSP - SYCAMORE CREEK 11112268 PH 1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112268 | 0.0016039 | SYCAMORE CREEK 11112268 | 0.021521 | Tier 3 | 10.34 | 0 | 0 | 0 | 10.34 | 0 | 39.9035 | -121.742
CWSP - SYCAMORE CREEK 11112268 PH 2 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112268 | 0.0016039 | SYCAMORE CREEK 11112268 | 0.021521 | Tier 3 | 9.59 | 0 | 0 | 0 | 9.59 | 0 | 39.9339 | -121.7255
CWSP - SYCAMORE CREEK 11112268 PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Chico | Butte | WDRM v3 | SYCAMORE CREEK 11112268 | 0.0016039 | SYCAMORE CREEK 11112268 | 0.021521 | Tier 3 | 7.1701 | 0 | 0 | 0 | 0 | 7.1701 | 39.9339 | -121.7255
CWSP - TIDEWATER 210614072 PH 1.1 | Base SH | 08W | PEND | DI | Region 3 - Bay Area | Concord | Contra Costa | WDRM v2 | TIDEWATER 210614072 | 0.65331 | TIDEWATER 210614072 | 0.0062529 | Tier 2 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 37.9632 | -121.9407
CWSP - TIGER CREEK 201 CB & 320746 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | TIGER CREEK 0201CB | 0.016801 | TIGER CREEK 0201CB | 0.040941 | Tier 2 & 3 | 4.42 | 0 | 0 | 4.42 | 0 | 0 | 38.4492 | -120.492
CWSP - UPPER LAKE 1101 1276 PH 2.4 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 39.1673 | -123.0087
CWSP - UPPER LAKE 1101 1276 PH 2.6 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 39.1758 | -123.0191
CWSP - UPPER LAKE 1101 1276 PH 2.7 | Base SH | 08W | UNSE | HB | Region 1 - North Coast | Upper Lake | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 0.035985 | 0 | 0 | 0 | 0.035985 | 0 | 39.1699 | -123.006
CWSP - UPPER LAKE 1101 LR 75370 PH 1 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Upper Lake | Lake | WDRM v3 | UPPER LAKE 110175370 | 0.11161 | UPPER LAKE 110175370 | 0.0089653 | Tier 2 | 6.04 | 0 | 0 | 0 | 6.04 | 0 | 39.1892 | -122.9009
CWSP - UPPER LAKE 1101 LR 75370 PH 2 | Targeted UG | 3UG | UNSE | HB | Region 1 - North Coast | Upper Lake | Lake | WDRM v3 | UPPER LAKE 110175370 | 0.11161 | UPPER LAKE 110175370 | 0.0089653 | Tier 2 & 3 | 5.26 | 0 | 0 | 0 | 5.26 | 0 | 39.213 | -122.9301
CWSP - UPPER LAKE 11011276 PH 2 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 1.847 | 0 | 1.847 | 0 | 0 | 0 | 39.1434 | -123.0023
CWSP - VACAVILLE 11046542 PH 1.1 | Base SH | 08W | PEND | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11046542 | 0.44642 | VACAVILLE 11046542 | 0.0073117 | Tier 3 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 38.3423 | -122.0077
CWSP - VACAVILLE 11046542 PH 1.3 | Base SH | 08W | CONS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11046542 | 0.44642 | VACAVILLE 11046542 | 0.0073117 | Tier 3 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 38.3423 | -122.0077
CWSP - VOLTA 11011596 - PH1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011596 | 0.071922 | VOLTA 11011596 | 0.0099219 | Tier 2 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 40.351 | -121.7811
CWSP - VOLTA 11011596 - PH1.5 | Base SH | 08W | PEND | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011596 | 0.071922 | VOLTA 11011596 | 0.0099219 | Tier 2 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 40.351 | -121.7811
CWSP - VOLTA 110153118 PH 1.3 | Base SH | 08W | CONS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 110153118 | 0.27952 | VOLTA 110153118 | 0.0099281 | Tier 2 | 0.30436 | 0.30436 | 0 | 0 | 0 | 0 | 40.4013 | -121.8752
CWSP - VOLTA 1101CB PH 1.1 | Base SH | 08W | CONS | NV | Region 2 - North East | Manton | Shasta | WDRM v2 | VOLTA 1101CB | 0.37545 | VOLTA 1101CB | 0.00043332 | Tier 2 & 3 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 40.4595 | -121.8662
CWSP - VOLTA 1101CB PH 1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Manton | Shasta | WDRM v2 | VOLTA 1101CB | 0.37545 | VOLTA 1101CB | 0.00043332 | Tier 2 & 3 | 0.275 | 0 | 0.275 | 0 | 0 | 0 | 40.4594 | -121.8662
CWSP - WEST POINT 1101 CB & 12256 PH 1.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 1101CB | 0.015736 | WEST POINT 1101CB | 0.011836 | Tier 3 | 13.5701 | 0 | 0 | 0 | 0 | 13.5701 | 38.4187 | -120.557
CWSP - WEST POINT 1101 CB & 12256 PH2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 1101CB | 0.015736 | WEST POINT 1101CB | 0.011836 | Tier 3 | 13.7 | 0 | 0 | 0 | 13.7 | 0 | 38.4214 | -120.5494
CWSP - WEST POINT 110113444 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 110113444 | 0.0035258 | WEST POINT 110113444 | 0.01053 | Tier 3 | 12.09 | 0 | 0 | 0 | 12.09 | 0 | 38.4868 | -120.523
CWSP - WEST POINT 110113444 PH 2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 110113444 | 0.0035258 | WEST POINT 110113444 | 0.01053 | Tier 3 | 12.45 | 0 | 0 | 0 | 0 | 12.45 | 38.4894 | -120.5255
CWSP - WEST POINT 11014706 PH2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 11014706 | 0.0020959 | WEST POINT 11014706 | 0.017455 | Tier 3 | 4.99 | 0 | 0 | 0 | 0 | 4.99 | 38.4646 | -120.5292
CWSP - WEST POINT 11021341 PH1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11021341 | 0.0041901 | WEST POINT 11021341 | 0.019265 | Tier 3 | 10.8 | 0 | 0 | 0 | 10.8 | 0 | 38.3174 | -120.5211
CWSP - WEST POINT 11024788 PH 1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11024788 | 0.047319 | WEST POINT 11024788 | 0.014654 | Tier 2 | 9.1 | 0 | 0 | 0 | 0 | 9.1 | 38.3313 | -120.5186
CWSP - WEST POINT 11024788 PH2 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11024788 | 0.047319 | WEST POINT 11024788 | 0.014654 | Tier 2 & 3 | 9.1 | 0 | 0 | 0 | 9.1 | 0 | 38.3313 | -120.5186
CWSP - WEST POINT 11024788 PH3 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11024788 | 0.047319 | WEST POINT 11024788 | 0.014654 | Tier 2 & 3 | 9.1 | 0 | 0 | 0 | 9.1 | 0 | 38.3313 | -120.5186
CWSP - WEST POINT 11024788 PH4 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11024788 | 0.047319 | WEST POINT 11024788 | 0.014654 | Tier 2 & 3 | 9.1 | 0 | 0 | 0 | 0 | 9.1 | 38.3313 | -120.5186
CWSP - WEST POINT 11024788 PH5 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | WDRM v3 | WEST POINT 11024788 | 0.047319 | WEST POINT 11024788 | 0.014654 | Tier 2 & 3 | 9.1 | 0 | 0 | 0 | 0 | 9.1 | 38.3313 | -120.5186
CWSP - WILLOW CREEK 11032936 | Base SH | 08W | UNSE | HB | Region 1 - North Coast | Salyer | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 2 | 0 | 0 | 0 | 2 | 0 | 40.8669 | -123.5148
CWSP - WOODSIDE 1101 FS 775939 PH 1.1 | Base SH | 08W | PEND | PN | Region 3 - Bay Area | Redwood City | San Mateo | WDRM v2 | WOODSIDE 11018974 | 0.05299 | WOODSIDE 11018974 | 0.0021738 | Tier 3 | 1.1939 | 0 | 0 | 1.1939 | 0 | 0 | 37.3845 | -122.2937
CWSP - WYANDOTTE 110932586 PH 1.2 | Base SH | 08W | CONS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 110932586 | 0.52987 | WYANDOTTE 110932586 | 0.0002242 | Tier 2 | 0.4214 | 0.41477 | 0.0066288 | 0 | 0 | 0 | 39.4647 | -121.5189
CWSP ANDERSON 1103 LR1600 PH1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | ANDERSON 11031600 | 0.2889 | ANDERSON 11031600 | 0.00011858 | Tier 2 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 40.469 | -122.2542
CWSP ANDERSON 1103 LR1600 PH2.4 | Base SH | 08W | PEND | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | ANDERSON 11031600 | 0.2889 | ANDERSON 11031600 | 0.00011858 | Tier 2 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 40.4699 | -122.2473
CWSP ANDERSON 1103 LR226050 PH 1.1 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | ANDERSON 1103226050 | 0.22913 | ANDERSON 1103226050 | 8.0345e-05 | Tier 2 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 40.4803 | -122.2646
CWSP ANDERSON 1103 LR226050 PH 1.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | ANDERSON 1103226050 | 0.22913 | ANDERSON 1103226050 | 8.0345e-05 | Tier 2 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 40.4792 | -122.2645
CWSP AUBERRY 1101 R2578 PH1.5 | Base SH | 08W | PEND | FR | Region 5 - Central Valley | Tollhouse | Fresno | WDRM v2 | AUBERRY 1101R2578 | 0.27714 | AUBERRY 1101R2578 | 0.0047219 | Tier 2 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 37.0071 | -119.4086
CWSP AUBERRY 1101 R2578 PH2.4 | Base SH | 08W | PEND | FR | Region 5 - Central Valley | Tollhouse | Fresno | WDRM v2 | AUBERRY 1101R2578 | 0.27714 | AUBERRY 1101R2578 | 0.0047219 | Tier 2 | 0.42822 | 0 | 0.42822 | 0 | 0 | 0 | 37.0125 | -119.4038
CWSP AUBERRY 1101 R2839 PH1.4 | Base SH | 08W | PEND | FR | Region 5 - Central Valley | Tollhouse | Fresno | WDRM v2 | AUBERRY 1101R2839 | 0.22501 | AUBERRY 1101R2839 | 0.0043344 | Tier 2 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 37.0313 | -119.4396
CWSP BIG MEADOWS 2101 2510 PH1.1 | Base SH | 08W | UNSE | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012510 | 4.13e-06 | BIG MEADOWS 21012510 | 0.0023864 | Tier 2 | 3.0701 | 0 | 0 | 0 | 3.0701 | 0 | 40.1581 | -121.081
CWSP BIG MEADOWS 2101 2510 PH1.2 | Base SH | 08W | UNSE | NV | Region 2 - North East | Canyon Dam | Plumas | WDRM v2 | BIG MEADOWS 21012510 | 4.13e-06 | BIG MEADOWS 21012510 | 0.0023864 | Tier 2 | 3 | 0 | 0 | 0 | 3 | 0 | 40.2105 | -121.1643
CWSP BIG MEADOWS 2101 2510 PH1.3 | Base SH | 08W | UNSE | NV | Region 2 - North East | Canyon Dam | Plumas | WDRM v2 | BIG MEADOWS 21012510 | 4.13e-06 | BIG MEADOWS 21012510 | 0.0023864 | Tier 2 | 3.64 | 0 | 0 | 0 | 3.64 | 0 | 40.2105 | -121.1643
CWSP BIG MEADOWS 2101 2510 PH1.4 | Base SH | 08W | UNSE | NV | Region 2 - North East | Canyon Dam | Plumas | WDRM v2 | BIG MEADOWS 21012510 | 4.13e-06 | BIG MEADOWS 21012510 | 0.0023864 | Tier 2 | 2.05 | 0 | 0 | 0 | 2.05 | 0 | 40.2105 | -121.1643
CWSP ELK CREEK 1101 LR2002 PH 2.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 39.4868 | -122.5188
CWSP ELK CREEK 1101 LR2002 PH 2.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Willows | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 39.456 | -122.5138
CWSP ELK CREEK 1101 LR2002 PH 2.4 | Base SH | 08W | ADER | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 39.4286 | -122.5052
CWSP ELK CREEK 1101 LR2002 PH 2.5 | Base SH | 08W | PEND | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 39.4073 | -122.5471
CWSP ELK CREEK 1101 LR2002 PH 2.6 | Base SH | 08W | ADER | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 39.3944 | -122.5518
CWSP ELK CREEK 1101 LR93504 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 110193504 | 0.25426 | ELK CREEK 110193504 | 0.0012407 | Tier 2 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 39.5927 | -122.5431
CWSP FLINT 1101 750 PH 1.2 | Base SH | 08W | ESTS | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | FLINT 1101750 | 0.28318 | FLINT 1101750 | 0.00097924 | Tier 2 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 38.8537 | -121.0803
CWSP FLINT 1101 750 PH 1.3 | Base SH | 08W | ESTS | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | FLINT 1101750 | 0.28318 | FLINT 1101750 | 0.00097924 | Tier 2 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 38.8575 | -121.0758
CWSP HARTLEY 1101 LR698 PH 1.4 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | HARTLEY 1101698 | 0.39723 | HARTLEY 1101698 | 0.0056859 | Tier 2 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 39.108 | -122.9558
CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | Base SH | 08W | PEND | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 1104275986 | 0.26526 | LINCOLN 1104275986 | 0.0001399 | Tier 2 | 3.2375 | 0 | 3.2375 | 0 | 0 | 0 | 38.9755 | -121.2772
CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | Base SH | 08W | ESTS | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 1104275986 | 0.26526 | LINCOLN 1104275986 | 0.0001399 | Tier 2 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 38.97 | -121.2606
CWSP LINCOLN 1104 LR2070 PH 2.1 | Base SH | 08W | ESTS | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 11042070 | 0.14111 | LINCOLN 11042070 | 0.00011911 | Tier 2 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 38.9507 | -121.219
CWSP LINCOLN 1104 LR2070 PH 2.2 | Base SH | 08W | ADER | SI | Region 2 - North East | Lincoln | Placer | WDRM v2 | LINCOLN 11042070 | 0.14111 | LINCOLN 11042070 | 0.00011911 | Tier 2 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 38.9431 | -121.219
CWSP MARIPOSA 2101 LR 35244 PH 2.3 | Base SH | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v2 | MARIPOSA 210135244 | 0.17286 | MARIPOSA 2101151918 | 0.010861 | Tier 2 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 37.5165 | -119.9716
CWSP MARIPOSA 2101 LR 35244 PH1.2 | Base SH | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v2 | MARIPOSA 210135244 | 0.17286 | MARIPOSA 2101151918 | 0.010861 | Tier 2 & 3 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 37.5186 | -119.9402
CWSP MARIPOSA 210110240 PH 1.1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 4.74 | 0 | 0 | 4.74 | 0 | 0 | 37.5251 | -119.9182
CWSP MARIPOSA 210110240 PH 1.2 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 2.46 | 0 | 0 | 0 | 2.46 | 0 | 37.541 | -119.9184
CWSP MARIPOSA 210110240 PH 1.3 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 3.11 | 0 | 0 | 0 | 3.11 | 0 | 37.5582 | -119.9305
CWSP MARIPOSA 210110240 PH 1.4 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 3.15 | 0 | 0 | 0 | 3.15 | 0 | 37.5474 | -119.93
CWSP MARIPOSA 210110240 PH 2.1 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 4 | 0 | 0 | 0 | 4 | 0 | 37.5611 | -119.9354
CWSP MARIPOSA 210110240 PH 2.2 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 4.2 | 0 | 0 | 4.2 | 0 | 0 | 37.5616 | -119.9349
CWSP MARIPOSA 210110240 PH 2.3 | Targeted UG | 3UG | UNSE | YO | Region 5 - Central Valley | Midpines | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 3.88 | 0 | 0 | 3.88 | 0 | 0 | 37.57 | -119.9414
CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | Base SH | 08W | ESTS | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 0.38665 | MOUNTAIN QUARRIES 2101CB | 0.017565 | Tier 2 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 38.8729 | -120.991
CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | Base SH | 08W | PEND | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 38.8972 | -120.989
CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7 | Base SH | 08W | ESTS | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 0.66799 | 0 | 0 | 0.66799 | 0 | 0 | 38.8944 | -120.9647
CWSP POTTER VALLEY PH 1105 LR1904 PH1.9 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Potter Valley | Mendocino | WDRM v2 | POTTER VALLEY P H 11051904 | 0.37685 | POTTER VALLEY P H 11051904 | 0.0046795 | Tier 2 & 3 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 39.3009 | -123.0524
CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Potter Valley | Mendocino | WDRM v2 | POTTER VALLEY P H 11051904 | 0.37685 | POTTER VALLEY P H 11051904 | 0.0046795 | Tier 2 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 39.2815 | -123.1027
CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Ukiah | Mendocino | WDRM v2 | POTTER VALLEY P H 11051904 | 0.37685 | POTTER VALLEY P H 11051904 | 0.0046795 | Tier 2 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 39.2145 | -123.0742
CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Ukiah | Mendocino | WDRM v2 | POTTER VALLEY P H 11051904 | 0.37685 | POTTER VALLEY P H 11051904 | 0.0046795 | Tier 2 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 39.1987 | -123.0496
CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Potter Valley | Mendocino | WDRM v2 | POTTER VALLEY P H 110537476 | 0.18107 | POTTER VALLEY P H 110537476 | 0.00037714 | Tier 2 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 39.3076 | -123.1132
CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Potter Valley | Mendocino | WDRM v2 | POTTER VALLEY P H 110537476 | 0.18107 | POTTER VALLEY P H 110537476 | 0.00037714 | Tier 2 | 0.25398 | 0 | 0.25398 | 0 | 0 | 0 | 39.2968 | -123.1087
CWSP REDBUD 1101 708166 PH 1.1 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 39.023 | -122.6779
CWSP REDBUD 1101 708166 PH 1.2 | Base SH | 08W | ADER | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 39.0531 | -122.6813
CWSP REDBUD 1101 708166 PH 1.3 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 39.0541 | -122.6767
CWSP REDBUD 1101 708166 PH 1.4 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 39.0448 | -122.6814
CWSP REDBUD 1101 708166 PH 1.5 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 39.04 | -122.6823
CWSP REDBUD 1101 708166 PH 1.6 | Base SH | 08W | ADER | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 39.0296 | -122.6802
CWSP REDBUD 1101 708166 PH 1.7 | Base SH | 08W | ADER | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101708166 | 0.0038601 | Tier 2 & 3 | 4 | 0 | 4 | 0 | 0 | 0 | 39.0287 | -122.6799
CWSP REDBUD 1101 754544 PH 1.1 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101754544 | 0.007396 | Tier 2 & 3 | 3.5201 | 0 | 0 | 3.5201 | 0 | 0 | 39.0581 | -122.693
CWSP REDBUD 1101 754544 PH 1.2 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake Oaks | Lake | WDRM v2 | REDBUD 1101708166 | 0.19539 | REDBUD 1101754544 | 0.007396 | Tier 2 & 3 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 39.0932 | -122.6804
CWSP STANISLAUS 1702 CB PH 1.2 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Murphys | Calaveras | WDRM v2 | STANISLAUS 1702CB | 0.24096 | STANISLAUS 1702CB | 0.022026 | Tier 2 & 3 | 0.91742 | 0 | 0.91742 | 0 | 0 | 0 | 38.1677 | -120.3831
CWSP STANISLAUS 1702 CB PH 1.3 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v2 | STANISLAUS 1702CB | 0.24096 | STANISLAUS 1702CB | 0.022026 | Tier 2 & 3 | 2.7547 | 0 | 2.7547 | 0 | 0 | 0 | 38.2399 | -120.3619
CWSP STANISLAUS 1702 CB PH 1.5 | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Murphys | Calaveras | WDRM v2 | STANISLAUS 1702CB | 0.24096 | STANISLAUS 1702CB | 0.022026 | Tier 2 & 3 | 2.2667 | 0 | 2.2667 | 0 | 0 | 0 | 38.1677 | -120.3831
CWSP UPPER LAKE 1101 1276 PH 1.3 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 0.72614 | 0 | 0.72614 | 0 | 0 | 0 | 39.1488 | -122.9992
CWSP UPPER LAKE 1101 1276 PH 1.5 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Lakeport | Lake | WDRM v2 | UPPER LAKE 11011276 | 0.19794 | UPPER LAKE 11011276 | 0.024971 | Tier 2 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 39.13 | -122.997
CWSP WEST POINT 1101 LR4706 PH1.1 | Targeted UG | 3UG | UNSE | ST | Region 5 - Central Valley | Pioneer | Amador | WDRM v3 | WEST POINT 11014706 | 0.0020959 | WEST POINT 11014706 | 0.017455 | Tier 3 | 14.3201 | 0 | 0 | 0 | 0 | 14.3201 | 38.4678 | -120.5277
CWSP_0780_EL DORADO 21026645 1.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | (blank) | 0.0020868 | EL DORADO PH 21026645 | 0.0031904 | Tier 3 | 4.29 | 0 | 0 | 0 | 4.29 | 0 | 38.7701 | -120.5893
CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | Base SH | 08W | PEND | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 38.8956 | -120.9606
CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | Base SH | 08W | PEND | SI | Region 2 - North East | Greenwood | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 0.98996 | 0 | 0 | 0.98996 | 0 | 0 | 38.8964 | -120.922
CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | Base SH | 08W | UNSC | SI | Region 2 - North East | Greenwood | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 38.8973 | -120.9098
CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | Base SH | 08W | PEND | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 0.0069368 | Tier 2 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 38.8805 | -120.9418
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Base SH | 08W | CONS | SI | Region 2 - North East | Shingle Springs | El Dorado | WDRM v2 | SHINGLE SPRINGS 210935598 | 0.27855 | SHINGLE SPRINGS 210935598 | 0.011098 | Tier 3 | 5.0311 | 0.97178 | 4.0593 | 0 | 0 | 0 | 38.7686 | -120.9251
CWSP-SILVERADO 2105 167360&990552 PH1.1 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105167360 | 0.0056116 | SILVERADO 2105167360 | 0.0070204 | Tier 3 | 8.2201 | 0 | 0 | 8.2201 | 0 | 0 | 38.4983 | -122.4796
CWSP-SILVERADO 2105 167360&990552 PH1.2 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105167360 | 0.0056116 | SILVERADO 2105167360 | 0.0070204 | Tier 3 | 1.25 | 0 | 0 | 0 | 0 | 1.25 | 38.4996 | -122.4892
CWSP-SILVERADO 2105 167360&990552 PH1.3 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105167360 | 0.0056116 | SILVERADO 2105167360 | 0.0070204 | Tier 3 | 2.31 | 0 | 0 | 0 | 0 | 2.31 | 38.4944 | -122.4756
CWSP-SILVERADO 2105 167360&990552 PH1.4 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105167360 | 0.0056116 | SILVERADO 2105167360 | 0.0070204 | Tier 3 | 1.5299 | 0 | 0 | 0 | 0 | 1.5299 | 38.4947 | -122.494
CWSP-SILVERADO 2105 167360&990552 PH1.5 | Targeted UG | 3UG | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v3 | SILVERADO 2105167360 | 0.0056116 | SILVERADO 2105167360 | 0.0070204 | Tier 3 | 2.95 | 0 | 0 | 0 | 0 | 2.95 | 38.4911 | -122.5229
CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Base SH | 08W | CONS | ST | Region 5 - Central Valley | Arnold | Calaveras | WDRM v2 | STANISLAUS 17021804 | 0.00058985 | STANISLAUS 17021804 | 0.00088659 | Tier 3 | 0.053977 | 0.053977 | 0 | 0 | 0 | 0 | 38.2579 | -120.3477
CYPRESS LN | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 3.9 | 0 | 3.9 | 0 | 0 | 0 | 39.784 | -121.5864
DOG TOWN & MAGALIA DAM | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.5 | 0 | 0 | 3.5 | 0 | 0 | 39.8149 | -121.5802
DREXEL DR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 39.8182 | -121.5952
ECOP - CLAYTON 2212 - H01-LR2951 | Base SH | 08W | PEND | DI | Region 3 - Bay Area | Clayton | Contra Costa | WDRM v2 | CLAYTON 221296224 | 0.18755 | CLAYTON 221296224 | 0.034099 | Tier 3 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 37.8684 | -121.8574
ECOP - LAS GALLINAS A 1105 PH 2 | Base SH | 08W | PEND | NB | Region 1 - North Coast | San Rafael | Marin | WDRM v2 | LAS GALLINAS A 110599904 | 0.25006 | LAS GALLINAS A 110599904 | 0.0014262 | Tier 3 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 38.0443 | -122.6155
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 38.7576 | -122.6358
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 0.41894 | 0 | 0 | 0.41894 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Base SH | 08W | DOCC | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.2508 | 1.2034 | 0.047348 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Base SH | 08W | UNSE | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 38.7988 | -122.7044
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 38.7576 | -122.6358
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 38.7576 | -122.6358
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 38.7576 | -122.6358
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 38.7577 | -122.6359
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Base SH | 08W | PEND | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 1101548 | 0.15935 | MIDDLETOWN 1101548 | 0.018129 | Tier 3 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 38.7576 | -122.6358
ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 110148212 | 0.1603 | MIDDLETOWN 110148212 | 0.035184 | Tier 3 | 1.3765 | 0 | 1.3765 | 0 | 0 | 0 | 38.7249 | -122.6186
ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Base SH | 08W | CONS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 110148212 | 0.1603 | MIDDLETOWN 110148212 | 0.035184 | Tier 3 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 38.7249 | -122.6186
ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 110148212 | 0.1603 | MIDDLETOWN 110148212 | 0.035184 | Tier 3 | 2.04 | 0 | 0 | 2.04 | 0 | 0 | 38.7241 | -122.619
ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Middletown | Lake | WDRM v2 | MIDDLETOWN 110148212 | 0.1603 | MIDDLETOWN 110148212 | 0.035184 | Tier 3 | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 38.7249 | -122.6186
EQUIP ACCESS ISSUE 1025 HIDDEN VALLEY RD | Other | 2BP | UNSC | CC | Region 4 - Central Coast | Soquel | Santa Cruz | WDRM v2 | CAMP EVERS 210311046 | 0.0012326 | CAMP EVERS 210311046 | 0.0013011 | Tier 3 | 0.015341 | 0 | 0 | 0 | 0.015341 | 0 | 37.0341 | -121.9738
EUREKA DR | Community Rebuild | 08W | PEND | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.3 | 0 | 0 | 2.3 | 0 | 0 | 39.8082 | -121.5973
FOSTER RD | Community Rebuild | 95F O | CONS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | 39.7484 | -121.6266
FRRB - BIG BASIN 1102 UG6 BB VINEYARD | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 110296986 | 0.0075562 | BIG BASIN 110296986 | 0.0011281 | Tier 3 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 37.1837 | -122.1598
FRRB - BIG BASIN 1102 UG2 CAMPGROUND | Fire Rebuild | 08W | UNSE | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 11025066 | 0.0029066 | BIG BASIN 11025066 | 0.0013052 | Tier 3 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 37.1699 | -122.2026
FRRB - BIG BASIN 1102 UG3 HWY 236 | Fire Rebuild | 08W | ESTS | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 11025066 | 0.0029066 | BIG BASIN 11025066 | 0.0013052 | Tier 3 | 1.5299 | 0 | 0 | 1.5299 | 0 | 0 | 37.1672 | -122.2131
FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN | Fire Rebuild | 08W | UNSE | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 11025066 | 0.0029066 | BIG BASIN 11025066 | 0.0013052 | Tier 3 | 0.52008 | 0 | 0 | 0 | 0.52008 | 0 | 37.1657 | -122.2231
FRRB - BIG BASIN 1102 UG5 LITTLEBASIN CG | Fire Rebuild | 08W | UNSE | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 11025066 | 0.0029066 | BIG BASIN 11025066 | 0.0013052 | Tier 3 | 1.24 | 0 | 0 | 0 | 1.24 | 0 | 37.163 | -122.1902
FRRB - BIG BEND 1102 884340 - B4 SM2 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Berry Creek | Butte | WDRM v3 | BIG BEND 11021972 | 0.040961 | BIG BEND 1102884340 | 0.010152 | Tier 3 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 39.6626 | -121.4006
FRRB - BIG MEADOWS 21012248 UG ML PH1 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 1.2858 | 0 | 1.2858 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BIG MEADOWS 21012248 UG ML PH2 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BIG MEADOWS 21012248 UG ML PH3 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012260 | 0.067786 | BIG MEADOWS 21012260 | 0.00047036 | Tier 2 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012260 | 0.067786 | BIG MEADOWS 21012260 | 0.00047036 | Tier 2 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - BUCKS CREEK 1101 CB PH 2.1 | Fire Rebuild | 08W | UNSC | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1101CB | 0.73491 | BUCKS CREEK 1101CB | 0.029234 | Tier 2 & 3 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 39.9101 | -121.3297
FRRB - BUCKS CREEK 1101 CB PH 3.1 | Fire Rebuild | 08W | UNSC | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1101CB | 0.73491 | BUCKS CREEK 1101CB | 0.029234 | Tier 2 & 3 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 39.9007 | -121.3594
FRRB - BUCKS CREEK 1102 CB PH1 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 39.9141 | -121.3272
FRRB - BUCKS CREEK 1102 CB PH2 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 39.9141 | -121.3272
FRRB - BUCKS CREEK 1102 CB PH3 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 39.9141 | -121.3272
FRRB - BUCKS CREEK 1102 CB PH4 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Belden | Plumas | WDRM v2 | BUCKS CREEK 1102CB | 0.1873 | BUCKS CREEK 1102CB | 0.023178 | Tier 2 & 3 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 39.9141 | -121.3272
FRRB - BUCKS CREEK 1102CB PH5 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012260 | 0.067786 | BIG MEADOWS 21012260 | 0.00047036 | Tier 2 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | CRESCENT MILLS 21012056 | 0.080308 | CRESCENT MILLS 21012056 | 0.0028532 | Tier 2 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB - DUNBAR 1101416 | Fire Rebuild | 08W | ESTS | SO | Region 1 - North Coast | Santa Rosa | Sonoma | WDRM v2 | DUNBAR 1101416 | 0.019316 | DUNBAR 1103416 | 0.0035071 | Tier 3 | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | 38.4361 | -122.5779
FRRB - ECHO SUMMIT 1101 - UG - 10 | Fire Rebuild | 08W | ESTS | SI | Region 2 - North East | Twin Bridges | El Dorado | WDRM v2 | ECHO SUMMIT 1101481660 | 0.0089565 | ECHO SUMMIT 1101481660 | 0.00038767 | Tier 2 | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | 38.8075 | -120.0935
FRRB - GANSNER 11012424 UG PH1.2 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Quincy | Plumas | WDRM v2 | GANSNER 11012424 | 0.050559 | GANSNER 11012424 | 0.0031715 | Tier 2 & 3 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 40.0075 | -120.9605
FRRB - GRAYS FLAT 0401904916 PH1.1 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Twain | Plumas | WDRM v2 | GRAYS FLAT 0401CB | 0.016728 | GRAYS FLAT 0401CB | 0.0051671 | Tier 2 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 40.0222 | -121.0643
FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Fire Rebuild | 08W | CONS | PN | Region 3 - Bay Area | Pescadero | San Mateo | WDRM v2 | HALF MOON BAY 110369412 | 0.0078448 | HALF MOON BAY 110369412 | 0.0002898 | Tier 2 | 2.5239 | 1.6411 | 0 | 0.88277 | 0 | 0 | 37.2551 | -122.3815
FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Fire Rebuild | 08W | CONS | CC | Region 3 - Bay Area | Pescadero | San Mateo | WDRM v2 | HALF MOON BAY 110369412 | 0.0078448 | HALF MOON BAY 110369412 | 0.0002898 | Tier 2 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 37.2551 | -122.3815
FRRB - HMB 1103 SM CO LR6012 PUMP HOUSE | Fire Rebuild | 08W | UNSE | PN | Region 3 - Bay Area | Pescadero | San Mateo | WDRM v2 | HALF MOON BAY 11036012 | 0.0054078 | HALF MOON BAY 11036012 | 0.00033154 | Tier 2 | 0.85814 | 0 | 0 | 0.85814 | 0 | 0 | 37.2086 | -122.3251
FRRB - KANAKA 1101 - K1 PH 1.1 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | KANAKA 1101CB | 0.029281 | KANAKA 1101CB | 0.01209 | Tier 3 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 39.5762 | -121.3051
FRRB - KANAKA 1101CB - K2 SM3 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v3 | KANAKA 1101CB | 0.029281 | KANAKA 1101CB | 0.01209 | Tier 3 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 39.574 | -121.3077
FRRB - MARIPOSA 210110170 ML-5 | Fire Rebuild | 08W | PEND | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 & 3 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 37.517 | -119.8344
FRRB - MARIPOSA 210110170 TL-10 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110170 | 0.014293 | MARIPOSA 210110170 | 0.015939 | Tier 3 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 37.5083 | -119.8773
FRRB - MARIPOSA 210110240 ML-1 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 & 3 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 37.541 | -119.9184
FRRB - MARIPOSA 210110240 TL-1 | Fire Rebuild | 08W | PEND | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 37.517 | -119.8344
FRRB - MARIPOSA 21019400 ML-2 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 2 & 3 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 37.5113 | -119.9076
FRRB - MARIPOSA 21019400 ML-3 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 & 3 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 37.5087 | -119.8728
FRRB - MARIPOSA 21019400 ML-4 | Fire Rebuild | 08W | PEND | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 & 3 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 37.513 | -119.8444
FRRB - MARIPOSA 21019400 ML-6 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110240 | 0.11431 | MARIPOSA 210110240 | 0.016323 | Tier 3 | 0.71004 | 0 | 0 | 0.71004 | 0 | 0 | 37.5139 | -119.8384
FRRB - MARIPOSA 21019400 TL-11 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 & 3 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 37.5136 | -119.8722
FRRB - MARIPOSA 21019400 TL-2 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 37.5268 | -119.904
FRRB - MARIPOSA 21019400 TL-3 | Fire Rebuild | 08W | PEND | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 2 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 37.5083 | -119.8773
FRRB - MARIPOSA 21019400 TL-4 INSTALL | Fire Rebuild | 08W | ADER | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 210110170 | 0.014293 | MARIPOSA 210110170 | 0.015939 | Tier 2 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 37.5016 | -119.8815
FRRB - MARIPOSA 21019400 TL-5 INSTALL | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 37.5083 | -119.8773
FRRB - MARIPOSA 21019400 TL-6 INSTALL | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 37.5363 | -119.833
FRRB - MARIPOSA 21019400 TL-7 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 37.5363 | -119.833
FRRB - MARIPOSA 21019400 TL-8 INSTALL | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 0.45 | 0 | 0 | 0.45 | 0 | 0 | 37.5136 | -119.8722
FRRB - MARIPOSA 21019400 TL-9 INSTALL | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 | 37.5268 | -119.904
FRRB - MARIPOSA 21029590 TL-1 | Fire Rebuild | 08W | ESTS | YO | Region 5 - Central Valley | Mariposa | Mariposa | WDRM v3 | MARIPOSA 21019400 | 0.11849 | MARIPOSA 21019400 | 0.00537 | Tier 3 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 37.5079 | -119.8466
FRRB - PT MORETTI 1101 12122 PH1 SM4 | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Davenport | Santa Cruz | WDRM v2 | POINT MORETTI 110112122 | 0.0051004 | POINT MORETTI 110112122 | 0.00042654 | Tier 2 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 37.0773 | -122.2434
FRRB - SPANISH CREEK UG ML PH1.1 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Crescent Mills | Plumas | WDRM v2 | SPANISH CREEK 4401CB | 0.038702 | SPANISH CREEK 4401CB | 0.0020497 | Tier 2 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 40.0604 | -120.9643
FRRB - SPANISH CREEK UG TL PH1.2 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Crescent Mills | Plumas | WDRM v2 | SPANISH CREEK 4401CB | 0.038702 | SPANISH CREEK 4401CB | 0.0020497 | Tier 2 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 40.0553 | -120.9636
FRRB - WILLOW CREEK 11032936 - UG TL4 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 40.7875 | -123.4468
FRRB - WILLOW CREEK 11032936 UG ML1 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG ML3 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG ML4 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG ML5 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 1 | 0 | 1 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG ML6 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG TL1 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG TL2 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WILLOW CREEK 11032936 UG TL3 | Fire Rebuild | 08W | PEND | HB | Region 1 - North Coast | Burnt Ranch | Trinity | WDRM v2 | WILLOW CREEK 11032936 | 0.029513 | WILLOW CREEK 11032936 | 0.0024804 | Tier 2 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 40.8422 | -123.485
FRRB - WYANDOTTE 1103 - W3 PH 3.2 | Fire Rebuild | 08W | DOCC | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 1103640652 | 0.010796 | Tier 3 | 1.8256 | 1.8193 | 0.00625 | 0 | 0 | 0 | 39.6343 | -121.4112
FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 39.6348 | -121.3915
FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 39.6348 | -121.3915
FRRB - WYANDOTTE 1103 W5 PH5.4 SM | Fire Rebuild | 08W | UNSC | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 39.6348 | -121.3915
FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 39.5852 | -121.4309
FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 39.6827 | -121.3105
FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Berry Creek | Butte | WDRM v2 | WYANDOTTE 11031976 | 0.040282 | WYANDOTTE 11031508 | 0.0051219 | Tier 3 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 39.655 | -121.459
FRRB -BIG BASIN 1102 12758 P1S2 CYPRESS | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 110212758 | 0.002947 | BIG BASIN 110212758 | 0.0026407 | Tier 3 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 37.1443 | -122.1579
FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012476 | 0.0030704 | BIG MEADOWS 21012476 | 0.00093756 | Tier 2 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB -BIG MEADOWS 21012260 UG TL 1.13 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 0.35 | 0 | 0.35 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB -BIG MEADOWS 21012260 UG TL 1.6 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012260 | 0.067786 | BIG MEADOWS 21012260 | 0.00047036 | Tier 2 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB -BIG MEADOWS 21012260 UG TL 1.9 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012260 | 0.067786 | BIG MEADOWS 21012260 | 0.00047036 | Tier 2 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | Fire Rebuild | 08W | ESTS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012476 | 0.0030704 | BIG MEADOWS 21012476 | 0.00093756 | Tier 2 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB -BIG MEADOWS 21012586 UG PH1 | Fire Rebuild | 08W | CONS | NV | Region 2 - North East | Greenville | Plumas | WDRM v2 | BIG MEADOWS 21012586 | 0.041237 | BIG MEADOWS 21012586 | 0.00013567 | Tier 2 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 40.1581 | -121.081
FRRB FORESTHILL 110137238 UG TL4 | Fire Rebuild | 08W | UNSE | SI | Region 2 - North East | Foresthill | Placer | WDRM v3 | FORESTHILL 110137238 | 0.031693 | FORESTHILL 110137238 | 0.0088134 | Tier 3 | 1.2197 | 0 | 0 | 0 | 1.2197 | 0 | 39.0444 | -120.7393
FRRB PLACERVILLE 21061104 UG TL5 | Fire Rebuild | 08W | UNSE | SI | Region 2 - North East | Georgetown | El Dorado | WDRM v3 | PLACERVILLE 21061104 | 0.0064469 | PLACERVILLE 21061104 | 0.0070659 | Tier 3 | 0.84905 | 0 | 0 | 0 | 0 | 0.84905 | 38.9878 | -120.7412
FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Davenport | Santa Cruz | WDRM v2 | POINT MORETTI 110112122 | 0.0051004 | POINT MORETTI 110112122 | 0.00042654 | Tier 2 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 37.0777 | -122.2439
FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | WDRM v2 | BIG BASIN 110110720 | 0.002283 | BIG BASIN 110110720 | 0.0019396 | Tier 3 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 37.1291 | -122.1378
FRRB-BIG BASIN 1101 UG1 SAN VICENTE | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | WDRM v2 | BIG BASIN 11015000 | 0.0013814 | BIG BASIN 11015000 | 0.0018854 | Tier 3 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 37.0992 | -122.1435
FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | Fire Rebuild | 08W | PEND | NV | Region 2 - North East | Chester | Plumas | WDRM v2 | BIG MEADOWS 21012248 | 0.077859 | BIG MEADOWS 21012248 | 0.0046735 | Tier 2 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 40.2927 | -121.2429
FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | Fire Rebuild | 08W | PEND | CC | Region 4 - Central Coast | Davenport | Santa Cruz | WDRM v2 | BIG BASIN 11022253 | 0.0041981 | BIG BASIN 11022253 | 0.002497 | Tier 2 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 37.072 | -122.2298
GLENDALE DR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | 39.8082 | -121.6017
GREEN VALLEY RD EL DORADO CNTY R20A | Other | 30A | PEND | SI | Region 2 - North East | Placerville | El Dorado | WDRM v2 | DIAMOND SPRINGS 11071402 | 0.092281 | Diamond Springs 11071402 | 0.0016787 | Tier 2 | 1.3299 | 0 | 0 | 1.3299 | 0 | 0 | 38.726 | -120.8396
GRIZZLY PEAK BLVD BERKELEY R20A | Other | 30A | PEND | EB | Region 3 - Bay Area | Berkeley | Alameda | WDRM v2 | EL CERRITO G 1105BR160 | 0.00031068 | El Cerrito G 1105BR160 | 0.00025777 | Tier 2 & 3 | 1.4576 | 0 | 0 | 1.4576 | 0 | 0 | 37.8838 | -122.2484
HAPPY WOODS | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 39.7681 | -121.5891
HERMAN | Community Rebuild | 08W | ADER | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 39.7813 | -121.594
HIGH SCHOOL MAXWELL | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 39.7619 | -121.6125
HILLPARK LN | Community Rebuild | 95F O | CONS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 39.7392 | -121.5724
HONEY RUN | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 39.7717 | -121.6118
HOSPITAL | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.2 | 0 | 0 | 3.2 | 0 | 0 | 39.7572 | -121.5722
HWY 299 SHASTA R20A | Other | 30A | ESTS | NV | Region 2 - North East | Shasta | Shasta | WDRM v2 | KESWICK 11019712 | 0.022607 | Keswick 11019712 | 0.023649 | Tier 3 | 0.37879 | 0 | 0 | 0 | 0 | 0.37879 | 40.5923 | -122.4836
JARVIS LN | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 5.2 | 0 | 5.2 | 0 | 0 | 0 | 39.7389 | -121.6402
JERRYS WAY | Community Rebuild | 95F O | CONS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 39.7741 | -121.5895
JOPLIN CT | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.5 | 0 | 0 | 3.5 | 0 | 0 | 39.8146 | -121.6066
KLING CT | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 39.764 | -121.5986
MAPLE PARK | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 39.7616 | -121.6079
MYRTLE WAY | Community Rebuild | 95F CEMA | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.9 | 0 | 0 | 2.9 | 0 | 0 | 39.7858 | -121.6004
NORWOOD | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 39.7637 | -121.5732
OAK KNOLL (Caltrans) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 4.3 | 0 | 0 | 4.3 | 0 | 0 | 39.7485 | -121.6086
OAK WAY | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.9 | 0 | 0 | 1.9 | 0 | 0 | 39.7712 | -121.6031
PALOMA AVE | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 39.7471 | -121.6129
PARAGALIA | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | 39.78 | -121.6092
PBS-360 OAK SPRING RD | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 0.12027 | 0 | 0 | 0.12027 | 0 | 0 | 39.7414 | -121.6432
PBS-5552 CLARK RD | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | 39.7484 | -121.6087
PBS-BURKE LN | Community Rebuild | 95F | PEND | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 0.066288 | 0 | 0 | 0.066288 | 0 | 0 | 39.7704 | -121.6012
PBS-NOTTONGHAM PARK | Community Rebuild | 95F | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 0.088447 | 0 | 0 | 0.088447 | 0 | 0 | 39.7598 | -121.6341
PBS-NUTMEG WAY | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 0.066288 | 0 | 0 | 0.066288 | 0 | 0 | 39.7874 | -121.601
PEARSON RD | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 39.7524 | -121.6126
PENTZ & WAGSTAFF | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 4.8 | 0 | 4.8 | 0 | 0 | 0 | 39.7886 | -121.5797
PENTZ PH1 (Arrowhead to Fickett) | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2 | 0 | 0 | 2 | 0 | 0 | 39.769 | -121.5786
PLUCODIXIE-ALTA CAMP Z6 GREENVILLE | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 40.1415 | -120.9483
PLUCODIXIE-BIDWELL ST Z2 GREENVILLE | Community Rebuild | 95F | PEND | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.7197 | 0 | 0.7197 | 0 | 0 | 0 | 40.1407 | -120.9513
PLUCODIXIE-BUSH ST Z1 GREENVILLE | Community Rebuild | 95F | PEND | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 1.2871 | 0 | 1.2871 | 0 | 0 | 0 | 40.1415 | -120.9483
PLUCODIXIE-COMMERCIAL-Z2 GREENVILLE | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 40.1407 | -120.9513
PLUCODIXIE-FORGAY AVE Z3 GREENVILLE | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 1.017 | 0 | 1.017 | 0 | 0 | 0 | 40.1435 | -120.9581
PLUCODIXIE-HIDEAWAY Z7 GREENVILLE | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 40.1415 | -120.9483
PLUCODIXIE-HOT SPRINGS RD Z5 GREENVILLE | Community Rebuild | 95F | ESTS | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 40.1397 | -120.9389
PLUCODIXIE-KINDER AVE Z4 GREENVILLE | Community Rebuild | 95F | PEND | NV | Region 2 - North East | Greenville | Plumas | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 1.0417 | 0 | 1.0417 | 0 | 0 | 0 | 40.1413 | -120.957
PONDEROSA DR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 39.8167 | -121.598
PRINCETON WAY | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 2 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 39.7461 | -121.6435
PSPS - BANGOR 1101 CB - MICROGRID | Base SH | 08W | CONS | NV | Region 2 - North East | Bangor | Butte | WDRM v2 | BANGOR 1101CB | 0.19378 | BANGOR 1101CB | 0.00020951 | Tier 2 | 1.1968 | 1.1364 | 0.060417 | 0 | 0 | 0 | 39.3878 | -121.4038
PSPS - CLARK ROAD 1102 LR514690 PH 1.4 | Base SH | 08W | UNSE | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 11022070 | 0.063106 | CLARK ROAD 11022070 | 0.0036217 | Tier 2 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0 | 39.6578 | -121.5657
PSPS CLARK ROAD 1102 LR81296 PH 1.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 110281296 | 0.11218 | CLARK ROAD 110281296 | 0.0021691 | Tier 2 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 39.6474 | -121.6306
PSPS CLARK ROAD 1102 LR81296 PH 1.2 | Base SH | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 110281296 | 0.11218 | CLARK ROAD 110281296 | 0.0021691 | Tier 2 | 0.94091 | 0 | 0.94091 | 0 | 0 | 0 | 39.655 | -121.5839
PSPS CLARK ROAD 1102 LR81296 PH 1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 110281296 | 0.11218 | CLARK ROAD 110281296 | 0.0021691 | Tier 2 | 2.814 | 0 | 2.814 | 0 | 0 | 0 | 39.6564 | -121.5838
PSPS CLARK ROAD 1102 LR81296 PH 1.4 | Base SH | 08W | ADER | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 110281296 | 0.11218 | CLARK ROAD 110281296 | 0.0021691 | Tier 2 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 39.6667 | -121.5826
PSPS - CLAYTON 2215 - CB | Base SH | 08W | CONS | DI | Region 3 - Bay Area | Concord | Contra Costa | WDRM v2 | CLAYTON 2215184604 | 0.016935 | CLAYTON 2215184604 | 0.0006705 | Tier 2 & 3 | 1.8845 | 0 | 0 | 1.8845 | 0 | 0 | 37.931 | -121.9736
PSPS - CORNING 1102 LR53184 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Corning | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 39.8685 | -122.5663
PSPS - CORNING 1102 LR53184 PH 1.10 | Base SH | 08W | ESTS | NV | Region 2 - North East | Corning | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 39.8773 | -122.5512
PSPS - CORNING 1102 LR53184 PH 1.11 | Base SH | 08W | ESTS | NV | Region 2 - North East | Covelo | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 39.8634 | -122.5862
PSPS - CORNING 1102 LR53184 PH 1.12 | Base SH | 08W | ESTS | NV | Region 2 - North East | Covelo | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 39.8466 | -122.59
PSPS - CORNING 1102 LR53184 PH 1.15 | Base SH | 08W | ESTS | NV | Region 2 - North East | Covelo | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 39.846 | -122.5891
PSPS - CORNING 1102 LR53184 PH 1.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Covelo | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 39.8493 | -122.6179
PSPS - CORNING 1102 LR53184 PH 1.5 | Base SH | 08W | ESTS | NV | Region 2 - North East | Corning | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 39.9089 | -122.4786
PSPS - CORNING 1102 LR53184 PH 1.7 | Base SH | 08W | ESTS | NV | Region 2 - North East | Red Bluff | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 39.9108 | -122.493
PSPS - CORNING 1102 LR53184 PH 1.8 | Base SH | 08W | ESTS | NV | Region 2 - North East | Red Bluff | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 39.8928 | -122.5171
PSPS - CORNING 1102 LR53184 PH 1.9 | Base SH | 08W | ESTS | NV | Region 2 - North East | Red Bluff | Tehama | WDRM v2 | CORNING 110253184 | 0.17544 | CORNING 110253184 | 0.0037456 | Tier 2 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 39.887 | -122.5361
PSPS - CORNING 1102 LR915324 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Corning | Tehama | WDRM v2 | CORNING 1102915324 | 0.16319 | CORNING 1102915324 | 0.0001615 | Tier 2 | 2 | 0 | 2 | 0 | 0 | 0 | 39.9193 | -122.4369
PSPS - CORNING 1102 LR915324 PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Corning | Tehama | WDRM v2 | CORNING 1102915324 | 0.16319 | CORNING 1102915324 | 0.0001615 | Tier 2 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 39.918 | -122.4709
PSPS - COTTONWOOD 1102544790 PH 1 | Base SH | 08W | ADER | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 1102544790 | 0.31273 | COTTONWOOD 1102544790 | 0.0007912 | Tier 2 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 40.3895 | -122.3067
PSPS - COTTONWOOD 1102544790 PH 2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 1102544790 | 0.31273 | COTTONWOOD 1102544790 | 0.0007912 | Tier 2 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 40.3895 | -122.3067
PSPS - COTTONWOOD 11029026 PH1 | Base SH | 08W | ADER | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 40.3893 | -122.3434
PSPS - COTTONWOOD 11029026 PH2 | Base SH | 08W | PEND | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 40.3893 | -122.3434
PSPS - COTTONWOOD 11029026 PH3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 4.81 | 0 | 4.81 | 0 | 0 | 0 | 40.3893 | -122.3434
PSPS - CURTIS 1701 CB PH 1.1 | Base SH | 08W | ADER | YO | Region 5 - Central Valley | Sonora | Tuolumne | WDRM v2 | CURTIS 1701CB | 0.051116 | CURTIS 1701CB | 0.0021952 | Tier 2 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 37.9777 | -120.3274
PSPS - CURTIS 1701 CB PH 1.2 | Base SH | 08W | ESTS | YO | Region 5 - Central Valley | Sonora | Tuolumne | WDRM v2 | CURTIS 1701CB | 0.051116 | CURTIS 1701CB | 0.0021952 | Tier 2 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 37.9803 | -120.337
PSPS - CURTIS 1701 CB PH 1.3 | Base SH | 08W | ESTS | YO | Region 5 - Central Valley | Sonora | Tuolumne | WDRM v2 | CURTIS 1701CB | 0.051116 | CURTIS 1701CB | 0.0021952 | Tier 2 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 37.9737 | -120.3714
PSPS - DUNBAR 1101 - OAKMONT | Base SH | 08W | PEND | SO | Region 1 - North Coast | Santa Rosa | Sonoma | WDRM v2 | DUNBAR 1101CB | 0.007993 | DUNBAR 1101CB | 0.00012812 | Tier 2 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 38.4438 | -122.602
PSPS - DUNBAR 1101 - OAKMONT PH 2 | Base SH | 08W | ESTS | SO | Region 1 - North Coast | Santa Rosa | Sonoma | WDRM v2 | DUNBAR 1101CB | 0.007993 | DUNBAR 1101CB | 0.00012812 | Tier 2 | 1.0008 | 0 | 0 | 1.0008 | 0 | 0 | 38.4438 | -122.602
PSPS - DUNBAR 1101 - OAKMONT PH 3 | Base SH | 08W | PEND | SO | Region 1 - North Coast | Santa Rosa | Sonoma | WDRM v2 | DUNBAR 1101CB | 0.007993 | DUNBAR 1101CB | 0.00012812 | Tier 2 | 0.90341 | 0 | 0 | 0.90341 | 0 | 0 | 38.4438 | -122.602
PSPS - DUNBAR 1101 440 PH 1.1 | Base SH | 08W | ESTS | SO | Region 1 - North Coast | Glen Ellen | Sonoma | WDRM v2 | DUNBAR 1103534 | 0.01369 | DUNBAR 1101534 | 0.0063584 | Tier 2 & 3 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 38.3791 | -122.5192
PSPS - DUNBAR 1101 440 PH 1.3 | Base SH | 08W | ESTS | SO | Region 1 - North Coast | Sonoma | Sonoma | WDRM v2 | DUNBAR 1103534 | 0.01369 | DUNBAR 1101534 | 0.0063584 | Tier 2 & 3 | 0.58 | 0 | 0 | 0.58 | 0 | 0 | 38.3371 | -122.4929
PSPS - EL DORADO PH 2101 LR 668674 PH1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 2101CB | 0.0041406 | EL DORADO PH 2101CB | 0.019264 | Tier 3 | 6.65 | 0 | 0 | 6.65 | 0 | 0 | 38.7928 | -120.6194
PSPS - EL DORADO PH 2101 LR 668674 PH2.1 | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | Pollock Pines | El Dorado | WDRM v3 | EL DORADO PH 2101CB | 0.0041406 | EL DORADO PH 2101CB | 0.019264 | Tier 3 | 4.41 | 0 | 0 | 4.41 | 0 | 0 | 38.7646 | -120.5783
PSPS - FLINT1101 CB & 40666 PH1.1 | Base SH | 08W | ESTS | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | FLINT 1101958726 | 1.76e-05 | FLINT 1101958726 | 0.00050684 | Tier 2 | 1.0131 | 0 | 0 | 1.0131 | 0 | 0 | 38.8933 | -121.0677
PSPS - FLINT1101 CB & 40666 PH1.2 | Base SH | 08W | ESTS | SI | Region 2 - North East | Auburn | Placer | WDRM v2 | FLINT 1101958726 | 1.76e-05 | FLINT 1101958726 | 0.00050684 | Tier 2 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 38.8934 | -121.0677
PSPS - FROGTOWN 1702 - CB | Base SH | 08W | PEND | ST | Region 5 - Central Valley | Angels Camp | Calaveras | WDRM v2 | FROGTOWN 1702CB | 0.039234 | FROGTOWN 1702CB | 0.0016222 | Tier 3 | 0.53447 | 0 | 0.53447 | 0 | 0 | 0 | 38.0453 | -120.5253
PSPS - JAMESON 1102 LR65516 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 38.2515 | -122.161
PSPS - JAMESON 1102 LR65516 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 38.2645 | -122.1722
PSPS - JAMESON 1102 LR65516 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 38.2553 | -122.1615
PSPS - JAMESON 1102 LR65516 1.4 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 38.2565 | -122.1688
PSPS - JAMESON 1102 LR65516 1.5 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 38.262 | -122.1635
PSPS - JAMESON 1102 LR65516 1.6 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 38.2706 | -122.167
PSPS - JAMESON 1102 LR65516 1.7 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 38.2714 | -122.1672
PSPS - JAMESON 1102 LR65516 1.9 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 110265516 | 0.104 | JAMESON 110265516 | 0.0089196 | Tier 2 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 38.2491 | -122.1769
PSPS - JAMESON 1105 LR466348 PH 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 38.3063 | -122.1288
PSPS - JAMESON 1105 LR466348 PH 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 38.3141 | -122.1263
PSPS - JAMESON 1105 LR466348 PH 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 38.2972 | -122.1262
PSPS - JAMESON 1105 LR466348 PH 1.4 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 38.2877 | -122.1043
PSPS - JAMESON 1105 LR466348 PH 1.5 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 38.3039 | -122.0964
PSPS - JAMESON 1105 LR466348 PH 1.6 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 38.3148 | -122.0962
PSPS - JAMESON 1105 LR466348 PH 1.7 | Base SH | 08W | ESTS | NB | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 38.3158 | -122.1039
PSPS - JAMESON 1105 LR466348 PH 2.1 | Base SH | 08W | ADER | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 38.299 | -122.1519
PSPS - JAMESON 1105 LR466348 PH 2.2 | Base SH | 08W | ADER | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 38.2968 | -122.1356
PSPS - JAMESON 1105 LR466348 PH 2.3 | Base SH | 08W | ADER | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105466348 | 0.18223 | JAMESON 1105466348 | 0.0035256 | Tier 2 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 38.2925 | -122.1292
PSPS - JAMESON 1105371694 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105371694 | 0.012819 | JAMESON 1105371694 | (blank) | Tier 2 | 0.34508 | 0 | 0 | 0.34508 | 0 | 0 | 38.2642 | -122.1295
PSPS - JAMESON 1105913400 | Base SH | 08W | ESTS | SA | Region 2 - North East | Fairfield | Solano | WDRM v2 | JAMESON 1105913400 | 0.17457 | JAMESON 1105913400 | 0.0022992 | Tier 2 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 38.284 | -122.128
PSPS - JESSUP 1103 LR348657 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | JESSUP 1103348657 | 0.13388 | JESSUP 1103770356 | 0.00016206 | Tier 2 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 40.4913 | -122.2744
PSPS - JESSUP 1103 LR348657 PH 1.4 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | JESSUP 1103348657 | 0.13388 | JESSUP 1103728460 | 0.00046034 | Tier 2 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 40.4668 | -122.3357
PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Base SH | 08W | CONS | ST | Region 5 - Central Valley | Sutter Creek | Amador | WDRM v2 | MARTELL 1101CB | 0.067405 | MARTELL 1101CB | 0.0002828 | Tier 2 | 1.225 | 0 | 0 | 1.225 | 0 | 0 | 38.3949 | -120.804
PSPS - MOUNTAIN QUARRIES 2101 - COOL | Base SH | 08W | PEND | SI | Region 2 - North East | Cool | El Dorado | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 0.38665 | MOUNTAIN QUARRIES 2101CB | 0.017565 | Tier 2 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 38.8855 | -121.0156
PSPS - PANORAMA 1101 CB PH 1.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | PANORAMA 1101CB | 0.062374 | PANORAMA 1101CB | 5.6461e-05 | Tier 2 | 0.15 | 0 | 0.15 | 0 | 0 | 0 | 40.4267 | -122.2656
PSPS - PANORAMA 1101 CB PH 1.2 | Base SH | 08W | PEND | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | PANORAMA 1101CB | 0.062374 | PANORAMA 1101CB | 5.6461e-05 | Tier 2 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 40.4214 | -122.2578
PSPS - PIT NO 3 21011482 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 3.1407 | 0 | 0 | 0 | 3.1407 | 0 | 40.9982 | -121.7479
PSPS - PIT NO 3 21011482 PH 2.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 2.9066 | 0 | 0 | 2.9066 | 0 | 0 | 40.9685 | -121.8246
PSPS - PIT NO 3 2101CB PH 1.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 2101CB | 0.01407 | PIT NO 3 2101CB | 0.0086689 | Tier 2 | 1.893 | 0 | 0 | 0 | 1.893 | 0 | 40.9982 | -121.7478
PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Base SH | 08W | CONS | SI | Region 2 - North East | Georgetown | El Dorado | WDRM v2 | PLACERVILLE 21067522 | 0.035529 | PLACERVILLE 21067522 | 0.0099544 | Tier 3 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 38.905 | -120.8401
PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Base SH | 08W | CONS | SI | Region 2 - North East | Georgetown | El Dorado | WDRM v2 | PLACERVILLE 21067522 | 0.035529 | PLACERVILLE 21067522 | 0.0099544 | Tier 3 | 0.84962 | 0 | 0.84962 | 0 | 0 | 0 | 38.9063 | -120.837
PSPS - SAN LUIS OBISPO 1101 PH 1.1 | Base SH | 08W | UNSE | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | WDRM v2 | GOLDTREE 1105CB | 0.056447 | GOLDTREE 1105CB | 0.00059698 | Tier 2 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 35.2683 | -120.6383
PSPS - SILVERADO 2104708 | Base SH | 08W | UNSE | NB | Region 1 - North Coast | Saint Helena | Napa | WDRM v2 | SILVERADO 2104708 | 0.02118 | SILVERADO 2104708 | 0.0043024 | Tier 3 | 3.5799 | 0 | 0 | 3.5799 | 0 | 0 | 38.5192 | -122.4719
PSPS - TEJON 1102 LR2455 PH 1.1 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11022455 | 0.12034 | TEJON 11022455 | 0.020158 | Tier 2 | 2.39 | 0 | 0 | 2.39 | 0 | 0 | 34.8582 | -118.8837
PSPS - TEJON 1102 LR2455 PH 1.2 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11022455 | 0.12034 | TEJON 11022455 | 0.020158 | Tier 2 | 5.21 | 0 | 0 | 5.21 | 0 | 0 | 34.8542 | -118.893
PSPS - TEJON 1102 LR2455 PH 1.3 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11022455 | 0.12034 | TEJON 11022455 | 0.020158 | Tier 2 | 2.1799 | 0 | 0 | 2.1799 | 0 | 0 | 34.8466 | -118.8987
PSPS - TEJON 1102 LR3751 PH 1.1 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 1.6 | 0 | 0 | 0 | 1.6 | 0 | 34.9321 | -118.9283
PSPS - TEJON 1102 LR3751 PH 1.2 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 3.6 | 0 | 0 | 0 | 3.6 | 0 | 34.9158 | -118.9258
PSPS - TEJON 1102 LR3751 PH 1.3 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 1.5775 | 0 | 0 | 0 | 0 | 1.5775 | 34.8908 | -118.9154
PSPS - TEJON 1102 LR732836 PH 1.1 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 1.979 | 0 | 0 | 1.979 | 0 | 0 | 34.8814 | -118.9012
PSPS - TEJON 1102 LR732836 PH 1.2 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 2.174 | 0 | 0 | 2.174 | 0 | 0 | 34.8765 | -118.8926
PSPS - TEJON 1102 LR732836 PH 1.3 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 1.591 | 0 | 0 | 1.591 | 0 | 0 | 34.8726 | -118.8905
PSPS - TEJON 1102 LR732836 PH 1.4 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 2.902 | 0 | 0 | 2.902 | 0 | 0 | 34.8582 | -118.8835
PSPS - TEJON 1102 LR732836 PH 1.5 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 0.421 | 0 | 0 | 0 | 0.421 | 0 | 34.8594 | -118.8797
PSPS - TEJON 1102 LR732836 PH 2.1 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 2.8129 | 0 | 0 | 2.8129 | 0 | 0 | 34.846 | -118.872
PSPS - TEJON 1102 LR732836 PH 2.2 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 1.723 | 0 | 0 | 0 | 1.723 | 0 | 34.8407 | -118.8677
PSPS - TEJON 1102 LR732836 PH 2.3 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 2.443 | 0 | 0 | 0 | 2.443 | 0 | 34.837 | -118.8663
PSPS - TEJON 1102 LR732836 PH 2.4 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 2.604 | 0 | 0 | 0 | 2.604 | 0 | 34.8295 | -118.8723
PSPS - TEJON 1102 LR732836 PH 2.5 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 1102732836 | 0.1353 | TEJON 1102732836 | 0.011818 | Tier 2 | 4.508 | 0 | 0 | 0 | 4.508 | 0 | 34.8363 | -118.8637
PSPS - TEJON 11023751 PH 2.1 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 2.958 | 0 | 0 | 0 | 2.958 | 0 | 34.8908 | -118.9154
PSPS - TEJON 11023751 PH 2.2 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 2.252 | 0 | 0 | 0 | 0 | 2.252 | 34.8833 | -118.9271
PSPS - TEJON 11023751 PH 2.3 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 2.997 | 0 | 0 | 0 | 0 | 2.997 | 34.8868 | -118.9361
PSPS - TEJON 11023751 PH 2.4 | Base SH | 08W | UNSE | KE | Region 5 - Central Valley | Lebec | Kern | WDRM v2 | TEJON 11023751 | 0.11269 | TEJON 11023751 | 0.0075263 | Tier 2 | 1.357 | 0 | 0 | 0 | 0 | 1.357 | 34.8814 | -118.9012
PSPS - VACAVILLE 1108 LR38316 PH 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 2.3 | 0 | 0 | 2.3 | 0 | 0 | 38.4365 | -122.0527
PSPS - VACAVILLE 1108 LR38316 PH 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 38.4313 | -122.05
PSPS - VACAVILLE 1108 LR38316 PH 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 38.4267 | -122.0475
PSPS - VACAVILLE 1108 LR38316 PH 1.4 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | 38.4201 | -122.0443
PSPS - VACAVILLE 1108 LR38316 PH 1.5 | Base SH | 08W | ADER | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 0.95 | 0 | 0 | 0 | 0.95 | 0 | 38.4295 | -122.0489
PSPS - VACAVILLE 1108 LR38316 PH 2.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 38.4168 | -122.0381
PSPS - VACAVILLE 1108 LR38316 PH 2.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 38.4024 | -122.0318
PSPS - VACAVILLE 1108 LR38316 PH 2.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 110838316 | 0.31672 | VACAVILLE 110838316 | 0.0056058 | Tier 2 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 38.3911 | -122.0367
PSPS - VACAVILLE 1108 LR8762 PH 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11088762 | 0.39138 | VACAVILLE 11088762 | 0.0032459 | Tier 2 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 38.344 | -122.0247
PSPS - VACAVILLE 1108 LR8762 PH 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11088762 | 0.39138 | VACAVILLE 11088762 | 0.0032459 | Tier 2 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 38.3588 | -122.0245
PSPS - VACAVILLE 1108 LR8762 PH 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11088762 | 0.39138 | VACAVILLE 11088762 | 0.0032459 | Tier 2 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 38.3655 | -122.0233
PSPS - VACAVILLE 1108 LR8762 PH 2.0 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 11088762 | 0.39138 | VACAVILLE 11088762 | 0.0032459 | Tier 2 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 38.3618 | -122.0219
PSPS - VACAVILLE 1111 CB PH 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 1111CB | 0.15336 | VACAVILLE 1111CB | 0.00055328 | Tier 2 | 2.2 | 0 | 0 | 2.2 | 0 | 0 | 38.3783 | -122.0044
PSPS - VACAVILLE 1111 CB PH 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 1111CB | 0.15336 | VACAVILLE 1111CB | 0.00055328 | Tier 2 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 38.3771 | -121.9968
PSPS - VACAVILLE 1111 CB PH 1.3 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 1111CB | 0.15336 | VACAVILLE 1111CB | 0.00055328 | Tier 2 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 38.3772 | -121.9918
PSPS - VACAVILLE 1111 CB PH 1.4 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 1111CB | 0.15336 | VACAVILLE 1111CB | 0.00055328 | Tier 2 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 38.3663 | -121.9916
PSPS - VACAVILLE 1111 LR13652 PH 1.1 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 111113652 | 0.26339 | VACAVILLE 111113652 | 0.00074783 | Tier 2 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 38.3933 | -122.0146
PSPS - VACAVILLE 1111 LR13652 PH 1.2 | Base SH | 08W | ESTS | SA | Region 2 - North East | Vacaville | Solano | WDRM v2 | VACAVILLE 111113652 | 0.26339 | VACAVILLE 111113652 | 0.00074783 | Tier 2 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 38.3898 | -122.0001
PSPS - VOLTA 11011516 PH 1.10 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 1.8561 | 0 | 0 | 0 | 0 | 1.8561 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.11 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.5091 | 0 | 0 | 2.5091 | 0 | 0 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.12 | Base SH | 08W | UNSE | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.746 | 0 | 0 | 2.746 | 0 | 0 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.13 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.8689 | 0 | 0 | 0 | 0 | 2.8689 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.14 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 4.621 | 0 | 0 | 4.621 | 0 | 0 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.15 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.5381 | 0 | 0 | 0 | 0 | 2.5381 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.16 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 3.2201 | 0 | 0 | 0 | 3.2201 | 0 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.4 | Base SH | 08W | ESTS | NV | Region 2 - North East | Red Bluff | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 1.5951 | 0 | 0 | 1.5951 | 0 | 0 | 40.3386 | -122.1218
PSPS - VOLTA 11011516 PH 1.5 | Base SH | 08W | ESTS | NV | Region 2 - North East | Red Bluff | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.014 | 0 | 0 | 2.014 | 0 | 0 | 40.3305 | -122.0971
PSPS - VOLTA 11011516 PH 1.7 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.4159 | 0 | 0 | 0 | 2.4159 | 0 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.8 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.8131 | 0 | 0 | 0 | 0 | 2.8131 | 40.3452 | -121.8922
PSPS - VOLTA 11011516 PH 1.9 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paynes Creek | Tehama | WDRM v2 | VOLTA 11011516 | 0.13616 | VOLTA 11011516 | 0.0036607 | Tier 2 | 2.1591 | 0 | 0 | 2.1591 | 0 | 0 | 40.3452 | -121.8922
PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Base SH | 08W | UNSE | SI | Region 2 - North East | Placerville | El Dorado | WDRM v2 | PLACERVILLE 1112CB | 0.0065148 | PLACERVILLE 1112CB | 0.00055552 | Tier 2 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 38.7293 | -120.7998
PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Base SH | 08W | CONS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1109702710 | 0.24845 | WYANDOTTE 1109702710 | 0.00032066 | Tier 2 | 0.53561 | 0.40985 | 0 | 0.12576 | 0 | 0 | 39.4738 | -121.5307
PSPS - WYANDOTTE 1110 LR980944 PH1.6 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 39.5152 | -121.4932
PSPS - WYANDOTTE 1110 LR980944 PH1.7 | Base SH | 08W | UNSE | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 39.5168 | -121.4943
PSPS - WYANDOTTE 1110 LR980944 PH1.8 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 39.52 | -121.4943
PSPS - WYANDOTTE 1110 LR980944 PH1.9 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 0.84 | 0 | 0 | 0.84 | 0 | 0 | 39.5082 | -121.5038
PSPS CLARK ROAD 1102 CB PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 1102CB | 0.22632 | CLARK ROAD 1102CB | 0.00031072 | Tier 2 | 0.89091 | 0 | 0 | 0.89091 | 0 | 0 | 39.654 | -121.6323
PSPS CLARK ROAD 1102 CB PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 1102CB | 0.22632 | CLARK ROAD 1102CB | 0.00031072 | Tier 2 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 39.6413 | -121.6413
PSPS CLARK ROAD 1102 LR47006 PH 1.1 | Base SH | 08W | ADER | NV | Region 2 - North East | Paradise | Butte | WDRM v2 | CLARK ROAD 110247006 | 0.025936 | CLARK ROAD 110247006 | 0.022808 | Tier 2 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 39.6988 | -121.5743
PSPS CLARK ROAD 1102 LR47006 PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | WDRM v2 | CLARK ROAD 110247006 | 0.025936 | CLARK ROAD 110247006 | 0.022808 | Tier 2 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 39.709 | -121.5757
PSPS CLARK ROAD 1102 LR514690 PH 1.1 | Base SH | 08W | ADER | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 11022070 | 0.063106 | CLARK ROAD 11022070 | 0.0036217 | Tier 2 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 39.6568 | -121.5763
PSPS CLARK ROAD 1102 LR514690 PH 1.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 11022070 | 0.063106 | CLARK ROAD 11022070 | 0.0036217 | Tier 2 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 39.6666 | -121.5712
PSPS CLARK ROAD 1102 LR514690 PH 2.1 | Base SH | 08W | PEND | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | CLARK ROAD 11022094 | 0.018088 | CLARK ROAD 1102407706 | 0.0022353 | Tier 2 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 39.6766 | -121.5675
PSPS CLARK ROAD 1102 LR514690 PH 2.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Paradise | Butte | WDRM v2 | CLARK ROAD 11022094 | 0.018088 | CLARK ROAD 1102407706 | 0.0022353 | Tier 2 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 39.6908 | -121.5733
PSPS CLARK ROAD 1102 LR514690 PH 2.3 | Base SH | 08W | ADER | NV | Region 2 - North East | Paradise | Butte | WDRM v2 | CLARK ROAD 11022094 | 0.018088 | CLARK ROAD 1102514690 | 0.0025042 | Tier 2 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 39.6805 | -121.5693
PSPS COTTONWOOD 1102 LR544790 PH 1.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 1102544790 | 0.31273 | COTTONWOOD 1102544790 | 0.0007912 | Tier 2 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 40.3986 | -122.3143
PSPS COTTONWOOD 1102 LR544790 PH 2.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 1102544790 | 0.31273 | COTTONWOOD 1102544790 | 0.0007912 | Tier 2 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 40.3892 | -122.3258
PSPS COTTONWOOD 1102 LR9026 PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 40.3899 | -122.3499
PSPS COTTONWOOD 1102 LR9026 PH 2.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Anderson | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 40.4149 | -122.3421
PSPS COTTONWOOD 1102 LR9026 PH 2.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 40.4042 | -122.3264
PSPS COTTONWOOD 1102 LR9026 PH 3.2 | Base SH | 08W | ADER | NV | Region 2 - North East | Cottonwood | Shasta | WDRM v2 | COTTONWOOD 11029026 | 0.22599 | COTTONWOOD 11029026 | 0.0002216 | Tier 2 | 3.0299 | 0 | 3.0299 | 0 | 0 | 0 | 40.3886 | -122.3831
PSPS ELK CREEK 1101 LR2002 PH 1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 39.5896 | -122.5395
PSPS ELK CREEK 1101 LR2002 PH 1.2 | Base SH | 08W | PEND | NV | Region 2 - North East | Elk Creek | Glenn | WDRM v2 | ELK CREEK 11012002 | 0.20473 | ELK CREEK 11012002 | 0.0021026 | Tier 2 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 39.5561 | -122.5414
PSPS HIGHLANDS 1104 CB PH 1.2 | Base SH | 08W | ESTS | HB | Region 1 - North Coast | Clearlake | Lake | WDRM v2 | HIGHLANDS 1104CB | 5.43e-06 | HIGHLANDS 1104CB | 0.00090896 | Tier 2 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 38.9373 | -122.6091
PSPS PIT NO 3 21011482 PH 1.2 | Base SH | 08W | PEND | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 3.6396 | 0 | 0 | 0 | 3.6396 | 0 | 40.9729 | -121.7814
PSPS PIT NO 3 21011482 PH 2.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 3.5241 | 0 | 0 | 0 | 3.5241 | 0 | 40.9868 | -121.8481
PSPS PIT NO 3 21011482 PH 2.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v3 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 0.55814 | 0 | 0 | 0 | 0.55814 | 0 | 40.9849 | -121.8485
PSPS PIT NO 3 2101CB PH 1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v2 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 3.284 | 0 | 0 | 0 | 3.284 | 0 | 41.0088 | -121.7129
PSPS PIT NO 3 2101CB PH 1.3 | Base SH | 08W | PEND | NV | Region 2 - North East | Montgomery Creek | Shasta | WDRM v3 | PIT NO 3 21011482 | 0.0032735 | PIT NO 3 21011482 | 0.0070854 | Tier 2 | 0.52917 | 0 | 0 | 0.52917 | 0 | 0 | 40.9947 | -121.7415
PSPS WYANDOTTE 1110 LR980944 PH1.1 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 39.5054 | -121.4999
PSPS WYANDOTTE 1110 LR980944 PH1.2 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 2.67 | 0 | 0 | 2.67 | 0 | 0 | 39.5178 | -121.4854
PSPS WYANDOTTE 1110 LR980944 PH1.3 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 39.5261 | -121.4815
PSPS WYANDOTTE 1110 LR980944 PH1.4 | Base SH | 08W | ESTS | NV | Region 2 - North East | Oroville | Butte | WDRM v2 | WYANDOTTE 1110980944 | 0.070566 | WYANDOTTE 1110980944 | 0.00070123 | Tier 2 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 39.5171 | -121.4825
R20A - FREESTONE SONOMA COUNTY | Other | 30A | PEND | SO | Region 1 - North Coast | Sebastopol | Sonoma | WDRM v2 | MOLINO 110266006 | 0.14747 | Molino 110266006 | 0.00074971 | Tier 3 | 1.5138 | 0 | 0 | 1.5138 | 0 | 0 | 38.3734 | -122.918
REDBUD DR | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 39.7551 | -121.6455
REMG 36 - ORO FINO 1102 PH 5 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 2 | 8.75 | 0 | 0 | 0 | 0 | 8.75 | 39.8856 | -121.666
REMG 368 - STILLWATER 1101 | Fire Rebuild | 08W | UNSE | NV | Region 2 - North East | Redding | Shasta | WDRM v2 | STILLWATER 110148950 | 0.085979 | STILLWATER 110148950 | 0.00040165 | Tier 2 | 1.1201 | 0 | 0 | 0 | 0 | 1.1201 | 40.6951 | -122.3174
REMG 508 - ORO FINO 1102 PH 1 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 3 | 10.19 | 0 | 0 | 10.19 | 0 | 0 | 39.8871 | -121.6654
REMG 510 - ORO FINO 1102 PH 3 | Targeted UG | 3UG | UNSE | NV | Region 2 - North East | Forest Ranch | Butte | WDRM v3 | ORO FINO 110239154 | 0.0013923 | ORO FINO 110239154 | 0.010009 | Tier 2 & 3 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 39.8868 | -121.6655
ROSEHILL | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.7 | 0 | 0 | 3.7 | 0 | 0 | 39.7382 | -121.6208
S PARK DR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.1 | 0 | 0 | 3.1 | 0 | 0 | 39.8005 | -121.6047
SHADOWBROOK | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 39.7578 | -121.6071
SHAW CIR | Community Rebuild | 95F O | PEND | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 39.8116 | -121.5956
SHERWOOD CIR | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.8 | 0 | 0 | 2.8 | 0 | 0 | 39.8243 | -121.5994
SIERRA PARK DR | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.6 | 0 | 0 | 3.6 | 0 | 0 | 39.7501 | -121.6242
SKYWAY PH4 (Bille to Wagstaff) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Non-HFTD | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 39.7752 | -121.6093
SKYWAY PH5 (Wagstaff to Pentz) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 5.9 | 0 | 0 | 5.9 | 0 | 0 | 39.7842 | -121.5991
SKYWAY PH6 (Old Magalia) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 5.5 | 0 | 0 | 5.5 | 0 | 0 | 39.7285 | -121.6363
STARLIGHT CT | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 2 | 5.6 | 0 | 0 | 5.6 | 0 | 0 | 39.7423 | -121.6423
STINSON LN | Community Rebuild | 95F O | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 39.7703 | -121.6071
VALLEY SPRINGS 1102 FEEDER OUTLET | Other | 06A | PEND | ST | Region 5 - Central Valley | Valley Springs | Calaveras | WDRM v2 | NORTH BRANCH 1101CB | 0.20132 | NORTH BRANCH 1101CB | 0.0020877 | Tier 2 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 38.2131 | -120.7638
W PARK DR | Community Rebuild | 08W | PEND | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 39.8091 | -121.5998
WARREN RD | Community Rebuild | 95F O | UNSC | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2 | 0 | 2 | 0 | 0 | 0 | 39.7886 | -121.5873
WAYLAND (elec only) | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 3.6 | 0 | 0 | 3.6 | 0 | 0 | 39.7265 | -121.6374
WHATEVER LN | Community Rebuild | 95F O | PEND | NV | Region 2 - North East | Paradise | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 39.7404 | -121.5939
WYCLIFF WAY | Community Rebuild | 08W | ESTS | NV | Region 2 - North East | Magalia | Butte | 0 | N/A | N/A | N/A | N/A | Tier 3 | 2.2 | 0 | 0 | 2.2 | 0 | 0 | 39.8192 | -121.6024
(blank) | Targeted UG | 3UG | UNSE | SI | Region 2 - North East | COLFAX | Placer | WDRM v3 | SHADY GLEN 11022232 | 0.0086414 | SHADY GLEN 11022232 | 0.018723 | Tier 3 | 25.9 | 0 | 0 | 0 | 10.9 | 15 | 78.2889 | -241.8161
[6 empty] | Placerville | El Dorado | WDRM v3 | APPLE HILL 21026552 | 0.2712 | APPLE HILL 21026552 | 0.025831 | Tier 3 | 15.1375 | 0 | 0 | 15.1375 | 0 | 0 | 38.6817 | -120.6632
|  |  |  | ST | Region 5 - Central Valley | Avery | Calaveras | WDRM v3 | STANISLAUS 17011812 | 0.032657 | STANISLAUS 17011812 | 0.02064 | Tier 3 | 23.788 | 0 | 0 | 0 | 8.788 | 15 | 76.3663 | -240.7508
[6 empty] | Murphys | Calaveras | WDRM v3 | STANISLAUS 1701CB | 0.40353 | STANISLAUS 1701CB | 0.018647 | Tier 2 & 3 | 44.875 | 0 | 0 | 0 | 17.95 | 26.925 | 190.8676 | -601.9167
Grand Total | [13 empty] | 2697.1635 | 10.6458 | 534.3408 | 588.2466 | 682.9839 | 880.9464 | 30372.155 | -94740.0974

## SH 23-26_workplan_Conf (hidden)
SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan - filter by Y | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan | SH Workplan
PG&E 2023-2026 System Hardening Workplan |  | Confidential
Data as of January 3, 2023
Data Sources: DOT update from Merih as of 1/3/23, Butte Rebuild List from Kyle Hughes, Tranch 1 High Risk pre-scoping miles from Brad Koelling
[7 empty] | 502.9049 | 2520.6644 | 139.8031 | 3163.3724 | 44.9333 | 10.6458 | 0.8839 | 56.4631 | 184.1431 | 456.6398 | 55.6509 | 696.4338 | 127.3717 | 489.4485 | 57.8243 | 674.6445 | 143.1446 | 682.9839 | 23.454 | 849.5824 | 0.59405 | 880.9464 | 1.99 | 883.5304
Order | Order Description | Category | MAT | SAP Status | Status (see 2nd tab) | WMP GH-03 SH (Y/N) | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles | OH - 2025 Forecast | UG - 2025 Forecast | Removal - 2025 Forecast | 2025 Total Miles | OH - 2026 Forecast | UG - 2026 Forecast | Removal - 2026 Forecast | 2026 Total Miles | Div | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (V2) | 2021-2023 Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | 2024-2026 Risk Rank (V3) | v3 Mean Risk | HFTD Tier
35311627 | CWSP BIG MEADOWS 2101 2510 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 | 0 | 3328 | 4.13e-06 | 0 | 969 | 0.0023864 | Tier 2
35398090 | FRRB -BIG MEADOWS 21012260 OH TL 1.14 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0.57027 | 0 | 0 | 0.57027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1356 | -120.9468 | WDRM v3 | 0 | 995 | 0 | 0 | 2135 | 0 | Tier 2
35374057 | CWSP - GEYSERVILLE - 1101482 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 | 0 | 2170 | 0.0056711 | 0 | 1375 | 0.0011879 | Tier 2
35379282 | REMG - EL DORADO PH 21016852 PH 5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7271 | -120.5477 | WDRM v3 | #REF! | 2252 | 0 | 0 | 1042 | 0 | Tier 3
35367472 | CWSP_0780_EL DORADO 21026645 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 | 0 | 2469 | 0.0020868 | 0 | 780 | 0.0031904 | Tier 3
35373630 | CWSP - ORO FINO 11012022 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 | 0 | 2420 | 0.0024209 | 0 | 657 | 0.003959 | Tier 3
35373629 | CWSP - ORO FINO 11012022 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.76 | 0 | 5.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.76 | 0 | 5.76 | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 | 0 | 2420 | 0.0024209 | 0 | 657 | 0.003959 | Tier 3
35367501 | CWSP - ORO FINO 11012022 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.54 | 0 | 4.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.54 | 0 | 4.54 | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 | 0 | 2420 | 0.0024209 | 0 | 657 | 0.003959 | Tier 3
35373626 | CWSP - EL DORADO PH 21016852 PH 4.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.2701 | 0 | 6.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2701 | 0 | 6.2701 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 | 0 | 2028 | 0.0085289 | 0 | 625 | 0.0042306 | Tier 3
35373625 | CWSP - EL DORADO PH 21016852 PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.2201 | 0 | 6.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2201 | 0 | 6.2201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 | 0 | 2028 | 0.0085289 | 0 | 625 | 0.0042306 | Tier 3
35311626 | CWSP BIG MEADOWS 2101 2510 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 | 0 | 3328 | 4.13e-06 | 0 | 969 | 0.0023864 | Tier 2
35311596 | CWSP BIG MEADOWS 2101 2510 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 | 0 | 3328 | 4.13e-06 | 0 | 969 | 0.0023864 | Tier 2
35286103 | CWSP BIG MEADOWS 2101 2510 PH1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0701 | 0 | 3.0701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 3328 | 4.13e-06 | 0 | 969 | 0.0023864 | Tier 2
35373624 | CWSP - EL DORADO 21016852 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9201 | 0 | 11.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 | 0 | 2028 | 0.0085289 | 0 | 625 | 0.0042306 | Tier 3
35367473 | CWSP - EL DORADO 21016852 - PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 | 0 | 2028 | 0.0085289 | 0 | 625 | 0.0042306 | Tier 3
35390389 | CWSP - MARIPOSA 210110070 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.51 | 0 | 5.51 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 | 0 | 187 | 0.2644 | 0 | 531 | 0.0051015 | Tier 2
35375091 | CWSP - LOS OSITOS 21037062 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.6799 | 0 | 7.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6799 | 0 | 7.6799 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 | 0 | 1359 | 0.035805 | 0 | 516 | 0.0052285 | Tier 2
35364020 | CWSP - LOS OSITOS 21037062 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 | 0 | 1359 | 0.035805 | 0 | 516 | 0.0052285 | Tier 2
35376306 | FRRB - MARIPOSA 21019400 TL-11 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2 & 3
35376304 | FRRB - MARIPOSA 21019400 TL-8 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35376303 | FRRB - MARIPOSA 21019400 TL-9 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21004 | 0 | 0.21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374866 | FRRB - MARIPOSA 21019400 TL-7 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374865 | FRRB - MARIPOSA 21019400 TL-6 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374864 | FRRB - MARIPOSA 21019400 TL-5 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374862 | FRRB - MARIPOSA 21029590 TL-1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374687 | FRRB - MARIPOSA 21019400 TL-3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2
35374686 | FRRB - MARIPOSA 21019400 TL-2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374685 | FRRB - MARIPOSA 210110240 TL-1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 3
35374684 | FRRB - MARIPOSA 210110170 ML-5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2 & 3
35374683 | FRRB - MARIPOSA 21019400 ML-4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2 & 3
35374682 | FRRB - MARIPOSA 210110240 ML-1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2 & 3
35374559 | FRRB - MARIPOSA 21019400 ML-3 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 | 0 | 655 | 0.11849 | 0 | 504 | 0.00537 | Tier 2 & 3
35364022 | CWSP - LOS COCHES 1101625902 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 | 0 | 2006 | 0.0089147 | 0 | 462 | 0.0060529 | Tier 2
35374455 | CWSP - SYCAMORE CREEK 11112014 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 | 0 | 1137 | 0.053762 | 0 | 434 | 0.0064305 | Tier 2 & 3
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86269 | 0 | 0 | 0.86269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9747 | -121.8839 | WDRM v2 | 0 | 3283 | 4.6505e-06 | 0 | 2739 | 0.00021707 | Tier 3
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9718 | -121.8758 | WDRM v2 | 0 | 3283 | 4.6505e-06 | 0 | 2739 | 0.00021707 | Tier 3
35329471 | PSPS HIGHLANDS 1104 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 | 0 | 3243 | 5.43e-06 | 0 | 1561 | 0.00090896 | Tier 2
35374454 | CWSP - SYCAMORE CREEK 11112014 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 | 0 | 1137 | 0.053762 | 0 | 434 | 0.0064305 | Tier 2
35374444 | CWSP - SYCAMORE CREEK 11112014 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.66 | 0 | 8.66 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 | 0 | 1137 | 0.053762 | 0 | 434 | 0.0064305 | Tier 2
35396304 | CWSP - BRUNSWICK 11062104 PH2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 | 0 | 2157 | 0.0059169 | 0 | 429 | 0.0065825 | Tier 3
35392779 | CWSP - BRUNSWICK 11062104 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 | 0 | 2157 | 0.0059169 | 0 | 429 | 0.0065825 | Tier 3
35392778 | CWSP - BRUNSWICK 11062104 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 | 0 | 2157 | 0.0059169 | 0 | 429 | 0.0065825 | Tier 3
35373585 | CWSP - BRUNSWICK 11062104 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 | 0 | 2157 | 0.0059169 | 0 | 429 | 0.0065825 | Tier 3
35367418 | CWSP - BRUNSWICK 11062104 PH1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.02 | 0 | 4.02 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 | 0 | 2157 | 0.0059169 | 0 | 429 | 0.0065825 | Tier 3
35396074 | FRRB - BUCKS CREEK 1103CB PH1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.8984 | -121.3203 | WDRM v3 | 0 | 1658 | 0 | 0 | 404 | 0 | Tier 3
35403554 | CWSP-SILVERADO 2105 167360&990552 PH1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 | 0 | 2174 | 0.0056116 | 0 | 398 | 0.0070204 | Tier 3
35403553 | CWSP-SILVERADO 2105 167360&990552 PH1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 | 0 | 2174 | 0.0056116 | 0 | 398 | 0.0070204 | Tier 3
35403552 | CWSP-SILVERADO 2105 167360&990552 PH1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 | 0 | 2174 | 0.0056116 | 0 | 398 | 0.0070204 | Tier 3
35403551 | CWSP-SILVERADO 2105 167360&990552 PH1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.25 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 | 0 | 2174 | 0.0056116 | 0 | 398 | 0.0070204 | Tier 3
35367518 | CWSP-SILVERADO 2105 167360&990552 PH1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2201 | 0 | 8.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 | 0 | 2174 | 0.0056116 | 0 | 398 | 0.0070204 | Tier 3
35392114 | FRRB PLACERVILLE 21061104 UG TL5 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0.84905 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 | 0 | 2131 | 0.0064469 | 0 | 397 | 0.0070659 | Tier 3
35355173 | PSPS PIT NO 3 2101CB PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52917 | 0 | 0.52917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35355171 | PSPS PIT NO 3 21011482 PH 2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55814 | 0 | 0.55814 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35404753 | CWSP - STANISLAUS 17021888 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35385890 | CWSP - STANISLAUS 1702 LR1888 PH1.4 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 1.383 | 0 | 1.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35385889 | CWSP - STANISLAUS 1702 LR1888 PH1.3 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.453 | 0 | 2.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35385888 | CWSP - STANISLAUS 1702 LR1888 PH1.2 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35376888 | CWSP - STANISLAUS 17021888 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.2701 | 0 | 7.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2701 | 0 | 7.2701 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35373705 | CWSP - STANISLAUS 1702 LR1888 PH 2 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.517 | 0 | 5.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35367520 | CWSP - STANISLAUS 1702 LR1888 PH1.1 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | 0 | 2386 | 0.0026855 | 0 | 379 | 0.0073524 | Tier 3
35373599 | CWSP - EL DORADO PH 2101 LR 63464 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.44 | 0 | 8.44 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 | 0 | 1138 | 0.05356 | 0 | 370 | 0.0074889 | Tier 2 & 3
35367467 | CWSP - EL DORADO PH 2101 LR 63464 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 | 0 | 1138 | 0.05356 | 0 | 370 | 0.0074889 | Tier 2
35392113 | FRRB FORESTHILL 110137238 UG TL4 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2197 | 0 | 1.2197 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 | 0 | 1434 | 0.031693 | 0 | 322 | 0.0088134 | Tier 3
35387916 | CWSP - FORESTHILL 110137238 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 | 0 | 1434 | 0.031693 | 0 | 322 | 0.0088134 | Tier 2 & 3
35397456 | CWSP - BRUNSWICK 110651486 PH 7.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.529 | 0 | 3.529 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35397455 | CWSP - BRUNSWICK 110651486 PH 7.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.312 | 0 | 1.312 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35397454 | CWSP - BRUNSWICK 110651486 PH 4.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778 | 0 | 2.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35397453 | CWSP - BRUNSWICK 110651486 PH 3.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.302 | 0 | 4.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 2 & 3
35397452 | CWSP - BRUNSWICK 110651486 PH 3.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.074 | 0 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 2 & 3
35326790 | PSPS - FLINT1101 CB & 40666 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 | 0 | 2980 | 1.76e-05 | 0 | 2071 | 0.00050684 | Tier 2
35396863 | CWSP - BRUNSWICK 110651486 PH 5.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.487 | 0 | 2.487 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396862 | CWSP - BRUNSWICK 110651486 PH 5.3 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.798 | 0 | 1.798 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396861 | CWSP - BRUNSWICK 110651486 PH 5.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.134 | 0 | 2.134 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396860 | CWSP - BRUNSWICK 110651486 PH 2.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396779 | CWSP - BRUNSWICK 110651486 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396778 | CWSP - BRUNSWICK 110651486 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396776 | CWSP - BRUNSWICK 110651486 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.79 | 0 | 2.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35396775 | CWSP - BRUNSWICK 110651486 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35390288 | CWSP - BRUNSWICK 110651486 - 13993 SEVEN | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | 0 | 0.12973 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12973 | 0 | 0.12973 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373596 | CWSP - BRUNSWICK 110651486 PH 8 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.09 | 0 | 8.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09 | 0 | 8.09 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373595 | CWSP - BRUNSWICK 110651486 PH 7.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.061 | 0 | 3.061 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373594 | CWSP - BRUNSWICK 110651486 PH 6.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 10.76 | 0 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373593 | CWSP - BRUNSWICK 110651486 PH 5.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 3.081 | 0 | 3.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373592 | CWSP - BRUNSWICK 110651486 PH 4.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.642 | 0 | 5.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35373590 | CWSP - BRUNSWICK 110651486 PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.268 | 0 | 2.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 2 & 3
35373589 | CWSP - BRUNSWICK 110651486 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1201 | 0 | 8.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35367462 | CWSP - BRUNSWICK 110651486 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.653 | 0 | 4.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 | 0 | 1788 | 0.014797 | 0 | 315 | 0.0088799 | Tier 3
35382936 | CWSP - UPPER LAKE 1101 LR 75370 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 | 0 | 705 | 0.11161 | 0 | 309 | 0.0089653 | Tier 2 & 3
35382934 | CWSP - UPPER LAKE 1101 LR 75370 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 | 0 | 705 | 0.11161 | 0 | 309 | 0.0089653 | Tier 2
35379289 | CWSP - PIKE CITY 11011730 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.74 | 0 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.74 | 0 | 6.74 | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 | 0 | 1400 | 0.033438 | 0 | 301 | 0.0093855 | Tier 3
35375453 | CWSP - PIKE CITY 11011730 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5875 | 0 | 10.5875 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 | 0 | 1400 | 0.033438 | 0 | 301 | 0.0093855 | Tier 3
35385801 | CWSP - NOTRE DAME 11042537 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.1 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 6.1 | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 | 0 | 1045 | 0.061762 | 0 | 290 | 0.0096296 | Tier 2 & 3
35401222 | CWSP - EL DORADO PH 210119612 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.3201 | 0 | 4.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3201 | 0 | 4.3201 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 | 0 | 2037 | 0.0083743 | 0 | 287 | 0.0097168 | Tier 3
35401221 | CWSP - EL DORADO PH 210119612 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1201 | 0 | 3.1201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 | 0 | 2037 | 0.0083743 | 0 | 287 | 0.0097168 | Tier 3
35401220 | CWSP - EL DORADO PH 210119612 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 | 0 | 2037 | 0.0083743 | 0 | 287 | 0.0097168 | Tier 3
35373598 | CWSP - EL DORADO PH 2101 19612 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.91 | 0 | 9.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.91 | 0 | 9.91 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 | 0 | 2037 | 0.0083743 | 0 | 287 | 0.0097168 | Tier 3
35367466 | CWSP - EL DORADO PH 2101 19612 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.1 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 4.1 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 | 0 | 2037 | 0.0083743 | 0 | 287 | 0.0097168 | Tier 3
35367475 | CWSP - EL DORADO 2102CB PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.8875 | 0 | 6.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8875 | 0 | 6.8875 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 | 0 | 2732 | 0.00051722 | 0 | 278 | 0.0099516 | Tier 3
35396572 | REMG 339, SWIFT 2110 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Livermore | Santa Clara | 37.3643 | -121.5789 | WDRM v3 | 0 | 1769 | 0.015532 | 0 | 276 | 0 | Tier 2
35374562 | CWSP - ORO FINO 110239154 PH 6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 2
35374561 | REMG 36 - ORO FINO 1102 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 2
35374459 | CWSP - ORO FINO 110239154 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 2
35374458 | REMG 510 - ORO FINO 1102 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 2 & 3
35374457 | CWSP - ORO FINO 110239154 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 3
35374456 | REMG 508 - ORO FINO 1102 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.19 | 0 | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 | 0 | 2575 | 0.0013923 | 0 | 273 | 0.010009 | Tier 3
35350039 | FRRB - BIG BEND 1102 884340 - B4 SM2 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 | 0 | 1288 | 0.040961 | 0 | 267 | 0.010152 | Tier 3
35373588 | CWSP - BRUNSWICK 110651484 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 | 0 | 1154 | 0.052212 | 0 | 266 | 0.010208 | Tier 2 & 3
35373587 | CWSP - BRUNSWICK 110651484 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7799 | 0 | 9.7799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 | 0 | 1154 | 0.052212 | 0 | 266 | 0.010208 | Tier 2 & 3
35367460 | CWSP - BRUNSWICK 110651484 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.41 | 0 | 12.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 | 0 | 12.41 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 | 0 | 1154 | 0.052212 | 0 | 266 | 0.010208 | Tier 2 & 3
35396567 | REMG 823 - FRENCHGULCH 1102,SHASTA BALLY | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Igo | Shasta | 40.6068 | -122.6544 | WDRM v3 | 0 | 2518 | 0.0016954 | 0 | 262 | 0 | Tier 2
35373706 | CWSP - WEST POINT 110113444 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.45 | 0 | 12.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.45 | 0 | 12.45 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 | 0 | 2293 | 0.0035258 | 0 | 256 | 0.01053 | Tier 3
35367522 | CWSP - WEST POINT 110113444 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.09 | 0 | 12.09 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 | 0 | 2293 | 0.0035258 | 0 | 256 | 0.01053 | Tier 3
35397961 | CWSP - PUEBLO 2103678 PH 4.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.161 | 0 | 1.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35397960 | CWSP - PUEBLO 2103678 PH 4.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396905 | CWSP - PUEBLO 2103678 PH 3.9 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.481 | 0 | 0.481 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396904 | CWSP - PUEBLO 2103678 PH 3.8 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.848 | 0 | 0.848 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396903 | CWSP - PUEBLO 2103678 PH 3.7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.957 | 0 | 1.957 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396902 | CWSP - PUEBLO 2103678 PH 3.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.575 | 0 | 2.575 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396900 | CWSP - PUEBLO 2103678 PH 3.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.418 | 0 | 1.418 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396878 | CWSP - PUEBLO 2103678 PH 3.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396877 | CWSP - PUEBLO 2103678 PH 3.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.262 | 0 | 4.262 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396876 | CWSP - PUEBLO 2103678 PH 3.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.725 | 0 | 1.725 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396875 | CWSP - PUEBLO 2103678 PH 2.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.705 | 0 | 2.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396874 | CWSP - PUEBLO 2103678 PH 2.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.965 | 0 | 2.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396871 | CWSP - PUEBLO 2103678 PH 2.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.703 | 0 | 0.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396870 | CWSP - PUEBLO 2103678 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.619 | 0 | 1.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35396869 | CWSP - PUEBLO 2103678 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.618 | 0 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35392777 | CWSP - PUEBLO 2103678 PH 1.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 1.8201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 2 & 3
35392776 | CWSP - PUEBLO 2103678 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35392775 | CWSP - PUEBLO 2103678 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35392774 | CWSP - PUEBLO 2103678 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35392773 | CWSP - PUEBLO 2103678 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 2 & 3
35373703 | CWSP - PUEBLO 2103678 PH 4.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35373637 | CWSP - PUEBLO 2103678 PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35373636 | CWSP - PUEBLO 2103678 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 3
35367513 | CWSP - PUEBLO 2103678 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 2.27 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 | 0 | 1224 | 0.046077 | 0 | 255 | 0.010549 | Tier 2
35373581 | CWSP - BRUNSWICK 11021010 PH 7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12992 | 6.7299 | 0 | 6.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35373580 | CWSP - BRUNSWICK 11021010 PH 6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.3799 | 0 | 8.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3799 | 0 | 8.3799 | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35373539 | CWSP - BRUNSWICK 11021010 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.31 | 0 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 9.31 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35373538 | CWSP - BRUNSWICK 11021010 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.24 | 0 | 8.24 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35373537 | CWSP - BRUNSWICK 11021010 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35373536 | CWSP - BRUNSWICK 11021010 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3 | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35367415 | CWSP - BRUNSWICK 11021010 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.01 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 | 0 | 1649 | 0.021168 | 0 | 234 | 0.011407 | Tier 3
35396760 | CWSP - PINE GROVE 110245292 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 | 0 | 2447 | 0.002235 | 0 | 233 | 0.011408 | Tier 3
35396699 | CWSP - PINE GROVE 110245292 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.3701 | 0 | 3.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3701 | 0 | 3.3701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 | 0 | 2447 | 0.002235 | 0 | 233 | 0.011408 | Tier 3
35396698 | CWSP - PINE GROVE 110245292 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 3.64 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 | 0 | 2447 | 0.002235 | 0 | 233 | 0.011408 | Tier 3
35367511 | CWSP - PINE GROVE 110245292 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7701 | 0 | 12.7701 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 | 0 | 2447 | 0.002235 | 0 | 233 | 0.011408 | Tier 2 & 3
35418371 | CWSP - STANISLAUS 170179826 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.675 | 0 | 12.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 | 0 | 2142 | 0.0062159 | 0 | 231 | 0.011425 | Tier 2
35376889 | CWSP - WEST POINT 1101 CB & 12256 PH2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7 | 0 | 13.7 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 | 0 | 1765 | 0.015736 | 0 | 218 | 0.011836 | Tier 3
35367526 | CWSP - WEST POINT 1101 CB & 12256 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 13.5701 | 0 | 13.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5701 | 0 | 13.5701 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 | 0 | 1765 | 0.015736 | 0 | 218 | 0.011836 | Tier 3
35312546 | PSPS - FLINT1101 CB & 40666 PH1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0131 | 0 | 1.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8933 | -121.0677 | WDRM v2 | 0 | 2980 | 1.76e-05 | 0 | 2071 | 0.00050684 | Tier 2
35396073 | FRRB - KANAKA 1101CB - K4 SM5 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5468 | -121.3424 | WDRM v3 | 0 | 1480 | 0 | 0 | 212 | 0 | Tier 2
35373051 | FRRB - KANAKA 1101CB - K2 SM3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35367500 | CWSP - MIDDLETOWN 1101614 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 | 0 | 2060 | 0.0076984 | 0 | 211 | 0.01209 | Tier 3
35404267 | CWSP - PINE GROVE 110213438 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.192 | 0 | 6.192 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 | 0 | 2136 | 0.0063999 | 0 | 204 | 0.012447 | Tier 2 & 3
35402642 | CWSP - PINE GROVE 110213438 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 | 0 | 2136 | 0.0063999 | 0 | 204 | 0 | Tier 2 & 3
35402641 | CWSP - PINE GROVE 110213438 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 | 0 | 2136 | 0.0063999 | 0 | 204 | 0.012447 | Tier 2 & 3
35373635 | CWSP - PINE GROVE 110213438 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.888 | 0 | 4.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 | 0 | 2136 | 0.0063999 | 0 | 204 | 0.012447 | Tier 2 & 3
35367510 | CWSP - PINE GROVE 110213438 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 | 0 | 2136 | 0.0063999 | 0 | 204 | 0.012447 | Tier 2 & 3
35403850 | CWSP - MARIPOSA 2101752630 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35403849 | CWSP - MARIPOSA 2101752630 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.31 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 4.31 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35403848 | CWSP - MARIPOSA 2101752630 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 0 | 3.81 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35403847 | CWSP - MARIPOSA 2101752630 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 0 | 4.39 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35078178 | STS-COND_IDLE_REMV-295 EAST RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1304 | -122.1182 | WDRM v2 | 0 | 2968 | 1.8516e-05 | 0 | 1102 | 0.0019468 | Tier 3
35221765 | STS-COND_IDLE_REMV - 1504 PINE DR ARNOLD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2531 | -120.3592 | WDRM v2 | 0 | 2810 | 0.00026318 | 0 | 98 | 0.01848 | Tier 3
31383326 | E CAP - SR 1107 & 1110 RECONFIGURE | Other | 06E | CONS | In-Construction | Y | 0.41856 | 0 | 0 | 0.41856 | 0.29867 | 0 | 0 | 0.29867 | 0.11989 | 0 | 0 | 0.11989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4388 | -122.6868 | WDRM v2 | 0 | 2799 | 0.00029462 | 0 | 7022 | 3.4973e-05 | Tier 2
74001486 | GRIZZLY PEAK BLVD BERKELEY R20A | Other | 30A | PEND | Permitting/Dependency | Y | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4576 | 0 | 1.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | WDRM v2 | 0 | 2792 | 0.00031068 | 0 | 2633 | 0.00025777 | Tier 2 & 3
35277146 | STS-COND_IDLE_REMV-29040 SNOWHITE RD | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne | 38.1406 | -120.0581 | WDRM v2 | 0 | 2788 | 0.00031402 | 0 | 922 | 0.0025407 | Tier 3
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 | WDRM v2 | 0 | 2738 | 0.0004909 | 0 | 482 | 0.0057466 | Tier 3
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 1.7748 | 0.053977 | 0 | 1.8288 | 1.483 | 0.053977 | 0 | 1.5369 | 0.29186 | 0 | 0 | 0.29186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 | 0 | 2712 | 0.00058985 | 0 | 1583 | 0.00088659 | Tier 3
35243446 | REMG 665 - OLEMA 1101, MT VISIONS PRNS | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 | 0 | 2644 | 0.00096084 | 0 | 2439 | 0.00032912 | Tier 2
35237937 | EQUIP ACCESS ISSUE 1025 HIDDEN VALLEY RD | Other | 2BP | UNSC | Ready for Construction | Y | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015341 | 0.18466 | 0.2 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Soquel | Santa Cruz | 37.0341 | -121.9738 | WDRM v2 | 0 | 2595 | 0.0012326 | 0 | 1319 | 0.0013011 | Tier 3
35342333 | FRRB-BIG BASIN 1101 UG1 SAN VICENTE | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 | 0 | 2579 | 0.0013814 | 0 | 1120 | 0.0018854 | Tier 3
35237593 | #CZUSCRUZ 425 SAN VICENTE TERRACE, SCRUZ | Fire Rebuild | 95F | CONS | In-Construction | Y | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.1011 | -122.1426 | WDRM v2 | 0 | 2579 | 0.0013814 | 0 | 1120 | 0.0018854 | Tier 3
35382933 | CWSP - MARIPOSA 2101752630 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.24 | 0 | 5.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.24 | 0 | 5.24 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35379382 | CWSP - MARIPOSA 2101752630 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 | 0 | 5.28 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 | 0 | 700 | 0.11205 | 0 | 199 | 0.012689 | Tier 2
35375184 | CWSP - LOS OSITOS 21037014 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 | 0 | N/A | N/A | 0 | 193 | 0.012994 | HFRA
35375183 | CWSP - LOS OSITOS 21037014 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 | 0 | N/A | N/A | 0 | 193 | 0.012994 | HFRA
35375182 | CWSP - LOS OSITOS 21037014 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 | 0 | N/A | N/A | 0 | 193 | 0.012994 | HFRA
35375181 | CWSP - LOS OSITOS 21037014 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 | 0 | N/A | N/A | 0 | 193 | 0.012994 | HFRA
35375180 | CWSP - LOS OSITOS 21037014 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.71 | 0 | 12.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 | 0 | N/A | N/A | 0 | 193 | 0.012994 | HFRA
35376642 | CWSP - BONNIE NOOK 1102CB PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.06 | 0 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.06 | 0 | 9.06 | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 | 0 | 2087 | 0.0071702 | 0 | 192 | 0.013013 | Tier 3
35376641 | CWSP - BONNIE NOOK 1102CB PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0.5 | 8.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 | 0 | 2087 | 0.0071702 | 0 | 192 | 0.013013 | Tier 3
35376640 | CWSP - BONNIE NOOK 1102CB PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 | 0 | 2087 | 0.0071702 | 0 | 192 | 0.013013 | Tier 3
35376556 | CWSP - BONNIE NOOK 1102CB & 1103CB PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0.32992 | 5.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 | 0 | 2087 | 0.0071702 | 0 | 192 | 0.013013 | Tier 3
35368118 | FRRB - BIG BEND 1102 CB - B1 SM1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6347 | -121.4543 | WDRM v3 | 0 | 865 | 0 | 0 | 187 | 0 | Tier 3
35378690 | CWSP - MIDDLETOWN 11014646 -PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.46 | 0 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.46 | 0 | 4.46 | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 | 0 | 328 | 0.19983 | 0 | 182 | 0.013549 | Tier 3
35378688 | CWSP - MIDDLETOWN 11014646 -PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.89 | 0 | 10.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.89 | 0 | 10.89 | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 | 0 | 328 | 0.19983 | 0 | 182 | 0.013549 | Tier 3
35378687 | CWSP - MIDDLETOWN 11014646 -PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.84 | 0 | 8.84 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 | 0 | 328 | 0.19983 | 0 | 182 | 0.013549 | Tier 3
35377437 | CWSP - MIDDLETOWN 11014646 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.19 | 0 | 7.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 | 0 | 328 | 0.19983 | 0 | 182 | 0.013549 | Tier 3
35403556 | CWSP - FORESTHILL 11011802 PH 3.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35403555 | CWSP - FORESTHILL 11011802 PH 3.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.172 | 0 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35399836 | CWSP - FORESTHILL 1101 1802 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.387 | 0 | 5.387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.387 | 0 | 5.387 | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35399835 | CWSP - FORESTHILL 1101 1802 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.342 | 0 | 2.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.342 | 0 | 2.342 | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35399834 | CWSP - FORESTHILL 1101 1802 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.952 | 0 | 3.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35373526 | CWSP - FORESTHILL 11011802 PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.785 | 0.91004 | 3.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35373525 | CWSP - FORESTHILL 1101 1802 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35367476 | CWSP - FORESTHILL 1101 1802 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.52 | 0 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 | 0 | 1865 | 0.012496 | 0 | 179 | 0.013637 | Tier 3
35382858 | CWSP - LOS OSITOS 21033010 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9701 | 0 | 7.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 | 0 | 1509 | 0.027281 | 0 | 178 | 0.013726 | Tier 2
35375099 | CWSP - LOS OSITOS 21033010 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 | 0 | 1509 | 0.027281 | 0 | 178 | 0.013726 | Tier 2
35375096 | CWSP - LOS OSITOS 21033010 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 | 0 | 1509 | 0.027281 | 0 | 178 | 0.013726 | Tier 2
35375095 | CWSP - LOS OSITOS 21033010 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 | 0 | 1509 | 0.027281 | 0 | 178 | 0.013726 | Tier 2
35375094 | CWSP - LOS OSITOS 21033010 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9799 | 0 | 8.9799 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 | 0 | 1509 | 0.027281 | 0 | 178 | 0.013726 | Tier 2
35373621 | CWSP - EL DORADO 210219542 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.31 | 0 | 7.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.31 | 0 | 7.31 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 | 0 | 2512 | 0.0017374 | 0 | 176 | 0.013848 | Tier 3
35367470 | CWSP - EL DORADO 210219542 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.71 | 0 | 6.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.71 | 0 | 6.71 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 | 0 | 2512 | 0.0017374 | 0 | 176 | 0.013848 | Tier 3
35383757 | CWSP - WEST POINT 11024788 PH5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 | 0 | 1206 | 0.047319 | 0 | 164 | 0.014654 | Tier 2 & 3
35383756 | CWSP - WEST POINT 11024788 PH4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 | 0 | 1206 | 0.047319 | 0 | 164 | 0.014654 | Tier 2 & 3
35383755 | CWSP - WEST POINT 11024788 PH3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 | 0 | 1206 | 0.047319 | 0 | 164 | 0.014654 | Tier 2 & 3
35383754 | CWSP - WEST POINT 11024788 PH2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 | 0 | 1206 | 0.047319 | 0 | 164 | 0.014654 | Tier 2 & 3
35383753 | CWSP - WEST POINT 11024788 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 0 | 9.1 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 | 0 | 1206 | 0.047319 | 0 | 164 | 0.014654 | Tier 2
35373535 | CWSP - ORO FINO 1101CB PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 | 0 | 2289 | 0.0035789 | 0 | 158 | 0.015008 | Tier 3
35373534 | CWSP - ORO FINO 1101CB PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5701 | 0 | 5.5701 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 | 0 | 2289 | 0.0035789 | 0 | 158 | 0.015008 | Tier 3
35367503 | CWSP - ORO FINO 1101CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 0 | 7.75 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 | 0 | 2289 | 0.0035789 | 0 | 158 | 0.015008 | Tier 3
35374203 | CWSP - NOTRE DAME 1104176446 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6299 | 0 | 10.6299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 | 0 | 73 | 0.37815 | 0 | 155 | 0.015172 | Tier 2 & 3
35402643 | CWSP - PINE GROVE 11013166 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.4561 | 0 | 2.4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4561 | 0 | 2.4561 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 | 0 | 1764 | 0.015763 | 0 | 147 | 0.015597 | Tier 2
35396761 | CWSP - PINE GROVE 11013166 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 0 | 4.64 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 | 0 | 1764 | 0.015763 | 0 | 147 | 0.015597 | Tier 2
35373707 | CWSP - PINE GROVE 11013166 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3299 | 0 | 7.3299 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 | 0 | 1764 | 0.015763 | 0 | 147 | 0.015597 | Tier 2
35372460 | CWSP - PINE GROVE 11013166 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.4299 | 0 | 7.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4299 | 0 | 7.4299 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 | 0 | 1764 | 0.015763 | 0 | 147 | 0.015597 | Tier 2
35376305 | FRRB - MARIPOSA 210110170 TL-10 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | 0 | 1809 | 0.014293 | 0 | 137 | 0.015939 | Tier 3
35374863 | FRRB - MARIPOSA 21019400 TL-4 INSTALL | Fire Rebuild | 08W | ADER | Estimating | Y | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 | 0 | 1809 | 0.014293 | 0 | 137 | 0.015939 | Tier 2
35367515 | CWSP - SALT SPRINGS 210297924 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.6799 | 0 | 6.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6799 | 0 | 6.6799 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 | 0 | 2620 | 0.0010653 | 0 | 133 | 0.016045 | Tier 3
35375515 | CWSP - APPLE HILL 2102836878 PH 7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2
35375514 | CWSP - APPLE HILL 2102836878 PH 6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2 & 3
35375513 | CWSP - APPLE HILL 2102836878 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2 & 3
35375512 | CWSP - APPLE HILL 2102836878 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2 & 3
35375511 | CWSP - APPLE HILL 2102836878 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 3
35375510 | CWSP - APPLE HILL 2102836878 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2 & 3
35375509 | CWSP - APPLE HILL 2102836878 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 | 0 | 644 | 0.12006 | 0 | 132 | 0.01606 | Tier 2 & 3
35404716 | CWSP - PINE GROVE 11026080 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 | 0 | 1271 | 0.042249 | 0 | 131 | 0.016072 | Tier 2
35404715 | CWSP - PINE GROVE 11026080 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 | 0 | 1271 | 0.042249 | 0 | 131 | 0.016072 | Tier 2
35401013 | CWSP MARIPOSA 210110240 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35401012 | CWSP MARIPOSA 210110240 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35401011 | CWSP MARIPOSA 210110240 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35397963 | CWSP MARIPOSA 210110240 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35397962 | CWSP MARIPOSA 210110240 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35382932 | CWSP MARIPOSA 210110240 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35379383 | CWSP MARIPOSA 210110240 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.74 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35375721 | FRRB - MARIPOSA 21019400 ML-6 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71004 | 0 | 0.71004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 3
35374681 | FRRB - MARIPOSA 21019400 ML-2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 | 0 | 679 | 0.11431 | 0 | 126 | 0.016323 | Tier 2 & 3
35373529 | CWSP - APPLE HILL 110413512 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 | 0 | 1284 | 0.041392 | 0 | 124 | 0.016427 | Tier 3
35373528 | CWSP - APPLE HILL 110413512 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 | 0 | 1284 | 0.041392 | 0 | 124 | 0.016427 | Tier 3
35373527 | CWSP - APPLE HILL 110413512 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 | 0 | 1284 | 0.041392 | 0 | 124 | 0.016427 | Tier 2 & 3
35367412 | CWSP - APPLE HILL 110413512 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.19 | 0 | 8.19 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 | 0 | 1284 | 0.041392 | 0 | 124 | 0.016427 | Tier 2 & 3
35396570 | REMG 432 - PEORIA 1701, TBD | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | La Grange | Tuolumne | 37.7952 | -120.2836 | WDRM v3 | 0 | 780 | 0.09692 | 0 | 122 | 0 | Tier 2
35374059 | CWSP - ELECTRA 1101L1697 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6701 | 0.87992 | 6.55 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 | 0 | 2349 | 0.0030208 | 0 | 118 | 0.016781 | Tier 2
35377525 | CWSP - PIKE CITY 1101CB PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.9701 | 0 | 6.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701 | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 | 0 | 1484 | 0.029034 | 0 | 116 | 0.016874 | Tier 3
35375450 | CWSP - PIKE CITY 1101CB PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.66 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66 | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 | 0 | 1484 | 0.029034 | 0 | 116 | 0.016874 | Tier 3
35375449 | CWSP - PIKE CITY 1101CB PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.85 | 0 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 10.85 | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 | 0 | 1484 | 0.029034 | 0 | 116 | 0.016874 | Tier 3
35379381 | CWSP - CLAYTON 2212681608 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.4 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 10.4 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 | 0 | 400 | 0.18021 | 0 | 115 | 0.016899 | Tier 2 & 3
35396911 | CWSP - FORESTHILL 110150486 - PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.13 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35396910 | CWSP - FORESTHILL 110150486 - PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35396909 | CWSP - FORESTHILL 110150486 - PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35396908 | CWSP - FORESTHILL 110150486 - PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35373533 | CWSP - FORESTHILL 110150486 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35367478 | CWSP - FORESTHILL 110150486 - PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 | 0 | 2270 | 0.0037622 | 0 | 114 | 0.01695 | Tier 3
35383305 | CWSP - WEST POINT 11014706 PH2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.99 | 0 | 4.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.99 | 0 | 4.99 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 | 0 | 2468 | 0.0020959 | 0 | 107 | 0.017455 | Tier 3
35367524 | CWSP WEST POINT 1101 LR4706 PH1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 14.3201 | 0 | 14.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3201 | 0 | 14.3201 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 | 0 | 2468 | 0.0020959 | 0 | 107 | 0.017455 | Tier 3
35373597 | CWSP - CALISTOGA 110143924 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.0201 | 0 | 5.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0201 | 0 | 5.0201 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 | 0 | 1005 | 0.066852 | 0 | 105 | 0.017566 | Tier 3
35367464 | CWSP - CALISTOGA 110143924 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.0299 | 0 | 9.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0299 | 0 | 9.0299 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 | 0 | 1005 | 0.066852 | 0 | 105 | 0.017566 | Tier 3
35404726 | CWSP - SILVERADO 210478268 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35404355 | CWSP - SILVERADO 210478268 PH 1.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35404354 | CWSP - SILVERADO 210478268 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35404353 | CWSP - SILVERADO 210478268 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35404352 | CWSP - SILVERADO 210478268 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35404351 | CWSP - SILVERADO 210478268 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35373704 | CWSP - SILVERADO 210478268 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35367516 | CWSP - SILVERADO 210478268 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 | 0 | 1254 | 0.043133 | 0 | 101 | 0.018153 | Tier 3
35362666 | CWSP - CLAYTON 2212614950 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 | 0 | 2561 | 0.0014894 | 0 | 100 | 0.018211 | Tier 2 & 3
35409203 | CWSP - MIDDLETOWN 1101433160 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 | 0 | 314 | 0.20636 | 0 | 99 | 0.018456 | Tier 2 & 3
35418379 | CWSP - STANISLAUS 170237278 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4875 | 0 | 8.4875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 | 0 | 2810 | 0.00026318 | 0 | 98 | 0.01848 | Tier 3
35417148 | CWSP - Foresthill 1102 2106 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.56 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.56 | 0 | 8.56 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 | 0 | 1301 | 0.040196 | 0 | 97 | 0.018495 | Tier 3
35417144 | CWSP - Foresthill 1102 2106 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.7 | 0 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 0 | 10.7 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 | 0 | 1301 | 0.040196 | 0 | 97 | 0.018495 | Tier 3
35417117 | CWSP - Foresthill 1102 2106 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.04 | 0 | 6.04 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 | 0 | 1301 | 0.040196 | 0 | 97 | 0.018495 | Tier 3
35417110 | CWSP - Foresthill 1102 2106 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.57 | 0 | 9.57 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 | 0 | 1301 | 0.040196 | 0 | 97 | 0.018495 | Tier 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.975 | 0 | 8.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.975 | 0 | 8.975 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35362685 | CWSP - STANISLAUS 1701 CB PH1.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.42708 | 0 | 0 | 0.42708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42708 | 0 | 0 | 0.42708 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.178 | -120.3801 | WDRM v3 | 0 | 56 | 0 | 0 | 95 | 0 | Tier 2
35372463 | CWSP - ANTLER 1101CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0.020076 | 1.99 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020076 | 1.99 | 0 | 2.01 | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 | 0 | 2207 | 0.0049349 | 0 | 94 | 0.0187 | Tier 2
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9 | 0 | 10.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 | 0 | 2022 | 0.0086414 | 0 | 93 | 0.018723 | Tier 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 | 0 | 2022 | 0.0086414 | 0 | 93 | 0.018723 | Tier 3
35395931 | REMG - ANTLER 11011520 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.9225 | -122.4132 | WDRM v3 | 0 | 2407 | 0.002519 | 0 | 91 | 0 | Tier 2
35395930 | CWSP - ANTLER 11011520 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.369 | 0 | 0.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.369 | 0 | 0.369 | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 | 0 | 2407 | 0.002519 | 0 | 91 | 0.018782 | Tier 2
35395929 | CWSP - ANTLER 11011520 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.057 | 0 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057 | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 | 0 | 2407 | 0.002519 | 0 | 91 | 0.018782 | Tier 2
35395928 | CWSP - ANTLER 11011520 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.937 | 0 | 1.937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.937 | 0 | 1.937 | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 | 0 | 2407 | 0.002519 | 0 | 91 | 0.018782 | Tier 2
35372464 | CWSP - ANTLER 11011520 PH1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.553 | 0 | 6.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.553 | 0 | 6.553 | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 | 0 | 2407 | 0.002519 | 0 | 91 | 0.018782 | Tier 2
35418356 | CWSP - SILVERADO 2105900104 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 | 0 | 2351 | 0.0030112 | 0 | 90 | 0.018786 | Tier 3
35418366 | CWSP - SHADY GLEN 110248894 PH2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.062 | 0 | 6.062 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 | 0 | 1378 | 0.034658 | 0 | 89 | 0.018876 | Tier 3
35418361 | CWSP - SHADY GLEN 110248894 PH1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.601 | 0 | 6.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.601 | 0 | 6.601 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 | 0 | 1378 | 0.034658 | 0 | 89 | 0.018876 | Tier 3
35376559 | CWSP - SILVERADO 2105658898 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 | 0 | 1361 | 0.035763 | 0 | 87 | 0.018978 | Tier 3
35376558 | CWSP - SILVERADO 2105658898 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.25 | 0 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 0 | 10.25 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 | 0 | 1361 | 0.035763 | 0 | 87 | 0.018978 | Tier 3
35396569 | REMG 841 - KESWICK 1101, WSKYTWN ENV SCH | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.5822 | -122.5413 | WDRM v3 | 0 | 1135 | 0.053968 | 0 | 83 | 0 | Tier 2
35396568 | REMG 840 - KESWICK 1101, BRANDY CRK BEAC | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | French Gulch | Shasta | 40.616 | -122.5718 | WDRM v3 | 0 | 1135 | 0.053968 | 0 | 83 | 0 | Tier 2
35373620 | PSPS - EL DORADO PH 2101 LR 668674 PH2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 | 0 | 2250 | 0.0041406 | 0 | 81 | 0.019264 | Tier 3
35367468 | PSPS - EL DORADO PH 2101 LR 668674 PH1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 0 | 6.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 | 0 | 2250 | 0.0041406 | 0 | 81 | 0.019264 | Tier 3
35383758 | CWSP - WEST POINT 11021341 PH1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8 | 0 | 10.8 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 | 0 | 2247 | 0.0041901 | 0 | 80 | 0.019265 | Tier 3
35409211 | CWSP - SHADY GLEN 110132726 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 | 0 | 2201 | 0.00506 | 0 | 71 | 0.02023 | Tier 2
35409205 | CWSP - SHADY GLEN 110132726 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 15.2 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2 | 0 | 15.2 | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 | 0 | 2201 | 0.00506 | 0 | 71 | 0.02023 | Tier 2
35391723 | CWSP - PLACERVILLE 210611132 PH 6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 3
35391722 | CWSP - PLACERVILLE 210611132 PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 3
35391721 | CWSP - PLACERVILLE 210611132 PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 3
35391473 | CWSP - PLACERVILLE 210611132 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 2
35391472 | CWSP - PLACERVILLE 210611132 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0799 | 0 | 10.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 2 & 3
35391471 | CWSP - PLACERVILLE 210611132 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7201 | 0 | 10.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 2 & 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.788 | 0 | 8.788 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 | 0 | 1412 | 0.032657 | 0 | 66 | 0.02064 | Tier 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 | 0 | 1412 | 0.032657 | 0 | 66 | 0.02064 | Tier 3
35409217 | CWSP - OREGON TRAIL 11021584 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.7 | 0 | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 0 | 9.7 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 | 0 | 1773 | 0.015387 | 0 | 64 | 0.0208 | Tier 2
35409215 | CWSP - OREGON TRAIL 11021584 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.1 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 5.1 | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 | 0 | 1773 | 0.015387 | 0 | 64 | 0.0208 | Tier 2
35373532 | CWSP - APPLE HILL 21027502 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4701 | 0 | 8.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 | 0 | 1505 | 0.027532 | 0 | 63 | 0.020812 | Tier 3
35373530 | CWSP - APPLE HILL 21027502 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 15.51 | 0 | 15.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.51 | 0 | 15.51 | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 | 0 | 1505 | 0.027532 | 0 | 63 | 0.020812 | Tier 3
35367414 | CWSP - APPLE HILL 21027502 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 | 0 | 1505 | 0.027532 | 0 | 63 | 0.020812 | Tier 2 & 3
35404349 | CWSP - ELECTRA 1101 LR7104 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.47 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 | 0 | 1548 | 0.025302 | 0 | 62 | 0.020861 | Tier 2
35376890 | CWSP - ELECTRA 11017104 PH2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.09 | 0 | 7.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.09 | 0 | 7.09 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 | 0 | 1548 | 0.025302 | 0 | 62 | 0.020861 | Tier 2
35372462 | CWSP - ELECTRA 1101 LR7104 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0.019886 | 4.85 | 0 | 4.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 | 0 | 1548 | 0.025302 | 0 | 62 | 0.020861 | Tier 2
35373628 | CWSP - ORO FINO 110276008 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.7299 | 0 | 8.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7299 | 0 | 8.7299 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 | 0 | 2763 | 0.000401 | 0 | 61 | 0.020869 | Tier 3
35367504 | CWSP - ORO FINO 110276008 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.35 | 0 | 9.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 0 | 9.35 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 | 0 | 2763 | 0.000401 | 0 | 61 | 0.020869 | Tier 3
35418375 | CWSP - STANISLAUS 17026028 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3875 | 0 | 10.3875 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 | 0 | 2670 | 0.0008147 | 0 | 60 | 0.021109 | Tier 3
35385804 | CWSP - SILVERADO 2104 LR 632 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 | 0 | 792 | 0.094959 | 0 | 59 | 0.021383 | Tier 3
35385803 | CWSP - SILVERADO 2104 LR 632 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.29 | 0 | 11.29 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 | 0 | 792 | 0.094959 | 0 | 59 | 0.021383 | Tier 3
35418305 | CWSP - PLACERVILLE 2106935216 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 | 0 | 904 | 0.079474 | 0 | 58 | 0.021398 | Tier 3
35418255 | CWSP - PLACERVILLE 2106935216 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 | 0 | 904 | 0.079474 | 0 | 58 | 0.021398 | Tier 3
35417127 | CWSP - PLACERVILLE 2106935216 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0 | 4.9 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 | 0 | 904 | 0.079474 | 0 | 58 | 0.021398 | Tier 3
35364784 | CWSP - SYCAMORE CREEK 11112268 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.1701 | 0 | 7.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1701 | 0 | 7.1701 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 | 0 | 2537 | 0.0016039 | 0 | 57 | 0.021521 | Tier 3
35363720 | CWSP - SYCAMORE CREEK 11112268 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.59 | 0 | 9.59 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 | 0 | 2537 | 0.0016039 | 0 | 57 | 0.021521 | Tier 3
35363559 | CWSP - SYCAMORE CREEK 11112268 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0 | 10.34 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 | 0 | 2537 | 0.0016039 | 0 | 57 | 0.021521 | Tier 3
35409202 | CWSP - MIDDLETOWN 11011314 PH1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 | 0 | 915 | 0.078235 | 0 | 56 | 0.021686 | Tier 2 & 3
35375452 | CWSP - PIKE CITY 11011720 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9201 | 0 | 6.9201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 | 0 | 1710 | 0.017864 | 0 | 52 | 0.02211 | Tier 3
35374570 | CWSP - NARROWS 2102CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.2799 | 0 | 7.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2799 | 0 | 7.2799 | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 | 0 | 658 | 0.11807 | 0 | 46 | 0.022999 | Tier 2
35374569 | CWSP - BUCKS CREEK 1102CB - BELDEN | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35374567 | CWSP - BUCKS CREEK 1102CB - RODGERS FLAT | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35374566 | CWSP - BUCKS CREEK 1102CB - ROCK CREST | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2
35374564 | CWSP - BUCKS CREEK 1102CB PH 2 N/O HWY 7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.79 | 1.76 | 8.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.79 | 1.76 | 8.55 | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2
35374563 | CWSP - BUCKS CREEK 1102CB PH 1 N/O HWY 7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 7.21 | 0 | 7.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | 7.21 | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2
35374443 | CWSP - ALLEGHANY 1102CB NEVADA PH 5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.7701 | 0 | 6.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7701 | 0 | 6.7701 | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35374208 | CWSP - ALLEGHANY 1102CB NEVADA PH 4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.89 | 0 | 4.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.89 | 0 | 4.89 | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35374206 | CWSP - ALLEGHANY 1102CB NEVADA PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.69 | 0 | 9.69 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35374205 | CWSP - ALLEGHANY 1102CB SIERRA PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.24 | 0 | 6.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.24 | 0 | 6.24 | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35374204 | CWSP - ALLEGHANY 1102CB SIERRA PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.7201 | 0 | 6.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7201 | 0 | 6.7201 | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35377520 | CWSP - MIDDLETOWN 1101171414 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 | 0 | 328 | 0.19983 | 0 | 38 | 0.024501 | Tier 3
35374202 | CWSP - NOTRE DAME 11042028 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.6701 | 0 | 4.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6701 | 0 | 4.6701 | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 | 0 | 1043 | 0.062015 | 0 | 37 | 0.024521 | Tier 3
35374200 | CWSP - NOTRE DAME 11042028 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.04 | 0 | 8.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.04 | 0 | 8.04 | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 | 0 | 1043 | 0.062015 | 0 | 37 | 0.024521 | Tier 3
35385806 | CWSP - SILVERADO 2104 LR 515946 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 6.69 | 0 | 6.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.69 | 0 | 6.69 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 | 0 | 1235 | 0.044601 | 0 | 33 | 0.025445 | Tier 3
35385805 | CWSP - SILVERADO 2104 LR 515946 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.74 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74 | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 | 0 | 1235 | 0.044601 | 0 | 33 | 0.025445 | Tier 3
TBD | 0 | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1375 | 0 | 15.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 | 0 | 178 | 0.2712 | 0 | 32 | 0.025831 | Tier 3
35409213 | CWSP - APPLE HILL 1104CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7299 | 0 | 4.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 | 0 | 1422 | 0.032289 | 0 | 30 | 0.025967 | Tier 2
35367335 | CWSP - BONNIE NOOK 1101CB PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7201 | 0.97992 | 10.7 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 | 0 | 1526 | 0.026396 | 0 | 20 | 0.02949 | Tier 3
35365064 | CWSP - BONNIE NOOK 1101CB PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.34 | 0.22992 | 10.5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.34 | 0.22992 | 10.5699 | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 | 0 | 1526 | 0.026396 | 0 | 20 | 0.02949 | Tier 3
35373634 | CWSP - ORO FINO 11022090 PH 3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.4299 | 0 | 4.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299 | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 | 0 | 2451 | 0.0021922 | 0 | 17 | 0.031702 | Tier 3
35373632 | CWSP - ORO FINO 11022090 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 10.2299 | 0 | 10.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2299 | 0 | 10.2299 | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 | 0 | 2451 | 0.0021922 | 0 | 17 | 0.031702 | Tier 3
35367508 | CWSP - ORO FINO 11022090 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 5.94 | 0 | 5.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0 | 5.94 | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 | 0 | 2451 | 0.0021922 | 0 | 17 | 0.031702 | Tier 3
35367507 | CWSP - ORO FINO 1102CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 | 0 | 2451 | 0.0021922 | 0 | 17 | 0.031702 | Tier 3
35235158 | #CZUSCRUZ 2151 PINE FLAT RD, SCRUZ | Fire Rebuild | 95F | FICL | In-Construction | Y | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0.030871 | 0 | 0 | 0.030871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Felton | Santa Cruz | 37.0448 | -122.0673 | WDRM v2 | 0 | 2539 | 0.0016007 | 0 | 903 | 0.0026122 | Tier 3
35211671 | DR~STS-COND_IDLE_REMV-1120 NATUREWOOD DR | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83769 | 0.83769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0289 | -121.0036 | WDRM v2 | 0 | 2536 | 0.0016155 | 0 | 1432 | 0.0011018 | Tier 2
35244167 | DR-COND_IDLE_REMV-WINCHESTER DR | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22519 | 0.22519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Meadow Vista | Placer | 38.9969 | -121.0593 | WDRM v2 | 0 | 2500 | 0.001823 | 0 | 1766 | 0.00071024 | Tier 2
35225253 | STS-COND_IDLE_REMV-214 TABERNACLE DRIVE | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 37.0631 | -122.0333 | WDRM v2 | 0 | 2474 | 0.0020379 | 0 | 1225 | 0.0015415 | Tier 3
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 3.4441 | 0 | 0 | 3.4441 | 3.3188 | 0 | 0 | 3.3188 | 0.12538 | 0 | 0 | 0.12538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1332 | -122.1257 | WDRM v2 | 0 | 2456 | 0.0021702 | 0 | 1113 | 0.0019056 | Tier 3
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 | 0 | 2435 | 0.002283 | 0 | 1105 | 0.0019396 | Tier 3
35225011 | STS-COND_IDLE_REMV - AT 1580 PRESTON ST | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Cambria | San Luis Obispo | 35.5452 | -121.0718 | WDRM v2 | 0 | 2433 | 0.0023119 | 0 | 2127 | 0.00047475 | Tier 2
35224941 | +STS-COND_IDLE_REMV-R/O 2PE 1PS/O #67 BL | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Morro Bay | San Luis Obispo | 35.3583 | -120.8253 | WDRM v2 | 0 | 2399 | 0.0025799 | 0 | 2247 | 0.00041125 | Tier 2
35225467 | STS-COND_IDLE_REMV - 1/P/S/O/587 AVOCADO | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Watsonville | Santa Cruz | 37.012 | -121.7958 | WDRM v2 | 0 | 2387 | 0.0026825 | 0 | 1464 | 0.0010495 | Tier 2
35243445 | REMG 49 - OLEMA 1101, HOME RANCH PRNS | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | WDRM v2 | 0 | 2360 | 0.0028981 | 0 | 3015 | 0.00012995 | Tier 2
35342460 | FRRB - BIG BASIN 1102 OH1 LODGE RD | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1741 | -122.1812 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35385802 | CWSP - CLAYTON 2212 LR 96224 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.6 | 0 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 0 | 9.6 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 | 0 | 377 | 0.18755 | 0 | 15 | 0.034099 | Tier 3
35376891 | CWSP - SILVERADO 2104646776 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.4 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 4.4 | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 | 0 | 1235 | 0.044601 | 0 | 14 | 0.034265 | Tier 3
35373708 | CWSP - ANTLER 11011384 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 3.73 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73 | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 | 0 | 2361 | 0.0028857 | 0 | 11 | 0.038738 | Tier 2
35372465 | CWSP - ANTLER 11011384 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 11.84 | 0 | 11.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.84 | 0 | 11.84 | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 | 0 | 2361 | 0.0028857 | 0 | 11 | 0.038738 | Tier 2
35372258 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 8.892 | 0 | 8.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.892 | 0 | 8.892 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 | 0 | 555 | 0.14347 | 0 | 10 | 0.039297 | Tier 2
35372257 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 9.808 | 0 | 9.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.808 | 0 | 9.808 | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 | 0 | 555 | 0.14347 | 0 | 10 | 0.039297 | Tier 2
35372461 | CWSP - TIGER CREEK 201 CB & 320746 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 | 0 | 1744 | 0.016801 | 0 | 8 | 0.040941 | Tier 2 & 3
35396763 | CWSP - PINE GROVE 1101CB PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | Y | 0 | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0.88 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 | 0 | 2334 | 0.0031502 | 0 | 6 | 0.047261 | Tier 2
35342338 | FRRB - BIG BASIN 1102 UG5 LITTLEBASIN CG | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 1.24 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.163 | -122.1902 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35396762 | CWSP - PINE GROVE 1101CB PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | Y | 0.07 | 2.91 | 0 | 2.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 2.91 | 0 | 2.98 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 | 0 | 2334 | 0.0031502 | 0 | 6 | 0.047261 | Tier 2
35342337 | FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1657 | -122.2231 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35342336 | FRRB - BIG BASIN 1102 UG2 CAMPGROUND | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1699 | -122.2026 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35342335 | FRRB - BIG BASIN 1102 UG3 HWY 236 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1672 | -122.2131 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35222036 | CZUSCRUZ 21600 BIG BASIN, BOULDER CRK | Fire Rebuild | 95F | PEND | Permitting/Dependency | Y | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0.52462 | 0 | 0 | 0.52462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1676 | -122.2 | WDRM v2 | 0 | 2359 | 0.0029066 | 0 | 1314 | 0.0013052 | Tier 3
35334541 | FRRB -BIG BASIN 1102 12758 P1S2 CYPRESS | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 | 0 | 2358 | 0.002947 | 0 | 897 | 0.0026407 | Tier 3
35250987 | X22: XCZUSCRUZ 185 KNOB HILL DR, BOULDER | Fire Rebuild | 95F | UNSC | Ready for Construction | Y | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0.088258 | 0 | 0 | 0.088258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1376 | -122.1453 | WDRM v2 | 0 | 2358 | 0.002947 | 0 | 897 | 0.0026407 | Tier 3
35275478 | STS-POLE_IDLE_REMV-23600 STATE HWY 9 | Idle Facilities | 2AF | DCNL | In-Construction | Y | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara | 37.2476 | -122.0791 | WDRM v2 | 0 | 2354 | 0.0029842 | 0 | 825 | 0.0029655 | Tier 3
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 2342 | 0.0030704 | 0 | 1533 | 0.00093756 | Tier 2
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 2342 | 0.0030704 | 0 | 1533 | 0.00093756 | Tier 2
35372259 | CWSP - PINE GROVE 1101CB | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84 | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 | 0 | 2334 | 0.0031502 | 0 | 6 | 0.047261 | Tier 2
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16004 | 0 | 0 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 2342 | 0.0030704 | 0 | 1533 | 0.00093756 | Tier 2
35325226 | PSPS PIT NO 3 21011482 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5241 | 0 | 3.5241 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9868 | -121.8481 | WDRM v2 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35325225 | PSPS PIT NO 3 21011482 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6396 | 0 | 3.6396 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9729 | -121.7814 | WDRM v2 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35325224 | PSPS PIT NO 3 2101CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.051 | 3.284 | 0 | 3.335 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 41.0088 | -121.7129 | WDRM v2 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35294730 | PSPS - PIT NO 3 21011482 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9066 | 0 | 2.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9685 | -121.8246 | WDRM v2 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35294729 | PSPS - PIT NO 3 21011482 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1407 | 0 | 3.1407 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7479 | WDRM v2 | 0 | 2320 | 0.0032735 | 0 | 394 | 0.0070854 | Tier 2
35128962 | RECOND HWY 20 - FTBRAGG 1102 | Other | 08J | UNSE | Scoping/Scoped | Y | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6288 | 0 | 0 | 1.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.4154 | -123.7771 | WDRM v2 | 0 | 2305 | 0.0033857 | 0 | 2316 | 0.00037958 | Tier 2
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 1.3718 | 0.093561 | 0 | 1.4653 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.099242 | 0.052841 | 0 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 | 0 | 2271 | 0.0037571 | 0 | 558 | 0.0048336 | Tier 3
35318074 | FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 | 0 | 2246 | 0.0041981 | 0 | 936 | 0.002497 | Tier 2
35321894 | FRRB - PT MORETTI 1101 12122 PH1 SM4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 | 0 | 2199 | 0.0051004 | 0 | 2216 | 0.00042654 | Tier 2
35297464 | FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 | 0 | 2199 | 0.0051004 | 0 | 2216 | 0.00042654 | Tier 2
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Base SH | 08W | CONS | In-Construction | Y | 1.8559 | 0 | 0 | 1.8559 | 0 | 0 | 0 | 0 | 0.01572 | 0 | 0 | 0.01572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.5056 | -122.9307 | WDRM v2 | 0 | 2192 | 0.0053427 | 0 | 1383 | 0.0011714 | Tier 3
35284810 | FRRB - HMB 1103 SM CO LR6012 PUMP HOUSE | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2086 | -122.3251 | WDRM v2 | 0 | 2186 | 0.0054078 | 0 | 2434 | 0.00033154 | Tier 2
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 | 0 | 2123 | 0.0065148 | 0 | 1979 | 0.00055552 | Tier 2
35244173 | DR-COND_IDLE_REMV-5260 GRANITE CREEK RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7888 | -120.9206 | WDRM v2 | 0 | 2116 | 0.0066099 | 0 | 237 | 0.011346 | Tier 2
35342339 | FRRB - BIG BASIN 1102 UG6 BB VINEYARD | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 | 0 | 2070 | 0.0075562 | 0 | 1413 | 0.0011281 | Tier 3
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 | 0 | 2055 | 0.0078448 | 0 | 2554 | 0.0002898 | Tier 2
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 2.5239 | 0 | 2.5239 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 | 0 | 2055 | 0.0078448 | 0 | 2554 | 0.0002898 | Tier 2
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90341 | 0 | 0.90341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 | 0 | 2048 | 0.007993 | 0 | 3020 | 0.00012812 | Tier 2
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0008 | 0 | 1.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 | 0 | 2048 | 0.007993 | 0 | 3020 | 0.00012812 | Tier 2
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 | 0 | 2048 | 0.007993 | 0 | 3020 | 0.00012812 | Tier 2
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8075 | -120.0935 | WDRM v2 | 0 | 2005 | 0.0089565 | 0 | 2299 | 0.00038767 | Tier 2
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Base SH | 08W | DOCC | In-Construction | Y | 2.3513 | 0.44621 | 0 | 2.7975 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 | 0 | 1946 | 0.0103 | 0 | 49 | 0.022482 | Tier 3
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 2.8136 | 0.37955 | 0 | 3.1932 | 2.2008 | 0.04072 | 0 | 2.2415 | 0.61288 | 0.33883 | 0 | 0.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 | 0 | 1946 | 0.0103 | 0 | 49 | 0.022482 | Tier 3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0.62519 | 2.2513 | 0 | 2.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 | 0 | 1946 | 0.0103 | 0 | 49 | 0.022482 | Tier 3
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 1.7455 | 0.57576 | 0 | 2.3212 | 1.6231 | 0 | 0 | 1.6231 | 0 | 0 | 0 | 0 | 0.12235 | 0.57576 | 0 | 0.69811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 | 0 | 1946 | 0.0103 | 0 | 49 | 0.022482 | Tier 3
35223241 | DR~STS-COND_IDLE_REMV-R/O 5500 ALPINE R | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Portola Valley | San Mateo | 37.3567 | -122.2181 | WDRM v2 | 0 | 1917 | 0.011065 | 0 | 630 | 0.0042054 | Tier 2
35320462 | PSPS - JAMESON 1105371694 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34508 | 0 | 0.34508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2642 | -122.1295 | WDRM v2 | 0 | 1848 | 0.012819 | 0 | 8953 | 0 | Tier 2
35120413 | DR-STS-COND_IDLE_REMV78TOYONDRIVE | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Fairfax | Marin | 37.9797 | -122.6039 | WDRM v2 | 0 | 1837 | 0.013281 | 0 | 1001 | 0.0022627 | Tier 3
35275962 | STS-COND_IDLE_REMV-1W/O 14508 WONDERLAND | Idle Facilities | 2BF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035227 | 0.035227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.7096 | -122.3366 | WDRM v2 | 0 | 1828 | 0.013687 | 0 | 838 | 0.002921 | Tier 2
35343741 | PSPS - DUNBAR 1101 440 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3371 | -122.4929 | WDRM v2 | 0 | 1827 | 0.01369 | 0 | 440 | 0.0063584 | Tier 2 & 3
35312542 | PSPS - DUNBAR 1101 440 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Glen Ellen | Sonoma | 38.3791 | -122.5192 | WDRM v2 | 0 | 1827 | 0.01369 | 0 | 440 | 0.0063584 | Tier 2 & 3
35294728 | PSPS - PIT NO 3 2101CB PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.893 | 0 | 1.893 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7478 | WDRM v2 | 0 | 1816 | 0.01407 | 0 | 326 | 0.0086689 | Tier 2
35211297 | DR~STS-COND_IDLE_REMV-2000 PONDEROSA WY | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21326 | 0.21326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.02 | -120.944 | WDRM v2 | 0 | 1801 | 0.014579 | 0 | 142 | 0.015811 | Tier 2
35221715 | STS-COND_IDLE_REMV-20599 KINGS CT | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Soulsbyville | Tuolumne | 37.9965 | -120.2635 | WDRM v2 | 0 | 1770 | 0.015509 | 0 | 2025 | 0.00052763 | Tier 2
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 | 0 | 1748 | 0.016728 | 0 | 521 | 0.0051671 | Tier 2
35145001 | PSPS - CLAYTON 2215 - CB | Base SH | 08W | CONS | In-Construction | Y | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091098 | 1.8845 | 0 | 1.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.931 | -121.9736 | WDRM v2 | 0 | 1739 | 0.016935 | 0 | 1812 | 0.0006705 | Tier 2 & 3
35121520 | NR7 OFAC_IDLE_REMV-LAKEVIEW RD-14LOC | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8122 | -122.3073 | WDRM v2 | 0 | 1722 | 0.017574 | 0 | 247 | 0.010915 | Tier 2
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 | 0 | 1703 | 0.018088 | 0 | 933 | 0.0025042 | Tier 2
35329012 | PSPS CLARK ROAD 1102 LR514690 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 | 0 | 1703 | 0.018088 | 0 | 1009 | 0.0022353 | Tier 2
35299633 | PSPS CLARK ROAD 1102 LR514690 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 | 0 | 1703 | 0.018088 | 0 | 1009 | 0.0022353 | Tier 2
35244150 | FT-COND_IDLE_REMV-D/P R/O 19182 GERMAN | Idle Facilities | 2AF | ESTS | Estimating | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.437 | -120.8154 | WDRM v2 | 0 | 1700 | 0.018204 | 0 | 41 | 0.023951 | Tier 3
35284023 | FRRB - DUNBAR 1101416 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1699 | 0 | 1.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 | WDRM v2 | 0 | 1684 | 0.019316 | 0 | 732 | 0.0035071 | Tier 3
35208054 | STS-COND_IDLE_REMV-BAYNE RD | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7975 | -120.8281 | WDRM v2 | 0 | 1666 | 0.020262 | 0 | 68 | 0.020612 | Tier 2
35295446 | FRRB - BUCKS CREEK 1103 CB PH2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 39.8957 | -121.2789 | WDRM v2 | 0 | 1658 | 0.020623 | 0 | 404 | 0.0069107 | Tier 2 & 3
35335235 | PSPS - SILVERADO 2104708 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5192 | -122.4719 | WDRM v2 | 0 | 1648 | 0.02118 | 0 | 619 | 0.0043024 | Tier 3
35280505 | HWY 299 SHASTA R20A | Other | 30A | ESTS | Estimating | Y | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5923 | -122.4836 | WDRM v2 | 0 | 1614 | 0.022607 | 0 | 43 | 0.023649 | Tier 3
35211659 | DR-COND_IDLE_REMV-14932 MOONSHINE RD | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.3894 | -121.0978 | WDRM v2 | 0 | 1590 | 0.023389 | 0 | 149 | 0.015567 | Tier 3
35224856 | BR-12-5A HWY 191 RELOCATION, PARB | Other | 10K | CONS | In-Construction | Y | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11136 | 2.4956 | 0 | 2.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | WDRM v2 | 0 | 1537 | 0.025842 | 0 | 362 | 0.0076725 | Tier 2 & 3
35329016 | PSPS CLARK ROAD 1102 LR47006 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 | 0 | 1535 | 0.025936 | 0 | 47 | 0.022808 | Tier 2
35299635 | PSPS CLARK ROAD 1102 LR47006 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 | 0 | 1535 | 0.025936 | 0 | 47 | 0.022808 | Tier 2
35245152 | FRRB - KANAKA 1101 - K4 PH 4.17 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48125 | 0 | 0 | 0.48125 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35245141 | FRRB - KANAKA 1101 - K4 PH 4.6 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35244699 | FRRB - KANAKA 1101 - K4 PH 4.4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.080114 | 0 | 0 | 0.080114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35244698 | FRRB - KANAKA 1101 - K4 PH 4.3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35236989 | FRRB - KANAKA 1101 - K2 PH2.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51136 | 0 | 0 | 0.51136 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35235704 | FRRB - KANAKA 1101 - K5 PH5.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18902 | 0 | 0 | 0.18902 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0 | 0.10909 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 | 0 | 1480 | 0.029281 | 0 | 212 | 0.01209 | Tier 3
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35320466 | CWSP - WILLOW CREEK 11032936 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Salyer | Trinity | 40.8669 | -123.5148 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297697 | FRRB - WILLOW CREEK 11032936 UG TL3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35281816 | FRRB - WILLOW CREEK 11032936 ML2OHBRIDGE | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0.046591 | 0 | 0 | 0.046591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | 0 | 1474 | 0.029513 | 0 | 938 | 0.0024804 | Tier 2
35264104 | DRSTS-OFAC_IDLE_REMV-7NE/O 15921 STATE H | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5593 | -120.8348 | WDRM v2 | 0 | 1446 | 0.030867 | 0 | 254 | 0.010591 | Tier 3
35150991 | T2-POLE_IDLE_REMV - GIBNEY DR MIRANDA*RM | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt | 40.2188 | -123.8212 | WDRM v2 | 0 | 1429 | 0.031951 | 0 | 2354 | 0.00036401 | Tier 2
35243441 | REMG 17 - CHALLENGE 1102, PONDEROSA WAY | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.483 | -121.2466 | WDRM v2 | 0 | 1428 | 0.032082 | 0 | 408 | 0.0068437 | Tier 2 & 3
35290901 | EP BICKFORD RANCH RD WATER TANK LINCOLN | Other | 16H | CONS | In-Construction | Y | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0.64432 | 0 | 0 | 0.64432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 0 | 0 | WDRM v2 | 0 | 1408 | 0.032911 | 0 | 2686 | 0.0002367 | Tier 2
35242865 | DR~STS-COND_IDLE_REMV-410 STAR HILL RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.4126 | -122.3299 | WDRM v2 | 0 | 1376 | 0.034933 | 0 | 1131 | 0.0018648 | Tier 3
35353435 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9081 | -120.8468 | WDRM v2 | 0 | 1363 | 0.035529 | 0 | 277 | 0.0099544 | Tier 3
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0.84962 | 0.52121 | 1.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 | 0 | 1363 | 0.035529 | 0 | 277 | 0.0099544 | Tier 3
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 | 0 | 1363 | 0.035529 | 0 | 277 | 0.0099544 | Tier 3
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 | 0 | 1322 | 0.038702 | 0 | 1064 | 0.0020497 | Tier 2
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 | 0 | 1322 | 0.038702 | 0 | 1064 | 0.0020497 | Tier 2
35145540 | PSPS - FROGTOWN 1702 - CB | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 | 0 | 1316 | 0.039234 | 0 | 1205 | 0.0016222 | Tier 3
35251360 | MIRABEL 1101 - RECONDUCTOR 3,338 FT | Other | 06E | PEND | Permitting/Dependency | Y | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0.34261 | 0 | 0 | 0.34261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Forestville | Sonoma | 38.4736 | -122.8979 | WDRM v2 | 0 | 1313 | 0.039363 | 0 | 1448 | 0.001078 | Tier 2
35243442 | REMG 130 - PIKE CITY 1102, TAHOE NF | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | North San Juan | Sierra | 39.4385 | -120.9959 | WDRM v2 | 0 | 1308 | 0.03956 | 0 | 162 | 0.0147 | Tier 3
35083699 | *CANC*STS-COND_IDLE_REMV-38113 PETERSON | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0361 | -119.3341 | WDRM v2 | 0 | 1302 | 0.040157 | 0 | 348 | 0.0080497 | Tier 3
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 SM | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | Fire Rebuild | 08W | DOCC | In-Construction | Y | 0 | 1.8256 | 0 | 1.8256 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 250 | 0.010796 | Tier 3
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 | 0 | 1299 | 0.040282 | 0 | 526 | 0.0051219 | Tier 3
35038684 | REMV IDLE 4 LOCS 48600 VALLEY DR LAY | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | Mendocino | 39.7297 | -123.5078 | WDRM v2 | 0 | 1293 | 0.040695 | 0 | 992 | 0.0022826 | Tier 2
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 1285 | 0.041237 | 0 | 2987 | 0.00013567 | Tier 2
35208094 | FT STS-TRAN_IDLE_REMV-2W/O6NW/O 7251 WIL | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.1679 | -124.0858 | WDRM v2 | 0 | 1237 | 0.044439 | 0 | 2057 | 0.00051421 | Tier 2
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 | 0 | 1172 | 0.050559 | 0 | 785 | 0.0031715 | Tier 2 & 3
35332870 | PSPS - CURTIS 1701 CB PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 | 0 | 1166 | 0.051116 | 0 | 1018 | 0.0021952 | Tier 2
35332868 | PSPS - CURTIS 1701 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 | 0 | 1166 | 0.051116 | 0 | 1018 | 0.0021952 | Tier 2
35312541 | PSPS - CURTIS 1701 CB PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 | 0 | 1166 | 0.051116 | 0 | 1018 | 0.0021952 | Tier 2
35283938 | CWSP - WOODSIDE 1101 FS 775939 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1939 | 0 | 1.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3845 | -122.2937 | WDRM v2 | 0 | 1145 | 0.05299 | 0 | 1026 | 0.0021738 | Tier 3
35399833 | PSPS - SAN LUIS OBISPO 1101 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 1.33 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2752 | -120.6435 | WDRM v2 | 0 | 1104 | 0.056447 | 0 | 1903 | 0.00059698 | Tier 2
35320444 | PSPS - SAN LUIS OBISPO 1101 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0.48 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2683 | -120.6383 | WDRM v2 | 0 | 1104 | 0.056447 | 0 | 1903 | 0.00059698 | Tier 2
35341551 | REMG 499 - PIT NO 7 1101 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.8417 | -122.0114 | WDRM v2 | 0 | 1055 | 0.060819 | 0 | 549 | 0.0049268 | Tier 2
35338402 | PSPS - PANORAMA 1101 CB PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 | 0 | 1038 | 0.062374 | 0 | 3890 | 5.6461e-05 | Tier 2
35320464 | PSPS - PANORAMA 1101 CB PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.070076 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 | 0 | 1038 | 0.062374 | 0 | 3890 | 5.6461e-05 | Tier 2
35244146 | FT-COND_IDLE_REMV-6935-6963 MORNING CAN | Idle Facilities | 2AF | MAPP | In-Construction | Y | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6211 | -120.7249 | WDRM v2 | 0 | 1035 | 0.06292 | 0 | 436 | 0.0063805 | Tier 2
35384087 | PSPS - CLARK ROAD 1102 LR514690 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0.47992 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6578 | -121.5657 | WDRM v2 | 0 | 1033 | 0.063106 | 0 | 711 | 0.0036217 | Tier 2
35329015 | REMG 794 - CLARK ROAD 1102 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6575 | -121.5646 | WDRM v2 | 0 | 1033 | 0.063106 | 0 | 711 | 0.0036217 | Tier 2
35329014 | PSPS CLARK ROAD 1102 LR514690 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 | 0 | 1033 | 0.063106 | 0 | 711 | 0.0036217 | Tier 2
35299634 | PSPS CLARK ROAD 1102 LR514690 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 | 0 | 1033 | 0.063106 | 0 | 711 | 0.0036217 | Tier 2
35277147 | STS-POLE_IDLE_REMV-GREELY HILL RD CO#423 | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40871 | 0.40871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | Mariposa | 37.7302 | -120.182 | WDRM v2 | 0 | 1019 | 0.065187 | 0 | 433 | 0.0064317 | Tier 2
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Base SH | 08W | CONS | In-Construction | Y | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0.13258 | 1.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | WDRM v2 | 0 | 999 | 0.067405 | 0 | 2578 | 0.0002828 | Tier 2
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 995 | 0.067786 | 0 | 2135 | 0.00047036 | Tier 2
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 995 | 0.067786 | 0 | 2135 | 0.00047036 | Tier 2
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 995 | 0.067786 | 0 | 2135 | 0.00047036 | Tier 2
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 995 | 0.067786 | 0 | 2135 | 0.00047036 | Tier 2
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 995 | 0.067786 | 0 | 2135 | 0.00047036 | Tier 2
35211643 | DR-STS-COND_IDLE_REMV-6 PLS W/O 11554 ON | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6201 | -122.4409 | WDRM v2 | 0 | 981 | 0.069495 | 0 | 957 | 0.0024201 | Tier 2
35343398 | PSPS - WYANDOTTE 1110 LR980944 PH1.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0.32008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5169 | -121.5161 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35343397 | PSPS - WYANDOTTE 1110 LR980944 PH1.9 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84 | 0 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5082 | -121.5038 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35343396 | PSPS - WYANDOTTE 1110 LR980944 PH1.8 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35343395 | PSPS - WYANDOTTE 1110 LR980944 PH1.7 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35343394 | PSPS - WYANDOTTE 1110 LR980944 PH1.6 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35331309 | REMG 801 - WYANDOTTE 1110, OROVILLE DAM | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5255 | -121.4817 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35331308 | PSPS WYANDOTTE 1110 LR980944 PH1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35331307 | PSPS WYANDOTTE 1110 LR980944 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35331306 | PSPS WYANDOTTE 1110 LR980944 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.67 | 0 | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5178 | -121.4854 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35312560 | PSPS WYANDOTTE 1110 LR980944 PH1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 | 0 | 976 | 0.070566 | 0 | 1779 | 0.00070123 | Tier 2
35254948 | X22: CWSP - VOLTA 11011596 - PH1.6 | Base SH | 08W | CONS | In-Construction | Y | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0.9803 | 0 | 0 | 0.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | 0 | 966 | 0.071922 | 0 | 281 | 0.0099219 | Tier 2
35254947 | CWSP - VOLTA 11011596 - PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0.263 | 0 | 0.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | 0 | 966 | 0.071922 | 0 | 281 | 0.0099219 | Tier 2
35254946 | X22: CWSP - VOLTA 11011596 - PH1.4 | Base SH | 08W | CONS | In-Construction | Y | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0.88277 | 0 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | 0 | 966 | 0.071922 | 0 | 281 | 0.0099219 | Tier 2
35254945 | CWSP - VOLTA 11011596 - PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | 0 | 966 | 0.071922 | 0 | 281 | 0.0099219 | Tier 2
35243453 | X22: CWSP-VOLTA-11011596-PH1 | Base SH | 08W | CONS | In-Construction | Y | 1.428 | 0 | 0 | 1.428 | 1.086 | 0 | 0 | 1.086 | 0.34205 | 0 | 0 | 0.34205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | 0 | 966 | 0.071922 | 0 | 281 | 0.0099219 | Tier 2
35227033 | PUEBLO 2102, DRY CREEK | Base SH | 08W | APPR | Estimating | Y | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4517 | 0 | 0 | 0.4517 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.433 | -122.4021 | WDRM v2 | 0 | 951 | 0.073389 | 0 | 338 | 0.0083787 | Tier 3
35224438 | #+STS-COND_IDLE_REMV-SUDDEN RANCH AT RR | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | Santa Barbara | 34.5386 | -120.5365 | WDRM v2 | 0 | 949 | 0.073569 | 0 | 2028 | 0.00052681 | Tier 2
35292758 | FRRB BIG MEADOWS 2101 CB PH1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0.055682 | 1.2858 | 0.094697 | 1.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35280493 | FRRB -BIG MEADOWS 21012260 UG TL 1.13 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0.12008 | 0.35 | 0 | 0.47008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35279985 | FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 3.115 | 0 | 3.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 | 0 | 916 | 0.077859 | 0 | 575 | 0.0046735 | Tier 2
35280498 | FRRB - CRESCENT MILLS 21012056 OH TL 1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 895 | 0.080308 | 0 | 854 | 0.0028532 | Tier 2
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | 0 | 895 | 0.080308 | 0 | 854 | 0.0028532 | Tier 2
35145458 | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.758 | -120.0408 | WDRM v2 | 0 | 882 | 0.08233 | 0 | 550 | 0.0049103 | Tier 2
35235674 | FRRB - BIG BEND 1102 - B1 PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0 | 0.1108 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 | 0 | 865 | 0.084888 | 0 | 187 | 0.013302 | Tier 3
35221620 | STS-COND_IDLE_REMV-12345 HERITAGE WAY | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SJ | Region 4 - Central Coast | Gilroy | Santa Clara | 37.0533 | -121.6625 | WDRM v2 | 0 | 854 | 0.085689 | 0 | 1052 | 0.0020756 | Tier 2
35297984 | REMG 368 - STILLWATER 1101 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.1201 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 1.1201 | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 | WDRM v2 | 0 | 851 | 0.085979 | 0 | 2266 | 0.00040165 | Tier 2
35190945 | EP 2951 HIGHWAY 4 MURPHYS WAGON TRAIL | Other | 10Q | CONS | In-Construction | Y | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 1.1169 | 0 | 0 | 1.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | Calaveras | 0 | 0 | WDRM v2 | 0 | 838 | 0.088153 | 0 | 1734 | 0.00073728 | Tier 2
35332718 | PEORIA 1705 RECONDUCTORING | Other | 06H | ESTS | Estimating | Y | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 | 1.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne | 37.8663 | -120.4293 | WDRM v2 | 0 | 835 | 0.088489 | 0 | 1778 | 0.00070132 | Tier 2
35204814 | DR-COND_IDLE_REMV-14820 FERN RD | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6759 | -121.971 | WDRM v2 | 0 | 820 | 0.09042 | 0 | 1536 | 0.00093567 | Tier 2 & 3
74010582 | GREEN VALLEY RD EL DORADO CNTY R20A | Other | 30A | PEND | Permitting/Dependency | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | WDRM v2 | 0 | 811 | 0.092281 | 0 | 1184 | 0.0016787 | Tier 2
35173857 | SILVERADO 2104_RECONDUCTOR NEAR FUSE 797 | Other | 06E | CONS | In-Construction | Y | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | Angwin | Napa | 38.5866 | -122.4424 | WDRM v2 | 0 | 792 | 0.094959 | 0 | 59 | 0.021383 | Tier 3
35211230 | DRCOND_IDLE_REMV-5726 EVERGLADE | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2454 | -121.3989 | WDRM v2 | 0 | 774 | 0.098287 | 0 | 3122 | 0.00010395 | Tier 2
35221249 | DR~STS-OFAC_IDLE_REMV - 1/N/O/AT 908 ORE | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5519 | -121.5068 | WDRM v2 | 0 | 771 | 0.098498 | 0 | 1281 | 0.0013786 | Tier 2
35217564 | DR-COND_IDLE_REMV - 1PWO 11188 TOWNSHIP | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Browns Valley | Yuba | 39.2864 | -121.3535 | WDRM v2 | 0 | 758 | 0.10087 | 0 | 2091 | 0.00049399 | Tier 2
35221659 | STS-COND_IDLE_REMV-1N/O 2W/O 10835 WATER | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15076 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Ione | Amador | 38.3665 | -120.9291 | WDRM v2 | 0 | 744 | 0.10338 | 0 | 2444 | 0.00032629 | Tier 2
35342151 | PSPS - JAMESON 1102 LR65516 1.9 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342150 | PSPS - JAMESON 1102 LR65516 1.8 | Base SH | 08W | UNSC | Ready for Construction | Y | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2521 | 4.2521 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2623 | -122.1638 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342148 | PSPS - JAMESON 1102 LR65516 1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342147 | PSPS - JAMESON 1102 LR65516 1.6 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342146 | PSPS - JAMESON 1102 LR65516 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 2.397 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342145 | PSPS - JAMESON 1102 LR65516 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342144 | PSPS - JAMESON 1102 LR65516 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 1.617 | 0 | 1.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35342143 | PSPS - JAMESON 1102 LR65516 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35320442 | PSPS - JAMESON 1102 LR65516 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 | 0 | 739 | 0.104 | 0 | 313 | 0.0089196 | Tier 2
35337015 | CWSP - JAMESON 1105 LR9472 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 | 0 | 724 | 0.10731 | 0 | 1928 | 0.00057842 | Tier 2
35337014 | CWSP - JAMESON 1105 LR9472 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0.82992 | 0.020076 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 | 0 | 724 | 0.10731 | 0 | 1928 | 0.00057842 | Tier 2
35337013 | CWSP - JAMESON 1105 LR9472 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28996 | 0 | 0 | 0.28996 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1517 | WDRM v2 | 0 | 724 | 0.10731 | 0 | 1928 | 0.00057842 | Tier 2
35320459 | CWSP - JAMESON 1105 LR9472 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0 | 0.97008 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.157 | WDRM v2 | 0 | 724 | 0.10731 | 0 | 1928 | 0.00057842 | Tier 2
35329011 | PSPS CLARK ROAD 1102 LR81296 PH 1.4 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 | 0 | 698 | 0.11218 | 0 | 1028 | 0.0021691 | Tier 2
35329010 | PSPS CLARK ROAD 1102 LR81296 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 2.814 | 0.020076 | 2.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 | 0 | 698 | 0.11218 | 0 | 1028 | 0.0021691 | Tier 2
35329009 | PSPS CLARK ROAD 1102 LR81296 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0.94091 | 0.020076 | 0.96098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 | 0 | 698 | 0.11218 | 0 | 1028 | 0.0021691 | Tier 2
35299631 | PSPS CLARK ROAD 1102 LR81296 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 | 0 | 698 | 0.11218 | 0 | 1028 | 0.0021691 | Tier 2
35342310 | PSPS - TEJON 11023751 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.357 | 0 | 1.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35342308 | PSPS - TEJON 11023751 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.997 | 0 | 2.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8868 | -118.9361 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35342307 | PSPS - TEJON 11023751 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.252 | 0 | 2.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.252 | 0 | 2.252 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8833 | -118.9271 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35335289 | PSPS - TEJON 1102 LR3751 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.5775 | 0 | 1.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5775 | 0 | 1.5775 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35335288 | PSPS - TEJON 1102 LR3751 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 3.6 | 0 | 4.9799 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9158 | -118.9258 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35321445 | PSPS - TEJON 11023751 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35312554 | PSPS - TEJON 1102 LR3751 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.9321 | -118.9283 | WDRM v2 | 0 | 691 | 0.11269 | 0 | 368 | 0.0075263 | Tier 2
35207962 | FT-COND_IDLE_REMV-13080 FERN RD EAST | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6587 | -121.8939 | WDRM v2 | 0 | 678 | 0.11449 | 0 | 1076 | 0.0020262 | Tier 2
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Base SH | 08W | CONS | In-Construction | Y | 1.0733 | 0 | 0 | 1.0733 | 0.2928 | 0 | 0 | 0.2928 | 0.78049 | 0 | 0 | 0.78049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.6824 | -120.8551 | WDRM v2 | 0 | 666 | 0.11621 | 0 | 775 | 0.0032085 | Tier 2
35339665 | CWSP - HORSESHOE 1101 LR50140 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 | 0 | 661 | 0.11734 | 0 | 2556 | 0.00028839 | Tier 2
35339664 | CWSP - HORSESHOE 1101 LR50140 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0.75208 | 0.17008 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 | 0 | 661 | 0.11734 | 0 | 2556 | 0.00028839 | Tier 2
35339663 | CWSP - HORSESHOE 1101 LR50140 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 | 0 | 661 | 0.11734 | 0 | 2556 | 0.00028839 | Tier 2
35320447 | CWSP - HORSESHOE 1101 LR50140 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 1.09 | 0.83996 | 0 | 1.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 | 0 | 661 | 0.11734 | 0 | 2556 | 0.00028839 | Tier 2
35335287 | PSPS - TEJON 1102 LR2455 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1799 | 0 | 2.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8466 | -118.8987 | WDRM v2 | 0 | 642 | 0.12034 | 0 | 72 | 0.020158 | Tier 2
35335286 | PSPS - TEJON 1102 LR2455 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.21 | 0 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8542 | -118.893 | WDRM v2 | 0 | 642 | 0.12034 | 0 | 72 | 0.020158 | Tier 2
35312553 | PSPS - TEJON 1102 LR2455 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8837 | WDRM v2 | 0 | 642 | 0.12034 | 0 | 72 | 0.020158 | Tier 2
35246501 | REMG 44-FULTON 1107, PEPPERWOOD PRESERVE | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0994 | 7.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5702 | -122.6772 | WDRM v2 | 0 | 637 | 0.12169 | 0 | 1034 | 0.0021304 | Tier 3
35149235 | 8/31-REMV IDLE 6 LOCS 13311 HWY 29 | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8612 | -122.6264 | WDRM v2 | 0 | 626 | 0.12376 | 0 | 582 | 0.0045905 | Tier 2
35274596 | CWSP MARIPOSA 2101 LR 309438 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2138 | 0 | 1.1187 | 2.3326 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4889 | -119.9738 | WDRM v2 | 0 | 605 | 0.12966 | 0 | 565 | 0.0047998 | Tier 2
35274595 | CWSP MARIPOSA 2101 LR 309438 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4983 | -119.9732 | WDRM v2 | 0 | 605 | 0.12966 | 0 | 565 | 0.0047998 | Tier 2
35250572 | CWSP - MARIPOSA 2101 LR 309438 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.953 | 0 | 0 | 1.953 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5026 | -119.9886 | WDRM v2 | 0 | 605 | 0.12966 | 0 | 565 | 0.0047998 | Tier 2
35317937 | CWSP HARTLEY 1101 LR336932 1.10 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0436 | -122.9704 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317936 | CWSP HARTLEY 1101 LR336932 1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0402 | -122.9674 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317935 | CWSP HARTLEY 1101 LR336932 1.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.53 | 0 | 0 | 1.53 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0405 | -122.9316 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317934 | CWSP HARTLEY 1101 LR336932 1.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.041 | -122.9443 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317932 | CWSP HARTLEY 1101 LR336932 1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.044 | -122.9654 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317931 | CWSP HARTLEY 1101 LR336932 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0439 | -122.9625 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317930 | CWSP HARTLEY 1101 LR336932 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0 | 0 | 1.19 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317929 | CWSP HARTLEY 1101 LR336932 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0441 | -122.9543 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35317928 | CWSP HARTLEY 1101 LR336932 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0406 | -122.9405 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35250574 | CWSP HARTLEY 1101 LR336932 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 | 0.73996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0512 | -122.9379 | WDRM v2 | 0 | 593 | 0.13303 | 0 | 1213 | 0.0015984 | Tier 2
35332866 | PSPS - JESSUP 1103 LR348657 PH 1.4 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 | 0 | 590 | 0.13388 | 0 | 2153 | 0.00046034 | Tier 2
35332864 | PSPS - JESSUP 1103 LR348657 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2585 | 0 | 0 | 1.2585 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5058 | -122.2644 | WDRM v2 | 0 | 590 | 0.13388 | 0 | 2901 | 0.00016206 | Tier 2
35332863 | PSPS - JESSUP 1103 LR348657 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22633 | 0 | 0 | 0.22633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4921 | -122.2838 | WDRM v2 | 0 | 590 | 0.13388 | 0 | 2901 | 0.00016206 | Tier 2
35312549 | PSPS - JESSUP 1103 LR348657 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 | 0 | 590 | 0.13388 | 0 | 2901 | 0.00016206 | Tier 2
35342318 | PSPS - TEJON 1102 LR732836 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.508 | 0 | 4.508 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8363 | -118.8637 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342317 | PSPS - TEJON 1102 LR732836 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.604 | 0 | 2.604 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8295 | -118.8723 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342316 | PSPS - TEJON 1102 LR732836 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.837 | -118.8663 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342315 | PSPS - TEJON 1102 LR732836 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8407 | -118.8677 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342314 | PSPS - TEJON 1102 LR732836 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.421 | 0 | 0.421 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8594 | -118.8797 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342313 | PSPS - TEJON 1102 LR732836 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.902 | 0 | 2.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8835 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342312 | PSPS - TEJON 1102 LR732836 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.591 | 0 | 1.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8726 | -118.8905 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35342311 | PSPS - TEJON 1102 LR732836 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.174 | 0 | 2.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8765 | -118.8926 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35320607 | PSPS - TEJON 1102 LR732836 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8129 | 0 | 2.8129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.846 | -118.872 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35312555 | PSPS - TEJON 1102 LR732836 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 | 0 | 583 | 0.1353 | 0 | 219 | 0.011818 | Tier 2
35364450 | PSPS - VOLTA 11011516 PH 1.17 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 1.496 | 0 | 0 | 1.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364448 | PSPS - VOLTA 11011516 PH 1.16 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2201 | 0 | 3.2201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364446 | PSPS - VOLTA 11011516 PH 1.15 | Base SH | 08W | ESTS | Estimating | Y | 0.057008 | 2.5381 | 0 | 2.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.057008 | 2.5381 | 0 | 2.5951 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364442 | PSPS - VOLTA 11011516 PH 1.14 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.621 | 0 | 4.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364440 | PSPS - VOLTA 11011516 PH 1.13 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364339 | PSPS - VOLTA 11011516 PH 1.12 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.746 | 0 | 2.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364337 | PSPS - VOLTA 11011516 PH 1.11 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5091 | 0 | 2.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364336 | PSPS - VOLTA 11011516 PH 1.10 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.8561 | 0 | 1.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8561 | 0 | 1.8561 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364334 | PSPS - VOLTA 11011516 PH 1.9 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1591 | 0 | 2.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364333 | PSPS - VOLTA 11011516 PH 1.8 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.8131 | 0 | 2.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35364332 | PSPS - VOLTA 11011516 PH 1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4159 | 0 | 2.4159 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35334468 | REMG 465 - VOLTA 1101 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.77 | 5.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3139 | -122.0706 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35334467 | PSPS - VOLTA 11011516 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.014 | 0.83295 | 2.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3305 | -122.0971 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35334466 | PSPS - VOLTA 11011516 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5951 | 1.5951 | 3.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3386 | -122.1218 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35334465 | PSPS - VOLTA 11011516 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.989 | 0 | 0 | 1.989 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3507 | -122.1218 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35334464 | PSPS - VOLTA 11011516 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7991 | 0 | 0 | 1.7991 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.3748 | -122.1217 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35312556 | CWSP - VOLTA 11011516 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.178 | 0 | 0 | 2.178 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3453 | -121.8922 | WDRM v2 | 0 | 580 | 0.13616 | 0 | 704 | 0.0036607 | Tier 2
35335283 | CWSP - LINCOLN 1104 LR2070 PH 1.4 | Base SH | 08W | ADER | Estimating | Y | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 0 | 1.94 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9566 | -121.2286 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35335282 | CWSP - LINCOLN 1104 LR2070 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35335281 | CWSP - LINCOLN 1104 LR2070 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0201 | 0 | 0 | 3.0201 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9448 | -121.2456 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35332959 | CWSP LINCOLN 1104 LR2070 PH 2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.8975 | -121.2471 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35332958 | CWSP LINCOLN 1104 LR2070 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35320454 | CWSP - LINCOLN 1104 LR2070 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.952 | -121.2551 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35320312 | CWSP LINCOLN 1104 LR2070 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 | 0 | 568 | 0.14111 | 0 | 3055 | 0.00011911 | Tier 2
35262345 | DR-STS-POLE_IDLE_REMV-4S/OR/O3235MEADOW | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3774 | -122.4352 | WDRM v2 | 0 | 554 | 0.14355 | 0 | 1152 | 0.0017959 | Tier 2
35056808 | R20A - FREESTONE SONOMA COUNTY | Other | 30A | PEND | Permitting/Dependency | Y | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | WDRM v2 | 0 | 534 | 0.14747 | 0 | 1720 | 0.00074971 | Tier 3
35275479 | FT-OFAC_IDLE_REMV - #7 ON LINE S/O CO#5 | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26705 | 0.26705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4236 | -121.8237 | WDRM v2 | 0 | 532 | 0.14786 | 0 | 1752 | 0.00072124 | Tier 2
35262812 | LUCERNE 1103 - DIST LINE WORK | Other | 06H | ESTS | Estimating | Y | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lucerne | Lake | 0 | 0 | WDRM v2 | 0 | 512 | 0.1512 | 0 | 3737 | 5.9361e-05 | Tier 2
35260649 | X22: CWSP - PASO ROBLES 1103N04 PH 1 | Base SH | 08W | CONS | In-Construction | Y | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61742 | 0 | 0 | 0.61742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7334 | -120.8792 | WDRM v2 | 0 | 510 | 0.1516 | 0 | 1729 | 0.00074213 | Tier 2
35335293 | PSPS - VACAVILLE 1111 CB PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 2.41 | 0 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 | 0 | 500 | 0.15336 | 0 | 1985 | 0.00055328 | Tier 2
35335292 | PSPS - VACAVILLE 1111 CB PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 | 0 | 500 | 0.15336 | 0 | 1985 | 0.00055328 | Tier 2
35335291 | PSPS - VACAVILLE 1111 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 | 0 | 500 | 0.15336 | 0 | 1985 | 0.00055328 | Tier 2
35320440 | PSPS - VACAVILLE 1111 CB PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3783 | -122.0044 | WDRM v2 | 0 | 500 | 0.15336 | 0 | 1985 | 0.00055328 | Tier 2
35243443 | REMG 188 - TIVY VALLEY 1107 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Sanger | Fresno | 36.8168 | -119.3407 | WDRM v2 | 0 | 491 | 0.15534 | 0 | 1657 | 0.00080485 | Tier 2
35244105 | DR-COND_IDLE_REMV-20095 HWY 175 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7672 | -122.6631 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Base SH | 08W | DOCC | In-Construction | Y | 0.17614 | 1.2508 | 0 | 1.4269 | 0.088068 | 1.2034 | 0 | 1.2915 | 0.088068 | 0.047348 | 0 | 0.13542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Base SH | 08W | CONS | In-Construction | Y | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0.79375 | 0 | 0 | 0.79375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41894 | 0 | 0.41894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Base SH | 08W | CONS | In-Construction | Y | 0.71326 | 0 | 0 | 0.71326 | 0.5358 | 0 | 0 | 0.5358 | 0.17746 | 0 | 0 | 0.17746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87992 | 0 | 0 | 0.87992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35174479 | REMG 749-MIDDLETOWN 1101,ANDERSON SPRNGS | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | 0 | 474 | 0.15935 | 0 | 102 | 0.018129 | Tier 3
35301110 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40322 | 0 | 0 | 0.40322 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Base SH | 08W | CONS | In-Construction | Y | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Base SH | 08W | CONS | In-Construction | Y | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0.0037879 | 1.3765 | 0 | 1.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97576 | 0 | 0 | 0.97576 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2953 | 0 | 0 | 1.2953 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87841 | 0 | 0 | 0.87841 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Base SH | 08W | ESTS | Estimating | Y | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7241 | -122.619 | WDRM v2 | 0 | 468 | 0.1603 | 0 | 13 | 0.035184 | Tier 3
35340270 | PSPS - CORNING 1102 LR915324 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 | 0 | 457 | 0.16319 | 0 | 2905 | 0.0001615 | Tier 2
35311898 | PSPS - CORNING 1102 LR915324 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 | 0 | 457 | 0.16319 | 0 | 2905 | 0.0001615 | Tier 2
35274594 | CWSP MARIPOSA 2101 LR 35244 PH 2.4 | Base SH | 08W | ESTS | Estimating | Y | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.078 | 0 | 0 | 3.078 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5353 | -119.9554 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 2.756 | 0 | 2.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2
35274592 | CWSP MARIPOSA 2101 LR 35244 PH 2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.963 | 0 | 0 | 1.963 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5116 | -119.9647 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2
35274591 | CWSP MARIPOSA 2101 LR 35244 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.022 | 0 | 0 | 1.022 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5195 | -119.9397 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2 & 3
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 2.132 | 0 | 2.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2 & 3
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.595 | 0 | 0 | 4.595 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 | 2.4009 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 2 & 3
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | Base SH | 08W | CONS | In-Construction | Y | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | WDRM v2 | 0 | 428 | 0.17286 | 0 | 249 | 0.010861 | Tier 3
35250938 | STS-POLE_IDLE_REMV-4/S/O 1/N/O 4511 BROO | Idle Facilities | 2AF | ESTS | Estimating | Y | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.6385 | -120.9907 | WDRM v2 | 0 | 424 | 0.1736 | 0 | 886 | 0.0026967 | Tier 3
35330243 | CWSP - REDBUD 1101 LR323962 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0621 | -122.5786 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 3
35330242 | CWSP - REDBUD 1101 LR323962 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69091 | 0 | 0 | 0.69091 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0671 | -122.5853 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 3
35330241 | CWSP - REDBUD 1101 LR323962 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 3
35330219 | CWSP - REDBUD 1101 LR323962 PH1.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 3
35330217 | CWSP - REDBUD 1101323962 PH 2.6 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35330216 | CWSP - REDBUD 1101323962 PH 2.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35330215 | CWSP - REDBUD 1101323962 PH 2.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 3.54 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35330213 | CWSP - REDBUD 1101323962 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.26 | 0 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.5887 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35330211 | CWSP - REDBUD 1101323962 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35317399 | CWSP - REDBUD 1101323962 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 2 & 3
35312550 | CWSP - REDBUD 1101 LR323962 PH1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 | 0 | 423 | 0.17389 | 0 | 127 | 0.016255 | Tier 3
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Ahwahnee | Madera | 37.3642 | -119.7251 | WDRM v2 | 0 | 421 | 0.17437 | 0 | 913 | 0.0025801 | Tier 3
35320463 | PSPS - JAMESON 1105913400 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 | 0 | 419 | 0.17457 | 0 | 987 | 0.0022992 | Tier 2
35221246 | DR~T2 REMV IDLE POLE 6 N/O #1 E/0 ENT | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Yorkville | Mendocino | 38.9374 | -123.309 | WDRM v2 | 0 | 417 | 0.17472 | 0 | 1638 | 0.0008197 | Tier 2
35380377 | REMG 301 - CORNING 1102, NEWVILLE | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8303 | -122.5775 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380376 | PSPS - CORNING 1102 LR53184 PH 1.15 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380375 | REMG 797 - CORNING 1102 PH 1.14 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8374 | -122.6306 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380374 | REMG 818 - CORNING 1102 PH 1.13 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8507 | -122.6133 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380373 | PSPS - CORNING 1102 LR53184 PH 1.12 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380372 | PSPS - CORNING 1102 LR53184 PH 1.11 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380371 | PSPS - CORNING 1102 LR53184 PH 1.10 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380370 | PSPS - CORNING 1102 LR53184 PH 1.9 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380369 | PSPS - CORNING 1102 LR53184 PH 1.8 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380368 | PSPS - CORNING 1102 LR53184 PH 1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35380365 | PSPS - CORNING 1102 LR53184 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35334230 | REMG 817 - CORNING 1102 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8348 | -122.6319 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35334229 | PSPS - CORNING 1102 LR53184 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35311897 | PSPS - CORNING 1102 LR53184 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 4.84 | 0 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 2
35276100 | REMG 300 - CORNING 1102, TURRI MAIN | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 3
35229051 | REMG 299 - CORNING 1102, TURRI ELLIS | Base SH | 08W | CONS | In-Construction | Y | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9003 | -122.5065 | WDRM v2 | 0 | 413 | 0.17544 | 0 | 694 | 0.0037456 | Tier 3
35285245 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38333 | 0 | 0 | 0.38333 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3019 | -123.109 | WDRM v2 | 0 | 396 | 0.18107 | 0 | 2321 | 0.00037714 | Tier 2
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0.012311 | 0.25398 | 0 | 0.26629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 | 0 | 396 | 0.18107 | 0 | 2321 | 0.00037714 | Tier 2
35285064 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 | 0 | 396 | 0.18107 | 0 | 2321 | 0.00037714 | Tier 2
35254077 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3171 | -123.1131 | WDRM v2 | 0 | 396 | 0.18107 | 0 | 2321 | 0.00037714 | Tier 2
35339293 | PSPS - JAMESON 1105 LR466348 PH 1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338410 | PSPS - JAMESON 1105 LR466348 PH 2.3 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338409 | PSPS - JAMESON 1105 LR466348 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338408 | PSPS - JAMESON 1105 LR466348 PH 1.6 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338407 | PSPS - JAMESON 1105 LR466348 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338405 | PSPS - JAMESON 1105 LR466348 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35338404 | PSPS - JAMESON 1105 LR466348 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35320461 | PSPS - JAMESON 1105 LR466348 PH 2.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35320460 | PSPS - JAMESON 1105 LR466348 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 | 0 | 393 | 0.18223 | 0 | 728 | 0.0035256 | Tier 2
35339289 | CWSP - JESSUP 1102 LR1550 PH 3.4 | Base SH | 08W | ADER | Estimating | Y | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 1.82 | 0 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339288 | CWSP - JESSUP 1102 LR1550 PH 3.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339287 | CWSP - JESSUP 1102 LR1550 PH 3.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339286 | CWSP - JESSUP 1102 LR1550 PH 2.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 2.54 | 0 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339285 | CWSP - JESSUP 1102 LR1550 PH 2.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339283 | CWSP - JESSUP 1102 LR1550 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35339282 | CWSP - JESSUP 1102 LR1550 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0.51 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35337012 | CWSP - JESSUP 1102 LR1550 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.92 | 0 | 4.92 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.443 | -122.3663 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35337011 | CWSP - JESSUP 1102 LR1550 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35337010 | CWSP - JESSUP 1102 LR1550 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 3.82 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35317887 | CWSP - JESSUP 1102 LR1550 PH 3.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35317480 | CWSP - JESSUP 1102 LR1550 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35312548 | CWSP - JESSUP 1102 LR1550 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 | 0 | 389 | 0.18396 | 0 | 1853 | 0.00063997 | Tier 2
35338403 | CWSP - PANORAMA 1101 LR885215 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92008 | 0 | 0 | 0.92008 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4063 | -122.2482 | WDRM v2 | 0 | 380 | 0.18705 | 0 | 3890 | 5.6461e-05 | Tier 2
35320465 | CWSP - PANORAMA 1101 LR885215 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 0 | 1.11 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4073 | -122.2444 | WDRM v2 | 0 | 380 | 0.18705 | 0 | 3890 | 5.6461e-05 | Tier 2
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 5.589 | 0 | 5.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | 0 | 378 | 0.1873 | 0 | 45 | 0.023178 | Tier 2 & 3
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1756 | 0 | 0 | 1.1756 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8879 | -121.8676 | WDRM v2 | 0 | 377 | 0.18755 | 0 | 15 | 0.034099 | Tier 3
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 | 0 | 377 | 0.18755 | 0 | 15 | 0.034099 | Tier 3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Base SH | 08W | CONS | In-Construction | Y | 0.28352 | 1.1968 | 0 | 1.4803 | 0.28352 | 1.1364 | 0 | 1.4199 | 0 | 0.060417 | 0 | 0.060417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 | 0 | 355 | 0.19378 | 0 | 2768 | 0.00020951 | Tier 2
35330249 | CWSP REDBUD 1101 708166 PH 1.7 | Base SH | 08W | ADER | Estimating | Y | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0.25 | 4 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35330248 | CWSP REDBUD 1101 708166 PH 1.6 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0296 | -122.6802 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35330247 | CWSP REDBUD 1101 708166 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35330246 | CWSP REDBUD 1101 708166 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35330245 | CWSP REDBUD 1101 708166 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35330244 | CWSP REDBUD 1101 708166 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35329474 | CWSP REDBUD 1101 754544 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 1.16 | 0.11004 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 375 | 0.007396 | Tier 2 & 3
35317398 | CWSP REDBUD 1101 754544 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5201 | 0 | 3.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0581 | -122.693 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 375 | 0.007396 | Tier 2 & 3
35312552 | CWSP REDBUD 1101 708166 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 2 & 3
35208096 | 8/31-HOLD REMV IDLE FAC -LONGVALLEY *KS | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.069 | -122.6909 | WDRM v2 | 0 | 345 | 0.19539 | 0 | 679 | 0.0038601 | Tier 3
35226625 | REMG 670 - ELK CREEK 1101, VALLEY VIEW | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.6065 | -122.5419 | WDRM v2 | 0 | 340 | 0.1961 | 0 | 308 | 0.0090072 | Tier 2
35083879 | STS-POLE_IDLE_REMV - NEGRO CK RD/RD 152 | Idle Facilities | 2AF | ADER | Estimating | Y | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Orange Cove | Tulare | 36.6365 | -119.1962 | WDRM v2 | 0 | 337 | 0.19768 | 0 | 2377 | 0.00035672 | Tier 2
35349642 | CWSP - UPPER LAKE 1101 1276 PH 2.7 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1699 | -123.006 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35285250 | CWSP - UPPER LAKE 1101 1276 PH 2.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 | 0.51705 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1756 | -123.0186 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35285249 | CWSP - UPPER LAKE 1101 1276 PH 2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35285248 | CWSP - UPPER LAKE 1101 1276 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.461 | 0 | 0 | 1.461 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1679 | -123.0053 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35285247 | CWSP - UPPER LAKE 1101 1276 PH 2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30379 | 0 | 0 | 0.30379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1668 | -123.0058 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283349 | CWSP UPPER LAKE 1101 1276 PH 1.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0549 | 0 | 0 | 1.0549 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.113 | -122.9818 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283348 | CWSP UPPER LAKE 1101 1276 PH 1.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95379 | 0 | 0 | 0.95379 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1213 | -122.9896 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4144 | 0 | 0 | 1.4144 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1253 | -122.9948 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283344 | CWSP UPPER LAKE 1101 1276 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6561 | 0 | 0 | 1.6561 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1474 | -122.9995 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35283343 | CWSP UPPER LAKE 1101 1276 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0.18447 | 0.72614 | 0 | 0.91061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35256083 | CWSP - UPPER LAKE 11011276 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0.0079545 | 1.847 | 0 | 1.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35256082 | CWSP - UPPER LAKE 11011276 PH 1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 1.1477 | 0 | 0 | 1.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1583 | -122.9898 | WDRM v2 | 0 | 335 | 0.19794 | 0 | 35 | 0.024971 | Tier 2
35278889 | CWSP - AUBERRY 1101 LR49122 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1968 | 0 | 0 | 2.1968 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0894 | -119.4783 | WDRM v2 | 0 | 330 | 0.19907 | 0 | 734 | 0.0034999 | Tier 2
35254242 | CWSP - AUBERRY 1101 LR 49122 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 | 1.9436 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0812 | -119.4864 | WDRM v2 | 0 | 330 | 0.19907 | 0 | 734 | 0.0034999 | Tier 2
35083893 | STS-COND_IDLE_REMV-5282 MINES RD | Idle Facilities | 2AF | CONS | In-Construction | Y | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6459 | -121.7137 | WDRM v2 | 0 | 324 | 0.20121 | 0 | 764 | 0.0032627 | Tier 2
35134959 | VALLEY SPRINGS 1102 FEEDER OUTLET | Other | 06A | PEND | Permitting/Dependency | Y | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0.18939 | 0 | 1.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Valley Springs | Calaveras | 38.2131 | -120.7638 | WDRM v2 | 0 | 322 | 0.20132 | 0 | 1048 | 0.0020877 | Tier 2
35332364 | CWSP ELK CREEK 1101 LR2002 PH 2.6 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35332363 | CWSP ELK CREEK 1101 LR2002 PH 2.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35332362 | CWSP ELK CREEK 1101 LR2002 PH 2.4 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35332361 | REMG 255 - ELK CREEK 1101, BRAVO | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4277 | -122.5067 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35332360 | CWSP ELK CREEK 1101 LR2002 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 5.46 | 0 | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35330813 | REMG 256 - ELK CREEK 1101, MILANO | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5331 | -122.5377 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35330812 | PSPS ELK CREEK 1101 LR2002 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 2.49 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35316278 | CWSP ELK CREEK 1101 LR2002 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35312543 | PSPS ELK CREEK 1101 LR2002 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 3.71 | 0 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 | 0 | 315 | 0.20473 | 0 | 1044 | 0.0021026 | Tier 2
35329473 | CWSP - REDBUD 1101 LR454 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0654 | -122.6333 | WDRM v2 | 0 | 312 | 0.20738 | 0 | 44 | 0.023647 | Tier 3
35329472 | CWSP - REDBUD 1101 LR454 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 | 0 | 312 | 0.20738 | 0 | 44 | 0.023647 | Tier 3
35312551 | CWSP - REDBUD 1101 LR454 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 | 0 | 312 | 0.20738 | 0 | 44 | 0.023647 | Tier 3
35349646 | CWSP - BUELLTON 1102 CB PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.5925 | -120.1558 | WDRM v2 | 0 | 307 | 0.21085 | 0 | 2847 | 0.00018253 | Tier 2
35349645 | CWSP - BUELLTON 1102 CB PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4199 | 0 | 0 | 1.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6005 | -120.1908 | WDRM v2 | 0 | 307 | 0.21085 | 0 | 2847 | 0.00018253 | Tier 2
35349643 | CWSP - BUELLTON 1102 CB PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 | 1.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1576 | WDRM v2 | 0 | 307 | 0.21085 | 0 | 2847 | 0.00018253 | Tier 2
35320445 | CWSP - BUELLTON 1102 CB PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Buellton | Santa Barbara | 34.6236 | -120.185 | WDRM v2 | 0 | 307 | 0.21085 | 0 | 2847 | 0.00018253 | Tier 2
35259514 | CWSP - DESCHUTES 11041582 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 0 | 0 | 3.61 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5894 | -122.2244 | WDRM v2 | 0 | 301 | 0.21327 | 0 | 3101 | 0.0001094 | Tier 2
35279629 | CWSP PASO ROBLES 1103 LRN52 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8534 | 0 | 0 | 1.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7141 | -120.8386 | WDRM v2 | 0 | 291 | 0.21643 | 0 | 311 | 0.0089389 | Tier 2
35279628 | CWSP PASO ROBLES 1103 LRN52 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.706 | -120.8189 | WDRM v2 | 0 | 291 | 0.21643 | 0 | 311 | 0.0089389 | Tier 2
35254252 | +CWSP - PASO ROBLES 1103 LR N52 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 2.414 | 0 | 0 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6886 | -120.7649 | WDRM v2 | 0 | 291 | 0.21643 | 0 | 311 | 0.0089389 | Tier 2
35278090 | CWSP - AUBERRY 1101R2839 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.849 | 0 | 0.39583 | 3.2448 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0201 | -119.4294 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35277935 | CWSP AUBERRY 1101 R2839 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35277934 | CWSP AUBERRY 1101 R2839 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1282 | 0 | 0 | 2.1282 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0314 | -119.4428 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35277933 | CWSP AUBERRY 1101 R2839 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1036 | 0 | 0 | 2.1036 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0335 | -119.4426 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35254241 | CWSP - AUBERRY 1101 LR R2839 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8248 | 0 | 0 | 2.8248 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35254240 | CWSP - AUBERRY 1101 LR R2839 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 | WDRM v2 | 0 | 274 | 0.22501 | 0 | 614 | 0.0043344 | Tier 2
35332217 | PSPS COTTONWOOD 1102 LR9026 PH 3.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0.05303 | 3.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35332216 | PSPS COTTONWOOD 1102 LR9026 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35332215 | PSPS COTTONWOOD 1102 LR9026 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35332214 | PSPS COTTONWOOD 1102 LR9026 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 4.04 | 0 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35316569 | PSPS - COTTONWOOD 11029026 PH3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0.032008 | 4.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35316567 | PSPS - COTTONWOOD 11029026 PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35312540 | PSPS - COTTONWOOD 11029026 PH1 | Base SH | 08W | ADER | Estimating | Y | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | 0 | 271 | 0.22599 | 0 | 2723 | 0.0002216 | Tier 2
35349651 | CWSP - BUELLTON 1102 Y50 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4951 | 0 | 0 | 2.4951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6136 | -120.1365 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35349650 | CWSP - BUELLTON 1102 Y50 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35349649 | CWSP - BUELLTON 1102 Y50 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7606 | 0.25019 | 0 | 3.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35349648 | CWSP - BUELLTON 1102 Y50 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0.25625 | 0 | 1.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35349647 | CWSP - BUELLTON 1102 Y50 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0398 | 0 | 0 | 1.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Goleta | Santa Barbara | 34.6129 | -120.1624 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35320446 | CWSP - BUELLTON 1102 Y50 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.613 | -120.1749 | WDRM v2 | 0 | 269 | 0.22624 | 0 | 2607 | 0.00026962 | Tier 2
35329008 | PSPS CLARK ROAD 1102 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 | 0 | 268 | 0.22632 | 0 | 2491 | 0.00031072 | Tier 2
35299629 | PSPS CLARK ROAD 1102 CB PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.654 | -121.6323 | WDRM v2 | 0 | 268 | 0.22632 | 0 | 2491 | 0.00031072 | Tier 2
35331302 | CWSP ANDERSON 1103 LR226050 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.532 | 0 | 0 | 1.532 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4766 | -122.2926 | WDRM v2 | 0 | 262 | 0.22913 | 0 | 3263 | 8.0345e-05 | Tier 2
35331301 | CWSP ANDERSON 1103 LR226050 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66705 | 0 | 0 | 0.66705 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4791 | -122.2929 | WDRM v2 | 0 | 262 | 0.22913 | 0 | 3263 | 8.0345e-05 | Tier 2
35330816 | CWSP ANDERSON 1103 LR226050 PH 1.3 UPDAT | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.5058 | -122.2574 | WDRM v2 | 0 | 262 | 0.22913 | 0 | 3263 | 8.0345e-05 | Tier 2
35330815 | CWSP ANDERSON 1103 LR226050 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 | 0 | 262 | 0.22913 | 0 | 3263 | 8.0345e-05 | Tier 2
35311895 | CWSP ANDERSON 1103 LR226050 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 | 0 | 262 | 0.22913 | 0 | 3263 | 8.0345e-05 | Tier 2
35279626 | +X22: CWSP -PASO ROBLES 1103 LR 2731 PH1 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0.16364 | 0 | 0 | 0.16364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.73 | WDRM v2 | 0 | 260 | 0.2296 | 0 | 940 | 0.0024787 | Tier 2
35254254 | +X22: CWSP - PASO ROBLES 1103 LR 2731 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.7299 | WDRM v2 | 0 | 260 | 0.2296 | 0 | 940 | 0.0024787 | Tier 2
35151005 | 8/31 REMV IDLE 4 LOCS OLD WITTER SP*RA | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.185 | -122.9886 | WDRM v2 | 0 | 259 | 0.23008 | 0 | 327 | 0.0086415 | Tier 2
35279631 | CWSP - PASO ROBLES 1103 LRN58 PH1.2 | Base SH | 08W | CONS | In-Construction | Y | 3.064 | 0 | 0 | 3.064 | 1.4223 | 0 | 0 | 1.4223 | 1.6417 | 0 | 0 | 1.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6385 | -120.7157 | WDRM v2 | 0 | 257 | 0.23099 | 0 | 771 | 0.0032279 | Tier 2
35254248 | CWSP - PASO ROBLES 1103 LR N58 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | El Paso De Robles | San Luis Obispo | 35.6286 | -120.6955 | WDRM v2 | 0 | 257 | 0.23099 | 0 | 771 | 0.0032279 | Tier 2
35225318 | +STS-COND_IDLE_REMV-CAT CANYON RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | Y | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Maria | Santa Barbara | 34.8111 | -120.2748 | WDRM v2 | 0 | 256 | 0.23169 | 0 | 2229 | 0.00042166 | Tier 2
35337306 | CWSP STANISLAUS 1702 CB PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0.0094697 | 2.2667 | 0 | 2.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 | 0 | 235 | 0.24096 | 0 | 54 | 0.022026 | Tier 2 & 3
35284366 | REMG 512 - STANISLAUS 1702, FOREBAY | Base SH | 08W | ESTS | Estimating | Y | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1446 | -120.3574 | WDRM v2 | 0 | 235 | 0.24096 | 0 | 54 | 0.022026 | Tier 2 & 3
35284365 | CWSP STANISLAUS 1702 CB PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0.025 | 2.7547 | 0 | 2.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 | 0 | 235 | 0.24096 | 0 | 54 | 0.022026 | Tier 2 & 3
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0.0047348 | 0.91742 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 | 0 | 235 | 0.24096 | 0 | 54 | 0.022026 | Tier 2 & 3
35250577 | CWSP - STANISLAUS 1702 CB | Base SH | 08W | CONS | In-Construction | Y | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 3.5777 | 0 | 0 | 3.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1377 | -120.3701 | WDRM v2 | 0 | 235 | 0.24096 | 0 | 54 | 0.022026 | Tier 2 & 3
35349244 | CWSP - LINCOLN 1104 LR685276 PH 1.5 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v2 | 0 | 230 | 0.24208 | 0 | 4147 | 5.2842e-05 | Tier 2
35339292 | CWSP - LINCOLN 1104 LR685276 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9969 | -121.2718 | WDRM v2 | 0 | 230 | 0.24208 | 0 | 4147 | 5.2842e-05 | Tier 2
35339291 | CWSP - LINCOLN 1104 LR685276 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9964 | -121.2681 | WDRM v2 | 0 | 230 | 0.24208 | 0 | 4147 | 5.2842e-05 | Tier 2
35339290 | CWSP - LINCOLN 1104 LR685276 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 | 0 | 230 | 0.24208 | 0 | 4147 | 5.2842e-05 | Tier 2
35320450 | CWSP - LINCOLN 1104 LR685276 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 | 0 | 230 | 0.24208 | 0 | 4147 | 5.2842e-05 | Tier 2
35211757 | DR-COND_IDLE_REMV-13716 LOS VERJELES | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Marysville | Yuba | 39.3562 | -121.3774 | WDRM v2 | 0 | 225 | 0.24429 | 0 | 2534 | 0.00029638 | Tier 2
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Base SH | 08W | CONS | In-Construction | Y | 0.076705 | 0.53561 | 0 | 0.61231 | 0.062879 | 0.40985 | 0 | 0.47273 | 0 | 0 | 0 | 0 | 0.013826 | 0.12576 | 0 | 0.13958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WDRM v2 | 0 | 218 | 0.24845 | 0 | 2461 | 0.00032066 | Tier 2
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 | 0 | 215 | 0.25006 | 0 | 1267 | 0.0014262 | Tier 3
35150641 | T2-COND_IDLE_REMV-16853 DAM RD *KS | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9248 | -122.5972 | WDRM v2 | 0 | 212 | 0.25222 | 0 | 847 | 0.0028915 | Tier 2
35332219 | PSPS ELK CREEK 1101 LR93504 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1299 | 0 | 0 | 1.1299 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.593 | -122.5412 | WDRM v2 | 0 | 206 | 0.25426 | 0 | 1350 | 0.0012407 | Tier 2
35312544 | CWSP ELK CREEK 1101 LR93504 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 | 0 | 206 | 0.25426 | 0 | 1350 | 0.0012407 | Tier 2
35262347 | STS-POLE_IDLE_REMV - A/F 45771 BUTTERNUT | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6995 | -119.1257 | WDRM v2 | 0 | 195 | 0.26095 | 0 | 1266 | 0.0014269 | Tier 2
35215883 | STS-TRAN_CORR_REPL - 45886 CHUCKWAGON RD | Idle Facilities | 2AA | PEND | Permitting/Dependency | Y | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Squaw Valley | Fresno | 36.6914 | -119.1303 | WDRM v2 | 0 | 195 | 0.26095 | 0 | 1266 | 0.0014269 | Tier 2
35335290 | PSPS - VACAVILLE 1111 LR13652 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 | 0 | 190 | 0.26339 | 0 | 1722 | 0.00074783 | Tier 2
35320441 | PSPS - VACAVILLE 1111 LR13652 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 | 0 | 190 | 0.26339 | 0 | 1722 | 0.00074783 | Tier 2
35337164 | CWSP LINCOLN 1104 51756 & 275986 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9708 | -121.2498 | WDRM v2 | 0 | 185 | 0.26526 | 0 | 2971 | 0.0001399 | Tier 2
35337163 | CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0.48996 | 1.39 | 1.2646 | 3.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 | 0 | 185 | 0.26526 | 0 | 2971 | 0.0001399 | Tier 2
35320449 | CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 3.2375 | 1.5472 | 4.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 | 0 | 185 | 0.26526 | 0 | 2971 | 0.0001399 | Tier 2
35208097 | 8/31-REMV IDLE 19824 MORGAN HOLD FOR 10J | Idle Facilities | 2AF | UNSC | Ready for Construction | Y | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8926 | -122.5433 | WDRM v2 | 0 | 181 | 0.26975 | 0 | 270 | 0.010079 | Tier 2
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 | Base SH | 08W | CONS | In-Construction | Y | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 | 0 | 171 | 0.27308 | 0 | 712 | 0.0036194 | Tier 2
35240173 | CWSP - PUTAH CREEK 11028352 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 1.567 | 0 | 0 | 1.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo | 38.5035 | -122.002 | WDRM v2 | 0 | 171 | 0.27308 | 0 | 712 | 0.0036194 | Tier 2
35310704 | CWSP MOUNTAIN QUARRIES 2101 1350 PH1.12 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.196 | 0 | 0 | 1.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305312 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.11 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14792 | 0 | 0 | 0.14792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.9674 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305311 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73201 | 0 | 0 | 0.73201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8965 | -120.9455 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305310 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0771 | 0 | 0 | 1.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.899 | -120.9485 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305309 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 | 0 | 0 | 1.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9633 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305308 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8944 | -120.9647 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305307 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.6 | Base SH | 08W | ADER | Estimating | Y | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0741 | 0 | 0 | 1.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8962 | -120.9648 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305306 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65398 | 0 | 0 | 0.65398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8977 | -120.972 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305305 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.522 | 0 | 0 | 1.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8981 | -120.9738 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305304 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99205 | 0 | 0 | 0.99205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8978 | -120.9866 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 1.065 | 0 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293670 | CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293669 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 0 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8852 | -120.96 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293668 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8894 | -120.9589 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293667 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8974 | -120.9338 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293666 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22992 | 0 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9012 | -120.9346 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | Base SH | 08W | UNSC | Ready for Construction | Y | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293664 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8981 | -120.914 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98996 | 0 | 0.98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH2. | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8932 | -120.9965 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35254070 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95701 | 0 | 0 | 0.95701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8931 | -120.9966 | WDRM v2 | 0 | 169 | 0.27537 | 0 | 401 | 0.0069368 | Tier 2
35278892 | CWSP - AUBERRY 1101R2578 PH5.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 0 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9662 | -119.3834 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278891 | CWSP - AUBERRY 1101R2578 PH5.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9752 | -119.3882 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278890 | CWSP - AUBERRY 1101R2578 PH5.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9737 | -119.3888 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278097 | CWSP - AUBERRY 1101R2578 PH4.3 | Base SH | 08W | CONS | In-Construction | Y | 1.286 | 0 | 0.20095 | 1.4869 | 0.66345 | 0 | 0 | 0.66345 | 0.62254 | 0 | 0.20095 | 0.82348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.98 | -119.4029 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278093 | CWSP - AUBERRY 1101R2578 PH3.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.41496 | 0 | 0.41496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278092 | CWSP - AUBERRY 1101R2578 PH3.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8369 | 0 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.978 | -119.3677 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35278091 | CWSP - AUBERRY 1101R2578 PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.839 | 0 | 0 | 2.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9796 | -119.3694 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277938 | CWSP AUBERRY 1101 R2578 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0.42822 | 0.31742 | 0.74564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277937 | CWSP AUBERRY 1101 R2578 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9004 | 0 | 0 | 2.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0129 | -119.3939 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277936 | CWSP AUBERRY 1101 R2578 PH2.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 3.5307 | 0 | 0 | 3.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0143 | -119.4031 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277924 | CWSP AUBERRY 1101 R2578 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277923 | CWSP AUBERRY 1101 R2578 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 3.1777 | 0 | 0 | 3.1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9916 | -119.4068 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277922 | CWSP AUBERRY 1101 R2578 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.005 | -119.4055 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35277921 | CWSP AUBERRY 1101 R2578 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 0 | 0 | 2.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0111 | -119.4175 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35254247 | CWSP - AUBERRY 1101 LR R2578 PH5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 2.9581 | 0 | 0 | 2.9581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35254244 | CWSP - AUBERRY 1101 LR R2578 PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 2.4244 | 0 | 0 | 2.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35254243 | CWSP - AUBERRY 1101 LR R2578 PH1 | Base SH | 08W | ESTS | Estimating | Y | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9083 | 0 | 0 | 2.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 | WDRM v2 | 0 | 163 | 0.27714 | 0 | 569 | 0.0047219 | Tier 2
35226852 | X22: CWSP-SHINGLE SPRINGS 2109-LR 9372-P | Base SH | 08W | UNSC | Ready for Construction | Y | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 | 2.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | WDRM v2 | 0 | 159 | 0.27855 | 0 | 241 | 0.011098 | Tier 3
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Base SH | 08W | CONS | In-Construction | Y | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 | 0 | 159 | 0.27855 | 0 | 241 | 0.011098 | Tier 3
35254651 | CWSP - VOLTA 110153118 PH 1.4 | Base SH | 08W | CONS | In-Construction | Y | 2.4038 | 0 | 0 | 2.4038 | 2.3117 | 0 | 0 | 2.3117 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 | 0 | 157 | 0.27952 | 0 | 280 | 0.0099281 | Tier 2
35254650 | CWSP - VOLTA 110153118 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0.0056818 | 0.30436 | 0 | 0.31004 | 0 | 0.30436 | 0 | 0.30436 | 0.0056818 | 0 | 0 | 0.0056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 | 0 | 157 | 0.27952 | 0 | 280 | 0.0099281 | Tier 2
35264190 | CWSP - SANTA YNEZ 1104 Y66 PH 2.3 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 2.3576 | 0 | 0 | 2.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6451 | -119.9634 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35264189 | CWSP - SANTA YNEZ 1104Y66 PH 2.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 2.6055 | 0 | 0 | 2.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6377 | -119.9713 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35264188 | CWSP - SANTA YNEZ 1104Y66 PH 1.5 | Base SH | 08W | CONS | In-Construction | Y | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 1.1292 | 0 | 0 | 1.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6065 | -119.9508 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35264187 | CWSP - SANTA YNEZ 1104Y66 PH 1.4 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 1.6919 | 0 | 0 | 1.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6112 | -119.9786 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35264185 | CWSP - SANTA YNEZ 1104Y66 PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 1.4926 | 0 | 0 | 1.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6142 | -119.9878 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2.1 | Base SH | 08W | CONS | In-Construction | Y | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 2.589 | 0 | 0 | 2.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1.1 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 2.1089 | 0 | 0 | 2.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6109 | -120.0203 | WDRM v2 | 0 | 153 | 0.28279 | 0 | 1417 | 0.0011255 | Tier 2 & 3
35325590 | CWSP FLINT 1101 750 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 | 0 | 152 | 0.28318 | 0 | 1508 | 0.00097924 | Tier 2
35325589 | CWSP FLINT 1101 750 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 | 0 | 152 | 0.28318 | 0 | 1508 | 0.00097924 | Tier 2
35312545 | CWSP - FLINT 1101750 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 | 0 | 152 | 0.28318 | 0 | 1508 | 0.00097924 | Tier 2
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 | Base SH | 08W | CONS | In-Construction | Y | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 2.218 | 0 | 0 | 2.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 | 0 | 144 | 0.28655 | 0 | 2787 | 0.00020217 | Tier 2
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 | Base SH | 08W | CONS | In-Construction | Y | 3.4638 | 0 | 0 | 3.4638 | 3.3981 | 0 | 0 | 3.3981 | 0.06572 | 0 | 0 | 0.06572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | WDRM v2 | 0 | 144 | 0.28655 | 0 | 2787 | 0.00020217 | Tier 2
35331305 | CWSP ANDERSON 1103 LR1600 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 | 0 | 143 | 0.2889 | 0 | 3058 | 0.00011858 | Tier 2
35331304 | CWSP ANDERSON 1103 LR1600 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4829 | -122.2057 | WDRM v2 | 0 | 143 | 0.2889 | 0 | 3058 | 0.00011858 | Tier 2
35331303 | CWSP ANDERSON 1103 LR1600 PH2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4832 | -122.214 | WDRM v2 | 0 | 143 | 0.2889 | 0 | 3058 | 0.00011858 | Tier 2
35311894 | CWSP ANDERSON 1103 LR1600 PH2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67633 | 0 | 0 | 0.67633 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4768 | -122.2276 | WDRM v2 | 0 | 143 | 0.2889 | 0 | 3058 | 0.00011858 | Tier 2
35298571 | CWSP ANDERSON 1103 LR1600 PH1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 | 0 | 143 | 0.2889 | 0 | 3058 | 0.00011858 | Tier 2
35279627 | X22: CWSP - PASO ROBLES 1103 LRN50 PH 1. | Base SH | 08W | CONS | In-Construction | Y | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3269 | 0 | 0 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7253 | -120.8701 | WDRM v2 | 0 | 138 | 0.30039 | 0 | 742 | 0.0034276 | Tier 2
35249877 | REMG 755 - COARSEGOLD 2104, MELVIN | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 | 0 | 132 | 0.30465 | 0 | 1380 | 0.0011778 | Tier 2
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 3.7142 | 0 | 0 | 3.7142 | 0.94489 | 0 | 0 | 0.94489 | 2.7693 | 0 | 0 | 2.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 | 0 | 132 | 0.30465 | 0 | 1380 | 0.0011778 | Tier 2
35249875 | X22: CWSP - COARSEGOLD 21046210 PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 2.6394 | 0 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 | 0 | 132 | 0.30465 | 0 | 1380 | 0.0011778 | Tier 2
35240165 | X22: CWSP - COARSEGOLD 21046210 PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 3.8498 | 0 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | WDRM v2 | 0 | 132 | 0.30465 | 0 | 1380 | 0.0011778 | Tier 2
35332218 | PSPS COTTONWOOD 1102 LR544790 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 | 0 | 123 | 0.31273 | 0 | 1675 | 0.0007912 | Tier 2
35332213 | PSPS COTTONWOOD 1102 LR544790 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 | 0 | 123 | 0.31273 | 0 | 1675 | 0.0007912 | Tier 2
35316561 | PSPS - COTTONWOOD 1102544790 PH 2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 4.41 | 0 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 | 0 | 123 | 0.31273 | 0 | 1675 | 0.0007912 | Tier 2
35311899 | PSPS - COTTONWOOD 1102544790 PH 1 | Base SH | 08W | ADER | Estimating | Y | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 3.44 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 | 0 | 123 | 0.31273 | 0 | 1675 | 0.0007912 | Tier 2
35404729 | PSPS - VACAVILLE 1108 LR38316 PH 1.5 | Base SH | 08W | ADER | Estimating | Y | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4295 | -122.0489 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35404728 | PSPS - VACAVILLE 1108 LR38316 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4201 | -122.0443 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35404727 | PSPS - VACAVILLE 1108 LR38316 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4267 | -122.0475 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35334755 | PSPS - VACAVILLE 1108 LR38316 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35334754 | PSPS - VACAVILLE 1108 LR38316 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 3.93 | 0 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35334753 | PSPS - VACAVILLE 1108 LR38316 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35320339 | PSPS - VACAVILLE 1108 LR38316 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35320336 | PSPS - VACAVILLE 1108 LR38316 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4365 | -122.0527 | WDRM v2 | 0 | 122 | 0.31672 | 0 | 491 | 0.0056058 | Tier 2
35334234 | CWSP - BELL 1108 LR2202 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1088 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35334233 | CWSP - BELL 1108 LR2202 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1075 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35334232 | CWSP - BELL 1108 LR2202 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9855 | -121.1087 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35334231 | CWSP - BELL 1108 LR2202 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9856 | -121.1102 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333510 | CWSP - BELL 1108 LR2202 PH 3.6 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63996 | 0 | 0 | 0.63996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0081 | -121.1482 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333509 | CWSP - BELL 1108 LR2202 PH 3.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.41 | 0 | 0 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0145 | -121.1236 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333508 | CWSP - BELL 1108 LR2202 PH 3.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0083 | -121.1247 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333507 | CWSP - BELL 1108 LR2202 PH 3.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 39.0003 | -121.1276 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333506 | CWSP - BELL 1108 LR2202 PH 3.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9995 | -121.122 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333505 | CWSP - BELL 1108 LR2202 PH 2.7 | Base SH | 08W | ESTS | Estimating | Y | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.143 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333504 | CWSP - BELL 1108 LR2202 PH 2.6 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333503 | CWSP - BELL 1108 LR2202 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333502 | CWSP - BELL 1108 LR2202 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9891 | -121.1353 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333501 | CWSP - BELL 1108 LR2202 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9851 | -121.1296 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35333500 | CWSP - BELL 1108 LR2202 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1268 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35314416 | CWSP - BELL 1108 LR2202 PH 3.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9981 | -121.1168 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35314415 | CWSP - BELL 1108 LR2202 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35311896 | CWSP - BELL 1108 LR2202 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1091 | WDRM v2 | 0 | 118 | 0.32016 | 0 | 2685 | 0.00023693 | Tier 2
35149246 | STS-COND_IDLE_REMV-16251 HWY 101*JM | Idle Facilities | 2AF | MAPP | In-Construction | Y | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hopland | Mendocino | 38.9503 | -123.0881 | WDRM v2 | 0 | 110 | 0.32431 | 0 | 519 | 0.0051934 | Tier 2
35264182 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 2.6348 | 0 | 0 | 2.6348 | 2.4572 | 0 | 0 | 2.4572 | 0.17765 | 0 | 0 | 0.17765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6278 | -120.0209 | WDRM v2 | 0 | 108 | 0.32463 | 0 | 2888 | 0.0001675 | Tier 2
35264181 | X22: CWSP - SANTA YNEZ 1104Y04 PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 2.7506 | 0 | 0 | 2.7506 | 0.89205 | 0 | 0 | 0.89205 | 1.8585 | 0 | 0 | 1.8585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6365 | -120.0218 | WDRM v2 | 0 | 108 | 0.32463 | 0 | 2888 | 0.0001675 | Tier 2
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 | 0 | 100 | 0.34561 | 0 | 2704 | 0.00022756 | Tier 2
35243447 | CWSP - DESCHUTES 11041370 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.573 | -122.2386 | WDRM v2 | 0 | 100 | 0.34561 | 0 | 2704 | 0.00022756 | Tier 2
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5964 | 0 | 0 | 4.5964 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.5917 | -122.2743 | WDRM v2 | 0 | 99 | 0.34786 | 0 | 2481 | 0.00031475 | Tier 2
35243448 | CWSP - DESCHUTES 110449024 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5929 | -122.2396 | WDRM v2 | 0 | 99 | 0.34786 | 0 | 2481 | 0.00031475 | Tier 2
35254940 | REMG 761 - VOLTA 1101, BATTLE CREEK | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 | 0 | 85 | 0.36191 | 0 | 2428 | 0.00033385 | Tier 2
35254738 | REMG 760 - VOLTA 1101, WILDCAT | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 | 0 | 85 | 0.36191 | 0 | 2428 | 0.00033385 | Tier 2
35254658 | CWSP - VOLTA 11011568 PH 1.4 | Base SH | 08W | DOCC | In-Construction | Y | 1.8225 | 0 | 0 | 1.8225 | 1.7841 | 0 | 0 | 1.7841 | 0.038447 | 0 | 0 | 0.038447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 | 0 | 85 | 0.36191 | 0 | 2428 | 0.00033385 | Tier 2 & 3
35243444 | REMG 757 - VOLTA 1101, PRESLEIGH | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4587 | -121.867 | WDRM v2 | 0 | 85 | 0.36191 | 0 | 2428 | 0.00033385 | Tier 2
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 2.0985 | 0 | 0 | 2.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2635 | -119.7123 | WDRM v2 | 0 | 78 | 0.37306 | 0 | 1728 | 0.00074257 | Tier 2
35254259 | CWSP - VOLTA 1101CB PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0.22803 | 0.275 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 | 0 | 76 | 0.37545 | 0 | 2202 | 0.00043332 | Tier 2 & 3
35254258 | X22: CWSP - VOLTA 1101CB PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 1.3525 | 0 | 0 | 1.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 | 0 | 76 | 0.37545 | 0 | 2202 | 0.00043332 | Tier 2 & 3
35240166 | CWSP - VOLTA 1101CB PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 0.46326 | 0.015341 | 0 | 0.4786 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 | 0 | 76 | 0.37545 | 0 | 2202 | 0.00043332 | Tier 2 & 3
35293846 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293845 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.8 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3031 | -123.057 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293844 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.7 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2984 | -123.0591 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293843 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 1.31 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2953 | -123.0616 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293841 | CWSP - POTTER VALLEY PH 11051904 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2927 | -123.085 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293775 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.4 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3018 | -123.0942 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293774 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2699 | 0 | 0 | 1.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3095 | -123.0931 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35293770 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3146 | -123.0942 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35290808 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290807 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3699 | 0 | 0 | 1.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2457 | -123.1271 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290510 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.3 | Base SH | 08W | ESTS | Estimating | Y | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1887 | -123.0323 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290509 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1918 | -123.0344 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290507 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1963 | -123.0435 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290506 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 0 | 0 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2105 | -123.0641 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290503 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1157 | 0 | 0 | 1.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2248 | -123.0882 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290502 | REMG 436 - POTTER VALLEY 1105, CCA-SCP | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.228 | -123.0887 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290501 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2328 | -123.1053 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290500 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.7 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2537 | -123.1188 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290299 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.6 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299 | 0 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2594 | -123.1172 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290298 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.5 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2619 | -123.1148 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290297 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.4 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2696 | -123.1053 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290296 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2715 | -123.097 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35290295 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2738 | -123.0944 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35254074 | CWSP POTTER VALLEY PH 1105 LR1904 PH2 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0.56989 | 0 | 0 | 0.56989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2
35254073 | CWSP POTTER VALLEY PH 1105 LR1904 PH1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 1.0676 | 0 | 0 | 1.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 | WDRM v2 | 0 | 75 | 0.37685 | 0 | 573 | 0.0046795 | Tier 2 & 3
35290514 | CWSP - HIGHLANDS 1102 LR623120 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9794 | -122.6125 | WDRM v2 | 0 | 74 | 0.3774 | 0 | 1256 | 0.00146 | Tier 2
35290513 | CWSP - HIGHLANDS 1102 LR623120 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0201 | 0 | 0 | 2.0201 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9769 | -122.6124 | WDRM v2 | 0 | 74 | 0.3774 | 0 | 1256 | 0.00146 | Tier 2
35290512 | CWSP - HIGHLANDS 1102 LR623120 PH1.3 | Base SH | 08W | ADER | Estimating | Y | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.06 | 0 | 0 | 2.06 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9612 | -122.6089 | WDRM v2 | 0 | 74 | 0.3774 | 0 | 1256 | 0.00146 | Tier 2
35290511 | CWSP - HIGHLANDS 1102 LR623120 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2799 | 0 | 0 | 1.2799 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.979 | -122.6124 | WDRM v2 | 0 | 74 | 0.3774 | 0 | 1256 | 0.00146 | Tier 2
35254072 | CWSP - HIGHLANDS 1102 LR 623120 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9544 | -122.6079 | WDRM v2 | 0 | 74 | 0.3774 | 0 | 1256 | 0.00146 | Tier 2
35278888 | +X22: CWSP - PASO ROBLES 1103 LRN54 PH2. | Base SH | 08W | UNSC | Ready for Construction | Y | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6848 | -120.73 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35278887 | +X22: CWSP -PASO ROBLES 1103 LRN54 PH2.6 | Base SH | 08W | CONS | In-Construction | Y | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 1.4799 | 0 | 0 | 1.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6819 | -120.738 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35278884 | +CWSP - PASO ROBLES 1103 LRN54 PH2.3 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 2.7701 | 0 | 0 | 2.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6807 | -120.7554 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35278883 | +CWSP - PASO ROBLES 1103 LRN54 PH2.2 | Base SH | 08W | CONS | In-Construction | Y | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 1.81 | 0 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6795 | -120.745 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35278882 | +CWSP - PASO ROBLES 1103 LRN54 PH1.4 | Base SH | 08W | CONS | In-Construction | Y | 2.6322 | 0 | 0 | 2.6322 | 1.7252 | 0 | 0 | 1.7252 | 0.90701 | 0 | 0 | 0.90701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6747 | -120.7423 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35278881 | +CWSP - PASO ROBLES 1103 LRN54 PH1.3 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 2.6799 | 0 | 0 | 2.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6635 | -120.7259 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1.1 | Base SH | 08W | CONS | In-Construction | Y | 2.6725 | 0 | 0 | 2.6725 | 2.5458 | 0 | 0 | 2.5458 | 0.1267 | 0 | 0 | 0.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6543 | -120.7258 | WDRM v2 | 0 | 69 | 0.38568 | 0 | 940 | 0.0024787 | Tier 2
35301114 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8694 | -120.979 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35301113 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8632 | -120.9814 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35301112 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0.067235 | 0.52576 | 0 | 0.59299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35300934 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6409 | 0 | 0 | 1.6409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8708 | -120.9825 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35300933 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293847 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0 | 0 | 0.38636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8704 | -121.0217 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293677 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71989 | 0 | 0 | 0.71989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8918 | -120.9988 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293676 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.6 | Base SH | 08W | ESTS | Estimating | Y | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8745 | -121.0198 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293675 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9528 | 0 | 0 | 1.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8795 | -121.0164 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293674 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8882 | -121.0144 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293673 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7534 | 0 | 0 | 1.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8939 | -121.0149 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293672 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0322 | 0 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9075 | -121.0168 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293509 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0441 | 0 | 0 | 2.0441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8608 | -120.993 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293507 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8774 | -120.9979 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293506 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72083 | 0 | 0 | 0.72083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8803 | -121.0037 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35293505 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3019 | 0 | 0 | 1.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8782 | -120.9979 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35254069 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3778 | 0 | 0 | 1.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8777 | -120.9979 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35254068 | CWSP - MOUNTAIN QUARRIES 2101 CB PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | Base SH | 08W | ESTS | Estimating | Y | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0.039962 | 0.43996 | 0 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 | 0 | 68 | 0.38665 | 0 | 106 | 0.017565 | Tier 2
35320443 | CWSP - JAMESON 1102865502 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.236 | -122.1528 | WDRM v2 | 0 | 67 | 0.38957 | 0 | 1581 | 0.00088788 | Tier 2
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 | 0 | 64 | 0.39138 | 0 | 768 | 0.0032459 | Tier 2
35334750 | PSPS - VACAVILLE 1108 LR8762 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 | 0 | 64 | 0.39138 | 0 | 768 | 0.0032459 | Tier 2
35320334 | PSPS - VACAVILLE 1108 LR8762 PH 2.0 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 | 0 | 64 | 0.39138 | 0 | 768 | 0.0032459 | Tier 2
35320333 | PSPS - VACAVILLE 1108 LR8762 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 | 0 | 64 | 0.39138 | 0 | 768 | 0.0032459 | Tier 2
35277931 | CWSP - AUBERRY 1101CB PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 0 | 3.51 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0503 | -119.4639 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35277930 | CWSP - AUBERRY 1101CB PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0528 | -119.4629 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35277929 | CWSP - AUBERRY 1101CB PH2.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 2.5536 | 0 | 0 | 2.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0578 | -119.4739 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35277926 | AUBERRY 1101CB PH1.3 | Base SH | 08W | CONS | In-Construction | Y | 3.4381 | 0 | 0 | 3.4381 | 2.1538 | 0 | 0 | 2.1538 | 1.2843 | 0 | 0 | 1.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0749 | -119.4852 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35277925 | CWSP - AUBERRY 1101CB PH1.2 | Base SH | 08W | CONS | In-Construction | Y | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35254079 | X22: CWSP - AUBERRY 1101 CB PH2.1 | Base SH | 08W | CONS | In-Construction | Y | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0677 | -119.4958 | WDRM v2 | 0 | 63 | 0.39206 | 0 | 2126 | 0.00047477 | Tier 2
35250738 | CWSP - COARSEGOLD 21045310 PH 2.3 | Base SH | 08W | UNSC | Ready for Construction | Y | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 3.4856 | 0 | 0 | 3.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35250737 | CWSP - COARSEGOLD 21045310 PH 2.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 2.8564 | 0 | 0 | 2.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35249874 | CWSP - COARSEGOLD 21045310 PH 3.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7163 | 0 | 0 | 4.7163 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35249873 | CWSP - COARSEGOLD 21045310 PH 3.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7049 | 0 | 0 | 3.7049 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35240163 | CWSP - COARSEGOLD 21045310 PH 3.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1735 | 0 | 0 | 2.1735 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | Base SH | 08W | UNSC | Ready for Construction | Y | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 2.1252 | 0 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2285 | -119.7103 | WDRM v2 | 0 | 61 | 0.39401 | 0 | 1416 | 0.001126 | Tier 2
35311135 | CWSP - POTTER VALLEY PH 1104 95878 PH1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35311134 | CWSP - POTTER VALLEY PH 1104 95878 PH1.8 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35311133 | CWSP - POTTER VALLEY PH 1104 95878 PH1.7 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35311132 | CWSP - POTTER VALLEY PH 1104 95878 PH1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35311131 | CWSP - POTTER VALLEY PH 1104 95878 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87008 | 0 | 0 | 0.87008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35310715 | CWSP - POTTER VALLEY PH 1104 95878 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35310714 | CWSP - POTTER VALLEY PH 1104 95878 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35310713 | CWSP - POTTER VALLEY PH 1104 95878 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35250579 | CWSP - POTTER VALLEY PH 1104 95878 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 | WDRM v2 | 0 | 60 | 0.3965 | 0 | 2459 | 0.00032085 | Tier 2 & 3
35283340 | CWSP HARTLEY 1101 LR698 PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.105 | -122.9581 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35283199 | CWSP HARTLEY 1101 LR698 PH 1.5 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0813 | -122.9625 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35283198 | CWSP HARTLEY 1101 LR698 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35283197 | CWSP HARTLEY 1101 LR698 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 2.4381 | 0 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0946 | -122.9632 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35283196 | CWSP HARTLEY 1101 LR698 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 1.3345 | 0 | 0 | 1.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.095 | -122.9656 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35250576 | CWSP - HARTLEY 1101 LR 698 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 1.217 | 0 | 0 | 1.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0803 | -122.9513 | WDRM v2 | 0 | 58 | 0.39723 | 0 | 486 | 0.0056859 | Tier 2
35274597 | CWSP MARIPOSA 2101 CB PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0.63295 | 0 | 0 | 0.63295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5054 | -120.0067 | WDRM v2 | 0 | 57 | 0.39837 | 0 | 82 | 0.019246 | Tier 2
35250573 | CWSP - MARIPOSA 2101 CB | Base SH | 08W | ESTS | Estimating | Y | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 1.7591 | 0 | 0 | 1.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5046 | -120.0081 | WDRM v2 | 0 | 57 | 0.39837 | 0 | 82 | 0.019246 | Tier 2
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35279122 | CWSP - STANISLAUS 1701 CB PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0.90909 | 0 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1379 | -120.3707 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35279121 | CWSP - STANISLAUS 1701 CB PH1.4 | Base SH | 08W | CONS | In-Construction | Y | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0.77235 | 0 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1797 | -120.3786 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 1.004 | 0 | 1.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35250578 | CWSP - STANISLAUS 1701 CB PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 2.4174 | 0 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1376 | -120.3702 | WDRM v2 | 0 | 56 | 0.40353 | 0 | 95 | 0.018647 | Tier 2 & 3
35219591 | CWSP - OLETA 1101754718 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | Amador | 38.4692 | -120.8536 | WDRM v2 | 0 | 54 | 0.40712 | 0 | 2197 | 0.00043538 | Tier 2
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Base SH | 08W | UNSC | Ready for Construction | Y | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 | 0 | 52 | 0.41883 | 0 | 86 | 0.018983 | Tier 2
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 1.7034 | 0 | 0 | 1.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 | 0 | 52 | 0.41883 | 0 | 86 | 0.018983 | Tier 2
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 2.4055 | 0 | 0 | 2.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WDRM v2 | 0 | 52 | 0.41883 | 0 | 86 | 0.018983 | Tier 2
35280362 | CWSP - MARIPOSA 2102440236 PH1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0.047348 | 0.13258 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 | 0 | 50 | 0.4205 | 0 | 400 | 0.0069412 | Tier 2 & 3
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | Base SH | 08W | DOCC | In-Construction | Y | 0.88182 | 0 | 0.27973 | 1.1616 | 0.87045 | 0 | 0.27973 | 1.1502 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9482 | WDRM v2 | 0 | 50 | 0.4205 | 0 | 400 | 0.0069412 | Tier 2 & 3
35316537 | CWSP - OREGON TRAIL 110335002 PH1.7 | Base SH | 08W | ESTS | Estimating | Y | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20152 | 0 | 0.20152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.624 | -122.3049 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Base SH | 08W | CONS | In-Construction | Y | 1.2771 | 0 | 0 | 1.2771 | 1.2277 | 0 | 0 | 1.2277 | 0.049432 | 0 | 0 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Base SH | 08W | CONS | In-Construction | Y | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042614 | 0.55985 | 0 | 0.60246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Base SH | 08W | CONS | In-Construction | Y | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 2.8206 | 0 | 0 | 2.8206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | Base SH | 08W | CONS | In-Construction | Y | 0.71345 | 0 | 0 | 0.71345 | 0.56856 | 0 | 0 | 0.56856 | 0.14489 | 0 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234396 | X22: CWSP - OREGON TRAIL 110335002 PH5.5 | Base SH | 08W | CONS | In-Construction | Y | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 1.5604 | 0 | 0 | 1.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | Base SH | 08W | CONS | In-Construction | Y | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 1.79 | 0 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | Base SH | 08W | CONS | In-Construction | Y | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 2.42 | 0 | 0 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | Base SH | 08W | UNSC | Ready for Construction | Y | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 1.5875 | 0 | 0 | 1.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | Base SH | 08W | CONS | In-Construction | Y | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 1.5468 | 0 | 0 | 1.5468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35233951 | X22: CWSP - OREGON TRAIL 110335002 PH1.6 | Base SH | 08W | CONS | In-Construction | Y | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 1.6214 | 0 | 0 | 1.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5701 | 0 | 4.5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35233949 | X22: CWSP - OREGON TRAIL 110335002 PH1.4 | Base SH | 08W | CONS | In-Construction | Y | 1.7706 | 0 | 0 | 1.7706 | 0.12955 | 0 | 0 | 0.12955 | 1.6411 | 0 | 0 | 1.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6722 | 0 | 4.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Base SH | 08W | CONS | In-Construction | Y | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7973 | 0 | 6.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Base SH | 08W | CONS | In-Construction | Y | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6299 | -122.2445 | WDRM v2 | 0 | 49 | 0.42185 | 0 | 2405 | 0.00034131 | Tier 2
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 1.7 | 0 | 0 | 1.7 | 1.6364 | 0 | 0 | 1.6364 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.362 | -123.1283 | WDRM v2 | 0 | 43 | 0.44262 | 0 | 1733 | 0.00073797 | Tier 2
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | Base SH | 08W | UNSC | Ready for Construction | Y | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 | 0 | 42 | 0.44642 | 0 | 383 | 0.0073117 | Tier 3
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 | 0 | 42 | 0.44642 | 0 | 383 | 0.0073117 | Tier 3
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 | 0 | 42 | 0.44642 | 0 | 383 | 0.0073117 | Tier 3
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Base SH | 08W | DOCC | In-Construction | Y | 3.6491 | 0 | 0 | 3.6491 | 3.5733 | 0 | 0 | 3.5733 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | WDRM v2 | 0 | 37 | 0.46772 | 0 | 1554 | 0.00091401 | Tier 2
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 0 | 0.4214 | 0 | 0.4214 | 0 | 0.41477 | 0 | 0.41477 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 | 0 | 29 | 0.52987 | 0 | 2717 | 0.0002242 | Tier 2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 0.92822 | 0 | 0.86723 | 1.7955 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.86723 | 0.91742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4631 | -121.5149 | WDRM v2 | 0 | 29 | 0.52987 | 0 | 2717 | 0.0002242 | Tier 2
35231631 | OCGC-CWSP-HIGHLANDS 1102628 PH 1.13 | Base SH | 08W | FICL | In-Construction | Y | 0.44867 | 0 | 0 | 0.44867 | 0.36439 | 0 | 0 | 0.36439 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 1.2165 | 0 | 0 | 1.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231628 | REMG 729 - HIGHLANDS 1102, WATERTROUGH | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 | 0.39867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231626 | OCGC_X22: CWSP-HIGHLANDS 1102628 PH 1.8 | Base SH | 08W | MAPP | In-Construction | Y | 0.78295 | 0 | 0.64962 | 1.4326 | 0.78295 | 0 | 0.60417 | 1.3871 | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231624 | REMG 728 - HIGHLANDS 1102, BUCKSKIN WAY | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231623 | REMG 205 - HIGHLANDS 1102, OASIS | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231622 | REMG 706 - HIGHLANDS 1102, INDIAN CREEK | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 2.7275 | 0 | 0 | 2.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | 0 | 27 | 0.5487 | 0 | 29 | 0.026126 | Tier 2 & 3
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 3.2598 | 0 | 0 | 3.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 | 0 | 21 | 0.61454 | 0 | 571 | 0.00471 | Tier 2
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 0.11288 | 1.8303 | 0.028409 | 1.9716 | 0.11288 | 1.8019 | 0 | 1.9148 | 0 | 0.028409 | 0.028409 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 | 0 | 21 | 0.61454 | 0 | 571 | 0.00471 | Tier 2
35299137 | CWSP HARTLEY 1101 LR789752 PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0.57292 | 0 | 0 | 0.57292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.067 | -122.9672 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 595 | 0.0044545 | Tier 2
35299136 | CWSP HARTLEY 1101 LR789752 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0.67197 | 0 | 0 | 0.67197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0716 | -122.9638 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 595 | 0.0044545 | Tier 2
35299135 | CWSP HARTLEY 1101 LR789752 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0.92102 | 0 | 0 | 0.92102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0722 | -122.9571 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 595 | 0.0044545 | Tier 2
35299134 | CWSP HARTLEY 1101 LR789752 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0.40303 | 0 | 0 | 0.40303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0704 | -122.9571 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 595 | 0.0044545 | Tier 2
35299133 | CWSP HARTLEY 1101 LR789752 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0.28144 | 0 | 0 | 0.28144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0729 | -122.9569 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 595 | 0.0044545 | Tier 2
35250575 | CWSP HARTLEY 1101 LR789752 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0.2428 | 0 | 0 | 0.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0636 | -122.9526 | WDRM v2 | 0 | 19 | 0.64187 | 0 | 2963 | 0.00014245 | Tier 2
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 | 0 | 18 | 0.65331 | 0 | 448 | 0.0062529 | Tier 2
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Base SH | 08W | CONS | In-Construction | Y | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 3.45 | 0 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | 0 | 14 | 0.71618 | 0 | 443 | 0.006302 | Tier 2 & 3
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Base SH | 08W | CONS | In-Construction | Y | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | 0 | 14 | 0.71618 | 0 | 443 | 0.006302 | Tier 2 & 3
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Base SH | 08W | CONS | In-Construction | Y | 0.57727 | 0 | 0 | 0.57727 | 0.13788 | 0 | 0 | 0.13788 | 0.43939 | 0 | 0 | 0.43939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | 0 | 14 | 0.71618 | 0 | 443 | 0.006302 | Tier 2 & 3
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Base SH | 08W | CONS | In-Construction | Y | 0 | 1.3212 | 0 | 1.3212 | 0 | 0.36136 | 0 | 0.36136 | 0 | 0.95985 | 0 | 0.95985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | 0 | 14 | 0.71618 | 0 | 443 | 0.006302 | Tier 2 & 3
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Base SH | 08W | CONS | In-Construction | Y | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 | 0 | 14 | 0.71618 | 0 | 443 | 0.006302 | Tier 2 & 3
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 | 0 | 11 | 0.73491 | 0 | 21 | 0.029234 | Tier 2 & 3
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 | 0 | 11 | 0.73491 | 0 | 21 | 0.029234 | Tier 2 & 3
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1 | Fire Rebuild | 08W | ADER | Estimating | Y | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9107 | -121.3275 | WDRM v2 | 0 | 11 | 0.73491 | 0 | 21 | 0.029234 | Tier 2 & 3
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57614 | 0 | 0 | 0.57614 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.93 | -122.7428 | WDRM v2 | 0 | 9 | 0.87629 | 0 | 735 | 0.0034918 | Tier 3
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0.73068 | 0 | 0 | 0.73068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 | 0 | 8 | 0.91632 | 0 | 392 | 0.007089 | Tier 2
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033333 | 1.3201 | 0 | 1.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 | 0 | 8 | 0.91632 | 0 | 392 | 0.007089 | Tier 2
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.321 | 0 | 0 | 1.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 | 0 | 8 | 0.91632 | 0 | 392 | 0.007089 | Tier 2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 | 0 | 7 | 1.2524 | 0 | 48 | 0.022602 | Tier 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 | 0 | 7 | 1.2524 | 0 | 48 | 0.022602 | Tier 3
35058839 | STS-POLE_BROK_REPL - 17 STARWOOD DR REDW | Other | 07D | DOCC | In-Construction | Y | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0.1625 | 0 | 0 | 0.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3801 | -122.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35342302 | CWSP - LINCOLN 1104 LR997576 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0278 | -121.2938 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2
35334404 | FRRB - PT MORETTI 1101 P1S2 310SWAN | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0671 | -122.2231 | WDRM v2 | 0 | 1393 | 0.033758 | 0 | 2485 | 0.00031335 | Tier 2
35332878 | CWSP - LINCOLN 1104 LR997576 PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1021 | 0 | 0 | 2.1021 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0128 | -121.263 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2
35332876 | CWSP - LINCOLN 1104 LR997576 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.307 | 0 | 0 | 2.307 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0181 | -121.2717 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2
35332874 | CWSP - LINCOLN 1104 LR997576 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7729 | 0 | 0 | 1.7729 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 39.0224 | -121.2874 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2
35332872 | CWSP - LINCOLN 1104 LR997576 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0337 | -121.3086 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2
35320453 | CWSP - LINCOLN 1104 LR997576 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Sheridan | Placer | 39.0371 | -121.3366 | WDRM v2 | 0 | 693 | 0.11252 | 0 | 3098 | 0.00010977 | Tier 2

## Status (hidden)
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles

## Category (hidden)
Category | Description
Base SH | Planned projects in System Hardening program
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Other | Non-08W projects (New Busines, WRO, Capacity, Rule 20A, etc.)
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Idle Facilities | Removal of Primary Conductor in HFTD

## ProjectType (hidden)
Category | Description | DO NOT SUBMIT: ProjectType | Description
Base SH | Planned projects in System Hardening program | CWSP 2022-2023 | Community Wildfire Safety Program for projects aimed for 2022-2023
|  | CWSP - 2023 ICUG | Incremental Undergrounding (ICUG) for 2023
|  | ECOP | EC Tag Optimization
|  | ECOP - Top 20% | EC Tag Optimization in the top 20% of the 2021 risk model
|  | PRE | Projects that had poles in the ground and construction had begun, based on 2018 risk model
|  | PSPS - Community Resiliency | Public Safety Power Shutoff projects
|  | PSPS - 2023 ICUG | Public Safety Power Shutoff projects - Incremental Undergrounding (ICUG) for 2023
|  | PSPS – Scoped | Public Safety Power Shutoff projects that had been scoped, based on 2018 risk model
|  | PSS Approved | Public Safety Specialists approved projects
|  | Remote Grid | Remote Grid projects
|  | Remote Grid Pilot | Remote Grid projects part of the Pilot program
|  | Storm Rebuild | Storm Rebuild projects
|  | Top 20% MAVF CPZ | Top 20% of Multi-Attribute Value Function Circuit Protection Zones based on the 2021 risk model
|  | Top 250 miles | Top 250 miles based on the 2021 risk model
|  | Top 50 Miles | Top 50 miles based on the 2021 risk model
Fire Rebuild | Hardening Scope as a result of fires in HFTD | FRRB - OH – 2021 | Fire Rebuild - Overhead Hardening
|  | FRRB - REMG – 2021 | Fire Rebuild - Remote Grid Projects
|  | FRRB - UG – 2021 | Fire Rebuild - Underground Hardening
|  | FRRB - UG - 2022 | Fire Rebuild - Underground Hardening
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH | V3 Tranche 1 | Bundled Circuit Segments based on WFE (Wildfire Feasibility Efficiency) calculation
Other | Non-08W projects (New Busines, WRO, Capacity, Rule 20A, etc.) | Other | Non-08W projects (New Busines, WRO, Capacity, Rule 20A, etc.)
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds | Butte Rebuild | Paradise and Surrounding Areas
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds | Greenville Rebuild | Rebuild within City of Greenville as a result of Dixie Fire (majority of Dixie rebuild is captured in Fire Rebuild category - HFTD work)
Idle Facilities | Removal of Primary Conductor in HFTD | Idle Facilities | Electric Distribution line with Primary Conductor in HFTD de-energized and removed

## Agency list _Observer request (hidden)
Order Number | Project: Project Name | California Department of Transportation (Caltrans) | United States Forest Service (USFS) | Bureau of Land Management (BLM) | Bureau of Reclamation (BOR) | Federal Energy Regulatory Commission (FERC) | California Department of Parks and Recreation (State Parks) | California Department of Fish and Wildlife (CDFW) | State Water (California Department of Water Resources) | California State Lands Commission (State Lands) | Land Trusts | Conservation Easements | Midpeninsula Regional Open Space District (Open Space) | Match Validation to Workplan
35325226 | PSPS - PIT NO 3 21011482 PH 2.2 |  |  |  |  | Yes | [7 empty] | 407 | ** % is based on current understanding of the mileage in the DOT and the overlap
35234756 | ECOP - MIDDLETOWN 1101-H12-LR548-PH3.9 | Yes | [11 empty] | 668
35290504 | CWSP - POTTER VALLEY PH 1105 LR1904 PH3.5 | Yes | [11 empty] | 1021
35355173 | PSPS - PIT NO 3 2101CB PH 1.3 |  | Yes |  |  | Yes | [7 empty] | 58
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 |  | Yes | [10 empty] | 427
35332362 | CWSP ELK CREEK 1101 LR2002 PH 2.4-HOLD |  |  | Yes | [9 empty] | 802
35312543 | 35312543_PSPS - ELK CREEK 11012002 PH1_Scoping |  |  |  | Yes | [8 empty] | 808
35284365 | CWSP - STANISLAUS 1702 CB PH 1.3-HOLD | Yes | [11 empty] | 854
35325225 | PSPS PIT NO 3 21011482 PH 1.2-HOLD |  | Yes |  |  | Yes | [7 empty] | 408
35294729 | CWSP - Pit No 3 21011482 PH1_Scoping |  | Yes |  |  | Yes | [7 empty] | 411
35294730 | CWSP - Pit No 3 21011482 PH2_Scoping |  | Yes |  |  | Yes | [7 empty] | 410
35294728 | CWSP - Pit No 3 2101CB_Scoping |  | Yes |  |  | Yes | [7 empty] | 438
35355171 | PSPS PIT NO 3 21011482 PH 2.3-HOLD |  | Yes |  |  | Yes | [7 empty] | 59
35325224 | PSPS PIT NO 3 2101CB PH 1.2-HOLD |  | Yes |  |  | Yes | [7 empty] | 409
35312560 | PSPS - Wyandotte 1110980944_Scoping | Yes | [11 empty] | 532
35331306 | PSPS WYANDOTTE 1110 LR980944 PH1.2-HOLD | [7 empty] | Yes |  |  |  |  | 531
35342337 | FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN_Scoping | Yes |  |  |  |  | Yes | [6 empty] | 396
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | Yes | [11 empty] | 441
35342338 | FRRB - BIG BASIN 1102 UG5 LITTLEBASIN CG_Scoping | [5 empty] | Yes | [6 empty] | 389
35332868 | PSPS - CURTIS 1701 CB PH 1.2-HOLD | Yes | [11 empty] | 502
35342146 | PSPS - JAMESON 1102 LR65516 1.5-HOLD | [9 empty] | Yes |  |  | 566
35330248 | CWSP REDBUD 1101 708166 PH 1.6-HOLD | Yes | [11 empty] | 770
35299633 | PSPS - CLARK ROAD 1102514690 PH2_Scoping | [5 empty] | Yes | [6 empty] | 446
35342335 | FRRB - BIG BASIN 1102 UG3 HWY 236_Scoping | Yes |  |  |  |  | Yes | [6 empty] | 398
35342336 | FRRB - BIG BASIN 1102 UG2 CAMPGROUND_Scoping | [5 empty] | Yes | [6 empty] | 397
35279307 | FRRB - Gansner 11012424 UG PH1.2 | Yes | Yes | [10 empty] | 500
35279181 | 35279181 (08W) - FRRB - BUCKS CREEK 1102 CB PH1 (South) | Yes | Yes |  |  | Yes | [7 empty] | 765
35279182 | FRRB - BUCKS CREEK 1102CB PH 2 (North) | Yes | Yes |  |  | Yes | [7 empty] | 764
35280499 | FRRB - BUCKS CREEK 1102 CB PH 3 | Yes | Yes |  |  | Yes | [7 empty] | 763
35280560 | FRRB - BUCKS CREEK 1102 CB PH 4 | Yes | Yes |  |  | Yes | [7 empty] | 762
35292788 | FRRB -Big Meadows 21012476 UG ML PH1.2 | Yes | Yes |  |  | Yes | [7 empty] | 404
35316537 | CWSP - OREGON TRAIL 110335002 PH1.7-HOLD | Yes | [11 empty] | 1129
35274589 | CWSP - MARIPOSA 2101 LR 35244 PH1.2-HOLD | Yes | [11 empty] | 697
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3-HOLD | [9 empty] | Yes |  |  | 1084
35343741 | PSPS - DUNBAR 1101 440 PH 1.3-HOLD | Yes | [11 empty] | 436
35282166 | FRRB - Spanish Creek UG ML PH1.1 | Yes | Yes | [10 empty] | 485
35254067 | MOUNTAIN QUARRIES 2101 - CB PH1_Scoping | Yes |  |  |  |  | Yes | [6 empty] | 1081
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3-HOLD | [5 empty] | Yes | [6 empty] | 444
35329471 | PSPS HIGHLANDS 1104 CB PH 1.2-HOLD | Yes | [11 empty] | 43
35317399 | 35317399_CWSP - REDBUD 1101323962 Ph 2_Scoping | Yes | [11 empty] | 711
35332363 | CWSP ELK CREEK 1101 LR2002 PH 2.5-HOLD | [8 empty] | Yes |  |  |  | 801
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Yes | [11 empty] | 548
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4-HOLD | [10 empty] | Yes |  | 741
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3-HOLD |  |  | Yes | [9 empty] | 896
35374685 | FRRB - MARIPOSA 210110240 TL-1 |  | Yes | [10 empty] | 34
35343397 | PSPS - WYANDOTTE 1110 LR980944 PH1.9-HOLD | [5 empty] | Yes | [6 empty] | 524
35283938 | CWSP – Woodside 1101 FS 775949 Scoping Session | [11 empty] | Yes | 504
35312546 | 35312546_PSPS - FLINT 1101CB & 40666_Scoping |  |  |  | Yes |  | Yes | [6 empty] | 157
35305308 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7-HOLD | Yes | [11 empty] | 883
35299629 | PSPS - CLARK ROAD 1102CB_Scoping | Yes | [11 empty] | 840
35374682 | FRRB - MARIPOSA 210110240 ML-1 | Yes | Yes | [10 empty] | 37
35320462 | PSPS - JAMESON 1105371694-HOLD | [9 empty] | Yes |  |  | 433
35334467 | PSPS - VOLTA 11011516 PH 1.5-HOLD | [6 empty] | Yes |  |  |  | Yes |  | 640
35312542 | 35312542_PSPS - DUNBAR 1101440_Scoping | Yes | [11 empty] | 437
35280362 | CWSP - MARIPOSA 2102440236 PH1.4-HOLD | Yes | [11 empty] | 1127
35334466 | PSPS - VOLTA 11011516 PH 1.4-HOLD | [10 empty] | Yes |  | 641
35320466 | CWSP - WILLOW CREEK 11032936-HOLD | Yes | Yes | [10 empty] | 466
35311896 | 35311896_CWSP - BELL 1108 - LR2202 - Ph1_Scoping | Yes | [9 empty] | Yes |  | 990
35312554 | 35312554_PSPS - TEJON 11023751 PH1_Scoping | Yes | [11 empty] | 585
35312555 | 35312555_PSPS - TEJON 1102732836 PH1_Scoping | Yes |  |  |  |  | Yes | [6 empty] | 623
35314416 | 35314416_CWSP - BELL 1108 LR2202 PH3_Scoping | Yes | [8 empty] | Yes | Yes |  | 988
35320444 | 35320444_PSPS - GOLDTREE 1105CB_Scoping | Yes | [11 empty] | 506
35321445 | 35321445_PSPS - TEJON 11023751 PH2_Scoping | Yes | [9 empty] | Yes |  | 584
35367418 | 35367418_CWSP - Brunswick 11062104 PH 1_Scoping | Yes | [11 empty] | 50
35367462 | 35367462_CWSP - Brunswick 110651486 PH 1_Scoping | Yes | [11 empty] | 93
35367516 | 35367516_CWSP - Silverado 210478268 PH 1_Scoping | [9 empty] | Yes | Yes |  | 274
35372259 | 35372259_CWSP_Pine Grove 1101CB_Scoping | Yes | [11 empty] | 405
35372460 | 35372460_CWSP_Pine Grove 11013166 PH 1_Scoping | Yes | [11 empty] | 225
35372461 | 35372461_CWSP-TIGER CREEK 0201-CB & 320746_Scoping |  | Yes | Yes |  | Yes | [5 empty] | Yes |  | 378
35372464 | 35372464_CWSP - Antler 11011520_Scoping | Yes | Yes | [10 empty] | 295
35373585 | 35373585_CWSP - Brunswick 11062104 PH 2_Scoping | Yes | [11 empty] | 49
35373589 | 35373589_CWSP - Brunswick 110651486 PH 2_Scoping | Yes | [9 empty] | Yes |  | 92
35373635 | 35373635_CWSP - PINE GROVE 1102 LR13438 PH 2_Scoping |  |  | Yes | [9 empty] | 164
35373703 | 35373703_CWSP - PUEBLO 2103678 PH 4_Scoping | [9 empty] | Yes | Yes |  | 139
35373704 | 35373704_CWSP - Silverado 210478268 PH 2_Scoping | [8 empty] | Yes |  |  |  | 273
35373708 | 35373708_CWSP - ANTLER 11011384 PH 2_Scoping |  | Yes | [10 empty] | 374
35372465 | CWSP - ANTLER 11011384-HOLD |  | Yes | [10 empty] | 375
35372463 | CWSP - ANTLER 1101CB-HOLD |  | Yes | [10 empty] | 288
35334232 | CWSP - BELL 1108 LR2202 PH 1.3-HOLD | Yes | [11 empty] | 973
35334234 | CWSP - BELL 1108 LR2202 PH 1.5-HOLD | Yes | [11 empty] | 971
35373590 | CWSP - Brunswick 110651486 PH 3_Scoping | Yes | [11 empty] | 91
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | Yes |  | Yes | [9 empty] | 1171
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  |  | Yes | Yes | [8 empty] | 1207
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  |  | Yes | Yes | [8 empty] | 1206
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Yes | [11 empty] | 1204
35305303 | CWSP - MOUNTAIN QUARRIES 2101 LR 1350 Ph 1.2 | Yes | [11 empty] | 888
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Yes | [11 empty] | 1145
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | Yes | [11 empty] | 1143
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | Yes | [11 empty] | 1141
35367511 | CWSP - PINE GROVE 110245292-HOLD | Yes | [11 empty] | 153
35397961 | CWSP - PUEBLO 2103678 PH 4.3-HOLD | [9 empty] | Yes | Yes |  | 119
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | Yes | Yes | [10 empty] | 1120
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | [10 empty] | Yes |  | 1117
35283346 | CWSP - UPPER LAKE 1101 1276 PH 1.5 |  |  | Yes | [9 empty] | 791
35286103 | CWSP ? Big Meadows 2101 LR 2510 Scoping Session | Yes | Yes |  |  | Yes | [7 empty] | 19
35311596 | CWSP BIG MEADOWS 2101 2510 PH1.2 |  | Yes |  |  | Yes | [7 empty] | 18
35311626 | CWSP BIG MEADOWS 2101 2510 PH1.3 |  | Yes |  |  | Yes | [7 empty] | 17
35311627 | CWSP BIG MEADOWS 2101 2510 PH1.4 |  | Yes |  |  | Yes | [7 empty] | 7
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Yes | Yes | [10 empty] | #N/A
35373526 | ECOP - FORESTHILL 1101 - H02-LR1802 - PH 3_Scoping |  |  | Yes | [9 empty] | 203
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Yes | [11 empty] | 682
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Yes | [11 empty] | 667
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Yes | [11 empty] | 665
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Yes | [11 empty] | 690
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Yes | [11 empty] | 689
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | Yes | [11 empty] | 543
35292784 | FRRB - BUCKS CREEK 1102 CB PH 5 | Yes | Yes | [10 empty] | 517
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | [5 empty] | Yes |  |  |  |  | Yes |  | 422
35297695 | FRRB - WILLOW CREEK 11032936 - UG - TL1 | Yes | Yes | [10 empty] | 470
35297696 | FRRB - WILLOW CREEK 11032936 - UG - TL2 | Yes | Yes | [10 empty] | 469
35297697 | FRRB - WILLOW CREEK 11032936 - UG - TL3 | Yes | Yes | [10 empty] | 468
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | Yes | [11 empty] | 465
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | Yes | Yes | [10 empty] | 475
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | Yes | Yes | [10 empty] | 467
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | Yes | Yes | [10 empty] | 473
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | Yes | Yes | [10 empty] | 472
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | Yes | Yes | [10 empty] | 471
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | Yes | [11 empty] | 403
35224712 | FRRB- Dixie_Bucks Creek 1101 Phase 2 | Yes | Yes |  |  | Yes | [7 empty] | 1200
35224713 | FRRB- Dixie-Bucks Creek 1101 Phase 3 | Yes | Yes |  |  | Yes | [7 empty] | 1199
35279985 | FRRB-BIG MEADOWS 2101 RND VALLY RES |  | Yes | [10 empty] | 546
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Yes | [11 empty] | 426
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | Yes | [9 empty] | Yes |  | 425
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | Yes | [11 empty] | 424
35145540 | PSPS - FROGTOWN 1702 - CB | Yes | [11 empty] | 486
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Yes | [11 empty] | 1082
35335288 | PSPS - TEJON 1102 LR3751 PH 1.2-HOLD | Yes | [11 empty] | 583
35335289 | PSPS - TEJON 1102 LR3751 PH 1.3-HOLD | Yes | [11 empty] | 582
35342312 | PSPS - TEJON 1102 LR732836 PH 1.3-HOLD | Yes | [11 empty] | 620
35342314 | PSPS - TEJON 1102 LR732836 PH 1.5-HOLD | Yes | [11 empty] | 618
35342315 | PSPS - TEJON 1102 LR732836 PH 2.2-HOLD | Yes | [11 empty] | 617
35342318 | PSPS - TEJON 1102 LR732836 PH 2.5-HOLD | Yes | [11 empty] | 614
35342308 | PSPS - TEJON 11023751 PH 2.3-HOLD | [10 empty] | Yes |  | 580
35364336 | PSPS - VOLTA 11011516 PH 1.10-HOLD | Yes | [11 empty] | 631
35364337 | PSPS - VOLTA 11011516 PH 1.11 | Yes | [11 empty] | 630
35364339 | PSPS - VOLTA 11011516 PH 1.12-HOLD | Yes | [11 empty] | 629
35364440 | PSPS - VOLTA 11011516 PH 1.13-HOLD | Yes | [5 empty] | Yes | [5 empty] | 628
35364442 | PSPS - VOLTA 11011516 PH 1.14-HOLD | Yes | [11 empty] | 627
35364446 | PSPS - VOLTA 11011516 PH 1.15-HOLD | Yes | [11 empty] | 626
35364448 | PSPS - VOLTA 11011516 PH 1.16-HOLD | [6 empty] | Yes | [5 empty] | 625
35364332 | PSPS - VOLTA 11011516 PH 1.7-HOLD | Yes | [5 empty] | Yes |  |  |  | Yes |  | 634
35364333 | PSPS - VOLTA 11011516 PH 1.8-HOLD | Yes | [9 empty] | Yes |  | 633
35364334 | PSPS - VOLTA 11011516 PH 1.9-HOLD | Yes | [9 empty] | Yes |  | 632
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Yes | [11 empty] | 1150
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Yes | [11 empty] | 1018
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Yes | [11 empty] | 679
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Yes | [11 empty] | 671
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Yes | [11 empty] | 680
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | Yes | [11 empty] | 1172

## Data Pivot Summaries (hidden)
Undergrounding by County Summary | [5 empty] | Undergrounding Portfolio Summary | [5 empty] | Undergounding Only Summary - avg. mean risk score
Row Labels | 2023 | 2024 | 2025 | 2026 | Total | Row Labels | 2023 | 2024 | 2025 | 2026 | Total | Average of v3 Mean Risk | Column Labels
Alameda | 0 | 1.4576 | 0 | 0 | 1.4576 | Base SH | 356.3963 | 115.3326 | 63.6284 | 18.6746 | 554.0318 | Row Labels | 2023 | 2024 | 2025 | 2026 | Grand Total
Amador | 0.052841 | 40.057 | 61.392 | 87.196 | 188.6979 | Community Rebuild | 77.7009 | 98.7981 | 0 | 0 | 176.4991 | Base SH | 0.0070687 | 0.0065297 | 0.0070802 | 0.0054967 | 0.0069268
Butte | 112.5877 | 124.7604 | 80.5199 | 120.0398 | 437.9077 | Fire Rebuild | 77.5087 | 7.8307 | 2.9797 | 1.9691 | 90.2883 | Fire Rebuild | 0.0062964 | 0.0039559 | 0.0038079 | 0.0037338 | 0.005852
Calaveras | 15.636 | 24.5744 | 74.613 | 83.175 | 197.9984 | Other | 0 | 6.9864 | 0.015341 | 0.37879 | 7.3805 | Other |  | 0.0024893 | 0.0013011 | 0.023649 | 0.0053424
Contra Costa | 2.5083 | 1.8845 | 0 | 20.6799 | 25.0727 | Targeted UG | 22.7349 | 359.4579 | 616.3603 | 859.924 | 1858.4771 | Targeted UG | 0.00905 | 0.014025 | 0.013353 | 0.017851 | 0.015292
El Dorado | 14.1237 | 106.2311 | 109.3699 | 120.6467 | 350.3714 | Grand Total | 534.3408 | 588.4057 | 682.9839 | 880.9464 | 2686.6767 | Grand Total | 0.0069425 | 0.00993 | 0.01175 | 0.016896 | 0.010404
Fresno | 0.76818 | 0 | 0 | 0.41496 | 1.1831
Glenn | 19.1348 | 0 | 0 | 0 | 19.1348 | System Hardening Portfolio Summary
Humboldt | 0 | 0 | 0 | 0 | 0 | Row Labels | 2023 | 2024 | 2025 | 2026 | Total
Kern | 0 | 21.2388 | 19.857 | 8.1835 | 49.2792 | Base SH | 580.0977 | 293.3992 | 226.0693 | 19.1587 | 1118.7248
Lake | 68.722 | 21.2701 | 27.3659 | 23.35 | 140.708 | Fire Rebuild | 82.3718 | 8.0286 | 4.593 | 1.9691 | 96.9625 | Undergrounding
Madera | 0 | 0 | 0 | 0 | 0 | Idle Facilities | 8.654 | 0.15852 | 0 | 0 | 8.8125 | - UG SH, Commnity and fire rebuild, other, Target UG
Marin | 1.3843 | 0 | 0 | 0 | 1.3843 | Other | 2.5756 | 12.2303 | 0.2 | 0.37879 | 15.3847
Mariposa | 21.7905 | 14.87 | 31.71 | 31.38 | 99.7505 | Targeted UG | 22.7349 | 360.8278 | 618.7202 | 862.0239 | 1864.3068 | SH
Mendocino | 3.8559 | 0 | 0 | 0 | 3.8559 | Grand Total | 696.4338 | 674.6445 | 849.5824 | 883.5304 | 3104.1912 | OH SH, Underground (excluding community rebuild), Line removal
Monterey | 0 | 7.9701 | 20.1299 | 32.6799 | 60.7799
Napa | 0 | 41.398 | 47.5551 | 66.6699 | 155.623
Nevada | 15.281 | 64.9271 | 62.0108 | 66.5697 | 208.7887 | Overhead Portfolio Summary
Placer | 20.2945 | 51.6623 | 68.4218 | 86.03 | 226.4086 | Row Labels | 2023 | 2024 | 2025 | 2026 | Total
Plumas | 49.015 | 0 | 11.76 | 15.06 | 75.835 | Base SH | 176.7991 | 121.6409 | 141.5313 | 0.48409 | 440.4554
San Benito | 0 | 12.71 | 17.5 | 17.5 | 47.71 | Community Rebuild | 0 | 0 | 0 | 0 | 0
San Luis Obispo | 0 | 0.48 | 0 | 0 | 0.48 | Fire Rebuild | 4.7684 | 0.19792 | 1.6133 | 0 | 6.5795
San Mateo | 2.7439 | 2.9348 | 0 | 0 | 5.6788 | Idle Facilities | 0 | 0 | 0 | 0 | 0
Santa Barbara | 0 | 0.50644 | 0 | 0 | 0.50644 | Other | 2.5756 | 5.2439 | 0 | 0 | 7.8195
Santa Clara | 0 | 0 | 0 | 0 | 0 | Targeted UG | 0 | 0.12992 | 0 | 0.10996 | 0.23989
Santa Cruz | 2.389 | 2.65 | 1.7754 | 0 | 6.8144 | Grand Total | 184.1431 | 127.2127 | 143.1446 | 0.59405 | 455.0943
Shasta | 76.9154 | 20.2367 | 20.9595 | 42.7748 | 160.8864
Sierra | 0 | 0 | 0 | 23.81 | 23.81 | Line Removal Portfolio Summary
Solano | 61.5348 | 4.8451 | 2.9 | 0 | 69.2799 | Row Labels | 2023 | 2024 | 2025 | 2026 | Total
Sonoma | 0.3197 | 5.9379 | 0 | 0.33996 | 6.5975 | Base SH | 46.9023 | 56.4258 | 20.9095 | 0 | 124.2375
Tehama | 32.5124 | 15.6443 | 5.636 | 10.0761 | 63.8688 | Community Rebuild | 0 | 0 | 0 | 0 | 0
Trinity | 9.4242 | 0 | 2 | 0 | 11.4242 | Fire Rebuild | 0.094697 | 0 | 0 | 0 | 0.094697
Tulare | 0 | 0 | 0 | 0 | 0 | Idle Facilities | 8.654 | 0.15852 | 0 | 0 | 8.8125
Tuolumne | 3.3466 | 0 | 0 | 0 | 3.3466 | Other | 0 | 0 | 0.18466 | 0 | 0.18466
Yolo | 0 | 0 | 0 | 0 | 0 | Targeted UG | 0 | 1.24 | 2.3598 | 1.99 | 5.5898
Yuba | 0 | 0 | 17.5076 | 24.3701 | 41.8777 | Grand Total | 55.6509 | 57.8243 | 23.454 | 1.99 | 138.9192
Grand Total | 534.3408 | 588.2466 | 682.9839 | 880.9464 | 2686.5176
Annual Target | 350 | 450 | 550 | 750 | 2100
Buffer | 52.67% | 30.72% | 24.18% | 17.46% | 27.93%
WMP Workplan Miles | 534.3408 | 588.2466 | 682.9839 | 880.9464 | 2686.5176

## Observer Data Request_1-13-23 (hidden)
WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan -- filtered by Y | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | WMP Workplan | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP | do not submit in WMP
PG&E 2023-2026 System Hardening Workplan |  | Confidential
Data as of January 3, 2023
[24 empty] | 50 | 22 | 5 | 3 | 7 | 4 | 0 | 0 | 1 | 2 | 3 | 0
[7 empty] | 542.9357 | 8.5949 | 534.3408 | [14 empty] | Required Agency Support
Order | Order Description | Category | MAT | SAP Status | Status (see 2nd tab) | WMP GH-05 10k UG (Y/N) | Total Planned UG Miles | UG - 2022 Complete | UG - 2023 Forecast | Div | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (V2) | 2021-2023 Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | 2024-2026 Risk Rank (V3) | v3 Mean Risk | HFTD Tier | California Department of Transportation (Caltrans) | United States Forest Service (USFS) | Bureau of Land Management (BLM) | Bureau of Reclamation (BOR) | Federal Energy Regulatory Commission (FERC) | California Department of Parks and Recreation (State Parks) | California Department of Fish and Wildlife (CDFW) | State Water (California Department of Water Resources) | California State Lands Commission (State Lands) | Land Trusts | Conservation Easements | Midpeninsula Regional Open Space District (Open Space)
35385890 | CWSP - STANISLAUS 1702 LR1888 PH1.4 | Targeted UG | 3UG | ESTS | Estimating | Y | 1.383 | 0 | 1.383 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | STANISLAUS 17021888 | 2386 | 0.0026855 | STANISLAUS 17021888 | 379 | 0.0073524 | Tier 3
35385888 | CWSP - STANISLAUS 1702 LR1888 PH1.2 | Targeted UG | 3UG | ESTS | Estimating | Y | 1.5439 | 0 | 1.5439 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | STANISLAUS 17021888 | 2386 | 0.0026855 | STANISLAUS 17021888 | 379 | 0.0073524 | Tier 3
35380376 | PSPS - CORNING 1102 LR53184 PH 1.15 | Base SH | 08W | ESTS | Estimating | Y | 2.5799 | 0 | 2.5799 | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380373 | PSPS - CORNING 1102 LR53184 PH 1.12 | Base SH | 08W | ESTS | Estimating | Y | 1.79 | 0 | 1.79 | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380372 | PSPS - CORNING 1102 LR53184 PH 1.11 | Base SH | 08W | ESTS | Estimating | Y | 1.74 | 0 | 1.74 | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380371 | PSPS - CORNING 1102 LR53184 PH 1.10 | Base SH | 08W | ESTS | Estimating | Y | 2.8299 | 0 | 2.8299 | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380370 | PSPS - CORNING 1102 LR53184 PH 1.9 | Base SH | 08W | ESTS | Estimating | Y | 3.1799 | 0 | 3.1799 | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380369 | PSPS - CORNING 1102 LR53184 PH 1.8 | Base SH | 08W | ESTS | Estimating | Y | 2.1299 | 0 | 2.1299 | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380368 | PSPS - CORNING 1102 LR53184 PH 1.7 | Base SH | 08W | ESTS | Estimating | Y | 2.2299 | 0 | 2.2299 | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35380365 | PSPS - CORNING 1102 LR53184 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 3.04 | 0 | 3.04 | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35378609 | PLUCODIXIE-COMMERCIAL-Z2 GREENVILLE | Community Rebuild | 95F | ESTS | Estimating | Y | 0.7 | 0 | 0.7 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35376305 | FRRB - MARIPOSA 210110170 TL-10 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.61004 | 0 | 0.61004 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | MARIPOSA 210110170 | 1809 | 0.014293 | MARIPOSA 210110170 | 137 | 0.015939 | Tier 3
35374866 | FRRB - MARIPOSA 21019400 TL-7 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.43996 | 0 | 0.43996 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3
35374865 | FRRB - MARIPOSA 21019400 TL-6 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.47008 | 0 | 0.47008 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3
35374864 | FRRB - MARIPOSA 21019400 TL-5 INSTALL | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.0799 | 0 | 2.0799 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3
35374863 | FRRB - MARIPOSA 21019400 TL-4 INSTALL | Fire Rebuild | 08W | ADER | Estimating | Y | 0.46004 | 0 | 0.46004 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 | MARIPOSA 210110170 | 1809 | 0.014293 | MARIPOSA 210110170 | 137 | 0.015939 | Tier 2
35374862 | FRRB - MARIPOSA 21029590 TL-1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.5299 | 0 | 1.5299 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3
35374687 | FRRB - MARIPOSA 21019400 TL-3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.45 | 0 | 0.45 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 2
35374686 | FRRB - MARIPOSA 21019400 TL-2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.59 | 0 | 1.59 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3
35374685 | FRRB - MARIPOSA 210110240 TL-1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.4299 | 0 | 1.4299 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 3 |  | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35374684 | FRRB - MARIPOSA 210110170 ML-5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.4201 | 0 | 1.4201 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 2 & 3
35374683 | FRRB - MARIPOSA 21019400 ML-4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.1799 | 0 | 1.1799 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 2 & 3
35374682 | FRRB - MARIPOSA 210110240 ML-1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.45 | 0 | 2.45 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 2 & 3 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35374681 | FRRB - MARIPOSA 21019400 ML-2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.96004 | 0 | 0.96004 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 | MARIPOSA 210110240 | 679 | 0.11431 | MARIPOSA 210110240 | 126 | 0.016323 | Tier 2 & 3
35374559 | FRRB - MARIPOSA 21019400 ML-3 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.7 | 0 | 1.7 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 | MARIPOSA 21019400 | 655 | 0.11849 | MARIPOSA 21019400 | 504 | 0.00537 | Tier 2 & 3
35373594 | CWSP - BRUNSWICK 110651486 PH 6.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 10.76 | 0 | 10.76 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 | BRUNSWICK 110651486 | 1788 | 0.014797 | BRUNSWICK 110651486 | 315 | 0.0088799 | Tier 3
35373593 | CWSP - BRUNSWICK 110651486 PH 5.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 3.081 | 0 | 3.081 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 | BRUNSWICK 110651486 | 1788 | 0.014797 | BRUNSWICK 110651486 | 315 | 0.0088799 | Tier 3
35373585 | CWSP - BRUNSWICK 11062104 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 1.44 | 0 | 1.44 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 | BRUNSWICK 11062104 | 2157 | 0.0059169 | BRUNSWICK 11062104 | 429 | 0.0065825 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35373533 | CWSP - FORESTHILL 110150486 PH 2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | 2.24 | 0 | 2.24 | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 | FORESTHILL 110150486 | 2270 | 0.0037622 | FORESTHILL 110150486 | 114 | 0.01695 | Tier 3
35373051 | FRRB - KANAKA 1101CB - K2 SM3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.13864 | 0 | 0.13864 | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 | KANAKA 1101CB | 1480 | 0.029281 | KANAKA 1101CB | 212 | 0.01209 | Tier 3
35367520 | CWSP - STANISLAUS 1702 LR1888 PH1.1 | Targeted UG | 3UG | ESTS | Estimating | Y | 2.2869 | 0 | 2.2869 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 | STANISLAUS 17021888 | 2386 | 0.0026855 | STANISLAUS 17021888 | 379 | 0.0073524 | Tier 3
35353467 | DREXEL DR | Community Rebuild | 08W | ESTS | Estimating | Y | 2.4 | 0 | 2.4 | NV | Region 2 - North East | Magalia | Butte | 39.8182 | -121.5952 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35353466 | W PARK DR | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | 2.4 | 0 | 2.4 | NV | Region 2 - North East | Magalia | Butte | 39.8091 | -121.5998 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35352075 | BILLE WAGSTAFF | Community Rebuild | 08W | ESTS | Estimating | Y | 6.1 | 0 | 6.1 | NV | Region 2 - North East | Paradise | Butte | 39.7777 | -121.6077 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35350874 | NORWOOD | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 2.5 | 0 | 2.5 | NV | Region 2 - North East | Paradise | Butte | 39.7637 | -121.5732 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35350582 | PLUCODIXIE-HIDEAWAY Z7 GREENVILLE | Community Rebuild | 95F | ESTS | Estimating | Y | 0.37879 | 0 | 0.37879 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35350519 | PLUCODIXIE-ALTA CAMP Z6 GREENVILLE | Community Rebuild | 95F | ESTS | Estimating | Y | 0.47348 | 0 | 0.47348 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35350039 | FRRB - BIG BEND 1102 884340 - B4 SM2 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0.066288 | 0 | 0.066288 | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 | BIG BEND 11021972 | 1288 | 0.040961 | BIG BEND 1102884340 | 267 | 0.010152 | Tier 3
35349244 | CWSP - LINCOLN 1104 LR685276 PH 1.5 | Base SH | 08W | ADER | Estimating | Y | 0.67992 | 0 | 0.67992 | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v3 | LINCOLN 1104685276 | 230 | 0.24208 | LINCOLN 1104685276 | 4147 | 5.2842e-05 | Tier 2
35343396 | PSPS - WYANDOTTE 1110 LR980944 PH1.8 | Base SH | 08W | ESTS | Estimating | Y | 1.0822 | 0 | 1.0822 | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2
35343395 | PSPS - WYANDOTTE 1110 LR980944 PH1.7 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.76 | 0 | 1.76 | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2
35343394 | PSPS - WYANDOTTE 1110 LR980944 PH1.6 | Base SH | 08W | ESTS | Estimating | Y | 1.17 | 0 | 1.17 | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2
35342339 | FRRB - BIG BASIN 1102 UG6 BB VINEYARD | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.16193 | 0 | 0.16193 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 | BIG BASIN 110296986 | 2070 | 0.0075562 | BIG BASIN 110296986 | 1413 | 0.0011281 | Tier 3
35342333 | FRRB-BIG BASIN 1101 UG1 SAN VICENTE | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.42576 | 0 | 0.42576 | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 | BIG BASIN 11015000 | 2579 | 0.0013814 | BIG BASIN 11015000 | 1120 | 0.0018854 | Tier 3
35342151 | PSPS - JAMESON 1102 LR65516 1.9 | Base SH | 08W | ESTS | Estimating | Y | 0.079924 | 0 | 0.079924 | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35342148 | PSPS - JAMESON 1102 LR65516 1.7 | Base SH | 08W | ESTS | Estimating | Y | 1.19 | 0 | 1.19 | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35342147 | PSPS - JAMESON 1102 LR65516 1.6 | Base SH | 08W | ESTS | Estimating | Y | 1.8259 | 0 | 1.8259 | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35342146 | PSPS - JAMESON 1102 LR65516 1.5 | Base SH | 08W | ESTS | Estimating | Y | 2.397 | 0 | 2.397 | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2 | [6 empty] | 0 | 0 | 0 | Yes | 0 | 0
35342145 | PSPS - JAMESON 1102 LR65516 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.16307 | 0 | 0.16307 | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35342144 | PSPS - JAMESON 1102 LR65516 1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.617 | 0 | 1.617 | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35342143 | PSPS - JAMESON 1102 LR65516 1.2 | Base SH | 08W | ESTS | Estimating | Y | 3.2771 | 0 | 3.2771 | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35340270 | PSPS - CORNING 1102 LR915324 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.34 | 0 | 2.34 | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | Tier 2
35339665 | CWSP - HORSESHOE 1101 LR50140 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.75909 | 0 | 0.75909 | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | Tier 2
35339664 | CWSP - HORSESHOE 1101 LR50140 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.17008 | 0 | 0.17008 | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | Tier 2
35339293 | PSPS - JAMESON 1105 LR466348 PH 1.7 | Base SH | 08W | ESTS | Estimating | Y | 1.1799 | 0 | 1.1799 | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35339289 | CWSP - JESSUP 1102 LR1550 PH 3.4 | Base SH | 08W | ADER | Estimating | Y | 1.82 | 0 | 1.82 | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339288 | CWSP - JESSUP 1102 LR1550 PH 3.3 | Base SH | 08W | ESTS | Estimating | Y | 2.25 | 0 | 2.25 | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339287 | CWSP - JESSUP 1102 LR1550 PH 3.2 | Base SH | 08W | ESTS | Estimating | Y | 1.2 | 0 | 1.2 | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339286 | CWSP - JESSUP 1102 LR1550 PH 2.5 | Base SH | 08W | ESTS | Estimating | Y | 2.54 | 0 | 2.54 | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339285 | CWSP - JESSUP 1102 LR1550 PH 2.4 | Base SH | 08W | ESTS | Estimating | Y | 2.32 | 0 | 2.32 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339283 | CWSP - JESSUP 1102 LR1550 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 2.96 | 0 | 2.96 | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35339282 | CWSP - JESSUP 1102 LR1550 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 0.51 | 0 | 0.51 | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35338410 | PSPS - JAMESON 1105 LR466348 PH 2.3 | Base SH | 08W | ADER | Estimating | Y | 2.21 | 0 | 2.21 | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338409 | PSPS - JAMESON 1105 LR466348 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 2.35 | 0 | 2.35 | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338408 | PSPS - JAMESON 1105 LR466348 PH 1.6 | Base SH | 08W | ESTS | Estimating | Y | 1.1299 | 0 | 1.1299 | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338407 | PSPS - JAMESON 1105 LR466348 PH 1.5 | Base SH | 08W | ESTS | Estimating | Y | 0.66004 | 0 | 0.66004 | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 1.14 | 0 | 1.14 | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2 | [6 empty] | 0 | 0 | 0 | 0 | Yes | 0
35338405 | PSPS - JAMESON 1105 LR466348 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 2.24 | 0 | 2.24 | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338404 | PSPS - JAMESON 1105 LR466348 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.0299 | 0 | 1.0299 | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35338402 | PSPS - PANORAMA 1101 CB PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.42008 | 0 | 0.42008 | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 | PANORAMA 1101CB | 1038 | 0.062374 | PANORAMA 1101CB | 3890 | 5.6461e-05 | Tier 2
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.6 | 0 | 1.6 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | Tier 2 & 3 | [6 empty] | 0 | 0 | 0 | 0 | Yes | 0
35337306 | CWSP STANISLAUS 1702 CB PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.2667 | 0 | 2.2667 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | Tier 2 & 3
35337163 | CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.39 | 0 | 1.39 | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 | LINCOLN 1104275986 | 185 | 0.26526 | LINCOLN 1104275986 | 2971 | 0.0001399 | Tier 2
35337015 | CWSP - JAMESON 1105 LR9472 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.48996 | 0 | 0.48996 | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 | JAMESON 11059472 | 724 | 0.10731 | JAMESON 11059472 | 1928 | 0.00057842 | Tier 2
35337014 | CWSP - JAMESON 1105 LR9472 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.020076 | 0 | 0.020076 | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 | JAMESON 11059472 | 724 | 0.10731 | JAMESON 11059472 | 1928 | 0.00057842 | Tier 2
35337011 | CWSP - JESSUP 1102 LR1550 PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 2.89 | 0 | 2.89 | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35337010 | CWSP - JESSUP 1102 LR1550 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 3.82 | 0 | 3.82 | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.35 | 0 | 2.35 | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35335293 | PSPS - VACAVILLE 1111 CB PH 1.4 | Base SH | 08W | ESTS | Estimating | Y | 2.41 | 0 | 2.41 | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | Tier 2
35335292 | PSPS - VACAVILLE 1111 CB PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.8799 | 0 | 1.8799 | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | Tier 2
35335291 | PSPS - VACAVILLE 1111 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.3299 | 0 | 1.3299 | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | Tier 2
35335290 | PSPS - VACAVILLE 1111 LR13652 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.61 | 0 | 2.61 | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 | VACAVILLE 111113652 | 190 | 0.26339 | VACAVILLE 111113652 | 1722 | 0.00074783 | Tier 2
35334755 | PSPS - VACAVILLE 1108 LR38316 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 1.47 | 0 | 1.47 | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | Tier 2
35334754 | PSPS - VACAVILLE 1108 LR38316 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 3.93 | 0 | 3.93 | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | Tier 2
35334753 | PSPS - VACAVILLE 1108 LR38316 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.26 | 0 | 1.26 | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | Tier 2
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 1.81 | 0 | 1.81 | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | Tier 2 | [6 empty] | 0 | 0 | 0 | Yes | 0 | 0
35334750 | PSPS - VACAVILLE 1108 LR8762 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.49 | 0 | 1.49 | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | Tier 2
35334541 | FRRB -BIG BASIN 1102 12758 P1S2 CYPRESS | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.16629 | 0 | 0.16629 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 | BIG BASIN 110212758 | 2358 | 0.002947 | BIG BASIN 110212758 | 897 | 0.0026407 | Tier 3
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.089962 | 0 | 0.089962 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35334229 | PSPS - CORNING 1102 LR53184 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 3.04 | 0 | 3.04 | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35333504 | CWSP - BELL 1108 LR2202 PH 2.6 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.45 | 0 | 0.45 | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | Tier 2
35333503 | CWSP - BELL 1108 LR2202 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.3 | 0 | 0.3 | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | Tier 2
35332958 | CWSP LINCOLN 1104 LR2070 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 1.3701 | 0 | 1.3701 | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 | LINCOLN 11042070 | 568 | 0.14111 | LINCOLN 11042070 | 3055 | 0.00011911 | Tier 2
35332870 | PSPS - CURTIS 1701 CB PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.38674 | 0 | 0.38674 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 | CURTIS 1701CB | 1166 | 0.051116 | CURTIS 1701CB | 1018 | 0.0021952 | Tier 2
35332868 | PSPS - CURTIS 1701 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.5299 | 0 | 2.5299 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 | CURTIS 1701CB | 1166 | 0.051116 | CURTIS 1701CB | 1018 | 0.0021952 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35332866 | PSPS - JESSUP 1103 LR348657 PH 1.4 | Base SH | 08W | ADER | Estimating | Y | 1.01 | 0 | 1.01 | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 | JESSUP 1103348657 | 590 | 0.13388 | JESSUP 1103728460 | 2153 | 0.00046034 | Tier 2
35332364 | CWSP ELK CREEK 1101 LR2002 PH 2.6 | Base SH | 08W | ADER | Estimating | Y | 0.085038 | 0 | 0.085038 | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2
35332363 | CWSP ELK CREEK 1101 LR2002 PH 2.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1299 | 0 | 1.1299 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2 | [6 empty] | 0 | 0 | Yes | 0 | 0 | 0
35332362 | CWSP ELK CREEK 1101 LR2002 PH 2.4 | Base SH | 08W | ADER | Estimating | Y | 3.8299 | 0 | 3.8299 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2 |  |  | Yes |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35332360 | CWSP ELK CREEK 1101 LR2002 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 5.46 | 0 | 5.46 | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2
35332218 | PSPS COTTONWOOD 1102 LR544790 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 3.26 | 0 | 3.26 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | Tier 2
35332217 | PSPS COTTONWOOD 1102 LR9026 PH 3.2 | Base SH | 08W | ADER | Estimating | Y | 3.0299 | 0 | 3.0299 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35332216 | PSPS COTTONWOOD 1102 LR9026 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 1.4299 | 0 | 1.4299 | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35332215 | PSPS COTTONWOOD 1102 LR9026 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 2.26 | 0 | 2.26 | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35332214 | PSPS COTTONWOOD 1102 LR9026 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 4.04 | 0 | 4.04 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35332213 | PSPS COTTONWOOD 1102 LR544790 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 2.3701 | 0 | 2.3701 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | Tier 2
35331308 | PSPS WYANDOTTE 1110 LR980944 PH1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.82 | 0 | 0.82 | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2
35331307 | PSPS WYANDOTTE 1110 LR980944 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 2.55 | 0 | 2.55 | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2
35331305 | CWSP ANDERSON 1103 LR1600 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.44508 | 0 | 0.44508 | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 | ANDERSON 11031600 | 143 | 0.2889 | ANDERSON 11031600 | 3058 | 0.00011858 | Tier 2
35330815 | CWSP ANDERSON 1103 LR226050 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0.51004 | 0 | 0.51004 | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 | ANDERSON 1103226050 | 262 | 0.22913 | ANDERSON 1103226050 | 3263 | 8.0345e-05 | Tier 2
35330812 | PSPS ELK CREEK 1101 LR2002 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.49 | 0 | 2.49 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2
35330249 | CWSP REDBUD 1101 708166 PH 1.7 | Base SH | 08W | ADER | Estimating | Y | 4 | 0 | 4 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35330247 | CWSP REDBUD 1101 708166 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.75 | 0 | 0.75 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35330246 | CWSP REDBUD 1101 708166 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0299 | 0 | 1.0299 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35330245 | CWSP REDBUD 1101 708166 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 0.089962 | 0 | 0.089962 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35330244 | CWSP REDBUD 1101 708166 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 0.42008 | 0 | 0.42008 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35330241 | CWSP - REDBUD 1101 LR323962 PH1.3 | Base SH | 08W | ESTS | Estimating | Y | 2.8549 | 0 | 2.8549 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 3
35330219 | CWSP - REDBUD 1101 LR323962 PH1.2 | Base SH | 08W | ADER | Estimating | Y | 3.1299 | 0 | 3.1299 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 3
35330217 | CWSP - REDBUD 1101323962 PH 2.6 | Base SH | 08W | ESTS | Estimating | Y | 0.27992 | 0 | 0.27992 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 2 & 3
35330216 | CWSP - REDBUD 1101323962 PH 2.5 | Base SH | 08W | ESTS | Estimating | Y | 1.4299 | 0 | 1.4299 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 2 & 3
35330215 | CWSP - REDBUD 1101323962 PH 2.4 | Base SH | 08W | ESTS | Estimating | Y | 3.54 | 0 | 3.54 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 2 & 3
35330211 | CWSP - REDBUD 1101323962 PH 2.2 | Base SH | 08W | ESTS | Estimating | Y | 1.9701 | 0 | 1.9701 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 2 & 3
35329474 | CWSP REDBUD 1101 754544 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0.11004 | 0 | 0.11004 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101754544 | 375 | 0.007396 | Tier 2 & 3
35329472 | CWSP - REDBUD 1101 LR454 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.8689 | 0 | 2.8689 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | Tier 3
35329471 | PSPS HIGHLANDS 1104 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.55 | 0 | 1.55 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 | HIGHLANDS 1104CB | 3243 | 5.43e-06 | HIGHLANDS 1104CB | 1561 | 0.00090896 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35329016 | PSPS CLARK ROAD 1102 LR47006 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 3.54 | 0 | 3.54 | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 | CLARK ROAD 110247006 | 1535 | 0.025936 | CLARK ROAD 110247006 | 47 | 0.022808 | Tier 2
35329014 | PSPS CLARK ROAD 1102 LR514690 PH 1.2 | Base SH | 08W | ADER | Estimating | Y | 3.1701 | 0 | 3.1701 | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 | CLARK ROAD 11022070 | 1033 | 0.063106 | CLARK ROAD 11022070 | 711 | 0.0036217 | Tier 2
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3 | Base SH | 08W | ADER | Estimating | Y | 1.85 | 0 | 1.85 | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102514690 | 933 | 0.0025042 | Tier 2 | [5 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0
35329012 | PSPS CLARK ROAD 1102 LR514690 PH 2.2 | Base SH | 08W | ADER | Estimating | Y | 1.6201 | 0 | 1.6201 | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102407706 | 1009 | 0.0022353 | Tier 2
35329011 | PSPS CLARK ROAD 1102 LR81296 PH 1.4 | Base SH | 08W | ADER | Estimating | Y | 2.3229 | 0 | 2.3229 | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | Tier 2
35329010 | PSPS CLARK ROAD 1102 LR81296 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.814 | 0 | 2.814 | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | Tier 2
35329009 | PSPS CLARK ROAD 1102 LR81296 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.94091 | 0 | 0.94091 | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | Tier 2
35329008 | PSPS CLARK ROAD 1102 CB PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 0.31307 | 0 | 0.31307 | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 | CLARK ROAD 1102CB | 268 | 0.22632 | CLARK ROAD 1102CB | 2491 | 0.00031072 | Tier 2
35326790 | PSPS - FLINT1101 CB & 40666 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 0.14792 | 0 | 0.14792 | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 | FLINT 1101958726 | 2980 | 1.76e-05 | FLINT 1101958726 | 2071 | 0.00050684 | Tier 2
35325590 | CWSP FLINT 1101 750 PH 1.3 | Base SH | 08W | ESTS | Estimating | Y | 2.06 | 0 | 2.06 | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | Tier 2
35325589 | CWSP FLINT 1101 750 PH 1.2 | Base SH | 08W | ESTS | Estimating | Y | 1.21 | 0 | 1.21 | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | Tier 2
35321894 | FRRB - PT MORETTI 1101 12122 PH1 SM4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.13826 | 0 | 0.13826 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 | POINT MORETTI 110112122 | 2199 | 0.0051004 | POINT MORETTI 110112122 | 2216 | 0.00042654 | Tier 2
35320464 | PSPS - PANORAMA 1101 CB PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.15 | 0 | 0.15 | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 | PANORAMA 1101CB | 1038 | 0.062374 | PANORAMA 1101CB | 3890 | 5.6461e-05 | Tier 2
35320463 | PSPS - JAMESON 1105913400 | Base SH | 08W | ESTS | Estimating | Y | 0.56004 | 0 | 0.56004 | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 | JAMESON 1105913400 | 419 | 0.17457 | JAMESON 1105913400 | 987 | 0.0022992 | Tier 2
35320461 | PSPS - JAMESON 1105 LR466348 PH 2.1 | Base SH | 08W | ADER | Estimating | Y | 3.56 | 0 | 3.56 | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35320460 | PSPS - JAMESON 1105 LR466348 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 1.7799 | 0 | 1.7799 | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | Tier 2
35320450 | CWSP - LINCOLN 1104 LR685276 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 2.0701 | 0 | 2.0701 | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 | LINCOLN 1104685276 | 230 | 0.24208 | LINCOLN 1104685276 | 4147 | 5.2842e-05 | Tier 2
35320449 | CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.2375 | 0 | 3.2375 | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 | LINCOLN 1104275986 | 185 | 0.26526 | LINCOLN 1104275986 | 2971 | 0.0001399 | Tier 2
35320447 | CWSP - HORSESHOE 1101 LR50140 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.83996 | 0 | 0.83996 | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | Tier 2
35320442 | PSPS - JAMESON 1102 LR65516 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.38693 | 0 | 0.38693 | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | Tier 2
35320441 | PSPS - VACAVILLE 1111 LR13652 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 2.14 | 0 | 2.14 | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 | VACAVILLE 111113652 | 190 | 0.26339 | VACAVILLE 111113652 | 1722 | 0.00074783 | Tier 2
35320339 | PSPS - VACAVILLE 1108 LR38316 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 2.2 | 0 | 2.2 | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | Tier 2
35320334 | PSPS - VACAVILLE 1108 LR8762 PH 2.0 | Base SH | 08W | ESTS | Estimating | Y | 2.5 | 0 | 2.5 | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | Tier 2
35320333 | PSPS - VACAVILLE 1108 LR8762 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 2.95 | 0 | 2.95 | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | Tier 2
35320312 | CWSP LINCOLN 1104 LR2070 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 2.04 | 0 | 2.04 | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 | LINCOLN 11042070 | 568 | 0.14111 | LINCOLN 11042070 | 3055 | 0.00011911 | Tier 2
35318074 | FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.29356 | 0 | 0.29356 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 | BIG BASIN 11022253 | 2246 | 0.0041981 | BIG BASIN 11022253 | 936 | 0.002497 | Tier 2
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.20114 | 0 | 0.20114 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 | BIG BASIN 110110720 | 2435 | 0.002283 | BIG BASIN 110110720 | 1105 | 0.0019396 | Tier 3
35317887 | CWSP - JESSUP 1102 LR1550 PH 3.1 | Base SH | 08W | ADER | Estimating | Y | 0.8 | 0 | 0.8 | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35317480 | CWSP - JESSUP 1102 LR1550 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 2.06 | 0 | 2.06 | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35317399 | CWSP - REDBUD 1101323962 PH 2.1 | Base SH | 08W | ESTS | Estimating | Y | 1.1799 | 0 | 1.1799 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 2 & 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35316569 | PSPS - COTTONWOOD 11029026 PH3 | Base SH | 08W | ESTS | Estimating | Y | 4.81 | 0 | 4.81 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35316567 | PSPS - COTTONWOOD 11029026 PH2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.4201 | 0 | 3.4201 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35316561 | PSPS - COTTONWOOD 1102544790 PH 2 | Base SH | 08W | ESTS | Estimating | Y | 4.41 | 0 | 4.41 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | Tier 2
35316278 | CWSP ELK CREEK 1101 LR2002 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.35 | 0 | 2.35 | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2
35316201 | PLUCODIXIE-HOT SPRINGS RD Z5 GREENVILLE | Community Rebuild | 95F | ESTS | Estimating | Y | 0.68314 | 0 | 0.68314 | NV | Region 2 - North East | Greenville | Plumas | 40.1397 | -120.9389 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35316200 | PLUCODIXIE-KINDER AVE Z4 GREENVILLE | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | 1.0417 | 0 | 1.0417 | NV | Region 2 - North East | Greenville | Plumas | 40.1413 | -120.957 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35316019 | PLUCODIXIE-FORGAY AVE Z3 GREENVILLE | Community Rebuild | 95F | ESTS | Estimating | Y | 1.017 | 0 | 1.017 | NV | Region 2 - North East | Greenville | Plumas | 40.1435 | -120.9581 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35316018 | PLUCODIXIE-BIDWELL ST Z2 GREENVILLE | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | 0.7197 | 0 | 0.7197 | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35313249 | PLUCODIXIE-BUSH ST Z1 GREENVILLE | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | 1.2871 | 0 | 1.2871 | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35312560 | PSPS WYANDOTTE 1110 LR980944 PH1.1 | Base SH | 08W | ESTS | Estimating | Y | 3.61 | 0 | 3.61 | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 | WYANDOTTE 1110980944 | 976 | 0.070566 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35312552 | CWSP REDBUD 1101 708166 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.77008 | 0 | 0.77008 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | Tier 2 & 3
35312551 | CWSP - REDBUD 1101 LR454 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 3.2049 | 0 | 3.2049 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | Tier 3
35312550 | CWSP - REDBUD 1101 LR323962 PH1.1 | Base SH | 08W | ADER | Estimating | Y | 1.54 | 0 | 1.54 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | Tier 3
35312549 | PSPS - JESSUP 1103 LR348657 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.98 | 0 | 0.98 | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 | JESSUP 1103348657 | 590 | 0.13388 | JESSUP 1103770356 | 2901 | 0.00016206 | Tier 2
35312548 | CWSP - JESSUP 1102 LR1550 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 1.2 | 0 | 1.2 | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | Tier 2
35312545 | CWSP - FLINT 1101750 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 1.3299 | 0 | 1.3299 | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | Tier 2
35312544 | CWSP ELK CREEK 1101 LR93504 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 0.079924 | 0 | 0.079924 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 | ELK CREEK 110193504 | 206 | 0.25426 | ELK CREEK 110193504 | 1350 | 0.0012407 | Tier 2
35312543 | PSPS ELK CREEK 1101 LR2002 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 3.71 | 0 | 3.71 | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | Tier 2 |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0
35312541 | PSPS - CURTIS 1701 CB PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 0.42992 | 0 | 0.42992 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 | CURTIS 1701CB | 1166 | 0.051116 | CURTIS 1701CB | 1018 | 0.0021952 | Tier 2
35312540 | PSPS - COTTONWOOD 11029026 PH1 | Base SH | 08W | ADER | Estimating | Y | 4.8799 | 0 | 4.8799 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | Tier 2
35311899 | PSPS - COTTONWOOD 1102544790 PH 1 | Base SH | 08W | ADER | Estimating | Y | 3.44 | 0 | 3.44 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | Tier 2
35311898 | PSPS - CORNING 1102 LR915324 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 2 | 0 | 2 | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | Tier 2
35311897 | PSPS - CORNING 1102 LR53184 PH 1.1 | Base SH | 08W | ESTS | Estimating | Y | 4.84 | 0 | 4.84 | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | Tier 2
35311895 | CWSP ANDERSON 1103 LR226050 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 2.7799 | 0 | 2.7799 | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 | ANDERSON 1103226050 | 262 | 0.22913 | ANDERSON 1103226050 | 3263 | 8.0345e-05 | Tier 2
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.065 | 0 | 1.065 | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35301112 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.52576 | 0 | 0.52576 | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | Tier 2
35300933 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.59489 | 0 | 0.59489 | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | Tier 2
35299635 | PSPS CLARK ROAD 1102 LR47006 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 2.24 | 0 | 2.24 | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 | CLARK ROAD 110247006 | 1535 | 0.025936 | CLARK ROAD 110247006 | 47 | 0.022808 | Tier 2
35299634 | PSPS CLARK ROAD 1102 LR514690 PH 1.1 | Base SH | 08W | ADER | Estimating | Y | 2.2799 | 0 | 2.2799 | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 | CLARK ROAD 11022070 | 1033 | 0.063106 | CLARK ROAD 11022070 | 711 | 0.0036217 | Tier 2
35299633 | PSPS CLARK ROAD 1102 LR514690 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.14 | 0 | 2.14 | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102407706 | 1009 | 0.0022353 | Tier 2 | [5 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0
35299631 | PSPS CLARK ROAD 1102 LR81296 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.4299 | 0 | 3.4299 | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | Tier 2
35298571 | CWSP ANDERSON 1103 LR1600 PH1 | Base SH | 08W | ESTS | Estimating | Y | 0.33996 | 0 | 0.33996 | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 | ANDERSON 11031600 | 143 | 0.2889 | ANDERSON 11031600 | 3058 | 0.00011858 | Tier 2
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.0199 | 0 | 1.0199 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297697 | FRRB - WILLOW CREEK 11032936 UG TL3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.014773 | 0 | 0.014773 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.78996 | 0 | 0.78996 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.43996 | 0 | 0.43996 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.95 | 0 | 0.95 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1 | 0 | 1 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 4.6598 | 0 | 4.6598 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35297464 | FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.0021 | 0 | 1.0021 | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 | POINT MORETTI 110112122 | 2199 | 0.0051004 | POINT MORETTI 110112122 | 2216 | 0.00042654 | Tier 2
35293846 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.85985 | 0 | 0.85985 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | Tier 2 & 3
35293670 | CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.54394 | 0 | 0.54394 | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | Tier 2
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | Base SH | 08W | UNSC | Ready for Construction | Y | 0.43655 | 0 | 0.43655 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | Tier 2
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.68788 | 0 | 0.68788 | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | Tier 2
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | Base SH | 08W | ESTS | Estimating | Y | 0.51004 | 0 | 0.51004 | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | Tier 2
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0.11932 | 0 | 0.11932 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012586 | 1285 | 0.041237 | BIG MEADOWS 21012586 | 2987 | 0.00013567 | Tier 2
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.1 | 0 | 0.1 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012476 | 2342 | 0.0030704 | BIG MEADOWS 21012476 | 1533 | 0.00093756 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.1 | 0 | 1.1 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012476 | 2342 | 0.0030704 | BIG MEADOWS 21012476 | 1533 | 0.00093756 | Tier 2 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | Fire Rebuild | 08W | ESTS | Estimating | Y | 3.0644 | 0 | 3.0644 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.17159 | 0 | 0.17159 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | Tier 2
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 1.2786 | 0 | 1.2786 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | Fire Rebuild | 08W | CONS | In-Construction | Y | 2.6481 | 0 | 2.6481 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | Fire Rebuild | 08W | CONS | In-Construction | Y | 4.0852 | 0 | 4.0852 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0.49451 | 0 | 0.49451 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | Tier 2
35290808 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.27992 | 0 | 0.27992 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | Tier 2
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | Fire Rebuild | 08W | CONS | In-Construction | Y | 0.97992 | 0 | 0.97992 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | Tier 2
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.66004 | 0 | 0.66004 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | Tier 2
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | Fire Rebuild | 08W | CONS | In-Construction | Y | 1.2858 | 0 | 1.2858 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.86989 | 0 | 0.86989 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 | SPANISH CREEK 4401CB | 1322 | 0.038702 | SPANISH CREEK 4401CB | 1064 | 0.0020497 | Tier 2
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Base SH | 08W | ESTS | Estimating | Y | 0.62008 | 0 | 0.62008 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0436 | 0 | 1.0436 | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.65303 | 0 | 0.65303 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | Tier 2
35285249 | CWSP - UPPER LAKE 1101 1276 PH 2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.6288 | 0 | 2.6288 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | Tier 2
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.25398 | 0 | 0.25398 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 | POTTER VALLEY P H 110537476 | 396 | 0.18107 | POTTER VALLEY P H 110537476 | 2321 | 0.00037714 | Tier 2
35285064 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.79848 | 0 | 0.79848 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 | POTTER VALLEY P H 110537476 | 396 | 0.18107 | POTTER VALLEY P H 110537476 | 2321 | 0.00037714 | Tier 2
35284365 | CWSP STANISLAUS 1702 CB PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.7547 | 0 | 2.7547 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | Tier 2 & 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.91742 | 0 | 0.91742 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | Tier 2 & 3
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.6591 | 0 | 1.6591 | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | Tier 2 |  |  | Yes |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35283343 | CWSP UPPER LAKE 1101 1276 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.72614 | 0 | 0.72614 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | Tier 2
35283198 | CWSP HARTLEY 1101 LR698 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.27803 | 0 | 0.27803 | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 | HARTLEY 1101698 | 58 | 0.39723 | HARTLEY 1101698 | 486 | 0.0056859 | Tier 2
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.5902 | 0 | 2.5902 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 | SPANISH CREEK 4401CB | 1322 | 0.038702 | SPANISH CREEK 4401CB | 1064 | 0.0020497 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.45985 | 0 | 0.45985 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | Tier 2 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 1.4 | 0 | 1.4 | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 | GRAYS FLAT 0401CB | 1748 | 0.016728 | GRAYS FLAT 0401CB | 521 | 0.0051671 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.64 | 0 | 2.64 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.85 | 0 | 0.85 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 0.82008 | 0 | 0.82008 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | CRESCENT MILLS 21012056 | 895 | 0.080308 | CRESCENT MILLS 21012056 | 854 | 0.0028532 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35280493 | FRRB -BIG MEADOWS 21012260 UG TL 1.13 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 0.35 | 0 | 0.35 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2
35280362 | CWSP - MARIPOSA 2102440236 PH1.4 | Base SH | 08W | ESTS | Estimating | Y | 0.13258 | 0 | 0.13258 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 | MARIPOSA 2102440236 | 50 | 0.4205 | MARIPOSA 2102440236 | 400 | 0.0069412 | Tier 2 & 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35279985 | FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 3.115 | 0 | 3.115 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 | BIG MEADOWS 21012248 | 916 | 0.077859 | BIG MEADOWS 21012248 | 575 | 0.0046735 | Tier 2 |  | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.25 | 0 | 2.25 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 | GANSNER 11012424 | 1172 | 0.050559 | GANSNER 11012424 | 785 | 0.0031715 | Tier 2 & 3 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | Fire Rebuild | 08W | ESTS | Estimating | Y | 2.0701 | 0 | 2.0701 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | Fire Rebuild | 08W | ESTS | Estimating | Y | 5.589 | 0 | 5.589 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.004 | 0 | 1.004 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | Tier 2 & 3 | Yes | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3449 | 0 | 1.3449 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | Tier 2 & 3
35277938 | CWSP AUBERRY 1101 R2578 PH2.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.42822 | 0 | 0.42822 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 | AUBERRY 1101R2578 | 163 | 0.27714 | AUBERRY 1101R2578 | 569 | 0.0047219 | Tier 2
35277935 | CWSP AUBERRY 1101 R2839 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.089394 | 0 | 0.089394 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 | AUBERRY 1101R2839 | 274 | 0.22501 | AUBERRY 1101R2839 | 614 | 0.0043344 | Tier 2
35277925 | CWSP - AUBERRY 1101CB PH1.2 | Base SH | 08W | CONS | In-Construction | Y | 0.14148 | 0 | 0.14148 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 | AUBERRY 1101CB | 63 | 0.39206 | AUBERRY 1101CB | 2126 | 0.00047477 | Tier 2
35277924 | CWSP AUBERRY 1101 R2578 PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.10909 | 0 | 0.10909 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 | AUBERRY 1101R2578 | 163 | 0.27714 | AUBERRY 1101R2578 | 569 | 0.0047219 | Tier 2
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | Base SH | 08W | ESTS | Estimating | Y | 2.756 | 0 | 2.756 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 | MARIPOSA 210135244 | 428 | 0.17286 | MARIPOSA 2101151918 | 249 | 0.010861 | Tier 2
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | Base SH | 08W | ESTS | Estimating | Y | 2.132 | 0 | 2.132 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 | MARIPOSA 210135244 | 428 | 0.17286 | MARIPOSA 2101151918 | 249 | 0.010861 | Tier 2 & 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | Base SH | 08W | CONS | In-Construction | Y | 0.25871 | 0 | 0.25871 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 | DESCHUTES 11041370 | 100 | 0.34561 | DESCHUTES 11041370 | 2704 | 0.00022756 | Tier 2
35256083 | CWSP - UPPER LAKE 11011276 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.847 | 0 | 1.847 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | Tier 2
35254947 | CWSP - VOLTA 11011596 - PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.263 | 0 | 0.263 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | VOLTA 11011596 | 966 | 0.071922 | VOLTA 11011596 | 281 | 0.0099219 | Tier 2
35254945 | CWSP - VOLTA 11011596 - PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.51 | 0 | 0.51 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 | VOLTA 11011596 | 966 | 0.071922 | VOLTA 11011596 | 281 | 0.0099219 | Tier 2
35254650 | CWSP - VOLTA 110153118 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0.30436 | 0.30436 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 | VOLTA 110153118 | 157 | 0.27952 | VOLTA 110153118 | 280 | 0.0099281 | Tier 2
35254259 | CWSP - VOLTA 1101CB PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.275 | 0 | 0.275 | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 | VOLTA 1101CB | 76 | 0.37545 | VOLTA 1101CB | 2202 | 0.00043332 | Tier 2 & 3
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | Base SH | 08W | ESTS | Estimating | Y | 0.43996 | 0 | 0.43996 | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | Tier 2 | Yes |  |  |  |  | Yes | 0 | 0 | 0 | 0 | 0 | 0
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 SM | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 0.31004 | 0 | 0.31004 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.11004 | 0 | 0.11004 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.070076 | 0 | 0.070076 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35240166 | CWSP - VOLTA 1101CB PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 0.015341 | 0 | 0.015341 | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 | VOLTA 1101CB | 76 | 0.37545 | VOLTA 1101CB | 2202 | 0.00043332 | Tier 2 & 3
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | Fire Rebuild | 08W | DOCC | In-Construction | Y | 1.8256 | 1.8193 | 0.00625 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 1103640652 | 250 | 0.010796 | Tier 3
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.28409 | 0 | 0.28409 | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | 2.0655 | 0 | 2.0655 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 | KANAKA 1101CB | 1480 | 0.029281 | KANAKA 1101CB | 212 | 0.01209 | Tier 3
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Base SH | 08W | DOCC | In-Construction | Y | 1.2508 | 1.2034 | 0.047348 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.11364 | 0 | 0.11364 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | 0.30303 | 0 | 0.30303 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 11031508 | 526 | 0.0051219 | Tier 3
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0684 | 0 | 1.0684 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.12311 | 0 | 0.12311 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.0267 | 0 | 1.0267 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.782 | 0 | 2.782 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0.84962 | 0 | 0.84962 | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 | PLACERVILLE 21067522 | 1363 | 0.035529 | PLACERVILLE 21067522 | 277 | 0.0099544 | Tier 3
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 0.73144 | 0 | 0.73144 | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 | PLACERVILLE 21067522 | 1363 | 0.035529 | PLACERVILLE 21067522 | 277 | 0.0099544 | Tier 3
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.8943 | 0 | 2.8943 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | HIGHLANDS 1102628 | 27 | 0.5487 | HIGHLANDS 1102628 | 29 | 0.026126 | Tier 2 & 3 | Yes |  | Yes |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.6782 | 0 | 2.6782 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 | HIGHLANDS 1102628 | 27 | 0.5487 | HIGHLANDS 1102628 | 29 | 0.026126 | Tier 2 & 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Base SH | 08W | CONS | In-Construction | Y | 1.49 | 0 | 1.49 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | Tier 2 & 3
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Base SH | 08W | CONS | In-Construction | Y | 1.3212 | 0.36136 | 0.95985 | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | Tier 2 & 3
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0.53996 | 0 | 0.53996 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 | VACAVILLE 11046542 | 42 | 0.44642 | VACAVILLE 11046542 | 383 | 0.0073117 | Tier 3
35227481 | HILLPARK LN | Community Rebuild | 95F O | CONS | In-Construction | Y | 4.2 | 0 | 4.2 | NV | Region 2 - North East | Paradise | Butte | 39.7392 | -121.5724 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35227415 | JARVIS LN | Community Rebuild | 95F O | ESTS | Estimating | Y | 5.2 | 0 | 5.2 | NV | Region 2 - North East | Paradise | Butte | 39.7389 | -121.6402 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35227408 | PEARSON RD | Community Rebuild | 95F O | ESTS | Estimating | Y | 2.1 | 0 | 2.1 | NV | Region 2 - North East | Paradise | Butte | 39.7524 | -121.6126 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35227406 | COLLEGE HILL | Community Rebuild | 95F O | ADER | Estimating | Y | 4.5 | 0 | 4.5 | NV | Region 2 - North East | Paradise | Butte | 39.7523 | -121.6185 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35227405 | SHADOWBROOK | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 0.3 | 0 | 0.3 | NV | Region 2 - North East | Paradise | Butte | 39.7578 | -121.6071 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35227404 | ACADEMY | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | 3.3 | 0 | 3.3 | NV | Region 2 - North East | Paradise | Butte | 39.7538 | -121.6172 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35227403 | MAPLE PARK | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 2.2 | 0 | 2.2 | NV | Region 2 - North East | Paradise | Butte | 39.7616 | -121.6079 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35227402 | STINSON LN | Community Rebuild | 95F O | ESTS | Estimating | Y | 1.9 | 0 | 1.9 | NV | Region 2 - North East | Paradise | Butte | 39.7703 | -121.6071 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35227401 | CAMELLIA DR | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | 1.2 | 0 | 1.2 | NV | Region 2 - North East | Paradise | Butte | 39.7628 | -121.6233 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Base SH | 08W | CONS | In-Construction | Y | 1.55 | 0 | 1.55 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 110148212 | 13 | 0.035184 | Tier 3
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Base SH | 08W | CONS | In-Construction | Y | 1.3765 | 0 | 1.3765 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 110148212 | 13 | 0.035184 | Tier 3
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Base SH | 08W | CONS | In-Construction | Y | 0.79413 | 0 | 0.79413 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.8756 | 0 | 2.8756 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Base SH | 08W | CONS | In-Construction | Y | 0.85246 | 0 | 0.85246 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.58883 | 0 | 0.58883 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Base SH | 08W | UNSE | Scoping/Scoped | Y | 1.0394 | 0 | 1.0394 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.1449 | 0 | 1.1449 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 0.4214 | 0.41477 | 0.0066288 | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 | WYANDOTTE 110932586 | 29 | 0.52987 | WYANDOTTE 110932586 | 2717 | 0.0002242 | Tier 2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | Y | 4.8061 | 0 | 4.8061 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 | KESWICK 11011586 | 7 | 1.2524 | KESWICK 11011586 | 48 | 0.022602 | Tier 3 |  |  | Yes | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.85511 | 0 | 0.85511 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 | KESWICK 11011586 | 7 | 1.2524 | KESWICK 11011586 | 48 | 0.022602 | Tier 3 |  |  | Yes | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 1.9095 | 0 | 1.9095 | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 | BUCKS CREEK 1101CB | 11 | 0.73491 | BUCKS CREEK 1101CB | 21 | 0.029234 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | 2.2729 | 0 | 2.2729 | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 | BUCKS CREEK 1101CB | 11 | 0.73491 | BUCKS CREEK 1101CB | 21 | 0.029234 | Tier 2 & 3 | Yes | Yes |  |  | Yes |  | 0 | 0 | 0 | 0 | 0 | 0
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.3843 | 0 | 1.3843 | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 | LAS GALLINAS A 110599904 | 215 | 0.25006 | LAS GALLINAS A 110599904 | 1267 | 0.0014262 | Tier 3
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.3197 | 0 | 0.3197 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 | DUNBAR 1101CB | 2048 | 0.007993 | DUNBAR 1101CB | 3020 | 0.00012812 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.84924 | 0 | 0.84924 | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | Tier 2 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Base SH | 08W | CONS | In-Construction | Y | 1.1968 | 1.1364 | 0.060417 | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 | BANGOR 1101CB | 355 | 0.19378 | BANGOR 1101CB | 2768 | 0.00020951 | Tier 2
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Base SH | 08W | CONS | In-Construction | Y | 2.0494 | 0 | 2.0494 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | Tier 2 & 3
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Base SH | 08W | UNSE | Scoping/Scoped | Y | 0.24 | 0 | 0.24 | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 | PLACERVILLE 1112CB | 2123 | 0.0065148 | PLACERVILLE 1112CB | 1979 | 0.00055552 | Tier 2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.7282 | 0 | 3.7282 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 | VACAVILLE 11046542 | 42 | 0.44642 | VACAVILLE 11046542 | 383 | 0.0073117 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 1.8303 | 1.8019 | 0.028409 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 | KIRKER 2104442850 | 21 | 0.61454 | KIRKER 2104442850 | 571 | 0.00471 | Tier 2
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.14 | 0 | 1.14 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 | TIDEWATER 210614072 | 18 | 0.65331 | TIDEWATER 210614072 | 448 | 0.0062529 | Tier 2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Fire Rebuild | 08W | CONS | In-Construction | Y | 2.7439 | 0 | 2.7439 | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 | HALF MOON BAY 110369412 | 2055 | 0.0078448 | HALF MOON BAY 110369412 | 2554 | 0.0002898 | Tier 2 | [5 empty] | Yes | 0 | 0 | 0 | 0 | Yes | 0
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.34 | 0 | 1.34 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 | CLAYTON 221296224 | 377 | 0.18755 | CLAYTON 221296224 | 15 | 0.034099 | Tier 3
35189987 | WHATEVER LN | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | 2.7 | 0 | 2.7 | NV | Region 2 - North East | Paradise | Butte | 39.7404 | -121.5939 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35189984 | PALOMA AVE | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 3.3 | 0 | 3.3 | NV | Region 2 - North East | Paradise | Butte | 39.7471 | -121.6129 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35189853 | HAPPY WOODS | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 1.4 | 0 | 1.4 | NV | Region 2 - North East | Paradise | Butte | 39.7681 | -121.5891 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35189792 | CYPRESS LN | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 3.9 | 0 | 3.9 | NV | Region 2 - North East | Paradise | Butte | 39.784 | -121.5864 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35189791 | WARREN RD | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 2 | 0 | 2 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5873 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35175548 | HIGH SCHOOL MAXWELL | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 3.2 | 0 | 3.2 | NV | Region 2 - North East | Paradise | Butte | 39.7619 | -121.6125 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35175547 | PENTZ & WAGSTAFF | Community Rebuild | 95F O | ESTS | Estimating | Y | 4.8 | 0 | 4.8 | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5797 |  | N/A | N/A | N/A | N/A | N/A | N/A | Non-HFTD
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 3.8303 | 0 | 3.8303 | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 1.04 | 0 | 1.04 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35145540 | PSPS - FROGTOWN 1702 - CB | Base SH | 08W | PEND | Permitting/Dependency | Y | 0.53447 | 0 | 0.53447 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 | FROGTOWN 1702CB | 1316 | 0.039234 | FROGTOWN 1702CB | 1205 | 0.0016222 | Tier 3 | Yes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
35144480 | SHAW CIR | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | 2.6 | 0 | 2.6 | NV | Region 2 - North East | Magalia | Butte | 39.8116 | -121.5956 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35126750 | JERRYS WAY | Community Rebuild | 95F O | CONS | In-Construction | Y | 2.4 | 0 | 2.4 | NV | Region 2 - North East | Paradise | Butte | 39.7741 | -121.5895 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35126645 | CRESTVIEW | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 2.2 | 0 | 2.2 | NV | Region 2 - North East | Paradise | Butte | 39.7612 | -121.6342 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35118676 | REDBUD DR | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | 3.2 | 0 | 3.2 | NV | Region 2 - North East | Paradise | Butte | 39.7551 | -121.6455 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35117455 | HERMAN | Community Rebuild | 08W | ADER | Estimating | Y | 1.4 | 0 | 1.4 | NV | Region 2 - North East | Paradise | Butte | 39.7813 | -121.594 |  | N/A | N/A | N/A | N/A | N/A | N/A | Tier 3
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Base SH | 08W | CONS | In-Construction | Y | 0.093561 | 0.04072 | 0.052841 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 | PINE GROVE 11021222 | 2271 | 0.0037571 | PINE GROVE 11021222 | 558 | 0.0048336 | Tier 3
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Base SH | 08W | DOCC | In-Construction | Y | 0.44621 | 0.44621 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 | EL DORADO PH 210119752 | 1946 | 0.0103 | EL DORADO PH 210119752 | 49 | 0.022482 | Tier 3
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | Base SH | 08W | CONS | In-Construction | Y | 0.37955 | 0.04072 | 0.33883 | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 | EL DORADO PH 210119752 | 1946 | 0.0103 | EL DORADO PH 210119752 | 49 | 0.022482 | Tier 3
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Base SH | 08W | CONS | In-Construction | Y | 0.053977 | 0.053977 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 | STANISLAUS 17021804 | 2712 | 0.00058985 | STANISLAUS 17021804 | 1583 | 0.00088659 | Tier 3
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Base SH | 08W | CONS | In-Construction | Y | 5.0311 | 0.97178 | 4.0593 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 | SHINGLE SPRINGS 210935598 | 159 | 0.27855 | SHINGLE SPRINGS 210935598 | 241 | 0.011098 | Tier 3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | Y | 2.2513 | 0 | 2.2513 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 | EL DORADO PH 210119752 | 1946 | 0.0103 | EL DORADO PH 210119752 | 49 | 0.022482 | Tier 3

## Sheet3 (hidden)
Order | Order Description | Applicable Risk Model | Risk Rank | WSHP Risk | Top Risk/Not Top Risk (Used for Table) | Progam | Project Type | Old Risk Rank Methodology - Risk Rank | Old Risk Rank Methodology - Top Risk/Not Top Risk | Alternate Risk Rank (All V3 Tranches are Top Risk unless 0 or empty) | Category | MAT | SAP Status | Status (see 2nd tab) | WMP GH-03 SH (Y/N) | WMP GH-05 10k UG (Y/N) | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2022 Complete | UG - Pre-2022 Complete | Removal - Pre-2022 Complete | Pre-2022 Total Complete | OH - 2022 Complete | UG - 2022 Complete | Removal - 2022 Complete | 2022 Total Complete | OH - Remaining | UG - Remaining | Removal - Remaining | Total Remaining | Years Assigned (for completion) | OH - 2023 Forecast | UG - 2023 Forecast | Removal - 2023 Forecast | 2023 Total Miles | OH - 2024 Forecast | UG - 2024 Forecast | Removal - 2024 Forecast | 2024 Total Miles | OH - 2025 Forecast | UG - 2025 Forecast | Removal - 2025 Forecast | 2025 Total Miles | OH - 2026 Forecast | UG - 2026 Forecast | Removal - 2026 Forecast | 2026 Total Miles | Div | Region | City | County | Latitude | Longitude | Applicable Risk Model2 | Circuit Protection Zone (V2) | Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | Risk Rank (V3) | 2022 Risk Tranches v3 | v3 Mean Risk | Project Type (see 3rd tab for description) | HFTD Tier | California Department of Transportation (Caltrans) | United States Forest Service (USFS) | Bureau of Land Management (BLM) | Bureau of Reclamation (BOR) | Federal Energy Regulatory Commission (FERC) | California Department of Parks and Recreation (State Parks) | California Department of Fish and Wildlife (CDFW) | State Water (California Department of Water Resources) | California State Lands Commission (State Lands) | Land Trusts | Conservation Easements | Midpeninsula Regional Open Space District (Open Space)
35367472 | CWSP_0780_EL DORADO 21026645 1.1 | WDRM v3 | 1 | V3 Tranche 1 | V3 Tranche 1 | SH | CWSP | 780 | V3 Not Top Risk | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.29 | 0 | 4.29 | 0 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 | EL DORADO PH 21026645 | 780 | 1 | 0.0031904 | CWSP 2024 | Tier 3
35374057 | CWSP - GEYSERVILLE - 1101482 | WDRM v3 | 1 | V3 Tranche 1 | V3 Tranche 1 | SH | CWSP | 1375 | V3 Not Top Risk | V3 Top Risk | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | Y | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0.33996 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 | GEYSERVILLE 1101482 | 2170 | 0.0056711 | GEYSERVILLE 1101482 | 1375 | 1 | 0.0011879 | CWSP 2024 | Tier 2

## Pivot
Top 20% Risk/Not Top Risk | Progam | Project Type 2 | Sum of UG - 2023 Forecast | Sum of UG - 2024 Forecast | Sum of UG - 2025 Forecast | Sum of UG - 2026 Forecast
No Risk Vintage |  | Butte Rebuild | 71.4 | 98.7981 | 0 | 0
| Community Rebuild | Greenville Rebuild | 6.3009 | 0 | 0 | 0
| Other |  | 0 | 0 | 0 | 0
No Risk Vintage Total |  |  | 77.7009 | 98.7981 | 0 | 0
V2 Not Top Risk | FRRB |  | 45.2025 | 5.7807 | 1.76 | 1.1201
| IF |  | 0 | 0 | 0 | 0
| Other |  | 0 | 5.2831 | 0.015341 | 0.37879
| SH | 0 | 0 | 0 | 0 | 0
|  | 2023 ICUG | 0 | 0 | 0 | 0
|  | CWSP - 2023 ICUG | 0 | 0 | 2 | 0
|  | CWSP 2022-2023 | 0.773 | 1.1939 | 11.76 | 0
|  | ECOP | 0 | 0 | 0 | 0
|  | Pre | 0.052841 | 0 | 0 | 0
|  | PSPS | 16.84 | 2.9066 | 15.9613 | 0
|  | PSPS - 2023 ICUG | 27.5437 | 10.2781 | 0 | 0
|  | PSPS - Community Resiliency | 2.1408 | 5.0136 | 0 | 0
|  | PSPS - Scoped | 0.53447 | 0 | 0 | 0
|  | PSS Approved | 2.5902 | 0.57576 | 0 | 0
|  | REMG 2022-2023 | 0 | 0 | 0 | 0
|  | Remote Grid Pilot | 0 | 0 | 0 | 0
V2 Not Top Risk Total |  |  | 95.6774 | 31.0319 | 31.4967 | 1.4989
V2 Top Risk | FRRB |  | 15.3314 | 0 | 0 | 0
| IF |  | 0 | 0 | 0 | 0
| Other |  | 0 | 1.7032 | 0 | 0
| SH | 2023 ICUG | 0 | 0.50644 | 0 | 0
|  | CWSP | 0.089394 | 0 | 0 | 0
|  | CWSP - 2023 ICUG | 90.2153 | 28.1413 | 4.92 | 0
|  | CWSP 2022-2023 | 33.4753 | 1.658 | 0.035985 | 0.41496
|  | ECOP - Top 20% | 22.8638 | 4.0089 | 0 | 0
|  | FRRB - REMG - 2021 | 0 | 0 | 0 | 0
|  | PSPS | 9.8208 | 0.89091 | 0 | 0
|  | PSPS - 2023 ICUG | 123.179 | 41.3831 | 28.393 | 18.2596
|  | PSPS - Community Resiliency | 0.90966 | 0.12576 | 0 | 0
|  | REMG 2022-2023 | 0 | 0 | 0 | 0
|  | Remote Grid Pilot | 0 | 0 | 0 | 0
|  | Top 20% MAVF CPZ | 4.0593 | 0 | 0 | 0
|  | Top 250 Miles | 10.0083 | 16.8009 | 0 | 0
|  | Top 50 Miles | 11.3004 | 1.3201 | 0 | 0
V2 Top Risk Total |  |  | 321.2528 | 96.5386 | 33.349 | 18.6746
V3 Not Top Risk | FRRB |  | 0 | 0 | 0 | 0
| SH | 0 | 0 | 0 | 0 | 0
|  | CWSP 2024 | 0 | 0 | 4.29 | 0.33996
V3 Not Top Risk Total |  |  | 0 | 0 | 4.29 | 0.33996
V3 Top Risk |  | V3 Tranche 1 | 0 | 15.1375 | 53.248 | 76.185
| FRRB |  | 16.9748 | 2.05 | 1.2197 | 0.84905
| SH | 0 | 0 | 0 | 0 | 0
|  | CWSP 2024 | 22.7349 | 297.3763 | 520.3354 | 768.0183
|  | PSPS | 0 | 11.06 | 0 | 0
|  | PSPS - 2023 ICUG | 0 | 0.52917 | 0.55814 | 0
|  | V3 Tranche 1 | 0 | 35.725 | 38.487 | 15.3807
V3 Top Risk Total |  |  | 39.7097 | 361.878 | 613.8482 | 860.433
Grand Total |  |  | 534.3408 | 588.2466 | 682.9839 | 880.9464

## July 2022_Project List_Updated (hidden)
CONFIDENTIAL – Provided Pursuant to Confidentiality Declaration ("OEIS Confidentiality Declaration-RN-PGE-22-04 Attachment")
Order | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2023 Forecast Miles | 2024-2026 Forecast Miles | Div | Region | City | County | Latitude | Longitude | Circuit Protection Zone (V2) | 2021-2023 Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | 2024-2026 Risk Rank (V3) | v3 Mean Risk | Measured Effectiveness | Project Type (see 3rd tab for description) | HFTD Tier | Unique ID
35117455 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.172 | - | - | 1.172 | 1.172 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.594 | PARADISE 11052214 | 2141 | 0.0062243 | PARADISE 11052214 | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 1
35118673 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.6064 | - | - | 2.6064 | 2.6064 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8005 | -121.6047 | PARADISE 1105121988 | 2484 | 0.0019488 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 2
35118674 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5212 | - | - | 2.5212 | 2.5212 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.6017 | PARADISE 1105121988 | 2484 | 0.0019488 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 3
35126752 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.5909 | - | - | 1.5909 | 1.5909 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7333 | -121.6353 | PARADISE 1104409622 | 817 | 0.090831 | PARADISE 11032486 | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 4
35127550 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.9189 | - | - | 2.9189 | 2.9189 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7858 | -121.6004 | PARADISE 110636042 | 2933 | 3.0817e-05 | PARADISE 110636042 | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 5
35144480 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.7155 | - | - | 3.7155 | 3.7155 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8116 | -121.5956 | PARADISE 1105121988 | 2484 | 0.0019488 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 6
35227400 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.233 | - | - | 3.233 | 3.233 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7712 | -121.6031 | PARADISE 1105CB | 2808 | 0.00026897 | PARADISE 1105CB | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 7
35227401 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.7701 | - | - | 1.7701 | 1.7701 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7628 | -121.6233 | PARADISE 11032534 | 2922 | 3.3375e-05 | PARADISE 11032534 | 69 | 0.020609 | 99% | Butte Rebuild | Tier 2 | 8
35227402 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.404 | - | - | 1.404 | 1.404 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6071 | PARADISE 1105CB | 2808 | 0.00026897 | PARADISE 1105CB | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 9
35227404 | Community Rebuild | 95F | ESTS | ESTIMATING | 0.99697 | - | - | 0.99697 | 0.99697 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7538 | -121.6172 | PARADISE 1104CB | 2941 | 2.9018e-05 | PARADISE 1104CB | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 10
35227405 | Community Rebuild | 95F | PEND | PERMITTING/DEPENDENCY | 0.41477 | - | - | 0.41477 | 0.41477 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7578 | -121.6071 | PARADISE 1105CB | 2808 | 0.00026897 | PARADISE 1105CB | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 11
35227406 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.8989 | - | - | 2.8989 | 2.8989 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7523 | -121.6185 | PARADISE 110439216 | 2467 | 0.0021 | PARADISE 1104CB | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 12
35227408 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.1447 | - | - | 2.1447 | 2.1447 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7524 | -121.6126 | PARADISE 1104CB | 2941 | 2.9018e-05 | PARADISE 1104CB | 2530 | 0.00029731 | 99% | Butte Rebuild | HFRA | 13
35227409 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.646 | - | - | 3.646 | 3.646 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7501 | -121.6242 | PARADISE 110439216 | 2467 | 0.0021 | PARADISE 110439216 | 1178 | 0.0017042 | 99% | Butte Rebuild | Tier 2 | 14
35227411 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.3665 | - | - | 3.3665 | 3.3665 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7595 | 121.6024 | PARADISE 110599226 | 2912 | 4.1187e-05 | PARADISE 1105CB | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 15
35227412 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.2926 | - | - | 1.2926 | 1.2926 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.769 | -121.5786 | PARADISE 1104961990 | 2954 | 2.3677e-05 | PARADISE 1104961990 | 622 | 0.0042646 | 99% | Butte Rebuild | Tier 2 | 16
35227413 | Community Rebuild | 95F | ESTS | ESTIMATING | 4.1278 | - | - | 4.1278 | 4.1278 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7423 | -121.6423 | PARADISE 110443008 | 734 | 0.10501 | PARADISE 110343008 | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 17
35227415 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.2267 | - | - | 5.2267 | 5.2267 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7389 | -121.6402 | PARADISE 11042488 | 2924 | 3.2259e-05 | PARADISE 11032486 | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 18
35227417 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.7458 | - | - | 5.7458 | 5.7458 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7323 | -121.6513 | PARADISE 110443008 | 734 | 0.10501 | PARADISE 110343008 | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 19
35246308 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.3438 | - | - | 2.3438 | 2.3438 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7572 | -121.5722 | PARADISE 1104920400 | 2126 | 0.0064968 | PARADISE 1104920400 | 1617 | 0.00084939 | 99% | Butte Rebuild | Tier 2 | 20
35246309 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.2898 | - | - | 1.2898 | 1.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7752 | -121.6093 | PARADISE 1106CB | 2813 | 0.0002457 | PARADISE 1106CB | 1546 | 0.00092573 | 99% | Butte Rebuild | Tier 2 | 21
35246316 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.5938 | - | - | 3.5938 | 3.5938 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7265 | -121.6374 | PARADISE 1104409622 | 817 | 0.090831 | PARADISE 11032486 | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 22
35246589 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.0511 | - | - | 1.0511 | 1.0511 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.764 | -121.5986 | PARADISE 1105CB | 2808 | 0.00026897 | PARADISE 1105CB | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 23
35246590 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.2388 | - | - | 2.2388 | 2.2388 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7696 | -121.579 | PARADISE 11042206 | 2383 | 0.0027 | PARADISE 11042206 | 2198 | 0.00043536 | 99% | Butte Rebuild | Tier 2 | 24
35246591 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.2898 | - | - | 4.2898 | 4.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7485 | -121.6086 | PARADISE 1104CB | 2941 | 2.9018e-05 | PARADISE 110439214 | 1563 | 0.00090699 | 99% | Butte Rebuild | Tier 2 | 25
35246598 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.4871 | - | - | 3.4871 | 3.4871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8149 | -121.5802 | PARADISE 1105878870 | 2211 | 0.0048412 | PARADISE 1105878870 | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 26
35352072 | Community Rebuild | 08W | ESTS | ESTIMATING | 0.56818 | - | - | 0.56818 | 0.56818 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6265 | PARADISE 11061212 | 2910 | 4.2503e-05 | PARADISE 11061212 | 26 | 0.026975 | 99% | Butte Rebuild | Tier 2 | 27
35353399 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.2386 | - | - | 3.2386 | 3.2386 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.5973 | PARADISE 1105121988 | 2484 | 0.0019488 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 28
35353463 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.8871 | - | - | 4.8871 | 4.8871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8121 | -121.5914 | PARADISE 1105121988 | 2484 | 0.0019488 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 29
35353466 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.4148 | - | - | 2.4148 | 2.4148 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8091 | -121.5998 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105121988 | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 30
35353467 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5544 | - | - | 2.5544 | 2.5544 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8182 | -121.5952 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 31
35321894 | Fire Rebuild | 08W | ESTS | Estimating | 0.087121 | - | - | 0.087121 | 0.087121 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0773 | -122.2434 | POINT MORETTI 110112122 | 2199 | 0.0051004 | POINT MORETTI 110112122 | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 32
35334404 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.6 | - | - | 0.6 | 0.6 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0671 | -122.2231 | POINT MORETTI 11015076 | 1393 | 0.033758 | POINT MORETTI 1101415734 | 2485 | 0.00031335 | 99% | FRRB | Tier 2 | 33
35298571 | Base SH | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.469 | -122.2542 | ANDERSON 11031600 | 143 | 0.2889 | ANDERSON 11031600 | 3058 | 0.00011858 | 99% | CWSP 2022-2023 | Tier 2 | 34
35331305 | Base SH | 08W | UNSE | Scoping/Scoped | 0.445 | - | - | 0.445 | 0.445 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4699 | -122.2473 | ANDERSON 11031600 | 143 | 0.2889 | ANDERSON 11031600 | 3058 | 0.00011858 | 99% | CWSP - 2023 ICUG | Tier 2 | 35
35311895 | Base SH | 08W | UNSE | Scoping/Scoped | 2.78 | - | - | 2.78 | 2.78 | - | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | ANDERSON 1103226050 | 262 | 0.22913 | ANDERSON 1103226050 | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 36
35330815 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4792 | -122.2645 | ANDERSON 1103226050 | 262 | 0.22913 | ANDERSON 1103226050 | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 37
35277925 | Base SH | 08W | PEND | Permitting/Dependency | 0.21326 | - | - | 0.21326 | 0.21326 | - | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0746 | -119.4845 | AUBERRY 1101CB | 63 | 0.39206 | AUBERRY 1101CB | 2126 | 0.00047477 | 99% | CWSP 2022-2023 | Tier 2 | 38
35277924 | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | - | 0.12955 | 0.23864 | 0.23864 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0071 | -119.4086 | AUBERRY 1101R2578 | 163 | 0.27714 | AUBERRY 1101R2578 | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 39
35277938 | Base SH | 08W | ESTS | Estimating | 0.38996 | - | 0.27973 | 0.6697 | 0.6697 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0125 | -119.4038 | AUBERRY 1101R2578 | 163 | 0.27714 | AUBERRY 1101R2578 | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 40
35278093 | Base SH | 08W | ESTS | Estimating | 0.41496 | - | 0.52008 | 0.93504 | 0.93504 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9797 | -119.3677 | AUBERRY 1101R2578 | 163 | 0.27714 | AUBERRY 1101R2578 | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 41
35333501 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9851 | -121.1296 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 42
35333503 | Base SH | 08W | UNSE | Scoping/Scoped | 0.3 | 1.44 | - | 1.74 | 1.74 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9959 | -121.1355 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 43
35333504 | Base SH | 08W | UNSE | Scoping/Scoped | 0.45 | - | - | 0.45 | 0.45 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9992 | -121.1363 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 44
35311896 | Base SH | 08W | UNSE | Scoping/Scoped | 2.76 | - | - | 2.76 | 2.76 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9961 | -121.1091 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 45
35314415 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | 0.04 | - | 2.09 | 2.09 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9962 | -121.1167 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 46
35314416 | Base SH | 08W | UNSE | Scoping/Scoped | 1.1199 | 0.48011 | - | 1.6 | 1.6 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9981 | -121.1168 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 47
35334232 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9855 | -121.1087 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 48
35334234 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9781 | -121.1088 | BELL 11082202 | 118 | 0.32016 | BELL 11082202 | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 49
35318074 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.072 | -122.2298 | BIG BASIN 11022253 | 2246 | 0.0041981 | BIG BASIN 11022253 | 936 | 0.002497 | 99% | FRRB | Tier 2 | 50
35342335 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.5299 | - | - | 1.5299 | 1.5299 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1672 | -122.2131 | BIG BASIN 11025066 | 2359 | 0.0029066 | BIG BASIN 11025066 | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 51
35342336 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1699 | -122.2026 | BIG BASIN 11025066 | 2359 | 0.0029066 | BIG BASIN 11025066 | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 52
35342337 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.52008 | - | - | 0.52008 | 0.52008 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1657 | -122.2231 | BIG BASIN 11025066 | 2359 | 0.0029066 | BIG BASIN 11025066 | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 53
35342338 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.163 | -122.1902 | BIG BASIN 11025066 | 2359 | 0.0029066 | BIG BASIN 11025066 | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 54
35311924 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.08447 | - | - | 0.08447 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6747 | -121.3798 | BIG BEND 11021972 | 1288 | 0.040961 | BIG BEND 1102884340 | 267 | 0.010152 | 99% | FRRB | Tier 3 | 55
35292784 | Fire Rebuild | 08W | ESTS | Estimating | 3.0644 | - | - | 3.0644 | 3.0644 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | BIG MEADOWS 21012260 | 995 | 0.067786 | BIG MEADOWS 21012260 | 2135 | 0.00047036 | 99% | FRRB | Tier 2 | 56
35292788 | Fire Rebuild | 08W | ESTS | Estimating | 1.1 | - | - | 1.1 | 1.1 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | BIG MEADOWS 21012476 | 2342 | 0.0030704 | BIG MEADOWS 21012476 | 1533 | 0.00093756 | 99% | FRRB | Tier 2 | 57
35286103 | Base SH | 08W | UNSE | Scoping/Scoped | 3.0701 | - | - | 3.0701 | 3.0701 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | BIG MEADOWS 21012510 | 3328 | 4.1333e-06 | BIG MEADOWS 21012510 | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 58
35311596 | Base SH | 08W | UNSE | Scoping/Scoped | 3 | - | - | 3 | 3 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 | BIG MEADOWS 21012510 | 3328 | 4.1333e-06 | BIG MEADOWS 21012510 | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 59
35311626 | Base SH | 08W | UNSE | Scoping/Scoped | 3.64 | - | - | 3.64 | 3.64 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 | BIG MEADOWS 21012510 | 3328 | 4.1333e-06 | BIG MEADOWS 21012510 | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 60
35311627 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | - | - | 2.05 | 2.05 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 | BIG MEADOWS 21012510 | 3328 | 4.1333e-06 | BIG MEADOWS 21012510 | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 61
35279181 | Fire Rebuild | 08W | ESTS | Estimating | 5.589 | - | - | 5.589 | 5.589 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 62
35279182 | Fire Rebuild | 08W | ESTS | Estimating | 2.0701 | - | - | 2.0701 | 2.0701 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 63
35280560 | Fire Rebuild | 08W | ESTS | Estimating | 2.64 | - | - | 2.64 | 2.64 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 64
35320445 | Base SH | 08W | UNSE | Scoping/Scoped | 17.7201 | - | - | 17.7201 | 17.7201 | - | LP | Region 4 - Central Coast | Buellton | SANTA BARBARA | 34.6236 | -120.185 | BUELLTON 1102CB | 307 | 0.21085 | BUELLTON 1102CB | 2847 | 0.00018253 | 99% | CWSP - 2023 ICUG | Tier 2 | 65
35299634 | Base SH | 08W | UNSE | Scoping/Scoped | 2.61 | - | - | 2.61 | 2.61 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6568 | -121.5763 | CLARK ROAD 11022070 | 1033 | 0.063106 | CLARK ROAD 11022070 | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 66
35329014 | Base SH | 08W | UNSE | Scoping/Scoped | 3.1701 | - | - | 3.1701 | 3.1701 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6666 | -121.5712 | CLARK ROAD 11022070 | 1033 | 0.063106 | CLARK ROAD 11022070 | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 67
35329012 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6201 | - | - | 1.6201 | 1.6201 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6908 | -121.5733 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102514690 | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 68
35329013 | Base SH | 08W | UNSE | Scoping/Scoped | 1.85 | 0.039962 | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6805 | -121.5693 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102514690 | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 69
35299633 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | - | - | 2.14 | 2.14 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6766 | -121.5675 | CLARK ROAD 11022094 | 1703 | 0.018088 | CLARK ROAD 1102514690 | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 70
35299635 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6988 | -121.5743 | CLARK ROAD 110247006 | 1535 | 0.025936 | CLARK ROAD 110247006 | 47 | 0.022808 | 99% | PSPS | Tier 2 | 71
35329016 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.709 | -121.5757 | CLARK ROAD 110247006 | 1535 | 0.025936 | CLARK ROAD 110247006 | 47 | 0.022808 | 99% | PSPS | Tier 2 | 72
35329009 | Base SH | 08W | UNSE | Scoping/Scoped | 0.94091 | - | 0.020076 | 0.96098 | 0.96098 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.655 | -121.5839 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 73
35329010 | Base SH | 08W | UNSE | Scoping/Scoped | 2.814 | - | 0.020076 | 2.8341 | 2.8341 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6564 | -121.5838 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 74
35329011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3229 | - | - | 2.3229 | 2.3229 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6667 | -121.5826 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 75
35299631 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4299 | - | - | 3.4299 | 3.4299 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6474 | -121.6306 | CLARK ROAD 110281296 | 698 | 0.11218 | CLARK ROAD 110281296 | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 76
35299629 | Base SH | 08W | UNSE | Scoping/Scoped | 0.89091 | - | - | 0.89091 | 0.89091 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.654 | -121.6323 | CLARK ROAD 1102CB | 268 | 0.22632 | CLARK ROAD 1102CB | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 77
35329008 | Base SH | 08W | UNSE | Scoping/Scoped | 0.31307 | - | - | 0.31307 | 0.31307 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6413 | -121.6413 | CLARK ROAD 1102CB | 268 | 0.22632 | CLARK ROAD 1102CB | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 78
35334228 | Base SH | 08W | UNSE | Scoping/Scoped | 1.89 | - | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8468 | -122.589 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 79
35334229 | Base SH | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8493 | -122.6179 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 80
35334230 | Base SH | 08W | UNSE | Scoping/Scoped | 1.64 | - | - | 1.64 | 1.64 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8348 | -122.6319 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 81
35311897 | Base SH | 08W | UNSE | Scoping/Scoped | 2.11 | - | - | 2.11 | 2.11 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 | CORNING 110253184 | 413 | 0.17544 | CORNING 110253184 | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 82
35311898 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.9193 | -122.4369 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 83
35340270 | Base SH | 08W | UNSE | Scoping/Scoped | 1.84 | - | - | 1.84 | 1.84 | - | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 84
35340271 | Base SH | 08W | UNSE | Scoping/Scoped | 1.96 | - | - | 1.96 | 1.96 | - | NV | Region 2 - North East | Corning | Tehama | 39.9043 | -122.5022 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 85
35340272 | Base SH | 08W | UNSE | Scoping/Scoped | 1.56 | - | - | 1.56 | 1.56 | - | NV | Region 2 - North East | Corning | Tehama | 39.8887 | -122.5232 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 86
35340273 | Base SH | 08W | UNSE | Scoping/Scoped | 1.4299 | - | - | 1.4299 | 1.4299 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8831 | -122.5469 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 87
35340274 | Base SH | 08W | UNSE | Scoping/Scoped | 1.59 | - | - | 1.59 | 1.59 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 | CORNING 1102915324 | 457 | 0.16319 | CORNING 1102915324 | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 88
35311899 | Base SH | 08W | UNSE | Scoping/Scoped | 3.44 | - | - | 3.44 | 3.44 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 89
35316561 | Base SH | 08W | UNSE | Scoping/Scoped | 4.41 | - | - | 4.41 | 4.41 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 90
35332218 | Base SH | 08W | UNSE | Scoping/Scoped | 3.26 | - | - | 3.26 | 3.26 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3986 | -122.3143 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 91
35332213 | Base SH | 08W | UNSE | Scoping/Scoped | 2.37 | - | - | 2.37 | 2.37 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3892 | -122.3258 | COTTONWOOD 1102544790 | 123 | 0.31273 | COTTONWOOD 1102544790 | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 92
35332214 | Base SH | 08W | UNSE | Scoping/Scoped | 4.04 | - | - | 4.04 | 4.04 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3899 | -122.3499 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 93
35332215 | Base SH | 08W | UNSE | Scoping/Scoped | 2.26 | - | - | 2.26 | 2.26 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4149 | -122.3421 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 94
35332216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.4042 | -122.3264 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 95
35332217 | Base SH | 08W | UNSE | Scoping/Scoped | 3.03 | - | 0.053 | 3.083 | 3.083 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3886 | -122.3831 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 96
35316567 | Base SH | 08W | UNSE | Scoping/Scoped | 3.42 | - | - | 3.42 | 3.42 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 97
35316569 | Base SH | 08W | UNSE | Scoping/Scoped | 4.81 | - | 0.032 | 4.842 | 4.842 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 98
35312540 | Base SH | 08W | UNSE | Scoping/Scoped | 4.88 | - | - | 4.88 | 4.88 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 | COTTONWOOD 11029026 | 271 | 0.22599 | COTTONWOOD 11029026 | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 99
35312541 | Base SH | 08W | UNSE | Scoping/Scoped | 0.43 | - | - | 0.43 | 0.43 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9777 | -120.3274 | CURTIS 1701CB | 1166 | 0.051116 | CURTIS 1701CB | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 100
35332868 | Base SH | 08W | UNSE | Scoping/Scoped | 2.53 | - | - | 2.53 | 2.53 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9803 | -120.337 | CURTIS 1701CB | 1166 | 0.051116 | CURTIS 1701CB | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 101
74010582 | Other | 30A | PEND | Permitting/Dependency | 1.3299 | - | - | 1.3299 | 1.3299 | - | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | DIAMOND SPRINGS 11071402 | 811 | 0.092281 | DIAMOND SPRINGS 11071402 | 1184 | 0.0016787 | 99% | Other | Tier 2 | 102
35284023 | Fire Rebuild | 08W | DCNL | CLOSED | 1.1699 | - | - | 1.1699 | 1.1699 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4361 | -122.5779 | DUNBAR 1101416 | 1684 | 0.019316 | DUNBAR 1103416 | 732 | 0.0035071 | 99% | FRRB - UG - 2021 | Tier 3 | 103
35228774 | Base SH | 08W | ESTS | Estimating | 1.0008 | - | - | 1.0008 | 1.0008 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 | DUNBAR 1101CB | 2048 | 0.007993 | DUNBAR 1103234 | 1091 | 0.0019786 | 99% | PSPS - Community Resiliency | Tier 2 | 104
35228775 | Base SH | 08W | ESTS | Estimating | 0.90341 | - | - | 0.90341 | 0.90341 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 | DUNBAR 1101CB | 2048 | 0.007993 | DUNBAR 1103160 | 1232 | 0.0015282 | 99% | PSPS - Community Resiliency | Tier 2 | 105
35223063 | Base SH | 08W | ESTS | Estimating | 0.3197 | - | - | 0.3197 | 0.3197 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 | DUNBAR 1101CB | 2048 | 0.007993 | DUNBAR 1103839384 | 1567 | 0.00090511 | 99% | PSPS - Community Resiliency | Tier 2 | 106
35312542 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | SO | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3791 | -122.5192 | DUNBAR 1103534 | 1827 | 0.01369 | DUNBAR 1101534 | 440 | 0.0063584 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 107
35343741 | Base SH | 08W | UNSE | Scoping/Scoped | 0.58 | - | - | 0.58 | 0.58 | - | SO | Region 1 - North Coast | Sonoma | SONOMA | 38.3371 | -122.4929 | DUNBAR 1103534 | 1827 | 0.01369 | DUNBAR 1101440 | 1080 | 0.0020136 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 108
35285594 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | SI | Region 2 - North East | Twin Bridges | EL DORADO | 38.8075 | -120.0935 | ECHO SUMMIT 1101481660 | 2005 | 0.0089565 | ECHO SUMMIT 1101481660 | 2299 | 0.00038767 | 99% | FRRB | Tier 2 | 109
74001486 | Other | 30A | ADER | Estimating | 1.4576 | - | - | 1.4576 | 1.4576 | - | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | El Cerrito G 1105BR160 | 2792 | 0.00031068 | El Cerrito G 1105BR160 | 2633 | 0.00025777 | 99% | Other | Tier 2 & 3 | 110
35058026 | Base SH | 08W | PEND | Permitting/Dependency | 0.6267 | - | - | 0.6267 | 0.6267 | - | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7593 | -120.5087 | EL DORADO PH 210163464 | 1138 | 0.05356 | EL DORADO PH 210163464 | 370 | 0.0074889 | 99% | CWSP 2022-2023 | Tier 3 | 111
35312543 | Base SH | 08W | UNSE | Scoping/Scoped | 3.71 | - | - | 3.71 | 3.71 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5896 | -122.5395 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 112
35332360 | Base SH | 08W | UNSE | Scoping/Scoped | 5.46 | - | - | 5.46 | 5.46 | - | NV | Region 2 - North East | Willows | GLENN | 39.456 | -122.5138 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 113
35332362 | Base SH | 08W | UNSE | Scoping/Scoped | 3.83 | - | - | 3.83 | 3.83 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4286 | -122.5052 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 114
35332363 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | - | 1.13 | 1.13 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4073 | -122.5471 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 115
35332364 | Base SH | 08W | UNSE | Scoping/Scoped | 0.085 | - | 0.6 | 0.685 | 0.685 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.3944 | -122.5518 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 116
35330812 | Base SH | 08W | UNSE | Scoping/Scoped | 2.49 | - | - | 2.49 | 2.49 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5561 | -122.5414 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 117
35316278 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4868 | -122.5188 | ELK CREEK 11012002 | 315 | 0.20473 | ELK CREEK 11012002 | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 118
35312544 | Base SH | 08W | UNSE | Scoping/Scoped | 0.44 | - | - | 0.44 | 0.44 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5927 | -122.5431 | ELK CREEK 110193504 | 206 | 0.25426 | ELK CREEK 110193504 | 1350 | 0.0012407 | 99% | PSPS - 2023 ICUG | Tier 2 | 119
35312545 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8586 | -121.0805 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 120
35325589 | Base SH | 08W | UNSE | Scoping/Scoped | 1.21 | - | - | 1.21 | 1.21 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8537 | -121.0803 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 121
35325590 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8575 | -121.0758 | FLINT 1101750 | 152 | 0.28318 | FLINT 1101750 | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 122
35326790 | Base SH | 08W | UNSE | Scoping/Scoped | 0.14792 | - | - | 0.14792 | 0.14792 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8934 | -121.0677 | FLINT 1101958726 | 2980 | 1.7619e-05 | FLINT 1101958726 | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 123
35312546 | Base SH | 08W | UNSE | Scoping/Scoped | 1.013 | - | - | 1.013 | 1.013 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8933 | -121.0676 | FLINT 1101958726 | 2980 | 1.7619e-05 | FLINT 1101958726 | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 124
35320444 | Base SH | 08W | UNSE | Scoping/Scoped | 7.4 | - | - | 7.4 | 7.4 | - | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.3203 | -120.6932 | GOLDTREE 1105CB | 1104 | 0.056447 | GOLDTREE 1105CB | 1903 | 0.00059698 | 99% | PSPS - 2023 ICUG | Tier 2 | 125
35284810 | Fire Rebuild | 08W | ESTS | Estimating | 0.85814 | - | - | 0.85814 | 0.85814 | - | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.2086 | -122.3251 | HALF MOON BAY 11036012 | 2186 | 0.0054078 | HALF MOON BAY 11036018 | 2174 | 0.00044555 | 99% | FRRB | Tier 2 | 126
35283198 | Base SH | 08W | ESTS | Estimating | 0.27803 | - | - | 0.27803 | 0.27803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.108 | -122.9558 | HARTLEY 1101698 | 58 | 0.39723 | HARTLEY 1101698 | 486 | 0.0056859 | 99% | CWSP 2022-2023 | Tier 2 | 127
35231620 | Base SH | 08W | PEND | Permitting/Dependency | 2.6782 | - | - | 2.6782 | 2.6782 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 | HIGHLANDS 1102628 | 27 | 0.5487 | HIGHLANDS 1102628 | 29 | 0.026126 | 99% | Top 250 Miles | Tier 2 & 3 | 128
35329471 | Base SH | 08W | UNSE | Scoping/Scoped | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9373 | -122.6091 | HIGHLANDS 1104CB | 3243 | 5.4342e-06 | HIGHLANDS 1104CB | 1561 | 0.00090896 | 99% | PSPS - 2023 ICUG | Tier 2 | 129
35320447 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | 1.09 | - | 1.93 | 1.93 | - | SI | Region 2 - North East | Granite Bay | PLACER | 38.782 | -121.1456 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 130
35339664 | Base SH | 08W | UNSE | Scoping/Scoped | 0.17 | 0.75 | - | 0.92 | 0.92 | - | SI | Region 2 - North East | Loomis | PLACER | 38.7815 | -121.1632 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 131
35339665 | Base SH | 08W | UNSE | Scoping/Scoped | 0.69 | - | - | 0.69 | 0.69 | - | SI | Region 2 - North East | Loomis | PLACER | 38.767 | -121.1635 | HORSESHOE 110150140 | 661 | 0.11734 | HORSESHOE 110150140 | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 132
35342143 | Base SH | 08W | UNSE | Scoping/Scoped | 3.354 | - | 1.962 | 5.316 | 5.316 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2645 | -122.1722 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 133
35342144 | Base SH | 08W | UNSE | Scoping/Scoped | 1.802 | - | 1.046 | 2.848 | 2.848 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2553 | -122.1615 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 134
35342145 | Base SH | 08W | UNSE | Scoping/Scoped | 0.163 | - | 0.13 | 0.293 | 0.293 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2566 | -122.1697 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 135
35342146 | Base SH | 08W | UNSE | Scoping/Scoped | 2.386 | - | 1.875 | 4.261 | 4.261 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.262 | -122.1635 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 136
35342147 | Base SH | 08W | UNSE | Scoping/Scoped | 1.865 | - | 1.343 | 3.208 | 3.208 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2706 | -122.167 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 137
35342148 | Base SH | 08W | UNSE | Scoping/Scoped | 1.265 | - | 1.095 | 2.36 | 2.36 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2714 | -122.1672 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 138
35342151 | Base SH | 08W | UNSE | Scoping/Scoped | 0.08 | - | 0.085 | 0.165 | 0.165 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2491 | -122.1769 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 139
35320442 | Base SH | 08W | UNSE | Scoping/Scoped | 0.578 | - | 0.464 | 1.052 | 1.052 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2515 | -122.161 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 140
35320462 | Base SH | 08W | UNSE | Scoping/Scoped | 0.35 | - | - | 0.35 | 0.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2642 | -122.1295 | JAMESON 1105371694 | 1848 | 0.012819 | JAMESON 1105371694 | 8953 | 2.3644e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 141
35320460 | Base SH | 08W | UNSE | Scoping/Scoped | 1.78 | - | - | 1.78 | 1.78 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3063 | -122.1288 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 142
35320461 | Base SH | 08W | UNSE | Scoping/Scoped | 3.56 | - | - | 3.56 | 3.56 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.299 | -122.1519 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 143
35338404 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | 0.56 | 1.59 | 1.59 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3141 | -122.1263 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 144
35338405 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2972 | -122.1262 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 145
35338406 | Base SH | 08W | UNSE | Scoping/Scoped | 1.14 | - | - | 1.14 | 1.14 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2877 | -122.1043 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 146
35338407 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66 | - | 0.41 | 1.07 | 1.07 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3039 | -122.0964 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 147
35338408 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | 0.09 | 1.22 | 1.22 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3148 | -122.0962 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 148
35338409 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2968 | -122.1356 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 149
35338410 | Base SH | 08W | UNSE | Scoping/Scoped | 2.21 | - | - | 2.21 | 2.21 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2925 | -122.1292 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 150
35339293 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | NB | Region 2 - North East | Fairfield | SOLANO | 38.3158 | -122.1039 | JAMESON 1105466348 | 393 | 0.18223 | JAMESON 1105466348 | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 151
35320463 | Base SH | 08W | UNSE | Scoping/Scoped | 1.44 | - | - | 1.44 | 1.44 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.284 | -122.128 | JAMESON 1105913400 | 419 | 0.17457 | JAMESON 1105913400 | 987 | 0.0022992 | 99% | PSPS - 2023 ICUG | Tier 2 | 152
35337014 | Base SH | 08W | UNSE | Scoping/Scoped | 0.02 | 0.83 | - | 0.85 | 0.85 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2525 | -122.144 | JAMESON 11059472 | 724 | 0.10731 | JAMESON 11059472 | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 153
35337015 | Base SH | 08W | UNSE | Scoping/Scoped | 0.49 | - | - | 0.49 | 0.49 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2533 | -122.1356 | JAMESON 11059472 | 724 | 0.10731 | JAMESON 11059472 | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 154
35312548 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4517 | -122.3081 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 155
35339282 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4516 | -122.3245 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 156
35339283 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 157
35339285 | Base SH | 08W | UNSE | Scoping/Scoped | 2.32 | - | - | 2.32 | 2.32 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 158
35339286 | Base SH | 08W | UNSE | Scoping/Scoped | 2.54 | - | - | 2.54 | 2.54 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4362 | -122.3535 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 159
35339287 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4427 | -122.3927 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 160
35339288 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4403 | -122.4075 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 161
35339289 | Base SH | 08W | UNSE | Scoping/Scoped | 1.82 | - | - | 1.82 | 1.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4493 | -122.4078 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 162
35337008 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4409 | -122.3061 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 163
35337010 | Base SH | 08W | UNSE | Scoping/Scoped | 3.82 | - | - | 3.82 | 3.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4416 | -122.3258 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 164
35337011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.89 | - | - | 2.89 | 2.89 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4406 | -122.3414 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 165
35337012 | Base SH | 08W | UNSE | Scoping/Scoped | 4.92 | - | - | 4.92 | 4.92 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.443 | -122.3663 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 166
35317480 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4488 | -122.3179 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 167
35317887 | Base SH | 08W | UNSE | Scoping/Scoped | 0.8 | - | - | 0.8 | 0.8 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4377 | -122.3878 | JESSUP 11021550 | 389 | 0.18396 | JESSUP 11021550 | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 168
35312549 | Base SH | 08W | UNSE | Scoping/Scoped | 0.98 | - | - | 0.98 | 0.98 | - | NV | Region 2 - North East | Redding | SHASTA | 40.4913 | -122.2744 | JESSUP 1103348657 | 590 | 0.13388 | JESSUP 1103770356 | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 169
35332866 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4668 | -122.3357 | JESSUP 1103348657 | 590 | 0.13388 | JESSUP 1103770356 | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 170
35337163 | Base SH | 08W | ESTS | Estimating | 1.39 | 0.49 | - | 1.88 | 1.88 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.97 | -121.2606 | LINCOLN 1104275986 | 185 | 0.26526 | LINCOLN 1104275986 | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 171
35320449 | Base SH | 08W | ESTS | Estimating | 1.84 | - | - | 1.84 | 1.84 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9755 | -121.2772 | LINCOLN 1104275986 | 185 | 0.26526 | LINCOLN 1104275986 | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 172
35320312 | Base SH | 08W | ESTS | Estimating | 2.04 | - | - | 2.04 | 2.04 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9507 | -121.219 | LINCOLN 11042070 | 568 | 0.14111 | LINCOLN 11042070 | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 173
35332958 | Base SH | 08W | ESTS | Estimating | 1.37 | - | - | 1.37 | 1.37 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9431 | -121.219 | LINCOLN 11042070 | 568 | 0.14111 | LINCOLN 11042070 | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 174
35320450 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | 0.02 | - | 2.16 | 2.16 | - | SI | Region 2 - North East | Lincoln | PLACER | 39.0041 | -121.2605 | LINCOLN 1104685276 | 230 | 0.24208 | LINCOLN 1104685276 | 4147 | 5.2842e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 175
35274589 | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | - | - | 2.132 | 2.132 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5186 | -119.9402 | MARIPOSA 210135244 | 428 | 0.17286 | MARIPOSA 2101151918 | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 176
35274593 | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | - | - | 2.756 | 2.756 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5165 | -119.9716 | MARIPOSA 210135244 | 428 | 0.17286 | MARIPOSA 2101151918 | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 | 177
35280362 | Base SH | 08W | ESTS | Estimating | 0.1089 | - | - | 0.1089 | 0.1089 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9483 | MARIPOSA 2102440236 | 50 | 0.4205 | MARIPOSA 2102440236 | 400 | 0.0069412 | 99% | Top 250 Miles | Tier 2 & 3 | 178
35226621 | Base SH | 08W | PEND | Permitting/Dependency | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 110148212 | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 179
35192282 | Base SH | 08W | PEND | Permitting/Dependency | 2.04 | - | - | 2.04 | 2.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 110148212 | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 180
35174478 | Base SH | 08W | PEND | Permitting/Dependency | 1.04 | - | - | 1.04 | 1.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 181
35226873 | Base SH | 08W | UNSE | Scoping/Scoped | 1.0394 | - | - | 1.0394 | 1.0394 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 182
35226878 | Base SH | 08W | PEND | Permitting/Dependency | 0.58883 | - | - | 0.58883 | 0.58883 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 183
35227001 | Base SH | 08W | PEND | Permitting/Dependency | 0.7214 | - | - | 0.7214 | 0.7214 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 184
35227002 | Base SH | 08W | PEND | Permitting/Dependency | 0.43295 | - | - | 0.43295 | 0.43295 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 185
35227003 | Base SH | 08W | PEND | Permitting/Dependency | 0.58087 | - | - | 0.58087 | 0.58087 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 186
35227007 | Base SH | 08W | PEND | Permitting/Dependency | 2.8756 | - | - | 2.8756 | 2.8756 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 187
35227015 | Base SH | 08W | CONS | In-Construction | 0.01572 | 0.80947 | - | 0.82519 | 0.82519 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 188
35227025 | Base SH | 08W | ESTS | Estimating | 1.1828 | - | - | 1.1828 | 1.1828 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 189
35234756 | Base SH | 08W | ESTS | Estimating | 2.782 | - | - | 2.782 | 2.782 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 190
35234758 | Base SH | 08W | PEND | Permitting/Dependency | 0.58201 | - | - | 0.58201 | 0.58201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 191
35234862 | Base SH | 08W | PEND | Permitting/Dependency | 0.079924 | - | - | 0.079924 | 0.079924 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 192
35234865 | Base SH | 08W | PEND | Permitting/Dependency | 0.64754 | - | - | 0.64754 | 0.64754 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 193
35227160 | Base SH | 08W | PEND | Permitting/Dependency | 1.3201 | - | - | 1.3201 | 1.3201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | 8 | 0.91632 | MIDDLETOWN 1102302610 | 392 | 0.007089 | 99% | Top 50 Miles | Tier 2 | 194
35217271 | Base SH | 08W | PEND | Permitting/Dependency | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 195
35220895 | Base SH | 08W | PEND | Permitting/Dependency | 1.9299 | - | - | 1.9299 | 1.9299 | - | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 196
35228186 | Base SH | 08W | APPR | Estimating | 1.49 | - | - | 1.49 | 1.49 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 | MIDDLETOWN 1103830 | 14 | 0.71618 | MIDDLETOWN 1103830 | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 197
35056808 | Other | 30A | PEND | Permitting/Dependency | 1.5138 | - | - | 1.5138 | 1.5138 | - | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | Molino 110266006 | 534 | 0.14747 | Molino 110266006 | 1720 | 0.00074971 | 99% | Other | Tier 3 | 198
35305303 | Base SH | 08W | ESTS | Estimating | 1.065 | - | - | 1.065 | 1.065 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8972 | -120.989 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 199
35305308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66799 | - | - | 0.66799 | 0.66799 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8944 | -120.9647 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 200
35293662 | Base SH | 08W | ESTS | Estimating | 0.5 | - | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8956 | -120.9606 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 201
35293663 | Base SH | 08W | ESTS | Estimating | 0.98996 | - | - | 0.98996 | 0.98996 | - | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8964 | -120.922 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 202
35293665 | Base SH | 08W | ESTS | Estimating | 0.41572 | - | 0.070833 | 0.48655 | 0.48655 | - | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 203
35293670 | Base SH | 08W | UNSE | Scoping/Scoped | 0.54394 | - | - | 0.54394 | 0.54394 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8805 | -120.9418 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 204
35223032 | Base SH | 08W | ESTS | Estimating | 0.84924 | - | - | 0.84924 | 0.84924 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8855 | -121.0156 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | 99% | PSPS - Community Resiliency | Tier 2 | 205
35293508 | Base SH | 08W | ESTS | Estimating | 0.51004 | - | - | 0.51004 | 0.51004 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8729 | -120.991 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 206
35301112 | Base SH | 08W | ESTS | Estimating | 0.45 | 0.05 | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8641 | -120.9817 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 207
35300933 | Base SH | 08W | ESTS | Estimating | 0.77992 | - | - | 0.77992 | 0.77992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8775 | -120.993 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 208
35254067 | Base SH | 08W | ESTS | Estimating | 0.43996 | 0.039962 | - | 0.47992 | 0.47992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 | MOUNTAIN QUARRIES 2101CB | 68 | 0.38665 | MOUNTAIN QUARRIES 2101CB | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 209
35320464 | Base SH | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4267 | -122.2656 | PANORAMA 1101CB | 1038 | 0.062374 | PANORAMA 1101CB | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 210
35338402 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4214 | -122.2578 | PANORAMA 1101CB | 1038 | 0.062374 | PANORAMA 1101CB | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 211
35224856 | Other | 10K | APPR | Estimating | 2.803 | 0.10985 | - | 2.9129 | 1.7765 | - | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | Paradise 11042034 | 1537 | 0.025842 | Paradise 11042034 | 362 | 0.0076725 | 99% | Other | Tier 2 & 3 | 212
35219543 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24 | - | - | 0.24 | 0.24 | - | SI | Region 2 - North East | Placerville | EL DORADO | 38.7293 | -120.7998 | PLACERVILLE 1112CB | 2123 | 0.0065148 | PLACERVILLE 1112CB | 1979 | 0.00055552 | 99% | PSPS - Community Resiliency | Tier 2 | 213
35297464 | Fire Rebuild | 08W | ESTS | Estimating | 0.56818 | - | - | 0.56818 | 0.56818 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0777 | -122.2439 | POINT MORETTI 110112122 | 2199 | 0.0051004 | POINT MORETTI 110112122 | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 214
35293846 | Base SH | 08W | ESTS | Estimating | 0.85985 | - | - | 0.85985 | 0.85985 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3008 | -123.0524 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 215
35290504 | Base SH | 08W | ESTS | Estimating | 0.61004 | - | - | 0.61004 | 0.61004 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2145 | -123.0742 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 216
35290508 | Base SH | 08W | ESTS | Estimating | 0.62008 | - | - | 0.62008 | 0.62008 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1987 | -123.0496 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 217
35290808 | Base SH | 08W | ESTS | Estimating | 0.24508 | - | - | 0.24508 | 0.24508 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2815 | -123.1027 | POTTER VALLEY P H 11051904 | 75 | 0.37685 | POTTER VALLEY P H 11051904 | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 218
35285064 | Base SH | 08W | ADER | Estimating | 0.58636 | - | - | 0.58636 | 0.58636 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3076 | -123.1132 | POTTER VALLEY P H 110537476 | 396 | 0.18107 | POTTER VALLEY P H 110537476 | 2321 | 0.00037714 | 99% | CWSP 2022-2023 | Tier 2 | 219
35312550 | Base SH | 08W | UNSE | Scoping/Scoped | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 220
35317399 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 221
35330211 | Base SH | 08W | UNSE | Scoping/Scoped | 1.97 | - | - | 1.97 | 1.97 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.5858 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 222
35330213 | Base SH | 08W | UNSE | Scoping/Scoped | 5.26 | - | - | 5.26 | 5.26 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.5887 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 223
35330215 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0669 | -122.5993 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 224
35330216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0696 | -122.585 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 225
35330217 | Base SH | 08W | UNSE | Scoping/Scoped | 0.28 | - | - | 0.28 | 0.28 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0506 | -122.5833 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 226
35330219 | Base SH | 08W | UNSE | Scoping/Scoped | 3.13 | - | - | 3.13 | 3.13 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0688 | -122.6043 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 227
35330241 | Base SH | 08W | UNSE | Scoping/Scoped | 2.855 | - | - | 2.855 | 2.855 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0823 | -122.6045 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 228
35329472 | Base SH | 08W | UNSE | Scoping/Scoped | 2.869 | - | - | 2.869 | 2.869 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0748 | -122.6503 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 229
35329473 | Base SH | 08W | UNSE | Scoping/Scoped | 4.761 | - | - | 4.761 | 4.761 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0654 | -122.6333 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 230
35312551 | Base SH | 08W | UNSE | Scoping/Scoped | 3.205 | - | - | 3.205 | 3.205 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0837 | -122.66 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 231
35312552 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.023 | -122.6779 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 232
35330244 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0531 | -122.6813 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 233
35330245 | Base SH | 08W | UNSE | Scoping/Scoped | 0.09 | - | - | 0.09 | 0.09 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0541 | -122.6767 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 234
35330246 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | - | 1.03 | 1.03 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.6814 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 235
35330247 | Base SH | 08W | UNSE | Scoping/Scoped | 0.75 | - | - | 0.75 | 0.75 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.04 | -122.6823 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 236
35330248 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4 | - | - | 2.4 | 2.4 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0296 | -122.6802 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 237
35330249 | Base SH | 08W | UNSE | Scoping/Scoped | 4 | 0.25 | - | 4.25 | 4.25 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.6799 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 238
35329474 | Base SH | 08W | UNSE | Scoping/Scoped | 0.11 | 1.16 | - | 1.27 | 1.27 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0932 | -122.6804 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101754544 | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 239
35317398 | Base SH | 08W | UNSE | Scoping/Scoped | 3.52 | - | - | 3.52 | 3.52 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0581 | -122.693 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101754544 | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 240
35312558 | Base SH | 08W | UNSE | Scoping/Scoped | 0.71004 | - | - | 0.71004 | 0.71004 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0269 | -122.663 | REDBUD 1102CB | 371 | 0.18973 | REDBUD 1102523244 | 407 | 0.0068603 | 99% | PSPS - 2023 ICUG | Tier 2 | 241
35335235 | Base SH | 08W | UNSE | Scoping/Scoped | 3.15 | - | - | 3.15 | 3.15 | - | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5192 | -122.4719 | SILVERADO 2104708 | 1648 | 0.02118 | SILVERADO 2104708 | 619 | 0.0043024 | 99% | PSPS - 2023 ICUG | Tier 3 | 242
35278899 | Base SH | 08W | ESTS | Estimating | 1.3449 | - | - | 1.3449 | 1.3449 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 243
35279120 | Base SH | 08W | ESTS | Estimating | 1.004 | - | - | 1.004 | 1.004 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 244
35338384 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 | 245
35284364 | Base SH | 08W | ESTS | Estimating | 0.64261 | 0.040341 | - | 0.68295 | 0.68295 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 246
35284365 | Base SH | 08W | ESTS | Estimating | 1.6292 | 0.019508 | - | 1.6487 | 1.6487 | - | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2399 | -120.3619 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 247
35337306 | Base SH | 08W | ESTS | Estimating | 2.1871 | - | - | 2.1871 | 2.1871 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 | 248
35297984 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | NV | Region 2 - North East | Redding | SHASTA | 40.6951 | -122.3174 | STILLWATER 110148950 | 851 | 0.085979 | STILLWATER 110148950 | 2266 | 0.00040165 | 99% | FRRB | Tier 2 | 249
35312553 | Base SH | 08W | UNSE | Scoping/Scoped | 2.39 | - | - | 2.39 | 2.39 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8582 | -118.8837 | TEJON 11022455 | 642 | 0.12034 | TEJON 11022455 | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 250
35335286 | Base SH | 08W | UNSE | Scoping/Scoped | 5.21 | - | - | 5.21 | 5.21 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8542 | -118.893 | TEJON 11022455 | 642 | 0.12034 | TEJON 11022455 | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 251
35335287 | Base SH | 08W | UNSE | Scoping/Scoped | 2.18 | - | - | 2.18 | 2.18 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8466 | -118.8987 | TEJON 11022455 | 642 | 0.12034 | TEJON 11022455 | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 252
35335288 | Base SH | 08W | UNSE | Scoping/Scoped | 3.6 | 1.38 | - | 4.98 | 4.98 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9158 | -118.9258 | TEJON 11023751 | 691 | 0.11269 | TEJON 11023751 | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 253
35321445 | Base SH | 08W | UNSE | Scoping/Scoped | 8.11 | - | - | 8.11 | 8.11 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8908 | -118.9154 | TEJON 11023751 | 691 | 0.11269 | TEJON 11023751 | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 254
35312554 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 | TEJON 11023751 | 691 | 0.11269 | TEJON 11023751 | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 255
35312555 | Base SH | 08W | UNSE | Scoping/Scoped | 7.41 | - | - | 7.41 | 7.41 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8814 | -118.9012 | TEJON 1102732836 | 583 | 0.1353 | TEJON 1102732836 | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 256
35320607 | Base SH | 08W | UNSE | Scoping/Scoped | 10 | - | - | 10 | 10 | - | KE | Region 5 - Central Valley | LEBEC | KERN | 34.846 | -118.872 | TEJON 1102732836 | 583 | 0.1353 | TEJON 1102732836 | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 257
35256083 | Base SH | 08W | ESTS | Estimating | 1.847 | 0.0075758 | - | 1.8545 | 1.8545 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1434 | -123.0023 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 258
35283343 | Base SH | 08W | ESTS | Estimating | 0.85303 | - | - | 0.85303 | 0.85303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1488 | -122.9992 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 259
35283346 | Base SH | 08W | ESTS | Estimating | 0.77803 | - | - | 0.77803 | 0.77803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.13 | -122.997 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 260
35285249 | Base SH | 08W | ESTS | Estimating | 2.593 | - | - | 2.593 | 2.593 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1673 | -123.0087 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 261
35285251 | Base SH | 08W | ESTS | Estimating | 0.65303 | - | - | 0.65303 | 0.65303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1758 | -123.0191 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 262
35334753 | Base SH | 08W | ESTS | Estimating | 5.69 | - | - | 5.69 | 5.69 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4313 | -122.05 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 263
35334754 | Base SH | 08W | UNSE | Scoping/Scoped | 3.93 | - | - | 3.93 | 3.93 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4024 | -122.0318 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 264
35334755 | Base SH | 08W | UNSE | Scoping/Scoped | 1.47 | - | - | 1.47 | 1.47 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3911 | -122.0367 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 265
35320336 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4365 | -122.0527 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 266
35320339 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4168 | -122.0381 | VACAVILLE 110838316 | 122 | 0.31672 | VACAVILLE 110838316 | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 267
35320333 | Base SH | 08W | UNSE | Scoping/Scoped | 2.95 | - | - | 2.95 | 2.95 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.344 | -122.0247 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 268
35320334 | Base SH | 08W | UNSE | Scoping/Scoped | 2.5 | - | - | 2.5 | 2.5 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3618 | -122.0219 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 269
35334750 | Base SH | 08W | UNSE | Scoping/Scoped | 1.49 | - | - | 1.49 | 1.49 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3588 | -122.0245 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 270
35334752 | Base SH | 08W | UNSE | Scoping/Scoped | 1.81 | - | - | 1.81 | 1.81 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3655 | -122.0233 | VACAVILLE 11088762 | 64 | 0.39138 | VACAVILLE 11088762 | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 271
35320440 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3783 | -122.0044 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 272
35335291 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3771 | -121.9968 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 273
35335292 | Base SH | 08W | UNSE | Scoping/Scoped | 1.88 | - | - | 1.88 | 1.88 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3772 | -121.9918 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 274
35335293 | Base SH | 08W | UNSE | Scoping/Scoped | 2.41 | - | - | 2.41 | 2.41 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3663 | -121.9916 | VACAVILLE 1111CB | 500 | 0.15336 | VACAVILLE 1111CB | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 275
35334466 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3386 | -122.1218 | VOLTA 11011516 | 580 | 0.13616 | VOLTA 11011516 | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 276
35334467 | Base SH | 08W | UNSE | Scoping/Scoped | 2.0271 | - | - | 2.0271 | 2.0271 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3305 | -122.0971 | VOLTA 11011516 | 580 | 0.13616 | VOLTA 11011516 | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 277
35334468 | Base SH | 08W | UNSE | Scoping/Scoped | 1.136 | 0.095076 | - | 1.2311 | 1.2311 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3139 | -122.0706 | VOLTA 11011516 | 580 | 0.13616 | VOLTA 11011516 | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 278
35254656 | Base SH | 08W | PEND | Permitting/Dependency | 0.44205 | - | - | 0.44205 | 0.44205 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 | VOLTA 11011568 | 85 | 0.36191 | VOLTA 11011568 | 2428 | 0.00033385 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 279
35254259 | Base SH | 08W | UNSE | Scoping/Scoped | 0.85 | - | - | 0.85 | 0.85 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 | VOLTA 1101CB | 76 | 0.37545 | VOLTA 1101CB | 2202 | 0.00043332 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 280
35297692 | Fire Rebuild | 08W | ESTS | Estimating | 4.6598 | - | - | 4.6598 | 4.6598 | - | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 281
35334407 | Fire Rebuild | 08W | ESTS | Estimating | 0.089962 | - | - | 0.089962 | 0.089962 | - | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7875 | -123.4468 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 282
35320466 | Base SH | 08W | UNSE | Scoping/Scoped | 2 | - | - | 2 | 2 | - | HB | Region 1 - North Coast | Salyer | TRINITY | 40.8669 | -123.5148 | WILLOW CREEK 11032936 | 1474 | 0.029513 | WILLOW CREEK 11032936 | 938 | 0.0024804 | 99% | CWSP - 2023 ICUG | Tier 2 | 283
35283938 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | - | - | 2.4799 | 2.4799 | - | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3845 | -122.2937 | WOODSIDE 11018974 | 1145 | 0.05299 | WOODSIDE 11018974 | 1026 | 0.0021738 | 99% | CWSP 2022-2023 | Tier 3 | 284
35341054 | Fire Rebuild | 08W | ESTS | Estimating | 0.088258 | - | - | 0.088258 | 0.088258 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6143 | -121.4029 | WYANDOTTE 11031974 | 1849 | 0.012814 | WYANDOTTE 1103640652 | 250 | 0.010796 | 99% | FRRB | Tier 3 | 285
35335712 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.0087121 | - | - | 0.0087121 | 0.0087121 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6333 | -121.4164 | WYANDOTTE 11031974 | 1849 | 0.012814 | WYANDOTTE 1103640652 | 250 | 0.010796 | 99% | FRRB - UG - 2021 | Tier 3 | 286
35241075 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | - | - | 0.070076 | 0.070076 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 287
35241076 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | - | - | 0.11004 | 0.11004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 288
35241077 | Fire Rebuild | 08W | ADER | Estimating | 0.31004 | - | - | 0.31004 | 0.31004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 289
35236997 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | - | - | 0.28409 | 0.28409 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6827 | -121.3105 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - REMG - 2021 | Tier 3 | 290
35235672 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | - | - | 0.30303 | 0.30303 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 291
35235675 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | - | - | 0.11364 | 0.11364 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 | WYANDOTTE 11031508 | 1176 | 0.050062 | WYANDOTTE 11031508 | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 292
35320807 | Fire Rebuild | 08W | ADER | Estimating | 0.085227 | - | - | 0.085227 | 0.085227 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6274 | -121.3727 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 1103640652 | 250 | 0.010796 | 99% | FRRB | Tier 3 | 293
35331458 | Fire Rebuild | 08W | ESTS | Estimating | 0.08428 | - | - | 0.08428 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6272 | -121.3969 | WYANDOTTE 11031976 | 1299 | 0.040282 | WYANDOTTE 1103640652 | 250 | 0.010796 | 99% | FRRB | Tier 3 | 294
35312560 | Base SH | 08W | UNSE | Scoping/Scoped | 1.98 | - | - | 1.98 | 1.98 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5054 | -121.4999 | WYANDOTTE 11031504 | 645 | 0.12006 | WYANDOTTE 11031504 | 1945 | 0.0005689 | 99% | PSPS - 2023 ICUG | Tier 2 | 295
35331306 | Base SH | 08W | UNSE | Scoping/Scoped | 2.67 | - | - | 2.67 | 2.67 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5178 | -121.4854 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 296
35331307 | Base SH | 08W | UNSE | Scoping/Scoped | 2.55 | - | - | 2.55 | 2.55 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5261 | -121.4815 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 297
35331308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.82 | - | - | 0.82 | 0.82 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5171 | -121.4825 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 298
35343394 | Base SH | 08W | UNSE | Scoping/Scoped | 1.17 | - | - | 1.17 | 1.17 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5152 | -121.4932 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 299
35343395 | Base SH | 08W | UNSE | Scoping/Scoped | 1.76 | - | - | 1.76 | 1.76 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5168 | -121.4943 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 300
35343396 | Base SH | 08W | UNSE | Scoping/Scoped | 1.08 | - | - | 1.08 | 1.08 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.52 | -121.4943 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 301
35343397 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | - | - | 0.84 | 0.84 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5082 | -121.5038 | WYANDOTTE 11101954 | 1724 | 0.017468 | WYANDOTTE 1110980944 | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 302
35320446 | Base SH | 08W | UNSE | Scoping/Scoped | 0.32 | 10.66 | - | 10.98 | 10.98 | - | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 35.6126 | -120.1756 | BUELLTON 1102Y50 | 269 | 0.22624 | BUELLTON 1102Y50 | 2607 | 0.00026962 | 99% | CWSP - 2023 ICUG | Tier 2 | 303
35286270 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2428 | - | - | 1.2428 | - | 1.2428 | NV | Region 2 - North East | Paradise | BUTTE | 39.7573 | -121.6264 | PARADISE 1103CB | 2257 | 0.0039747 | PARADISE 1103CB | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 304
35144489 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.1733 | - | - | 2.1733 | - | 2.1733 | NV | Region 2 - North East | Magalia | BUTTE | 39.8201 | -121.6017 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 305
35112126 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.1095 | - | - | 2.1095 | - | 2.1095 | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.603 | PARADISE 110636042 | 2933 | 3.0817e-05 | PARADISE 110636042 | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 306
35246595 | Community Rebuild | 08W | ESTS | Estimating | 5.8735 | - | - | 5.8735 | - | 5.8735 | NV | Region 2 - North East | Paradise | BUTTE | 39.7778 | -121.6061 | PARADISE 110636042 | 2933 | 3.0817e-05 | PARADISE 110636042 | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 307
35127360 | Community Rebuild | 95F | UNSE | Scoping/Scoped | 1.3352 | - | - | 1.3352 | - | 1.3352 | NV | Region 2 - North East | Paradise | BUTTE | 39.7463 | -121.6437 | PARADISE 110453544 | 2950 | 2.5314e-05 | PARADISE 110353544 | 875 | 0.0027476 | 99% | Butte Rebuild | Tier 3 | 308
35144487 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4989 | - | - | 2.4989 | - | 2.4989 | NV | Region 2 - North East | Magalia | BUTTE | 39.8181 | -121.5952 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 309
35144488 | Community Rebuild | 95F | ESTS ERDY | Estimating | 3.5227 | - | - | 3.5227 | - | 3.5227 | NV | Region 2 - North East | Magalia | BUTTE | 39.8148 | -121.6065 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 310
35244220 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.5284 | - | - | 2.5284 | - | 2.5284 | NV | Region 2 - North East | Paradise | BUTTE | 39.7553 | -121.6287 | PARADISE 1103CB | 2257 | 0.0039747 | PARADISE 1103CB | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 311
35246594 | Community Rebuild | 08W | UNSE | Estimating | 3.7216 | - | - | 3.7216 | - | 3.7216 | NV | Region 2 - North East | Paradise | BUTTE | 39.741 | -121.6219 | PARADISE 11042486 | 2906 | 4.4268e-05 | PARADISE 11032486 | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 312
35144490 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4928 | - | - | 2.4928 | - | 2.4928 | NV | Region 2 - North East | Magalia | BUTTE | 39.8242 | -121.5995 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 313
35144491 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.7557 | - | - | 2.7557 | - | 2.7557 | NV | Region 2 - North East | Magalia | BUTTE | 39.8259 | -121.5971 | PARADISE 1105829194 | 2849 | 0.00016422 | PARADISE 1105829194 | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 314
35144492 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2159 | - | - | 1.2159 | - | 1.2159 | NV | Region 2 - North East | Magalia | BUTTE | 39.8227 | -121.5947 | PARADISE 1105878870 | 2211 | 0.0048412 | PARADISE 1105878870 | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 315
35246592 | Community Rebuild | 08W | ESTS ERDY | Estimating | 6.2074 | - | - | 6.2074 | - | 6.2074 | NV | Region 2 - North East | Paradise | BUTTE | 39.7412 | -121.6079 | PARADISE 11042034 | 1537 | 0.025842 | PARADISE 11042034 | 362 | 0.0076725 | 99% | Butte Rebuild | Tier 2 | 316
35244027 | Community Rebuild | 08W | ESTS ERDY | Estimating | 5.483 | - | - | 5.483 | - | 5.483 | NV | Region 2 - North East | Paradise | BUTTE | 39.8026 | -121.5798 | PARADISE 11052214 | 2141 | 0.0062243 | PARADISE 11052214 | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 317
35234527 | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | - | - | 0.075947 | - | 0.075947 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | 2010 | 0.0088541 | ALLEGHANY 1101VR816 | 128 | 0.016217 | 99% | PSPS | Tier 3 | 318
35234528 | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | - | - | 0.035985 | - | 0.035985 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | 2010 | 0.0088541 | ALLEGHANY 1101VR816 | 128 | 0.016217 | 99% | PSPS | Tier 3 | 319
35234529 | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | - | - | 0.70833 | - | 0.70833 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | 2010 | 0.0088541 | ALLEGHANY 1101VR816 | 128 | 0.016217 | 99% | PSPS | Tier 3 | 320
35277935 | Base SH | 08W | ESTS | Estimating | 0.092992 | - | - | 0.092992 | - | 0.092992 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0313 | -119.4396 | AUBERRY 1101R2839 | 274 | 0.22501 | AUBERRY 1101R2839 | 614 | 0.0043344 | 99% | CWSP | Tier 2 | 321
35280505 | Other | 30A | ESTS | Estimating | 0.37879 | - | - | 0.37879 | - | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5947 | -122.4862 | Keswick 11019712 | 1614 | 0.022607 | Keswick 11019712 | 43 | 0.023649 | 99% | Other | Tier 3 | 322
35294729 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4089 | - | - | 3.4089 | - | 3.4089 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7479 | PIT NO 3 21011482 | 2320 | 0.0032735 | PIT NO 3 21011482 | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 323
35294730 | Base SH | 08W | UNSE | Scoping/Scoped | 2.8409 | - | - | 2.8409 | - | 2.8409 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9685 | -121.8246 | PIT NO 3 21011482 | 2320 | 0.0032735 | PIT NO 3 21011482 | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 324
35325224 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2799 | 0.05 | - | 3.3299 | - | 3.3299 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 41.0088 | -121.7129 | PIT NO 3 21011482 | 2320 | 0.0032735 | PIT NO 3 21011482 | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 325
35325225 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2449 | - | - | 3.2449 | - | 3.2449 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9729 | -121.7814 | PIT NO 3 21011482 | 2320 | 0.0032735 | PIT NO 3 21011482 | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 326
35325226 | Base SH | 08W | UNSE | Scoping/Scoped | 4.218 | - | - | 4.218 | - | 4.218 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9868 | -121.8481 | PIT NO 3 21011482 | 2320 | 0.0032735 | PIT NO 3 21011482 | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 327
35294728 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4201 | - | - | 2.4201 | - | 2.4201 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7478 | PIT NO 3 2101CB | 1816 | 0.01407 | PIT NO 3 2101CB | 326 | 0.0086689 | 99% | CWSP | Tier 2 | 328
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018365 | - | - | 0.018365 | - | 0.018365 | SI | Region 2 - North East | ALLEGHANY | Nevada | 39.364 | -120.7923 | ALLEGHANY 11021101/2 | 3054 | 1.0723e-05 | ALLEGHANY 11021101/2 | 4 | 0.066078 | 99% | V3 Tranche 1 | Tier 3 | 329
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.7026 | - | - | 21.7026 | - | 21.7026 | SI | Region 2 - North East | ALLEGHANY | Sierra | 39.4655 | -120.8449 | ALLEGHANY 1102CB | 1700 | 0.018204 | ALLEGHANY 1102CB | 41 | 0.023951 | 99% | V3 Tranche 1 | Tier 3 | 330
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4687 | - | - | 11.4687 | - | 11.4687 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8524 | -122.3324 | ANTLER 11011376 | 1674 | 0.019836 | ANTLER 11011376 | 210 | 0.012094 | 99% | V3 Tranche 1 | Tier 2 | 331
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.278 | - | - | 30.278 | - | 30.278 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8489 | -122.3313 | ANTLER 11011378 | 1722 | 0.017574 | ANTLER 11011378 | 247 | 0.010915 | 99% | V3 Tranche 1 | Tier 3 | 332
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.0657 | - | - | 11.0657 | - | 11.0657 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8937 | -122.382 | ANTLER 11011384 | 2361 | 0.0028857 | ANTLER 11011384 | 11 | 0.038738 | 99% | V3 Tranche 1 | Tier 2 | 333
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.1874 | - | - | 11.1874 | - | 11.1874 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8995 | -122.3862 | ANTLER 11011520 | 2407 | 0.002519 | ANTLER 11011520 | 91 | 0.018782 | 99% | V3 Tranche 1 | Tier 2 | 334
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.622 | - | - | 9.622 | - | 9.622 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8916 | -122.3764 | ANTLER 11011612 | 1791 | 0.014748 | ANTLER 11011612 | 143 | 0.015772 | 99% | V3 Tranche 1 | Tier 3 | 335
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9879 | - | - | 1.9879 | - | 1.9879 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8945 | -122.3808 | ANTLER 1101CB | 2207 | 0.0049349 | ANTLER 1101CB | 94 | 0.0187 | 99% | V3 Tranche 1 | Tier 2 | 336
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.4383 | - | - | 34.4383 | - | 34.4383 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7391 | -120.6681 | APPLE HILL 110413512 | 1284 | 0.041392 | APPLE HILL 110413512 | 124 | 0.016427 | 99% | V3 Tranche 1 | Tier 3 | 337
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.021845 | - | - | 0.021845 | - | 0.021845 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7721 | -120.7002 | APPLE HILL 1104814656 | 1657 | 0.020643 | APPLE HILL 1104814656 | 386 | 0.0072633 | 99% | V3 Tranche 1 | Tier 3 | 338
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9275 | - | - | 31.9275 | - | 31.9275 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7652 | -120.7045 | APPLE HILL 110497086 | 1934 | 0.010689 | APPLE HILL 110497086 | 197 | 0.012828 | 99% | V3 Tranche 1 | Tier 3 | 339
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1021 | - | - | 5.1021 | - | 5.1021 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7396 | -120.6772 | APPLE HILL 1104CB | 1422 | 0.032289 | APPLE HILL 1104CB | 30 | 0.025967 | 99% | V3 Tranche 1 | Tier 2 | 340
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.136 | - | - | 15.136 | - | 15.136 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | APPLE HILL 21026552 | 178 | 0.2712 | APPLE HILL 21026552 | 32 | 0.025831 | 99% | V3 Tranche 1 | Tier 3 | 341
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.5084 | - | - | 28.5084 | - | 28.5084 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6607 | APPLE HILL 21027502 | 1505 | 0.027532 | APPLE HILL 21027502 | 63 | 0.020812 | 99% | V3 Tranche 1 | Tier 3 | 342
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 51.0474 | - | - | 51.0474 | - | 51.0474 | SI | Region 2 - North East | Camino | El Dorado | 38.7371 | -120.6759 | APPLE HILL 2102CB | 644 | 0.12006 | APPLE HILL 2102836878 | 132 | 0.01606 | 99% | V3 Tranche 1 | Tier 3 | 343
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.078916 | - | - | 0.078916 | - | 0.078916 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6765 | APPLE HILL 2102CB | 644 | 0.12006 | APPLE HILL 2102CB | 2 | 0.090117 | 99% | V3 Tranche 1 | Tier 2 | 344
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.2757 | - | - | 19.2757 | - | 19.2757 | NV | Region 2 - North East | BERRY CREEK | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | 1288 | 0.040961 | BIG BEND 1102884340 | 267 | 0.010152 | 99% | V3 Tranche 1 | Tier 3 | 345
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.6217 | - | - | 13.6217 | - | 13.6217 | NV | Region 2 - North East | CONCOW | Butte | 39.6773 | -121.4916 | BIG BEND 1102CB | 865 | 0.084888 | BIG BEND 1102CB | 187 | 0.013302 | 99% | V3 Tranche 1 | Tier 3 | 346
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.0546 | - | - | 18.0546 | - | 18.0546 | SI | Region 2 - North East | ALTA | Placer | 39.2148 | -120.8091 | BONNIE NOOK 1101CB | 1526 | 0.026396 | BONNIE NOOK 1101CB | 20 | 0.02949 | 99% | V3 Tranche 1 | Tier 3 | 347
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.5031 | - | - | 42.5031 | - | 42.5031 | SI | Region 2 - North East | ALTA | Placer | 39.2147 | -120.8094 | BONNIE NOOK 1102CB | 2087 | 0.0071702 | BONNIE NOOK 1102CB | 192 | 0.013013 | 99% | V3 Tranche 1 | Tier 3 | 348
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 55.3006 | - | - | 55.3006 | - | 55.3006 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.2129 | -121.0129 | BRUNSWICK 11021010 | 1649 | 0.021168 | BRUNSWICK 11021010 | 234 | 0.011407 | 99% | V3 Tranche 1 | Tier 3 | 349
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.0096 | - | - | 12.0096 | - | 12.0096 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1995 | -121.0171 | BRUNSWICK 11062104 | 2157 | 0.0059169 | BRUNSWICK 11062104 | 429 | 0.0065825 | 99% | V3 Tranche 1 | Tier 3 | 350
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.1704 | - | - | 28.1704 | - | 28.1704 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1909 | -120.9999 | BRUNSWICK 110651484 | 1154 | 0.052211 | BRUNSWICK 110651484 | 266 | 0.010208 | 99% | V3 Tranche 1 | Tier 3 | 351
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 70.6282 | - | - | 70.6282 | - | 70.6282 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1911 | -120.9965 | BRUNSWICK 110651486 | 1788 | 0.014797 | BRUNSWICK 110651486 | 315 | 0.0088799 | 99% | V3 Tranche 1 | Tier 3 | 352
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.2781 | - | - | 33.2781 | - | 33.2781 | NV | Region 2 - North East | STORRIE | Plumas | 39.9109 | -121.3276 | BUCKS CREEK 1102CB | 378 | 0.1873 | BUCKS CREEK 1102CB | 45 | 0.023178 | 99% | V3 Tranche 1 | Tier 3 | 353
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.9616 | - | - | 15.9616 | - | 15.9616 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6088 | -122.591 | CALISTOGA 110189150 | 1093 | 0.057148 | CALISTOGA 1101122350 | 134 | 0.016019 | 99% | V3 Tranche 1 | Tier 3 | 354
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.64 | - | - | 1.64 | - | 1.64 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6222 | -122.679 | CALISTOGA 1101242919 | 565 | 0.14151 | CALISTOGA 1101242919 | 480 | 0.0057895 | 99% | V3 Tranche 1 | Tier 3 | 355
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.636 | - | - | 15.636 | - | 15.636 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5894 | -122.6079 | CALISTOGA 1101734 | 683 | 0.11348 | CALISTOGA 1101257964 | 428 | 0.006597 | 99% | V3 Tranche 1 | Tier 3 | 356
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.5931 | - | - | 3.5931 | - | 3.5931 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6577 | -122.5951 | CALISTOGA 110135588 | 614 | 0.12786 | CALISTOGA 110135588 | 389 | 0.0071797 | 99% | V3 Tranche 1 | Tier 3 | 357
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3819 | - | - | 9.3819 | - | 9.3819 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5953 | -122.6022 | CALISTOGA 110143924 | 1005 | 0.066852 | CALISTOGA 110143924 | 105 | 0.017566 | 99% | V3 Tranche 1 | Tier 3 | 358
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9467 | - | - | 31.9467 | - | 31.9467 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5803 | -122.5979 | CALISTOGA 1101736 | 833 | 0.088841 | CALISTOGA 11015934 | 299 | 0.0094322 | 99% | V3 Tranche 1 | Tier 3 | 359
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.518 | - | - | 4.518 | - | 4.518 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6318 | -122.6741 | CALISTOGA 1101890 | 406 | 0.17857 | CALISTOGA 1101843761 | 589 | 0.0045153 | 99% | V3 Tranche 1 | Tier 3 | 360
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8478 | - | - | 11.8478 | - | 11.8478 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.5599 | -122.6285 | CALISTOGA 1101736 | 833 | 0.088841 | CALISTOGA 1101886282 | 411 | 0.006798 | 99% | V3 Tranche 1 | Tier 3 | 361
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.10844 | - | - | 0.10844 | - | 0.10844 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.592 | -122.5786 | CALISTOGA 1101CB | 55 | 0.40561 | CALISTOGA 1101CB | 1636 | 0.00082073 | 99% | V3 Tranche 1 | Tier 2 | 362
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.8011 | - | - | 5.8011 | - | 5.8011 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5637 | -122.5595 | CALISTOGA 1102634 | 1477 | 0.029373 | CALISTOGA 1102131531 | 24 | 0.027222 | 99% | V3 Tranche 1 | Tier 3 | 363
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.052643 | - | - | 0.052643 | - | 0.052643 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5686 | -122.5417 | CALISTOGA 1102141073 | 1014 | 0.065722 | CALISTOGA 1102141073 | 78 | 0.019531 | 99% | V3 Tranche 1 | Tier 3 | 364
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.1129 | - | - | 0.1129 | - | 0.1129 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5762 | -122.5825 | CALISTOGA 1102705 | 2828 | 0.00021298 | CALISTOGA 1102177784 | 382 | 0.0073271 | 99% | V3 Tranche 1 | Tier 2 | 365
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7313 | - | - | 0.7313 | - | 0.7313 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5787 | -122.5826 | CALISTOGA 1102184814 | 3098 | 8.707e-06 | CALISTOGA 1102184814 | 843 | 0.0029014 | 99% | V3 Tranche 1 | Tier 3 | 366
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9317 | - | - | 6.9317 | - | 6.9317 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5859 | -122.5714 | CALISTOGA 1102634 | 1477 | 0.029373 | CALISTOGA 1102634 | 769 | 0.0032407 | 99% | V3 Tranche 1 | Tier 3 | 367
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.0843 | - | - | 7.0843 | - | 7.0843 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5678 | -122.5383 | CALISTOGA 1102769230 | 1624 | 0.022338 | CALISTOGA 1102769230 | 534 | 0.0050695 | 99% | V3 Tranche 1 | Tier 3 | 368
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018445 | - | - | 0.018445 | - | 0.018445 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8059 | -122.8081 | CALPINE 1144276-G | 2 | 1.8786 | CALPINE 1144276-G | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 369
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.057948 | - | - | 0.057948 | - | 0.057948 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7727 | -122.7295 | CALPINE 1144304 | 2308 | 0.0033555 | CALPINE 1144304 | 3 | 0.068443 | 99% | V3 Tranche 1 | Tier 3 | 370
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.0767 | - | - | 5.0767 | - | 5.0767 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7658 | -122.7076 | CALPINE 1144962 | 1049 | 0.061428 | CALPINE 1144960 | 238 | 0.011276 | 99% | V3 Tranche 1 | Tier 3 | 371
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3133 | - | - | 33.3133 | - | 33.3133 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8154 | -122.8003 | CALPINE 1144CB | 334 | 0.19817 | CALPINE 1144CB | 169 | 0.014299 | 99% | V3 Tranche 1 | Tier 3 | 372
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.010654 | - | - | 0.010654 | - | 0.010654 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8266 | -122.7997 | CALPINE 1146200-G | 31 | 0.50979 | CALPINE 1146200-G | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 373
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.014112 | - | - | 0.014112 | - | 0.014112 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8264 | -122.7997 | CALPINE 1146394G | 32 | 0.50979 | CALPINE 1146394G | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 374
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.3029 | - | - | 2.3029 | - | 2.3029 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8265 | -122.8041 | CALPINE 1146400 | 97 | 0.34896 | CALPINE 1146400 | 543 | 0.0049805 | 99% | V3 Tranche 1 | Tier 3 | 375
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.6798 | - | - | 4.6798 | - | 4.6798 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.815 | -122.8021 | CALPINE 1146CB | 297 | 0.21399 | CALPINE 1146CB | 79 | 0.019348 | 99% | V3 Tranche 1 | Tier 3 | 376
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.58901 | - | - | 0.58901 | - | 0.58901 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9412 | -121.9576 | CLAYTON 2212158138 | 1321 | 0.038704 | CLAYTON 2212158138 | 471 | 0.0058873 | 99% | V3 Tranche 1 | Tier 2 | 377
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.7558 | - | - | 14.7558 | - | 14.7558 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.8797 | -121.8678 | CLAYTON 221296224 | 377 | 0.18755 | CLAYTON 2212204416 | 223 | 0.011731 | 99% | V3 Tranche 1 | Tier 3 | 378
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.79978 | - | - | 0.79978 | - | 0.79978 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9332 | -121.9419 | CLAYTON 2212CB | 2561 | 0.0014894 | CLAYTON 2212614950 | 100 | 0.018211 | 99% | V3 Tranche 1 | Tier 3 | 379
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3146 | - | - | 33.3146 | - | 33.3146 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9245 | -121.9125 | CLAYTON 2212CB | 2561 | 0.0014894 | CLAYTON 2212681608 | 115 | 0.016899 | 99% | V3 Tranche 1 | Tier 3 | 380
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.6045 | - | - | 9.6045 | - | 9.6045 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9039 | -121.8741 | CLAYTON 221296224 | 377 | 0.18755 | CLAYTON 221296224 | 15 | 0.034099 | 99% | V3 Tranche 1 | Tier 3 | 381
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.37986 | - | - | 0.37986 | - | 0.37986 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9439 | -121.9691 | CLAYTON 2212CB | 2561 | 0.0014894 | CLAYTON 2212CB | 1654 | 0.00080781 | 99% | V3 Tranche 1 | Tier 2 | 382
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6612 | - | - | 3.6612 | - | 3.6612 | HB | Region 1 - North Coast | LAKEPORT | Lake | 39.0183 | -122.917 | CLEAR LAKE 1102904 | 239 | 0.23862 | CLEAR LAKE 1102904 | 200 | 0.012549 | 99% | V3 Tranche 1 | Tier 2 | 383
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.052 | - | - | 17.052 | - | 17.052 | NV | Region 2 - North East | CORNING | Tehama | 39.9967 | -122.4058 | CORNING 110164090 | 549 | 0.1444 | CORNING 110164090 | 615 | 0.0043341 | 99% | V3 Tranche 1 | Tier 2 | 384
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.8387 | - | - | 28.8387 | - | 28.8387 | NV | Region 2 - North East | CORNING | Tehama | 40.0157 | -122.4005 | CORNING 110185152 | 986 | 0.068983 | CORNING 110185152 | 194 | 0.012991 | 99% | V3 Tranche 1 | Tier 2 | 385
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.96092 | - | - | 0.96092 | - | 0.96092 | NV | Region 2 - North East | OROVILLE | Butte | 39.8269 | -121.4092 | CRESTA 1101103126 | 2890 | 6.9083e-05 | CRESTA 1101103126 | 40 | 0.023964 | 99% | V3 Tranche 1 | Tier 3 | 386
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.54712 | - | - | 0.54712 | - | 0.54712 | NV | Region 2 - North East | OROVILLE | Butte | 39.8308 | -121.4091 | CRESTA 1101546650 | 33 | 0.50291 | CRESTA 1101546650 | 31 | 0.025946 | 99% | V3 Tranche 1 | Tier 3 | 387
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.7057 | - | - | 2.7057 | - | 2.7057 | SI | Region 2 - North East | ALTA | Placer | 39.2564 | -120.7671 | DRUM 1101CB | 942 | 0.074456 | DRUM 1101CB | 103 | 0.018102 | 99% | V3 Tranche 1 | Tier 3 | 388
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8641 | - | - | 11.8641 | - | 11.8641 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7617 | -120.5776 | EL DORADO PH 210219542 | 2512 | 0.0017374 | EL DORADO PH 210219542 | 176 | 0.013848 | 99% | V3 Tranche 1 | Tier 3 | 389
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.31289 | - | - | 0.31289 | - | 0.31289 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7602 | -120.5769 | EL DORADO PH 210219562 | 3014 | 1.4503e-05 | EL DORADO PH 210219562 | 195 | 0.012963 | 99% | V3 Tranche 1 | Tier 3 | 390
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.077102 | - | - | 0.077102 | - | 0.077102 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7539 | -120.5747 | EL DORADO PH 2102542272 | 2000 | 0.0090446 | EL DORADO PH 2102542272 | 121 | 0.016629 | 99% | V3 Tranche 1 | Tier 3 | 391
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.9464 | - | - | 3.9464 | - | 3.9464 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7649 | -120.5894 | EL DORADO PH 21026645 | 2469 | 0.0020868 | EL DORADO PH 21026645 | 780 | 0.0031904 | 99% | V3 Tranche 1 | Tier 3 | 392
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.8959 | - | - | 6.8959 | - | 6.8959 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7935 | -120.6192 | EL DORADO PH 2102CB | 2732 | 0.00051722 | EL DORADO PH 2102CB | 278 | 0.0099516 | 99% | V3 Tranche 1 | Tier 3 | 393
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.2319 | - | - | 6.2319 | - | 6.2319 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3604 | -120.7525 | ELECTRA 110136816 | 1720 | 0.017625 | ELECTRA 110136816 | 288 | 0.0096899 | 99% | V3 Tranche 1 | Tier 2 | 394
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3872 | - | - | 29.3872 | - | 29.3872 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3633 | -120.6486 | ELECTRA 110161816 | 1571 | 0.0243 | ELECTRA 110161816 | 355 | 0.0078671 | 99% | V3 Tranche 1 | Tier 2 | 395
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.0949 | - | - | 15.0949 | - | 15.0949 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3639 | -120.6467 | ELECTRA 11017104 | 1548 | 0.025302 | ELECTRA 11017104 | 62 | 0.020861 | 99% | V3 Tranche 1 | Tier 2 | 396
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.1029 | - | - | 29.1029 | - | 29.1029 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3314 | -120.6731 | ELECTRA 1101CB | 1088 | 0.05741 | ELECTRA 1101CB | 251 | 0.010795 | 99% | V3 Tranche 1 | Tier 2 | 397
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.211 | - | - | 7.211 | - | 7.211 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3793 | -120.638 | ELECTRA 1101L1697 | 2349 | 0.0030208 | ELECTRA 1101L1697 | 118 | 0.016781 | 99% | V3 Tranche 1 | Tier 2 | 398
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7233 | - | - | 27.7233 | - | 27.7233 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0162 | -120.8351 | FORESTHILL 11011802 | 1865 | 0.012496 | FORESTHILL 11011802 | 179 | 0.013637 | 99% | V3 Tranche 1 | Tier 3 | 399
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.4919 | - | - | 14.4919 | - | 14.4919 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0474 | -120.7852 | FORESTHILL 110137238 | 1434 | 0.031693 | FORESTHILL 110137238 | 322 | 0.0088134 | 99% | V3 Tranche 1 | Tier 3 | 400
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.6369 | - | - | 14.6369 | - | 14.6369 | SI | Region 2 - North East | FORESTHILL | Placer | 38.9929 | -120.8827 | FORESTHILL 110150486 | 2270 | 0.0037623 | FORESTHILL 110150486 | 114 | 0.01695 | 99% | V3 Tranche 1 | Tier 3 | 401
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.3473 | - | - | 11.3473 | - | 11.3473 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0193 | -120.8302 | FORESTHILL 1101CB | 2058 | 0.0077431 | FORESTHILL 1101CB | 232 | 0.011424 | 99% | V3 Tranche 1 | Tier 3 | 402
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.8558 | - | - | 34.8558 | - | 34.8558 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0198 | -120.8509 | FORESTHILL 11022106 | 1301 | 0.040196 | FORESTHILL 11022106 | 97 | 0.018495 | 99% | V3 Tranche 1 | Tier 3 | 403
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.25572 | - | - | 0.25572 | - | 0.25572 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.7004 | -122.9575 | GEYSERVILLE 1101482 | 2170 | 0.0056711 | GEYSERVILLE 1101482 | 1375 | 0.0011879 | 99% | V3 Tranche 1 | Tier 2 | 404
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.037341 | - | - | 0.037341 | - | 0.037341 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.937 | -122.609 | HIGHLANDS 1101CB | 3186 | 6.536e-06 | HIGHLANDS 1101CB | 163 | 0.014683 | 99% | V3 Tranche 1 | Tier 2 | 405
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.7877 | - | - | 17.7877 | - | 17.7877 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | 27 | 0.5487 | HIGHLANDS 1102628 | 29 | 0.026126 | 99% | V3 Tranche 1 | Tier 3 | 406
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.6035 | - | - | 7.6035 | - | 7.6035 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8802 | -122.6125 | HIGHLANDS 11031282 | 626 | 0.12376 | HIGHLANDS 11031282 | 582 | 0.0045905 | 99% | V3 Tranche 1 | Tier 2 | 407
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.1732 | - | - | 21.1732 | - | 21.1732 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8967 | -122.5542 | HIGHLANDS 1103482 | 181 | 0.26975 | HIGHLANDS 1103287766 | 156 | 0.015099 | 99% | V3 Tranche 1 | Tier 2 | 408
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.8369 | - | - | 9.8369 | - | 9.8369 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8705 | -122.6229 | HIGHLANDS 11031282 | 626 | 0.12376 | HIGHLANDS 1103726580 | 144 | 0.015697 | 99% | V3 Tranche 1 | Tier 2 | 409
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.0855 | - | - | 9.0855 | - | 9.0855 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.9079 | -122.5968 | HIGHLANDS 1103CB | 461 | 0.16238 | HIGHLANDS 1103917328 | 270 | 0.010079 | 99% | V3 Tranche 1 | Tier 2 | 410
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.29571 | - | - | 0.29571 | - | 0.29571 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.677 | -119.7768 | INDIAN FLAT 11044440 | 16 | 0.68656 | INDIAN FLAT 11044440 | 12 | 0.038638 | 99% | V3 Tranche 1 | Tier 2 | 411
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.8871 | - | - | 19.8871 | - | 19.8871 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.6649 | -119.8411 | INDIAN FLAT 1104CB | 555 | 0.14347 | INDIAN FLAT 1104CB | 10 | 0.039297 | 99% | V3 Tranche 1 | Tier 2 | 412
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3548 | - | - | 9.3548 | - | 9.3548 | SA | Region 2 - North East | GREEN VALLEY | Solano | 38.2496 | -122.1606 | JAMESON 110265516 | 739 | 0.104 | JAMESON 110265516 | 313 | 0.0089196 | 99% | V3 Tranche 1 | Tier 2 | 413
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.8683 | - | - | 2.8683 | - | 2.8683 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.3482 | -121.3219 | LOS COCHES 1101625902 | 2006 | 0.0089147 | LOS COCHES 1101625902 | 462 | 0.0060529 | 99% | V3 Tranche 1 | Tier 2 | 414
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.4274 | - | - | 37.4274 | - | 37.4274 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2804 | -121.3064 | LOS OSITOS 21033010 | 1509 | 0.027281 | LOS OSITOS 21033010 | 178 | 0.013726 | 99% | V3 Tranche 1 | Tier 2 | 415
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 38.1684 | - | - | 38.1684 | - | 38.1684 | CC | Region 4 - Central Coast | BITTERWATER | San Benito | 36.3875 | -121.0045 | LOS OSITOS 21037014 | N/A (HFRA, not in v2) | - | LOS OSITOS 21037014 | 193 | 0.012994 | 99% | V3 Tranche 1 | HFRA | 416
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.182 | - | - | 15.182 | - | 15.182 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2789 | -121.3033 | LOS OSITOS 21037062 | 1359 | 0.035805 | LOS OSITOS 21037062 | 516 | 0.0052285 | 99% | V3 Tranche 1 | Tier 2 | 417
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.6522 | - | - | 24.6522 | - | 24.6522 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5251 | -119.9181 | MARIPOSA 210110240 | 679 | 0.11431 | MARIPOSA 210110240 | 126 | 0.016323 | 99% | V3 Tranche 1 | Tier 3 | 418
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.4258 | - | - | 23.4258 | - | 23.4258 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5697 | -119.942 | MARIPOSA 2101752630 | 700 | 0.11205 | MARIPOSA 2101752630 | 199 | 0.012689 | 99% | V3 Tranche 1 | Tier 3 | 419
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.13992 | - | - | 0.13992 | - | 0.13992 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4872 | -119.9618 | MARIPOSA 2102241564 | 10 | 0.77248 | MARIPOSA 2102241564 | 515 | 0.0052627 | 99% | V3 Tranche 1 | Tier 2 | 420
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.070448 | - | - | 0.070448 | - | 0.070448 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4632 | -119.9482 | MARIPOSA 2102527766 | 3264 | 5.0408e-06 | MARIPOSA 2102527766 | 464 | 0.0059574 | 99% | V3 Tranche 1 | Tier 2 | 421
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65665 | - | - | 0.65665 | - | 0.65665 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4861 | -119.9697 | MARIPOSA 2102594143 | 587 | 0.13461 | MARIPOSA 2102594143 | 312 | 0.0089197 | 99% | V3 Tranche 1 | Tier 2 | 422
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0221 | - | - | 1.0221 | - | 1.0221 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.5044 | -120.0079 | MARIPOSA 2102CB | 35 | 0.47165 | MARIPOSA 2102CB | 77 | 0.019783 | 99% | V3 Tranche 1 | Tier 2 | 423
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76835 | - | - | 0.76835 | - | 0.76835 | HB | Region 1 - North Coast | COBB | Lake | 38.8237 | -122.7214 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101128648 | 258 | 0.010457 | 99% | V3 Tranche 1 | Tier 3 | 424
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.1567 | - | - | 1.1567 | - | 1.1567 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7312 | -122.6235 | MIDDLETOWN 11011314 | 915 | 0.078235 | MIDDLETOWN 11011314 | 56 | 0.021686 | 99% | V3 Tranche 1 | Tier 3 | 425
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3963 | - | - | 4.3963 | - | 4.3963 | HB | Region 1 - North Coast | COBB | Lake | 38.8481 | -122.7562 | MIDDLETOWN 11014646 | 328 | 0.19983 | MIDDLETOWN 1101171414 | 38 | 0.024501 | 99% | V3 Tranche 1 | Tier 3 | 426
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.6615 | - | - | 2.6615 | - | 2.6615 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.695 | -122.5975 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 1101352182 | 175 | 0.013904 | 99% | V3 Tranche 1 | Tier 3 | 427
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3985 | - | - | 1.3985 | - | 1.3985 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7253 | -122.619 | MIDDLETOWN 1101644756 | 314 | 0.20636 | MIDDLETOWN 1101433160 | 99 | 0.018456 | 99% | V3 Tranche 1 | Tier 3 | 428
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.4605 | - | - | 1.4605 | - | 1.4605 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7522 | -122.6207 | MIDDLETOWN 1101439572 | 450 | 0.16479 | MIDDLETOWN 1101439572 | 174 | 0.013914 | 99% | V3 Tranche 1 | Tier 2 | 429
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.4241 | - | - | 26.4241 | - | 26.4241 | HB | Region 1 - North Coast | COBB | Lake | 38.8291 | -122.7295 | MIDDLETOWN 11014646 | 328 | 0.19983 | MIDDLETOWN 11014646 | 182 | 0.013549 | 99% | V3 Tranche 1 | Tier 3 | 430
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0487 | - | - | 1.0487 | - | 1.0487 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7628 | -122.6133 | MIDDLETOWN 1101481876 | 38 | 0.46769 | MIDDLETOWN 1101481876 | 673 | 0.0038943 | 99% | V3 Tranche 1 | Tier 3 | 431
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.9927 | - | - | 10.9927 | - | 10.9927 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | 468 | 0.1603 | MIDDLETOWN 110148212 | 13 | 0.035184 | 99% | V3 Tranche 1 | Tier 3 | 432
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.0007 | - | - | 26.0007 | - | 26.0007 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 474 | 0.15935 | MIDDLETOWN 1101548 | 102 | 0.018129 | 99% | V3 Tranche 1 | Tier 3 | 433
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.707 | - | - | 1.707 | - | 1.707 | HB | Region 1 - North Coast | COBB | Lake | 38.8266 | -122.727 | MIDDLETOWN 1101614 | 2060 | 0.0076984 | MIDDLETOWN 1101614 | 211 | 0.01209 | 99% | V3 Tranche 1 | Tier 3 | 434
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5662 | - | - | 18.5662 | - | 18.5662 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7462 | -122.6206 | MIDDLETOWN 1101644756 | 314 | 0.20636 | MIDDLETOWN 1101644756 | 185 | 0.013349 | 99% | V3 Tranche 1 | Tier 3 | 435
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9629 | - | - | 1.9629 | - | 1.9629 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7537 | -122.6111 | MIDDLETOWN 1101CB | 86 | 0.36174 | MIDDLETOWN 1101829164 | 935 | 0.002498 | 99% | V3 Tranche 1 | Tier 3 | 436
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65224 | - | - | 0.65224 | - | 0.65224 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7523 | -122.6178 | MIDDLETOWN 1101932140 | 3073 | 9.669e-06 | MIDDLETOWN 1101932140 | 146 | 0.015654 | 99% | V3 Tranche 1 | Tier 2 | 437
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3099 | - | - | 4.3099 | - | 4.3099 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7722 | -122.6244 | MIDDLETOWN 1101CB | 86 | 0.36174 | MIDDLETOWN 1101959140 | 160 | 0.014882 | 99% | V3 Tranche 1 | Tier 3 | 438
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.995 | - | - | 13.995 | - | 13.995 | SI | Region 2 - North East | GEOGETOWN | El Dorado | 38.8995 | -120.8545 | MOUNTAIN QUARRIES 21011184 | 2212 | 0.0048403 | MOUNTAIN QUARRIES 21011184 | 275 | 0.009997 | 99% | V3 Tranche 1 | Tier 3 | 439
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.104 | - | - | 27.104 | - | 27.104 | SI | Region 2 - North East | COOL | El Dorado | 38.8932 | -120.9965 | MOUNTAIN QUARRIES 21011350 | 169 | 0.27537 | MOUNTAIN QUARRIES 21011350 | 401 | 0.0069368 | 99% | V3 Tranche 1 | Tier 2 | 440
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6797 | - | - | 10.6797 | - | 10.6797 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.9 | -120.9074 | MOUNTAIN QUARRIES 21012422 | 1706 | 0.018043 | MOUNTAIN QUARRIES 21012422 | 165 | 0.014598 | 99% | V3 Tranche 1 | Tier 2 | 441
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.3111 | - | - | 18.3111 | - | 18.3111 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.8958 | -120.879 | MOUNTAIN QUARRIES 210192474 | 1212 | 0.046937 | MOUNTAIN QUARRIES 210192474 | 177 | 0.013764 | 99% | V3 Tranche 1 | Tier 3 | 442
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6043 | - | - | 10.6043 | - | 10.6043 | NV | Region 2 - North East | CHICO | Butte | 39.7784 | -121.7318 | NOTRE DAME 11042408 | 73 | 0.37815 | NOTRE DAME 1104176446 | 155 | 0.015172 | 99% | V3 Tranche 1 | Tier 3 | 443
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5667 | - | - | 13.5667 | - | 13.5667 | NV | Region 2 - North East | FOREST RANCH | Butte | 39.839 | -121.7019 | NOTRE DAME 11042028 | 1043 | 0.062015 | NOTRE DAME 11042028 | 37 | 0.024521 | 99% | V3 Tranche 1 | Tier 3 | 444
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.8427 | - | - | 3.8427 | - | 3.8427 | NV | Region 2 - North East | CHICO | Butte | 39.7393 | -121.7854 | NOTRE DAME 11042408 | 73 | 0.37815 | NOTRE DAME 11042408 | 926 | 0.0025265 | 99% | V3 Tranche 1 | Tier 2 | 445
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.098 | - | - | 6.098 | - | 6.098 | NV | Region 2 - North East | CHICO | Butte | 39.7911 | -121.7217 | NOTRE DAME 11042537 | 1045 | 0.061762 | NOTRE DAME 11042537 | 290 | 0.0096296 | 99% | V3 Tranche 1 | Tier 3 | 446
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.7141 | - | - | 30.7141 | - | 30.7141 | YO | Region 5 - Central Valley | AHWAHNEE | Madera | 37.3399 | -119.6754 | OAKHURST 11015490 | 541 | 0.14657 | OAKHURST 11015490 | 172 | 0.014056 | 99% | V3 Tranche 1 | Tier 2 | 447
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.15233 | - | - | 0.15233 | - | 0.15233 | YO | Region 5 - Central Valley | OAKHURST | Madera | 37.3219 | -119.6344 | OAKHURST 1101CB | 847 | 0.086583 | OAKHURST 1101CB | 1208 | 0.0016106 | 99% | V3 Tranche 1 | Tier 3 | 448
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.4642 | - | - | 16.4642 | - | 16.4642 | NV | Region 2 - North East | SHASTA LAKE | Shasta | 40.6653 | -122.3866 | OREGON TRAIL 11021584 | 1773 | 0.015387 | OREGON TRAIL 11021584 | 64 | 0.0208 | 99% | V3 Tranche 1 | Tier 2 | 449
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1749 | - | - | 20.1749 | - | 20.1749 | NV | Region 2 - North East | MAGALIA | Butte | 39.8542 | -121.6058 | ORO FINO 11012022 | 2420 | 0.0024209 | ORO FINO 11012022 | 657 | 0.003959 | 99% | V3 Tranche 1 | Tier 3 | 450
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.3261 | - | - | 20.3261 | - | 20.3261 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 | ORO FINO 1101CB | 2289 | 0.0035789 | ORO FINO 1101CB | 158 | 0.015008 | 99% | V3 Tranche 1 | Tier 3 | 451
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5511 | - | - | 18.5511 | - | 18.5511 | NV | Region 2 - North East | MAGALIA | Butte | 39.8582 | -121.6134 | ORO FINO 11022090 | 2440 | 0.0022675 | ORO FINO 11022090 | 150 | 0.015441 | 99% | V3 Tranche 1 | Tier 3 | 452
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.1705 | - | - | 3.1705 | - | 3.1705 | NV | Region 2 - North East | MAGALIA | Butte | 39.872 | -121.612 | ORO FINO 11022236 | 1287 | 0.040994 | ORO FINO 11022236 | 129 | 0.016201 | 99% | V3 Tranche 1 | Tier 3 | 453
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.3248 | - | - | 8.3248 | - | 8.3248 | NV | Region 2 - North East | MAGALIA | Butte | 39.8901 | -121.5778 | ORO FINO 11022556 | 1441 | 0.031032 | ORO FINO 11022556 | 181 | 0.013572 | 99% | V3 Tranche 1 | Tier 3 | 454
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.8784 | - | - | 52.8784 | - | 52.8784 | NV | Region 2 - North East | MAGALIA | Butte | 39.8872 | -121.6653 | ORO FINO 110239154 | 2575 | 0.0013923 | ORO FINO 110239154 | 273 | 0.010009 | 99% | V3 Tranche 1 | Tier 3 | 455
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.8338 | - | - | 13.8338 | - | 13.8338 | NV | Region 2 - North East | MAGALIA | Butte | 39.8705 | -121.6503 | ORO FINO 110265932 | 1667 | 0.020219 | ORO FINO 110265932 | 140 | 0.015891 | 99% | V3 Tranche 1 | Tier 3 | 456
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1864 | - | - | 20.1864 | - | 20.1864 | NV | Region 2 - North East | MAGALIA | Butte | 39.8877 | -121.6654 | ORO FINO 110276008 | 2763 | 0.000401 | ORO FINO 110276008 | 61 | 0.020869 | 99% | V3 Tranche 1 | Tier 3 | 457
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.714 | - | - | 2.714 | - | 2.714 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 | ORO FINO 1102CB | 2451 | 0.0021922 | ORO FINO 1102CB | 17 | 0.031702 | 99% | V3 Tranche 1 | Tier 3 | 458
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9289 | - | - | 1.9289 | - | 1.9289 | NV | Region 2 - North East | PARADISE | Butte | 39.7704 | -121.6138 | PARADISE 11061212 | 2910 | 4.2503e-05 | PARADISE 11061212 | 26 | 0.026975 | 99% | V3 Tranche 1 | Tier 3 | 459
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.3679 | - | - | 7.3679 | - | 7.3679 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4553 | -121.053 | PIKE CITY 11011720 | 1710 | 0.017864 | PIKE CITY 11011720 | 52 | 0.02211 | 99% | V3 Tranche 1 | Tier 3 | 460
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.588 | - | - | 10.588 | - | 10.588 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4519 | -121.0542 | PIKE CITY 11011730 | 1400 | 0.033438 | PIKE CITY 11011730 | 301 | 0.0093855 | 99% | V3 Tranche 1 | Tier 3 | 461
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.605 | - | - | 24.605 | - | 24.605 | SI | Region 2 - North East | NORTH SAN JUAN | Sierra | 39.4381 | -120.9961 | PIKE CITY 1101CB | 1484 | 0.029034 | PIKE CITY 1101CB | 116 | 0.016874 | 99% | V3 Tranche 1 | Tier 3 | 462
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.2062 | - | - | 5.2062 | - | 5.2062 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.414 | -120.6754 | PINE GROVE 11011021 | 2455 | 0.0021716 | PINE GROVE 11011021 | 310 | 0.0089413 | 99% | V3 Tranche 1 | Tier 2 | 463
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.187 | - | - | 15.187 | - | 15.187 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4069 | -120.6707 | PINE GROVE 11013166 | 1764 | 0.015763 | PINE GROVE 11013166 | 147 | 0.015597 | 99% | V3 Tranche 1 | Tier 2 | 464
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 49.4644 | - | - | 49.4644 | - | 49.4644 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4151 | -120.6853 | PINE GROVE 11013170 | 1768 | 0.015534 | PINE GROVE 11013170 | 410 | 0.0068091 | 99% | V3 Tranche 1 | Tier 2 | 465
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4439 | - | - | 11.4439 | - | 11.4439 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3852 | -120.6921 | PINE GROVE 110194936 | 1943 | 0.010365 | PINE GROVE 110194936 | 240 | 0.011105 | 99% | V3 Tranche 1 | Tier 2 | 466
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.3432 | - | - | 5.3432 | - | 5.3432 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 | PINE GROVE 1101CB | 2334 | 0.0031502 | PINE GROVE 1101CB | 6 | 0.047261 | 99% | V3 Tranche 1 | Tier 2 | 467
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.6574 | - | - | 20.6574 | - | 20.6574 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4739 | -120.6268 | PINE GROVE 110213438 | 2136 | 0.0063999 | PINE GROVE 110213438 | 204 | 0.012447 | 99% | V3 Tranche 1 | Tier 3 | 468
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.38 | - | - | 37.38 | - | 37.38 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4143 | -120.6541 | PINE GROVE 11023168 | 1602 | 0.023045 | PINE GROVE 11023168 | 303 | 0.0092748 | 99% | V3 Tranche 1 | Tier 3 | 469
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.82 | - | - | 11.82 | - | 11.82 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4102 | -120.6518 | PINE GROVE 11023172 | 1592 | 0.023346 | PINE GROVE 11023172 | 139 | 0.015893 | 99% | V3 Tranche 1 | Tier 3 | 470
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.4813 | - | - | 13.4813 | - | 13.4813 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4535 | -120.5298 | PINE GROVE 110245292 | 2447 | 0.002235 | PINE GROVE 110245292 | 233 | 0.011408 | 99% | V3 Tranche 1 | Tier 3 | 471
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.9356 | - | - | 42.9356 | - | 42.9356 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4612 | -120.6579 | PINE GROVE 11026080 | 1271 | 0.042249 | PINE GROVE 11026080 | 131 | 0.016072 | 99% | V3 Tranche 1 | Tier 2 | 472
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5197 | - | - | 13.5197 | - | 13.5197 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 | PINE GROVE 1102CB | 1920 | 0.010952 | PINE GROVE 1102CB | 161 | 0.014761 | 99% | V3 Tranche 1 | Tier 3 | 473
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.1028 | - | - | 16.1028 | - | 16.1028 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7219 | -120.7904 | PLACERVILLE 111219712 | 2135 | 0.0064118 | PLACERVILLE 111219712 | 148 | 0.015591 | 99% | V3 Tranche 1 | Tier 2 | 474
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.9958 | - | - | 52.9958 | - | 52.9958 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7716 | -120.8148 | PLACERVILLE 210611132 | 1666 | 0.020262 | PLACERVILLE 210611132 | 68 | 0.020612 | 99% | V3 Tranche 1 | Tier 3 | 475
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.066273 | - | - | 0.066273 | - | 0.066273 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7719 | -120.8138 | PLACERVILLE 2106CB | 1168 | 0.050873 | PLACERVILLE 210658118 | 1 | 0.10471 | 99% | V3 Tranche 1 | Tier 3 | 476
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 25.9329 | - | - | 25.9329 | - | 25.9329 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | PLACERVILLE 2106935216 | 904 | 0.079474 | PLACERVILLE 2106935216 | 58 | 0.021398 | 99% | V3 Tranche 1 | Tier 3 | 477
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.8769 | - | - | 30.8769 | - | 30.8769 | SI | Region 2 - North East | SPANISH FLAT | El Dorado | 38.8328 | -120.8176 | PLACERVILLE 21069712 | 1646 | 0.021241 | PLACERVILLE 21069712 | 236 | 0.011373 | 99% | V3 Tranche 1 | Tier 3 | 478
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7465 | - | - | 7.7465 | - | 7.7465 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7308 | -120.7838 | PLACERVILLE 2106CB | 1168 | 0.050873 | PLACERVILLE 2106CB | 230 | 0.011469 | 99% | V3 Tranche 1 | Tier 3 | 479
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.2953 | - | - | 2.2953 | - | 2.2953 | NB | Region 1 - North Coast | ENCHANTED HILLS | Napa | 38.397 | -122.4504 | PUEBLO 2103678 | 1224 | 0.046077 | PUEBLO 2103355186 | 264 | 0.010245 | 99% | V3 Tranche 1 | Tier 3 | 480
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 41.2147 | - | - | 41.2147 | - | 41.2147 | NB | Region 1 - North Coast | NAPA | Napa | 38.3155 | -122.3422 | PUEBLO 2103678 | 1224 | 0.046077 | PUEBLO 2103678 | 255 | 0.010549 | 99% | V3 Tranche 1 | Tier 3 | 481
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3813 | - | - | 9.3813 | - | 9.3813 | NB | Region 1 - North Coast | NAPA | Napa | 38.3469 | -122.3299 | PUEBLO 2103895784 | 1630 | 0.022046 | PUEBLO 210378504 | 1000 | 0.0022679 | 99% | V3 Tranche 1 | Tier 3 | 482
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.7002 | - | - | 24.7002 | - | 24.7002 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0662 | -122.611 | REDBUD 1101323962 | 423 | 0.17389 | REDBUD 1101323962 | 127 | 0.016255 | 99% | V3 Tranche 1 | Tier 3 | 483
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9186 | - | - | 6.9186 | - | 6.9186 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0836 | -122.6599 | REDBUD 1101454 | 312 | 0.20738 | REDBUD 1101454 | 44 | 0.023647 | 99% | V3 Tranche 1 | Tier 3 | 484
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4951 | - | - | 5.4951 | - | 5.4951 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0231 | -122.678 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101708166 | 679 | 0.0038601 | 99% | V3 Tranche 1 | Tier 3 | 485
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1996 | - | - | 5.1996 | - | 5.1996 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0581 | -122.693 | REDBUD 1101708166 | 345 | 0.19539 | REDBUD 1101754544 | 375 | 0.007396 | 99% | V3 Tranche 1 | Tier 3 | 486
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.0551 | - | - | 4.0551 | - | 4.0551 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0275 | -122.6625 | REDBUD 1101CB | 2343 | 0.0030523 | REDBUD 1101CB | 395 | 0.0070846 | 99% | V3 Tranche 1 | Tier 2 | 487
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.5016 | - | - | 6.5016 | - | 6.5016 | ST | Region 5 - Central Valley | DORRINGTON | Calaveras | 38.323 | -120.2534 | SALT SPRINGS 210297924 | 2620 | 0.0010653 | SALT SPRINGS 210297924 | 133 | 0.016045 | 99% | V3 Tranche 1 | Tier 3 | 488
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6822e-05 | - | - | 3.6822e-05 | - | 3.6822e-05 | NB | Region 1 - North Coast | SAN RAFAEL | Marin | 37.9807 | -122.5155 | SAN RAFAEL 1109535284 | 3129 | 7.8608e-06 | SAN RAFAEL 1109535284 | 5066 | 4.4996e-05 | 99% | V3 Tranche 1 | Tier 2 | 489
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | MI | Region 3 - Bay Area | DUBLIN | Alameda | 37.7029 | -121.9121 | SAN RAMON 2103MR279 | 3206 | 6.0521e-06 | SAN RAMON 2103MR279 | 1337 | 0.0012585 | 99% | V3 Tranche 1 | Tier 3 | 490
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.5259 | - | - | 7.5259 | - | 7.5259 | SI | Region 2 - North East | COLFAX | Placer | 39.103 | -120.9601 | SHADY GLEN 11012768 | 1885 | 0.011963 | SHADY GLEN 11012768 | 120 | 0.016673 | 99% | V3 Tranche 1 | Tier 3 | 491
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.5495 | - | - | 14.5495 | - | 14.5495 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | SHADY GLEN 110132726 | 2201 | 0.00506 | SHADY GLEN 110132726 | 71 | 0.02023 | 99% | V3 Tranche 1 | Tier 2 | 492
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.986 | - | - | 0.986 | - | 0.986 | SI | Region 2 - North East | COLFAX | Placer | 39.0992 | -120.95 | SHADY GLEN 110151696 | 1581 | 0.023753 | SHADY GLEN 1101585766 | 542 | 0.0049817 | 99% | V3 Tranche 1 | Tier 2 | 493
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32802 | - | - | 0.32802 | - | 0.32802 | SI | Region 2 - North East | COLFAX | Placer | 39.0994 | -120.9559 | SHADY GLEN 1101CB | 2622 | 0.0010502 | SHADY GLEN 1101898212 | 869 | 0.0027704 | 99% | V3 Tranche 1 | Tier 2 | 494
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.2383 | - | - | 24.2383 | - | 24.2383 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | SHADY GLEN 11022232 | 2022 | 0.0086414 | SHADY GLEN 11022232 | 93 | 0.018723 | 99% | V3 Tranche 1 | Tier 3 | 495
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6883 | - | - | 12.6883 | - | 12.6883 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | SHADY GLEN 110248894 | 1378 | 0.034658 | SHADY GLEN 110248894 | 89 | 0.018876 | 99% | V3 Tranche 1 | Tier 3 | 496
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.814 | - | - | 23.814 | - | 23.814 | SI | Region 2 - North East | COLFAX | Placer | 39.1153 | -120.953 | SHADY GLEN 1102CB | 1829 | 0.01359 | SHADY GLEN 1102CB | 180 | 0.01361 | 99% | V3 Tranche 1 | Tier 3 | 497
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.020723 | - | - | 0.020723 | - | 0.020723 | SI | Region 2 - North East | CAMERON PARK | El Dorado | 38.6795 | -120.9797 | SHINGLE SPRINGS 210551738 | 1047 | 0.061564 | SHINGLE SPRINGS 210551738 | 1953 | 0.00056455 | 99% | V3 Tranche 1 | Tier 2 | 498
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.73323 | - | - | 0.73323 | - | 0.73323 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5715 | -122.4451 | SILVERADO 210437632 | 1235 | 0.044601 | SILVERADO 2104324994 | 873 | 0.0027563 | 99% | V3 Tranche 1 | Tier 3 | 499
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.5423 | - | - | 16.5423 | - | 16.5423 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5446 | -122.4781 | SILVERADO 210437632 | 1235 | 0.044601 | SILVERADO 2104515946 | 33 | 0.025445 | 99% | V3 Tranche 1 | Tier 3 | 500
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.5752 | - | - | 22.5752 | - | 22.5752 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.574 | -122.4444 | SILVERADO 2104632 | 792 | 0.094959 | SILVERADO 2104632 | 59 | 0.021383 | 99% | V3 Tranche 1 | Tier 3 | 501
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3951 | - | - | 4.3951 | - | 4.3951 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5755 | -122.4443 | SILVERADO 210437632 | 1235 | 0.044601 | SILVERADO 2104646776 | 14 | 0.034265 | 99% | V3 Tranche 1 | Tier 3 | 502
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.3167 | - | - | 3.3167 | - | 3.3167 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5146 | -122.4742 | SILVERADO 2104708 | 1648 | 0.02118 | SILVERADO 2104708 | 619 | 0.0043024 | 99% | V3 Tranche 1 | Tier 3 | 503
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.946 | - | - | 0.946 | - | 0.946 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.545 | -122.4756 | SILVERADO 2104722 | 690 | 0.11274 | SILVERADO 2104722 | 435 | 0.0064165 | 99% | V3 Tranche 1 | Tier 3 | 504
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 32.9297 | - | - | 32.9297 | - | 32.9297 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.6152 | -122.4292 | SILVERADO 2104726 | 279 | 0.22347 | SILVERADO 2104726 | 203 | 0.012452 | 99% | V3 Tranche 1 | Tier 3 | 505
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.1027 | - | - | 14.1027 | - | 14.1027 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5533 | -122.4563 | SILVERADO 210478268 | 1254 | 0.043133 | SILVERADO 210478268 | 101 | 0.018153 | 99% | V3 Tranche 1 | Tier 3 | 506
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.9886 | - | - | 22.9886 | - | 22.9886 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.617 | -122.4242 | SILVERADO 2104806 | 309 | 0.21008 | SILVERADO 2104806 | 805 | 0.00309 | 99% | V3 Tranche 1 | Tier 3 | 507
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7133 | - | - | 0.7133 | - | 0.7133 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5099 | -122.4785 | SILVERADO 21051306 | 2341 | 0.0030939 | SILVERADO 21051306 | 419 | 0.0067032 | 99% | V3 Tranche 1 | Tier 3 | 508
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.16686 | - | - | 0.16686 | - | 0.16686 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.505 | -122.4747 | SILVERADO 21051308 | 3223 | 5.7874e-06 | SILVERADO 21051308 | 793 | 0.0031429 | 99% | V3 Tranche 1 | Tier 3 | 509
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3898 | - | - | 4.3898 | - | 4.3898 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5377 | -122.4954 | SILVERADO 2105131568 | 1947 | 0.010281 | SILVERADO 2105131568 | 556 | 0.0048458 | 99% | V3 Tranche 1 | Tier 3 | 510
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.2957 | - | - | 9.2957 | - | 9.2957 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4984 | -122.4795 | SILVERADO 2105167360 | 2174 | 0.0056116 | SILVERADO 2105167360 | 398 | 0.0070204 | 99% | V3 Tranche 1 | Tier 3 | 511
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.5635 | - | - | 2.5635 | - | 2.5635 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5286 | -122.5007 | SILVERADO 2105247660 | 1901 | 0.011541 | SILVERADO 2105247660 | 291 | 0.0096168 | 99% | V3 Tranche 1 | Tier 3 | 512
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0817 | - | - | 1.0817 | - | 1.0817 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5471 | -122.5102 | SILVERADO 2105309298 | 2241 | 0.0043094 | SILVERADO 2105309298 | 594 | 0.0044669 | 99% | V3 Tranche 1 | Tier 3 | 513
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.3847 | - | - | 0.3847 | - | 0.3847 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5057 | -122.4845 | SILVERADO 2105337226 | 3085 | 9.3615e-06 | SILVERADO 2105337226 | 416 | 0.0067497 | 99% | V3 Tranche 1 | Tier 3 | 514
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.1185 | - | - | 13.1185 | - | 13.1185 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5071 | -122.4907 | SILVERADO 2105658898 | 1361 | 0.035763 | SILVERADO 2105658898 | 87 | 0.018978 | 99% | V3 Tranche 1 | Tier 3 | 515
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.19139 | - | - | 0.19139 | - | 0.19139 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5206 | -122.4936 | SILVERADO 21051306 | 2341 | 0.0030939 | SILVERADO 2105764650 | 1407 | 0.0011424 | 99% | V3 Tranche 1 | HFRA | 516
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.12596 | - | - | 0.12596 | - | 0.12596 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | SILVERADO 2105616 | 2351 | 0.0030112 | SILVERADO 2105900104 | 90 | 0.018786 | 99% | V3 Tranche 1 | Tier 3 | 517
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76549 | - | - | 0.76549 | - | 0.76549 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4943 | -122.4756 | SILVERADO 2105CB | 3201 | 6.2313e-06 | SILVERADO 2105990552 | 117 | 0.016818 | 99% | V3 Tranche 1 | Tier 3 | 518
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4863 | - | - | 5.4863 | - | 5.4863 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2328 | -120.3655 | STANISLAUS 17011331 | 2540 | 0.0015977 | STANISLAUS 17011331 | 186 | 0.013343 | 99% | V3 Tranche 1 | Tier 3 | 519
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7986 | - | - | 23.7986 | - | 23.7986 | ST | Region 5 - Central Valley | AVERY | Calaveras | 38.1832 | -120.3754 | STANISLAUS 17011812 | 1412 | 0.032657 | STANISLAUS 17011812 | 66 | 0.02064 | 99% | V3 Tranche 1 | Tier 3 | 520
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.7987 | - | - | 5.7987 | - | 5.7987 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1743 | -120.3835 | STANISLAUS 17017144 | 1661 | 0.020479 | STANISLAUS 17017144 | 269 | 0.010091 | 99% | V3 Tranche 1 | Tier 2 | 521
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6801 | - | - | 12.6801 | - | 12.6801 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1699 | -120.4067 | STANISLAUS 170179826 | 2142 | 0.0062159 | STANISLAUS 170179826 | 231 | 0.011425 | 99% | V3 Tranche 1 | Tier 2 | 522
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 44.875 | - | - | 44.875 | - | 44.875 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 | STANISLAUS 1701CB | 56 | 0.40353 | STANISLAUS 1701CB | 95 | 0.018647 | 99% | V3 Tranche 1 | Tier 2 | 523
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7229 | - | - | 23.7229 | - | 23.7229 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2366 | -120.3628 | STANISLAUS 17021888 | 2386 | 0.0026855 | STANISLAUS 17021888 | 379 | 0.0073524 | 99% | V3 Tranche 1 | Tier 3 | 524
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.4909 | - | - | 8.4909 | - | 8.4909 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2465 | -120.3642 | STANISLAUS 170237278 | 2810 | 0.00026318 | STANISLAUS 170237278 | 98 | 0.01848 | 99% | V3 Tranche 1 | Tier 3 | 525
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.3846 | - | - | 10.3846 | - | 10.3846 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2369 | -120.3646 | STANISLAUS 17026028 | 2670 | 0.0008147 | STANISLAUS 17026028 | 60 | 0.021109 | 99% | V3 Tranche 1 | Tier 3 | 526
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.2061 | - | - | 10.2061 | - | 10.2061 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 | STANISLAUS 1702CB | 235 | 0.24096 | STANISLAUS 1702CB | 54 | 0.022026 | 99% | V3 Tranche 1 | Tier 3 | 527
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7453 | - | - | 27.7453 | - | 27.7453 | NV | Region 2 - North East | CHICO | Butte | 39.8318 | -121.8444 | SYCAMORE CREEK 11112014 | 1137 | 0.053762 | SYCAMORE CREEK 11112014 | 434 | 0.0064305 | 99% | V3 Tranche 1 | Tier 3 | 528
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.1262 | - | - | 27.1262 | - | 27.1262 | NV | Region 2 - North East | COHASSET | Butte | 39.9034 | -121.742 | SYCAMORE CREEK 11112268 | 2537 | 0.0016039 | SYCAMORE CREEK 11112268 | 57 | 0.021521 | 99% | V3 Tranche 1 | Tier 3 | 529
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3948 | - | - | 4.3948 | - | 4.3948 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4495 | -120.4908 | TIGER CREEK 0201CB | 1744 | 0.016801 | TIGER CREEK 0201320746 | 151 | 0.015433 | 99% | V3 Tranche 1 | Tier 3 | 530
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32281 | - | - | 0.32281 | - | 0.32281 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4491 | -120.4927 | TIGER CREEK 0201CB | 1744 | 0.016801 | TIGER CREEK 0201CB | 8 | 0.040941 | 99% | V3 Tranche 1 | Tier 3 | 531
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.0017 | - | - | 16.0017 | - | 16.0017 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1583 | -122.9898 | UPPER LAKE 11011276 | 335 | 0.19794 | UPPER LAKE 11011276 | 35 | 0.024971 | 99% | V3 Tranche 1 | Tier 2 | 532
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8763 | - | - | 11.8763 | - | 11.8763 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1825 | -122.9619 | UPPER LAKE 1101412 | 259 | 0.23008 | UPPER LAKE 1101412 | 327 | 0.0086415 | 99% | V3 Tranche 1 | Tier 2 | 533
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.4939 | - | - | 15.4939 | - | 15.4939 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1894 | -122.9009 | UPPER LAKE 110175370 | 705 | 0.11161 | UPPER LAKE 110175370 | 309 | 0.0089653 | 99% | V3 Tranche 1 | Tier 3 | 534
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3587 | - | - | 1.3587 | - | 1.3587 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1457 | -122.9167 | UPPER LAKE 1101CB | 6 | 1.2559 | UPPER LAKE 1101CB | 588 | 0.0045199 | 99% | V3 Tranche 1 | Tier 2 | 535
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.4554 | - | - | 29.4554 | - | 29.4554 | SI | Region 2 - North East | WEIMAR | Placer | 39.0443 | -120.9859 | WEIMAR 11012058 | 1379 | 0.034582 | WEIMAR 11012058 | 166 | 0.014596 | 99% | V3 Tranche 1 | Tier 2 | 536
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.2219 | - | - | 23.2219 | - | 23.2219 | SI | Region 2 - North East | WEIMAR | Placer | 39.0318 | -120.9741 | WEIMAR 11012084 | 1801 | 0.014579 | WEIMAR 11012084 | 142 | 0.015811 | 99% | V3 Tranche 1 | Tier 2 | 537
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.6912 | - | - | 19.6912 | - | 19.6912 | SI | Region 2 - North East | WEIMAR | Placer | 39.0342 | -120.9744 | WEIMAR 11012740 | 2258 | 0.003969 | WEIMAR 11012740 | 272 | 0.010047 | 99% | V3 Tranche 1 | Tier 2 | 538
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7753 | - | - | 7.7753 | - | 7.7753 | SI | Region 2 - North East | WEIMAR | Placer | 39.0352 | -120.9794 | WEIMAR 11012764 | 2599 | 0.0011906 | WEIMAR 11012764 | 268 | 0.010095 | 99% | V3 Tranche 1 | Tier 2 | 539
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.8119 | - | - | 10.8119 | - | 10.8119 | SI | Region 2 - North East | WEIMAR | Placer | 39.036 | -120.9881 | WEIMAR 1101CB | 2422 | 0.0023893 | WEIMAR 1101CB | 214 | 0.012028 | 99% | V3 Tranche 1 | Tier 2 | 540
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.1738 | - | - | 8.1738 | - | 8.1738 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4437 | -120.5088 | WEST POINT 110112256 | 2589 | 0.0012622 | WEST POINT 110112256 | 352 | 0.0079522 | 99% | V3 Tranche 1 | Tier 3 | 541
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3469 | - | - | 29.3469 | - | 29.3469 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.487 | -120.5231 | WEST POINT 110113444 | 2293 | 0.0035258 | WEST POINT 110113444 | 256 | 0.01053 | 99% | V3 Tranche 1 | Tier 3 | 542
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.385 | - | - | 14.385 | - | 14.385 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4645 | -120.5292 | WEST POINT 11014706 | 2468 | 0.0020959 | WEST POINT 11014706 | 107 | 0.017455 | 99% | V3 Tranche 1 | Tier 3 | 543
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0056 | - | - | 6.0056 | - | 6.0056 | ST | Region 5 - Central Valley | MOUNTAIN RANCH | Amador | 38.421 | -120.5497 | WEST POINT 1101CB | 1765 | 0.015736 | WEST POINT 1101CB | 218 | 0.011836 | 99% | V3 Tranche 1 | Tier 3 | 544
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.374 | - | - | 1.374 | - | 1.374 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4575 | -120.5238 | WEST POINT 1101L1969 | 2786 | 0.00032448 | WEST POINT 1101L1969 | 681 | 0.0038479 | 99% | V3 Tranche 1 | Tier 3 | 545
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.2384 | - | - | 12.2384 | - | 12.2384 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3174 | -120.5212 | WEST POINT 11021341 | 2247 | 0.0041901 | WEST POINT 11021341 | 80 | 0.019265 | 99% | V3 Tranche 1 | Tier 3 | 546
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 90.2567 | - | - | 90.2567 | - | 90.2567 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3314 | -120.5186 | WEST POINT 11024788 | 1206 | 0.047319 | WEST POINT 11024788 | 164 | 0.014654 | 99% | V3 Tranche 1 | Tier 3 | 547
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.7214 | - | - | 9.7214 | - | 9.7214 | NV | Region 2 - North East | PLATINA | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | 52 | 0.41883 | WILDWOOD 11011454 | 86 | 0.018983 | 99% | V3 Tranche 1 | Tier 2 | 548
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.0775 | - | - | 10.0775 | - | 10.0775 | NV | Region 2 - North East | WILDWOOD | Trinity | 40.3846 | -123.0286 | WILDWOOD 11011576 | 1125 | 0.054922 | WILDWOOD 11011576 | 191 | 0.013119 | 99% | V3 Tranche 1 | Tier 2 | 549
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.6734 | - | - | 5.6734 | - | 5.6734 | NV | Region 2 - North East | PLATINA | Shasta | 40.3606 | -122.8896 | WILDWOOD 1101384582 | 598 | 0.13184 | WILDWOOD 1101384582 | 111 | 0.017225 | 99% | V3 Tranche 1 | Tier 2 | 550
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.284 | - | - | 6.284 | - | 6.284 | NV | Region 2 - North East | PLATINA | Shasta | 40.3607 | -122.9513 | WILDWOOD 110198896 | 454 | 0.16402 | WILDWOOD 110198896 | 109 | 0.017355 | 99% | V3 Tranche 1 | Tier 2 | 551
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.023199 | - | - | 0.023199 | - | 0.023199 | NB | Region 1 - North Coast | Calistoga | Napa | 38.579 | -122.5144 | CALISTOGA 1102769230 | 1624 | 0.022 | CALISTOGA 1102100335 | 874 | 0.0027 | 99% | V3 Tranche 1 | Tier 3 | 552 | 0.01856 | 0.023199
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0166 | - | - | 6.0166 | - | 6.0166 | NV | Region 2 - North East | Belden | Plumas | 39.9114 | -121.327 | BUCKS CREEK 1101CB | 11 | 0.735 | BUCKS CREEK 1101CB | 21 | 0.029 | 99% | V3 Tranche 1 | Tier 2/3 | 553 | 4.8133 | 6.0166
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.2372 | - | - | 20.2372 | - | 20.2372 | SI | Region 2 - North East | COLFAX | Placer | 39.1003 | -120.9524 | SHADY GLEN 110151696 | 1581 | 0.0237 | SHADY GLEN 110151696 | 208 | 0.0122 | 99% | V3 Tranche 1 | Non Tier, Tier 2 | 554 | 16.1898 | 20.2372
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1681 | -120.1025 | SPRING GAP 1702188426 | 911 | 0.0788 | SPRING GAP 1702188426 | 335 | 0.0085 | 99% | V3 Tranche 1 | Tier 3 | 555 | 0.0028409 | 0.0035511
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035512 | - | - | 0.0035512 | - | 0.0035512 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 | Narrows 2104 CB | 323 | 0.201 | NARROWS 2104CB | 136 | 0.016 | 99% | V3 Tranche 1 | Tier 2 | 556 | 0.0028409 | 0.0035512
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.35 | - | - | 6.35 | - | 6.35 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 | Narrows 2102 CB | 658 | 0.118 | NARROWS 2102CB | 46 | 0.023 | 99% | V3 Tranche 1 | Tier 2 | 557 | 5.08 | 6.35

## July 2022 Redacted (hidden)
Order | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2023 Forecast Miles | 2024-2026 Forecast Miles | Div | Region | City | County | Latitude | Longitude | Circuit Protection Zone (V2) | 2021-2023 Risk Rank (V2) | v2 Mean Risk | Circuit Protection Zone (V3) | 2024-2026 Risk Rank (V3) | v3 Mean Risk | Measured Effectiveness | Project Type (see 3rd tab for description) | HFTD Tier | Unique ID
35117455 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.172 | - | - | 1.172 | 1.172 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.594 |  | 2141 | 0.0062243 |  | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 1
35118673 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.6064 | - | - | 2.6064 | 2.6064 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8005 | -121.6047 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 2
35118674 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5212 | - | - | 2.5212 | 2.5212 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.6017 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 3
35126752 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.5909 | - | - | 1.5909 | 1.5909 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7333 | -121.6353 |  | 817 | 0.090831 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 4
35127550 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.9189 | - | - | 2.9189 | 2.9189 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7858 | -121.6004 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 5
35144480 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.7155 | - | - | 3.7155 | 3.7155 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8116 | -121.5956 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 6
35227400 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.233 | - | - | 3.233 | 3.233 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7712 | -121.6031 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 7
35227401 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.7701 | - | - | 1.7701 | 1.7701 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7628 | -121.6233 |  | 2922 | 3.3375e-05 |  | 69 | 0.020609 | 99% | Butte Rebuild | Tier 2 | 8
35227402 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.404 | - | - | 1.404 | 1.404 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6071 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 9
35227404 | Community Rebuild | 95F | ESTS | ESTIMATING | 0.99697 | - | - | 0.99697 | 0.99697 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7538 | -121.6172 |  | 2941 | 2.9018e-05 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 10
35227405 | Community Rebuild | 95F | PEND | PERMITTING/DEPENDENCY | 0.41477 | - | - | 0.41477 | 0.41477 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7578 | -121.6071 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 11
35227406 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.8989 | - | - | 2.8989 | 2.8989 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7523 | -121.6185 |  | 2467 | 0.0021 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | Tier 2 | 12
35227408 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.1447 | - | - | 2.1447 | 2.1447 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7524 | -121.6126 |  | 2941 | 2.9018e-05 |  | 2530 | 0.00029731 | 99% | Butte Rebuild | HFRA | 13
35227409 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.646 | - | - | 3.646 | 3.646 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7501 | -121.6242 |  | 2467 | 0.0021 |  | 1178 | 0.0017042 | 99% | Butte Rebuild | Tier 2 | 14
35227411 | Community Rebuild | 95F | ESTS | ESTIMATING | 3.3665 | - | - | 3.3665 | 3.3665 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7595 | 121.6024 |  | 2912 | 4.1187e-05 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 15
35227412 | Community Rebuild | 95F | ESTS | ESTIMATING | 1.2926 | - | - | 1.2926 | 1.2926 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.769 | -121.5786 |  | 2954 | 2.3677e-05 |  | 622 | 0.0042646 | 99% | Butte Rebuild | Tier 2 | 16
35227413 | Community Rebuild | 95F | ESTS | ESTIMATING | 4.1278 | - | - | 4.1278 | 4.1278 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7423 | -121.6423 |  | 734 | 0.10501 |  | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 17
35227415 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.2267 | - | - | 5.2267 | 5.2267 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7389 | -121.6402 |  | 2924 | 3.2259e-05 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 18
35227417 | Community Rebuild | 95F | ESTS | ESTIMATING | 5.7458 | - | - | 5.7458 | 5.7458 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7323 | -121.6513 |  | 734 | 0.10501 |  | 406 | 0.006875 | 99% | Butte Rebuild | Tier 2 & 3 | 19
35246308 | Community Rebuild | 95F | ESTS | ESTIMATING | 2.3438 | - | - | 2.3438 | 2.3438 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7572 | -121.5722 |  | 2126 | 0.0064968 |  | 1617 | 0.00084939 | 99% | Butte Rebuild | Tier 2 | 20
35246309 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.2898 | - | - | 1.2898 | 1.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7752 | -121.6093 |  | 2813 | 0.0002457 |  | 1546 | 0.00092573 | 99% | Butte Rebuild | Tier 2 | 21
35246316 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.5938 | - | - | 3.5938 | 3.5938 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7265 | -121.6374 |  | 817 | 0.090831 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 22
35246589 | Community Rebuild | 08W | ESTS | ESTIMATING | 1.0511 | - | - | 1.0511 | 1.0511 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.764 | -121.5986 |  | 2808 | 0.00026897 |  | 1618 | 0.00084828 | 99% | Butte Rebuild | Tier 2 | 23
35246590 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.2388 | - | - | 2.2388 | 2.2388 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7696 | -121.579 |  | 2383 | 0.0027 |  | 2198 | 0.00043536 | 99% | Butte Rebuild | Tier 2 | 24
35246591 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.2898 | - | - | 4.2898 | 4.2898 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7485 | -121.6086 |  | 2941 | 2.9018e-05 |  | 1563 | 0.00090699 | 99% | Butte Rebuild | Tier 2 | 25
35246598 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.4871 | - | - | 3.4871 | 3.4871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8149 | -121.5802 |  | 2211 | 0.0048412 |  | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 26
35352072 | Community Rebuild | 08W | ESTS | ESTIMATING | 0.56818 | - | - | 0.56818 | 0.56818 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.7703 | -121.6265 |  | 2910 | 4.2503e-05 |  | 26 | 0.026975 | 99% | Butte Rebuild | Tier 2 | 27
35353399 | Community Rebuild | 08W | ESTS | ESTIMATING | 3.2386 | - | - | 3.2386 | 3.2386 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8082 | -121.5973 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 28
35353463 | Community Rebuild | 08W | ESTS | ESTIMATING | 4.8871 | - | - | 4.8871 | 4.8871 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8121 | -121.5914 |  | 2484 | 0.0019488 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 29
35353466 | Community Rebuild | 08W | ESTS | ESTIMATING | 2.4148 | - | - | 2.4148 | 2.4148 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8091 | -121.5998 |  | 2849 | 0.00016422 |  | 302 | 0.0093524 | 99% | Butte Rebuild | Tier 2 | 30
35353467 | Community Rebuild | 08W | UNSE | SCOPING/SCOPED | 2.5544 | - | - | 2.5544 | 2.5544 | - | NV | Region 2 - North East | Magalia | BUTTE | 39.8182 | -121.5952 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 31
35321894 | Fire Rebuild | 08W | ESTS | Estimating | 0.087121 | - | - | 0.087121 | 0.087121 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0773 | -122.2434 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 32
35334404 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.6 | - | - | 0.6 | 0.6 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0671 | -122.2231 |  | 1393 | 0.033758 |  | 2485 | 0.00031335 | 99% | FRRB | Tier 2 | 33
35298571 | Base SH | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.469 | -122.2542 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | 99% | CWSP 2022-2023 | Tier 2 | 34
35331305 | Base SH | 08W | UNSE | Scoping/Scoped | 0.445 | - | - | 0.445 | 0.445 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4699 | -122.2473 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | 99% | CWSP - 2023 ICUG | Tier 2 | 35
35311895 | Base SH | 08W | UNSE | Scoping/Scoped | 2.78 | - | - | 2.78 | 2.78 | - | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 36
35330815 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4792 | -122.2645 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 37
35277925 | Base SH | 08W | PEND | Permitting/Dependency | 0.21326 | - | - | 0.21326 | 0.21326 | - | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0746 | -119.4845 |  | 63 | 0.39206 |  | 2126 | 0.00047477 | 99% | CWSP 2022-2023 | Tier 2 | 38
35277924 | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | - | 0.12955 | 0.23864 | 0.23864 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0071 | -119.4086 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 39
35277938 | Base SH | 08W | ESTS | Estimating | 0.38996 | - | 0.27973 | 0.6697 | 0.6697 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0125 | -119.4038 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 40
35278093 | Base SH | 08W | ESTS | Estimating | 0.41496 | - | 0.52008 | 0.93504 | 0.93504 | - | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9797 | -119.3677 |  | 163 | 0.27714 |  | 569 | 0.0047219 | 99% | CWSP 2022-2023 | Tier 2 | 41
35333501 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9851 | -121.1296 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 42
35333503 | Base SH | 08W | UNSE | Scoping/Scoped | 0.3 | 1.44 | - | 1.74 | 1.74 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9959 | -121.1355 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 43
35333504 | Base SH | 08W | UNSE | Scoping/Scoped | 0.45 | - | - | 0.45 | 0.45 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9992 | -121.1363 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 44
35311896 | Base SH | 08W | UNSE | Scoping/Scoped | 2.76 | - | - | 2.76 | 2.76 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9961 | -121.1091 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 45
35314415 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | 0.04 | - | 2.09 | 2.09 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9962 | -121.1167 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 46
35314416 | Base SH | 08W | UNSE | Scoping/Scoped | 1.1199 | 0.48011 | - | 1.6 | 1.6 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9981 | -121.1168 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 47
35334232 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9855 | -121.1087 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 48
35334234 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SI | Region 2 - North East | Auburn | PLACER | 38.9781 | -121.1088 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | 99% | CWSP - 2023 ICUG | Tier 2 | 49
35318074 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.33996 | - | - | 0.33996 | 0.33996 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.072 | -122.2298 |  | 2246 | 0.0041981 |  | 936 | 0.002497 | 99% | FRRB | Tier 2 | 50
35342335 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.5299 | - | - | 1.5299 | 1.5299 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1672 | -122.2131 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 51
35342336 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1699 | -122.2026 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 52
35342337 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.52008 | - | - | 0.52008 | 0.52008 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1657 | -122.2231 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 53
35342338 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.163 | -122.1902 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | 99% | FRRB | Tier 3 | 54
35311924 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.08447 | - | - | 0.08447 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6747 | -121.3798 |  | 1288 | 0.040961 |  | 267 | 0.010152 | 99% | FRRB | Tier 3 | 55
35292784 | Fire Rebuild | 08W | ESTS | Estimating | 3.0644 | - | - | 3.0644 | 3.0644 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | 99% | FRRB | Tier 2 | 56
35292788 | Fire Rebuild | 08W | ESTS | Estimating | 1.1 | - | - | 1.1 | 1.1 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | 99% | FRRB | Tier 2 | 57
35286103 | Base SH | 08W | UNSE | Scoping/Scoped | 3.0701 | - | - | 3.0701 | 3.0701 | - | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 58
35311596 | Base SH | 08W | UNSE | Scoping/Scoped | 3 | - | - | 3 | 3 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 59
35311626 | Base SH | 08W | UNSE | Scoping/Scoped | 3.64 | - | - | 3.64 | 3.64 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 60
35311627 | Base SH | 08W | UNSE | Scoping/Scoped | 2.05 | - | - | 2.05 | 2.05 | - | NV | Region 2 - North East | Canyon Dam | PLUMAS | 40.2105 | -121.1643 |  | 3328 | 4.1333e-06 |  | 969 | 0.0023864 | 99% | CWSP 2022-2023 | Tier 2 | 61
35279181 | Fire Rebuild | 08W | ESTS | Estimating | 5.589 | - | - | 5.589 | 5.589 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 62
35279182 | Fire Rebuild | 08W | ESTS | Estimating | 2.0701 | - | - | 2.0701 | 2.0701 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 63
35280560 | Fire Rebuild | 08W | ESTS | Estimating | 2.64 | - | - | 2.64 | 2.64 | - | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | FRRB - UG - 2021 | Tier 2 & 3 | 64
35320445 | Base SH | 08W | UNSE | Scoping/Scoped | 17.7201 | - | - | 17.7201 | 17.7201 | - | LP | Region 4 - Central Coast | Buellton | SANTA BARBARA | 34.6236 | -120.185 |  | 307 | 0.21085 |  | 2847 | 0.00018253 | 99% | CWSP - 2023 ICUG | Tier 2 | 65
35299634 | Base SH | 08W | UNSE | Scoping/Scoped | 2.61 | - | - | 2.61 | 2.61 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6568 | -121.5763 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 66
35329014 | Base SH | 08W | UNSE | Scoping/Scoped | 3.1701 | - | - | 3.1701 | 3.1701 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6666 | -121.5712 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | 99% | PSPS | Tier 2 | 67
35329012 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6201 | - | - | 1.6201 | 1.6201 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6908 | -121.5733 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 68
35329013 | Base SH | 08W | UNSE | Scoping/Scoped | 1.85 | 0.039962 | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6805 | -121.5693 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 69
35299633 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | - | - | 2.14 | 2.14 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6766 | -121.5675 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | 99% | PSPS | Tier 2 | 70
35299635 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.6988 | -121.5743 |  | 1535 | 0.025936 |  | 47 | 0.022808 | 99% | PSPS | Tier 2 | 71
35329016 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | NV | Region 2 - North East | Paradise | BUTTE | 39.709 | -121.5757 |  | 1535 | 0.025936 |  | 47 | 0.022808 | 99% | PSPS | Tier 2 | 72
35329009 | Base SH | 08W | UNSE | Scoping/Scoped | 0.94091 | - | 0.020076 | 0.96098 | 0.96098 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.655 | -121.5839 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 73
35329010 | Base SH | 08W | UNSE | Scoping/Scoped | 2.814 | - | 0.020076 | 2.8341 | 2.8341 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6564 | -121.5838 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 74
35329011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3229 | - | - | 2.3229 | 2.3229 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6667 | -121.5826 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 75
35299631 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4299 | - | - | 3.4299 | 3.4299 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6474 | -121.6306 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | 99% | PSPS | Tier 2 | 76
35299629 | Base SH | 08W | UNSE | Scoping/Scoped | 0.89091 | - | - | 0.89091 | 0.89091 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.654 | -121.6323 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 77
35329008 | Base SH | 08W | UNSE | Scoping/Scoped | 0.31307 | - | - | 0.31307 | 0.31307 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.6413 | -121.6413 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | 99% | PSPS | Tier 2 | 78
35334228 | Base SH | 08W | UNSE | Scoping/Scoped | 1.89 | - | - | 1.89 | 1.89 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8468 | -122.589 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 79
35334229 | Base SH | 08W | UNSE | Scoping/Scoped | 1.24 | - | - | 1.24 | 1.24 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8493 | -122.6179 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 80
35334230 | Base SH | 08W | UNSE | Scoping/Scoped | 1.64 | - | - | 1.64 | 1.64 | - | NV | Region 2 - North East | Covelo | TEHAMA | 39.8348 | -122.6319 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 81
35311897 | Base SH | 08W | UNSE | Scoping/Scoped | 2.11 | - | - | 2.11 | 2.11 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 |  | 413 | 0.17544 |  | 694 | 0.0037456 | 99% | PSPS - 2023 ICUG | Tier 2 | 82
35311898 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.9193 | -122.4369 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 83
35340270 | Base SH | 08W | UNSE | Scoping/Scoped | 1.84 | - | - | 1.84 | 1.84 | - | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 84
35340271 | Base SH | 08W | UNSE | Scoping/Scoped | 1.96 | - | - | 1.96 | 1.96 | - | NV | Region 2 - North East | Corning | Tehama | 39.9043 | -122.5022 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 85
35340272 | Base SH | 08W | UNSE | Scoping/Scoped | 1.56 | - | - | 1.56 | 1.56 | - | NV | Region 2 - North East | Corning | Tehama | 39.8887 | -122.5232 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 86
35340273 | Base SH | 08W | UNSE | Scoping/Scoped | 1.4299 | - | - | 1.4299 | 1.4299 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8831 | -122.5469 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 87
35340274 | Base SH | 08W | UNSE | Scoping/Scoped | 1.59 | - | - | 1.59 | 1.59 | - | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | 99% | PSPS - 2023 ICUG | Tier 2 | 88
35311899 | Base SH | 08W | UNSE | Scoping/Scoped | 3.44 | - | - | 3.44 | 3.44 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 89
35316561 | Base SH | 08W | UNSE | Scoping/Scoped | 4.41 | - | - | 4.41 | 4.41 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 90
35332218 | Base SH | 08W | UNSE | Scoping/Scoped | 3.26 | - | - | 3.26 | 3.26 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3986 | -122.3143 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 91
35332213 | Base SH | 08W | UNSE | Scoping/Scoped | 2.37 | - | - | 2.37 | 2.37 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3892 | -122.3258 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | 99% | PSPS - 2023 ICUG | Tier 2 | 92
35332214 | Base SH | 08W | UNSE | Scoping/Scoped | 4.04 | - | - | 4.04 | 4.04 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3899 | -122.3499 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 93
35332215 | Base SH | 08W | UNSE | Scoping/Scoped | 2.26 | - | - | 2.26 | 2.26 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4149 | -122.3421 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 94
35332216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.4042 | -122.3264 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 95
35332217 | Base SH | 08W | UNSE | Scoping/Scoped | 3.03 | - | 0.053 | 3.083 | 3.083 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3886 | -122.3831 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 96
35316567 | Base SH | 08W | UNSE | Scoping/Scoped | 3.42 | - | - | 3.42 | 3.42 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 97
35316569 | Base SH | 08W | UNSE | Scoping/Scoped | 4.81 | - | 0.032 | 4.842 | 4.842 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 98
35312540 | Base SH | 08W | UNSE | Scoping/Scoped | 4.88 | - | - | 4.88 | 4.88 | - | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | 99% | PSPS - 2023 ICUG | Tier 2 | 99
35312541 | Base SH | 08W | UNSE | Scoping/Scoped | 0.43 | - | - | 0.43 | 0.43 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9777 | -120.3274 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 100
35332868 | Base SH | 08W | UNSE | Scoping/Scoped | 2.53 | - | - | 2.53 | 2.53 | - | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9803 | -120.337 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | 99% | PSPS - 2023 ICUG | Tier 2 | 101
74010582 | Other | 30A | PEND | Permitting/Dependency | 1.3299 | - | - | 1.3299 | 1.3299 | - | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 |  | 811 | 0.092281 |  | 1184 | 0.0016787 | 99% | Other | Tier 2 | 102
35284023 | Fire Rebuild | 08W | DCNL | CLOSED | 1.1699 | - | - | 1.1699 | 1.1699 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4361 | -122.5779 |  | 1684 | 0.019316 |  | 732 | 0.0035071 | 99% | FRRB - UG - 2021 | Tier 3 | 103
35228774 | Base SH | 08W | ESTS | Estimating | 1.0008 | - | - | 1.0008 | 1.0008 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1091 | 0.0019786 | 99% | PSPS - Community Resiliency | Tier 2 | 104
35228775 | Base SH | 08W | ESTS | Estimating | 0.90341 | - | - | 0.90341 | 0.90341 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1232 | 0.0015282 | 99% | PSPS - Community Resiliency | Tier 2 | 105
35223063 | Base SH | 08W | ESTS | Estimating | 0.3197 | - | - | 0.3197 | 0.3197 | - | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | 2048 | 0.007993 |  | 1567 | 0.00090511 | 99% | PSPS - Community Resiliency | Tier 2 | 106
35312542 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | SO | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3791 | -122.5192 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 107
35343741 | Base SH | 08W | UNSE | Scoping/Scoped | 0.58 | - | - | 0.58 | 0.58 | - | SO | Region 1 - North Coast | Sonoma | SONOMA | 38.3371 | -122.4929 |  | 1827 | 0.01369 |  | 1080 | 0.0020136 | 99% | PSPS - 2023 ICUG | Tier 2 & 3 | 108
35285594 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | SI | Region 2 - North East | Twin Bridges | EL DORADO | 38.8075 | -120.0935 |  | 2005 | 0.0089565 |  | 2299 | 0.00038767 | 99% | FRRB | Tier 2 | 109
74001486 | Other | 30A | ADER | Estimating | 1.4576 | - | - | 1.4576 | 1.4576 | - | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 |  | 2792 | 0.00031068 |  | 2633 | 0.00025777 | 99% | Other | Tier 2 & 3 | 110
35058026 | Base SH | 08W | PEND | Permitting/Dependency | 0.6267 | - | - | 0.6267 | 0.6267 | - | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7593 | -120.5087 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | 99% | CWSP 2022-2023 | Tier 3 | 111
35312543 | Base SH | 08W | UNSE | Scoping/Scoped | 3.71 | - | - | 3.71 | 3.71 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5896 | -122.5395 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 112
35332360 | Base SH | 08W | UNSE | Scoping/Scoped | 5.46 | - | - | 5.46 | 5.46 | - | NV | Region 2 - North East | Willows | GLENN | 39.456 | -122.5138 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 113
35332362 | Base SH | 08W | UNSE | Scoping/Scoped | 3.83 | - | - | 3.83 | 3.83 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4286 | -122.5052 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 114
35332363 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | - | 1.13 | 1.13 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4073 | -122.5471 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 115
35332364 | Base SH | 08W | UNSE | Scoping/Scoped | 0.085 | - | 0.6 | 0.685 | 0.685 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.3944 | -122.5518 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 116
35330812 | Base SH | 08W | UNSE | Scoping/Scoped | 2.49 | - | - | 2.49 | 2.49 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5561 | -122.5414 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | PSPS - 2023 ICUG | Tier 2 | 117
35316278 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.4868 | -122.5188 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | 99% | CWSP - 2023 ICUG | Tier 2 | 118
35312544 | Base SH | 08W | UNSE | Scoping/Scoped | 0.44 | - | - | 0.44 | 0.44 | - | NV | Region 2 - North East | Elk Creek | GLENN | 39.5927 | -122.5431 |  | 206 | 0.25426 |  | 1350 | 0.0012407 | 99% | PSPS - 2023 ICUG | Tier 2 | 119
35312545 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8586 | -121.0805 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 120
35325589 | Base SH | 08W | UNSE | Scoping/Scoped | 1.21 | - | - | 1.21 | 1.21 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8537 | -121.0803 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 121
35325590 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8575 | -121.0758 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | 99% | CWSP - 2023 ICUG | Tier 2 | 122
35326790 | Base SH | 08W | UNSE | Scoping/Scoped | 0.14792 | - | - | 0.14792 | 0.14792 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8934 | -121.0677 |  | 2980 | 1.7619e-05 |  | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 123
35312546 | Base SH | 08W | UNSE | Scoping/Scoped | 1.013 | - | - | 1.013 | 1.013 | - | SI | Region 2 - North East | Auburn | PLACER | 38.8933 | -121.0676 |  | 2980 | 1.7619e-05 |  | 2071 | 0.00050684 | 99% | PSPS - 2023 ICUG | Tier 2 | 124
35320444 | Base SH | 08W | UNSE | Scoping/Scoped | 7.4 | - | - | 7.4 | 7.4 | - | LP | Region 4 - Central Coast | San Luis Obispo | SAN LUIS OBISPO | 35.3203 | -120.6932 |  | 1104 | 0.056447 |  | 1903 | 0.00059698 | 99% | PSPS - 2023 ICUG | Tier 2 | 125
35284810 | Fire Rebuild | 08W | ESTS | Estimating | 0.85814 | - | - | 0.85814 | 0.85814 | - | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.2086 | -122.3251 |  | 2186 | 0.0054078 |  | 2174 | 0.00044555 | 99% | FRRB | Tier 2 | 126
35283198 | Base SH | 08W | ESTS | Estimating | 0.27803 | - | - | 0.27803 | 0.27803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.108 | -122.9558 |  | 58 | 0.39723 |  | 486 | 0.0056859 | 99% | CWSP 2022-2023 | Tier 2 | 127
35231620 | Base SH | 08W | PEND | Permitting/Dependency | 2.6782 | - | - | 2.6782 | 2.6782 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | 27 | 0.5487 |  | 29 | 0.026126 | 99% | Top 250 Miles | Tier 2 & 3 | 128
35329471 | Base SH | 08W | UNSE | Scoping/Scoped | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9373 | -122.6091 |  | 3243 | 5.4342e-06 |  | 1561 | 0.00090896 | 99% | PSPS - 2023 ICUG | Tier 2 | 129
35320447 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | 1.09 | - | 1.93 | 1.93 | - | SI | Region 2 - North East | Granite Bay | PLACER | 38.782 | -121.1456 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 130
35339664 | Base SH | 08W | UNSE | Scoping/Scoped | 0.17 | 0.75 | - | 0.92 | 0.92 | - | SI | Region 2 - North East | Loomis | PLACER | 38.7815 | -121.1632 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 131
35339665 | Base SH | 08W | UNSE | Scoping/Scoped | 0.69 | - | - | 0.69 | 0.69 | - | SI | Region 2 - North East | Loomis | PLACER | 38.767 | -121.1635 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | 99% | CWSP - 2023 ICUG | Tier 2 | 132
35342143 | Base SH | 08W | UNSE | Scoping/Scoped | 3.354 | - | 1.962 | 5.316 | 5.316 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2645 | -122.1722 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 133
35342144 | Base SH | 08W | UNSE | Scoping/Scoped | 1.802 | - | 1.046 | 2.848 | 2.848 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2553 | -122.1615 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 134
35342145 | Base SH | 08W | UNSE | Scoping/Scoped | 0.163 | - | 0.13 | 0.293 | 0.293 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2566 | -122.1697 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 135
35342146 | Base SH | 08W | UNSE | Scoping/Scoped | 2.386 | - | 1.875 | 4.261 | 4.261 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.262 | -122.1635 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 136
35342147 | Base SH | 08W | UNSE | Scoping/Scoped | 1.865 | - | 1.343 | 3.208 | 3.208 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2706 | -122.167 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 137
35342148 | Base SH | 08W | UNSE | Scoping/Scoped | 1.265 | - | 1.095 | 2.36 | 2.36 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2714 | -122.1672 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 138
35342151 | Base SH | 08W | UNSE | Scoping/Scoped | 0.08 | - | 0.085 | 0.165 | 0.165 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2491 | -122.1769 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 139
35320442 | Base SH | 08W | UNSE | Scoping/Scoped | 0.578 | - | 0.464 | 1.052 | 1.052 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2515 | -122.161 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | PSPS - 2023 ICUG | Tier 2 | 140
35320462 | Base SH | 08W | UNSE | Scoping/Scoped | 0.35 | - | - | 0.35 | 0.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2642 | -122.1295 |  | 1848 | 0.012819 |  | 8953 | 2.3644e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 141
35320460 | Base SH | 08W | UNSE | Scoping/Scoped | 1.78 | - | - | 1.78 | 1.78 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3063 | -122.1288 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 142
35320461 | Base SH | 08W | UNSE | Scoping/Scoped | 3.56 | - | - | 3.56 | 3.56 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.299 | -122.1519 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 143
35338404 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | 0.56 | 1.59 | 1.59 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3141 | -122.1263 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 144
35338405 | Base SH | 08W | UNSE | Scoping/Scoped | 2.24 | - | - | 2.24 | 2.24 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2972 | -122.1262 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 145
35338406 | Base SH | 08W | UNSE | Scoping/Scoped | 1.14 | - | - | 1.14 | 1.14 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2877 | -122.1043 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 146
35338407 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66 | - | 0.41 | 1.07 | 1.07 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3039 | -122.0964 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 147
35338408 | Base SH | 08W | UNSE | Scoping/Scoped | 1.13 | - | 0.09 | 1.22 | 1.22 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.3148 | -122.0962 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 148
35338409 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2968 | -122.1356 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 149
35338410 | Base SH | 08W | UNSE | Scoping/Scoped | 2.21 | - | - | 2.21 | 2.21 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2925 | -122.1292 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 150
35339293 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | NB | Region 2 - North East | Fairfield | SOLANO | 38.3158 | -122.1039 |  | 393 | 0.18223 |  | 728 | 0.0035256 | 99% | PSPS - 2023 ICUG | Tier 2 | 151
35320463 | Base SH | 08W | UNSE | Scoping/Scoped | 1.44 | - | - | 1.44 | 1.44 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.284 | -122.128 |  | 419 | 0.17457 |  | 987 | 0.0022992 | 99% | PSPS - 2023 ICUG | Tier 2 | 152
35337014 | Base SH | 08W | UNSE | Scoping/Scoped | 0.02 | 0.83 | - | 0.85 | 0.85 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2525 | -122.144 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 153
35337015 | Base SH | 08W | UNSE | Scoping/Scoped | 0.49 | - | - | 0.49 | 0.49 | - | SA | Region 2 - North East | Fairfield | SOLANO | 38.2533 | -122.1356 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | 99% | CWSP - 2023 ICUG | Tier 2 | 154
35312548 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4517 | -122.3081 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 155
35339282 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | - | - | 0.51 | 0.51 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4516 | -122.3245 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 156
35339283 | Base SH | 08W | UNSE | Scoping/Scoped | 2.96 | - | - | 2.96 | 2.96 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 157
35339285 | Base SH | 08W | UNSE | Scoping/Scoped | 2.32 | - | - | 2.32 | 2.32 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 158
35339286 | Base SH | 08W | UNSE | Scoping/Scoped | 2.54 | - | - | 2.54 | 2.54 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4362 | -122.3535 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 159
35339287 | Base SH | 08W | UNSE | Scoping/Scoped | 1.2 | - | - | 1.2 | 1.2 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4427 | -122.3927 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 160
35339288 | Base SH | 08W | UNSE | Scoping/Scoped | 2.25 | - | - | 2.25 | 2.25 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4403 | -122.4075 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 161
35339289 | Base SH | 08W | UNSE | Scoping/Scoped | 1.82 | - | - | 1.82 | 1.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4493 | -122.4078 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 162
35337008 | Base SH | 08W | UNSE | Scoping/Scoped | 2.35 | - | - | 2.35 | 2.35 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4409 | -122.3061 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 163
35337010 | Base SH | 08W | UNSE | Scoping/Scoped | 3.82 | - | - | 3.82 | 3.82 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4416 | -122.3258 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 164
35337011 | Base SH | 08W | UNSE | Scoping/Scoped | 2.89 | - | - | 2.89 | 2.89 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4406 | -122.3414 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 165
35337012 | Base SH | 08W | UNSE | Scoping/Scoped | 4.92 | - | - | 4.92 | 4.92 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.443 | -122.3663 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 166
35317480 | Base SH | 08W | UNSE | Scoping/Scoped | 2.06 | - | - | 2.06 | 2.06 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4488 | -122.3179 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 167
35317887 | Base SH | 08W | UNSE | Scoping/Scoped | 0.8 | - | - | 0.8 | 0.8 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4377 | -122.3878 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | 99% | CWSP - 2023 ICUG | Tier 2 | 168
35312549 | Base SH | 08W | UNSE | Scoping/Scoped | 0.98 | - | - | 0.98 | 0.98 | - | NV | Region 2 - North East | Redding | SHASTA | 40.4913 | -122.2744 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 169
35332866 | Base SH | 08W | UNSE | Scoping/Scoped | 1.01 | - | - | 1.01 | 1.01 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4668 | -122.3357 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | 99% | PSPS - 2023 ICUG | Tier 2 | 170
35337163 | Base SH | 08W | ESTS | Estimating | 1.39 | 0.49 | - | 1.88 | 1.88 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.97 | -121.2606 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 171
35320449 | Base SH | 08W | ESTS | Estimating | 1.84 | - | - | 1.84 | 1.84 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9755 | -121.2772 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | 99% | CWSP - 2023 ICUG | Tier 2 | 172
35320312 | Base SH | 08W | ESTS | Estimating | 2.04 | - | - | 2.04 | 2.04 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9507 | -121.219 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 173
35332958 | Base SH | 08W | ESTS | Estimating | 1.37 | - | - | 1.37 | 1.37 | - | SI | Region 2 - North East | Lincoln | PLACER | 38.9431 | -121.219 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | 99% | CWSP - 2023 ICUG | Tier 2 | 174
35320450 | Base SH | 08W | UNSE | Scoping/Scoped | 2.14 | 0.02 | - | 2.16 | 2.16 | - | SI | Region 2 - North East | Lincoln | PLACER | 39.0041 | -121.2605 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | 99% | CWSP - 2023 ICUG | Tier 2 | 175
35274589 | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | - | - | 2.132 | 2.132 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5186 | -119.9402 |  | 428 | 0.17286 |  | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 176
35274593 | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | - | - | 2.756 | 2.756 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5165 | -119.9716 |  | 428 | 0.17286 |  | 249 | 0.010861 | 99% | CWSP 2022-2023 | Tier 2 | 177
35280362 | Base SH | 08W | ESTS | Estimating | 0.1089 | - | - | 0.1089 | 0.1089 | - | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9483 |  | 50 | 0.4205 |  | 400 | 0.0069412 | 99% | Top 250 Miles | Tier 2 & 3 | 178
35226621 | Base SH | 08W | PEND | Permitting/Dependency | 1.55 | - | - | 1.55 | 1.55 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 179
35192282 | Base SH | 08W | PEND | Permitting/Dependency | 2.04 | - | - | 2.04 | 2.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | ECOP - Top 20% | Tier 3 | 180
35174478 | Base SH | 08W | PEND | Permitting/Dependency | 1.04 | - | - | 1.04 | 1.04 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 181
35226873 | Base SH | 08W | UNSE | Scoping/Scoped | 1.0394 | - | - | 1.0394 | 1.0394 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 182
35226878 | Base SH | 08W | PEND | Permitting/Dependency | 0.58883 | - | - | 0.58883 | 0.58883 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 183
35227001 | Base SH | 08W | PEND | Permitting/Dependency | 0.7214 | - | - | 0.7214 | 0.7214 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 184
35227002 | Base SH | 08W | PEND | Permitting/Dependency | 0.43295 | - | - | 0.43295 | 0.43295 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 185
35227003 | Base SH | 08W | PEND | Permitting/Dependency | 0.58087 | - | - | 0.58087 | 0.58087 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 186
35227007 | Base SH | 08W | PEND | Permitting/Dependency | 2.8756 | - | - | 2.8756 | 2.8756 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 187
35227015 | Base SH | 08W | CONS | In-Construction | 0.01572 | 0.80947 | - | 0.82519 | 0.82519 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 188
35227025 | Base SH | 08W | ESTS | Estimating | 1.1828 | - | - | 1.1828 | 1.1828 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 189
35234756 | Base SH | 08W | ESTS | Estimating | 2.782 | - | - | 2.782 | 2.782 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 190
35234758 | Base SH | 08W | PEND | Permitting/Dependency | 0.58201 | - | - | 0.58201 | 0.58201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 191
35234862 | Base SH | 08W | PEND | Permitting/Dependency | 0.079924 | - | - | 0.079924 | 0.079924 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 192
35234865 | Base SH | 08W | PEND | Permitting/Dependency | 0.64754 | - | - | 0.64754 | 0.64754 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | ECOP - Top 20% | Tier 3 | 193
35227160 | Base SH | 08W | PEND | Permitting/Dependency | 1.3201 | - | - | 1.3201 | 1.3201 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | 8 | 0.91632 |  | 392 | 0.007089 | 99% | Top 50 Miles | Tier 2 | 194
35217271 | Base SH | 08W | PEND | Permitting/Dependency | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 195
35220895 | Base SH | 08W | PEND | Permitting/Dependency | 1.9299 | - | - | 1.9299 | 1.9299 | - | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 196
35228186 | Base SH | 08W | APPR | Estimating | 1.49 | - | - | 1.49 | 1.49 | - | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | 14 | 0.71618 |  | 443 | 0.006302 | 99% | Top 50 Miles | Tier 2 & 3 | 197
35056808 | Other | 30A | PEND | Permitting/Dependency | 1.5138 | - | - | 1.5138 | 1.5138 | - | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 |  | 534 | 0.14747 |  | 1720 | 0.00074971 | 99% | Other | Tier 3 | 198
35305303 | Base SH | 08W | ESTS | Estimating | 1.065 | - | - | 1.065 | 1.065 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8972 | -120.989 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 199
35305308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.66799 | - | - | 0.66799 | 0.66799 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8944 | -120.9647 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 200
35293662 | Base SH | 08W | ESTS | Estimating | 0.5 | - | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8956 | -120.9606 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 201
35293663 | Base SH | 08W | ESTS | Estimating | 0.98996 | - | - | 0.98996 | 0.98996 | - | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8964 | -120.922 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 202
35293665 | Base SH | 08W | ESTS | Estimating | 0.41572 | - | 0.070833 | 0.48655 | 0.48655 | - | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 203
35293670 | Base SH | 08W | UNSE | Scoping/Scoped | 0.54394 | - | - | 0.54394 | 0.54394 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8805 | -120.9418 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | CWSP 2022-2023 | Tier 2 | 204
35223032 | Base SH | 08W | ESTS | Estimating | 0.84924 | - | - | 0.84924 | 0.84924 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8855 | -121.0156 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | PSPS - Community Resiliency | Tier 2 | 205
35293508 | Base SH | 08W | ESTS | Estimating | 0.51004 | - | - | 0.51004 | 0.51004 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8729 | -120.991 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 206
35301112 | Base SH | 08W | ESTS | Estimating | 0.45 | 0.05 | - | 0.5 | 0.5 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8641 | -120.9817 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 207
35300933 | Base SH | 08W | ESTS | Estimating | 0.77992 | - | - | 0.77992 | 0.77992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.8775 | -120.993 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 208
35254067 | Base SH | 08W | ESTS | Estimating | 0.43996 | 0.039962 | - | 0.47992 | 0.47992 | - | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 |  | 68 | 0.38665 |  | 106 | 0.017565 | 99% | CWSP 2022-2023 | Tier 2 | 209
35320464 | Base SH | 08W | UNSE | Scoping/Scoped | 0.21989 | - | - | 0.21989 | 0.21989 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4267 | -122.2656 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 210
35338402 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | NV | Region 2 - North East | Anderson | SHASTA | 40.4214 | -122.2578 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | 99% | PSPS - 2023 ICUG | Tier 2 | 211
35224856 | Other | 10K | APPR | Estimating | 2.803 | 0.10985 | - | 2.9129 | 1.7765 | - | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | 99% | Other | Tier 2 & 3 | 212
35219543 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24 | - | - | 0.24 | 0.24 | - | SI | Region 2 - North East | Placerville | EL DORADO | 38.7293 | -120.7998 |  | 2123 | 0.0065148 |  | 1979 | 0.00055552 | 99% | PSPS - Community Resiliency | Tier 2 | 213
35297464 | Fire Rebuild | 08W | ESTS | Estimating | 0.56818 | - | - | 0.56818 | 0.56818 | - | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0777 | -122.2439 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | 99% | FRRB | Tier 2 | 214
35293846 | Base SH | 08W | ESTS | Estimating | 0.85985 | - | - | 0.85985 | 0.85985 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3008 | -123.0524 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 215
35290504 | Base SH | 08W | ESTS | Estimating | 0.61004 | - | - | 0.61004 | 0.61004 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2145 | -123.0742 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 216
35290508 | Base SH | 08W | ESTS | Estimating | 0.62008 | - | - | 0.62008 | 0.62008 | - | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1987 | -123.0496 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 217
35290808 | Base SH | 08W | ESTS | Estimating | 0.24508 | - | - | 0.24508 | 0.24508 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2815 | -123.1027 |  | 75 | 0.37685 |  | 573 | 0.0046795 | 99% | CWSP 2022-2023 | Tier 2 | 218
35285064 | Base SH | 08W | ADER | Estimating | 0.58636 | - | - | 0.58636 | 0.58636 | - | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3076 | -123.1132 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | 99% | CWSP 2022-2023 | Tier 2 | 219
35312550 | Base SH | 08W | UNSE | Scoping/Scoped | 1.54 | - | - | 1.54 | 1.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 220
35317399 | Base SH | 08W | UNSE | Scoping/Scoped | 1.18 | - | - | 1.18 | 1.18 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 221
35330211 | Base SH | 08W | UNSE | Scoping/Scoped | 1.97 | - | - | 1.97 | 1.97 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.5858 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 222
35330213 | Base SH | 08W | UNSE | Scoping/Scoped | 5.26 | - | - | 5.26 | 5.26 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.5887 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 223
35330215 | Base SH | 08W | UNSE | Scoping/Scoped | 3.54 | - | - | 3.54 | 3.54 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0669 | -122.5993 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 224
35330216 | Base SH | 08W | UNSE | Scoping/Scoped | 1.43 | - | - | 1.43 | 1.43 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0696 | -122.585 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 225
35330217 | Base SH | 08W | UNSE | Scoping/Scoped | 0.28 | - | - | 0.28 | 0.28 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0506 | -122.5833 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 226
35330219 | Base SH | 08W | UNSE | Scoping/Scoped | 3.13 | - | - | 3.13 | 3.13 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0688 | -122.6043 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 227
35330241 | Base SH | 08W | UNSE | Scoping/Scoped | 2.855 | - | - | 2.855 | 2.855 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0823 | -122.6045 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | CWSP - 2023 ICUG | Tier 3 | 228
35329472 | Base SH | 08W | UNSE | Scoping/Scoped | 2.869 | - | - | 2.869 | 2.869 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0748 | -122.6503 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 229
35329473 | Base SH | 08W | UNSE | Scoping/Scoped | 4.761 | - | - | 4.761 | 4.761 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0654 | -122.6333 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 230
35312551 | Base SH | 08W | UNSE | Scoping/Scoped | 3.205 | - | - | 3.205 | 3.205 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0837 | -122.66 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | CWSP - 2023 ICUG | Tier 3 | 231
35312552 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77 | - | - | 0.77 | 0.77 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.023 | -122.6779 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 232
35330244 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42 | - | - | 0.42 | 0.42 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0531 | -122.6813 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 233
35330245 | Base SH | 08W | UNSE | Scoping/Scoped | 0.09 | - | - | 0.09 | 0.09 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0541 | -122.6767 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 234
35330246 | Base SH | 08W | UNSE | Scoping/Scoped | 1.03 | - | - | 1.03 | 1.03 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.6814 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 235
35330247 | Base SH | 08W | UNSE | Scoping/Scoped | 0.75 | - | - | 0.75 | 0.75 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.04 | -122.6823 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 236
35330248 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4 | - | - | 2.4 | 2.4 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0296 | -122.6802 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 237
35330249 | Base SH | 08W | UNSE | Scoping/Scoped | 4 | 0.25 | - | 4.25 | 4.25 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.6799 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 238
35329474 | Base SH | 08W | UNSE | Scoping/Scoped | 0.11 | 1.16 | - | 1.27 | 1.27 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0932 | -122.6804 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 239
35317398 | Base SH | 08W | UNSE | Scoping/Scoped | 3.52 | - | - | 3.52 | 3.52 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0581 | -122.693 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | CWSP - 2023 ICUG | Tier 2 & 3 | 240
35312558 | Base SH | 08W | UNSE | Scoping/Scoped | 0.71004 | - | - | 0.71004 | 0.71004 | - | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0269 | -122.663 |  | 371 | 0.18973 |  | 407 | 0.0068603 | 99% | PSPS - 2023 ICUG | Tier 2 | 241
35335235 | Base SH | 08W | UNSE | Scoping/Scoped | 3.15 | - | - | 3.15 | 3.15 | - | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5192 | -122.4719 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | 99% | PSPS - 2023 ICUG | Tier 3 | 242
35278899 | Base SH | 08W | ESTS | Estimating | 1.3449 | - | - | 1.3449 | 1.3449 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 243
35279120 | Base SH | 08W | ESTS | Estimating | 1.004 | - | - | 1.004 | 1.004 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 244
35338384 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | CWSP 2022-2023 | Tier 2 | 245
35284364 | Base SH | 08W | ESTS | Estimating | 0.64261 | 0.040341 | - | 0.68295 | 0.68295 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 246
35284365 | Base SH | 08W | ESTS | Estimating | 1.6292 | 0.019508 | - | 1.6487 | 1.6487 | - | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2399 | -120.3619 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 247
35337306 | Base SH | 08W | ESTS | Estimating | 2.1871 | - | - | 2.1871 | 2.1871 | - | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | CWSP 2022-2023 | Tier 2 | 248
35297984 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1201 | - | - | 1.1201 | 1.1201 | - | NV | Region 2 - North East | Redding | SHASTA | 40.6951 | -122.3174 |  | 851 | 0.085979 |  | 2266 | 0.00040165 | 99% | FRRB | Tier 2 | 249
35312553 | Base SH | 08W | UNSE | Scoping/Scoped | 2.39 | - | - | 2.39 | 2.39 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8582 | -118.8837 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 250
35335286 | Base SH | 08W | UNSE | Scoping/Scoped | 5.21 | - | - | 5.21 | 5.21 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8542 | -118.893 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 251
35335287 | Base SH | 08W | UNSE | Scoping/Scoped | 2.18 | - | - | 2.18 | 2.18 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8466 | -118.8987 |  | 642 | 0.12034 |  | 72 | 0.020158 | 99% | PSPS - 2023 ICUG | Tier 2 | 252
35335288 | Base SH | 08W | UNSE | Scoping/Scoped | 3.6 | 1.38 | - | 4.98 | 4.98 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9158 | -118.9258 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 253
35321445 | Base SH | 08W | UNSE | Scoping/Scoped | 8.11 | - | - | 8.11 | 8.11 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8908 | -118.9154 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 254
35312554 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | 691 | 0.11269 |  | 368 | 0.0075263 | 99% | PSPS - 2023 ICUG | Tier 2 | 255
35312555 | Base SH | 08W | UNSE | Scoping/Scoped | 7.41 | - | - | 7.41 | 7.41 | - | KE | Region 5 - Central Valley | Lebec | KERN | 34.8814 | -118.9012 |  | 583 | 0.1353 |  | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 256
35320607 | Base SH | 08W | UNSE | Scoping/Scoped | 10 | - | - | 10 | 10 | - | KE | Region 5 - Central Valley | LEBEC | KERN | 34.846 | -118.872 |  | 583 | 0.1353 |  | 219 | 0.011818 | 99% | PSPS - 2023 ICUG | Tier 2 | 257
35256083 | Base SH | 08W | ESTS | Estimating | 1.847 | 0.0075758 | - | 1.8545 | 1.8545 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1434 | -123.0023 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 258
35283343 | Base SH | 08W | ESTS | Estimating | 0.85303 | - | - | 0.85303 | 0.85303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1488 | -122.9992 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 259
35283346 | Base SH | 08W | ESTS | Estimating | 0.77803 | - | - | 0.77803 | 0.77803 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.13 | -122.997 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 260
35285249 | Base SH | 08W | ESTS | Estimating | 2.593 | - | - | 2.593 | 2.593 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1673 | -123.0087 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 261
35285251 | Base SH | 08W | ESTS | Estimating | 0.65303 | - | - | 0.65303 | 0.65303 | - | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1758 | -123.0191 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | CWSP 2022-2023 | Tier 2 | 262
35334753 | Base SH | 08W | ESTS | Estimating | 5.69 | - | - | 5.69 | 5.69 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4313 | -122.05 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 263
35334754 | Base SH | 08W | UNSE | Scoping/Scoped | 3.93 | - | - | 3.93 | 3.93 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4024 | -122.0318 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 264
35334755 | Base SH | 08W | UNSE | Scoping/Scoped | 1.47 | - | - | 1.47 | 1.47 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3911 | -122.0367 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 265
35320336 | Base SH | 08W | UNSE | Scoping/Scoped | 2.3 | - | - | 2.3 | 2.3 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4365 | -122.0527 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 266
35320339 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.4168 | -122.0381 |  | 122 | 0.31672 |  | 491 | 0.0056058 | 99% | PSPS - 2023 ICUG | Tier 2 | 267
35320333 | Base SH | 08W | UNSE | Scoping/Scoped | 2.95 | - | - | 2.95 | 2.95 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.344 | -122.0247 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 268
35320334 | Base SH | 08W | UNSE | Scoping/Scoped | 2.5 | - | - | 2.5 | 2.5 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3618 | -122.0219 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 269
35334750 | Base SH | 08W | UNSE | Scoping/Scoped | 1.49 | - | - | 1.49 | 1.49 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3588 | -122.0245 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 270
35334752 | Base SH | 08W | UNSE | Scoping/Scoped | 1.81 | - | - | 1.81 | 1.81 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3655 | -122.0233 |  | 64 | 0.39138 |  | 768 | 0.0032459 | 99% | PSPS - 2023 ICUG | Tier 2 | 271
35320440 | Base SH | 08W | UNSE | Scoping/Scoped | 2.2 | - | - | 2.2 | 2.2 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3783 | -122.0044 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 272
35335291 | Base SH | 08W | UNSE | Scoping/Scoped | 1.33 | - | - | 1.33 | 1.33 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3771 | -121.9968 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 273
35335292 | Base SH | 08W | UNSE | Scoping/Scoped | 1.88 | - | - | 1.88 | 1.88 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3772 | -121.9918 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 274
35335293 | Base SH | 08W | UNSE | Scoping/Scoped | 2.41 | - | - | 2.41 | 2.41 | - | SA | Region 2 - North East | Vacaville | SOLANO | 38.3663 | -121.9916 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | 99% | PSPS - 2023 ICUG | Tier 2 | 275
35334466 | Base SH | 08W | UNSE | Scoping/Scoped | 1.6 | - | - | 1.6 | 1.6 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3386 | -122.1218 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 276
35334467 | Base SH | 08W | UNSE | Scoping/Scoped | 2.0271 | - | - | 2.0271 | 2.0271 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3305 | -122.0971 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 277
35334468 | Base SH | 08W | UNSE | Scoping/Scoped | 1.136 | 0.095076 | - | 1.2311 | 1.2311 | - | NV | Region 2 - North East | Red Bluff | TEHAMA | 40.3139 | -122.0706 |  | 580 | 0.13616 |  | 704 | 0.0036607 | 99% | PSPS - 2023 ICUG | Tier 2 | 278
35254656 | Base SH | 08W | PEND | Permitting/Dependency | 0.44205 | - | - | 0.44205 | 0.44205 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4587 | -121.867 |  | 85 | 0.36191 |  | 2428 | 0.00033385 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 279
35254259 | Base SH | 08W | UNSE | Scoping/Scoped | 0.85 | - | - | 0.85 | 0.85 | - | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8662 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | 99% | CWSP 2022-2023 | Tier 2 & 3 | 280
35297692 | Fire Rebuild | 08W | ESTS | Estimating | 4.6598 | - | - | 4.6598 | 4.6598 | - | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 281
35334407 | Fire Rebuild | 08W | ESTS | Estimating | 0.089962 | - | - | 0.089962 | 0.089962 | - | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7875 | -123.4468 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | FRRB | Tier 2 | 282
35320466 | Base SH | 08W | UNSE | Scoping/Scoped | 2 | - | - | 2 | 2 | - | HB | Region 1 - North Coast | Salyer | TRINITY | 40.8669 | -123.5148 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | 99% | CWSP - 2023 ICUG | Tier 2 | 283
35283938 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | - | - | 2.4799 | 2.4799 | - | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3845 | -122.2937 |  | 1145 | 0.05299 |  | 1026 | 0.0021738 | 99% | CWSP 2022-2023 | Tier 3 | 284
35341054 | Fire Rebuild | 08W | ESTS | Estimating | 0.088258 | - | - | 0.088258 | 0.088258 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6143 | -121.4029 |  | 1849 | 0.012814 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 285
35335712 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.0087121 | - | - | 0.0087121 | 0.0087121 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6333 | -121.4164 |  | 1849 | 0.012814 |  | 250 | 0.010796 | 99% | FRRB - UG - 2021 | Tier 3 | 286
35241075 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | - | - | 0.070076 | 0.070076 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 287
35241076 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | - | - | 0.11004 | 0.11004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 288
35241077 | Fire Rebuild | 08W | ADER | Estimating | 0.31004 | - | - | 0.31004 | 0.31004 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 289
35236997 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | - | - | 0.28409 | 0.28409 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6827 | -121.3105 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - REMG - 2021 | Tier 3 | 290
35235672 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | - | - | 0.30303 | 0.30303 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 291
35235675 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | - | - | 0.11364 | 0.11364 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.655 | -121.459 |  | 1176 | 0.050062 |  | 526 | 0.0051219 | 99% | FRRB - UG - 2021 | Tier 3 | 292
35320807 | Fire Rebuild | 08W | ADER | Estimating | 0.085227 | - | - | 0.085227 | 0.085227 | - | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6274 | -121.3727 |  | 1299 | 0.040282 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 293
35331458 | Fire Rebuild | 08W | ESTS | Estimating | 0.08428 | - | - | 0.08428 | 0.08447 | - | NV | Region 2 - North East | Berry Creek | Butte | 39.6272 | -121.3969 |  | 1299 | 0.040282 |  | 250 | 0.010796 | 99% | FRRB | Tier 3 | 294
35312560 | Base SH | 08W | UNSE | Scoping/Scoped | 1.98 | - | - | 1.98 | 1.98 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5054 | -121.4999 |  | 645 | 0.12006 |  | 1945 | 0.0005689 | 99% | PSPS - 2023 ICUG | Tier 2 | 295
35331306 | Base SH | 08W | UNSE | Scoping/Scoped | 2.67 | - | - | 2.67 | 2.67 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5178 | -121.4854 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 296
35331307 | Base SH | 08W | UNSE | Scoping/Scoped | 2.55 | - | - | 2.55 | 2.55 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5261 | -121.4815 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 297
35331308 | Base SH | 08W | UNSE | Scoping/Scoped | 0.82 | - | - | 0.82 | 0.82 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5171 | -121.4825 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 298
35343394 | Base SH | 08W | UNSE | Scoping/Scoped | 1.17 | - | - | 1.17 | 1.17 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5152 | -121.4932 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 299
35343395 | Base SH | 08W | UNSE | Scoping/Scoped | 1.76 | - | - | 1.76 | 1.76 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5168 | -121.4943 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 300
35343396 | Base SH | 08W | UNSE | Scoping/Scoped | 1.08 | - | - | 1.08 | 1.08 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.52 | -121.4943 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 301
35343397 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84 | - | - | 0.84 | 0.84 | - | NV | Region 2 - North East | Oroville | BUTTE | 39.5082 | -121.5038 |  | 1724 | 0.017468 |  | 1779 | 0.00070123 | 99% | PSPS - 2023 ICUG | Tier 2 | 302
35320446 | Base SH | 08W | UNSE | Scoping/Scoped | 0.32 | 10.66 | - | 10.98 | 10.98 | - | LP | Region 4 - Central Coast | Solvang | SANTA BARBARA | 35.6126 | -120.1756 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | 99% | CWSP - 2023 ICUG | Tier 2 | 303
35286270 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2428 | - | - | 1.2428 | - | 1.2428 | NV | Region 2 - North East | Paradise | BUTTE | 39.7573 | -121.6264 |  | 2257 | 0.0039747 |  | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 304
35144489 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.1733 | - | - | 2.1733 | - | 2.1733 | NV | Region 2 - North East | Magalia | BUTTE | 39.8201 | -121.6017 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 305
35112126 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.1095 | - | - | 2.1095 | - | 2.1095 | NV | Region 2 - North East | Paradise | BUTTE | 39.7813 | -121.603 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 306
35246595 | Community Rebuild | 08W | ESTS | Estimating | 5.8735 | - | - | 5.8735 | - | 5.8735 | NV | Region 2 - North East | Paradise | BUTTE | 39.7778 | -121.6061 |  | 2933 | 3.0817e-05 |  | 809 | 0.0030677 | 99% | Butte Rebuild | Tier 2 | 307
35127360 | Community Rebuild | 95F | UNSE | Scoping/Scoped | 1.3352 | - | - | 1.3352 | - | 1.3352 | NV | Region 2 - North East | Paradise | BUTTE | 39.7463 | -121.6437 |  | 2950 | 2.5314e-05 |  | 875 | 0.0027476 | 99% | Butte Rebuild | Tier 3 | 308
35144487 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4989 | - | - | 2.4989 | - | 2.4989 | NV | Region 2 - North East | Magalia | BUTTE | 39.8181 | -121.5952 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 309
35144488 | Community Rebuild | 95F | ESTS ERDY | Estimating | 3.5227 | - | - | 3.5227 | - | 3.5227 | NV | Region 2 - North East | Magalia | BUTTE | 39.8148 | -121.6065 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 310
35244220 | Community Rebuild | 08W | ESTS ERDY | Estimating | 2.5284 | - | - | 2.5284 | - | 2.5284 | NV | Region 2 - North East | Paradise | BUTTE | 39.7553 | -121.6287 |  | 2257 | 0.0039747 |  | 503 | 0.0053751 | 99% | Butte Rebuild | Tier 2 | 311
35246594 | Community Rebuild | 08W | UNSE | Estimating | 3.7216 | - | - | 3.7216 | - | 3.7216 | NV | Region 2 - North East | Paradise | BUTTE | 39.741 | -121.6219 |  | 2906 | 4.4268e-05 |  | 497 | 0.0054934 | 99% | Butte Rebuild | Tier 2 | 312
35144490 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.4928 | - | - | 2.4928 | - | 2.4928 | NV | Region 2 - North East | Magalia | BUTTE | 39.8242 | -121.5995 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 313
35144491 | Community Rebuild | 95F | ESTS ERDY | Estimating | 2.7557 | - | - | 2.7557 | - | 2.7557 | NV | Region 2 - North East | Magalia | BUTTE | 39.8259 | -121.5971 |  | 2849 | 0.00016422 |  | 159 | 0.014996 | 99% | Butte Rebuild | Tier 2 | 314
35144492 | Community Rebuild | 95F | ESTS ERDY | Estimating | 1.2159 | - | - | 1.2159 | - | 1.2159 | NV | Region 2 - North East | Magalia | BUTTE | 39.8227 | -121.5947 |  | 2211 | 0.0048412 |  | 1124 | 0.0018782 | 99% | Butte Rebuild | Tier 2 | 315
35246592 | Community Rebuild | 08W | ESTS ERDY | Estimating | 6.2074 | - | - | 6.2074 | - | 6.2074 | NV | Region 2 - North East | Paradise | BUTTE | 39.7412 | -121.6079 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | 99% | Butte Rebuild | Tier 2 | 316
35244027 | Community Rebuild | 08W | ESTS ERDY | Estimating | 5.483 | - | - | 5.483 | - | 5.483 | NV | Region 2 - North East | Paradise | BUTTE | 39.8026 | -121.5798 |  | 2141 | 0.0062243 |  | 755 | 0.0033502 | 99% | Butte Rebuild | Tier 2 | 317
35234527 | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | - | - | 0.075947 | - | 0.075947 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 318
35234528 | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | - | - | 0.035985 | - | 0.035985 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 319
35234529 | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | - | - | 0.70833 | - | 0.70833 | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.8274 |  | 2010 | 0.0088541 |  | 128 | 0.016217 | 99% | PSPS | Tier 3 | 320
35277935 | Base SH | 08W | ESTS | Estimating | 0.092992 | - | - | 0.092992 | - | 0.092992 | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0313 | -119.4396 |  | 274 | 0.22501 |  | 614 | 0.0043344 | 99% | CWSP | Tier 2 | 321
35280505 | Other | 30A | ESTS | Estimating | 0.37879 | - | - | 0.37879 | - | 0.37879 | NV | Region 2 - North East | Shasta | Shasta | 40.5947 | -122.4862 |  | 1614 | 0.022607 |  | 43 | 0.023649 | 99% | Other | Tier 3 | 322
35294729 | Base SH | 08W | UNSE | Scoping/Scoped | 3.4089 | - | - | 3.4089 | - | 3.4089 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7479 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 323
35294730 | Base SH | 08W | UNSE | Scoping/Scoped | 2.8409 | - | - | 2.8409 | - | 2.8409 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9685 | -121.8246 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 324
35325224 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2799 | 0.05 | - | 3.3299 | - | 3.3299 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 41.0088 | -121.7129 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 325
35325225 | Base SH | 08W | UNSE | Scoping/Scoped | 3.2449 | - | - | 3.2449 | - | 3.2449 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9729 | -121.7814 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 326
35325226 | Base SH | 08W | UNSE | Scoping/Scoped | 4.218 | - | - | 4.218 | - | 4.218 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9868 | -121.8481 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | 99% | CWSP | Tier 2 | 327
35294728 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4201 | - | - | 2.4201 | - | 2.4201 | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9982 | -121.7478 |  | 1816 | 0.01407 |  | 326 | 0.0086689 | 99% | CWSP | Tier 2 | 328
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018365 | - | - | 0.018365 | - | 0.018365 | SI | Region 2 - North East | ALLEGHANY | Nevada | 39.364 | -120.7923 |  | 3054 | 1.0723e-05 |  | 4 | 0.066078 | 99% | V3 Tranche 1 | Tier 3 | 329
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.7026 | - | - | 21.7026 | - | 21.7026 | SI | Region 2 - North East | ALLEGHANY | Sierra | 39.4655 | -120.8449 |  | 1700 | 0.018204 |  | 41 | 0.023951 | 99% | V3 Tranche 1 | Tier 3 | 330
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4687 | - | - | 11.4687 | - | 11.4687 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8524 | -122.3324 |  | 1674 | 0.019836 |  | 210 | 0.012094 | 99% | V3 Tranche 1 | Tier 2 | 331
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.278 | - | - | 30.278 | - | 30.278 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8489 | -122.3313 |  | 1722 | 0.017574 |  | 247 | 0.010915 | 99% | V3 Tranche 1 | Tier 3 | 332
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.0657 | - | - | 11.0657 | - | 11.0657 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8937 | -122.382 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | 99% | V3 Tranche 1 | Tier 2 | 333
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.1874 | - | - | 11.1874 | - | 11.1874 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8995 | -122.3862 |  | 2407 | 0.002519 |  | 91 | 0.018782 | 99% | V3 Tranche 1 | Tier 2 | 334
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.622 | - | - | 9.622 | - | 9.622 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8916 | -122.3764 |  | 1791 | 0.014748 |  | 143 | 0.015772 | 99% | V3 Tranche 1 | Tier 3 | 335
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9879 | - | - | 1.9879 | - | 1.9879 | NV | Region 2 - North East | LAKEHEAD | Shasta | 40.8945 | -122.3808 |  | 2207 | 0.0049349 |  | 94 | 0.0187 | 99% | V3 Tranche 1 | Tier 2 | 336
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.4383 | - | - | 34.4383 | - | 34.4383 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7391 | -120.6681 |  | 1284 | 0.041392 |  | 124 | 0.016427 | 99% | V3 Tranche 1 | Tier 3 | 337
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.021845 | - | - | 0.021845 | - | 0.021845 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7721 | -120.7002 |  | 1657 | 0.020643 |  | 386 | 0.0072633 | 99% | V3 Tranche 1 | Tier 3 | 338
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9275 | - | - | 31.9275 | - | 31.9275 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7652 | -120.7045 |  | 1934 | 0.010689 |  | 197 | 0.012828 | 99% | V3 Tranche 1 | Tier 3 | 339
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1021 | - | - | 5.1021 | - | 5.1021 | SI | Region 2 - North East | CAMINO | El Dorado | 38.7396 | -120.6772 |  | 1422 | 0.032289 |  | 30 | 0.025967 | 99% | V3 Tranche 1 | Tier 2 | 340
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.136 | - | - | 15.136 | - | 15.136 | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 |  | 178 | 0.2712 |  | 32 | 0.025831 | 99% | V3 Tranche 1 | Tier 3 | 341
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.5084 | - | - | 28.5084 | - | 28.5084 | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6607 |  | 1505 | 0.027532 |  | 63 | 0.020812 | 99% | V3 Tranche 1 | Tier 3 | 342
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 51.0474 | - | - | 51.0474 | - | 51.0474 | SI | Region 2 - North East | Camino | El Dorado | 38.7371 | -120.6759 |  | 644 | 0.12006 |  | 132 | 0.01606 | 99% | V3 Tranche 1 | Tier 3 | 343
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.078916 | - | - | 0.078916 | - | 0.078916 | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6765 |  | 644 | 0.12006 |  | 2 | 0.090117 | 99% | V3 Tranche 1 | Tier 2 | 344
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.2757 | - | - | 19.2757 | - | 19.2757 | NV | Region 2 - North East | BERRY CREEK | Butte | 39.6444 | -121.4314 |  | 1288 | 0.040961 |  | 267 | 0.010152 | 99% | V3 Tranche 1 | Tier 3 | 345
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.6217 | - | - | 13.6217 | - | 13.6217 | NV | Region 2 - North East | CONCOW | Butte | 39.6773 | -121.4916 |  | 865 | 0.084888 |  | 187 | 0.013302 | 99% | V3 Tranche 1 | Tier 3 | 346
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.0546 | - | - | 18.0546 | - | 18.0546 | SI | Region 2 - North East | ALTA | Placer | 39.2148 | -120.8091 |  | 1526 | 0.026396 |  | 20 | 0.02949 | 99% | V3 Tranche 1 | Tier 3 | 347
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.5031 | - | - | 42.5031 | - | 42.5031 | SI | Region 2 - North East | ALTA | Placer | 39.2147 | -120.8094 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | 99% | V3 Tranche 1 | Tier 3 | 348
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 55.3006 | - | - | 55.3006 | - | 55.3006 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.2129 | -121.0129 |  | 1649 | 0.021168 |  | 234 | 0.011407 | 99% | V3 Tranche 1 | Tier 3 | 349
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.0096 | - | - | 12.0096 | - | 12.0096 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1995 | -121.0171 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | 99% | V3 Tranche 1 | Tier 3 | 350
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.1704 | - | - | 28.1704 | - | 28.1704 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1909 | -120.9999 |  | 1154 | 0.052211 |  | 266 | 0.010208 | 99% | V3 Tranche 1 | Tier 3 | 351
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 70.6282 | - | - | 70.6282 | - | 70.6282 | SI | Region 2 - North East | GRASS VALLEY | Nevada | 39.1911 | -120.9965 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | 99% | V3 Tranche 1 | Tier 3 | 352
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.2781 | - | - | 33.2781 | - | 33.2781 | NV | Region 2 - North East | STORRIE | Plumas | 39.9109 | -121.3276 |  | 378 | 0.1873 |  | 45 | 0.023178 | 99% | V3 Tranche 1 | Tier 3 | 353
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.9616 | - | - | 15.9616 | - | 15.9616 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6088 | -122.591 |  | 1093 | 0.057148 |  | 134 | 0.016019 | 99% | V3 Tranche 1 | Tier 3 | 354
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.64 | - | - | 1.64 | - | 1.64 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6222 | -122.679 |  | 565 | 0.14151 |  | 480 | 0.0057895 | 99% | V3 Tranche 1 | Tier 3 | 355
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.636 | - | - | 15.636 | - | 15.636 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5894 | -122.6079 |  | 683 | 0.11348 |  | 428 | 0.006597 | 99% | V3 Tranche 1 | Tier 3 | 356
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.5931 | - | - | 3.5931 | - | 3.5931 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.6577 | -122.5951 |  | 614 | 0.12786 |  | 389 | 0.0071797 | 99% | V3 Tranche 1 | Tier 3 | 357
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3819 | - | - | 9.3819 | - | 9.3819 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5953 | -122.6022 |  | 1005 | 0.066852 |  | 105 | 0.017566 | 99% | V3 Tranche 1 | Tier 3 | 358
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 31.9467 | - | - | 31.9467 | - | 31.9467 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5803 | -122.5979 |  | 833 | 0.088841 |  | 299 | 0.0094322 | 99% | V3 Tranche 1 | Tier 3 | 359
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.518 | - | - | 4.518 | - | 4.518 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.6318 | -122.6741 |  | 406 | 0.17857 |  | 589 | 0.0045153 | 99% | V3 Tranche 1 | Tier 3 | 360
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8478 | - | - | 11.8478 | - | 11.8478 | NB | Region 1 - North Coast | CALISTOGA | Sonoma | 38.5599 | -122.6285 |  | 833 | 0.088841 |  | 411 | 0.006798 | 99% | V3 Tranche 1 | Tier 3 | 361
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.10844 | - | - | 0.10844 | - | 0.10844 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.592 | -122.5786 |  | 55 | 0.40561 |  | 1636 | 0.00082073 | 99% | V3 Tranche 1 | Tier 2 | 362
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.8011 | - | - | 5.8011 | - | 5.8011 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5637 | -122.5595 |  | 1477 | 0.029373 |  | 24 | 0.027222 | 99% | V3 Tranche 1 | Tier 3 | 363
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.052643 | - | - | 0.052643 | - | 0.052643 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5686 | -122.5417 |  | 1014 | 0.065722 |  | 78 | 0.019531 | 99% | V3 Tranche 1 | Tier 3 | 364
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.1129 | - | - | 0.1129 | - | 0.1129 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5762 | -122.5825 |  | 2828 | 0.00021298 |  | 382 | 0.0073271 | 99% | V3 Tranche 1 | Tier 2 | 365
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7313 | - | - | 0.7313 | - | 0.7313 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5787 | -122.5826 |  | 3098 | 8.707e-06 |  | 843 | 0.0029014 | 99% | V3 Tranche 1 | Tier 3 | 366
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9317 | - | - | 6.9317 | - | 6.9317 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5859 | -122.5714 |  | 1477 | 0.029373 |  | 769 | 0.0032407 | 99% | V3 Tranche 1 | Tier 3 | 367
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.0843 | - | - | 7.0843 | - | 7.0843 | NB | Region 1 - North Coast | CALISTOGA | Napa | 38.5678 | -122.5383 |  | 1624 | 0.022338 |  | 534 | 0.0050695 | 99% | V3 Tranche 1 | Tier 3 | 368
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.018445 | - | - | 0.018445 | - | 0.018445 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8059 | -122.8081 |  | 2 | 1.8786 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 369
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.057948 | - | - | 0.057948 | - | 0.057948 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7727 | -122.7295 |  | 2308 | 0.0033555 |  | 3 | 0.068443 | 99% | V3 Tranche 1 | Tier 3 | 370
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.0767 | - | - | 5.0767 | - | 5.0767 | SO | Region 1 - North Coast | GEYSERVILLE | Lake | 38.7658 | -122.7076 |  | 1049 | 0.061428 |  | 238 | 0.011276 | 99% | V3 Tranche 1 | Tier 3 | 371
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3133 | - | - | 33.3133 | - | 33.3133 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8154 | -122.8003 |  | 334 | 0.19817 |  | 169 | 0.014299 | 99% | V3 Tranche 1 | Tier 3 | 372
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.010654 | - | - | 0.010654 | - | 0.010654 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8266 | -122.7997 |  | 31 | 0.50979 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 373
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.014112 | - | - | 0.014112 | - | 0.014112 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8264 | -122.7997 |  | 32 | 0.50979 |  | 11159 |  | 99% | V3 Tranche 1 | Tier 3 | 374
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.3029 | - | - | 2.3029 | - | 2.3029 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.8265 | -122.8041 |  | 97 | 0.34896 |  | 543 | 0.0049805 | 99% | V3 Tranche 1 | Tier 3 | 375
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.6798 | - | - | 4.6798 | - | 4.6798 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.815 | -122.8021 |  | 297 | 0.21399 |  | 79 | 0.019348 | 99% | V3 Tranche 1 | Tier 3 | 376
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.58901 | - | - | 0.58901 | - | 0.58901 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9412 | -121.9576 |  | 1321 | 0.038704 |  | 471 | 0.0058873 | 99% | V3 Tranche 1 | Tier 2 | 377
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.7558 | - | - | 14.7558 | - | 14.7558 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.8797 | -121.8678 |  | 377 | 0.18755 |  | 223 | 0.011731 | 99% | V3 Tranche 1 | Tier 3 | 378
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.79978 | - | - | 0.79978 | - | 0.79978 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9332 | -121.9419 |  | 2561 | 0.0014894 |  | 100 | 0.018211 | 99% | V3 Tranche 1 | Tier 3 | 379
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 33.3146 | - | - | 33.3146 | - | 33.3146 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9245 | -121.9125 |  | 2561 | 0.0014894 |  | 115 | 0.016899 | 99% | V3 Tranche 1 | Tier 3 | 380
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.6045 | - | - | 9.6045 | - | 9.6045 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9039 | -121.8741 |  | 377 | 0.18755 |  | 15 | 0.034099 | 99% | V3 Tranche 1 | Tier 3 | 381
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.37986 | - | - | 0.37986 | - | 0.37986 | DI | Region 3 - Bay Area | CONCORD | Contra Costa | 37.9439 | -121.9691 |  | 2561 | 0.0014894 |  | 1654 | 0.00080781 | 99% | V3 Tranche 1 | Tier 2 | 382
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6612 | - | - | 3.6612 | - | 3.6612 | HB | Region 1 - North Coast | LAKEPORT | Lake | 39.0183 | -122.917 |  | 239 | 0.23862 |  | 200 | 0.012549 | 99% | V3 Tranche 1 | Tier 2 | 383
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.052 | - | - | 17.052 | - | 17.052 | NV | Region 2 - North East | CORNING | Tehama | 39.9967 | -122.4058 |  | 549 | 0.1444 |  | 615 | 0.0043341 | 99% | V3 Tranche 1 | Tier 2 | 384
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 28.8387 | - | - | 28.8387 | - | 28.8387 | NV | Region 2 - North East | CORNING | Tehama | 40.0157 | -122.4005 |  | 986 | 0.068983 |  | 194 | 0.012991 | 99% | V3 Tranche 1 | Tier 2 | 385
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.96092 | - | - | 0.96092 | - | 0.96092 | NV | Region 2 - North East | OROVILLE | Butte | 39.8269 | -121.4092 |  | 2890 | 6.9083e-05 |  | 40 | 0.023964 | 99% | V3 Tranche 1 | Tier 3 | 386
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.54712 | - | - | 0.54712 | - | 0.54712 | NV | Region 2 - North East | OROVILLE | Butte | 39.8308 | -121.4091 |  | 33 | 0.50291 |  | 31 | 0.025946 | 99% | V3 Tranche 1 | Tier 3 | 387
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.7057 | - | - | 2.7057 | - | 2.7057 | SI | Region 2 - North East | ALTA | Placer | 39.2564 | -120.7671 |  | 942 | 0.074456 |  | 103 | 0.018102 | 99% | V3 Tranche 1 | Tier 3 | 388
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8641 | - | - | 11.8641 | - | 11.8641 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7617 | -120.5776 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | 99% | V3 Tranche 1 | Tier 3 | 389
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.31289 | - | - | 0.31289 | - | 0.31289 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7602 | -120.5769 |  | 3014 | 1.4503e-05 |  | 195 | 0.012963 | 99% | V3 Tranche 1 | Tier 3 | 390
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.077102 | - | - | 0.077102 | - | 0.077102 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7539 | -120.5747 |  | 2000 | 0.0090446 |  | 121 | 0.016629 | 99% | V3 Tranche 1 | Tier 3 | 391
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.9464 | - | - | 3.9464 | - | 3.9464 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7649 | -120.5894 |  | 2469 | 0.0020868 |  | 780 | 0.0031904 | 99% | V3 Tranche 1 | Tier 3 | 392
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.8959 | - | - | 6.8959 | - | 6.8959 | SI | Region 2 - North East | POLLOCK PINES | El Dorado | 38.7935 | -120.6192 |  | 2732 | 0.00051722 |  | 278 | 0.0099516 | 99% | V3 Tranche 1 | Tier 3 | 393
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.2319 | - | - | 6.2319 | - | 6.2319 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3604 | -120.7525 |  | 1720 | 0.017625 |  | 288 | 0.0096899 | 99% | V3 Tranche 1 | Tier 2 | 394
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3872 | - | - | 29.3872 | - | 29.3872 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3633 | -120.6486 |  | 1571 | 0.0243 |  | 355 | 0.0078671 | 99% | V3 Tranche 1 | Tier 2 | 395
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.0949 | - | - | 15.0949 | - | 15.0949 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3639 | -120.6467 |  | 1548 | 0.025302 |  | 62 | 0.020861 | 99% | V3 Tranche 1 | Tier 2 | 396
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.1029 | - | - | 29.1029 | - | 29.1029 | ST | Region 5 - Central Valley | JACKSON | Amador | 38.3314 | -120.6731 |  | 1088 | 0.05741 |  | 251 | 0.010795 | 99% | V3 Tranche 1 | Tier 2 | 397
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.211 | - | - | 7.211 | - | 7.211 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3793 | -120.638 |  | 2349 | 0.0030208 |  | 118 | 0.016781 | 99% | V3 Tranche 1 | Tier 2 | 398
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7233 | - | - | 27.7233 | - | 27.7233 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0162 | -120.8351 |  | 1865 | 0.012496 |  | 179 | 0.013637 | 99% | V3 Tranche 1 | Tier 3 | 399
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.4919 | - | - | 14.4919 | - | 14.4919 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0474 | -120.7852 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | 99% | V3 Tranche 1 | Tier 3 | 400
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.6369 | - | - | 14.6369 | - | 14.6369 | SI | Region 2 - North East | FORESTHILL | Placer | 38.9929 | -120.8827 |  | 2270 | 0.0037623 |  | 114 | 0.01695 | 99% | V3 Tranche 1 | Tier 3 | 401
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.3473 | - | - | 11.3473 | - | 11.3473 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0193 | -120.8302 |  | 2058 | 0.0077431 |  | 232 | 0.011424 | 99% | V3 Tranche 1 | Tier 3 | 402
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 34.8558 | - | - | 34.8558 | - | 34.8558 | SI | Region 2 - North East | FORESTHILL | Placer | 39.0198 | -120.8509 |  | 1301 | 0.040196 |  | 97 | 0.018495 | 99% | V3 Tranche 1 | Tier 3 | 403
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.25572 | - | - | 0.25572 | - | 0.25572 | SO | Region 1 - North Coast | GEYSERVILLE | Sonoma | 38.7004 | -122.9575 |  | 2170 | 0.0056711 |  | 1375 | 0.0011879 | 99% | V3 Tranche 1 | Tier 2 | 404
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.037341 | - | - | 0.037341 | - | 0.037341 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.937 | -122.609 |  | 3186 | 6.536e-06 |  | 163 | 0.014683 | 99% | V3 Tranche 1 | Tier 2 | 405
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 17.7877 | - | - | 17.7877 | - | 17.7877 | HB | Region 1 - North Coast | CLEARLAKE | Lake | 38.9822 | -122.6031 |  | 27 | 0.5487 |  | 29 | 0.026126 | 99% | V3 Tranche 1 | Tier 3 | 406
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.6035 | - | - | 7.6035 | - | 7.6035 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8802 | -122.6125 |  | 626 | 0.12376 |  | 582 | 0.0045905 | 99% | V3 Tranche 1 | Tier 2 | 407
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 21.1732 | - | - | 21.1732 | - | 21.1732 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8967 | -122.5542 |  | 181 | 0.26975 |  | 156 | 0.015099 | 99% | V3 Tranche 1 | Tier 2 | 408
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.8369 | - | - | 9.8369 | - | 9.8369 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.8705 | -122.6229 |  | 626 | 0.12376 |  | 144 | 0.015697 | 99% | V3 Tranche 1 | Tier 2 | 409
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.0855 | - | - | 9.0855 | - | 9.0855 | HB | Region 1 - North Coast | LOWER LAKE | Lake | 38.9079 | -122.5968 |  | 461 | 0.16238 |  | 270 | 0.010079 | 99% | V3 Tranche 1 | Tier 2 | 410
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.29571 | - | - | 0.29571 | - | 0.29571 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.677 | -119.7768 |  | 16 | 0.68656 |  | 12 | 0.038638 | 99% | V3 Tranche 1 | Tier 2 | 411
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.8871 | - | - | 19.8871 | - | 19.8871 | YO | Region 5 - Central Valley | EL PORTAL | Mariposa | 37.6649 | -119.8411 |  | 555 | 0.14347 |  | 10 | 0.039297 | 99% | V3 Tranche 1 | Tier 2 | 412
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3548 | - | - | 9.3548 | - | 9.3548 | SA | Region 2 - North East | GREEN VALLEY | Solano | 38.2496 | -122.1606 |  | 739 | 0.104 |  | 313 | 0.0089196 | 99% | V3 Tranche 1 | Tier 2 | 413
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.8683 | - | - | 2.8683 | - | 2.8683 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.3482 | -121.3219 |  | 2006 | 0.0089147 |  | 462 | 0.0060529 | 99% | V3 Tranche 1 | Tier 2 | 414
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.4274 | - | - | 37.4274 | - | 37.4274 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2804 | -121.3064 |  | 1509 | 0.027281 |  | 178 | 0.013726 | 99% | V3 Tranche 1 | Tier 2 | 415
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 38.1684 | - | - | 38.1684 | - | 38.1684 | CC | Region 4 - Central Coast | BITTERWATER | San Benito | 36.3875 | -121.0045 |  | N/A (HFRA, not in v2) | - |  | 193 | 0.012994 | 99% | V3 Tranche 1 | HFRA | 416
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.182 | - | - | 15.182 | - | 15.182 | CC | Region 4 - Central Coast | GREENFIELD | Monterey | 36.2789 | -121.3033 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | 99% | V3 Tranche 1 | Tier 2 | 417
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.6522 | - | - | 24.6522 | - | 24.6522 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5251 | -119.9181 |  | 679 | 0.11431 |  | 126 | 0.016323 | 99% | V3 Tranche 1 | Tier 3 | 418
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.4258 | - | - | 23.4258 | - | 23.4258 | YO | Region 5 - Central Valley | MIDPINES | Mariposa | 37.5697 | -119.942 |  | 700 | 0.11205 |  | 199 | 0.012689 | 99% | V3 Tranche 1 | Tier 3 | 419
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.13992 | - | - | 0.13992 | - | 0.13992 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4872 | -119.9618 |  | 10 | 0.77248 |  | 515 | 0.0052627 | 99% | V3 Tranche 1 | Tier 2 | 420
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.070448 | - | - | 0.070448 | - | 0.070448 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4632 | -119.9482 |  | 3264 | 5.0408e-06 |  | 464 | 0.0059574 | 99% | V3 Tranche 1 | Tier 2 | 421
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65665 | - | - | 0.65665 | - | 0.65665 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.4861 | -119.9697 |  | 587 | 0.13461 |  | 312 | 0.0089197 | 99% | V3 Tranche 1 | Tier 2 | 422
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0221 | - | - | 1.0221 | - | 1.0221 | YO | Region 5 - Central Valley | MARIPOSA | Mariposa | 37.5044 | -120.0079 |  | 35 | 0.47165 |  | 77 | 0.019783 | 99% | V3 Tranche 1 | Tier 2 | 423
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76835 | - | - | 0.76835 | - | 0.76835 | HB | Region 1 - North Coast | COBB | Lake | 38.8237 | -122.7214 |  | 474 | 0.15935 |  | 258 | 0.010457 | 99% | V3 Tranche 1 | Tier 3 | 424
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.1567 | - | - | 1.1567 | - | 1.1567 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7312 | -122.6235 |  | 915 | 0.078235 |  | 56 | 0.021686 | 99% | V3 Tranche 1 | Tier 3 | 425
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3963 | - | - | 4.3963 | - | 4.3963 | HB | Region 1 - North Coast | COBB | Lake | 38.8481 | -122.7562 |  | 328 | 0.19983 |  | 38 | 0.024501 | 99% | V3 Tranche 1 | Tier 3 | 426
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.6615 | - | - | 2.6615 | - | 2.6615 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.695 | -122.5975 |  | 468 | 0.1603 |  | 175 | 0.013904 | 99% | V3 Tranche 1 | Tier 3 | 427
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3985 | - | - | 1.3985 | - | 1.3985 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7253 | -122.619 |  | 314 | 0.20636 |  | 99 | 0.018456 | 99% | V3 Tranche 1 | Tier 3 | 428
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.4605 | - | - | 1.4605 | - | 1.4605 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7522 | -122.6207 |  | 450 | 0.16479 |  | 174 | 0.013914 | 99% | V3 Tranche 1 | Tier 2 | 429
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.4241 | - | - | 26.4241 | - | 26.4241 | HB | Region 1 - North Coast | COBB | Lake | 38.8291 | -122.7295 |  | 328 | 0.19983 |  | 182 | 0.013549 | 99% | V3 Tranche 1 | Tier 3 | 430
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0487 | - | - | 1.0487 | - | 1.0487 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7628 | -122.6133 |  | 38 | 0.46769 |  | 673 | 0.0038943 | 99% | V3 Tranche 1 | Tier 3 | 431
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.9927 | - | - | 10.9927 | - | 10.9927 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7249 | -122.6186 |  | 468 | 0.1603 |  | 13 | 0.035184 | 99% | V3 Tranche 1 | Tier 3 | 432
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 26.0007 | - | - | 26.0007 | - | 26.0007 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7577 | -122.6359 |  | 474 | 0.15935 |  | 102 | 0.018129 | 99% | V3 Tranche 1 | Tier 3 | 433
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.707 | - | - | 1.707 | - | 1.707 | HB | Region 1 - North Coast | COBB | Lake | 38.8266 | -122.727 |  | 2060 | 0.0076984 |  | 211 | 0.01209 | 99% | V3 Tranche 1 | Tier 3 | 434
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5662 | - | - | 18.5662 | - | 18.5662 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7462 | -122.6206 |  | 314 | 0.20636 |  | 185 | 0.013349 | 99% | V3 Tranche 1 | Tier 3 | 435
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9629 | - | - | 1.9629 | - | 1.9629 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7537 | -122.6111 |  | 86 | 0.36174 |  | 935 | 0.002498 | 99% | V3 Tranche 1 | Tier 3 | 436
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.65224 | - | - | 0.65224 | - | 0.65224 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7523 | -122.6178 |  | 3073 | 9.669e-06 |  | 146 | 0.015654 | 99% | V3 Tranche 1 | Tier 2 | 437
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3099 | - | - | 4.3099 | - | 4.3099 | HB | Region 1 - North Coast | MIDDLETOWN | Lake | 38.7722 | -122.6244 |  | 86 | 0.36174 |  | 160 | 0.014882 | 99% | V3 Tranche 1 | Tier 3 | 438
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.995 | - | - | 13.995 | - | 13.995 | SI | Region 2 - North East | GEOGETOWN | El Dorado | 38.8995 | -120.8545 |  | 2212 | 0.0048403 |  | 275 | 0.009997 | 99% | V3 Tranche 1 | Tier 3 | 439
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.104 | - | - | 27.104 | - | 27.104 | SI | Region 2 - North East | COOL | El Dorado | 38.8932 | -120.9965 |  | 169 | 0.27537 |  | 401 | 0.0069368 | 99% | V3 Tranche 1 | Tier 2 | 440
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6797 | - | - | 10.6797 | - | 10.6797 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.9 | -120.9074 |  | 1706 | 0.018043 |  | 165 | 0.014598 | 99% | V3 Tranche 1 | Tier 2 | 441
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.3111 | - | - | 18.3111 | - | 18.3111 | SI | Region 2 - North East | GREENWOOD | El Dorado | 38.8958 | -120.879 |  | 1212 | 0.046937 |  | 177 | 0.013764 | 99% | V3 Tranche 1 | Tier 3 | 442
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.6043 | - | - | 10.6043 | - | 10.6043 | NV | Region 2 - North East | CHICO | Butte | 39.7784 | -121.7318 |  | 73 | 0.37815 |  | 155 | 0.015172 | 99% | V3 Tranche 1 | Tier 3 | 443
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5667 | - | - | 13.5667 | - | 13.5667 | NV | Region 2 - North East | FOREST RANCH | Butte | 39.839 | -121.7019 |  | 1043 | 0.062015 |  | 37 | 0.024521 | 99% | V3 Tranche 1 | Tier 3 | 444
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.8427 | - | - | 3.8427 | - | 3.8427 | NV | Region 2 - North East | CHICO | Butte | 39.7393 | -121.7854 |  | 73 | 0.37815 |  | 926 | 0.0025265 | 99% | V3 Tranche 1 | Tier 2 | 445
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.098 | - | - | 6.098 | - | 6.098 | NV | Region 2 - North East | CHICO | Butte | 39.7911 | -121.7217 |  | 1045 | 0.061762 |  | 290 | 0.0096296 | 99% | V3 Tranche 1 | Tier 3 | 446
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.7141 | - | - | 30.7141 | - | 30.7141 | YO | Region 5 - Central Valley | AHWAHNEE | Madera | 37.3399 | -119.6754 |  | 541 | 0.14657 |  | 172 | 0.014056 | 99% | V3 Tranche 1 | Tier 2 | 447
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.15233 | - | - | 0.15233 | - | 0.15233 | YO | Region 5 - Central Valley | OAKHURST | Madera | 37.3219 | -119.6344 |  | 847 | 0.086583 |  | 1208 | 0.0016106 | 99% | V3 Tranche 1 | Tier 3 | 448
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.4642 | - | - | 16.4642 | - | 16.4642 | NV | Region 2 - North East | SHASTA LAKE | Shasta | 40.6653 | -122.3866 |  | 1773 | 0.015387 |  | 64 | 0.0208 | 99% | V3 Tranche 1 | Tier 2 | 449
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1749 | - | - | 20.1749 | - | 20.1749 | NV | Region 2 - North East | MAGALIA | Butte | 39.8542 | -121.6058 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | 99% | V3 Tranche 1 | Tier 3 | 450
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.3261 | - | - | 20.3261 | - | 20.3261 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | 99% | V3 Tranche 1 | Tier 3 | 451
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 18.5511 | - | - | 18.5511 | - | 18.5511 | NV | Region 2 - North East | MAGALIA | Butte | 39.8582 | -121.6134 |  | 2440 | 0.0022675 |  | 150 | 0.015441 | 99% | V3 Tranche 1 | Tier 3 | 452
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.1705 | - | - | 3.1705 | - | 3.1705 | NV | Region 2 - North East | MAGALIA | Butte | 39.872 | -121.612 |  | 1287 | 0.040994 |  | 129 | 0.016201 | 99% | V3 Tranche 1 | Tier 3 | 453
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.3248 | - | - | 8.3248 | - | 8.3248 | NV | Region 2 - North East | MAGALIA | Butte | 39.8901 | -121.5778 |  | 1441 | 0.031032 |  | 181 | 0.013572 | 99% | V3 Tranche 1 | Tier 3 | 454
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.8784 | - | - | 52.8784 | - | 52.8784 | NV | Region 2 - North East | MAGALIA | Butte | 39.8872 | -121.6653 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | 99% | V3 Tranche 1 | Tier 3 | 455
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.8338 | - | - | 13.8338 | - | 13.8338 | NV | Region 2 - North East | MAGALIA | Butte | 39.8705 | -121.6503 |  | 1667 | 0.020219 |  | 140 | 0.015891 | 99% | V3 Tranche 1 | Tier 3 | 456
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.1864 | - | - | 20.1864 | - | 20.1864 | NV | Region 2 - North East | MAGALIA | Butte | 39.8877 | -121.6654 |  | 2763 | 0.000401 |  | 61 | 0.020869 | 99% | V3 Tranche 1 | Tier 3 | 457
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.714 | - | - | 2.714 | - | 2.714 | NV | Region 2 - North East | MAGALIA | Butte | 39.8716 | -121.6108 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | 99% | V3 Tranche 1 | Tier 3 | 458
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.9289 | - | - | 1.9289 | - | 1.9289 | NV | Region 2 - North East | PARADISE | Butte | 39.7704 | -121.6138 |  | 2910 | 4.2503e-05 |  | 26 | 0.026975 | 99% | V3 Tranche 1 | Tier 3 | 459
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.3679 | - | - | 7.3679 | - | 7.3679 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4553 | -121.053 |  | 1710 | 0.017864 |  | 52 | 0.02211 | 99% | V3 Tranche 1 | Tier 3 | 460
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.588 | - | - | 10.588 | - | 10.588 | SI | Region 2 - North East | CAMPTONVILLE | Yuba | 39.4519 | -121.0542 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | 99% | V3 Tranche 1 | Tier 3 | 461
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.605 | - | - | 24.605 | - | 24.605 | SI | Region 2 - North East | NORTH SAN JUAN | Sierra | 39.4381 | -120.9961 |  | 1484 | 0.029034 |  | 116 | 0.016874 | 99% | V3 Tranche 1 | Tier 3 | 462
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.2062 | - | - | 5.2062 | - | 5.2062 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.414 | -120.6754 |  | 2455 | 0.0021716 |  | 310 | 0.0089413 | 99% | V3 Tranche 1 | Tier 2 | 463
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.187 | - | - | 15.187 | - | 15.187 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4069 | -120.6707 |  | 1764 | 0.015763 |  | 147 | 0.015597 | 99% | V3 Tranche 1 | Tier 2 | 464
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 49.4644 | - | - | 49.4644 | - | 49.4644 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4151 | -120.6853 |  | 1768 | 0.015534 |  | 410 | 0.0068091 | 99% | V3 Tranche 1 | Tier 2 | 465
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.4439 | - | - | 11.4439 | - | 11.4439 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.3852 | -120.6921 |  | 1943 | 0.010365 |  | 240 | 0.011105 | 99% | V3 Tranche 1 | Tier 2 | 466
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.3432 | - | - | 5.3432 | - | 5.3432 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | 99% | V3 Tranche 1 | Tier 2 | 467
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.6574 | - | - | 20.6574 | - | 20.6574 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4739 | -120.6268 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | 99% | V3 Tranche 1 | Tier 3 | 468
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 37.38 | - | - | 37.38 | - | 37.38 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4143 | -120.6541 |  | 1602 | 0.023045 |  | 303 | 0.0092748 | 99% | V3 Tranche 1 | Tier 3 | 469
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.82 | - | - | 11.82 | - | 11.82 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4102 | -120.6518 |  | 1592 | 0.023346 |  | 139 | 0.015893 | 99% | V3 Tranche 1 | Tier 3 | 470
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.4813 | - | - | 13.4813 | - | 13.4813 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4535 | -120.5298 |  | 2447 | 0.002235 |  | 233 | 0.011408 | 99% | V3 Tranche 1 | Tier 3 | 471
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 42.9356 | - | - | 42.9356 | - | 42.9356 | ST | Region 5 - Central Valley | VOLCANO | Amador | 38.4612 | -120.6579 |  | 1271 | 0.042249 |  | 131 | 0.016072 | 99% | V3 Tranche 1 | Tier 2 | 472
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.5197 | - | - | 13.5197 | - | 13.5197 | ST | Region 5 - Central Valley | PINE GROVE | Amador | 38.4128 | -120.6603 |  | 1920 | 0.010952 |  | 161 | 0.014761 | 99% | V3 Tranche 1 | Tier 3 | 473
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.1028 | - | - | 16.1028 | - | 16.1028 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7219 | -120.7904 |  | 2135 | 0.0064118 |  | 148 | 0.015591 | 99% | V3 Tranche 1 | Tier 2 | 474
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 52.9958 | - | - | 52.9958 | - | 52.9958 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7716 | -120.8148 |  | 1666 | 0.020262 |  | 68 | 0.020612 | 99% | V3 Tranche 1 | Tier 3 | 475
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.066273 | - | - | 0.066273 | - | 0.066273 | SI | Region 2 - North East | KELSEY | El Dorado | 38.7719 | -120.8138 |  | 1168 | 0.050873 |  | 1 | 0.10471 | 99% | V3 Tranche 1 | Tier 3 | 476
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 25.9329 | - | - | 25.9329 | - | 25.9329 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 |  | 904 | 0.079474 |  | 58 | 0.021398 | 99% | V3 Tranche 1 | Tier 3 | 477
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 30.8769 | - | - | 30.8769 | - | 30.8769 | SI | Region 2 - North East | SPANISH FLAT | El Dorado | 38.8328 | -120.8176 |  | 1646 | 0.021241 |  | 236 | 0.011373 | 99% | V3 Tranche 1 | Tier 3 | 478
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7465 | - | - | 7.7465 | - | 7.7465 | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7308 | -120.7838 |  | 1168 | 0.050873 |  | 230 | 0.011469 | 99% | V3 Tranche 1 | Tier 3 | 479
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.2953 | - | - | 2.2953 | - | 2.2953 | NB | Region 1 - North Coast | ENCHANTED HILLS | Napa | 38.397 | -122.4504 |  | 1224 | 0.046077 |  | 264 | 0.010245 | 99% | V3 Tranche 1 | Tier 3 | 480
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 41.2147 | - | - | 41.2147 | - | 41.2147 | NB | Region 1 - North Coast | NAPA | Napa | 38.3155 | -122.3422 |  | 1224 | 0.046077 |  | 255 | 0.010549 | 99% | V3 Tranche 1 | Tier 3 | 481
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.3813 | - | - | 9.3813 | - | 9.3813 | NB | Region 1 - North Coast | NAPA | Napa | 38.3469 | -122.3299 |  | 1630 | 0.022046 |  | 1000 | 0.0022679 | 99% | V3 Tranche 1 | Tier 3 | 482
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.7002 | - | - | 24.7002 | - | 24.7002 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0662 | -122.611 |  | 423 | 0.17389 |  | 127 | 0.016255 | 99% | V3 Tranche 1 | Tier 3 | 483
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.9186 | - | - | 6.9186 | - | 6.9186 | HB | Region 1 - North Coast | SPRING VALLEY | Lake | 39.0836 | -122.6599 |  | 312 | 0.20738 |  | 44 | 0.023647 | 99% | V3 Tranche 1 | Tier 3 | 484
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4951 | - | - | 5.4951 | - | 5.4951 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0231 | -122.678 |  | 345 | 0.19539 |  | 679 | 0.0038601 | 99% | V3 Tranche 1 | Tier 3 | 485
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.1996 | - | - | 5.1996 | - | 5.1996 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0581 | -122.693 |  | 345 | 0.19539 |  | 375 | 0.007396 | 99% | V3 Tranche 1 | Tier 3 | 486
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.0551 | - | - | 4.0551 | - | 4.0551 | HB | Region 1 - North Coast | CLEARLAKE OAKS | Lake | 39.0275 | -122.6625 |  | 2343 | 0.0030523 |  | 395 | 0.0070846 | 99% | V3 Tranche 1 | Tier 2 | 487
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.5016 | - | - | 6.5016 | - | 6.5016 | ST | Region 5 - Central Valley | DORRINGTON | Calaveras | 38.323 | -120.2534 |  | 2620 | 0.0010653 |  | 133 | 0.016045 | 99% | V3 Tranche 1 | Tier 3 | 488
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.6822e-05 | - | - | 3.6822e-05 | - | 3.6822e-05 | NB | Region 1 - North Coast | SAN RAFAEL | Marin | 37.9807 | -122.5155 |  | 3129 | 7.8608e-06 |  | 5066 | 4.4996e-05 | 99% | V3 Tranche 1 | Tier 2 | 489
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | MI | Region 3 - Bay Area | DUBLIN | Alameda | 37.7029 | -121.9121 |  | 3206 | 6.0521e-06 |  | 1337 | 0.0012585 | 99% | V3 Tranche 1 | Tier 3 | 490
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.5259 | - | - | 7.5259 | - | 7.5259 | SI | Region 2 - North East | COLFAX | Placer | 39.103 | -120.9601 |  | 1885 | 0.011963 |  | 120 | 0.016673 | 99% | V3 Tranche 1 | Tier 3 | 491
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.5495 | - | - | 14.5495 | - | 14.5495 | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 |  | 2201 | 0.00506 |  | 71 | 0.02023 | 99% | V3 Tranche 1 | Tier 2 | 492
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.986 | - | - | 0.986 | - | 0.986 | SI | Region 2 - North East | COLFAX | Placer | 39.0992 | -120.95 |  | 1581 | 0.023753 |  | 542 | 0.0049817 | 99% | V3 Tranche 1 | Tier 2 | 493
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32802 | - | - | 0.32802 | - | 0.32802 | SI | Region 2 - North East | COLFAX | Placer | 39.0994 | -120.9559 |  | 2622 | 0.0010502 |  | 869 | 0.0027704 | 99% | V3 Tranche 1 | Tier 2 | 494
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 24.2383 | - | - | 24.2383 | - | 24.2383 | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | 99% | V3 Tranche 1 | Tier 3 | 495
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6883 | - | - | 12.6883 | - | 12.6883 | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 |  | 1378 | 0.034658 |  | 89 | 0.018876 | 99% | V3 Tranche 1 | Tier 3 | 496
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.814 | - | - | 23.814 | - | 23.814 | SI | Region 2 - North East | COLFAX | Placer | 39.1153 | -120.953 |  | 1829 | 0.01359 |  | 180 | 0.01361 | 99% | V3 Tranche 1 | Tier 3 | 497
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.020723 | - | - | 0.020723 | - | 0.020723 | SI | Region 2 - North East | CAMERON PARK | El Dorado | 38.6795 | -120.9797 |  | 1047 | 0.061564 |  | 1953 | 0.00056455 | 99% | V3 Tranche 1 | Tier 2 | 498
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.73323 | - | - | 0.73323 | - | 0.73323 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5715 | -122.4451 |  | 1235 | 0.044601 |  | 873 | 0.0027563 | 99% | V3 Tranche 1 | Tier 3 | 499
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.5423 | - | - | 16.5423 | - | 16.5423 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5446 | -122.4781 |  | 1235 | 0.044601 |  | 33 | 0.025445 | 99% | V3 Tranche 1 | Tier 3 | 500
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.5752 | - | - | 22.5752 | - | 22.5752 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.574 | -122.4444 |  | 792 | 0.094959 |  | 59 | 0.021383 | 99% | V3 Tranche 1 | Tier 3 | 501
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3951 | - | - | 4.3951 | - | 4.3951 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5755 | -122.4443 |  | 1235 | 0.044601 |  | 14 | 0.034265 | 99% | V3 Tranche 1 | Tier 3 | 502
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 3.3167 | - | - | 3.3167 | - | 3.3167 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5146 | -122.4742 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | 99% | V3 Tranche 1 | Tier 3 | 503
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.946 | - | - | 0.946 | - | 0.946 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.545 | -122.4756 |  | 690 | 0.11274 |  | 435 | 0.0064165 | 99% | V3 Tranche 1 | Tier 3 | 504
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 32.9297 | - | - | 32.9297 | - | 32.9297 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.6152 | -122.4292 |  | 279 | 0.22347 |  | 203 | 0.012452 | 99% | V3 Tranche 1 | Tier 3 | 505
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.1027 | - | - | 14.1027 | - | 14.1027 | NB | Region 1 - North Coast | ANGWIN | Napa | 38.5533 | -122.4563 |  | 1254 | 0.043133 |  | 101 | 0.018153 | 99% | V3 Tranche 1 | Tier 3 | 506
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 22.9886 | - | - | 22.9886 | - | 22.9886 | NB | Region 1 - North Coast | POPE VALLEY | Napa | 38.617 | -122.4242 |  | 309 | 0.21008 |  | 805 | 0.00309 | 99% | V3 Tranche 1 | Tier 3 | 507
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.7133 | - | - | 0.7133 | - | 0.7133 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5099 | -122.4785 |  | 2341 | 0.0030939 |  | 419 | 0.0067032 | 99% | V3 Tranche 1 | Tier 3 | 508
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.16686 | - | - | 0.16686 | - | 0.16686 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.505 | -122.4747 |  | 3223 | 5.7874e-06 |  | 793 | 0.0031429 | 99% | V3 Tranche 1 | Tier 3 | 509
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3898 | - | - | 4.3898 | - | 4.3898 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5377 | -122.4954 |  | 1947 | 0.010281 |  | 556 | 0.0048458 | 99% | V3 Tranche 1 | Tier 3 | 510
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.2957 | - | - | 9.2957 | - | 9.2957 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4984 | -122.4795 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | 99% | V3 Tranche 1 | Tier 3 | 511
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 2.5635 | - | - | 2.5635 | - | 2.5635 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5286 | -122.5007 |  | 1901 | 0.011541 |  | 291 | 0.0096168 | 99% | V3 Tranche 1 | Tier 3 | 512
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.0817 | - | - | 1.0817 | - | 1.0817 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5471 | -122.5102 |  | 2241 | 0.0043094 |  | 594 | 0.0044669 | 99% | V3 Tranche 1 | Tier 3 | 513
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.3847 | - | - | 0.3847 | - | 0.3847 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5057 | -122.4845 |  | 3085 | 9.3615e-06 |  | 416 | 0.0067497 | 99% | V3 Tranche 1 | Tier 3 | 514
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 13.1185 | - | - | 13.1185 | - | 13.1185 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5071 | -122.4907 |  | 1361 | 0.035763 |  | 87 | 0.018978 | 99% | V3 Tranche 1 | Tier 3 | 515
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.19139 | - | - | 0.19139 | - | 0.19139 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.5206 | -122.4936 |  | 2341 | 0.0030939 |  | 1407 | 0.0011424 | 99% | V3 Tranche 1 | HFRA | 516
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.12596 | - | - | 0.12596 | - | 0.12596 | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 |  | 2351 | 0.0030112 |  | 90 | 0.018786 | 99% | V3 Tranche 1 | Tier 3 | 517
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.76549 | - | - | 0.76549 | - | 0.76549 | NB | Region 1 - North Coast | SAINT HELENA | Napa | 38.4943 | -122.4756 |  | 3201 | 6.2313e-06 |  | 117 | 0.016818 | 99% | V3 Tranche 1 | Tier 3 | 518
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.4863 | - | - | 5.4863 | - | 5.4863 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2328 | -120.3655 |  | 2540 | 0.0015977 |  | 186 | 0.013343 | 99% | V3 Tranche 1 | Tier 3 | 519
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7986 | - | - | 23.7986 | - | 23.7986 | ST | Region 5 - Central Valley | AVERY | Calaveras | 38.1832 | -120.3754 |  | 1412 | 0.032657 |  | 66 | 0.02064 | 99% | V3 Tranche 1 | Tier 3 | 520
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.7987 | - | - | 5.7987 | - | 5.7987 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1743 | -120.3835 |  | 1661 | 0.020479 |  | 269 | 0.010091 | 99% | V3 Tranche 1 | Tier 2 | 521
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.6801 | - | - | 12.6801 | - | 12.6801 | ST | Region 5 - Central Valley | FOREST MEADOWS | Calaveras | 38.1699 | -120.4067 |  | 2142 | 0.0062159 |  | 231 | 0.011425 | 99% | V3 Tranche 1 | Tier 2 | 522
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 44.875 | - | - | 44.875 | - | 44.875 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 |  | 56 | 0.40353 |  | 95 | 0.018647 | 99% | V3 Tranche 1 | Tier 2 | 523
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.7229 | - | - | 23.7229 | - | 23.7229 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2366 | -120.3628 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | 99% | V3 Tranche 1 | Tier 3 | 524
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.4909 | - | - | 8.4909 | - | 8.4909 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2465 | -120.3642 |  | 2810 | 0.00026318 |  | 98 | 0.01848 | 99% | V3 Tranche 1 | Tier 3 | 525
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.3846 | - | - | 10.3846 | - | 10.3846 | ST | Region 5 - Central Valley | ARNOLD | Calaveras | 38.2369 | -120.3646 |  | 2670 | 0.0008147 |  | 60 | 0.021109 | 99% | V3 Tranche 1 | Tier 3 | 526
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.2061 | - | - | 10.2061 | - | 10.2061 | ST | Region 5 - Central Valley | MURPHYS | Tuolumne | 38.139 | -120.3704 |  | 235 | 0.24096 |  | 54 | 0.022026 | 99% | V3 Tranche 1 | Tier 3 | 527
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.7453 | - | - | 27.7453 | - | 27.7453 | NV | Region 2 - North East | CHICO | Butte | 39.8318 | -121.8444 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | 99% | V3 Tranche 1 | Tier 3 | 528
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 27.1262 | - | - | 27.1262 | - | 27.1262 | NV | Region 2 - North East | COHASSET | Butte | 39.9034 | -121.742 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | 99% | V3 Tranche 1 | Tier 3 | 529
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 4.3948 | - | - | 4.3948 | - | 4.3948 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4495 | -120.4908 |  | 1744 | 0.016801 |  | 151 | 0.015433 | 99% | V3 Tranche 1 | Tier 3 | 530
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.32281 | - | - | 0.32281 | - | 0.32281 | ST | Region 5 - Central Valley | PIONEER | Amador | 38.4491 | -120.4927 |  | 1744 | 0.016801 |  | 8 | 0.040941 | 99% | V3 Tranche 1 | Tier 3 | 531
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 16.0017 | - | - | 16.0017 | - | 16.0017 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1583 | -122.9898 |  | 335 | 0.19794 |  | 35 | 0.024971 | 99% | V3 Tranche 1 | Tier 2 | 532
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 11.8763 | - | - | 11.8763 | - | 11.8763 | HB | Region 1 - North Coast | SARATOGA SPRINGS | Lake | 39.1825 | -122.9619 |  | 259 | 0.23008 |  | 327 | 0.0086415 | 99% | V3 Tranche 1 | Tier 2 | 533
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 15.4939 | - | - | 15.4939 | - | 15.4939 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1894 | -122.9009 |  | 705 | 0.11161 |  | 309 | 0.0089653 | 99% | V3 Tranche 1 | Tier 3 | 534
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.3587 | - | - | 1.3587 | - | 1.3587 | HB | Region 1 - North Coast | UPPER LAKE | Lake | 39.1457 | -122.9167 |  | 6 | 1.2559 |  | 588 | 0.0045199 | 99% | V3 Tranche 1 | Tier 2 | 535
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.4554 | - | - | 29.4554 | - | 29.4554 | SI | Region 2 - North East | WEIMAR | Placer | 39.0443 | -120.9859 |  | 1379 | 0.034582 |  | 166 | 0.014596 | 99% | V3 Tranche 1 | Tier 2 | 536
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 23.2219 | - | - | 23.2219 | - | 23.2219 | SI | Region 2 - North East | WEIMAR | Placer | 39.0318 | -120.9741 |  | 1801 | 0.014579 |  | 142 | 0.015811 | 99% | V3 Tranche 1 | Tier 2 | 537
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 19.6912 | - | - | 19.6912 | - | 19.6912 | SI | Region 2 - North East | WEIMAR | Placer | 39.0342 | -120.9744 |  | 2258 | 0.003969 |  | 272 | 0.010047 | 99% | V3 Tranche 1 | Tier 2 | 538
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 7.7753 | - | - | 7.7753 | - | 7.7753 | SI | Region 2 - North East | WEIMAR | Placer | 39.0352 | -120.9794 |  | 2599 | 0.0011906 |  | 268 | 0.010095 | 99% | V3 Tranche 1 | Tier 2 | 539
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.8119 | - | - | 10.8119 | - | 10.8119 | SI | Region 2 - North East | WEIMAR | Placer | 39.036 | -120.9881 |  | 2422 | 0.0023893 |  | 214 | 0.012028 | 99% | V3 Tranche 1 | Tier 2 | 540
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 8.1738 | - | - | 8.1738 | - | 8.1738 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4437 | -120.5088 |  | 2589 | 0.0012622 |  | 352 | 0.0079522 | 99% | V3 Tranche 1 | Tier 3 | 541
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 29.3469 | - | - | 29.3469 | - | 29.3469 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.487 | -120.5231 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | 99% | V3 Tranche 1 | Tier 3 | 542
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 14.385 | - | - | 14.385 | - | 14.385 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4645 | -120.5292 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | 99% | V3 Tranche 1 | Tier 3 | 543
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0056 | - | - | 6.0056 | - | 6.0056 | ST | Region 5 - Central Valley | MOUNTAIN RANCH | Amador | 38.421 | -120.5497 |  | 1765 | 0.015736 |  | 218 | 0.011836 | 99% | V3 Tranche 1 | Tier 3 | 544
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 1.374 | - | - | 1.374 | - | 1.374 | ST | Region 5 - Central Valley | BUCKHORN | Amador | 38.4575 | -120.5238 |  | 2786 | 0.00032448 |  | 681 | 0.0038479 | 99% | V3 Tranche 1 | Tier 3 | 545
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 12.2384 | - | - | 12.2384 | - | 12.2384 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3174 | -120.5212 |  | 2247 | 0.0041901 |  | 80 | 0.019265 | 99% | V3 Tranche 1 | Tier 3 | 546
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 90.2567 | - | - | 90.2567 | - | 90.2567 | ST | Region 5 - Central Valley | RAIL ROAD FLAT | Calaveras | 38.3314 | -120.5186 |  | 1206 | 0.047319 |  | 164 | 0.014654 | 99% | V3 Tranche 1 | Tier 3 | 547
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 9.7214 | - | - | 9.7214 | - | 9.7214 | NV | Region 2 - North East | PLATINA | Shasta | 40.3595 | -122.8928 |  | 52 | 0.41883 |  | 86 | 0.018983 | 99% | V3 Tranche 1 | Tier 2 | 548
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 10.0775 | - | - | 10.0775 | - | 10.0775 | NV | Region 2 - North East | WILDWOOD | Trinity | 40.3846 | -123.0286 |  | 1125 | 0.054922 |  | 191 | 0.013119 | 99% | V3 Tranche 1 | Tier 2 | 549
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 5.6734 | - | - | 5.6734 | - | 5.6734 | NV | Region 2 - North East | PLATINA | Shasta | 40.3606 | -122.8896 |  | 598 | 0.13184 |  | 111 | 0.017225 | 99% | V3 Tranche 1 | Tier 2 | 550
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.284 | - | - | 6.284 | - | 6.284 | NV | Region 2 - North East | PLATINA | Shasta | 40.3607 | -122.9513 |  | 454 | 0.16402 |  | 109 | 0.017355 | 99% | V3 Tranche 1 | Tier 2 | 551
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.023199 | - | - | 0.023199 | - | 0.023199 | NB | Region 1 - North Coast | Calistoga | Napa | 38.579 | -122.5144 |  | 1624 | 0.022 |  | 874 | 0.0027 | 99% | V3 Tranche 1 | Tier 3 | 552
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.0166 | - | - | 6.0166 | - | 6.0166 | NV | Region 2 - North East | Belden | Plumas | 39.9114 | -121.327 |  | 11 | 0.735 |  | 21 | 0.029 | 99% | V3 Tranche 1 | Tier 2/3 | 553
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 20.2372 | - | - | 20.2372 | - | 20.2372 | SI | Region 2 - North East | COLFAX | Placer | 39.1003 | -120.9524 |  | 1581 | 0.0237 |  | 208 | 0.0122 | 99% | V3 Tranche 1 | Non Tier, Tier 2 | 554
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035511 | - | - | 0.0035511 | - | 0.0035511 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1681 | -120.1025 |  | 911 | 0.0788 |  | 335 | 0.0085 | 99% | V3 Tranche 1 | Tier 3 | 555
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 0.0035512 | - | - | 0.0035512 | - | 0.0035512 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 |  | 323 | 0.201 |  | 136 | 0.016 | 99% | V3 Tranche 1 | Tier 2 | 556
TBD | Targeted UG | 3UG | Order not created | Pre-Scoping | 6.35 | - | - | 6.35 | - | 6.35 | SI | Region 2 - North East | Smartsville | Nevada | 39.2357 | -121.2689 |  | 658 | 0.118 |  | 46 | 0.023 | 99% | V3 Tranche 1 | Tier 2 | 557

## v3_SH_composite_cs_summary (hidden)
WDRM v3
Circuit Segment Name | Feeder Name | Feeder ID | HFTD < 1km | Primary Ovhd Length (miles) | Secondary Ovhd Length (miles) | HFTD Length (miles) | SH Risk Pixel Count | SH Ignition Probability | Rank: SH Ignition Probability | Consequence v3.4 | Rank: Consequence v3.4 | SH Risk | Rank: SH Risk
PLACERVILLE 210658118 | PLACERVILLE 2106 | 153082106 | TRUE | 0.053018 | 0.055209 | 0.10823 | 0.83333 | 0.0013961 | 145 | 75.0013 | 48 | 0.10471 | 1
APPLE HILL 2102CB | APPLE HILL 2102 | 153662102 | TRUE | 0.063133 | 0.106 | 0.16914 | 1.5 | 0.0012983 | 205 | 69.4098 | 70 | 0.090117 | 2
CALPINE 1144304 | CALPINE 1144 | 48011144 | TRUE | 0.046359 | 0 | 0.046358 | 2.5 | 0.0009601 | 961 | 69.5114 | 69 | 0.068443 | 3
ALLEGHANY 11021101/2 | ALLEGHANY 1102 | 152101102 | TRUE | 0.014692 | 0 | 0.014692 | 0.5 | 0.0010449 | 637 | 63.2373 | 97 | 0.066078 | 4
BALCH NO 1 1101CB | BALCH NO 1 1101 | 252501101 | TRUE | 0.0137 | 0 | 0.0137 | 1.5 | 0.00036862 | 6863 | 144.6407 | 2 | 0.053317 | 5
PINE GROVE 1101CB | PINE GROVE 1101 | 163751101 | FALSE | 4.2753 | 0.77697 | 5.0523 | 72 | 0.00067601 | 3357 | 61.4169 | 107 | 0.047261 | 6
CAMP EVERS 2105BL 2101 | CAMP EVERS 2105 | 83622105 | TRUE | 0.0032255 | 0 | 0.0032255 | 0.2 | 0.03669 | 1 | 1.2226 | 2099 | 0.044857 | 7
TIGER CREEK 0201CB | TIGER CREEK 0201 | 161380201 | TRUE | 0.23574 | 0.16036 | 0.39611 | 5.5 | 0.00051875 | 5188 | 78.9226 | 40 | 0.040941 | 8
MONTICELLO 1101630 | MONTICELLO 1101 | 43051101 | FALSE | 4.8887 | 0.69087 | 4.9383 | 97 | 0.00047459 | 5653 | 84.0033 | 26 | 0.039591 | 9
INDIAN FLAT 1104CB | INDIAN FLAT 1104 | 252691104 | FALSE | 15.817 | 1.3996 | 13.7984 | 303.5 | 0.00034216 | 7272 | 111.7635 | 6 | 0.039297 | 10
ANTLER 11011384 | ANTLER 1101 | 103271101 | FALSE | 9.0375 | 1.4991 | 10.3375 | 149 | 0.00065552 | 3632 | 45.6506 | 195 | 0.038738 | 11
INDIAN FLAT 11044440 | INDIAN FLAT 1104 | 252691104 | TRUE | 0.23657 | 0 | 0.23656 | 4.5 | 0.00044594 | 5953 | 85.0158 | 23 | 0.038638 | 12
MIDDLETOWN 110148212 | MIDDLETOWN 1101 | 43141101 | FALSE | 8.8255 | 1.1871 | 9.8342 | 163.8333 | 0.00041642 | 6264 | 83.7228 | 29 | 0.035184 | 13
SILVERADO 2104646776 | SILVERADO 2104 | 43432104 | FALSE | 3.5161 | 2.1701 | 5.6861 | 72.5 | 0.00098192 | 861 | 31.5514 | 349 | 0.034265 | 14
CLAYTON 221296224 | CLAYTON 2212 | 12022212 | FALSE | 7.6836 | 2.4915 | 10.1751 | 138 | 0.00040748 | 6364 | 81.5656 | 34 | 0.034099 | 15
MARIPOSA 2101929360 | MARIPOSA 2101 | 254452101 | TRUE | 0.067118 | 0 | 0.067118 | 0.25 | 0.00071677 | 2891 | 46.6081 | 186 | 0.033407 | 16
ORO FINO 1102CB | ORO FINO 1102 | 103031102 | FALSE | 2.157 | 0.57723 | 2.7342 | 41.5 | 0.00055748 | 4788 | 52.3371 | 154 | 0.031702 | 17
BALCH NO 1 1101105414 | BALCH NO 1 1101 | 252501101 | FALSE | 6.9964 | 0.47461 | 7.471 | 130 | 0.00022933 | 9505 | 138.6072 | 3 | 0.031265 | 18
MONTICELLO 1101CB | MONTICELLO 1101 | 43051101 | TRUE | 0.53696 | 0 | 0.53696 | 10 | 0.00034915 | 7158 | 85.9446 | 22 | 0.030464 | 19
BONNIE NOOK 1101CB | BONNIE NOOK 1101 | 152301101 | FALSE | 14.4437 | 3.3608 | 17.8044 | 281.5 | 0.0004932 | 5464 | 59.6869 | 114 | 0.02949 | 20
BUCKS CREEK 1101CB | BUCKS CREEK 1101 | 102211101 | FALSE | 4.8133 | 0 | 4.8133 | 95.8333 | 0.00035098 | 7122 | 83.0275 | 31 | 0.029234 | 21
OAKHURST 110310140 | OAKHURST 1103 | 254421103 | FALSE | 16.6046 | 2.1528 | 18.7573 | 312.8333 | 0.0005129 | 5255 | 53.1921 | 149 | 0.028816 | 22
PARADISE 1103283794 | PARADISE 1103 | 102831103 | FALSE | 2.2274 | 0.51698 | 2.5507 | 37 | 0.00049286 | 5466 | 59.6349 | 115 | 0.027788 | 23
CALISTOGA 1102131531 | CALISTOGA 1102 | 42711102 | FALSE | 4.8416 | 0.20041 | 5.042 | 91 | 0.00066621 | 3479 | 40.9771 | 237 | 0.027222 | 24
MIDDLETOWN 1103CB | MIDDLETOWN 1103 | 43141103 | TRUE | 0.090014 | 0 | 0.052964 | 3.1667 | 0.0008895 | 1302 | 37.9292 | 277 | 0.027013 | 25
PARADISE 11061212 | PARADISE 1106 | 102831106 | FALSE | 1.5881 | 0.7961 | 2.3681 | 21 | 0.00073299 | 2696 | 35.2436 | 307 | 0.026975 | 26
MONTICELLO 1101654 | MONTICELLO 1101 | 43051101 | FALSE | 8.5423 | 0.30547 | 8.302 | 152 | 0.00031694 | 7679 | 83.9453 | 27 | 0.026786 | 27
ELECTRA 1102CB | ELECTRA 1102 | 162161102 | FALSE | 2.6041 | 0 | 2.6041 | 52.8333 | 0.00045065 | 5914 | 57.327 | 126 | 0.026433 | 28
HIGHLANDS 1102628 | HIGHLANDS 1102 | 43361102 | FALSE | 14.7136 | 1.0698 | 15.7833 | 278.5 | 0.00021792 | 9733 | 121.748 | 4 | 0.026126 | 29
APPLE HILL 1104CB | APPLE HILL 1104 | 153661104 | FALSE | 4.0817 | 1.5662 | 5.6478 | 71.5 | 0.0006531 | 3669 | 32.6504 | 337 | 0.025967 | 30
CRESTA 1101546650 | CRESTA 1101 | 102251101 | FALSE | 0.89675 | 0 | 0.89675 | 16.5 | 0.00042099 | 6215 | 61.2767 | 109 | 0.025946 | 31
APPLE HILL 21026552 | APPLE HILL 2102 | 153662102 | FALSE | 12.1088 | 0.91528 | 13.0241 | 224 | 0.00036666 | 6890 | 66.5156 | 79 | 0.025831 | 32
SILVERADO 2104515946 | SILVERADO 2104 | 43432104 | FALSE | 16.2604 | 2.7956 | 19.0559 | 310.8333 | 0.00065403 | 3655 | 38.9085 | 263 | 0.025445 | 33
CURTIS 170356972 | CURTIS 1703 | 163351703 | FALSE | 8.2034 | 0.31618 | 8.4156 | 160.8333 | 0.00022419 | 9624 | 111.2432 | 7 | 0.02502 | 34
UPPER LAKE 11011276 | UPPER LAKE 1101 | 42871101 | FALSE | 12.7917 | 1.6228 | 12.2879 | 259 | 0.00035077 | 7126 | 72.4825 | 61 | 0.024971 | 35
FRENCH GULCH 1101CB | FRENCH GULCH 1101 | 103381101 | FALSE | 2.3629 | 0.34745 | 2.7103 | 47.5 | 0.00037181 | 6811 | 64.4995 | 92 | 0.024965 | 36
NOTRE DAME 11042028 | NOTRE DAME 1104 | 102041104 | FALSE | 10.8392 | 0.5512 | 11.3904 | 201.5 | 0.00030826 | 7837 | 78.1156 | 42 | 0.024521 | 37
MIDDLETOWN 1101171414 | MIDDLETOWN 1101 | 43141101 | FALSE | 3.5119 | 0.079457 | 3.5913 | 66 | 0.0003973 | 6487 | 61.7223 | 106 | 0.024501 | 38
CALPINE 1144962 | CALPINE 1144 | 48011144 | TRUE | 0.039372 | 0 | 0.039372 | 0.83333 | 0.00033341 | 7404 | 73.3311 | 55 | 0.024449 | 39
CALPINE 1144962 | CALPINE 1144 | 48011144 | TRUE | 0.039372 | 0 | 0.039372 | 0.83333 | 0.00033341 | 7404 | 73.3311 | 55 | 0.024449 | 39
CRESTA 1101103126 | CRESTA 1101 | 102251101 | FALSE | 0.80752 | 0.064503 | 0.87202 | 15.5 | 0.00045697 | 5846 | 67.945 | 75 | 0.023964 | 40
ALLEGHANY 1102CB | ALLEGHANY 1102 | 152101102 | FALSE | 17.7807 | 1.1304 | 18.911 | 350 | 0.00043108 | 6108 | 55.8651 | 136 | 0.023951 | 41
FRENCH GULCH 1102CB | FRENCH GULCH 1102 | 103381102 | FALSE | 1.8226 | 0.0070996 | 1.8297 | 30.8333 | 0.00031652 | 7692 | 74.9471 | 49 | 0.023712 | 42
KESWICK 11019712 | KESWICK 1101 | 103451101 | FALSE | 18.5915 | 1.994 | 20.5855 | 340 | 0.00036642 | 6896 | 66.2459 | 81 | 0.023649 | 43
REDBUD 1101454 | REDBUD 1101 | 43191101 | FALSE | 5.5315 | 0.27901 | 5.8104 | 106 | 0.00024026 | 9284 | 96.3211 | 10 | 0.023647 | 44
BUCKS CREEK 1102CB | BUCKS CREEK 1102 | 102211102 | FALSE | 29.4282 | 2.3231 | 31.7512 | 580.8333 | 0.00034985 | 7142 | 64.6354 | 90 | 0.023178 | 45
NARROWS 2102CB | NARROWS 2102 | 153132102 | FALSE | 5.08 | 0.11393 | 5.1939 | 83.5833 | 0.00057679 | 4564 | 40.001 | 251 | 0.022999 | 46
CLARK ROAD 110247006 | CLARK ROAD 1102 | 103091102 | FALSE | 4.4768 | 0.21461 | 4.6914 | 68.8333 | 0.00042245 | 6202 | 59.5332 | 117 | 0.022808 | 47
KESWICK 11011586 | KESWICK 1101 | 103451101 | FALSE | 7.4823 | 0.038297 | 7.5206 | 139 | 0.00032816 | 7482 | 69.959 | 68 | 0.022602 | 48
EL DORADO PH 210119752 | EL DORADO PH 2101 | 152762101 | FALSE | 38.5695 | 3.4043 | 41.9737 | 681.5 | 0.00055978 | 4759 | 41.8066 | 227 | 0.022482 | 49
MIWUK 170236888 | MIWUK 1702 | 163661702 | FALSE | 0.61464 | 0.14865 | 0.75203 | 9 | 0.00046983 | 5702 | 47.189 | 182 | 0.022171 | 50
KONOCTI 11022293 | KONOCTI 1102 | 43311102 | FALSE | 1.7304 | 0.35379 | 2.0842 | 31.5 | 0.00036931 | 6852 | 60.0318 | 112 | 0.022125 | 51
PIKE CITY 11011720 | PIKE CITY 1101 | 152201101 | FALSE | 5.8943 | 0.13007 | 6.0244 | 112.5 | 0.00035282 | 7091 | 66.0542 | 82 | 0.02211 | 52
BEAR VALLEY 2105CB | BEAR VALLEY 2105 | 252192105 | FALSE | 16.0286 | 0.20096 | 16.2295 | 323 | 0.00019299 | 10165 | 116.2035 | 5 | 0.022066 | 53
STANISLAUS 1702CB | STANISLAUS 1702 | 162821702 | FALSE | 8.1019 | 0.59316 | 8.695 | 131 | 0.00036286 | 6948 | 87.1066 | 19 | 0.022026 | 54
APPLE HILL 210289934 | APPLE HILL 2102 | 153662102 | FALSE | 5.4274 | 0.43767 | 5.865 | 89.5 | 0.00031243 | 7761 | 70.905 | 67 | 0.021839 | 55
MIDDLETOWN 11011314 | MIDDLETOWN 1101 | 43141101 | FALSE | 0.92536 | 0.071 | 0.99636 | 19 | 0.00030084 | 7997 | 73.8788 | 53 | 0.021686 | 56
SYCAMORE CREEK 11112268 | SYCAMORE CREEK 1111 | 102971111 | FALSE | 21.6869 | 1.4694 | 23.1562 | 393.5 | 0.00039725 | 6490 | 51.1997 | 159 | 0.021521 | 57
PLACERVILLE 2106935216 | PLACERVILLE 2106 | 153082106 | FALSE | 20.7464 | 1.1938 | 21.9401 | 393.3333 | 0.00024586 | 9169 | 87.9463 | 18 | 0.021398 | 58
SILVERADO 2104632 | SILVERADO 2104 | 43432104 | FALSE | 18.385 | 0.97289 | 19.0469 | 333 | 0.00067052 | 3428 | 40.2134 | 247 | 0.021383 | 59
STANISLAUS 17026028 | STANISLAUS 1702 | 162821702 | FALSE | 8.3079 | 1.1476 | 9.4555 | 131 | 0.00072468 | 2794 | 30.3073 | 365 | 0.021109 | 60
ORO FINO 110276008 | ORO FINO 1102 | 103031102 | FALSE | 16.1491 | 1.2494 | 17.3985 | 278.5 | 0.00043392 | 6072 | 47.6432 | 177 | 0.020869 | 61
ELECTRA 11017104 | ELECTRA 1101 | 162161101 | FALSE | 12.074 | 1.5611 | 13.6351 | 209.5 | 0.00035071 | 7128 | 54.7741 | 140 | 0.020861 | 62
APPLE HILL 21027502 | APPLE HILL 2102 | 153662102 | FALSE | 22.8336 | 1.9456 | 24.7792 | 420.5 | 0.00037975 | 6699 | 57.0812 | 128 | 0.020812 | 63
OREGON TRAIL 11021584 | OREGON TRAIL 1102 | 103521102 | FALSE | 13.1714 | 1.7091 | 14.8805 | 250 | 0.0003817 | 6678 | 56.2041 | 131 | 0.0208 | 64
MARIPOSA REMOTE 0001CB | MARIPOSA REMOTE 0001 | 257010001 | TRUE | 0 | 0.15519 | 0.15519 | 4 | 0.00013939 | 10795 | 149.8982 | 1 | 0.02071 | 65
STANISLAUS 17011812 | STANISLAUS 1701 | 162821701 | FALSE | 19.2034 | 2.1522 | 21.3556 | 347 | 0.00048866 | 5509 | 42.4492 | 219 | 0.02064 | 66
CURTIS 17039240 | CURTIS 1703 | 163351703 | FALSE | 10.8962 | 3.7165 | 14.6126 | 198.3333 | 0.00040554 | 6388 | 50.6955 | 162 | 0.020635 | 67
PLACERVILLE 210611132 | PLACERVILLE 2106 | 153082106 | FALSE | 42.7004 | 2.0548 | 44.7551 | 783.8333 | 0.00033314 | 7406 | 66.6961 | 78 | 0.020612 | 68
PARADISE 11032534 | PARADISE 1103 | 102831103 | FALSE | 2.3608 | 0.96959 | 3.0595 | 48.5 | 0.00055206 | 4846 | 37.9498 | 276 | 0.020609 | 69
MOUNTAIN QUARRIES 210135466 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 7.2944 | 0.76173 | 8.0561 | 125.3333 | 0.00031745 | 7673 | 63.2322 | 98 | 0.020297 | 70
SHADY GLEN 110132726 | SHADY GLEN 1101 | 152431101 | FALSE | 12.2854 | 1.5429 | 13.6021 | 223 | 0.00028948 | 8207 | 72.9059 | 58 | 0.02023 | 71
TEJON 11022455 | TEJON 1102 | 252931102 | FALSE | 6.319 | 1.5217 | 7.8407 | 116.5 | 0.00060319 | 4265 | 34.2828 | 317 | 0.020158 | 72
GIRVAN 11029012 | GIRVAN 1102 | 103401102 | FALSE | 15.5575 | 0.5815 | 16.139 | 274.5 | 0.00031066 | 7793 | 66.3579 | 80 | 0.020102 | 73
BRUNSWICK 1103639148 | BRUNSWICK 1103 | 152481103 | FALSE | 8.9938 | 0.73394 | 9.7277 | 165 | 0.00027354 | 8565 | 72.5966 | 60 | 0.020041 | 74
COLUMBIA HILL 110190730 | COLUMBIA HILL 1101 | 152471101 | FALSE | 8.3716 | 0.72065 | 9.0922 | 156.5 | 0.00028684 | 8262 | 65.7488 | 83 | 0.020034 | 75
BEAR VALLEY 210576694 | BEAR VALLEY 2105 | 252192105 | FALSE | 4.5851 | 0.20867 | 4.7938 | 85 | 0.00020758 | 9918 | 92.0923 | 15 | 0.019903 | 76
MARIPOSA 2102CB | MARIPOSA 2102 | 254452102 | FALSE | 5.5893 | 0.19298 | 5.6591 | 107.5 | 0.00030418 | 7927 | 62.6253 | 102 | 0.019783 | 77
CALISTOGA 1102141073 | CALISTOGA 1102 | 42711102 | FALSE | 2.1301 | 0.38615 | 1.2828 | 39 | 0.00082428 | 1780 | 20.0307 | 556 | 0.019531 | 78
CALPINE 1146CB | CALPINE 1146 | 48011146 | FALSE | 2.9685 | 0.02565 | 2.9941 | 54.5 | 0.00030647 | 7879 | 62.7416 | 101 | 0.019348 | 79
WEST POINT 11021341 | WEST POINT 1102 | 163201102 | FALSE | 9.7908 | 0.32075 | 10.1115 | 172.5 | 0.00023505 | 9387 | 80.5551 | 37 | 0.019265 | 80
EL DORADO PH 2101CB | EL DORADO PH 2101 | 152762101 | FALSE | 7.2823 | 0.45914 | 7.7414 | 114.8333 | 0.00039884 | 6466 | 52.3222 | 155 | 0.019264 | 81
MARIPOSA 2101CB | MARIPOSA 2101 | 254452101 | FALSE | 2.4592 | 0.27085 | 2.73 | 44 | 0.00042902 | 6130 | 46.0007 | 192 | 0.019246 | 82
KESWICK 11011588 | KESWICK 1101 | 103451101 | FALSE | 8.7083 | 0.1505 | 8.8034 | 171.5 | 0.00034687 | 7190 | 57.8766 | 124 | 0.019054 | 83
BALCH NO 1 1101406582 | BALCH NO 1 1101 | 252501101 | FALSE | 3.6869 | 0.098013 | 3.7849 | 73 | 0.0001919 | 10180 | 94.7849 | 12 | 0.019009 | 84
ELK CREEK 11012032 | ELK CREEK 1101 | 102781101 | FALSE | 9.3496 | 0.40717 | 8.8944 | 178.5 | 0.00022491 | 9611 | 83.9069 | 28 | 0.018987 | 85
WILDWOOD 11011454 | WILDWOOD 1101 | 103611101 | FALSE | 7.7772 | 0.16237 | 7.9395 | 153 | 0.00019718 | 10085 | 97.0843 | 9 | 0.018983 | 86
SILVERADO 2105658898 | SILVERADO 2105 | 43432105 | FALSE | 16.8969 | 0.53268 | 17.4296 | 325.5 | 0.00063933 | 3832 | 28.564 | 392 | 0.018978 | 87
FRENCH GULCH 11011464 | FRENCH GULCH 1101 | 103381101 | FALSE | 0.86423 | 0.038506 | 0.90273 | 17 | 0.00025383 | 9001 | 73.5639 | 54 | 0.018889 | 88
SHADY GLEN 110248894 | SHADY GLEN 1102 | 152431102 | FALSE | 11.4113 | 1.3573 | 11.4474 | 212 | 0.00034233 | 7270 | 59.4258 | 118 | 0.018876 | 89
SILVERADO 2105900104 | SILVERADO 2105 | 43432105 | TRUE | 0.10732 | 0.019634 | 0.1244 | 1.5 | 0.00080633 | 1929 | 23.2981 | 489 | 0.018786 | 90
ANTLER 11011520 | ANTLER 1101 | 103271101 | FALSE | 8.9409 | 0.55204 | 9.4929 | 169 | 0.0004806 | 5597 | 38.8252 | 265 | 0.018782 | 91
MIWUK 170111800 | MIWUK 1701 | 163661701 | FALSE | 9.5064 | 2.2513 | 11.7576 | 158.5 | 0.00049839 | 5407 | 44.1384 | 204 | 0.018751 | 92
SHADY GLEN 11022232 | SHADY GLEN 1102 | 152431102 | FALSE | 19.7286 | 2.2482 | 21.9767 | 377 | 0.00049543 | 5440 | 41.0226 | 235 | 0.018723 | 93
ANTLER 1101CB | ANTLER 1101 | 103271101 | FALSE | 1.5904 | 0.03706 | 1.6274 | 25.5 | 0.00047152 | 5684 | 37.9955 | 274 | 0.0187 | 94
STANISLAUS 1701CB | STANISLAUS 1701 | 162821701 | FALSE | 36.4691 | 2.014 | 38.2338 | 655 | 0.00023742 | 9335 | 79.3601 | 39 | 0.018647 | 95
PLACERVILLE 210692012 | PLACERVILLE 2106 | 153082106 | FALSE | 18.4325 | 1.9873 | 20.4197 | 340 | 0.00053524 | 5007 | 33.2363 | 329 | 0.018499 | 96
FORESTHILL 11022106 | FORESTHILL 1102 | 152181102 | FALSE | 27.8705 | 1.2393 | 29.1097 | 532 | 0.00028237 | 8365 | 71.3911 | 65 | 0.018495 | 97
STANISLAUS 170237278 | STANISLAUS 1702 | 162821702 | FALSE | 6.7927 | 0.69283 | 7.4855 | 106 | 0.00074389 | 2565 | 27.3647 | 416 | 0.01848 | 98
MIDDLETOWN 1101433160 | MIDDLETOWN 1101 | 43141101 | FALSE | 1.5408 | 0.13294 | 1.2518 | 32.8333 | 0.00035153 | 7115 | 54.6557 | 142 | 0.018456 | 99
CLAYTON 2212614950 | CLAYTON 2212 | 12022212 | FALSE | 1.4029 | 0.035846 | 0.67567 | 24.5 | 0.0004155 | 6269 | 60.7429 | 110 | 0.018211 | 100
SILVERADO 210478268 | SILVERADO 2104 | 43432104 | FALSE | 11.4487 | 2.1667 | 13.6153 | 219.8333 | 0.00083985 | 1649 | 22.9751 | 495 | 0.018153 | 101
MIDDLETOWN 1101548 | MIDDLETOWN 1101 | 43141101 | FALSE | 28.1417 | 6.0741 | 32.6793 | 520 | 0.00035154 | 7114 | 61.8677 | 105 | 0.018129 | 102
DRUM 1101CB | DRUM 1101 | 152321101 | FALSE | 2.1646 | 0 | 2.1646 | 38.5 | 0.00037646 | 6743 | 50.188 | 166 | 0.018102 | 103
PIT NO 5 1101CB | PIT NO 5 1101 | 101321101 | FALSE | 0.744 | 0.22706 | 0.97105 | 14.5 | 0.00047809 | 5620 | 36.9776 | 281 | 0.01767 | 104
CALISTOGA 110143924 | CALISTOGA 1101 | 42711101 | FALSE | 9.3913 | 1.5795 | 8.6373 | 177.5 | 0.00068769 | 3253 | 23.902 | 475 | 0.017566 | 105
MOUNTAIN QUARRIES 2101CB | MOUNTAIN QUARRIES 2101 | 152282101 | TRUE | 0.016109 | 0 | 0.016109 | 1.5 | 0.00027183 | 8611 | 64.6171 | 91 | 0.017565 | 106
WEST POINT 11014706 | WEST POINT 1101 | 163201101 | FALSE | 11.4709 | 2.4448 | 13.9157 | 216 | 0.00046041 | 5802 | 40.0928 | 248 | 0.017455 | 107
BIG BEND 1101180398 | BIG BEND 1101 | 103751101 | FALSE | 5.3451 | 0.09098 | 5.4361 | 93 | 0.00024924 | 9096 | 65.3077 | 85 | 0.017411 | 108
WILDWOOD 110198896 | WILDWOOD 1101 | 103611101 | FALSE | 5.0272 | 0.22418 | 5.2514 | 100 | 0.00021996 | 9698 | 78.6557 | 41 | 0.017355 | 109
WEST POINT 110277204 | WEST POINT 1102 | 163201102 | FALSE | 7.4433 | 0.27248 | 7.7158 | 140 | 0.00027086 | 8630 | 67.2471 | 76 | 0.017351 | 110
WILDWOOD 1101384582 | WILDWOOD 1101 | 103611101 | FALSE | 4.5387 | 0 | 4.5387 | 87.5 | 0.00019024 | 10210 | 89.93 | 16 | 0.017225 | 111
COLUMBIA HILL 110135424 | COLUMBIA HILL 1101 | 152471101 | FALSE | 13.8934 | 1.7492 | 15.6426 | 263 | 0.00034658 | 7196 | 46.2072 | 190 | 0.017167 | 112
SO. CAL. EDISON #3 1101CB | SO. CAL. EDISON #3 1101 | 258861101 | FALSE | 8.1187 | 0.015782 | 8.1344 | 156 | 0.00019072 | 10200 | 89.3192 | 17 | 0.017011 | 113
FORESTHILL 110150486 | FORESTHILL 1101 | 152181101 | FALSE | 11.6351 | 3.1985 | 14.8336 | 228 | 0.00052446 | 5132 | 36.5699 | 284 | 0.01695 | 114
CLAYTON 2212681608 | CLAYTON 2212 | 12022212 | FALSE | 26.818 | 6.6762 | 33.2135 | 513 | 0.00022419 | 9623 | 72.9362 | 57 | 0.016899 | 115
PIKE CITY 1101CB | PIKE CITY 1101 | 152201101 | FALSE | 19.67 | 2.1993 | 21.8692 | 373.5 | 0.00038416 | 6648 | 44.6119 | 200 | 0.016874 | 116
SILVERADO 2105990552 | SILVERADO 2105 | 43432105 | TRUE | 0.61356 | 0.31293 | 0.59582 | 13 | 0.00097465 | 896 | 18.0691 | 597 | 0.016818 | 117
ELECTRA 1101L1697 | ELECTRA 1101 | 162161101 | FALSE | 5.7665 | 1.2435 | 7.01 | 113.5 | 0.00020425 | 9970 | 82.8752 | 32 | 0.016781 | 118
KESWICK 110148480 | KESWICK 1101 | 103451101 | FALSE | 10.5204 | 0.61144 | 11.1318 | 173 | 0.00040039 | 6452 | 41.7821 | 229 | 0.016757 | 119
SHADY GLEN 11012768 | SHADY GLEN 1101 | 152431101 | FALSE | 8.0771 | 0.96593 | 7.9445 | 146.5 | 0.00032041 | 7622 | 57.7052 | 125 | 0.016673 | 120
EL DORADO PH 2102542272 | EL DORADO PH 2102 | 152762102 | FALSE | 7.7436 | 0.29615 | 8.0398 | 138 | 0.00062626 | 3986 | 27.4396 | 414 | 0.016629 | 121
PEORIA 170190090 | PEORIA 1701 | 163781701 | FALSE | 29.8614 | 1.0393 | 30.4758 | 573 | 0.00020691 | 9934 | 75.8685 | 47 | 0.016615 | 122
FROGTOWN 1702815616 | FROGTOWN 1702 | 163451702 | FALSE | 0.99205 | 0 | 0.99205 | 18.3333 | 0.00027343 | 8568 | 65.2429 | 86 | 0.016505 | 123
APPLE HILL 110413512 | APPLE HILL 1104 | 153661104 | FALSE | 30.2001 | 4.1058 | 31.4056 | 546.5 | 0.00049189 | 5474 | 36.1339 | 291 | 0.016427 | 124
BEAR VALLEY 21059570 | BEAR VALLEY 2105 | 252192105 | FALSE | 7.9708 | 0.36437 | 8.3351 | 161 | 0.00016167 | 10578 | 92.897 | 14 | 0.016409 | 125
MARIPOSA 210110240 | MARIPOSA 2101 | 254452101 | FALSE | 19.8722 | 1.2046 | 21.0767 | 385 | 0.00019523 | 10127 | 85.9701 | 21 | 0.016323 | 126
REDBUD 1101323962 | REDBUD 1101 | 43191101 | FALSE | 28.5898 | 3.0425 | 21.228 | 553.5 | 0.0002042 | 9971 | 79.8595 | 38 | 0.016255 | 127
ALLEGHANY 1101VR816 | ALLEGHANY 1101 | 152101101 | FALSE | 4.0965 | 2.0846 | 6.1811 | 74 | 0.00057388 | 4604 | 30.7649 | 362 | 0.016217 | 128
ORO FINO 11022236 | ORO FINO 1102 | 103031102 | FALSE | 2.5364 | 0.039435 | 2.5758 | 45 | 0.00023716 | 9338 | 71.9828 | 64 | 0.016201 | 129
MONTICELLO 11011780 | MONTICELLO 1101 | 43051101 | TRUE | 0.071663 | 0 | 0.071662 | 0.33333 | 0.00056695 | 4691 | 28.4539 | 395 | 0.016132 | 130
PINE GROVE 11026080 | PINE GROVE 1102 | 163751102 | FALSE | 34.3486 | 0.57549 | 34.9239 | 621.5 | 0.00024691 | 9146 | 60.5795 | 111 | 0.016072 | 131
APPLE HILL 2102836878 | APPLE HILL 2102 | 153662102 | FALSE | 40.8369 | 3.1006 | 43.9374 | 751 | 0.00038931 | 6581 | 43.3733 | 213 | 0.01606 | 132
SALT SPRINGS 210297924 | SALT SPRINGS 2102 | 163692102 | FALSE | 5.2013 | 1.2667 | 6.468 | 92.8333 | 0.00089918 | 1237 | 17.1056 | 621 | 0.016045 | 133
CALISTOGA 1101122350 | CALISTOGA 1101 | 42711101 | FALSE | 13.4533 | 1.073 | 14.5262 | 252 | 0.00059745 | 4335 | 26.9987 | 422 | 0.016019 | 134
KESWICK 11011590 | KESWICK 1101 | 103451101 | FALSE | 6.2972 | 0.19335 | 6.4906 | 117 | 0.00030382 | 7935 | 49.4249 | 170 | 0.015989 | 135
NARROWS 2104CB | NARROWS 2104 | 153132104 | TRUE | 0.0028409 | 0 | 0.0028409 | 0.25 | 0.00038958 | 6579 | 41.0166 | 236 | 0.015979 | 136
MARIPOSA 210110170 | MARIPOSA 2101 | 254452101 | FALSE | 16.1371 | 0.97599 | 17.113 | 305.5 | 0.00024166 | 9255 | 65.2073 | 87 | 0.015939 | 137
COLUMBIA HILL 1101CB | COLUMBIA HILL 1101 | 152471101 | FALSE | 44.1613 | 2.6109 | 41.488 | 845.5 | 0.00028242 | 8364 | 59.6284 | 116 | 0.015927 | 138
PINE GROVE 11023172 | PINE GROVE 1102 | 163751102 | FALSE | 9.4625 | 1.0442 | 10.5066 | 162 | 0.0004098 | 6337 | 43.6274 | 208 | 0.015893 | 139
ORO FINO 110265932 | ORO FINO 1102 | 103031102 | FALSE | 11.2245 | 0.63512 | 5.018 | 199 | 0.00032974 | 7453 | 49.8949 | 167 | 0.015891 | 140
COLUMBIA HILL 11012212 | COLUMBIA HILL 1101 | 152471101 | FALSE | 8.4346 | 0.44979 | 8.8844 | 165 | 0.00041036 | 6330 | 39.9615 | 252 | 0.015814 | 141
WEIMAR 11012084 | WEIMAR 1101 | 152491101 | FALSE | 18.5776 | 1.485 | 20.0626 | 344.5 | 0.00029634 | 8076 | 55.7799 | 137 | 0.015811 | 142
ANTLER 11011612 | ANTLER 1101 | 103271101 | FALSE | 7.9154 | 0.52714 | 8.1983 | 158.5 | 0.00026652 | 8730 | 55.9545 | 135 | 0.015772 | 143
HIGHLANDS 1103726580 | HIGHLANDS 1103 | 43361103 | FALSE | 8.5171 | 0.17786 | 8.0477 | 160 | 0.00018134 | 10332 | 84.7139 | 24 | 0.015697 | 144
APPLE HILL 21029722 | APPLE HILL 2102 | 153662102 | FALSE | 38.1954 | 2.0555 | 40.2507 | 725.5 | 0.00025679 | 8947 | 58.1071 | 122 | 0.01567 | 145
MIDDLETOWN 1101932140 | MIDDLETOWN 1101 | 43141101 | FALSE | 0.95294 | 0.94679 | 1.1572 | 20.8333 | 0.0005789 | 4538 | 28.4179 | 396 | 0.015654 | 146
PINE GROVE 11013166 | PINE GROVE 1101 | 163751101 | FALSE | 12.1497 | 0.83361 | 12.9832 | 223 | 0.00026648 | 8731 | 54.714 | 141 | 0.015597 | 147
PLACERVILLE 111219712 | PLACERVILLE 1112 | 153081112 | FALSE | 12.9786 | 1.2914 | 14.0596 | 235.3333 | 0.00033037 | 7443 | 50.3179 | 165 | 0.015591 | 148
COLUMBIA HILL 1101764 | COLUMBIA HILL 1101 | 152471101 | FALSE | 14.691 | 0.87736 | 15.5683 | 286 | 0.00031012 | 7803 | 50.5888 | 163 | 0.015567 | 149
ORO FINO 11022090 | ORO FINO 1102 | 103031102 | FALSE | 14.8409 | 2.629 | 17.4699 | 258.5 | 0.00049483 | 5446 | 35.1964 | 308 | 0.015441 | 150
TIGER CREEK 0201320746 | TIGER CREEK 0201 | 161380201 | FALSE | 3.5158 | 0 | 3.5158 | 73.5 | 0.00022353 | 9637 | 68.7315 | 73 | 0.015433 | 151
KONOCTI 1102806668 | KONOCTI 1102 | 43311102 | FALSE | 2.0853 | 0.40769 | 2.4929 | 34 | 0.00077632 | 2190 | 22.5036 | 505 | 0.015365 | 152
KESWICK 1101CB | KESWICK 1101 | 103451101 | TRUE | 0.016571 | 0 | 0.016571 | 0.5 | 0.00096214 | 947 | 15.9638 | 640 | 0.015359 | 153
WEST POINT 110236676 | WEST POINT 1102 | 163201102 | FALSE | 16.6363 | 0.81093 | 17.4472 | 306 | 0.0002891 | 8214 | 53.2627 | 148 | 0.015203 | 154
NOTRE DAME 1104176446 | NOTRE DAME 1104 | 102041104 | FALSE | 8.505 | 0.33059 | 8.8356 | 166.5 | 0.00032334 | 7572 | 43.8382 | 207 | 0.015172 | 155
HIGHLANDS 1103287766 | HIGHLANDS 1103 | 43361103 | FALSE | 17.1622 | 0.039891 | 16.9784 | 331.5 | 0.00018144 | 10326 | 84.0775 | 25 | 0.015099 | 156
KANAKA 1101859138 | KANAKA 1101 | 103221101 | FALSE | 6.2333 | 0.029182 | 6.2211 | 116.5 | 0.00034071 | 7295 | 49.7024 | 168 | 0.015062 | 157
ORO FINO 1101CB | ORO FINO 1101 | 103031101 | FALSE | 22.6501 | 8.965 | 31.615 | 367 | 0.00076107 | 2368 | 20.6589 | 544 | 0.015008 | 158
PARADISE 1105829194 | PARADISE 1105 | 102831105 | FALSE | 11.3666 | 5.0989 | 16.4654 | 187 | 0.00059544 | 4355 | 26.1321 | 434 | 0.014996 | 159
MIDDLETOWN 1101959140 | MIDDLETOWN 1101 | 43141101 | FALSE | 3.9356 | 0.035496 | 3.9711 | 76.5 | 0.00020921 | 9885 | 64.8069 | 88 | 0.014882 | 160
PINE GROVE 1102CB | PINE GROVE 1102 | 163751102 | FALSE | 10.8158 | 1.4116 | 12.2273 | 193.5 | 0.00035688 | 7027 | 46.1645 | 191 | 0.014761 | 161
PIKE CITY 1102CB | PIKE CITY 1102 | 152201102 | FALSE | 9.5167 | 0.33318 | 9.8499 | 180.5 | 0.00039219 | 6539 | 40.5015 | 242 | 0.0147 | 162
HIGHLANDS 1101CB | HIGHLANDS 1101 | 43361101 | TRUE | 0.029873 | 0 | 0.029873 | 0.58333 | 0.0011435 | 375 | 12.8413 | 732 | 0.014683 | 163
WEST POINT 11024788 | WEST POINT 1102 | 163201102 | FALSE | 72.2384 | 2.2249 | 70.904 | 1350 | 0.00019713 | 10089 | 74.362 | 51 | 0.014654 | 164
MOUNTAIN QUARRIES 21012422 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 8.5438 | 0.25662 | 8.8004 | 157 | 0.0003166 | 7691 | 43.3262 | 214 | 0.014598 | 165
WEIMAR 11012058 | WEIMAR 1101 | 152491101 | FALSE | 24.5192 | 2.2378 | 26.757 | 452 | 0.00037664 | 6739 | 38.0373 | 273 | 0.014596 | 166
APPLE HILL 210251792 | APPLE HILL 2102 | 153662102 | FALSE | 9.257 | 1.0339 | 10.2805 | 168 | 0.00035443 | 7067 | 40.5143 | 241 | 0.014392 | 167
HARTLEY 11014710 | HARTLEY 1101 | 43211101 | FALSE | 1.5223 | 0.073146 | 1.5954 | 25.5 | 0.00030291 | 7949 | 48.8086 | 173 | 0.014369 | 168
CALPINE 1144CB | CALPINE 1144 | 48011144 | FALSE | 26.765 | 0.31278 | 27.0777 | 481.8333 | 0.00024214 | 9243 | 58.2794 | 121 | 0.014299 | 169
ALLEGHANY 1101CB | ALLEGHANY 1101 | 152101101 | FALSE | 4.3611 | 1.6919 | 6.053 | 91.8333 | 0.00047598 | 5639 | 30.5875 | 364 | 0.014158 | 170
TULE POWER HOUSE 1101CB | TULE POWER HOUSE 1101 | 258591101 | FALSE | 4.0705 | 0.18699 | 4.2575 | 83 | 0.000219 | 9719 | 68.218 | 74 | 0.014129 | 171
OAKHURST 11015490 | OAKHURST 1101 | 254421101 | FALSE | 24.6359 | 2.9635 | 27.5869 | 459 | 0.00029064 | 8183 | 49.4842 | 169 | 0.014056 | 172
NARROWS PH 1151CB | NARROWS PH 1151 | 153131151 | TRUE | 0.19775 | 0 | 0.19775 | 2.3333 | 0.00034029 | 7302 | 41.0384 | 233 | 0.013968 | 173
MIDDLETOWN 1101439572 | MIDDLETOWN 1101 | 43141101 | FALSE | 1.2561 | 0.44378 | 1.5926 | 23.8333 | 0.00040673 | 6374 | 35.8067 | 294 | 0.013914 | 174
MIDDLETOWN 1101352182 | MIDDLETOWN 1101 | 43141101 | FALSE | 2.0574 | 0.028071 | 2.0855 | 41 | 0.00030076 | 8004 | 45.3975 | 197 | 0.013904 | 175
EL DORADO PH 210219542 | EL DORADO PH 2102 | 152762102 | FALSE | 9.4781 | 2.3021 | 11.7801 | 162.5 | 0.00071023 | 2973 | 19.8766 | 558 | 0.013848 | 176
MOUNTAIN QUARRIES 210192474 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 15.3488 | 0.72176 | 15.2703 | 280.5 | 0.0003887 | 6594 | 35.1098 | 309 | 0.013764 | 177
LOS OSITOS 21033010 | LOS OSITOS 2103 | 182082103 | FALSE | 30.0247 | 4.3942 | 34.3363 | 620 | 0.00018362 | 10297 | 72.2504 | 63 | 0.013726 | 178
FORESTHILL 11011802 | FORESTHILL 1101 | 152181101 | FALSE | 22.1876 | 3.3492 | 25.5367 | 421 | 0.00048942 | 5503 | 31.155 | 354 | 0.013637 | 179
SHADY GLEN 1102CB | SHADY GLEN 1102 | 152431102 | FALSE | 21.1169 | 2.3332 | 22.9323 | 393.5 | 0.00039013 | 6571 | 39.6978 | 259 | 0.01361 | 180
ORO FINO 11022556 | ORO FINO 1102 | 103031102 | FALSE | 6.6456 | 1.9352 | 8.5808 | 138.5 | 0.0005672 | 4688 | 23.5786 | 483 | 0.013572 | 181
MIDDLETOWN 11014646 | MIDDLETOWN 1101 | 43141101 | FALSE | 23.5712 | 1.404 | 15.9247 | 454.5 | 0.00030886 | 7825 | 47.2919 | 179 | 0.013549 | 182
OAKHURST 110310723 | OAKHURST 1103 | 254421103 | TRUE | 0.0039404 | 0 | 0.0039404 | 0.33333 | 0.0013211 | 189 | 10.2271 | 826 | 0.013511 | 183
CALAVERAS CEMENT 11014786 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 17.7888 | 0.775 | 18.5638 | 348 | 0.00017022 | 10482 | 77.371 | 44 | 0.013502 | 184
MIDDLETOWN 1101644756 | MIDDLETOWN 1101 | 43141101 | FALSE | 18.3135 | 0.59992 | 6.1785 | 348.8333 | 0.00030136 | 7982 | 45.7535 | 194 | 0.013349 | 185
STANISLAUS 17011331 | STANISLAUS 1701 | 162821701 | FALSE | 4.3891 | 0.77334 | 5.1624 | 68 | 0.00075949 | 2395 | 15.2531 | 653 | 0.013343 | 186
BIG BEND 1102CB | BIG BEND 1102 | 103751102 | FALSE | 17.3311 | 0.37381 | 17.4826 | 303.8333 | 0.00028822 | 8229 | 42.5471 | 218 | 0.013302 | 187
MONTICELLO 1101720 | MONTICELLO 1101 | 43051101 | FALSE | 8.1324 | 0.23789 | 6.9678 | 161 | 0.00023869 | 9310 | 55.5258 | 139 | 0.013232 | 188
HARTLEY 1101336932 | HARTLEY 1101 | 43211101 | FALSE | 8.4794 | 0.30044 | 8.5123 | 158 | 0.00021064 | 9866 | 63.0279 | 99 | 0.013202 | 189
APPLE HILL 11038412 | APPLE HILL 1103 | 153661103 | FALSE | 19.6178 | 1.3464 | 20.9642 | 369.5 | 0.0003479 | 7175 | 35.7864 | 295 | 0.013168 | 190
WILDWOOD 11011576 | WILDWOOD 1101 | 103611101 | FALSE | 8.062 | 0.4223 | 8.4843 | 161.5 | 0.00041482 | 6284 | 32.1012 | 343 | 0.013119 | 191
BONNIE NOOK 1102CB | BONNIE NOOK 1102 | 152301102 | FALSE | 34.0026 | 4.3904 | 38.3929 | 646 | 0.00042831 | 6138 | 39.7651 | 258 | 0.013013 | 192
LOS OSITOS 21037014 | LOS OSITOS 2103 | 182082103 |  | 39.719 | 0.81683 |  | 806.5 | 0.00013563 | 10835 | 95.1294 | 11 | 0.012994 | 193
CORNING 110185152 | CORNING 1101 | 103331101 | FALSE | 23.071 | 2.6055 | 25.6764 | 438.5 | 0.00024703 | 9145 | 52.7051 | 152 | 0.012991 | 194
EL DORADO PH 210219562 | EL DORADO PH 2102 | 152762102 | FALSE | 2.8622 | 0.52152 | 3.3837 | 42.5 | 0.00095532 | 987 | 13.635 | 705 | 0.012963 | 195
SHINGLE SPRINGS 2108CB | SHINGLE SPRINGS 2108 | 153652108 | FALSE | 1.428 | 0.10115 | 1.5227 | 24.6667 | 0.0011123 | 452 | 10.5549 | 815 | 0.012917 | 196
APPLE HILL 110497086 | APPLE HILL 1104 | 153661104 | FALSE | 25.5648 | 2.8586 | 28.4233 | 480.5 | 0.00029062 | 8184 | 44.4785 | 203 | 0.012828 | 197
CALAVERAS CEMENT 11011419 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 14.8876 | 0.58967 | 15.4772 | 286 | 0.0001512 | 10690 | 86.1291 | 20 | 0.012702 | 198
MARIPOSA 2101752630 | MARIPOSA 2101 | 254452101 | FALSE | 18.7528 | 0.56707 | 19.3198 | 357 | 0.00013417 | 10847 | 94.5826 | 13 | 0.012689 | 199
CLEAR LAKE 1102904 | CLEAR LAKE 1102 | 42141102 | FALSE | 3.5481 | 0.10124 | 2.9951 | 64 | 0.00030442 | 7922 | 39.4532 | 260 | 0.012549 | 200
PARADISE 1104954322 | PARADISE 1104 | 102831104 | FALSE | 2.8216 | 0.55699 | 3.3785 | 53.5 | 0.00057424 | 4598 | 27.1156 | 420 | 0.012514 | 201
TASSAJARA 2112791386 | TASSAJARA 2112 | 14662112 | FALSE | 2.4112 | 0.067702 | 2.4789 | 47 | 0.00025382 | 9002 | 46.578 | 187 | 0.012505 | 202
SILVERADO 2104726 | SILVERADO 2104 | 43432104 | FALSE | 33.6539 | 1.4817 | 28.0868 | 650.5 | 0.00024366 | 9208 | 53.0116 | 151 | 0.012452 | 203
PINE GROVE 110213438 | PINE GROVE 1102 | 163751102 | FALSE | 16.5261 | 0.87301 | 17.3991 | 287 | 0.0004077 | 6361 | 35.3911 | 305 | 0.012447 | 204
BEAR VALLEY 2101CB | BEAR VALLEY 2101 | 252192101 | FALSE | 18.1114 | 1.1088 | 19.2201 | 349.5 | 0.00027977 | 8424 | 42.2882 | 222 | 0.012382 | 205
WEST POINT 11021305 | WEST POINT 1102 | 163201102 | FALSE | 11.3098 | 0.54612 | 11.8559 | 213.5 | 0.00034511 | 7220 | 39.7916 | 257 | 0.012287 | 206
WISHON 1101CB | WISHON 1101 | 251511101 | FALSE | 7.553 | 0.64306 | 7.9792 | 148.5 | 0.00021378 | 9802 | 56.6018 | 130 | 0.012162 | 207
SHADY GLEN 110151696 | SHADY GLEN 1101 | 152431101 | FALSE | 18.3265 | 2.4906 | 17.7045 | 332 | 0.0003953 | 6506 | 36.495 | 285 | 0.012161 | 208
GIRVAN 11019732 | GIRVAN 1101 | 103401101 | FALSE | 20.9965 | 0.95944 | 21.9559 | 382.5 | 0.000346 | 7206 | 38.5367 | 269 | 0.012148 | 209
ANTLER 11011376 | ANTLER 1101 | 103271101 | FALSE | 9.175 | 0.17301 | 9.348 | 184.5 | 0.0002199 | 9699 | 53.0254 | 150 | 0.012094 | 210
MIDDLETOWN 1101614 | MIDDLETOWN 1101 | 43141101 | FALSE | 1.3822 | 0.72627 | 2.1084 | 25 | 0.00069119 | 3205 | 17.5222 | 611 | 0.01209 | 211
KANAKA 1101CB | KANAKA 1101 | 103221101 | FALSE | 41.2802 | 0.41135 | 40.9653 | 694 | 0.00025958 | 8891 | 44.58 | 201 | 0.01209 | 212
WEST POINT 11024790 | WEST POINT 1102 | 163201102 | FALSE | 32.5359 | 2.8049 | 35.3406 | 605.5 | 0.00038675 | 6623 | 36.2859 | 289 | 0.012049 | 213
WEIMAR 1101CB | WEIMAR 1101 | 152491101 | FALSE | 9.2257 | 1.6872 | 10.9129 | 157.5 | 0.00050647 | 5323 | 23.1822 | 492 | 0.012028 | 214
MOUNTAIN QUARRIES 21011180 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 12.9561 | 0.89247 | 13.8486 | 230.3333 | 0.00035293 | 7090 | 35.4379 | 304 | 0.011942 | 215
MIWUK 17021808 | MIWUK 1702 | 163661702 | FALSE | 1.8076 | 1.4012 | 3.2072 | 34 | 0.00065399 | 3656 | 18.5994 | 581 | 0.011878 | 216
CALAVERAS CEMENT 11012646 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 17.5628 | 0.57173 | 18.1345 | 331 | 0.00017503 | 10421 | 72.3536 | 62 | 0.011871 | 217
WEST POINT 1101CB | WEST POINT 1101 | 163201101 | FALSE | 4.7928 | 0.051649 | 4.8444 | 95.5 | 0.00032986 | 7450 | 41.712 | 230 | 0.011836 | 218
TEJON 1102732836 | TEJON 1102 | 252931102 | FALSE | 15.5796 | 1.7846 | 17.3641 | 299.5 | 0.00051412 | 5243 | 20.2277 | 553 | 0.011818 | 219
STILLWATER 11021466 | STILLWATER 1102 | 103561102 | FALSE | 20.397 | 3.2287 | 23.5347 | 382.5 | 0.00022575 | 9588 | 40.8316 | 238 | 0.011789 | 220
BUTTE 1105398234 | BUTTE 1105 | 103081105 | FALSE | 15.0803 | 0.46905 | 10.2382 | 266.5 | 0.00019907 | 10059 | 55.5708 | 138 | 0.011775 | 221
LUCERNE 1103245134 | LUCERNE 1103 | 43351103 | FALSE | 5.0029 | 0.69806 | 5.163 | 91.5 | 0.00029431 | 8121 | 42.4037 | 221 | 0.011774 | 222
CLAYTON 2212204416 | CLAYTON 2212 | 12022212 | FALSE | 11.7586 | 1.1104 | 12.869 | 230 | 0.00023075 | 9468 | 47.129 | 183 | 0.011731 | 223
PIT NO 5 110190846 | PIT NO 5 1101 | 101321101 | TRUE | 0.088249 | 0 | 0.088249 | 1.5 | 0.00032613 | 7519 | 35.643 | 301 | 0.011624 | 224
SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 18.052 | 1.0022 | 19.0541 | 323 | 0.00030402 | 7930 | 43.4303 | 210 | 0.011577 | 225
FROGTOWN 170113412 | FROGTOWN 1701 | 163451701 | FALSE | 38.8027 | 4.2513 | 43.0539 | 727.5 | 0.00024619 | 9159 | 65.4876 | 84 | 0.011574 | 226
FRENCH GULCH 11012905 | FRENCH GULCH 1101 | 103381101 | FALSE | 9.5145 | 0.42789 | 9.9424 | 177.5 | 0.00020802 | 9912 | 54.2668 | 145 | 0.011565 | 227
TEMPLETON 2113A10 | TEMPLETON 2113 | 183052113 | FALSE | 30.7752 | 1.1097 | 31.8849 | 584.5 | 0.00015153 | 10683 | 73.2869 | 56 | 0.011532 | 228
UKIAH 1113968652 | UKIAH 1113 | 42771113 | FALSE | 1.8875 | 0.72157 | 1.1553 | 29.5 | 0.00040326 | 6418 | 34.9485 | 310 | 0.011507 | 229
PLACERVILLE 2106CB | PLACERVILLE 2106 | 153082106 | FALSE | 6.4582 | 0.086063 | 6.2833 | 112.1667 | 0.00048359 | 5564 | 28.5061 | 393 | 0.011469 | 230
STANISLAUS 170179826 | STANISLAUS 1701 | 162821701 | FALSE | 10.1921 | 0.88318 | 11.0752 | 189.5 | 0.00037556 | 6754 | 36.4757 | 286 | 0.011425 | 231
FORESTHILL 1101CB | FORESTHILL 1101 | 152181101 | FALSE | 9.0779 | 2.7419 | 11.8197 | 170.5 | 0.00064056 | 3816 | 20.3006 | 552 | 0.011424 | 232
PINE GROVE 110245292 | PINE GROVE 1102 | 163751102 | FALSE | 10.7857 | 1.274 | 12.0597 | 191.5 | 0.00040866 | 6348 | 35.4936 | 303 | 0.011408 | 233
BRUNSWICK 11021010 | BRUNSWICK 1102 | 152481102 | FALSE | 44.5228 | 2.5955 | 47.1181 | 802 | 0.00034306 | 7260 | 41.9673 | 225 | 0.011407 | 234
BALCH NO 1 1101R372 | BALCH NO 1 1101 | 252501101 | FALSE | 3.8992 | 0.03532 | 3.9345 | 80.5 | 0.00019376 | 10146 | 58.4821 | 119 | 0.011393 | 235
PLACERVILLE 21069712 | PLACERVILLE 2106 | 153082106 | FALSE | 24.6861 | 1.5038 | 26.1899 | 483.5 | 0.00040577 | 6384 | 28.6157 | 391 | 0.011373 | 236
SHINGLE SPRINGS 210911092 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 22.0883 | 1.6891 | 23.7773 | 400.5 | 0.00029672 | 8069 | 46.8181 | 185 | 0.011346 | 237
CALPINE 1144960 | CALPINE 1144 | 48011144 | FALSE | 4.0614 | 0 | 4.0614 | 65.8333 | 0.00015113 | 10691 | 76.8978 | 46 | 0.011276 | 238
BEAR VALLEY 2105293732 | BEAR VALLEY 2105 | 252192105 | FALSE | 26.0604 | 2.8908 | 28.9512 | 508 | 0.00017227 | 10453 | 66.8308 | 77 | 0.011118 | 239
PINE GROVE 110194936 | PINE GROVE 1101 | 163751101 | FALSE | 9.1551 | 0.18106 | 9.3362 | 169 | 0.00022817 | 9533 | 50.9181 | 161 | 0.011105 | 240
SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 11.3804 | 0.71746 | 12.0979 | 205 | 0.00023284 | 9429 | 49.0685 | 172 | 0.011098 | 241
MARIPOSA 2101439030 | MARIPOSA 2101 | 254452101 | FALSE | 19.5831 | 1.6937 | 21.2767 | 361 | 0.00023631 | 9354 | 44.5348 | 202 | 0.01102 | 242
WEST POINT 110272036 | WEST POINT 1102 | 163201102 | FALSE | 13.1539 | 0.61524 | 13.2666 | 246.5 | 0.00020077 | 10031 | 64.2755 | 93 | 0.01094 | 243
BIG BEND 1101CB | BIG BEND 1101 | 103751101 | FALSE | 23.1433 | 0.4968 | 23.6401 | 430.3333 | 0.00022731 | 9556 | 54.6159 | 143 | 0.010938 | 244
BANGOR 1101626862 | BANGOR 1101 | 103191101 | FALSE | 11.2783 | 0.68059 | 11.9588 | 208 | 0.00026858 | 8684 | 41.0339 | 234 | 0.010936 | 245
TASSAJARA 21123202 | TASSAJARA 2112 | 14662112 | TRUE | 0.39411 | 0.012472 | 0.40658 | 8.5 | 0.00017323 | 10443 | 62.8224 | 100 | 0.010934 | 246
ANTLER 11011378 | ANTLER 1101 | 103271101 | FALSE | 24.904 | 1.4862 | 25.7133 | 473.5 | 0.00023776 | 9327 | 43.601 | 209 | 0.010915 | 247
GRASS VALLEY 11012208 | GRASS VALLEY 1101 | 152031101 | FALSE | 12.8805 | 1.341 | 13.1655 | 230.5 | 0.00059503 | 4363 | 16.5277 | 630 | 0.010913 | 248
MARIPOSA 2101151918 | MARIPOSA 2101 | 254452101 | FALSE | 16.5872 | 0.72921 | 17.3163 | 331.75 | 0.00019037 | 10206 | 57.1337 | 127 | 0.010861 | 249
WYANDOTTE 1103640652 | WYANDOTTE 1103 | 102911103 | FALSE | 34.4733 | 1.2472 | 35.7204 | 632.5 | 0.00039792 | 6478 | 33.5264 | 327 | 0.010796 | 250
ELECTRA 1101CB | ELECTRA 1101 | 162161101 | FALSE | 23.2606 | 0.65642 | 23.917 | 434.5 | 0.00017445 | 10429 | 59.7672 | 113 | 0.010795 | 251
PUTAH CREEK 110264044 | PUTAH CREEK 1102 | 63681102 | FALSE | 7.4872 | 0.31202 | 5.6121 | 141.5 | 0.00017777 | 10385 | 56.0455 | 134 | 0.010752 | 252
PEORIA 170169124 | PEORIA 1701 | 163781701 | FALSE | 2.6937 | 0.30458 | 2.9983 | 49.5 | 0.00040921 | 6342 | 29.1563 | 382 | 0.010697 | 253
ALLEGHANY 1101806 | ALLEGHANY 1101 | 152101101 | FALSE | 11.3077 | 0.79025 | 12.0979 | 231.8333 | 0.00043802 | 6032 | 26.246 | 430 | 0.010591 | 254
PUEBLO 2103678 | PUEBLO 2103 | 43292103 | FALSE | 33.1561 | 1.9236 | 34.8621 | 631.5 | 0.00050758 | 5308 | 22.411 | 507 | 0.010549 | 255
WEST POINT 110113444 | WEST POINT 1101 | 163201101 | FALSE | 27.7558 | 2.4112 | 18.4126 | 529 | 0.00034499 | 7221 | 32.1018 | 342 | 0.01053 | 256
RINCON 11035152 | RINCON 1103 | 43321103 | FALSE | 1.6684 | 0.015509 | 1.6839 | 32.5 | 0.00050941 | 5291 | 20.1588 | 554 | 0.010477 | 257
MIDDLETOWN 1101128648 | MIDDLETOWN 1101 | 43141101 | FALSE | 0.61466 | 0.11097 | 0.72563 | 9.5 | 0.00059472 | 4365 | 17.592 | 607 | 0.010457 | 258
MONTICELLO 110165454 | MONTICELLO 1101 | 43051101 | FALSE | 1.9351 | 0.10206 | 1.0047 | 38.5 | 0.00034765 | 7180 | 33.0031 | 331 | 0.010399 | 259
CALAVERAS CEMENT 110147968 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 17.211 | 0.37191 | 17.5828 | 332.5 | 0.00014287 | 10764 | 72.8402 | 59 | 0.010384 | 260
MONTICELLO 11011589 | MONTICELLO 1101 | 43051101 | FALSE | 4.2252 | 0.62913 | 4.8543 | 70.5 | 0.00047263 | 5670 | 21.7366 | 526 | 0.010317 | 261
FRENCH GULCH 11022902 | FRENCH GULCH 1102 | 103381102 | FALSE | 7.023 | 0.036386 | 7.0593 | 141.3333 | 0.0002452 | 9183 | 42.4405 | 220 | 0.010288 | 262
BEAR VALLEY 21054170 | BEAR VALLEY 2105 | 252192105 | FALSE | 9.3206 | 0.11211 | 9.4327 | 175 | 0.0001184 | 10963 | 81.3816 | 35 | 0.010248 | 263
PUEBLO 2103355186 | PUEBLO 2103 | 43292103 | FALSE | 1.8362 | 0.21671 | 2.0529 | 38.8333 | 0.00062122 | 4037 | 16.5354 | 629 | 0.010245 | 264
TEMPLETON 2113A12 | TEMPLETON 2113 | 183052113 | FALSE | 40.801 | 0.58259 | 41.3834 | 795 | 0.00013991 | 10789 | 71.0159 | 66 | 0.010232 | 265
BRUNSWICK 110651484 | BRUNSWICK 1106 | 152481106 | FALSE | 24.4319 | 1.8452 | 15.6303 | 427.8333 | 0.00028624 | 8279 | 37.8393 | 278 | 0.010208 | 266
BIG BEND 1102884340 | BIG BEND 1102 | 103751102 | FALSE | 20.9221 | 1.3069 | 22.2289 | 410.5 | 0.00039989 | 6456 | 26.77 | 425 | 0.010152 | 267
WEIMAR 11012764 | WEIMAR 1101 | 152491101 | FALSE | 6.2203 | 0.96133 | 7.1816 | 109 | 0.00054175 | 4937 | 17.3196 | 615 | 0.010095 | 268
STANISLAUS 17017144 | STANISLAUS 1701 | 162821701 | FALSE | 4.639 | 0.45547 | 5.0944 | 87.5 | 0.00023752 | 9334 | 42.8212 | 216 | 0.010091 | 269
HIGHLANDS 1103917328 | HIGHLANDS 1103 | 43361103 | FALSE | 8.8059 | 0.23309 | 7.362 | 167.5 | 0.00017722 | 10392 | 74.1138 | 52 | 0.010079 | 270
FRENCH GULCH 11011892 | FRENCH GULCH 1101 | 103381101 | FALSE | 3.234 | 0 | 3.0199 | 61.5 | 0.0001639 | 10548 | 62.2561 | 103 | 0.010065 | 271
WEIMAR 11012740 | WEIMAR 1101 | 152491101 | FALSE | 15.6695 | 2.9706 | 18.64 | 279.5 | 0.00036528 | 6917 | 28.6823 | 390 | 0.010047 | 272
ORO FINO 110239154 | ORO FINO 1102 | 103031102 | FALSE | 42.1729 | 4.8842 | 0.89341 | 829 | 0.00029874 | 8041 | 32.4101 | 340 | 0.010009 | 273
SISQUOC 1102M52 | SISQUOC 1102 | 182811102 | FALSE | 35.2771 | 0.072833 | 33.2762 | 692.5 | 0.00013747 | 10818 | 63.5047 | 95 | 0.010002 | 274
MOUNTAIN QUARRIES 21011184 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 11.4188 | 1.5107 | 12.7067 | 204.5 | 0.00063572 | 3872 | 15.0263 | 662 | 0.009997 | 275
SWIFT 2110XR332 | SWIFT 2110 | 83392110 | FALSE | 18.463 | 0.17414 | 18.6371 | 345 | 0.00011493 | 10985 | 77.187 | 45 | 0.0099814 | 276
PLACERVILLE 21067522 | PLACERVILLE 2106 | 153082106 | FALSE | 67.3979 | 6.6617 | 74.0595 | 1237.5 | 0.00033004 | 7449 | 38.3694 | 271 | 0.0099544 | 277
EL DORADO PH 2102CB | EL DORADO PH 2102 | 152762102 | FALSE | 5.5262 | 1.1606 | 6.6868 | 77.8333 | 0.0007373 | 2649 | 20.878 | 536 | 0.0099516 | 278
MARTELL 110191216 | MARTELL 1101 | 163011101 | FALSE | 40.2681 | 1.301 | 41.569 | 741.5 | 0.00025278 | 9024 | 41.9005 | 226 | 0.0099397 | 279
VOLTA 110153118 | VOLTA 1101 | 102541101 | FALSE | 9.6029 | 0.29557 | 9.8985 | 199 | 0.0001358 | 10832 | 69.2672 | 71 | 0.0099281 | 280
VOLTA 11011596 | VOLTA 1101 | 102541101 | FALSE | 21.6979 | 2.0744 | 23.7722 | 395 | 0.00025632 | 8958 | 38.6124 | 268 | 0.0099219 | 281
DOBBINS 110169722 | DOBBINS 1101 | 153741101 | FALSE | 6.5279 | 0.35308 | 6.881 | 121 | 0.000273 | 8582 | 43.3977 | 211 | 0.0098616 | 282
MIWUK 170193062 | MIWUK 1701 | 163661701 | FALSE | 7.8055 | 0.81865 | 8.6241 | 143 | 0.00022984 | 9492 | 39.1048 | 262 | 0.0098397 | 283
APPLE HILL 1103CB | APPLE HILL 1103 | 153661103 | FALSE | 22.8514 | 3.1126 | 21.5541 | 407.5 | 0.00046411 | 5758 | 22.7343 | 501 | 0.0098301 | 284
SCE VEGAS 1701CB | SCE VEGAS 1701 | 188881701 | TRUE | 0.10465 | 0 | 0.10465 | 4 | 0.00015315 | 10667 | 64.1814 | 94 | 0.0098291 | 285
BRUNSWICK 11052130 | BRUNSWICK 1105 | 152481105 | FALSE | 11.5892 | 0.58555 | 12.1747 | 213 | 0.0003277 | 7488 | 28.3584 | 397 | 0.00981 | 286
EL DORADO PH 210119612 | EL DORADO PH 2101 | 152762101 | FALSE | 8.6815 | 1.456 | 10.1375 | 164 | 0.00084665 | 1599 | 10.9134 | 805 | 0.0097168 | 287
ELECTRA 110136816 | ELECTRA 1101 | 162161101 | FALSE | 4.9856 | 0.35684 | 5.3424 | 88.5 | 0.00034794 | 7174 | 28.2143 | 398 | 0.0096899 | 288
TEMPLETON 2113641367 | TEMPLETON 2113 | 183052113 | FALSE | 39.0256 | 0.91183 | 39.9373 | 748.5 | 0.00012189 | 10942 | 77.6075 | 43 | 0.0096557 | 289
NOTRE DAME 11042537 | NOTRE DAME 1104 | 102041104 | FALSE | 4.8784 | 0.27947 | 5.1579 | 98.5 | 0.00012834 | 10899 | 68.9376 | 72 | 0.0096296 | 290
SILVERADO 2105247660 | SILVERADO 2105 | 43432105 | FALSE | 3.246 | 0.23386 | 2.2928 | 61 | 0.00047056 | 5693 | 21.3902 | 531 | 0.0096168 | 291
WYANDOTTE 1107829470 | WYANDOTTE 1107 | 102911107 | FALSE | 10.3312 | 0.23119 | 10.5624 | 190 | 0.00030908 | 7821 | 37.9954 | 275 | 0.0096151 | 292
PEORIA 1701169700 | PEORIA 1701 | 163781701 | FALSE | 8.3152 | 0.3205 | 8.6357 | 162 | 0.00017164 | 10466 | 58.0721 | 123 | 0.0095839 | 293
BRUNSWICK 1105875388 | BRUNSWICK 1105 | 152481105 | FALSE | 2.9513 | 0.3032 | 3.2545 | 60 | 0.00037146 | 6820 | 23.8011 | 477 | 0.0095744 | 294
CALAVERAS CEMENT 110180930 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 17.8564 | 0.96688 | 18.8232 | 338.5 | 0.0001772 | 10393 | 50.4928 | 164 | 0.0095072 | 295
CURTIS 170390320 | CURTIS 1703 | 163351703 | FALSE | 27.8854 | 4.1487 | 32.034 | 514.5 | 0.0002617 | 8844 | 32.7014 | 336 | 0.0094919 | 296
KONOCTI 110264664 | KONOCTI 1102 | 43311102 | FALSE | 26.668 | 1.5524 | 26.419 | 491 | 0.00023121 | 9459 | 40.4141 | 243 | 0.0094852 | 297
STELLING 1110396595 | STELLING 1110 | 83481110 |  | 0.49971 | 0.172 |  | 7.5 | 0.00077879 | 2158 | 12.1151 | 754 | 0.0094352 | 298
CALISTOGA 11015934 | CALISTOGA 1101 | 42711101 | FALSE | 25.7753 | 1.8354 | 27.6107 | 492.5 | 0.00042706 | 6147 | 22.8631 | 498 | 0.0094322 | 299
APPLE HILL 21021532 | APPLE HILL 2102 | 153662102 | FALSE | 41.8821 | 2.9703 | 40.4788 | 763.5 | 0.00027603 | 8511 | 35.6052 | 302 | 0.0094096 | 300
PIKE CITY 11011730 | PIKE CITY 1101 | 152201101 | FALSE | 8.4704 | 0.64371 | 9.1141 | 168.5 | 0.00037137 | 6822 | 22.8831 | 496 | 0.0093855 | 301
PARADISE 1105121988 | PARADISE 1105 | 102831105 | FALSE | 6.7158 | 2.5649 | 9.2806 | 113.5 | 0.00049187 | 5476 | 18.1107 | 594 | 0.0093524 | 302
PINE GROVE 11023168 | PINE GROVE 1102 | 163751102 | FALSE | 29.9753 | 1.5186 | 31.4938 | 569 | 0.00031488 | 7719 | 30.8394 | 361 | 0.0092748 | 303
PLACERVILLE 21062224 | PLACERVILLE 2106 | 153082106 | FALSE | 10.3969 | 1.9361 | 12.333 | 187 | 0.00057536 | 4586 | 19.4994 | 566 | 0.0092412 | 304
PLACERVILLE 210619552 | PLACERVILLE 2106 | 153082106 | FALSE | 21.378 | 2.6883 | 24.0662 | 383 | 0.00037401 | 6778 | 25.5694 | 444 | 0.0091386 | 305
WEST POINT 1102CB | WEST POINT 1102 | 163201102 | FALSE | 22.4117 | 2.768 | 18.4714 | 408 | 0.00057668 | 4567 | 17.179 | 618 | 0.0090923 | 306
WEST POINT 110234416 | WEST POINT 1102 | 163201102 | FALSE | 25.7664 | 2.0629 | 27.8292 | 487.5 | 0.0004624 | 5780 | 25.498 | 446 | 0.0090883 | 307
ELK CREEK 11012106 | ELK CREEK 1101 | 102781101 | FALSE | 13.1577 | 0.42471 | 13.5824 | 257.5 | 0.00014396 | 10755 | 64.7011 | 89 | 0.0090072 | 308
UPPER LAKE 110175370 | UPPER LAKE 1101 | 42871101 | FALSE | 17.1753 | 1.4389 | 11.1324 | 334.5 | 0.00021503 | 9775 | 47.5175 | 178 | 0.0089653 | 309
PINE GROVE 11011021 | PINE GROVE 1101 | 163751101 | FALSE | 4.165 | 0.53953 | 4.7045 | 76.5 | 0.00028022 | 8415 | 30.0719 | 371 | 0.0089413 | 310
PASO ROBLES 1103N52 | PASO ROBLES 1103 | 182611103 | FALSE | 6.569 | 0.043376 | 6.6124 | 129 | 0.000186 | 10262 | 44.7268 | 198 | 0.0089389 | 311
MARIPOSA 2102594143 | MARIPOSA 2102 | 254452102 | FALSE | 4.3001 | 2.0664 | 0.78528 | 79.5 | 0.00053544 | 5003 | 16.6733 | 627 | 0.0089197 | 312
JAMESON 110265516 | JAMESON 1102 | 63801102 | FALSE | 11.2949 | 2.4084 | 8.3553 | 201.5 | 0.00044091 | 6003 | 24.4719 | 461 | 0.0089196 | 313
CALISTOGA 1101267806 | CALISTOGA 1101 | 42711101 |  | 0.019918 | 0 |  | 0.33333 | 0.0047539 | 7 | 1.8762 | 1678 | 0.0089192 | 314
BRUNSWICK 110651486 | BRUNSWICK 1106 | 152481106 | FALSE | 56.752 | 5.0832 | 61.835 | 1034.5 | 0.00037349 | 6787 | 29.6934 | 374 | 0.0088799 | 315
PIT NO 5 11011614 | PIT NO 5 1101 | 101321101 | FALSE | 1.8419 | 0 | 1.8419 | 34 | 0.00019355 | 10158 | 43.885 | 206 | 0.0088717 | 316
SPAULDING 1101CB | SPAULDING 1101 | 152251101 | TRUE | 0.044275 | 0 | 0.044275 | 0.5 | 0.00028279 | 8356 | 31.3586 | 353 | 0.008868 | 317
BIG BEND 1101641808 | BIG BEND 1101 | 103751101 | FALSE | 28.6377 | 0.98085 | 26.5632 | 533 | 0.00018665 | 10251 | 43.3959 | 212 | 0.0088552 | 318
HIGGINS 1110166282 | HIGGINS 1110 | 152691110 | FALSE | 23.6133 | 1.4155 | 25.0287 | 423 | 0.00023755 | 9332 | 36.6938 | 283 | 0.0088449 | 319
COVELO 1101516510 | COVELO 1101 | 43061101 | FALSE | 8.4329 | 0.42555 | 3.8133 | 155.5 | 0.0002071 | 9928 | 45.5817 | 196 | 0.008836 | 320
CALAVERAS CEMENT 1101502 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 40.703 | 1.6007 | 38.458 | 754.5 | 0.00016038 | 10593 | 61.2884 | 108 | 0.0088265 | 321
FORESTHILL 110137238 | FORESTHILL 1101 | 152181101 | FALSE | 11.5935 | 0.7268 | 12.1545 | 221.5 | 0.00036034 | 6977 | 26.5511 | 427 | 0.0088134 | 322
AUBERRY 110137536 | AUBERRY 1101 | 254151101 | FALSE | 3.4218 | 0.065498 | 3.4555 | 63.5 | 0.00037181 | 6812 | 22.8636 | 497 | 0.0088053 | 323
COVELO 1101536 | COVELO 1101 | 43061101 |  | 3.3134 | 0 |  | 64.5 | 0.00021923 | 9715 | 47.2266 | 180 | 0.0088043 | 324
CURTIS 170411290 | CURTIS 1704 | 163351704 | FALSE | 7.8564 | 0.15578 | 8.0122 | 151.5 | 0.00019055 | 10202 | 44.6714 | 199 | 0.0087475 | 325
PIT NO 3 2101CB | PIT NO 3 2101 | 103732101 | FALSE | 4.5495 | 0.95393 | 5.5034 | 92 | 0.00041959 | 6230 | 23.5624 | 484 | 0.0086689 | 326
UPPER LAKE 1101412 | UPPER LAKE 1101 | 42871101 | FALSE | 17.429 | 1.4115 | 10.0214 | 334 | 0.00024237 | 9240 | 32.9516 | 332 | 0.0086415 | 327
PLACERVILLE 1109868678 | PLACERVILLE 1109 | 153081109 | FALSE | 10.9807 | 3.2885 | 13.9055 | 211 | 0.00053773 | 4981 | 17.9209 | 600 | 0.0086362 | 328
MIWUK 1701767890 | MIWUK 1701 | 163661701 | FALSE | 11.8268 | 1.5438 | 13.3705 | 220 | 0.00034039 | 7300 | 31.5275 | 350 | 0.0086221 | 329
MONTICELLO 1101256640 | MONTICELLO 1101 | 43051101 | FALSE | 10.4771 | 0.4391 | 9.0593 | 191 | 0.00020064 | 10033 | 30.8627 | 359 | 0.0086014 | 330
CALAVERAS CEMENT 1101544800 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 22.9909 | 0.56746 | 23.5583 | 439.5 | 0.0001057 | 11038 | 83.3986 | 30 | 0.0085783 | 331
KONOCTI 1102714370 | KONOCTI 1102 | 43311102 | FALSE | 2.6765 | 0.73169 | 2.9563 | 47 | 0.00034149 | 7283 | 24.076 | 471 | 0.0085492 | 332
COARSEGOLD 210410110 | COARSEGOLD 2104 | 254432104 | FALSE | 49.2754 | 3.217 | 52.4922 | 922.5 | 0.00021759 | 9740 | 37.1989 | 280 | 0.0085254 | 333
SALT SPRINGS 210110416 | SALT SPRINGS 2101 | 163692101 | FALSE | 0.68994 | 0.37229 | 1.0622 | 16.5 | 0.00027158 | 8617 | 31.4444 | 351 | 0.0085165 | 334
SPRING GAP 1702188426 | SPRING GAP 1702 | 162831702 | TRUE | 0.0028409 | 0 | 0.0028409 | 0.5 | 0.00033627 | 7361 | 25.2588 | 448 | 0.0084938 | 335
SHINGLE SPRINGS 210985766 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 18.517 | 1.1892 | 19.7062 | 356.5 | 0.0003293 | 7463 | 34.4832 | 315 | 0.0084494 | 336
SANTA YNEZ 1101980192 | SANTA YNEZ 1101 | 182721101 | FALSE | 3.8797 | 0 | 3.8797 | 73.5 | 0.00015803 | 10615 | 54.2171 | 146 | 0.0083898 | 337
PUEBLO 2102378860 | PUEBLO 2102 | 43292102 | FALSE | 20.1907 | 1.1354 | 19.5808 | 395.8333 | 0.00036921 | 6853 | 23.3339 | 487 | 0.0083787 | 338
HIGGINS 11044281 | HIGGINS 1104 | 152691104 | FALSE | 13.3553 | 0.10764 | 13.4629 | 254.5 | 0.00019594 | 10115 | 42.2679 | 223 | 0.008344 | 339
GIRVAN 11011636 | GIRVAN 1101 | 103401101 | FALSE | 18.3837 | 0.80201 | 16.3554 | 335.5 | 0.00047518 | 5644 | 20.7039 | 542 | 0.0083159 | 340
HALSEY 1102CB | HALSEY 1102 | 152241102 | FALSE | 14.4793 | 1.4849 | 8.588 | 261.3333 | 0.00044256 | 5990 | 27.9095 | 403 | 0.0083105 | 341
STELLING 1110733294 | STELLING 1110 | 83481110 |  | 0.6537 | 0.2965 |  | 13 | 0.00070936 | 2983 | 11.8135 | 764 | 0.0083024 | 342
DOBBINS 11011264 | DOBBINS 1101 | 153741101 | FALSE | 27.561 | 1.0474 | 28.5369 | 510.5 | 0.00026926 | 8671 | 27.7232 | 407 | 0.0082955 | 343
DOBBINS 1101CB | DOBBINS 1101 | 153741101 | FALSE | 0.69425 | 0.056778 | 0.7488 | 11 | 0.00013995 | 10788 | 58.4083 | 120 | 0.0082658 | 344
GIRVAN 11011330 | GIRVAN 1101 | 103401101 | FALSE | 30.9852 | 0.68625 | 31.1625 | 566 | 0.00027319 | 8579 | 29.6418 | 377 | 0.0081786 | 345
SILVERADO 2103920793 | SILVERADO 2103 | 43432103 | FALSE | 7.9849 | 0.23632 | 6.5628 | 162 | 0.00031496 | 7714 | 27.0376 | 421 | 0.0081455 | 346
CALPELLA 1101908688 | CALPELLA 1101 | 43411101 | FALSE | 9.4603 | 1.3903 | 9.5479 | 172 | 0.00033231 | 7416 | 24.1964 | 467 | 0.0081025 | 347
AUBERRY 1101R324 | AUBERRY 1101 | 254151101 | FALSE | 24.4374 | 0.82976 | 25.2097 | 452 | 0.00024606 | 9162 | 31.3895 | 352 | 0.0080497 | 348
FRENCH GULCH 11021462 | FRENCH GULCH 1102 | 103381102 | FALSE | 9.8869 | 0.093495 | 9.881 | 181.3333 | 0.00014493 | 10747 | 46.4376 | 188 | 0.0080404 | 349
STELLING 111060090 | STELLING 1110 | 83481110 | FALSE | 6.525 | 0.37603 | 6.6549 | 119.5 | 0.00052789 | 5096 | 14.9533 | 666 | 0.0080227 | 350
EL DORADO PH 210113532 | EL DORADO PH 2101 | 152762101 | FALSE | 5.42 | 1.5047 | 6.9247 | 110 | 0.00065003 | 3706 | 12.8997 | 728 | 0.0079604 | 351
WEST POINT 110112256 | WEST POINT 1101 | 163201101 | FALSE | 6.5391 | 0.88305 | 7.4221 | 111.5 | 0.00059289 | 4384 | 13.4568 | 712 | 0.0079522 | 352
UKIAH 1113548420 | UKIAH 1113 | 42771113 | FALSE | 5.1738 | 0.51148 | 5.5821 | 93 | 0.00022479 | 9615 | 33.8148 | 321 | 0.007899 | 353
ARBUCKLE 1101932352 | ARBUCKLE 1101 | 62081101 |  | 0.61589 | 0 |  | 12.5 | 0.00012701 | 10910 | 63.3665 | 96 | 0.0078718 | 354
ELECTRA 110161816 | ELECTRA 1101 | 162161101 | FALSE | 23.4847 | 1.616 | 25.1007 | 445.5 | 0.00019694 | 10094 | 40.5549 | 240 | 0.0078671 | 355
MONTICELLO 1101718 | MONTICELLO 1101 | 43051101 | FALSE | 29.3286 | 1.4306 | 27.0354 | 555 | 0.0002642 | 8773 | 28.8216 | 389 | 0.007832 | 356
UKIAH 1113691436 | UKIAH 1113 | 42771113 | FALSE | 2.238 | 0.63658 | 1.1264 | 39.5 | 0.00043197 | 6091 | 22.1316 | 516 | 0.0078118 | 357
MONTICELLO 110152910 | MONTICELLO 1101 | 43051101 | FALSE | 3.1422 | 0.19696 | 2.1931 | 60.8333 | 0.00021073 | 9865 | 24.5399 | 460 | 0.0078039 | 358
CAMP EVERS 210595394 | CAMP EVERS 2105 | 83622105 | FALSE | 0.48966 | 0.22322 | 0.71287 | 4.0333 | 0.0063274 | 6 | 1.2226 | 2098 | 0.007736 | 359
BUTTE 1105612016 | BUTTE 1105 | 103081105 | FALSE | 5.4167 | 0.1106 | 5.5273 | 108 | 0.0001587 | 10606 | 45.8718 | 193 | 0.0077053 | 360
MONTICELLO 1101666 | MONTICELLO 1101 | 43051101 | FALSE | 13.5051 | 0.36475 | 10.9447 | 252.5 | 0.00024095 | 9269 | 30.8903 | 358 | 0.0076976 | 361
PARADISE 11042034 | PARADISE 1104 | 102831104 | FALSE | 10.9811 | 0.80178 | 11.749 | 197.5 | 0.00020886 | 9896 | 39.8004 | 256 | 0.0076725 | 362
MIWUK 170238218 | MIWUK 1702 | 163661702 | FALSE | 14.4348 | 2.051 | 12.2736 | 247.5 | 0.00042464 | 6178 | 22.0435 | 519 | 0.0076507 | 363
PUEBLO 2102769868 | PUEBLO 2102 | 43292102 | TRUE | 2.1596 | 0.36154 | 0.39783 | 44 | 0.00060539 | 4231 | 14.6544 | 676 | 0.0076446 | 364
ARBUCKLE 1104669720 | ARBUCKLE 1104 | 62081104 | FALSE | 4.866 | 0.062876 | 1.9232 | 91.5 | 0.00017598 | 10409 | 41.6294 | 231 | 0.0076314 | 365
MONTICELLO 110193384 | MONTICELLO 1101 | 43051101 | FALSE | 17.2515 | 0.52192 | 15.5406 | 327.8333 | 0.0001327 | 10859 | 56.1185 | 133 | 0.0076193 | 366
ELECTRA 11024756 | ELECTRA 1102 | 162161102 | FALSE | 9.5967 | 0.41736 | 9.4594 | 194.3333 | 0.00024081 | 9274 | 29.6602 | 376 | 0.0075811 | 367
TEJON 11023751 | TEJON 1102 | 252931102 | FALSE | 9.2397 | 0.21773 | 8.6769 | 179.5 | 0.00024265 | 9229 | 36.4708 | 287 | 0.0075263 | 368
CUYAMA 1103684566 | CUYAMA 1103 | 253141103 | FALSE | 3.0278 | 0 | 2.5774 | 65.5 | 7.7337e-05 | 11112 | 101.7677 | 8 | 0.0075212 | 369
EL DORADO PH 210163464 | EL DORADO PH 2101 | 152762101 | FALSE | 13.7502 | 0.66197 | 14.4122 | 273 | 0.00038832 | 6602 | 21.8913 | 523 | 0.0074889 | 370
SAN JOAQUIN #3 1101CB | SAN JOAQUIN #3 1101 | 252531101 | FALSE | 5.1632 | 0.19961 | 5.3628 | 101 | 0.00032959 | 7456 | 26.7624 | 426 | 0.0074779 | 371
PLACERVILLE 1110953474 | PLACERVILLE 1110 | 153081110 | FALSE | 10.7893 | 2.911 | 13.7003 | 189.8333 | 0.00054125 | 4944 | 11.9638 | 760 | 0.007475 | 372
RACETRACK 170311270 | RACETRACK 1703 | 163761703 | FALSE | 12.4632 | 0.56267 | 13.0258 | 226.5 | 0.00026029 | 8877 | 29.0615 | 386 | 0.0074595 | 373
CLOVERDALE 1102672 | CLOVERDALE 1102 | 42821102 | FALSE | 22.2289 | 1.0232 | 22.5809 | 439.5 | 0.00019294 | 10167 | 40.0013 | 250 | 0.0074176 | 374
REDBUD 1101754544 | REDBUD 1101 | 43191101 | FALSE | 9.1433 | 0.019278 | 4.1597 | 177 | 0.0001249 | 10926 | 50.9406 | 160 | 0.007396 | 375
DIAMOND SPRINGS 11057722 | DIAMOND SPRINGS 1105 | 152261105 | FALSE | 61.4374 | 4.0377 | 62.403 | 1122.5 | 0.00019316 | 10162 | 41.7895 | 228 | 0.0073956 | 376
PEORIA 1704877670 | PEORIA 1704 | 163781704 | FALSE | 6.4384 | 0.022912 | 6.3808 | 127.5 | 0.00013474 | 10841 | 42.8993 | 215 | 0.0073874 | 377
BRUNSWICK 11062790 | BRUNSWICK 1106 | 152481106 | FALSE | 9.6827 | 0.38216 | 8.2462 | 175.3333 | 0.00022233 | 9663 | 40.3562 | 244 | 0.007356 | 378
STANISLAUS 17021888 | STANISLAUS 1702 | 162821702 | FALSE | 18.9786 | 1.8091 | 20.7876 | 324.5 | 0.00045534 | 5864 | 18.5306 | 585 | 0.0073524 | 379
MOUNTAIN QUARRIES 21011130 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 19.9125 | 1.5146 | 21.4271 | 381.5 | 0.00024178 | 9251 | 36.8978 | 282 | 0.0073453 | 380
SHINGLE SPRINGS 210961892 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 30.0462 | 1.2046 | 31.2506 | 530.5 | 0.00026883 | 8678 | 29.025 | 387 | 0.0073282 | 381
CALISTOGA 1102177784 | CALISTOGA 1102 | 42711102 | TRUE | 0.10644 | 0.079287 | 0.1696 | 2.5 | 0.00066665 | 3474 | 9.4703 | 860 | 0.0073271 | 382
VACAVILLE 11046542 | VACAVILLE 1104 | 63601104 | FALSE | 15.3394 | 0.79568 | 16.1351 | 261 | 0.00038309 | 6663 | 27.6589 | 409 | 0.0073117 | 383
WEST POINT 110293116 | WEST POINT 1102 | 163201102 | FALSE | 42.2884 | 2.11 | 44.3983 | 779 | 0.00036073 | 6971 | 22.522 | 504 | 0.0073052 | 384
RINCON 1103925054 | RINCON 1103 | 43321103 | FALSE | 11.9402 | 0.83544 | 12.7756 | 228.5 | 0.00037162 | 6816 | 19.5907 | 561 | 0.0072816 | 385
APPLE HILL 1104814656 | APPLE HILL 1104 | 153661104 | TRUE | 0.017476 | 0 | 0.017476 | 0.5 | 0.00042055 | 6222 | 17.2709 | 616 | 0.0072633 | 386
TEJON 11023760 | TEJON 1102 | 252931102 | FALSE | 6.4769 | 0 | 6.4769 | 142.5 | 0.00017322 | 10444 | 46.2083 | 189 | 0.007218 | 387
HIGGINS 110432747 | HIGGINS 1104 | 152691104 | FALSE | 1.7698 | 0.64792 | 0.86016 | 30 | 0.00068861 | 3238 | 10.3784 | 822 | 0.0072157 | 388
CALISTOGA 110135588 | CALISTOGA 1101 | 42711101 | FALSE | 3.0901 | 0 | 3.0901 | 58 | 0.00023681 | 9344 | 29.9976 | 373 | 0.0071797 | 389
PLACERVILLE 1109CB | PLACERVILLE 1109 | 153081109 | TRUE | 0.077924 | 0.035296 | 0.0088181 | 2.5 | 0.00090047 | 1229 | 8.586 | 907 | 0.0071211 | 390
DUNBAR 1102694641 | DUNBAR 1102 | 43071102 | FALSE | 3.9951 | 0.099515 | 4.0946 | 74.5 | 0.00046028 | 5805 | 14.2702 | 687 | 0.0070997 | 391
MIDDLETOWN 1102302610 | MIDDLETOWN 1102 | 43141102 | FALSE | 5.7365 | 0.17627 | 4.658 | 107 | 0.00030724 | 7858 | 25.7025 | 441 | 0.007089 | 392
LOYOLA 1102550291 | LOYOLA 1102 | 82161102 |  | 5.155 | 1.0461 |  | 105.5 | 0.00070668 | 3020 | 11.2377 | 791 | 0.0070884 | 393
PIT NO 3 21011482 | PIT NO 3 2101 | 103732101 | FALSE | 12.1398 | 0.12186 | 12.2617 | 236 | 0.00038973 | 6575 | 15.854 | 642 | 0.0070854 | 394
REDBUD 1101CB | REDBUD 1101 | 43191101 | FALSE | 7.2989 | 4.3439 | 5.1157 | 107.3333 | 0.00059892 | 4313 | 12.6209 | 737 | 0.0070846 | 395
OAKHURST 11035480 | OAKHURST 1103 | 254421103 | FALSE | 16.8067 | 2.6048 | 19.4114 | 323 | 0.00038726 | 6615 | 20.4291 | 550 | 0.0070741 | 396
PLACERVILLE 21061104 | PLACERVILLE 2106 | 153082106 | FALSE | 49.2341 | 3.7745 | 53.0085 | 916 | 0.00040546 | 6390 | 18.5375 | 584 | 0.0070659 | 397
SILVERADO 2105167360 | SILVERADO 2105 | 43432105 | FALSE | 9.5243 | 0.29368 | 6.0689 | 183 | 0.00031938 | 7641 | 24.3484 | 463 | 0.0070204 | 398
CURTIS 17039210 | CURTIS 1703 | 163351703 | FALSE | 21.7808 | 0.62668 | 22.4074 | 433.5 | 0.00015804 | 10614 | 47.2174 | 181 | 0.0069842 | 399
MARIPOSA 2102440236 | MARIPOSA 2102 | 254452102 | FALSE | 43.1986 | 2.4155 | 5.0925 | 812.5 | 0.00017271 | 10448 | 38.652 | 267 | 0.0069412 | 400
MOUNTAIN QUARRIES 21011350 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 21.7138 | 1.0656 | 22.7794 | 386.3333 | 0.00023842 | 9316 | 35.7216 | 300 | 0.0069368 | 401
PIT NO 5 11011658 | PIT NO 5 1101 | 101321101 | FALSE | 4.5603 | 0.15776 | 4.7141 | 86 | 0.00026509 | 8754 | 20.8104 | 539 | 0.0069198 | 402
CURTIS 170234426 | CURTIS 1702 | 163351702 | FALSE | 6.7934 | 3.3166 | 5.1626 | 113.5 | 0.00037597 | 6750 | 32.5888 | 339 | 0.0069142 | 403
BUCKS CREEK 1103CB | BUCKS CREEK 1103 | 102211103 | FALSE | 2.1814 | 0.052788 | 2.2342 | 56.3333 | 0.00036265 | 6952 | 22.746 | 500 | 0.0069107 | 404
JOLON 11027040 | JOLON 1102 | 182981102 | FALSE | 22.6167 | 0.62223 | 20.286 | 444.5 | 0.0002008 | 10030 | 34.2242 | 318 | 0.0069053 | 405
PARADISE 110343008 | PARADISE 1103 | 102831103 | FALSE | 12.9647 | 1.9569 | 14.9216 | 237 | 0.00025385 | 9000 | 30.2503 | 367 | 0.006875 | 406
REDBUD 1102523244 | REDBUD 1102 | 43191102 | FALSE | 19.1015 | 0.741 | 16.0278 | 350.8333 | 0.00026653 | 8729 | 29.3258 | 381 | 0.0068603 | 407
CHALLENGE 11025462 | CHALLENGE 1102 | 103201102 | FALSE | 23.2454 | 1.6081 | 24.8534 | 421 | 0.00045553 | 5861 | 15.4285 | 648 | 0.0068437 | 408
BEAR VALLEY 210513430 | BEAR VALLEY 2105 | 252192105 | FALSE | 12.8151 | 0.5932 | 13.4083 | 244 | 0.00014715 | 10726 | 49.1872 | 171 | 0.0068296 | 409
PINE GROVE 11013170 | PINE GROVE 1101 | 163751101 | FALSE | 39.8105 | 2.2408 | 42.0511 | 725 | 0.00028881 | 8218 | 25.9697 | 436 | 0.0068091 | 410
CALISTOGA 1101886282 | CALISTOGA 1101 | 42711101 | FALSE | 10.8643 | 0.58862 | 11.4503 | 213 | 0.00036095 | 6967 | 16.9845 | 625 | 0.006798 | 411
DIAMOND SPRINGS 110676088 | DIAMOND SPRINGS 1106 | 152261106 | FALSE | 32.3939 | 2.0004 | 11.6927 | 595.5 | 0.00019498 | 10130 | 36.2834 | 290 | 0.0067878 | 412
PLACERVILLE 210623190 | PLACERVILLE 2106 | 153082106 | FALSE | 3.5347 | 0.72052 | 4.2552 | 58.8333 | 0.00070805 | 3008 | 11.4822 | 781 | 0.0067663 | 413
BUTTE 1105235788 | BUTTE 1105 | 103081105 | FALSE | 7.9849 | 0.34483 | 7.3968 | 142.5 | 0.00021278 | 9829 | 40.2571 | 246 | 0.0067565 | 414
MONTICELLO 110137384 | MONTICELLO 1101 | 43051101 | FALSE | 9.3362 | 0.29206 | 9.6283 | 163 | 0.0002471 | 9143 | 27.2595 | 418 | 0.006753 | 415
SILVERADO 2105337226 | SILVERADO 2105 | 43432105 | TRUE | 0.82176 | 0.43002 | 0.47255 | 14 | 0.0012165 | 275 | 6.147 | 1059 | 0.0067497 | 416
LOS GATOS 1106697500 | LOS GATOS 1106 | 82021106 | FALSE | 6.7775 | 1.3579 | 7.9776 | 119 | 0.0010314 | 681 | 7.4777 | 964 | 0.0067367 | 417
CURTIS 17048140 | CURTIS 1704 | 163351704 | FALSE | 35.6796 | 2.3463 | 38.0258 | 662.3333 | 0.00019636 | 10103 | 40.3331 | 245 | 0.0067349 | 418
SILVERADO 21051306 | SILVERADO 2105 | 43432105 | TRUE | 4.0764 | 0.6302 | 0.24969 | 76.3333 | 0.00080343 | 1948 | 10.6908 | 813 | 0.0067032 | 419
PIT NO 3 21011480 | PIT NO 3 2101 | 103732101 | FALSE | 2.5579 | 0.09623 | 2.21 | 49.5 | 0.00029846 | 8044 | 18.1035 | 595 | 0.0067006 | 420
DIAMOND SPRINGS 110656026 | DIAMOND SPRINGS 1106 | 152261106 | FALSE | 14.6792 | 1.2603 | 15.9062 | 252 | 0.00031372 | 7741 | 24.3951 | 462 | 0.0066886 | 421
PASO ROBLES 1103N02 | PASO ROBLES 1103 | 182611103 | TRUE | 0.032736 | 0 | 0.032736 | 0.5 | 0.00030113 | 7992 | 22.2089 | 510 | 0.0066878 | 422
PUTAH CREEK 110267858 | PUTAH CREEK 1102 | 63681102 | FALSE | 11.2878 | 0.35655 | 11.6443 | 200.5 | 0.00016464 | 10537 | 42.1817 | 224 | 0.0066851 | 423
STELLING 11109265 | STELLING 1110 | 83481110 | FALSE | 5.4912 | 0.106 | 5.5972 | 103.5 | 0.00036208 | 6959 | 18.7823 | 577 | 0.0066835 | 424
MONTICELLO 11014360 | MONTICELLO 1101 | 43051101 | FALSE | 9.2878 | 0.4677 | 7.32 | 177.5 | 0.00025 | 9083 | 30.2697 | 366 | 0.0066706 | 425
RINCON 1103655192 | RINCON 1103 | 43321103 | FALSE | 3.9474 | 0.22833 | 4.1757 | 71.5 | 0.00044162 | 5997 | 15.2178 | 654 | 0.0066623 | 426
SWIFT 2110853720 | SWIFT 2110 | 83392110 | FALSE | 30.4124 | 0.37612 | 30.7884 | 595.5 | 8.5607e-05 | 11095 | 82.3059 | 33 | 0.0066237 | 427
CALISTOGA 1101257964 | CALISTOGA 1101 | 42711101 | FALSE | 16.2586 | 1.6258 | 14.4258 | 315.5 | 0.00061823 | 4067 | 10.0878 | 829 | 0.006597 | 428
BRUNSWICK 11062104 | BRUNSWICK 1106 | 152481106 | FALSE | 9.6082 | 1.8437 | 11.4519 | 174 | 0.00055846 | 4770 | 11.346 | 786 | 0.0065825 | 429
LUCERNE 11034200 | LUCERNE 1103 | 43351103 | FALSE | 4.9035 | 0.12564 | 4.0381 | 92.5 | 0.00020655 | 9941 | 46.923 | 184 | 0.0065801 | 430
KONOCTI 110275382 | KONOCTI 1102 | 43311102 | FALSE | 23.4088 | 2.5796 | 25.0595 | 448 | 0.00024595 | 9167 | 26.8804 | 424 | 0.0065452 | 431
CALPELLA 1101619542 | CALPELLA 1101 | 43411101 | FALSE | 1.4872 | 0.12486 | 1.5523 | 28.8333 | 0.00038758 | 6611 | 15.8249 | 644 | 0.0065201 | 432
BEAR VALLEY 210521160 | BEAR VALLEY 2105 | 252192105 | FALSE | 22.9632 | 1.2263 | 24.1894 | 441.5 | 0.00012112 | 10944 | 48.257 | 175 | 0.0064317 | 433
SYCAMORE CREEK 11112014 | SYCAMORE CREEK 1111 | 102971111 | FALSE | 22.393 | 0.7211 | 22.9179 | 439 | 0.0002242 | 9622 | 30.0774 | 370 | 0.0064305 | 434
SILVERADO 2104722 | SILVERADO 2104 | 43432104 | FALSE | 7.7922 | 0.61796 | 8.4101 | 137.5 | 0.00057299 | 4618 | 11.8878 | 763 | 0.0064165 | 435
APPLE HILL 2102186912 | APPLE HILL 2102 | 153662102 | FALSE | 60.4176 | 4.3006 | 62.1561 | 1146.5 | 0.00022775 | 9543 | 30.0336 | 372 | 0.0063805 | 436
MARTELL 110111244 | MARTELL 1101 | 163011101 | FALSE | 21.5189 | 1.0619 | 14.4458 | 409 | 0.00030702 | 7865 | 25.0087 | 451 | 0.0063783 | 437
KONOCTI 1102948 | KONOCTI 1102 | 43311102 | FALSE | 7.9446 | 0.67579 | 6.8339 | 145.5 | 0.00022657 | 9572 | 25.155 | 450 | 0.006375 | 438
COARSEGOLD 210210050 | COARSEGOLD 2102 | 254432102 | FALSE | 7.061 | 0.90579 | 7.9668 | 129.8333 | 0.00040151 | 6434 | 15.4691 | 646 | 0.0063689 | 439
DUNBAR 1101534 | DUNBAR 1101 | 43071101 | FALSE | 17.232 | 0.48541 | 15.955 | 309.8333 | 0.00027708 | 8492 | 23.9774 | 473 | 0.0063584 | 440
BEAR VALLEY 21014160 | BEAR VALLEY 2101 | 252192101 | FALSE | 22.8172 | 1.1139 | 23.931 | 448 | 0.00018697 | 10244 | 31.1051 | 355 | 0.0063442 | 441
RACETRACK 1703CB | RACETRACK 1703 | 163761703 | FALSE | 18.1121 | 4.5046 | 19.4193 | 302.1667 | 0.00060759 | 4201 | 10.5305 | 817 | 0.0063351 | 442
MIDDLETOWN 1103830 | MIDDLETOWN 1103 | 43141103 | FALSE | 39.0621 | 0.87966 | 23.4623 | 780.8333 | 0.00019828 | 10073 | 31.7047 | 348 | 0.006302 | 443
ATASCADERO 1103A14 | ATASCADERO 1103 | 182541103 | FALSE | 25.246 | 0.58804 | 25.834 | 504 | 0.0001639 | 10549 | 39.8389 | 255 | 0.0063018 | 444
CURTIS 17028000 | CURTIS 1702 | 163351702 | FALSE | 14.1863 | 1.3442 | 15.5304 | 262 | 0.00030963 | 7814 | 14.9211 | 668 | 0.0062937 | 445
LOW GAP 1101449990 | LOW GAP 1101 | 192411101 | FALSE | 3.9824 | 0.14598 | 4.0708 | 78.5 | 0.00045896 | 5816 | 13.5596 | 708 | 0.0062657 | 446
COALINGA NO 2 11059260 | COALINGA NO 2 1105 | 252381105 |  | 19.6372 | 0.11255 |  | 384.5 | 0.00015219 | 10677 | 41.0834 | 232 | 0.0062649 | 447
TIDEWATER 210614072 | TIDEWATER 2106 | 14652106 | FALSE | 3.8711 | 0.19579 | 3.813 | 77 | 0.00043319 | 6083 | 15.0699 | 660 | 0.0062529 | 448
RACETRACK 170310870 | RACETRACK 1703 | 163761703 | FALSE | 2.4884 | 0.69542 | 2.3783 | 46.5 | 0.00046782 | 5718 | 15.8292 | 643 | 0.0062516 | 449
DIAMOND SPRINGS 110519910 | DIAMOND SPRINGS 1105 | 152261105 | FALSE | 20.594 | 1.5041 | 22.0981 | 359.5 | 0.0001965 | 10099 | 31.0201 | 356 | 0.0062478 | 450
COVELO 1101112804 | COVELO 1101 | 43061101 | FALSE | 19.083 | 0.4009 | 8.5751 | 356 | 0.00012218 | 10940 | 51.8574 | 157 | 0.006247 | 451
CHALLENGE 11015460 | CHALLENGE 1101 | 103201101 | FALSE | 31.8409 | 1.9263 | 12.4814 | 617.5 | 0.00040032 | 6453 | 14.2024 | 688 | 0.0061982 | 452
OAKHURST 110377384 | OAKHURST 1103 | 254421103 | FALSE | 4.7055 | 2.6346 | 7.3401 | 91.3333 | 0.0007512 | 2468 | 8.6762 | 900 | 0.0061573 | 453
RINCON 1103474 | RINCON 1103 | 43321103 | FALSE | 6.4053 | 0.68018 | 7.0854 | 126.5 | 0.00045833 | 5828 | 13.44 | 713 | 0.006141 | 454
CAMP EVERS 210511010 | CAMP EVERS 2105 | 83622105 | FALSE | 2.1786 | 1.161 | 3.3396 | 31 | 0.0026128 | 14 | 2.2966 | 1555 | 0.0061283 | 455
TEMPLETON 2110N30 | TEMPLETON 2110 | 183052110 | FALSE | 19.7776 | 0.32498 | 20.1025 | 383.5 | 0.00014934 | 10711 | 40.788 | 239 | 0.0061132 | 456
KERCKHOFF 1101R308 | KERCKHOFF 1101 | 252561101 | FALSE | 3.7523 | 0.11114 | 3.8634 | 69 | 0.00018422 | 10287 | 32.7415 | 333 | 0.0061096 | 457
CURTIS 170510590 | CURTIS 1705 | 163351705 | FALSE | 16.1136 | 1.8433 | 17.9568 | 279.3333 | 0.00027871 | 8452 | 20.5425 | 546 | 0.0060824 | 458
LOS OSITOS 2102258878 | LOS OSITOS 2102 | 182082102 | FALSE | 4.322 | 0.14977 | 2.515 | 91.5 | 0.00021332 | 9812 | 33.6967 | 324 | 0.0060726 | 459
RINCON 1103568 | RINCON 1103 | 43321103 | FALSE | 8.6721 | 1.0798 | 9.7519 | 163.5 | 0.00048095 | 5593 | 12.559 | 741 | 0.0060622 | 460
RACETRACK 170455798 | RACETRACK 1704 | 163761704 | FALSE | 22.9733 | 1.8454 | 24.8186 | 426.5 | 0.00018677 | 10249 | 32.3534 | 341 | 0.0060598 | 461
LOS COCHES 1101625902 | LOS COCHES 1101 | 182151101 | FALSE | 5.6071 | 0.085531 | 2.3491 | 109.5 | 0.00028663 | 8267 | 23.0485 | 494 | 0.0060529 | 462
APPLE HILL 21028372 | APPLE HILL 2102 | 153662102 | FALSE | 62.6502 | 3.3268 | 59.3546 | 1164 | 0.00026737 | 8712 | 24.8374 | 456 | 0.0060081 | 463
MARIPOSA 2102527766 | MARIPOSA 2102 | 254452102 | TRUE | 0.056359 | 0 | 0.056359 | 1.5 | 0.00040384 | 6415 | 14.7535 | 671 | 0.0059574 | 464
CHALLENGE 1102CB | CHALLENGE 1102 | 103201102 | FALSE | 15.3136 | 0.76464 | 16.0782 | 286.5 | 0.00049594 | 5435 | 14.3452 | 686 | 0.0059406 | 465
CALISTOGA 1102963232 | CALISTOGA 1102 | 42711102 |  | 0.047767 | 0.026269 |  | 1.5 | 0.0016141 | 77 | 3.9769 | 1257 | 0.0059367 | 466
CURTIS 17039330 | CURTIS 1703 | 163351703 | FALSE | 40.7469 | 1.9178 | 42.6646 | 762.3333 | 0.00016315 | 10559 | 37.2321 | 279 | 0.0059364 | 467
DUNLAP 11037170 | DUNLAP 1103 | 254061103 | FALSE | 5.0285 | 1.2828 | 6.3112 | 103 | 0.00048393 | 5557 | 14.5357 | 681 | 0.0059162 | 468
BRUNSWICK 11062416 | BRUNSWICK 1106 | 152481106 | FALSE | 34.593 | 5.2725 | 36.9943 | 625.5 | 0.00044409 | 5971 | 14.5434 | 680 | 0.0059134 | 469
POTTER VALLEY P H 1105640888 | POTTER VALLEY P H 1105 | 42281105 | FALSE | 8.5868 | 0.63995 | 9.2267 | 171 | 0.00021258 | 9832 | 27.5814 | 410 | 0.005901 | 470
CLAYTON 2212158138 | CLAYTON 2212 | 12022212 | TRUE | 0.89774 | 0.0096138 | 0.47121 | 17 | 0.00074358 | 2571 | 9.3168 | 867 | 0.0058873 | 471
MOUNTAIN QUARRIES 21011102 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 43.1516 | 2.1209 | 45.2716 | 788.5 | 0.00023016 | 9484 | 30.2056 | 368 | 0.0058813 | 472
GIRVAN 1101323094 | GIRVAN 1101 | 103401101 | FALSE | 34.5865 | 1.0169 | 35.6033 | 669.5 | 0.00019209 | 10176 | 23.7619 | 479 | 0.005863 | 473
MOUNTAIN QUARRIES 21011346 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 30.8507 | 1.7693 | 32.6198 | 565 | 0.00027082 | 8632 | 26.4175 | 429 | 0.0058394 | 474
ALHAMBRA 1105295792 | ALHAMBRA 1105 | 14101105 | FALSE | 2.8805 | 1.5259 | 4.4064 | 53.5 | 0.00062337 | 4013 | 9.5268 | 857 | 0.0058321 | 475
LOS GATOS 1107914254 | LOS GATOS 1107 | 82021107 | FALSE | 1.172 | 0 | 1.172 | 19.5 | 0.00074807 | 2505 | 7.7847 | 949 | 0.0058196 | 476
CLARK ROAD 110290548 | CLARK ROAD 1102 | 103091102 | FALSE | 17.8017 | 0.79054 | 18.5922 | 322.5 | 0.0002194 | 9713 | 27.1902 | 419 | 0.0058163 | 477
KONOCTI 1102532 | KONOCTI 1102 | 43311102 | FALSE | 7.491 | 1.7279 | 9.2188 | 134 | 0.00036085 | 6970 | 19.0479 | 571 | 0.005813 | 478
JESSUP 110141356 | JESSUP 1101 | 103441101 | FALSE | 32.4205 | 2.2216 | 34.642 | 584.5 | 0.00018107 | 10337 | 35.768 | 296 | 0.0057944 | 479
CALISTOGA 1101242919 | CALISTOGA 1101 | 42711101 | FALSE | 1.312 | 0.043161 | 1.3552 | 29.5 | 0.00039348 | 6529 | 14.6863 | 673 | 0.0057895 | 480
HALSEY 110239104 | HALSEY 1102 | 152241102 | FALSE | 30.673 | 4.7723 | 35.4453 | 568 | 0.00041701 | 6255 | 19.3768 | 568 | 0.0057596 | 481
DUNLAP 11027050 | DUNLAP 1102 | 254061102 | FALSE | 12.66 | 3.3106 | 12.7497 | 259 | 0.00033364 | 7400 | 18.2457 | 589 | 0.0057466 | 482
SILVERADO 210234959 | SILVERADO 2102 | 43432102 | FALSE | 26.3601 | 0.7547 | 25.503 | 519 | 0.0002318 | 9447 | 24.5936 | 457 | 0.005726 | 483
MARIPOSA 210237282 | MARIPOSA 2102 | 254452102 | FALSE | 58.7539 | 3.077 | 53.3867 | 1090.5 | 0.00018252 | 10311 | 27.79 | 405 | 0.0057135 | 484
SAN JOAQUIN #3 110110060 | SAN JOAQUIN #3 1101 | 252531101 | FALSE | 6.5479 | 1.2317 | 7.7796 | 127.8333 | 0.00031906 | 7649 | 18.2779 | 588 | 0.005692 | 485
HARTLEY 1101698 | HARTLEY 1101 | 43211101 | FALSE | 10.6191 | 0.77309 | 6.5377 | 209 | 0.00024771 | 9134 | 24.5629 | 458 | 0.0056859 | 486
MARIPOSA 210190180 | MARIPOSA 2101 | 254452101 | FALSE | 4.8788 | 0.21546 | 5.0942 | 93 | 0.00011011 | 11012 | 51.847 | 158 | 0.0056724 | 487
LAURELES 11116617 | LAURELES 1111 | 182371111 | FALSE | 1.7797 | 0.52328 | 2.303 | 39.5 | 0.00031059 | 7795 | 18.2241 | 590 | 0.0056434 | 488
HIGGINS 11041374 | HIGGINS 1104 | 152691104 | FALSE | 8.273 | 1.8185 | 9.1895 | 149.5 | 0.00049106 | 5486 | 12.416 | 744 | 0.0056258 | 489
PARADISE 1104457900 | PARADISE 1104 | 102831104 | FALSE | 13.3277 | 5.6112 | 13.8132 | 240.8333 | 0.00049862 | 5403 | 16.4669 | 632 | 0.0056077 | 490
VACAVILLE 110838316 | VACAVILLE 1108 | 63601108 | FALSE | 22.9879 | 0.92583 | 15.6887 | 420 | 0.00017425 | 10433 | 34.7494 | 313 | 0.0056058 | 491
SAN JOAQUIN #3 11035100 | SAN JOAQUIN #3 1103 | 252531103 | FALSE | 25.8561 | 2.3508 | 22.6432 | 491.5 | 0.00025354 | 9007 | 25.8158 | 438 | 0.0055802 | 492
KANAKA 110183288 | KANAKA 1101 | 103221101 | FALSE | 17.3082 | 0.46119 | 17.7694 | 331 | 0.00034668 | 7195 | 21.2352 | 533 | 0.0055443 | 493
COALINGA NO 1 110878186 | COALINGA NO 1 1108 | 252161108 |  | 35.9855 | 0.33631 |  | 713.5 | 0.00011163 | 11006 | 53.4698 | 147 | 0.0055326 | 494
SANTA YNEZ 1101Y52 | SANTA YNEZ 1101 | 182721101 | FALSE | 20.4198 | 0.98888 | 21.0494 | 394 | 0.00017228 | 10452 | 32.6482 | 338 | 0.0055232 | 495
SAN JOAQUIN #3 110210342 | SAN JOAQUIN #3 1102 | 252531102 | FALSE | 1.7906 | 0.47839 | 2.269 | 31.5 | 0.00058364 | 4489 | 9.4283 | 861 | 0.0054992 | 496
PARADISE 11032486 | PARADISE 1103 | 102831103 | FALSE | 12.1907 | 3.2636 | 15.2916 | 215.5 | 0.00038753 | 6612 | 23.7839 | 478 | 0.0054934 | 497
DIAMOND SPRINGS 11062100 | DIAMOND SPRINGS 1106 | 152261106 | FALSE | 38.1846 | 3.0083 | 41.1928 | 684.5 | 0.00029386 | 8133 | 24.8965 | 453 | 0.0054595 | 498
FROGTOWN 17011623 | FROGTOWN 1701 | 163451701 | FALSE | 15.2038 | 0.70198 | 15.9057 | 295.5 | 0.00014218 | 10771 | 52.205 | 156 | 0.0054401 | 499
DUNBAR 1102528 | DUNBAR 1102 | 43071102 | FALSE | 4.0235 | 0.24534 | 3.1626 | 76 | 0.00040926 | 6340 | 13.1297 | 721 | 0.0054266 | 500
CAMP EVERS 210510996 | CAMP EVERS 2105 | 83622105 | FALSE | 0.75301 | 0 | 0.75301 | 6.5 | 0.0035719 | 9 | 1.5131 | 1836 | 0.0054046 | 501
CLEAR LAKE 1101406 | CLEAR LAKE 1101 | 42141101 | FALSE | 32.9936 | 2.6493 | 11.4451 | 613.5 | 0.00025038 | 9068 | 27.4852 | 413 | 0.0054037 | 502
PARADISE 1103CB | PARADISE 1103 | 102831103 | FALSE | 6.6375 | 2.6595 | 1.3252 | 125.0333 | 0.00056957 | 4660 | 12.4797 | 742 | 0.0053751 | 503
MARIPOSA 21019400 | MARIPOSA 2101 | 254452101 | FALSE | 62.3092 | 3.7293 | 66.0383 | 1141.5 | 0.00021426 | 9793 | 29.689 | 375 | 0.00537 | 504
SAN JOAQUIN #2 1103157026 | SAN JOAQUIN #2 1103 | 252521103 | FALSE | 3.1855 | 0.3324 | 3.5179 | 56.8333 | 0.00028014 | 8418 | 17.0625 | 622 | 0.0053594 | 505
CALAVERAS CEMENT 110111188 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 29.9323 | 3.5587 | 33.4908 | 547 | 0.00023911 | 9299 | 24.1651 | 469 | 0.0053345 | 506
DUNLAP 1102CB | DUNLAP 1102 | 254061102 | FALSE | 6.6295 | 1.4243 | 8.0538 | 135 | 0.00022863 | 9523 | 23.238 | 490 | 0.0053343 | 507
LOS GATOS 1107CB | LOS GATOS 1107 | 82021107 | FALSE | 14.1093 | 4.6918 | 17.8706 | 236.5 | 0.00051598 | 5217 | 13.0059 | 726 | 0.0053096 | 508
JOLON 1103CB | JOLON 1103 | 182981103 | FALSE | 18.5216 | 0.074279 | 12.4623 | 351.5 | 0.00026938 | 8666 | 25.5721 | 443 | 0.0053075 | 509
LAYTONVILLE 11022502 | LAYTONVILLE 1102 | 42681102 | FALSE | 17.5791 | 0.30411 | 17.8831 | 345 | 0.00020695 | 9931 | 25.7714 | 440 | 0.0053046 | 510
POSO MOUNTAIN 2101CB | POSO MOUNTAIN 2101 | 253642101 | FALSE | 4.3358 | 0.011161 | 4.347 | 71.3333 | 0.00037112 | 6824 | 12.9097 | 727 | 0.0052897 | 511
CORNING 11021622 | CORNING 1102 | 103331102 | FALSE | 33.6775 | 0.468 | 34.1454 | 665.5 | 0.00012063 | 10946 | 47.7365 | 176 | 0.0052826 | 512
PEORIA 17051834 | PEORIA 1705 | 163781705 | FALSE | 23.3416 | 1.244 | 24.0063 | 430.5 | 0.0001757 | 10413 | 33.9469 | 320 | 0.0052718 | 513
KONOCTI 1108950 | KONOCTI 1108 | 43311108 | FALSE | 7.4086 | 2.6715 | 7.7609 | 129 | 0.00032165 | 7596 | 17.7484 | 605 | 0.0052635 | 514
MARIPOSA 2102241564 | MARIPOSA 2102 | 254452102 | FALSE | 1.1694 | 0.047896 | 0.68367 | 22.25 | 0.00039968 | 6460 | 33.5817 | 325 | 0.0052627 | 515
LOS OSITOS 21037062 | LOS OSITOS 2103 | 182082103 | FALSE | 12.1456 | 0.41501 | 12.5606 | 243.5 | 0.00013796 | 10812 | 38.8383 | 264 | 0.0052285 | 516
DUNLAP 11037220 | DUNLAP 1103 | 254061103 | FALSE | 25.156 | 1.0808 | 26.2367 | 502.5 | 0.00013054 | 10881 | 38.4814 | 270 | 0.0052175 | 517
GRASS VALLEY 11032110 | GRASS VALLEY 1103 | 152031103 | FALSE | 19.6684 | 1.5229 | 20.7297 | 346.5 | 0.00039199 | 6542 | 13.3429 | 717 | 0.0051957 | 518
HOPLAND 1101768 | HOPLAND 1101 | 42251101 | FALSE | 19.6589 | 0.65136 | 16.5351 | 381 | 0.00016255 | 10569 | 35.9678 | 293 | 0.0051934 | 519
MORGAN HILL 2111123422 | MORGAN HILL 2111 | 83242111 | FALSE | 1.3237 | 0.035114 | 1.3588 | 21.5 | 0.00019198 | 10179 | 27.5741 | 411 | 0.0051696 | 520
GRAYS FLAT 0401CB | GRAYS FLAT 0401 | 102530401 | FALSE | 10.6401 | 0.74146 | 11.3815 | 214 | 0.00027123 | 8627 | 20.8754 | 537 | 0.0051671 | 521
HOPLAND 11014626 | HOPLAND 1101 | 42251101 | FALSE | 31.1609 | 1.1063 | 25.9391 | 596 | 0.00015764 | 10624 | 38.3532 | 272 | 0.0051604 | 522
ELECTRA 11026014 | ELECTRA 1102 | 162161102 | FALSE | 5.0942 | 0.06445 | 5.1586 | 87.3333 | 0.00022694 | 9565 | 22.13 | 517 | 0.0051584 | 523
BRUNSWICK 11041020 | BRUNSWICK 1104 | 152481104 | FALSE | 28.7064 | 2.3611 | 31.0674 | 522 | 0.00030879 | 7826 | 18.8799 | 575 | 0.0051473 | 524
CLARK ROAD 11022068 | CLARK ROAD 1102 | 103091102 | FALSE | 11.0914 | 0.22245 | 11.0281 | 201.3333 | 0.00019565 | 10118 | 25.265 | 447 | 0.0051287 | 525
WYANDOTTE 11031508 | WYANDOTTE 1103 | 102911103 | FALSE | 26.9664 | 0.39749 | 27.3638 | 485 | 0.00029291 | 8149 | 15.1799 | 657 | 0.0051219 | 526
GIRVAN 1101CB | GIRVAN 1101 | 103401101 | FALSE | 3.2748 | 0.15617 | 1.3882 | 57 | 0.0006654 | 3492 | 8.3795 | 918 | 0.0051162 | 527
PASO ROBLES 1104R56 | PASO ROBLES 1104 | 182611104 | FALSE | 12.4436 | 0.52311 | 11.4113 | 218 | 0.00014639 | 10736 | 31.8603 | 346 | 0.0051132 | 528
CAMP EVERS 210510214 | CAMP EVERS 2105 | 83622105 | FALSE | 2.2219 | 1.211 | 3.4329 | 35.5 | 0.0019948 | 29 | 2.5655 | 1493 | 0.0051129 | 529
PINE GROVE 110235576 | PINE GROVE 1102 | 163751102 | FALSE | 7.8751 | 0.64857 | 8.5237 | 150 | 0.00041013 | 6332 | 14.9506 | 667 | 0.005103 | 530
MARIPOSA 210110070 | MARIPOSA 2101 | 254452101 | FALSE | 25.7417 | 0.6194 | 26.361 | 490 | 0.00013803 | 10811 | 35.7396 | 298 | 0.0051015 | 531
LUCERNE 110638632 | LUCERNE 1106 | 43351106 | FALSE | 4.6558 | 1.4036 | 5.8995 | 72 | 0.0003409 | 7293 | 14.83 | 669 | 0.0050895 | 532
HIGGINS 1104324510 | HIGGINS 1104 | 152691104 | FALSE | 12.4416 | 0.47441 | 12.916 | 234 | 0.00021325 | 9816 | 24.0112 | 472 | 0.0050836 | 533
CALISTOGA 1102769230 | CALISTOGA 1102 | 42711102 | FALSE | 16.549 | 1.2553 | 10.4308 | 310 | 0.00052441 | 5134 | 11.2561 | 790 | 0.0050695 | 534
DIAMOND SPRINGS 1106930190 | DIAMOND SPRINGS 1106 | 152261106 | FALSE | 18.1945 | 2.4443 | 19.0128 | 323 | 0.00034326 | 7255 | 17.1573 | 619 | 0.0050676 | 535
RACETRACK 1704CB | RACETRACK 1704 | 163761704 | FALSE | 22.431 | 1.282 | 23.7129 | 415.5 | 0.00020569 | 9946 | 26.2245 | 432 | 0.0050601 | 536
CLOVERDALE 1102429006 | CLOVERDALE 1102 | 42821102 | FALSE | 1.9585 | 0.077388 | 2.0056 | 36.5 | 0.0002517 | 9047 | 22.1333 | 515 | 0.0050573 | 537
MOUNTAIN QUARRIES 210151584 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 21.8671 | 1.3073 | 23.1744 | 398.5 | 0.00021035 | 9869 | 24.1589 | 470 | 0.0050499 | 538
PIT NO 5 11011618 | PIT NO 5 1101 | 101321101 | FALSE | 6.1596 | 0 | 6.1596 | 123 | 0.00020957 | 9879 | 19.5392 | 563 | 0.005049 | 539
PUEBLO 2102943820 | PUEBLO 2102 | 43292102 | FALSE | 2.4801 | 0.030096 | 1.8021 | 54.5 | 0.00032213 | 7590 | 16.3828 | 633 | 0.0050048 | 540
MARIPOSA 21021960 | MARIPOSA 2102 | 254452102 | FALSE | 24.1642 | 0.88355 | 25.0477 | 465 | 0.00018836 | 10232 | 24.847 | 455 | 0.0050042 | 541
SHADY GLEN 1101585766 | SHADY GLEN 1101 | 152431101 | FALSE | 0.84767 | 0.074759 | 0.86356 | 13 | 0.0006941 | 3167 | 7.1772 | 987 | 0.0049817 | 542
CALPINE 1146400 | CALPINE 1146 | 48011146 | FALSE | 1.8423 | 0 | 1.8423 | 37.5 | 0.00017874 | 10369 | 27.7742 | 406 | 0.0049805 | 543
CAMP EVERS 210660120 | CAMP EVERS 2106 | 83622106 | FALSE | 4.2802 | 0.37267 | 4.6528 | 77 | 0.0010892 | 497 | 4.5818 | 1176 | 0.0049798 | 544
GIRVAN 11021028 | GIRVAN 1102 | 103401102 | FALSE | 17.753 | 2.0262 | 19.7791 | 322 | 0.00043575 | 6059 | 13.9873 | 693 | 0.0049438 | 545
CAMP EVERS 210510294 | CAMP EVERS 2105 | 83622105 | FALSE | 8.3678 | 3.438 | 11.8058 | 126 | 0.0022032 | 21 | 2.1866 | 1580 | 0.0049416 | 546
SAN ARDO 1102896438 | SAN ARDO 1102 | 182191102 |  | 25.0015 | 0.20882 |  | 509.5 | 0.00010561 | 11039 | 43.9598 | 205 | 0.0049302 | 547
PINE GROVE 1102269286 | PINE GROVE 1102 | 163751102 | FALSE | 28.1464 | 3.5061 | 31.6525 | 494.5 | 0.00052702 | 5104 | 13.8791 | 695 | 0.0049276 | 548
PIT NO 7 1101CB | PIT NO 7 1101 | 103501101 | FALSE | 2.8406 | 0 | 2.8406 | 57 | 0.00011422 | 10989 | 42.6511 | 217 | 0.0049268 | 549
BEAR VALLEY 2105454432 | BEAR VALLEY 2105 | 252192105 | FALSE | 13.9808 | 0.59342 | 14.5742 | 276.5 | 0.00022273 | 9652 | 21.178 | 534 | 0.0049103 | 550
TEMPLETON 2111A66 | TEMPLETON 2111 | 183052111 | FALSE | 34.0519 | 3.2296 | 37.2814 | 650.8333 | 0.00022731 | 9555 | 22.2956 | 508 | 0.0048868 | 551
TASSAJARA 2112676362 | TASSAJARA 2112 | 14662112 | FALSE | 3.0421 | 0.11468 | 3.1568 | 63 | 0.00024778 | 9132 | 20.8384 | 538 | 0.0048858 | 552
UKIAH 1114408 | UKIAH 1114 | 42771114 | FALSE | 38.1194 | 0.8111 | 37.8981 | 752.5 | 0.00020255 | 10003 | 24.2647 | 464 | 0.0048805 | 553
UKIAH 1111807988 | UKIAH 1111 | 42771111 | FALSE | 4.1426 | 0.066032 | 3.7621 | 70.5 | 0.00019632 | 10105 | 32.7078 | 335 | 0.0048798 | 554
IGNACIO 1105775176 | IGNACIO 1105 | 42481105 | TRUE | 0.45111 | 0.18177 | 0.59648 | 8 | 0.00065133 | 3693 | 7.6978 | 954 | 0.0048734 | 555
SILVERADO 2105131568 | SILVERADO 2105 | 43432105 | FALSE | 4.8943 | 0.74499 | 4.4171 | 89.5 | 0.00080216 | 1954 | 5.9305 | 1075 | 0.0048458 | 556
CURTIS 170384944 | CURTIS 1703 | 163351703 | FALSE | 57.355 | 2.4316 | 59.7865 | 1098 | 0.00016364 | 10554 | 33.3446 | 328 | 0.0048395 | 557
PINE GROVE 11021222 | PINE GROVE 1102 | 163751102 | FALSE | 17.0253 | 2.6612 | 19.6864 | 293.5 | 0.00058799 | 4443 | 8.7259 | 897 | 0.0048336 | 558
SISQUOC 110245261 | SISQUOC 1102 | 182811102 | TRUE | 13.3525 | 0 | 0.072712 | 122.5 | 0.00011134 | 11008 | 74.6652 | 50 | 0.0048221 | 559
HIGGINS 11032194 | HIGGINS 1103 | 152691103 | FALSE | 2.7524 | 0.44364 | 1.5397 | 46 | 0.00061956 | 4054 | 9.2405 | 869 | 0.0048197 | 560
POTTER VALLEY P H 110576498 | POTTER VALLEY P H 1105 | 42281105 | FALSE | 6.2878 | 0.86844 | 7.1562 | 126.5 | 0.00024245 | 9238 | 18.7454 | 578 | 0.0048188 | 561
SHINGLE SPRINGS 2108449638 | SHINGLE SPRINGS 2108 | 153652108 | TRUE | 0.032317 | 0 | 0.032317 | 0.5 | 0.00032825 | 7480 | 14.6567 | 675 | 0.004811 | 562
ALLEGHANY 1101183068 | ALLEGHANY 1101 | 152101101 | FALSE | 3.3692 | 0.0062909 | 3.3755 | 65 | 0.00044816 | 5933 | 11.3448 | 787 | 0.0048054 | 563
FROGTOWN 1702592404 | FROGTOWN 1702 | 163451702 | TRUE | 0.25792 | 0.092001 | 0.21794 | 4.6667 | 0.00079186 | 2045 | 7.4423 | 966 | 0.0048038 | 564
MARIPOSA 2101309438 | MARIPOSA 2101 | 254452101 | FALSE | 8.0755 | 1.3315 | 3.2272 | 146.75 | 0.00033026 | 7445 | 20.0094 | 557 | 0.0047998 | 565
CALAVERAS CEMENT 1101CB | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 18.3839 | 3.5025 | 10.4499 | 329.5 | 0.00048431 | 5552 | 14.3661 | 685 | 0.0047662 | 566
SARATOGA 1107LC12 | SARATOGA 1107 | 83371107 | FALSE | 7.3435 | 1.1324 | 8.4759 | 137 | 0.00076016 | 2382 | 6.3987 | 1038 | 0.0047379 | 567
CHOLAME 21025597 | CHOLAME 2102 | 182562102 | FALSE | 4.8632 | 0.030204 | 4.8934 | 97.5 | 0.00013997 | 10786 | 35.3606 | 306 | 0.0047251 | 568
AUBERRY 1101R2578 | AUBERRY 1101 | 254151101 | FALSE | 44.8682 | 2.0464 | 46.9145 | 807 | 0.00013013 | 10883 | 34.8196 | 311 | 0.0047219 | 569
OAKHURST 110310190 | OAKHURST 1103 | 254421103 | FALSE | 8.3751 | 0.7772 | 9.1523 | 153.8333 | 0.000451 | 5910 | 9.9736 | 834 | 0.0047188 | 570
KIRKER 2104442850 | KIRKER 2104 | 14452104 | FALSE | 5.6891 | 0.21663 | 5.9057 | 111 | 0.00016543 | 10529 | 39.8791 | 254 | 0.00471 | 571
IGNACIO 11051943 | IGNACIO 1105 | 42481105 | FALSE | 1.2084 | 0.4482 | 1.6566 | 23.5 | 0.00041918 | 6233 | 11.1711 | 794 | 0.0046837 | 572
POTTER VALLEY P H 11051904 | POTTER VALLEY P H 1105 | 42281105 | FALSE | 40.2546 | 2.1075 | 25.2997 | 754.5 | 0.00018529 | 10272 | 26.11 | 435 | 0.0046795 | 573
OAKHURST 1103719490 | OAKHURST 1103 | 254421103 | FALSE | 2.9793 | 1.4972 | 4.4765 | 64.3333 | 0.00055564 | 4808 | 7.7924 | 948 | 0.004675 | 574
BIG MEADOWS 21012248 | BIG MEADOWS 2101 | 102812101 | FALSE | 9.2087 | 0.11209 | 9.3208 | 174.5 | 0.00044488 | 5964 | 9.8965 | 839 | 0.0046735 | 575
PINE GROVE 110283098 | PINE GROVE 1102 | 163751102 | FALSE | 7.9157 | 1.4591 | 9.3747 | 154.5 | 0.00038369 | 6657 | 12.1057 | 755 | 0.0046727 | 576
SILVERADO 2103507513 | SILVERADO 2103 | 43432103 | FALSE | 5.0603 | 1.1858 | 3.0073 | 103.5 | 0.00067171 | 3420 | 7.3763 | 969 | 0.0046682 | 577
MORGAN HILL 2111919856 | MORGAN HILL 2111 | 83242111 | FALSE | 9.3769 | 0.55388 | 9.9308 | 184.5 | 0.00022218 | 9666 | 23.5227 | 485 | 0.0046575 | 578
FROGTOWN 17027134 | FROGTOWN 1702 | 163451702 | FALSE | 22.9184 | 0.41588 | 19.4184 | 369.3333 | 0.00018967 | 10220 | 29.6388 | 378 | 0.0046229 | 579
AUBERRY 1101R2838 | AUBERRY 1101 | 254151101 | FALSE | 20.5038 | 2.4082 | 22.9119 | 375 | 0.00019716 | 10087 | 28.1519 | 400 | 0.00462 | 580
DOBBINS 110191464 | DOBBINS 1101 | 153741101 | FALSE | 7.0186 | 0.37564 | 7.3665 | 125 | 0.00030301 | 7948 | 14.544 | 679 | 0.0045999 | 581
HIGHLANDS 11031282 | HIGHLANDS 1103 | 43361103 | FALSE | 8.0146 | 0.84142 | 6.5549 | 150.5 | 0.00022494 | 9610 | 13.8319 | 699 | 0.0045905 | 582
CEDAR CREEK 1101CB | CEDAR CREEK 1101 | 103321101 | FALSE | 48.5242 | 1.5506 | 15.7692 | 929 | 0.00019366 | 10153 | 19.5328 | 565 | 0.0045868 | 583
CEDAR CREEK 11011664 | CEDAR CREEK 1101 | 103321101 | FALSE | 29.3637 | 1.426 | 30.7896 | 547 | 0.0002468 | 9148 | 17.8708 | 602 | 0.0045848 | 584
BEAR VALLEY 210190550 | BEAR VALLEY 2101 | 252192101 | FALSE | 8.0911 | 0.27565 | 8.3667 | 152 | 0.00013214 | 10865 | 33.7285 | 323 | 0.004555 | 585
PUEBLO 1105637242 | PUEBLO 1105 | 43291105 | FALSE | 21.9074 | 0.73202 | 15.5836 | 399.5 | 0.00022871 | 9520 | 18.911 | 572 | 0.0045508 | 586
ORO FINO 11022096 | ORO FINO 1102 | 103031102 | FALSE | 13.9689 | 0.85407 | 14.8229 | 255.5 | 0.000466 | 5738 | 13.8216 | 700 | 0.0045219 | 587
UPPER LAKE 1101CB | UPPER LAKE 1101 | 42871101 | FALSE | 1.0869 | 0 | 1.0869 | 20.5 | 0.00011878 | 10960 | 56.8229 | 129 | 0.0045199 | 588
CALISTOGA 1101843761 | CALISTOGA 1101 | 42711101 | FALSE | 4.1326 | 0.19463 | 3.7869 | 86 | 0.00031054 | 7797 | 14.3682 | 683 | 0.0045153 | 589
DUNLAP 11027360 | DUNLAP 1102 | 254061102 | FALSE | 8.9415 | 0.38598 | 9.3275 | 162 | 0.00013494 | 10839 | 31.9335 | 345 | 0.004509 | 590
OAKHURST 1102683678 | OAKHURST 1102 | 254421102 | FALSE | 8.1618 | 0.61134 | 7.9741 | 152.3333 | 0.00036578 | 6910 | 25.7902 | 439 | 0.0045005 | 591
CLOVERDALE 1102674 | CLOVERDALE 1102 | 42821102 | FALSE | 20.2103 | 1.5238 | 16.948 | 386.5 | 0.0002294 | 9501 | 26.1708 | 433 | 0.0044866 | 592
DUNLAP 1103CB | DUNLAP 1103 | 254061103 | FALSE | 5.5101 | 0.090982 | 5.601 | 102 | 0.00015219 | 10676 | 30.1031 | 369 | 0.0044679 | 593
SILVERADO 2105309298 | SILVERADO 2105 | 43432105 | FALSE | 1.9176 | 0.17056 | 0.92293 | 35.5 | 0.00046324 | 5769 | 9.1645 | 875 | 0.0044669 | 594
HARTLEY 1101789752 | HARTLEY 1101 | 43211101 | FALSE | 4.1528 | 0.48847 | 2.8421 | 77.5 | 0.0001388 | 10804 | 38.7281 | 266 | 0.0044545 | 595
FROGTOWN 1702307998 | FROGTOWN 1702 | 163451702 | TRUE | 0.47396 | 0.10208 | 0.53862 | 9.5 | 0.00035826 | 7004 | 11.6202 | 776 | 0.0044531 | 596
ELK CREEK 110137334 | ELK CREEK 1101 | 102781101 | FALSE | 9.4194 | 1.3785 | 10.7979 | 185 | 0.00018137 | 10331 | 29.3306 | 380 | 0.0044503 | 597
PIT NO 3 21011386 | PIT NO 3 2101 | 103732101 | FALSE | 6.7694 | 0.36769 | 6.8493 | 126 | 0.00024715 | 9141 | 17.062 | 623 | 0.0044429 | 598
CHALLENGE 1101CB | CHALLENGE 1101 | 103201101 | FALSE | 16.4398 | 1.3415 | 17.7813 | 320 | 0.0006032 | 4264 | 9.5764 | 854 | 0.004432 | 599
CLOVERDALE 1102801904 | CLOVERDALE 1102 | 42821102 | TRUE | 0.032241 | 0 | 0.032241 | 1 | 0.000158 | 10616 | 28.0182 | 402 | 0.0044269 | 600
CAMP EVERS 2105426822 | CAMP EVERS 2105 | 83622105 | FALSE | 1.1372 | 0 | 1.1372 | 21 | 0.0018114 | 42 | 2.407 | 1531 | 0.004412 | 601
WEIMAR 1102CB | WEIMAR 1102 | 152491102 | FALSE | 14.9283 | 3.0776 | 14.7595 | 275.8333 | 0.00033282 | 7409 | 13.8677 | 697 | 0.004401 | 602
SILVERADO 2103403102 | SILVERADO 2103 | 43432103 | TRUE | 1.719 | 0.13936 | 0.57115 | 36.5 | 0.00053505 | 5010 | 6.8429 | 1007 | 0.004396 | 603
SAN JOAQUIN #3 1101673480 | SAN JOAQUIN #3 1101 | 252531101 | FALSE | 12.5405 | 2.8001 | 15.3405 | 251 | 0.00039831 | 6473 | 10.705 | 812 | 0.0043954 | 604
CLARKSVILLE 210419772 | CLARKSVILLE 2104 | 153612104 | FALSE | 18.1334 | 0.4472 | 17.5325 | 320.5 | 0.00022891 | 9514 | 23.1757 | 493 | 0.0043871 | 605
MILPITAS 110962157 | MILPITAS 1109 | 82831109 | TRUE | 0.060309 | 0 | 0.060309 | 1 | 0.0001507 | 10697 | 29.1075 | 385 | 0.0043865 | 606
DUNBAR 1103681238 | DUNBAR 1103 | 43071103 | TRUE | 0.4879 | 0.0168 | 0.5047 | 9.5 | 0.00057647 | 4571 | 7.9186 | 942 | 0.0043839 | 607
FROGTOWN 17016807 | FROGTOWN 1701 | 163451701 | FALSE | 4.9864 | 0.5188 | 5.5051 | 89.5 | 0.0003583 | 7002 | 11.1387 | 796 | 0.0043786 | 608
PANOCHE 11034008 | PANOCHE 1103 | 253671103 | FALSE | 35.1601 | 0.93104 | 36.091 | 700.5 | 7.7827e-05 | 11110 | 56.1234 | 132 | 0.0043547 | 609
CURTIS 170411300 | CURTIS 1704 | 163351704 | FALSE | 3.5255 | 0.5136 | 4.0391 | 61.8333 | 0.00030678 | 7871 | 17.6755 | 606 | 0.0043464 | 610
LOS GATOS 1108LB86 | LOS GATOS 1108 | 82021108 | FALSE | 5.4015 | 3.2445 | 6.7251 | 89.5 | 0.00071124 | 2959 | 6.667 | 1022 | 0.0043437 | 611
OILFIELDS 1103N48 | OILFIELDS 1103 | 182391103 | FALSE | 47.5257 | 0.77241 | 48.2979 | 903.5 | 0.00013702 | 10820 | 33.9674 | 319 | 0.0043433 | 612
CALAVERAS CEMENT 1101585 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 14.1242 | 0.30013 | 14.4243 | 271.5 | 0.0001167 | 10974 | 39.148 | 261 | 0.0043402 | 613
AUBERRY 1101R2839 | AUBERRY 1101 | 254151101 | FALSE | 12.5465 | 0.58771 | 13.1341 | 240 | 0.00015147 | 10684 | 32.7199 | 334 | 0.0043344 | 614
CORNING 110164090 | CORNING 1101 | 103331101 | FALSE | 13.6417 | 0.73144 | 14.3731 | 256.5 | 0.00020393 | 9980 | 22.038 | 520 | 0.0043341 | 615
MONTICELLO 1101130412 | MONTICELLO 1101 | 43051101 | FALSE | 3.8729 | 0 | 3.7796 | 68.5 | 8.9547e-05 | 11084 | 54.3521 | 144 | 0.0043264 | 616
ALTO 11243121 | ALTO 1124 | 42031124 | FALSE | 2.7541 | 1.5033 | 4.2574 | 44.5 | 0.0010816 | 522 | 4.2595 | 1215 | 0.0043083 | 617
OAKHURST 1101636114 | OAKHURST 1101 | 254421101 | FALSE | 20.5595 | 0.21081 | 20.7702 | 400 | 0.00010933 | 11018 | 30.8953 | 357 | 0.0043039 | 618
SILVERADO 2104708 | SILVERADO 2104 | 43432104 | FALSE | 4.9167 | 1.2445 | 4.3496 | 87 | 0.00078991 | 2062 | 5.8491 | 1081 | 0.0043024 | 619
ALTO 1124430 | ALTO 1124 | 42031124 | FALSE | 7.0398 | 4.7966 | 11.8364 | 120 | 0.0011412 | 384 | 3.5391 | 1308 | 0.0042918 | 620
RED BLUFF 11041302 | RED BLUFF 1104 | 103541104 | FALSE | 14.529 | 0.27416 | 13.6919 | 276 | 0.00019418 | 10143 | 27.2944 | 417 | 0.0042782 | 621
PARADISE 1104961990 | PARADISE 1104 | 102831104 | FALSE | 5.0355 | 2.0714 | 7.1069 | 102 | 0.00046645 | 5735 | 18.6852 | 579 | 0.0042646 | 622
SARATOGA 1105LC14 | SARATOGA 1105 | 83371105 | FALSE | 11.2464 | 2.0958 | 11.0156 | 204.5 | 0.00055629 | 4800 | 7.5973 | 960 | 0.0042618 | 623
CLOVERDALE 110247214 | CLOVERDALE 1102 | 42821102 | TRUE | 0.019382 | 0 | 0.019382 | 0.5 | 0.00015088 | 10693 | 28.1634 | 399 | 0.0042493 | 624
EL DORADO PH 21016852 | EL DORADO PH 2101 | 152762101 | FALSE | 25.0605 | 3.3043 | 28.3647 | 430.5 | 0.00057117 | 4644 | 9.2166 | 871 | 0.0042306 | 625
OREGON TRAIL 11031448 | OREGON TRAIL 1103 | 103521103 | FALSE | 30.6012 | 0.87275 | 31.4739 | 583.5 | 0.00018508 | 10275 | 21.5438 | 529 | 0.0042254 | 626
STAFFORD 11021048 | STAFFORD 1102 | 43201102 | FALSE | 5.2099 | 1.5272 | 6.7341 | 100 | 0.00047229 | 5674 | 9.4173 | 862 | 0.0042223 | 627
CAMP EVERS 210595050 | CAMP EVERS 2105 | 83622105 | TRUE | 0.14266 | 0 | 0.14266 | 2.25 | 0.0029515 | 12 | 1.4055 | 1922 | 0.0042092 | 628
SARATOGA 1107LC26 | SARATOGA 1107 | 83371107 | FALSE | 5.644 | 1.5227 | 7.1667 | 109.5 | 0.00058705 | 4455 | 7.2434 | 980 | 0.0042088 | 629
MENLO 11028896 | MENLO 1102 | 24131102 | FALSE | 1.5357 | 0.055549 | 0.6657 | 21.8333 | 0.00087281 | 1404 | 4.4236 | 1197 | 0.0042054 | 630
WILLITS 11032500 | WILLITS 1103 | 42661103 | FALSE | 29.677 | 0.43812 | 30.1151 | 509.5 | 0.0001916 | 10185 | 22.1713 | 513 | 0.0041992 | 631
DUNBAR 110347964 | DUNBAR 1103 | 43071103 | FALSE | 7.7118 | 0.68989 | 7.0902 | 153 | 0.00041176 | 6315 | 11.5419 | 780 | 0.0041839 | 632
HIGGINS 1103995672 | HIGGINS 1103 | 152691103 | FALSE | 5.8155 | 0.66721 | 3.5944 | 102.5 | 0.00054292 | 4923 | 8.2422 | 926 | 0.0041805 | 633
BEAR VALLEY 210110019 | BEAR VALLEY 2101 | 252192101 | FALSE | 1.933 | 0.023521 | 1.9565 | 37 | 0.00016543 | 10528 | 32.0809 | 344 | 0.0041706 | 634
SAN LUIS OBISPO 1101V12 | SAN LUIS OBISPO 1101 | 182631101 | FALSE | 20.457 | 1.1328 | 21.5897 | 392 | 0.0001889 | 10227 | 23.687 | 481 | 0.0041542 | 635
PIT NO 1 1101CB | PIT NO 1 1101 | 103721101 | FALSE | 6.6314 | 0.17071 | 6.8021 | 126 | 0.00018365 | 10296 | 27.4142 | 415 | 0.0041462 | 636
PUEBLO 1104580658 | PUEBLO 1104 | 43291104 | FALSE | 10.2757 | 0.67658 | 9.6571 | 189.5 | 0.00030058 | 8008 | 15.1812 | 656 | 0.0041408 | 637
LAYTONVILLE 1101518 | LAYTONVILLE 1101 | 42681101 | FALSE | 22.4154 | 0.43971 | 2.133 | 415 | 0.00018972 | 10218 | 23.9587 | 474 | 0.0041384 | 638
HICKS 2101XR250 | HICKS 2101 | 83432101 |  | 13.1469 | 3.0252 |  | 251.5 | 0.00032722 | 7500 | 16.661 | 628 | 0.0041308 | 639
BRUNSWICK 11052210 | BRUNSWICK 1105 | 152481105 | FALSE | 24.6511 | 4.0251 | 26.327 | 459 | 0.00039413 | 6521 | 11.779 | 767 | 0.0041204 | 640
MORGAN HILL 2111XR398 | MORGAN HILL 2111 | 83242111 | FALSE | 29.2145 | 1.376 | 25.4231 | 541.5 | 0.00020629 | 9943 | 20.6409 | 545 | 0.0041198 | 641
ATASCADERO 1101A02 | ATASCADERO 1101 | 182541101 | FALSE | 25.261 | 1.6624 | 26.9234 | 493.3333 | 0.00017449 | 10428 | 22.0191 | 521 | 0.0041179 | 642
JESSUP 1102158468 | JESSUP 1102 | 103441102 | FALSE | 0.85775 | 0.33345 | 0.91946 | 14.5 | 0.00066855 | 3452 | 6.8774 | 1003 | 0.0041155 | 643
CALAVERAS CEMENT 110111236 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 19.5866 | 0.68694 | 20.2735 | 379.5 | 0.00021441 | 9786 | 22.1956 | 512 | 0.0041131 | 644
CHOLAME 2102867686 | CHOLAME 2102 | 182562102 | FALSE | 25.2044 | 0.24857 | 20.4866 | 501.5 | 0.00011655 | 10976 | 35.7677 | 297 | 0.0041105 | 645
OILFIELDS 1103N62 | OILFIELDS 1103 | 182391103 | FALSE | 5.6723 | 0.14599 | 5.8183 | 103.5 | 0.00014719 | 10724 | 29.1519 | 384 | 0.0041021 | 646
LOS GATOS 110160052 | LOS GATOS 1101 | 82021101 | FALSE | 1.9053 | 0.20347 | 2.1087 | 35 | 0.00045037 | 5919 | 10.4014 | 821 | 0.0040937 | 647
WOODACRE 1102851 | WOODACRE 1102 | 43021102 | FALSE | 1.2608 | 0.97221 | 2.233 | 24.5 | 0.00087275 | 1405 | 4.8268 | 1157 | 0.0040889 | 648
OTTER 110263868 | OTTER 1102 | 182941102 | FALSE | 15.7816 | 1.4621 | 17.2437 | 320 | 0.00066088 | 3566 | 6.8998 | 1002 | 0.0040828 | 649
SCE REFUGIO 1701CB | SCE REFUGIO 1701 | 188071701 | TRUE | 0.0022449 | 0 | 0.0022449 | 0.5 | 0.00013825 | 10810 | 29.4705 | 379 | 0.0040743 | 650
OAKHURST 110310570 | OAKHURST 1103 | 254421103 | FALSE | 9.5969 | 0.27366 | 9.8705 | 188 | 0.00021126 | 9857 | 20.687 | 543 | 0.004065 | 651
ALLEGHANY 1101804 | ALLEGHANY 1101 | 152101101 | FALSE | 18.4885 | 3.0863 | 21.5748 | 349.5 | 0.00041004 | 6335 | 10.6842 | 814 | 0.0040462 | 652
CURTIS 170247488 | CURTIS 1702 | 163351702 | FALSE | 20.7078 | 3.0136 | 20.4528 | 365.5 | 0.00023797 | 9322 | 33.5769 | 326 | 0.0040259 | 653
OILFIELDS 1103N04 | OILFIELDS 1103 | 182391103 | TRUE | 0.37741 | 0 | 0.37741 | 8.8333 | 0.00018084 | 10343 | 22.2089 | 511 | 0.0040162 | 654
OILFIELDS 1103451760 | OILFIELDS 1103 | 182391103 | TRUE | 0.061054 | 0 | 0.061054 | 1.3333 | 0.00018049 | 10346 | 22.2089 | 509 | 0.0040085 | 655
CAMP EVERS 210533542 | CAMP EVERS 2105 | 83622105 | FALSE | 2.6586 | 0.90917 | 3.5677 | 41.5 | 0.0015525 | 89 | 2.5481 | 1496 | 0.003969 | 656
ORO FINO 11012022 | ORO FINO 1101 | 103031101 | FALSE | 16.1465 | 5.811 | 21.9575 | 278 | 0.00081174 | 1885 | 4.0723 | 1248 | 0.003959 | 657
CURTIS 170210940 | CURTIS 1702 | 163351702 | FALSE | 10.5907 | 1.4762 | 9.3888 | 194.3333 | 0.00034569 | 7212 | 17.9454 | 599 | 0.0039501 | 658
SUNOL 1101MR299 | SUNOL 1101 | 14241101 | FALSE | 4.9395 | 1.5957 | 6.5352 | 97 | 0.00053598 | 4996 | 7.3307 | 972 | 0.00393 | 659
VOLTA 1102CB | VOLTA 1102 | 102541102 | FALSE | 3.3373 | 0 | 3.3373 | 62.8333 | 0.0002784 | 8463 | 21.6582 | 527 | 0.0039262 | 660
OILFIELDS 11032757 | OILFIELDS 1103 | 182391103 | FALSE | 2.4949 | 0.022912 | 2.5178 | 51 | 0.00014391 | 10756 | 26.9973 | 423 | 0.0039244 | 661
BRUNSWICK 110350070 | BRUNSWICK 1103 | 152481103 | FALSE | 8.0109 | 1.0477 | 9.0586 | 142.5 | 0.00039853 | 6470 | 9.5975 | 853 | 0.0039176 | 662
CURTIS 170349746 | CURTIS 1703 | 163351703 | TRUE | 0.31098 | 0 | 0.31098 | 6.5 | 0.00027247 | 8595 | 14.3663 | 684 | 0.0039143 | 663
HIGGINS 11041006 | HIGGINS 1104 | 152691104 | FALSE | 19.9813 | 4.1621 | 11.482 | 355 | 0.00057487 | 4592 | 10.8825 | 807 | 0.0039127 | 664
JARVIS 1111907698 | JARVIS 1111 | 13501111 | FALSE | 1.8294 | 0.039466 | 0.96108 | 34.5 | 0.00045826 | 5832 | 8.9474 | 886 | 0.0039124 | 665
SWIFT 2110XR254 | SWIFT 2110 | 83392110 | FALSE | 24.8051 | 0.21148 | 25.0165 | 482.5 | 0.00012655 | 10915 | 33.1731 | 330 | 0.0039097 | 666
DUNBAR 110379086 | DUNBAR 1103 | 43071103 | FALSE | 6.7893 | 1.3995 | 7.8329 | 133 | 0.00048546 | 5545 | 8.4666 | 909 | 0.0039079 | 667
APPLE HILL 210297982 | APPLE HILL 2102 | 153662102 | FALSE | 9.6784 | 0.51616 | 10.1946 | 184 | 0.00037817 | 6724 | 10.987 | 801 | 0.0039067 | 668
ATASCADERO 1101A50 | ATASCADERO 1101 | 182541101 | FALSE | 21.7907 | 4.4897 | 23.3202 | 396.3333 | 0.00028134 | 8392 | 17.5249 | 609 | 0.0039066 | 669
WYANDOTTE 11071510 | WYANDOTTE 1107 | 102911107 | FALSE | 25.3115 | 0.74358 | 26.055 | 470.5 | 0.00017794 | 10381 | 20.4441 | 548 | 0.0039035 | 670
DUNLAP 110239190 | DUNLAP 1102 | 254061102 | FALSE | 1.7106 | 0.24848 | 1.9591 | 32 | 0.00017332 | 10440 | 22.1465 | 514 | 0.0038999 | 671
CHOLAME 2102796386 | CHOLAME 2102 | 182562102 | FALSE | 39.8284 | 0.74448 | 34.3743 | 760 | 0.00011297 | 10997 | 34.3014 | 316 | 0.0038963 | 672
MIDDLETOWN 1101481876 | MIDDLETOWN 1101 | 43141101 | FALSE | 1.5901 | 0.020451 | 0.83906 | 30.5 | 0.00022936 | 9504 | 13.0439 | 725 | 0.0038943 | 673
FULTON 1107145720 | FULTON 1107 | 42561107 | FALSE | 10.2573 | 0.64409 | 10.9013 | 192 | 0.00031116 | 7784 | 11.8021 | 765 | 0.0038831 | 674
KING CITY 11037038 | KING CITY 1103 | 182031103 | FALSE | 22.0226 | 1.898 | 18.5725 | 428.5 | 0.00013066 | 10880 | 35.9732 | 292 | 0.0038783 | 675
CURTIS 170539256 | CURTIS 1705 | 163351705 | FALSE | 26.17 | 2.2122 | 28.3822 | 487 | 0.00023841 | 9317 | 17.8268 | 604 | 0.003875 | 676
AUBERRY 1101233716 | AUBERRY 1101 | 254151101 | FALSE | 3.1838 | 0.062071 | 3.2458 | 62.5 | 0.00029512 | 8106 | 12.0809 | 756 | 0.003862 | 677
CALPELLA 1101542 | CALPELLA 1101 | 43411101 | FALSE | 33.2958 | 1.3926 | 34.5444 | 617 | 0.00018217 | 10316 | 21.7941 | 524 | 0.0038606 | 678
REDBUD 1101708166 | REDBUD 1101 | 43191101 | FALSE | 11.7176 | 0.55002 | 5.7587 | 209.5 | 0.00022913 | 9511 | 14.0033 | 692 | 0.0038601 | 679
ALTO 1124432 | ALTO 1124 | 42031124 | FALSE | 7.7261 | 4.2072 | 11.8933 | 131 | 0.0009956 | 806 | 4.3241 | 1209 | 0.0038559 | 680
WEST POINT 1101L1969 | WEST POINT 1101 | 163201101 | FALSE | 1.099 | 0.13602 | 1.235 | 20.5 | 0.00049119 | 5485 | 7.4163 | 968 | 0.0038479 | 681
CLOVERDALE 1101964556 | CLOVERDALE 1101 | 42821101 | FALSE | 5.2094 | 0.33621 | 5.4334 | 106 | 0.00016799 | 10506 | 25.522 | 445 | 0.0038441 | 682
SILVERADO 2102808 | SILVERADO 2102 | 43432102 | FALSE | 5.5586 | 0.19435 | 2.8409 | 103 | 0.00023865 | 9312 | 19.551 | 562 | 0.003821 | 683
FROGTOWN 170232556 | FROGTOWN 1702 | 163451702 | TRUE | 1.304 | 0.70933 | 0.045028 | 19.1667 | 0.0005501 | 4860 | 8.062 | 933 | 0.0037926 | 684
OAKHURST 1102333062 | OAKHURST 1102 | 254421102 | TRUE | 0.32941 | 0.087556 | 0.16858 | 5.8333 | 0.00092589 | 1117 | 4.208 | 1226 | 0.00379 | 685
COVELO 1101664688 | COVELO 1101 | 43061101 |  | 0.83891 | 0.11232 |  | 15.5 | 0.00016731 | 10513 | 15.2954 | 652 | 0.0037869 | 686
JESSUP 11012839 | JESSUP 1101 | 103441101 | FALSE | 1.4938 | 0.55331 | 2.0471 | 28.5 | 0.00054533 | 4905 | 6.8383 | 1008 | 0.0037758 | 687
BRUNSWICK 1103173934 | BRUNSWICK 1103 | 152481103 | FALSE | 10.9398 | 0.57827 | 11.5181 | 195.5 | 0.00039111 | 6556 | 9.4108 | 863 | 0.0037716 | 688
LOS GATOS 1106LA42 | LOS GATOS 1106 | 82021106 | FALSE | 2.743 | 1.8743 | 4.6173 | 44.5 | 0.0015233 | 102 | 2.4906 | 1511 | 0.0037657 | 689
NARROWS 210248484 | NARROWS 2102 | 153132102 | FALSE | 41.8422 | 2.8083 | 44.6504 | 777.5 | 0.00023787 | 9325 | 19.6723 | 559 | 0.00376 | 690
HIGHLANDS 1103520 | HIGHLANDS 1103 | 43361103 | FALSE | 43.6096 | 4.3736 | 47.9831 | 800.5 | 0.00017266 | 10449 | 25.2433 | 449 | 0.0037595 | 691
AUBERRY 1101R2845 | AUBERRY 1101 | 254151101 | FALSE | 17.6672 | 1.1297 | 18.7968 | 335.5 | 0.00018753 | 10239 | 19.3562 | 569 | 0.0037567 | 692
WILDWOOD 110185112 | WILDWOOD 1101 | 103611101 | FALSE | 6.793 | 0.51039 | 7.3034 | 122.5 | 0.00028377 | 8334 | 13.4131 | 715 | 0.0037515 | 693
CORNING 110253184 | CORNING 1102 | 103331102 | FALSE | 31.8906 | 0.80743 | 32.6979 | 628.5 | 0.0001377 | 10815 | 24.1875 | 468 | 0.0037456 | 694
CLAYTON 2212334476 | CLAYTON 2212 | 12022212 | TRUE | 0.06003 | 0 | 0.031767 | 1.5 | 0.00062262 | 4019 | 6.0153 | 1073 | 0.0037453 | 695
CLARK ROAD 11022582 | CLARK ROAD 1102 | 103091102 | FALSE | 20.8663 | 0.85225 | 18.7444 | 383.5 | 0.00017047 | 10479 | 25.5933 | 442 | 0.0037445 | 696
LOS GATOS 1106LA46 | LOS GATOS 1106 | 82021106 | FALSE | 1.4934 | 1.2374 | 2.7308 | 22.5 | 0.0017516 | 46 | 2.1134 | 1601 | 0.0037111 | 697
HIGHLANDS 1102CB | HIGHLANDS 1102 | 43361102 | FALSE | 7.4912 | 2.8101 | 10.3012 | 100.5833 | 0.00045533 | 5865 | 9.5266 | 858 | 0.0037075 | 698
CLOVERDALE 110184088 | CLOVERDALE 1101 | 42821101 | FALSE | 17.4858 | 1.1104 | 16.5145 | 333 | 0.00020278 | 9999 | 21.5618 | 528 | 0.0037006 | 699
SARATOGA 1106340986 | SARATOGA 1106 | 83371106 | FALSE | 8.2903 | 3.6117 | 10.3313 | 151.5 | 0.00059034 | 4411 | 6.6154 | 1025 | 0.0036751 | 700
OAKHURST 1103CB | OAKHURST 1103 | 254421103 | FALSE | 33.4604 | 3.0269 | 34.5648 | 583.3333 | 0.00051478 | 5238 | 7.9345 | 940 | 0.0036673 | 701
SALT SPRINGS 21011216 | SALT SPRINGS 2101 | 163692101 | FALSE | 5.4808 | 0.45128 | 5.9321 | 113.5 | 0.00023284 | 9428 | 16.0831 | 637 | 0.0036668 | 702
ATASCADERO 1103492068 | ATASCADERO 1103 | 182541103 | FALSE | 5.6643 | 0.3239 | 5.9882 | 110.5 | 0.00018019 | 10350 | 26.2429 | 431 | 0.0036645 | 703
VOLTA 11011516 | VOLTA 1101 | 102541101 | FALSE | 25.8308 | 0.99893 | 25.3122 | 472.5 | 0.00022442 | 9618 | 15.1767 | 658 | 0.0036607 | 704
LOS GATOS 1106LA64 | LOS GATOS 1106 | 82021106 | FALSE | 12.6486 | 3.055 | 15.7036 | 238 | 0.0011616 | 357 | 3.0162 | 1393 | 0.0036462 | 705
BIG BASIN 1101391980 | BIG BASIN 1101 | 82841101 | FALSE | 5.0526 | 0.30318 | 5.3557 | 101 | 0.0011938 | 307 | 3.0463 | 1386 | 0.003642 | 706
ALTO 11243745 | ALTO 1124 | 42031124 | FALSE | 4.4768 | 1.2003 | 5.6771 | 76.5 | 0.00081126 | 1888 | 7.7202 | 952 | 0.003638 | 707
BRUNSWICK 110532536 | BRUNSWICK 1105 | 152481105 | FALSE | 10.9898 | 1.2513 | 12.241 | 202.5 | 0.0004116 | 6318 | 9.4773 | 859 | 0.0036367 | 708
MENLO 11028952 | MENLO 1102 | 24131102 | FALSE | 3.3532 | 1.5488 | 4.902 | 63.5 | 0.00048267 | 5571 | 7.4328 | 967 | 0.0036339 | 709
DIAMOND SPRINGS 1106176130 | DIAMOND SPRINGS 1106 | 152261106 | TRUE | 0.019568 | 0 | 0.019568 | 1 | 0.00065062 | 3701 | 5.5796 | 1099 | 0.0036302 | 710
CLARK ROAD 11022070 | CLARK ROAD 1102 | 103091102 | TRUE | 0.17109 | 0 | 0.17109 | 1 | 0.00098107 | 866 | 3.6916 | 1285 | 0.0036217 | 711
PUTAH CREEK 11028352 | PUTAH CREEK 1102 | 63681102 | FALSE | 11.8345 | 0.49332 | 5.6317 | 214 | 0.00019266 | 10170 | 17.9154 | 601 | 0.0036194 | 712
MIWUK 17029270 | MIWUK 1702 | 163661702 | FALSE | 5.7379 | 0.442 | 6.1799 | 97.8333 | 0.00034559 | 7213 | 13.4376 | 714 | 0.0036131 | 713
MARIPOSA 21029590 | MARIPOSA 2102 | 254452102 | FALSE | 36.0398 | 1.5951 | 37.6348 | 666 | 0.00022947 | 9500 | 13.984 | 694 | 0.0036118 | 714
HIGGINS 110332120 | HIGGINS 1103 | 152691103 | FALSE | 39.9809 | 4.2947 | 43.6323 | 711.5 | 0.00036288 | 6946 | 8.4283 | 912 | 0.0036041 | 715
HOPLAND 110194006 | HOPLAND 1101 | 42251101 | FALSE | 15.4375 | 0.38379 | 12.7766 | 293 | 0.00015055 | 10700 | 27.8257 | 404 | 0.0036028 | 716
LAURELES 1111432 | LAURELES 1111 | 182371111 | FALSE | 48.9584 | 2.4268 | 51.385 | 935 | 0.00015047 | 10703 | 24.9528 | 452 | 0.0036006 | 717
BRUNSWICK 11052140 | BRUNSWICK 1105 | 152481105 | FALSE | 34.2806 | 2.72 | 37.0005 | 637 | 0.00033925 | 7322 | 11.4659 | 783 | 0.0035885 | 718
NARROWS 21022220 | NARROWS 2102 | 153132102 | FALSE | 28.4253 | 1.1955 | 28.3083 | 520.5 | 0.00024016 | 9287 | 17.4609 | 613 | 0.003575 | 719
CLOVERDALE 1102172096 | CLOVERDALE 1102 | 42821102 | TRUE | 0.75699 | 0.13497 | 0.081132 | 11.3333 | 0.00038366 | 6658 | 8.7763 | 895 | 0.0035694 | 720
SHINGLE SPRINGS 210913322 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 40.9124 | 3.2224 | 44.1347 | 745 | 0.00017648 | 10400 | 20.1238 | 555 | 0.0035675 | 721
SARATOGA 1105431214 | SARATOGA 1105 | 83371105 | TRUE | 0.50395 | 0.12086 | 0.32009 | 11.5 | 0.0005784 | 4545 | 5.7448 | 1090 | 0.0035649 | 722
MENLO 1102331044 | MENLO 1102 | 24131102 |  | 0.48562 | 0.1573 |  | 13.5 | 0.0004397 | 6015 | 7.2942 | 975 | 0.0035618 | 723
STELLING 1110568350 | STELLING 1110 | 83481110 | FALSE | 11.5215 | 0.61711 | 9.1341 | 221.8333 | 0.00048994 | 5495 | 8.8278 | 892 | 0.0035515 | 724
MARIPOSA 210197142 | MARIPOSA 2101 | 254452101 | FALSE | 4.7411 | 0.13893 | 4.88 | 70 | 0.00026177 | 8840 | 12.6281 | 736 | 0.0035474 | 725
RESEARCH 2102183888 | RESEARCH 2102 | 14692102 | FALSE | 2.9991 | 1.1979 | 1.175 | 53.3333 | 0.00089913 | 1238 | 4.8003 | 1160 | 0.0035426 | 726
MENDOCINO 110148750 | MENDOCINO 1101 | 42951101 | FALSE | 18.122 | 0.65684 | 16.9002 | 342.5 | 0.00019459 | 10137 | 18.0908 | 596 | 0.003533 | 727
JAMESON 1105466348 | JAMESON 1105 | 63801105 | FALSE | 30.2294 | 3.0465 | 14.4976 | 569.5 | 0.00026184 | 8839 | 20.3544 | 551 | 0.0035256 | 728
STELLING 111060094 | STELLING 1110 | 83481110 | FALSE | 9.5997 | 0.69817 | 10.2978 | 197 | 0.00089647 | 1256 | 3.8643 | 1264 | 0.0035236 | 729
SILVERADO 2103617828 | SILVERADO 2103 | 43432103 | FALSE | 2.5299 | 0.28624 | 0.86482 | 56.5 | 0.00036195 | 6960 | 18.0384 | 598 | 0.0035223 | 730
DIAMOND SPRINGS 1106279670 | DIAMOND SPRINGS 1106 | 152261106 | FALSE | 4.9272 | 0.3554 | 4.0083 | 80 | 0.00031073 | 7791 | 13.701 | 701 | 0.0035109 | 731
DUNBAR 1103416 | DUNBAR 1103 | 43071103 | TRUE | 2.7616 | 0.07094 | 0.11414 | 49 | 0.00050044 | 5386 | 8.4655 | 910 | 0.0035071 | 732
CLAYTON 2215812394 | CLAYTON 2215 | 12022215 | FALSE | 2.0742 | 0.14606 | 2.2203 | 36.5 | 0.0003011 | 7993 | 10.2281 | 825 | 0.0035044 | 733
AUBERRY 110149122 | AUBERRY 1101 | 254151101 | FALSE | 11.3875 | 0.30873 | 4.3768 | 222.5 | 0.00011324 | 10994 | 40.0297 | 249 | 0.0034999 | 734
KONOCTI 1102965078 | KONOCTI 1102 | 43311102 | FALSE | 7.2213 | 0.077144 | 5.8367 | 134 | 0.00030155 | 7977 | 9.899 | 838 | 0.0034918 | 735
VINEYARD 2108MR172 | VINEYARD 2108 | 14502108 | TRUE | 1.4726 | 0.25548 | 0.3328 | 41.5 | 0.00049788 | 5414 | 8.6415 | 903 | 0.0034897 | 736
CAMP EVERS 210660124 | CAMP EVERS 2106 | 83622106 | FALSE | 25.0618 | 4.4334 | 26.637 | 448 | 0.00086644 | 1448 | 4.1148 | 1241 | 0.0034764 | 737
ATASCADERO 1103440856 | ATASCADERO 1103 | 182541103 | FALSE | 35.176 | 2.0475 | 36.609 | 661 | 0.00014492 | 10749 | 22.8155 | 499 | 0.0034579 | 738
RESEARCH 2102644462 | RESEARCH 2102 | 14692102 | TRUE | 1.5815 | 0.8765 | 0.51629 | 31.5 | 0.00067913 | 3335 | 6.1726 | 1056 | 0.0034397 | 739
PIT NO 5 11011606 | PIT NO 5 1101 | 101321101 | FALSE | 5.3571 | 0.46644 | 5.8235 | 106 | 0.00024353 | 9212 | 14.7236 | 672 | 0.0034383 | 740
COALINGA NO 2 110541954 | COALINGA NO 2 1105 | 252381105 |  | 38.715 | 0.68716 |  | 683.5 | 0.00018429 | 10285 | 34.7731 | 312 | 0.003428 | 741
PASO ROBLES 1103N50 | PASO ROBLES 1103 | 182611103 | FALSE | 1.8588 | 0 | 1.8588 | 39.5 | 0.00012894 | 10890 | 25.9289 | 437 | 0.0034276 | 742
SAN LUIS OBISPO 1104982992 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 8.483 | 0.14927 | 8.6322 | 164.5 | 0.00014104 | 10777 | 24.5409 | 459 | 0.0034215 | 743
NARROWS 21052748 | NARROWS 2105 | 153132105 | FALSE | 19.8731 | 1.336 | 14.0837 | 368.5 | 0.00044327 | 5982 | 13.311 | 719 | 0.0034191 | 744
COARSEGOLD 210210040 | COARSEGOLD 2102 | 254432102 | FALSE | 20.5246 | 1.4278 | 18.5122 | 378.4167 | 0.00028736 | 8246 | 13.4838 | 711 | 0.0034115 | 745
AUBERRY 1101R2579 | AUBERRY 1101 | 254151101 | FALSE | 34.2672 | 1.2945 | 35.5616 | 641 | 9.3619e-05 | 11071 | 36.3944 | 288 | 0.00341 | 746
CLEAR LAKE 11011302 | CLEAR LAKE 1101 | 42141101 | FALSE | 17.6725 | 3.0637 | 8.2792 | 324.5 | 0.00033104 | 7436 | 10.7067 | 811 | 0.0034084 | 747
SUNOL 1101MR387 | SUNOL 1101 | 14241101 | FALSE | 5.045 | 0 | 4.8983 | 96.5 | 0.00033717 | 7345 | 10.2175 | 827 | 0.0034076 | 748
MC KEE 1107827486 | MC KEE 1107 | 83531107 | FALSE | 2.9996 | 0.31448 | 2.9844 | 56.5 | 0.0002692 | 8672 | 12.4008 | 745 | 0.0033891 | 749
MORGAN HILL 2111419718 | MORGAN HILL 2111 | 83242111 | FALSE | 2.0969 | 0.53427 | 2.6312 | 45 | 0.00031302 | 7753 | 12.0141 | 758 | 0.0033825 | 750
GUSTINE 1102999258 | GUSTINE 1102 | 163111102 |  | 7.1956 | 0.025101 |  | 148.5 | 0.000107 | 11026 | 34.6936 | 314 | 0.0033754 | 751
BRUNSWICK 11032200 | BRUNSWICK 1103 | 152481103 | FALSE | 5.5818 | 0.87292 | 6.4547 | 108.5 | 0.00053761 | 4984 | 6.5605 | 1029 | 0.0033744 | 752
MORGAN HILL 2111XR292 | MORGAN HILL 2111 | 83242111 | FALSE | 12.0337 | 1.1525 | 11.6265 | 223 | 0.00029005 | 8198 | 13.0962 | 724 | 0.0033644 | 753
KONOCTI 11084037 | KONOCTI 1108 | 43311108 | FALSE | 1.7277 | 0.96729 | 1.4678 | 30.5 | 0.00031692 | 7680 | 12.1995 | 751 | 0.0033534 | 754
PARADISE 11052214 | PARADISE 1105 | 102831105 | FALSE | 17.4143 | 2.998 | 16.3703 | 299.5 | 0.00049636 | 5431 | 10.0334 | 831 | 0.0033502 | 755
NARROWS 21022728 | NARROWS 2102 | 153132102 | FALSE | 19.3646 | 0.76229 | 17.9729 | 373.5 | 0.00026693 | 8721 | 18.1529 | 591 | 0.0033476 | 756
MIRABEL 110257840 | MIRABEL 1102 | 42091102 | FALSE | 4.6775 | 1.2069 | 3.4934 | 78.5 | 0.0011404 | 387 | 2.9256 | 1407 | 0.003334 | 757
BEAR VALLEY 2105916436 | BEAR VALLEY 2105 | 252192105 | FALSE | 17.1506 | 0.38368 | 17.5343 | 306 | 0.00011972 | 10951 | 22.1138 | 518 | 0.0033051 | 758
UKIAH 1113CB | UKIAH 1113 | 42771113 | TRUE | 6.627 | 2.1077 | 0.019618 | 98.25 | 0.00057024 | 4656 | 6.9096 | 1000 | 0.0033027 | 759
OAKHURST 1102455174 | OAKHURST 1102 | 254421102 | FALSE | 2.3577 | 0.31342 | 2.6711 | 48 | 0.00025682 | 8946 | 13.656 | 704 | 0.0032946 | 760
MIWUK 1701360164 | MIWUK 1701 | 163661701 | FALSE | 6.9025 | 0.55964 | 7.4621 | 119 | 0.00041471 | 6288 | 13.677 | 703 | 0.0032906 | 761
DOBBINS 110183186 | DOBBINS 1101 | 153741101 | FALSE | 7.3225 | 0.048583 | 7.3711 | 134.5 | 0.00015382 | 10659 | 20.766 | 540 | 0.0032737 | 762
HOPLAND 1101960 | HOPLAND 1101 | 42251101 | FALSE | 13.6393 | 0.26473 | 9.642 | 264.3333 | 0.00017813 | 10376 | 28.0235 | 401 | 0.0032637 | 763
VASCO 1102546328 | VASCO 1102 | 13751102 | FALSE | 42.1012 | 1.3392 | 39.3623 | 817.5 | 0.00010694 | 11027 | 48.7115 | 174 | 0.0032627 | 764
WILLITS 1103538 | WILLITS 1103 | 42661103 | FALSE | 6.3232 | 0.15264 | 6.4758 | 123.5 | 0.00021423 | 9794 | 14.9617 | 665 | 0.0032591 | 765
CURTIS 17046060 | CURTIS 1704 | 163351704 | FALSE | 4.0007 | 0.59655 | 4.5973 | 74.8333 | 0.00042558 | 6169 | 10.9209 | 804 | 0.0032585 | 766
EL DORADO PH 2102771208 | EL DORADO PH 2102 | 152762102 | FALSE | 4.2927 | 0.44646 | 4.7392 | 72 | 0.00092165 | 1141 | 3.3588 | 1335 | 0.0032559 | 767
VACAVILLE 11088762 | VACAVILLE 1108 | 63601108 | FALSE | 20.8491 | 1.3186 | 14.8285 | 385.5 | 0.00022564 | 9591 | 23.3055 | 488 | 0.0032459 | 768
CALISTOGA 1102634 | CALISTOGA 1102 | 42711102 | FALSE | 11.967 | 1.2754 | 6.1973 | 220 | 0.0005743 | 4597 | 4.3785 | 1200 | 0.0032407 | 769
TEMPLETON 2110941946 | TEMPLETON 2110 | 183052110 | FALSE | 31.8098 | 0.44872 | 27.5522 | 617 | 0.0001291 | 10889 | 27.7124 | 408 | 0.0032361 | 770
PASO ROBLES 1103N58 | PASO ROBLES 1103 | 182611103 | FALSE | 10.2436 | 1.463 | 4.6206 | 175 | 0.00017321 | 10445 | 22.4928 | 506 | 0.0032279 | 771
WOODSIDE 11043583 | WOODSIDE 1104 | 24251104 | FALSE | 2.7983 | 1.0555 | 3.8538 | 56 | 0.0010089 | 765 | 3.1289 | 1368 | 0.0032277 | 772
KONOCTI 11024300 | KONOCTI 1102 | 43311102 | FALSE | 27.133 | 2.5461 | 28.1318 | 502 | 0.0003515 | 7117 | 7.9251 | 941 | 0.0032153 | 773
WOODSIDE 11018884 | WOODSIDE 1101 | 24251101 | FALSE | 7.4686 | 0.1927 | 7.6612 | 135 | 0.0013472 | 164 | 2.708 | 1455 | 0.0032144 | 774
DIAMOND SPRINGS 11052102 | DIAMOND SPRINGS 1105 | 152261105 | FALSE | 38.8553 | 3.4628 | 39.6935 | 708.5 | 0.00029376 | 8136 | 17.2297 | 617 | 0.0032085 | 775
SARATOGA 1107413816 | SARATOGA 1107 | 83371107 | FALSE | 1.6265 | 0.10621 | 1.7327 | 33.5 | 0.00080307 | 1950 | 3.6363 | 1292 | 0.0032079 | 776
OLETA 11022642 | OLETA 1102 | 163541102 | FALSE | 4.6558 | 0.10072 | 4.7565 | 81 | 0.0001918 | 10182 | 16.8157 | 626 | 0.0032048 | 777
CAMP EVERS 21055232 | CAMP EVERS 2105 | 83622105 | FALSE | 4.4967 | 1.8779 | 6.3745 | 75 | 0.0017069 | 53 | 1.852 | 1684 | 0.0032043 | 778
RINCON 1101146053 | RINCON 1101 | 43321101 | FALSE | 18.3449 | 1.3665 | 17.6692 | 342.5 | 0.00027208 | 8605 | 14.0038 | 691 | 0.0031989 | 779
EL DORADO PH 21026645 | EL DORADO PH 2102 | 152762102 | FALSE | 4.0873 | 0.73059 | 4.8179 | 75 | 0.00056524 | 4705 | 6.1462 | 1060 | 0.0031904 | 780
LAURELES 111110141 | LAURELES 1111 | 182371111 | FALSE | 2.8669 | 0.79536 | 3.6622 | 58 | 0.00028298 | 8355 | 9.913 | 837 | 0.0031883 | 781
SISQUOC 1103858898 | SISQUOC 1103 | 182811103 | FALSE | 19.5963 | 0.89697 | 20.1701 | 377.5 | 0.00014606 | 10739 | 22.6126 | 502 | 0.003179 | 782
MORGAN HILL 2105345099 | MORGAN HILL 2105 | 83242105 | TRUE | 0.30842 | 0.34344 | 0.22958 | 5.5 | 0.00061797 | 4071 | 5.1439 | 1128 | 0.0031788 | 783
BRUNSWICK 1104761310 | BRUNSWICK 1104 | 152481104 | TRUE | 0.039035 | 0 | 0.039035 | 0.5 | 0.00027379 | 8558 | 11.6068 | 778 | 0.0031778 | 784
GANSNER 11012424 | GANSNER 1101 | 103021101 | FALSE | 18.6545 | 1.8954 | 20.3582 | 356.5 | 0.00024971 | 9089 | 13.1255 | 722 | 0.0031715 | 785
CHALLENGE 11021064 | CHALLENGE 1102 | 103201102 | FALSE | 19.5837 | 0.88006 | 20.4637 | 356.5 | 0.0003719 | 6809 | 9.8068 | 843 | 0.0031641 | 786
COARSEGOLD 210210330 | COARSEGOLD 2102 | 254432102 | FALSE | 9.7643 | 0.10301 | 9.8673 | 179.25 | 0.00043166 | 6099 | 8.4413 | 911 | 0.0031628 | 787
MORAGA 1101CB | MORAGA 1101 | 13801101 | FALSE | 9.6612 | 4.9462 | 9.9549 | 144.25 | 0.00071845 | 2870 | 4.7185 | 1166 | 0.0031586 | 788
CAMP EVERS 210574170 | CAMP EVERS 2105 | 83622105 | FALSE | 3.5962 | 2.2459 | 5.8421 | 56.5 | 0.0020915 | 27 | 1.5002 | 1845 | 0.0031521 | 789
DIAMOND SPRINGS 110518935 | DIAMOND SPRINGS 1105 | 152261105 | FALSE | 6.4696 | 0.32706 | 6.7966 | 120 | 0.00022106 | 9684 | 15.8783 | 641 | 0.0031474 | 790
SAND CREEK 11037070 | SAND CREEK 1103 | 254601103 | FALSE | 17.0866 | 0.74152 | 17.828 | 328 | 0.00015434 | 10653 | 21.7775 | 525 | 0.003145 | 791
BEN LOMOND 04015400 | BEN LOMOND 0401 | 83040401 | TRUE | 0.45402 | 0.089816 | 0.54383 | 3.8333 | 0.0020773 | 28 | 1.5131 | 1836 | 0.0031431 | 792
SILVERADO 21051308 | SILVERADO 2105 | 43432105 | TRUE | 5.0202 | 2.8699 | 0.20255 | 87.5 | 0.00082727 | 1758 | 5.2695 | 1120 | 0.0031429 | 793
OTTER 11022166 | OTTER 1102 | 182941102 | FALSE | 4.0307 | 0.47098 | 4.5017 | 73.5 | 0.00069938 | 3107 | 5.0886 | 1131 | 0.003141 | 794
KONOCTI 1102716 | KONOCTI 1102 | 43311102 | FALSE | 17.1034 | 0.14192 | 13.1431 | 316 | 0.00022315 | 9640 | 12.4245 | 743 | 0.0031317 | 795
JESSUP 110168362 | JESSUP 1101 | 103441101 | FALSE | 7.3033 | 1.0626 | 5.7667 | 126.3333 | 0.0005046 | 5339 | 6.6755 | 1020 | 0.0031244 | 796
CAMP EVERS 21065020 | CAMP EVERS 2106 | 83622106 | FALSE | 11.9072 | 1.8675 | 13.7747 | 208 | 0.0011564 | 364 | 2.6987 | 1458 | 0.0031225 | 797
WILLITS 110337506 | WILLITS 1103 | 42661103 | FALSE | 11.2077 | 0.494 | 11.7016 | 231.5 | 0.00034581 | 7208 | 8.2483 | 924 | 0.0031126 | 798
SAN RAFAEL 11071166 | SAN RAFAEL 1107 | 42011107 | FALSE | 15.0348 | 8.9528 | 19.1432 | 279 | 0.00097886 | 877 | 2.9282 | 1405 | 0.0031024 | 799
CURTIS 1702CB | CURTIS 1702 | 163351702 | FALSE | 22.7742 | 2.9437 | 24.477 | 418.7 | 0.00037804 | 6727 | 10.1124 | 828 | 0.0031009 | 800
ELK CREEK 11012008 | ELK CREEK 1101 | 102781101 | FALSE | 18.0722 | 0.93819 | 4.1188 | 327 | 0.00016752 | 10512 | 23.6891 | 480 | 0.0030963 | 801
SAN ARDO 11027030 | SAN ARDO 1102 | 182191102 |  | 23.6422 | 0.52151 |  | 495.5 | 9.6034e-05 | 11063 | 39.9213 | 253 | 0.0030947 | 802
MENLO 11031721 | MENLO 1103 | 24131103 | FALSE | 7.0953 | 0.083564 | 7.1788 | 138.5 | 0.00057512 | 4589 | 5.4024 | 1111 | 0.0030912 | 803
TEMPLETON 2111R86 | TEMPLETON 2111 | 183052111 | FALSE | 14.3097 | 0.62906 | 10.8987 | 263 | 0.00015446 | 10652 | 22.5968 | 503 | 0.0030906 | 804
SILVERADO 2104806 | SILVERADO 2104 | 43432104 | FALSE | 34.066 | 0.93352 | 18.6999 | 690 | 0.00025592 | 8963 | 11.0034 | 800 | 0.00309 | 805
CORNING 110185162 | CORNING 1101 | 103331101 | FALSE | 5.7586 | 0.028163 | 5.7867 | 101 | 0.00017329 | 10441 | 17.4769 | 612 | 0.0030856 | 806
SARATOGA 1103LC16 | SARATOGA 1103 | 83371103 | FALSE | 5.1324 | 3.1917 | 6.7644 | 95 | 0.00054626 | 4896 | 6.1156 | 1061 | 0.0030824 | 807
SOLEDAD 2102858388 | SOLEDAD 2102 | 182052102 | FALSE | 8.2144 | 0.9187 | 4.9401 | 170.5 | 0.00026626 | 8740 | 17.5735 | 608 | 0.0030795 | 808
PARADISE 110636042 | PARADISE 1106 | 102831106 | FALSE | 8.0118 | 2.134 | 9.6078 | 142 | 0.00058411 | 4483 | 5.766 | 1088 | 0.0030677 | 809
POINT MORETTI 110110722 | POINT MORETTI 1101 | 82931101 | FALSE | 0.58281 | 0.14487 | 0.72768 | 10.8333 | 0.0012852 | 219 | 2.4269 | 1528 | 0.0030639 | 810
TEMPLETON 2110N32 | TEMPLETON 2110 | 183052110 | FALSE | 28.5956 | 2.5473 | 30.8468 | 544.5 | 0.00010751 | 11022 | 28.8611 | 388 | 0.0030638 | 811
DIAMOND SPRINGS 110699658 | DIAMOND SPRINGS 1106 | 152261106 |  | 7.1074 | 2.0126 |  | 123 | 0.00042411 | 6183 | 9.3371 | 866 | 0.0030483 | 812
SOLEDAD 2101107872 | SOLEDAD 2101 | 182052101 | FALSE | 12.14 | 0.062359 | 11.187 | 189.5 | 0.0001284 | 10897 | 33.8016 | 322 | 0.0030371 | 813
BUTTE 1105134600 | BUTTE 1105 | 103081105 | TRUE | 0.34934 | 0 | 0.34934 | 7.5 | 0.00045434 | 5880 | 6.6689 | 1021 | 0.0030299 | 814
ELECTRA 1101175840 | ELECTRA 1101 | 162161101 | FALSE | 8.4314 | 0.41683 | 8.8482 | 161 | 0.00019791 | 10077 | 19.4557 | 567 | 0.0030293 | 815
NAPA 1112850068 | NAPA 1112 | 42021112 | FALSE | 11.2426 | 0.72641 | 9.8305 | 212 | 0.00023031 | 9480 | 15.9983 | 639 | 0.0030024 | 816
LOS GATOS 110660116 | LOS GATOS 1106 | 82021106 | FALSE | 12.1344 | 2.3002 | 14.4345 | 207 | 0.0011131 | 448 | 2.7872 | 1440 | 0.0029921 | 817
HIGGINS 111051794 | HIGGINS 1110 | 152691110 | FALSE | 3.9671 | 0.066939 | 4.017 | 71.8333 | 0.00050937 | 5292 | 6.6636 | 1023 | 0.0029881 | 818
LAYTONVILLE 110237586 | LAYTONVILLE 1102 | 42681102 | FALSE | 13.895 | 0.21997 | 14.1149 | 279 | 0.00023687 | 9342 | 11.7054 | 771 | 0.0029855 | 819
SALT SPRINGS 210237300 | SALT SPRINGS 2102 | 163692102 | FALSE | 6.9165 | 0.2629 | 7.1794 | 137.8333 | 0.00042858 | 6137 | 8.1324 | 929 | 0.0029843 | 820
SCE TEJON TIE 1101CB | SCE TEJON TIE 1101 | 258191101 | TRUE | 0.01394 | 0 | 0.01394 | 0.5 | 0.00042435 | 6180 | 7.032 | 996 | 0.002984 | 821
AUBERRY 1101323028 | AUBERRY 1101 | 254151101 | FALSE | 4.9842 | 0.016063 | 5.0003 | 92 | 0.00032547 | 7532 | 9.1272 | 878 | 0.0029837 | 822
REDBUD 1102922 | REDBUD 1102 | 43191102 | FALSE | 7.7169 | 2.3915 | 9.8892 | 133 | 0.0003522 | 7103 | 11.6562 | 772 | 0.0029796 | 823
SAN JOAQUIN #2 1103CB | SAN JOAQUIN #2 1103 | 252521103 | FALSE | 67.8276 | 3.3143 | 71.1417 | 1290.5 | 0.00019919 | 10057 | 21.1305 | 535 | 0.0029695 | 824
SARATOGA 1107167792 | SARATOGA 1107 | 83371107 | FALSE | 4.7512 | 0 | 4.7512 | 91.5 | 0.00082058 | 1813 | 3.4714 | 1320 | 0.0029655 | 825
DUNBAR 1102CB | DUNBAR 1102 | 43071102 | FALSE | 8.5745 | 3.2428 | 10.4971 | 152.6667 | 0.00070898 | 2993 | 4.3325 | 1208 | 0.0029637 | 826
LAURELES 11112028 | LAURELES 1111 | 182371111 | FALSE | 8.7081 | 4.3689 | 13.0509 | 161.5 | 0.0004073 | 6367 | 7.3355 | 971 | 0.0029637 | 827
HARTLEY 110194178 | HARTLEY 1101 | 43211101 | FALSE | 4.1213 | 1.0706 | 2.3438 | 69.8333 | 0.00041534 | 6277 | 7.1362 | 991 | 0.0029586 | 828
ALLEGHANY 11011101/2 | ALLEGHANY 1101 | 152101101 | TRUE | 0.038172 | 0 | 0.038172 | 1 | 0.0006859 | 3270 | 5.0713 | 1134 | 0.0029581 | 829
ALLEGHANY 11011101/2 | ALLEGHANY 1101 | 152101101 | TRUE | 0.038172 | 0 | 0.038172 | 1 | 0.0006859 | 3270 | 5.0713 | 1134 | 0.0029581 | 829
POINT MORETTI 110139126 | POINT MORETTI 1101 | 82931101 | FALSE | 4.8408 | 0.83798 | 2.7221 | 90 | 0.0013114 | 195 | 2.2562 | 1565 | 0.002954 | 830
RACETRACK 17032553 | RACETRACK 1703 | 163761703 | FALSE | 2.4935 | 0.57357 | 1.0373 | 41 | 0.00044323 | 5983 | 8.0826 | 931 | 0.0029419 | 831
DUNBAR 1103596218 | DUNBAR 1103 | 43071103 | TRUE | 0.23697 | 0 | 0.23697 | 3.5 | 0.00073662 | 2660 | 3.9821 | 1256 | 0.0029332 | 832
LOW GAP 11014086 | LOW GAP 1101 | 192411101 | FALSE | 11.5881 | 0.24278 | 11.8309 | 215.5 | 0.00022571 | 9590 | 14.0282 | 690 | 0.0029316 | 833
DOBBINS 11015202 | DOBBINS 1101 | 153741101 | FALSE | 17.2464 | 0.46025 | 16.5248 | 338.5 | 0.00018104 | 10339 | 19.6385 | 560 | 0.00293 | 834
SPRING GAP 1702CB | SPRING GAP 1702 | 162831702 | FALSE | 7.3322 | 0.19585 | 7.5281 | 150.8333 | 0.00019723 | 10084 | 15.3974 | 650 | 0.0029297 | 835
MIDDLETOWN 11021312 | MIDDLETOWN 1102 | 43141102 | FALSE | 9.7943 | 4.1171 | 13.9114 | 154.5 | 0.00032956 | 7458 | 13.3919 | 716 | 0.0029252 | 836
LOS GATOS 1102526868 | LOS GATOS 1102 | 82021102 | FALSE | 1.2806 | 1.3003 | 2.2592 | 23.5 | 0.00081823 | 1830 | 3.8168 | 1270 | 0.0029247 | 837
STILLWATER 11011320 | STILLWATER 1101 | 103561101 | FALSE | 19.8461 | 2.2196 | 21.6046 | 379 | 0.00038445 | 6645 | 11.0241 | 798 | 0.002921 | 838
COARSEGOLD 2102383092 | COARSEGOLD 2102 | 254432102 | TRUE | 0.32165 | 0 | 0.32165 | 2.25 | 0.00072011 | 2852 | 4.0547 | 1253 | 0.0029198 | 839
CLARKSVILLE 210413352 | CLARKSVILLE 2104 | 153612104 | FALSE | 35.8073 | 1.5229 | 33.964 | 636 | 0.0002409 | 9271 | 14.5508 | 677 | 0.0029109 | 840
MONTE RIO 1111140 | MONTE RIO 1111 | 42811111 | FALSE | 2.5925 | 1.622 | 4.2145 | 39.5 | 0.0022194 | 19 | 1.3752 | 1947 | 0.002909 | 841
MORGAN HILL 2105XR152 | MORGAN HILL 2105 | 83242105 | FALSE | 12.8017 | 1.9545 | 8.8917 | 243.5 | 0.00031358 | 7746 | 11.0823 | 797 | 0.0029057 | 842
CALISTOGA 1102184814 | CALISTOGA 1102 | 42711102 | FALSE | 2.3461 | 1.643 | 0.88153 | 38 | 0.0010149 | 749 | 3.0514 | 1383 | 0.0029014 | 843
HOLLISTER 21054018 | HOLLISTER 2105 | 182492105 | FALSE | 54.1493 | 1.4256 | 45.8592 | 1072.5 | 8.7379e-05 | 11089 | 35.7372 | 299 | 0.0028966 | 844
ALHAMBRA 1105CB | ALHAMBRA 1105 | 14101105 | FALSE | 1.8918 | 1.06 | 0.86712 | 31.8333 | 0.0007501 | 2479 | 5.1637 | 1126 | 0.0028959 | 845
MONTE RIO 11125040 | MONTE RIO 1112 | 42811112 | FALSE | 5.8129 | 3.7176 | 6.1747 | 110 | 0.00089384 | 1274 | 3.0549 | 1382 | 0.0028916 | 846
HIGHLANDS 1103568 | HIGHLANDS 1103 | 43361103 | FALSE | 9.1573 | 2.0626 | 9.3586 | 159 | 0.00032705 | 7503 | 11.0125 | 799 | 0.0028915 | 847
HIGGINS 1104CB | HIGGINS 1104 | 152691104 | FALSE | 11.9008 | 0.38137 | 11.5026 | 215.4167 | 0.000291 | 8178 | 13.1713 | 720 | 0.0028907 | 848
APPLE HILL 110313312 | APPLE HILL 1103 | 153661103 | FALSE | 17.7135 | 1.815 | 13.2844 | 329.1667 | 0.00035233 | 7100 | 10.5085 | 818 | 0.0028729 | 849
CAMP EVERS 2106287578 | CAMP EVERS 2106 | 83622106 | FALSE | 4.3091 | 1.4931 | 5.8022 | 72.3333 | 0.0018986 | 35 | 1.5295 | 1823 | 0.0028689 | 850
KONOCTI 11084039 | KONOCTI 1108 | 43311108 | FALSE | 2.3141 | 1.1042 | 2.5347 | 41 | 0.00037597 | 6751 | 6.6246 | 1024 | 0.0028685 | 851
PIERCY 2110XR258 | PIERCY 2110 | 83912110 | FALSE | 26.322 | 1.0167 | 20.0989 | 532.5 | 0.00018194 | 10318 | 18.5947 | 582 | 0.0028592 | 852
SILVERADO 210437632 | SILVERADO 2104 | 43432104 | FALSE | 7.4045 | 2.036 | 9.4406 | 131.5 | 0.00068934 | 3229 | 4.2207 | 1220 | 0.0028585 | 853
CRESCENT MILLS 21012056 | CRESCENT MILLS 2101 | 103132101 | FALSE | 6.4599 | 1.2613 | 4.3708 | 120 | 0.00034363 | 7246 | 7.2149 | 983 | 0.0028532 | 854
ALTO 1125510 | ALTO 1125 | 42031125 | FALSE | 7.3727 | 3.0369 | 10.4095 | 130.3333 | 0.00055164 | 4851 | 8.0873 | 930 | 0.0028454 | 855
PINE GROVE 11021765 | PINE GROVE 1102 | 163751102 | FALSE | 1.4555 | 0.095873 | 1.5514 | 23.5 | 0.00073338 | 2693 | 3.8461 | 1266 | 0.0028428 | 856
CURTIS 170268380 | CURTIS 1702 | 163351702 | FALSE | 8.453 | 1.8201 | 7.6635 | 138.5 | 0.0005097 | 5288 | 6.9583 | 999 | 0.0028411 | 857
BIG MEADOWS 2101CB | BIG MEADOWS 2101 | 102812101 | FALSE | 2.2107 | 0.55712 | 2.7678 | 22 | 0.00032115 | 7605 | 9.5688 | 855 | 0.0028392 | 858
CALPELLA 1101600 | CALPELLA 1101 | 43411101 | FALSE | 24.4389 | 1.3091 | 19.3991 | 479.5 | 0.00017931 | 10364 | 20.4438 | 549 | 0.0028358 | 859
CURTIS 170463502 | CURTIS 1704 | 163351704 | FALSE | 10.5504 | 1.2777 | 11.828 | 193.5 | 0.00029615 | 8080 | 10.4849 | 819 | 0.0028337 | 860
MOUNTAIN QUARRIES 21012504 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 25.1103 | 1.7044 | 26.8146 | 453 | 0.0003082 | 7838 | 10.7271 | 810 | 0.002833 | 861
WOODACRE 1102CB | WOODACRE 1102 | 43021102 | FALSE | 12.4595 | 5.5612 | 17.8576 | 213 | 0.00084223 | 1635 | 3.3132 | 1340 | 0.0028255 | 862
KONOCTI 1102354890 | KONOCTI 1102 | 43311102 | FALSE | 9.1017 | 1.671 | 7.9776 | 159 | 0.00026903 | 8674 | 14.9629 | 663 | 0.0028063 | 863
OILFIELDS 110387034 | OILFIELDS 1103 | 182391103 | FALSE | 5.8779 | 0.11017 | 5.9881 | 116 | 0.00013465 | 10843 | 24.2639 | 465 | 0.0028046 | 864
SYCAMORE CREEK 1111976428 | SYCAMORE CREEK 1111 | 102971111 | FALSE | 10.5355 | 0.20158 | 8.2609 | 199.5 | 0.00025733 | 8938 | 8.802 | 894 | 0.0027997 | 865
MIWUK 1701953336 | MIWUK 1701 | 163661701 | FALSE | 11.6452 | 2.117 | 13.7611 | 208.5 | 0.00044352 | 5979 | 8.9292 | 887 | 0.0027925 | 866
EL DORADO PH 210152456 | EL DORADO PH 2101 | 152762101 | FALSE | 10.2621 | 2.7457 | 13.0078 | 204 | 0.00051567 | 5222 | 6.0913 | 1064 | 0.0027874 | 867
LOS GATOS 1106LB48 | LOS GATOS 1106 | 82021106 | FALSE | 14.7043 | 0.93362 | 15.6379 | 274.5 | 0.00077172 | 2240 | 3.5608 | 1301 | 0.0027775 | 868
SHADY GLEN 1101898212 | SHADY GLEN 1101 | 152431101 | TRUE | 0.84374 | 0.79543 | 0.42251 | 17 | 0.00061484 | 4109 | 4.6687 | 1168 | 0.0027704 | 869
GEYSERVILLE 110179788 | GEYSERVILLE 1101 | 42891101 | FALSE | 41.6594 | 0.45222 | 38.9646 | 820.5 | 0.00024935 | 9093 | 11.291 | 789 | 0.002764 | 870
WESTLEY 1103237522 | WESTLEY 1103 | 162671103 | TRUE | 16.6587 | 0.010131 | 0.42602 | 325.5 | 8.7092e-05 | 11090 | 30.8435 | 360 | 0.0027636 | 871
MARIPOSA 210110990 | MARIPOSA 2101 | 254452101 | FALSE | 38.8218 | 2.2268 | 41.0486 | 733 | 0.00022356 | 9635 | 15.137 | 659 | 0.0027613 | 872
SILVERADO 2104324994 | SILVERADO 2104 | 43432104 | TRUE | 0.63917 | 0.12973 | 0.27486 | 11.8333 | 0.00065636 | 3619 | 4.3042 | 1210 | 0.0027563 | 873
CALISTOGA 1102100335 | CALISTOGA 1102 | 42711102 | TRUE | 0.01856 | 0 | 0.01856 | 2.5 | 0.0005892 | 4424 | 4.8244 | 1158 | 0.0027549 | 874
PARADISE 110353544 | PARADISE 1103 | 102831103 | TRUE | 1.0485 | 0.58386 | 0.54044 | 22.5 | 0.0005924 | 4387 | 4.1068 | 1243 | 0.0027476 | 875
MERCED FALLS 110287352 | MERCED FALLS 1102 | 252811102 | FALSE | 26.3779 | 0.9156 | 27.2934 | 498.5 | 0.00014471 | 10751 | 30.7139 | 363 | 0.0027423 | 876
FELTON 0401CB | FELTON 0401 | 83140401 | FALSE | 2.5372 | 0.29813 | 2.68 | 27.8333 | 0.0023851 | 16 | 1.1137 | 2283 | 0.00274 | 877
OAKHURST 11035120 | OAKHURST 1103 | 254421103 | FALSE | 6.2338 | 0 | 6.2338 | 116.5 | 0.00047206 | 5677 | 5.7805 | 1087 | 0.0027374 | 878
LAYTONVILLE 1102CB | LAYTONVILLE 1102 | 42681102 | FALSE | 12.9695 | 0.39878 | 10.7259 | 241 | 0.00018669 | 10250 | 17.0007 | 624 | 0.0027248 | 879
KETTLEMAN HILLS 2104358094 | KETTLEMAN HILLS 2104 | 252732104 |  | 5.0441 | 0 |  | 111.5 | 9.9912e-05 | 11050 | 28.4801 | 394 | 0.0027121 | 880
DUNLAP 11037040 | DUNLAP 1103 | 254061103 | FALSE | 25.4411 | 1.3416 | 26.7826 | 468.5 | 0.00014679 | 10732 | 18.5813 | 583 | 0.0027108 | 881
SHINGLE SPRINGS 210981390 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 18.4357 | 1.5202 | 19.9558 | 353 | 0.00032188 | 7592 | 9.1784 | 874 | 0.0027108 | 882
FROGTOWN 1701CB | FROGTOWN 1701 | 163451701 | FALSE | 11.0963 | 0.80608 | 10.1957 | 217.8333 | 0.00033031 | 7444 | 10.318 | 823 | 0.0027017 | 883
LAS POSITAS 2108631066 | LAS POSITAS 2108 | 14402108 | FALSE | 7.1585 | 1.8314 | 8.0878 | 137.5 | 0.00026551 | 8750 | 10.7859 | 809 | 0.0026995 | 884
PLACERVILLE 1111508410 | PLACERVILLE 1111 | 153081111 | FALSE | 5.0967 | 1.8053 | 6.0256 | 83.5 | 0.00064354 | 3781 | 4.4255 | 1196 | 0.0026995 | 885
SHINGLE SPRINGS 210851476 | SHINGLE SPRINGS 2108 | 153652108 | FALSE | 6.5394 | 0.12252 | 4.3735 | 116.3333 | 0.00022213 | 9669 | 12.6542 | 734 | 0.0026967 | 886
SNEATH LANE 11016525 | SNEATH LANE 1101 | 22721101 |  | 0.039114 | 0 |  | 0.66667 | 0.0010607 | 585 | 2.5297 | 1501 | 0.0026834 | 887
CAMP EVERS 210510786 | CAMP EVERS 2105 | 83622105 | FALSE | 4.4699 | 0.50756 | 4.9774 | 83.2 | 0.0022807 | 18 | 1.172 | 2185 | 0.0026817 | 888
CEDAR CREEK 11011656 | CEDAR CREEK 1101 | 103321101 | FALSE | 31.9505 | 1.504 | 33.4545 | 596.5 | 0.00019297 | 10166 | 13.8757 | 696 | 0.0026746 | 889
KANAKA 110165606 | KANAKA 1101 | 103221101 | FALSE | 12.7484 | 1.0372 | 13.7856 | 247.5 | 0.00048391 | 5558 | 5.5407 | 1102 | 0.0026725 | 890
MENLO 1103866118 | MENLO 1103 | 24131103 | FALSE | 13.7345 | 0.53947 | 11.6681 | 251.5 | 0.00040059 | 6449 | 5.7972 | 1085 | 0.0026693 | 891
CRESCENT MILLS 2101CB | CRESCENT MILLS 2101 | 103132101 | FALSE | 6.7994 | 1.2153 | 3.4635 | 110 | 0.00029926 | 8031 | 11.1678 | 795 | 0.0026577 | 892
SARATOGA 11075696 | SARATOGA 1107 | 83371107 | FALSE | 6.2446 | 2.7525 | 7.092 | 130.5 | 0.00061056 | 4161 | 4.2188 | 1221 | 0.0026577 | 893
CASTRO VALLEY 111010315 | CASTRO VALLEY 1110 | 14091110 | FALSE | 5.403 | 0.11818 | 5.5211 | 108.5 | 0.00035405 | 7073 | 7.2478 | 979 | 0.0026569 | 894
WOODSIDE 110147872 | WOODSIDE 1101 | 24251101 | FALSE | 4.7418 | 0.73942 | 4.775 | 86.5 | 0.0018209 | 41 | 1.456 | 1882 | 0.0026503 | 895
CAMP EVERS 2106478670 | CAMP EVERS 2106 | 83622106 | FALSE | 2.8069 | 0.25912 | 1.3435 | 53 | 0.0012873 | 217 | 2.0529 | 1619 | 0.0026495 | 896
BIG BASIN 110212758 | BIG BASIN 1102 | 82841102 | FALSE | 5.8734 | 2.1164 | 7.9898 | 97 | 0.0022061 | 20 | 1.2106 | 2115 | 0.0026407 | 897
LAURELES 11116421 | LAURELES 1111 | 182371111 | FALSE | 1.7275 | 0.070373 | 1.7979 | 34.5 | 0.00016367 | 10552 | 16.0806 | 638 | 0.0026395 | 898
LUCERNE 110638436 | LUCERNE 1106 | 43351106 | FALSE | 4.7494 | 1.5739 | 5.9838 | 65.5 | 0.00028175 | 8383 | 10.4528 | 820 | 0.0026371 | 899
CAMP EVERS 2106130936 | CAMP EVERS 2106 | 83622106 | FALSE | 2.51 | 0.030881 | 2.5409 | 50 | 0.0019405 | 31 | 1.4194 | 1912 | 0.002636 | 900
SAN ARDO 1102323708 | SAN ARDO 1102 | 182191102 |  | 2.6967 | 0.022774 |  | 56.5 | 9.4381e-05 | 11066 | 31.8013 | 347 | 0.002628 | 901
RAWSON 1103428534 | RAWSON 1103 | 103531103 | FALSE | 5.435 | 0.017775 | 2.745 | 108.5 | 0.00018348 | 10299 | 12.6493 | 735 | 0.002624 | 902
POINT MORETTI 110110726 | POINT MORETTI 1101 | 82931101 | FALSE | 10.4869 | 1.6022 | 12.0891 | 183.8333 | 0.0011181 | 434 | 2.3125 | 1551 | 0.0026122 | 903
LOS GATOS 1106917258 | LOS GATOS 1106 | 82021106 | FALSE | 4.0824 | 0.25029 | 4.3327 | 79.5 | 0.00072652 | 2770 | 3.6957 | 1284 | 0.0026082 | 904
SHINGLE SPRINGS 2105CB | SHINGLE SPRINGS 2105 | 153652105 | FALSE | 18.9503 | 2.0318 | 20.982 | 338.3333 | 0.00050311 | 5355 | 5.6289 | 1096 | 0.0026063 | 905
SAN JUSTO 11014002 | SAN JUSTO 1101 | 183181101 | FALSE | 18.6728 | 0.74802 | 18.6548 | 356.5 | 0.00015346 | 10663 | 15.1915 | 655 | 0.002606 | 906
CAMP EVERS 210512590 | CAMP EVERS 2105 | 83622105 | FALSE | 5.4869 | 3.014 | 7.5692 | 87.3333 | 0.0019226 | 32 | 1.3266 | 1983 | 0.0026049 | 907
CLAYTON 2213167700 | CLAYTON 2213 | 12022213 | FALSE | 2.4874 | 0 | 2.4874 | 47.5 | 0.00018252 | 10312 | 20.7588 | 541 | 0.0025986 | 908
WYANDOTTE 110213044 | WYANDOTTE 1102 | 102911102 | FALSE | 6.0113 | 0.1254 | 4.3837 | 109 | 0.00032812 | 7483 | 8.2254 | 928 | 0.0025956 | 909
SAN RAFAEL 110839156 | SAN RAFAEL 1108 | 42011108 | FALSE | 4.8189 | 3.9578 | 6.3993 | 98 | 0.0010271 | 703 | 2.6226 | 1478 | 0.0025904 | 910
CLOVERDALE 1102383183 | CLOVERDALE 1102 | 42821102 | FALSE | 14.7748 | 0.19477 | 14.6824 | 283.5 | 0.00012884 | 10892 | 23.3995 | 486 | 0.0025886 | 911
RACETRACK 170310850 | RACETRACK 1703 | 163761703 | FALSE | 1.9053 | 1.402 | 0.8832 | 27.8333 | 0.00071088 | 2965 | 3.071 | 1379 | 0.0025873 | 912
OAKHURST 110110090 | OAKHURST 1101 | 254421101 | FALSE | 43.8357 | 2.7646 | 46.6002 | 801.5 | 0.00020834 | 9903 | 19.0835 | 570 | 0.0025801 | 913
HALF MOON BAY 11038898 | HALF MOON BAY 1103 | 24101103 | FALSE | 0.61974 | 0.22903 | 0.84877 | 11 | 0.0016213 | 75 | 1.5098 | 1839 | 0.0025777 | 914
BEN LOMOND 0401CB | BEN LOMOND 0401 | 83040401 | FALSE | 7.7092 | 3.1567 | 10.8659 | 121.2833 | 0.0019157 | 33 | 1.3331 | 1980 | 0.0025749 | 915
OLETA 11021204 | OLETA 1102 | 163541102 | FALSE | 28.9671 | 0.96334 | 24.8563 | 543 | 0.00016876 | 10500 | 18.8882 | 574 | 0.0025746 | 916
LOS GATOS 1106LB44 | LOS GATOS 1106 | 82021106 | FALSE | 15.5274 | 1.961 | 9.9229 | 278.5 | 0.00054624 | 4899 | 4.7638 | 1163 | 0.0025708 | 917
GRASS VALLEY 11031700 | GRASS VALLEY 1103 | 152031103 | FALSE | 21.7769 | 2.2037 | 23.8902 | 397 | 0.00034054 | 7298 | 9.8287 | 842 | 0.0025659 | 918
EMERALD LAKE 04028858 | EMERALD LAKE 0402 | 24080402 | FALSE | 1.8845 | 1.2329 | 3.1174 | 30.3333 | 0.00050135 | 5382 | 5.1383 | 1129 | 0.0025594 | 919
CALISTOGA 1101890 | CALISTOGA 1101 | 42711101 | FALSE | 9.0971 | 0.48673 | 9.1084 | 186.5 | 0.00041563 | 6268 | 6.8073 | 1011 | 0.0025473 | 920
SONOMA 11045661 | SONOMA 1104 | 42721104 | FALSE | 5.0119 | 0.8973 | 2.6645 | 98.5 | 0.00038666 | 6625 | 8.6439 | 902 | 0.0025443 | 921
SPRING GAP 17029690 | SPRING GAP 1702 | 162831702 | FALSE | 16.6921 | 2.8302 | 19.5223 | 281.5 | 0.00042268 | 6198 | 6.4995 | 1034 | 0.0025407 | 922
SHADY GLEN 1101145584 | SHADY GLEN 1101 | 152431101 | FALSE | 0.96889 | 0.42868 | 0.93912 | 16 | 0.00059175 | 4396 | 4.9108 | 1148 | 0.0025376 | 923
FULTON 1107914380 | FULTON 1107 | 42561107 | FALSE | 3.0401 | 0.21618 | 3.2563 | 57.5 | 0.00021333 | 9811 | 11.7861 | 766 | 0.0025342 | 924
FROGTOWN 1702812366 | FROGTOWN 1702 | 163451702 | FALSE | 2.6833 | 0.28931 | 2.7867 | 53 | 0.00018806 | 10233 | 14.4478 | 682 | 0.0025267 | 925
NOTRE DAME 11042408 | NOTRE DAME 1104 | 102041104 | FALSE | 5.5261 | 0.02497 | 3.0991 | 111 | 0.00026513 | 8753 | 7.6017 | 959 | 0.0025265 | 926
MIWUK 1702S2247 | MIWUK 1702 | 163661702 | FALSE | 1.5243 | 1.2343 | 2.7574 | 25 | 0.00051238 | 5263 | 4.9261 | 1145 | 0.002524 | 927
CLOVERDALE 11024646 | CLOVERDALE 1102 | 42821102 | TRUE | 0.29658 | 0 | 0.14877 | 6.3333 | 0.00045803 | 5835 | 12.3072 | 747 | 0.002524 | 928
LOS GATOS 110760118 | LOS GATOS 1107 | 82021107 | FALSE | 18.6541 | 2.3484 | 14.6062 | 347 | 0.00095361 | 997 | 2.5721 | 1491 | 0.0025146 | 929
BEAR VALLEY 210110000 | BEAR VALLEY 2101 | 252192101 | FALSE | 33.8533 | 1.4991 | 30.8734 | 659 | 0.00011161 | 11007 | 23.1998 | 491 | 0.0025111 | 930
LOW GAP 110137498 | LOW GAP 1101 | 192411101 | FALSE | 16.2342 | 0.8496 | 17.0837 | 321.5 | 0.00023141 | 9453 | 11.72 | 769 | 0.0025058 | 931
CAMP EVERS 210610718 | CAMP EVERS 2106 | 83622106 | FALSE | 8.3427 | 0.79975 | 9.1424 | 146 | 0.0012719 | 228 | 1.9532 | 1656 | 0.0025058 | 932
CLARK ROAD 1102514690 | CLARK ROAD 1102 | 103091102 | FALSE | 3.4101 | 0.071741 | 3.4819 | 34.6667 | 0.00024844 | 9113 | 10.0124 | 832 | 0.0025042 | 933
JOLON 11027068 | JOLON 1102 | 182981102 | FALSE | 3.8089 | 0.074656 | 3.8255 | 76.5 | 9.0534e-05 | 11082 | 29.1526 | 383 | 0.0024997 | 934
MIDDLETOWN 1101829164 | MIDDLETOWN 1101 | 43141101 | TRUE | 9.8853 | 1.845 | 0.5112 | 174.3333 | 0.00031918 | 7647 | 12.2347 | 750 | 0.002498 | 935
BIG BASIN 11022253 | BIG BASIN 1102 | 82841102 | FALSE | 0.64585 | 0 | 0.64585 | 12.3333 | 0.0021713 | 22 | 1.15 | 2248 | 0.002497 | 936
POINT MORETTI 110136516 | POINT MORETTI 1101 | 82931101 | FALSE | 3.9186 | 0.45936 | 4.3779 | 72.1667 | 0.0015262 | 100 | 1.6023 | 1785 | 0.0024963 | 937
WILLOW CREEK 11032936 | WILLOW CREEK 1103 | 192171103 | FALSE | 32.6024 | 1.5405 | 34.1427 | 622.5 | 0.00027183 | 8612 | 10.9401 | 802 | 0.0024804 | 938
SAND CREEK 11037110 | SAND CREEK 1103 | 254601103 | FALSE | 18.5818 | 1.9365 | 20.5182 | 374.5 | 0.00015049 | 10701 | 15.4194 | 649 | 0.0024788 | 939
PASO ROBLES 1103N54 | PASO ROBLES 1103 | 182611103 | FALSE | 23.1579 | 0.66957 | 21.8026 | 403.3333 | 0.00014553 | 10743 | 15.0659 | 661 | 0.0024787 | 940
SARATOGA 1106LC24 | SARATOGA 1106 | 83371106 | FALSE | 11.5296 | 3.8802 | 10.6338 | 202 | 0.00061382 | 4123 | 4.1508 | 1235 | 0.0024786 | 941
CALISTOGA 110178734 | CALISTOGA 1101 | 42711101 | FALSE | 11.0321 | 0.19352 | 11.0023 | 212.5 | 0.00020369 | 9987 | 12.8166 | 733 | 0.0024672 | 942
WILDWOOD 1101CB | WILDWOOD 1101 | 103611101 | TRUE | 0.12481 | 0.021104 | 0.14591 | 1.5 | 0.000405 | 6399 | 6.0879 | 1066 | 0.0024656 | 943
UPPER LAKE 1101472084 | UPPER LAKE 1101 | 42871101 | FALSE | 7.3403 | 1.0067 | 4.9819 | 135 | 0.00030253 | 7954 | 8.3891 | 916 | 0.002465 | 944
CUYAMA 1103622728 | CUYAMA 1103 | 253141103 |  | 35.1217 | 0.23143 |  | 705 | 0.00012066 | 10945 | 17.5225 | 610 | 0.0024633 | 945
CURTIS 1703CB | CURTIS 1703 | 163351703 | FALSE | 11.1253 | 0.97682 | 9.6883 | 197.7 | 0.00044795 | 5934 | 6.7236 | 1017 | 0.0024621 | 946
LOS GATOS 1101LB40 | LOS GATOS 1101 | 82021101 | FALSE | 9.337 | 4.5408 | 11.9019 | 158 | 0.00047783 | 5622 | 8.6355 | 904 | 0.0024608 | 947
MONTE RIO 1113532 | MONTE RIO 1113 | 42811113 | FALSE | 0.52464 | 0.31222 | 0.83686 | 7.5 | 0.0021383 | 24 | 1.15 | 2248 | 0.0024591 | 948
PENRYN 1103604 | PENRYN 1103 | 152561103 | FALSE | 26.6934 | 1.8431 | 28.032 | 476.3333 | 0.00022995 | 9489 | 8.7656 | 896 | 0.0024548 | 949
MOUNTAIN QUARRIES 21016953 | MOUNTAIN QUARRIES 2101 | 152282101 | FALSE | 5.5274 | 0.63885 | 6.1662 | 104 | 0.00016095 | 10589 | 17.8491 | 603 | 0.0024509 | 950
MORAGA 1102CB | MORAGA 1102 | 13801102 | FALSE | 8.2428 | 5.4681 | 7.6923 | 137.75 | 0.00074965 | 2488 | 3.5393 | 1307 | 0.002442 | 951
COVELO 1101430286 | COVELO 1101 | 43061101 | FALSE | 5.592 | 0.020919 | 2.773 | 107.5 | 0.00010039 | 11047 | 27.5345 | 412 | 0.0024413 | 952
ALLEGHANY 1101808 | ALLEGHANY 1101 | 152101101 | FALSE | 6.1773 | 0 | 6.1773 | 124.8333 | 0.00037994 | 6696 | 5.8872 | 1078 | 0.0024397 | 953
NARROWS 2105CB | NARROWS 2105 | 153132105 | FALSE | 35.9784 | 1.8077 | 37.0159 | 644.25 | 0.00024924 | 9095 | 9.2638 | 868 | 0.0024388 | 954
BIG BASIN 110165444 | BIG BASIN 1101 | 82841101 | FALSE | 0.4654 | 0.29522 | 0.76062 | 8.8333 | 0.0021177 | 25 | 1.15 | 2247 | 0.0024354 | 955
HOPLAND 1101154790 | HOPLAND 1101 | 42251101 | FALSE | 15.261 | 0.35195 | 6.4475 | 304.8333 | 0.00021967 | 9708 | 13.6296 | 706 | 0.0024268 | 956
OREGON TRAIL 11031500 | OREGON TRAIL 1103 | 103521103 | FALSE | 25.927 | 2.9453 | 28.8722 | 468 | 0.00032559 | 7529 | 11.6402 | 774 | 0.0024201 | 957
MIWUK 17028130 | MIWUK 1702 | 163661702 | FALSE | 9.669 | 0.68308 | 10.352 | 163 | 0.00035524 | 7050 | 9.6619 | 851 | 0.0024172 | 958
CLAYTON 2215W531R | CLAYTON 2215 | 12022215 | FALSE | 8.2819 | 1.3496 | 4.2669 | 150 | 0.00043066 | 6111 | 7.72 | 953 | 0.0024107 | 959
COARSEGOLD 2102CB | COARSEGOLD 2102 | 254432102 | FALSE | 14.0764 | 0.15583 | 14.2322 | 248.6667 | 0.00017766 | 10388 | 14.1943 | 689 | 0.0024072 | 960
SUMMIT 1101CB | SUMMIT 1101 | 152591101 | TRUE | 0.13735 | 0 | 0.13735 | 1 | 0.001111 | 456 | 2.1666 | 1588 | 0.0024071 | 961
GEYSERVILLE 1102484 | GEYSERVILLE 1102 | 42891102 | FALSE | 49.0571 | 2.5151 | 32.0689 | 979.5 | 0.00024913 | 9099 | 14.671 | 674 | 0.0024054 | 962
WILLITS 1103409216 | WILLITS 1103 | 42661103 | FALSE | 19.8451 | 0.55901 | 20.3982 | 359 | 0.00026214 | 8828 | 8.387 | 917 | 0.0024054 | 963
LOS GATOS 110760092 | LOS GATOS 1107 | 82021107 | FALSE | 9.7198 | 1.7083 | 11.4281 | 177.5 | 0.00096266 | 944 | 2.377 | 1537 | 0.0024045 | 964
BEN LOMOND 040116010 | BEN LOMOND 0401 | 83040401 | FALSE | 1.6882 | 1.1809 | 2.8691 | 29.0833 | 0.0018746 | 38 | 1.2926 | 2013 | 0.0024034 | 965
CAMP EVERS 21055146 | CAMP EVERS 2105 | 83622105 | FALSE | 5.9263 | 2.0095 | 7.9358 | 94.3333 | 0.0018311 | 40 | 1.3136 | 1995 | 0.0024029 | 966
MONTE RIO 111264682 | MONTE RIO 1112 | 42811112 | FALSE | 1.7722 | 1.4966 | 3.2688 | 27.5 | 0.0014853 | 116 | 1.4865 | 1859 | 0.0023926 | 967
PARADISE 1105828400 | PARADISE 1105 | 102831105 | TRUE | 0.031137 | 0 | 0.031136 | 1.5 | 0.00098046 | 871 | 2.4329 | 1527 | 0.0023866 | 968
BIG MEADOWS 21012510 | BIG MEADOWS 2101 | 102812101 | FALSE | 8.6382 | 0 | 8.6382 | 172.8333 | 0.00027046 | 8640 | 9.7345 | 849 | 0.0023864 | 969
EAST QUINCY 1101186938 | EAST QUINCY 1101 | 102551101 | FALSE | 2.9866 | 1.9727 | 1.959 | 58 | 0.00041266 | 6306 | 6.2062 | 1053 | 0.0023851 | 970
ROSSMOOR 1109CB | ROSSMOOR 1109 | 14161109 |  | 0.05655 | 0 |  | 0.91667 | 0.0013491 | 163 | 1.4643 | 1876 | 0.0023822 | 971
LAURELES 11112020 | LAURELES 1111 | 182371111 | FALSE | 33.9289 | 2.5805 | 36.5093 | 650 | 0.00019841 | 10071 | 12.2781 | 749 | 0.0023689 | 972
SAN ARDO 110273254 | SAN ARDO 1102 | 182191102 |  | 3.3504 | 0 |  | 61.5 | 0.0001166 | 10975 | 19.5385 | 564 | 0.0023588 | 973
SAN RAFAEL 1101546438 | SAN RAFAEL 1101 | 42011101 | FALSE | 0.93992 | 0.63074 | 1.5158 | 15.3333 | 0.0011627 | 355 | 1.7224 | 1735 | 0.0023568 | 974
AUBERRY 1101D4982 | AUBERRY 1101 | 254151101 | FALSE | 2.6245 | 0 | 2.6245 | 43.5 | 0.0003083 | 7836 | 7.6855 | 956 | 0.0023564 | 975
BIG BASIN 110169550 | BIG BASIN 1101 | 82841101 | FALSE | 12.4742 | 1.8996 | 8.907 | 220.5 | 0.0010987 | 474 | 2.1248 | 1598 | 0.0023502 | 976
MIRABEL 1102332 | MIRABEL 1102 | 42091102 | FALSE | 6.9611 | 2.6424 | 7.8544 | 126.5 | 0.00084909 | 1580 | 2.5475 | 1497 | 0.0023452 | 977
LOS GATOS 1101950286 | LOS GATOS 1101 | 82021101 | FALSE | 1.0346 | 0.85964 | 1.8942 | 17.5 | 0.00075754 | 2413 | 3.2483 | 1349 | 0.002339 | 978
SHINGLE SPRINGS 21107742 | SHINGLE SPRINGS 2110 | 153652110 | FALSE | 23.1444 | 1.7991 | 24.907 | 412 | 0.00026142 | 8856 | 11.2158 | 792 | 0.0023324 | 979
APPLE HILL 110412842 | APPLE HILL 1104 | 153661104 | FALSE | 16.8588 | 3.2547 | 18.5326 | 309.5 | 0.00040437 | 6404 | 4.6229 | 1175 | 0.0023233 | 980
MONTE RIO 1112387984 | MONTE RIO 1112 | 42811112 | TRUE | 0.45068 | 0.0075931 | 0.45827 | 9.5 | 0.00079253 | 2038 | 2.4342 | 1526 | 0.0023208 | 981
WOODACRE 1102137662 | WOODACRE 1102 | 43021102 | FALSE | 8.6127 | 6.5109 | 14.993 | 144 | 0.00081961 | 1823 | 3.0758 | 1374 | 0.0023176 | 982
SCE TEHACHAPI 1101CB | SCE TEHACHAPI 1101 | 258131101 | FALSE | 1.1708 | 0 | 1.1708 | 26 | 3.706e-05 | 11137 | 52.4309 | 153 | 0.0023148 | 983
SAN RAFAEL 1108322 | SAN RAFAEL 1108 | 42011108 | FALSE | 7.4326 | 6.2762 | 13.3894 | 107.3333 | 0.0010265 | 704 | 2.1788 | 1586 | 0.0023118 | 984
SUNOL 1101MR297 | SUNOL 1101 | 14241101 | FALSE | 6.0926 | 0.79814 | 6.5644 | 118 | 0.00038321 | 6661 | 5.7328 | 1091 | 0.0023031 | 985
POINT MORETTI 110136514 | POINT MORETTI 1101 | 82931101 | FALSE | 6.8662 | 0.29208 | 7.1583 | 129.5 | 0.0009382 | 1059 | 2.3904 | 1534 | 0.002303 | 986
JAMESON 1105913400 | JAMESON 1105 | 63801105 | TRUE | 1.0937 | 0.079125 | 0.040017 | 19.5 | 0.00016256 | 10568 | 17.4157 | 614 | 0.0022992 | 987
HICKS 111660050 | HICKS 1116 | 83431116 | FALSE | 8.169 | 1.3998 | 9.5291 | 137.5 | 0.00034405 | 7237 | 7.5347 | 961 | 0.0022986 | 988
LUCERNE 1106664 | LUCERNE 1106 | 43351106 | FALSE | 11.1503 | 3.494 | 12.2137 | 199.5 | 0.00043024 | 6115 | 4.8042 | 1159 | 0.0022973 | 989
CAMP EVERS 210510728 | CAMP EVERS 2105 | 83622105 | FALSE | 11.5447 | 6.5141 | 16.5511 | 171.0833 | 0.0017479 | 47 | 1.2669 | 2035 | 0.0022953 | 990
DUNLAP 11037080 | DUNLAP 1103 | 254061103 | FALSE | 10.7588 | 2.5446 | 13.3034 | 212.5 | 0.00037097 | 6825 | 5.6944 | 1093 | 0.0022903 | 991
LAYTONVILLE 1101402 | LAYTONVILLE 1101 | 42681101 | FALSE | 23.3671 | 0.42185 | 23.2981 | 458 | 0.00020563 | 9951 | 12.5734 | 739 | 0.0022826 | 992
HIGGINS 1104533648 | HIGGINS 1104 | 152691104 | FALSE | 6.7297 | 1.3691 | 8.0988 | 126.5 | 0.00041453 | 6290 | 5.4763 | 1107 | 0.0022826 | 993
AUBURN 11028611 | AUBURN 1102 | 152161102 | FALSE | 1.7982 | 1.0511 | 2.8493 | 28.5 | 0.00060789 | 4195 | 3.3953 | 1330 | 0.0022814 | 994
PEORIA 170413490 | PEORIA 1704 | 163781704 | FALSE | 5.42 | 0.34349 | 3.7686 | 97.5 | 0.00042323 | 6189 | 8.0146 | 934 | 0.0022807 | 995
CAMP EVERS 210510912 | CAMP EVERS 2105 | 83622105 | FALSE | 4.865 | 0.31993 | 5.1849 | 84.6667 | 0.0016432 | 70 | 1.4851 | 1860 | 0.0022797 | 996
LOS GATOS 110760024 | LOS GATOS 1107 | 82021107 | FALSE | 3.7366 | 0.060972 | 3.7976 | 71.5 | 0.00012601 | 10920 | 18.6791 | 580 | 0.0022767 | 997
WILLOW CREEK 110347966 | WILLOW CREEK 1103 | 192171103 | FALSE | 17.1146 | 2.0753 | 17.0476 | 308.5 | 0.00032631 | 7515 | 6.727 | 1016 | 0.0022694 | 998
BURNS 2101CB | BURNS 2101 | 183582101 | FALSE | 1.666 | 0.24792 | 1.914 | 26.8333 | 0.0017309 | 50 | 1.3587 | 1961 | 0.0022686 | 999
PUEBLO 210378504 | PUEBLO 2103 | 43292103 |  | 11.7489 | 0.6109 |  | 222 | 0.00042425 | 6181 | 5.4067 | 1110 | 0.0022679 | 1000
SAN RAFAEL 1108516 | SAN RAFAEL 1108 | 42011108 | FALSE | 10.8191 | 8.6209 | 19.44 | 190 | 0.00074935 | 2494 | 3.1197 | 1369 | 0.0022627 | 1001
LOS GATOS 1107812664 | LOS GATOS 1107 | 82021107 | FALSE | 8.188 | 0.40793 | 8.5959 | 158.5 | 0.00016127 | 10582 | 16.1967 | 634 | 0.0022615 | 1002
LOS GATOS 1107772050 | LOS GATOS 1107 | 82021107 | FALSE | 14.5035 | 2.1119 | 16.6153 | 266.5 | 0.00077779 | 2174 | 2.7011 | 1457 | 0.0022599 | 1003
CARBONA 1101975330 | CARBONA 1101 | 163091101 |  | 1.3598 | 0 |  | 25.5 | 0.00011653 | 10977 | 23.6272 | 482 | 0.0022582 | 1004
SHADY GLEN 1101578248 | SHADY GLEN 1101 | 152431101 | TRUE | 0.21681 | 0 | 0.19667 | 4.5 | 0.00031451 | 7730 | 7.1772 | 987 | 0.0022573 | 1005
MORGAN HILL 2105XR070 | MORGAN HILL 2105 | 83242105 | FALSE | 8.6751 | 0.82371 | 6.3969 | 162 | 0.00027793 | 8471 | 7.9579 | 938 | 0.0022511 | 1006
HIGHLANDS 1103CB | HIGHLANDS 1103 | 43361103 | FALSE | 12.2277 | 3.0231 | 12.4921 | 203.75 | 0.00043144 | 6104 | 5.4867 | 1106 | 0.0022491 | 1007
OAKHURST 1102538042 | OAKHURST 1102 | 254421102 |  | 0.4352 | 0.10304 |  | 8.3333 | 0.00080382 | 1946 | 2.3226 | 1549 | 0.0022429 | 1008
CLARK ROAD 1102407706 | CLARK ROAD 1102 | 103091102 | FALSE | 9.183 | 0.12281 | 9.0959 | 140.5 | 0.00016179 | 10576 | 16.1011 | 636 | 0.0022353 | 1009
RISING RIVER 11019032 | RISING RIVER 1101 | 103551101 | FALSE | 23.289 | 1.953 | 23.6291 | 452.5 | 0.00019366 | 10152 | 14.9622 | 664 | 0.0022267 | 1010
FROGTOWN 17021573 | FROGTOWN 1702 | 163451702 | FALSE | 17.9534 | 0.59539 | 18.5487 | 343.5 | 9.7793e-05 | 11062 | 18.5077 | 586 | 0.0022166 | 1011
CALISTOGA 1101727772 | CALISTOGA 1101 | 42711101 | FALSE | 1.9315 | 0 | 1.3476 | 38.5 | 0.00039221 | 6538 | 5.9969 | 1074 | 0.0022109 | 1012
OLETA 1101296804 | OLETA 1101 | 163541101 | FALSE | 3.3899 | 0 | 3.3899 | 61.75 | 0.00024836 | 9117 | 9.7261 | 850 | 0.0022015 | 1013
ELK CREEK 11012212 | ELK CREEK 1101 | 102781101 | FALSE | 33.6921 | 1.1142 | 10.6557 | 639.5 | 0.00012375 | 10932 | 21.4879 | 530 | 0.0022012 | 1014
BIG BASIN 110112838 | BIG BASIN 1101 | 82841101 | FALSE | 2.3734 | 1.1047 | 3.4781 | 37.5 | 0.0019107 | 34 | 1.15 | 2248 | 0.0021973 | 1015
LOW GAP 11014160 | LOW GAP 1101 | 192411101 | FALSE | 17.385 | 0.95917 | 18.3441 | 344 | 0.00028843 | 8226 | 7.2554 | 977 | 0.002197 | 1016
DUNBAR 1103302 | DUNBAR 1103 | 43071103 | FALSE | 4.3767 | 0.26617 | 1.5375 | 80 | 0.00051143 | 5270 | 5.3657 | 1113 | 0.0021967 | 1017
CURTIS 1701CB | CURTIS 1701 | 163351701 | FALSE | 12.0898 | 1.9504 | 8.549 | 216.2 | 0.00050013 | 5388 | 4.5659 | 1178 | 0.0021952 | 1018
KERCKHOFF 1101CB | KERCKHOFF 1101 | 252561101 | FALSE | 16.6898 | 0.97645 | 17.6662 | 309.5 | 0.00019697 | 10092 | 12.367 | 746 | 0.0021949 | 1019
MIWUK 1702576504 | MIWUK 1702 | 163661702 | FALSE | 4.0914 | 2.2173 | 6.3062 | 71.5 | 0.00057217 | 4628 | 3.9601 | 1258 | 0.0021939 | 1020
POINT MORETTI 11015078 | POINT MORETTI 1101 | 82931101 | FALSE | 14.8482 | 1.2534 | 16.1015 | 272 | 0.00086356 | 1467 | 2.4543 | 1519 | 0.0021937 | 1021
APPLE HILL 210277546 | APPLE HILL 2102 | 153662102 | FALSE | 42.3317 | 1.3692 | 43.7008 | 796.5 | 0.00022251 | 9657 | 11.7123 | 770 | 0.002192 | 1022
LONE TREE 2105708440 | LONE TREE 2105 | 13232105 | FALSE | 15.9536 | 0.10575 | 11.1333 | 304.5 | 0.00011257 | 11001 | 24.2525 | 466 | 0.0021833 | 1023
WYANDOTTE 110738438 | WYANDOTTE 1107 | 102911107 | FALSE | 16.6395 | 0.81966 | 17.4591 | 286.5 | 0.00017795 | 10380 | 10.8879 | 806 | 0.0021794 | 1024
TEMPLETON 2110317796 | TEMPLETON 2110 | 183052110 | FALSE | 7.3781 | 0.12529 | 4.4678 | 133 | 0.00021439 | 9789 | 9.9711 | 835 | 0.0021788 | 1025
WOODSIDE 11018974 | WOODSIDE 1101 | 24251101 | FALSE | 13.1152 | 2.653 | 13.2209 | 245 | 0.0012485 | 243 | 1.8334 | 1691 | 0.0021738 | 1026
NARROWS 21052216 | NARROWS 2105 | 153132105 | FALSE | 58.1749 | 4.5855 | 61.1276 | 1049.5 | 0.00028867 | 8220 | 6.9022 | 1001 | 0.0021725 | 1027
CLARK ROAD 110281296 | CLARK ROAD 1102 | 103091102 | FALSE | 15.6241 | 0.57964 | 6.0988 | 281.3333 | 0.0002095 | 9881 | 18.2926 | 587 | 0.0021691 | 1028
SARATOGA 1115463510 | SARATOGA 1115 | 83371115 | FALSE | 2.9744 | 0.47844 | 3.301 | 55.5 | 0.00037003 | 6838 | 6.3441 | 1043 | 0.0021633 | 1029
CAMP EVERS 210612518 | CAMP EVERS 2106 | 83622106 | FALSE | 15.4984 | 1.5047 | 17.0031 | 291 | 0.0010298 | 689 | 2.0109 | 1627 | 0.002162 | 1030
POSO MOUNTAIN 2104CB | POSO MOUNTAIN 2104 | 253642104 | FALSE | 7.756 | 0.015906 | 3.3596 | 135.3333 | 0.00034089 | 7294 | 4.5287 | 1183 | 0.0021587 | 1031
CAMP EVERS 210311056 | CAMP EVERS 2103 | 83622103 | FALSE | 4.1356 | 2.5187 | 6.5138 | 68 | 0.0017844 | 44 | 1.1831 | 2157 | 0.0021574 | 1032
SANTA YNEZ 1102320270 | SANTA YNEZ 1102 | 182721102 | FALSE | 17.2354 | 1.0333 | 8.5433 | 325.5 | 0.00019694 | 10093 | 11.6521 | 773 | 0.0021438 | 1033
FULTON 1107604 | FULTON 1107 | 42561107 | FALSE | 4.2385 | 0.11792 | 4.3564 | 82 | 0.00023639 | 9353 | 9.144 | 876 | 0.0021304 | 1034
MONTE RIO 111164758 | MONTE RIO 1111 | 42811111 | FALSE | 10.48 | 2.2536 | 12.7336 | 203.8333 | 0.00076737 | 2293 | 3.4065 | 1328 | 0.0021232 | 1035
CAMP EVERS 2105601610 | CAMP EVERS 2105 | 83622105 | FALSE | 10.4054 | 0.21801 | 10.6234 | 185.5 | 0.00072313 | 2814 | 3.023 | 1391 | 0.0021206 | 1036
CAYETANO 2109884904 | CAYETANO 2109 | 14422109 | FALSE | 25.728 | 2.4883 | 28.1942 | 488 | 0.00013596 | 10830 | 20.4862 | 547 | 0.0021189 | 1037
SUMMIT 11016627 | SUMMIT 1101 | 152591101 | FALSE | 0.56569 | 0.20179 | 0.76748 | 10.5 | 0.00070172 | 3078 | 2.962 | 1399 | 0.0021163 | 1038
APPLE HILL 110412832 | APPLE HILL 1104 | 153661104 | FALSE | 18.7715 | 1.1419 | 19.029 | 328.5 | 0.00044776 | 5936 | 6.115 | 1062 | 0.0021151 | 1039
CURTIS 170565908 | CURTIS 1705 | 163351705 | FALSE | 16.7731 | 1.279 | 14.5304 | 310 | 0.00030573 | 7893 | 7.9577 | 939 | 0.002111 | 1040
SAN RAMON 210853732 | SAN RAMON 2108 | 14232108 | FALSE | 7.6074 | 0.68391 | 8.2912 | 153.5 | 0.0003574 | 7017 | 6.0369 | 1071 | 0.0021105 | 1041
EL DORADO PH 210126000 | EL DORADO PH 2101 | 152762101 | FALSE | 3.6612 | 0.031429 | 3.6926 | 60.5 | 0.00038908 | 6585 | 5.524 | 1104 | 0.0021089 | 1042
WYANDOTTE 1105601234 | WYANDOTTE 1105 | 102911105 | FALSE | 10.479 | 0 | 9.7221 | 177.1667 | 0.00017545 | 10418 | 12.1782 | 752 | 0.0021046 | 1043
ELK CREEK 11012002 | ELK CREEK 1101 | 102781101 | FALSE | 29.7516 | 0.39292 | 15.3386 | 572 | 0.00018967 | 10219 | 15.337 | 651 | 0.0021026 | 1044
PUTAH CREEK 110396792 | PUTAH CREEK 1103 | 63681103 | FALSE | 4.8845 | 0.34527 | 3.5181 | 97.5 | 0.0001273 | 10908 | 18.1325 | 593 | 0.0021015 | 1045
LAYTONVILLE 1102572 | LAYTONVILLE 1102 | 42681102 | FALSE | 15.843 | 0.84523 | 16.6882 | 305.5 | 0.00033903 | 7326 | 6.2347 | 1048 | 0.0020934 | 1046
HICKS 2103LB50 | HICKS 2103 | 83432103 | FALSE | 10.9822 | 0.27767 | 10.561 | 221.5 | 0.0001818 | 10321 | 12.561 | 740 | 0.0020912 | 1047
NORTH BRANCH 1101CB | NORTH BRANCH 1101 | 163231101 | FALSE | 20.3201 | 0.47979 | 15.3119 | 372 | 0.00024491 | 9190 | 7.8605 | 946 | 0.0020877 | 1048
RADUM 1105806392 | RADUM 1105 | 13151105 | FALSE | 5.3848 | 1.5804 | 3.8253 | 99.5 | 0.00055279 | 4837 | 3.9239 | 1261 | 0.0020796 | 1049
BANGOR 11017446 | BANGOR 1101 | 103191101 | FALSE | 43.1608 | 1.3636 | 39.6723 | 758 | 0.00022765 | 9545 | 9.2108 | 873 | 0.0020777 | 1050
MIDDLETOWN 1102878 | MIDDLETOWN 1102 | 43141102 | FALSE | 5.6332 | 0.20967 | 1.9823 | 102.5 | 0.00027731 | 8484 | 21.3804 | 532 | 0.0020761 | 1051
MORGAN HILL 2105XR176 | MORGAN HILL 2105 | 83242105 | FALSE | 27.3946 | 3.0847 | 23.1575 | 518.5 | 0.00025857 | 8914 | 8.6014 | 906 | 0.0020756 | 1052
WEST POINT 110136674 | WEST POINT 1101 | 163201101 | FALSE | 11.6832 | 1.3751 | 13.0583 | 219 | 0.00048094 | 5594 | 4.914 | 1147 | 0.002074 | 1053
LAYTONVILLE 11011760 | LAYTONVILLE 1101 | 42681101 | FALSE | 12.5889 | 0.76503 | 10.0012 | 250 | 0.00042032 | 6225 | 5.0581 | 1135 | 0.0020732 | 1054
DIAMOND SPRINGS 1104705100 | DIAMOND SPRINGS 1104 | 152261104 | FALSE | 8.2784 | 0.65822 | 7.8745 | 153.5 | 0.00028148 | 8389 | 8.271 | 923 | 0.0020695 | 1055
DUNLAP 11027849F | DUNLAP 1102 | 254061102 | FALSE | 8.6069 | 0.55112 | 9.158 | 175 | 0.0001331 | 10855 | 14.7817 | 670 | 0.0020669 | 1056
UKIAH 1111534 | UKIAH 1111 | 42771111 | FALSE | 20.5975 | 0.62068 | 18.5698 | 392.5 | 0.00015895 | 10605 | 14.5448 | 678 | 0.0020651 | 1057
BIG TREES 0402737512 | BIG TREES 0402 | 83050402 | FALSE | 6.838 | 4.3406 | 10.9449 | 119 | 0.0017366 | 48 | 1.1725 | 2182 | 0.0020626 | 1058
PINE GROVE 1102467560 | PINE GROVE 1102 | 163751102 | FALSE | 2.0079 | 0.32901 | 2.3369 | 36.5 | 0.00039845 | 6471 | 5.2722 | 1119 | 0.0020619 | 1059
CURTIS 17019230 | CURTIS 1701 | 163351701 | FALSE | 2.9616 | 1.0019 | 2.8378 | 43.3333 | 0.00055202 | 4847 | 3.9142 | 1262 | 0.0020612 | 1060
FROGTOWN 1702737236 | FROGTOWN 1702 | 163451702 | FALSE | 26.6465 | 2.4142 | 9.7388 | 500.3333 | 0.00016933 | 10495 | 16.5189 | 631 | 0.002061 | 1061
SHINGLE SPRINGS 21092679 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 6.9571 | 0.14091 | 7.098 | 122.5 | 0.00023555 | 9376 | 8.7217 | 898 | 0.0020596 | 1062
BOLINAS 1101806 | BOLINAS 1101 | 42261101 | FALSE | 3.089 | 0 | 3.089 | 60.5 | 0.00040926 | 6339 | 4.867 | 1152 | 0.0020525 | 1063
SPANISH CREEK 4401CB | SPANISH CREEK 4401 | 103104401 | FALSE | 7.9437 | 0.24925 | 6.7834 | 116.5 | 0.00030342 | 7941 | 7.354 | 970 | 0.0020497 | 1064
SAN RAFAEL 11081210 | SAN RAFAEL 1108 | 42011108 | FALSE | 5.4847 | 3.856 | 5.0354 | 99 | 0.0010771 | 538 | 2.1442 | 1592 | 0.0020496 | 1065
CLARKSVILLE 210551478 | CLARKSVILLE 2105 | 153612105 | TRUE | 0.055366 | 0 | 0.052525 | 1.5 | 0.00099338 | 816 | 1.9993 | 1632 | 0.0020452 | 1066
MONTE RIO 1112CB | MONTE RIO 1112 | 42811112 | FALSE | 3.5251 | 2.9172 | 6.4423 | 57.4167 | 0.0014825 | 118 | 1.3135 | 1996 | 0.0020435 | 1067
SALT SPRINGS 21028442 | SALT SPRINGS 2102 | 163692102 | FALSE | 12.0784 | 0.3238 | 12.3316 | 248.5 | 0.00051777 | 5197 | 3.8053 | 1272 | 0.0020431 | 1068
PUEBLO 2102895310 | PUEBLO 2102 | 43292102 | TRUE | 2.6729 | 0.19133 | 0.43206 | 52.5 | 0.00033763 | 7343 | 5.5843 | 1098 | 0.0020346 | 1069
UKIAH 1114206824 | UKIAH 1114 | 42771114 | FALSE | 16.9073 | 1.4136 | 10.9241 | 316.5 | 0.00020312 | 9995 | 22.0089 | 522 | 0.0020318 | 1070
MONTE RIO 1111506 | MONTE RIO 1111 | 42811111 | FALSE | 1.2682 | 1.0426 | 2.3108 | 22.6667 | 0.0013851 | 148 | 1.4165 | 1915 | 0.002031 | 1071
BUTTE 1105751990 | BUTTE 1105 | 103081105 | FALSE | 1.8687 | 0.25739 | 2.0839 | 28 | 0.00058627 | 4462 | 3.7707 | 1275 | 0.0020299 | 1072
CANTUA 1103792930 | CANTUA 1103 | 253591103 |  | 3.883 | 0 |  | 72.5 | 8.8742e-05 | 11087 | 26.4479 | 428 | 0.0020297 | 1073
BIG BASIN 110276752 | BIG BASIN 1102 | 82841102 | FALSE | 2.6958 | 0.79291 | 3.4861 | 46 | 0.0016584 | 61 | 1.2226 | 2099 | 0.0020276 | 1074
PINE GROVE 110152088 | PINE GROVE 1101 | 163751101 | FALSE | 2.4863 | 0.27552 | 2.7618 | 48 | 0.00038708 | 6616 | 6.212 | 1051 | 0.0020264 | 1075
WHITMORE 11011594 | WHITMORE 1101 | 103601101 | FALSE | 24.0015 | 0.55518 | 24.5566 | 452 | 0.00021691 | 9751 | 11.4363 | 784 | 0.0020262 | 1076
HIGGINS 1104498932 | HIGGINS 1104 | 152691104 | FALSE | 4.1675 | 0.59892 | 4.0515 | 81 | 0.0003976 | 6481 | 5.5343 | 1103 | 0.0020202 | 1077
EAST QUINCY 1101424048 | EAST QUINCY 1101 | 102551101 | TRUE | 0.94309 | 0.2014 | 0.57048 | 16 | 0.00028049 | 8408 | 7.8679 | 944 | 0.0020201 | 1078
FROGTOWN 170212282 | FROGTOWN 1702 | 163451702 | FALSE | 6.4576 | 0.43348 | 6.8911 | 120 | 0.00021525 | 9770 | 13.8597 | 698 | 0.0020156 | 1079
DUNBAR 1101440 | DUNBAR 1101 | 43071101 | FALSE | 14.4489 | 1.1895 | 11.5402 | 280 | 0.00030145 | 7980 | 11.2123 | 793 | 0.0020136 | 1080
VINEYARD 2108609690 | VINEYARD 2108 | 14502108 | FALSE | 7.5157 | 0.54489 | 4.7696 | 137.5 | 0.00035169 | 7111 | 6.6062 | 1027 | 0.0020134 | 1081
OILFIELDS 1103N64 | OILFIELDS 1103 | 182391103 | FALSE | 12.6078 | 0.32779 | 10.7421 | 229 | 0.00022055 | 9689 | 7.6277 | 958 | 0.0020134 | 1082
FULTON 1107214 | FULTON 1107 | 42561107 | FALSE | 11.6396 | 1.2938 | 12.9334 | 201 | 0.00037924 | 6705 | 5.3571 | 1114 | 0.0020085 | 1083
HICKS 1116583284 | HICKS 1116 | 83431116 | TRUE | 0.24606 | 0.25315 | 0.26164 | 7 | 0.00038447 | 6644 | 5.9129 | 1076 | 0.0020003 | 1084
PLACERVILLE 210619732 | PLACERVILLE 2106 | 153082106 | FALSE | 9.246 | 4.1624 | 13.402 | 160.6667 | 0.00072958 | 2735 | 2.7378 | 1450 | 0.0020003 | 1085
SONOMA 11033052 | SONOMA 1103 | 42721103 | FALSE | 15.6399 | 1.6194 | 13.1724 | 306 | 0.0003311 | 7435 | 7.7634 | 950 | 0.0019988 | 1086
ATASCADERO 1103A16 | ATASCADERO 1103 | 182541103 | FALSE | 20.1897 | 0.20049 | 18.9144 | 389.5 | 0.0001507 | 10698 | 11.8979 | 762 | 0.0019963 | 1087
MENDOCINO 110137462 | MENDOCINO 1101 | 42951101 | FALSE | 4.8265 | 0.79869 | 2.3457 | 85 | 0.00042664 | 6151 | 5.3322 | 1117 | 0.0019958 | 1088
SAN RAFAEL 11081457 | SAN RAFAEL 1108 | 42011108 | FALSE | 0.75417 | 0.88757 | 1.6417 | 13.3333 | 0.0011136 | 446 | 1.5664 | 1797 | 0.0019918 | 1089
HOPLAND 1101558 | HOPLAND 1101 | 42251101 | FALSE | 9.2239 | 0.3888 | 1.3285 | 180.5 | 0.00028662 | 8268 | 6.3646 | 1041 | 0.0019806 | 1090
DUNBAR 1103234 | DUNBAR 1103 | 43071103 | FALSE | 11.62 | 2.3816 | 3.4842 | 236 | 0.00044584 | 5954 | 7.8646 | 945 | 0.0019786 | 1091
CURTIS 170190120 | CURTIS 1701 | 163351701 | FALSE | 5.1026 | 2.0846 | 3.655 | 72.8333 | 0.00055573 | 4806 | 3.7369 | 1278 | 0.0019693 | 1092
RACETRACK 17038120 | RACETRACK 1703 | 163761703 | FALSE | 8.7115 | 1.3319 | 10.0434 | 158.5 | 0.00047148 | 5685 | 4.0861 | 1247 | 0.0019687 | 1093
SAN JOAQUIN #3 1102CB | SAN JOAQUIN #3 1102 | 252531102 | FALSE | 9.5798 | 1.2599 | 10.8397 | 176.8333 | 0.00038836 | 6601 | 4.9018 | 1149 | 0.0019679 | 1094
DUNBAR 1103799422 | DUNBAR 1103 | 43071103 | TRUE | 0.43286 | 0 | 0.43286 | 8.5 | 0.00018682 | 10247 | 10.5432 | 816 | 0.0019571 | 1095
AUBURN 1101173014 | AUBURN 1101 | 152161101 | FALSE | 3.3902 | 1.9445 | 5.0416 | 53 | 0.00053012 | 5074 | 7.2064 | 984 | 0.0019566 | 1096
OILFIELDS 1103N44 | OILFIELDS 1103 | 182391103 | FALSE | 18.007 | 0.27865 | 18.2316 | 341.5 | 0.00011251 | 11002 | 15.4625 | 647 | 0.0019549 | 1097
PASO ROBLES 1104R12 | PASO ROBLES 1104 | 182611104 | FALSE | 39.8499 | 0.89882 | 26.7138 | 738 | 0.00013977 | 10791 | 12.8946 | 729 | 0.0019545 | 1098
KONOCTI 1108CB | KONOCTI 1108 | 43311108 | FALSE | 8.8634 | 3.8735 | 7.6758 | 136 | 0.00032413 | 7557 | 7.1613 | 988 | 0.0019506 | 1099
RINCON 1103198 | RINCON 1103 | 43321103 | FALSE | 6.3704 | 0.39055 | 3.2906 | 130 | 0.00028554 | 8296 | 6.5348 | 1032 | 0.001948 | 1100
OTTER 11012052 | OTTER 1101 | 182941101 | FALSE | 9.2176 | 1.3492 | 2.1382 | 179.5 | 0.00050137 | 5381 | 4.3714 | 1201 | 0.0019476 | 1101
BIG BASIN 1101393582 | BIG BASIN 1101 | 82841101 | FALSE | 5.6021 | 2.8466 | 7.4556 | 90.3333 | 0.0016929 | 57 | 1.15 | 2248 | 0.0019468 | 1102
CHALLENGE 11021902 | CHALLENGE 1102 | 103201102 | FALSE | 4.8702 | 0.23686 | 5.107 | 93 | 0.0005995 | 4300 | 3.1071 | 1371 | 0.0019466 | 1103
DUNBAR 1102261774 | DUNBAR 1102 | 43071102 | FALSE | 13.4851 | 0.75154 | 14.2366 | 250.5 | 0.00028385 | 8332 | 7.3077 | 974 | 0.0019444 | 1104
BIG BASIN 110110720 | BIG BASIN 1101 | 82841101 | FALSE | 4.5212 | 1.5237 | 6.0449 | 81 | 0.0016632 | 60 | 1.2298 | 2083 | 0.0019396 | 1105
CALISTOGA 1102CB | CALISTOGA 1102 | 42711102 | TRUE | 0.24223 | 0.072233 | 0.053457 | 3.8333 | 0.0015515 | 90 | 1.244 | 2068 | 0.0019345 | 1106
HALF MOON BAY 1103825502 | HALF MOON BAY 1103 | 24101103 | FALSE | 1.452 | 0.018993 | 1.4709 | 27 | 0.00038617 | 6627 | 5.0807 | 1133 | 0.0019316 | 1107
SAN BENITO 2101295566 | SAN BENITO 2101 | 182742101 | TRUE | 2.1323 | 0.045669 | 0.27939 | 39.5 | 0.00016957 | 10491 | 6.7604 | 1015 | 0.0019278 | 1108
SAN MIGUEL 1106605393 | SAN MIGUEL 1106 | 182661106 | FALSE | 25.0234 | 0.35506 | 20.894 | 493.5 | 0.00012369 | 10933 | 16.1128 | 635 | 0.0019184 | 1109
LAYTONVILLE 1101448108 | LAYTONVILLE 1101 | 42681101 | FALSE | 7.1118 | 0.20612 | 7.2723 | 138 | 0.00031094 | 7788 | 6.1985 | 1054 | 0.0019172 | 1110
BIG TREES 04025300 | BIG TREES 0402 | 83050402 | FALSE | 9.7027 | 3.707 | 13.4097 | 158 | 0.0016331 | 71 | 1.1693 | 2195 | 0.0019082 | 1111
BIG BASIN 110212992 | BIG BASIN 1102 | 82841102 | FALSE | 14.9919 | 4.0683 | 18.0112 | 257 | 0.0012878 | 215 | 1.5576 | 1801 | 0.0019059 | 1112
BIG BASIN 110110296 | BIG BASIN 1101 | 82841101 | FALSE | 14.4156 | 6.737 | 20.2314 | 243.5 | 0.001655 | 63 | 1.1513 | 2243 | 0.0019056 | 1113
HIGHLANDS 1103828 | HIGHLANDS 1103 | 43361103 | FALSE | 10.534 | 0.87025 | 7.8808 | 190 | 0.00026806 | 8699 | 9.8064 | 844 | 0.0019049 | 1114
DUNLAP 11027060 | DUNLAP 1102 | 254061102 | FALSE | 18.0342 | 1.4289 | 19.463 | 343.5 | 0.00012621 | 10918 | 18.1425 | 592 | 0.0018983 | 1115
HALF MOON BAY 1103157944 | HALF MOON BAY 1103 | 24101103 | FALSE | 4.2767 | 0.12509 | 4.4018 | 86.5 | 0.00043884 | 6023 | 3.9489 | 1260 | 0.0018955 | 1116
MARTELL 11016074 | MARTELL 1101 | 163011101 | FALSE | 3.7096 | 0.25247 | 3.9621 | 65.8333 | 0.0004589 | 5818 | 3.6854 | 1286 | 0.0018908 | 1117
SALT SPRINGS 21023118 | SALT SPRINGS 2102 | 163692102 | TRUE | 0.054151 | 0.010772 | 0.064923 | 1 | 0.0015447 | 91 | 1.2226 | 2099 | 0.0018886 | 1118
SANTA ROSA A 1111147198 | SANTA ROSA A 1111 | 42151111 | FALSE | 1.9242 | 0.67551 | 1.3222 | 40 | 0.00047377 | 5663 | 4.6663 | 1169 | 0.0018869 | 1119
BIG BASIN 11015000 | BIG BASIN 1101 | 82841101 | FALSE | 1.6885 | 0.28993 | 1.9784 | 28.3333 | 0.0015437 | 93 | 1.223 | 2097 | 0.0018854 | 1120
SHINGLE SPRINGS 210819762 | SHINGLE SPRINGS 2108 | 153652108 | FALSE | 5.4505 | 0.16305 | 4.3152 | 83 | 0.0004801 | 5602 | 6.4137 | 1036 | 0.0018846 | 1121
BIG BASIN 110212124 | BIG BASIN 1102 | 82841102 | FALSE | 4.4638 | 0.99174 | 5.4556 | 76 | 0.0015905 | 82 | 1.1745 | 2176 | 0.001882 | 1122
WOODSIDE 1104420146 | WOODSIDE 1104 | 24251104 | FALSE | 3.0556 | 0.70539 | 3.2459 | 65.5 | 0.00075882 | 2402 | 2.7187 | 1452 | 0.0018814 | 1123
PARADISE 1105878870 | PARADISE 1105 | 102831105 | FALSE | 2.7121 | 0.83498 | 3.547 | 44.5 | 0.00066276 | 3533 | 2.8846 | 1418 | 0.0018782 | 1124
SAN LUIS OBISPO 1104V46 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 20.8368 | 0.40278 | 18.9304 | 398.5 | 0.00015985 | 10602 | 15.6097 | 645 | 0.0018745 | 1125
CAMP EVERS 210611006 | CAMP EVERS 2106 | 83622106 | FALSE | 2.0452 | 1.112 | 3.1572 | 31.5 | 0.0016267 | 73 | 1.15 | 2247 | 0.0018707 | 1126
MONTE RIO 11135024 | MONTE RIO 1113 | 42811113 | TRUE | 0.32078 | 0.025382 | 0.34616 | 4.3333 | 0.0016263 | 74 | 1.15 | 2249 | 0.0018702 | 1127
KERN OIL 1106412184 | KERN OIL 1106 | 252721106 | FALSE | 0.87399 | 0 | 0.86011 | 15 | 0.00022582 | 9587 | 8.4055 | 915 | 0.0018676 | 1128
HOLLISTER 2102855412 | HOLLISTER 2102 | 182492102 | FALSE | 31.5051 | 0.17712 | 26.2148 | 623 | 0.00015766 | 10622 | 12.847 | 731 | 0.0018674 | 1129
MIWUK 1702823548 | MIWUK 1702 | 163661702 | FALSE | 21.9766 | 2.2495 | 21.3323 | 373.5 | 0.00031372 | 7742 | 7.9928 | 936 | 0.0018669 | 1130
WOODSIDE 11018972 | WOODSIDE 1101 | 24251101 | FALSE | 6.1602 | 0.75365 | 6.9138 | 130.5 | 0.00071033 | 2972 | 3.2355 | 1351 | 0.0018648 | 1131
BIG BASIN 11028403 | BIG BASIN 1102 | 82841102 | FALSE | 5.532 | 0.94438 | 5.5744 | 101 | 0.0009548 | 989 | 2.1752 | 1587 | 0.0018627 | 1132
LOS GATOS 110760114 | LOS GATOS 1107 | 82021107 | FALSE | 23.9383 | 1.6069 | 25.5451 | 449.5 | 0.00042233 | 6203 | 8.2856 | 922 | 0.0018601 | 1133
SHINGLE SPRINGS 2110386572 | SHINGLE SPRINGS 2110 | 153652110 | FALSE | 22.2353 | 1.4821 | 23.7173 | 413 | 0.00021682 | 9752 | 8.9503 | 885 | 0.0018593 | 1134
OAKHURST 1101910120 | OAKHURST 1101 | 254421101 | FALSE | 1.8071 | 0.22587 | 1.8308 | 32 | 0.00037922 | 6708 | 4.6497 | 1170 | 0.001856 | 1135
OLETA 110241396 | OLETA 1102 | 163541102 | FALSE | 7.2819 | 1.5059 | 8.1683 | 128.5 | 0.00042996 | 6120 | 4.1783 | 1229 | 0.0018541 | 1136
KONOCTI 11081278 | KONOCTI 1108 | 43311108 | FALSE | 7.9722 | 2.3092 | 6.4634 | 140 | 0.00045206 | 5904 | 4.3997 | 1199 | 0.0018535 | 1137
MONTE RIO 1111CB | MONTE RIO 1111 | 42811111 | TRUE | 0.25501 | 0.14794 | 0.40295 | 2.25 | 0.001224 | 263 | 1.5131 | 1837 | 0.001852 | 1138
BEN LOMOND 1101BL 1101 | BEN LOMOND 1101 | 83041101 | FALSE | 8.4304 | 4.6844 | 13.1148 | 158.5333 | 0.0015597 | 88 | 1.1935 | 2142 | 0.0018501 | 1139
BIG BASIN 110195690 | BIG BASIN 1101 | 82841101 | FALSE | 3.8589 | 2.8232 | 6.682 | 76.8333 | 0.0016678 | 58 | 1.1073 | 2296 | 0.0018455 | 1140
MENLO 1102223286 | MENLO 1102 | 24131102 | FALSE | 0.93104 | 0.028113 | 0.95915 | 20 | 0.00025275 | 9025 | 7.2498 | 978 | 0.0018324 | 1141
MIWUK 1702531976 | MIWUK 1702 | 163661702 | FALSE | 1.1972 | 0.11079 | 1.3079 | 16.5 | 0.00064291 | 3790 | 2.7938 | 1438 | 0.001826 | 1142
MARIPOSA 21014410 | MARIPOSA 2101 | 254452101 | FALSE | 22.5349 | 1.2269 | 23.7617 | 410.5 | 0.00021119 | 9859 | 9.0691 | 880 | 0.0018209 | 1143
MIRABEL 1102503000 | MIRABEL 1102 | 42091102 | FALSE | 4.6942 | 3.3921 | 7.5052 | 76 | 0.001073 | 549 | 1.7129 | 1738 | 0.0018178 | 1144
PAUL SWEET 2106974130 | PAUL SWEET 2106 | 83252106 | FALSE | 3.8103 | 0.77316 | 4.5835 | 72 | 0.0011686 | 346 | 1.4733 | 1867 | 0.0018131 | 1145
SONOMA 1102441730 | SONOMA 1102 | 42721102 | FALSE | 6.6288 | 0.77518 | 6.7471 | 121.5 | 0.00029258 | 8154 | 6.3235 | 1044 | 0.0018097 | 1146
RISING RIVER 11011530 | RISING RIVER 1101 | 103551101 | FALSE | 17.7173 | 1.1491 | 10.9226 | 328.5 | 0.00014054 | 10782 | 11.3658 | 785 | 0.0018035 | 1147
RACETRACK 17036014 | RACETRACK 1703 | 163761703 | FALSE | 6.836 | 0.95902 | 7.795 | 129.8333 | 0.00030714 | 7859 | 9.8681 | 840 | 0.0018016 | 1148
TAR FLAT 0401CB | TAR FLAT 0401 | 163240401 | FALSE | 3.6577 | 1.9275 | 4.8702 | 50.1667 | 0.00070915 | 2988 | 2.5122 | 1507 | 0.0017979 | 1149
FULTON 1102885254 | FULTON 1102 | 42561102 | FALSE | 2.0764 | 0.032877 | 2.1092 | 41.5 | 0.0001963 | 10107 | 9.5411 | 856 | 0.001797 | 1150
WILLOW CREEK 1103205028 | WILLOW CREEK 1103 | 192171103 | FALSE | 1.5379 | 0.49175 | 2.0296 | 23.5 | 0.0005151 | 5232 | 3.1802 | 1359 | 0.001797 | 1151
COTTONWOOD 11021578 | COTTONWOOD 1102 | 102931102 | FALSE | 34.3924 | 1.2647 | 28.8549 | 634 | 0.00020101 | 10025 | 8.8434 | 891 | 0.0017959 | 1152
SAN RAFAEL 110863598 | SAN RAFAEL 1108 | 42011108 | FALSE | 2.0549 | 0.55116 | 2.191 | 39.5 | 0.00056492 | 4708 | 3.1787 | 1360 | 0.0017946 | 1153
NARROWS 21022718 | NARROWS 2102 | 153132102 | TRUE | 7.2526 | 0.054399 | 0.25389 | 135.5 | 0.00062506 | 3995 | 3.012 | 1394 | 0.001788 | 1154
CALPELLA 1101345230 | CALPELLA 1101 | 43411101 | FALSE | 2.4377 | 0.18528 | 0.79136 | 46.5 | 0.00026901 | 8675 | 8.2264 | 927 | 0.0017841 | 1155
CRESCENT MILLS 21012232 | CRESCENT MILLS 2101 | 103132101 | FALSE | 20.2771 | 0.79852 | 15.0231 | 389.5 | 0.00024263 | 9231 | 7.7629 | 951 | 0.001781 | 1156
CUYAMA 21013542 | CUYAMA 2101 | 253142101 | FALSE | 12.641 | 1.515 | 3.7079 | 245.3333 | 0.00020146 | 10018 | 10.2377 | 824 | 0.0017791 | 1157
CAMP EVERS 210612840 | CAMP EVERS 2106 | 83622106 | FALSE | 3.9148 | 0.38598 | 4.3007 | 69.3333 | 0.0014518 | 126 | 1.2321 | 2081 | 0.0017784 | 1158
WILLOW CREEK 1103CB | WILLOW CREEK 1103 | 192171103 | FALSE | 2.3945 | 0.70684 | 3.1014 | 40.6667 | 0.00051377 | 5248 | 3.2916 | 1346 | 0.0017755 | 1159
OTTER 1101CB | OTTER 1101 | 182941101 | FALSE | 6.7914 | 0.38373 | 6.7726 | 132 | 0.00049734 | 5421 | 3.4617 | 1321 | 0.0017743 | 1160
CAMP EVERS 210511384 | CAMP EVERS 2105 | 83622105 | FALSE | 5.1848 | 3.3531 | 8.538 | 82.8333 | 0.0015292 | 98 | 1.1588 | 2224 | 0.0017682 | 1161
PEORIA 170449256 | PEORIA 1704 | 163781704 |  | 0.10083 | 0 |  | 1.5 | 0.0004314 | 6105 | 4.1031 | 1244 | 0.0017664 | 1162
CLOVERDALE 1102570 | CLOVERDALE 1102 | 42821102 | FALSE | 21.5411 | 0.93642 | 17.4238 | 409.5 | 0.00020744 | 9920 | 11.723 | 768 | 0.001766 | 1163
HIGGINS 11102408 | HIGGINS 1110 | 152691110 | FALSE | 11.4002 | 0.7609 | 12.161 | 213 | 0.00020773 | 9917 | 9.0625 | 882 | 0.0017577 | 1164
HOPLAND 110180620 | HOPLAND 1101 | 42251101 | FALSE | 5.6192 | 0.38492 | 1.0179 | 104 | 0.00030656 | 7876 | 6.9784 | 998 | 0.0017534 | 1165
MONTE RIO 1113250 | MONTE RIO 1113 | 42811113 | FALSE | 1.2404 | 0.64762 | 1.888 | 23 | 0.0015241 | 101 | 1.15 | 2248 | 0.0017527 | 1166
LOW GAP 1101CB | LOW GAP 1101 | 192411101 | FALSE | 2.1247 | 0.37792 | 2.5026 | 43 | 0.00035226 | 7101 | 4.4828 | 1189 | 0.0017475 | 1167
BRUNSWICK 11042112 | BRUNSWICK 1104 | 152481104 | FALSE | 19.392 | 2.6047 | 21.9966 | 345 | 0.00030812 | 7843 | 5.8885 | 1077 | 0.001745 | 1168
COTTONWOOD 11011610 | COTTONWOOD 1101 | 102931101 | FALSE | 38.259 | 0.84382 | 39.1028 | 711.5 | 0.00013321 | 10852 | 13.6912 | 702 | 0.0017434 | 1169
PEORIA 170587222 | PEORIA 1705 | 163781705 | FALSE | 4.9965 | 0.87213 | 5.6683 | 90.5 | 0.00047193 | 5680 | 3.7263 | 1279 | 0.0017334 | 1170
SILVERADO 2102922022 | SILVERADO 2102 | 43432102 | FALSE | 6.5367 | 0.17486 | 6.7115 | 136.5 | 0.0002043 | 9969 | 11.8997 | 761 | 0.001724 | 1171
CEDAR CREEK 11011362 | CEDAR CREEK 1101 | 103321101 | TRUE | 0.015504 | 0 | 0.015504 | 0.5 | 0.00050379 | 5350 | 3.4011 | 1329 | 0.0017134 | 1172
SHEPHERD 2111327814 | SHEPHERD 2111 | 252062111 | FALSE | 11.1146 | 0.16093 | 10.8319 | 210 | 0.00020048 | 10035 | 12.2943 | 748 | 0.0017124 | 1173
MORGAN HILL 2105XR268 | MORGAN HILL 2105 | 83242105 | FALSE | 7.5199 | 0.32569 | 7.8456 | 143.5 | 0.00024028 | 9283 | 7.2941 | 976 | 0.0017123 | 1174
SALT SPRINGS 21023142 | SALT SPRINGS 2102 | 163692102 | FALSE | 20.0272 | 2.0259 | 19.6348 | 336.8333 | 0.00066996 | 3436 | 2.78 | 1441 | 0.0017109 | 1175
OAKLAND K 1101CR178 | OAKLAND K 1101 | 12101101 | TRUE | 0.33211 | 0.18088 | 0.51299 | 5.8333 | 0.00069973 | 3103 | 2.4986 | 1510 | 0.0017085 | 1176
OAKLAND K 1101CR346 | OAKLAND K 1101 | 12101101 | TRUE | 0.21009 | 0.25534 | 0.46543 | 2.8333 | 0.00083534 | 1678 | 2.0812 | 1614 | 0.0017065 | 1177
PARADISE 110439216 | PARADISE 1104 | 102831104 | FALSE | 3.2113 | 0.98372 | 2.1284 | 54 | 0.00053578 | 4999 | 3.2005 | 1354 | 0.0017042 | 1178
MIRABEL 11022043 | MIRABEL 1102 | 42091102 | FALSE | 0.56062 | 0.72593 | 1.2865 | 10.5 | 0.0012979 | 206 | 1.3264 | 1985 | 0.0017041 | 1179
HOLLISTER 21054048 | HOLLISTER 2105 | 182492105 | FALSE | 28.5588 | 0.76607 | 15.8824 | 558 | 0.00013584 | 10831 | 12.8877 | 730 | 0.0017019 | 1180
TASSAJARA 2112725488 | TASSAJARA 2112 | 14662112 | FALSE | 3.2037 | 1.3173 | 3.4335 | 60 | 0.00073892 | 2615 | 2.4206 | 1530 | 0.0016931 | 1181
BIG BASIN 1102307348 | BIG BASIN 1102 | 82841102 | FALSE | 12.1671 | 0.45787 | 12.6249 | 231 | 0.00055585 | 4805 | 3.154 | 1364 | 0.0016894 | 1182
CURTIS 17026008 | CURTIS 1702 | 163351702 | FALSE | 23.0747 | 1.1229 | 24.1976 | 416.5 | 0.00023396 | 9410 | 9.0665 | 881 | 0.0016843 | 1183
DIAMOND SPRINGS 11071402 | DIAMOND SPRINGS 1107 | 152261107 | FALSE | 44.4339 | 2.0366 | 46.4703 | 804 | 0.00023144 | 9451 | 7.0227 | 997 | 0.0016787 | 1184
CALPELLA 1101931142 | CALPELLA 1101 | 43411101 | FALSE | 7.9644 | 0.22092 | 8.1853 | 159.5 | 0.00020714 | 9927 | 9.0142 | 883 | 0.0016768 | 1185
EL DORADO PH 210136764 | EL DORADO PH 2101 | 152762101 | FALSE | 2.3068 | 0.61757 | 2.9244 | 48 | 0.0005532 | 4833 | 3.0297 | 1389 | 0.0016676 | 1186
SAN RAFAEL 11081262 | SAN RAFAEL 1108 | 42011108 | FALSE | 4.417 | 2.617 | 6.0716 | 68.5 | 0.00090881 | 1194 | 2.1855 | 1582 | 0.001667 | 1187
BRUNSWICK 111061602 | BRUNSWICK 1110 | 152481110 | FALSE | 12.2037 | 4.5181 | 12.3737 | 207 | 0.0005289 | 5088 | 4.1553 | 1234 | 0.0016638 | 1188
ALTO 1125902 | ALTO 1125 | 42031125 | FALSE | 12.1744 | 0.99426 | 13.1686 | 233.3333 | 0.00035056 | 7131 | 4.744 | 1165 | 0.0016614 | 1189
CEDAR CREEK 1101451856 | CEDAR CREEK 1101 | 103321101 | TRUE | 0.054774 | 0 | 0.054774 | 1 | 0.00021175 | 9847 | 7.8307 | 947 | 0.0016581 | 1190
WILLOW CREEK 1101CB | WILLOW CREEK 1101 | 192171101 | TRUE | 0.28791 | 0.070155 | 0.35807 | 3.3333 | 0.0010957 | 482 | 1.5131 | 1837 | 0.0016579 | 1191
LAURELES 111268454 | LAURELES 1112 | 182371112 | FALSE | 11.0043 | 5.8326 | 12.1829 | 235 | 0.00043608 | 6055 | 4.2446 | 1216 | 0.0016578 | 1192
VOLTA 11021504 | VOLTA 1102 | 102541102 | FALSE | 8.3225 | 0.22549 | 8.548 | 169 | 0.00032891 | 7471 | 6.1805 | 1055 | 0.0016559 | 1193
BEN LOMOND 110196738 | BEN LOMOND 1101 | 83041101 | FALSE | 6.7064 | 1.9575 | 8.6638 | 121 | 0.001419 | 134 | 1.186 | 2153 | 0.0016557 | 1194
LAYTONVILLE 1102682 | LAYTONVILLE 1102 | 42681102 | FALSE | 14.9851 | 0.37686 | 15.3619 | 299.5 | 0.00042291 | 6195 | 3.5353 | 1310 | 0.0016497 | 1195
MENLO 1102154024 | MENLO 1102 | 24131102 | FALSE | 2.2624 | 0.56356 | 2.826 | 47.5 | 0.00042096 | 6216 | 3.6804 | 1287 | 0.0016487 | 1196
BEN LOMOND 04015206 | BEN LOMOND 0401 | 83040401 | FALSE | 7.0754 | 0.73698 | 7.8124 | 126.5 | 0.0011827 | 329 | 1.4232 | 1907 | 0.001647 | 1197
HIGGINS 1103789714 | HIGGINS 1103 | 152691103 | FALSE | 27.2026 | 2.4354 | 29.6379 | 488.25 | 0.0002775 | 8479 | 6.3974 | 1039 | 0.0016408 | 1198
COALINGA NO 1 11089080 | COALINGA NO 1 1108 | 252161108 |  | 12.2238 | 0.22521 |  | 213 | 0.00025657 | 8952 | 8.3097 | 921 | 0.0016389 | 1199
CURTIS 1702295684 | CURTIS 1702 | 163351702 | FALSE | 11.3255 | 0.37926 | 11.2107 | 194.8333 | 0.00024359 | 9211 | 7.5176 | 963 | 0.0016367 | 1200
WILLITS 1104934 | WILLITS 1104 | 42661104 | FALSE | 31.0208 | 1.2182 | 32.2389 | 589.5 | 0.00021299 | 9826 | 7.9619 | 937 | 0.0016335 | 1201
HOLLISTER 21064004 | HOLLISTER 2106 | 182492106 | FALSE | 20.4469 | 0.94016 | 8.3517 | 418.5 | 0.00018791 | 10235 | 8.8489 | 889 | 0.0016326 | 1202
WOODSIDE 11011922 | WOODSIDE 1101 | 24251101 | FALSE | 4.8019 | 1.3405 | 5.7382 | 92.5 | 0.00088758 | 1319 | 1.8701 | 1679 | 0.0016323 | 1203
RED BLUFF 110451238 | RED BLUFF 1104 | 103541104 | FALSE | 38.06 | 1.2711 | 39.3309 | 702.5 | 0.00013313 | 10853 | 13.4957 | 710 | 0.0016223 | 1204
FROGTOWN 1702CB | FROGTOWN 1702 | 163451702 | FALSE | 5.2946 | 0.98315 | 1.6279 | 69.8333 | 0.00064485 | 3766 | 3.131 | 1367 | 0.0016222 | 1205
PUEBLO 2102595938 | PUEBLO 2102 | 43292102 |  | 2.8955 | 0.16756 |  | 61.5 | 0.00045298 | 5893 | 4.5589 | 1179 | 0.0016211 | 1206
APPLE HILL 210239544 | APPLE HILL 2102 | 153662102 | FALSE | 24.9708 | 1.5871 | 26.5578 | 353 | 0.00057971 | 4524 | 2.5357 | 1499 | 0.0016145 | 1207
OAKHURST 1101CB | OAKHURST 1101 | 254421101 | TRUE | 0.74525 | 0.036829 | 0.10163 | 19.5 | 0.00076771 | 2286 | 2.795 | 1436 | 0.0016106 | 1208
TASSAJARA 2108437582 | TASSAJARA 2108 | 14662108 | FALSE | 2.3732 | 1.1296 | 0.85883 | 43.5 | 0.00057281 | 4619 | 5.6383 | 1095 | 0.001607 | 1209
SHINGLE SPRINGS 1103CB | SHINGLE SPRINGS 1103 | 153651103 | FALSE | 11.8012 | 0.72355 | 6.3497 | 213.1667 | 0.00035664 | 7032 | 5.0283 | 1139 | 0.0016033 | 1210
BANGOR 11011804 | BANGOR 1101 | 103191101 | FALSE | 31.5918 | 1.5221 | 33.1138 | 602 | 0.00018188 | 10319 | 8.8435 | 890 | 0.0016024 | 1211
BOLINAS 1101504 | BOLINAS 1101 | 42261101 | FALSE | 6.6523 | 0.19154 | 6.8438 | 134.5 | 0.00039352 | 6527 | 4.2085 | 1225 | 0.0015994 | 1212
HARTLEY 11011306 | HARTLEY 1101 | 43211101 | TRUE | 2.8599 | 0.50931 | 0.36461 | 55.5 | 0.00025086 | 9060 | 8.61 | 905 | 0.0015984 | 1213
NAPA 1112943158 | NAPA 1112 | 42021112 | FALSE | 1.623 | 0.07268 | 1.5931 | 30 | 0.00036099 | 6966 | 5.8004 | 1084 | 0.0015881 | 1214
CURTIS 17058110 | CURTIS 1705 | 163351705 | FALSE | 7.9531 | 0.59512 | 8.5482 | 143.8333 | 0.00022729 | 9557 | 7.6917 | 955 | 0.001586 | 1215
SUNOL 1101MR298 | SUNOL 1101 | 14241101 | FALSE | 5.2654 | 0.64618 | 5.7021 | 96 | 0.00031737 | 7675 | 6.2672 | 1046 | 0.0015784 | 1216
HICKS 1116983580 | HICKS 1116 | 83431116 | FALSE | 2.4087 | 0.89316 | 3.2365 | 35.3333 | 0.00037604 | 6747 | 4.9163 | 1146 | 0.0015779 | 1217
SARATOGA 1107899344 | SARATOGA 1107 | 83371107 | FALSE | 9.4937 | 0.49955 | 9.0921 | 180 | 0.00053373 | 5031 | 4.4444 | 1194 | 0.0015753 | 1218
EL DORADO PH 2101668674 | EL DORADO PH 2101 | 152762101 | FALSE | 9.3396 | 1.5616 | 10.9011 | 161.8333 | 0.00064596 | 3756 | 1.9212 | 1661 | 0.0015647 | 1219
FORESTHILL 11011820 | FORESTHILL 1101 | 152181101 | FALSE | 5.7252 | 0.079024 | 5.8042 | 114.5 | 0.00034981 | 7143 | 4.1777 | 1230 | 0.0015625 | 1220
HIGGINS 1104842642 | HIGGINS 1104 | 152691104 | FALSE | 5.6369 | 0.79042 | 6.4273 | 102.5 | 0.00049983 | 5393 | 2.902 | 1411 | 0.0015584 | 1221
BANGOR 1101870548 | BANGOR 1101 | 103191101 | FALSE | 5.0022 | 0.17359 | 5.1697 | 78.5 | 0.00012693 | 10911 | 12.0089 | 759 | 0.0015518 | 1222
ZACA 1102Y54 | ZACA 1102 | 182681102 | FALSE | 34.4264 | 0.32003 | 34.5224 | 636 | 0.00019847 | 10068 | 11.6153 | 777 | 0.0015462 | 1223
FAIRVIEW 2207P150 | FAIRVIEW 2207 | 13432207 | FALSE | 2.2003 | 0.9686 | 3.1546 | 37.8333 | 0.00037855 | 6716 | 3.5435 | 1306 | 0.0015451 | 1224
CAMP EVERS 210411048 | CAMP EVERS 2104 | 83622104 | FALSE | 21.6297 | 3.8896 | 1.2981 | 394.3333 | 0.00099897 | 797 | 1.6829 | 1750 | 0.0015415 | 1225
FORT ROSS 112170288 | FORT ROSS 1121 | 42851121 | FALSE | 23.9733 | 1.0398 | 12.2607 | 477.5 | 0.00039135 | 6551 | 4.5151 | 1184 | 0.0015372 | 1226
MONTE RIO 1112938174 | MONTE RIO 1112 | 42811112 | FALSE | 0.77844 | 0.2443 | 1.0227 | 14.5 | 0.0013366 | 180 | 1.15 | 2248 | 0.0015371 | 1227
LOW GAP 11012094 | LOW GAP 1101 | 192411101 | FALSE | 9.1591 | 0.72278 | 9.8818 | 183.5 | 0.00027003 | 8653 | 5.8588 | 1080 | 0.0015347 | 1228
TEMPLETON 2113R82 | TEMPLETON 2113 | 183052113 | FALSE | 69.2666 | 1.595 | 37.9649 | 1301.5 | 0.00012045 | 10947 | 13.3359 | 718 | 0.0015339 | 1229
LAURELES 1111CB | LAURELES 1111 | 182371111 | FALSE | 8.2109 | 2.2317 | 8.5994 | 159 | 0.00035439 | 7069 | 4.7561 | 1164 | 0.0015319 | 1230
TEMPLETON 2110901690 | TEMPLETON 2110 | 183052110 | FALSE | 39.0632 | 0.79333 | 37.6533 | 758.5 | 0.00012779 | 10904 | 13.125 | 723 | 0.0015289 | 1231
DUNBAR 1103160 | DUNBAR 1103 | 43071103 | TRUE | 4.184 | 0 | 0.19181 | 66 | 0.00054487 | 4912 | 2.3777 | 1536 | 0.0015282 | 1232
BANGOR 11011806 | BANGOR 1101 | 103191101 | FALSE | 3.9853 | 0 | 3.8509 | 81.5 | 0.00015102 | 10692 | 9.3789 | 865 | 0.0015225 | 1233
CAMP EVERS 210637210 | CAMP EVERS 2106 | 83622106 | FALSE | 6.0719 | 1.084 | 5.7 | 118.5 | 0.0010768 | 540 | 1.3446 | 1969 | 0.0015202 | 1234
FROGTOWN 170274648 | FROGTOWN 1702 | 163451702 | TRUE | 5.3658 | 2.4514 | 0.1224 | 85.5 | 0.00046793 | 5717 | 4.6393 | 1173 | 0.0015193 | 1235
JOLON 11027002 | JOLON 1102 | 182981102 | FALSE | 18.7184 | 0.41475 | 8.3135 | 333.5 | 9.8551e-05 | 11055 | 24.8848 | 454 | 0.0015171 | 1236
DUNBAR 1102861496 | DUNBAR 1102 | 43071102 | FALSE | 4.4695 | 0.59047 | 5.0599 | 82.5 | 0.00038859 | 6596 | 4.2008 | 1227 | 0.0015168 | 1237
ALTO 11251226 | ALTO 1125 | 42031125 | FALSE | 7.7062 | 6.1765 | 13.4357 | 124 | 0.00093056 | 1095 | 1.5101 | 1838 | 0.0015115 | 1238
PAUL SWEET 2107774760 | PAUL SWEET 2107 | 83252107 | FALSE | 3.4085 | 0.14706 | 3.5555 | 56.5 | 0.0011658 | 351 | 1.2637 | 2039 | 0.0015107 | 1239
GEYSERVILLE 110135492 | GEYSERVILLE 1101 | 42891101 | FALSE | 21.6714 | 0.9614 | 8.7487 | 423 | 0.00030079 | 8000 | 6.6133 | 1026 | 0.0015042 | 1240
OAKLAND X 1104438648 | OAKLAND X 1104 | 12541104 | TRUE | 0.39064 | 0.044047 | 0.43468 | 3.3333 | 0.0015023 | 110 | 0.87925 | 2501 | 0.0015038 | 1241
CALPELLA 1102144510 | CALPELLA 1102 | 43411102 | FALSE | 3.261 | 0.072491 | 1.518 | 58 | 0.00029845 | 8045 | 7.1234 | 992 | 0.0014962 | 1242
OAKHURST 1102CB | OAKHURST 1102 | 254421102 | FALSE | 2.3871 | 0.54117 | 2.8586 | 40.8333 | 0.00063598 | 3868 | 3.2005 | 1355 | 0.0014954 | 1243
SANTA ROSA A 110432180 | SANTA ROSA A 1104 | 42151104 | FALSE | 2.5388 | 0.84577 | 3.2227 | 48.5 | 0.00060689 | 4217 | 2.5694 | 1492 | 0.0014924 | 1244
JESSUP 11013383 | JESSUP 1101 | 103441101 | FALSE | 1.8752 | 0.70786 | 1.7294 | 36.5 | 0.00045845 | 5822 | 3.5651 | 1299 | 0.0014917 | 1245
CALPELLA 1102789282 | CALPELLA 1102 | 43411102 | FALSE | 1.9857 | 0.1708 | 1.5729 | 39.5 | 0.00028236 | 8366 | 6.8147 | 1010 | 0.0014912 | 1246
REDBUD 110191960 | REDBUD 1101 | 43191101 | FALSE | 7.1621 | 2.9103 | 8.6659 | 124.5 | 0.00039874 | 6467 | 3.5018 | 1316 | 0.0014883 | 1247
PUEBLO 1104105708 | PUEBLO 1104 | 43291104 | FALSE | 19.7895 | 0.77187 | 0.77405 | 368 | 0.00020418 | 9973 | 9.7775 | 845 | 0.001483 | 1248
NARROWS 2101CB | NARROWS 2101 | 153132101 | FALSE | 15.9098 | 0.13731 | 16.0471 | 310.0833 | 0.00015429 | 10654 | 9.747 | 847 | 0.0014826 | 1249
SAN LUIS OBISPO 1101483444 | SAN LUIS OBISPO 1101 | 182631101 | FALSE | 5.0631 | 2.4774 | 2.5384 | 79.3333 | 0.00047817 | 5619 | 3.7784 | 1274 | 0.0014777 | 1250
SAN CARLOS 1104699632 | SAN CARLOS 1104 | 24181104 | FALSE | 3.2391 | 1.7256 | 4.9647 | 60.5 | 0.00033539 | 7377 | 4.3458 | 1204 | 0.0014748 | 1251
DOBBINS 11011808 | DOBBINS 1101 | 153741101 | FALSE | 15.6192 | 0.26203 | 15.8812 | 280.5 | 0.00017248 | 10451 | 8.7072 | 899 | 0.0014726 | 1252
SUNOL 1101MR650 | SUNOL 1101 | 14241101 | FALSE | 2.7264 | 0.60042 | 1.183 | 49.5 | 0.0004316 | 6100 | 3.5633 | 1300 | 0.0014703 | 1253
CLEAR LAKE 11024708 | CLEAR LAKE 1102 | 42141102 |  | 2.8547 | 0.51648 |  | 51 | 0.00030046 | 8009 | 6.0489 | 1068 | 0.0014685 | 1254
GRASS VALLEY 11032180 | GRASS VALLEY 1103 | 152031103 | FALSE | 43.9953 | 1.8668 | 45.8619 | 805 | 0.00017499 | 10422 | 8.4118 | 914 | 0.0014614 | 1255
HIGHLANDS 1102623120 | HIGHLANDS 1102 | 43361102 | FALSE | 7.5267 | 0.32446 | 6.0249 | 129.5 | 0.00028317 | 8349 | 6.0459 | 1070 | 0.00146 | 1256
MENLO 11038512 | MENLO 1103 | 24131103 | FALSE | 16.7392 | 0.88723 | 17.6263 | 296.8333 | 0.00071494 | 2911 | 2.1585 | 1589 | 0.0014596 | 1257
MIWUK 1702667248 | MIWUK 1702 | 163661702 | FALSE | 2.73 | 0.070773 | 2.8008 | 52 | 0.00033051 | 7441 | 3.841 | 1268 | 0.0014588 | 1258
PACIFICA 1104230272 | PACIFICA 1104 | 22811104 | FALSE | 1.135 | 0.48048 | 0.89038 | 18.8333 | 0.00054167 | 4939 | 2.8731 | 1419 | 0.0014584 | 1259
BIG BASIN 1101CB | BIG BASIN 1101 | 82841101 | FALSE | 4.7474 | 0.1485 | 4.8959 | 90.5 | 0.0009098 | 1188 | 1.5552 | 1804 | 0.0014579 | 1260
WOODSIDE 1104456052 | WOODSIDE 1104 | 24251104 | TRUE | 0.64093 | 0.081706 | 0.18495 | 15.5 | 0.0005672 | 4689 | 2.4798 | 1515 | 0.0014562 | 1261
CAMP EVERS 21055188 | CAMP EVERS 2105 | 83622105 | FALSE | 2.0229 | 0.12792 | 2.1508 | 38 | 0.0012526 | 240 | 1.1576 | 2226 | 0.0014531 | 1262
MADISON 2101351038 | MADISON 2101 | 63172101 | FALSE | 14.1051 | 1.2964 | 1.1152 | 280.5 | 0.00031574 | 7703 | 7.6528 | 957 | 0.0014465 | 1263
MIDDLETOWN 1101CB | MIDDLETOWN 1101 | 43141101 | TRUE | 0.26335 | 0.04751 | 0.24238 | 1.8333 | 0.00096653 | 930 | 1.4999 | 1846 | 0.001441 | 1264
WOODSIDE 11012299 | WOODSIDE 1101 | 24251101 | FALSE | 1.8185 | 0.87897 | 2.6975 | 28.5 | 0.00099808 | 800 | 1.5906 | 1793 | 0.0014298 | 1265
SAND CREEK 110345190 | SAND CREEK 1103 | 254601103 | FALSE | 37.5224 | 2.6633 | 40.1856 | 708 | 0.00013126 | 10875 | 10.9386 | 803 | 0.0014269 | 1266
LAS GALLINAS A 110599904 | LAS GALLINAS A 1105 | 42991105 | FALSE | 5.3936 | 0.26577 | 5.6593 | 105.5 | 0.00051863 | 5189 | 2.7131 | 1454 | 0.0014262 | 1267
OILFIELDS 110383158 | OILFIELDS 1103 | 182391103 | FALSE | 19.5814 | 0.47636 | 17.9185 | 352 | 0.00016114 | 10585 | 6.8696 | 1004 | 0.0014203 | 1268
SAN LUIS OBISPO 1107136678 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 13.9574 | 0.57944 | 14.5368 | 277 | 0.00019362 | 10155 | 7.1444 | 990 | 0.0014145 | 1269
DIAMOND SPRINGS 1104CB | DIAMOND SPRINGS 1104 | 152261104 | TRUE | 3.0617 | 0.46309 | 0.55655 | 45.3333 | 0.00066125 | 3559 | 2.4406 | 1523 | 0.0014139 | 1270
BERKELEY F 1103813976 | BERKELEY F 1103 | 12061103 | TRUE | 0.20541 | 0.097792 | 0.21751 | 2.8333 | 0.00065256 | 3674 | 2.1666 | 1588 | 0.0014139 | 1271
MARIPOSA 210237288 | MARIPOSA 2102 | 254452102 | FALSE | 85.0018 | 1.9778 | 86.9794 | 1596 | 0.00012367 | 10934 | 11.3174 | 788 | 0.0014122 | 1272
OAKLAND K 1104CR206 | OAKLAND K 1104 | 12101104 | FALSE | 1.7679 | 1.404 | 3.1719 | 22.3333 | 0.0012608 | 233 | 1.1256 | 2273 | 0.0014089 | 1273
MIRABEL 110238514 | MIRABEL 1102 | 42091102 | FALSE | 10.2891 | 2.9649 | 9.9798 | 196 | 0.00078985 | 2063 | 1.7417 | 1725 | 0.0014081 | 1274
HALF MOON BAY 11038920 | HALF MOON BAY 1103 | 24101103 | TRUE | 0.098254 | 0.067486 | 0.16574 | 2 | 0.0007787 | 2160 | 1.8036 | 1699 | 0.0014044 | 1275
WILLITS 1104627552 | WILLITS 1104 | 42661104 | TRUE | 0.0028409 | 0 | 0.0028409 | 0.5 | 0.00097473 | 894 | 1.4405 | 1893 | 0.0014041 | 1276
SANTA ROSA A 1104642 | SANTA ROSA A 1104 | 42151104 | FALSE | 9.2931 | 0.5355 | 9.8286 | 167.8333 | 0.00038895 | 6588 | 3.5437 | 1305 | 0.0014015 | 1277
SILVERADO 210258626 | SILVERADO 2102 | 43432102 | FALSE | 8.6944 | 0.49591 | 9.177 | 168.5 | 0.00030699 | 7867 | 6.4227 | 1035 | 0.0013995 | 1278
WILLOW CREEK 11033090 | WILLOW CREEK 1103 | 192171103 | FALSE | 10.7388 | 0.44183 | 11.1805 | 217 | 0.00024294 | 9225 | 5.3192 | 1118 | 0.0013985 | 1279
SANTA MARIA 1108M18 | SANTA MARIA 1108 | 182671108 | FALSE | 17.9592 | 0.73389 | 15.2332 | 314.5 | 0.00012668 | 10914 | 8.8126 | 893 | 0.0013939 | 1280
CLARK ROAD 110292622 | CLARK ROAD 1102 | 103091102 | FALSE | 31.1465 | 1.894 | 32.9156 | 574.3333 | 0.00015857 | 10608 | 9.9627 | 836 | 0.0013786 | 1281
UKIAH 1114844294 | UKIAH 1114 | 42771114 | FALSE | 6.0895 | 0.21843 | 2.0474 | 115.5 | 0.00019544 | 10121 | 8.4963 | 908 | 0.0013771 | 1282
PINECREST 0401CB | PINECREST 0401 | 163160401 | TRUE | 0.013798 | 0 | 0.013798 | 0.33333 | 0.0010625 | 578 | 1.2952 | 2008 | 0.0013761 | 1283
WILLOW CREEK 1103181562 | WILLOW CREEK 1103 | 192171103 | TRUE | 0.002841 | 0 | 0.002841 | 0.33333 | 0.00090925 | 1193 | 1.5131 | 1837 | 0.0013758 | 1284
ROB ROY 2104974520 | ROB ROY 2104 | 83692104 | FALSE | 17.1008 | 1.6995 | 6.6088 | 321 | 0.00095968 | 964 | 1.5481 | 1810 | 0.0013741 | 1285
SANTA MARIA 1108M80 | SANTA MARIA 1108 | 182671108 | FALSE | 58.1351 | 2.1162 | 60.2511 | 1123 | 0.00011953 | 10955 | 11.5972 | 779 | 0.0013706 | 1286
FITCH MOUNTAIN 11134566 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 17.3318 | 1.7703 | 12.2001 | 347 | 0.00039443 | 6516 | 4.6417 | 1172 | 0.0013701 | 1287
SAN RAMON 2106CB | SAN RAMON 2106 | 14232106 | FALSE | 2.174 | 0.28224 | 0.72489 | 28.25 | 0.0010822 | 521 | 1.7417 | 1724 | 0.0013688 | 1288
BUELLTON 1101Y36 | BUELLTON 1101 | 183041101 | FALSE | 45.0127 | 2.4569 | 37.5591 | 855 | 0.00019668 | 10097 | 7.4625 | 965 | 0.0013618 | 1289
MONTE RIO 11135020 | MONTE RIO 1113 | 42811113 | FALSE | 4.4862 | 2.7197 | 7.2059 | 70.25 | 0.0011771 | 334 | 1.1565 | 2228 | 0.001358 | 1290
MIWUK 1701CB | MIWUK 1701 | 163661701 | FALSE | 4.5688 | 0.52059 | 5.0893 | 77 | 0.00069149 | 3201 | 2.1421 | 1593 | 0.0013549 | 1291
COVELO 1101562360 | COVELO 1101 | 43061101 |  | 38.3507 | 2.6147 |  | 680 | 0.00018308 | 10303 | 13.6134 | 707 | 0.0013495 | 1292
CALPELLA 11011204 | CALPELLA 1101 | 43411101 | TRUE | 2.0208 | 0.16621 | 0.50059 | 34.8333 | 0.00043254 | 6086 | 3.8079 | 1271 | 0.0013479 | 1293
SHADY GLEN 1101100230 | SHADY GLEN 1101 | 152431101 |  | 1.1265 | 0.72568 |  | 14.5 | 0.00074618 | 2534 | 1.7837 | 1707 | 0.0013473 | 1294
ALTO 1124207690 | ALTO 1124 | 42031124 | FALSE | 0.5297 | 0.44756 | 0.96874 | 8.5 | 0.0011993 | 295 | 1.1785 | 2166 | 0.0013445 | 1295
PAUL SWEET 21065178 | PAUL SWEET 2106 | 83252106 | FALSE | 9.3826 | 1.3097 | 4.051 | 170.3333 | 0.0010877 | 501 | 1.2353 | 2077 | 0.0013409 | 1296
SHEPHERD 2111688294 | SHEPHERD 2111 | 252062111 | TRUE | 0.015137 | 0 | 0.015137 | 0.5 | 0.00080643 | 1925 | 1.6583 | 1765 | 0.0013373 | 1297
JESSUP 110296554 | JESSUP 1102 | 103441102 | FALSE | 14.7579 | 1.6504 | 7.7694 | 258 | 0.00017514 | 10419 | 9.6379 | 852 | 0.0013357 | 1298
MILPITAS 1109903328 | MILPITAS 1109 | 82831109 | FALSE | 20.0381 | 0.965 | 19.8719 | 381.5 | 0.00013159 | 10870 | 12.1756 | 753 | 0.0013356 | 1299
MIRABEL 1102503294 | MIRABEL 1102 | 42091102 | FALSE | 2.3183 | 1.8132 | 4.1315 | 51.5 | 0.00096571 | 932 | 1.3982 | 1930 | 0.0013338 | 1300
CAMP EVERS 210310946 | CAMP EVERS 2103 | 83622103 | FALSE | 4.2358 | 0.72082 | 4.8603 | 74 | 0.0010868 | 506 | 1.2256 | 2092 | 0.0013322 | 1301
GARBERVILLE 11016014 | GARBERVILLE 1101 | 192221101 |  | 51.5395 | 1.1379 |  | 887 | 0.00016121 | 10584 | 8.3407 | 919 | 0.0013265 | 1302
CAMP EVERS 210612760 | CAMP EVERS 2106 | 83622106 | FALSE | 26.2217 | 2.2781 | 28.4997 | 472.5 | 0.0010083 | 767 | 1.3424 | 1973 | 0.0013237 | 1303
CAMP EVERS 210584166 | CAMP EVERS 2105 | 83622105 | FALSE | 8.5958 | 1.5488 | 9.209 | 140.8333 | 0.0011546 | 367 | 1.1567 | 2227 | 0.0013193 | 1304
LOS GATOS 1106CB | LOS GATOS 1106 | 82021106 | TRUE | 0.72718 | 0.27306 | 0.18021 | 9.5 | 0.0010283 | 696 | 1.2896 | 2019 | 0.0013189 | 1305
SUMMIT 110148632 | SUMMIT 1101 | 152591101 | FALSE | 2.7379 | 1.1458 | 3.8837 | 47.5 | 0.00063583 | 3870 | 2.0747 | 1616 | 0.0013176 | 1306
MONTE RIO 1111969182 | MONTE RIO 1111 | 42811111 | FALSE | 7.3937 | 2.0719 | 5.5818 | 141.8333 | 0.00097279 | 908 | 1.4138 | 1917 | 0.0013163 | 1307
JOLON 1102CB | JOLON 1102 | 182981102 | FALSE | 24.0982 | 0.50301 | 23.4 | 443 | 0.00011296 | 10998 | 9.3836 | 864 | 0.0013131 | 1308
FITCH MOUNTAIN 111324918 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 28.0666 | 0.48501 | 28.3334 | 462.5 | 0.00056435 | 4713 | 2.5063 | 1509 | 0.0013119 | 1309
KERCKHOFF 1101R353 | KERCKHOFF 1101 | 252561101 | FALSE | 13.7426 | 0.49139 | 14.234 | 270 | 6.4874e-05 | 11118 | 18.8739 | 576 | 0.0013114 | 1310
ELK CREEK 11012004 | ELK CREEK 1101 | 102781101 | FALSE | 54.0803 | 0.9187 | 21.9279 | 1028 | 9.1548e-05 | 11078 | 18.8938 | 573 | 0.001311 | 1311
MIDDLETOWN 1102414 | MIDDLETOWN 1102 | 43141102 | FALSE | 12.041 | 2.7229 | 4.9572 | 221.5 | 0.00030133 | 7983 | 8.2477 | 925 | 0.0013099 | 1312
TASSAJARA 210812712 | TASSAJARA 2108 | 14662108 | FALSE | 3.3315 | 1.7643 | 0.78743 | 60.25 | 0.00070933 | 2985 | 1.7729 | 1710 | 0.0013095 | 1313
BIG BASIN 11025066 | BIG BASIN 1102 | 82841102 | FALSE | 9.5221 | 0.28843 | 9.8105 | 182.3333 | 0.0011176 | 436 | 1.1705 | 2193 | 0.0013052 | 1314
FORESTHILL 110175340 | FORESTHILL 1101 | 152181101 | FALSE | 4.8099 | 0.29815 | 5.108 | 88 | 0.00053086 | 5061 | 2.5359 | 1498 | 0.0013048 | 1315
PLACERVILLE 1112566624 | PLACERVILLE 1112 | 153081112 | FALSE | 5.7028 | 1.3639 | 6.5832 | 99.6667 | 0.00049503 | 5443 | 2.858 | 1422 | 0.0013045 | 1316
CAMP EVERS 210355638 | CAMP EVERS 2103 | 83622103 | FALSE | 3.4934 | 1.4824 | 1.5834 | 57.5 | 0.0010069 | 770 | 1.2552 | 2051 | 0.001303 | 1317
PACIFICA 1103885952 | PACIFICA 1103 | 22811103 | TRUE | 0.19264 | 0.077244 | 0.18083 | 5 | 0.00078538 | 2097 | 1.6583 | 1765 | 0.0013024 | 1318
CAMP EVERS 210311046 | CAMP EVERS 2103 | 83622103 | FALSE | 16.0708 | 2.6192 | 18.69 | 300 | 0.0010518 | 616 | 1.2422 | 2071 | 0.0013011 | 1319
BRUNSWICK 1103164092 | BRUNSWICK 1103 | 152481103 | TRUE | 0.095658 | 0.045258 | 0.095721 | 0.83333 | 0.0010293 | 691 | 1.2517 | 2056 | 0.0012964 | 1320
SPAULDING 1101578852 | SPAULDING 1101 | 152251101 | FALSE | 24.0753 | 1.3855 | 21.5767 | 484.5 | 0.00030983 | 7807 | 4.8573 | 1153 | 0.0012916 | 1321
WOODACRE 11021280 | WOODACRE 1102 | 43021102 | FALSE | 8.684 | 5.9862 | 14.384 | 147.5 | 0.00059231 | 4388 | 2.2117 | 1575 | 0.0012843 | 1322
KING CITY 1106958502 | KING CITY 1106 | 182031106 |  | 12.0027 | 0.38003 |  | 256 | 8.3766e-05 | 11099 | 13.5439 | 709 | 0.0012824 | 1323
GARBERVILLE 11011770 | GARBERVILLE 1101 | 192221101 | FALSE | 8.5834 | 0.95715 | 9.5406 | 170 | 0.00049144 | 5480 | 2.8178 | 1431 | 0.001277 | 1324
FORT SEWARD 1121CB | FORT SEWARD 1121 | 192321121 | FALSE | 31.9691 | 1.7937 | 10.1202 | 610 | 0.00021158 | 9850 | 6.5492 | 1031 | 0.0012733 | 1325
OAKLAND K 1102CB | OAKLAND K 1102 | 12101102 | FALSE | 0.88681 | 0.064029 | 0.95083 | 13.5 | 0.00076989 | 2258 | 1.7847 | 1706 | 0.0012721 | 1326
ALTO 1124870444 | ALTO 1124 | 42031124 | FALSE | 2.9665 | 1.8956 | 4.8181 | 44.8333 | 0.0010435 | 638 | 1.1741 | 2177 | 0.0012714 | 1327
HIGHLANDS 11034630 | HIGHLANDS 1103 | 43361103 | FALSE | 3.4343 | 1.1834 | 0.7233 | 59.5 | 0.00037896 | 6711 | 3.539 | 1309 | 0.0012713 | 1328
ALHAMBRA 11058302 | ALHAMBRA 1105 | 14101105 | FALSE | 8.1238 | 0.72391 | 8.8476 | 152 | 0.000279 | 8445 | 4.1502 | 1236 | 0.0012681 | 1329
MORAGA 110183424 | MORAGA 1101 | 13801101 | FALSE | 1.6431 | 0 | 1.4427 | 32.5 | 0.00084616 | 1604 | 1.4301 | 1901 | 0.0012663 | 1330
SONOMA 110478372 | SONOMA 1104 | 42721104 | FALSE | 16.7739 | 1.7726 | 17.9747 | 331.5 | 0.00027796 | 8470 | 4.8724 | 1151 | 0.0012653 | 1331
MONTE RIO 1112120 | MONTE RIO 1112 | 42811112 | FALSE | 5.9505 | 0.60416 | 6.2009 | 109.5 | 0.00076754 | 2288 | 1.6703 | 1757 | 0.0012646 | 1332
FROGTOWN 17028482 | FROGTOWN 1702 | 163451702 | FALSE | 14.7536 | 0.73244 | 15.486 | 300 | 0.00015176 | 10679 | 7.3176 | 973 | 0.0012644 | 1333
SANTA ROSA A 1104716 | SANTA ROSA A 1104 | 42151104 | FALSE | 8.898 | 0.26496 | 9.163 | 162.3333 | 0.00025673 | 8949 | 5.0563 | 1136 | 0.0012604 | 1334
SUMMIT 110186658 | SUMMIT 1101 | 152591101 | FALSE | 0.67221 | 0.078956 | 0.66616 | 10.5 | 0.00064169 | 3807 | 1.8762 | 1677 | 0.0012597 | 1335
NAPA 11121302 | NAPA 1112 | 42021112 | FALSE | 21.0914 | 2.1757 | 8.174 | 381.5 | 0.00034261 | 7265 | 6.5667 | 1028 | 0.0012592 | 1336
SAN RAMON 2103MR279 | SAN RAMON 2103 | 14232103 | TRUE | 0.20088 | 0.044233 | 0.0028409 | 3.8333 | 0.0011412 | 383 | 1.1879 | 2146 | 0.0012585 | 1337
OTTER 11022002 | OTTER 1102 | 182941102 | FALSE | 8.5069 | 0.80871 | 9.3156 | 164 | 0.00032359 | 7565 | 4.7828 | 1162 | 0.0012566 | 1338
CAMP EVERS 210312990 | CAMP EVERS 2103 | 83622103 | FALSE | 13.1801 | 2.4425 | 15.6225 | 241 | 0.0010214 | 717 | 1.2463 | 2063 | 0.0012558 | 1339
PEORIA 17013186 | PEORIA 1701 | 163781701 | FALSE | 9.7719 | 2.3096 | 12.0814 | 171 | 0.00037222 | 6800 | 3.3497 | 1336 | 0.0012542 | 1340
PUEBLO 1104968601 | PUEBLO 1104 | 43291104 | TRUE | 0.0076055 | 0 | 0.0076054 | 1 | 0.00064274 | 3792 | 1.9488 | 1657 | 0.0012526 | 1341
PEORIA 1705CB | PEORIA 1705 | 163781705 | FALSE | 7.1267 | 0.12132 | 7.248 | 141 | 0.00018283 | 10305 | 6.7896 | 1013 | 0.001252 | 1342
CAMP EVERS 210611044 | CAMP EVERS 2106 | 83622106 | FALSE | 12.8113 | 5.9297 | 9.4877 | 210.8333 | 0.0014357 | 130 | 0.78941 | 2569 | 0.0012499 | 1343
HALF MOON BAY 11012500 | HALF MOON BAY 1101 | 24101101 | FALSE | 6.8432 | 1.1919 | 6.96 | 137 | 0.00081936 | 1825 | 1.7489 | 1720 | 0.0012495 | 1344
MONTE RIO 11131067 | MONTE RIO 1113 | 42811113 | FALSE | 0.81175 | 0.6738 | 1.4855 | 16.3333 | 0.0010864 | 508 | 1.15 | 2249 | 0.0012494 | 1345
SONOMA 1106746130 | SONOMA 1106 | 42721106 | FALSE | 0.84188 | 0.049851 | 0.79434 | 17.5 | 0.00041894 | 6234 | 2.953 | 1400 | 0.0012434 | 1346
ROSSMOOR 1106CB | ROSSMOOR 1106 | 14161106 | FALSE | 4.8226 | 3.2843 | 2.3677 | 77.6429 | 0.00071375 | 2927 | 1.8159 | 1695 | 0.0012426 | 1347
MONTE RIO 1113180 | MONTE RIO 1113 | 42811113 | FALSE | 1.9635 | 0.91886 | 2.8823 | 34.5 | 0.0010778 | 537 | 1.1521 | 2239 | 0.0012414 | 1348
GREENBRAE 1103718674 | GREENBRAE 1103 | 43091103 | FALSE | 1.1549 | 0.80583 | 1.3917 | 23.5 | 0.00059817 | 4322 | 2.0877 | 1610 | 0.0012414 | 1349
ELK CREEK 110193504 | ELK CREEK 1101 | 102781101 | FALSE | 2.4653 | 0.092649 | 2.0322 | 36 | 0.00011841 | 10962 | 17.1057 | 620 | 0.0012407 | 1350
MONTE RIO 1113524 | MONTE RIO 1113 | 42811113 | FALSE | 6.215 | 4.9875 | 11.2025 | 119 | 0.0010546 | 602 | 1.1677 | 2202 | 0.0012395 | 1351
GANSNER 110137550 | GANSNER 1101 | 103021101 | TRUE | 3.2876 | 0.50282 | 0.26926 | 61 | 0.00025374 | 9003 | 3.3246 | 1338 | 0.0012388 | 1352
DUNBAR 1103831696 | DUNBAR 1103 | 43071103 | FALSE | 9.1137 | 0.63256 | 6.3181 | 161.5 | 0.00032984 | 7451 | 3.709 | 1281 | 0.0012382 | 1353
MONTE RIO 1112212 | MONTE RIO 1112 | 42811112 | FALSE | 1.3866 | 1.1185 | 2.5051 | 23.5 | 0.0010751 | 545 | 1.15 | 2248 | 0.0012363 | 1354
PEORIA 170492888 | PEORIA 1704 | 163781704 | TRUE | 0.44994 | 0 | 0.23321 | 7.5 | 0.00026782 | 8704 | 3.5216 | 1312 | 0.0012354 | 1355
SAN RAFAEL 11081250 | SAN RAFAEL 1108 | 42011108 | FALSE | 3.5628 | 0.11684 | 3.6796 | 70.5 | 0.00038582 | 6633 | 3.2456 | 1350 | 0.0012333 | 1356
MERCED FALLS 110238748 | MERCED FALLS 1102 | 252811102 | FALSE | 15.3251 | 0.73497 | 16.06 | 279 | 0.0001865 | 10255 | 6.4099 | 1037 | 0.0012316 | 1357
CAMP EVERS 210511004 | CAMP EVERS 2105 | 83622105 | FALSE | 4.3276 | 2.1018 | 6.4293 | 74.5 | 0.0010671 | 565 | 1.1588 | 2223 | 0.0012316 | 1358
CLOVERDALE 1101474708 | CLOVERDALE 1101 | 42821101 | TRUE | 0.86455 | 0.3362 | 0.19178 | 15 | 0.0005045 | 5340 | 3.1493 | 1365 | 0.0012308 | 1359
MC KEE 1111711900 | MC KEE 1111 | 83531111 | FALSE | 12.448 | 2.53 | 9.8062 | 229.6667 | 0.00025667 | 8950 | 7.1593 | 989 | 0.0012296 | 1360
BIG BASIN 1102243760 | BIG BASIN 1102 | 82841102 | FALSE | 5.4334 | 0.20877 | 5.6422 | 97.3333 | 0.00095752 | 973 | 1.294 | 2010 | 0.0012218 | 1361
PERRY 110179696 | PERRY 1101 | 183071101 | FALSE | 29.3591 | 0.72142 | 30.0804 | 569 | 0.00011535 | 10982 | 12.5928 | 738 | 0.0012193 | 1362
FOOTHILL 1102CB | FOOTHILL 1102 | 182951102 | FALSE | 9.7591 | 0.96424 | 8.2658 | 193.5 | 0.00033207 | 7422 | 5.1237 | 1130 | 0.0012189 | 1363
TRIDAM POWERHOUSE 2101CB | TRIDAM POWERHOUSE 2101 | 168152101 | TRUE | 0.050742 | 0 | 0.050742 | 3 | 0.0002851 | 8305 | 4.2725 | 1212 | 0.0012181 | 1364
STILLWATER 11021644 | STILLWATER 1102 | 103561102 | FALSE | 22.5956 | 1.7488 | 24.3443 | 407 | 0.00021193 | 9845 | 6.016 | 1072 | 0.0012164 | 1365
OLETA 1101CB | OLETA 1101 | 163541101 | TRUE | 0.097289 | 0 | 0.058358 | 0.75 | 0.0010567 | 596 | 1.15 | 2248 | 0.0012153 | 1366
SAN RAMON 2107MR441 | SAN RAMON 2107 | 14232107 | TRUE | 0.20781 | 0.11799 | 0.018482 | 7.3333 | 0.00090045 | 1230 | 1.2469 | 2062 | 0.0012097 | 1367
ALTO 11221260 | ALTO 1122 | 42031122 | FALSE | 2.9958 | 2.8275 | 5.6293 | 48 | 0.00093558 | 1071 | 1.2272 | 2086 | 0.0012094 | 1368
PLACERVILLE 1110421358 | PLACERVILLE 1110 | 153081110 | FALSE | 14.808 | 0.80224 | 15.6102 | 280 | 0.00027772 | 8473 | 4.2099 | 1224 | 0.0012082 | 1369
MOLINO 1102509516 | MOLINO 1102 | 42571102 | TRUE | 0.27972 | 0.096036 | 0.37576 | 5.5 | 0.00088134 | 1357 | 1.3679 | 1952 | 0.0012055 | 1370
MONTE RIO 111137520 | MONTE RIO 1111 | 42811111 | FALSE | 5.6124 | 0.46919 | 2.5386 | 115.8333 | 0.00058614 | 4463 | 2.657 | 1469 | 0.0012049 | 1371
SHEPHERD 2111443696 | SHEPHERD 2111 | 252062111 |  | 14.3119 | 0.40353 |  | 278 | 0.00015067 | 10699 | 6.2743 | 1045 | 0.0011998 | 1372
OAKHURST 1102204618 | OAKHURST 1102 | 254421102 |  | 0.24524 | 0 |  | 4.5 | 0.00077215 | 2235 | 1.2543 | 2053 | 0.0011911 | 1373
PURISIMA 1101CB | PURISIMA 1101 | 182971101 | FALSE | 4.6657 | 1.3165 | 3.7103 | 88 | 0.00036481 | 6922 | 3.4925 | 1317 | 0.0011883 | 1374
GEYSERVILLE 1101482 | GEYSERVILLE 1101 | 42891101 | TRUE | 3.7239 | 0.52131 | 0.20457 | 70.5 | 0.00037691 | 6735 | 2.5823 | 1490 | 0.0011879 | 1375
SHINGLE SPRINGS 210519522 | SHINGLE SPRINGS 2105 | 153652105 | FALSE | 10.3112 | 0.72901 | 10.3277 | 177.5 | 0.00020537 | 9955 | 6.3768 | 1040 | 0.0011865 | 1376
MONTE RIO 1111240 | MONTE RIO 1111 | 42811111 | FALSE | 5.799 | 1.9804 | 4.0885 | 98 | 0.00096292 | 942 | 1.2197 | 2103 | 0.0011843 | 1377
ROB ROY 2105439972 | ROB ROY 2105 | 83692105 | FALSE | 8.7586 | 0.15171 | 8.9103 | 164 | 0.0010124 | 755 | 1.1639 | 2212 | 0.0011797 | 1378
RED BLUFF 110176020 | RED BLUFF 1101 | 103541101 | FALSE | 14.5167 | 0.40191 | 8.8922 | 277 | 0.00021671 | 9754 | 6.168 | 1057 | 0.0011793 | 1379
COARSEGOLD 21046210 | COARSEGOLD 2104 | 254432104 | FALSE | 10.7056 | 0.025783 | 10.7313 | 229.5 | 0.00010918 | 11019 | 9.1363 | 877 | 0.0011778 | 1380
HALF MOON BAY 110329454 | HALF MOON BAY 1103 | 24101103 | FALSE | 4.4519 | 0.27028 | 4.7222 | 89 | 0.00030847 | 7831 | 4.5059 | 1186 | 0.0011739 | 1381
BRIDGEVILLE 110137484 | BRIDGEVILLE 1101 | 192461101 | FALSE | 10.2354 | 0.28078 | 8.2199 | 185 | 0.00026427 | 8768 | 4.4644 | 1193 | 0.0011722 | 1382
MONTE RIO 1113652 | MONTE RIO 1113 | 42811113 | FALSE | 1.5908 | 0.92827 | 2.5191 | 30.5 | 0.0010102 | 761 | 1.1714 | 2188 | 0.0011714 | 1383
ROB ROY 2104588930 | ROB ROY 2104 | 83692104 | FALSE | 4.685 | 0.25457 | 4.9396 | 93.5 | 0.00095902 | 966 | 1.2234 | 2095 | 0.0011709 | 1384
ZACA 1101CB | ZACA 1101 | 182681101 | FALSE | 11.0496 | 0.12361 | 7.2265 | 211 | 0.00025825 | 8919 | 6.2612 | 1047 | 0.0011698 | 1385
MENLO 11038982 | MENLO 1103 | 24131103 | FALSE | 4.6849 | 0.47473 | 5.1593 | 87 | 0.0009423 | 1045 | 1.2449 | 2066 | 0.0011682 | 1386
VIEJO 2202CB | VIEJO 2202 | 182852202 | FALSE | 2.1375 | 0 | 2.1375 | 40.6667 | 0.0010154 | 745 | 1.15 | 2248 | 0.0011677 | 1387
CORNING 110182846 | CORNING 1101 | 103331101 | FALSE | 5.0703 | 0.64769 | 5.3106 | 99.5 | 0.00027335 | 8575 | 4.3405 | 1207 | 0.0011632 | 1388
WOODACRE 1101CB | WOODACRE 1101 | 43021101 | FALSE | 2.7424 | 0.88789 | 3.3519 | 48 | 0.00076698 | 2296 | 1.4883 | 1857 | 0.0011624 | 1389
MIRABEL 1101774276 | MIRABEL 1101 | 42091101 | FALSE | 4.9633 | 0.5514 | 4.1786 | 92.5 | 0.00067142 | 3422 | 1.7284 | 1733 | 0.0011617 | 1390
MIWUK 170153038 | MIWUK 1701 | 163661701 | FALSE | 6.6246 | 2.2059 | 8.8282 | 114 | 0.00048834 | 5510 | 2.5266 | 1502 | 0.0011574 | 1391
PHILO 110137222 | PHILO 1101 | 42601101 | FALSE | 25.3217 | 0.72985 | 26.0514 | 485.5 | 0.00020026 | 10038 | 6.6781 | 1019 | 0.0011566 | 1392
LAYTONVILLE 1102141962 | LAYTONVILLE 1102 | 42681102 | FALSE | 5.0711 | 0.025321 | 5.0965 | 98 | 0.0003822 | 6673 | 3.0473 | 1385 | 0.0011565 | 1393
GIRVAN 1102296428 | GIRVAN 1102 | 103401102 | FALSE | 3.3193 | 0.085545 | 1.7068 | 68.5 | 0.00068819 | 3245 | 1.7712 | 1712 | 0.0011564 | 1394
OAKLAND K 1104CR204 | OAKLAND K 1104 | 12101104 | FALSE | 4.008 | 2.6271 | 6.6351 | 60.6667 | 0.0010047 | 777 | 1.15 | 2248 | 0.0011554 | 1395
SNEATH LANE 1101CB | SNEATH LANE 1101 | 22721101 | TRUE | 0.9939 | 0.71601 | 0.44955 | 16.0833 | 0.00093034 | 1096 | 1.2215 | 2101 | 0.0011533 | 1396
ELK CREEK 11012228 | ELK CREEK 1101 | 102781101 | FALSE | 10.5647 | 1.356 | 3.0229 | 200.5 | 0.00019273 | 10169 | 6.701 | 1018 | 0.0011514 | 1397
NORTH BRANCH 110113496 | NORTH BRANCH 1101 | 163231101 | FALSE | 4.125 | 1.4224 | 1.5159 | 70 | 0.00040403 | 6411 | 3.3031 | 1343 | 0.0011506 | 1398
WOODACRE 11011456 | WOODACRE 1101 | 43021101 | FALSE | 3.8237 | 0.51761 | 4.3413 | 80.5 | 0.00061775 | 4074 | 1.9727 | 1648 | 0.0011494 | 1399
MIDDLETOWN 1102998 | MIDDLETOWN 1102 | 43141102 | FALSE | 17.0251 | 3.1903 | 17.3308 | 314.5 | 0.00019494 | 10132 | 8.6615 | 901 | 0.001149 | 1400
RINCON 1103CB | RINCON 1103 | 43321103 | FALSE | 3.7556 | 0.32983 | 3.4382 | 66.6667 | 0.00058393 | 4486 | 2.6278 | 1477 | 0.0011481 | 1401
TEMPLETON 2108A64 | TEMPLETON 2108 | 183052108 | FALSE | 11.7217 | 2.2022 | 2.7859 | 232 | 0.00033345 | 7403 | 2.8549 | 1423 | 0.0011472 | 1402
MIRABEL 1102976908 | MIRABEL 1102 | 42091102 | FALSE | 1.1151 | 0.048932 | 1.1641 | 20.5 | 0.00071105 | 2964 | 1.5946 | 1789 | 0.0011459 | 1403
WOODSIDE 11018912 | WOODSIDE 1101 | 24251101 | FALSE | 3.8561 | 0.64602 | 4.2275 | 75.5 | 0.00079716 | 1992 | 1.4589 | 1880 | 0.0011458 | 1404
ALTO 1122591122 | ALTO 1122 | 42031122 | FALSE | 0.46727 | 0.38924 | 0.84519 | 9 | 0.00096064 | 958 | 1.227 | 2087 | 0.0011434 | 1405
MONTE RIO 1113202 | MONTE RIO 1113 | 42811113 | FALSE | 5.27 | 0.81549 | 6.0854 | 100 | 0.00072996 | 2729 | 1.5396 | 1816 | 0.0011425 | 1406
SILVERADO 2105764650 | SILVERADO 2105 | 43432105 |  | 0.5717 | 0.01457 |  | 12.5 | 0.00066509 | 3498 | 5.7567 | 1089 | 0.0011424 | 1407
LOW GAP 1101750090 | LOW GAP 1101 | 192411101 | FALSE | 7.7313 | 0.55462 | 6.3985 | 151 | 0.00045633 | 5853 | 2.4058 | 1532 | 0.001137 | 1408
MERCED FALLS 11029470 | MERCED FALLS 1102 | 252811102 | FALSE | 22.7597 | 0.85549 | 23.6151 | 425 | 0.00020872 | 9900 | 5.2118 | 1122 | 0.0011362 | 1409
OLETA 1102186326 | OLETA 1102 | 163541102 | FALSE | 12.6954 | 0.51847 | 11.8 | 236 | 0.00024123 | 9265 | 6.8589 | 1005 | 0.001136 | 1410
DRUM 11011602 | DRUM 1101 | 152321101 | FALSE | 16.2032 | 1.2464 | 17.4495 | 334 | 0.00041114 | 6321 | 3.0499 | 1384 | 0.0011339 | 1411
MONTE RIO 1111256 | MONTE RIO 1111 | 42811111 | FALSE | 7.2549 | 3.0544 | 10.3093 | 147.1667 | 0.00093156 | 1090 | 1.1943 | 2139 | 0.0011331 | 1412
BIG BASIN 110296986 | BIG BASIN 1102 | 82841102 | FALSE | 4.9192 | 0.58896 | 5.5081 | 90 | 0.00096597 | 931 | 1.1707 | 2191 | 0.0011281 | 1413
BOLINAS 1101CB | BOLINAS 1101 | 42261101 | FALSE | 2.1741 | 0.19818 | 2.2996 | 39.5 | 0.00035085 | 7124 | 2.8974 | 1413 | 0.0011272 | 1414
GREEN VALLEY 210111054 | GREEN VALLEY 2101 | 83192101 | FALSE | 25.1378 | 2.2329 | 25.3357 | 483 | 0.00074477 | 2553 | 1.471 | 1868 | 0.0011265 | 1415
COARSEGOLD 21045310 | COARSEGOLD 2104 | 254432104 | FALSE | 27.8334 | 1.1491 | 28.9825 | 509.5 | 0.00015262 | 10672 | 8.416 | 913 | 0.001126 | 1416
SANTA YNEZ 1104Y66 | SANTA YNEZ 1104 | 182721104 | FALSE | 18.5339 | 0.45357 | 16.7168 | 356.5 | 0.00013293 | 10858 | 9.0885 | 879 | 0.0011255 | 1417
MIWUK 170247143 | MIWUK 1702 | 163661702 | FALSE | 4.8556 | 0.97794 | 5.8335 | 73.8333 | 0.00055544 | 4813 | 2.4454 | 1522 | 0.0011229 | 1418
NARROWS 21052228 | NARROWS 2105 | 153132105 | FALSE | 20.9619 | 1.4355 | 21.7541 | 394 | 0.00019032 | 10209 | 5.4264 | 1108 | 0.0011214 | 1419
SHADY GLEN 1101941844 | SHADY GLEN 1101 | 152431101 |  | 0.89102 | 0.12701 |  | 18.5 | 0.00052364 | 5145 | 1.9912 | 1637 | 0.0011193 | 1420
LAKEWOOD 2107396264 | LAKEWOOD 2107 | 13532107 | FALSE | 6.29 | 2.2849 | 6.2465 | 115 | 0.0005483 | 4875 | 2.1844 | 1583 | 0.0011189 | 1421
ROSSMOOR 110639424 | ROSSMOOR 1106 | 14161106 | FALSE | 2.5077 | 1.6206 | 1.0418 | 40.3333 | 0.0006151 | 4104 | 2.0837 | 1613 | 0.0011186 | 1422
HALF MOON BAY 1103695411 | HALF MOON BAY 1103 | 24101103 | FALSE | 8.3247 | 3.2547 | 11.5794 | 138.3333 | 0.00063052 | 3935 | 1.9105 | 1665 | 0.001118 | 1423
PEORIA 1704CB | PEORIA 1704 | 163781704 | FALSE | 8.6964 | 0.043341 | 7.9103 | 141.5 | 0.00018128 | 10334 | 6.5276 | 1033 | 0.0011148 | 1424
CAMP EVERS 210694770 | CAMP EVERS 2106 | 83622106 | FALSE | 3.9849 | 1.4768 | 3.2635 | 69.8333 | 0.0012903 | 211 | 0.70673 | 2636 | 0.0011122 | 1425
SAN CARLOS 1103586832 | SAN CARLOS 1103 | 24181103 | FALSE | 4.1807 | 2.6516 | 6.3089 | 68.8333 | 0.00054482 | 4914 | 1.9821 | 1644 | 0.0011085 | 1426
CALISTOGA 110266730 | CALISTOGA 1102 | 42711102 | FALSE | 1.0675 | 0 | 1.0675 | 22.5 | 0.00030531 | 7904 | 3.7029 | 1282 | 0.0011085 | 1427
TASSAJARA 2113MR276 | TASSAJARA 2113 | 14662113 | FALSE | 3.9116 | 1.5477 | 5.2627 | 75.5 | 0.00042767 | 6144 | 2.8365 | 1427 | 0.0011085 | 1428
ALTO 11221212 | ALTO 1122 | 42031122 | FALSE | 2.3725 | 1.7393 | 2.9325 | 29 | 0.0011341 | 402 | 0.88862 | 2492 | 0.0011084 | 1429
OLETA 110113478 | OLETA 1101 | 163541101 | FALSE | 11.3812 | 0.62825 | 11.9784 | 210 | 0.00020399 | 9977 | 5.2535 | 1121 | 0.0011049 | 1430
OLETA 11011217 | OLETA 1101 | 163541101 | FALSE | 17.0728 | 0.45451 | 13.2167 | 332.5 | 0.0001046 | 11041 | 9.7645 | 846 | 0.0011036 | 1431
WEIMAR 11022038 | WEIMAR 1102 | 152491102 | FALSE | 13.3363 | 1.6505 | 14.9868 | 231.1667 | 0.00044441 | 5965 | 2.6368 | 1475 | 0.0011018 | 1432
FITCH MOUNTAIN 1113356 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 15.2288 | 1.2923 | 10.5098 | 296.5 | 0.00038082 | 6689 | 3.8608 | 1265 | 0.0010995 | 1433
LAS GALLINAS A 1105532 | LAS GALLINAS A 1105 | 42991105 | FALSE | 4.4986 | 0.23961 | 4.5825 | 92 | 0.00029996 | 8018 | 4.363 | 1202 | 0.001099 | 1434
CORRAL 110214028 | CORRAL 1102 | 162991102 | FALSE | 7.8297 | 1.2874 | 3.8438 | 146.5 | 0.00038395 | 6654 | 3.0718 | 1378 | 0.0010982 | 1435
DIAMOND SPRINGS 11039432 | DIAMOND SPRINGS 1103 | 152261103 | FALSE | 20.3571 | 2.5966 | 18.9209 | 369.5 | 0.00036904 | 6858 | 4.1144 | 1242 | 0.0010982 | 1436
CLAYTON 22159765 | CLAYTON 2215 | 12022215 | TRUE | 0.96208 | 0.3198 | 0.25229 | 17.5 | 0.00062478 | 4002 | 2.6794 | 1464 | 0.0010959 | 1437
WILLITS 110391810 | WILLITS 1103 | 42661103 | FALSE | 29.2971 | 2.1756 | 31.4725 | 512 | 0.00034247 | 7267 | 4.0685 | 1250 | 0.0010938 | 1438
ORINDA 0402402/2 LR | ORINDA 0402 | 12350402 | FALSE | 6.6103 | 4.4824 | 10.6346 | 104.5 | 0.000737 | 2654 | 1.4947 | 1851 | 0.0010937 | 1439
STELLING 1110LL72 | STELLING 1110 | 83481110 |  | 3.8301 | 3.6243 |  | 61.5 | 0.00056115 | 4741 | 1.9188 | 1662 | 0.0010922 | 1440
MONTE RIO 11131313 | MONTE RIO 1113 | 42811113 | FALSE | 1.2405 | 1.0121 | 2.2526 | 26 | 0.00094754 | 1021 | 1.15 | 2248 | 0.0010897 | 1441
HATTON 11029642 | HATTON 1102 | 182291102 | FALSE | 1.2356 | 0.63894 | 1.8582 | 25.5 | 0.00093395 | 1078 | 1.15 | 2248 | 0.0010872 | 1442
COVELO 1101679050 | COVELO 1101 | 43061101 |  | 2.9226 | 1.3237 |  | 56.5 | 0.00022154 | 9677 | 9.2138 | 872 | 0.001082 | 1443
BRUNSWICK 1103904574 | BRUNSWICK 1103 | 152481103 | FALSE | 1.5408 | 0.49835 | 2.0391 | 31.5 | 0.00065755 | 3606 | 1.6526 | 1767 | 0.001081 | 1444
MONTE RIO 1113320 | MONTE RIO 1113 | 42811113 | FALSE | 3.9601 | 0.92735 | 3.3592 | 65 | 0.00076502 | 2327 | 1.5958 | 1787 | 0.0010804 | 1445
STANISLAUS 17021850 | STANISLAUS 1702 | 162821702 | FALSE | 14.6139 | 2.2892 | 16.903 | 237.5 | 0.00074739 | 2516 | 1.3653 | 1958 | 0.0010798 | 1446
OAKLAND X 1104391688 | OAKLAND X 1104 | 12541104 | FALSE | 1.2563 | 1.466 | 2.7086 | 21.8333 | 0.00093748 | 1061 | 1.15 | 2249 | 0.0010781 | 1447
MIRABEL 1101116 | MIRABEL 1101 | 42091101 | FALSE | 5.924 | 0.37454 | 5.5322 | 108.8333 | 0.00067977 | 3328 | 1.5906 | 1792 | 0.001078 | 1448
MORAGA 1101822414 | MORAGA 1101 | 13801101 | FALSE | 3.0862 | 1.1217 | 4.0791 | 49.3333 | 0.00057632 | 4572 | 1.9056 | 1670 | 0.0010768 | 1449
SANTA ROSA A 1104220 | SANTA ROSA A 1104 | 42151104 | FALSE | 9.6079 | 0.36957 | 8.0509 | 163.8333 | 0.00031712 | 7677 | 3.3149 | 1339 | 0.0010697 | 1450
UPPER LAKE 1101660 | UPPER LAKE 1101 | 42871101 | FALSE | 9.781 | 0.87474 | 5.2331 | 188 | 0.00025131 | 9054 | 4.9276 | 1144 | 0.0010659 | 1451
PENRYN 11032198 | PENRYN 1103 | 152561103 | FALSE | 20.9878 | 2.3307 | 22.5031 | 369 | 0.0002715 | 8619 | 4.5583 | 1180 | 0.0010655 | 1452
SILVERADO 2102636 | SILVERADO 2102 | 43432102 | FALSE | 6.3699 | 0.98003 | 5.9757 | 124 | 0.00077746 | 2179 | 1.6592 | 1763 | 0.0010652 | 1453
SHADY GLEN 1101CB | SHADY GLEN 1101 | 152431101 | FALSE | 2.6232 | 0.48221 | 2.8174 | 45.5 | 0.00055257 | 4841 | 2.3235 | 1548 | 0.0010588 | 1454
MIRABEL 1101298 | MIRABEL 1101 | 42091101 | FALSE | 12.6327 | 1.019 | 12.3828 | 232.5 | 0.00074388 | 2566 | 1.4029 | 1925 | 0.001057 | 1455
PEORIA 170590374 | PEORIA 1705 | 163781705 | FALSE | 4.324 | 0.31764 | 4.2656 | 75.5 | 0.00033647 | 7358 | 3.5755 | 1296 | 0.0010557 | 1456
CAMP EVERS 21067603 | CAMP EVERS 2106 | 83622106 | FALSE | 0.94898 | 0.15669 | 1.1057 | 16.5 | 0.00090424 | 1214 | 1.1654 | 2206 | 0.0010554 | 1457
POSO MOUNTAIN 2103CB | POSO MOUNTAIN 2103 | 253642103 | FALSE | 18.6395 | 0.18333 | 18.7401 | 338.8333 | 0.00011486 | 10986 | 9.2349 | 870 | 0.0010527 | 1458
DESCHUTES 11011580 | DESCHUTES 1101 | 103351101 | FALSE | 49.2393 | 1.6697 | 46.9323 | 951 | 0.0002431 | 9222 | 5.4085 | 1109 | 0.0010521 | 1459
BRIDGEVILLE 110169866 | BRIDGEVILLE 1101 | 192461101 | FALSE | 6.5361 | 0.12721 | 6.6632 | 128 | 0.00034106 | 7289 | 2.873 | 1420 | 0.0010506 | 1460
CLARK ROAD 1102212118 | CLARK ROAD 1102 | 103091102 | FALSE | 9.4016 | 0.24102 | 8.8127 | 171 | 0.00017642 | 10402 | 9.7457 | 848 | 0.0010506 | 1461
SAN JOAQUIN #3 1103CB | SAN JOAQUIN #3 1103 | 252531103 | FALSE | 27.9455 | 1.8319 | 29.7774 | 514.5 | 0.00033387 | 7397 | 4.263 | 1214 | 0.0010503 | 1462
FULTON 1102287172 | FULTON 1102 | 42561102 | FALSE | 24.5197 | 1.2545 | 16.8504 | 469.5 | 0.00026032 | 8876 | 4.24 | 1217 | 0.0010502 | 1463
ROB ROY 210410298 | ROB ROY 2104 | 83692104 | FALSE | 13.3858 | 1.2966 | 11.4392 | 246 | 0.00086689 | 1442 | 1.082 | 2321 | 0.0010495 | 1464
WYANDOTTE 110366146 | WYANDOTTE 1103 | 102911103 | TRUE | 0.18121 | 0 | 0.18121 | 5 | 0.00048181 | 5586 | 2.1521 | 1590 | 0.001047 | 1465
OILFIELDS 1103643162 | OILFIELDS 1103 | 182391103 | FALSE | 6.2124 | 0.073988 | 3.176 | 114 | 0.00012791 | 10902 | 8.0053 | 935 | 0.0010461 | 1466
BRUNSWICK 11062392 | BRUNSWICK 1106 | 152481106 | FALSE | 8.794 | 0.88505 | 6.0605 | 162.3333 | 0.00037656 | 6740 | 3.2172 | 1352 | 0.0010401 | 1467
MIRABEL 11014859 | MIRABEL 1101 | 42091101 | FALSE | 1.8696 | 0.28898 | 2.1585 | 38 | 0.00086623 | 1449 | 1.2092 | 2121 | 0.0010397 | 1468
OAKLAND K 1104CB | OAKLAND K 1104 | 12101104 | FALSE | 1.4823 | 0.73323 | 2.2155 | 17.4167 | 0.0010191 | 725 | 1.1132 | 2286 | 0.0010394 | 1469
MIWUK 1702CB | MIWUK 1702 | 163661702 | FALSE | 6.25 | 0.19052 | 6.4405 | 106 | 0.00049363 | 5460 | 2.0368 | 1622 | 0.0010383 | 1470
EMERALD LAKE 0402CB | EMERALD LAKE 0402 | 24080402 | FALSE | 1.8749 | 0.86511 | 2.74 | 27 | 0.00053039 | 5071 | 1.9595 | 1653 | 0.0010373 | 1471
CLOVERDALE 1102670 | CLOVERDALE 1102 | 42821102 | TRUE | 3.1089 | 0.25412 | 0.084825 | 59.8333 | 0.00038211 | 6674 | 1.8364 | 1690 | 0.0010367 | 1472
CURTIS 170511790 | CURTIS 1705 | 163351705 | TRUE | 0.014229 | 0 | 0.014229 | 0.5 | 0.00084635 | 1601 | 1.2226 | 2099 | 0.0010348 | 1473
FORT SEWARD 11211690 | FORT SEWARD 1121 | 192321121 | FALSE | 16.4862 | 0.5435 | 10.3513 | 306 | 0.00027359 | 8564 | 4.0875 | 1246 | 0.0010343 | 1474
ALHAMBRA 110213333 | ALHAMBRA 1102 | 14101102 | TRUE | 0.2968 | 0.32707 | 0.10424 | 4.5 | 0.00075391 | 2444 | 1.3679 | 1952 | 0.0010312 | 1475
SILVERADO 2102772792 | SILVERADO 2102 | 43432102 | FALSE | 2.7592 | 0.1224 | 2.1599 | 53.5 | 0.00050769 | 5307 | 2.0966 | 1607 | 0.00103 | 1476
LAYTONVILLE 110189606 | LAYTONVILLE 1101 | 42681101 | FALSE | 4.8898 | 1.3591 | 5.7953 | 86.5 | 0.00037275 | 6793 | 3.1567 | 1363 | 0.0010296 | 1477
MONTE RIO 11133970 | MONTE RIO 1113 | 42811113 | FALSE | 7.2893 | 3.4749 | 10.7642 | 131.5 | 0.00092487 | 1123 | 1.1116 | 2289 | 0.0010265 | 1478
BIG BASIN 1102351054 | BIG BASIN 1102 | 82841102 | FALSE | 1.8143 | 0 | 1.8143 | 33 | 0.00072699 | 2761 | 1.3734 | 1949 | 0.001026 | 1479
CAMP EVERS 2103CB | CAMP EVERS 2103 | 83622103 | TRUE | 0.13755 | 0 | 0.11526 | 4.5 | 0.0011092 | 459 | 0.79243 | 2563 | 0.0010233 | 1480
MONTE RIO 1113CB | MONTE RIO 1113 | 42811113 | TRUE | 0.047363 | 0 | 0.047363 | 0.25 | 0.00067586 | 3361 | 1.5131 | 1837 | 0.0010226 | 1481
GARBERVILLE 110135706 | GARBERVILLE 1101 | 192221101 | FALSE | 9.8902 | 1.4515 | 11.3417 | 184.5 | 0.00051682 | 5207 | 1.9719 | 1649 | 0.0010217 | 1482
MENLO 11037902 | MENLO 1103 | 24131103 |  | 2.3926 | 0.51941 |  | 44 | 0.0004635 | 5768 | 1.3449 | 1968 | 0.0010211 | 1483
COTTONWOOD 11039072 | COTTONWOOD 1103 | 102931103 | FALSE | 28.6596 | 1.3344 | 29.9939 | 547.5 | 0.00013435 | 10846 | 7.1909 | 986 | 0.0010208 | 1484
HALF MOON BAY 1102350336 | HALF MOON BAY 1102 | 24101102 | FALSE | 1.7299 | 0.056828 | 1.1326 | 32.5 | 0.00034467 | 7227 | 3.4137 | 1326 | 0.0010198 | 1485
STAFFORD 1102CB | STAFFORD 1102 | 43201102 | TRUE | 0.58047 | 0 | 0.45329 | 8.8333 | 0.00055847 | 4769 | 2.0981 | 1606 | 0.0010197 | 1486
ATASCADERO 1103A18 | ATASCADERO 1103 | 182541103 | FALSE | 18.0245 | 1.0547 | 8.571 | 329.5 | 0.00017641 | 10403 | 5.5937 | 1097 | 0.0010186 | 1487
PUEBLO 21031968 | PUEBLO 2103 | 43292103 |  | 6.9549 | 2.2331 |  | 125.5 | 0.00040026 | 6454 | 4.6495 | 1171 | 0.0010181 | 1488
CLAY 1103R5386 | CLAY 1103 | 163341103 | FALSE | 16.0447 | 0.38159 | 15.141 | 296 | 0.00019148 | 10188 | 5.495 | 1105 | 0.0010163 | 1489
SILVERADO 2102437194 | SILVERADO 2102 | 43432102 | FALSE | 1.0824 | 0 | 1.0582 | 23.5 | 0.00044758 | 5938 | 2.4557 | 1518 | 0.001013 | 1490
BRUNSWICK 11062796 | BRUNSWICK 1106 | 152481106 | FALSE | 19.9736 | 2.6121 | 22.5856 | 359.5 | 0.00048116 | 5589 | 2.0047 | 1629 | 0.0010106 | 1491
SAND CREEK 11037140 | SAND CREEK 1103 | 254601103 | FALSE | 30.9608 | 1.3873 | 27.4337 | 578 | 0.00012701 | 10909 | 7.5181 | 962 | 0.0010047 | 1492
TASSAJARA 2104CB | TASSAJARA 2104 | 14662104 | TRUE | 9.6816 | 0.68134 | 0.14511 | 169.3333 | 0.00034062 | 7296 | 4.4746 | 1191 | 0.0010033 | 1493
SANTA ROSA A 1104173590 | SANTA ROSA A 1104 | 42151104 | FALSE | 4.2372 | 0.38877 | 4.626 | 76 | 0.00029009 | 8195 | 3.5086 | 1315 | 0.0010029 | 1494
DUNBAR 1102246 | DUNBAR 1102 | 43071102 | FALSE | 14.7318 | 2.226 | 15.3275 | 272.5 | 0.00037054 | 6835 | 2.776 | 1442 | 0.00099922 | 1495
MARTELL 1101473004 | MARTELL 1101 | 163011101 | TRUE | 0.16342 | 0.10588 | 0.18518 | 1.3333 | 0.00086846 | 1434 | 1.15 | 2248 | 0.00099872 | 1496
POSO MOUNTAIN 210448268 | POSO MOUNTAIN 2104 | 253642104 | FALSE | 4.7827 | 0 | 4.6501 | 83 | 0.00016214 | 10573 | 6.0599 | 1067 | 0.00099466 | 1497
CAMP EVERS 21035404 | CAMP EVERS 2103 | 83622103 | FALSE | 4.6221 | 1.8846 | 3.1654 | 75.9167 | 0.0013013 | 203 | 0.60329 | 2729 | 0.00099143 | 1498
OLETA 1101440008 | OLETA 1101 | 163541101 | FALSE | 0.73463 | 0.088668 | 0.70658 | 14 | 0.00023596 | 9364 | 4.1999 | 1228 | 0.000991 | 1499
OAKLAND K 1102378866 | OAKLAND K 1102 | 12101102 | FALSE | 1.3517 | 0.02502 | 1.3739 | 29 | 0.00081912 | 1829 | 1.2101 | 2118 | 0.00099094 | 1500
DIAMOND SPRINGS 1103467046 | DIAMOND SPRINGS 1103 | 152261103 | FALSE | 23.4025 | 3.8999 | 17.704 | 416.5 | 0.00044617 | 5949 | 2.6871 | 1461 | 0.00099052 | 1501
BURNEY 11011340 | BURNEY 1101 | 103311101 | FALSE | 18.0538 | 2.5744 | 20.6281 | 318.3333 | 0.00019674 | 10096 | 7.0513 | 994 | 0.00099046 | 1502
HALF MOON BAY 1103389114 | HALF MOON BAY 1103 | 24101103 | FALSE | 4.8638 | 0.26099 | 5.1248 | 97.5 | 0.00026496 | 8756 | 3.4756 | 1319 | 0.00098691 | 1503
SOBRANTE 1102CB | SOBRANTE 1102 | 14671102 | FALSE | 10.3912 | 3.658 | 14.0492 | 187.5 | 0.00061081 | 4158 | 1.6252 | 1778 | 0.00098675 | 1504
WILLOW CREEK 11037514 | WILLOW CREEK 1103 | 192171103 | FALSE | 10.2126 | 1.5544 | 10.426 | 184.5 | 0.0003661 | 6901 | 2.7132 | 1453 | 0.0009803 | 1505
VIEJO 2201CB | VIEJO 2201 | 182852201 | FALSE | 5.0811 | 2.4159 | 7.2946 | 88.5 | 0.00088456 | 1340 | 1.1133 | 2284 | 0.0009802 | 1506
WOODSIDE 1104520832 | WOODSIDE 1104 | 24251104 | FALSE | 7.9315 | 2.1596 | 7.049 | 155 | 0.00057834 | 4547 | 1.5617 | 1799 | 0.00097946 | 1507
FLINT 1101750 | FLINT 1101 | 152531101 | FALSE | 9.2159 | 1.4633 | 4.7865 | 157 | 0.00022241 | 9661 | 7.2225 | 982 | 0.00097924 | 1508
RISING RIVER 11011532 | RISING RIVER 1101 | 103551101 | FALSE | 4.6967 | 0.17953 | 3.0674 | 91.5 | 0.00011967 | 10953 | 7.0484 | 995 | 0.0009788 | 1509
LLAGAS 2107142710 | LLAGAS 2107 | 83182107 | TRUE | 0.42061 | 0 | 0.35707 | 8.5 | 0.00062503 | 3996 | 1.498 | 1847 | 0.00097858 | 1510
WILLITS 110434008 | WILLITS 1104 | 42661104 | FALSE | 19.9304 | 1.111 | 21.0414 | 352 | 0.00054336 | 4921 | 1.8834 | 1676 | 0.00097419 | 1511
GEYSERVILLE 1101711966 | GEYSERVILLE 1101 | 42891101 | FALSE | 11.8532 | 0.98514 | 3.6141 | 224.3333 | 0.00032329 | 7575 | 3.3731 | 1331 | 0.00097411 | 1512
BIG BASIN 110210254 | BIG BASIN 1102 | 82841102 | FALSE | 2.1436 | 0 | 2.1436 | 38.5 | 0.00073742 | 2645 | 1.399 | 1928 | 0.00097093 | 1513
CURTIS 1705CB | CURTIS 1705 | 163351705 | FALSE | 13.5113 | 1.7511 | 14.6019 | 249.2 | 0.0004078 | 6358 | 2.6736 | 1465 | 0.00096858 | 1514
SAN RAFAEL 1108CB | SAN RAFAEL 1108 | 42011108 | FALSE | 7.3899 | 4.813 | 7.57 | 113.5 | 0.00089139 | 1284 | 1.0081 | 2381 | 0.00096022 | 1515
SPRING GAP 17029280 | SPRING GAP 1702 | 162831702 | FALSE | 6.4026 | 1.7693 | 8.1719 | 121.3333 | 0.0005804 | 4516 | 1.9844 | 1642 | 0.00095956 | 1516
ROSSMOOR 1108CB | ROSSMOOR 1108 | 14161108 | FALSE | 3.8764 | 1.4716 | 2.3696 | 63.2262 | 0.00054771 | 4879 | 2.2894 | 1556 | 0.00095948 | 1517
PIT NO 1 110170952 | PIT NO 1 1101 | 103721101 | FALSE | 1.7084 | 1.1009 | 2.8019 | 29 | 0.00032436 | 7552 | 3.037 | 1388 | 0.00095908 | 1518
BRENTWOOD 2105B504R | BRENTWOOD 2105 | 14592105 | FALSE | 11.2292 | 0.33894 | 8.2565 | 190.3333 | 0.00022135 | 9680 | 4.8457 | 1155 | 0.00095798 | 1519
SAN CARLOS 1104833770 | SAN CARLOS 1104 | 24181104 | TRUE | 0.01528 | 0 | 0.01528 | 0.33333 | 0.00083244 | 1710 | 1.15 | 2248 | 0.0009573 | 1520
CAMP EVERS 2104189010 | CAMP EVERS 2104 | 83622104 | TRUE | 0.056789 | 0 | 0.027848 | 4 | 0.0011959 | 302 | 0.74387 | 2607 | 0.00095693 | 1521
EMERALD LAKE 0401CB | EMERALD LAKE 0401 | 24080401 | FALSE | 13.2238 | 3.007 | 12.0359 | 246 | 0.00049716 | 5422 | 1.908 | 1667 | 0.00095169 | 1522
POTTER VALLEY P H 1104546986 | POTTER VALLEY P H 1104 | 42281104 | FALSE | 4.4638 | 0.17933 | 2.5442 | 80 | 0.00027627 | 8509 | 3.6037 | 1293 | 0.00095087 | 1523
LAURELES 11122768 | LAURELES 1112 | 182371112 | FALSE | 8.0408 | 1.7463 | 7.0152 | 153.5 | 0.00038481 | 6641 | 2.737 | 1451 | 0.00095073 | 1524
VOLTA 110280982 | VOLTA 1102 | 102541102 | TRUE | 0.50915 | 0 | 0.50915 | 10 | 0.00051555 | 5223 | 1.7527 | 1717 | 0.00094999 | 1525
SAUSALITO 11021268 | SAUSALITO 1102 | 42491102 | FALSE | 4.9323 | 0.69404 | 5.6263 | 100.5 | 0.00035706 | 7021 | 2.8162 | 1433 | 0.00094991 | 1526
MIWUK 170179118 | MIWUK 1701 | 163661701 | TRUE | 0.01936 | 0 | 0.01936 | 1.5 | 0.00082563 | 1769 | 1.15 | 2248 | 0.00094947 | 1527
OAKLAND X 1104CR214 | OAKLAND X 1104 | 12541104 | FALSE | 2.8586 | 2.6634 | 5.5219 | 48.5 | 0.00075986 | 2387 | 1.2159 | 2109 | 0.00094429 | 1528
SALT SPRINGS 21024796 | SALT SPRINGS 2102 | 163692102 | FALSE | 7.8013 | 0.75632 | 7.7549 | 144 | 0.00068277 | 3300 | 1.4589 | 1881 | 0.00094334 | 1529
PUEBLO 2103253312 | PUEBLO 2103 | 43292103 | TRUE | 0.4234 | 0 | 0.40227 | 9.5 | 0.00037326 | 6789 | 2.5259 | 1503 | 0.0009428 | 1530
BRUNSWICK 1106CB | BRUNSWICK 1106 | 152481106 | FALSE | 8.8204 | 1.9827 | 10.5911 | 145.5833 | 0.00067668 | 3351 | 1.5216 | 1828 | 0.00093811 | 1531
VACAVILLE 1109799940 | VACAVILLE 1109 | 63601109 | TRUE | 0.83285 | 0.03642 | 0.51138 | 17.5 | 0.00022625 | 9576 | 6.7847 | 1014 | 0.00093781 | 1532
BIG MEADOWS 21012476 | BIG MEADOWS 2101 | 102812101 | FALSE | 8.6544 | 1.3019 | 8.7887 | 168.3333 | 0.00040211 | 6426 | 3.0252 | 1390 | 0.00093756 | 1533
VIEJO 22012064 | VIEJO 2201 | 182852201 | FALSE | 0.86986 | 0.50302 | 1.3729 | 16.5 | 0.00081513 | 1855 | 1.15 | 2248 | 0.0009374 | 1534
OAKLAND X 1104CR022 | OAKLAND X 1104 | 12541104 | FALSE | 3.943 | 3.8157 | 7.7586 | 60 | 0.00082086 | 1811 | 1.1246 | 2274 | 0.00093728 | 1535
WHITMORE 11011598 | WHITMORE 1101 | 103601101 | FALSE | 33.0211 | 0.98169 | 34.0027 | 621 | 0.00027253 | 8593 | 3.4071 | 1327 | 0.00093567 | 1536
GARCIA 0401CB | GARCIA 0401 | 43040401 | TRUE | 0.029025 | 0 | 0.029025 | 0.5 | 0.00058957 | 4421 | 1.5857 | 1796 | 0.00093488 | 1537
STAFFORD 1102784704 | STAFFORD 1102 | 43201102 | TRUE | 0.027927 | 0 | 0.027927 | 1.5 | 0.00023039 | 9477 | 4.0547 | 1253 | 0.00093415 | 1538
PAUL SWEET 2105CB | PAUL SWEET 2105 | 83252105 | FALSE | 8.8205 | 0.41104 | 7.1537 | 142.1667 | 0.00099366 | 815 | 0.93869 | 2458 | 0.00093391 | 1539
ATASCADERO 1103A06 | ATASCADERO 1103 | 182541103 | TRUE | 2.0385 | 0.10843 | 0.15554 | 36 | 0.00022959 | 9498 | 4.9644 | 1142 | 0.0009339 | 1540
CAL WATER 1102690954 | CAL WATER 1102 | 255451102 | FALSE | 4.2454 | 0.17582 | 3.7239 | 80 | 8.4691e-05 | 11097 | 10.7868 | 808 | 0.0009331 | 1541
LOS GATOS 1101CB | LOS GATOS 1101 | 82021101 | TRUE | 2.8964 | 1.7511 | 0.014595 | 49 | 0.0010599 | 587 | 1.3221 | 1987 | 0.0009318 | 1542
GARBERVILLE 1102802246 | GARBERVILLE 1102 | 192221102 | FALSE | 7.7736 | 0.6461 | 8.4197 | 153 | 0.00055769 | 4784 | 1.6892 | 1744 | 0.00092635 | 1543
BOLINAS 1101530 | BOLINAS 1101 | 42261101 | FALSE | 10.9396 | 0.11809 | 11.0577 | 225 | 0.00020524 | 9959 | 5.0837 | 1132 | 0.00092633 | 1544
GOLDTREE 1105551904 | GOLDTREE 1105 | 182581105 | TRUE | 0.022194 | 0 | 0.022194 | 0.5 | 0.00032012 | 7627 | 2.8928 | 1415 | 0.00092605 | 1545
PARADISE 1106CB | PARADISE 1106 | 102831106 | FALSE | 4.841 | 1.444 | 5.9225 | 71.5333 | 0.00072231 | 2828 | 1.2753 | 2030 | 0.00092573 | 1546
DIAMOND SPRINGS 1106762780 | DIAMOND SPRINGS 1106 | 152261106 | TRUE | 0.77416 | 0.38699 | 0.23233 | 18.5 | 0.00035837 | 7001 | 2.4798 | 1514 | 0.00092187 | 1547
MORGAN HILL 210542348 | MORGAN HILL 2105 | 83242105 | FALSE | 3.9258 | 2.0104 | 1.4952 | 73.5 | 0.0004509 | 5913 | 2.6986 | 1459 | 0.00092137 | 1548
OAKLAND K 1102172340 | OAKLAND K 1102 | 12101102 | FALSE | 0.81239 | 0.64721 | 1.4596 | 19 | 0.00079907 | 1976 | 1.15 | 2248 | 0.00091893 | 1549
CALAVERAS CEMENT 110113424 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 3.605 | 0.98076 | 1.4951 | 63 | 0.00039114 | 6555 | 2.7574 | 1447 | 0.00091818 | 1550
CMC 1102CB | CMC 1102 | 183111102 | TRUE | 0.39747 | 0 | 0.39747 | 4.1667 | 0.00029828 | 8047 | 3.0613 | 1380 | 0.000917 | 1551
MIWUK 1701992162 | MIWUK 1701 | 163661701 | FALSE | 3.7307 | 0.42151 | 4.1522 | 73 | 0.00034219 | 7271 | 2.6899 | 1460 | 0.00091666 | 1552
OAKLAND K 1104CR326 | OAKLAND K 1104 | 12101104 | FALSE | 1.245 | 0.80578 | 2.0507 | 17.1667 | 0.00078909 | 2069 | 1.1712 | 2189 | 0.0009162 | 1553
VACA DIXON 110540092 | VACA DIXON 1105 | 63591105 | FALSE | 42.8429 | 2.1257 | 23.3152 | 745.5 | 0.00019349 | 10159 | 5.8431 | 1083 | 0.00091401 | 1554
GARBERVILLE 11026084 | GARBERVILLE 1102 | 192221102 | FALSE | 7.5157 | 0.47253 | 7.9882 | 156 | 0.00051984 | 5181 | 1.8392 | 1689 | 0.00091352 | 1555
FULTON 110258990 | FULTON 1102 | 42561102 | TRUE | 0.60825 | 0 | 0.14307 | 10 | 0.00026956 | 8662 | 2.8089 | 1435 | 0.00091245 | 1556
VOLTA 110165764 | VOLTA 1101 | 102541101 | FALSE | 10.2951 | 0.16702 | 10.4621 | 203 | 0.00010951 | 11016 | 8.3186 | 920 | 0.00091138 | 1557
AUBERRY 1101R314 | AUBERRY 1101 | 254151101 | FALSE | 44.3993 | 1.0858 | 43.0751 | 814 | 9.2885e-05 | 11073 | 9.831 | 841 | 0.00091123 | 1558
SAN RAMON 2107MR284 | SAN RAMON 2107 | 14232107 | FALSE | 14.8032 | 3.6966 | 17.498 | 265.5 | 0.00032581 | 7524 | 2.5184 | 1506 | 0.00091029 | 1559
OAKLAND K 1102CR014 | OAKLAND K 1102 | 12101102 | FALSE | 10.4386 | 8.6742 | 19.1128 | 168.3333 | 0.0008053 | 1939 | 1.148 | 2250 | 0.00090998 | 1560
HIGHLANDS 1104CB | HIGHLANDS 1104 | 43361104 | FALSE | 8.2701 | 3.9854 | 7.4912 | 122.5833 | 0.00054005 | 4956 | 1.9172 | 1664 | 0.00090896 | 1561
JESSUP 1101271314 | JESSUP 1101 | 103441101 | FALSE | 2.3803 | 0.17402 | 1.2526 | 44.5 | 0.00030187 | 7968 | 3.0747 | 1375 | 0.00090884 | 1562
PARADISE 110439214 | PARADISE 1104 | 102831104 | TRUE | 1.2235 | 0.32938 | 0.00042227 | 18.5 | 0.00062028 | 4046 | 1.4246 | 1906 | 0.00090699 | 1563
MARTELL 1101131918 | MARTELL 1101 | 163011101 | TRUE | 0.39174 | 0.062554 | 0.41561 | 8.3333 | 0.00078797 | 2074 | 1.15 | 2247 | 0.00090617 | 1564
OAKLAND K 1104CR210 | OAKLAND K 1104 | 12101104 | FALSE | 2.7892 | 2.6241 | 5.4115 | 36.5 | 0.0007845 | 2103 | 1.1517 | 2241 | 0.00090582 | 1565
CAMP EVERS 210616000 | CAMP EVERS 2106 | 83622106 | FALSE | 3.8752 | 1.6773 | 2.9192 | 58.1667 | 0.0011934 | 308 | 0.71277 | 2631 | 0.00090575 | 1566
DUNBAR 1103839384 | DUNBAR 1103 | 43071103 | FALSE | 10.9577 | 2.7538 | 2.2259 | 203 | 0.00059191 | 4394 | 2.1893 | 1579 | 0.00090511 | 1567
GANSNER 11012006 | GANSNER 1101 | 103021101 | FALSE | 17.2625 | 2.4737 | 19.7361 | 330.5 | 0.00023122 | 9458 | 3.6746 | 1289 | 0.00090414 | 1568
PEORIA 17048040 | PEORIA 1704 | 163781704 | FALSE | 25.6861 | 0.48669 | 6.7307 | 477.5 | 0.00014111 | 10776 | 5.6558 | 1094 | 0.00090346 | 1569
ALLEGHANY 1101978 | ALLEGHANY 1101 | 152101101 | FALSE | 29.2964 | 1.8825 | 12.5958 | 586.5 | 0.00019249 | 10173 | 4.4256 | 1195 | 0.00090188 | 1570
MARTELL 110299214 | MARTELL 1102 | 163011102 | FALSE | 2.07 | 0.12684 | 1.7592 | 37.1667 | 0.0004878 | 5521 | 1.8661 | 1680 | 0.0008986 | 1571
HALF MOON BAY 110398440 | HALF MOON BAY 1103 | 24101103 | FALSE | 8.3032 | 1.4153 | 9.7185 | 160.5 | 0.00078124 | 2138 | 1.15 | 2248 | 0.00089842 | 1572
NORTH BRANCH 1101752104 | NORTH BRANCH 1101 | 163231101 | FALSE | 18.3815 | 1.0855 | 19.365 | 342 | 0.0001387 | 10805 | 10.0067 | 833 | 0.00089825 | 1573
AUBERRY 1102R1013 | AUBERRY 1102 | 254151102 | FALSE | 12.3762 | 0.47883 | 12.855 | 220.5 | 0.00014093 | 10778 | 6.8365 | 1009 | 0.00089538 | 1574
HICKS 1116647210 | HICKS 1116 | 83431116 | FALSE | 3.3066 | 1.6174 | 3.3931 | 52.5 | 0.00055048 | 4857 | 2.4738 | 1516 | 0.00089196 | 1575
BRUNSWICK 110633050 | BRUNSWICK 1106 | 152481106 | FALSE | 3.8067 | 1.1807 | 1.3588 | 67.5 | 0.00077101 | 2249 | 1.1469 | 2252 | 0.00089195 | 1576
SOBRANTE 1102L510R | SOBRANTE 1102 | 14671102 | FALSE | 9.7475 | 4.8258 | 14.3233 | 167 | 0.00067038 | 3429 | 1.3222 | 1986 | 0.00089135 | 1577
SOBRANTE 1102690098 | SOBRANTE 1102 | 14671102 | FALSE | 7.4936 | 3.6466 | 10.897 | 133.8333 | 0.00059897 | 4311 | 1.5295 | 1822 | 0.00089099 | 1578
CAMP EVERS 210410442 | CAMP EVERS 2104 | 83622104 | FALSE | 10.3305 | 3.2561 | 6.0171 | 179.5 | 0.00099004 | 831 | 0.86827 | 2510 | 0.00089031 | 1579
MENDOCINO 1101450 | MENDOCINO 1101 | 42951101 | FALSE | 18.9559 | 1.3657 | 5.3025 | 333.5 | 0.00026609 | 8742 | 6.1488 | 1058 | 0.00089003 | 1580
JAMESON 1102865502 | JAMESON 1102 | 63801102 | FALSE | 2.8374 | 0.14426 | 0.63194 | 48.5 | 0.00034239 | 7268 | 2.9377 | 1404 | 0.00088788 | 1581
WOODACRE 110196844 | WOODACRE 1101 | 43021101 | FALSE | 5.8232 | 0.55218 | 6.3754 | 112 | 0.0006268 | 3983 | 1.4534 | 1886 | 0.00088667 | 1582
STANISLAUS 17021804 | STANISLAUS 1702 | 162821702 | FALSE | 8.3786 | 1.4969 | 9.8755 | 144.8333 | 0.00065411 | 3654 | 1.3653 | 1955 | 0.00088659 | 1583
ALTO 1124703432 | ALTO 1124 | 42031124 | TRUE | 0.75186 | 0.75004 | 0.44962 | 10.6667 | 0.00077003 | 2257 | 1.15 | 2248 | 0.00088554 | 1584
SAN RAFAEL 11071276 | SAN RAFAEL 1107 | 42011107 | FALSE | 3.9703 | 3.0112 | 6.1941 | 70 | 0.00084223 | 1636 | 1.0188 | 2370 | 0.00088437 | 1585
MILPITAS 1109XR524 | MILPITAS 1109 | 82831109 | FALSE | 11.2038 | 0.13443 | 10.669 | 210 | 7.7391e-05 | 11111 | 11.6261 | 775 | 0.00088432 | 1586
VACAVILLE 1109592742 | VACAVILLE 1109 | 63601109 | TRUE | 0.4253 | 0 | 0.29648 | 9.5 | 0.00030844 | 7832 | 3.0957 | 1372 | 0.00088401 | 1587
HIGGINS 1108CB | HIGGINS 1108 | 152691108 |  | 0.02041 | 0 |  | 0.5 | 0.00072167 | 2835 | 1.2226 | 2099 | 0.00088232 | 1588
MONTE RIO 11135026 | MONTE RIO 1113 | 42811113 | FALSE | 1.8473 | 1.1078 | 2.9551 | 33 | 0.00089325 | 1277 | 1.0173 | 2374 | 0.00088127 | 1589
STILLWATER 1101CB | STILLWATER 1101 | 103561101 | FALSE | 4.2666 | 0.33289 | 4.2652 | 71 | 0.00052691 | 5105 | 1.6774 | 1753 | 0.00088054 | 1590
HALF MOON BAY 11018902 | HALF MOON BAY 1101 | 24101101 | FALSE | 17.8907 | 1.0082 | 13.0082 | 346.5 | 0.00035569 | 7047 | 2.3876 | 1535 | 0.00087986 | 1591
BELMONT 11038958 | BELMONT 1103 | 24031103 | FALSE | 5.914 | 4.0367 | 5.5499 | 84 | 0.00049394 | 5456 | 1.6765 | 1754 | 0.00087832 | 1592
SOBRANTE 1103CB | SOBRANTE 1103 | 14671103 | FALSE | 4.3229 | 0.53135 | 4.6918 | 75.6667 | 0.00070402 | 3054 | 1.3048 | 2001 | 0.00087825 | 1593
DIAMOND SPRINGS 110777086 | DIAMOND SPRINGS 1107 | 152261107 | FALSE | 3.7555 | 0.26484 | 2.6256 | 67.5 | 0.00035359 | 7080 | 2.7693 | 1444 | 0.00087798 | 1594
OAKLAND K 1103CR188 | OAKLAND K 1103 | 12101103 | FALSE | 3.5356 | 3.6528 | 7.1883 | 57.9167 | 0.00077054 | 2251 | 1.1147 | 2282 | 0.00087684 | 1595
WOODACRE 1101404 | WOODACRE 1101 | 43021101 | FALSE | 12.3716 | 6.6358 | 19.0074 | 238.5 | 0.00067772 | 3344 | 1.3178 | 1990 | 0.00087565 | 1596
OAKLAND K 1104432850 | OAKLAND K 1104 | 12101104 | FALSE | 1.2526 | 1.2976 | 2.5501 | 31.9167 | 0.00076088 | 2371 | 1.1683 | 2200 | 0.00087511 | 1597
SANTA ROSA A 1104210 | SANTA ROSA A 1104 | 42151104 | FALSE | 8.6378 | 4.1848 | 9.8635 | 164.8333 | 0.00082586 | 1768 | 0.99922 | 2394 | 0.00087298 | 1598
SAN ARDO 11017632 | SAN ARDO 1101 | 182191101 | FALSE | 8.2654 | 0.17939 | 0.90418 | 167.5 | 0.00014299 | 10763 | 7.2396 | 981 | 0.00087277 | 1599
CLOVERDALE 1101409224 | CLOVERDALE 1101 | 42821101 | TRUE | 0.21924 | 0.11501 | 0.086865 | 5.5 | 0.00043911 | 6018 | 1.8893 | 1674 | 0.00087262 | 1600
PUEBLO 1105426584 | PUEBLO 1105 | 43291105 | FALSE | 3.8259 | 0.086955 | 3.6621 | 71.5 | 0.00024372 | 9206 | 5.027 | 1140 | 0.00087201 | 1601
ROSSMOOR 1108543356 | ROSSMOOR 1108 | 14161108 | FALSE | 1.7062 | 0.80479 | 0.9975 | 19.6667 | 0.00076616 | 2309 | 1.1727 | 2181 | 0.00087083 | 1602
PAUL SWEET 21045394 | PAUL SWEET 2104 | 83252104 | FALSE | 15.1898 | 1.1096 | 15.3931 | 267 | 0.00068638 | 3260 | 1.2758 | 2029 | 0.00087008 | 1603
WHITMORE 1101CB | WHITMORE 1101 | 103601101 | FALSE | 5.5805 | 0.5094 | 6.0899 | 104.5 | 0.00039177 | 6546 | 2.3748 | 1539 | 0.00087003 | 1604
HOOPA 11013174 | HOOPA 1101 | 192401101 | FALSE | 21.8485 | 1.638 | 18.7076 | 426.5 | 0.00038695 | 6620 | 2.1473 | 1591 | 0.00086279 | 1605
PANOCHE 11034036 | PANOCHE 1103 | 253671103 | FALSE | 25.4096 | 0.39025 | 7.2659 | 506.5 | 9.7983e-05 | 11059 | 11.4685 | 782 | 0.0008605 | 1606
GRASS VALLEY 1101750804 | GRASS VALLEY 1101 | 152031101 | TRUE | 0.27925 | 0.076317 | 0.31834 | 6 | 0.00055496 | 4821 | 1.5494 | 1808 | 0.00085976 | 1607
TEMPLETON 2111CB | TEMPLETON 2111 | 183052111 | FALSE | 11.2516 | 0.65929 | 2.325 | 211.3333 | 0.0003458 | 7210 | 4.2678 | 1213 | 0.00085873 | 1608
BRUNSWICK 1103234378 | BRUNSWICK 1103 | 152481103 | FALSE | 0.74539 | 0.2411 | 0.75553 | 12 | 0.00072258 | 2823 | 1.1863 | 2149 | 0.00085829 | 1609
BUELLTON 1101Y26 | BUELLTON 1101 | 183041101 | FALSE | 15.5591 | 0.65324 | 14.7371 | 298.5 | 0.00021083 | 9864 | 4.8399 | 1156 | 0.00085783 | 1610
ZACA 1101Y72 | ZACA 1101 | 182681101 | FALSE | 6.3886 | 0.2694 | 5.5692 | 135.5 | 0.00013145 | 10871 | 6.8528 | 1006 | 0.00085697 | 1611
GARBERVILLE 11011514 | GARBERVILLE 1101 | 192221101 | FALSE | 9.6659 | 0.74231 | 10.4082 | 183 | 0.00059559 | 4353 | 1.422 | 1909 | 0.00085627 | 1612
BERKELEY F 1103162952 | BERKELEY F 1103 | 12061103 | FALSE | 2.1656 | 1.9435 | 3.2448 | 32.3333 | 0.00057813 | 4551 | 1.4846 | 1861 | 0.00085618 | 1613
MONTE RIO 1113678 | MONTE RIO 1113 | 42811113 | TRUE | 1.8807 | 0.36986 | 0.58954 | 33.5 | 0.00074448 | 2562 | 1.15 | 2248 | 0.00085615 | 1614
ANDERSON 1101337668 | ANDERSON 1101 | 103261101 | TRUE | 0.31566 | 0.15716 | 0.4579 | 6.5 | 0.00061836 | 4065 | 1.3455 | 1967 | 0.00085556 | 1615
SHINGLE SPRINGS 210912392 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 14.7535 | 1.7455 | 16.4989 | 259.5 | 0.00034843 | 7166 | 2.6037 | 1484 | 0.00085065 | 1616
PARADISE 1104920400 | PARADISE 1104 | 102831104 | FALSE | 3.7132 | 1.3568 | 4.7809 | 70 | 0.00057621 | 4573 | 1.8327 | 1692 | 0.00084939 | 1617
PARADISE 1105CB | PARADISE 1105 | 102831105 | FALSE | 7.2369 | 2.1339 | 7.7481 | 121.5333 | 0.00064088 | 3814 | 1.302 | 2003 | 0.00084828 | 1618
MONTE RIO 1113477 | MONTE RIO 1113 | 42811113 | FALSE | 1.8209 | 2.1104 | 3.9313 | 40.8333 | 0.00073751 | 2643 | 1.15 | 2247 | 0.00084814 | 1619
TYLER 110585132 | TYLER 1105 | 103571105 | FALSE | 31.3933 | 0.70793 | 32.1011 | 588.5 | 0.00017034 | 10481 | 5.3424 | 1116 | 0.00084459 | 1620
WILLOW CREEK 110237374 | WILLOW CREEK 1102 | 192171102 | FALSE | 2.2474 | 0 | 2.2473 | 40 | 0.0004716 | 5683 | 1.7972 | 1703 | 0.00084388 | 1621
SNEATH LANE 110134438 | SNEATH LANE 1101 | 22721101 | FALSE | 5.1275 | 4.8553 | 3.5953 | 82.6667 | 0.00072622 | 2776 | 1.1197 | 2279 | 0.00084316 | 1622
VIEJO 220235388 | VIEJO 2202 | 182852202 | TRUE | 0.46125 | 0.37556 | 0.38742 | 6.3333 | 0.00080973 | 1899 | 0.9768 | 2422 | 0.0008421 | 1623
PLACERVILLE 1112774186 | PLACERVILLE 1112 | 153081112 | TRUE | 0.73677 | 0.41026 | 0.43329 | 13.3333 | 0.0008992 | 1236 | 0.80464 | 2553 | 0.00083769 | 1624
BRIDGEVILLE 110255612 | BRIDGEVILLE 1102 | 192461102 | FALSE | 22.1131 | 0.40925 | 22.5222 | 443.5 | 0.00026634 | 8737 | 2.8441 | 1426 | 0.00083729 | 1625
SUMMIT 110249484 | SUMMIT 1102 | 152591102 | FALSE | 2.6457 | 0.59428 | 3.24 | 42 | 0.00064626 | 3751 | 1.3445 | 1970 | 0.00083631 | 1626
CURTIS 1704CB | CURTIS 1704 | 163351704 | FALSE | 14.2517 | 1.7101 | 15.3735 | 255.2 | 0.00032792 | 7486 | 2.7923 | 1439 | 0.00083532 | 1627
HARTLEY 110186876 | HARTLEY 1101 | 43211101 | FALSE | 8.7353 | 4.8657 | 2.6039 | 136.8333 | 0.00046358 | 5766 | 2.9191 | 1409 | 0.00083468 | 1628
COARSEGOLD 21025380 | COARSEGOLD 2102 | 254432102 | FALSE | 14.0856 | 0.61699 | 14.7025 | 245.75 | 0.0003067 | 7873 | 3.001 | 1395 | 0.00083191 | 1629
GEYSERVILLE 1102756 | GEYSERVILLE 1102 | 42891102 | TRUE | 0.6023 | 0 | 0.6023 | 12.5 | 0.00034641 | 7199 | 2.3583 | 1541 | 0.00082967 | 1630
FITCH MOUNTAIN 1113352 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 10.2886 | 3.5691 | 13.6763 | 196 | 0.00052334 | 5149 | 1.9687 | 1651 | 0.00082885 | 1631
OTTER 110298036 | OTTER 1102 | 182941102 | FALSE | 9.308 | 0.20716 | 9.5152 | 187.5 | 0.0002188 | 9722 | 4.5091 | 1185 | 0.00082695 | 1632
TEMPLETON 2113A70 | TEMPLETON 2113 | 183052113 | FALSE | 66.3942 | 1.6084 | 24.646 | 1222.5 | 0.00014485 | 10750 | 7.909 | 943 | 0.00082406 | 1633
OAKLAND X 1106CR020 | OAKLAND X 1106 | 12541106 | FALSE | 2.4398 | 0.43671 | 2.8765 | 50 | 0.00072247 | 2825 | 1.1174 | 2280 | 0.00082293 | 1634
FAIRVIEW 220799096 | FAIRVIEW 2207 | 13432207 | FALSE | 9.8981 | 0.21022 | 10.0183 | 197.5 | 0.0002148 | 9777 | 3.7968 | 1273 | 0.00082229 | 1635
CALISTOGA 1101CB | CALISTOGA 1101 | 42711101 | TRUE | 0.69733 | 0.036094 | 0.12285 | 11.3333 | 0.00072961 | 2734 | 1.0752 | 2327 | 0.00082073 | 1636
SAN LUIS OBISPO 110596874 | SAN LUIS OBISPO 1105 | 182631105 | FALSE | 1.0683 | 1.0274 | 1.4719 | 19.6667 | 0.00065917 | 3589 | 1.4182 | 1913 | 0.00082026 | 1637
PHILO 11013700 | PHILO 1101 | 42601101 | FALSE | 20.9489 | 0.32592 | 21.2747 | 355 | 0.00023006 | 9487 | 4.8976 | 1150 | 0.0008197 | 1638
MORGAN HILL 2105XR564 | MORGAN HILL 2105 | 83242105 | FALSE | 7.2687 | 0.8215 | 5.9077 | 132 | 0.00030183 | 7971 | 2.6693 | 1467 | 0.00081864 | 1639
VOLTA 110237350 | VOLTA 1102 | 102541102 | FALSE | 24.207 | 1.8946 | 26.1015 | 444 | 0.00025893 | 8906 | 4.2125 | 1223 | 0.00081806 | 1640
TAR FLAT 04023144 | TAR FLAT 0402 | 163240402 | FALSE | 5.2078 | 1.4482 | 6.0159 | 95.8333 | 0.00041833 | 6240 | 1.9629 | 1652 | 0.00081777 | 1641
PUEBLO 2102391312 | PUEBLO 2102 | 43292102 | TRUE | 1.2 | 0.071364 | 0.13272 | 24.5 | 0.00026374 | 8785 | 3.5917 | 1294 | 0.00081711 | 1642
JESSUP 11021314 | JESSUP 1102 | 103441102 | FALSE | 14.4923 | 1.7359 | 5.5621 | 246.5 | 0.00019492 | 10133 | 5.186 | 1124 | 0.00081678 | 1643
FORESTHILL 1102CB | FORESTHILL 1102 | 152181102 | FALSE | 1.6383 | 0.054191 | 1.6925 | 29.5 | 0.0004307 | 6110 | 1.9898 | 1638 | 0.00081547 | 1644
BIG RIVER 1101CB | BIG RIVER 1101 | 43081101 | TRUE | 0.029925 | 0 | 0.029925 | 0.5 | 0.00070898 | 2992 | 1.15 | 2248 | 0.00081533 | 1645
STANISLAUS 170237276 | STANISLAUS 1702 | 162821702 | FALSE | 11.6066 | 1.6843 | 13.2909 | 193 | 0.00061804 | 4069 | 1.3161 | 1993 | 0.00081474 | 1646
BRUNSWICK 110584480 | BRUNSWICK 1105 | 152481105 | FALSE | 4.5877 | 0.40912 | 4.9968 | 87 | 0.00058926 | 4423 | 1.4004 | 1927 | 0.00081441 | 1647
SPRING GAP 1702693441 | SPRING GAP 1702 | 162831702 | FALSE | 4.3244 | 1.5944 | 5.9187 | 82.3333 | 0.00056435 | 4714 | 1.4593 | 1879 | 0.00081289 | 1648
GANSNER 1101336664 | GANSNER 1101 | 103021101 | FALSE | 1.5706 | 0.23558 | 0.66212 | 25.5 | 0.00033009 | 7446 | 2.6101 | 1483 | 0.00081286 | 1649
FAIRVIEW 2207M501R | FAIRVIEW 2207 | 13432207 | FALSE | 4.6268 | 4.6376 | 3.7232 | 71.3333 | 0.00066037 | 3575 | 1.75 | 1719 | 0.00081252 | 1650
ORINDA 0401401/2 LR | ORINDA 0401 | 12350401 | TRUE | 0.14657 | 0 | 0.098331 | 2.1667 | 0.00093654 | 1065 | 0.87466 | 2503 | 0.00081186 | 1651
HOPLAND 1101865263 | HOPLAND 1101 | 42251101 | FALSE | 8.6076 | 0.26055 | 5.8469 | 164 | 0.00023605 | 9360 | 4.4761 | 1190 | 0.00081148 | 1652
WILLITS 11032506 | WILLITS 1103 | 42661103 | FALSE | 12.2443 | 0.48662 | 12.6279 | 239.5 | 0.00034959 | 7145 | 2.3069 | 1554 | 0.00081063 | 1653
CLAYTON 2212CB | CLAYTON 2212 | 12022212 | TRUE | 9.588 | 5.6388 | 0.0065327 | 151.6667 | 0.00083699 | 1665 | 1.9867 | 1641 | 0.00080781 | 1654
LUCERNE 110647198 | LUCERNE 1106 | 43351106 | FALSE | 4.5758 | 2.9097 | 0.76178 | 69.5 | 0.00043649 | 6049 | 4.1685 | 1232 | 0.00080665 | 1655
GARBERVILLE 11022124 | GARBERVILLE 1102 | 192221102 | FALSE | 3.3466 | 0 | 3.3466 | 45 | 0.00048995 | 5494 | 2.041 | 1621 | 0.00080524 | 1656
TIVY VALLEY 1107869946 | TIVY VALLEY 1107 | 252941107 | FALSE | 29.1243 | 0.50363 | 29.6278 | 564.5 | 9.2631e-05 | 11077 | 10.0756 | 830 | 0.00080485 | 1657
TAR FLAT 0402588710 | TAR FLAT 0402 | 163240402 | FALSE | 1.1342 | 0.77194 | 0.84631 | 15 | 0.00075255 | 2455 | 1.1668 | 2205 | 0.00080434 | 1658
DEL MONTE 2104181640 | DEL MONTE 2104 | 182222104 | TRUE | 0.016177 | 0 | 0.016177 | 0.58333 | 0.0005315 | 5054 | 1.5131 | 1836 | 0.0008042 | 1659
PLACERVILLE 1112239390 | PLACERVILLE 1112 | 153081112 | FALSE | 1.8914 | 1.2409 | 3.1323 | 33.3333 | 0.00074158 | 2586 | 1.0986 | 2303 | 0.00080228 | 1660
MARTELL 1101532836 | MARTELL 1101 | 163011101 | FALSE | 2.1215 | 0.03284 | 2.1266 | 43.5 | 0.00035762 | 7013 | 3.5438 | 1304 | 0.00080182 | 1661
GARBERVILLE 110256048 | GARBERVILLE 1102 | 192221102 | FALSE | 4.9405 | 0.019837 | 4.9603 | 98 | 0.00052052 | 5172 | 1.5531 | 1806 | 0.00080077 | 1662
LAYTONVILLE 1102538750 | LAYTONVILLE 1102 | 42681102 | FALSE | 9.3864 | 0.27816 | 9.6645 | 189 | 0.00017591 | 10411 | 3.2964 | 1345 | 0.0007977 | 1663
TASSAJARA 2108954811 | TASSAJARA 2108 | 14662108 | TRUE | 0.56698 | 0.566 | 0.19651 | 12.1667 | 0.00085439 | 1544 | 1.3776 | 1945 | 0.00079751 | 1664
MOLINO 1102658 | MOLINO 1102 | 42571102 | FALSE | 10.7791 | 0.60587 | 6.7338 | 203.5 | 0.00046876 | 5710 | 1.7748 | 1709 | 0.00079714 | 1665
EDES 1112484536 | EDES 1112 | 13681112 | FALSE | 1.2606 | 0.69595 | 1.9565 | 18.6667 | 0.0006611 | 3561 | 1.15 | 2248 | 0.00079608 | 1666
TASSAJARA 2109CB | TASSAJARA 2109 | 14662109 | FALSE | 4.0225 | 0.02052 | 2.9132 | 42.3333 | 0.00042068 | 6220 | 1.8496 | 1686 | 0.00079537 | 1667
WILLOW CREEK 11015002 | WILLOW CREEK 1101 | 192171101 | FALSE | 13.7441 | 2.2077 | 15.2885 | 251 | 0.00040178 | 6430 | 1.9763 | 1647 | 0.00079518 | 1668
OAKLAND K 1104CR208 | OAKLAND K 1104 | 12101104 | FALSE | 2.3791 | 2.3476 | 4.7267 | 33.5 | 0.00071485 | 2914 | 1.0845 | 2318 | 0.00079474 | 1669
COALINGA NO 1 1109696152 | COALINGA NO 1 1109 | 252161109 |  | 7.9789 | 0.14715 |  | 163 | 0.00016676 | 10516 | 5.35 | 1115 | 0.00079428 | 1670
PACIFICA 1102968736 | PACIFICA 1102 | 22811102 | FALSE | 0.97186 | 0.55159 | 0.85454 | 14.5 | 0.00064172 | 3806 | 1.1372 | 2262 | 0.00079382 | 1671
COTTONWOOD 110335470 | COTTONWOOD 1103 | 102931103 | FALSE | 24.8616 | 0.45547 | 19.7788 | 459.5 | 0.00019064 | 10201 | 4.1713 | 1231 | 0.00079319 | 1672
MONTE RIO 1113346 | MONTE RIO 1113 | 42811113 | FALSE | 9.9691 | 3.1294 | 13.0984 | 181.5 | 0.00067011 | 3434 | 1.3211 | 1988 | 0.00079263 | 1673
ROB ROY 2105796388 | ROB ROY 2105 | 83692105 | FALSE | 5.4695 | 1.5056 | 6.975 | 97 | 0.00068846 | 3241 | 1.15 | 2248 | 0.00079173 | 1674
COTTONWOOD 1102544790 | COTTONWOOD 1102 | 102931102 | FALSE | 17.1463 | 1.6242 | 17.8005 | 295.1667 | 0.00022186 | 9673 | 4.0615 | 1251 | 0.0007912 | 1675
SAUSALITO 1101331806 | SAUSALITO 1101 | 42491101 | TRUE | 0.67958 | 0 | 0.44078 | 8.3333 | 0.00042396 | 6184 | 2.0612 | 1618 | 0.00079034 | 1676
TEMPLETON 2113A08 | TEMPLETON 2113 | 183052113 | FALSE | 24.2837 | 1.7296 | 8.9326 | 448.5 | 0.00018945 | 10223 | 4.1149 | 1240 | 0.00078633 | 1677
CRESCENT MILLS 21012230 | CRESCENT MILLS 2101 | 103132101 | FALSE | 11.1443 | 1.9189 | 6.0917 | 215.5 | 0.00024247 | 9237 | 3.572 | 1297 | 0.00078409 | 1678
PEORIA 170184318 | PEORIA 1701 | 163781701 | FALSE | 10.2 | 2.3566 | 12.5565 | 184 | 0.00036594 | 6904 | 2.1815 | 1585 | 0.00078396 | 1679
MONROE 2107380760 | MONROE 2107 | 43302107 | TRUE | 0.70621 | 0.025609 | 0.61022 | 14 | 0.00048191 | 5582 | 1.7412 | 1726 | 0.00078389 | 1680
VIEJO 22029104 | VIEJO 2202 | 182852202 | FALSE | 5.9376 | 4.8865 | 10.1777 | 95.5 | 0.00074813 | 2502 | 1.0406 | 2354 | 0.00078364 | 1681
RINCON 1104786782 | RINCON 1104 | 43321104 | FALSE | 3.2002 | 1.5571 | 3.1941 | 57.8333 | 0.00079882 | 1980 | 0.95186 | 2447 | 0.00078344 | 1682
RINCON 1101576 | RINCON 1101 | 43321101 | FALSE | 12.8691 | 1.2397 | 3.6255 | 253 | 0.00049821 | 5410 | 1.5938 | 1791 | 0.00077783 | 1683
LAS AROMAS 04013342 | LAS AROMAS 0401 | 13600401 | FALSE | 2.3077 | 1.6907 | 3.9984 | 41 | 0.00062441 | 4005 | 1.2052 | 2130 | 0.00077539 | 1684
DEL MONTE 21049500 | DEL MONTE 2104 | 182222104 | FALSE | 6.724 | 0.64176 | 5.9988 | 124.5 | 0.00034578 | 7211 | 2.2519 | 1567 | 0.00077536 | 1685
WILLOW CREEK 1102CB | WILLOW CREEK 1102 | 192171102 | FALSE | 7.3627 | 0.67827 | 8.041 | 139.1667 | 0.0004149 | 6283 | 1.8562 | 1683 | 0.00077507 | 1686
SAN LUIS OBISPO 1107V02 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 17.7548 | 1.0193 | 18.7741 | 335.5 | 0.00026212 | 8831 | 2.928 | 1406 | 0.00077492 | 1687
MONTE RIO 11131989 | MONTE RIO 1113 | 42811113 | FALSE | 0.74266 | 0.48129 | 1.2239 | 15.5 | 0.00066465 | 3503 | 1.1687 | 2198 | 0.00077473 | 1688
BRUNSWICK 1102CB | BRUNSWICK 1102 | 152481102 | FALSE | 6.2948 | 0.82106 | 6.8515 | 95.4167 | 0.00066256 | 3536 | 1.1951 | 2138 | 0.00077432 | 1689
FRUITLAND 1142899734 | FRUITLAND 1142 | 192311142 | FALSE | 3.4324 | 0.13902 | 3.5714 | 61.5 | 0.00068818 | 3246 | 1.1324 | 2267 | 0.00077343 | 1690
TEMPLETON 2112116402 | TEMPLETON 2112 | 183052112 | FALSE | 7.2233 | 0.11972 | 2.5233 | 131.5 | 0.00011928 | 10957 | 8.0779 | 932 | 0.00077269 | 1691
BEN LOMOND 04015144 | BEN LOMOND 0401 | 83040401 | FALSE | 3.9292 | 0.1117 | 4.0409 | 69.5 | 0.00066143 | 3558 | 1.1613 | 2218 | 0.00077134 | 1692
CURTIS 17036064 | CURTIS 1703 | 163351703 | FALSE | 19.6355 | 1.3876 | 20.0823 | 351.5 | 0.00021368 | 9807 | 4.5401 | 1182 | 0.00077124 | 1693
MADISON 2101484892 | MADISON 2101 | 63172101 | TRUE | 8.064 | 0.78349 | 0.026351 | 159.5 | 0.00024184 | 9250 | 4.5413 | 1181 | 0.00077102 | 1694
CMC 1101CB | CMC 1101 | 183111101 | FALSE | 1.9908 | 0 | 1.9908 | 35.5 | 0.0002462 | 9158 | 3.0576 | 1381 | 0.00077069 | 1695
BRUNSWICK 1105452800 | BRUNSWICK 1105 | 152481105 | FALSE | 0.81559 | 0.18762 | 1.0032 | 18.3333 | 0.00066176 | 3550 | 1.1678 | 2201 | 0.00077005 | 1696
SANTA ROSA A 1111758024 | SANTA ROSA A 1111 | 42151111 | FALSE | 6.4488 | 0.41152 | 4.4406 | 122.5 | 0.00025249 | 9033 | 3.3614 | 1333 | 0.00076926 | 1697
HATTON 11022010 | HATTON 1102 | 182291102 | FALSE | 3.9951 | 0.99471 | 4.9898 | 72.5 | 0.00050839 | 5303 | 2.2418 | 1571 | 0.00076801 | 1698
HALF MOON BAY 1103H80 | HALF MOON BAY 1103 | 24101103 | FALSE | 19.7167 | 2.0408 | 21.7575 | 373.3333 | 0.00041445 | 6291 | 1.8907 | 1673 | 0.0007673 | 1699
MENLO 1102W80 | MENLO 1102 | 24131102 | FALSE | 11.6947 | 0.75995 | 9.414 | 222.8333 | 0.00028221 | 8372 | 2.6188 | 1480 | 0.00076664 | 1700
PLACERVILLE 1111610322 | PLACERVILLE 1111 | 153081111 | TRUE | 0.12306 | 0 | 0.12306 | 2.5 | 0.00090626 | 1205 | 0.93061 | 2466 | 0.00076496 | 1701
LAS GALLINAS A 1105126886 | LAS GALLINAS A 1105 | 42991105 | TRUE | 1.0623 | 0.10407 | 0.48229 | 13.3333 | 0.00063358 | 3897 | 1.2334 | 2079 | 0.00076447 | 1702
EMERALD LAKE 04028872 | EMERALD LAKE 0402 | 24080402 | FALSE | 2.7843 | 1.7765 | 4.5607 | 41 | 0.00056479 | 4711 | 1.3653 | 1956 | 0.00076434 | 1703
SAUSALITO 110284278 | SAUSALITO 1102 | 42491102 | FALSE | 1.5573 | 0.17497 | 1.6662 | 28 | 0.00038915 | 6582 | 2.6018 | 1485 | 0.0007633 | 1704
OAKLAND K 1101CR170 | OAKLAND K 1101 | 12101101 | FALSE | 1.2182 | 1.2833 | 2.5015 | 22 | 0.00080857 | 1907 | 1.0595 | 2335 | 0.0007631 | 1705
JESSUP 11011496 | JESSUP 1101 | 103441101 | FALSE | 19.1245 | 2.2701 | 15.3694 | 341.5 | 0.00025902 | 8905 | 2.7592 | 1446 | 0.00076211 | 1706
MOLINO 1102318 | MOLINO 1102 | 42571102 | FALSE | 25.9296 | 1.8765 | 20.1471 | 478 | 0.00044332 | 5981 | 1.7666 | 1713 | 0.00076096 | 1707
BRUNSWICK 11051030 | BRUNSWICK 1105 | 152481105 | FALSE | 15.6495 | 2.7031 | 18.3526 | 270 | 0.00054534 | 4904 | 1.4128 | 1918 | 0.00076051 | 1708
RED BLUFF 11011556 | RED BLUFF 1101 | 103541101 | FALSE | 39.98 | 1.5257 | 39.0728 | 735.5 | 0.00017156 | 10467 | 4.8469 | 1154 | 0.00075934 | 1709
VIEJO 2203CB | VIEJO 2203 | 182852203 | FALSE | 3.3399 | 1.0142 | 3.2193 | 54.3333 | 0.00077761 | 2177 | 1.0501 | 2343 | 0.00075765 | 1710
ROSSMOOR 1102457174 | ROSSMOOR 1102 | 14161102 | TRUE | 1.2103 | 0 | 0.4469 | 25 | 0.00066628 | 3477 | 1.4696 | 1870 | 0.00075752 | 1711
COVELO 1101694140 | COVELO 1101 | 43061101 |  | 1.5019 | 0 |  | 27.5 | 8.6998e-05 | 11091 | 23.8633 | 476 | 0.00075638 | 1712
GARBERVILLE 11028189 | GARBERVILLE 1102 | 192221102 | FALSE | 0.97544 | 0.096595 | 1.072 | 22 | 0.00033397 | 7396 | 2.255 | 1566 | 0.00075453 | 1713
NORTH DUBLIN 2101MR765 | NORTH DUBLIN 2101 | 14052101 | TRUE | 0.029406 | 0 | 0.029406 | 0.66667 | 0.00061688 | 4088 | 1.2226 | 2098 | 0.00075421 | 1714
VACAVILLE 111112342 | VACAVILLE 1111 | 63601111 | TRUE | 0.12264 | 0 | 0.011497 | 3.8333 | 0.0010492 | 622 | 0.60824 | 2722 | 0.00075398 | 1715
BRUNSWICK 110663124 | BRUNSWICK 1106 | 152481106 | FALSE | 5.9903 | 1.1906 | 7.1809 | 104.3333 | 0.00063049 | 3936 | 1.193 | 2143 | 0.00075391 | 1716
WILLITS 1104504 | WILLITS 1104 | 42661104 | FALSE | 22.6964 | 0.6384 | 23.3347 | 403.5 | 0.00036049 | 6975 | 2.2316 | 1572 | 0.00075086 | 1717
SAN CARLOS 11049052 | SAN CARLOS 1104 | 24181104 | FALSE | 1.9138 | 1.394 | 2.3875 | 32.5 | 0.00049831 | 5408 | 1.6402 | 1774 | 0.00075071 | 1718
SAUSALITO 1102964592 | SAUSALITO 1102 | 42491102 | TRUE | 1.1208 | 0.086533 | 0.38461 | 22.8333 | 0.00076625 | 2307 | 0.98186 | 2412 | 0.00075013 | 1719
MOLINO 110266006 | MOLINO 1102 | 42571102 | FALSE | 8.9373 | 0.98119 | 9.9185 | 176.5 | 0.00054664 | 4893 | 1.3983 | 1929 | 0.00074971 | 1720
MOLINO 1102178 | MOLINO 1102 | 42571102 | FALSE | 13.5224 | 2.4233 | 12.4975 | 253 | 0.00055745 | 4790 | 1.4214 | 1910 | 0.00074802 | 1721
VACAVILLE 111113652 | VACAVILLE 1111 | 63601111 | FALSE | 4.2811 | 0.49698 | 4.7781 | 78 | 0.00036978 | 6844 | 1.9953 | 1636 | 0.00074783 | 1722
STANISLAUS 170275348 | STANISLAUS 1702 | 162821702 | FALSE | 5.3015 | 0.43044 | 5.7319 | 90.3333 | 0.00056956 | 4661 | 1.318 | 1989 | 0.00074658 | 1723
WOODWARD 210878448 | WOODWARD 2108 | 255292108 | FALSE | 29.8275 | 0.49624 | 18.6098 | 559 | 8.6505e-05 | 11093 | 8.9105 | 888 | 0.00074558 | 1724
JAMESON 1103118944 | JAMESON 1103 | 63801103 | FALSE | 5.2737 | 0.18464 | 2.2965 | 91 | 0.00018283 | 10304 | 3.3319 | 1337 | 0.00074554 | 1725
DUNBAR 1102448 | DUNBAR 1102 | 43071102 | FALSE | 8.9571 | 2.6473 | 2.6995 | 157 | 0.00054051 | 4952 | 1.9779 | 1646 | 0.00074549 | 1726
MORAGA 1101669542 | MORAGA 1101 | 13801101 | FALSE | 4.8759 | 0.78986 | 4.0611 | 85.3333 | 0.0005214 | 5162 | 1.3965 | 1932 | 0.00074442 | 1727
COARSEGOLD 2104570682 | COARSEGOLD 2104 | 254432104 | FALSE | 2.1196 | 0.14543 | 2.265 | 39.5 | 0.00018775 | 10237 | 3.8938 | 1263 | 0.00074257 | 1728
OILFIELDS 1103N40 | OILFIELDS 1103 | 182391103 | FALSE | 1.3263 | 0.024278 | 1.3506 | 21.3333 | 0.00015686 | 10632 | 4.5749 | 1177 | 0.00074213 | 1729
DEL MONTE 21043088 | DEL MONTE 2104 | 182222104 | FALSE | 15.1651 | 1.2466 | 16.4116 | 281 | 0.00024838 | 9116 | 3.1879 | 1357 | 0.00074146 | 1730
SAN RAMON 2108CB | SAN RAMON 2108 | 14232108 | TRUE | 9.6997 | 1.1143 | 0.16426 | 177.75 | 0.0003413 | 7285 | 2.7944 | 1437 | 0.00074017 | 1731
WILLITS 1104936096 | WILLITS 1104 | 42661104 | FALSE | 3.0705 | 0.48083 | 3.5513 | 58 | 0.00054498 | 4909 | 1.3516 | 1965 | 0.00073971 | 1732
POTTER VALLEY P H 110564118 | POTTER VALLEY P H 1105 | 42281105 | FALSE | 9.6279 | 0.96496 | 1.2049 | 164.3333 | 0.00030231 | 7960 | 3.6754 | 1288 | 0.00073797 | 1733
FROGTOWN 170275252 | FROGTOWN 1702 | 163451702 | FALSE | 62.3504 | 1.8437 | 59.6167 | 1171.5 | 0.0001204 | 10948 | 6.5503 | 1030 | 0.00073728 | 1734
ORINDA 04013442 | ORINDA 0401 | 12350401 | FALSE | 5.2541 | 2.6137 | 5.2312 | 83.5 | 0.00073101 | 2715 | 1.0888 | 2314 | 0.00073546 | 1735
GOLDTREE 1108CB | GOLDTREE 1108 | 182581108 | FALSE | 4.853 | 1.837 | 2.2237 | 79.5 | 0.0004822 | 5577 | 1.7297 | 1732 | 0.00073457 | 1736
OAKLAND X 1104CR288 | OAKLAND X 1104 | 12541104 | FALSE | 2.6782 | 2.3132 | 4.9914 | 52.8333 | 0.0006805 | 3319 | 1.1336 | 2266 | 0.00073404 | 1737
PARADISE 110599226 | PARADISE 1105 | 102831105 | FALSE | 3.1121 | 1.8495 | 1.4215 | 52.3333 | 0.00054539 | 4903 | 1.3094 | 1999 | 0.00073358 | 1738
MOLINO 1102104 | MOLINO 1102 | 42571102 | FALSE | 21.3386 | 2.0253 | 20.9101 | 412 | 0.00041684 | 6258 | 1.7976 | 1702 | 0.00073176 | 1739
OAKHURST 1101352740 | OAKHURST 1101 | 254421101 | TRUE | 0.31093 | 0 | 0.31093 | 5 | 0.00063579 | 3871 | 1.15 | 2248 | 0.00073116 | 1740
NARROWS 210551582 | NARROWS 2105 | 153132105 | FALSE | 25.2133 | 1.05 | 10.2361 | 455.5 | 0.00013301 | 10857 | 5.3762 | 1112 | 0.00073038 | 1741
HALF MOON BAY 1101818874 | HALF MOON BAY 1101 | 24101101 | FALSE | 6.5901 | 0.36155 | 5.6216 | 130 | 0.00032096 | 7611 | 2.6309 | 1476 | 0.00073011 | 1742
PLACERVILLE 111019582 | PLACERVILLE 1110 | 153081110 | FALSE | 7.0073 | 0.90176 | 7.909 | 121 | 0.00042731 | 6146 | 2.1855 | 1581 | 0.00072882 | 1743
SONOMA 1105229588 | SONOMA 1105 | 42721105 | FALSE | 13.2374 | 0.81202 | 9.524 | 256.5 | 0.00018134 | 10333 | 4.2211 | 1219 | 0.00072853 | 1744
KONOCTI 1102CB | KONOCTI 1102 | 43311102 | FALSE | 9.3202 | 0.40123 | 3.0632 | 160 | 0.00031742 | 7674 | 2.2784 | 1560 | 0.00072818 | 1745
MARTELL 1101803328 | MARTELL 1101 | 163011101 | TRUE | 0.15701 | 0 | 0.13611 | 2 | 0.00037263 | 6794 | 1.9488 | 1657 | 0.00072618 | 1746
EL CERRITO G 1112779030 | EL CERRITO G 1112 | 12501112 | FALSE | 0.66881 | 0.62614 | 0.90506 | 9.8333 | 0.00063105 | 3926 | 1.15 | 2248 | 0.00072571 | 1747
OAKLAND X 1104CR101 | OAKLAND X 1104 | 12541104 | TRUE | 0.025185 | 0 | 0.025185 | 0.33333 | 0.00063076 | 3933 | 1.15 | 2248 | 0.00072538 | 1748
COALINGA NO 2 11059000 | COALINGA NO 2 1105 | 252381105 |  | 11.9392 | 0.16234 |  | 206.5 | 0.00021561 | 9766 | 4.7072 | 1167 | 0.00072396 | 1749
LLAGAS 2104603392 | LLAGAS 2104 | 83182104 | FALSE | 3.2265 | 0.028202 | 2.7112 | 63.5 | 0.00012686 | 10912 | 5.1599 | 1127 | 0.0007226 | 1750
BRUNSWICK 11032784 | BRUNSWICK 1103 | 152481103 | FALSE | 15.4115 | 7.6091 | 21.6761 | 284.5 | 0.00058693 | 4457 | 1.2534 | 2054 | 0.00072231 | 1751
VOLTA 110180454 | VOLTA 1101 | 102541101 | FALSE | 31.9691 | 1.6877 | 32.6569 | 595.5 | 0.00016345 | 10556 | 6.3569 | 1042 | 0.00072124 | 1752
GRASS VALLEY 11012766 | GRASS VALLEY 1101 | 152031101 | FALSE | 3.2574 | 0.34994 | 3.6073 | 58.3333 | 0.00051515 | 5230 | 1.4222 | 1908 | 0.0007198 | 1753
CLOVERDALE 1101112 | CLOVERDALE 1101 | 42821101 |  | 8.848 | 3.9351 |  | 156 | 0.00039988 | 6457 | 4.0092 | 1255 | 0.00071937 | 1754
FITCH MOUNTAIN 1113482752 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 1.7117 | 0.1161 | 1.8278 | 33.5 | 0.00046592 | 5739 | 1.5434 | 1813 | 0.00071778 | 1755
ALTO 11251256 | ALTO 1125 | 42031125 | FALSE | 7.6065 | 4.6349 | 11.7378 | 132.8333 | 0.00053308 | 5038 | 1.428 | 1902 | 0.00071632 | 1756
ALPINE 1101CB | ALPINE 1101 | 163561101 |  | 0.87373 | 0.21018 |  | 15.5 | 0.00044095 | 6002 | 1.5271 | 1825 | 0.00071576 | 1757
TASSAJARA 2108189700 | TASSAJARA 2108 | 14662108 | TRUE | 1.3408 | 0.90366 | 0.25225 | 24.6667 | 0.00066451 | 3506 | 1.3604 | 1959 | 0.00071519 | 1758
IGNACIO 1105683542 | IGNACIO 1105 | 42481105 | TRUE | 0.090863 | 0.08744 | 0.1783 | 3 | 0.00058481 | 4476 | 1.2226 | 2099 | 0.000715 | 1759
HALSEY 110176178 | HALSEY 1101 | 152241101 | FALSE | 20.2719 | 3.6498 | 23.9216 | 374.8333 | 0.00037834 | 6720 | 2.113 | 1602 | 0.0007146 | 1760
ROB ROY 2105821894 | ROB ROY 2105 | 83692105 | FALSE | 2.4187 | 0.15301 | 2.5717 | 42 | 0.00061981 | 4052 | 1.15 | 2248 | 0.00071278 | 1761
PLACERVILLE 1111CB | PLACERVILLE 1111 | 153081111 | FALSE | 1.3727 | 0.30374 | 1.6336 | 18 | 0.00067163 | 3421 | 1.0891 | 2312 | 0.00071234 | 1762
LAKEWOOD 2107474346 | LAKEWOOD 2107 | 13532107 | FALSE | 1.3678 | 0.54845 | 1.2048 | 26 | 0.00049162 | 5478 | 1.6822 | 1751 | 0.00071172 | 1763
RIO DELL 11021504 | RIO DELL 1102 | 192251102 | FALSE | 12.4283 | 0.9311 | 11.3694 | 234.5 | 0.00066788 | 3458 | 1.0489 | 2345 | 0.00071076 | 1764
MIWUK 1701176798 | MIWUK 1701 | 163661701 | FALSE | 2.956 | 0.28672 | 3.2427 | 42 | 0.0006077 | 4199 | 1.1699 | 2194 | 0.00071053 | 1765
HALSEY 11011704 | HALSEY 1101 | 152241101 | FALSE | 13.2874 | 3.0426 | 16.3266 | 229.5 | 0.00038106 | 6686 | 1.9883 | 1639 | 0.00071024 | 1766
FORT ROSS 112137326 | FORT ROSS 1121 | 42851121 | TRUE | 0.48095 | 0.058306 | 0.53926 | 5.5 | 0.00060735 | 4203 | 1.1764 | 2171 | 0.00070996 | 1767
STILLWATER 1102CB | STILLWATER 1102 | 103561102 | FALSE | 25.0809 | 1.9776 | 27.049 | 440.5 | 0.00034098 | 7291 | 2.1085 | 1605 | 0.00070992 | 1768
GARBERVILLE 11021510 | GARBERVILLE 1102 | 192221102 | FALSE | 13.0686 | 1.3097 | 14.3783 | 250 | 0.0004158 | 6267 | 1.8004 | 1701 | 0.00070856 | 1769
ROB ROY 210410954 | ROB ROY 2104 | 83692104 | FALSE | 11.5727 | 2.5316 | 14.1043 | 227.5 | 0.00062037 | 4042 | 1.1356 | 2265 | 0.00070656 | 1770
FRUITLAND 1141200856 | FRUITLAND 1141 | 192311141 | FALSE | 2.5319 | 1.1945 | 3.7264 | 42.5 | 0.00061431 | 4115 | 1.15 | 2248 | 0.00070645 | 1771
HATTON 110137088 | HATTON 1101 | 182291101 | FALSE | 8.6629 | 3.725 | 8.5181 | 203.5 | 0.00036654 | 6893 | 2.5959 | 1487 | 0.00070573 | 1772
SUMMIT 1101742 | SUMMIT 1101 | 152591101 | FALSE | 1.3004 | 0.18596 | 1.4863 | 25 | 0.00059356 | 4375 | 1.2002 | 2134 | 0.00070536 | 1773
MOLINO 1101891 | MOLINO 1101 | 42571101 | FALSE | 3.2905 | 0.69911 | 3.9889 | 63 | 0.00060981 | 4171 | 1.1602 | 2220 | 0.00070524 | 1774
PERRY 1101618168 | PERRY 1101 | 183071101 | FALSE | 1.8577 | 1.0129 | 2.8706 | 23 | 0.00065774 | 3602 | 1.0557 | 2340 | 0.00070423 | 1775
ROB ROY 21055090 | ROB ROY 2105 | 83692105 | FALSE | 9.7511 | 1.3936 | 11.1447 | 171 | 0.00061037 | 4163 | 1.15 | 2248 | 0.00070193 | 1776
OAKHURST 110311900 | OAKHURST 1103 | 254421103 |  | 0.85737 | 0.15215 |  | 19.6667 | 0.00067312 | 3398 | 1.085 | 2317 | 0.00070169 | 1777
PEORIA 170510580 | PEORIA 1705 | 163781705 | FALSE | 11.3227 | 2.7269 | 7.8861 | 210 | 0.00029521 | 8101 | 2.8991 | 1412 | 0.00070132 | 1778
WYANDOTTE 1110980944 | WYANDOTTE 1110 | 102911110 | FALSE | 16.3101 | 1.2482 | 10.7192 | 279 | 0.00045516 | 5867 | 1.5888 | 1795 | 0.00070123 | 1779
BOLINAS 1101528 | BOLINAS 1101 | 42261101 | FALSE | 3.1026 | 2.2811 | 2.8015 | 54.5 | 0.00051554 | 5224 | 1.1668 | 2204 | 0.00070103 | 1780
COARSEGOLD 210410400 | COARSEGOLD 2104 | 254432104 | FALSE | 44.4939 | 3.2898 | 45.0978 | 827.5 | 0.00021089 | 9863 | 3.3052 | 1342 | 0.00070098 | 1781
RIO DELL 11024230 | RIO DELL 1102 | 192251102 | FALSE | 22.6678 | 0.23697 | 22.6738 | 459 | 0.00034844 | 7165 | 2.088 | 1608 | 0.00069762 | 1782
SPENCE 1104965598 | SPENCE 1104 | 182201104 | FALSE | 15.873 | 0.84963 | 9.6044 | 319.5 | 0.00020676 | 9936 | 4.1219 | 1239 | 0.00069626 | 1783
HALF MOON BAY 1103869962 | HALF MOON BAY 1103 | 24101103 | FALSE | 1.0911 | 0.12815 | 0.89754 | 23.5 | 0.00058103 | 4508 | 1.2543 | 2052 | 0.00069385 | 1784
MORAGA 1105553110 | MORAGA 1105 | 13801105 | FALSE | 5.6512 | 0.81201 | 6.4632 | 118 | 0.00049264 | 5468 | 1.381 | 1943 | 0.00069245 | 1785
OAKLAND J 1102CR102 | OAKLAND J 1102 | 12091102 | TRUE | 0.20411 | 0.11399 | 0.3181 | 3.5 | 0.00055298 | 4836 | 1.2745 | 2031 | 0.00069162 | 1786
ROB ROY 2104CB | ROB ROY 2104 | 83692104 | FALSE | 9.6546 | 1.8073 | 11.4618 | 171.8333 | 0.00060056 | 4292 | 1.1508 | 2245 | 0.00069153 | 1787
GARBERVILLE 11022010 | GARBERVILLE 1102 | 192221102 | FALSE | 6.9691 | 0.17992 | 7.149 | 136 | 0.00046684 | 5729 | 1.5523 | 1807 | 0.00069128 | 1788
MIWUK 170110600 | MIWUK 1701 | 163661701 | FALSE | 11.3418 | 3.3022 | 14.644 | 144 | 0.00057327 | 4612 | 1.204 | 2132 | 0.00068962 | 1789
CASTRO VALLEY 1110MR273 | CASTRO VALLEY 1110 | 14091110 | FALSE | 0.70956 | 0.14859 | 0.85814 | 13.5 | 0.00047491 | 5650 | 1.4378 | 1894 | 0.00068884 | 1790
ALTO 1125530664 | ALTO 1125 | 42031125 | FALSE | 2.585 | 1.2276 | 3.1058 | 38.3333 | 0.00057909 | 4535 | 1.6053 | 1784 | 0.00068777 | 1791
REDBUD 1102CB | REDBUD 1102 | 43191102 | FALSE | 0.74087 | 0.053648 | 0.76348 | 13.6667 | 0.00052893 | 5087 | 1.336 | 1978 | 0.00068734 | 1792
HIGGINS 11077559 | HIGGINS 1107 | 152691107 | FALSE | 4.4699 | 0.49662 | 4.9665 | 90 | 0.00020999 | 9874 | 3.3052 | 1341 | 0.00068722 | 1793
BERKELEY F 1103620294 | BERKELEY F 1103 | 12061103 | TRUE | 0.18946 | 0.14708 | 0.12689 | 2.6667 | 0.00072828 | 2748 | 1.1099 | 2290 | 0.00068605 | 1794
COTATI 1105CB | COTATI 1105 | 42271105 | FALSE | 0.73097 | 0.27647 | 1.0074 | 10.25 | 0.00059604 | 4348 | 1.15 | 2249 | 0.00068545 | 1795
BRIDGEVILLE 1102839652 | BRIDGEVILLE 1102 | 192461102 |  | 1.5918 | 0.49115 |  | 27.5 | 0.00054483 | 4913 | 1.2583 | 2048 | 0.00068524 | 1796
RINCON 1102644432 | RINCON 1102 | 43321102 | FALSE | 0.77413 | 0.081962 | 0.85609 | 14.5 | 0.00026992 | 8657 | 2.6174 | 1481 | 0.00068429 | 1797
JESSUP 11019752 | JESSUP 1101 | 103441101 | FALSE | 3.8637 | 0.29205 | 4.0789 | 72.5 | 0.0002765 | 8507 | 2.5833 | 1489 | 0.00068418 | 1798
PLACERVILLE 111219742 | PLACERVILLE 1112 | 153081112 | FALSE | 7.4692 | 2.8962 | 8.7588 | 124.5 | 0.00061729 | 4081 | 1.1471 | 2251 | 0.00068261 | 1799
OAKHURST 1103464622 | OAKHURST 1103 | 254421103 | FALSE | 9.2003 | 3.2476 | 12.4478 | 181.5 | 0.00039518 | 6507 | 1.6838 | 1749 | 0.00068066 | 1800
SANTA YNEZ 1102Y18 | SANTA YNEZ 1102 | 182721102 | FALSE | 7.6117 | 2.056 | 5.0215 | 130.8333 | 0.0002858 | 8291 | 5.5605 | 1101 | 0.00067832 | 1801
BRUNSWICK 111063100 | BRUNSWICK 1110 | 152481110 | FALSE | 4.1577 | 1.5871 | 5.7448 | 67 | 0.00058793 | 4444 | 1.15 | 2248 | 0.00067612 | 1802
CASTRO VALLEY 1110MR748 | CASTRO VALLEY 1110 | 14091110 | FALSE | 6.0498 | 0.65976 | 6.7095 | 118 | 0.00038895 | 6587 | 1.7426 | 1723 | 0.00067611 | 1803
PEORIA 170411232 | PEORIA 1704 | 163781704 | FALSE | 17.1908 | 2.7353 | 13.8006 | 338.5 | 0.00018782 | 10236 | 3.2727 | 1347 | 0.00067537 | 1804
VALLEY VIEW 1106865650 | VALLEY VIEW 1106 | 14341106 | FALSE | 4.5469 | 1.237 | 4.1976 | 89 | 0.00046552 | 5743 | 1.7934 | 1705 | 0.00067422 | 1805
GREENBRAE 11021254 | GREENBRAE 1102 | 43091102 | FALSE | 9.4822 | 10.0512 | 12.4175 | 176.5 | 0.0007433 | 2574 | 0.9654 | 2434 | 0.00067413 | 1806
BRUNSWICK 1103262343 | BRUNSWICK 1103 | 152481103 | FALSE | 0.80074 | 0.40353 | 1.2043 | 14.3333 | 0.00063286 | 3904 | 1.207 | 2127 | 0.00067219 | 1807
ECHO SUMMIT 1101741586 | ECHO SUMMIT 1101 | 158031101 | FALSE | 0.68933 | 0.33703 | 1.0264 | 13 | 0.00047044 | 5695 | 1.4265 | 1903 | 0.00067094 | 1808
SOBRANTE 1101CB | SOBRANTE 1101 | 14671101 | FALSE | 15.4306 | 5.4539 | 18.6741 | 284.5 | 0.00062301 | 4016 | 1.1391 | 2260 | 0.00067088 | 1809
STAFFORD 11011082 | STAFFORD 1101 | 43201101 | FALSE | 3.0687 | 3.1322 | 2.0664 | 44 | 0.00053534 | 5005 | 1.3758 | 1946 | 0.00067088 | 1810
ALTO 1124810594 | ALTO 1124 | 42031124 | FALSE | 0.67148 | 0.28307 | 0.74481 | 6.5 | 0.00069886 | 3115 | 0.89686 | 2488 | 0.00067054 | 1811
CLAYTON 2215184604 | CLAYTON 2215 | 12022215 | FALSE | 10.2784 | 4.9193 | 2.0728 | 160 | 0.00061064 | 4159 | 2.1275 | 1597 | 0.0006705 | 1812
BRUNSWICK 1105733408 | BRUNSWICK 1105 | 152481105 | FALSE | 3.5412 | 1.2567 | 4.7978 | 67.5 | 0.00054193 | 4934 | 1.2457 | 2064 | 0.00066988 | 1813
VIEJO 2201563516 | VIEJO 2201 | 182852201 | FALSE | 6.8606 | 2.7809 | 9.5541 | 128.5 | 0.00060138 | 4285 | 1.1217 | 2277 | 0.00066932 | 1814
ALTO 1124635972 | ALTO 1124 | 42031124 | FALSE | 1.3757 | 1.1726 | 1.4723 | 20.6667 | 0.00087334 | 1400 | 0.68115 | 2658 | 0.00066906 | 1815
SHINGLE SPRINGS 2110CB | SHINGLE SPRINGS 2110 | 153652110 | FALSE | 1.2954 | 0.1165 | 0.79553 | 18 | 0.00077161 | 2242 | 0.89374 | 2490 | 0.00066887 | 1816
ANDERSON 1101583708 | ANDERSON 1101 | 103261101 | FALSE | 0.78484 | 0.70458 | 1.087 | 16.5 | 0.00046944 | 5703 | 1.2928 | 2012 | 0.00066872 | 1817
BIG BASIN 1102CB | BIG BASIN 1102 | 82841102 | FALSE | 0.78715 | 0 | 0.78715 | 14.5 | 0.00058061 | 4512 | 1.15 | 2248 | 0.0006677 | 1818
FRUITLAND 114137410 | FRUITLAND 1141 | 192311141 | FALSE | 1.8517 | 0.22891 | 2.0806 | 40 | 0.00058038 | 4518 | 1.15 | 2248 | 0.00066744 | 1819
CLAYTON 2215CB | CLAYTON 2215 | 12022215 | TRUE | 0.75999 | 0 | 0.0046756 | 15.2 | 0.0013455 | 166 | 0.99297 | 2402 | 0.0006671 | 1820
SAN LUIS OBISPO 1107456456 | SAN LUIS OBISPO 1107 | 182631107 |  | 0.018898 | 0 |  | 0.5 | 0.00057971 | 4523 | 1.15 | 2248 | 0.00066667 | 1821
DEL MONTE 21042760 | DEL MONTE 2104 | 182222104 | FALSE | 2.695 | 0.1312 | 2.8262 | 44.5833 | 0.00027383 | 8556 | 2.4464 | 1521 | 0.00066604 | 1822
STANISLAUS 1702L3151 | STANISLAUS 1702 | 162821702 | FALSE | 0.99134 | 0.15324 | 1.1446 | 24.5 | 0.00046766 | 5720 | 1.4449 | 1891 | 0.00066532 | 1823
CASTRO VALLEY 1110MR243 | CASTRO VALLEY 1110 | 14091110 | FALSE | 5.5797 | 3.2414 | 8.802 | 95.5 | 0.00054254 | 4928 | 1.2483 | 2059 | 0.00066496 | 1824
ELK 1101CB | ELK 1101 | 42981101 | TRUE | 0.026371 | 0 | 0.0077088 | 0.5 | 0.00041766 | 6245 | 1.5857 | 1796 | 0.00066228 | 1825
HALSEY 11022514 | HALSEY 1102 | 152241102 | FALSE | 19.5038 | 5.3387 | 11.6403 | 353.5 | 0.0004942 | 5449 | 4.344 | 1205 | 0.0006619 | 1826
OAKLAND X 1106CR266 | OAKLAND X 1106 | 12541106 | FALSE | 1.1607 | 0.11757 | 1.2782 | 22.5 | 0.00052973 | 5077 | 1.2339 | 2078 | 0.00066135 | 1827
CALAVERAS CEMENT 110136880 | CALAVERAS CEMENT 1101 | 162211101 | FALSE | 8.5971 | 1.1248 | 6.0506 | 158.5 | 0.00022745 | 9551 | 5.5713 | 1100 | 0.00066131 | 1828
GARBERVILLE 11011750 | GARBERVILLE 1101 | 192221101 | FALSE | 8.2294 | 0.72878 | 8.9582 | 162.5 | 0.000421 | 6214 | 1.5334 | 1819 | 0.00066075 | 1829
HALF MOON BAY 1103341542 | HALF MOON BAY 1103 | 24101103 | FALSE | 2.1255 | 0.19457 | 1.6882 | 44 | 0.00041941 | 6231 | 1.5332 | 1820 | 0.00066048 | 1830
OTTER 1102CB | OTTER 1102 | 182941102 | FALSE | 6.6213 | 0.32438 | 6.8815 | 135.5 | 0.00027003 | 8652 | 2.6503 | 1472 | 0.00065977 | 1831
ALHAMBRA 110582622 | ALHAMBRA 1105 | 14101105 | FALSE | 25.5065 | 1.403 | 26.9094 | 466.5 | 0.000208 | 9914 | 2.6424 | 1474 | 0.00065872 | 1832
OAKLAND J 1102CR184 | OAKLAND J 1102 | 12091102 | FALSE | 3.4289 | 2.7949 | 6.2238 | 56 | 0.00057168 | 4634 | 1.1394 | 2259 | 0.00065588 | 1833
ROB ROY 2104464844 | ROB ROY 2104 | 83692104 | FALSE | 3.3413 | 0.14326 | 3.4846 | 64.5 | 0.00056072 | 4747 | 1.165 | 2207 | 0.00065476 | 1834
TIVY VALLEY 1107822606 | TIVY VALLEY 1107 | 252941107 | FALSE | 36.8003 | 1.7974 | 12.4202 | 686 | 0.00013241 | 10863 | 6.8034 | 1012 | 0.00065371 | 1835
HATTON 1101CB | HATTON 1101 | 182291101 | FALSE | 1.9162 | 0.46172 | 2.3779 | 34.8333 | 0.00056714 | 4690 | 1.15 | 2247 | 0.00065222 | 1836
STANISLAUS 17024905 | STANISLAUS 1702 | 162821702 | FALSE | 2.3017 | 0.13994 | 2.4416 | 39.8333 | 0.00048647 | 5532 | 1.3524 | 1964 | 0.00064982 | 1837
FORT SEWARD 1122CB | FORT SEWARD 1122 | 192321122 | FALSE | 21.8263 | 1.2607 | 16.1328 | 423.5 | 0.00022286 | 9649 | 3.0433 | 1387 | 0.0006484 | 1838
WILLOW CREEK 11013050 | WILLOW CREEK 1101 | 192171101 | FALSE | 2.6244 | 0.088367 | 2.7128 | 52.5 | 0.00028937 | 8209 | 2.1832 | 1584 | 0.00064837 | 1839
EL CERRITO G 1112418480 | EL CERRITO G 1112 | 12501112 | FALSE | 0.73585 | 0.6191 | 1.3428 | 11.3333 | 0.00060373 | 4258 | 0.95794 | 2440 | 0.0006482 | 1840
HALF MOON BAY 1103623460 | HALF MOON BAY 1103 | 24101103 | FALSE | 8.3188 | 0.20535 | 8.5242 | 161.5 | 0.00017155 | 10468 | 3.7546 | 1276 | 0.00064754 | 1841
LAS AROMAS 0401LA401R | LAS AROMAS 0401 | 13600401 | FALSE | 3.8621 | 2.6809 | 5.0375 | 68 | 0.00078087 | 2142 | 0.83756 | 2533 | 0.00064723 | 1842
MOLINO 1102495692 | MOLINO 1102 | 42571102 | FALSE | 15.9229 | 2.4775 | 18.4004 | 306.5 | 0.00042129 | 6211 | 1.4696 | 1871 | 0.00064684 | 1843
ELECTRA 11011238 | ELECTRA 1101 | 162161101 | FALSE | 1.2588 | 0.075469 | 0.92474 | 24.1667 | 0.00054061 | 4950 | 1.414 | 1916 | 0.00064668 | 1844
WINDSOR 1103701650 | WINDSOR 1103 | 43501103 | FALSE | 0.72613 | 0.033132 | 0.75926 | 15 | 0.00041308 | 6303 | 2.2846 | 1558 | 0.00064649 | 1845
BRIDGEVILLE 1102384530 | BRIDGEVILLE 1102 | 192461102 | FALSE | 3.6622 | 0.15633 | 3.8186 | 76 | 0.00049864 | 5402 | 1.2651 | 2037 | 0.00064558 | 1846
CLARKSVILLE 2103593454 | CLARKSVILLE 2103 | 153612103 | FALSE | 41.0936 | 1.2997 | 31.0196 | 787 | 0.00014283 | 10765 | 4.5008 | 1187 | 0.00064539 | 1847
HIGGINS 11039753 | HIGGINS 1103 | 152691103 | FALSE | 2.0132 | 0.20525 | 2.2185 | 35.5 | 0.00018402 | 10290 | 3.7468 | 1277 | 0.0006453 | 1848
ROSSMOOR 1109847274 | ROSSMOOR 1109 | 14161109 | FALSE | 7.7471 | 0.12412 | 0.96277 | 130 | 0.00032728 | 7499 | 2.3514 | 1542 | 0.00064456 | 1849
COVELO 110137328 | COVELO 1101 | 43061101 |  | 17.9688 | 0.99371 |  | 314.3333 | 0.00020694 | 9932 | 5.8489 | 1082 | 0.00064448 | 1850
SAN JOAQUIN #2 110310320 | SAN JOAQUIN #2 1103 | 252521103 | FALSE | 11.6637 | 0.74805 | 12.4117 | 215 | 0.00025892 | 8907 | 2.7452 | 1449 | 0.00064313 | 1851
LLAGAS 2107374344 | LLAGAS 2107 | 83182107 | FALSE | 12.9525 | 1.3498 | 5.4739 | 230.5 | 0.00026901 | 8676 | 2.9102 | 1410 | 0.00064307 | 1852
JESSUP 11021550 | JESSUP 1102 | 103441102 | FALSE | 28.3195 | 2.5628 | 18.8709 | 501 | 0.00020898 | 9893 | 3.5324 | 1311 | 0.00063997 | 1853
CLOVERDALE 1102736078 | CLOVERDALE 1102 | 42821102 | TRUE | 0.26381 | 0 | 0.17757 | 5.5 | 0.00019598 | 10114 | 5.1915 | 1123 | 0.00063995 | 1854
EDES 1112CR312 | EDES 1112 | 13681112 | FALSE | 3.6656 | 2.2072 | 5.8149 | 60.6667 | 0.00061214 | 4143 | 1.066 | 2332 | 0.00063966 | 1855
FRUITLAND 114195324 | FRUITLAND 1141 | 192311141 | FALSE | 6.4841 | 0.28509 | 6.7691 | 122 | 0.00052363 | 5146 | 1.2241 | 2094 | 0.00063839 | 1856
NORTH DUBLIN 2103CB | NORTH DUBLIN 2103 | 14052103 | FALSE | 21.1539 | 3.8148 | 14.141 | 363.8333 | 0.00021643 | 9756 | 4.1272 | 1238 | 0.00063767 | 1857
WOODSIDE 1104555372 | WOODSIDE 1104 | 24251104 | FALSE | 4.9554 | 4.0804 | 7.2824 | 79 | 0.00048763 | 5524 | 1.3741 | 1948 | 0.00063744 | 1858
LAYTONVILLE 1102500 | LAYTONVILLE 1102 | 42681102 | FALSE | 29.4812 | 0.9849 | 20.4716 | 562.5 | 0.00015564 | 10641 | 4.3468 | 1203 | 0.00063677 | 1859
ROB ROY 210571630 | ROB ROY 2105 | 83692105 | FALSE | 1.8798 | 1.2943 | 1.6283 | 29.5 | 0.00062065 | 4040 | 0.96585 | 2432 | 0.00063602 | 1860
WYANDOTTE 110796390 | WYANDOTTE 1107 | 102911107 | FALSE | 10.1233 | 1.0144 | 9.2377 | 173 | 0.00022186 | 9672 | 4.4657 | 1192 | 0.00063511 | 1861
OAKLAND K 110217430 | OAKLAND K 1102 | 12101102 | FALSE | 1.4558 | 0 | 1.4558 | 28.5 | 0.00050377 | 5351 | 1.2621 | 2040 | 0.00063489 | 1862
FRUITLAND 1141CB | FRUITLAND 1141 | 192311141 | FALSE | 3.1636 | 0.070721 | 3.2343 | 61 | 0.000538 | 4977 | 1.181 | 2159 | 0.00063272 | 1863
HALF MOON BAY 110258448 | HALF MOON BAY 1102 | 24101102 | FALSE | 4.8627 | 0.044896 | 3.2643 | 95.3333 | 0.00028104 | 8398 | 2.8632 | 1421 | 0.00063179 | 1864
MERCED FALLS 1102482838 | MERCED FALLS 1102 | 252811102 | FALSE | 10.8868 | 0.24981 | 8.1054 | 219.5 | 0.00022789 | 9537 | 3.5149 | 1314 | 0.00063151 | 1865
PEORIA 17056697 | PEORIA 1705 | 163781705 | FALSE | 4.1329 | 0.33466 | 4.4597 | 73 | 0.00034427 | 7231 | 2.2846 | 1557 | 0.00063132 | 1866
OREGON TRAIL 1103CB | OREGON TRAIL 1103 | 103521103 | FALSE | 2.9158 | 0.40622 | 3.0096 | 58 | 0.0004628 | 5775 | 1.3572 | 1963 | 0.00063024 | 1867
ROSSMOOR 11018132 | ROSSMOOR 1101 | 14161101 | FALSE | 3.6212 | 1.9861 | 3.9171 | 72.5 | 0.00053786 | 4978 | 1.2606 | 2042 | 0.00062996 | 1868
BRUNSWICK 11052100 | BRUNSWICK 1105 | 152481105 | FALSE | 3.9864 | 0.21202 | 4.1984 | 77 | 0.00045488 | 5872 | 1.4037 | 1923 | 0.0006299 | 1869
CAYUCOS 1102613456 | CAYUCOS 1102 | 182551102 | FALSE | 23.3764 | 0.62425 | 12.4077 | 469.8333 | 0.00010736 | 11024 | 6.22 | 1049 | 0.00062892 | 1870
ALTO 1124246034 | ALTO 1124 | 42031124 | TRUE | 0.2547 | 0.29906 | 0.20847 | 4.3333 | 0.0010875 | 503 | 0.55935 | 2773 | 0.00062849 | 1871
PAUL SWEET 2104885736 | PAUL SWEET 2104 | 83252104 | FALSE | 3.1112 | 1.4023 | 4.2303 | 47.5 | 0.00094052 | 1049 | 0.76274 | 2591 | 0.00062811 | 1872
SEACLIFF 0401CB | SEACLIFF 0401 | 83500401 | FALSE | 5.9063 | 1.0515 | 6.6517 | 117.6667 | 0.00057831 | 4549 | 1.0973 | 2306 | 0.00062796 | 1873
MAXWELL 11053008 | MAXWELL 1105 | 62881105 | FALSE | 15.2749 | 0.55327 | 4.005 | 294.5 | 0.0001126 | 11000 | 6.0889 | 1065 | 0.00062596 | 1874
PAUL SWEET 2106607772 | PAUL SWEET 2106 | 83252106 | FALSE | 7.0288 | 1.3768 | 6.2405 | 125.3333 | 0.00058892 | 4428 | 1.0225 | 2367 | 0.00062534 | 1875
SAN RAFAEL 1101189400 | SAN RAFAEL 1101 | 42011101 | FALSE | 3.4549 | 2.9144 | 4.9406 | 48.1667 | 0.00080639 | 1926 | 0.81599 | 2547 | 0.00062462 | 1876
HALSEY 11015731 | HALSEY 1101 | 152241101 | FALSE | 3.1154 | 0.58895 | 3.7044 | 58 | 0.00046438 | 5757 | 1.3378 | 1977 | 0.00062315 | 1877
GEYSERVILLE 110137454 | GEYSERVILLE 1101 | 42891101 | FALSE | 12.0506 | 0.37482 | 6.3766 | 223 | 0.00028119 | 8395 | 3.436 | 1325 | 0.00062298 | 1878
SHINGLE SPRINGS 1104CB | SHINGLE SPRINGS 1104 | 153651104 | FALSE | 2.3072 | 0.34344 | 0.72556 | 29.5 | 0.00064459 | 3770 | 1.1871 | 2148 | 0.00062256 | 1879
ALTO 1125296476 | ALTO 1125 | 42031125 | FALSE | 0.73678 | 0.71708 | 0.99396 | 14.3333 | 0.00065787 | 3599 | 1.0322 | 2359 | 0.00062247 | 1880
DIABLO CANYON 1101CB | DIABLO CANYON 1101 | 189001101 | TRUE | 0 | 0.039914 | 0.039914 | 2 | 0.00028653 | 8274 | 2.1666 | 1588 | 0.00062139 | 1881
MARTELL 110368192 | MARTELL 1103 | 163011103 | FALSE | 6.3204 | 1.8665 | 2.6801 | 94.5 | 0.00050745 | 5309 | 2.2837 | 1559 | 0.000618 | 1882
ANDERSON 1101909424 | ANDERSON 1101 | 103261101 | TRUE | 0.39912 | 0 | 0.39912 | 8.5 | 0.00052135 | 5163 | 1.1756 | 2174 | 0.00061792 | 1883
SAN RAFAEL 1107CB | SAN RAFAEL 1107 | 42011107 | FALSE | 7.8173 | 6.5518 | 7.75 | 131.6667 | 0.00089742 | 1249 | 0.71559 | 2629 | 0.00061734 | 1884
PIT NO 1 11013312 | PIT NO 1 1101 | 103721101 | FALSE | 9.0791 | 1.2375 | 8.3883 | 166.5 | 0.00012932 | 10886 | 7.068 | 993 | 0.00061671 | 1885
TAMARACK 1101CB | TAMARACK 1101 | 152291101 | FALSE | 19.5842 | 3.361 | 21.9115 | 354 | 0.00041666 | 6260 | 1.4695 | 1872 | 0.00061517 | 1886
ALTO 1124428 | ALTO 1124 | 42031124 |  | 2.362 | 1.74 |  | 30.6667 | 0.00088294 | 1349 | 0.61914 | 2713 | 0.00061486 | 1887
STELLING 1110881330 | STELLING 1110 | 83481110 |  | 0.67967 | 0.055016 |  | 14.3333 | 0.00041548 | 6270 | 1.698 | 1743 | 0.0006133 | 1888
BRIDGEVILLE 1101365380 | BRIDGEVILLE 1101 | 192461101 | FALSE | 4.9897 | 0.24969 | 5.2393 | 100 | 0.00029123 | 8177 | 2.0869 | 1612 | 0.00061204 | 1889
REDBUD 1101400 | REDBUD 1101 | 43191101 | FALSE | 1.0253 | 0.60149 | 1.1381 | 18.5 | 0.00047683 | 5629 | 1.3431 | 1972 | 0.00061196 | 1890
SHINGLE SPRINGS 2109CB | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 27.7123 | 2.5879 | 29.6152 | 491.6667 | 0.00041043 | 6328 | 1.3599 | 1960 | 0.00061034 | 1891
VACAVILLE 1111905076 | VACAVILLE 1111 | 63601111 | TRUE | 0.78189 | 0.075345 | 0.15661 | 15 | 0.00053115 | 5058 | 1.0576 | 2337 | 0.00060863 | 1892
VIEJO 2204CB | VIEJO 2204 | 182852204 | FALSE | 2.4653 | 0.17456 | 2.4119 | 39.3333 | 0.00053877 | 4970 | 1.1361 | 2264 | 0.00060831 | 1893
HOOPA 110137202 | HOOPA 1101 | 192401101 | FALSE | 28.1989 | 0.93767 | 24.931 | 555.5 | 0.0003421 | 7273 | 1.7246 | 1734 | 0.00060814 | 1894
PLACER 1102CB | PLACER 1102 | 152461102 | FALSE | 2.1226 | 0.31176 | 2.1715 | 34.1667 | 0.00062171 | 4027 | 1.0801 | 2323 | 0.00060505 | 1895
GUALALA 1111CB | GUALALA 1111 | 42841111 | FALSE | 3.9221 | 0.28692 | 4.209 | 75 | 0.00052383 | 5144 | 1.1544 | 2234 | 0.00060452 | 1896
TASSAJARA 2112D514R | TASSAJARA 2112 | 14662112 | TRUE | 1.4683 | 0.29019 | 0.58213 | 27 | 0.00090607 | 1206 | 0.80524 | 2552 | 0.00060336 | 1897
GEYSERVILLE 1102537096 | GEYSERVILLE 1102 | 42891102 | TRUE | 0.59314 | 0 | 0.46929 | 11.3333 | 0.0002439 | 9200 | 2.5983 | 1486 | 0.0006023 | 1898
CORNING 110290036 | CORNING 1102 | 103331102 | FALSE | 14.2664 | 0.36174 | 12.6339 | 264.5 | 0.00015481 | 10648 | 4.1012 | 1245 | 0.00060102 | 1899
NOTRE DAME 1103317782 | NOTRE DAME 1103 | 102041103 | TRUE | 4.1904 | 0.20204 | 0.60986 | 85.5 | 0.00036756 | 6878 | 6.0482 | 1069 | 0.00060063 | 1900
BRUNSWICK 1103956424 | BRUNSWICK 1103 | 152481103 | FALSE | 1.6482 | 0.54893 | 1.1803 | 31.5 | 0.00056287 | 4728 | 1.0749 | 2328 | 0.00059987 | 1901
BRUNSWICK 110456468 | BRUNSWICK 1104 | 152481104 | FALSE | 6.7601 | 2.8714 | 7.7303 | 117.8333 | 0.00056948 | 4662 | 1.2323 | 2080 | 0.00059921 | 1902
GOLDTREE 1105CB | GOLDTREE 1105 | 182581105 | FALSE | 9.3941 | 0.83893 | 6.9998 | 179.6667 | 0.00030005 | 8017 | 3.5162 | 1313 | 0.00059698 | 1903
GARBERVILLE 11012026 | GARBERVILLE 1101 | 192221101 | FALSE | 6.2533 | 0.33969 | 6.593 | 133.5 | 0.00045775 | 5836 | 1.3445 | 1971 | 0.00059656 | 1904
VIEJO 22019698 | VIEJO 2201 | 182852201 | FALSE | 0.67384 | 0.49066 | 0.79858 | 14 | 0.00051759 | 5200 | 1.15 | 2248 | 0.00059523 | 1905
ROSSMOOR 1101L503R | ROSSMOOR 1101 | 14161101 | FALSE | 4.2664 | 3.1948 | 7.4611 | 72.3333 | 0.00054625 | 4898 | 1.1047 | 2300 | 0.00059467 | 1906
SILVERADO 2102714 | SILVERADO 2102 | 43432102 | FALSE | 10.9098 | 1.5068 | 3.2013 | 217.5 | 0.00057894 | 4537 | 1.0714 | 2331 | 0.00059404 | 1907
VASCO 1102886522 | VASCO 1102 | 13751102 | FALSE | 19.0163 | 0.46015 | 6.5753 | 335.5 | 0.00010036 | 11048 | 7.2005 | 985 | 0.00059344 | 1908
VOLTA 1102453266 | VOLTA 1102 | 102541102 | TRUE | 0.333 | 0 | 0.333 | 6 | 0.00045771 | 5837 | 1.2952 | 2009 | 0.00059284 | 1909
BRUNSWICK 111094368 | BRUNSWICK 1110 | 152481110 | TRUE | 0.4648 | 0.027456 | 0.31912 | 6.3333 | 0.0006176 | 4077 | 0.97982 | 2415 | 0.00059164 | 1910
MOLINO 1102189602 | MOLINO 1102 | 42571102 | FALSE | 0.6452 | 0.10471 | 0.7499 | 13.5 | 0.00051413 | 5242 | 1.15 | 2248 | 0.00059125 | 1911
GARBERVILLE 11028652 | GARBERVILLE 1102 | 192221102 | FALSE | 13.3138 | 0.44425 | 13.758 | 258 | 0.00048814 | 5513 | 1.2152 | 2111 | 0.00059107 | 1912
LUCERNE 1103630 | LUCERNE 1103 | 43351103 | FALSE | 13.5748 | 4.7033 | 16.1339 | 202.8333 | 0.00042253 | 6201 | 1.5148 | 1833 | 0.00059015 | 1913
WILLITS 1104CB | WILLITS 1104 | 42661104 | FALSE | 7.6593 | 1.517 | 3.4435 | 130.3333 | 0.00035379 | 7079 | 1.7379 | 1728 | 0.00058984 | 1914
FULTON 110777670 | FULTON 1107 | 42561107 | FALSE | 6.8332 | 2.0149 | 8.3642 | 119.5 | 0.00042591 | 6164 | 1.4549 | 1884 | 0.00058966 | 1915
BRENTWOOD 210596324 | BRENTWOOD 2105 | 14592105 | TRUE | 0.46327 | 0.027197 | 0.49046 | 8 | 0.00037174 | 6814 | 1.5857 | 1796 | 0.00058947 | 1916
HATTON 11012654 | HATTON 1101 | 182291101 | FALSE | 1.8082 | 0.99429 | 2.7944 | 31.5 | 0.00052831 | 5094 | 1.1152 | 2281 | 0.00058884 | 1917
NORTH DUBLIN 2101CB | NORTH DUBLIN 2101 | 14052101 | FALSE | 1.4419 | 0 | 1.3758 | 15.5 | 0.00061208 | 4144 | 1.0822 | 2320 | 0.00058858 | 1918
COARSEGOLD 2103CB | COARSEGOLD 2103 | 254432103 | FALSE | 38.3805 | 2.2332 | 40.6125 | 711.3333 | 0.00029626 | 8079 | 2.2429 | 1570 | 0.00058726 | 1919
MORAGA 1104750618 | MORAGA 1104 | 13801104 | FALSE | 0.98794 | 0.71935 | 1.5279 | 10.5 | 0.00085159 | 1566 | 0.66569 | 2673 | 0.0005867 | 1920
EDES 1112CR306 | EDES 1112 | 13681112 | FALSE | 1.0087 | 0.64594 | 1.6546 | 19 | 0.00063906 | 3839 | 0.86666 | 2512 | 0.00058658 | 1921
SEACLIFF 040112946 | SEACLIFF 0401 | 83500401 | FALSE | 3.2254 | 1.7626 | 3.0747 | 51.5 | 0.00058819 | 4438 | 0.97977 | 2416 | 0.00058398 | 1922
VACAVILLE 110847860 | VACAVILLE 1108 | 63601108 | TRUE | 3.8755 | 2.1226 | 0.31452 | 61.8333 | 0.00090588 | 1208 | 0.99236 | 2403 | 0.00058319 | 1923
KONOCTI 11084041 | KONOCTI 1108 | 43311108 | FALSE | 4.7027 | 2.8286 | 1.8569 | 69 | 0.00034492 | 7222 | 1.7385 | 1727 | 0.00058288 | 1924
FORT ROSS 1121204 | FORT ROSS 1121 | 42851121 | FALSE | 19.621 | 0.11558 | 19.7366 | 393 | 0.00019624 | 10111 | 3.1686 | 1361 | 0.0005805 | 1925
HIGGINS 110950072 | HIGGINS 1109 | 152691109 | FALSE | 55.5155 | 1.4438 | 43.7069 | 1002 | 0.00014946 | 10710 | 3.9598 | 1259 | 0.00057963 | 1926
ATASCADERO 1103CB | ATASCADERO 1103 | 182541103 | TRUE | 1.3508 | 0.34616 | 0.03889 | 24 | 0.00053531 | 5006 | 0.88954 | 2491 | 0.00057918 | 1927
JAMESON 11059472 | JAMESON 1105 | 63801105 | FALSE | 7.2592 | 0.7974 | 2.3358 | 136.5 | 0.00040853 | 6350 | 1.2034 | 2133 | 0.00057842 | 1928
CRESCENT MILLS 21012562 | CRESCENT MILLS 2101 | 103132101 | FALSE | 34.8619 | 1.4237 | 15.9936 | 659 | 0.00017891 | 10366 | 3.1112 | 1370 | 0.00057717 | 1929
GANSNER 1101590690 | GANSNER 1101 | 103021101 | TRUE | 0.22388 | 0.045629 | 0.058447 | 2 | 0.00050174 | 5375 | 1.15 | 2248 | 0.00057701 | 1930
MORAGA 1104CB | MORAGA 1104 | 13801104 | FALSE | 15.5565 | 9.617 | 14.727 | 274.75 | 0.00061018 | 4166 | 1.0037 | 2388 | 0.0005766 | 1931
WILLOW CREEK 110129362 | WILLOW CREEK 1101 | 192171101 | FALSE | 11.4255 | 0.15621 | 7.1322 | 220 | 0.00040921 | 6343 | 1.297 | 2005 | 0.00057635 | 1932
ROSSMOOR 110168920 | ROSSMOOR 1101 | 14161101 | FALSE | 7.3247 | 2.471 | 8.1678 | 124.6667 | 0.00056914 | 4672 | 0.9806 | 2413 | 0.00057509 | 1933
BIG RIVER 1101262924 | BIG RIVER 1101 | 43081101 | FALSE | 1.8829 | 0.56372 | 2.3403 | 33 | 0.00049954 | 5395 | 1.15 | 2248 | 0.00057447 | 1934
PEABODY 2113945670 | PEABODY 2113 | 63642113 | TRUE | 0.25047 | 0 | 0.17627 | 4.5 | 0.0003078 | 7851 | 2.1933 | 1578 | 0.00057388 | 1935
ALTO 112081716 | ALTO 1120 | 42031120 | TRUE | 0.25274 | 0.1643 | 0.41704 | 5.3333 | 0.00047219 | 5676 | 1.2181 | 2105 | 0.00057363 | 1936
LUCERNE 1103CB | LUCERNE 1103 | 43351103 | FALSE | 4.4464 | 1.4062 | 2.2958 | 78.3333 | 0.00047398 | 5660 | 1.2497 | 2057 | 0.00057129 | 1937
GARBERVILLE 110139524 | GARBERVILLE 1101 | 192221101 | FALSE | 15.3555 | 1.4359 | 4.4813 | 280 | 0.00041328 | 6299 | 1.4602 | 1878 | 0.0005711 | 1938
BRUNSWICK 1103851116 | BRUNSWICK 1103 | 152481103 | TRUE | 0.25963 | 0.20463 | 0.41476 | 6 | 0.00049104 | 5487 | 1.1863 | 2152 | 0.0005704 | 1939
HALF MOON BAY 11038894 | HALF MOON BAY 1103 | 24101103 | FALSE | 11.0414 | 1.0821 | 11.8178 | 207 | 0.00046995 | 5700 | 1.2103 | 2117 | 0.00056956 | 1940
CAMP EVERS 2103449218 | CAMP EVERS 2103 | 83622103 | FALSE | 4.2603 | 1.1702 | 1.4813 | 70.5 | 0.00090628 | 1204 | 0.49749 | 2824 | 0.00056942 | 1941
PLACER 1103CB | PLACER 1103 | 152461103 | FALSE | 9.0844 | 1.5982 | 7.5432 | 154 | 0.00040116 | 6438 | 1.6744 | 1755 | 0.00056937 | 1942
CHESTER 11022564 | CHESTER 1102 | 103181102 | FALSE | 2.2391 | 0.29807 | 2.5184 | 47.5 | 0.00048579 | 5544 | 1.1798 | 2163 | 0.00056922 | 1943
WYANDOTTE 1107219854 | WYANDOTTE 1107 | 102911107 | TRUE | 0.34953 | 0.12535 | 0.084609 | 3.5 | 0.00095355 | 998 | 0.76887 | 2585 | 0.00056902 | 1944
WYANDOTTE 11031504 | WYANDOTTE 1103 | 102911103 | FALSE | 14.7086 | 1.8678 | 11.3976 | 255.5 | 0.00043233 | 6088 | 1.3685 | 1951 | 0.0005689 | 1945
SUMMIT 11022302 | SUMMIT 1102 | 152591102 | FALSE | 1.337 | 0.10944 | 1.4465 | 25.5 | 0.00041539 | 6274 | 1.3579 | 1962 | 0.00056666 | 1946
PAUL SWEET 2106CB | PAUL SWEET 2106 | 83252106 | FALSE | 24.2863 | 4.8964 | 5.252 | 399.3333 | 0.00064521 | 3762 | 0.88403 | 2498 | 0.00056662 | 1947
GARBERVILLE 11022500 | GARBERVILLE 1102 | 192221102 | FALSE | 15.863 | 0.53851 | 16.4014 | 314 | 0.00033888 | 7331 | 1.7114 | 1739 | 0.00056639 | 1948
PLACERVILLE 11118582 | PLACERVILLE 1111 | 153081111 | FALSE | 10.088 | 2.3549 | 10.8727 | 182.8333 | 0.00041586 | 6266 | 1.3174 | 1992 | 0.00056623 | 1949
PETALUMA C 1109259100 | PETALUMA C 1109 | 42631109 | FALSE | 1.7189 | 0.13058 | 1.8495 | 33.5 | 0.00027295 | 8583 | 2.0877 | 1611 | 0.00056616 | 1950
HIGGINS 1109594 | HIGGINS 1109 | 152691109 | FALSE | 20.4737 | 1.7592 | 22.029 | 363.5 | 0.00026764 | 8706 | 2.6427 | 1473 | 0.00056537 | 1951
COARSEGOLD 210410335 | COARSEGOLD 2104 | 254432104 | FALSE | 5.8089 | 0.30826 | 6.1171 | 109.5 | 0.00030538 | 7902 | 1.8503 | 1685 | 0.00056512 | 1952
SHINGLE SPRINGS 210551738 | SHINGLE SPRINGS 2105 | 153652105 | TRUE | 1.146 | 0.14123 | 0.016579 | 19 | 0.00063629 | 3867 | 0.68599 | 2655 | 0.00056455 | 1953
CORRAL 110236666 | CORRAL 1102 | 162991102 | FALSE | 18.112 | 1.2837 | 17.8793 | 353.5 | 0.00017179 | 10462 | 3.3715 | 1332 | 0.00056378 | 1954
FORT ROSS 1121CB | FORT ROSS 1121 | 42851121 | TRUE | 0.016114 | 0 | 0.016114 | 0.5 | 0.00029973 | 8024 | 1.8762 | 1678 | 0.00056234 | 1955
OREGON TRAIL 110249144 | OREGON TRAIL 1102 | 103521102 | FALSE | 21.2023 | 2.109 | 19.4037 | 369.5 | 0.00043464 | 6064 | 1.4967 | 1849 | 0.00056229 | 1956
BRUNSWICK 1105963830 | BRUNSWICK 1105 | 152481105 | FALSE | 3.939 | 0.13897 | 4.0779 | 73 | 0.00036973 | 6845 | 1.522 | 1826 | 0.00056159 | 1957
GARBERVILLE 1101574630 | GARBERVILLE 1101 | 192221101 | FALSE | 4.947 | 0.32628 | 5.2732 | 98 | 0.00042624 | 6156 | 1.3117 | 1998 | 0.00056081 | 1958
FITCH MOUNTAIN 1113583202 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 9.8232 | 1.037 | 5.1637 | 183.5 | 0.00043353 | 6078 | 1.4426 | 1892 | 0.00056033 | 1959
HALSEY 1101CB | HALSEY 1101 | 152241101 | FALSE | 17.248 | 3.5946 | 20.8425 | 331.1667 | 0.0003861 | 6629 | 1.4692 | 1874 | 0.00056028 | 1960
WATERSHED 0402CB | WATERSHED 0402 | 24240402 | TRUE | 1.0938 | 0.060052 | 0.019395 | 24.5 | 0.00047476 | 5652 | 1.1912 | 2145 | 0.00056007 | 1961
LOYOLA 110260128 | LOYOLA 1102 | 82161102 |  | 10.3506 | 3.0083 |  | 182.5 | 0.00054272 | 4925 | 1.282 | 2026 | 0.00055995 | 1962
HOOPA 11013290 | HOOPA 1101 | 192401101 | FALSE | 13.652 | 1.1254 | 14.7773 | 274.5 | 0.00026409 | 8777 | 2.139 | 1594 | 0.00055978 | 1963
OREGON TRAIL 1102CB | OREGON TRAIL 1102 | 103521102 | FALSE | 9.561 | 0.44171 | 9.5293 | 173.5 | 0.00040578 | 6383 | 1.3668 | 1953 | 0.00055975 | 1964
HIGHLANDS 1103973816 | HIGHLANDS 1103 | 43361103 | FALSE | 2.7103 | 0.045444 | 2.7557 | 48.5 | 0.00015457 | 10651 | 3.0784 | 1373 | 0.00055964 | 1965
SHINGLE SPRINGS 21092053 | SHINGLE SPRINGS 2109 | 153652109 | FALSE | 5.5843 | 0.77082 | 6.3551 | 101 | 0.00027429 | 8549 | 2.0343 | 1624 | 0.0005595 | 1966
MOLINO 1102381468 | MOLINO 1102 | 42571102 | FALSE | 1.5605 | 0.19373 | 1.6224 | 30.5 | 0.0005285 | 5091 | 1.079 | 2324 | 0.00055895 | 1967
TIVY VALLEY 1107584840 | TIVY VALLEY 1107 | 252941107 | FALSE | 44.6472 | 2.604 | 47.251 | 823.5 | 0.00012236 | 10939 | 5.0132 | 1141 | 0.00055881 | 1968
WILLOW CREEK 11014904 | WILLOW CREEK 1101 | 192171101 | FALSE | 11.2832 | 0.16155 | 11.4447 | 219 | 0.00032717 | 7502 | 1.7514 | 1718 | 0.0005585 | 1969
HIGGINS 1109CB | HIGGINS 1109 | 152691109 | FALSE | 23.2435 | 1.4006 | 23.9519 | 416.3333 | 0.00023958 | 9292 | 2.44 | 1524 | 0.00055833 | 1970
HIGGINS 11071070 | HIGGINS 1107 | 152691107 | FALSE | 8.2099 | 0.64551 | 7.9894 | 148 | 0.0002558 | 8966 | 2.2773 | 1561 | 0.00055762 | 1971
IGNACIO 1105908 | IGNACIO 1105 | 42481105 | TRUE | 1.8183 | 1.4414 | 0.26983 | 47 | 0.00064461 | 3769 | 1.194 | 2140 | 0.00055759 | 1972
BRUNSWICK 1104285704 | BRUNSWICK 1104 | 152481104 | FALSE | 1.2142 | 0.65331 | 1.7196 | 22.5 | 0.00054748 | 4887 | 1.0056 | 2385 | 0.00055734 | 1973
TASSAJARA 211238868 | TASSAJARA 2112 | 14662112 | FALSE | 4.3276 | 1.5254 | 2.0502 | 74 | 0.0007304 | 2721 | 0.66693 | 2672 | 0.00055721 | 1974
SAN LEANDRO U 1109CR182 | SAN LEANDRO U 1109 | 13111109 | FALSE | 4.8955 | 4.239 | 9.1345 | 94 | 0.00056274 | 4730 | 0.99422 | 2401 | 0.00055717 | 1975
DALY CITY 1115CB | DALY CITY 1115 | 22641115 |  | 0.031525 | 0 |  | 0.16667 | 0.008271 | 2 | 0.067315 | 5721 | 0.00055676 | 1976
NORTH BRANCH 110111158 | NORTH BRANCH 1101 | 163231101 | FALSE | 29.4468 | 1.5022 | 11.2914 | 555 | 0.00013858 | 10806 | 4.2217 | 1218 | 0.00055658 | 1977
RESERVATION ROAD 1101383718 | RESERVATION ROAD 1101 | 182731101 | FALSE | 22.272 | 4.0501 | 23.9971 | 415 | 0.00027271 | 8586 | 2.8339 | 1430 | 0.00055578 | 1978
PLACERVILLE 1112CB | PLACERVILLE 1112 | 153081112 | FALSE | 0.87436 | 0.18801 | 0.9577 | 16.3333 | 0.00059088 | 4404 | 0.96101 | 2437 | 0.00055552 | 1979
ALTO 112265474 | ALTO 1122 | 42031122 | FALSE | 3.6234 | 1.2786 | 2.9257 | 60.3333 | 0.00059752 | 4333 | 0.96213 | 2436 | 0.00055547 | 1980
IGNACIO 1101CB | IGNACIO 1101 | 42481101 | FALSE | 1.8261 | 0.099376 | 1.599 | 27.5 | 0.00055 | 4861 | 1.0455 | 2347 | 0.00055462 | 1981
MERCED FALLS 11029460 | MERCED FALLS 1102 | 252811102 | FALSE | 11.0544 | 0.35498 | 11.117 | 188.5 | 0.00023586 | 9368 | 2.318 | 1550 | 0.00055428 | 1982
UKIAH 1114822 | UKIAH 1114 | 42771114 |  | 7.9429 | 1.4472 |  | 139 | 0.00035453 | 7063 | 2.0034 | 1630 | 0.0005542 | 1983
VALLEY VIEW 1106P166 | VALLEY VIEW 1106 | 14341106 | FALSE | 4.4707 | 0.041466 | 4.2573 | 88.5 | 0.00040845 | 6352 | 1.3947 | 1934 | 0.00055374 | 1984
VACAVILLE 1111CB | VACAVILLE 1111 | 63601111 | FALSE | 7.2139 | 3.0997 | 6.3602 | 119.3333 | 0.00058589 | 4466 | 1.1078 | 2294 | 0.00055328 | 1985
RACETRACK 1703759144 | RACETRACK 1703 | 163761703 | FALSE | 9.077 | 1.8421 | 10.919 | 174.8333 | 0.00042986 | 6121 | 1.3025 | 2002 | 0.00055305 | 1986
MADISON 210144634 | MADISON 2101 | 63172101 |  | 19.731 | 0.3641 |  | 341 | 0.00018336 | 10301 | 12.0397 | 757 | 0.000552 | 1987
OAKLAND X 1106CR008 | OAKLAND X 1106 | 12541106 | FALSE | 4.3743 | 3.8844 | 8.2563 | 91 | 0.00052349 | 5148 | 1.0578 | 2336 | 0.00055162 | 1988
BRIDGEVILLE 1101CB | BRIDGEVILLE 1101 | 192461101 | FALSE | 3.493 | 0.044646 | 3.5376 | 57 | 0.00033157 | 7426 | 1.803 | 1700 | 0.00055038 | 1989
MORAGA 1101108540 | MORAGA 1101 | 13801101 | FALSE | 4.765 | 0.80152 | 5.5665 | 86.6667 | 0.00037944 | 6703 | 1.3264 | 1984 | 0.00055034 | 1990
TYLER 11051536 | TYLER 1105 | 103571105 | FALSE | 18.0358 | 0.30406 | 17.7422 | 346.5 | 0.00013665 | 10824 | 5.0453 | 1137 | 0.00055015 | 1991
CORTINA 1101302192 | CORTINA 1101 | 63121101 |  | 17.8286 | 0.25788 |  | 317 | 0.0001364 | 10826 | 8.9879 | 884 | 0.00054963 | 1992
GARBERVILLE 11011604 | GARBERVILLE 1101 | 192221101 | FALSE | 18.8013 | 0.38642 | 4.6096 | 329.0833 | 0.00018075 | 10344 | 3.2976 | 1344 | 0.00054943 | 1993
WILLOW CREEK 1101729000 | WILLOW CREEK 1101 | 192171101 | FALSE | 6.838 | 0.087092 | 6.9251 | 131.5 | 0.00036397 | 6930 | 1.5574 | 1802 | 0.00054867 | 1994
MARTELL 11033152 | MARTELL 1103 | 163011103 | FALSE | 16.8609 | 0.53639 | 17.0766 | 302 | 0.00017457 | 10425 | 3.5452 | 1303 | 0.00054772 | 1995
OLETA 1102799924 | OLETA 1102 | 163541102 | TRUE | 0.39175 | 0 | 0.39175 | 9.3333 | 0.0002055 | 9954 | 2.8928 | 1414 | 0.00054571 | 1996
PACIFICA 1102267868 | PACIFICA 1102 | 22811102 | FALSE | 1.2087 | 0.39681 | 0.88648 | 23 | 0.0004584 | 5824 | 1.4367 | 1895 | 0.0005451 | 1997
SUMMIT 1102CB | SUMMIT 1102 | 152591102 | FALSE | 1.0558 | 0.43633 | 1.4921 | 28 | 0.00041519 | 6280 | 1.3471 | 1966 | 0.00054495 | 1998
FRUITLAND 11413902 | FRUITLAND 1141 | 192311141 | FALSE | 5.1109 | 0.06123 | 4.8274 | 101 | 0.0005058 | 5330 | 1.0428 | 2351 | 0.00054459 | 1999
PINECREST 04011818 | PINECREST 0401 | 163160401 | FALSE | 3.1239 | 2.4141 | 5.3976 | 64.3333 | 0.00039499 | 6511 | 1.3655 | 1954 | 0.00054321 | 2000
BRUNSWICK 11052204 | BRUNSWICK 1105 | 152481105 | FALSE | 3.2148 | 0.94092 | 4.1557 | 69.5 | 0.0003692 | 6854 | 1.4559 | 1883 | 0.00054191 | 2001
SHINGLE SPRINGS 211051800 | SHINGLE SPRINGS 2110 | 153652110 | FALSE | 9.8437 | 1.018 | 9.9603 | 172 | 0.00035906 | 6996 | 1.5135 | 1834 | 0.00054177 | 2002
REDBUD 1102510 | REDBUD 1102 | 43191102 | FALSE | 8.0923 | 2.7965 | 4.6362 | 112.5 | 0.00043556 | 6060 | 1.1641 | 2209 | 0.0005414 | 2003
WILLITS 1103826 | WILLITS 1103 | 42661103 | FALSE | 7.5664 | 0.86367 | 8.43 | 127.5 | 0.00043397 | 6071 | 1.2294 | 2084 | 0.00054018 | 2004
FRUITLAND 11426064 | FRUITLAND 1142 | 192311142 | FALSE | 8.2665 | 0.59263 | 6.915 | 157.3333 | 0.00034318 | 7257 | 1.6436 | 1773 | 0.00054016 | 2005
ROB ROY 2105CB | ROB ROY 2105 | 83692105 | FALSE | 1.3441 | 0.40906 | 0.7135 | 22.3333 | 0.00066368 | 3517 | 0.8348 | 2534 | 0.00053913 | 2006
FRUITLAND 11426054 | FRUITLAND 1142 | 192311142 | FALSE | 6.8396 | 0.86125 | 7.7008 | 133 | 0.0004669 | 5728 | 1.156 | 2231 | 0.00053878 | 2007
BRUNSWICK 110750010 | BRUNSWICK 1107 | 152481107 | FALSE | 9.3347 | 4.8503 | 8.6232 | 146 | 0.00067014 | 3432 | 0.86675 | 2511 | 0.00053815 | 2008
MADISON 2101760730 | MADISON 2101 | 63172101 | TRUE | 2.6826 | 0.077891 | 0.16628 | 48 | 0.00020087 | 10027 | 5.0372 | 1138 | 0.00053784 | 2009
MAPLE CREEK 1101555034 | MAPLE CREEK 1101 | 192101101 | FALSE | 2.5307 | 0.062343 | 0.98936 | 45 | 0.00046701 | 5725 | 1.15 | 2248 | 0.00053706 | 2010
MEADOW LANE 2106970936 | MEADOW LANE 2106 | 14302106 | FALSE | 1.4064 | 0 | 0.84478 | 31.5 | 0.00020832 | 9906 | 2.8507 | 1425 | 0.00053617 | 2011
SAN LUIS OBISPO 1107V60 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 1.6614 | 0.14605 | 1.8074 | 31 | 0.00045886 | 5819 | 1.1605 | 2219 | 0.00053533 | 2012
SAND CREEK 110397354 | SAND CREEK 1103 | 254601103 | FALSE | 10.1482 | 0.2978 | 8.5719 | 194 | 0.00012835 | 10898 | 4.4228 | 1198 | 0.00053504 | 2013
WILLOW CREEK 11035012 | WILLOW CREEK 1103 | 192171103 | FALSE | 10.9752 | 1.0373 | 12.0125 | 206.5 | 0.0003506 | 7130 | 1.532 | 1821 | 0.00053492 | 2014
WHITMORE 110145262 | WHITMORE 1101 | 103601101 | FALSE | 28.2865 | 0.9092 | 29.1956 | 540.5 | 0.00016628 | 10519 | 4.3417 | 1206 | 0.0005347 | 2015
VOLTA 110149742 | VOLTA 1101 | 102541101 | FALSE | 3.4789 | 0.10081 | 3.5797 | 57.5 | 0.0001369 | 10821 | 3.6726 | 1290 | 0.00053274 | 2016
OTTER 1101440 | OTTER 1101 | 182941101 | FALSE | 10.9187 | 2.2923 | 7.2676 | 206.5 | 0.00057101 | 4645 | 0.99593 | 2399 | 0.00053172 | 2017
SOLEDAD 2102304826 | SOLEDAD 2102 | 182052102 | FALSE | 8.7324 | 0.36357 | 4.1083 | 173.5 | 0.00022918 | 9509 | 2.8346 | 1429 | 0.00053169 | 2018
COARSEGOLD 2104CB | COARSEGOLD 2104 | 254432104 | FALSE | 2.4763 | 0.043402 | 2.5197 | 44.3333 | 0.0003888 | 6591 | 1.3842 | 1942 | 0.00053157 | 2019
BRIDGEVILLE 1102353222 | BRIDGEVILLE 1102 | 192461102 | FALSE | 6.7636 | 0.95237 | 7.5271 | 127 | 0.00035015 | 7140 | 1.4963 | 1850 | 0.00053105 | 2020
LUCERNE 11031663 | LUCERNE 1103 | 43351103 | FALSE | 1.2131 | 0.55459 | 1.7677 | 19.3333 | 0.0004209 | 6217 | 1.2602 | 2044 | 0.00053079 | 2021
FULTON 11024522 | FULTON 1102 | 42561102 | FALSE | 12.1473 | 0.51756 | 8.4002 | 224 | 0.00024331 | 9219 | 2.6512 | 1470 | 0.00052883 | 2022
DUNBAR 1101904852 | DUNBAR 1101 | 43071101 | FALSE | 9.4199 | 1.2191 | 2.2434 | 187 | 0.00048399 | 5556 | 1.4888 | 1855 | 0.00052771 | 2023
EL DORADO PH 2101887684 | EL DORADO PH 2101 | 152762101 | FALSE | 2.0453 | 1.1588 | 0.7919 | 44 | 0.00039562 | 6504 | 0.95543 | 2442 | 0.00052765 | 2024
CURTIS 17058170 | CURTIS 1705 | 163351705 | FALSE | 7.7917 | 1.2562 | 8.7384 | 134.5 | 0.00039511 | 6508 | 1.4542 | 1885 | 0.00052763 | 2025
SALT SPRINGS 210117012 | SALT SPRINGS 2101 | 163692101 |  | 1.9123 | 0.0253 |  | 36.5 | 0.00031127 | 7781 | 1.6882 | 1746 | 0.00052734 | 2026
GARCIA 0401666 | GARCIA 0401 | 43040401 | FALSE | 2.4077 | 0.038476 | 2.4461 | 48.5 | 0.00028365 | 8337 | 2.0154 | 1626 | 0.00052699 | 2027
CABRILLO 1104Y24 | CABRILLO 1104 | 183101104 | FALSE | 19.3615 | 0.52618 | 18.7923 | 362.5 | 0.00017664 | 10398 | 4.0404 | 1254 | 0.00052681 | 2028
OLETA 1102CB | OLETA 1102 | 163541102 | TRUE | 0.83394 | 0.07051 | 0.37612 | 9.5833 | 0.00058448 | 4479 | 0.92398 | 2470 | 0.00052671 | 2029
OAKLAND X 1106950688 | OAKLAND X 1106 | 12541106 | FALSE | 3.6117 | 2.4514 | 6.0631 | 76.5 | 0.0005252 | 5122 | 1.0024 | 2389 | 0.00052604 | 2030
PUTAH CREEK 110246012 | PUTAH CREEK 1102 | 63681102 | TRUE | 2.9529 | 0.25807 | 0.52758 | 52.5 | 0.00027815 | 8468 | 1.5905 | 1794 | 0.00052598 | 2031
JESSUP 110194468 | JESSUP 1101 | 103441101 | FALSE | 1.7138 | 0.18308 | 1.8969 | 34.3333 | 0.00025876 | 8911 | 2.817 | 1432 | 0.0005251 | 2032
MONTE RIO 1113539938 | MONTE RIO 1113 | 42811113 | FALSE | 9.8836 | 0.11149 | 2.8626 | 192 | 0.00030383 | 7933 | 1.9333 | 1658 | 0.00052444 | 2033
LOGAN CREEK 2199CB | LOGAN CREEK 2199 | 103142199 |  | 0.029407 | 0 |  | 0.33333 | 0.0078037 | 3 | 0.067105 | 5893 | 0.00052366 | 2034
DEL MONTE 21042624 | DEL MONTE 2104 | 182222104 | FALSE | 19.0945 | 2.2675 | 20.6806 | 344.75 | 0.00027886 | 8448 | 2.0353 | 1623 | 0.00052261 | 2035
CARLOTTA 112144150 | CARLOTTA 1121 | 192291121 | FALSE | 3.5772 | 0.078162 | 3.6554 | 72 | 0.00045409 | 5884 | 1.15 | 2248 | 0.00052221 | 2036
VOLTA 11021502 | VOLTA 1102 | 102541102 | FALSE | 7.2877 | 0.68134 | 7.969 | 131.5 | 0.00037602 | 6748 | 1.4018 | 1926 | 0.00052195 | 2037
CAMP EVERS 21035402 | CAMP EVERS 2103 | 83622103 | FALSE | 6.7342 | 2.4809 | 2.8968 | 117.8333 | 0.0008629 | 1474 | 0.57384 | 2763 | 0.00052143 | 2038
PAUL SWEET 2109634576 | PAUL SWEET 2109 | 83252109 | FALSE | 2.0559 | 0.80659 | 2.3653 | 38.8333 | 0.00052495 | 5125 | 1.0321 | 2360 | 0.00052112 | 2039
OAKLAND X 1106735592 | OAKLAND X 1106 | 12541106 | FALSE | 3.0433 | 2.542 | 5.5661 | 40.5833 | 0.00067574 | 3363 | 0.79058 | 2567 | 0.00052099 | 2040
UPPER LAKE 1101861806 | UPPER LAKE 1101 | 42871101 | FALSE | 17.9946 | 2.0935 | 4.2647 | 327.5 | 0.00026791 | 8702 | 2.8359 | 1428 | 0.00052046 | 2041
HALF MOON BAY 11028848 | HALF MOON BAY 1102 | 24101102 | FALSE | 10.0399 | 2.0189 | 3.6583 | 177.5 | 0.00052168 | 5161 | 1.1984 | 2135 | 0.00052021 | 2042
WISE 1102CB | WISE 1102 | 152271102 | FALSE | 14.4535 | 2.3724 | 16.3473 | 253.3333 | 0.00038581 | 6634 | 1.341 | 1975 | 0.00052015 | 2043
AUBERRY 1102R902 | AUBERRY 1102 | 254151102 | FALSE | 15.5972 | 0.391 | 15.9882 | 275 | 0.00015987 | 10601 | 3.4602 | 1322 | 0.00051963 | 2044
PENNGROVE 1101170 | PENNGROVE 1101 | 43471101 | FALSE | 22.409 | 1.4687 | 18.5377 | 408.5 | 0.00021433 | 9791 | 2.666 | 1468 | 0.00051959 | 2045
FITCH MOUNTAIN 1113775992 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 3.1415 | 0.22881 | 2.1171 | 54.5 | 0.000467 | 5726 | 1.3386 | 1976 | 0.00051897 | 2046
JESSUP 110276068 | JESSUP 1102 | 103441102 | FALSE | 19.3637 | 1.7123 | 18.1326 | 345.5 | 0.00020802 | 9911 | 2.5944 | 1488 | 0.00051896 | 2047
SAN LUIS OBISPO 1104350030 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 8.5885 | 0 | 5.4418 | 81.6667 | 0.00031582 | 7701 | 1.6599 | 1761 | 0.00051894 | 2048
OLETA 1101994386 | OLETA 1101 | 163541101 | TRUE | 0.19248 | 0.031775 | 0.15036 | 4 | 0.00039975 | 6458 | 1.2952 | 2009 | 0.00051777 | 2049
GUALALA 1111887180 | GUALALA 1111 | 42841111 | FALSE | 5.4173 | 0.25712 | 5.3615 | 108.5 | 0.00040228 | 6422 | 1.2444 | 2067 | 0.00051755 | 2050
OCEANO 1104Q12 | OCEANO 1104 | 182601104 | FALSE | 15.7127 | 0.89369 | 10.0369 | 294.3333 | 0.00020223 | 10008 | 2.5084 | 1508 | 0.00051752 | 2051
TEMPLETON 2113175566 | TEMPLETON 2113 | 183052113 | FALSE | 8.9199 | 0.3375 | 6.8162 | 167.5 | 0.00024192 | 9248 | 1.8423 | 1688 | 0.00051748 | 2052
HICKS 1116733078 | HICKS 1116 | 83431116 | FALSE | 0.35234 | 0.39366 | 0.70036 | 5.3333 | 0.00051837 | 5190 | 1.0472 | 2346 | 0.00051647 | 2053
ANDERSON 1101514412 | ANDERSON 1101 | 103261101 | TRUE | 0.30094 | 0 | 0.24772 | 6.5 | 0.00034119 | 7286 | 1.5354 | 1817 | 0.00051548 | 2054
MENLO 1102560798 | MENLO 1102 | 24131102 | FALSE | 9.084 | 0.052875 | 9.1368 | 171.5 | 0.00016108 | 10586 | 3.168 | 1362 | 0.00051448 | 2055
FORT BRAGG A 1102816 | FORT BRAGG A 1102 | 42761102 | FALSE | 2.5384 | 0.37696 | 2.7559 | 51 | 0.00049481 | 5447 | 1.0226 | 2366 | 0.00051441 | 2056
GARBERVILLE 110237054 | GARBERVILLE 1102 | 192221102 | FALSE | 9.0971 | 0.24826 | 8.5372 | 183 | 0.00043156 | 6101 | 1.1132 | 2285 | 0.00051421 | 2057
SAN LUIS OBISPO 1107V18 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 3.1586 | 0.37409 | 2.6302 | 62.5 | 0.00033686 | 7350 | 1.6884 | 1745 | 0.00051357 | 2058
PEORIA 1705999 | PEORIA 1705 | 163781705 | FALSE | 2.3019 | 0.54333 | 2.8453 | 41.5 | 0.00031075 | 7790 | 1.83 | 1693 | 0.00051295 | 2059
MIRABEL 1102334 | MIRABEL 1102 | 42091102 | FALSE | 8.354 | 0.39535 | 4.8306 | 157.5 | 0.0005391 | 4966 | 0.85783 | 2517 | 0.00051279 | 2060
VIEJO 22049540 | VIEJO 2204 | 182852204 | FALSE | 2.2461 | 1.7622 | 2.5899 | 34.6667 | 0.0007675 | 2291 | 0.68138 | 2657 | 0.00051275 | 2061
BRUNSWICK 11038918 | BRUNSWICK 1103 | 152481103 | FALSE | 2.1099 | 0.50175 | 1.7982 | 37.5 | 0.00064027 | 3822 | 0.91673 | 2473 | 0.00051262 | 2062
CLARKSVILLE 2109CB | CLARKSVILLE 2109 | 153612109 | FALSE | 1.1019 | 0.093672 | 0.89105 | 24.3333 | 0.000655 | 3640 | 0.81317 | 2549 | 0.0005115 | 2063
RESERVATION ROAD 110222136 | RESERVATION ROAD 1102 | 182731102 | FALSE | 5.2978 | 0.41955 | 1.4599 | 105.5 | 0.00028068 | 8404 | 1.7634 | 1714 | 0.00051145 | 2064
MORAGA 1104N532R | MORAGA 1104 | 13801104 | FALSE | 4.6191 | 3.3398 | 6.271 | 83 | 0.00050354 | 5354 | 1.0771 | 2325 | 0.00050998 | 2065
OCEANO 1104Q10 | OCEANO 1104 | 182601104 | FALSE | 23.6644 | 2.2778 | 25.9422 | 445.3333 | 0.00021927 | 9714 | 2.4839 | 1512 | 0.00050986 | 2066
SILVERADO 2105861266 | SILVERADO 2105 | 43432105 | FALSE | 2.3647 | 0.42606 | 1.8416 | 47 | 0.00072799 | 2751 | 0.7458 | 2603 | 0.0005091 | 2067
SUMMIT 110147786 | SUMMIT 1101 | 152591101 | FALSE | 1.8112 | 0 | 1.8112 | 35 | 0.00043906 | 6019 | 1.1593 | 2221 | 0.00050906 | 2068
VOLTA 110297816 | VOLTA 1102 | 102541102 | FALSE | 5.2488 | 0.47957 | 5.7284 | 97.5 | 0.0002472 | 9139 | 2.0415 | 1620 | 0.00050867 | 2069
FORT BRAGG A 1104529076 | FORT BRAGG A 1104 | 42761104 | FALSE | 0.95121 | 0.052062 | 1.0033 | 19.5 | 0.0004421 | 5994 | 1.15 | 2248 | 0.00050842 | 2070
FLINT 1101958726 | FLINT 1101 | 152531101 | FALSE | 0.9988 | 0.43375 | 1.378 | 18.5 | 0.00044073 | 6004 | 1.15 | 2248 | 0.00050684 | 2071
NORTH BRANCH 1101TS1115 | NORTH BRANCH 1101 | 163231101 | FALSE | 17.5095 | 1.0993 | 18.6087 | 321 | 0.00013882 | 10803 | 3.5695 | 1298 | 0.00050657 | 2072
VIEJO 22029089 | VIEJO 2202 | 182852202 | FALSE | 1.6329 | 1.2896 | 2.2765 | 25 | 0.00057967 | 4525 | 0.80323 | 2556 | 0.00050596 | 2073
SAN RAFAEL 1104802 | SAN RAFAEL 1104 | 42011104 | FALSE | 13.6292 | 10.7227 | 12.7047 | 243.5 | 0.00057072 | 4651 | 0.99985 | 2392 | 0.0005058 | 2074
VACAVILLE 1104CB | VACAVILLE 1104 | 63601104 | TRUE | 3.1214 | 1.8824 | 0.52883 | 58 | 0.00083636 | 1671 | 1.9561 | 1654 | 0.00050559 | 2075
DEL MONTE 21032000 | DEL MONTE 2103 | 182222103 | FALSE | 8.904 | 0.86605 | 9.77 | 158.8333 | 0.00043707 | 6042 | 1.15 | 2248 | 0.00050478 | 2076
SANTA NELLA 1104611232 | SANTA NELLA 1104 | 254051104 |  | 2.2764 | 0 |  | 44.5 | 0.00016442 | 10539 | 2.4698 | 1517 | 0.00050462 | 2077
MORGAN HILL 2105CB | MORGAN HILL 2105 | 83242105 |  | 1.8002 | 1.5015 |  | 29.8333 | 0.00053755 | 4986 | 1.4199 | 1911 | 0.00050346 | 2078
FORT BRAGG A 1102265870 | FORT BRAGG A 1102 | 42761102 | FALSE | 1.5034 | 0 | 1.5034 | 31.5 | 0.00043765 | 6035 | 1.15 | 2248 | 0.00050329 | 2079
CAMPHORA 1101613562 | CAMPHORA 1101 | 182071101 | FALSE | 5.9623 | 0.19674 | 1.955 | 121 | 0.00012272 | 10936 | 5.1683 | 1125 | 0.00050205 | 2080
PERRY 1101986322 | PERRY 1101 | 183071101 | FALSE | 8.7577 | 6.1513 | 10.5772 | 116.5 | 0.00056737 | 4687 | 0.84174 | 2530 | 0.00050184 | 2081
FORT BRAGG A 1102667996 | FORT BRAGG A 1102 | 42761102 | FALSE | 5.7828 | 0.79922 | 6.582 | 102.5 | 0.00042612 | 6160 | 1.1691 | 2196 | 0.0005004 | 2082
MORAGA 1103CB | MORAGA 1103 | 13801103 | FALSE | 6.3832 | 5.295 | 2.1516 | 102.75 | 0.00078641 | 2088 | 0.63332 | 2701 | 0.0005004 | 2083
FORT BRAGG A 1102418 | FORT BRAGG A 1102 | 42761102 | FALSE | 14.2601 | 3.2127 | 17.1013 | 264.8333 | 0.00044832 | 5930 | 1.1076 | 2295 | 0.0004984 | 2084
ZACA 1102CB | ZACA 1102 | 182681102 | FALSE | 20.7409 | 1.433 | 15.2851 | 385.5 | 0.00027681 | 8499 | 2.4833 | 1513 | 0.00049821 | 2085
SALT SPRINGS 21011232 | SALT SPRINGS 2101 | 163692101 | FALSE | 9.056 | 1.2039 | 7.3307 | 186 | 0.00039868 | 6468 | 1.2431 | 2069 | 0.00049794 | 2086
TEMPLETON 2110R94 | TEMPLETON 2110 | 183052110 | FALSE | 21.0371 | 0.68476 | 13.0468 | 395 | 0.00011522 | 10984 | 5.7132 | 1092 | 0.00049712 | 2087
HOOPA 11013304 | HOOPA 1101 | 192401101 | FALSE | 16.6864 | 0.6704 | 17.3567 | 319.5 | 0.00040689 | 6370 | 1.2875 | 2022 | 0.00049608 | 2088
SHINGLE SPRINGS 1104556218 | SHINGLE SPRINGS 1104 | 153651104 | FALSE | 42.0616 | 2.0026 | 39.5506 | 773.5 | 0.000168 | 10505 | 3.586 | 1295 | 0.00049597 | 2089
EAST QUINCY 11012452 | EAST QUINCY 1101 | 102551101 | TRUE | 8.5097 | 5.1433 | 0.1967 | 149 | 0.00038993 | 6573 | 1.6181 | 1780 | 0.00049582 | 2090
NARROWS 21011202 | NARROWS 2101 | 153132101 | FALSE | 45.5566 | 0.4693 | 46.0258 | 811.5 | 0.00015708 | 10627 | 3.2669 | 1348 | 0.00049399 | 2091
GARBERVILLE 1102CB | GARBERVILLE 1102 | 192221102 | FALSE | 16.6497 | 5.0835 | 13.2452 | 293.5833 | 0.00051334 | 5250 | 0.87131 | 2508 | 0.00049375 | 2092
MERCED FALLS 110285002 | MERCED FALLS 1102 | 252811102 | FALSE | 35.2625 | 1.5979 | 36.8603 | 671 | 0.0001778 | 10383 | 2.7043 | 1456 | 0.00049293 | 2093
PUTAH CREEK 1105748272 | PUTAH CREEK 1105 | 63681105 | FALSE | 3.8618 | 0.058992 | 0.66177 | 70.5 | 8.2615e-05 | 11100 | 4.6313 | 1174 | 0.00049285 | 2094
CORRAL 110213498 | CORRAL 1102 | 162991102 | FALSE | 0.96899 | 0.039779 | 0.87783 | 19.5 | 0.00038297 | 6664 | 1.2215 | 2102 | 0.00049201 | 2095
LOS GATOS 1101206248 | LOS GATOS 1101 | 82021101 | TRUE | 0.55126 | 0.25941 | 0.085546 | 7 | 0.00074541 | 2541 | 0.63984 | 2694 | 0.00049199 | 2096
FRUITLAND 1142CB | FRUITLAND 1142 | 192311142 | FALSE | 3.727 | 0.15783 | 3.8849 | 63.3333 | 0.0004293 | 6125 | 1.15 | 2249 | 0.0004919 | 2097
CAROLANDS 04049024 | CAROLANDS 0404 | 24060404 | FALSE | 3.7904 | 2.1469 | 5.5188 | 69.8333 | 0.00048037 | 5600 | 1.043 | 2350 | 0.00049127 | 2098
BRIDGEVILLE 110237486 | BRIDGEVILLE 1102 | 192461102 |  | 0.71801 | 0.11008 |  | 13.5 | 0.00040634 | 6380 | 1.2065 | 2128 | 0.0004909 | 2099
CALPELLA 1102477890 | CALPELLA 1102 | 43411102 | FALSE | 2.9236 | 0.36582 | 0.9644 | 50.5 | 0.0002871 | 8253 | 2.0317 | 1625 | 0.00049031 | 2100
BRUNSWICK 110765574 | BRUNSWICK 1107 | 152481107 | TRUE | 1.7479 | 0.34278 | 0.48339 | 25.9167 | 0.00083169 | 1715 | 0.59101 | 2747 | 0.00049009 | 2101
OLEMA 11011200 | OLEMA 1101 | 42291101 | FALSE | 2.8445 | 2.0372 | 4.8817 | 52.5 | 0.00038747 | 6613 | 1.2613 | 2041 | 0.00048987 | 2102
ESTUDILLO 0401850884 | ESTUDILLO 0401 | 13480401 | FALSE | 1.5674 | 1.196 | 1.4393 | 20.6667 | 0.00067266 | 3407 | 0.69884 | 2647 | 0.00048846 | 2103
BIG MEADOWS 21012474 | BIG MEADOWS 2101 | 102812101 | FALSE | 8.3175 | 1.2992 | 9.5406 | 157 | 0.000231 | 9464 | 2.1156 | 1600 | 0.00048813 | 2104
LLAGAS 2107XR188 | LLAGAS 2107 | 83182107 |  | 2.8458 | 0.35789 |  | 50.5 | 0.00051585 | 5219 | 0.99601 | 2398 | 0.00048813 | 2105
HIGHLANDS 110275140 | HIGHLANDS 1102 | 43361102 | FALSE | 20.0577 | 10.0714 | 12.3912 | 297.1667 | 0.00041457 | 6289 | 1.7059 | 1740 | 0.00048754 | 2106
CALPELLA 1101CB | CALPELLA 1101 | 43411101 | FALSE | 20.3619 | 2.4856 | 11.7677 | 354.6667 | 0.00038203 | 6675 | 1.9186 | 1663 | 0.00048555 | 2107
ROSSMOOR 110845268 | ROSSMOOR 1108 | 14161108 | FALSE | 7.6774 | 3.785 | 2.8916 | 136 | 0.00068479 | 3278 | 0.70486 | 2639 | 0.00048497 | 2108
OLEMA 1101416 | OLEMA 1101 | 42291101 | FALSE | 19.7356 | 1.6004 | 21.2727 | 398.5 | 0.00038424 | 6646 | 1.2588 | 2047 | 0.00048461 | 2109
CLARKSVILLE 210575884 | CLARKSVILLE 2105 | 153612105 | FALSE | 10.6821 | 0.26019 | 10.3272 | 196.8333 | 0.00031935 | 7643 | 1.759 | 1715 | 0.00048437 | 2110
PLACER 1101106534 | PLACER 1101 | 152461101 | FALSE | 2.6293 | 0.84453 | 1.2554 | 44.5 | 0.00060858 | 4185 | 0.88147 | 2500 | 0.0004829 | 2111
STAFFORD 1102361952 | STAFFORD 1102 | 43201102 | FALSE | 1.4298 | 0.10236 | 1.5322 | 27 | 0.00016068 | 10592 | 3.0165 | 1392 | 0.0004828 | 2112
MOLINO 1101322 | MOLINO 1101 | 42571101 | FALSE | 14.1511 | 1.8901 | 15.6466 | 258 | 0.00039728 | 6489 | 1.2195 | 2104 | 0.00048239 | 2113
WYANDOTTE 11071026 | WYANDOTTE 1107 | 102911107 | FALSE | 27.9297 | 0.94166 | 22.0542 | 486 | 0.00014825 | 10715 | 3.8435 | 1267 | 0.00048157 | 2114
UKIAH 11151216 | UKIAH 1115 | 42771115 | FALSE | 19.1201 | 1.0156 | 13.5462 | 362 | 0.00031349 | 7747 | 3.1455 | 1366 | 0.00048123 | 2115
OAKHURST 110363334 | OAKHURST 1103 | 254421103 | FALSE | 20.6921 | 0.80171 | 17.9162 | 392 | 0.00018595 | 10263 | 2.6797 | 1463 | 0.00048117 | 2116
WISE 1102465074 | WISE 1102 | 152271102 | FALSE | 4.7527 | 0.67571 | 5.4284 | 85.5 | 0.00036406 | 6929 | 1.3275 | 1982 | 0.00048044 | 2117
ARCATA 11225384 | ARCATA 1122 | 192021122 | FALSE | 17.449 | 2.6209 | 16.5986 | 326.5 | 0.00045454 | 5878 | 1.0416 | 2353 | 0.0004789 | 2118
COARSEGOLD 21045300 | COARSEGOLD 2104 | 254432104 | FALSE | 55.6003 | 1.5727 | 57.1729 | 1013.5 | 0.00015081 | 10694 | 3.2133 | 1353 | 0.00047692 | 2119
GARBERVILLE 1101438596 | GARBERVILLE 1101 | 192221101 | FALSE | 10.8373 | 0.52221 | 11.3595 | 216 | 0.00033793 | 7338 | 1.4178 | 1914 | 0.00047658 | 2120
CARRIZO PLAINS 1101711854 | CARRIZO PLAINS 1101 | 253461101 |  | 6.4283 | 0 |  | 99.5 | 0.00010583 | 11036 | 4.7828 | 1161 | 0.0004758 | 2121
FORT ROSS 11214614 | FORT ROSS 1121 | 42851121 | FALSE | 12.5694 | 0.90563 | 13.4749 | 248.5 | 0.00026839 | 8692 | 2.2046 | 1577 | 0.0004758 | 2122
PAUL SWEET 2102959032 | PAUL SWEET 2102 | 83252102 | FALSE | 0.95823 | 0.036684 | 0.76793 | 18.3333 | 0.00047796 | 5621 | 1.0201 | 2368 | 0.00047563 | 2123
CALISTOGA 1101537148 | CALISTOGA 1101 | 42711101 | TRUE | 1.5342 | 0.0026695 | 0.39264 | 28 | 0.000455 | 5870 | 1.5083 | 1841 | 0.00047551 | 2124
CLAY 1103CB | CLAY 1103 | 163341103 | FALSE | 13.2995 | 0.53749 | 5.5127 | 235.3333 | 0.00044406 | 5972 | 0.88196 | 2499 | 0.00047538 | 2125
AUBERRY 1101CB | AUBERRY 1101 | 254151101 | FALSE | 18.1452 | 1.4359 | 19.581 | 345.5 | 0.00025812 | 8922 | 1.814 | 1696 | 0.00047477 | 2126
PERRY 1101V74 | PERRY 1101 | 183071101 | FALSE | 3.1743 | 1.1708 | 2.7452 | 45 | 0.00045903 | 5815 | 1.0537 | 2341 | 0.00047475 | 2127
BRUNSWICK 1103CB | BRUNSWICK 1103 | 152481103 | FALSE | 5.3139 | 2.5452 | 2.0861 | 87.5 | 0.00091695 | 1161 | 0.52969 | 2796 | 0.00047469 | 2128
POINT ARENA 11012637 | POINT ARENA 1101 | 43381101 | FALSE | 4.1155 | 0.058043 | 4.1735 | 76.5 | 0.00036378 | 6932 | 1.2934 | 2011 | 0.00047412 | 2129
EDES 1112CR282 | EDES 1112 | 13681112 | FALSE | 4.0682 | 3.7216 | 7.7898 | 59.6667 | 0.00054768 | 4881 | 0.7993 | 2560 | 0.00047377 | 2130
GARBERVILLE 1101323694 | GARBERVILLE 1101 | 192221101 | FALSE | 6.3496 | 0.05232 | 6.4019 | 129.5 | 0.00032126 | 7602 | 1.5424 | 1814 | 0.00047328 | 2131
SEACLIFF 0402558727 | SEACLIFF 0402 | 83500402 | TRUE | 1.4197 | 0.61195 | 0.078744 | 22 | 0.00056223 | 4732 | 0.82781 | 2539 | 0.00047223 | 2132
VOLTA 11011640 | VOLTA 1101 | 102541101 | FALSE | 11.629 | 1.1983 | 12.8273 | 197 | 0.00019252 | 10171 | 2.3425 | 1543 | 0.00047058 | 2133
FORT ORD 21069658 | FORT ORD 2106 | 182402106 | TRUE | 0.094002 | 0 | 0.094001 | 1.5 | 0.00040904 | 6344 | 1.15 | 2248 | 0.00047039 | 2134
BIG MEADOWS 21012260 | BIG MEADOWS 2101 | 102812101 | FALSE | 16.9751 | 3.4591 | 11.6188 | 285.5 | 0.00031833 | 7663 | 1.7353 | 1729 | 0.00047036 | 2135
GEYSERVILLE 1102868292 | GEYSERVILLE 1102 | 42891102 | FALSE | 2.6502 | 0.064117 | 2.2087 | 53.5 | 0.00016018 | 10597 | 3.7169 | 1280 | 0.00046998 | 2136
OAKLAND J 1102951816 | OAKLAND J 1102 | 12091102 | TRUE | 0.31793 | 0.11103 | 0.42897 | 6 | 0.00040836 | 6353 | 1.15 | 2248 | 0.00046961 | 2137
BRIDGEVILLE 1102CB | BRIDGEVILLE 1102 | 192461102 | FALSE | 12.0915 | 0.57626 | 2.3897 | 213.5 | 0.0002025 | 10004 | 2.3345 | 1546 | 0.00046952 | 2138
VIEJO 22019490 | VIEJO 2201 | 182852201 | FALSE | 1.3569 | 0.37957 | 1.5646 | 28.5 | 0.00047921 | 5606 | 0.998 | 2397 | 0.00046948 | 2139
FORT BRAGG A 110235592 | FORT BRAGG A 1102 | 42761102 | FALSE | 13.5717 | 2.1277 | 11.5502 | 249 | 0.00040779 | 6359 | 1.15 | 2248 | 0.00046896 | 2140
BERESFORD 04039154 | BERESFORD 0403 | 24040403 | FALSE | 6.5754 | 4.0795 | 6.2946 | 122 | 0.00056613 | 4698 | 0.84087 | 2531 | 0.00046759 | 2141
BRUNSWICK 110756240 | BRUNSWICK 1107 | 152481107 | FALSE | 0.81043 | 0.41544 | 0.92756 | 13 | 0.00065242 | 3677 | 0.77458 | 2580 | 0.00046716 | 2142
SUNOL 110148180 | SUNOL 1101 | 14241101 | TRUE | 0.013142 | 0 | 0.013142 | 1.5 | 0.00040523 | 6393 | 1.15 | 2248 | 0.00046602 | 2143
COARSEGOLD 210310820 | COARSEGOLD 2103 | 254432103 | FALSE | 28.5729 | 2.032 | 30.3933 | 535.5 | 0.00025721 | 8941 | 1.6575 | 1766 | 0.00046488 | 2144
SANTA YNEZ 110477098 | SANTA YNEZ 1104 | 182721104 | FALSE | 13.1277 | 0.45657 | 11.7141 | 246.5 | 0.00019107 | 10196 | 2.8849 | 1417 | 0.00046453 | 2145
FRUITLAND 11418860 | FRUITLAND 1141 | 192311141 | FALSE | 3.6863 | 0.78692 | 1.9182 | 67.5 | 0.00059872 | 4314 | 0.66247 | 2677 | 0.00046369 | 2146
FORT ROSS 1121134 | FORT ROSS 1121 | 42851121 | FALSE | 8.3362 | 0.3823 | 8.4048 | 153 | 0.00038127 | 6681 | 1.217 | 2106 | 0.00046321 | 2147
PERRY 1101CB | PERRY 1101 | 183071101 | FALSE | 2.4217 | 0.099565 | 2.5213 | 45 | 0.00039419 | 6518 | 1.1734 | 2179 | 0.00046314 | 2148
CASTRO VALLEY 11088971 | CASTRO VALLEY 1108 | 14091108 | FALSE | 8.0138 | 0.41351 | 8.369 | 148.5 | 0.00024351 | 9215 | 2.0079 | 1628 | 0.00046291 | 2149
PETALUMA C 110948000 | PETALUMA C 1109 | 42631109 | FALSE | 11.4427 | 0.41955 | 7.4408 | 203.5 | 0.00029469 | 8114 | 1.6871 | 1748 | 0.00046168 | 2150
GREEN VALLEY 2101942143 | GREEN VALLEY 2101 | 83192101 | FALSE | 10.2954 | 1.2922 | 4.6737 | 188.5 | 0.0004968 | 5426 | 0.85008 | 2524 | 0.00046139 | 2151
ROB ROY 210412596 | ROB ROY 2104 | 83692104 | FALSE | 10.6632 | 1.8655 | 8.3071 | 201.5 | 0.00050232 | 5366 | 0.90712 | 2480 | 0.00046133 | 2152
JESSUP 1103728460 | JESSUP 1103 | 103441103 | FALSE | 1.4151 | 0.81053 | 0.88092 | 25 | 0.00045744 | 5841 | 1.2598 | 2045 | 0.00046034 | 2153
SAUSALITO 11021500 | SAUSALITO 1102 | 42491102 | FALSE | 1.2798 | 0 | 0.95277 | 19.0833 | 0.0002667 | 8727 | 1.9544 | 1655 | 0.00045995 | 2154
LUCERNE 11062327 | LUCERNE 1106 | 43351106 | FALSE | 1.2656 | 0.40068 | 1.5795 | 22 | 0.00034795 | 7173 | 1.3864 | 1940 | 0.00045877 | 2155
BUCKS CREEK 1103338520 | BUCKS CREEK 1103 | 102211103 | FALSE | 10.6022 | 1.2738 | 11.5781 | 193.5 | 0.00028676 | 8264 | 1.5485 | 1809 | 0.00045821 | 2156
PANORAMA 1101713592 | PANORAMA 1101 | 103461101 | FALSE | 10.5413 | 0.7722 | 11.1377 | 184 | 0.00019395 | 10145 | 2.6115 | 1482 | 0.00045744 | 2157
EEL RIVER 1102630456 | EEL RIVER 1102 | 192381102 | FALSE | 5.3541 | 0.30764 | 5.6618 | 97.5 | 0.00039139 | 6550 | 1.15 | 2248 | 0.00045634 | 2158
HARRIS 11082062 | HARRIS 1108 | 192431108 | FALSE | 5.2683 | 3.3072 | 2.1058 | 81 | 0.00057755 | 4556 | 0.7834 | 2575 | 0.00045594 | 2159
VOLTA 1102641544 | VOLTA 1102 | 102541102 | FALSE | 4.8762 | 0.40358 | 5.2797 | 84.3333 | 0.00029914 | 8034 | 1.5083 | 1840 | 0.00045535 | 2160
LUCERNE 1106526 | LUCERNE 1106 | 43351106 | FALSE | 10.6089 | 1.5857 | 10.996 | 192 | 0.00029919 | 8033 | 1.9981 | 1634 | 0.0004553 | 2161
BURNEY 110145984 | BURNEY 1101 | 103311101 | FALSE | 4.8359 | 2.6751 | 7.511 | 79.3333 | 0.00039682 | 6492 | 1.1432 | 2254 | 0.00045527 | 2162
LOW GAP 110186816 | LOW GAP 1101 | 192411101 | FALSE | 4.3788 | 0.93668 | 5.3155 | 89.5 | 0.00026701 | 8719 | 1.7133 | 1736 | 0.00045491 | 2163
CLARKSVILLE 2104CB | CLARKSVILLE 2104 | 153612104 | FALSE | 10.1011 | 0.32709 | 8.3403 | 172.8333 | 0.00041145 | 6319 | 1.1777 | 2168 | 0.00045469 | 2164
PEABODY 2113873304 | PEABODY 2113 | 63642113 | FALSE | 0.81657 | 0 | 0.81657 | 16.5 | 0.00013043 | 10882 | 3.5596 | 1302 | 0.00045453 | 2165
SONOMA 1105539450 | SONOMA 1105 | 42721105 | FALSE | 2.3335 | 0.63458 | 1.5924 | 49 | 0.00035027 | 7137 | 1.3653 | 1957 | 0.000453 | 2166
GARBERVILLE 11022540 | GARBERVILLE 1102 | 192221102 | FALSE | 17.7261 | 0.94853 | 14.9274 | 349.5 | 0.00033217 | 7418 | 1.2708 | 2033 | 0.00045184 | 2167
STAFFORD 11021202 | STAFFORD 1102 | 43201102 | FALSE | 7.7608 | 0.25359 | 7.7024 | 148.5 | 0.00020393 | 9979 | 2.1117 | 1604 | 0.00044867 | 2168
RED BLUFF 11031702 | RED BLUFF 1103 | 103541103 | FALSE | 18.3733 | 0.74943 | 17.2848 | 344.5 | 0.00018393 | 10293 | 2.7694 | 1443 | 0.00044788 | 2169
HALSEY 11012414 | HALSEY 1101 | 152241101 | FALSE | 14.7581 | 2.724 | 17.482 | 272.5 | 0.00030661 | 7875 | 1.4365 | 1897 | 0.00044783 | 2170
CASTRO VALLEY 1110610800 | CASTRO VALLEY 1110 | 14091110 | FALSE | 2.5711 | 1.0236 | 3.2581 | 44 | 0.00034652 | 7197 | 1.329 | 1981 | 0.00044771 | 2171
SPRING GAP 170210720 | SPRING GAP 1702 | 162831702 | FALSE | 4.8062 | 0.79815 | 5.6044 | 101.3333 | 0.00030401 | 7931 | 1.3924 | 1936 | 0.00044756 | 2172
DESCHUTES 1104378894 | DESCHUTES 1104 | 103351104 | FALSE | 2.9674 | 0.22704 | 2.471 | 53 | 0.00032105 | 7608 | 1.7532 | 1716 | 0.00044593 | 2173
HALF MOON BAY 11036018 | HALF MOON BAY 1103 | 24101103 | FALSE | 18.6769 | 1.8974 | 15.2208 | 342.5 | 0.00029758 | 8057 | 1.6598 | 1762 | 0.00044555 | 2174
ROB ROY 21045304 | ROB ROY 2104 | 83692104 | FALSE | 4.9735 | 0.82636 | 3.3194 | 87 | 0.00052351 | 5147 | 0.86321 | 2515 | 0.00044507 | 2175
MARTELL 1101185268 | MARTELL 1101 | 163011101 | TRUE | 0.43959 | 0 | 0.30394 | 8.5 | 0.00058714 | 4453 | 0.67922 | 2661 | 0.000445 | 2176
LUCERNE 11062355 | LUCERNE 1106 | 43351106 | TRUE | 1.0713 | 0.066124 | 0.40409 | 16 | 0.00030559 | 7895 | 1.2042 | 2131 | 0.00044474 | 2177
SAN RAFAEL 1101854822 | SAN RAFAEL 1101 | 42011101 | FALSE | 9.1921 | 6.1633 | 9.3149 | 138.1667 | 0.00065549 | 3633 | 0.75109 | 2596 | 0.00044375 | 2178
SHINGLE SPRINGS 110419502 | SHINGLE SPRINGS 1104 | 153651104 | FALSE | 15.7627 | 2.1809 | 6.3738 | 272.8333 | 0.00028587 | 8290 | 1.6455 | 1771 | 0.0004436 | 2179
GUALALA 1111402866 | GUALALA 1111 | 42841111 | FALSE | 1.5463 | 0.062021 | 1.5423 | 32.5 | 0.000379 | 6710 | 1.1757 | 2173 | 0.00044351 | 2180
SHEPHERD 2111707358 | SHEPHERD 2111 | 252062111 | FALSE | 23.1421 | 0.84109 | 19.6328 | 403 | 0.00013097 | 10876 | 3.0734 | 1377 | 0.00044341 | 2181
VOLTA 11021646 | VOLTA 1102 | 102541102 | FALSE | 24.085 | 0.88078 | 24.1099 | 452 | 0.00025036 | 9070 | 2.8138 | 1434 | 0.00044325 | 2182
AUBERRY 1102CB | AUBERRY 1102 | 254151102 | FALSE | 34.7674 | 1.7546 | 36.5219 | 596 | 0.00017175 | 10463 | 2.7501 | 1448 | 0.00044317 | 2183
VOLTA 110185234 | VOLTA 1101 | 102541101 | FALSE | 6.9283 | 2.9458 | 9.8741 | 115.5 | 0.00038094 | 6687 | 1.1732 | 2180 | 0.0004426 | 2184
SHINGLE SPRINGS 211051790 | SHINGLE SPRINGS 2110 | 153652110 | FALSE | 8.6438 | 0.89757 | 8.4508 | 155.5 | 0.00043623 | 6053 | 1.113 | 2288 | 0.00044204 | 2185
ECHO SUMMIT 1101344250 | ECHO SUMMIT 1101 | 158031101 | FALSE | 1.0176 | 0.21353 | 0.63799 | 19 | 0.00046187 | 5784 | 0.82607 | 2540 | 0.00044105 | 2186
CLEAR LAKE 1102223792 | CLEAR LAKE 1102 | 42141102 | FALSE | 0.90821 | 0.11373 | 0.89532 | 15 | 0.00042184 | 6207 | 1.0304 | 2361 | 0.00044013 | 2187
HAMILTON BRANCH 110187784 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 1.4554 | 0.66401 | 2.1194 | 28.3333 | 0.00042115 | 6212 | 1.0604 | 2334 | 0.00044005 | 2188
HALSEY 11026129 | HALSEY 1102 | 152241102 | FALSE | 3.2613 | 0.91189 | 4.1732 | 58 | 0.00037475 | 6768 | 1.1863 | 2151 | 0.00043999 | 2189
SISQUOC 1103M98 | SISQUOC 1103 | 182811103 | FALSE | 9.7114 | 0.14225 | 5.6135 | 187 | 0.00021832 | 9727 | 1.9787 | 1645 | 0.00043973 | 2190
CLOVERDALE 1102307342 | CLOVERDALE 1102 | 42821102 | TRUE | 0.35161 | 0 | 0.20066 | 5.5 | 0.00037156 | 6818 | 1.1764 | 2170 | 0.00043905 | 2191
MC ARTHUR 11011490 | MC ARTHUR 1101 | 103491101 | FALSE | 15.1322 | 0.93916 | 9.2103 | 287.5 | 0.00016167 | 10579 | 2.374 | 1540 | 0.00043812 | 2192
BRUNSWICK 1105297538 | BRUNSWICK 1105 | 152481105 | FALSE | 1.0572 | 0.27074 | 1.3279 | 17.5 | 0.00047345 | 5665 | 0.97526 | 2424 | 0.00043786 | 2193
GREEN VALLEY 2101535998 | GREEN VALLEY 2101 | 83192101 | FALSE | 4.9368 | 0.2952 | 4.6687 | 93 | 0.0003928 | 6535 | 1.1807 | 2160 | 0.00043743 | 2194
FROGTOWN 1702832694 | FROGTOWN 1702 | 163451702 | TRUE | 0.29768 | 0.065995 | 0.36287 | 6 | 0.00037556 | 6755 | 1.1561 | 2230 | 0.0004373 | 2195
MONROE 210392868 | MONROE 2103 | 43302103 | TRUE | 0.65243 | 0.36847 | 0.1478 | 20.3333 | 0.00073839 | 2626 | 0.4762 | 2846 | 0.00043641 | 2196
OLETA 1101754718 | OLETA 1101 | 163541101 | FALSE | 2.9382 | 0.11894 | 3.0571 | 47.5 | 0.00015791 | 10618 | 4.0562 | 1252 | 0.00043538 | 2197
PARADISE 11042206 | PARADISE 1104 | 102831104 | FALSE | 7.3932 | 2.5442 | 1.4244 | 134.8333 | 0.00049147 | 5479 | 1.0976 | 2305 | 0.00043536 | 2198
DIAMOND SPRINGS 1105CB | DIAMOND SPRINGS 1105 | 152261105 | FALSE | 4.6964 | 1.0998 | 1.2359 | 66.5 | 0.00061844 | 4064 | 0.78667 | 2572 | 0.00043476 | 2199
FAIRVIEW 2207P304 | FAIRVIEW 2207 | 13432207 | FALSE | 6.1166 | 1.1287 | 6.2164 | 98.1667 | 0.00035224 | 7102 | 1.3343 | 1979 | 0.00043459 | 2200
LLAGAS 2101984552 | LLAGAS 2101 | 83182101 | FALSE | 5.8225 | 0.86064 | 5.2058 | 118.5 | 0.00018992 | 10214 | 4.4973 | 1188 | 0.0004343 | 2201
VOLTA 1101CB | VOLTA 1101 | 102541101 | FALSE | 9.0089 | 0.28003 | 9.289 | 152.8333 | 0.00016272 | 10563 | 2.9517 | 1401 | 0.00043332 | 2202
MOLINO 1101277292 | MOLINO 1101 | 42571101 | FALSE | 1.4439 | 0.20556 | 1.6494 | 24.5 | 0.00035395 | 7074 | 1.2226 | 2099 | 0.00043275 | 2203
PETALUMA C 1109820458 | PETALUMA C 1109 | 42631109 | FALSE | 7.3422 | 0.17032 | 7.5125 | 145.3333 | 0.00017192 | 10458 | 2.393 | 1533 | 0.0004314 | 2204
FORT BRAGG A 11014698 | FORT BRAGG A 1101 | 42761101 | FALSE | 8.1458 | 0.74752 | 8.8933 | 143.5 | 0.00034321 | 7256 | 1.2837 | 2024 | 0.00043119 | 2205
SAN RAFAEL 1106991658 | SAN RAFAEL 1106 | 42011106 | FALSE | 1.2415 | 0.49119 | 0.78666 | 22.5 | 0.0004819 | 5584 | 0.9867 | 2409 | 0.00043088 | 2206
SARATOGA 11076867 | SARATOGA 1107 | 83371107 | FALSE | 0.84483 | 0.6367 | 1.0582 | 17.5 | 0.00064514 | 3763 | 1.1965 | 2137 | 0.00043003 | 2207
GANSNER 1101489276 | GANSNER 1101 | 103021101 | TRUE | 0.67211 | 0.33285 | 0.57989 | 11.5 | 0.0005449 | 4911 | 0.81252 | 2550 | 0.00042951 | 2208
ROSSMOOR 1106L522R | ROSSMOOR 1106 | 14161106 | FALSE | 4.2378 | 3.4239 | 3.1222 | 69.6667 | 0.0007744 | 2210 | 0.60619 | 2726 | 0.00042926 | 2209
LLAGAS 2101XR586 | LLAGAS 2101 | 83182101 |  | 20.2437 | 2.0173 |  | 399.5 | 0.00019187 | 10181 | 3.6976 | 1283 | 0.00042903 | 2210
ELECTRA 1102285758 | ELECTRA 1102 | 162161102 | TRUE | 2.1539 | 0.58899 | 0.0098714 | 31 | 0.00062989 | 3945 | 0.74421 | 2604 | 0.0004289 | 2211
MORGAN HILL 2105XR602 | MORGAN HILL 2105 | 83242105 | TRUE | 0.87574 | 0.15665 | 0.087943 | 18 | 0.00034332 | 7251 | 0.7867 | 2571 | 0.00042879 | 2212
SONOMA 1105575872 | SONOMA 1105 | 42721105 | FALSE | 1.5197 | 0.01487 | 0.94365 | 27.5 | 9.2809e-05 | 11075 | 6.1068 | 1063 | 0.00042807 | 2213
CONTRA COSTA 2106CB | CONTRA COSTA 2106 | 13652106 |  | 0.023808 | 0 |  | 0.25 | 0.0063797 | 5 | 0.067 | 6057 | 0.00042744 | 2214
ROSSMOOR 1102CB | ROSSMOOR 1102 | 14161102 |  | 0.23729 | 0 |  | 3.1429 | 0.0010374 | 657 | 0.67941 | 2660 | 0.00042741 | 2215
POINT MORETTI 110112122 | POINT MORETTI 1101 | 82931101 | FALSE | 8.833 | 0.30938 | 6.855 | 168 | 0.0004069 | 6369 | 0.93989 | 2457 | 0.00042654 | 2216
LOGAN CREEK 2102767046 | LOGAN CREEK 2102 | 103142102 |  | 23.4644 | 0.44522 |  | 466 | 8.0125e-05 | 11107 | 6.2064 | 1052 | 0.0004258 | 2217
OREGON TRAIL 1103CUS391 | OREGON TRAIL 1103 | 103521103 | TRUE | 0.022592 | 0 | 0.022592 | 0.5 | 0.0002685 | 8689 | 1.5857 | 1796 | 0.00042577 | 2218
WISE 11022234 | WISE 1102 | 152271102 | FALSE | 15.2058 | 1.5453 | 16.7511 | 259 | 0.00020596 | 9945 | 2.1384 | 1595 | 0.00042575 | 2219
FRUITLAND 114293234 | FRUITLAND 1142 | 192311142 | FALSE | 11.427 | 0.9375 | 12.3645 | 220.5 | 0.00031254 | 7756 | 1.3902 | 1939 | 0.00042542 | 2220
GARBERVILLE 110197300 | GARBERVILLE 1101 | 192221101 | FALSE | 3.2469 | 0.21713 | 3.464 | 61 | 0.00034713 | 7186 | 1.2285 | 2085 | 0.00042528 | 2221
CASTRO VALLEY 1110264914 | CASTRO VALLEY 1110 | 14091110 | FALSE | 0.88727 | 0.4334 | 1.1589 | 17.5 | 0.00043834 | 6029 | 1.0039 | 2387 | 0.00042436 | 2222
NEWBURG 113190242 | NEWBURG 1131 | 192151131 | FALSE | 4.3208 | 0.66596 | 4.0112 | 83.5 | 0.00038577 | 6635 | 1.0247 | 2365 | 0.00042417 | 2223
LUCERNE 1106CB | LUCERNE 1106 | 43351106 | FALSE | 3.7912 | 2.163 | 2.4971 | 71 | 0.0005322 | 5045 | 0.87198 | 2505 | 0.00042399 | 2224
PUEBLO 210398394 | PUEBLO 2103 | 43292103 |  | 2.092 | 0.84916 |  | 36.5 | 0.00077401 | 2214 | 0.20624 | 3136 | 0.00042313 | 2225
DESCHUTES 1104622260 | DESCHUTES 1104 | 103351104 | FALSE | 6.1982 | 0.20849 | 5.7956 | 108 | 0.00029527 | 8100 | 1.4692 | 1873 | 0.00042246 | 2226
OREGON TRAIL 1104CB | OREGON TRAIL 1104 | 103521104 | FALSE | 14.6382 | 1.5735 | 10.5059 | 257.5 | 0.00036643 | 6895 | 1.1415 | 2256 | 0.00042224 | 2227
GUALALA 111135562 | GUALALA 1111 | 42841111 | FALSE | 14.3505 | 1.2969 | 15.6474 | 273 | 0.00036654 | 6892 | 1.1524 | 2238 | 0.00042222 | 2228
PALMER 1101M84 | PALMER 1101 | 183031101 | FALSE | 24.6606 | 0.24273 | 22.2106 | 463.5 | 0.00016276 | 10561 | 2.6842 | 1462 | 0.00042166 | 2229
SAUSALITO 1101688590 | SAUSALITO 1101 | 42491101 | FALSE | 2.0124 | 1.1413 | 1.1114 | 28.5 | 0.00056208 | 4735 | 0.90939 | 2476 | 0.00042144 | 2230
BROWNS VALLEY 110197188 | BROWNS VALLEY 1101 | 152921101 | FALSE | 6.9131 | 0.073473 | 6.9865 | 118.5 | 0.00036802 | 6872 | 1.1444 | 2253 | 0.00042072 | 2231
STILLWATER 110248952 | STILLWATER 1102 | 103561102 | FALSE | 10.5498 | 0.42811 | 10.9779 | 186.5 | 0.00026937 | 8667 | 1.5275 | 1824 | 0.00042059 | 2232
VOLTA 110254932 | VOLTA 1102 | 102541102 | FALSE | 4.3843 | 0.19832 | 4.5826 | 80.3333 | 0.00021915 | 9716 | 1.9693 | 1650 | 0.00041943 | 2233
WOODSIDE 11049032 | WOODSIDE 1104 | 24251104 | FALSE | 4.7619 | 1.5147 | 1.8403 | 96 | 0.00085882 | 1504 | 0.6771 | 2664 | 0.00041921 | 2234
ANNAPOLIS 1101202158 | ANNAPOLIS 1101 | 42861101 | FALSE | 17.9282 | 0.3973 | 18.3254 | 354.5 | 0.00029439 | 8120 | 1.4319 | 1899 | 0.0004181 | 2235
BELL 1109724884 | BELL 1109 | 152701109 | FALSE | 14.2087 | 2.1203 | 16.0859 | 253.8333 | 0.00035391 | 7076 | 1.1807 | 2161 | 0.00041733 | 2236
SALT SPRINGS 2101TS4913 | SALT SPRINGS 2101 | 163692101 | FALSE | 3.769 | 0.23649 | 4.0054 | 65.5 | 0.00034138 | 7284 | 1.216 | 2108 | 0.00041683 | 2237
CAMBRIA 1101175422 | CAMBRIA 1101 | 182771101 | FALSE | 18.8093 | 0.43763 | 18.959 | 376.5 | 0.00017135 | 10469 | 2.5237 | 1504 | 0.00041681 | 2238
MC ARTHUR 110137388 | MC ARTHUR 1101 | 103491101 | FALSE | 12.7374 | 0.35411 | 7.8409 | 226 | 0.00010712 | 11025 | 4.3042 | 1211 | 0.00041634 | 2239
MESA 11016111 | MESA 1101 | 182821101 | FALSE | 25.6689 | 0.65631 | 24.4672 | 489 | 0.00014077 | 10779 | 2.885 | 1416 | 0.00041422 | 2240
OAKLAND D 1112CR192 | OAKLAND D 1112 | 12041112 | FALSE | 4.2274 | 4.0673 | 0.73189 | 72.25 | 0.0004984 | 5406 | 0.98049 | 2414 | 0.00041387 | 2241
ALHAMBRA 110595016 | ALHAMBRA 1105 | 14101105 | FALSE | 4.8419 | 2.713 | 0.96759 | 85 | 0.00057093 | 4648 | 1.1323 | 2268 | 0.00041384 | 2242
FRUITLAND 1142615540 | FRUITLAND 1142 | 192311142 | FALSE | 11.5443 | 0.774 | 6.5471 | 215.8333 | 0.00030089 | 7995 | 1.4031 | 1924 | 0.00041356 | 2243
OAKLAND K 1103CR422 | OAKLAND K 1103 | 12101103 | FALSE | 2.0443 | 1.3209 | 3.2641 | 24.9167 | 0.0011298 | 413 | 0.42813 | 2886 | 0.00041344 | 2244
LAKEWOOD 2224568670 | LAKEWOOD 2224 | 13532224 | TRUE | 2.6678 | 0.22693 | 0.00064558 | 36.0833 | 0.00052947 | 5079 | 1.2915 | 2016 | 0.00041257 | 2245
CAYETANO 2109MR572 | CAYETANO 2109 | 14422109 | FALSE | 12.1181 | 0.44462 | 7.4818 | 220 | 0.00013301 | 10856 | 4.1394 | 1237 | 0.00041149 | 2246
MORRO BAY 1102CB | MORRO BAY 1102 | 183011102 | FALSE | 5.5938 | 0.55276 | 3.6735 | 81.5 | 0.00033951 | 7317 | 1.0973 | 2307 | 0.00041125 | 2247
HATTON 1102CB | HATTON 1102 | 182291102 | FALSE | 4.7709 | 0.89586 | 2.5232 | 89.8333 | 0.00064414 | 3775 | 0.57792 | 2760 | 0.00040973 | 2248
WILLITS 11044650 | WILLITS 1104 | 42661104 | FALSE | 6.1082 | 2.3235 | 4.4991 | 103.8333 | 0.00027045 | 8641 | 1.9992 | 1633 | 0.00040962 | 2249
HALF MOON BAY 1103531594 | HALF MOON BAY 1103 | 24101103 | FALSE | 2.6623 | 0.0071614 | 2.3569 | 55.5 | 0.0002602 | 8880 | 1.6273 | 1777 | 0.00040934 | 2250
COARSEGOLD 21035020 | COARSEGOLD 2103 | 254432103 | FALSE | 16.5601 | 0.61664 | 16.6286 | 300 | 0.00023071 | 9470 | 1.8968 | 1671 | 0.00040903 | 2251
EDES 1112CR100 | EDES 1112 | 13681112 | FALSE | 2.0766 | 1.9337 | 4.0102 | 29 | 0.00057848 | 4544 | 0.73893 | 2614 | 0.0004075 | 2252
FORT ORD 21069656 | FORT ORD 2106 | 182402106 | TRUE | 0.1163 | 0 | 0.1163 | 1.5 | 0.00031454 | 7729 | 1.2952 | 2009 | 0.00040741 | 2253
OLEMA 11011318 | OLEMA 1101 | 42291101 | FALSE | 10.2749 | 1.8621 | 9.9601 | 201.3333 | 0.0003961 | 6501 | 1.1873 | 2147 | 0.00040675 | 2254
HARRIS 1109183860 | HARRIS 1109 | 192431109 | FALSE | 7.6357 | 2.3251 | 5.8952 | 145.5 | 0.00055681 | 4794 | 0.80392 | 2554 | 0.00040668 | 2255
PAUL SWEET 2109687295 | PAUL SWEET 2109 | 83252109 | FALSE | 0.92129 | 0.16074 | 1.082 | 14.3333 | 0.00038113 | 6683 | 0.99814 | 2396 | 0.00040661 | 2256
SAN BENITO 2104785888 | SAN BENITO 2104 | 182742104 | FALSE | 6.8613 | 0.48742 | 4.7825 | 101.3333 | 0.00047081 | 5691 | 0.81533 | 2548 | 0.00040611 | 2257
SAN JUSTO 110136902 | SAN JUSTO 1101 | 183181101 | FALSE | 14.6473 | 1.7944 | 13.5768 | 250.6667 | 0.00027293 | 8584 | 1.5944 | 1790 | 0.00040578 | 2258
BIG RIVER 110169032 | BIG RIVER 1101 | 43081101 | FALSE | 8.6033 | 0.6802 | 9.2835 | 161.5 | 0.00035262 | 7095 | 1.1509 | 2244 | 0.00040569 | 2259
BRENTWOOD 21056512 | BRENTWOOD 2105 | 14592105 | FALSE | 0.6268 | 0 | 0.6268 | 7 | 0.00025572 | 8969 | 1.6002 | 1786 | 0.00040549 | 2260
HIGHLANDS 110448262 | HIGHLANDS 1104 | 43361104 | FALSE | 6.0417 | 3.6278 | 9.6206 | 82 | 0.00044631 | 5947 | 0.93341 | 2462 | 0.00040525 | 2261
FLINT 1102CB | FLINT 1102 | 152531102 | TRUE | 0.11882 | 0 | 0.11882 | 3 | 0.0005608 | 4745 | 0.6085 | 2721 | 0.00040513 | 2262
PEORIA 1701CB | PEORIA 1701 | 163781701 | FALSE | 8.6773 | 0.4019 | 9.0792 | 165.5 | 0.00024888 | 9102 | 1.6742 | 1756 | 0.00040332 | 2263
CAMBRIA 1102CB | CAMBRIA 1102 | 182771102 | FALSE | 23.699 | 2.3097 | 15.9913 | 440 | 0.00021789 | 9735 | 4.1679 | 1233 | 0.00040327 | 2264
FOOTHILL 110299432 | FOOTHILL 1102 | 182951102 | FALSE | 8.6861 | 4.3245 | 1.4941 | 152.5 | 0.00041959 | 6229 | 1.4263 | 1904 | 0.00040198 | 2265
STILLWATER 110148950 | STILLWATER 1101 | 103561101 | FALSE | 12.3703 | 1.5777 | 13.948 | 228 | 0.0003192 | 7644 | 1.2704 | 2034 | 0.00040165 | 2266
FORT BRAGG A 110195294 | FORT BRAGG A 1101 | 42761101 | FALSE | 27.0344 | 1.4322 | 28.4665 | 516.5 | 0.0002744 | 8546 | 1.4739 | 1866 | 0.00040111 | 2267
CAMP EVERS 2106CB | CAMP EVERS 2106 | 83622106 | TRUE | 2.3659 | 0.69706 | 0.51014 | 41.3333 | 0.0011257 | 421 | 0.38177 | 2938 | 0.00039787 | 2268
DEL MONTE 21042762 | DEL MONTE 2104 | 182222104 | FALSE | 10.9738 | 1.1441 | 9.5742 | 203.5833 | 0.00036421 | 6927 | 1.2373 | 2075 | 0.00039773 | 2269
PALMER 1101M82 | PALMER 1101 | 183031101 | FALSE | 14.7228 | 2.9974 | 10.7654 | 254 | 0.00024786 | 9130 | 1.9071 | 1668 | 0.00039743 | 2270
HATTON 1102648928 | HATTON 1102 | 182291102 | FALSE | 4.8553 | 0.29696 | 4.043 | 92 | 0.00043191 | 6093 | 1.0066 | 2384 | 0.00039685 | 2271
FORT ROSS 1121124 | FORT ROSS 1121 | 42851121 | FALSE | 18.517 | 0.41298 | 18.9299 | 375 | 0.00020565 | 9949 | 2.2475 | 1568 | 0.00039682 | 2272
CAMP EVERS 2104CB | CAMP EVERS 2104 | 83622104 | TRUE | 4.4607 | 1.2204 | 0.028881 | 90.5 | 0.0010314 | 682 | 0.38962 | 2928 | 0.00039645 | 2273
SAN CARLOS 110436864 | SAN CARLOS 1104 | 24181104 | FALSE | 0.55663 | 0.24318 | 0.77032 | 7.1667 | 0.00068377 | 3286 | 0.71633 | 2628 | 0.00039618 | 2274
GUALALA 11121294 | GUALALA 1112 | 42841112 | FALSE | 20.4643 | 1.8242 | 21.3908 | 382.5 | 0.00032929 | 7464 | 1.2231 | 2096 | 0.00039596 | 2275
NARROWS 21057203 | NARROWS 2105 | 153132105 | FALSE | 18.6136 | 0.65614 | 18.5516 | 336.5 | 0.00017642 | 10401 | 2.2759 | 1562 | 0.00039589 | 2276
PUTAH CREEK 1102710384 | PUTAH CREEK 1102 | 63681102 | FALSE | 9.3359 | 0.40989 | 4.321 | 172.5 | 0.00016037 | 10594 | 5.7849 | 1086 | 0.00039529 | 2277
FROGTOWN 1702224708 | FROGTOWN 1702 | 163451702 | FALSE | 0.64089 | 0 | 0.64089 | 12.5 | 0.00042189 | 6205 | 0.99149 | 2406 | 0.00039438 | 2278
ZACA 1101Y70 | ZACA 1101 | 182681101 | FALSE | 8.7914 | 0.26655 | 5.6817 | 162 | 0.00017503 | 10420 | 2.9466 | 1402 | 0.00039414 | 2279
PIT NO 1 11011552 | PIT NO 1 1101 | 103721101 | FALSE | 26.2894 | 1.794 | 13.5487 | 469.5 | 0.00015546 | 10642 | 2.8523 | 1424 | 0.0003938 | 2280
GRASS VALLEY 110358498 | GRASS VALLEY 1103 | 152031103 | FALSE | 2.1579 | 0.44495 | 1.2145 | 34 | 0.00066925 | 3441 | 0.64015 | 2693 | 0.00039294 | 2281
POINT ARENA 1101CB | POINT ARENA 1101 | 43381101 | TRUE | 0.05237 | 0 | 0.05237 | 1.3333 | 0.00034158 | 7281 | 1.15 | 2248 | 0.00039282 | 2282
EEL RIVER 1102409694 | EEL RIVER 1102 | 192381102 | FALSE | 3.2458 | 0.087877 | 3.3337 | 67.5 | 0.0001872 | 10242 | 1.8563 | 1682 | 0.00039266 | 2283
MORGAN HILL 2109145998 | MORGAN HILL 2109 | 83242109 | FALSE | 2.5453 | 0.56477 | 2.8887 | 43.5 | 0.00035922 | 6992 | 1.1387 | 2261 | 0.00039206 | 2284
SAN CARLOS 11048846 | SAN CARLOS 1104 | 24181104 | FALSE | 4.3696 | 4.2495 | 4.0363 | 71.3333 | 0.00057604 | 4577 | 0.99215 | 2404 | 0.00039139 | 2285
NARROWS 21052426 | NARROWS 2105 | 153132105 | FALSE | 17.3647 | 3.3074 | 9.1314 | 321.5 | 0.00035593 | 7045 | 1.4497 | 1888 | 0.00039139 | 2286
SMARTVILLE 1101CB | SMARTVILLE 1101 | 153791101 | FALSE | 16.1735 | 0.65061 | 16.5498 | 299 | 0.0002013 | 10019 | 1.6586 | 1764 | 0.00039114 | 2287
FORT BRAGG A 11041316 | FORT BRAGG A 1104 | 42761104 | FALSE | 10.441 | 2.5055 | 12.3311 | 191.3333 | 0.00034825 | 7169 | 1.1275 | 2271 | 0.00039105 | 2288
STAFFORD 1102524 | STAFFORD 1102 | 43201102 | FALSE | 12.8168 | 5.177 | 6.8143 | 244.8333 | 0.00050684 | 5319 | 1.0183 | 2371 | 0.00039073 | 2289
COTATI 1105701873 | COTATI 1105 | 42271105 | TRUE | 0.48703 | 0.065451 | 0.55248 | 9.5 | 0.00033958 | 7314 | 1.15 | 2248 | 0.00039052 | 2290
FROGTOWN 170211212 | FROGTOWN 1702 | 163451702 | FALSE | 22.281 | 1.1022 | 23.3832 | 445.5 | 0.00016431 | 10542 | 2.5229 | 1505 | 0.00039045 | 2291
DEL MONTE 2103617344 | DEL MONTE 2103 | 182222103 | FALSE | 2.4867 | 0.92471 | 2.4235 | 46 | 0.00045842 | 5823 | 0.96566 | 2433 | 0.00039038 | 2292
GUALALA 1112662 | GUALALA 1112 | 42841112 | FALSE | 10.0773 | 1.2623 | 6.4206 | 185.5 | 0.000395 | 6510 | 0.92009 | 2471 | 0.00038993 | 2293
SUNOL 1101605520 | SUNOL 1101 | 14241101 | FALSE | 16.2034 | 0.34064 | 2.8032 | 315 | 0.00015791 | 10619 | 2.4342 | 1525 | 0.00038948 | 2294
PHILO 11022600 | PHILO 1102 | 42601102 | FALSE | 20.55 | 0.39093 | 20.9409 | 386.5 | 0.00031394 | 7738 | 1.2426 | 2070 | 0.00038907 | 2295
DEL MAR 210975802 | DEL MAR 2109 | 152582109 | TRUE | 0.40656 | 0 | 0.33943 | 8.5 | 0.00047443 | 5655 | 0.91653 | 2474 | 0.00038886 | 2296
COLUSA 1100CB | COLUSA 1100 | 62021100 |  | 0.023412 | 0 |  | 0.5 | 0.0073173 | 4 | 0.053073 | 8251 | 0.00038835 | 2297
ALTO 1122CB | ALTO 1122 | 42031122 | FALSE | 3.4776 | 1.767 | 2.914 | 54.3333 | 0.00074715 | 2519 | 0.47893 | 2843 | 0.00038771 | 2298
ECHO SUMMIT 1101481660 | ECHO SUMMIT 1101 | 158031101 | FALSE | 1.1404 | 0 | 1.0487 | 22 | 0.00032688 | 7509 | 1.1863 | 2150 | 0.00038767 | 2299
WILLOW PASS 2107273996 | WILLOW PASS 2107 | 13912107 |  | 1.5681 | 0.7553 |  | 27 | 0.00054576 | 4901 | 1.8964 | 1672 | 0.00038758 | 2300
BIG RIVER 1101954 | BIG RIVER 1101 | 43081101 | FALSE | 10.4557 | 0.53649 | 7.8332 | 187.5 | 0.00033623 | 7362 | 1.1309 | 2270 | 0.00038742 | 2301
VOLTA 110253130 | VOLTA 1102 | 102541102 | FALSE | 13.8447 | 1.1242 | 14.9689 | 265.5 | 0.0002459 | 9168 | 1.621 | 1779 | 0.00038715 | 2302
BOLINAS 110137034 | BOLINAS 1101 | 42261101 | FALSE | 4.5639 | 0.3696 | 4.9335 | 97 | 0.00023587 | 9367 | 1.6477 | 1768 | 0.00038657 | 2303
ANNAPOLIS 110176842 | ANNAPOLIS 1101 | 42861101 | FALSE | 5.5249 | 0.11885 | 5.6438 | 108 | 0.00032181 | 7595 | 1.2152 | 2110 | 0.00038606 | 2304
HIGGINS 1110429714 | HIGGINS 1110 | 152691110 | FALSE | 8.9935 | 0.16114 | 8.6572 | 166.5 | 0.00034391 | 7239 | 1.1831 | 2158 | 0.00038457 | 2305
BIG RIVER 110179628 | BIG RIVER 1101 | 43081101 | FALSE | 14.6743 | 2.1105 | 16.2292 | 278.5 | 0.00032949 | 7459 | 1.1718 | 2186 | 0.00038444 | 2306
SUNOL 1101CB | SUNOL 1101 | 14241101 | FALSE | 6.8104 | 0.4305 | 3.3971 | 115.5 | 0.00040507 | 6398 | 1.1311 | 2269 | 0.00038418 | 2307
ALTO 112278672 | ALTO 1122 | 42031122 | FALSE | 9.3165 | 8.239 | 6.4065 | 144.6667 | 0.00075586 | 2423 | 0.49309 | 2827 | 0.00038371 | 2308
COTTONWOOD 11031348 | COTTONWOOD 1103 | 102931103 | FALSE | 31.8731 | 2.8654 | 31.2087 | 565.5 | 0.00023099 | 9465 | 1.9219 | 1660 | 0.00038337 | 2309
PERRY 1101W52 | PERRY 1101 | 183071101 | FALSE | 4.105 | 2.6403 | 5.0284 | 60.5 | 0.00047899 | 5609 | 0.80002 | 2559 | 0.00038122 | 2310
FORT BRAGG A 11013100 | FORT BRAGG A 1101 | 42761101 | FALSE | 14.7025 | 3.5562 | 15.1809 | 279.5 | 0.00040073 | 6446 | 0.95469 | 2444 | 0.00038108 | 2311
NOVATO 1101405812 | NOVATO 1101 | 42211101 | TRUE | 0.43275 | 0.33864 | 0.21879 | 9.5 | 0.00044492 | 5963 | 0.97753 | 2421 | 0.00038045 | 2312
COARSEGOLD 21045525 | COARSEGOLD 2104 | 254432104 | FALSE | 12.8089 | 1.1952 | 14.004 | 241 | 0.00023563 | 9373 | 1.5456 | 1811 | 0.00038006 | 2313
ROB ROY 210538430 | ROB ROY 2105 | 83692105 | FALSE | 6.375 | 1.8213 | 4.0427 | 96.1667 | 0.00059273 | 4385 | 0.7293 | 2618 | 0.00037971 | 2314
WOODSIDE 11049030 | WOODSIDE 1104 | 24251104 | FALSE | 2.5913 | 1.7685 | 3.2909 | 41.8333 | 0.00054243 | 4931 | 0.73849 | 2615 | 0.00037964 | 2315
FORT BRAGG A 110231304 | FORT BRAGG A 1102 | 42761102 | FALSE | 20.0559 | 0.46552 | 20.5214 | 402 | 0.00033007 | 7447 | 1.15 | 2248 | 0.00037958 | 2316
FRUITLAND 11422006 | FRUITLAND 1142 | 192311142 | FALSE | 8.8163 | 1.5078 | 8.588 | 170 | 0.00040584 | 6382 | 1.0109 | 2377 | 0.00037937 | 2317
OCEANO 1104V36 | OCEANO 1104 | 182601104 | FALSE | 12.9417 | 1.3321 | 10.3756 | 224.1667 | 0.00018482 | 10279 | 2.223 | 1574 | 0.00037914 | 2318
RED BLUFF 1105146070 | RED BLUFF 1105 | 103541105 | FALSE | 14.1022 | 0.81494 | 12.9457 | 259.5 | 0.0003084 | 7833 | 1.3177 | 1991 | 0.00037907 | 2319
FRANKLIN 1101P138 | FRANKLIN 1101 | 13921101 | FALSE | 1.4956 | 0.47528 | 1.7455 | 23.5 | 0.00037411 | 6777 | 1.0503 | 2342 | 0.00037874 | 2320
POTTER VALLEY P H 110537476 | POTTER VALLEY P H 1105 | 42281105 | FALSE | 8.7707 | 0.42344 | 2.0055 | 157 | 0.00024016 | 9286 | 2.4227 | 1529 | 0.00037714 | 2321
GANSNER 1101372132 | GANSNER 1101 | 103021101 | TRUE | 1.3621 | 0.018127 | 0.30472 | 26 | 0.00029807 | 8049 | 1.0963 | 2309 | 0.00037693 | 2322
LAKEVILLE 110287432 | LAKEVILLE 1102 | 43371102 | FALSE | 13.5113 | 0.48663 | 9.3663 | 271 | 0.00014072 | 10781 | 2.6224 | 1479 | 0.00037682 | 2323
GARBERVILLE 1101CB | GARBERVILLE 1101 | 192221101 | FALSE | 8.9483 | 0.85498 | 6.4009 | 158.9167 | 0.00034355 | 7248 | 1.1914 | 2144 | 0.0003767 | 2324
WOODSIDE 11018522 | WOODSIDE 1101 | 24251101 | FALSE | 9.4278 | 2.5375 | 2.0229 | 181 | 0.00072016 | 2851 | 0.59527 | 2741 | 0.00037531 | 2325
COTTONWOOD 11031616 | COTTONWOOD 1103 | 102931103 | FALSE | 49.1834 | 2.5585 | 48.8275 | 900.5 | 0.00013828 | 10809 | 3.185 | 1358 | 0.00037479 | 2326
FORT BRAGG A 11013113 | FORT BRAGG A 1101 | 42761101 | FALSE | 9.6134 | 0.67241 | 10.2858 | 187.5 | 0.00031616 | 7696 | 1.1736 | 2178 | 0.00037387 | 2327
CORRAL 110275622 | CORRAL 1102 | 162991102 | FALSE | 5.6959 | 1.6831 | 1.2385 | 99.5 | 0.00033555 | 7376 | 1.0854 | 2316 | 0.00037376 | 2328
SAN RAFAEL 1109519234 | SAN RAFAEL 1109 | 42011109 | FALSE | 3.5575 | 2.767 | 4.0422 | 59.5 | 0.00057485 | 4593 | 0.64597 | 2688 | 0.0003737 | 2329
DIAMOND SPRINGS 1104147386 | DIAMOND SPRINGS 1104 | 152261104 | FALSE | 6.7501 | 1.9856 | 5.7303 | 113.3333 | 0.00044164 | 5996 | 0.92399 | 2469 | 0.00037364 | 2330
BOLINAS 11011236 | BOLINAS 1101 | 42261101 | FALSE | 4.1557 | 0.1896 | 3.1585 | 81.5 | 0.00024848 | 9112 | 1.3944 | 1935 | 0.00037363 | 2331
BIG RIVER 11012183 | BIG RIVER 1101 | 43081101 | FALSE | 2.4871 | 0.066884 | 2.554 | 44.5 | 0.00029502 | 8108 | 1.2659 | 2036 | 0.00037334 | 2332
CLARK ROAD 1101CB | CLARK ROAD 1101 | 103091101 | TRUE | 0.020705 | 0 | 0.017864 | 1 | 0.00049141 | 5481 | 0.6085 | 2721 | 0.00037317 | 2333
FROGTOWN 1702L5407 | FROGTOWN 1702 | 163451702 | FALSE | 18.1213 | 0.50787 | 18.5432 | 359.5 | 7.8447e-05 | 11109 | 4.9561 | 1143 | 0.00037268 | 2334
LAYTONVILLE 110264908 | LAYTONVILLE 1102 | 42681102 | FALSE | 6.2623 | 1.6885 | 4.4148 | 113 | 0.00036352 | 6935 | 0.94359 | 2455 | 0.00037236 | 2335
VOLTA 110293418 | VOLTA 1102 | 102541102 | FALSE | 2.5574 | 0.010396 | 2.5678 | 43.3333 | 0.0002956 | 8093 | 1.2739 | 2032 | 0.00037199 | 2336
BELL 1108127062 | BELL 1108 | 152701108 | FALSE | 10.4553 | 2.6711 | 12.9769 | 187.5 | 0.00031902 | 7652 | 1.1686 | 2199 | 0.00037191 | 2337
SAN LUIS OBISPO 1101CB | SAN LUIS OBISPO 1101 | 182631101 | FALSE | 6.6669 | 3.092 | 4.4962 | 111.1667 | 0.00037054 | 6836 | 1.184 | 2156 | 0.0003719 | 2338
COTTONWOOD 1101384360 | COTTONWOOD 1101 | 102931101 | FALSE | 6.2338 | 1.4152 | 5.2576 | 97.1667 | 0.00038705 | 6617 | 0.9603 | 2438 | 0.00037103 | 2339
FORT BRAGG A 1102956 | FORT BRAGG A 1102 | 42761102 | FALSE | 6.4519 | 0.96106 | 6.1014 | 112 | 0.00037069 | 6829 | 1.0338 | 2358 | 0.00037071 | 2340
DEL MONTE 210436720 | DEL MONTE 2104 | 182222104 | FALSE | 7.9765 | 1.6543 | 6.217 | 154 | 0.00033681 | 7351 | 1.3906 | 1938 | 0.00037041 | 2341
ELK 110191336 | ELK 1101 | 42981101 | FALSE | 8.3318 | 0.42605 | 3.4088 | 155.3333 | 0.00032059 | 7618 | 1.1585 | 2225 | 0.00036942 | 2342
PEORIA 170570198 | PEORIA 1705 | 163781705 | FALSE | 3.2114 | 0.42645 | 2.1289 | 58.5 | 0.00034523 | 7217 | 1.4528 | 1887 | 0.00036891 | 2343
BERESFORD 0403435168 | BERESFORD 0403 | 24040403 | FALSE | 1.8038 | 1.0116 | 1.839 | 36 | 0.00041739 | 6250 | 0.98319 | 2411 | 0.00036871 | 2344
OCEANO 1104Q08 | OCEANO 1104 | 182601104 | FALSE | 12.3893 | 0.99115 | 13.3804 | 237 | 0.0002441 | 9199 | 1.4875 | 1858 | 0.00036771 | 2345
HIGHLANDS 110439458 | HIGHLANDS 1104 | 43361104 | FALSE | 5.3626 | 1.7188 | 1.065 | 83.5 | 0.00044437 | 5966 | 0.77339 | 2582 | 0.00036762 | 2346
PENRYN 11072708 | PENRYN 1107 | 152561107 | FALSE | 10.6052 | 0.59249 | 9.8218 | 182.5 | 0.00036284 | 6949 | 0.97791 | 2420 | 0.00036752 | 2347
HIGGINS 1107CB | HIGGINS 1107 | 152691107 | FALSE | 19.0337 | 7.7087 | 5.4458 | 322.0833 | 0.00057743 | 4557 | 1.038 | 2355 | 0.00036699 | 2348
SNEATH LANE 110715341 | SNEATH LANE 1107 | 22721107 | TRUE | 1.2853 | 0.80676 | 0.21148 | 19.3333 | 0.00079502 | 2011 | 0.38552 | 2932 | 0.00036672 | 2349
SAN LUIS OBISPO 1108144690 | SAN LUIS OBISPO 1108 | 182631108 | TRUE | 0.55924 | 0.39125 | 0.3537 | 10 | 0.00043698 | 6044 | 0.98871 | 2407 | 0.00036608 | 2350
MENDOCINO 1101CB | MENDOCINO 1101 | 42951101 | FALSE | 4.122 | 0.7945 | 2.4865 | 76.3333 | 0.00040112 | 6439 | 0.94669 | 2452 | 0.00036549 | 2351
POINT ARENA 11014923 | POINT ARENA 1101 | 43381101 | FALSE | 2.9333 | 0.090892 | 3.0241 | 65.5 | 0.00028315 | 8350 | 1.2914 | 2017 | 0.00036544 | 2352
ROB ROY 210410960 | ROB ROY 2104 | 83692104 | FALSE | 27.9956 | 5.708 | 20.4481 | 539 | 0.00044069 | 6005 | 0.79379 | 2562 | 0.0003647 | 2353
FRUITLAND 114263170 | FRUITLAND 1142 | 192311142 | FALSE | 13.4568 | 1.558 | 5.672 | 263 | 0.00035263 | 7094 | 1.0758 | 2326 | 0.00036401 | 2354
SONOMA 1105404 | SONOMA 1105 | 42721105 | FALSE | 4.575 | 1.235 | 2.9181 | 92.5 | 0.00038949 | 6580 | 1.1238 | 2276 | 0.00036386 | 2355
ANNAPOLIS 1101528344 | ANNAPOLIS 1101 | 42861101 | FALSE | 26.8538 | 0.94952 | 27.8032 | 517.5 | 0.00029504 | 8107 | 1.2572 | 2050 | 0.00036291 | 2356
DEL MONTE 2103468158 | DEL MONTE 2103 | 182222103 | FALSE | 0.9686 | 0.4179 | 0.68716 | 18 | 0.00055827 | 4774 | 0.6382 | 2696 | 0.00036288 | 2357
LAYTONVILLE 1101CB | LAYTONVILLE 1101 | 42681101 | FALSE | 9.2078 | 1.289 | 6.2758 | 171 | 0.00030233 | 7958 | 1.1796 | 2164 | 0.00036243 | 2358
DIVIDE 1103567884 | DIVIDE 1103 | 182571103 | FALSE | 2.8345 | 1.1706 | 3.5341 | 54.5 | 0.00021902 | 9718 | 1.545 | 1812 | 0.00036241 | 2359
BELLEVUE 2103646 | BELLEVUE 2103 | 43182103 | FALSE | 12.2055 | 2.0644 | 8.5126 | 225 | 0.00030478 | 7916 | 1.245 | 2065 | 0.00036239 | 2360
NOVATO 110455398 | NOVATO 1104 | 42211104 | FALSE | 11.2161 | 0.07532 | 3.043 | 211.5 | 0.00031895 | 7654 | 1.4748 | 1865 | 0.00036158 | 2361
PARADISE 110536656 | PARADISE 1105 | 102831105 | TRUE | 0.64755 | 0.30431 | 0.18636 | 10.5 | 0.00068423 | 3283 | 0.47767 | 2844 | 0.00036148 | 2362
GEYSERVILLE 1102274 | GEYSERVILLE 1102 | 42891102 | FALSE | 18.4081 | 1.3238 | 6.3669 | 347 | 0.00028928 | 8210 | 1.0284 | 2364 | 0.00036109 | 2363
LAURELES 1112562376 | LAURELES 1112 | 182371112 | FALSE | 8.051 | 1.9107 | 9.3357 | 164.5 | 0.00023443 | 9399 | 1.8278 | 1694 | 0.00036028 | 2364
FORT BRAGG A 11014622 | FORT BRAGG A 1101 | 42761101 | FALSE | 13.5612 | 0.86317 | 14.4244 | 256 | 0.00029542 | 8097 | 1.2572 | 2049 | 0.00036024 | 2365
DIAMOND SPRINGS 1107203504 | DIAMOND SPRINGS 1107 | 152261107 | TRUE | 0.33067 | 0.034358 | 0.13508 | 6.5 | 0.00029441 | 8119 | 1.2226 | 2099 | 0.00035995 | 2366
BRUNSWICK 11102664 | BRUNSWICK 1110 | 152481110 | FALSE | 10.815 | 4.184 | 9.1717 | 208.5 | 0.00035913 | 6993 | 1.2165 | 2107 | 0.0003594 | 2367
FAIRVIEW 2207CB | FAIRVIEW 2207 | 13432207 | TRUE | 4.9914 | 0.94613 | 0.17053 | 66.8333 | 0.00084442 | 1619 | 0.65946 | 2680 | 0.00035893 | 2368
SALT SPRINGS 21013116 | SALT SPRINGS 2101 | 163692101 | FALSE | 1.0415 | 0.28574 | 0.9611 | 23 | 0.00029247 | 8156 | 1.2258 | 2090 | 0.00035861 | 2369
CLAY 1102CB | CLAY 1102 | 163341102 | FALSE | 1.5875 | 0.0094437 | 0.8161 | 25.3333 | 0.00055273 | 4838 | 0.60002 | 2734 | 0.00035861 | 2370
SILVERADO 2102942170 | SILVERADO 2102 | 43432102 | FALSE | 9.0499 | 0.47102 | 2.966 | 178.5 | 0.00041407 | 6294 | 1.1718 | 2187 | 0.00035849 | 2371
CORRAL 110336680 | CORRAL 1103 | 162991103 | FALSE | 19.7613 | 3.0057 | 9.5139 | 377.5 | 0.00025257 | 9030 | 1.4492 | 1890 | 0.0003578 | 2372
PENRYN 1103CB | PENRYN 1103 | 152561103 | FALSE | 3.1381 | 0.58931 | 2.8594 | 48.75 | 0.00036983 | 6842 | 0.97805 | 2419 | 0.00035774 | 2373
FLINT 110140666 | FLINT 1101 | 152531101 | TRUE | 1.6511 | 0.75611 | 0.3747 | 25.3333 | 0.00074266 | 2576 | 0.49095 | 2833 | 0.00035749 | 2374
SNEATH LANE 1106CB | SNEATH LANE 1106 | 22721106 | FALSE | 6.1467 | 4.7902 | 3.6977 | 93.5833 | 0.00066923 | 3442 | 1.2256 | 2091 | 0.00035746 | 2375
EEL RIVER 11021902 | EEL RIVER 1102 | 192381102 | FALSE | 7.261 | 0.094266 | 6.2785 | 144 | 0.00032949 | 7460 | 1.0006 | 2390 | 0.00035743 | 2376
SAND CREEK 1103CB | SAND CREEK 1103 | 254601103 | FALSE | 13.0144 | 0.18444 | 13.1988 | 247 | 0.00011831 | 10966 | 2.97 | 1398 | 0.00035672 | 2377
COARSEGOLD 210210610 | COARSEGOLD 2102 | 254432102 | FALSE | 1.3787 | 0.036833 | 1.4155 | 22.5 | 0.00030809 | 7844 | 1.1565 | 2229 | 0.00035657 | 2378
SNEATH LANE 1107CB | SNEATH LANE 1107 | 22721107 | FALSE | 3.8962 | 3.743 | 1.3422 | 59.5833 | 0.00070964 | 2981 | 0.61615 | 2717 | 0.00035649 | 2379
ELK 11011272 | ELK 1101 | 42981101 | FALSE | 27.079 | 1.9348 | 7.0791 | 501.3333 | 0.00030707 | 7864 | 1.164 | 2211 | 0.00035637 | 2380
WISE 110163199 | WISE 1101 | 152271101 | TRUE | 0.90893 | 0.13662 | 0.61247 | 16 | 0.0003627 | 6951 | 1.105 | 2299 | 0.00035474 | 2381
RESERVATION ROAD 11023030 | RESERVATION ROAD 1102 | 182731102 | FALSE | 25.6702 | 1.3704 | 7.4928 | 524 | 0.00023164 | 9448 | 2.2049 | 1576 | 0.00035462 | 2382
VOLTA 11021650 | VOLTA 1102 | 102541102 | FALSE | 21.6661 | 1.3291 | 22.9951 | 418.5 | 0.00020737 | 9922 | 1.747 | 1721 | 0.00035435 | 2383
ALTO 11201214 | ALTO 1120 | 42031120 | FALSE | 4.5318 | 2.2159 | 4.4562 | 85.1667 | 0.00040877 | 6346 | 1.595 | 1788 | 0.0003543 | 2384
PUEBLO 2102279478 | PUEBLO 2102 | 43292102 |  | 1.7448 | 0.060197 |  | 34.5 | 0.00021197 | 9842 | 2.6508 | 1471 | 0.00035292 | 2385
GUALALA 1111289822 | GUALALA 1111 | 42841111 | FALSE | 3.0777 | 0 | 2.5947 | 63.5 | 0.00035392 | 7075 | 1.0418 | 2352 | 0.00035256 | 2386
ROB ROY 210410714 | ROB ROY 2104 | 83692104 | FALSE | 19.524 | 2.5168 | 15.0862 | 368.3333 | 0.00038701 | 6618 | 0.8313 | 2537 | 0.00035219 | 2387
LAKEVILLE 1102347280 | LAKEVILLE 1102 | 43371102 | FALSE | 12.474 | 0.32821 | 7.4691 | 246.5 | 0.00013939 | 10794 | 2.3124 | 1552 | 0.00035211 | 2388
WISE 11022230 | WISE 1102 | 152271102 | FALSE | 25.0704 | 2.6624 | 25.9306 | 464.5 | 0.00021881 | 9721 | 1.6457 | 1770 | 0.00035184 | 2389
BRUNSWICK 1107969778 | BRUNSWICK 1107 | 152481107 | FALSE | 1.0162 | 0.87026 | 1.2306 | 20 | 0.00047498 | 5648 | 0.7706 | 2583 | 0.00035093 | 2390
MAPLE CREEK 1101CB | MAPLE CREEK 1101 | 192101101 | FALSE | 12.089 | 0.28832 | 8.5003 | 221.5 | 0.00024861 | 9106 | 1.4495 | 1889 | 0.0003484 | 2391
HAMILTON BRANCH 11012436 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 5.3369 | 0.027317 | 5.3642 | 110.5 | 0.00024036 | 9280 | 1.4366 | 1896 | 0.00034787 | 2392
VALLEY VIEW 1105P126 | VALLEY VIEW 1105 | 14341105 | FALSE | 2.0564 | 1.7727 | 1.7578 | 40 | 0.00050448 | 5341 | 0.70109 | 2642 | 0.00034771 | 2393
TIVY VALLEY 11077380 | TIVY VALLEY 1107 | 252941107 | FALSE | 28.223 | 2.7931 | 12.6322 | 550 | 0.00017223 | 10454 | 2.3397 | 1545 | 0.00034699 | 2394
PENRYN 11051378 | PENRYN 1105 | 152561105 | FALSE | 1.9199 | 0.83312 | 0.98839 | 31 | 0.00056602 | 4699 | 0.6968 | 2650 | 0.00034665 | 2395
PUEBLO 2102773926 | PUEBLO 2102 | 43292102 | TRUE | 2.1157 | 0.091018 | 0.21164 | 42.5 | 0.00039418 | 6520 | 0.9685 | 2431 | 0.00034664 | 2396
FORT ROSS 1121612266 | FORT ROSS 1121 | 42851121 | FALSE | 4.6367 | 0.31586 | 4.9526 | 90 | 0.00023127 | 9456 | 1.6687 | 1758 | 0.00034608 | 2397
MORGAN HILL 2111997000 | MORGAN HILL 2111 | 83242111 | FALSE | 16.0079 | 2.7704 | 1.6307 | 333 | 0.00028614 | 8285 | 1.164 | 2210 | 0.0003458 | 2398
RESERVATION ROAD 1102CB | RESERVATION ROAD 1102 | 182731102 | FALSE | 17.1648 | 2.3133 | 8.0979 | 346.8333 | 0.00032971 | 7454 | 1.5628 | 1798 | 0.00034569 | 2399
COTTONWOOD 110168190 | COTTONWOOD 1101 | 102931101 | FALSE | 25.2715 | 1.2999 | 24.6293 | 451 | 0.00015138 | 10686 | 2.375 | 1538 | 0.00034512 | 2400
HIGGINS 1103CB | HIGGINS 1103 | 152691103 | FALSE | 1.1457 | 0.084989 | 0.851 | 23.0833 | 0.00042306 | 6192 | 0.90135 | 2484 | 0.00034503 | 2401
SAN LUIS OBISPO 1107248566 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 1.5552 | 0.17 | 1.7252 | 31.5 | 0.00027592 | 8514 | 1.2384 | 2073 | 0.00034288 | 2402
WILLITS 1103968 | WILLITS 1103 | 42661103 | FALSE | 7.9886 | 1.3867 | 7.9957 | 142 | 0.00026356 | 8791 | 1.1846 | 2155 | 0.0003426 | 2403
SAND CREEK 1103799118 | SAND CREEK 1103 | 254601103 | FALSE | 23.1334 | 1.5272 | 24.6606 | 437.5 | 0.00011545 | 10980 | 2.9719 | 1396 | 0.000342 | 2404
OREGON TRAIL 110335002 | OREGON TRAIL 1103 | 103521103 | FALSE | 57.1254 | 4.3508 | 61.4761 | 1002.5 | 0.00023549 | 9378 | 1.5183 | 1832 | 0.00034131 | 2405
SAN LUIS OBISPO 1107V58 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 2.249 | 0.024454 | 1.077 | 38.5 | 0.00055673 | 4796 | 0.64031 | 2692 | 0.00034096 | 2406
DESCHUTES 11011380 | DESCHUTES 1101 | 103351101 | FALSE | 23.5255 | 1.5269 | 17.7489 | 446 | 0.00022562 | 9592 | 1.6157 | 1781 | 0.00034045 | 2407
LAKEWOOD 210738404 | LAKEWOOD 2107 | 13532107 | FALSE | 4.3988 | 0 | 1.9328 | 48 | 0.00069889 | 3114 | 0.51362 | 2812 | 0.0003403 | 2408
OREGON TRAIL 11021382 | OREGON TRAIL 1102 | 103521102 | FALSE | 5.5597 | 0.38501 | 5.9447 | 103 | 0.00024792 | 9127 | 1.4077 | 1921 | 0.00033988 | 2409
RINCON 1101580 | RINCON 1101 | 43321101 |  | 2.8885 | 1.0887 |  | 54 | 0.00079562 | 2002 | 0.46407 | 2856 | 0.00033966 | 2410
BRUNSWICK 1102940 | BRUNSWICK 1102 | 152481102 | FALSE | 3.5027 | 0.44241 | 1.1205 | 59.1667 | 0.0006122 | 4142 | 0.48737 | 2836 | 0.00033921 | 2411
SAN RAFAEL 1105534 | SAN RAFAEL 1105 | 42011105 | FALSE | 1.5789 | 0.71645 | 1.2564 | 31.5 | 0.00049778 | 5416 | 0.71891 | 2627 | 0.00033885 | 2412
BIG RIVER 11011052 | BIG RIVER 1101 | 43081101 | FALSE | 3.8606 | 0.32634 | 2.9841 | 71 | 0.00036704 | 6883 | 0.90841 | 2479 | 0.00033854 | 2413
GUALALA 111223444 | GUALALA 1112 | 42841112 | FALSE | 14.7065 | 0.49808 | 15.2046 | 289 | 0.00028903 | 8215 | 1.1725 | 2183 | 0.00033831 | 2414
EL CERRITO G 111257953 | EL CERRITO G 1112 | 12501112 | TRUE | 0.75099 | 0.91182 | 0.35301 | 11.5 | 0.00052581 | 5113 | 0.53 | 2795 | 0.00033796 | 2415
CLAY 110359714 | CLAY 1103 | 163341103 | FALSE | 4.5527 | 0.2053 | 4.758 | 83.5 | 0.00022939 | 9503 | 1.4324 | 1898 | 0.00033792 | 2416
HORSESHOE 1101603250 | HORSESHOE 1101 | 152571101 | TRUE | 1.3975 | 0.48431 | 0.56865 | 21.3333 | 0.00042828 | 6139 | 0.74388 | 2606 | 0.00033767 | 2417
MOLINO 11015042 | MOLINO 1101 | 42571101 | FALSE | 6.9389 | 0.85801 | 3.7468 | 123.5 | 0.00032083 | 7615 | 1.0072 | 2383 | 0.00033742 | 2418
IGNACIO 110584764 | IGNACIO 1105 | 42481105 | TRUE | 2.8965 | 2.7137 | 0.29188 | 45 | 0.00068346 | 3290 | 0.62745 | 2707 | 0.00033656 | 2419
IGNACIO 11011300 | IGNACIO 1101 | 42481101 | FALSE | 6.1088 | 5.5087 | 4.6044 | 108 | 0.00061177 | 4148 | 0.58664 | 2750 | 0.00033649 | 2420
SOBRANTE 1103N510R | SOBRANTE 1103 | 14671103 | TRUE | 0.8718 | 0.16458 | 0.19223 | 15.3333 | 0.00092235 | 1137 | 0.38495 | 2933 | 0.00033636 | 2421
MIRABEL 1101688780 | MIRABEL 1101 | 42091101 | FALSE | 1.2923 | 0.27892 | 0.63435 | 22.3333 | 0.00041855 | 6239 | 0.99867 | 2395 | 0.00033563 | 2422
SOLEDAD 21027008 | SOLEDAD 2102 | 182052102 | FALSE | 18.0743 | 0.57419 | 3.0155 | 360 | 0.00021619 | 9760 | 3.4457 | 1323 | 0.00033469 | 2423
LAS PULGAS 0401104588 | LAS PULGAS 0401 | 24120401 | FALSE | 0.77158 | 0.74578 | 0.6671 | 11.5 | 0.00054701 | 4889 | 0.62538 | 2708 | 0.00033451 | 2424
ATASCADERO 1102A28 | ATASCADERO 1102 | 182541102 | FALSE | 2.5484 | 0.91792 | 2.083 | 40 | 0.0003458 | 7209 | 1.1783 | 2167 | 0.00033414 | 2425
VALLEY VIEW 1103218424 | VALLEY VIEW 1103 | 14341103 | TRUE | 0.54711 | 0 | 0.45837 | 9.5 | 0.00029049 | 8189 | 1.15 | 2248 | 0.00033406 | 2426
HOLLISTER 21044403 | HOLLISTER 2104 | 182492104 |  | 19.1062 | 1.1065 |  | 361.5 | 9.5962e-05 | 11065 | 6.2141 | 1050 | 0.00033389 | 2427
VOLTA 11011568 | VOLTA 1101 | 102541101 | FALSE | 23.493 | 0.44911 | 23.8686 | 471.8333 | 0.00013681 | 10822 | 2.2297 | 1573 | 0.00033385 | 2428
DESCHUTES 11049726 | DESCHUTES 1104 | 103351104 | FALSE | 16.9022 | 1.1933 | 16.4591 | 300 | 0.00020492 | 9964 | 1.6989 | 1742 | 0.00033358 | 2429
SISQUOC 1102M54 | SISQUOC 1102 | 182811102 | FALSE | 30.4447 | 0.80986 | 17.9377 | 565 | 0.00015538 | 10643 | 2.2468 | 1569 | 0.00033291 | 2430
OLEMA 11011252 | OLEMA 1101 | 42291101 | FALSE | 4.0536 | 0.35557 | 4.4092 | 68.3333 | 0.0002817 | 8384 | 1.1688 | 2197 | 0.00033272 | 2431
UKIAH 1115CB | UKIAH 1115 | 42771115 | FALSE | 6.2104 | 1.1932 | 5.309 | 99.75 | 0.00045736 | 5843 | 0.78347 | 2574 | 0.00033265 | 2432
BURNEY 11019042 | BURNEY 1101 | 103311101 | FALSE | 3.1535 | 0.82865 | 3.9821 | 54.5 | 0.00032465 | 7546 | 1.0907 | 2311 | 0.00033184 | 2433
HALF MOON BAY 11036012 | HALF MOON BAY 1103 | 24101103 | FALSE | 12.3729 | 1.3867 | 4.4585 | 247.5 | 0.00036349 | 6937 | 0.8566 | 2518 | 0.00033154 | 2434
LUCERNE 110676850 | LUCERNE 1106 | 43351106 | FALSE | 3.7187 | 2.6102 | 3.0102 | 56.5 | 0.00056578 | 4700 | 0.69223 | 2652 | 0.00033124 | 2435
VIEJO 220285904 | VIEJO 2202 | 182852202 | FALSE | 1.9829 | 1.3267 | 1.2297 | 17.1667 | 0.00083531 | 1680 | 0.43803 | 2880 | 0.00033049 | 2436
POINT ARENA 1101474 | POINT ARENA 1101 | 43381101 | FALSE | 8.8361 | 0.42356 | 9.2596 | 171.8333 | 0.0002778 | 8472 | 1.1939 | 2141 | 0.00033016 | 2437
DESCHUTES 11011652 | DESCHUTES 1101 | 103351101 | FALSE | 24.5724 | 0.77987 | 20.9271 | 464 | 0.00018641 | 10257 | 1.7132 | 1737 | 0.00032927 | 2438
OLEMA 110150396 | OLEMA 1101 | 42291101 | FALSE | 12.8333 | 3.1914 | 15.7392 | 234.8333 | 0.00026672 | 8726 | 1.265 | 2038 | 0.00032912 | 2439
HALF MOON BAY 1103461558 | HALF MOON BAY 1103 | 24101103 | FALSE | 4.1937 | 0.37997 | 4.5737 | 88.5 | 0.00019133 | 10191 | 1.7972 | 1704 | 0.00032903 | 2440
VOLTA 11029742 | VOLTA 1102 | 102541102 | FALSE | 8.9834 | 1.0791 | 8.9277 | 175 | 0.00026297 | 8807 | 1.2473 | 2060 | 0.00032826 | 2441
WYANDOTTE 1110873858 | WYANDOTTE 1110 | 102911110 | FALSE | 3.2118 | 0.67153 | 2.531 | 57.5 | 0.00032214 | 7589 | 1.113 | 2287 | 0.00032676 | 2442
POSO MOUNTAIN 21013990 | POSO MOUNTAIN 2101 | 253642101 | FALSE | 5.5508 | 0.011832 | 3.649 | 98 | 0.00017123 | 10471 | 1.6458 | 1769 | 0.00032629 | 2443
CLAY 110113442 | CLAY 1101 | 163341101 | FALSE | 30.9128 | 2.9878 | 25.7021 | 564 | 0.00021156 | 9851 | 2.4514 | 1520 | 0.00032629 | 2444
CHESTER 1102546744 | CHESTER 1102 | 103181102 | TRUE | 0.38228 | 0.018532 | 0.18074 | 6.5 | 0.00039794 | 6477 | 0.80049 | 2558 | 0.00032618 | 2445
WILLOW PASS 1101152874 | WILLOW PASS 1101 | 13911101 | TRUE | 0.81061 | 0.017464 | 0.45539 | 15.5 | 0.00030302 | 7947 | 1.0978 | 2304 | 0.00032613 | 2446
VALLEY VIEW 1105305072 | VALLEY VIEW 1105 | 14341105 | FALSE | 3.8442 | 2.6297 | 4.9618 | 68.5 | 0.00037309 | 6791 | 0.94628 | 2453 | 0.00032593 | 2447
MARTELL 1102CB | MARTELL 1102 | 163011102 | FALSE | 6.8681 | 0.38766 | 5.2225 | 130.8333 | 0.00031249 | 7758 | 1.4705 | 1869 | 0.00032561 | 2448
WYANDOTTE 1109170732 | WYANDOTTE 1109 | 102911109 | FALSE | 1.3837 | 0.017508 | 1.3768 | 21 | 0.00035351 | 7083 | 0.9695 | 2430 | 0.00032531 | 2449
ALTO 11251158 | ALTO 1125 | 42031125 | TRUE | 2.9546 | 2.0613 | 0.072006 | 44.6667 | 0.00078223 | 2127 | 0.31651 | 2996 | 0.00032521 | 2450
FLINT 1101CB | FLINT 1101 | 152531101 | TRUE | 2.6018 | 1.6721 | 0.56776 | 41 | 0.00074761 | 2514 | 0.46203 | 2859 | 0.00032519 | 2451
CHOLAME 2102X06 | CHOLAME 2102 | 182562102 | TRUE | 13.0063 | 0.24575 | 0.11683 | 285 | 0.00012749 | 10906 | 2.3295 | 1547 | 0.00032343 | 2452
PHILO 1102928 | PHILO 1102 | 42601102 | FALSE | 15.3476 | 0.53542 | 14.0164 | 299.5 | 0.00030198 | 7966 | 1.0344 | 2357 | 0.00032278 | 2453
WYANDOTTE 110777578 | WYANDOTTE 1107 | 102911107 | FALSE | 32.1156 | 3.5392 | 21.2158 | 574.5 | 0.00031538 | 7707 | 1.1081 | 2293 | 0.00032256 | 2454
RIO DELL 11028852 | RIO DELL 1102 | 192251102 | FALSE | 4.6672 | 0.34971 | 4.3175 | 91 | 0.00032768 | 7489 | 0.89653 | 2489 | 0.00032194 | 2455
RESERVATION ROAD 1101975548 | RESERVATION ROAD 1101 | 182731101 | FALSE | 8.8349 | 1.2575 | 4.8871 | 142 | 0.00043119 | 6107 | 0.67485 | 2666 | 0.00032114 | 2456
BELL 11082226 | BELL 1108 | 152701108 | FALSE | 15.0344 | 2.6813 | 15.9992 | 286.5 | 0.0003073 | 7857 | 1.1026 | 2301 | 0.00032108 | 2457
EDES 1112CR308 | EDES 1112 | 13681112 | FALSE | 3.5381 | 2.8195 | 5.4509 | 65 | 0.00060494 | 4241 | 0.51642 | 2811 | 0.00032091 | 2458
POTTER VALLEY P H 110495878 | POTTER VALLEY P H 1104 | 42281104 | FALSE | 14.3322 | 1.7794 | 2.5791 | 251.25 | 0.00029749 | 8058 | 1.5217 | 1827 | 0.00032085 | 2459
STELLING 110913228 | STELLING 1109 | 83481109 |  | 8.5317 | 4.7503 |  | 143.3333 | 0.00048635 | 5536 | 1.5556 | 1803 | 0.00032066 | 2460
WYANDOTTE 1109702710 | WYANDOTTE 1109 | 102911109 | TRUE | 1.4621 | 0.35778 | 0.50013 | 34.5 | 0.00048687 | 5529 | 0.58586 | 2752 | 0.00032066 | 2461
EEL RIVER 11024814 | EEL RIVER 1102 | 192381102 | FALSE | 24.2776 | 0.56654 | 24.1249 | 488 | 0.00021837 | 9725 | 1.4312 | 1900 | 0.00032053 | 2462
PETALUMA C 1109857148 | PETALUMA C 1109 | 42631109 | FALSE | 1.8745 | 0.79197 | 0.89193 | 31.5 | 0.00055171 | 4850 | 0.7465 | 2601 | 0.00032006 | 2463
CHESTER 1101656108 | CHESTER 1101 | 103181101 | FALSE | 0.73677 | 0.50463 | 0.78233 | 14.5 | 0.00033785 | 7339 | 1.038 | 2356 | 0.00031956 | 2464
PIT NO 5 11011660 | PIT NO 5 1101 | 101321101 | FALSE | 4.8692 | 0.42655 | 5.2957 | 91.5 | 0.00027718 | 8490 | 1.15 | 2248 | 0.00031876 | 2465
BIG RIVER 1101952 | BIG RIVER 1101 | 43081101 | FALSE | 16.9 | 1.9819 | 11.9543 | 330 | 0.00028009 | 8419 | 1.1408 | 2257 | 0.00031866 | 2466
OLETA 11011208 | OLETA 1101 | 163541101 | FALSE | 38.1317 | 1.8284 | 34.4495 | 689.5 | 0.00012631 | 10917 | 2.2647 | 1564 | 0.00031856 | 2467
ROSSMOOR 110676468 | ROSSMOOR 1106 | 14161106 | FALSE | 2.9789 | 2.3021 | 0.68055 | 44.3333 | 0.00060787 | 4197 | 0.4874 | 2835 | 0.00031846 | 2468
LOS OSITOS 2103695270 | LOS OSITOS 2103 | 182082103 | FALSE | 1.1051 | 0.17735 | 0.76327 | 17.5 | 0.00032333 | 7573 | 0.95562 | 2441 | 0.00031842 | 2469
KONOCTI 1102985276 | KONOCTI 1102 | 43311102 | TRUE | 1.1679 | 0.53239 | 0.13115 | 16 | 0.00049841 | 5405 | 0.63745 | 2697 | 0.00031793 | 2470
CLARKSVILLE 210419632 | CLARKSVILLE 2104 | 153612104 | FALSE | 9.0736 | 0.45219 | 5.4032 | 163.5 | 0.00035495 | 7055 | 1.6674 | 1759 | 0.0003179 | 2471
SAN RAFAEL 1104717160 | SAN RAFAEL 1104 | 42011104 | FALSE | 8.0275 | 7.8795 | 6.1092 | 124.8333 | 0.00082588 | 1767 | 0.38987 | 2927 | 0.00031769 | 2472
VACAVILLE 1112CB | VACAVILLE 1112 | 63601112 | TRUE | 3.3033 | 3.4447 | 0.39223 | 52.5 | 0.0007505 | 2475 | 0.46091 | 2862 | 0.00031742 | 2473
PERRY 110185870 | PERRY 1101 | 183071101 | FALSE | 2.0506 | 0.052634 | 0.9591 | 31.5 | 0.00048182 | 5585 | 0.58619 | 2751 | 0.00031732 | 2474
BRUNSWICK 1107357568 | BRUNSWICK 1107 | 152481107 | FALSE | 2.4144 | 1.5641 | 1.9362 | 36 | 0.00066912 | 3443 | 0.51651 | 2809 | 0.00031706 | 2475
SAN LUIS OBISPO 1104V10 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 4.8421 | 0.1369 | 2.1043 | 86.3333 | 0.00033112 | 7434 | 0.83427 | 2535 | 0.00031635 | 2476
HOOPA 110182542 | HOOPA 1101 | 192401101 | FALSE | 14.9576 | 1.5247 | 11.8005 | 296.5 | 0.00031183 | 7772 | 0.93212 | 2465 | 0.00031586 | 2477
OREGON TRAIL 11041634 | OREGON TRAIL 1104 | 103521104 | FALSE | 18.272 | 0.63452 | 18.2344 | 307 | 0.00021335 | 9810 | 1.5212 | 1829 | 0.00031579 | 2478
RESEARCH 2102D537R | RESEARCH 2102 | 14692102 |  | 6.203 | 3.4398 |  | 101 | 0.0007241 | 2801 | 0.74407 | 2605 | 0.00031558 | 2479
PENRYN 110351658 | PENRYN 1103 | 152561103 | FALSE | 8.7475 | 0.56607 | 8.4699 | 153.3333 | 0.00028144 | 8390 | 1.0875 | 2315 | 0.00031488 | 2480
DESCHUTES 110449024 | DESCHUTES 1104 | 103351104 | FALSE | 16.7525 | 1.1296 | 17.3633 | 290.5 | 0.00019548 | 10120 | 1.6397 | 1775 | 0.00031475 | 2481
COARSEGOLD 21025722 | COARSEGOLD 2102 | 254432102 | FALSE | 1.9348 | 0.33082 | 2.2656 | 40 | 0.00027345 | 8566 | 1.15 | 2248 | 0.00031447 | 2482
SAN LUIS OBISPO 1107CB | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 1.2095 | 0.12923 | 0.81761 | 23 | 0.00056845 | 4675 | 0.72198 | 2624 | 0.00031412 | 2483
WYANDOTTE 110313018 | WYANDOTTE 1103 | 102911103 | TRUE | 1.6511 | 0.12565 | 0.28216 | 30.5 | 0.00046797 | 5714 | 0.79133 | 2566 | 0.0003134 | 2484
POINT MORETTI 1101415734 | POINT MORETTI 1101 | 82931101 | FALSE | 8.154 | 0.49118 | 5.8874 | 160.5 | 0.00038315 | 6662 | 0.77476 | 2578 | 0.00031335 | 2485
VINEYARD 2107246084 | VINEYARD 2107 | 14502107 | TRUE | 0.55009 | 0 | 0.028959 | 9.5 | 0.00029442 | 8118 | 1.6873 | 1747 | 0.00031309 | 2486
COTATI 1103CB | COTATI 1103 | 42271103 | FALSE | 11.9545 | 0.82187 | 12.7763 | 235.4167 | 0.00025765 | 8931 | 1.2092 | 2122 | 0.00031244 | 2487
ROSSMOOR 1104892332 | ROSSMOOR 1104 | 14161104 | TRUE | 0.24831 | 0.056221 | 0.30453 | 6.3333 | 0.00027151 | 8618 | 1.15 | 2248 | 0.00031223 | 2488
SAN RAFAEL 1106155772 | SAN RAFAEL 1106 | 42011106 | FALSE | 2.6772 | 1.3044 | 1.7558 | 51.5 | 0.00057138 | 4638 | 0.60257 | 2732 | 0.00031217 | 2489
MARTELL 1103CB | MARTELL 1103 | 163011103 | FALSE | 6.2876 | 1.5637 | 1.2434 | 97.3333 | 0.00062855 | 3962 | 0.39387 | 2921 | 0.00031154 | 2490
CLARK ROAD 1102CB | CLARK ROAD 1102 | 103091102 | FALSE | 1.5088 | 0.19149 | 0.73998 | 26 | 0.00055253 | 4842 | 0.46271 | 2857 | 0.00031072 | 2491
DEL MONTE 21049096 | DEL MONTE 2104 | 182222104 | FALSE | 6.6819 | 2.6244 | 3.9136 | 116.5 | 0.00059341 | 4378 | 0.52862 | 2797 | 0.0003107 | 2492
BANGOR 11011958 | BANGOR 1101 | 103191101 | FALSE | 33.6264 | 0.77068 | 34.397 | 588 | 0.00016591 | 10521 | 1.9057 | 1669 | 0.00031053 | 2493
ARCATA 11224218 | ARCATA 1122 | 192021122 | FALSE | 4.8982 | 0.38852 | 5.1576 | 86.5 | 0.00024939 | 9092 | 1.2796 | 2028 | 0.00031048 | 2494
HARRIS 1109355914 | HARRIS 1109 | 192431109 | FALSE | 9.095 | 2.1891 | 9.8985 | 168 | 0.00031584 | 7700 | 0.99993 | 2391 | 0.00031044 | 2495
FORT BRAGG A 1104872358 | FORT BRAGG A 1104 | 42761104 | FALSE | 3.7205 | 0.093818 | 3.8143 | 66.5 | 0.00026981 | 8658 | 1.15 | 2248 | 0.00031028 | 2496
DIAMOND SPRINGS 1107217974 | DIAMOND SPRINGS 1107 | 152261107 | FALSE | 4.2665 | 0.37019 | 4.4672 | 71 | 0.00026424 | 8770 | 1.1848 | 2154 | 0.00030994 | 2497
COTATI 110599720 | COTATI 1105 | 42271105 | FALSE | 6.8292 | 1.3108 | 8.1399 | 114 | 0.00027035 | 8643 | 1.1545 | 2233 | 0.00030967 | 2498
FORT BRAGG A 11044690 | FORT BRAGG A 1104 | 42761104 | FALSE | 13.2022 | 2.8578 | 11.1082 | 245.3333 | 0.00034684 | 7192 | 0.9363 | 2459 | 0.00030904 | 2499
ANDERSON 1101CB | ANDERSON 1101 | 103261101 | FALSE | 7.2099 | 3.6406 | 1.0914 | 106 | 0.00066312 | 3528 | 0.66545 | 2674 | 0.00030882 | 2500
BUELLTON 1101Y06 | BUELLTON 1101 | 183041101 | FALSE | 39.1322 | 1.8543 | 29.0312 | 744.5 | 0.00020376 | 9986 | 1.9831 | 1643 | 0.00030832 | 2501
WILLITS 1104188268 | WILLITS 1104 | 42661104 | FALSE | 5.4118 | 1.7196 | 5.0546 | 92.8333 | 0.0002963 | 8077 | 1.1758 | 2172 | 0.00030801 | 2502
BIG MEADOWS 21012246 | BIG MEADOWS 2101 | 102812101 | FALSE | 1.8083 | 0.562 | 2.3703 | 38.3333 | 0.00026767 | 8705 | 1.15 | 2247 | 0.00030782 | 2503
MORGAN HILL 2104152774 | MORGAN HILL 2104 | 83242104 | FALSE | 7.7035 | 0.66092 | 6.3649 | 148 | 0.00024759 | 9136 | 2.5338 | 1500 | 0.00030771 | 2504
FRANKLIN 1104P146 | FRANKLIN 1104 | 13921104 | FALSE | 3.6399 | 0.18491 | 3.7071 | 67.5 | 0.00028527 | 8303 | 1.0932 | 2310 | 0.00030695 | 2505
SAN LUIS OBISPO 1107834556 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 2.5747 | 0.014284 | 2.589 | 50.5 | 0.00017444 | 10430 | 1.8568 | 1681 | 0.00030693 | 2506
SHINGLE SPRINGS 210819622 | SHINGLE SPRINGS 2108 | 153652108 | FALSE | 11.6415 | 0.94745 | 5.4224 | 186.3333 | 0.00060872 | 4180 | 0.46904 | 2852 | 0.00030673 | 2507
CORNING 110187304 | CORNING 1101 | 103331101 | FALSE | 14.7427 | 0.48262 | 2.3201 | 277 | 0.00027651 | 8506 | 1.0498 | 2344 | 0.00030556 | 2508
CASTRO VALLEY 1108MR233 | CASTRO VALLEY 1108 | 14091108 | TRUE | 0.5963 | 0.33994 | 0.13457 | 10 | 0.00046677 | 5731 | 0.59066 | 2748 | 0.00030485 | 2509
FRUITLAND 1141866852 | FRUITLAND 1141 | 192311141 | FALSE | 3.5757 | 0.20157 | 2.9287 | 71.5 | 0.0002739 | 8551 | 1.0109 | 2378 | 0.00030441 | 2510
SAN LUIS OBISPO 1107V62 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 2.7056 | 0.27483 | 2.7921 | 55.5 | 0.00030332 | 7943 | 1.0638 | 2333 | 0.00030401 | 2511
MIRABEL 1101CB | MIRABEL 1101 | 42091101 | FALSE | 7.3469 | 3.051 | 0.66645 | 133.8333 | 0.00055156 | 4852 | 0.74703 | 2599 | 0.00030356 | 2512
SAN RAFAEL 1109692576 | SAN RAFAEL 1109 | 42011109 | FALSE | 3.4242 | 2.1542 | 3.2442 | 63 | 0.00054963 | 4866 | 0.59034 | 2749 | 0.000303 | 2513
CASTRO VALLEY 1105853216 | CASTRO VALLEY 1105 | 14091105 | FALSE | 2.9358 | 2.7971 | 1.9135 | 41.5 | 0.00044011 | 6011 | 0.70107 | 2643 | 0.00030273 | 2514
SAN CARLOS 110479774 | SAN CARLOS 1104 | 24181104 | FALSE | 1.629 | 1.2089 | 1.3832 | 26.5 | 0.00048139 | 5588 | 0.59774 | 2737 | 0.00030266 | 2515
COTATI 1102CB | COTATI 1102 | 42271102 | FALSE | 1.9935 | 0.043119 | 1.7207 | 40.25 | 0.00034711 | 7187 | 1.0075 | 2382 | 0.00030258 | 2516
PANORAMA 11021632 | PANORAMA 1102 | 103461102 | FALSE | 8.4702 | 0.31071 | 8.7809 | 144.5 | 8.4758e-05 | 11096 | 2.9705 | 1397 | 0.00030236 | 2517
AUBERRY 1102R309 | AUBERRY 1102 | 254151102 | FALSE | 8.5535 | 0.29926 | 8.8527 | 149 | 0.00012003 | 10950 | 2.7622 | 1445 | 0.00030234 | 2518
MIRABEL 1102524356 | MIRABEL 1102 | 42091102 | FALSE | 2.5511 | 0.13944 | 1.2529 | 48.5 | 0.00036592 | 6905 | 0.66991 | 2670 | 0.00030226 | 2519
MOLINO 1101600112 | MOLINO 1101 | 42571101 | FALSE | 1.2578 | 0.39264 | 0.93833 | 20.5 | 0.00045906 | 5812 | 0.65166 | 2682 | 0.00030181 | 2520
STONE CORRAL 1110189488 | STONE CORRAL 1110 | 252921110 | FALSE | 0.84289 | 0.035639 | 0.77328 | 20 | 0.00017823 | 10374 | 1.638 | 1776 | 0.00030174 | 2521
HOOPA 1101CB | HOOPA 1101 | 192401101 | FALSE | 39.2392 | 7.9523 | 24.2787 | 726.5 | 0.00037921 | 6709 | 0.69722 | 2649 | 0.00030124 | 2522
MORGAN HILL 2105XR494 | MORGAN HILL 2105 | 83242105 | TRUE | 7.2712 | 2.6311 | 0.31259 | 142.5 | 0.00040858 | 6349 | 0.78798 | 2570 | 0.00030038 | 2523
WISE 11022054 | WISE 1102 | 152271102 | FALSE | 12.8746 | 1.2443 | 14.1189 | 235 | 0.0002229 | 9648 | 1.3728 | 1950 | 0.00029919 | 2524
HOPLAND 11011100 | HOPLAND 1101 | 42251101 | FALSE | 6.7821 | 0.57305 | 3.6317 | 144.5 | 0.00020921 | 9886 | 1.5183 | 1831 | 0.00029858 | 2525
RED BLUFF 11041566 | RED BLUFF 1104 | 103541104 | FALSE | 16.3531 | 0.29329 | 11.3714 | 305.5 | 0.0001664 | 10517 | 1.7764 | 1708 | 0.00029835 | 2526
ELK 11011260 | ELK 1101 | 42981101 | FALSE | 15.6601 | 0.53411 | 16.0665 | 315.3333 | 0.00025782 | 8928 | 1.1629 | 2215 | 0.00029813 | 2527
NOVATO 1104676060 | NOVATO 1104 | 42211104 | TRUE | 0.89467 | 0.076108 | 0.4512 | 18.5 | 0.00040876 | 6347 | 0.71524 | 2630 | 0.00029758 | 2528
BELL 11072400 | BELL 1107 | 152701107 | FALSE | 27.7091 | 3.2335 | 27.7646 | 509.5 | 0.00023071 | 9469 | 1.2598 | 2046 | 0.00029744 | 2529
PARADISE 1104CB | PARADISE 1104 | 102831104 | FALSE | 3.712 | 1.0973 | 1.563 | 64.7 | 0.00065123 | 3695 | 0.52797 | 2798 | 0.00029731 | 2530
VIEJO 2203947314 | VIEJO 2203 | 182852203 | TRUE | 1.4413 | 1.0547 | 0.30327 | 19.5 | 0.00082776 | 1754 | 0.42612 | 2888 | 0.00029695 | 2531
BIG RIVER 11013002 | BIG RIVER 1101 | 43081101 | FALSE | 8.3015 | 0.67277 | 7.5655 | 148.5 | 0.00032362 | 7562 | 0.92557 | 2468 | 0.0002968 | 2532
CARLOTTA 11214914 | CARLOTTA 1121 | 192291121 | FALSE | 14.0004 | 3.617 | 11.7258 | 274 | 0.0003122 | 7764 | 0.89892 | 2487 | 0.00029654 | 2533
BANGOR 110131502 | BANGOR 1101 | 103191101 | FALSE | 11.6695 | 0.38454 | 12.054 | 219 | 0.00016364 | 10553 | 1.813 | 1697 | 0.00029638 | 2534
FROGTOWN 1702739858 | FROGTOWN 1702 | 163451702 | FALSE | 4.8557 | 0.12207 | 4.8797 | 90 | 0.00023704 | 9339 | 1.2495 | 2058 | 0.00029594 | 2535
DESCHUTES 1104116082 | DESCHUTES 1104 | 103351104 | FALSE | 3.8913 | 0.28411 | 2.782 | 76.5 | 0.00025855 | 8915 | 1.2263 | 2088 | 0.00029531 | 2536
GEYSERVILLE 1101166 | GEYSERVILLE 1101 | 42891101 | FALSE | 15.686 | 0.84918 | 11.3487 | 302.5 | 0.00026841 | 8691 | 1.2077 | 2125 | 0.00029514 | 2537
KONOCTI 1102410004 | KONOCTI 1102 | 43311102 | FALSE | 3.5957 | 0.86263 | 4.1442 | 58.5 | 0.00029739 | 8061 | 1.7331 | 1730 | 0.00029472 | 2538
PUTAH CREEK 11033783 | PUTAH CREEK 1103 | 63681103 |  | 10.9746 | 1.0487 |  | 211.5 | 0.00019127 | 10193 | 2.2706 | 1563 | 0.0002947 | 2539
OREGON TRAIL 11041574 | OREGON TRAIL 1104 | 103521104 | FALSE | 18.61 | 2.2407 | 18.0606 | 320.5 | 0.00027581 | 8516 | 1.1083 | 2292 | 0.00029453 | 2540
NEWBURG 1132665674 | NEWBURG 1132 | 192151132 | TRUE | 1.5346 | 0.16547 | 0.43693 | 28.5 | 0.00032771 | 7487 | 0.70602 | 2637 | 0.00029433 | 2541
GEYSERVILLE 1102522 | GEYSERVILLE 1102 | 42891102 | FALSE | 10.998 | 0.80106 | 7.9169 | 213.5 | 0.00021453 | 9784 | 1.4834 | 1862 | 0.00029428 | 2542
OLEMA 1101758594 | OLEMA 1101 | 42291101 | FALSE | 2.0589 | 0.53065 | 1.46 | 43.5 | 0.00043824 | 6031 | 0.66452 | 2675 | 0.00029407 | 2543
CLAY 110334338 | CLAY 1103 | 163341103 | FALSE | 10.2453 | 0.12132 | 8.7554 | 196.5 | 0.00013211 | 10866 | 3.4373 | 1324 | 0.00029314 | 2544
VALLEY VIEW 1106P176 | VALLEY VIEW 1106 | 14341106 | TRUE | 4.1907 | 4.098 | 0.39014 | 75 | 0.0005008 | 5385 | 0.6623 | 2678 | 0.00029259 | 2545
WILLITS 1102350324 | WILLITS 1102 | 42661102 | FALSE | 5.3962 | 3.091 | 5.0426 | 93.8333 | 0.00036261 | 6954 | 0.88714 | 2494 | 0.00029229 | 2546
PERRY 1101W10 | PERRY 1101 | 183071101 | FALSE | 1.8117 | 1.2891 | 2.1216 | 41 | 0.00031359 | 7743 | 0.88663 | 2495 | 0.00029189 | 2547
RISING RIVER 1101CB | RISING RIVER 1101 | 103551101 | FALSE | 12.9375 | 1.5792 | 9.9305 | 246.5 | 0.00018541 | 10269 | 1.5347 | 1818 | 0.00029168 | 2548
SAN LUIS OBISPO 1105796050 | SAN LUIS OBISPO 1105 | 182631105 | TRUE | 4.0178 | 3.6553 | 0.28875 | 66.3333 | 0.00059378 | 4371 | 0.60731 | 2724 | 0.00029096 | 2549
BELL 110750172 | BELL 1107 | 152701107 | FALSE | 18.8284 | 2.2967 | 18.8405 | 347 | 0.00018683 | 10246 | 2.0878 | 1609 | 0.00029091 | 2550
COTATI 1105103816 | COTATI 1105 | 42271105 | FALSE | 2.0232 | 0.27832 | 2.3015 | 35.8333 | 0.00024957 | 9091 | 1.1541 | 2236 | 0.00029022 | 2551
POSO MOUNTAIN 21012181 | POSO MOUNTAIN 2101 | 253642101 | FALSE | 23.7029 | 0.14959 | 16.7766 | 411.5 | 0.00020661 | 9938 | 1.0097 | 2380 | 0.00028999 | 2552
MONTE RIO 1111292 | MONTE RIO 1111 | 42811111 | FALSE | 19.5154 | 2.0826 | 14.394 | 388 | 0.00020721 | 9925 | 1.4793 | 1863 | 0.00028981 | 2553
HALF MOON BAY 110369412 | HALF MOON BAY 1103 | 24101103 | FALSE | 21.0649 | 1.216 | 14.6191 | 429 | 0.00036256 | 6956 | 0.80555 | 2551 | 0.0002898 | 2554
SAN LEANDRO U 1114523960 | SAN LEANDRO U 1114 | 13111114 | FALSE | 2.9363 | 3.0096 | 3.1847 | 48 | 0.00060325 | 4262 | 0.58249 | 2755 | 0.00028924 | 2555
HORSESHOE 110150140 | HORSESHOE 1101 | 152571101 | FALSE | 6.2749 | 0.41143 | 3.829 | 109.3333 | 0.00038912 | 6584 | 0.77854 | 2577 | 0.00028839 | 2556
FORT ORD 210637286 | FORT ORD 2106 | 182402106 | FALSE | 3.6556 | 0 | 1.9888 | 56.25 | 0.00043637 | 6051 | 0.69989 | 2644 | 0.00028822 | 2557
VIEJO 22029112 | VIEJO 2202 | 182852202 | FALSE | 3.3117 | 2.2142 | 0.88288 | 53.6667 | 0.00071003 | 2975 | 0.44324 | 2875 | 0.00028806 | 2558
BROWNS VALLEY 1101CB | BROWNS VALLEY 1101 | 152921101 | FALSE | 2.939 | 0.034449 | 2.0294 | 50 | 0.00032141 | 7598 | 0.8521 | 2521 | 0.00028805 | 2559
TEMPLETON 2113A20 | TEMPLETON 2113 | 183052113 | FALSE | 8.0092 | 0.41545 | 7.5489 | 161.8333 | 0.0002793 | 8439 | 1.555 | 1805 | 0.00028757 | 2560
FORT ROSS 1121560 | FORT ROSS 1121 | 42851121 | FALSE | 5.6307 | 0.12713 | 4.3622 | 119 | 0.00026153 | 8852 | 0.9794 | 2418 | 0.00028732 | 2561
OLETA 1102793776 | OLETA 1102 | 163541102 | FALSE | 1.1816 | 0 | 1.1816 | 20.3333 | 0.00021549 | 9768 | 1.3125 | 1997 | 0.00028716 | 2562
SILVERADO 2102CB | SILVERADO 2102 | 43432102 | TRUE | 1.6984 | 0.17837 | 0.51784 | 35.5 | 0.0010452 | 635 | 0.30297 | 3019 | 0.00028671 | 2563
FRANKLIN 1104P136 | FRANKLIN 1104 | 13921104 | FALSE | 5.4759 | 0.55859 | 4.1235 | 85.5 | 0.00040811 | 6356 | 0.88521 | 2497 | 0.00028656 | 2564
BELMONT 1110522372 | BELMONT 1110 | 24031110 |  | 1.2431 | 0.68102 |  | 23 | 0.00040475 | 6403 | 0.72591 | 2621 | 0.0002864 | 2565
TEMPLETON 2110307832 | TEMPLETON 2110 | 183052110 | FALSE | 14.1963 | 0.35487 | 1.2128 | 269.5 | 0.00015409 | 10656 | 3.6392 | 1291 | 0.00028633 | 2566
HAMILTON BRANCH 110190334 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 3.4297 | 0.5184 | 3.9481 | 61 | 0.00024836 | 9118 | 1.1617 | 2217 | 0.000286 | 2567
SAUSALITO 1102410 | SAUSALITO 1102 | 42491102 | FALSE | 2.2584 | 1.4376 | 2.0445 | 34.5 | 0.00051179 | 5267 | 0.63524 | 2700 | 0.0002854 | 2568
OILFIELDS 110241992 | OILFIELDS 1102 | 182391102 |  | 18.7555 | 0.37868 |  | 382 | 9.7899e-05 | 11060 | 5.8869 | 1079 | 0.000285 | 2569
ARCATA 1121716954 | ARCATA 1121 | 192021121 | TRUE | 11.4134 | 1.1726 | 0.16716 | 219.5 | 0.00042909 | 6127 | 0.72589 | 2622 | 0.00028479 | 2570
FAIRVIEW 2207P142 | FAIRVIEW 2207 | 13432207 | FALSE | 3.0844 | 3.4876 | 1.4536 | 45.1667 | 0.00052069 | 5171 | 0.61531 | 2718 | 0.00028461 | 2571
CAMBRIA 1101858200 | CAMBRIA 1101 | 182771101 | FALSE | 6.1654 | 0.10483 | 5.9952 | 116 | 0.00022497 | 9609 | 1.2829 | 2025 | 0.00028456 | 2572
PETALUMA C 1108296 | PETALUMA C 1108 | 42631108 | FALSE | 14.6339 | 1.1554 | 15.7893 | 284.5 | 0.00020515 | 9962 | 1.408 | 1920 | 0.00028395 | 2573
POINT ARENA 110147952 | POINT ARENA 1101 | 43381101 | FALSE | 10.3278 | 0.17431 | 10.5021 | 191.5 | 0.00024605 | 9163 | 1.1526 | 2237 | 0.00028367 | 2574
BURNEY 1101CB | BURNEY 1101 | 103311101 | FALSE | 1.985 | 1.2957 | 2.0001 | 34.6667 | 0.00042449 | 6179 | 0.62412 | 2710 | 0.00028364 | 2575
HIGGINS 110950078 | HIGGINS 1109 | 152691109 | FALSE | 48.9307 | 1.2901 | 50.2207 | 912 | 9.0795e-05 | 11081 | 3.1993 | 1356 | 0.00028325 | 2576
BELLEVUE 2103552 | BELLEVUE 2103 | 43182103 | FALSE | 14.8765 | 0.98596 | 7.8638 | 269.5 | 0.00036175 | 6961 | 0.80213 | 2557 | 0.00028291 | 2577
MARTELL 1101CB | MARTELL 1101 | 163011101 | FALSE | 7.9078 | 2.3467 | 1.1634 | 128.3333 | 0.00070463 | 3048 | 0.50728 | 2816 | 0.0002828 | 2578
SAN LUIS OBISPO 1102357407 | SAN LUIS OBISPO 1102 | 182631102 | TRUE | 0.24152 | 0 | 0.19017 | 4.5 | 0.00024528 | 9182 | 1.15 | 2248 | 0.00028207 | 2579
BIG RIVER 11011286 | BIG RIVER 1101 | 43081101 | FALSE | 7.6444 | 0.71553 | 4.5175 | 143 | 0.00039298 | 6534 | 0.69938 | 2646 | 0.0002818 | 2580
COTATI 1103148 | COTATI 1103 | 42271103 | FALSE | 15.4443 | 0.78399 | 15.5305 | 296.5 | 0.0002092 | 9887 | 1.3136 | 1994 | 0.00028154 | 2581
OCEANO 1104891294 | OCEANO 1104 | 182601104 | FALSE | 12.5081 | 1.8112 | 14.3193 | 235 | 0.00023246 | 9436 | 1.2403 | 2072 | 0.00028139 | 2582
LUCERNE 1106709252 | LUCERNE 1106 | 43351106 | FALSE | 1.2862 | 0.5449 | 1.3456 | 17.5 | 0.00037792 | 6729 | 0.93222 | 2464 | 0.00027992 | 2583
PANOCHE 1103107270 | PANOCHE 1103 | 253671103 | FALSE | 12.5928 | 0.31173 | 2.0119 | 217 | 0.00013079 | 10878 | 2.5647 | 1494 | 0.0002798 | 2584
PHILO 11021308 | PHILO 1102 | 42601102 | FALSE | 32.3249 | 1.0714 | 33.3962 | 619 | 0.00024213 | 9244 | 1.1516 | 2242 | 0.00027861 | 2585
MOLINO 110251788 | MOLINO 1102 | 42571102 | FALSE | 13.1422 | 1.6747 | 5.4984 | 237.5 | 0.00041532 | 6278 | 0.57348 | 2764 | 0.0002779 | 2586
RINCON 1104CB | RINCON 1104 | 43321104 |  | 1.8969 | 0.50655 |  | 31.8333 | 0.00088602 | 1330 | 0.45164 | 2867 | 0.00027747 | 2587
CORRAL 1102CB | CORRAL 1102 | 162991102 | FALSE | 21.397 | 1.4112 | 17.2359 | 400.8333 | 0.00022853 | 9524 | 1.0742 | 2329 | 0.00027725 | 2588
LAS GALLINAS A 1106685656 | LAS GALLINAS A 1106 | 42991106 | FALSE | 3.6353 | 4.7589 | 1.2012 | 64.8333 | 0.00055621 | 4801 | 0.5241 | 2804 | 0.000277 | 2589
PACIFICA 110266732 | PACIFICA 1102 | 22811102 | TRUE | 2.0349 | 1.7155 | 0.23439 | 38.5 | 0.00070965 | 2980 | 0.36111 | 2953 | 0.00027589 | 2590
COTATI 1102462 | COTATI 1102 | 42271102 | FALSE | 3.9162 | 0.34753 | 2.9677 | 79 | 0.0003398 | 7309 | 0.85939 | 2516 | 0.00027587 | 2591
PEORIA 170459596 | PEORIA 1704 | 163781704 | FALSE | 35.9939 | 3.5852 | 20.0369 | 682.5 | 0.00017332 | 10439 | 2.1283 | 1596 | 0.00027547 | 2592
PEORIA 170488630 | PEORIA 1704 | 163781704 | FALSE | 0.74281 | 0 | 0.74281 | 14.5 | 0.00023144 | 9450 | 1.175 | 2175 | 0.00027545 | 2593
OAKLAND J 1102CR254 | OAKLAND J 1102 | 12091102 | FALSE | 1.516 | 2.1564 | 2.2548 | 27 | 0.00051275 | 5258 | 0.62337 | 2711 | 0.00027513 | 2594
OAKLAND J 1105CR256 | OAKLAND J 1105 | 12091105 | FALSE | 1.845 | 2.0272 | 2.3657 | 33.8333 | 0.00055839 | 4773 | 0.59502 | 2742 | 0.00027483 | 2595
PIT NO 3 21011360 | PIT NO 3 2101 | 103732101 | FALSE | 22.4773 | 0.27359 | 22.3644 | 434.5 | 0.00019845 | 10069 | 1.4779 | 1864 | 0.00027478 | 2596
RIO DELL 110275970 | RIO DELL 1102 | 192251102 | FALSE | 7.117 | 0.050242 | 7.1672 | 139 | 0.00020863 | 9902 | 1.3419 | 1974 | 0.00027463 | 2597
HAMILTON BRANCH 11012046 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 9.2891 | 1.368 | 10.0366 | 177 | 0.00021804 | 9730 | 1.2982 | 2004 | 0.00027403 | 2598
BAY MEADOWS 210257886 | BAY MEADOWS 2102 | 24012102 | FALSE | 5.2648 | 2.5238 | 5.8362 | 103.6667 | 0.0004923 | 5469 | 0.59549 | 2740 | 0.00027364 | 2599
SONOMA 1103581588 | SONOMA 1103 | 42721103 | TRUE | 0.94431 | 0.18441 | 0.1348 | 18.5 | 0.0003111 | 7785 | 1.2122 | 2113 | 0.00027347 | 2600
GARBERVILLE 11024744 | GARBERVILLE 1102 | 192221102 | FALSE | 15.9844 | 1.8995 | 10.7866 | 312.5 | 0.00028129 | 8394 | 0.95044 | 2448 | 0.0002733 | 2601
PLACERVILLE 1110CB | PLACERVILLE 1110 | 153081110 | FALSE | 1.7871 | 1.0553 | 1.0635 | 27.3333 | 0.00095378 | 994 | 0.39776 | 2914 | 0.00027186 | 2602
LOS GATOS 1101502026 | LOS GATOS 1101 | 82021101 | TRUE | 1.0751 | 0.82063 | 0.096812 | 16 | 0.00061205 | 4146 | 0.4599 | 2863 | 0.00027174 | 2603
SAN LUIS OBISPO 1104V40 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 23.0924 | 0.74248 | 13.8451 | 398.5 | 0.00017357 | 10437 | 1.7301 | 1731 | 0.00027105 | 2604
FOOTHILL 1101251688 | FOOTHILL 1101 | 182951101 | FALSE | 7.8459 | 0.30554 | 7.021 | 148.5 | 0.00012675 | 10913 | 2.9398 | 1403 | 0.00027092 | 2605
OTTER 11022012 | OTTER 1102 | 182941102 | FALSE | 9.9037 | 0.22354 | 9.0803 | 198.5 | 0.00021255 | 9833 | 1.5412 | 1815 | 0.00027051 | 2606
BUELLTON 1102Y50 | BUELLTON 1102 | 183041102 | FALSE | 12.6071 | 1.4867 | 10.7413 | 225.8333 | 0.00031118 | 7783 | 0.99486 | 2400 | 0.00026962 | 2607
WYANDOTTE 110913052 | WYANDOTTE 1109 | 102911109 | FALSE | 19.5007 | 1.0953 | 20.4884 | 376.5 | 0.00017713 | 10395 | 1.746 | 1722 | 0.00026895 | 2608
PETALUMA C 1109738866 | PETALUMA C 1109 | 42631109 | FALSE | 2.5868 | 0.55712 | 2.0209 | 47 | 0.00030041 | 8010 | 1.1706 | 2192 | 0.00026883 | 2609
WILLOW CREEK 110191926 | WILLOW CREEK 1101 | 192171101 | FALSE | 10.512 | 0.50769 | 5.053 | 207.5 | 0.00043702 | 6043 | 0.54195 | 2788 | 0.00026835 | 2610
VIEJO 22019704 | VIEJO 2201 | 182852201 | TRUE | 2.5512 | 2.1794 | 0.37167 | 40.3333 | 0.00076649 | 2303 | 0.44641 | 2868 | 0.00026777 | 2611
IGNACIO 1104450582 | IGNACIO 1104 | 42481104 | FALSE | 4.2107 | 1.1261 | 3.7906 | 80 | 0.00033606 | 7364 | 0.93444 | 2460 | 0.00026699 | 2612
MENLO 11029110 | MENLO 1102 | 24131102 | FALSE | 8.819 | 2.4498 | 0.86935 | 169.8333 | 0.00058648 | 4460 | 0.48022 | 2842 | 0.00026698 | 2613
OLETA 1101239062 | OLETA 1101 | 163541101 | FALSE | 14.0215 | 0.35336 | 11.7829 | 264.5 | 0.00016581 | 10523 | 1.8453 | 1687 | 0.00026683 | 2614
PENRYN 1107346 | PENRYN 1107 | 152561107 | FALSE | 24.9861 | 2.4826 | 13.8714 | 428 | 0.00036978 | 6843 | 0.74646 | 2602 | 0.00026631 | 2615
BELL 1108467470 | BELL 1108 | 152701108 | FALSE | 3.0264 | 0.78525 | 2.536 | 55.5 | 0.00038791 | 6607 | 0.82402 | 2542 | 0.00026543 | 2616
LOYOLA 1102CB | LOYOLA 1102 | 82161102 |  | 14.2944 | 6.5162 |  | 269.95 | 0.00065472 | 3644 | 0.35909 | 2956 | 0.00026458 | 2617
SAN RAMON 2102CB | SAN RAMON 2102 | 14232102 | FALSE | 2.1197 | 0 | 1.524 | 29.1667 | 0.0004704 | 5696 | 0.84768 | 2525 | 0.00026381 | 2618
CASTRO VALLEY 1111MR334 | CASTRO VALLEY 1111 | 14091111 | FALSE | 5.9978 | 1.5385 | 6.7663 | 115.8333 | 0.00031944 | 7640 | 0.93295 | 2463 | 0.00026356 | 2619
AUBERRY 1102R2850 | AUBERRY 1102 | 254151102 | FALSE | 25.9343 | 0.94316 | 26.8774 | 485.5 | 0.00010175 | 11044 | 3.0742 | 1376 | 0.00026347 | 2620
PERRY 1101W12 | PERRY 1101 | 183071101 | FALSE | 6.3057 | 3.8717 | 5.8983 | 71.5 | 0.00051762 | 5198 | 0.45405 | 2865 | 0.00026271 | 2621
LAURELES 1112438 | LAURELES 1112 | 182371112 | FALSE | 5.6378 | 1.0729 | 5.5147 | 109.5 | 0.00022873 | 9518 | 1.6136 | 1782 | 0.0002624 | 2622
VIEJO 22029118 | VIEJO 2202 | 182852202 | FALSE | 2.9866 | 1.4733 | 1.1123 | 53.5 | 0.00059396 | 4370 | 0.41067 | 2901 | 0.00026204 | 2623
STONE CORRAL 1108255186 | STONE CORRAL 1108 | 252921108 | FALSE | 13.416 | 1.0039 | 2.1564 | 256.5 | 0.00016593 | 10520 | 2.0014 | 1631 | 0.00026129 | 2624
PHILO 1102CB | PHILO 1102 | 42601102 | FALSE | 12.4533 | 1.1362 | 6.5918 | 238.5 | 0.0003495 | 7148 | 0.66986 | 2671 | 0.00026077 | 2625
WYANDOTTE 1105329930 | WYANDOTTE 1105 | 102911105 | FALSE | 12.2603 | 3.1375 | 7.0643 | 192.6667 | 0.00046011 | 5806 | 0.70548 | 2638 | 0.0002604 | 2626
PEABODY 2106CB | PEABODY 2106 | 63642106 | TRUE | 1.0773 | 0 | 0.10832 | 22.2 | 0.00056313 | 4726 | 1.1505 | 2246 | 0.00025949 | 2627
UKIAH 1114528 | UKIAH 1114 | 42771114 | FALSE | 12.4874 | 0.74053 | 3.0388 | 248 | 0.00028376 | 8335 | 1.9287 | 1659 | 0.00025927 | 2628
OLD RIVER 1001CB | OLD RIVER 1001 | 252821001 |  | 0.0041889 | 0 |  | 0.25 | 0.0033459 | 11 | 0.0774 | 3397 | 0.00025897 | 2629
SAN RAMON 2101CB | SAN RAMON 2101 | 14232101 | TRUE | 0.99271 | 0 | 0.60799 | 8.6667 | 0.00071726 | 2888 | 0.59594 | 2739 | 0.00025854 | 2630
IONE 1101L3141 | IONE 1101 | 163881101 | FALSE | 13.9986 | 0.27083 | 13.7205 | 252.5 | 0.00014994 | 10708 | 1.9981 | 1635 | 0.00025838 | 2631
LINCOLN 1101210168 | LINCOLN 1101 | 153701101 | FALSE | 7.4025 | 0.29833 | 4.2256 | 134.5 | 0.00022865 | 9522 | 1.1968 | 2136 | 0.00025817 | 2632
EL CERRITO G 1105BR160 | EL CERRITO G 1105 | 12501105 | FALSE | 11.4361 | 7.1941 | 12.0439 | 197.1667 | 0.0005018 | 5374 | 0.58318 | 2753 | 0.00025777 | 2633
CHESTER 1101922138 | CHESTER 1101 | 103181101 | FALSE | 2.3005 | 1.2013 | 2.2241 | 48.5 | 0.00028315 | 8351 | 0.87152 | 2507 | 0.00025742 | 2634
FROGTOWN 170236870 | FROGTOWN 1702 | 163451702 | TRUE | 2.9076 | 0.84581 | 0.40061 | 46.5 | 0.00040646 | 6377 | 0.70144 | 2641 | 0.00025674 | 2635
PACIFICA 1101CB | PACIFICA 1101 | 22811101 | TRUE | 2.7032 | 1.1878 | 0.13305 | 49 | 0.00069386 | 3171 | 0.73355 | 2616 | 0.00025656 | 2636
MARTELL 1101766574 | MARTELL 1101 | 163011101 | FALSE | 2.4534 | 0.16759 | 1.2858 | 42.5 | 0.00037543 | 6756 | 0.70846 | 2634 | 0.00025604 | 2637
MILPITAS 1109XR044 | MILPITAS 1109 | 82831109 | TRUE | 1.8653 | 0.18781 | 0.27146 | 35.5 | 0.00041419 | 6293 | 0.50433 | 2818 | 0.00025581 | 2638
COTATI 110379140 | COTATI 1103 | 42271103 | FALSE | 12.3237 | 2.0392 | 11.1038 | 219 | 0.00026403 | 8779 | 0.97966 | 2417 | 0.00025456 | 2639
BOLINAS 11011232 | BOLINAS 1101 | 42261101 | FALSE | 2.4925 | 0.086237 | 2.3087 | 47.5 | 0.00017767 | 10387 | 1.5011 | 1844 | 0.00025401 | 2640
DESCHUTES 1104715242 | DESCHUTES 1104 | 103351104 | FALSE | 1.5486 | 0.01773 | 1.3905 | 22.5 | 0.00017702 | 10396 | 1.4978 | 1848 | 0.00025394 | 2641
WYANDOTTE 110942650 | WYANDOTTE 1109 | 102911109 | FALSE | 2.6859 | 0.71304 | 0.7172 | 48 | 0.00052265 | 5153 | 0.428 | 2887 | 0.00025373 | 2642
COTATI 1103132 | COTATI 1103 | 42271103 | FALSE | 25.3128 | 0.87381 | 26.1865 | 462 | 0.00020893 | 9894 | 1.2088 | 2123 | 0.00025363 | 2643
BRUNSWICK 110378862 | BRUNSWICK 1103 | 152481103 | TRUE | 1.1392 | 0.88689 | 0.02272 | 15.5 | 0.00099154 | 822 | 0.27616 | 3044 | 0.00025358 | 2644
PETALUMA C 1109128 | PETALUMA C 1109 | 42631109 | FALSE | 30.3414 | 0.76591 | 27.7157 | 590.3333 | 0.00017692 | 10397 | 1.4915 | 1854 | 0.00025333 | 2645
DEL MAR 2109CB | DEL MAR 2109 | 152582109 | FALSE | 6.7149 | 0.52297 | 1.306 | 108.8333 | 0.00062201 | 4023 | 0.42358 | 2891 | 0.00025332 | 2646
VINEYARD 2107978364 | VINEYARD 2107 | 14502107 | FALSE | 2.522 | 1.39 | 1.3526 | 45 | 0.00045965 | 5810 | 0.59751 | 2738 | 0.00025328 | 2647
FULTON 110746958 | FULTON 1107 | 42561107 |  | 0.52059 | 0 |  | 8.3333 | 0.00086996 | 1422 | 0.31941 | 2991 | 0.00025308 | 2648
PACIFIC GROVE 04222614 | PACIFIC GROVE 0422 | 182440422 | TRUE | 2.1439 | 1.1024 | 0.15009 | 26.1667 | 0.00068624 | 3261 | 0.31338 | 3002 | 0.00025284 | 2649
WISE 1101CB | WISE 1101 | 152271101 | FALSE | 9.1419 | 1.514 | 4.4293 | 155.3333 | 0.0004817 | 5587 | 0.60721 | 2725 | 0.00025255 | 2650
PETALUMA C 1108636 | PETALUMA C 1108 | 42631108 | FALSE | 9.2803 | 1.3315 | 10.6118 | 178.8333 | 0.00020409 | 9974 | 1.2242 | 2093 | 0.00025233 | 2651
CABRILLO 1104597930 | CABRILLO 1104 | 183101104 | FALSE | 13.6376 | 4.2229 | 4.0822 | 242.5 | 0.00039085 | 6558 | 0.74032 | 2611 | 0.00025186 | 2652
HALF MOON BAY 1101CB | HALF MOON BAY 1101 | 24101101 | FALSE | 6.434 | 0.8368 | 1.1763 | 95 | 0.00064299 | 3789 | 0.56243 | 2769 | 0.00025168 | 2653
MC KEE 1103333750 | MC KEE 1103 | 83531103 | TRUE | 1.376 | 0.094184 | 0.61082 | 24.5 | 0.00032334 | 7571 | 0.63034 | 2703 | 0.00025151 | 2654
SAN MIGUEL 1104954082 | SAN MIGUEL 1104 | 182661104 | FALSE | 8.6122 | 0.12302 | 7.4999 | 153.8333 | 0.00010171 | 11045 | 2.9235 | 1408 | 0.00025145 | 2655
ALHAMBRA 1102CB | ALHAMBRA 1102 | 14101102 | TRUE | 5.7302 | 5.4335 | 0.25524 | 80.3333 | 0.00076743 | 2292 | 0.2778 | 3042 | 0.00025131 | 2656
GARBERVILLE 1102176634 | GARBERVILLE 1102 | 192221102 | FALSE | 4.2648 | 0.023489 | 4.2883 | 82.5 | 0.00018662 | 10253 | 1.2961 | 2006 | 0.00025116 | 2657
WINDSOR 11035060 | WINDSOR 1103 | 43501103 | TRUE | 0.67671 | 0.042703 | 0.16332 | 12 | 0.00057133 | 4640 | 0.38316 | 2937 | 0.00025043 | 2658
OILFIELDS 1103370932 | OILFIELDS 1103 | 182391103 | TRUE | 1.6573 | 0 | 0.31302 | 28.5 | 9.5968e-05 | 11064 | 4.0704 | 1249 | 0.00025011 | 2659
SAN BENITO 210488772 | SAN BENITO 2104 | 182742104 | FALSE | 42.4877 | 7.6596 | 26.1049 | 791 | 0.00038891 | 6589 | 0.68102 | 2659 | 0.00024849 | 2660
SAN LUIS OBISPO 110342344 | SAN LUIS OBISPO 1103 | 182631103 | FALSE | 10.8724 | 0.60182 | 9.2288 | 181 | 0.00022872 | 9519 | 1.1794 | 2165 | 0.00024779 | 2661
POINT MORETTI 1101CB | POINT MORETTI 1101 | 82931101 | TRUE | 0.012784 | 0 | 0.012784 | 0.5 | 0.00020263 | 10000 | 1.2226 | 2099 | 0.00024774 | 2662
MARTELL 1101915018 | MARTELL 1101 | 163011101 | FALSE | 0.62937 | 0.04119 | 0.65028 | 13 | 0.00027758 | 8477 | 1.0118 | 2376 | 0.0002475 | 2663
FROGTOWN 1701L3361 | FROGTOWN 1701 | 163451701 | FALSE | 1.8419 | 0.18774 | 2.0297 | 35 | 0.00015472 | 10650 | 1.6106 | 1783 | 0.00024679 | 2664
PANORAMA 1102280170 | PANORAMA 1102 | 103461102 | FALSE | 15.4213 | 0.35111 | 10.4037 | 300 | 0.00023204 | 9443 | 1.3062 | 2000 | 0.00024667 | 2665
PENRYN 110551676 | PENRYN 1105 | 152561105 | FALSE | 11.9011 | 2.1731 | 8.8043 | 217.5 | 0.0004068 | 6372 | 0.72107 | 2625 | 0.00024656 | 2666
HALF MOON BAY 1103H82 | HALF MOON BAY 1103 | 24101103 | FALSE | 13.3397 | 0.93686 | 7.896 | 259.5 | 0.0003736 | 6786 | 0.89967 | 2485 | 0.00024622 | 2667
PENRYN 11051342 | PENRYN 1105 | 152561105 | FALSE | 38.7271 | 4.164 | 21.398 | 719.5 | 0.00027146 | 8620 | 0.82506 | 2541 | 0.00024502 | 2668
MIDDLETOWN 1102514 | MIDDLETOWN 1102 | 43141102 | FALSE | 5.3043 | 3.23 | 4.8807 | 104.5 | 0.00035697 | 7023 | 0.67186 | 2668 | 0.00024469 | 2669
DOLAN ROAD 1101857972 | DOLAN ROAD 1101 | 182381101 | FALSE | 1.2568 | 0.14628 | 0.93404 | 26 | 0.00027451 | 8542 | 0.84472 | 2528 | 0.00024421 | 2670
SAN LUIS OBISPO 1104V14 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 7.9198 | 1.7833 | 9.5977 | 141.8333 | 0.00030215 | 7964 | 1.0297 | 2363 | 0.00024391 | 2671
BROWNS VALLEY 11011268 | BROWNS VALLEY 1101 | 152921101 | FALSE | 10.9311 | 0.12399 | 11.0044 | 198.5 | 0.00018373 | 10295 | 1.3844 | 1941 | 0.00024384 | 2672
VINEYARD 2107CB | VINEYARD 2107 | 14502107 | FALSE | 7.7063 | 1.5426 | 2.1953 | 141 | 0.0005028 | 5361 | 0.61289 | 2720 | 0.00024281 | 2673
MAPLE CREEK 11016906 | MAPLE CREEK 1101 | 192101101 |  | 18.172 | 0.31457 |  | 336 | 0.00018093 | 10341 | 1.3809 | 1944 | 0.00024243 | 2674
GIRVAN 110280726 | GIRVAN 1102 | 103401102 | FALSE | 18.3812 | 2.7054 | 7.4333 | 304.5 | 0.00042612 | 6159 | 0.6076 | 2723 | 0.00024156 | 2675
ELK 11011298 | ELK 1101 | 42981101 | FALSE | 16.4182 | 0.90142 | 9.1208 | 308.5 | 0.00024114 | 9266 | 1.0997 | 2302 | 0.00024087 | 2676
POINT MORETTI 11015074 | POINT MORETTI 1101 | 82931101 | FALSE | 3.0633 | 0.82956 | 1.3869 | 65.5 | 0.00053575 | 5002 | 0.54258 | 2787 | 0.00024048 | 2677
WILLITS 1102CB | WILLITS 1102 | 42661102 | FALSE | 4.3325 | 1.1013 | 1.7181 | 70.3333 | 0.0003787 | 6715 | 0.56548 | 2768 | 0.0002404 | 2678
OAKHURST 1102963056 | OAKHURST 1102 | 254421102 | TRUE | 2.3689 | 0.60691 | 0.075168 | 32.6667 | 0.00080461 | 1941 | 0.39649 | 2916 | 0.00024028 | 2679
SAN LEANDRO U 1114213524 | SAN LEANDRO U 1114 | 13111114 | FALSE | 8.3677 | 6.7102 | 7.3243 | 131.5 | 0.00053125 | 5057 | 0.36719 | 2951 | 0.00023894 | 2680
IGNACIO 11011264 | IGNACIO 1101 | 42481101 | FALSE | 3.2751 | 3.2389 | 3.6939 | 58.5 | 0.00056496 | 4707 | 0.47346 | 2849 | 0.00023863 | 2681
HORSESHOE 110450142 | HORSESHOE 1104 | 152571104 | FALSE | 4.1074 | 1.0506 | 2.2305 | 74.5 | 0.00047711 | 5627 | 0.53619 | 2790 | 0.00023818 | 2682
RINCON 1101205854 | RINCON 1101 | 43321101 | TRUE | 0.31386 | 0 | 0.2262 | 7.5 | 0.00030712 | 7861 | 0.94949 | 2449 | 0.00023769 | 2683
CAYETANO 2111MR444 | CAYETANO 2111 | 14422111 | TRUE | 0.14872 | 0 | 0.14872 | 3 | 0.00040225 | 6424 | 0.6085 | 2721 | 0.00023705 | 2684
BELL 11082202 | BELL 1108 | 152701108 | FALSE | 26.7235 | 1.7612 | 27.6411 | 471 | 0.0002162 | 9759 | 1.1673 | 2203 | 0.00023693 | 2685
LINCOLN 1101875554 | LINCOLN 1101 | 153701101 | FALSE | 6.4679 | 0.36574 | 5.7182 | 119.5 | 0.00021748 | 9742 | 1.1051 | 2298 | 0.0002367 | 2686
HATTON 11022070 | HATTON 1102 | 182291102 | FALSE | 1.9192 | 1.701 | 1.0427 | 38 | 0.00060473 | 4244 | 0.40967 | 2905 | 0.00023558 | 2687
LLAGAS 2104CB | LLAGAS 2104 | 83182104 |  | 0.12002 | 0 |  | 1.1667 | 0.0039374 | 8 | 0.057052 | 7430 | 0.00023511 | 2688
RESEARCH 210263274 | RESEARCH 2102 | 14692102 | TRUE | 9.6423 | 4.573 | 0.043457 | 168.3333 | 0.00072262 | 2822 | 0.31774 | 2995 | 0.00023471 | 2689
HOLLISTER 2102676164 | HOLLISTER 2102 | 182492102 | TRUE | 2.7383 | 0.17064 | 0.24241 | 51 | 0.00046578 | 5740 | 0.51342 | 2813 | 0.00023441 | 2690
COTATI 110387402 | COTATI 1103 | 42271103 | FALSE | 11.2012 | 0.18262 | 11.3838 | 226 | 0.00016269 | 10565 | 1.4254 | 1905 | 0.0002343 | 2691
PAUL SWEET 2102337544 | PAUL SWEET 2102 | 83252102 | TRUE | 0.87932 | 0.089418 | 0.32207 | 16 | 0.00077346 | 2223 | 0.34686 | 2967 | 0.00023369 | 2692
VIEJO 22022606 | VIEJO 2202 | 182852202 | FALSE | 2.9863 | 1.0345 | 1.145 | 62.5 | 0.00057279 | 4620 | 0.36174 | 2952 | 0.00023353 | 2693
TEMPLETON 21132949 | TEMPLETON 2113 | 183052113 | TRUE | 0.48734 | 0.027832 | 0.51517 | 10.5 | 0.00020005 | 10042 | 1.1707 | 2190 | 0.00023336 | 2694
PETALUMA C 1108208 | PETALUMA C 1108 | 42631108 | FALSE | 12.4726 | 0.5052 | 12.9778 | 243.3333 | 0.00018478 | 10280 | 1.2925 | 2014 | 0.00023317 | 2695
CLARKSVILLE 21096502 | CLARKSVILLE 2109 | 153612109 | TRUE | 5.6247 | 0.52056 | 0.58613 | 93 | 0.00050407 | 5347 | 0.60279 | 2730 | 0.00023254 | 2696
WINDSOR 1103171410 | WINDSOR 1103 | 43501103 | FALSE | 4.3534 | 0.064042 | 1.1516 | 85.5 | 0.00016991 | 10487 | 0.85549 | 2519 | 0.00023122 | 2697
CORONA 1103776806 | CORONA 1103 | 43491103 | TRUE | 1.0156 | 0.27137 | 0.24823 | 19.8333 | 0.00026414 | 8775 | 0.99208 | 2405 | 0.00023119 | 2698
SILVERADO 2103CB | SILVERADO 2103 | 43432103 |  | 13.7343 | 2.2875 |  | 305.5 | 0.0005352 | 5008 | 0.8645 | 2513 | 0.00023036 | 2699
OLETA 11021228 | OLETA 1102 | 163541102 | FALSE | 43.0424 | 1.5786 | 7.4742 | 809.5 | 0.00024169 | 9253 | 1.4097 | 1919 | 0.00022897 | 2700
ZACA 1102Y02 | ZACA 1102 | 182681102 | FALSE | 13.1091 | 0.5021 | 10.2421 | 234 | 0.00026818 | 8694 | 0.90484 | 2481 | 0.00022854 | 2701
HARRIS 1108395498 | HARRIS 1108 | 192431108 | TRUE | 0.50268 | 0.46185 | 0.17561 | 9.5 | 0.00049666 | 5427 | 0.52007 | 2808 | 0.00022852 | 2702
PHILO 1101CB | PHILO 1101 | 42601101 | FALSE | 49.7743 | 4.1094 | 31.4695 | 960.5 | 0.00027881 | 8449 | 0.94875 | 2450 | 0.00022777 | 2703
DESCHUTES 11041370 | DESCHUTES 1104 | 103351104 | FALSE | 22.0115 | 1.7819 | 12.3158 | 386 | 0.00025432 | 8994 | 0.92624 | 2467 | 0.00022756 | 2704
PALO SECO 0401CB | PALO SECO 0401 | 13180401 | FALSE | 4.7143 | 2.8219 | 7.4744 | 60.5833 | 0.00067238 | 3410 | 0.35163 | 2964 | 0.00022723 | 2705
GUALALA 1112CB | GUALALA 1112 | 42841112 | FALSE | 2.1715 | 0.39686 | 1.8477 | 46 | 0.00037496 | 6764 | 0.72606 | 2620 | 0.00022711 | 2706
PETALUMA C 1108618 | PETALUMA C 1108 | 42631108 | FALSE | 10.8244 | 1.6454 | 9.1474 | 214.5 | 0.00025302 | 9018 | 0.95491 | 2443 | 0.00022696 | 2707
MORRO BAY 1101CB | MORRO BAY 1101 | 183011101 | TRUE | 2.1595 | 1.5816 | 0.031439 | 34.5 | 0.00068226 | 3306 | 0.33256 | 2978 | 0.00022666 | 2708
OLETA 110163500 | OLETA 1101 | 163541101 | TRUE | 4.414 | 1.5028 | 0.15082 | 68.25 | 0.00042881 | 6135 | 0.85413 | 2520 | 0.00022619 | 2709
WILLITS 1103966 | WILLITS 1103 | 42661103 | FALSE | 2.2584 | 0.69411 | 1.0662 | 43.3333 | 0.00031381 | 7739 | 0.872 | 2504 | 0.00022605 | 2710
OLEMA 1101337220 | OLEMA 1101 | 42291101 | FALSE | 5.2382 | 0.20398 | 3.0524 | 105 | 0.0002866 | 8271 | 0.74862 | 2598 | 0.00022528 | 2711
BROWNS VALLEY 110136622 | BROWNS VALLEY 1101 | 152921101 | FALSE | 9.4126 | 0.069195 | 4.7696 | 183 | 0.00033677 | 7352 | 0.60271 | 2731 | 0.00022518 | 2712
WISE 1102697216 | WISE 1102 | 152271102 | FALSE | 13.3296 | 0.99687 | 12.1224 | 234.5 | 0.00018163 | 10323 | 1.2382 | 2074 | 0.00022504 | 2713
SAN LUIS OBISPO 110788962 | SAN LUIS OBISPO 1107 | 182631107 | FALSE | 3.7743 | 0.58388 | 2.4412 | 68 | 0.00033659 | 7357 | 0.97069 | 2429 | 0.00022463 | 2714
MIDDLETOWN 1102CB | MIDDLETOWN 1102 | 43141102 | TRUE | 0.78592 | 0 | 0.36317 | 10.6667 | 0.00067311 | 3399 | 0.24562 | 3087 | 0.00022426 | 2715
TEMPLETON 2108A40 | TEMPLETON 2108 | 183052108 | FALSE | 12.8389 | 5.9867 | 4.4139 | 242.5 | 0.00045169 | 5906 | 0.56026 | 2771 | 0.00022425 | 2716
WYANDOTTE 110932586 | WYANDOTTE 1109 | 102911109 | FALSE | 0.96552 | 0 | 0.77971 | 15.5 | 0.00025483 | 8984 | 0.88745 | 2493 | 0.0002242 | 2717
COTATI 110475972 | COTATI 1104 | 42271104 | FALSE | 4.5321 | 1.792 | 4.0502 | 88.5 | 0.00032792 | 7485 | 0.72811 | 2619 | 0.00022365 | 2718
DESCHUTES 11011654 | DESCHUTES 1101 | 103351101 | FALSE | 17.3912 | 0.913 | 18.3041 | 334 | 0.00017992 | 10355 | 1.2298 | 2082 | 0.0002227 | 2719
COTTONWOOD 11031344 | COTTONWOOD 1103 | 102931103 | FALSE | 12.3346 | 1.0204 | 10.6583 | 224 | 0.00024668 | 9153 | 1.0562 | 2339 | 0.00022266 | 2720
GARBERVILLE 1103CB | GARBERVILLE 1103 | 192221103 | FALSE | 2.2357 | 1.7432 | 0.74633 | 28.4167 | 0.00045835 | 5827 | 0.51307 | 2814 | 0.00022235 | 2721
LAURELES 11122142 | LAURELES 1112 | 182371112 | TRUE | 1.6028 | 0.86949 | 0.1137 | 28 | 0.00064603 | 3754 | 0.62271 | 2712 | 0.00022217 | 2722
COTTONWOOD 11029026 | COTTONWOOD 1102 | 102931102 | FALSE | 24.4659 | 1.3048 | 12.4975 | 419 | 0.00023019 | 9482 | 1.0733 | 2330 | 0.0002216 | 2723
HOOPA 110193038 | HOOPA 1101 | 192401101 | FALSE | 2.7979 | 0.83039 | 1.2561 | 51 | 0.00033299 | 7408 | 0.53803 | 2789 | 0.00022153 | 2724
WYANDOTTE 1105CB | WYANDOTTE 1105 | 102911105 | FALSE | 2.9926 | 0 | 0.98653 | 35 | 0.00073281 | 2699 | 0.52523 | 2800 | 0.0002214 | 2725
HAMILTON BRANCH 11012082 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 3.0696 | 1.8767 | 1.8146 | 53 | 0.00041826 | 6242 | 0.63204 | 2702 | 0.00022099 | 2726
COTATI 1104CB | COTATI 1104 | 42271104 | FALSE | 7.8953 | 1.7598 | 4.0198 | 141.25 | 0.00042898 | 6131 | 0.53333 | 2792 | 0.00022022 | 2727
SOLEDAD 2105404754 | SOLEDAD 2105 | 182052105 | FALSE | 0.86824 | 0.01517 | 0.74904 | 17.5 | 0.00021563 | 9765 | 1.0572 | 2338 | 0.00021941 | 2728
BURNEY 11011358 | BURNEY 1101 | 103311101 | FALSE | 9.5657 | 0.36807 | 7.9738 | 194.3333 | 0.00020383 | 9983 | 0.98693 | 2408 | 0.00021908 | 2729
PEORIA 170567898 | PEORIA 1705 | 163781705 | FALSE | 5.9191 | 1.219 | 3.9516 | 106 | 0.00037385 | 6783 | 0.5914 | 2746 | 0.00021887 | 2730
PETALUMA C 1108600 | PETALUMA C 1108 | 42631108 | FALSE | 8.6781 | 2.813 | 4.9784 | 166.5 | 0.00031802 | 7667 | 0.7846 | 2573 | 0.00021881 | 2731
ANTELOPE 1101318686 | ANTELOPE 1101 | 252021101 | FALSE | 3.0685 | 0 | 0.91823 | 63.5 | 0.00016415 | 10545 | 1.4934 | 1852 | 0.00021871 | 2732
COTATI 1102282 | COTATI 1102 | 42271102 | FALSE | 8.8899 | 1.47 | 3.0517 | 148 | 0.00026257 | 8816 | 0.83317 | 2536 | 0.00021822 | 2733
DESCHUTES 11019722 | DESCHUTES 1101 | 103351101 | FALSE | 4.7349 | 0.14529 | 3.0967 | 75 | 0.00026151 | 8853 | 0.97157 | 2428 | 0.00021812 | 2734
PLACER 1103284874 | PLACER 1103 | 152461103 | FALSE | 4.8807 | 1.2443 | 1.9286 | 95.5 | 0.00028447 | 8322 | 0.76606 | 2587 | 0.00021804 | 2735
PURISIMA 1101Y44 | PURISIMA 1101 | 182971101 | FALSE | 11.5124 | 0.045211 | 10.3524 | 206.5 | 0.00011304 | 10996 | 2.1219 | 1599 | 0.00021799 | 2736
WYANDOTTE 110737472 | WYANDOTTE 1107 | 102911107 | FALSE | 15.1751 | 0.82255 | 8.8347 | 274.5 | 0.00025742 | 8936 | 0.8517 | 2522 | 0.00021796 | 2737
CLAY 110398680 | CLAY 1103 | 163341103 | TRUE | 0.028954 | 0 | 0.028954 | 0.5 | 0.00018908 | 10224 | 1.15 | 2248 | 0.00021744 | 2738
ROB ROY 210512474 | ROB ROY 2105 | 83692105 | FALSE | 8.6014 | 3.51 | 4.2964 | 128.3333 | 0.00064856 | 3721 | 0.34653 | 2968 | 0.00021707 | 2739
OCEANO 1104104102 | OCEANO 1104 | 182601104 | FALSE | 3.62 | 0.26707 | 3.1935 | 74.5 | 0.00017915 | 10365 | 1.2088 | 2124 | 0.00021637 | 2740
PETALUMA C 1108233646 | PETALUMA C 1108 | 42631108 | FALSE | 11.1501 | 2.2568 | 11.0026 | 206 | 0.00022673 | 9570 | 1.03 | 2362 | 0.00021605 | 2741
HAMILTON BRANCH 1101CB | HAMILTON BRANCH 1101 | 102361101 | FALSE | 3.6259 | 2.0087 | 3.2457 | 64 | 0.0003896 | 6576 | 0.61682 | 2716 | 0.00021549 | 2742
POINT ARENA 110198224 | POINT ARENA 1101 | 43381101 | FALSE | 2.3469 | 0 | 2.3469 | 41.8333 | 0.00018617 | 10261 | 1.1639 | 2213 | 0.00021538 | 2743
ANDERSON 11011752 | ANDERSON 1101 | 103261101 | FALSE | 9.9535 | 0.75434 | 8.7888 | 177.5 | 0.00024849 | 9110 | 0.97232 | 2427 | 0.00021485 | 2744
ELK 11014628 | ELK 1101 | 42981101 | FALSE | 4.3138 | 0.6934 | 2.6839 | 81 | 0.00031668 | 7688 | 0.68952 | 2653 | 0.00021483 | 2745
SANTA ROSA A 1107CB | SANTA ROSA A 1107 | 42151107 | FALSE | 6.1674 | 4.3388 | 4.8999 | 111.5 | 0.00073592 | 2668 | 0.38842 | 2931 | 0.00021463 | 2746
ANNAPOLIS 1101CB | ANNAPOLIS 1101 | 42861101 | FALSE | 0.75314 | 0 | 0.75314 | 13 | 0.00016714 | 10514 | 1.2924 | 2015 | 0.00021437 | 2747
ROB ROY 210512586 | ROB ROY 2105 | 83692105 | FALSE | 6.5392 | 4.2291 | 2.7143 | 93.6667 | 0.00061175 | 4149 | 0.39456 | 2918 | 0.00021436 | 2748
WOODSIDE 1101CB | WOODSIDE 1101 | 24251101 | TRUE | 4.202 | 0.85846 | 0.00030012 | 87.5 | 0.00075787 | 2410 | 0.22076 | 3117 | 0.00021418 | 2749
HARTLEY 1101CB | HARTLEY 1101 | 43211101 | FALSE | 2.9693 | 0.28711 | 1.3807 | 51 | 0.00037528 | 6759 | 0.49548 | 2826 | 0.000214 | 2750
SHINGLE SPRINGS 11038752 | SHINGLE SPRINGS 1103 | 153651103 | FALSE | 1.8712 | 0.23495 | 2.0743 | 28.6667 | 0.00067908 | 3336 | 0.2756 | 3047 | 0.00021394 | 2751
WISE 1102307494 | WISE 1102 | 152271102 | FALSE | 33.5436 | 1.2869 | 31.4985 | 622 | 0.00014045 | 10783 | 2.0674 | 1617 | 0.00021373 | 2752
PLACER 1103429574 | PLACER 1103 | 152461103 | FALSE | 9.5508 | 2.8913 | 3.9872 | 170 | 0.0003964 | 6496 | 0.63651 | 2698 | 0.00021339 | 2753
CLOVERDALE 1102156 | CLOVERDALE 1102 | 42821102 | FALSE | 11.7977 | 1.5801 | 5.6684 | 225.5 | 0.00027562 | 8522 | 1.3918 | 1937 | 0.00021319 | 2754
HAMILTON BRANCH 11013049 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 1.6762 | 0.71385 | 1.2906 | 28.5 | 0.00034022 | 7303 | 0.58 | 2756 | 0.00021308 | 2755
SAN RAMON 2119CB | SAN RAMON 2119 | 14232119 | TRUE | 1.1338 | 0.079702 | 0.59007 | 9.9167 | 0.00093374 | 1079 | 0.4169 | 2896 | 0.00021298 | 2756
POINT ARENA 110183354 | POINT ARENA 1101 | 43381101 | FALSE | 5.2547 | 0.16812 | 5.4228 | 100.5 | 0.00017719 | 10394 | 1.2108 | 2114 | 0.00021268 | 2757
MORGAN HILL 2111CB | MORGAN HILL 2111 | 83242111 | TRUE | 2.5916 | 0.82427 | 0.15323 | 51.1667 | 0.00059091 | 4402 | 0.64795 | 2685 | 0.00021254 | 2758
RINCON 1102CB | RINCON 1102 | 43321102 | FALSE | 2.2745 | 0.56105 | 1.9513 | 38 | 0.00070038 | 3093 | 0.33839 | 2974 | 0.00021249 | 2759
POINT MORETTI 110135874 | POINT MORETTI 1101 | 82931101 | TRUE | 0.20473 | 0.01344 | 0.21817 | 3 | 0.00017558 | 10414 | 1.2105 | 2116 | 0.00021201 | 2760
GUALALA 1111445166 | GUALALA 1111 | 42841111 | FALSE | 9.5077 | 0.031297 | 5.7511 | 193 | 0.00022257 | 9656 | 0.82325 | 2543 | 0.00021184 | 2761
MONTE RIO 111159046 | MONTE RIO 1111 | 42811111 | FALSE | 3.7396 | 0.21622 | 3.4879 | 75 | 0.00016793 | 10507 | 1.8127 | 1698 | 0.0002115 | 2762
FORT ORD 210736596 | FORT ORD 2107 | 182402107 | FALSE | 12.5166 | 5.1085 | 3.9701 | 217 | 0.00069295 | 3178 | 0.44458 | 2872 | 0.00021096 | 2763
BURNEY 11011322 | BURNEY 1101 | 103311101 | FALSE | 18.6301 | 0.36564 | 15.0832 | 333.3333 | 0.00020233 | 10006 | 1.0134 | 2375 | 0.00021092 | 2764
OILFIELDS 1103233424 | OILFIELDS 1103 | 182391103 | FALSE | 1.9976 | 0.034148 | 2.0317 | 36.5 | 0.00017983 | 10356 | 1.1649 | 2208 | 0.00021075 | 2765
HIGGINS 1107746082 | HIGGINS 1107 | 152691107 | FALSE | 0.81159 | 0 | 0.81159 | 13 | 0.00014566 | 10741 | 1.4628 | 1877 | 0.00021019 | 2766
FITCH MOUNTAIN 111324550 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 21.5512 | 1.4778 | 9.2245 | 403 | 0.00037206 | 6804 | 0.9032 | 2483 | 0.00021008 | 2767
BANGOR 1101CB | BANGOR 1101 | 103191101 | FALSE | 20.8882 | 1.4637 | 1.4438 | 381 | 0.00016487 | 10535 | 1.1543 | 2235 | 0.00020951 | 2768
SAN MIGUEL 1106428314 | SAN MIGUEL 1106 | 182661106 | FALSE | 18.2512 | 0.33731 | 14.8985 | 366.5 | 0.00012494 | 10925 | 1.5606 | 1800 | 0.00020868 | 2769
COPPERMINE 1104613086 | COPPERMINE 1104 | 252411104 | FALSE | 9.2262 | 0.36692 | 4.6565 | 170.5 | 0.00011832 | 10965 | 2.5562 | 1495 | 0.00020834 | 2770
LLAGAS 2105XR234 | LLAGAS 2105 | 83182105 | TRUE | 2.2018 | 0.083636 | 0.0025629 | 46.5 | 0.00033847 | 7334 | 0.94714 | 2451 | 0.00020788 | 2771
SNEATH LANE 110168070 | SNEATH LANE 1101 | 22721101 | TRUE | 2.1453 | 2.211 | 0.49106 | 37.5 | 0.00073492 | 2677 | 0.3215 | 2989 | 0.00020767 | 2772
BANGOR 1101614048 | BANGOR 1101 | 103191101 | FALSE | 16.7729 | 0.49789 | 14.5199 | 312.5 | 0.00014785 | 10721 | 1.2882 | 2021 | 0.00020748 | 2773
POINT MORETTI 11015104 | POINT MORETTI 1101 | 82931101 | FALSE | 1.801 | 0.01409 | 1.8151 | 38 | 0.0001795 | 10360 | 1.1548 | 2232 | 0.0002069 | 2774
CLAY 110184572 | CLAY 1101 | 163341101 | TRUE | 2.1937 | 0.8358 | 0.46757 | 31.5 | 0.00057094 | 4647 | 0.44322 | 2876 | 0.00020629 | 2775
PASO ROBLES 1103351084 | PASO ROBLES 1103 | 182611103 | FALSE | 9.033 | 1.7174 | 2.3571 | 164.5 | 0.00014145 | 10773 | 4.2186 | 1222 | 0.00020586 | 2776
MORAGA 1105CB | MORAGA 1105 | 13801105 | TRUE | 6.2996 | 3.8442 | 0.26387 | 98.3333 | 0.00075679 | 2418 | 0.2652 | 3059 | 0.00020526 | 2777
SAN LEANDRO U 1114653758 | SAN LEANDRO U 1114 | 13111114 | TRUE | 0.36276 | 0 | 0.36276 | 7.5 | 0.00017818 | 10375 | 1.15 | 2248 | 0.0002049 | 2778
SOBRANTE 1101L534R | SOBRANTE 1101 | 14671101 | FALSE | 1.8977 | 0.95741 | 1.3871 | 35.5 | 0.00073091 | 2717 | 0.3543 | 2960 | 0.00020417 | 2779
COTATI 11055156 | COTATI 1105 | 42271105 | FALSE | 9.8962 | 1.745 | 5.0282 | 176.5 | 0.00034559 | 7214 | 0.60388 | 2727 | 0.00020407 | 2780
CAMBRIA 1102W50 | CAMBRIA 1102 | 182771102 | FALSE | 3.6148 | 3.4338 | 0.91974 | 37 | 0.00058762 | 4448 | 0.30746 | 3011 | 0.00020302 | 2781
TASSAJARA 2103883664 | TASSAJARA 2103 | 14662103 | TRUE | 1.2209 | 0.37169 | 0.090594 | 19.5 | 0.00089843 | 1242 | 0.1979 | 3147 | 0.00020291 | 2782
SAN LEANDRO U 1109CR284 | SAN LEANDRO U 1109 | 13111109 | FALSE | 0.94655 | 0.87514 | 1.201 | 15.1667 | 0.00076219 | 2350 | 0.27005 | 3055 | 0.00020282 | 2783
DESCHUTES 1101CB | DESCHUTES 1101 | 103351101 | FALSE | 11.2954 | 0.8025 | 4.0452 | 191 | 0.00033411 | 7394 | 0.60367 | 2728 | 0.00020235 | 2784
COTATI 110536536 | COTATI 1105 | 42271105 | FALSE | 19.5566 | 1.7828 | 16.5301 | 349 | 0.00022022 | 9695 | 0.91747 | 2472 | 0.0002023 | 2785
PAUL SWEET 210912828 | PAUL SWEET 2109 | 83252109 | FALSE | 4.8585 | 2.3155 | 1.2319 | 74 | 0.00061335 | 4130 | 0.42236 | 2892 | 0.00020224 | 2786
COARSEGOLD 210410030 | COARSEGOLD 2104 | 254432104 | FALSE | 36.9708 | 1.0138 | 34.0927 | 677.5 | 0.00012132 | 10943 | 1.6655 | 1760 | 0.00020217 | 2787
PETALUMA C 1108883512 | PETALUMA C 1108 | 42631108 | TRUE | 0.17411 | 0 | 0.17411 | 2.5 | 0.00016531 | 10531 | 1.2226 | 2099 | 0.00020211 | 2788
PENRYN 1103660 | PENRYN 1103 | 152561103 | FALSE | 19.6221 | 2.4085 | 10.8127 | 345.6667 | 0.00029557 | 8094 | 0.62802 | 2706 | 0.00020188 | 2789
BOLINAS 11011064 | BOLINAS 1101 | 42261101 | TRUE | 4.4151 | 1.9561 | 0.60372 | 88.5 | 0.0004964 | 5430 | 0.35184 | 2963 | 0.00020173 | 2790
GIRVAN 1102212096 | GIRVAN 1102 | 103401102 | FALSE | 4.0762 | 0.14454 | 2.4845 | 72.5 | 0.00023309 | 9424 | 0.82156 | 2544 | 0.00020139 | 2791
ELK 1101311906 | ELK 1101 | 42981101 | TRUE | 0.941 | 0.030424 | 0.35551 | 18.3333 | 0.00038402 | 6651 | 0.5789 | 2759 | 0.0002011 | 2792
HARTLEY 1101738 | HARTLEY 1101 | 43211101 | FALSE | 8.1186 | 3.2791 | 2.7952 | 124.1667 | 0.00045832 | 5830 | 0.52512 | 2801 | 0.00020054 | 2793
HUMBOLDT BAY 1102104220 | HUMBOLDT BAY 1102 | 192341102 | FALSE | 3.2296 | 1.7807 | 1.0087 | 56.8333 | 0.00050497 | 5335 | 0.40967 | 2906 | 0.00020049 | 2794
VACAVILLE 1103CB | VACAVILLE 1103 | 63601103 |  | 11.1249 | 9.492 |  | 154.3333 | 0.0010474 | 630 | 0.30065 | 3020 | 0.00019994 | 2795
VALLEY VIEW 1106P128 | VALLEY VIEW 1106 | 14341106 | TRUE | 2.5427 | 1.8169 | 0.16039 | 40 | 0.00055586 | 4804 | 0.39738 | 2915 | 0.00019981 | 2796
PLACER 1104CB | PLACER 1104 | 152461104 |  | 0.60811 | 0.1804 |  | 10.3333 | 0.0011591 | 361 | 0.20631 | 3135 | 0.00019965 | 2797
HICKS 2101CB | HICKS 2101 | 83432101 | FALSE | 10.8575 | 0 | 2.7886 | 102.1667 | 0.00074729 | 2517 | 0.49248 | 2829 | 0.00019955 | 2798
SAN LUIS OBISPO 1103V82 | SAN LUIS OBISPO 1103 | 182631103 | FALSE | 14.0641 | 2.7667 | 9.5934 | 256.3333 | 0.00031319 | 7751 | 0.81934 | 2545 | 0.00019893 | 2799
SAN RAFAEL 1109418 | SAN RAFAEL 1109 | 42011109 | FALSE | 12.7066 | 6.4874 | 5.7715 | 237.5 | 0.00036822 | 6869 | 0.69375 | 2651 | 0.00019892 | 2800
HICKS 2101984788 | HICKS 2101 | 83432101 | FALSE | 1.0261 | 0 | 1.0261 | 22.5 | 0.00011223 | 11004 | 2.3121 | 1553 | 0.00019785 | 2801
LOS OSITOS 2103220608 | LOS OSITOS 2103 | 182082103 | FALSE | 2.2077 | 0.19873 | 0.97496 | 41.5 | 0.00011534 | 10983 | 3.3598 | 1334 | 0.00019771 | 2802
VIEJO 22039094 | VIEJO 2203 | 182852203 | TRUE | 2.5259 | 2.96 | 0.00079843 | 39.5 | 0.00079717 | 1991 | 0.22974 | 3105 | 0.00019736 | 2803
{-1} | [6 empty] | 22301 | 3.4206e-05 | 11141 | 0.98431 | 2410 | 0.00019729 | 2804
OAKLAND X 1105184672 | OAKLAND X 1105 | 12541105 | FALSE | 3.2575 | 3.7995 | 3.494 | 52.25 | 0.00041883 | 6236 | 0.44026 | 2878 | 0.00019671 | 2805
MIRABEL 110286326 | MIRABEL 1102 | 42091102 | TRUE | 0.70193 | 0.0075793 | 0.56096 | 13.5 | 0.00031466 | 7728 | 0.70878 | 2633 | 0.00019656 | 2806
PERRY 1101W26 | PERRY 1101 | 183071101 | FALSE | 2.668 | 0.10202 | 2.7701 | 51 | 0.00016033 | 10596 | 1.2262 | 2089 | 0.00019644 | 2807
MORGAN HILL 2106CB | MORGAN HILL 2106 | 83242106 | TRUE | 3.8916 | 1.0085 | 0.12309 | 72.6667 | 0.00060704 | 4215 | 0.48298 | 2839 | 0.00019561 | 2808
COTTONWOOD 110131500 | COTTONWOOD 1101 | 102931101 | FALSE | 11.7328 | 0.47942 | 4.0472 | 211.5 | 0.00020398 | 9978 | 1.0053 | 2386 | 0.00019556 | 2809
BURNEY 110237284 | BURNEY 1102 | 103311102 | TRUE | 0.51739 | 0.48585 | 0.35171 | 14 | 0.00041088 | 6325 | 0.37394 | 2946 | 0.00019537 | 2810
COTATI 1105213984 | COTATI 1105 | 42271105 | FALSE | 4.533 | 0.34317 | 4.8762 | 88.3333 | 0.00015644 | 10636 | 1.2226 | 2098 | 0.00019479 | 2811
WYANDOTTE 110979932 | WYANDOTTE 1109 | 102911109 | FALSE | 32.9192 | 2.015 | 22.5148 | 589 | 0.00016942 | 10494 | 1.2073 | 2126 | 0.00019455 | 2812
ARBUCKLE 1103CB | ARBUCKLE 1103 | 62081103 |  | 0.042474 | 0.028338 |  | 0.75 | 0.002897 | 13 | 0.067105 | 5893 | 0.0001944 | 2813
PAUL SWEET 210710986 | PAUL SWEET 2107 | 83252107 | FALSE | 19.4124 | 1.2035 | 2.1889 | 378 | 0.00034989 | 7141 | 0.6407 | 2690 | 0.00019429 | 2814
POSO MOUNTAIN 21014456 | POSO MOUNTAIN 2101 | 253642101 | FALSE | 23.3384 | 0.15297 | 23.4913 | 451.5 | 7.5323e-05 | 11114 | 2.0763 | 1615 | 0.00019412 | 2815
ELECTRA 1101105880 | ELECTRA 1101 | 162161101 | FALSE | 5.7966 | 1.2066 | 2.7478 | 90.1667 | 0.00037992 | 6698 | 0.86998 | 2509 | 0.00019381 | 2816
PUEBLO 1105348368 | PUEBLO 1105 | 43291105 | FALSE | 9.2992 | 1.0796 | 2.1519 | 170.5 | 0.00046765 | 5721 | 0.39623 | 2917 | 0.0001933 | 2817
HATTON 11012026 | HATTON 1101 | 182291101 | FALSE | 10.1721 | 3.0946 | 6.2165 | 188.5 | 0.00039401 | 6522 | 0.6474 | 2686 | 0.00019322 | 2818
SILVERADO 2105533226 | SILVERADO 2105 | 43432105 | TRUE | 7.3198 | 1.0863 | 0.0014991 | 141.8333 | 0.00071859 | 2868 | 0.64376 | 2689 | 0.00019268 | 2819
JESSUP 1102CB | JESSUP 1102 | 103441102 |  | 4.6145 | 1.1054 |  | 86 | 0.00049414 | 5453 | 0.54396 | 2786 | 0.00019242 | 2820
FROGTOWN 1702204480 | FROGTOWN 1702 | 163451702 | TRUE | 2.0229 | 0.61036 | 0.46729 | 39 | 0.0003884 | 6598 | 0.57988 | 2758 | 0.00019227 | 2821
LOYOLA 1102429970 | LOYOLA 1102 | 82161102 |  | 4.1181 | 0.9815 |  | 79 | 0.00060537 | 4232 | 0.46722 | 2855 | 0.00019211 | 2822
PETALUMA C 1109270 | PETALUMA C 1109 | 42631109 | FALSE | 7.6587 | 4.8446 | 2.5225 | 133.8333 | 0.00049742 | 5420 | 0.52441 | 2803 | 0.00019176 | 2823
WOODSIDE 1102472928 | WOODSIDE 1102 | 24251102 | TRUE | 1.0083 | 0.97953 | 0.15358 | 12.5833 | 0.00065972 | 3582 | 0.34093 | 2971 | 0.00019156 | 2824
BRUNSWICK 1105CB | BRUNSWICK 1105 | 152481105 | TRUE | 0.53772 | 0 | 0.28341 | 12 | 0.0010013 | 787 | 0.1723 | 3182 | 0.00019105 | 2825
CABRILLO 1103Y46 | CABRILLO 1103 | 183101103 | FALSE | 47.4901 | 1.4695 | 26.1259 | 908 | 0.00015695 | 10630 | 1.5132 | 1835 | 0.00019091 | 2826
PENRYN 110790970 | PENRYN 1107 | 152561107 | FALSE | 4.1983 | 1.3872 | 1.3096 | 71.5 | 0.0004672 | 5723 | 0.45319 | 2866 | 0.00019055 | 2827
HUMBOLDT BAY 1102741980 | HUMBOLDT BAY 1102 | 192341102 | FALSE | 9.459 | 1.0444 | 6.0162 | 189.5 | 0.00027081 | 8633 | 0.67851 | 2662 | 0.00019051 | 2828
SANTA ROSA A 110439786 | SANTA ROSA A 1104 | 42151104 | TRUE | 3.3819 | 2.255 | 0.41876 | 42.5 | 0.00077922 | 2155 | 0.31642 | 2997 | 0.00018992 | 2829
CORRAL 110112612 | CORRAL 1101 | 162991101 | FALSE | 19.9927 | 0.68511 | 19.7583 | 350 | 0.00017454 | 10426 | 1.1086 | 2291 | 0.0001899 | 2830
PENRYN 1106212772 | PENRYN 1106 | 152561106 | FALSE | 0.94895 | 0.055914 | 0.85906 | 16.3333 | 0.0002203 | 9694 | 0.99973 | 2393 | 0.00018978 | 2831
IGNACIO 1103CB | IGNACIO 1103 | 42481103 | TRUE | 2.5476 | 1.1487 | 0.15444 | 43.1667 | 0.0006316 | 3922 | 0.44394 | 2874 | 0.00018898 | 2832
OLETA 1101190308 | OLETA 1101 | 163541101 |  | 3.1594 | 1.1714 |  | 45.5 | 0.00053878 | 4968 | 0.33243 | 2979 | 0.00018897 | 2833
GEYSERVILLE 1102504260 | GEYSERVILLE 1102 | 42891102 | FALSE | 2.9614 | 0.057635 | 2.0883 | 52.5 | 0.00021699 | 9750 | 1.4885 | 1856 | 0.00018869 | 2834
OILFIELDS 1103N42 | OILFIELDS 1103 | 182391103 | FALSE | 5.921 | 0 | 2.5929 | 107 | 0.00019137 | 10190 | 1.5185 | 1830 | 0.00018868 | 2835
AUBERRY 110237466 | AUBERRY 1102 | 254151102 | FALSE | 31.7044 | 0.63394 | 32.3382 | 571 | 9.8384e-05 | 11057 | 1.9082 | 1666 | 0.00018823 | 2836
DUNBAR 1101872066 | DUNBAR 1101 | 43071101 | FALSE | 0.7988 | 0.42951 | 0.66782 | 15.5 | 0.00059308 | 4382 | 0.52395 | 2805 | 0.00018785 | 2837
VIEJO 22029120 | VIEJO 2202 | 182852202 | FALSE | 7.3899 | 5.2316 | 2.8374 | 148.5833 | 0.000517 | 5205 | 0.37711 | 2941 | 0.00018713 | 2838
MILPITAS 1103CB | MILPITAS 1103 | 82831103 |  | 0.036183 | 0 |  | 0.91667 | 0.0035034 | 10 | 0.053073 | 8251 | 0.00018594 | 2839
MORRO BAY 1102868170 | MORRO BAY 1102 | 183011102 | FALSE | 9.6005 | 0.2466 | 9.1816 | 150 | 0.00014114 | 10775 | 1.2846 | 2023 | 0.00018559 | 2840
MOLINO 110241392 | MOLINO 1102 | 42571102 | FALSE | 14.2944 | 1.8228 | 3.5879 | 261 | 0.00040225 | 6423 | 0.50182 | 2819 | 0.00018517 | 2841
TIDEWATER 210665866 | TIDEWATER 2106 | 14652106 | TRUE | 8.9379 | 2.2395 | 0.35972 | 176.8333 | 0.000498 | 5413 | 0.38452 | 2934 | 0.00018479 | 2842
PERRY 1101V88 | PERRY 1101 | 183071101 | FALSE | 3.1476 | 1.459 | 0.8223 | 59 | 0.0004279 | 6142 | 0.4812 | 2841 | 0.00018444 | 2843
MOLINO 1101338 | MOLINO 1101 | 42571101 | FALSE | 14.4305 | 1.1755 | 7.339 | 261.5 | 0.00030792 | 7849 | 0.64722 | 2687 | 0.00018422 | 2844
BURNEY 1102272636 | BURNEY 1102 | 103311102 | TRUE | 0.24615 | 0.059832 | 0.30598 | 1.5 | 0.00033586 | 7367 | 0.41872 | 2895 | 0.00018283 | 2845
GEYSERVILLE 110289714 | GEYSERVILLE 1102 | 42891102 | TRUE | 7.5139 | 0.24469 | 0.10143 | 141.3333 | 0.00032418 | 7555 | 0.55914 | 2774 | 0.0001828 | 2846
BUELLTON 1102CB | BUELLTON 1102 | 183041102 | FALSE | 13.8909 | 2.577 | 6.0867 | 266 | 0.00034928 | 7156 | 0.67589 | 2665 | 0.00018253 | 2847
SYCAMORE CREEK 1111153260 | SYCAMORE CREEK 1111 | 102971111 | TRUE | 0.26375 | 0.0069353 | 0.27068 | 6.5 | 0.00015847 | 10612 | 1.15 | 2248 | 0.00018224 | 2848
SAN LUIS OBISPO 1102348318 | SAN LUIS OBISPO 1102 | 182631102 | TRUE | 0.37047 | 0 | 0.37047 | 6 | 0.00015676 | 10633 | 1.15 | 2248 | 0.00018027 | 2849
CORRAL 110112606 | CORRAL 1101 | 162991101 | FALSE | 22.2674 | 0.32869 | 22.5961 | 400.5 | 0.00015345 | 10664 | 1.1804 | 2162 | 0.0001802 | 2850
GEYSERVILLE 1102350 | GEYSERVILLE 1102 | 42891102 | FALSE | 16.6846 | 0.86823 | 1.8335 | 324.5 | 0.00027866 | 8454 | 0.84244 | 2529 | 0.00017971 | 2851
CLAY 11031821 | CLAY 1103 | 163341103 | FALSE | 3.6589 | 0.088351 | 3.2776 | 72.5 | 0.00016102 | 10588 | 1.7726 | 1711 | 0.0001793 | 2852
WILLITS 110391948 | WILLITS 1103 | 42661103 | FALSE | 7.0472 | 0.41526 | 7.0596 | 124 | 0.00017035 | 10480 | 1.0965 | 2308 | 0.0001786 | 2853
PETALUMA C 1109664732 | PETALUMA C 1109 | 42631109 | FALSE | 0.86541 | 0.031503 | 0.89691 | 15.8333 | 0.00015528 | 10644 | 1.15 | 2248 | 0.00017857 | 2854
GRASS VALLEY 1101CB | GRASS VALLEY 1101 | 152031101 | FALSE | 2.4296 | 0.70281 | 0.80818 | 28.8333 | 0.00078126 | 2137 | 0.20991 | 3130 | 0.00017776 | 2855
CLARKSVILLE 210619642 | CLARKSVILLE 2106 | 153612106 | TRUE | 1.6149 | 0 | 0.46963 | 31.3333 | 0.00066444 | 3508 | 0.30906 | 3010 | 0.00017761 | 2856
CORRAL 1101639614 | CORRAL 1101 | 162991101 | FALSE | 16.4895 | 0.60029 | 17.0897 | 285.5 | 0.00013343 | 10851 | 1.4915 | 1853 | 0.00017749 | 2857
LLAGAS 2106338878 | LLAGAS 2106 | 83182106 | FALSE | 3.9387 | 0.096837 | 1.1813 | 81.5 | 0.0001638 | 10551 | 2.3416 | 1544 | 0.0001771 | 2858
CORRAL 110136652 | CORRAL 1101 | 162991101 | FALSE | 36.195 | 2.2218 | 38.4167 | 634 | 0.00014633 | 10737 | 1.2354 | 2076 | 0.0001771 | 2859
SAN LUIS OBISPO 1108809986 | SAN LUIS OBISPO 1108 | 182631108 | FALSE | 1.6434 | 0.024535 | 0.90298 | 26.5 | 0.00046007 | 5807 | 0.63626 | 2699 | 0.00017693 | 2860
OAKLAND K 1101CB | OAKLAND K 1101 | 12101101 | TRUE | 2.3865 | 2.1941 | 0.47167 | 34.3333 | 0.00063961 | 3830 | 0.27596 | 3046 | 0.00017669 | 2861
SANTA YNEZ 1104512912 | SANTA YNEZ 1104 | 182721104 | FALSE | 1.9539 | 0.64301 | 0.81521 | 30.5 | 0.00028818 | 8231 | 0.59962 | 2736 | 0.00017666 | 2862
WILLITS 1103CB | WILLITS 1103 | 42661103 | FALSE | 3.99 | 0.52418 | 3.1054 | 64.3333 | 0.00023143 | 9452 | 0.67828 | 2663 | 0.00017664 | 2863
BASALT 1106267462 | BASALT 1106 | 42461106 | FALSE | 1.845 | 0.006379 | 0.80909 | 37.5 | 0.0002246 | 9616 | 3.4827 | 1318 | 0.0001765 | 2864
DEL MONTE 21052644 | DEL MONTE 2105 | 182222105 | FALSE | 1.8081 | 1.6999 | 2.0428 | 28.6667 | 0.00057266 | 4621 | 0.40222 | 2912 | 0.00017625 | 2865
VINEYARD 2110CB | VINEYARD 2110 | 14502110 | FALSE | 11.0027 | 0.44951 | 1.5443 | 191.1667 | 0.00040169 | 6432 | 0.7196 | 2626 | 0.00017602 | 2866
SONOMA 1106510055 | SONOMA 1106 | 42721106 |  | 1.2425 | 0.096407 |  | 23.5 | 0.00050578 | 5331 | 0.65217 | 2681 | 0.00017591 | 2867
MORAGA 110381146 | MORAGA 1103 | 13801103 | FALSE | 5.1293 | 2.9384 | 0.96375 | 89.0833 | 0.00072965 | 2733 | 0.25244 | 3078 | 0.00017554 | 2868
WOODACRE 110191900 | WOODACRE 1101 | 43021101 | FALSE | 13.7749 | 0.60517 | 6.7081 | 280.5 | 0.00013923 | 10796 | 0.94096 | 2456 | 0.00017523 | 2869
PLEASANT GROVE 2107CB | PLEASANT GROVE 2107 | 152442107 |  | 0.016356 | 0 |  | 0.83333 | 0.0026092 | 15 | 0.067 | 6056 | 0.00017482 | 2870
HIGGINS 11095703 | HIGGINS 1109 | 152691109 | FALSE | 7.8954 | 0.83003 | 5.3272 | 144 | 0.00020111 | 10023 | 0.87187 | 2506 | 0.00017436 | 2871
CASTRO VALLEY 1110MR379 | CASTRO VALLEY 1110 | 14091110 | FALSE | 1.5966 | 1.5583 | 2.0216 | 28.5 | 0.00052001 | 5178 | 0.29797 | 3024 | 0.00017382 | 2872
CABRILLO 1103Y12 | CABRILLO 1103 | 183101103 | FALSE | 30.7384 | 1.2052 | 26.0063 | 545.8333 | 0.00015672 | 10635 | 1.2894 | 2020 | 0.00017379 | 2873
NEWBURG 1133CB | NEWBURG 1133 | 192151133 | FALSE | 9.195 | 1.6694 | 2.5862 | 160.6667 | 0.00042336 | 6187 | 0.41156 | 2900 | 0.0001736 | 2874
CORRAL 1101CB | CORRAL 1101 | 162991101 | FALSE | 26.8622 | 0.74025 | 26.2912 | 473.3333 | 0.00016218 | 10572 | 1.0817 | 2322 | 0.00017247 | 2875
LLAGAS 2101XR584 | LLAGAS 2101 | 83182101 | FALSE | 15.5587 | 1.328 | 5.962 | 315 | 0.00020716 | 9926 | 2.67 | 1466 | 0.00017175 | 2876
SOLEDAD 2101955138 | SOLEDAD 2101 | 182052101 | FALSE | 2.9715 | 0.059723 | 2.8105 | 54.5 | 0.00014687 | 10730 | 1.1592 | 2222 | 0.00017012 | 2877
AUBURN 1101CB | AUBURN 1101 | 152161101 |  | 1.5582 | 1.4606 |  | 23.3333 | 0.0011089 | 460 | 0.15142 | 3201 | 0.00016969 | 2878
RINCON 1101CB | RINCON 1101 | 43321101 | FALSE | 3.7591 | 2.124 | 0.98207 | 57.1667 | 0.00087496 | 1393 | 0.21086 | 3129 | 0.00016965 | 2879
FORT BRAGG A 1102CB | FORT BRAGG A 1102 | 42761102 | FALSE | 5.8421 | 1.5735 | 2.2585 | 98.0833 | 0.00048951 | 5502 | 0.40363 | 2911 | 0.0001694 | 2880
PAUL SWEET 210212850 | PAUL SWEET 2102 | 83252102 | TRUE | 4.1202 | 1.1265 | 0.54117 | 51.4167 | 0.0007071 | 3015 | 0.34561 | 2969 | 0.000169 | 2881
COTATI 1104426 | COTATI 1104 | 42271104 | FALSE | 3.8458 | 1.6191 | 2.2997 | 71.8333 | 0.00041254 | 6307 | 0.56005 | 2772 | 0.00016888 | 2882
MORRO BAY 1101W20 | MORRO BAY 1101 | 183011101 | FALSE | 3.9812 | 2.0207 | 2.0481 | 44 | 0.00011834 | 10964 | 0.71016 | 2632 | 0.00016878 | 2883
SAN LUIS OBISPO 1108337126 | SAN LUIS OBISPO 1108 | 182631108 | TRUE | 1.3546 | 0.13146 | 0.42429 | 20.5 | 0.00039969 | 6459 | 0.55643 | 2776 | 0.00016844 | 2884
GANSNER 110152664 | GANSNER 1101 | 103021101 | TRUE | 3.8914 | 2.3845 | 0.20509 | 57.5 | 0.00038364 | 6659 | 0.51649 | 2810 | 0.00016806 | 2885
HILLSDALE 0401289582 | HILLSDALE 0401 | 24110401 |  | 0.76712 | 0.51868 |  | 13.5 | 0.00046072 | 5801 | 0.43092 | 2882 | 0.00016765 | 2886
MORAGA 1105829530 | MORAGA 1105 | 13801105 | FALSE | 2.5791 | 0.23863 | 1.6914 | 44.8333 | 0.00035549 | 7048 | 0.97649 | 2423 | 0.00016753 | 2887
SANTA YNEZ 1104Y04 | SANTA YNEZ 1104 | 182721104 | FALSE | 21.5699 | 0.7238 | 14.8412 | 381.5 | 0.0001963 | 10108 | 0.9728 | 2425 | 0.0001675 | 2888
WILLITS 1103964 | WILLITS 1103 | 42661103 | FALSE | 5.4737 | 0.092669 | 2.753 | 98.5 | 0.00018107 | 10338 | 0.61729 | 2715 | 0.0001674 | 2889
CORRAL 110359770 | CORRAL 1103 | 162991103 | FALSE | 7.119 | 1.0682 | 4.7071 | 134 | 0.00024287 | 9226 | 0.75143 | 2595 | 0.00016625 | 2890
CLAY 1101CB | CLAY 1101 | 163341101 | TRUE | 2.7709 | 0.84556 | 0.48017 | 38.8333 | 0.00077656 | 2189 | 0.23408 | 3102 | 0.00016608 | 2891
MC ARTHUR 11011546 | MC ARTHUR 1101 | 103491101 | FALSE | 23.4991 | 0.77764 | 13.3225 | 444 | 0.00011402 | 10991 | 1.6815 | 1752 | 0.00016603 | 2892
SALMON CREEK 110188998 | SALMON CREEK 1101 | 43161101 | FALSE | 13.6448 | 1.0787 | 3.8853 | 258.5 | 0.00018622 | 10260 | 0.81686 | 2546 | 0.00016592 | 2893
PURISIMA 110149394 | PURISIMA 1101 | 182971101 | FALSE | 8.7856 | 6.9943 | 1.0503 | 152.5 | 0.00043175 | 6097 | 0.42175 | 2893 | 0.00016572 | 2894
HIGHLANDS 110484640 | HIGHLANDS 1104 | 43361104 | TRUE | 0.72642 | 0.18404 | 0.31827 | 14 | 0.0005714 | 4637 | 0.22339 | 3113 | 0.00016518 | 2895
DIAMOND SPRINGS 1107CB | DIAMOND SPRINGS 1107 | 152261107 | TRUE | 6.1446 | 1.261 | 0.039701 | 104.6667 | 0.00065835 | 3594 | 0.43968 | 2879 | 0.00016454 | 2896
SWIFT 2110XR366 | SWIFT 2110 | 83392110 | FALSE | 10.9381 | 1.7148 | 8.8015 | 200.8333 | 0.00022924 | 9508 | 0.88633 | 2496 | 0.00016413 | 2897
CLARKSVILLE 2105CB | CLARKSVILLE 2105 | 153612105 | TRUE | 0.92493 | 0 | 0.52907 | 11.1667 | 0.00063803 | 3852 | 0.19631 | 3152 | 0.00016346 | 2898
SAN LEANDRO U 1114MR545 | SAN LEANDRO U 1114 | 13111114 | FALSE | 4.5145 | 4.4739 | 3.9524 | 76.3333 | 0.00061062 | 4160 | 0.25295 | 3077 | 0.00016335 | 2899
CASTRO VALLEY 1110CB | CASTRO VALLEY 1110 | 14091110 | TRUE | 1.2875 | 0.89754 | 0.47679 | 30.5 | 0.00053768 | 4982 | 0.39931 | 2913 | 0.00016273 | 2900
JESSUP 1103770356 | JESSUP 1103 | 103441103 | TRUE | 4.6411 | 1.2039 | 0.16711 | 84.5 | 0.00027857 | 8458 | 0.70227 | 2640 | 0.00016206 | 2901
HOPLAND 1101CB | HOPLAND 1101 | 42251101 | TRUE | 5.3349 | 1.1242 | 0.38455 | 100.3333 | 0.00038292 | 6667 | 1.4676 | 1875 | 0.00016203 | 2902
POINT ARENA 11013702 | POINT ARENA 1101 | 43381101 | FALSE | 5.0154 | 0 | 4.9183 | 99 | 0.00013912 | 10799 | 1.1637 | 2214 | 0.000162 | 2903
PUEBLO 2103329486 | PUEBLO 2103 | 43292103 |  | 2.8997 | 0.86556 |  | 58 | 0.00041248 | 6308 | 0.54896 | 2782 | 0.00016179 | 2904
CORNING 1102915324 | CORNING 1102 | 103331102 | FALSE | 3.3709 | 0.093161 | 1.9367 | 63.5 | 0.00017947 | 10361 | 1.0889 | 2313 | 0.0001615 | 2905
LLAGAS 2107870396 | LLAGAS 2107 | 83182107 | FALSE | 2.9519 | 0.31278 | 0.83636 | 61 | 0.0003425 | 7266 | 0.40812 | 2907 | 0.0001615 | 2906
COTATI 1105844060 | COTATI 1105 | 42271105 | FALSE | 2.2351 | 0.021653 | 2.2567 | 41.5 | 0.00013175 | 10868 | 1.2226 | 2099 | 0.00016132 | 2907
SAN LUIS OBISPO 1105CB | SAN LUIS OBISPO 1105 | 182631105 | TRUE | 3.5111 | 2.9111 | 0.0080792 | 53.3333 | 0.00060803 | 4194 | 0.31181 | 3004 | 0.00016074 | 2908
OCEANO 1102CB | OCEANO 1102 | 182601102 | FALSE | 16.5317 | 2.0226 | 17.4718 | 285.25 | 0.00014798 | 10719 | 1.1519 | 2240 | 0.0001605 | 2909
SEACLIFF 0402CB | SEACLIFF 0402 | 83500402 |  | 0.13845 | 0.017597 |  | 2.8333 | 0.00077417 | 2213 | 0.18704 | 3164 | 0.00015962 | 2910
MARTELL 110198374 | MARTELL 1101 | 163011101 | TRUE | 3.1783 | 0.99949 | 0.10144 | 45 | 0.00062721 | 3981 | 0.2983 | 3023 | 0.00015958 | 2911
WISE 11011404 | WISE 1101 | 152271101 | FALSE | 3.5588 | 0.61791 | 1.3666 | 64 | 0.00038914 | 6583 | 0.55145 | 2780 | 0.00015884 | 2912
IGNACIO 11041290 | IGNACIO 1104 | 42481104 | FALSE | 13.0112 | 2.5217 | 4.396 | 253.5 | 0.00031493 | 7717 | 0.4626 | 2858 | 0.00015879 | 2913
HALF MOON BAY 11036014 | HALF MOON BAY 1103 | 24101103 | FALSE | 12.3568 | 0.64877 | 4.3708 | 237.5 | 0.00029996 | 8019 | 0.54676 | 2784 | 0.00015874 | 2914
PENRYN 11072410 | PENRYN 1107 | 152561107 | FALSE | 7.4885 | 0.69153 | 3.0526 | 125.5 | 0.00028046 | 8409 | 0.59227 | 2745 | 0.00015648 | 2915
SAN LUIS OBISPO 1103153199 | SAN LUIS OBISPO 1103 | 182631103 | FALSE | 5.5408 | 0.28732 | 2.5773 | 105.8333 | 0.00015131 | 10689 | 1.2606 | 2043 | 0.00015635 | 2916
GREEN VALLEY 2101509068 | GREEN VALLEY 2101 | 83192101 | FALSE | 1.7853 | 0.15162 | 1.0551 | 36.5 | 0.0003015 | 7978 | 0.57141 | 2765 | 0.00015601 | 2917
PETALUMA C 1108632 | PETALUMA C 1108 | 42631108 | FALSE | 14.581 | 0.30407 | 14.885 | 283.3333 | 0.00012255 | 10937 | 1.2811 | 2027 | 0.00015562 | 2918
DOLAN ROAD 1101590402 | DOLAN ROAD 1101 | 182381101 | FALSE | 6.0114 | 1.2627 | 2.1172 | 115.5 | 0.00028318 | 8348 | 0.52577 | 2799 | 0.00015534 | 2919
OREGON TRAIL 110346860 | OREGON TRAIL 1103 | 103521103 | FALSE | 3.335 | 0 | 0.7097 | 60.5 | 0.00055264 | 4840 | 0.32452 | 2987 | 0.00015529 | 2920
MIRABEL 1101228 | MIRABEL 1101 | 42091101 | FALSE | 9.7158 | 1.5665 | 2.1439 | 184.5 | 0.0003546 | 7062 | 0.42467 | 2890 | 0.0001549 | 2921
SNEATH LANE 11015311 | SNEATH LANE 1101 | 22721101 |  | 1.1147 | 1.1359 |  | 15 | 0.00066093 | 3563 | 0.2475 | 3084 | 0.00015419 | 2922
CASTRO VALLEY 1108MR337 | CASTRO VALLEY 1108 | 14091108 | FALSE | 19.0705 | 14.1941 | 12.0888 | 313.6667 | 0.00045502 | 5869 | 0.57081 | 2766 | 0.00015384 | 2923
MADISON 2101725408 | MADISON 2101 | 63172101 | FALSE | 1.3085 | 0.044419 | 0.62764 | 18 | 0.00019812 | 10075 | 1.127 | 2272 | 0.0001532 | 2924
HOLLISTER 2105903238 | HOLLISTER 2105 | 182492105 | FALSE | 6.1743 | 0.11402 | 3.9159 | 120.5 | 5.3198e-05 | 11124 | 3.8308 | 1269 | 0.00015285 | 2925
CABRILLO 1103Y10 | CABRILLO 1103 | 183101103 | FALSE | 15.0813 | 7.6594 | 5.1102 | 259.8333 | 0.0003552 | 7051 | 0.59977 | 2735 | 0.00015232 | 2926
FROGTOWN 17027108 | FROGTOWN 1702 | 163451702 | FALSE | 12.9465 | 0.37271 | 9.1673 | 258.5 | 0.00011466 | 10988 | 1.5057 | 1843 | 0.00015218 | 2927
BANGOR 110182350 | BANGOR 1101 | 103191101 | FALSE | 20.6944 | 0.56858 | 19.0509 | 360.5 | 0.00014631 | 10738 | 1.1419 | 2255 | 0.00015217 | 2928
SILVERADO 2105359428 | SILVERADO 2105 | 43432105 | TRUE | 1.0841 | 0.11992 | 0.29747 | 15.5 | 0.00066865 | 3448 | 0.55662 | 2775 | 0.0001519 | 2929
JOLON 11027070 | JOLON 1102 | 182981102 | FALSE | 16.7035 | 0.50394 | 6.2155 | 301.5 | 0.00012781 | 10903 | 1.6451 | 1772 | 0.00015172 | 2930
OCEANO 1104V38 | OCEANO 1104 | 182601104 | FALSE | 17.2991 | 4.288 | 13.1479 | 345.1667 | 0.00025084 | 9061 | 0.73927 | 2613 | 0.00015171 | 2931
BOGARD 1101CB | BOGARD 1101 | 103301101 | TRUE | 0.52532 | 0 | 0.52532 | 10 | 0.0001316 | 10869 | 1.15 | 2248 | 0.00015134 | 2932
BURNEY 110297318 | BURNEY 1102 | 103311102 | TRUE | 1.017 | 0.50959 | 0.27843 | 19.3333 | 0.00029246 | 8158 | 0.37536 | 2943 | 0.00015095 | 2933
ZACA 1102Y48 | ZACA 1102 | 182681102 | FALSE | 11.9106 | 1.0591 | 4.1615 | 208 | 0.00031827 | 7665 | 0.39448 | 2919 | 0.00015092 | 2934
DEL MONTE 210332886 | DEL MONTE 2103 | 182222103 |  | 1.4975 | 0.71522 |  | 25 | 0.00093325 | 1081 | 0.17446 | 3179 | 0.00015086 | 2935
CORRAL 110313474 | CORRAL 1103 | 162991103 | FALSE | 7.2068 | 1.5676 | 2.8596 | 148.5 | 0.00026165 | 8849 | 0.52459 | 2802 | 0.0001508 | 2936
OAKLAND J 1106CR164 | OAKLAND J 1106 | 12091106 | FALSE | 6.5295 | 6.9016 | 2.7278 | 103.8333 | 0.00059557 | 4354 | 0.25601 | 3076 | 0.00015058 | 2937
PEORIA 170176030 | PEORIA 1701 | 163781701 | FALSE | 15.2644 | 0.7635 | 5.0039 | 288.5 | 0.0001779 | 10382 | 0.85107 | 2523 | 0.00015023 | 2938
VIEJO 22032634 | VIEJO 2203 | 182852203 | TRUE | 1.6731 | 2.1842 | 0.071574 | 28 | 0.00078686 | 2081 | 0.20237 | 3140 | 0.0001501 | 2939
WYANDOTTE 11095607 | WYANDOTTE 1109 | 102911109 | FALSE | 6.3892 | 0.33377 | 4.295 | 111.5 | 0.00017441 | 10432 | 0.90879 | 2478 | 0.00014945 | 2940
RALSTON 1101836528 | RALSTON 1101 | 24141101 | FALSE | 2.973 | 2.2067 | 5.094 | 49.5 | 0.00044647 | 5946 | 0.37425 | 2945 | 0.00014911 | 2941
CORRAL 110214026 | CORRAL 1102 | 162991102 | FALSE | 10.3418 | 0.33016 | 10.6719 | 186 | 0.00012938 | 10885 | 1.15 | 2248 | 0.00014879 | 2942
WYANDOTTE 1109758802 | WYANDOTTE 1109 | 102911109 | FALSE | 2.0319 | 0.26232 | 0.69993 | 36 | 0.00034377 | 7244 | 0.59346 | 2744 | 0.00014825 | 2943
SAN RAFAEL 11061230 | SAN RAFAEL 1106 | 42011106 | FALSE | 4.3961 | 2.5953 | 1.0639 | 81.4167 | 0.00066357 | 3518 | 0.31094 | 3008 | 0.00014813 | 2944
RED BLUFF 1104135854 | RED BLUFF 1104 | 103541104 |  | 2.6555 | 0.13873 |  | 51.5 | 0.00026673 | 8725 | 0.63903 | 2695 | 0.00014766 | 2945
COTATI 110361736 | COTATI 1103 | 42271103 | FALSE | 16.6515 | 1.9207 | 11.9428 | 314.5 | 0.00022269 | 9654 | 0.78977 | 2568 | 0.00014706 | 2946
STAFFORD 1101CB | STAFFORD 1101 | 43201101 | FALSE | 12.2219 | 3.1374 | 1.4327 | 206.6667 | 0.00056137 | 4739 | 0.22815 | 3108 | 0.00014677 | 2947
CASTRO VALLEY 1111CB | CASTRO VALLEY 1111 | 14091111 | TRUE | 0.81367 | 0.15683 | 0.24587 | 16.3333 | 0.00041918 | 6232 | 0.48846 | 2834 | 0.0001467 | 2948
STELLING 1111LM10 | STELLING 1111 | 83481111 |  | 2.7306 | 0.92236 |  | 51.5 | 0.00048595 | 5543 | 0.66315 | 2676 | 0.000146 | 2949
PARADISE 11052024 | PARADISE 1105 | 102831105 |  | 0.46719 | 0.10558 |  | 7.5 | 0.00063508 | 3879 | 0.22005 | 3118 | 0.00014564 | 2950
DESCHUTES 1104CB | DESCHUTES 1104 | 103351104 | TRUE | 11.7459 | 2.7676 | 0.039632 | 190 | 0.00042903 | 6129 | 0.44591 | 2870 | 0.00014546 | 2951
PENRYN 1107CB | PENRYN 1107 | 152561107 | FALSE | 16.0353 | 2.3132 | 4.957 | 263.75 | 0.00044564 | 5958 | 0.31168 | 3005 | 0.00014484 | 2952
SUMMIT 110148636 | SUMMIT 1101 | 152591101 | TRUE | 2.7969 | 0.57611 | 0.015292 | 40 | 0.0005952 | 4359 | 0.24721 | 3085 | 0.00014475 | 2953
RESERVATION ROAD 1102303870 | RESERVATION ROAD 1102 | 182731102 | TRUE | 0.65639 | 0 | 0.33925 | 13.5 | 0.00015856 | 10609 | 0.90933 | 2477 | 0.00014467 | 2954
GABILAN 1101460414 | GABILAN 1101 | 182331101 | FALSE | 6.6693 | 0.21281 | 3.789 | 131.5 | 0.0001557 | 10639 | 1.3978 | 1931 | 0.00014462 | 2955
NORTH TOWER 2101CB | NORTH TOWER 2101 | 42042101 | TRUE | 4.4158 | 0.069055 | 0.5884 | 37.2667 | 0.00071396 | 2926 | 0.3192 | 2992 | 0.00014438 | 2956
RALSTON 11029126 | RALSTON 1102 | 24141102 | FALSE | 1.9092 | 1.1503 | 1.8615 | 25 | 0.00049608 | 5434 | 0.27544 | 3048 | 0.00014435 | 2957
CLARKSVILLE 210951744 | CLARKSVILLE 2109 | 153612109 | FALSE | 1.766 | 0.19769 | 0.90669 | 33 | 0.00036932 | 6851 | 0.50507 | 2817 | 0.0001437 | 2958
SAN RAFAEL 11042235 | SAN RAFAEL 1104 | 42011104 | TRUE | 0.86564 | 0.84949 | 0.29803 | 11.5 | 0.00084696 | 1597 | 0.24967 | 3083 | 0.00014313 | 2959
POINT ARENA 11011296 | POINT ARENA 1101 | 43381101 | FALSE | 5.2887 | 0.18745 | 3.0089 | 100.5 | 0.00018154 | 10325 | 0.76896 | 2584 | 0.00014307 | 2960
GOLDTREE 1107CB | GOLDTREE 1107 | 182581107 | FALSE | 3.4895 | 0.16245 | 0.92315 | 65.1667 | 0.00033498 | 7383 | 0.55606 | 2777 | 0.00014305 | 2961
CLOVERDALE 1101CB | CLOVERDALE 1101 | 42821101 |  | 4.0172 | 2.2096 |  | 76.8333 | 0.00053656 | 4993 | 0.25063 | 3081 | 0.00014286 | 2962
HARTLEY 1101658 | HARTLEY 1101 | 43211101 | TRUE | 10.7916 | 2.2709 | 0.3013 | 201.5 | 0.00023459 | 9396 | 1.2093 | 2120 | 0.00014245 | 2963
SAN RAMON 2117CB | SAN RAMON 2117 | 14232117 | TRUE | 1.6712 | 0.12811 | 0.55787 | 16 | 0.00098947 | 835 | 0.23974 | 3094 | 0.00014217 | 2964
SANTA YNEZ 1104117616 | SANTA YNEZ 1104 | 182721104 | TRUE | 0.37179 | 0 | 0.059012 | 5 | 0.00035348 | 7084 | 0.3919 | 2926 | 0.00014214 | 2965
EDES 1112CB | EDES 1112 | 13681112 | TRUE | 1.4151 | 1.4175 | 0.038072 | 27.1667 | 0.0006472 | 3738 | 0.21311 | 3127 | 0.00014206 | 2966
VIEJO 22029488 | VIEJO 2202 | 182852202 | FALSE | 1.2989 | 0.13057 | 0.65051 | 24.5 | 0.00070853 | 3001 | 0.17318 | 3181 | 0.00014197 | 2967
BELL 1108339792 | BELL 1108 | 152701108 | FALSE | 3.5919 | 0.5062 | 2.507 | 63.5 | 0.00022562 | 9594 | 0.69804 | 2648 | 0.00014065 | 2968
LINCOLN 110195756 | LINCOLN 1101 | 153701101 | FALSE | 18.0746 | 1.7374 | 6.5391 | 316.5 | 0.0002269 | 9568 | 0.53378 | 2791 | 0.00014022 | 2969
RIO DEL MAR 0401931192 | RIO DEL MAR 0401 | 83260401 | FALSE | 7.0556 | 3.8689 | 2.6303 | 85.6667 | 0.00059705 | 4340 | 0.19972 | 3143 | 0.00014013 | 2970
LINCOLN 1104275986 | LINCOLN 1104 | 153701104 | FALSE | 0.59634 | 0.044926 | 0.64126 | 12.5 | 0.00015022 | 10705 | 1.02 | 2369 | 0.0001399 | 2971
SOBRANTE 110142914 | SOBRANTE 1101 | 14671101 | TRUE | 2.0166 | 0.78559 | 0.41366 | 33.5 | 0.00070513 | 3041 | 0.26097 | 3065 | 0.00013957 | 2972
OCEANO 1104CB | OCEANO 1104 | 182601104 | FALSE | 11.2251 | 5.6649 | 5.7335 | 208.25 | 0.00043322 | 6082 | 0.43095 | 2881 | 0.00013954 | 2973
JESSUP 1101CB | JESSUP 1101 | 103441101 |  | 3.4619 | 1.3688 |  | 55.5 | 0.00067327 | 3395 | 0.29618 | 3027 | 0.00013917 | 2974
SAN RAFAEL 1107434 | SAN RAFAEL 1107 | 42011107 | TRUE | 1.1418 | 1.0506 | 0.027336 | 18 | 0.00074538 | 2542 | 0.13689 | 3241 | 0.00013908 | 2975
PALMER 110198478 | PALMER 1101 | 183031101 | FALSE | 5.609 | 0.012638 | 5.2982 | 103.5 | 0.00012851 | 10895 | 1.124 | 2275 | 0.00013874 | 2976
MORAGA 1102221914 | MORAGA 1102 | 13801102 | TRUE | 6.6833 | 4.3187 | 0.45029 | 122.6667 | 0.00074771 | 2513 | 0.1805 | 3172 | 0.00013783 | 2977
MORGAN HILL 2110654924 | MORGAN HILL 2110 | 83242110 | FALSE | 4.9943 | 0.73075 | 2.4983 | 100.5 | 0.00021414 | 9797 | 0.61882 | 2714 | 0.0001375 | 2978
PERRY 1101200598 | PERRY 1101 | 183071101 | FALSE | 14.7397 | 0.7076 | 9.2428 | 285.5 | 0.00016806 | 10504 | 0.96449 | 2435 | 0.00013733 | 2979
PHILO 1102920 | PHILO 1102 | 42601102 | FALSE | 26.2926 | 1.0002 | 17.2084 | 507 | 0.00019707 | 10091 | 0.75071 | 2597 | 0.00013724 | 2980
VIEJO 220292792 | VIEJO 2202 | 182852202 | TRUE | 1.4531 | 0.76427 | 0.016405 | 24.5 | 0.00066046 | 3572 | 0.24382 | 3091 | 0.00013722 | 2981
TULUCAY 1101628 | TULUCAY 1101 | 42301101 | FALSE | 8.8213 | 0 | 1.6052 | 164.5 | 0.00024127 | 9264 | 1.0098 | 2379 | 0.00013714 | 2982
FITCH MOUNTAIN 1113154 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 9.1051 | 0.64498 | 1.7307 | 162 | 0.00042422 | 6182 | 0.27603 | 3045 | 0.00013648 | 2983
BIG RIVER 110155402 | BIG RIVER 1101 | 43081101 | FALSE | 10.3108 | 1.3997 | 2.0804 | 186.5 | 0.00033069 | 7438 | 0.38105 | 2939 | 0.00013643 | 2984
PAUL SWEET 2102168368 | PAUL SWEET 2102 | 83252102 | TRUE | 0.71436 | 0 | 0.17911 | 15 | 0.00043737 | 6038 | 0.47377 | 2848 | 0.00013596 | 2985
PUEBLO 2103694 | PUEBLO 2103 | 43292103 |  | 5.6154 | 0.051839 |  | 83.5 | 0.00052045 | 5173 | 0.24027 | 3093 | 0.00013568 | 2986
BIG MEADOWS 21012586 | BIG MEADOWS 2101 | 102812101 | FALSE | 10.9901 | 0.73191 | 6.0247 | 187.5 | 0.00016397 | 10546 | 0.7747 | 2579 | 0.00013567 | 2987
CLARK ROAD 11022044 | CLARK ROAD 1102 | 103091102 | FALSE | 12.5514 | 0.24504 | 8.0539 | 186.5 | 0.00024057 | 9278 | 0.77444 | 2581 | 0.00013554 | 2988
SANTA ROSA A 1104991788 | SANTA ROSA A 1104 | 42151104 | FALSE | 3.415 | 3.0666 | 1.2214 | 51.8333 | 0.00063314 | 3901 | 0.20857 | 3132 | 0.00013521 | 2989
BELL 110880680 | BELL 1108 | 152701108 | TRUE | 1.7796 | 0.29497 | 0.57094 | 28 | 0.0003276 | 7492 | 0.31841 | 2993 | 0.00013488 | 2990
WOODSIDE 11049116 | WOODSIDE 1104 | 24251104 | FALSE | 4.2448 | 3.3951 | 1.0265 | 69.3333 | 0.00056415 | 4716 | 0.2296 | 3106 | 0.00013484 | 2991
MC ARTHUR 11011544 | MC ARTHUR 1101 | 103491101 | FALSE | 28.0418 | 0.83503 | 13.6391 | 518 | 0.00013093 | 10877 | 1.1772 | 2169 | 0.00013478 | 2992
MORRO BAY 1101V70 | MORRO BAY 1101 | 183011101 |  | 0.60744 | 0.32655 |  | 16.8333 | 0.00045869 | 5821 | 0.28322 | 3037 | 0.00013454 | 2993
OLETA 110151740 | OLETA 1101 | 163541101 | FALSE | 21.1833 | 0.27543 | 13.0673 | 385.5 | 0.00014383 | 10759 | 1.1399 | 2258 | 0.00013426 | 2994
HALF MOON BAY 1103CB | HALF MOON BAY 1103 | 24101103 |  | 8.4341 | 4.0544 |  | 141 | 0.00049355 | 5461 | 0.47648 | 2845 | 0.00013423 | 2995
TOCALOMA 0241CB | TOCALOMA 0241 | 43150241 | TRUE | 0.039088 | 0 | 0.039088 | 2 | 9.8086e-05 | 11058 | 1.3679 | 1952 | 0.00013417 | 2996
RESERVATION ROAD 11023032 | RESERVATION ROAD 1102 | 182731102 | FALSE | 10.096 | 0.5983 | 3.7585 | 198 | 0.0002782 | 8466 | 0.46198 | 2860 | 0.00013401 | 2997
SAN RAFAEL 1103CB | SAN RAFAEL 1103 | 42011103 |  | 2.8846 | 0.47817 |  | 41.3333 | 0.00084816 | 1588 | 0.13269 | 3247 | 0.00013386 | 2998
FORT BRAGG A 11021226 | FORT BRAGG A 1102 | 42761102 | FALSE | 7.9211 | 1.6095 | 1.6166 | 140 | 0.00042182 | 6208 | 0.32831 | 2982 | 0.0001336 | 2999
PACIFICA 1103915474 | PACIFICA 1103 | 22811103 | TRUE | 8.5191 | 7.057 | 0.27015 | 134.8333 | 0.00059963 | 4298 | 0.17954 | 3174 | 0.00013351 | 3000
VIEJO 2203573610 | VIEJO 2203 | 182852203 |  | 3.1249 | 3.5524 |  | 47 | 0.00058269 | 4496 | 0.29368 | 3029 | 0.00013347 | 3001
MAGUNDEN 1108250674 | MAGUNDEN 1108 | 252771108 | FALSE | 15.6835 | 0.43214 | 3.983 | 286 | 0.00022618 | 9577 | 1.018 | 2372 | 0.00013336 | 3002
SWIFT 2109XR300 | SWIFT 2109 | 83392109 | TRUE | 0.90151 | 0.13069 | 0.040711 | 16.3333 | 0.00045588 | 5857 | 0.38887 | 2930 | 0.000133 | 3003
PETALUMA C 1109373772 | PETALUMA C 1109 | 42631109 | TRUE | 0.022511 | 0 | 0.022511 | 0.5 | 0.00011544 | 10981 | 1.15 | 2248 | 0.00013276 | 3004
PEABODY 2108CB | PEABODY 2108 | 63642108 |  | 3.166 | 0.15977 |  | 58.3333 | 0.00069882 | 3116 | 0.52076 | 2806 | 0.0001324 | 3005
UKIAH 111472990 | UKIAH 1114 | 42771114 | FALSE | 3.2677 | 0.72272 | 1.0951 | 60 | 0.00038022 | 6692 | 0.29905 | 3021 | 0.00013189 | 3006
MONROE 2103848530 | MONROE 2103 | 43302103 | TRUE | 1.5952 | 0.28971 | 0.44704 | 32.5 | 0.00035661 | 7033 | 0.43008 | 2884 | 0.00013171 | 3007
VIEJO 2204385618 | VIEJO 2204 | 182852204 | TRUE | 4.3232 | 3.5698 | 0.23293 | 59.4167 | 0.000742 | 2584 | 0.17668 | 3176 | 0.00013155 | 3008
SAN LEANDRO U 1109936988 | SAN LEANDRO U 1109 | 13111109 | FALSE | 6.7258 | 7.128 | 13.8538 | 114.8333 | 0.0004733 | 5667 | 0.41246 | 2899 | 0.00013139 | 3009
RIO DELL 110270960 | RIO DELL 1102 | 192251102 | FALSE | 11.7425 | 1.8309 | 4.2014 | 212.5 | 0.00030654 | 7877 | 0.40788 | 2908 | 0.00013131 | 3010
BRUNSWICK 1104CB | BRUNSWICK 1104 | 152481104 | TRUE | 1.8261 | 0.95009 | 0.3968 | 38.4167 | 0.00052914 | 5083 | 0.27088 | 3053 | 0.00013058 | 3011
WILLOW PASS 1101CB | WILLOW PASS 1101 | 13911101 | FALSE | 6.2493 | 2.9944 | 0.68573 | 115 | 0.00068463 | 3279 | 0.20986 | 3131 | 0.0001305 | 3012
HIGGINS 1110CB | HIGGINS 1110 | 152691110 | TRUE | 2.2796 | 0.49969 | 0.032252 | 37.8333 | 0.00069983 | 3101 | 0.35337 | 2961 | 0.00013042 | 3013
LAS GALLINAS A 1106228906 | LAS GALLINAS A 1106 | 42991106 | FALSE | 1.3879 | 1.264 | 0.83213 | 22.8333 | 0.00050626 | 5328 | 0.29857 | 3022 | 0.0001304 | 3014
OLEMA 1101602 | OLEMA 1101 | 42291101 | FALSE | 23.3424 | 0.94089 | 14.9885 | 481 | 0.00013312 | 10854 | 0.84739 | 2526 | 0.00012995 | 3015
IGNACIO 1105318 | IGNACIO 1105 | 42481105 | FALSE | 11.5047 | 9.6861 | 2.9002 | 198.75 | 0.00074462 | 2557 | 0.20106 | 3142 | 0.00012968 | 3016
ATASCADERO 1103A46 | ATASCADERO 1103 | 182541103 | TRUE | 9.3603 | 3.5857 | 0.30272 | 177.5 | 0.00021326 | 9815 | 1.0449 | 2348 | 0.00012913 | 3017
EAST QUINCY 1101951424 | EAST QUINCY 1101 | 102551101 | FALSE | 3.63 | 1.2301 | 0.78169 | 68.5 | 0.0003237 | 7560 | 0.57694 | 2761 | 0.00012873 | 3018
CAMP EVERS 2105CB | CAMP EVERS 2105 | 83622105 |  | 1.6559 | 0.36301 |  | 28.3333 | 0.0010508 | 620 | 0.14197 | 3227 | 0.00012825 | 3019
DUNBAR 1101CB | DUNBAR 1101 | 43071101 |  | 2.5462 | 0.30072 |  | 44.6667 | 0.00076514 | 2325 | 0.14208 | 3225 | 0.00012812 | 3020
WILLITS 11021270 | WILLITS 1102 | 42661102 |  | 1.5358 | 0.74839 |  | 21 | 0.00045353 | 5889 | 0.34351 | 2970 | 0.00012757 | 3021
SPRING GAP 170286032 | SPRING GAP 1702 | 162831702 | FALSE | 2.8954 | 0 | 1.0146 | 59.5 | 0.00020749 | 9919 | 0.41053 | 2902 | 0.0001274 | 3022
JOLON 11027004 | JOLON 1102 | 182981102 | FALSE | 19.9278 | 0.64604 | 5.0033 | 350.5 | 0.00011262 | 10999 | 0.97258 | 2426 | 0.00012735 | 3023
VIEJO 220393964 | VIEJO 2203 | 182852203 |  | 2.5823 | 2.8608 |  | 38.1667 | 0.00093605 | 1069 | 0.1659 | 3188 | 0.00012719 | 3024
OCEANO 1103839302 | OCEANO 1103 | 182601103 | FALSE | 1.0224 | 0 | 1.0224 | 19.5 | 0.00010839 | 11021 | 1.1723 | 2184 | 0.00012708 | 3025
COTATI 110259258 | COTATI 1102 | 42271102 | FALSE | 5.5611 | 1.3129 | 2.5975 | 98.5 | 0.00022939 | 9502 | 0.6995 | 2645 | 0.00012704 | 3026
HARTLEY 1102CB | HARTLEY 1102 | 43211102 | FALSE | 11.7204 | 0.90995 | 3.2555 | 212.5 | 0.00030609 | 7885 | 0.40586 | 2909 | 0.00012687 | 3027
CALISTOGA 1102960240 | CALISTOGA 1102 | 42711102 | TRUE | 0.50721 | 0.040905 | 0.54811 | 11 | 0.00071145 | 2956 | 0.32566 | 2986 | 0.00012657 | 3028
LAS POSITAS 2110MR356 | LAS POSITAS 2110 | 14402110 |  | 0.085373 | 0 |  | 1.1667 | 0.001883 | 36 | 0.067035 | 5974 | 0.00012623 | 3029
EDENVALE 2105469810 | EDENVALE 2105 | 82952105 | TRUE | 5.9058 | 0 | 0.49769 | 126 | 0.0001998 | 10046 | 0.84636 | 2527 | 0.00012622 | 3030
SWIFT 2102889948 | SWIFT 2102 | 83392102 | TRUE | 1.2401 | 0.04881 | 0.39532 | 21.5 | 0.00026545 | 8751 | 0.74087 | 2609 | 0.00012579 | 3031
ASHLAN AVE 2117CB | ASHLAN AVE 2117 | 252052117 |  | 0.019303 | 0 |  | 1 | 0.0023641 | 17 | 0.053073 | 8251 | 0.00012547 | 3032
HICKS 111512494 | HICKS 1115 | 83431115 | TRUE | 2.599 | 1.7378 | 0.11396 | 38.5 | 0.00062379 | 4011 | 0.16704 | 3187 | 0.00012529 | 3033
PEORIA 170575274 | PEORIA 1705 | 163781705 | TRUE | 3.3679 | 1.9728 | 0.34714 | 56.5 | 0.00050858 | 5301 | 0.305 | 3016 | 0.00012505 | 3034
SPRUCE 0402BR304 | SPRUCE 0402 | 13340402 | FALSE | 3.5879 | 4.0221 | 2.9694 | 65.9167 | 0.00058757 | 4450 | 0.17688 | 3175 | 0.00012456 | 3035
HICKS 1116CB | HICKS 1116 | 83431116 | TRUE | 14.2025 | 13.4385 | 0.21178 | 186.15 | 0.00067449 | 3378 | 0.24651 | 3086 | 0.00012452 | 3036
LAS GALLINAS A 1105904 | LAS GALLINAS A 1105 | 42991105 | FALSE | 7.1998 | 7.3279 | 1.8428 | 111 | 0.00057481 | 4594 | 0.26241 | 3061 | 0.00012408 | 3037
BELLEVUE 2103648 | BELLEVUE 2103 | 43182103 | FALSE | 16.2895 | 1.0386 | 3.416 | 298.5 | 0.00032884 | 7472 | 0.64897 | 2683 | 0.00012353 | 3038
SAN BRUNO 0402CB | SAN BRUNO 0402 | 22700402 |  | 1.4764 | 0.80798 |  | 19.4167 | 0.00064097 | 3813 | 0.13781 | 3240 | 0.00012342 | 3039
HIGGINS 1110197930 | HIGGINS 1110 | 152691110 | FALSE | 3.9381 | 2.3651 | 1.2628 | 69.5 | 0.00061279 | 4133 | 0.23519 | 3100 | 0.00012297 | 3040
SAN RAFAEL 1104CB | SAN RAFAEL 1104 | 42011104 | TRUE | 2.4418 | 1.7956 | 0.10993 | 34 | 0.00085189 | 1563 | 0.16182 | 3192 | 0.00012238 | 3041
CAYETANO 2109CB | CAYETANO 2109 | 14422109 | TRUE | 5.4915 | 0.34373 | 0.10194 | 96.5 | 0.00049386 | 5458 | 0.38354 | 2936 | 0.00012236 | 3042
CABRILLO 1104Y22 | CABRILLO 1104 | 183101104 | FALSE | 25.2948 | 1.2935 | 9.6017 | 470 | 0.0002861 | 8286 | 0.54657 | 2785 | 0.00012223 | 3043
CARLOTTA 112142896 | CARLOTTA 1121 | 192291121 | FALSE | 5.4465 | 0.89175 | 2.5741 | 99 | 0.00032902 | 7470 | 0.33332 | 2976 | 0.00012203 | 3044
BELLEVUE 2103478 | BELLEVUE 2103 | 43182103 | FALSE | 19.926 | 1.9028 | 4.054 | 359.5 | 0.00027876 | 8450 | 0.73943 | 2612 | 0.00012124 | 3045
SANTA ROSA A 1111114 | SANTA ROSA A 1111 | 42151111 | TRUE | 3.1407 | 1.1478 | 0.071396 | 49.8333 | 0.00064719 | 3739 | 0.52066 | 2807 | 0.0001212 | 3046
ATASCADERO 1102A88 | ATASCADERO 1102 | 182541102 | FALSE | 2.7117 | 0.27463 | 0.98417 | 55.5 | 0.00028706 | 8254 | 0.58295 | 2754 | 0.00012103 | 3047
MC ARTHUR 1101501106 | MC ARTHUR 1101 | 103491101 | FALSE | 10.3726 | 0.29308 | 9.7084 | 182.5 | 0.00011123 | 11010 | 1.1361 | 2263 | 0.00012093 | 3048
DUNBAR 1101725292 | DUNBAR 1101 | 43071101 | TRUE | 0.94443 | 0.54639 | 0.25223 | 18.5 | 0.00061772 | 4076 | 0.27967 | 3041 | 0.00012048 | 3049
SALMON CREEK 1101194 | SALMON CREEK 1101 | 43161101 | FALSE | 8.5297 | 0.81937 | 2.2917 | 155 | 0.00021972 | 9704 | 1.0437 | 2349 | 0.00012038 | 3050
GONZALES 11013094 | GONZALES 1101 | 182131101 | FALSE | 9.1163 | 0.44501 | 4.0139 | 188.8333 | 0.00020332 | 9990 | 1.2096 | 2119 | 0.00012038 | 3051
VALLEY VIEW 1103CB | VALLEY VIEW 1103 | 14341103 | TRUE | 6.511 | 6.0752 | 0.2353 | 97.1667 | 0.00078667 | 2085 | 0.15001 | 3204 | 0.00012008 | 3052
MORAGA 1105116034 | MORAGA 1105 | 13801105 | TRUE | 3.0889 | 1.2877 | 0.24716 | 40.3333 | 0.00059038 | 4409 | 0.2151 | 3125 | 0.00011981 | 3053
BRENTWOOD 2105500796 | BRENTWOOD 2105 | 14592105 | FALSE | 5.5574 | 0.14923 | 1.2711 | 104.5 | 7.7036e-05 | 11113 | 1.7025 | 1741 | 0.00011978 | 3054
LINCOLN 11042070 | LINCOLN 1104 | 153701104 | FALSE | 29.9947 | 1.8837 | 17.997 | 533 | 0.00016447 | 10538 | 0.74052 | 2610 | 0.00011911 | 3055
PETALUMA C 1108630 | PETALUMA C 1108 | 42631108 | FALSE | 4.2867 | 0.97152 | 1.6871 | 81 | 0.00030346 | 7940 | 0.33213 | 2980 | 0.00011894 | 3056
SAUSALITO 11022033 | SAUSALITO 1102 | 42491102 | TRUE | 0.8509 | 0.64936 | 0.014905 | 9.5 | 0.00070656 | 3022 | 0.21298 | 3128 | 0.00011881 | 3057
ANDERSON 11031600 | ANDERSON 1103 | 103261103 | FALSE | 10.7218 | 0.72755 | 3.5476 | 204 | 0.00018495 | 10277 | 0.75634 | 2592 | 0.00011858 | 3058
STAFFORD 11021258 | STAFFORD 1102 | 43201102 | TRUE | 4.896 | 3.9347 | 0.18472 | 92 | 0.00063055 | 3934 | 0.28301 | 3038 | 0.00011856 | 3059
SAN RAFAEL 1105645362 | SAN RAFAEL 1105 | 42011105 | FALSE | 2.9486 | 3.2096 | 1.3555 | 46 | 0.00046817 | 5712 | 0.23925 | 3095 | 0.00011851 | 3060
SAN RAFAEL 110168970 | SAN RAFAEL 1101 | 42011101 | TRUE | 3.2713 | 2.6139 | 0.11231 | 47.6667 | 0.001028 | 698 | 0.11494 | 3280 | 0.00011851 | 3061
JAMESON 11028842 | JAMESON 1102 | 63801102 |  | 3.003 | 0.23676 |  | 58 | 0.00043728 | 6039 | 0.37912 | 2940 | 0.0001185 | 3062
ALTO 1124CB | ALTO 1124 | 42031124 | TRUE | 4.2038 | 3.5445 | 0.14745 | 65.1667 | 0.00074986 | 2483 | 0.14758 | 3211 | 0.00011849 | 3063
CALPELLA 1102CB | CALPELLA 1102 | 43411102 | TRUE | 5.6604 | 0.62888 | 0.20064 | 102 | 0.0004534 | 5891 | 0.38942 | 2929 | 0.00011789 | 3064
DESCHUTES 11049718 | DESCHUTES 1104 | 103351104 | FALSE | 33.8645 | 1.6186 | 15.1425 | 598.5 | 0.00019142 | 10189 | 0.70743 | 2635 | 0.00011784 | 3065
MESA 1101M86 | MESA 1101 | 182821101 | FALSE | 20.6591 | 1.473 | 11.5718 | 381.5 | 0.00015317 | 10666 | 0.87554 | 2502 | 0.00011774 | 3066
MOLINO 1102344 | MOLINO 1102 | 42571102 | FALSE | 6.0096 | 0.73992 | 1.12 | 113 | 0.00034346 | 7250 | 0.31619 | 2998 | 0.00011741 | 3067
PLACER 1101CB | PLACER 1101 | 152461101 |  | 4.1886 | 2.5668 |  | 68.8333 | 0.0010784 | 535 | 0.11564 | 3276 | 0.00011731 | 3068
HATTON 1101399900 | HATTON 1101 | 182291101 | TRUE | 2.4178 | 0.55817 | 0.51831 | 40.5 | 0.00043284 | 6085 | 0.30689 | 3012 | 0.00011671 | 3069
CAROLANDS 040484797 | CAROLANDS 0404 | 24060404 | TRUE | 1.3861 | 0.36282 | 0.020624 | 16.4167 | 0.00076058 | 2374 | 0.13313 | 3246 | 0.00011668 | 3070
DEL MONTE 210386496 | DEL MONTE 2103 | 182222103 | FALSE | 6.5086 | 3.7512 | 1.6071 | 105.9167 | 0.00072685 | 2764 | 0.2265 | 3109 | 0.00011545 | 3071
MORRO BAY 1101V66 | MORRO BAY 1101 | 183011101 | FALSE | 16.1759 | 1.5729 | 3.6335 | 326.5 | 0.0001964 | 10102 | 0.79718 | 2561 | 0.00011522 | 3072
CAYETANO 2111CB | CAYETANO 2111 | 14422111 | TRUE | 11.7595 | 0.85839 | 0.029509 | 189.5 | 0.00035266 | 7093 | 0.67195 | 2667 | 0.00011519 | 3073
PASO ROBLES 1107CB | PASO ROBLES 1107 | 182611107 |  | 14.1392 | 1.1161 |  | 255 | 0.00029008 | 8196 | 1.083 | 2319 | 0.00011505 | 3074
NARROWS 210276952 | NARROWS 2102 | 153132102 | FALSE | 11.3027 | 0.55945 | 2.2968 | 190 | 0.00054895 | 4871 | 0.31469 | 3001 | 0.00011451 | 3075
SAN LUIS OBISPO 1104777686 | SAN LUIS OBISPO 1104 | 182631104 | FALSE | 1.9047 | 0.019856 | 1.5451 | 38 | 0.00013575 | 10834 | 0.95888 | 2439 | 0.00011451 | 3076
HARRIS 1109700 | HARRIS 1109 | 192431109 |  | 12.6237 | 2.5573 |  | 227 | 0.00057781 | 4553 | 0.21969 | 3119 | 0.00011429 | 3077
STAGG 21056410 | STAGG 2105 | 162422105 |  | 0.011364 | 0 |  | 0.5 | 0.0021461 | 23 | 0.053073 | 8251 | 0.0001139 | 3078
DIAMOND SPRINGS 110650324 | DIAMOND SPRINGS 1106 | 152261106 |  | 1.5859 | 0.2023 |  | 26.5 | 0.00087198 | 1408 | 0.12845 | 3249 | 0.00011364 | 3079
MOLINO 1101152 | MOLINO 1101 | 42571101 | FALSE | 10.3047 | 2.1512 | 2.2474 | 188.5 | 0.00036489 | 6920 | 0.24517 | 3088 | 0.0001136 | 3080
SAN MIGUEL 1106N34 | SAN MIGUEL 1106 | 182661106 | FALSE | 13.7265 | 0.7432 | 2.6342 | 254 | 0.00020656 | 9940 | 0.40491 | 2910 | 0.00011345 | 3081
VACA DIXON 110118292 | VACA DIXON 1101 | 63591101 | FALSE | 5.8416 | 0.44662 | 0.81277 | 109.5 | 0.00029181 | 8170 | 0.68277 | 2656 | 0.0001132 | 3082
MOLINO 110279306 | MOLINO 1102 | 42571102 | FALSE | 8.1986 | 0.58433 | 3.5337 | 159.5 | 0.00021509 | 9774 | 0.49236 | 2831 | 0.00011309 | 3083
PENRYN 11072704 | PENRYN 1107 | 152561107 | FALSE | 5.7114 | 0.97935 | 1.2359 | 102.5 | 0.00041739 | 6249 | 0.28125 | 3039 | 0.00011301 | 3084
LAKEWOOD 2109432198 | LAKEWOOD 2109 | 13532109 | TRUE | 2.393 | 0.65101 | 0.56907 | 46 | 0.00042197 | 6204 | 0.26713 | 3057 | 0.00011288 | 3085
CLAYTON 2213CB | CLAYTON 2213 | 12022213 | TRUE | 2.3573 | 1.0756 | 0.026667 | 39.3667 | 0.00092838 | 1105 | 0.1744 | 3180 | 0.00011256 | 3086
JESSUP 11019002 | JESSUP 1101 | 103441101 | FALSE | 6.1225 | 0.82582 | 0.97931 | 111.8333 | 0.00052588 | 5112 | 0.18909 | 3160 | 0.00011241 | 3087
SWIFT 2107XR526 | SWIFT 2107 | 83392107 | FALSE | 5.3422 | 0.40604 | 1.9535 | 103.5 | 0.00024429 | 9195 | 0.53145 | 2794 | 0.0001123 | 3088
JARVIS 1111MR121 | JARVIS 1111 | 13501111 |  | 3.3301 | 2.0967 |  | 56.5 | 0.00046988 | 5701 | 0.30308 | 3018 | 0.00011173 | 3089
PANORAMA 1102508502 | PANORAMA 1102 | 103461102 | FALSE | 16.0873 | 0.50227 | 11.5589 | 301 | 0.00014866 | 10714 | 0.90394 | 2482 | 0.00011164 | 3090
BELMONT 11103975 | BELMONT 1110 | 24031110 |  | 1.5304 | 0.99389 |  | 22 | 0.00046091 | 5799 | 0.30593 | 3013 | 0.00011137 | 3091
WEST FRESNO 110875144 | WEST FRESNO 1108 | 253731108 |  | 0.019339 | 0 |  | 0.33333 | 0.0020981 | 26 | 0.053073 | 8251 | 0.00011135 | 3092
CALPELLA 1102379946 | CALPELLA 1102 | 43411102 | TRUE | 1.8358 | 0.16247 | 0.25975 | 35.5 | 0.00045969 | 5809 | 0.27465 | 3049 | 0.00011117 | 3093
RIO DELL 11027124 | RIO DELL 1102 | 192251102 | TRUE | 0.57385 | 0 | 0.57384 | 14 | 8.0226e-05 | 11104 | 1.3951 | 1933 | 0.00011102 | 3094
HILLSDALE 0405CB | HILLSDALE 0405 | 24110405 |  | 0.042186 | 0 |  | 0.33333 | 0.0016458 | 66 | 0.067 | 6056 | 0.00011027 | 3095
UKIAH 1114943840 | UKIAH 1114 | 42771114 | TRUE | 3.5412 | 1.2137 | 0.55568 | 54.5 | 0.00043355 | 6077 | 0.24498 | 3089 | 0.00010992 | 3096
FITCH MOUNTAIN 111349826 | FITCH MOUNTAIN 1113 | 42751113 | TRUE | 3.0428 | 0.1955 | 0.23738 | 49 | 0.00060952 | 4176 | 0.20292 | 3139 | 0.00010983 | 3097
LINCOLN 1104997576 | LINCOLN 1104 | 153701104 | FALSE | 15.9865 | 0.40529 | 9.9325 | 293.5 | 0.0001516 | 10681 | 0.72434 | 2623 | 0.00010977 | 3098
LAS PULGAS 0401CB | LAS PULGAS 0401 | 24120401 | FALSE | 8.0911 | 6.7554 | 2.6149 | 114.8333 | 0.00066598 | 3482 | 0.19643 | 3150 | 0.0001095 | 3099
DIAMOND SPRINGS 1106CB | DIAMOND SPRINGS 1106 | 152261106 |  | 2.2887 | 0.6502 |  | 37.8333 | 0.0005334 | 5036 | 0.23903 | 3096 | 0.0001094 | 3100
DESCHUTES 11041582 | DESCHUTES 1104 | 103351104 | FALSE | 15.0026 | 1.2125 | 5.382 | 268 | 0.00025799 | 8924 | 0.50077 | 2820 | 0.0001094 | 3101
CAMP EVERS 210392582 | CAMP EVERS 2103 | 83622103 | TRUE | 2.8055 | 1.5393 | 0.052245 | 43 | 0.0010034 | 782 | 0.075869 | 4239 | 0.00010923 | 3102
POSO MOUNTAIN 21011703 | POSO MOUNTAIN 2101 | 253642101 | FALSE | 2.3714 | 0 | 0.72455 | 39.5 | 0.00016147 | 10581 | 0.54679 | 2783 | 0.00010903 | 3103
TYLER 1105816852 | TYLER 1105 | 103571105 | FALSE | 43.3794 | 2.8687 | 12.097 | 770.5 | 0.0001676 | 10511 | 0.67073 | 2669 | 0.00010897 | 3104
LLAGAS 21014523 | LLAGAS 2101 | 83182101 | FALSE | 2.744 | 0.40162 | 0.96253 | 57.5 | 0.00027314 | 8581 | 0.37643 | 2942 | 0.00010852 | 3105
SAN BENITO 210136912 | SAN BENITO 2101 | 182742101 |  | 10.6243 | 0.91795 |  | 194.25 | 0.000201 | 10026 | 1.1206 | 2278 | 0.00010847 | 3106
SAN LUIS OBISPO 1101592368 | SAN LUIS OBISPO 1101 | 182631101 |  | 4.5859 | 3.6964 |  | 70 | 0.00065692 | 3614 | 0.14386 | 3221 | 0.00010811 | 3107
FITCH MOUNTAIN 1111752596 | FITCH MOUNTAIN 1111 | 42751111 | TRUE | 0.65989 | 0 | 0.060322 | 13.5 | 0.00031144 | 7778 | 0.46811 | 2853 | 0.00010786 | 3108
TEJON 1103286542 | TEJON 1103 | 252931103 | FALSE | 6.2382 | 0 | 2.9637 | 106.5 | 0.00011949 | 10956 | 0.94426 | 2454 | 0.00010782 | 3109
RALSTON 11021601 | RALSTON 1102 | 24141102 |  | 2.2124 | 1.6992 |  | 27.5 | 0.00040515 | 6395 | 0.2591 | 3071 | 0.00010728 | 3110
EL CERRITO G 1112CB | EL CERRITO G 1112 | 12501112 |  | 6.6088 | 5.3068 |  | 76.9 | 0.00060148 | 4282 | 0.19698 | 3149 | 0.00010722 | 3111
CLAY 11031230 | CLAY 1103 | 163341103 | FALSE | 3.3179 | 0 | 1.0225 | 59.5 | 0.00027003 | 8654 | 0.56118 | 2770 | 0.00010644 | 3112
PENRYN 1105168616 | PENRYN 1105 | 152561105 | FALSE | 8.4645 | 1.3599 | 3.1714 | 155.5 | 0.00025243 | 9034 | 0.49646 | 2825 | 0.00010613 | 3113
SAN ARDO 1101610148 | SAN ARDO 1101 | 182191101 | FALSE | 12.4032 | 0.24025 | 1.1186 | 222 | 0.00010213 | 11043 | 2.112 | 1603 | 0.00010548 | 3114
RED BLUFF 110585632 | RED BLUFF 1105 | 103541105 |  | 0.72307 | 0.06336 |  | 12 | 0.00050127 | 5383 | 0.20237 | 3140 | 0.00010543 | 3115
OAKLAND J 1102CR252 | OAKLAND J 1102 | 12091102 | FALSE | 5.9912 | 6.0246 | 1.0486 | 87.9167 | 0.00066384 | 3514 | 0.16536 | 3189 | 0.00010526 | 3116
SOLEDAD 2105315500 | SOLEDAD 2105 | 182052105 | FALSE | 3.463 | 0.12319 | 0.9619 | 63 | 0.00032037 | 7623 | 0.42949 | 2885 | 0.00010525 | 3117
NORTH BRANCH 1101750010 | NORTH BRANCH 1101 | 163231101 | TRUE | 0.75687 | 0.28673 | 0.19444 | 16 | 0.0004068 | 6371 | 0.27071 | 3054 | 0.00010508 | 3118
ELK 1101900 | ELK 1101 | 42981101 | FALSE | 21.2971 | 0.97991 | 7.4914 | 386 | 0.00018577 | 10265 | 0.64064 | 2691 | 0.00010496 | 3119
OROSI 1102617446 | OROSI 1102 | 252841102 |  | 1.6178 | 0.045978 |  | 27.5 | 0.00012396 | 10930 | 1.2053 | 2129 | 0.00010464 | 3120
NEWBURG 1131CB | NEWBURG 1131 | 192151131 | TRUE | 12.5335 | 4.2175 | 0.015116 | 225.3333 | 0.0003447 | 7226 | 0.35952 | 2955 | 0.00010414 | 3121
BROWNS VALLEY 110193870 | BROWNS VALLEY 1101 | 152921101 | FALSE | 36.397 | 1.0735 | 18.2934 | 642.5 | 0.00014493 | 10748 | 0.6623 | 2679 | 0.00010395 | 3122
SONOMA 1107844168 | SONOMA 1107 | 42721107 | FALSE | 11.593 | 0.43164 | 3.7101 | 232.5 | 0.00028556 | 8295 | 0.47266 | 2850 | 0.00010367 | 3123
STOCKDALE 21074163 | STOCKDALE 2107 | 254072107 |  | 0.019385 | 0 |  | 1 | 0.0019496 | 30 | 0.053073 | 8251 | 0.00010347 | 3124
FOOTHILL 1101CB | FOOTHILL 1101 | 182951101 | FALSE | 21.7709 | 0.87758 | 11.8452 | 433.5 | 0.00016961 | 10490 | 0.93366 | 2461 | 0.00010286 | 3125
ROB ROY 210512584 | ROB ROY 2105 | 83692105 | FALSE | 25.8402 | 5.9974 | 3.713 | 480 | 0.00048965 | 5499 | 0.18791 | 3161 | 0.0001022 | 3126
PENRYN 11072706 | PENRYN 1107 | 152561107 | FALSE | 14.9392 | 1.4862 | 5.1928 | 256 | 0.00034586 | 7207 | 0.32591 | 2985 | 0.00010218 | 3127
TAFT 1102CB | TAFT 1102 | 252081102 |  | 0.046798 | 0 |  | 0.41667 | 0.0015192 | 104 | 0.067063 | 5934 | 0.0001019 | 3128
BELL 111050522 | BELL 1110 | 152701110 |  | 0.020459 | 0 |  | 0.5 | 0.0015204 | 103 | 0.067 | 6057 | 0.00010187 | 3129
SAN LUIS OBISPO 1102597518 | SAN LUIS OBISPO 1102 | 182631102 | TRUE | 2.2551 | 0.83378 | 0.03003 | 45.5 | 0.00061696 | 4087 | 0.17135 | 3184 | 0.00010148 | 3130
SNEATH LANE 1102CB | SNEATH LANE 1102 | 22721102 | FALSE | 2.5286 | 2.2401 | 1.9093 | 37.5833 | 0.00096137 | 953 | 0.091155 | 3338 | 0.00010125 | 3131
CALISTOGA 1102270153 | CALISTOGA 1102 | 42711102 |  | 0.011545 | 0 |  | 0.5 | 0.0012408 | 246 | 0.08151 | 3383 | 0.00010113 | 3132
BELL 1109CB | BELL 1109 | 152701109 | TRUE | 3.4729 | 0.62962 | 0.028173 | 61.25 | 0.00079319 | 2030 | 0.15506 | 3196 | 0.00010108 | 3133
NAPA 1102561208 | NAPA 1102 | 42021102 | TRUE | 2.7983 | 0.03837 | 0.29497 | 58.5 | 0.00016782 | 10508 | 0.86418 | 2514 | 0.00010105 | 3134
MERCED FALLS 110222774 | MERCED FALLS 1102 | 252811102 | FALSE | 3.7916 | 0.068571 | 1.3564 | 66.5 | 0.00017082 | 10476 | 0.75324 | 2593 | 0.00010104 | 3135
GREEN VALLEY 2101380922 | GREEN VALLEY 2101 | 83192101 | FALSE | 2.7177 | 0.29797 | 0.79339 | 53.5 | 0.00030418 | 7928 | 0.30992 | 3009 | 0.00010083 | 3136
BURNEY 11012402 | BURNEY 1101 | 103311101 | FALSE | 3.7382 | 0 | 1.4129 | 64.6667 | 0.00017187 | 10459 | 0.36936 | 2949 | 0.00010065 | 3137
ARCATA 112233060 | ARCATA 1122 | 192021122 |  | 4.9332 | 1.4925 |  | 90.5 | 0.00047415 | 5657 | 0.18736 | 3162 | 0.00010039 | 3138
GREENBRAE 1102CB | GREENBRAE 1102 | 43091102 | TRUE | 2.1444 | 1.5046 | 0.033233 | 32.5 | 0.00079013 | 2060 | 0.12801 | 3252 | 0.00010026 | 3139
AUBURN 1102251946 | AUBURN 1102 | 152161102 | FALSE | 5.0003 | 3.1883 | 2.1812 | 78 | 0.00068348 | 3289 | 0.2644 | 3060 | 9.9913e-05 | 3140
FAIRVIEW 2207P148 | FAIRVIEW 2207 | 13432207 | FALSE | 4.5534 | 4.5435 | 0.97171 | 56.5 | 0.00055677 | 4795 | 0.26224 | 3062 | 9.9908e-05 | 3141
PINEDALE 2105CB | PINEDALE 2105 | 252852105 |  | 0.64484 | 0.031639 |  | 9.5 | 0.0018765 | 37 | 0.053073 | 8251 | 9.9589e-05 | 3142
SOLEDAD 2101823854 | SOLEDAD 2101 | 182052101 | FALSE | 4.4115 | 0.17918 | 1.7799 | 72 | 0.0003684 | 6865 | 0.48565 | 2838 | 9.8906e-05 | 3143
MOLINO 1104368158 | MOLINO 1104 | 42571104 | FALSE | 8.6852 | 1.2608 | 2.667 | 161.5 | 0.00026858 | 8683 | 0.44417 | 2873 | 9.8828e-05 | 3144
FULTON 1102CB | FULTON 1102 | 42561102 | TRUE | 3.9509 | 1.0106 | 0.05277 | 72.1667 | 0.00070806 | 3007 | 0.14036 | 3232 | 9.8811e-05 | 3145
COTTONWOOD 11011510 | COTTONWOOD 1101 | 102931101 | TRUE | 3.3029 | 0.14039 | 0.32034 | 55.1667 | 0.00032696 | 7507 | 0.25896 | 3072 | 9.8455e-05 | 3146
GEYSERVILLE 1101354 | GEYSERVILLE 1101 | 42891101 | TRUE | 8.3047 | 1.5561 | 0.20289 | 159.1667 | 0.00037066 | 6832 | 0.31194 | 3003 | 9.84e-05 | 3147
RANCHERS COTTON 1000CB | RANCHERS COTTON 1000 | 254801000 |  | 0.0060208 | 0 |  | 0.5 | 0.0018529 | 39 | 0.053073 | 8251 | 9.8339e-05 | 3148
CABRILLO 11031437 | CABRILLO 1103 | 183101103 | FALSE | 4.661 | 0.21276 | 2.6111 | 81.5 | 0.00021968 | 9706 | 0.6287 | 2704 | 9.7837e-05 | 3149
PUTAH CREEK 1105617260 | PUTAH CREEK 1105 | 63681105 | FALSE | 2.7957 | 0.020082 | 1.0961 | 49.5 | 0.00012914 | 10888 | 1.5061 | 1842 | 9.7771e-05 | 3150
HATTON 110240461 | HATTON 1102 | 182291102 |  | 2.7777 | 2.3133 |  | 47.5 | 0.00065136 | 3692 | 0.1531 | 3199 | 9.7617e-05 | 3151
VINEYARD 2107MR332 | VINEYARD 2107 | 14502107 | TRUE | 2.9674 | 0.36284 | 0.23477 | 56 | 0.00050199 | 5371 | 0.43024 | 2883 | 9.6488e-05 | 3152
FULTON 1107126742 | FULTON 1107 | 42561107 | TRUE | 1.8725 | 0.22808 | 0.41328 | 32 | 0.00051696 | 5206 | 0.20447 | 3138 | 9.6096e-05 | 3153
MILPITAS 2113CB | MILPITAS 2113 | 82832113 |  | 0.1151 | 0 |  | 4.5833 | 0.0018031 | 43 | 0.053073 | 8251 | 9.5695e-05 | 3154
FULTON 11024994 | FULTON 1102 | 42561102 | FALSE | 4.3003 | 0.28976 | 1.1971 | 74 | 0.00049898 | 5400 | 0.18451 | 3170 | 9.5666e-05 | 3155
LLAGAS 2104XR294 | LLAGAS 2104 | 83182104 |  | 5.4741 | 0.56876 |  | 100.5 | 0.00046569 | 5742 | 0.32428 | 2988 | 9.5456e-05 | 3156
CALPELLA 1102421412 | CALPELLA 1102 | 43411102 | FALSE | 3.6729 | 0.14177 | 0.75281 | 65.5 | 0.00035969 | 6987 | 0.26557 | 3058 | 9.5255e-05 | 3157
LAMONT 11024222 | LAMONT 1102 | 253911102 | FALSE | 16.2507 | 0.42799 | 3.2201 | 286 | 0.00022968 | 9495 | 0.79171 | 2565 | 9.4775e-05 | 3158
FITCH MOUNTAIN 1111821431 | FITCH MOUNTAIN 1111 | 42751111 |  | 1.0575 | 0.042757 |  | 23.5 | 0.00039185 | 6544 | 0.29743 | 3025 | 9.4709e-05 | 3159
ROB ROY 210410930 | ROB ROY 2104 | 83692104 | FALSE | 11.3427 | 4.1067 | 1.194 | 209 | 0.00051814 | 5193 | 0.19888 | 3146 | 9.4634e-05 | 3160
OLEMA 110175686 | OLEMA 1101 | 42291101 | FALSE | 5.155 | 0 | 4.3448 | 107 | 9.2868e-05 | 11074 | 1.2127 | 2112 | 9.4249e-05 | 3161
LLAGAS 2107CB | LLAGAS 2107 | 83182107 |  | 3.0518 | 0.76246 |  | 42.5 | 0.00085341 | 1552 | 0.11921 | 3268 | 9.4232e-05 | 3162
ROSSMOOR 110479146 | ROSSMOOR 1104 | 14161104 | TRUE | 1.9394 | 0.93661 | 0.052133 | 29.8333 | 0.00060713 | 4212 | 0.14749 | 3212 | 9.3112e-05 | 3163
PINEDALE 2111CB | PINEDALE 2111 | 252852111 |  | 0.74948 | 0.22339 |  | 11.1667 | 0.0017539 | 45 | 0.053073 | 8251 | 9.3086e-05 | 3164
WILLITS 1103696 | WILLITS 1103 | 42661103 | FALSE | 9.0976 | 0.66979 | 5.2623 | 162.5 | 0.00015402 | 10658 | 0.55152 | 2779 | 9.301e-05 | 3165
MORRO BAY 1102W34 | MORRO BAY 1102 | 183011102 | FALSE | 9.5706 | 1.6205 | 8.0081 | 172.5 | 0.00013653 | 10825 | 0.73239 | 2617 | 9.2705e-05 | 3166
CALIFORNIA AVE 110446974 | CALIFORNIA AVE 1104 | 252281104 |  | 1.0957 | 0.6403 |  | 17 | 0.001736 | 49 | 0.053073 | 8251 | 9.2134e-05 | 3167
COTATI 1105104502 | COTATI 1105 | 42271105 | FALSE | 5.4124 | 0.635 | 2.3489 | 101 | 0.00017626 | 10406 | 0.49248 | 2828 | 9.1995e-05 | 3168
MC ARTHUR 1102542920 | MC ARTHUR 1102 | 103491102 | FALSE | 1.4692 | 0.028384 | 1.0154 | 25.5 | 0.00014873 | 10713 | 0.74653 | 2600 | 9.1952e-05 | 3169
PACIFICA 1103CB | PACIFICA 1103 | 22811103 | TRUE | 4.9258 | 4.5164 | 0.069669 | 94.6667 | 0.00074365 | 2570 | 0.10718 | 3298 | 9.1833e-05 | 3170
CHESTER 1102CB | CHESTER 1102 | 103181102 | TRUE | 2.7871 | 1.0267 | 0.018498 | 46 | 0.0004004 | 6451 | 0.23307 | 3103 | 9.1761e-05 | 3171
CLAY 11037142 | CLAY 1103 | 163341103 | FALSE | 15.5763 | 0.41673 | 3.4619 | 298 | 0.00022355 | 9636 | 0.29644 | 3026 | 9.173e-05 | 3172
KIRKER 2106P525R | KIRKER 2106 | 14452106 |  | 0.54086 | 0.21547 |  | 7.6667 | 0.0015331 | 97 | 0.059734 | 7047 | 9.1696e-05 | 3173
WOODWARD 2102CB | WOODWARD 2102 | 255292102 |  | 0.23029 | 0 |  | 2 | 0.0017234 | 51 | 0.053073 | 8251 | 9.1464e-05 | 3174
MESA 1101CB | MESA 1101 | 182821101 | FALSE | 25.5204 | 4.4145 | 12.5613 | 454.5 | 0.0001626 | 10567 | 0.74089 | 2608 | 9.1429e-05 | 3175
STOCKDALE 2111CB | STOCKDALE 2111 | 254072111 |  | 0.0092799 | 0 |  | 0.5 | 0.0017168 | 52 | 0.053073 | 8251 | 9.1118e-05 | 3176
MIRABEL 1102CB | MIRABEL 1102 | 42091102 | TRUE | 6.6977 | 2.6123 | 0.19875 | 111.5 | 0.00063409 | 3889 | 0.11704 | 3273 | 9.1022e-05 | 3177
ROSSMOOR 1106L541R | ROSSMOOR 1106 | 14161106 |  | 0.60624 | 0.46761 |  | 12.5 | 0.00064341 | 3784 | 0.1464 | 3215 | 9.0988e-05 | 3178
CAYETANO 2109MR186 | CAYETANO 2109 | 14422109 | TRUE | 2.5528 | 0.060292 | 0.33589 | 49 | 0.000184 | 10291 | 0.47489 | 2847 | 9.0578e-05 | 3179
EDENVALE 2105739448 | EDENVALE 2105 | 82952105 | FALSE | 2.3438 | 0 | 1.5219 | 46.5 | 0.00014822 | 10716 | 0.82818 | 2538 | 9.0565e-05 | 3180
FITCH MOUNTAIN 1113443164 | FITCH MOUNTAIN 1113 | 42751113 | FALSE | 9.3731 | 1.432 | 2.7132 | 173 | 0.00029518 | 8104 | 0.31121 | 3007 | 9.0363e-05 | 3181
RICHMOND R 1120BR328 | RICHMOND R 1120 | 13471120 |  | 0.016647 | 0 |  | 0.25 | 0.0017021 | 54 | 0.053073 | 8251 | 9.0335e-05 | 3182
STOCKDALE 2113CB | STOCKDALE 2113 | 254072113 |  | 0.29074 | 0.0095308 |  | 4.5 | 0.001697 | 55 | 0.053073 | 8251 | 9.0067e-05 | 3183
PINEDALE 210541238 | PINEDALE 2105 | 252852105 |  | 1.1123 | 0 |  | 23.5 | 0.0016958 | 56 | 0.053073 | 8251 | 9e-05 | 3184
MADISON 2101117644 | MADISON 2101 | 63172101 | TRUE | 2.3347 | 0.092748 | 0.56732 | 43.5 | 0.00026409 | 8778 | 0.37154 | 2947 | 8.9969e-05 | 3185
BRUNSWICK 1107CB | BRUNSWICK 1107 | 152481107 |  | 0.073748 | 0 |  | 0.66667 | 0.0013419 | 171 | 0.067 | 6056 | 8.9909e-05 | 3186
OROSI 11027948F | OROSI 1102 | 252841102 | FALSE | 8.601 | 0.79943 | 0.8195 | 161.5 | 0.00019206 | 10177 | 0.80381 | 2555 | 8.9621e-05 | 3187
MC ARTHUR 1101648698 | MC ARTHUR 1101 | 103491101 | FALSE | 19.7543 | 1.2193 | 11.0343 | 369.5 | 0.00010682 | 11028 | 1.0174 | 2373 | 8.9301e-05 | 3188
MADISON 210189332 | MADISON 2101 | 63172101 |  | 20.0776 | 1.2644 |  | 396.5 | 0.00024882 | 9103 | 1.988 | 1640 | 8.8848e-05 | 3189
CALISTOGA 1101157668 | CALISTOGA 1101 | 42711101 |  | 0.23576 | 0 |  | 3 | 0.0010911 | 494 | 0.08081 | 3384 | 8.8727e-05 | 3190
LAKEWOOD 210769586 | LAKEWOOD 2107 | 13532107 | TRUE | 5.9985 | 5.077 | 0.11303 | 102.1667 | 0.00058802 | 4442 | 0.13466 | 3244 | 8.8577e-05 | 3191
BULLARD 211155476 | BULLARD 2111 | 253962111 |  | 0.79707 | 0.20464 |  | 11.8333 | 0.0016672 | 59 | 0.053073 | 8250 | 8.8481e-05 | 3192
STAGG 21087410 | STAGG 2108 | 162422108 |  | 0.011364 | 0 |  | 0.5 | 0.0016567 | 62 | 0.053073 | 8251 | 8.7926e-05 | 3193
MOSHER 211010062 | MOSHER 2110 | 163722110 |  | 0.011364 | 0 |  | 0.83333 | 0.0016538 | 64 | 0.053073 | 8250 | 8.7769e-05 | 3194
DEL MONTE 110138582 | DEL MONTE 1101 | 182221101 | TRUE | 5.3445 | 2.338 | 0.50753 | 65.6667 | 0.00062094 | 4038 | 0.15251 | 3200 | 8.7593e-05 | 3195
KIRKER 210885526 | KIRKER 2108 | 14452108 |  | 0.19997 | 0.0098597 |  | 3.5 | 0.0016445 | 67 | 0.053073 | 8251 | 8.728e-05 | 3196
SAN RAMON 2111MR293 | SAN RAMON 2111 | 14232111 |  | 0.038436 | 0 |  | 0.58333 | 0.0016439 | 68 | 0.053073 | 8250 | 8.7247e-05 | 3197
PINEDALE 210653722 | PINEDALE 2106 | 252852106 |  | 0.13074 | 0 |  | 1.1667 | 0.0016436 | 69 | 0.053073 | 8250 | 8.7228e-05 | 3198
CALPELLA 1102422886 | CALPELLA 1102 | 43411102 |  | 6.9161 | 1.0326 |  | 120 | 0.00050273 | 5364 | 0.18603 | 3166 | 8.719e-05 | 3199
VACAVILLE 1102CB | VACAVILLE 1102 | 63601102 |  | 1.0025 | 0.77793 |  | 18 | 0.001467 | 122 | 0.06199 | 6764 | 8.7178e-05 | 3200
VALLEY VIEW 1105CB | VALLEY VIEW 1105 | 14341105 | TRUE | 4.6468 | 4.7072 | 0.01407 | 81.1667 | 0.0005908 | 4405 | 0.18624 | 3165 | 8.7107e-05 | 3201
MENDOCINO 110131322 | MENDOCINO 1101 | 42951101 | FALSE | 28.7637 | 3.6016 | 5.2882 | 512 | 0.00030079 | 8001 | 0.31965 | 2990 | 8.7107e-05 | 3202
MADISON 1105495270 | MADISON 1105 | 63171105 | TRUE | 8.1801 | 0.18469 | 0.35006 | 142.5 | 0.00013833 | 10808 | 1.8862 | 1675 | 8.703e-05 | 3203
CONTRA COSTA 2105CB | CONTRA COSTA 2105 | 13652105 |  | 0.040056 | 0 |  | 0.66667 | 0.001296 | 207 | 0.067035 | 5974 | 8.6877e-05 | 3204
OCEANO 110376678 | OCEANO 1103 | 182601103 | TRUE | 0.37432 | 0.22256 | 0.11673 | 11.5 | 0.00040559 | 6386 | 0.34831 | 2966 | 8.6718e-05 | 3205
SUISUN 1111CB | SUISUN 1111 | 62131111 |  | 0.6277 | 0.78392 |  | 13.3333 | 0.0013628 | 157 | 0.06085 | 6905 | 8.6579e-05 | 3206
NEWBURG 11322074 | NEWBURG 1132 | 192151132 |  | 10.3521 | 6.6884 |  | 177.8333 | 0.00046149 | 5791 | 0.22286 | 3114 | 8.6509e-05 | 3207
MOSHER 211010068 | MOSHER 2110 | 163722110 |  | 0.011364 | 0 |  | 0.33333 | 0.001629 | 72 | 0.053073 | 8251 | 8.6454e-05 | 3208
LOS GATOS 110160136 | LOS GATOS 1101 | 82021101 |  | 4.0784 | 2.8186 |  | 67 | 0.0007479 | 2507 | 0.12728 | 3254 | 8.6305e-05 | 3209
BELL 1107643778 | BELL 1107 | 152701107 | TRUE | 0.25744 | 0.048884 | 0.098947 | 4 | 0.00028691 | 8259 | 0.33775 | 2975 | 8.607e-05 | 3210
SILVERADO 210578326 | SILVERADO 2105 | 43432105 |  | 0.44086 | 0.4081 |  | 7 | 0.0015377 | 95 | 0.055961 | 7584 | 8.6007e-05 | 3211
PACIFICA 1104CB | PACIFICA 1104 | 22811104 |  | 3.0898 | 3.8602 |  | 50 | 0.00064864 | 3720 | 0.15404 | 3198 | 8.589e-05 | 3212
STOCKDALE 21074713 | STOCKDALE 2107 | 254072107 |  | 0.0511 | 0 |  | 0.5 | 0.0016161 | 76 | 0.053073 | 8251 | 8.5768e-05 | 3213
STOCKDALE 2108CB | STOCKDALE 2108 | 254072108 |  | 0.93048 | 0 |  | 13.8333 | 0.0016078 | 78 | 0.053073 | 8251 | 8.5329e-05 | 3214
SANTA ROSA A 1104CB | SANTA ROSA A 1104 | 42151104 | TRUE | 6.093 | 5.6113 | 0.11851 | 87 | 0.00075353 | 2449 | 0.13118 | 3248 | 8.5174e-05 | 3215
COTATI 1102464 | COTATI 1102 | 42271102 | FALSE | 8.4473 | 2.4532 | 2.0624 | 165.5 | 0.00028668 | 8266 | 0.36009 | 2954 | 8.5102e-05 | 3216
PAUL SWEET 2109CB | PAUL SWEET 2109 | 83252109 | TRUE | 12.1275 | 5.3236 | 0.061476 | 186.6667 | 0.00070889 | 2995 | 0.14092 | 3231 | 8.5094e-05 | 3217
MOSHER 210865528 | MOSHER 2108 | 163722108 |  | 0.25929 | 0.016677 |  | 4 | 0.0011945 | 305 | 0.071318 | 4852 | 8.5063e-05 | 3218
POTRERO PP (A) 111814777 | POTRERO PP (A) 1118 | 22031118 |  | 0.025923 | 0 |  | 0.80952 | 0.0016027 | 79 | 0.053073 | 8251 | 8.5061e-05 | 3219
OAKLAND X 1104645092 | OAKLAND X 1104 | 12541104 | FALSE | 1.0193 | 0.32483 | 1.0101 | 12.3333 | 0.00053894 | 4967 | 0.19533 | 3153 | 8.5007e-05 | 3220
STOCKDALE 21084115 | STOCKDALE 2108 | 254072108 |  | 0.017082 | 0 |  | 1.5 | 0.0016014 | 80 | 0.053073 | 8251 | 8.4993e-05 | 3221
FIGARDEN 2102CB | FIGARDEN 2102 | 254552102 |  | 0.6882 | 0 |  | 12 | 0.0016006 | 81 | 0.053073 | 8251 | 8.4949e-05 | 3222
CAROLANDS 04049026 | CAROLANDS 0404 | 24060404 | FALSE | 5.0112 | 4.5118 | 1.0531 | 99.5 | 0.00060273 | 4271 | 0.18582 | 3169 | 8.4922e-05 | 3223
MOSHER 2108CB | MOSHER 2108 | 163722108 |  | 1.4134 | 0 |  | 20 | 0.0014396 | 128 | 0.059978 | 7021 | 8.4699e-05 | 3224
STAFFORD 110242542 | STAFFORD 1102 | 43201102 | TRUE | 4.2192 | 3.393 | 0.61337 | 70.1667 | 0.00070841 | 3002 | 0.13828 | 3237 | 8.4486e-05 | 3225
STOCKDALE 2107CB | STOCKDALE 2107 | 254072107 |  | 1.4462 | 0.015403 |  | 18 | 0.0015898 | 83 | 0.053073 | 8251 | 8.4374e-05 | 3226
CORNING 110135974 | CORNING 1101 | 103331101 | TRUE | 0.83189 | 0.015941 | 0.10274 | 13 | 0.0001949 | 10134 | 0.3181 | 2994 | 8.4354e-05 | 3227
SAN RAMON 2107CB | SAN RAMON 2107 | 14232107 | TRUE | 9.1004 | 6.5013 | 0.3083 | 140 | 0.00071281 | 2939 | 0.19427 | 3154 | 8.4153e-05 | 3228
SPRUCE 0401BR316 | SPRUCE 0401 | 13340401 | FALSE | 4.1034 | 4.1956 | 8.2951 | 66.0833 | 0.00048766 | 5523 | 0.25628 | 3074 | 8.4116e-05 | 3229
FLINT 110138570 | FLINT 1101 | 152531101 |  | 3.4478 | 1.7378 |  | 46.5 | 0.00078676 | 2084 | 0.10939 | 3293 | 8.4047e-05 | 3230
STOCKDALE 210788914 | STOCKDALE 2107 | 254072107 |  | 0.30752 | 0 |  | 4 | 0.001582 | 84 | 0.053073 | 8251 | 8.3962e-05 | 3231
BAKERSFIELD 2106CB | BAKERSFIELD 2106 | 253372106 |  | 4.7353 | 3.546 |  | 76.6167 | 0.00158 | 85 | 0.053073 | 8251 | 8.3857e-05 | 3232
KING CITY 1102728782 | KING CITY 1102 | 182031102 |  | 3.9345 | 0.067248 |  | 83.5 | 0.0001188 | 10959 | 1.1054 | 2297 | 8.3389e-05 | 3233
WILLITS 110337504 | WILLITS 1103 | 42661103 | FALSE | 3.599 | 0.75662 | 1.3019 | 56.8333 | 0.0002953 | 8099 | 0.32712 | 2984 | 8.3193e-05 | 3234
FIGARDEN 210965596 | FIGARDEN 2109 | 254552109 |  | 0.84282 | 0.40944 |  | 12 | 0.0015657 | 86 | 0.053073 | 8251 | 8.3096e-05 | 3235
STAGG 21076482 | STAGG 2107 | 162422107 |  | 0.011363 | 0 |  | 0.33333 | 0.0015629 | 87 | 0.053073 | 8251 | 8.2949e-05 | 3236
FULTON 1102258281 | FULTON 1102 | 42561102 |  | 2.5437 | 0.059591 |  | 44.5 | 0.00030666 | 7874 | 0.23737 | 3098 | 8.2718e-05 | 3237
RIO DELL 1102772210 | RIO DELL 1102 | 192251102 | TRUE | 3.479 | 0.23265 | 0.40873 | 66 | 0.0005287 | 5090 | 0.14116 | 3230 | 8.27e-05 | 3238
EIGHT MILE 2103CB | EIGHT MILE 2103 | 163912103 |  | 0.0028409 | 0 |  | 0.5 | 0.0010671 | 564 | 0.0774 | 3397 | 8.2596e-05 | 3239
FIGARDEN 2113CB | FIGARDEN 2113 | 254552113 |  | 0.53383 | 0 |  | 6.3333 | 0.0013434 | 168 | 0.062675 | 6694 | 8.2543e-05 | 3240
NOVATO 1101CB | NOVATO 1101 | 42211101 | FALSE | 6.8525 | 4.8616 | 1.2873 | 115.8333 | 0.00061697 | 4086 | 0.18719 | 3163 | 8.2529e-05 | 3241
CLAY 11037124 | CLAY 1103 | 163341103 | FALSE | 32.0773 | 0.99773 | 8.7641 | 574 | 0.00017181 | 10461 | 0.76559 | 2588 | 8.2319e-05 | 3242
KERN OIL 1106397902 | KERN OIL 1106 | 252721106 | TRUE | 1.2115 | 0 | 0.4523 | 20.5 | 0.00013246 | 10862 | 0.56797 | 2767 | 8.2007e-05 | 3243
STOCKDALE 2115CB | STOCKDALE 2115 | 254072115 |  | 0.44635 | 0 |  | 4.1667 | 0.0015438 | 92 | 0.053073 | 8250 | 8.1934e-05 | 3244
BULLARD 2112CB | BULLARD 2112 | 253962112 |  | 3.2425 | 0.043162 |  | 29.5 | 0.0011843 | 323 | 0.069405 | 5126 | 8.1859e-05 | 3245
SANTA YNEZ 1101277014 | SANTA YNEZ 1101 | 182721101 | FALSE | 16.6818 | 0.58534 | 4.6008 | 299.5 | 0.00018985 | 10216 | 0.64843 | 2684 | 8.1845e-05 | 3246
STAGG 21056498 | STAGG 2105 | 162422105 |  | 0.010741 | 0 |  | 0.5 | 0.001541 | 94 | 0.053073 | 8251 | 8.1785e-05 | 3247
MOSHER 210869920 | MOSHER 2108 | 163722108 |  | 0.20671 | 0.12545 |  | 3 | 0.0011773 | 333 | 0.070724 | 4931 | 8.1646e-05 | 3248
BAKERSFIELD 1110CB | BAKERSFIELD 1110 | 253371110 |  | 0.91832 | 0.26884 |  | 14.95 | 0.0015377 | 96 | 0.053073 | 8251 | 8.161e-05 | 3249
PEABODY 2113CB | PEABODY 2113 | 63642113 | TRUE | 4.7844 | 0.44023 | 0.031963 | 52.1667 | 0.0010635 | 574 | 0.09102 | 3339 | 8.142e-05 | 3250
DEL MONTE 21042032 | DEL MONTE 2104 | 182222104 |  | 6.0257 | 6.2937 |  | 94.5833 | 0.00065193 | 3687 | 0.14862 | 3209 | 8.1212e-05 | 3251
MILPITAS 1109XR374 | MILPITAS 1109 | 82831109 | TRUE | 3.0799 | 0.10167 | 0.20819 | 61.5 | 0.00021998 | 9697 | 0.41248 | 2898 | 8.113e-05 | 3252
BRENTWOOD 210598606 | BRENTWOOD 2105 | 14592105 |  | 8.2509 | 0.60261 |  | 142.1667 | 0.00034728 | 7184 | 0.49806 | 2823 | 8.1124e-05 | 3253
GREEN VALLEY 2101135762 | GREEN VALLEY 2101 | 83192101 | FALSE | 2.8217 | 0.75819 | 0.63052 | 56.5 | 0.00024704 | 9144 | 0.39286 | 2923 | 8.1057e-05 | 3254
BULLARD 110382776 | BULLARD 1103 | 253961103 |  | 0.29253 | 0 |  | 1.9167 | 0.0015264 | 99 | 0.053073 | 8250 | 8.1013e-05 | 3255
SONOMA 1104414 | SONOMA 1104 | 42721104 | FALSE | 18.677 | 6.4418 | 0.68912 | 345 | 0.00054533 | 4906 | 0.27421 | 3051 | 8.0743e-05 | 3256
ROBLES 0401CB | ROBLES 0401 | 13580401 |  | 7.0891 | 4.0295 |  | 100.75 | 0.00073488 | 2678 | 0.11248 | 3284 | 8.0616e-05 | 3257
HORSESHOE 1104CB | HORSESHOE 1104 | 152571104 |  | 2.9634 | 1.6453 |  | 50.8333 | 0.0007631 | 2344 | 0.095137 | 3327 | 8.0614e-05 | 3258
HAMMER 110291106 | HAMMER 1102 | 163301102 |  | 0.45762 | 0 |  | 7 | 0.0015189 | 105 | 0.053073 | 8251 | 8.0613e-05 | 3259
SUNOL 1101MR169 | SUNOL 1101 | 14241101 | FALSE | 11.92 | 0.096684 | 3.0548 | 177 | 0.00015625 | 10638 | 0.49883 | 2822 | 8.0581e-05 | 3260
STAGG 21056502 | STAGG 2105 | 162422105 |  | 0.011361 | 0 |  | 0.5 | 0.0015178 | 106 | 0.053073 | 8251 | 8.0554e-05 | 3261
MEADOW LANE 2109CB | MEADOW LANE 2109 | 14302109 |  | 0.58444 | 0.035011 |  | 13.5 | 0.0015176 | 107 | 0.053073 | 8251 | 8.0543e-05 | 3262
ANDERSON 1103226050 | ANDERSON 1103 | 103261103 | FALSE | 15.0076 | 1.7149 | 4.4018 | 274 | 0.00029323 | 8146 | 0.28688 | 3033 | 8.0345e-05 | 3263
STONE CORRAL 1108001 | STONE CORRAL 1108 | 252921108 |  | 0.0056818 | 0 |  | 1.3333 | 0.0011968 | 299 | 0.067 | 6056 | 8.0187e-05 | 3264
SOLEDAD 2105526864 | SOLEDAD 2105 | 182052105 | FALSE | 3.7611 | 0.061226 | 2.8348 | 69.5 | 9.9862e-05 | 11051 | 0.89915 | 2486 | 8.0168e-05 | 3265
VACAVILLE 1108CB | VACAVILLE 1108 | 63601108 |  | 4.5887 | 5.1661 |  | 70.6667 | 0.00093769 | 1060 | 0.091393 | 3337 | 8.004e-05 | 3266
SILVERADO 2104CB | SILVERADO 2104 | 43432104 |  | 2.5534 | 1.3037 |  | 42 | 0.001249 | 241 | 0.064698 | 6471 | 7.9997e-05 | 3267
LINCOLN 1101860022 | LINCOLN 1101 | 153701101 | FALSE | 2.6324 | 0 | 0.96992 | 51 | 0.00028208 | 8374 | 0.45958 | 2864 | 7.9916e-05 | 3268
CALIFORNIA AVE 1112CB | CALIFORNIA AVE 1112 | 252281112 |  | 1.1393 | 0.3547 |  | 10.6667 | 0.0015057 | 108 | 0.053073 | 8252 | 7.9909e-05 | 3269
NAPA 1102CB | NAPA 1102 | 42021102 |  | 0.59724 | 0.048888 |  | 4.6167 | 0.0015047 | 109 | 0.053073 | 8251 | 7.9858e-05 | 3270
PAUL SWEET 210349246 | PAUL SWEET 2103 | 83252103 |  | 0.076562 | 0 |  | 0.53333 | 0.0011917 | 310 | 0.067 | 6057 | 7.9844e-05 | 3271
VIEJO 220436948 | VIEJO 2204 | 182852204 | FALSE | 8.41 | 6.9638 | 1.1716 | 114.4167 | 0.00075141 | 2466 | 0.14244 | 3224 | 7.9747e-05 | 3272
MOSHER 2110CB | MOSHER 2110 | 163722110 |  | 2.201 | 0.11901 |  | 34.6667 | 0.0015016 | 111 | 0.053073 | 8252 | 7.9694e-05 | 3273
STOCKDALE 21081736 | STOCKDALE 2108 | 254072108 |  | 0.96033 | 0.077647 |  | 13 | 0.0015002 | 112 | 0.053073 | 8251 | 7.9619e-05 | 3274
PEABODY 211375820 | PEABODY 2113 | 63642113 |  | 0.042927 | 0 |  | 0.5 | 0.0011878 | 317 | 0.067 | 6057 | 7.9586e-05 | 3275
ELK 11011300 | ELK 1101 | 42981101 | FALSE | 10.0115 | 0.3906 | 2.2245 | 187.8333 | 0.00016943 | 10493 | 0.44285 | 2877 | 7.9309e-05 | 3276
STOCKDALE 210899105 | STOCKDALE 2108 | 254072108 |  | 0.49578 | 0 |  | 7.8333 | 0.0014938 | 113 | 0.053073 | 8252 | 7.928e-05 | 3277
PINEDALE 210365598 | PINEDALE 2103 | 252852103 |  | 0.84208 | 0.10091 |  | 12.5 | 0.0014867 | 114 | 0.053073 | 8251 | 7.8904e-05 | 3278
CHICO B 1106CB | CHICO B 1106 | 102491106 |  | 0.97375 | 0.69298 |  | 13.3333 | 0.0014854 | 115 | 0.053073 | 8251 | 7.8833e-05 | 3279
BAKERSFIELD 2104CB | BAKERSFIELD 2104 | 253372104 |  | 3.8889 | 1.3691 |  | 44.45 | 0.0014825 | 117 | 0.053073 | 8250 | 7.8682e-05 | 3280
TASSAJARA 2108D520R | TASSAJARA 2108 | 14662108 |  | 5.2823 | 3.0226 |  | 93.5 | 0.00085071 | 1570 | 0.099475 | 3314 | 7.8439e-05 | 3281
FIGARDEN 210262168 | FIGARDEN 2102 | 254552102 |  | 0.62341 | 0 |  | 9.5 | 0.0013501 | 162 | 0.058194 | 7269 | 7.8355e-05 | 3282
GATES 1106755338 | GATES 1106 | 253931106 |  | 2.328 | 0.20234 |  | 43.5 | 0.00018014 | 10352 | 0.55473 | 2778 | 7.8248e-05 | 3283
STOCKDALE 21084269 | STOCKDALE 2108 | 254072108 |  | 0.035536 | 0 |  | 1.3333 | 0.0014734 | 119 | 0.053073 | 8251 | 7.8195e-05 | 3284
PINEDALE 2106R3270 | PINEDALE 2106 | 252852106 |  | 1.9034 | 0.13538 |  | 34.3333 | 0.001473 | 120 | 0.053073 | 8252 | 7.8178e-05 | 3285
FLORENCE 0401CB | FLORENCE 0401 | 12690401 | FALSE | 2.9107 | 2.363 | 1.1269 | 44.5 | 0.00061553 | 4101 | 0.089717 | 3344 | 7.816e-05 | 3286
BULLARD 1107331778 | BULLARD 1107 | 253961107 |  | 0.67675 | 0.067925 |  | 9.8333 | 0.001472 | 121 | 0.053073 | 8251 | 7.8124e-05 | 3287
CARLOTTA 1121686774 | CARLOTTA 1121 | 192291121 | FALSE | 5.8856 | 0.71703 | 1.5702 | 104 | 0.00025294 | 9020 | 0.35065 | 2965 | 7.7928e-05 | 3288
FULTON 1104466 | FULTON 1104 | 42561104 | TRUE | 1.5147 | 0.24783 | 0.41213 | 26.8333 | 0.00040657 | 6376 | 0.35306 | 2962 | 7.7837e-05 | 3289
WESTPARK 1103CB | WESTPARK 1103 | 253701103 |  | 2.8157 | 2.1828 |  | 40.5 | 0.0014615 | 123 | 0.053073 | 8251 | 7.7566e-05 | 3290
DEL MONTE 2104CB | DEL MONTE 2104 | 182222104 |  | 0.60604 | 0.26331 |  | 6.8333 | 0.0012344 | 252 | 0.062244 | 6741 | 7.7487e-05 | 3291
STOCKDALE 2106CB | STOCKDALE 2106 | 254072106 |  | 3.5138 | 0.065826 |  | 31.2833 | 0.0014431 | 127 | 0.053683 | 8038 | 7.7245e-05 | 3292
OCEANO 1106CB | OCEANO 1106 | 182601106 | FALSE | 4.5073 | 0.97564 | 0.91509 | 64.0833 | 0.00045912 | 5811 | 0.37527 | 2944 | 7.7212e-05 | 3293
WEST FRESNO 110460801 | WEST FRESNO 1104 | 253731104 |  | 0.1241 | 0.012127 |  | 2.6667 | 0.0014544 | 124 | 0.053073 | 8251 | 7.7191e-05 | 3294
TIDEWATER 2108C551R | TIDEWATER 2108 | 14652108 |  | 1.3965 | 0.9552 |  | 17.1667 | 0.0014538 | 125 | 0.053073 | 8253 | 7.7158e-05 | 3295
SILVERADO 210581662 | SILVERADO 2105 | 43432105 |  | 0.66146 | 0.59447 |  | 8.8333 | 0.001337 | 178 | 0.059562 | 7076 | 7.6835e-05 | 3296
WOODWARD 2109CB | WOODWARD 2109 | 255292109 |  | 0.27718 | 0.03542 |  | 6.5 | 0.0014054 | 138 | 0.056815 | 7464 | 7.6675e-05 | 3297
SAN JUSTO 1101CB | SAN JUSTO 1101 | 183181101 |  | 22.593 | 1.97 |  | 395.1667 | 0.00020011 | 10041 | 0.57562 | 2762 | 7.6601e-05 | 3298
EL CERRITO G 1105BR164 | EL CERRITO G 1105 | 12501105 | TRUE | 0.047569 | 0 | 0.047569 | 0.25 | 0.0011423 | 378 | 0.067035 | 5975 | 7.6576e-05 | 3299
SAN BERNARD 1101641042 | SAN BERNARD 1101 | 253191101 | FALSE | 6.5459 | 0.014832 | 0.98882 | 109.5 | 0.00021714 | 9747 | 0.57995 | 2757 | 7.6483e-05 | 3300
FIGARDEN 2103CB | FIGARDEN 2103 | 254552103 |  | 0.75469 | 0 |  | 7.3333 | 0.0014395 | 129 | 0.053073 | 8251 | 7.6396e-05 | 3301
HIGHLANDS 1102556 | HIGHLANDS 1102 | 43361102 | TRUE | 7.5685 | 2.5234 | 0.028065 | 109.5 | 0.00035609 | 7043 | 0.33307 | 2977 | 7.636e-05 | 3302
TASSAJARA 2113MR457 | TASSAJARA 2113 | 14662113 |  | 0.20317 | 0 |  | 2.5 | 0.0011338 | 405 | 0.06721 | 5799 | 7.6201e-05 | 3303
TASSAJARA 2103CB | TASSAJARA 2103 | 14662103 | TRUE | 16.7087 | 7.4761 | 0.27342 | 305.3333 | 0.00067588 | 3359 | 0.15407 | 3197 | 7.6104e-05 | 3304
FIGARDEN 210392114 | FIGARDEN 2103 | 254552103 |  | 1.8894 | 0.28677 |  | 20.6667 | 0.0014332 | 131 | 0.053073 | 8251 | 7.6064e-05 | 3305
KIRKER 2107CB | KIRKER 2107 | 14452107 |  | 1.0022 | 0.037636 |  | 11.8333 | 0.001135 | 401 | 0.067 | 6056 | 7.6044e-05 | 3306
RALSTON 1102CB | RALSTON 1102 | 24141102 | FALSE | 4.2825 | 1.3527 | 0.90455 | 76 | 0.00052918 | 5081 | 0.19082 | 3157 | 7.599e-05 | 3307
BARTON 1105CB | BARTON 1105 | 253571105 |  | 3.2367 | 1.0503 |  | 34.8333 | 0.0014252 | 133 | 0.05332 | 8169 | 7.5978e-05 | 3308
REDBUD 1102432 | REDBUD 1102 | 43191102 | FALSE | 11.2221 | 8.2709 | 1.6004 | 159.5 | 0.00053698 | 4991 | 0.18593 | 3167 | 7.5871e-05 | 3309
FULTON 1103CB | FULTON 1103 | 42561103 |  | 0.0094663 | 0 |  | 0.25 | 0.0011296 | 414 | 0.06707 | 5925 | 7.5763e-05 | 3310
COTTLE 1704CB | COTTLE 1704 | 163711704 |  | 0.028549 | 0 |  | 0.33333 | 0.0014275 | 132 | 0.053073 | 8251 | 7.5759e-05 | 3311
FIGARDEN 2104CB | FIGARDEN 2104 | 254552104 |  | 0.98473 | 0.30609 |  | 8.8333 | 0.0013654 | 156 | 0.055827 | 7608 | 7.5698e-05 | 3312
ROSSMOOR 1109961536 | ROSSMOOR 1109 | 14161109 |  | 0.36225 | 0 |  | 4.6667 | 0.0011548 | 366 | 0.065256 | 6397 | 7.5663e-05 | 3313
CAROLANDS 0404CB | CAROLANDS 0404 | 24060404 |  | 0.026534 | 0 |  | 0.25 | 0.0011165 | 440 | 0.067315 | 5722 | 7.5155e-05 | 3314
LAKEWOOD 2225CB | LAKEWOOD 2225 | 13532225 |  | 1.4349 | 0.11543 |  | 13.25 | 0.0011847 | 322 | 0.062445 | 6722 | 7.5154e-05 | 3315
OLEMA 110137074 | OLEMA 1101 | 42291101 | TRUE | 0.35935 | 0.17611 | 0.032408 | 8.5 | 0.00043427 | 6068 | 0.25812 | 3073 | 7.5154e-05 | 3316
EL CERRITO G 1112664184 | EL CERRITO G 1112 | 12501112 | FALSE | 1.9446 | 2.2924 | 0.79851 | 25.3333 | 0.00049216 | 5472 | 0.18377 | 3171 | 7.5081e-05 | 3317
PARADISE 1102CB | PARADISE 1102 | 102831102 |  | 0.002796 | 0 |  | 0.2 | 0.0011174 | 437 | 0.067105 | 5893 | 7.4984e-05 | 3318
WESTPARK 1109689790 | WESTPARK 1109 | 253701109 |  | 0.017573 | 0 |  | 0.5 | 0.0014122 | 135 | 0.053073 | 8251 | 7.4948e-05 | 3319
STAGG 21077408 | STAGG 2107 | 162422107 |  | 0.011364 | 0 |  | 0.5 | 0.0014121 | 136 | 0.053073 | 8251 | 7.4945e-05 | 3320
PLACERVILLE 1112778710 | PLACERVILLE 1112 | 153081112 | TRUE | 0.14015 | 0 | 0.015789 | 2.1667 | 0.0010872 | 504 | 0.068923 | 5203 | 7.4932e-05 | 3321
SARATOGA 1103LC40 | SARATOGA 1103 | 83371103 | TRUE | 1.9447 | 1.3785 | 0.015393 | 41 | 0.00069111 | 3206 | 0.18916 | 3159 | 7.483e-05 | 3322
OAKLAND J 1105CR150 | OAKLAND J 1105 | 12091105 | TRUE | 0.50024 | 0.39747 | 0.26813 | 8.5 | 0.0006714 | 3423 | 0.11842 | 3270 | 7.4763e-05 | 3323
EDES 1112417626 | EDES 1112 | 13681112 |  | 0.081688 | 0.048351 |  | 1 | 0.0014069 | 137 | 0.053073 | 8251 | 7.4666e-05 | 3324
PINEDALE 210232912 | PINEDALE 2102 | 252852102 |  | 1.3112 | 0.76803 |  | 23 | 0.0014053 | 139 | 0.053073 | 8251 | 7.4585e-05 | 3325
FIGARDEN 210347324 | FIGARDEN 2103 | 254552103 |  | 0.059602 | 0 |  | 2.5 | 0.0014043 | 140 | 0.053073 | 8251 | 7.4532e-05 | 3326
HOLLYWOOD 0401CB | HOLLYWOOD 0401 | 13170401 | FALSE | 5.3549 | 5.7223 | 5.6357 | 75.5 | 0.00048251 | 5573 | 0.16017 | 3193 | 7.4483e-05 | 3327
WEST FRESNO 110655414 | WEST FRESNO 1106 | 253731106 |  | 2.5086 | 1.0298 |  | 40.3333 | 0.001403 | 141 | 0.053073 | 8251 | 7.4458e-05 | 3328
STOCKDALE 211035420 | STOCKDALE 2110 | 254072110 |  | 0.020726 | 0 |  | 0.5 | 0.0014028 | 142 | 0.053073 | 8251 | 7.4449e-05 | 3329
CLOVIS 1105CB | CLOVIS 1105 | 254081105 |  | 2.2285 | 1.0746 |  | 29.1167 | 0.0013993 | 143 | 0.053073 | 8250 | 7.4265e-05 | 3330
RENFRO 21054828 | RENFRO 2105 | 254572105 |  | 0.035396 | 0 |  | 0.66667 | 0.0013067 | 198 | 0.057374 | 7378 | 7.4244e-05 | 3331
LAKEWOOD 2227CB | LAKEWOOD 2227 | 13532227 |  | 0.24498 | 0 |  | 3.3333 | 0.001134 | 403 | 0.065607 | 6338 | 7.4171e-05 | 3332
PUEBLO 110256136 | PUEBLO 1102 | 43291102 |  | 0.11145 | 0.059372 |  | 1.3333 | 0.0013963 | 144 | 0.053073 | 8251 | 7.4104e-05 | 3333
MEADOW LANE 2102CB | MEADOW LANE 2102 | 14302102 |  | 0.0056818 | 0 |  | 1 | 0.001396 | 146 | 0.053073 | 8251 | 7.4091e-05 | 3334
PINEDALE 2106R3250 | PINEDALE 2106 | 252852106 |  | 0.50843 | 0 |  | 7 | 0.0013713 | 153 | 0.054148 | 7914 | 7.4022e-05 | 3335
SAUSALITO 11021224 | SAUSALITO 1102 | 42491102 | TRUE | 2.0345 | 0.66738 | 0.0053059 | 32.8333 | 0.00069795 | 3132 | 0.12431 | 3260 | 7.4013e-05 | 3336
CLOVERDALE 1102262 | CLOVERDALE 1102 | 42821102 | FALSE | 5.9321 | 0.55042 | 0.86568 | 102.5 | 0.00029989 | 8021 | 0.26222 | 3063 | 7.3958e-05 | 3337
BERKELEY F 1105BR166 | BERKELEY F 1105 | 12061105 | TRUE | 0.038174 | 0 | 0.038174 | 0.5 | 0.0011027 | 465 | 0.067035 | 5975 | 7.392e-05 | 3338
COVELO 110146208 | COVELO 1101 | 43061101 |  | 7.907 | 0.16995 |  | 133 | 0.00018096 | 10340 | 0.32792 | 2983 | 7.3788e-05 | 3339
CALISTOGA 1102447865 | CALISTOGA 1102 | 42711102 |  | 0.0098501 | 0 |  | 0.5 | 0.0010196 | 723 | 0.072279 | 4746 | 7.3693e-05 | 3340
STOCKDALE 21051503 | STOCKDALE 2105 | 254072105 |  | 0.10611 | 0.008134 |  | 1.3333 | 0.0013875 | 147 | 0.053073 | 8251 | 7.3639e-05 | 3341
JAMESON 1101CB | JAMESON 1101 | 63801101 |  | 0.0056819 | 0 |  | 1 | 0.0010977 | 476 | 0.067017 | 6004 | 7.3563e-05 | 3342
CLOVIS 211138752 | CLOVIS 2111 | 254082111 |  | 1.9601 | 0.8356 |  | 24.5 | 0.0013848 | 149 | 0.053073 | 8251 | 7.3493e-05 | 3343
MILPITAS 1104CB | MILPITAS 1104 | 82831104 |  | 1.0478 | 0.033122 |  | 15.0833 | 0.0013847 | 150 | 0.053073 | 8250 | 7.3492e-05 | 3344
BULLARD 211242194 | BULLARD 2112 | 253962112 |  | 1.9725 | 0.5964 |  | 33.1667 | 0.0012649 | 231 | 0.056618 | 7488 | 7.3485e-05 | 3345
VINEYARD 2107MR649 | VINEYARD 2107 | 14502107 |  | 0.18676 | 0 |  | 3.5 | 0.0010945 | 485 | 0.067035 | 5975 | 7.337e-05 | 3346
LAKEWOOD 222454676 | LAKEWOOD 2224 | 13532224 |  | 0.47983 | 0.13901 |  | 5.1667 | 0.0010919 | 493 | 0.067167 | 5839 | 7.3365e-05 | 3347
PACIFICA 11026783 | PACIFICA 1102 | 22811102 | TRUE | 4.7597 | 4.2028 | 0.00014074 | 64 | 0.00063816 | 3849 | 0.17987 | 3173 | 7.3213e-05 | 3348
STAGG 210511564 | STAGG 2105 | 162422105 |  | 0.011364 | 0 |  | 0.5 | 0.0013787 | 151 | 0.053073 | 8251 | 7.3172e-05 | 3349
SANTA ROSA A 1111CB | SANTA ROSA A 1111 | 42151111 |  | 5.6335 | 3.6147 |  | 110 | 0.00084895 | 1583 | 0.13828 | 3236 | 7.3014e-05 | 3350
STAGG 210741764 | STAGG 2107 | 162422107 |  | 0.6457 | 0.12309 |  | 9.3333 | 0.0013738 | 152 | 0.053073 | 8250 | 7.2909e-05 | 3351
LOS OSITOS 2103258688 | LOS OSITOS 2103 | 182082103 | FALSE | 3.4999 | 0.13993 | 0.63159 | 76.5 | 0.00019426 | 10141 | 0.53167 | 2793 | 7.2909e-05 | 3352
WESTPARK 1106CB | WESTPARK 1106 | 253701106 |  | 2.7577 | 2.6896 |  | 41.3333 | 0.0013706 | 154 | 0.053073 | 8250 | 7.2741e-05 | 3353
SAN RAMON 2118CB | SAN RAMON 2118 | 14232118 |  | 0.83371 | 0.095755 |  | 12.0833 | 0.0012017 | 289 | 0.060661 | 6936 | 7.2718e-05 | 3354
BARTON 1109CB | BARTON 1109 | 253571109 |  | 1.0072 | 0.52767 |  | 17.8333 | 0.001368 | 155 | 0.053073 | 8250 | 7.2604e-05 | 3355
SARATOGA 1104209146 | SARATOGA 1104 | 83371104 | FALSE | 6.0603 | 1.1367 | 3.7034 | 113 | 0.00055817 | 4777 | 0.12802 | 3251 | 7.2598e-05 | 3356
KERN POWER 2101CB | KERN POWER 2101 | 255262101 |  | 1.1945 | 0 |  | 13.8667 | 0.0010363 | 662 | 0.07157 | 4818 | 7.2551e-05 | 3357
CALIFORNIA AVE 111391862 | CALIFORNIA AVE 1113 | 252281113 |  | 0.23108 | 0.048175 |  | 3.5 | 0.001362 | 158 | 0.053073 | 8251 | 7.2286e-05 | 3358
TRIMBLE 2115CB | TRIMBLE 2115 | 83802115 |  | 0.31317 | 0.052034 |  | 3.6667 | 0.001076 | 542 | 0.067 | 6058 | 7.2092e-05 | 3359
MEADOW LANE 2110CB | MEADOW LANE 2110 | 14302110 |  | 6.611 | 4.3308 |  | 110 | 0.0013573 | 159 | 0.053073 | 8251 | 7.2036e-05 | 3360
SYCAMORE CREEK 1111CB | SYCAMORE CREEK 1111 | 102971111 | TRUE | 7.4267 | 0.58622 | 0.049308 | 125.5 | 0.00059324 | 4381 | 0.13473 | 3243 | 7.197e-05 | 3361
BAKERSFIELD 1115CB | BAKERSFIELD 1115 | 253371115 |  | 5.6038 | 3.0833 |  | 77.5 | 0.0013556 | 160 | 0.053073 | 8250 | 7.1943e-05 | 3362
CONTRA COSTA 2110CB | CONTRA COSTA 2110 | 13652110 |  | 0.55395 | 0.032442 |  | 9.5667 | 0.0011988 | 296 | 0.059728 | 7050 | 7.1913e-05 | 3363
VALLEY VIEW 1103P156 | VALLEY VIEW 1103 | 14341103 |  | 0.014355 | 0 |  | 1 | 0.0010729 | 550 | 0.067 | 6057 | 7.1885e-05 | 3364
MARTELL 110292172 | MARTELL 1102 | 163011102 | TRUE | 3.2418 | 1.3408 | 0.093679 | 52.5 | 0.00056568 | 4702 | 0.19705 | 3148 | 7.1847e-05 | 3365
WEST SACRAMENTO 1111CB | WEST SACRAMENTO 1111 | 63131111 |  | 0.0056819 | 0 |  | 0.33333 | 0.0013528 | 161 | 0.053073 | 8251 | 7.1796e-05 | 3366
DEL MONTE 21029060 | DEL MONTE 2102 | 182222102 | FALSE | 8.906 | 6.7962 | 0.65824 | 113.1667 | 0.00089778 | 1244 | 0.097184 | 3322 | 7.1743e-05 | 3367
HICKS 2101XR162 | HICKS 2101 | 83432101 | TRUE | 9.5682 | 3.5356 | 0.47631 | 172.5 | 0.00046117 | 5795 | 0.24361 | 3092 | 7.1571e-05 | 3368
TRACY 111213998 | TRACY 1112 | 162881112 |  | 0.011526 | 0 |  | 0.5 | 0.0013471 | 165 | 0.053073 | 8251 | 7.1492e-05 | 3369
BRUNSWICK 110750008 | BRUNSWICK 1107 | 152481107 | TRUE | 3.7791 | 2.4342 | 0.24189 | 56.3333 | 0.00075567 | 2427 | 0.11985 | 3266 | 7.1473e-05 | 3370
SOLEDAD 2102CB | SOLEDAD 2102 | 182052102 |  | 0.41852 | 0 |  | 7 | 0.0010663 | 569 | 0.067 | 6057 | 7.1439e-05 | 3371
SAN MIGUEL 1104895760 | SAN MIGUEL 1104 | 182661104 | FALSE | 12.2825 | 0.096887 | 8.4285 | 227.8333 | 9.2681e-05 | 11076 | 0.7924 | 2564 | 7.1408e-05 | 3372
BAKERSFIELD 1107CB | BAKERSFIELD 1107 | 253371107 |  | 3.5463 | 1.1411 |  | 45.45 | 0.0013453 | 167 | 0.053073 | 8251 | 7.1398e-05 | 3373
MANTECA 170338588 | MANTECA 1703 | 162611703 |  | 0.58657 | 0.29175 |  | 13 | 0.0013426 | 169 | 0.053073 | 8251 | 7.1255e-05 | 3374
SWIFT 2110CB | SWIFT 2110 | 83392110 |  | 0.12211 | 0.018938 |  | 3.6667 | 0.0013423 | 170 | 0.053073 | 8251 | 7.1239e-05 | 3375
SAN ARDO 1101650772 | SAN ARDO 1101 | 182191101 | FALSE | 2.762 | 0.027796 | 0.71912 | 57.3333 | 0.00015292 | 10668 | 0.95252 | 2446 | 7.1232e-05 | 3376
BAKERSFIELD 1105CB | BAKERSFIELD 1105 | 253371105 |  | 6.4095 | 3.3272 |  | 78.8667 | 0.0013418 | 172 | 0.053073 | 8250 | 7.1215e-05 | 3377
BAKERSFIELD 2109CB | BAKERSFIELD 2109 | 253372109 |  | 2.3862 | 2.5074 |  | 33.2 | 0.0013411 | 173 | 0.053073 | 8250 | 7.1176e-05 | 3378
BULLARD 1102CB | BULLARD 1102 | 253961102 |  | 1.7847 | 0.47044 |  | 24.5833 | 0.0013411 | 174 | 0.053073 | 8252 | 7.1176e-05 | 3379
KERN POWER 21054959 | KERN POWER 2105 | 255262105 |  | 0.47949 | 0 |  | 9.5 | 0.0013403 | 175 | 0.053073 | 8251 | 7.1136e-05 | 3380
IGNACIO 1104316 | IGNACIO 1104 | 42481104 |  | 0.015625 | 0 |  | 0.25 | 0.0010607 | 586 | 0.067 | 6057 | 7.1065e-05 | 3381
SPENCE 1102990464 | SPENCE 1102 | 182201102 | FALSE | 5.327 | 0.091987 | 2.0362 | 106 | 0.00023777 | 9326 | 0.48172 | 2840 | 7.1035e-05 | 3382
BULLARD 110567230 | BULLARD 1105 | 253961105 |  | 1.393 | 0.20357 |  | 20 | 0.0013379 | 176 | 0.053073 | 8251 | 7.1006e-05 | 3383
WESTPARK 1102CB | WESTPARK 1102 | 253701102 |  | 3.7586 | 2.206 |  | 56.3333 | 0.0013372 | 177 | 0.053073 | 8251 | 7.097e-05 | 3384
STAGG 21066654 | STAGG 2106 | 162422106 |  | 0.011364 | 0 |  | 1.3333 | 0.0013367 | 179 | 0.053073 | 8251 | 7.0944e-05 | 3385
BAKERSFIELD 1114CB | BAKERSFIELD 1114 | 253371114 |  | 4.8352 | 3.3808 |  | 74.3333 | 0.0013365 | 181 | 0.053073 | 8251 | 7.0933e-05 | 3386
EDENVALE 1103CB | EDENVALE 1103 | 82951103 | TRUE | 0.31829 | 0 | 0.0056485 | 6.5 | 0.0007243 | 2798 | 0.14304 | 3223 | 7.0881e-05 | 3387
PINEDALE 2110CB | PINEDALE 2110 | 252852110 |  | 0.19156 | 0 |  | 3.5 | 0.0013333 | 182 | 0.053073 | 8251 | 7.0762e-05 | 3388
NORTH DUBLIN 2101MR333 | NORTH DUBLIN 2101 | 14052101 |  | 0.39641 | 0 |  | 3.3333 | 0.001332 | 183 | 0.053073 | 8250 | 7.0693e-05 | 3389
BULLARD 211155478 | BULLARD 2111 | 253962111 |  | 1.2604 | 0 |  | 16.3333 | 0.0013288 | 184 | 0.053073 | 8252 | 7.0521e-05 | 3390
ECHO SUMMIT 1101CB | ECHO SUMMIT 1101 | 158031101 | TRUE | 0.092284 | 0 | 0.092284 | 0.33333 | 5.765e-05 | 11121 | 1.2226 | 2100 | 7.0484e-05 | 3391
ASHLAN AVE 2101CB | ASHLAN AVE 2101 | 252052101 |  | 2.2384 | 2.2012 |  | 44.45 | 0.0013268 | 185 | 0.053073 | 8251 | 7.0416e-05 | 3392
STAGG 210614574 | STAGG 2106 | 162422106 |  | 0.10104 | 0 |  | 2 | 0.0013253 | 186 | 0.053073 | 8251 | 7.0336e-05 | 3393
FIGARDEN 210787746 | FIGARDEN 2107 | 254552107 |  | 0.23227 | 0 |  | 4.5 | 0.001287 | 218 | 0.055776 | 7622 | 7.0295e-05 | 3394
BELLEVUE 21018146 | BELLEVUE 2101 | 43182101 |  | 0.012784 | 0 |  | 0.33333 | 0.0013232 | 187 | 0.053073 | 8251 | 7.0224e-05 | 3395
DEL MAR 1104CB | DEL MAR 1104 | 152581104 |  | 0.0034562 | 0 |  | 0.33333 | 0.0013224 | 188 | 0.053073 | 8251 | 7.0182e-05 | 3396
SILVERADO 2105CB | SILVERADO 2105 | 43432105 | TRUE | 3.996 | 3.1627 | 0.016501 | 65.5 | 0.0011288 | 415 | 0.062885 | 6672 | 7.0102e-05 | 3397
BASALT 1104CB | BASALT 1104 | 42461104 |  | 0.66558 | 0 |  | 7.8333 | 0.0011118 | 454 | 0.062438 | 6723 | 7.0084e-05 | 3398
FIGARDEN 2111CB | FIGARDEN 2111 | 254552111 |  | 0.22406 | 0 |  | 4 | 0.0013173 | 190 | 0.053073 | 8251 | 6.9912e-05 | 3399
DIXON LANDING 2111CB | DIXON LANDING 2111 | 14722111 |  | 0.1306 | 0 |  | 3 | 0.0013168 | 191 | 0.053073 | 8251 | 6.9886e-05 | 3400
BAKERSFIELD 1106CB | BAKERSFIELD 1106 | 253371106 |  | 2.5651 | 1.0161 |  | 24.5333 | 0.0013166 | 192 | 0.053073 | 8251 | 6.9875e-05 | 3401
MERCED 21029970 | MERCED 2102 | 252802102 |  | 1.2793 | 1.041 |  | 21.8333 | 0.0013162 | 193 | 0.053073 | 8251 | 6.9857e-05 | 3402
ECHO SUMMIT 110155262 | ECHO SUMMIT 1101 | 158031101 | TRUE | 0.18657 | 0.024699 | 0.21127 | 1.3333 | 5.7116e-05 | 11122 | 1.2226 | 2099 | 6.9831e-05 | 3403
PACIFIC GROVE 04222608 | PACIFIC GROVE 0422 | 182440422 |  | 3.0315 | 2.1889 |  | 46 | 0.00060571 | 4230 | 0.1014 | 3310 | 6.9746e-05 | 3404
MANCHESTER 1108D8824 | MANCHESTER 1108 | 253921108 |  | 0.29012 | 0 |  | 3.5 | 0.0013139 | 194 | 0.053073 | 8251 | 6.973e-05 | 3405
BRUNSWICK 1110CB | BRUNSWICK 1110 | 152481110 | TRUE | 1.7231 | 0.8605 | 0.00068285 | 30.1667 | 0.000723 | 2816 | 0.08793 | 3351 | 6.9567e-05 | 3406
STOCKDALE 2110CB | STOCKDALE 2110 | 254072110 |  | 2.572 | 1.3743 |  | 28.1667 | 0.0013104 | 196 | 0.053073 | 8251 | 6.9544e-05 | 3407
HILLSDALE 0404CB | HILLSDALE 0404 | 24110404 |  | 0.0068182 | 0 |  | 0.5 | 0.0010372 | 659 | 0.067 | 6057 | 6.9491e-05 | 3408
CLOVIS 2109CB | CLOVIS 2109 | 254082109 |  | 1.2367 | 0.24098 |  | 18.8667 | 0.0013074 | 197 | 0.053073 | 8250 | 6.9386e-05 | 3409
FIGARDEN 210249606 | FIGARDEN 2102 | 254552102 |  | 1.5371 | 0.68586 |  | 26 | 0.0012653 | 230 | 0.054875 | 7774 | 6.9342e-05 | 3410
STAGG 2107CB | STAGG 2107 | 162422107 |  | 0.98939 | 0 |  | 9.5 | 0.0013065 | 199 | 0.053073 | 8251 | 6.9341e-05 | 3411
PENRYN 1105154362 | PENRYN 1105 | 152561105 | FALSE | 7.4152 | 0.61897 | 1.5819 | 129 | 0.00022273 | 9653 | 0.40991 | 2904 | 6.9326e-05 | 3412
FOOTHILL 1101549904 | FOOTHILL 1101 | 182951101 | TRUE | 7.4944 | 0.92812 | 0.044661 | 144 | 0.00034318 | 7258 | 0.22527 | 3110 | 6.9287e-05 | 3413
SHEPHERD 211038450 | SHEPHERD 2110 | 252062110 |  | 1.8537 | 0.9147 |  | 29.8333 | 0.0013051 | 200 | 0.053073 | 8251 | 6.9268e-05 | 3414
LAS POSITAS 2103MR161 | LAS POSITAS 2103 | 14402103 |  | 1.3309 | 0 |  | 12.6667 | 0.0010334 | 669 | 0.067 | 6057 | 6.9239e-05 | 3415
STOCKDALE 21074712 | STOCKDALE 2107 | 254072107 |  | 0.016221 | 0 |  | 0.5 | 0.0013046 | 201 | 0.053073 | 8251 | 6.9238e-05 | 3416
BULLARD 110269280 | BULLARD 1102 | 253961102 |  | 0.64893 | 0.34119 |  | 14.3333 | 0.0013043 | 202 | 0.053073 | 8251 | 6.9225e-05 | 3417
MILLBRAE 11045521 | MILLBRAE 1104 | 22691104 |  | 4.6117 | 3.2452 |  | 62.8333 | 0.00049827 | 5409 | 0.148 | 3210 | 6.9139e-05 | 3418
JARVIS 1110CB | JARVIS 1110 | 13501110 |  | 6.0017 | 2.0055 |  | 127 | 0.00047132 | 5686 | 0.19246 | 3155 | 6.913e-05 | 3419
KIRKER 2104CB | KIRKER 2104 | 14452104 | TRUE | 10.1116 | 10.0719 | 0.031087 | 166.25 | 0.00094814 | 1017 | 0.080126 | 3386 | 6.9059e-05 | 3420
WYANDOTTE 11091520 | WYANDOTTE 1109 | 102911109 | FALSE | 19.7563 | 4.0233 | 3.7066 | 349.5 | 0.00032702 | 7504 | 0.3567 | 2958 | 6.9033e-05 | 3421
STAGG 21066476 | STAGG 2106 | 162422106 |  | 0.011364 | 0 |  | 0.5 | 0.0012999 | 204 | 0.053073 | 8251 | 6.899e-05 | 3422
RESEARCH 2101D576R | RESEARCH 2101 | 14692101 |  | 2.195 | 0.36231 |  | 39 | 0.0010628 | 577 | 0.064857 | 6457 | 6.8929e-05 | 3423
CALISTOGA 1102929461 | CALISTOGA 1102 | 42711102 |  | 0.0093255 | 0 |  | 0.5 | 0.00095362 | 996 | 0.07221 | 4755 | 6.886e-05 | 3424
DEL MAR 210938684 | DEL MAR 2109 | 152582109 |  | 0.062402 | 0 |  | 1.5 | 0.001024 | 711 | 0.06721 | 5799 | 6.882e-05 | 3425
PEORIA 170413494 | PEORIA 1704 | 163781704 | FALSE | 7.4929 | 0.94423 | 2.2245 | 143.5 | 0.00022394 | 9628 | 0.35531 | 2959 | 6.8731e-05 | 3426
CALIFORNIA AVE 111279552 | CALIFORNIA AVE 1112 | 252281112 |  | 3.6608 | 1.3876 |  | 57.1667 | 0.0012934 | 208 | 0.053073 | 8251 | 6.8643e-05 | 3427
MANTECA 1701CB | MANTECA 1701 | 162611701 |  | 1.1678 | 0.0033407 |  | 17.5 | 0.0012925 | 209 | 0.053073 | 8251 | 6.8594e-05 | 3428
PINEDALE 2102CB | PINEDALE 2102 | 252852102 |  | 1.4319 | 0.074574 |  | 27 | 0.0012919 | 210 | 0.053073 | 8251 | 6.8566e-05 | 3429
FIGARDEN 210538320 | FIGARDEN 2105 | 254552105 |  | 0.66443 | 0 |  | 10.8333 | 0.0012902 | 212 | 0.053073 | 8251 | 6.8476e-05 | 3430
MEADOW LANE 210365632 | MEADOW LANE 2103 | 14302103 |  | 0.27139 | 0 |  | 3.1667 | 0.0012891 | 213 | 0.053073 | 8251 | 6.8414e-05 | 3431
KIRKER 2109CB | KIRKER 2109 | 14452109 |  | 8.5187 | 1.7131 |  | 129.8333 | 0.0011674 | 349 | 0.059173 | 7135 | 6.8404e-05 | 3432
CLOVIS 2111CB | CLOVIS 2111 | 254082111 |  | 4.5599 | 4.4697 |  | 67.3667 | 0.0012881 | 214 | 0.053073 | 8250 | 6.8361e-05 | 3433
CALIFORNIA AVE 1104CB | CALIFORNIA AVE 1104 | 252281104 |  | 2.4083 | 0.43827 |  | 26.8333 | 0.0012876 | 216 | 0.053073 | 8251 | 6.8337e-05 | 3434
OAKLAND X 1101CR224 | OAKLAND X 1101 | 12541101 | FALSE | 1.1484 | 1.0156 | 0.81554 | 24.8333 | 0.00051546 | 5225 | 0.10675 | 3299 | 6.8285e-05 | 3435
CHICO A 110229504 | CHICO A 1102 | 102051102 |  | 2.2273 | 1.6655 |  | 27.6667 | 0.0012222 | 267 | 0.056177 | 7551 | 6.8267e-05 | 3436
SAN RAMON 2105CB | SAN RAMON 2105 | 14232105 |  | 3.2878 | 0 |  | 68 | 0.001173 | 338 | 0.058534 | 7219 | 6.8182e-05 | 3437
GIRVAN 1102CB | GIRVAN 1102 | 103401102 | TRUE | 13.7046 | 0.92234 | 0.38691 | 246.5 | 0.00064553 | 3758 | 0.10662 | 3301 | 6.8156e-05 | 3438
TULUCAY 1101504524 | TULUCAY 1101 | 42301101 | TRUE | 1.5202 | 0.032135 | 0.076182 | 27 | 0.00034685 | 7191 | 0.27668 | 3043 | 6.8059e-05 | 3439
SUMMIT 110168706 | SUMMIT 1101 | 152591101 |  | 5.1674 | 0.99211 |  | 76.5 | 0.0006317 | 3921 | 0.083504 | 3380 | 6.8053e-05 | 3440
WOODWARD 210192860 | WOODWARD 2101 | 255292101 |  | 1.3612 | 0.031068 |  | 25.5 | 0.0012805 | 220 | 0.053073 | 8251 | 6.796e-05 | 3441
SANTA MARIA 1112CB | SANTA MARIA 1112 | 182671112 |  | 0.37603 | 0.20947 |  | 5.8333 | 0.0012795 | 221 | 0.053073 | 8252 | 6.7907e-05 | 3442
MOSHER 21109174 | MOSHER 2110 | 163722110 |  | 0.011364 | 0 |  | 1 | 0.0012785 | 222 | 0.053073 | 8251 | 6.7855e-05 | 3443
SALINAS 1101CB | SALINAS 1101 | 182011101 |  | 0.4492 | 0.2879 |  | 4 | 0.0011248 | 424 | 0.060036 | 7014 | 6.7825e-05 | 3444
WEST FRESNO 1105CB | WEST FRESNO 1105 | 253731105 |  | 5.2647 | 3.0892 |  | 68.6845 | 0.0012741 | 224 | 0.05325 | 8197 | 6.7798e-05 | 3445
KIRKER 2105CB | KIRKER 2105 | 14452105 |  | 8.257 | 0.76685 |  | 112.75 | 0.0011948 | 303 | 0.056968 | 7443 | 6.7787e-05 | 3446
GREEN VALLEY 210190860 | GREEN VALLEY 2101 | 83192101 |  | 18.3087 | 2.4167 |  | 340 | 0.00039182 | 6545 | 0.25606 | 3075 | 6.7668e-05 | 3447
NOTRE DAME 1101CB | NOTRE DAME 1101 | 102041101 |  | 1.5965 | 0.14422 |  | 26 | 0.0011108 | 457 | 0.060633 | 6941 | 6.7649e-05 | 3448
CORDELIA 111013382 | CORDELIA 1110 | 62701110 |  | 0.08298 | 0 |  | 2.5 | 0.0012744 | 223 | 0.053073 | 8251 | 6.7635e-05 | 3449
SERRAMONTE 1104CB | SERRAMONTE 1104 | 22861104 |  | 0.2951 | 0 |  | 3.8333 | 0.0010092 | 763 | 0.067 | 6057 | 6.7619e-05 | 3450
STOCKDALE 1111CB | STOCKDALE 1111 | 254071111 |  | 3.2211 | 0.94152 |  | 44.2833 | 0.0012729 | 225 | 0.053073 | 8249 | 6.7556e-05 | 3451
CALIFORNIA AVE 1117CB | CALIFORNIA AVE 1117 | 252281117 |  | 0.96789 | 0 |  | 10.1667 | 0.0012725 | 226 | 0.053073 | 8252 | 6.7535e-05 | 3452
STAGG 21066652 | STAGG 2106 | 162422106 |  | 0.0099608 | 0 |  | 0.5 | 0.0012722 | 227 | 0.053073 | 8251 | 6.7519e-05 | 3453
STOCKDALE 21124665 | STOCKDALE 2112 | 254072112 |  | 0.75749 | 0.035663 |  | 12.5 | 0.0011694 | 343 | 0.058911 | 7166 | 6.7429e-05 | 3454
PEABODY 2102CB | PEABODY 2102 | 63642102 |  | 1.4565 | 0 |  | 20.2833 | 0.0010097 | 762 | 0.066717 | 6134 | 6.7306e-05 | 3455
HAMILTON BRANCH 110153192 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 2.0124 | 0.64936 | 0.63759 | 36.5 | 0.00031619 | 7695 | 0.25987 | 3068 | 6.7279e-05 | 3456
PORTRERO PP(A) 1120CB | PORTRERO PP(A) 1120 | 22031120 |  | 0.0038426 | 0 |  | 0.33333 | 0.0012674 | 229 | 0.053073 | 8251 | 6.7263e-05 | 3457
OAKLAND X 1106121588 | OAKLAND X 1106 | 12541106 | FALSE | 1.8955 | 2.022 | 1.5689 | 29.8333 | 0.00044056 | 6006 | 0.16337 | 3191 | 6.7261e-05 | 3458
TIDEWATER 2109CB | TIDEWATER 2109 | 14652109 |  | 3.0589 | 1.042 |  | 36.4167 | 0.0011695 | 342 | 0.057531 | 7355 | 6.7212e-05 | 3459
HICKS 2111CB | HICKS 2111 | 83432111 |  | 1.0108 | 0.57507 |  | 14 | 0.0010519 | 615 | 0.064016 | 6539 | 6.7192e-05 | 3460
LAKEWOOD 2108CB | LAKEWOOD 2108 | 13532108 |  | 0.52793 | 0.032597 |  | 4.8667 | 0.0011987 | 297 | 0.055934 | 7587 | 6.719e-05 | 3461
STOCKDALE 2109CB | STOCKDALE 2109 | 254072109 |  | 5.8364 | 0.092493 |  | 69.2833 | 0.001232 | 255 | 0.055767 | 7625 | 6.7098e-05 | 3462
MILPITAS 1108342498 | MILPITAS 1108 | 82831108 | TRUE | 0.70299 | 0.08415 | 0.016758 | 14.5 | 0.0002296 | 9497 | 0.44599 | 2869 | 6.7062e-05 | 3463
MOSHER 2104CB | MOSHER 2104 | 163722104 |  | 0.014302 | 0 |  | 2.5 | 0.001263 | 232 | 0.053073 | 8251 | 6.7031e-05 | 3464
MONTAGUE 2109CB | MONTAGUE 2109 | 83892109 |  | 0.81134 | 0 |  | 8 | 0.0012599 | 234 | 0.053073 | 8251 | 6.6866e-05 | 3465
BULLARD 110355680 | BULLARD 1103 | 253961103 |  | 0.46011 | 0.24669 |  | 7.9167 | 0.0012593 | 235 | 0.053073 | 8250 | 6.6836e-05 | 3466
WOODLAND 1111CB | WOODLAND 1111 | 62031111 |  | 0.26701 | 0 |  | 4 | 0.0012585 | 236 | 0.053073 | 8251 | 6.679e-05 | 3467
PENRYN 110550550 | PENRYN 1105 | 152561105 | TRUE | 14.4632 | 1.2302 | 0.0034319 | 262 | 0.0002641 | 8776 | 0.41943 | 2894 | 6.6771e-05 | 3468
NAPA 1112315244 | NAPA 1112 | 42021112 | TRUE | 4.2345 | 0.45855 | 0.22955 | 72 | 0.00036869 | 6862 | 0.30561 | 3014 | 6.6734e-05 | 3469
BRUNSWICK 110767218 | BRUNSWICK 1107 | 152481107 |  | 0.34597 | 0.030461 |  | 4.8333 | 0.0010476 | 628 | 0.064143 | 6525 | 6.6629e-05 | 3470
EAST STOCKTON 1101CB | EAST STOCKTON 1101 | 163131101 |  | 1.0108 | 0.46224 |  | 11.1667 | 0.001255 | 237 | 0.053073 | 8249 | 6.6608e-05 | 3471
TIDEWATER 2110CB | TIDEWATER 2110 | 14652110 |  | 4.7652 | 1.1275 |  | 71.8333 | 0.0011805 | 330 | 0.057284 | 7395 | 6.6586e-05 | 3472
MANCHESTER 1104351482 | MANCHESTER 1104 | 253921104 |  | 2.7843 | 3.7491 |  | 42.8333 | 0.0012536 | 238 | 0.053073 | 8251 | 6.6535e-05 | 3473
WESTPARK 11091558 | WESTPARK 1109 | 253701109 |  | 0.03961 | 0 |  | 0.5 | 0.0012536 | 239 | 0.053073 | 8251 | 6.6533e-05 | 3474
BULLARD 1105CB | BULLARD 1105 | 253961105 |  | 1.2946 | 0.36802 |  | 11.75 | 0.0012486 | 242 | 0.053073 | 8251 | 6.6268e-05 | 3475
DEL MAR 2110CB | DEL MAR 2110 | 152582110 |  | 2.115 | 0.072157 |  | 28.1667 | 0.0010113 | 759 | 0.065948 | 6283 | 6.62e-05 | 3476
MILLBRAE 0404CB | MILLBRAE 0404 | 22690404 |  | 1.5264 | 0.32745 |  | 12.3667 | 0.0011378 | 395 | 0.056085 | 7567 | 6.6155e-05 | 3477
TIDEWATER 210657926 | TIDEWATER 2106 | 14652106 | TRUE | 11.6101 | 1.9526 | 0.067379 | 206.1667 | 0.00065942 | 3587 | 0.10252 | 3309 | 6.6133e-05 | 3478
RANCHERS COTTON 1101323356 | RANCHERS COTTON 1101 | 254801101 |  | 0.14797 | 0.034098 |  | 2.5 | 0.0012461 | 244 | 0.053073 | 8251 | 6.6132e-05 | 3479
WESTPARK 1109CB | WESTPARK 1109 | 253701109 |  | 5.0872 | 1.0743 |  | 66.4167 | 0.0012088 | 282 | 0.054538 | 7841 | 6.6069e-05 | 3480
NEWARK 21KV 2104863090 | NEWARK 21KV 2104 | 12232104 |  | 0.14706 | 0 |  | 3 | 0.0010657 | 571 | 0.062358 | 6731 | 6.6023e-05 | 3481
SILVERADO 2104940 | SILVERADO 2104 | 43432104 |  | 1.6964 | 0.95514 |  | 33 | 0.00098503 | 842 | 0.067422 | 5649 | 6.6021e-05 | 3482
WOODWARD 2109R9546 | WOODWARD 2109 | 255292109 |  | 1.5795 | 0.20399 |  | 25.5 | 0.0011763 | 336 | 0.057843 | 7318 | 6.6013e-05 | 3483
COTATI 1102825 | COTATI 1102 | 42271102 | TRUE | 2.0785 | 0.7489 | 0.38496 | 42.5 | 0.00023849 | 9314 | 0.41504 | 2897 | 6.6012e-05 | 3484
EDENVALE 1102XR064 | EDENVALE 1102 | 82951102 | TRUE | 3.7748 | 0.20004 | 0.51334 | 73 | 0.00028686 | 8261 | 0.2303 | 3104 | 6.5983e-05 | 3485
LAS POSITAS 2110CB | LAS POSITAS 2110 | 14402110 |  | 1.3698 | 0.20832 |  | 26.9167 | 0.0011154 | 442 | 0.058367 | 7239 | 6.5914e-05 | 3486
MANCHESTER 1109CB | MANCHESTER 1109 | 253921109 |  | 5.7751 | 4.879 |  | 80.5 | 0.0012416 | 245 | 0.053073 | 8251 | 6.5896e-05 | 3487
PINEDALE 210979984 | PINEDALE 2109 | 252852109 |  | 6.8648 | 5.6581 |  | 110.6667 | 0.0012402 | 247 | 0.053073 | 8250 | 6.5822e-05 | 3488
SAN LUIS OBISPO 1103365572 | SAN LUIS OBISPO 1103 | 182631103 | TRUE | 0.45108 | 0 | 0.10021 | 8.5 | 8.0193e-05 | 11105 | 0.95263 | 2445 | 6.5726e-05 | 3489
FIGARDEN 2107CB | FIGARDEN 2107 | 254552107 |  | 0.35084 | 0.047028 |  | 5 | 0.0012383 | 248 | 0.053073 | 8251 | 6.5718e-05 | 3490
TIDEWATER 21072152 | TIDEWATER 2107 | 14652107 |  | 0.045496 | 0 |  | 0.5 | 0.00098049 | 870 | 0.067 | 6057 | 6.5693e-05 | 3491
CALIFORNIA AVE 111297998 | CALIFORNIA AVE 1112 | 252281112 |  | 0.019668 | 0 |  | 0.5 | 0.0012365 | 249 | 0.053073 | 8251 | 6.5622e-05 | 3492
VIERRA 1703744838 | VIERRA 1703 | 162701703 |  | 0.0098968 | 0 |  | 0.5 | 0.0012359 | 250 | 0.053073 | 8251 | 6.5591e-05 | 3493
GANSNER 110199388 | GANSNER 1101 | 103021101 |  | 0.65998 | 0.3999 |  | 14 | 0.00036051 | 6974 | 0.26014 | 3067 | 6.5579e-05 | 3494
BULLARD 1107CB | BULLARD 1107 | 253961107 |  | 1.7195 | 1.2235 |  | 24.5 | 0.0012353 | 251 | 0.053073 | 8251 | 6.5562e-05 | 3495
RED BLUFF 1105CB | RED BLUFF 1105 | 103541105 |  | 1.4631 | 0.73408 |  | 21.75 | 0.00099514 | 808 | 0.066051 | 6260 | 6.5542e-05 | 3496
BULLARD 1102R6062 | BULLARD 1102 | 253961102 |  | 0.35147 | 0.022211 |  | 4 | 0.001234 | 253 | 0.053073 | 8251 | 6.5494e-05 | 3497
MOSHER 2107CB | MOSHER 2107 | 163722107 |  | 0.94238 | 0.72366 |  | 14 | 0.001233 | 254 | 0.053073 | 8251 | 6.544e-05 | 3498
BULLARD 1108CB | BULLARD 1108 | 253961108 |  | 1.6243 | 0.7908 |  | 22.0833 | 0.0012156 | 277 | 0.053657 | 8044 | 6.5439e-05 | 3499
PINEDALE 2107CB | PINEDALE 2107 | 252852107 |  | 1.5828 | 0.87485 |  | 32 | 0.0012317 | 256 | 0.053073 | 8251 | 6.5372e-05 | 3500
TAR FLAT 0402CB | TAR FLAT 0402 | 163240402 |  | 0.29912 | 0.18252 |  | 3.6667 | 0.00098917 | 837 | 0.065795 | 6304 | 6.5364e-05 | 3501
STOCKDALE 21084265 | STOCKDALE 2108 | 254072108 |  | 0.035312 | 0 |  | 0.5 | 0.0012315 | 257 | 0.053073 | 8251 | 6.5361e-05 | 3502
STOCKDALE 21084267 | STOCKDALE 2108 | 254072108 |  | 0.072387 | 0 |  | 1 | 0.0012308 | 258 | 0.053073 | 8251 | 6.532e-05 | 3503
KERN POWER 21054931 | KERN POWER 2105 | 255262105 |  | 0.27136 | 0 |  | 3.8333 | 0.0012304 | 259 | 0.053073 | 8250 | 6.5301e-05 | 3504
RENFRO 2107454076 | RENFRO 2107 | 254572107 |  | 1.5486 | 0.002029 |  | 25.5 | 0.00098924 | 836 | 0.06758 | 5564 | 6.5301e-05 | 3505
TASSAJARA 2106203380 | TASSAJARA 2106 | 14662106 | TRUE | 1.8561 | 0.31708 | 0.39747 | 33 | 0.00037025 | 6837 | 0.37147 | 2948 | 6.5283e-05 | 3506
SYCAMORE CREEK 11112544 | SYCAMORE CREEK 1111 | 102971111 |  | 1.9002 | 0.85553 |  | 34.5 | 0.0011205 | 429 | 0.059731 | 7049 | 6.5227e-05 | 3507
ATASCADERO 1102A26 | ATASCADERO 1102 | 182541102 |  | 7.0652 | 1.4198 |  | 132.5 | 0.00032093 | 7613 | 0.28699 | 3032 | 6.5189e-05 | 3508
WEST FRESNO 110470610 | WEST FRESNO 1104 | 253731104 |  | 3.584 | 2.5708 |  | 58 | 0.0012281 | 260 | 0.053073 | 8251 | 6.5176e-05 | 3509
CHICO B 11062580 | CHICO B 1106 | 102491106 |  | 1.0391 | 0.69769 |  | 11.8333 | 0.0012278 | 261 | 0.053073 | 8250 | 6.5162e-05 | 3510
HUNTERS POINT (P) 1107CB | HUNTERS POINT (P) 1107 | 22331107 |  | 2.3992 | 0.68124 |  | 17.6917 | 0.0012259 | 262 | 0.053073 | 8254 | 6.506e-05 | 3511
TASSAJARA 2108CB | TASSAJARA 2108 | 14662108 |  | 3.577 | 1.1479 |  | 65 | 0.0010278 | 701 | 0.062783 | 6681 | 6.5048e-05 | 3512
TIDEWATER 2108CB | TIDEWATER 2108 | 14652108 |  | 1.9893 | 0.58562 |  | 22.5833 | 0.0011561 | 365 | 0.055894 | 7597 | 6.5001e-05 | 3513
SAN RAFAEL 1106910 | SAN RAFAEL 1106 | 42011106 | TRUE | 4.7272 | 4.3324 | 0.11051 | 72.8333 | 0.0007162 | 2902 | 0.1358 | 3242 | 6.498e-05 | 3514
PUEBLO 1105684564 | PUEBLO 1105 | 43291105 | TRUE | 2.6414 | 0.051646 | 0.25036 | 48.3333 | 0.0002826 | 8362 | 0.19638 | 3151 | 6.4947e-05 | 3515
NEWARK 21KV 2102CB | NEWARK 21KV 2102 | 12232102 |  | 0.51434 | 0.092403 |  | 10.5 | 0.0012233 | 264 | 0.053073 | 8251 | 6.4923e-05 | 3516
MANCHESTER 1103CB | MANCHESTER 1103 | 253921103 |  | 7.1977 | 6.4145 |  | 97.0833 | 0.0012229 | 265 | 0.053073 | 8252 | 6.4902e-05 | 3517
STAGG 210744270 | STAGG 2107 | 162422107 |  | 0.58063 | 0 |  | 9 | 0.0012227 | 266 | 0.053073 | 8251 | 6.489e-05 | 3518
WEBER 110191832 | WEBER 1101 | 163481101 |  | 0.011364 | 0 |  | 0.5 | 0.0012206 | 268 | 0.053073 | 8251 | 6.4778e-05 | 3519
BELL 1107CB | BELL 1107 | 152701107 |  | 3.6016 | 1.6293 |  | 74.25 | 0.00056569 | 4701 | 0.13946 | 3233 | 6.4753e-05 | 3520
STOCKDALE 21134765 | STOCKDALE 2113 | 254072113 |  | 4.0568 | 1.8914 |  | 58.5 | 0.00122 | 269 | 0.053073 | 8251 | 6.4747e-05 | 3521
WESTPARK 1101CB | WESTPARK 1101 | 253701101 |  | 6.9183 | 5.6535 |  | 93.1667 | 0.0012199 | 270 | 0.053073 | 8250 | 6.4743e-05 | 3522
BAKERSFIELD 11023391 | BAKERSFIELD 1102 | 253371102 |  | 2.5978 | 2.8443 |  | 41.6667 | 0.0012196 | 271 | 0.053073 | 8251 | 6.4728e-05 | 3523
ASHLAN AVE 2119CB | ASHLAN AVE 2119 | 252052119 |  | 5.3149 | 5.2699 |  | 80.9167 | 0.0012194 | 272 | 0.053073 | 8250 | 6.4717e-05 | 3524
LAKEWOOD 2227W503R | LAKEWOOD 2227 | 13532227 | TRUE | 7.6437 | 7.0196 | 0.050997 | 106.3333 | 0.00072568 | 2782 | 0.093126 | 3333 | 6.4679e-05 | 3525
PINEDALE 2103CB | PINEDALE 2103 | 252852103 |  | 1.1387 | 0.84731 |  | 25 | 0.0012179 | 273 | 0.053073 | 8251 | 6.4636e-05 | 3526
DAYTON ROAD 0401CB | DAYTON ROAD 0401 | 102940401 |  | 2.1092 | 1.6837 |  | 28.6667 | 0.0011874 | 318 | 0.054368 | 7872 | 6.4634e-05 | 3527
WESTPARK 1104CB | WESTPARK 1104 | 253701104 |  | 8.1108 | 7.4631 |  | 119.4167 | 0.0012145 | 278 | 0.053378 | 8143 | 6.4594e-05 | 3528
TRACY 110412866 | TRACY 1104 | 162881104 |  | 0.065734 | 0 |  | 0.16667 | 0.0012167 | 274 | 0.053073 | 8251 | 6.4573e-05 | 3529
STAGG 2106CB | STAGG 2106 | 162422106 |  | 2.5976 | 0.14679 |  | 30.1667 | 0.0012161 | 276 | 0.053073 | 8250 | 6.4543e-05 | 3530
ROSEDALE 2102CB | ROSEDALE 2102 | 254762102 |  | 3.7075 | 0.51384 |  | 56.1667 | 0.0010089 | 766 | 0.066211 | 6232 | 6.4526e-05 | 3531
STOCKDALE 2105CB | STOCKDALE 2105 | 254072105 |  | 2.3295 | 0 |  | 28.9167 | 0.0011827 | 328 | 0.056958 | 7444 | 6.4491e-05 | 3532
BAY MEADOWS 1106CB | BAY MEADOWS 1106 | 24011106 |  | 0.32681 | 0.017882 |  | 4.5 | 0.0011123 | 451 | 0.058479 | 7222 | 6.4439e-05 | 3533
HAMMER 1106967040 | HAMMER 1106 | 163301106 |  | 0.76451 | 0.39506 |  | 14.1667 | 0.0012135 | 279 | 0.053073 | 8251 | 6.4402e-05 | 3534
PLEASANT GROVE 2104CB | PLEASANT GROVE 2104 | 152442104 |  | 2.4266 | 0.089435 |  | 38 | 0.00098089 | 867 | 0.065904 | 6291 | 6.4366e-05 | 3535
ECHO SUMMIT 11012500 | ECHO SUMMIT 1101 | 158031101 | FALSE | 2.1525 | 1.0729 | 3.2254 | 43.3333 | 4.948e-05 | 11128 | 1.2901 | 2018 | 6.4343e-05 | 3536
SWIFT 2102CB | SWIFT 2102 | 83392102 |  | 1.0554 | 0.53393 |  | 16.3333 | 0.0010834 | 516 | 0.060154 | 7002 | 6.4342e-05 | 3537
ROSSMOOR 1101CB | ROSSMOOR 1101 | 14161101 |  | 4.8293 | 2.3372 |  | 66.8095 | 0.00095548 | 985 | 0.0673 | 5730 | 6.4316e-05 | 3538
STAGG 21056452 | STAGG 2105 | 162422105 |  | 1.3745 | 0 |  | 12.3333 | 0.0012111 | 280 | 0.053073 | 8251 | 6.4277e-05 | 3539
CONTRA COSTA 210963935 | CONTRA COSTA 2109 | 13652109 |  | 1.2293 | 0.49476 |  | 18.3333 | 0.0012094 | 281 | 0.053073 | 8251 | 6.4185e-05 | 3540
CLOVIS 2110CB | CLOVIS 2110 | 254082110 |  | 3.8376 | 3.9999 |  | 54.8333 | 0.0012088 | 283 | 0.053073 | 8251 | 6.4154e-05 | 3541
ASHLAN AVE 2105CB | ASHLAN AVE 2105 | 252052105 |  | 5.0196 | 5.01 |  | 58.95 | 0.0012085 | 284 | 0.053073 | 8251 | 6.4138e-05 | 3542
NEWARK 21KV 2104819304 | NEWARK 21KV 2104 | 12232104 |  | 1.6814 | 0 |  | 38 | 0.0011773 | 332 | 0.054544 | 7839 | 6.4123e-05 | 3543
MADISON 21011606 | MADISON 2101 | 63172101 | TRUE | 18.5114 | 1.7737 | 0.14133 | 358.5 | 0.00024367 | 9207 | 0.78082 | 2576 | 6.4061e-05 | 3544
NORTECH 2109XR004 | NORTECH 2109 | 82462109 |  | 0.034104 | 0 |  | 2.5 | 0.00095599 | 983 | 0.067 | 6057 | 6.4051e-05 | 3545
BOGUE 11046134 | BOGUE 1104 | 153781104 |  | 0.11437 | 0.031841 |  | 2 | 0.0012053 | 285 | 0.053073 | 8251 | 6.3968e-05 | 3546
SAN RAMON 211995606 | SAN RAMON 2119 | 14232119 |  | 2.2312 | 1.0116 |  | 35.5 | 0.00097082 | 914 | 0.065826 | 6300 | 6.3957e-05 | 3547
BAIR 1101CB | BAIR 1101 | 24261101 |  | 0.055851 | 0 |  | 1 | 0.0012028 | 286 | 0.053073 | 8251 | 6.3835e-05 | 3548
STAGG 1101CB | STAGG 1101 | 162421101 |  | 2.5066 | 0.27974 |  | 28.3333 | 0.0012027 | 287 | 0.053073 | 8251 | 6.3829e-05 | 3549
HONCUT 1102301886 | HONCUT 1102 | 103211102 | FALSE | 7.7491 | 0.32278 | 2.3783 | 131.5 | 0.00016925 | 10496 | 0.33878 | 2973 | 6.3785e-05 | 3550
STAGG 21056496 | STAGG 2105 | 162422105 |  | 0.011364 | 0 |  | 1.5 | 0.0012018 | 288 | 0.053073 | 8251 | 6.3783e-05 | 3551
BAY MEADOWS 21029162 | BAY MEADOWS 2102 | 24012102 |  | 0.13355 | 0 |  | 1.5833 | 0.0012017 | 290 | 0.053073 | 8251 | 6.3779e-05 | 3552
ASHLAN AVE 2119D8229 | ASHLAN AVE 2119 | 252052119 |  | 0.55778 | 0.33043 |  | 8.5 | 0.0012017 | 291 | 0.053073 | 8251 | 6.3777e-05 | 3553
ASHLAN AVE 1108R3340 | ASHLAN AVE 1108 | 252051108 |  | 3.4211 | 3.13 |  | 52 | 0.0012009 | 292 | 0.053073 | 8251 | 6.3737e-05 | 3554
COUNTRY CLUB 1102CB | COUNTRY CLUB 1102 | 163121102 |  | 1.3186 | 0.54346 |  | 24.5333 | 0.0012009 | 293 | 0.053073 | 8251 | 6.3733e-05 | 3555
TASSAJARA 2113CB | TASSAJARA 2113 | 14662113 |  | 0.050907 | 0.081704 |  | 2 | 0.0012005 | 294 | 0.053073 | 8251 | 6.3712e-05 | 3556
KERN POWER 210138356 | KERN POWER 2101 | 255262101 |  | 0.77776 | 0.048827 |  | 13.6667 | 0.0010081 | 769 | 0.064382 | 6497 | 6.361e-05 | 3557
POTRERO PP (A) 11136647 | POTRERO PP (A) 1113 | 22031113 |  | 0.17971 | 0.058727 |  | 1.5 | 0.0011974 | 298 | 0.053073 | 8250 | 6.3547e-05 | 3558
BAKERSFIELD 11101841 | BAKERSFIELD 1110 | 253371110 |  | 5.0368 | 2.5776 |  | 70 | 0.0011966 | 300 | 0.053073 | 8251 | 6.3508e-05 | 3559
BARTON 1101CB | BARTON 1101 | 253571101 |  | 3.835 | 0.18381 |  | 53.1667 | 0.00094644 | 1024 | 0.069559 | 5110 | 6.3493e-05 | 3560
DIXON LANDING 2103XR400 | DIXON LANDING 2103 | 14722103 |  | 0.033893 | 0.013172 |  | 0.5 | 0.00094614 | 1027 | 0.067105 | 5893 | 6.349e-05 | 3561
MANCHESTER 111255404 | MANCHESTER 1112 | 253921112 |  | 4.7026 | 4.6626 |  | 57.8333 | 0.0011961 | 301 | 0.053073 | 8251 | 6.3479e-05 | 3562
BULLARD 211465560 | BULLARD 2114 | 253962114 |  | 0.66597 | 0.22064 |  | 12.5 | 0.00093971 | 1051 | 0.070588 | 4943 | 6.3463e-05 | 3563
LAS PALMAS 1101CB | LAS PALMAS 1101 | 254921101 |  | 0.26192 | 0 |  | 3 | 0.00081962 | 1822 | 0.0774 | 3397 | 6.3439e-05 | 3564
WOODWARD 210238556 | WOODWARD 2102 | 255292102 |  | 0.64143 | 0.32193 |  | 16.5 | 0.0011842 | 324 | 0.053594 | 8062 | 6.3404e-05 | 3565
BAKERSFIELD 1102CB | BAKERSFIELD 1102 | 253371102 |  | 3.6536 | 3.1713 |  | 47.7 | 0.0011946 | 304 | 0.053073 | 8251 | 6.3399e-05 | 3566
WEST FRESNO 11099422 | WEST FRESNO 1109 | 253731109 |  | 2.4622 | 2.443 |  | 36.8333 | 0.0011943 | 306 | 0.053073 | 8251 | 6.3385e-05 | 3567
MONTAGUE 2105CB | MONTAGUE 2105 | 83892105 |  | 0.77864 | 0.0061714 |  | 14.6667 | 0.0011177 | 435 | 0.056555 | 7499 | 6.3377e-05 | 3568
CONTRA COSTA 2107825994 | CONTRA COSTA 2107 | 13652107 |  | 0.37944 | 0.055665 |  | 5.5 | 0.0011676 | 348 | 0.054342 | 7881 | 6.3375e-05 | 3569
WEST FRESNO 1102CB | WEST FRESNO 1102 | 253731102 |  | 4.1776 | 2.3736 |  | 57.3512 | 0.0011713 | 339 | 0.054312 | 7885 | 6.3357e-05 | 3570
OAKLAND J 1104CR386 | OAKLAND J 1104 | 12091104 |  | 0.45867 | 0.28807 |  | 5.6667 | 0.001193 | 309 | 0.053073 | 8251 | 6.3316e-05 | 3571
TEMPLETON 2113A32 | TEMPLETON 2113 | 183052113 | FALSE | 7.3744 | 3.4244 | 1.283 | 122.8333 | 0.00043854 | 6027 | 0.17619 | 3177 | 6.3286e-05 | 3572
MEADOW LANE 2107CB | MEADOW LANE 2107 | 14302107 |  | 3.3614 | 2.12 |  | 45 | 0.0011913 | 311 | 0.053073 | 8251 | 6.3227e-05 | 3573
FIREBAUGH 110298862 | FIREBAUGH 1102 | 253471102 |  | 0.031875 | 0 |  | 0.5 | 0.00081688 | 1841 | 0.0774 | 3397 | 6.3226e-05 | 3574
STOCKDALE 21104546 | STOCKDALE 2110 | 254072110 |  | 1.7435 | 1.0576 |  | 24.8333 | 0.0011907 | 312 | 0.053073 | 8252 | 6.3193e-05 | 3575
ROSSMOOR 110181770 | ROSSMOOR 1101 | 14161101 | TRUE | 1.4 | 0.84746 | 0.081965 | 23.8333 | 0.00056115 | 4742 | 0.11244 | 3285 | 6.3169e-05 | 3576
BULLARD 1113CB | BULLARD 1113 | 253961113 |  | 5.2151 | 2.0752 |  | 67 | 0.0010757 | 543 | 0.058872 | 7175 | 6.3143e-05 | 3577
SF H 1107343268 | SF H 1107 | 22101107 |  | 0.0087294 | 0 |  | 0.25 | 0.0011897 | 313 | 0.053073 | 8251 | 6.3141e-05 | 3578
WESTPARK 1110CB | WESTPARK 1110 | 253701110 |  | 7.5771 | 7.4838 |  | 114.6667 | 0.0011892 | 314 | 0.053073 | 8250 | 6.3112e-05 | 3579
STOCKTON A 1103CB | STOCKTON A 1103 | 162371103 |  | 0.20219 | 0 |  | 1.8333 | 0.0011881 | 315 | 0.053073 | 8251 | 6.3054e-05 | 3580
BURLINGAME 21013784 | BURLINGAME 2101 | 24052101 |  | 0.019246 | 0 |  | 0.83333 | 0.001188 | 316 | 0.053073 | 8250 | 6.3052e-05 | 3581
EIGHT MILE 210214582 | EIGHT MILE 2102 | 163912102 |  | 1.0729 | 0 |  | 15.5 | 0.00096302 | 941 | 0.064614 | 6478 | 6.3039e-05 | 3582
MANCHESTER 1106CB | MANCHESTER 1106 | 253921106 |  | 3.4265 | 3.7537 |  | 50.6667 | 0.0011873 | 319 | 0.053073 | 8252 | 6.3013e-05 | 3583
NORTECH 2110CB | NORTECH 2110 | 82462110 |  | 0.040096 | 0 |  | 1.5 | 0.0011865 | 320 | 0.053073 | 8251 | 6.2973e-05 | 3584
MANCHESTER 1109R9418 | MANCHESTER 1109 | 253921109 |  | 3.67 | 3.1826 |  | 56.3333 | 0.0011854 | 321 | 0.053073 | 8251 | 6.2911e-05 | 3585
JACINTO 1102CB | JACINTO 1102 | 102851102 |  | 0.19696 | 0 |  | 2 | 0.0008128 | 1874 | 0.0774 | 3397 | 6.2911e-05 | 3586
CALIFORNIA AVE 1103CB | CALIFORNIA AVE 1103 | 252281103 |  | 7.7454 | 4.913 |  | 118.9167 | 0.0011839 | 325 | 0.053073 | 8251 | 6.2834e-05 | 3587
LERDO 1111CB | LERDO 1111 | 253491111 |  | 0.087107 | 0 |  | 0.5 | 0.00081177 | 1884 | 0.0774 | 3397 | 6.2831e-05 | 3588
MANTECA 170712616 | MANTECA 1707 | 162611707 |  | 1.0333 | 0.55974 |  | 16.5 | 0.00109 | 496 | 0.056759 | 7471 | 6.2802e-05 | 3589
MEADOW LANE 210796222 | MEADOW LANE 2107 | 14302107 |  | 0.41228 | 0.054661 |  | 6.5 | 0.0011833 | 326 | 0.053073 | 8251 | 6.2801e-05 | 3590
BULLARD 1110R577 | BULLARD 1110 | 253961110 |  | 2.5952 | 1.9122 |  | 39.5 | 0.0011831 | 327 | 0.053073 | 8251 | 6.2788e-05 | 3591
HARRIS 11084674 | HARRIS 1108 | 192431108 | TRUE | 7.6669 | 4.9892 | 0.037782 | 125.8333 | 0.0005761 | 4576 | 0.11636 | 3275 | 6.2691e-05 | 3592
TIDEWATER 2106CB | TIDEWATER 2106 | 14652106 |  | 2.4125 | 1.0219 |  | 58.8333 | 0.001062 | 583 | 0.059849 | 7035 | 6.2659e-05 | 3593
HUNTERS POINT (P) 1101CB | HUNTERS POINT (P) 1101 | 22331101 |  | 1.5319 | 1.1567 |  | 15.1583 | 0.0011786 | 331 | 0.053073 | 8252 | 6.255e-05 | 3594
CLOVIS 1102CB | CLOVIS 1102 | 254081102 |  | 0.93248 | 0.075288 |  | 13.3667 | 0.0010889 | 498 | 0.060086 | 7007 | 6.251e-05 | 3595
BAKERSFIELD 210637524 | BAKERSFIELD 2106 | 253372106 |  | 6.784 | 6.1895 |  | 112.8333 | 0.0011764 | 335 | 0.053149 | 8234 | 6.2473e-05 | 3596
FRANKLIN 1101CB | FRANKLIN 1101 | 13921101 |  | 0.74161 | 0 |  | 12.75 | 0.00093198 | 1087 | 0.067 | 6057 | 6.2443e-05 | 3597
STOCKTON A 1109CB | STOCKTON A 1109 | 162371109 |  | 1.338 | 0.7615 |  | 18.0833 | 0.0011762 | 337 | 0.053073 | 8252 | 6.2426e-05 | 3598
POTTER VALLEY P H 1104CB | POTTER VALLEY P H 1104 | 42281104 | TRUE | 0.083052 | 0 | 0.083051 | 0.58333 | 0.00089641 | 1257 | 0.069587 | 5105 | 6.2378e-05 | 3599
CHICO B 1105585536 | CHICO B 1105 | 102491105 |  | 1.5444 | 1.3297 |  | 28.5 | 0.0010596 | 588 | 0.059657 | 7062 | 6.2283e-05 | 3600
LAKEWOOD 2110CB | LAKEWOOD 2110 | 13532110 |  | 4.3567 | 3.0897 |  | 67.7 | 0.00099069 | 826 | 0.065427 | 6372 | 6.2255e-05 | 3601
BUTTE 11052224 | BUTTE 1105 | 103081105 |  | 0.033455 | 0 |  | 1 | 0.00092915 | 1099 | 0.067 | 6057 | 6.2253e-05 | 3602
STAGG 2105CB | STAGG 2105 | 162422105 |  | 3.1023 | 1.3885 |  | 40.3333 | 0.0011304 | 412 | 0.054882 | 7772 | 6.2229e-05 | 3603
WESTPARK 1105CB | WESTPARK 1105 | 253701105 |  | 2.2881 | 0.12353 |  | 36.75 | 0.0011683 | 347 | 0.053307 | 8175 | 6.2186e-05 | 3604
HUNTERS POINT (P) 1108CB | HUNTERS POINT (P) 1108 | 22331108 |  | 2.2905 | 0.58743 |  | 22.825 | 0.0011713 | 340 | 0.053073 | 8250 | 6.2164e-05 | 3605
CALIFORNIA AVE 1111R2610 | CALIFORNIA AVE 1111 | 252281111 |  | 2.5917 | 0.055701 |  | 41 | 0.0011261 | 420 | 0.056039 | 7575 | 6.2077e-05 | 3606
BARTON 1110CB | BARTON 1110 | 253571110 |  | 4.142 | 3.0007 |  | 64.4167 | 0.0011696 | 341 | 0.053073 | 8252 | 6.2074e-05 | 3607
CARNATION 2101CB | CARNATION 2101 | 255282101 |  | 0.0049235 | 0 |  | 1 | 0.0011691 | 344 | 0.053073 | 8251 | 6.205e-05 | 3608
STOCKDALE 21063928 | STOCKDALE 2106 | 254072106 |  | 5.4404 | 2.5724 |  | 73.3333 | 0.0011689 | 345 | 0.053073 | 8251 | 6.2038e-05 | 3609
PUEBLO 1105CB | PUEBLO 1105 | 43291105 |  | 0.96863 | 0 |  | 10.6667 | 0.00087113 | 1414 | 0.071399 | 4843 | 6.1999e-05 | 3610
TIDEWATER 2106C540R | TIDEWATER 2106 | 14652106 |  | 0.04986 | 0 |  | 0.83333 | 0.00092241 | 1136 | 0.06721 | 5799 | 6.1995e-05 | 3611
WESTPARK 1107CB | WESTPARK 1107 | 253701107 |  | 2.3565 | 0.14962 |  | 37.5833 | 0.0011208 | 427 | 0.055662 | 7645 | 6.1991e-05 | 3612
CHICO A 0402CB | CHICO A 0402 | 102050402 |  | 5.6527 | 4.5438 |  | 64.0833 | 0.0011359 | 399 | 0.054827 | 7788 | 6.1938e-05 | 3613
VINEYARD 2105CB | VINEYARD 2105 | 14502105 |  | 3.2718 | 0.83212 |  | 46.5 | 0.0010634 | 575 | 0.056717 | 7477 | 6.1908e-05 | 3614
EVERGREEN 2104XR380 | EVERGREEN 2104 | 82012104 |  | 0.030582 | 0 |  | 0.25 | 0.0011664 | 350 | 0.053073 | 8251 | 6.1902e-05 | 3615
CATLETT 1101CB | CATLETT 1101 | 153761101 |  | 0.025009 | 0 |  | 1 | 0.00079878 | 1981 | 0.0774 | 3397 | 6.1826e-05 | 3616
CHICO A 1102CB | CHICO A 1102 | 102051102 |  | 4.2864 | 3.7472 |  | 55.75 | 0.0011645 | 352 | 0.053073 | 8252 | 6.1802e-05 | 3617
LONE TREE 2101625622 | LONE TREE 2101 | 13232101 |  | 1.3835 | 0.02627 |  | 21 | 0.00090768 | 1199 | 0.067992 | 5406 | 6.178e-05 | 3618
COTATI 1105328 | COTATI 1105 | 42271105 | FALSE | 13.8528 | 4.5154 | 1.6719 | 256.5 | 0.00022784 | 9539 | 0.27393 | 3052 | 6.1752e-05 | 3619
SUISUN 1112CB | SUISUN 1112 | 62131112 |  | 2.8452 | 0.32208 |  | 52.3333 | 0.00095054 | 1010 | 0.064674 | 6475 | 6.1729e-05 | 3620
TEVIS 2102CB | TEVIS 2102 | 255322102 |  | 1.2293 | 0.034631 |  | 20.3333 | 0.001163 | 353 | 0.053073 | 8252 | 6.1721e-05 | 3621
SF H 1103CB | SF H 1103 | 22101103 |  | 1.0221 | 0.18039 |  | 5.7512 | 0.0011628 | 354 | 0.053073 | 8250 | 6.1713e-05 | 3622
WESTPARK 110115325 | WESTPARK 1101 | 253701101 |  | 0.74734 | 0.39226 |  | 10 | 0.0011625 | 356 | 0.053073 | 8251 | 6.1695e-05 | 3623
MILLBRAE 1108639978 | MILLBRAE 1108 | 22691108 |  | 5.2975 | 3.6944 |  | 82.25 | 0.00066485 | 3500 | 0.081512 | 3382 | 6.1673e-05 | 3624
PLACER 1103238990 | PLACER 1103 | 152461103 | TRUE | 6.0504 | 2.9657 | 0.034486 | 113 | 0.00058327 | 4490 | 0.10642 | 3302 | 6.1671e-05 | 3625
DEL MAR 1103CB | DEL MAR 1103 | 152581103 |  | 1.9719 | 0.59848 |  | 30 | 0.00099305 | 818 | 0.061976 | 6767 | 6.1659e-05 | 3626
BULLARD 1106CB | BULLARD 1106 | 253961106 |  | 2.2549 | 2.1266 |  | 24.4167 | 0.0011616 | 358 | 0.053073 | 8251 | 6.1651e-05 | 3627
KIRKER 2108CB | KIRKER 2108 | 14452108 |  | 7.0886 | 4.3344 |  | 99.75 | 0.0010805 | 525 | 0.057162 | 7410 | 6.1574e-05 | 3628
FORT BRAGG A 1104CB | FORT BRAGG A 1104 | 42761104 |  | 2.8574 | 1.8066 |  | 44.5833 | 0.00053271 | 5040 | 0.094246 | 3330 | 6.1568e-05 | 3629
WEBER 1108CB | WEBER 1108 | 163481108 |  | 0.51045 | 0.21325 |  | 10 | 0.00116 | 359 | 0.053073 | 8251 | 6.1563e-05 | 3630
CLOVIS 211138754 | CLOVIS 2111 | 254082111 |  | 2.4129 | 2.276 |  | 36.5 | 0.0011522 | 368 | 0.053406 | 8130 | 6.154e-05 | 3631
MISSION (X) 111014601 | MISSION (X) 1110 | 22011110 |  | 0.076606 | 0 |  | 0.66667 | 0.0011594 | 360 | 0.053073 | 8251 | 6.1532e-05 | 3632
PAUL SWEET 21075134 | PAUL SWEET 2107 | 83252107 | TRUE | 3.0327 | 0.16078 | 0.53509 | 59 | 0.00030577 | 7891 | 0.2442 | 3090 | 6.1481e-05 | 3633
DAVIS 110323092 | DAVIS 1103 | 62041103 |  | 0.012784 | 0 |  | 0.5 | 0.00079433 | 2015 | 0.0774 | 3397 | 6.1481e-05 | 3634
STOCKDALE 211073058 | STOCKDALE 2110 | 254072110 |  | 1.6805 | 1.8322 |  | 27 | 0.0011584 | 362 | 0.053073 | 8251 | 6.1477e-05 | 3635
LAS GALLINAS A 11051218 | LAS GALLINAS A 1105 | 42991105 | TRUE | 2.3409 | 2.3689 | 0.079603 | 39.8333 | 0.00061411 | 4120 | 0.10808 | 3296 | 6.1461e-05 | 3636
MILLBRAE 1101CB | MILLBRAE 1101 | 22691101 |  | 0.53661 | 0.039111 |  | 5.8667 | 0.0011189 | 432 | 0.054853 | 7780 | 6.1443e-05 | 3637
BAKERSFIELD 210990726 | BAKERSFIELD 2109 | 253372109 |  | 5.9364 | 5.0261 |  | 96.5 | 0.0011572 | 363 | 0.053073 | 8251 | 6.1416e-05 | 3638
EL CERRITO G 1105CB | EL CERRITO G 1105 | 12501105 | FALSE | 7.4343 | 6.381 | 13.8129 | 121.3333 | 0.00047032 | 5697 | 0.14207 | 3226 | 6.1403e-05 | 3639
SERRAMONTE 110312787 | SERRAMONTE 1103 | 22861103 |  | 0.092451 | 0.063527 |  | 3.3333 | 0.0009739 | 901 | 0.063518 | 6610 | 6.13e-05 | 3640
WEBER 11029448 | WEBER 1102 | 163481102 |  | 0.011364 | 0 |  | 0.25 | 0.00079148 | 2051 | 0.0774 | 3397 | 6.126e-05 | 3641
TIDEWATER 2107CB | TIDEWATER 2107 | 14652107 |  | 8.0849 | 4.5374 |  | 107.75 | 0.0010948 | 484 | 0.055593 | 7660 | 6.1259e-05 | 3642
WEBER 1112CB | WEBER 1112 | 163481112 |  | 0.018828 | 0 |  | 0.58333 | 0.00079113 | 2055 | 0.0774 | 3396 | 6.1233e-05 | 3643
SALMON CREEK 1101196 | SALMON CREEK 1101 | 43161101 | FALSE | 7.2861 | 0.14153 | 3.7231 | 146 | 9.3635e-05 | 11070 | 0.7662 | 2586 | 6.1181e-05 | 3644
GOLDTREE 1108961060 | GOLDTREE 1108 | 182581108 | FALSE | 14.6222 | 10.2143 | 1.4975 | 244.5 | 0.00050973 | 5287 | 0.20131 | 3141 | 6.1169e-05 | 3645
CALIFORNIA AVE 1113CB | CALIFORNIA AVE 1113 | 252281113 |  | 3.559 | 3.7844 |  | 68.25 | 0.0011519 | 369 | 0.053073 | 8253 | 6.1134e-05 | 3646
LAMONT 11029785 | LAMONT 1102 | 253911102 | TRUE | 5.2009 | 0.12635 | 0.42618 | 89.5 | 0.00028819 | 8230 | 0.28593 | 3035 | 6.1124e-05 | 3647
VINEYARD 2108CB | VINEYARD 2108 | 14502108 |  | 2.2301 | 1.097 |  | 28 | 0.0011433 | 377 | 0.05357 | 8074 | 6.1116e-05 | 3648
FIGARDEN 211093078 | FIGARDEN 2110 | 254552110 |  | 0.85662 | 0.2887 |  | 11 | 0.0010575 | 591 | 0.058602 | 7211 | 6.1109e-05 | 3649
LOYOLA 1102LL12 | LOYOLA 1102 | 82161102 |  | 0.8627 | 0.27713 |  | 15.5 | 0.00086925 | 1428 | 0.070144 | 5011 | 6.108e-05 | 3650
CONCORD NO 1 040165618 | CONCORD NO 1 0401 | 12960401 |  | 0.032302 | 0 |  | 1 | 0.00091086 | 1180 | 0.067 | 6057 | 6.1028e-05 | 3651
CORDELIA 1102CB | CORDELIA 1102 | 62701102 |  | 0.04273 | 0 |  | 0.2 | 0.0009105 | 1182 | 0.067 | 6057 | 6.1003e-05 | 3652
CORDELIA 1101CB | CORDELIA 1101 | 62701101 |  | 0.019146 | 0 |  | 0.2 | 0.0009105 | 1182 | 0.067 | 6057 | 6.1003e-05 | 3652
RENFRO 210587494 | RENFRO 2105 | 254572105 |  | 1.4708 | 0.050544 |  | 21.8333 | 0.0010883 | 499 | 0.056252 | 7541 | 6.0989e-05 | 3653
SWIFT 2106CB | SWIFT 2106 | 83392106 |  | 1.0232 | 0.23271 |  | 20.5 | 0.0011491 | 370 | 0.053073 | 8251 | 6.0985e-05 | 3654
WEST FRESNO 1108CB | WEST FRESNO 1108 | 253731108 |  | 2.4739 | 1.6651 |  | 36.5 | 0.0011476 | 371 | 0.053073 | 8251 | 6.0908e-05 | 3655
ROSSMOOR 110654472 | ROSSMOOR 1106 | 14161106 |  | 4.6076 | 3.0882 |  | 82.8333 | 0.00066861 | 3451 | 0.10345 | 3308 | 6.0902e-05 | 3656
BURLINGAME 04019058 | BURLINGAME 0401 | 24050401 |  | 0.04372 | 0.058769 |  | 1.8333 | 0.0010623 | 579 | 0.056871 | 7456 | 6.0847e-05 | 3657
BULLARD 1110CB | BULLARD 1110 | 253961110 |  | 1.7125 | 0.69387 |  | 24.5 | 0.0011454 | 372 | 0.053073 | 8251 | 6.079e-05 | 3658
WEEDPATCH 110315958 | WEEDPATCH 1103 | 252971103 |  | 0.46663 | 0.63221 |  | 6.8333 | 0.0010544 | 603 | 0.057864 | 7314 | 6.0776e-05 | 3659
MANCHESTER 1105CB | MANCHESTER 1105 | 253921105 |  | 1.4402 | 0.22259 |  | 33.75 | 0.001145 | 373 | 0.053073 | 8251 | 6.0768e-05 | 3660
SAN RAMON 2114CB | SAN RAMON 2114 | 14232114 |  | 1.6966 | 0.79055 |  | 33.75 | 0.0010637 | 573 | 0.056629 | 7485 | 6.0723e-05 | 3661
RIO DELL 1102CB | RIO DELL 1102 | 192251102 |  | 7.0723 | 4.1561 |  | 110.5 | 0.00059609 | 4347 | 0.11039 | 3292 | 6.0714e-05 | 3662
OAKLAND J 1110CR272 | OAKLAND J 1110 | 12091110 |  | 0.70716 | 0.061225 |  | 10.5 | 0.0011436 | 374 | 0.053073 | 8251 | 6.0696e-05 | 3663
WESTPARK 1111CB | WESTPARK 1111 | 253701111 |  | 5.2171 | 3.4804 |  | 67.1667 | 0.0011434 | 376 | 0.053073 | 8252 | 6.0686e-05 | 3664
KIRKER 210688828 | KIRKER 2106 | 14452106 |  | 3.9817 | 1.646 |  | 43.0833 | 0.0011146 | 443 | 0.054096 | 7930 | 6.0676e-05 | 3665
CLARKSVILLE 2103CB | CLARKSVILLE 2103 | 153612103 |  | 1.4366 | 0.027707 |  | 29.75 | 0.00093622 | 1066 | 0.065415 | 6375 | 6.0672e-05 | 3666
TRACY 110611538 | TRACY 1106 | 162881106 |  | 0.017551 | 0 |  | 0.5 | 0.0011422 | 379 | 0.053073 | 8251 | 6.0621e-05 | 3667
7TH STANDARD 2103250354 | 7TH STANDARD 2103 | 254582103 |  | 0.014481 | 0 |  | 0.5 | 0.0007832 | 2117 | 0.0774 | 3397 | 6.0619e-05 | 3668
EDES 1101CB | EDES 1101 | 13681101 |  | 0.5751 | 0.27318 |  | 6.3333 | 0.0011421 | 380 | 0.053073 | 8251 | 6.0615e-05 | 3669
PINEDALE 2106CB | PINEDALE 2106 | 252852106 |  | 2.8841 | 2.1074 |  | 40.5 | 0.0011421 | 381 | 0.053073 | 8251 | 6.0614e-05 | 3670
CONTRA COSTA 21032212 | CONTRA COSTA 2103 | 13652103 |  | 0.011364 | 0 |  | 0.5 | 0.0011416 | 382 | 0.053073 | 8251 | 6.0589e-05 | 3671
SF H 0403CB | SF H 0403 | 22100403 |  | 1.0642 | 1.0708 |  | 10.4179 | 0.001141 | 385 | 0.053073 | 8252 | 6.0556e-05 | 3672
WOODLAND 1112CB | WOODLAND 1112 | 62031112 |  | 1.0405 | 0.29001 |  | 17 | 0.0011405 | 386 | 0.053073 | 8251 | 6.0527e-05 | 3673
ASHLAN AVE 2117R1100 | ASHLAN AVE 2117 | 252052117 |  | 1.8611 | 0.91759 |  | 29.5 | 0.00114 | 388 | 0.053073 | 8251 | 6.0502e-05 | 3674
CLOVIS 2110R3070 | CLOVIS 2110 | 254082110 |  | 4.2116 | 4.6171 |  | 53.5 | 0.00114 | 389 | 0.053073 | 8251 | 6.0502e-05 | 3675
BARTON 1105167170 | BARTON 1105 | 253571105 |  | 0.018909 | 0 |  | 0.33333 | 0.00114 | 390 | 0.053073 | 8251 | 6.0501e-05 | 3676
CALISTOGA 1102640833 | CALISTOGA 1102 | 42711102 |  | 0.011839 | 0 |  | 0.5 | 0.0008359 | 1674 | 0.072349 | 4740 | 6.0477e-05 | 3677
STOCKDALE 1105CB | STOCKDALE 1105 | 254071105 |  | 0.56667 | 0 |  | 6.7833 | 0.0011393 | 391 | 0.053073 | 8251 | 6.0463e-05 | 3678
VACAVILLE 110541272 | VACAVILLE 1105 | 63601105 |  | 0.015669 | 0 |  | 0.33333 | 0.0011392 | 392 | 0.053073 | 8251 | 6.0462e-05 | 3679
HAMILTON BRANCH 110137534 | HAMILTON BRANCH 1101 | 102361101 |  | 2.5138 | 1.8158 |  | 53.5 | 0.00043332 | 6081 | 0.13785 | 3239 | 6.0454e-05 | 3680
MT EDEN 1106MR668 | MT EDEN 1106 | 13761106 |  | 0.081011 | 0 |  | 0.58333 | 0.001139 | 393 | 0.053073 | 8250 | 6.0447e-05 | 3681
SHEPHERD 2110R1660 | SHEPHERD 2110 | 252062110 |  | 2.5063 | 1.5677 |  | 41.8333 | 0.0011386 | 394 | 0.053073 | 8251 | 6.0428e-05 | 3682
BULLARD 1101CB | BULLARD 1101 | 253961101 |  | 1.8628 | 0.016574 |  | 25 | 0.0010333 | 670 | 0.057857 | 7316 | 6.0397e-05 | 3683
FLORENCE 0401CR220 | FLORENCE 0401 | 12690401 | TRUE | 1.3396 | 1.1982 | 0.36624 | 24.5 | 0.00052172 | 5160 | 0.11209 | 3288 | 6.038e-05 | 3684
ASHLAN AVE 1111CB | ASHLAN AVE 1111 | 252051111 |  | 2.2405 | 1.3557 |  | 26.75 | 0.0011376 | 396 | 0.053073 | 8251 | 6.0376e-05 | 3685
CHICO A 110291814 | CHICO A 1102 | 102051102 |  | 2.8218 | 2.5358 |  | 47.3333 | 0.0010299 | 688 | 0.057934 | 7303 | 6.0369e-05 | 3686
TEVIS 2105CB | TEVIS 2105 | 255322105 |  | 1.3125 | 0 |  | 19.3333 | 0.0011374 | 397 | 0.053073 | 8251 | 6.0365e-05 | 3687
PEABODY 211357908 | PEABODY 2113 | 63642113 |  | 1.7242 | 0.091306 |  | 16.9167 | 0.0010189 | 727 | 0.060364 | 6978 | 6.0332e-05 | 3688
RENFRO 2105536906 | RENFRO 2105 | 254572105 |  | 0.0028408 | 0 |  | 0.5 | 0.0011362 | 398 | 0.053073 | 8251 | 6.0302e-05 | 3689
MILPITAS 2112CB | MILPITAS 2112 | 82832112 |  | 0.62318 | 0.020088 |  | 11.6667 | 0.0011359 | 400 | 0.053073 | 8251 | 6.0283e-05 | 3690
STOCKDALE 2112CB | STOCKDALE 2112 | 254072112 |  | 5.653 | 0.025454 |  | 70.5 | 0.00093608 | 1068 | 0.066876 | 6100 | 6.0203e-05 | 3691
NEWARK 21KV 2105MR826 | NEWARK 21KV 2105 | 12232105 |  | 0.060532 | 0 |  | 1.5 | 0.001134 | 404 | 0.053073 | 8251 | 6.0184e-05 | 3692
PACIFICA 1102CB | PACIFICA 1102 | 22811102 | TRUE | 3.8865 | 3.1932 | 0.20481 | 69 | 0.00074855 | 2499 | 0.071107 | 4882 | 6.017e-05 | 3693
CALIFORNIA AVE 1114D6429 | CALIFORNIA AVE 1114 | 252281114 |  | 0.18522 | 0.48243 |  | 4.3333 | 0.0011336 | 406 | 0.053073 | 8250 | 6.0162e-05 | 3694
STONE 1109XR514 | STONE 1109 | 83701109 |  | 0.019726 | 0 |  | 0.33333 | 0.0011335 | 407 | 0.053073 | 8251 | 6.0156e-05 | 3695
DEL MONTE 1101CB | DEL MONTE 1101 | 182221101 |  | 0.37837 | 0.31403 |  | 7.3333 | 0.0011133 | 447 | 0.054022 | 7947 | 6.0156e-05 | 3696
ROSSMOOR 110665858 | ROSSMOOR 1106 | 14161106 |  | 1.1384 | 0.46763 |  | 19.3333 | 0.00088504 | 1336 | 0.067944 | 5416 | 6.0133e-05 | 3697
DIXON LANDING 2101CB | DIXON LANDING 2101 | 14722101 |  | 0.039699 | 0 |  | 1 | 0.0011329 | 408 | 0.053073 | 8251 | 6.0124e-05 | 3698
BAKERSFIELD 11141505 | BAKERSFIELD 1114 | 253371114 |  | 4.8304 | 5.1226 |  | 79.8333 | 0.0011317 | 409 | 0.053073 | 8252 | 6.0064e-05 | 3699
PAUL SWEET 210210290 | PAUL SWEET 2102 | 83252102 |  | 5.7646 | 3.353 |  | 74.5333 | 0.00080834 | 1909 | 0.083729 | 3378 | 6.0064e-05 | 3700
CLOVIS 210992532 | CLOVIS 2109 | 254082109 |  | 0.82059 | 0.63673 |  | 15.6667 | 0.0011313 | 410 | 0.053073 | 8252 | 6.0043e-05 | 3701
FIGARDEN 210765564 | FIGARDEN 2107 | 254552107 |  | 0.40932 | 0.14126 |  | 7.5 | 0.0010723 | 552 | 0.056316 | 7528 | 6.0035e-05 | 3702
STOCKTON A 0406CB | STOCKTON A 0406 | 162370406 |  | 3.2845 | 2.7235 |  | 34.4333 | 0.001131 | 411 | 0.053073 | 8251 | 6.0026e-05 | 3703
WYANDOTTE 1102CB | WYANDOTTE 1102 | 102911102 |  | 6.4249 | 4.809 |  | 80 | 0.0010317 | 679 | 0.057382 | 7377 | 5.9991e-05 | 3704
PEABODY 211218312 | PEABODY 2112 | 63642112 |  | 0.34726 | 0 |  | 9 | 0.0010172 | 734 | 0.060048 | 7012 | 5.9971e-05 | 3705
ROSSMOOR 110192164 | ROSSMOOR 1101 | 14161101 |  | 0.97961 | 0.78625 |  | 19.6667 | 0.00078604 | 2089 | 0.083557 | 3379 | 5.9944e-05 | 3706
PEABODY 2104CB | PEABODY 2104 | 63642104 |  | 2.5891 | 0.0075043 |  | 24.6167 | 0.00099153 | 823 | 0.062505 | 6715 | 5.9936e-05 | 3707
SAN JOSE B 1107CB | SAN JOSE B 1107 | 82261107 |  | 0.49862 | 0.44242 |  | 5.25 | 0.0011288 | 416 | 0.053073 | 8250 | 5.9906e-05 | 3708
MANCHESTER 1108CB | MANCHESTER 1108 | 253921108 |  | 14.3701 | 12.992 |  | 200.6667 | 0.0011287 | 417 | 0.053073 | 8252 | 5.9902e-05 | 3709
TASSAJARA 210875010 | TASSAJARA 2108 | 14662108 |  | 2.0642 | 0.60055 |  | 25.6667 | 0.00091277 | 1176 | 0.064899 | 6451 | 5.9894e-05 | 3710
FIGARDEN 211353111 | FIGARDEN 2113 | 254552113 |  | 0.20152 | 0 |  | 2.5 | 0.0010241 | 709 | 0.057938 | 7300 | 5.9883e-05 | 3711
ASHLAN AVE 1108CB | ASHLAN AVE 1108 | 252051108 |  | 6.4457 | 1.8676 |  | 66.3667 | 0.0011281 | 418 | 0.053073 | 8253 | 5.9873e-05 | 3712
LAS GALLINAS A 1107554 | LAS GALLINAS A 1107 | 42991107 | TRUE | 3.7293 | 3.6453 | 0.044534 | 57.8333 | 0.00071141 | 2957 | 0.099219 | 3315 | 5.9855e-05 | 3713
EL PATIO 1119CB | EL PATIO 1119 | 82921119 |  | 2.3592 | 1.5431 |  | 34.8333 | 0.0011273 | 419 | 0.053073 | 8250 | 5.9831e-05 | 3714
RIO BRAVO 1104231800 | RIO BRAVO 1104 | 252861104 |  | 0.070876 | 0 |  | 1.5 | 0.00077245 | 2234 | 0.0774 | 3397 | 5.9787e-05 | 3715
ALTO 112088190 | ALTO 1120 | 42031120 | TRUE | 2.8825 | 2.069 | 0.059208 | 39.1667 | 0.00061863 | 4061 | 0.088797 | 3348 | 5.978e-05 | 3716
PAUL SWEET 21075291 | PAUL SWEET 2107 | 83252107 | TRUE | 0.99187 | 0.45532 | 0.031341 | 22 | 0.00051526 | 5229 | 0.09657 | 3323 | 5.9776e-05 | 3717
VACA DIXON 1105965390 | VACA DIXON 1105 | 63591105 | TRUE | 1.6069 | 0.2043 | 0.57011 | 30.5 | 0.00020878 | 9898 | 0.76473 | 2589 | 5.9765e-05 | 3718
DAVIS 1109CB | DAVIS 1109 | 62041109 |  | 1.8518 | 0.7885 |  | 21.3667 | 0.0011255 | 422 | 0.053073 | 8250 | 5.9732e-05 | 3719
MONROE 2102CB | MONROE 2102 | 43302102 |  | 2.6426 | 0.61782 |  | 38 | 0.0011254 | 423 | 0.053073 | 8251 | 5.9727e-05 | 3720
TIDEWATER 210618972 | TIDEWATER 2106 | 14652106 |  | 0.0291 | 0 |  | 0.33333 | 0.00088823 | 1311 | 0.06721 | 5799 | 5.9698e-05 | 3721
EAST GRAND 1108CB | EAST GRAND 1108 | 22571108 |  | 2.3022 | 0.84309 |  | 30 | 0.0011247 | 425 | 0.053073 | 8251 | 5.9691e-05 | 3722
SWIFT 2107XR102 | SWIFT 2107 | 83392107 |  | 0.93942 | 0.53283 |  | 19.5 | 0.00093919 | 1053 | 0.063248 | 6639 | 5.9683e-05 | 3723
EIGHT MILE 2106CB | EIGHT MILE 2106 | 163912106 |  | 2.2094 | 0 |  | 37 | 0.00088473 | 1338 | 0.069085 | 5177 | 5.967e-05 | 3724
FORT ORD 2107CB | FORT ORD 2107 | 182402107 |  | 1.8303 | 0.22459 |  | 16.5833 | 0.00097722 | 882 | 0.061261 | 6862 | 5.9655e-05 | 3725
CONTRA COSTA 2103435976 | CONTRA COSTA 2103 | 13652103 |  | 0.59162 | 0.030687 |  | 8.5 | 0.00088967 | 1301 | 0.067 | 6057 | 5.9608e-05 | 3726
BAY MEADOWS 1108CB | BAY MEADOWS 1108 | 24011108 |  | 1.0478 | 0.021382 |  | 10.8333 | 0.0011229 | 426 | 0.053073 | 8251 | 5.9596e-05 | 3727
KERN POWER 210594407 | KERN POWER 2105 | 255262105 |  | 1.0832 | 0.069287 |  | 19 | 0.0011129 | 449 | 0.053978 | 7961 | 5.9579e-05 | 3728
VIERRA 1701CB | VIERRA 1701 | 162701701 |  | 1.5828 | 0.055647 |  | 27.8333 | 0.00089754 | 1247 | 0.067597 | 5551 | 5.9569e-05 | 3729
CHICO A 11012604 | CHICO A 1101 | 102051101 |  | 5.1591 | 4.683 |  | 93.1667 | 0.0009824 | 857 | 0.060547 | 6951 | 5.9545e-05 | 3730
CHICO A 0401CB | CHICO A 0401 | 102050401 |  | 2.1977 | 2.0859 |  | 32.4167 | 0.0010867 | 507 | 0.05472 | 7800 | 5.9519e-05 | 3731
BAKERSFIELD 111413932 | BAKERSFIELD 1114 | 253371114 |  | 0.87046 | 0.99542 |  | 15 | 0.0011207 | 428 | 0.053073 | 8251 | 5.9477e-05 | 3732
PUEBLO 110247720 | PUEBLO 1102 | 43291102 |  | 0.34275 | 0.12459 |  | 7.5 | 0.00088845 | 1308 | 0.066603 | 6168 | 5.9451e-05 | 3733
BULLARD 110165566 | BULLARD 1101 | 253961101 |  | 1.7432 | 0.91811 |  | 24.6667 | 0.0011196 | 430 | 0.053073 | 8251 | 5.9422e-05 | 3734
BURLINGAME 2101CB | BURLINGAME 2101 | 24052101 |  | 1.3496 | 0.44322 |  | 15.4167 | 0.0011195 | 431 | 0.053073 | 8252 | 5.9415e-05 | 3735
SILVERADO 2105768606 | SILVERADO 2105 | 43432105 |  | 0.32961 | 0.073305 |  | 7 | 0.00076896 | 2275 | 0.077219 | 3574 | 5.9388e-05 | 3736
LUCERNE 11031280 | LUCERNE 1103 | 43351103 | FALSE | 18.5798 | 2.4372 | 3.1461 | 339.3333 | 0.00031437 | 7732 | 0.23595 | 3099 | 5.9361e-05 | 3737
STOCKDALE 21104143 | STOCKDALE 2110 | 254072110 |  | 2.7584 | 1.6664 |  | 39 | 0.0011181 | 433 | 0.053073 | 8251 | 5.9341e-05 | 3738
HIGHWAY 1104976 | HIGHWAY 1104 | 42651104 |  | 0.81953 | 0.55773 |  | 11 | 0.0010944 | 486 | 0.05496 | 7755 | 5.9334e-05 | 3739
ROSSMOOR 1104305926 | ROSSMOOR 1104 | 14161104 |  | 0.10413 | 0.035597 |  | 3 | 0.00088523 | 1335 | 0.067 | 6057 | 5.931e-05 | 3740
DAVIS 1111CB | DAVIS 1111 | 62041111 |  | 1.0677 | 0.53494 |  | 15.75 | 0.0011172 | 438 | 0.053073 | 8252 | 5.9291e-05 | 3741
SARATOGA 1103CB | SARATOGA 1103 | 83371103 |  | 1.2633 | 0.67517 |  | 19.5 | 0.0011171 | 439 | 0.053073 | 8251 | 5.9285e-05 | 3742
RENFRO 2107515188 | RENFRO 2107 | 254572107 |  | 1.1858 | 0.054745 |  | 17.5 | 0.00077857 | 2161 | 0.07601 | 4197 | 5.9285e-05 | 3743
STOREY 1107CB | STOREY 1107 | 254611107 |  | 0.86205 | 0.34527 |  | 11.9167 | 0.0008199 | 1820 | 0.072296 | 4744 | 5.9236e-05 | 3744
MANTECA 170875060 | MANTECA 1708 | 162611708 |  | 0.91062 | 0.049459 |  | 12.6667 | 0.0011157 | 441 | 0.053073 | 8252 | 5.9214e-05 | 3745
MORAGA 110531512 | MORAGA 1105 | 13801105 |  | 2.0341 | 0.44365 |  | 31.8333 | 0.00060647 | 4223 | 0.11331 | 3281 | 5.9129e-05 | 3746
PINEDALE 210155278 | PINEDALE 2101 | 252852101 |  | 0.01457 | 0 |  | 1.5 | 0.0011141 | 444 | 0.053073 | 8251 | 5.9128e-05 | 3747
MALAGA 110968312 | MALAGA 1109 | 254251109 |  | 0.28759 | 0 |  | 3.8333 | 0.001114 | 445 | 0.053073 | 8250 | 5.9125e-05 | 3748
BAKERSFIELD 11061912 | BAKERSFIELD 1106 | 253371106 |  | 4.1214 | 5.2162 |  | 77.8333 | 0.0011126 | 450 | 0.053073 | 8251 | 5.9047e-05 | 3749
WESTPARK 1108CB | WESTPARK 1108 | 253701108 |  | 7.6961 | 4.2417 |  | 98.8333 | 0.0011122 | 453 | 0.053073 | 8251 | 5.903e-05 | 3750
MAGUNDEN 21084505 | MAGUNDEN 2108 | 252772108 |  | 2.0438 | 0.16993 |  | 29.5 | 0.0010827 | 520 | 0.055838 | 7607 | 5.9015e-05 | 3751
CHICO B 1103CB | CHICO B 1103 | 102491103 |  | 1.2888 | 0.76576 |  | 20.5 | 0.0010432 | 640 | 0.05647 | 7505 | 5.8993e-05 | 3752
OAKLAND D 1103CB | OAKLAND D 1103 | 12041103 |  | 0.33908 | 0.095521 |  | 4.6667 | 0.0011113 | 455 | 0.053073 | 8250 | 5.8982e-05 | 3753
HILLSDALE 0401CB | HILLSDALE 0401 | 24110401 |  | 0.10508 | 0 |  | 1.25 | 0.00087999 | 1365 | 0.067 | 6055 | 5.896e-05 | 3754
CLARKSVILLE 2106CB | CLARKSVILLE 2106 | 153612106 | TRUE | 0.51246 | 0 | 0.014002 | 10.5833 | 0.00087916 | 1372 | 0.067036 | 5969 | 5.8937e-05 | 3755
KERN OIL 110313885 | KERN OIL 1103 | 252721103 |  | 0.69238 | 0.8591 |  | 11 | 0.0011099 | 458 | 0.053073 | 8251 | 5.8904e-05 | 3756
SAN RAFAEL 1106588020 | SAN RAFAEL 1106 | 42011106 | TRUE | 1.7958 | 1.4712 | 0.13579 | 26.0833 | 0.00066837 | 3453 | 0.10665 | 3300 | 5.8894e-05 | 3757
MOSHER 210747888 | MOSHER 2107 | 163722107 |  | 1.6949 | 0.76167 |  | 25.3333 | 0.00085743 | 1514 | 0.068437 | 5299 | 5.8878e-05 | 3758
CLOVIS 1106CB | CLOVIS 1106 | 254081106 |  | 4.9908 | 2.7931 |  | 68.75 | 0.0010997 | 471 | 0.053427 | 8117 | 5.8863e-05 | 3759
PALMER 1101M88 | PALMER 1101 | 183031101 | FALSE | 15.5234 | 0.20118 | 1.9621 | 285 | 0.00020383 | 9984 | 0.2885 | 3030 | 5.8847e-05 | 3760
VASONA 1102944322 | VASONA 1102 | 83771102 |  | 0.14031 | 0 |  | 1.8333 | 0.0011083 | 461 | 0.053073 | 8251 | 5.8819e-05 | 3761
STOCKDALE 1109CB | STOCKDALE 1109 | 254071109 |  | 2.8051 | 0.13468 |  | 38.8333 | 0.0010347 | 667 | 0.057329 | 7391 | 5.8805e-05 | 3762
EDENVALE 2110CB | EDENVALE 2110 | 82952110 |  | 0.0029578 | 0 |  | 0.33333 | 0.0011079 | 462 | 0.053073 | 8251 | 5.8801e-05 | 3763
MEADOW LANE 2104CB | MEADOW LANE 2104 | 14302104 |  | 4.1654 | 3.0521 |  | 65.3333 | 0.0010542 | 604 | 0.055443 | 7682 | 5.8783e-05 | 3764
CHICO A 1103CB | CHICO A 1103 | 102051103 |  | 4.8664 | 3.2166 |  | 70.5 | 0.001013 | 753 | 0.058256 | 7259 | 5.8761e-05 | 3765
STOCKDALE 1108CB | STOCKDALE 1108 | 254071108 |  | 1.5914 | 1.1083 |  | 22.8333 | 0.0011072 | 463 | 0.053073 | 8251 | 5.8761e-05 | 3766
STOCKTON A 1101CB | STOCKTON A 1101 | 162371101 |  | 4.0695 | 1.6432 |  | 43.8167 | 0.0011062 | 464 | 0.053073 | 8252 | 5.8706e-05 | 3767
DAVIS 1110CB | DAVIS 1110 | 62041110 |  | 1.8306 | 0.092774 |  | 28.3333 | 0.0010972 | 478 | 0.053502 | 8096 | 5.8701e-05 | 3768
ALTO 1120CB | ALTO 1120 | 42031120 |  | 1.665 | 0.92276 |  | 26.6667 | 0.00084054 | 1645 | 0.070098 | 5023 | 5.8671e-05 | 3769
CLAY 110113450 | CLAY 1101 | 163341101 | TRUE | 4.8433 | 0.86997 | 0.57457 | 94.5 | 0.00042189 | 6206 | 0.21613 | 3122 | 5.8656e-05 | 3770
ROSSMOOR 1107857172 | ROSSMOOR 1107 | 14161107 | TRUE | 1.1698 | 0.59478 | 0.059962 | 19 | 0.00059294 | 4383 | 0.124 | 3261 | 5.8603e-05 | 3771
STOCKTON A 1108CB | STOCKTON A 1108 | 162371108 |  | 2.7297 | 1.1008 |  | 36.4 | 0.0011025 | 466 | 0.053073 | 8251 | 5.8511e-05 | 3772
BAKERSFIELD 210913002 | BAKERSFIELD 2109 | 253372109 |  | 0.55891 | 0.58729 |  | 11 | 0.0011024 | 467 | 0.053073 | 8251 | 5.8507e-05 | 3773
EL CAPITAN 11039700 | EL CAPITAN 1103 | 253881103 |  | 1.2369 | 0 |  | 7.6667 | 0.0010835 | 514 | 0.05413 | 7920 | 5.8503e-05 | 3774
LAURELES 1112CB | LAURELES 1112 | 182371112 | TRUE | 2.3816 | 1.3933 | 0.062742 | 46 | 0.00083374 | 1696 | 0.070203 | 5002 | 5.8487e-05 | 3775
EL PATIO 1118CB | EL PATIO 1118 | 82921118 |  | 1.1579 | 0.70217 |  | 17.1667 | 0.0011013 | 468 | 0.053073 | 8252 | 5.8447e-05 | 3776
SAN RAMON 2116CB | SAN RAMON 2116 | 14232116 |  | 0.0028409 | 0 |  | 0.5 | 0.001101 | 469 | 0.053073 | 8251 | 5.8432e-05 | 3777
SAN RAFAEL 1106CB | SAN RAFAEL 1106 | 42011106 |  | 0.99017 | 1.0036 |  | 10.9167 | 0.0010214 | 718 | 0.057644 | 7339 | 5.8431e-05 | 3778
DAVIS 1104CB | DAVIS 1104 | 62041104 |  | 1.8868 | 1.3611 |  | 22.2 | 0.0011003 | 470 | 0.053073 | 8251 | 5.8395e-05 | 3779
SYCAMORE CREEK 1102CB | SYCAMORE CREEK 1102 | 102971102 |  | 5.9158 | 2.9967 |  | 88.5 | 0.001032 | 677 | 0.05622 | 7543 | 5.8371e-05 | 3780
RICHMOND R 1122CB | RICHMOND R 1122 | 13471122 |  | 2.2089 | 1.7347 |  | 35.6667 | 0.001051 | 619 | 0.058585 | 7213 | 5.8362e-05 | 3781
CALISTOGA 1102102918 | CALISTOGA 1102 | 42711102 |  | 0.33936 | 0.15263 |  | 7 | 0.00080688 | 1920 | 0.072319 | 4743 | 5.8356e-05 | 3782
EEL RIVER 110249130 | EEL RIVER 1102 | 192381102 |  | 13.8478 | 1.2459 |  | 266.5 | 0.0002132 | 9817 | 0.21357 | 3126 | 5.8355e-05 | 3783
KERN OIL 11108628 | KERN OIL 1110 | 252721110 |  | 0.86693 | 1.0959 |  | 13.8333 | 0.0010989 | 472 | 0.053073 | 8251 | 5.8324e-05 | 3784
STAGG 21066650 | STAGG 2106 | 162422106 |  | 0.011272 | 0 |  | 0.5 | 0.0010988 | 473 | 0.053073 | 8251 | 5.8315e-05 | 3785
MEADOW LANE 2107C589R | MEADOW LANE 2107 | 14302107 |  | 3.8033 | 2.797 |  | 62 | 0.0010983 | 475 | 0.053073 | 8251 | 5.8288e-05 | 3786
CORRAL 1103936674 | CORRAL 1103 | 162991103 | TRUE | 3.9537 | 0.73998 | 0.44257 | 76.5 | 0.00023032 | 9479 | 0.28643 | 3034 | 5.8273e-05 | 3787
ASHLAN AVE 1114CB | ASHLAN AVE 1114 | 252051114 |  | 6.3994 | 5.7803 |  | 91.8333 | 0.0010977 | 477 | 0.053073 | 8252 | 5.8255e-05 | 3788
PLACER 1101208930 | PLACER 1101 | 152461101 | TRUE | 0.89072 | 0.48677 | 0.074855 | 15 | 0.00071538 | 2908 | 0.14409 | 3220 | 5.8253e-05 | 3789
TASSAJARA 2112CB | TASSAJARA 2112 | 14662112 | TRUE | 1.3202 | 0.13957 | 0.15409 | 24 | 0.00094455 | 1031 | 0.063138 | 6652 | 5.8224e-05 | 3790
MANCHESTER 1106R213 | MANCHESTER 1106 | 253921106 |  | 9.2405 | 9.0863 |  | 136.25 | 0.0010969 | 479 | 0.053073 | 8251 | 5.8216e-05 | 3791
AIRWAYS 110877764 | AIRWAYS 1108 | 252041108 |  | 0.58528 | 0.026922 |  | 11 | 0.0010967 | 480 | 0.053073 | 8251 | 5.8203e-05 | 3792
TIDEWATER 210695842 | TIDEWATER 2106 | 14652106 |  | 1.0637 | 0.18197 |  | 18.5 | 0.00085594 | 1526 | 0.067964 | 5411 | 5.8197e-05 | 3793
CLOVIS 1103CB | CLOVIS 1103 | 254081103 |  | 1.8748 | 0.042233 |  | 28.6167 | 0.0010965 | 481 | 0.053073 | 8251 | 5.8192e-05 | 3794
CALIFORNIA AVE 1110CB | CALIFORNIA AVE 1110 | 252281110 |  | 8.7599 | 7.876 |  | 117.8333 | 0.0010951 | 483 | 0.053073 | 8251 | 5.8122e-05 | 3795
CAYETANO 2111MR329 | CAYETANO 2111 | 14422111 |  | 0.3537 | 0 |  | 6.3333 | 0.00086738 | 1440 | 0.067 | 6057 | 5.8114e-05 | 3796
LAKEWOOD 1103CB | LAKEWOOD 1103 | 13531103 |  | 0.92269 | 0.43455 |  | 12 | 0.00098989 | 832 | 0.057135 | 7414 | 5.8112e-05 | 3797
LAWRENCE 1103CB | LAWRENCE 1103 | 83421103 |  | 0.21356 | 0.062366 |  | 2.25 | 0.0010942 | 487 | 0.053073 | 8251 | 5.8074e-05 | 3798
SAN RAFAEL 1101CB | SAN RAFAEL 1101 | 42011101 | TRUE | 0.98163 | 0.30277 | 0.0061861 | 13.3333 | 0.0010938 | 488 | 0.053073 | 8250 | 5.8053e-05 | 3799
IONE 110113446 | IONE 1101 | 163881101 |  | 0.87428 | 0.017521 |  | 19 | 0.00086579 | 1452 | 0.067041 | 5958 | 5.8044e-05 | 3800
MANTECA 1708CB | MANTECA 1708 | 162611708 |  | 1.3564 | 0.67588 |  | 17 | 0.0010935 | 489 | 0.053073 | 8251 | 5.8036e-05 | 3801
STAGG 210682812 | STAGG 2106 | 162422106 |  | 0.65564 | 0.67508 |  | 11.5 | 0.0010933 | 490 | 0.053073 | 8251 | 5.8022e-05 | 3802
REDBUD 11021212 | REDBUD 1102 | 43191102 |  | 4.0945 | 0.33341 |  | 69.6667 | 0.0003577 | 7012 | 0.14498 | 3217 | 5.8012e-05 | 3803
CALISTOGA 1102706 | CALISTOGA 1102 | 42711102 |  | 3.1048 | 1.9636 |  | 49.8333 | 0.00091033 | 1184 | 0.06548 | 6363 | 5.8005e-05 | 3804
HARDING 0406CB | HARDING 0406 | 163310406 |  | 3.2032 | 2.2933 |  | 37.45 | 0.0010927 | 491 | 0.053073 | 8249 | 5.7991e-05 | 3805
BARTON 1102373096 | BARTON 1102 | 253571102 |  | 0.96117 | 0.074095 |  | 12.5 | 0.0010926 | 492 | 0.053073 | 8251 | 5.7988e-05 | 3806
LOS GATOS 1108CB | LOS GATOS 1108 | 82021108 |  | 0.72493 | 0.29349 |  | 13 | 0.0009099 | 1187 | 0.063299 | 6628 | 5.7933e-05 | 3807
MOLINO 1102111666 | MOLINO 1102 | 42571102 | TRUE | 0.96521 | 0.12694 | 0.046244 | 18.5 | 0.0003272 | 7501 | 0.12723 | 3255 | 5.7892e-05 | 3808
KING CITY 1106CB | KING CITY 1106 | 182031106 |  | 0.40258 | 0.18785 |  | 9.3333 | 0.00086993 | 1423 | 0.066503 | 6186 | 5.7884e-05 | 3809
SAN RAMON 2111MR673 | SAN RAMON 2111 | 14232111 |  | 2.2895 | 1.4304 |  | 38.5833 | 0.0010423 | 644 | 0.055238 | 7713 | 5.7879e-05 | 3810
TRACY 1104CB | TRACY 1104 | 162881104 |  | 4.6654 | 2.7228 |  | 63.8333 | 0.0010905 | 495 | 0.053073 | 8251 | 5.7876e-05 | 3811
STAGG 1103CB | STAGG 1103 | 162421103 |  | 3.3356 | 2.9885 |  | 49.6667 | 0.0010797 | 530 | 0.053562 | 8078 | 5.7826e-05 | 3812
LAKEWOOD 210964992 | LAKEWOOD 2109 | 13532109 |  | 0.25782 | 0.096754 |  | 5 | 0.00097649 | 886 | 0.060036 | 7014 | 5.7815e-05 | 3813
LAKEWOOD 2110D578R | LAKEWOOD 2110 | 13532110 |  | 0.46211 | 0.21563 |  | 9 | 0.0008778 | 1378 | 0.06548 | 6364 | 5.7777e-05 | 3814
BRUNSWICK 111095576 | BRUNSWICK 1110 | 152481110 | TRUE | 2.2083 | 1.0129 | 0.03723 | 32.6667 | 0.00073002 | 2728 | 0.082512 | 3381 | 5.7761e-05 | 3815
BULLARD 211228639 | BULLARD 2112 | 253962112 |  | 2.6784 | 3.0688 |  | 36.5 | 0.0010883 | 500 | 0.053073 | 8251 | 5.7757e-05 | 3816
EDENVALE 2108CB | EDENVALE 2108 | 82952108 |  | 0.050463 | 0 |  | 0.66667 | 0.0010876 | 502 | 0.053073 | 8251 | 5.7724e-05 | 3817
SAN RAFAEL 11071415 | SAN RAFAEL 1107 | 42011107 | FALSE | 1.208 | 1.0793 | 1.3067 | 16 | 0.00083296 | 1701 | 0.12324 | 3263 | 5.7715e-05 | 3818
OAKLAND J 1118CR198 | OAKLAND J 1118 | 12091118 | FALSE | 5.2805 | 5.9049 | 0.63237 | 81.1667 | 0.00060734 | 4204 | 0.12597 | 3258 | 5.7689e-05 | 3819
ASHLAN AVE 1116R3330 | ASHLAN AVE 1116 | 252051116 |  | 8.4136 | 9.7692 |  | 119.75 | 0.0010869 | 505 | 0.053073 | 8250 | 5.7684e-05 | 3820
EL PATIO 1101CB | EL PATIO 1101 | 82921101 |  | 0.0028409 | 0 |  | 0.5 | 0.0010862 | 509 | 0.053073 | 8251 | 5.7646e-05 | 3821
DIAMOND SPRINGS 1103CB | DIAMOND SPRINGS 1103 | 152261103 | TRUE | 9.5074 | 1.9649 | 0.087241 | 157.3333 | 0.00051599 | 5216 | 0.13813 | 3238 | 5.7626e-05 | 3822
PAUL SWEET 2103CB | PAUL SWEET 2103 | 83252103 |  | 1.0979 | 0.153 |  | 15 | 0.0010141 | 752 | 0.057425 | 7368 | 5.7612e-05 | 3823
FRANKLIN 1104P122 | FRANKLIN 1104 | 13921104 |  | 0.37044 | 0.075645 |  | 7.5 | 0.00085981 | 1499 | 0.067 | 6057 | 5.7607e-05 | 3824
LOCKHEED NO 2 1107CB | LOCKHEED NO 2 1107 | 83001107 |  | 0.76561 | 0 |  | 11.3333 | 0.0010852 | 510 | 0.053073 | 8250 | 5.7594e-05 | 3825
COUNTRY CLUB 1105CB | COUNTRY CLUB 1105 | 163121105 |  | 1.6505 | 1.0954 |  | 34.5 | 0.0010852 | 511 | 0.053073 | 8251 | 5.7594e-05 | 3826
ASHLAN AVE 111299838 | ASHLAN AVE 1112 | 252051112 |  | 1.5077 | 0.8264 |  | 19.6667 | 0.0010851 | 512 | 0.053073 | 8250 | 5.7588e-05 | 3827
LAKEWOOD 1101CB | LAKEWOOD 1101 | 13531101 |  | 0.71883 | 0 |  | 5 | 0.00098267 | 855 | 0.058644 | 7205 | 5.7573e-05 | 3828
NEWARK 21KV 2108CB | NEWARK 21KV 2108 | 12232108 |  | 4.4635 | 1.4045 |  | 71.0833 | 0.0010848 | 513 | 0.053073 | 8250 | 5.7572e-05 | 3829
CLARKSVILLE 210351564 | CLARKSVILLE 2103 | 153612103 |  | 1.5615 | 0 |  | 32 | 0.00087973 | 1369 | 0.0657 | 6324 | 5.7527e-05 | 3830
POTRERO PP (A) 1101CB | POTRERO PP (A) 1101 | 22031101 |  | 3.2887 | 1.5177 |  | 32.3667 | 0.0010834 | 515 | 0.053073 | 8248 | 5.75e-05 | 3831
WEST FRESNO 110558860 | WEST FRESNO 1105 | 253731105 |  | 0.73949 | 0.69812 |  | 11.3333 | 0.001083 | 517 | 0.053073 | 8250 | 5.7479e-05 | 3832
BARTON 1108R3500 | BARTON 1108 | 253571108 |  | 4.1364 | 2.774 |  | 64.5 | 0.001083 | 518 | 0.053073 | 8251 | 5.7476e-05 | 3833
MANCHESTER 1106628276 | MANCHESTER 1106 | 253921106 |  | 2.2698 | 2.0613 |  | 37 | 0.0010828 | 519 | 0.053073 | 8251 | 5.7465e-05 | 3834
BAKERSFIELD 210413017 | BAKERSFIELD 2104 | 253372104 |  | 0.83579 | 0.79189 |  | 16 | 0.001081 | 523 | 0.053073 | 8251 | 5.7372e-05 | 3835
BARTON 1112R1370 | BARTON 1112 | 253571112 |  | 1.0002 | 0.34389 |  | 21.5 | 0.0010808 | 524 | 0.053073 | 8251 | 5.7362e-05 | 3836
RICHMOND R 1119BR290 | RICHMOND R 1119 | 13471119 |  | 0.57429 | 0.25333 |  | 5.3333 | 0.0010802 | 526 | 0.053073 | 8249 | 5.7327e-05 | 3837
LAKEWOOD 2112CB | LAKEWOOD 2112 | 13532112 |  | 6.1372 | 3.2185 |  | 122.8333 | 0.00094092 | 1048 | 0.061023 | 6888 | 5.7323e-05 | 3838
EL PATIO 1102CB | EL PATIO 1102 | 82921102 |  | 0.98219 | 0.40873 |  | 14 | 0.00108 | 527 | 0.053073 | 8251 | 5.7318e-05 | 3839
SAN LEANDRO U 1112MR775 | SAN LEANDRO U 1112 | 13111112 |  | 0.020883 | 0 |  | 0.5 | 0.0010799 | 528 | 0.053073 | 8251 | 5.7314e-05 | 3840
ASHLAN AVE 1106CB | ASHLAN AVE 1106 | 252051106 |  | 7.3068 | 0.96083 |  | 69.6167 | 0.0010798 | 529 | 0.053073 | 8251 | 5.7307e-05 | 3841
SWIFT 2109CB | SWIFT 2109 | 83392109 |  | 1.0937 | 0.17868 |  | 22.6667 | 0.0010791 | 531 | 0.053073 | 8251 | 5.7269e-05 | 3842
ASHLAN AVE 1112CB | ASHLAN AVE 1112 | 252051112 |  | 2.5798 | 2.32 |  | 30.7833 | 0.0010789 | 532 | 0.053073 | 8251 | 5.7262e-05 | 3843
WESTPARK 1112CB | WESTPARK 1112 | 253701112 |  | 6.9113 | 3.9562 |  | 91.6667 | 0.0010789 | 533 | 0.053073 | 8250 | 5.7258e-05 | 3844
DIXON LANDING 2109MR613 | DIXON LANDING 2109 | 14722109 |  | 0.46933 | 0.12087 |  | 7.5 | 0.0010786 | 534 | 0.053073 | 8251 | 5.7245e-05 | 3845
WEBER 1101CB | WEBER 1101 | 163481101 |  | 2.6309 | 0.028767 |  | 42.1667 | 0.00096308 | 939 | 0.060392 | 6973 | 5.7226e-05 | 3846
STOREY 110789798 | STOREY 1107 | 254611107 |  | 0.16473 | 0 |  | 1.6667 | 0.0010778 | 536 | 0.053073 | 8250 | 5.7204e-05 | 3847
CONTRA COSTA 211496897 | CONTRA COSTA 2114 | 13652114 |  | 1.4098 | 0.033077 |  | 26.3333 | 0.0008264 | 1761 | 0.07368 | 4583 | 5.7183e-05 | 3848
EAST GRAND 1111CB | EAST GRAND 1111 | 22571111 |  | 0.89804 | 0.12796 |  | 14.8333 | 0.0010769 | 539 | 0.053073 | 8250 | 5.7156e-05 | 3849
MONROE 2107CB | MONROE 2107 | 43302107 |  | 3.4987 | 2.8051 |  | 55.8333 | 0.0010554 | 600 | 0.05395 | 7969 | 5.7155e-05 | 3850
BANCROFT 0402CB | BANCROFT 0402 | 13030402 | TRUE | 4.5816 | 5.4458 | 0.26966 | 61.8333 | 0.00061268 | 4135 | 0.08934 | 3346 | 5.7144e-05 | 3851
OROVILLE 1102434320 | OROVILLE 1102 | 102521102 |  | 2.874 | 1.5793 |  | 38 | 0.001057 | 594 | 0.054202 | 7902 | 5.7118e-05 | 3852
BULLARD 110192306 | BULLARD 1101 | 253961101 |  | 1.7406 | 0.69333 |  | 24.3333 | 0.0010761 | 541 | 0.053073 | 8251 | 5.7114e-05 | 3853
BELLE HAVEN 0406CB | BELLE HAVEN 0406 | 24020406 |  | 0.25485 | 0 |  | 2.3333 | 0.00087664 | 1384 | 0.06501 | 6430 | 5.7108e-05 | 3854
EAST GRAND 1103CB | EAST GRAND 1103 | 22571103 |  | 1.0482 | 0.43571 |  | 15.3333 | 0.0010756 | 544 | 0.053073 | 8250 | 5.7083e-05 | 3855
HUNTERS POINT (P) 110168026 | HUNTERS POINT (P) 1101 | 22331101 |  | 0.45176 | 0.26362 |  | 5.1667 | 0.0010749 | 546 | 0.053073 | 8250 | 5.705e-05 | 3856
BULLARD 1104CB | BULLARD 1104 | 253961104 |  | 4.5715 | 3.9686 |  | 57.1667 | 0.0010747 | 547 | 0.053073 | 8251 | 5.7036e-05 | 3857
TEVIS 21021504 | TEVIS 2102 | 255322102 |  | 1.0418 | 0.0011364 |  | 15 | 0.00084725 | 1594 | 0.069596 | 5102 | 5.7024e-05 | 3858
FRUITVALE 1105CB | FRUITVALE 1105 | 253391105 |  | 3.3958 | 0 |  | 32.75 | 0.00097513 | 893 | 0.061681 | 6801 | 5.7011e-05 | 3859
BURLINGAME 0403CB | BURLINGAME 0403 | 24050403 |  | 0.68045 | 0.42414 |  | 6.4167 | 0.0010742 | 548 | 0.053073 | 8251 | 5.7008e-05 | 3860
LAKEWOOD 1103149504 | LAKEWOOD 1103 | 13531103 |  | 1.6555 | 0.81824 |  | 20.8333 | 0.00092821 | 1106 | 0.06119 | 6870 | 5.6933e-05 | 3861
STAGG 210659040 | STAGG 2106 | 162422106 |  | 2.0642 | 1.9023 |  | 22.8333 | 0.0010726 | 551 | 0.053073 | 8251 | 5.6927e-05 | 3862
MEADOW LANE 210793364 | MEADOW LANE 2107 | 14302107 |  | 0.85956 | 0.49172 |  | 16.5 | 0.001072 | 553 | 0.053073 | 8251 | 5.6896e-05 | 3863
SHEPHERD 211089234 | SHEPHERD 2110 | 252062110 |  | 1.029 | 0.58894 |  | 16.5 | 0.0010719 | 554 | 0.053073 | 8251 | 5.6891e-05 | 3864
FULTON 11025102 | FULTON 1102 | 42561102 |  | 0.012784 | 0 |  | 0.5 | 0.00084907 | 1581 | 0.067 | 6057 | 5.6888e-05 | 3865
WYANDOTTE 1107CB | WYANDOTTE 1107 | 102911107 | TRUE | 14.7965 | 4.9394 | 0.059344 | 244 | 0.00047178 | 5681 | 0.13911 | 3234 | 5.6887e-05 | 3866
SYCAMORE CREEK 11092458 | SYCAMORE CREEK 1109 | 102971109 |  | 3.6571 | 3.0453 |  | 55 | 0.00095343 | 999 | 0.059462 | 7089 | 5.6871e-05 | 3867
LAKEWOOD 22247381 | LAKEWOOD 2224 | 13532224 |  | 0.16058 | 0 |  | 2.6667 | 0.00097534 | 892 | 0.058295 | 7251 | 5.6847e-05 | 3868
WEST FRESNO 1107CB | WEST FRESNO 1107 | 253731107 |  | 1.8213 | 1.2179 |  | 22.3095 | 0.0010708 | 555 | 0.053073 | 8251 | 5.6833e-05 | 3869
EL CAPITAN 2109CB | EL CAPITAN 2109 | 253882109 |  | 1.1741 | 0 |  | 18.8333 | 0.00093009 | 1097 | 0.063989 | 6545 | 5.6833e-05 | 3870
FIGARDEN 210949236 | FIGARDEN 2109 | 254552109 |  | 1.2858 | 0.4026 |  | 22 | 0.00107 | 556 | 0.053073 | 8251 | 5.6786e-05 | 3871
FIGARDEN 2110CB | FIGARDEN 2110 | 254552110 |  | 1.2131 | 0.092131 |  | 23.3333 | 0.0010491 | 623 | 0.055005 | 7751 | 5.6749e-05 | 3872
HUNTERS POINT (P) 1109CB | HUNTERS POINT (P) 1109 | 22331109 |  | 1.6091 | 0 |  | 13.5417 | 0.0010693 | 557 | 0.053073 | 8253 | 5.6748e-05 | 3873
OAK PARK 0402CB | OAK PARK 0402 | 163270402 |  | 0.49947 | 0.86569 |  | 7.5 | 0.0010686 | 558 | 0.053073 | 8250 | 5.6714e-05 | 3874
BAKERSFIELD 11064568 | BAKERSFIELD 1106 | 253371106 |  | 2.1523 | 1.8568 |  | 30.8333 | 0.0010686 | 559 | 0.053073 | 8252 | 5.6711e-05 | 3875
CALISTOGA 1102306462 | CALISTOGA 1102 | 42711102 | TRUE | 2.0606 | 1.2325 | 0.098051 | 33.8333 | 0.00082004 | 1819 | 0.069594 | 5103 | 5.6704e-05 | 3876
CHICO A 110156294 | CHICO A 1101 | 102051101 |  | 0.036973 | 0 |  | 0.5 | 0.0010683 | 560 | 0.053073 | 8251 | 5.6698e-05 | 3877
STAGG 11019210 | STAGG 1101 | 162421101 |  | 0.55215 | 0.1264 |  | 6.8333 | 0.0010681 | 561 | 0.053073 | 8251 | 5.6689e-05 | 3878
BULLARD 2114CB | BULLARD 2114 | 253962114 |  | 2.1212 | 0.29212 |  | 26.3333 | 0.0010675 | 562 | 0.053073 | 8251 | 5.6656e-05 | 3879
OAKLAND C 1114CR196 | OAKLAND C 1114 | 12011114 |  | 0.02471 | 0 |  | 0.83333 | 0.0010671 | 563 | 0.053073 | 8250 | 5.6636e-05 | 3880
BAY MEADOWS 2103CB | BAY MEADOWS 2103 | 24012103 |  | 0.0028409 | 0 |  | 0.33333 | 0.0010669 | 566 | 0.053073 | 8251 | 5.6624e-05 | 3881
EMBARCADERO (Z) 1113CB | EMBARCADERO (Z) 1113 | 22871113 |  | 0.19009 | 0.050211 |  | 3.6667 | 0.0010669 | 567 | 0.053073 | 8251 | 5.6623e-05 | 3882
GEYSERVILLE 1101CB | GEYSERVILLE 1101 | 42891101 |  | 0.028472 | 0 |  | 0.33333 | 0.00083456 | 1686 | 0.067839 | 5461 | 5.6616e-05 | 3883
KIRKER 210559847 | KIRKER 2105 | 14452105 |  | 0.29967 | 0.020075 |  | 5.5 | 0.0010665 | 568 | 0.053073 | 8251 | 5.6601e-05 | 3884
BULLARD 110592538 | BULLARD 1105 | 253961105 |  | 0.78051 | 0.60166 |  | 17.6667 | 0.0010662 | 570 | 0.053073 | 8252 | 5.6584e-05 | 3885
VACAVILLE 110582908 | VACAVILLE 1105 | 63601105 |  | 0.70518 | 0.02759 |  | 11.5 | 0.00097072 | 915 | 0.057917 | 7307 | 5.6544e-05 | 3886
EDES 1101CR388 | EDES 1101 | 13681101 |  | 0.29868 | 0.0469 |  | 4.8333 | 0.0010648 | 572 | 0.053073 | 8252 | 5.6513e-05 | 3887
SYCAMORE CREEK 1109CB | SYCAMORE CREEK 1109 | 102971109 | TRUE | 9.0626 | 1.047 | 0.12958 | 144.3333 | 0.00083012 | 1734 | 0.080754 | 3385 | 5.6498e-05 | 3888
EL CAPITAN 2110CB | EL CAPITAN 2110 | 253882110 |  | 1.5054 | 0 |  | 15.0333 | 0.00095792 | 969 | 0.060678 | 6930 | 5.649e-05 | 3889
PANORAMA 1101CB | PANORAMA 1101 | 103461101 | FALSE | 18.9123 | 1.5603 | 0.63954 | 354.5 | 0.00036771 | 6876 | 0.21955 | 3120 | 5.6461e-05 | 3890
WOODLAND 1104CB | WOODLAND 1104 | 62031104 |  | 4.2085 | 2.9888 |  | 52.5 | 0.0010631 | 576 | 0.053073 | 8252 | 5.642e-05 | 3891
CALIFORNIA AVE 1106CB | CALIFORNIA AVE 1106 | 252281106 |  | 3.9303 | 3.1058 |  | 53.5833 | 0.0010422 | 645 | 0.053981 | 7960 | 5.6412e-05 | 3892
LAS POSITAS 2104CB | LAS POSITAS 2104 | 14402104 |  | 1.7234 | 0.9993 |  | 37.1667 | 0.0010327 | 674 | 0.055413 | 7686 | 5.6412e-05 | 3893
BAY MEADOWS 2101955062 | BAY MEADOWS 2101 | 24012101 |  | 0.88806 | 0.57511 |  | 13.9167 | 0.0010622 | 580 | 0.053073 | 8251 | 5.6373e-05 | 3894
VASCO 1101CB | VASCO 1101 | 13751101 |  | 0.89082 | 0.056544 |  | 14.25 | 0.0010621 | 581 | 0.053073 | 8251 | 5.6369e-05 | 3895
WEST LANE 110310382 | WEST LANE 1103 | 163621103 |  | 0.61748 | 0 |  | 7.8333 | 0.001062 | 582 | 0.053073 | 8252 | 5.6363e-05 | 3896
HICKS 2111XR042 | HICKS 2111 | 83432111 |  | 0.07055 | 0 |  | 3.5 | 0.00093066 | 1094 | 0.059042 | 7153 | 5.6361e-05 | 3897
BERKELEY F 1103BR110 | BERKELEY F 1103 | 12061103 | TRUE | 3.186 | 3.1145 | 0.0174 | 36.5 | 0.00062365 | 4012 | 0.087401 | 3356 | 5.6334e-05 | 3898
ASHLAN AVE 1116D13085 | ASHLAN AVE 1116 | 252051116 |  | 0.95251 | 0.74036 |  | 15 | 0.0010609 | 584 | 0.053073 | 8251 | 5.6305e-05 | 3899
KIRKER 210921652 | KIRKER 2109 | 14452109 |  | 0.10825 | 0.093974 |  | 3.5 | 0.00083916 | 1652 | 0.067 | 6057 | 5.6223e-05 | 3900
NORTH DUBLIN 2103727584 | NORTH DUBLIN 2103 | 14052103 |  | 0.51204 | 0 |  | 11.5 | 0.00083906 | 1653 | 0.067 | 6057 | 5.6217e-05 | 3901
MEADOW LANE 2106CB | MEADOW LANE 2106 | 14302106 |  | 3.3862 | 2.4696 |  | 51.6667 | 0.00095476 | 990 | 0.058999 | 7160 | 5.6202e-05 | 3902
MISSION (X) 1125293336 | MISSION (X) 1125 | 22011125 |  | 0.84847 | 0.33506 |  | 5.3429 | 0.0010589 | 589 | 0.053073 | 8252 | 5.6199e-05 | 3903
ASHLAN AVE 111189578 | ASHLAN AVE 1111 | 252051111 |  | 2.4472 | 0.70924 |  | 38.3333 | 0.0010585 | 590 | 0.053073 | 8250 | 5.618e-05 | 3904
CLOVIS 211084702 | CLOVIS 2110 | 254082110 |  | 3.4215 | 2.5967 |  | 52 | 0.0010575 | 592 | 0.053073 | 8251 | 5.6122e-05 | 3905
MANCHESTER 1101CB | MANCHESTER 1101 | 253921101 |  | 5.1518 | 3.9459 |  | 75.0833 | 0.0010574 | 593 | 0.053073 | 8251 | 5.6118e-05 | 3906
STOCKTON A 1104CB | STOCKTON A 1104 | 162371104 |  | 4.3509 | 2.502 |  | 48.9333 | 0.001057 | 595 | 0.053073 | 8252 | 5.6096e-05 | 3907
COARSEGOLD 21036110 | COARSEGOLD 2103 | 254432103 | FALSE | 29.9853 | 0.36038 | 10.6661 | 553.5 | 8.8747e-05 | 11086 | 0.59405 | 2743 | 5.609e-05 | 3908
CHICO C 0401CB | CHICO C 0401 | 102650401 |  | 2.774 | 2.2708 |  | 39 | 0.0010564 | 597 | 0.053073 | 8251 | 5.6068e-05 | 3909
BARTON 1109R3140 | BARTON 1109 | 253571109 |  | 6.1618 | 3.5237 |  | 86.5 | 0.0010562 | 598 | 0.053073 | 8251 | 5.6054e-05 | 3910
SYCAMORE CREEK 110576092 | SYCAMORE CREEK 1105 | 102971105 |  | 4.7679 | 2.8221 |  | 63.8333 | 0.0010082 | 768 | 0.055909 | 7594 | 5.605e-05 | 3911
SARATOGA 1110CB | SARATOGA 1110 | 83371110 |  | 3.5219 | 2.5123 |  | 47.3333 | 0.00092013 | 1148 | 0.060625 | 6942 | 5.6048e-05 | 3912
BUTTE 1106CB | BUTTE 1106 | 103081106 |  | 3.3263 | 0.77081 |  | 55.3333 | 0.00099669 | 803 | 0.056177 | 7552 | 5.6019e-05 | 3913
BAY MEADOWS 2101CB | BAY MEADOWS 2101 | 24012101 |  | 0.021819 | 0 |  | 0.33333 | 0.0010555 | 599 | 0.053073 | 8251 | 5.6019e-05 | 3914
LEMOORE 1101CB | LEMOORE 1101 | 253601101 |  | 1.2826 | 0.27816 |  | 19.0333 | 0.00097254 | 910 | 0.05845 | 7226 | 5.6013e-05 | 3915
EMBARCADERO (Z) 111390064 | EMBARCADERO (Z) 1113 | 22871113 |  | 0.13104 | 0.1281 |  | 3.3333 | 0.0010552 | 601 | 0.053073 | 8250 | 5.6003e-05 | 3916
MILLBRAE 1107CB | MILLBRAE 1107 | 22691107 |  | 0.98918 | 0.097833 |  | 11.3667 | 0.0010351 | 665 | 0.053992 | 7955 | 5.5995e-05 | 3917
OAKLAND L 1103CR144 | OAKLAND L 1103 | 12111103 |  | 0.20652 | 0.11258 |  | 4.8333 | 0.0010541 | 605 | 0.053073 | 8251 | 5.5946e-05 | 3918
STOCKDALE 110946228 | STOCKDALE 1109 | 254071109 |  | 0.6037 | 0 |  | 8.6667 | 0.0010541 | 606 | 0.053073 | 8252 | 5.5943e-05 | 3919
DUNBAR 11034882 | DUNBAR 1103 | 43071103 |  | 0.038458 | 0 |  | 1.5 | 0.00082525 | 1773 | 0.067734 | 5498 | 5.5898e-05 | 3920
BAKERSFIELD 2109530574 | BAKERSFIELD 2109 | 253372109 |  | 4.6747 | 4.3396 |  | 64.8333 | 0.0010531 | 607 | 0.053073 | 8250 | 5.5891e-05 | 3921
STAGG 210899882 | STAGG 2108 | 162422108 |  | 1.3099 | 0.31089 |  | 22.3333 | 0.0010531 | 608 | 0.053073 | 8251 | 5.5889e-05 | 3922
PLEASANT GROVE 2110CB | PLEASANT GROVE 2110 | 152442110 |  | 4.1594 | 0.04741 |  | 61.8333 | 0.00083177 | 1714 | 0.067168 | 5836 | 5.5888e-05 | 3923
BULLARD 211482880 | BULLARD 2114 | 253962114 |  | 2.5866 | 0.54448 |  | 34.6667 | 0.0010326 | 675 | 0.053774 | 8006 | 5.5882e-05 | 3924
BULLARD 2111CB | BULLARD 2111 | 253962111 |  | 2.4123 | 1.4205 |  | 31.6667 | 0.0010528 | 609 | 0.053073 | 8250 | 5.5874e-05 | 3925
WEST FRESNO 110923744 | WEST FRESNO 1109 | 253731109 |  | 4.9276 | 4.3503 |  | 74.5 | 0.0010527 | 610 | 0.053073 | 8251 | 5.5872e-05 | 3926
LOCKHEED NO 2 1103CB | LOCKHEED NO 2 1103 | 83001103 |  | 0.46371 | 0 |  | 4.3333 | 0.0010527 | 611 | 0.053073 | 8252 | 5.5872e-05 | 3927
BAKERSFIELD 11062723 | BAKERSFIELD 1106 | 253371106 |  | 2.9881 | 2.9132 |  | 46.3333 | 0.0010524 | 612 | 0.053073 | 8251 | 5.5852e-05 | 3928
WILLOW PASS 2107CB | WILLOW PASS 2107 | 13912107 |  | 0.94014 | 0.86811 |  | 17 | 0.00091473 | 1167 | 0.059627 | 7065 | 5.5849e-05 | 3929
MANCHESTER 1111CB | MANCHESTER 1111 | 253921111 |  | 14.4396 | 16.0239 |  | 191.8333 | 0.0010522 | 613 | 0.053073 | 8250 | 5.5843e-05 | 3930
KERN POWER 21044281 | KERN POWER 2104 | 255262104 |  | 0.15675 | 0 |  | 2.5 | 0.001052 | 614 | 0.053073 | 8251 | 5.5835e-05 | 3931
VIERRA 170138486 | VIERRA 1701 | 162701701 |  | 0.69451 | 0.073532 |  | 12.5 | 0.00084471 | 1613 | 0.066696 | 6139 | 5.5813e-05 | 3932
MANCHESTER 1104CB | MANCHESTER 1104 | 253921104 |  | 1.1847 | 0.84056 |  | 21.5 | 0.0010513 | 617 | 0.053073 | 8251 | 5.5797e-05 | 3933
FITCH MOUNTAIN 1113CB | FITCH MOUNTAIN 1113 | 42751113 | TRUE | 2.1031 | 0.095582 | 0.14347 | 35.3333 | 0.00081374 | 1865 | 0.068714 | 5239 | 5.5789e-05 | 3934
ASHLAN AVE 2110R3090 | ASHLAN AVE 2110 | 252052110 |  | 1.8957 | 1.4191 |  | 30.5 | 0.001051 | 618 | 0.053073 | 8251 | 5.578e-05 | 3935
WHEATLAND 1101CB | WHEATLAND 1101 | 152811101 |  | 0.0034832 | 0 |  | 0.33333 | 0.00083251 | 1708 | 0.067 | 6056 | 5.5778e-05 | 3936
BAKERSFIELD 21063459 | BAKERSFIELD 2106 | 253372106 |  | 19.3256 | 18.7752 |  | 304.6667 | 0.0010493 | 621 | 0.053073 | 8250 | 5.569e-05 | 3937
SOBRANTE 1101934036 | SOBRANTE 1101 | 14671101 |  | 2.0966 | 1.6654 |  | 44.5 | 0.00085981 | 1498 | 0.065505 | 6358 | 5.5668e-05 | 3938
BARTON 1102CB | BARTON 1102 | 253571102 |  | 3.4569 | 1.1706 |  | 44 | 0.0010489 | 624 | 0.053073 | 8251 | 5.5665e-05 | 3939
MERIDIAN 1102CB | MERIDIAN 1102 | 62541102 |  | 0.45597 | 0.68676 |  | 6.8333 | 0.00082881 | 1746 | 0.065533 | 6352 | 5.5639e-05 | 3940
MANCHESTER 1112CB | MANCHESTER 1112 | 253921112 |  | 0.81099 | 0.43215 |  | 14.3333 | 0.0010482 | 625 | 0.053073 | 8251 | 5.563e-05 | 3941
WESTPARK 11033768 | WESTPARK 1103 | 253701103 |  | 12.0105 | 9.2755 |  | 171.5 | 0.0010481 | 626 | 0.053073 | 8251 | 5.5626e-05 | 3942
WYANDOTTE 11091040 | WYANDOTTE 1109 | 102911109 | FALSE | 6.076 | 0.60574 | 0.82033 | 112 | 0.00027685 | 8497 | 0.26076 | 3066 | 5.5622e-05 | 3943
OAKLAND J 1110CB | OAKLAND J 1110 | 12091110 |  | 1.3831 | 0.62165 |  | 28.25 | 0.0010477 | 627 | 0.053073 | 8251 | 5.5606e-05 | 3944
MONARCH 0402CB | MONARCH 0402 | 162300402 |  | 2.8436 | 2.8452 |  | 38.2 | 0.0010475 | 629 | 0.053073 | 8251 | 5.5592e-05 | 3945
SHINGLE SPRINGS 210851474 | SHINGLE SPRINGS 2108 | 153652108 | TRUE | 4.6815 | 0.4199 | 0.23509 | 78 | 0.00082979 | 1738 | 0.066961 | 6077 | 5.5576e-05 | 3946
EL PATIO 1114XR158 | EL PATIO 1114 | 82921114 |  | 0.033698 | 0 |  | 1.1667 | 0.0010467 | 631 | 0.053073 | 8250 | 5.5552e-05 | 3947
BARTON 1108D5460 | BARTON 1108 | 253571108 |  | 1.0204 | 1.6011 |  | 18.8333 | 0.0010462 | 632 | 0.053073 | 8251 | 5.5526e-05 | 3948
RADUM 1105420576 | RADUM 1105 | 13151105 |  | 0.93755 | 0 |  | 17.3333 | 0.00048304 | 5567 | 0.093532 | 3332 | 5.5511e-05 | 3949
TIDEWATER 21098835 | TIDEWATER 2109 | 14652109 |  | 0.74429 | 0.70321 |  | 11.5 | 0.0010459 | 633 | 0.053073 | 8251 | 5.5509e-05 | 3950
MANCHESTER 1102CB | MANCHESTER 1102 | 253921102 |  | 13.6249 | 12.7012 |  | 167.9167 | 0.0010456 | 634 | 0.053073 | 8251 | 5.5495e-05 | 3951
CAMPHORA 1101CB | CAMPHORA 1101 | 182071101 |  | 0.50359 | 0 |  | 10.5833 | 0.00082809 | 1752 | 0.067 | 6056 | 5.5482e-05 | 3952
CONTRA COSTA 210348208 | CONTRA COSTA 2103 | 13652103 |  | 7.5926 | 7.4878 |  | 91.8333 | 0.0010299 | 687 | 0.054134 | 7917 | 5.548e-05 | 3953
PUEBLO 2103CB | PUEBLO 2103 | 43292103 |  | 3.9221 | 2.0196 |  | 75 | 0.00095721 | 976 | 0.058663 | 7204 | 5.5464e-05 | 3954
HARDING 0404CB | HARDING 0404 | 163310404 |  | 2.688 | 1.7245 |  | 30.7 | 0.001045 | 636 | 0.053073 | 8250 | 5.5459e-05 | 3955
WOODSIDE 110176194 | WOODSIDE 1101 | 24251101 |  | 1.6059 | 0.28756 |  | 30.5 | 0.0008203 | 1816 | 0.067594 | 5552 | 5.5447e-05 | 3956
SANTA NELLA 1101CUS8000 | SANTA NELLA 1101 | 254051101 |  | 0.0081699 | 0 |  | 0.25 | 0.00071631 | 2900 | 0.0774 | 3397 | 5.5443e-05 | 3957
NORD 11032548 | NORD 1103 | 103071103 |  | 4.296 | 2.1436 |  | 80 | 0.00099294 | 819 | 0.055336 | 7701 | 5.5383e-05 | 3958
STOCKDALE 21144151 | STOCKDALE 2114 | 254072114 |  | 5.2938 | 4.1361 |  | 80 | 0.0010433 | 639 | 0.053073 | 8251 | 5.5373e-05 | 3959
KIRKER 2103P524R | KIRKER 2103 | 14452103 |  | 7.254 | 2.4121 |  | 121.75 | 0.0010264 | 705 | 0.054018 | 7948 | 5.5353e-05 | 3960
YOSEMITE 0403CB | YOSEMITE 0403 | 22490403 |  | 0.0022313 | 0 |  | 0.16667 | 0.001043 | 641 | 0.053073 | 8251 | 5.5353e-05 | 3961
EAST GRAND 1106CB | EAST GRAND 1106 | 22571106 |  | 3.735 | 0.96101 |  | 52.5 | 0.0010426 | 642 | 0.053073 | 8252 | 5.5335e-05 | 3962
PEABODY 2107CB | PEABODY 2107 | 63642107 |  | 5.5548 | 1.5357 |  | 80.2 | 0.00082663 | 1759 | 0.067591 | 5557 | 5.5335e-05 | 3963
WEEDPATCH 110315942 | WEEDPATCH 1103 | 252971103 |  | 0.77256 | 0.76084 |  | 12 | 0.00085134 | 1567 | 0.064679 | 6474 | 5.5332e-05 | 3964
HARDING 0403CB | HARDING 0403 | 163310403 |  | 1.8464 | 1.8377 |  | 29.7833 | 0.0010424 | 643 | 0.053073 | 8251 | 5.5326e-05 | 3965
PAUL SWEET 2102CB | PAUL SWEET 2102 | 83252102 |  | 4.4473 | 2.662 |  | 59.6667 | 0.00088622 | 1328 | 0.062721 | 6687 | 5.5306e-05 | 3966
BAKERSFIELD 1116CB | BAKERSFIELD 1116 | 253371116 |  | 7.2465 | 7.2015 |  | 97.5833 | 0.001042 | 646 | 0.053073 | 8250 | 5.5304e-05 | 3967
HILLSDALE 0402CB | HILLSDALE 0402 | 24110402 |  | 0.10895 | 0 |  | 0.95 | 0.00082519 | 1774 | 0.067 | 6057 | 5.5288e-05 | 3968
POTRERO PP (A) 1119CB | POTRERO PP (A) 1119 | 22031119 |  | 2.5198 | 2.7084 |  | 29.6167 | 0.0010417 | 647 | 0.053073 | 8250 | 5.5287e-05 | 3969
ASHLAN AVE 2119920229 | ASHLAN AVE 2119 | 252052119 |  | 0.0177 | 0 |  | 0.5 | 0.0010417 | 648 | 0.053073 | 8251 | 5.5286e-05 | 3970
STOCKDALE 11092526 | STOCKDALE 1109 | 254071109 |  | 0.51889 | 0 |  | 6.8333 | 0.0010416 | 649 | 0.053073 | 8252 | 5.5282e-05 | 3971
BUENA VISTA 1101CB | BUENA VISTA 1101 | 182261101 |  | 0.70229 | 0.083389 |  | 10.5 | 0.0010414 | 650 | 0.053073 | 8251 | 5.5271e-05 | 3972
BARTON 110455534 | BARTON 1104 | 253571104 |  | 5.159 | 5.2866 |  | 79.9167 | 0.0010411 | 651 | 0.053073 | 8251 | 5.5252e-05 | 3973
HUNTERS POINT (P) 110398158 | HUNTERS POINT (P) 1103 | 22331103 |  | 1.1284 | 1.2275 |  | 17.3333 | 0.0010406 | 652 | 0.053073 | 8250 | 5.5228e-05 | 3974
DEL MONTE 210235404 | DEL MONTE 2102 | 182222102 |  | 1.9573 | 1.0355 |  | 35 | 0.0010403 | 653 | 0.053073 | 8251 | 5.521e-05 | 3975
WESTPARK 11074090 | WESTPARK 1107 | 253701107 |  | 3.1382 | 0.3309 |  | 46 | 0.0010235 | 713 | 0.05413 | 7921 | 5.5208e-05 | 3976
STAGG 1106CB | STAGG 1106 | 162421106 |  | 1.8594 | 0.73646 |  | 36.5 | 0.0010384 | 654 | 0.053073 | 8251 | 5.5111e-05 | 3977
OAKLAND D 1116CB | OAKLAND D 1116 | 12041116 |  | 2.806 | 2.3899 |  | 37.9167 | 0.0010383 | 655 | 0.053073 | 8249 | 5.5105e-05 | 3978
ROSSMOOR 1105W564R | ROSSMOOR 1105 | 14161105 |  | 1.3155 | 1.0211 |  | 22.5 | 0.00092273 | 1133 | 0.059574 | 7075 | 5.5093e-05 | 3979
CUYAMA 21021000 | CUYAMA 2102 | 253142102 |  | 21.816 | 0.31008 |  | 411 | 0.0001065 | 11031 | 0.76349 | 2590 | 5.5084e-05 | 3980
EVERGREEN 2104XR236 | EVERGREEN 2104 | 82012104 |  | 0.59209 | 0.079045 |  | 11 | 0.0010378 | 656 | 0.053073 | 8251 | 5.5079e-05 | 3981
ASHLAN AVE 1113CB | ASHLAN AVE 1113 | 252051113 |  | 1.3961 | 0.32273 |  | 19.5833 | 0.00099056 | 827 | 0.056178 | 7549 | 5.5066e-05 | 3982
MEADOW LANE 2103CB | MEADOW LANE 2103 | 14302103 |  | 5.9978 | 4.2087 |  | 82.1667 | 0.0010373 | 658 | 0.053073 | 8251 | 5.5055e-05 | 3983
KIRKER 2106CB | KIRKER 2106 | 14452106 |  | 7.28 | 5.1253 |  | 105.6667 | 0.00097367 | 903 | 0.056503 | 7504 | 5.505e-05 | 3984
PANAMA 2102CB | PANAMA 2102 | 253422102 |  | 2.4625 | 0.54968 |  | 30.8333 | 0.0010369 | 660 | 0.053073 | 8251 | 5.5029e-05 | 3985
STAGG 21049472 | STAGG 2104 | 162422104 |  | 0.16178 | 0 |  | 3.5 | 0.00094636 | 1025 | 0.060023 | 7018 | 5.5028e-05 | 3986
MONROE 210278440 | MONROE 2102 | 43302102 |  | 0.86533 | 0.3233 |  | 13.5 | 0.0010368 | 661 | 0.053073 | 8251 | 5.5024e-05 | 3987
DIXON LANDING 2102CB | DIXON LANDING 2102 | 14722102 |  | 3.8609 | 2.7846 |  | 64 | 0.00097905 | 875 | 0.056555 | 7499 | 5.4984e-05 | 3988
WESTPARK 11014897 | WESTPARK 1101 | 253701101 |  | 3.7203 | 3.7506 |  | 51.6667 | 0.0010356 | 663 | 0.053073 | 8251 | 5.4964e-05 | 3989
TIDEWATER 2110C594R | TIDEWATER 2110 | 14652110 |  | 3.587 | 2.0557 |  | 60.5 | 0.00092772 | 1110 | 0.0596 | 7072 | 5.4964e-05 | 3990
SAUSALITO 1102CB | SAUSALITO 1102 | 42491102 |  | 0.46691 | 0.078127 |  | 4.6667 | 0.0010156 | 743 | 0.053819 | 7993 | 5.4963e-05 | 3991
ROCKLIN 110232724 | ROCKLIN 1102 | 152061102 |  | 0.63004 | 0 |  | 8.8333 | 0.00088984 | 1299 | 0.06227 | 6737 | 5.4961e-05 | 3992
GEARY 0401GY401/2 | GEARY 0401 | 13590401 |  | 4.2657 | 3.8141 |  | 59.6667 | 0.00085718 | 1516 | 0.063927 | 6554 | 5.496e-05 | 3993
FRANKLIN 1101P172 | FRANKLIN 1101 | 13921101 |  | 0.18614 | 0 |  | 3 | 0.00082007 | 1817 | 0.067 | 6057 | 5.4945e-05 | 3994
HARTER 1107CB | HARTER 1107 | 152851107 |  | 2.2902 | 0.33612 |  | 36.0333 | 0.0010352 | 664 | 0.053073 | 8251 | 5.4942e-05 | 3995
CALIFORNIA AVE 1111CB | CALIFORNIA AVE 1111 | 252281111 |  | 4.4868 | 0.54254 |  | 58.3333 | 0.0010221 | 714 | 0.055366 | 7692 | 5.4941e-05 | 3996
MALAGA 1101CB | MALAGA 1101 | 254251101 |  | 3.9333 | 0.65083 |  | 64.1667 | 0.00081611 | 1846 | 0.068111 | 5383 | 5.4937e-05 | 3997
ASHLAN AVE 1102CB | ASHLAN AVE 1102 | 252051102 |  | 13.2096 | 12.5161 |  | 169.1167 | 0.0010347 | 666 | 0.053073 | 8252 | 5.4915e-05 | 3998
LARKIN (Y) 1136CB | LARKIN (Y) 1136 | 22801136 |  | 0.43127 | 0.21874 |  | 5.1667 | 0.0010346 | 668 | 0.053073 | 8250 | 5.491e-05 | 3999
LAMONT 1106143302 | LAMONT 1106 | 253911106 |  | 0.023958 | 0 |  | 1.3333 | 0.00070932 | 2986 | 0.0774 | 3396 | 5.4901e-05 | 4000
SF H 1103897904 | SF H 1103 | 22101103 |  | 0.27739 | 0.050031 |  | 5 | 0.0010333 | 671 | 0.053073 | 8251 | 5.4838e-05 | 4001
MANTECA 170414590 | MANTECA 1704 | 162611704 |  | 0.2046 | 0 |  | 5 | 0.0010177 | 731 | 0.055505 | 7671 | 5.4829e-05 | 4002
BULLARD 1109CB | BULLARD 1109 | 253961109 |  | 5.4022 | 5.1092 |  | 71.3333 | 0.001033 | 672 | 0.053073 | 8252 | 5.4823e-05 | 4003
CALIFORNIA AVE 1114CB | CALIFORNIA AVE 1114 | 252281114 |  | 11.7668 | 10.7591 |  | 172.3333 | 0.0010329 | 673 | 0.053073 | 8250 | 5.482e-05 | 4004
PACIFICA 1102660408 | PACIFICA 1102 | 22811102 | TRUE | 1.9958 | 3.0405 | 0.59988 | 31 | 0.00067545 | 3368 | 0.066614 | 6163 | 5.4803e-05 | 4005
STOCKTON A 0405CB | STOCKTON A 0405 | 162370405 |  | 0.38604 | 0.096445 |  | 4.8333 | 0.0010326 | 676 | 0.053073 | 8251 | 5.4802e-05 | 4006
GREENBRAE 1103343788 | GREENBRAE 1103 | 43091103 |  | 2.4895 | 1.6572 |  | 51 | 0.00061202 | 4147 | 0.1184 | 3271 | 5.4801e-05 | 4007
STOCKDALE 1110CB | STOCKDALE 1110 | 254071110 |  | 6.3146 | 4.6498 |  | 80.7833 | 0.0010274 | 702 | 0.053309 | 8172 | 5.4783e-05 | 4008
MANCHESTER 1105859208 | MANCHESTER 1105 | 253921105 |  | 4.3915 | 1.9295 |  | 73.8333 | 0.0010319 | 678 | 0.053073 | 8252 | 5.4765e-05 | 4009
LAS POSITAS 2103CB | LAS POSITAS 2103 | 14402103 |  | 1.6729 | 0.49466 |  | 27.75 | 0.00086068 | 1492 | 0.064867 | 6456 | 5.476e-05 | 4010
MONTAGUE 2106CB | MONTAGUE 2106 | 83892106 |  | 0.0037879 | 0 |  | 1 | 0.0010316 | 680 | 0.053073 | 8251 | 5.4748e-05 | 4011
HICKS 1116LB16 | HICKS 1116 | 83431116 |  | 5.5419 | 5.8911 |  | 75.3333 | 0.00061046 | 4162 | 0.11305 | 3282 | 5.473e-05 | 4012
FIGARDEN 2108R1020 | FIGARDEN 2108 | 254552108 |  | 2.3454 | 1.1504 |  | 27.9167 | 0.00092356 | 1127 | 0.059617 | 7068 | 5.4729e-05 | 4013
HORSESHOE 1101CB | HORSESHOE 1101 | 152571101 | TRUE | 4.0143 | 1.2682 | 0.24844 | 72.3333 | 0.00067978 | 3327 | 0.089753 | 3343 | 5.4727e-05 | 4014
BULLARD 110647944 | BULLARD 1106 | 253961106 |  | 1.4304 | 0.85975 |  | 21.5 | 0.001031 | 683 | 0.053073 | 8251 | 5.4719e-05 | 4015
BAKERSFIELD 21094129 | BAKERSFIELD 2109 | 253372109 |  | 17.8473 | 15.1605 |  | 258.6667 | 0.001031 | 684 | 0.053073 | 8250 | 5.4717e-05 | 4016
SAN MATEO 04109068 | SAN MATEO 0410 | 24190410 |  | 2.6008 | 2.9666 |  | 48.1667 | 0.00083604 | 1673 | 0.065892 | 6293 | 5.4701e-05 | 4017
EDES 1114CB | EDES 1114 | 13681114 |  | 0.95519 | 0.23782 |  | 11.3333 | 0.0010303 | 685 | 0.053073 | 8251 | 5.4678e-05 | 4018
BAKERSFIELD 11144420 | BAKERSFIELD 1114 | 253371114 |  | 5.1753 | 6.3664 |  | 90.1667 | 0.0010301 | 686 | 0.053073 | 8250 | 5.467e-05 | 4019
POTRERO PP (A) 1114CB | POTRERO PP (A) 1114 | 22031114 |  | 0.071214 | 0 |  | 2.5 | 0.0010297 | 690 | 0.053073 | 8251 | 5.4649e-05 | 4020
POTRERO PP (A) 1121CB | POTRERO PP (A) 1121 | 22031121 |  | 0.16128 | 0 |  | 3 | 0.0010293 | 692 | 0.053073 | 8251 | 5.4628e-05 | 4021
RICHMOND R 1119BR294 | RICHMOND R 1119 | 13471119 |  | 0.09113 | 0.063219 |  | 1.4167 | 0.0010292 | 693 | 0.053073 | 8250 | 5.4622e-05 | 4022
CLOVIS 210958802 | CLOVIS 2109 | 254082109 |  | 1.7907 | 0.85799 |  | 22.3333 | 0.001029 | 694 | 0.053073 | 8252 | 5.4613e-05 | 4023
MANCHESTER 1110CB | MANCHESTER 1110 | 253921110 |  | 13.4235 | 11.3355 |  | 189.1667 | 0.001029 | 695 | 0.053073 | 8251 | 5.4612e-05 | 4024
WEST FRESNO 1103CB | WEST FRESNO 1103 | 253731103 |  | 5.859 | 4.9149 |  | 76.6012 | 0.0010175 | 732 | 0.053708 | 8025 | 5.4608e-05 | 4025
CALISTOGA 1102279135 | CALISTOGA 1102 | 42711102 |  | 0.48139 | 0.3777 |  | 9.3333 | 0.00077623 | 2192 | 0.070289 | 4982 | 5.4605e-05 | 4026
PINEDALE 2101CB | PINEDALE 2101 | 252852101 |  | 1.4132 | 0.041367 |  | 31.3333 | 0.0010283 | 697 | 0.053073 | 8251 | 5.4574e-05 | 4027
LEMOORE 11058740 | LEMOORE 1105 | 253601105 |  | 0.038728 | 0 |  | 1.5 | 0.0010279 | 699 | 0.053073 | 8251 | 5.4555e-05 | 4028
KERN OIL 1110CB | KERN OIL 1110 | 252721110 |  | 0.58908 | 0.58288 |  | 10.8333 | 0.0010279 | 700 | 0.053073 | 8251 | 5.4554e-05 | 4029
NEWARK 21KV 2105CB | NEWARK 21KV 2105 | 12232105 |  | 2.4457 | 0.7104 |  | 46 | 0.0009963 | 804 | 0.054659 | 7812 | 5.4552e-05 | 4030
PETALUMA C 1101CB | PETALUMA C 1101 | 42631101 |  | 0.50539 | 0.16304 |  | 6.5 | 0.0010252 | 706 | 0.053073 | 8251 | 5.4411e-05 | 4031
NORTECH 2109CB | NORTECH 2109 | 82462109 |  | 3.1238 | 0.037714 |  | 53.5 | 0.00086237 | 1480 | 0.063616 | 6598 | 5.439e-05 | 4032
OAKLAND J 1104CB | OAKLAND J 1104 | 12091104 |  | 2.9647 | 1.3823 |  | 29.25 | 0.0010248 | 707 | 0.053073 | 8248 | 5.439e-05 | 4033
CLAYTON 2215500240 | CLAYTON 2215 | 12022215 | TRUE | 0.5036 | 0.0090763 | 0.075197 | 7.5 | 0.00081459 | 1862 | 0.065554 | 6349 | 5.4356e-05 | 4034
PARKWAY 1102CB | PARKWAY 1102 | 42051102 |  | 0.0028409 | 0 |  | 0.5 | 0.0010241 | 708 | 0.053073 | 8251 | 5.4354e-05 | 4035
SAN RAMON 2107818336 | SAN RAMON 2107 | 14232107 |  | 0.33201 | 0.15381 |  | 5.8333 | 0.0010241 | 710 | 0.053073 | 8252 | 5.4353e-05 | 4036
ASHLAN AVE 2118R1520 | ASHLAN AVE 2118 | 252052118 |  | 2.5676 | 1.5507 |  | 39 | 0.0010236 | 712 | 0.053073 | 8251 | 5.4326e-05 | 4037
MONROE 2103CB | MONROE 2103 | 43302103 |  | 7.9681 | 2.0319 |  | 115.1667 | 0.00089432 | 1272 | 0.061338 | 6847 | 5.4311e-05 | 4038
PLACER 110451734 | PLACER 1104 | 152461104 |  | 4.747 | 2.1932 |  | 71 | 0.00091278 | 1175 | 0.059815 | 7037 | 5.4297e-05 | 4039
FRUITVALE 1101CB | FRUITVALE 1101 | 253391101 |  | 3.3266 | 0 |  | 26.6667 | 0.0009096 | 1192 | 0.062421 | 6725 | 5.4276e-05 | 4040
TWISSELMAN 1104CB | TWISSELMAN 1104 | 254401104 |  | 0.012657 | 0 |  | 0.75 | 0.00080996 | 1897 | 0.067 | 6057 | 5.4267e-05 | 4041
TWISSELMAN 1101CB | TWISSELMAN 1101 | 254401101 |  | 0.012652 | 0 |  | 0.75 | 0.00080996 | 1897 | 0.067 | 6057 | 5.4267e-05 | 4041
TIDEWATER 2109C512R | TIDEWATER 2109 | 14652109 |  | 3.4651 | 1.3579 |  | 63 | 0.0008831 | 1347 | 0.061806 | 6785 | 5.426e-05 | 4042
SAN RAFAEL 1105CB | SAN RAFAEL 1105 | 42011105 |  | 9.6729 | 4.915 |  | 176.5 | 0.00059528 | 4357 | 0.10099 | 3311 | 5.4244e-05 | 4043
TEMPLETON 2110R06 | TEMPLETON 2110 | 183052110 |  | 4.2418 | 0.10573 |  | 77.5 | 0.00025978 | 8887 | 0.12612 | 3257 | 5.424e-05 | 4044
COLUMBUS 1110CB | COLUMBUS 1110 | 253951110 |  | 1.7542 | 0.80388 |  | 18.4167 | 0.001022 | 715 | 0.053073 | 8251 | 5.4239e-05 | 4045
MAGUNDEN 2108CB | MAGUNDEN 2108 | 252772108 |  | 5.6846 | 0.6294 |  | 82.2262 | 0.00098894 | 839 | 0.054952 | 7757 | 5.4227e-05 | 4046
ASHLAN AVE 2115CB | ASHLAN AVE 2115 | 252052115 |  | 5.5104 | 3.4885 |  | 82.8333 | 0.0010216 | 716 | 0.053073 | 8251 | 5.422e-05 | 4047
WEST FRESNO 110749176 | WEST FRESNO 1107 | 253731107 |  | 2.4594 | 2.029 |  | 42 | 0.0010213 | 719 | 0.053073 | 8251 | 5.4202e-05 | 4048
OROVILLE 1103CB | OROVILLE 1103 | 102521103 |  | 1.396 | 0 |  | 16.6667 | 0.00084819 | 1587 | 0.063936 | 6553 | 5.4199e-05 | 4049
VACAVILLE 1109CB | VACAVILLE 1109 | 63601109 |  | 2.1138 | 0.85892 |  | 38 | 0.00094333 | 1038 | 0.057507 | 7362 | 5.4156e-05 | 4050
ASHLAN AVE 1107CB | ASHLAN AVE 1107 | 252051107 |  | 8.3157 | 8.575 |  | 120.5833 | 0.0010203 | 720 | 0.053073 | 8251 | 5.4152e-05 | 4051
TRACY 1112CB | TRACY 1112 | 162881112 |  | 5.1204 | 2.1337 |  | 71.8667 | 0.0010203 | 721 | 0.053073 | 8251 | 5.4149e-05 | 4052
COTTLE 1702813762 | COTTLE 1702 | 163711702 |  | 1.1788 | 0.63504 |  | 18.8333 | 0.0010164 | 740 | 0.053529 | 8092 | 5.4136e-05 | 4053
DEVILS DEN 1101824190 | DEVILS DEN 1101 | 253451101 |  | 28.7039 | 0.2708 |  | 492.5 | 0.00012844 | 10896 | 0.75208 | 2594 | 5.4129e-05 | 4054
HARDING 0405CB | HARDING 0405 | 163310405 |  | 2.8977 | 2.3343 |  | 34.45 | 0.0010196 | 722 | 0.053073 | 8252 | 5.4114e-05 | 4055
HAMMER 1102CB | HAMMER 1102 | 163301102 |  | 2.3056 | 1.5625 |  | 33.5 | 0.0010192 | 724 | 0.053073 | 8251 | 5.4094e-05 | 4056
OAKLAND C 1132CR138 | OAKLAND C 1132 | 12011132 |  | 0.23612 | 0.056868 |  | 5.5 | 0.0010189 | 726 | 0.053073 | 8251 | 5.4078e-05 | 4057
TRINIDAD 110233936 | TRINIDAD 1102 | 192231102 |  | 3.7834 | 0.66085 |  | 69 | 0.00080669 | 1923 | 0.067009 | 6023 | 5.4052e-05 | 4058
REDWOOD CITY 110448466 | REDWOOD CITY 1104 | 24161104 |  | 0.21668 | 0.18953 |  | 6.8333 | 0.0010184 | 728 | 0.053073 | 8251 | 5.405e-05 | 4059
EIGHT MILE 2101816304 | EIGHT MILE 2101 | 163912101 |  | 0.023069 | 0 |  | 0.5 | 0.0010183 | 729 | 0.053073 | 8251 | 5.4045e-05 | 4060
MANCHESTER 1105952950 | MANCHESTER 1105 | 253921105 |  | 3.201 | 2.3739 |  | 47.5 | 0.0010181 | 730 | 0.053073 | 8251 | 5.4034e-05 | 4061
DAVIS 110477080 | DAVIS 1104 | 62041104 |  | 3.2929 | 3.0516 |  | 46.1667 | 0.0010173 | 733 | 0.053073 | 8251 | 5.399e-05 | 4062
DEEPWATER 1108CB | DEEPWATER 1108 | 63621108 |  | 0.085532 | 0 |  | 1.8333 | 0.00069746 | 3140 | 0.0774 | 3397 | 5.3984e-05 | 4063
CALIFORNIA AVE 1113901816 | CALIFORNIA AVE 1113 | 252281113 |  | 1.3021 | 1.419 |  | 21 | 0.001017 | 735 | 0.053073 | 8251 | 5.3976e-05 | 4064
REDWOOD CITY 1104CB | REDWOOD CITY 1104 | 24161104 |  | 0.71801 | 0.30396 |  | 8.8667 | 0.0010168 | 736 | 0.053073 | 8251 | 5.3966e-05 | 4065
MANCHESTER 1107CB | MANCHESTER 1107 | 253921107 |  | 8.679 | 7.3497 |  | 130.3333 | 0.0010167 | 737 | 0.053073 | 8252 | 5.396e-05 | 4066
TRACY 1111CB | TRACY 1111 | 162881111 |  | 6.7869 | 4.5205 |  | 82.6167 | 0.0010165 | 738 | 0.053073 | 8250 | 5.3949e-05 | 4067
MONARCH 0401CB | MONARCH 0401 | 162300401 |  | 3.1977 | 3.7564 |  | 41.95 | 0.0010164 | 739 | 0.053073 | 8250 | 5.3941e-05 | 4068
MEADOW LANE 210813902 | MEADOW LANE 2108 | 14302108 |  | 2.999 | 2.4794 |  | 40.5 | 0.00092709 | 1114 | 0.057371 | 7379 | 5.3929e-05 | 4069
POTRERO PP (A) 112169424 | POTRERO PP (A) 1121 | 22031121 |  | 0.0048029 | 0 |  | 0.5 | 0.0010159 | 741 | 0.053073 | 8251 | 5.3915e-05 | 4070
MEADOW LANE 2105990692 | MEADOW LANE 2105 | 14302105 |  | 1.9449 | 1.4909 |  | 28 | 0.0010158 | 742 | 0.053073 | 8251 | 5.3912e-05 | 4071
BARTON 1106CB | BARTON 1106 | 253571106 |  | 5.8699 | 4.1559 |  | 83.75 | 0.0010156 | 744 | 0.053073 | 8251 | 5.3898e-05 | 4072
STOCKDALE 1106CB | STOCKDALE 1106 | 254071106 |  | 5.6029 | 3.6008 |  | 71.3333 | 0.0010151 | 746 | 0.053073 | 8250 | 5.3872e-05 | 4073
EDENVALE 2108XR570 | EDENVALE 2108 | 82952108 |  | 1.2731 | 0.30547 |  | 20.8333 | 0.001015 | 747 | 0.053073 | 8251 | 5.3868e-05 | 4074
LAWRENCE 1102CB | LAWRENCE 1102 | 83421102 |  | 0.084996 | 0 |  | 1.3333 | 0.0010149 | 748 | 0.053073 | 8251 | 5.3866e-05 | 4075
LAMONT 11044113 | LAMONT 1104 | 253911104 | FALSE | 10.1415 | 0.39783 | 1.5462 | 169 | 0.00026869 | 8679 | 0.39255 | 2924 | 5.3847e-05 | 4076
MANCHESTER 11099509 | MANCHESTER 1109 | 253921109 |  | 6.4929 | 4.3533 |  | 101.5 | 0.0010144 | 750 | 0.053073 | 8251 | 5.3837e-05 | 4077
BAY MEADOWS 1104CB | BAY MEADOWS 1104 | 24011104 |  | 0.54426 | 0.12144 |  | 8.6667 | 0.0010141 | 751 | 0.053073 | 8252 | 5.3821e-05 | 4078
EEL RIVER 11033820 | EEL RIVER 1103 | 192381103 |  | 19.7048 | 1.1314 |  | 362.5 | 0.00024378 | 9203 | 0.2947 | 3028 | 5.3821e-05 | 4079
COTTLE 17079840 | COTTLE 1707 | 163711707 |  | 1.4001 | 1.1145 |  | 23.6667 | 0.0010128 | 754 | 0.053073 | 8250 | 5.3754e-05 | 4080
CALIFORNIA AVE 1114509378 | CALIFORNIA AVE 1114 | 252281114 |  | 4.1364 | 5.8353 |  | 62 | 0.0010122 | 756 | 0.053073 | 8251 | 5.3721e-05 | 4081
RANCHERS COTTON 1101CB | RANCHERS COTTON 1101 | 254801101 |  | 5.9841 | 1.7192 |  | 97.3333 | 0.0010121 | 757 | 0.053073 | 8252 | 5.3714e-05 | 4082
LAKEWOOD 222568791 | LAKEWOOD 2225 | 13532225 |  | 1.0088 | 0.59204 |  | 12.0833 | 0.00097414 | 900 | 0.055202 | 7723 | 5.3711e-05 | 4083
LOCKHEED NO 2 1106CB | LOCKHEED NO 2 1106 | 83001106 |  | 0.37358 | 0 |  | 4.8333 | 0.0010117 | 758 | 0.053073 | 8252 | 5.3693e-05 | 4084
SERRAMONTE 110456936 | SERRAMONTE 1104 | 22861104 |  | 1.8223 | 1.1322 |  | 30 | 0.00082934 | 1741 | 0.064963 | 6444 | 5.3673e-05 | 4085
EAST GRAND 1102CB | EAST GRAND 1102 | 22571102 |  | 2.2088 | 0.28219 |  | 38 | 0.0010105 | 760 | 0.053073 | 8251 | 5.3629e-05 | 4086
DEL MAR 210584138 | DEL MAR 2105 | 152582105 |  | 2.2806 | 0.0033075 |  | 39.5 | 0.00084543 | 1611 | 0.063694 | 6580 | 5.3615e-05 | 4087
SAN PABLO 1106CB | SAN PABLO 1106 | 14371106 |  | 0.64867 | 0 |  | 13.5 | 0.00084977 | 1575 | 0.062889 | 6671 | 5.3611e-05 | 4088
STOCKTON A 11098586 | STOCKTON A 1109 | 162371109 |  | 6.4813 | 7.3535 |  | 84.5 | 0.0010091 | 764 | 0.053073 | 8251 | 5.3556e-05 | 4089
CASTRO VALLEY 1111227862 | CASTRO VALLEY 1111 | 14091111 | TRUE | 1.752 | 1.0171 | 0.13922 | 35.8333 | 0.00046777 | 5719 | 0.16842 | 3186 | 5.3524e-05 | 4090
LINCOLN 2109CB | LINCOLN 2109 | 153702109 |  | 0.34229 | 0.060372 |  | 8.5 | 0.00077611 | 2194 | 0.068224 | 5354 | 5.3513e-05 | 4091
WESTPARK 11041514 | WESTPARK 1104 | 253701104 |  | 2.2911 | 2.1711 |  | 40 | 0.0009943 | 812 | 0.054593 | 7828 | 5.3508e-05 | 4092
WOODLAND 1107CB | WOODLAND 1107 | 62031107 |  | 2.9176 | 2.1112 |  | 38.6667 | 0.0010069 | 771 | 0.053073 | 8252 | 5.3438e-05 | 4093
NORD 11062480 | NORD 1106 | 103071106 |  | 1.9135 | 0.54122 |  | 33.5 | 0.00085004 | 1573 | 0.062843 | 6676 | 5.3438e-05 | 4094
STOCKDALE 11112172 | STOCKDALE 1111 | 254071111 |  | 4.8456 | 4.1159 |  | 64.5 | 0.0010067 | 772 | 0.053073 | 8251 | 5.3427e-05 | 4095
WOLFE 1104CB | WOLFE 1104 | 83671104 |  | 1.1326 | 0.94969 |  | 15.3333 | 0.0010061 | 773 | 0.053073 | 8251 | 5.3395e-05 | 4096
BARTON 1108R3370 | BARTON 1108 | 253571108 |  | 6.1773 | 6.7808 |  | 99.1667 | 0.0010058 | 774 | 0.053073 | 8250 | 5.3382e-05 | 4097
WESTPARK 110857726 | WESTPARK 1108 | 253701108 |  | 2.885 | 2.3762 |  | 46.5 | 0.0010057 | 775 | 0.053073 | 8251 | 5.3375e-05 | 4098
TEVIS 2101CB | TEVIS 2101 | 255322101 |  | 2.085 | 0.025974 |  | 33.6667 | 0.00088724 | 1323 | 0.061149 | 6875 | 5.3371e-05 | 4099
BAKERSFIELD 1118CB | BAKERSFIELD 1118 | 253371118 |  | 2.1802 | 0.041948 |  | 40.7833 | 0.00094389 | 1035 | 0.060038 | 7013 | 5.3362e-05 | 4100
FIGARDEN 2108CB | FIGARDEN 2108 | 254552108 |  | 1.7337 | 0.95891 |  | 28 | 0.00093669 | 1064 | 0.057417 | 7371 | 5.3339e-05 | 4101
BAY MEADOWS 110468208 | BAY MEADOWS 1104 | 24011104 |  | 0.040785 | 0.058161 |  | 0.58333 | 0.001005 | 776 | 0.053073 | 8250 | 5.3336e-05 | 4102
DAVIS 1105CB | DAVIS 1105 | 62041105 |  | 3.0605 | 2.4711 |  | 42.1667 | 0.0010047 | 778 | 0.053073 | 8252 | 5.332e-05 | 4103
OAKLAND L 1103CR302 | OAKLAND L 1103 | 12111103 |  | 1.585 | 1.6758 |  | 18.8333 | 0.0010044 | 779 | 0.053073 | 8251 | 5.3305e-05 | 4104
LAWRENCE 1108CB | LAWRENCE 1108 | 83421108 |  | 0.80442 | 0 |  | 5.5 | 0.0010043 | 780 | 0.053073 | 8250 | 5.3299e-05 | 4105
EAST GRAND 1107CB | EAST GRAND 1107 | 22571107 |  | 2.8987 | 1.2341 |  | 42.0833 | 0.0010035 | 781 | 0.053073 | 8250 | 5.3258e-05 | 4106
POTRERO PP (A) 1117CB | POTRERO PP (A) 1117 | 22031117 |  | 0.6632 | 0.27133 |  | 8.0833 | 0.0010031 | 783 | 0.053073 | 8250 | 5.3236e-05 | 4107
DEL MAR 2105CB | DEL MAR 2105 | 152582105 |  | 4.2015 | 0.87457 |  | 74.5 | 0.00082149 | 1806 | 0.063505 | 6612 | 5.3228e-05 | 4108
CLAYTON 2214CB | CLAYTON 2214 | 12022214 |  | 1.0767 | 0.83744 |  | 15.5333 | 0.00095265 | 1003 | 0.055498 | 7673 | 5.3227e-05 | 4109
FIGARDEN 211132482 | FIGARDEN 2111 | 254552111 |  | 2.5297 | 0.15046 |  | 38.75 | 0.00097541 | 891 | 0.054642 | 7817 | 5.3208e-05 | 4110
SONOMA 1106296492 | SONOMA 1106 | 42721106 |  | 1.477 | 0.46213 |  | 29 | 0.00054964 | 4865 | 0.11099 | 3291 | 5.3205e-05 | 4111
SF H 1111CB | SF H 1111 | 22101111 |  | 3.8806 | 0.023744 |  | 28.7512 | 0.0010019 | 784 | 0.053073 | 8248 | 5.3172e-05 | 4112
GONZALES 1103CB | GONZALES 1103 | 182131103 |  | 2.5571 | 2.1032 |  | 42.5833 | 0.00085675 | 1522 | 0.063371 | 6624 | 5.3172e-05 | 4113
LARKIN (Y) 1127CB | LARKIN (Y) 1127 | 22801127 |  | 0.66442 | 0.6366 |  | 10.1667 | 0.0010017 | 785 | 0.053073 | 8251 | 5.3164e-05 | 4114
OAKLAND L 1103CR300 | OAKLAND L 1103 | 12111103 |  | 2.604 | 2.5518 |  | 33.0833 | 0.0010016 | 786 | 0.053073 | 8250 | 5.316e-05 | 4115
LAWRENCE 1109CB | LAWRENCE 1109 | 83421109 |  | 1.8797 | 0.40109 |  | 19 | 0.0010012 | 788 | 0.053073 | 8251 | 5.3135e-05 | 4116
BELL 110950520 | BELL 1109 | 152701109 |  | 0.36968 | 0 |  | 6.5 | 0.00079282 | 2034 | 0.067013 | 6015 | 5.313e-05 | 4117
FIGARDEN 211132528 | FIGARDEN 2111 | 254552111 |  | 0.61729 | 0.031834 |  | 7.5 | 0.001001 | 789 | 0.053073 | 8251 | 5.3127e-05 | 4118
ALTO 1125CB | ALTO 1125 | 42031125 |  | 1.5869 | 1.2356 |  | 22.8333 | 0.00088837 | 1310 | 0.077891 | 3392 | 5.3118e-05 | 4119
FMC 1105CB | FMC 1105 | 83871105 |  | 0.34553 | 0.1556 |  | 4.8333 | 0.0010004 | 790 | 0.053073 | 8252 | 5.3096e-05 | 4120
ATASCADERO 1101747522 | ATASCADERO 1101 | 182541101 | FALSE | 1.0639 | 1.0805 | 0.711 | 21 | 0.00034719 | 7185 | 0.22138 | 3116 | 5.3091e-05 | 4121
STAGG 110336598 | STAGG 1103 | 162421103 |  | 2.7131 | 2.4339 |  | 49.5 | 0.0010003 | 791 | 0.053073 | 8251 | 5.3087e-05 | 4122
OAKLAND D 1106CB | OAKLAND D 1106 | 12041106 |  | 1.7665 | 1.7035 |  | 23.1667 | 0.0010002 | 792 | 0.053073 | 8250 | 5.3085e-05 | 4123
MILPITAS 2114CB | MILPITAS 2114 | 82832114 |  | 0.1713 | 0.055914 |  | 3.5833 | 0.0010002 | 793 | 0.053073 | 8250 | 5.3081e-05 | 4124
HUNTERS POINT (P) 110339072 | HUNTERS POINT (P) 1103 | 22331103 |  | 0.16569 | 0 |  | 0.66667 | 0.00099998 | 794 | 0.053073 | 8251 | 5.3072e-05 | 4125
DEL MONTE 2102CB | DEL MONTE 2102 | 182222102 |  | 1.6008 | 1.3032 |  | 27 | 0.00086275 | 1478 | 0.06081 | 6911 | 5.3068e-05 | 4126
SOLEDAD 2101775342 | SOLEDAD 2101 | 182052101 |  | 3.0411 | 1.8924 |  | 46.6667 | 0.00089594 | 1262 | 0.060196 | 6993 | 5.3047e-05 | 4127
KERN POWER 21032487 | KERN POWER 2103 | 255262103 |  | 7.2993 | 1.1678 |  | 106.9167 | 0.00097017 | 917 | 0.054632 | 7819 | 5.3046e-05 | 4128
SF H 110388014 | SF H 1103 | 22101103 |  | 1.004 | 1.1885 |  | 14.0833 | 0.00099943 | 795 | 0.053073 | 8252 | 5.3043e-05 | 4129
LAKEWOOD 1102CB | LAKEWOOD 1102 | 13531102 | TRUE | 9.6098 | 6.3705 | 0.082204 | 132.5 | 0.00073924 | 2608 | 0.079719 | 3387 | 5.3035e-05 | 4130
KEARNEY 1113CB | KEARNEY 1113 | 252701113 |  | 0.62688 | 0 |  | 6 | 0.00068505 | 3276 | 0.0774 | 3397 | 5.3022e-05 | 4131
WESTPARK 11091508 | WESTPARK 1109 | 253701109 |  | 4.7321 | 3.8495 |  | 75.3333 | 0.00099901 | 796 | 0.053073 | 8251 | 5.302e-05 | 4132
DEL MONTE 2105176544 | DEL MONTE 2105 | 182222105 |  | 2.4317 | 2.0425 |  | 31.5 | 0.00069653 | 3146 | 0.087896 | 3352 | 5.301e-05 | 4133
KERN POWER 21054930 | KERN POWER 2105 | 255262105 |  | 0.75909 | 0 |  | 10 | 0.0009986 | 798 | 0.053073 | 8251 | 5.2999e-05 | 4134
DEL MAR 11032716 | DEL MAR 1103 | 152581103 |  | 0.71973 | 0.16257 |  | 13 | 0.00078414 | 2109 | 0.067403 | 5665 | 5.2989e-05 | 4135
OAKLAND L 1103CB | OAKLAND L 1103 | 12111103 |  | 0.29117 | 0.24464 |  | 5.8333 | 0.00099823 | 799 | 0.053073 | 8252 | 5.2979e-05 | 4136
HICKS 2101XR548 | HICKS 2101 | 83432101 | FALSE | 7.8556 | 1.2008 | 0.64533 | 138 | 0.00034878 | 7161 | 0.17489 | 3178 | 5.2949e-05 | 4137
WYANDOTTE 1103CB | WYANDOTTE 1103 | 102911103 | TRUE | 7.9061 | 2.3522 | 0.21594 | 117.0833 | 0.00079663 | 1997 | 0.069807 | 5075 | 5.2945e-05 | 4138
EDENVALE 2105XR350 | EDENVALE 2105 | 82952105 |  | 0.11997 | 0 |  | 1.5 | 0.00099739 | 801 | 0.053073 | 8251 | 5.2934e-05 | 4139
CASTRO VALLEY 1105MR236 | CASTRO VALLEY 1105 | 14091105 | FALSE | 8.4841 | 8.4661 | 2.2793 | 122.5 | 0.00064002 | 3823 | 0.098703 | 3317 | 5.2933e-05 | 4140
EDENVALE 1102CB | EDENVALE 1102 | 82951102 |  | 1.945 | 0.84063 |  | 24.5833 | 0.00098888 | 840 | 0.053567 | 8077 | 5.2931e-05 | 4141
SF H 1111144648 | SF H 1111 | 22101111 |  | 0.021127 | 0 |  | 0.2 | 0.00099675 | 802 | 0.053073 | 8251 | 5.29e-05 | 4142
SAN RAFAEL 11051806 | SAN RAFAEL 1105 | 42011105 |  | 1.8954 | 0.11956 |  | 35.5 | 0.00079207 | 2044 | 0.066611 | 6165 | 5.2885e-05 | 4143
MT EDEN 1107CB | MT EDEN 1107 | 13761107 |  | 1.3881 | 0.73379 |  | 14.8167 | 0.00099603 | 805 | 0.053073 | 8253 | 5.2862e-05 | 4144
COTTLE 1702CB | COTTLE 1702 | 163711702 |  | 2.2833 | 1.4519 |  | 36.6667 | 0.00099406 | 813 | 0.053307 | 8174 | 5.2854e-05 | 4145
TAFT 110439520 | TAFT 1104 | 252081104 |  | 1.2468 | 1.6571 |  | 28.5 | 0.00094636 | 1026 | 0.055823 | 7609 | 5.2844e-05 | 4146
LINCOLN 1104685276 | LINCOLN 1104 | 153701104 | FALSE | 21.7154 | 0.54932 | 5.5157 | 392.5 | 0.00013453 | 10845 | 0.41004 | 2903 | 5.2842e-05 | 4147
WEST SACRAMENTO 1106CB | WEST SACRAMENTO 1106 | 63131106 |  | 2.8536 | 1.4785 |  | 53.3333 | 0.00098453 | 843 | 0.053757 | 8014 | 5.2839e-05 | 4148
MEADOW LANE 2103C510R | MEADOW LANE 2103 | 14302103 |  | 6.1652 | 4.0733 |  | 98.3333 | 0.00091777 | 1159 | 0.05836 | 7240 | 5.2838e-05 | 4149
KERN OIL 11104083 | KERN OIL 1110 | 252721110 |  | 4.1536 | 3.2272 |  | 51.6667 | 0.00099538 | 807 | 0.053073 | 8253 | 5.2827e-05 | 4150
WEST FRESNO 1106CB | WEST FRESNO 1106 | 253731106 |  | 3.384 | 2.5917 |  | 35.3095 | 0.0009904 | 829 | 0.053302 | 8177 | 5.2823e-05 | 4151
MT EDEN 1110CB | MT EDEN 1110 | 13761110 |  | 2.4838 | 0.31066 |  | 21.9333 | 0.00099504 | 809 | 0.053073 | 8252 | 5.2809e-05 | 4152
POTRERO PP (A) 110198694 | POTRERO PP (A) 1101 | 22031101 |  | 2.3895 | 2.0032 |  | 23.6667 | 0.00099494 | 810 | 0.053073 | 8249 | 5.2804e-05 | 4153
HARDING 0402CB | HARDING 0402 | 163310402 |  | 3.8609 | 3.1336 |  | 50.5 | 0.00099484 | 811 | 0.053073 | 8251 | 5.2799e-05 | 4154
GREENBRAE 1103CB | GREENBRAE 1103 | 43091103 |  | 1.6606 | 0.73788 |  | 25.5 | 0.00085318 | 1555 | 0.061562 | 6818 | 5.2798e-05 | 4155
BAIR 1105CB | BAIR 1105 | 24261105 |  | 2.2926 | 0.72944 |  | 50.6429 | 0.00098362 | 852 | 0.053898 | 7976 | 5.2761e-05 | 4156
CHICO B 11052482 | CHICO B 1105 | 102491105 |  | 5.0689 | 3.9751 |  | 71.3333 | 0.00098969 | 834 | 0.053282 | 8186 | 5.2759e-05 | 4157
MANTECA 170184188 | MANTECA 1701 | 162611701 |  | 1.0207 | 0.089602 |  | 15.5 | 0.00099372 | 814 | 0.053073 | 8251 | 5.2739e-05 | 4158
KERN POWER 2104CB | KERN POWER 2104 | 255262104 |  | 4.877 | 1.1569 |  | 72.4 | 0.00088275 | 1351 | 0.063535 | 6608 | 5.2728e-05 | 4159
STAGG 21088924 | STAGG 2108 | 162422108 |  | 2.3266 | 2.9065 |  | 31.5 | 0.00099335 | 817 | 0.053073 | 8251 | 5.272e-05 | 4160
NEWARK 12KV 1101CB | NEWARK 12KV 1101 | 12221101 |  | 1.5142 | 0.080182 |  | 17.6167 | 0.00095288 | 1001 | 0.055604 | 7656 | 5.2712e-05 | 4161
SUISUN 1110CB | SUISUN 1110 | 62131110 |  | 2.923 | 3.2888 |  | 48.8333 | 0.00088174 | 1355 | 0.058609 | 7210 | 5.2702e-05 | 4162
LAS POSITAS 2105CB | LAS POSITAS 2105 | 14402105 |  | 3.5695 | 0.30502 |  | 64.5 | 0.00086005 | 1495 | 0.062255 | 6739 | 5.2698e-05 | 4163
STOCKTON A 1105CB | STOCKTON A 1105 | 162371105 |  | 10.7176 | 5.759 |  | 135.6 | 0.00099265 | 820 | 0.053073 | 8250 | 5.2682e-05 | 4164
SAN JOSE B 1115CB | SAN JOSE B 1115 | 82261115 |  | 0.11057 | 0.013104 |  | 2.5833 | 0.00099169 | 821 | 0.053073 | 8251 | 5.2632e-05 | 4165
MEADOW LANE 210890850 | MEADOW LANE 2108 | 14302108 |  | 3.2219 | 3.4019 |  | 39.1667 | 0.00099106 | 824 | 0.053073 | 8251 | 5.2598e-05 | 4166
OAKLAND J 1117CB | OAKLAND J 1117 | 12091117 |  | 2.6724 | 2.1009 |  | 35.1667 | 0.00099077 | 825 | 0.053073 | 8247 | 5.2583e-05 | 4167
WEST FRESNO 110936256 | WEST FRESNO 1109 | 253731109 |  | 1.5899 | 1.9069 |  | 23.8333 | 0.00099055 | 828 | 0.053073 | 8252 | 5.2571e-05 | 4168
BORDEN 1103CB | BORDEN 1103 | 255121103 |  | 0.055047 | 0 |  | 0.83333 | 0.00067905 | 3337 | 0.0774 | 3396 | 5.2558e-05 | 4169
STOCKTON A 1107CB | STOCKTON A 1107 | 162371107 |  | 7.7504 | 7.4434 |  | 92.9 | 0.00099018 | 830 | 0.053073 | 8249 | 5.2552e-05 | 4170
STOCKTON A 110444086 | STOCKTON A 1104 | 162371104 |  | 6.7417 | 4.6733 |  | 83.2833 | 0.00098972 | 833 | 0.053073 | 8252 | 5.2527e-05 | 4171
CHICO B 1101CB | CHICO B 1101 | 102491101 |  | 4.6118 | 2.6418 |  | 82.5 | 0.00093583 | 1070 | 0.056882 | 7454 | 5.2502e-05 | 4172
SF E 1101CB | SF E 1101 | 22071101 |  | 0.037173 | 0 |  | 0.33333 | 0.00098914 | 838 | 0.053073 | 8251 | 5.2496e-05 | 4173
CALIFORNIA AVE 1116CB | CALIFORNIA AVE 1116 | 252281116 |  | 7.0881 | 5.2143 |  | 116.6667 | 0.00098349 | 853 | 0.053368 | 8147 | 5.2485e-05 | 4174
DEL MAR 210631415 | DEL MAR 2106 | 152582106 |  | 0.0019236 | 0 |  | 0.5 | 0.00078251 | 2126 | 0.067035 | 5975 | 5.2455e-05 | 4175
RED BLUFF 11041630 | RED BLUFF 1104 | 103541104 | FALSE | 14.0735 | 1.4552 | 2.1184 | 275.5 | 0.00027507 | 8531 | 0.22829 | 3107 | 5.2425e-05 | 4176
TASSAJARA 2113MR280 | TASSAJARA 2113 | 14662113 |  | 0.76166 | 0.3304 |  | 15.5 | 0.00092071 | 1146 | 0.057177 | 7408 | 5.2389e-05 | 4177
LAKEWOOD 2223W540R | LAKEWOOD 2223 | 13532223 |  | 6.6404 | 5.7441 |  | 113.8333 | 0.00084465 | 1615 | 0.062284 | 6735 | 5.2384e-05 | 4178
LAKEWOOD 222565266 | LAKEWOOD 2225 | 13532225 |  | 1.6454 | 0.88077 |  | 24.3333 | 0.00090503 | 1212 | 0.058796 | 7187 | 5.2367e-05 | 4179
BEAR VALLEY 21014500 | BEAR VALLEY 2101 | 252192101 | FALSE | 82.5401 | 2.5935 | 21.3154 | 1631 | 9.9949e-05 | 11049 | 0.62859 | 2705 | 5.2303e-05 | 4180
TIDEWATER 2105CB | TIDEWATER 2105 | 14652105 |  | 10.6053 | 6.4821 |  | 160 | 0.00098079 | 868 | 0.053377 | 8144 | 5.2287e-05 | 4181
TIDEWATER 21091784 | TIDEWATER 2109 | 14652109 |  | 0.85993 | 0.32729 |  | 12 | 0.00098517 | 841 | 0.053073 | 8252 | 5.2285e-05 | 4182
CHICO A 1101CB | CHICO A 1101 | 102051101 |  | 2.9015 | 2.2157 |  | 42.75 | 0.00097862 | 879 | 0.053398 | 8137 | 5.227e-05 | 4183
CALIFORNIA AVE 110663184 | CALIFORNIA AVE 1106 | 252281106 |  | 4.975 | 4.0935 |  | 70.1667 | 0.00097452 | 897 | 0.054633 | 7818 | 5.2261e-05 | 4184
FAIRVIEW 220893616 | FAIRVIEW 2208 | 13432208 |  | 1.1193 | 0.34114 |  | 18.5 | 0.00098442 | 844 | 0.053073 | 8251 | 5.2246e-05 | 4185
SAN JOSE B 1112XR284 | SAN JOSE B 1112 | 82261112 |  | 1.0827 | 0.26612 |  | 17.5 | 0.00098424 | 845 | 0.053073 | 8251 | 5.2236e-05 | 4186
OAKLAND C 1132CB | OAKLAND C 1132 | 12011132 |  | 0.98115 | 0.13938 |  | 10.95 | 0.00098418 | 846 | 0.053073 | 8251 | 5.2233e-05 | 4187
STOCKDALE 111114072 | STOCKDALE 1111 | 254071111 |  | 0.58297 | 0.65395 |  | 8 | 0.00098408 | 847 | 0.053073 | 8251 | 5.2228e-05 | 4188
MANTECA 1704CB | MANTECA 1704 | 162611704 |  | 4.4818 | 2.9492 |  | 59.3333 | 0.00098407 | 848 | 0.053073 | 8251 | 5.2227e-05 | 4189
SARATOGA 1109CB | SARATOGA 1109 | 83371109 |  | 4.5595 | 4.5331 |  | 78.6667 | 0.00088908 | 1306 | 0.058797 | 7186 | 5.2211e-05 | 4190
BERESFORD 0401CB | BERESFORD 0401 | 24040401 |  | 1.0764 | 0.54034 |  | 8.6667 | 0.00098376 | 849 | 0.053073 | 8250 | 5.2211e-05 | 4191
EMBARCADERO (Z) 1114CB | EMBARCADERO (Z) 1114 | 22871114 |  | 0.0018939 | 0 |  | 1 | 0.00098368 | 850 | 0.053073 | 8251 | 5.2207e-05 | 4192
MANTECA 1707CB | MANTECA 1707 | 162611707 |  | 3.4184 | 1.884 |  | 43.5 | 0.00098364 | 851 | 0.053073 | 8251 | 5.2205e-05 | 4193
GEYSERVILLE 1101122 | GEYSERVILLE 1101 | 42891101 | TRUE | 6.9458 | 0.32914 | 0.57373 | 137.5 | 0.00025529 | 8978 | 0.62437 | 2709 | 5.2172e-05 | 4194
WINDSOR 11025066 | WINDSOR 1102 | 43501102 |  | 0.012784 | 0 |  | 0.5 | 0.00098297 | 854 | 0.053073 | 8251 | 5.2169e-05 | 4195
DIXON LANDING 2103CB | DIXON LANDING 2103 | 14722103 |  | 0.53779 | 0 |  | 8.5 | 0.00084703 | 1596 | 0.061265 | 6861 | 5.2162e-05 | 4196
GREEN VALLEY 210412552 | GREEN VALLEY 2104 | 83192104 |  | 5.5891 | 2.2779 |  | 82.5833 | 0.00089001 | 1297 | 0.059136 | 7141 | 5.2161e-05 | 4197
RENFRO 21071388 | RENFRO 2107 | 254572107 |  | 0.046436 | 0 |  | 2.5 | 0.0009826 | 856 | 0.053073 | 8251 | 5.2149e-05 | 4198
CAROLANDS 04018886 | CAROLANDS 0401 | 24060401 |  | 0.012752 | 0 |  | 0.33333 | 0.00077471 | 2207 | 0.067315 | 5721 | 5.2149e-05 | 4199
PANAMA 2101CB | PANAMA 2101 | 253422101 |  | 1.6983 | 0.021227 |  | 31.3333 | 0.00083051 | 1728 | 0.064103 | 6528 | 5.2146e-05 | 4200
SONOMA 1104914376 | SONOMA 1104 | 42721104 | TRUE | 6.4966 | 2.3639 | 0.45013 | 116.5 | 0.00052041 | 5175 | 0.14429 | 3219 | 5.2139e-05 | 4201
ALMADEN 1110CB | ALMADEN 1110 | 82311110 |  | 0.9912 | 0.30449 |  | 14.8333 | 0.00098222 | 858 | 0.053073 | 8251 | 5.2129e-05 | 4202
MILPITAS 2110XR276 | MILPITAS 2110 | 82832110 |  | 0.70093 | 0.18553 |  | 15 | 0.00098216 | 859 | 0.053073 | 8251 | 5.2126e-05 | 4203
MANCHESTER 1109D6083 | MANCHESTER 1109 | 253921109 |  | 0.25166 | 0.15973 |  | 4.5 | 0.00098214 | 860 | 0.053073 | 8251 | 5.2125e-05 | 4204
MAGUNDEN 2109CB | MAGUNDEN 2109 | 252772109 |  | 5.5756 | 2.6563 |  | 85.5595 | 0.00097444 | 898 | 0.053552 | 8084 | 5.2109e-05 | 4205
MONTAGUE 2103CB | MONTAGUE 2103 | 83892103 |  | 0.94372 | 0.65659 |  | 16 | 0.00098173 | 862 | 0.053073 | 8251 | 5.2103e-05 | 4206
BRITTON 111477584 | BRITTON 1114 | 83611114 |  | 0.93712 | 0.24538 |  | 16.8333 | 0.00098165 | 863 | 0.053073 | 8252 | 5.2099e-05 | 4207
LAKEWOOD 2223CB | LAKEWOOD 2223 | 13532223 |  | 1.8742 | 1.4696 |  | 32.5 | 0.00080112 | 1960 | 0.064 | 6543 | 5.209e-05 | 4208
HALF MOON BAY 1102CB | HALF MOON BAY 1102 | 24101102 | TRUE | 3.3904 | 0.74458 | 0.11841 | 57.8333 | 0.00054687 | 4891 | 0.10719 | 3297 | 5.2087e-05 | 4209
HARDING 0401CB | HARDING 0401 | 163310401 |  | 1.013 | 0.87095 |  | 12.6167 | 0.00098132 | 864 | 0.053073 | 8252 | 5.2081e-05 | 4210
CALIFORNIA AVE 1108CB | CALIFORNIA AVE 1108 | 252281108 |  | 4.1289 | 1.4494 |  | 63.5833 | 0.00098129 | 865 | 0.053073 | 8251 | 5.208e-05 | 4211
MC KEE 110870535 | MC KEE 1108 | 83531108 |  | 3.3028 | 0.61002 |  | 60.5 | 0.00023881 | 9306 | 0.39404 | 2920 | 5.2062e-05 | 4212
EDENVALE 2107CB | EDENVALE 2107 | 82952107 |  | 0.069859 | 0 |  | 1 | 0.00098064 | 869 | 0.053073 | 8251 | 5.2045e-05 | 4213
MORGAN HILL 2109XR246 | MORGAN HILL 2109 | 83242109 | TRUE | 3.891 | 0.84588 | 0.030661 | 87.5 | 0.00044668 | 5944 | 0.14478 | 3218 | 5.2015e-05 | 4214
CHICO B 1105CB | CHICO B 1105 | 102491105 |  | 3.5229 | 2.9579 |  | 60.3333 | 0.00092782 | 1109 | 0.056381 | 7516 | 5.2014e-05 | 4215
BULLARD 1103CB | BULLARD 1103 | 253961103 |  | 7.3622 | 2.1614 |  | 101.6667 | 0.00097997 | 872 | 0.053073 | 8251 | 5.201e-05 | 4216
CASTRO VALLEY 1110MR341 | CASTRO VALLEY 1110 | 14091110 | TRUE | 0.66772 | 0.1651 | 0.1587 | 13 | 0.00077434 | 2211 | 0.065973 | 6278 | 5.1997e-05 | 4217
LAS POSITAS 2109MR419 | LAS POSITAS 2109 | 14402109 |  | 3.3165 | 2.9857 |  | 58 | 0.00097946 | 873 | 0.053073 | 8251 | 5.1982e-05 | 4218
MANCHESTER 111255406 | MANCHESTER 1112 | 253921112 |  | 10.4369 | 8.5228 |  | 154.1667 | 0.00097894 | 876 | 0.053128 | 8241 | 5.1968e-05 | 4219
EL CAPITAN 210990230 | EL CAPITAN 2109 | 253882109 |  | 1.9593 | 1.5668 |  | 34.6667 | 0.00094961 | 1013 | 0.055178 | 7726 | 5.1967e-05 | 4220
ASHLAN AVE 110685038 | ASHLAN AVE 1106 | 252051106 |  | 2.9346 | 0.82196 |  | 41.25 | 0.00097909 | 874 | 0.053073 | 8251 | 5.1963e-05 | 4221
EAST GRAND 1108693548 | EAST GRAND 1108 | 22571108 |  | 1.5543 | 0.36134 |  | 23.3333 | 0.00097865 | 878 | 0.053073 | 8252 | 5.194e-05 | 4222
COVELO 1101CB | COVELO 1101 | 43061101 |  | 0.017268 | 0 |  | 0.33333 | 0.00077517 | 2201 | 0.067 | 6056 | 5.1936e-05 | 4223
POINT ARENA 1101476 | POINT ARENA 1101 | 43381101 | FALSE | 15.1434 | 0.77465 | 2.4352 | 290 | 0.00019776 | 10078 | 0.23863 | 3097 | 5.1909e-05 | 4224
SYCAMORE CREEK 110272104 | SYCAMORE CREEK 1102 | 102971102 |  | 0.563 | 0.062063 |  | 10.5 | 0.00097767 | 880 | 0.053073 | 8251 | 5.1888e-05 | 4225
DEL MONTE 2103CB | DEL MONTE 2103 | 182222103 |  | 3.7404 | 2.7247 |  | 61.8333 | 0.00091907 | 1155 | 0.056845 | 7463 | 5.1885e-05 | 4226
EVERGREEN 2104CB | EVERGREEN 2104 | 82012104 |  | 1.4387 | 0.29291 |  | 20.0833 | 0.00095317 | 1000 | 0.05446 | 7851 | 5.1878e-05 | 4227
MEADOW LANE 2105CB | MEADOW LANE 2105 | 14302105 |  | 12.4215 | 9.1852 |  | 175.6667 | 0.00097743 | 881 | 0.053073 | 8252 | 5.1875e-05 | 4228
NEWARK 12KV 1108CB | NEWARK 12KV 1108 | 12221108 |  | 0.96286 | 0.11969 |  | 11.9167 | 0.00095435 | 992 | 0.055114 | 7734 | 5.1864e-05 | 4229
BELL 111050182 | BELL 1110 | 152701110 |  | 1.4207 | 0.94585 |  | 28.5 | 0.00084222 | 1637 | 0.062734 | 6685 | 5.1863e-05 | 4230
NAPA 1110CB | NAPA 1110 | 42021110 |  | 2.091 | 1.1743 |  | 26.9167 | 0.00097705 | 883 | 0.053073 | 8250 | 5.1855e-05 | 4231
GALLO 1102CB | GALLO 1102 | 254901102 |  | 0.002823 | 0 |  | 0.5 | 0.00066994 | 3437 | 0.0774 | 3397 | 5.1853e-05 | 4232
BELLE HAVEN 1105819370 | BELLE HAVEN 1105 | 24021105 |  | 1.0053 | 0.56442 |  | 13.5 | 0.00097694 | 884 | 0.053073 | 8251 | 5.1849e-05 | 4233
BELLEVUE 21015092 | BELLEVUE 2101 | 43182101 |  | 0.012653 | 0 |  | 1.5 | 0.0009767 | 885 | 0.053073 | 8251 | 5.1836e-05 | 4234
CASTRO VALLEY 1110MR525 | CASTRO VALLEY 1110 | 14091110 | TRUE | 0.049847 | 0.049246 | 0.051998 | 0.5 | 0.00033279 | 7411 | 0.06714 | 5862 | 5.1836e-05 | 4235
MOUNTAIN VIEW 1112CB | MOUNTAIN VIEW 1112 | 82031112 |  | 0.9735 | 0.12989 |  | 13.2333 | 0.00097608 | 887 | 0.053073 | 8251 | 5.1803e-05 | 4236
ROSSMOOR 110542088 | ROSSMOOR 1105 | 14161105 |  | 1.1818 | 0.82104 |  | 21 | 0.00076342 | 2340 | 0.067772 | 5484 | 5.1787e-05 | 4237
DEL MONTE 2105CB | DEL MONTE 2105 | 182222105 |  | 5.4483 | 3.9314 |  | 88.6667 | 0.00092193 | 1138 | 0.055949 | 7585 | 5.1785e-05 | 4238
TAFT 11013512 | TAFT 1101 | 252081101 |  | 0.47235 | 0.48213 |  | 8 | 0.0009757 | 888 | 0.053073 | 8251 | 5.1783e-05 | 4239
BARTON 1108CB | BARTON 1108 | 253571108 |  | 4.8153 | 4.0234 |  | 66.6667 | 0.00097565 | 889 | 0.053073 | 8250 | 5.1781e-05 | 4240
NEWARK 21KV 2107CB | NEWARK 21KV 2107 | 12232107 |  | 2.3857 | 0.93083 |  | 43.1667 | 0.00097564 | 890 | 0.053073 | 8252 | 5.178e-05 | 4241
FAIRVIEW 2207M500R | FAIRVIEW 2207 | 13432207 |  | 4.0368 | 0.48282 |  | 66.1667 | 0.00084462 | 1616 | 0.061442 | 6839 | 5.1765e-05 | 4242
7TH STANDARD 210281004 | 7TH STANDARD 2102 | 254582102 |  | 0.64018 | 0 |  | 10.3333 | 0.00096303 | 940 | 0.053857 | 7987 | 5.1744e-05 | 4243
CALIFORNIA AVE 1108839702 | CALIFORNIA AVE 1108 | 252281108 |  | 5.3722 | 5.3784 |  | 76.3333 | 0.00097473 | 895 | 0.053073 | 8251 | 5.1731e-05 | 4244
DALY CITY 1104CB | DALY CITY 1104 | 22641104 |  | 2.0047 | 1.2477 |  | 27 | 0.0009537 | 995 | 0.0536 | 8060 | 5.1729e-05 | 4245
WEST SACRAMENTO 1108599922 | WEST SACRAMENTO 1108 | 63131108 |  | 1.192 | 1.4038 |  | 19.8333 | 0.00097435 | 899 | 0.053073 | 8252 | 5.1712e-05 | 4246
FORT BRAGG A 110436526 | FORT BRAGG A 1104 | 42761104 | TRUE | 6.5753 | 6.8951 | 0.0031904 | 88 | 0.00059212 | 4391 | 0.087498 | 3354 | 5.1686e-05 | 4247
LIVERMORE 11036792 | LIVERMORE 1103 | 12141103 |  | 0.0028409 | 0 |  | 0.5 | 0.0009738 | 902 | 0.053073 | 8251 | 5.1682e-05 | 4248
BELMONT 110347804 | BELMONT 1103 | 24031103 |  | 6.8573 | 5.6797 |  | 101.8333 | 0.00060059 | 4290 | 0.089833 | 3342 | 5.1664e-05 | 4249
ASHLAN AVE 211931576 | ASHLAN AVE 2119 | 252052119 |  | 4.2909 | 2.6535 |  | 61.8333 | 0.00097333 | 904 | 0.053073 | 8250 | 5.1657e-05 | 4250
CASTRO VALLEY 1108MR580 | CASTRO VALLEY 1108 | 14091108 |  | 0.41517 | 0.43602 |  | 5.3333 | 0.00097316 | 905 | 0.053073 | 8252 | 5.1648e-05 | 4251
CONTRA COSTA 2103304858 | CONTRA COSTA 2103 | 13652103 |  | 0.64289 | 0.59628 |  | 8.5 | 0.00097298 | 906 | 0.053073 | 8251 | 5.1638e-05 | 4252
PAUL SWEET 2102156208 | PAUL SWEET 2102 | 83252102 |  | 6.2974 | 3.0878 |  | 101.95 | 0.00076362 | 2339 | 0.066828 | 6116 | 5.1638e-05 | 4253
DEEPWATER 110522130 | DEEPWATER 1105 | 63621105 |  | 0.012668 | 0 |  | 0.5 | 0.00097289 | 907 | 0.053073 | 8251 | 5.1634e-05 | 4254
LAKEWOOD 2107CB | LAKEWOOD 2107 | 13532107 |  | 4.7483 | 2.1796 |  | 53.6667 | 0.00088769 | 1318 | 0.05755 | 7348 | 5.1631e-05 | 4255
FIGARDEN 2112R3150 | FIGARDEN 2112 | 254552112 |  | 0.41605 | 0 |  | 7.5 | 0.00097277 | 909 | 0.053073 | 8251 | 5.1627e-05 | 4256
KERN OIL 11035247 | KERN OIL 1103 | 252721103 |  | 5.5544 | 4.9141 |  | 94.5 | 0.00095697 | 979 | 0.053982 | 7957 | 5.1618e-05 | 4257
SILVERADO 21023010 | SILVERADO 2102 | 43432102 | TRUE | 9.1298 | 1.1287 | 0.14021 | 172 | 0.00058153 | 4504 | 0.12364 | 3262 | 5.1607e-05 | 4258
LAKEWOOD 2112W513R | LAKEWOOD 2112 | 13532112 |  | 2.7519 | 1.0987 |  | 45.8333 | 0.00094284 | 1043 | 0.054896 | 7767 | 5.1595e-05 | 4259
NOTRE DAME 110287268 | NOTRE DAME 1102 | 102041102 |  | 4.4243 | 2.3062 |  | 65.8333 | 0.00082045 | 1814 | 0.062175 | 6750 | 5.1591e-05 | 4260
ASHLAN AVE 1103CB | ASHLAN AVE 1103 | 252051103 |  | 9.2719 | 6.9627 |  | 152.2 | 0.0009715 | 912 | 0.053129 | 8240 | 5.1589e-05 | 4261
OAKLAND D 1111BR268 | OAKLAND D 1111 | 12041111 |  | 0.96463 | 0.68242 |  | 14.5 | 0.00097198 | 911 | 0.053073 | 8251 | 5.1585e-05 | 4262
MONROE 210765424 | MONROE 2107 | 43302107 |  | 4.0095 | 2.344 |  | 74 | 0.00085897 | 1502 | 0.060381 | 6975 | 5.157e-05 | 4263
PUEBLO 2101CB | PUEBLO 2101 | 43292101 |  | 1.9542 | 0.74797 |  | 37.6667 | 0.00091894 | 1156 | 0.056008 | 7579 | 5.1548e-05 | 4264
WESTPARK 11104871 | WESTPARK 1110 | 253701110 |  | 5.4114 | 4.8192 |  | 81 | 0.00097106 | 913 | 0.053073 | 8251 | 5.1537e-05 | 4265
CHICO B 11032464 | CHICO B 1103 | 102491103 |  | 6.7342 | 2.8108 |  | 123.5 | 0.0008555 | 1530 | 0.061146 | 6876 | 5.1528e-05 | 4266
WOODLAND 1105CB | WOODLAND 1105 | 62031105 |  | 2.6986 | 1.3968 |  | 42.6667 | 0.00096405 | 936 | 0.053526 | 8093 | 5.1523e-05 | 4267
BAKERSFIELD 210913182 | BAKERSFIELD 2109 | 253372109 |  | 0.67333 | 1.0008 |  | 12.1667 | 0.00097042 | 916 | 0.053073 | 8251 | 5.1503e-05 | 4268
RED BLUFF 11051564 | RED BLUFF 1105 | 103541105 | FALSE | 10.629 | 1.6446 | 1.1569 | 196 | 0.00033711 | 7347 | 0.25173 | 3079 | 5.1489e-05 | 4269
POTRERO PP (A) 1108CB | POTRERO PP (A) 1108 | 22031108 |  | 1.8795 | 1.6864 |  | 24.1667 | 0.00097007 | 918 | 0.053073 | 8251 | 5.1484e-05 | 4270
SUISUN 1103CB | SUISUN 1103 | 62131103 |  | 0.80204 | 0.32777 |  | 14.3333 | 0.00084013 | 1647 | 0.061887 | 6777 | 5.1476e-05 | 4271
BARTON 110841140 | BARTON 1108 | 253571108 |  | 2.5667 | 3.1376 |  | 44.8333 | 0.00096982 | 919 | 0.053073 | 8250 | 5.1471e-05 | 4272
KIRKER 210695832 | KIRKER 2106 | 14452106 |  | 1.7692 | 1.0548 |  | 19.9167 | 0.00096791 | 928 | 0.053422 | 8120 | 5.1466e-05 | 4273
CONTRA COSTA 2114CB | CONTRA COSTA 2114 | 13652114 |  | 0.49982 | 0.29794 |  | 9 | 0.00096931 | 920 | 0.053073 | 8251 | 5.1444e-05 | 4274
ASHLAN AVE 1104CB | ASHLAN AVE 1104 | 252051104 |  | 7.6185 | 7.2955 |  | 91.2 | 0.00096931 | 921 | 0.053073 | 8251 | 5.1444e-05 | 4275
PITTSBURG 0402CB | PITTSBURG 0402 | 12160402 |  | 1.8696 | 1.8371 |  | 21.75 | 0.00096917 | 922 | 0.053073 | 8252 | 5.1437e-05 | 4276
COTTLE 170490360 | COTTLE 1704 | 163711704 |  | 1.1287 | 0.25832 |  | 17.8333 | 0.00096894 | 923 | 0.053073 | 8252 | 5.1424e-05 | 4277
EAST GRAND 1107540874 | EAST GRAND 1107 | 22571107 |  | 0.065899 | 0 |  | 2.5 | 0.00096866 | 924 | 0.053073 | 8251 | 5.1409e-05 | 4278
SYCAMORE CREEK 1104CB | SYCAMORE CREEK 1104 | 102971104 |  | 8.1333 | 5.9861 |  | 118 | 0.00095543 | 986 | 0.053643 | 8049 | 5.1406e-05 | 4279
EDES 1101CR354 | EDES 1101 | 13681101 |  | 1.0649 | 0.6039 |  | 15.6667 | 0.00096859 | 925 | 0.053073 | 8252 | 5.1406e-05 | 4280
MEADOW LANE 210865456 | MEADOW LANE 2108 | 14302108 |  | 3.3497 | 2.6366 |  | 46.3333 | 0.00096261 | 945 | 0.053783 | 8003 | 5.1397e-05 | 4281
CONTRA COSTA 210313962 | CONTRA COSTA 2103 | 13652103 |  | 0.26353 | 0.037442 |  | 4.5 | 0.00079751 | 1989 | 0.065484 | 6362 | 5.1396e-05 | 4282
BELMONT 1103CB | BELMONT 1103 | 24031103 |  | 1.0142 | 0.13195 |  | 10.25 | 0.00096827 | 926 | 0.053073 | 8251 | 5.1388e-05 | 4283
STAFFORD 11026121 | STAFFORD 1102 | 43201102 |  | 0.40942 | 0.29249 |  | 7.5 | 0.00082343 | 1789 | 0.06273 | 6686 | 5.1388e-05 | 4284
TASSAJARA 210865438 | TASSAJARA 2108 | 14662108 |  | 1.4721 | 0.86327 |  | 20.6667 | 0.00076191 | 2354 | 0.067401 | 5668 | 5.1387e-05 | 4285
STOCKTON A 0404CB | STOCKTON A 0404 | 162370404 |  | 5.1724 | 4.3608 |  | 57.2333 | 0.0009682 | 927 | 0.053073 | 8252 | 5.1385e-05 | 4286
WEST FRESNO 1104CB | WEST FRESNO 1104 | 253731104 |  | 2.939 | 2.6803 |  | 45.0179 | 0.00088097 | 1358 | 0.058434 | 7229 | 5.138e-05 | 4287
SAN RAFAEL 110991742 | SAN RAFAEL 1109 | 42011109 |  | 1.231 | 1.0003 |  | 19 | 0.00083208 | 1712 | 0.061502 | 6831 | 5.1371e-05 | 4288
ALTO 11256405 | ALTO 1125 | 42031125 |  | 2.0678 | 1.598 |  | 27.3333 | 0.00086213 | 1483 | 0.059248 | 7123 | 5.1361e-05 | 4289
SAN JOSE A 0404CB | SAN JOSE A 0404 | 82250404 |  | 1.7389 | 1.1915 |  | 26.4167 | 0.0009677 | 929 | 0.053073 | 8249 | 5.1359e-05 | 4290
WHEATLAND 1105248490 | WHEATLAND 1105 | 152811105 | FALSE | 26.9587 | 0.16917 | 10.6202 | 480 | 0.00011558 | 10979 | 0.49208 | 2832 | 5.1346e-05 | 4291
SALINAS 1104CB | SALINAS 1104 | 182011104 |  | 2.2297 | 0.85113 |  | 32.6667 | 0.00086474 | 1458 | 0.057865 | 7313 | 5.1338e-05 | 4292
BUTTE 1105CB | BUTTE 1105 | 103081105 |  | 2.7331 | 0.49839 |  | 48 | 0.0008143 | 1864 | 0.063735 | 6574 | 5.13e-05 | 4293
SAN RAMON 2111CB | SAN RAMON 2111 | 14232111 |  | 7.1102 | 4.8296 |  | 114.1667 | 0.00083939 | 1650 | 0.06026 | 6988 | 5.1276e-05 | 4294
ALTO 1121CB | ALTO 1121 | 42031121 |  | 3.6263 | 1.4976 |  | 47.8333 | 0.00088781 | 1317 | 0.057101 | 7424 | 5.127e-05 | 4295
CHOLAME 2102X16 | CHOLAME 2102 | 182562102 |  | 17.3085 | 0.3622 |  | 346.3333 | 0.00010946 | 11017 | 0.55102 | 2781 | 5.1249e-05 | 4296
SONOMA 1105513138 | SONOMA 1105 | 42721105 |  | 0.023959 | 0 |  | 0.5 | 0.00076434 | 2332 | 0.067035 | 5975 | 5.1238e-05 | 4297
MOSHER 21079614 | MOSHER 2107 | 163722107 |  | 0.011364 | 0 |  | 1 | 0.00077735 | 2180 | 0.065236 | 6401 | 5.1233e-05 | 4298
SAN RAFAEL 1101312 | SAN RAFAEL 1101 | 42011101 |  | 2.2592 | 2.1171 |  | 37 | 0.0006544 | 3648 | 0.075251 | 4376 | 5.1206e-05 | 4299
WALNUT CREEK 0403CB | WALNUT CREEK 0403 | 12200403 |  | 0.51077 | 0.23332 |  | 9.1667 | 0.00091026 | 1185 | 0.055858 | 7602 | 5.1197e-05 | 4300
HOLLISTER 210347052 | HOLLISTER 2103 | 182492103 |  | 0.58232 | 0.38782 |  | 8.1667 | 0.00096417 | 933 | 0.053073 | 8250 | 5.1171e-05 | 4301
STOCKTON A 110611700 | STOCKTON A 1106 | 162371106 |  | 3.6829 | 3.2545 |  | 50.1667 | 0.0009641 | 934 | 0.053073 | 8251 | 5.1167e-05 | 4302
OAKLAND D 1133CR290 | OAKLAND D 1133 | 12041133 |  | 0.29434 | 0.25268 |  | 4.1667 | 0.00096409 | 935 | 0.053073 | 8252 | 5.1167e-05 | 4303
TRACY 1105CB | TRACY 1105 | 162881105 |  | 4.7216 | 2.2367 |  | 69.2 | 0.00095775 | 970 | 0.053677 | 8040 | 5.1164e-05 | 4304
COLUMBUS 111077274 | COLUMBUS 1110 | 253951110 |  | 0.011451 | 0 |  | 0.5 | 0.00096403 | 937 | 0.053073 | 8251 | 5.1164e-05 | 4305
WEST LANE 1103CB | WEST LANE 1103 | 163621103 |  | 4.0848 | 2.0709 |  | 69.5 | 0.00096014 | 960 | 0.05332 | 8168 | 5.1151e-05 | 4306
OAKLAND L 1102CB | OAKLAND L 1102 | 12111102 |  | 1.28 | 0.98842 |  | 14.6667 | 0.00096329 | 938 | 0.053073 | 8252 | 5.1124e-05 | 4307
OROVILLE 1104CB | OROVILLE 1104 | 102521104 |  | 0.90206 | 0.1763 |  | 15.75 | 0.00094755 | 1020 | 0.053957 | 7967 | 5.1118e-05 | 4308
VACAVILLE 1111772224 | VACAVILLE 1111 | 63601111 | TRUE | 0.077491 | 0 | 0.042027 | 1.5 | 0.00076255 | 2346 | 0.067035 | 5975 | 5.1117e-05 | 4309
TRACY 110313302 | TRACY 1103 | 162881103 |  | 0.017895 | 0 |  | 1.5 | 0.00096269 | 943 | 0.053073 | 8251 | 5.1093e-05 | 4310
EL CAPITAN 110690310 | EL CAPITAN 1106 | 253881106 |  | 0.91235 | 0.51506 |  | 12 | 0.00096256 | 946 | 0.053073 | 8251 | 5.1086e-05 | 4311
TIDEWATER 2104226374 | TIDEWATER 2104 | 14652104 |  | 13.1005 | 10.8487 |  | 174.25 | 0.00095011 | 1011 | 0.053631 | 8052 | 5.1069e-05 | 4312
PAUL SWEET 210312075 | PAUL SWEET 2103 | 83252103 |  | 1.9295 | 1.2384 |  | 28.3667 | 0.00090253 | 1221 | 0.056777 | 7470 | 5.106e-05 | 4313
ASHLAN AVE 1116CB | ASHLAN AVE 1116 | 252051116 |  | 9.6843 | 11.9642 |  | 130.5833 | 0.00096177 | 948 | 0.053073 | 8250 | 5.1044e-05 | 4314
LARKIN (Y) 1135CB | LARKIN (Y) 1135 | 22801135 |  | 0.50153 | 0.27383 |  | 3.5 | 0.00096175 | 949 | 0.053073 | 8251 | 5.1043e-05 | 4315
HAMMER 1106CB | HAMMER 1106 | 163301106 |  | 1.4411 | 1.5895 |  | 21.6667 | 0.00096173 | 950 | 0.053073 | 8250 | 5.1041e-05 | 4316
BELLEVUE 2103388 | BELLEVUE 2103 | 43182103 |  | 0.90026 | 0.35876 |  | 15 | 0.00076197 | 2353 | 0.06848 | 5292 | 5.1034e-05 | 4317
POTRERO PP (A) 1109CB | POTRERO PP (A) 1109 | 22031109 |  | 1.6259 | 0.061932 |  | 13.25 | 0.00096154 | 951 | 0.053073 | 8251 | 5.1031e-05 | 4318
BAKERSFIELD 11163742 | BAKERSFIELD 1116 | 253371116 |  | 9.6164 | 8.9825 |  | 141.5 | 0.00096149 | 952 | 0.053073 | 8251 | 5.1029e-05 | 4319
CONTRA COSTA 2109827875 | CONTRA COSTA 2109 | 13652109 |  | 2.453 | 0.19228 |  | 37.5 | 0.00088447 | 1341 | 0.059114 | 7145 | 5.1023e-05 | 4320
VINEYARD 2105MR256 | VINEYARD 2105 | 14502105 |  | 0.15895 | 0 |  | 4 | 0.00096133 | 954 | 0.053073 | 8251 | 5.102e-05 | 4321
EIGHT MILE 21017406 | EIGHT MILE 2101 | 163912101 |  | 0.011364 | 0 |  | 0.33333 | 0.00096122 | 955 | 0.053073 | 8251 | 5.1014e-05 | 4322
RANCHERS COTTON 110149814 | RANCHERS COTTON 1101 | 254801101 |  | 2.9645 | 1.8272 |  | 50.5 | 0.0009609 | 956 | 0.053243 | 8200 | 5.1014e-05 | 4323
SOLEDAD 2104375878 | SOLEDAD 2104 | 182052104 |  | 1.5005 | 0.68035 |  | 26.1667 | 0.00082395 | 1784 | 0.063186 | 6645 | 5.1008e-05 | 4324
CONTRA COSTA 210375878 | CONTRA COSTA 2103 | 13652103 |  | 0.027907 | 0 |  | 0.5 | 0.00076127 | 2364 | 0.067 | 6057 | 5.1005e-05 | 4325
MONTAGUE 2108CB | MONTAGUE 2108 | 83892108 |  | 0.92681 | 0.4541 |  | 19.5 | 0.00096084 | 957 | 0.053073 | 8251 | 5.0994e-05 | 4326
PENRYN 1105CB | PENRYN 1105 | 152561105 | TRUE | 1.0549 | 0.14163 | 0.094658 | 12.4167 | 0.00076042 | 2377 | 0.067025 | 5994 | 5.0964e-05 | 4327
TIDEWATER 2107M517R | TIDEWATER 2107 | 14652107 |  | 1.1149 | 0.37996 |  | 21.5 | 0.00096014 | 959 | 0.053073 | 8251 | 5.0957e-05 | 4328
SAN CARLOS 1104CB | SAN CARLOS 1104 | 24181104 |  | 2.8899 | 0.9128 |  | 27.1762 | 0.00096004 | 962 | 0.053073 | 8251 | 5.0952e-05 | 4329
RICHMOND R 1126BR278 | RICHMOND R 1126 | 13471126 |  | 0.18415 | 0.14256 |  | 2.1667 | 0.00095968 | 963 | 0.053073 | 8250 | 5.0933e-05 | 4330
JAMESON 1104CB | JAMESON 1104 | 63801104 |  | 0.083536 | 0.032308 |  | 2 | 0.00071206 | 2945 | 0.07151 | 4830 | 5.092e-05 | 4331
STOCKTON A 110612484 | STOCKTON A 1106 | 162371106 |  | 2.1684 | 1.5684 |  | 23.6667 | 0.00095916 | 965 | 0.053073 | 8250 | 5.0905e-05 | 4332
BULLARD 2112R2566 | BULLARD 2112 | 253962112 |  | 3.2233 | 3.1839 |  | 52.3333 | 0.00083412 | 1690 | 0.061759 | 6791 | 5.0903e-05 | 4333
CLAYTON 2216CB | CLAYTON 2216 | 12022216 |  | 11.3376 | 7.3902 |  | 180.8167 | 0.00086212 | 1484 | 0.05823 | 7264 | 5.0892e-05 | 4334
LAKEWOOD 2109CB | LAKEWOOD 2109 | 13532109 |  | 4.6176 | 3.0843 |  | 65.8333 | 0.00085875 | 1506 | 0.059631 | 7064 | 5.0885e-05 | 4335
MISSION (X) 1127CB | MISSION (X) 1127 | 22011127 |  | 0.46792 | 0.35057 |  | 14 | 0.00095875 | 967 | 0.053073 | 8251 | 5.0883e-05 | 4336
COUNTRY CLUB 1103CB | COUNTRY CLUB 1103 | 163121103 |  | 5.965 | 4.4648 |  | 100.5333 | 0.00095799 | 968 | 0.053073 | 8251 | 5.0843e-05 | 4337
BELLEVUE 2101102360 | BELLEVUE 2101 | 43182101 |  | 0.74457 | 0.26393 |  | 11.3333 | 0.00095772 | 971 | 0.053073 | 8251 | 5.0829e-05 | 4338
COTTLE 1707CB | COTTLE 1707 | 163711707 |  | 0.72681 | 0 |  | 7.3333 | 0.00072605 | 2778 | 0.070832 | 4913 | 5.0828e-05 | 4339
CONTRA COSTA 211639010 | CONTRA COSTA 2116 | 13652116 |  | 7.8623 | 2.949 |  | 108.5 | 0.00086922 | 1429 | 0.058233 | 7263 | 5.0824e-05 | 4340
RICHMOND R 1125BR308 | RICHMOND R 1125 | 13471125 |  | 0.59476 | 0.060787 |  | 5.3333 | 0.00095761 | 972 | 0.053073 | 8252 | 5.0823e-05 | 4341
RICHMOND R 1124CB | RICHMOND R 1124 | 13471124 |  | 2.023 | 1.1317 |  | 19.65 | 0.00095745 | 974 | 0.053073 | 8251 | 5.0814e-05 | 4342
CORNING 1102CB | CORNING 1102 | 103331102 |  | 0.74501 | 0.14427 |  | 10.3333 | 0.00075795 | 2408 | 0.067028 | 5988 | 5.0807e-05 | 4343
STOCKTON A 0410CB | STOCKTON A 0410 | 162370410 |  | 6.3097 | 5.7361 |  | 69.6 | 0.00095722 | 975 | 0.053073 | 8252 | 5.0802e-05 | 4344
DIXON LANDING 2101XR012 | DIXON LANDING 2101 | 14722101 |  | 0.98127 | 0.53159 |  | 16.8333 | 0.00095718 | 977 | 0.053073 | 8250 | 5.08e-05 | 4345
PANORAMA 11029762 | PANORAMA 1102 | 103461102 |  | 0.94443 | 0.16071 |  | 14 | 0.00081122 | 1889 | 0.062523 | 6713 | 5.08e-05 | 4346
ASHLAN AVE 111266668 | ASHLAN AVE 1112 | 252051112 |  | 0.57533 | 0.17753 |  | 11.5 | 0.00095699 | 978 | 0.053073 | 8251 | 5.079e-05 | 4347
LAS POSITAS 2108MR190 | LAS POSITAS 2108 | 14402108 | TRUE | 11.1846 | 1.0288 | 0.54044 | 210.3333 | 0.0004571 | 5845 | 0.14986 | 3206 | 5.0782e-05 | 4348
CONTRA COSTA 2116CB | CONTRA COSTA 2116 | 13652116 |  | 14.0869 | 12.8477 |  | 194.5 | 0.00092841 | 1103 | 0.054712 | 7804 | 5.0766e-05 | 4349
ARCATA 11216004 | ARCATA 1121 | 192021121 |  | 3.3451 | 2.6496 |  | 55.5 | 0.00078336 | 2115 | 0.064598 | 6479 | 5.0761e-05 | 4350
SAN JOSE B 1105XR504 | SAN JOSE B 1105 | 82261105 |  | 1.5137 | 1.3983 |  | 26 | 0.00095634 | 980 | 0.053073 | 8251 | 5.0755e-05 | 4351
WEST LANE 110199872 | WEST LANE 1101 | 163621101 |  | 2.6732 | 2.2924 |  | 40.1167 | 0.00095613 | 981 | 0.053073 | 8249 | 5.0744e-05 | 4352
SAN JOSE A 111281630 | SAN JOSE A 1112 | 82251112 |  | 0.86358 | 0.33072 |  | 15.5 | 0.00095612 | 982 | 0.053073 | 8251 | 5.0744e-05 | 4353
MISSION (X) 111678144 | MISSION (X) 1116 | 22011116 |  | 0.06471 | 0 |  | 1.1667 | 0.00095593 | 984 | 0.053073 | 8250 | 5.0734e-05 | 4354
PUEBLO 1104536006 | PUEBLO 1104 | 43291104 |  | 0.75231 | 0.19613 |  | 14.5 | 0.00077286 | 2233 | 0.065591 | 6343 | 5.0727e-05 | 4355
FELLOWS 21041074 | FELLOWS 2104 | 254242104 |  | 0.67483 | 0 |  | 12 | 0.00075685 | 2417 | 0.067 | 6057 | 5.0709e-05 | 4356
LOS OSITOS 2103606732 | LOS OSITOS 2103 | 182082103 |  | 1.0667 | 0.16562 |  | 22.5 | 0.00075665 | 2420 | 0.067 | 6057 | 5.0695e-05 | 4357
OAKLAND D 1101CB | OAKLAND D 1101 | 12041101 |  | 0.16496 | 0.062727 |  | 2 | 0.00095489 | 988 | 0.053073 | 8251 | 5.0678e-05 | 4358
MONTAGUE 2102CB | MONTAGUE 2102 | 83892102 |  | 0.8123 | 0.42527 |  | 10.5 | 0.00095475 | 991 | 0.053073 | 8251 | 5.0671e-05 | 4359
PLAINFIELD 1105CB | PLAINFIELD 1105 | 63441105 |  | 1.2863 | 0.059707 |  | 15.1667 | 0.00065465 | 3645 | 0.0774 | 3396 | 5.0669e-05 | 4360
FAIRVIEW 2208CB | FAIRVIEW 2208 | 13432208 |  | 8.8892 | 6.3242 |  | 135.5 | 0.00088798 | 1314 | 0.057363 | 7381 | 5.0651e-05 | 4361
EDENVALE 2112CB | EDENVALE 2112 | 82952112 |  | 1.3231 | 0.044511 |  | 25.5 | 0.00078479 | 2100 | 0.064397 | 6495 | 5.0648e-05 | 4362
MADERA 1118CB | MADERA 1118 | 252761118 |  | 1.9747 | 0 |  | 24.3333 | 0.00075181 | 2462 | 0.067902 | 5437 | 5.0643e-05 | 4363
CASSIDY 210868818 | CASSIDY 2108 | 254272108 |  | 0.011751 | 0 |  | 1 | 0.00065423 | 3649 | 0.0774 | 3397 | 5.0637e-05 | 4364
VINEYARD 2104CB | VINEYARD 2104 | 14502104 |  | 3.8657 | 0.075129 |  | 55.6667 | 0.00079355 | 2024 | 0.063825 | 6566 | 5.063e-05 | 4365
LAS GALLINAS A 110436840 | LAS GALLINAS A 1104 | 42991104 |  | 0.21712 | 0 |  | 3.1667 | 0.00095396 | 993 | 0.053073 | 8251 | 5.0629e-05 | 4366
BAY MEADOWS 2102CB | BAY MEADOWS 2102 | 24012102 | TRUE | 6.9389 | 5.4813 | 0.12353 | 94.1667 | 0.0008459 | 1605 | 0.060894 | 6902 | 5.0627e-05 | 4367
COUNTRY CLUB 0403CB | COUNTRY CLUB 0403 | 163120403 |  | 2.7036 | 2.2451 |  | 40.3333 | 0.00095285 | 1002 | 0.053073 | 8250 | 5.057e-05 | 4368
ASHLAN AVE 1109CB | ASHLAN AVE 1109 | 252051109 |  | 9.1007 | 7.6224 |  | 109.75 | 0.00091297 | 1174 | 0.056065 | 7571 | 5.0568e-05 | 4369
GREEN VALLEY 2101CB | GREEN VALLEY 2101 | 83192101 |  | 1.6022 | 0 |  | 25.6667 | 0.00075436 | 2442 | 0.067 | 6057 | 5.0542e-05 | 4370
AUBURN 1102CB | AUBURN 1102 | 152161102 |  | 2.2742 | 1.4298 |  | 32.8333 | 0.00082913 | 1743 | 0.062203 | 6744 | 5.0526e-05 | 4371
SF L 1103CB | SF L 1103 | 22261103 |  | 0.12291 | 0 |  | 0.83333 | 0.00095197 | 1004 | 0.053073 | 8250 | 5.0523e-05 | 4372
MERCED 2102CB | MERCED 2102 | 252802102 |  | 0.76072 | 0 |  | 7 | 0.00085218 | 1560 | 0.061591 | 6814 | 5.0508e-05 | 4373
GRASS VALLEY 1102CB | GRASS VALLEY 1102 | 152031102 | TRUE | 5.7929 | 4.2309 | 0.086575 | 91 | 0.00082629 | 1763 | 0.061604 | 6811 | 5.0503e-05 | 4374
STONE 110942894 | STONE 1109 | 83701109 |  | 0.70621 | 0.34694 |  | 14 | 0.00095125 | 1005 | 0.053073 | 8251 | 5.0486e-05 | 4375
SUISUN 1107CB | SUISUN 1107 | 62131107 |  | 1.3214 | 0.85756 |  | 18.3333 | 0.00095123 | 1006 | 0.053073 | 8252 | 5.0484e-05 | 4376
WEEDPATCH 11031672 | WEEDPATCH 1103 | 252971103 |  | 4.1915 | 4.0578 |  | 59.3333 | 0.0008704 | 1419 | 0.058442 | 7228 | 5.0475e-05 | 4377
POTRERO PP (A) 1117548866 | POTRERO PP (A) 1117 | 22031117 |  | 0.03951 | 0 |  | 0.33333 | 0.00095104 | 1007 | 0.053073 | 8251 | 5.0474e-05 | 4378
FELLOWS 21041098 | FELLOWS 2104 | 254242104 |  | 2.0959 | 0 |  | 30.3333 | 0.00074622 | 2532 | 0.067922 | 5429 | 5.0466e-05 | 4379
RICHMOND R 1127BR232 | RICHMOND R 1127 | 13471127 |  | 1.7376 | 1.0752 |  | 15.6667 | 0.00095081 | 1008 | 0.053073 | 8253 | 5.0462e-05 | 4380
EAST GRAND 111012515 | EAST GRAND 1110 | 22571110 |  | 2.0576 | 0.84526 |  | 32.5 | 0.00095073 | 1009 | 0.053073 | 8251 | 5.0458e-05 | 4381
BARTON 1104CB | BARTON 1104 | 253571104 |  | 4.5641 | 3.2278 |  | 66.6667 | 0.00094996 | 1012 | 0.053073 | 8250 | 5.0417e-05 | 4382
RED BLUFF 1102CB | RED BLUFF 1102 | 103541102 |  | 1.48 | 0.9626 |  | 22.4167 | 0.00084154 | 1640 | 0.061697 | 6799 | 5.0413e-05 | 4383
FIGARDEN 210479486 | FIGARDEN 2104 | 254552104 |  | 0.49048 | 0.31864 |  | 8.5 | 0.00094955 | 1014 | 0.053073 | 8251 | 5.0395e-05 | 4384
SARATOGA 1107CB | SARATOGA 1107 | 83371107 | TRUE | 9.8003 | 7.6674 | 0.2685 | 159.6667 | 0.00078927 | 2066 | 0.063274 | 6632 | 5.0377e-05 | 4385
RAWSON 11039052 | RAWSON 1103 | 103531103 |  | 2.3829 | 1.207 |  | 42 | 0.00086961 | 1424 | 0.057928 | 7305 | 5.0377e-05 | 4386
SNEATH LANE 11061339 | SNEATH LANE 1106 | 22721106 |  | 5.2201 | 5.5147 |  | 73.3333 | 0.0007627 | 2345 | 0.066335 | 6214 | 5.0351e-05 | 4387
DAVIS 110521162 | DAVIS 1105 | 62041105 |  | 0.015625 | 0 |  | 0.83333 | 0.00094836 | 1015 | 0.053073 | 8250 | 5.0332e-05 | 4388
COLUMBUS 1103CB | COLUMBUS 1103 | 253951103 |  | 7.5003 | 6.0681 |  | 101.0833 | 0.0009482 | 1016 | 0.053073 | 8252 | 5.0323e-05 | 4389
VINEYARD 2105MR270 | VINEYARD 2105 | 14502105 |  | 0.51091 | 0.14737 |  | 10.5 | 0.0008672 | 1441 | 0.059058 | 7149 | 5.0315e-05 | 4390
STELLING 1102CB | STELLING 1102 | 83481102 |  | 0.69216 | 0 |  | 8.8333 | 0.00094796 | 1018 | 0.053073 | 8250 | 5.0311e-05 | 4391
OAKLAND L 1101568018 | OAKLAND L 1101 | 12111101 |  | 2.6175 | 2.1614 |  | 33.5 | 0.00094791 | 1019 | 0.053073 | 8251 | 5.0308e-05 | 4392
MERCED 210259150 | MERCED 2102 | 252802102 |  | 4.1308 | 2.9664 |  | 72.8333 | 0.00090268 | 1219 | 0.056246 | 7542 | 5.0271e-05 | 4393
OAKLAND J 1116CR328 | OAKLAND J 1116 | 12091116 | FALSE | 4.9194 | 5.6382 | 1.0085 | 75.5 | 0.00055876 | 4765 | 0.10548 | 3304 | 5.0267e-05 | 4394
CARBONA 1104569492 | CARBONA 1104 | 163091104 |  | 0.010711 | 0 |  | 0.5 | 0.00075019 | 2477 | 0.067 | 6057 | 5.0262e-05 | 4395
MILPITAS 2110CB | MILPITAS 2110 | 82832110 |  | 2.2591 | 2.075 |  | 36.5 | 0.00094682 | 1022 | 0.053073 | 8251 | 5.025e-05 | 4396
WEBER 1107CB | WEBER 1107 | 163481107 |  | 0.035205 | 0 |  | 2.5 | 0.00094647 | 1023 | 0.053073 | 8251 | 5.0232e-05 | 4397
EAST GRAND 1107131 | EAST GRAND 1107 | 22571107 |  | 0.85511 | 0.41055 |  | 10.25 | 0.00094612 | 1028 | 0.053073 | 8251 | 5.0213e-05 | 4398
SNEATH LANE 110748338 | SNEATH LANE 1107 | 22721107 | TRUE | 1.1061 | 0.21665 | 0.089785 | 17.3333 | 0.00079652 | 1999 | 0.06272 | 6688 | 5.0174e-05 | 4399
WEST FRESNO 1109CB | WEST FRESNO 1109 | 253731109 |  | 11.4057 | 8.5022 |  | 173.9167 | 0.00094522 | 1029 | 0.053073 | 8252 | 5.0165e-05 | 4400
SF L 110182980 | SF L 1101 | 22261101 |  | 0.30687 | 0.083417 |  | 2.7 | 0.00094491 | 1030 | 0.053073 | 8251 | 5.0149e-05 | 4401
MALAGA 1109CB | MALAGA 1109 | 254251109 |  | 3.0201 | 0.94161 |  | 50.1667 | 0.00075455 | 2440 | 0.067721 | 5505 | 5.0131e-05 | 4402
STAGG 2108CB | STAGG 2108 | 162422108 |  | 2.1834 | 2.6858 |  | 30.8333 | 0.00094442 | 1032 | 0.053073 | 8251 | 5.0123e-05 | 4403
OAKLAND C 1115CB | OAKLAND C 1115 | 12011115 |  | 1.108 | 0.41345 |  | 13.7833 | 0.00094422 | 1033 | 0.053073 | 8252 | 5.0112e-05 | 4404
PIERCY 2110XR260 | PIERCY 2110 | 83912110 |  | 0.89319 | 0.13347 |  | 16.5 | 0.00075337 | 2450 | 0.066578 | 6175 | 5.0112e-05 | 4405
POTRERO PP (A) 11103415 | POTRERO PP (A) 1110 | 22031110 |  | 1.8915 | 2.2515 |  | 24 | 0.00094414 | 1034 | 0.053073 | 8249 | 5.0108e-05 | 4406
RICHMOND R 1126CB | RICHMOND R 1126 | 13471126 |  | 2.412 | 1.0164 |  | 20.9833 | 0.00094381 | 1036 | 0.053073 | 8249 | 5.009e-05 | 4407
SAN RAFAEL 1110CB | SAN RAFAEL 1110 | 42011110 |  | 0.0028409 | 0 |  | 0.5 | 0.00094358 | 1037 | 0.053073 | 8251 | 5.0078e-05 | 4408
HUNTERS POINT (P) 110276684 | HUNTERS POINT (P) 1102 | 22331102 |  | 2.4391 | 1.7493 |  | 37.8333 | 0.00094309 | 1039 | 0.053073 | 8251 | 5.0052e-05 | 4409
BARTON 1116CB | BARTON 1116 | 253571116 |  | 5.0892 | 4.7581 |  | 73.75 | 0.00094308 | 1040 | 0.053073 | 8251 | 5.0052e-05 | 4410
SANTA ROSA A 1112CB | SANTA ROSA A 1112 | 42151112 |  | 0.56694 | 0.3462 |  | 9.8333 | 0.00094304 | 1041 | 0.053073 | 8251 | 5.005e-05 | 4411
OAKLAND D 1106CR390 | OAKLAND D 1106 | 12041106 |  | 6.109 | 5.9241 |  | 74.6667 | 0.000943 | 1042 | 0.053073 | 8250 | 5.0048e-05 | 4412
SARATOGA 1104CB | SARATOGA 1104 | 83371104 |  | 5.3891 | 4.5035 |  | 101.5 | 0.00079278 | 2035 | 0.06326 | 6635 | 5.0046e-05 | 4413
HICKS 2102XR384 | HICKS 2102 | 83432102 |  | 0.0095089 | 0 |  | 1 | 0.00094235 | 1044 | 0.053073 | 8251 | 5.0013e-05 | 4414
JAMESON 11057792 | JAMESON 1105 | 63801105 |  | 0.023418 | 0 |  | 1.5 | 0.00074572 | 2537 | 0.067058 | 5938 | 5.0008e-05 | 4415
WEST FRESNO 110493599 | WEST FRESNO 1104 | 253731104 |  | 3.497 | 3.1603 |  | 58.1667 | 0.00094104 | 1047 | 0.053221 | 8209 | 5.0003e-05 | 4416
BELLEVUE 2105CB | BELLEVUE 2105 | 43182105 |  | 1.2275 | 0.036044 |  | 20 | 0.00083105 | 1723 | 0.061082 | 6884 | 5.0002e-05 | 4417
OLEMA 1101320 | OLEMA 1101 | 42291101 |  | 7.8716 | 1.6112 |  | 145.5 | 0.0004493 | 5925 | 0.10005 | 3313 | 5e-05 | 4418
FIGARDEN 2105CB | FIGARDEN 2105 | 254552105 |  | 4.7343 | 0.64477 |  | 64.8333 | 0.00093888 | 1054 | 0.053537 | 8090 | 4.9959e-05 | 4419
SAN MATEO 21029022 | SAN MATEO 2102 | 24192102 |  | 2.7215 | 2.2967 |  | 44.6667 | 0.00092857 | 1101 | 0.053696 | 8031 | 4.9958e-05 | 4420
SAN JOSE B 1116CB | SAN JOSE B 1116 | 82261116 |  | 5.0215 | 3.5933 |  | 78.3333 | 0.00094131 | 1046 | 0.053073 | 8251 | 4.9958e-05 | 4421
AIRWAYS 1103CB | AIRWAYS 1103 | 252041103 |  | 4.0972 | 0.3735 |  | 69.3333 | 0.00070073 | 3086 | 0.072475 | 4719 | 4.9946e-05 | 4422
BELL 110950506 | BELL 1109 | 152701109 |  | 0.14389 | 0 |  | 1.5 | 0.00074521 | 2545 | 0.067012 | 6021 | 4.994e-05 | 4423
BAYWOOD 1101CB | BAYWOOD 1101 | 182801101 | FALSE | 28.6478 | 1.1604 | 3.5291 | 578 | 0.00021355 | 9808 | 0.31492 | 3000 | 4.9887e-05 | 4424
VACAVILLE 1106CB | VACAVILLE 1106 | 63601106 |  | 1.7558 | 0.10526 |  | 28 | 0.0009399 | 1050 | 0.053073 | 8251 | 4.9883e-05 | 4425
SF N 11023431 | SF N 1102 | 22281102 |  | 1.0165 | 1.3467 |  | 15.3333 | 0.00093968 | 1052 | 0.053073 | 8251 | 4.9871e-05 | 4426
RENFRO 2107361292 | RENFRO 2107 | 254572107 |  | 0.86563 | 0.010903 |  | 12 | 0.00078175 | 2133 | 0.064284 | 6510 | 4.9869e-05 | 4427
7TH STANDARD 2101CB | 7TH STANDARD 2101 | 254582101 |  | 2.5627 | 0 |  | 22.5833 | 0.00075958 | 2393 | 0.069237 | 5158 | 4.9823e-05 | 4428
VIERRA 1706CB | VIERRA 1706 | 162701706 |  | 1.3905 | 0.27993 |  | 26 | 0.00093871 | 1055 | 0.053073 | 8251 | 4.982e-05 | 4429
DEL MONTE 11012108 | DEL MONTE 1101 | 182221101 |  | 0.18596 | 0.13628 |  | 3 | 0.00093867 | 1056 | 0.053073 | 8251 | 4.9818e-05 | 4430
ASHLAN AVE 111199204 | ASHLAN AVE 1111 | 252051111 |  | 2.0741 | 1.6836 |  | 29 | 0.0009386 | 1057 | 0.053073 | 8251 | 4.9814e-05 | 4431
EMBARCADERO (Z) 1112CB | EMBARCADERO (Z) 1112 | 22871112 |  | 0.0014205 | 0 |  | 0.33333 | 0.00093848 | 1058 | 0.053073 | 8251 | 4.9808e-05 | 4432
MEADOW LANE 2108CB | MEADOW LANE 2108 | 14302108 |  | 5.8812 | 5.7021 |  | 93 | 0.00089568 | 1263 | 0.055743 | 7630 | 4.9807e-05 | 4433
LOS GATOS 1102CB | LOS GATOS 1102 | 82021102 |  | 4.6785 | 2.9832 |  | 81.5 | 0.0008287 | 1747 | 0.060485 | 6961 | 4.9738e-05 | 4434
OAKLAND J 1114CB | OAKLAND J 1114 | 12091114 |  | 0.0024624 | 0 |  | 0.5 | 0.00093715 | 1062 | 0.053073 | 8251 | 4.9737e-05 | 4435
OAKLAND D 1115CB | OAKLAND D 1115 | 12041115 |  | 2.7178 | 2.5814 |  | 38 | 0.00093697 | 1063 | 0.053073 | 8250 | 4.9728e-05 | 4436
HARTER 1102CB | HARTER 1102 | 152851102 |  | 4.3857 | 0.60369 |  | 64.1167 | 0.00085519 | 1537 | 0.059333 | 7108 | 4.9697e-05 | 4437
ASHLAN AVE 111454300 | ASHLAN AVE 1114 | 252051114 |  | 2.0385 | 2.2113 |  | 28.4167 | 0.00093616 | 1067 | 0.053073 | 8250 | 4.9685e-05 | 4438
WEST SACRAMENTO 1104CB | WEST SACRAMENTO 1104 | 63131104 |  | 4.9201 | 0.36872 |  | 91 | 0.00089384 | 1273 | 0.056729 | 7475 | 4.9674e-05 | 4439
VIEJO 220486890 | VIEJO 2204 | 182852204 |  | 2.2031 | 2.066 |  | 31.5 | 0.00087405 | 1396 | 0.056811 | 7465 | 4.9666e-05 | 4440
PUEBLO 11031751 | PUEBLO 1103 | 43291103 |  | 1.9169 | 1.8587 |  | 27 | 0.00093558 | 1072 | 0.053073 | 8251 | 4.9654e-05 | 4441
EAST GRAND 1110CB | EAST GRAND 1110 | 22571110 |  | 1.3632 | 0.80247 |  | 22.25 | 0.0009354 | 1073 | 0.053073 | 8251 | 4.9644e-05 | 4442
BAY MEADOWS 21029062 | BAY MEADOWS 2102 | 24012102 |  | 0.63958 | 0.32398 |  | 14.8333 | 0.00074484 | 2551 | 0.066687 | 6141 | 4.9632e-05 | 4443
MILLBRAE 1106CB | MILLBRAE 1106 | 22691106 |  | 3.7506 | 1.7872 |  | 66.2833 | 0.00084787 | 1590 | 0.05817 | 7271 | 4.9627e-05 | 4444
WEST LANE 1103D1057 | WEST LANE 1103 | 163621103 |  | 0.25622 | 0.019048 |  | 3.5 | 0.00093492 | 1074 | 0.053073 | 8251 | 4.9619e-05 | 4445
WHISMAN 1107CB | WHISMAN 1107 | 83631107 |  | 0.12876 | 0 |  | 0.83333 | 0.00093479 | 1075 | 0.053073 | 8250 | 4.9612e-05 | 4446
SAUSALITO 1102678 | SAUSALITO 1102 | 42491102 |  | 3.4636 | 2.5289 |  | 48.8333 | 0.00079663 | 1998 | 0.061698 | 6798 | 4.9607e-05 | 4447
SAN JOSE B 1108CB | SAN JOSE B 1108 | 82261108 |  | 2.0596 | 1.8226 |  | 35.5 | 0.00093465 | 1076 | 0.053073 | 8251 | 4.9604e-05 | 4448
NOTRE DAME 11022038 | NOTRE DAME 1102 | 102041102 |  | 0.88367 | 0.31619 |  | 17 | 0.000924 | 1126 | 0.053892 | 7978 | 4.959e-05 | 4449
HARTER 110790768 | HARTER 1107 | 152851107 |  | 0.91774 | 0.56459 |  | 9.3333 | 0.0009341 | 1077 | 0.053073 | 8250 | 4.9575e-05 | 4450
EIGHT MILE 2102CB | EIGHT MILE 2102 | 163912102 |  | 2.5163 | 0.056363 |  | 46.5 | 0.00069001 | 3217 | 0.07257 | 4713 | 4.9575e-05 | 4451
ERTA 0403CB | ERTA 0403 | 83510403 |  | 2.9768 | 1.5756 |  | 32.3333 | 0.0008921 | 1282 | 0.055585 | 7662 | 4.9573e-05 | 4452
SAN JOSE B 1114CB | SAN JOSE B 1114 | 82261114 |  | 0.68322 | 0.51237 |  | 12.5 | 0.00093358 | 1080 | 0.053073 | 8251 | 4.9548e-05 | 4453
STOCKDALE 21094718 | STOCKDALE 2109 | 254072109 |  | 2.6929 | 0.17884 |  | 48.3333 | 0.00083029 | 1731 | 0.061304 | 6854 | 4.9544e-05 | 4454
WINDSOR 1102CB | WINDSOR 1102 | 43501102 |  | 2.8543 | 0.17801 |  | 43.8333 | 0.00079173 | 2047 | 0.061916 | 6772 | 4.9542e-05 | 4455
SAN JOSE B 1106CB | SAN JOSE B 1106 | 82261106 |  | 0.69966 | 0.40083 |  | 19.5 | 0.00093302 | 1082 | 0.053073 | 8251 | 4.9518e-05 | 4456
7TH STANDARD 2104CB | 7TH STANDARD 2104 | 254582104 |  | 0.039986 | 0 |  | 0.25 | 0.00063964 | 3829 | 0.0774 | 3397 | 4.9508e-05 | 4457
OAKLAND L 1107CB | OAKLAND L 1107 | 12111107 |  | 1.4615 | 1.5475 |  | 20.0833 | 0.00093282 | 1083 | 0.053073 | 8251 | 4.9507e-05 | 4458
BAKERSFIELD 21043326 | BAKERSFIELD 2104 | 253372104 |  | 16.7375 | 16.1716 |  | 266.5 | 0.00093275 | 1084 | 0.053073 | 8251 | 4.9503e-05 | 4459
EAST STOCKTON 0401CB | EAST STOCKTON 0401 | 163130401 |  | 8.342 | 9.2723 |  | 106.4167 | 0.00093268 | 1085 | 0.053073 | 8249 | 4.95e-05 | 4460
PUEBLO 1105115766 | PUEBLO 1105 | 43291105 |  | 2.6503 | 0 |  | 44.1667 | 0.00073858 | 2622 | 0.067004 | 6033 | 4.9489e-05 | 4461
OAKLAND D 1111CB | OAKLAND D 1111 | 12041111 |  | 6.8378 | 5.9969 |  | 86.25 | 0.00093228 | 1086 | 0.053073 | 8250 | 4.9479e-05 | 4462
PLEASANT GROVE 2108CB | PLEASANT GROVE 2108 | 152442108 |  | 2.0977 | 0 |  | 24 | 0.00073848 | 2624 | 0.067 | 6057 | 4.9478e-05 | 4463
BURLINGAME 2101A82 | BURLINGAME 2101 | 24052101 |  | 2.0689 | 1.9336 |  | 29.5833 | 0.00077143 | 2246 | 0.064043 | 6535 | 4.947e-05 | 4464
WEST SACRAMENTO 111022422 | WEST SACRAMENTO 1110 | 63131110 |  | 0.99234 | 0.44676 |  | 17.5 | 0.0009318 | 1088 | 0.053073 | 8251 | 4.9453e-05 | 4465
GREEN VALLEY 210410266 | GREEN VALLEY 2104 | 83192104 |  | 3.8761 | 2.8133 |  | 64.5 | 0.00092862 | 1100 | 0.053935 | 7972 | 4.945e-05 | 4466
WESTPARK 110849640 | WESTPARK 1108 | 253701108 |  | 6.4087 | 6.2916 |  | 85 | 0.00093164 | 1089 | 0.053073 | 8251 | 4.9445e-05 | 4467
EDES 1103648284 | EDES 1103 | 13681103 |  | 0.30372 | 0.25306 |  | 5.8333 | 0.00093109 | 1091 | 0.053073 | 8251 | 4.9416e-05 | 4468
TIDEWATER 210749626 | TIDEWATER 2107 | 14652107 |  | 6.7876 | 4.2236 |  | 111.8333 | 0.00082517 | 1775 | 0.0608 | 6913 | 4.9415e-05 | 4469
SONOMA 1102118 | SONOMA 1102 | 42721102 |  | 0.22965 | 0.16658 |  | 3.8333 | 0.00093092 | 1092 | 0.053073 | 8251 | 4.9406e-05 | 4470
KERN OIL 1103CB | KERN OIL 1103 | 252721103 |  | 5.1221 | 4.3262 |  | 71.5 | 0.0009308 | 1093 | 0.053073 | 8251 | 4.94e-05 | 4471
PLACER 110451732 | PLACER 1104 | 152461104 | TRUE | 6.4946 | 1.973 | 0.59488 | 107 | 0.00074429 | 2564 | 0.06655 | 6179 | 4.9395e-05 | 4472
SYCAMORE CREEK 1105CB | SYCAMORE CREEK 1105 | 102971105 |  | 8.5247 | 6.8123 |  | 126 | 0.00088995 | 1298 | 0.055762 | 7628 | 4.9392e-05 | 4473
COTTLE 1707496160 | COTTLE 1707 | 163711707 |  | 0.81836 | 0.040053 |  | 13 | 0.00079179 | 2046 | 0.061494 | 6832 | 4.9369e-05 | 4474
ROUGH AND READY ISLA 1102CB | ROUGH AND READY ISLA 1102 | 163081102 |  | 6.9483 | 1.1105 |  | 119 | 0.00090682 | 1202 | 0.05439 | 7866 | 4.9357e-05 | 4475
ASHLAN AVE 111277320 | ASHLAN AVE 1112 | 252051112 |  | 1.0735 | 1.1284 |  | 14.3333 | 0.00092977 | 1098 | 0.053073 | 8251 | 4.9346e-05 | 4476
VALLEY VIEW 1106P180 | VALLEY VIEW 1106 | 14341106 |  | 2.1361 | 1.9386 |  | 36.5 | 0.00062169 | 4029 | 0.089564 | 3345 | 4.9337e-05 | 4477
EL CAPITAN 1102CB | EL CAPITAN 1102 | 253881102 |  | 3.4319 | 0.15937 |  | 42.7833 | 0.00072832 | 2746 | 0.068681 | 5244 | 4.9331e-05 | 4478
KERN OIL 1109CB | KERN OIL 1109 | 252721109 |  | 11.3325 | 8.9638 |  | 169 | 0.00090809 | 1195 | 0.054834 | 7786 | 4.9299e-05 | 4479
PETALUMA C 1109CB | PETALUMA C 1109 | 42631109 |  | 2.8856 | 2.4272 |  | 42.8333 | 0.00089635 | 1258 | 0.055465 | 7675 | 4.9285e-05 | 4480
STELLING 1105CB | STELLING 1105 | 83481105 |  | 0.40055 | 0.018941 |  | 6.3333 | 0.00092857 | 1102 | 0.053073 | 8252 | 4.9282e-05 | 4481
ASHLAN AVE 210572920 | ASHLAN AVE 2105 | 252052105 |  | 8.9208 | 4.9563 |  | 149.1667 | 0.0009284 | 1104 | 0.053073 | 8251 | 4.9273e-05 | 4482
CAROLANDS 040197209 | CAROLANDS 0401 | 24060401 |  | 0.27435 | 0.064602 |  | 3 | 0.00075119 | 2469 | 0.065732 | 6318 | 4.9266e-05 | 4483
BUENA VISTA 1104810866 | BUENA VISTA 1104 | 182261104 |  | 0.016565 | 0 |  | 0.5 | 0.00092808 | 1107 | 0.053073 | 8251 | 4.9256e-05 | 4484
BELMONT 1104CB | BELMONT 1104 | 24031104 |  | 0.46592 | 0.10681 |  | 7.5833 | 0.00092807 | 1108 | 0.053073 | 8252 | 4.9255e-05 | 4485
RICHMOND R 1127BR216 | RICHMOND R 1127 | 13471127 |  | 0.31561 | 0 |  | 4.5 | 0.00071892 | 2863 | 0.069291 | 5147 | 4.925e-05 | 4486
MISSION (X) 110877660 | MISSION (X) 1108 | 22011108 |  | 0.50852 | 0.52423 |  | 5.0667 | 0.0008909 | 1287 | 0.055473 | 7674 | 4.9243e-05 | 4487
BAHIA 110243940 | BAHIA 1102 | 43251102 |  | 1.6678 | 0.43151 |  | 31 | 0.00092771 | 1111 | 0.053073 | 8251 | 4.9236e-05 | 4488
STOCKDALE 11054502 | STOCKDALE 1105 | 254071105 |  | 2.8573 | 0.20128 |  | 40.8333 | 0.00089024 | 1293 | 0.055456 | 7678 | 4.9229e-05 | 4489
OAKLAND J 1111CB | OAKLAND J 1111 | 12091111 |  | 1.4385 | 1.0724 |  | 21.25 | 0.00092749 | 1112 | 0.053073 | 8251 | 4.9224e-05 | 4490
REEDLEY 1104887932 | REEDLEY 1104 | 252341104 | FALSE | 4.8654 | 0.38078 | 1.6881 | 94.5 | 0.00015962 | 10603 | 0.46921 | 2851 | 4.9219e-05 | 4491
SWIFT 2108CB | SWIFT 2108 | 83392108 |  | 1.0382 | 0.66481 |  | 20.5 | 0.00092721 | 1113 | 0.053073 | 8251 | 4.9209e-05 | 4492
GILL 0402CB | GILL 0402 | 13550402 |  | 3.9179 | 3.0478 |  | 45.4167 | 0.0009105 | 1183 | 0.054333 | 7884 | 4.9207e-05 | 4493
OAKLAND C 1110CB | OAKLAND C 1110 | 12011110 |  | 1.2472 | 0.55526 |  | 21.75 | 0.0009268 | 1115 | 0.053073 | 8251 | 4.9188e-05 | 4494
LONE TREE 2102405024 | LONE TREE 2102 | 13232102 |  | 0.451 | 0.30295 |  | 8.5 | 0.00076005 | 2384 | 0.065386 | 6381 | 4.9182e-05 | 4495
CONTRA COSTA 2104CB | CONTRA COSTA 2104 | 13652104 |  | 9.1758 | 7.4584 |  | 114.5667 | 0.00091937 | 1151 | 0.053405 | 8132 | 4.9168e-05 | 4496
WAHTOKE 11093010 | WAHTOKE 1109 | 254531109 |  | 0.020833 | 0 |  | 0.5 | 0.00092639 | 1116 | 0.053073 | 8251 | 4.9166e-05 | 4497
EDES 1114CR318 | EDES 1114 | 13681114 |  | 1.5706 | 1.1966 |  | 24.1667 | 0.00092581 | 1118 | 0.053073 | 8251 | 4.9135e-05 | 4498
EL CERRITO G 1112649732 | EL CERRITO G 1112 | 12501112 | TRUE | 6.6457 | 6.7252 | 0.020012 | 107.6667 | 0.0005417 | 4938 | 0.089164 | 3347 | 4.9128e-05 | 4499
BASALT 1101CB | BASALT 1101 | 42461101 |  | 1.6643 | 0.189 |  | 17.25 | 0.00074117 | 2590 | 0.066592 | 6170 | 4.9123e-05 | 4500
LAS POSITAS 210572161 | LAS POSITAS 2105 | 14402105 |  | 0.016838 | 0 |  | 0.5 | 0.00092525 | 1119 | 0.053073 | 8251 | 4.9106e-05 | 4501
ECHO SUMMIT 1101927812 | ECHO SUMMIT 1101 | 158031101 |  | 0.38515 | 0.055646 |  | 4.5 | 0.0007288 | 2743 | 0.067396 | 5670 | 4.9101e-05 | 4502
CALIFORNIA AVE 1114653348 | CALIFORNIA AVE 1114 | 252281114 |  | 3.2435 | 2.5606 |  | 47.5 | 0.00092515 | 1120 | 0.053073 | 8252 | 4.91e-05 | 4503
SANTA ROSA A 1101138498 | SANTA ROSA A 1101 | 42151101 |  | 2.1259 | 2.2396 |  | 30 | 0.00092497 | 1121 | 0.053073 | 8251 | 4.9091e-05 | 4504
WATSONVILLE 0414CB | WATSONVILLE 0414 | 83330414 |  | 1.222 | 0.84256 |  | 11.4167 | 0.00080461 | 1940 | 0.061002 | 6891 | 4.909e-05 | 4505
OAKLAND C 1114CB | OAKLAND C 1114 | 12011114 |  | 0.84614 | 0.32294 |  | 8.7833 | 0.00092491 | 1122 | 0.053073 | 8252 | 4.9087e-05 | 4506
MALAGA 1107CB | MALAGA 1107 | 254251107 |  | 2.6619 | 0.67038 |  | 37 | 0.00086294 | 1473 | 0.058442 | 7227 | 4.9086e-05 | 4507
CARQUINEZ 1104CB | CARQUINEZ 1104 | 43281104 |  | 0.38068 | 0.16446 |  | 8 | 0.00092453 | 1124 | 0.053073 | 8251 | 4.9067e-05 | 4508
OAKLAND D 1132CB | OAKLAND D 1132 | 12041132 |  | 2.8798 | 2.4425 |  | 41.75 | 0.00092443 | 1125 | 0.053073 | 8251 | 4.9062e-05 | 4509
NEWARK 21KV 2103CB | NEWARK 21KV 2103 | 12232103 |  | 4.271 | 0.4487 |  | 70.9167 | 0.00076819 | 2281 | 0.065422 | 6373 | 4.9061e-05 | 4510
FORT ORD 2105CB | FORT ORD 2105 | 182402105 |  | 3.506 | 0.17849 |  | 54.8333 | 0.00080946 | 1903 | 0.06065 | 6939 | 4.905e-05 | 4511
VIEJO 22022179 | VIEJO 2202 | 182852202 |  | 2.0664 | 1.1943 |  | 28.6667 | 0.00075509 | 2434 | 0.064814 | 6461 | 4.9035e-05 | 4512
PAUL SWEET 2103811390 | PAUL SWEET 2103 | 83252103 |  | 2.2939 | 1.5238 |  | 28.5 | 0.00089287 | 1280 | 0.055819 | 7611 | 4.9031e-05 | 4513
WEEDPATCH 11031670 | WEEDPATCH 1103 | 252971103 |  | 4.7196 | 2.4342 |  | 67.8333 | 0.00077706 | 2184 | 0.063558 | 6604 | 4.9007e-05 | 4514
AIRWAYS 1108CB | AIRWAYS 1108 | 252041108 |  | 3.2353 | 1.9391 |  | 55 | 0.00092338 | 1128 | 0.053073 | 8251 | 4.9006e-05 | 4515
POTRERO PP (A) 1118CB | POTRERO PP (A) 1118 | 22031118 |  | 4.2677 | 1.9612 |  | 44.5762 | 0.00092332 | 1129 | 0.053073 | 8250 | 4.9003e-05 | 4516
ASHLAN AVE 1106965866 | ASHLAN AVE 1106 | 252051106 |  | 2.5928 | 0.70589 |  | 38.8333 | 0.00092329 | 1130 | 0.053073 | 8251 | 4.9002e-05 | 4517
STOCKTON A 110814362 | STOCKTON A 1108 | 162371108 |  | 3.1018 | 3.8687 |  | 56.6667 | 0.00092329 | 1131 | 0.053073 | 8252 | 4.9002e-05 | 4518
NOTRE DAME 1102CB | NOTRE DAME 1102 | 102041102 |  | 2.1747 | 0.6619 |  | 39.5 | 0.00077727 | 2182 | 0.063909 | 6556 | 4.8978e-05 | 4519
RIVERBANK 171438382 | RIVERBANK 1714 | 163191714 |  | 0.43479 | 0.27925 |  | 5.8333 | 0.00092283 | 1132 | 0.053073 | 8251 | 4.8977e-05 | 4520
FRUITVALE 2108CB | FRUITVALE 2108 | 253392108 |  | 9.1147 | 0.40002 |  | 114.1167 | 0.00083215 | 1711 | 0.060526 | 6955 | 4.8971e-05 | 4521
KERN POWER 2102CB | KERN POWER 2102 | 255262102 |  | 4.3256 | 0.0056937 |  | 58.4 | 0.00069212 | 3189 | 0.072096 | 4768 | 4.8962e-05 | 4522
SAN JOSE A 1110XR338 | SAN JOSE A 1110 | 82251110 |  | 0.21086 | 0.26623 |  | 4 | 0.00092246 | 1134 | 0.053073 | 8251 | 4.8958e-05 | 4523
FIGARDEN 2105R2050 | FIGARDEN 2105 | 254552105 |  | 2.9057 | 0.96779 |  | 44.8333 | 0.00092245 | 1135 | 0.053073 | 8251 | 4.8957e-05 | 4524
MOUNTAIN VIEW 111360130 | MOUNTAIN VIEW 1113 | 82031113 |  | 1.6232 | 0.78275 |  | 28.8333 | 0.00081089 | 1890 | 0.060238 | 6992 | 4.894e-05 | 4525
FIGARDEN 210438288 | FIGARDEN 2104 | 254552104 |  | 0.33421 | 0.23703 |  | 10 | 0.00092187 | 1139 | 0.053073 | 8251 | 4.8926e-05 | 4526
COUNTRY CLUB 1101CB | COUNTRY CLUB 1101 | 163121101 |  | 7.1717 | 6.3105 |  | 104.3667 | 0.00092183 | 1140 | 0.053073 | 8250 | 4.8924e-05 | 4527
POTRERO PP (A) 1102CB | POTRERO PP (A) 1102 | 22031102 |  | 0.47932 | 0.16813 |  | 6.8333 | 0.00092131 | 1142 | 0.053073 | 8251 | 4.8897e-05 | 4528
MONROE 110694986 | MONROE 1106 | 43301106 |  | 1.4316 | 0.45878 |  | 20.3333 | 0.00092099 | 1143 | 0.053073 | 8252 | 4.8879e-05 | 4529
SHINGLE SPRINGS 210511172 | SHINGLE SPRINGS 2105 | 153652105 | FALSE | 2.4792 | 0.27887 | 2.2306 | 42.5 | 0.00075686 | 2416 | 0.064215 | 6517 | 4.8877e-05 | 4530
POTRERO PP (A) 11015207 | POTRERO PP (A) 1101 | 22031101 |  | 1.4932 | 1.8179 |  | 21.3333 | 0.00092081 | 1144 | 0.053073 | 8252 | 4.887e-05 | 4531
BELLE HAVEN 1105CB | BELLE HAVEN 1105 | 24021105 |  | 0.83172 | 0.3501 |  | 9.45 | 0.00092075 | 1145 | 0.053073 | 8251 | 4.8867e-05 | 4532
HUNTERS POINT (P) 11016675 | HUNTERS POINT (P) 1101 | 22331101 |  | 1.7597 | 1.8391 |  | 20.6667 | 0.00092034 | 1147 | 0.053073 | 8250 | 4.8845e-05 | 4533
OAKLAND C 1134CB | OAKLAND C 1134 | 12011134 |  | 1.4026 | 0.82257 |  | 20.8333 | 0.00091995 | 1149 | 0.053073 | 8251 | 4.8824e-05 | 4534
MORGAN HILL 2110CB | MORGAN HILL 2110 | 83242110 |  | 3.1278 | 2.2796 |  | 61.1667 | 0.0007684 | 2279 | 0.06369 | 6582 | 4.8819e-05 | 4535
HOLLISTER 2106CB | HOLLISTER 2106 | 182492106 |  | 4.263 | 4.4205 |  | 77.1667 | 0.00086035 | 1494 | 0.056787 | 7467 | 4.8814e-05 | 4536
SAN LEANDRO U 1115CB | SAN LEANDRO U 1115 | 13111115 |  | 1.4687 | 0.4897 |  | 19 | 0.0009195 | 1150 | 0.053073 | 8251 | 4.88e-05 | 4537
COUNTRY CLUB 110314257 | COUNTRY CLUB 1103 | 163121103 |  | 0.24634 | 0.078285 |  | 5 | 0.00091933 | 1152 | 0.053073 | 8251 | 4.8791e-05 | 4538
WATSONVILLE 0413CB | WATSONVILLE 0413 | 83330413 |  | 1.104 | 0.36849 |  | 12.1667 | 0.00091928 | 1153 | 0.053073 | 8251 | 4.8789e-05 | 4539
BARTON 110449296 | BARTON 1104 | 253571104 |  | 1.8923 | 1.2106 |  | 25.5 | 0.00091908 | 1154 | 0.053073 | 8251 | 4.8778e-05 | 4540
OAKLAND X 0402CB | OAKLAND X 0402 | 12540402 |  | 0.47594 | 0.30749 |  | 3 | 0.00072799 | 2752 | 0.067 | 6057 | 4.8775e-05 | 4541
MANTECA 1705CB | MANTECA 1705 | 162611705 |  | 5.2123 | 2.9693 |  | 80.3333 | 0.00089608 | 1260 | 0.054845 | 7783 | 4.875e-05 | 4542
FMC 1109CB | FMC 1109 | 83871109 |  | 1.0166 | 0.61006 |  | 15.9167 | 0.00091839 | 1157 | 0.053073 | 8251 | 4.8741e-05 | 4543
CONTRA COSTA 2116A548R | CONTRA COSTA 2116 | 13652116 |  | 1.1957 | 1.0621 |  | 18.6667 | 0.0009183 | 1158 | 0.053073 | 8251 | 4.8737e-05 | 4544
BAKERSFIELD 21044770 | BAKERSFIELD 2104 | 253372104 |  | 6.5487 | 2.2198 |  | 106.5 | 0.00087284 | 1403 | 0.056922 | 7446 | 4.8732e-05 | 4545
WILLOW PASS 2108CB | WILLOW PASS 2108 | 13912108 | TRUE | 11.1676 | 1.8245 | 0.23271 | 167.3333 | 0.00055423 | 4825 | 0.1502 | 3203 | 4.8713e-05 | 4546
SAN MATEO 2102CB | SAN MATEO 2102 | 24192102 |  | 2.1806 | 1.5315 |  | 32.5 | 0.0008782 | 1375 | 0.055232 | 7714 | 4.8707e-05 | 4547
MALAGA 110455328 | MALAGA 1104 | 254251104 |  | 0.76032 | 0 |  | 11 | 0.00087208 | 1407 | 0.055675 | 7644 | 4.8691e-05 | 4548
ACTON 0401683338 | ACTON 0401 | 22470401 |  | 0.02103 | 0 |  | 0.66667 | 0.00091743 | 1160 | 0.053073 | 8251 | 4.869e-05 | 4549
GREEN VALLEY 2102CB | GREEN VALLEY 2102 | 83192102 |  | 13.7663 | 6.4946 |  | 211.3333 | 0.00084055 | 1644 | 0.05829 | 7254 | 4.8685e-05 | 4550
WEBER 1113CB | WEBER 1113 | 163481113 |  | 2.1223 | 0.27092 |  | 38.5 | 0.00077572 | 2198 | 0.065302 | 6393 | 4.8679e-05 | 4551
MAGUNDEN 110188892 | MAGUNDEN 1101 | 252771101 |  | 9.3634 | 10.4277 |  | 151 | 0.0009168 | 1163 | 0.05313 | 8239 | 4.8677e-05 | 4552
ALMADEN 1102CB | ALMADEN 1102 | 82311102 |  | 1.2301 | 0.284 |  | 12.1667 | 0.00091686 | 1162 | 0.053073 | 8253 | 4.866e-05 | 4553
VIEJO 22032628 | VIEJO 2203 | 182852203 |  | 3.715 | 4.1046 |  | 61.8333 | 0.00076385 | 2335 | 0.064033 | 6537 | 4.8636e-05 | 4554
VIEJO 22032636 | VIEJO 2203 | 182852203 |  | 1.6185 | 2.6534 |  | 25.6667 | 0.0007368 | 2657 | 0.065915 | 6290 | 4.8632e-05 | 4555
LOCKEFORD 21026204 | LOCKEFORD 2102 | 163682102 |  | 0.027135 | 0 |  | 0.83333 | 0.00072563 | 2784 | 0.067 | 6056 | 4.8617e-05 | 4556
VACA DIXON 1103CB | VACA DIXON 1103 | 63591103 |  | 2.185 | 0.13284 |  | 26.0667 | 0.00072703 | 2760 | 0.067663 | 5521 | 4.8615e-05 | 4557
EDENVALE 2109CB | EDENVALE 2109 | 82952109 |  | 2.0428 | 0.49688 |  | 30.5833 | 0.00091593 | 1164 | 0.053073 | 8252 | 4.8611e-05 | 4558
FELLOWS 2103CB | FELLOWS 2103 | 254242103 |  | 2.0355 | 0.016562 |  | 30.8333 | 0.00071625 | 2901 | 0.06801 | 5404 | 4.8578e-05 | 4559
DUNBAR 1103CB | DUNBAR 1103 | 43071103 | TRUE | 3.3395 | 0.192 | 0.014771 | 64.1667 | 0.00069079 | 3209 | 0.070259 | 4991 | 4.8578e-05 | 4560
ASHLAN AVE 2119S60 | ASHLAN AVE 2119 | 252052119 |  | 3.9673 | 2.4987 |  | 73.5 | 0.00091514 | 1165 | 0.053073 | 8251 | 4.8569e-05 | 4561
MOUNTAIN VIEW 1113CB | MOUNTAIN VIEW 1113 | 82031113 |  | 1.4659 | 0.30836 |  | 24.45 | 0.00085893 | 1503 | 0.055921 | 7592 | 4.8553e-05 | 4562
EL CAPITAN 110690350 | EL CAPITAN 1106 | 253881106 |  | 3.9646 | 2.4047 |  | 70.8333 | 0.00088707 | 1325 | 0.055598 | 7658 | 4.8552e-05 | 4563
STOCKTON A 1111CB | STOCKTON A 1111 | 162371111 |  | 0.068472 | 0.41417 |  | 6.4167 | 0.0009148 | 1166 | 0.053073 | 8250 | 4.8551e-05 | 4564
MAGUNDEN 1108CB | MAGUNDEN 1108 | 252771108 |  | 3.2795 | 0.13735 |  | 44.2262 | 0.00075667 | 2419 | 0.06558 | 6346 | 4.8549e-05 | 4565
OAKLAND C 1117CB | OAKLAND C 1117 | 12011117 |  | 0.39546 | 0.092771 |  | 6.3333 | 0.00091425 | 1168 | 0.053073 | 8251 | 4.8522e-05 | 4566
WALNUT CREEK 0404CB | WALNUT CREEK 0404 | 12200404 |  | 6.4399 | 5.2721 |  | 87.7 | 0.00075888 | 2401 | 0.064002 | 6542 | 4.8518e-05 | 4567
TRIMBLE 2116CB | TRIMBLE 2116 | 83802116 |  | 1.0387 | 0.20999 |  | 16.5 | 0.00091389 | 1169 | 0.053073 | 8251 | 4.8503e-05 | 4568
DAVIS 110743434 | DAVIS 1107 | 62041107 |  | 0.86593 | 0.42739 |  | 14.6667 | 0.00091382 | 1170 | 0.053073 | 8252 | 4.8499e-05 | 4569
OAKLAND D 1102CB | OAKLAND D 1102 | 12041102 |  | 2.7573 | 2.3494 |  | 41.0833 | 0.0009138 | 1171 | 0.053073 | 8251 | 4.8498e-05 | 4570
DAVIS 1102CB | DAVIS 1102 | 62041102 |  | 3.9393 | 3.9112 |  | 57.2 | 0.00091369 | 1172 | 0.053073 | 8251 | 4.8492e-05 | 4571
CALISTOGA 1101894 | CALISTOGA 1101 | 42711101 |  | 2.4583 | 0.87869 |  | 46.5 | 0.00053472 | 5013 | 0.12504 | 3259 | 4.8487e-05 | 4572
COTTONWOOD 110359128 | COTTONWOOD 1103 | 102931103 | FALSE | 7.0029 | 0.67922 | 0.71269 | 128.5 | 0.00035244 | 7098 | 0.20755 | 3134 | 4.8473e-05 | 4573
MADERA 111411430 | MADERA 1114 | 252761114 |  | 5.4469 | 4.6671 |  | 97.5 | 0.00091326 | 1173 | 0.053073 | 8251 | 4.8469e-05 | 4574
PAUL SWEET 210112594 | PAUL SWEET 2101 | 83252101 |  | 0.76372 | 0.35205 |  | 11.6667 | 0.00080143 | 1958 | 0.059638 | 7063 | 4.8469e-05 | 4575
BASALT 110138824 | BASALT 1101 | 42461101 |  | 1.0407 | 0.23237 |  | 20.7 | 0.00090136 | 1224 | 0.053745 | 8016 | 4.8413e-05 | 4576
BULLARD 110475696 | BULLARD 1104 | 253961104 |  | 3.4711 | 3.437 |  | 49 | 0.00091209 | 1177 | 0.053073 | 8251 | 4.8407e-05 | 4577
ALHAMBRA 110581514 | ALHAMBRA 1105 | 14101105 | TRUE | 1.9138 | 1.7143 | 0.11449 | 31.5 | 0.00066778 | 3460 | 0.072489 | 4717 | 4.8407e-05 | 4578
COLUMBUS 11101307 | COLUMBUS 1110 | 253951110 |  | 4.6406 | 4.7759 |  | 67 | 0.00091115 | 1178 | 0.053073 | 8251 | 4.8357e-05 | 4579
IGNACIO 1103151462 | IGNACIO 1103 | 42481103 | TRUE | 0.14469 | 0.12723 | 0.27193 | 4 | 0.00091105 | 1179 | 0.053073 | 8251 | 4.8352e-05 | 4580
VASONA 1101CB | VASONA 1101 | 83771101 |  | 1.3265 | 1.4533 |  | 21.5 | 0.00073021 | 2724 | 0.066352 | 6211 | 4.8347e-05 | 4581
KIRKER 2103CB | KIRKER 2103 | 14452103 |  | 0.77388 | 0.29591 |  | 13.8333 | 0.00073532 | 2674 | 0.066697 | 6137 | 4.8341e-05 | 4582
MONROE 210781174 | MONROE 2107 | 43302107 |  | 1.8264 | 1.7659 |  | 30.5 | 0.00089018 | 1295 | 0.054726 | 7799 | 4.8339e-05 | 4583
LAKEWOOD 2224CB | LAKEWOOD 2224 | 13532224 |  | 8.9206 | 4.5954 |  | 128.0333 | 0.00076191 | 2355 | 0.063691 | 6581 | 4.8332e-05 | 4584
ASHLAN AVE 211832478 | ASHLAN AVE 2118 | 252052118 |  | 0.84678 | 0.15192 |  | 19.5 | 0.00091066 | 1181 | 0.053073 | 8251 | 4.8331e-05 | 4585
CONTRA COSTA 2115CB | CONTRA COSTA 2115 | 13652115 |  | 5.0538 | 2.8697 |  | 68.3167 | 0.00086799 | 1436 | 0.055006 | 7750 | 4.831e-05 | 4586
BRENTWOOD 2109CB | BRENTWOOD 2109 | 14592109 |  | 1.2845 | 0.029005 |  | 17.8333 | 0.00075536 | 2429 | 0.063877 | 6560 | 4.8304e-05 | 4587
OAKLAND D 1134CB | OAKLAND D 1134 | 12041134 |  | 0.61372 | 0 |  | 4.75 | 0.00091014 | 1186 | 0.053073 | 8251 | 4.8303e-05 | 4588
BAKERSFIELD 11183338 | BAKERSFIELD 1118 | 253371118 |  | 9.2403 | 8.3944 |  | 158.3333 | 0.00089996 | 1232 | 0.053597 | 8061 | 4.8294e-05 | 4589
PIERCY 210942383 | PIERCY 2109 | 83912109 |  | 0.87396 | 1.0068 |  | 14 | 0.00090973 | 1189 | 0.053073 | 8251 | 4.8282e-05 | 4590
ROSSMOOR 110798488 | ROSSMOOR 1107 | 14161107 |  | 8.3478 | 4.6855 |  | 145.8333 | 0.00073781 | 2639 | 0.065627 | 6335 | 4.8281e-05 | 4591
WOODLAND 1109CB | WOODLAND 1109 | 62031109 |  | 10.0841 | 7.268 |  | 141.6667 | 0.00090969 | 1190 | 0.053073 | 8252 | 4.828e-05 | 4592
SF L 110147096 | SF L 1101 | 22261101 |  | 0.32299 | 0.28571 |  | 3.7 | 0.0009096 | 1191 | 0.053073 | 8251 | 4.8275e-05 | 4593
STOREY 110749686 | STOREY 1107 | 254611107 |  | 1.2865 | 0.97571 |  | 25.6667 | 0.00079887 | 1979 | 0.059391 | 7099 | 4.8269e-05 | 4594
KERN POWER 2103CB | KERN POWER 2103 | 255262103 |  | 5.1459 | 1.4538 |  | 74.1167 | 0.0008536 | 1550 | 0.057467 | 7364 | 4.8266e-05 | 4595
PUEBLO 110548264 | PUEBLO 1105 | 43291105 |  | 3.4386 | 0.98667 |  | 59 | 0.00071981 | 2854 | 0.067044 | 5952 | 4.8257e-05 | 4596
SAN LEANDRO U 1114MR544 | SAN LEANDRO U 1114 | 13111114 | TRUE | 4.4234 | 3.9571 | 0.017444 | 64.5833 | 0.00085658 | 1523 | 0.061565 | 6817 | 4.8246e-05 | 4597
PITTSBURG 0401CB | PITTSBURG 0401 | 12160401 |  | 1.0542 | 0.18379 |  | 6.75 | 0.00089152 | 1283 | 0.054107 | 7928 | 4.8236e-05 | 4598
SNEATH LANE 110796530 | SNEATH LANE 1107 | 22721107 |  | 2.2178 | 1.7875 |  | 32.3333 | 0.0007381 | 2635 | 0.065133 | 6414 | 4.8212e-05 | 4599
STONE CORRAL 1110894956 | STONE CORRAL 1110 | 252921110 | FALSE | 1.6641 | 0.13811 | 0.69128 | 30.5 | 0.00018741 | 10240 | 0.31556 | 2999 | 4.8205e-05 | 4600
SAN RAFAEL 1109CB | SAN RAFAEL 1109 | 42011109 |  | 4.9077 | 3.6628 |  | 69.8333 | 0.00084042 | 1646 | 0.05789 | 7310 | 4.8194e-05 | 4601
TAFT 11041556 | TAFT 1104 | 252081104 |  | 3.9149 | 3.1613 |  | 59.8333 | 0.00086665 | 1445 | 0.055313 | 7705 | 4.8188e-05 | 4602
SANTA ROSA A 110179038 | SANTA ROSA A 1101 | 42151101 |  | 1.973 | 2.0271 |  | 28.5 | 0.00084211 | 1638 | 0.056982 | 7440 | 4.8182e-05 | 4603
WOODWARD 210266406 | WOODWARD 2102 | 255292102 |  | 0.70515 | 0.021841 |  | 15 | 0.00090771 | 1196 | 0.053073 | 8251 | 4.8175e-05 | 4604
FMC 1105XR050 | FMC 1105 | 83871105 |  | 4.4472 | 4.191 |  | 78 | 0.0009077 | 1197 | 0.053073 | 8251 | 4.8174e-05 | 4605
GREENBRAE 1104107508 | GREENBRAE 1104 | 43091104 | TRUE | 0.17582 | 0.18263 | 0.060499 | 3.5 | 0.00090768 | 1198 | 0.053073 | 8251 | 4.8173e-05 | 4606
DEL MONTE 210478676 | DEL MONTE 2104 | 182222104 |  | 1.1013 | 1.0569 |  | 24.8333 | 0.00084799 | 1589 | 0.056157 | 7554 | 4.8169e-05 | 4607
CONTRA COSTA 210338886 | CONTRA COSTA 2103 | 13652103 |  | 3.0093 | 2.3199 |  | 50 | 0.00087467 | 1395 | 0.054631 | 7820 | 4.8166e-05 | 4608
CAMPHORA 1101552534 | CAMPHORA 1101 | 182071101 |  | 0.017347 | 0 |  | 0.5 | 0.00071879 | 2864 | 0.067 | 6057 | 4.8159e-05 | 4609
MONARCH 0403CB | MONARCH 0403 | 162300403 |  | 4.7436 | 4.7762 |  | 58.3667 | 0.00090736 | 1200 | 0.053073 | 8252 | 4.8156e-05 | 4610
BELLE HAVEN 110611881 | BELLE HAVEN 1106 | 24021106 |  | 0.2828 | 0.20325 |  | 2.6667 | 0.00090735 | 1201 | 0.053073 | 8252 | 4.8156e-05 | 4611
OAKLAND X 1106CB | OAKLAND X 1106 | 12541106 | TRUE | 6.869 | 7.1415 | 0.178 | 97.25 | 0.00071418 | 2922 | 0.073497 | 4612 | 4.8128e-05 | 4612
MARYSVILLE 1107CB | MARYSVILLE 1107 | 152011107 |  | 8.518 | 3.075 |  | 119.5 | 0.00089047 | 1290 | 0.05457 | 7834 | 4.812e-05 | 4613
SAN JOSE B 1104CB | SAN JOSE B 1104 | 82261104 |  | 0.48522 | 0.0089486 |  | 12.8333 | 0.00089501 | 1269 | 0.053743 | 8018 | 4.8116e-05 | 4614
OAKLAND J 1102159816 | OAKLAND J 1102 | 12091102 | TRUE | 0.18208 | 0.10143 | 0.19969 | 2.5833 | 0.00090653 | 1203 | 0.053073 | 8250 | 4.8112e-05 | 4615
BERKELEY T 0402302696 | BERKELEY T 0402 | 12660402 |  | 0.054929 | 0.074362 |  | 0.83333 | 0.00090603 | 1207 | 0.053073 | 8250 | 4.8086e-05 | 4616
JARVIS 1103CB | JARVIS 1103 | 13501103 |  | 2.0034 | 1.5208 |  | 21.75 | 0.00089016 | 1296 | 0.054033 | 7941 | 4.8063e-05 | 4617
EAST STOCKTON 0402CB | EAST STOCKTON 0402 | 163130402 |  | 7.3587 | 5.219 |  | 89.25 | 0.00090556 | 1209 | 0.053073 | 8250 | 4.806e-05 | 4618
TIDEWATER 2105992888 | TIDEWATER 2105 | 14652105 |  | 3.477 | 3.5389 |  | 47.5 | 0.00090554 | 1210 | 0.053073 | 8251 | 4.8059e-05 | 4619
WATSONVILLE 0411CB | WATSONVILLE 0411 | 83330411 |  | 2.2342 | 2.436 |  | 27.0833 | 0.00082988 | 1737 | 0.057399 | 7374 | 4.8045e-05 | 4620
ARCATA 1124CB | ARCATA 1124 | 192021124 |  | 0.002643 | 0 |  | 0.25 | 0.00090509 | 1211 | 0.053073 | 8251 | 4.8036e-05 | 4621
ROSSMOOR 1103W514R | ROSSMOOR 1103 | 14161103 |  | 0.10642 | 0 |  | 1.5 | 0.00070283 | 3068 | 0.068329 | 5324 | 4.8023e-05 | 4622
ROSSMOOR 110136572 | ROSSMOOR 1101 | 14161101 |  | 6.1315 | 5.7787 |  | 113.5 | 0.00075323 | 2451 | 0.064168 | 6521 | 4.8003e-05 | 4623
CALIFORNIA AVE 111079664 | CALIFORNIA AVE 1110 | 252281110 |  | 3.8722 | 3.6244 |  | 57.5 | 0.00090429 | 1213 | 0.053073 | 8252 | 4.7993e-05 | 4624
MANTECA 1706CB | MANTECA 1706 | 162611706 |  | 3.9481 | 2.2306 |  | 54.8333 | 0.00086334 | 1468 | 0.056178 | 7550 | 4.7965e-05 | 4625
VALLEJO B 0415CB | VALLEJO B 0415 | 42450415 |  | 1.9407 | 1.4802 |  | 20.1667 | 0.00090349 | 1215 | 0.053073 | 8251 | 4.7951e-05 | 4626
BARTON 1114CB | BARTON 1114 | 253571114 |  | 12.8163 | 12.0898 |  | 197.6667 | 0.00090291 | 1217 | 0.053116 | 8244 | 4.7926e-05 | 4627
PETALUMA C 1110456 | PETALUMA C 1110 | 42631110 |  | 0.24833 | 0.085806 |  | 4.5 | 0.00090292 | 1216 | 0.053073 | 8251 | 4.792e-05 | 4628
SAN JOSE B 1112XR280 | SAN JOSE B 1112 | 82261112 |  | 1.4017 | 0.51643 |  | 24.3333 | 0.00090287 | 1218 | 0.053073 | 8251 | 4.7917e-05 | 4629
WOODLAND 1101CB | WOODLAND 1101 | 62031101 |  | 3.6723 | 0.13731 |  | 62 | 0.00081223 | 1879 | 0.06047 | 6964 | 4.7917e-05 | 4630
MANZANITA 0404878376 | MANZANITA 0404 | 183150404 |  | 0.43509 | 0.39737 |  | 5 | 0.00090262 | 1220 | 0.053073 | 8250 | 4.7904e-05 | 4631
FORT ORD 1101CB | FORT ORD 1101 | 182401101 |  | 4.5894 | 2.6556 |  | 59.0833 | 0.00081633 | 1844 | 0.0582 | 7268 | 4.7891e-05 | 4632
FAIRVIEW 2207M526R | FAIRVIEW 2207 | 13432207 |  | 2.458 | 2.4247 |  | 44.6667 | 0.00088093 | 1360 | 0.054489 | 7846 | 4.7881e-05 | 4633
FIGARDEN 210245890 | FIGARDEN 2102 | 254552102 |  | 2.4338 | 1.4858 |  | 32.8333 | 0.00090193 | 1222 | 0.053073 | 8250 | 4.7868e-05 | 4634
POTRERO PP (A) 111041854 | POTRERO PP (A) 1110 | 22031110 |  | 1.6272 | 1.324 |  | 16.75 | 0.00090148 | 1223 | 0.053073 | 8251 | 4.7844e-05 | 4635
FAIRVIEW 2206CB | FAIRVIEW 2206 | 13432206 |  | 6.5005 | 3.7134 |  | 95.5 | 0.00085627 | 1524 | 0.057131 | 7416 | 4.7842e-05 | 4636
RENFRO 2105CB | RENFRO 2105 | 254572105 |  | 3.7703 | 0.13597 |  | 62.1667 | 0.00074545 | 2539 | 0.06537 | 6382 | 4.784e-05 | 4637
VINEYARD 2108MR696 | VINEYARD 2108 | 14502108 |  | 2.2922 | 1.0461 |  | 39.3333 | 0.00074986 | 2482 | 0.064049 | 6534 | 4.7826e-05 | 4638
LAKEWOOD 222466408 | LAKEWOOD 2224 | 13532224 |  | 1.9187 | 1.0657 |  | 33.3333 | 0.00060721 | 4207 | 0.099074 | 3316 | 4.7824e-05 | 4639
EAST GRAND 1115CB | EAST GRAND 1115 | 22571115 |  | 0.0028892 | 0 |  | 0.5 | 0.00090085 | 1225 | 0.053073 | 8251 | 4.7811e-05 | 4640
EMBARCADERO (Z) 1116CB | EMBARCADERO (Z) 1116 | 22871116 |  | 0.97281 | 0.97864 |  | 17.6667 | 0.0009008 | 1226 | 0.053073 | 8250 | 4.7808e-05 | 4641
STOCKDALE 11081521 | STOCKDALE 1108 | 254071108 |  | 2.2512 | 1.8845 |  | 39.6667 | 0.00090078 | 1227 | 0.053073 | 8252 | 4.7807e-05 | 4642
POTRERO PP (A) 110811489 | POTRERO PP (A) 1108 | 22031108 |  | 1.7066 | 1.4029 |  | 29.8333 | 0.00090073 | 1228 | 0.053073 | 8250 | 4.7804e-05 | 4643
TRACY 0402CB | TRACY 0402 | 162880402 |  | 2.8934 | 1.5465 |  | 29.7833 | 0.00090023 | 1231 | 0.053073 | 8251 | 4.7778e-05 | 4644
SILVERADO 21022495 | SILVERADO 2102 | 43432102 |  | 1.7398 | 0.34892 |  | 37.5 | 0.00066421 | 3511 | 0.098066 | 3321 | 4.7776e-05 | 4645
COLUMBUS 1106CB | COLUMBUS 1106 | 253951106 |  | 13.0811 | 11.8416 |  | 164.4167 | 0.000899 | 1239 | 0.05323 | 8207 | 4.7768e-05 | 4646
WEBER 1103CB | WEBER 1103 | 163481103 |  | 1.8618 | 0.014117 |  | 33.1667 | 0.00082595 | 1766 | 0.059718 | 7053 | 4.7767e-05 | 4647
TEMPLETON 2112238418 | TEMPLETON 2112 | 183052112 | TRUE | 0.81372 | 0 | 0.16709 | 15.5 | 0.00014277 | 10766 | 0.38402 | 2935 | 4.7766e-05 | 4648
STONE 1104XR410 | STONE 1104 | 83701104 |  | 0.53824 | 0.11019 |  | 8.8333 | 0.00088716 | 1324 | 0.053861 | 7985 | 4.7764e-05 | 4649
WEBER 1109CB | WEBER 1109 | 163481109 |  | 5.3993 | 1.2417 |  | 84.9167 | 0.00086674 | 1444 | 0.055448 | 7681 | 4.7756e-05 | 4650
MOUNTAIN VIEW 1102CB | MOUNTAIN VIEW 1102 | 82031102 |  | 6.5861 | 3.934 |  | 78.1667 | 0.00086889 | 1431 | 0.055122 | 7733 | 4.7751e-05 | 4651
MOUNTAIN VIEW 1102LM32 | MOUNTAIN VIEW 1102 | 82031102 |  | 1.0657 | 0.19072 |  | 13.3333 | 0.00086835 | 1435 | 0.054988 | 7754 | 4.7747e-05 | 4652
SAN JOSE A 1111CB | SAN JOSE A 1111 | 82251111 |  | 0.12304 | 0.13281 |  | 4.8333 | 0.0008995 | 1233 | 0.053073 | 8251 | 4.7739e-05 | 4653
RINCON 1104207458 | RINCON 1104 | 43321104 |  | 5.3604 | 1.9724 |  | 92.3333 | 0.00078786 | 2076 | 0.060297 | 6985 | 4.7738e-05 | 4654
AIRWAYS 110854868 | AIRWAYS 1108 | 252041108 |  | 3.3769 | 2.1297 |  | 45.5 | 0.00089928 | 1234 | 0.053073 | 8251 | 4.7727e-05 | 4655
LAS GALLINAS A 1107980 | LAS GALLINAS A 1107 | 42991107 |  | 0.012716 | 0 |  | 0.5 | 0.00089923 | 1235 | 0.053073 | 8251 | 4.7724e-05 | 4656
MERCED 210111520 | MERCED 2101 | 252802101 |  | 0.7044 | 0 |  | 6 | 0.00061646 | 4096 | 0.0774 | 3397 | 4.7714e-05 | 4657
EAST GRAND 1101CB | EAST GRAND 1101 | 22571101 |  | 1.7811 | 1.6086 |  | 22.5833 | 0.00089883 | 1240 | 0.053073 | 8251 | 4.7703e-05 | 4658
MOUNTAIN VIEW 1103CB | MOUNTAIN VIEW 1103 | 82031103 |  | 2.8623 | 0.41535 |  | 38.5833 | 0.00089543 | 1266 | 0.053253 | 8195 | 4.7702e-05 | 4659
TEVIS 21012439 | TEVIS 2101 | 255322101 |  | 3.6227 | 0.0095479 |  | 59 | 0.00064432 | 3774 | 0.074418 | 4497 | 4.7699e-05 | 4660
EDES 1114CR324 | EDES 1114 | 13681114 |  | 4.0743 | 2.5846 |  | 72 | 0.00089866 | 1241 | 0.053073 | 8251 | 4.7694e-05 | 4661
COLUMBUS 1104CB | COLUMBUS 1104 | 253951104 |  | 7.635 | 7.2844 |  | 119.25 | 0.00089838 | 1243 | 0.053073 | 8249 | 4.7679e-05 | 4662
SARATOGA 1106CB | SARATOGA 1106 | 83371106 |  | 6.9436 | 4.6956 |  | 117.5 | 0.00080636 | 1927 | 0.059473 | 7088 | 4.7674e-05 | 4663
SWIFT 2107XR086 | SWIFT 2107 | 83392107 |  | 0.30151 | 0 |  | 6 | 0.00077145 | 2245 | 0.062358 | 6731 | 4.7668e-05 | 4664
SARATOGA 1115CB | SARATOGA 1115 | 83371115 |  | 3.5438 | 2.0372 |  | 53.3333 | 0.00082992 | 1736 | 0.056729 | 7476 | 4.7657e-05 | 4665
DAVIS 110489158 | DAVIS 1104 | 62041104 |  | 0.53437 | 0.34179 |  | 9.5 | 0.00089774 | 1245 | 0.053073 | 8251 | 4.7646e-05 | 4666
STOCKDALE 2113203905 | STOCKDALE 2113 | 254072113 |  | 11.503 | 10.0464 |  | 162.3333 | 0.00089762 | 1246 | 0.053073 | 8251 | 4.7639e-05 | 4667
REDWOOD CITY 0406CB | REDWOOD CITY 0406 | 24160406 |  | 0.086424 | 0.11616 |  | 0.86667 | 0.00089747 | 1248 | 0.053073 | 8252 | 4.7631e-05 | 4668
MAGUNDEN 21094102 | MAGUNDEN 2109 | 252772109 |  | 8.8226 | 7.4219 |  | 133.6667 | 0.00089741 | 1250 | 0.053073 | 8250 | 4.7628e-05 | 4669
TRINIDAD 11021032 | TRINIDAD 1102 | 192231102 |  | 10.6988 | 1.3765 |  | 194 | 0.000709 | 2991 | 0.067158 | 5845 | 4.7623e-05 | 4670
MADERA 11189810 | MADERA 1118 | 252761118 |  | 1.4926 | 0.14219 |  | 20.8333 | 0.00076942 | 2266 | 0.063995 | 6544 | 4.7623e-05 | 4671
ASHLAN AVE 2110CB | ASHLAN AVE 2110 | 252052110 |  | 4.8191 | 1.4335 |  | 72.2833 | 0.00089721 | 1251 | 0.053073 | 8250 | 4.7617e-05 | 4672
LAMMERS 1102CB | LAMMERS 1102 | 162771102 |  | 3.6042 | 0.73013 |  | 51.3333 | 0.00078129 | 2136 | 0.062417 | 6727 | 4.7617e-05 | 4673
GREEN VALLEY 210485200 | GREEN VALLEY 2104 | 83192104 |  | 3.0205 | 2.4024 |  | 36.0833 | 0.00084708 | 1595 | 0.056101 | 7561 | 4.7615e-05 | 4674
VALLEJO B 110175246 | VALLEJO B 1101 | 42451101 |  | 0.49184 | 0.1693 |  | 7.5 | 0.00089711 | 1252 | 0.053073 | 8251 | 4.7612e-05 | 4675
FREMONT 1104645342 | FREMONT 1104 | 14351104 | FALSE | 4.4375 | 0 | 1.0843 | 81.5 | 0.00011959 | 10954 | 0.61492 | 2719 | 4.7611e-05 | 4676
AMES 1101CB | AMES 1101 | 83901101 |  | 0.12362 | 0 |  | 1.3333 | 0.00089681 | 1253 | 0.053073 | 8251 | 4.7596e-05 | 4677
SAN RAFAEL 1102848296 | SAN RAFAEL 1102 | 42011102 |  | 0.73469 | 0.27516 |  | 13.3333 | 0.00089667 | 1254 | 0.053073 | 8250 | 4.7589e-05 | 4678
EDENVALE 2106CB | EDENVALE 2106 | 82952106 |  | 4.8974 | 1.4671 |  | 59.9167 | 0.00089651 | 1255 | 0.053073 | 8252 | 4.758e-05 | 4679
EDENVALE 2108XR118 | EDENVALE 2108 | 82952108 |  | 1.5613 | 0.22334 |  | 34 | 0.00089627 | 1259 | 0.053073 | 8251 | 4.7567e-05 | 4680
SAN JOSE B 1117CB | SAN JOSE B 1117 | 82261117 |  | 3.6576 | 2.5956 |  | 59.8333 | 0.00089607 | 1261 | 0.053073 | 8252 | 4.7557e-05 | 4681
LAS POSITAS 2106CB | LAS POSITAS 2106 | 14402106 |  | 1.15 | 0.086037 |  | 19 | 0.00072844 | 2745 | 0.064434 | 6493 | 4.7554e-05 | 4682
MONROE 110636930 | MONROE 1106 | 43301106 |  | 0.59356 | 0.099029 |  | 7.5 | 0.00089565 | 1264 | 0.053073 | 8251 | 4.7535e-05 | 4683
OAKLAND C 1115CR162 | OAKLAND C 1115 | 12011115 |  | 0.036834 | 0.050234 |  | 1.75 | 0.00089565 | 1265 | 0.053073 | 8251 | 4.7534e-05 | 4684
TULUCAY 11012280 | TULUCAY 1101 | 42301101 |  | 0.023758 | 0 |  | 1 | 0.00070702 | 3017 | 0.067227 | 5781 | 4.7532e-05 | 4685
FULTON 1106CB | FULTON 1106 | 42561106 |  | 4.859 | 0.063812 |  | 73.4167 | 0.00072441 | 2797 | 0.06575 | 6316 | 4.7528e-05 | 4686
SYCAMORE CREEK 11055315 | SYCAMORE CREEK 1105 | 102971105 |  | 1.2035 | 0.76049 |  | 18.3333 | 0.00088791 | 1316 | 0.053453 | 8110 | 4.7526e-05 | 4687
NEWARK 21KV 2107MR111 | NEWARK 21KV 2107 | 12232107 |  | 1.0999 | 0.12646 |  | 18.5 | 0.00085018 | 1572 | 0.055725 | 7635 | 4.7525e-05 | 4688
TRIMBLE 1103XR342 | TRIMBLE 1103 | 83801103 |  | 2.2246 | 0.62683 |  | 38.3333 | 0.00089524 | 1267 | 0.053073 | 8250 | 4.7513e-05 | 4689
SANTA MARIA 1107773358 | SANTA MARIA 1107 | 182671107 |  | 0.38455 | 0 |  | 4.5 | 0.00070906 | 2990 | 0.067 | 6057 | 4.7507e-05 | 4690
SERRAMONTE 1103CB | SERRAMONTE 1103 | 22861103 |  | 4.0446 | 3.5917 |  | 62.3333 | 0.00081155 | 1887 | 0.058212 | 7266 | 4.7505e-05 | 4691
STAGG 110514706 | STAGG 1105 | 162421105 |  | 3.3715 | 3.2284 |  | 45.8333 | 0.00089502 | 1268 | 0.053073 | 8251 | 4.7501e-05 | 4692
BAKERSFIELD 110249648 | BAKERSFIELD 1102 | 253371102 |  | 11.2994 | 11.0794 |  | 171.3333 | 0.00089335 | 1275 | 0.053272 | 8190 | 4.7498e-05 | 4693
SAN RAFAEL 1102CB | SAN RAFAEL 1102 | 42011102 |  | 1.8399 | 0.89306 |  | 30.3333 | 0.00089492 | 1270 | 0.053073 | 8251 | 4.7496e-05 | 4694
SANTA ROSA A 1102608 | SANTA ROSA A 1102 | 42151102 |  | 0.084138 | 0 |  | 2.5 | 0.00089471 | 1271 | 0.053073 | 8251 | 4.7485e-05 | 4695
HORSESHOE 110296830 | HORSESHOE 1102 | 152571102 |  | 0.051334 | 0 |  | 0.5 | 0.00070854 | 3000 | 0.067 | 6057 | 4.7472e-05 | 4696
MARYSVILLE 1106CB | MARYSVILLE 1106 | 152011106 |  | 3.541 | 2.0594 |  | 54.6667 | 0.00088697 | 1326 | 0.05374 | 8020 | 4.7459e-05 | 4697
RICHMOND R 1129557351 | RICHMOND R 1129 | 13471129 |  | 0.42132 | 0 |  | 8.5 | 0.0007043 | 3050 | 0.067372 | 5686 | 4.745e-05 | 4698
HAMILTON BRANCH 110137436 | HAMILTON BRANCH 1101 | 102361101 | FALSE | 2.0509 | 1.1676 | 0.86069 | 38.3333 | 0.00044353 | 5978 | 0.12006 | 3265 | 4.7444e-05 | 4699
SALINAS 1108CB | SALINAS 1108 | 182011108 |  | 2.7348 | 0.74674 |  | 48 | 0.00087682 | 1383 | 0.054233 | 7897 | 4.7426e-05 | 4700
STOCKTON A 110814708 | STOCKTON A 1108 | 162371108 |  | 3.1385 | 2.107 |  | 51 | 0.0008903 | 1291 | 0.05341 | 8126 | 4.7409e-05 | 4701
OAKLAND X 1103221898 | OAKLAND X 1103 | 12541103 |  | 0.14943 | 0.13731 |  | 2.5 | 0.00089326 | 1276 | 0.053073 | 8251 | 4.7408e-05 | 4702
SAN LEANDRO U 1106CB | SAN LEANDRO U 1106 | 13111106 |  | 0.97109 | 0.17777 |  | 13.3333 | 0.00089317 | 1278 | 0.053073 | 8251 | 4.7403e-05 | 4703
MT EDEN 1106CB | MT EDEN 1106 | 13761106 |  | 4.9479 | 3.2322 |  | 71.3 | 0.00089316 | 1279 | 0.053073 | 8250 | 4.7402e-05 | 4704
MEADOW LANE 2106C537R | MEADOW LANE 2106 | 14302106 |  | 4.9944 | 4.1523 |  | 67.5 | 0.00083665 | 1667 | 0.056787 | 7468 | 4.7401e-05 | 4705
PUEBLO 11042802 | PUEBLO 1104 | 43291104 |  | 0.48765 | 0.14239 |  | 8.5 | 0.00070345 | 3059 | 0.067223 | 5787 | 4.7386e-05 | 4706
CLEAR LAKE 1101529830 | CLEAR LAKE 1101 | 42141101 |  | 0.025672 | 0.022906 |  | 1 | 0.0007054 | 3039 | 0.067175 | 5831 | 4.7385e-05 | 4707
PUTAH CREEK 110537280 | PUTAH CREEK 1105 | 63681105 |  | 1.1796 | 0.60681 |  | 18 | 0.00088357 | 1345 | 0.0537 | 8029 | 4.7377e-05 | 4708
STOCKTON A 11097402 | STOCKTON A 1109 | 162371109 |  | 4.0841 | 2.2157 |  | 61.3333 | 0.00089268 | 1281 | 0.053073 | 8251 | 4.7377e-05 | 4709
BRENTWOOD 211199210 | BRENTWOOD 2111 | 14592111 |  | 1.1176 | 0.23254 |  | 22 | 0.00077042 | 2252 | 0.063518 | 6610 | 4.7372e-05 | 4710
OROVILLE 0402CB | OROVILLE 0402 | 102520402 |  | 1.5878 | 0.92893 |  | 22.0833 | 0.00088477 | 1337 | 0.054174 | 7909 | 4.7356e-05 | 4711
IONE 110112236 | IONE 1101 | 163881101 |  | 0.011049 | 0 |  | 1 | 0.00070671 | 3018 | 0.067 | 6057 | 4.7349e-05 | 4712
HICKS 2102CB | HICKS 2102 | 83432102 |  | 3.9025 | 0.52268 |  | 46.6 | 0.00088942 | 1303 | 0.053177 | 8222 | 4.7344e-05 | 4713
JAMESON 1105CB | JAMESON 1105 | 63801105 |  | 10.5436 | 2.6532 |  | 182.2 | 0.00073308 | 2695 | 0.065184 | 6405 | 4.7335e-05 | 4714
KINGSBURG 111139720 | KINGSBURG 1111 | 252241111 |  | 0.032924 | 0 |  | 1 | 0.00061149 | 4150 | 0.0774 | 3397 | 4.733e-05 | 4715
LLAGAS 2101CB | LLAGAS 2101 | 83182101 |  | 0.84796 | 0 |  | 14.8333 | 0.00070612 | 3026 | 0.067 | 6056 | 4.731e-05 | 4716
PAUL SWEET 2104CB | PAUL SWEET 2104 | 83252104 |  | 8.0517 | 3.8097 |  | 112.1667 | 0.00083283 | 1703 | 0.056365 | 7520 | 4.7309e-05 | 4717
SAN LEANDRO U 1116CB | SAN LEANDRO U 1116 | 13111116 |  | 1.5711 | 1.1491 |  | 21.25 | 0.00089126 | 1285 | 0.053073 | 8251 | 4.7302e-05 | 4718
SANTA ROSA A 1105390 | SANTA ROSA A 1105 | 42151105 |  | 0.43793 | 0.15037 |  | 8.5 | 0.00089115 | 1286 | 0.053073 | 8251 | 4.7296e-05 | 4719
LUCERNE 11034624 | LUCERNE 1103 | 43351103 | TRUE | 3.7734 | 0.82717 | 0.061249 | 73 | 0.00028761 | 8241 | 0.14964 | 3208 | 4.7293e-05 | 4720
BELL 1110CB | BELL 1110 | 152701110 |  | 3.2546 | 1.5805 |  | 55.75 | 0.0007993 | 1972 | 0.058381 | 7236 | 4.7277e-05 | 4721
BRENTWOOD 2106CB | BRENTWOOD 2106 | 14592106 |  | 3.8904 | 1.291 |  | 63.1667 | 0.00083862 | 1655 | 0.057794 | 7326 | 4.7273e-05 | 4722
ATWATER 1107CB | ATWATER 1107 | 253611107 |  | 1.0502 | 0.31669 |  | 13.5 | 0.0008906 | 1288 | 0.053073 | 8251 | 4.7266e-05 | 4723
JAMESON 1102CB | JAMESON 1102 | 63801102 |  | 3.1485 | 0.14213 |  | 59.5 | 0.00070223 | 3075 | 0.067642 | 5528 | 4.7263e-05 | 4724
PANAMA 2102784680 | PANAMA 2102 | 253422102 |  | 3.3983 | 1.7052 |  | 46.8333 | 0.00089048 | 1289 | 0.053073 | 8250 | 4.726e-05 | 4725
MOUNTAIN VIEW 11073225 | MOUNTAIN VIEW 1107 | 82031107 |  | 0.92706 | 1.0271 |  | 10.8333 | 0.00078311 | 2119 | 0.060786 | 6916 | 4.726e-05 | 4726
BARTON 1110D8927 | BARTON 1110 | 253571110 |  | 0.90006 | 1.5806 |  | 18.8333 | 0.00089026 | 1292 | 0.053073 | 8251 | 4.7249e-05 | 4727
WOODLAND 110822232 | WOODLAND 1108 | 62031108 |  | 0.025284 | 0 |  | 2 | 0.00089019 | 1294 | 0.053073 | 8251 | 4.7245e-05 | 4728
NORTH TOWER 2104CB | NORTH TOWER 2104 | 42042104 |  | 4.2092 | 0 |  | 38.2333 | 0.00081441 | 1863 | 0.059682 | 7058 | 4.7233e-05 | 4729
LAS POSITAS 210576660 | LAS POSITAS 2105 | 14402105 |  | 0.16874 | 0 |  | 1.5 | 0.00088971 | 1300 | 0.053073 | 8251 | 4.7219e-05 | 4730
DAVIS 111157658 | DAVIS 1111 | 62041111 |  | 6.1848 | 4.6184 |  | 97.8333 | 0.00088463 | 1339 | 0.053497 | 8097 | 4.7217e-05 | 4731
LONE TREE 2102CB | LONE TREE 2102 | 13232102 |  | 1.7712 | 0.35837 |  | 33.3333 | 0.00074264 | 2577 | 0.065167 | 6409 | 4.7203e-05 | 4732
CHESTER 1101CB | CHESTER 1101 | 103181101 | TRUE | 5.1267 | 3.9243 | 0.049297 | 82 | 0.00042609 | 6161 | 0.115 | 3279 | 4.7203e-05 | 4733
WHISMAN 1111CB | WHISMAN 1111 | 83631111 |  | 2.195 | 0.79894 |  | 35.5 | 0.00088941 | 1304 | 0.053073 | 8251 | 4.7203e-05 | 4734
CLAYTON 2218CB | CLAYTON 2218 | 12022218 |  | 8.3209 | 7.2975 |  | 132.4167 | 0.0008477 | 1591 | 0.056561 | 7497 | 4.72e-05 | 4735
TRIMBLE 1103CB | TRIMBLE 1103 | 83801103 |  | 0.51115 | 0.074915 |  | 10.5 | 0.00088913 | 1305 | 0.053073 | 8251 | 4.7189e-05 | 4736
SAN JOSE B 110816141 | SAN JOSE B 1108 | 82261108 |  | 0.64475 | 0.3015 |  | 11 | 0.00088868 | 1307 | 0.053073 | 8251 | 4.7165e-05 | 4737
LAS GALLINAS A 1105CB | LAS GALLINAS A 1105 | 42991105 |  | 1.0658 | 0.32545 |  | 15.3333 | 0.00075907 | 2398 | 0.063963 | 6549 | 4.7152e-05 | 4738
SF E 0409CB | SF E 0409 | 22070409 |  | 1.8485 | 1.3319 |  | 20.2595 | 0.00088842 | 1309 | 0.053073 | 8251 | 4.7151e-05 | 4739
BARTON 111549016 | BARTON 1115 | 253571115 |  | 2.2309 | 2.9077 |  | 38 | 0.00088805 | 1312 | 0.053073 | 8251 | 4.7131e-05 | 4740
ROSEDALE 11012154 | ROSEDALE 1101 | 254761101 |  | 3.4072 | 1.4591 |  | 67 | 0.00083847 | 1658 | 0.056106 | 7560 | 4.713e-05 | 4741
JARVIS 1107CB | JARVIS 1107 | 13501107 |  | 0.0045607 | 0 |  | 0.5 | 0.00088802 | 1313 | 0.053073 | 8251 | 4.713e-05 | 4742
MARINA (F) 0404CB | MARINA (F) 0404 | 22780404 |  | 0.36735 | 0 |  | 3 | 0.00088794 | 1315 | 0.053073 | 8250 | 4.7125e-05 | 4743
MILLBRAE 1108CB | MILLBRAE 1108 | 22691108 |  | 1.755 | 1.1726 |  | 23.1667 | 0.00074933 | 2495 | 0.06191 | 6774 | 4.7119e-05 | 4744
DALY CITY 11045169 | DALY CITY 1104 | 22641104 |  | 2.2117 | 1.2932 |  | 41.5 | 0.00076771 | 2287 | 0.062164 | 6751 | 4.7107e-05 | 4745
PENNGROVE 1101CB | PENNGROVE 1101 | 43471101 |  | 0.029067 | 0 |  | 0.5 | 0.00070309 | 3064 | 0.067 | 6057 | 4.7107e-05 | 4746
HUNTERS POINT (P) 1106CB | HUNTERS POINT (P) 1106 | 22331106 |  | 0.41876 | 0.078883 |  | 9.5 | 0.00088752 | 1320 | 0.053073 | 8251 | 4.7103e-05 | 4747
VASONA 1108CB | VASONA 1108 | 83771108 |  | 1.925 | 1.6336 |  | 32.8333 | 0.00086413 | 1463 | 0.054345 | 7879 | 4.7102e-05 | 4748
SAN JOSE B 1107XR020 | SAN JOSE B 1107 | 82261107 |  | 1.4453 | 1.0974 |  | 25.1667 | 0.00088749 | 1321 | 0.053073 | 8250 | 4.7101e-05 | 4749
BRITTON 1111CB | BRITTON 1111 | 83611111 |  | 1.2715 | 0.23365 |  | 25.8333 | 0.00088744 | 1322 | 0.053073 | 8252 | 4.7099e-05 | 4750
SANTA ROSA A 111098988 | SANTA ROSA A 1110 | 42151110 |  | 2.5313 | 2.0457 |  | 34.3333 | 0.00086777 | 1438 | 0.05439 | 7867 | 4.7082e-05 | 4751
RICHMOND R 1124459242 | RICHMOND R 1124 | 13471124 |  | 1.0751 | 0.79627 |  | 14.8333 | 0.00088682 | 1327 | 0.053073 | 8251 | 4.7066e-05 | 4752
GRANT 1102CB | GRANT 1102 | 14381102 |  | 4.7079 | 1.1671 |  | 74.8333 | 0.00086371 | 1465 | 0.054916 | 7762 | 4.7061e-05 | 4753
TULUCAY 1101926496 | TULUCAY 1101 | 42301101 |  | 0.73027 | 0.16671 |  | 11.5 | 0.00066716 | 3466 | 0.069953 | 5055 | 4.7054e-05 | 4754
COTATI 11025080 | COTATI 1102 | 42271102 |  | 0.015625 | 0 |  | 0.5 | 0.00070191 | 3077 | 0.067 | 6057 | 4.7028e-05 | 4755
PIERCY 2109XR376 | PIERCY 2109 | 83912109 |  | 0.73761 | 1.0004 |  | 10 | 0.00088605 | 1329 | 0.053073 | 8251 | 4.7025e-05 | 4756
GILL 0401CB | GILL 0401 | 13550401 |  | 3.2486 | 3.7013 |  | 48.0833 | 0.00088585 | 1331 | 0.053073 | 8251 | 4.7014e-05 | 4757
TEVIS 2103CB | TEVIS 2103 | 255322103 |  | 3.2845 | 0 |  | 45.5 | 0.00072082 | 2843 | 0.066974 | 6072 | 4.7009e-05 | 4758
EL PATIO 1116CB | EL PATIO 1116 | 82921116 |  | 0.68094 | 0.39213 |  | 13.8333 | 0.0008857 | 1332 | 0.053073 | 8251 | 4.7006e-05 | 4759
PLACER 1104426944 | PLACER 1104 | 152461104 |  | 1.5386 | 0.5801 |  | 26 | 0.00070151 | 3080 | 0.067 | 6057 | 4.7001e-05 | 4760
BAY MEADOWS 110447476 | BAY MEADOWS 1104 | 24011104 |  | 0.71566 | 0.44917 |  | 5.5 | 0.00088554 | 1333 | 0.053073 | 8251 | 4.6998e-05 | 4761
HARTLEY 1102524 | HARTLEY 1102 | 43211102 | TRUE | 4.1955 | 0.1762 | 0.0028739 | 74 | 0.00020995 | 9875 | 0.30354 | 3017 | 4.6992e-05 | 4762
HUNTERS POINT (P) 110612531 | HUNTERS POINT (P) 1106 | 22331106 |  | 1.116 | 0.75946 |  | 19.8667 | 0.00088541 | 1334 | 0.053073 | 8252 | 4.6991e-05 | 4763
MONROE 210290988 | MONROE 2102 | 43302102 |  | 1.37 | 0.37996 |  | 22.3333 | 0.00079764 | 1987 | 0.060638 | 6940 | 4.6978e-05 | 4764
CHANNEL 1101CB | CHANNEL 1101 | 163071101 |  | 6.4511 | 3.5297 |  | 91.8333 | 0.00088436 | 1342 | 0.05312 | 8243 | 4.6978e-05 | 4765
FULTON 1101CB | FULTON 1101 | 42561101 |  | 5.2189 | 0.34505 |  | 60.75 | 0.0007447 | 2554 | 0.062432 | 6724 | 4.6944e-05 | 4766
OAKLAND X 1105CB | OAKLAND X 1105 | 12541105 | FALSE | 11.5886 | 11.3702 | 1.7248 | 154.3333 | 0.00060715 | 4211 | 0.098201 | 3320 | 4.6937e-05 | 4767
BAKERSFIELD 210616874 | BAKERSFIELD 2106 | 253372106 |  | 0.69782 | 1.0874 |  | 11.3333 | 0.0008843 | 1343 | 0.053073 | 8250 | 4.6932e-05 | 4768
TRIMBLE 1107CB | TRIMBLE 1107 | 83801107 |  | 1.0457 | 0.17087 |  | 23.1667 | 0.00086277 | 1476 | 0.054075 | 7938 | 4.6929e-05 | 4769
STOCKTON A 110737868 | STOCKTON A 1107 | 162371107 |  | 3.529 | 1.2208 |  | 55.8333 | 0.00083663 | 1668 | 0.056558 | 7498 | 4.6916e-05 | 4770
AIRWAYS 110365600 | AIRWAYS 1103 | 252041103 |  | 1.0888 | 0.5188 |  | 13.8333 | 0.00088393 | 1344 | 0.053073 | 8250 | 4.6912e-05 | 4771
COPPERMINE 2110CB | COPPERMINE 2110 | 252412110 |  | 0.002841 | 0 |  | 0.25 | 0.00069999 | 3099 | 0.067 | 6057 | 4.69e-05 | 4772
IGNACIO 11011779 | IGNACIO 1101 | 42481101 | TRUE | 0.42162 | 0.19415 | 0.46714 | 6.5 | 0.00069878 | 3117 | 0.067105 | 5893 | 4.6892e-05 | 4773
MERCED 2101CB | MERCED 2101 | 252802101 |  | 9.8247 | 6.0953 |  | 155.8333 | 0.00087818 | 1376 | 0.053436 | 8113 | 4.6892e-05 | 4774
RICHMOND R 1130CB | RICHMOND R 1130 | 13471130 |  | 3.3336 | 2.103 |  | 36.0833 | 0.00088349 | 1346 | 0.053073 | 8250 | 4.6889e-05 | 4775
NORD 1103CB | NORD 1103 | 103071103 |  | 5.6053 | 1.9774 |  | 114.8333 | 0.00073838 | 2628 | 0.064867 | 6455 | 4.6885e-05 | 4776
LLAGAS 2105CB | LLAGAS 2105 | 83182105 |  | 3.5044 | 2.3743 |  | 49.3333 | 0.00087162 | 1412 | 0.053167 | 8227 | 4.6877e-05 | 4777
CLAYTON 2212523764 | CLAYTON 2212 | 12022212 | TRUE | 0.34437 | 0 | 0.024911 | 4.5 | 0.00076567 | 2317 | 0.058479 | 7222 | 4.6877e-05 | 4778
BAHIA 1103CB | BAHIA 1103 | 43251103 |  | 2.8553 | 0.56799 |  | 54 | 0.00081016 | 1894 | 0.059538 | 7081 | 4.687e-05 | 4779
POTRERO PP (A) 1107CB | POTRERO PP (A) 1107 | 22031107 |  | 0.89619 | 0.73495 |  | 9.3333 | 0.00088296 | 1348 | 0.053073 | 8250 | 4.6861e-05 | 4780
ESTUDILLO 0401CB | ESTUDILLO 0401 | 13480401 |  | 3.1601 | 4.0013 |  | 43.8333 | 0.00061446 | 4111 | 0.070866 | 4907 | 4.6859e-05 | 4781
MAGUNDEN 11064176 | MAGUNDEN 1106 | 252771106 |  | 8.6319 | 7.695 |  | 128.5 | 0.00088286 | 1350 | 0.053073 | 8251 | 4.6856e-05 | 4782
VIRGINIA 0401CB | VIRGINIA 0401 | 13780401 |  | 3.0473 | 3.6009 |  | 26.95 | 0.00088266 | 1352 | 0.053073 | 8249 | 4.6845e-05 | 4783
BAY MEADOWS 1107CB | BAY MEADOWS 1107 | 24011107 |  | 1.582 | 0.73838 |  | 23.3333 | 0.0008826 | 1353 | 0.053073 | 8251 | 4.6842e-05 | 4784
SAN JOSE B 1112CB | SAN JOSE B 1112 | 82261112 |  | 5.6995 | 4.6383 |  | 99.8333 | 0.00088233 | 1354 | 0.053073 | 8250 | 4.6827e-05 | 4785
OCEANO 1106V28 | OCEANO 1106 | 182601106 | FALSE | 8.8912 | 2.9622 | 1.2448 | 166.5 | 0.00033713 | 7346 | 0.22425 | 3111 | 4.6827e-05 | 4786
SALMON CREEK 1101676 | SALMON CREEK 1101 | 43161101 |  | 0.012806 | 0 |  | 0.5 | 0.0006899 | 3219 | 0.067874 | 5450 | 4.6826e-05 | 4787
FRANKLIN 1102P120 | FRANKLIN 1102 | 13921102 |  | 0.014323 | 0 |  | 0.5 | 0.00069875 | 3118 | 0.067 | 6057 | 4.6817e-05 | 4788
LINCOLN 1101744292 | LINCOLN 1101 | 153701101 |  | 0.34678 | 0.083463 |  | 9 | 0.00082185 | 1802 | 0.056168 | 7553 | 4.6784e-05 | 4789
SAN JOSE B 110897260 | SAN JOSE B 1108 | 82261108 |  | 2.0574 | 1.0964 |  | 31.3333 | 0.00088149 | 1356 | 0.053073 | 8251 | 4.6783e-05 | 4790
LAKEWOOD 222475242 | LAKEWOOD 2224 | 13532224 |  | 2.3997 | 1.9387 |  | 44.5 | 0.00073617 | 2666 | 0.063963 | 6548 | 4.6775e-05 | 4791
DAVIS 1105130744 | DAVIS 1105 | 62041105 |  | 4.5352 | 2.704 |  | 63.5 | 0.00088093 | 1359 | 0.053073 | 8251 | 4.6753e-05 | 4792
STOCKTON ACRES 0402CB | STOCKTON ACRES 0402 | 163220402 |  | 2.9989 | 3.6739 |  | 45 | 0.00088091 | 1361 | 0.053073 | 8251 | 4.6752e-05 | 4793
CHANNEL 110148608 | CHANNEL 1101 | 163071101 |  | 0.0087561 | 0 |  | 0.5 | 0.00088084 | 1362 | 0.053073 | 8251 | 4.6749e-05 | 4794
SANTA ROSA A 111265702 | SANTA ROSA A 1112 | 42151112 |  | 3.4826 | 3.0686 |  | 51 | 0.00084552 | 1608 | 0.055394 | 7688 | 4.6734e-05 | 4795
ROSEDALE 1101CB | ROSEDALE 1101 | 254761101 |  | 8.6465 | 0.73413 |  | 112.0833 | 0.00083114 | 1721 | 0.057342 | 7389 | 4.6725e-05 | 4796
MORGAN HILL 2109CB | MORGAN HILL 2109 | 83242109 |  | 2.2498 | 0.5352 |  | 38.5 | 0.00082274 | 1796 | 0.058094 | 7278 | 4.6725e-05 | 4797
NAPA 1103CB | NAPA 1103 | 42021103 |  | 9.4553 | 6.8045 |  | 144.7833 | 0.00085003 | 1574 | 0.055228 | 7716 | 4.6725e-05 | 4798
EMBARCADERO (Z) 1122CB | EMBARCADERO (Z) 1122 | 22871122 |  | 0.0089576 | 0 |  | 0.83333 | 0.00088013 | 1363 | 0.053073 | 8250 | 4.6711e-05 | 4799
SARATOGA 1112CB | SARATOGA 1112 | 83371112 |  | 4.6399 | 3.2164 |  | 73 | 0.00079511 | 2010 | 0.059273 | 7114 | 4.671e-05 | 4800
CHANNEL 110111824 | CHANNEL 1101 | 163071101 |  | 1.0863 | 0.56547 |  | 16.6667 | 0.00088004 | 1364 | 0.053073 | 8250 | 4.6706e-05 | 4801
BARTON 111094098 | BARTON 1110 | 253571110 |  | 10.4121 | 14.4486 |  | 189.6667 | 0.00087994 | 1366 | 0.053073 | 8252 | 4.6701e-05 | 4802
OAKLAND X 1110CB | OAKLAND X 1110 | 12541110 |  | 0.43337 | 0 |  | 4.9167 | 0.00087987 | 1367 | 0.053073 | 8251 | 4.6697e-05 | 4803
HUNTERS POINT (P) 1108993640 | HUNTERS POINT (P) 1108 | 22331108 |  | 0.054314 | 0.07303 |  | 0.58333 | 0.00087976 | 1368 | 0.053073 | 8250 | 4.6691e-05 | 4804
LAKEWOOD 22258748 | LAKEWOOD 2225 | 13532225 |  | 0.2599 | 0.04751 |  | 5.5 | 0.00087964 | 1370 | 0.053073 | 8251 | 4.6685e-05 | 4805
MILLBRAE 1105CB | MILLBRAE 1105 | 22691105 |  | 0.26345 | 0.034974 |  | 5.5 | 0.00069611 | 3149 | 0.067076 | 5922 | 4.6681e-05 | 4806
ECHO SUMMIT 11018922 | ECHO SUMMIT 1101 | 158031101 | FALSE | 1.1795 | 0.86894 | 2.0484 | 22 | 3.755e-05 | 11136 | 1.2473 | 2061 | 4.6677e-05 | 4807
ROSSMOOR 1104CB | ROSSMOOR 1104 | 14161104 |  | 11.0383 | 6.0374 |  | 169.6429 | 0.00069578 | 3153 | 0.06697 | 6073 | 4.6673e-05 | 4808
SAN JOSE B 1113CB | SAN JOSE B 1113 | 82261113 |  | 0.10098 | 0 |  | 2.5 | 0.0008794 | 1371 | 0.053073 | 8251 | 4.6672e-05 | 4809
WAHTOKE 1106CB | WAHTOKE 1106 | 254531106 |  | 13.9604 | 12.6332 |  | 243.5 | 0.0008618 | 1486 | 0.055569 | 7663 | 4.6655e-05 | 4810
PUEBLO 1103CB | PUEBLO 1103 | 43291103 |  | 1.3781 | 0.38743 |  | 26.6667 | 0.00075482 | 2437 | 0.062666 | 6696 | 4.6641e-05 | 4811
EDES 1101CR148 | EDES 1101 | 13681101 |  | 3.936 | 2.6579 |  | 48 | 0.00087876 | 1373 | 0.053073 | 8252 | 4.6638e-05 | 4812
SUISUN 1102CB | SUISUN 1102 | 62131102 |  | 5.282 | 5.2747 |  | 76.25 | 0.00087185 | 1410 | 0.053398 | 8138 | 4.6638e-05 | 4813
NAPA 11021360 | NAPA 1102 | 42021102 |  | 4.7902 | 4.3253 |  | 79 | 0.00087309 | 1402 | 0.053689 | 8035 | 4.6637e-05 | 4814
MT EDEN 1107MR138 | MT EDEN 1107 | 13761107 |  | 3.3322 | 0.78767 |  | 57 | 0.00087838 | 1374 | 0.053073 | 8251 | 4.6618e-05 | 4815
WESTPARK 110874556 | WESTPARK 1108 | 253701108 |  | 2.6082 | 2.9359 |  | 35.1667 | 0.00087805 | 1377 | 0.053073 | 8250 | 4.66e-05 | 4816
FIGARDEN 211275770 | FIGARDEN 2112 | 254552112 |  | 1.1565 | 0.50548 |  | 24 | 0.00082007 | 1818 | 0.058858 | 7176 | 4.6593e-05 | 4817
TRIMBLE 2118CB | TRIMBLE 2118 | 83802118 |  | 0.93146 | 0.04139 |  | 19.5 | 0.0008777 | 1379 | 0.053073 | 8251 | 4.6582e-05 | 4818
SOLEDAD 21027646 | SOLEDAD 2102 | 182052102 |  | 1.5788 | 0.27313 |  | 35 | 0.00069522 | 3157 | 0.067 | 6057 | 4.658e-05 | 4819
OCEANO 1103V22 | OCEANO 1103 | 182601103 | TRUE | 0.44791 | 0 | 0.031374 | 10 | 0.00029336 | 8143 | 0.15976 | 3194 | 4.6572e-05 | 4820
SANTA NELLA 110111370 | SANTA NELLA 1101 | 254051101 |  | 0.036129 | 0 |  | 0.75 | 0.00060161 | 4281 | 0.0774 | 3397 | 4.6564e-05 | 4821
TIDEWATER 210978302 | TIDEWATER 2109 | 14652109 |  | 9.456 | 7.9426 |  | 145.1667 | 0.0008772 | 1380 | 0.053073 | 8251 | 4.6555e-05 | 4822
ALMADEN 111149970 | ALMADEN 1111 | 82311111 |  | 0.98601 | 0.012046 |  | 19.5 | 0.0008771 | 1381 | 0.053073 | 8251 | 4.655e-05 | 4823
WHITNEY 0402CB | WHITNEY 0402 | 13240402 |  | 1.7946 | 1.5944 |  | 27 | 0.00086223 | 1482 | 0.054365 | 7874 | 4.6549e-05 | 4824
WEBER 11099316 | WEBER 1109 | 163481109 |  | 0.011364 | 0 |  | 0.5 | 0.00087692 | 1382 | 0.053073 | 8251 | 4.654e-05 | 4825
LAKEWOOD 1104CB | LAKEWOOD 1104 | 13531104 |  | 1.2239 | 0.5003 |  | 19.5333 | 0.0008732 | 1401 | 0.054023 | 7946 | 4.6523e-05 | 4826
BAY MEADOWS 2101410526 | BAY MEADOWS 2101 | 24012101 |  | 9.4787 | 7.1582 |  | 121.3667 | 0.00086131 | 1490 | 0.053975 | 7962 | 4.6517e-05 | 4827
HUNTERS POINT (P) 110775148 | HUNTERS POINT (P) 1107 | 22331107 |  | 0.49186 | 0.52936 |  | 4.8333 | 0.00087645 | 1385 | 0.053073 | 8251 | 4.6516e-05 | 4828
EL PATIO 1109CB | EL PATIO 1109 | 82921109 |  | 1.0656 | 0.93183 |  | 11.8333 | 0.00087645 | 1386 | 0.053073 | 8250 | 4.6515e-05 | 4829
OAKLAND L 1101829806 | OAKLAND L 1101 | 12111101 |  | 0.099736 | 0.04649 |  | 1.1667 | 0.00087631 | 1387 | 0.053073 | 8250 | 4.6508e-05 | 4830
TIDEWATER 2104CB | TIDEWATER 2104 | 14652104 |  | 8.5061 | 5.2055 |  | 130.5 | 0.00082953 | 1740 | 0.055819 | 7612 | 4.6502e-05 | 4831
BOGUE 11027020 | BOGUE 1102 | 153781102 |  | 8.7078 | 4.0907 |  | 114.3333 | 0.00087618 | 1388 | 0.053073 | 8252 | 4.6501e-05 | 4832
VACAVILLE 110569806 | VACAVILLE 1105 | 63601105 |  | 0.91677 | 0.88456 |  | 10.6667 | 0.00087558 | 1389 | 0.053073 | 8251 | 4.6469e-05 | 4833
LAKEVILLE 1102367100 | LAKEVILLE 1102 | 43371102 | TRUE | 0.69673 | 0.018369 | 0.10233 | 14.5 | 0.00027074 | 8635 | 0.2222 | 3115 | 4.6469e-05 | 4834
EAST STOCKTON 1101530016 | EAST STOCKTON 1101 | 163131101 |  | 5.1826 | 2.9376 |  | 74.8333 | 0.00087556 | 1390 | 0.053073 | 8252 | 4.6468e-05 | 4835
OAKLAND C 1121829656 | OAKLAND C 1121 | 12011121 |  | 0.16898 | 0.16294 |  | 2.1667 | 0.00087532 | 1391 | 0.053073 | 8250 | 4.6456e-05 | 4836
WAHTOKE 1109CB | WAHTOKE 1109 | 254531109 |  | 3.8313 | 1.2088 |  | 48.6667 | 0.00083711 | 1664 | 0.055842 | 7606 | 4.6455e-05 | 4837
STOCKTON ACRES 0401CB | STOCKTON ACRES 0401 | 163220401 |  | 2.3727 | 2.5745 |  | 32 | 0.00087525 | 1392 | 0.053073 | 8251 | 4.6452e-05 | 4838
BURLINGAME 2101A80 | BURLINGAME 2101 | 24052101 |  | 3.3921 | 3.7558 |  | 48.9167 | 0.00083036 | 1730 | 0.056299 | 7531 | 4.6449e-05 | 4839
PUEBLO 1102662 | PUEBLO 1102 | 43291102 |  | 1.1338 | 0.78354 |  | 17.3333 | 0.0008749 | 1394 | 0.053073 | 8252 | 4.6433e-05 | 4840
NOTRE DAME 1103CB | NOTRE DAME 1103 | 102041103 |  | 2.4615 | 0.0048366 |  | 43 | 0.00071055 | 2968 | 0.066028 | 6266 | 4.6413e-05 | 4841
WEEDPATCH 110217701 | WEEDPATCH 1102 | 252971102 |  | 0.87551 | 0.55371 |  | 16 | 0.0006977 | 3136 | 0.065836 | 6297 | 4.64e-05 | 4842
BARTON 1111CB | BARTON 1111 | 253571111 |  | 8.9706 | 8.1702 |  | 143.6667 | 0.00087387 | 1397 | 0.053073 | 8250 | 4.6379e-05 | 4843
LAS GALLINAS A 1107CB | LAS GALLINAS A 1107 | 42991107 |  | 3.0762 | 1.1869 |  | 48 | 0.00079268 | 2036 | 0.059021 | 7157 | 4.6378e-05 | 4844
SANTA ROSA A 1110CB | SANTA ROSA A 1110 | 42151110 |  | 10.4408 | 9.6482 |  | 150 | 0.00081281 | 1873 | 0.057107 | 7423 | 4.6373e-05 | 4845
PUEBLO 110298730 | PUEBLO 1102 | 43291102 |  | 0.35899 | 0.041766 |  | 5.3333 | 0.0008736 | 1398 | 0.053073 | 8252 | 4.6364e-05 | 4846
WEBER 111113724 | WEBER 1111 | 163481111 |  | 0.0028409 | 0 |  | 0.5 | 0.00087345 | 1399 | 0.053073 | 8251 | 4.6356e-05 | 4847
PLEASANT GROVE 2103CB | PLEASANT GROVE 2103 | 152442103 |  | 1.8847 | 0.023447 |  | 19.8333 | 0.00069182 | 3194 | 0.067 | 6058 | 4.6352e-05 | 4848
NORD 11063307 | NORD 1106 | 103071106 |  | 0.84803 | 0.33143 |  | 18.5 | 0.00083338 | 1698 | 0.054955 | 7756 | 4.6351e-05 | 4849
SWIFT 2102XR440 | SWIFT 2102 | 83392102 |  | 0.66274 | 0.13632 |  | 16.5 | 0.00071042 | 2971 | 0.064468 | 6490 | 4.6341e-05 | 4850
NAPA 1105CB | NAPA 1105 | 42021105 |  | 9.5278 | 7.2602 |  | 160.2833 | 0.00084255 | 1630 | 0.055071 | 7739 | 4.634e-05 | 4851
CAROLANDS 04018506 | CAROLANDS 0401 | 24060401 |  | 2.831 | 2.5156 |  | 50.5 | 0.00073814 | 2633 | 0.063277 | 6631 | 4.6329e-05 | 4852
SF H 1101CB | SF H 1101 | 22101101 |  | 2.1068 | 1.4047 |  | 23.825 | 0.00085182 | 1564 | 0.054094 | 7931 | 4.6299e-05 | 4853
FIGARDEN 210384860 | FIGARDEN 2103 | 254552103 |  | 2.7625 | 0.030796 |  | 42 | 0.00074209 | 2581 | 0.063703 | 6578 | 4.629e-05 | 4854
MOSHER 210738444 | MOSHER 2107 | 163722107 |  | 0.48587 | 0 |  | 6.5 | 0.00087215 | 1406 | 0.053073 | 8251 | 4.6287e-05 | 4855
WHISMAN 1104CB | WHISMAN 1104 | 83631104 |  | 0.0028632 | 0 |  | 0.5 | 0.00087192 | 1409 | 0.053073 | 8251 | 4.6275e-05 | 4856
BELLE HAVEN 1101CB | BELLE HAVEN 1101 | 24021101 |  | 0.91091 | 0 |  | 7.1667 | 0.00086298 | 1472 | 0.053559 | 8081 | 4.6267e-05 | 4857
SF H 110612123 | SF H 1106 | 22101106 |  | 2.3915 | 3.1518 |  | 36.4167 | 0.00087167 | 1411 | 0.053073 | 8251 | 4.6262e-05 | 4858
MENLO 11029152 | MENLO 1102 | 24131102 |  | 2.1718 | 1.2028 |  | 37 | 0.00067322 | 3397 | 0.068713 | 5240 | 4.6259e-05 | 4859
BARTON 1115CB | BARTON 1115 | 253571115 |  | 5.1186 | 4.3909 |  | 79.0833 | 0.00086424 | 1462 | 0.053588 | 8066 | 4.6248e-05 | 4860
POTRERO PP (A) 1103CB | POTRERO PP (A) 1103 | 22031103 |  | 0.98796 | 0.37459 |  | 14 | 0.00087133 | 1413 | 0.053073 | 8251 | 4.6244e-05 | 4861
LIVERMORE 1103CB | LIVERMORE 1103 | 12141103 |  | 0.70603 | 0.57546 |  | 10.3333 | 0.0008711 | 1415 | 0.053073 | 8250 | 4.6232e-05 | 4862
HAMMER 1109CB | HAMMER 1109 | 163301109 |  | 3.8343 | 4.5707 |  | 57.5 | 0.00085733 | 1515 | 0.053707 | 8026 | 4.6231e-05 | 4863
RICHMOND R 1120CB | RICHMOND R 1120 | 13471120 |  | 2.9576 | 0.67891 |  | 39.45 | 0.00087097 | 1416 | 0.053073 | 8250 | 4.6225e-05 | 4864
VIERRA 170313694 | VIERRA 1703 | 162701703 |  | 0.083635 | 0 |  | 3 | 0.00059713 | 4339 | 0.0774 | 3397 | 4.6218e-05 | 4865
DEL MAR 210551694 | DEL MAR 2105 | 152582105 |  | 2.6809 | 1.9487 |  | 41.5 | 0.0007466 | 2526 | 0.062469 | 6721 | 4.6206e-05 | 4866
PINEDALE 2109CB | PINEDALE 2109 | 252852109 |  | 0.27158 | 0.45291 |  | 14.1667 | 0.00087044 | 1417 | 0.053073 | 8251 | 4.6197e-05 | 4867
DAVIS 110520567 | DAVIS 1105 | 62041105 |  | 0.45964 | 0.35183 |  | 8 | 0.0008704 | 1418 | 0.053073 | 8251 | 4.6195e-05 | 4868
PAUL SWEET 210712222 | PAUL SWEET 2107 | 83252107 |  | 0.0029581 | 0 |  | 0.33333 | 0.00087035 | 1420 | 0.053073 | 8251 | 4.6192e-05 | 4869
BASALT 1105CB | BASALT 1105 | 42461105 |  | 1.6501 | 0 |  | 23.3333 | 0.00072567 | 2783 | 0.064141 | 6526 | 4.6184e-05 | 4870
WEST SACRAMENTO 111022412 | WEST SACRAMENTO 1110 | 63131110 |  | 0.81815 | 0.17323 |  | 15.5 | 0.00087005 | 1421 | 0.053073 | 8251 | 4.6176e-05 | 4871
SARATOGA 1105CB | SARATOGA 1105 | 83371105 |  | 4.9712 | 2.9546 |  | 73.5 | 0.00083845 | 1659 | 0.054873 | 7775 | 4.6165e-05 | 4872
JARVIS 1104CB | JARVIS 1104 | 13501104 |  | 3.5028 | 1.0742 |  | 35.0833 | 0.00086161 | 1488 | 0.053867 | 7983 | 4.6162e-05 | 4873
PEABODY 210769886 | PEABODY 2107 | 63642107 |  | 0.48297 | 0.062907 |  | 7.5 | 0.00068699 | 3257 | 0.067189 | 5822 | 4.6155e-05 | 4874
SF G 0401CB | SF G 0401 | 22090401 |  | 0.67422 | 0.35104 |  | 6 | 0.00086956 | 1425 | 0.053073 | 8251 | 4.615e-05 | 4875
WOODSIDE 11049016 | WOODSIDE 1104 | 24251104 |  | 4.499 | 0.96371 |  | 93.5 | 0.0006877 | 3251 | 0.067104 | 5895 | 4.6149e-05 | 4876
SARATOGA 1111CB | SARATOGA 1111 | 83371111 |  | 9.0575 | 9.8173 |  | 127.5 | 0.00079461 | 2014 | 0.057733 | 7332 | 4.6149e-05 | 4877
MOLINO 1102535 | MOLINO 1102 | 42571102 |  | 0.99959 | 0.29835 |  | 20.5 | 0.00068873 | 3233 | 0.067 | 6057 | 4.6145e-05 | 4878
SAN RAFAEL 1102480 | SAN RAFAEL 1102 | 42011102 |  | 0.24623 | 0.13353 |  | 4.3333 | 0.00086936 | 1426 | 0.053073 | 8252 | 4.6139e-05 | 4879
WEST SACRAMENTO 1108CB | WEST SACRAMENTO 1108 | 63131108 |  | 4.2704 | 4.2736 |  | 76.0333 | 0.00086933 | 1427 | 0.053073 | 8250 | 4.6138e-05 | 4880
SNEATH LANE 110210287 | SNEATH LANE 1102 | 22721102 |  | 4.5692 | 3.9707 |  | 65.3333 | 0.00078556 | 2096 | 0.058561 | 7215 | 4.6132e-05 | 4881
OAKLAND C 1121CB | OAKLAND C 1121 | 12011121 |  | 1.7406 | 1.7613 |  | 24 | 0.000869 | 1430 | 0.053073 | 8251 | 4.612e-05 | 4882
SYCAMORE CREEK 11051763 | SYCAMORE CREEK 1105 | 102971105 |  | 0.62748 | 0.43395 |  | 13 | 0.00081933 | 1826 | 0.057894 | 7309 | 4.6117e-05 | 4883
MISSION (X) 1118CB | MISSION (X) 1118 | 22011118 |  | 0.60135 | 0.10858 |  | 6.3333 | 0.00086888 | 1432 | 0.053073 | 8250 | 4.6114e-05 | 4884
VACA DIXON 110531546 | VACA DIXON 1105 | 63591105 |  | 0.053682 | 0 |  | 0.5 | 0.00059568 | 4352 | 0.0774 | 3397 | 4.6106e-05 | 4885
STAGG 1105CB | STAGG 1105 | 162421105 |  | 8.702 | 8.0346 |  | 125.8333 | 0.00086289 | 1475 | 0.053414 | 8125 | 4.6104e-05 | 4886
STOREY 1106315398 | STOREY 1106 | 254611106 |  | 2.6225 | 0.45694 |  | 46.6667 | 0.00078105 | 2139 | 0.05985 | 7034 | 4.6101e-05 | 4887
NAPA 1109CB | NAPA 1109 | 42021109 |  | 5.6486 | 4.1003 |  | 89.3333 | 0.00086852 | 1433 | 0.053073 | 8251 | 4.6095e-05 | 4888
TRACY 1109CB | TRACY 1109 | 162881109 |  | 6.1682 | 1.2432 |  | 98.0833 | 0.0007915 | 2050 | 0.060535 | 6952 | 4.607e-05 | 4889
NEWHALL 1109CUS5328 | NEWHALL 1109 | 254461109 |  | 0.0074595 | 0 |  | 0.5 | 0.00059518 | 4360 | 0.0774 | 3397 | 4.6066e-05 | 4890
EL PATIO 1104XR096 | EL PATIO 1104 | 82921104 |  | 0.58652 | 0.28466 |  | 7.1667 | 0.0008678 | 1437 | 0.053073 | 8250 | 4.6057e-05 | 4891
EVERGREEN 2104XR150 | EVERGREEN 2104 | 82012104 |  | 1.4845 | 0.035123 |  | 28.1667 | 0.00074358 | 2572 | 0.062962 | 6665 | 4.6043e-05 | 4892
OAK PARK 0401CB | OAK PARK 0401 | 163270401 |  | 2.475 | 2.7948 |  | 35.5 | 0.00086754 | 1439 | 0.053073 | 8251 | 4.6043e-05 | 4893
MANTECA 170866580 | MANTECA 1708 | 162611708 |  | 1.8935 | 0.28326 |  | 31.3333 | 0.00077126 | 2247 | 0.059947 | 7027 | 4.6037e-05 | 4894
CALIFORNIA AVE 1102CB | CALIFORNIA AVE 1102 | 252281102 |  | 11.5086 | 2.8423 |  | 187.1667 | 0.00079357 | 2022 | 0.062328 | 6732 | 4.6019e-05 | 4895
WEST SACRAMENTO 1105CB | WEST SACRAMENTO 1105 | 63131105 |  | 6.3059 | 2.6962 |  | 100.5333 | 0.00085379 | 1548 | 0.054083 | 7936 | 4.6012e-05 | 4896
OAKLAND J 1101CB | OAKLAND J 1101 | 12091101 |  | 2.7759 | 2.3076 |  | 36.1667 | 0.00086685 | 1443 | 0.053073 | 8250 | 4.6006e-05 | 4897
SAN JOSE A 1112XR066 | SAN JOSE A 1112 | 82251112 |  | 3.5284 | 3.7808 |  | 53.8333 | 0.00083502 | 1683 | 0.055789 | 7620 | 4.6003e-05 | 4898
LARKIN (Y) 1138CB | LARKIN (Y) 1138 | 22801138 |  | 0.89836 | 0.47993 |  | 7.3333 | 0.00086654 | 1446 | 0.053073 | 8250 | 4.5989e-05 | 4899
SHARON 1101CB | SHARON 1101 | 255331101 |  | 0.01411 | 0 |  | 0.33333 | 0.00059417 | 4369 | 0.0774 | 3396 | 4.5988e-05 | 4900
SYCAMORE CREEK 1110CB | SYCAMORE CREEK 1110 | 102971110 |  | 7.6424 | 4.527 |  | 135.8333 | 0.00085898 | 1501 | 0.053568 | 8076 | 4.5988e-05 | 4901
SAN CARLOS 1101CB | SAN CARLOS 1101 | 24181101 |  | 1.4639 | 0.68259 |  | 16.0929 | 0.00086644 | 1447 | 0.053073 | 8251 | 4.5984e-05 | 4902
VIEJO 2204746866 | VIEJO 2204 | 182852204 |  | 1.5332 | 1.0596 |  | 28.8333 | 0.0006876 | 3255 | 0.067052 | 5945 | 4.5981e-05 | 4903
HOLLISTER 2102113634 | HOLLISTER 2102 | 182492102 | FALSE | 8.7817 | 0.51333 | 1.5892 | 167 | 0.0001941 | 10144 | 0.33183 | 2981 | 4.5978e-05 | 4904
MILLBRAE 040479782 | MILLBRAE 0404 | 22690404 |  | 2.098 | 1.4513 |  | 22.4167 | 0.00084569 | 1606 | 0.054212 | 7899 | 4.5971e-05 | 4905
HAMMER 110414704 | HAMMER 1104 | 163301104 |  | 6.8657 | 8.4586 |  | 101.6667 | 0.00086592 | 1450 | 0.053073 | 8250 | 4.5957e-05 | 4906
SF E 1107CB | SF E 1107 | 22071107 |  | 0.42146 | 0.38667 |  | 7.3333 | 0.00086586 | 1451 | 0.053073 | 8251 | 4.5953e-05 | 4907
SYCAMORE CREEK 11022536 | SYCAMORE CREEK 1102 | 102971102 |  | 1.0698 | 0.61959 |  | 21 | 0.00086558 | 1453 | 0.053073 | 8251 | 4.5939e-05 | 4908
TRACY 0405CB | TRACY 0405 | 162880405 |  | 3.2187 | 2.8467 |  | 36.8667 | 0.00086506 | 1454 | 0.053073 | 8251 | 4.5911e-05 | 4909
OAKLAND J 1103CB | OAKLAND J 1103 | 12091103 |  | 1.9509 | 0.21699 |  | 22.6667 | 0.00084251 | 1633 | 0.054101 | 7929 | 4.5909e-05 | 4910
FORT ORD 210779670 | FORT ORD 2107 | 182402107 |  | 5.0668 | 3.6011 |  | 81.8333 | 0.00080713 | 1918 | 0.05805 | 7284 | 4.5905e-05 | 4911
STONE 1101CB | STONE 1101 | 83701101 |  | 1.1717 | 0.23433 |  | 18.8333 | 0.00086494 | 1455 | 0.053073 | 8252 | 4.5905e-05 | 4912
MAGUNDEN 1105878284 | MAGUNDEN 1105 | 252771105 |  | 4.6094 | 4.5226 |  | 66.5 | 0.00086492 | 1456 | 0.053073 | 8251 | 4.5904e-05 | 4913
HAMMER 1104CB | HAMMER 1104 | 163301104 |  | 3.7698 | 4.6636 |  | 54.3333 | 0.0008648 | 1457 | 0.053073 | 8250 | 4.5897e-05 | 4914
SALINAS 110422050 | SALINAS 1104 | 182011104 |  | 2.3213 | 1.4281 |  | 17.9167 | 0.00086469 | 1459 | 0.053073 | 8252 | 4.5892e-05 | 4915
FRUITVALE 1106CB | FRUITVALE 1106 | 253391106 |  | 9.4963 | 6.1608 |  | 166.7 | 0.00086402 | 1464 | 0.053137 | 8236 | 4.5887e-05 | 4916
LAMMERS 110211806 | LAMMERS 1102 | 162771102 |  | 3.35 | 0.35628 |  | 60.5 | 0.00072777 | 2753 | 0.063549 | 6606 | 4.5881e-05 | 4917
WOODLAND 110422652 | WOODLAND 1104 | 62031104 |  | 1.6451 | 1.2024 |  | 30 | 0.00086441 | 1460 | 0.053073 | 8251 | 4.5876e-05 | 4918
STOCKDALE 21114035 | STOCKDALE 2111 | 254072111 |  | 2.8683 | 2.2136 |  | 43 | 0.00085856 | 1508 | 0.053673 | 8041 | 4.5876e-05 | 4919
SAN LEANDRO U 1109CB | SAN LEANDRO U 1109 | 13111109 |  | 3.6515 | 3.5917 |  | 51.3667 | 0.00086437 | 1461 | 0.053073 | 8250 | 4.5874e-05 | 4920
STELLING 111160020 | STELLING 1111 | 83481111 |  | 2.7169 | 1.5579 |  | 45 | 0.00071601 | 2903 | 0.06406 | 6533 | 4.5872e-05 | 4921
VACAVILLE 1107CB | VACAVILLE 1107 | 63601107 |  | 1.9062 | 1.2895 |  | 34.6667 | 0.00085799 | 1512 | 0.054 | 7952 | 4.5863e-05 | 4922
FULTON 1104CB | FULTON 1104 | 42561104 |  | 6.0936 | 1.6902 |  | 107.1667 | 0.000725 | 2791 | 0.063958 | 6550 | 4.5857e-05 | 4923
DALY CITY 11121565 | DALY CITY 1112 | 22641112 |  | 4.4578 | 3.9951 |  | 76 | 0.00070647 | 3024 | 0.065051 | 6425 | 4.5839e-05 | 4924
SUISUN 110418802 | SUISUN 1104 | 62131104 |  | 0.47777 | 0 |  | 6.5 | 0.00086369 | 1466 | 0.053073 | 8251 | 4.5838e-05 | 4925
POINT PINOLE 1103CB | POINT PINOLE 1103 | 14261103 |  | 0.036425 | 0 |  | 1.3333 | 0.00068396 | 3284 | 0.067 | 6056 | 4.5825e-05 | 4926
WOODLAND 1107388804 | WOODLAND 1107 | 62031107 |  | 8.2244 | 7.0009 |  | 128.1667 | 0.00086329 | 1469 | 0.053073 | 8252 | 4.5817e-05 | 4927
REDWOOD CITY 1101CB | REDWOOD CITY 1101 | 24161101 |  | 1.9403 | 0.73557 |  | 27.25 | 0.00086325 | 1470 | 0.053073 | 8250 | 4.5815e-05 | 4928
EAST GRAND 110784276 | EAST GRAND 1107 | 22571107 |  | 1.9831 | 1.9061 |  | 29.5833 | 0.00086323 | 1471 | 0.053073 | 8251 | 4.5814e-05 | 4929
CASTRO VALLEY 1109MR250 | CASTRO VALLEY 1109 | 14091109 |  | 2.0855 | 1.7234 |  | 31.6667 | 0.00083446 | 1688 | 0.054685 | 7809 | 4.5806e-05 | 4930
WEBER 1102CB | WEBER 1102 | 163481102 |  | 2.8047 | 0.4853 |  | 49.25 | 0.00074538 | 2543 | 0.064063 | 6532 | 4.5802e-05 | 4931
STOCKTON A 110442574 | STOCKTON A 1104 | 162371104 |  | 4.9453 | 4.8119 |  | 68.8333 | 0.00086276 | 1477 | 0.053073 | 8252 | 4.5789e-05 | 4932
BUENA VISTA 1102CB | BUENA VISTA 1102 | 182261102 |  | 1.926 | 0.14783 |  | 28.5 | 0.00081005 | 1896 | 0.057158 | 7411 | 4.5786e-05 | 4933
BULLARD 11019527 | BULLARD 1101 | 253961101 |  | 5.1527 | 2.324 |  | 63.6667 | 0.00086263 | 1479 | 0.053073 | 8252 | 4.5782e-05 | 4934
MILPITAS 1106CB | MILPITAS 1106 | 82831106 |  | 3.1395 | 2.5668 |  | 56.5 | 0.00086073 | 1491 | 0.053196 | 8218 | 4.5771e-05 | 4935
GLENWOOD 1102CB | GLENWOOD 1102 | 24091102 |  | 1.2575 | 0.55281 |  | 19.5 | 0.00083148 | 1718 | 0.055453 | 7680 | 4.5767e-05 | 4936
DAIRYLAND 1105306810 | DAIRYLAND 1105 | 252421105 |  | 0.020322 | 0 |  | 0.5 | 0.00059125 | 4399 | 0.0774 | 3397 | 4.5763e-05 | 4937
ASHLAN AVE 1104D10406 | ASHLAN AVE 1104 | 252051104 |  | 0.64669 | 0.22864 |  | 11.4167 | 0.00086226 | 1481 | 0.053073 | 8252 | 4.5762e-05 | 4938
GLENWOOD 0406CB | GLENWOOD 0406 | 24090406 |  | 2.3154 | 1.7579 |  | 35.1667 | 0.00076001 | 2385 | 0.060518 | 6956 | 4.5752e-05 | 4939
PEABODY 210741980 | PEABODY 2107 | 63642107 |  | 1.5172 | 0.31593 |  | 18.5 | 0.00072034 | 2848 | 0.064932 | 6448 | 4.5747e-05 | 4940
MALAGA 1111CB | MALAGA 1111 | 254251111 |  | 8.9216 | 1.1837 |  | 152.5 | 0.00080668 | 1924 | 0.057594 | 7343 | 4.5745e-05 | 4941
CONTRA COSTA 211521471 | CONTRA COSTA 2115 | 13652115 |  | 1.7113 | 1.524 |  | 34.3333 | 0.00077714 | 2183 | 0.058549 | 7217 | 4.5744e-05 | 4942
HUNTERS POINT (P) 1105875780 | HUNTERS POINT (P) 1105 | 22331105 |  | 3.2242 | 3.0164 |  | 42.8333 | 0.00086187 | 1485 | 0.053073 | 8250 | 4.5742e-05 | 4943
PLAINFIELD 110522322 | PLAINFIELD 1105 | 63441105 |  | 0.018466 | 0 |  | 1.5 | 0.00067647 | 3353 | 0.069291 | 5147 | 4.5741e-05 | 4944
MANCHESTER 110133068 | MANCHESTER 1101 | 253921101 |  | 7.7423 | 5.0759 |  | 103.8333 | 0.0008549 | 1540 | 0.053624 | 8054 | 4.5741e-05 | 4945
CHANNEL 110249982 | CHANNEL 1102 | 163071102 |  | 2.7045 | 2.2976 |  | 35.3333 | 0.00086164 | 1487 | 0.053073 | 8250 | 4.5729e-05 | 4946
SYCAMORE CREEK 1103CB | SYCAMORE CREEK 1103 | 102971103 |  | 3.1449 | 1.7406 |  | 55.3333 | 0.00080632 | 1930 | 0.05731 | 7393 | 4.5729e-05 | 4947
SAN RAFAEL 110648752 | SAN RAFAEL 1106 | 42011106 | TRUE | 2.328 | 1.7943 | 0.032837 | 37.3333 | 0.00077766 | 2176 | 0.058731 | 7193 | 4.5727e-05 | 4948
SAN RAMON 2103CB | SAN RAMON 2103 | 14232103 |  | 2.5706 | 1.7165 |  | 46 | 0.00078879 | 2072 | 0.058722 | 7195 | 4.5727e-05 | 4949
SALINAS 110393720 | SALINAS 1103 | 182011103 |  | 0.88014 | 0.7008 |  | 13.8333 | 0.00082181 | 1803 | 0.056093 | 7563 | 4.5725e-05 | 4950
OAKLAND D 1117CB | OAKLAND D 1117 | 12041117 |  | 0.50133 | 0.41599 |  | 9 | 0.0008614 | 1489 | 0.053073 | 8251 | 4.5717e-05 | 4951
CALIFORNIA AVE 1106R651 | CALIFORNIA AVE 1106 | 252281106 |  | 0.7889 | 0.25168 |  | 17 | 0.00072052 | 2847 | 0.063805 | 6568 | 4.5703e-05 | 4952
PACIFIC GROVE 0424CB | PACIFIC GROVE 0424 | 182440424 |  | 2.5396 | 2.7275 |  | 28.0833 | 0.00081761 | 1837 | 0.055737 | 7631 | 4.5692e-05 | 4953
VACAVILLE 1105CB | VACAVILLE 1105 | 63601105 |  | 1.2316 | 1.4065 |  | 19.3333 | 0.00086054 | 1493 | 0.053073 | 8251 | 4.5671e-05 | 4954
SOLEDAD 210435306 | SOLEDAD 2104 | 182052104 |  | 3.2243 | 0.05541 |  | 45.3333 | 0.0007182 | 2875 | 0.074306 | 4512 | 4.5661e-05 | 4955
FORT ORD 2108CB | FORT ORD 2108 | 182402108 |  | 0.90124 | 0.53692 |  | 10.25 | 0.00078178 | 2132 | 0.057036 | 7432 | 4.5639e-05 | 4956
RANCHERS COTTON 110179852 | RANCHERS COTTON 1101 | 254801101 |  | 4.9917 | 4.9479 |  | 78.5 | 0.00085992 | 1496 | 0.053073 | 8251 | 4.5638e-05 | 4957
BARTON 1112CB | BARTON 1112 | 253571112 |  | 2.3666 | 1.8929 |  | 41.5 | 0.00085982 | 1497 | 0.053073 | 8251 | 4.5633e-05 | 4958
AVENAL 210192528 | AVENAL 2101 | 255002101 |  | 0.068449 | 0 |  | 1.5 | 0.00068089 | 3314 | 0.067 | 6057 | 4.562e-05 | 4959
HICKS 2111XR210 | HICKS 2111 | 83432111 |  | 0.81804 | 0.14346 |  | 14 | 0.00085413 | 1546 | 0.053687 | 8036 | 4.562e-05 | 4960
PAUL SWEET 2107CB | PAUL SWEET 2107 | 83252107 |  | 2.5608 | 1.7593 |  | 36.1667 | 0.00084764 | 1592 | 0.053587 | 8068 | 4.5603e-05 | 4961
SF E 1103555674 | SF E 1103 | 22071103 |  | 0.0061497 | 0 |  | 0.5 | 0.00085912 | 1500 | 0.053073 | 8251 | 4.5596e-05 | 4962
SAUSALITO 0402CB | SAUSALITO 0402 | 42490402 |  | 2.9658 | 2.1081 |  | 40.1667 | 0.00070662 | 3021 | 0.065071 | 6422 | 4.5586e-05 | 4963
BALFOUR 11016142 | BALFOUR 1101 | 14321101 |  | 0.8411 | 0.52585 |  | 10 | 0.0008588 | 1505 | 0.053073 | 8251 | 4.5579e-05 | 4964
HUMBOLDT BAY 11027600 | HUMBOLDT BAY 1102 | 192341102 |  | 0.25617 | 0.039309 |  | 4 | 0.00068022 | 3321 | 0.067 | 6057 | 4.5575e-05 | 4965
ASHLAN AVE 1108R3320 | ASHLAN AVE 1108 | 252051108 |  | 1.7917 | 1.7193 |  | 27.6667 | 0.00085871 | 1507 | 0.053073 | 8250 | 4.5574e-05 | 4966
OAKLAND J 111710136 | OAKLAND J 1117 | 12091117 |  | 0.23669 | 0.23014 |  | 3.1667 | 0.00085852 | 1509 | 0.053073 | 8251 | 4.5564e-05 | 4967
MARYSVILLE 1104CB | MARYSVILLE 1104 | 152011104 |  | 5.5591 | 2.476 |  | 62.9167 | 0.00084422 | 1622 | 0.053882 | 7981 | 4.5562e-05 | 4968
SANGER 110437372 | SANGER 1104 | 252351104 |  | 2.6237 | 1.7953 |  | 38.5 | 0.00085822 | 1510 | 0.053073 | 8251 | 4.5548e-05 | 4969
NEWARK 21KV 2104CB | NEWARK 21KV 2104 | 12232104 |  | 2.8758 | 0 |  | 55.75 | 0.00069805 | 3130 | 0.065704 | 6322 | 4.5543e-05 | 4970
EL PATIO 1111CB | EL PATIO 1111 | 82921111 |  | 0.77272 | 0.17275 |  | 10.3333 | 0.00085812 | 1511 | 0.053073 | 8251 | 4.5543e-05 | 4971
LAMMERS 1106CB | LAMMERS 1106 | 162771106 |  | 2.2619 | 0.078139 |  | 44.5 | 0.00072323 | 2812 | 0.063791 | 6569 | 4.5541e-05 | 4972
SAN MATEO 0409CB | SAN MATEO 0409 | 24190409 |  | 3.118 | 2.2714 |  | 30.95 | 0.00084547 | 1609 | 0.053859 | 7986 | 4.5531e-05 | 4973
MAGUNDEN 2108636808 | MAGUNDEN 2108 | 252772108 |  | 0.035791 | 0 |  | 0.5 | 0.00058823 | 4437 | 0.0774 | 3397 | 4.5529e-05 | 4974
SAN JOSE B 1108XR406 | SAN JOSE B 1108 | 82261108 |  | 3.3224 | 1.3793 |  | 51.8333 | 0.00085772 | 1513 | 0.053073 | 8250 | 4.5522e-05 | 4975
ROCKLIN 1102CB | ROCKLIN 1102 | 152061102 |  | 5.5073 | 2.752 |  | 89.8333 | 0.00073283 | 2698 | 0.062176 | 6749 | 4.552e-05 | 4976
WOODSIDE 11029046 | WOODSIDE 1102 | 24251102 |  | 4.8104 | 4.0871 |  | 64.75 | 0.00085464 | 1543 | 0.053198 | 8216 | 4.5516e-05 | 4977
WEBER 1114832888 | WEBER 1114 | 163481114 |  | 2.5268 | 0.7975 |  | 42.5 | 0.00085566 | 1528 | 0.053275 | 8187 | 4.5509e-05 | 4978
DEEPWATER 1109CB | DEEPWATER 1109 | 63621109 |  | 4.1671 | 2.1231 |  | 66.3333 | 0.00075991 | 2386 | 0.060843 | 6906 | 4.5505e-05 | 4979
DEL MONTE 2105109480 | DEL MONTE 2105 | 182222105 |  | 2.1511 | 1.5878 |  | 36.8333 | 0.00081032 | 1893 | 0.056854 | 7459 | 4.5501e-05 | 4980
WESTPARK 110314893 | WESTPARK 1103 | 253701103 |  | 0.84232 | 0.79815 |  | 11.3333 | 0.00085714 | 1517 | 0.053073 | 8250 | 4.5491e-05 | 4981
LARKIN (Y) 1127338022 | LARKIN (Y) 1127 | 22801127 |  | 0.16902 | 0.1728 |  | 1.9167 | 0.00085713 | 1518 | 0.053073 | 8250 | 4.549e-05 | 4982
BARTON 1101899908 | BARTON 1101 | 253571101 |  | 2.1084 | 0.51688 |  | 34.5 | 0.00085709 | 1519 | 0.053073 | 8251 | 4.5488e-05 | 4983
CONTRA COSTA 2104A505R | CONTRA COSTA 2104 | 13652104 |  | 1.6999 | 1.5338 |  | 20.3333 | 0.00085703 | 1520 | 0.053073 | 8252 | 4.5485e-05 | 4984
STONE 110995808 | STONE 1109 | 83701109 |  | 4.1033 | 4.2181 |  | 56.1667 | 0.00085697 | 1521 | 0.053073 | 8252 | 4.5482e-05 | 4985
HICKS 1109CB | HICKS 1109 | 83431109 |  | 3.3923 | 3.6146 |  | 44.85 | 0.00084457 | 1617 | 0.053722 | 8023 | 4.5478e-05 | 4986
MADERA 1102CB | MADERA 1102 | 252761102 |  | 0.005136 | 0 |  | 0.5 | 0.00073726 | 2650 | 0.061675 | 6804 | 4.547e-05 | 4987
TIDEWATER 210949552 | TIDEWATER 2109 | 14652109 |  | 8.602 | 7.3682 |  | 133.3333 | 0.00075113 | 2470 | 0.060413 | 6971 | 4.5468e-05 | 4988
ASHLAN AVE 2118CB | ASHLAN AVE 2118 | 252052118 |  | 6.0762 | 4.5903 |  | 98.45 | 0.00085533 | 1534 | 0.05316 | 8229 | 4.5462e-05 | 4989
SANTA ROSA A 1112102 | SANTA ROSA A 1112 | 42151112 |  | 3.8386 | 2.8935 |  | 54.8333 | 0.00084255 | 1631 | 0.05396 | 7965 | 4.5458e-05 | 4990
NOTRE DAME 11022420 | NOTRE DAME 1102 | 102041102 |  | 3.1224 | 2.1158 |  | 48 | 0.00080005 | 1965 | 0.057351 | 7385 | 4.5456e-05 | 4991
SAN RAFAEL 1106837 | SAN RAFAEL 1106 | 42011106 |  | 0.35603 | 0.2946 |  | 3.8333 | 0.00081927 | 1827 | 0.056011 | 7578 | 4.544e-05 | 4992
DEL MONTE 210533708 | DEL MONTE 2105 | 182222105 |  | 1.1444 | 1.1694 |  | 21.8333 | 0.00083856 | 1657 | 0.05403 | 7943 | 4.5439e-05 | 4993
SAN RAFAEL 1101310 | SAN RAFAEL 1101 | 42011101 | TRUE | 3.5975 | 3.2379 | 0.42099 | 55 | 0.00074164 | 2585 | 0.060416 | 6970 | 4.5435e-05 | 4994
ROCKLIN 1104CB | ROCKLIN 1104 | 152061104 |  | 3.1246 | 2.2176 |  | 48.5 | 0.0007693 | 2270 | 0.058993 | 7161 | 4.5432e-05 | 4995
OROVILLE 1102CB | OROVILLE 1102 | 102521102 |  | 3.4016 | 1.3025 |  | 47.0833 | 0.000856 | 1525 | 0.053073 | 8251 | 4.543e-05 | 4996
SAN JOSE A 0405CB | SAN JOSE A 0405 | 82250405 |  | 1.8349 | 1.8604 |  | 29.3333 | 0.00085578 | 1527 | 0.053073 | 8251 | 4.5419e-05 | 4997
OCEANO 1102V50 | OCEANO 1102 | 182601102 | FALSE | 10.6329 | 1.2741 | 7.8913 | 173 | 6.6395e-05 | 11116 | 0.84034 | 2532 | 4.5409e-05 | 4998
SAN JOSE B 1111CB | SAN JOSE B 1111 | 82261111 |  | 0.080824 | 0.050538 |  | 2.5 | 0.0008556 | 1529 | 0.053073 | 8251 | 4.5409e-05 | 4999
MANTECA 1703CB | MANTECA 1703 | 162611703 |  | 5.1246 | 5.1736 |  | 73.8333 | 0.00085539 | 1531 | 0.053073 | 8251 | 4.5398e-05 | 5000
BAY MEADOWS 2101912030 | BAY MEADOWS 2101 | 24012101 |  | 3.518 | 2.256 |  | 40 | 0.00085534 | 1532 | 0.053073 | 8251 | 4.5395e-05 | 5001
SYCAMORE CREEK 11102570 | SYCAMORE CREEK 1110 | 102971110 |  | 0.77292 | 0.5298 |  | 13.5 | 0.00085534 | 1533 | 0.053073 | 8251 | 4.5395e-05 | 5002
RICHMOND R 1125BR310 | RICHMOND R 1125 | 13471125 |  | 0.48316 | 0.44464 |  | 7.6667 | 0.00085533 | 1535 | 0.053073 | 8250 | 4.5395e-05 | 5003
EL PATIO 1108CB | EL PATIO 1108 | 82921108 |  | 6.7529 | 5.3063 |  | 97.5 | 0.00085525 | 1536 | 0.053073 | 8251 | 4.5391e-05 | 5004
SNEATH LANE 110210255 | SNEATH LANE 1102 | 22721102 |  | 2.9053 | 2.6288 |  | 42.8333 | 0.00074678 | 2524 | 0.061527 | 6825 | 4.5387e-05 | 5005
CARQUINEZ 110383138 | CARQUINEZ 1103 | 43281103 |  | 4.3217 | 2.3381 |  | 57.5 | 0.00085501 | 1538 | 0.053073 | 8251 | 4.5378e-05 | 5006
DEL MONTE 21059454 | DEL MONTE 2105 | 182222105 |  | 1.4113 | 0.96578 |  | 18.5 | 0.00077984 | 2150 | 0.05759 | 7344 | 4.5377e-05 | 5007
IGNACIO 1105CB | IGNACIO 1105 | 42481105 |  | 0.71484 | 0 |  | 6.9167 | 0.00071011 | 2974 | 0.063644 | 6592 | 4.5375e-05 | 5008
RICHMOND R 1119CB | RICHMOND R 1119 | 13471119 |  | 2.9149 | 2.8188 |  | 39.6167 | 0.00085493 | 1539 | 0.053073 | 8249 | 4.5373e-05 | 5009
OAKLAND J 1108CB | OAKLAND J 1108 | 12091108 |  | 3.2946 | 3.4015 |  | 49.1667 | 0.0008547 | 1541 | 0.053073 | 8252 | 4.5361e-05 | 5010
KIRKER 21065792 | KIRKER 2106 | 14452106 |  | 0.020983 | 0 |  | 0.5 | 0.00085466 | 1542 | 0.053073 | 8251 | 4.5359e-05 | 5011
RENFRO 2103CB | RENFRO 2103 | 254572103 |  | 0.48745 | 0 |  | 5 | 0.00072632 | 2771 | 0.062804 | 6678 | 4.5348e-05 | 5012
SAN MATEO 0404CB | SAN MATEO 0404 | 24190404 |  | 4.0304 | 2.4001 |  | 43.7 | 0.00083329 | 1699 | 0.054401 | 7865 | 4.5346e-05 | 5013
BAY MEADOWS 110439402 | BAY MEADOWS 1104 | 24011104 |  | 4.132 | 3.7733 |  | 55.4167 | 0.00085426 | 1545 | 0.053073 | 8251 | 4.5338e-05 | 5014
LAS POSITAS 2105775742 | LAS POSITAS 2105 | 14402105 |  | 0.0097255 | 0 |  | 1.5 | 0.00085395 | 1547 | 0.053073 | 8251 | 4.5322e-05 | 5015
BELLEVUE 110242164 | BELLEVUE 1102 | 43181102 |  | 1.3434 | 0.25942 |  | 23.5 | 0.00068953 | 3226 | 0.066107 | 6246 | 4.5311e-05 | 5016
POTRERO PP (A) 1105CB | POTRERO PP (A) 1105 | 22031105 |  | 1.6059 | 1.0439 |  | 25.3333 | 0.00085374 | 1549 | 0.053073 | 8251 | 4.531e-05 | 5017
NAPA 1112CB | NAPA 1112 | 42021112 |  | 12.4216 | 6.4211 |  | 204.0333 | 0.00073289 | 2697 | 0.062107 | 6754 | 4.5307e-05 | 5018
PEASE 1105CB | PEASE 1105 | 153751105 |  | 3.9805 | 0.89461 |  | 65.0833 | 0.00072348 | 2811 | 0.066666 | 6150 | 4.5306e-05 | 5019
HARTER 1104CB | HARTER 1104 | 152851104 |  | 7.2386 | 4.5575 |  | 102.95 | 0.00085341 | 1551 | 0.053073 | 8251 | 4.5293e-05 | 5020
STONE 1104CB | STONE 1104 | 83701104 |  | 5.0044 | 4.0789 |  | 75.8333 | 0.00085334 | 1553 | 0.053073 | 8251 | 4.5289e-05 | 5021
OAKLAND C 1114CR416 | OAKLAND C 1114 | 12011114 |  | 0.59843 | 0.36182 |  | 7.6667 | 0.00085319 | 1554 | 0.053073 | 8250 | 4.5281e-05 | 5022
KIRKER 210475648 | KIRKER 2104 | 14452104 |  | 3.1145 | 2.8117 |  | 49.5 | 0.00076426 | 2333 | 0.058961 | 7163 | 4.5278e-05 | 5023
MILPITAS 1109XR372 | MILPITAS 1109 | 82831109 |  | 1.2458 | 1.9603 |  | 20.5 | 0.00085302 | 1556 | 0.053073 | 8251 | 4.5272e-05 | 5024
SHEPHERD 2110CB | SHEPHERD 2110 | 252062110 |  | 3.0703 | 0.57755 |  | 60 | 0.00064398 | 3776 | 0.071723 | 4799 | 4.5265e-05 | 5025
VINEYARD 2106CB | VINEYARD 2106 | 14502106 |  | 1.8099 | 1.2559 |  | 34.5833 | 0.00081625 | 1845 | 0.05579 | 7619 | 4.5265e-05 | 5026
PAUL SWEET 2108CB | PAUL SWEET 2108 | 83252108 |  | 7.4708 | 5.6787 |  | 110 | 0.00076519 | 2324 | 0.05937 | 7101 | 4.5257e-05 | 5027
MILLBRAE 1102CB | MILLBRAE 1102 | 22691102 |  | 2.9352 | 2.2992 |  | 42.3667 | 0.00083256 | 1707 | 0.054306 | 7887 | 4.5253e-05 | 5028
DEL MONTE 210276218 | DEL MONTE 2102 | 182222102 |  | 0.37065 | 0.098718 |  | 7.5 | 0.00074041 | 2595 | 0.064215 | 6517 | 4.5252e-05 | 5029
POTRERO PP (A) 1110CB | POTRERO PP (A) 1110 | 22031110 |  | 2.9716 | 3.0066 |  | 32.7 | 0.00085259 | 1557 | 0.053073 | 8250 | 4.5249e-05 | 5030
ROSSMOOR 1101L501R | ROSSMOOR 1101 | 14161101 |  | 2.0036 | 1.6081 |  | 43 | 0.00075573 | 2425 | 0.060113 | 7005 | 4.5247e-05 | 5031
SHEPHERD 2112R4588 | SHEPHERD 2112 | 252062112 |  | 1.4429 | 0.46613 |  | 25 | 0.0006447 | 3767 | 0.072392 | 4731 | 4.5247e-05 | 5032
SAN JOSE B 1101CB | SAN JOSE B 1101 | 82261101 |  | 0.15793 | 0.066977 |  | 3.5 | 0.00085236 | 1558 | 0.053073 | 8251 | 4.5237e-05 | 5033
LAKEWOOD 2226CB | LAKEWOOD 2226 | 13532226 |  | 3.3002 | 2.725 |  | 57.3333 | 0.00082294 | 1794 | 0.05506 | 7742 | 4.5236e-05 | 5034
BOGUE 110751666 | BOGUE 1107 | 153781107 |  | 5.6434 | 2.9933 |  | 81.75 | 0.00085227 | 1559 | 0.053073 | 8251 | 4.5232e-05 | 5035
STONE 1110XR458 | STONE 1110 | 83701110 |  | 2.3106 | 1.9721 |  | 38.3333 | 0.00085216 | 1561 | 0.053073 | 8251 | 4.5227e-05 | 5036
VALLEJO C 0401CB | VALLEJO C 0401 | 42550401 |  | 2.8026 | 2.6571 |  | 38.0833 | 0.0008521 | 1562 | 0.053073 | 8250 | 4.5223e-05 | 5037
HIGHLANDS 110487040 | HIGHLANDS 1104 | 43361104 |  | 7.102 | 4.7931 |  | 93.1667 | 0.00072763 | 2754 | 0.061688 | 6800 | 4.5219e-05 | 5038
RICHMOND R 1128CB | RICHMOND R 1128 | 13471128 |  | 0.89606 | 0.24832 |  | 14.8667 | 0.00085172 | 1565 | 0.053073 | 8252 | 4.5203e-05 | 5039
GREENBRAE 1104CB | GREENBRAE 1104 | 43091104 |  | 0.52479 | 0 |  | 7 | 0.00077308 | 2229 | 0.058047 | 7286 | 4.5196e-05 | 5040
SF N 040671068 | SF N 0406 | 22280406 |  | 0.48715 | 0.2915 |  | 7.8333 | 0.0007739 | 2215 | 0.057731 | 7333 | 4.5189e-05 | 5041
TERMINOUS 1102CB | TERMINOUS 1102 | 163021102 |  | 0.29314 | 0 |  | 3.3333 | 0.00058376 | 4487 | 0.0774 | 3398 | 4.5183e-05 | 5042
TASSAJARA 210791094 | TASSAJARA 2107 | 14662107 |  | 5.7373 | 4.4838 |  | 103 | 0.0007693 | 2271 | 0.059175 | 7134 | 4.5179e-05 | 5043
STOREY 11052830 | STOREY 1105 | 254611105 |  | 0.98556 | 0 |  | 15 | 0.00067557 | 3365 | 0.066858 | 6107 | 4.5162e-05 | 5044
HUNTERS POINT (P) 110790058 | HUNTERS POINT (P) 1107 | 22331107 |  | 2.3898 | 2.9289 |  | 31.0833 | 0.00085084 | 1568 | 0.053073 | 8250 | 4.5157e-05 | 5045
JARVIS 1101CB | JARVIS 1101 | 13501101 |  | 6.2704 | 6.8186 |  | 88.5833 | 0.00085082 | 1569 | 0.053073 | 8252 | 4.5155e-05 | 5046
SYCAMORE CREEK 11112602 | SYCAMORE CREEK 1111 | 102971111 |  | 0.82947 | 0.33165 |  | 16.5 | 0.00073481 | 2679 | 0.0613 | 6855 | 4.5154e-05 | 5047
SERRAMONTE 11046055 | SERRAMONTE 1104 | 22861104 |  | 0.59472 | 0.69988 |  | 8.6667 | 0.00076537 | 2320 | 0.059799 | 7040 | 4.5136e-05 | 5048
SAN JOSE B 1105CB | SAN JOSE B 1105 | 82261105 |  | 2.719 | 2.7845 |  | 40.8333 | 0.00085044 | 1571 | 0.053073 | 8251 | 4.5135e-05 | 5049
VIEJO 22029100 | VIEJO 2202 | 182852202 |  | 6.5871 | 6.1247 |  | 109.1667 | 0.00068839 | 3242 | 0.065788 | 6306 | 4.5122e-05 | 5050
SF K 0404CB | SF K 0404 | 22130404 |  | 0.97496 | 1.5392 |  | 11.4 | 0.00079965 | 1968 | 0.056274 | 7538 | 4.5101e-05 | 5051
MAGUNDEN 1101CB | MAGUNDEN 1101 | 252771101 |  | 2.7763 | 1.2937 |  | 33.0595 | 0.00084967 | 1576 | 0.053073 | 8251 | 4.5094e-05 | 5052
WEST SACRAMENTO 1110CB | WEST SACRAMENTO 1110 | 63131110 |  | 6.6733 | 4.9526 |  | 108.5333 | 0.00084925 | 1577 | 0.053073 | 8250 | 4.5072e-05 | 5053
EL CAPITAN 110630980 | EL CAPITAN 1106 | 253881106 |  | 3.2049 | 3.0784 |  | 50.5 | 0.00084924 | 1578 | 0.053073 | 8251 | 4.5071e-05 | 5054
SAN JOSE A 0407CB | SAN JOSE A 0407 | 82250407 |  | 1.8251 | 1.5497 |  | 26.5 | 0.0008492 | 1579 | 0.053073 | 8250 | 4.507e-05 | 5055
STELLING 1103LL02 | STELLING 1103 | 83481103 |  | 0.047791 | 0 |  | 0.5 | 0.00084901 | 1582 | 0.053073 | 8251 | 4.5059e-05 | 5056
MT EDEN 1101MR112 | MT EDEN 1101 | 13761101 |  | 1.2576 | 0.37048 |  | 21.25 | 0.00084892 | 1584 | 0.053073 | 8251 | 4.5054e-05 | 5057
RENFRO 2102CB | RENFRO 2102 | 254572102 |  | 2.4585 | 0.4875 |  | 40.5 | 0.00072882 | 2742 | 0.061719 | 6796 | 4.5048e-05 | 5058
REDWOOD CITY 110476624 | REDWOOD CITY 1104 | 24161104 |  | 0.019207 | 0 |  | 0.2 | 0.0008488 | 1585 | 0.053073 | 8251 | 4.5048e-05 | 5059
MAGUNDEN 1106CB | MAGUNDEN 1106 | 252771106 |  | 4.4314 | 3.2565 |  | 62.6429 | 0.00076019 | 2380 | 0.061282 | 6858 | 4.5044e-05 | 5060
VACAVILLE 1110CB | VACAVILLE 1110 | 63601110 |  | 2.3567 | 1.2673 |  | 47 | 0.00075905 | 2399 | 0.060196 | 6994 | 4.5043e-05 | 5061
OAKLAND I 0401CB | OAKLAND I 0401 | 12080401 |  | 3.2527 | 3.6765 |  | 36.1667 | 0.00084869 | 1586 | 0.053073 | 8250 | 4.5042e-05 | 5062
CHANNEL 1102CB | CHANNEL 1102 | 163071102 |  | 5.6711 | 4.2162 |  | 79.1667 | 0.00084632 | 1602 | 0.05329 | 8184 | 4.5036e-05 | 5063
FRANKLIN 1103CB | FRANKLIN 1103 | 13921103 |  | 2.7703 | 2.0362 |  | 42.0833 | 0.00068835 | 3243 | 0.064852 | 6458 | 4.5026e-05 | 5064
STAGG 210763320 | STAGG 2107 | 162422107 |  | 2.13 | 0.023059 |  | 36.1667 | 0.00073656 | 2661 | 0.067198 | 5814 | 4.5023e-05 | 5065
SAN RAFAEL 1109535284 | SAN RAFAEL 1109 | 42011109 | TRUE | 0.56783 | 0.47589 | 0.066016 | 12 | 0.00073797 | 2637 | 0.061914 | 6773 | 4.4996e-05 | 5066
VIEJO 22022014 | VIEJO 2202 | 182852202 |  | 4.087 | 0.28444 |  | 86.5 | 0.00051075 | 5277 | 0.07326 | 4642 | 4.4993e-05 | 5067
BURLINGAME 0404CB | BURLINGAME 0404 | 24050404 |  | 3.1472 | 2.7987 |  | 47 | 0.00079804 | 1985 | 0.057129 | 7418 | 4.4967e-05 | 5068
EAST GRAND 1114CB | EAST GRAND 1114 | 22571114 |  | 0.002841 | 0 |  | 0.5 | 0.00084725 | 1593 | 0.053073 | 8251 | 4.4966e-05 | 5069
SARATOGA 110413314 | SARATOGA 1104 | 83371104 |  | 6.6566 | 4.4491 |  | 116.5 | 0.00067452 | 3377 | 0.066685 | 6143 | 4.495e-05 | 5070
SANTA YNEZ 1102CB | SANTA YNEZ 1102 | 182721102 | FALSE | 8.9247 | 2.3058 | 0.92959 | 159.1667 | 0.00040129 | 6436 | 0.12656 | 3256 | 4.4948e-05 | 5071
SAN CARLOS 0401CB | SAN CARLOS 0401 | 24180401 |  | 1.6185 | 0.75145 |  | 21.45 | 0.00084445 | 1618 | 0.053231 | 8206 | 4.4942e-05 | 5072
SF H 110365488 | SF H 1103 | 22101103 |  | 0.53667 | 0.65724 |  | 8.9167 | 0.00084671 | 1598 | 0.053073 | 8252 | 4.4937e-05 | 5073
BARTON 111664447 | BARTON 1116 | 253571116 |  | 4.1062 | 1.7604 |  | 62.1667 | 0.00082631 | 1762 | 0.054385 | 7869 | 4.4933e-05 | 5074
BARTON 1110D8931 | BARTON 1110 | 253571110 |  | 0.88367 | 1.2026 |  | 15 | 0.00084651 | 1600 | 0.053073 | 8251 | 4.4926e-05 | 5075
STELLING 1111CB | STELLING 1111 | 83481111 |  | 8.794 | 7.0597 |  | 129.1667 | 0.00079913 | 1974 | 0.056307 | 7530 | 4.4924e-05 | 5076
EDES 1103CR358 | EDES 1103 | 13681103 |  | 1.2745 | 0.80172 |  | 16.6667 | 0.00084626 | 1603 | 0.053073 | 8250 | 4.4913e-05 | 5077
FRANKLIN 1102P168 | FRANKLIN 1102 | 13921102 |  | 1.3809 | 0 |  | 26 | 0.00067015 | 3430 | 0.067007 | 6025 | 4.4905e-05 | 5078
CAROLANDS 0403CB | CAROLANDS 0403 | 24060403 |  | 0.15272 | 0 |  | 1.6667 | 0.00074781 | 2511 | 0.060194 | 6995 | 4.4903e-05 | 5079
ANDERSON 1102CB | ANDERSON 1102 | 103261102 |  | 1.144 | 0.86664 |  | 19.5 | 0.00082656 | 1760 | 0.055229 | 7715 | 4.4876e-05 | 5080
TRACY 110514012 | TRACY 1105 | 162881105 |  | 0.011364 | 0 |  | 0.5 | 0.00084552 | 1607 | 0.053073 | 8251 | 4.4874e-05 | 5081
GABILAN 1101989608 | GABILAN 1101 | 182331101 | FALSE | 2.3439 | 0 | 0.73051 | 45.5 | 8.2347e-05 | 11101 | 0.91646 | 2475 | 4.4873e-05 | 5082
STAGG 110159806 | STAGG 1101 | 162421101 |  | 1.4193 | 1.0489 |  | 20 | 0.00084543 | 1610 | 0.053073 | 8251 | 4.4869e-05 | 5083
DALY CITY 110415369 | DALY CITY 1104 | 22641104 |  | 2.1476 | 1.5043 |  | 36.8333 | 0.00078159 | 2134 | 0.058508 | 7220 | 4.4861e-05 | 5084
FORT ORD 1101131442 | FORT ORD 1101 | 182401101 |  | 4.5294 | 3.5562 |  | 91.8333 | 0.00082401 | 1783 | 0.054589 | 7830 | 4.4856e-05 | 5085
CALIFORNIA AVE 1116D6132 | CALIFORNIA AVE 1116 | 252281116 |  | 1.2389 | 1.5471 |  | 21.5 | 0.00084494 | 1612 | 0.053073 | 8251 | 4.4843e-05 | 5086
DUMBARTON 1108CB | DUMBARTON 1108 | 14471108 |  | 1.4693 | 0 |  | 14.1667 | 0.00077586 | 2196 | 0.058316 | 7248 | 4.4829e-05 | 5087
SONOMA 11061678 | SONOMA 1106 | 42721106 |  | 1.3751 | 0.96326 |  | 16.5 | 0.00084465 | 1614 | 0.053073 | 8251 | 4.4828e-05 | 5088
SANTA MARIA 1112M140 | SANTA MARIA 1112 | 182671112 |  | 1.1606 | 1.0541 |  | 19.5 | 0.0008443 | 1620 | 0.053073 | 8251 | 4.4809e-05 | 5089
OAKLAND D 0406CB | OAKLAND D 0406 | 12040406 |  | 1.8567 | 1.1464 |  | 22.5833 | 0.00084425 | 1621 | 0.053073 | 8249 | 4.4807e-05 | 5090
MOLINO 1104468882 | MOLINO 1104 | 42571104 |  | 2.6629 | 1.7888 |  | 53.5 | 0.00076641 | 2305 | 0.059345 | 7106 | 4.4805e-05 | 5091
SAN LEANDRO U 1112CB | SAN LEANDRO U 1112 | 13111112 |  | 3.9659 | 2.906 |  | 60.5 | 0.00084419 | 1623 | 0.053073 | 8251 | 4.4804e-05 | 5092
STOREY 110713000 | STOREY 1107 | 254611107 |  | 5.1528 | 4.2622 |  | 86 | 0.00084411 | 1624 | 0.053073 | 8250 | 4.4799e-05 | 5093
HATTON 110240465 | HATTON 1102 | 182291102 |  | 2.8547 | 2.3483 |  | 47 | 0.0007383 | 2629 | 0.060777 | 6918 | 4.4769e-05 | 5094
SF H 110944832 | SF H 1109 | 22101109 |  | 0.70411 | 0.56184 |  | 6.1667 | 0.0008431 | 1625 | 0.053073 | 8250 | 4.4746e-05 | 5095
OAKLAND C 1117465596 | OAKLAND C 1117 | 12011117 |  | 2.5744 | 0.44846 |  | 33.1667 | 0.00084308 | 1626 | 0.053073 | 8250 | 4.4745e-05 | 5096
AIRWAYS 1104CB | AIRWAYS 1104 | 252041104 |  | 2.0271 | 0.72121 |  | 39 | 0.000784 | 2110 | 0.060558 | 6949 | 4.4741e-05 | 5097
SAN JOSE B 1105XR506 | SAN JOSE B 1105 | 82261105 |  | 0.91473 | 0.9947 |  | 14.5 | 0.00084287 | 1627 | 0.053073 | 8250 | 4.4733e-05 | 5098
SAN PABLO 1105BR142 | SAN PABLO 1105 | 14371105 |  | 5.1198 | 5.7026 |  | 75 | 0.00074802 | 2506 | 0.059269 | 7116 | 4.4732e-05 | 5099
SF H 0404CB | SF H 0404 | 22100404 |  | 2.7427 | 2.6057 |  | 26.9179 | 0.00084284 | 1628 | 0.053073 | 8250 | 4.4732e-05 | 5100
WINDSOR 1101CB | WINDSOR 1101 | 43501101 |  | 2.2849 | 0.45588 |  | 33.8333 | 0.00070649 | 3023 | 0.062678 | 6693 | 4.4731e-05 | 5101
KONOCTI 1108430588 | KONOCTI 1108 | 43311108 |  | 0.030684 | 0 |  | 3 | 0.00061823 | 4066 | 0.072349 | 4740 | 4.4728e-05 | 5102
SAN JOSE B 1115XR448 | SAN JOSE B 1115 | 82261115 |  | 0.67075 | 0.52608 |  | 12.25 | 0.00084275 | 1629 | 0.053073 | 8251 | 4.4727e-05 | 5103
CONTRA COSTA 211375910 | CONTRA COSTA 2113 | 13652113 |  | 3.2934 | 0.46752 |  | 53.5 | 0.00072073 | 2844 | 0.062538 | 6708 | 4.4725e-05 | 5104
SALINAS 1103CB | SALINAS 1103 | 182011103 |  | 0.53227 | 0.080432 |  | 7.3333 | 0.00073404 | 2682 | 0.05972 | 7052 | 4.4724e-05 | 5105
SANTA ROSA A 1105CB | SANTA ROSA A 1105 | 42151105 |  | 8.9351 | 5.0878 |  | 134.5 | 0.00082177 | 1804 | 0.054796 | 7789 | 4.4724e-05 | 5106
SARATOGA 1114XR540 | SARATOGA 1114 | 83371114 |  | 0.40432 | 0 |  | 5 | 0.00084252 | 1632 | 0.053073 | 8251 | 4.4715e-05 | 5107
FIGARDEN 211358912 | FIGARDEN 2113 | 254552113 |  | 1.5665 | 0.56502 |  | 26 | 0.00070263 | 3070 | 0.065704 | 6323 | 4.4712e-05 | 5108
CLAYTON 2216C544R | CLAYTON 2216 | 12022216 |  | 6.1974 | 3.931 |  | 98.5 | 0.00084237 | 1634 | 0.053073 | 8251 | 4.4707e-05 | 5109
SAN CARLOS 0406CB | SAN CARLOS 0406 | 24180406 |  | 6.5368 | 5.564 |  | 94.0929 | 0.00077463 | 2208 | 0.057661 | 7338 | 4.4679e-05 | 5110
EAST GRAND 1105CB | EAST GRAND 1105 | 22571105 |  | 3.1202 | 2.6822 |  | 47.3333 | 0.0008416 | 1639 | 0.053073 | 8251 | 4.4666e-05 | 5111
NAPA 1109700752 | NAPA 1109 | 42021109 |  | 6.0634 | 4.1145 |  | 90.8333 | 0.0008415 | 1641 | 0.053073 | 8252 | 4.4661e-05 | 5112
STOCKTON A 1110CB | STOCKTON A 1110 | 162371110 |  | 10.0819 | 6.4145 |  | 157.6667 | 0.00083268 | 1705 | 0.053759 | 8011 | 4.4657e-05 | 5113
VACA DIXON 110965548 | VACA DIXON 1109 | 63591109 |  | 0.28742 | 0 |  | 7.5 | 0.00066466 | 3502 | 0.067205 | 5802 | 4.4653e-05 | 5114
NEWARK 21KV 2102MR223 | NEWARK 21KV 2102 | 12232102 |  | 2.165 | 1.422 |  | 39 | 0.00073828 | 2630 | 0.060393 | 6972 | 4.4651e-05 | 5115
HAMMER 110812452 | HAMMER 1108 | 163301108 |  | 4.7225 | 4.094 |  | 66.6667 | 0.00084131 | 1642 | 0.053073 | 8252 | 4.4651e-05 | 5116
MALAGA 1110CB | MALAGA 1110 | 254251110 |  | 8.8448 | 3.5526 |  | 159.3333 | 0.00077213 | 2236 | 0.059212 | 7126 | 4.4641e-05 | 5117
TASSAJARA 2107CB | TASSAJARA 2107 | 14662107 |  | 2.7924 | 0.47298 |  | 60 | 0.00073965 | 2599 | 0.06161 | 6810 | 4.464e-05 | 5118
COUNTRY CLUB 0402CB | COUNTRY CLUB 0402 | 163120402 |  | 5.1291 | 6.019 |  | 78.3667 | 0.00083407 | 1691 | 0.053694 | 8033 | 4.4621e-05 | 5119
MANTECA 1702CB | MANTECA 1702 | 162611702 |  | 14.0483 | 11.4419 |  | 181.1667 | 0.00084056 | 1643 | 0.053207 | 8215 | 4.4621e-05 | 5120
LOCKEFORD 2102CB | LOCKEFORD 2102 | 163682102 |  | 0.82807 | 0.27613 |  | 16 | 0.00058232 | 4498 | 0.076908 | 3823 | 4.4612e-05 | 5121
COLUMBUS 1109CB | COLUMBUS 1109 | 253951109 |  | 1.6682 | 0.050249 |  | 27.3333 | 0.00077516 | 2203 | 0.057368 | 7380 | 4.4586e-05 | 5122
MANZANITA 04039680 | MANZANITA 0403 | 183150403 |  | 1.0258 | 1.2202 |  | 14.25 | 0.00083989 | 1648 | 0.053073 | 8251 | 4.4575e-05 | 5123
SANTA ROSA A 111179354 | SANTA ROSA A 1111 | 42151111 |  | 3.623 | 1.395 |  | 65.3333 | 0.00068233 | 3305 | 0.064991 | 6434 | 4.4569e-05 | 5124
STONE 1107CB | STONE 1107 | 83701107 |  | 5.2295 | 2.0855 |  | 83.4167 | 0.00083099 | 1724 | 0.053741 | 8019 | 4.4566e-05 | 5125
SAN MATEO 0410CB | SAN MATEO 0410 | 24190410 |  | 2.5481 | 2.0631 |  | 28.25 | 0.00080903 | 1905 | 0.055456 | 7679 | 4.4547e-05 | 5126
MILPITAS 2111CB | MILPITAS 2111 | 82832111 |  | 1.8014 | 1.0052 |  | 33.8333 | 0.00083921 | 1651 | 0.053073 | 8252 | 4.4539e-05 | 5127
SAN JOSE A 1112CB | SAN JOSE A 1112 | 82251112 |  | 2.7263 | 1.7257 |  | 47.5 | 0.00083891 | 1654 | 0.053073 | 8251 | 4.4523e-05 | 5128
DEL MONTE 21039452 | DEL MONTE 2103 | 182222103 |  | 1.9831 | 1.2323 |  | 28.4167 | 0.00079421 | 2017 | 0.05641 | 7514 | 4.4521e-05 | 5129
SAN LEANDRO U 1111CB | SAN LEANDRO U 1111 | 13111111 |  | 2.2946 | 1.6018 |  | 37.5833 | 0.00083857 | 1656 | 0.053073 | 8250 | 4.4505e-05 | 5130
LARKIN (Y) 1110CB | LARKIN (Y) 1110 | 22801110 |  | 0.03129 | 0.019014 |  | 0.83333 | 0.00083841 | 1660 | 0.053073 | 8250 | 4.4497e-05 | 5131
HARTER 1106CB | HARTER 1106 | 152851106 |  | 2.1179 | 0.28328 |  | 37.45 | 0.00083247 | 1709 | 0.054602 | 7825 | 4.4483e-05 | 5132
WOLFE 111435446 | WOLFE 1114 | 83671114 |  | 0.99001 | 0.62375 |  | 16.5 | 0.00083802 | 1661 | 0.053073 | 8251 | 4.4476e-05 | 5133
DAVIS 1102294582 | DAVIS 1102 | 62041102 |  | 0.61471 | 0.49223 |  | 11 | 0.00083741 | 1662 | 0.053073 | 8251 | 4.4443e-05 | 5134
OROVILLE 11042588 | OROVILLE 1104 | 102521104 |  | 8.981 | 4.8717 |  | 134.5 | 0.00069646 | 3147 | 0.064227 | 6516 | 4.4438e-05 | 5135
PEASE 110551698 | PEASE 1105 | 153751105 |  | 4.2903 | 2.7208 |  | 59.6667 | 0.0008372 | 1663 | 0.053073 | 8252 | 4.4433e-05 | 5136
MORGAN HILL 2111XR354 | MORGAN HILL 2111 | 83242111 |  | 0.53448 | 0.22218 |  | 12.1667 | 0.0006844 | 3281 | 0.06452 | 6486 | 4.442e-05 | 5137
MAGUNDEN 110115264 | MAGUNDEN 1101 | 252771101 |  | 1.0035 | 1.3976 |  | 17 | 0.00083678 | 1666 | 0.053073 | 8251 | 4.441e-05 | 5138
POTTER VALLEY P H 1105990354 | POTTER VALLEY P H 1105 | 42281105 | TRUE | 0.095886 | 0 | 0.095885 | 1.0833 | 0.00063813 | 3850 | 0.069587 | 5105 | 4.4405e-05 | 5139
NEWARK 12KV 1103MR823 | NEWARK 12KV 1103 | 12221103 |  | 0.0020876 | 0 |  | 0.5 | 0.00083658 | 1669 | 0.053073 | 8251 | 4.4399e-05 | 5140
SANTA ROSA A 1108CB | SANTA ROSA A 1108 | 42151108 |  | 3.0925 | 2.2268 |  | 64.3333 | 0.00083655 | 1670 | 0.053073 | 8252 | 4.4398e-05 | 5141
COUNTRY CLUB 0401CB | COUNTRY CLUB 0401 | 163120401 |  | 2.105 | 2.339 |  | 31.3667 | 0.00083623 | 1672 | 0.053073 | 8250 | 4.4381e-05 | 5142
CLOVIS 1101CB | CLOVIS 1101 | 254081101 |  | 3.9796 | 3.3277 |  | 64.5 | 0.0008319 | 1713 | 0.053273 | 8189 | 4.4367e-05 | 5143
MEADOW LANE 210856034 | MEADOW LANE 2108 | 14302108 |  | 4.2035 | 2.6863 |  | 63.8333 | 0.00074817 | 2500 | 0.059436 | 7094 | 4.4364e-05 | 5144
VACAVILLE 110941782 | VACAVILLE 1109 | 63601109 |  | 2.1972 | 0.27406 |  | 34.5 | 0.00066033 | 3576 | 0.067222 | 5789 | 4.4358e-05 | 5145
OAKLAND C 1113CB | OAKLAND C 1113 | 12011113 |  | 2.7835 | 2.1316 |  | 40.45 | 0.0008355 | 1675 | 0.053073 | 8250 | 4.4342e-05 | 5146
TIDEWATER 210965264 | TIDEWATER 2109 | 14652109 |  | 1.4556 | 1.2159 |  | 24.5 | 0.00083543 | 1676 | 0.053073 | 8251 | 4.4339e-05 | 5147
STOCKTON A 1102CB | STOCKTON A 1102 | 162371102 |  | 6.4678 | 2.3207 |  | 100.5667 | 0.00083156 | 1716 | 0.053329 | 8165 | 4.4337e-05 | 5148
NORD 110348020 | NORD 1103 | 103071103 |  | 0.74605 | 0.2343 |  | 15.5 | 0.0008354 | 1677 | 0.053073 | 8251 | 4.4337e-05 | 5149
SAN LEANDRO U 1116MR592 | SAN LEANDRO U 1116 | 13111116 |  | 1.4819 | 1.0735 |  | 18.8333 | 0.00083533 | 1679 | 0.053073 | 8251 | 4.4333e-05 | 5150
HICKS 1112CB | HICKS 1112 | 83431112 |  | 4.4902 | 5.0183 |  | 59.8667 | 0.00083529 | 1681 | 0.053073 | 8252 | 4.4331e-05 | 5151
PEABODY 211340336 | PEABODY 2113 | 63642113 |  | 2.1085 | 1.9279 |  | 31.8333 | 0.00083519 | 1682 | 0.053073 | 8252 | 4.4326e-05 | 5152
MEADOW LANE 210395110 | MEADOW LANE 2103 | 14302103 |  | 2.0511 | 1.5303 |  | 32.6667 | 0.00083483 | 1684 | 0.053073 | 8252 | 4.4307e-05 | 5153
WEST SACRAMENTO 1107CB | WEST SACRAMENTO 1107 | 63131107 |  | 18.7293 | 16.5153 |  | 286.5333 | 0.00083464 | 1685 | 0.053073 | 8251 | 4.4297e-05 | 5154
OAKLAND C 1119CB | OAKLAND C 1119 | 12011119 |  | 0.42052 | 0.10911 |  | 4.3333 | 0.00083453 | 1687 | 0.053073 | 8252 | 4.4291e-05 | 5155
FMC 1108CB | FMC 1108 | 83871108 |  | 1.3503 | 1.3639 |  | 22.9167 | 0.00083443 | 1689 | 0.053073 | 8250 | 4.4286e-05 | 5156
BELLEVUE 210342412 | BELLEVUE 2103 | 43182103 |  | 0.058666 | 0 |  | 2 | 0.00078252 | 2125 | 0.060054 | 7009 | 4.4277e-05 | 5157
BELLE HAVEN 1106287588 | BELLE HAVEN 1106 | 24021106 |  | 2.6483 | 1.255 |  | 35.7 | 0.00083405 | 1692 | 0.053073 | 8250 | 4.4266e-05 | 5158
BELLEVUE 110275956 | BELLEVUE 1102 | 43181102 |  | 2.4938 | 0.37808 |  | 37.5 | 0.00066728 | 3465 | 0.066444 | 6196 | 4.4265e-05 | 5159
VASONA 1105CB | VASONA 1105 | 83771105 |  | 1.3306 | 0.36058 |  | 24.5 | 0.00083393 | 1693 | 0.053073 | 8251 | 4.4259e-05 | 5160
OAKLAND C 1109CB | OAKLAND C 1109 | 12011109 |  | 0.20035 | 0.093391 |  | 3.1667 | 0.00083386 | 1694 | 0.053073 | 8251 | 4.4255e-05 | 5161
LAS PULGAS 0404CB | LAS PULGAS 0404 | 24120404 |  | 2.9292 | 2.4739 |  | 37.3333 | 0.00083376 | 1695 | 0.053073 | 8250 | 4.425e-05 | 5162
PAUL SWEET 210349370 | PAUL SWEET 2103 | 83252103 |  | 3.4218 | 2.1086 |  | 44.2833 | 0.00074461 | 2558 | 0.058719 | 7196 | 4.4246e-05 | 5163
BRENTWOOD 2110CB | BRENTWOOD 2110 | 14592110 |  | 3.4414 | 0 |  | 31.9167 | 0.0006579 | 3598 | 0.067177 | 5828 | 4.4244e-05 | 5164
VALLEJO B 0411CB | VALLEJO B 0411 | 42450411 |  | 7.0657 | 7.2068 |  | 100.75 | 0.00083352 | 1697 | 0.053073 | 8251 | 4.4237e-05 | 5165
EL PATIO 1107CB | EL PATIO 1107 | 82921107 |  | 8.4535 | 7.667 |  | 116.1667 | 0.00079135 | 2053 | 0.05607 | 7570 | 4.4225e-05 | 5166
CLAYTON 221442582 | CLAYTON 2214 | 12022214 |  | 2.3464 | 1.829 |  | 31.5 | 0.00081572 | 1850 | 0.05462 | 7822 | 4.422e-05 | 5167
FORT ORD 210633694 | FORT ORD 2106 | 182402106 |  | 4.2647 | 0.54844 |  | 45.25 | 0.00066117 | 3560 | 0.066896 | 6093 | 4.4217e-05 | 5168
HAMMER 1101CB | HAMMER 1101 | 163301101 |  | 3.6305 | 3.3318 |  | 48 | 0.00083307 | 1700 | 0.053073 | 8251 | 4.4213e-05 | 5169
MILLBRAE 110480106 | MILLBRAE 1104 | 22691104 |  | 2.5951 | 2.6179 |  | 41 | 0.00066092 | 3564 | 0.06652 | 6182 | 4.4209e-05 | 5170
CONTRA COSTA 2107K526R | CONTRA COSTA 2107 | 13652107 |  | 5.7096 | 4.152 |  | 87 | 0.0007965 | 2000 | 0.05577 | 7624 | 4.4205e-05 | 5171
POTRERO PP (A) 110338452 | POTRERO PP (A) 1103 | 22031103 |  | 0.5659 | 0.48054 |  | 10 | 0.00083289 | 1702 | 0.053073 | 8251 | 4.4203e-05 | 5172
COUNTRY CLUB 1106CB | COUNTRY CLUB 1106 | 163121106 |  | 8.9579 | 9.1574 |  | 123.5 | 0.00083281 | 1704 | 0.053073 | 8251 | 4.4199e-05 | 5173
CARBONA 1103CB | CARBONA 1103 | 163091103 |  | 2.1384 | 0.58797 |  | 44.8333 | 0.00070072 | 3087 | 0.061874 | 6779 | 4.4192e-05 | 5174
ATWATER 1106CB | ATWATER 1106 | 253611106 |  | 5.7689 | 4.7202 |  | 87.75 | 0.0008326 | 1706 | 0.053073 | 8251 | 4.4188e-05 | 5175
SAN LUIS OBISPO 1108CB | SAN LUIS OBISPO 1108 | 182631108 | TRUE | 4.9219 | 3.1562 | 0.056542 | 78.8333 | 0.00058887 | 4430 | 0.088138 | 3350 | 4.4184e-05 | 5176
WILLOWS A 1103CB | WILLOWS A 1103 | 102741103 |  | 2.7172 | 1.9955 |  | 43.95 | 0.0007499 | 2481 | 0.059415 | 7095 | 4.4166e-05 | 5177
7TH STANDARD 21021499 | 7TH STANDARD 2102 | 254582102 |  | 2.1678 | 0.064083 |  | 29.1667 | 0.00059162 | 4397 | 0.074628 | 4469 | 4.4148e-05 | 5178
TRIMBLE 1105CB | TRIMBLE 1105 | 83801105 |  | 0.3277 | 0.04117 |  | 7.5 | 0.00083148 | 1717 | 0.053073 | 8251 | 4.4129e-05 | 5179
HUNTERS POINT (P) 1104CB | HUNTERS POINT (P) 1104 | 22331104 |  | 1.4071 | 0.65565 |  | 18.625 | 0.00083146 | 1719 | 0.053073 | 8251 | 4.4128e-05 | 5180
BRENTWOOD 2105B503R | BRENTWOOD 2105 | 14592105 |  | 2.4451 | 0.066861 |  | 37.5 | 0.00066197 | 3546 | 0.066995 | 6061 | 4.4126e-05 | 5181
EL PATIO 1113LC02 | EL PATIO 1113 | 82921113 |  | 3.5649 | 1.2901 |  | 56.5 | 0.00083117 | 1720 | 0.053073 | 8251 | 4.4112e-05 | 5182
COLUMBUS 110614325 | COLUMBUS 1106 | 253951106 |  | 1.2344 | 1.4297 |  | 15.3333 | 0.00083112 | 1722 | 0.053073 | 8251 | 4.411e-05 | 5183
STELLING 1111LL04 | STELLING 1111 | 83481111 |  | 4.3804 | 2.8943 |  | 70 | 0.00070226 | 3073 | 0.062324 | 6733 | 4.4099e-05 | 5184
MOUNTAIN VIEW 1104LM26 | MOUNTAIN VIEW 1104 | 82031104 |  | 2.7907 | 1.9445 |  | 41.75 | 0.00083082 | 1725 | 0.053073 | 8252 | 4.4094e-05 | 5185
WOODLAND 1103CB | WOODLAND 1103 | 62031103 |  | 1.2342 | 0.013577 |  | 17.8333 | 0.00083074 | 1726 | 0.053073 | 8252 | 4.409e-05 | 5186
EL CAPITAN 110290272 | EL CAPITAN 1102 | 253881102 |  | 0.49344 | 0.080029 |  | 7 | 0.00066985 | 3438 | 0.066465 | 6191 | 4.4089e-05 | 5187
GLENWOOD 1101CB | GLENWOOD 1101 | 24091101 |  | 0.59114 | 0.50882 |  | 9.1667 | 0.0007448 | 2552 | 0.061176 | 6872 | 4.4086e-05 | 5188
OAKLAND J 1102CB | OAKLAND J 1102 | 12091102 |  | 6.0775 | 5.1639 |  | 76.8333 | 0.00083063 | 1727 | 0.053073 | 8251 | 4.4084e-05 | 5189
OAKLAND D 0406235358 | OAKLAND D 0406 | 12040406 |  | 1.3362 | 0.61303 |  | 15.4167 | 0.0008305 | 1729 | 0.053073 | 8253 | 4.4077e-05 | 5190
OAKLAND X 111223947 | OAKLAND X 1112 | 12541112 |  | 0.1193 | 0.084922 |  | 3 | 0.00073088 | 2718 | 0.061182 | 6871 | 4.4072e-05 | 5191
PANAMA 21011128 | PANAMA 2101 | 253422101 |  | 0.5457 | 0.0083122 |  | 9 | 0.00070777 | 3011 | 0.062533 | 6710 | 4.4066e-05 | 5192
STONE 1101XR472 | STONE 1101 | 83701101 |  | 2.5809 | 2.6602 |  | 42.1667 | 0.00083026 | 1732 | 0.053073 | 8252 | 4.4064e-05 | 5193
EMBARCADERO (Z) 1119CB | EMBARCADERO (Z) 1119 | 22871119 |  | 0.14609 | 0.14264 |  | 3.5 | 0.00083024 | 1733 | 0.053073 | 8251 | 4.4063e-05 | 5194
NEWARK 21KV 2107MR595 | NEWARK 21KV 2107 | 12232107 |  | 0.80314 | 0.37159 |  | 13.5 | 0.00068959 | 3224 | 0.062873 | 6673 | 4.4056e-05 | 5195
BELLE HAVEN 11068916 | BELLE HAVEN 1106 | 24021106 |  | 2.0196 | 1.2341 |  | 26.5333 | 0.00082996 | 1735 | 0.053073 | 8251 | 4.4048e-05 | 5196
WEEDPATCH 11012405 | WEEDPATCH 1101 | 252971101 |  | 3.0497 | 2.9464 |  | 65 | 0.00072668 | 2766 | 0.061011 | 6889 | 4.4047e-05 | 5197
DEL MONTE 210596246 | DEL MONTE 2105 | 182222105 |  | 5.6256 | 5.1819 |  | 70.9167 | 0.0008239 | 1785 | 0.053465 | 8107 | 4.4046e-05 | 5198
RAWSON 1103CB | RAWSON 1103 | 103531103 |  | 12.0709 | 3.7406 |  | 213.5 | 0.0006689 | 3445 | 0.066325 | 6215 | 4.4041e-05 | 5199
WYANDOTTE 1109CB | WYANDOTTE 1109 | 102911109 |  | 4.7657 | 1.9637 |  | 74.5833 | 0.00066027 | 3577 | 0.06691 | 6086 | 4.404e-05 | 5200
TRACY 111011900 | TRACY 1110 | 162881110 |  | 0.3006 | 0.2408 |  | 5 | 0.00066982 | 3439 | 0.066244 | 6224 | 4.4037e-05 | 5201
HALF MOON BAY 11029114 | HALF MOON BAY 1102 | 24101102 |  | 0.24141 | 0.042137 |  | 2.5 | 0.00082974 | 1739 | 0.053073 | 8251 | 4.4037e-05 | 5202
WEST LANE 110195948 | WEST LANE 1101 | 163621101 |  | 4.5389 | 2.9401 |  | 84.1667 | 0.00082854 | 1748 | 0.053175 | 8224 | 4.4035e-05 | 5203
EL CERRITO G 111451228 | EL CERRITO G 1114 | 12501114 |  | 0.027257 | 0 |  | 0.53333 | 0.00082927 | 1742 | 0.053073 | 8251 | 4.4012e-05 | 5204
TRINIDAD 1102CB | TRINIDAD 1102 | 192231102 |  | 4.4567 | 0.89795 |  | 79.5 | 0.00065675 | 3616 | 0.067013 | 6018 | 4.4011e-05 | 5205
CANAL 1104CB | CANAL 1104 | 252091104 |  | 5.9308 | 3.3356 |  | 82.3333 | 0.00082768 | 1755 | 0.053177 | 8221 | 4.4009e-05 | 5206
VINEYARD 2106MR168 | VINEYARD 2106 | 14502106 |  | 0.60182 | 0.40962 |  | 14.8333 | 0.00075238 | 2457 | 0.058817 | 7183 | 4.4005e-05 | 5207
SAN MATEO 04048554 | SAN MATEO 0404 | 24190404 |  | 1.04 | 0.67601 |  | 24.5 | 0.0006659 | 3483 | 0.066432 | 6200 | 4.3999e-05 | 5208
HARTER 110774924 | HARTER 1107 | 152851107 |  | 7.0365 | 2.8442 |  | 104.3333 | 0.00082325 | 1791 | 0.054005 | 7949 | 4.3999e-05 | 5209
MILLBRAE 0403CB | MILLBRAE 0403 | 22690403 |  | 1.4742 | 0.86642 |  | 17.5 | 0.00082447 | 1779 | 0.053273 | 8188 | 4.3997e-05 | 5210
RICHMOND R 1118CB | RICHMOND R 1118 | 13471118 |  | 1.4775 | 0.62237 |  | 23.3333 | 0.00082899 | 1744 | 0.053073 | 8252 | 4.3997e-05 | 5211
BRITTON 1115CB | BRITTON 1115 | 83611115 |  | 1.1226 | 0.13877 |  | 17 | 0.00082893 | 1745 | 0.053073 | 8251 | 4.3993e-05 | 5212
CORNING 11021666 | CORNING 1102 | 103331102 |  | 0.80539 | 0.51465 |  | 15.3333 | 0.00064785 | 3731 | 0.067266 | 5755 | 4.3992e-05 | 5213
MERCED 21029740 | MERCED 2102 | 252802102 |  | 5.7812 | 3.8849 |  | 101.6667 | 0.00082083 | 1812 | 0.053819 | 7994 | 4.3974e-05 | 5214
FRUITVALE 1104CB | FRUITVALE 1104 | 253391104 |  | 3.0003 | 1.4047 |  | 40.9833 | 0.00077381 | 2217 | 0.058639 | 7206 | 4.3968e-05 | 5215
SWIFT 210646779 | SWIFT 2106 | 83392106 |  | 1.9237 | 2.6207 |  | 25.6667 | 0.00082843 | 1749 | 0.053073 | 8250 | 4.3967e-05 | 5216
FIGARDEN 210584594 | FIGARDEN 2105 | 254552105 |  | 4.3226 | 2.483 |  | 69.5 | 0.00082837 | 1750 | 0.053073 | 8251 | 4.3964e-05 | 5217
EL PATIO 1112XR604 | EL PATIO 1112 | 82921112 |  | 3.0232 | 2.9964 |  | 43.5 | 0.0008283 | 1751 | 0.053073 | 8251 | 4.396e-05 | 5218
NAPA 111038966 | NAPA 1110 | 42021110 |  | 1.9829 | 0.96933 |  | 34.5 | 0.00076953 | 2264 | 0.057432 | 7367 | 4.3957e-05 | 5219
CONTRA COSTA 2103CB | CONTRA COSTA 2103 | 13652103 |  | 4.4153 | 3.1783 |  | 61.4 | 0.00075153 | 2465 | 0.058899 | 7168 | 4.3955e-05 | 5220
EL CAPITAN 110511480 | EL CAPITAN 1105 | 253881105 |  | 2.8965 | 2.0027 |  | 44.8333 | 0.00078427 | 2105 | 0.055898 | 7596 | 4.3953e-05 | 5221
SONOMA 1106CB | SONOMA 1106 | 42721106 |  | 3.0472 | 1.3919 |  | 54.5 | 0.00080341 | 1949 | 0.05566 | 7646 | 4.3951e-05 | 5222
EIGHT MILE 210238448 | EIGHT MILE 2102 | 163912102 |  | 1.9666 | 0.39429 |  | 28.8333 | 0.00058556 | 4471 | 0.074869 | 4433 | 4.3943e-05 | 5223
DAVIS 1107CB | DAVIS 1107 | 62041107 |  | 2.5779 | 0.12639 |  | 45.4167 | 0.00065274 | 3672 | 0.070056 | 5034 | 4.3943e-05 | 5224
WEST LANE 110214604 | WEST LANE 1102 | 163621102 |  | 10.1688 | 9.9522 |  | 172 | 0.0008278 | 1753 | 0.053073 | 8251 | 4.3934e-05 | 5225
BERKELEY F 1105CB | BERKELEY F 1105 | 12061105 | FALSE | 8.073 | 6.7985 | 1.7924 | 96.75 | 0.00077309 | 2228 | 0.056971 | 7442 | 4.3923e-05 | 5226
NORTECH 2111CB | NORTECH 2111 | 82462111 |  | 0.71333 | 0 |  | 15 | 0.00082758 | 1756 | 0.053073 | 8251 | 4.3922e-05 | 5227
WEST SACRAMENTO 110820222 | WEST SACRAMENTO 1108 | 63131108 |  | 3.2655 | 3.5817 |  | 48.3333 | 0.00082748 | 1757 | 0.053073 | 8250 | 4.3917e-05 | 5228
CLARKSVILLE 2110CB | CLARKSVILLE 2110 | 153612110 |  | 1.9455 | 0.055423 |  | 35.5 | 0.00065462 | 3646 | 0.067064 | 5932 | 4.3907e-05 | 5229
SAN MATEO 0408CB | SAN MATEO 0408 | 24190408 |  | 5.6105 | 5.2003 |  | 88.0333 | 0.0007565 | 2421 | 0.057977 | 7294 | 4.3883e-05 | 5230
CANAL 1102CB | CANAL 1102 | 252091102 |  | 4.4776 | 1.2679 |  | 72.3333 | 0.00069168 | 3196 | 0.065602 | 6340 | 4.3853e-05 | 5231
MANTECA 170414784 | MANTECA 1704 | 162611704 |  | 2.8582 | 1.6702 |  | 36.5 | 0.00082623 | 1764 | 0.053073 | 8251 | 4.385e-05 | 5232
ALMADEN 1111CB | ALMADEN 1111 | 82311111 |  | 4.043 | 4.6027 |  | 61.1667 | 0.00082601 | 1765 | 0.053073 | 8252 | 4.3839e-05 | 5233
RICHMOND R 1124BR300 | RICHMOND R 1124 | 13471124 |  | 1.5425 | 0.55913 |  | 19.25 | 0.00082556 | 1770 | 0.053073 | 8251 | 4.3814e-05 | 5234
LLAGAS 2102CB | LLAGAS 2102 | 83182102 |  | 5.3217 | 5.4646 |  | 83.3333 | 0.00079238 | 2039 | 0.055552 | 7668 | 4.3812e-05 | 5235
WEST LANE 1101CB | WEST LANE 1101 | 163621101 |  | 2.2561 | 1.4793 |  | 32 | 0.00082549 | 1771 | 0.053073 | 8251 | 4.3811e-05 | 5236
REDWOOD CITY 1103CB | REDWOOD CITY 1103 | 24161103 |  | 1.6526 | 0.71115 |  | 30.5595 | 0.0008083 | 1910 | 0.05444 | 7855 | 4.3802e-05 | 5237
MANTECA 1707621318 | MANTECA 1707 | 162611707 |  | 3.4873 | 2.9765 |  | 51.3333 | 0.00082531 | 1772 | 0.053073 | 8251 | 4.3801e-05 | 5238
RALSTON 1101100040 | RALSTON 1101 | 24141101 | TRUE | 0.80177 | 0 | 0.42782 | 10 | 9.8423e-05 | 11056 | 0.39367 | 2922 | 4.38e-05 | 5239
CONTRA COSTA 2107CB | CONTRA COSTA 2107 | 13652107 |  | 3.8992 | 1.0629 |  | 76.75 | 0.00065312 | 3668 | 0.06705 | 5947 | 4.3788e-05 | 5240
POINT ARENA 110137426 | POINT ARENA 1101 | 43381101 | TRUE | 5.1148 | 1.7759 | 0.49141 | 98.5 | 0.0003201 | 7629 | 0.14988 | 3205 | 4.3781e-05 | 5241
OAKLAND J 1117CR190 | OAKLAND J 1117 | 12091117 |  | 2.3784 | 2.8832 |  | 26.3333 | 0.00082487 | 1776 | 0.053073 | 8249 | 4.3778e-05 | 5242
TEVIS 2104145344 | TEVIS 2104 | 255322104 |  | 2.2413 | 0.072602 |  | 35.5 | 0.00069405 | 3168 | 0.063594 | 6599 | 4.3777e-05 | 5243
NEWARK 21KV 2108MR117 | NEWARK 21KV 2108 | 12232108 |  | 0.35553 | 0 |  | 6.5 | 0.00082479 | 1777 | 0.053073 | 8251 | 4.3774e-05 | 5244
18TH STREET 0401CB | 18TH STREET 0401 | 22390401 |  | 1.2652 | 1.1743 |  | 17.3333 | 0.00082472 | 1778 | 0.053073 | 8252 | 4.377e-05 | 5245
MANTECA 1701992915 | MANTECA 1701 | 162611701 |  | 0.97203 | 0.20346 |  | 13 | 0.00076648 | 2304 | 0.057808 | 7325 | 4.3756e-05 | 5246
BERESFORD 0402CB | BERESFORD 0402 | 24040402 |  | 2.107 | 1.8608 |  | 46.3333 | 0.00069897 | 3111 | 0.062992 | 6663 | 4.3753e-05 | 5247
WOODLAND 111222552 | WOODLAND 1112 | 62031112 |  | 9.672 | 7.0313 |  | 130.5 | 0.00082311 | 1792 | 0.053128 | 8242 | 4.3752e-05 | 5248
TIDEWATER 210756052 | TIDEWATER 2107 | 14652107 |  | 3.4531 | 1.1238 |  | 60 | 0.00080155 | 1957 | 0.05609 | 7565 | 4.3739e-05 | 5249
MEADOW LANE 210388136 | MEADOW LANE 2103 | 14302103 |  | 3.5177 | 2.4881 |  | 53 | 0.00082412 | 1781 | 0.053073 | 8251 | 4.3738e-05 | 5250
EAST STOCKTON 1102CB | EAST STOCKTON 1102 | 163131102 |  | 3.9605 | 1.3816 |  | 47.1667 | 0.00082411 | 1782 | 0.053073 | 8253 | 4.3738e-05 | 5251
HAMMER 1105CB | HAMMER 1105 | 163301105 |  | 7.0734 | 5.7445 |  | 107.8333 | 0.00082244 | 1799 | 0.053152 | 8232 | 4.3732e-05 | 5252
CLAYTON 221798080 | CLAYTON 2217 | 12022217 |  | 1.9018 | 1.1912 |  | 34.3333 | 0.00071926 | 2859 | 0.059781 | 7043 | 4.3732e-05 | 5253
DALY CITY 1110CB | DALY CITY 1110 | 22641110 |  | 1.7955 | 0.37994 |  | 39 | 0.00075806 | 2407 | 0.058251 | 7260 | 4.3731e-05 | 5254
EL CERRITO G 1110BR240 | EL CERRITO G 1110 | 12501110 |  | 3.6941 | 3.4412 |  | 40.6667 | 0.00082354 | 1786 | 0.053073 | 8252 | 4.3708e-05 | 5255
MOUNTAIN VIEW 1111CB | MOUNTAIN VIEW 1111 | 82031111 |  | 1.1078 | 0.36341 |  | 16.2333 | 0.00082352 | 1787 | 0.053073 | 8251 | 4.3706e-05 | 5256
COLUSA 110141792 | COLUSA 1101 | 62021101 |  | 0.91252 | 0.81726 |  | 14.1667 | 0.00082351 | 1788 | 0.053073 | 8251 | 4.3706e-05 | 5257
VASONA 1104CB | VASONA 1104 | 83771104 |  | 3.7274 | 1.284 |  | 60 | 0.00081788 | 1834 | 0.053421 | 8121 | 4.37e-05 | 5258
MANTECA 170193022 | MANTECA 1701 | 162611701 |  | 0.75368 | 0.010011 |  | 11 | 0.00082339 | 1790 | 0.053073 | 8251 | 4.37e-05 | 5259
SAN MATEO 2102897982 | SAN MATEO 2102 | 24192102 |  | 8.1024 | 6.5065 |  | 112.6667 | 0.00080592 | 1933 | 0.055062 | 7741 | 4.3697e-05 | 5260
SF L 0402CB | SF L 0402 | 22260402 |  | 0.0019887 | 0 |  | 0.5 | 0.00082298 | 1793 | 0.053073 | 8251 | 4.3678e-05 | 5261
ALTO 1123CB | ALTO 1123 | 42031123 | FALSE | 6.02 | 5.0709 | 0.70958 | 101.1667 | 0.00076046 | 2376 | 0.057524 | 7356 | 4.3675e-05 | 5262
SF K 0408CB | SF K 0408 | 22130408 |  | 1.355 | 1.6577 |  | 19.25 | 0.00082284 | 1795 | 0.053073 | 8250 | 4.367e-05 | 5263
RED BLUFF 1101CB | RED BLUFF 1101 | 103541101 |  | 4.0085 | 3.7325 |  | 57.4167 | 0.00073635 | 2662 | 0.060853 | 6904 | 4.3667e-05 | 5264
JARVIS 110662269 | JARVIS 1106 | 13501106 |  | 0.0028409 | 0 |  | 0.5 | 0.00082265 | 1797 | 0.053073 | 8251 | 4.366e-05 | 5265
SAN MATEO 210155256 | SAN MATEO 2101 | 24192101 |  | 3.1217 | 2.5106 |  | 42.6667 | 0.00081804 | 1831 | 0.053345 | 8158 | 4.3659e-05 | 5266
SOLEDAD 2104413916 | SOLEDAD 2104 | 182052104 | FALSE | 4.0398 | 0.12097 | 1.2154 | 70.5 | 0.00020187 | 10014 | 0.44567 | 2871 | 4.3659e-05 | 5267
TRACY 1103CB | TRACY 1103 | 162881103 |  | 4.3937 | 2.9553 |  | 59.25 | 0.00082257 | 1798 | 0.053073 | 8251 | 4.3656e-05 | 5268
SAUSALITO 0401CB | SAUSALITO 0401 | 42490401 |  | 2.0299 | 1.5639 |  | 28.1667 | 0.00078919 | 2068 | 0.055221 | 7720 | 4.3642e-05 | 5269
SARATOGA 1110XR396 | SARATOGA 1110 | 83371110 |  | 2.9173 | 2.5748 |  | 36.6667 | 0.00082221 | 1800 | 0.053073 | 8251 | 4.3637e-05 | 5270
OAKLAND D 1131CR430 | OAKLAND D 1131 | 12041131 |  | 2.4044 | 2.286 |  | 37.6667 | 0.00082188 | 1801 | 0.053073 | 8251 | 4.3619e-05 | 5271
SUISUN 1105CB | SUISUN 1105 | 62131105 |  | 5.3873 | 4.6259 |  | 71.25 | 0.0007779 | 2170 | 0.056293 | 7532 | 4.3617e-05 | 5272
PAUL SWEET 2108467366 | PAUL SWEET 2108 | 83252108 |  | 6.1568 | 4.7001 |  | 84.1667 | 0.00082174 | 1805 | 0.053073 | 8251 | 4.3612e-05 | 5273
IONE 1101CB | IONE 1101 | 163881101 | FALSE | 14.0788 | 0.13802 | 1.4473 | 281.5 | 0.00036808 | 6870 | 0.19972 | 3144 | 4.3597e-05 | 5274
EL CERRITO G 1113BR282 | EL CERRITO G 1113 | 12501113 |  | 2.891 | 2.3423 |  | 36 | 0.00082142 | 1807 | 0.053073 | 8251 | 4.3595e-05 | 5275
OAKLAND C 1120CB | OAKLAND C 1120 | 12011120 |  | 3.0351 | 0.84955 |  | 43.6167 | 0.0008214 | 1808 | 0.053073 | 8250 | 4.3594e-05 | 5276
BAY MEADOWS 110411223 | BAY MEADOWS 1104 | 24011104 |  | 0.54657 | 0.76094 |  | 9.3333 | 0.00082121 | 1809 | 0.053073 | 8251 | 4.3584e-05 | 5277
NORD 110334040 | NORD 1103 | 103071103 |  | 2.7728 | 0.56054 |  | 57.5 | 0.00070061 | 3090 | 0.063301 | 6627 | 4.3583e-05 | 5278
RIO BRAVO 110432450 | RIO BRAVO 1104 | 252861104 |  | 3.4929 | 0.18169 |  | 58.5 | 0.000571 | 4646 | 0.076152 | 4143 | 4.358e-05 | 5279
CAYUCOS 1102317156 | CAYUCOS 1102 | 182551102 | FALSE | 11.0471 | 0.40701 | 1.8023 | 220.5 | 0.00015996 | 10599 | 0.49243 | 2830 | 4.3577e-05 | 5280
KING CITY 1103723816 | KING CITY 1103 | 182031103 |  | 1.2812 | 0.75906 |  | 21.5 | 0.00073883 | 2618 | 0.05955 | 7077 | 4.3574e-05 | 5281
AIRWAYS 110894718 | AIRWAYS 1108 | 252041108 |  | 4.4258 | 2.9441 |  | 65.5 | 0.00082098 | 1810 | 0.053073 | 8251 | 4.3571e-05 | 5282
MANTECA 170880800 | MANTECA 1708 | 162611708 |  | 3.5646 | 0.61964 |  | 62.5 | 0.00076046 | 2375 | 0.060297 | 6984 | 4.3567e-05 | 5283
SNEATH LANE 110275844 | SNEATH LANE 1102 | 22721102 | TRUE | 0.52311 | 0.41704 | 0.098434 | 11.5 | 0.0006682 | 3454 | 0.065183 | 6406 | 4.3553e-05 | 5284
DAVIS 110168458 | DAVIS 1101 | 62041101 |  | 0.02059 | 0 |  | 0.5 | 0.00070592 | 3029 | 0.061675 | 6804 | 4.3538e-05 | 5285
STONE 1110XR456 | STONE 1110 | 83701110 |  | 2.3872 | 2.1977 |  | 40.5 | 0.00082031 | 1815 | 0.053073 | 8251 | 4.3536e-05 | 5286
HAMMER 11058624 | HAMMER 1105 | 163301105 |  | 2.6618 | 2.5578 |  | 36.8333 | 0.00081987 | 1821 | 0.053073 | 8250 | 4.3513e-05 | 5287
SF H 1106CB | SF H 1106 | 22101106 |  | 3.1034 | 3.3881 |  | 35.8345 | 0.00081957 | 1824 | 0.053073 | 8249 | 4.3497e-05 | 5288
SYCAMORE CREEK 1107CB | SYCAMORE CREEK 1107 | 102971107 |  | 5.4305 | 3.2903 |  | 85.5 | 0.00081775 | 1836 | 0.053154 | 8231 | 4.3489e-05 | 5289
LAKEWOOD 211082806 | LAKEWOOD 2110 | 13532110 |  | 6.5854 | 5.3765 |  | 121.5 | 0.00069251 | 3183 | 0.063635 | 6594 | 4.3486e-05 | 5290
MABURY 1105CB | MABURY 1105 | 82191105 |  | 0.85046 | 0.17838 |  | 18 | 0.00081916 | 1828 | 0.053073 | 8251 | 4.3475e-05 | 5291
EAST STOCKTON 110169982 | EAST STOCKTON 1101 | 163131101 |  | 8.3935 | 2.2969 |  | 136.8333 | 0.00080051 | 1962 | 0.054851 | 7782 | 4.3458e-05 | 5292
MEADOW LANE 2106C558R | MEADOW LANE 2106 | 14302106 |  | 13.5883 | 8.8746 |  | 241.5 | 0.00071429 | 2920 | 0.061601 | 6812 | 4.3443e-05 | 5293
LODI 110164912 | LODI 1101 | 162111101 |  | 1.7491 | 0.67286 |  | 27 | 0.00075232 | 2458 | 0.058479 | 7222 | 4.3441e-05 | 5294
BAKERSFIELD 1101CB | BAKERSFIELD 1101 | 253371101 |  | 7.4426 | 3.7815 |  | 101.0333 | 0.00078962 | 2064 | 0.057888 | 7311 | 4.3438e-05 | 5295
STONE 1107XR168 | STONE 1107 | 83701107 |  | 4.5598 | 4.3081 |  | 70.8333 | 0.00081801 | 1832 | 0.053073 | 8250 | 4.3414e-05 | 5296
SALINAS 110922364 | SALINAS 1109 | 182011109 |  | 1.7234 | 1.4341 |  | 29.8333 | 0.00080976 | 1898 | 0.053888 | 7979 | 4.3409e-05 | 5297
SANTA ROSA A 1108626 | SANTA ROSA A 1108 | 42151108 |  | 3.7349 | 0.64748 |  | 79 | 0.00038806 | 6605 | 0.128 | 3253 | 4.3408e-05 | 5298
MILLBRAE 11072030 | MILLBRAE 1107 | 22691107 |  | 3.7547 | 2.8216 |  | 51.6667 | 0.00081789 | 1833 | 0.053073 | 8251 | 4.3408e-05 | 5299
SAN LEANDRO U 1103CB | SAN LEANDRO U 1103 | 13111103 |  | 1.9304 | 1.2976 |  | 38.1667 | 0.00081779 | 1835 | 0.053073 | 8251 | 4.3402e-05 | 5300
PACIFIC GROVE 0422CB | PACIFIC GROVE 0422 | 182440422 |  | 1.7195 | 1.4016 |  | 26.75 | 0.00077339 | 2224 | 0.057238 | 7401 | 4.3396e-05 | 5301
RESEARCH 2101CB | RESEARCH 2101 | 14692101 |  | 5.6066 | 0.43117 |  | 93.3333 | 0.00072157 | 2836 | 0.060173 | 7001 | 4.3396e-05 | 5302
DAVIS 1108CB | DAVIS 1108 | 62041108 |  | 3.3371 | 0.24651 |  | 59.25 | 0.0007868 | 2082 | 0.055536 | 7670 | 4.3392e-05 | 5303
INDUSTRIAL ACRES 0411CB | INDUSTRIAL ACRES 0411 | 182300411 |  | 2.0094 | 1.0094 |  | 29.25 | 0.00081759 | 1838 | 0.053073 | 8251 | 4.3392e-05 | 5304
ANDERSON 11011390 | ANDERSON 1101 | 103261101 |  | 1.0829 | 0.56406 |  | 19.5 | 0.00066342 | 3522 | 0.06593 | 6287 | 4.3389e-05 | 5305
MARINA (F) 1103CB | MARINA (F) 1103 | 22781103 |  | 0.20161 | 0.20445 |  | 2.1667 | 0.00081751 | 1839 | 0.053073 | 8250 | 4.3388e-05 | 5306
OAKLAND K 1101CR172 | OAKLAND K 1101 | 12101101 | FALSE | 2.0718 | 2.602 | 1.0152 | 37.6667 | 0.00042889 | 6132 | 0.14524 | 3216 | 4.3387e-05 | 5307
EDES 1101CR230 | EDES 1101 | 13681101 |  | 2.6872 | 3.1009 |  | 37 | 0.0008172 | 1840 | 0.053073 | 8251 | 4.3371e-05 | 5308
WOODLAND 1108CB | WOODLAND 1108 | 62031108 |  | 5.8944 | 1.4098 |  | 95.8333 | 0.00080004 | 1966 | 0.054447 | 7853 | 4.337e-05 | 5309
EDES 1103CR136 | EDES 1103 | 13681103 |  | 4.1257 | 4.9322 |  | 57.7833 | 0.00081658 | 1842 | 0.053073 | 8252 | 4.3338e-05 | 5310
RAINBOW 1103CB | RAINBOW 1103 | 254441103 |  | 0.27046 | 0 |  | 2.8333 | 0.00055989 | 4756 | 0.0774 | 3398 | 4.3336e-05 | 5311
PACIFIC GROVE 04212616 | PACIFIC GROVE 0421 | 182440421 |  | 2.888 | 2.9219 |  | 37.1667 | 0.00080273 | 1952 | 0.053822 | 7992 | 4.3333e-05 | 5312
COUNTRY CLUB 1104CB | COUNTRY CLUB 1104 | 163121104 |  | 7.2061 | 8.4504 |  | 106.5 | 0.00081635 | 1843 | 0.053073 | 8251 | 4.3326e-05 | 5313
NORD 1105CB | NORD 1105 | 103071105 |  | 6.9938 | 1.1291 |  | 127.5 | 0.00070335 | 3061 | 0.062792 | 6679 | 4.3325e-05 | 5314
DEL MONTE 21039106 | DEL MONTE 2103 | 182222103 |  | 4.2455 | 0.99877 |  | 75.5 | 0.00065336 | 3665 | 0.066078 | 6251 | 4.3309e-05 | 5315
MT EDEN 1112MR538 | MT EDEN 1112 | 13761112 |  | 1.781 | 0.74117 |  | 27.5 | 0.00081595 | 1847 | 0.053073 | 8251 | 4.3304e-05 | 5316
SWIFT 2106XR060 | SWIFT 2106 | 83392106 |  | 7.1075 | 8.3644 |  | 107.1667 | 0.00081582 | 1848 | 0.053073 | 8251 | 4.3298e-05 | 5317
CALIFORNIA AVE 1116D8892 | CALIFORNIA AVE 1116 | 252281116 |  | 1.0592 | 1.1788 |  | 18.5 | 0.00081575 | 1849 | 0.053073 | 8251 | 4.3294e-05 | 5318
GREEN VALLEY 210412776 | GREEN VALLEY 2104 | 83192104 |  | 4.8514 | 4.5194 |  | 67.0833 | 0.00080916 | 1904 | 0.053489 | 8100 | 4.3291e-05 | 5319
STELLING 1103CB | STELLING 1103 | 83481103 |  | 2.807 | 1.8033 |  | 39.3333 | 0.00081559 | 1851 | 0.053073 | 8251 | 4.3285e-05 | 5320
SANTA ROSA A 111298576 | SANTA ROSA A 1112 | 42151112 |  | 4.8167 | 4.6575 |  | 75.5 | 0.00072818 | 2749 | 0.05905 | 7152 | 4.3281e-05 | 5321
MILPITAS 1109CB | MILPITAS 1109 | 82831109 |  | 6.452 | 6.1083 |  | 98 | 0.00081371 | 1866 | 0.053233 | 8203 | 4.3271e-05 | 5322
ASHLAN AVE 210536538 | ASHLAN AVE 2105 | 252052105 |  | 2.4536 | 1.318 |  | 32 | 0.0008153 | 1852 | 0.053073 | 8251 | 4.327e-05 | 5323
COPPERMINE 1104556430 | COPPERMINE 1104 | 252411104 | FALSE | 16.366 | 0.24163 | 4.528 | 308.5 | 8.0151e-05 | 11106 | 0.68944 | 2654 | 4.3268e-05 | 5324
BELMONT 1102CB | BELMONT 1102 | 24031102 |  | 1.5248 | 1.1266 |  | 25.8333 | 0.00081524 | 1853 | 0.053073 | 8252 | 4.3267e-05 | 5325
OAKLAND D 1130CB | OAKLAND D 1130 | 12041130 |  | 6.2587 | 5.1594 |  | 85.3333 | 0.00081524 | 1854 | 0.053073 | 8252 | 4.3267e-05 | 5326
EL PATIO 1113CB | EL PATIO 1113 | 82921113 |  | 1.1914 | 0.487 |  | 21.8333 | 0.00081502 | 1856 | 0.053073 | 8252 | 4.3255e-05 | 5327
SARATOGA 1110XR228 | SARATOGA 1110 | 83371110 |  | 2.1462 | 2.3532 |  | 29.3333 | 0.00081483 | 1857 | 0.053073 | 8252 | 4.3245e-05 | 5328
EDENVALE 2113CB | EDENVALE 2113 | 82952113 | TRUE | 1.4647 | 2.1356 | 0.015054 | 26 | 0.00069411 | 3166 | 0.074167 | 4531 | 4.3244e-05 | 5329
MC KEE 1104XR100 | MC KEE 1104 | 83531104 |  | 0.75146 | 0.61124 |  | 12.1667 | 0.00081476 | 1858 | 0.053073 | 8251 | 4.3242e-05 | 5330
SF E 0408CB | SF E 0408 | 22070408 |  | 2.6845 | 3.0269 |  | 26.9167 | 0.00081475 | 1859 | 0.053073 | 8249 | 4.3241e-05 | 5331
BRITTON 1104CB | BRITTON 1104 | 83611104 |  | 1.1834 | 0.39556 |  | 22 | 0.00081474 | 1860 | 0.053073 | 8251 | 4.3241e-05 | 5332
COTTLE 170426578 | COTTLE 1704 | 163711704 |  | 3.7094 | 2.0726 |  | 48.6667 | 0.00081472 | 1861 | 0.053073 | 8251 | 4.324e-05 | 5333
LAS GALLINAS A 1103CB | LAS GALLINAS A 1103 | 42991103 |  | 5.4373 | 2.0236 |  | 93 | 0.00048265 | 5572 | 0.084233 | 3376 | 4.3236e-05 | 5334
LAMONT 110349134 | LAMONT 1103 | 253911103 |  | 0.91628 | 0 |  | 15 | 0.00055848 | 4768 | 0.0774 | 3397 | 4.3226e-05 | 5335
WHISMAN 1108CB | WHISMAN 1108 | 83631108 |  | 1.9995 | 1.6298 |  | 30.5 | 0.00078591 | 2092 | 0.054899 | 7764 | 4.3215e-05 | 5336
BOGUE 1107CB | BOGUE 1107 | 153781107 |  | 2.6223 | 0.51382 |  | 39.75 | 0.00078657 | 2086 | 0.058618 | 7208 | 4.3211e-05 | 5337
CLOVIS 110599912 | CLOVIS 1105 | 254081105 |  | 5.4556 | 4.3046 |  | 95.5 | 0.00081317 | 1869 | 0.053163 | 8228 | 4.3192e-05 | 5338
CRESSEY 210464194 | CRESSEY 2104 | 254702104 |  | 0.72814 | 0.14416 |  | 11.8333 | 0.00055802 | 4779 | 0.0774 | 3397 | 4.319e-05 | 5339
SOLEDAD 21027644 | SOLEDAD 2102 | 182052102 |  | 1.5764 | 0.40618 |  | 29.5 | 0.00072442 | 2796 | 0.059446 | 7091 | 4.3183e-05 | 5340
TIDEWATER 21098830 | TIDEWATER 2109 | 14652109 |  | 1.6891 | 1.3261 |  | 29.6667 | 0.00081364 | 1867 | 0.053073 | 8250 | 4.3182e-05 | 5341
COTTLE 1704795368 | COTTLE 1704 | 163711704 |  | 5.5969 | 3.3245 |  | 83.3333 | 0.00080623 | 1932 | 0.05376 | 8010 | 4.3173e-05 | 5342
SARATOGA 1114XR418 | SARATOGA 1114 | 83371114 |  | 2.0543 | 1.9438 |  | 30.5 | 0.00081345 | 1868 | 0.053073 | 8251 | 4.3172e-05 | 5343
JANES CREEK 1104CB | JANES CREEK 1104 | 192391104 |  | 2.3663 | 0.19997 |  | 41.5 | 0.00064825 | 3727 | 0.066432 | 6199 | 4.3167e-05 | 5344
FORT ORD 11019518 | FORT ORD 1101 | 182401101 |  | 6.4751 | 4.1254 |  | 119.8333 | 0.00072513 | 2789 | 0.061003 | 6890 | 4.3165e-05 | 5345
ROUGH AND READY ISLA 110295784 | ROUGH AND READY ISLA 1102 | 163081102 |  | 0.34678 | 0.046044 |  | 5.5 | 0.00081312 | 1870 | 0.053073 | 8251 | 4.3154e-05 | 5346
HAMMER 110175256 | HAMMER 1101 | 163301101 |  | 1.8712 | 1.3354 |  | 26 | 0.00081299 | 1871 | 0.053073 | 8251 | 4.3148e-05 | 5347
AVENAL 2103CB | AVENAL 2103 | 255002103 |  | 2.4512 | 0 |  | 19.6667 | 0.00059927 | 4305 | 0.072376 | 4736 | 4.3145e-05 | 5348
AVENAL 2102CB | AVENAL 2102 | 255002102 |  | 2.4583 | 0 |  | 19.6667 | 0.00059927 | 4306 | 0.072376 | 4737 | 4.3145e-05 | 5349
WESTPARK 110849636 | WESTPARK 1108 | 253701108 |  | 1.434 | 1.6267 |  | 22 | 0.00081288 | 1872 | 0.053073 | 8251 | 4.3141e-05 | 5350
KIRKER 210639188 | KIRKER 2106 | 14452106 |  | 0.5461 | 0 |  | 6.6667 | 0.00079528 | 2007 | 0.05412 | 7926 | 4.314e-05 | 5351
BUTTE 1103883320 | BUTTE 1103 | 103081103 |  | 0.039421 | 0 |  | 0.5 | 0.00064387 | 3778 | 0.067 | 6057 | 4.3139e-05 | 5352
SARATOGA 1111XR416 | SARATOGA 1111 | 83371111 |  | 2.3976 | 1.5568 |  | 34.8333 | 0.00081264 | 1875 | 0.053073 | 8250 | 4.3129e-05 | 5353
PUEBLO 2102CB | PUEBLO 2102 | 43292102 |  | 13.6571 | 1.1956 |  | 264.8333 | 0.00063221 | 3915 | 0.068442 | 5297 | 4.3129e-05 | 5354
SF L 110299986 | SF L 1102 | 22261102 |  | 0.71512 | 0.89629 |  | 9.2 | 0.00081262 | 1876 | 0.053073 | 8250 | 4.3128e-05 | 5355
SAN JOSE B 1105XR238 | SAN JOSE B 1105 | 82261105 |  | 3.5136 | 1.9253 |  | 49.5 | 0.00081258 | 1877 | 0.053073 | 8251 | 4.3126e-05 | 5356
OAKLAND C 1116CB | OAKLAND C 1116 | 12011116 |  | 2.089 | 2.4554 |  | 34.9167 | 0.00081241 | 1878 | 0.053073 | 8252 | 4.3117e-05 | 5357
CARBONA 110458036 | CARBONA 1104 | 163091104 |  | 0.016607 | 0 |  | 0.5 | 0.00064333 | 3785 | 0.067 | 6057 | 4.3103e-05 | 5358
MOLINO 1102384 | MOLINO 1102 | 42571102 |  | 0.98581 | 0.28064 |  | 15 | 0.00063826 | 3846 | 0.067347 | 5705 | 4.3102e-05 | 5359
PIERCY 2110CB | PIERCY 2110 | 83912110 |  | 0.20298 | 0 |  | 4 | 0.00081204 | 1880 | 0.053073 | 8251 | 4.3097e-05 | 5360
HURON 1109CB | HURON 1109 | 253161109 |  | 0.32668 | 0 |  | 3.1667 | 0.00057854 | 4541 | 0.073559 | 4603 | 4.3093e-05 | 5361
MISSION (X) 111012451 | MISSION (X) 1110 | 22011110 |  | 3.6339 | 4.938 |  | 52 | 0.00081196 | 1881 | 0.053073 | 8253 | 4.3093e-05 | 5362
MONROE 110681758 | MONROE 1106 | 43301106 |  | 0.65917 | 0.24632 |  | 8.3333 | 0.00081186 | 1882 | 0.053073 | 8252 | 4.3087e-05 | 5363
OAKLAND X 1115CR294 | OAKLAND X 1115 | 12541115 |  | 1.1627 | 1.0079 |  | 15.8333 | 0.00081182 | 1883 | 0.053073 | 8250 | 4.3085e-05 | 5364
CARQUINEZ 1105CB | CARQUINEZ 1105 | 43281105 |  | 1.9398 | 1.8404 |  | 32.1667 | 0.00081166 | 1886 | 0.053073 | 8250 | 4.3077e-05 | 5365
NORD 1106CB | NORD 1106 | 103071106 |  | 8.0482 | 2.1205 |  | 159.3333 | 0.00070009 | 3096 | 0.063239 | 6640 | 4.3069e-05 | 5366
VALLEY VIEW 1103P160 | VALLEY VIEW 1103 | 14341103 | TRUE | 6.4049 | 6.4644 | 0.00072733 | 139.5 | 0.00051049 | 5281 | 0.08627 | 3361 | 4.3065e-05 | 5367
BOGUE 1104CB | BOGUE 1104 | 153781104 |  | 3.338 | 0.59114 |  | 65.2 | 0.00074271 | 2575 | 0.060067 | 7008 | 4.3063e-05 | 5368
EL CAPITAN 1106CB | EL CAPITAN 1106 | 253881106 |  | 3.0124 | 0.75566 |  | 30.7833 | 0.00078203 | 2131 | 0.055799 | 7615 | 4.3056e-05 | 5369
CAROLANDS 040387073 | CAROLANDS 0403 | 24060403 |  | 4.1183 | 0.47922 |  | 86.8333 | 0.00064047 | 3818 | 0.067154 | 5848 | 4.3042e-05 | 5370
EL CERRITO G 1110BR126 | EL CERRITO G 1110 | 12501110 |  | 0.67719 | 0.095457 |  | 7.1667 | 0.00081082 | 1891 | 0.053073 | 8250 | 4.3032e-05 | 5371
STONE 1109CB | STONE 1109 | 83701109 |  | 1.4047 | 0.67575 |  | 25.6667 | 0.00081082 | 1892 | 0.053073 | 8251 | 4.3032e-05 | 5372
PUEBLO 1102671 | PUEBLO 1102 | 43291102 |  | 0.72908 | 0.13167 |  | 14.5 | 0.00059767 | 4327 | 0.072396 | 4730 | 4.3032e-05 | 5373
VINEYARD 2110946322 | VINEYARD 2110 | 14502110 |  | 0.20065 | 0 |  | 5 | 0.00064203 | 3803 | 0.067 | 6057 | 4.3016e-05 | 5374
OAKLAND J 1111CR374 | OAKLAND J 1111 | 12091111 |  | 1.6231 | 1.0062 |  | 24.1667 | 0.00081014 | 1895 | 0.053073 | 8250 | 4.2997e-05 | 5375
MORAGA 1103E510R | MORAGA 1103 | 13801103 | TRUE | 6.1093 | 2.1382 | 0.36916 | 109.6667 | 0.00050735 | 5311 | 0.085052 | 3370 | 4.2993e-05 | 5376
WEBER 1110CB | WEBER 1110 | 163481110 |  | 4.7462 | 0.89432 |  | 70 | 0.00071397 | 2925 | 0.062528 | 6711 | 4.299e-05 | 5377
WYANDOTTE 1106CB | WYANDOTTE 1106 | 102911106 |  | 5.2818 | 1.4146 |  | 76.5833 | 0.00064985 | 3708 | 0.066269 | 6218 | 4.2988e-05 | 5378
MAGUNDEN 1105CB | MAGUNDEN 1105 | 252771105 |  | 7.0563 | 7.028 |  | 102.6429 | 0.00079115 | 2054 | 0.054591 | 7829 | 4.2983e-05 | 5379
BAY MEADOWS 210248770 | BAY MEADOWS 2102 | 24012102 |  | 1.2903 | 0.097981 |  | 21.8333 | 0.00063995 | 3827 | 0.067128 | 5876 | 4.2976e-05 | 5380
WHISMAN 1103CB | WHISMAN 1103 | 83631103 |  | 2.5543 | 1.3387 |  | 37.8333 | 0.00080967 | 1900 | 0.053073 | 8250 | 4.2971e-05 | 5381
LARKIN (Y) 1127971378 | LARKIN (Y) 1127 | 22801127 |  | 0.045311 | 0.053037 |  | 1.3333 | 0.00080966 | 1901 | 0.053073 | 8251 | 4.2971e-05 | 5382
BAHIA 1102CB | BAHIA 1102 | 43251102 |  | 1.6036 | 0.26108 |  | 27.5 | 0.00073344 | 2690 | 0.059403 | 7097 | 4.2969e-05 | 5383
KERN POWER 210565342 | KERN POWER 2105 | 255262105 |  | 0.73772 | 0 |  | 11 | 0.0008096 | 1902 | 0.053073 | 8251 | 4.2968e-05 | 5384
OAKLAND D 0408CB | OAKLAND D 0408 | 12040408 |  | 4.2536 | 3.9958 |  | 45.8333 | 0.00080902 | 1906 | 0.053073 | 8255 | 4.2937e-05 | 5385
HALF MOON BAY 1101821698 | HALF MOON BAY 1101 | 24101101 | FALSE | 0.82892 | 0.19762 | 0.9673 | 13.3333 | 0.00064032 | 3820 | 0.067052 | 5944 | 4.2932e-05 | 5386
FIGARDEN 211191186 | FIGARDEN 2111 | 254552111 |  | 1.8953 | 0.75574 |  | 30 | 0.00076502 | 2326 | 0.055505 | 7671 | 4.2932e-05 | 5387
LOYOLA 1101CB | LOYOLA 1101 | 82161101 |  | 5.4047 | 2.9138 |  | 88.95 | 0.00068486 | 3277 | 0.063229 | 6642 | 4.292e-05 | 5388
RINCON 1102640 | RINCON 1102 | 43321102 |  | 4.257 | 3.0892 |  | 70.5 | 0.00071969 | 2856 | 0.05991 | 7032 | 4.292e-05 | 5389
VASONA 1103CB | VASONA 1103 | 83771103 |  | 4.751 | 4.227 |  | 85.5 | 0.00073869 | 2619 | 0.057755 | 7329 | 4.2918e-05 | 5390
ORLAND B 1102CB | ORLAND B 1102 | 102701102 |  | 9.464 | 5.0063 |  | 154.5 | 0.00070413 | 3051 | 0.062411 | 6728 | 4.2914e-05 | 5391
FULTON 1107CB | FULTON 1107 | 42561107 |  | 10.2751 | 3.7602 |  | 185.0833 | 0.00068965 | 3223 | 0.062572 | 6705 | 4.2911e-05 | 5392
SF H 110114687 | SF H 1101 | 22101101 |  | 2.3569 | 3.2084 |  | 31.0833 | 0.00080842 | 1908 | 0.053073 | 8251 | 4.2905e-05 | 5393
SAN LEANDRO U 1116MR590 | SAN LEANDRO U 1116 | 13111116 |  | 0.28094 | 0.038834 |  | 5.3333 | 0.00080829 | 1911 | 0.053073 | 8251 | 4.2898e-05 | 5394
STUART 0404CB | STUART 0404 | 13840404 |  | 1.0704 | 1.0145 |  | 12.0833 | 0.00080816 | 1912 | 0.053073 | 8251 | 4.2891e-05 | 5395
COLUMBUS 11051767 | COLUMBUS 1105 | 253951105 |  | 3.5851 | 2.9582 |  | 57.8333 | 0.00076965 | 2262 | 0.055725 | 7634 | 4.289e-05 | 5396
POTRERO PP (A) 1113CB | POTRERO PP (A) 1113 | 22031113 |  | 1.5565 | 1.0186 |  | 22.1667 | 0.00080806 | 1913 | 0.053073 | 8249 | 4.2886e-05 | 5397
MC KEE 111169100 | MC KEE 1111 | 83531111 |  | 5.0545 | 5.9244 |  | 72.5 | 0.00080789 | 1914 | 0.053073 | 8251 | 4.2877e-05 | 5398
OAKLAND J 1101CR352 | OAKLAND J 1101 | 12091101 |  | 3.0949 | 2.8624 |  | 38.3333 | 0.00080781 | 1915 | 0.053073 | 8251 | 4.2873e-05 | 5399
MORGAN HILL 2108CB | MORGAN HILL 2108 | 83242108 |  | 5.4959 | 3.1388 |  | 106.5 | 0.00062887 | 3956 | 0.07079 | 4919 | 4.2869e-05 | 5400
NAPA 110549856 | NAPA 1105 | 42021105 |  | 6.0617 | 3.1292 |  | 102.3333 | 0.00071183 | 2951 | 0.061317 | 6851 | 4.2866e-05 | 5401
RIVERBANK 17169170 | RIVERBANK 1716 | 163191716 |  | 1.0402 | 0.22322 |  | 19 | 0.00080752 | 1916 | 0.053073 | 8251 | 4.2857e-05 | 5402
DEL MAR 210551692 | DEL MAR 2105 | 152582105 |  | 4.5233 | 0.042122 |  | 71.5 | 0.00070808 | 3006 | 0.061156 | 6874 | 4.2848e-05 | 5403
KING CITY 1102CB | KING CITY 1102 | 182031102 |  | 3.9793 | 0.38615 |  | 75.1667 | 0.00068978 | 3221 | 0.062927 | 6667 | 4.2841e-05 | 5404
EVERGREEN 2101XR112 | EVERGREEN 2101 | 82012101 |  | 0.35516 | 0.022277 |  | 11 | 0.00080721 | 1917 | 0.053073 | 8251 | 4.2841e-05 | 5405
DIXON 1105CB | DIXON 1105 | 62061105 |  | 3.8614 | 2.2473 |  | 56.6667 | 0.00077928 | 2154 | 0.055434 | 7683 | 4.2838e-05 | 5406
MAGUNDEN 11064445 | MAGUNDEN 1106 | 252771106 |  | 1.8886 | 1.6874 |  | 30.5 | 0.000807 | 1919 | 0.053073 | 8251 | 4.2829e-05 | 5407
IGNACIO 1104CB | IGNACIO 1104 | 42481104 |  | 1.4226 | 0.15716 |  | 23.5833 | 0.00064637 | 3750 | 0.066244 | 6225 | 4.2829e-05 | 5408
TASSAJARA 210883368 | TASSAJARA 2108 | 14662108 |  | 4.1526 | 2.1892 |  | 70.0833 | 0.00065479 | 3643 | 0.065271 | 6396 | 4.2826e-05 | 5409
KIRKER 210618742 | KIRKER 2106 | 14452106 |  | 3.1893 | 0.53982 |  | 62.8333 | 0.00077612 | 2193 | 0.056853 | 7460 | 4.2824e-05 | 5410
BOGUE 11071386 | BOGUE 1107 | 153781107 |  | 7.6198 | 3.5427 |  | 112.5 | 0.00073767 | 2641 | 0.059497 | 7083 | 4.2822e-05 | 5411
MILLBRAE 1101135416 | MILLBRAE 1101 | 22691101 |  | 2.2408 | 0.24416 |  | 31.6667 | 0.00080673 | 1921 | 0.053073 | 8251 | 4.2815e-05 | 5412
OAKLAND J 1118CB | OAKLAND J 1118 | 12091118 |  | 2.386 | 2.531 |  | 35.5 | 0.00080672 | 1922 | 0.053073 | 8251 | 4.2815e-05 | 5413
BELLE HAVEN 1106CB | BELLE HAVEN 1106 | 24021106 |  | 2.3228 | 0.73946 |  | 20.9167 | 0.00079429 | 2016 | 0.053905 | 7975 | 4.2814e-05 | 5414
SANTA MARIA 1112M108 | SANTA MARIA 1112 | 182671112 |  | 5.3901 | 4.9252 |  | 83.8333 | 0.00080634 | 1928 | 0.053073 | 8251 | 4.2795e-05 | 5415
TRACY 110214018 | TRACY 1102 | 162881102 |  | 3.4742 | 3.3313 |  | 48.4167 | 0.00080624 | 1931 | 0.053073 | 8251 | 4.2789e-05 | 5416
MERCED 21029450 | MERCED 2102 | 252802102 |  | 2.4509 | 2.4417 |  | 48.8333 | 0.00079704 | 1993 | 0.054026 | 7945 | 4.2785e-05 | 5417
BELLEVUE 2103940234 | BELLEVUE 2103 | 43182103 |  | 0.96056 | 0.36238 |  | 15 | 0.00059855 | 4316 | 0.073255 | 4643 | 4.2782e-05 | 5418
NORTECH 21107561 | NORTECH 2110 | 82462110 |  | 0.34685 | 0 |  | 6.5 | 0.00063847 | 3842 | 0.067 | 6057 | 4.2777e-05 | 5419
CORNING 1104CB | CORNING 1104 | 103331104 |  | 4.1864 | 1.8672 |  | 60.6667 | 0.00062809 | 3969 | 0.068053 | 5393 | 4.2775e-05 | 5420
SF L 1102CB | SF L 1102 | 22261102 |  | 1.4821 | 1.2202 |  | 15.75 | 0.0008059 | 1934 | 0.053073 | 8251 | 4.2771e-05 | 5421
BELLE HAVEN 0401CB | BELLE HAVEN 0401 | 24020401 |  | 9.4267 | 8.7014 |  | 137.3667 | 0.00076364 | 2338 | 0.056092 | 7564 | 4.2769e-05 | 5422
OAKLAND X 1112CR25 | OAKLAND X 1112 | 12541112 |  | 1.5462 | 1.3379 |  | 21 | 0.00080579 | 1935 | 0.053073 | 8251 | 4.2765e-05 | 5423
MC CALL 1105CB | MC CALL 1105 | 254121105 |  | 7.6134 | 2.3569 |  | 129.75 | 0.00070538 | 3040 | 0.061517 | 6829 | 4.2762e-05 | 5424
STOCKDALE 2114CB | STOCKDALE 2114 | 254072114 |  | 1.9616 | 0.57134 |  | 31.5 | 0.00080569 | 1936 | 0.053073 | 8251 | 4.276e-05 | 5425
RICHMOND R 1129BR148 | RICHMOND R 1129 | 13471129 |  | 2.8872 | 0.71217 |  | 42.5 | 0.00079339 | 2027 | 0.053922 | 7973 | 4.2759e-05 | 5426
DIXON LANDING 2109CB | DIXON LANDING 2109 | 14722109 |  | 2.6902 | 2.21 |  | 44 | 0.00072379 | 2804 | 0.061809 | 6784 | 4.2753e-05 | 5427
STOCKTON A 1106CB | STOCKTON A 1106 | 162371106 |  | 13.2658 | 9.1112 |  | 203.2667 | 0.00080429 | 1943 | 0.053242 | 8201 | 4.2753e-05 | 5428
SAN JOSE A 111297886 | SAN JOSE A 1112 | 82251112 |  | 2.4364 | 1.7333 |  | 33 | 0.0008054 | 1937 | 0.053073 | 8251 | 4.2745e-05 | 5429
MADERA 1118205056 | MADERA 1118 | 252761118 |  | 0.8835 | 0.5497 |  | 13.8333 | 0.00079739 | 1990 | 0.053695 | 8032 | 4.2741e-05 | 5430
SUISUN 110779930 | SUISUN 1107 | 62131107 |  | 1.9694 | 1.0222 |  | 27.5 | 0.00080533 | 1938 | 0.053073 | 8251 | 4.2741e-05 | 5431
BELMONT 1105CB | BELMONT 1105 | 24031105 |  | 0.63727 | 0 |  | 7.8333 | 0.00072926 | 2738 | 0.058766 | 7189 | 4.2734e-05 | 5432
MABURY 1101CB | MABURY 1101 | 82191101 |  | 4.2172 | 1.5042 |  | 72.9167 | 0.00078779 | 2077 | 0.05441 | 7863 | 4.273e-05 | 5433
LINCOLN 1101CB | LINCOLN 1101 | 153701101 |  | 12.7688 | 5.2812 |  | 188.25 | 0.00069939 | 3106 | 0.062753 | 6684 | 4.2716e-05 | 5434
FORT ORD 210531972 | FORT ORD 2105 | 182402105 |  | 3.7856 | 1.9516 |  | 68.5 | 0.00067587 | 3360 | 0.063593 | 6600 | 4.2696e-05 | 5435
MADERA 11126360 | MADERA 1112 | 252761112 |  | 0.17529 | 0.0085661 |  | 3.5 | 0.00062598 | 3987 | 0.070449 | 4954 | 4.2696e-05 | 5436
CLAYTON 2217C500R | CLAYTON 2217 | 12022217 |  | 2.2494 | 2.1411 |  | 35.6667 | 0.00080447 | 1942 | 0.053073 | 8252 | 4.2695e-05 | 5437
HICKS 2103CB | HICKS 2103 | 83432103 |  | 8.7955 | 7.8109 |  | 152.1667 | 0.00069045 | 3212 | 0.062588 | 6702 | 4.269e-05 | 5438
BRITTON 110779156 | BRITTON 1107 | 83611107 |  | 2.531 | 2.1042 |  | 41 | 0.00080408 | 1944 | 0.053073 | 8251 | 4.2675e-05 | 5439
FIGARDEN 211255614 | FIGARDEN 2112 | 254552112 |  | 2.6564 | 1.805 |  | 41.3333 | 0.00080394 | 1945 | 0.053073 | 8251 | 4.2667e-05 | 5440
STONE 1101XR478 | STONE 1101 | 83701101 |  | 3.7039 | 3.8293 |  | 50.6667 | 0.0008038 | 1947 | 0.053073 | 8252 | 4.266e-05 | 5441
ASHLAN AVE 1113R2990 | ASHLAN AVE 1113 | 252051113 |  | 3.9331 | 0.82367 |  | 55.4167 | 0.0006382 | 3848 | 0.070005 | 5045 | 4.2657e-05 | 5442
RICHMOND R 1129439370 | RICHMOND R 1129 | 13471129 |  | 2.4885 | 3.1345 |  | 31.6667 | 0.00076591 | 2313 | 0.056371 | 7517 | 4.2641e-05 | 5443
EDES 1111MR220 | EDES 1111 | 13681111 |  | 0.83196 | 0.14209 |  | 14 | 0.00074205 | 2582 | 0.060023 | 7018 | 4.2622e-05 | 5444
SAUSALITO 1101CB | SAUSALITO 1101 | 42491101 |  | 3.7266 | 1.2791 |  | 54.25 | 0.00076695 | 2297 | 0.055191 | 7724 | 4.2613e-05 | 5445
ROB ROY 210511028 | ROB ROY 2105 | 83692105 |  | 6.872 | 3.8192 |  | 102.8333 | 0.00065372 | 3659 | 0.064305 | 6507 | 4.2609e-05 | 5446
DALY CITY 110812513 | DALY CITY 1108 | 22641108 |  | 0.2349 | 0.1191 |  | 6.5 | 0.00080277 | 1951 | 0.053073 | 8251 | 4.2605e-05 | 5447
JARVIS 1106CB | JARVIS 1106 | 13501106 |  | 1.9321 | 1.7019 |  | 26.8333 | 0.0007954 | 2005 | 0.053592 | 8064 | 4.2605e-05 | 5448
CORNING 1101CB | CORNING 1101 | 103331101 |  | 3.7197 | 1.2969 |  | 55.3333 | 0.00065121 | 3696 | 0.065339 | 6385 | 4.26e-05 | 5449
LOYOLA 1102LL64 | LOYOLA 1102 | 82161102 |  | 4.4003 | 0.83026 |  | 76.5 | 0.00060863 | 4182 | 0.070029 | 5040 | 4.2586e-05 | 5450
SARATOGA 1108CB | SARATOGA 1108 | 83371108 |  | 5.1794 | 3.8504 |  | 83 | 0.00076114 | 2367 | 0.055562 | 7665 | 4.258e-05 | 5451
CLAYTON 221738248 | CLAYTON 2217 | 12022217 |  | 3.2954 | 2.7126 |  | 46 | 0.00079525 | 2008 | 0.053678 | 8039 | 4.2574e-05 | 5452
WHISMAN 1110CB | WHISMAN 1110 | 83631110 |  | 1.9889 | 1.1984 |  | 33 | 0.00080217 | 1953 | 0.053073 | 8251 | 4.2573e-05 | 5453
JARVIS 1108MR366 | JARVIS 1108 | 13501108 | TRUE | 9.8815 | 10.2114 | 0.043592 | 155.5 | 0.0005336 | 5033 | 0.084714 | 3371 | 4.257e-05 | 5454
NAPA 110349050 | NAPA 1103 | 42021103 |  | 5.3944 | 4.6256 |  | 79 | 0.00078598 | 2091 | 0.054059 | 7939 | 4.256e-05 | 5455
LAS GALLINAS A 1107662 | LAS GALLINAS A 1107 | 42991107 |  | 1.4346 | 0.68494 |  | 25.5 | 0.00080176 | 1955 | 0.053073 | 8251 | 4.2551e-05 | 5456
SAN CARLOS 1103CB | SAN CARLOS 1103 | 24181103 |  | 2.5497 | 0.37305 |  | 31.2833 | 0.000764 | 2334 | 0.057968 | 7295 | 4.2548e-05 | 5457
COUNTRY CLUB 110173018 | COUNTRY CLUB 1101 | 163121101 |  | 4.8231 | 5.6957 |  | 67.5 | 0.00080165 | 1956 | 0.053073 | 8251 | 4.2546e-05 | 5458
KINGSBURG 110279838 | KINGSBURG 1102 | 252241102 |  | 3.9505 | 4.3356 |  | 62.8333 | 0.00080126 | 1959 | 0.053073 | 8250 | 4.2525e-05 | 5459
ALTO 112087204 | ALTO 1120 | 42031120 |  | 7.9016 | 6.4996 |  | 119 | 0.00070553 | 3035 | 0.060052 | 7010 | 4.2523e-05 | 5460
PACIFIC GROVE 0421CB | PACIFIC GROVE 0421 | 182440421 |  | 0.45129 | 0.3964 |  | 5.5833 | 0.0008011 | 1961 | 0.053073 | 8252 | 4.2517e-05 | 5461
SAN MATEO 0407CB | SAN MATEO 0407 | 24190407 |  | 3.5888 | 2.5687 |  | 41.45 | 0.00080011 | 1964 | 0.053241 | 8202 | 4.2517e-05 | 5462
EUREKA E 110498682 | EUREKA E 1104 | 192331104 |  | 4.1634 | 2.4504 |  | 74 | 0.00064956 | 3711 | 0.065164 | 6410 | 4.2516e-05 | 5463
EL CERRITO G 1102BR230 | EL CERRITO G 1102 | 12501102 |  | 1.6907 | 0 |  | 23 | 0.00077154 | 2244 | 0.054659 | 7812 | 4.2513e-05 | 5464
SAN JOSE B 1107XR464 | SAN JOSE B 1107 | 82261107 |  | 4.1996 | 4.3126 |  | 63.1667 | 0.00079668 | 1995 | 0.053403 | 8134 | 4.2486e-05 | 5465
SALINAS 110722414 | SALINAS 1107 | 182011107 |  | 0.83214 | 0.11292 |  | 15 | 0.00080025 | 1963 | 0.053073 | 8251 | 4.2471e-05 | 5466
BELLE HAVEN 1104CB | BELLE HAVEN 1104 | 24021104 |  | 3.9334 | 2.1089 |  | 49.1167 | 0.00074463 | 2556 | 0.058421 | 7231 | 4.2468e-05 | 5467
SAN RAFAEL 1103258864 | SAN RAFAEL 1103 | 42011103 |  | 0.17455 | 0 |  | 3 | 0.00063374 | 3893 | 0.067 | 6057 | 4.246e-05 | 5468
LARKIN (Y) 112738696 | LARKIN (Y) 1127 | 22801127 |  | 0.62106 | 0.3672 |  | 6.9167 | 0.0008 | 1967 | 0.053073 | 8250 | 4.2458e-05 | 5469
SF E 0401CB | SF E 0401 | 22070401 |  | 3.5324 | 1.8089 |  | 41.2095 | 0.00079956 | 1969 | 0.053073 | 8251 | 4.2435e-05 | 5470
WEBER 11059148 | WEBER 1105 | 163481105 |  | 8.1345 | 6.5235 |  | 119.75 | 0.00079953 | 1970 | 0.053073 | 8252 | 4.2433e-05 | 5471
RADUM 1102CB | RADUM 1102 | 13151102 |  | 1.1494 | 0 |  | 25 | 0.00079952 | 1971 | 0.053073 | 8251 | 4.2433e-05 | 5472
ERTA 0404CB | ERTA 0404 | 83510404 |  | 3.9868 | 2.4529 |  | 53 | 0.0007057 | 3030 | 0.060817 | 6909 | 4.2423e-05 | 5473
SARATOGA 1111XR538 | SARATOGA 1111 | 83371111 |  | 3.8152 | 3.0395 |  | 47 | 0.00079924 | 1973 | 0.053073 | 8251 | 4.2418e-05 | 5474
BAHIA 11031628 | BAHIA 1103 | 43251103 |  | 1.2472 | 0.29628 |  | 20.1667 | 0.00075773 | 2411 | 0.05618 | 7548 | 4.2413e-05 | 5475
CARBONA 1104CB | CARBONA 1104 | 163091104 |  | 3.9655 | 0.53514 |  | 70.3333 | 0.00063234 | 3912 | 0.068247 | 5347 | 4.2413e-05 | 5476
MT EDEN 1106MR222 | MT EDEN 1106 | 13761106 |  | 0.89888 | 0.32098 |  | 17 | 0.00079911 | 1975 | 0.053073 | 8251 | 4.2411e-05 | 5477
FELLOWS 2104CB | FELLOWS 2104 | 254242104 |  | 4.1428 | 0 |  | 78 | 0.00059921 | 4307 | 0.070897 | 4905 | 4.2411e-05 | 5478
CANAL 110336722 | CANAL 1103 | 252091103 |  | 0.54791 | 0 |  | 13.5 | 0.00079901 | 1977 | 0.053073 | 8251 | 4.2405e-05 | 5479
WEST FRESNO 1104D3042 | WEST FRESNO 1104 | 253731104 |  | 1.4316 | 3.023 |  | 27.3333 | 0.00079898 | 1978 | 0.053073 | 8252 | 4.2404e-05 | 5480
BELLEVUE 2101CB | BELLEVUE 2101 | 43182101 |  | 4.1215 | 0.92384 |  | 66.8333 | 0.00072427 | 2799 | 0.060813 | 6910 | 4.2404e-05 | 5481
CHEROKEE 1101CB | CHEROKEE 1101 | 163651101 |  | 7.5889 | 3.2455 |  | 143.3333 | 0.00073723 | 2651 | 0.059579 | 7074 | 4.2397e-05 | 5482
OLIVEHURST 1103CB | OLIVEHURST 1103 | 152901103 |  | 6.42 | 1.1832 |  | 111 | 0.00062486 | 3999 | 0.06973 | 5083 | 4.2394e-05 | 5483
SF H 11016225 | SF H 1101 | 22101101 |  | 1.8915 | 0.1837 |  | 33 | 0.00065452 | 3647 | 0.065416 | 6374 | 4.2393e-05 | 5484
PUEBLO 1103857188 | PUEBLO 1103 | 43291103 |  | 4.8049 | 4.5179 |  | 72.5 | 0.0007845 | 2102 | 0.054898 | 7765 | 4.2391e-05 | 5485
PIERCY 2109XR378 | PIERCY 2109 | 83912109 |  | 3.0273 | 3.2822 |  | 37.8333 | 0.00079867 | 1982 | 0.053073 | 8250 | 4.2388e-05 | 5486
HUNTERS POINT (P) 1102CB | HUNTERS POINT (P) 1102 | 22331102 |  | 2.0858 | 2.1981 |  | 33.9917 | 0.00079857 | 1983 | 0.053073 | 8251 | 4.2382e-05 | 5487
TIDEWATER 2110C561R | TIDEWATER 2110 | 14652110 |  | 1.8202 | 1.8459 |  | 29.5 | 0.00079355 | 2023 | 0.053781 | 8005 | 4.238e-05 | 5488
OAKLAND J 1106CR262 | OAKLAND J 1106 | 12091106 |  | 1.6128 | 1.7302 |  | 23.0333 | 0.00079165 | 2048 | 0.054129 | 7922 | 4.2377e-05 | 5489
HAMMER 110614602 | HAMMER 1106 | 163301106 |  | 5.0292 | 5.1589 |  | 70.1667 | 0.00079805 | 1984 | 0.053073 | 8250 | 4.2355e-05 | 5490
OAKLAND C 1114CR440 | OAKLAND C 1114 | 12011114 |  | 1.8106 | 0.95719 |  | 25.75 | 0.00079775 | 1986 | 0.053073 | 8251 | 4.2339e-05 | 5491
SOLEDAD 21053076 | SOLEDAD 2105 | 182052105 |  | 1.1312 | 0.066689 |  | 19.3333 | 0.00063187 | 3917 | 0.067 | 6056 | 4.2335e-05 | 5492
COLUSA 1101929414 | COLUSA 1101 | 62021101 |  | 0.77177 | 0.79921 |  | 15.1667 | 0.00079755 | 1988 | 0.053073 | 8251 | 4.2328e-05 | 5493
BELL 111056214 | BELL 1110 | 152701110 |  | 6.6155 | 1.3454 |  | 113.5 | 0.00042478 | 6177 | 0.14119 | 3229 | 4.2309e-05 | 5494
COTTLE 17029890 | COTTLE 1702 | 163711702 |  | 4.8382 | 3.0999 |  | 69.3333 | 0.00079484 | 2013 | 0.053424 | 8119 | 4.2308e-05 | 5495
SNEATH LANE 11071277 | SNEATH LANE 1107 | 22721107 | TRUE | 2.157 | 2.1825 | 0.045184 | 36 | 0.00064588 | 3757 | 0.065512 | 6357 | 4.2302e-05 | 5496
WOODSIDE 11028862 | WOODSIDE 1102 | 24251102 | TRUE | 2.8354 | 3.1328 | 0.030775 | 46.25 | 0.00060614 | 4225 | 0.09555 | 3324 | 4.2296e-05 | 5497
MC KEE 1110CB | MC KEE 1110 | 83531110 |  | 1.1132 | 0 |  | 25 | 0.00079688 | 1994 | 0.053073 | 8251 | 4.2292e-05 | 5498
SF N 11026213 | SF N 1102 | 22281102 |  | 2.2367 | 2.3328 |  | 26.5 | 0.00079666 | 1996 | 0.053073 | 8248 | 4.2281e-05 | 5499
BUTTE 11062616 | BUTTE 1106 | 103081106 |  | 8.5193 | 3.5145 |  | 144.3333 | 0.00069152 | 3200 | 0.063479 | 6615 | 4.2277e-05 | 5500
STONE 1107XR166 | STONE 1107 | 83701107 |  | 2.2352 | 1.8158 |  | 33.8333 | 0.00077124 | 2248 | 0.055131 | 7732 | 4.2276e-05 | 5501
CONCORD NO 1 0401CB | CONCORD NO 1 0401 | 12960401 |  | 4.7201 | 4.4985 |  | 67.8333 | 0.0007875 | 2078 | 0.053586 | 8069 | 4.226e-05 | 5502
LAKEWOOD 1104W526R | LAKEWOOD 1104 | 13531104 |  | 0.61918 | 0.24177 |  | 10.5 | 0.0007959 | 2001 | 0.053073 | 8251 | 4.224e-05 | 5503
NORTH TOWER 1104CB | NORTH TOWER 1104 | 42041104 |  | 0.63284 | 0.053513 |  | 6.9 | 0.00062171 | 4028 | 0.068131 | 5375 | 4.2227e-05 | 5504
ROSSMOOR 1104L530R | ROSSMOOR 1104 | 14161104 |  | 1.9964 | 1.1711 |  | 35.5 | 0.00071786 | 2877 | 0.059546 | 7079 | 4.2224e-05 | 5505
SF E 110310485 | SF E 1103 | 22071103 |  | 1.9078 | 2.4694 |  | 29.5333 | 0.00079559 | 2003 | 0.053073 | 8249 | 4.2224e-05 | 5506
OAKLAND J 1115CB | OAKLAND J 1115 | 12091115 |  | 3.9098 | 2.4108 |  | 58.3333 | 0.00079551 | 2004 | 0.053073 | 8251 | 4.222e-05 | 5507
FRUITVALE 11044645 | FRUITVALE 1104 | 253391104 |  | 0.63809 | 0 |  | 8 | 0.00072206 | 2829 | 0.057634 | 7340 | 4.2217e-05 | 5508
SF L 110246994 | SF L 1102 | 22261102 |  | 1.3198 | 2.5412 |  | 23.8667 | 0.0007953 | 2006 | 0.053073 | 8251 | 4.2209e-05 | 5509
RINCON 1101839669 | RINCON 1101 | 43321101 |  | 0.0034804 | 0 |  | 0.5 | 0.00062893 | 3954 | 0.067105 | 5893 | 4.2205e-05 | 5510
OAKLAND L 1105CB | OAKLAND L 1105 | 12111105 |  | 2.5744 | 1.991 |  | 48.6667 | 0.00079519 | 2009 | 0.053073 | 8251 | 4.2203e-05 | 5511
RED BLUFF 110529222 | RED BLUFF 1105 | 103541105 |  | 6.0267 | 2.3082 |  | 100.5 | 0.00069234 | 3186 | 0.062034 | 6760 | 4.2202e-05 | 5512
PANAMA 210213071 | PANAMA 2102 | 253422102 |  | 1.5601 | 1.4409 |  | 20.3333 | 0.00070403 | 3053 | 0.060251 | 6989 | 4.2202e-05 | 5513
SF H 110313203 | SF H 1103 | 22101103 |  | 3.5802 | 3.9741 |  | 61.0833 | 0.00079334 | 2028 | 0.053354 | 8152 | 4.2198e-05 | 5514
LAWRENCE 1106CB | LAWRENCE 1106 | 83421106 |  | 2.7026 | 0.66373 |  | 31.8333 | 0.00079489 | 2012 | 0.053073 | 8249 | 4.2187e-05 | 5515
SONOMA 110213367 | SONOMA 1102 | 42721102 |  | 2.2707 | 1.687 |  | 34.3333 | 0.00070966 | 2979 | 0.061219 | 6866 | 4.2181e-05 | 5516
LERDO 11112483 | LERDO 1111 | 253491111 |  | 0.60169 | 0.022852 |  | 5.3333 | 0.00063009 | 3943 | 0.068277 | 5340 | 4.2177e-05 | 5517
ARLINGTON 0401404226 | ARLINGTON 0401 | 13700401 | FALSE | 0.98642 | 1.0625 | 1.5573 | 11.9167 | 0.0006391 | 3837 | 0.066221 | 6230 | 4.2175e-05 | 5518
STAGG 210790102 | STAGG 2107 | 162422107 |  | 1.1481 | 0.22307 |  | 24.3333 | 0.00071302 | 2936 | 0.06407 | 6530 | 4.2172e-05 | 5519
EAST MARYSVILLE 1107CB | EAST MARYSVILLE 1107 | 152331107 |  | 8.6791 | 5.6945 |  | 93.8333 | 0.0007453 | 2544 | 0.056425 | 7510 | 4.215e-05 | 5520
BRITTON 1107LV66 | BRITTON 1107 | 83611107 |  | 0.50961 | 0 |  | 3.6667 | 0.00079418 | 2018 | 0.053073 | 8251 | 4.2149e-05 | 5521
BOGUE 1102CB | BOGUE 1102 | 153781102 |  | 6.8625 | 2.9927 |  | 98.1167 | 0.00079223 | 2040 | 0.053294 | 8182 | 4.2148e-05 | 5522
CASTRO VALLEY 1105CB | CASTRO VALLEY 1105 | 14091105 |  | 6.6267 | 6.6834 |  | 104.3333 | 0.00079404 | 2019 | 0.053073 | 8250 | 4.2142e-05 | 5523
CANAL 110478274 | CANAL 1104 | 252091104 |  | 4.748 | 4.0977 |  | 74.1667 | 0.00079402 | 2020 | 0.053073 | 8250 | 4.2141e-05 | 5524
EL CERRITO G 1110BR236 | EL CERRITO G 1110 | 12501110 | TRUE | 0.52971 | 0.12726 | 0.61374 | 4.25 | 0.00062429 | 4009 | 0.067421 | 5650 | 4.214e-05 | 5525
DALY CITY 1105101 | DALY CITY 1105 | 22641105 |  | 1.3378 | 1.1833 |  | 20.3333 | 0.000686 | 3268 | 0.061548 | 6821 | 4.2137e-05 | 5526
DALY CITY 1112CB | DALY CITY 1112 | 22641112 |  | 5.1763 | 4.1487 |  | 91 | 0.00079374 | 2021 | 0.053073 | 8250 | 4.2126e-05 | 5527
COTTLE 1702526442 | COTTLE 1702 | 163711702 |  | 2.0116 | 1.0527 |  | 29.5 | 0.00079354 | 2025 | 0.053073 | 8251 | 4.2115e-05 | 5528
MARINA (F) 0401CB | MARINA (F) 0401 | 22780401 |  | 0.52836 | 0.41289 |  | 9.0833 | 0.00079343 | 2026 | 0.053073 | 8251 | 4.2109e-05 | 5529
WEST LANE 110161986 | WEST LANE 1101 | 163621101 |  | 0.53352 | 0.19635 |  | 12.5 | 0.00079326 | 2029 | 0.053073 | 8251 | 4.21e-05 | 5530
JARVIS 1103MR226 | JARVIS 1103 | 13501103 |  | 0.002841 | 0 |  | 0.5 | 0.00079311 | 2031 | 0.053073 | 8251 | 4.2093e-05 | 5531
MALAGA 1104CB | MALAGA 1104 | 254251104 |  | 9.1345 | 2.0368 |  | 155.1667 | 0.00068602 | 3266 | 0.064294 | 6508 | 4.2088e-05 | 5532
STAGG 11019212 | STAGG 1101 | 162421101 |  | 4.7184 | 5.7897 |  | 70.5 | 0.00079291 | 2032 | 0.053073 | 8251 | 4.2082e-05 | 5533
SUISUN 1104CB | SUISUN 1104 | 62131104 |  | 1.6829 | 2.3279 |  | 38.75 | 0.00079291 | 2033 | 0.053073 | 8251 | 4.2082e-05 | 5534
LOS MOLINOS 1101297862 | LOS MOLINOS 1101 | 103481101 | TRUE | 0.24834 | 0.059474 | 0.24876 | 7.5 | 0.00013578 | 10833 | 0.5002 | 2821 | 4.2078e-05 | 5535
BRITTON 1112CB | BRITTON 1112 | 83611112 |  | 1.8447 | 0.016722 |  | 21.5 | 0.00079268 | 2037 | 0.053073 | 8250 | 4.207e-05 | 5536
MARYSVILLE 1102CB | MARYSVILLE 1102 | 152011102 |  | 7.4433 | 3.9132 |  | 98.4167 | 0.00077781 | 2173 | 0.054306 | 7888 | 4.2046e-05 | 5537
MILPITAS 2110XR404 | MILPITAS 2110 | 82832110 |  | 4.6077 | 6.4648 |  | 72 | 0.00079222 | 2041 | 0.053073 | 8251 | 4.2045e-05 | 5538
TASSAJARA 2112D569R | TASSAJARA 2112 | 14662112 |  | 2.4075 | 1.5761 |  | 41 | 0.00069246 | 3184 | 0.061112 | 6881 | 4.204e-05 | 5539
EL PATIO 1109XR568 | EL PATIO 1109 | 82921109 |  | 5.0683 | 3.8573 |  | 62.8333 | 0.00079213 | 2042 | 0.053073 | 8251 | 4.204e-05 | 5540
RIVERBANK 171690450 | RIVERBANK 1716 | 163191716 |  | 2.6921 | 1.5084 |  | 39.8333 | 0.00079209 | 2043 | 0.053073 | 8250 | 4.2038e-05 | 5541
LAS GALLINAS A 1104CB | LAS GALLINAS A 1104 | 42991104 |  | 5.3695 | 4.5622 |  | 83.6667 | 0.00077007 | 2256 | 0.054735 | 7798 | 4.2033e-05 | 5542
CASTROVILLE 2104CB | CASTROVILLE 2104 | 182352104 |  | 2.918 | 0.60412 |  | 54.1667 | 0.00067435 | 3380 | 0.063234 | 6641 | 4.2026e-05 | 5543
LAKEWOOD 210757670 | LAKEWOOD 2107 | 13532107 |  | 6.2944 | 5.1318 |  | 100 | 0.00069835 | 3125 | 0.059744 | 7046 | 4.2016e-05 | 5544
SAN RAMON 2104MR376 | SAN RAMON 2104 | 14232104 |  | 5.1607 | 4.424 |  | 79 | 0.00079154 | 2049 | 0.053073 | 8251 | 4.2009e-05 | 5545
LLAGAS 2103XR286 | LLAGAS 2103 | 83182103 |  | 1.2283 | 0.41389 |  | 25.5 | 0.00072349 | 2810 | 0.058396 | 7234 | 4.2007e-05 | 5546
PARSONS 0401CB | PARSONS 0401 | 13660401 |  | 1.3192 | 1.0208 |  | 15.25 | 0.00079146 | 2052 | 0.053073 | 8250 | 4.2005e-05 | 5547
PETALUMA C 1102CB | PETALUMA C 1102 | 42631102 |  | 3.8758 | 1.1865 |  | 62 | 0.00079002 | 2061 | 0.053192 | 8219 | 4.2e-05 | 5548
OAKLAND X 1114CR124 | OAKLAND X 1114 | 12541114 |  | 2.0168 | 2.2241 |  | 35.9167 | 0.00079107 | 2056 | 0.053073 | 8250 | 4.1984e-05 | 5549
STOCKDALE 21121466 | STOCKDALE 2112 | 254072112 |  | 3.3883 | 0.16906 |  | 58 | 0.00060573 | 4229 | 0.071466 | 4835 | 4.1981e-05 | 5550
EL PATIO 1112CB | EL PATIO 1112 | 82921112 |  | 5.0723 | 5.4608 |  | 75.8333 | 0.00079096 | 2057 | 0.053073 | 8251 | 4.1978e-05 | 5551
WYANDOTTE 110697550 | WYANDOTTE 1106 | 102911106 |  | 4.5568 | 0.50829 |  | 74 | 0.00063438 | 3885 | 0.066214 | 6231 | 4.196e-05 | 5552
REDWOOD CITY 1105CB | REDWOOD CITY 1105 | 24161105 |  | 6.2762 | 2.9873 |  | 91.0762 | 0.00079046 | 2058 | 0.053073 | 8250 | 4.1952e-05 | 5553
HOLLISTER 2103CB | HOLLISTER 2103 | 182492103 |  | 2.0214 | 1.3946 |  | 29.3333 | 0.00073402 | 2683 | 0.056317 | 7527 | 4.1949e-05 | 5554
LARKIN (Y) 112032934 | LARKIN (Y) 1120 | 22801120 |  | 2.1077 | 2.2136 |  | 25.1667 | 0.00079037 | 2059 | 0.053073 | 8250 | 4.1947e-05 | 5555
MANTECA 1705391150 | MANTECA 1705 | 162611705 |  | 0.16919 | 0.0036482 |  | 1.5 | 0.00057582 | 4580 | 0.072158 | 4760 | 4.1938e-05 | 5556
CARBONA 1102CB | CARBONA 1102 | 163091102 |  | 2.9479 | 0.14858 |  | 46.8333 | 0.0006947 | 3161 | 0.061201 | 6867 | 4.1935e-05 | 5557
VACA DIXON 1104CB | VACA DIXON 1104 | 63591104 |  | 2.9774 | 1.6255 |  | 47.7333 | 0.00071838 | 2871 | 0.059025 | 7156 | 4.1919e-05 | 5558
BELMONT 110281412 | BELMONT 1102 | 24031102 |  | 6.1503 | 4.3024 |  | 78.9167 | 0.00078961 | 2065 | 0.053073 | 8251 | 4.1907e-05 | 5559
LAKEWOOD 2226W505R | LAKEWOOD 2226 | 13532226 |  | 4.7187 | 3.7742 |  | 76 | 0.00066155 | 3555 | 0.063664 | 6587 | 4.1889e-05 | 5560
BURLINGAME 0405CB | BURLINGAME 0405 | 24050405 |  | 1.5244 | 1.3999 |  | 20.25 | 0.00078926 | 2067 | 0.053073 | 8252 | 4.1888e-05 | 5561
ALMADEN 1102743078 | ALMADEN 1102 | 82311102 |  | 1.8849 | 1.1297 |  | 27.6667 | 0.00078891 | 2070 | 0.053073 | 8251 | 4.1869e-05 | 5562
FMC 1105XR052 | FMC 1105 | 83871105 |  | 11.7996 | 12.121 |  | 178.5833 | 0.00078885 | 2071 | 0.053073 | 8251 | 4.1866e-05 | 5563
OAKLAND J 0409CB | OAKLAND J 0409 | 12090409 |  | 3.0383 | 2.5275 |  | 34.75 | 0.00078869 | 2073 | 0.053073 | 8251 | 4.1858e-05 | 5564
LONE TREE 2101CB | LONE TREE 2101 | 13232101 |  | 1.1501 | 0.35174 |  | 21.5 | 0.00066759 | 3461 | 0.065063 | 6423 | 4.1832e-05 | 5565
SANGER 1106CB | SANGER 1106 | 252351106 |  | 14.0138 | 11.1099 |  | 224.6667 | 0.00076191 | 2356 | 0.056867 | 7457 | 4.1822e-05 | 5566
OAKLAND J 0403CB | OAKLAND J 0403 | 12090403 |  | 6.269 | 5.5987 |  | 61.7 | 0.00078789 | 2075 | 0.053073 | 8254 | 4.1815e-05 | 5567
WOODSIDE 110179892 | WOODSIDE 1101 | 24251101 |  | 4.7163 | 2.0313 |  | 91.5 | 0.00062395 | 4010 | 0.067035 | 5972 | 4.181e-05 | 5568
LODI 110268142 | LODI 1102 | 162111102 |  | 13.6146 | 0.66505 |  | 141 | 0.00072239 | 2826 | 0.060527 | 6954 | 4.1797e-05 | 5569
MT EDEN 1112CB | MT EDEN 1112 | 13761112 |  | 3.6364 | 2.6686 |  | 58.4167 | 0.0007753 | 2199 | 0.053906 | 7974 | 4.1796e-05 | 5570
HUNTERS POINT (P) 1105CB | HUNTERS POINT (P) 1105 | 22331105 |  | 4.0955 | 2.735 |  | 50.4583 | 0.00078748 | 2079 | 0.053073 | 8251 | 4.1794e-05 | 5571
LAKEWOOD 222464093 | LAKEWOOD 2224 | 13532224 |  | 2.4829 | 0.92638 |  | 41.3333 | 0.00065125 | 3694 | 0.064671 | 6476 | 4.1791e-05 | 5572
LAKEWOOD 211021345 | LAKEWOOD 2110 | 13532110 |  | 1.1544 | 1.1124 |  | 24 | 0.00065042 | 3704 | 0.062963 | 6664 | 4.1783e-05 | 5573
MOUNTAIN VIEW 1104CB | MOUNTAIN VIEW 1104 | 82031104 |  | 3.661 | 2.8424 |  | 58.25 | 0.00078719 | 2080 | 0.053073 | 8251 | 4.1778e-05 | 5574
HAMMER 1103CB | HAMMER 1103 | 163301103 |  | 3.7548 | 4.1017 |  | 49.5 | 0.00078679 | 2083 | 0.053073 | 8251 | 4.1757e-05 | 5575
SARATOGA 1110XR574 | SARATOGA 1110 | 83371110 |  | 6.4019 | 7.6536 |  | 87.5 | 0.0007839 | 2111 | 0.053232 | 8205 | 4.1748e-05 | 5576
PACIFICA 1102934870 | PACIFICA 1102 | 22811102 | TRUE | 0.50074 | 0.24945 | 0.31996 | 10 | 0.00072661 | 2769 | 0.058291 | 7253 | 4.1745e-05 | 5577
DOS PALOS 1102CB | DOS PALOS 1102 | 254041102 |  | 0.18543 | 0 |  | 3 | 0.00053927 | 4965 | 0.0774 | 3397 | 4.1739e-05 | 5578
MEADOW LANE 210379492 | MEADOW LANE 2103 | 14302103 |  | 2.4065 | 1.201 |  | 41.8333 | 0.00078643 | 2087 | 0.053073 | 8251 | 4.1738e-05 | 5579
FORT ORD 21069136 | FORT ORD 2106 | 182402106 |  | 3.1821 | 1.9559 |  | 46.8333 | 0.00062274 | 4017 | 0.06703 | 5984 | 4.1732e-05 | 5580
ASHLAN AVE 1106R4494 | ASHLAN AVE 1106 | 252051106 |  | 4.0621 | 2.8071 |  | 65 | 0.0007662 | 2308 | 0.055505 | 7671 | 4.1731e-05 | 5581
MOUNTAIN VIEW 1108CB | MOUNTAIN VIEW 1108 | 82031108 |  | 3.5011 | 2.8198 |  | 55.5333 | 0.00078421 | 2107 | 0.053198 | 8217 | 4.173e-05 | 5582
EL CERRITO G 1107CB | EL CERRITO G 1107 | 12501107 |  | 3.5951 | 0 |  | 31.4 | 0.0007649 | 2329 | 0.055104 | 7735 | 4.1726e-05 | 5583
SF G 0402CB | SF G 0402 | 22090402 |  | 1.5612 | 0.55708 |  | 15.25 | 0.00077448 | 2209 | 0.054668 | 7810 | 4.1725e-05 | 5584
WAHTOKE 1109479598 | WAHTOKE 1109 | 254531109 |  | 3.275 | 1.1831 |  | 64 | 0.00066251 | 3537 | 0.064879 | 6453 | 4.1724e-05 | 5585
WOODLAND 1102CB | WOODLAND 1102 | 62031102 |  | 13.5073 | 6.8129 |  | 203 | 0.000759 | 2400 | 0.057112 | 7422 | 4.1723e-05 | 5586
SARATOGA 1103LC82 | SARATOGA 1103 | 83371103 |  | 2.1376 | 1.2414 |  | 43 | 0.00074453 | 2561 | 0.058269 | 7257 | 4.1719e-05 | 5587
STELLING 1108LL20 | STELLING 1108 | 83481108 |  | 4.2865 | 5.6691 |  | 61.3333 | 0.00070553 | 3034 | 0.059544 | 7080 | 4.1718e-05 | 5588
PUEBLO 2101654716 | PUEBLO 2101 | 43292101 |  | 2.7561 | 1.8724 |  | 52.5 | 0.00078601 | 2090 | 0.053073 | 8251 | 4.1716e-05 | 5589
LAKEWOOD 2110139484 | LAKEWOOD 2110 | 13532110 |  | 3.4147 | 1.1079 |  | 60.5 | 0.00065602 | 3625 | 0.063072 | 6655 | 4.1711e-05 | 5590
RIPON 1704464030 | RIPON 1704 | 163801704 |  | 1.5755 | 0.076992 |  | 34.5 | 0.00071128 | 2958 | 0.059482 | 7086 | 4.1708e-05 | 5591
SF E 0406CB | SF E 0406 | 22070406 |  | 1.4643 | 1.9866 |  | 23.0833 | 0.00078584 | 2093 | 0.053073 | 8251 | 4.1706e-05 | 5592
SALINAS 1106CB | SALINAS 1106 | 182011106 |  | 6.1932 | 4.7702 |  | 91.25 | 0.00078441 | 2104 | 0.053149 | 8233 | 4.1703e-05 | 5593
TYLER 1103CB | TYLER 1103 | 103571103 |  | 6.4039 | 2.5677 |  | 103 | 0.00068372 | 3288 | 0.061758 | 6792 | 4.1702e-05 | 5594
SAN JOSE B 110769776 | SAN JOSE B 1107 | 82261107 |  | 2.7222 | 3.2953 |  | 40.6667 | 0.00078566 | 2094 | 0.053073 | 8251 | 4.1697e-05 | 5595
ELECTRA 110213414 | ELECTRA 1102 | 162161102 |  | 0.011364 | 0 |  | 0.5 | 0.00062198 | 4025 | 0.067035 | 5975 | 4.1694e-05 | 5596
MABURY 1103CB | MABURY 1103 | 82191103 |  | 3.158 | 1.4309 |  | 48.5833 | 0.00078559 | 2095 | 0.053073 | 8250 | 4.1693e-05 | 5597
BRENTWOOD 210556344 | BRENTWOOD 2105 | 14592105 |  | 3.8024 | 0.59427 |  | 63 | 0.00062431 | 4007 | 0.06704 | 5959 | 4.1678e-05 | 5598
SARANAP 0401CB | SARANAP 0401 | 13560401 |  | 2.4568 | 1.4629 |  | 35 | 0.00068527 | 3273 | 0.060567 | 6948 | 4.1675e-05 | 5599
WATERLOO 11022964 | WATERLOO 1102 | 163151102 |  | 2.6691 | 0.61805 |  | 43.5 | 0.00066235 | 3540 | 0.066088 | 6250 | 4.1675e-05 | 5600
EDES 1113CB | EDES 1113 | 13681113 |  | 3.7833 | 0.43066 |  | 66.5 | 0.00077817 | 2166 | 0.053804 | 7998 | 4.1674e-05 | 5601
SERRAMONTE 110412705 | SERRAMONTE 1104 | 22861104 |  | 5.8178 | 5.2382 |  | 72 | 0.00067137 | 3424 | 0.059217 | 7125 | 4.1671e-05 | 5602
DEL MONTE 110195818 | DEL MONTE 1101 | 182221101 |  | 2.4748 | 2.727 |  | 34.0833 | 0.00078502 | 2098 | 0.053073 | 8250 | 4.1663e-05 | 5603
KERN OIL 11102852 | KERN OIL 1110 | 252721110 |  | 2.9326 | 3.0716 |  | 51.3333 | 0.00078498 | 2099 | 0.053073 | 8250 | 4.1661e-05 | 5604
MABURY 1106XR116 | MABURY 1106 | 82191106 |  | 3.9947 | 5.6954 |  | 65.3333 | 0.00074677 | 2525 | 0.055737 | 7632 | 4.166e-05 | 5605
HALF MOON BAY 110264293 | HALF MOON BAY 1102 | 24101102 |  | 1.8863 | 1.1679 |  | 29 | 0.00066557 | 3487 | 0.061896 | 6776 | 4.165e-05 | 5606
VALLEJO B 0414CB | VALLEJO B 0414 | 42450414 |  | 8.3144 | 7.1825 |  | 104.2833 | 0.00078457 | 2101 | 0.053073 | 8251 | 4.1639e-05 | 5607
LOS OSITOS 2103CB | LOS OSITOS 2103 | 182082103 |  | 0.13374 | 0 |  | 1.25 | 0.00062134 | 4035 | 0.067 | 6057 | 4.163e-05 | 5608
STELLING 1113LL24 | STELLING 1113 | 83481113 |  | 3.0334 | 2.4869 |  | 38.8333 | 0.00078423 | 2106 | 0.053073 | 8251 | 4.1621e-05 | 5609
EL PATIO 1103XR022 | EL PATIO 1103 | 82921103 |  | 6.482 | 6.6575 |  | 95.1667 | 0.00078417 | 2108 | 0.053073 | 8250 | 4.1618e-05 | 5610
MANTECA 1708878023 | MANTECA 1708 | 162611708 |  | 2.1684 | 0.17869 |  | 34.3333 | 0.00070567 | 3032 | 0.058823 | 7181 | 4.1617e-05 | 5611
WHISMAN 1102CB | WHISMAN 1102 | 83631102 |  | 1.7943 | 0 |  | 30.3333 | 0.00078389 | 2112 | 0.053073 | 8252 | 4.1603e-05 | 5612
CASTRO VALLEY 1108MR215 | CASTRO VALLEY 1108 | 14091108 |  | 1.4226 | 1.3587 |  | 18.5 | 0.00078386 | 2113 | 0.053073 | 8250 | 4.1601e-05 | 5613
HALF MOON BAY 11039112 | HALF MOON BAY 1103 | 24101103 |  | 4.1909 | 0.58786 |  | 73 | 0.0006451 | 3765 | 0.064965 | 6443 | 4.1596e-05 | 5614
VALLEY VIEW 1105P190 | VALLEY VIEW 1105 | 14341105 | TRUE | 2.0442 | 1.7918 | 0.019627 | 37.3333 | 0.00052129 | 5164 | 0.072986 | 4664 | 4.1582e-05 | 5615
POTRERO PP (A) 11176695 | POTRERO PP (A) 1117 | 22031117 |  | 3.9579 | 3.5848 |  | 45.8667 | 0.00078344 | 2114 | 0.053073 | 8252 | 4.1579e-05 | 5616
SAN LEANDRO U 1113MR203 | SAN LEANDRO U 1113 | 13111113 |  | 0.095599 | 0 |  | 2 | 0.00078335 | 2116 | 0.053073 | 8251 | 4.1575e-05 | 5617
EVERGREEN 2105XR170 | EVERGREEN 2105 | 82012105 |  | 2.03 | 0.59326 |  | 38 | 0.00077818 | 2165 | 0.053247 | 8198 | 4.1573e-05 | 5618
MISSION (X) 111342336 | MISSION (X) 1113 | 22011113 |  | 1.2636 | 1.0173 |  | 12.0833 | 0.00078314 | 2118 | 0.053073 | 8251 | 4.1563e-05 | 5619
DIXON LANDING 2101XR590 | DIXON LANDING 2101 | 14722101 |  | 2.0879 | 1.5034 |  | 32.3333 | 0.00078304 | 2120 | 0.053073 | 8252 | 4.1558e-05 | 5620
DEL MAR 21051270 | DEL MAR 2105 | 152582105 |  | 0.0063734 | 0 |  | 0.5 | 0.000783 | 2121 | 0.053073 | 8251 | 4.1556e-05 | 5621
SAN LEANDRO U 1114CB | SAN LEANDRO U 1114 | 13111114 |  | 4.4067 | 3.6418 |  | 60 | 0.00076084 | 2372 | 0.054581 | 7833 | 4.1551e-05 | 5622
NORTH TOWER 1108CB | NORTH TOWER 1108 | 42041108 |  | 1.8864 | 0.11875 |  | 20.1167 | 0.00060727 | 4206 | 0.068548 | 5276 | 4.155e-05 | 5623
DUNBAR 1102264 | DUNBAR 1102 | 43071102 |  | 3.851 | 2.9056 |  | 55.5 | 0.0007326 | 2701 | 0.056972 | 7441 | 4.1548e-05 | 5624
SALINAS 110624521 | SALINAS 1106 | 182011106 |  | 2.0023 | 2.3249 |  | 32 | 0.00078278 | 2122 | 0.053073 | 8251 | 4.1544e-05 | 5625
COLUMBUS 11094443 | COLUMBUS 1109 | 253951109 |  | 3.875 | 0.83176 |  | 68.5 | 0.00072501 | 2790 | 0.057837 | 7319 | 4.1543e-05 | 5626
ALMADEN 1102XR278 | ALMADEN 1102 | 82311102 |  | 1.3431 | 0.5583 |  | 21.8333 | 0.00078268 | 2123 | 0.053073 | 8251 | 4.1539e-05 | 5627
AIRWAYS 1106CB | AIRWAYS 1106 | 252041106 |  | 1.7899 | 0.36792 |  | 33.5 | 0.00076776 | 2284 | 0.054419 | 7860 | 4.1537e-05 | 5628
YOSEMITE 0401CB | YOSEMITE 0401 | 22490401 |  | 3.5538 | 3.2435 |  | 49.6667 | 0.00078256 | 2124 | 0.053073 | 8253 | 4.1532e-05 | 5629
REDWOOD CITY 0409CB | REDWOOD CITY 0409 | 24160409 |  | 4.9693 | 4.0188 |  | 61.4095 | 0.00076569 | 2316 | 0.054093 | 7934 | 4.153e-05 | 5630
MALAGA 1105CB | MALAGA 1105 | 254251105 |  | 0.64456 | 0 |  | 9.8333 | 0.00070051 | 3091 | 0.063431 | 6619 | 4.1529e-05 | 5631
EVERGREEN 2103CB | EVERGREEN 2103 | 82012103 |  | 6.1777 | 3.5214 |  | 70.3333 | 0.00076168 | 2358 | 0.054657 | 7813 | 4.1515e-05 | 5632
DAVIS 110123072 | DAVIS 1101 | 62041101 |  | 0.95184 | 0.63144 |  | 16 | 0.00078218 | 2128 | 0.053073 | 8251 | 4.1512e-05 | 5633
LAS POSITAS 2107CB | LAS POSITAS 2107 | 14402107 |  | 5.4713 | 0.81974 |  | 87.5 | 0.00070259 | 3071 | 0.058166 | 7272 | 4.1511e-05 | 5634
STOREY 110799922 | STOREY 1107 | 254611107 |  | 3.4271 | 3.2981 |  | 53 | 0.00075927 | 2397 | 0.056056 | 7574 | 4.1511e-05 | 5635
SWIFT 2107CB | SWIFT 2107 | 83392107 |  | 1.9195 | 1.265 |  | 36.3333 | 0.00078213 | 2129 | 0.053073 | 8251 | 4.151e-05 | 5636
MT EDEN 1101CB | MT EDEN 1101 | 13761101 |  | 1.3489 | 1.3412 |  | 19.7 | 0.00078206 | 2130 | 0.053073 | 8251 | 4.1506e-05 | 5637
SANTA MARIA 1108CB | SANTA MARIA 1108 | 182671108 |  | 6.2427 | 4.047 |  | 98.8333 | 0.00077289 | 2231 | 0.053804 | 7999 | 4.149e-05 | 5638
CALISTOGA 1101134232 | CALISTOGA 1101 | 42711101 |  | 2.9072 | 0.55866 |  | 54.5 | 0.00061415 | 4119 | 0.067735 | 5497 | 4.1483e-05 | 5639
RICHMOND R 1129BR224 | RICHMOND R 1129 | 13471129 |  | 1.0246 | 0.064034 |  | 18.5 | 0.00067001 | 3435 | 0.061757 | 6793 | 4.1481e-05 | 5640
WHISMAN 1101CB | WHISMAN 1101 | 83631101 |  | 5.0893 | 0 |  | 65.7833 | 0.00072198 | 2832 | 0.057833 | 7322 | 4.1477e-05 | 5641
MC KEE 1109CB | MC KEE 1109 | 83531109 |  | 1.7658 | 1.1751 |  | 37.3333 | 0.00078151 | 2135 | 0.053073 | 8250 | 4.1477e-05 | 5642
WEEDPATCH 11024106 | WEEDPATCH 1102 | 252971102 |  | 4.7169 | 1.4688 |  | 72 | 0.0006323 | 3913 | 0.065764 | 6309 | 4.1473e-05 | 5643
MOLINO 11015034 | MOLINO 1101 | 42571101 |  | 4.3697 | 2.9678 |  | 75 | 0.00067311 | 3400 | 0.061522 | 6828 | 4.1456e-05 | 5644
BERKELEY F 1104CB | BERKELEY F 1104 | 12061104 |  | 0.044406 | 0 |  | 0.66667 | 0.00078102 | 2140 | 0.053073 | 8251 | 4.1451e-05 | 5645
HUNTERS POINT (P) 110212301 | HUNTERS POINT (P) 1102 | 22331102 |  | 3.7674 | 5.7202 |  | 65.5833 | 0.00078096 | 2141 | 0.053073 | 8252 | 4.1448e-05 | 5646
OAKLAND L 1106CB | OAKLAND L 1106 | 12111106 |  | 0.34579 | 0.13384 |  | 11 | 0.00078079 | 2143 | 0.053073 | 8251 | 4.1438e-05 | 5647
SF J 0406CB | SF J 0406 | 22220406 |  | 0.51437 | 0.66827 |  | 9 | 0.00078072 | 2144 | 0.053073 | 8251 | 4.1435e-05 | 5648
CASTROVILLE 210422316 | CASTROVILLE 2104 | 182352104 |  | 0.017378 | 0 |  | 1 | 0.00078067 | 2145 | 0.053073 | 8251 | 4.1432e-05 | 5649
EAST STOCKTON 110214316 | EAST STOCKTON 1102 | 163131102 |  | 8.23 | 5.9047 |  | 105.75 | 0.00078055 | 2146 | 0.053073 | 8251 | 4.1426e-05 | 5650
MT EDEN 1101MR618 | MT EDEN 1101 | 13761101 |  | 2.1624 | 1.5711 |  | 30.0833 | 0.00078046 | 2147 | 0.053073 | 8251 | 4.1421e-05 | 5651
KERN POWER 21052256 | KERN POWER 2105 | 255262105 |  | 3.6082 | 1.2503 |  | 54.5 | 0.00071965 | 2857 | 0.058206 | 7267 | 4.1421e-05 | 5652
RED BLUFF 1103CB | RED BLUFF 1103 | 103541103 | TRUE | 19.6371 | 9.073 | 0.086784 | 335.4167 | 0.00062449 | 4004 | 0.071092 | 4885 | 4.1412e-05 | 5653
SOTO 0402CB | SOTO 0402 | 13260402 |  | 2.0517 | 1.8093 |  | 30.1667 | 0.00075321 | 2452 | 0.055227 | 7717 | 4.1407e-05 | 5654
WOODWARD 2106CB | WOODWARD 2106 | 255292106 |  | 0.29443 | 0.0075625 |  | 9 | 0.00063316 | 3900 | 0.066588 | 6172 | 4.1405e-05 | 5655
EL CERRITO G 1113BR120 | EL CERRITO G 1113 | 12501113 |  | 1.6081 | 1.0918 |  | 15.95 | 0.00078014 | 2148 | 0.053073 | 8253 | 4.1404e-05 | 5656
SONOMA 1102CB | SONOMA 1102 | 42721102 |  | 8.3223 | 5.32 |  | 157.5 | 0.0007502 | 2476 | 0.05536 | 7693 | 4.1398e-05 | 5657
LARKIN (Y) 111012459 | LARKIN (Y) 1110 | 22801110 |  | 0.19469 | 0.15168 |  | 4.5833 | 0.00077994 | 2149 | 0.053073 | 8252 | 4.1393e-05 | 5658
NOVATO 1103CB | NOVATO 1103 | 42211103 |  | 2.9466 | 1.881 |  | 51.3333 | 0.00074551 | 2538 | 0.056333 | 7524 | 4.1391e-05 | 5659
WEST FRESNO 1110CB | WEST FRESNO 1110 | 253731110 |  | 5.8294 | 2.2963 |  | 100.375 | 0.00065482 | 3642 | 0.065255 | 6398 | 4.1383e-05 | 5660
SARATOGA 1112XR140 | SARATOGA 1112 | 83371112 |  | 3.8002 | 4.8884 |  | 61.5 | 0.00077967 | 2151 | 0.053073 | 8251 | 4.1379e-05 | 5661
SWIFT 2106918614 | SWIFT 2106 | 83392106 |  | 3.2455 | 3.0514 |  | 42.6667 | 0.00077953 | 2152 | 0.053073 | 8251 | 4.1372e-05 | 5662
MEADOW LANE 2108PH401/2 | MEADOW LANE 2108 | 14302108 |  | 4.3522 | 3.5823 |  | 62.1667 | 0.00070395 | 3055 | 0.059018 | 7158 | 4.1369e-05 | 5663
BULLARD 110133906 | BULLARD 1101 | 253961101 |  | 1.5116 | 0.19632 |  | 21.5 | 0.00077946 | 2153 | 0.053073 | 8251 | 4.1368e-05 | 5664
NEWARK 12KV 1107CB | NEWARK 12KV 1107 | 12221107 |  | 4.0624 | 2.6102 |  | 60.75 | 0.00074205 | 2583 | 0.057211 | 7405 | 4.1361e-05 | 5665
SALMON CREEK 1101460 | SALMON CREEK 1101 | 43161101 |  | 2.5467 | 1.2452 |  | 41 | 0.00063017 | 3941 | 0.066012 | 6271 | 4.1361e-05 | 5666
BERKELEY F 1105BR100 | BERKELEY F 1105 | 12061105 |  | 1.5695 | 1.7144 |  | 27.3333 | 0.00066733 | 3463 | 0.061769 | 6790 | 4.1357e-05 | 5667
SALINAS 110322382 | SALINAS 1103 | 182011103 |  | 2.7065 | 3.0326 |  | 36.8333 | 0.00077918 | 2156 | 0.053073 | 8251 | 4.1353e-05 | 5668
NOTRE DAME 1104937710 | NOTRE DAME 1104 | 102041104 | TRUE | 1.4121 | 0.030728 | 0.40498 | 27.5 | 0.00011348 | 10993 | 0.48724 | 2837 | 4.1353e-05 | 5669
OAKLAND X 1112CR116 | OAKLAND X 1112 | 12541112 |  | 1.6706 | 1.6957 |  | 20 | 0.00077903 | 2157 | 0.053073 | 8251 | 4.1345e-05 | 5670
LINCOLN 2108CB | LINCOLN 2108 | 153702108 |  | 1.8066 | 0.038754 |  | 37 | 0.00062799 | 3970 | 0.066059 | 6257 | 4.1345e-05 | 5671
SONOMA 11053742 | SONOMA 1105 | 42721105 |  | 2.7519 | 1.5816 |  | 46.5 | 0.00064967 | 3710 | 0.063741 | 6573 | 4.134e-05 | 5672
OAKLAND C 1109CR142 | OAKLAND C 1109 | 12011109 |  | 2.6661 | 2.1513 |  | 47.1667 | 0.00077876 | 2159 | 0.053073 | 8251 | 4.1331e-05 | 5673
ASHLAN AVE 1104R3310 | ASHLAN AVE 1104 | 252051104 |  | 5.9026 | 5.2989 |  | 92.5 | 0.00076208 | 2352 | 0.054651 | 7815 | 4.1325e-05 | 5674
WOLFE 1105CB | WOLFE 1105 | 83671105 |  | 4.2624 | 5.3907 |  | 71.8333 | 0.00075077 | 2473 | 0.055399 | 7687 | 4.1322e-05 | 5675
PAUL SWEET 210793260 | PAUL SWEET 2107 | 83252107 |  | 3.4545 | 2.3811 |  | 53.6667 | 0.00076369 | 2337 | 0.055017 | 7749 | 4.1318e-05 | 5676
BAY MEADOWS 11049124 | BAY MEADOWS 1104 | 24011104 |  | 2.624 | 2.0301 |  | 36.3333 | 0.0007785 | 2162 | 0.053073 | 8250 | 4.1317e-05 | 5677
BULLARD 110182586 | BULLARD 1101 | 253961101 |  | 2.3287 | 2.2041 |  | 31.8333 | 0.00077785 | 2171 | 0.053343 | 8159 | 4.1316e-05 | 5678
OAKLAND C 1119CR286 | OAKLAND C 1119 | 12011119 |  | 0.01433 | 0 |  | 1.3333 | 0.00077849 | 2163 | 0.053073 | 8251 | 4.1316e-05 | 5679
BAY MEADOWS 1105265162 | BAY MEADOWS 1105 | 24011105 |  | 2.5446 | 0.701 |  | 36 | 0.00077844 | 2164 | 0.053073 | 8251 | 4.1314e-05 | 5680
AIRWAYS 1103R2030 | AIRWAYS 1103 | 252041103 |  | 2.5204 | 2.2134 |  | 37.8333 | 0.00077688 | 2186 | 0.0533 | 8178 | 4.1314e-05 | 5681
FORT BRAGG A 1103CB | FORT BRAGG A 1103 | 42761103 | TRUE | 2.6196 | 1.293 | 0.0068674 | 48.0833 | 0.00053783 | 4979 | 0.10389 | 3306 | 4.1312e-05 | 5682
TRINIDAD 1101495696 | TRINIDAD 1101 | 192231101 |  | 9.3508 | 2.6411 |  | 176 | 0.00061656 | 4093 | 0.067004 | 6038 | 4.1312e-05 | 5683
DUNBAR 1101835658 | DUNBAR 1101 | 43071101 | TRUE | 0.73982 | 0.49586 | 0.092253 | 13.5 | 0.00061086 | 4156 | 0.067663 | 5522 | 4.1309e-05 | 5684
WILLOWS A 1104CB | WILLOWS A 1104 | 102741104 |  | 9.3873 | 6.6572 |  | 153.95 | 0.00073681 | 2656 | 0.056464 | 7506 | 4.1306e-05 | 5685
FAIRWAY 1106CB | FAIRWAY 1106 | 182061106 |  | 5.5162 | 0.36939 |  | 79.8333 | 0.0006645 | 3507 | 0.062564 | 6706 | 4.1302e-05 | 5686
EL PATIO 110447296 | EL PATIO 1104 | 82921104 |  | 2.1213 | 1.401 |  | 32.3333 | 0.00077815 | 2167 | 0.053073 | 8252 | 4.1298e-05 | 5687
ARBUCKLE 1102247832 | ARBUCKLE 1102 | 62081102 |  | 0.017718 | 0 |  | 0.5 | 0.00053357 | 5034 | 0.0774 | 3397 | 4.1298e-05 | 5688
JARVIS 1103MR245 | JARVIS 1103 | 13501103 |  | 0.76754 | 0.40369 |  | 10.8333 | 0.0007781 | 2168 | 0.053073 | 8250 | 4.1296e-05 | 5689
VASONA 110548314 | VASONA 1105 | 83771105 |  | 2.8999 | 2.4571 |  | 43 | 0.00077808 | 2169 | 0.053073 | 8251 | 4.1295e-05 | 5690
HICKS 2111255740 | HICKS 2111 | 83432111 |  | 1.8115 | 0.44224 |  | 33 | 0.00064815 | 3728 | 0.064497 | 6487 | 4.1286e-05 | 5691
ANDERSON 11029792 | ANDERSON 1102 | 103261102 |  | 2.3417 | 1.3379 |  | 43.5 | 0.00072727 | 2757 | 0.056511 | 7502 | 4.1284e-05 | 5692
OAKLAND X 1103CB | OAKLAND X 1103 | 12541103 |  | 2.4469 | 2.9292 |  | 26.75 | 0.00077783 | 2172 | 0.053073 | 8250 | 4.1281e-05 | 5693
RINCON 1102644 | RINCON 1102 | 43321102 |  | 8.1224 | 3.8581 |  | 153 | 0.00066868 | 3447 | 0.061873 | 6780 | 4.1279e-05 | 5694
MANTECA 170636142 | MANTECA 1706 | 162611706 |  | 3.5365 | 3.3757 |  | 47.3333 | 0.00077777 | 2175 | 0.053073 | 8251 | 4.1278e-05 | 5695
18TH STREET 0402CB | 18TH STREET 0402 | 22390402 |  | 1.8168 | 1.7684 |  | 28.6667 | 0.00072623 | 2774 | 0.056891 | 7452 | 4.1276e-05 | 5696
LOGAN CREEK 210137352 | LOGAN CREEK 2101 | 103142101 |  | 0.88338 | 0.10686 |  | 13.5 | 0.00057154 | 4636 | 0.075015 | 4411 | 4.1275e-05 | 5697
COTATI 110257108 | COTATI 1102 | 42271102 |  | 0.35941 | 0 |  | 8.5 | 0.00077757 | 2178 | 0.053073 | 8251 | 4.1268e-05 | 5698
KERN POWER 2105CB | KERN POWER 2105 | 255262105 |  | 5.586 | 1.0135 |  | 84.1833 | 0.00068246 | 3302 | 0.063046 | 6658 | 4.1265e-05 | 5699
SAN RAFAEL 11023997 | SAN RAFAEL 1102 | 42011102 |  | 0.32514 | 0.06472 |  | 5.8333 | 0.00077735 | 2181 | 0.053073 | 8251 | 4.1256e-05 | 5700
LAS POSITAS 2107MR199 | LAS POSITAS 2107 | 14402107 |  | 3.4392 | 0.4693 |  | 64.5 | 0.00062678 | 3984 | 0.066411 | 6203 | 4.1249e-05 | 5701
VIERRA 1702593096 | VIERRA 1702 | 162701702 |  | 2.0626 | 0.47174 |  | 34.5 | 0.00060225 | 4274 | 0.068482 | 5290 | 4.1242e-05 | 5702
NEWARK 12KV 110792040 | NEWARK 12KV 1107 | 12221107 |  | 0.042476 | 0 |  | 0.33333 | 0.00077698 | 2185 | 0.053073 | 8251 | 4.1237e-05 | 5703
WHISMAN 1106CB | WHISMAN 1106 | 83631106 |  | 3.7741 | 2.2989 |  | 59.5 | 0.00077684 | 2187 | 0.053073 | 8251 | 4.1229e-05 | 5704
EL CERRITO G 1103BR124 | EL CERRITO G 1103 | 12501103 |  | 2.3172 | 1.1148 |  | 39.3333 | 0.00076894 | 2276 | 0.053691 | 8034 | 4.1224e-05 | 5705
MABURY 1104286586 | MABURY 1104 | 82191104 |  | 4.8732 | 5.4486 |  | 65.4167 | 0.00077166 | 2241 | 0.053445 | 8112 | 4.122e-05 | 5706
EVERGREEN 2105XR094 | EVERGREEN 2105 | 82012105 |  | 0.27427 | 0.035297 |  | 6.5 | 0.00077661 | 2188 | 0.053073 | 8251 | 4.1217e-05 | 5707
OAKLAND J 1118CR134 | OAKLAND J 1118 | 12091118 |  | 4.1566 | 4.6799 |  | 51.3333 | 0.00077628 | 2191 | 0.053073 | 8252 | 4.1199e-05 | 5708
BELL 1108CB | BELL 1108 | 152701108 |  | 5.9947 | 1.5103 |  | 98.75 | 0.00062934 | 3950 | 0.066436 | 6198 | 4.1188e-05 | 5709
MT EDEN 1112MR246 | MT EDEN 1112 | 13761112 |  | 0.71557 | 0.23423 |  | 13 | 0.0007759 | 2195 | 0.053073 | 8251 | 4.1179e-05 | 5710
NAPA 1106CB | NAPA 1106 | 42021106 |  | 1.2397 | 0.65597 |  | 24.8333 | 0.00077577 | 2197 | 0.053073 | 8251 | 4.1172e-05 | 5711
STELLING 1109CB | STELLING 1109 | 83481109 |  | 8.0879 | 6.4596 |  | 131 | 0.00072972 | 2731 | 0.057583 | 7346 | 4.1168e-05 | 5712
SONOMA 1105CB | SONOMA 1105 | 42721105 |  | 7.0642 | 1.4723 |  | 124 | 0.0006227 | 4018 | 0.065932 | 6285 | 4.1159e-05 | 5713
ERTA 04045308 | ERTA 0404 | 83510404 |  | 1.2068 | 0.53621 |  | 12.1667 | 0.00061432 | 4114 | 0.067 | 6059 | 4.1159e-05 | 5714
BORDEN 110285930 | BORDEN 1102 | 255121102 |  | 3.6212 | 0.49654 |  | 59.5 | 0.0005718 | 4632 | 0.073047 | 4656 | 4.1153e-05 | 5715
PACIFIC GROVE 0423CB | PACIFIC GROVE 0423 | 182440423 |  | 1.6772 | 1.9675 |  | 19.3333 | 0.00077517 | 2200 | 0.053073 | 8252 | 4.1141e-05 | 5716
DALY CITY 110457240 | DALY CITY 1104 | 22641104 |  | 2.6972 | 2.3783 |  | 36.6667 | 0.00077516 | 2202 | 0.053073 | 8252 | 4.114e-05 | 5717
GLENWOOD 110280757 | GLENWOOD 1102 | 24091102 |  | 5.9226 | 3.8098 |  | 92 | 0.00073088 | 2719 | 0.056327 | 7525 | 4.1136e-05 | 5718
POTRERO PP (A) 1116CB | POTRERO PP (A) 1116 | 22031116 |  | 2.2181 | 2.757 |  | 31.9167 | 0.00077498 | 2204 | 0.053073 | 8250 | 4.113e-05 | 5719
SUISUN 1108CB | SUISUN 1108 | 62131108 |  | 6.5941 | 6.813 |  | 113.5 | 0.00077489 | 2205 | 0.053073 | 8251 | 4.1126e-05 | 5720
ARCATA 11211206 | ARCATA 1121 | 192021121 |  | 4.3651 | 0.78263 |  | 78 | 0.00061381 | 4124 | 0.067 | 6057 | 4.1125e-05 | 5721
STONE 1110CB | STONE 1110 | 83701110 |  | 7.1345 | 6.1162 |  | 111.1667 | 0.00077479 | 2206 | 0.053073 | 8250 | 4.112e-05 | 5722
GRANT 1107CB | GRANT 1107 | 14381107 |  | 2.7736 | 0.58996 |  | 53.5 | 0.00064764 | 3736 | 0.06438 | 6498 | 4.1112e-05 | 5723
ATWATER 1104CB | ATWATER 1104 | 253611104 |  | 3.3602 | 0.35561 |  | 53.0833 | 0.00065695 | 3611 | 0.065446 | 6369 | 4.1111e-05 | 5724
PAUL SWEET 210737234 | PAUL SWEET 2107 | 83252107 |  | 1.5174 | 0.26271 |  | 18.2 | 0.00066376 | 3515 | 0.062638 | 6697 | 4.1109e-05 | 5725
LAS POSITAS 2106MR149 | LAS POSITAS 2106 | 14402106 |  | 13.1806 | 13.1415 |  | 195.3333 | 0.00073933 | 2607 | 0.055657 | 7647 | 4.1107e-05 | 5726
STONE 110141435 | STONE 1101 | 83701101 |  | 3.2537 | 4.0063 |  | 51 | 0.00077427 | 2212 | 0.053073 | 8251 | 4.1093e-05 | 5727
SAN JOSE B 1110XR306 | SAN JOSE B 1110 | 82261110 |  | 3.2275 | 3.351 |  | 45.3333 | 0.0007739 | 2216 | 0.053073 | 8250 | 4.1073e-05 | 5728
SAN LEANDRO U 1104CB | SAN LEANDRO U 1104 | 13111104 |  | 6.2604 | 5.4123 |  | 92.5833 | 0.0007738 | 2218 | 0.053073 | 8251 | 4.1067e-05 | 5729
TIDEWATER 210447828 | TIDEWATER 2104 | 14652104 |  | 2.754 | 2.6352 |  | 41.5 | 0.00077371 | 2219 | 0.053073 | 8251 | 4.1063e-05 | 5730
LAKEWOOD 2111CB | LAKEWOOD 2111 | 13532111 |  | 2.2868 | 1.446 |  | 35.0833 | 0.00077362 | 2220 | 0.053073 | 8252 | 4.1058e-05 | 5731
OAKLAND D 1133CB | OAKLAND D 1133 | 12041133 |  | 2.2454 | 2.598 |  | 28 | 0.00077361 | 2221 | 0.053073 | 8251 | 4.1058e-05 | 5732
STELLING 1112CB | STELLING 1112 | 83481112 |  | 2.1873 | 1.9312 |  | 33.3333 | 0.00077359 | 2222 | 0.053073 | 8250 | 4.1057e-05 | 5733
MT EDEN 1111CB | MT EDEN 1111 | 13761111 |  | 3.2378 | 1.5153 |  | 52.9 | 0.00077337 | 2225 | 0.053073 | 8251 | 4.1045e-05 | 5734
SHEPHERD 2109CB | SHEPHERD 2109 | 252062109 |  | 4.3552 | 0.70324 |  | 82 | 0.00061435 | 4113 | 0.069952 | 5056 | 4.1042e-05 | 5735
EL CERRITO G 1112807878 | EL CERRITO G 1112 | 12501112 |  | 0.0086224 | 0 |  | 0.2 | 0.0007732 | 2226 | 0.053073 | 8251 | 4.1036e-05 | 5736
SUISUN 1109CB | SUISUN 1109 | 62131109 |  | 8.0735 | 7.4667 |  | 118.6667 | 0.0007732 | 2227 | 0.053073 | 8250 | 4.1036e-05 | 5737
LAKEVILLE 1102280 | LAKEVILLE 1102 | 43371102 | TRUE | 8.969 | 0.2174 | 0.50833 | 182.5 | 0.00018045 | 10347 | 0.42472 | 2889 | 4.1035e-05 | 5738
TIDEWATER 210487978 | TIDEWATER 2104 | 14652104 |  | 1.6443 | 0.5653 |  | 30.3333 | 0.00069544 | 3156 | 0.061273 | 6859 | 4.1032e-05 | 5739
VASONA 1101LC56 | VASONA 1101 | 83771101 |  | 2.3362 | 1.2915 |  | 33 | 0.00077304 | 2230 | 0.053073 | 8251 | 4.1027e-05 | 5740
RIVERBANK 1716412688 | RIVERBANK 1716 | 163191716 |  | 1.7424 | 0.20756 |  | 31 | 0.00075573 | 2426 | 0.055704 | 7640 | 4.1021e-05 | 5741
BRITTON 1108CB | BRITTON 1108 | 83611108 |  | 1.7277 | 0 |  | 16 | 0.00077287 | 2232 | 0.053073 | 8254 | 4.1018e-05 | 5742
LAKEWOOD 2224W544R | LAKEWOOD 2224 | 13532224 |  | 5.3248 | 4.006 |  | 95.3333 | 0.00063634 | 3866 | 0.064195 | 6519 | 4.1001e-05 | 5743
STONE 1108CB | STONE 1108 | 83701108 |  | 4.3987 | 2.6138 |  | 89.1667 | 0.0007446 | 2559 | 0.055884 | 7598 | 4.0998e-05 | 5744
SANTA ROSA A 1109CB | SANTA ROSA A 1109 | 42151109 |  | 5.8884 | 5.107 |  | 98.8333 | 0.00075205 | 2460 | 0.054851 | 7781 | 4.0991e-05 | 5745
SAUSALITO 11011270 | SAUSALITO 1101 | 42491101 |  | 0.32421 | 0.16606 |  | 4.1667 | 0.00064854 | 3722 | 0.063379 | 6623 | 4.099e-05 | 5746
MERCED 21027050 | MERCED 2102 | 252802102 |  | 3.8068 | 3.8085 |  | 72.3333 | 0.00077212 | 2237 | 0.053073 | 8252 | 4.0979e-05 | 5747
SAN CARLOS 0405CB | SAN CARLOS 0405 | 24180405 |  | 8.1716 | 6.237 |  | 106.2595 | 0.00073987 | 2598 | 0.055334 | 7702 | 4.0978e-05 | 5748
WOODLAND 110722312 | WOODLAND 1107 | 62031107 |  | 0.012784 | 0 |  | 1.5 | 0.00077195 | 2238 | 0.053073 | 8251 | 4.097e-05 | 5749
CALISTOGA 1101959538 | CALISTOGA 1101 | 42711101 | TRUE | 2.5803 | 0.75477 | 0.077659 | 48 | 0.00060398 | 4256 | 0.067834 | 5464 | 4.0969e-05 | 5750
GRANT 110281924 | GRANT 1102 | 14381102 |  | 0.37095 | 0 |  | 7 | 0.00077189 | 2239 | 0.053073 | 8251 | 4.0966e-05 | 5751
KIRKER 2105A536R | KIRKER 2105 | 14452105 |  | 0.76544 | 0.10387 |  | 16 | 0.00071398 | 2924 | 0.061319 | 6850 | 4.0954e-05 | 5752
LARKIN (Y) 1107907142 | LARKIN (Y) 1107 | 22801107 |  | 1.1139 | 1.3076 |  | 19.8333 | 0.00077155 | 2243 | 0.053073 | 8252 | 4.0948e-05 | 5753
CORONA 1103CB | CORONA 1103 | 43491103 |  | 0.75741 | 0.12198 |  | 20 | 0.00072614 | 2777 | 0.058288 | 7255 | 4.0947e-05 | 5754
HILLSDALE 040485812 | HILLSDALE 0404 | 24110404 |  | 5.669 | 3.7971 |  | 67.2833 | 0.00055524 | 4816 | 0.067927 | 5424 | 4.0935e-05 | 5755
EAST GRAND 110776054 | EAST GRAND 1107 | 22571107 |  | 4.3091 | 3.5066 |  | 58 | 0.00071912 | 2861 | 0.057955 | 7297 | 4.0921e-05 | 5756
EL CERRITO G 1104CB | EL CERRITO G 1104 | 12501104 |  | 7.9498 | 3.2983 |  | 69.7 | 0.00077086 | 2250 | 0.053073 | 8253 | 4.0912e-05 | 5757
BUELLTON 1101Y34 | BUELLTON 1101 | 183041101 |  | 0.98519 | 0.54629 |  | 21 | 0.00067591 | 3358 | 0.061101 | 6882 | 4.0905e-05 | 5758
PEABODY 210218112 | PEABODY 2102 | 63642102 |  | 3.5549 | 0.88618 |  | 58 | 0.00067918 | 3333 | 0.060652 | 6938 | 4.0899e-05 | 5759
SONOMA 1104CB | SONOMA 1104 | 42721104 |  | 6.3248 | 1.096 |  | 117 | 0.0006133 | 4131 | 0.066628 | 6160 | 4.0898e-05 | 5760
HAMMER 1108CB | HAMMER 1108 | 163301108 |  | 1.2919 | 0.92753 |  | 24.5 | 0.00076794 | 2283 | 0.053424 | 8118 | 4.0894e-05 | 5761
MOUNTAIN VIEW 1110CB | MOUNTAIN VIEW 1110 | 82031110 |  | 9.3588 | 10.9401 |  | 133.3667 | 0.00075978 | 2391 | 0.053699 | 8030 | 4.0892e-05 | 5762
BRITTON 1109CB | BRITTON 1109 | 83611109 |  | 2.4153 | 1.8919 |  | 35 | 0.0007704 | 2253 | 0.053073 | 8253 | 4.0887e-05 | 5763
SAN JOSE B 1109CB | SAN JOSE B 1109 | 82261109 |  | 0.38427 | 0.3217 |  | 8.3333 | 0.00077037 | 2254 | 0.053073 | 8250 | 4.0886e-05 | 5764
TAFT 1104CB | TAFT 1104 | 252081104 |  | 6.0228 | 5.6821 |  | 82.0833 | 0.0006916 | 3199 | 0.060241 | 6991 | 4.0884e-05 | 5765
MC KEE 1108CB | MC KEE 1108 | 83531108 |  | 0.57828 | 0.048012 |  | 18 | 0.0006576 | 3604 | 0.060423 | 6969 | 4.0876e-05 | 5766
SF G 1102207276 | SF G 1102 | 22091102 |  | 0.37036 | 0.24258 |  | 3.8333 | 0.00077015 | 2255 | 0.053073 | 8250 | 4.0874e-05 | 5767
RINCON 1102666 | RINCON 1102 | 43321102 |  | 0.9919 | 0.56548 |  | 19 | 0.00070549 | 3037 | 0.059363 | 7102 | 4.0865e-05 | 5768
MERCED 21017220 | MERCED 2101 | 252802101 |  | 2.7893 | 2.3388 |  | 42.5 | 0.00076986 | 2259 | 0.053073 | 8251 | 4.0859e-05 | 5769
SAN RAFAEL 11025615 | SAN RAFAEL 1102 | 42011102 |  | 0.2007 | 0.16202 |  | 3.5 | 0.00076972 | 2260 | 0.053073 | 8251 | 4.0851e-05 | 5770
DALY CITY 110289878 | DALY CITY 1102 | 22641102 |  | 0.099243 | 0.12071 |  | 1.3333 | 0.00076969 | 2261 | 0.053073 | 8251 | 4.085e-05 | 5771
PUEBLO 210182742 | PUEBLO 2101 | 43292101 |  | 6.8903 | 5.5818 |  | 117 | 0.00074459 | 2560 | 0.055382 | 7690 | 4.0847e-05 | 5772
CLAYTON 2217CB | CLAYTON 2217 | 12022217 |  | 0.34344 | 0.078423 |  | 4.1167 | 0.00070468 | 3046 | 0.060531 | 6953 | 4.0847e-05 | 5773
MISSION (X) 112899358 | MISSION (X) 1128 | 22011128 |  | 0.63642 | 0.61146 |  | 11 | 0.00076956 | 2263 | 0.053073 | 8251 | 4.0842e-05 | 5774
LARKIN (Y) 113584195 | LARKIN (Y) 1135 | 22801135 |  | 0.42006 | 0.46361 |  | 5.75 | 0.00076951 | 2265 | 0.053073 | 8251 | 4.084e-05 | 5775
TRIMBLE 2114XR394 | TRIMBLE 2114 | 83802114 |  | 0.002841 | 0 |  | 0.5 | 0.0007694 | 2267 | 0.053073 | 8251 | 4.0834e-05 | 5776
SF N 0406CB | SF N 0406 | 22280406 |  | 0.36425 | 0.34713 |  | 6.3333 | 0.00076935 | 2268 | 0.053073 | 8251 | 4.0831e-05 | 5777
RICHMOND R 1128BR130 | RICHMOND R 1128 | 13471128 |  | 3.7398 | 2.1228 |  | 32.1667 | 0.00076931 | 2269 | 0.053073 | 8249 | 4.083e-05 | 5778
MILLBRAE 0401CB | MILLBRAE 0401 | 22690401 |  | 2.8207 | 2.3021 |  | 52.8333 | 0.0007007 | 3089 | 0.059202 | 7128 | 4.0827e-05 | 5779
BELMONT 1110CB | BELMONT 1110 | 24031110 |  | 2.811 | 1.7512 |  | 37.1667 | 0.0007691 | 2272 | 0.053073 | 8249 | 4.0818e-05 | 5780
PAUL SWEET 2101CB | PAUL SWEET 2101 | 83252101 |  | 1.6506 | 0.65636 |  | 21.3333 | 0.00076904 | 2273 | 0.053073 | 8252 | 4.0815e-05 | 5781
SAN LEANDRO U 1108CB | SAN LEANDRO U 1108 | 13111108 |  | 4.2649 | 3.8518 |  | 60 | 0.00076904 | 2274 | 0.053073 | 8251 | 4.0815e-05 | 5782
ATASCADERO 1101CB | ATASCADERO 1101 | 182541101 | TRUE | 1.0446 | 0.75299 | 0.17816 | 28.5 | 0.0003973 | 6488 | 0.14318 | 3222 | 4.0813e-05 | 5783
COTTONWOOD 1103CB | COTTONWOOD 1103 | 102931103 |  | 4.217 | 1.0081 |  | 71.1667 | 0.0006188 | 4060 | 0.066056 | 6258 | 4.0812e-05 | 5784
BRITTON 1107CB | BRITTON 1107 | 83611107 |  | 2.3996 | 0.84287 |  | 31.3333 | 0.00076889 | 2277 | 0.053073 | 8251 | 4.0807e-05 | 5785
STELLING 1113LL28 | STELLING 1113 | 83481113 |  | 3.1398 | 4.2519 |  | 53 | 0.00065812 | 3596 | 0.062007 | 6763 | 4.0805e-05 | 5786
MISSION (X) 1108CB | MISSION (X) 1108 | 22011108 |  | 2.1346 | 3.1361 |  | 28.8333 | 0.00067424 | 3384 | 0.060666 | 6932 | 4.0804e-05 | 5787
DEL MONTE 110172040 | DEL MONTE 1101 | 182221101 |  | 4.2583 | 3.5952 |  | 60 | 0.00076094 | 2370 | 0.053653 | 8046 | 4.0801e-05 | 5788
FREMONT 1103CB | FREMONT 1103 | 14351103 |  | 0.032849 | 0 |  | 2 | 0.00076849 | 2278 | 0.053073 | 8251 | 4.0786e-05 | 5789
ATWATER 110710500 | ATWATER 1107 | 253611107 |  | 1.7747 | 0.041971 |  | 30 | 0.00076822 | 2280 | 0.053073 | 8251 | 4.0771e-05 | 5790
CASTRO VALLEY 1109CB | CASTRO VALLEY 1109 | 14091109 |  | 1.9061 | 1.5474 |  | 40.1667 | 0.00068505 | 3275 | 0.059198 | 7129 | 4.0771e-05 | 5791
EDENVALE 2113XR106 | EDENVALE 2113 | 82952113 |  | 0.95604 | 0.88427 |  | 14.5 | 0.00076819 | 2282 | 0.053073 | 8251 | 4.077e-05 | 5792
EL PATIO 1105CB | EL PATIO 1105 | 82921105 |  | 6.992 | 7.681 |  | 116.1667 | 0.00076775 | 2285 | 0.053073 | 8251 | 4.0746e-05 | 5793
EAST GRAND 110739200 | EAST GRAND 1107 | 22571107 |  | 1.6119 | 1.6478 |  | 24 | 0.00076754 | 2289 | 0.053073 | 8251 | 4.0735e-05 | 5794
LARKIN (Y) 110734976 | LARKIN (Y) 1107 | 22801107 |  | 0.26027 | 0.031872 |  | 2.8333 | 0.00076751 | 2290 | 0.053073 | 8251 | 4.0734e-05 | 5795
BRITTON 1113CB | BRITTON 1113 | 83611113 |  | 1.3454 | 1.1036 |  | 26 | 0.00076722 | 2294 | 0.053073 | 8251 | 4.0718e-05 | 5796
RENFRO 21051594 | RENFRO 2105 | 254572105 |  | 2.5397 | 0.42264 |  | 43 | 0.00074935 | 2493 | 0.054621 | 7821 | 4.0718e-05 | 5797
HICKS 2103XR068 | HICKS 2103 | 83432103 |  | 3.0522 | 3.5542 |  | 50.8333 | 0.00068995 | 3218 | 0.059912 | 7031 | 4.0717e-05 | 5798
BOGUE 11037012 | BOGUE 1103 | 153781103 |  | 9.2719 | 4.72 |  | 149.3333 | 0.00076718 | 2295 | 0.053073 | 8251 | 4.0716e-05 | 5799
RED BLUFF 1105161818 | RED BLUFF 1105 | 103541105 | TRUE | 4.7589 | 0.63784 | 0.0080205 | 80.5 | 0.00031985 | 7631 | 0.14663 | 3213 | 4.0705e-05 | 5800
GOLDTREE 1105912920 | GOLDTREE 1105 | 182581105 |  | 0.76619 | 0.54414 |  | 12.5 | 0.0007669 | 2298 | 0.053073 | 8251 | 4.0701e-05 | 5801
BELLE HAVEN 11069150 | BELLE HAVEN 1106 | 24021106 |  | 1.5503 | 0.98536 |  | 19.1667 | 0.00076678 | 2299 | 0.053073 | 8250 | 4.0695e-05 | 5802
NORIEGA 0401CB | NORIEGA 0401 | 22510401 |  | 1.558 | 2.2128 |  | 20.7 | 0.00076675 | 2300 | 0.053073 | 8251 | 4.0693e-05 | 5803
STOCKDALE 21054854 | STOCKDALE 2105 | 254072105 |  | 2.5664 | 1.3562 |  | 41.1667 | 0.00076663 | 2301 | 0.053073 | 8251 | 4.0687e-05 | 5804
MT EDEN 1102CB | MT EDEN 1102 | 13761102 |  | 4.0732 | 3.2925 |  | 59.9 | 0.00076655 | 2302 | 0.053073 | 8251 | 4.0683e-05 | 5805
MOUNTAIN VIEW 1114CB | MOUNTAIN VIEW 1114 | 82031114 |  | 5.9111 | 2.1782 |  | 82.8167 | 0.00071415 | 2923 | 0.057096 | 7425 | 4.0681e-05 | 5806
GREEN VALLEY 2104CB | GREEN VALLEY 2104 | 83192104 |  | 10.338 | 6.0942 |  | 157.0833 | 0.00067381 | 3390 | 0.061723 | 6795 | 4.0677e-05 | 5807
DALY CITY 04014165 | DALY CITY 0401 | 22640401 |  | 1.1588 | 1.5095 |  | 14 | 0.00076633 | 2306 | 0.053073 | 8251 | 4.0671e-05 | 5808
LINCOLN 1102CB | LINCOLN 1102 | 153701102 |  | 6.1795 | 3.6034 |  | 91.25 | 0.0007225 | 2824 | 0.055858 | 7602 | 4.0663e-05 | 5809
DEL MONTE 210342226 | DEL MONTE 2103 | 182222103 | FALSE | 2.5015 | 2.5235 | 0.65449 | 50 | 0.00061381 | 4125 | 0.066788 | 6123 | 4.0662e-05 | 5810
STONE 1109XR490 | STONE 1109 | 83701109 |  | 2.0236 | 1.0523 |  | 36.5 | 0.0007661 | 2310 | 0.053073 | 8251 | 4.0659e-05 | 5811
EIGHT MILE 21025272 | EIGHT MILE 2102 | 163912102 |  | 0.20456 | 0 |  | 2.8333 | 0.00052529 | 5121 | 0.0774 | 3397 | 4.0657e-05 | 5812
EMBARCADERO (Z) 1120CB | EMBARCADERO (Z) 1120 | 22871120 |  | 0.20813 | 0.042132 |  | 4 | 0.00076596 | 2311 | 0.053073 | 8251 | 4.0652e-05 | 5813
EL CERRITO G 1110BR238 | EL CERRITO G 1110 | 12501110 |  | 2.5092 | 1.5579 |  | 23.6167 | 0.00076594 | 2312 | 0.053073 | 8248 | 4.0651e-05 | 5814
BAY MEADOWS 110339666 | BAY MEADOWS 1103 | 24011103 |  | 0.96342 | 0.43648 |  | 10.1667 | 0.00076586 | 2314 | 0.053073 | 8252 | 4.0646e-05 | 5815
MOUNTAIN VIEW 111360060 | MOUNTAIN VIEW 1113 | 82031113 |  | 0.86801 | 0.66279 |  | 15.3333 | 0.00076572 | 2315 | 0.053073 | 8250 | 4.0639e-05 | 5816
OAKLAND D 1133CR292 | OAKLAND D 1133 | 12041133 |  | 0.42949 | 0.46748 |  | 5.1667 | 0.0007656 | 2318 | 0.053073 | 8251 | 4.0633e-05 | 5817
EL PATIO 1109XR054 | EL PATIO 1109 | 82921109 |  | 4.4192 | 2.8387 |  | 64.3333 | 0.00076559 | 2319 | 0.053073 | 8250 | 4.0632e-05 | 5818
HICKS 1110CB | HICKS 1110 | 83431110 |  | 6.5465 | 6.5521 |  | 100.1667 | 0.00075795 | 2409 | 0.05346 | 8109 | 4.0628e-05 | 5819
COTTLE 1707380150 | COTTLE 1707 | 163711707 |  | 0.88835 | 0.045873 |  | 14.3333 | 0.00070829 | 3003 | 0.058164 | 7273 | 4.0628e-05 | 5820
DALY CITY 111210099 | DALY CITY 1112 | 22641112 |  | 1.9188 | 1.8352 |  | 29.1667 | 0.00075014 | 2478 | 0.054196 | 7904 | 4.0628e-05 | 5821
CLARKSVILLE 2105385236 | CLARKSVILLE 2105 | 153612105 |  | 1.7724 | 0 |  | 31.5 | 0.00060606 | 4226 | 0.067022 | 5998 | 4.062e-05 | 5822
NAPA 111048232 | NAPA 1110 | 42021110 |  | 2.9448 | 2.0585 |  | 39.5 | 0.00076537 | 2321 | 0.053073 | 8252 | 4.062e-05 | 5823
MAGUNDEN 110148518 | MAGUNDEN 1101 | 252771101 |  | 6.3288 | 6.7702 |  | 108.3333 | 0.00076534 | 2322 | 0.053073 | 8252 | 4.0619e-05 | 5824
COALINGA NO 1 11099870 | COALINGA NO 1 1109 | 252161109 |  | 3.6724 | 1.9652 |  | 62.5 | 0.00066161 | 3554 | 0.061652 | 6807 | 4.0618e-05 | 5825
UKIAH 1111CB | UKIAH 1111 | 42771111 |  | 2.253 | 0.13891 |  | 34.25 | 0.00059745 | 4336 | 0.068112 | 5382 | 4.0618e-05 | 5826
MISSION (X) 1113CB | MISSION (X) 1113 | 22011113 |  | 0.64964 | 1.2841 |  | 10.5 | 0.00076525 | 2323 | 0.053073 | 8251 | 4.0614e-05 | 5827
MC KEE 110698388 | MC KEE 1106 | 83531106 |  | 1.6238 | 1.3631 |  | 33.5 | 0.00076498 | 2328 | 0.053073 | 8251 | 4.0599e-05 | 5828
BERKELEY F 0402CB | BERKELEY F 0402 | 12060402 | TRUE | 1.6027 | 1.6091 | 0.18649 | 23.1667 | 0.00073956 | 2603 | 0.055774 | 7623 | 4.0592e-05 | 5829
SF E 11076461 | SF E 1107 | 22071107 |  | 1.7435 | 1.5043 |  | 19.2 | 0.00075827 | 2405 | 0.05434 | 7883 | 4.0592e-05 | 5830
KING CITY 1103CB | KING CITY 1103 | 182031103 |  | 1.8625 | 1.4746 |  | 29.6667 | 0.00072191 | 2834 | 0.056005 | 7580 | 4.059e-05 | 5831
VASONA 1101LC68 | VASONA 1101 | 83771101 |  | 4.9092 | 3.2466 |  | 87.3333 | 0.00069669 | 3145 | 0.058985 | 7162 | 4.0588e-05 | 5832
SAN CARLOS 0402CB | SAN CARLOS 0402 | 24180402 |  | 4.2939 | 3.3639 |  | 60.9262 | 0.00076473 | 2330 | 0.053073 | 8251 | 4.0586e-05 | 5833
MARINA (F) 0408CB | MARINA (F) 0408 | 22780408 |  | 0.51713 | 0.65824 |  | 5.6667 | 0.0007645 | 2331 | 0.053073 | 8251 | 4.0574e-05 | 5834
LAS GALLINAS A 1106CB | LAS GALLINAS A 1106 | 42991106 | TRUE | 10.0772 | 4.0573 | 0.059516 | 173.3333 | 0.00057833 | 4548 | 0.070337 | 4974 | 4.057e-05 | 5835
SANTA ROSA A 110376232 | SANTA ROSA A 1103 | 42151103 |  | 2.2266 | 0.55776 |  | 38.5 | 0.00067508 | 3370 | 0.059946 | 7028 | 4.055e-05 | 5836
FITCH MOUNTAIN 1112CB | FITCH MOUNTAIN 1112 | 42751112 |  | 0.0086406 | 0 |  | 0.33333 | 0.00060506 | 4239 | 0.067 | 6056 | 4.0539e-05 | 5837
PAUL SWEET 210437482 | PAUL SWEET 2104 | 83252104 |  | 1.3037 | 0.64506 |  | 19.3333 | 0.00069855 | 3120 | 0.058115 | 7276 | 4.0538e-05 | 5838
EL PATIO 1103CB | EL PATIO 1103 | 82921103 |  | 6.636 | 6.9648 |  | 99.3333 | 0.00076378 | 2336 | 0.053073 | 8250 | 4.0536e-05 | 5839
EAST STOCKTON 0402549752 | EAST STOCKTON 0402 | 163130402 |  | 2.4342 | 2.6912 |  | 31.5 | 0.00076317 | 2343 | 0.053346 | 8157 | 4.0532e-05 | 5840
CANAL 110411160 | CANAL 1104 | 252091104 |  | 2.2504 | 1.5016 |  | 31.5 | 0.00073965 | 2600 | 0.054937 | 7760 | 4.0531e-05 | 5841
HIGHLANDS 110486807 | HIGHLANDS 1104 | 43361104 |  | 0.68133 | 0.34092 |  | 9.5 | 0.0006043 | 4253 | 0.06707 | 5925 | 4.053e-05 | 5842
MENLO 1103CB | MENLO 1103 | 24131103 |  | 2.8967 | 1.581 |  | 52 | 0.0006671 | 3467 | 0.061775 | 6789 | 4.0528e-05 | 5843
ALTO 112191428 | ALTO 1121 | 42031121 |  | 6.9609 | 3.0794 |  | 138.3333 | 0.00066067 | 3570 | 0.061049 | 6887 | 4.0524e-05 | 5844
CORNING 1104905234 | CORNING 1104 | 103331104 |  | 6.2103 | 4.7103 |  | 90.6667 | 0.00074076 | 2592 | 0.054942 | 7759 | 4.0513e-05 | 5845
ROSSMOOR 110493664 | ROSSMOOR 1104 | 14161104 |  | 4.1222 | 2.6642 |  | 78.5 | 0.0006149 | 4107 | 0.066226 | 6227 | 4.0512e-05 | 5846
CAROLANDS 0401CB | CAROLANDS 0401 | 24060401 |  | 0.030571 | 0 |  | 0.83333 | 0.00076331 | 2341 | 0.053073 | 8250 | 4.0511e-05 | 5847
EDENVALE 2109XR192 | EDENVALE 2109 | 82952109 |  | 0.42356 | 0 |  | 6 | 0.00076327 | 2342 | 0.053073 | 8251 | 4.0509e-05 | 5848
EVERGREEN 2101CB | EVERGREEN 2101 | 82012101 |  | 2.0257 | 1.2453 |  | 50.5 | 0.00068688 | 3258 | 0.059829 | 7036 | 4.0499e-05 | 5849
VIEJO 22032016 | VIEJO 2203 | 182852203 |  | 2.712 | 2.7735 |  | 42 | 0.00067179 | 3419 | 0.060781 | 6917 | 4.0499e-05 | 5850
ORLAND B 110353574 | ORLAND B 1103 | 102701103 |  | 14.0147 | 8.2163 |  | 228 | 0.0006986 | 3119 | 0.059123 | 7142 | 4.0485e-05 | 5851
MENLO 040365975 | MENLO 0403 | 24130403 |  | 2.0916 | 1.4528 |  | 36.1667 | 0.00062153 | 4030 | 0.065001 | 6432 | 4.0484e-05 | 5852
COTTLE 1708CB | COTTLE 1708 | 163711708 |  | 2.4885 | 0.62395 |  | 35.8333 | 0.00055997 | 4755 | 0.072887 | 4674 | 4.0483e-05 | 5853
PAUL SWEET 2107239036 | PAUL SWEET 2107 | 83252107 |  | 3.4694 | 1.1423 |  | 59.5 | 0.00063917 | 3834 | 0.064034 | 6536 | 4.048e-05 | 5854
CAROLANDS 04038980 | CAROLANDS 0403 | 24060403 |  | 2.1065 | 1.4376 |  | 36.25 | 0.00060298 | 4266 | 0.067228 | 5780 | 4.047e-05 | 5855
RICHMOND R 1126BR242 | RICHMOND R 1126 | 13471126 |  | 4.1127 | 2.2357 |  | 47.6667 | 0.00076248 | 2347 | 0.053073 | 8251 | 4.0467e-05 | 5856
EDENVALE 2106XR240 | EDENVALE 2106 | 82952106 |  | 9.6076 | 11.9697 |  | 140.1667 | 0.00076248 | 2348 | 0.053073 | 8250 | 4.0467e-05 | 5857
CORNING 1103CB | CORNING 1103 | 103331103 |  | 5.6615 | 3.7183 |  | 94.3333 | 0.00069037 | 3214 | 0.05921 | 7127 | 4.0463e-05 | 5858
BELLEVUE 1102CB | BELLEVUE 1102 | 43181102 |  | 2.1192 | 0.83767 |  | 33 | 0.00068237 | 3304 | 0.062714 | 6690 | 4.0458e-05 | 5859
HICKS 1111CB | HICKS 1111 | 83431111 |  | 13.3731 | 14.2318 |  | 187.1167 | 0.00075949 | 2394 | 0.053228 | 8208 | 4.0454e-05 | 5860
STONE 1101XR226 | STONE 1101 | 83701101 |  | 3.6378 | 3.3757 |  | 51.8333 | 0.00076221 | 2349 | 0.053073 | 8251 | 4.0453e-05 | 5861
SF L 110213881 | SF L 1102 | 22261102 |  | 2.0212 | 2.9173 |  | 28.5 | 0.00076217 | 2351 | 0.053073 | 8251 | 4.045e-05 | 5862
POTTER VALLEY P H 1105CB | POTTER VALLEY P H 1105 | 42281105 | TRUE | 0.055521 | 0 | 0.055521 | 1.25 | 0.00058124 | 4506 | 0.069587 | 5105 | 4.0447e-05 | 5863
LOS OSITOS 2101109138 | LOS OSITOS 2101 | 182082101 |  | 3.0961 | 2.9173 |  | 52.8333 | 0.00074812 | 2503 | 0.054094 | 7932 | 4.0444e-05 | 5864
DUMBARTON 1103CB | DUMBARTON 1103 | 14471103 |  | 0.53556 | 0 |  | 10.8333 | 0.00074808 | 2504 | 0.054144 | 7915 | 4.0432e-05 | 5865
SF N 1102CB | SF N 1102 | 22281102 |  | 1.0682 | 1.2053 |  | 14.4833 | 0.00076179 | 2357 | 0.053073 | 8251 | 4.043e-05 | 5866
OAKLAND X 1102CB | OAKLAND X 1102 | 12541102 |  | 1.4724 | 1.2536 |  | 22.6667 | 0.00076165 | 2359 | 0.053073 | 8251 | 4.0423e-05 | 5867
PANAMA 21021689 | PANAMA 2102 | 253422102 |  | 9.2028 | 5.7749 |  | 138.1667 | 0.00072349 | 2809 | 0.058718 | 7197 | 4.0421e-05 | 5868
RICHMOND R 1129BR220 | RICHMOND R 1129 | 13471129 |  | 0.31001 | 0.01218 |  | 4 | 0.00076148 | 2360 | 0.053073 | 8251 | 4.0414e-05 | 5869
JARVIS 1104MR244 | JARVIS 1104 | 13501104 |  | 2.0118 | 0.83971 |  | 24.5 | 0.00076141 | 2361 | 0.053073 | 8251 | 4.041e-05 | 5870
SAN CARLOS 11048942 | SAN CARLOS 1104 | 24181104 | FALSE | 2.7755 | 3.0818 | 4.282 | 37.8333 | 0.00041809 | 6244 | 0.068024 | 5401 | 4.041e-05 | 5871
BURLINGAME 04039064 | BURLINGAME 0403 | 24050403 |  | 3.1811 | 4.0506 |  | 46 | 0.0007614 | 2362 | 0.053073 | 8251 | 4.041e-05 | 5872
MOUNTAIN VIEW 110560110 | MOUNTAIN VIEW 1105 | 82031105 |  | 2.3929 | 1.1029 |  | 38.5 | 0.0007613 | 2363 | 0.053073 | 8251 | 4.0404e-05 | 5873
CASTRO VALLEY 1105MR201 | CASTRO VALLEY 1105 | 14091105 |  | 5.7752 | 6.417 |  | 89 | 0.00066878 | 3446 | 0.060051 | 7011 | 4.0399e-05 | 5874
MILPITAS 1101CB | MILPITAS 1101 | 82831101 |  | 4.0592 | 5.1135 |  | 74.5 | 0.00076119 | 2365 | 0.053073 | 8251 | 4.0398e-05 | 5875
EL CAPITAN 21099420 | EL CAPITAN 2109 | 253882109 |  | 1.3386 | 0.25271 |  | 24.1667 | 0.00076117 | 2366 | 0.053073 | 8250 | 4.0397e-05 | 5876
PEABODY 2109CB | PEABODY 2109 | 63642109 |  | 3.6273 | 0 |  | 40.8333 | 0.00065611 | 3623 | 0.064004 | 6541 | 4.039e-05 | 5877
SAN LEANDRO U 1101CB | SAN LEANDRO U 1101 | 13111101 |  | 3.8928 | 2.6397 |  | 61.1667 | 0.000761 | 2369 | 0.053073 | 8251 | 4.0389e-05 | 5878
ALTO 1120500 | ALTO 1120 | 42031120 | TRUE | 3.1481 | 2.2358 | 0.35883 | 46.1667 | 0.00068931 | 3231 | 0.058668 | 7203 | 4.038e-05 | 5879
BERKELEY F 1104BR116 | BERKELEY F 1104 | 12061104 |  | 0.26605 | 0.23085 |  | 1.9167 | 0.00076074 | 2373 | 0.053073 | 8250 | 4.0375e-05 | 5880
MALAGA 1106CB | MALAGA 1106 | 254251106 |  | 3.568 | 1.596 |  | 61 | 0.00073376 | 2686 | 0.05529 | 7708 | 4.0374e-05 | 5881
GONZALES 1102CB | GONZALES 1102 | 182131102 |  | 0.71786 | 0.10236 |  | 10.5833 | 0.00065111 | 3697 | 0.064258 | 6511 | 4.0373e-05 | 5882
NEWARK 21KV 21077972 | NEWARK 21KV 2107 | 12232107 |  | 0.24386 | 0 |  | 5.5 | 0.00064656 | 3748 | 0.062028 | 6761 | 4.0354e-05 | 5883
EL PATIO 1104CB | EL PATIO 1104 | 82921104 |  | 9.164 | 8.221 |  | 127 | 0.0007603 | 2378 | 0.053073 | 8249 | 4.0351e-05 | 5884
FMC 111190062 | FMC 1111 | 83871111 |  | 0.015938 | 0 |  | 0.5 | 0.00076026 | 2379 | 0.053073 | 8251 | 4.0349e-05 | 5885
DALY CITY 1106CB | DALY CITY 1106 | 22641106 |  | 3.3985 | 0.72366 |  | 59.75 | 0.00063295 | 3902 | 0.063458 | 6616 | 4.0345e-05 | 5886
WOLFE 1104LC28 | WOLFE 1104 | 83671104 |  | 5.6646 | 7.1378 |  | 82.8333 | 0.00076018 | 2381 | 0.053073 | 8252 | 4.0345e-05 | 5887
ARLINGTON 0401CB | ARLINGTON 0401 | 13700401 |  | 3.0132 | 3.3047 |  | 42.3333 | 0.00067711 | 3349 | 0.059399 | 7098 | 4.0342e-05 | 5888
DEL MAR 21061686 | DEL MAR 2106 | 152582106 |  | 3.368 | 0.15592 |  | 58 | 0.00060186 | 4278 | 0.067027 | 5991 | 4.0342e-05 | 5889
SARATOGA 111319114 | SARATOGA 1113 | 83371113 |  | 11.5851 | 14.6709 |  | 158.1667 | 0.00070861 | 2998 | 0.056419 | 7512 | 4.0339e-05 | 5890
VALLEJO B 0415865600 | VALLEJO B 0415 | 42450415 |  | 5.6716 | 5.0506 |  | 71.1667 | 0.00076006 | 2383 | 0.053073 | 8250 | 4.0338e-05 | 5891
WOODSIDE 11042337 | WOODSIDE 1104 | 24251104 |  | 1.8676 | 0.3754 |  | 39.5 | 0.00060118 | 4286 | 0.067099 | 5899 | 4.0336e-05 | 5892
HICKS 1114CB | HICKS 1114 | 83431114 |  | 3.9434 | 3.7259 |  | 53.5667 | 0.00075248 | 2456 | 0.05348 | 8101 | 4.0336e-05 | 5893
CORCORAN 1108CB | CORCORAN 1108 | 252171108 |  | 5.5255 | 3.5735 |  | 90.75 | 0.00074576 | 2535 | 0.054237 | 7896 | 4.0332e-05 | 5894
SARATOGA 11091024 | SARATOGA 1109 | 83371109 |  | 6.7283 | 8.2279 |  | 86.3333 | 0.00075984 | 2388 | 0.053073 | 8252 | 4.0327e-05 | 5895
PIERCY 210917515 | PIERCY 2109 | 83912109 |  | 1.3395 | 1.8597 |  | 18.8333 | 0.0007598 | 2389 | 0.053073 | 8252 | 4.0325e-05 | 5896
OAKLAND X 1103CR410 | OAKLAND X 1103 | 12541103 |  | 2.5374 | 3.1133 |  | 33.5 | 0.00075978 | 2390 | 0.053073 | 8251 | 4.0324e-05 | 5897
ATWATER 110710510 | ATWATER 1107 | 253611107 |  | 1.6234 | 1.1793 |  | 27 | 0.0007597 | 2392 | 0.053073 | 8251 | 4.0319e-05 | 5898
LOCKEFORD 210167588 | LOCKEFORD 2101 | 163682101 |  | 12.1028 | 2.2421 |  | 207.5 | 0.00052404 | 5139 | 0.077014 | 3755 | 4.0316e-05 | 5899
BAY MEADOWS 110633524 | BAY MEADOWS 1106 | 24011106 |  | 0.53582 | 0.48919 |  | 9.8333 | 0.00075931 | 2396 | 0.053073 | 8250 | 4.0299e-05 | 5900
NEWMAN 110590470 | NEWMAN 1105 | 162741105 |  | 3.0741 | 1.7544 |  | 50.5 | 0.00073864 | 2620 | 0.056445 | 7508 | 4.0295e-05 | 5901
SONOMA 1103418 | SONOMA 1103 | 42721103 |  | 4.9681 | 2.2662 |  | 89.5 | 0.00066818 | 3455 | 0.061141 | 6877 | 4.027e-05 | 5902
SYCAMORE CREEK 1101CB | SYCAMORE CREEK 1101 | 102971101 |  | 4.7813 | 2.4417 |  | 84 | 0.00075177 | 2463 | 0.053653 | 8046 | 4.0267e-05 | 5903
SAN RAMON 2104CB | SAN RAMON 2104 | 14232104 |  | 5.8366 | 5.096 |  | 99.75 | 0.00070746 | 3013 | 0.057014 | 7436 | 4.0261e-05 | 5904
BELMONT 1104458906 | BELMONT 1104 | 24031104 |  | 6.5781 | 5.1374 |  | 100.3333 | 0.00071956 | 2858 | 0.05628 | 7537 | 4.026e-05 | 5905
LAWRENCE 1104CB | LAWRENCE 1104 | 83421104 |  | 4.3234 | 4.2942 |  | 66.4167 | 0.00075851 | 2403 | 0.053073 | 8252 | 4.0256e-05 | 5906
RAINBOW 110563342 | RAINBOW 1105 | 254441105 |  | 1.7011 | 1.4045 |  | 29 | 0.00075837 | 2404 | 0.053073 | 8251 | 4.0249e-05 | 5907
BURLINGAME 04049066 | BURLINGAME 0404 | 24050404 |  | 0.83192 | 0.66857 |  | 12.5 | 0.0007582 | 2406 | 0.053073 | 8251 | 4.024e-05 | 5908
RIPON 1703CB | RIPON 1703 | 163801703 |  | 3.0531 | 0.384 |  | 49.5 | 0.00062013 | 4048 | 0.067253 | 5761 | 4.0238e-05 | 5909
BELMONT 11038956 | BELMONT 1103 | 24031103 | TRUE | 1.3892 | 0.63955 | 0.31538 | 18.8333 | 0.00066312 | 3529 | 0.060468 | 6965 | 4.0237e-05 | 5910
WOODLAND 1110CB | WOODLAND 1110 | 62031110 |  | 3.3722 | 1.4495 |  | 58.6667 | 0.00072119 | 2839 | 0.057584 | 7345 | 4.0237e-05 | 5911
LONE TREE 2102B558R | LONE TREE 2102 | 13232102 |  | 5.3156 | 2.476 |  | 84.3333 | 0.0006135 | 4128 | 0.0656 | 6341 | 4.0228e-05 | 5912
STOCKDALE 110512306 | STOCKDALE 1105 | 254071105 |  | 1.1069 | 0 |  | 14.1667 | 0.00073006 | 2727 | 0.056507 | 7503 | 4.0221e-05 | 5913
WILSON 110290190 | WILSON 1102 | 254301102 |  | 4.3351 | 0.06551 |  | 71.5 | 0.00053809 | 4975 | 0.074636 | 4468 | 4.0217e-05 | 5914
RICHMOND R 1127BR104 | RICHMOND R 1127 | 13471127 |  | 2.254 | 2.1709 |  | 22.6667 | 0.00075771 | 2412 | 0.053073 | 8250 | 4.0214e-05 | 5915
DIXON LANDING 2102393382 | DIXON LANDING 2102 | 14722102 |  | 5.4654 | 6.6378 |  | 67 | 0.00075753 | 2414 | 0.053073 | 8251 | 4.0204e-05 | 5916
MAGUNDEN 1108804974 | MAGUNDEN 1108 | 252771108 |  | 3.7948 | 1.8129 |  | 54 | 0.00066168 | 3553 | 0.061871 | 6781 | 4.02e-05 | 5917
SANTA MARIA 1110CB | SANTA MARIA 1110 | 182671110 |  | 5.0151 | 0.80007 |  | 58 | 0.00068903 | 3232 | 0.059804 | 7038 | 4.0185e-05 | 5918
TAFT 11042337 | TAFT 1104 | 252081104 |  | 2.1626 | 2.4621 |  | 40 | 0.00071755 | 2885 | 0.057511 | 7360 | 4.0182e-05 | 5919
OAKLAND D 1105CB | OAKLAND D 1105 | 12041105 |  | 3.4494 | 2.6563 |  | 43.5833 | 0.00075706 | 2415 | 0.053073 | 8249 | 4.0179e-05 | 5920
MOLINO 1101CB | MOLINO 1101 | 42571101 |  | 6.1596 | 2.6934 |  | 107 | 0.00063936 | 3831 | 0.063258 | 6637 | 4.0178e-05 | 5921
KERMAN 110863970 | KERMAN 1108 | 252711108 |  | 1.0101 | 0.1318 |  | 15 | 0.00061922 | 4057 | 0.065236 | 6401 | 4.0175e-05 | 5922
SULLIVAN 0402CB | SULLIVAN 0402 | 22850402 |  | 3.2005 | 2.7229 |  | 44.1667 | 0.00075353 | 2448 | 0.053256 | 8193 | 4.0174e-05 | 5923
TAFT 11063065 | TAFT 1106 | 252081106 |  | 0.46476 | 0.014932 |  | 10.3333 | 0.00071428 | 2921 | 0.056451 | 7507 | 4.0173e-05 | 5924
LAS PULGAS 0402CB | LAS PULGAS 0402 | 24120402 |  | 2.5659 | 2.2059 |  | 43.8333 | 0.00073788 | 2638 | 0.055297 | 7707 | 4.0155e-05 | 5925
LLAGAS 2103XR402 | LLAGAS 2103 | 83182103 |  | 0.063805 | 0 |  | 1.5 | 0.00059931 | 4303 | 0.067 | 6057 | 4.0154e-05 | 5926
OAKLAND D 1131CB | OAKLAND D 1131 | 12041131 |  | 5.3566 | 5.8236 |  | 89.3333 | 0.00074226 | 2580 | 0.054401 | 7864 | 4.015e-05 | 5927
WEST SACRAMENTO 110920032 | WEST SACRAMENTO 1109 | 63131109 |  | 4.6135 | 5.4296 |  | 63 | 0.00075626 | 2422 | 0.053073 | 8252 | 4.0137e-05 | 5928
RIVERBANK 1713435672 | RIVERBANK 1713 | 163191713 |  | 1.8103 | 0.78377 |  | 24 | 0.00074367 | 2569 | 0.055458 | 7676 | 4.0127e-05 | 5929
PLUMAS 2106CB | PLUMAS 2106 | 153732106 |  | 4.8512 | 0.016576 |  | 83.5 | 0.00052197 | 5157 | 0.076835 | 3868 | 4.0125e-05 | 5930
PARKWAY 1101CB | PARKWAY 1101 | 42051101 |  | 0.96653 | 0.22874 |  | 15.3333 | 0.0007462 | 2533 | 0.054458 | 7852 | 4.0121e-05 | 5931
DALY CITY 1108CB | DALY CITY 1108 | 22641108 |  | 2.7258 | 1.5839 |  | 44.3333 | 0.00074814 | 2501 | 0.053649 | 8047 | 4.012e-05 | 5932
SAN LUIS OBISPO 1105994498 | SAN LUIS OBISPO 1105 | 182631105 |  | 3.1615 | 2.9958 |  | 41.3333 | 0.0007511 | 2471 | 0.053367 | 8148 | 4.012e-05 | 5933
EDES 1114CR156 | EDES 1114 | 13681114 |  | 3.865 | 3.9414 |  | 49.3333 | 0.00075573 | 2424 | 0.053073 | 8250 | 4.0109e-05 | 5934
DUMBARTON 1108MR561 | DUMBARTON 1108 | 14471108 |  | 0.73613 | 0.070293 |  | 14.8333 | 0.00071218 | 2944 | 0.055652 | 7648 | 4.0103e-05 | 5935
MONROE 1104CB | MONROE 1104 | 43301104 |  | 5.214 | 2.2865 |  | 85.3333 | 0.00072232 | 2827 | 0.055857 | 7603 | 4.01e-05 | 5936
BURLINGAME 0401CB | BURLINGAME 0401 | 24050401 |  | 2.042 | 2.5108 |  | 27.8333 | 0.00075557 | 2428 | 0.053073 | 8251 | 4.01e-05 | 5937
MOLINO 110276066 | MOLINO 1102 | 42571102 |  | 4.1585 | 1.901 |  | 73 | 0.00063265 | 3906 | 0.064086 | 6529 | 4.0098e-05 | 5938
RESEARCH 2102CB | RESEARCH 2102 | 14692102 |  | 0.34182 | 0.13414 |  | 10.8333 | 0.00067932 | 3331 | 0.058545 | 7218 | 4.0093e-05 | 5939
SF H 111041644 | SF H 1110 | 22101110 |  | 1.3321 | 0 |  | 24 | 0.00060513 | 4237 | 0.066131 | 6241 | 4.0092e-05 | 5940
BELLE HAVEN 1103CB | BELLE HAVEN 1103 | 24021103 |  | 1.3334 | 0.11443 |  | 23.0833 | 0.00075533 | 2430 | 0.053073 | 8251 | 4.0087e-05 | 5941
EVERGREEN 2101XR080 | EVERGREEN 2101 | 82012101 |  | 0.15591 | 0.04508 |  | 3.5 | 0.00075526 | 2431 | 0.053073 | 8251 | 4.0084e-05 | 5942
EDES 1103CB | EDES 1103 | 13681103 |  | 3.7978 | 3.7538 |  | 51.8333 | 0.00075518 | 2432 | 0.053073 | 8250 | 4.0079e-05 | 5943
OAKLAND D 1105BR138 | OAKLAND D 1105 | 12041105 |  | 2.2397 | 1.7851 |  | 30.6667 | 0.00075512 | 2433 | 0.053073 | 8250 | 4.0076e-05 | 5944
KIRKER 210719592 | KIRKER 2107 | 14452107 |  | 2.3677 | 1.167 |  | 47.5 | 0.00068297 | 3296 | 0.059679 | 7059 | 4.0069e-05 | 5945
OAKLAND I 0402CB | OAKLAND I 0402 | 12080402 |  | 5.1147 | 4.8239 |  | 68.6667 | 0.00075495 | 2435 | 0.053073 | 8252 | 4.0067e-05 | 5946
LEMOORE 1102CB | LEMOORE 1102 | 253601102 |  | 1.7676 | 1.0057 |  | 27.0333 | 0.00069479 | 3159 | 0.058472 | 7225 | 4.0066e-05 | 5947
MC KEE 1111CB | MC KEE 1111 | 83531111 |  | 5.6986 | 4.7355 |  | 81.3333 | 0.00075006 | 2480 | 0.053415 | 8124 | 4.0063e-05 | 5948
BRENTWOOD 2108CB | BRENTWOOD 2108 | 14592108 |  | 2.7243 | 0.89181 |  | 39.75 | 0.00065494 | 3641 | 0.060568 | 6946 | 4.0062e-05 | 5949
SAN RAMON 2104MR143 | SAN RAMON 2104 | 14232104 |  | 8.8696 | 9.2929 |  | 125.8333 | 0.00072452 | 2795 | 0.055376 | 7691 | 4.0061e-05 | 5950
TIDEWATER 2108520863 | TIDEWATER 2108 | 14652108 |  | 4.5747 | 4.1726 |  | 68.8333 | 0.00075484 | 2436 | 0.053073 | 8252 | 4.0061e-05 | 5951
MALAGA 110690812 | MALAGA 1106 | 254251106 |  | 4.8232 | 1.212 |  | 86.5 | 0.00064604 | 3753 | 0.065102 | 6418 | 4.0054e-05 | 5952
BERKELEY F 1105BR168 | BERKELEY F 1105 | 12061105 |  | 0.022537 | 0 |  | 0.33333 | 0.00075469 | 2438 | 0.053073 | 8251 | 4.0053e-05 | 5953
OAKLAND X 1103CR408 | OAKLAND X 1103 | 12541103 |  | 1.3879 | 1.6755 |  | 19.8333 | 0.00075462 | 2439 | 0.053073 | 8251 | 4.005e-05 | 5954
MISSION (X) 0401CB | MISSION (X) 0401 | 22010401 |  | 1.6343 | 1.5312 |  | 15.5833 | 0.00075444 | 2441 | 0.053073 | 8251 | 4.004e-05 | 5955
VIERRA 1702CB | VIERRA 1702 | 162701702 |  | 4.8393 | 2.1226 |  | 83 | 0.000673 | 3403 | 0.060823 | 6907 | 4.0026e-05 | 5956
BERKELEY T 0401CB | BERKELEY T 0401 | 12660401 |  | 0.65873 | 0.63341 |  | 7 | 0.00075402 | 2443 | 0.053073 | 8251 | 4.0018e-05 | 5957
LOCKEFORD 210243430 | LOCKEFORD 2102 | 163682102 |  | 0.019195 | 0 |  | 1 | 0.00051702 | 5204 | 0.0774 | 3397 | 4.0017e-05 | 5958
MALAGA 1108CB | MALAGA 1108 | 254251108 |  | 7.2402 | 1.4544 |  | 119.5 | 0.00068619 | 3263 | 0.061599 | 6813 | 4.0015e-05 | 5959
ALMADEN 1102XR216 | ALMADEN 1102 | 82311102 |  | 2.5884 | 2.9007 |  | 38.8333 | 0.00075391 | 2445 | 0.053073 | 8251 | 4.0012e-05 | 5960
SF G 0406CB | SF G 0406 | 22090406 |  | 1.2769 | 1.2517 |  | 19.8333 | 0.0007539 | 2446 | 0.053073 | 8249 | 4.0011e-05 | 5961
EL CERRITO G 1112BR152 | EL CERRITO G 1112 | 12501112 |  | 0.18467 | 0.056484 |  | 2.8333 | 0.00075387 | 2447 | 0.053073 | 8250 | 4.001e-05 | 5962
LOGAN CREEK 210157110 | LOGAN CREEK 2101 | 103142101 |  | 4.7838 | 2.7827 |  | 63.5 | 0.00065289 | 3671 | 0.061477 | 6836 | 3.9996e-05 | 5963
CASTRO VALLEY 1107CB | CASTRO VALLEY 1107 | 14091107 |  | 3.8988 | 3.4278 |  | 63 | 0.0007007 | 3088 | 0.057384 | 7376 | 3.9985e-05 | 5964
SF K 0410CB | SF K 0410 | 22130410 |  | 2.0289 | 3.3254 |  | 28.5833 | 0.00073742 | 2646 | 0.054349 | 7878 | 3.9976e-05 | 5965
MILLBRAE 1108341881 | MILLBRAE 1108 | 22691108 |  | 2.6819 | 2.6273 |  | 34.75 | 0.00074064 | 2593 | 0.05354 | 8088 | 3.9974e-05 | 5966
SF H 111071826 | SF H 1110 | 22101110 |  | 2.4048 | 0.88367 |  | 37.5 | 0.00062795 | 3973 | 0.063628 | 6597 | 3.9973e-05 | 5967
EDENVALE 2106XR436 | EDENVALE 2106 | 82952106 |  | 0.50962 | 0.093883 |  | 8 | 0.00075304 | 2453 | 0.053073 | 8251 | 3.9966e-05 | 5968
ARCATA 1121CB | ARCATA 1121 | 192021121 |  | 9.8213 | 5.8105 |  | 159.75 | 0.00065977 | 3581 | 0.060568 | 6947 | 3.9962e-05 | 5969
DEEPWATER 1105CB | DEEPWATER 1105 | 63621105 |  | 4.1045 | 0.54154 |  | 73 | 0.0007154 | 2907 | 0.056738 | 7474 | 3.9952e-05 | 5970
JARVIS 1111MR120 | JARVIS 1111 | 13501111 |  | 0.76406 | 0.73692 |  | 13.5 | 0.00075274 | 2454 | 0.053073 | 8251 | 3.995e-05 | 5971
SHAFTER 1101CB | SHAFTER 1101 | 253651101 |  | 0.014473 | 0 |  | 0.16667 | 0.00051609 | 5213 | 0.0774 | 3396 | 3.9945e-05 | 5972
LLAGAS 2103CB | LLAGAS 2103 | 83182103 |  | 10.1801 | 4.6233 |  | 184.4167 | 0.00066512 | 3497 | 0.061231 | 6864 | 3.9934e-05 | 5973
EDENVALE 2105CB | EDENVALE 2105 | 82952105 |  | 3.4714 | 0.1209 |  | 53.0833 | 0.00067916 | 3334 | 0.23478 | 3101 | 3.9925e-05 | 5974
SF E 1105CB | SF E 1105 | 22071105 |  | 2.0704 | 2.5435 |  | 28.5833 | 0.00075223 | 2459 | 0.053073 | 8249 | 3.9923e-05 | 5975
LAKEWOOD 211090650 | LAKEWOOD 2110 | 13532110 |  | 1.0489 | 0.75698 |  | 17.5 | 0.00059585 | 4350 | 0.067 | 6057 | 3.9922e-05 | 5976
SUISUN 1106CB | SUISUN 1106 | 62131106 |  | 5.0235 | 7.7357 |  | 97.8333 | 0.00074634 | 2530 | 0.053326 | 8167 | 3.9921e-05 | 5977
VASONA 1108LC30 | VASONA 1108 | 83771108 |  | 9.0079 | 9.7588 |  | 135.3333 | 0.00066508 | 3499 | 0.061305 | 6853 | 3.9916e-05 | 5978
MC KEE 1105CB | MC KEE 1105 | 83531105 |  | 2.4411 | 2.3819 |  | 42 | 0.00075183 | 2461 | 0.053073 | 8251 | 3.9902e-05 | 5979
PUEBLO 1104CB | PUEBLO 1104 | 43291104 |  | 4.0235 | 0.723 |  | 66.6667 | 0.00058828 | 4436 | 0.067602 | 5548 | 3.9896e-05 | 5980
DUMBARTON 1109CB | DUMBARTON 1109 | 14471109 |  | 2.3031 | 0.093998 |  | 31.6667 | 0.00072093 | 2842 | 0.055418 | 7684 | 3.9895e-05 | 5981
OAKLAND D 1104CB | OAKLAND D 1104 | 12041104 |  | 5.9212 | 5.8725 |  | 83.5 | 0.00075167 | 2464 | 0.053073 | 8251 | 3.9893e-05 | 5982
OAKLAND J 0401CB | OAKLAND J 0401 | 12090401 |  | 4.6319 | 3.5816 |  | 56.9167 | 0.00075135 | 2467 | 0.053073 | 8253 | 3.9876e-05 | 5983
COALINGA NO 2 1104CB | COALINGA NO 2 1104 | 252381104 |  | 0.1498 | 0 |  | 2.5 | 0.0005936 | 4373 | 0.067175 | 5831 | 3.9875e-05 | 5984
JARVIS 1106MR687 | JARVIS 1106 | 13501106 |  | 2.8665 | 1.1358 |  | 45.8333 | 0.00074867 | 2498 | 0.054134 | 7918 | 3.9866e-05 | 5985
SAN JOSE B 1102CB | SAN JOSE B 1102 | 82261102 |  | 0.26099 | 0.10305 |  | 5.8333 | 0.00075109 | 2472 | 0.053073 | 8251 | 3.9862e-05 | 5986
SILVERADO 2105268508 | SILVERADO 2105 | 43432105 |  | 0.048603 | 0 |  | 1 | 0.00055843 | 4772 | 0.07137 | 4846 | 3.9855e-05 | 5987
JESSUP 1103CB | JESSUP 1103 | 103441103 |  | 12.9107 | 1.2728 |  | 227.5 | 0.00053942 | 4964 | 0.07407 | 4544 | 3.984e-05 | 5988
SILVER 0401CB | SILVER 0401 | 22670401 |  | 5.0411 | 4.5813 |  | 60.75 | 0.0007506 | 2474 | 0.053073 | 8252 | 3.9836e-05 | 5989
PACIFIC GROVE 04242610 | PACIFIC GROVE 0424 | 182440424 |  | 6.4261 | 5.9444 |  | 97.6667 | 0.00067864 | 3338 | 0.058781 | 7188 | 3.9826e-05 | 5990
SARATOGA 1110840021 | SARATOGA 1110 | 83371110 |  | 1.3109 | 1.8043 |  | 16.6667 | 0.00074985 | 2484 | 0.053073 | 8252 | 3.9797e-05 | 5991
OAKLAND X 1115CR298 | OAKLAND X 1115 | 12541115 |  | 0.64865 | 0.67713 |  | 9.3333 | 0.00074982 | 2485 | 0.053073 | 8250 | 3.9795e-05 | 5992
ALHAMBRA 110281034 | ALHAMBRA 1102 | 14101102 |  | 8.0847 | 8.6893 |  | 133.6667 | 0.0007149 | 2913 | 0.055561 | 7666 | 3.9793e-05 | 5993
DALY CITY 1111CB | DALY CITY 1111 | 22641111 |  | 1.1227 | 0.84338 |  | 14.1667 | 0.00074972 | 2486 | 0.053073 | 8252 | 3.979e-05 | 5994
OAKLAND J 1104CR382 | OAKLAND J 1104 | 12091104 |  | 3.4291 | 3.7673 |  | 45.0833 | 0.0007497 | 2487 | 0.053073 | 8253 | 3.9789e-05 | 5995
OAKLAND J 1103CR446 | OAKLAND J 1103 | 12091103 |  | 0.7617 | 0.22285 |  | 14 | 0.00074965 | 2489 | 0.053073 | 8251 | 3.9786e-05 | 5996
CONTRA COSTA 2113CB | CONTRA COSTA 2113 | 13652113 |  | 11.3633 | 1.2007 |  | 187.1667 | 0.00060806 | 4192 | 0.065699 | 6325 | 3.9785e-05 | 5997
WALDO 0402CB | WALDO 0402 | 13350402 | TRUE | 2.1693 | 2.4309 | 0.015433 | 17.0167 | 0.00074956 | 2490 | 0.053073 | 8253 | 3.9781e-05 | 5998
MADERA 111211550 | MADERA 1112 | 252761112 |  | 0.25833 | 0 |  | 4.8333 | 0.00072024 | 2850 | 0.055589 | 7661 | 3.978e-05 | 5999
SF K 0406CB | SF K 0406 | 22130406 |  | 1.7163 | 2.1346 |  | 20.5 | 0.00074943 | 2491 | 0.053073 | 8251 | 3.9774e-05 | 6000
SYCAMORE CREEK 11072250 | SYCAMORE CREEK 1107 | 102971107 |  | 0.57893 | 0.38128 |  | 11 | 0.00074941 | 2492 | 0.053073 | 8251 | 3.9773e-05 | 6001
BRITTON 1105CB | BRITTON 1105 | 83611105 |  | 5.2034 | 3.8526 |  | 76.5 | 0.0007493 | 2496 | 0.053073 | 8251 | 3.9767e-05 | 6002
OAKLAND J 1101CR348 | OAKLAND J 1101 | 12091101 |  | 4.548 | 4.9202 |  | 51.75 | 0.00074924 | 2497 | 0.053073 | 8252 | 3.9764e-05 | 6003
BRUNSWICK 1110528196 | BRUNSWICK 1110 | 152481110 |  | 1.1094 | 0.84624 |  | 14.8333 | 0.00060815 | 4190 | 0.064521 | 6484 | 3.9755e-05 | 6004
CLAY 1102CUST | CLAY 1102 | 163341102 |  | 0.37719 | 0.10224 |  | 6.5 | 0.00059327 | 4380 | 0.067 | 6057 | 3.9749e-05 | 6005
GRANT 1107MR221 | GRANT 1107 | 14381107 |  | 2.5931 | 2.2143 |  | 49 | 0.00073043 | 2720 | 0.054282 | 7892 | 3.9744e-05 | 6006
CAROLANDS 04038508 | CAROLANDS 0403 | 24060403 |  | 3.5214 | 2.439 |  | 60 | 0.00059819 | 4320 | 0.066526 | 6181 | 3.974e-05 | 6007
BELLE HAVEN 11068988 | BELLE HAVEN 1106 | 24021106 |  | 6.9174 | 3.3819 |  | 89.5333 | 0.00071146 | 2955 | 0.055458 | 7677 | 3.9731e-05 | 6008
FAIRVIEW 2206M523R | FAIRVIEW 2206 | 13432206 |  | 2.2654 | 0.93187 |  | 43.8333 | 0.0007269 | 2762 | 0.054502 | 7844 | 3.9731e-05 | 6009
BELLEVUE 2105316 | BELLEVUE 2105 | 43182105 |  | 2.7882 | 1.8868 |  | 42.1667 | 0.00071861 | 2866 | 0.055054 | 7744 | 3.9728e-05 | 6010
LOS ALTOS 1104LM22 | LOS ALTOS 1104 | 82241104 |  | 1.8165 | 0.91992 |  | 26.8333 | 0.00070335 | 3062 | 0.056619 | 7487 | 3.972e-05 | 6011
PUEBLO 110548260 | PUEBLO 1105 | 43291105 |  | 1.3527 | 0.26019 |  | 27 | 0.00066067 | 3571 | 0.061373 | 6842 | 3.9708e-05 | 6012
RAINBOW 1105CB | RAINBOW 1105 | 254441105 |  | 1.7579 | 0.67478 |  | 25.8333 | 0.00056944 | 4666 | 0.070808 | 4917 | 3.9699e-05 | 6013
CLARKSVILLE 210419662 | CLARKSVILLE 2104 | 153612104 |  | 2.7323 | 0.38779 |  | 51 | 0.00058394 | 4484 | 0.068352 | 5317 | 3.9699e-05 | 6014
BAY MEADOWS 1102CB | BAY MEADOWS 1102 | 24011102 |  | 4.9851 | 3.4059 |  | 61.6667 | 0.00074788 | 2508 | 0.053073 | 8251 | 3.9692e-05 | 6015
SF G 0409CB | SF G 0409 | 22090409 |  | 0.99127 | 0.48802 |  | 10.75 | 0.00074787 | 2509 | 0.053073 | 8251 | 3.9691e-05 | 6016
EDES 1110CB | EDES 1110 | 13681110 |  | 7.5172 | 6.372 |  | 109.8333 | 0.00074787 | 2510 | 0.053073 | 8251 | 3.9691e-05 | 6017
TRACY 1106CB | TRACY 1106 | 162881106 |  | 7.2334 | 1.3916 |  | 120.9167 | 0.00066353 | 3519 | 0.062595 | 6701 | 3.9687e-05 | 6018
EUREKA E 110435934 | EUREKA E 1104 | 192331104 | TRUE | 3.3913 | 2.1411 | 0.033137 | 65 | 0.00060493 | 4242 | 0.065762 | 6310 | 3.9683e-05 | 6019
FMC 1111CB | FMC 1111 | 83871111 |  | 1.5609 | 0 |  | 31.25 | 0.00074771 | 2512 | 0.053073 | 8251 | 3.9683e-05 | 6020
WILSON 110111120 | WILSON 1101 | 254301101 |  | 2.4709 | 1.647 |  | 40.5 | 0.00072197 | 2833 | 0.055299 | 7706 | 3.9679e-05 | 6021
AIRWAYS 1108576040 | AIRWAYS 1108 | 252041108 |  | 0.088022 | 0 |  | 2 | 0.0007474 | 2515 | 0.053073 | 8251 | 3.9667e-05 | 6022
EAST MARYSVILLE 11051384 | EAST MARYSVILLE 1105 | 152331105 |  | 5.9862 | 3.9713 |  | 86 | 0.00071773 | 2881 | 0.056184 | 7547 | 3.9665e-05 | 6023
CLEAR LAKE 110237582 | CLEAR LAKE 1102 | 42141102 |  | 0.64954 | 0.58728 |  | 11.5 | 0.0007362 | 2665 | 0.054889 | 7770 | 3.9662e-05 | 6024
GRANT 1103CB | GRANT 1103 | 14381103 |  | 4.1933 | 0.71804 |  | 71.8333 | 0.00071644 | 2899 | 0.055822 | 7610 | 3.9657e-05 | 6025
PORTOLA 0401900726 | PORTOLA 0401 | 22610401 |  | 0.03576 | 0 |  | 0.5 | 0.0007472 | 2518 | 0.053073 | 8251 | 3.9656e-05 | 6026
FORT ORD 210695186 | FORT ORD 2106 | 182402106 |  | 6.4282 | 0.69673 |  | 111.5833 | 0.00065586 | 3627 | 0.060946 | 6896 | 3.9656e-05 | 6027
FAIRVIEW 2207752858 | FAIRVIEW 2207 | 13432207 |  | 6.6946 | 3.2833 |  | 112.3333 | 0.00062466 | 4003 | 0.06415 | 6524 | 3.9651e-05 | 6028
SF G 0408CB | SF G 0408 | 22090408 |  | 1.3145 | 1.1601 |  | 14.25 | 0.00074704 | 2520 | 0.053073 | 8253 | 3.9648e-05 | 6029
CASTRO VALLEY 1103190144 | CASTRO VALLEY 1103 | 14091103 |  | 1.6462 | 1.3985 |  | 23.8333 | 0.00074694 | 2521 | 0.053073 | 8252 | 3.9642e-05 | 6030
WHISMAN 110660000 | WHISMAN 1106 | 83631106 |  | 3.3466 | 1.139 |  | 51 | 0.00074685 | 2522 | 0.053073 | 8251 | 3.9637e-05 | 6031
WHISMAN 110331472 | WHISMAN 1103 | 83631103 |  | 0.11362 | 0.038778 |  | 2.5 | 0.00074685 | 2523 | 0.053073 | 8251 | 3.9637e-05 | 6032
PAUL SWEET 2104273794 | PAUL SWEET 2104 | 83252104 |  | 2.872 | 1.3859 |  | 32.8333 | 0.00073356 | 2688 | 0.054133 | 7919 | 3.9627e-05 | 6033
LOS ALTOS 1106CB | LOS ALTOS 1106 | 82241106 |  | 6.7485 | 4.3815 |  | 114.5 | 0.00063486 | 3880 | 0.062864 | 6674 | 3.962e-05 | 6034
MABURY 1104CB | MABURY 1104 | 82191104 |  | 5.7468 | 4.5184 |  | 81.9167 | 0.00074649 | 2527 | 0.053073 | 8251 | 3.9618e-05 | 6035
PANAMA 21021690 | PANAMA 2102 | 253422102 |  | 0.7713 | 0.28725 |  | 11 | 0.00074644 | 2528 | 0.053073 | 8251 | 3.9615e-05 | 6036
SARATOGA 1111XR536 | SARATOGA 1111 | 83371111 |  | 1.3011 | 1.5312 |  | 15.6667 | 0.00074637 | 2529 | 0.053073 | 8252 | 3.9612e-05 | 6037
LARKIN (Y) 1110639640 | LARKIN (Y) 1110 | 22801110 |  | 0.76845 | 0.85494 |  | 13.3333 | 0.00074634 | 2531 | 0.053073 | 8251 | 3.961e-05 | 6038
EIGHT MILE 210288822 | EIGHT MILE 2102 | 163912102 |  | 3.5661 | 0.29533 |  | 71.3333 | 0.00054953 | 4867 | 0.072824 | 4681 | 3.961e-05 | 6039
COALINGA NO 1 1108CB | COALINGA NO 1 1108 | 252161108 |  | 4.4735 | 1.4522 |  | 62.25 | 0.00066092 | 3565 | 0.062491 | 6718 | 3.9607e-05 | 6040
OLIVEHURST 11037442 | OLIVEHURST 1103 | 152901103 |  | 7.8474 | 4.7562 |  | 142.3333 | 0.00063243 | 3910 | 0.063988 | 6546 | 3.9584e-05 | 6041
OAKLAND D 1112CB | OAKLAND D 1112 | 12041112 |  | 0.56475 | 0.57947 |  | 7.3333 | 0.00074576 | 2536 | 0.053073 | 8251 | 3.9579e-05 | 6042
EL CERRITO G 1110CB | EL CERRITO G 1110 | 12501110 | TRUE | 2.5831 | 2.2897 | 0.17604 | 29.95 | 0.00073709 | 2653 | 0.053538 | 8089 | 3.9579e-05 | 6043
BURLINGAME 04029056 | BURLINGAME 0402 | 24050402 |  | 3.9627 | 4.6404 |  | 61.3333 | 0.0006505 | 3703 | 0.060357 | 6981 | 3.9568e-05 | 6044
BERKELEY F 1102BR156 | BERKELEY F 1102 | 12061102 |  | 0.23423 | 0.13655 |  | 3.5 | 0.00074541 | 2540 | 0.053073 | 8251 | 3.9561e-05 | 6045
HICKS 1113CB | HICKS 1113 | 83431113 |  | 10.8965 | 11.6174 |  | 131.8667 | 0.00073602 | 2667 | 0.053753 | 8015 | 3.9556e-05 | 6046
DAVIS 1112CB | DAVIS 1112 | 62041112 |  | 2.3584 | 0.26855 |  | 37.4167 | 0.00061986 | 4051 | 0.067701 | 5508 | 3.9555e-05 | 6047
TIDEWATER 2106703654 | TIDEWATER 2106 | 14652106 |  | 1.0661 | 0 |  | 13.8333 | 0.00056157 | 4736 | 0.070564 | 4948 | 3.9555e-05 | 6048
BRENTWOOD 210838994 | BRENTWOOD 2108 | 14592108 |  | 1.9559 | 0.99273 |  | 36 | 0.0007392 | 2609 | 0.054233 | 7897 | 3.9553e-05 | 6049
SF L 0409CB | SF L 0409 | 22260409 |  | 0.14594 | 0.090042 |  | 3.5 | 0.0007452 | 2546 | 0.053073 | 8251 | 3.955e-05 | 6050
WHISMAN 1108LM34 | WHISMAN 1108 | 83631108 |  | 4.4079 | 3.5388 |  | 63.25 | 0.00074514 | 2547 | 0.053073 | 8252 | 3.9546e-05 | 6051
MARINA (F) 0405CB | MARINA (F) 0405 | 22780405 |  | 0.13855 | 0.10278 |  | 4.5 | 0.00074511 | 2548 | 0.053073 | 8251 | 3.9545e-05 | 6052
MONTAGUE 2104CB | MONTAGUE 2104 | 83892104 |  | 0.83795 | 0.13103 |  | 25.3333 | 0.00073764 | 2642 | 0.054091 | 7935 | 3.9541e-05 | 6053
RICHMOND Q 0401563674 | RICHMOND Q 0401 | 12520401 |  | 5.9502 | 6.447 |  | 67.25 | 0.000745 | 2549 | 0.053073 | 8253 | 3.9539e-05 | 6054
DALY CITY 111212075 | DALY CITY 1112 | 22641112 |  | 2.4855 | 2.4088 |  | 38.8333 | 0.00072052 | 2846 | 0.055179 | 7725 | 3.9537e-05 | 6055
DUMBARTON 1104MR300 | DUMBARTON 1104 | 14471104 |  | 0.10234 | 0 |  | 2.5 | 0.00074496 | 2550 | 0.053073 | 8251 | 3.9537e-05 | 6056
MADISON 2101888814 | MADISON 2101 | 63172101 |  | 0.020848 | 0 |  | 0.5 | 0.00058964 | 4420 | 0.067035 | 5975 | 3.9526e-05 | 6057
SAN PABLO 1105P200 | SAN PABLO 1105 | 14371105 |  | 2.9406 | 2.9616 |  | 53 | 0.00070967 | 2978 | 0.055546 | 7669 | 3.9523e-05 | 6058
LAS POSITAS 2106MR180 | LAS POSITAS 2106 | 14402106 |  | 1.8447 | 1.2382 |  | 36 | 0.00068601 | 3267 | 0.057522 | 7358 | 3.9522e-05 | 6059
YOSEMITE 0402CB | YOSEMITE 0402 | 22490402 |  | 2.4022 | 3.1785 |  | 31.5 | 0.00074466 | 2555 | 0.053073 | 8250 | 3.9521e-05 | 6060
CASTRO VALLEY 1107MR586 | CASTRO VALLEY 1107 | 14091107 |  | 2.2521 | 2.0853 |  | 41 | 0.00068239 | 3303 | 0.059264 | 7118 | 3.9516e-05 | 6061
RINCON 110275816 | RINCON 1102 | 43321102 |  | 0.86624 | 0 |  | 14.3333 | 0.00074446 | 2563 | 0.053073 | 8251 | 3.951e-05 | 6062
SERRAMONTE 110467957 | SERRAMONTE 1104 | 22861104 |  | 4.0904 | 3.6215 |  | 61.8333 | 0.00070302 | 3065 | 0.056284 | 7536 | 3.951e-05 | 6063
SONOMA 1107CB | SONOMA 1107 | 42721107 |  | 12.9004 | 2.9774 |  | 249 | 0.0005899 | 4417 | 0.066958 | 6080 | 3.9506e-05 | 6064
MC KEE 1107CB | MC KEE 1107 | 83531107 |  | 8.764 | 8.1014 |  | 141.6667 | 0.00074249 | 2579 | 0.05322 | 8210 | 3.949e-05 | 6065
DUMBARTON 11066672 | DUMBARTON 1106 | 14471106 |  | 0.03613 | 0 |  | 2 | 0.00062564 | 3990 | 0.063544 | 6607 | 3.9489e-05 | 6066
PACIFICA 110252715 | PACIFICA 1102 | 22811102 |  | 3.8043 | 3.8209 |  | 70.3333 | 0.00069188 | 3193 | 0.05703 | 7433 | 3.9486e-05 | 6067
ANDERSON 1103CB | ANDERSON 1103 | 103261103 |  | 5.9076 | 1.2814 |  | 107 | 0.00060507 | 4238 | 0.06575 | 6315 | 3.9482e-05 | 6068
DIXON LANDING 21028439 | DIXON LANDING 2102 | 14722102 |  | 1.5304 | 2.1911 |  | 22.5 | 0.00074378 | 2567 | 0.053073 | 8251 | 3.9474e-05 | 6069
SF H 1107CB | SF H 1107 | 22101107 |  | 1.3014 | 1.2688 |  | 17.9167 | 0.00074377 | 2568 | 0.053073 | 8250 | 3.9474e-05 | 6070
GLENWOOD 0405CB | GLENWOOD 0405 | 24090405 |  | 5.7416 | 4.4615 |  | 88.1667 | 0.0006574 | 3608 | 0.060787 | 6915 | 3.9465e-05 | 6071
WATSONVILLE 2101CB | WATSONVILLE 2101 | 83332101 |  | 10.5636 | 2.8885 |  | 167.25 | 0.00061243 | 4141 | 0.064815 | 6460 | 3.9464e-05 | 6072
OAKLAND J 1117CR104 | OAKLAND J 1117 | 12091117 |  | 3.1255 | 3.1027 |  | 45.5 | 0.00074356 | 2573 | 0.053073 | 8251 | 3.9463e-05 | 6073
EL CAPITAN 11062350 | EL CAPITAN 1106 | 253881106 |  | 3.2463 | 2.0203 |  | 61.1667 | 0.00073174 | 2708 | 0.054149 | 7913 | 3.9444e-05 | 6074
PUEBLO 1104640 | PUEBLO 1104 | 43291104 |  | 2.029 | 0.77966 |  | 40.5 | 0.00059355 | 4376 | 0.066417 | 6202 | 3.9439e-05 | 6075
LOYOLA 0401CB | LOYOLA 0401 | 82160401 |  | 4.6659 | 3.4505 |  | 71.45 | 0.00066079 | 3568 | 0.059869 | 7033 | 3.9436e-05 | 6076
OAKLAND D 1105BR306 | OAKLAND D 1105 | 12041105 |  | 2.5773 | 2.9659 |  | 35.1667 | 0.00074254 | 2578 | 0.053073 | 8250 | 3.9409e-05 | 6077
NEWARK 12KV 1102CB | NEWARK 12KV 1102 | 12221102 |  | 8.8773 | 6.8645 |  | 134.1167 | 0.00073722 | 2652 | 0.053405 | 8131 | 3.9407e-05 | 6078
CAROLANDS 04018888 | CAROLANDS 0401 | 24060401 |  | 1.371 | 0.24279 |  | 31.3333 | 0.00058803 | 4441 | 0.067013 | 6016 | 3.9407e-05 | 6079
PIERCY 2109CB | PIERCY 2109 | 83912109 |  | 1.8185 | 1.1677 |  | 29.1667 | 0.00063185 | 3919 | 0.06127 | 6860 | 3.9405e-05 | 6080
PUTAH CREEK 1103CB | PUTAH CREEK 1103 | 63681103 |  | 9.9807 | 4.0034 |  | 171.3333 | 0.00062862 | 3959 | 0.064174 | 6520 | 3.9404e-05 | 6081
DALY CITY 11061801 | DALY CITY 1106 | 22641106 |  | 6.7879 | 10.4369 |  | 120.3667 | 0.00073188 | 2707 | 0.053603 | 8057 | 3.937e-05 | 6082
BOGUE 1103CB | BOGUE 1103 | 153781103 |  | 6.9046 | 2.5179 |  | 98.8667 | 0.00071871 | 2865 | 0.056896 | 7451 | 3.9362e-05 | 6083
SARATOGA 110460104 | SARATOGA 1104 | 83371104 |  | 0.020744 | 0 |  | 0.5 | 0.00058746 | 4451 | 0.067 | 6057 | 3.936e-05 | 6084
MALAGA 1104R9510 | MALAGA 1104 | 254251104 |  | 2.471 | 0.47688 |  | 44 | 0.00064955 | 3712 | 0.062944 | 6666 | 3.9356e-05 | 6085
COARSEGOLD 210490356 | COARSEGOLD 2104 | 254432104 | FALSE | 17.4036 | 1.8262 | 4.8709 | 325 | 0.00011792 | 10970 | 0.39196 | 2925 | 3.9356e-05 | 6086
CAMPHORA 0401CB | CAMPHORA 0401 | 182070401 |  | 0.37901 | 0.026232 |  | 8.5 | 0.00058734 | 4452 | 0.067 | 6057 | 3.9352e-05 | 6087
VIERRA 170111718 | VIERRA 1701 | 162701701 |  | 6.1953 | 1.8045 |  | 43.3333 | 0.00074126 | 2587 | 0.054469 | 7849 | 3.9341e-05 | 6088
NORIEGA 0402CB | NORIEGA 0402 | 22510402 |  | 1.7271 | 2.9465 |  | 30.3667 | 0.00074124 | 2588 | 0.053073 | 8250 | 3.9339e-05 | 6089
OAKLAND D 1107CB | OAKLAND D 1107 | 12041107 |  | 2.5069 | 2.8641 |  | 40.25 | 0.00074123 | 2589 | 0.053073 | 8251 | 3.9339e-05 | 6090
BASALT 1106CB | BASALT 1106 | 42461106 |  | 13.6744 | 5.9266 |  | 212.5833 | 0.00067014 | 3431 | 0.059952 | 7025 | 3.9334e-05 | 6091
WOLFE 1109CB | WOLFE 1109 | 83671109 |  | 8.8869 | 10.9915 |  | 126.6667 | 0.00073801 | 2636 | 0.053403 | 8136 | 3.9329e-05 | 6092
STUART 0402CB | STUART 0402 | 13840402 |  | 3.7294 | 4.4396 |  | 44.8333 | 0.0007408 | 2591 | 0.053073 | 8251 | 3.9316e-05 | 6093
LAMMERS 1107CB | LAMMERS 1107 | 162771107 |  | 5.7642 | 0.57951 |  | 89.1667 | 0.00057327 | 4611 | 0.070214 | 5000 | 3.9311e-05 | 6094
REDWOOD CITY 1102CB | REDWOOD CITY 1102 | 24161102 |  | 1.6167 | 0.062534 |  | 18.0429 | 0.00074049 | 2594 | 0.053073 | 8251 | 3.93e-05 | 6095
BIG MEADOWS 21012016 | BIG MEADOWS 2101 | 102812101 | TRUE | 4.2474 | 2.6916 | 0.078732 | 84.3333 | 0.00042698 | 6148 | 0.086163 | 3363 | 3.9292e-05 | 6096
DAVIS 1101CB | DAVIS 1101 | 62041101 |  | 3.5189 | 0.36568 |  | 58 | 0.0006924 | 3185 | 0.05728 | 7396 | 3.9284e-05 | 6097
SF H 110510345 | SF H 1105 | 22101105 |  | 0.45033 | 0.53361 |  | 8.0833 | 0.00074015 | 2596 | 0.053073 | 8250 | 3.9282e-05 | 6098
HUNTERS POINT (P) 110341994 | HUNTERS POINT (P) 1103 | 22331103 |  | 3.2401 | 3.7502 |  | 45.3333 | 0.00074004 | 2597 | 0.053073 | 8251 | 3.9276e-05 | 6099
TRACY 1107CB | TRACY 1107 | 162881107 |  | 6.7626 | 4.1964 |  | 108.5833 | 0.00072531 | 2786 | 0.054655 | 7814 | 3.9272e-05 | 6100
MALAGA 1110R176 | MALAGA 1110 | 254251110 |  | 1.8781 | 0.44813 |  | 30 | 0.00056779 | 4686 | 0.070913 | 4903 | 3.9263e-05 | 6101
ALMADEN 111149936 | ALMADEN 1111 | 82311111 |  | 3.5868 | 4.3672 |  | 56.3333 | 0.00073964 | 2601 | 0.053073 | 8251 | 3.9255e-05 | 6102
CONTRA COSTA 2109CB | CONTRA COSTA 2109 | 13652109 |  | 5.1512 | 1.3436 |  | 71.8333 | 0.00058932 | 4422 | 0.06667 | 6149 | 3.9254e-05 | 6103
BURLINGAME 0402CB | BURLINGAME 0402 | 24050402 |  | 1.9232 | 2.0538 |  | 25.75 | 0.00073959 | 2602 | 0.053073 | 8252 | 3.9252e-05 | 6104
CHOWCHILLA 1103CB | CHOWCHILLA 1103 | 254101103 |  | 5.1015 | 0.99547 |  | 92.75 | 0.00056399 | 4718 | 0.072154 | 4761 | 3.925e-05 | 6105
CASTROVILLE 21035018 | CASTROVILLE 2103 | 182352103 |  | 0.19784 | 0.017093 |  | 2.5 | 0.0005858 | 4469 | 0.067 | 6057 | 3.9249e-05 | 6106
SF L 110286908 | SF L 1102 | 22261102 |  | 2.4211 | 2.851 |  | 32.3333 | 0.00073953 | 2604 | 0.053073 | 8250 | 3.9249e-05 | 6107
MARINA (F) 0407CB | MARINA (F) 0407 | 22780407 |  | 0.75542 | 0.84993 |  | 15.75 | 0.00073946 | 2605 | 0.053073 | 8251 | 3.9245e-05 | 6108
SAN JOSE A 1112XR428 | SAN JOSE A 1112 | 82251112 |  | 0.023077 | 0 |  | 0.5 | 0.00073943 | 2606 | 0.053073 | 8251 | 3.9244e-05 | 6109
OAKLAND X 1103CR414 | OAKLAND X 1103 | 12541103 |  | 0.81387 | 0.51262 |  | 14.6667 | 0.00073916 | 2610 | 0.053073 | 8252 | 3.9229e-05 | 6110
STELLING 1107CB | STELLING 1107 | 83481107 |  | 4.5094 | 3.6673 |  | 72.6667 | 0.00073909 | 2611 | 0.053073 | 8250 | 3.9226e-05 | 6111
HARRIS 11085984 | HARRIS 1108 | 192431108 |  | 0.45243 | 0.57093 |  | 6 | 0.00073905 | 2612 | 0.053073 | 8250 | 3.9224e-05 | 6112
OAKLAND X 1112CB | OAKLAND X 1112 | 12541112 |  | 0.60049 | 0.48917 |  | 9.5 | 0.00073898 | 2613 | 0.053073 | 8251 | 3.9219e-05 | 6113
SARATOGA 11141160 | SARATOGA 1114 | 83371114 |  | 10.0469 | 13.5345 |  | 151.5 | 0.00073897 | 2614 | 0.053073 | 8251 | 3.9219e-05 | 6114
BERKELEY F 1104BR118 | BERKELEY F 1104 | 12061104 |  | 2.421 | 2.0352 |  | 30.9167 | 0.0007389 | 2616 | 0.053073 | 8251 | 3.9215e-05 | 6115
RICHMOND R 1127CB | RICHMOND R 1127 | 13471127 |  | 2.6923 | 3.1578 |  | 44.9167 | 0.00073885 | 2617 | 0.053073 | 8251 | 3.9213e-05 | 6116
SONOMA 1103CB | SONOMA 1103 | 42721103 |  | 1.9941 | 1.3347 |  | 38.5 | 0.00067309 | 3401 | 0.058355 | 7241 | 3.921e-05 | 6117
LOCKEFORD 21024482 | LOCKEFORD 2102 | 163682102 |  | 0.13803 | 0 |  | 1.8333 | 0.00050656 | 5320 | 0.0774 | 3397 | 3.9208e-05 | 6118
BERESFORD 040249078 | BERESFORD 0402 | 24040402 |  | 0.25813 | 0.2129 |  | 4.5 | 0.00073864 | 2621 | 0.053073 | 8251 | 3.9201e-05 | 6119
SUISUN 110746732 | SUISUN 1107 | 62131107 |  | 4.7912 | 4.9659 |  | 70.1667 | 0.00073857 | 2623 | 0.053073 | 8250 | 3.9198e-05 | 6120
EAST GRAND 11071603 | EAST GRAND 1107 | 22571107 |  | 1.9084 | 1.4977 |  | 35.3333 | 0.0007334 | 2691 | 0.053467 | 8106 | 3.9196e-05 | 6121
BERKELEY T 0403CB | BERKELEY T 0403 | 12660403 |  | 0.70882 | 0.64754 |  | 9.8333 | 0.00073847 | 2625 | 0.053073 | 8251 | 3.9192e-05 | 6122
CASTRO VALLEY 11057406 | CASTRO VALLEY 1105 | 14091105 |  | 0.52218 | 0.60702 |  | 8.9167 | 0.00073838 | 2627 | 0.053073 | 8250 | 3.9188e-05 | 6123
SWIFT 2107XR356 | SWIFT 2107 | 83392107 |  | 3.4197 | 3.3849 |  | 52.8333 | 0.00065949 | 3585 | 0.059267 | 7117 | 3.9185e-05 | 6124
FLINT 110150960 | FLINT 1101 | 152531101 |  | 0.43711 | 0.012335 |  | 8.5 | 0.00060652 | 4222 | 0.064542 | 6481 | 3.9183e-05 | 6125
DIXON LANDING 2101XR340 | DIXON LANDING 2101 | 14722101 |  | 1.4778 | 1.7134 |  | 27.3333 | 0.00073828 | 2631 | 0.053073 | 8252 | 3.9183e-05 | 6126
CLAYTON 1104CB | CLAYTON 1104 | 12021104 |  | 8.7176 | 6.7794 |  | 134.7833 | 0.00068942 | 3228 | 0.057595 | 7342 | 3.9179e-05 | 6127
CASTRO VALLEY 1108CB | CASTRO VALLEY 1108 | 14091108 |  | 3.1781 | 3.6305 |  | 52.3333 | 0.00072353 | 2806 | 0.053804 | 8000 | 3.9178e-05 | 6128
MANTECA 17047788 | MANTECA 1704 | 162611704 |  | 0.0099598 | 0 |  | 0.5 | 0.00073814 | 2632 | 0.053073 | 8251 | 3.9175e-05 | 6129
OAKLAND X 1115CR216 | OAKLAND X 1115 | 12541115 |  | 2.9752 | 3.0298 |  | 40.8333 | 0.0007381 | 2634 | 0.053073 | 8251 | 3.9173e-05 | 6130
COTTONWOOD 110385050 | COTTONWOOD 1103 | 102931103 |  | 0.21093 | 0 |  | 4 | 0.00058461 | 4478 | 0.067 | 6057 | 3.9169e-05 | 6131
FRUITVALE 11042464 | FRUITVALE 1104 | 253391104 |  | 7.5683 | 2.2837 |  | 129.8333 | 0.00069973 | 3102 | 0.057533 | 7353 | 3.9167e-05 | 6132
NEWARK 12KV 11034162 | NEWARK 12KV 1103 | 12221103 |  | 0.0028156 | 0 |  | 0.5 | 0.00073769 | 2640 | 0.053073 | 8251 | 3.9151e-05 | 6133
SUISUN 110738516 | SUISUN 1107 | 62131107 |  | 1.5845 | 1.51 |  | 24 | 0.00073751 | 2644 | 0.053073 | 8251 | 3.9142e-05 | 6134
MABURY 1106XR026 | MABURY 1106 | 82191106 |  | 4.881 | 4.2594 |  | 76.3333 | 0.00073445 | 2680 | 0.053255 | 8194 | 3.914e-05 | 6135
OAKLAND J 1117CR108 | OAKLAND J 1117 | 12091117 |  | 4.7056 | 4.9066 |  | 65.6667 | 0.0007268 | 2765 | 0.054345 | 7880 | 3.914e-05 | 6136
BERKELEY F 0408CB | BERKELEY F 0408 | 12060408 |  | 0.79439 | 0.86141 |  | 9.3333 | 0.00073742 | 2647 | 0.053073 | 8251 | 3.9137e-05 | 6137
DEL MONTE 21032642 | DEL MONTE 2103 | 182222103 | TRUE | 2.263 | 2.4761 | 0.0092031 | 35.9167 | 0.00064325 | 3786 | 0.061454 | 6838 | 3.9137e-05 | 6138
SF H 1108CB | SF H 1108 | 22101108 |  | 3.3378 | 2.4417 |  | 38.8845 | 0.00071755 | 2886 | 0.055269 | 7711 | 3.9137e-05 | 6139
EUREKA A 11075980 | EUREKA A 1107 | 192121107 |  | 0.074118 | 0.065188 |  | 1 | 0.0007374 | 2648 | 0.053073 | 8251 | 3.9136e-05 | 6140
MT EDEN 1106MR652 | MT EDEN 1106 | 13761106 |  | 0.039113 | 0 |  | 1.5 | 0.00073694 | 2655 | 0.053073 | 8251 | 3.9111e-05 | 6141
MERCED 21026470 | MERCED 2102 | 252802102 |  | 7.4228 | 5.1558 |  | 110.8333 | 0.00070753 | 3012 | 0.055357 | 7697 | 3.9109e-05 | 6142
MABURY 1103XR346 | MABURY 1103 | 82191103 |  | 4.7515 | 5.9548 |  | 77.5 | 0.00073672 | 2658 | 0.053073 | 8251 | 3.9099e-05 | 6143
BOGUE 11027100 | BOGUE 1102 | 153781102 |  | 2.1326 | 0.69946 |  | 27.75 | 0.00073662 | 2659 | 0.053073 | 8251 | 3.9094e-05 | 6144
HICKS 1108CB | HICKS 1108 | 83431108 |  | 12.2026 | 14.3112 |  | 172.8333 | 0.00073216 | 2705 | 0.053297 | 8181 | 3.9091e-05 | 6145
SF K 0402CB | SF K 0402 | 22130402 |  | 3.3115 | 4.1619 |  | 45.3667 | 0.00073635 | 2663 | 0.053073 | 8251 | 3.908e-05 | 6146
LOS ALTOS 1104LM18 | LOS ALTOS 1104 | 82241104 |  | 3.8856 | 3.232 |  | 55.6667 | 0.00064832 | 3724 | 0.060662 | 6934 | 3.908e-05 | 6147
BELMONT 1106CB | BELMONT 1106 | 24031106 |  | 1.6422 | 0.23155 |  | 28.1667 | 0.00073631 | 2664 | 0.053073 | 8250 | 3.9078e-05 | 6148
HORSESHOE 1102CB | HORSESHOE 1102 | 152571102 |  | 1.6069 | 0.56686 |  | 21.8333 | 0.00058291 | 4491 | 0.067034 | 5980 | 3.9077e-05 | 6149
SARATOGA 1115LC18 | SARATOGA 1115 | 83371115 |  | 5.5493 | 4.4147 |  | 77.3333 | 0.00071909 | 2862 | 0.054423 | 7859 | 3.9059e-05 | 6150
SALINAS 110232832 | SALINAS 1102 | 182011102 |  | 3.225 | 3.7069 |  | 45.3333 | 0.00073582 | 2669 | 0.053073 | 8251 | 3.9052e-05 | 6151
BELLE HAVEN 0404CB | BELLE HAVEN 0404 | 24020404 |  | 8.6525 | 5.7176 |  | 132.1667 | 0.00060721 | 4208 | 0.064365 | 6501 | 3.9046e-05 | 6152
SAUSALITO 1102758798 | SAUSALITO 1102 | 42491102 | TRUE | 0.042277 | 0.023797 | 0.015194 | 1 | 0.00073563 | 2670 | 0.053073 | 8251 | 3.9042e-05 | 6153
OAKLAND J 0408CB | OAKLAND J 0408 | 12090408 |  | 4.5614 | 3.6783 |  | 53.25 | 0.00073556 | 2671 | 0.053073 | 8255 | 3.9038e-05 | 6154
DALY CITY 111113279 | DALY CITY 1111 | 22641111 |  | 5.816 | 9.5019 |  | 95.5333 | 0.00073553 | 2672 | 0.053073 | 8251 | 3.9037e-05 | 6155
BONITA 110238524 | BONITA 1102 | 255391102 |  | 0.17833 | 0 |  | 3 | 0.00073552 | 2673 | 0.053073 | 8251 | 3.9036e-05 | 6156
SANTA ROSA A 1106CB | SANTA ROSA A 1106 | 42151106 |  | 7.8323 | 5.5378 |  | 118 | 0.0007126 | 2942 | 0.05532 | 7704 | 3.9028e-05 | 6157
STOREY 1106CB | STOREY 1106 | 254611106 |  | 5.0664 | 3.519 |  | 86.0833 | 0.00063824 | 3847 | 0.059973 | 7022 | 3.9027e-05 | 6158
HICKS 2111XR154 | HICKS 2111 | 83432111 |  | 0.87215 | 0.67059 |  | 16 | 0.0007254 | 2785 | 0.053943 | 7971 | 3.9015e-05 | 6159
REEDLEY 11127441F | REEDLEY 1112 | 252341112 |  | 1.2116 | 1.2994 |  | 23.5 | 0.000586 | 4465 | 0.065815 | 6302 | 3.9015e-05 | 6160
MADERA 1114CB | MADERA 1114 | 252761114 |  | 4.1776 | 1.5039 |  | 58 | 0.00062208 | 4022 | 0.06573 | 6319 | 3.9014e-05 | 6161
EAST GRAND 0404CB | EAST GRAND 0404 | 22570404 |  | 3.8248 | 4.0354 |  | 48.75 | 0.00073501 | 2675 | 0.053073 | 8251 | 3.9009e-05 | 6162
SF H 110947238 | SF H 1109 | 22101109 |  | 3.2812 | 3.7886 |  | 49 | 0.00073496 | 2676 | 0.053073 | 8252 | 3.9006e-05 | 6163
SPENCE 1102CB | SPENCE 1102 | 182201102 |  | 3.3631 | 0.2578 |  | 48.0833 | 0.00058787 | 4445 | 0.066259 | 6219 | 3.9002e-05 | 6164
POTRERO PP (A) 11175545 | POTRERO PP (A) 1117 | 22031117 |  | 0.27064 | 0.40399 |  | 4.5833 | 0.00073441 | 2681 | 0.053073 | 8251 | 3.8977e-05 | 6165
VIRGINIA 0401BR312 | VIRGINIA 0401 | 13780401 |  | 0.98979 | 1.0539 |  | 12.4167 | 0.00073391 | 2684 | 0.053073 | 8252 | 3.895e-05 | 6166
VALLEJO B 0413CB | VALLEJO B 0413 | 42450413 |  | 6.4851 | 6.0673 |  | 80.7 | 0.00073381 | 2685 | 0.053073 | 8250 | 3.8946e-05 | 6167
PAUL SWEET 210794948 | PAUL SWEET 2107 | 83252107 |  | 8.5378 | 6.4725 |  | 122 | 0.00072286 | 2817 | 0.053786 | 8001 | 3.8941e-05 | 6168
POTRERO PP (A) 11096625 | POTRERO PP (A) 1109 | 22031109 |  | 1.4349 | 2.1626 |  | 24.5667 | 0.00073356 | 2687 | 0.053073 | 8250 | 3.8932e-05 | 6169
EMBARCADERO (Z) 1120273892 | EMBARCADERO (Z) 1120 | 22871120 |  | 0.11406 | 0.039919 |  | 4 | 0.00073351 | 2689 | 0.053073 | 8251 | 3.893e-05 | 6170
EL CERRITO G 1108BR254 | EL CERRITO G 1108 | 12501108 |  | 0.012066 | 0 |  | 0.25 | 0.0007334 | 2692 | 0.053073 | 8251 | 3.8923e-05 | 6171
TIDEWATER 210837382 | TIDEWATER 2108 | 14652108 |  | 1.6174 | 0.73917 |  | 23.3333 | 0.00073334 | 2694 | 0.053073 | 8251 | 3.892e-05 | 6172
TIDEWATER 210638108 | TIDEWATER 2106 | 14652106 |  | 1.8153 | 0 |  | 34.3333 | 0.00064342 | 3783 | 0.062766 | 6683 | 3.8898e-05 | 6173
ASHLAN AVE 1113635386 | ASHLAN AVE 1113 | 252051113 |  | 2.2205 | 0.42929 |  | 40 | 0.00056036 | 4750 | 0.070317 | 4976 | 3.8897e-05 | 6174
BASALT 1106316302 | BASALT 1106 | 42461106 |  | 0.024404 | 0 |  | 0.25 | 0.00050254 | 5365 | 0.0774 | 3397 | 3.8897e-05 | 6175
BASALT 1106CUS167 | BASALT 1106 | 42461106 |  | 0.013698 | 0 |  | 0.25 | 0.00050254 | 5365 | 0.0774 | 3397 | 3.8897e-05 | 6175
EDES 1105CB | EDES 1105 | 13681105 |  | 2.9843 | 2.4389 |  | 48 | 0.00073275 | 2700 | 0.053073 | 8251 | 3.8889e-05 | 6176
JESSUP 11031518 | JESSUP 1103 | 103441103 |  | 0.19363 | 0 |  | 3 | 0.0005804 | 4517 | 0.067 | 6057 | 3.8887e-05 | 6177
EL PATIO 1112XR222 | EL PATIO 1112 | 82921112 |  | 5.4054 | 4.8799 |  | 83.5 | 0.00073241 | 2702 | 0.053073 | 8251 | 3.8871e-05 | 6178
SARATOGA 1114XR420 | SARATOGA 1114 | 83371114 |  | 1.5047 | 1.5622 |  | 23 | 0.00073221 | 2703 | 0.053073 | 8251 | 3.8861e-05 | 6179
OAKLAND L 1101CB | OAKLAND L 1101 | 12111101 |  | 3.1179 | 2.9225 |  | 48.3333 | 0.00073219 | 2704 | 0.053073 | 8251 | 3.8859e-05 | 6180
VASONA 1102CB | VASONA 1102 | 83771102 |  | 14.7601 | 9.6804 |  | 261.8333 | 0.00065817 | 3595 | 0.059532 | 7082 | 3.8856e-05 | 6181
RICHMOND R 1130BR188 | RICHMOND R 1130 | 13471130 |  | 0.5083 | 0.4365 |  | 9.9167 | 0.00073192 | 2706 | 0.053073 | 8251 | 3.8845e-05 | 6182
ROSSMOOR 1106L552R | ROSSMOOR 1106 | 14161106 |  | 0.22844 | 0.25601 |  | 4.5 | 0.00057922 | 4532 | 0.06721 | 5799 | 3.8839e-05 | 6183
RINCON 1102228730 | RINCON 1102 | 43321102 |  | 1.4311 | 0.28627 |  | 27 | 0.00069925 | 3109 | 0.055921 | 7590 | 3.8832e-05 | 6184
OAKLAND C 1112CB | OAKLAND C 1112 | 12011112 |  | 1.1572 | 1.0961 |  | 19.6667 | 0.00073164 | 2709 | 0.053073 | 8250 | 3.883e-05 | 6185
TRINIDAD 1101CB | TRINIDAD 1101 | 192231101 |  | 11.1123 | 2.0246 |  | 206.5 | 0.00057929 | 4530 | 0.067024 | 5996 | 3.8823e-05 | 6186
NORTH TOWER 1104626 | NORTH TOWER 1104 | 42041104 |  | 4.9195 | 3.2181 |  | 58.75 | 0.0007315 | 2710 | 0.053073 | 8252 | 3.8823e-05 | 6187
RICHMOND R 1124BR302 | RICHMOND R 1124 | 13471124 |  | 2.1183 | 1.7266 |  | 29.5 | 0.00073141 | 2711 | 0.053073 | 8251 | 3.8818e-05 | 6188
OAKLAND X 1107CB | OAKLAND X 1107 | 12541107 |  | 1.538 | 1.6396 |  | 20.3333 | 0.00073137 | 2712 | 0.053073 | 8251 | 3.8816e-05 | 6189
POTRERO PP (A) 11123405 | POTRERO PP (A) 1112 | 22031112 |  | 0.89677 | 0.78875 |  | 11.75 | 0.00073132 | 2713 | 0.053073 | 8251 | 3.8813e-05 | 6190
FRANKLIN 1101P174 | FRANKLIN 1101 | 13921101 |  | 2.9293 | 2.7893 |  | 48 | 0.00066571 | 3485 | 0.058295 | 7251 | 3.8812e-05 | 6191
EAST GRAND 1103382750 | EAST GRAND 1103 | 22571103 |  | 0.45736 | 0.015713 |  | 6 | 0.00073126 | 2714 | 0.053073 | 8251 | 3.881e-05 | 6192
MENDOCINO 1102CB | MENDOCINO 1102 | 42951102 |  | 0.046493 | 0 |  | 0.83333 | 0.00057925 | 4531 | 0.067 | 6056 | 3.881e-05 | 6193
GREEN VALLEY 2103CB | GREEN VALLEY 2103 | 83192103 |  | 9.6916 | 2.6366 |  | 150.6667 | 0.00063183 | 3920 | 0.062244 | 6740 | 3.8805e-05 | 6194
MILPITAS 1108CB | MILPITAS 1108 | 82831108 |  | 5.7358 | 4.0011 |  | 86.1667 | 0.00071666 | 2893 | 0.055349 | 7700 | 3.8803e-05 | 6195
RICHMOND R 1118BR132 | RICHMOND R 1118 | 13471118 |  | 1.4974 | 0.48864 |  | 20 | 0.000731 | 2716 | 0.053073 | 8251 | 3.8796e-05 | 6196
FIGARDEN 2109CB | FIGARDEN 2109 | 254552109 |  | 1.774 | 0.91431 |  | 31 | 0.00073026 | 2723 | 0.053211 | 8212 | 3.8796e-05 | 6197
GREENBRAE 1101CB | GREENBRAE 1101 | 43091101 |  | 1.1423 | 0.41209 |  | 20 | 0.00071498 | 2910 | 0.054289 | 7891 | 3.8793e-05 | 6198
FAIRWAY 1104CB | FAIRWAY 1104 | 182061104 |  | 12.4827 | 7.3668 |  | 210.8333 | 0.00060097 | 4287 | 0.064967 | 6442 | 3.8788e-05 | 6199
WAHTOKE 1107CB | WAHTOKE 1107 | 254531107 |  | 11.8228 | 8.3016 |  | 187 | 0.00069465 | 3162 | 0.056343 | 7523 | 3.8775e-05 | 6200
TIDEWATER 2107M522R | TIDEWATER 2107 | 14652107 |  | 2.3966 | 2.35 |  | 32.8333 | 0.00072742 | 2756 | 0.053285 | 8185 | 3.8772e-05 | 6201
CLOVIS 1108CB | CLOVIS 1108 | 254081108 |  | 1.4861 | 0.12929 |  | 28.5833 | 0.00064455 | 3771 | 0.06387 | 6561 | 3.8769e-05 | 6202
MOUNTAIN VIEW 110251642 | MOUNTAIN VIEW 1102 | 82031102 |  | 5.003 | 5.7077 |  | 77.6667 | 0.00073035 | 2722 | 0.053073 | 8250 | 3.8761e-05 | 6203
REDWOOD CITY 0410CB | REDWOOD CITY 0410 | 24160410 |  | 3.5809 | 2.5275 |  | 47.3762 | 0.00073017 | 2725 | 0.053073 | 8250 | 3.8752e-05 | 6204
SAN JOSE A 0403CB | SAN JOSE A 0403 | 82250403 |  | 3.9888 | 3.3904 |  | 52.75 | 0.00073016 | 2726 | 0.053073 | 8251 | 3.8752e-05 | 6205
KING CITY 1101CB | KING CITY 1101 | 182031101 |  | 6.8974 | 5.6147 |  | 113 | 0.00071223 | 2943 | 0.054921 | 7761 | 3.8752e-05 | 6206
GRANT 1105CB | GRANT 1105 | 14381105 |  | 4.2033 | 2.7686 |  | 60 | 0.00069146 | 3203 | 0.056089 | 7566 | 3.8744e-05 | 6207
JARVIS 1111MR133 | JARVIS 1111 | 13501111 |  | 1.2446 | 0.58666 |  | 27 | 0.00067495 | 3371 | 0.057457 | 7366 | 3.8742e-05 | 6208
HUNTERS POINT (P) 1103CB | HUNTERS POINT (P) 1103 | 22331103 |  | 1.2468 | 1.5979 |  | 20.9583 | 0.00072995 | 2730 | 0.053073 | 8251 | 3.8741e-05 | 6209
WASCO 11041269 | WASCO 1104 | 252961104 |  | 4.4796 | 3.576 |  | 62.8333 | 0.00072941 | 2737 | 0.05321 | 8213 | 3.873e-05 | 6210
LOS ALTOS 1103CB | LOS ALTOS 1103 | 82241103 |  | 6.8221 | 5.7834 |  | 92 | 0.00069015 | 3216 | 0.056267 | 7539 | 3.873e-05 | 6211
RICHMOND R 1128BR324 | RICHMOND R 1128 | 13471128 |  | 2.8878 | 2.1773 |  | 49 | 0.0007297 | 2732 | 0.053073 | 8251 | 3.8727e-05 | 6212
ASHLAN AVE 111276862 | ASHLAN AVE 1112 | 252051112 |  | 3.1991 | 1.2517 |  | 56.5 | 0.00066862 | 3450 | 0.058759 | 7190 | 3.8727e-05 | 6213
MENLO 110276134 | MENLO 1102 | 24131102 |  | 0.72266 | 0.12432 |  | 13.5 | 0.00057743 | 4558 | 0.067067 | 5927 | 3.8726e-05 | 6214
LAKEWOOD 110483796 | LAKEWOOD 1104 | 13531104 |  | 2.832 | 1.5866 |  | 41.5833 | 0.0007176 | 2883 | 0.053826 | 7991 | 3.8726e-05 | 6215
WINTERS 110187886 | WINTERS 1101 | 63321101 |  | 0.036187 | 0 |  | 0.5 | 0.00057769 | 4554 | 0.067035 | 5975 | 3.8726e-05 | 6216
HARTER 1105CB | HARTER 1105 | 152851105 |  | 1.8687 | 0.63134 |  | 36.45 | 0.00066151 | 3556 | 0.05855 | 7216 | 3.8725e-05 | 6217
RICHMOND R 1130BR162 | RICHMOND R 1130 | 13471130 |  | 5.6632 | 6.2944 |  | 76.9167 | 0.00072958 | 2736 | 0.053073 | 8250 | 3.8721e-05 | 6218
DALY CITY 110115279 | DALY CITY 1101 | 22641101 |  | 1.5701 | 0.8926 |  | 25.5833 | 0.00063657 | 3864 | 0.061646 | 6808 | 3.8719e-05 | 6219
CASTRO 0401CB | CASTRO 0401 | 22480401 |  | 2.9253 | 2.5463 |  | 38.9 | 0.00072915 | 2739 | 0.053073 | 8251 | 3.8698e-05 | 6220
LAS PULGAS 0403CB | LAS PULGAS 0403 | 24120403 |  | 7.8449 | 7.2227 |  | 125.8333 | 0.00066619 | 3480 | 0.058828 | 7180 | 3.8697e-05 | 6221
CARQUINEZ 1103CB | CARQUINEZ 1103 | 43281103 |  | 3.1322 | 1.8035 |  | 45.6667 | 0.000729 | 2740 | 0.053073 | 8251 | 3.869e-05 | 6222
MADERA 1106CB | MADERA 1106 | 252761106 |  | 5.0439 | 2.0436 |  | 92.1667 | 0.00065762 | 3603 | 0.059721 | 7051 | 3.8689e-05 | 6223
OAKLAND J 1111CR378 | OAKLAND J 1111 | 12091111 |  | 1.6034 | 1.8065 |  | 24 | 0.00072898 | 2741 | 0.053073 | 8250 | 3.8689e-05 | 6224
ASHLAN AVE 110985686 | ASHLAN AVE 1109 | 252051109 |  | 5.0428 | 1.5722 |  | 70.5 | 0.00062894 | 3953 | 0.062583 | 6703 | 3.8683e-05 | 6225
WEST LANE 1102CB | WEST LANE 1102 | 163621102 |  | 2.9603 | 0.73798 |  | 53.5 | 0.00062841 | 3964 | 0.063653 | 6590 | 3.8679e-05 | 6226
SANTA MARIA 1107CB | SANTA MARIA 1107 | 182671107 |  | 4.5653 | 2.6781 |  | 69.5 | 0.00066691 | 3471 | 0.058183 | 7270 | 3.8679e-05 | 6227
SAN PABLO 1105P188 | SAN PABLO 1105 | 14371105 |  | 0.81399 | 0.33366 |  | 15.1667 | 0.00065636 | 3620 | 0.059195 | 7132 | 3.8677e-05 | 6228
EAST GRAND 0401CB | EAST GRAND 0401 | 22570401 |  | 4.76 | 4.9121 |  | 67.75 | 0.00070508 | 3042 | 0.055503 | 7672 | 3.8677e-05 | 6229
GATES 1109CB | GATES 1109 | 253931109 |  | 0.30006 | 0 |  | 5.8333 | 0.00058112 | 4507 | 0.066698 | 6136 | 3.8674e-05 | 6230
COTTLE 17049110 | COTTLE 1704 | 163711704 |  | 2.1082 | 1.0808 |  | 34.3333 | 0.00071974 | 2855 | 0.053781 | 8004 | 3.8669e-05 | 6231
OAKLAND X 1102CR120 | OAKLAND X 1102 | 12541102 |  | 1.6268 | 2.0436 |  | 24.1667 | 0.00072845 | 2744 | 0.053073 | 8250 | 3.8661e-05 | 6232
OAKLAND D 1112CR166 | OAKLAND D 1112 | 12041112 |  | 2.0424 | 2.3159 |  | 28.8333 | 0.00072831 | 2747 | 0.053073 | 8251 | 3.8654e-05 | 6233
FIGARDEN 210846252 | FIGARDEN 2108 | 254552108 |  | 1.8768 | 1.5928 |  | 36.1667 | 0.00065145 | 3691 | 0.060696 | 6926 | 3.8651e-05 | 6234
TEMBLOR 2103CB | TEMBLOR 2103 | 252552103 |  | 5.6963 | 0.017472 |  | 92 | 0.00057682 | 4563 | 0.067 | 6057 | 3.8647e-05 | 6235
ROSSMOOR 1105CB | ROSSMOOR 1105 | 14161105 |  | 1.7803 | 0 |  | 17.8095 | 0.00058393 | 4485 | 0.066113 | 6243 | 3.8645e-05 | 6236
NAPA 11025057 | NAPA 1102 | 42021102 |  | 1.9774 | 2.3699 |  | 36.5 | 0.0007281 | 2750 | 0.053073 | 8251 | 3.8642e-05 | 6237
RICHMOND R 1126BR274 | RICHMOND R 1126 | 13471126 |  | 0.63577 | 0.87257 |  | 13.3333 | 0.00067492 | 3373 | 0.057251 | 7398 | 3.863e-05 | 6238
CLAYTON 2215W573R | CLAYTON 2215 | 12022215 |  | 8.0274 | 5.1706 |  | 121 | 0.00067622 | 3355 | 0.05713 | 7417 | 3.8626e-05 | 6239
VIERRA 170198454 | VIERRA 1701 | 162701701 |  | 3.1172 | 0.3497 |  | 49.3333 | 0.00065614 | 3622 | 0.059658 | 7061 | 3.8622e-05 | 6240
NEWMAN 1102CB | NEWMAN 1102 | 162741102 |  | 5.7297 | 2.5582 |  | 94 | 0.00066626 | 3478 | 0.061575 | 6815 | 3.8622e-05 | 6241
CORDELIA 1110965712 | CORDELIA 1110 | 62701110 |  | 2.058 | 0.75889 |  | 39.8333 | 0.00059036 | 4410 | 0.065961 | 6280 | 3.862e-05 | 6242
MORGAN HILL 2106XR224 | MORGAN HILL 2106 | 83242106 |  | 1.7652 | 0.21922 |  | 35 | 0.00065197 | 3685 | 0.06068 | 6929 | 3.8615e-05 | 6243
MC CALL 1107CB | MC CALL 1107 | 254121107 |  | 4.9761 | 0.44345 |  | 71.95 | 0.00050439 | 5344 | 0.076868 | 3846 | 3.8608e-05 | 6244
MOUNTAIN VIEW 1106CB | MOUNTAIN VIEW 1106 | 82031106 |  | 3.7823 | 2.8976 |  | 64.3333 | 0.00072745 | 2755 | 0.053073 | 8252 | 3.8608e-05 | 6245
SALINAS 1101932856 | SALINAS 1101 | 182011101 |  | 2.773 | 1.2414 |  | 49.1667 | 0.00072723 | 2758 | 0.053073 | 8252 | 3.8596e-05 | 6246
EVERGREEN 2105CB | EVERGREEN 2105 | 82012105 |  | 2.3278 | 0.24897 |  | 41.0833 | 0.00066143 | 3557 | 0.060361 | 6979 | 3.8596e-05 | 6247
BRITTON 1110LV32 | BRITTON 1110 | 83611110 |  | 2.4609 | 2.2058 |  | 33 | 0.00072708 | 2759 | 0.053073 | 8251 | 3.8588e-05 | 6248
LEMOORE 110275452 | LEMOORE 1102 | 253601102 |  | 2.919 | 0.075537 |  | 47.5 | 0.00058433 | 4480 | 0.068031 | 5400 | 3.8584e-05 | 6249
MISSION (X) 110812135 | MISSION (X) 1108 | 22011108 |  | 0.50167 | 0.64209 |  | 10.75 | 0.0007269 | 2763 | 0.053073 | 8251 | 3.8579e-05 | 6250
GREEN VALLEY 210395184 | GREEN VALLEY 2103 | 83192103 |  | 3.2796 | 0.7767 |  | 57 | 0.00065748 | 3607 | 0.059332 | 7109 | 3.8576e-05 | 6251
DEL MAR 211064434 | DEL MAR 2110 | 152582110 |  | 0.21446 | 0 |  | 5 | 0.0005574 | 4791 | 0.06804 | 5397 | 3.8576e-05 | 6252
CLAY 11029999 | CLAY 1102 | 163341102 |  | 0.12154 | 0 |  | 2.5 | 0.00057566 | 4582 | 0.067 | 6057 | 3.8569e-05 | 6253
MALAGA 1110R9547 | MALAGA 1110 | 254251110 |  | 4.6711 | 2.6362 |  | 82 | 0.00072581 | 2781 | 0.053178 | 8220 | 3.8569e-05 | 6254
BARRETT 0401CB | BARRETT 0401 | 13020401 |  | 6.5757 | 7.8706 |  | 80 | 0.00072667 | 2767 | 0.053073 | 8251 | 3.8566e-05 | 6255
FIGARDEN 211263889 | FIGARDEN 2112 | 254552112 |  | 2.1491 | 0.083266 |  | 34.5 | 0.00069622 | 3148 | 0.057553 | 7347 | 3.8565e-05 | 6256
SF H 110614703 | SF H 1106 | 22101106 |  | 2.0509 | 1.9667 |  | 27.75 | 0.00072664 | 2768 | 0.053073 | 8251 | 3.8565e-05 | 6257
FAIRWAY 1103CB | FAIRWAY 1103 | 182061103 |  | 5.6291 | 0.99717 |  | 91.5 | 0.00060655 | 4221 | 0.064487 | 6488 | 3.8564e-05 | 6258
CLAYTON 221714102 | CLAYTON 2217 | 12022217 |  | 12.0329 | 10.9753 |  | 169.3333 | 0.00071286 | 2938 | 0.05443 | 7858 | 3.8553e-05 | 6259
JARVIS 1101467034 | JARVIS 1101 | 13501101 |  | 7.5821 | 4.7044 |  | 137.5 | 0.00050915 | 5296 | 0.098427 | 3319 | 3.8549e-05 | 6260
WEBER 110170700 | WEBER 1101 | 163481101 |  | 0.61157 | 0.026614 |  | 10.5 | 0.00072628 | 2772 | 0.053073 | 8251 | 3.8546e-05 | 6261
ALMADEN 1111XR120 | ALMADEN 1111 | 82311111 |  | 1.1781 | 0.10812 |  | 19.5 | 0.00072626 | 2773 | 0.053073 | 8251 | 3.8545e-05 | 6262
REDWOOD CITY 0405CB | REDWOOD CITY 0405 | 24160405 |  | 3.354 | 2.8837 |  | 50.3667 | 0.00072623 | 2775 | 0.053073 | 8251 | 3.8543e-05 | 6263
HIGHWAY 11044701 | HIGHWAY 1104 | 42651104 |  | 0.82982 | 0.71477 |  | 10.8333 | 0.00071469 | 2915 | 0.054195 | 7905 | 3.854e-05 | 6264
CORONA 1102CB | CORONA 1102 | 43491102 |  | 1.3829 | 0.045893 |  | 26.5 | 0.00072322 | 2813 | 0.053327 | 8166 | 3.8535e-05 | 6265
MAGUNDEN 2108289792 | MAGUNDEN 2108 | 252772108 |  | 0.019075 | 0 |  | 0.5 | 0.00049779 | 5415 | 0.0774 | 3397 | 3.8528e-05 | 6266
MT EDEN 1101MR113 | MT EDEN 1101 | 13761101 |  | 1.7883 | 0.98708 |  | 28.5 | 0.00072595 | 2779 | 0.053073 | 8251 | 3.8528e-05 | 6267
FIGARDEN 2112R1012 | FIGARDEN 2112 | 254552112 |  | 1.7859 | 0.43703 |  | 27 | 0.00057414 | 4599 | 0.070961 | 4897 | 3.8528e-05 | 6268
PUEBLO 1105642 | PUEBLO 1105 | 43291105 |  | 4.2942 | 2.0146 |  | 89.5 | 0.00057677 | 4565 | 0.066672 | 6148 | 3.8527e-05 | 6269
COTATI 110283200 | COTATI 1102 | 42271102 |  | 2.8523 | 1.4617 |  | 55.5 | 0.00071291 | 2937 | 0.054388 | 7868 | 3.8526e-05 | 6270
CHOWCHILLA 110510650 | CHOWCHILLA 1105 | 254101105 |  | 3.1423 | 4.1411 |  | 64 | 0.00072588 | 2780 | 0.053073 | 8251 | 3.8525e-05 | 6271
VACA DIXON 1101CB | VACA DIXON 1101 | 63591101 |  | 2.6897 | 0 |  | 37.7333 | 0.00057327 | 4613 | 0.067203 | 5806 | 3.8509e-05 | 6272
VASONA 1105LC32 | VASONA 1105 | 83771105 |  | 6.547 | 5.1764 |  | 95.3333 | 0.00071781 | 2879 | 0.053583 | 8070 | 3.8507e-05 | 6273
FORT BRAGG A 1101CB | FORT BRAGG A 1101 | 42761101 | TRUE | 7.9372 | 5.3182 | 0.0072987 | 111.75 | 0.00066318 | 3525 | 0.058401 | 7233 | 3.8505e-05 | 6274
BELMONT 0401CB | BELMONT 0401 | 24030401 |  | 5.5664 | 3.921 |  | 71.75 | 0.0006903 | 3215 | 0.055984 | 7581 | 3.8498e-05 | 6275
LAKEWOOD 211093966 | LAKEWOOD 2110 | 13532110 |  | 1.1334 | 0.33304 |  | 20.3333 | 0.00065243 | 3676 | 0.057926 | 7306 | 3.8496e-05 | 6276
BERKELEY T 0403566022 | BERKELEY T 0403 | 12660403 |  | 0.15559 | 0.15142 |  | 2.5 | 0.0007253 | 2787 | 0.053073 | 8251 | 3.8493e-05 | 6277
BRITTON 1114CB | BRITTON 1114 | 83611114 |  | 4.0661 | 3.1746 |  | 62.8333 | 0.00072516 | 2788 | 0.053073 | 8251 | 3.8486e-05 | 6278
SAN JOSE B 1110CB | SAN JOSE B 1110 | 82261110 |  | 10.0579 | 7.7548 |  | 169.9167 | 0.00072474 | 2792 | 0.053073 | 8251 | 3.8464e-05 | 6279
EL PATIO 1117CB | EL PATIO 1117 | 82921117 |  | 4.1659 | 3.6221 |  | 77.5 | 0.00072472 | 2793 | 0.053073 | 8251 | 3.8463e-05 | 6280
BARTON 1111R1200 | BARTON 1111 | 253571111 |  | 6.5918 | 4.005 |  | 99.8333 | 0.00072351 | 2807 | 0.053245 | 8199 | 3.8459e-05 | 6281
NORTH TOWER 1104784 | NORTH TOWER 1104 | 42041104 |  | 0.52502 | 0.18469 |  | 11.75 | 0.00057387 | 4605 | 0.067011 | 6022 | 3.8457e-05 | 6282
RIPON 1702CB | RIPON 1702 | 163801702 |  | 5.5537 | 1.2404 |  | 97 | 0.00067849 | 3340 | 0.060184 | 6998 | 3.8455e-05 | 6283
BELMONT 0403CB | BELMONT 0403 | 24030403 |  | 4.658 | 2.8 |  | 50.1667 | 0.00072001 | 2853 | 0.053489 | 8099 | 3.8437e-05 | 6284
TIDEWATER 2106C514R | TIDEWATER 2106 | 14652106 |  | 3.4262 | 3.2705 |  | 55.6667 | 0.00065099 | 3700 | 0.060177 | 6999 | 3.8436e-05 | 6285
BERKELEY F 0405CB | BERKELEY F 0405 | 12060405 |  | 1.0147 | 0.84031 |  | 15.1667 | 0.00072421 | 2800 | 0.053073 | 8252 | 3.8436e-05 | 6286
SAN LUIS OBISPO 1102V96 | SAN LUIS OBISPO 1102 | 182631102 |  | 3.9712 | 3.3336 |  | 54.3333 | 0.00070356 | 3058 | 0.054614 | 7823 | 3.8424e-05 | 6287
SAN JOSE A 1109CB | SAN JOSE A 1109 | 82251109 |  | 0.58549 | 0.3078 |  | 13.3333 | 0.00072391 | 2802 | 0.053073 | 8250 | 3.842e-05 | 6288
EL CAPITAN 211010960 | EL CAPITAN 2110 | 253882110 |  | 3.4741 | 1.5958 |  | 54.5 | 0.00072389 | 2803 | 0.053073 | 8251 | 3.8419e-05 | 6289
PAUL SWEET 210398594 | PAUL SWEET 2103 | 83252103 |  | 3.0811 | 2.7514 |  | 49.8667 | 0.00068868 | 3234 | 0.055619 | 7653 | 3.8411e-05 | 6290
SF E 1103CB | SF E 1103 | 22071103 |  | 1.2388 | 1.2549 |  | 17.4167 | 0.00072371 | 2805 | 0.053073 | 8253 | 3.8409e-05 | 6291
EAST QUINCY 1101CB | EAST QUINCY 1101 | 102551101 |  | 1.3551 | 0.54176 |  | 19.5 | 0.0005445 | 4916 | 0.070064 | 5032 | 3.8404e-05 | 6292
OAKLAND X 1102CR122 | OAKLAND X 1102 | 12541102 |  | 1.8343 | 1.7278 |  | 23 | 0.00072349 | 2808 | 0.053073 | 8251 | 3.8398e-05 | 6293
GERBER 1101CB | GERBER 1101 | 103391101 |  | 3.1955 | 1.5582 |  | 56.5 | 0.00058663 | 4459 | 0.065526 | 6355 | 3.8395e-05 | 6294
CONTRA COSTA 210974988 | CONTRA COSTA 2109 | 13652109 |  | 5.1337 | 1.1171 |  | 89.3333 | 0.00060755 | 4202 | 0.066785 | 6124 | 3.8395e-05 | 6295
STOCKDALE 11094704 | STOCKDALE 1109 | 254071109 |  | 0.54789 | 0.01055 |  | 7.8333 | 0.00072308 | 2815 | 0.053073 | 8252 | 3.8376e-05 | 6296
PAUL SWEET 210878006 | PAUL SWEET 2108 | 83252108 |  | 5.1853 | 5.0208 |  | 73.6667 | 0.00067637 | 3354 | 0.057232 | 7402 | 3.8373e-05 | 6297
STELLING 1108LL08 | STELLING 1108 | 83481108 |  | 3.6478 | 3.2678 |  | 58.3333 | 0.00066316 | 3527 | 0.057967 | 7296 | 3.8364e-05 | 6298
BAY MEADOWS 110748112 | BAY MEADOWS 1107 | 24011107 |  | 1.592 | 1.0193 |  | 31 | 0.00072284 | 2818 | 0.053073 | 8251 | 3.8363e-05 | 6299
SF E 110162024 | SF E 1101 | 22071101 |  | 1.0926 | 1.3713 |  | 17.6167 | 0.00072283 | 2819 | 0.053073 | 8252 | 3.8363e-05 | 6300
WYANDOTTE 11102590 | WYANDOTTE 1110 | 102911110 |  | 0.61053 | 0 |  | 9.5 | 0.0005822 | 4500 | 0.064373 | 6499 | 3.8359e-05 | 6301
OAKLAND D 1130455660 | OAKLAND D 1130 | 12041130 |  | 0.24304 | 0.23757 |  | 4.8333 | 0.00072276 | 2820 | 0.053073 | 8252 | 3.8359e-05 | 6302
VALLEJO B 11017410 | VALLEJO B 1101 | 42451101 |  | 9.7375 | 8.6789 |  | 135.3333 | 0.00072273 | 2821 | 0.053073 | 8252 | 3.8357e-05 | 6303
RIDGE 0401CB | RIDGE 0401 | 12840401 | FALSE | 2.6559 | 2.8332 | 5.4697 | 39.6667 | 0.00057368 | 4606 | 0.066838 | 6112 | 3.8355e-05 | 6304
WYANDOTTE 11101952 | WYANDOTTE 1110 | 102911110 |  | 8.7468 | 3.7237 |  | 150 | 0.0005573 | 4792 | 0.079585 | 3388 | 3.8354e-05 | 6305
BAKERSFIELD 21041574 | BAKERSFIELD 2104 | 253372104 |  | 6.8737 | 5.2724 |  | 115.5 | 0.00069107 | 3207 | 0.056016 | 7576 | 3.8346e-05 | 6306
SAN LEANDRO U 1110CB | SAN LEANDRO U 1110 | 13111110 |  | 5.8351 | 5.3381 |  | 83.3333 | 0.00071362 | 2929 | 0.053657 | 8045 | 3.8332e-05 | 6307
EL CERRITO G 1109CB | EL CERRITO G 1109 | 12501109 |  | 5.2763 | 2.8134 |  | 60.8167 | 0.00070004 | 3097 | 0.054894 | 7768 | 3.8328e-05 | 6308
MABURY 1106CB | MABURY 1106 | 82191106 |  | 6.1775 | 6.3519 |  | 101.9167 | 0.00072202 | 2830 | 0.053073 | 8250 | 3.8319e-05 | 6309
POTRERO PP (A) 110966602 | POTRERO PP (A) 1109 | 22031109 |  | 2.0839 | 2.7733 |  | 31.0333 | 0.000722 | 2831 | 0.053073 | 8251 | 3.8318e-05 | 6310
MC KEE 1108XR302 | MC KEE 1108 | 83531108 |  | 6.5906 | 6.1016 |  | 113.8333 | 0.00065546 | 3634 | 0.05884 | 7178 | 3.8305e-05 | 6311
KERN OIL 1114CB | KERN OIL 1114 | 252721114 |  | 21.5646 | 11.8605 |  | 317.75 | 0.00064166 | 3808 | 0.062526 | 6712 | 3.8296e-05 | 6312
MAGUNDEN 210814402 | MAGUNDEN 2108 | 252772108 |  | 2.043 | 1.3047 |  | 28 | 0.00060685 | 4218 | 0.063064 | 6656 | 3.8292e-05 | 6313
PAUL SWEET 210711064 | PAUL SWEET 2107 | 83252107 |  | 4.6289 | 3.8832 |  | 66.8333 | 0.00063537 | 3877 | 0.060128 | 7003 | 3.8287e-05 | 6314
6TH AVENUE 0403CB | 6TH AVENUE 0403 | 22530403 |  | 1.7802 | 2.4357 |  | 25.25 | 0.00072131 | 2837 | 0.053073 | 8251 | 3.8282e-05 | 6315
WOODLAND 1113CB | WOODLAND 1113 | 62031113 |  | 9.8813 | 0.75788 |  | 153.8333 | 0.00061032 | 4164 | 0.067836 | 5463 | 3.8281e-05 | 6316
NEWARK 21KV 2107MR494 | NEWARK 21KV 2107 | 12232107 |  | 2.489 | 1.1569 |  | 43 | 0.00069966 | 3104 | 0.054692 | 7807 | 3.8277e-05 | 6317
ANDERSON 110299392 | ANDERSON 1102 | 103261102 |  | 0.26498 | 0.10973 |  | 7 | 0.00072122 | 2838 | 0.053073 | 8251 | 3.8277e-05 | 6318
SARATOGA 1109LC42 | SARATOGA 1109 | 83371109 |  | 5.0089 | 5.5515 |  | 65 | 0.0007211 | 2840 | 0.053073 | 8251 | 3.827e-05 | 6319
CANAL 1105990288 | CANAL 1105 | 252091105 |  | 4.3041 | 2.3705 |  | 58.3333 | 0.00069065 | 3210 | 0.055931 | 7588 | 3.827e-05 | 6320
JARVIS 11039057 | JARVIS 1103 | 13501103 |  | 0.060951 | 0 |  | 1.3333 | 0.00072105 | 2841 | 0.053073 | 8251 | 3.8268e-05 | 6321
WOLFE 1105LC34 | WOLFE 1105 | 83671105 |  | 3.0295 | 3.7392 |  | 41.5 | 0.0006908 | 3208 | 0.055086 | 7736 | 3.8255e-05 | 6322
SAN JOSE A 0408CB | SAN JOSE A 0408 | 82250408 |  | 2.4052 | 2.165 |  | 36.5 | 0.00072064 | 2845 | 0.053073 | 8251 | 3.8246e-05 | 6323
WEBER 1105CB | WEBER 1105 | 163481105 |  | 12.7522 | 10.2888 |  | 218 | 0.00069846 | 3123 | 0.055816 | 7613 | 3.823e-05 | 6324
SAN RAFAEL 1105344 | SAN RAFAEL 1105 | 42011105 | TRUE | 4.6119 | 3.5417 | 0.092455 | 80 | 0.00055529 | 4815 | 0.072636 | 4706 | 3.8229e-05 | 6325
HICKS 1109XR138 | HICKS 1109 | 83431109 |  | 4.4461 | 4.9231 |  | 65.8333 | 0.00072029 | 2849 | 0.053073 | 8250 | 3.8228e-05 | 6326
LEMOORE 1105CB | LEMOORE 1105 | 253601105 |  | 3.0089 | 1.0571 |  | 56.0333 | 0.00066222 | 3543 | 0.063927 | 6555 | 3.8218e-05 | 6327
RICHMOND R 1129BR218 | RICHMOND R 1129 | 13471129 |  | 1.0788 | 0.10919 |  | 17 | 0.00062238 | 4020 | 0.061869 | 6782 | 3.8216e-05 | 6328
WILLIAMS 1101CB | WILLIAMS 1101 | 62051101 |  | 1.8517 | 0.089114 |  | 27 | 0.00061375 | 4126 | 0.063302 | 6626 | 3.8207e-05 | 6329
STELLING 1108LM42 | STELLING 1108 | 83481108 |  | 11.9762 | 7.4384 |  | 203.5 | 0.0006149 | 4108 | 0.062494 | 6717 | 3.8203e-05 | 6330
SAN RAFAEL 1103302 | SAN RAFAEL 1103 | 42011103 |  | 2.8108 | 0.89399 |  | 57 | 0.00065393 | 3657 | 0.058856 | 7177 | 3.8197e-05 | 6331
DALY CITY 110539396 | DALY CITY 1105 | 22641105 |  | 3.9706 | 3.6593 |  | 58.8333 | 0.00068003 | 3324 | 0.055765 | 7627 | 3.8188e-05 | 6332
STONE 1101XR470 | STONE 1101 | 83701101 |  | 5.6094 | 6.3673 |  | 85.3333 | 0.00071812 | 2876 | 0.053154 | 8230 | 3.8185e-05 | 6333
LLAGAS 2105XR320 | LLAGAS 2105 | 83182105 |  | 5.7517 | 7.6749 |  | 102.3333 | 0.0007116 | 2954 | 0.054261 | 7895 | 3.8184e-05 | 6334
CONTRA COSTA 210378825 | CONTRA COSTA 2103 | 13652103 |  | 6.0478 | 2.1334 |  | 100 | 0.00062014 | 4047 | 0.061089 | 6883 | 3.8181e-05 | 6335
CABRILLO 1104CB | CABRILLO 1104 | 183101104 |  | 3.9338 | 0 |  | 50.5 | 0.00071653 | 2898 | 0.053348 | 8156 | 3.8178e-05 | 6336
MAGUNDEN 1104CB | MAGUNDEN 1104 | 252771104 |  | 5.159 | 4.2797 |  | 93.4762 | 0.00064638 | 3749 | 0.059763 | 7045 | 3.8174e-05 | 6337
SF G 0405CB | SF G 0405 | 22090405 |  | 1.4702 | 1.2579 |  | 16.75 | 0.00071917 | 2860 | 0.053073 | 8251 | 3.8168e-05 | 6338
MILPITAS 1109XR208 | MILPITAS 1109 | 82831109 |  | 0.38712 | 0.16105 |  | 8.5 | 0.00058893 | 4427 | 0.065957 | 6281 | 3.8168e-05 | 6339
NORD 11032478 | NORD 1103 | 103071103 |  | 5.8293 | 1.7776 |  | 106.5 | 0.00057437 | 4596 | 0.067236 | 5774 | 3.8163e-05 | 6340
OAKLAND K 1101CR174 | OAKLAND K 1101 | 12101101 |  | 1.0496 | 0.87714 |  | 19.3333 | 0.00065524 | 3637 | 0.058716 | 7198 | 3.8141e-05 | 6341
TRACY 1106352284 | TRACY 1106 | 162881106 |  | 0.65347 | 0 |  | 12 | 0.00062198 | 4024 | 0.06154 | 6823 | 3.8141e-05 | 6342
RALSTON 1101CB | RALSTON 1101 | 24141101 | FALSE | 2.9167 | 2.399 | 0.69497 | 47 | 0.00057008 | 4657 | 0.066985 | 6066 | 3.814e-05 | 6343
GREEN VALLEY 2103938286 | GREEN VALLEY 2103 | 83192103 |  | 2.0723 | 1.5228 |  | 36.6667 | 0.00069211 | 3190 | 0.055352 | 7698 | 3.8139e-05 | 6344
SF K 0405CB | SF K 0405 | 22130405 |  | 2.8108 | 3.2152 |  | 32.6667 | 0.00071861 | 2867 | 0.053073 | 8250 | 3.8138e-05 | 6345
TARAVAL 0401CB | TARAVAL 0401 | 22500401 |  | 1.8162 | 2.6198 |  | 26.7 | 0.00071848 | 2869 | 0.053073 | 8249 | 3.8132e-05 | 6346
BANTA 1102CB | BANTA 1102 | 162471102 |  | 4.3769 | 0.6305 |  | 72.5 | 0.00055345 | 4829 | 0.070353 | 4970 | 3.8131e-05 | 6347
POINT PINOLE 1102P152 | POINT PINOLE 1102 | 14261102 |  | 0.39139 | 0.16269 |  | 7.5 | 0.00071834 | 2872 | 0.053073 | 8251 | 3.8124e-05 | 6348
SANTA ROSA A 1102CB | SANTA ROSA A 1102 | 42151102 |  | 8.5377 | 6.8863 |  | 136 | 0.00070453 | 3049 | 0.054201 | 7903 | 3.8124e-05 | 6349
MISSION (X) 1116265740 | MISSION (X) 1116 | 22011116 |  | 0.40597 | 0.36173 |  | 9.9167 | 0.00071833 | 2873 | 0.053073 | 8251 | 3.8124e-05 | 6350
SONOMA 1104412 | SONOMA 1104 | 42721104 |  | 2.3457 | 1.7154 |  | 42.5 | 0.00065961 | 3583 | 0.058316 | 7247 | 3.8123e-05 | 6351
STUART 0403CB | STUART 0403 | 13840403 |  | 3.1153 | 3.0016 |  | 38.75 | 0.0007182 | 2874 | 0.053073 | 8251 | 3.8117e-05 | 6352
EIGHT MILE 2101CB | EIGHT MILE 2101 | 163912101 |  | 5.08 | 0.68345 |  | 86.8333 | 0.0005847 | 4477 | 0.069158 | 5166 | 3.8116e-05 | 6353
DALY CITY 1105CB | DALY CITY 1105 | 22641105 |  | 2.2628 | 1.2566 |  | 46.3333 | 0.00062541 | 3991 | 0.060581 | 6943 | 3.8098e-05 | 6354
SWIFT 2111XR314 | SWIFT 2111 | 83392111 |  | 2.5235 | 1.826 |  | 43.3333 | 0.00071783 | 2878 | 0.053073 | 8250 | 3.8097e-05 | 6355
SF H 1103562348 | SF H 1103 | 22101103 |  | 2.3016 | 1.9622 |  | 46.5 | 0.00071108 | 2961 | 0.053707 | 8027 | 3.8096e-05 | 6356
SAN LUIS OBISPO 1102CB | SAN LUIS OBISPO 1102 | 182631102 |  | 5.485 | 4.5836 |  | 88.8333 | 0.00064124 | 3811 | 0.060364 | 6977 | 3.8095e-05 | 6357
SAN LEANDRO U 1110MR360 | SAN LEANDRO U 1110 | 13111110 |  | 0.83101 | 0.90787 |  | 9.3333 | 0.00071778 | 2880 | 0.053073 | 8250 | 3.8095e-05 | 6358
CLAYTON 2211CB | CLAYTON 2211 | 12022211 |  | 10.5055 | 7.4626 |  | 170.2333 | 0.00071083 | 2966 | 0.053744 | 8017 | 3.8094e-05 | 6359
BERKELEY F 0402502466 | BERKELEY F 0402 | 12060402 | TRUE | 0.53175 | 0.54669 | 0.19637 | 8.8333 | 0.00067214 | 3415 | 0.057204 | 7406 | 3.8087e-05 | 6360
STELLING 1110CB | STELLING 1110 | 83481110 |  | 10.573 | 7.2302 |  | 163.1667 | 0.0006825 | 3301 | 0.056071 | 7569 | 3.8087e-05 | 6361
REDWOOD CITY 0404CB | REDWOOD CITY 0404 | 24160404 |  | 1.6076 | 1.1937 |  | 20.9167 | 0.00071762 | 2882 | 0.053073 | 8251 | 3.8086e-05 | 6362
GLENWOOD 110144610 | GLENWOOD 1101 | 24091101 |  | 2.4786 | 0.71869 |  | 37.3333 | 0.00059514 | 4361 | 0.064557 | 6480 | 3.8084e-05 | 6363
EDES 1111MR647 | EDES 1111 | 13681111 |  | 0.048972 | 0 |  | 0.5 | 0.00071758 | 2884 | 0.053073 | 8251 | 3.8084e-05 | 6364
VALLEJO B 1101CB | VALLEJO B 1101 | 42451101 |  | 4.7734 | 3.5361 |  | 64.3333 | 0.00071747 | 2887 | 0.053073 | 8252 | 3.8078e-05 | 6365
STOCKDALE 21144236 | STOCKDALE 2114 | 254072114 |  | 3.2334 | 3.3497 |  | 53 | 0.00071178 | 2952 | 0.05356 | 8079 | 3.8072e-05 | 6366
TULUCAY 1101613014 | TULUCAY 1101 | 42301101 |  | 0.069975 | 0 |  | 0.5 | 0.00056822 | 4678 | 0.067 | 6057 | 3.8071e-05 | 6367
MOUNTAIN VIEW 110460076 | MOUNTAIN VIEW 1104 | 82031104 |  | 1.3819 | 0.7346 |  | 28.3333 | 0.00071724 | 2889 | 0.053073 | 8251 | 3.8066e-05 | 6368
SAN LEANDRO U 1114501762 | SAN LEANDRO U 1114 | 13111114 | FALSE | 1.5139 | 1.5165 | 0.81622 | 23 | 0.00061921 | 4058 | 0.10077 | 3312 | 3.8061e-05 | 6369
SUISUN 110247992 | SUISUN 1102 | 62131102 |  | 4.5297 | 5.3261 |  | 58.5 | 0.00071124 | 2960 | 0.053886 | 7980 | 3.8058e-05 | 6370
EVERGREEN 2102CB | EVERGREEN 2102 | 82012102 |  | 10.4334 | 8.233 |  | 183 | 0.00069315 | 3176 | 0.054595 | 7827 | 3.805e-05 | 6371
PLAINFIELD 110618162 | PLAINFIELD 1106 | 63441106 |  | 3.8163 | 0.016636 |  | 64.8333 | 0.00051835 | 5191 | 0.074441 | 4493 | 3.8045e-05 | 6372
CASTRO VALLEY 1107MR587 | CASTRO VALLEY 1107 | 14091107 |  | 1.9491 | 1.8106 |  | 33.5 | 0.00064984 | 3709 | 0.059303 | 7110 | 3.8044e-05 | 6373
TARAVAL 0403CB | TARAVAL 0403 | 22500403 |  | 3.4697 | 6.3708 |  | 56.3667 | 0.0007168 | 2890 | 0.053073 | 8251 | 3.8043e-05 | 6374
LOS ALTOS 1107CB | LOS ALTOS 1107 | 82241107 |  | 2.9737 | 0.75051 |  | 55.5 | 0.00068858 | 3239 | 0.055206 | 7722 | 3.8042e-05 | 6375
GRAND ISLAND 2226292892 | GRAND ISLAND 2226 | 62462226 |  | 4.6507 | 1.2815 |  | 91 | 0.00059471 | 4366 | 0.065756 | 6313 | 3.8042e-05 | 6376
EUREKA A 1107CB | EUREKA A 1107 | 192121107 |  | 4.4321 | 2.8031 |  | 65 | 0.0006804 | 3320 | 0.056197 | 7545 | 3.8041e-05 | 6377
REDWOOD CITY 0402CB | REDWOOD CITY 0402 | 24160402 |  | 1.2484 | 1.0384 |  | 22.7 | 0.0007167 | 2892 | 0.053073 | 8251 | 3.8037e-05 | 6378
CAROLANDS 040387173 | CAROLANDS 0403 | 24060403 |  | 3.4487 | 3.1022 |  | 57.25 | 0.00056643 | 4695 | 0.067035 | 5970 | 3.8035e-05 | 6379
SAN LEANDRO U 110810570 | SAN LEANDRO U 1108 | 13111108 |  | 0.65628 | 0.78563 |  | 9.5 | 0.0007166 | 2894 | 0.053073 | 8251 | 3.8032e-05 | 6380
WEST FRESNO 1102829424 | WEST FRESNO 1102 | 253731102 |  | 0.0077498 | 0 |  | 0.83333 | 0.00071659 | 2895 | 0.053073 | 8250 | 3.8032e-05 | 6381
OAKLAND X 1103980100 | OAKLAND X 1103 | 12541103 |  | 0.33892 | 0.14303 |  | 6.8333 | 0.00071655 | 2896 | 0.053073 | 8251 | 3.8029e-05 | 6382
FIGARDEN 2112CB | FIGARDEN 2112 | 254552112 |  | 1.6795 | 0.28662 |  | 20.3333 | 0.00071654 | 2897 | 0.053073 | 8251 | 3.8029e-05 | 6383
MABURY 1104XR274 | MABURY 1104 | 82191104 |  | 3.1879 | 4.9985 |  | 67.3333 | 0.00071443 | 2918 | 0.053176 | 8223 | 3.8003e-05 | 6384
TRIMBLE 1105XR126 | TRIMBLE 1105 | 83801105 |  | 1.3686 | 0.23047 |  | 27.5 | 0.00070781 | 3010 | 0.053957 | 7966 | 3.7991e-05 | 6385
PAUL SWEET 210335240 | PAUL SWEET 2103 | 83252103 |  | 2.7952 | 2.9359 |  | 43.1667 | 0.00070717 | 3014 | 0.054363 | 7875 | 3.7989e-05 | 6386
LAMONT 110390940 | LAMONT 1103 | 253911103 |  | 6.7474 | 4.8867 |  | 95.5 | 0.00068605 | 3265 | 0.057052 | 7429 | 3.7981e-05 | 6387
OAKLAND C 1113CR418 | OAKLAND C 1113 | 12011113 |  | 0.58288 | 0.45807 |  | 13 | 0.00071555 | 2904 | 0.053073 | 8251 | 3.7976e-05 | 6388
CLAYTON 1103CB | CLAYTON 1103 | 12021103 |  | 1.9165 | 1.1735 |  | 28.3667 | 0.00070287 | 3067 | 0.053588 | 8067 | 3.7974e-05 | 6389
OAKLAND J 1103CR436 | OAKLAND J 1103 | 12091103 |  | 0.066475 | 0 |  | 1.5 | 0.00071543 | 2906 | 0.053073 | 8251 | 3.797e-05 | 6390
MOSHER 21115266 | MOSHER 2111 | 163722111 |  | 15.5302 | 5.0852 |  | 253.3333 | 0.00065959 | 3584 | 0.059787 | 7042 | 3.7967e-05 | 6391
LODI 1101CB | LODI 1101 | 162111101 |  | 12.928 | 2.1382 |  | 200.8333 | 0.00057346 | 4608 | 0.068869 | 5213 | 3.7964e-05 | 6392
ASHLAN AVE 1112230054 | ASHLAN AVE 1112 | 252051112 |  | 0.62371 | 0.13086 |  | 10.8333 | 0.0007153 | 2909 | 0.053073 | 8251 | 3.7963e-05 | 6393
MOUNTAIN VIEW 110560056 | MOUNTAIN VIEW 1105 | 82031105 |  | 2.7644 | 1.5384 |  | 42.1667 | 0.00070982 | 2976 | 0.053403 | 8135 | 3.7957e-05 | 6394
SAN MATEO 2101CB | SAN MATEO 2101 | 24192101 |  | 5.3899 | 5.1207 |  | 78 | 0.00066068 | 3569 | 0.058221 | 7265 | 3.7952e-05 | 6395
BERKELEY F 1104BR114 | BERKELEY F 1104 | 12061104 |  | 0.80023 | 1.0489 |  | 12.5833 | 0.00071493 | 2912 | 0.053073 | 8250 | 3.7943e-05 | 6396
DAVIS 1103CB | DAVIS 1103 | 62041103 |  | 5.8468 | 1.8884 |  | 86.0333 | 0.00063545 | 3874 | 0.065531 | 6353 | 3.7932e-05 | 6397
COLUSA 110130272 | COLUSA 1101 | 62021101 |  | 0.66457 | 0.19359 |  | 11.5 | 0.00056125 | 4740 | 0.069996 | 5048 | 3.7927e-05 | 6398
RINCON 110499918 | RINCON 1104 | 43321104 |  | 1.0647 | 0.052551 |  | 19.3333 | 0.00065253 | 3675 | 0.057755 | 7330 | 3.7924e-05 | 6399
GREENBRAE 110498902 | GREENBRAE 1104 | 43091104 |  | 0.64269 | 0.017322 |  | 9 | 0.00071453 | 2916 | 0.053073 | 8251 | 3.7922e-05 | 6400
BELLEVUE 110423772 | BELLEVUE 1104 | 43181104 |  | 0.33398 | 0 |  | 4.5 | 0.00071451 | 2917 | 0.053073 | 8251 | 3.7921e-05 | 6401
SOLEDAD 2105CB | SOLEDAD 2105 | 182052105 |  | 11.4483 | 0.4042 |  | 230.4167 | 0.00056402 | 4717 | 0.067273 | 5750 | 3.7912e-05 | 6402
EL PATIO 1116123364 | EL PATIO 1116 | 82921116 |  | 8.0453 | 8.7431 |  | 115 | 0.00071433 | 2919 | 0.053073 | 8251 | 3.7911e-05 | 6403
SHAFTER 11041419 | SHAFTER 1104 | 253651104 |  | 5.4857 | 1.6456 |  | 96.3333 | 0.00062826 | 3966 | 0.063979 | 6547 | 3.7905e-05 | 6404
DALY CITY 110212767 | DALY CITY 1102 | 22641102 |  | 2.8156 | 2.9463 |  | 45.8333 | 0.00069359 | 3174 | 0.054842 | 7784 | 3.79e-05 | 6405
FORT ORD 21069138 | FORT ORD 2106 | 182402106 |  | 6.8563 | 3.1947 |  | 105.6667 | 0.0005692 | 4671 | 0.066426 | 6201 | 3.7895e-05 | 6406
MILLBRAE 1104CB | MILLBRAE 1104 | 22691104 |  | 1.7297 | 1.5905 |  | 26.9167 | 0.00068508 | 3274 | 0.053637 | 8051 | 3.7887e-05 | 6407
OAKLAND X 1109CB | OAKLAND X 1109 | 12541109 |  | 5.2247 | 4.5802 |  | 67 | 0.00071047 | 2970 | 0.05335 | 8154 | 3.7881e-05 | 6408
EL PATIO 1107XR528 | EL PATIO 1107 | 82921107 |  | 3.9032 | 3.4666 |  | 57 | 0.00071362 | 2928 | 0.053073 | 8251 | 3.7874e-05 | 6409
WASCO 1104CB | WASCO 1104 | 252961104 |  | 5.2066 | 4.7599 |  | 78.1667 | 0.00070897 | 2994 | 0.053552 | 8085 | 3.7868e-05 | 6410
BRITTON 1110CB | BRITTON 1110 | 83611110 |  | 2.1121 | 0.48625 |  | 21.6667 | 0.00071349 | 2930 | 0.053073 | 8251 | 3.7867e-05 | 6411
GREENBRAE 11041302 | GREENBRAE 1104 | 43091104 |  | 5.8272 | 1.7128 |  | 104 | 0.00056643 | 4696 | 0.06684 | 6111 | 3.7865e-05 | 6412
EL PATIO 111896416 | EL PATIO 1118 | 82921118 |  | 3.6943 | 4.5502 |  | 49.8333 | 0.00071341 | 2931 | 0.053073 | 8251 | 3.7863e-05 | 6413
LLAGAS 2103XR006 | LLAGAS 2103 | 83182103 |  | 0.072941 | 0.071225 |  | 1.5 | 0.000565 | 4706 | 0.067 | 6057 | 3.7855e-05 | 6414
LARKIN (Y) 113511309 | LARKIN (Y) 1135 | 22801135 |  | 0.73734 | 0.87356 |  | 12.9167 | 0.00071323 | 2932 | 0.053073 | 8252 | 3.7853e-05 | 6415
BERKELEY F 1105BR106 | BERKELEY F 1105 | 12061105 |  | 0.61305 | 0.70359 |  | 13 | 0.00069813 | 3128 | 0.054149 | 7912 | 3.7853e-05 | 6416
OAKLAND C 1108CB | OAKLAND C 1108 | 12011108 |  | 2.0366 | 1.9598 |  | 27 | 0.0007132 | 2933 | 0.053073 | 8251 | 3.7851e-05 | 6417
ASHLAN AVE 1109R1650 | ASHLAN AVE 1109 | 252051109 |  | 1.5096 | 0.84762 |  | 28.5 | 0.00066105 | 3562 | 0.058194 | 7269 | 3.7848e-05 | 6418
PETALUMA C 11024086 | PETALUMA C 1102 | 42631102 |  | 0.34716 | 0 |  | 6.5 | 0.00071309 | 2934 | 0.053073 | 8251 | 3.7846e-05 | 6419
BERKELEY F 0406CB | BERKELEY F 0406 | 12060406 |  | 3.794 | 4.0308 |  | 41.1667 | 0.00071307 | 2935 | 0.053073 | 8251 | 3.7844e-05 | 6420
COTTONWOOD 1102CB | COTTONWOOD 1102 | 102931102 |  | 6.8752 | 1.9486 |  | 106.6667 | 0.00057247 | 4622 | 0.066077 | 6252 | 3.7842e-05 | 6421
PARLIER 110242210 | PARLIER 1102 | 252291102 |  | 0.015352 | 0 |  | 0.75 | 0.00071274 | 2940 | 0.053073 | 8251 | 3.7827e-05 | 6422
HATTON 110256680 | HATTON 1102 | 182291102 |  | 0.036523 | 0 |  | 0.5 | 0.00056455 | 4712 | 0.067 | 6057 | 3.7825e-05 | 6423
BARTON 1105R1080 | BARTON 1105 | 253571105 |  | 1.5327 | 0.76575 |  | 32.8333 | 0.00071262 | 2941 | 0.053073 | 8252 | 3.782e-05 | 6424
LAS POSITAS 2108CB | LAS POSITAS 2108 | 14402108 |  | 2.1246 | 0.19635 |  | 26.3333 | 0.00056428 | 4715 | 0.067021 | 6001 | 3.7816e-05 | 6425
OREGON TRAIL 11043310 | OREGON TRAIL 1104 | 103521104 |  | 3.4291 | 0.099008 |  | 58.5 | 0.00058588 | 4467 | 0.064933 | 6447 | 3.7815e-05 | 6426
WILLOWS A 11032262 | WILLOWS A 1103 | 102741103 |  | 7.1089 | 4.3718 |  | 119.5 | 0.00063103 | 3928 | 0.060487 | 6959 | 3.7811e-05 | 6427
PUEBLO 1102CB | PUEBLO 1102 | 43291102 |  | 6.3189 | 0.72959 |  | 122.1667 | 0.00055981 | 4758 | 0.068157 | 5366 | 3.7797e-05 | 6428
PACIFICA 110110067 | PACIFICA 1101 | 22811101 |  | 1.2313 | 0.84618 |  | 21.8333 | 0.00062795 | 3972 | 0.059983 | 7019 | 3.7797e-05 | 6429
PENRYN 1106CB | PENRYN 1106 | 152561106 |  | 12.2113 | 3.5754 |  | 217.75 | 0.00058179 | 4502 | 0.065744 | 6317 | 3.7792e-05 | 6430
FRANKLIN 1101P134 | FRANKLIN 1101 | 13921101 |  | 2.6719 | 2.9404 |  | 41 | 0.00069436 | 3163 | 0.054602 | 7824 | 3.7791e-05 | 6431
SF K 0409CB | SF K 0409 | 22130409 |  | 2.385 | 3.0052 |  | 35.0833 | 0.00071206 | 2946 | 0.053073 | 8253 | 3.7791e-05 | 6432
OAKLAND D 1110CR158 | OAKLAND D 1110 | 12041110 |  | 0.32724 | 0.28588 |  | 4.5 | 0.00071197 | 2947 | 0.053073 | 8251 | 3.7786e-05 | 6433
GREEN VALLEY 210449146 | GREEN VALLEY 2104 | 83192104 |  | 2.4964 | 2.1205 |  | 33.5833 | 0.00071196 | 2948 | 0.053073 | 8252 | 3.7786e-05 | 6434
MISSION (X) 1110CB | MISSION (X) 1110 | 22011110 |  | 0.34158 | 0.52801 |  | 5.6667 | 0.0007119 | 2949 | 0.053073 | 8250 | 3.7782e-05 | 6435
WEST LANE 11028457 | WEST LANE 1102 | 163621102 |  | 1.4452 | 1.3005 |  | 24 | 0.00071184 | 2950 | 0.053073 | 8251 | 3.7779e-05 | 6436
ALMADEN 110211827 | ALMADEN 1102 | 82311102 |  | 1.154 | 1.341 |  | 16 | 0.00071178 | 2953 | 0.053073 | 8251 | 3.7776e-05 | 6437
IGNACIO 1105784032 | IGNACIO 1105 | 42481105 | FALSE | 0.62702 | 0.62195 | 0.96625 | 9.5 | 0.00071547 | 2905 | 0.053073 | 8251 | 3.7775e-05 | 6438
LAS POSITAS 2104MR188 | LAS POSITAS 2104 | 14402104 |  | 9.6472 | 10.6901 |  | 143.5 | 0.00070912 | 2989 | 0.053315 | 8170 | 3.7762e-05 | 6439
PENNGROVE 1101554 | PENNGROVE 1101 | 43471101 |  | 13.2708 | 3.7269 |  | 231 | 0.0002645 | 8760 | 0.14966 | 3207 | 3.7761e-05 | 6440
HURON 1107CB | HURON 1107 | 253161107 |  | 0.28469 | 0 |  | 1.6667 | 0.00048784 | 5519 | 0.0774 | 3396 | 3.7759e-05 | 6441
SF L 0407CB | SF L 0407 | 22260407 |  | 0.5456 | 0.11534 |  | 12.5 | 0.00071108 | 2962 | 0.053073 | 8251 | 3.7739e-05 | 6442
WOLFE 1106LV18 | WOLFE 1106 | 83671106 |  | 6.3975 | 6.4582 |  | 97 | 0.00071106 | 2963 | 0.053073 | 8251 | 3.7738e-05 | 6443
MONROE 1105588 | MONROE 1105 | 43301105 |  | 1.3055 | 0.27116 |  | 21 | 0.00063264 | 3907 | 0.059705 | 7056 | 3.7737e-05 | 6444
VIERRA 170114306 | VIERRA 1701 | 162701701 |  | 1.6578 | 0.65122 |  | 32.5 | 0.00070857 | 2999 | 0.053337 | 8163 | 3.773e-05 | 6445
MADERA 1112CB | MADERA 1112 | 252761112 |  | 11.4679 | 0.90845 |  | 188.1667 | 0.00050627 | 5327 | 0.074783 | 4446 | 3.7727e-05 | 6446
MC CALL 110738694 | MC CALL 1107 | 254121107 |  | 0.014512 | 0 |  | 0.5 | 0.00048741 | 5526 | 0.0774 | 3397 | 3.7725e-05 | 6447
MT EDEN 1109CB | MT EDEN 1109 | 13761109 |  | 2.3224 | 2.2133 |  | 31.75 | 0.00071071 | 2967 | 0.053073 | 8251 | 3.7719e-05 | 6448
LOS OSITOS 21017594 | LOS OSITOS 2101 | 182082101 |  | 1.8832 | 0.96121 |  | 43 | 0.00064073 | 3815 | 0.05833 | 7243 | 3.7711e-05 | 6449
EL CERRITO G 1103CB | EL CERRITO G 1103 | 12501103 |  | 6.7599 | 5.2473 |  | 87.45 | 0.00070472 | 3044 | 0.05357 | 8075 | 3.7709e-05 | 6450
NOVATO 1102CB | NOVATO 1102 | 42211102 |  | 0.58673 | 0.29791 |  | 8.5 | 0.00071052 | 2969 | 0.053073 | 8251 | 3.7709e-05 | 6451
MONROE 1106CB | MONROE 1106 | 43301106 |  | 2.7654 | 0.99188 |  | 53.6667 | 0.00065511 | 3639 | 0.05724 | 7400 | 3.7706e-05 | 6452
LOS ALTOS 1104LM16 | LOS ALTOS 1104 | 82241104 |  | 6.3278 | 3.8487 |  | 101.3333 | 0.00060187 | 4277 | 0.063152 | 6650 | 3.7684e-05 | 6453
SAN JOSE A 0410CB | SAN JOSE A 0410 | 82250410 |  | 4.6851 | 4.9966 |  | 82.5 | 0.00070975 | 2977 | 0.053073 | 8251 | 3.7668e-05 | 6454
SF E 11076273 | SF E 1107 | 22071107 |  | 0.53057 | 0.81609 |  | 9.25 | 0.00070959 | 2982 | 0.053073 | 8251 | 3.766e-05 | 6455
MT EDEN 1103CB | MT EDEN 1103 | 13761103 |  | 6.7859 | 7.0504 |  | 99.95 | 0.00070935 | 2984 | 0.053073 | 8250 | 3.7647e-05 | 6456
BERKELEY F 0407CB | BERKELEY F 0407 | 12060407 |  | 0.0054018 | 0 |  | 0.5 | 0.00070917 | 2987 | 0.053073 | 8251 | 3.7638e-05 | 6457
WEBER 1114CB | WEBER 1114 | 163481114 |  | 7.3182 | 3.5943 |  | 122.75 | 0.00068596 | 3269 | 0.055798 | 7616 | 3.7629e-05 | 6458
MONROE 1105CB | MONROE 1105 | 43301105 |  | 6.5832 | 2.1021 |  | 118.1667 | 0.00066538 | 3493 | 0.057518 | 7359 | 3.7625e-05 | 6459
EL PATIO 1112XR588 | EL PATIO 1112 | 82921112 |  | 6.0393 | 6.3263 |  | 92.3333 | 0.00070887 | 2996 | 0.053073 | 8251 | 3.7621e-05 | 6460
SANTA ROSA A 111199050 | SANTA ROSA A 1111 | 42151111 |  | 4.749 | 3.0648 |  | 78.5 | 0.00068078 | 3316 | 0.056642 | 7481 | 3.7621e-05 | 6461
TULUCAY 1101CB | TULUCAY 1101 | 42301101 |  | 5.7264 | 0.26456 |  | 104 | 0.00056813 | 4679 | 0.066551 | 6178 | 3.7619e-05 | 6462
EVERGREEN 2103XR566 | EVERGREEN 2103 | 82012103 |  | 0.58873 | 0.0051749 |  | 11 | 0.00061757 | 4078 | 0.060036 | 7014 | 3.7616e-05 | 6463
VALLEJO B 1102CB | VALLEJO B 1102 | 42451102 |  | 2.4871 | 1.5107 |  | 24.6167 | 0.00070865 | 2997 | 0.053073 | 8249 | 3.761e-05 | 6464
LIVERMORE 1103MR286 | LIVERMORE 1103 | 12141103 |  | 3.8894 | 2.9128 |  | 56.1667 | 0.00068125 | 3313 | 0.055923 | 7589 | 3.7599e-05 | 6465
SF H 0405CB | SF H 0405 | 22100405 |  | 2.4616 | 2.1599 |  | 27.5833 | 0.00069849 | 3122 | 0.053964 | 7964 | 3.7593e-05 | 6466
SARATOGA 1111XR134 | SARATOGA 1111 | 83371111 |  | 2.8104 | 3.6208 |  | 34.6667 | 0.00070816 | 3004 | 0.053073 | 8250 | 3.7584e-05 | 6467
GATES 1108CB | GATES 1108 | 253931108 |  | 2.575 | 0 |  | 18.9167 | 0.00050293 | 5359 | 0.075622 | 4306 | 3.7583e-05 | 6468
OAKLAND C 1116CR442 | OAKLAND C 1116 | 12011116 |  | 0.3798 | 0.19844 |  | 8 | 0.0007081 | 3005 | 0.053073 | 8251 | 3.7581e-05 | 6469
VIEJO 22049440 | VIEJO 2204 | 182852204 | TRUE | 3.4238 | 3.9658 | 0.00057819 | 66.5 | 0.00064919 | 3717 | 0.058234 | 7262 | 3.7578e-05 | 6470
CORCORAN 1106258236 | CORCORAN 1106 | 252171106 |  | 0.22462 | 0 |  | 4 | 0.00061508 | 4105 | 0.06149 | 6833 | 3.7578e-05 | 6471
BAHIA 1102946 | BAHIA 1102 | 43251102 |  | 1.0985 | 0.012716 |  | 23 | 0.00055756 | 4787 | 0.067455 | 5634 | 3.7571e-05 | 6472
BERKELEY T 0402CB | BERKELEY T 0402 | 12660402 |  | 4.6739 | 4.802 |  | 58.6667 | 0.00070782 | 3009 | 0.053073 | 8253 | 3.7566e-05 | 6473
GRAND ISLAND 222747742 | GRAND ISLAND 2227 | 62462227 |  | 1.2972 | 0.039474 |  | 13.9167 | 0.00048814 | 5512 | 0.076817 | 3879 | 3.7563e-05 | 6474
CASTROVILLE 21033710 | CASTROVILLE 2103 | 182352103 |  | 5.1567 | 0.14534 |  | 101.5 | 0.00056933 | 4669 | 0.066794 | 6122 | 3.7562e-05 | 6475
ATWATER 1102CB | ATWATER 1102 | 253611102 |  | 3.5894 | 0.2697 |  | 53.6667 | 0.00051674 | 5208 | 0.073036 | 4659 | 3.756e-05 | 6476
WYANDOTTE 110613016 | WYANDOTTE 1106 | 102911106 |  | 3.3178 | 1.0581 |  | 50.8333 | 0.00062135 | 4034 | 0.06184 | 6783 | 3.7553e-05 | 6477
CORCORAN 1116497218 | CORCORAN 1116 | 252171116 |  | 0.031835 | 0 |  | 1 | 0.00048518 | 5547 | 0.0774 | 3397 | 3.7553e-05 | 6478
HURON 1106CB | HURON 1106 | 253161106 |  | 2.5324 | 0 |  | 32.25 | 0.00048802 | 5514 | 0.076912 | 3820 | 3.7552e-05 | 6479
CASTROVILLE 2103CB | CASTROVILLE 2103 | 182352103 |  | 7.9992 | 5.2961 |  | 130.1667 | 0.00062721 | 3982 | 0.060098 | 7006 | 3.7541e-05 | 6480
WOODWARD 2104CB | WOODWARD 2104 | 255292104 |  | 2.7632 | 0.114 |  | 57 | 0.00057591 | 4579 | 0.06722 | 5791 | 3.7538e-05 | 6481
HIGHWAY 1103CB | HIGHWAY 1103 | 42651103 |  | 6.2998 | 3.0932 |  | 95 | 0.0006735 | 3394 | 0.055635 | 7651 | 3.7538e-05 | 6482
FRANKLIN 1102CB | FRANKLIN 1102 | 13921102 |  | 0.96082 | 0 |  | 15.5833 | 0.00056021 | 4753 | 0.067 | 6058 | 3.7534e-05 | 6483
GALLO 1101CB | GALLO 1101 | 254901101 |  | 0.7241 | 0.036585 |  | 12 | 0.00048494 | 5549 | 0.0774 | 3397 | 3.7534e-05 | 6484
EL PATIO 1119XR124 | EL PATIO 1119 | 82921119 |  | 5.8933 | 5.4588 |  | 89.8333 | 0.00070706 | 3016 | 0.053073 | 8251 | 3.7526e-05 | 6485
SAN RAFAEL 1107328 | SAN RAFAEL 1107 | 42011107 |  | 0.026543 | 0 |  | 1.5 | 0.00070669 | 3019 | 0.053073 | 8251 | 3.7506e-05 | 6486
PAUL SWEET 210980246 | PAUL SWEET 2109 | 83252109 |  | 3.558 | 3.0388 |  | 57.1667 | 0.00064 | 3825 | 0.059405 | 7096 | 3.7506e-05 | 6487
COALINGA NO 1 11089850 | COALINGA NO 1 1108 | 252161108 |  | 3.8792 | 3.8715 |  | 61 | 0.00067219 | 3414 | 0.056325 | 7526 | 3.7503e-05 | 6488
JARVIS 1109CB | JARVIS 1109 | 13501109 |  | 4.1121 | 1.635 |  | 68.5 | 0.00070473 | 3043 | 0.053174 | 8225 | 3.7499e-05 | 6489
JANES CREEK 11044844 | JANES CREEK 1104 | 192391104 |  | 0.28245 | 0.021836 |  | 3 | 0.00055961 | 4761 | 0.067 | 6057 | 3.7494e-05 | 6490
EAST GRAND 110175693 | EAST GRAND 1101 | 22571101 |  | 1.1487 | 0.65028 |  | 12.6667 | 0.00070636 | 3025 | 0.053073 | 8252 | 3.7488e-05 | 6491
NARROWS 210242584 | NARROWS 2102 | 153132102 |  | 4.5759 | 0.18537 |  | 84.5 | 0.00054988 | 4863 | 0.068243 | 5350 | 3.748e-05 | 6492
OAKLAND C 1118CB | OAKLAND C 1118 | 12011118 |  | 3.3206 | 0.75035 |  | 51.6667 | 0.0006785 | 3339 | 0.056641 | 7482 | 3.7478e-05 | 6493
SAN LORENZO 0401CB | SAN LORENZO 0401 | 13460401 |  | 4.3666 | 4.3789 |  | 56.5 | 0.00070612 | 3027 | 0.053073 | 8252 | 3.7476e-05 | 6494
RIVERBANK 171338756 | RIVERBANK 1713 | 163191713 |  | 7.7834 | 2.7451 |  | 130 | 0.00060825 | 4188 | 0.065556 | 6348 | 3.7475e-05 | 6495
MT EDEN 1109MR237 | MT EDEN 1109 | 13761109 |  | 1.9482 | 0.97135 |  | 33 | 0.00070605 | 3028 | 0.053073 | 8251 | 3.7472e-05 | 6496
BOGUE 1105CB | BOGUE 1105 | 153781105 |  | 10.459 | 3.1474 |  | 164.3667 | 0.00064345 | 3782 | 0.05926 | 7121 | 3.7465e-05 | 6497
CORCORAN 1117CB | CORCORAN 1117 | 252171117 |  | 0.5394 | 0 |  | 5.1167 | 0.00049087 | 5488 | 0.076449 | 4034 | 3.7462e-05 | 6498
DALY CITY 1107CB | DALY CITY 1107 | 22641107 |  | 5.3037 | 6.3674 |  | 81.9167 | 0.00070568 | 3031 | 0.053073 | 8251 | 3.7452e-05 | 6499
SF J 1108CB | SF J 1108 | 22221108 |  | 0.0018939 | 0 |  | 1 | 0.00070564 | 3033 | 0.053073 | 8251 | 3.745e-05 | 6500
OAKLAND D 1110CR152 | OAKLAND D 1110 | 12041110 |  | 1.8572 | 2.574 |  | 32.3333 | 0.0007055 | 3036 | 0.053073 | 8252 | 3.7443e-05 | 6501
EL PATIO 111860108 | EL PATIO 1118 | 82921118 |  | 6.0261 | 6.5388 |  | 70.1667 | 0.00070547 | 3038 | 0.053073 | 8252 | 3.7441e-05 | 6502
NAPA 1102710 | NAPA 1102 | 42021102 |  | 8.2813 | 6.6656 |  | 123.6667 | 0.0006923 | 3187 | 0.054792 | 7790 | 3.7433e-05 | 6503
AVENA 1701CUS267772 | AVENA 1701 | 163571701 |  | 0.0094697 | 0 |  | 0.5 | 0.00048351 | 5565 | 0.0774 | 3397 | 3.7424e-05 | 6504
BELLE HAVEN 11018990 | BELLE HAVEN 1101 | 24021101 |  | 0.52235 | 0 |  | 6.25 | 0.00066352 | 3520 | 0.055858 | 7602 | 3.7421e-05 | 6505
OLD RIVER 110556702 | OLD RIVER 1105 | 252821105 |  | 3.6919 | 0 |  | 48.6667 | 0.00049024 | 5491 | 0.0764 | 4055 | 3.742e-05 | 6506
LOYOLA 1102LL86 | LOYOLA 1102 | 82161102 |  | 4.8815 | 1.3522 |  | 90 | 0.00054952 | 4868 | 0.067892 | 5441 | 3.7418e-05 | 6507
SF M 0406CB | SF M 0406 | 22270406 |  | 2.9077 | 4.1173 |  | 49.0833 | 0.00070469 | 3045 | 0.053073 | 8252 | 3.74e-05 | 6508
MT EDEN 1107MR608 | MT EDEN 1107 | 13761107 |  | 1.0201 | 0.72729 |  | 18.5 | 0.00070464 | 3047 | 0.053073 | 8251 | 3.7397e-05 | 6509
DIXON 1106CB | DIXON 1106 | 62061106 |  | 2.5463 | 0.56917 |  | 40.1667 | 0.0005611 | 4743 | 0.069551 | 5113 | 3.7387e-05 | 6510
MISSION (X) 1116CB | MISSION (X) 1116 | 22011116 |  | 0.22984 | 0.29016 |  | 5.25 | 0.00070408 | 3052 | 0.053073 | 8251 | 3.7368e-05 | 6511
FREMONT 11041516 | FREMONT 1104 | 14351104 |  | 0.0077932 | 0 |  | 0.5 | 0.0007039 | 3056 | 0.053073 | 8251 | 3.7358e-05 | 6512
HICKS 1114XR182 | HICKS 1114 | 83431114 |  | 5.5623 | 5.4025 |  | 85.1667 | 0.00070331 | 3063 | 0.053174 | 8226 | 3.7355e-05 | 6513
DUNBAR 1101137736 | DUNBAR 1101 | 43071101 |  | 7.2554 | 3.6755 |  | 140.5 | 0.00056945 | 4665 | 0.065316 | 6390 | 3.7352e-05 | 6514
DIXON LANDING 2103XR016 | DIXON LANDING 2103 | 14722103 |  | 1.6401 | 0 |  | 31 | 0.00056331 | 4724 | 0.066551 | 6177 | 3.7348e-05 | 6515
STOREY 110838522 | STOREY 1108 | 254611108 |  | 0.3619 | 0 |  | 4.5 | 0.00048248 | 5574 | 0.0774 | 3397 | 3.7344e-05 | 6516
SILVERADO 2103315138 | SILVERADO 2103 | 43432103 |  | 1.512 | 0.72232 |  | 35.5 | 0.00054559 | 4902 | 0.068569 | 5268 | 3.7344e-05 | 6517
RIDGE 0402CB | RIDGE 0402 | 12840402 | FALSE | 2.4125 | 2.7246 | 3.8189 | 32.4167 | 0.00057062 | 4653 | 0.065891 | 6294 | 3.7343e-05 | 6518
SAN JOSE A 111243227 | SAN JOSE A 1112 | 82251112 |  | 1.0069 | 0.9732 |  | 16.5 | 0.00070361 | 3057 | 0.053073 | 8251 | 3.7342e-05 | 6519
MC CALL 110538010 | MC CALL 1105 | 254121105 |  | 7.2715 | 5.2155 |  | 119.3333 | 0.00066515 | 3496 | 0.057935 | 7302 | 3.7334e-05 | 6520
ATWATER 110411880 | ATWATER 1104 | 253611104 |  | 0.13133 | 0.053972 |  | 3 | 0.0007034 | 3060 | 0.053073 | 8251 | 3.7332e-05 | 6521
WEBER 111079480 | WEBER 1110 | 163481110 |  | 0.3151 | 0 |  | 4.75 | 0.00055571 | 4807 | 0.067157 | 5846 | 3.7319e-05 | 6522
WOLFE 1113CB | WOLFE 1113 | 83671113 |  | 11.8055 | 10.5435 |  | 179.1667 | 0.00070295 | 3066 | 0.053073 | 8251 | 3.7307e-05 | 6523
GLENWOOD 0404CB | GLENWOOD 0404 | 24090404 |  | 6.048 | 3.7433 |  | 110.5 | 0.00057617 | 4574 | 0.064983 | 6436 | 3.7298e-05 | 6524
CLOVERDALE 1102CB | CLOVERDALE 1102 | 42821102 |  | 2.7384 | 1.0153 |  | 50 | 0.00048994 | 5496 | 0.07864 | 3390 | 3.7295e-05 | 6525
SALINAS 110368200 | SALINAS 1103 | 182011103 |  | 5.2869 | 5.8036 |  | 83.6667 | 0.00070268 | 3069 | 0.053073 | 8251 | 3.7293e-05 | 6526
SWIFT 2110XR092 | SWIFT 2110 | 83392110 |  | 1.9653 | 1.0362 |  | 42.1667 | 0.00070036 | 3094 | 0.053403 | 8135 | 3.729e-05 | 6527
BELLE HAVEN 0408CB | BELLE HAVEN 0408 | 24020408 |  | 5.2552 | 4.293 |  | 68.5833 | 0.00068012 | 3322 | 0.055357 | 7695 | 3.728e-05 | 6528
SALINAS 1107CB | SALINAS 1107 | 182011107 |  | 3.3137 | 1.4102 |  | 60.4167 | 0.00070233 | 3072 | 0.053073 | 8252 | 3.7275e-05 | 6529
EVERGREEN 210213943 | EVERGREEN 2102 | 82012102 |  | 0.32085 | 0.53196 |  | 6.3333 | 0.00070226 | 3074 | 0.053073 | 8251 | 3.7271e-05 | 6530
BAY MEADOWS 11049072 | BAY MEADOWS 1104 | 24011104 |  | 3.1329 | 2.8071 |  | 43.5 | 0.00069759 | 3138 | 0.053393 | 8141 | 3.727e-05 | 6531
BAY MEADOWS 1103CB | BAY MEADOWS 1103 | 24011103 |  | 3.8999 | 2.8183 |  | 45.3333 | 0.00069892 | 3112 | 0.053252 | 8196 | 3.7264e-05 | 6532
MOUNTAIN VIEW 1102LM80 | MOUNTAIN VIEW 1102 | 82031102 |  | 1.6342 | 1.3165 |  | 27.3333 | 0.00070206 | 3076 | 0.053073 | 8251 | 3.726e-05 | 6533
MADERA 110449760 | MADERA 1104 | 252761104 |  | 7.0875 | 4.3064 |  | 111.8333 | 0.00069784 | 3133 | 0.053514 | 8094 | 3.7254e-05 | 6534
LAKEWOOD 1104W528R | LAKEWOOD 1104 | 13531104 |  | 0.024461 | 0 |  | 0.5 | 0.00055562 | 4809 | 0.067035 | 5975 | 3.7246e-05 | 6535
WHISMAN 1105CB | WHISMAN 1105 | 83631105 |  | 0.96503 | 0.068065 |  | 20.5 | 0.00070172 | 3079 | 0.053073 | 8251 | 3.7242e-05 | 6536
CORNING 110437508 | CORNING 1104 | 103331104 |  | 0.23884 | 0.026015 |  | 3 | 0.00052469 | 5131 | 0.070542 | 4950 | 3.7232e-05 | 6537
OAKLAND J 1108CR276 | OAKLAND J 1108 | 12091108 |  | 5.9517 | 6.3255 |  | 85.6667 | 0.00070146 | 3081 | 0.053073 | 8251 | 3.7229e-05 | 6538
SAN CARLOS 1103313472 | SAN CARLOS 1103 | 24181103 | TRUE | 0.73536 | 0.74333 | 0.11176 | 11.8333 | 0.00061558 | 4100 | 0.0619 | 6775 | 3.7227e-05 | 6539
COTTLE 17049160 | COTTLE 1704 | 163711704 |  | 2.2154 | 1.0167 |  | 29.6667 | 0.00070121 | 3082 | 0.053073 | 8251 | 3.7215e-05 | 6540
SF H 110839004 | SF H 1108 | 22101108 |  | 1.4532 | 0.4515 |  | 17 | 0.0007011 | 3083 | 0.053073 | 8251 | 3.7209e-05 | 6541
EDES 1103CR112 | EDES 1103 | 13681103 |  | 2.9397 | 3.2243 |  | 44.3333 | 0.00070109 | 3084 | 0.053073 | 8250 | 3.7209e-05 | 6542
OAKLAND X 1102CR118 | OAKLAND X 1102 | 12541102 |  | 1.4351 | 1.6778 |  | 19.8333 | 0.000701 | 3085 | 0.053073 | 8251 | 3.7204e-05 | 6543
LOS ALTOS 110660028 | LOS ALTOS 1106 | 82241106 |  | 3.276 | 2.5735 |  | 54 | 0.00067473 | 3375 | 0.054749 | 7797 | 3.7193e-05 | 6544
LAMONT 11064094 | LAMONT 1106 | 253911106 |  | 12.0813 | 6.2058 |  | 192.5 | 0.00062824 | 3967 | 0.061414 | 6840 | 3.719e-05 | 6545
CABRILLO 1103CB | CABRILLO 1103 | 183101103 | TRUE | 4.3798 | 0.25525 | 0.45032 | 80.3333 | 0.00032478 | 7543 | 0.21555 | 3124 | 3.7189e-05 | 6546
SOLEDAD 210246928 | SOLEDAD 2102 | 182052102 |  | 0.027942 | 0 |  | 0.5 | 0.00055497 | 4820 | 0.067 | 6057 | 3.7183e-05 | 6547
COLUSA 110167052 | COLUSA 1101 | 62021101 |  | 1.1383 | 0.96979 |  | 18 | 0.00070048 | 3092 | 0.053073 | 8251 | 3.7176e-05 | 6548
SF E 0405CB | SF E 0405 | 22070405 |  | 2.2038 | 1.9903 |  | 28.25 | 0.00070034 | 3095 | 0.053073 | 8250 | 3.7169e-05 | 6549
SAN CARLOS 11028932 | SAN CARLOS 1102 | 24181102 |  | 0.046297 | 0 |  | 1.5 | 0.0007 | 3098 | 0.053073 | 8251 | 3.7151e-05 | 6550
WYANDOTTE 11101954 | WYANDOTTE 1110 | 102911110 |  | 7.167 | 2.6484 |  | 125 | 0.00055767 | 4785 | 0.06687 | 6104 | 3.7151e-05 | 6551
RADUM 1101CB | RADUM 1101 | 13151101 |  | 1.6247 | 0.52241 |  | 28.8333 | 0.00069593 | 3150 | 0.053314 | 8171 | 3.7144e-05 | 6552
SWIFT 2106XR058 | SWIFT 2106 | 83392106 |  | 3.3336 | 2.8169 |  | 43.3333 | 0.00069985 | 3100 | 0.053073 | 8251 | 3.7143e-05 | 6553
CASTRO VALLEY 1102CB | CASTRO VALLEY 1102 | 14091102 |  | 7.2593 | 6.6584 |  | 131.3333 | 0.00063151 | 3923 | 0.058899 | 7169 | 3.7143e-05 | 6554
GREENBRAE 110182270 | GREENBRAE 1101 | 43091101 |  | 0.77975 | 0.50259 |  | 14.5 | 0.00066545 | 3490 | 0.054994 | 7753 | 3.7138e-05 | 6555
OAKLAND X 0401CB | OAKLAND X 0401 | 12540401 |  | 5.5541 | 4.7446 |  | 60.25 | 0.00069739 | 3142 | 0.053265 | 8191 | 3.7137e-05 | 6556
PUEBLO 21033020 | PUEBLO 2103 | 43292103 |  | 1.9138 | 0.24126 |  | 36 | 0.00058905 | 4426 | 0.065073 | 6421 | 3.7132e-05 | 6557
CANAL 1105872392 | CANAL 1105 | 252091105 |  | 0.82439 | 0.83446 |  | 19 | 0.00069943 | 3105 | 0.053073 | 8251 | 3.7121e-05 | 6558
MC CALL 1104CB | MC CALL 1104 | 254121104 |  | 16.6159 | 9.5108 |  | 279.2833 | 0.00063404 | 3891 | 0.061937 | 6769 | 3.7115e-05 | 6559
SAN RAMON 2107MR287 | SAN RAMON 2107 | 14232107 |  | 3.0348 | 2.9135 |  | 46.8333 | 0.00063399 | 3892 | 0.059073 | 7147 | 3.7114e-05 | 6560
LOS ALTOS 1105CB | LOS ALTOS 1105 | 82241105 |  | 1.8056 | 0.70808 |  | 30 | 0.0006993 | 3108 | 0.053073 | 8251 | 3.7114e-05 | 6561
RICHMOND R 1126BR276 | RICHMOND R 1126 | 13471126 |  | 1.4687 | 0.34839 |  | 26.5 | 0.00064916 | 3718 | 0.058328 | 7244 | 3.7109e-05 | 6562
JARVIS 1108MR367 | JARVIS 1108 | 13501108 |  | 1.7193 | 2.0319 |  | 22 | 0.00069919 | 3110 | 0.053073 | 8251 | 3.7108e-05 | 6563
CORRAL 1103CB | CORRAL 1103 | 162991103 |  | 24.7656 | 4.5107 |  | 469.3333 | 0.0002232 | 9639 | 0.18586 | 3168 | 3.7104e-05 | 6564
NORTH TOWER 1108993638 | NORTH TOWER 1108 | 42041108 |  | 9.1186 | 8.8772 |  | 142.6667 | 0.00067771 | 3345 | 0.054884 | 7771 | 3.7103e-05 | 6565
PANAMA 21014678 | PANAMA 2101 | 253422101 |  | 2.6123 | 0.088286 |  | 38 | 0.00059957 | 4299 | 0.062262 | 6738 | 3.7097e-05 | 6566
SAN BRUNO 040139086 | SAN BRUNO 0401 | 22700401 |  | 1.6432 | 1.8751 |  | 24 | 0.00069891 | 3113 | 0.053073 | 8251 | 3.7093e-05 | 6567
HARRIS 1108CB | HARRIS 1108 | 192431108 |  | 4.6805 | 3.4441 |  | 84.3333 | 0.00063 | 3944 | 0.059447 | 7090 | 3.7087e-05 | 6568
PACIFICA 1103398620 | PACIFICA 1103 | 22811103 | FALSE | 0.48825 | 0.37283 | 0.75448 | 3 | 0.00053078 | 5063 | 0.053073 | 8251 | 3.7085e-05 | 6569
ARANA 0402CB | ARANA 0402 | 83010402 |  | 2.9789 | 1.7285 |  | 48.1667 | 0.00064773 | 3733 | 0.057409 | 7372 | 3.7082e-05 | 6570
SARATOGA 110860088 | SARATOGA 1108 | 83371108 |  | 6.4054 | 6.1866 |  | 96 | 0.00069851 | 3121 | 0.053073 | 8251 | 3.7072e-05 | 6571
WYANDOTTE 110931758 | WYANDOTTE 1109 | 102911109 |  | 5.0984 | 2.2612 |  | 81 | 0.00057884 | 4540 | 0.06504 | 6427 | 3.7071e-05 | 6572
RICHMOND R 1129CB | RICHMOND R 1129 | 13471129 |  | 5.8066 | 3.1069 |  | 83.2 | 0.00069674 | 3144 | 0.053409 | 8127 | 3.707e-05 | 6573
DUMBARTON 1107MR448 | DUMBARTON 1107 | 14471107 |  | 0.21708 | 0.22829 |  | 4.1667 | 0.00069845 | 3124 | 0.053073 | 8250 | 3.7069e-05 | 6574
HUMBOLDT BAY 11024714 | HUMBOLDT BAY 1102 | 192341102 |  | 4.7996 | 4.4458 |  | 74 | 0.0005909 | 4403 | 0.062718 | 6689 | 3.7063e-05 | 6575
21ST AVENUE 0402CB | 21ST AVENUE 0402 | 22550402 |  | 2.1054 | 2.4672 |  | 31.4167 | 0.00069834 | 3126 | 0.053073 | 8251 | 3.7063e-05 | 6576
STAGG 110186148 | STAGG 1101 | 162421101 |  | 10.4063 | 7.7974 |  | 168 | 0.00068063 | 3318 | 0.054837 | 7785 | 3.7061e-05 | 6577
COALINGA NO 1 1106CB | COALINGA NO 1 1106 | 252161106 |  | 7.2203 | 6.9436 |  | 124.25 | 0.0006681 | 3456 | 0.056443 | 7509 | 3.7057e-05 | 6578
MISSION (X) 1102CB | MISSION (X) 1102 | 22011102 |  | 0.1757 | 0.29403 |  | 7.5 | 0.0006982 | 3127 | 0.053073 | 8251 | 3.7055e-05 | 6579
SF N 0405CB | SF N 0405 | 22280405 |  | 1.0698 | 1.3748 |  | 18.3333 | 0.00069808 | 3129 | 0.053073 | 8252 | 3.7049e-05 | 6580
MOUNTAIN VIEW 1105CB | MOUNTAIN VIEW 1105 | 82031105 |  | 4.3855 | 2.8311 |  | 68 | 0.00069804 | 3131 | 0.053073 | 8251 | 3.7047e-05 | 6581
MONROE 2103408 | MONROE 2103 | 43302103 |  | 1.3132 | 0.38591 |  | 20.8333 | 0.00057393 | 4602 | 0.064011 | 6540 | 3.7046e-05 | 6582
SALINAS 1102512906 | SALINAS 1102 | 182011102 |  | 0.74111 | 0.14599 |  | 13.5 | 0.00056343 | 4722 | 0.065968 | 6279 | 3.7038e-05 | 6583
SAN LEANDRO U 1102CB | SAN LEANDRO U 1102 | 13111102 |  | 8.2193 | 6.566 |  | 111.3333 | 0.00069779 | 3134 | 0.053073 | 8250 | 3.7033e-05 | 6584
EVERGREEN 2103XR072 | EVERGREEN 2103 | 82012103 |  | 6.372 | 5.9007 |  | 124.8333 | 0.00069299 | 3177 | 0.053407 | 8128 | 3.7033e-05 | 6585
SARATOGA 1111XR128 | SARATOGA 1111 | 83371111 |  | 4.5626 | 4.8288 |  | 62.1667 | 0.00069771 | 3135 | 0.053073 | 8251 | 3.7029e-05 | 6586
RICHMOND R 1125CB | RICHMOND R 1125 | 13471125 |  | 3.5603 | 3.1694 |  | 50.6167 | 0.00069768 | 3137 | 0.053073 | 8254 | 3.7028e-05 | 6587
BURLINGAME 04059054 | BURLINGAME 0405 | 24050405 |  | 1.7291 | 3.0559 |  | 30.3333 | 0.00069588 | 3151 | 0.053875 | 7982 | 3.7024e-05 | 6588
BUENA VISTA 1104CB | BUENA VISTA 1104 | 182261104 |  | 3.9039 | 0.58991 |  | 69.1667 | 0.00064252 | 3793 | 0.057836 | 7320 | 3.7022e-05 | 6589
LAKEWOOD 211094814 | LAKEWOOD 2110 | 13532110 |  | 3.5896 | 2.0726 |  | 59.5 | 0.00059337 | 4379 | 0.062902 | 6670 | 3.7018e-05 | 6590
TASSAJARA 2106CB | TASSAJARA 2106 | 14662106 |  | 1.1552 | 0 |  | 25 | 0.00055597 | 4803 | 0.067548 | 5575 | 3.7017e-05 | 6591
SF N 0401CB | SF N 0401 | 22280401 |  | 3.129 | 4.6186 |  | 48.8333 | 0.00069747 | 3139 | 0.053073 | 8251 | 3.7017e-05 | 6592
RENFRO 210256408 | RENFRO 2102 | 254572102 |  | 0.43125 | 0.0074793 |  | 6.8333 | 0.00066457 | 3505 | 0.056633 | 7484 | 3.7015e-05 | 6593
LIVERMORE 1102CB | LIVERMORE 1102 | 12141102 |  | 4.2255 | 3.7971 |  | 58.8333 | 0.00069743 | 3141 | 0.053073 | 8251 | 3.7014e-05 | 6594
WOODLAND 111222542 | WOODLAND 1112 | 62031112 |  | 2.152 | 0.38062 |  | 32.3333 | 0.00066171 | 3551 | 0.057211 | 7404 | 3.6996e-05 | 6595
LOGAN CREEK 2103CB | LOGAN CREEK 2103 | 103142103 |  | 3.1664 | 0.021523 |  | 43.8333 | 0.00054578 | 4900 | 0.068193 | 5360 | 3.6993e-05 | 6596
MENLO 11038914 | MENLO 1103 | 24131103 |  | 1.1849 | 0.15065 |  | 16.8333 | 0.00066659 | 3475 | 0.055003 | 7752 | 3.6993e-05 | 6597
ALMADEN 1102815266 | ALMADEN 1102 | 82311102 |  | 9.6615 | 12.0083 |  | 142.3333 | 0.00069683 | 3143 | 0.053073 | 8252 | 3.6983e-05 | 6598
MOUNTAIN VIEW 1106LM82 | MOUNTAIN VIEW 1106 | 82031106 |  | 3.5624 | 3.4554 |  | 56.3333 | 0.00066535 | 3495 | 0.056369 | 7518 | 3.6981e-05 | 6599
REEDLEY 111053586 | REEDLEY 1110 | 252341110 |  | 10.4295 | 8.1515 |  | 158 | 0.0006619 | 3548 | 0.058308 | 7249 | 3.6979e-05 | 6600
MISSION (X) 111384198 | MISSION (X) 1113 | 22011113 |  | 0.71489 | 0.78507 |  | 9.6667 | 0.0006511 | 3698 | 0.058106 | 7277 | 3.697e-05 | 6601
MADERA 1104CB | MADERA 1104 | 252761104 |  | 5.0372 | 2.706 |  | 84.8333 | 0.00063441 | 3884 | 0.061642 | 6809 | 3.6964e-05 | 6602
SAN MATEO 210170256 | SAN MATEO 2101 | 24192101 |  | 1.8513 | 1.7602 |  | 31.3333 | 0.00060965 | 4174 | 0.061296 | 6856 | 3.6931e-05 | 6603
CASTRO VALLEY 1108MR581 | CASTRO VALLEY 1108 | 14091108 |  | 0.90502 | 1.0255 |  | 14.6667 | 0.00069585 | 3152 | 0.053073 | 8252 | 3.6931e-05 | 6604
ALHAMBRA 1101CB | ALHAMBRA 1101 | 14101101 |  | 8.4097 | 4.3669 |  | 161.3333 | 0.00055082 | 4855 | 0.067533 | 5583 | 3.693e-05 | 6605
ROCKLIN 1103CB | ROCKLIN 1103 | 152061103 |  | 5.1053 | 0.48717 |  | 82.3333 | 0.00065229 | 3680 | 0.056597 | 7494 | 3.6925e-05 | 6606
VACAVILLE 110996966 | VACAVILLE 1109 | 63601109 |  | 0.077064 | 0 |  | 3 | 0.00069564 | 3154 | 0.053073 | 8251 | 3.692e-05 | 6607
EAST STOCKTON 110290582 | EAST STOCKTON 1102 | 163131102 |  | 0.28296 | 0 |  | 5.6667 | 0.00069552 | 3155 | 0.053073 | 8251 | 3.6913e-05 | 6608
FREMONT 1110MR130 | FREMONT 1110 | 14351110 |  | 1.4335 | 0.32339 |  | 28.5 | 0.00064161 | 3810 | 0.05893 | 7165 | 3.6904e-05 | 6609
RIPON 17036178 | RIPON 1703 | 163801703 |  | 2.4209 | 1.6488 |  | 37 | 0.00067927 | 3332 | 0.054388 | 7868 | 3.6903e-05 | 6610
EAST GRAND 1104CB | EAST GRAND 1104 | 22571104 |  | 8.2152 | 7.8254 |  | 122.1667 | 0.0006637 | 3516 | 0.056757 | 7472 | 3.6901e-05 | 6611
EAST GRAND 1109CB | EAST GRAND 1109 | 22571109 |  | 2.076 | 1.5658 |  | 41 | 0.00064282 | 3791 | 0.058009 | 7289 | 3.6896e-05 | 6612
TEVIS 21014690 | TEVIS 2101 | 255322101 |  | 3.7247 | 0.049091 |  | 61.5 | 0.00049484 | 5445 | 0.07583 | 4253 | 3.6894e-05 | 6613
LAMONT 1102CB | LAMONT 1102 | 253911102 |  | 8.7796 | 0.4076 |  | 126.95 | 0.0004786 | 5613 | 0.07718 | 3612 | 3.6893e-05 | 6614
CHOWCHILLA 1105CB | CHOWCHILLA 1105 | 254101105 |  | 2.0792 | 0.15903 |  | 30.4167 | 0.00060499 | 4240 | 0.061137 | 6878 | 3.689e-05 | 6615
BELLE HAVEN 0405CB | BELLE HAVEN 0405 | 24020405 |  | 7.2165 | 4.5344 |  | 121.1667 | 0.00059204 | 4392 | 0.06292 | 6668 | 3.6886e-05 | 6616
OAKLAND D 1110CR160 | OAKLAND D 1110 | 12041110 |  | 1.4326 | 1.3938 |  | 17.5 | 0.00069495 | 3158 | 0.053073 | 8251 | 3.6883e-05 | 6617
SF H 110553680 | SF H 1105 | 22101105 |  | 0.40396 | 0.48194 |  | 7 | 0.00069471 | 3160 | 0.053073 | 8250 | 3.687e-05 | 6618
NORTH TOWER 11024153 | NORTH TOWER 1102 | 42041102 |  | 4.2341 | 3.9941 |  | 61.0833 | 0.00065366 | 3661 | 0.056607 | 7492 | 3.6864e-05 | 6619
RICHMOND R 1127BR176 | RICHMOND R 1127 | 13471127 |  | 1.3506 | 0.80933 |  | 14.75 | 0.00069429 | 3164 | 0.053073 | 8252 | 3.6848e-05 | 6620
PAUL SWEET 2103458558 | PAUL SWEET 2103 | 83252103 |  | 2.2625 | 1.7734 |  | 35.8333 | 0.00064314 | 3788 | 0.057737 | 7331 | 3.6847e-05 | 6621
SONOMA 110749132 | SONOMA 1107 | 42721107 |  | 2.5628 | 0.048558 |  | 47.5 | 0.00060292 | 4267 | 0.060689 | 6927 | 3.6845e-05 | 6622
LAMMERS 1101CB | LAMMERS 1101 | 162771101 |  | 4.6166 | 0.27885 |  | 70.1667 | 0.00054808 | 4876 | 0.067246 | 5766 | 3.6843e-05 | 6623
DALY CITY 1109CB | DALY CITY 1109 | 22641109 |  | 4.1994 | 3.5554 |  | 57.1667 | 0.00069418 | 3165 | 0.053073 | 8252 | 3.6842e-05 | 6624
SALINAS 110122052 | SALINAS 1101 | 182011101 |  | 5.0493 | 4.335 |  | 70.3333 | 0.00069396 | 3169 | 0.053073 | 8252 | 3.683e-05 | 6625
JARVIS 1105CB | JARVIS 1105 | 13501105 |  | 1.4742 | 0.47317 |  | 21.8333 | 0.00069268 | 3180 | 0.053392 | 8142 | 3.6828e-05 | 6626
SANTA ROSA A 1101CB | SANTA ROSA A 1101 | 42151101 |  | 0.41855 | 0.4114 |  | 10 | 0.0006939 | 3170 | 0.053073 | 8251 | 3.6827e-05 | 6627
RENFRO 21014863 | RENFRO 2101 | 254572101 |  | 0.42285 | 0 |  | 6.5 | 0.0006938 | 3172 | 0.053073 | 8251 | 3.6822e-05 | 6628
FRANKLIN 1104CB | FRANKLIN 1104 | 13921104 | TRUE | 5.1926 | 3.9335 | 0.22479 | 83.0833 | 0.00061091 | 4155 | 0.059625 | 7066 | 3.682e-05 | 6629
SAN JOSE A 1110XR426 | SAN JOSE A 1110 | 82251110 |  | 2.6432 | 2.6935 |  | 39 | 0.00069367 | 3173 | 0.053073 | 8251 | 3.6815e-05 | 6630
HIGHLANDS 110476156 | HIGHLANDS 1104 | 43361104 |  | 1.0692 | 0.64123 |  | 16.3333 | 0.00055506 | 4818 | 0.066295 | 6217 | 3.6805e-05 | 6631
STELLING 1111LM40 | STELLING 1111 | 83481111 |  | 8.231 | 5.3463 |  | 139.5 | 0.0005805 | 4513 | 0.063902 | 6558 | 3.6802e-05 | 6632
MAGUNDEN 11054439 | MAGUNDEN 1105 | 252771105 |  | 2.0595 | 0.36198 |  | 36.3333 | 0.00057182 | 4631 | 0.065654 | 6331 | 3.68e-05 | 6633
PLUMAS 2107CB | PLUMAS 2107 | 153732107 |  | 2.6596 | 0.046028 |  | 50.3333 | 0.00050655 | 5321 | 0.073533 | 4606 | 3.6798e-05 | 6634
WHISMAN 110860014 | WHISMAN 1108 | 83631108 |  | 0.49292 | 0 |  | 10 | 0.00069324 | 3175 | 0.053073 | 8251 | 3.6792e-05 | 6635
RENFRO 21012252 | RENFRO 2101 | 254572101 |  | 2.2475 | 0.036233 |  | 38.5 | 0.000497 | 5425 | 0.074872 | 4432 | 3.6785e-05 | 6636
WINDSOR 1102382 | WINDSOR 1102 | 43501102 |  | 2.0833 | 0.63456 |  | 39.3333 | 0.00067427 | 3383 | 0.054354 | 7877 | 3.6783e-05 | 6637
JANES CREEK 1102CB | JANES CREEK 1102 | 192391102 |  | 6.2539 | 1.5423 |  | 103.3333 | 0.00057413 | 4600 | 0.064366 | 6500 | 3.6776e-05 | 6638
BERKELEY F 0403CB | BERKELEY F 0403 | 12060403 |  | 2.1862 | 2.4981 |  | 31.0833 | 0.00067988 | 3325 | 0.053894 | 7977 | 3.6775e-05 | 6639
PUEBLO 110447912 | PUEBLO 1104 | 43291104 |  | 4.0689 | 0.68173 |  | 71.8333 | 0.00054756 | 4883 | 0.067182 | 5826 | 3.6775e-05 | 6640
FREMONT 1112CB | FREMONT 1112 | 14351112 |  | 0.17746 | 0.11468 |  | 4.5 | 0.00069279 | 3179 | 0.053073 | 8251 | 3.6768e-05 | 6641
WILLIAMS 110275412 | WILLIAMS 1102 | 62051102 |  | 0.25918 | 0.23212 |  | 5 | 0.00066044 | 3573 | 0.055505 | 7671 | 3.6763e-05 | 6642
SALINAS 110245272 | SALINAS 1102 | 182011102 |  | 6.9464 | 6.9313 |  | 115.6667 | 0.00069267 | 3181 | 0.053073 | 8250 | 3.6762e-05 | 6643
LARKIN (Y) 11383527 | LARKIN (Y) 1138 | 22801138 |  | 0.5785 | 0.67909 |  | 8.0833 | 0.00069257 | 3182 | 0.053073 | 8252 | 3.6757e-05 | 6644
GUERNSEY 1108CB | GUERNSEY 1108 | 252661108 |  | 2.1735 | 0 |  | 13.4167 | 0.00047645 | 5632 | 0.07706 | 3725 | 3.6749e-05 | 6645
OAKLAND J 1105CB | OAKLAND J 1105 | 12091105 |  | 9.1928 | 10.3303 |  | 109.2833 | 0.00068758 | 3256 | 0.053407 | 8129 | 3.6742e-05 | 6646
HIGGINS 1110861610 | HIGGINS 1110 | 152691110 |  | 3.0515 | 2.1334 |  | 52 | 0.00054895 | 4872 | 0.066868 | 6106 | 3.6738e-05 | 6647
SAN CARLOS 1104636064 | SAN CARLOS 1104 | 24181104 | TRUE | 0.32676 | 0.20116 | 0.0063015 | 4.8333 | 0.00069219 | 3188 | 0.053073 | 8251 | 3.6736e-05 | 6648
MC CALL 110341168 | MC CALL 1103 | 254121103 |  | 0.01765 | 0 |  | 0.5 | 0.00069207 | 3191 | 0.053073 | 8251 | 3.673e-05 | 6649
FAIRWAY 1107M124 | FAIRWAY 1107 | 182061107 |  | 1.2856 | 0.017147 |  | 21.5 | 0.00060786 | 4198 | 0.060477 | 6963 | 3.6728e-05 | 6650
LAMONT 110316321 | LAMONT 1103 | 253911103 |  | 0.97748 | 0.78477 |  | 13.5 | 0.00069202 | 3192 | 0.053073 | 8251 | 3.6727e-05 | 6651
JESSUP 110269928 | JESSUP 1102 | 103441102 |  | 2.5842 | 0.75234 |  | 43.5 | 0.00055201 | 4848 | 0.066632 | 6157 | 3.6724e-05 | 6652
SANTA MARIA 1105CB | SANTA MARIA 1105 | 182671105 |  | 6.0458 | 3.0411 |  | 97.1667 | 0.00060804 | 4193 | 0.061326 | 6848 | 3.6722e-05 | 6653
LARKIN (Y) 1119645148 | LARKIN (Y) 1119 | 22801119 |  | 0.74954 | 0.82726 |  | 14 | 0.00069181 | 3195 | 0.053073 | 8251 | 3.6716e-05 | 6654
GRAND ISLAND 2223CB | GRAND ISLAND 2223 | 62462223 |  | 5.2165 | 0.91822 |  | 96.3667 | 0.00048116 | 5590 | 0.076143 | 4145 | 3.6715e-05 | 6655
COALINGA NO 1 11089714F | COALINGA NO 1 1108 | 252161108 |  | 0.79503 | 0.24746 |  | 15.8333 | 0.00065873 | 3592 | 0.0566 | 7493 | 3.6713e-05 | 6656
KIRKER 210849190 | KIRKER 2108 | 14452108 |  | 2.283 | 2.3226 |  | 33 | 0.00067119 | 3425 | 0.054556 | 7836 | 3.6713e-05 | 6657
PETALUMA A 0411CB | PETALUMA A 0411 | 42120411 |  | 3.063 | 2.9594 |  | 47.3333 | 0.0006674 | 3462 | 0.055084 | 7737 | 3.671e-05 | 6658
EUREKA E 1105CB | EUREKA E 1105 | 192331105 |  | 7.254 | 6.5013 |  | 89.75 | 0.00068377 | 3287 | 0.053474 | 8103 | 3.671e-05 | 6659
WYANDOTTE 1110CB | WYANDOTTE 1110 | 102911110 |  | 3.4943 | 0.76662 |  | 55.0833 | 0.0005476 | 4882 | 0.067032 | 5981 | 3.6707e-05 | 6660
SAN LEANDRO U 1102MR594 | SAN LEANDRO U 1102 | 13111102 |  | 4.1554 | 3.8347 |  | 59.7833 | 0.00069163 | 3197 | 0.053073 | 8252 | 3.6707e-05 | 6661
SARATOGA 11108645 | SARATOGA 1110 | 83371110 |  | 1.6328 | 1.2227 |  | 25 | 0.00069162 | 3198 | 0.053073 | 8251 | 3.6706e-05 | 6662
MALAGA 110455326 | MALAGA 1104 | 254251104 |  | 3.0191 | 1.8812 |  | 52.5 | 0.00066238 | 3539 | 0.056316 | 7528 | 3.6703e-05 | 6663
NEWARK 12KV 1106CB | NEWARK 12KV 1106 | 12221106 |  | 5.5904 | 4.5425 |  | 78.45 | 0.00069147 | 3202 | 0.053073 | 8251 | 3.6698e-05 | 6664
MILPITAS 2110XR024 | MILPITAS 2110 | 82832110 |  | 2.7992 | 2.9863 |  | 36 | 0.00069133 | 3204 | 0.053073 | 8251 | 3.6691e-05 | 6665
GUERNSEY 1105CB | GUERNSEY 1105 | 252661105 |  | 2.1667 | 0 |  | 13.4167 | 0.00047568 | 5642 | 0.077036 | 3741 | 3.6689e-05 | 6666
BAY MEADOWS 110448036 | BAY MEADOWS 1104 | 24011104 |  | 3.1995 | 2.7493 |  | 46 | 0.00064193 | 3804 | 0.058143 | 7275 | 3.6687e-05 | 6667
MOLINO 1104CB | MOLINO 1104 | 42571104 |  | 3.9906 | 1.4018 |  | 72.5 | 0.00056027 | 4751 | 0.066059 | 6257 | 3.6681e-05 | 6668
HOLLISTER 2104CB | HOLLISTER 2104 | 182492104 |  | 6.0759 | 0.84753 |  | 92.8333 | 0.00058421 | 4481 | 0.063149 | 6651 | 3.6679e-05 | 6669
CASTROVILLE 210395522 | CASTROVILLE 2103 | 182352103 |  | 3.3119 | 2.4602 |  | 56.5 | 0.00060488 | 4243 | 0.061326 | 6849 | 3.6663e-05 | 6670
LOS OSITOS 210187960 | LOS OSITOS 2101 | 182082101 |  | 3.8028 | 0.90836 |  | 76.3333 | 0.00057508 | 4590 | 0.064521 | 6485 | 3.6653e-05 | 6671
ROCKLIN 1101CB | ROCKLIN 1101 | 152061101 |  | 4.7232 | 1.0792 |  | 87 | 0.00056657 | 4693 | 0.064997 | 6433 | 3.665e-05 | 6672
LAWRENCE 1111CB | LAWRENCE 1111 | 83421111 |  | 3.7103 | 4.5366 |  | 49.3333 | 0.00069048 | 3211 | 0.053073 | 8252 | 3.6646e-05 | 6673
OAKLAND D 1110CR154 | OAKLAND D 1110 | 12041110 |  | 1.0104 | 0.91041 |  | 15.1667 | 0.00069043 | 3213 | 0.053073 | 8252 | 3.6643e-05 | 6674
ATWATER 110710520 | ATWATER 1107 | 253611107 |  | 1.3297 | 1.1076 |  | 23.8333 | 0.00067397 | 3388 | 0.054093 | 7933 | 3.6631e-05 | 6675
FIGARDEN 2110R9530 | FIGARDEN 2110 | 254552110 |  | 3.2515 | 1.1496 |  | 66.8333 | 0.00060443 | 4249 | 0.063779 | 6571 | 3.663e-05 | 6676
OAKLAND K 1103CB | OAKLAND K 1103 | 12101103 | TRUE | 4.9566 | 4.5283 | 0.57168 | 82.1667 | 0.00062075 | 4039 | 0.057857 | 7315 | 3.6616e-05 | 6677
SWIFT 2106XR088 | SWIFT 2106 | 83392106 |  | 4.6459 | 5.6219 |  | 67.3333 | 0.00068981 | 3220 | 0.053073 | 8252 | 3.661e-05 | 6678
ATWATER 1106269952 | ATWATER 1106 | 253611106 |  | 3.3407 | 1.2245 |  | 57.8333 | 0.00060371 | 4259 | 0.061783 | 6788 | 3.6608e-05 | 6679
SARATOGA 1114CB | SARATOGA 1114 | 83371114 |  | 7.0809 | 6.5767 |  | 104.3333 | 0.00065797 | 3597 | 0.056098 | 7562 | 3.6608e-05 | 6680
VASONA 110160084 | VASONA 1101 | 83771101 |  | 1.7558 | 1.6473 |  | 22 | 0.00068976 | 3222 | 0.053073 | 8251 | 3.6607e-05 | 6681
SF H 111084104 | SF H 1110 | 22101110 |  | 6.2708 | 6.8834 |  | 103 | 0.00057915 | 4533 | 0.063633 | 6595 | 3.6601e-05 | 6682
TULARE LAKE 1104748282 | TULARE LAKE 1104 | 252951104 |  | 0.044342 | 0 |  | 1.5 | 0.00054626 | 4897 | 0.067 | 6057 | 3.6599e-05 | 6683
WOODLAND 110922332 | WOODLAND 1109 | 62031109 |  | 0.58632 | 0.35955 |  | 8 | 0.00068959 | 3225 | 0.053073 | 8251 | 3.6598e-05 | 6684
MORAGA 1105E512R | MORAGA 1105 | 13801105 |  | 0.087676 | 0 |  | 1 | 0.00068943 | 3227 | 0.053073 | 8251 | 3.659e-05 | 6685
REDWOOD CITY 0406913566 | REDWOOD CITY 0406 | 24160406 |  | 6.4923 | 4.2238 |  | 105 | 0.0006286 | 3960 | 0.059477 | 7087 | 3.6589e-05 | 6686
SARATOGA 1109LC44 | SARATOGA 1109 | 83371109 |  | 9.0373 | 9.8542 |  | 143.5 | 0.00068933 | 3230 | 0.053073 | 8251 | 3.6584e-05 | 6687
SAN BRUNO 0401CB | SAN BRUNO 0401 | 22700401 |  | 1.9497 | 1.4778 |  | 19.9167 | 0.00067399 | 3386 | 0.054588 | 7831 | 3.6578e-05 | 6688
SAN RAFAEL 1102940 | SAN RAFAEL 1102 | 42011102 |  | 1.5063 | 0.7171 |  | 23 | 0.00066669 | 3473 | 0.054889 | 7770 | 3.6572e-05 | 6689
SONOMA 1106376 | SONOMA 1106 | 42721106 |  | 3.1586 | 1.946 |  | 57.5 | 0.00062122 | 4036 | 0.059712 | 7054 | 3.6564e-05 | 6690
HALF MOON BAY 1101903182 | HALF MOON BAY 1101 | 24101101 | FALSE | 1.0996 | 0.37596 | 0.75562 | 17 | 0.00051622 | 5212 | 0.067848 | 5460 | 3.6564e-05 | 6691
OLD RIVER 1105CB | OLD RIVER 1105 | 252821105 |  | 1.9935 | 0 |  | 16.3333 | 0.00048427 | 5553 | 0.075064 | 4406 | 3.655e-05 | 6692
MERCED 210190340 | MERCED 2101 | 252802101 |  | 0.27233 | 0 |  | 4.3333 | 0.00068867 | 3235 | 0.053073 | 8250 | 3.6549e-05 | 6693
GLENWOOD 11013855 | GLENWOOD 1101 | 24091101 |  | 0.29743 | 0.31029 |  | 4.3333 | 0.00068863 | 3236 | 0.053073 | 8250 | 3.6548e-05 | 6694
SAN LEANDRO U 1116MR212 | SAN LEANDRO U 1116 | 13111116 |  | 0.46587 | 0.32638 |  | 8.5 | 0.00068863 | 3237 | 0.053073 | 8251 | 3.6547e-05 | 6695
SF K 0411CB | SF K 0411 | 22130411 |  | 2.3126 | 3.6735 |  | 30.7 | 0.00068857 | 3240 | 0.053073 | 8250 | 3.6544e-05 | 6696
EL CERRITO G 1111CB | EL CERRITO G 1111 | 12501111 |  | 8.7263 | 6.2551 |  | 95.9833 | 0.00068568 | 3271 | 0.053435 | 8114 | 3.6539e-05 | 6697
MERCED 21014710 | MERCED 2101 | 252802101 |  | 14.3808 | 2.9881 |  | 220 | 0.00058507 | 4475 | 0.06363 | 6596 | 3.6534e-05 | 6698
FRUITVALE 1103CB | FRUITVALE 1103 | 253391103 |  | 6.6487 | 4.2541 |  | 106.4833 | 0.00066393 | 3512 | 0.055177 | 7727 | 3.6529e-05 | 6699
DEL MONTE 110138576 | DEL MONTE 1101 | 182221101 |  | 2.2203 | 1.8225 |  | 26.25 | 0.00068826 | 3244 | 0.053073 | 8251 | 3.6528e-05 | 6700
BELLE HAVEN 11058964 | BELLE HAVEN 1105 | 24021105 |  | 1.7107 | 0.87935 |  | 25.8333 | 0.00068793 | 3247 | 0.053073 | 8251 | 3.651e-05 | 6701
LAWRENCE 111233105 | LAWRENCE 1112 | 83421112 |  | 0.15736 | 0.13326 |  | 4.3333 | 0.00068789 | 3248 | 0.053073 | 8250 | 3.6508e-05 | 6702
CONCORD NO 1 0402CB | CONCORD NO 1 0402 | 12960402 |  | 3.8034 | 2.8515 |  | 55.8333 | 0.00068784 | 3249 | 0.053073 | 8250 | 3.6506e-05 | 6703
MISSION (X) 111639048 | MISSION (X) 1116 | 22011116 |  | 0.39142 | 0.42995 |  | 5.5 | 0.00068784 | 3250 | 0.053073 | 8250 | 3.6505e-05 | 6704
BELLE HAVEN 1107CB | BELLE HAVEN 1107 | 24021107 |  | 1.2726 | 1.3818 |  | 25.7833 | 0.00068769 | 3252 | 0.053073 | 8251 | 3.6498e-05 | 6705
8TH AVENUE 0401CB | 8TH AVENUE 0401 | 12670401 |  | 4.8857 | 5.6375 |  | 57.5 | 0.00068769 | 3254 | 0.053073 | 8254 | 3.6498e-05 | 6706
PUEBLO 110459106 | PUEBLO 1104 | 43291104 |  | 0.48349 | 0.047421 |  | 9.3333 | 0.00058277 | 4495 | 0.063666 | 6586 | 3.6497e-05 | 6707
SPENCE 1103CB | SPENCE 1103 | 182201103 |  | 7.0802 | 0.23022 |  | 118.5833 | 0.00054501 | 4908 | 0.067067 | 5928 | 3.6488e-05 | 6708
MILLBRAE 110482544 | MILLBRAE 1104 | 22691104 |  | 2.3177 | 1.9701 |  | 37 | 0.00060146 | 4283 | 0.060467 | 6967 | 3.6482e-05 | 6709
MERCED 1114CB | MERCED 1114 | 252801114 |  | 1.1589 | 0.17422 |  | 17.3333 | 0.00063656 | 3865 | 0.058744 | 7191 | 3.6481e-05 | 6710
EAST MARYSVILLE 1108CB | EAST MARYSVILLE 1108 | 152331108 |  | 11.763 | 1.5656 |  | 160.5 | 0.00051176 | 5268 | 0.073422 | 4619 | 3.6473e-05 | 6711
SANTA MARIA 1111CB | SANTA MARIA 1111 | 182671111 |  | 15.6007 | 7.6595 |  | 239.5833 | 0.00064029 | 3821 | 0.058157 | 7274 | 3.6472e-05 | 6712
CLAYTON 110371340 | CLAYTON 1103 | 12021103 |  | 2.5447 | 1.9171 |  | 43 | 0.00066194 | 3547 | 0.055067 | 7740 | 3.6468e-05 | 6713
7TH STANDARD 210348188 | 7TH STANDARD 2103 | 254582103 |  | 2.5317 | 0.1133 |  | 45 | 0.00051332 | 5251 | 0.070913 | 4903 | 3.6466e-05 | 6714
GOOSE LAKE 1103414584 | GOOSE LAKE 1103 | 254201103 |  | 0.021108 | 0 |  | 0.5 | 0.00047109 | 5689 | 0.0774 | 3397 | 3.6462e-05 | 6715
SANTA ROSA A 1111526 | SANTA ROSA A 1111 | 42151111 |  | 0.58886 | 0.48008 |  | 9.6667 | 0.00065261 | 3673 | 0.055714 | 7637 | 3.6451e-05 | 6716
STELLING 1108LV06 | STELLING 1108 | 83481108 |  | 6.063 | 5.3447 |  | 98.5 | 0.00057402 | 4601 | 0.063677 | 6585 | 3.645e-05 | 6717
NEWHALL 1109658906 | NEWHALL 1109 | 254461109 |  | 0.6496 | 0 |  | 10 | 0.00047091 | 5690 | 0.0774 | 3397 | 3.6448e-05 | 6718
OAKLAND X 1115CR296 | OAKLAND X 1115 | 12541115 |  | 2.3571 | 2.3615 |  | 37.5 | 0.00067265 | 3408 | 0.054376 | 7870 | 3.6445e-05 | 6719
POINT PINOLE 1102502690 | POINT PINOLE 1102 | 14261102 |  | 2.5754 | 2.4646 |  | 38.6667 | 0.00066693 | 3470 | 0.054513 | 7843 | 3.6444e-05 | 6720
EUREKA E 1104CB | EUREKA E 1104 | 192331104 |  | 13.7923 | 12.9109 |  | 192.4167 | 0.00064619 | 3752 | 0.056689 | 7479 | 3.6441e-05 | 6721
LOYOLA 1102LL62 | LOYOLA 1102 | 82161102 |  | 2.623 | 0.66902 |  | 49.5 | 0.00053387 | 5027 | 0.068361 | 5312 | 3.6434e-05 | 6722
CORCORAN 1101CB | CORCORAN 1101 | 252171101 |  | 0.52353 | 0 |  | 4.6167 | 0.00047829 | 5617 | 0.076346 | 4071 | 3.6431e-05 | 6723
SF G 0410CB | SF G 0410 | 22090410 |  | 0.58192 | 0.54173 |  | 7.4167 | 0.0006864 | 3259 | 0.053073 | 8251 | 3.6429e-05 | 6724
SF J 0402CB | SF J 0402 | 22220402 |  | 0.89311 | 0.83057 |  | 16.9167 | 0.0006862 | 3262 | 0.053073 | 8250 | 3.6419e-05 | 6725
MONROE 1105602 | MONROE 1105 | 43301105 |  | 0.87636 | 0.28544 |  | 16 | 0.00063186 | 3918 | 0.059601 | 7070 | 3.6415e-05 | 6726
WEST FRESNO 111179367 | WEST FRESNO 1111 | 253731111 |  | 5.6048 | 3.5653 |  | 95 | 0.00059623 | 4346 | 0.063008 | 6662 | 3.6412e-05 | 6727
SWIFT 2111XR316 | SWIFT 2111 | 83392111 |  | 1.766 | 1.8062 |  | 26 | 0.00068605 | 3264 | 0.053073 | 8251 | 3.6411e-05 | 6728
FIGARDEN 2107R1150 | FIGARDEN 2107 | 254552107 |  | 4.3953 | 0.5751 |  | 80.5 | 0.00052958 | 5078 | 0.07021 | 5001 | 3.6406e-05 | 6729
WEST FRESNO 1112749610 | WEST FRESNO 1112 | 253731112 |  | 6.439 | 1.572 |  | 85.8333 | 0.00055034 | 4858 | 0.066778 | 6125 | 3.6398e-05 | 6730
DUMBARTON 1102CB | DUMBARTON 1102 | 14471102 |  | 0.15468 | 0 |  | 5 | 0.00068544 | 3272 | 0.053073 | 8251 | 3.6378e-05 | 6731
PLUMAS 1102CB | PLUMAS 1102 | 153731102 |  | 5.6275 | 0.65567 |  | 98.8333 | 0.00048096 | 5592 | 0.075858 | 4244 | 3.6363e-05 | 6732
GATES 1107CB | GATES 1107 | 253931107 |  | 2.5191 | 0 |  | 19.4167 | 0.00048668 | 5531 | 0.075668 | 4295 | 3.636e-05 | 6733
SANGER 110485476 | SANGER 1104 | 252351104 |  | 1.2498 | 0.095428 |  | 21.5 | 0.00055989 | 4757 | 0.066651 | 6152 | 3.6347e-05 | 6734
WILLOW PASS 1102CB | WILLOW PASS 1102 | 13911102 |  | 5.1225 | 4.9247 |  | 102 | 0.00063858 | 3841 | 0.057331 | 7390 | 3.6344e-05 | 6735
RIO BRAVO 1102422657 | RIO BRAVO 1102 | 252861102 |  | 3.755 | 3.3798 |  | 58.1667 | 0.00067743 | 3346 | 0.053839 | 7988 | 3.6332e-05 | 6736
OAKLAND D 1112CR340 | OAKLAND D 1112 | 12041112 |  | 5.0672 | 6.0975 |  | 75.4167 | 0.00068072 | 3317 | 0.05335 | 8155 | 3.6326e-05 | 6737
SAN JOSE B 1112XR304 | SAN JOSE B 1112 | 82261112 |  | 4.3569 | 5.1801 |  | 66.8333 | 0.00068444 | 3280 | 0.053073 | 8252 | 3.6325e-05 | 6738
WESTLEY 1102CB | WESTLEY 1102 | 162671102 |  | 0.048395 | 0 |  | 2 | 0.00046922 | 5704 | 0.0774 | 3397 | 3.6317e-05 | 6739
PAUL SWEET 210875588 | PAUL SWEET 2108 | 83252108 |  | 3.7218 | 3.7319 |  | 66 | 0.00067272 | 3405 | 0.054547 | 7838 | 3.6316e-05 | 6740
OAKLAND D 1106CR396 | OAKLAND D 1106 | 12041106 |  | 0.92777 | 0.79665 |  | 22 | 0.00068427 | 3282 | 0.053073 | 8251 | 3.6316e-05 | 6741
BUELLTON 1101CB | BUELLTON 1101 | 183041101 |  | 3.6116 | 0.8923 |  | 65 | 0.00058223 | 4499 | 0.063516 | 6611 | 3.6305e-05 | 6742
FREMONT 1104MR707 | FREMONT 1104 | 14351104 |  | 0.097327 | 0 |  | 2 | 0.00068384 | 3285 | 0.053073 | 8251 | 3.6293e-05 | 6743
CHARCA 1106CB | CHARCA 1106 | 254501106 |  | 3.4508 | 0.29403 |  | 43.1667 | 0.00061643 | 4097 | 0.060174 | 7000 | 3.6273e-05 | 6744
FAIRHAVEN 1103CB | FAIRHAVEN 1103 | 192451103 |  | 4.3853 | 0.075696 |  | 84 | 0.0005453 | 4907 | 0.066673 | 6147 | 3.6273e-05 | 6745
FREMONT 1110CB | FREMONT 1110 | 14351110 |  | 3.639 | 2.9248 |  | 69.1667 | 0.00068333 | 3291 | 0.053073 | 8252 | 3.6266e-05 | 6746
ALMADEN 1110XR408 | ALMADEN 1110 | 82311110 |  | 7.4612 | 11.0261 |  | 106.8333 | 0.00068332 | 3292 | 0.053073 | 8251 | 3.6266e-05 | 6747
SAN LEANDRO U 1105MR803 | SAN LEANDRO U 1105 | 13111105 |  | 4.2164 | 4.3806 |  | 49.5833 | 0.00068178 | 3310 | 0.053213 | 8211 | 3.6264e-05 | 6748
CASTRO VALLEY 1105MR585 | CASTRO VALLEY 1105 | 14091105 |  | 2.6271 | 2.1217 |  | 37.4167 | 0.00068318 | 3293 | 0.053073 | 8251 | 3.6258e-05 | 6749
ORO LOMA 1108CB | ORO LOMA 1108 | 255371108 |  | 0.51737 | 0 |  | 5 | 0.00046845 | 5711 | 0.0774 | 3395 | 3.6258e-05 | 6750
DIXON 110512382 | DIXON 1105 | 62061105 |  | 2.356 | 2.306 |  | 34 | 0.00068312 | 3294 | 0.053073 | 8251 | 3.6255e-05 | 6751
MC KEE 1106CB | MC KEE 1106 | 83531106 |  | 4.392 | 3.7038 |  | 84.8333 | 0.00068312 | 3295 | 0.053073 | 8251 | 3.6255e-05 | 6752
MERCED 210190270 | MERCED 2101 | 252802101 |  | 0.79144 | 0.58469 |  | 17.3333 | 0.00051824 | 5192 | 0.071318 | 4852 | 3.6255e-05 | 6753
SAN CARLOS 11039148 | SAN CARLOS 1103 | 24181103 | TRUE | 4.3057 | 3.4187 | 0.021062 | 59.1667 | 0.00062934 | 3951 | 0.05778 | 7328 | 3.625e-05 | 6754
HICKS 2105XR516 | HICKS 2105 | 83432105 |  | 2.083 | 2.3305 |  | 30.5 | 0.00067556 | 3367 | 0.053758 | 8013 | 3.6244e-05 | 6755
MISSION (X) 11083555 | MISSION (X) 1108 | 22011108 |  | 0.93079 | 1.8538 |  | 16.8667 | 0.00068289 | 3297 | 0.053073 | 8252 | 3.6243e-05 | 6756
MILPITAS 1109XR370 | MILPITAS 1109 | 82831109 |  | 4.7798 | 7.9748 |  | 72.6667 | 0.00068287 | 3298 | 0.053073 | 8251 | 3.6242e-05 | 6757
HICKS 110913234 | HICKS 1109 | 83431109 |  | 7.1346 | 8.125 |  | 110.8333 | 0.00068283 | 3299 | 0.053073 | 8251 | 3.624e-05 | 6758
BABEL 0401CB | BABEL 0401 | 13850401 |  | 3.0716 | 2.7674 |  | 52.6667 | 0.00065146 | 3690 | 0.055717 | 7636 | 3.6235e-05 | 6759
DOLAN ROAD 11013012 | DOLAN ROAD 1101 | 182381101 | TRUE | 13.7286 | 2.6421 | 0.072611 | 267 | 0.00034873 | 7163 | 0.10535 | 3305 | 3.6234e-05 | 6760
DIXON LANDING 2109MR119 | DIXON LANDING 2109 | 14722109 |  | 5.4241 | 4.7339 |  | 94 | 0.00067362 | 3392 | 0.054296 | 7890 | 3.6231e-05 | 6761
TAFT 110136578 | TAFT 1101 | 252081101 |  | 5.0421 | 6.4365 |  | 90.8333 | 0.00062537 | 3993 | 0.05955 | 7078 | 3.6223e-05 | 6762
NEW HOPE 110257150 | NEW HOPE 1102 | 162081102 |  | 2.4209 | 0.28218 |  | 44 | 0.00050228 | 5368 | 0.073253 | 4644 | 3.6214e-05 | 6763
MC KEE 1105XR272 | MC KEE 1105 | 83531105 |  | 3.0576 | 4.1146 |  | 46.5 | 0.00068213 | 3307 | 0.053073 | 8251 | 3.6203e-05 | 6764
REEDLEY 110181110 | REEDLEY 1101 | 252341101 |  | 3.9748 | 2.7657 |  | 62.25 | 0.00067961 | 3329 | 0.053463 | 8108 | 3.6198e-05 | 6765
WASCO 1102CB | WASCO 1102 | 252961102 |  | 5.7144 | 4.9118 |  | 99.6667 | 0.00067621 | 3356 | 0.053683 | 8037 | 3.6197e-05 | 6766
SF N 1102405616 | SF N 1102 | 22281102 |  | 1.7654 | 2.9777 |  | 29.8333 | 0.00068199 | 3308 | 0.053073 | 8251 | 3.6195e-05 | 6767
CASTRO VALLEY 1102MR359 | CASTRO VALLEY 1102 | 14091102 |  | 6.768 | 6.1113 |  | 117.8333 | 0.00056991 | 4658 | 0.063157 | 6649 | 3.6192e-05 | 6768
BERKELEY F 0401CB | BERKELEY F 0401 | 12060401 |  | 0.0014204 | 0 |  | 0.5 | 0.0006819 | 3309 | 0.053073 | 8251 | 3.619e-05 | 6769
PUEBLO 210375612 | PUEBLO 2103 | 43292103 |  | 6.8007 | 0.76403 |  | 119 | 0.00053449 | 5015 | 0.067692 | 5512 | 3.6185e-05 | 6770
SF H 1102CB | SF H 1102 | 22101102 |  | 0.89667 | 1.7128 |  | 13.5833 | 0.00068175 | 3311 | 0.053073 | 8251 | 3.6182e-05 | 6771
SYCAMORE CREEK 110979474 | SYCAMORE CREEK 1109 | 102971109 |  | 0.69447 | 0.16683 |  | 13.5 | 0.00054003 | 4957 | 0.067 | 6057 | 3.6182e-05 | 6772
EL CAPITAN 1104CB | EL CAPITAN 1104 | 253881104 |  | 7.1511 | 0.7859 |  | 123.75 | 0.00052176 | 5159 | 0.070733 | 4928 | 3.6172e-05 | 6773
STOREY 11066320 | STOREY 1106 | 254611106 |  | 1.1976 | 0.19399 |  | 14.8333 | 0.0006563 | 3621 | 0.057173 | 7409 | 3.6168e-05 | 6774
SOLANO 0401BR320 | SOLANO 0401 | 13140401 |  | 1.8283 | 2.0151 |  | 25.9167 | 0.00068143 | 3312 | 0.053073 | 8249 | 3.6165e-05 | 6775
LINCOLN 1105CB | LINCOLN 1105 | 153701105 |  | 5.6387 | 0.38063 |  | 91.25 | 0.00055523 | 4817 | 0.066008 | 6273 | 3.6155e-05 | 6776
SARATOGA 1113CB | SARATOGA 1113 | 83371113 |  | 14.0449 | 16.6769 |  | 211 | 0.00067359 | 3393 | 0.053601 | 8059 | 3.6154e-05 | 6777
SONOMA 11033138 | SONOMA 1103 | 42721103 |  | 1.8502 | 0.42089 |  | 29.5 | 0.00054983 | 4864 | 0.06525 | 6400 | 3.6151e-05 | 6778
MESA 1103126697 | MESA 1103 | 182821103 | FALSE | 0.98323 | 0.12891 | 1.0914 | 14.5 | 2.8442e-05 | 11144 | 1.2532 | 2055 | 3.6145e-05 | 6779
TAFT 1101CB | TAFT 1101 | 252081101 |  | 3.955 | 0.3216 |  | 51.75 | 0.00055878 | 4764 | 0.065588 | 6344 | 3.6143e-05 | 6780
LAWRENCE 1113CB | LAWRENCE 1113 | 83421113 |  | 4.5322 | 4.2295 |  | 61.4167 | 0.0006808 | 3315 | 0.053073 | 8252 | 3.6132e-05 | 6781
DEL MONTE 21022650 | DEL MONTE 2102 | 182222102 |  | 1.9817 | 1.5943 |  | 36 | 0.00061597 | 4098 | 0.059069 | 7148 | 3.6126e-05 | 6782
MAXWELL 1105CB | MAXWELL 1105 | 62881105 |  | 9.5665 | 3.1526 |  | 154.3333 | 0.00055548 | 4812 | 0.0665 | 6187 | 3.6122e-05 | 6783
REEDLEY 110493222 | REEDLEY 1104 | 252341104 |  | 4.4878 | 2.1612 |  | 77 | 0.0005723 | 4626 | 0.063852 | 6565 | 3.6117e-05 | 6784
SAN PABLO 1105BR186 | SAN PABLO 1105 | 14371105 |  | 4.5914 | 5.4071 |  | 77.6667 | 0.00061757 | 4079 | 0.058831 | 7179 | 3.6115e-05 | 6785
PAUL SWEET 210110716 | PAUL SWEET 2101 | 83252101 |  | 1.3127 | 0.18141 |  | 13 | 0.00061679 | 4091 | 0.058429 | 7230 | 3.6114e-05 | 6786
DEL MONTE 210448004 | DEL MONTE 2104 | 182222104 |  | 2.9905 | 3.7784 |  | 53.1667 | 0.000669 | 3444 | 0.05412 | 7925 | 3.6106e-05 | 6787
TRIMBLE 1110CB | TRIMBLE 1110 | 83801110 |  | 0.5919 | 0 |  | 13.5 | 0.00066223 | 3542 | 0.054875 | 7774 | 3.6096e-05 | 6788
BELLE HAVEN 0402CB | BELLE HAVEN 0402 | 24020402 |  | 4.1159 | 4.017 |  | 64.6167 | 0.00068007 | 3323 | 0.053073 | 8252 | 3.6093e-05 | 6789
BUENA VISTA 1104388555 | BUENA VISTA 1104 | 182261104 |  | 0.050992 | 0 |  | 1.3333 | 0.00067979 | 3326 | 0.053073 | 8251 | 3.6078e-05 | 6790
HALF MOON BAY 11026153 | HALF MOON BAY 1102 | 24101102 |  | 1.6922 | 1.4274 |  | 27.5 | 0.00054998 | 4862 | 0.066035 | 6265 | 3.6073e-05 | 6791
EAST GRAND 1105727 | EAST GRAND 1105 | 22571105 |  | 2.4305 | 2.2905 |  | 42.3333 | 0.0006479 | 3730 | 0.055705 | 7639 | 3.6069e-05 | 6792
BELMONT 110268446 | BELMONT 1102 | 24031102 |  | 4.8931 | 2.3303 |  | 57.8333 | 0.00061973 | 4053 | 0.059013 | 7159 | 3.6066e-05 | 6793
POTRERO PP (A) 1115CB | POTRERO PP (A) 1115 | 22031115 |  | 0.83594 | 0.89718 |  | 21.3333 | 0.00067947 | 3330 | 0.053073 | 8252 | 3.6061e-05 | 6794
EL CAPITAN 1105CB | EL CAPITAN 1105 | 253881105 |  | 1.9336 | 0.039012 |  | 21.45 | 0.00057235 | 4625 | 0.068327 | 5325 | 3.6051e-05 | 6795
BELMONT 11109090 | BELMONT 1110 | 24031110 | TRUE | 2.6103 | 2.2402 | 0.00013502 | 42.8333 | 0.00061922 | 4056 | 0.058058 | 7281 | 3.605e-05 | 6796
FREMONT 1103MR127 | FREMONT 1103 | 14351103 |  | 4.1541 | 2.1086 |  | 78.5 | 0.0006231 | 4015 | 0.057943 | 7299 | 3.6049e-05 | 6797
SHAFTER 1111CB | SHAFTER 1111 | 253651111 |  | 5.2228 | 0.77398 |  | 59.6667 | 0.00051573 | 5221 | 0.070446 | 4956 | 3.6042e-05 | 6798
BELLE HAVEN 110580572 | BELLE HAVEN 1105 | 24021105 |  | 0.77459 | 0.60526 |  | 12.5 | 0.00060172 | 4279 | 0.060872 | 6903 | 3.6042e-05 | 6799
MAGUNDEN 21081267 | MAGUNDEN 2108 | 252772108 |  | 3.3085 | 0.063266 |  | 57.5 | 0.00050706 | 5317 | 0.073556 | 4604 | 3.6024e-05 | 6800
MENLO 11049086 | MENLO 1104 | 24131104 |  | 7.9472 | 7.4377 |  | 128.8333 | 0.00067439 | 3379 | 0.053559 | 8080 | 3.6012e-05 | 6801
GOLDTREE 1108939400 | GOLDTREE 1108 | 182581108 |  | 0.32702 | 0.30169 |  | 7 | 0.00053727 | 4988 | 0.06703 | 5983 | 3.6012e-05 | 6802
ARBUCKLE 1101CB | ARBUCKLE 1101 | 62081101 |  | 4.1531 | 1.1208 |  | 63.4167 | 0.00053433 | 5017 | 0.067924 | 5427 | 3.6002e-05 | 6803
MC KEE 110693368 | MC KEE 1106 | 83531106 |  | 9.1779 | 9.1482 |  | 146.3333 | 0.00067484 | 3374 | 0.053571 | 8073 | 3.5997e-05 | 6804
SAN LEANDRO U 1105CB | SAN LEANDRO U 1105 | 13111105 |  | 3.5113 | 2.5915 |  | 45.4167 | 0.00067817 | 3341 | 0.053073 | 8252 | 3.5992e-05 | 6805
SF G 0413CB | SF G 0413 | 22090413 |  | 0.97936 | 1.0218 |  | 13.3333 | 0.00067813 | 3342 | 0.053073 | 8251 | 3.599e-05 | 6806
VIERRA 1707CB | VIERRA 1707 | 162701707 |  | 8.1932 | 0.60522 |  | 143 | 0.00048714 | 5528 | 0.074543 | 4483 | 3.598e-05 | 6807
MILLBRAE 110465748 | MILLBRAE 1104 | 22691104 |  | 1.5145 | 1.6196 |  | 27.5 | 0.00059523 | 4358 | 0.060332 | 6983 | 3.598e-05 | 6808
PARKWAY 1103CB | PARKWAY 1103 | 42051103 |  | 6.6815 | 4.9736 |  | 99.8333 | 0.00065419 | 3650 | 0.055026 | 7748 | 3.5977e-05 | 6809
6TH AVENUE 0401CB | 6TH AVENUE 0401 | 22530401 |  | 1.2675 | 1.5374 |  | 18.0833 | 0.00067778 | 3343 | 0.053073 | 8249 | 3.5971e-05 | 6810
CASTROVILLE 210380794 | CASTROVILLE 2103 | 182352103 |  | 5.8019 | 0.23651 |  | 121 | 0.00054788 | 4878 | 0.066597 | 6169 | 3.596e-05 | 6811
JANES CREEK 110141990 | JANES CREEK 1101 | 192391101 |  | 4.4435 | 0.11644 |  | 77 | 0.00054025 | 4955 | 0.066457 | 6194 | 3.5956e-05 | 6812
OAKLAND D 1110CB | OAKLAND D 1110 | 12041110 |  | 0.28344 | 0.52634 |  | 11.8333 | 0.00067721 | 3347 | 0.053073 | 8250 | 3.5941e-05 | 6813
WOLFE 1114CB | WOLFE 1114 | 83671114 |  | 1.9302 | 1.4118 |  | 35.5 | 0.00067718 | 3348 | 0.053073 | 8251 | 3.594e-05 | 6814
POTRERO PP (A) 110395150 | POTRERO PP (A) 1103 | 22031103 |  | 0.25108 | 0.2429 |  | 7 | 0.00067698 | 3350 | 0.053073 | 8251 | 3.5929e-05 | 6815
SANGER 111695584 | SANGER 1116 | 252351116 |  | 7.2766 | 4.3984 |  | 116 | 0.00061405 | 4122 | 0.062418 | 6726 | 3.5918e-05 | 6816
BERESFORD 0403CB | BERESFORD 0403 | 24040403 |  | 3.783 | 3.0371 |  | 59 | 0.00066793 | 3457 | 0.054311 | 7886 | 3.5916e-05 | 6817
PIERCY 2109XR202 | PIERCY 2109 | 83912109 |  | 0.55408 | 0 |  | 10 | 0.00060861 | 4183 | 0.057947 | 7298 | 3.5915e-05 | 6818
TRES VIAS 110147580 | TRES VIAS 1101 | 103251101 |  | 0.93347 | 0.015929 |  | 15 | 0.00046391 | 5761 | 0.0774 | 3397 | 3.5906e-05 | 6819
LAWRENCE 1112CB | LAWRENCE 1112 | 83421112 |  | 10.8638 | 11.5809 |  | 153.5833 | 0.00067653 | 3352 | 0.053073 | 8249 | 3.5905e-05 | 6820
PACIFICA 1102320094 | PACIFICA 1102 | 22811102 | TRUE | 0.96202 | 0.90659 | 0.31805 | 10.5 | 0.00050807 | 5306 | 0.070694 | 4935 | 3.5903e-05 | 6821
EL CERRITO G 1109BR122 | EL CERRITO G 1109 | 12501109 |  | 2.9472 | 1.1139 |  | 44.5 | 0.00064251 | 3794 | 0.056983 | 7437 | 3.5903e-05 | 6822
ATWATER 110558858 | ATWATER 1105 | 253611105 |  | 1.5182 | 0.62033 |  | 22 | 0.0006343 | 3886 | 0.058082 | 7279 | 3.5902e-05 | 6823
RENFRO 2101CB | RENFRO 2101 | 254572101 |  | 8.4125 | 0.51516 |  | 133 | 0.00059847 | 4317 | 0.062484 | 6719 | 3.5896e-05 | 6824
MIRABEL 1102206 | MIRABEL 1102 | 42091102 | TRUE | 8.9962 | 0.99269 | 0.015232 | 164 | 0.00053429 | 5018 | 0.067199 | 5813 | 3.5883e-05 | 6825
CORDELIA 1110CB | CORDELIA 1110 | 62701110 |  | 5.3404 | 0.6357 |  | 94.0333 | 0.00053589 | 4998 | 0.067271 | 5751 | 3.5876e-05 | 6826
SEMITROPIC 111081868 | SEMITROPIC 1110 | 252901110 |  | 2.7005 | 0.78089 |  | 52.8333 | 0.00051893 | 5187 | 0.07103 | 4892 | 3.5871e-05 | 6827
STELLING 1113CB | STELLING 1113 | 83481113 |  | 10.9813 | 13.1939 |  | 174.6667 | 0.00067583 | 3362 | 0.053073 | 8251 | 3.5868e-05 | 6828
SOLEDAD 210475336 | SOLEDAD 2104 | 182052104 |  | 4.6627 | 5.36 |  | 85 | 0.00063657 | 3863 | 0.056368 | 7519 | 3.5863e-05 | 6829
OLIVEHURST 1101505262 | OLIVEHURST 1101 | 152901101 |  | 0.019281 | 0 |  | 1.3333 | 0.00050158 | 5376 | 0.073469 | 4615 | 3.5861e-05 | 6830
BANCROFT 0401CB | BANCROFT 0401 | 13030401 | TRUE | 8.2243 | 8.637 | 0.0070811 | 108.45 | 0.00067568 | 3364 | 0.053073 | 8251 | 3.586e-05 | 6831
RIO BRAVO 1104CB | RIO BRAVO 1104 | 252861104 |  | 4.6097 | 0 |  | 42 | 0.0004727 | 5669 | 0.075674 | 4294 | 3.5857e-05 | 6832
PETALUMA C 110835448 | PETALUMA C 1108 | 42631108 |  | 1.9341 | 1.7879 |  | 29.5 | 0.00067557 | 3366 | 0.053073 | 8251 | 3.5854e-05 | 6833
CLEAR LAKE 1102720 | CLEAR LAKE 1102 | 42141102 |  | 2.602 | 1.6582 |  | 40.5 | 0.00063203 | 3916 | 0.056849 | 7461 | 3.585e-05 | 6834
SANTA MARIA 1106CB | SANTA MARIA 1106 | 182671106 |  | 2.1577 | 1.73 |  | 36.75 | 0.00067544 | 3369 | 0.053073 | 8251 | 3.5847e-05 | 6835
CLIFF DRIVE 0402893980 | CLIFF DRIVE 0402 | 83230402 |  | 3.5935 | 1.3972 |  | 39.0333 | 0.00061424 | 4116 | 0.058292 | 7252 | 3.5845e-05 | 6836
OAKLAND J 1116CB | OAKLAND J 1116 | 12091116 | TRUE | 18.6187 | 21.095 | 0.12601 | 277.5833 | 0.00065554 | 3631 | 0.055041 | 7746 | 3.5843e-05 | 6837
MENLO 0404CB | MENLO 0404 | 24130404 |  | 8.1904 | 5.0694 |  | 145.8333 | 0.00055701 | 4793 | 0.06434 | 6505 | 3.5839e-05 | 6838
WINDSOR 1101158 | WINDSOR 1101 | 43501101 |  | 1.9204 | 0.27863 |  | 32.8333 | 0.0005378 | 4980 | 0.06668 | 6145 | 3.5825e-05 | 6839
CLARKSVILLE 211019692 | CLARKSVILLE 2110 | 153612110 |  | 1.5938 | 0 |  | 29.3333 | 0.00053379 | 5028 | 0.067095 | 5903 | 3.5824e-05 | 6840
REDWOOD CITY 0408CB | REDWOOD CITY 0408 | 24160408 |  | 5.7203 | 4.5091 |  | 88.2095 | 0.00067493 | 3372 | 0.053073 | 8251 | 3.5821e-05 | 6841
PAUL SWEET 210112488 | PAUL SWEET 2101 | 83252101 |  | 6.2041 | 4.4953 |  | 107.3333 | 0.00066536 | 3494 | 0.053981 | 7959 | 3.582e-05 | 6842
GREENBRAE 1104300 | GREENBRAE 1104 | 43091104 |  | 8.2003 | 5.7296 |  | 154 | 0.00059917 | 4308 | 0.05944 | 7093 | 3.5819e-05 | 6843
LIVERMORE 1104CB | LIVERMORE 1104 | 12141104 |  | 6.0723 | 1.766 |  | 81.6667 | 0.00063547 | 3873 | 0.056057 | 7572 | 3.5815e-05 | 6844
SUISUN 110447404 | SUISUN 1104 | 62131104 |  | 2.6534 | 2.7371 |  | 35.8333 | 0.00067472 | 3376 | 0.053073 | 8250 | 3.5809e-05 | 6845
PUEBLO 2102656 | PUEBLO 2102 | 43292102 |  | 14.6112 | 1.0246 |  | 284 | 0.00051503 | 5235 | 0.069721 | 5084 | 3.5805e-05 | 6846
PUEBLO 2102850102 | PUEBLO 2102 | 43292102 | TRUE | 2.4525 | 0.2728 | 0.033761 | 50.5 | 0.00033903 | 7325 | 0.17219 | 3183 | 3.5799e-05 | 6847
DOLAN ROAD 1101156268 | DOLAN ROAD 1101 | 182381101 | TRUE | 2.2507 | 0.54632 | 0.025784 | 41.5 | 0.00052904 | 5085 | 0.067623 | 5538 | 3.579e-05 | 6848
SF M 0402CB | SF M 0402 | 22270402 |  | 1.9394 | 3.0559 |  | 31.1667 | 0.00067431 | 3381 | 0.053073 | 8250 | 3.5787e-05 | 6849
CASTRO VALLEY 1104CB | CASTRO VALLEY 1104 | 14091104 |  | 7.3303 | 7.2531 |  | 121.9167 | 0.00067427 | 3382 | 0.053073 | 8250 | 3.5785e-05 | 6850
MENLO 0401CB | MENLO 0401 | 24130401 |  | 6.4089 | 5.9903 |  | 102.8333 | 0.00057361 | 4607 | 0.062824 | 6677 | 3.5777e-05 | 6851
MARINA (F) 040740279 | MARINA (F) 0407 | 22780407 |  | 0.66387 | 0.64463 |  | 8.8333 | 0.00067405 | 3385 | 0.053073 | 8252 | 3.5774e-05 | 6852
BELMONT 1110330790 | BELMONT 1110 | 24031110 | TRUE | 0.44234 | 0.21932 | 0.12969 | 6.3333 | 0.00067397 | 3387 | 0.053073 | 8251 | 3.577e-05 | 6853
COTATI 1104232 | COTATI 1104 | 42271104 |  | 0.27458 | 0.1772 |  | 5.3333 | 0.00067395 | 3389 | 0.053073 | 8251 | 3.5768e-05 | 6854
FIGARDEN 2102R833 | FIGARDEN 2102 | 254552102 |  | 2.1897 | 0.5242 |  | 42.5 | 0.00049815 | 5412 | 0.073679 | 4584 | 3.5768e-05 | 6855
ROSSMOOR 1103CB | ROSSMOOR 1103 | 14161103 |  | 2.4845 | 0 |  | 29.8095 | 0.00052677 | 5107 | 0.067916 | 5431 | 3.5767e-05 | 6856
FITCH MOUNTAIN 1111792628 | FITCH MOUNTAIN 1111 | 42751111 | TRUE | 0.90872 | 0.22946 | 0.28492 | 16.5 | 0.00054156 | 4941 | 0.064468 | 6490 | 3.5761e-05 | 6857
SF G 0412CB | SF G 0412 | 22090412 |  | 1.1007 | 0.95734 |  | 13 | 0.000673 | 3404 | 0.053734 | 8021 | 3.5758e-05 | 6858
STELLING 1104CB | STELLING 1104 | 83481104 |  | 7.8757 | 7.6203 |  | 120.3333 | 0.0006737 | 3391 | 0.053073 | 8251 | 3.5755e-05 | 6859
RIO DELL 11026151 | RIO DELL 1102 | 192251102 |  | 1.1736 | 1.0273 |  | 17.5 | 0.00055231 | 4844 | 0.065408 | 6378 | 3.5744e-05 | 6860
EL CERRITO G 1106CB | EL CERRITO G 1106 | 12501106 |  | 2.2059 | 0.9539 |  | 27.4833 | 0.00067324 | 3396 | 0.053073 | 8248 | 3.5731e-05 | 6861
DEL MONTE 21032144 | DEL MONTE 2103 | 182222103 |  | 1.6371 | 1.2664 |  | 35.5 | 0.0005325 | 5042 | 0.067194 | 5816 | 3.5726e-05 | 6862
MILLBRAE 1103CB | MILLBRAE 1103 | 22691103 |  | 0.18413 | 0 |  | 3 | 0.00053302 | 5039 | 0.067035 | 5973 | 3.5725e-05 | 6863
OAKLAND D 0410CB | OAKLAND D 0410 | 12040410 |  | 2.7512 | 2.5151 |  | 34.25 | 0.00067302 | 3402 | 0.053073 | 8249 | 3.5719e-05 | 6864
LARKIN (Y) 11366663 | LARKIN (Y) 1136 | 22801136 |  | 0.61599 | 0.80494 |  | 10 | 0.00067267 | 3406 | 0.053073 | 8251 | 3.5701e-05 | 6865
COLUSA 1101CB | COLUSA 1101 | 62021101 |  | 11.3862 | 6.1054 |  | 178.1667 | 0.00061786 | 4072 | 0.059269 | 7115 | 3.5698e-05 | 6866
REDWOOD CITY 1105742744 | REDWOOD CITY 1105 | 24161105 |  | 0.070514 | 0.0036703 |  | 0.83333 | 0.00067257 | 3409 | 0.053073 | 8250 | 3.5695e-05 | 6867
BELLEVUE 110485960 | BELLEVUE 1104 | 43181104 |  | 1.55 | 0.71037 |  | 30 | 0.0006045 | 4248 | 0.058002 | 7290 | 3.5694e-05 | 6868
VASONA 1102944560 | VASONA 1102 | 83771102 | TRUE | 0.58749 | 0.080907 | 0.13019 | 11.5 | 0.00053265 | 5041 | 0.067 | 6057 | 3.5688e-05 | 6869
HICKS 1113XR180 | HICKS 1113 | 83431113 |  | 8.3334 | 10 |  | 116.5 | 0.00067233 | 3411 | 0.053073 | 8250 | 3.5682e-05 | 6870
SF G 0407CB | SF G 0407 | 22090407 |  | 1.3562 | 1.3401 |  | 16.25 | 0.00067231 | 3412 | 0.053073 | 8251 | 3.5681e-05 | 6871
NEWARK 21KV 2103MR128 | NEWARK 21KV 2103 | 12232103 |  | 10.2665 | 7.9328 |  | 173 | 0.00067224 | 3413 | 0.053073 | 8251 | 3.5678e-05 | 6872
RAINBOW 1105R9550 | RAINBOW 1105 | 254441105 |  | 7.6885 | 3.1225 |  | 121.5 | 0.00056278 | 4729 | 0.066683 | 6144 | 3.5673e-05 | 6873
RIPON 1704343465 | RIPON 1704 | 163801704 |  | 1.1892 | 0.27303 |  | 21.5 | 0.00055323 | 4832 | 0.065719 | 6320 | 3.5673e-05 | 6874
SALMON CREEK 1101242382 | SALMON CREEK 1101 | 43161101 |  | 1.2966 | 0.14604 |  | 25 | 0.00052768 | 5098 | 0.066223 | 6229 | 3.5669e-05 | 6875
CHANNEL 110111822 | CHANNEL 1101 | 163071101 |  | 2.3716 | 0.84854 |  | 43.1667 | 0.00067205 | 3416 | 0.053073 | 8251 | 3.5667e-05 | 6876
BERKELEY F 1103CB | BERKELEY F 1103 | 12061103 |  | 0.54178 | 0.55476 |  | 12 | 0.00067204 | 3417 | 0.053073 | 8251 | 3.5667e-05 | 6877
SANTA ROSA A 1103CB | SANTA ROSA A 1103 | 42151103 |  | 7.6598 | 5.5045 |  | 159 | 0.00065692 | 3613 | 0.05465 | 7816 | 3.566e-05 | 6878
BERESFORD 0404CB | BERESFORD 0404 | 24040404 |  | 5.7448 | 5.7098 |  | 82.1667 | 0.0006665 | 3476 | 0.053666 | 8042 | 3.5659e-05 | 6879
HICKS 1111XR220 | HICKS 1111 | 83431111 |  | 8.5187 | 11.5261 |  | 124.5 | 0.00067187 | 3418 | 0.053073 | 8251 | 3.5658e-05 | 6880
BAHIA 1105CB | BAHIA 1105 | 43251105 |  | 4.8847 | 1.7441 |  | 78.3333 | 0.00059809 | 4323 | 0.060456 | 6968 | 3.5644e-05 | 6881
SAN LUIS OBISPO 1103CB | SAN LUIS OBISPO 1103 | 182631103 | TRUE | 7.9719 | 0.63135 | 0.01469 | 125 | 0.00030377 | 7936 | 0.28065 | 3040 | 3.5638e-05 | 6882
CORCORAN 1106339194 | CORCORAN 1106 | 252171106 |  | 3.3033 | 0.70405 |  | 58.8333 | 0.00060646 | 4224 | 0.059494 | 7084 | 3.5638e-05 | 6883
HALF MOON BAY 110265568 | HALF MOON BAY 1102 | 24101102 |  | 3.1304 | 0.74045 |  | 52.3333 | 0.00055747 | 4789 | 0.063434 | 6618 | 3.5628e-05 | 6884
MT EDEN 1104CB | MT EDEN 1104 | 13761104 |  | 7.3059 | 6.2352 |  | 96.7 | 0.00067097 | 3426 | 0.053073 | 8250 | 3.561e-05 | 6885
MC CALL 110398596 | MC CALL 1103 | 254121103 |  | 0.024317 | 0 |  | 0.5 | 0.00067091 | 3427 | 0.053073 | 8251 | 3.5607e-05 | 6886
LOCKEFORD 21013912 | LOCKEFORD 2101 | 163682101 |  | 6.2701 | 0.58566 |  | 83.25 | 0.00050827 | 5305 | 0.071571 | 4817 | 3.5606e-05 | 6887
SARATOGA 1115LC20 | SARATOGA 1115 | 83371115 |  | 1.8585 | 1.796 |  | 27.8333 | 0.00065233 | 3679 | 0.055154 | 7731 | 3.5599e-05 | 6888
PEABODY 210441042 | PEABODY 2104 | 63642104 |  | 4.125 | 1.576 |  | 73.8333 | 0.00055306 | 4834 | 0.066061 | 6256 | 3.5594e-05 | 6889
VINEYARD 2109CB | VINEYARD 2109 | 14502109 |  | 0.22811 | 0 |  | 7.25 | 0.00064944 | 3715 | 0.054033 | 7942 | 3.5581e-05 | 6890
MIRABEL 1101254 | MIRABEL 1101 | 42091101 |  | 7.5648 | 1.348 |  | 140.5 | 0.00053205 | 5048 | 0.066974 | 6071 | 3.558e-05 | 6891
MC KEE 1103XR028 | MC KEE 1103 | 83531103 |  | 9.012 | 6.6033 |  | 157.3333 | 0.00046132 | 5794 | 0.0948 | 3328 | 3.5567e-05 | 6892
SF L 0408CB | SF L 0408 | 22260408 |  | 2.444 | 2.622 |  | 30.75 | 0.00067013 | 3433 | 0.053073 | 8251 | 3.5566e-05 | 6893
SAN BENITO 2103CB | SAN BENITO 2103 | 182742103 |  | 0.59024 | 0 |  | 7.0833 | 0.0005257 | 5116 | 0.067826 | 5466 | 3.5565e-05 | 6894
NORTH TOWER 110477646 | NORTH TOWER 1104 | 42041104 |  | 6.2797 | 3.8281 |  | 88.5 | 0.00063787 | 3853 | 0.056126 | 7557 | 3.5561e-05 | 6895
PUTAH CREEK 110242982 | PUTAH CREEK 1102 | 63681102 |  | 4.8381 | 2.468 |  | 81.5 | 0.0005884 | 4435 | 0.063058 | 6657 | 3.5559e-05 | 6896
TIDEWATER 210967868 | TIDEWATER 2109 | 14652109 |  | 2.307 | 0.80337 |  | 44 | 0.0006001 | 4297 | 0.058932 | 7164 | 3.5554e-05 | 6897
EL CERRITO G 1102CB | EL CERRITO G 1102 | 12501102 |  | 6.1389 | 3.4205 |  | 80.5333 | 0.00065989 | 3579 | 0.054432 | 7857 | 3.5552e-05 | 6898
SAN CARLOS 0404CB | SAN CARLOS 0404 | 24180404 |  | 8.7216 | 7.1879 |  | 102.7595 | 0.00064236 | 3797 | 0.055554 | 7667 | 3.555e-05 | 6899
FULTON 11065056 | FULTON 1106 | 42561106 |  | 0.022138 | 0 |  | 3.5 | 0.00053059 | 5067 | 0.067 | 6057 | 3.5549e-05 | 6900
DALY CITY 110985658 | DALY CITY 1109 | 22641109 |  | 2.0265 | 2.1687 |  | 29.8333 | 0.00066572 | 3484 | 0.053306 | 8176 | 3.5549e-05 | 6901
WEST SACRAMENTO 1109CB | WEST SACRAMENTO 1109 | 63131109 |  | 12.5586 | 8.9472 |  | 213.0333 | 0.00064165 | 3809 | 0.058477 | 7223 | 3.5549e-05 | 6902
BERKELEY F 0409CB | BERKELEY F 0409 | 12060409 |  | 3.5791 | 4.5971 |  | 53.6667 | 0.00066959 | 3440 | 0.053073 | 8253 | 3.5537e-05 | 6903
CLARKSVILLE 2103547420 | CLARKSVILLE 2103 | 153612103 |  | 0.24464 | 0 |  | 3.5 | 0.00059045 | 4408 | 0.059042 | 7153 | 3.5517e-05 | 6904
OROVILLE 0403CB | OROVILLE 0403 | 102520403 |  | 2.0349 | 0.88036 |  | 27.9167 | 0.0006535 | 3662 | 0.055687 | 7642 | 3.5516e-05 | 6905
HICKS 2105CB | HICKS 2105 | 83432105 |  | 4.3941 | 4.6538 |  | 73 | 0.00066042 | 3574 | 0.053956 | 7968 | 3.5489e-05 | 6906
6TH AVENUE 0402CB | 6TH AVENUE 0402 | 22530402 |  | 1.2159 | 1.4692 |  | 19.3333 | 0.00066863 | 3449 | 0.053073 | 8252 | 3.5486e-05 | 6907
CATLETT 110538000 | CATLETT 1105 | 153761105 |  | 0.069477 | 0 |  | 1.5 | 0.00045827 | 5831 | 0.0774 | 3397 | 3.547e-05 | 6908
KINGSBURG 1108913944 | KINGSBURG 1108 | 252241108 |  | 0.075478 | 0 |  | 1.5 | 0.00045818 | 5834 | 0.0774 | 3397 | 3.5463e-05 | 6909
HARRIS 1109CB | HARRIS 1109 | 192431109 |  | 14.1261 | 10.3276 |  | 224.5 | 0.00057941 | 4529 | 0.061315 | 6852 | 3.5458e-05 | 6910
CHOWCHILLA 1101CB | CHOWCHILLA 1101 | 254101101 |  | 0.67956 | 0.39773 |  | 7.3333 | 0.0005105 | 5280 | 0.069659 | 5088 | 3.5455e-05 | 6911
MOUNTAIN VIEW 1107LM30 | MOUNTAIN VIEW 1107 | 82031107 |  | 11.5706 | 8.7709 |  | 167.3333 | 0.00062141 | 4032 | 0.056782 | 7469 | 3.5453e-05 | 6912
KIRKER 21076332 | KIRKER 2107 | 14452107 |  | 4.696 | 4.5352 |  | 84.8333 | 0.00061032 | 4165 | 0.05787 | 7312 | 3.5446e-05 | 6913
SF N 0402CB | SF N 0402 | 22280402 |  | 1.0101 | 0.90668 |  | 17.1667 | 0.00064354 | 3780 | 0.055907 | 7595 | 3.5446e-05 | 6914
SAN RAMON 2110CB | SAN RAMON 2110 | 14232110 |  | 0.10253 | 0.17353 |  | 6 | 0.00066781 | 3459 | 0.053073 | 8251 | 3.5443e-05 | 6915
ROCKLIN 110450090 | ROCKLIN 1104 | 152061104 |  | 0.17105 | 0.13488 |  | 5 | 0.00064722 | 3737 | 0.054476 | 7847 | 3.5439e-05 | 6916
GREENBRAE 110276992 | GREENBRAE 1102 | 43091102 |  | 1.4274 | 0.013433 |  | 28 | 0.0005372 | 4990 | 0.066254 | 6221 | 3.5439e-05 | 6917
WEBER 1111173750 | WEBER 1111 | 163481111 |  | 10.5688 | 6.0976 |  | 186 | 0.00066197 | 3545 | 0.053766 | 8008 | 3.5438e-05 | 6918
TYLER 11049082 | TYLER 1104 | 103571104 |  | 0.014186 | 0 |  | 0.5 | 0.0005287 | 5089 | 0.067 | 6057 | 3.5423e-05 | 6919
BAHIA 1105172836 | BAHIA 1105 | 43251105 |  | 4.1939 | 3.593 |  | 73.1667 | 0.00066729 | 3464 | 0.053073 | 8251 | 3.5415e-05 | 6920
MC CALL 1106CB | MC CALL 1106 | 254121106 |  | 5.5998 | 0.30331 |  | 84.45 | 0.0005086 | 5300 | 0.070678 | 4936 | 3.5415e-05 | 6921
CHOWCHILLA 1102CB | CHOWCHILLA 1102 | 254101102 |  | 2.8938 | 0.53198 |  | 55.5 | 0.00054102 | 4949 | 0.066661 | 6151 | 3.541e-05 | 6922
BELMONT 1109CB | BELMONT 1109 | 24031109 |  | 0.0033713 | 0 |  | 1 | 0.00052849 | 5092 | 0.067 | 6057 | 3.5409e-05 | 6923
WHISMAN 110834748 | WHISMAN 1108 | 83631108 |  | 0.44572 | 0.31568 |  | 14 | 0.00066708 | 3468 | 0.053073 | 8251 | 3.5403e-05 | 6924
MISSION (X) 111090264 | MISSION (X) 1110 | 22011110 |  | 1.6682 | 2.1154 |  | 32.5 | 0.00066702 | 3469 | 0.053073 | 8251 | 3.5401e-05 | 6925
STELLING 110760030 | STELLING 1107 | 83481107 |  | 3.6529 | 4.5099 |  | 49.8333 | 0.00061844 | 4063 | 0.05691 | 7449 | 3.54e-05 | 6926
LAWRENCE 111360068 | LAWRENCE 1113 | 83421113 |  | 1.1095 | 0.99253 |  | 17.3333 | 0.00066674 | 3472 | 0.053073 | 8250 | 3.5386e-05 | 6927
PEORIA 17046090 | PEORIA 1704 | 163781704 | TRUE | 0.80356 | 0.18485 | 0.44594 | 7.5 | 0.00060718 | 4209 | 0.069913 | 5060 | 3.5381e-05 | 6928
AVENAL 210144778 | AVENAL 2101 | 255002101 |  | 9.7202 | 5.1319 |  | 155 | 0.00057697 | 4561 | 0.06352 | 6609 | 3.5378e-05 | 6929
KERMAN 1103CB | KERMAN 1103 | 252711103 |  | 4.4616 | 2.2436 |  | 62.6667 | 0.00057132 | 4641 | 0.062599 | 6700 | 3.5369e-05 | 6930
TULARE LAKE 1104CB | TULARE LAKE 1104 | 252951104 |  | 1.9342 | 0.10888 |  | 26.6667 | 0.0005257 | 5117 | 0.067395 | 5671 | 3.5367e-05 | 6931
BOSTON 0401CR242 | BOSTON 0401 | 13320401 | TRUE | 4.5748 | 3.4788 | 0.40965 | 51.0833 | 0.00066021 | 3578 | 0.053758 | 8012 | 3.5355e-05 | 6932
CABRILLO 1104838078 | CABRILLO 1104 | 183101104 |  | 0.044005 | 0 |  | 1 | 0.00066615 | 3481 | 0.053073 | 8251 | 3.5354e-05 | 6933
FELLOWS 21041073 | FELLOWS 2104 | 254242104 |  | 4.7175 | 0.010619 |  | 81 | 0.00052756 | 5099 | 0.067016 | 6008 | 3.5352e-05 | 6934
CORONA 1101CB | CORONA 1101 | 43491101 |  | 5.2958 | 2.0514 |  | 105.5 | 0.00059761 | 4331 | 0.060664 | 6933 | 3.5351e-05 | 6935
BELLE HAVEN 0406226075 | BELLE HAVEN 0406 | 24020406 |  | 8.1601 | 7.1358 |  | 108 | 0.00064696 | 3742 | 0.054857 | 7778 | 3.5346e-05 | 6936
FAIRVIEW 2206768080 | FAIRVIEW 2206 | 13432206 |  | 5.4939 | 3.8751 |  | 110 | 0.00061013 | 4168 | 0.059117 | 7143 | 3.5333e-05 | 6937
ORO LOMA 1115245946 | ORO LOMA 1115 | 255371115 |  | 2.2167 | 2.0126 |  | 39.5 | 0.0006205 | 4041 | 0.057692 | 7335 | 3.533e-05 | 6938
LARKIN (Y) 1108CB | LARKIN (Y) 1108 | 22801108 |  | 0.1103 | 0 |  | 4.5 | 0.00066561 | 3486 | 0.053073 | 8251 | 3.5326e-05 | 6939
SAN LEANDRO U 1109CR344 | SAN LEANDRO U 1109 | 13111109 | TRUE | 2.5165 | 2.4926 | 0.0089164 | 32.0333 | 0.00066553 | 3488 | 0.053073 | 8251 | 3.5321e-05 | 6940
SF H 1110326008 | SF H 1110 | 22101110 |  | 0.019258 | 0 |  | 0.5 | 0.00066547 | 3489 | 0.053073 | 8251 | 3.5318e-05 | 6941
ATWATER 110610470 | ATWATER 1106 | 253611106 |  | 2.8918 | 3.7419 |  | 46 | 0.00066542 | 3491 | 0.053073 | 8251 | 3.5316e-05 | 6942
SALINAS 1102CB | SALINAS 1102 | 182011102 |  | 7.6772 | 5.9918 |  | 113.5 | 0.00058277 | 4494 | 0.061063 | 6885 | 3.5311e-05 | 6943
WOODCHUCK 2101R4610 | WOODCHUCK 2101 | 254912101 |  | 0.054162 | 0 |  | 1 | 0.0005165 | 5211 | 0.068364 | 5310 | 3.531e-05 | 6944
FORT ORD 11019516 | FORT ORD 1101 | 182401101 |  | 1.2744 | 0.19657 |  | 23.5 | 0.00063541 | 3875 | 0.056629 | 7486 | 3.5309e-05 | 6945
CLOVERDALE 110282888 | CLOVERDALE 1102 | 42821102 |  | 0.19515 | 0.1763 |  | 5.5 | 0.00058845 | 4434 | 0.059707 | 7055 | 3.5307e-05 | 6946
OLIVEHURST 1104CB | OLIVEHURST 1104 | 152901104 |  | 11.4323 | 6.0348 |  | 189.5 | 0.00060057 | 4291 | 0.059488 | 7085 | 3.5301e-05 | 6947
CANAL 110611640 | CANAL 1106 | 252091106 |  | 4.9224 | 0.8339 |  | 73 | 0.00062439 | 4006 | 0.058047 | 7285 | 3.53e-05 | 6948
RALSTON 110148936 | RALSTON 1101 | 24141101 | FALSE | 6.102 | 3.8148 | 8.3954 | 102.1667 | 0.00049701 | 5424 | 0.084376 | 3374 | 3.5298e-05 | 6949
HOLLISTER 210491424 | HOLLISTER 2104 | 182492104 | TRUE | 8.7813 | 0.5941 | 0.17275 | 166.3333 | 0.00031796 | 7668 | 0.10628 | 3303 | 3.5284e-05 | 6950
PLEASANT GROVE 211048528 | PLEASANT GROVE 2110 | 152442110 |  | 0.96901 | 0 |  | 8.5 | 0.00051461 | 5239 | 0.068224 | 5354 | 3.5279e-05 | 6951
POINT PINOLE 1101P140 | POINT PINOLE 1101 | 14261101 |  | 1.3077 | 1.6012 |  | 18.5 | 0.00062946 | 3948 | 0.056084 | 7568 | 3.5277e-05 | 6952
RICHMOND R 1130BR174 | RICHMOND R 1130 | 13471130 |  | 3.5599 | 3.8553 |  | 49.25 | 0.00066467 | 3501 | 0.053073 | 8251 | 3.5276e-05 | 6953
WOODSIDE 110239574 | WOODSIDE 1102 | 24251102 |  | 6.8919 | 4.0215 |  | 122.4167 | 0.00054115 | 4947 | 0.065578 | 6347 | 3.5274e-05 | 6954
HARRIS 11087920 | HARRIS 1108 | 192431108 |  | 10.4956 | 8.7764 |  | 150.5 | 0.00058694 | 4456 | 0.060296 | 6986 | 3.5274e-05 | 6955
OAKLAND D 1110CR336 | OAKLAND D 1110 | 12041110 |  | 0.55698 | 0.75495 |  | 10 | 0.00066463 | 3504 | 0.053073 | 8251 | 3.5273e-05 | 6956
KERN OIL 11164513 | KERN OIL 1116 | 252721116 |  | 2.5319 | 0.22841 |  | 47 | 0.00062796 | 3971 | 0.056178 | 7550 | 3.5273e-05 | 6957
GRAND ISLAND 222492264 | GRAND ISLAND 2224 | 62462224 |  | 7.6881 | 2.2597 |  | 141.3333 | 0.00049353 | 5462 | 0.072135 | 4764 | 3.527e-05 | 6958
HORSESHOE 1106CB | HORSESHOE 1106 | 152571106 |  | 6.7789 | 1.8234 |  | 119.5 | 0.00052938 | 5080 | 0.066688 | 6140 | 3.527e-05 | 6959
MT EDEN 1113CB | MT EDEN 1113 | 13761113 |  | 2.633 | 2.207 |  | 37.0333 | 0.0006578 | 3601 | 0.05373 | 8022 | 3.5268e-05 | 6960
VIERRA 170614268 | VIERRA 1706 | 162701706 |  | 5.5154 | 2.0273 |  | 94 | 0.00060853 | 4186 | 0.061354 | 6844 | 3.5261e-05 | 6961
SAN RAMON 2106MR285 | SAN RAMON 2106 | 14232106 |  | 2.9183 | 2.6302 |  | 45 | 0.00066439 | 3509 | 0.053073 | 8251 | 3.5261e-05 | 6962
WASCO 11042699 | WASCO 1104 | 252961104 |  | 0.6292 | 0.391 |  | 10.8333 | 0.00066425 | 3510 | 0.053073 | 8250 | 3.5254e-05 | 6963
WILSON 110173322 | WILSON 1101 | 254301101 |  | 3.6804 | 3.1941 |  | 63 | 0.00065558 | 3629 | 0.054038 | 7940 | 3.5249e-05 | 6964
LOCKEFORD 210157564 | LOCKEFORD 2101 | 163682101 |  | 4.715 | 0.69325 |  | 86.0833 | 0.00045721 | 5844 | 0.077198 | 3596 | 3.5242e-05 | 6965
FAIRMOUNT 0401CB | FAIRMOUNT 0401 | 12650401 |  | 4.2276 | 4.5258 |  | 41.5333 | 0.00066388 | 3513 | 0.053073 | 8253 | 3.5234e-05 | 6966
VACA DIXON 1102CB | VACA DIXON 1102 | 63591102 |  | 1.9557 | 0.35517 |  | 30.9 | 0.00052092 | 5169 | 0.067391 | 5677 | 3.5222e-05 | 6967
KERMAN 1108CB | KERMAN 1108 | 252711108 |  | 7.7557 | 0.65566 |  | 126.2 | 0.00046411 | 5759 | 0.07605 | 4181 | 3.5218e-05 | 6968
BROOKSIDE 0401CB | BROOKSIDE 0401 | 13210401 |  | 3.7161 | 4.2574 |  | 48.9167 | 0.0006635 | 3521 | 0.053073 | 8252 | 3.5214e-05 | 6969
OAKLAND J 1106CB | OAKLAND J 1106 | 12091106 |  | 6.1864 | 5.6219 |  | 69.7833 | 0.0006624 | 3538 | 0.05377 | 8007 | 3.521e-05 | 6970
BAYWOOD 1101V102 | BAYWOOD 1101 | 182801101 |  | 0.12394 | 0 |  | 3 | 0.00052518 | 5123 | 0.067035 | 5975 | 3.5206e-05 | 6971
EL CERRITO G 1101CB | EL CERRITO G 1101 | 12501101 |  | 10.1318 | 7.1117 |  | 114.4833 | 0.00066325 | 3523 | 0.053073 | 8246 | 3.52e-05 | 6972
GRANT 1108CB | GRANT 1108 | 14381108 |  | 8.6785 | 9.1843 |  | 120 | 0.0006632 | 3524 | 0.053073 | 8250 | 3.5198e-05 | 6973
FAIRWAY 1107CB | FAIRWAY 1107 | 182061107 |  | 3.659 | 0.097282 |  | 60 | 0.00052681 | 5106 | 0.067113 | 5886 | 3.5197e-05 | 6974
NORTECH 2107CB | NORTECH 2107 | 82462107 |  | 0.11213 | 0 |  | 3 | 0.00066317 | 3526 | 0.053073 | 8251 | 3.5196e-05 | 6975
NOVATO 1104CB | NOVATO 1104 | 42211104 |  | 6.1692 | 4.3385 |  | 117.3333 | 0.00063077 | 3932 | 0.055696 | 7641 | 3.5194e-05 | 6976
EL PATIO 1114CB | EL PATIO 1114 | 82921114 |  | 0.56671 | 0.049351 |  | 11.5 | 0.00066303 | 3530 | 0.053073 | 8251 | 3.5189e-05 | 6977
ARCATA 1122CB | ARCATA 1122 | 192021122 |  | 15.4598 | 5.5286 |  | 290.5 | 0.00053237 | 5044 | 0.066317 | 6216 | 3.5187e-05 | 6978
OAKLAND X 1114CB | OAKLAND X 1114 | 12541114 |  | 3.0802 | 3.3144 |  | 39 | 0.00066299 | 3531 | 0.053073 | 8251 | 3.5186e-05 | 6979
DUMBARTON 1104CB | DUMBARTON 1104 | 14471104 |  | 7.3387 | 7.766 |  | 121 | 0.00066286 | 3532 | 0.053073 | 8251 | 3.518e-05 | 6980
SF N 040377850 | SF N 0403 | 22280403 |  | 1.6802 | 1.4416 |  | 27.1667 | 0.00061406 | 4121 | 0.057401 | 7373 | 3.5174e-05 | 6981
SAN JOSE A 1110CB | SAN JOSE A 1110 | 82251110 |  | 6.1933 | 4.912 |  | 112.3333 | 0.0006627 | 3534 | 0.053073 | 8251 | 3.5171e-05 | 6982
TRINIDAD 110246990 | TRINIDAD 1102 | 192231102 |  | 1.3046 | 0 |  | 29 | 0.00052494 | 5126 | 0.067 | 6057 | 3.5171e-05 | 6983
FRANKLIN 1101P132 | FRANKLIN 1101 | 13921101 | TRUE | 1.5154 | 0.12511 | 0.0032458 | 28.5 | 0.00063366 | 3895 | 0.056012 | 7577 | 3.5166e-05 | 6984
JARVIS 1104MR139 | JARVIS 1104 | 13501104 |  | 0.012682 | 0 |  | 0.5 | 0.00066259 | 3535 | 0.053073 | 8251 | 3.5165e-05 | 6985
MOLINO 1102905231 | MOLINO 1102 | 42571102 |  | 0.025282 | 0 |  | 0.5 | 0.00052477 | 5130 | 0.067 | 6057 | 3.516e-05 | 6986
BAY MEADOWS 110565187 | BAY MEADOWS 1105 | 24011105 |  | 2.7282 | 0.76786 |  | 36.6667 | 0.00063244 | 3909 | 0.055976 | 7583 | 3.5154e-05 | 6987
MARYSVILLE 1105CB | MARYSVILLE 1105 | 152011105 |  | 8.5961 | 4.1138 |  | 144.75 | 0.00058101 | 4509 | 0.062067 | 6755 | 3.515e-05 | 6988
CARQUINEZ 1105680 | CARQUINEZ 1105 | 43281105 |  | 3.7986 | 2.8192 |  | 65.5 | 0.00066226 | 3541 | 0.053073 | 8251 | 3.5148e-05 | 6989
SF K 0401CB | SF K 0401 | 22130401 |  | 2.4807 | 3.1916 |  | 40.1167 | 0.00064513 | 3764 | 0.053982 | 7956 | 3.5148e-05 | 6990
POINT PINOLE 1102BR158 | POINT PINOLE 1102 | 14261102 |  | 1.4562 | 0.84135 |  | 23 | 0.00065608 | 3624 | 0.053678 | 8039 | 3.5147e-05 | 6991
HALF MOON BAY 11018940 | HALF MOON BAY 1101 | 24101101 |  | 3.4521 | 1.7849 |  | 47 | 0.00059066 | 4406 | 0.059951 | 7026 | 3.5142e-05 | 6992
EL CERRITO G 1111818638 | EL CERRITO G 1111 | 12501111 |  | 2.7023 | 2.7779 |  | 30.5 | 0.00066213 | 3544 | 0.053073 | 8252 | 3.5141e-05 | 6993
LIVERMORE 1101CB | LIVERMORE 1101 | 12141101 |  | 2.5087 | 2.5854 |  | 36.5 | 0.00063419 | 3887 | 0.05479 | 7791 | 3.5123e-05 | 6994
LLAGAS 2105XR008 | LLAGAS 2105 | 83182105 |  | 1.9068 | 2.4384 |  | 36.5 | 0.00066176 | 3549 | 0.053073 | 8251 | 3.5121e-05 | 6995
SARATOGA 1108LC106 | SARATOGA 1108 | 83371108 |  | 6.9763 | 8.0489 |  | 100.3333 | 0.00066169 | 3552 | 0.053073 | 8252 | 3.5118e-05 | 6996
BURLINGAME 040139556 | BURLINGAME 0401 | 24050401 |  | 1.036 | 0.93751 |  | 23.5 | 0.00060972 | 4173 | 0.059592 | 7073 | 3.5116e-05 | 6997
SAN RAFAEL 110668694 | SAN RAFAEL 1106 | 42011106 | TRUE | 2.5806 | 2.0998 | 0.060621 | 46.0833 | 0.00059934 | 4302 | 0.055846 | 7605 | 3.511e-05 | 6998
WILLITS 1104329646 | WILLITS 1104 | 42661104 |  | 0.14538 | 0.045016 |  | 1.8333 | 0.00052395 | 5142 | 0.067 | 6057 | 3.5105e-05 | 6999
HIGHWAY 1104CB | HIGHWAY 1104 | 42651104 |  | 3.2477 | 2.8496 |  | 55 | 0.00065198 | 3684 | 0.053591 | 8065 | 3.5085e-05 | 7000
OAKLAND D 0407CB | OAKLAND D 0407 | 12040407 |  | 0.33075 | 0.31993 |  | 7 | 0.00064314 | 3787 | 0.055324 | 7703 | 3.5076e-05 | 7001
RENFRO 2107CB | RENFRO 2107 | 254572107 |  | 0.9617 | 0.034657 |  | 14.8333 | 0.00045837 | 5826 | 0.07687 | 3845 | 3.5075e-05 | 7002
CASTRO VALLEY 1107MR235 | CASTRO VALLEY 1107 | 14091107 |  | 3.3154 | 2.786 |  | 59.5 | 0.00065292 | 3670 | 0.054416 | 7861 | 3.5071e-05 | 7003
MT EDEN 1103MR643 | MT EDEN 1103 | 13761103 |  | 6.256 | 5.9386 |  | 94 | 0.0006608 | 3567 | 0.053073 | 8251 | 3.507e-05 | 7004
MERCED 2101449613 | MERCED 2101 | 252802101 |  | 1.3391 | 1.3178 |  | 26 | 0.00063367 | 3894 | 0.056347 | 7521 | 3.507e-05 | 7005
MC KEE 1111XR132 | MC KEE 1111 | 83531111 |  | 3.4322 | 4.2074 |  | 54.6667 | 0.00064694 | 3743 | 0.054686 | 7808 | 3.5065e-05 | 7006
NOVATO 11041282 | NOVATO 1104 | 42211104 | TRUE | 3.7184 | 1.0463 | 0.0039092 | 78.5 | 0.00046468 | 5753 | 0.073513 | 4611 | 3.5064e-05 | 7007
LOCKEFORD 2101CB | LOCKEFORD 2101 | 163682101 |  | 5.6303 | 1.1238 |  | 96 | 0.00046523 | 5747 | 0.076074 | 4171 | 3.5063e-05 | 7008
LLAGAS 2106XR296 | LLAGAS 2106 | 83182106 |  | 1.7479 | 0.40399 |  | 32.5 | 0.0005399 | 4959 | 0.064963 | 6445 | 3.5043e-05 | 7009
DOLAN ROAD 1103CB | DOLAN ROAD 1103 | 182381103 |  | 3.4491 | 0.21324 |  | 65.8333 | 0.00053374 | 5029 | 0.065894 | 6292 | 3.504e-05 | 7010
PETALUMA C 1108594 | PETALUMA C 1108 | 42631108 |  | 5.6784 | 3.696 |  | 90.5 | 0.00057041 | 4655 | 0.061286 | 6857 | 3.5037e-05 | 7011
DALY CITY 0401CB | DALY CITY 0401 | 22640401 |  | 4.4931 | 3.1872 |  | 59.1667 | 0.00063336 | 3899 | 0.054756 | 7796 | 3.5031e-05 | 7012
TEVIS 21054116 | TEVIS 2105 | 255322105 |  | 0.65411 | 0 |  | 15.5 | 0.00060079 | 4289 | 0.061198 | 6868 | 3.5026e-05 | 7013
BAY MEADOWS 1105CB | BAY MEADOWS 1105 | 24011105 |  | 1.3677 | 1.1348 |  | 18.5 | 0.00065979 | 3580 | 0.053073 | 8250 | 3.5017e-05 | 7014
CORNING 110368304 | CORNING 1103 | 103331103 |  | 1.1814 | 0.25034 |  | 26.5 | 0.00053722 | 4989 | 0.0648 | 6463 | 3.501e-05 | 7015
LAS GALLINAS A 1106685852 | LAS GALLINAS A 1106 | 42991106 | TRUE | 0.13456 | 0 | 0.028955 | 1 | 0.00048645 | 5534 | 0.053073 | 8251 | 3.5007e-05 | 7016
MT EDEN 1112MR364 | MT EDEN 1112 | 13761112 |  | 1.4903 | 1.5241 |  | 22.5 | 0.00065949 | 3586 | 0.053073 | 8251 | 3.5001e-05 | 7017
RENFRO 21033351 | RENFRO 2103 | 254572103 |  | 2.717 | 1.0745 |  | 44.5 | 0.00057552 | 4584 | 0.061546 | 6822 | 3.4992e-05 | 7018
SF H 110810335 | SF H 1108 | 22101108 |  | 0.075828 | 0.18169 |  | 1.4167 | 0.00065917 | 3588 | 0.053073 | 8250 | 3.4984e-05 | 7019
LARKIN (Y) 1107CB | LARKIN (Y) 1107 | 22801107 |  | 0.98588 | 1.1038 |  | 12.8333 | 0.00065914 | 3590 | 0.053073 | 8250 | 3.4983e-05 | 7020
GRANT 1104CB | GRANT 1104 | 14381104 |  | 15.3363 | 15.788 |  | 227.75 | 0.00065911 | 3591 | 0.053073 | 8251 | 3.4981e-05 | 7021
RINCON 1103472 | RINCON 1103 | 43321103 | FALSE | 4.5403 | 1.9889 | 4.3043 | 78.3333 | 0.00054222 | 4932 | 0.064809 | 6462 | 3.4973e-05 | 7022
BAY MEADOWS 110339664 | BAY MEADOWS 1103 | 24011103 |  | 1.953 | 1.6939 |  | 31.6667 | 0.00059592 | 4349 | 0.058679 | 7201 | 3.4971e-05 | 7023
TEMPLETON 2110R02 | TEMPLETON 2110 | 183052110 |  | 0.6285 | 0.083011 |  | 9 | 0.00057136 | 4639 | 0.062148 | 6752 | 3.4962e-05 | 7024
OLIVEHURST 1101CB | OLIVEHURST 1101 | 152901101 |  | 8.3491 | 2.7585 |  | 130.5 | 0.00052667 | 5108 | 0.069088 | 5176 | 3.4959e-05 | 7025
HALF MOON BAY 11026097 | HALF MOON BAY 1102 | 24101102 |  | 2.1505 | 0.97366 |  | 36 | 0.00054687 | 4890 | 0.063589 | 6601 | 3.4958e-05 | 7026
HUNTERS POINT (P) 110513303 | HUNTERS POINT (P) 1105 | 22331105 |  | 3.2144 | 3.3398 |  | 53 | 0.00065851 | 3593 | 0.053073 | 8251 | 3.4949e-05 | 7027
LAWRENCE 1110CB | LAWRENCE 1110 | 83421110 |  | 4.8375 | 0.066432 |  | 60.8333 | 0.00064039 | 3819 | 0.055684 | 7643 | 3.4946e-05 | 7028
LODI 1102301436 | LODI 1102 | 162111102 |  | 4.6891 | 0.43697 |  | 84.3333 | 0.00059361 | 4372 | 0.063169 | 6647 | 3.4935e-05 | 7029
HILLSDALE 040198526 | HILLSDALE 0401 | 24110401 |  | 6.4938 | 5.1375 |  | 88.4167 | 0.00056073 | 4746 | 0.062274 | 6736 | 3.4928e-05 | 7030
WILSON 1101CB | WILSON 1101 | 254301101 |  | 10.3337 | 2.2426 |  | 192.3333 | 0.0004896 | 5501 | 0.072121 | 4766 | 3.4928e-05 | 7031
CASTRO VALLEY 1107MR336 | CASTRO VALLEY 1107 | 14091107 |  | 4.6814 | 4.7796 |  | 86.5 | 0.00059121 | 4400 | 0.059148 | 7140 | 3.4923e-05 | 7032
DUMBARTON 1110CB | DUMBARTON 1110 | 14471110 |  | 5.5537 | 5.3835 |  | 89 | 0.00065038 | 3705 | 0.054168 | 7911 | 3.4919e-05 | 7033
STOREY 11066330 | STOREY 1106 | 254611106 |  | 3.3424 | 2.61 |  | 51.1667 | 0.00065784 | 3600 | 0.053073 | 8251 | 3.4913e-05 | 7034
SANTA MARIA 1110M04 | SANTA MARIA 1110 | 182671110 |  | 0.7297 | 0.50123 |  | 10 | 0.00059819 | 4321 | 0.058644 | 7205 | 3.4908e-05 | 7035
WOODSIDE 1105CB | WOODSIDE 1105 | 24251105 |  | 4.2448 | 2.0157 |  | 88.5 | 0.00052518 | 5124 | 0.066579 | 6173 | 3.4906e-05 | 7036
OCEANO 1105V44 | OCEANO 1105 | 182601105 | FALSE | 1.0869 | 0.44267 | 0.74493 | 17.1667 | 0.00054427 | 4918 | 0.064701 | 6470 | 3.4904e-05 | 7037
MISSION (X) 111641380 | MISSION (X) 1116 | 22011116 |  | 1.925 | 2.4441 |  | 29.6667 | 0.0006576 | 3605 | 0.053073 | 8250 | 3.49e-05 | 7038
EL CERRITO G 1114CB | EL CERRITO G 1114 | 12501114 |  | 6.6391 | 3.4091 |  | 82.6667 | 0.00065518 | 3638 | 0.053297 | 8179 | 3.4881e-05 | 7039
VACA DIXON 1109CB | VACA DIXON 1109 | 63591109 |  | 1.8459 | 0 |  | 22.2333 | 0.00052714 | 5102 | 0.066484 | 6189 | 3.4879e-05 | 7040
HAMMER 11052943 | HAMMER 1105 | 163301105 |  | 1.0907 | 1.4232 |  | 18 | 0.00065706 | 3609 | 0.053073 | 8251 | 3.4872e-05 | 7041
MILLBRAE 110453676 | MILLBRAE 1104 | 22691104 |  | 3.1123 | 1.9556 |  | 51.1667 | 0.00053388 | 5026 | 0.065513 | 6356 | 3.4872e-05 | 7042
NAPA 111069632 | NAPA 1110 | 42021110 |  | 1.0492 | 0.74694 |  | 19.8333 | 0.00060194 | 4276 | 0.057342 | 7388 | 3.4872e-05 | 7043
PETALUMA A 0413CB | PETALUMA A 0413 | 42120413 |  | 2.3542 | 2.1792 |  | 38.5 | 0.00065696 | 3610 | 0.053073 | 8251 | 3.4866e-05 | 7044
PETALUMA C 11054238 | PETALUMA C 1105 | 42631105 |  | 1.3145 | 0.98822 |  | 23 | 0.00065695 | 3612 | 0.053073 | 8251 | 3.4866e-05 | 7045
HORSESHOE 110250022 | HORSESHOE 1102 | 152571102 |  | 4.1155 | 0.35729 |  | 68.5 | 0.0005201 | 5177 | 0.067036 | 5968 | 3.4866e-05 | 7046
ATWATER 110411850 | ATWATER 1104 | 253611104 |  | 4.6865 | 0.70289 |  | 91.5 | 0.00048243 | 5575 | 0.074264 | 4519 | 3.4864e-05 | 7047
LARKIN (Y) 1137CB | LARKIN (Y) 1137 | 22801137 |  | 0.0093364 | 0.11606 |  | 4.25 | 0.00065688 | 3615 | 0.053073 | 8251 | 3.4863e-05 | 7048
VINEYARD 2106MR274 | VINEYARD 2106 | 14502106 |  | 1.2103 | 0.4352 |  | 17.5 | 0.00061514 | 4102 | 0.056256 | 7540 | 3.4855e-05 | 7049
SF H 110877020 | SF H 1108 | 22101108 |  | 0.72711 | 0.88975 |  | 12.0333 | 0.00065662 | 3617 | 0.053073 | 8253 | 3.4849e-05 | 7050
GRAND ISLAND 22255902 | GRAND ISLAND 2225 | 62462225 |  | 12.6998 | 7.5678 |  | 208 | 0.00057593 | 4578 | 0.06279 | 6680 | 3.4844e-05 | 7051
VINEYARD 2109MR170 | VINEYARD 2109 | 14502109 |  | 4.4816 | 0.02424 |  | 65.5 | 0.00064231 | 3799 | 0.053817 | 7995 | 3.4844e-05 | 7052
DUMBARTON 1103MR369 | DUMBARTON 1103 | 14471103 |  | 0.94091 | 0.032731 |  | 17.5 | 0.00065653 | 3618 | 0.053073 | 8251 | 3.4844e-05 | 7053
NORTECH 2110XR036 | NORTECH 2110 | 82462110 |  | 0.57823 | 0 |  | 9 | 0.00051996 | 5179 | 0.067 | 6057 | 3.4837e-05 | 7054
ACTON 0401CB | ACTON 0401 | 22470401 |  | 3.8443 | 3.6155 |  | 47 | 0.00064467 | 3768 | 0.054762 | 7793 | 3.4833e-05 | 7055
LOGAN CREEK 2101CB | LOGAN CREEK 2101 | 103142101 |  | 9.2513 | 0.97473 |  | 158.3667 | 0.00050481 | 5336 | 0.070341 | 4973 | 3.4828e-05 | 7056
DIVIDE 11021385 | DIVIDE 1102 | 182571102 |  | 1.9457 | 1.5111 |  | 31 | 0.00051976 | 5183 | 0.067 | 6057 | 3.4824e-05 | 7057
LAWNDALE 0401CB | LAWNDALE 0401 | 22440401 |  | 4.7254 | 3.8873 |  | 62.3333 | 0.00062761 | 3979 | 0.055882 | 7599 | 3.4818e-05 | 7058
CASTRO VALLEY 1102MR518 | CASTRO VALLEY 1102 | 14091102 |  | 1.5602 | 0.85475 |  | 29.5 | 0.00052845 | 5093 | 0.065584 | 6345 | 3.4816e-05 | 7059
BECK STREET 0401CB | BECK STREET 0401 | 12640401 |  | 1.5796 | 1.4688 |  | 22.8667 | 0.00065596 | 3626 | 0.053073 | 8251 | 3.4814e-05 | 7060
VIERRA 170795714 | VIERRA 1707 | 162701707 |  | 2.4054 | 0.52391 |  | 38.8333 | 0.00051243 | 5262 | 0.069601 | 5100 | 3.4811e-05 | 7061
GRAND ISLAND 2224CB | GRAND ISLAND 2224 | 62462224 |  | 9.2157 | 0.62974 |  | 112.8667 | 0.00045464 | 5876 | 0.07669 | 3941 | 3.4797e-05 | 7062
MOUNTAIN VIEW 1108LV12 | MOUNTAIN VIEW 1108 | 82031108 |  | 8.2673 | 7.8714 |  | 116 | 0.00065565 | 3628 | 0.053073 | 8251 | 3.4797e-05 | 7063
MC KEE 1112CB | MC KEE 1112 | 83531112 |  | 8.3914 | 8.972 |  | 108.8333 | 0.00065555 | 3630 | 0.053073 | 8251 | 3.4792e-05 | 7064
SWIFT 2111CB | SWIFT 2111 | 83392111 |  | 4.288 | 4.8729 |  | 59.6667 | 0.00064245 | 3795 | 0.054462 | 7850 | 3.4787e-05 | 7065
STOREY 1105CB | STOREY 1105 | 254611105 |  | 7.936 | 2.1071 |  | 146.25 | 0.0004753 | 5643 | 0.074166 | 4532 | 3.4786e-05 | 7066
HIGHWAY 110492586 | HIGHWAY 1104 | 42651104 |  | 1.6535 | 0.99894 |  | 23.3333 | 0.00061906 | 4059 | 0.05524 | 7712 | 3.4783e-05 | 7067
EDENVALE 1101CB | EDENVALE 1101 | 82951101 |  | 6.4637 | 8.7183 |  | 97.1667 | 0.00065528 | 3635 | 0.053073 | 8250 | 3.4778e-05 | 7068
EDES 1111CB | EDES 1111 | 13681111 |  | 3.3433 | 2.881 |  | 58.8333 | 0.00065527 | 3636 | 0.053073 | 8251 | 3.4777e-05 | 7069
HIGHWAY 1102CB | HIGHWAY 1102 | 42651102 |  | 2.8645 | 0.65957 |  | 49 | 0.00056341 | 4723 | 0.061679 | 6802 | 3.4769e-05 | 7070
IGNACIO 11041274 | IGNACIO 1104 | 42481104 |  | 1.3655 | 0 |  | 28 | 0.00051573 | 5220 | 0.067449 | 5636 | 3.4765e-05 | 7071
EAST GRAND 1101250170 | EAST GRAND 1101 | 22571101 |  | 5.0389 | 4.3417 |  | 80.4167 | 0.00063682 | 3858 | 0.055288 | 7709 | 3.4763e-05 | 7072
LAKEWOOD 2223W532R | LAKEWOOD 2223 | 13532223 |  | 0.22698 | 0.15678 |  | 3.3333 | 0.00063342 | 3898 | 0.055162 | 7730 | 3.4744e-05 | 7073
NAPA 111289474 | NAPA 1112 | 42021112 |  | 1.2976 | 0.54301 |  | 29 | 0.00059577 | 4351 | 0.059795 | 7041 | 3.4741e-05 | 7074
PANAMA 210165480 | PANAMA 2101 | 253422101 |  | 7.6975 | 3.743 |  | 129 | 0.00056215 | 4733 | 0.064316 | 6506 | 3.4741e-05 | 7075
MC KEE 1112XR256 | MC KEE 1112 | 83531112 |  | 2.2812 | 2.8724 |  | 34.1667 | 0.00065195 | 3686 | 0.053209 | 8214 | 3.474e-05 | 7076
GREEN VALLEY 210112106 | GREEN VALLEY 2101 | 83192101 | TRUE | 12.1573 | 2.1297 | 0.2561 | 205 | 0.00039749 | 6483 | 0.10377 | 3307 | 3.4737e-05 | 7077
SALINAS 1105CB | SALINAS 1105 | 182011105 |  | 7.3054 | 6.6622 |  | 113.3333 | 0.00062031 | 4045 | 0.055807 | 7614 | 3.4734e-05 | 7078
SF L 110369372 | SF L 1103 | 22261103 |  | 1.8436 | 2.3792 |  | 25.5 | 0.00065417 | 3651 | 0.053073 | 8251 | 3.4718e-05 | 7079
WALDO 0401CB | WALDO 0401 | 13350401 | TRUE | 4.0456 | 5.0195 | 0.063297 | 43.85 | 0.00065415 | 3652 | 0.053073 | 8254 | 3.4717e-05 | 7080
MORGAN HILL 2106XR324 | MORGAN HILL 2106 | 83242106 |  | 1.4086 | 0.2618 |  | 30 | 0.00053343 | 5035 | 0.065078 | 6420 | 3.4717e-05 | 7081
MC KEE 1103CB | MC KEE 1103 | 83531103 |  | 11.5598 | 12.1958 |  | 185.6667 | 0.0006469 | 3744 | 0.054003 | 7950 | 3.4717e-05 | 7082
DEL MONTE 210547700 | DEL MONTE 2105 | 182222105 |  | 0.17113 | 0.10614 |  | 4.5 | 0.00065413 | 3653 | 0.053073 | 8251 | 3.4716e-05 | 7083
VALLEY VIEW 1106P182 | VALLEY VIEW 1106 | 14341106 |  | 2.4192 | 2.8114 |  | 39 | 0.00062538 | 3992 | 0.056639 | 7483 | 3.4715e-05 | 7084
LLAGAS 2104524360 | LLAGAS 2104 | 83182104 |  | 1.8493 | 0.039931 |  | 31 | 0.00048106 | 5591 | 0.07232 | 4742 | 3.4712e-05 | 7085
HAMILTON A 1102CB | HAMILTON A 1102 | 102121102 |  | 2.3631 | 1.9281 |  | 48 | 0.0005663 | 4697 | 0.06199 | 6765 | 3.4711e-05 | 7086
SOTO 0401CB | SOTO 0401 | 13260401 |  | 4.0857 | 5.1155 |  | 66.5 | 0.0006539 | 3658 | 0.053073 | 8251 | 3.4704e-05 | 7087
MENLO 11039096 | MENLO 1103 | 24131103 |  | 2.2339 | 0.03348 |  | 36.8333 | 0.00051783 | 5195 | 0.067004 | 6036 | 3.4696e-05 | 7088
MILLBRAE 11018944 | MILLBRAE 1101 | 22691101 |  | 1.2987 | 0.21579 |  | 21.3333 | 0.00065372 | 3660 | 0.053073 | 8251 | 3.4694e-05 | 7089
HALF MOON BAY 11019014 | HALF MOON BAY 1101 | 24101101 |  | 1.8073 | 0.57304 |  | 31.8333 | 0.00057611 | 4575 | 0.060113 | 7004 | 3.469e-05 | 7090
OAKLAND X 1107CR426 | OAKLAND X 1107 | 12541107 |  | 2.6808 | 3.4235 |  | 46.8333 | 0.00057966 | 4526 | 0.060507 | 6957 | 3.4684e-05 | 7091
HALF MOON BAY 11022032 | HALF MOON BAY 1102 | 24101102 | TRUE | 9.537 | 4.358 | 0.44716 | 152.1667 | 0.00052773 | 5097 | 0.065112 | 6416 | 3.4682e-05 | 7092
DUMBARTON 1109MR241 | DUMBARTON 1109 | 14471109 |  | 1.4118 | 0.91805 |  | 21 | 0.00065348 | 3663 | 0.053073 | 8251 | 3.4682e-05 | 7093
FAIRMOUNT 0402CB | FAIRMOUNT 0402 | 12650402 |  | 5.0723 | 6.3139 |  | 57.5833 | 0.00065347 | 3664 | 0.053073 | 8255 | 3.4682e-05 | 7094
STELLING 1108CB | STELLING 1108 | 83481108 |  | 5.8315 | 6.4381 |  | 82.6667 | 0.00065331 | 3666 | 0.053073 | 8250 | 3.4673e-05 | 7095
ALMADEN 1102685706 | ALMADEN 1102 | 82311102 |  | 2.0771 | 1.7342 |  | 28.8333 | 0.0006533 | 3667 | 0.053073 | 8252 | 3.4673e-05 | 7096
GRANT 1108MR354 | GRANT 1108 | 14381108 |  | 4.8448 | 5.437 |  | 85.6667 | 0.00064548 | 3759 | 0.053641 | 8050 | 3.4667e-05 | 7097
FAIRVIEW 22078275 | FAIRVIEW 2207 | 13432207 |  | 1.8261 | 0.78185 |  | 33.5 | 0.00051713 | 5202 | 0.067017 | 6007 | 3.4656e-05 | 7098
RAINBOW 1105508780 | RAINBOW 1105 | 254441105 |  | 1.9319 | 1.3802 |  | 32.5 | 0.00062862 | 3957 | 0.057345 | 7386 | 3.4654e-05 | 7099
HICKS 1115CB | HICKS 1115 | 83431115 |  | 12.8161 | 12.6585 |  | 167.9833 | 0.00065227 | 3681 | 0.053114 | 8245 | 3.4651e-05 | 7100
ATWATER 11039640 | ATWATER 1103 | 253611103 |  | 0.7662 | 0.49855 |  | 12 | 0.00052445 | 5133 | 0.066608 | 6166 | 3.4649e-05 | 7101
SF K 1101CB | SF K 1101 | 22131101 |  | 1.4473 | 2.3106 |  | 20.5833 | 0.00064394 | 3777 | 0.053664 | 8043 | 3.4646e-05 | 7102
VALLEY VIEW 1106CB | VALLEY VIEW 1106 | 14341106 |  | 0.50084 | 0.11485 |  | 12.1667 | 0.00052483 | 5129 | 0.065474 | 6366 | 3.4646e-05 | 7103
DALY CITY 110277934 | DALY CITY 1102 | 22641102 |  | 2.9777 | 3.0006 |  | 67 | 0.00059529 | 4356 | 0.058585 | 7212 | 3.4641e-05 | 7104
LAS POSITAS 2109CB | LAS POSITAS 2109 | 14402109 |  | 2.5486 | 1.8622 |  | 42.5 | 0.00065157 | 3688 | 0.053275 | 8187 | 3.4635e-05 | 7105
HIGHWAY 1106CB | HIGHWAY 1106 | 42651106 |  | 12.1903 | 7.463 |  | 184.6667 | 0.0006367 | 3859 | 0.054374 | 7871 | 3.4635e-05 | 7106
SF H 110268336 | SF H 1102 | 22101102 |  | 0.84048 | 1.0703 |  | 10.3333 | 0.00065235 | 3678 | 0.053073 | 8250 | 3.4622e-05 | 7107
HIGHWAY 11062105 | HIGHWAY 1106 | 42651106 |  | 3.1114 | 2.923 |  | 43.3333 | 0.00065223 | 3682 | 0.053073 | 8251 | 3.4616e-05 | 7108
LOS OSITOS 2103174580 | LOS OSITOS 2103 | 182082103 |  | 4.174 | 0.36342 |  | 84.5 | 0.00051601 | 5214 | 0.067123 | 5880 | 3.461e-05 | 7109
SANTA ROSA A 1102336 | SANTA ROSA A 1102 | 42151102 |  | 1.8178 | 1.6577 |  | 39.5 | 0.00065212 | 3683 | 0.053073 | 8251 | 3.461e-05 | 7110
MT EDEN 1105CB | MT EDEN 1105 | 13761105 |  | 6.8379 | 6.7027 |  | 103.5333 | 0.00064714 | 3740 | 0.053543 | 8087 | 3.4598e-05 | 7111
JESSUP 110238330 | JESSUP 1102 | 103441102 |  | 2.2237 | 0.59237 |  | 43.5 | 0.00050715 | 5314 | 0.068432 | 5300 | 3.4594e-05 | 7112
ARANA 0401CB | ARANA 0401 | 83010401 |  | 3.3929 | 3.2306 |  | 52.6667 | 0.00063015 | 3942 | 0.05489 | 7769 | 3.459e-05 | 7113
CASTRO VALLEY 1102960346 | CASTRO VALLEY 1102 | 14091102 |  | 0.17082 | 0.093274 |  | 3.5 | 0.00049584 | 5436 | 0.067 | 6057 | 3.4577e-05 | 7114
EAST GRAND 1113CB | EAST GRAND 1113 | 22571113 |  | 0.38734 | 0.028638 |  | 7.5 | 0.00065149 | 3689 | 0.053073 | 8251 | 3.4576e-05 | 7115
CLAYTON 1104C550R | CLAYTON 1104 | 12021104 |  | 4.6496 | 4.8116 |  | 67.5 | 0.00062862 | 3958 | 0.055651 | 7649 | 3.4574e-05 | 7116
RESERVE OIL 1101CB | RESERVE OIL 1101 | 254181101 |  | 2.1945 | 0.0055602 |  | 37.5 | 0.00046136 | 5793 | 0.074615 | 4472 | 3.4559e-05 | 7117
VINEYARD 2107MR801 | VINEYARD 2107 | 14502107 |  | 0.0036163 | 0 |  | 0.33333 | 0.00065101 | 3699 | 0.053073 | 8251 | 3.4551e-05 | 7118
KINGSBURG 11146760 | KINGSBURG 1114 | 252241114 |  | 3.3661 | 0.82985 |  | 56 | 0.0005544 | 4824 | 0.065761 | 6311 | 3.455e-05 | 7119
HUMBOLDT BAY 11027598 | HUMBOLDT BAY 1102 | 192341102 |  | 5.5669 | 3.5271 |  | 100.5 | 0.00053201 | 5050 | 0.065057 | 6424 | 3.4545e-05 | 7120
BERKELEY F 1105189500 | BERKELEY F 1105 | 12061105 | FALSE | 1.0614 | 1.2494 | 1.269 | 18.3333 | 0.00054428 | 4917 | 0.064152 | 6523 | 3.4536e-05 | 7121
RIPON 170213544 | RIPON 1702 | 163801702 |  | 5.5685 | 3.5737 |  | 99 | 0.00064433 | 3773 | 0.053645 | 8048 | 3.4534e-05 | 7122
LLAGAS 2104XR148 | LLAGAS 2104 | 83182104 |  | 19.3549 | 0.47333 |  | 352 | 0.00051456 | 5240 | 0.067581 | 5562 | 3.4534e-05 | 7123
DAIRYLAND 110293892 | DAIRYLAND 1102 | 252421102 |  | 0.17298 | 0.034839 |  | 3 | 0.00044617 | 5950 | 0.0774 | 3397 | 3.4534e-05 | 7124
GRAND ISLAND 222550300 | GRAND ISLAND 2225 | 62462225 |  | 2.9454 | 1.9395 |  | 49.5 | 0.00055058 | 4856 | 0.063504 | 6613 | 3.4532e-05 | 7125
NORTH TOWER 1103CB | NORTH TOWER 1103 | 42041103 |  | 13.0325 | 10.8174 |  | 141.7833 | 0.00061942 | 4055 | 0.055859 | 7600 | 3.453e-05 | 7126
RICHMOND R 1130BR144 | RICHMOND R 1130 | 13471130 |  | 2.8937 | 3.0243 |  | 34.5833 | 0.0006506 | 3702 | 0.053073 | 8252 | 3.4529e-05 | 7127
PENNGROVE 11013476 | PENNGROVE 1101 | 43471101 |  | 3.8223 | 1.018 |  | 63 | 0.00051922 | 5186 | 0.066937 | 6082 | 3.4521e-05 | 7128
BUELLTON 1102Y20 | BUELLTON 1102 | 183041102 |  | 1.7277 | 0.61543 |  | 27.5 | 0.00053017 | 5073 | 0.065231 | 6402 | 3.4512e-05 | 7129
PRUNEDALE 1110CB | PRUNEDALE 1110 | 182961110 |  | 7.6668 | 3.301 |  | 137.5 | 0.00051544 | 5226 | 0.066874 | 6101 | 3.451e-05 | 7130
PETALUMA C 1108CB | PETALUMA C 1108 | 42631108 |  | 11.122 | 9.0525 |  | 198 | 0.0005877 | 4447 | 0.060671 | 6931 | 3.4506e-05 | 7131
GREENBRAE 11037315 | GREENBRAE 1103 | 43091103 |  | 2.2417 | 2.3629 |  | 37.8333 | 0.00063909 | 3838 | 0.053995 | 7954 | 3.45e-05 | 7132
STUART 0401CB | STUART 0401 | 13840401 |  | 2.9385 | 3.6921 |  | 36.9167 | 0.00064988 | 3707 | 0.053073 | 8251 | 3.4491e-05 | 7133
NORTH TOWER 110291736 | NORTH TOWER 1102 | 42041102 |  | 0.54942 | 0.1534 |  | 6.2 | 0.00053247 | 5043 | 0.063279 | 6630 | 3.4476e-05 | 7134
JARVIS 1112MR238 | JARVIS 1112 | 13501112 |  | 3.1802 | 2.354 |  | 56.5 | 0.00064951 | 3713 | 0.053073 | 8251 | 3.4471e-05 | 7135
FREMONT 1107MR110 | FREMONT 1107 | 14351107 |  | 1.3031 | 1.3714 |  | 17.3333 | 0.0006495 | 3714 | 0.053073 | 8252 | 3.4471e-05 | 7136
SANTA MARIA 1106M112 | SANTA MARIA 1106 | 182671106 |  | 12.635 | 12.8991 |  | 194.3333 | 0.00064187 | 3805 | 0.053981 | 7958 | 3.4468e-05 | 7137
MILLBRAE 040376176 | MILLBRAE 0403 | 22690403 |  | 3.4145 | 2.8621 |  | 50.8333 | 0.00061094 | 4154 | 0.056425 | 7511 | 3.4463e-05 | 7138
BERKELEY F 0404CB | BERKELEY F 0404 | 12060404 |  | 3.6802 | 4.8434 |  | 51.5 | 0.00064923 | 3716 | 0.053073 | 8252 | 3.4456e-05 | 7139
SF H 110713525 | SF H 1107 | 22101107 |  | 2.6007 | 4.2866 |  | 42.1667 | 0.00064895 | 3719 | 0.053073 | 8251 | 3.4442e-05 | 7140
TEMPLETON 2113A24 | TEMPLETON 2113 | 183052113 |  | 0.93549 | 0.11191 |  | 19.5 | 0.00051124 | 5274 | 0.067512 | 5593 | 3.4424e-05 | 7141
SF H 110514741 | SF H 1105 | 22101105 |  | 2.2098 | 2.8369 |  | 40.4167 | 0.00064851 | 3723 | 0.053073 | 8251 | 3.4418e-05 | 7142
SANTA ROSA A 1102622 | SANTA ROSA A 1102 | 42151102 |  | 1.4398 | 1.0203 |  | 33 | 0.00056849 | 4674 | 0.060771 | 6921 | 3.4415e-05 | 7143
EL PATIO 1107XR532 | EL PATIO 1107 | 82921107 |  | 3.2444 | 2.895 |  | 45 | 0.00064827 | 3725 | 0.053073 | 8251 | 3.4405e-05 | 7144
SAN BRUNO 040265746 | SAN BRUNO 0402 | 22700402 |  | 1.6183 | 1.2822 |  | 21.3333 | 0.00064826 | 3726 | 0.053073 | 8251 | 3.4405e-05 | 7145
GLENN 110133450 | GLENN 1101 | 102601101 |  | 5.596 | 1.268 |  | 89.5 | 0.00053763 | 4983 | 0.064541 | 6482 | 3.4401e-05 | 7146
EUREKA E 1101CB | EUREKA E 1101 | 192331101 |  | 6.6468 | 6.2537 |  | 90.4167 | 0.00064216 | 3801 | 0.053573 | 8071 | 3.4393e-05 | 7147
VIEJO 220298146 | VIEJO 2202 | 182852202 |  | 2.2307 | 2.4119 |  | 33 | 0.00064798 | 3729 | 0.053073 | 8251 | 3.439e-05 | 7148
NAPA 1110944 | NAPA 1110 | 42021110 |  | 3.2512 | 1.4157 |  | 56.5 | 0.00053101 | 5059 | 0.064917 | 6449 | 3.4388e-05 | 7149
BELLE HAVEN 0407CB | BELLE HAVEN 0407 | 24020407 |  | 6.1383 | 5.3087 |  | 93.9167 | 0.00056923 | 4670 | 0.061135 | 6880 | 3.4388e-05 | 7150
AMES 1102CB | AMES 1102 | 83901102 |  | 2.4357 | 0.65802 |  | 30.6667 | 0.00055396 | 4828 | 0.06247 | 6720 | 3.4381e-05 | 7151
BEACH (Q) 0402CB | BEACH (Q) 0402 | 22340402 |  | 2.0354 | 1.6512 |  | 24.75 | 0.00064781 | 3732 | 0.053073 | 8249 | 3.4381e-05 | 7152
FAIRHAVEN 110353174 | FAIRHAVEN 1103 | 192451103 |  | 5.0707 | 3.6079 |  | 101.5 | 0.0005291 | 5084 | 0.065161 | 6411 | 3.4378e-05 | 7153
MISSION (X) 112441340 | MISSION (X) 1124 | 22011124 |  | 0.63124 | 0.84012 |  | 12.3333 | 0.00064771 | 3734 | 0.053073 | 8251 | 3.4376e-05 | 7154
EDENVALE 1101XR184 | EDENVALE 1101 | 82951101 |  | 3.2159 | 3.6861 |  | 48.8333 | 0.00064765 | 3735 | 0.053073 | 8250 | 3.4372e-05 | 7155
SANTA ROSA A 1106300 | SANTA ROSA A 1106 | 42151106 |  | 2.153 | 0.99692 |  | 38.8333 | 0.00057245 | 4624 | 0.060246 | 6990 | 3.4371e-05 | 7156
CASTROVILLE 210399672 | CASTROVILLE 2103 | 182352103 |  | 3.6936 | 0.36221 |  | 73 | 0.00051216 | 5264 | 0.067094 | 5907 | 3.4355e-05 | 7157
SAN LUIS OBISPO 1102V98 | SAN LUIS OBISPO 1102 | 182631102 |  | 1.1805 | 0.7711 |  | 18 | 0.00064713 | 3741 | 0.053073 | 8251 | 3.4345e-05 | 7158
EUREKA E 11017104 | EUREKA E 1101 | 192331101 |  | 6.6441 | 4.7726 |  | 98.8333 | 0.00059763 | 4329 | 0.05804 | 7287 | 3.4344e-05 | 7159
SF N 1101CB | SF N 1101 | 22281101 |  | 0.2745 | 0.39274 |  | 7.75 | 0.00060386 | 4257 | 0.059351 | 7104 | 3.4343e-05 | 7160
SAN CARLOS 1103195306 | SAN CARLOS 1103 | 24181103 |  | 4.7165 | 4.5737 |  | 83.4167 | 0.00064686 | 3745 | 0.053073 | 8251 | 3.4331e-05 | 7161
LAWRENCE 110455186 | LAWRENCE 1104 | 83421104 |  | 4.8696 | 7.3506 |  | 76.5 | 0.0006468 | 3746 | 0.053073 | 8251 | 3.4328e-05 | 7162
UKIAH 1114CB | UKIAH 1114 | 42771114 |  | 5.0113 | 0.29226 |  | 85.25 | 0.00051061 | 5279 | 0.067213 | 5796 | 3.4325e-05 | 7163
BARRETT 0402CB | BARRETT 0402 | 13020402 |  | 5.8929 | 7.0914 |  | 74.3333 | 0.00064662 | 3747 | 0.053073 | 8251 | 3.4318e-05 | 7164
VALLEY VIEW 1105P124 | VALLEY VIEW 1105 | 14341105 |  | 3.15 | 3.3162 |  | 48.3333 | 0.00055323 | 4831 | 0.060997 | 6892 | 3.4315e-05 | 7165
PLUMAS 1101618170 | PLUMAS 1101 | 153731101 |  | 0.021815 | 0 |  | 0.5 | 0.00044312 | 5984 | 0.0774 | 3397 | 3.4297e-05 | 7166
KETTLEMAN HILLS 210464373 | KETTLEMAN HILLS 2104 | 252732104 |  | 5.1605 | 4.6057 |  | 82 | 0.00055821 | 4776 | 0.061673 | 6805 | 3.4291e-05 | 7167
SAN CARLOS 04039012 | SAN CARLOS 0403 | 24180403 |  | 1.6175 | 1.3901 |  | 22.6667 | 0.00064602 | 3755 | 0.053073 | 8250 | 3.4286e-05 | 7168
SCHINDLER 1108CB | SCHINDLER 1108 | 252891108 |  | 2.3098 | 0 |  | 15.1167 | 0.00044608 | 5951 | 0.077053 | 3731 | 3.4278e-05 | 7169
MORMON 1102465508 | MORMON 1102 | 163211102 |  | 0.039456 | 0 |  | 0.66667 | 0.00044267 | 5988 | 0.0774 | 3396 | 3.4263e-05 | 7170
OAKLAND X 1109CR126 | OAKLAND X 1109 | 12541109 |  | 1.844 | 2.6572 |  | 30.1667 | 0.00064542 | 3760 | 0.053073 | 8250 | 3.4254e-05 | 7171
HIGHWAY 110181590 | HIGHWAY 1101 | 42651101 |  | 0.69449 | 0.184 |  | 13 | 0.00064538 | 3761 | 0.053073 | 8251 | 3.4252e-05 | 7172
TULUCAY 1101684 | TULUCAY 1101 | 42301101 |  | 1.2099 | 0.016941 |  | 20.5 | 0.00055614 | 4802 | 0.061732 | 6794 | 3.4231e-05 | 7173
HONCUT 110255206 | HONCUT 1102 | 103211102 |  | 2.6007 | 0.43638 |  | 48.5 | 0.00019373 | 10148 | 0.25013 | 3082 | 3.4231e-05 | 7174
VASCO 1102CB | VASCO 1102 | 13751102 |  | 7.9816 | 3.2684 |  | 127.3333 | 0.00055251 | 4843 | 0.063015 | 6661 | 3.4221e-05 | 7175
VACA DIXON 1106CB | VACA DIXON 1106 | 63591106 |  | 7.1676 | 1.5076 |  | 131.6667 | 0.00051948 | 5185 | 0.066376 | 6209 | 3.4221e-05 | 7176
TULUCAY 1101323426 | TULUCAY 1101 | 42301101 |  | 0.14173 | 0 |  | 2.5 | 0.00050957 | 5289 | 0.06714 | 5862 | 3.4213e-05 | 7177
CORDELIA 1112CB | CORDELIA 1112 | 62701112 |  | 8.5615 | 0.78671 |  | 146.5333 | 0.00050849 | 5302 | 0.067244 | 5768 | 3.4211e-05 | 7178
OAKLAND J 1105CR132 | OAKLAND J 1105 | 12091105 |  | 4.5372 | 4.8561 |  | 67.6667 | 0.00058287 | 4492 | 0.059289 | 7113 | 3.4208e-05 | 7179
CANAL 1106CB | CANAL 1106 | 252091106 |  | 2.9073 | 0.77931 |  | 45.8333 | 0.00057684 | 4562 | 0.06194 | 6768 | 3.4207e-05 | 7180
RICHMOND Q 0402895422 | RICHMOND Q 0402 | 12520402 |  | 3.6083 | 3.873 |  | 44.6667 | 0.00064448 | 3772 | 0.053073 | 8252 | 3.4204e-05 | 7181
PEABODY 2112CB | PEABODY 2112 | 63642112 |  | 3.1031 | 0 |  | 60.0833 | 0.00053202 | 5049 | 0.065252 | 6399 | 3.4201e-05 | 7182
KINGSBURG 110281042 | KINGSBURG 1102 | 252241102 |  | 6.9205 | 3.9628 |  | 115.8333 | 0.00059001 | 4413 | 0.059775 | 7044 | 3.4181e-05 | 7183
WOOD 0401CB | WOOD 0401 | 13380401 |  | 3.3158 | 3.9543 |  | 68 | 0.00043906 | 6020 | 0.07585 | 4247 | 3.4176e-05 | 7184
SAN CARLOS 0403CB | SAN CARLOS 0403 | 24180403 |  | 5.2872 | 4.8404 |  | 66.4262 | 0.00064361 | 3779 | 0.053073 | 8252 | 3.4158e-05 | 7185
FULTON 1105CB | FULTON 1105 | 42561105 |  | 11.9762 | 2.7136 |  | 207 | 0.00051287 | 5256 | 0.066961 | 6078 | 3.4151e-05 | 7186
PAUL SWEET 210166806 | PAUL SWEET 2101 | 83252101 |  | 5.8719 | 4.2969 |  | 79 | 0.00062237 | 4021 | 0.054718 | 7801 | 3.4143e-05 | 7187
SCHINDLER 1107CB | SCHINDLER 1107 | 252891107 |  | 1.4289 | 0 |  | 8.7833 | 0.00044099 | 6001 | 0.0774 | 3396 | 3.4133e-05 | 7188
SF H 11086563 | SF H 1108 | 22101108 |  | 2.8443 | 4.845 |  | 50.5 | 0.00062491 | 3998 | 0.054518 | 7842 | 3.4124e-05 | 7189
BELLEVUE 1102463316 | BELLEVUE 1102 | 43181102 | TRUE | 6.4165 | 0.86295 | 0.32634 | 113 | 0.00035468 | 7059 | 0.086263 | 3362 | 3.4122e-05 | 7190
CASTROVILLE 210322156 | CASTROVILLE 2103 | 182352103 |  | 1.7106 | 0.026128 |  | 32 | 0.00050922 | 5294 | 0.067 | 6057 | 3.4118e-05 | 7191
MOUNTAIN VIEW 1109CB | MOUNTAIN VIEW 1109 | 82031109 |  | 8.4435 | 5.1044 |  | 120.5 | 0.00058421 | 4482 | 0.058389 | 7235 | 3.4108e-05 | 7192
GONZALES 1103684642 | GONZALES 1103 | 182131103 |  | 1.2629 | 0.19448 |  | 19.8333 | 0.00051978 | 5182 | 0.065596 | 6342 | 3.4106e-05 | 7193
PIERCY 2109906172 | PIERCY 2109 | 83912109 |  | 2.2454 | 2.1132 |  | 33.6667 | 0.00061654 | 4095 | 0.055417 | 7685 | 3.4098e-05 | 7194
WOLFE 1107CB | WOLFE 1107 | 83671107 |  | 10.638 | 10.5269 |  | 151.8333 | 0.00064243 | 3796 | 0.053073 | 8251 | 3.4095e-05 | 7195
EUREKA A 1103CB | EUREKA A 1103 | 192121103 |  | 10.4212 | 9.4745 |  | 147.25 | 0.00059915 | 4309 | 0.057836 | 7321 | 3.4095e-05 | 7196
PARKWAY 1103652 | PARKWAY 1103 | 42051103 |  | 0.046163 | 0 |  | 2.5 | 0.00064233 | 3798 | 0.053073 | 8251 | 3.409e-05 | 7197
SALINAS 1104895672 | SALINAS 1104 | 182011104 |  | 2.483 | 2.1479 |  | 33.75 | 0.00064229 | 3800 | 0.053073 | 8251 | 3.4088e-05 | 7198
MC KEE 1104CB | MC KEE 1104 | 83531104 |  | 8.5611 | 9.1206 |  | 130.3333 | 0.0006421 | 3802 | 0.053073 | 8252 | 3.4078e-05 | 7199
MC CALL 1103CB | MC CALL 1103 | 254121103 |  | 11.7935 | 4.1991 |  | 202.1167 | 0.00052404 | 5140 | 0.067941 | 5418 | 3.4072e-05 | 7200
LOCKEFORD 210137600 | LOCKEFORD 2101 | 163682101 |  | 10.8089 | 2.106 |  | 194 | 0.00044952 | 5922 | 0.076316 | 4084 | 3.4071e-05 | 7201
WINDSOR 1103CB | WINDSOR 1103 | 43501103 |  | 5.4886 | 0.75887 |  | 106.8333 | 0.00052296 | 5151 | 0.065531 | 6354 | 3.4069e-05 | 7202
MERCED 1116CB | MERCED 1116 | 252801116 |  | 13.1427 | 4.6406 |  | 235 | 0.00050921 | 5295 | 0.069808 | 5074 | 3.4064e-05 | 7203
LAMONT 1104CB | LAMONT 1104 | 253911104 |  | 9.2344 | 0.4565 |  | 155.2 | 0.00044824 | 5932 | 0.075994 | 4201 | 3.406e-05 | 7204
PANAMA 21011400 | PANAMA 2101 | 253422101 |  | 6.0223 | 1.405 |  | 99 | 0.00046657 | 5734 | 0.074394 | 4505 | 3.4046e-05 | 7205
GLENWOOD 110168889 | GLENWOOD 1101 | 24091101 |  | 2.0556 | 0.76755 |  | 27.3333 | 0.00059358 | 4374 | 0.057993 | 7291 | 3.4043e-05 | 7206
DAIRYLAND 11055990 | DAIRYLAND 1105 | 252421105 |  | 4.316 | 0.17945 |  | 72.5 | 0.00043977 | 6014 | 0.0774 | 3397 | 3.4038e-05 | 7207
MANTECA 170114588 | MANTECA 1701 | 162611701 |  | 2.2202 | 0.46731 |  | 37.5 | 0.00053397 | 5023 | 0.066411 | 6204 | 3.4036e-05 | 7208
PEASE 1101CB | PEASE 1101 | 153751101 |  | 4.5943 | 0.62695 |  | 76 | 0.00052488 | 5128 | 0.068127 | 5378 | 3.4032e-05 | 7209
PAUL SWEET 210216008 | PAUL SWEET 2102 | 83252102 |  | 5.8902 | 5.3014 |  | 85.6667 | 0.00058912 | 4425 | 0.058057 | 7282 | 3.4031e-05 | 7210
GRANT 1105MR362 | GRANT 1105 | 14381105 |  | 3.4107 | 3.9609 |  | 49.6667 | 0.00064112 | 3812 | 0.053073 | 8251 | 3.4026e-05 | 7211
EDENVALE 2111CB | EDENVALE 2111 | 82952111 |  | 0.43305 | 0.0125 |  | 11.5 | 0.0005964 | 4344 | 0.058634 | 7207 | 3.4014e-05 | 7212
GOLDTREE 1105588830 | GOLDTREE 1105 | 182581105 |  | 1.6769 | 0.58688 |  | 17.5 | 0.00062771 | 3977 | 0.054664 | 7811 | 3.4006e-05 | 7213
WOODWARD 2101R1210 | WOODWARD 2101 | 255292101 |  | 4.9791 | 0.24559 |  | 87.3333 | 0.0004819 | 5583 | 0.070573 | 4945 | 3.3999e-05 | 7214
CANAL 1105CB | CANAL 1105 | 252091105 |  | 1.5444 | 0.79173 |  | 22 | 0.00064056 | 3817 | 0.053073 | 8250 | 3.3996e-05 | 7215
NORTH TOWER 11028964 | NORTH TOWER 1102 | 42041102 |  | 4.1411 | 3.6658 |  | 65.3333 | 0.00060289 | 4268 | 0.056308 | 7529 | 3.3986e-05 | 7216
FITCH MOUNTAIN 1113406 | FITCH MOUNTAIN 1113 | 42751113 |  | 6.3446 | 0.87459 |  | 115 | 0.00051505 | 5234 | 0.066048 | 6261 | 3.3974e-05 | 7217
MILPITAS 110913377 | MILPITAS 1109 | 82831109 |  | 0.48588 | 0.4637 |  | 9.8333 | 0.00064 | 3824 | 0.053073 | 8250 | 3.3967e-05 | 7218
SAN LEANDRO U 1108MR566 | SAN LEANDRO U 1108 | 13111108 |  | 3.6045 | 2.9404 |  | 45.6667 | 0.00063997 | 3826 | 0.053073 | 8251 | 3.3965e-05 | 7219
LAMONT 11064784 | LAMONT 1106 | 253911106 |  | 1.8299 | 0.011939 |  | 31.1667 | 0.00045091 | 5912 | 0.075304 | 4365 | 3.3965e-05 | 7220
EIGHT MILE 2104CB | EIGHT MILE 2104 | 163912104 |  | 1.3622 | 1.2836 |  | 35 | 0.00063988 | 3828 | 0.053073 | 8251 | 3.396e-05 | 7221
SALINAS 110322384 | SALINAS 1103 | 182011103 |  | 1.3928 | 1.4826 |  | 24.3333 | 0.00063669 | 3860 | 0.053359 | 8150 | 3.3951e-05 | 7222
GRANT 1106MR664 | GRANT 1106 | 14381106 |  | 6.3608 | 6.778 |  | 120 | 0.00063912 | 3836 | 0.053131 | 8238 | 3.3949e-05 | 7223
HUMBOLDT BAY 1101CB | HUMBOLDT BAY 1101 | 192341101 |  | 11.885 | 4.0926 |  | 214 | 0.00052327 | 5150 | 0.065112 | 6415 | 3.3946e-05 | 7224
STELLING 1104LC120 | STELLING 1104 | 83481104 |  | 3.1392 | 3.9365 |  | 45.3333 | 0.00061998 | 4049 | 0.054715 | 7803 | 3.3944e-05 | 7225
MAGUNDEN 1108563881 | MAGUNDEN 1108 | 252771108 |  | 4.1075 | 1.7131 |  | 66.5 | 0.00057088 | 4650 | 0.063262 | 6634 | 3.3944e-05 | 7226
MADERA 1118610994 | MADERA 1118 | 252761118 |  | 4.6989 | 1.8773 |  | 76.3333 | 0.00060859 | 4184 | 0.056897 | 7450 | 3.3939e-05 | 7227
POINT PINOLE 1102BR154 | POINT PINOLE 1102 | 14261102 |  | 0.042464 | 0 |  | 1 | 0.0005052 | 5334 | 0.067175 | 5831 | 3.3936e-05 | 7228
DALY CITY 110576128 | DALY CITY 1105 | 22641105 |  | 3.0885 | 3.0557 |  | 52.3333 | 0.00060162 | 4280 | 0.056133 | 7555 | 3.3933e-05 | 7229
FULTON 1105864 | FULTON 1105 | 42561105 |  | 2.4825 | 0.43155 |  | 49 | 0.00051028 | 5282 | 0.066702 | 6135 | 3.3929e-05 | 7230
MC KEE 110468892 | MC KEE 1104 | 83531104 |  | 2.4045 | 3.1042 |  | 42.8333 | 0.00063929 | 3833 | 0.053073 | 8251 | 3.3929e-05 | 7231
SNEATH LANE 110611792 | SNEATH LANE 1106 | 22721106 |  | 0.23362 | 0.020979 |  | 5.5 | 0.00063917 | 3835 | 0.053073 | 8251 | 3.3922e-05 | 7232
PUTAH CREEK 1105CB | PUTAH CREEK 1105 | 63681105 |  | 1.7855 | 0.14852 |  | 26.5 | 0.00050122 | 5384 | 0.067521 | 5591 | 3.3914e-05 | 7233
TIDEWATER 210638866 | TIDEWATER 2106 | 14652106 |  | 2.6822 | 0 |  | 45.3333 | 0.00050443 | 5343 | 0.067167 | 5838 | 3.3904e-05 | 7234
VASONA 110360132 | VASONA 1103 | 83771103 |  | 5.5997 | 5.2208 |  | 96 | 0.00063534 | 3878 | 0.053435 | 8115 | 3.3893e-05 | 7235
CORCORAN 110837412 | CORCORAN 1108 | 252171108 |  | 7.2866 | 6.9871 |  | 121.3333 | 0.00063858 | 3840 | 0.053073 | 8251 | 3.3891e-05 | 7236
WYANDOTTE 11061046 | WYANDOTTE 1106 | 102911106 |  | 3.6381 | 0.32707 |  | 61 | 0.0005093 | 5293 | 0.066769 | 6129 | 3.3886e-05 | 7237
VASONA 1105LC88 | VASONA 1105 | 83771105 |  | 0.84794 | 0.80446 |  | 14.8333 | 0.00063845 | 3843 | 0.053073 | 8251 | 3.3884e-05 | 7238
BELMONT 0406CB | BELMONT 0406 | 24030406 |  | 5.0243 | 3.3517 |  | 72.1667 | 0.00061205 | 4145 | 0.055387 | 7689 | 3.3881e-05 | 7239
TRIMBLE 1106CB | TRIMBLE 1106 | 83801106 |  | 0.64104 | 0.017486 |  | 13 | 0.00063833 | 3844 | 0.053073 | 8251 | 3.3878e-05 | 7240
SAN LEANDRO U 1107CB | SAN LEANDRO U 1107 | 13111107 |  | 3.6958 | 1.7413 |  | 56.5 | 0.00063831 | 3845 | 0.053073 | 8253 | 3.3877e-05 | 7241
CLARKSVILLE 21066832 | CLARKSVILLE 2106 | 153612106 |  | 0.084979 | 0 |  | 1.8333 | 0.00050549 | 5333 | 0.067 | 6057 | 3.3868e-05 | 7242
MENLO 1104CB | MENLO 1104 | 24131104 |  | 8.8137 | 6.3155 |  | 186.1667 | 0.00053213 | 5046 | 0.063045 | 6659 | 3.3867e-05 | 7243
BERKELEY F 0410CB | BERKELEY F 0410 | 12060410 |  | 2.8582 | 3.597 |  | 38.25 | 0.0006381 | 3851 | 0.053073 | 8252 | 3.3866e-05 | 7244
RADUM 1105CB | RADUM 1105 | 13151105 |  | 3.737 | 2.3131 |  | 60.6667 | 0.00060962 | 4175 | 0.055598 | 7659 | 3.3865e-05 | 7245
LODI 1102CB | LODI 1102 | 162111102 |  | 14.4582 | 1.6189 |  | 223 | 0.0004998 | 5394 | 0.070313 | 4977 | 3.3855e-05 | 7246
PIERCY 2109XR482 | PIERCY 2109 | 83912109 |  | 1.9842 | 2.5849 |  | 30 | 0.00063779 | 3854 | 0.053073 | 8251 | 3.3849e-05 | 7247
ROSSMOOR 110982962 | ROSSMOOR 1109 | 14161109 |  | 1.3923 | 0 |  | 26.75 | 0.00057535 | 4587 | 0.057904 | 7308 | 3.3848e-05 | 7248
HICKS 2105XR174 | HICKS 2105 | 83432105 |  | 3.2139 | 3.5349 |  | 55 | 0.00063451 | 3883 | 0.053551 | 8086 | 3.3845e-05 | 7249
HOLLISTER 2101CB | HOLLISTER 2101 | 182492101 |  | 6.4142 | 4.4029 |  | 117.3333 | 0.0005681 | 4681 | 0.059684 | 7057 | 3.3838e-05 | 7250
CASTRO VALLEY 1105132304 | CASTRO VALLEY 1105 | 14091105 | TRUE | 0.92776 | 0.88644 | 0.0059716 | 16.5 | 0.00063736 | 3855 | 0.053073 | 8251 | 3.3826e-05 | 7251
SANTA MARIA 110556022 | SANTA MARIA 1105 | 182671105 |  | 3.0407 | 0.16197 |  | 41.1667 | 0.0005174 | 5201 | 0.065985 | 6276 | 3.3825e-05 | 7252
BUTTE 1105518014 | BUTTE 1105 | 103081105 |  | 3.7935 | 0.17319 |  | 64 | 0.00045101 | 5909 | 0.07603 | 4190 | 3.3824e-05 | 7253
MISSION (X) 110969980 | MISSION (X) 1109 | 22011109 |  | 0.65567 | 0.91097 |  | 8.1667 | 0.00063705 | 3856 | 0.053073 | 8250 | 3.381e-05 | 7254
CORCORAN 1106CB | CORCORAN 1106 | 252171106 |  | 6.0417 | 1.3616 |  | 102.9167 | 0.00056344 | 4721 | 0.061502 | 6830 | 3.3804e-05 | 7255
PURISIMA 110154728 | PURISIMA 1101 | 182971101 | FALSE | 5.0041 | 0.1156 | 0.93536 | 100.5 | 0.00017313 | 10446 | 0.25984 | 3069 | 3.3804e-05 | 7256
GUERNSEY 1103CB | GUERNSEY 1103 | 252661103 |  | 3.9884 | 0.17835 |  | 45.0333 | 0.00043673 | 6047 | 0.0774 | 3398 | 3.3803e-05 | 7257
OAKLAND J 1106CR330 | OAKLAND J 1106 | 12091106 | FALSE | 2.3992 | 2.2103 | 0.97451 | 32.8333 | 0.00063686 | 3857 | 0.053073 | 8252 | 3.38e-05 | 7258
IGNACIO 11031068 | IGNACIO 1103 | 42481103 |  | 0.077415 | 0 |  | 1.5 | 0.00053177 | 5053 | 0.062358 | 6731 | 3.3793e-05 | 7259
HAYWARD O 0402CB | HAYWARD O 0402 | 12240402 |  | 3.7371 | 4.8524 |  | 59.4167 | 0.00063665 | 3861 | 0.053073 | 8252 | 3.3789e-05 | 7260
HUNTERS POINT (P) 110810569 | HUNTERS POINT (P) 1108 | 22331108 |  | 3.3855 | 4.2131 |  | 56.9167 | 0.00063664 | 3862 | 0.053073 | 8253 | 3.3788e-05 | 7261
RICHMOND R 1129BR348 | RICHMOND R 1129 | 13471129 |  | 0.024421 | 0 |  | 1.5 | 0.00050002 | 5392 | 0.067571 | 5567 | 3.3787e-05 | 7262
EUREKA A 1106CB | EUREKA A 1106 | 192121106 |  | 1.8095 | 0.48262 |  | 29.1667 | 0.00058509 | 4474 | 0.058803 | 7185 | 3.3787e-05 | 7263
TASSAJARA 21032705 | TASSAJARA 2103 | 14662103 |  | 1.6501 | 0.3466 |  | 32 | 0.00051511 | 5231 | 0.065546 | 6350 | 3.3779e-05 | 7264
EVERGREEN 2103980314 | EVERGREEN 2103 | 82012103 |  | 1.1378 | 0.55046 |  | 18.8333 | 0.00059766 | 4328 | 0.05751 | 7361 | 3.3775e-05 | 7265
WAHTOKE 1110CB | WAHTOKE 1110 | 254531110 |  | 7.7121 | 2.2122 |  | 119.5 | 0.00052435 | 5135 | 0.068447 | 5296 | 3.3767e-05 | 7266
CLARKSVILLE 210951742 | CLARKSVILLE 2109 | 153612109 |  | 1.7732 | 0.12694 |  | 31 | 0.00050386 | 5349 | 0.067029 | 5987 | 3.3763e-05 | 7267
VALLEJO B 1101779 | VALLEJO B 1101 | 42451101 |  | 1.301 | 1.2954 |  | 18.8333 | 0.00063595 | 3869 | 0.053073 | 8251 | 3.3751e-05 | 7268
PUEBLO 2102600010 | PUEBLO 2102 | 43292102 |  | 0.25633 | 0.10764 |  | 6.5 | 0.00060457 | 4246 | 0.054539 | 7840 | 3.3736e-05 | 7269
CONTRA COSTA 210788664 | CONTRA COSTA 2107 | 13652107 |  | 1.3647 | 0 |  | 24 | 0.00046477 | 5751 | 0.073345 | 4629 | 3.3735e-05 | 7270
ALMADEN 1102722120 | ALMADEN 1102 | 82311102 |  | 1.9249 | 3.0402 |  | 29.5 | 0.0006354 | 3876 | 0.053073 | 8251 | 3.3722e-05 | 7271
SILVERADO 210298998 | SILVERADO 2102 | 43432102 | TRUE | 12.4288 | 1.1644 | 0.069111 | 260 | 0.00048359 | 5563 | 0.074859 | 4434 | 3.3721e-05 | 7272
LAS POSITAS 2107MR184 | LAS POSITAS 2107 | 14402107 |  | 2.3289 | 0 |  | 43.5 | 0.00054643 | 4895 | 0.061881 | 6778 | 3.3704e-05 | 7273
SAN PABLO 1105BR192 | SAN PABLO 1105 | 14371105 |  | 1.9178 | 1.2292 |  | 33.6667 | 0.00051127 | 5272 | 0.066111 | 6244 | 3.3687e-05 | 7274
SPENCE 1102227476 | SPENCE 1102 | 182201102 |  | 0.29432 | 0 |  | 5.6667 | 0.00050277 | 5362 | 0.067 | 6056 | 3.3686e-05 | 7275
SF H 110886122 | SF H 1108 | 22101108 |  | 1.3427 | 1.9449 |  | 21.8333 | 0.00060985 | 4170 | 0.055858 | 7601 | 3.3685e-05 | 7276
DAVIS 110266336 | DAVIS 1102 | 62041102 |  | 1.9073 | 1.5099 |  | 26.5 | 0.00063465 | 3881 | 0.053073 | 8251 | 3.3682e-05 | 7277
DALY CITY 1102CB | DALY CITY 1102 | 22641102 |  | 1.6601 | 0.97478 |  | 23.1667 | 0.00063463 | 3882 | 0.053073 | 8250 | 3.3682e-05 | 7278
MOUNTAIN VIEW 1107LM06 | MOUNTAIN VIEW 1107 | 82031107 |  | 2.3513 | 2.0554 |  | 30.3333 | 0.00057837 | 4546 | 0.058353 | 7242 | 3.3674e-05 | 7279
LAKEWOOD 110492910 | LAKEWOOD 1104 | 13531104 |  | 7.0474 | 6.1171 |  | 116 | 0.00057851 | 4542 | 0.0585 | 7221 | 3.3673e-05 | 7280
PIERCY 2109XR200 | PIERCY 2109 | 83912109 |  | 7.3464 | 7.9844 |  | 93.1667 | 0.000618 | 4070 | 0.054368 | 7873 | 3.3672e-05 | 7281
LIVE OAK 1104CB | LIVE OAK 1104 | 153771104 |  | 6.5066 | 2.0933 |  | 110.5 | 0.00056692 | 4692 | 0.063369 | 6625 | 3.367e-05 | 7282
SF L 0405CB | SF L 0405 | 22260405 |  | 2.2987 | 3.9631 |  | 48.8333 | 0.0005817 | 4503 | 0.058303 | 7250 | 3.3662e-05 | 7283
BOLINAS 110146152 | BOLINAS 1101 | 42261101 |  | 10.1052 | 4.1245 |  | 161.5 | 0.0004808 | 5596 | 0.085134 | 3368 | 3.3661e-05 | 7284
KINGSBURG 1102CB | KINGSBURG 1102 | 252241102 |  | 4.7507 | 1.5149 |  | 70.3333 | 0.00047703 | 5628 | 0.072557 | 4714 | 3.3659e-05 | 7285
CONTRA COSTA 210749724 | CONTRA COSTA 2107 | 13652107 |  | 1.3929 | 0.52142 |  | 25 | 0.00046224 | 5781 | 0.070382 | 4963 | 3.3658e-05 | 7286
MOUNTAIN VIEW 110860022 | MOUNTAIN VIEW 1108 | 82031108 |  | 2.9172 | 1.5377 |  | 44.5 | 0.00063412 | 3888 | 0.053073 | 8251 | 3.3654e-05 | 7287
SF H 110857238 | SF H 1108 | 22101108 |  | 2.532 | 3.6645 |  | 39.7 | 0.00063408 | 3890 | 0.053073 | 8250 | 3.3652e-05 | 7288
LAS GALLINAS A 11041220 | LAS GALLINAS A 1104 | 42991104 |  | 4.865 | 5.0262 |  | 64.5 | 0.00062482 | 4000 | 0.053827 | 7990 | 3.3647e-05 | 7289
SANTA MARIA 1109473720 | SANTA MARIA 1109 | 182671109 |  | 0.58411 | 0.071726 |  | 9.5 | 0.00050216 | 5370 | 0.067 | 6057 | 3.3645e-05 | 7290
BRITTON 1110LV38 | BRITTON 1110 | 83611110 |  | 7.2849 | 4.8716 |  | 116 | 0.00063361 | 3896 | 0.053073 | 8251 | 3.3627e-05 | 7291
EVERGREEN 2103XR074 | EVERGREEN 2103 | 82012103 |  | 4.8933 | 4.1944 |  | 72 | 0.00060046 | 4294 | 0.057931 | 7304 | 3.3617e-05 | 7292
WOODCHUCK 2101R1115 | WOODCHUCK 2101 | 254912101 |  | 0.62613 | 0 |  | 10 | 0.00049135 | 5482 | 0.068358 | 5313 | 3.359e-05 | 7293
VASCO 1101MR292 | VASCO 1101 | 13751101 |  | 0.17718 | 0 |  | 4.5 | 0.00063291 | 3903 | 0.053073 | 8251 | 3.359e-05 | 7294
MADERA 1116CB | MADERA 1116 | 252761116 |  | 2.074 | 0.061293 |  | 40 | 0.00043723 | 6041 | 0.076792 | 3892 | 3.3589e-05 | 7295
GOLDTREE 110814115 | GOLDTREE 1108 | 182581108 |  | 1.3097 | 1.7908 |  | 24.5 | 0.00061256 | 4139 | 0.05421 | 7900 | 3.3588e-05 | 7296
ALMADEN 1101CB | ALMADEN 1101 | 82311101 |  | 18.2638 | 24.7365 |  | 262 | 0.00063268 | 3905 | 0.053073 | 8251 | 3.3578e-05 | 7297
DALY CITY 1101CB | DALY CITY 1101 | 22641101 |  | 1.8509 | 1.3302 |  | 32.6667 | 0.00062835 | 3965 | 0.053468 | 8105 | 3.3569e-05 | 7298
NEWARK 21KV 2103906 | NEWARK 21KV 2103 | 12232103 |  | 0.010739 | 0 |  | 0.83333 | 0.00063245 | 3908 | 0.053073 | 8250 | 3.3566e-05 | 7299
EL CERRITO G 1113BR280 | EL CERRITO G 1113 | 12501113 |  | 0.74806 | 0.67619 |  | 7.2 | 0.00063235 | 3911 | 0.053073 | 8250 | 3.356e-05 | 7300
DUMBARTON 1107CB | DUMBARTON 1107 | 14471107 |  | 5.1854 | 5.0002 |  | 88.5 | 0.00063223 | 3914 | 0.053073 | 8251 | 3.3554e-05 | 7301
BRENTWOOD 2111CB | BRENTWOOD 2111 | 14592111 |  | 6.1719 | 0.89219 |  | 106.4167 | 0.00050157 | 5378 | 0.067037 | 5965 | 3.3544e-05 | 7302
CHEROKEE 110236802 | CHEROKEE 1102 | 163651102 |  | 1.4563 | 0.25352 |  | 25.5 | 0.00043744 | 6037 | 0.076446 | 4036 | 3.354e-05 | 7303
SALINAS 110638220 | SALINAS 1106 | 182011106 |  | 2.5012 | 2.2922 |  | 35.5 | 0.00055933 | 4762 | 0.058897 | 7170 | 3.354e-05 | 7304
ERTA 04046633 | ERTA 0404 | 83510404 |  | 1.3272 | 1.0514 |  | 17.3333 | 0.00059896 | 4312 | 0.057492 | 7363 | 3.3538e-05 | 7305
WEST FRESNO 110423640 | WEST FRESNO 1104 | 253731104 |  | 2.7897 | 2.5967 |  | 44.3333 | 0.00053374 | 5030 | 0.063418 | 6620 | 3.3536e-05 | 7306
MALAGA 1103CB | MALAGA 1103 | 254251103 |  | 14.8253 | 6.4921 |  | 256.1667 | 0.00055021 | 4859 | 0.063221 | 6643 | 3.3526e-05 | 7307
LOYOLA 0403CB | LOYOLA 0403 | 82160403 |  | 8.7878 | 8.507 |  | 124.6167 | 0.00057671 | 4566 | 0.058059 | 7280 | 3.3512e-05 | 7308
SF M 0404CB | SF M 0404 | 22270404 |  | 3.5649 | 4.7197 |  | 61.6167 | 0.00063143 | 3924 | 0.053073 | 8251 | 3.3512e-05 | 7309
BELLE HAVEN 11038970 | BELLE HAVEN 1103 | 24021103 |  | 0.51614 | 0.045788 |  | 8.5 | 0.0006313 | 3925 | 0.053073 | 8251 | 3.3505e-05 | 7310
FRENCH CAMP 1104CB | FRENCH CAMP 1104 | 163291104 |  | 5.6109 | 0.77617 |  | 102.3333 | 0.00047024 | 5698 | 0.072974 | 4666 | 3.3505e-05 | 7311
CHEROKEE 110175176 | CHEROKEE 1101 | 163651101 |  | 4.2855 | 0.89617 |  | 83.5 | 0.00053664 | 4992 | 0.06435 | 6502 | 3.3493e-05 | 7312
SF E 110510491 | SF E 1105 | 22071105 |  | 0.36189 | 0.68555 |  | 8.3333 | 0.00063104 | 3927 | 0.053073 | 8250 | 3.3491e-05 | 7313
JARVIS 1111MR132 | JARVIS 1111 | 13501111 |  | 3.8676 | 3.5632 |  | 61.5 | 0.00060901 | 4178 | 0.055227 | 7718 | 3.349e-05 | 7314
MERCED 110811130 | MERCED 1108 | 252801108 |  | 2.1312 | 2.387 |  | 40.8333 | 0.00063101 | 3929 | 0.053073 | 8250 | 3.3489e-05 | 7315
CARQUINEZ 110369014 | CARQUINEZ 1103 | 43281103 |  | 6.1373 | 4.8434 |  | 94.8333 | 0.00063095 | 3930 | 0.053073 | 8252 | 3.3486e-05 | 7316
SANGER 1104CB | SANGER 1104 | 252351104 |  | 5.7311 | 0.55934 |  | 88.3333 | 0.00047498 | 5647 | 0.073406 | 4623 | 3.3482e-05 | 7317
SALINAS 110745054 | SALINAS 1107 | 182011107 |  | 3.073 | 2.2232 |  | 43.6667 | 0.0006308 | 3931 | 0.053073 | 8251 | 3.3478e-05 | 7318
MOLINO 1102CB | MOLINO 1102 | 42571102 |  | 13.7428 | 2.3603 |  | 248.5 | 0.00049952 | 5396 | 0.067083 | 5918 | 3.3477e-05 | 7319
PLAINFIELD 1101CB | PLAINFIELD 1101 | 63441101 |  | 0.61831 | 0 |  | 6.8333 | 0.00043248 | 6087 | 0.0774 | 3396 | 3.3474e-05 | 7320
OLIVEHURST 1102CB | OLIVEHURST 1102 | 152901102 |  | 6.0317 | 3.7533 |  | 105 | 0.00060519 | 4236 | 0.055172 | 7728 | 3.3463e-05 | 7321
MT EDEN 1104MR137 | MT EDEN 1104 | 13761104 |  | 6.6613 | 5.5193 |  | 111.1667 | 0.00063048 | 3937 | 0.053073 | 8250 | 3.3461e-05 | 7322
NORTECH 211079884 | NORTECH 2110 | 82462110 |  | 0.022807 | 0 |  | 1.5 | 0.0004994 | 5397 | 0.067 | 6057 | 3.346e-05 | 7323
SAN LEANDRO U 1106MR630 | SAN LEANDRO U 1106 | 13111106 |  | 3.5555 | 2.8792 |  | 63.6667 | 0.00063045 | 3938 | 0.053073 | 8252 | 3.346e-05 | 7324
DEL MAR 1103624 | DEL MAR 1103 | 152581103 |  | 2.505 | 1.0438 |  | 41.5 | 0.00049934 | 5399 | 0.067 | 6057 | 3.3455e-05 | 7325
STUART 0405CB | STUART 0405 | 13840405 |  | 2.805 | 3.3011 |  | 39.75 | 0.0006303 | 3939 | 0.053073 | 8250 | 3.3452e-05 | 7326
STOREY 110741316 | STOREY 1107 | 254611107 |  | 4.7903 | 2.8005 |  | 92.3333 | 0.00052102 | 5167 | 0.067409 | 5660 | 3.3451e-05 | 7327
DIXON LANDING 2103XR142 | DIXON LANDING 2103 | 14722103 |  | 0.86679 | 0.0089608 |  | 14 | 0.00057712 | 4560 | 0.056811 | 7466 | 3.3449e-05 | 7328
JARVIS 1112CB | JARVIS 1112 | 13501112 |  | 1.9891 | 0.23315 |  | 29.8333 | 0.00063018 | 3940 | 0.053073 | 8251 | 3.3445e-05 | 7329
FULTON 1102904058 | FULTON 1102 | 42561102 |  | 2.9636 | 0.43086 |  | 57 | 0.00051006 | 5283 | 0.064968 | 6440 | 3.344e-05 | 7330
LLAGAS 2102XR190 | LLAGAS 2102 | 83182102 |  | 1.3786 | 0.74603 |  | 28 | 0.00051389 | 5245 | 0.066987 | 6065 | 3.3439e-05 | 7331
EL CAPITAN 21108500 | EL CAPITAN 2110 | 253882110 |  | 9.7087 | 2.6255 |  | 140.5 | 0.00058781 | 4446 | 0.058675 | 7202 | 3.3438e-05 | 7332
TAFT 11061666 | TAFT 1106 | 252081106 |  | 2.7592 | 0.91717 |  | 42.8333 | 0.0005117 | 5269 | 0.065629 | 6333 | 3.3436e-05 | 7333
EAST MARYSVILLE 1105CB | EAST MARYSVILLE 1105 | 152331105 |  | 10.9594 | 1.6888 |  | 199 | 0.0004782 | 5618 | 0.072064 | 4772 | 3.3426e-05 | 7334
HENRIETTA 110656636 | HENRIETTA 1106 | 252681106 |  | 0.032044 | 0 |  | 0.83333 | 0.00043186 | 6094 | 0.0774 | 3396 | 3.3426e-05 | 7335
HALF MOON BAY 1102863822 | HALF MOON BAY 1102 | 24101102 | TRUE | 0.66544 | 0.049889 | 0.06002 | 12.5 | 0.00049388 | 5457 | 0.22363 | 3112 | 3.3424e-05 | 7336
RICHMOND R 1123CB | RICHMOND R 1123 | 13471123 |  | 1.3297 | 0.086215 |  | 25.3333 | 0.00061511 | 4103 | 0.054172 | 7910 | 3.3422e-05 | 7337
VASONA 110360072 | VASONA 1103 | 83771103 |  | 5.1867 | 5.5256 |  | 77.5 | 0.00062962 | 3946 | 0.053073 | 8251 | 3.3416e-05 | 7338
MILPITAS 2112XR040 | MILPITAS 2112 | 82832112 |  | 0.24194 | 0.051701 |  | 5.3333 | 0.00062957 | 3947 | 0.053073 | 8251 | 3.3413e-05 | 7339
WEBER 110914062 | WEBER 1109 | 163481109 |  | 5.2758 | 4.4614 |  | 93.5 | 0.00060527 | 4235 | 0.055598 | 7657 | 3.3409e-05 | 7340
SF E 110765846 | SF E 1107 | 22071107 |  | 1.0686 | 1.3345 |  | 18.75 | 0.00062938 | 3949 | 0.053073 | 8251 | 3.3403e-05 | 7341
JARVIS 1108767280 | JARVIS 1108 | 13501108 | FALSE | 0.71113 | 0.41553 | 0.64667 | 9.5 | 0.00048721 | 5527 | 0.061136 | 6879 | 3.3399e-05 | 7342
JUDAH 0402CB | JUDAH 0402 | 22400402 |  | 2.1378 | 3.3569 |  | 43.8333 | 0.0006279 | 3974 | 0.053628 | 8053 | 3.3395e-05 | 7343
WEST FRESNO 1112R4693 | WEST FRESNO 1112 | 253731112 |  | 1.4109 | 0.43864 |  | 22.5 | 0.00052095 | 5168 | 0.066047 | 6262 | 3.3386e-05 | 7344
SARATOGA 111046892 | SARATOGA 1110 | 83371110 |  | 2.0658 | 2.9008 |  | 32 | 0.00062903 | 3952 | 0.053073 | 8251 | 3.3384e-05 | 7345
CHEROKEE 110263488 | CHEROKEE 1102 | 163651102 |  | 5.0265 | 1.2922 |  | 105 | 0.0004603 | 5804 | 0.07306 | 4655 | 3.338e-05 | 7346
LAWRENCE 1105CB | LAWRENCE 1105 | 83421105 |  | 1.0576 | 1.1265 |  | 18.6667 | 0.00062892 | 3955 | 0.053073 | 8250 | 3.3378e-05 | 7347
BAHIA 1105910176 | BAHIA 1105 | 43251105 |  | 4.8998 | 3.6051 |  | 80.3333 | 0.00062147 | 4031 | 0.054121 | 7924 | 3.3375e-05 | 7348
PRUNEDALE 110722232 | PRUNEDALE 1107 | 182961107 |  | 2.4564 | 1.6452 |  | 43 | 0.00060708 | 4214 | 0.054854 | 7779 | 3.3371e-05 | 7349
DEEPWATER 1107CB | DEEPWATER 1107 | 63621107 |  | 12.533 | 3.7986 |  | 225.3333 | 0.00053755 | 4985 | 0.064249 | 6513 | 3.337e-05 | 7350
VIERRA 1703CB | VIERRA 1703 | 162701703 |  | 5.7871 | 0.37752 |  | 105.3333 | 0.00050649 | 5322 | 0.066874 | 6102 | 3.3366e-05 | 7351
7TH STANDARD 2103CB | 7TH STANDARD 2103 | 254582103 |  | 10.7435 | 0.55456 |  | 167.0833 | 0.00046368 | 5764 | 0.073414 | 4621 | 3.3364e-05 | 7352
LAKEVILLE 1102CB | LAKEVILLE 1102 | 43371102 |  | 1.4194 | 0.13294 |  | 23.5 | 0.0004942 | 5451 | 0.067522 | 5590 | 3.3362e-05 | 7353
RUSSELL 0401CB | RUSSELL 0401 | 13310401 |  | 3.4089 | 4.0461 |  | 48.3333 | 0.00062859 | 3961 | 0.053073 | 8251 | 3.3361e-05 | 7354
MT EDEN 110211986 | MT EDEN 1102 | 13761102 |  | 1.3588 | 1.5806 |  | 21.3333 | 0.0006285 | 3963 | 0.053073 | 8251 | 3.3356e-05 | 7355
DIXON 110248308 | DIXON 1102 | 62061102 |  | 0.014869 | 0 |  | 0.5 | 0.00043092 | 6109 | 0.0774 | 3397 | 3.3353e-05 | 7356
SF L 1101CB | SF L 1101 | 22261101 |  | 1.8005 | 1.6719 |  | 32.0833 | 0.00062431 | 4008 | 0.053452 | 8111 | 3.3353e-05 | 7357
SANTA ROSA A 111038858 | SANTA ROSA A 1110 | 42151110 |  | 6.4061 | 5.9483 |  | 100.3333 | 0.00058981 | 4418 | 0.056588 | 7495 | 3.3351e-05 | 7358
WOLFE 1113LV20 | WOLFE 1113 | 83671113 |  | 5.4817 | 5.6985 |  | 78.8333 | 0.00062821 | 3968 | 0.053073 | 8251 | 3.3341e-05 | 7359
BELMONT 11109088 | BELMONT 1110 | 24031110 |  | 5.5134 | 4.4646 |  | 77 | 0.00057557 | 4583 | 0.057547 | 7350 | 3.334e-05 | 7360
MOUNTAIN VIEW 1114LM12 | MOUNTAIN VIEW 1114 | 82031114 |  | 0.69664 | 0.28122 |  | 10 | 0.00058814 | 4440 | 0.057251 | 7399 | 3.3327e-05 | 7361
GREEN VALLEY 2103186292 | GREEN VALLEY 2103 | 83192103 |  | 2.235 | 1.2759 |  | 36.5 | 0.0005886 | 4433 | 0.056888 | 7453 | 3.3324e-05 | 7362
RUSSELL 0402CB | RUSSELL 0402 | 13310402 |  | 3.3354 | 4.4804 |  | 47.5 | 0.00062787 | 3975 | 0.053073 | 8252 | 3.3323e-05 | 7363
EDENVALE 2106XR438 | EDENVALE 2106 | 82952106 |  | 1.8932 | 1.3486 |  | 27.1667 | 0.00062785 | 3976 | 0.053073 | 8250 | 3.3322e-05 | 7364
RIVERBANK 17139000 | RIVERBANK 1713 | 163191713 |  | 5.7614 | 2.711 |  | 86 | 0.00057131 | 4642 | 0.059446 | 7092 | 3.332e-05 | 7365
BELMONT 1107CB | BELMONT 1107 | 24031107 |  | 0.9733 | 0.25113 |  | 25.5 | 0.00062031 | 4044 | 0.054027 | 7944 | 3.332e-05 | 7366
EL CERRITO G 1113CB | EL CERRITO G 1113 | 12501113 | TRUE | 4.3123 | 3.0743 | 0.22208 | 53.9167 | 0.00060233 | 4273 | 0.056879 | 7455 | 3.3313e-05 | 7367
COLUMBUS 11048058 | COLUMBUS 1104 | 253951104 |  | 0.63445 | 0.91323 |  | 10.5 | 0.00062762 | 3978 | 0.053073 | 8251 | 3.331e-05 | 7368
GOLDTREE 1105944608 | GOLDTREE 1105 | 182581105 |  | 2.8236 | 2.4309 |  | 42.5 | 0.00060596 | 4228 | 0.055039 | 7747 | 3.3304e-05 | 7369
OAKLAND C 1109683734 | OAKLAND C 1109 | 12011109 |  | 0.43075 | 0.37122 |  | 12.1667 | 0.00062743 | 3980 | 0.053073 | 8251 | 3.3299e-05 | 7370
BRENTWOOD 2108B512R | BRENTWOOD 2108 | 14592108 |  | 1.4524 | 0.11417 |  | 28 | 0.00053739 | 4987 | 0.062773 | 6682 | 3.3299e-05 | 7371
DALY CITY 1103CB | DALY CITY 1103 | 22641103 |  | 4.7363 | 4.0393 |  | 65.5 | 0.00061688 | 4089 | 0.054558 | 7835 | 3.3296e-05 | 7372
FRENCH CAMP 1103CB | FRENCH CAMP 1103 | 163291103 |  | 1.2266 | 0.086389 |  | 18.3333 | 0.00048243 | 5576 | 0.071429 | 4841 | 3.329e-05 | 7373
BELLEVUE 1104CB | BELLEVUE 1104 | 43181104 |  | 2.4339 | 1.2611 |  | 44.5 | 0.00057126 | 4643 | 0.060351 | 6982 | 3.3286e-05 | 7374
BAY MEADOWS 21013369 | BAY MEADOWS 2101 | 24012101 |  | 0.89748 | 0.76578 |  | 12.8333 | 0.00062135 | 4033 | 0.053615 | 8055 | 3.3282e-05 | 7375
MISSION (X) 1108991594 | MISSION (X) 1108 | 22011108 |  | 1.1706 | 1.8012 |  | 20.6667 | 0.00058605 | 4464 | 0.05837 | 7238 | 3.3273e-05 | 7376
CORDELIA 1104CB | CORDELIA 1104 | 62701104 |  | 4.06 | 0.079945 |  | 74 | 0.00049622 | 5432 | 0.067593 | 5554 | 3.3262e-05 | 7377
CASTRO VALLEY 1108MR205 | CASTRO VALLEY 1108 | 14091108 | TRUE | 5.4258 | 5.362 | 0.016922 | 83.3333 | 0.00058048 | 4514 | 0.058029 | 7288 | 3.3251e-05 | 7378
MENLO 0403CB | MENLO 0403 | 24130403 |  | 5.9874 | 5.6284 |  | 99 | 0.00054769 | 4880 | 0.060904 | 6900 | 3.3248e-05 | 7379
MC KEE 1104XR270 | MC KEE 1104 | 83531104 |  | 3.8541 | 4.7597 |  | 61.3333 | 0.00062641 | 3985 | 0.053073 | 8251 | 3.3246e-05 | 7380
VINEYARD 2106MR519 | VINEYARD 2106 | 14502106 |  | 1.8783 | 2.1823 |  | 29.5 | 0.00060036 | 4295 | 0.055947 | 7586 | 3.3244e-05 | 7381
WOODWARD 2105CB | WOODWARD 2105 | 255292105 |  | 0.36379 | 0 |  | 8.5 | 0.00057945 | 4528 | 0.060821 | 6908 | 3.324e-05 | 7382
BELMONT 1106872866 | BELMONT 1106 | 24031106 |  | 0.0056709 | 0 |  | 0.5 | 0.00062595 | 3988 | 0.053073 | 8251 | 3.3221e-05 | 7383
FITCH MOUNTAIN 1111CB | FITCH MOUNTAIN 1111 | 42751111 |  | 12.7814 | 1.5427 |  | 225.6667 | 0.00049614 | 5433 | 0.066984 | 6068 | 3.3219e-05 | 7384
SF K 11016365 | SF K 1101 | 22131101 |  | 5.2892 | 8.1655 |  | 89.5 | 0.00060433 | 4252 | 0.055168 | 7729 | 3.3216e-05 | 7385
WOODSIDE 110551262 | WOODSIDE 1105 | 24251105 |  | 1.4546 | 0.51508 |  | 26.8333 | 0.00049574 | 5438 | 0.067 | 6058 | 3.3215e-05 | 7386
SANTA MARIA 1108M120 | SANTA MARIA 1108 | 182671108 |  | 7.1701 | 6.6803 |  | 109.8333 | 0.0006258 | 3989 | 0.053073 | 8251 | 3.3213e-05 | 7387
WILLOWS A 1101CB | WILLOWS A 1101 | 102741101 |  | 4.2768 | 1.4982 |  | 73.45 | 0.00051385 | 5247 | 0.065691 | 6327 | 3.3203e-05 | 7388
OCEANO 1105V48 | OCEANO 1105 | 182601105 | TRUE | 2.5532 | 2.2641 | 0.24191 | 47.1667 | 0.00057537 | 4585 | 0.058262 | 7258 | 3.32e-05 | 7389
WEEDPATCH 11031668 | WEEDPATCH 1103 | 252971103 |  | 2.0145 | 0.60785 |  | 35 | 0.00048374 | 5560 | 0.0691 | 5175 | 3.32e-05 | 7390
RICHMOND R 1126BR182 | RICHMOND R 1126 | 13471126 |  | 4.2224 | 4.5382 |  | 66 | 0.00058817 | 4439 | 0.056343 | 7522 | 3.3196e-05 | 7391
COTTLE 1707376892 | COTTLE 1707 | 163711707 |  | 3.5901 | 0.80386 |  | 63.1667 | 0.00054451 | 4915 | 0.067459 | 5631 | 3.3191e-05 | 7392
EDES 1103161972 | EDES 1103 | 13681103 |  | 2.0942 | 3.0138 |  | 31.1667 | 0.00062519 | 3994 | 0.053073 | 8250 | 3.3181e-05 | 7393
FRANKLIN 1103P202 | FRANKLIN 1103 | 13921103 |  | 8.6046 | 7.4294 |  | 145.5 | 0.00055914 | 4763 | 0.059342 | 7107 | 3.3176e-05 | 7394
GREENBRAE 1104751 | GREENBRAE 1104 | 43091104 | TRUE | 3.0133 | 3.2266 | 0.24152 | 49.5 | 0.00057884 | 4539 | 0.058906 | 7167 | 3.3175e-05 | 7395
HARRIS 110866386 | HARRIS 1108 | 192431108 |  | 3.5776 | 4.1025 |  | 52.6667 | 0.00062495 | 3997 | 0.053073 | 8252 | 3.3168e-05 | 7396
HOLLISTER 21014790 | HOLLISTER 2101 | 182492101 |  | 3.446 | 3.4333 |  | 61 | 0.00061356 | 4127 | 0.054584 | 7832 | 3.3161e-05 | 7397
OAKLAND X 1115CB | OAKLAND X 1115 | 12541115 |  | 3.5556 | 4.0119 |  | 53.6667 | 0.0006248 | 4001 | 0.053073 | 8251 | 3.316e-05 | 7398
DIXON 1104CB | DIXON 1104 | 62061104 |  | 4.8293 | 0.9787 |  | 86.3333 | 0.00053854 | 4972 | 0.065438 | 6370 | 3.316e-05 | 7399
PUEBLO 1105716 | PUEBLO 1105 | 43291105 |  | 9.182 | 2.3189 |  | 169 | 0.0004951 | 5442 | 0.067236 | 5775 | 3.3159e-05 | 7400
7TH STANDARD 2102CB | 7TH STANDARD 2102 | 254582102 |  | 11.9602 | 0.27447 |  | 191.9167 | 0.00046473 | 5752 | 0.073738 | 4577 | 3.3155e-05 | 7401
OAKLAND J 1105153228 | OAKLAND J 1105 | 12091105 | TRUE | 4.1503 | 4.1773 | 0.47974 | 56.6667 | 0.00060664 | 4219 | 0.054598 | 7826 | 3.3146e-05 | 7402
NEW HOPE 110111623 | NEW HOPE 1101 | 162081101 |  | 0.86876 | 0.60698 |  | 18.5 | 0.00047124 | 5687 | 0.071786 | 4797 | 3.3146e-05 | 7403
PASO ROBLES 1104CB | PASO ROBLES 1104 | 182611104 |  | 1.6115 | 1.3135 |  | 32 | 0.00060324 | 4263 | 0.054708 | 7806 | 3.3142e-05 | 7404
MORGAN HILL 2104XR018 | MORGAN HILL 2104 | 83242104 |  | 2.9999 | 0.73343 |  | 69 | 0.00052572 | 5115 | 0.063721 | 6577 | 3.3141e-05 | 7405
ATWATER 1105CB | ATWATER 1105 | 253611105 |  | 2.3424 | 2.4072 |  | 44 | 0.00061654 | 4094 | 0.054276 | 7893 | 3.3139e-05 | 7406
HORSESHOE 110451536 | HORSESHOE 1104 | 152571104 |  | 4.5773 | 1.6438 |  | 71 | 0.00049574 | 5437 | 0.06659 | 6171 | 3.3138e-05 | 7407
ANITA 1105CB | ANITA 1105 | 102841105 |  | 10.1264 | 1.2759 |  | 180 | 0.00049188 | 5475 | 0.067957 | 5413 | 3.3137e-05 | 7408
MT EDEN 1112MR365 | MT EDEN 1112 | 13761112 |  | 4.1727 | 4.2816 |  | 69 | 0.00061821 | 4068 | 0.053678 | 8039 | 3.3102e-05 | 7409
COLUSA 1101137302 | COLUSA 1101 | 62021101 |  | 1.1958 | 0.77457 |  | 20 | 0.00062326 | 4014 | 0.053073 | 8251 | 3.3078e-05 | 7410
BOGUE 1106CB | BOGUE 1106 | 153781106 |  | 7.3494 | 1.6777 |  | 118.2 | 0.00046523 | 5748 | 0.07183 | 4788 | 3.3071e-05 | 7411
EL CAPITAN 1102605060 | EL CAPITAN 1102 | 253881102 |  | 4.9479 | 0.47753 |  | 85 | 0.00045529 | 5866 | 0.073223 | 4646 | 3.3068e-05 | 7412
WARD 0401CB | WARD 0401 | 12980401 |  | 4.5217 | 3.8203 |  | 56 | 0.00061248 | 4140 | 0.054502 | 7845 | 3.3065e-05 | 7413
UPPER LAKE 110142378 | UPPER LAKE 1101 | 42871101 |  | 1.3561 | 0.76907 |  | 27.3333 | 0.00048407 | 5555 | 0.068414 | 5302 | 3.3058e-05 | 7414
SISQUOC 1103867486 | SISQUOC 1103 | 182811103 | TRUE | 3.3591 | 0.020971 | 0.60466 | 65.5 | 0.00014817 | 10717 | 0.26899 | 3056 | 3.3053e-05 | 7415
MORGAN HILL 21103093 | MORGAN HILL 2110 | 83242110 |  | 1.6487 | 0.55254 |  | 33.3333 | 0.00050369 | 5353 | 0.0661 | 6247 | 3.3053e-05 | 7416
ATWATER 110710490 | ATWATER 1107 | 253611107 |  | 4.9321 | 0.90213 |  | 86.5 | 0.00046323 | 5770 | 0.072999 | 4663 | 3.3045e-05 | 7417
CRESSEY 2104CB | CRESSEY 2104 | 254702104 |  | 2.6235 | 0.14186 |  | 44.5 | 0.00042691 | 6149 | 0.0774 | 3397 | 3.3043e-05 | 7418
LODI 1102476180 | LODI 1102 | 162111102 |  | 4.3659 | 0.411 |  | 62.5833 | 0.00043982 | 6012 | 0.075647 | 4299 | 3.3033e-05 | 7419
VALLEY VIEW 1103P158 | VALLEY VIEW 1103 | 14341103 |  | 4.7435 | 5.4102 |  | 77 | 0.00057189 | 4630 | 0.057549 | 7349 | 3.3025e-05 | 7420
LOS ALTOS 1104CB | LOS ALTOS 1104 | 82241104 |  | 0.79178 | 0.10464 |  | 10.8333 | 0.0005694 | 4668 | 0.057358 | 7383 | 3.3021e-05 | 7421
MARYSVILLE 1103CB | MARYSVILLE 1103 | 152011103 |  | 11.8348 | 5.0576 |  | 204.75 | 0.00054183 | 4935 | 0.063199 | 6644 | 3.3018e-05 | 7422
OAKLAND X 1107CR428 | OAKLAND X 1107 | 12541107 |  | 3.3741 | 3.4993 |  | 53.5 | 0.00053492 | 5011 | 0.062397 | 6729 | 3.3008e-05 | 7423
BRITTON 1106CB | BRITTON 1106 | 83611106 |  | 3.7206 | 2.9186 |  | 64.3333 | 0.00062193 | 4026 | 0.053073 | 8252 | 3.3007e-05 | 7424
MC CALL 11055160 | MC CALL 1105 | 254121105 |  | 0.22344 | 0 |  | 4 | 0.00059845 | 4318 | 0.056114 | 7559 | 3.3001e-05 | 7425
HIGHLANDS 11021304 | HIGHLANDS 1102 | 43361102 |  | 2.5355 | 1.9715 |  | 34.3333 | 0.00059015 | 4412 | 0.056115 | 7558 | 3.2986e-05 | 7426
FULTON 11045016 | FULTON 1104 | 42561104 |  | 0.84526 | 0.0090805 |  | 16.5 | 0.00050003 | 5390 | 0.066578 | 6175 | 3.2983e-05 | 7427
TRACY 1110CB | TRACY 1110 | 162881110 |  | 8.8285 | 0.50508 |  | 147.75 | 0.00048783 | 5520 | 0.070347 | 4972 | 3.2981e-05 | 7428
EL CERRITO G 1108CB | EL CERRITO G 1108 | 12501108 | TRUE | 7.3219 | 8.3104 | 0.0026986 | 91.6833 | 0.00061419 | 4118 | 0.053832 | 7989 | 3.2975e-05 | 7429
NEWARK 12KV 1105CB | NEWARK 12KV 1105 | 12221105 |  | 1.7258 | 0.51428 |  | 23.45 | 0.00061726 | 4083 | 0.053418 | 8123 | 3.2956e-05 | 7430
HICKS 2103XR262 | HICKS 2103 | 83432103 |  | 0.81898 | 1.0591 |  | 15.3333 | 0.00051585 | 5218 | 0.065329 | 6387 | 3.2951e-05 | 7431
RIVERBANK 17169050 | RIVERBANK 1716 | 163191716 |  | 13.5874 | 5.7818 |  | 229.3333 | 0.00056799 | 4682 | 0.061229 | 6865 | 3.2948e-05 | 7432
NEWMAN 1105CB | NEWMAN 1105 | 162741105 |  | 5.2498 | 1.6514 |  | 86 | 0.00055418 | 4826 | 0.063639 | 6593 | 3.2944e-05 | 7433
ORO LOMA 1102CB | ORO LOMA 1102 | 255371102 |  | 1.0708 | 0 |  | 5.6167 | 0.00045904 | 5813 | 0.070726 | 4929 | 3.2938e-05 | 7434
ORO LOMA 1103CB | ORO LOMA 1103 | 255371103 |  | 1.0966 | 0 |  | 5.6167 | 0.00045904 | 5814 | 0.070726 | 4930 | 3.2938e-05 | 7434
EUREKA E 110429676 | EUREKA E 1104 | 192331104 |  | 5.5331 | 4.5762 |  | 72 | 0.00058093 | 4510 | 0.056911 | 7448 | 3.2931e-05 | 7435
BELLE HAVEN 0409CB | BELLE HAVEN 0409 | 24020409 |  | 3.8758 | 3.3075 |  | 62.25 | 0.00062033 | 4043 | 0.053073 | 8253 | 3.2922e-05 | 7436
TAFT 1108CB | TAFT 1108 | 252081108 |  | 9.1854 | 3.0256 |  | 135.4167 | 0.00052389 | 5143 | 0.064107 | 6527 | 3.292e-05 | 7437
PURISIMA 1101104948 | PURISIMA 1101 | 182971101 | FALSE | 16.6963 | 1.2323 | 2.1282 | 317.5 | 0.00014072 | 10780 | 0.28736 | 3031 | 3.2906e-05 | 7438
NEWARK 12KV 1103CB | NEWARK 12KV 1103 | 12221103 |  | 9.7458 | 4.7409 |  | 150.3667 | 0.0006199 | 4050 | 0.053073 | 8251 | 3.29e-05 | 7439
UKIAH 111129452 | UKIAH 1111 | 42771111 |  | 8.5891 | 0.93882 |  | 147.5 | 0.00054212 | 4933 | 0.061523 | 6827 | 3.2891e-05 | 7440
ORLAND B 1101CB | ORLAND B 1101 | 102701101 |  | 10.035 | 3.463 |  | 171 | 0.00051988 | 5180 | 0.065328 | 6388 | 3.2885e-05 | 7441
STONE CORRAL 1110975698 | STONE CORRAL 1110 | 252921110 | FALSE | 4.8784 | 0.80945 | 0.63272 | 92 | 0.0002212 | 9683 | 0.20808 | 3133 | 3.2859e-05 | 7442
WOODWARD 2108CB | WOODWARD 2108 | 255292108 |  | 12.0105 | 1.1246 |  | 226.5 | 0.00048787 | 5518 | 0.067293 | 5736 | 3.2848e-05 | 7443
WEST FRESNO 1111CB | WEST FRESNO 1111 | 253731111 |  | 9.5869 | 5.3075 |  | 169.375 | 0.00054751 | 4885 | 0.060791 | 6914 | 3.2843e-05 | 7444
FORT ORD 21059140 | FORT ORD 2105 | 182402105 |  | 0.14367 | 0.27811 |  | 5.5 | 0.00058281 | 4493 | 0.056871 | 7456 | 3.284e-05 | 7445
SAN LUIS OBISPO 1108V92 | SAN LUIS OBISPO 1108 | 182631108 |  | 1.5537 | 0.77779 |  | 33 | 0.00054925 | 4870 | 0.060573 | 6945 | 3.2837e-05 | 7446
NOTRE DAME 1104CB | NOTRE DAME 1104 | 102041104 |  | 4.7115 | 0.30263 |  | 87 | 0.00051489 | 5237 | 0.065043 | 6426 | 3.2836e-05 | 7447
HICKS 1110XR308 | HICKS 1110 | 83431110 |  | 1.4757 | 1.5015 |  | 22.5 | 0.00061857 | 4062 | 0.053073 | 8251 | 3.2829e-05 | 7448
OROSI 11047753F | OROSI 1104 | 252841104 |  | 1.3672 | 1.129 |  | 18 | 0.0004899 | 5497 | 0.067 | 6057 | 3.2823e-05 | 7449
OLD RIVER 11033851 | OLD RIVER 1103 | 252821103 |  | 6.0146 | 0 |  | 90.8333 | 0.00042653 | 6152 | 0.076864 | 3847 | 3.2813e-05 | 7450
BELLEVUE 2103CB | BELLEVUE 2103 | 43182103 |  | 4.5616 | 1.8702 |  | 77.5 | 0.00050195 | 5372 | 0.066508 | 6185 | 3.2812e-05 | 7451
MC FARLAND 110184604 | MC FARLAND 1101 | 253181101 |  | 4.1723 | 3.7829 |  | 73.5 | 0.00060883 | 4179 | 0.054231 | 7898 | 3.2806e-05 | 7452
MC KEE 1112XR098 | MC KEE 1112 | 83531112 |  | 3.1884 | 3.2205 |  | 47.5 | 0.00060143 | 4284 | 0.05571 | 7638 | 3.2804e-05 | 7453
FULTON 11075058 | FULTON 1107 | 42561107 |  | 0.49458 | 0 |  | 12.5 | 0.00051099 | 5276 | 0.064233 | 6514 | 3.28e-05 | 7454
CLIFF DRIVE 0401197474 | CLIFF DRIVE 0401 | 83230401 |  | 7.7673 | 6.5158 |  | 110.0333 | 0.00056885 | 4673 | 0.05763 | 7341 | 3.2796e-05 | 7455
SANTA MARIA 1105116500 | SANTA MARIA 1105 | 182671105 |  | 1.1458 | 1.5867 |  | 21.3333 | 0.00061295 | 4132 | 0.053592 | 8063 | 3.2789e-05 | 7456
SF M 0403CB | SF M 0403 | 22270403 |  | 3.6858 | 4.0532 |  | 51.75 | 0.0006178 | 4073 | 0.053073 | 8251 | 3.2788e-05 | 7457
PEASE 1104CB | PEASE 1104 | 153751104 |  | 13.3682 | 4.8882 |  | 227.5833 | 0.00055199 | 4849 | 0.061676 | 6803 | 3.2787e-05 | 7458
MONTEREY 0403CB | MONTEREY 0403 | 182090403 |  | 0.0023766 | 0 |  | 0.5 | 0.00061773 | 4075 | 0.053073 | 8251 | 3.2785e-05 | 7459
LLAGAS 2105XR144 | LLAGAS 2105 | 83182105 |  | 4.2839 | 1.7871 |  | 79.8333 | 0.00055303 | 4835 | 0.060948 | 6895 | 3.2768e-05 | 7460
BRENTWOOD 2112CB | BRENTWOOD 2112 | 14592112 |  | 13.1198 | 2.2875 |  | 209.5 | 0.00048875 | 5508 | 0.068511 | 5285 | 3.2768e-05 | 7461
OAKLAND J 1112CB | OAKLAND J 1112 | 12091112 |  | 2.7243 | 0.96019 |  | 43.25 | 0.00061737 | 4080 | 0.053354 | 8153 | 3.2767e-05 | 7462
NORTH TOWER 110470732 | NORTH TOWER 1104 | 42041104 |  | 6.6515 | 4.3421 |  | 104.25 | 0.0005978 | 4326 | 0.055212 | 7721 | 3.2764e-05 | 7463
ALTO 11231222 | ALTO 1123 | 42031123 |  | 0.79425 | 1.7271 |  | 14.5 | 0.00061729 | 4082 | 0.053073 | 8251 | 3.2761e-05 | 7464
LEMOORE 1101746655 | LEMOORE 1101 | 253601101 |  | 0.66895 | 0.41069 |  | 9.5 | 0.00061724 | 4084 | 0.053073 | 8251 | 3.2759e-05 | 7465
LOYOLA 0401LM02 | LOYOLA 0401 | 82160401 |  | 3.6391 | 2.8484 |  | 54.2 | 0.00057314 | 4615 | 0.057458 | 7365 | 3.2754e-05 | 7466
COTTONWOOD 1101CB | COTTONWOOD 1101 | 102931101 | TRUE | 16.5146 | 3.9319 | 0.18792 | 285.1667 | 0.00043128 | 6106 | 0.077513 | 3394 | 3.2745e-05 | 7467
EAST STOCKTON 1102323786 | EAST STOCKTON 1102 | 163131102 |  | 3.0121 | 2.8497 |  | 42.1667 | 0.00061697 | 4085 | 0.053073 | 8252 | 3.2744e-05 | 7468
KINGSBURG 1113235934 | KINGSBURG 1113 | 252241113 |  | 0.018465 | 0 |  | 0.5 | 0.00061683 | 4090 | 0.053073 | 8251 | 3.2737e-05 | 7469
HIGHWAY 1101992028 | HIGHWAY 1101 | 42651101 |  | 1.9095 | 1.3533 |  | 26.3333 | 0.00061662 | 4092 | 0.053073 | 8251 | 3.2726e-05 | 7470
FAIRWAY 1108CB | FAIRWAY 1108 | 182061108 |  | 2.9246 | 1.5674 |  | 45.3333 | 0.00053463 | 5014 | 0.062848 | 6675 | 3.2722e-05 | 7471
BIG LAGOON 1101CB | BIG LAGOON 1101 | 192361101 |  | 3.9392 | 0.57239 |  | 80.5 | 0.00048302 | 5568 | 0.067726 | 5502 | 3.2713e-05 | 7472
OAKLAND X 1101CR222 | OAKLAND X 1101 | 12541101 |  | 1.3426 | 1.3813 |  | 21.3333 | 0.00049882 | 5401 | 0.065368 | 6383 | 3.2713e-05 | 7473
SANTA MARIA 1105M134 | SANTA MARIA 1105 | 182671105 |  | 0.6744 | 0 |  | 6.3333 | 0.00047619 | 5635 | 0.068642 | 5250 | 3.2712e-05 | 7474
SWIFT 2108XR364 | SWIFT 2108 | 83392108 |  | 3.878 | 2.7435 |  | 64.5 | 0.0005722 | 4627 | 0.05739 | 7375 | 3.2709e-05 | 7475
SF H 110588460 | SF H 1105 | 22101105 |  | 9.3397 | 9.6803 |  | 132.3333 | 0.0005484 | 4874 | 0.060382 | 6974 | 3.2696e-05 | 7476
FITCH MOUNTAIN 1111592 | FITCH MOUNTAIN 1111 | 42751111 |  | 0.88114 | 0.012487 |  | 15.6667 | 0.00048794 | 5517 | 0.067 | 6056 | 3.2692e-05 | 7477
HARRIS 11095982 | HARRIS 1109 | 192431109 |  | 3.1039 | 0.79936 |  | 56 | 0.00053071 | 5065 | 0.061713 | 6797 | 3.2683e-05 | 7478
LAMMERS 1103CB | LAMMERS 1103 | 162771103 |  | 7.0688 | 0.44722 |  | 111.3333 | 0.00048913 | 5504 | 0.067116 | 5884 | 3.2683e-05 | 7479
SF G 1101CB | SF G 1101 | 22091101 |  | 1.0212 | 0.59757 |  | 17.0833 | 0.0006158 | 4099 | 0.053073 | 8250 | 3.2682e-05 | 7480
HARTER 1105469850 | HARTER 1105 | 152851105 |  | 9.0747 | 1.5307 |  | 155.5 | 0.00050157 | 5377 | 0.067094 | 5909 | 3.2677e-05 | 7481
JARVIS 1108CB | JARVIS 1108 | 13501108 |  | 4.5545 | 4.8899 |  | 68.75 | 0.00060284 | 4269 | 0.054716 | 7802 | 3.267e-05 | 7482
BUENA VISTA 1103CB | BUENA VISTA 1103 | 182261103 |  | 7.5892 | 3.49 |  | 119.6667 | 0.00057209 | 4629 | 0.057522 | 7357 | 3.2655e-05 | 7483
MERCED 110890500 | MERCED 1108 | 252801108 |  | 7.087 | 1.4314 |  | 123.5 | 0.00048439 | 5551 | 0.068872 | 5212 | 3.2647e-05 | 7484
MT EDEN 1108MR216 | MT EDEN 1108 | 13761108 |  | 5.8105 | 5.4342 |  | 90.5 | 0.000615 | 4106 | 0.053073 | 8251 | 3.264e-05 | 7485
LIVINGSTON 110611500 | LIVINGSTON 1106 | 252261106 |  | 1.809 | 1.4795 |  | 36.3333 | 0.00060527 | 4234 | 0.054077 | 7937 | 3.2639e-05 | 7486
HARRIS 11098862 | HARRIS 1109 | 192431109 |  | 3.3437 | 2.459 |  | 51.3333 | 0.00053983 | 4961 | 0.061232 | 6863 | 3.2639e-05 | 7487
HIGHWAY 1102658 | HIGHWAY 1102 | 42651102 |  | 3.0066 | 2.9517 |  | 45.5 | 0.00059224 | 4390 | 0.054914 | 7763 | 3.2631e-05 | 7488
HARTLEY 1102490 | HARTLEY 1102 | 43211102 |  | 3.7842 | 1.3836 |  | 64 | 0.00041858 | 6238 | 0.076603 | 3981 | 3.2618e-05 | 7489
BELMONT 1103543076 | BELMONT 1103 | 24031103 |  | 2.2976 | 2.1824 |  | 40 | 0.00055457 | 4823 | 0.0596 | 7071 | 3.2617e-05 | 7490
NEWMAN 1101CB | NEWMAN 1101 | 162741101 |  | 3.5998 | 1.2436 |  | 56.8333 | 0.00058147 | 4505 | 0.058235 | 7261 | 3.2615e-05 | 7491
SAN LORENZO 0402CB | SAN LORENZO 0402 | 13460402 |  | 3.9666 | 4.2525 |  | 50.5 | 0.00061453 | 4110 | 0.053073 | 8252 | 3.2615e-05 | 7492
STUART 0406CB | STUART 0406 | 13840406 |  | 2.9367 | 3.4145 |  | 46.5833 | 0.00061443 | 4112 | 0.053073 | 8251 | 3.2609e-05 | 7493
SANTA ROSA A 111095984 | SANTA ROSA A 1110 | 42151110 |  | 1.8694 | 1.1114 |  | 36.5 | 0.00055223 | 4845 | 0.059186 | 7133 | 3.2602e-05 | 7494
BERKELEY F 0411CB | BERKELEY F 0411 | 12060411 |  | 4.4136 | 5.3809 |  | 59.4167 | 0.00061419 | 4117 | 0.053073 | 8253 | 3.2597e-05 | 7495
SAN LEANDRO U 1113CB | SAN LEANDRO U 1113 | 13111113 |  | 7.0152 | 7.4023 |  | 111.75 | 0.00060952 | 4177 | 0.053943 | 7970 | 3.2596e-05 | 7496
LOCKEFORD 21013002 | LOCKEFORD 2101 | 163682101 |  | 6.2998 | 0.73657 |  | 110.5 | 0.00046661 | 5733 | 0.070952 | 4899 | 3.2577e-05 | 7497
ARBUCKLE 110247648 | ARBUCKLE 1102 | 62081102 |  | 3.6983 | 2.1084 |  | 59.6667 | 0.00053838 | 4973 | 0.062603 | 6699 | 3.2574e-05 | 7498
FELLOWS 21031100 | FELLOWS 2103 | 254242103 |  | 17.9409 | 2.4146 |  | 316 | 0.00048599 | 5542 | 0.067066 | 5929 | 3.257e-05 | 7499
CASSERLY 0401CB | CASSERLY 0401 | 83110401 |  | 3.0324 | 1.5339 |  | 43.8333 | 0.00049309 | 5465 | 0.066047 | 6263 | 3.2566e-05 | 7500
MC CALL 110379896 | MC CALL 1103 | 254121103 |  | 3.9912 | 2.3014 |  | 81.5 | 0.0006111 | 4153 | 0.053573 | 8072 | 3.2566e-05 | 7501
ARCATA 11220664 | ARCATA 1122 | 192021122 |  | 9.3121 | 2.045 |  | 158.5 | 0.00048602 | 5541 | 0.067004 | 6039 | 3.2566e-05 | 7502
MC KEE 1105773372 | MC KEE 1105 | 83531105 |  | 2.8221 | 3.8848 |  | 44 | 0.00061085 | 4157 | 0.053232 | 8204 | 3.2563e-05 | 7503
SERRAMONTE 110359766 | SERRAMONTE 1103 | 22861103 |  | 1.9086 | 1.3899 |  | 25.8333 | 0.00061269 | 4134 | 0.053342 | 8160 | 3.2562e-05 | 7504
SALINAS 110525049 | SALINAS 1105 | 182011105 |  | 1.4867 | 1.8234 |  | 23.3333 | 0.00061338 | 4129 | 0.053073 | 8251 | 3.2554e-05 | 7505
ARCATA 112293912 | ARCATA 1122 | 192021122 |  | 11.2766 | 2.4507 |  | 215 | 0.0004876 | 5525 | 0.066611 | 6164 | 3.2547e-05 | 7506
COALINGA NO 1 1109CB | COALINGA NO 1 1109 | 252161109 |  | 5.7026 | 0.22535 |  | 85.75 | 0.00049345 | 5463 | 0.066805 | 6120 | 3.2542e-05 | 7507
ARBUCKLE 1102CB | ARBUCKLE 1102 | 62081102 |  | 5.0749 | 0.48442 |  | 77.4167 | 0.00043632 | 6052 | 0.076037 | 4187 | 3.2539e-05 | 7508
HORSESHOE 11011682 | HORSESHOE 1101 | 152571101 | TRUE | 9.5682 | 0.86289 | 0.15045 | 157.5 | 0.00027235 | 8599 | 0.11698 | 3274 | 3.2539e-05 | 7509
COALINGA NO 1 11089860 | COALINGA NO 1 1108 | 252161108 |  | 1.912 | 2.3117 |  | 32.3333 | 0.00061265 | 4137 | 0.053339 | 8162 | 3.2534e-05 | 7510
PUEBLO 2103489964 | PUEBLO 2103 | 43292103 |  | 1.5986 | 0.68293 |  | 29 | 0.00052223 | 5156 | 0.063451 | 6617 | 3.2523e-05 | 7511
PORTOLA 040240323 | PORTOLA 0402 | 22610402 |  | 0.65332 | 0.83497 |  | 16.3333 | 0.00052901 | 5086 | 0.063499 | 6614 | 3.2521e-05 | 7512
DIXON 1102CB | DIXON 1102 | 62061102 |  | 6.3957 | 1.9701 |  | 97.8333 | 0.00049126 | 5483 | 0.069652 | 5091 | 3.2519e-05 | 7513
LAKEWOOD 2223289858 | LAKEWOOD 2223 | 13532223 |  | 0.39299 | 0.21533 |  | 6.1667 | 0.00061265 | 4136 | 0.053073 | 8251 | 3.2515e-05 | 7514
RICHMOND R 1127BR350 | RICHMOND R 1127 | 13471127 |  | 0.034364 | 0 |  | 1.5 | 0.00061261 | 4138 | 0.053073 | 8251 | 3.2513e-05 | 7515
SONOMA 1107126 | SONOMA 1107 | 42721107 |  | 11.3467 | 1.4538 |  | 217.5 | 0.00047615 | 5636 | 0.068335 | 5321 | 3.2511e-05 | 7516
OAKLAND X 0402CR406 | OAKLAND X 0402 | 12540402 |  | 1.2925 | 1.2439 |  | 20.6667 | 0.00053476 | 5012 | 0.060281 | 6987 | 3.2505e-05 | 7517
FRENCH CAMP 1101841572 | FRENCH CAMP 1101 | 163291101 |  | 5.6129 | 2.1737 |  | 104.8333 | 0.0005132 | 5252 | 0.065222 | 6403 | 3.2495e-05 | 7518
PORTOLA 0402CB | PORTOLA 0402 | 22610402 |  | 2.8419 | 2.7429 |  | 48.6667 | 0.00056812 | 4680 | 0.057988 | 7292 | 3.2486e-05 | 7519
WOODSIDE 1104CB | WOODSIDE 1104 | 24251104 |  | 6.8435 | 3.4541 |  | 140.5 | 0.00048543 | 5546 | 0.066578 | 6174 | 3.2463e-05 | 7520
BELMONT 0402CB | BELMONT 0402 | 24030402 |  | 6.9891 | 6.2136 |  | 90.25 | 0.00060815 | 4189 | 0.053297 | 8180 | 3.2458e-05 | 7521
SF E 0407CB | SF E 0407 | 22070407 |  | 0.94277 | 1.0581 |  | 18.0833 | 0.00061124 | 4151 | 0.053073 | 8250 | 3.244e-05 | 7522
MC KEE 111275342 | MC KEE 1112 | 83531112 |  | 2.823 | 3.543 |  | 39.3333 | 0.00061117 | 4152 | 0.053073 | 8251 | 3.2436e-05 | 7523
CAMPHORA 110122412 | CAMPHORA 1101 | 182071101 | FALSE | 15.2983 | 1.3211 | 2.0456 | 314.5 | 0.00021243 | 9835 | 0.30515 | 3015 | 3.2414e-05 | 7524
GUSTINE 110246166 | GUSTINE 1102 | 163111102 |  | 1.5752 | 0.56333 |  | 23.5 | 0.00059658 | 4343 | 0.054108 | 7927 | 3.2411e-05 | 7525
MENLO 110235722 | MENLO 1102 | 24131102 |  | 4.7783 | 3.5475 |  | 81 | 0.00051253 | 5261 | 0.063556 | 6605 | 3.2401e-05 | 7526
SF H 110213885 | SF H 1102 | 22101102 |  | 1.3308 | 1.5806 |  | 27 | 0.00060436 | 4251 | 0.053974 | 7963 | 3.2397e-05 | 7527
HALF MOON BAY 11016369 | HALF MOON BAY 1101 | 24101101 |  | 1.3826 | 0.49966 |  | 26.8333 | 0.00048213 | 5579 | 0.067248 | 5764 | 3.2386e-05 | 7528
MT EDEN 1108MR481 | MT EDEN 1108 | 13761108 |  | 7.744 | 8.0263 |  | 107.3333 | 0.00061017 | 4167 | 0.053073 | 8252 | 3.2383e-05 | 7529
OROVILLE 110313028 | OROVILLE 1103 | 102521103 |  | 8.96 | 4.1779 |  | 153 | 0.0004977 | 5418 | 0.065334 | 6386 | 3.2378e-05 | 7530
LIVINGSTON 110637390 | LIVINGSTON 1106 | 252261106 |  | 1.9627 | 1.3782 |  | 35.8333 | 0.00060423 | 4254 | 0.053553 | 8083 | 3.2371e-05 | 7531
DUMBARTON 1104MR667 | DUMBARTON 1104 | 14471104 |  | 5.7422 | 3.7202 |  | 96.5 | 0.00060992 | 4169 | 0.053073 | 8251 | 3.237e-05 | 7532
TARAVAL 0402CB | TARAVAL 0402 | 22500402 |  | 3.186 | 4.5071 |  | 48.6667 | 0.00060414 | 4255 | 0.054203 | 7901 | 3.2367e-05 | 7533
MOSHER 2111CB | MOSHER 2111 | 163722111 |  | 0.93342 | 0.20011 |  | 21 | 0.00053575 | 5001 | 0.063908 | 6557 | 3.2364e-05 | 7534
DUMBARTON 1108MR488 | DUMBARTON 1108 | 14471108 |  | 1.7395 | 0.32752 |  | 39 | 0.00060978 | 4172 | 0.053073 | 8251 | 3.2362e-05 | 7535
CORNING 110366390 | CORNING 1103 | 103331103 |  | 4.5354 | 1.7309 |  | 81 | 0.00050883 | 5299 | 0.065134 | 6413 | 3.2349e-05 | 7536
LINCOLN 110251600 | LINCOLN 1102 | 153701102 |  | 1.7444 | 0.01232 |  | 33 | 0.0004828 | 5570 | 0.067 | 6057 | 3.2347e-05 | 7537
SHEPHERD 2112R1743 | SHEPHERD 2112 | 252062112 |  | 2.3011 | 0.15813 |  | 38 | 0.00045603 | 5856 | 0.072825 | 4680 | 3.2343e-05 | 7538
JUDAH 0401CB | JUDAH 0401 | 22400401 |  | 3.6852 | 6.346 |  | 74.8333 | 0.00060847 | 4187 | 0.053398 | 8139 | 3.233e-05 | 7539
HURON 111675368 | HURON 1116 | 253161116 |  | 2.6437 | 0.10232 |  | 42 | 0.00044575 | 5955 | 0.072476 | 4718 | 3.2325e-05 | 7540
KERN OIL 1108CB | KERN OIL 1108 | 252721108 |  | 7.6193 | 3.5094 |  | 121.8333 | 0.00053861 | 4971 | 0.061359 | 6843 | 3.2319e-05 | 7541
MOUNTAIN VIEW 1109LM58 | MOUNTAIN VIEW 1109 | 82031109 |  | 1.5131 | 0.97495 |  | 25 | 0.00057908 | 4536 | 0.056287 | 7534 | 3.2313e-05 | 7542
IGNACIO 1102CB | IGNACIO 1102 | 42481102 |  | 1.3385 | 0.25165 |  | 22.8333 | 0.00056141 | 4738 | 0.058897 | 7171 | 3.2312e-05 | 7543
PUEBLO 2102618 | PUEBLO 2102 | 43292102 |  | 7.8602 | 0.79948 |  | 160.5 | 0.00045569 | 5859 | 0.0711 | 4884 | 3.2312e-05 | 7544
FIREBAUGH 1102CB | FIREBAUGH 1102 | 253471102 |  | 6.4518 | 3.4216 |  | 123.3333 | 0.00048611 | 5540 | 0.067808 | 5473 | 3.2304e-05 | 7545
OAKLAND X 1115CR218 | OAKLAND X 1115 | 12541115 |  | 1.9138 | 2.1224 |  | 30.8333 | 0.00060866 | 4181 | 0.053073 | 8251 | 3.2303e-05 | 7546
WEST FRESNO 111172322 | WEST FRESNO 1111 | 253731111 |  | 9.433 | 3.3996 |  | 172 | 0.00048645 | 5533 | 0.068244 | 5348 | 3.2298e-05 | 7547
VICTOR 110137012 | VICTOR 1101 | 163281101 |  | 11.436 | 3.2056 |  | 201.8333 | 0.0004589 | 5817 | 0.072827 | 4679 | 3.2286e-05 | 7548
CRESSEY 2103505894 | CRESSEY 2103 | 254702103 |  | 0.029934 | 0 |  | 0.5 | 0.00041705 | 6254 | 0.0774 | 3397 | 3.2279e-05 | 7549
SF M 0401CB | SF M 0401 | 22270401 |  | 3.7312 | 4.9737 |  | 49.1167 | 0.00060807 | 4191 | 0.053073 | 8251 | 3.2272e-05 | 7550
VINA 110198144 | VINA 1101 | 103581101 |  | 5.652 | 1.0958 |  | 114 | 0.00048087 | 5595 | 0.067199 | 5812 | 3.2266e-05 | 7551
NEWARK 12KV 1103MR247 | NEWARK 12KV 1103 | 12221103 |  | 8.5469 | 9.1888 |  | 131.8333 | 0.00060788 | 4196 | 0.053073 | 8252 | 3.2262e-05 | 7552
MARINA (F) 1102CB | MARINA (F) 1102 | 22781102 |  | 0.0014205 | 0 |  | 1 | 0.00060765 | 4200 | 0.053073 | 8251 | 3.225e-05 | 7553
ELK 110137434 | ELK 1101 | 42981101 |  | 2.7129 | 0.25004 |  | 48.3333 | 0.00029691 | 8066 | 0.10808 | 3295 | 3.2248e-05 | 7554
SHEPHERD 211275088 | SHEPHERD 2112 | 252062112 |  | 2.3399 | 0.21545 |  | 48 | 0.00046634 | 5737 | 0.071065 | 4889 | 3.2245e-05 | 7555
MENDOTA 1103CB | MENDOTA 1103 | 252311103 |  | 11.9494 | 1.2173 |  | 176.5833 | 0.00046181 | 5785 | 0.071318 | 4853 | 3.2243e-05 | 7556
ALTO 112332448 | ALTO 1123 | 42031123 |  | 3.5096 | 1.7597 |  | 57.8333 | 0.00056524 | 4704 | 0.057343 | 7387 | 3.2239e-05 | 7557
GREEN VALLEY 210310932 | GREEN VALLEY 2103 | 83192103 |  | 8.8945 | 3.0066 |  | 143.8333 | 0.00052071 | 5170 | 0.063183 | 6646 | 3.2235e-05 | 7558
DUMBARTON 1102MR466 | DUMBARTON 1102 | 14471102 |  | 8.6667 | 8.2311 |  | 127.8333 | 0.00059434 | 4367 | 0.053999 | 7953 | 3.223e-05 | 7559
KERMAN 110337770 | KERMAN 1103 | 252711103 |  | 3.7144 | 4.637 |  | 63.3333 | 0.00060727 | 4205 | 0.053073 | 8250 | 3.2229e-05 | 7560
FAIRWAY 1104M20 | FAIRWAY 1104 | 182061104 |  | 5.7859 | 6.7784 |  | 96 | 0.00050228 | 5369 | 0.064026 | 6538 | 3.2229e-05 | 7561
SF G 0414CB | SF G 0414 | 22090414 |  | 0.91928 | 1.1186 |  | 13 | 0.00060718 | 4210 | 0.053073 | 8251 | 3.2225e-05 | 7562
INDUSTRIAL ACRES 0413CB | INDUSTRIAL ACRES 0413 | 182300413 |  | 3.7054 | 3.408 |  | 55.6667 | 0.0006071 | 4213 | 0.053073 | 8252 | 3.2221e-05 | 7563
BELLEVUE 2101500 | BELLEVUE 2101 | 43182101 |  | 5.5108 | 4.5982 |  | 83.6667 | 0.00060693 | 4216 | 0.053073 | 8250 | 3.2211e-05 | 7564
MC KEE 1107XR462 | MC KEE 1107 | 83531107 |  | 4.9362 | 4.2286 |  | 86.3333 | 0.00051124 | 5273 | 0.063565 | 6603 | 3.2211e-05 | 7565
SAN CARLOS 1102CB | SAN CARLOS 1102 | 24181102 |  | 0.35649 | 0.075815 |  | 8.95 | 0.00055863 | 4766 | 0.056574 | 7496 | 3.221e-05 | 7566
SUISUN 1101CB | SUISUN 1101 | 62131101 |  | 6.1748 | 2.0252 |  | 118.5 | 0.00051186 | 5266 | 0.063947 | 6552 | 3.2207e-05 | 7567
PLAINFIELD 110623102 | PLAINFIELD 1106 | 63441106 |  | 0.45239 | 0.090491 |  | 5.5 | 0.0005876 | 4449 | 0.055284 | 7710 | 3.2196e-05 | 7568
21ST AVENUE 0401CB | 21ST AVENUE 0401 | 22550401 |  | 1.8965 | 3.4416 |  | 37.3333 | 0.00060658 | 4220 | 0.053073 | 8251 | 3.2193e-05 | 7569
BASALT 110175886 | BASALT 1101 | 42461101 |  | 8.1356 | 5.3526 |  | 126.5 | 0.00055119 | 4853 | 0.058738 | 7192 | 3.2187e-05 | 7570
UKIAH 11112504 | UKIAH 1111 | 42771111 |  | 2.2747 | 0.50383 |  | 30 | 0.00049938 | 5398 | 0.064438 | 6492 | 3.2183e-05 | 7571
COTTLE 1703CB | COTTLE 1703 | 163711703 |  | 1.9523 | 0.30585 |  | 22.8333 | 0.00043413 | 6069 | 0.074209 | 4525 | 3.2172e-05 | 7572
WOLFE 1110CB | WOLFE 1110 | 83671110 |  | 2.0224 | 1.6827 |  | 39 | 0.00060456 | 4247 | 0.053293 | 8183 | 3.217e-05 | 7573
PARSONS 0402CB | PARSONS 0402 | 13660402 |  | 3.4277 | 3.0895 |  | 41.6667 | 0.00060601 | 4227 | 0.053073 | 8251 | 3.2163e-05 | 7574
PETALUMA C 110856774 | PETALUMA C 1108 | 42631108 | TRUE | 2.7537 | 2.8586 | 0.4861 | 42 | 0.00059757 | 4332 | 0.053404 | 8133 | 3.2157e-05 | 7575
GONZALES 1101CB | GONZALES 1101 | 182131101 |  | 10.6625 | 3.9282 |  | 198.0833 | 0.00050833 | 5304 | 0.06477 | 6467 | 3.2154e-05 | 7576
MT EDEN 1110MR200 | MT EDEN 1110 | 13761110 |  | 0.85829 | 0.29785 |  | 15.5 | 0.00055549 | 4811 | 0.060369 | 6976 | 3.2146e-05 | 7577
SALINAS 110297880 | SALINAS 1102 | 182011102 |  | 2.6276 | 1.8449 |  | 46.5 | 0.00056644 | 4694 | 0.058614 | 7209 | 3.2143e-05 | 7578
GREEN VALLEY 21039959 | GREEN VALLEY 2103 | 83192103 |  | 1.9759 | 1.0384 |  | 38.5 | 0.00046889 | 5708 | 0.068621 | 5259 | 3.2139e-05 | 7579
WYANDOTTE 110213916 | WYANDOTTE 1102 | 102911102 |  | 11.6664 | 4.144 |  | 193.8333 | 0.00049427 | 5448 | 0.065437 | 6371 | 3.2139e-05 | 7580
MONROE 2107434 | MONROE 2107 | 43302107 |  | 0.31732 | 0.43273 |  | 8 | 0.0006053 | 4233 | 0.053073 | 8251 | 3.2125e-05 | 7581
EL CERRITO G 1108BR346 | EL CERRITO G 1108 | 12501108 |  | 7.0767 | 7.9993 |  | 111.3333 | 0.00057913 | 4534 | 0.055909 | 7593 | 3.2123e-05 | 7582
FAIRHAVEN 1104CB | FAIRHAVEN 1104 | 192451104 |  | 3.6133 | 0.99512 |  | 65.5 | 0.00048208 | 5580 | 0.066894 | 6096 | 3.2122e-05 | 7583
SERRAMONTE 110346872 | SERRAMONTE 1103 | 22861103 |  | 7.1167 | 8.1846 |  | 108.3333 | 0.00053193 | 5051 | 0.060897 | 6901 | 3.2116e-05 | 7584
BLUE LAKE 11021024 | BLUE LAKE 1102 | 192181102 |  | 4.946 | 0.95137 |  | 93.5 | 0.00047883 | 5611 | 0.067065 | 5930 | 3.2109e-05 | 7585
SAN CARLOS 11049010 | SAN CARLOS 1104 | 24181104 |  | 4.0548 | 3.4211 |  | 68.1667 | 0.00050726 | 5313 | 0.063856 | 6564 | 3.2105e-05 | 7586
PENNGROVE 1101190 | PENNGROVE 1101 | 43471101 |  | 2.3447 | 0.1289 |  | 37 | 0.00047882 | 5612 | 0.067039 | 5961 | 3.2095e-05 | 7587
OAKLAND L 1108CB | OAKLAND L 1108 | 12111108 |  | 0.0014205 | 0 |  | 0.5 | 0.0006047 | 4245 | 0.053073 | 8251 | 3.2093e-05 | 7588
OROSI 11047510 | OROSI 1104 | 252841104 |  | 4.539 | 3.2121 |  | 79 | 0.00047649 | 5631 | 0.06833 | 5323 | 3.209e-05 | 7589
MENLO 0402CB | MENLO 0402 | 24130402 |  | 6.1317 | 4.0077 |  | 117.1667 | 0.00048796 | 5516 | 0.066023 | 6267 | 3.2084e-05 | 7590
HILLSDALE 04059158 | HILLSDALE 0405 | 24110405 |  | 2.0846 | 2.3499 |  | 34.8333 | 0.0006044 | 4250 | 0.053073 | 8250 | 3.2077e-05 | 7591
SOQUEL 0402CB | SOQUEL 0402 | 83300402 |  | 6.5536 | 5.1271 |  | 88 | 0.00058583 | 4468 | 0.055224 | 7719 | 3.2076e-05 | 7592
SOLEDAD 2105328826 | SOLEDAD 2105 | 182052105 |  | 3.2464 | 0.12486 |  | 66.5 | 0.00047622 | 5634 | 0.067469 | 5621 | 3.2072e-05 | 7593
JANES CREEK 1101CB | JANES CREEK 1101 | 192391101 |  | 6.9698 | 0.9583 |  | 125.8333 | 0.00048879 | 5507 | 0.06598 | 6277 | 3.2071e-05 | 7594
SANGER 111087626 | SANGER 1110 | 252351110 |  | 1.9814 | 1.196 |  | 29 | 0.00049192 | 5473 | 0.066075 | 6254 | 3.2044e-05 | 7595
BRENTWOOD 2113CB | BRENTWOOD 2113 | 14592113 |  | 8.1779 | 1.0557 |  | 134 | 0.00047219 | 5675 | 0.068876 | 5209 | 3.2044e-05 | 7596
CASTRO VALLEY 1103CB | CASTRO VALLEY 1103 | 14091103 |  | 4.9442 | 5.5998 |  | 89.8333 | 0.00059121 | 4401 | 0.054003 | 7951 | 3.2043e-05 | 7597
PLAINFIELD 1106CB | PLAINFIELD 1106 | 63441106 |  | 8.8507 | 2.5175 |  | 144.3333 | 0.00045266 | 5896 | 0.072343 | 4741 | 3.204e-05 | 7598
EL CERRITO G 1114BR184 | EL CERRITO G 1114 | 12501114 |  | 0.016679 | 0 |  | 0.33333 | 0.00060364 | 4260 | 0.053073 | 8251 | 3.2037e-05 | 7599
GREEN VALLEY 210112126 | GREEN VALLEY 2101 | 83192101 |  | 11.8195 | 3.3934 |  | 216.8333 | 0.00048884 | 5506 | 0.065697 | 6326 | 3.2021e-05 | 7600
MARYSVILLE 110399726 | MARYSVILLE 1103 | 152011103 |  | 0.14613 | 0.012037 |  | 4.5 | 0.00060327 | 4261 | 0.053073 | 8251 | 3.2017e-05 | 7601
TAFT 1103CB | TAFT 1103 | 252081103 |  | 16.0817 | 9.7729 |  | 256.8333 | 0.00052558 | 5118 | 0.062223 | 6742 | 3.2002e-05 | 7602
BUTTE 110782496 | BUTTE 1107 | 103081107 |  | 0.14358 | 0 |  | 2 | 0.00047758 | 5624 | 0.067 | 6057 | 3.1998e-05 | 7603
PUEBLO 11053022 | PUEBLO 1105 | 43291105 |  | 6.4873 | 0.42973 |  | 121.3333 | 0.00047601 | 5638 | 0.067244 | 5769 | 3.199e-05 | 7604
ATWATER 110411860 | ATWATER 1104 | 253611104 |  | 4.7034 | 4.3245 |  | 73.8333 | 0.00060274 | 4270 | 0.053073 | 8252 | 3.1989e-05 | 7605
SANGER 1106802310 | SANGER 1106 | 252351106 |  | 0.014354 | 0 |  | 0.5 | 0.00060264 | 4272 | 0.053073 | 8251 | 3.1984e-05 | 7606
JARVIS 1111CB | JARVIS 1111 | 13501111 |  | 3.9966 | 2.6479 |  | 72.5 | 0.00055784 | 4782 | 0.05736 | 7382 | 3.1982e-05 | 7607
NORTH TOWER 110295588 | NORTH TOWER 1102 | 42041102 |  | 3.0241 | 1.4795 |  | 51.6667 | 0.00055267 | 4839 | 0.057081 | 7428 | 3.1979e-05 | 7608
CORDELIA 111015722 | CORDELIA 1110 | 62701110 |  | 1.4529 | 0.31114 |  | 26.5 | 0.00047494 | 5649 | 0.067392 | 5676 | 3.1978e-05 | 7609
PORTOLA 0401CB | PORTOLA 0401 | 22610401 |  | 2.415 | 2.6662 |  | 42.8333 | 0.00059907 | 4310 | 0.053357 | 8151 | 3.1974e-05 | 7610
MILLBRAE 040475548 | MILLBRAE 0404 | 22690404 |  | 3.4597 | 3.1385 |  | 55 | 0.00055661 | 4798 | 0.057815 | 7324 | 3.1973e-05 | 7611
HORSESHOE 1105CB | HORSESHOE 1105 | 152571105 |  | 2.2654 | 0.35215 |  | 40 | 0.00048191 | 5581 | 0.066673 | 6146 | 3.1971e-05 | 7612
SANTA ROSA A 1103258 | SANTA ROSA A 1103 | 42151103 |  | 1.2244 | 0.756 |  | 23.5 | 0.00051497 | 5236 | 0.061666 | 6806 | 3.1961e-05 | 7613
RIPON 17019498 | RIPON 1701 | 163801701 |  | 4.6418 | 0.77066 |  | 83 | 0.00046637 | 5736 | 0.070047 | 5037 | 3.1961e-05 | 7614
CASTRO VALLEY 1102MR204 | CASTRO VALLEY 1102 | 14091102 |  | 2.9453 | 1.9939 |  | 51.5 | 0.00052112 | 5165 | 0.060035 | 7015 | 3.1958e-05 | 7615
LAKEVILLE 1105CB | LAKEVILLE 1105 | 43371105 |  | 4.1946 | 1.8222 |  | 74.5 | 0.00054756 | 4884 | 0.05938 | 7100 | 3.1957e-05 | 7616
BLUE LAKE 11024624 | BLUE LAKE 1102 | 192181102 |  | 4.5485 | 0.35928 |  | 86 | 0.00047642 | 5633 | 0.067144 | 5858 | 3.1957e-05 | 7617
SAN RAMON 2104MR373 | SAN RAMON 2104 | 14232104 |  | 0.76892 | 0.0022776 |  | 15.5 | 0.00060213 | 4275 | 0.053073 | 8251 | 3.1956e-05 | 7618
SF K 0407CB | SF K 0407 | 22130407 |  | 1.2821 | 1.6555 |  | 22.8333 | 0.0005935 | 4377 | 0.054138 | 7916 | 3.1942e-05 | 7619
DIXON LANDING 2109MR211 | DIXON LANDING 2109 | 14722109 |  | 2.0157 | 0.31796 |  | 41.5 | 0.00056786 | 4684 | 0.059114 | 7144 | 3.1904e-05 | 7620
MAGUNDEN 1108160464 | MAGUNDEN 1108 | 252771108 |  | 3.7748 | 0.45923 |  | 69 | 0.00045676 | 5849 | 0.069825 | 5070 | 3.1898e-05 | 7621
EAST MARYSVILLE 11051244 | EAST MARYSVILLE 1105 | 152331105 |  | 10.6556 | 2.2911 |  | 176.3333 | 0.00047733 | 5625 | 0.070298 | 4981 | 3.1891e-05 | 7622
HURON 1112CB | HURON 1112 | 253161112 |  | 5.6754 | 2.427 |  | 89.5 | 0.00051781 | 5196 | 0.063027 | 6660 | 3.189e-05 | 7623
SAN LEANDRO U 1110MR361 | SAN LEANDRO U 1110 | 13111110 |  | 5.28 | 5.5458 |  | 70.1667 | 0.00060021 | 4296 | 0.053419 | 8122 | 3.1889e-05 | 7624
CLAYTON 221465785 | CLAYTON 2214 | 12022214 |  | 2.4218 | 2.1996 |  | 43.5 | 0.00057324 | 4614 | 0.055794 | 7617 | 3.1888e-05 | 7625
MT EDEN 1109MR523 | MT EDEN 1109 | 13761109 |  | 12.6675 | 12.7649 |  | 199.5833 | 0.00060083 | 4288 | 0.053073 | 8251 | 3.1887e-05 | 7626
WESTLAKE 0403CB | WESTLAKE 0403 | 22600403 |  | 1.7559 | 1.4403 |  | 33.8333 | 0.00050638 | 5324 | 0.063748 | 6572 | 3.1887e-05 | 7627
CHOWCHILLA 1106CB | CHOWCHILLA 1106 | 254101106 |  | 7.2006 | 0.84459 |  | 127.4167 | 0.00043895 | 6022 | 0.073776 | 4573 | 3.1886e-05 | 7628
MESA 1103198354 | MESA 1103 | 182821103 | FALSE | 9.5002 | 0.53543 | 8.568 | 144.5 | 2.4696e-05 | 11147 | 1.2954 | 2007 | 3.1881e-05 | 7629
PAUL SWEET 210716004 | PAUL SWEET 2107 | 83252107 |  | 6.9224 | 4.4223 |  | 89.8667 | 0.00058993 | 4416 | 0.054436 | 7856 | 3.1878e-05 | 7630
SANTA ROSA A 1110184 | SANTA ROSA A 1110 | 42151110 |  | 3.3871 | 2.4934 |  | 51.8333 | 0.00059804 | 4324 | 0.053307 | 8173 | 3.1877e-05 | 7631
TULUCAY 11019999 | TULUCAY 1101 | 42301101 |  | 1.606 | 0 |  | 32 | 0.00046265 | 5777 | 0.069298 | 5145 | 3.1877e-05 | 7632
SF H 110868272 | SF H 1108 | 22101108 |  | 1.0535 | 1.645 |  | 20.7833 | 0.00060048 | 4293 | 0.053073 | 8251 | 3.1869e-05 | 7633
SANGER 1118CB | SANGER 1118 | 252351118 |  | 9.3071 | 1.136 |  | 157.5 | 0.00041134 | 6320 | 0.0774 | 3397 | 3.1838e-05 | 7634
TIDEWATER 210618982 | TIDEWATER 2106 | 14652106 |  | 0.044806 | 0 |  | 0.5 | 0.00047414 | 5658 | 0.06714 | 5862 | 3.1834e-05 | 7635
KERMAN 110333316 | KERMAN 1103 | 252711103 |  | 2.9533 | 1.7028 |  | 47.3333 | 0.00057972 | 4522 | 0.056413 | 7513 | 3.1833e-05 | 7636
RENFRO 2105107332 | RENFRO 2105 | 254572105 |  | 2.2635 | 0.62209 |  | 34.3333 | 0.00056489 | 4710 | 0.056659 | 7480 | 3.1829e-05 | 7637
ANITA 11052572 | ANITA 1105 | 102841105 |  | 6.7398 | 0.56945 |  | 120.5 | 0.00049744 | 5419 | 0.064945 | 6446 | 3.1827e-05 | 7638
POINT PINOLE 1102CB | POINT PINOLE 1102 | 14261102 |  | 9.5801 | 8.4811 |  | 146.5 | 0.00054247 | 4930 | 0.059151 | 7139 | 3.1821e-05 | 7639
GEYSERVILLE 1101480 | GEYSERVILLE 1101 | 42891101 | FALSE | 15.9319 | 1.3779 | 0.80398 | 318.5 | 0.00032246 | 7587 | 0.14649 | 3214 | 3.1819e-05 | 7640
CLARKSVILLE 211011112 | CLARKSVILLE 2110 | 153612110 |  | 0.046133 | 0 |  | 1 | 0.0004744 | 5656 | 0.06707 | 5925 | 3.1818e-05 | 7641
CASTROVILLE 2103676150 | CASTROVILLE 2103 | 182352103 |  | 0.016299 | 0 |  | 0.5 | 0.00047487 | 5651 | 0.067 | 6057 | 3.1816e-05 | 7642
MENDOTA 110249344 | MENDOTA 1102 | 252311102 |  | 0.02482 | 0 |  | 0.33333 | 0.00041106 | 6322 | 0.0774 | 3396 | 3.1816e-05 | 7643
BAY MEADOWS 1104714234 | BAY MEADOWS 1104 | 24011104 |  | 1.7739 | 1.4268 |  | 21.3333 | 0.00059938 | 4301 | 0.053073 | 8251 | 3.1811e-05 | 7644
CLEAR LAKE 1102CB | CLEAR LAKE 1102 | 42141102 |  | 11.1188 | 2.6251 |  | 181.5 | 0.00046176 | 5786 | 0.069576 | 5109 | 3.1808e-05 | 7645
WOLFE 1106CB | WOLFE 1106 | 83671106 |  | 2.7344 | 4.364 |  | 39.5 | 0.00059929 | 4304 | 0.053073 | 8251 | 3.1806e-05 | 7646
PETALUMA C 1105CB | PETALUMA C 1105 | 42631105 |  | 9.2671 | 6.1676 |  | 154.5 | 0.00057989 | 4520 | 0.054897 | 7766 | 3.1791e-05 | 7647
SAN MIGUEL 1104R66 | SAN MIGUEL 1104 | 182661104 |  | 45.1349 | 0.54814 |  | 801.5 | 8.3987e-05 | 11098 | 0.50899 | 2815 | 3.1788e-05 | 7648
STAGG 21076446 | STAGG 2107 | 162422107 |  | 0.52297 | 0 |  | 9.3333 | 0.00045053 | 5916 | 0.073925 | 4562 | 3.1776e-05 | 7649
OCEAN 040197445 | OCEAN 0401 | 22580401 |  | 1.3243 | 1.6973 |  | 21 | 0.00059866 | 4315 | 0.053073 | 8251 | 3.1772e-05 | 7650
CORNING 110466230 | CORNING 1104 | 103331104 |  | 1.7191 | 0.10422 |  | 29 | 0.00047409 | 5659 | 0.067014 | 6012 | 3.1771e-05 | 7651
HUMBOLDT BAY 1101898396 | HUMBOLDT BAY 1101 | 192341101 |  | 1.1053 | 0.61222 |  | 28 | 0.00054493 | 4910 | 0.059971 | 7023 | 3.1768e-05 | 7652
NORTH TOWER 110291992 | NORTH TOWER 1102 | 42041102 |  | 1.6367 | 1.3205 |  | 23.6667 | 0.00059836 | 4319 | 0.053073 | 8250 | 3.1756e-05 | 7653
SAN LEANDRO U 1106MR134 | SAN LEANDRO U 1106 | 13111106 |  | 7.8249 | 6.3208 |  | 110.8333 | 0.00058708 | 4454 | 0.054871 | 7776 | 3.1746e-05 | 7654
KERN OIL 1116CB | KERN OIL 1116 | 252721116 |  | 2.0168 | 0.16518 |  | 32.75 | 0.00055642 | 4799 | 0.059092 | 7146 | 3.1745e-05 | 7655
ORTIGA 11059950 | ORTIGA 1105 | 254311105 |  | 7.7802 | 3.5295 |  | 123.3333 | 0.00053997 | 4958 | 0.060702 | 6925 | 3.1738e-05 | 7656
JARVIS 1112MR490 | JARVIS 1112 | 13501112 |  | 1.3906 | 0.68406 |  | 29.5 | 0.00059794 | 4325 | 0.053073 | 8251 | 3.1734e-05 | 7657
KEARNEY 1114188548 | KEARNEY 1114 | 252701114 |  | 3.8187 | 1.3817 |  | 62.8333 | 0.00048627 | 5538 | 0.066898 | 6092 | 3.1731e-05 | 7658
FIGARDEN 2102495424 | FIGARDEN 2102 | 254552102 |  | 1.9521 | 0.26701 |  | 35.5 | 0.00043643 | 6050 | 0.073631 | 4591 | 3.1729e-05 | 7659
HILLSDALE 040344318 | HILLSDALE 0403 | 24110403 |  | 3.0359 | 2.3582 |  | 41.45 | 0.00059632 | 4345 | 0.05314 | 8235 | 3.1721e-05 | 7660
FAIRWAY 110312087 | FAIRWAY 1103 | 182061103 |  | 1.162 | 1.7281 |  | 19.5 | 0.00054675 | 4892 | 0.057353 | 7384 | 3.1719e-05 | 7661
GIFFEN 11029600 | GIFFEN 1102 | 253151102 |  | 0.0055642 | 0 |  | 1 | 0.0004098 | 6336 | 0.0774 | 3397 | 3.1718e-05 | 7662
SAN JOSE B 110749542 | SAN JOSE B 1107 | 82261107 |  | 0.2328 | 0.28882 |  | 5.0833 | 0.00059762 | 4330 | 0.053073 | 8251 | 3.1717e-05 | 7663
CHEROKEE 110211666 | CHEROKEE 1102 | 163651102 |  | 0.58379 | 0.066105 |  | 13.5 | 0.00047024 | 5699 | 0.066588 | 6172 | 3.1714e-05 | 7664
WEST FRESNO 110149622 | WEST FRESNO 1101 | 253731101 |  | 0.017604 | 0 |  | 0.5 | 0.00059747 | 4334 | 0.053073 | 8251 | 3.1709e-05 | 7665
GATES 1110CB | GATES 1110 | 253931110 |  | 4.395 | 0.12677 |  | 65.6667 | 0.00046486 | 5750 | 0.069585 | 5106 | 3.1702e-05 | 7666
HAMILTON A 1101CB | HAMILTON A 1101 | 102121101 |  | 9.0641 | 2.3844 |  | 161.5 | 0.00048346 | 5566 | 0.068138 | 5371 | 3.1702e-05 | 7667
MAPLE 0401CB | MAPLE 0401 | 13520401 |  | 3.6571 | 4.3406 |  | 51.1667 | 0.0005972 | 4337 | 0.053073 | 8251 | 3.1695e-05 | 7668
HALF MOON BAY 11028910 | HALF MOON BAY 1102 | 24101102 |  | 6.745 | 3.4752 |  | 97.5 | 0.00050956 | 5290 | 0.063687 | 6583 | 3.1693e-05 | 7669
WEBER 1111CB | WEBER 1111 | 163481111 |  | 1.4822 | 0.64932 |  | 24.8333 | 0.00059716 | 4338 | 0.053073 | 8251 | 3.1693e-05 | 7670
SALMON CREEK 1101654 | SALMON CREEK 1101 | 43161101 |  | 0.017049 | 0 |  | 0.5 | 0.00059683 | 4341 | 0.053073 | 8251 | 3.1675e-05 | 7671
LLAGAS 2104735530 | LLAGAS 2104 | 83182104 |  | 0.078953 | 0 |  | 1.5 | 0.00045265 | 5898 | 0.069972 | 5050 | 3.1673e-05 | 7672
HILLSDALE 04059156 | HILLSDALE 0405 | 24110405 |  | 0.69656 | 0.58761 |  | 12.3333 | 0.00059673 | 4342 | 0.053073 | 8250 | 3.167e-05 | 7673
MORGAN HILL 2104CB | MORGAN HILL 2104 | 83242104 |  | 10.2665 | 1.8177 |  | 211.5 | 0.00049002 | 5493 | 0.065501 | 6359 | 3.1668e-05 | 7674
LAKEWOOD 2110W577R | LAKEWOOD 2110 | 13532110 |  | 0.91115 | 0.51057 |  | 13.5 | 0.00055498 | 4819 | 0.059263 | 7119 | 3.1666e-05 | 7675
WINTERS 1101CB | WINTERS 1101 | 63321101 |  | 1.3368 | 0.14058 |  | 22.3333 | 0.00047249 | 5671 | 0.067 | 6057 | 3.1657e-05 | 7676
METTLER 111086700 | METTLER 1110 | 163701110 |  | 8.4779 | 1.2443 |  | 148 | 0.00042968 | 6124 | 0.074693 | 4460 | 3.1639e-05 | 7677
JANES CREEK 1103CB | JANES CREEK 1103 | 192391103 |  | 10.5825 | 2.4004 |  | 190.1667 | 0.00048484 | 5550 | 0.06522 | 6404 | 3.1636e-05 | 7678
NAPA 1110712 | NAPA 1110 | 42021110 |  | 1.9569 | 1.0206 |  | 32.8333 | 0.00053327 | 5037 | 0.060773 | 6920 | 3.1633e-05 | 7679
HARTLEY 1102841676 | HARTLEY 1102 | 43211102 | TRUE | 7.821 | 2.6218 | 0.018728 | 137.5 | 0.00036889 | 6859 | 0.088765 | 3349 | 3.1624e-05 | 7680
TRES VIAS 11011970 | TRES VIAS 1101 | 103251101 |  | 9.6182 | 1.4642 |  | 154.5 | 0.00045476 | 5875 | 0.071672 | 4805 | 3.1613e-05 | 7681
CORTINA 110130006 | CORTINA 1101 | 63121101 |  | 0.42676 | 0 |  | 7.8333 | 0.00041227 | 6311 | 0.076731 | 3920 | 3.1612e-05 | 7682
VASCO 1101MR290 | VASCO 1101 | 13751101 |  | 1.5016 | 0 |  | 24.25 | 0.00051538 | 5227 | 0.058816 | 7184 | 3.1606e-05 | 7683
PARLIER 11045674F | PARLIER 1104 | 252291104 |  | 0.36244 | 0.35916 |  | 4.5 | 0.00051005 | 5284 | 0.060555 | 6950 | 3.16e-05 | 7684
BLUE LAKE 1101CB | BLUE LAKE 1101 | 192181101 |  | 3.7623 | 0.6562 |  | 78.5 | 0.00047238 | 5672 | 0.066685 | 6142 | 3.1593e-05 | 7685
SF G 1102CB | SF G 1102 | 22091102 |  | 0.19552 | 0.37396 |  | 6.3333 | 0.00059512 | 4362 | 0.053073 | 8251 | 3.1585e-05 | 7686
REDWOOD CITY 0403CB | REDWOOD CITY 0403 | 24160403 |  | 1.6681 | 2.1447 |  | 36.8333 | 0.0005949 | 4364 | 0.053073 | 8250 | 3.1573e-05 | 7687
LAWRENCE 1107CB | LAWRENCE 1107 | 83421107 |  | 4.6239 | 0 |  | 43.6667 | 0.00057165 | 4635 | 0.056711 | 7478 | 3.1542e-05 | 7688
BRITTON 110960112 | BRITTON 1109 | 83611109 |  | 0.024082 | 0 |  | 0.33333 | 0.0005942 | 4368 | 0.053073 | 8251 | 3.1536e-05 | 7689
TRIMBLE 2116XR360 | TRIMBLE 2116 | 83802116 |  | 2.3415 | 0.18667 |  | 40 | 0.0005863 | 4461 | 0.054363 | 7876 | 3.1519e-05 | 7690
GRAND ISLAND 22278302 | GRAND ISLAND 2227 | 62462227 |  | 7.5264 | 2.0077 |  | 154.5 | 0.00041659 | 6261 | 0.075789 | 4267 | 3.1493e-05 | 7691
MAXWELL 11053060 | MAXWELL 1105 | 62881105 |  | 1.8335 | 0.014075 |  | 26.5 | 0.00044382 | 5975 | 0.071433 | 4840 | 3.149e-05 | 7692
DAVIS 110999850 | DAVIS 1109 | 62041109 |  | 2.6089 | 0.47898 |  | 44.1667 | 0.00053086 | 5062 | 0.062194 | 6747 | 3.1488e-05 | 7693
GEYSERVILLE 11014570 | GEYSERVILLE 1101 | 42891101 |  | 0.49577 | 0 |  | 12.5 | 0.00045371 | 5888 | 0.069357 | 5138 | 3.1469e-05 | 7694
SF H 0402CB | SF H 0402 | 22100402 |  | 4.0828 | 5.1159 |  | 51.5833 | 0.00058078 | 4511 | 0.054264 | 7894 | 3.1464e-05 | 7695
BELLEVUE 11022995 | BELLEVUE 1102 | 43181102 |  | 0.74925 | 0.45808 |  | 14 | 0.00049216 | 5471 | 0.065501 | 6360 | 3.146e-05 | 7696
EIGHT MILE 2105CB | EIGHT MILE 2105 | 163912105 |  | 0.4902 | 0 |  | 10 | 0.00047199 | 5679 | 0.069389 | 5128 | 3.146e-05 | 7697
REDWOOD CITY 0403271809 | REDWOOD CITY 0403 | 24160403 |  | 0.48804 | 0.68524 |  | 9.8333 | 0.00059246 | 4386 | 0.053073 | 8250 | 3.1443e-05 | 7698
MT EDEN 1108CB | MT EDEN 1108 | 13761108 |  | 9.802 | 10.6635 |  | 146.5 | 0.00059227 | 4389 | 0.053073 | 8251 | 3.1433e-05 | 7699
MC FARLAND 1104152466 | MC FARLAND 1104 | 253181104 |  | 3.6168 | 2.8391 |  | 60 | 0.00050281 | 5360 | 0.063698 | 6579 | 3.1426e-05 | 7700
WATERLOO 110214592 | WATERLOO 1102 | 163151102 |  | 11.4315 | 3.0555 |  | 201.8333 | 0.00048799 | 5515 | 0.068129 | 5376 | 3.1423e-05 | 7701
NEWARK 12KV 1106MR118 | NEWARK 12KV 1106 | 12221106 |  | 8.7123 | 8.394 |  | 138.3333 | 0.00059202 | 4393 | 0.053073 | 8250 | 3.142e-05 | 7702
DAVIS 110623502 | DAVIS 1106 | 62041106 |  | 1.9523 | 0.18453 |  | 29 | 0.00055542 | 4814 | 0.058699 | 7199 | 3.1417e-05 | 7703
CORCORAN 1112CB | CORCORAN 1112 | 252171112 |  | 6.6143 | 4.316 |  | 87.5833 | 0.00056836 | 4676 | 0.055627 | 7652 | 3.1415e-05 | 7704
JANES CREEK 110191072 | JANES CREEK 1101 | 192391101 |  | 0.019337 | 0 |  | 0.33333 | 0.00059189 | 4395 | 0.053073 | 8251 | 3.1413e-05 | 7705
MAGUNDEN 2108216392 | MAGUNDEN 2108 | 252772108 |  | 2.6094 | 1.7629 |  | 48.5 | 0.00051535 | 5228 | 0.063282 | 6629 | 3.1408e-05 | 7706
CHEROKEE 110159732 | CHEROKEE 1101 | 163651101 |  | 8.0221 | 1.429 |  | 145.8333 | 0.00046109 | 5796 | 0.070232 | 4997 | 3.1406e-05 | 7707
ATWATER 11059720 | ATWATER 1105 | 253611105 |  | 6.2186 | 0.78852 |  | 109.5 | 0.00044572 | 5956 | 0.071721 | 4800 | 3.1397e-05 | 7708
LIVERMORE 1101MR328 | LIVERMORE 1101 | 12141101 |  | 3.5338 | 4.1755 |  | 49.6667 | 0.00059152 | 4398 | 0.053073 | 8252 | 3.1393e-05 | 7709
RICHMOND R 1127BR214 | RICHMOND R 1127 | 13471127 |  | 5.8031 | 2.8061 |  | 80.3333 | 0.00057067 | 4652 | 0.05536 | 7694 | 3.1375e-05 | 7710
MADERA 1116615882 | MADERA 1116 | 252761116 |  | 0.62129 | 0.016762 |  | 9.5 | 0.00040524 | 6392 | 0.0774 | 3397 | 3.1366e-05 | 7711
MT EDEN 1112MR537 | MT EDEN 1112 | 13761112 |  | 4.6708 | 4.2988 |  | 89.5 | 0.00050693 | 5318 | 0.062502 | 6716 | 3.1363e-05 | 7712
JANES CREEK 11017702 | JANES CREEK 1101 | 192391101 |  | 8.908 | 4.3751 |  | 147.8333 | 0.00048979 | 5498 | 0.063952 | 6551 | 3.1361e-05 | 7713
PACIFICA 110410195 | PACIFICA 1104 | 22811104 |  | 2.9593 | 3.0961 |  | 61.5 | 0.0005299 | 5076 | 0.061806 | 6786 | 3.135e-05 | 7714
DUMBARTON 1107MR242 | DUMBARTON 1107 | 14471107 |  | 5.5797 | 4.6158 |  | 101.5 | 0.00059058 | 4407 | 0.053073 | 8251 | 3.1344e-05 | 7715
MANTECA 170599928 | MANTECA 1705 | 162611705 |  | 3.8555 | 0.56445 |  | 63 | 0.00045274 | 5895 | 0.071302 | 4858 | 3.1329e-05 | 7716
RIVERBANK 171575582 | RIVERBANK 1715 | 163191715 |  | 16.5249 | 2.0051 |  | 281 | 0.0004405 | 6007 | 0.073762 | 4574 | 3.132e-05 | 7717
JESSUP 11031540 | JESSUP 1103 | 103441103 | TRUE | 10.622 | 2.264 | 0.014383 | 187 | 0.00046907 | 5706 | 0.066826 | 6117 | 3.1312e-05 | 7718
HUNTERS POINT (P) 1104611150 | HUNTERS POINT (P) 1104 | 22331104 |  | 2.2093 | 0 |  | 41.5 | 0.00058998 | 4414 | 0.053073 | 8251 | 3.1312e-05 | 7719
OCEAN 0401404230 | OCEAN 0401 | 22580401 |  | 0.88528 | 0.92919 |  | 13 | 0.00058993 | 4415 | 0.053073 | 8251 | 3.1309e-05 | 7720
GRANT 1108MR353 | GRANT 1108 | 14381108 |  | 9.1781 | 11.3674 |  | 157.6667 | 0.00058978 | 4419 | 0.053073 | 8252 | 3.1301e-05 | 7721
GANSO 1103330684 | GANSO 1103 | 254541103 |  | 0.012215 | 0 |  | 0.5 | 0.00040411 | 6410 | 0.0774 | 3397 | 3.1278e-05 | 7722
SONOMA 11071309 | SONOMA 1107 | 42721107 |  | 1.767 | 0.2198 |  | 33 | 0.00044289 | 5987 | 0.070622 | 4940 | 3.1271e-05 | 7723
MIRA VISTA 0403CB | MIRA VISTA 0403 | 12330403 |  | 7.0902 | 8.5397 |  | 92.7833 | 0.00058564 | 4470 | 0.053553 | 8082 | 3.1271e-05 | 7724
MORGAN HILL 2105XR578 | MORGAN HILL 2105 | 83242105 | TRUE | 0.69759 | 0.55943 | 0.14114 | 11.5 | 0.00045494 | 5871 | 0.06365 | 6591 | 3.1266e-05 | 7725
SONOMA 11054456 | SONOMA 1105 | 42721105 |  | 5.018 | 1.3414 |  | 90 | 0.00046542 | 5744 | 0.067188 | 5824 | 3.1256e-05 | 7726
WEST FRESNO 1104D9804 | WEST FRESNO 1104 | 253731104 |  | 1.9679 | 3.4227 |  | 34.8333 | 0.00058889 | 4429 | 0.053073 | 8250 | 3.1254e-05 | 7727
MALAGA 1102CB | MALAGA 1102 | 254251102 |  | 15.5098 | 3.0983 |  | 278.6667 | 0.00043052 | 6113 | 0.073515 | 4610 | 3.1252e-05 | 7728
TRACY 1102CB | TRACY 1102 | 162881102 |  | 8.3064 | 0.54202 |  | 144.3333 | 0.00042687 | 6150 | 0.075257 | 4374 | 3.1251e-05 | 7729
CASTRO VALLEY 1103MR526 | CASTRO VALLEY 1103 | 14091103 |  | 5.791 | 6.3694 |  | 99.5 | 0.00058876 | 4431 | 0.053073 | 8251 | 3.1247e-05 | 7730
SF G 0403CB | SF G 0403 | 22090403 |  | 0.71211 | 0.76062 |  | 13.3333 | 0.00058874 | 4432 | 0.053073 | 8250 | 3.1246e-05 | 7731
CHOWCHILLA 110311590 | CHOWCHILLA 1103 | 254101103 |  | 6.0729 | 6.8267 |  | 114.5 | 0.00058548 | 4472 | 0.053494 | 8098 | 3.124e-05 | 7732
MAXWELL 11023038 | MAXWELL 1102 | 62881102 |  | 0.11354 | 0 |  | 1.5 | 0.00043679 | 6046 | 0.072158 | 4760 | 3.1224e-05 | 7733
FRENCH CAMP 1101CB | FRENCH CAMP 1101 | 163291101 |  | 10.842 | 2.8494 |  | 197.5 | 0.00045832 | 5829 | 0.06955 | 5114 | 3.1215e-05 | 7734
JANES CREEK 11031012 | JANES CREEK 1103 | 192391103 |  | 21.6551 | 3.8108 |  | 391 | 0.00046534 | 5745 | 0.067143 | 5860 | 3.1214e-05 | 7735
PAUL SWEET 2101722422 | PAUL SWEET 2101 | 83252101 |  | 4.6779 | 4.5382 |  | 60.6667 | 0.00058683 | 4458 | 0.053371 | 8146 | 3.1203e-05 | 7736
WALL 0401CB | WALL 0401 | 13740401 |  | 5.379 | 5.2891 |  | 66.0333 | 0.00056327 | 4725 | 0.056199 | 7544 | 3.1197e-05 | 7737
CHARCA 11064326 | CHARCA 1106 | 254501106 |  | 4.3727 | 2.7055 |  | 69 | 0.00055843 | 4771 | 0.056921 | 7447 | 3.1194e-05 | 7738
BUTTE 1104CB | BUTTE 1104 | 103081104 |  | 4.4841 | 0.87071 |  | 90.3333 | 0.00047335 | 5666 | 0.067758 | 5493 | 3.119e-05 | 7739
MAGUNDEN 210892790 | MAGUNDEN 2108 | 252772108 |  | 11.1967 | 8.8493 |  | 192 | 0.00054705 | 4888 | 0.059349 | 7105 | 3.1188e-05 | 7740
SCHINDLER 1109CB | SCHINDLER 1109 | 252891109 |  | 1.6683 | 0 |  | 9.45 | 0.00040803 | 6357 | 0.076845 | 3859 | 3.1184e-05 | 7741
SF H 1105CB | SF H 1105 | 22101105 |  | 2.4336 | 1.1565 |  | 36.4167 | 0.00056491 | 4709 | 0.055792 | 7618 | 3.1182e-05 | 7742
HALF MOON BAY 110148868 | HALF MOON BAY 1101 | 24101101 |  | 1.8709 | 0.84016 |  | 23.3333 | 0.0005132 | 5253 | 0.061346 | 6845 | 3.1176e-05 | 7743
EL CERRITO G 1105BR194 | EL CERRITO G 1105 | 12501105 | FALSE | 5.2835 | 5.3209 | 7.4353 | 84.5 | 0.00049541 | 5441 | 0.062666 | 6695 | 3.1173e-05 | 7744
SOLEDAD 21017048 | SOLEDAD 2101 | 182052101 |  | 19.0666 | 0.75745 |  | 366 | 0.00024714 | 9142 | 0.357 | 2957 | 3.1172e-05 | 7745
SHAFTER 111153620 | SHAFTER 1111 | 253651111 |  | 9.2631 | 4.8405 |  | 148 | 0.00053206 | 5047 | 0.062534 | 6709 | 3.1165e-05 | 7746
KING CITY 1104CB | KING CITY 1104 | 182031104 |  | 0.28663 | 0.14088 |  | 12.5 | 0.00048283 | 5569 | 0.063657 | 6589 | 3.1159e-05 | 7747
KING CITY 1105CB | KING CITY 1105 | 182031105 |  | 2.1936 | 0.57875 |  | 46.5 | 0.00050293 | 5358 | 0.062907 | 6669 | 3.1153e-05 | 7748
OROSI 1101778698 | OROSI 1101 | 252841101 |  | 9.8245 | 6.1134 |  | 175 | 0.00048961 | 5500 | 0.066228 | 6226 | 3.1143e-05 | 7749
LAMONT 1104469262 | LAMONT 1104 | 253911104 |  | 13.0135 | 0.83971 |  | 213 | 0.0004442 | 5970 | 0.070774 | 4922 | 3.1138e-05 | 7750
MC CALL 1108CB | MC CALL 1108 | 254121108 |  | 12.039 | 2.1171 |  | 217.25 | 0.00041542 | 6272 | 0.075407 | 4349 | 3.1127e-05 | 7751
TEJON 1102CB | TEJON 1102 | 252931102 |  | 9.6109 | 0.035094 |  | 182.75 | 0.00045009 | 5921 | 0.069827 | 5069 | 3.1122e-05 | 7752
COPUS 1104CB | COPUS 1104 | 253871104 |  | 0.94073 | 0.011645 |  | 14.5 | 0.00044045 | 6010 | 0.071303 | 4856 | 3.1106e-05 | 7753
CANTUA 1106CB | CANTUA 1106 | 253591106 |  | 0.15927 | 0 |  | 1.5 | 0.00046399 | 5760 | 0.067 | 6057 | 3.1087e-05 | 7754
CANTUA 1104CB | CANTUA 1104 | 253591104 |  | 0.14197 | 0 |  | 1.5 | 0.00046399 | 5760 | 0.067 | 6057 | 3.1087e-05 | 7754
WEBER 11092142 | WEBER 1109 | 163481109 |  | 0.45531 | 0 |  | 8.5 | 0.0005694 | 4667 | 0.056947 | 7445 | 3.107e-05 | 7755
JARVIS 1112MR565 | JARVIS 1112 | 13501112 |  | 0.68692 | 0.26539 |  | 15.5 | 0.0005854 | 4473 | 0.053073 | 8251 | 3.1069e-05 | 7756
WILSON 110310700 | WILSON 1103 | 254301103 |  | 6.0609 | 6.202 |  | 114 | 0.00053448 | 5016 | 0.06019 | 6997 | 3.1067e-05 | 7757
RICHMOND R 1121CB | RICHMOND R 1121 | 13471121 |  | 2.8924 | 0.21956 |  | 49.3333 | 0.00053045 | 5069 | 0.059677 | 7060 | 3.1066e-05 | 7758
DINUBA 1102CB | DINUBA 1102 | 254091102 |  | 22.6587 | 11.4884 |  | 410.75 | 0.00050275 | 5363 | 0.066459 | 6193 | 3.1066e-05 | 7759
CASTRO VALLEY 1108MR578 | CASTRO VALLEY 1108 | 14091108 |  | 2.1604 | 2.2611 |  | 40 | 0.00057338 | 4609 | 0.054551 | 7837 | 3.1063e-05 | 7760
PEABODY 210518134 | PEABODY 2105 | 63642105 |  | 7.7953 | 0.91804 |  | 138.5 | 0.00045646 | 5851 | 0.068532 | 5279 | 3.1056e-05 | 7761
CRESSEY 2103593420 | CRESSEY 2103 | 254702103 |  | 1.2246 | 0.015707 |  | 17 | 0.0004154 | 6273 | 0.075506 | 4338 | 3.1054e-05 | 7762
SF H 110213521 | SF H 1102 | 22101102 |  | 3.8375 | 3.8474 |  | 62.75 | 0.00057661 | 4569 | 0.053783 | 8002 | 3.1047e-05 | 7763
CASTRO VALLEY 1102MR248 | CASTRO VALLEY 1102 | 14091102 |  | 1.3033 | 0.78097 |  | 25.3333 | 0.00046282 | 5774 | 0.06702 | 6003 | 3.102e-05 | 7764
HUMBOLDT BAY 110242066 | HUMBOLDT BAY 1102 | 192341102 |  | 0.7617 | 0.15899 |  | 13.5 | 0.00046295 | 5773 | 0.067 | 6057 | 3.1018e-05 | 7765
SILVERADO 2102285782 | SILVERADO 2102 | 43432102 |  | 7.4174 | 0.86735 |  | 152 | 0.00045574 | 5858 | 0.068384 | 5305 | 3.1013e-05 | 7766
POINT PINOLE 1101CB | POINT PINOLE 1101 | 14261101 |  | 9.1238 | 8.223 |  | 139.8333 | 0.00054652 | 4894 | 0.056846 | 7462 | 3.1009e-05 | 7767
MAXWELL 1106CB | MAXWELL 1106 | 62881106 |  | 1.7632 | 0.019858 |  | 26.8333 | 0.00040062 | 6448 | 0.0774 | 3396 | 3.1008e-05 | 7768
LAMONT 11034088 | LAMONT 1103 | 253911103 |  | 6.628 | 5.7494 |  | 113 | 0.00053507 | 5009 | 0.059297 | 7111 | 3.1007e-05 | 7769
CONTRA COSTA 2108CB | CONTRA COSTA 2108 | 13652108 |  | 0.8753 | 0.62096 |  | 16.8167 | 0.00046795 | 5716 | 0.066173 | 6237 | 3.1001e-05 | 7770
ROCKLIN 11022222 | ROCKLIN 1102 | 152061102 |  | 12.5125 | 1.4706 |  | 212.5 | 0.00047888 | 5610 | 0.065174 | 6407 | 3.0996e-05 | 7771
BELLEVUE 1102130 | BELLEVUE 1102 | 43181102 |  | 3.7363 | 2.44 |  | 67 | 0.00046494 | 5749 | 0.066896 | 6094 | 3.0993e-05 | 7772
WEBER 1111778020 | WEBER 1111 | 163481111 |  | 8.0909 | 1.7778 |  | 148.3333 | 0.00049086 | 5489 | 0.065765 | 6308 | 3.0986e-05 | 7773
FAIRVIEW 2207P302 | FAIRVIEW 2207 | 13432207 |  | 0.018302 | 0 |  | 1.5 | 0.00058373 | 4488 | 0.053073 | 8251 | 3.098e-05 | 7774
NOTRE DAME 1103407486 | NOTRE DAME 1103 | 102041103 |  | 1.2171 | 0.033404 |  | 21.5 | 0.00046671 | 5732 | 0.066836 | 6114 | 3.0979e-05 | 7775
STOREY 110623135 | STOREY 1106 | 254611106 |  | 1.2352 | 1.351 |  | 23 | 0.00057761 | 4555 | 0.053602 | 8058 | 3.0962e-05 | 7776
EDES 1113CR270 | EDES 1113 | 13681113 |  | 1.4652 | 0.28432 |  | 31.5 | 0.00053536 | 5004 | 0.057706 | 7334 | 3.0957e-05 | 7777
DIXON LANDING 2101XR580 | DIXON LANDING 2101 | 14722101 |  | 6.2649 | 6.8631 |  | 92 | 0.00057805 | 4552 | 0.053602 | 8058 | 3.0953e-05 | 7778
HILLSDALE 0403CB | HILLSDALE 0403 | 24110403 |  | 0.015662 | 0.086339 |  | 0.86667 | 0.00051785 | 5194 | 0.056287 | 7535 | 3.0943e-05 | 7779
HONCUT 11011006 | HONCUT 1101 | 103211101 |  | 4.8549 | 1.3942 |  | 84.5 | 0.00045738 | 5842 | 0.070703 | 4933 | 3.0932e-05 | 7780
MOUNTAIN VIEW 1107CB | MOUNTAIN VIEW 1107 | 82031107 |  | 4.4464 | 5.1883 |  | 69.5833 | 0.0005782 | 4550 | 0.053473 | 8104 | 3.0932e-05 | 7781
RINCON 1103649194 | RINCON 1103 | 43321103 |  | 0.7295 | 0 |  | 12.5 | 0.00054042 | 4954 | 0.056982 | 7439 | 3.093e-05 | 7782
BUTTE 11052576 | BUTTE 1105 | 103081105 |  | 1.2087 | 0.26204 |  | 24 | 0.00046154 | 5790 | 0.067 | 6057 | 3.0923e-05 | 7783
SAN BRUNO 040387798 | SAN BRUNO 0403 | 22700403 |  | 2.1273 | 2.1637 |  | 29.5 | 0.00058244 | 4497 | 0.053073 | 8251 | 3.0912e-05 | 7784
MC CALL 11065000 | MC CALL 1106 | 254121106 |  | 2.7918 | 0.44448 |  | 49.5 | 0.00045606 | 5855 | 0.069956 | 5054 | 3.091e-05 | 7785
PLAINFIELD 1105403328 | PLAINFIELD 1105 | 63441105 |  | 7.5545 | 0.35744 |  | 122 | 0.00041397 | 6295 | 0.075149 | 4394 | 3.0904e-05 | 7786
BOWLES 1104CB | BOWLES 1104 | 253531104 |  | 1.7447 | 0.56521 |  | 32.5 | 0.00042254 | 6200 | 0.074077 | 4543 | 3.0901e-05 | 7787
LAMONT 11071608 | LAMONT 1107 | 253911107 |  | 7.1093 | 2.0695 |  | 115.5 | 0.00045438 | 5879 | 0.069304 | 5144 | 3.0887e-05 | 7788
PANORAMA 11023320 | PANORAMA 1102 | 103461102 |  | 14.5128 | 3.9648 |  | 265 | 0.00047316 | 5668 | 0.065823 | 6301 | 3.0886e-05 | 7789
NEWARK 12KV 11079408 | NEWARK 12KV 1107 | 12221107 |  | 1.9901 | 1.9046 |  | 30 | 0.00058195 | 4501 | 0.053073 | 8251 | 3.0885e-05 | 7790
JARVIS 1111MR122 | JARVIS 1111 | 13501111 |  | 3.9587 | 3.3899 |  | 69 | 0.0005274 | 5101 | 0.05842 | 7232 | 3.0871e-05 | 7791
NEWMAN 110590460 | NEWMAN 1105 | 162741105 |  | 0.55953 | 0.0145 |  | 8 | 0.00051397 | 5244 | 0.059154 | 7138 | 3.0869e-05 | 7792
LODI 110237604 | LODI 1102 | 162111102 |  | 10.5699 | 0.77382 |  | 179.1667 | 0.00040743 | 6365 | 0.076226 | 4120 | 3.086e-05 | 7793
SF H 1110CB | SF H 1110 | 22101110 |  | 3.1044 | 0.37535 |  | 58.6429 | 0.00047963 | 5605 | 0.065011 | 6429 | 3.0854e-05 | 7794
GREEN VALLEY 210310438 | GREEN VALLEY 2103 | 83192103 |  | 7.7946 | 3.5707 |  | 147.3333 | 0.00045609 | 5854 | 0.067658 | 5524 | 3.084e-05 | 7795
OROSI 110468494 | OROSI 1104 | 252841104 |  | 2.4242 | 1.5516 |  | 38 | 0.00051666 | 5209 | 0.060661 | 6935 | 3.0831e-05 | 7796
ROSSMOOR 1107CB | ROSSMOOR 1107 | 14161107 |  | 0.9883 | 0 |  | 10.6667 | 0.00053576 | 5000 | 0.058889 | 7173 | 3.0827e-05 | 7797
LOS OSITOS 2102148504 | LOS OSITOS 2102 | 182082102 |  | 1.9918 | 0.21609 |  | 41.5 | 0.00041695 | 6257 | 0.073579 | 4598 | 3.0821e-05 | 7798
HURON 11129820 | HURON 1112 | 253161112 |  | 1.8885 | 0.20486 |  | 33 | 0.00055799 | 4780 | 0.055284 | 7710 | 3.0806e-05 | 7799
21ST AVENUE 0403CB | 21ST AVENUE 0403 | 22550403 |  | 1.8435 | 3.3473 |  | 34.3333 | 0.00058043 | 4515 | 0.053073 | 8252 | 3.0805e-05 | 7800
PETALUMA C 1106278842 | PETALUMA C 1106 | 42631106 |  | 2.9428 | 2.5086 |  | 56.5 | 0.00057988 | 4521 | 0.053503 | 8095 | 3.0805e-05 | 7801
UPPER LAKE 1101452 | UPPER LAKE 1101 | 42871101 |  | 1.625 | 0.84767 |  | 29.3333 | 0.00047831 | 5616 | 0.065171 | 6408 | 3.0804e-05 | 7802
SOLANO 0402CB | SOLANO 0402 | 13140402 |  | 6.3232 | 6.9272 |  | 80.6667 | 0.00058032 | 4519 | 0.053073 | 8251 | 3.0799e-05 | 7803
PASO ROBLES 1101CB | PASO ROBLES 1101 | 182611101 |  | 2.6668 | 0.92046 |  | 43.8333 | 0.00053654 | 4994 | 0.058053 | 7283 | 3.0796e-05 | 7804
BELMONT 11104946 | BELMONT 1110 | 24031110 |  | 6.1513 | 5.306 |  | 83.5 | 0.00054265 | 4927 | 0.057214 | 7403 | 3.0796e-05 | 7805
AVENAL 21019810 | AVENAL 2101 | 255002101 |  | 8.9114 | 3.9152 |  | 147 | 0.00050306 | 5356 | 0.063384 | 6622 | 3.079e-05 | 7806
MOLINO 11034894 | MOLINO 1103 | 42571103 |  | 15.3699 | 3.0086 |  | 282.5 | 0.00045884 | 5820 | 0.067056 | 5940 | 3.0762e-05 | 7807
NORTH TOWER 110293010 | NORTH TOWER 1102 | 42041102 |  | 2.8496 | 3.0061 |  | 47.3333 | 0.00057962 | 4527 | 0.053073 | 8253 | 3.0762e-05 | 7808
MORMON 110365312 | MORMON 1103 | 163211103 |  | 4.6505 | 4.2756 |  | 79.1667 | 0.00057054 | 4654 | 0.05441 | 7862 | 3.0759e-05 | 7809
ANGIOLA 1104CB | ANGIOLA 1104 | 252151104 |  | 11.5138 | 0.31917 |  | 193.3333 | 0.00039766 | 6480 | 0.077318 | 3449 | 3.0754e-05 | 7810
HORSESHOE 1103CB | HORSESHOE 1103 | 152571103 |  | 5.3597 | 3.3685 |  | 101.3333 | 0.00047502 | 5646 | 0.065111 | 6417 | 3.075e-05 | 7811
LODI 110223758 | LODI 1102 | 162111102 |  | 5.3255 | 0.77674 |  | 89.6667 | 0.00040387 | 6414 | 0.07632 | 4081 | 3.0747e-05 | 7812
BASALT 110635550 | BASALT 1106 | 42461106 |  | 1.0196 | 0.037643 |  | 18 | 0.00045062 | 5915 | 0.068224 | 5353 | 3.0743e-05 | 7813
MOLINO 1104186 | MOLINO 1104 | 42571104 |  | 13.5993 | 6.7784 |  | 248 | 0.00047591 | 5640 | 0.065495 | 6361 | 3.0737e-05 | 7814
CORONA 11034446 | CORONA 1103 | 43491103 |  | 11.4804 | 3.0794 |  | 219.8333 | 0.00025355 | 9006 | 0.11502 | 3278 | 3.0725e-05 | 7815
BALFOUR 1101CB | BALFOUR 1101 | 14321101 |  | 7.2209 | 0.69906 |  | 111.3333 | 0.00047776 | 5623 | 0.066095 | 6249 | 3.072e-05 | 7816
WILLOW PASS 210721135 | WILLOW PASS 2107 | 13912107 |  | 0.025546 | 0 |  | 0.5 | 0.0004543 | 5882 | 0.067594 | 5552 | 3.0708e-05 | 7817
GEYSERVILLE 1102CB | GEYSERVILLE 1102 | 42891102 |  | 2.9945 | 0.75139 |  | 60.3333 | 0.00044886 | 5927 | 0.068663 | 5247 | 3.0702e-05 | 7818
NEWARK 12KV 1107MR240 | NEWARK 12KV 1107 | 12221107 |  | 7.2455 | 7.6205 |  | 107.5 | 0.00057849 | 4543 | 0.053073 | 8251 | 3.0702e-05 | 7819
FAIRWAY 1108M02 | FAIRWAY 1108 | 182061108 |  | 8.4851 | 5.8029 |  | 147.5 | 0.00050391 | 5348 | 0.062043 | 6758 | 3.0687e-05 | 7820
STOREY 110765648 | STOREY 1107 | 254611107 |  | 3.4103 | 2.2204 |  | 64.3333 | 0.00052233 | 5155 | 0.060481 | 6962 | 3.0682e-05 | 7821
BRENTWOOD 2105CB | BRENTWOOD 2105 | 14592105 |  | 10.7928 | 1.0769 |  | 190.5 | 0.0004504 | 5918 | 0.068155 | 5368 | 3.068e-05 | 7822
MERCED 1114CUS250088 | MERCED 1114 | 252801114 |  | 0.0037078 | 0 |  | 0.33333 | 0.00039635 | 6497 | 0.0774 | 3396 | 3.0678e-05 | 7823
CLEAR LAKE 1101CB | CLEAR LAKE 1101 | 42141101 |  | 6.4199 | 1.7738 |  | 118 | 0.00045481 | 5873 | 0.067529 | 5586 | 3.0674e-05 | 7824
HILLSDALE 040277056 | HILLSDALE 0402 | 24110402 |  | 7.7766 | 6.7163 |  | 92.3667 | 0.00054855 | 4873 | 0.055767 | 7626 | 3.0667e-05 | 7825
COTATI 1102468 | COTATI 1102 | 42271102 |  | 0.79936 | 0.36411 |  | 14.5 | 0.00045767 | 5838 | 0.067 | 6057 | 3.0664e-05 | 7826
FULTON 11011734 | FULTON 1101 | 42561101 |  | 1.0111 | 0.16862 |  | 22.8333 | 0.0005112 | 5275 | 0.059221 | 7124 | 3.0659e-05 | 7827
SF H 0401CB | SF H 0401 | 22100401 |  | 4.6132 | 6.634 |  | 80.0179 | 0.00056037 | 4749 | 0.055619 | 7654 | 3.0656e-05 | 7828
DEL MAR 21051048 | DEL MAR 2105 | 152582105 |  | 0.13255 | 0.089538 |  | 5.5 | 0.00045753 | 5840 | 0.067 | 6057 | 3.0655e-05 | 7829
NEWARK 21KV 2103MR116 | NEWARK 21KV 2103 | 12232103 |  | 3.2742 | 0.59507 |  | 67.5 | 0.00056209 | 4734 | 0.05585 | 7604 | 3.0654e-05 | 7830
FORT BRAGG A 110465894 | FORT BRAGG A 1104 | 42761104 |  | 1.1421 | 0.54585 |  | 20.5 | 0.00037385 | 6782 | 0.11983 | 3267 | 3.0649e-05 | 7831
LERDO 11101616 | LERDO 1110 | 253491110 |  | 2.8409 | 0.020145 |  | 59 | 0.00050913 | 5297 | 0.062109 | 6753 | 3.0643e-05 | 7832
TAFT 1106CB | TAFT 1106 | 252081106 |  | 3.8781 | 0.73973 |  | 61.25 | 0.00046888 | 5709 | 0.065807 | 6303 | 3.0639e-05 | 7833
GUSTINE 1101CB | GUSTINE 1101 | 163111101 |  | 6.6023 | 3.4675 |  | 97 | 0.00052619 | 5111 | 0.05882 | 7182 | 3.0639e-05 | 7834
BARTON 111577150 | BARTON 1115 | 253571115 |  | 7.8133 | 1.3049 |  | 142 | 0.00045034 | 5920 | 0.069762 | 5080 | 3.0633e-05 | 7835
BELLEVUE 1104564 | BELLEVUE 1104 | 43181104 |  | 8.2799 | 3.7136 |  | 147 | 0.00047046 | 5694 | 0.065837 | 6296 | 3.0631e-05 | 7836
EL CERRITO G 1112BR198 | EL CERRITO G 1112 | 12501112 |  | 1.2414 | 1.5107 |  | 22.1667 | 0.00057713 | 4559 | 0.053073 | 8251 | 3.063e-05 | 7837
CLOVIS 1107CB | CLOVIS 1107 | 254081107 |  | 10.8687 | 0.84722 |  | 204 | 0.00041621 | 6265 | 0.074328 | 4508 | 3.0613e-05 | 7838
MILPITAS 1108XR122 | MILPITAS 1108 | 82831108 |  | 6.765 | 5.601 |  | 125.5 | 0.00051949 | 5184 | 0.059617 | 7069 | 3.061e-05 | 7839
EAST STOCKTON 1102D7545 | EAST STOCKTON 1102 | 163131102 |  | 0.60855 | 0.50348 |  | 9.5 | 0.00057664 | 4568 | 0.053073 | 8251 | 3.0604e-05 | 7840
FIGARDEN 2112R1140 | FIGARDEN 2112 | 254552112 |  | 2.4562 | 0.090084 |  | 43 | 0.00042882 | 6134 | 0.073722 | 4578 | 3.0601e-05 | 7841
SF G 0404CB | SF G 0404 | 22090404 |  | 0.95501 | 1.1239 |  | 17.5 | 0.0005765 | 4570 | 0.053073 | 8251 | 3.0596e-05 | 7842
MENLO 11029092 | MENLO 1102 | 24131102 |  | 8.5537 | 2.6689 |  | 176.5 | 0.00045512 | 5868 | 0.067202 | 5808 | 3.0569e-05 | 7843
LAMONT 1107CB | LAMONT 1107 | 253911107 |  | 8.7956 | 0.53932 |  | 137.95 | 0.00039807 | 6475 | 0.076907 | 3825 | 3.056e-05 | 7844
MC CALL 110793024 | MC CALL 1107 | 254121107 |  | 5.7617 | 1.256 |  | 103.8333 | 0.00041994 | 6227 | 0.073126 | 4651 | 3.0556e-05 | 7845
LAS PULGAS 040432524 | LAS PULGAS 0404 | 24120404 |  | 1.1216 | 1.0191 |  | 22 | 0.00057572 | 4581 | 0.053073 | 8251 | 3.0555e-05 | 7846
ATWATER 1108CB | ATWATER 1108 | 253611108 |  | 6.7218 | 1.2608 |  | 103.4167 | 0.00044825 | 5931 | 0.069989 | 5049 | 3.0552e-05 | 7847
PASO ROBLES 110638682 | PASO ROBLES 1106 | 182611106 |  | 0.47021 | 0.015031 |  | 8 | 0.00049652 | 5429 | 0.062195 | 6746 | 3.055e-05 | 7848
SAN LEANDRO U 1107MR560 | SAN LEANDRO U 1107 | 13111107 |  | 7.9361 | 8.5765 |  | 135.3333 | 0.00057528 | 4588 | 0.053073 | 8250 | 3.0531e-05 | 7849
CAL WATER 1103768902 | CAL WATER 1103 | 255451103 |  | 1.6994 | 0.67665 |  | 32.5 | 0.00047662 | 5630 | 0.064973 | 6438 | 3.0527e-05 | 7850
PENRYN 11052406 | PENRYN 1105 | 152561105 | TRUE | 3.9002 | 1.345 | 0.018237 | 66.5 | 0.0004556 | 5860 | 0.067004 | 6037 | 3.0527e-05 | 7851
HILLSDALE 040596742 | HILLSDALE 0405 | 24110405 |  | 3.0582 | 2.8225 |  | 41.75 | 0.00054125 | 4945 | 0.056131 | 7556 | 3.0524e-05 | 7852
JESSUP 11039281 | JESSUP 1103 | 103441103 |  | 0.83465 | 0.1452 |  | 14 | 0.00045548 | 5863 | 0.067005 | 6029 | 3.052e-05 | 7853
PEASE 1103264986 | PEASE 1103 | 153751103 |  | 0.016619 | 0 |  | 0.5 | 0.0005749 | 4591 | 0.053073 | 8251 | 3.0511e-05 | 7854
CAYETANO 2109MR198 | CAYETANO 2109 | 14422109 |  | 3.6399 | 0.43296 |  | 62.8333 | 0.00051507 | 5233 | 0.060468 | 6966 | 3.0506e-05 | 7855
SANGER 1116CB | SANGER 1116 | 252351116 |  | 6.3349 | 2.5313 |  | 114.3333 | 0.00045275 | 5894 | 0.069137 | 5170 | 3.0502e-05 | 7856
RAWSON 11033314 | RAWSON 1103 | 103531103 |  | 9.6873 | 2.8724 |  | 173 | 0.00045229 | 5902 | 0.067581 | 5563 | 3.0498e-05 | 7857
SF H 1109CB | SF H 1109 | 22101109 |  | 0.78155 | 1.5753 |  | 29.0833 | 0.00057439 | 4595 | 0.053073 | 8251 | 3.0485e-05 | 7858
MORGAN HILL 2110XR326 | MORGAN HILL 2110 | 83242110 | TRUE | 13.6198 | 3.2563 | 0.036351 | 219.75 | 0.00046382 | 5763 | 0.065668 | 6330 | 3.0478e-05 | 7859
LOS OSITOS 210137376 | LOS OSITOS 2101 | 182082101 |  | 4.7174 | 1.9454 |  | 95.8333 | 0.00051339 | 5249 | 0.060756 | 6922 | 3.0478e-05 | 7860
CORNING 110255208 | CORNING 1102 | 103331102 |  | 0.080752 | 0 |  | 1 | 0.00045381 | 5886 | 0.06714 | 5862 | 3.0469e-05 | 7861
BRENTWOOD 2112K504R | BRENTWOOD 2112 | 14592112 |  | 8.0972 | 2.8265 |  | 147.5 | 0.00041105 | 6323 | 0.075377 | 4352 | 3.0467e-05 | 7862
DUMBARTON 2111CB | DUMBARTON 2111 | 14472111 |  | 3.9654 | 0.62506 |  | 69 | 0.00052664 | 5109 | 0.05889 | 7172 | 3.0463e-05 | 7863
SANTA MARIA 1108M16 | SANTA MARIA 1108 | 182671108 |  | 3.7602 | 2.5298 |  | 54.5 | 0.00057392 | 4603 | 0.053073 | 8251 | 3.046e-05 | 7864
COVELO 1101225458 | COVELO 1101 | 43061101 |  | 0.299 | 0 |  | 4.3333 | 0.00045455 | 5877 | 0.067 | 6058 | 3.0455e-05 | 7865
PANORAMA 1102CB | PANORAMA 1102 | 103461102 |  | 11.184 | 1.9351 |  | 220 | 0.00045206 | 5903 | 0.067479 | 5615 | 3.0453e-05 | 7866
SF L 0406CB | SF L 0406 | 22260406 |  | 2.136 | 2.5812 |  | 48.0833 | 0.00054267 | 4926 | 0.05712 | 7421 | 3.0452e-05 | 7867
HONCUT 11012598 | HONCUT 1101 | 103211101 |  | 4.0274 | 0.10134 |  | 66 | 0.00039326 | 6532 | 0.0774 | 3397 | 3.0438e-05 | 7868
MENLO 11018908 | MENLO 1101 | 24131101 |  | 0.13651 | 0.14278 |  | 2 | 0.00057329 | 4610 | 0.053073 | 8251 | 3.0426e-05 | 7869
TRINIDAD 110137474 | TRINIDAD 1101 | 192231101 |  | 6.0733 | 0.44053 |  | 108 | 0.00045431 | 5881 | 0.066928 | 6083 | 3.0422e-05 | 7870
PUEBLO 2102698 | PUEBLO 2102 | 43292102 |  | 16.5675 | 2.569 |  | 335.5 | 0.00045478 | 5874 | 0.067549 | 5573 | 3.0418e-05 | 7871
OCEAN 0401794796 | OCEAN 0401 | 22580401 |  | 0.79805 | 1.3925 |  | 12.8333 | 0.00057308 | 4616 | 0.053073 | 8250 | 3.0415e-05 | 7872
REDWOOD CITY 041054820 | REDWOOD CITY 0410 | 24160410 |  | 1.8317 | 2.2953 |  | 27.9167 | 0.00057305 | 4617 | 0.053073 | 8251 | 3.0413e-05 | 7873
CORNING 110349740 | CORNING 1103 | 103331103 |  | 7.2894 | 1.9772 |  | 127 | 0.00045679 | 5848 | 0.066628 | 6159 | 3.0411e-05 | 7874
FREMONT 1109MR699 | FREMONT 1109 | 14351109 |  | 3.8862 | 3.1938 |  | 60 | 0.00056784 | 4685 | 0.053478 | 8102 | 3.0402e-05 | 7875
KNIGHTS LANDING 110165736 | KNIGHTS LANDING 1101 | 62721101 |  | 2.3646 | 0.7242 |  | 43 | 0.00046204 | 5783 | 0.068631 | 5253 | 3.0392e-05 | 7876
MENLO 040314383 | MENLO 0403 | 24130403 |  | 0.18242 | 0.20028 |  | 3 | 0.00057246 | 4623 | 0.053073 | 8251 | 3.0382e-05 | 7877
METTLER 110936726 | METTLER 1109 | 163701109 |  | 3.0345 | 0.48179 |  | 50.5 | 0.00039673 | 6493 | 0.076436 | 4040 | 3.0378e-05 | 7878
LOS OSITOS 2101115450 | LOS OSITOS 2101 | 182082101 |  | 2.6482 | 0.27364 |  | 51 | 0.00045332 | 5892 | 0.067 | 6057 | 3.0372e-05 | 7879
WESTLAKE 0401CB | WESTLAKE 0401 | 22600401 |  | 0.81342 | 0.57018 |  | 16 | 0.00053006 | 5075 | 0.058295 | 7251 | 3.0355e-05 | 7880
WEEDPATCH 1103CB | WEEDPATCH 1103 | 252971103 |  | 5.8261 | 0.38976 |  | 88.5 | 0.00041391 | 6296 | 0.073681 | 4582 | 3.0353e-05 | 7881
NORTECH 2110XR362 | NORTECH 2110 | 82462110 |  | 8.4603 | 4.8752 |  | 155 | 0.00050002 | 5391 | 0.061407 | 6841 | 3.0348e-05 | 7882
RANDOLPH 0403CB | RANDOLPH 0403 | 22590403 |  | 3.1239 | 4.7367 |  | 54.75 | 0.00057174 | 4633 | 0.053073 | 8252 | 3.0344e-05 | 7883
NEWBURG 1132CB | NEWBURG 1132 | 192151132 |  | 1.173 | 0.41201 |  | 20.8333 | 0.00050896 | 5298 | 0.059981 | 7020 | 3.0341e-05 | 7884
MADERA 1119CB | MADERA 1119 | 252761119 |  | 21.3528 | 1.3302 |  | 349 | 0.00040676 | 6373 | 0.075325 | 4362 | 3.0332e-05 | 7885
MERCED 1108CB | MERCED 1108 | 252801108 |  | 13.8335 | 4.0576 |  | 221.5 | 0.00047387 | 5662 | 0.067742 | 5496 | 3.033e-05 | 7886
CORTINA 1101CB | CORTINA 1101 | 63121101 |  | 0.051987 | 0 |  | 1.5 | 0.00045266 | 5897 | 0.067 | 6057 | 3.0328e-05 | 7887
WOODSIDE 11059160 | WOODSIDE 1105 | 24251105 |  | 0.62497 | 0.12023 |  | 13 | 0.00045252 | 5899 | 0.067 | 6057 | 3.0319e-05 | 7888
MC CALL 1108466172 | MC CALL 1108 | 254121108 |  | 0.019004 | 0 |  | 0.5 | 0.00039148 | 6549 | 0.0774 | 3397 | 3.03e-05 | 7889
RANDOLPH 0402CB | RANDOLPH 0402 | 22590402 |  | 1.265 | 1.6421 |  | 23 | 0.0005709 | 4649 | 0.053073 | 8250 | 3.0299e-05 | 7890
EDENVALE 2105XR392 | EDENVALE 2105 | 82952105 |  | 1.7418 | 0 |  | 39 | 0.00045051 | 5917 | 0.067512 | 5592 | 3.0267e-05 | 7891
BELMONT 111039182 | BELMONT 1110 | 24031110 |  | 1.7169 | 1.1841 |  | 27.1667 | 0.00055756 | 4786 | 0.054782 | 7792 | 3.0265e-05 | 7892
HORSESHOE 11061826 | HORSESHOE 1106 | 152571106 |  | 6.1589 | 1.6463 |  | 111.5 | 0.00045154 | 5908 | 0.066984 | 6067 | 3.0246e-05 | 7893
SANTA MARIA 1106M114 | SANTA MARIA 1106 | 182671106 |  | 2.244 | 1.6685 |  | 34.5 | 0.00056976 | 4659 | 0.053073 | 8251 | 3.0239e-05 | 7894
RICE 1103CB | RICE 1103 | 62831103 |  | 2.2824 | 0.17296 |  | 35.8333 | 0.00039372 | 6525 | 0.077174 | 3623 | 3.0235e-05 | 7895
KINGSBURG 111255052 | KINGSBURG 1112 | 252241112 |  | 0.051413 | 0 |  | 0.5 | 0.00039053 | 6563 | 0.0774 | 3397 | 3.0227e-05 | 7896
GRAND ISLAND 2225CB | GRAND ISLAND 2225 | 62462225 |  | 22.9448 | 2.3326 |  | 375.5333 | 0.00039744 | 6484 | 0.075967 | 4208 | 3.0224e-05 | 7897
SF E 0410CB | SF E 0410 | 22070410 |  | 1.8707 | 2.6712 |  | 35.5 | 0.00056948 | 4663 | 0.053073 | 8251 | 3.0224e-05 | 7898
OAKLAND J 1102CR250 | OAKLAND J 1102 | 12091102 |  | 0.59266 | 0.82277 |  | 9.5 | 0.00056946 | 4664 | 0.053073 | 8251 | 3.0223e-05 | 7899
SANTA MARIA 110558550 | SANTA MARIA 1105 | 182671105 |  | 0.014166 | 0 |  | 0.5 | 0.00045095 | 5911 | 0.067 | 6057 | 3.0214e-05 | 7900
RINCON 1102782389 | RINCON 1102 | 43321102 | TRUE | 0.53538 | 0.19164 | 0.40479 | 9.5 | 0.00042578 | 6165 | 0.068282 | 5337 | 3.0212e-05 | 7901
NORTH TOWER 1108780701 | NORTH TOWER 1108 | 42041108 |  | 2.2915 | 0.662 |  | 36.2 | 0.0005114 | 5271 | 0.060026 | 7017 | 3.0199e-05 | 7902
KEARNEY 1106CB | KEARNEY 1106 | 252701106 |  | 9.7151 | 0.64069 |  | 162 | 0.00039497 | 6512 | 0.076663 | 3951 | 3.0194e-05 | 7903
GUSTINE 1102CB | GUSTINE 1102 | 163111102 |  | 6.5822 | 2.0138 |  | 107 | 0.00044496 | 5962 | 0.069951 | 5057 | 3.0191e-05 | 7904
LOYOLA 110160096 | LOYOLA 1101 | 82161101 |  | 13.9318 | 4.5588 |  | 259 | 0.00045158 | 5907 | 0.066749 | 6131 | 3.0176e-05 | 7905
LEMOORE 1105671546 | LEMOORE 1105 | 253601105 |  | 8.7163 | 4.6398 |  | 161.3333 | 0.00050445 | 5342 | 0.064799 | 6464 | 3.0175e-05 | 7906
PLAINFIELD 11016562 | PLAINFIELD 1101 | 63441101 |  | 4.5579 | 0.45867 |  | 74 | 0.00039999 | 6455 | 0.076414 | 4049 | 3.0174e-05 | 7907
LAS POSITAS 2109MR310 | LAS POSITAS 2109 | 14402109 |  | 7.385 | 5.3283 |  | 113 | 0.00056305 | 4727 | 0.053812 | 7997 | 3.0173e-05 | 7908
JANES CREEK 1103136680 | JANES CREEK 1103 | 192391103 |  | 0.49945 | 0.21372 |  | 9.5 | 0.00046445 | 5756 | 0.064068 | 6531 | 3.0172e-05 | 7909
POTRERO PP (A) 1104CB | POTRERO PP (A) 1104 | 22031104 |  | 0.4678 | 0.24496 |  | 9 | 0.00056826 | 4677 | 0.053073 | 8251 | 3.0159e-05 | 7910
SANGER 111888052 | SANGER 1118 | 252351118 |  | 1.036 | 0.27452 |  | 23 | 0.0003896 | 6577 | 0.0774 | 3397 | 3.0155e-05 | 7911
BELLE HAVEN 11048966 | BELLE HAVEN 1104 | 24021104 |  | 1.7496 | 0.69011 |  | 28 | 0.00053184 | 5052 | 0.056982 | 7438 | 3.0142e-05 | 7912
SAN LEANDRO U 1109CR002 | SAN LEANDRO U 1109 | 13111109 | TRUE | 1.0707 | 0.92554 | 0.10537 | 14.6667 | 0.00056791 | 4683 | 0.053073 | 8251 | 3.014e-05 | 7913
LINDEN 1103CB | LINDEN 1103 | 162071103 |  | 6.1863 | 2.0429 |  | 100.3333 | 0.00046351 | 5767 | 0.06711 | 5888 | 3.0132e-05 | 7914
LIVE OAK 1101CB | LIVE OAK 1101 | 153771101 |  | 3.1972 | 1.3797 |  | 56 | 0.00052811 | 5095 | 0.05904 | 7155 | 3.0128e-05 | 7915
EL CERRITO G 1106BR140 | EL CERRITO G 1106 | 12501106 |  | 2.4416 | 2.4904 |  | 44.5 | 0.0005339 | 5025 | 0.056515 | 7501 | 3.0124e-05 | 7916
VASCO 1102MR178 | VASCO 1102 | 13751102 | FALSE | 13.3292 | 0.32789 | 1.1205 | 236.5 | 0.00014641 | 10735 | 0.34036 | 2972 | 3.0105e-05 | 7917
WOODLAND 11088802 | WOODLAND 1108 | 62031108 |  | 15.3122 | 0.84516 |  | 250 | 0.00040523 | 6394 | 0.074974 | 4417 | 3.01e-05 | 7918
RIPON 17025312 | RIPON 1702 | 163801702 |  | 4.201 | 1.5926 |  | 79 | 0.00049061 | 5490 | 0.065101 | 6419 | 3.01e-05 | 7919
DIVIDE 1102M130 | DIVIDE 1102 | 182571102 |  | 7.9239 | 6.0307 |  | 133 | 0.00048642 | 5535 | 0.062039 | 6759 | 3.0097e-05 | 7920
DIVIDE 1102CB | DIVIDE 1102 | 182571102 |  | 4.9669 | 2.0064 |  | 90.0833 | 0.00047716 | 5626 | 0.063732 | 6575 | 3.0096e-05 | 7921
PASO ROBLES 1104P02 | PASO ROBLES 1104 | 182611104 | TRUE | 7.2531 | 2.7172 | 0.24447 | 124.5 | 0.00027049 | 8638 | 0.36786 | 2950 | 3.0095e-05 | 7922
MAXWELL 1102CB | MAXWELL 1102 | 62881102 |  | 6.1484 | 0.10887 |  | 98.3333 | 0.00040551 | 6389 | 0.074475 | 4488 | 3.0086e-05 | 7923
OLIVEHURST 1105CB | OLIVEHURST 1105 | 152901105 |  | 15.8441 | 2.2188 |  | 288 | 0.00043179 | 6096 | 0.072377 | 4735 | 3.0082e-05 | 7924
CAYUCOS 1102W18 | CAYUCOS 1102 | 182551102 |  | 10.8592 | 10.5854 |  | 162 | 0.0004956 | 5439 | 0.061525 | 6826 | 3.0077e-05 | 7925
CANAL 110511060 | CANAL 1105 | 252091105 |  | 6.9605 | 4.0387 |  | 103.1667 | 0.00050738 | 5310 | 0.0598 | 7039 | 3.0049e-05 | 7926
SAN JOAQUIN 1108CB | SAN JOAQUIN 1108 | 252361108 |  | 2.1392 | 0.028664 |  | 32 | 0.00038813 | 6604 | 0.0774 | 3397 | 3.0041e-05 | 7927
METTLER 1109CB | METTLER 1109 | 163701109 |  | 9.8471 | 1.9478 |  | 180 | 0.00040056 | 6450 | 0.075771 | 4271 | 3.0036e-05 | 7928
KERMAN 1102CB | KERMAN 1102 | 252711102 |  | 5.0284 | 0.68625 |  | 78.5333 | 0.00039042 | 6565 | 0.076471 | 4029 | 3.003e-05 | 7929
CADET 1101CB | CADET 1101 | 254821101 |  | 0.025093 | 0 |  | 1 | 0.00044764 | 5937 | 0.06707 | 5925 | 3.0023e-05 | 7930
PRUNEDALE 11103716 | PRUNEDALE 1110 | 182961110 | TRUE | 13.1753 | 2.9556 | 0.24195 | 251.5 | 0.00044675 | 5943 | 0.067268 | 5752 | 3.0021e-05 | 7931
FRUITVALE 1103815842 | FRUITVALE 1103 | 253391103 |  | 4.9824 | 1.3297 |  | 79 | 0.00055559 | 4810 | 0.05483 | 7787 | 3.0019e-05 | 7932
INDUSTRIAL ACRES 0415CB | INDUSTRIAL ACRES 0415 | 182300415 |  | 1.4236 | 0.37643 |  | 15.6667 | 0.00056553 | 4703 | 0.053073 | 8252 | 3.0014e-05 | 7933
MONROE 110646702 | MONROE 1106 | 43301106 |  | 2.7801 | 0.95898 |  | 50 | 0.00045417 | 5883 | 0.066604 | 6167 | 3.0009e-05 | 7934
EL CERRITO G 1112BR196 | EL CERRITO G 1112 | 12501112 | TRUE | 3.615 | 3.6332 | 0.010953 | 57.75 | 0.00052705 | 5103 | 0.057531 | 7354 | 3.0005e-05 | 7935
GRANT 1106CB | GRANT 1106 | 14381106 |  | 10.6588 | 11.5805 |  | 148.1667 | 0.00053392 | 5024 | 0.05641 | 7515 | 3.0002e-05 | 7936
CHEROKEE 1102CB | CHEROKEE 1102 | 163651102 |  | 6.9707 | 1.834 |  | 135.3333 | 0.00041535 | 6276 | 0.074044 | 4550 | 2.9996e-05 | 7937
MOLINO 1104378 | MOLINO 1104 | 42571104 |  | 8.251 | 2.1051 |  | 150.5 | 0.00045985 | 5808 | 0.065953 | 6282 | 2.997e-05 | 7938
SHAFTER 1102CB | SHAFTER 1102 | 253651102 |  | 6.3891 | 0.54095 |  | 82.6667 | 0.00040121 | 6437 | 0.075349 | 4355 | 2.9967e-05 | 7939
EL CERRITO G 1110173396 | EL CERRITO G 1110 | 12501110 | TRUE | 0.16643 | 0.032263 | 0.19869 | 2.3333 | 0.00048426 | 5554 | 0.063499 | 6614 | 2.9938e-05 | 7940
GUERNSEY 1102CB | GUERNSEY 1102 | 252661102 |  | 6.9774 | 0.3822 |  | 113.45 | 0.00038837 | 6600 | 0.077185 | 3605 | 2.9932e-05 | 7941
MERCED 110890510 | MERCED 1108 | 252801108 |  | 0.686 | 0.011249 |  | 9 | 0.00056392 | 4719 | 0.053073 | 8251 | 2.9929e-05 | 7942
KEARNEY 111086202 | KEARNEY 1110 | 252701110 |  | 7.4338 | 2.0044 |  | 127.5 | 0.00042317 | 6190 | 0.072688 | 4696 | 2.9925e-05 | 7943
MC CALL 1102310426 | MC CALL 1102 | 254121102 |  | 10.7755 | 7.1204 |  | 174.5 | 0.00051438 | 5241 | 0.061528 | 6824 | 2.9924e-05 | 7944
NOVATO 1104889406 | NOVATO 1104 | 42211104 |  | 0.068584 | 0 |  | 1 | 0.0004275 | 6145 | 0.069972 | 5050 | 2.9913e-05 | 7945
MARYSVILLE 1108CB | MARYSVILLE 1108 | 152011108 |  | 22.3897 | 6.0348 |  | 405.3333 | 0.00043469 | 6062 | 0.07154 | 4825 | 2.9912e-05 | 7946
CASTRO VALLEY 1103MR219 | CASTRO VALLEY 1103 | 14091103 |  | 3.2835 | 3.4274 |  | 49.25 | 0.00056358 | 4720 | 0.053073 | 8252 | 2.9911e-05 | 7947
WILLIAMS 1102CB | WILLIAMS 1102 | 62051102 |  | 7.519 | 3.4324 |  | 118.5 | 0.00052016 | 5176 | 0.058688 | 7200 | 2.9907e-05 | 7948
BUTTE 1107CB | BUTTE 1107 | 103081107 |  | 15.1752 | 2.8716 |  | 271.5 | 0.00043844 | 6028 | 0.068998 | 5190 | 2.9905e-05 | 7949
TUDOR 1101CB | TUDOR 1101 | 153711101 |  | 0.23959 | 0.0054151 |  | 3.3333 | 0.00038621 | 6626 | 0.0774 | 3398 | 2.9893e-05 | 7950
GRAND ISLAND 2227CB | GRAND ISLAND 2227 | 62462227 |  | 8.7178 | 0.91632 |  | 146.3667 | 0.00038761 | 6610 | 0.07718 | 3613 | 2.9891e-05 | 7951
AIRWAYS 110629609 | AIRWAYS 1106 | 252041106 |  | 6.9464 | 1.0405 |  | 127 | 0.00039742 | 6485 | 0.075744 | 4280 | 2.9885e-05 | 7952
SALINAS 110455450 | SALINAS 1104 | 182011104 |  | 16.2378 | 14.743 |  | 258.0833 | 0.00052043 | 5174 | 0.05828 | 7256 | 2.9876e-05 | 7953
HICKS 2103XR248 | HICKS 2103 | 83432103 | TRUE | 1.5141 | 2.0879 | 0.06538 | 27.5 | 0.00042642 | 6154 | 0.070283 | 4984 | 2.9874e-05 | 7954
MARICOPA 110265196 | MARICOPA 1102 | 254211102 |  | 0.92586 | 1.0904 |  | 22.5 | 0.00046099 | 5797 | 0.06568 | 6328 | 2.9866e-05 | 7955
DINUBA 11057800 | DINUBA 1105 | 254091105 |  | 5.3061 | 3.1541 |  | 95 | 0.00047503 | 5645 | 0.068437 | 5299 | 2.9855e-05 | 7956
LARKIN (Y) 1111CB | LARKIN (Y) 1111 | 22801111 |  | 0.11595 | 0.1836 |  | 4.25 | 0.00056253 | 4731 | 0.053073 | 8251 | 2.9855e-05 | 7957
COALINGA NO 2 1105134928 | COALINGA NO 2 1105 | 252381105 |  | 0.046584 | 0 |  | 1.5 | 0.00044557 | 5959 | 0.067 | 6057 | 2.9853e-05 | 7958
PENRYN 110651674 | PENRYN 1106 | 152561106 |  | 11.059 | 3.0776 |  | 184.8333 | 0.00044945 | 5924 | 0.066623 | 6161 | 2.9844e-05 | 7959
ARCATA 112233062 | ARCATA 1122 | 192021122 |  | 4.8363 | 1.1217 |  | 87 | 0.00044618 | 5948 | 0.06692 | 6085 | 2.9842e-05 | 7960
COALINGA NO 1 11089240 | COALINGA NO 1 1108 | 252161108 |  | 2.6013 | 0.020505 |  | 43.5 | 0.00044523 | 5960 | 0.067 | 6057 | 2.9831e-05 | 7961
EL CAPITAN 110433808 | EL CAPITAN 1104 | 253881104 |  | 4.1596 | 4.033 |  | 74 | 0.00052917 | 5082 | 0.057424 | 7369 | 2.9807e-05 | 7962
INDUSTRIAL ACRES 041249158 | INDUSTRIAL ACRES 0412 | 182300412 |  | 2.5249 | 2.9104 |  | 40.8333 | 0.00056145 | 4737 | 0.053073 | 8250 | 2.9798e-05 | 7963
MC CALL 110390986 | MC CALL 1103 | 254121103 |  | 1.5369 | 0.21433 |  | 26 | 0.00042983 | 6122 | 0.070028 | 5041 | 2.9791e-05 | 7964
DOS PALOS 110137478 | DOS PALOS 1101 | 254041101 |  | 7.2271 | 6.3812 |  | 123.5 | 0.000516 | 5215 | 0.059261 | 7120 | 2.9787e-05 | 7965
CASSIDY 2108CB | CASSIDY 2108 | 254272108 |  | 3.8607 | 0.16734 |  | 53 | 0.00040757 | 6362 | 0.073279 | 4637 | 2.9767e-05 | 7966
MOUNTAIN VIEW 111160078 | MOUNTAIN VIEW 1111 | 82031111 |  | 0.62842 | 0.35588 |  | 10 | 0.00056088 | 4744 | 0.053073 | 8251 | 2.9767e-05 | 7967
LEMOORE 1101546704 | LEMOORE 1101 | 253601101 |  | 7.0867 | 5.1685 |  | 126.3333 | 0.00051286 | 5257 | 0.060193 | 6996 | 2.976e-05 | 7968
GABILAN 1102CB | GABILAN 1102 | 182331102 |  | 9.6857 | 5.7782 |  | 180 | 0.00046764 | 5722 | 0.06423 | 6515 | 2.9759e-05 | 7969
MIDDLETOWN 1102632616 | MIDDLETOWN 1102 | 43141102 |  | 0.23623 | 0.016171 |  | 5 | 0.00046273 | 5776 | 0.064972 | 6439 | 2.9752e-05 | 7970
PEABODY 210818182 | PEABODY 2108 | 63642108 |  | 0.013081 | 0 |  | 1 | 0.0004183 | 6241 | 0.071126 | 4879 | 2.9752e-05 | 7971
WEST FRESNO 1112CB | WEST FRESNO 1112 | 253731112 |  | 14.2958 | 4.9871 |  | 255.375 | 0.00040637 | 6379 | 0.074439 | 4494 | 2.9751e-05 | 7972
PARKWAY 1101688 | PARKWAY 1101 | 42051101 |  | 3.4758 | 2.6634 |  | 53.3333 | 0.00053069 | 5066 | 0.057083 | 7427 | 2.9747e-05 | 7973
MONROE 1105919 | MONROE 1105 | 43301105 |  | 0.82266 | 0.1636 |  | 14.3333 | 0.00056044 | 4748 | 0.053073 | 8250 | 2.9744e-05 | 7974
HAYWARD O 0401CB | HAYWARD O 0401 | 12240401 |  | 3.3605 | 3.7181 |  | 45.9167 | 0.00056026 | 4752 | 0.053073 | 8251 | 2.9735e-05 | 7975
SF L 0404CB | SF L 0404 | 22260404 |  | 0.79794 | 0.80549 |  | 16.8333 | 0.00056013 | 4754 | 0.053073 | 8252 | 2.9728e-05 | 7976
OAK 0401CB | OAK 0401 | 12600401 | FALSE | 2.971 | 3.0177 | 2.8044 | 40.9167 | 0.00047206 | 5678 | 0.06326 | 6636 | 2.9725e-05 | 7977
SF M 0405CB | SF M 0405 | 22270405 |  | 2.3564 | 2.8804 |  | 46 | 0.00055973 | 4760 | 0.05326 | 8192 | 2.9722e-05 | 7978
VINA 1101CB | VINA 1101 | 103581101 |  | 0.62635 | 0.020613 |  | 10.3333 | 0.00044349 | 5980 | 0.06702 | 6002 | 2.9721e-05 | 7979
WYANDOTTE 11095973 | WYANDOTTE 1109 | 102911109 | TRUE | 2.4732 | 1.1706 | 0.038454 | 50.5 | 0.00043 | 6119 | 0.067824 | 5468 | 2.9716e-05 | 7980
ACTON 0402CB | ACTON 0402 | 22470402 |  | 4.4377 | 5.009 |  | 67.0833 | 0.00054806 | 4877 | 0.054178 | 7908 | 2.9712e-05 | 7981
CORCORAN 1106936848 | CORCORAN 1106 | 252171106 |  | 1.854 | 0.097917 |  | 30.3333 | 0.0004439 | 5974 | 0.067942 | 5417 | 2.9705e-05 | 7982
HUMBOLDT BAY 1102CB | HUMBOLDT BAY 1102 | 192341102 |  | 6.4771 | 1.46 |  | 132.5 | 0.00044854 | 5928 | 0.066347 | 6212 | 2.9701e-05 | 7983
CLOVERDALE 110276878 | CLOVERDALE 1102 | 42821102 |  | 1.6218 | 0.8125 |  | 31.8333 | 0.00046795 | 5715 | 0.066022 | 6268 | 2.9698e-05 | 7984
AVENAL 2101CB | AVENAL 2101 | 255002101 |  | 9.2267 | 0.014006 |  | 159.3333 | 0.00043469 | 6063 | 0.069358 | 5137 | 2.9687e-05 | 7985
PANORAMA 11022009 | PANORAMA 1102 | 103461102 |  | 0.80562 | 0.11573 |  | 18 | 0.00044297 | 5985 | 0.067 | 6057 | 2.9679e-05 | 7986
RIVERBANK 17159850 | RIVERBANK 1715 | 163191715 |  | 7.5422 | 0.6229 |  | 135.5 | 0.00044366 | 5977 | 0.070041 | 5039 | 2.9662e-05 | 7987
OROVILLE 1101CB | OROVILLE 1101 | 102521101 |  | 14.3535 | 3.9329 |  | 219.5 | 0.00046464 | 5755 | 0.064688 | 6473 | 2.9655e-05 | 7988
BELMONT 040153783 | BELMONT 0401 | 24030401 |  | 0.3346 | 0.27135 |  | 6.3333 | 0.00055851 | 4767 | 0.053073 | 8251 | 2.9641e-05 | 7989
CLARKSVILLE 210319572 | CLARKSVILLE 2103 | 153612103 | TRUE | 2.7131 | 0 | 0.23228 | 55 | 0.0001379 | 10814 | 0.20484 | 3137 | 2.9632e-05 | 7990
LOS OSITOS 21017058 | LOS OSITOS 2101 | 182082101 |  | 5.4146 | 0.31446 |  | 110 | 0.00044226 | 5993 | 0.067 | 6057 | 2.9631e-05 | 7991
WILLOW PASS 2107537100 | WILLOW PASS 2107 | 13912107 |  | 0.58732 | 0.24307 |  | 11 | 0.00055825 | 4775 | 0.053073 | 8251 | 2.9628e-05 | 7992
DUMBARTON 1102MR228 | DUMBARTON 1102 | 14471102 |  | 4.0261 | 3.5196 |  | 78.5 | 0.00055811 | 4778 | 0.053073 | 8251 | 2.9621e-05 | 7993
HIGHLANDS 110265650 | HIGHLANDS 1102 | 43361102 |  | 0.8154 | 0.63333 |  | 16.3333 | 0.00050139 | 5380 | 0.060706 | 6924 | 2.9617e-05 | 7994
ATWATER 110710530 | ATWATER 1107 | 253611107 |  | 3.1048 | 2.179 |  | 54.8333 | 0.00054933 | 4869 | 0.054182 | 7907 | 2.961e-05 | 7995
WHEATLAND 1102CB | WHEATLAND 1102 | 152811102 |  | 9.9156 | 2.9986 |  | 160.3333 | 0.0004424 | 5991 | 0.070348 | 4971 | 2.9608e-05 | 7996
NEWARK 21KV 210348722 | NEWARK 21KV 2103 | 12232103 |  | 0.0049187 | 0 |  | 0.33333 | 0.00055786 | 4781 | 0.053073 | 8251 | 2.9607e-05 | 7997
WALDO 0402258792 | WALDO 0402 | 13350402 | FALSE | 3.0011 | 3.6441 | 6.5794 | 48.75 | 0.00047237 | 5673 | 0.061981 | 6766 | 2.9606e-05 | 7998
NEWARK 12KV 1107MR754 | NEWARK 12KV 1107 | 12221107 |  | 8.189 | 9.1867 |  | 120.3333 | 0.0005577 | 4783 | 0.053073 | 8251 | 2.9599e-05 | 7999
SAN BENITO 2101506268 | SAN BENITO 2101 | 182742101 |  | 0.27693 | 0 |  | 7.3333 | 0.00044173 | 5995 | 0.067 | 6058 | 2.9596e-05 | 8000
SANTA MARIA 1112M06 | SANTA MARIA 1112 | 182671112 |  | 3.9501 | 1.7152 |  | 69.5 | 0.00050232 | 5367 | 0.060688 | 6928 | 2.9591e-05 | 8001
SHARON 1101400060 | SHARON 1101 | 255331101 |  | 1.5137 | 0.016791 |  | 21.3333 | 0.00038193 | 6677 | 0.0774 | 3398 | 2.9562e-05 | 8002
LAWNDALE 0402CB | LAWNDALE 0402 | 22440402 |  | 4.7459 | 5.0668 |  | 81.8333 | 0.00051066 | 5278 | 0.057668 | 7336 | 2.9556e-05 | 8003
LOGAN CREEK 21012406 | LOGAN CREEK 2101 | 103142101 |  | 10.6261 | 0.54767 |  | 179 | 0.00040749 | 6363 | 0.072819 | 4682 | 2.9549e-05 | 8004
SF N 0408CB | SF N 0408 | 22280408 |  | 3.1196 | 4.2013 |  | 58.0833 | 0.00055672 | 4797 | 0.053073 | 8251 | 2.9547e-05 | 8005
FIREBAUGH 110297290 | FIREBAUGH 1102 | 253471102 |  | 2.4775 | 1.2772 |  | 45 | 0.00051706 | 5203 | 0.056857 | 7458 | 2.954e-05 | 8006
PAUL SWEET 210111147 | PAUL SWEET 2101 | 83252101 |  | 2.2783 | 1.9821 |  | 39 | 0.00047602 | 5637 | 0.061551 | 6819 | 2.9539e-05 | 8007
RESERVATION ROAD 1101CB | RESERVATION ROAD 1101 | 182731101 | TRUE | 0.69547 | 0.10643 | 0.26838 | 9 | 0.00038821 | 6603 | 0.068384 | 5307 | 2.9533e-05 | 8008
BAHIA 11033304 | BAHIA 1103 | 43251103 |  | 5.5913 | 1.7583 |  | 97.8333 | 0.00048367 | 5561 | 0.061575 | 6816 | 2.9525e-05 | 8009
MADERA 11041990 | MADERA 1104 | 252761104 |  | 2.5122 | 1.5822 |  | 40 | 0.0005541 | 4827 | 0.053395 | 8140 | 2.9521e-05 | 8010
ARCATA 110556120 | ARCATA 1105 | 192021105 |  | 2.4771 | 1.8085 |  | 35 | 0.00049121 | 5484 | 0.06068 | 6929 | 2.9521e-05 | 8011
WESTLEY 1101CB | WESTLEY 1101 | 162671101 |  | 6.6912 | 0.76013 |  | 115 | 0.00042077 | 6219 | 0.071215 | 4868 | 2.9516e-05 | 8012
KING CITY 11057078 | KING CITY 1105 | 182031105 |  | 0.89827 | 0.073685 |  | 18 | 0.00042978 | 6123 | 0.068733 | 5234 | 2.9507e-05 | 8013
BIOLA 1101R1129 | BIOLA 1101 | 252211101 |  | 0.85802 | 0.54995 |  | 13 | 0.00045636 | 5852 | 0.066172 | 6238 | 2.9507e-05 | 8014
SONOMA 1105308 | SONOMA 1105 | 42721105 |  | 10.0657 | 1.2003 |  | 183.5 | 0.00043774 | 6034 | 0.067403 | 5664 | 2.9495e-05 | 8015
LIVINGSTON 1106215606 | LIVINGSTON 1106 | 252261106 |  | 1.6095 | 0.66777 |  | 25.5 | 0.00052576 | 5114 | 0.056609 | 7491 | 2.9491e-05 | 8016
SPENCE 1102756550 | SPENCE 1102 | 182201102 |  | 0.72252 | 0.091678 |  | 16.3333 | 0.00043834 | 6030 | 0.067212 | 5797 | 2.9485e-05 | 8017
MC ARTHUR 1101CB | MC ARTHUR 1101 | 103491101 |  | 0.74423 | 0.30032 |  | 11.5 | 0.0004473 | 5939 | 0.065789 | 6305 | 2.9485e-05 | 8018
FIREBAUGH 110111940 | FIREBAUGH 1101 | 253471101 |  | 2.8067 | 1.9766 |  | 52 | 0.0004759 | 5641 | 0.063159 | 6648 | 2.9485e-05 | 8019
GRAND ISLAND 22248882 | GRAND ISLAND 2224 | 62462224 |  | 12.0415 | 0.86712 |  | 227.5 | 0.00038792 | 6606 | 0.076353 | 4067 | 2.9478e-05 | 8020
DAVIS 1106CB | DAVIS 1106 | 62041106 |  | 15.3975 | 3.798 |  | 229.2 | 0.00046709 | 5724 | 0.069418 | 5124 | 2.9472e-05 | 8021
RICE 1102CB | RICE 1102 | 62831102 |  | 5.2915 | 0.97058 |  | 83.5 | 0.00040083 | 6444 | 0.074589 | 4475 | 2.9466e-05 | 8022
METTLER 110936724 | METTLER 1109 | 163701109 |  | 7.4908 | 1.6476 |  | 134 | 0.00039886 | 6465 | 0.074827 | 4438 | 2.9461e-05 | 8023
OAKLAND X 1107CR424 | OAKLAND X 1107 | 12541107 |  | 5.3229 | 6.3366 |  | 76.6667 | 0.00054414 | 4919 | 0.054342 | 7882 | 2.9459e-05 | 8024
BAHIA 1101CB | BAHIA 1101 | 43251101 |  | 1.6807 | 0 |  | 26.3333 | 0.00045377 | 5887 | 0.065931 | 6286 | 2.9451e-05 | 8025
VINA 110189142 | VINA 1101 | 103581101 |  | 6.664 | 0.25169 |  | 135 | 0.00042564 | 6167 | 0.070365 | 4967 | 2.9449e-05 | 8026
UKIAH 1111168892 | UKIAH 1111 | 42771111 | TRUE | 0.69075 | 0.051714 | 0.091564 | 12.5 | 0.0002144 | 9787 | 0.19051 | 3158 | 2.9449e-05 | 8027
FREMONT 1107CB | FREMONT 1107 | 14351107 |  | 13.1944 | 12.9854 |  | 212.5 | 0.00055477 | 4822 | 0.053073 | 8251 | 2.9443e-05 | 8028
RICHMOND R 1121BR210 | RICHMOND R 1121 | 13471121 |  | 1.5792 | 2.1282 |  | 23.6667 | 0.0005071 | 5315 | 0.058583 | 7214 | 2.9441e-05 | 8029
ANITA 1106CB | ANITA 1106 | 102841106 |  | 10.7583 | 0.80103 |  | 193 | 0.00043796 | 6033 | 0.067647 | 5527 | 2.944e-05 | 8030
TEMPLETON 2110211842 | TEMPLETON 2110 | 183052110 |  | 0.067893 | 0 |  | 1 | 0.00043919 | 6017 | 0.067 | 6057 | 2.9426e-05 | 8031
LLAGAS 2106CB | LLAGAS 2106 | 83182106 |  | 10.9103 | 0.73881 |  | 219.5 | 0.00043693 | 6045 | 0.067472 | 5620 | 2.9421e-05 | 8032
TAFT 110189056 | TAFT 1101 | 252081101 |  | 2.4852 | 0.27017 |  | 41.3333 | 0.00043601 | 6057 | 0.067503 | 5599 | 2.9419e-05 | 8033
MENLO 1102CB | MENLO 1102 | 24131102 |  | 0.57569 | 0.50495 |  | 17.5 | 0.00050145 | 5379 | 0.056748 | 7473 | 2.9378e-05 | 8034
MORGAN HILL 2110XR164 | MORGAN HILL 2110 | 83242110 |  | 7.1238 | 2.3683 |  | 114.1667 | 0.00035098 | 7123 | 0.085805 | 3366 | 2.9368e-05 | 8035
HENRIETTA 110655710 | HENRIETTA 1106 | 252681106 |  | 0.025904 | 0 |  | 0.33333 | 0.00055328 | 4830 | 0.053073 | 8251 | 2.9364e-05 | 8036
MADERA 11195040 | MADERA 1119 | 252761119 |  | 6.7795 | 1.0043 |  | 115 | 0.00039034 | 6566 | 0.075677 | 4293 | 2.9361e-05 | 8037
SANTA RITA 110211310 | SANTA RITA 1102 | 253541102 |  | 0.027843 | 0 |  | 0.5 | 0.00037924 | 6706 | 0.0774 | 3397 | 2.9353e-05 | 8038
LAMONT 1106CB | LAMONT 1106 | 253911106 |  | 6.1533 | 0.37093 |  | 93.2833 | 0.00038786 | 6608 | 0.076533 | 4004 | 2.9332e-05 | 8039
BRENTWOOD 211249428 | BRENTWOOD 2112 | 14592112 |  | 3.1993 | 0.16533 |  | 55.5 | 0.00037891 | 6712 | 0.0774 | 3397 | 2.9328e-05 | 8040
HURON 11129840 | HURON 1112 | 253161112 |  | 1.9629 | 1.7275 |  | 35 | 0.00054248 | 4929 | 0.055056 | 7743 | 2.9323e-05 | 8041
LEMOORE 1103CB | LEMOORE 1103 | 253601103 |  | 8.2736 | 3.6156 |  | 133.0333 | 0.00049228 | 5470 | 0.062684 | 6692 | 2.9321e-05 | 8042
WOODLAND 1106CB | WOODLAND 1106 | 62031106 |  | 0.97662 | 0.066067 |  | 24.5 | 0.00046241 | 5779 | 0.065836 | 6298 | 2.9319e-05 | 8043
LOCKEFORD 21015724 | LOCKEFORD 2101 | 163682101 |  | 7.554 | 2.3653 |  | 133 | 0.00037958 | 6700 | 0.077308 | 3463 | 2.9309e-05 | 8044
BANTA 1101CB | BANTA 1101 | 162471101 |  | 5.3114 | 0.56673 |  | 100.5 | 0.0004149 | 6282 | 0.072039 | 4773 | 2.9309e-05 | 8045
LAMONT 11043855 | LAMONT 1104 | 253911104 |  | 3.5214 | 0.063512 |  | 59.5 | 0.00043315 | 6084 | 0.06754 | 5580 | 2.927e-05 | 8046
ORTIGA 110655980 | ORTIGA 1106 | 254311106 |  | 0.43495 | 0 |  | 3.8333 | 0.00037816 | 6725 | 0.0774 | 3397 | 2.9269e-05 | 8047
ATWATER 110375276 | ATWATER 1103 | 253611103 |  | 2.2958 | 0.40302 |  | 42.5 | 0.00038575 | 6636 | 0.076541 | 3999 | 2.9266e-05 | 8048
CORONA 1103176 | CORONA 1103 | 43491103 |  | 4.1953 | 0.88938 |  | 82.8333 | 0.0004424 | 5992 | 0.066253 | 6222 | 2.9253e-05 | 8049
KINGSBURG 111468916 | KINGSBURG 1114 | 252241114 |  | 0.06491 | 0 |  | 1.5 | 0.00037795 | 6728 | 0.0774 | 3397 | 2.9253e-05 | 8050
GERBER 110137366 | GERBER 1101 | 103391101 |  | 3.8368 | 0.083551 |  | 70.5 | 0.00043378 | 6074 | 0.06759 | 5558 | 2.9246e-05 | 8051
MENLO 1101CB | MENLO 1101 | 24131101 |  | 1.3732 | 1.0866 |  | 25.5 | 0.00055104 | 4854 | 0.053073 | 8251 | 2.9245e-05 | 8052
CORONA 1101248 | CORONA 1101 | 43491101 |  | 4.2087 | 1.0168 |  | 77 | 0.00043751 | 6036 | 0.066857 | 6108 | 2.9231e-05 | 8053
DAVIS 1106848866 | DAVIS 1106 | 62041106 |  | 0.02035 | 0 |  | 0.5 | 0.00037752 | 6730 | 0.0774 | 3397 | 2.922e-05 | 8054
OILFIELDS 1102CB | OILFIELDS 1102 | 182391102 |  | 2.533 | 0.021413 |  | 41.8333 | 0.00043652 | 6048 | 0.066948 | 6081 | 2.9217e-05 | 8055
REDWOOD CITY 11054828 | REDWOOD CITY 1105 | 24161105 |  | 0.027509 | 0 |  | 0.5 | 0.00037747 | 6731 | 0.0774 | 3397 | 2.9216e-05 | 8056
BORDEN 110290040 | BORDEN 1102 | 255121102 |  | 11.7385 | 4.4379 |  | 221.5 | 0.0004306 | 6112 | 0.069554 | 5112 | 2.9213e-05 | 8057
BELLE HAVEN 1102CB | BELLE HAVEN 1102 | 24021102 |  | 1.6789 | 0 |  | 30.5 | 0.0004822 | 5578 | 0.066632 | 6156 | 2.9197e-05 | 8058
ATWATER 1105524022 | ATWATER 1105 | 253611105 |  | 3.0865 | 1.8925 |  | 48 | 0.00053974 | 4962 | 0.054445 | 7854 | 2.9195e-05 | 8059
TULUCAY 1101137224 | TULUCAY 1101 | 42301101 |  | 0.10523 | 0 |  | 1 | 0.00043455 | 6065 | 0.06714 | 5862 | 2.9176e-05 | 8060
LOYOLA 1102LL66 | LOYOLA 1102 | 82161102 |  | 4.1896 | 1.3003 |  | 83 | 0.00043364 | 6075 | 0.067225 | 5784 | 2.9171e-05 | 8061
NAPA 1102942 | NAPA 1102 | 42021102 |  | 11.3417 | 0.8157 |  | 218 | 0.00042904 | 6128 | 0.067869 | 5452 | 2.9166e-05 | 8062
MORMON 110149738 | MORMON 1101 | 163211101 |  | 11.3998 | 3.6947 |  | 208.8333 | 0.0004398 | 6013 | 0.069046 | 5185 | 2.914e-05 | 8063
LIVINGSTON 1106CB | LIVINGSTON 1106 | 252261106 |  | 24.5477 | 5.0801 |  | 421.3333 | 0.00040432 | 6405 | 0.074051 | 4549 | 2.9129e-05 | 8064
LAMONT 11021644 | LAMONT 1102 | 253911102 |  | 3.1536 | 0.018713 |  | 52.5 | 0.00042089 | 6218 | 0.069761 | 5081 | 2.9126e-05 | 8065
TIVY VALLEY 110737522 | TIVY VALLEY 1107 | 252941107 | TRUE | 3.1041 | 1.0842 | 0.48418 | 65.5 | 0.00020337 | 9989 | 0.1914 | 3156 | 2.9115e-05 | 8066
KEARNEY 1104CB | KEARNEY 1104 | 252701104 |  | 5.2597 | 1.2659 |  | 93 | 0.00037957 | 6701 | 0.076877 | 3843 | 2.9104e-05 | 8067
SALINAS 110622288 | SALINAS 1106 | 182011106 |  | 4.7309 | 3.4245 |  | 80.8333 | 0.00051305 | 5254 | 0.05798 | 7293 | 2.9098e-05 | 8068
PLEASANT GROVE 211050514 | PLEASANT GROVE 2110 | 152442110 |  | 5.9472 | 0.10227 |  | 91 | 0.00043867 | 6025 | 0.066769 | 6128 | 2.9096e-05 | 8069
PRUNEDALE 110722448 | PRUNEDALE 1107 | 182961107 |  | 4.9112 | 0.5064 |  | 92 | 0.0004566 | 5850 | 0.064285 | 6509 | 2.9091e-05 | 8070
MILLBRAE 11021033 | MILLBRAE 1102 | 22691102 |  | 1.829 | 1.8538 |  | 38.5 | 0.0004918 | 5477 | 0.058884 | 7174 | 2.9086e-05 | 8071
SF H 11066955 | SF H 1106 | 22101106 |  | 0.39514 | 0.52021 |  | 6.6667 | 0.00053023 | 5072 | 0.057938 | 7301 | 2.907e-05 | 8072
BURNEY 110257046 | BURNEY 1102 | 103311102 | TRUE | 0.71336 | 0.29254 | 0.0079332 | 10.3333 | 0.00044511 | 5961 | 0.065302 | 6392 | 2.9063e-05 | 8073
LARKIN (Y) 1128CB | LARKIN (Y) 1128 | 22801128 |  | 0.11143 | 0.22136 |  | 3.8333 | 0.0005475 | 4886 | 0.053073 | 8251 | 2.9057e-05 | 8074
WOODWARD 2108CUS5875 | WOODWARD 2108 | 255292108 |  | 0.0094698 | 0 |  | 0.5 | 0.00043362 | 6076 | 0.067 | 6057 | 2.9052e-05 | 8075
GIFFEN 1107CB | GIFFEN 1107 | 253151107 |  | 2.6373 | 0 |  | 15.5833 | 0.00037497 | 6763 | 0.0774 | 3399 | 2.9023e-05 | 8076
MOLINO 11034682 | MOLINO 1103 | 42571103 |  | 7.4673 | 2.6901 |  | 126 | 0.00044712 | 5940 | 0.065145 | 6412 | 2.9007e-05 | 8077
SANGER 1114R2920 | SANGER 1114 | 252351114 |  | 9.7909 | 1.9506 |  | 173 | 0.00038994 | 6572 | 0.074112 | 4540 | 2.9006e-05 | 8078
LLAGAS 210137264 | LLAGAS 2101 | 83182101 |  | 10.567 | 1.1214 |  | 207.4167 | 0.0004279 | 6141 | 0.067869 | 5453 | 2.8986e-05 | 8079
PEACHTON 11011980 | PEACHTON 1101 | 103241101 |  | 7.9654 | 1.9054 |  | 136.5 | 0.00042325 | 6188 | 0.070276 | 4987 | 2.8979e-05 | 8080
PRUNEDALE 1110607060 | PRUNEDALE 1110 | 182961110 |  | 11.4464 | 3.2284 |  | 211 | 0.00043155 | 6102 | 0.067155 | 5847 | 2.8975e-05 | 8081
HALF MOON BAY 110376762 | HALF MOON BAY 1103 | 24101103 |  | 0.50809 | 0.34222 |  | 9 | 0.00043576 | 6058 | 0.065472 | 6367 | 2.8974e-05 | 8082
FREMONT 1104MR584 | FREMONT 1104 | 14351104 |  | 6.545 | 6.3891 |  | 101 | 0.00050708 | 5316 | 0.057667 | 7337 | 2.8955e-05 | 8083
FREMONT 1103MR733 | FREMONT 1103 | 14351103 |  | 0.18772 | 0 |  | 3.5 | 0.00049773 | 5417 | 0.057052 | 7431 | 2.8946e-05 | 8084
HOLLISTER 21034906 | HOLLISTER 2103 | 182492103 |  | 4.5299 | 2.8874 |  | 74.1667 | 0.00052419 | 5137 | 0.056545 | 7500 | 2.8944e-05 | 8085
WILLOW PASS 210879972 | WILLOW PASS 2108 | 13912108 |  | 10.2068 | 5.2938 |  | 140.8333 | 0.00048361 | 5562 | 0.062286 | 6734 | 2.8941e-05 | 8086
OLEMA 1101CB | OLEMA 1101 | 42291101 |  | 0.084684 | 0.049706 |  | 1.5 | 0.00043186 | 6095 | 0.067 | 6057 | 2.8934e-05 | 8087
LAMONT 1103CB | LAMONT 1103 | 253911103 |  | 11.6189 | 0.45778 |  | 196.45 | 0.00037461 | 6772 | 0.07732 | 3445 | 2.8934e-05 | 8088
IGNACIO 1105490728 | IGNACIO 1105 | 42481105 | FALSE | 0.87934 | 0.93074 | 1.0881 | 13.5 | 0.00050011 | 5389 | 0.05371 | 8024 | 2.8908e-05 | 8089
SONOMA 1102113082 | SONOMA 1102 | 42721102 |  | 0.68459 | 0.16455 |  | 12.8333 | 0.00043172 | 6098 | 0.067769 | 5485 | 2.8901e-05 | 8090
GANSNER 1101CB | GANSNER 1101 | 103021101 |  | 0.66783 | 0.11695 |  | 6.5 | 0.00043854 | 6026 | 0.065929 | 6288 | 2.89e-05 | 8091
MC KEE 1107XR032 | MC KEE 1107 | 83531107 |  | 10.7429 | 8.193 |  | 178.6667 | 0.00048046 | 5598 | 0.061341 | 6846 | 2.8895e-05 | 8092
CASTRO 0402CB | CASTRO 0402 | 22480402 |  | 2.6213 | 3.0847 |  | 39.0333 | 0.00053146 | 5055 | 0.055786 | 7621 | 2.8875e-05 | 8093
SEMITROPIC 1110CB | SEMITROPIC 1110 | 252901110 |  | 9.2772 | 0.23325 |  | 135.8333 | 0.00037883 | 6713 | 0.076631 | 3969 | 2.8874e-05 | 8094
MC FARLAND 1104330930 | MC FARLAND 1104 | 253181104 |  | 5.433 | 0.40422 |  | 94 | 0.00038277 | 6668 | 0.075658 | 4297 | 2.8861e-05 | 8095
SAN LEANDRO U 1151MR752 | SAN LEANDRO U 1151 | 13111151 |  | 1.8534 | 2.7275 |  | 33.1667 | 0.00054343 | 4920 | 0.053073 | 8250 | 2.8841e-05 | 8096
DIVIDE 110266960 | DIVIDE 1102 | 182571102 |  | 3.2412 | 3.4401 |  | 47 | 0.00046678 | 5730 | 0.06218 | 6748 | 2.884e-05 | 8097
SAN LEANDRO U 1151CB | SAN LEANDRO U 1151 | 13111151 |  | 4.0926 | 3.0629 |  | 57.8333 | 0.00054318 | 4922 | 0.053073 | 8254 | 2.8828e-05 | 8098
CRESSEY 210337008 | CRESSEY 2103 | 254702103 |  | 2.4396 | 0.057627 |  | 50.5 | 0.00037245 | 6797 | 0.0774 | 3397 | 2.8828e-05 | 8099
MILLBRAE 110810045 | MILLBRAE 1108 | 22691108 |  | 4.4176 | 4.8244 |  | 70.3333 | 0.00049408 | 5455 | 0.059292 | 7112 | 2.8827e-05 | 8100
SANTA YNEZ 1104Y30 | SANTA YNEZ 1104 | 182721104 |  | 9.9429 | 3.5855 |  | 166.5 | 0.00035714 | 7019 | 0.085794 | 3367 | 2.8825e-05 | 8101
DAIRYLAND 1102CB | DAIRYLAND 1102 | 252421102 |  | 3.869 | 0.32318 |  | 70.75 | 0.00037228 | 6798 | 0.0774 | 3397 | 2.8814e-05 | 8102
SF J 0409CB | SF J 0409 | 22220409 |  | 0.15039 | 0.1946 |  | 6.6667 | 0.00054281 | 4924 | 0.053073 | 8251 | 2.8808e-05 | 8103
AVENA 1701CB | AVENA 1701 | 163571701 |  | 12.9815 | 0.88941 |  | 215.5 | 0.0003747 | 6769 | 0.076988 | 3767 | 2.8805e-05 | 8104
OLD RIVER 1101372950 | OLD RIVER 1101 | 252821101 |  | 2.1952 | 0.015751 |  | 24.5 | 0.00040161 | 6433 | 0.072435 | 4722 | 2.8801e-05 | 8105
MADISON 1105CB | MADISON 1105 | 63171105 |  | 9.8275 | 1.4649 |  | 164.5 | 0.00041548 | 6271 | 0.07023 | 4998 | 2.88e-05 | 8106
REDBUD 110244119 | REDBUD 1102 | 43191102 | TRUE | 2.802 | 1.2723 | 0.299 | 46.1667 | 0.00044136 | 6000 | 0.066063 | 6255 | 2.8785e-05 | 8107
PLAINFIELD 110521472 | PLAINFIELD 1105 | 63441105 |  | 14.7488 | 0.79407 |  | 260.5 | 0.00038239 | 6671 | 0.07572 | 4285 | 2.8767e-05 | 8108
LARKIN (Y) 1109CB | LARKIN (Y) 1109 | 22801109 |  | 0.29856 | 0.53713 |  | 10.8333 | 0.00054176 | 4936 | 0.053073 | 8250 | 2.8753e-05 | 8109
RIO DELL 11028768 | RIO DELL 1102 | 192251102 |  | 2.3903 | 0 |  | 43.5 | 0.00042912 | 6126 | 0.067 | 6057 | 2.8751e-05 | 8110
TEMPLETON 2113A30 | TEMPLETON 2113 | 183052113 | TRUE | 1.5872 | 0.63752 | 0.25437 | 28 | 0.00038865 | 6595 | 0.085096 | 3369 | 2.8743e-05 | 8111
CARQUINEZ 1103646 | CARQUINEZ 1103 | 43281103 |  | 0.58769 | 0.58898 |  | 10.5 | 0.00054158 | 4940 | 0.053073 | 8251 | 2.8743e-05 | 8112
BELLEVUE 2101656 | BELLEVUE 2101 | 43182101 |  | 2.8745 | 2.8431 |  | 40.1667 | 0.00054135 | 4942 | 0.053073 | 8251 | 2.8731e-05 | 8113
TRIMBLE 1104CB | TRIMBLE 1104 | 83801104 |  | 0.40924 | 0.077874 |  | 7.5 | 0.00054131 | 4943 | 0.053073 | 8251 | 2.8729e-05 | 8114
CASTROVILLE 210422428 | CASTROVILLE 2104 | 182352104 |  | 6.5989 | 0.19895 |  | 129.5 | 0.00042494 | 6175 | 0.067451 | 5635 | 2.8728e-05 | 8115
HENRIETTA 11048560 | HENRIETTA 1104 | 252681104 |  | 0.78738 | 0.074075 |  | 13.5 | 0.00039162 | 6547 | 0.073268 | 4640 | 2.8723e-05 | 8116
SAN LEANDRO U 1107MR596 | SAN LEANDRO U 1107 | 13111107 |  | 1.1294 | 1.2273 |  | 16.8333 | 0.00054116 | 4946 | 0.053073 | 8250 | 2.8721e-05 | 8117
BIOLA 110196864 | BIOLA 1101 | 252211101 |  | 6.7908 | 1.2113 |  | 122.5 | 0.00037389 | 6781 | 0.076909 | 3822 | 2.872e-05 | 8118
NORTH TOWER 11044071 | NORTH TOWER 1104 | 42041104 |  | 0.70027 | 0.48603 |  | 12 | 0.00054113 | 4948 | 0.054944 | 7758 | 2.8719e-05 | 8119
LOS OSITOS 2102CB | LOS OSITOS 2102 | 182082102 |  | 0.34029 | 0 |  | 7.25 | 0.00042858 | 6136 | 0.067 | 6057 | 2.8715e-05 | 8120
GRAND ISLAND 2226CB | GRAND ISLAND 2226 | 62462226 |  | 16.3607 | 1.3949 |  | 313.0333 | 0.00039093 | 6557 | 0.073415 | 4620 | 2.8708e-05 | 8121
SANTA MARIA 1105560634 | SANTA MARIA 1105 | 182671105 |  | 6.075 | 5.1296 |  | 89.5 | 0.00053091 | 5060 | 0.054473 | 7848 | 2.8707e-05 | 8122
COLUSA JUNCTION 110159926 | COLUSA JUNCTION 1101 | 62071101 |  | 1.5499 | 0.26469 |  | 25.3333 | 0.00044427 | 5968 | 0.066696 | 6138 | 2.8695e-05 | 8123
RAWSON 110385334 | RAWSON 1103 | 103531103 |  | 4.1037 | 0.81267 |  | 72 | 0.000426 | 6163 | 0.067362 | 5696 | 2.8691e-05 | 8124
CANAL 1105653704 | CANAL 1105 | 252091105 |  | 0.5931 | 0.93437 |  | 18.5 | 0.00054058 | 4951 | 0.053073 | 8251 | 2.869e-05 | 8125
BORONDA 11013084 | BORONDA 1101 | 182461101 |  | 3.0776 | 0.25968 |  | 61.5 | 0.00042821 | 6140 | 0.067 | 6057 | 2.869e-05 | 8126
PARKWAY 1101702 | PARKWAY 1101 | 42051101 |  | 2.6754 | 2.8009 |  | 43.8333 | 0.00054047 | 4953 | 0.053073 | 8250 | 2.8684e-05 | 8127
OLIVEHURST 11011262 | OLIVEHURST 1101 | 152901101 |  | 6.4957 | 1.0932 |  | 103 | 0.00040096 | 6442 | 0.072663 | 4701 | 2.8676e-05 | 8128
STOREY 11059550 | STOREY 1105 | 254611105 |  | 5.4458 | 0.16602 |  | 94.5 | 0.00038747 | 6614 | 0.075689 | 4290 | 2.8665e-05 | 8129
METTLER 1110CB | METTLER 1110 | 163701110 |  | 11.6506 | 1.2661 |  | 218 | 0.00037832 | 6721 | 0.076107 | 4160 | 2.8656e-05 | 8130
LARKIN (Y) 1119CB | LARKIN (Y) 1119 | 22801119 |  | 0.97616 | 1.5379 |  | 24.8333 | 0.00053985 | 4960 | 0.053073 | 8250 | 2.8651e-05 | 8131
AIRWAYS 1102CB | AIRWAYS 1102 | 252041102 |  | 3.4509 | 0.489 |  | 68.8333 | 0.00039019 | 6570 | 0.074396 | 4503 | 2.8641e-05 | 8132
PLYMOUTH 0401CB | PLYMOUTH 0401 | 22680401 |  | 4.7039 | 6.2654 |  | 68.1667 | 0.00053964 | 4963 | 0.053073 | 8250 | 2.864e-05 | 8133
RIO DELL 1101CB | RIO DELL 1101 | 192251101 |  | 8.3521 | 3.6524 |  | 146 | 0.00043232 | 6089 | 0.065454 | 6368 | 2.8638e-05 | 8134
WEST FRESNO 1101CB | WEST FRESNO 1101 | 253731101 |  | 8.9701 | 4.6387 |  | 168.0179 | 0.00043934 | 6016 | 0.067914 | 5432 | 2.8636e-05 | 8135
VICTOR 1101CB | VICTOR 1101 | 163281101 |  | 6.8211 | 0.52995 |  | 112.3333 | 0.00038594 | 6630 | 0.074557 | 4480 | 2.8628e-05 | 8136
CORCORAN 1102CB | CORCORAN 1102 | 252171102 |  | 0.036957 | 0 |  | 0.45 | 0.00044787 | 5935 | 0.066588 | 6172 | 2.8625e-05 | 8137
OILFIELDS 1103CB | OILFIELDS 1103 | 182391103 |  | 3.3033 | 0.052079 |  | 55.8333 | 0.00042182 | 6209 | 0.067794 | 5477 | 2.8622e-05 | 8138
SAN RAFAEL 1105408 | SAN RAFAEL 1105 | 42011105 |  | 2.0927 | 0.12902 |  | 40 | 0.00043342 | 6080 | 0.066133 | 6240 | 2.8613e-05 | 8139
OAKLAND K 1103CR202 | OAKLAND K 1103 | 12101103 |  | 0.15508 | 0.24699 |  | 4.8333 | 0.00053877 | 4969 | 0.053073 | 8251 | 2.8594e-05 | 8140
PETALUMA C 1106CB | PETALUMA C 1106 | 42631106 |  | 6.0555 | 4.1277 |  | 91 | 0.00053637 | 4995 | 0.05334 | 8161 | 2.859e-05 | 8141
FREMONT 1108CB | FREMONT 1108 | 14351108 |  | 4.8808 | 5.0483 |  | 82.8333 | 0.00053836 | 4974 | 0.053073 | 8251 | 2.8572e-05 | 8142
JESSUP 110338864 | JESSUP 1103 | 103441103 | FALSE | 7.513 | 0.97429 | 1.759 | 133 | 0.00042644 | 6153 | 0.067001 | 6046 | 2.8572e-05 | 8143
WEST FRESNO 1111D2812 | WEST FRESNO 1111 | 253731111 |  | 2.266 | 1.4759 |  | 42 | 0.00047346 | 5664 | 0.062051 | 6757 | 2.8566e-05 | 8144
EL NIDO 1103CB | EL NIDO 1103 | 252451103 |  | 11.0634 | 0.85912 |  | 166.8333 | 0.00038019 | 6694 | 0.075565 | 4321 | 2.8564e-05 | 8145
SF N 0403CB | SF N 0403 | 22280403 |  | 0.7888 | 1.0475 |  | 16 | 0.00053808 | 4976 | 0.053073 | 8251 | 2.8557e-05 | 8146
SAN JOAQUIN 110642822 | SAN JOAQUIN 1106 | 252361106 |  | 1.2981 | 1.4179 |  | 25.8333 | 0.00047901 | 5608 | 0.060359 | 6980 | 2.855e-05 | 8147
WOODWARD 2101CB | WOODWARD 2101 | 255292101 |  | 10.1765 | 0.51144 |  | 190.5 | 0.00044605 | 5952 | 0.065715 | 6321 | 2.8549e-05 | 8148
WILKINS SLOUGH 1102CB | WILKINS SLOUGH 1102 | 62771102 |  | 4.9434 | 0.10426 |  | 52 | 0.00037188 | 6810 | 0.076708 | 3932 | 2.8531e-05 | 8149
AMES 1102LM04 | AMES 1102 | 83901102 |  | 0.86632 | 0.16022 |  | 15.8333 | 0.00053368 | 5032 | 0.053366 | 8149 | 2.8531e-05 | 8150
SUISUN 1103502542 | SUISUN 1103 | 62131103 |  | 1.9297 | 0.17386 |  | 28 | 0.00046311 | 5771 | 0.060806 | 6912 | 2.8512e-05 | 8151
PEASE 1102CB | PEASE 1102 | 153751102 |  | 3.981 | 0.86015 |  | 61.0833 | 0.00044436 | 5967 | 0.068506 | 5286 | 2.8507e-05 | 8152
MORRO BAY 1101V64 | MORRO BAY 1101 | 183011101 |  | 6.5561 | 5.1142 |  | 95.5 | 0.0004949 | 5444 | 0.058321 | 7246 | 2.8504e-05 | 8153
WOODWARD 2108441553 | WOODWARD 2108 | 255292108 |  | 2.0801 | 0.045496 |  | 44.5 | 0.00042534 | 6172 | 0.067 | 6057 | 2.8498e-05 | 8154
FRANKLIN 1103P144 | FRANKLIN 1103 | 13921103 |  | 1.0281 | 1.1962 |  | 28.5 | 0.00047178 | 5682 | 0.059054 | 7150 | 2.8493e-05 | 8155
BORDEN 110213186 | BORDEN 1102 | 255121102 |  | 0.63468 | 0.081674 |  | 9 | 0.00039706 | 6491 | 0.072076 | 4770 | 2.8488e-05 | 8156
DEEPWATER 1106CB | DEEPWATER 1106 | 63621106 |  | 0.060056 | 0.028031 |  | 3 | 0.00047395 | 5661 | 0.061182 | 6871 | 2.847e-05 | 8157
SAN BENITO 2102CB | SAN BENITO 2102 | 182742102 |  | 0.99305 | 0.020426 |  | 12.4167 | 0.00042488 | 6176 | 0.067 | 6057 | 2.8467e-05 | 8158
LOGAN CREEK 21022554 | LOGAN CREEK 2102 | 103142102 |  | 33.921 | 2.894 |  | 581 | 0.00041185 | 6313 | 0.06967 | 5087 | 2.8452e-05 | 8159
DOLAN ROAD 1101173702 | DOLAN ROAD 1101 | 182381101 |  | 0.12819 | 0.026151 |  | 2 | 0.0004231 | 6191 | 0.067236 | 5776 | 2.8446e-05 | 8160
BELMONT 110345238 | BELMONT 1103 | 24031103 |  | 1.1198 | 1.1098 |  | 19.25 | 0.00053598 | 4997 | 0.053073 | 8251 | 2.8446e-05 | 8161
MONROE 1105590 | MONROE 1105 | 43301105 |  | 1.0458 | 0.4736 |  | 21 | 0.00046168 | 5788 | 0.062699 | 6691 | 2.8442e-05 | 8162
ANITA 1101CB | ANITA 1101 | 102841101 |  | 5.5571 | 0.11162 |  | 86 | 0.00039863 | 6469 | 0.072841 | 4678 | 2.8439e-05 | 8163
FRANKLIN 1102P170 | FRANKLIN 1102 | 13921102 |  | 2.1136 | 2.2201 |  | 34 | 0.00050184 | 5373 | 0.056168 | 7553 | 2.8422e-05 | 8164
EIGHT MILE 21025274 | EIGHT MILE 2102 | 163912102 |  | 20.0647 | 5.1075 |  | 341.1667 | 0.00042502 | 6174 | 0.069956 | 5053 | 2.8414e-05 | 8165
WATSONVILLE 210142086 | WATSONVILLE 2101 | 83332101 |  | 5.7567 | 1.2451 |  | 107 | 0.00043012 | 6117 | 0.066186 | 6236 | 2.841e-05 | 8166
MESA 1104199586 | MESA 1104 | 182821104 |  | 2.5346 | 0.14488 |  | 46 | 0.00041721 | 6252 | 0.068256 | 5346 | 2.8409e-05 | 8167
PANAMA 210138252 | PANAMA 2101 | 253422101 |  | 9.8334 | 3.023 |  | 168 | 0.00040242 | 6420 | 0.073001 | 4662 | 2.8407e-05 | 8168
GIRVAN 110255307 | GIRVAN 1102 | 103401102 |  | 3.3731 | 0.42477 |  | 63 | 0.00042283 | 6196 | 0.067248 | 5765 | 2.8402e-05 | 8169
GIFFEN 1103R3610 | GIFFEN 1103 | 253151103 |  | 2.3301 | 0.088057 |  | 39 | 0.00037622 | 6744 | 0.075529 | 4332 | 2.8394e-05 | 8170
RIO BRAVO 11012638 | RIO BRAVO 1101 | 252861101 |  | 15.0702 | 4.3708 |  | 238.3333 | 0.0004304 | 6114 | 0.068789 | 5225 | 2.837e-05 | 8171
FIREBAUGH 1103CB | FIREBAUGH 1103 | 253471103 |  | 5.0036 | 0.12794 |  | 87.8333 | 0.00037173 | 6815 | 0.076575 | 3991 | 2.8367e-05 | 8172
OAKLAND J 1109CB | OAKLAND J 1109 | 12091109 |  | 0.040601 | 0 |  | 0.58333 | 0.00053428 | 5019 | 0.053073 | 8250 | 2.8356e-05 | 8173
ATWATER 110610450 | ATWATER 1106 | 253611106 |  | 0.92254 | 0.14902 |  | 16 | 0.00053425 | 5020 | 0.053073 | 8251 | 2.8354e-05 | 8174
PEABODY 2105CB | PEABODY 2105 | 63642105 |  | 7.9902 | 0.53817 |  | 138.2833 | 0.00042558 | 6170 | 0.067163 | 5842 | 2.8352e-05 | 8175
OCEAN 0401CB | OCEAN 0401 | 22580401 |  | 0.6671 | 1.123 |  | 15.6667 | 0.00053419 | 5021 | 0.053073 | 8251 | 2.8351e-05 | 8176
OAKLAND J 11067867 | OAKLAND J 1106 | 12091106 |  | 1.3224 | 1.3701 |  | 19 | 0.00053414 | 5022 | 0.053073 | 8251 | 2.8348e-05 | 8177
PAUL SWEET 21073959 | PAUL SWEET 2107 | 83252107 |  | 2.279 | 1.3176 |  | 35.3333 | 0.00050634 | 5325 | 0.056618 | 7489 | 2.8346e-05 | 8178
CLARKSVILLE 21036842 | CLARKSVILLE 2103 | 153612103 |  | 3.9053 | 0.10243 |  | 77 | 0.00042557 | 6171 | 0.066841 | 6110 | 2.8346e-05 | 8179
JANES CREEK 11011184 | JANES CREEK 1101 | 192391101 |  | 9.2642 | 0.95442 |  | 175.5 | 0.00042304 | 6193 | 0.067 | 6057 | 2.8344e-05 | 8180
GUERNSEY 1101176309 | GUERNSEY 1101 | 252661101 |  | 0.0099365 | 0 |  | 0.5 | 0.00036613 | 6900 | 0.0774 | 3397 | 2.8339e-05 | 8181
FREMONT 1109CB | FREMONT 1109 | 14351109 |  | 6.26 | 5.265 |  | 93 | 0.0005304 | 5070 | 0.053334 | 8164 | 2.8321e-05 | 8182
KINGSBURG 11166120 | KINGSBURG 1116 | 252241116 |  | 3.4086 | 3.0522 |  | 65.5 | 0.00048818 | 5511 | 0.061058 | 6886 | 2.8309e-05 | 8183
KEARNEY 111437294 | KEARNEY 1114 | 252701114 |  | 1.118 | 0.17758 |  | 22 | 0.00046173 | 5787 | 0.061919 | 6771 | 2.8304e-05 | 8184
FITCH MOUNTAIN 1113824468 | FITCH MOUNTAIN 1113 | 42751113 |  | 12.2329 | 1.5105 |  | 244 | 0.00041739 | 6248 | 0.067878 | 5448 | 2.8301e-05 | 8185
ORLAND B 1103CB | ORLAND B 1103 | 102701103 |  | 2.7464 | 0.76263 |  | 46 | 0.00041873 | 6237 | 0.068134 | 5374 | 2.8294e-05 | 8186
PRUNEDALE 111022160 | PRUNEDALE 1110 | 182961110 |  | 11.0752 | 3.3968 |  | 206.5 | 0.00041981 | 6228 | 0.067318 | 5717 | 2.8294e-05 | 8187
MC CALL 110738274 | MC CALL 1107 | 254121107 |  | 29.2383 | 5.2696 |  | 534 | 0.00037213 | 6803 | 0.076208 | 4126 | 2.825e-05 | 8188
MERIDIAN 110263950 | MERIDIAN 1102 | 62541102 |  | 3.4462 | 0.39563 |  | 64.3333 | 0.00037487 | 6766 | 0.076651 | 3960 | 2.8249e-05 | 8189
PEACHTON 110346176 | PEACHTON 1103 | 103241103 |  | 11.0116 | 1.4912 |  | 176.8333 | 0.00037097 | 6826 | 0.076626 | 3973 | 2.8242e-05 | 8190
SANGER 1112CB | SANGER 1112 | 252351112 |  | 3.7788 | 0.31571 |  | 50.8333 | 0.00036488 | 6921 | 0.0774 | 3397 | 2.8241e-05 | 8191
HOLLISTER 2102CB | HOLLISTER 2102 | 182492102 |  | 8.7371 | 0.88868 |  | 157.8333 | 0.00041669 | 6259 | 0.067791 | 5478 | 2.8237e-05 | 8192
MORMON 1103CB | MORMON 1103 | 163211103 |  | 8.0771 | 1.4612 |  | 152.1667 | 0.0003867 | 6624 | 0.074024 | 4554 | 2.8221e-05 | 8193
GREEN VALLEY 210210260 | GREEN VALLEY 2102 | 83192102 |  | 19.5669 | 2.0757 |  | 388.5 | 0.00041744 | 6247 | 0.067757 | 5494 | 2.8205e-05 | 8194
SAN LEANDRO U 1110MR275 | SAN LEANDRO U 1110 | 13111110 |  | 6.9341 | 9.239 |  | 111 | 0.00053141 | 5056 | 0.053073 | 8251 | 2.8203e-05 | 8195
MC CALL 1102CB | MC CALL 1102 | 254121102 |  | 14.3491 | 2.9966 |  | 237.95 | 0.00040331 | 6417 | 0.07324 | 4645 | 2.8198e-05 | 8196
SHAFTER 111187796 | SHAFTER 1111 | 253651111 |  | 10.2298 | 1.984 |  | 172.8333 | 0.00038699 | 6619 | 0.074705 | 4458 | 2.8195e-05 | 8197
SWIFT 2109XR386 | SWIFT 2109 | 83392109 |  | 3.4638 | 2.9524 |  | 63 | 0.00045838 | 5825 | 0.061473 | 6837 | 2.8189e-05 | 8198
LODI 110114322 | LODI 1101 | 162111101 |  | 2.7703 | 0.91201 |  | 53 | 0.00041328 | 6300 | 0.070285 | 4983 | 2.8183e-05 | 8199
KINGSBURG 11086820 | KINGSBURG 1108 | 252241108 |  | 25.0916 | 5.7823 |  | 469.5 | 0.00039019 | 6569 | 0.073627 | 4592 | 2.8183e-05 | 8200
JACOBS CORNER 1102CB | JACOBS CORNER 1102 | 254771102 |  | 11.7731 | 0.28853 |  | 184.8333 | 0.00036493 | 6919 | 0.077186 | 3603 | 2.8177e-05 | 8201
FREMONT 1109MR735 | FREMONT 1109 | 14351109 |  | 2.6657 | 1.3078 |  | 54 | 0.00046915 | 5705 | 0.060485 | 6960 | 2.8169e-05 | 8202
STELLING 1106CB | STELLING 1106 | 83481106 |  | 0.002841 | 0 |  | 0.5 | 0.00053071 | 5064 | 0.053073 | 8251 | 2.8166e-05 | 8203
SAN RAFAEL 11051278 | SAN RAFAEL 1105 | 42011105 |  | 0.28819 | 0.12889 |  | 5.5 | 0.00053054 | 5068 | 0.053073 | 8251 | 2.8157e-05 | 8204
CASTRO VALLEY 1102837904 | CASTRO VALLEY 1102 | 14091102 | FALSE | 2.0455 | 2.1869 | 2.1951 | 34.5 | 0.00044137 | 5999 | 0.06155 | 6820 | 2.8142e-05 | 8205
LERDO 1110CB | LERDO 1110 | 253491110 |  | 9.0499 | 0.2169 |  | 161.6667 | 0.0003907 | 6562 | 0.073285 | 4636 | 2.8139e-05 | 8206
WOODCHUCK 2101CB | WOODCHUCK 2101 | 254912101 |  | 0.53289 | 0.033241 |  | 8 | 0.00041173 | 6317 | 0.068342 | 5320 | 2.8138e-05 | 8207
KING CITY 1103139682 | KING CITY 1103 | 182031103 |  | 2.6507 | 0.20207 |  | 48.5 | 0.00043021 | 6116 | 0.065277 | 6394 | 2.8137e-05 | 8208
MC CALL 11015040 | MC CALL 1101 | 254121101 |  | 3.2994 | 0.60546 |  | 60 | 0.00036352 | 6936 | 0.0774 | 3397 | 2.8137e-05 | 8209
WEEDPATCH 1102CB | WEEDPATCH 1102 | 252971102 |  | 12.6192 | 2.0796 |  | 213 | 0.00041748 | 6246 | 0.069908 | 5061 | 2.8127e-05 | 8210
LIVE OAK 1102CB | LIVE OAK 1102 | 153771102 |  | 6.2918 | 1.3731 |  | 108 | 0.00043431 | 6067 | 0.069112 | 5174 | 2.8125e-05 | 8211
MORMON 110210502 | MORMON 1102 | 163211102 |  | 11.9131 | 3.3009 |  | 232 | 0.00037339 | 6788 | 0.075549 | 4327 | 2.812e-05 | 8212
RENFRO 210797560 | RENFRO 2107 | 254572107 |  | 1.4156 | 0.11602 |  | 26 | 0.00038244 | 6670 | 0.075061 | 4407 | 2.8117e-05 | 8213
SAN BERNARD 1101CB | SAN BERNARD 1101 | 253191101 |  | 22.255 | 0.22883 |  | 369.8333 | 0.00039615 | 6499 | 0.071142 | 4877 | 2.8114e-05 | 8214
COTTLE 170149704 | COTTLE 1701 | 163711701 |  | 3.4412 | 0.52638 |  | 58.5 | 0.00038401 | 6652 | 0.074094 | 4541 | 2.809e-05 | 8215
GIFFEN 1106CB | GIFFEN 1106 | 253151106 |  | 2.1614 | 0 |  | 11.75 | 0.00036287 | 6947 | 0.0774 | 3400 | 2.8086e-05 | 8216
ARCATA 1106CB | ARCATA 1106 | 192021106 |  | 6.3397 | 3.6901 |  | 106.5 | 0.00046575 | 5741 | 0.061161 | 6873 | 2.8071e-05 | 8217
CLEAR LAKE 110192870 | CLEAR LAKE 1101 | 42141101 | TRUE | 15.8413 | 4.2121 | 0.055732 | 273 | 0.00042621 | 6158 | 0.066535 | 6180 | 2.8061e-05 | 8218
BERKELEY T 0404CB | BERKELEY T 0404 | 12660404 |  | 1.2065 | 1.3589 |  | 19.9167 | 0.00052494 | 5127 | 0.05343 | 8116 | 2.8059e-05 | 8219
BLUE LAKE 110256630 | BLUE LAKE 1102 | 192181102 |  | 26.0978 | 3.0815 |  | 474.5 | 0.00041825 | 6243 | 0.067063 | 5933 | 2.8049e-05 | 8220
ARCATA 110538786 | ARCATA 1105 | 192021105 |  | 5.1895 | 2.7394 |  | 91 | 0.00042058 | 6221 | 0.066884 | 6099 | 2.8037e-05 | 8221
DIAMOND SPRINGS 110719702 | DIAMOND SPRINGS 1107 | 152261107 |  | 0.11084 | 0 |  | 3.5 | 0.00048508 | 5548 | 0.059042 | 7153 | 2.8034e-05 | 8222
WOODSIDE 1102CB | WOODSIDE 1102 | 24251102 |  | 1.6472 | 1.1087 |  | 47.5 | 0.00042602 | 6162 | 0.065534 | 6351 | 2.8025e-05 | 8223
SAN BENITO 2104CB | SAN BENITO 2104 | 182742104 |  | 2.1077 | 0.021087 |  | 29.4167 | 0.00041481 | 6285 | 0.067552 | 5571 | 2.8021e-05 | 8224
NEWBURG 113397612 | NEWBURG 1133 | 192151133 |  | 7.7292 | 2.1822 |  | 146.3333 | 0.00041719 | 6253 | 0.067153 | 5849 | 2.8016e-05 | 8225
ARCATA 110589784 | ARCATA 1105 | 192021105 |  | 2.4686 | 1.538 |  | 48.5 | 0.0004264 | 6155 | 0.065366 | 6384 | 2.7998e-05 | 8226
CORTINA 110130016 | CORTINA 1101 | 63121101 |  | 0.028564 | 0 |  | 0.5 | 0.00041698 | 6256 | 0.06714 | 5862 | 2.7996e-05 | 8227
DUMBARTON 1102MR100 | DUMBARTON 1102 | 14471102 |  | 3.6266 | 3.8859 |  | 52.5 | 0.00052741 | 5100 | 0.053073 | 8251 | 2.7991e-05 | 8228
CORCORAN 1116CB | CORCORAN 1116 | 252171116 |  | 12.6705 | 3.6716 |  | 234.9167 | 0.00039502 | 6509 | 0.072425 | 4724 | 2.7974e-05 | 8229
LOS COCHES 110256346 | LOS COCHES 1102 | 182151102 |  | 0.022731 | 0 |  | 0.5 | 0.00041737 | 6251 | 0.067 | 6057 | 2.7964e-05 | 8230
LIVINGSTON 110498586 | LIVINGSTON 1104 | 252261104 |  | 2.776 | 1.4703 |  | 43 | 0.00043436 | 6066 | 0.064871 | 6454 | 2.7958e-05 | 8231
PEACHTON 11021964 | PEACHTON 1102 | 103241102 |  | 16.5441 | 0.96738 |  | 285 | 0.00037216 | 6802 | 0.075589 | 4314 | 2.7952e-05 | 8232
PARLIER 11035140 | PARLIER 1103 | 252291103 |  | 1.286 | 0.95467 |  | 22.8333 | 0.00052276 | 5152 | 0.053605 | 8056 | 2.795e-05 | 8233
AIRWAYS 1105CB | AIRWAYS 1105 | 252041105 |  | 1.3519 | 0.17026 |  | 29.3333 | 0.00036938 | 6849 | 0.074912 | 4424 | 2.7938e-05 | 8234
EL CAPITAN 110490330 | EL CAPITAN 1104 | 253881104 |  | 2.1467 | 1.9766 |  | 39 | 0.00046035 | 5803 | 0.061805 | 6787 | 2.7937e-05 | 8235
21ST AVENUE 04024239 | 21ST AVENUE 0402 | 22550402 |  | 1.1638 | 1.7764 |  | 20.5 | 0.00052627 | 5110 | 0.053073 | 8251 | 2.7931e-05 | 8236
HONCUT 1102976552 | HONCUT 1102 | 103211102 |  | 1.3284 | 0.146 |  | 22 | 0.00041658 | 6262 | 0.067037 | 5967 | 2.7928e-05 | 8237
MORMON 110375226 | MORMON 1103 | 163211103 |  | 6.4809 | 2.5989 |  | 106.6667 | 0.00044267 | 5989 | 0.065616 | 6336 | 2.7927e-05 | 8238
RED BLUFF 1104CB | RED BLUFF 1104 | 103541104 |  | 7.9113 | 2.3119 |  | 125.5 | 0.00042529 | 6173 | 0.066099 | 6248 | 2.7919e-05 | 8239
SCHINDLER 111037306 | SCHINDLER 1110 | 252891110 |  | 8.1409 | 0.16303 |  | 131 | 0.00036799 | 6874 | 0.076378 | 4061 | 2.7913e-05 | 8240
SOLEDAD 21057056 | SOLEDAD 2105 | 182052105 |  | 9.0225 | 0.34709 |  | 185.3333 | 0.00041247 | 6309 | 0.067729 | 5499 | 2.7911e-05 | 8241
TEMPLETON 2109868666 | TEMPLETON 2109 | 183052109 |  | 0.11781 | 0 |  | 0.83333 | 0.00041646 | 6263 | 0.067 | 6056 | 2.7903e-05 | 8242
WILKINS SLOUGH 110276620 | WILKINS SLOUGH 1102 | 62771102 |  | 0.026302 | 0 |  | 0.5 | 0.00045238 | 5900 | 0.061675 | 6804 | 2.7901e-05 | 8243
NEWMAN 1106CB | NEWMAN 1106 | 162741106 |  | 5.3827 | 0.40013 |  | 99.1667 | 0.00040187 | 6428 | 0.071818 | 4791 | 2.7896e-05 | 8244
RIVERBANK 171490210 | RIVERBANK 1714 | 163191714 |  | 5.2878 | 2.6018 |  | 87.5 | 0.00049708 | 5423 | 0.059623 | 7067 | 2.789e-05 | 8245
NEWARK 12KV 1106MR642 | NEWARK 12KV 1106 | 12221106 |  | 3.6719 | 3.6789 |  | 55 | 0.00052546 | 5119 | 0.053073 | 8251 | 2.7888e-05 | 8246
MT EDEN 1114CB | MT EDEN 1114 | 13761114 |  | 3.5747 | 0.53639 |  | 57.2333 | 0.00049384 | 5459 | 0.057844 | 7317 | 2.7882e-05 | 8247
FREMONT 1110MR131 | FREMONT 1110 | 14351110 |  | 5.3068 | 6.3855 |  | 88.5 | 0.00052532 | 5120 | 0.053073 | 8251 | 2.788e-05 | 8248
MORMON 110158084 | MORMON 1101 | 163211101 |  | 0.24975 | 0 |  | 4.5 | 0.00036002 | 6981 | 0.0774 | 3397 | 2.7865e-05 | 8249
GOOSE LAKE 1101CB | GOOSE LAKE 1101 | 254201101 |  | 0.54411 | 0 |  | 7.1667 | 0.0003599 | 6985 | 0.0774 | 3397 | 2.7856e-05 | 8250
LONE TREE 210268100 | LONE TREE 2102 | 13232102 |  | 9.1884 | 4.3119 |  | 159.5 | 0.00042261 | 6199 | 0.067022 | 6000 | 2.7844e-05 | 8251
VASCO 1103CB | VASCO 1103 | 13751103 |  | 6.815 | 0.68596 |  | 124 | 0.00041514 | 6281 | 0.06767 | 5517 | 2.7843e-05 | 8252
SAN BRUNO 0403CB | SAN BRUNO 0403 | 22700403 |  | 2.9162 | 2.971 |  | 36.9167 | 0.00051761 | 5199 | 0.053701 | 8028 | 2.7835e-05 | 8253
PAUL SWEET 2101955754 | PAUL SWEET 2101 | 83252101 |  | 2.8824 | 2.3023 |  | 34.3333 | 0.00047985 | 5604 | 0.05754 | 7352 | 2.7834e-05 | 8254
LAKEVIEW 1103CB | LAKEVIEW 1103 | 253411103 |  | 5.6361 | 0 |  | 102.3333 | 0.00038589 | 6631 | 0.071597 | 4814 | 2.783e-05 | 8255
ZAMORA 1107CB | ZAMORA 1107 | 63191107 |  | 7.8518 | 0.22881 |  | 138.3333 | 0.00040569 | 6385 | 0.068993 | 5191 | 2.783e-05 | 8256
MENDOTA 110212230 | MENDOTA 1102 | 252311102 |  | 2.2983 | 1.4917 |  | 41.5 | 0.0005242 | 5136 | 0.053073 | 8251 | 2.7821e-05 | 8257
MIRA VISTA 0401CB | MIRA VISTA 0401 | 12330401 |  | 8.7115 | 11.2594 |  | 125.2 | 0.00052416 | 5138 | 0.053073 | 8251 | 2.7819e-05 | 8258
SANTA MARIA 1110353438 | SANTA MARIA 1110 | 182671110 |  | 0.013782 | 0 |  | 0.5 | 0.00052399 | 5141 | 0.053073 | 8251 | 2.7809e-05 | 8259
LEMOORE 110288290 | LEMOORE 1102 | 253601102 |  | 2.0715 | 0.88191 |  | 33.5 | 0.00046138 | 5792 | 0.060954 | 6894 | 2.7789e-05 | 8260
RAINBOW 1106R430 | RAINBOW 1106 | 254441106 |  | 6.6952 | 2.5477 |  | 139 | 0.00039353 | 6526 | 0.073112 | 4653 | 2.7785e-05 | 8261
REEDLEY 110198400 | REEDLEY 1101 | 252341101 |  | 6.4346 | 2.6424 |  | 100.75 | 0.00043492 | 6061 | 0.067766 | 5486 | 2.7777e-05 | 8262
LE GRAND 111212000 | LE GRAND 1112 | 255361112 |  | 1.8542 | 0.12482 |  | 35 | 0.0003678 | 6875 | 0.07601 | 4197 | 2.7775e-05 | 8263
PANAMA 21024810 | PANAMA 2102 | 253422102 |  | 17.1222 | 3.128 |  | 277.1667 | 0.00038855 | 6597 | 0.073488 | 4613 | 2.7772e-05 | 8264
CAL WATER 1103429550 | CAL WATER 1103 | 255451103 |  | 3.0859 | 0.044228 |  | 57 | 0.00042149 | 6210 | 0.066006 | 6274 | 2.7771e-05 | 8265
RENFRO 210754958 | RENFRO 2107 | 254572107 |  | 0.72061 | 0.015425 |  | 12.5 | 0.00039544 | 6505 | 0.072249 | 4752 | 2.7762e-05 | 8266
LATHROP 0402CB | LATHROP 0402 | 163030402 |  | 0.019792 | 0 |  | 2 | 0.00052263 | 5154 | 0.053073 | 8251 | 2.7737e-05 | 8267
MANTECA 170555786 | MANTECA 1705 | 162611705 |  | 11.3318 | 1.5797 |  | 202 | 0.00040487 | 6401 | 0.07094 | 4902 | 2.7725e-05 | 8268
BORONDA 1101CB | BORONDA 1101 | 182461101 |  | 4.236 | 3.0075 |  | 88.5 | 0.00044695 | 5942 | 0.062513 | 6714 | 2.7721e-05 | 8269
DUNNIGAN 1101CB | DUNNIGAN 1101 | 63811101 |  | 2.7506 | 0.15651 |  | 40.5 | 0.000368 | 6873 | 0.075823 | 4257 | 2.7718e-05 | 8270
CHARCA 1103CB | CHARCA 1103 | 254501103 |  | 9.1374 | 0.22913 |  | 156 | 0.00036069 | 6972 | 0.076932 | 3807 | 2.7714e-05 | 8271
AIRWAYS 1102R2664 | AIRWAYS 1102 | 252041102 |  | 4.2809 | 0.46488 |  | 76.5 | 0.0003672 | 6882 | 0.076287 | 4098 | 2.7712e-05 | 8272
DUNNIGAN 1101589936 | DUNNIGAN 1101 | 63811101 |  | 0.36904 | 0 |  | 7.5 | 0.00041356 | 6297 | 0.067 | 6057 | 2.7708e-05 | 8273
LAMONT 11052840 | LAMONT 1105 | 253911105 |  | 13.2444 | 1.5275 |  | 223.5 | 0.00038021 | 6693 | 0.073272 | 4639 | 2.7708e-05 | 8274
SANTA RITA 110569574 | SANTA RITA 1105 | 253541105 |  | 0.030628 | 0 |  | 0.5 | 0.00035793 | 7006 | 0.0774 | 3397 | 2.7704e-05 | 8275
WILSON 110347636 | WILSON 1103 | 254301103 |  | 0.022729 | 0 |  | 0.5 | 0.00035792 | 7007 | 0.0774 | 3397 | 2.7703e-05 | 8276
VIERRA 17078988 | VIERRA 1707 | 162701707 |  | 5.3561 | 0.93529 |  | 96 | 0.00037396 | 6779 | 0.074739 | 4452 | 2.7698e-05 | 8277
CARQUINEZ 11032357 | CARQUINEZ 1103 | 43281103 |  | 0.52934 | 0.56189 |  | 9.5 | 0.00052177 | 5158 | 0.053073 | 8251 | 2.7692e-05 | 8278
CORCORAN 111288132 | CORCORAN 1112 | 252171112 |  | 4.0178 | 2.3387 |  | 71.3333 | 0.00048031 | 5601 | 0.059041 | 7154 | 2.7686e-05 | 8279
PRUNEDALE 111022104 | PRUNEDALE 1110 | 182961110 |  | 21.4751 | 6.4443 |  | 389.5 | 0.00041308 | 6302 | 0.067044 | 5953 | 2.7683e-05 | 8280
HARTLEY 110167994 | HARTLEY 1101 | 43211101 |  | 1.9969 | 1.8922 |  | 29.8333 | 0.00049816 | 5411 | 0.055647 | 7650 | 2.7679e-05 | 8281
LLAGAS 2102XR492 | LLAGAS 2102 | 83182102 |  | 5.8585 | 5.6128 |  | 96 | 0.00050298 | 5357 | 0.054758 | 7794 | 2.7675e-05 | 8282
MALAGA 1108R9217 | MALAGA 1108 | 254251108 |  | 12.9951 | 4.5013 |  | 246 | 0.0003747 | 6770 | 0.074637 | 4467 | 2.7673e-05 | 8283
DOS PALOS 1101CB | DOS PALOS 1101 | 254041101 |  | 7.2205 | 3.262 |  | 122 | 0.00042773 | 6143 | 0.067172 | 5832 | 2.7667e-05 | 8284
ARVIN 110169618 | ARVIN 1101 | 253801101 |  | 2.0742 | 0.0084383 |  | 36 | 0.00040431 | 6406 | 0.068567 | 5269 | 2.7665e-05 | 8285
MILLBRAE 1104217 | MILLBRAE 1104 | 22691104 |  | 0.017853 | 0 |  | 0.5 | 0.00052111 | 5166 | 0.053073 | 8251 | 2.7657e-05 | 8286
CRESSEY 210337010 | CRESSEY 2103 | 254702103 |  | 4.3687 | 0.19095 |  | 81.5 | 0.00036437 | 6924 | 0.076408 | 4051 | 2.7654e-05 | 8287
DIXON 1103CB | DIXON 1103 | 62061103 |  | 16.3404 | 4.9452 |  | 270 | 0.00040642 | 6378 | 0.071856 | 4785 | 2.7652e-05 | 8288
MALAGA 1102R9215 | MALAGA 1102 | 254251102 |  | 8.3687 | 1.8282 |  | 171 | 0.00038519 | 6638 | 0.072091 | 4769 | 2.7647e-05 | 8289
BAHIA 1102350336 | BAHIA 1102 | 43251102 |  | 1.1989 | 0.099152 |  | 20 | 0.00040556 | 6387 | 0.068128 | 5377 | 2.7644e-05 | 8290
KNIGHTS LANDING 1102CB | KNIGHTS LANDING 1102 | 62721102 |  | 18.9074 | 2.2537 |  | 355 | 0.00038106 | 6685 | 0.07398 | 4556 | 2.7643e-05 | 8291
CATLETT 1105231738 | CATLETT 1105 | 153761105 |  | 0.020823 | 0 |  | 0.5 | 0.0003569 | 7026 | 0.0774 | 3397 | 2.7624e-05 | 8292
LAS GALLINAS A 1104304 | LAS GALLINAS A 1104 | 42991104 | TRUE | 2.5221 | 2.5669 | 0.19392 | 41.5 | 0.00044922 | 5926 | 0.05709 | 7426 | 2.7623e-05 | 8293
PUEBLO 21021326 | PUEBLO 2102 | 43292102 |  | 7.4655 | 0.33543 |  | 143 | 0.0004054 | 6391 | 0.068544 | 5277 | 2.7621e-05 | 8294
RIPON 1704CB | RIPON 1704 | 163801704 |  | 7.0309 | 0.40503 |  | 130.5 | 0.00039212 | 6540 | 0.072664 | 4700 | 2.7617e-05 | 8295
GRAND ISLAND 222756352 | GRAND ISLAND 2227 | 62462227 |  | 12.9755 | 0.62533 |  | 183.75 | 0.00035889 | 6998 | 0.076922 | 3815 | 2.7609e-05 | 8296
LE GRAND 1106CB | LE GRAND 1106 | 255361106 |  | 14.8091 | 0.81682 |  | 233.8333 | 0.00035745 | 7015 | 0.077161 | 3635 | 2.76e-05 | 8297
GOOSE LAKE 2104654010 | GOOSE LAKE 2104 | 254202104 |  | 0.24351 | 0 |  | 5.5 | 0.00041184 | 6314 | 0.067 | 6057 | 2.7593e-05 | 8298
SONOMA 1105138 | SONOMA 1105 | 42721105 | TRUE | 16.6322 | 2.4376 | 0.037946 | 296.5 | 0.00040898 | 6345 | 0.067447 | 5639 | 2.7585e-05 | 8299
SANGER 111867888 | SANGER 1118 | 252351118 |  | 4.0086 | 0.45793 |  | 68.5 | 0.00040422 | 6407 | 0.069827 | 5068 | 2.7565e-05 | 8300
RIVERBANK 171549752 | RIVERBANK 1715 | 163191715 |  | 0.026648 | 0 |  | 1 | 0.00035608 | 7044 | 0.0774 | 3397 | 2.756e-05 | 8301
DUMBARTON 2111MR105 | DUMBARTON 2111 | 14472111 |  | 2.4439 | 1.3551 |  | 44.5 | 0.00037485 | 6767 | 0.07396 | 4560 | 2.7554e-05 | 8302
FRENCH CAMP 11022132 | FRENCH CAMP 1102 | 163291102 |  | 4.2232 | 0.26587 |  | 68.5 | 0.00035759 | 7014 | 0.077045 | 3736 | 2.7554e-05 | 8303
PARLIER 1105CB | PARLIER 1105 | 252291105 |  | 3.1176 | 0.25181 |  | 47.9167 | 0.00036885 | 6861 | 0.076522 | 4007 | 2.7554e-05 | 8304
ORO LOMA 1115612248 | ORO LOMA 1115 | 255371115 |  | 3.3415 | 1.2681 |  | 63.5 | 0.00037706 | 6734 | 0.073569 | 4599 | 2.7544e-05 | 8305
PASO ROBLES 1107164828 | PASO ROBLES 1107 | 182611107 |  | 0.056459 | 0 |  | 2.5 | 0.0004051 | 6397 | 0.067965 | 5410 | 2.7533e-05 | 8306
RIVERBANK 171290140 | RIVERBANK 1712 | 163191712 |  | 12.6108 | 1.1049 |  | 216 | 0.00035659 | 7035 | 0.077214 | 3580 | 2.7521e-05 | 8307
CHOWCHILLA 11036180 | CHOWCHILLA 1103 | 254101103 |  | 6.8444 | 0.16015 |  | 116 | 0.00035618 | 7040 | 0.077295 | 3482 | 2.7518e-05 | 8308
TRES VIAS 11015667 | TRES VIAS 1101 | 103251101 |  | 1.6173 | 0.55639 |  | 25 | 0.00040925 | 6341 | 0.067416 | 5655 | 2.7507e-05 | 8309
PEACHTON 1102CB | PEACHTON 1102 | 103241102 |  | 12.0832 | 0.92613 |  | 201.1667 | 0.00037001 | 6839 | 0.075519 | 4334 | 2.7504e-05 | 8310
LOGAN CREEK 210114532 | LOGAN CREEK 2101 | 103142101 |  | 9.0841 | 0.34542 |  | 146.45 | 0.00036805 | 6871 | 0.075723 | 4284 | 2.7502e-05 | 8311
EDENVALE 2105XR336 | EDENVALE 2105 | 82952105 |  | 21.1093 | 2.7268 |  | 419 | 0.00041278 | 6304 | 0.06732 | 5715 | 2.7496e-05 | 8312
CORNING 110237400 | CORNING 1102 | 103331102 |  | 7.5397 | 0.79562 |  | 122.3333 | 0.00041009 | 6333 | 0.066979 | 6069 | 2.7465e-05 | 8313
LERDO 1110CUS3530 | LERDO 1110 | 253491110 |  | 0.01866 | 0 |  | 0.5 | 0.00035477 | 7058 | 0.0774 | 3397 | 2.7459e-05 | 8314
ORTIGA 11069780 | ORTIGA 1106 | 254311106 |  | 10.277 | 1.1441 |  | 180.5 | 0.00036377 | 6933 | 0.076088 | 4168 | 2.7455e-05 | 8315
WEEDPATCH 1105CB | WEEDPATCH 1105 | 252971105 |  | 0.86643 | 0.011814 |  | 13.75 | 0.00035466 | 7060 | 0.0774 | 3397 | 2.745e-05 | 8316
RIVERBANK 17138160 | RIVERBANK 1713 | 163191713 |  | 8.9605 | 0.70437 |  | 151.5 | 0.00036346 | 6938 | 0.076016 | 4194 | 2.7446e-05 | 8317
VACA DIXON 1104607900 | VACA DIXON 1104 | 63591104 |  | 4.6229 | 2.7235 |  | 76 | 0.00050435 | 5345 | 0.054757 | 7795 | 2.7434e-05 | 8318
TULARE LAKE 1108CB | TULARE LAKE 1108 | 252951108 |  | 1.5482 | 0 |  | 28.3333 | 0.00038549 | 6637 | 0.072873 | 4675 | 2.7428e-05 | 8319
MAGUNDEN 21084227 | MAGUNDEN 2108 | 252772108 |  | 14.678 | 2.4268 |  | 246.8333 | 0.00038162 | 6679 | 0.074825 | 4439 | 2.742e-05 | 8320
MONROE 110693710 | MONROE 1106 | 43301106 |  | 6.0522 | 1.4653 |  | 115.3333 | 0.00043206 | 6090 | 0.064254 | 6512 | 2.7419e-05 | 8321
WATSONVILLE 21015470 | WATSONVILLE 2101 | 83332101 |  | 35.0194 | 8.2416 |  | 649.5 | 0.00041005 | 6334 | 0.066829 | 6115 | 2.7419e-05 | 8322
JARVIS 1105MR474 | JARVIS 1105 | 13501105 |  | 5.3644 | 4.1183 |  | 93.5 | 0.00051659 | 5210 | 0.053073 | 8251 | 2.7417e-05 | 8323
LAMONT 11071913 | LAMONT 1107 | 253911107 |  | 7.4887 | 1.7324 |  | 130 | 0.00037847 | 6718 | 0.07423 | 4521 | 2.7412e-05 | 8324
GATES 1105CB | GATES 1105 | 253931105 |  | 8.4281 | 0.059209 |  | 119.5833 | 0.00036036 | 6976 | 0.076264 | 4104 | 2.7404e-05 | 8325
PUEBLO 110475462 | PUEBLO 1104 | 43291104 |  | 9.1549 | 1.5269 |  | 170.3333 | 0.00040834 | 6354 | 0.067055 | 5941 | 2.7382e-05 | 8326
HARTLEY 1101471 | HARTLEY 1101 | 43211101 |  | 1.2439 | 0.81693 |  | 18.3333 | 0.00045759 | 5839 | 0.059196 | 7130 | 2.7378e-05 | 8327
WATSONVILLE 210110788 | WATSONVILLE 2101 | 83332101 |  | 10.503 | 1.7049 |  | 188 | 0.00040673 | 6375 | 0.067491 | 5609 | 2.737e-05 | 8328
WOODWARD 2107CB | WOODWARD 2107 | 255292107 |  | 7.3871 | 0.49234 |  | 129.3333 | 0.00040706 | 6368 | 0.067493 | 5606 | 2.7359e-05 | 8329
MORGAN HILL 2108XR328 | MORGAN HILL 2108 | 83242108 |  | 7.5946 | 1.0798 |  | 161 | 0.00041035 | 6331 | 0.067695 | 5510 | 2.7337e-05 | 8330
RENFRO 21024923 | RENFRO 2102 | 254572102 |  | 1.5157 | 0.67176 |  | 40.3333 | 0.00045826 | 5833 | 0.060914 | 6898 | 2.7336e-05 | 8331
MADERA 110611730 | MADERA 1106 | 252761106 |  | 2.0458 | 0.8662 |  | 37.5 | 0.00042885 | 6133 | 0.065398 | 6379 | 2.7331e-05 | 8332
LOS OSITOS 21027470 | LOS OSITOS 2102 | 182082102 |  | 18.2667 | 1.1768 |  | 374.5 | 0.00040613 | 6381 | 0.06731 | 5724 | 2.7329e-05 | 8333
GUERNSEY 1106CB | GUERNSEY 1106 | 252661106 |  | 3.2209 | 0.3373 |  | 56.5333 | 0.00035308 | 7089 | 0.0774 | 3397 | 2.7328e-05 | 8334
AIRWAYS 1101CB | AIRWAYS 1101 | 252041101 |  | 1.4757 | 0.057019 |  | 36.5 | 0.00038979 | 6574 | 0.072637 | 4705 | 2.7305e-05 | 8335
KEARNEY 1114CB | KEARNEY 1114 | 252701114 |  | 8.4716 | 1.853 |  | 132.3333 | 0.00035315 | 7088 | 0.07736 | 3404 | 2.73e-05 | 8336
LOS OSITOS 2102780218 | LOS OSITOS 2102 | 182082102 |  | 0.025813 | 0 |  | 1.5 | 0.0004074 | 6366 | 0.067 | 6057 | 2.7296e-05 | 8337
SANTA NELLA 1104CB | SANTA NELLA 1104 | 254051104 |  | 8.9491 | 1.3177 |  | 143.5 | 0.00040847 | 6351 | 0.066872 | 6103 | 2.7295e-05 | 8338
OCEAN 0402CB | OCEAN 0402 | 22580402 |  | 2.9565 | 4.1122 |  | 66.1667 | 0.00051385 | 5246 | 0.053073 | 8250 | 2.7272e-05 | 8339
DAVIS 110739406 | DAVIS 1107 | 62041107 |  | 0.70686 | 0 |  | 5.5 | 0.00035211 | 7105 | 0.0774 | 3396 | 2.7254e-05 | 8340
MERIDIAN 11024302 | MERIDIAN 1102 | 62541102 |  | 4.1001 | 0.11984 |  | 81 | 0.00036385 | 6931 | 0.075554 | 4326 | 2.7251e-05 | 8341
TEJON 1106CB | TEJON 1106 | 252931106 |  | 5.7221 | 0.03939 |  | 84.5833 | 0.00038127 | 6682 | 0.071524 | 4828 | 2.725e-05 | 8342
SAN PABLO 1105CB | SAN PABLO 1105 | 14371105 |  | 3.1879 | 3.6677 |  | 57 | 0.00050994 | 5285 | 0.05353 | 8091 | 2.7249e-05 | 8343
NOVATO 110449280 | NOVATO 1104 | 42211104 |  | 1.6906 | 0.46012 |  | 32.5 | 0.00042048 | 6224 | 0.065414 | 6376 | 2.7248e-05 | 8344
MALAGA 1103R1110 | MALAGA 1103 | 254251103 |  | 8.8328 | 1.4562 |  | 153.5 | 0.00037559 | 6753 | 0.073485 | 4614 | 2.7237e-05 | 8345
CRESSEY 21049440 | CRESSEY 2104 | 254702104 |  | 9.2381 | 0.30682 |  | 155 | 0.00035641 | 7038 | 0.076772 | 3897 | 2.7235e-05 | 8346
FORT BRAGG A 110233064 | FORT BRAGG A 1102 | 42761102 | TRUE | 3.6933 | 0.82921 | 0.032212 | 66 | 0.00040395 | 6413 | 0.067473 | 5619 | 2.7233e-05 | 8347
KINGSBURG 1112CB | KINGSBURG 1112 | 252241112 |  | 12.2036 | 4.5641 |  | 200.8333 | 0.00043903 | 6021 | 0.06489 | 6452 | 2.723e-05 | 8348
MORMON 1101CB | MORMON 1101 | 163211101 |  | 9.0897 | 1.0284 |  | 173.6667 | 0.00035787 | 7008 | 0.076453 | 4033 | 2.7224e-05 | 8349
COLUMBUS 1105CB | COLUMBUS 1105 | 253951105 |  | 4.6086 | 0.062005 |  | 80.8333 | 0.00044048 | 6009 | 0.064789 | 6465 | 2.7221e-05 | 8350
KERMAN 1101R1630 | KERMAN 1101 | 252711101 |  | 8.4684 | 1.1238 |  | 145.5 | 0.00035261 | 7096 | 0.077233 | 3549 | 2.721e-05 | 8351
RIPON 17024077 | RIPON 1702 | 163801702 |  | 0.68204 | 0.66197 |  | 14.5 | 0.00051269 | 5259 | 0.053073 | 8251 | 2.721e-05 | 8352
GRAND ISLAND 22276532 | GRAND ISLAND 2227 | 62462227 |  | 13.5043 | 0.78637 |  | 246 | 0.00035151 | 7116 | 0.0774 | 3397 | 2.7207e-05 | 8353
FREMONT 11099929 | FREMONT 1109 | 14351109 |  | 0.74712 | 0.61766 |  | 11 | 0.00051258 | 5260 | 0.053073 | 8251 | 2.7204e-05 | 8354
BOSWELL 1101CB | BOSWELL 1101 | 254941101 |  | 0.01188 | 0 |  | 1 | 0.0003514 | 7118 | 0.0774 | 3397 | 2.7198e-05 | 8355
LAMONT 110715043 | LAMONT 1107 | 253911107 |  | 0.86142 | 0.18838 |  | 15 | 0.00037507 | 6762 | 0.07473 | 4454 | 2.7172e-05 | 8356
COALINGA NO 2 1105CB | COALINGA NO 2 1105 | 252381105 |  | 3.3934 | 0.063495 |  | 55.5 | 0.00040416 | 6409 | 0.067205 | 5803 | 2.7166e-05 | 8357
MENDOTA 110389538 | MENDOTA 1103 | 252311103 |  | 0.020207 | 0 |  | 0.5 | 0.00051187 | 5265 | 0.053073 | 8251 | 2.7166e-05 | 8358
POINT PINOLE 1101BR318 | POINT PINOLE 1101 | 14261101 |  | 10.5562 | 11.5678 |  | 174.5 | 0.00050464 | 5338 | 0.054302 | 7889 | 2.7151e-05 | 8359
CAYUCOS 1102W16 | CAYUCOS 1102 | 182551102 |  | 6.75 | 6.7251 |  | 107 | 0.00046464 | 5754 | 0.059165 | 7137 | 2.7149e-05 | 8360
INDUSTRIAL ACRES 0412CB | INDUSTRIAL ACRES 0412 | 182300412 |  | 7.2222 | 6.7531 |  | 109.4167 | 0.00050574 | 5332 | 0.054122 | 7923 | 2.7145e-05 | 8361
GOLDTREE 1107477878 | GOLDTREE 1107 | 182581107 |  | 0.020783 | 0 |  | 0.5 | 0.00040276 | 6419 | 0.067385 | 5679 | 2.714e-05 | 8362
GEYSERVILLE 110249056 | GEYSERVILLE 1102 | 42891102 |  | 0.071914 | 0 |  | 1.5 | 0.00040492 | 6400 | 0.067012 | 6021 | 2.7133e-05 | 8363
FELLOWS 21041052 | FELLOWS 2104 | 254242104 |  | 34.0803 | 2.3945 |  | 633.25 | 0.00040229 | 6421 | 0.067363 | 5693 | 2.7125e-05 | 8364
PLUMAS 210750806 | PLUMAS 2107 | 153732107 |  | 1.246 | 0.037501 |  | 26 | 0.00035862 | 6999 | 0.07619 | 4133 | 2.71e-05 | 8365
SANTA MARIA 1109M24 | SANTA MARIA 1109 | 182671109 |  | 4.5871 | 0 |  | 80.5 | 0.00040182 | 6429 | 0.06763 | 5536 | 2.708e-05 | 8366
WEEDPATCH 1106CB | WEEDPATCH 1106 | 252971106 |  | 18.512 | 3.0455 |  | 317.25 | 0.00036752 | 6880 | 0.074403 | 4500 | 2.7075e-05 | 8367
LAMONT 1105CB | LAMONT 1105 | 253911105 |  | 11.3601 | 0.37556 |  | 178.5 | 0.00035442 | 7068 | 0.076132 | 4150 | 2.7074e-05 | 8368
MOLINO 1103314 | MOLINO 1103 | 42571103 |  | 22.2201 | 4.4319 |  | 379 | 0.0004051 | 6396 | 0.066869 | 6105 | 2.7073e-05 | 8369
IGNACIO 11021350 | IGNACIO 1102 | 42481102 |  | 0.013327 | 0 |  | 0.5 | 0.00050984 | 5286 | 0.053073 | 8251 | 2.7059e-05 | 8370
WYANDOTTE 1107609792 | WYANDOTTE 1107 | 102911107 |  | 0.061562 | 0.015903 |  | 1 | 0.00040369 | 6416 | 0.067 | 6057 | 2.7047e-05 | 8371
MANTECA 170323670 | MANTECA 1703 | 162611703 |  | 9.9799 | 0.96346 |  | 178 | 0.00037687 | 6736 | 0.074666 | 4463 | 2.7038e-05 | 8372
SANGER 111044510 | SANGER 1110 | 252351110 |  | 20.3264 | 4.6253 |  | 358 | 0.00037068 | 6831 | 0.074708 | 4457 | 2.7036e-05 | 8373
CLEAR LAKE 1101740076 | CLEAR LAKE 1101 | 42141101 | TRUE | 8.7922 | 0.88124 | 0.18778 | 155.5 | 0.00030079 | 7999 | 0.090767 | 3340 | 2.7033e-05 | 8374
HALF MOON BAY 110260703 | HALF MOON BAY 1102 | 24101102 |  | 2.1006 | 0.84299 |  | 34.5 | 0.00042394 | 6185 | 0.064449 | 6491 | 2.7029e-05 | 8375
HOLLISTER 21064260 | HOLLISTER 2106 | 182492106 |  | 4.7837 | 2.2933 |  | 76.8333 | 0.00046889 | 5707 | 0.058726 | 7194 | 2.7028e-05 | 8376
JANES CREEK 11037588 | JANES CREEK 1103 | 192391103 |  | 9.6229 | 2.6651 |  | 165.5 | 0.00041087 | 6326 | 0.06541 | 6377 | 2.7019e-05 | 8377
PENRYN 1106980728 | PENRYN 1106 | 152561106 |  | 1.6543 | 0.081722 |  | 29.5 | 0.00041312 | 6301 | 0.066076 | 6253 | 2.7001e-05 | 8378
CAMDEN 110237596 | CAMDEN 1102 | 252301102 |  | 3.4944 | 2.7773 |  | 63 | 0.00043152 | 6103 | 0.064669 | 6477 | 2.6976e-05 | 8379
DIXON 110449598 | DIXON 1104 | 62061104 |  | 6.8443 | 0.36455 |  | 123 | 0.00037196 | 6808 | 0.072956 | 4668 | 2.6958e-05 | 8380
DOLAN ROAD 110122158 | DOLAN ROAD 1101 | 182381101 | TRUE | 9.0055 | 2.2964 | 0.023177 | 167 | 0.00035617 | 7041 | 0.084444 | 3373 | 2.6954e-05 | 8381
RIVERBANK 171290100 | RIVERBANK 1712 | 163191712 |  | 5.5649 | 0.80183 |  | 100.5 | 0.00036657 | 6891 | 0.074951 | 4421 | 2.6936e-05 | 8382
BORONDA 110136966 | BORONDA 1101 | 182461101 |  | 0.56427 | 0.1664 |  | 13.5 | 0.00040193 | 6427 | 0.067 | 6057 | 2.693e-05 | 8383
SF J 0404CB | SF J 0404 | 22220404 |  | 0.52042 | 0.84012 |  | 14.8333 | 0.00050731 | 5312 | 0.053073 | 8251 | 2.6924e-05 | 8384
HIGHWAY 1101CB | HIGHWAY 1101 | 42651101 |  | 2.1061 | 0.15112 |  | 41.3333 | 0.00046298 | 5772 | 0.06222 | 6743 | 2.6924e-05 | 8385
BRENTWOOD 211266654 | BRENTWOOD 2112 | 14592112 |  | 12.7362 | 1.4742 |  | 194 | 0.0003627 | 6950 | 0.075243 | 4378 | 2.6923e-05 | 8386
REEDLEY 1101CB | REEDLEY 1101 | 252341101 |  | 14.0858 | 3.179 |  | 221.75 | 0.00036596 | 6903 | 0.075008 | 4413 | 2.6903e-05 | 8387
PAUL SWEET 210438286 | PAUL SWEET 2104 | 83252104 |  | 5.5091 | 3.3077 |  | 72.8333 | 0.00050587 | 5329 | 0.053136 | 8237 | 2.6892e-05 | 8388
MOLINO 11014900 | MOLINO 1101 | 42571101 |  | 12.7467 | 2.9345 |  | 221.5 | 0.0004121 | 6312 | 0.06611 | 6245 | 2.6886e-05 | 8389
TRES VIAS 110194094 | TRES VIAS 1101 | 103251101 |  | 4.971 | 0.22523 |  | 84 | 0.00035912 | 6994 | 0.07533 | 4359 | 2.688e-05 | 8390
OAKLAND X 1101CB | OAKLAND X 1101 | 12541101 |  | 2.8 | 3.4112 |  | 59.3333 | 0.00048376 | 5559 | 0.055617 | 7655 | 2.6876e-05 | 8391
PASO ROBLES 110257672 | PASO ROBLES 1102 | 182611102 |  | 1.4446 | 1.1534 |  | 24.1667 | 0.00050633 | 5326 | 0.053073 | 8250 | 2.6872e-05 | 8392
CHOWCHILLA 1104CB | CHOWCHILLA 1104 | 254101104 |  | 10.0539 | 0.71565 |  | 174.0833 | 0.00035777 | 7011 | 0.075826 | 4255 | 2.6871e-05 | 8393
OROVILLE 11011062 | OROVILLE 1101 | 102521101 |  | 9.1813 | 3.9538 |  | 147 | 0.00041103 | 6324 | 0.066256 | 6220 | 2.6866e-05 | 8394
CLEAR LAKE 1101486 | CLEAR LAKE 1101 | 42141101 |  | 4.0838 | 1.0921 |  | 77.5 | 0.00040097 | 6441 | 0.067 | 6053 | 2.6865e-05 | 8395
CLOVERDALE 110294476 | CLOVERDALE 1102 | 42821102 |  | 1.5851 | 0.17554 |  | 32 | 0.00039895 | 6464 | 0.067411 | 5659 | 2.6863e-05 | 8396
PANAMA 21011393 | PANAMA 2101 | 253422101 |  | 10.2849 | 0.61868 |  | 178 | 0.00035684 | 7028 | 0.075358 | 4353 | 2.6857e-05 | 8397
LOS COCHES 110255146 | LOS COCHES 1102 | 182151102 |  | 0.46961 | 0.01327 |  | 9 | 0.00040084 | 6443 | 0.067 | 6057 | 2.6856e-05 | 8398
RALSTON 1101420730 | RALSTON 1101 | 24141101 | FALSE | 1.6491 | 1.3108 | 0.84306 | 31.5 | 0.00041537 | 6275 | 0.064424 | 6494 | 2.6856e-05 | 8399
LAS GALLINAS A 1106206332 | LAS GALLINAS A 1106 | 42991106 | TRUE | 0.60916 | 0.83559 | 0.28319 | 14.5 | 0.00043724 | 6040 | 0.059925 | 7030 | 2.6845e-05 | 8400
BRENTWOOD 211234690 | BRENTWOOD 2112 | 14592112 |  | 12.2823 | 4.4529 |  | 206.3333 | 0.00036997 | 6841 | 0.073649 | 4587 | 2.6845e-05 | 8401
RIVERBANK 1715CB | RIVERBANK 1715 | 163191715 |  | 18.0628 | 1.7832 |  | 309.5 | 0.00034956 | 7146 | 0.076944 | 3799 | 2.6842e-05 | 8402
SAN BENITO 21024918 | SAN BENITO 2102 | 182742102 |  | 9.0417 | 0.89241 |  | 146.0833 | 0.00039081 | 6559 | 0.0689 | 5207 | 2.6836e-05 | 8403
CASTROVILLE 21043718 | CASTROVILLE 2104 | 182352104 |  | 13.9643 | 0.39932 |  | 227.6667 | 0.00039624 | 6498 | 0.067651 | 5525 | 2.6834e-05 | 8404
SF K 0403CB | SF K 0403 | 22130403 |  | 2.4894 | 1.7892 |  | 35.6667 | 0.00049267 | 5467 | 0.054869 | 7777 | 2.6833e-05 | 8405
ARBUCKLE 1104CB | ARBUCKLE 1104 | 62081104 |  | 13.1754 | 1.6536 |  | 231.75 | 0.00039419 | 6519 | 0.070712 | 4932 | 2.6826e-05 | 8406
FAIRWAY 110748506 | FAIRWAY 1107 | 182061107 |  | 2.2534 | 0.086454 |  | 35.5 | 0.00039446 | 6515 | 0.067879 | 5447 | 2.682e-05 | 8407
COLUSA 11013012 | COLUSA 1101 | 62021101 |  | 9.7533 | 0.49893 |  | 194 | 0.00035251 | 7097 | 0.076235 | 4113 | 2.682e-05 | 8408
FIGARDEN 210265224 | FIGARDEN 2102 | 254552102 |  | 6.226 | 0.61419 |  | 105.5 | 0.00035074 | 7127 | 0.076674 | 3947 | 2.682e-05 | 8409
WEEDPATCH 1101CB | WEEDPATCH 1101 | 252971101 |  | 7.1239 | 0.37114 |  | 110.5 | 0.00035698 | 7022 | 0.075282 | 4370 | 2.6796e-05 | 8410
SAN CARLOS 110475210 | SAN CARLOS 1104 | 24181104 | TRUE | 0.37809 | 0.18817 | 0.56626 | 5 | 0.00050468 | 5337 | 0.053073 | 8251 | 2.6785e-05 | 8411
MOLINO 11034676 | MOLINO 1103 | 42571103 |  | 14.8241 | 3.3753 |  | 249 | 0.00040476 | 6402 | 0.066499 | 6188 | 2.6778e-05 | 8412
GUERNSEY 1103941042 | GUERNSEY 1103 | 252661103 |  | 8.1208 | 0.61531 |  | 145 | 0.00034758 | 7181 | 0.077124 | 3672 | 2.6777e-05 | 8413
MARICOPA 1102453320 | MARICOPA 1102 | 254211102 |  | 3.3409 | 0 |  | 58 | 0.00037469 | 6771 | 0.07121 | 4870 | 2.6776e-05 | 8414
SHEPHERD 2112CB | SHEPHERD 2112 | 252062112 |  | 1.6947 | 0.16723 |  | 36 | 0.00035516 | 7053 | 0.076287 | 4096 | 2.6771e-05 | 8415
GRAND ISLAND 22239492 | GRAND ISLAND 2223 | 62462223 |  | 11.4865 | 3.1725 |  | 236.5 | 0.00036584 | 6908 | 0.072521 | 4716 | 2.6766e-05 | 8416
HOLLISTER 21034816 | HOLLISTER 2103 | 182492103 |  | 3.1525 | 1.6627 |  | 58.8333 | 0.00045346 | 5890 | 0.060935 | 6897 | 2.6766e-05 | 8417
LOCKEFORD 21011330 | LOCKEFORD 2101 | 163682101 |  | 9.2441 | 2.0585 |  | 174.5 | 0.00036027 | 6979 | 0.075088 | 4402 | 2.6764e-05 | 8418
EMBARCADERO (Z) 1115CB | EMBARCADERO (Z) 1115 | 22871115 |  | 0.24501 | 0.30642 |  | 12.5 | 0.00050417 | 5346 | 0.053073 | 8251 | 2.6757e-05 | 8419
BELLEVUE 110239026 | BELLEVUE 1102 | 43181102 |  | 3.9958 | 1.2864 |  | 73 | 0.00039325 | 6533 | 0.068277 | 5341 | 2.6756e-05 | 8420
JACINTO 110287210 | JACINTO 1102 | 102851102 |  | 5.8843 | 0.78665 |  | 109 | 0.00034941 | 7151 | 0.077144 | 3653 | 2.6753e-05 | 8421
SAN LEANDRO U 1114458451 | SAN LEANDRO U 1114 | 13111114 | FALSE | 2.4412 | 2.7973 | 2.3165 | 35.8333 | 0.0005037 | 5352 | 0.053073 | 8250 | 2.6733e-05 | 8422
COTATI 110494186 | COTATI 1104 | 42271104 |  | 2.7773 | 0.98794 |  | 56.5 | 0.00042372 | 6186 | 0.065628 | 6334 | 2.673e-05 | 8423
SAN BENITO 2101CB | SAN BENITO 2101 | 182742101 |  | 8.3443 | 3.5757 |  | 152.25 | 0.00041475 | 6286 | 0.064967 | 6441 | 2.6716e-05 | 8424
KINGSBURG 1108923080 | KINGSBURG 1108 | 252241108 |  | 4.3685 | 0.87922 |  | 81.5 | 0.00034517 | 7219 | 0.0774 | 3397 | 2.6716e-05 | 8425
MERCED 11164380 | MERCED 1116 | 252801116 |  | 21.3876 | 3.1194 |  | 372 | 0.00037057 | 6834 | 0.074026 | 4553 | 2.671e-05 | 8426
PARLIER 1104CB | PARLIER 1104 | 252291104 |  | 5.0748 | 0.36084 |  | 82.1667 | 0.00035055 | 7133 | 0.076715 | 3927 | 2.6688e-05 | 8427
CRESSEY 210396596 | CRESSEY 2103 | 254702103 |  | 4.5406 | 0.44841 |  | 83 | 0.00034635 | 7200 | 0.077107 | 3685 | 2.6683e-05 | 8428
BORDEN 110238670 | BORDEN 1102 | 255121102 |  | 1.7431 | 0.33071 |  | 28.5 | 0.00035956 | 6988 | 0.074287 | 4516 | 2.6677e-05 | 8429
FITCH MOUNTAIN 1111610 | FITCH MOUNTAIN 1111 | 42751111 |  | 2.5843 | 0.52522 |  | 48.8333 | 0.00039807 | 6474 | 0.067 | 6057 | 2.6671e-05 | 8430
RIVERBANK 171357168 | RIVERBANK 1713 | 163191713 |  | 7.6501 | 0.56646 |  | 129.5 | 0.00034487 | 7223 | 0.077339 | 3422 | 2.6662e-05 | 8431
LOGAN CREEK 2102CB | LOGAN CREEK 2102 | 103142102 |  | 6.5929 | 0.04861 |  | 102.6667 | 0.00036596 | 6902 | 0.0743 | 4514 | 2.6661e-05 | 8432
BASALT 11065030 | BASALT 1106 | 42461106 |  | 5.6055 | 0.63319 |  | 109.5 | 0.00039079 | 6560 | 0.068428 | 5301 | 2.665e-05 | 8433
DEEPWATER 11076212 | DEEPWATER 1107 | 63621107 |  | 11.4715 | 1.5345 |  | 218.5 | 0.00035587 | 7046 | 0.075668 | 4296 | 2.665e-05 | 8434
LLAGAS 2101XR322 | LLAGAS 2101 | 83182101 |  | 9.9713 | 1.7741 |  | 197 | 0.00039756 | 6482 | 0.066994 | 6062 | 2.6636e-05 | 8435
PEASE 11037276 | PEASE 1103 | 153751103 |  | 15.7957 | 2.8856 |  | 257.5 | 0.0004083 | 6355 | 0.06783 | 5465 | 2.6613e-05 | 8436
LOCKEFORD 210180774 | LOCKEFORD 2101 | 163682101 |  | 6.5992 | 1.3031 |  | 117 | 0.00034381 | 7242 | 0.0774 | 3397 | 2.661e-05 | 8437
HOOPA 1101561116 | HOOPA 1101 | 192401101 |  | 0.012966 | 0 |  | 0.5 | 0.00038422 | 6647 | 0.069238 | 5157 | 2.6602e-05 | 8438
LOGAN CREEK 21012030 | LOGAN CREEK 2101 | 103142101 |  | 1.0986 | 0.075915 |  | 19 | 0.0003435 | 7249 | 0.0774 | 3397 | 2.6587e-05 | 8439
FULTON 1105172 | FULTON 1105 | 42561105 |  | 9.6044 | 0.4286 |  | 172.5 | 0.0003935 | 6528 | 0.067725 | 5503 | 2.6585e-05 | 8440
WATSONVILLE 210112662 | WATSONVILLE 2101 | 83332101 |  | 22.3058 | 3.2979 |  | 417.5 | 0.00039653 | 6495 | 0.067096 | 5902 | 2.6583e-05 | 8441
MOSHER 211112888 | MOSHER 2111 | 163722111 |  | 0.99085 | 0.052935 |  | 15 | 0.00046382 | 5762 | 0.058323 | 7245 | 2.6575e-05 | 8442
GOLDTREE 110815803 | GOLDTREE 1108 | 182581108 |  | 0.40828 | 0.62629 |  | 10.5 | 0.00039496 | 6513 | 0.06725 | 5763 | 2.6565e-05 | 8443
BELLE HAVEN 11058978 | BELLE HAVEN 1105 | 24021105 |  | 2.4572 | 2.2015 |  | 51.8333 | 0.00050029 | 5387 | 0.053073 | 8251 | 2.6552e-05 | 8444
WEBER 110814576 | WEBER 1108 | 163481108 |  | 13.6398 | 2.1982 |  | 259 | 0.00036291 | 6945 | 0.074182 | 4529 | 2.6549e-05 | 8445
MADISON 210134164 | MADISON 2101 | 63172101 |  | 2.7636 | 1.6441 |  | 51 | 0.0004457 | 5957 | 0.061486 | 6834 | 2.6541e-05 | 8446
MERCED 110890520 | MERCED 1108 | 252801108 |  | 0.88938 | 0.47844 |  | 15.5 | 0.00049851 | 5404 | 0.054642 | 7817 | 2.6535e-05 | 8447
LOCKEFORD 210212464 | LOCKEFORD 2102 | 163682102 |  | 2.8207 | 0.40464 |  | 50.8333 | 0.00034478 | 7225 | 0.077096 | 3694 | 2.6528e-05 | 8448
CELERON 1101CB | CELERON 1101 | 255271101 |  | 0.13233 | 0 |  | 2.3333 | 0.0003959 | 6502 | 0.067 | 6056 | 2.6525e-05 | 8449
LAMONT 11024409 | LAMONT 1102 | 253911102 |  | 10.6153 | 1.1141 |  | 178 | 0.00034647 | 7198 | 0.07654 | 4000 | 2.6525e-05 | 8450
OAK 0401R7252 | OAK 0401 | 12600401 | FALSE | 2.4167 | 2.8191 | 4.3285 | 40.8333 | 0.00044402 | 5973 | 0.059251 | 7122 | 2.6523e-05 | 8451
WRIGHT 11109090 | WRIGHT 1110 | 254641110 |  | 15.0874 | 1.0938 |  | 276.75 | 0.00034915 | 7159 | 0.076529 | 4005 | 2.6523e-05 | 8452
ARCATA 1105CB | ARCATA 1105 | 192021105 |  | 5.6114 | 2.8868 |  | 88.75 | 0.00043004 | 6118 | 0.063406 | 6621 | 2.6522e-05 | 8453
PEASE 11011248 | PEASE 1101 | 153751101 |  | 2.2174 | 0.041923 |  | 38 | 0.00039493 | 6514 | 0.068984 | 5194 | 2.6515e-05 | 8454
MADISON 110320062 | MADISON 1103 | 63171103 |  | 1.4085 | 0.03756 |  | 25.5 | 0.00035033 | 7136 | 0.075768 | 4272 | 2.6514e-05 | 8455
HURON 1108739538 | HURON 1108 | 253161108 |  | 0.82639 | 0.020788 |  | 13 | 0.00035107 | 7121 | 0.075529 | 4332 | 2.6506e-05 | 8456
FIREBAUGH 110236934 | FIREBAUGH 1102 | 253471102 |  | 4.0402 | 1.4697 |  | 75 | 0.00042302 | 6194 | 0.066411 | 6204 | 2.65e-05 | 8457
RIPON 1701848930 | RIPON 1701 | 163801701 |  | 5.2383 | 0.72651 |  | 93.5 | 0.00036165 | 6962 | 0.074814 | 4440 | 2.6496e-05 | 8458
DIVIDE 1102M144 | DIVIDE 1102 | 182571102 |  | 7.6266 | 3.2868 |  | 137 | 0.00040176 | 6431 | 0.066148 | 6239 | 2.6494e-05 | 8459
SMYRNA 1104CB | SMYRNA 1104 | 253551104 |  | 7.593 | 0.026798 |  | 117.0333 | 0.00034202 | 7274 | 0.0774 | 3398 | 2.6472e-05 | 8460
CORNING 110164132 | CORNING 1101 | 103331101 |  | 4.4066 | 0.67025 |  | 80.5 | 0.00039148 | 6548 | 0.067715 | 5506 | 2.6472e-05 | 8461
CARUTHERS 1102R5100 | CARUTHERS 1102 | 252371102 |  | 14.9419 | 6.6562 |  | 279 | 0.00038371 | 6656 | 0.070861 | 4908 | 2.6464e-05 | 8462
CASTROVILLE 21045002 | CASTROVILLE 2104 | 182352104 |  | 9.8241 | 0.48885 |  | 186 | 0.00039127 | 6553 | 0.067501 | 5600 | 2.6464e-05 | 8463
GERBER 110135536 | GERBER 1101 | 103391101 |  | 9.7404 | 1.8479 |  | 172.5 | 0.00039329 | 6531 | 0.068269 | 5343 | 2.6456e-05 | 8464
TEMPLETON 2113CB | TEMPLETON 2113 | 183052113 | TRUE | 25.7325 | 4.9619 | 0.072871 | 457.8333 | 0.0002999 | 8020 | 0.085815 | 3365 | 2.6451e-05 | 8465
MORGAN HILL 2106XR002 | MORGAN HILL 2106 | 83242106 |  | 8.5028 | 2.867 |  | 166 | 0.00039078 | 6561 | 0.067605 | 5544 | 2.6447e-05 | 8466
GREEN VALLEY 210312656 | GREEN VALLEY 2103 | 83192103 |  | 18.8102 | 1.837 |  | 353.5 | 0.00039564 | 6503 | 0.066902 | 6089 | 2.6443e-05 | 8467
WEST FRESNO 111183387 | WEST FRESNO 1111 | 253731111 |  | 7.3265 | 2.1542 |  | 135.5 | 0.00039033 | 6567 | 0.069907 | 5062 | 2.6439e-05 | 8468
KERMAN 1108R1690 | KERMAN 1108 | 252711108 |  | 5.3783 | 0.98938 |  | 111.5 | 0.00038324 | 6660 | 0.070741 | 4927 | 2.6417e-05 | 8469
PEASE 11042012 | PEASE 1104 | 153751104 |  | 16.2637 | 2.8146 |  | 261 | 0.00040937 | 6338 | 0.067923 | 5428 | 2.6407e-05 | 8470
KETTLEMAN HILLS 2104CB | KETTLEMAN HILLS 2104 | 252732104 |  | 3.9341 | 0.079865 |  | 66.5 | 0.00039278 | 6536 | 0.067499 | 5602 | 2.6404e-05 | 8471
ALTO 1121508 | ALTO 1121 | 42031121 |  | 6.0128 | 1.7222 |  | 117 | 0.00041174 | 6316 | 0.067608 | 5541 | 2.6401e-05 | 8472
LODI 110283726 | LODI 1102 | 162111102 |  | 5.841 | 0.62764 |  | 92 | 0.00034954 | 7147 | 0.076039 | 4185 | 2.6391e-05 | 8473
CANAL 1103CB | CANAL 1103 | 252091103 |  | 11.3506 | 1.411 |  | 190.3333 | 0.00039933 | 6462 | 0.070069 | 5030 | 2.6384e-05 | 8474
WEST FRESNO 1101R1766 | WEST FRESNO 1101 | 253731101 |  | 6.9709 | 1.1379 |  | 119 | 0.00036291 | 6944 | 0.073221 | 4647 | 2.6382e-05 | 8475
PEACHTON 11021960 | PEACHTON 1102 | 103241102 |  | 2.4555 | 0 |  | 38 | 0.00037495 | 6765 | 0.070116 | 5017 | 2.6377e-05 | 8476
PAUL SWEET 210910216 | PAUL SWEET 2109 | 83252109 |  | 7.4155 | 6.2981 |  | 103 | 0.00046265 | 5778 | 0.057179 | 7407 | 2.6366e-05 | 8477
OAKLAND D 1202CB | OAKLAND D 1202 | 12041202 |  | 0.23951 | 0 |  | 2.3333 | 0.00049661 | 5428 | 0.053073 | 8250 | 2.6356e-05 | 8478
LOS COCHES 11027046 | LOS COCHES 1102 | 182151102 |  | 3.2407 | 0.043183 |  | 65.5 | 0.00038692 | 6622 | 0.06827 | 5342 | 2.635e-05 | 8479
TYLER 1104CB | TYLER 1104 | 103571104 |  | 11.8841 | 1.5268 |  | 220.5 | 0.00039337 | 6530 | 0.067542 | 5578 | 2.6349e-05 | 8480
SANGER 1110CB | SANGER 1110 | 252351110 |  | 7.1625 | 1.168 |  | 123.3333 | 0.0003546 | 7061 | 0.075292 | 4366 | 2.6331e-05 | 8481
SANGER 111237242 | SANGER 1112 | 252351112 |  | 7.7398 | 1.4875 |  | 140.3333 | 0.00034112 | 7288 | 0.077232 | 3551 | 2.6331e-05 | 8482
LODI 110134834 | LODI 1101 | 162111101 |  | 1.1705 | 0.073909 |  | 23.5 | 0.00036093 | 6969 | 0.074143 | 4536 | 2.6321e-05 | 8483
WALDO 0401965216 | WALDO 0401 | 13350401 | FALSE | 1.6539 | 1.9999 | 3.5999 | 29.75 | 0.00043412 | 6070 | 0.060575 | 6944 | 2.6321e-05 | 8484
BAHIA 1104624 | BAHIA 1104 | 43251104 |  | 3.5205 | 0.69602 |  | 73.3333 | 0.00042109 | 6213 | 0.065009 | 6431 | 2.6312e-05 | 8485
ARVIN 1101CB | ARVIN 1101 | 253801101 |  | 4.1034 | 0.2371 |  | 69 | 0.00037258 | 6795 | 0.070581 | 4944 | 2.63e-05 | 8486
WHEATLAND 11021368 | WHEATLAND 1102 | 152811102 |  | 2.5194 | 0.16528 |  | 51 | 0.00034106 | 7290 | 0.077091 | 3697 | 2.6295e-05 | 8487
LLAGAS 2103XR424 | LLAGAS 2103 | 83182103 |  | 5.2202 | 0.76889 |  | 82.0833 | 0.00039396 | 6523 | 0.066895 | 6095 | 2.6291e-05 | 8488
EIGHT MILE 210111380 | EIGHT MILE 2101 | 163912101 |  | 61.2889 | 6.9138 |  | 1087 | 0.00034407 | 7235 | 0.076636 | 3966 | 2.6291e-05 | 8489
DINUBA 11067810 | DINUBA 1106 | 254091106 |  | 6.2342 | 1.8233 |  | 110 | 0.0003484 | 7167 | 0.076372 | 4062 | 2.6271e-05 | 8490
STOREY 11095200 | STOREY 1109 | 254611109 |  | 0.9789 | 0 |  | 21 | 0.00039207 | 6541 | 0.067 | 6057 | 2.6269e-05 | 8491
SALMON CREEK 1101CB | SALMON CREEK 1101 | 43161101 |  | 0.03752 | 0 |  | 3.5 | 0.00039134 | 6552 | 0.06707 | 5925 | 2.6247e-05 | 8492
ARCATA 11057580 | ARCATA 1105 | 192021105 |  | 6.8393 | 3.2311 |  | 117.5 | 0.00041522 | 6279 | 0.063266 | 6633 | 2.6245e-05 | 8493
NORTH TOWER 1102CB | NORTH TOWER 1102 | 42041102 |  | 2.2572 | 2.6939 |  | 45.2 | 0.00046362 | 5765 | 0.05714 | 7413 | 2.6229e-05 | 8494
GRANT 1105MR363 | GRANT 1105 | 14381105 |  | 6.3761 | 6.6328 |  | 92.6667 | 0.0004942 | 5450 | 0.053073 | 8250 | 2.6228e-05 | 8495
DUMBARTON 11108918 | DUMBARTON 1110 | 14471110 |  | 1.3919 | 1.4566 |  | 20.8333 | 0.00049414 | 5452 | 0.053073 | 8252 | 2.6225e-05 | 8496
LARKIN (Y) 1140CB | LARKIN (Y) 1140 | 22801140 |  | 0.083323 | 0.1971 |  | 4.75 | 0.00049413 | 5454 | 0.053073 | 8251 | 2.6225e-05 | 8497
GRAND ISLAND 222740136 | GRAND ISLAND 2227 | 62462227 |  | 15.7646 | 1.4261 |  | 294.5 | 0.00034607 | 7205 | 0.076127 | 4154 | 2.6211e-05 | 8498
MAGUNDEN 2108323832 | MAGUNDEN 2108 | 252772108 |  | 3.9879 | 0.27226 |  | 67 | 0.00036908 | 6856 | 0.072638 | 4703 | 2.62e-05 | 8499
ROB ROY 210512582 | ROB ROY 2105 | 83692105 |  | 0.19604 | 0 |  | 5.5 | 0.0004442 | 5969 | 0.060028 | 7016 | 2.6198e-05 | 8500
SALINAS 1109CB | SALINAS 1109 | 182011109 |  | 12.217 | 8.7713 |  | 210.3333 | 0.00047115 | 5688 | 0.057126 | 7420 | 2.6179e-05 | 8501
MC CALL 1106430534 | MC CALL 1106 | 254121106 |  | 5.9644 | 0.97857 |  | 112 | 0.00034406 | 7236 | 0.076314 | 4086 | 2.6177e-05 | 8502
TULARE LAKE 1104225890 | TULARE LAKE 1104 | 252951104 |  | 2.1014 | 0.060747 |  | 42.8333 | 0.00039048 | 6564 | 0.067022 | 5999 | 2.6171e-05 | 8503
RICE 11033032 | RICE 1103 | 62831103 |  | 11.4448 | 1.1419 |  | 195.5 | 0.00035428 | 7070 | 0.074886 | 4430 | 2.6165e-05 | 8504
BOGUE 11041382 | BOGUE 1104 | 153781104 |  | 1.1718 | 0.018039 |  | 22 | 0.00034709 | 7189 | 0.076132 | 4149 | 2.6158e-05 | 8505
KEARNEY 110477226 | KEARNEY 1104 | 252701104 |  | 5.5283 | 1.8344 |  | 100.5 | 0.00036584 | 6909 | 0.071875 | 4783 | 2.6157e-05 | 8506
MERCED FALLS 1102CB | MERCED FALLS 1102 | 252811102 |  | 14.1964 | 1.7136 |  | 265 | 0.00038055 | 6691 | 0.068374 | 5308 | 2.6148e-05 | 8507
SCHINDLER 1105CB | SCHINDLER 1105 | 252891105 |  | 7.8484 | 0.44749 |  | 108.7833 | 0.00034775 | 7179 | 0.075609 | 4309 | 2.6148e-05 | 8508
PEASE 110450628 | PEASE 1104 | 153751104 |  | 3.4849 | 0.25587 |  | 68 | 0.0003505 | 7134 | 0.074791 | 4444 | 2.6143e-05 | 8509
CRESSEY 2104104770 | CRESSEY 2104 | 254702104 |  | 9.9009 | 1.0503 |  | 181.8333 | 0.00034545 | 7215 | 0.076538 | 4002 | 2.6139e-05 | 8510
SANTA MARIA 1108M122 | SANTA MARIA 1108 | 182671108 |  | 1.421 | 0.53451 |  | 23.5 | 0.00044049 | 6008 | 0.060498 | 6958 | 2.6131e-05 | 8511
DINUBA 11047865F | DINUBA 1104 | 254091104 |  | 1.6853 | 0.22343 |  | 30.5 | 0.00034098 | 7292 | 0.076602 | 3982 | 2.613e-05 | 8512
LOS OSITOS 2101CB | LOS OSITOS 2101 | 182082101 |  | 10.9958 | 0.43621 |  | 230.25 | 0.00039031 | 6568 | 0.067165 | 5840 | 2.6108e-05 | 8513
BLACKWELL 2101434222 | BLACKWELL 2101 | 254682101 |  | 4.647 | 0.03933 |  | 78.5 | 0.0003889 | 6590 | 0.067151 | 5851 | 2.6101e-05 | 8514
GATES 1110950861 | GATES 1110 | 253931110 |  | 10.9948 | 0.14786 |  | 180 | 0.00033949 | 7318 | 0.076955 | 3791 | 2.6092e-05 | 8515
RIPON 1701397478 | RIPON 1701 | 163801701 |  | 21.0205 | 1.9853 |  | 381.5 | 0.00035666 | 7031 | 0.074547 | 4481 | 2.6092e-05 | 8516
MENDOTA 110390290 | MENDOTA 1103 | 252311103 |  | 1.2093 | 0.56177 |  | 22.5 | 0.00047455 | 5654 | 0.056857 | 7458 | 2.6091e-05 | 8517
VINA 1101247612 | VINA 1101 | 103581101 |  | 0.42802 | 0 |  | 7.5 | 0.00038908 | 6586 | 0.067047 | 5950 | 2.6086e-05 | 8518
DUNNIGAN 11014704 | DUNNIGAN 1101 | 63811101 |  | 3.4224 | 0.035046 |  | 65.5 | 0.00035018 | 7139 | 0.074771 | 4447 | 2.6076e-05 | 8519
RIVERBANK 1713CB | RIVERBANK 1713 | 163191713 |  | 19.9772 | 1.7114 |  | 341.8333 | 0.00034486 | 7224 | 0.076234 | 4114 | 2.607e-05 | 8520
TEMBLOR 110437694 | TEMBLOR 1104 | 252551104 |  | 2.9551 | 0 |  | 47.8333 | 0.0003943 | 6517 | 0.066344 | 6213 | 2.6062e-05 | 8521
LOS MOLINOS 1102CB | LOS MOLINOS 1102 | 103481102 |  | 22.0662 | 5.1207 |  | 399 | 0.00038959 | 6578 | 0.067457 | 5632 | 2.6047e-05 | 8522
BELMONT 11104845 | BELMONT 1110 | 24031110 |  | 2.1282 | 1.689 |  | 31.5 | 0.00046099 | 5798 | 0.057052 | 7431 | 2.6038e-05 | 8523
SANGER 1114CB | SANGER 1114 | 252351114 |  | 14.664 | 1.7474 |  | 250 | 0.00034264 | 7264 | 0.076297 | 4089 | 2.6031e-05 | 8524
HOLLISTER 2102406496 | HOLLISTER 2102 | 182492102 |  | 2.8302 | 0.47964 |  | 51.5 | 0.00038762 | 6609 | 0.067335 | 5712 | 2.6024e-05 | 8525
SF L 0401CB | SF L 0401 | 22260401 |  | 2.4767 | 3.0696 |  | 57 | 0.00049023 | 5492 | 0.053073 | 8251 | 2.6018e-05 | 8526
LODI 110237602 | LODI 1102 | 162111102 |  | 10.7168 | 1.0921 |  | 195.5 | 0.00034047 | 7299 | 0.076653 | 3957 | 2.6006e-05 | 8527
DAIRYLAND 1105CB | DAIRYLAND 1105 | 252421105 |  | 2.5553 | 0 |  | 30.25 | 0.00033562 | 7375 | 0.0774 | 3397 | 2.5977e-05 | 8528
VICTOR 110275234 | VICTOR 1102 | 163281102 |  | 12.6758 | 1.4589 |  | 222.5 | 0.00033571 | 7373 | 0.07729 | 3487 | 2.5954e-05 | 8529
MISSION (X) 1109CB | MISSION (X) 1109 | 22011109 |  | 0.46996 | 0.7912 |  | 17 | 0.00048897 | 5505 | 0.053073 | 8251 | 2.5951e-05 | 8530
WILSON 1103CB | WILSON 1103 | 254301103 |  | 16.539 | 1.3815 |  | 284.8333 | 0.00034413 | 7232 | 0.075931 | 4219 | 2.5942e-05 | 8531
RIO BRAVO 1102CB | RIO BRAVO 1102 | 252861102 |  | 12.7911 | 2.0788 |  | 203.6667 | 0.00037446 | 6774 | 0.07201 | 4774 | 2.5927e-05 | 8532
ATWATER 110790580 | ATWATER 1107 | 253611107 |  | 7.4824 | 0.6121 |  | 121.5 | 0.00035908 | 6995 | 0.072848 | 4677 | 2.5925e-05 | 8533
GABILAN 110191118 | GABILAN 1101 | 182331101 |  | 3.6297 | 2.3235 |  | 58 | 0.00044707 | 5941 | 0.059196 | 7131 | 2.5915e-05 | 8534
ORICK 11021484 | ORICK 1102 | 192261102 |  | 16.4297 | 0.49063 |  | 309.5 | 0.00038483 | 6640 | 0.06734 | 5710 | 2.591e-05 | 8535
DAVIS 110620232 | DAVIS 1106 | 62041106 |  | 8.3245 | 0.40714 |  | 141.5 | 0.00034943 | 7149 | 0.074903 | 4427 | 2.5906e-05 | 8536
COLUSA 110167508 | COLUSA 1101 | 62021101 |  | 13.477 | 3.3242 |  | 228.1667 | 0.00039257 | 6537 | 0.070067 | 5031 | 2.5906e-05 | 8537
RENFRO 21011146 | RENFRO 2101 | 254572101 |  | 9.5438 | 0.50402 |  | 161.5 | 0.00037621 | 6745 | 0.070419 | 4957 | 2.5903e-05 | 8538
EAST GRAND 110412701 | EAST GRAND 1104 | 22571104 |  | 7.3523 | 5.4493 |  | 119.6667 | 0.00043605 | 6056 | 0.06066 | 6937 | 2.5883e-05 | 8539
MC CALL 110386670 | MC CALL 1103 | 254121103 |  | 0.0072806 | 0 |  | 0.5 | 0.00048767 | 5522 | 0.053073 | 8251 | 2.5882e-05 | 8540
ORTIGA 1106CB | ORTIGA 1106 | 254311106 |  | 16.6775 | 1.5389 |  | 278 | 0.0003371 | 7348 | 0.076694 | 3938 | 2.5881e-05 | 8541
RIVERBANK 171466284 | RIVERBANK 1714 | 163191714 |  | 4.4054 | 0.45528 |  | 75.3333 | 0.00037822 | 6723 | 0.070597 | 4941 | 2.5881e-05 | 8542
DIVIDE 110245067 | DIVIDE 1102 | 182571102 |  | 0.91423 | 0.31363 |  | 16.5 | 0.00042558 | 6168 | 0.063107 | 6654 | 2.5878e-05 | 8543
MOLINO 1101324 | MOLINO 1101 | 42571101 |  | 15.119 | 4.0413 |  | 279 | 0.00038694 | 6621 | 0.066964 | 6076 | 2.5874e-05 | 8544
HOLLISTER 210193404 | HOLLISTER 2101 | 182492101 |  | 1.5443 | 0.42202 |  | 29.5 | 0.00039378 | 6524 | 0.066056 | 6259 | 2.586e-05 | 8545
LINCOLN 1104CB | LINCOLN 1104 | 153701104 |  | 2.605 | 0.092484 |  | 39.75 | 0.00038586 | 6632 | 0.067 | 6057 | 2.5853e-05 | 8546
ORTIGA 110678478 | ORTIGA 1106 | 254311106 |  | 3 | 0.1878 |  | 48.8333 | 0.00034188 | 7275 | 0.075583 | 4316 | 2.5839e-05 | 8547
MARINA (F) 0402CB | MARINA (F) 0402 | 22780402 |  | 0.4825 | 0.44652 |  | 9.5 | 0.0004868 | 5530 | 0.053073 | 8251 | 2.5836e-05 | 8548
WINDSOR 1102596 | WINDSOR 1102 | 43501102 |  | 9.8114 | 1.5592 |  | 177 | 0.00038871 | 6593 | 0.067012 | 6020 | 2.5833e-05 | 8549
EAST MARYSVILLE 11081706 | EAST MARYSVILLE 1108 | 152331108 |  | 24.6973 | 1.5566 |  | 430.5 | 0.00036252 | 6958 | 0.071437 | 4839 | 2.5827e-05 | 8550
REEDLEY 110186412 | REEDLEY 1101 | 252341101 |  | 2.3311 | 0.45727 |  | 43.75 | 0.00038415 | 6649 | 0.070785 | 4920 | 2.5822e-05 | 8551
CAPAY 110237148 | CAPAY 1102 | 102111102 |  | 4.1014 | 0.39927 |  | 68 | 0.00038296 | 6665 | 0.067539 | 5581 | 2.5821e-05 | 8552
WOODLAND 111021288 | WOODLAND 1110 | 62031110 |  | 7.5519 | 1.1807 |  | 134.5 | 0.00038003 | 6695 | 0.067985 | 5408 | 2.582e-05 | 8553
MT EDEN 110211056 | MT EDEN 1102 | 13761102 |  | 1.158 | 1.3616 |  | 17 | 0.00048629 | 5537 | 0.053073 | 8251 | 2.5809e-05 | 8554
CORCORAN 11082052F | CORCORAN 1108 | 252171108 |  | 0.57677 | 0.3409 |  | 11 | 0.00048619 | 5539 | 0.053073 | 8251 | 2.5803e-05 | 8555
BORDEN 11039820 | BORDEN 1103 | 255121103 |  | 23.5486 | 1.7792 |  | 394.3333 | 0.00033943 | 7319 | 0.076112 | 4158 | 2.58e-05 | 8556
DOLAN ROAD 110157184 | DOLAN ROAD 1101 | 182381101 |  | 3.5722 | 1.4239 |  | 58.5 | 0.00038501 | 6639 | 0.067003 | 6041 | 2.5797e-05 | 8557
KERMAN 1101R3040 | KERMAN 1101 | 252711101 |  | 11.6046 | 1.3226 |  | 200 | 0.0003416 | 7280 | 0.075869 | 4240 | 2.5794e-05 | 8558
TRACY 110685274 | TRACY 1106 | 162881106 |  | 5.641 | 0.35032 |  | 105 | 0.00033888 | 7330 | 0.076589 | 3988 | 2.5788e-05 | 8559
DIXON 110212352 | DIXON 1102 | 62061102 |  | 4.4556 | 0.62831 |  | 81.5 | 0.00034872 | 7164 | 0.075267 | 4372 | 2.5769e-05 | 8560
LIVINGSTON 1104CB | LIVINGSTON 1104 | 252261104 |  | 22.3455 | 2.7461 |  | 387 | 0.00034539 | 7216 | 0.075819 | 4258 | 2.5766e-05 | 8561
WEST SACRAMENTO 1109743964 | WEST SACRAMENTO 1109 | 63131109 |  | 22.0727 | 1.7735 |  | 434 | 0.00033993 | 7306 | 0.076504 | 4015 | 2.5756e-05 | 8562
MANTECA 17058990 | MANTECA 1705 | 162611705 |  | 14.4161 | 2.0365 |  | 259.5 | 0.00034186 | 7276 | 0.076074 | 4172 | 2.5754e-05 | 8563
GEYSERVILLE 1102501402 | GEYSERVILLE 1102 | 42891102 | TRUE | 1.9674 | 0.070394 | 0.01553 | 32 | 0.00037601 | 6749 | 0.067226 | 5782 | 2.5753e-05 | 8564
LOCKEFORD 210212462 | LOCKEFORD 2102 | 163682102 |  | 12.9404 | 1.724 |  | 215.5 | 0.0003337 | 7399 | 0.077217 | 3577 | 2.5741e-05 | 8565
ZAMORA 110723345 | ZAMORA 1107 | 63191107 |  | 4.7454 | 0.2873 |  | 79.5 | 0.00033965 | 7312 | 0.076157 | 4140 | 2.5736e-05 | 8566
KEARNEY 1110CB | KEARNEY 1110 | 252701110 |  | 7.3982 | 0.67314 |  | 126.5 | 0.00034057 | 7297 | 0.076132 | 4151 | 2.5736e-05 | 8567
CHOWCHILLA 1101901360 | CHOWCHILLA 1101 | 254101101 |  | 2.6743 | 0.18582 |  | 40.5 | 0.00033538 | 7378 | 0.076799 | 3887 | 2.573e-05 | 8568
ATWATER 110210680 | ATWATER 1102 | 253611102 |  | 8.9986 | 1.1525 |  | 155.8333 | 0.000335 | 7382 | 0.076987 | 3768 | 2.5724e-05 | 8569
BELLEVUE 110239024 | BELLEVUE 1102 | 43181102 |  | 5.147 | 1.3262 |  | 81.5 | 0.0003785 | 6717 | 0.067893 | 5440 | 2.5723e-05 | 8570
COALINGA NO 1 1107CB | COALINGA NO 1 1107 | 252161107 |  | 4.0428 | 0.1015 |  | 61.5833 | 0.00038613 | 6628 | 0.068203 | 5359 | 2.5712e-05 | 8571
PASO ROBLES 110195810 | PASO ROBLES 1101 | 182611101 |  | 3.9158 | 1.7177 |  | 69 | 0.0004555 | 5862 | 0.057421 | 7370 | 2.5712e-05 | 8572
OCEANO 1103CB | OCEANO 1103 | 182601103 |  | 5.3627 | 4.1557 |  | 83.75 | 0.00031493 | 7716 | 0.076552 | 3997 | 2.5711e-05 | 8573
STOREY 1108CB | STOREY 1108 | 254611108 |  | 12.274 | 3.1764 |  | 233.3333 | 0.00033935 | 7320 | 0.076474 | 4027 | 2.5704e-05 | 8574
OROSI 1104CB | OROSI 1104 | 252841104 |  | 12.4459 | 4.7384 |  | 231 | 0.00039614 | 6500 | 0.066814 | 6119 | 2.5704e-05 | 8575
KINGSBURG 1116CB | KINGSBURG 1116 | 252241116 |  | 8.0413 | 0.46339 |  | 115.5333 | 0.00033472 | 7386 | 0.076843 | 3862 | 2.57e-05 | 8576
ANITA 110153616 | ANITA 1101 | 102841101 |  | 7.6507 | 0.40979 |  | 115.5 | 0.00037513 | 6761 | 0.069296 | 5146 | 2.5699e-05 | 8577
ORO LOMA 111589060 | ORO LOMA 1115 | 255371115 |  | 11.4804 | 3.7314 |  | 207 | 0.00036934 | 6850 | 0.072354 | 4739 | 2.5688e-05 | 8578
TRES VIAS 11012618 | TRES VIAS 1101 | 103251101 |  | 4.5152 | 0.11763 |  | 77 | 0.00034326 | 7254 | 0.075134 | 4397 | 2.5686e-05 | 8579
VALLEY HOME 17029070 | VALLEY HOME 1702 | 162981702 |  | 9.2968 | 1.0684 |  | 161.8333 | 0.00034932 | 7155 | 0.07526 | 4373 | 2.5685e-05 | 8580
PARLIER 1102CB | PARLIER 1102 | 252291102 |  | 10.9179 | 4.312 |  | 183.9167 | 0.00041049 | 6327 | 0.066006 | 6275 | 2.5674e-05 | 8581
DAIRYVILLE 1101147562 | DAIRYVILLE 1101 | 103341101 |  | 22.9338 | 2.7842 |  | 468 | 0.00038108 | 6684 | 0.067913 | 5434 | 2.5673e-05 | 8582
RICHMOND R 1122BR02 | RICHMOND R 1122 | 13471122 |  | 1.6472 | 0.36504 |  | 29.5 | 0.00037994 | 6697 | 0.067529 | 5586 | 2.5663e-05 | 8583
BOWLES 1103R1470 | BOWLES 1103 | 253531103 |  | 10.456 | 4.9865 |  | 217.5 | 0.00036836 | 6866 | 0.070265 | 4990 | 2.5661e-05 | 8584
PARLIER 1103CB | PARLIER 1103 | 252291103 |  | 3.041 | 0.83308 |  | 45.8333 | 0.00036013 | 6980 | 0.074148 | 4535 | 2.5658e-05 | 8585
PEASE 1103CB | PEASE 1103 | 153751103 |  | 12.7041 | 1.534 |  | 198.5833 | 0.00034739 | 7183 | 0.075231 | 4381 | 2.5653e-05 | 8586
EL NIDO 1102CB | EL NIDO 1102 | 252451102 |  | 21.5802 | 0.95203 |  | 356.8333 | 0.00033993 | 7307 | 0.075964 | 4210 | 2.5644e-05 | 8587
MCKITTRICK 1101CB | MCKITTRICK 1101 | 252781101 |  | 15.1728 | 0.87927 |  | 245 | 0.00037227 | 6799 | 0.069085 | 5178 | 2.5637e-05 | 8588
ATASCADERO 1102CB | ATASCADERO 1102 | 182541102 |  | 5.0757 | 1.9402 |  | 93.5 | 0.00038162 | 6680 | 0.067297 | 5731 | 2.5637e-05 | 8589
RIVERBANK 171190440 | RIVERBANK 1711 | 163191711 |  | 12.2481 | 1.3772 |  | 214 | 0.00036698 | 6884 | 0.072779 | 4687 | 2.5635e-05 | 8590
TRES VIAS 110175132 | TRES VIAS 1101 | 103251101 |  | 6.0192 | 2.3869 |  | 98 | 0.00038268 | 6669 | 0.067123 | 5879 | 2.562e-05 | 8591
RIPON 1701CB | RIPON 1701 | 163801701 |  | 8.873 | 0.75254 |  | 156 | 0.00033903 | 7327 | 0.076476 | 4025 | 2.562e-05 | 8592
SPENCE 1103150484 | SPENCE 1103 | 182201103 |  | 1.0594 | 0.066941 |  | 19.5 | 0.00044663 | 5945 | 0.057261 | 7397 | 2.5615e-05 | 8593
HIGHWAY 1105CB | HIGHWAY 1105 | 42651105 |  | 0.46866 | 0 |  | 12 | 0.00039904 | 6463 | 0.065475 | 6365 | 2.561e-05 | 8594
NEWMAN 110542128 | NEWMAN 1105 | 162741105 |  | 0.15914 | 0 |  | 1.5 | 0.00038222 | 6672 | 0.067 | 6057 | 2.5609e-05 | 8595
SONOMA 1107294 | SONOMA 1107 | 42721107 |  | 9.2631 | 0.51437 |  | 185.5 | 0.0003359 | 7366 | 0.11263 | 3283 | 2.5605e-05 | 8596
BANTA 110211898 | BANTA 1102 | 162471102 |  | 10.7641 | 0.76301 |  | 212 | 0.00033609 | 7363 | 0.076219 | 4123 | 2.5605e-05 | 8597
BOWLES 1103CB | BOWLES 1103 | 253531103 |  | 13.6307 | 4.9024 |  | 277.3333 | 0.00033135 | 7431 | 0.077312 | 3457 | 2.5604e-05 | 8598
SAN LUIS OBISPO 1104CB | SAN LUIS OBISPO 1104 | 182631104 | TRUE | 6.8107 | 0.19346 | 0.076222 | 94.6667 | 0.00035355 | 7081 | 0.095362 | 3326 | 2.5604e-05 | 8599
NEWARK 21KV 2110CB | NEWARK 21KV 2110 | 12232110 |  | 3.1877 | 0.02051 |  | 49.9167 | 0.0003549 | 7057 | 0.072902 | 4672 | 2.5602e-05 | 8600
DAVIS 1107600194 | DAVIS 1107 | 62041107 |  | 11.1879 | 0.61528 |  | 197.5 | 0.00033956 | 7316 | 0.07585 | 4248 | 2.5602e-05 | 8601
KERMAN 1102D4115 | KERMAN 1102 | 252711102 |  | 3.4566 | 0.52216 |  | 61.5 | 0.00033184 | 7424 | 0.077004 | 3759 | 2.5596e-05 | 8602
PLEASANT GROVE 21102236 | PLEASANT GROVE 2110 | 152442110 |  | 1.8459 | 0 |  | 30.5 | 0.00038197 | 6676 | 0.067 | 6057 | 2.5592e-05 | 8603
PAUL SWEET 210410916 | PAUL SWEET 2104 | 83252104 |  | 2.3799 | 1.4975 |  | 31.3333 | 0.0004804 | 5599 | 0.055357 | 7696 | 2.5588e-05 | 8604
LOCKEFORD 210256996 | LOCKEFORD 2102 | 163682102 |  | 5.3137 | 1.2034 |  | 88.3333 | 0.00033279 | 7410 | 0.077222 | 3566 | 2.5577e-05 | 8605
WAHTOKE 111169760 | WAHTOKE 1111 | 254531111 |  | 0.52146 | 0.041307 |  | 9.5 | 0.00033038 | 7442 | 0.0774 | 3397 | 2.5571e-05 | 8606
HARTER 11052294 | HARTER 1105 | 152851105 |  | 12.6082 | 2.0406 |  | 230 | 0.00036887 | 6860 | 0.071797 | 4795 | 2.5567e-05 | 8607
CANAL 1101CB | CANAL 1101 | 252091101 |  | 5.5628 | 0.19741 |  | 99.1667 | 0.00039788 | 6479 | 0.069235 | 5160 | 2.5557e-05 | 8608
BASALT 11061781 | BASALT 1106 | 42461106 |  | 1.8606 | 0.69706 |  | 37.5 | 0.00038088 | 6688 | 0.067078 | 5921 | 2.5549e-05 | 8609
REEDLEY 1112CB | REEDLEY 1112 | 252341112 |  | 9.6562 | 2.3166 |  | 182.5 | 0.00033005 | 7448 | 0.0774 | 3397 | 2.5546e-05 | 8610
LIVERMORE 1104MR271 | LIVERMORE 1104 | 12141104 |  | 1.7104 | 0 |  | 26.3333 | 0.00045392 | 5885 | 0.055982 | 7582 | 2.553e-05 | 8611
LEMOORE 11048760 | LEMOORE 1104 | 253601104 |  | 1.6587 | 1.2518 |  | 26 | 0.00042572 | 6166 | 0.059953 | 7024 | 2.5529e-05 | 8612
FREMONT 1104CB | FREMONT 1104 | 14351104 |  | 8.0338 | 6.5983 |  | 127 | 0.0004653 | 5746 | 0.055732 | 7633 | 2.5524e-05 | 8613
LOS MOLINOS 110171402 | LOS MOLINOS 1101 | 103481101 |  | 3.3607 | 0.56733 |  | 66 | 0.00037836 | 6719 | 0.067362 | 5695 | 2.5517e-05 | 8614
GREEN VALLEY 2103478624 | GREEN VALLEY 2103 | 83192103 |  | 0.082159 | 0.059684 |  | 1 | 0.00038061 | 6690 | 0.067 | 6057 | 2.5501e-05 | 8615
ZAMORA 1105868420 | ZAMORA 1105 | 63191105 |  | 14.566 | 0.88255 |  | 251 | 0.00033659 | 7356 | 0.076317 | 4083 | 2.55e-05 | 8616
ECHO SUMMIT 1101265728 | ECHO SUMMIT 1101 | 158031101 |  | 1.1022 | 0.76397 |  | 28.5 | 0.00037825 | 6722 | 0.067401 | 5669 | 2.5486e-05 | 8617
DINUBA 110544364 | DINUBA 1105 | 254091105 |  | 10.1698 | 1.5887 |  | 176 | 0.00032927 | 7465 | 0.0774 | 3397 | 2.5485e-05 | 8618
KERMAN 110263968 | KERMAN 1102 | 252711102 |  | 6.9486 | 2.0603 |  | 122.5 | 0.00038293 | 6666 | 0.068575 | 5266 | 2.5485e-05 | 8619
PASO ROBLES 1104R14 | PASO ROBLES 1104 | 182611104 |  | 4.6906 | 2.7951 |  | 73.8333 | 0.00041042 | 6329 | 0.06594 | 6284 | 2.5484e-05 | 8620
HONCUT 110197092 | HONCUT 1101 | 103211101 |  | 13.964 | 1.4189 |  | 240.5 | 0.00033385 | 7398 | 0.076591 | 3986 | 2.5471e-05 | 8621
MONTAGUE 2101CB | MONTAGUE 2101 | 83892101 |  | 0.87112 | 1.4838 |  | 15.3333 | 0.00047992 | 5603 | 0.053073 | 8250 | 2.5471e-05 | 8622
LOGAN CREEK 21022540 | LOGAN CREEK 2102 | 103142102 |  | 5.5577 | 0.41245 |  | 98.5 | 0.00036954 | 6847 | 0.070325 | 4975 | 2.5461e-05 | 8623
VICTOR 11026246 | VICTOR 1102 | 163281102 |  | 21.3597 | 2.7645 |  | 381.3333 | 0.00032959 | 7457 | 0.077244 | 3540 | 2.5441e-05 | 8624
SOLEDAD 210242506 | SOLEDAD 2102 | 182052102 |  | 11.2014 | 0.61028 |  | 223.5 | 0.00037815 | 6726 | 0.067495 | 5604 | 2.5441e-05 | 8625
MENLO 110344283 | MENLO 1103 | 24131103 |  | 1.6992 | 0.95604 |  | 28.8333 | 0.00045232 | 5901 | 0.056615 | 7490 | 2.5439e-05 | 8626
SALINAS 110522408 | SALINAS 1105 | 182011105 |  | 2.0629 | 2.1213 |  | 34.5 | 0.00047916 | 5607 | 0.053073 | 8251 | 2.543e-05 | 8627
FAIRMOUNT 0401395180 | FAIRMOUNT 0401 | 12650401 | FALSE | 1.4637 | 1.9622 | 3.1144 | 24.25 | 0.0004416 | 5998 | 0.058376 | 7237 | 2.5427e-05 | 8628
MORGAN HILL 2110716210 | MORGAN HILL 2110 | 83242110 |  | 0.018489 | 0 |  | 1.3333 | 0.00037923 | 6707 | 0.067 | 6056 | 2.5408e-05 | 8629
ATWATER 110610460 | ATWATER 1106 | 253611106 |  | 3.2349 | 0.44743 |  | 59 | 0.00035829 | 7003 | 0.072185 | 4757 | 2.5408e-05 | 8630
KERMAN 110348784 | KERMAN 1103 | 252711103 |  | 20.0344 | 3.1302 |  | 354.5 | 0.0003357 | 7374 | 0.076193 | 4130 | 2.5408e-05 | 8631
EL CERRITO G 1112BR170 | EL CERRITO G 1112 | 12501112 |  | 2.142 | 1.8055 |  | 30.0333 | 0.00047858 | 5614 | 0.053073 | 8252 | 2.5399e-05 | 8632
GRAND ISLAND 22279442 | GRAND ISLAND 2227 | 62462227 |  | 16.2633 | 2.6141 |  | 286.5833 | 0.00034396 | 7238 | 0.075315 | 4364 | 2.5397e-05 | 8633
BIOLA 1104CB | BIOLA 1104 | 252211104 |  | 11.8889 | 1.1098 |  | 206.3333 | 0.0003281 | 7484 | 0.0774 | 3397 | 2.5395e-05 | 8634
MC CALL 11086980 | MC CALL 1108 | 254121108 |  | 9.8871 | 3.1203 |  | 190 | 0.00032943 | 7461 | 0.077146 | 3652 | 2.5394e-05 | 8635
ARBUCKLE 110130376 | ARBUCKLE 1101 | 62081101 |  | 0.0034151 | 0 |  | 0.5 | 0.00047847 | 5615 | 0.053073 | 8251 | 2.5394e-05 | 8636
CORCORAN 1104CB | CORCORAN 1104 | 252171104 |  | 10.0834 | 0.65994 |  | 174.95 | 0.00033406 | 7395 | 0.076471 | 4028 | 2.5388e-05 | 8637
ARCATA 11066554 | ARCATA 1106 | 192021106 |  | 0.28567 | 0.029651 |  | 4.5 | 0.00037153 | 6819 | 0.069311 | 5143 | 2.5359e-05 | 8638
WILKINS SLOUGH 11023066 | WILKINS SLOUGH 1102 | 62771102 |  | 19.125 | 1.8885 |  | 350.5 | 0.00035163 | 7112 | 0.073956 | 4561 | 2.5356e-05 | 8639
BIOLA 1103CB | BIOLA 1103 | 252211103 |  | 12.0403 | 1.6654 |  | 209.3333 | 0.00032757 | 7493 | 0.0774 | 3398 | 2.5354e-05 | 8640
CLARKSVILLE 211011142 | CLARKSVILLE 2110 | 153612110 |  | 3.4499 | 0.33578 |  | 74.5 | 0.00037672 | 6737 | 0.067414 | 5656 | 2.5314e-05 | 8641
KERMAN 1103R1570 | KERMAN 1103 | 252711103 |  | 12.1959 | 1.8092 |  | 219.5 | 0.00033243 | 7414 | 0.076386 | 4059 | 2.5298e-05 | 8642
LAMONT 11071988 | LAMONT 1107 | 253911107 |  | 3.7784 | 1.4498 |  | 57.5 | 0.00037203 | 6806 | 0.069797 | 5076 | 2.5294e-05 | 8643
CORCORAN 1118CB | CORCORAN 1118 | 252171118 |  | 12.2626 | 0.77786 |  | 219.0333 | 0.00033957 | 7315 | 0.075166 | 4389 | 2.5291e-05 | 8644
KEARNEY 1110251800 | KEARNEY 1110 | 252701110 |  | 22.1636 | 6.0448 |  | 430 | 0.00034453 | 7229 | 0.074157 | 4533 | 2.5286e-05 | 8645
MADISON 210137082 | MADISON 2101 | 63172101 |  | 4.4255 | 0.36349 |  | 92 | 0.00032012 | 7628 | 0.087871 | 3353 | 2.5285e-05 | 8646
WHEELER RIDGE 11024104 | WHEELER RIDGE 1102 | 253481102 |  | 2.3578 | 0.079098 |  | 39.5 | 0.00032665 | 7513 | 0.0774 | 3397 | 2.5283e-05 | 8647
ALPAUGH 1103CB | ALPAUGH 1103 | 254001103 |  | 5.6123 | 0.22575 |  | 106.1667 | 0.00034327 | 7253 | 0.074457 | 4490 | 2.5283e-05 | 8648
HORSESHOE 110250020 | HORSESHOE 1102 | 152571102 |  | 9.1167 | 0.47703 |  | 154.5 | 0.00037925 | 6704 | 0.066892 | 6097 | 2.5274e-05 | 8649
PEACHTON 1101633 | PEACHTON 1101 | 103241101 |  | 3.2106 | 0.54505 |  | 54.5 | 0.0003519 | 7109 | 0.073382 | 4626 | 2.5269e-05 | 8650
MC CALL 110766127 | MC CALL 1107 | 254121107 |  | 2.1463 | 0.60452 |  | 43.5 | 0.00032622 | 7516 | 0.0774 | 3397 | 2.5249e-05 | 8651
GRAND ISLAND 222318132 | GRAND ISLAND 2223 | 62462223 |  | 10.0872 | 2.1035 |  | 197.3333 | 0.00035344 | 7085 | 0.073306 | 4633 | 2.5243e-05 | 8652
CANAL 1102464575 | CANAL 1102 | 252091102 |  | 5.2958 | 0.649 |  | 94.5 | 0.00033052 | 7440 | 0.076461 | 4030 | 2.5241e-05 | 8653
KEARNEY 1104D1827 | KEARNEY 1104 | 252701104 |  | 2.2549 | 1.5853 |  | 39.5 | 0.0003519 | 7110 | 0.072383 | 4734 | 2.5236e-05 | 8654
MORMON 110296226 | MORMON 1102 | 163211102 |  | 0.1369 | 0 |  | 2.6667 | 0.00032576 | 7527 | 0.0774 | 3396 | 2.5213e-05 | 8655
CORDELIA 11128832 | CORDELIA 1112 | 62701112 |  | 6.3991 | 0.97499 |  | 122 | 0.0003631 | 6943 | 0.070053 | 5035 | 2.5213e-05 | 8656
GONZALES 1104CB | GONZALES 1104 | 182131104 |  | 16.8062 | 1.2422 |  | 347.75 | 0.0003738 | 6784 | 0.067493 | 5607 | 2.5211e-05 | 8657
KERMAN 1108R2686 | KERMAN 1108 | 252711108 |  | 13.9512 | 1.4074 |  | 241.5 | 0.000327 | 7505 | 0.077098 | 3693 | 2.521e-05 | 8658
JARVIS 1108289662 | JARVIS 1108 | 13501108 | TRUE | 0.81314 | 0.93469 | 0.58995 | 14.5 | 0.00038398 | 6653 | 0.062197 | 6745 | 2.5201e-05 | 8659
FIGARDEN 21104230 | FIGARDEN 2110 | 254552110 |  | 2.022 | 0.15047 |  | 47 | 0.00039831 | 6472 | 0.066379 | 6208 | 2.5195e-05 | 8660
OLD RIVER 1101CB | OLD RIVER 1101 | 252821101 |  | 12.1753 | 0.25554 |  | 174.25 | 0.00033147 | 7428 | 0.076337 | 4074 | 2.5193e-05 | 8661
STAGG 210411476 | STAGG 2104 | 162422104 |  | 1.2329 | 0.10798 |  | 25 | 0.00032546 | 7533 | 0.0774 | 3397 | 2.519e-05 | 8662
BAHIA 11031438 | BAHIA 1103 | 43251103 |  | 1.3648 | 0.12706 |  | 25 | 0.00037872 | 6714 | 0.066437 | 6197 | 2.519e-05 | 8663
FRENCH CAMP 1102CB | FRENCH CAMP 1102 | 163291102 |  | 18.6871 | 3.5128 |  | 327.1667 | 0.00034614 | 7203 | 0.074608 | 4473 | 2.5187e-05 | 8664
WEBER 11094920 | WEBER 1109 | 163481109 |  | 49.7885 | 4.1672 |  | 890.5 | 0.00034453 | 7228 | 0.074547 | 4482 | 2.5185e-05 | 8665
HIGHWAY 1102700 | HIGHWAY 1102 | 42651102 |  | 15.7863 | 1.6064 |  | 279 | 0.00039197 | 6543 | 0.065751 | 6314 | 2.518e-05 | 8666
CROWS LANDING 1102CB | CROWS LANDING 1102 | 163251102 |  | 7.518 | 0.3585 |  | 149 | 0.00033131 | 7433 | 0.076104 | 4162 | 2.5178e-05 | 8667
MERCED FALLS 11027905 | MERCED FALLS 1102 | 252811102 |  | 1.0946 | 0.093062 |  | 21.5 | 0.00037576 | 6752 | 0.067 | 6057 | 2.5176e-05 | 8668
REDBUD 11022013 | REDBUD 1102 | 43191102 | TRUE | 4.5994 | 3.1324 | 0.24299 | 61.5 | 0.00037671 | 6738 | 0.067076 | 5923 | 2.517e-05 | 8669
SPENCE 1104CB | SPENCE 1104 | 182201104 |  | 36.4476 | 2.4301 |  | 763.9167 | 0.00037437 | 6775 | 0.06724 | 5771 | 2.5155e-05 | 8670
ARCATA 110658538 | ARCATA 1106 | 192021106 |  | 2.8987 | 1.0087 |  | 51 | 0.00038837 | 6599 | 0.064841 | 6459 | 2.5155e-05 | 8671
WAHTOKE 111049396 | WAHTOKE 1110 | 254531110 |  | 1.5687 | 0.81777 |  | 29.5 | 0.00043345 | 6079 | 0.062023 | 6762 | 2.5148e-05 | 8672
ORLAND B 11022546 | ORLAND B 1102 | 102701102 |  | 10.5657 | 1.4493 |  | 181.5 | 0.00037518 | 6760 | 0.067303 | 5727 | 2.5147e-05 | 8673
ANGIOLA 1102CB | ANGIOLA 1102 | 252151102 |  | 9.2132 | 0.15247 |  | 151.8333 | 0.00035451 | 7065 | 0.071568 | 4819 | 2.5146e-05 | 8674
HOLLISTER 21034402 | HOLLISTER 2103 | 182492103 |  | 3.2786 | 1.1379 |  | 59 | 0.00040147 | 6435 | 0.064395 | 6496 | 2.5134e-05 | 8675
LE GRAND 11109630 | LE GRAND 1110 | 255361110 |  | 14.0115 | 2.8286 |  | 240 | 0.00035137 | 7119 | 0.071991 | 4777 | 2.5132e-05 | 8676
CAMDEN 1104753844 | CAMDEN 1104 | 252301104 |  | 2.1789 | 0.31076 |  | 43 | 0.00032466 | 7545 | 0.0774 | 3397 | 2.5128e-05 | 8677
OLIVEHURST 11011272 | OLIVEHURST 1101 | 152901101 |  | 6.9303 | 1.4152 |  | 121.8333 | 0.00034157 | 7282 | 0.075272 | 4371 | 2.5126e-05 | 8678
ROUGH AND READY ISLA 11022146 | ROUGH AND READY ISLA 1102 | 163081102 |  | 12.2575 | 1.5955 |  | 212 | 0.00033784 | 7340 | 0.074784 | 4445 | 2.5125e-05 | 8679
VALLEY HOME 170278842 | VALLEY HOME 1702 | 162981702 |  | 4.4999 | 0.21352 |  | 72 | 0.00035023 | 7138 | 0.073665 | 4585 | 2.5108e-05 | 8680
ATASCADERO 1101A22 | ATASCADERO 1101 | 182541101 | TRUE | 13.0788 | 5.6296 | 0.0053424 | 234.5 | 0.00033912 | 7324 | 0.074796 | 4443 | 2.5103e-05 | 8681
WAHTOKE 1108CB | WAHTOKE 1108 | 254531108 |  | 21.8008 | 2.6906 |  | 365.8333 | 0.00032924 | 7466 | 0.076632 | 3968 | 2.51e-05 | 8682
WILKINS SLOUGH 11036592 | WILKINS SLOUGH 1103 | 62771103 |  | 17.0882 | 0.56606 |  | 296.5 | 0.00032699 | 7506 | 0.076757 | 3904 | 2.5086e-05 | 8683
MESA 1104M40 | MESA 1104 | 182821104 |  | 4.2417 | 0.21236 |  | 76 | 0.00036578 | 6911 | 0.068984 | 5193 | 2.5085e-05 | 8684
ASHLAN AVE 1113313704 | ASHLAN AVE 1113 | 252051113 |  | 2.6259 | 0.68449 |  | 51.5 | 0.00035494 | 7056 | 0.072385 | 4733 | 2.5081e-05 | 8685
KEARNEY 111079554 | KEARNEY 1110 | 252701110 |  | 3.5614 | 1.0903 |  | 76 | 0.00034897 | 7160 | 0.074058 | 4548 | 2.5081e-05 | 8686
TAMARACK 1102CB | TAMARACK 1102 | 152291102 |  | 1.2938 | 0.43899 |  | 28.5 | 0.00037174 | 6813 | 0.067467 | 5623 | 2.5079e-05 | 8687
GREEN VALLEY 210136820 | GREEN VALLEY 2101 | 83192101 |  | 8.3691 | 1.4827 |  | 161 | 0.0003745 | 6773 | 0.066978 | 6070 | 2.5078e-05 | 8688
BUTTE 11042058 | BUTTE 1104 | 103081104 |  | 8.0592 | 2.5137 |  | 151.3333 | 0.00037199 | 6807 | 0.067552 | 5572 | 2.5051e-05 | 8689
BETHEL BANK 0401CB | BETHEL BANK 0401 | 18150401 |  | 0.77474 | 0 |  | 7.8333 | 0.00032344 | 7569 | 0.0774 | 3396 | 2.5034e-05 | 8690
PLEASANT GROVE 2110CUS18 | PLEASANT GROVE 2110 | 152442110 |  | 0.011098 | 0 |  | 0.5 | 0.00037362 | 6785 | 0.067 | 6057 | 2.5033e-05 | 8691
VACA DIXON 11065752 | VACA DIXON 1106 | 63591106 |  | 3.9422 | 0.64878 |  | 73 | 0.00036683 | 6885 | 0.06873 | 5235 | 2.5033e-05 | 8692
FIGARDEN 2113N40 | FIGARDEN 2113 | 254552113 |  | 5.0759 | 1.7845 |  | 97 | 0.00036678 | 6886 | 0.070393 | 4961 | 2.5032e-05 | 8693
JACOBS CORNER 1101CB | JACOBS CORNER 1101 | 254771101 |  | 12.9782 | 0.7849 |  | 219.5 | 0.000326 | 7520 | 0.076963 | 3788 | 2.5022e-05 | 8694
WAHTOKE 1111CB | WAHTOKE 1111 | 254531111 |  | 19.5443 | 3.3461 |  | 307.4167 | 0.00032838 | 7479 | 0.07684 | 3866 | 2.5018e-05 | 8695
CANAL 1102520064 | CANAL 1102 | 252091102 |  | 5.3795 | 0.78037 |  | 94.5 | 0.00033132 | 7432 | 0.075489 | 4340 | 2.5007e-05 | 8696
NORD 11042450 | NORD 1104 | 103071104 |  | 11.3802 | 3.1986 |  | 214 | 0.00036962 | 6846 | 0.068957 | 5198 | 2.4982e-05 | 8697
NEWMAN 110190300 | NEWMAN 1101 | 162741101 |  | 0.37011 | 0.044226 |  | 7.5 | 0.00034381 | 7241 | 0.070913 | 4903 | 2.498e-05 | 8698
REDWOOD CITY 11058992 | REDWOOD CITY 1105 | 24161105 |  | 0.90732 | 0.047405 |  | 17.3333 | 0.00037744 | 6732 | 0.066223 | 6228 | 2.498e-05 | 8699
JAMESON 110513392 | JAMESON 1105 | 63801105 |  | 2.7628 | 0.21252 |  | 54 | 0.00034936 | 7154 | 0.07183 | 4789 | 2.4979e-05 | 8700
MADERA 11125800 | MADERA 1112 | 252761112 |  | 0.28123 | 0 |  | 5.3333 | 0.00047062 | 5692 | 0.053073 | 8251 | 2.4977e-05 | 8701
AIRWAYS 1107CB | AIRWAYS 1107 | 252041107 |  | 13.1751 | 1.4639 |  | 228.3333 | 0.00032346 | 7567 | 0.077331 | 3431 | 2.4973e-05 | 8702
KNIGHTS LANDING 1101CB | KNIGHTS LANDING 1101 | 62721101 |  | 9.3336 | 0.12636 |  | 157.5 | 0.00032853 | 7476 | 0.076347 | 4070 | 2.4971e-05 | 8703
JAMESON 11057652 | JAMESON 1105 | 63801105 |  | 8.3828 | 1.6681 |  | 173 | 0.0003511 | 7120 | 0.072128 | 4765 | 2.4971e-05 | 8704
HONCUT 11015053 | HONCUT 1101 | 103211101 |  | 4.2221 | 0.48555 |  | 73 | 0.00032339 | 7570 | 0.077067 | 3719 | 2.4967e-05 | 8705
BIOLA 110437336 | BIOLA 1104 | 252211104 |  | 5.7902 | 1.032 |  | 106.5 | 0.00034328 | 7252 | 0.074142 | 4537 | 2.4963e-05 | 8706
BUTTE 11042400 | BUTTE 1104 | 103081104 |  | 11.5816 | 2.9025 |  | 212.3333 | 0.00037542 | 6757 | 0.06863 | 5254 | 2.4956e-05 | 8707
CARUTHERS 1102CB | CARUTHERS 1102 | 252371102 |  | 12.0659 | 0.22606 |  | 164.5833 | 0.00032272 | 7581 | 0.077353 | 3409 | 2.4952e-05 | 8708
HOLLISTER 21014900 | HOLLISTER 2101 | 182492101 |  | 4.3556 | 1.5655 |  | 76.5 | 0.00041237 | 6310 | 0.062379 | 6730 | 2.494e-05 | 8709
MC CALL 110848144 | MC CALL 1108 | 254121108 |  | 11.2065 | 2.487 |  | 219.5 | 0.0003287 | 7474 | 0.076259 | 4108 | 2.4916e-05 | 8710
MAXWELL 110545180 | MAXWELL 1105 | 62881105 |  | 8.7868 | 0.25224 |  | 144 | 0.00033573 | 7371 | 0.07447 | 4489 | 2.4913e-05 | 8711
DAVIS 111239408 | DAVIS 1112 | 62041112 |  | 0.033249 | 0 |  | 0.66667 | 0.00032182 | 7594 | 0.0774 | 3396 | 2.4909e-05 | 8712
HERDLYN 1102CB | HERDLYN 1102 | 163741102 |  | 16.5941 | 0.79243 |  | 314.3333 | 0.00035449 | 7066 | 0.070158 | 5008 | 2.4901e-05 | 8713
ALPAUGH 11048080 | ALPAUGH 1104 | 254001104 |  | 1.5166 | 0.030861 |  | 26.5 | 0.00032842 | 7478 | 0.075564 | 4322 | 2.4887e-05 | 8714
PACIFIC PIPE GRAPEVI 1101CB | PACIFIC PIPE GRAPEVI 1101 | 255441101 |  | 0.0072255 | 0 |  | 1 | 0.00036631 | 6898 | 0.067874 | 5450 | 2.4863e-05 | 8715
COLUSA 110144168 | COLUSA 1101 | 62021101 |  | 4.7153 | 0.49469 |  | 76.3333 | 0.00033482 | 7385 | 0.075859 | 4242 | 2.4857e-05 | 8716
ARCATA 1123CB | ARCATA 1123 | 192021123 |  | 5.9747 | 0.58762 |  | 100.25 | 0.00037728 | 6733 | 0.066246 | 6223 | 2.4855e-05 | 8717
ORTIGA 1106438684 | ORTIGA 1106 | 254311106 |  | 0.028767 | 0 |  | 1 | 0.00032099 | 7609 | 0.0774 | 3397 | 2.4845e-05 | 8718
LARKIN (Y) 1120CB | LARKIN (Y) 1120 | 22801120 |  | 0.01537 | 0.13883 |  | 4.5833 | 0.000468 | 5713 | 0.053073 | 8251 | 2.4838e-05 | 8719
WINDSOR 1101586 | WINDSOR 1101 | 43501101 |  | 2.2485 | 1.2806 |  | 51.6667 | 0.0003845 | 6642 | 0.064977 | 6437 | 2.4838e-05 | 8720
CLOVIS 110265614 | CLOVIS 1102 | 254081102 |  | 11.2854 | 0.72249 |  | 186.3333 | 0.00032481 | 7541 | 0.076905 | 3828 | 2.4837e-05 | 8721
ZAMORA 1105CB | ZAMORA 1105 | 63191105 |  | 15.1583 | 0.60428 |  | 255.3333 | 0.00032344 | 7568 | 0.076951 | 3796 | 2.4836e-05 | 8722
TRES VIAS 1101CB | TRES VIAS 1101 | 103251101 |  | 4.4719 | 0.23881 |  | 70 | 0.00033915 | 7323 | 0.073619 | 4593 | 2.4833e-05 | 8723
FELLOWS 210442100 | FELLOWS 2104 | 254242104 |  | 15.1564 | 0.22045 |  | 249.3333 | 0.00035199 | 7108 | 0.071712 | 4804 | 2.4831e-05 | 8724
TWISSELMAN 21054320 | TWISSELMAN 2105 | 254402105 |  | 6.8799 | 0.033505 |  | 122.5 | 0.00035929 | 6990 | 0.069337 | 5140 | 2.482e-05 | 8725
PLUMAS 1101CB | PLUMAS 1101 | 153731101 |  | 13.9672 | 0.59263 |  | 242.3333 | 0.00032139 | 7600 | 0.077335 | 3427 | 2.482e-05 | 8726
CLOVIS 1108402640 | CLOVIS 1108 | 254081108 |  | 9.9821 | 1.1017 |  | 180.3333 | 0.0003233 | 7574 | 0.077051 | 3732 | 2.4797e-05 | 8727
MIRABEL 1101831090 | MIRABEL 1101 | 42091101 |  | 0.033067 | 0 |  | 0.5 | 0.00036645 | 6894 | 0.067664 | 5520 | 2.4796e-05 | 8728
HORSESHOE 11061680 | HORSESHOE 1106 | 152571106 |  | 2.37 | 0.55274 |  | 44 | 0.00036999 | 6840 | 0.067013 | 6017 | 2.4792e-05 | 8729
LOGAN CREEK 210262032 | LOGAN CREEK 2102 | 103142102 |  | 19.6056 | 0.47159 |  | 329 | 0.00032882 | 7473 | 0.074588 | 4476 | 2.4789e-05 | 8730
GREEN VALLEY 210110976 | GREEN VALLEY 2101 | 83192101 |  | 26.6726 | 2.5474 |  | 493.5 | 0.00036946 | 6848 | 0.067136 | 5865 | 2.4787e-05 | 8731
LAMMERS 1105CB | LAMMERS 1105 | 162771105 |  | 1.7909 | 0.15693 |  | 26.8333 | 0.00037948 | 6702 | 0.066016 | 6269 | 2.4784e-05 | 8732
EMBARCADERO (Z) 1118CB | EMBARCADERO (Z) 1118 | 22871118 |  | 0.084835 | 0.24867 |  | 8.3333 | 0.00046693 | 5727 | 0.053073 | 8252 | 2.4781e-05 | 8733
CRESSEY 2103CB | CRESSEY 2103 | 254702103 |  | 14.8278 | 0.66309 |  | 277 | 0.00032098 | 7610 | 0.077312 | 3458 | 2.4781e-05 | 8734
FULTON 11054106 | FULTON 1105 | 42561105 |  | 4.841 | 0.35572 |  | 90 | 0.00036537 | 6915 | 0.067883 | 5444 | 2.4781e-05 | 8735
MC CALL 11066950 | MC CALL 1106 | 254121106 |  | 9.7029 | 2.0939 |  | 185.5 | 0.00032581 | 7525 | 0.076293 | 4092 | 2.477e-05 | 8736
ESQUON 1102CB | ESQUON 1102 | 102171102 |  | 15.2975 | 0.52965 |  | 270.3333 | 0.00035706 | 7020 | 0.070153 | 5009 | 2.4761e-05 | 8737
EAST NICOLAUS 1103CB | EAST NICOLAUS 1103 | 152151103 |  | 8.1766 | 0.64947 |  | 139 | 0.00032118 | 7604 | 0.077226 | 3558 | 2.4758e-05 | 8738
BUTTE 1103CB | BUTTE 1103 | 103081103 |  | 7.0649 | 0.26235 |  | 134.5 | 0.00036913 | 6855 | 0.068277 | 5339 | 2.4753e-05 | 8739
EL CAPITAN 11024030 | EL CAPITAN 1102 | 253881102 |  | 7.6854 | 0.62727 |  | 136.5 | 0.00037115 | 6823 | 0.071975 | 4778 | 2.4734e-05 | 8740
LIVINGSTON 11064900 | LIVINGSTON 1106 | 252261106 |  | 12.9851 | 1.1663 |  | 237.3333 | 0.00032567 | 7528 | 0.076499 | 4019 | 2.4732e-05 | 8741
VICTOR 110223754 | VICTOR 1102 | 163281102 |  | 12.9316 | 1.7035 |  | 209.8333 | 0.00031951 | 7639 | 0.0774 | 3398 | 2.473e-05 | 8742
SANTA MARIA 1110M138 | SANTA MARIA 1110 | 182671110 |  | 8.5592 | 3.6253 |  | 145.5 | 0.00040066 | 6447 | 0.063858 | 6563 | 2.4722e-05 | 8743
KINGSBURG 1111CB | KINGSBURG 1111 | 252241111 |  | 13.3839 | 2.6018 |  | 230.5833 | 0.00032062 | 7617 | 0.077083 | 3703 | 2.4717e-05 | 8744
PACIFICA 11015001 | PACIFICA 1101 | 22811101 | TRUE | 1.7039 | 0.083186 | 0.0042919 | 25.5 | 0.000398 | 6476 | 0.062634 | 6698 | 2.4706e-05 | 8745
NORD 11042202 | NORD 1104 | 103071104 |  | 16.7896 | 0.62759 |  | 264.5 | 0.0003566 | 7034 | 0.070839 | 4912 | 2.4701e-05 | 8746
CAYUCOS 1101CB | CAYUCOS 1101 | 182551101 |  | 5.055 | 2.1945 |  | 87.8333 | 0.00039665 | 6494 | 0.06373 | 6576 | 2.469e-05 | 8747
LEMOORE 11028290 | LEMOORE 1102 | 253601102 |  | 4.7834 | 1.5497 |  | 80.5 | 0.00038394 | 6655 | 0.065864 | 6295 | 2.4683e-05 | 8748
PRUNEDALE 11103080 | PRUNEDALE 1110 | 182961110 |  | 7.4721 | 1.0961 |  | 129 | 0.00036822 | 6868 | 0.067001 | 6050 | 2.4671e-05 | 8749
FIREBAUGH 1101CB | FIREBAUGH 1101 | 253471101 |  | 22.6425 | 1.0192 |  | 451.8333 | 0.00032736 | 7497 | 0.075692 | 4289 | 2.467e-05 | 8750
CAPAY 1102CB | CAPAY 1102 | 102111102 |  | 4.2627 | 0.56406 |  | 74 | 0.00036763 | 6877 | 0.067108 | 5889 | 2.4666e-05 | 8751
TRES PINOS 1111CB | TRES PINOS 1111 | 183221111 |  | 1.2503 | 0.41633 |  | 21.5 | 0.00036426 | 6926 | 0.067462 | 5627 | 2.4658e-05 | 8752
MC MULLIN 11066420 | MC MULLIN 1106 | 254411106 |  | 4.9894 | 0.72464 |  | 86 | 0.00031855 | 7659 | 0.0774 | 3397 | 2.4655e-05 | 8753
SAN JOAQUIN 111253186 | SAN JOAQUIN 1112 | 252361112 |  | 2.675 | 1.758 |  | 52.5 | 0.00042281 | 6197 | 0.060732 | 6923 | 2.4655e-05 | 8754
RIVERBANK 1716CB | RIVERBANK 1716 | 163191716 |  | 7.7004 | 0.93689 |  | 113.6667 | 0.00032238 | 7588 | 0.076805 | 3885 | 2.4651e-05 | 8755
CORTINA 110130192 | CORTINA 1101 | 63121101 |  | 0.28917 | 0 |  | 3 | 0.00036325 | 6941 | 0.068757 | 5229 | 2.4651e-05 | 8756
TYLER 1105CB | TYLER 1105 | 103571105 |  | 16.2904 | 1.2833 |  | 288.5 | 0.00037255 | 6796 | 0.066471 | 6190 | 2.4648e-05 | 8757
LOCKEFORD 210238342 | LOCKEFORD 2102 | 163682102 |  | 0.025478 | 0 |  | 1.3333 | 0.0003184 | 7662 | 0.0774 | 3396 | 2.4644e-05 | 8758
CORNING 11011624 | CORNING 1101 | 103331101 |  | 6.8969 | 0.1915 |  | 115 | 0.0003632 | 6942 | 0.068096 | 5385 | 2.4641e-05 | 8759
MARICOPA 1102CB | MARICOPA 1102 | 254211102 |  | 17.3413 | 1.4721 |  | 294 | 0.00036592 | 6906 | 0.067351 | 5700 | 2.4641e-05 | 8760
BOGUE 11062704 | BOGUE 1106 | 153781106 |  | 21.5747 | 3.3514 |  | 363.5 | 0.00034366 | 7245 | 0.074043 | 4551 | 2.464e-05 | 8761
BUENA VISTA 11023730 | BUENA VISTA 1102 | 182261102 |  | 6.8349 | 1.6028 |  | 133.5 | 0.00037217 | 6801 | 0.066395 | 6206 | 2.4635e-05 | 8762
MADISON 1103CB | MADISON 1103 | 63171103 |  | 16.0545 | 2.4949 |  | 286.5 | 0.00036435 | 6925 | 0.068804 | 5222 | 2.4629e-05 | 8763
LOS MOLINOS 110154804 | LOS MOLINOS 1101 | 103481101 |  | 0.22953 | 0 |  | 5.5 | 0.00036749 | 6881 | 0.067 | 6057 | 2.4622e-05 | 8764
EL CERRITO G 1111760530 | EL CERRITO G 1111 | 12501111 | TRUE | 1.2613 | 1.302 | 0.47908 | 18.25 | 0.00041884 | 6235 | 0.059936 | 7029 | 2.4614e-05 | 8765
WASCO 1102223060 | WASCO 1102 | 252961102 |  | 1.8439 | 0.24513 |  | 30.3333 | 0.00040399 | 6412 | 0.064349 | 6503 | 2.4611e-05 | 8766
WOODWARD 2107850960 | WOODWARD 2107 | 255292107 |  | 2.0943 | 0.15908 |  | 38 | 0.00036572 | 6912 | 0.067274 | 5749 | 2.4611e-05 | 8767
DOS PALOS 1101622694 | DOS PALOS 1101 | 254041101 |  | 5.3774 | 1.5063 |  | 93.5 | 0.00033214 | 7421 | 0.075426 | 4347 | 2.4609e-05 | 8768
OROSI 11017400 | OROSI 1101 | 252841101 |  | 7.7524 | 1.0576 |  | 138.5 | 0.00032188 | 7593 | 0.076651 | 3959 | 2.4592e-05 | 8769
MESA 110187454 | MESA 1101 | 182821101 |  | 0.064868 | 0 |  | 1.5 | 0.00036677 | 6888 | 0.067047 | 5951 | 2.4591e-05 | 8770
KERN OIL 1106CB | KERN OIL 1106 | 252721106 |  | 10.883 | 0.15283 |  | 146.25 | 0.00035084 | 7125 | 0.070304 | 4979 | 2.459e-05 | 8771
ZAMORA 11078892 | ZAMORA 1107 | 63191107 |  | 22.7561 | 2.791 |  | 399.5 | 0.00034283 | 7262 | 0.07261 | 4707 | 2.4588e-05 | 8772
NEWHALL 1109CB | NEWHALL 1109 | 254461109 |  | 6.9365 | 0.12427 |  | 114.5 | 0.00031953 | 7638 | 0.077119 | 3678 | 2.4587e-05 | 8773
PEACHTON 11021962 | PEACHTON 1102 | 103241102 |  | 12.6305 | 0.66152 |  | 220.3333 | 0.0003254 | 7534 | 0.075969 | 4206 | 2.4578e-05 | 8774
NORD 1104CB | NORD 1104 | 103071104 |  | 22.184 | 2.0228 |  | 386.8333 | 0.00034937 | 7153 | 0.070941 | 4901 | 2.4573e-05 | 8775
BRENTWOOD 21051494 | BRENTWOOD 2105 | 14592105 |  | 1.1337 | 0.48753 |  | 21.5 | 0.0003667 | 6889 | 0.067006 | 6027 | 2.4572e-05 | 8776
PLEASANT GROVE 211050516 | PLEASANT GROVE 2110 | 152442110 |  | 3.5685 | 0.55477 |  | 65.5 | 0.00037079 | 6827 | 0.066837 | 6113 | 2.4571e-05 | 8777
PEASE 11042292 | PEASE 1104 | 153751104 |  | 9.3241 | 1.1962 |  | 164 | 0.00032139 | 7599 | 0.076806 | 3882 | 2.457e-05 | 8778
SCHINDLER 1110CB | SCHINDLER 1110 | 252891110 |  | 12.6377 | 0.67967 |  | 195.5333 | 0.00035388 | 7077 | 0.071355 | 4849 | 2.4557e-05 | 8779
MENLO 11029018 | MENLO 1102 | 24131102 |  | 8.6224 | 1.9804 |  | 163 | 0.00036677 | 6887 | 0.067097 | 5901 | 2.4547e-05 | 8780
GERBER 1102CB | GERBER 1102 | 103391102 |  | 2.7223 | 0.25847 |  | 40.5 | 0.00036632 | 6897 | 0.067 | 6057 | 2.4543e-05 | 8781
WHEELER RIDGE 1101CB | WHEELER RIDGE 1101 | 253481101 |  | 22.0408 | 0.80929 |  | 371.1667 | 0.00034679 | 7194 | 0.071484 | 4834 | 2.454e-05 | 8782
GREEN VALLEY 210112130 | GREEN VALLEY 2101 | 83192101 |  | 11.9815 | 1.8668 |  | 247.3333 | 0.00036907 | 6857 | 0.066577 | 6176 | 2.4538e-05 | 8783
LEMOORE 11058770 | LEMOORE 1105 | 253601105 |  | 0.32979 | 0.024142 |  | 7.5 | 0.00031697 | 7678 | 0.0774 | 3397 | 2.4533e-05 | 8784
SAN LUIS OBISPO 1103191498 | SAN LUIS OBISPO 1103 | 182631103 | TRUE | 0.17289 | 0.11821 | 0.24078 | 3.5 | 0.00046205 | 5782 | 0.053073 | 8251 | 2.4522e-05 | 8785
SEMITROPIC 1106CB | SEMITROPIC 1106 | 252901106 |  | 6.2628 | 0.11566 |  | 91 | 0.00032208 | 7591 | 0.076692 | 3939 | 2.4517e-05 | 8786
RICE 11013102 | RICE 1101 | 62831101 |  | 3.2455 | 0.10974 |  | 55.5 | 0.00031673 | 7685 | 0.0774 | 3397 | 2.4515e-05 | 8787
MADERA 11199540 | MADERA 1119 | 252761119 |  | 41.8848 | 3.3684 |  | 733 | 0.00032599 | 7521 | 0.075756 | 4275 | 2.4515e-05 | 8788
TULARE LAKE 1104378350 | TULARE LAKE 1104 | 252951104 |  | 0.95218 | 0 |  | 15.8333 | 0.00036588 | 6907 | 0.067 | 6058 | 2.4514e-05 | 8789
AVENA 170113034 | AVENA 1701 | 163571701 |  | 11.2805 | 0.74075 |  | 191 | 0.00031788 | 7669 | 0.077104 | 3689 | 2.4513e-05 | 8790
WILSON 11039080 | WILSON 1103 | 254301103 |  | 15.4326 | 1.7188 |  | 260.3333 | 0.00034008 | 7304 | 0.073552 | 4605 | 2.4512e-05 | 8791
GRAND ISLAND 222412362 | GRAND ISLAND 2224 | 62462224 |  | 9.0087 | 0.11221 |  | 188 | 0.00031848 | 7660 | 0.077016 | 3753 | 2.4509e-05 | 8792
LIVE OAK 1101425666 | LIVE OAK 1101 | 153771101 |  | 0.40409 | 0.0063962 |  | 6.5 | 0.00046165 | 5789 | 0.053073 | 8251 | 2.4501e-05 | 8793
CHOWCHILLA 11036160 | CHOWCHILLA 1103 | 254101103 |  | 20.8905 | 0.84934 |  | 390 | 0.00032444 | 7549 | 0.075773 | 4270 | 2.45e-05 | 8794
FAMOSO 1101CB | FAMOSO 1101 | 252461101 |  | 12.9551 | 0.3752 |  | 193.3333 | 0.00032675 | 7511 | 0.075601 | 4312 | 2.4499e-05 | 8795
SANTA RITA 110266758 | SANTA RITA 1102 | 253541102 |  | 0.063993 | 0 |  | 1.5 | 0.00031651 | 7693 | 0.0774 | 3397 | 2.4498e-05 | 8796
EEL RIVER 1102CB | EEL RIVER 1102 | 192381102 |  | 8.1435 | 0.8027 |  | 150.3333 | 0.00036533 | 6916 | 0.067004 | 6031 | 2.4479e-05 | 8797
WOODLAND 11065842 | WOODLAND 1106 | 62031106 |  | 8.6739 | 0.2561 |  | 148.5 | 0.00032288 | 7579 | 0.075964 | 4209 | 2.4479e-05 | 8798
WEST FRESNO 1112448248 | WEST FRESNO 1112 | 253731112 |  | 1.671 | 0.32293 |  | 33.5 | 0.00033461 | 7387 | 0.072467 | 4720 | 2.4466e-05 | 8799
CHARCA 1106252004 | CHARCA 1106 | 254501106 |  | 11.065 | 0.61905 |  | 186.5 | 0.0003248 | 7542 | 0.075927 | 4220 | 2.4462e-05 | 8800
CARLOTTA 1121CB | CARLOTTA 1121 | 192291121 | FALSE | 19.4081 | 2.3525 | 0.6511 | 361 | 0.00021797 | 9731 | 0.13331 | 3245 | 2.4461e-05 | 8801
BELLE HAVEN 110538302 | BELLE HAVEN 1105 | 24021105 |  | 3.3422 | 3.031 |  | 43.3333 | 0.00046086 | 5800 | 0.053073 | 8250 | 2.4459e-05 | 8802
SAN JOAQUIN 1106CB | SAN JOAQUIN 1106 | 252361106 |  | 7.4021 | 0.83905 |  | 105.8333 | 0.00033205 | 7423 | 0.074478 | 4487 | 2.4449e-05 | 8803
DEL MAR 11032702 | DEL MAR 1103 | 152581103 |  | 7.8134 | 1.4515 |  | 131.5 | 0.00036466 | 6923 | 0.067001 | 6049 | 2.4433e-05 | 8804
JAMESON 1103CB | JAMESON 1103 | 63801103 |  | 5.5995 | 0.11769 |  | 110 | 0.00034927 | 7157 | 0.070163 | 5006 | 2.4427e-05 | 8805
EAST NICOLAUS 11011266 | EAST NICOLAUS 1101 | 152151101 |  | 15.2077 | 1.3353 |  | 292.5 | 0.00031936 | 7642 | 0.076823 | 3874 | 2.4426e-05 | 8806
LIVE OAK 11041292 | LIVE OAK 1104 | 153771104 |  | 3.3088 | 0.69269 |  | 55 | 0.0004008 | 6445 | 0.065679 | 6329 | 2.4424e-05 | 8807
NEWBURG 11326576 | NEWBURG 1132 | 192151132 |  | 4.406 | 2.9852 |  | 68.8333 | 0.00042623 | 6157 | 0.057322 | 7392 | 2.4419e-05 | 8808
STOREY 1111CB | STOREY 1111 | 254611111 |  | 19.922 | 4.9129 |  | 364 | 0.00035045 | 7135 | 0.070411 | 4958 | 2.4417e-05 | 8809
GUERNSEY 1104CB | GUERNSEY 1104 | 252661104 |  | 8.8954 | 0.53609 |  | 131.0333 | 0.00032094 | 7612 | 0.076537 | 4003 | 2.4413e-05 | 8810
NEW HOPE 1101CB | NEW HOPE 1101 | 162081101 |  | 20.8813 | 3.4396 |  | 375 | 0.00033243 | 7415 | 0.07503 | 4410 | 2.441e-05 | 8811
GATES 1101CB | GATES 1101 | 253931101 |  | 8.664 | 0.51097 |  | 141.8333 | 0.00035692 | 7025 | 0.06924 | 5154 | 2.4402e-05 | 8812
ARVIN 1103CB | ARVIN 1103 | 253801103 |  | 20.5742 | 0.6043 |  | 347 | 0.00033317 | 7405 | 0.073638 | 4590 | 2.4396e-05 | 8813
PARLIER 1104184200 | PARLIER 1104 | 252291104 |  | 12.8496 | 3.4394 |  | 232.3333 | 0.0003229 | 7578 | 0.076059 | 4178 | 2.4387e-05 | 8814
EL NIDO 1101CB | EL NIDO 1101 | 252451101 |  | 11.3537 | 0.94977 |  | 188.5 | 0.00031574 | 7702 | 0.077271 | 3516 | 2.4385e-05 | 8815
VACA DIXON 11059792 | VACA DIXON 1105 | 63591105 | FALSE | 27.4799 | 1.8673 | 0.84658 | 475 | 0.0002279 | 9536 | 0.13871 | 3235 | 2.4384e-05 | 8816
MC FARLAND 1104CB | MC FARLAND 1104 | 253181104 |  | 7.6074 | 0.24314 |  | 126.75 | 0.00031777 | 7671 | 0.076892 | 3836 | 2.4381e-05 | 8817
FULTON 110555802 | FULTON 1105 | 42561105 |  | 0.16879 | 0.0045767 |  | 3.5 | 0.00036253 | 6957 | 0.06724 | 5772 | 2.4377e-05 | 8818
WHEELER RIDGE 11014164 | WHEELER RIDGE 1101 | 253481101 |  | 4.5476 | 0.038718 |  | 76 | 0.00031919 | 7645 | 0.07644 | 4039 | 2.4373e-05 | 8819
BOWLES 1101CB | BOWLES 1101 | 253531101 |  | 14.9088 | 2.3081 |  | 265.3333 | 0.00031562 | 7705 | 0.077249 | 3538 | 2.4372e-05 | 8820
ESQUON 11022490 | ESQUON 1102 | 102171102 |  | 2.842 | 0.31722 |  | 46.5 | 0.00036145 | 6965 | 0.067447 | 5638 | 2.4359e-05 | 8821
ATWATER 1103CB | ATWATER 1103 | 253611103 |  | 18.1269 | 6.3909 |  | 334.0833 | 0.00035992 | 6984 | 0.069949 | 5058 | 2.4353e-05 | 8822
STOREY 110934630 | STOREY 1109 | 254611109 |  | 5.3036 | 0.63412 |  | 97.8333 | 0.00032438 | 7550 | 0.076187 | 4134 | 2.4345e-05 | 8823
EL PECO 11025090 | EL PECO 1102 | 253981102 |  | 17.8487 | 1.3107 |  | 300 | 0.00031692 | 7681 | 0.076913 | 3819 | 2.4334e-05 | 8824
GABILAN 1101CB | GABILAN 1101 | 182331101 |  | 5.3325 | 0.47993 |  | 98.5 | 0.00036262 | 6953 | 0.067053 | 5943 | 2.4329e-05 | 8825
LODI 11026130 | LODI 1102 | 162111102 |  | 21.731 | 1.1721 |  | 360 | 0.00031475 | 7721 | 0.077312 | 3456 | 2.4329e-05 | 8826
KERMAN 1103R1580 | KERMAN 1103 | 252711103 |  | 11.722 | 2.0579 |  | 212 | 0.00031865 | 7656 | 0.076293 | 4093 | 2.4328e-05 | 8827
CASSIDY 21089520 | CASSIDY 2108 | 254272108 |  | 7.6173 | 0.41294 |  | 133.3333 | 0.00034937 | 7152 | 0.069997 | 5047 | 2.4324e-05 | 8828
BLUE LAKE 1102CB | BLUE LAKE 1102 | 192181102 |  | 20.5385 | 4.7202 |  | 355 | 0.0003686 | 6864 | 0.066011 | 6272 | 2.4323e-05 | 8829
SANTA RITA 1102CB | SANTA RITA 1102 | 253541102 |  | 12.3912 | 0.9426 |  | 210 | 0.00032113 | 7607 | 0.075874 | 4238 | 2.4322e-05 | 8830
ROUGH AND READY ISLA 11025726 | ROUGH AND READY ISLA 1102 | 163081102 |  | 33.0206 | 1.7569 |  | 600 | 0.00032694 | 7508 | 0.075528 | 4333 | 2.4297e-05 | 8831
MERCED 11149040 | MERCED 1114 | 252801114 |  | 7.9289 | 0.3884 |  | 138 | 0.00033302 | 7407 | 0.074435 | 4496 | 2.4292e-05 | 8832
MORMON 110136806 | MORMON 1101 | 163211101 |  | 31.1572 | 5.1045 |  | 558.3333 | 0.00032417 | 7556 | 0.076057 | 4180 | 2.4292e-05 | 8833
BELLE HAVEN 0403CB | BELLE HAVEN 0403 | 24020403 |  | 5.5076 | 2.5525 |  | 92.3333 | 0.00043381 | 6073 | 0.057025 | 7434 | 2.4292e-05 | 8834
ECHO SUMMIT 1101927328 | ECHO SUMMIT 1101 | 158031101 |  | 1.8729 | 1.2256 |  | 47 | 0.00035934 | 6989 | 0.067531 | 5585 | 2.4289e-05 | 8835
RIPON 1701723166 | RIPON 1701 | 163801701 |  | 25.2651 | 2.0438 |  | 439 | 0.00032557 | 7530 | 0.075762 | 4274 | 2.4287e-05 | 8836
VALLEY HOME 1704CB | VALLEY HOME 1704 | 162981704 |  | 29.4112 | 2.4311 |  | 523.8333 | 0.00031672 | 7686 | 0.07686 | 3849 | 2.4273e-05 | 8837
OLD RIVER 1103CB | OLD RIVER 1103 | 252821103 |  | 6.6486 | 0.26509 |  | 89.9167 | 0.00032081 | 7616 | 0.075897 | 4232 | 2.4272e-05 | 8838
HONCUT 1101CB | HONCUT 1101 | 103211101 |  | 4.2541 | 0.29142 |  | 68 | 0.00032486 | 7539 | 0.076029 | 4193 | 2.4264e-05 | 8839
NEWBURG 113277894 | NEWBURG 1132 | 192151132 |  | 3.9042 | 1.2898 |  | 70.3333 | 0.00037648 | 6742 | 0.064781 | 6466 | 2.4259e-05 | 8840
WYANDOTTE 110940608 | WYANDOTTE 1109 | 102911109 |  | 8.5325 | 2.3248 |  | 145.5 | 0.00036355 | 6934 | 0.06708 | 5919 | 2.4254e-05 | 8841
SF L 0403CB | SF L 0403 | 22260403 |  | 0.2288 | 0.31208 |  | 10 | 0.00045693 | 5847 | 0.053073 | 8251 | 2.425e-05 | 8842
COTATI 1105616 | COTATI 1105 | 42271105 | FALSE | 30.6303 | 1.9401 | 2.7158 | 579.5 | 0.00015486 | 10647 | 0.11842 | 3269 | 2.4246e-05 | 8843
CORONA 110137424 | CORONA 1101 | 43491101 |  | 13.3151 | 5.2832 |  | 251.5 | 0.00036159 | 6964 | 0.067207 | 5801 | 2.4241e-05 | 8844
REEDLEY 111246926 | REEDLEY 1112 | 252341112 |  | 12.2182 | 3.9656 |  | 222 | 0.00036028 | 6978 | 0.068752 | 5230 | 2.4212e-05 | 8845
BRENTWOOD 2112K525R | BRENTWOOD 2112 | 14592112 |  | 3.9439 | 1.0033 |  | 79 | 0.00031905 | 7650 | 0.07664 | 3964 | 2.4186e-05 | 8846
PRUNEDALE 111020059 | PRUNEDALE 1110 | 182961110 |  | 0.25904 | 0.055818 |  | 4.5 | 0.00036064 | 6973 | 0.067016 | 6010 | 2.417e-05 | 8847
EL CAPITAN 110310910 | EL CAPITAN 1103 | 253881103 |  | 13.64 | 2.9962 |  | 238.5 | 0.00031341 | 7749 | 0.077181 | 3611 | 2.4163e-05 | 8848
STROUD 1101848548 | STROUD 1101 | 253661101 |  | 0.01653 | 0 |  | 0.5 | 0.00031202 | 7768 | 0.0774 | 3397 | 2.415e-05 | 8849
NEWARK 12KV 1104CB | NEWARK 12KV 1104 | 12221104 |  | 0.24743 | 0.071505 |  | 5.1667 | 0.00040222 | 6425 | 0.057781 | 7327 | 2.4148e-05 | 8850
CATLETT 1105CB | CATLETT 1105 | 153761105 |  | 11.4662 | 0.70282 |  | 194 | 0.00031219 | 7766 | 0.077359 | 3405 | 2.4148e-05 | 8851
FIGARDEN 2102D2872 | FIGARDEN 2102 | 254552102 |  | 0.73951 | 0.26759 |  | 19 | 0.00036624 | 6899 | 0.066969 | 6075 | 2.4145e-05 | 8852
KERMAN 1101CB | KERMAN 1101 | 252711101 |  | 17.4407 | 1.6799 |  | 289.0333 | 0.00031192 | 7770 | 0.0774 | 3397 | 2.4142e-05 | 8853
MERCED FALLS 11027006 | MERCED FALLS 1102 | 252811102 |  | 4.8083 | 0.13636 |  | 88.5 | 0.00034816 | 7171 | 0.069521 | 5118 | 2.4135e-05 | 8854
BALFOUR 1101227486 | BALFOUR 1101 | 14321101 |  | 4.4336 | 0.33178 |  | 73.8333 | 0.00032045 | 7621 | 0.075731 | 4281 | 2.4112e-05 | 8855
STOCKDALE 21122858 | STOCKDALE 2112 | 254072112 |  | 20.8031 | 1.658 |  | 340 | 0.00031492 | 7718 | 0.076752 | 3907 | 2.4111e-05 | 8856
BOWLES 1102CB | BOWLES 1102 | 253531102 |  | 8.6124 | 1.6354 |  | 153.3333 | 0.00031231 | 7763 | 0.077269 | 3518 | 2.4089e-05 | 8857
TRES VIAS 11015673 | TRES VIAS 1101 | 103251101 |  | 9.0249 | 0.31789 |  | 155.5 | 0.00031245 | 7759 | 0.077087 | 3701 | 2.4087e-05 | 8858
FITCH MOUNTAIN 1111424 | FITCH MOUNTAIN 1111 | 42751111 |  | 8.5521 | 0.58313 |  | 160.5 | 0.00035897 | 6997 | 0.06714 | 5861 | 2.4084e-05 | 8859
MALAGA 110272042 | MALAGA 1102 | 254251102 |  | 22.683 | 4.3576 |  | 434 | 0.00031406 | 7736 | 0.076935 | 3804 | 2.4084e-05 | 8860
MADISON 21017702 | MADISON 2101 | 63172101 |  | 18.6917 | 1.9226 |  | 371 | 0.00029514 | 8105 | 0.086131 | 3364 | 2.4083e-05 | 8861
RIPON 170213546 | RIPON 1702 | 163801702 |  | 8.6454 | 0.79089 |  | 152.5 | 0.00034776 | 7178 | 0.072441 | 4721 | 2.4081e-05 | 8862
SCE MCFARLAND 1101CB | SCE MCFARLAND 1101 | 258111101 |  | 0.48084 | 0.016281 |  | 9 | 0.00031105 | 7786 | 0.0774 | 3397 | 2.4075e-05 | 8863
WHEELER RIDGE 110183646 | WHEELER RIDGE 1101 | 253481101 |  | 5.7359 | 0.14219 |  | 101.5 | 0.00032977 | 7452 | 0.073364 | 4628 | 2.4068e-05 | 8864
DAIRYVILLE 1101CB | DAIRYVILLE 1101 | 103341101 |  | 15.8081 | 1.838 |  | 304 | 0.00035614 | 7042 | 0.068182 | 5363 | 2.4068e-05 | 8865
OLIVEHURST 11031238 | OLIVEHURST 1103 | 152901103 |  | 22.4424 | 2.4831 |  | 375.5 | 0.00031964 | 7636 | 0.07603 | 4192 | 2.4063e-05 | 8866
REEDLEY 111297364 | REEDLEY 1112 | 252341112 |  | 22.6295 | 8.6113 |  | 409 | 0.00035743 | 7016 | 0.068802 | 5223 | 2.4058e-05 | 8867
CASTROVILLE 210370782 | CASTROVILLE 2103 | 182352103 |  | 7.6338 | 0.11481 |  | 157.5 | 0.00035418 | 7071 | 0.067919 | 5430 | 2.4058e-05 | 8868
LOGAN CREEK 21012404 | LOGAN CREEK 2101 | 103142101 |  | 14.502 | 0.5819 |  | 240.5 | 0.00031416 | 7735 | 0.076903 | 3829 | 2.4058e-05 | 8869
MADERA 11196450 | MADERA 1119 | 252761119 |  | 16.6302 | 1.2187 |  | 276 | 0.00031128 | 7780 | 0.077312 | 3458 | 2.4055e-05 | 8870
WILLIAMS 110230242 | WILLIAMS 1102 | 62051102 |  | 11.6034 | 3.9647 |  | 198.5 | 0.00035992 | 6983 | 0.070129 | 5013 | 2.4048e-05 | 8871
LAMONT 11071952 | LAMONT 1107 | 253911107 |  | 6.521 | 0.34995 |  | 114.5 | 0.00031978 | 7633 | 0.075554 | 4325 | 2.4037e-05 | 8872
COLUSA 11013504 | COLUSA 1101 | 62021101 |  | 13.971 | 0.45625 |  | 252 | 0.00031667 | 7689 | 0.076372 | 4063 | 2.4031e-05 | 8873
BANTA 110169196 | BANTA 1101 | 162471101 |  | 19.205 | 1.6237 |  | 321 | 0.00031918 | 7646 | 0.075563 | 4323 | 2.403e-05 | 8874
KNIGHTS LANDING 11028432 | KNIGHTS LANDING 1102 | 62721102 |  | 8.9973 | 0.38756 |  | 171.5 | 0.00031098 | 7787 | 0.077308 | 3465 | 2.4027e-05 | 8875
COLUMBUS 1109CUS3980 | COLUMBUS 1109 | 253951109 |  | 0.017666 | 0 |  | 0.5 | 0.00035651 | 7037 | 0.067385 | 5679 | 2.4023e-05 | 8876
BAHIA 1104CUS8929 | BAHIA 1104 | 43251104 |  | 0.0090748 | 0 |  | 0.33333 | 0.00035782 | 7010 | 0.067105 | 5893 | 2.4011e-05 | 8877
REEDLEY 110676043 | REEDLEY 1106 | 252341106 |  | 15.8757 | 3.9076 |  | 301.5 | 0.00031421 | 7734 | 0.076731 | 3919 | 2.4008e-05 | 8878
LODI 110112190 | LODI 1101 | 162111101 |  | 9.7949 | 1.2823 |  | 176.5 | 0.00031016 | 7802 | 0.0774 | 3397 | 2.4006e-05 | 8879
CASSIDY 21079500 | CASSIDY 2107 | 254272107 |  | 13.8466 | 1.1361 |  | 210 | 0.0003912 | 6554 | 0.063816 | 6567 | 2.3987e-05 | 8880
LODI 110212596 | LODI 1102 | 162111102 |  | 9.1994 | 0.35213 |  | 162 | 0.00031036 | 7801 | 0.077325 | 3435 | 2.3985e-05 | 8881
WILSON 110310690 | WILSON 1103 | 254301103 |  | 6.9173 | 0.45287 |  | 120 | 0.0003241 | 7558 | 0.075068 | 4405 | 2.3981e-05 | 8882
CONTRA COSTA 210929718 | CONTRA COSTA 2109 | 13652109 |  | 0.34317 | 0 |  | 5.3333 | 0.00035784 | 7009 | 0.067004 | 6032 | 2.3978e-05 | 8883
LERDO 11111606 | LERDO 1111 | 253491111 |  | 10.9889 | 0.36782 |  | 177 | 0.00037324 | 6790 | 0.070075 | 5027 | 2.3975e-05 | 8884
PARLIER 110480102 | PARLIER 1104 | 252291104 |  | 0.06767 | 0 |  | 0.83333 | 0.00045173 | 5905 | 0.053073 | 8250 | 2.3974e-05 | 8885
WAHTOKE 1111CUS4140 | WAHTOKE 1111 | 254531111 |  | 0.0076912 | 0 |  | 0.83333 | 0.00030971 | 7809 | 0.0774 | 3396 | 2.3972e-05 | 8886
LOS OSITOS 210364348 | LOS OSITOS 2103 | 182082103 |  | 6.6289 | 0.41413 |  | 128.5 | 0.00035723 | 7018 | 0.067026 | 5992 | 2.3967e-05 | 8887
GABILAN 1101270626 | GABILAN 1101 | 182331101 |  | 2.494 | 0.10859 |  | 50 | 0.00035926 | 6991 | 0.066721 | 6133 | 2.3967e-05 | 8888
TEMPLETON 2113848137 | TEMPLETON 2113 | 183052113 |  | 0.05712 | 0 |  | 1 | 0.00035693 | 7024 | 0.067122 | 5881 | 2.3966e-05 | 8889
BLACKWELL 2101CB | BLACKWELL 2101 | 254682101 |  | 6.7411 | 0.14352 |  | 110.5 | 0.00035655 | 7036 | 0.067188 | 5823 | 2.3964e-05 | 8890
ANGIOLA 1103CB | ANGIOLA 1103 | 252151103 |  | 10.3547 | 0.1144 |  | 168.8333 | 0.00033576 | 7368 | 0.071571 | 4816 | 2.3963e-05 | 8891
OLEMA 110149756 | OLEMA 1101 | 42291101 | FALSE | 5.8548 | 0.60995 | 1.0419 | 109.5 | 0.00028005 | 8421 | 0.10896 | 3294 | 2.3962e-05 | 8892
DAIRYLAND 11135690 | DAIRYLAND 1113 | 252421113 |  | 8.893 | 0.40421 |  | 152.5 | 0.00030995 | 7805 | 0.07724 | 3545 | 2.396e-05 | 8893
DAVIS 11019702 | DAVIS 1101 | 62041101 |  | 17.0025 | 0.8702 |  | 302.5 | 0.00031841 | 7661 | 0.075905 | 4230 | 2.3958e-05 | 8894
TERMINOUS 1103CB | TERMINOUS 1103 | 163021103 |  | 28.8109 | 2.1872 |  | 498.8333 | 0.00031474 | 7723 | 0.076388 | 4058 | 2.3949e-05 | 8895
DINUBA 110476483 | DINUBA 1104 | 254091104 |  | 1.842 | 1.3563 |  | 33.5 | 0.00030936 | 7816 | 0.0774 | 3397 | 2.3945e-05 | 8896
BANTA 110179924 | BANTA 1101 | 162471101 |  | 8.4063 | 0.94465 |  | 174.5 | 0.00033142 | 7430 | 0.073345 | 4630 | 2.3936e-05 | 8897
OLD RIVER 1101583328 | OLD RIVER 1101 | 252821101 |  | 0.098714 | 0 |  | 1.5 | 0.00030905 | 7822 | 0.0774 | 3397 | 2.3921e-05 | 8898
BOWLES 110494802 | BOWLES 1104 | 253531104 |  | 14.2511 | 2.4528 |  | 256 | 0.00030965 | 7812 | 0.077182 | 3610 | 2.3913e-05 | 8899
SHAFTER 110266660 | SHAFTER 1102 | 253651102 |  | 10.3628 | 0.53913 |  | 175.5 | 0.00031072 | 7792 | 0.077082 | 3705 | 2.3908e-05 | 8900
MC CALL 11086540 | MC CALL 1108 | 254121108 |  | 13.2173 | 3.6327 |  | 239 | 0.00031242 | 7762 | 0.076735 | 3918 | 2.3906e-05 | 8901
RICE 1104CB | RICE 1104 | 62831104 |  | 5.4595 | 0.34262 |  | 100.3333 | 0.00032024 | 7625 | 0.075444 | 4344 | 2.3905e-05 | 8902
KEARNEY 110493554 | KEARNEY 1104 | 252701104 |  | 20.497 | 4.2562 |  | 377 | 0.00031171 | 7774 | 0.076842 | 3863 | 2.3901e-05 | 8903
NAPA 11025039 | NAPA 1102 | 42021102 | TRUE | 2.6378 | 0.087886 | 0.001046 | 54 | 0.00035503 | 7054 | 0.067318 | 5716 | 2.3898e-05 | 8904
GEYSERVILLE 1102331444 | GEYSERVILLE 1102 | 42891102 |  | 1.735 | 0.10764 |  | 32 | 0.00035157 | 7113 | 0.068481 | 5291 | 2.3892e-05 | 8905
SANTA MARIA 1109600274 | SANTA MARIA 1109 | 182671109 |  | 1.0178 | 0.071922 |  | 17.5 | 0.00036094 | 6968 | 0.066204 | 6234 | 2.3891e-05 | 8906
CORCORAN 1108954978 | CORCORAN 1108 | 252171108 |  | 9.9257 | 2.8862 |  | 174.5 | 0.00033413 | 7393 | 0.072799 | 4685 | 2.388e-05 | 8907
LEMOORE 110153572 | LEMOORE 1101 | 253601101 |  | 6.1131 | 0.58136 |  | 104 | 0.0003227 | 7582 | 0.075996 | 4199 | 2.3876e-05 | 8908
KNIGHTS LANDING 11027752 | KNIGHTS LANDING 1102 | 62721102 |  | 15.3212 | 0.41225 |  | 283 | 0.00032026 | 7624 | 0.075208 | 4386 | 2.3874e-05 | 8909
JACOBS CORNER 110137362 | JACOBS CORNER 1101 | 254771101 |  | 4.6777 | 0.44484 |  | 81 | 0.00031597 | 7698 | 0.075103 | 4401 | 2.3859e-05 | 8910
SAN LEANDRO U 1107MR217 | SAN LEANDRO U 1107 | 13111107 |  | 2.2606 | 2.893 |  | 43.3333 | 0.00044946 | 5923 | 0.053073 | 8251 | 2.3854e-05 | 8911
CARUTHERS 1101CB | CARUTHERS 1101 | 252371101 |  | 17.3858 | 1.6687 |  | 293.25 | 0.00030858 | 7828 | 0.077332 | 3430 | 2.3854e-05 | 8912
KINGSBURG 1108CB | KINGSBURG 1108 | 252241108 |  | 11.8989 | 2.7233 |  | 221.7 | 0.00030817 | 7841 | 0.0774 | 3397 | 2.3852e-05 | 8913
MENLO 1102362896 | MENLO 1102 | 24131102 |  | 0.14506 | 0 |  | 2.5 | 0.0003471 | 7188 | 0.068713 | 5240 | 2.385e-05 | 8914
LOS MOLINOS 110163998 | LOS MOLINOS 1101 | 103481101 |  | 15.3202 | 0.94576 |  | 262 | 0.00035343 | 7086 | 0.067442 | 5645 | 2.3842e-05 | 8915
SPENCE 1102276712 | SPENCE 1102 | 182201102 |  | 21.3055 | 1.1549 |  | 431.1667 | 0.00035453 | 7064 | 0.067202 | 5809 | 2.383e-05 | 8916
LE GRAND 11104600 | LE GRAND 1110 | 255361110 |  | 6.6092 | 1.3164 |  | 106.5 | 0.00033418 | 7392 | 0.072946 | 4669 | 2.3827e-05 | 8917
ALPAUGH 1104CB | ALPAUGH 1104 | 254001104 |  | 15.2898 | 0.45307 |  | 288.8333 | 0.0003294 | 7462 | 0.073025 | 4661 | 2.3809e-05 | 8918
RICE 1101CB | RICE 1101 | 62831101 |  | 8.2986 | 0.67491 |  | 131.8333 | 0.00032902 | 7469 | 0.074695 | 4459 | 2.3808e-05 | 8919
EL PECO 110690030 | EL PECO 1106 | 253981106 |  | 10.4142 | 1.2695 |  | 174 | 0.00030908 | 7820 | 0.07698 | 3776 | 2.3803e-05 | 8920
CHOWCHILLA 110184058 | CHOWCHILLA 1101 | 254101101 |  | 17.5727 | 1.9252 |  | 339 | 0.0003122 | 7765 | 0.076267 | 4103 | 2.3796e-05 | 8921
BERKELEY F 1102CB | BERKELEY F 1102 | 12061102 |  | 0.03903 | 0.069744 |  | 2.1667 | 0.00044836 | 5929 | 0.053073 | 8250 | 2.3796e-05 | 8922
BUTTE 11032208 | BUTTE 1103 | 103081103 |  | 22.6654 | 3.3395 |  | 380.5 | 0.0003506 | 7129 | 0.068363 | 5311 | 2.3787e-05 | 8923
HIGHWAY 1102815524 | HIGHWAY 1102 | 42651102 |  | 1.4652 | 0.049834 |  | 27.5 | 0.00035675 | 7030 | 0.066771 | 6127 | 2.3785e-05 | 8924
RIPON 17036176 | RIPON 1703 | 163801703 |  | 40.452 | 3.3412 |  | 732 | 0.00031062 | 7794 | 0.076694 | 3937 | 2.377e-05 | 8925
SANGER 1108CB | SANGER 1108 | 252351108 |  | 13.5239 | 2.212 |  | 235.8333 | 0.00030802 | 7846 | 0.077297 | 3477 | 2.3768e-05 | 8926
POINT ARENA 1101478 | POINT ARENA 1101 | 43381101 |  | 1.6417 | 0.1257 |  | 28.5 | 0.00035352 | 7082 | 0.067214 | 5794 | 2.3764e-05 | 8927
SISQUOC 1104675420 | SISQUOC 1104 | 182811104 |  | 5.4911 | 0.53712 |  | 92 | 0.00034626 | 7202 | 0.068583 | 5264 | 2.3758e-05 | 8928
MORGAN HILL 210653992 | MORGAN HILL 2106 | 83242106 |  | 23.5654 | 6.1378 |  | 455.8333 | 0.0003563 | 7039 | 0.066801 | 6121 | 2.3754e-05 | 8929
MORMON 110214686 | MORMON 1102 | 163211102 |  | 8.2084 | 0.53398 |  | 157 | 0.00031535 | 7709 | 0.07565 | 4298 | 2.3746e-05 | 8930
RIO DELL 110138332 | RIO DELL 1101 | 192251101 |  | 2.0467 | 1.4 |  | 36 | 0.00036336 | 6940 | 0.064769 | 6468 | 2.374e-05 | 8931
KERMAN 1103671860 | KERMAN 1103 | 252711103 |  | 0.89614 | 0.060084 |  | 15.5 | 0.000335 | 7381 | 0.071122 | 4881 | 2.3738e-05 | 8932
CROWS LANDING 1101CB | CROWS LANDING 1101 | 163251101 |  | 3.0058 | 0.036255 |  | 45.5 | 0.00030753 | 7854 | 0.077286 | 3494 | 2.3736e-05 | 8933
TEMBLOR 11041034 | TEMBLOR 1104 | 252551104 |  | 7.4506 | 0 |  | 140.5 | 0.00035529 | 7049 | 0.066849 | 6109 | 2.3736e-05 | 8934
MADERA 11195820 | MADERA 1119 | 252761119 |  | 11.5022 | 0.81508 |  | 199 | 0.00030855 | 7830 | 0.076976 | 3779 | 2.3731e-05 | 8935
ARBUCKLE 110430012 | ARBUCKLE 1104 | 62081104 |  | 0.88219 | 0.019592 |  | 15.5 | 0.00032484 | 7540 | 0.074381 | 4506 | 2.373e-05 | 8936
MERIDIAN 11013044 | MERIDIAN 1101 | 62541101 |  | 12.3625 | 0.43677 |  | 208.5 | 0.00030817 | 7839 | 0.077093 | 3696 | 2.3715e-05 | 8937
CRESSEY 2103421930 | CRESSEY 2103 | 254702103 |  | 11.2829 | 0.23737 |  | 215.5 | 0.00034281 | 7263 | 0.069579 | 5107 | 2.3712e-05 | 8938
LOS OSITOS 21037086 | LOS OSITOS 2103 | 182082103 |  | 16.0078 | 0.54236 |  | 341.5 | 0.00035207 | 7106 | 0.067402 | 5666 | 2.371e-05 | 8939
BORDEN 1102CB | BORDEN 1102 | 255121102 |  | 9.37 | 0.33108 |  | 168.8333 | 0.00030796 | 7848 | 0.077163 | 3634 | 2.3704e-05 | 8940
CHOWCHILLA 110111420 | CHOWCHILLA 1101 | 254101101 |  | 6.6169 | 2.7818 |  | 123 | 0.00037291 | 6792 | 0.067016 | 6009 | 2.3698e-05 | 8941
MC CALL 1106589348 | MC CALL 1106 | 254121106 |  | 6.7997 | 1.6126 |  | 135 | 0.00030685 | 7870 | 0.07731 | 3460 | 2.3695e-05 | 8942
MORGAN HILL 21094145 | MORGAN HILL 2109 | 83242109 |  | 2.0911 | 0.67272 |  | 43.5 | 0.00037144 | 6821 | 0.064755 | 6469 | 2.3693e-05 | 8943
GUSTINE 110290260 | GUSTINE 1102 | 163111102 |  | 9.1973 | 2.296 |  | 144 | 0.00038409 | 6650 | 0.067184 | 5825 | 2.3681e-05 | 8944
MC MULLIN 1104CB | MC MULLIN 1104 | 254411104 |  | 23.7324 | 0.26504 |  | 393.8333 | 0.00030789 | 7850 | 0.077115 | 3681 | 2.3676e-05 | 8945
WILKINS SLOUGH 1101CB | WILKINS SLOUGH 1101 | 62771101 |  | 14.3899 | 0.24739 |  | 235.6667 | 0.00032366 | 7561 | 0.073435 | 4618 | 2.3669e-05 | 8946
BUENA VISTA 1106CB | BUENA VISTA 1106 | 182261106 |  | 7.9698 | 0.26081 |  | 169.5 | 0.00035846 | 7000 | 0.06665 | 6153 | 2.3666e-05 | 8947
WATSONVILLE 21015306 | WATSONVILLE 2101 | 83332101 |  | 4.4609 | 0.1394 |  | 82 | 0.00035322 | 7087 | 0.067 | 6057 | 2.3666e-05 | 8948
FAIRWAY 1104M38 | FAIRWAY 1104 | 182061104 |  | 4.6758 | 0.2814 |  | 76 | 0.00037068 | 6830 | 0.064344 | 6504 | 2.3661e-05 | 8949
KERMAN 110286102 | KERMAN 1102 | 252711102 |  | 43.7127 | 4.4826 |  | 761 | 0.00030807 | 7845 | 0.076858 | 3853 | 2.3661e-05 | 8950
HERDLYN 1102575178 | HERDLYN 1102 | 163741102 |  | 13.0509 | 0.63259 |  | 184.5 | 0.00031901 | 7653 | 0.074218 | 4523 | 2.3653e-05 | 8951
ORO LOMA 1117CB | ORO LOMA 1117 | 255371117 |  | 9.2867 | 0.30626 |  | 152.45 | 0.00030587 | 7889 | 0.077353 | 3410 | 2.3649e-05 | 8952
JAMESON 1105371694 | JAMESON 1105 | 63801105 | TRUE | 4.034 | 0.5206 | 0.039721 | 72.5 | 0.00032379 | 7559 | 0.074489 | 4485 | 2.3644e-05 | 8953
RENFRO 2101134422 | RENFRO 2101 | 254572101 |  | 6.8628 | 0.69855 |  | 114.5 | 0.00031886 | 7655 | 0.074402 | 4501 | 2.3641e-05 | 8954
COLONY 1101CB | COLONY 1101 | 162231101 |  | 18.9242 | 1.9711 |  | 326.5 | 0.00030594 | 7886 | 0.077288 | 3490 | 2.3638e-05 | 8955
GREEN VALLEY 210112824 | GREEN VALLEY 2101 | 83192101 |  | 9.5371 | 0.89632 |  | 188 | 0.00034963 | 7144 | 0.067413 | 5657 | 2.3637e-05 | 8956
LERDO 1113CB | LERDO 1113 | 253491113 |  | 5.8319 | 0.0478 |  | 98.5 | 0.00032577 | 7526 | 0.074287 | 4518 | 2.3628e-05 | 8957
BANTA 110313928 | BANTA 1103 | 162471103 |  | 6.4394 | 4.0201 |  | 99.5 | 0.00033362 | 7401 | 0.071648 | 4809 | 2.3627e-05 | 8958
SAN BENITO 210192468 | SAN BENITO 2101 | 182742101 |  | 3.9086 | 0.57615 |  | 72 | 0.00035272 | 7092 | 0.066758 | 6130 | 2.3625e-05 | 8959
LLAGAS 2101XR244 | LLAGAS 2101 | 83182101 |  | 14.1411 | 2.1298 |  | 286.5 | 0.00035234 | 7099 | 0.067501 | 5601 | 2.3623e-05 | 8960
ORTIGA 1106593066 | ORTIGA 1106 | 254311106 |  | 0.017943 | 0 |  | 0.5 | 0.00030515 | 7908 | 0.0774 | 3397 | 2.3619e-05 | 8961
EL PECO 11056240 | EL PECO 1105 | 253981105 |  | 7.728 | 0.42733 |  | 132.5 | 0.00030579 | 7890 | 0.077216 | 3579 | 2.3609e-05 | 8962
MC CALL 1101CB | MC CALL 1101 | 254121101 |  | 9.5618 | 1.0677 |  | 157.9167 | 0.00030498 | 7912 | 0.0774 | 3396 | 2.3605e-05 | 8963
MORMON 1102CB | MORMON 1102 | 163211102 |  | 9.4061 | 0.40056 |  | 151.6667 | 0.00030971 | 7808 | 0.076716 | 3926 | 2.3604e-05 | 8964
SCHINDLER 11149630 | SCHINDLER 1114 | 252891114 |  | 0.018123 | 0 |  | 0.5 | 0.00035212 | 7104 | 0.067 | 6057 | 2.3592e-05 | 8965
BIOLA 11016280 | BIOLA 1101 | 252211101 |  | 17.1493 | 1.2664 |  | 287.5 | 0.00030519 | 7906 | 0.077261 | 3529 | 2.3586e-05 | 8966
MADERA 11195330 | MADERA 1119 | 252761119 |  | 11.2875 | 1.2782 |  | 194.5 | 0.0003047 | 7918 | 0.0774 | 3397 | 2.3584e-05 | 8967
LIVINGSTON 11029750 | LIVINGSTON 1102 | 252261102 |  | 9.009 | 0.48729 |  | 162 | 0.00030588 | 7888 | 0.077078 | 3709 | 2.3569e-05 | 8968
BIOLA 1104R1913 | BIOLA 1104 | 252211104 |  | 18.8198 | 2.8247 |  | 343.5 | 0.0003065 | 7878 | 0.076965 | 3786 | 2.3565e-05 | 8969
LIVE OAK 11021340 | LIVE OAK 1102 | 153771102 |  | 19.5431 | 1.4326 |  | 333.5 | 0.00030965 | 7811 | 0.07643 | 4044 | 2.3559e-05 | 8970
FAMOSO 1107CB | FAMOSO 1107 | 252461107 |  | 5.1681 | 0.17679 |  | 89.3333 | 0.00032436 | 7553 | 0.074404 | 4499 | 2.3558e-05 | 8971
LERDO 1114CB | LERDO 1114 | 253491114 |  | 9.8907 | 0.17227 |  | 151.1667 | 0.00032258 | 7585 | 0.074808 | 4441 | 2.3556e-05 | 8972
ORTIGA 1105CB | ORTIGA 1105 | 254311105 |  | 24.1376 | 1.2689 |  | 401 | 0.00030928 | 7817 | 0.076615 | 3977 | 2.3553e-05 | 8973
WAHTOKE 1108673298 | WAHTOKE 1108 | 254531108 |  | 0.014343 | 0 |  | 0.33333 | 0.00044377 | 5976 | 0.053073 | 8251 | 2.3552e-05 | 8974
KINGSBURG 11145080 | KINGSBURG 1114 | 252241114 |  | 11.3515 | 1.6684 |  | 208.5 | 0.00030535 | 7903 | 0.077208 | 3588 | 2.3546e-05 | 8975
DAIRYLAND 1111CB | DAIRYLAND 1111 | 252421111 |  | 18.7943 | 1.8858 |  | 322.5 | 0.00030417 | 7929 | 0.0774 | 3397 | 2.3543e-05 | 8976
DAIRYLAND 110936518 | DAIRYLAND 1109 | 252421109 |  | 20.5395 | 1.1272 |  | 348.5 | 0.0003054 | 7901 | 0.077121 | 3675 | 2.3539e-05 | 8977
SCHINDLER 1114CB | SCHINDLER 1114 | 252891114 |  | 19.289 | 0.71948 |  | 335 | 0.00032507 | 7536 | 0.073616 | 4595 | 2.3538e-05 | 8978
LOS MOLINOS 1101CB | LOS MOLINOS 1101 | 103481101 |  | 24.8598 | 2.7914 |  | 431 | 0.00035055 | 7132 | 0.067105 | 5894 | 2.3536e-05 | 8979
WASCO 1101CB | WASCO 1101 | 252961101 |  | 6.2823 | 0.11181 |  | 102.6667 | 0.00031197 | 7769 | 0.075914 | 4224 | 2.353e-05 | 8980
PEABODY 210240382 | PEABODY 2102 | 63642102 |  | 1.994 | 0 |  | 34 | 0.00034874 | 7162 | 0.067412 | 5658 | 2.3512e-05 | 8981
MADERA 1119677002 | MADERA 1119 | 252761119 |  | 8.8391 | 0.89695 |  | 152 | 0.00030426 | 7926 | 0.07732 | 3443 | 2.3509e-05 | 8982
KERMAN 110194216 | KERMAN 1101 | 252711101 |  | 12.993 | 0.72013 |  | 217 | 0.0003125 | 7757 | 0.075787 | 4268 | 2.3508e-05 | 8983
LARKIN (Y) 1141CB | LARKIN (Y) 1141 | 22801141 |  | 0.0339 | 0 |  | 1 | 0.0004429 | 5986 | 0.053073 | 8251 | 2.3506e-05 | 8984
STOREY 1104620474 | STOREY 1104 | 254611104 |  | 26.6748 | 2.1707 |  | 469 | 0.00031596 | 7699 | 0.074992 | 4416 | 2.349e-05 | 8985
SAN JOAQUIN 110846174 | SAN JOAQUIN 1108 | 252361108 |  | 7.7546 | 3.1875 |  | 130.8333 | 0.00034519 | 7218 | 0.070103 | 5021 | 2.3488e-05 | 8986
RIVERBANK 1711335302 | RIVERBANK 1711 | 163191711 |  | 8.7477 | 1.2605 |  | 153.8333 | 0.00033506 | 7379 | 0.072006 | 4775 | 2.3476e-05 | 8987
PRUNEDALE 1110826224 | PRUNEDALE 1110 | 182961110 |  | 7.2414 | 1.801 |  | 140.5 | 0.00034807 | 7172 | 0.067376 | 5685 | 2.3474e-05 | 8988
JACINTO 1101CB | JACINTO 1101 | 102851101 |  | 6.552 | 0.42109 |  | 108 | 0.00033729 | 7344 | 0.070557 | 4949 | 2.3468e-05 | 8989
DAIRYLAND 1113345006 | DAIRYLAND 1113 | 252421113 |  | 3.6494 | 0.14658 |  | 61 | 0.00030314 | 7946 | 0.0774 | 3397 | 2.3463e-05 | 8990
MADISON 210123272 | MADISON 2101 | 63172101 |  | 9.9758 | 1.3188 |  | 185 | 0.00034312 | 7259 | 0.069074 | 5181 | 2.3459e-05 | 8991
WEBER 110238326 | WEBER 1102 | 163481102 |  | 13.3236 | 0.8746 |  | 235 | 0.00031815 | 7666 | 0.074484 | 4486 | 2.3456e-05 | 8992
LLAGAS 21013835 | LLAGAS 2101 | 83182101 |  | 1.5793 | 0.32994 |  | 31.5 | 0.00034629 | 7201 | 0.067548 | 5574 | 2.345e-05 | 8993
MALAGA 1102R45 | MALAGA 1102 | 254251102 |  | 8.5071 | 1.2262 |  | 159.5 | 0.00030566 | 7894 | 0.076853 | 3857 | 2.3438e-05 | 8994
BONITA 110211870 | BONITA 1102 | 255391102 |  | 18.5583 | 1.1555 |  | 309.5 | 0.00030545 | 7899 | 0.077046 | 3735 | 2.3414e-05 | 8995
CASTROVILLE 21043571 | CASTROVILLE 2104 | 182352104 |  | 1.2574 | 0.087411 |  | 26.5 | 0.00034943 | 7150 | 0.067 | 6057 | 2.3412e-05 | 8996
KNIGHTS LANDING 11029502 | KNIGHTS LANDING 1102 | 62721102 |  | 8.9581 | 0.5594 |  | 162.5 | 0.00031477 | 7720 | 0.074287 | 4517 | 2.3402e-05 | 8997
EAST NICOLAUS 11032608 | EAST NICOLAUS 1103 | 152151103 |  | 15.7692 | 0.77168 |  | 264 | 0.00030218 | 7963 | 0.0774 | 3397 | 2.3389e-05 | 8998
MILPITAS 1105CB | MILPITAS 1105 | 82831105 |  | 4.6773 | 1.6154 |  | 90.1667 | 0.00041474 | 6287 | 0.060962 | 6893 | 2.3388e-05 | 8999
NEWBURG 113137512 | NEWBURG 1131 | 192151131 |  | 5.1987 | 2.5395 |  | 86 | 0.00039953 | 6461 | 0.05917 | 7136 | 2.337e-05 | 9000
COTATI 1105136 | COTATI 1105 | 42271105 |  | 13.4617 | 4.5547 |  | 237.5 | 0.00034837 | 7168 | 0.067306 | 5726 | 2.3369e-05 | 9001
LIVINGSTON 1106815510 | LIVINGSTON 1106 | 252261106 |  | 12.2034 | 1.3136 |  | 215.5 | 0.00031683 | 7684 | 0.074757 | 4451 | 2.3366e-05 | 9002
LOGAN CREEK 210174576 | LOGAN CREEK 2101 | 103142101 |  | 14.7482 | 0.42496 |  | 253 | 0.0003105 | 7798 | 0.075585 | 4315 | 2.3363e-05 | 9003
MARYSVILLE 110850856 | MARYSVILLE 1108 | 152011108 |  | 12.5169 | 0.85957 |  | 225.5 | 0.00031535 | 7708 | 0.074905 | 4426 | 2.3362e-05 | 9004
EL DORADO PH 210113362 | EL DORADO PH 2101 | 152762101 |  | 9.135 | 5.171 |  | 191 | 0.00033808 | 7335 | 0.069023 | 5187 | 2.3359e-05 | 9005
GREEN VALLEY 21035140 | GREEN VALLEY 2103 | 83192103 |  | 7.239 | 0.35409 |  | 140 | 0.00035203 | 7107 | 0.066353 | 6210 | 2.3357e-05 | 9006
CAMDEN 110237578 | CAMDEN 1102 | 252301102 |  | 3.9348 | 1.354 |  | 64.5 | 0.00031342 | 7748 | 0.07496 | 4420 | 2.3334e-05 | 9007
SMYRNA 1106CB | SMYRNA 1106 | 253551106 |  | 4.1928 | 0.053552 |  | 58.5333 | 0.00030147 | 7979 | 0.0774 | 3397 | 2.3333e-05 | 9008
EEL RIVER 11024600 | EEL RIVER 1102 | 192381102 |  | 5.9125 | 0.25522 |  | 111.5 | 0.00034785 | 7176 | 0.067133 | 5870 | 2.3331e-05 | 9009
CASTROVILLE 210436922 | CASTROVILLE 2104 | 182352104 |  | 5.4837 | 0.11684 |  | 99.5 | 0.00034816 | 7170 | 0.067002 | 6045 | 2.3328e-05 | 9010
BORONDA 1102CB | BORONDA 1102 | 182461102 |  | 4.3395 | 0.76838 |  | 64.9167 | 0.00036164 | 6963 | 0.065395 | 6380 | 2.3323e-05 | 9011
CATLETT 11051232 | CATLETT 1105 | 153761105 |  | 6.4671 | 0.30284 |  | 129.5 | 0.00030673 | 7872 | 0.076339 | 4073 | 2.3315e-05 | 9012
COTTLE 1701CB | COTTLE 1701 | 163711701 |  | 24.1462 | 2.0532 |  | 423.3333 | 0.00033274 | 7413 | 0.071511 | 4829 | 2.3313e-05 | 9013
DAIRYLAND 1113595578 | DAIRYLAND 1113 | 252421113 |  | 0.016381 | 0 |  | 0.5 | 0.00030121 | 7989 | 0.0774 | 3397 | 2.3313e-05 | 9014
LERDO 1115CUS1066 | LERDO 1115 | 253491115 |  | 0.0067521 | 0 |  | 0.33333 | 0.00030119 | 7991 | 0.0774 | 3396 | 2.3312e-05 | 9015
SANTA MARIA 1109M30 | SANTA MARIA 1109 | 182671109 |  | 19.3781 | 2.8738 |  | 337 | 0.00034608 | 7204 | 0.067761 | 5490 | 2.3309e-05 | 9016
BARRY 1103CB | BARRY 1103 | 152111103 |  | 18.8331 | 1.7864 |  | 324.3333 | 0.00030963 | 7813 | 0.075729 | 4282 | 2.33e-05 | 9017
EAST NICOLAUS 110355920 | EAST NICOLAUS 1103 | 152151103 |  | 0.020054 | 0 |  | 0.5 | 0.00030093 | 7994 | 0.0774 | 3397 | 2.3292e-05 | 9018
LOCKEFORD 210211692 | LOCKEFORD 2102 | 163682102 |  | 2.246 | 0.094578 |  | 36.8333 | 0.00030087 | 7996 | 0.0774 | 3397 | 2.3287e-05 | 9019
MARINA (F) 0403CB | MARINA (F) 0403 | 22780403 |  | 0.042966 | 0.070639 |  | 2 | 0.00043876 | 6024 | 0.053073 | 8251 | 2.3286e-05 | 9020
CORNING 110146022 | CORNING 1101 | 103331101 |  | 9.1266 | 0.67229 |  | 150.5 | 0.00034163 | 7278 | 0.068065 | 5392 | 2.3282e-05 | 9021
MC CALL 110641780 | MC CALL 1106 | 254121106 |  | 13.2291 | 2.5887 |  | 252.5 | 0.00030203 | 7965 | 0.077176 | 3619 | 2.328e-05 | 9022
GATES 1106CB | GATES 1106 | 253931106 |  | 8.6047 | 0.065683 |  | 145.3333 | 0.00032617 | 7517 | 0.072723 | 4693 | 2.327e-05 | 9023
ATWATER 11087210 | ATWATER 1108 | 253611108 |  | 7.0408 | 0.5514 |  | 125 | 0.00030497 | 7913 | 0.076621 | 3974 | 2.3269e-05 | 9024
STONE CORRAL 110878844 | STONE CORRAL 1108 | 252921108 |  | 32.626 | 5.7022 |  | 596 | 0.000305 | 7910 | 0.076631 | 3970 | 2.3268e-05 | 9025
LAMONT 11022862 | LAMONT 1102 | 253911102 |  | 18.9297 | 1.185 |  | 321 | 0.00030121 | 7988 | 0.077288 | 3489 | 2.3262e-05 | 9026
MERCED 1114345460 | MERCED 1114 | 252801114 |  | 1.9342 | 0.041818 |  | 31.8333 | 0.00030222 | 7961 | 0.077153 | 3643 | 2.3261e-05 | 9027
LOGAN CREEK 210137268 | LOGAN CREEK 2101 | 103142101 |  | 10.7979 | 0.31941 |  | 183 | 0.00032547 | 7531 | 0.072145 | 4763 | 2.3258e-05 | 9028
HIGHWAY 11058962 | HIGHWAY 1105 | 42651105 |  | 0.60732 | 0 |  | 10.5 | 0.00034446 | 7230 | 0.067509 | 5594 | 2.3254e-05 | 9029
MARICOPA 11023558 | MARICOPA 1102 | 254211102 |  | 8.4765 | 1.059 |  | 139 | 0.00034377 | 7243 | 0.067545 | 5577 | 2.3242e-05 | 9030
COTTONWOOD 11031508 | COTTONWOOD 1103 | 102931103 |  | 0.39204 | 0 |  | 8.5 | 0.00034683 | 7193 | 0.067004 | 6035 | 2.324e-05 | 9031
PEACHTON 1101CB | PEACHTON 1101 | 103241101 |  | 31.8544 | 2.4829 |  | 550.5 | 0.00031037 | 7800 | 0.076186 | 4135 | 2.3239e-05 | 9032
PEACHTON 110334944 | PEACHTON 1103 | 103241103 |  | 5.5689 | 0.95109 |  | 99.5 | 0.00030082 | 7998 | 0.077242 | 3542 | 2.3239e-05 | 9033
CORNING 110193362 | CORNING 1101 | 103331101 |  | 0.36774 | 0 |  | 7.5 | 0.00034304 | 7261 | 0.067713 | 5507 | 2.3233e-05 | 9034
BIOLA 1101D2029 | BIOLA 1101 | 252211101 |  | 2.5443 | 1.9906 |  | 47.5 | 0.00037536 | 6758 | 0.063859 | 6562 | 2.3232e-05 | 9035
ARCATA 11066552 | ARCATA 1106 | 192021106 |  | 0.83041 | 0.17212 |  | 13.5 | 0.00037158 | 6817 | 0.06416 | 6522 | 2.3232e-05 | 9036
MESA 11016113 | MESA 1101 | 182821101 | FALSE | 9.8687 | 0.59019 | 1.4452 | 197 | 0.00014262 | 10767 | 0.31139 | 3006 | 2.3231e-05 | 9037
DINUBA 110448592 | DINUBA 1104 | 254091104 |  | 0.62068 | 0.09615 |  | 9.5 | 0.00030575 | 7892 | 0.076119 | 4157 | 2.3221e-05 | 9038
CORNING 110237398 | CORNING 1102 | 103331102 |  | 7.4978 | 0.93178 |  | 127.8333 | 0.00034356 | 7247 | 0.067508 | 5596 | 2.3221e-05 | 9039
MC MULLIN 11066817F | MC MULLIN 1106 | 254411106 |  | 3.9634 | 0.7308 |  | 75.5 | 0.00030347 | 7939 | 0.076755 | 3905 | 2.322e-05 | 9040
WILSON 11034420 | WILSON 1103 | 254301103 |  | 9.8266 | 0.61728 |  | 168 | 0.00030461 | 7919 | 0.076748 | 3913 | 2.3214e-05 | 9041
WHEATLAND 1105CB | WHEATLAND 1105 | 152811105 |  | 3.2206 | 0.18289 |  | 63.5 | 0.00033671 | 7353 | 0.070112 | 5018 | 2.3182e-05 | 9042
TUDOR 1102CB | TUDOR 1102 | 153711102 |  | 5.7613 | 0.2895 |  | 95.3333 | 0.00031686 | 7682 | 0.07431 | 4510 | 2.3174e-05 | 9043
BIOLA 1101CB | BIOLA 1101 | 252211101 |  | 26.7928 | 3.1995 |  | 421.1667 | 0.00030062 | 8007 | 0.077227 | 3556 | 2.3168e-05 | 9044
KERMAN 110182402 | KERMAN 1101 | 252711101 |  | 24.2289 | 2.8609 |  | 419.5 | 0.00030166 | 7973 | 0.076902 | 3831 | 2.315e-05 | 9045
DAIRYLAND 1109CB | DAIRYLAND 1109 | 252421109 |  | 5.0503 | 0.42679 |  | 89 | 0.0002991 | 8035 | 0.0774 | 3397 | 2.315e-05 | 9046
BELLE HAVEN 110538298 | BELLE HAVEN 1105 | 24021105 |  | 0.44087 | 0.27068 |  | 8.5 | 0.00043613 | 6054 | 0.053073 | 8251 | 2.3147e-05 | 9047
BIOLA 1101R1912 | BIOLA 1101 | 252211101 |  | 25.4921 | 3.9267 |  | 462 | 0.00030019 | 8015 | 0.077167 | 3630 | 2.3142e-05 | 9048
OAKLAND X 1104CB | OAKLAND X 1104 | 12541104 |  | 1.0524 | 1.2049 |  | 24.5 | 0.00040102 | 6440 | 0.057147 | 7412 | 2.313e-05 | 9049
DIXON 11056232 | DIXON 1105 | 62061105 |  | 17.5225 | 1.2122 |  | 297.5 | 0.00030556 | 7897 | 0.07641 | 4050 | 2.3129e-05 | 9050
DAIRYLAND 111356348 | DAIRYLAND 1113 | 252421113 |  | 10.6409 | 0.88042 |  | 179.5 | 0.0003016 | 7975 | 0.076908 | 3824 | 2.3105e-05 | 9051
CRESSEY 21039370 | CRESSEY 2103 | 254702103 |  | 27.6476 | 0.91338 |  | 517.5 | 0.00029966 | 8025 | 0.077231 | 3552 | 2.3104e-05 | 9052
BORDEN 110349354 | BORDEN 1103 | 255121103 |  | 5.1853 | 0.40941 |  | 92 | 0.0002985 | 8043 | 0.0774 | 3397 | 2.3104e-05 | 9053
AVENA 17012284 | AVENA 1701 | 163571701 |  | 22.5093 | 1.9033 |  | 398.5 | 0.00030069 | 8006 | 0.076972 | 3782 | 2.3101e-05 | 9054
DOLAN ROAD 11013048 | DOLAN ROAD 1101 | 182381101 |  | 3.3713 | 0.13105 |  | 70.5 | 0.00034408 | 7234 | 0.067074 | 5924 | 2.3082e-05 | 9055
OLD RIVER 11021646 | OLD RIVER 1102 | 252821102 |  | 13.7727 | 1.3226 |  | 234 | 0.00030529 | 7905 | 0.075856 | 4245 | 2.3081e-05 | 9056
GRAND ISLAND 22239482 | GRAND ISLAND 2223 | 62462223 |  | 20.5837 | 0.81853 |  | 346.9167 | 0.00030484 | 7914 | 0.076248 | 4110 | 2.3061e-05 | 9057
LOCKEFORD 210211694 | LOCKEFORD 2102 | 163682102 |  | 12.3728 | 1.3704 |  | 213 | 0.00029885 | 8039 | 0.077252 | 3536 | 2.3055e-05 | 9058
TEMPLETON 2112R80 | TEMPLETON 2112 | 183052112 |  | 6.0319 | 0.42596 |  | 108 | 0.00035821 | 7005 | 0.065304 | 6391 | 2.3054e-05 | 9059
WOODWARD 21085060 | WOODWARD 2108 | 255292108 |  | 9.5847 | 0.15693 |  | 171.5 | 0.00033878 | 7333 | 0.068308 | 5332 | 2.3053e-05 | 9060
VICTOR 1102CB | VICTOR 1102 | 163281102 |  | 12.5181 | 1.6243 |  | 194.4167 | 0.0003113 | 7779 | 0.07505 | 4408 | 2.3051e-05 | 9061
SHEPHERD 2111CB | SHEPHERD 2111 | 252062111 |  | 14.692 | 0.7128 |  | 218.0833 | 0.00034238 | 7269 | 0.067525 | 5588 | 2.3047e-05 | 9062
GOOSE LAKE 2104993374 | GOOSE LAKE 2104 | 254202104 |  | 18.4247 | 2.3966 |  | 319 | 0.00034118 | 7287 | 0.068014 | 5403 | 2.304e-05 | 9063
GLENN 11012416 | GLENN 1101 | 102601101 |  | 8.8383 | 0.74433 |  | 148.5 | 0.00033963 | 7313 | 0.067939 | 5419 | 2.3029e-05 | 9064
LIVE OAK 1101338916 | LIVE OAK 1101 | 153771101 |  | 2.1537 | 0.1287 |  | 33.5 | 0.00029749 | 8059 | 0.0774 | 3397 | 2.3026e-05 | 9065
ZAMORA 1105485514 | ZAMORA 1105 | 63191105 |  | 4.955 | 0.064783 |  | 86.5 | 0.00030127 | 7985 | 0.076656 | 3956 | 2.3021e-05 | 9066
GLENN 1101CB | GLENN 1101 | 102601101 |  | 10.0822 | 0.42739 |  | 166.5 | 0.00033995 | 7305 | 0.067851 | 5458 | 2.302e-05 | 9067
KEARNEY 1106249259 | KEARNEY 1106 | 252701106 |  | 11.1247 | 0.38542 |  | 185.5 | 0.00029741 | 8060 | 0.0774 | 3397 | 2.302e-05 | 9068
TRACY 110613296 | TRACY 1106 | 162881106 |  | 22.4139 | 1.0795 |  | 391 | 0.00030139 | 7981 | 0.076564 | 3994 | 2.3013e-05 | 9069
HURON 1108CB | HURON 1108 | 253161108 |  | 9.3002 | 0.17782 |  | 144 | 0.00031378 | 7740 | 0.074624 | 4470 | 2.3008e-05 | 9070
LOS COCHES 1101CB | LOS COCHES 1101 | 182151101 |  | 18.8055 | 0.89164 |  | 388.5 | 0.00033632 | 7359 | 0.068523 | 5283 | 2.2997e-05 | 9071
VICTOR 1102452726 | VICTOR 1102 | 163281102 |  | 13.9938 | 2.338 |  | 218.6667 | 0.00030609 | 7884 | 0.075913 | 4225 | 2.2984e-05 | 9072
OLD RIVER 11042771 | OLD RIVER 1104 | 252821104 |  | 25.3176 | 2.2933 |  | 435 | 0.00029797 | 8051 | 0.077168 | 3629 | 2.2984e-05 | 9073
JACINTO 110245248 | JACINTO 1102 | 102851102 |  | 11.5645 | 0.47628 |  | 203 | 0.00031295 | 7754 | 0.07494 | 4423 | 2.2981e-05 | 9074
SAN JOAQUIN 1112873576 | SAN JOAQUIN 1112 | 252361112 |  | 0.082058 | 0 |  | 2.5 | 0.00029691 | 8067 | 0.0774 | 3397 | 2.298e-05 | 9075
CAL WATER 1102CB | CAL WATER 1102 | 255451102 |  | 6.2904 | 0.09505 |  | 102 | 0.00034384 | 7240 | 0.06713 | 5874 | 2.2972e-05 | 9076
LIVINGSTON 1105CB | LIVINGSTON 1105 | 252261105 |  | 21.668 | 0.72076 |  | 355.5 | 0.0002994 | 8030 | 0.076981 | 3774 | 2.2959e-05 | 9077
WILKINS SLOUGH 1103CB | WILKINS SLOUGH 1103 | 62771103 |  | 17.3585 | 0.76721 |  | 289.5 | 0.00030155 | 7976 | 0.076554 | 3996 | 2.2955e-05 | 9078
WILKINS SLOUGH 11029402 | WILKINS SLOUGH 1102 | 62771102 |  | 4.7156 | 0.13731 |  | 92 | 0.00030272 | 7950 | 0.075845 | 4249 | 2.2947e-05 | 9079
SMYRNA 1105CB | SMYRNA 1105 | 253551105 |  | 13.7187 | 0.24983 |  | 214.0333 | 0.00029638 | 8075 | 0.0774 | 3397 | 2.294e-05 | 9080
DINUBA 110466036 | DINUBA 1104 | 254091104 |  | 0.020309 | 0 |  | 1.5 | 0.00037069 | 6828 | 0.061182 | 6871 | 2.2933e-05 | 9081
RADUM 1105MR277 | RADUM 1105 | 13151105 |  | 1.7309 | 0.90397 |  | 28 | 0.00043194 | 6092 | 0.053073 | 8251 | 2.2924e-05 | 9082
LOGAN CREEK 21012444 | LOGAN CREEK 2101 | 103142101 |  | 8.0677 | 0.3015 |  | 130 | 0.00031159 | 7775 | 0.074088 | 4542 | 2.2921e-05 | 9083
MERIDIAN 11014373 | MERIDIAN 1101 | 62541101 |  | 9.3286 | 0.34722 |  | 154.5 | 0.00030165 | 7974 | 0.076038 | 4186 | 2.292e-05 | 9084
LOGAN CREEK 210247194 | LOGAN CREEK 2102 | 103142102 |  | 6.1967 | 0.28378 |  | 103 | 0.00031684 | 7683 | 0.072961 | 4667 | 2.2911e-05 | 9085
HOLLISTER 21054060 | HOLLISTER 2105 | 182492105 |  | 3.0933 | 0.17502 |  | 56.1667 | 0.00033975 | 7310 | 0.067286 | 5741 | 2.2903e-05 | 9086
COLUSA JUNCTION 1101CB | COLUSA JUNCTION 1101 | 62071101 |  | 14.024 | 1.2728 |  | 269.8333 | 0.00031056 | 7796 | 0.074875 | 4431 | 2.2892e-05 | 9087
METTLER 11106420 | METTLER 1110 | 163701110 |  | 9.724 | 0.93364 |  | 169 | 0.00031713 | 7676 | 0.073696 | 4581 | 2.289e-05 | 9088
CAPAY 1102635856 | CAPAY 1102 | 102111102 |  | 0.018497 | 0 |  | 0.5 | 0.00034161 | 7279 | 0.067 | 6057 | 2.2888e-05 | 9089
KNIGHTS LANDING 110236810 | KNIGHTS LANDING 1102 | 62721102 |  | 16.9404 | 0.95828 |  | 294 | 0.00033228 | 7417 | 0.070369 | 4965 | 2.2884e-05 | 9090
ORLAND B 11032538 | ORLAND B 1103 | 102701103 |  | 5.2317 | 0.59734 |  | 89.5 | 0.00033777 | 7341 | 0.06776 | 5491 | 2.2884e-05 | 9091
ORO LOMA 11153470 | ORO LOMA 1115 | 255371115 |  | 4.8552 | 0.3966 |  | 81 | 0.00029551 | 8095 | 0.0774 | 3397 | 2.2872e-05 | 9092
VACA DIXON 1105CB | VACA DIXON 1105 | 63591105 |  | 20.5677 | 2.3918 |  | 335.6667 | 0.00033771 | 7342 | 0.067664 | 5519 | 2.2869e-05 | 9093
LINCOLN 11042072 | LINCOLN 1104 | 153701104 | TRUE | 17.0581 | 2.7226 | 0.36067 | 304.5 | 0.00023308 | 9426 | 0.095394 | 3325 | 2.2866e-05 | 9094
FIGARDEN 2102R2730 | FIGARDEN 2102 | 254552102 |  | 4.4375 | 0.88887 |  | 81.5 | 0.00029542 | 8096 | 0.0774 | 3397 | 2.2865e-05 | 9095
EAST NICOLAUS 1102CB | EAST NICOLAUS 1102 | 152151102 |  | 12.2407 | 1.3294 |  | 214 | 0.00030392 | 7932 | 0.076268 | 4102 | 2.2864e-05 | 9096
MAXWELL 11023004 | MAXWELL 1102 | 62881102 |  | 16.8912 | 0.50114 |  | 285 | 0.0002998 | 8023 | 0.076479 | 4023 | 2.285e-05 | 9097
WILLIAMS 110130534 | WILLIAMS 1101 | 62051101 |  | 23.3733 | 0.74252 |  | 412.3333 | 0.00031992 | 7630 | 0.072892 | 4673 | 2.2842e-05 | 9098
MC FARLAND 1104708132 | MC FARLAND 1104 | 253181104 |  | 12.8665 | 0.50479 |  | 202 | 0.00029584 | 8087 | 0.077202 | 3593 | 2.2832e-05 | 9099
CARUTHERS 110478636 | CARUTHERS 1104 | 252371104 |  | 30.5834 | 3.3688 |  | 546 | 0.00029656 | 8073 | 0.076984 | 3770 | 2.2816e-05 | 9100
CAMDEN 1102CB | CAMDEN 1102 | 252301102 |  | 10.5972 | 1.8371 |  | 186.8333 | 0.00030751 | 7855 | 0.075543 | 4331 | 2.2807e-05 | 9101
FULTON 11024334 | FULTON 1102 | 42561102 |  | 9.0544 | 1.3667 |  | 158.5 | 0.00033989 | 7308 | 0.067086 | 5915 | 2.2806e-05 | 9102
LOGAN CREEK 21022454 | LOGAN CREEK 2102 | 103142102 |  | 12.2682 | 0.76336 |  | 210 | 0.00033591 | 7365 | 0.068032 | 5398 | 2.2804e-05 | 9103
CARBONA 110411720 | CARBONA 1104 | 163091104 |  | 18.4881 | 0.9016 |  | 318 | 0.00030558 | 7896 | 0.073966 | 4559 | 2.2797e-05 | 9104
LAKEVIEW 1102CB | LAKEVIEW 1102 | 253411102 |  | 6.3548 | 0.2033 |  | 97.3333 | 0.00032749 | 7494 | 0.07016 | 5007 | 2.2796e-05 | 9105
BOWLES 1101337559 | BOWLES 1101 | 253531101 |  | 4.0299 | 0.40469 |  | 72.5 | 0.00029664 | 8072 | 0.077064 | 3722 | 2.279e-05 | 9106
HUMBOLDT BAY 1102309413 | HUMBOLDT BAY 1102 | 192341102 |  | 8.066 | 0.70308 |  | 150.8333 | 0.00033932 | 7321 | 0.067139 | 5863 | 2.2786e-05 | 9107
SAN MIGUEL 1105CB | SAN MIGUEL 1105 | 182661105 |  | 10.2412 | 2.8897 |  | 180.5 | 0.00020456 | 9966 | 0.25959 | 3070 | 2.2783e-05 | 9108
MERIDIAN 1101CB | MERIDIAN 1101 | 62541101 |  | 18.6966 | 1.7127 |  | 325.5 | 0.00030182 | 7972 | 0.076138 | 4146 | 2.2783e-05 | 9109
NEW HOPE 1102CB | NEW HOPE 1102 | 162081102 |  | 15.8258 | 0.5123 |  | 271.5 | 0.00029779 | 8055 | 0.076649 | 3961 | 2.2782e-05 | 9110
PEACHTON 11031008 | PEACHTON 1103 | 103241103 |  | 2.751 | 0.23577 |  | 48.8333 | 0.00030239 | 7957 | 0.076326 | 4079 | 2.2781e-05 | 9111
GRAND ISLAND 22275882 | GRAND ISLAND 2227 | 62462227 |  | 22.1016 | 1.316 |  | 414.5 | 0.00030022 | 8013 | 0.076226 | 4119 | 2.278e-05 | 9112
CARBONA 110114204 | CARBONA 1101 | 163091101 |  | 0.78531 | 0 |  | 16 | 0.00037394 | 6780 | 0.060907 | 6899 | 2.2777e-05 | 9113
PUEBLO 1105419634 | PUEBLO 1105 | 43291105 | TRUE | 1.2521 | 0.23829 | 0.21902 | 25.5 | 0.00033896 | 7328 | 0.06717 | 5834 | 2.2769e-05 | 9114
BONITA 1102CB | BONITA 1102 | 255391102 |  | 10.8267 | 0.55668 |  | 191.3333 | 0.00029442 | 8117 | 0.077357 | 3406 | 2.2765e-05 | 9115
EL CAPITAN 1103CB | EL CAPITAN 1103 | 253881103 |  | 11.8839 | 2.5014 |  | 211.2 | 0.0003027 | 7951 | 0.075938 | 4218 | 2.2749e-05 | 9116
BRENTWOOD 211219647 | BRENTWOOD 2112 | 14592112 |  | 1.055 | 0.13946 |  | 18.5 | 0.00029388 | 8131 | 0.0774 | 3397 | 2.2746e-05 | 9117
MADISON 2101CB | MADISON 2101 | 63172101 |  | 13.6948 | 1.3279 |  | 242 | 0.00033575 | 7369 | 0.068127 | 5379 | 2.2746e-05 | 9118
MC CALL 11086970 | MC CALL 1108 | 254121108 |  | 9.9811 | 2.1795 |  | 182.5 | 0.00029387 | 8132 | 0.0774 | 3397 | 2.2746e-05 | 9119
STOREY 1104CB | STOREY 1104 | 254611104 |  | 21.7018 | 2.5502 |  | 354.25 | 0.00031648 | 7694 | 0.071718 | 4802 | 2.2745e-05 | 9120
MOLINO 1103CB | MOLINO 1103 | 42571103 |  | 8.7783 | 0.78441 |  | 148.5 | 0.00033807 | 7336 | 0.067253 | 5760 | 2.2742e-05 | 9121
ATWATER 11087190 | ATWATER 1108 | 253611108 |  | 36.0811 | 6.2673 |  | 623 | 0.00030427 | 7924 | 0.075635 | 4304 | 2.2739e-05 | 9122
CRESSEY 21034220 | CRESSEY 2103 | 254702103 |  | 10.5671 | 0.94613 |  | 183.5 | 0.00029591 | 8084 | 0.076983 | 3773 | 2.2726e-05 | 9123
WHEATLAND 11021370 | WHEATLAND 1102 | 152811102 |  | 10.6016 | 0.65803 |  | 186 | 0.00029562 | 8092 | 0.077018 | 3751 | 2.2726e-05 | 9124
OLIVEHURST 110165710 | OLIVEHURST 1101 | 152901101 |  | 0.02422 | 0 |  | 0.5 | 0.0002935 | 8141 | 0.0774 | 3397 | 2.2717e-05 | 9125
WHEELER RIDGE 110190844 | WHEELER RIDGE 1101 | 253481101 |  | 11.032 | 0.43898 |  | 186 | 0.00029963 | 8026 | 0.076315 | 4085 | 2.2716e-05 | 9126
BUTTE 11072566 | BUTTE 1107 | 103081107 |  | 0.015625 | 0 |  | 0.5 | 0.00033892 | 7329 | 0.067 | 6057 | 2.2707e-05 | 9127
WRIGHT 11103220 | WRIGHT 1110 | 254641110 |  | 8.2318 | 0.51536 |  | 138 | 0.00030008 | 8016 | 0.07599 | 4202 | 2.2707e-05 | 9128
KNIGHTS LANDING 11021702 | KNIGHTS LANDING 1102 | 62721102 |  | 28.1151 | 0.84646 |  | 520.5 | 0.00029894 | 8038 | 0.075943 | 4217 | 2.2696e-05 | 9129
TYLER 11041528 | TYLER 1104 | 103571104 |  | 3.719 | 0.065605 |  | 76 | 0.00033441 | 7391 | 0.068238 | 5352 | 2.2692e-05 | 9130
GATES 1102CB | GATES 1102 | 253931102 |  | 15.2076 | 0.3337 |  | 239.1667 | 0.00029856 | 8042 | 0.076073 | 4173 | 2.2691e-05 | 9131
CAPAY 110266596 | CAPAY 1102 | 102111102 |  | 7.4932 | 0.64025 |  | 137.5 | 0.00033666 | 7355 | 0.067364 | 5691 | 2.2685e-05 | 9132
SAN BERNARD 1104CB | SAN BERNARD 1104 | 253191104 |  | 9.2185 | 0.4045 |  | 153.3333 | 0.00031917 | 7648 | 0.070979 | 4895 | 2.2654e-05 | 9133
HENRIETTA 11089350 | HENRIETTA 1108 | 252681108 |  | 3.9411 | 0.060135 |  | 64 | 0.00029598 | 8083 | 0.07683 | 3871 | 2.2628e-05 | 9134
MC KEE 1110XR344 | MC KEE 1110 | 83531110 |  | 0.55296 | 0.022527 |  | 10.5 | 0.00042052 | 6223 | 0.054711 | 7805 | 2.2622e-05 | 9135
OLD RIVER 1104CB | OLD RIVER 1104 | 252821104 |  | 9.527 | 0.4922 |  | 161.5 | 0.00029365 | 8139 | 0.077001 | 3761 | 2.261e-05 | 9136
PASO ROBLES 1102CB | PASO ROBLES 1102 | 182611102 |  | 4.1839 | 2.388 |  | 70.8333 | 0.00034777 | 7177 | 0.065613 | 6337 | 2.2608e-05 | 9137
DOS PALOS 11019910 | DOS PALOS 1101 | 254041101 |  | 19.7131 | 2.1845 |  | 351 | 0.00029823 | 8048 | 0.076333 | 4075 | 2.2603e-05 | 9138
MERCED 1116237138 | MERCED 1116 | 252801116 |  | 26.8583 | 1.2977 |  | 496 | 0.00029374 | 8137 | 0.077007 | 3756 | 2.2582e-05 | 9139
BONITA 110211540 | BONITA 1102 | 255391102 |  | 1.9458 | 0.05739 |  | 31.5 | 0.00029799 | 8050 | 0.075855 | 4246 | 2.2581e-05 | 9140
CARUTHERS 1104CB | CARUTHERS 1104 | 252371104 |  | 23.5068 | 3.0419 |  | 404.75 | 0.00029247 | 8155 | 0.077263 | 3525 | 2.258e-05 | 9141
HORSESHOE 1101416226 | HORSESHOE 1101 | 152571101 | TRUE | 0.24474 | 0.14671 | 0.11112 | 4.5 | 0.00033699 | 7349 | 0.067 | 6057 | 2.2578e-05 | 9142
MERCED 11149200 | MERCED 1114 | 252801114 |  | 18.4002 | 0.86287 |  | 310.5 | 0.00029299 | 8147 | 0.077155 | 3640 | 2.2569e-05 | 9143
KERMAN 110197426 | KERMAN 1101 | 252711101 |  | 23.0847 | 3.6252 |  | 435.5 | 0.00029471 | 8113 | 0.076811 | 3880 | 2.2555e-05 | 9144
SANTA MARIA 110556064 | SANTA MARIA 1105 | 182671105 |  | 1.5284 | 0.049833 |  | 24.8333 | 0.00033503 | 7380 | 0.067419 | 5653 | 2.2555e-05 | 9145
LOGAN CREEK 210164198 | LOGAN CREEK 2101 | 103142101 |  | 9.6975 | 0.63531 |  | 163 | 0.0002973 | 8062 | 0.076162 | 4138 | 2.2554e-05 | 9146
FIGARDEN 211037172 | FIGARDEN 2110 | 254552110 |  | 8.677 | 0.91515 |  | 161.5 | 0.00029283 | 8151 | 0.07713 | 3663 | 2.255e-05 | 9147
PUTAH CREEK 1102CB | PUTAH CREEK 1102 | 63681102 |  | 3.4991 | 0.19422 |  | 63 | 0.00033158 | 7425 | 0.06789 | 5442 | 2.2548e-05 | 9148
MC CALL 11016080 | MC CALL 1101 | 254121101 |  | 49.6226 | 8.4326 |  | 922.3333 | 0.00029231 | 8159 | 0.077221 | 3571 | 2.2547e-05 | 9149
FRENCH CAMP 110211846 | FRENCH CAMP 1102 | 163291102 |  | 7.5829 | 0.89532 |  | 137.3333 | 0.00032853 | 7477 | 0.071026 | 4893 | 2.2547e-05 | 9150
RIO BRAVO 1101CB | RIO BRAVO 1101 | 252861101 |  | 5.7844 | 0.36907 |  | 94 | 0.0003236 | 7564 | 0.070131 | 5012 | 2.2545e-05 | 9151
LERDO 1115CB | LERDO 1115 | 253491115 |  | 9.6406 | 1.0315 |  | 134 | 0.00030186 | 7970 | 0.075565 | 4320 | 2.2535e-05 | 9152
MERIDIAN 110236928 | MERIDIAN 1102 | 62541102 |  | 10.1649 | 0.38904 |  | 178.5 | 0.00029193 | 8166 | 0.077224 | 3563 | 2.2531e-05 | 9153
BOGUE 11067408 | BOGUE 1106 | 153781106 |  | 7.1756 | 0.64341 |  | 126 | 0.00029155 | 8174 | 0.077152 | 3644 | 2.2528e-05 | 9154
TULARE LAKE 110491874 | TULARE LAKE 1104 | 252951104 |  | 5.7738 | 2.6527 |  | 96 | 0.00035995 | 6982 | 0.063664 | 6588 | 2.2523e-05 | 9155
LERDO 11133661 | LERDO 1113 | 253491113 |  | 15.6856 | 0.4368 |  | 278.5 | 0.00031325 | 7750 | 0.073393 | 4624 | 2.2523e-05 | 9156
WAHTOKE 11115170 | WAHTOKE 1111 | 254531111 |  | 9.8158 | 1.6436 |  | 179.3333 | 0.00029904 | 8037 | 0.075956 | 4213 | 2.2517e-05 | 9157
EL NIDO 1104CB | EL NIDO 1104 | 252451104 |  | 25.416 | 1.3598 |  | 429.8333 | 0.00029285 | 8150 | 0.077055 | 3728 | 2.2512e-05 | 9158
DAIRYLAND 1111279006 | DAIRYLAND 1111 | 252421111 |  | 10.2122 | 0.86508 |  | 172 | 0.00029208 | 8163 | 0.077121 | 3674 | 2.251e-05 | 9159
MIDDLE RIVER 110158942 | MIDDLE RIVER 1101 | 162091101 |  | 5.6065 | 0.14604 |  | 114 | 0.00029668 | 8071 | 0.075794 | 4266 | 2.2508e-05 | 9160
MC CALL 11016260 | MC CALL 1101 | 254121101 |  | 14.913 | 2.9079 |  | 271 | 0.0003004 | 8011 | 0.075824 | 4256 | 2.2507e-05 | 9161
GONZALES 1103727404 | GONZALES 1103 | 182131103 |  | 2.8686 | 0.19003 |  | 62.5 | 0.0003345 | 7389 | 0.067333 | 5713 | 2.2495e-05 | 9162
LINDEN 1101CB | LINDEN 1101 | 162071101 |  | 7.1357 | 0.66457 |  | 118.8333 | 0.00029925 | 8032 | 0.075834 | 4251 | 2.2491e-05 | 9163
NOVATO 1104422246 | NOVATO 1104 | 42211104 |  | 0.031082 | 0 |  | 0.5 | 0.00032122 | 7603 | 0.070007 | 5044 | 2.2488e-05 | 9164
LE GRAND 1106790446 | LE GRAND 1106 | 255361106 |  | 20.5424 | 1.3721 |  | 350.5 | 0.0002921 | 8162 | 0.077081 | 3707 | 2.2483e-05 | 9165
WATSONVILLE 210110952 | WATSONVILLE 2101 | 83332101 |  | 12.0911 | 1.831 |  | 217 | 0.00033452 | 7388 | 0.067191 | 5819 | 2.248e-05 | 9166
ZAMORA 1105993810 | ZAMORA 1105 | 63191105 |  | 11.0502 | 0.25563 |  | 183.5 | 0.0002903 | 8190 | 0.0774 | 3397 | 2.2469e-05 | 9167
CAMDEN 1105CB | CAMDEN 1105 | 252301105 |  | 12.6659 | 1.0606 |  | 214 | 0.00029268 | 8153 | 0.076831 | 3870 | 2.2469e-05 | 9168
EL NIDO 110456332 | EL NIDO 1104 | 252451104 |  | 17.9268 | 0.72747 |  | 305.5 | 0.00029269 | 8152 | 0.076796 | 3889 | 2.2468e-05 | 9169
LAMONT 11052213 | LAMONT 1105 | 253911105 |  | 11.4413 | 0.45487 |  | 197.5 | 0.00031466 | 7727 | 0.071248 | 4864 | 2.2467e-05 | 9170
ORICK 1101CB | ORICK 1101 | 192261101 |  | 7.9805 | 0.96673 |  | 166.5 | 0.00033488 | 7384 | 0.067087 | 5913 | 2.2464e-05 | 9171
GERBER 110237312 | GERBER 1102 | 103391102 |  | 16.0655 | 1.7014 |  | 268 | 0.00033059 | 7439 | 0.068384 | 5306 | 2.2456e-05 | 9172
WELLFIELD 1103CB | WELLFIELD 1103 | 254291103 |  | 0.22705 | 0.018434 |  | 4.5 | 0.00033444 | 7390 | 0.06714 | 5862 | 2.2454e-05 | 9173
SOLEDAD 21047248 | SOLEDAD 2104 | 182052104 |  | 11.6639 | 0.42503 |  | 229.75 | 0.00033217 | 7419 | 0.068222 | 5355 | 2.2453e-05 | 9174
LIVINGSTON 1102CB | LIVINGSTON 1102 | 252261102 |  | 4.5615 | 0.27221 |  | 76.5 | 0.00028999 | 8200 | 0.0774 | 3397 | 2.2445e-05 | 9175
LAMONT 11079871 | LAMONT 1107 | 253911107 |  | 2.3012 | 0.33032 |  | 38.5 | 0.00028993 | 8201 | 0.0774 | 3397 | 2.2441e-05 | 9176
DINUBA 1104CB | DINUBA 1104 | 254091104 |  | 8.2176 | 1.6775 |  | 140 | 0.00029193 | 8165 | 0.077157 | 3637 | 2.2435e-05 | 9177
CARUTHERS 1102109158 | CARUTHERS 1102 | 252371102 |  | 6.623 | 0.67265 |  | 113 | 0.00029183 | 8169 | 0.076969 | 3784 | 2.243e-05 | 9178
VIERRA 170734396 | VIERRA 1707 | 162701707 |  | 32.8551 | 2.6632 |  | 569.3333 | 0.00029477 | 8112 | 0.076512 | 4011 | 2.2429e-05 | 9179
DAIRYLAND 110268372 | DAIRYLAND 1102 | 252421102 |  | 6.1196 | 0.20894 |  | 104.5 | 0.00028976 | 8202 | 0.0774 | 3397 | 2.2428e-05 | 9180
DAIRYLAND 1113921862 | DAIRYLAND 1113 | 252421113 |  | 10.678 | 0.8422 |  | 193 | 0.00029347 | 8142 | 0.076517 | 4008 | 2.2417e-05 | 9181
HURON 1116CB | HURON 1116 | 253161116 |  | 2.3539 | 0.074519 |  | 42.5 | 0.00029156 | 8173 | 0.076827 | 3872 | 2.241e-05 | 9182
SANTA MARIA 1109CB | SANTA MARIA 1109 | 182671109 |  | 21.0149 | 2.0695 |  | 369.8333 | 0.00033883 | 7332 | 0.067729 | 5500 | 2.2407e-05 | 9183
PALMER 1101CB | PALMER 1101 | 183031101 |  | 2.0263 | 0.046913 |  | 35 | 0.0003315 | 7427 | 0.067532 | 5584 | 2.2403e-05 | 9184
FAMOSO 1103CB | FAMOSO 1103 | 252461103 |  | 7.4662 | 0.086246 |  | 127 | 0.00029006 | 8197 | 0.077208 | 3586 | 2.2398e-05 | 9185
MERIDIAN 11013002 | MERIDIAN 1101 | 62541101 |  | 13.1547 | 0.65697 |  | 240 | 0.00029586 | 8085 | 0.076135 | 4147 | 2.2384e-05 | 9186
SANTA RITA 11023080 | SANTA RITA 1102 | 253541102 |  | 16.6196 | 0.69139 |  | 301.5 | 0.00028953 | 8206 | 0.077319 | 3447 | 2.2383e-05 | 9187
PRUNEDALE 1107CB | PRUNEDALE 1107 | 182961107 |  | 8.5341 | 2.0729 |  | 158 | 0.00033572 | 7372 | 0.066743 | 6132 | 2.2383e-05 | 9188
NOVATO 110456282 | NOVATO 1104 | 42211104 |  | 0.6579 | 0.054169 |  | 13 | 0.00031968 | 7635 | 0.070007 | 5043 | 2.238e-05 | 9189
ORLAND B 110355050 | ORLAND B 1103 | 102701103 |  | 15.6906 | 1.6923 |  | 276.5 | 0.0003268 | 7510 | 0.069642 | 5094 | 2.2379e-05 | 9190
MOLINO 1104380 | MOLINO 1104 | 42571104 |  | 19.6064 | 5.0213 |  | 340 | 0.0003336 | 7402 | 0.067035 | 5971 | 2.2371e-05 | 9191
EL PECO 1102CB | EL PECO 1102 | 253981102 |  | 11.7264 | 0.4345 |  | 196.5 | 0.00028916 | 8213 | 0.07732 | 3444 | 2.2364e-05 | 9192
LAMONT 11044575 | LAMONT 1104 | 253911104 |  | 17.3082 | 0.20041 |  | 290.5 | 0.00032766 | 7491 | 0.068322 | 5326 | 2.2355e-05 | 9193
TERMINOUS 110214618 | TERMINOUS 1102 | 163021102 |  | 11.7124 | 0.63903 |  | 196.8333 | 0.00029365 | 8140 | 0.076459 | 4032 | 2.2349e-05 | 9194
PLUMAS 210680200 | PLUMAS 2106 | 153732106 |  | 15.762 | 1.7376 |  | 291 | 0.00029061 | 8185 | 0.077152 | 3646 | 2.2348e-05 | 9195
CASSIDY 21086060 | CASSIDY 2108 | 254272108 |  | 3.0427 | 0.090229 |  | 58.5 | 0.00029518 | 8102 | 0.076299 | 4088 | 2.2344e-05 | 9196
DAIRYLAND 1109336164 | DAIRYLAND 1109 | 252421109 |  | 2.074 | 0.090929 |  | 37.5 | 0.00029059 | 8186 | 0.07698 | 3775 | 2.2343e-05 | 9197
BAHIA 1101648 | BAHIA 1101 | 43251101 |  | 1.3835 | 0 |  | 21.5 | 0.00035385 | 7078 | 0.062541 | 6707 | 2.2338e-05 | 9198
CARUTHERS 11016290 | CARUTHERS 1101 | 252371101 |  | 22.3179 | 2.6323 |  | 399 | 0.00029491 | 8109 | 0.076234 | 4115 | 2.2334e-05 | 9199
KERN OIL 1107CB | KERN OIL 1107 | 252721107 |  | 21.0784 | 0.16273 |  | 316.1667 | 0.00030513 | 7909 | 0.073034 | 4660 | 2.2334e-05 | 9200
BOWLES 11035306F | BOWLES 1103 | 253531103 |  | 2.5309 | 1.3294 |  | 54.5 | 0.00029174 | 8171 | 0.076953 | 3794 | 2.2318e-05 | 9201
RICHMOND R 1127BR354 | RICHMOND R 1127 | 13471127 |  | 6.1458 | 0.37909 |  | 122.25 | 0.00035414 | 7072 | 0.064987 | 6435 | 2.2317e-05 | 9202
TEXACO EMIDIO 1101CB | TEXACO EMIDIO 1101 | 255421101 |  | 0.010571 | 0 |  | 1 | 0.00042032 | 6226 | 0.053073 | 8251 | 2.2307e-05 | 9203
GREEN VALLEY 21034929 | GREEN VALLEY 2103 | 83192103 |  | 0.48755 | 0.30414 |  | 9 | 0.00033274 | 7412 | 0.067 | 6057 | 2.2294e-05 | 9204
HURON 111242930 | HURON 1112 | 253161112 |  | 4.2368 | 0.15064 |  | 72 | 0.00036755 | 6879 | 0.061482 | 6835 | 2.2288e-05 | 9205
FAIRWAY 1107M12 | FAIRWAY 1107 | 182061107 |  | 12.0828 | 0.44793 |  | 226.5 | 0.00033216 | 7420 | 0.067107 | 5891 | 2.2274e-05 | 9206
SEMITROPIC 111037812 | SEMITROPIC 1110 | 252901110 |  | 12.0046 | 1.5197 |  | 205 | 0.00030243 | 7956 | 0.075323 | 4363 | 2.2271e-05 | 9207
LODI 110212592 | LODI 1102 | 162111102 |  | 22.52 | 2.6712 |  | 391.5 | 0.00030126 | 7986 | 0.075174 | 4388 | 2.2267e-05 | 9208
GUSTINE 11013502 | GUSTINE 1101 | 163111101 |  | 4.1318 | 0.23955 |  | 69 | 0.00030322 | 7945 | 0.074674 | 4462 | 2.2265e-05 | 9209
EAST NICOLAUS 11027254 | EAST NICOLAUS 1102 | 152151102 |  | 10.5177 | 1.1499 |  | 181 | 0.00028763 | 8240 | 0.0774 | 3397 | 2.2262e-05 | 9210
NEWBURG 11326982 | NEWBURG 1132 | 192151132 |  | 0.90201 | 0.11899 |  | 15.5 | 0.00038449 | 6643 | 0.059362 | 7103 | 2.2258e-05 | 9211
RIPON 17039814 | RIPON 1703 | 163801703 |  | 37.5393 | 3.4952 |  | 655 | 0.00029461 | 8115 | 0.076329 | 4076 | 2.2255e-05 | 9212
LE GRAND 1104560074 | LE GRAND 1104 | 255361104 |  | 4.2273 | 0.073665 |  | 74.5 | 0.00028749 | 8244 | 0.0774 | 3397 | 2.2251e-05 | 9213
STROUD 1104CB | STROUD 1104 | 253661104 |  | 15.1272 | 0.41162 |  | 255.3333 | 0.00030475 | 7917 | 0.073977 | 4557 | 2.2249e-05 | 9214
GEYSERVILLE 1102220154 | GEYSERVILLE 1102 | 42891102 | TRUE | 2.862 | 0.30152 | 0.26481 | 55 | 0.00033631 | 7360 | 0.066461 | 6192 | 2.2246e-05 | 9215
REEDLEY 1104CB | REEDLEY 1104 | 252341104 |  | 11.8667 | 2.2156 |  | 209.5 | 0.00030911 | 7819 | 0.072675 | 4698 | 2.2245e-05 | 9216
RAINBOW 1106R1440 | RAINBOW 1106 | 254441106 |  | 42.0818 | 5.5628 |  | 753.5 | 0.00029227 | 8161 | 0.076382 | 4060 | 2.2239e-05 | 9217
CANAL 110311170 | CANAL 1103 | 252091103 |  | 1.3967 | 0 |  | 26.5 | 0.00032018 | 7626 | 0.071433 | 4840 | 2.2238e-05 | 9218
KEARNEY 110464226 | KEARNEY 1104 | 252701104 |  | 11.953 | 2.6781 |  | 232 | 0.00029246 | 8157 | 0.076404 | 4052 | 2.2234e-05 | 9219
SHAFTER 1104CB | SHAFTER 1104 | 253651104 |  | 4.1202 | 0.38146 |  | 70.1667 | 0.00028723 | 8249 | 0.0774 | 3396 | 2.2232e-05 | 9220
BONITA 1101CB | BONITA 1101 | 255391101 |  | 3.0824 | 0.17063 |  | 53.3333 | 0.00029417 | 8124 | 0.075879 | 4235 | 2.2227e-05 | 9221
GRAND ISLAND 22258872 | GRAND ISLAND 2225 | 62462225 |  | 27.6593 | 2.1005 |  | 526.5 | 0.00029906 | 8036 | 0.075215 | 4384 | 2.2224e-05 | 9222
LERDO 11153910 | LERDO 1115 | 253491115 |  | 6.2354 | 0.26908 |  | 108 | 0.000287 | 8256 | 0.0774 | 3397 | 2.2214e-05 | 9223
WHEELER RIDGE 11032846 | WHEELER RIDGE 1103 | 253481103 |  | 9.8594 | 0.23817 |  | 170 | 0.00030219 | 7962 | 0.074218 | 4522 | 2.2211e-05 | 9224
DOLAN ROAD 1101672110 | DOLAN ROAD 1101 | 182381101 |  | 7.4314 | 1.261 |  | 131.5 | 0.00033087 | 7437 | 0.067084 | 5917 | 2.2209e-05 | 9225
BRUNSWICK 1110832231 | BRUNSWICK 1110 | 152481110 |  | 0.27875 | 0.034364 |  | 6.3333 | 0.00033142 | 7429 | 0.067 | 6057 | 2.2205e-05 | 9226
FELLOWS 210382182 | FELLOWS 2103 | 254242103 |  | 7.5412 | 0.058522 |  | 127.8333 | 0.00032906 | 7468 | 0.067285 | 5742 | 2.2205e-05 | 9227
RIVERBANK 1712130318 | RIVERBANK 1712 | 163191712 |  | 11.4085 | 0.35334 |  | 189 | 0.00028918 | 8211 | 0.076976 | 3778 | 2.2199e-05 | 9228
COLUSA 110195060 | COLUSA 1101 | 62021101 |  | 9.7596 | 0.68607 |  | 164.5 | 0.00030712 | 7860 | 0.074177 | 4530 | 2.2199e-05 | 9229
CAMPHORA 11013092 | CAMPHORA 1101 | 182071101 |  | 10.5036 | 0.31204 |  | 218.5833 | 0.00032767 | 7490 | 0.067905 | 5435 | 2.2191e-05 | 9230
FAMOSO 1105CB | FAMOSO 1105 | 252461105 |  | 10.0065 | 0.081986 |  | 173.8333 | 0.00030622 | 7882 | 0.073976 | 4558 | 2.2176e-05 | 9231
MC FARLAND 1105CB | MC FARLAND 1105 | 253181105 |  | 16.727 | 0.67146 |  | 281.75 | 0.00028809 | 8234 | 0.077128 | 3667 | 2.2175e-05 | 9232
CLEAR LAKE 110145252 | CLEAR LAKE 1101 | 42141101 |  | 5.7819 | 1.2788 |  | 106 | 0.0003296 | 7455 | 0.067297 | 5733 | 2.2173e-05 | 9233
WAHTOKE 1107788302 | WAHTOKE 1107 | 254531107 |  | 7.3316 | 1.1896 |  | 136.5 | 0.00028691 | 8260 | 0.077285 | 3495 | 2.2167e-05 | 9234
WILKINS SLOUGH 110237254 | WILKINS SLOUGH 1102 | 62771102 |  | 9.2076 | 0.31654 |  | 167.3333 | 0.00029094 | 8179 | 0.076263 | 4105 | 2.2163e-05 | 9235
ATWATER 11064570 | ATWATER 1106 | 253611106 |  | 19.0271 | 3.0602 |  | 350 | 0.0003071 | 7862 | 0.073819 | 4570 | 2.2157e-05 | 9236
SANTA NELLA 1101CB | SANTA NELLA 1101 | 254051101 |  | 13.1385 | 0.46652 |  | 212.5 | 0.00030591 | 7887 | 0.072903 | 4671 | 2.2154e-05 | 9237
MC FARLAND 1101CB | MC FARLAND 1101 | 253181101 |  | 9.969 | 0.81545 |  | 177.25 | 0.0002919 | 8168 | 0.076213 | 4124 | 2.2152e-05 | 9238
WHEELER RIDGE 110137662 | WHEELER RIDGE 1101 | 253481101 |  | 3.2252 | 0.07021 |  | 54 | 0.00028618 | 8282 | 0.0774 | 3397 | 2.215e-05 | 9239
MC CALL 11066280 | MC CALL 1106 | 254121106 |  | 9.7504 | 2.2556 |  | 195 | 0.00028727 | 8248 | 0.07715 | 3648 | 2.215e-05 | 9240
STONE CORRAL 11087759F | STONE CORRAL 1108 | 252921108 |  | 0.76913 | 0.089802 |  | 15.5 | 0.00028617 | 8284 | 0.0774 | 3397 | 2.2149e-05 | 9241
EL CAPITAN 11049610 | EL CAPITAN 1104 | 253881104 |  | 29.065 | 4.4587 |  | 520 | 0.00029781 | 8054 | 0.075138 | 4395 | 2.2139e-05 | 9242
OILFIELDS 11037064 | OILFIELDS 1103 | 182391103 |  | 5.1255 | 0.24432 |  | 99.5 | 0.00030898 | 7823 | 0.072272 | 4748 | 2.2137e-05 | 9243
CHOWCHILLA 110490020 | CHOWCHILLA 1104 | 254101104 |  | 15.1405 | 0.69674 |  | 270 | 0.00029416 | 8125 | 0.07603 | 4191 | 2.2137e-05 | 9244
KEARNEY 111049534 | KEARNEY 1110 | 252701110 |  | 9.8834 | 0.8501 |  | 174.5 | 0.00028694 | 8258 | 0.077172 | 3627 | 2.2131e-05 | 9245
GUERNSEY 1101CB | GUERNSEY 1101 | 252661101 |  | 9.8399 | 0.81465 |  | 150.6167 | 0.00028895 | 8216 | 0.076781 | 3896 | 2.213e-05 | 9246
DINUBA 1106CB | DINUBA 1106 | 254091106 |  | 4.0569 | 0.54454 |  | 60 | 0.00028867 | 8219 | 0.077096 | 3695 | 2.2129e-05 | 9247
PLUMAS 210750636 | PLUMAS 2107 | 153732107 |  | 22.1223 | 2.088 |  | 383.5 | 0.00028659 | 8272 | 0.077286 | 3493 | 2.2126e-05 | 9248
CARUTHERS 110434456 | CARUTHERS 1104 | 252371104 |  | 17.0406 | 2.4343 |  | 309 | 0.0002862 | 8281 | 0.077325 | 3436 | 2.2124e-05 | 9249
LEMOORE 1104CB | LEMOORE 1104 | 253601104 |  | 20.4506 | 3.9276 |  | 363.7 | 0.00030076 | 8003 | 0.074619 | 4471 | 2.2123e-05 | 9250
BLACKWELL 21011104 | BLACKWELL 2101 | 254682101 |  | 2.0898 | 0 |  | 35 | 0.00032915 | 7467 | 0.067149 | 5856 | 2.2115e-05 | 9251
CAROLANDS 0402CB | CAROLANDS 0402 | 24060402 |  | 0.033498 | 0.023293 |  | 1.25 | 0.00035675 | 7029 | 0.055921 | 7591 | 2.2114e-05 | 9252
ANITA 110137724 | ANITA 1101 | 102841101 |  | 8.0608 | 0.403 |  | 131 | 0.0003205 | 7620 | 0.070282 | 4985 | 2.2113e-05 | 9253
BORDEN 11035850 | BORDEN 1103 | 255121103 |  | 21.5452 | 1.7401 |  | 382 | 0.00028739 | 8245 | 0.076873 | 3844 | 2.21e-05 | 9254
MERIDIAN 110288128 | MERIDIAN 1102 | 62541102 |  | 8.2712 | 0.55469 |  | 154.3333 | 0.00029518 | 8103 | 0.075252 | 4375 | 2.2096e-05 | 9255
LIVINGSTON 110411260 | LIVINGSTON 1104 | 252261104 |  | 23.2674 | 2.1157 |  | 397.5 | 0.00028541 | 8298 | 0.0774 | 3397 | 2.2091e-05 | 9256
SPENCE 1102321000 | SPENCE 1102 | 182201102 | TRUE | 2.5301 | 0.11351 | 0.32535 | 51 | 0.00016182 | 10575 | 0.21605 | 3123 | 2.2089e-05 | 9257
LAMONT 11072469 | LAMONT 1107 | 253911107 |  | 9.3837 | 0.80425 |  | 169 | 0.00028788 | 8237 | 0.076896 | 3835 | 2.2072e-05 | 9258
WILLIAMS 11024104 | WILLIAMS 1102 | 62051102 |  | 8.8521 | 0.23329 |  | 143.5 | 0.00028816 | 8232 | 0.076925 | 3811 | 2.2069e-05 | 9259
WINTERS 110115822 | WINTERS 1101 | 63321101 |  | 3.739 | 0.069976 |  | 61.8333 | 0.00032475 | 7544 | 0.068838 | 5217 | 2.2066e-05 | 9260
RENFRO 21034686 | RENFRO 2103 | 254572103 |  | 23.2627 | 1.6959 |  | 379 | 0.00029946 | 8029 | 0.074848 | 4435 | 2.2062e-05 | 9261
COVELO 11012467 | COVELO 1101 | 43061101 |  | 2.701 | 0.42162 |  | 50.5 | 0.00023247 | 9435 | 0.15832 | 3195 | 2.2054e-05 | 9262
DUMBARTON 1106CB | DUMBARTON 1106 | 14471106 |  | 7.217 | 1.1689 |  | 147.5 | 0.00034753 | 7182 | 0.066014 | 6270 | 2.2052e-05 | 9263
HERDLYN 11038046 | HERDLYN 1103 | 163741103 |  | 20.2081 | 0.59702 |  | 360.5 | 0.00028797 | 8236 | 0.076749 | 3911 | 2.2049e-05 | 9264
BIOLA 1103R2800 | BIOLA 1103 | 252211103 |  | 12.1912 | 0.75817 |  | 213.5 | 0.00028482 | 8314 | 0.0774 | 3397 | 2.2045e-05 | 9265
SHAFTER 1112CB | SHAFTER 1112 | 253651112 |  | 8.1263 | 0.74798 |  | 140.6667 | 0.00028516 | 8304 | 0.077288 | 3491 | 2.2042e-05 | 9266
LONE TREE 2105CB | LONE TREE 2105 | 13232105 |  | 4.8175 | 0.19993 |  | 83.5 | 0.00032822 | 7481 | 0.067139 | 5864 | 2.2038e-05 | 9267
PASO ROBLES 1108CB | PASO ROBLES 1108 | 182611108 |  | 3.784 | 1.8761 |  | 65.5 | 0.00039735 | 6486 | 0.056189 | 7546 | 2.2035e-05 | 9268
CANAL 110312120 | CANAL 1103 | 252091103 |  | 3.664 | 0.093398 |  | 62 | 0.00028462 | 8317 | 0.0774 | 3397 | 2.203e-05 | 9269
BASALT 1106657038 | BASALT 1106 | 42461106 | FALSE | 8.2332 | 0.45795 | 0.90401 | 155 | 0.00032749 | 7495 | 0.067263 | 5757 | 2.2029e-05 | 9270
LOGAN CREEK 210269358 | LOGAN CREEK 2102 | 103142102 |  | 7.2349 | 0.185 |  | 129 | 0.00028568 | 8293 | 0.077156 | 3638 | 2.202e-05 | 9271
KNIGHTS LANDING 11018962 | KNIGHTS LANDING 1101 | 62721101 |  | 24.3289 | 0.61782 |  | 421.5 | 0.00028466 | 8316 | 0.077343 | 3418 | 2.2019e-05 | 9272
SOLEDAD 210237204 | SOLEDAD 2102 | 182052102 |  | 3.2595 | 0.28139 |  | 70.5 | 0.00032861 | 7475 | 0.067 | 6057 | 2.2017e-05 | 9273
CORDELIA 111240402 | CORDELIA 1112 | 62701112 |  | 1.1528 | 0.061094 |  | 23.5 | 0.00031359 | 7745 | 0.070105 | 5020 | 2.2012e-05 | 9274
HOLLISTER 210441808 | HOLLISTER 2104 | 182492104 |  | 10.9199 | 1.2071 |  | 203.8333 | 0.00032513 | 7535 | 0.067816 | 5471 | 2.2002e-05 | 9275
KINGSBURG 1114CB | KINGSBURG 1114 | 252241114 |  | 11.6814 | 1.6015 |  | 198.7833 | 0.00028678 | 8263 | 0.076954 | 3793 | 2.1998e-05 | 9276
RIVERBANK 17149150 | RIVERBANK 1714 | 163191714 |  | 6.9085 | 0.94869 |  | 120.3333 | 0.00029602 | 8081 | 0.075502 | 4339 | 2.1992e-05 | 9277
TEMPLETON 2109P60 | TEMPLETON 2109 | 183052109 |  | 3.1691 | 0.049951 |  | 53 | 0.00033575 | 7370 | 0.06621 | 6233 | 2.1991e-05 | 9278
LAKEVIEW 11023776 | LAKEVIEW 1102 | 253411102 |  | 16.6685 | 0.19528 |  | 283 | 0.00029144 | 8176 | 0.075697 | 4288 | 2.199e-05 | 9279
EMBARCADERO (Z) 1123CB | EMBARCADERO (Z) 1123 | 22871123 |  | 0.35592 | 0.56407 |  | 11.6667 | 0.00041433 | 6292 | 0.053073 | 8252 | 2.1989e-05 | 9280
TEMBLOR 110437696 | TEMBLOR 1104 | 252551104 |  | 4.3023 | 0 |  | 71.5 | 0.00032143 | 7597 | 0.068751 | 5231 | 2.1981e-05 | 9281
COLONY 1102CB | COLONY 1102 | 162231102 |  | 17.6391 | 1.1746 |  | 300.5 | 0.00028483 | 8312 | 0.07724 | 3544 | 2.198e-05 | 9282
HONCUT 11021702 | HONCUT 1102 | 103211102 |  | 11.7139 | 0.83741 |  | 206 | 0.00028886 | 8217 | 0.076287 | 4097 | 2.1979e-05 | 9283
OCEANO 1105V20 | OCEANO 1105 | 182601105 |  | 5.4533 | 4.616 |  | 89.5 | 0.0003765 | 6741 | 0.057546 | 7351 | 2.1974e-05 | 9284
MENDOTA 110337432 | MENDOTA 1103 | 252311103 |  | 2.5917 | 0.2795 |  | 48 | 0.0003655 | 6913 | 0.063135 | 6653 | 2.1974e-05 | 9285
ATWATER 1102839304 | ATWATER 1102 | 253611102 |  | 0.052001 | 0 |  | 1 | 0.00028385 | 8333 | 0.0774 | 3397 | 2.197e-05 | 9286
OLD RIVER 11044169 | OLD RIVER 1104 | 252821104 |  | 23.4135 | 1.3918 |  | 399 | 0.00028736 | 8247 | 0.07677 | 3898 | 2.1967e-05 | 9287
SHAFTER 1103CB | SHAFTER 1103 | 253651103 |  | 7.8073 | 0.6256 |  | 138.6667 | 0.0002903 | 8191 | 0.076093 | 4165 | 2.1964e-05 | 9288
CHOWCHILLA 1106867748 | CHOWCHILLA 1106 | 254101106 |  | 11.899 | 0.28478 |  | 198 | 0.00028425 | 8326 | 0.077277 | 3508 | 2.1964e-05 | 9289
METTLER 111063452 | METTLER 1110 | 163701110 |  | 8.7858 | 1.1583 |  | 157.5 | 0.00028462 | 8318 | 0.077173 | 3624 | 2.1958e-05 | 9290
LOCKEFORD 210237614 | LOCKEFORD 2102 | 163682102 |  | 17.3218 | 1.0141 |  | 304.3333 | 0.00029393 | 8129 | 0.074583 | 4478 | 2.1953e-05 | 9291
SPENCE 1105CB | SPENCE 1105 | 182201105 |  | 10.549 | 0.57728 |  | 206.25 | 0.00032729 | 7498 | 0.06705 | 5946 | 2.1952e-05 | 9292
LIVINGSTON 1104261292 | LIVINGSTON 1104 | 252261104 |  | 0.41791 | 0.065275 |  | 7.5 | 0.00028362 | 8340 | 0.0774 | 3397 | 2.1952e-05 | 9293
SAN BERNARD 1102CB | SAN BERNARD 1102 | 253191102 |  | 11.9503 | 0.3415 |  | 200.3333 | 0.00031474 | 7724 | 0.070121 | 5016 | 2.1947e-05 | 9294
VASCO 1102MR418 | VASCO 1102 | 13751102 |  | 5.6854 | 0.20236 |  | 101 | 0.00034413 | 7233 | 0.065276 | 6395 | 2.1942e-05 | 9295
GRAND ISLAND 22238492 | GRAND ISLAND 2223 | 62462223 |  | 11.0159 | 0.58112 |  | 233 | 0.0002845 | 8320 | 0.077191 | 3601 | 2.194e-05 | 9296
FIREBAUGH 11013540 | FIREBAUGH 1101 | 253471101 |  | 0.011644 | 0 |  | 1 | 0.00041333 | 6298 | 0.053073 | 8251 | 2.1937e-05 | 9297
HENRIETTA 11068710 | HENRIETTA 1106 | 252681106 |  | 1.8551 | 0.31073 |  | 29.8333 | 0.00028535 | 8300 | 0.077128 | 3668 | 2.1936e-05 | 9298
OCEANO 1105V16 | OCEANO 1105 | 182601105 |  | 5.3761 | 6.3588 |  | 90.5 | 0.00041272 | 6305 | 0.053862 | 7984 | 2.1934e-05 | 9299
ESQUON 11012052 | ESQUON 1101 | 102171101 |  | 18.8454 | 0.86026 |  | 344 | 0.00029163 | 8172 | 0.075478 | 4341 | 2.1933e-05 | 9300
DOLAN ROAD 1104CB | DOLAN ROAD 1104 | 182381104 |  | 5.0587 | 0.34943 |  | 89.1667 | 0.00032362 | 7563 | 0.067933 | 5422 | 2.1931e-05 | 9301
PANORAMA 11021249 | PANORAMA 1102 | 103461102 |  | 5.2948 | 0.82602 |  | 105.5 | 0.00032505 | 7537 | 0.067368 | 5689 | 2.1918e-05 | 9302
DINUBA 1105CB | DINUBA 1105 | 254091105 |  | 6.5962 | 1.024 |  | 128 | 0.00028621 | 8280 | 0.076984 | 3771 | 2.1918e-05 | 9303
BOWLES 11026530 | BOWLES 1102 | 253531102 |  | 25.7929 | 5.0458 |  | 489.5 | 0.00028485 | 8311 | 0.07707 | 3717 | 2.1911e-05 | 9304
MC CALL 110793252 | MC CALL 1107 | 254121107 |  | 0.022376 | 0 |  | 1 | 0.00028307 | 8354 | 0.0774 | 3397 | 2.191e-05 | 9305
BOWLES 11016210 | BOWLES 1101 | 253531101 |  | 11.8228 | 1.6925 |  | 223 | 0.00029003 | 8199 | 0.075883 | 4234 | 2.1905e-05 | 9306
LOGAN CREEK 21012218 | LOGAN CREEK 2101 | 103142101 |  | 28.9287 | 1.4234 |  | 494.5 | 0.00028644 | 8276 | 0.07661 | 3979 | 2.1901e-05 | 9307
SCHINDLER 111447668 | SCHINDLER 1114 | 252891114 |  | 15.7853 | 0.47877 |  | 261 | 0.00028671 | 8265 | 0.07646 | 4031 | 2.1895e-05 | 9308
COTATI 11052121 | COTATI 1105 | 42271105 |  | 2.4636 | 0.91805 |  | 40 | 0.00032593 | 7522 | 0.067294 | 5735 | 2.189e-05 | 9309
MENDOTA 1104CB | MENDOTA 1104 | 252311104 |  | 10.2716 | 0.55099 |  | 161.25 | 0.0002949 | 8110 | 0.074836 | 4437 | 2.189e-05 | 9310
MENLO 04029070 | MENLO 0402 | 24130402 |  | 1.3886 | 0.66096 |  | 33 | 0.00032667 | 7512 | 0.067 | 6057 | 2.1887e-05 | 9311
BOWLES 11045030 | BOWLES 1104 | 253531104 |  | 11.1005 | 1.701 |  | 205.5 | 0.00028364 | 8338 | 0.077281 | 3502 | 2.1887e-05 | 9312
BONITA 11036020 | BONITA 1103 | 255391103 |  | 34.8371 | 2.6348 |  | 594.5 | 0.00028332 | 8343 | 0.077292 | 3484 | 2.1883e-05 | 9313
CARUTHERS 1105665998 | CARUTHERS 1105 | 252371105 |  | 0.99405 | 0.10523 |  | 15.5 | 0.00028273 | 8360 | 0.0774 | 3397 | 2.1883e-05 | 9314
ALPAUGH 1106CB | ALPAUGH 1106 | 254001106 |  | 13.9097 | 0.39023 |  | 230.1667 | 0.00028617 | 8283 | 0.076677 | 3944 | 2.1872e-05 | 9315
WILKINS SLOUGH 110298742 | WILKINS SLOUGH 1102 | 62771102 |  | 10.1601 | 0.19819 |  | 180 | 0.00028839 | 8227 | 0.076061 | 4176 | 2.1861e-05 | 9316
GUERNSEY 11048630 | GUERNSEY 1104 | 252661104 |  | 9.5083 | 0.73906 |  | 163 | 0.00028528 | 8302 | 0.076656 | 3955 | 2.1861e-05 | 9317
BLUE LAKE 110266454 | BLUE LAKE 1102 | 192181102 |  | 8.6854 | 1.3844 |  | 161.5 | 0.00032586 | 7523 | 0.067034 | 5979 | 2.1842e-05 | 9318
BUENA VISTA 11063714 | BUENA VISTA 1106 | 182261106 |  | 4.947 | 0.24903 |  | 99 | 0.00032438 | 7551 | 0.067315 | 5720 | 2.1834e-05 | 9319
BASALT 1106724 | BASALT 1106 | 42461106 |  | 19.9975 | 1.6329 |  | 366.5 | 0.00032462 | 7547 | 0.067279 | 5746 | 2.183e-05 | 9320
WATERLOO 1101CB | WATERLOO 1101 | 163151101 |  | 17.975 | 1.4993 |  | 310.5 | 0.00028252 | 8363 | 0.077221 | 3570 | 2.1816e-05 | 9321
ORTIGA 110677310 | ORTIGA 1106 | 254311106 |  | 6.9817 | 0.68851 |  | 120.5 | 0.0002872 | 8251 | 0.075472 | 4342 | 2.181e-05 | 9322
GATES 11069090 | GATES 1106 | 253931106 |  | 8.1734 | 0.14772 |  | 128 | 0.00031184 | 7771 | 0.071128 | 4878 | 2.1808e-05 | 9323
BUTTE 11072078 | BUTTE 1107 | 103081107 |  | 36.6862 | 4.4609 |  | 695.3333 | 0.00031904 | 7651 | 0.069223 | 5162 | 2.1807e-05 | 9324
FULTON 1105142 | FULTON 1105 | 42561105 |  | 9.106 | 1.3762 |  | 160.5 | 0.00032665 | 7514 | 0.066901 | 6090 | 2.1807e-05 | 9325
NEWMAN 110610800 | NEWMAN 1106 | 162741106 |  | 13.1661 | 0.84215 |  | 231.5 | 0.00028235 | 8367 | 0.077295 | 3483 | 2.1807e-05 | 9326
SAN JOAQUIN 110683170 | SAN JOAQUIN 1106 | 252361106 |  | 22.16 | 0.47881 |  | 374 | 0.00028361 | 8341 | 0.076902 | 3830 | 2.1805e-05 | 9327
LAKEVIEW 11029360 | LAKEVIEW 1102 | 253411102 |  | 3.1291 | 0.045135 |  | 55.5 | 0.00028699 | 8257 | 0.075943 | 4216 | 2.1797e-05 | 9328
OCEANO 1102V56 | OCEANO 1102 | 182601102 | FALSE | 9.897 | 0.35823 | 9.4288 | 153 | 1.8285e-05 | 11153 | 1.1619 | 2216 | 2.1771e-05 | 9329
CANTUA 11059790 | CANTUA 1105 | 253591105 |  | 2.0516 | 0.089582 |  | 34.5 | 0.00028757 | 8243 | 0.076032 | 4189 | 2.1762e-05 | 9330
LAS POSITAS 2110MR327 | LAS POSITAS 2110 | 14402110 |  | 4.0653 | 0 |  | 66.3333 | 0.0003761 | 6746 | 0.057132 | 7415 | 2.1757e-05 | 9331
KINGSBURG 111284417 | KINGSBURG 1112 | 252241112 |  | 1.8888 | 0.84983 |  | 41 | 0.00030037 | 8012 | 0.07473 | 4453 | 2.1754e-05 | 9332
TEMPLETON 2111R76 | TEMPLETON 2111 | 183052111 |  | 2.0255 | 1.7893 |  | 42.5 | 0.00036546 | 6914 | 0.060774 | 6919 | 2.1754e-05 | 9333
CASTROVILLE 21045004 | CASTROVILLE 2104 | 182352104 |  | 10.4298 | 0.59754 |  | 221 | 0.00032303 | 7577 | 0.067394 | 5674 | 2.1752e-05 | 9334
WAHTOKE 11087160 | WAHTOKE 1108 | 254531108 |  | 14.1068 | 1.1403 |  | 253.5 | 0.00030258 | 7953 | 0.0728 | 4684 | 2.175e-05 | 9335
KEARNEY 1106563038 | KEARNEY 1106 | 252701106 |  | 18.4039 | 1.7973 |  | 321.5 | 0.00028191 | 8378 | 0.077173 | 3625 | 2.1747e-05 | 9336
TEMBLOR 1104CB | TEMBLOR 1104 | 252551104 |  | 7.5539 | 0 |  | 149 | 0.00032447 | 7548 | 0.067 | 6057 | 2.1739e-05 | 9337
BOWLES 11016909F | BOWLES 1101 | 253531101 |  | 1.1954 | 0.079523 |  | 21.5 | 0.00028073 | 8403 | 0.0774 | 3397 | 2.1728e-05 | 9338
CABRILLO 1104431976 | CABRILLO 1104 | 183101104 |  | 0.033241 | 0 |  | 1 | 0.0003243 | 7554 | 0.067 | 6057 | 2.1728e-05 | 9339
DOLAN ROAD 1101882610 | DOLAN ROAD 1101 | 182381101 | TRUE | 0.41153 | 0.11099 | 0.047804 | 9 | 0.00032269 | 7583 | 0.067309 | 5725 | 2.1724e-05 | 9340
RAINBOW 1106CB | RAINBOW 1106 | 254441106 |  | 4.5929 | 0.65548 |  | 83.8333 | 0.00028062 | 8406 | 0.0774 | 3396 | 2.172e-05 | 9341
AVENA 1701427866 | AVENA 1701 | 163571701 |  | 19.899 | 1.248 |  | 322 | 0.00028973 | 8204 | 0.07606 | 4177 | 2.1711e-05 | 9342
PASO ROBLES 1106R70 | PASO ROBLES 1106 | 182611106 |  | 5.9621 | 1.6523 |  | 104 | 0.00033666 | 7354 | 0.065637 | 6332 | 2.1705e-05 | 9343
SANTA YNEZ 1104CB | SANTA YNEZ 1104 | 182721104 | TRUE | 7.9834 | 0.85636 | 0.016462 | 137.3333 | 0.00032127 | 7601 | 0.067348 | 5704 | 2.1704e-05 | 9344
ANITA 110166258 | ANITA 1101 | 102841101 |  | 13.3827 | 1.1707 |  | 228.5 | 0.00031244 | 7760 | 0.071265 | 4863 | 2.1704e-05 | 9345
PLAINFIELD 110621482 | PLAINFIELD 1106 | 63441106 |  | 9.8222 | 0.53271 |  | 163.8333 | 0.00028032 | 8413 | 0.0774 | 3398 | 2.1696e-05 | 9346
GUSTINE 110137354 | GUSTINE 1101 | 163111101 |  | 5.7034 | 0.30663 |  | 96.5 | 0.00028116 | 8396 | 0.077148 | 3650 | 2.1696e-05 | 9347
PEACHTON 1103CB | PEACHTON 1103 | 103241103 |  | 6.8125 | 0.6589 |  | 119.6667 | 0.00028113 | 8397 | 0.077268 | 3519 | 2.1694e-05 | 9348
GRAND ISLAND 222347924 | GRAND ISLAND 2223 | 62462223 |  | 10.4344 | 1.3585 |  | 196.3333 | 0.00028318 | 8347 | 0.076765 | 3901 | 2.1691e-05 | 9349
ARVIN 1102CB | ARVIN 1102 | 253801102 |  | 10.449 | 0.24411 |  | 174 | 0.00030701 | 7866 | 0.070829 | 4914 | 2.1679e-05 | 9350
BLUE LAKE 11013578 | BLUE LAKE 1101 | 192181101 |  | 3.6489 | 0.063513 |  | 69 | 0.00032284 | 7580 | 0.067151 | 5852 | 2.1676e-05 | 9351
GREEN VALLEY 210182789 | GREEN VALLEY 2101 | 83192101 |  | 1.183 | 0.16431 |  | 24.5 | 0.0003235 | 7566 | 0.067 | 6057 | 2.1674e-05 | 9352
EAST NICOLAUS 11031254 | EAST NICOLAUS 1103 | 152151103 |  | 22.6128 | 1.5135 |  | 381 | 0.00028938 | 8208 | 0.075071 | 4404 | 2.1673e-05 | 9353
PANORAMA 11021342 | PANORAMA 1102 | 103461102 |  | 9.0209 | 0.83638 |  | 181 | 0.00032263 | 7584 | 0.067058 | 5939 | 2.1657e-05 | 9354
COALINGA NO 2 1107793144 | COALINGA NO 2 1107 | 252381107 |  | 1.9789 | 0.14714 |  | 34 | 0.00031218 | 7767 | 0.069918 | 5059 | 2.1656e-05 | 9355
CATLETT 1102CB | CATLETT 1102 | 153761102 |  | 26.1577 | 1.1305 |  | 441.5 | 0.00028445 | 8323 | 0.075638 | 4303 | 2.1654e-05 | 9356
AVENA 1702CB | AVENA 1702 | 163571702 |  | 38.4336 | 2.5302 |  | 670 | 0.00028185 | 8381 | 0.077014 | 3754 | 2.1651e-05 | 9357
LIVINGSTON 1101CB | LIVINGSTON 1101 | 252261101 |  | 9.9605 | 0.53986 |  | 168 | 0.00027971 | 8427 | 0.0774 | 3397 | 2.165e-05 | 9358
BANTA 1103CB | BANTA 1103 | 162471103 |  | 30.1227 | 1.2749 |  | 617 | 0.00028496 | 8308 | 0.076475 | 4026 | 2.1648e-05 | 9359
FIREBAUGH 11013430 | FIREBAUGH 1101 | 253471101 |  | 4.4938 | 0.29942 |  | 91 | 0.00028862 | 8222 | 0.075642 | 4300 | 2.1648e-05 | 9360
CONTRA COSTA 2112CB | CONTRA COSTA 2112 | 13652112 |  | 0.037846 | 0.011633 |  | 3 | 0.00032304 | 7576 | 0.067 | 6057 | 2.1644e-05 | 9361
KERMAN 1101R42 | KERMAN 1101 | 252711101 |  | 25.8383 | 4.2229 |  | 465.5 | 0.00028132 | 8393 | 0.077072 | 3716 | 2.1643e-05 | 9362
WHEELER RIDGE 11031609 | WHEELER RIDGE 1103 | 253481103 |  | 12.7525 | 0.37772 |  | 220 | 0.00028437 | 8325 | 0.076593 | 3985 | 2.164e-05 | 9363
MISSION (X) 1124CB | MISSION (X) 1124 | 22011124 |  | 0.07781 | 0.19566 |  | 7.4167 | 0.00040774 | 6360 | 0.053073 | 8251 | 2.164e-05 | 9364
SANTA NELLA 11049660 | SANTA NELLA 1104 | 254051104 |  | 9.9057 | 0.46005 |  | 173.5 | 0.00028493 | 8310 | 0.076231 | 4118 | 2.1639e-05 | 9365
OLD RIVER 1101479636 | OLD RIVER 1101 | 252821101 |  | 6.2286 | 0.064491 |  | 103.5 | 0.00028076 | 8400 | 0.077089 | 3699 | 2.1636e-05 | 9366
COLONY 110236728 | COLONY 1102 | 162231102 |  | 19.4643 | 2.5782 |  | 350.5 | 0.00028361 | 8342 | 0.076571 | 3992 | 2.1635e-05 | 9367
CANTUA 1101CB | CANTUA 1101 | 253591101 |  | 8.7274 | 0.097023 |  | 141.5 | 0.00031474 | 7722 | 0.07 | 5046 | 2.1632e-05 | 9368
SCHINDLER 1111CB | SCHINDLER 1111 | 252891111 |  | 13.4684 | 0.056472 |  | 205.3333 | 0.00028405 | 8328 | 0.076262 | 4107 | 2.1627e-05 | 9369
CHOLAME 2102127926 | CHOLAME 2102 | 182562102 |  | 0.0073369 | 0 |  | 0.33333 | 0.00032252 | 7586 | 0.067 | 6056 | 2.1609e-05 | 9370
ANGIOLA 110457276 | ANGIOLA 1104 | 252151104 |  | 8.0702 | 0.16557 |  | 131 | 0.00029384 | 8134 | 0.074315 | 4509 | 2.1596e-05 | 9371
EL PECO 11062040 | EL PECO 1106 | 253981106 |  | 13.3967 | 1.1269 |  | 230 | 0.0002816 | 8385 | 0.076765 | 3902 | 2.1596e-05 | 9372
7TH STANDARD 21031381 | 7TH STANDARD 2103 | 254582103 |  | 9.5488 | 0.20371 |  | 158.5 | 0.000279 | 8444 | 0.0774 | 3397 | 2.1595e-05 | 9373
DINUBA 11057030 | DINUBA 1105 | 254091105 |  | 25.9454 | 1.4385 |  | 443 | 0.00027945 | 8434 | 0.07729 | 3488 | 2.1594e-05 | 9374
PEACHTON 110386522 | PEACHTON 1103 | 103241103 |  | 6.9294 | 1.3219 |  | 119.8333 | 0.00028578 | 8292 | 0.076294 | 4091 | 2.1594e-05 | 9375
BONITA 11015740 | BONITA 1101 | 255391101 |  | 44.0081 | 5.0792 |  | 790.5 | 0.00028039 | 8412 | 0.077114 | 3682 | 2.158e-05 | 9376
LE GRAND 1112CB | LE GRAND 1112 | 255361112 |  | 7.9656 | 0.66522 |  | 142.5 | 0.0002822 | 8373 | 0.076806 | 3882 | 2.1569e-05 | 9377
COPUS 1103CB | COPUS 1103 | 253871103 |  | 2.5191 | 0.014317 |  | 40.5 | 0.00031469 | 7726 | 0.069825 | 5071 | 2.1558e-05 | 9378
MERIDIAN 110253048 | MERIDIAN 1102 | 62541102 |  | 22.0493 | 0.81555 |  | 422.5 | 0.00028149 | 8386 | 0.07675 | 3910 | 2.1546e-05 | 9379
CRESSEY 21037022 | CRESSEY 2103 | 254702103 |  | 6.2245 | 0.37495 |  | 104.5 | 0.00029019 | 8193 | 0.075154 | 4392 | 2.1543e-05 | 9380
ATWATER 110342444 | ATWATER 1103 | 253611103 |  | 9.4351 | 1.1905 |  | 168.5 | 0.00028273 | 8358 | 0.076657 | 3954 | 2.1541e-05 | 9381
BIOLA 110489728 | BIOLA 1104 | 252211104 |  | 13.2551 | 1.9804 |  | 236 | 0.00027937 | 8436 | 0.077127 | 3669 | 2.1541e-05 | 9382
SANGER 1114R3000 | SANGER 1114 | 252351114 |  | 17.111 | 2.7437 |  | 295 | 0.00027985 | 8423 | 0.077099 | 3692 | 2.1539e-05 | 9383
HURON 110697762 | HURON 1106 | 253161106 |  | 14.4965 | 0.12642 |  | 243.5 | 0.00028029 | 8414 | 0.077036 | 3742 | 2.1534e-05 | 9384
KINGSBURG 111677276 | KINGSBURG 1116 | 252241116 |  | 10.3089 | 0.93859 |  | 167.5 | 0.00028232 | 8369 | 0.07658 | 3989 | 2.1529e-05 | 9385
BOGUE 11067398 | BOGUE 1106 | 153781106 |  | 23.8367 | 2.4789 |  | 426.5 | 0.00028604 | 8287 | 0.075877 | 4236 | 2.1529e-05 | 9386
PUEBLO 1105696 | PUEBLO 1105 | 43291105 |  | 3.3674 | 0.52357 |  | 63 | 0.00031976 | 7634 | 0.06735 | 5701 | 2.1527e-05 | 9387
SCHINDLER 1116CB | SCHINDLER 1116 | 252891116 |  | 10.688 | 0.39688 |  | 166.3333 | 0.00028188 | 8379 | 0.076818 | 3878 | 2.1523e-05 | 9388
MORMON 110210274 | MORMON 1102 | 163211102 |  | 10.9716 | 0.31407 |  | 184 | 0.00029565 | 8091 | 0.074141 | 4539 | 2.1522e-05 | 9389
CATLETT 11022512 | CATLETT 1102 | 153761102 |  | 4.3378 | 0.16994 |  | 72.3333 | 0.00029201 | 8164 | 0.074189 | 4527 | 2.1516e-05 | 9390
HERDLYN 1102608254 | HERDLYN 1102 | 163741102 |  | 21.5979 | 1.6242 |  | 402 | 0.00031983 | 7632 | 0.067668 | 5518 | 2.1509e-05 | 9391
RIVERBANK 1711CB | RIVERBANK 1711 | 163191711 |  | 13.4333 | 1.0166 |  | 235.8333 | 0.00028449 | 8321 | 0.07682 | 3875 | 2.1508e-05 | 9392
LE GRAND 1106141672 | LE GRAND 1106 | 255361106 |  | 15.7146 | 0.60697 |  | 258.3333 | 0.00028196 | 8377 | 0.076505 | 4013 | 2.1508e-05 | 9393
MC CALL 1106640598 | MC CALL 1106 | 254121106 |  | 22.521 | 3.9633 |  | 418.5 | 0.00028015 | 8417 | 0.076937 | 3803 | 2.1503e-05 | 9394
DAIRYLAND 1113CB | DAIRYLAND 1113 | 252421113 |  | 19.4779 | 0.97972 |  | 328.25 | 0.0002795 | 8430 | 0.077029 | 3743 | 2.1499e-05 | 9395
BIOLA 11016270 | BIOLA 1101 | 252211101 |  | 10.4437 | 1.0819 |  | 194 | 0.00027948 | 8432 | 0.077149 | 3649 | 2.1496e-05 | 9396
EL PECO 1106CB | EL PECO 1106 | 253981106 |  | 10.1847 | 0.57247 |  | 175.5 | 0.00027762 | 8476 | 0.0774 | 3397 | 2.1488e-05 | 9397
MIDDLE RIVER 110395572 | MIDDLE RIVER 1103 | 162091103 |  | 6.8037 | 0.32409 |  | 132 | 0.00028205 | 8375 | 0.076131 | 4152 | 2.1484e-05 | 9398
LEMOORE 1101719720 | LEMOORE 1101 | 253601101 |  | 4.8211 | 0.22749 |  | 87.5 | 0.00029487 | 8111 | 0.074996 | 4415 | 2.1481e-05 | 9399
GUERNSEY 1103849262 | GUERNSEY 1103 | 252661103 |  | 19.7827 | 1.4539 |  | 335.5 | 0.00027874 | 8451 | 0.077089 | 3700 | 2.1479e-05 | 9400
RICE 110379200 | RICE 1103 | 62831103 |  | 13.5145 | 0.94503 |  | 241 | 0.00028149 | 8387 | 0.076717 | 3924 | 2.1478e-05 | 9401
SAN JOAQUIN 1108R1700 | SAN JOAQUIN 1108 | 252361108 |  | 19.4 | 0.82312 |  | 355 | 0.00028372 | 8336 | 0.075893 | 4233 | 2.1472e-05 | 9402
EAST NICOLAUS 11011358 | EAST NICOLAUS 1101 | 152151101 |  | 11.434 | 0.49174 |  | 202 | 0.00028137 | 8391 | 0.076447 | 4035 | 2.1471e-05 | 9403
EL PECO 11054010 | EL PECO 1105 | 253981105 |  | 16.0157 | 1.3625 |  | 281 | 0.00027736 | 8482 | 0.0774 | 3397 | 2.1468e-05 | 9404
GRAND ISLAND 222322452 | GRAND ISLAND 2223 | 62462223 |  | 14.1202 | 1.0709 |  | 260.6667 | 0.00027897 | 8447 | 0.076966 | 3785 | 2.1463e-05 | 9405
STROUD 1104R435 | STROUD 1104 | 253661104 |  | 5.0536 | 0.24251 |  | 90.8333 | 0.0002958 | 8089 | 0.073042 | 4658 | 2.146e-05 | 9406
MC CALL 11064282F | MC CALL 1106 | 254121106 |  | 0.73678 | 0.054851 |  | 11.5 | 0.00027725 | 8486 | 0.0774 | 3397 | 2.1459e-05 | 9407
WATERLOO 110112968 | WATERLOO 1101 | 163151101 |  | 9.3752 | 1.1287 |  | 177.5 | 0.00028496 | 8309 | 0.076094 | 4164 | 2.1454e-05 | 9408
STROUD 110449602 | STROUD 1104 | 253661104 |  | 0.075389 | 0 |  | 3 | 0.00040417 | 6408 | 0.053073 | 8251 | 2.145e-05 | 9409
BELLEVUE 1102182 | BELLEVUE 1102 | 43181102 |  | 7.7238 | 1.4864 |  | 134 | 0.00032058 | 7619 | 0.067025 | 5995 | 2.145e-05 | 9410
BASALT 1106783176 | BASALT 1106 | 42461106 |  | 12.9416 | 0.42309 |  | 234.5 | 0.00031661 | 7690 | 0.067849 | 5459 | 2.1437e-05 | 9411
LAKEVIEW 1107CB | LAKEVIEW 1107 | 253411107 |  | 6.592 | 0.041826 |  | 97 | 0.00030775 | 7852 | 0.070059 | 5033 | 2.1435e-05 | 9412
BOWLES 11016220 | BOWLES 1101 | 253531101 |  | 26.8237 | 3.4239 |  | 474 | 0.00027819 | 8467 | 0.077143 | 3654 | 2.1425e-05 | 9413
ATWATER 110264566 | ATWATER 1102 | 253611102 |  | 4.885 | 0.56238 |  | 87.3333 | 0.0002769 | 8495 | 0.07722 | 3572 | 2.1422e-05 | 9414
EAST NICOLAUS 1101CB | EAST NICOLAUS 1101 | 152151101 |  | 7.8221 | 0.25116 |  | 138 | 0.00027801 | 8469 | 0.077224 | 3564 | 2.1409e-05 | 9415
PLAINFIELD 110146254 | PLAINFIELD 1101 | 63441101 |  | 22.409 | 1.0767 |  | 377 | 0.00028017 | 8416 | 0.076802 | 3886 | 2.1393e-05 | 9416
HALF MOON BAY 110155210 | HALF MOON BAY 1101 | 24101101 |  | 0.33721 | 0 |  | 6.8333 | 0.00031672 | 7687 | 0.067477 | 5617 | 2.1385e-05 | 9417
GRAND ISLAND 22272802 | GRAND ISLAND 2227 | 62462227 |  | 22.4537 | 1.5026 |  | 378 | 0.00028055 | 8407 | 0.076233 | 4116 | 2.1382e-05 | 9418
WILLIAMS 110230222 | WILLIAMS 1102 | 62051102 |  | 3.5927 | 0.10251 |  | 71.5 | 0.00030078 | 8002 | 0.073589 | 4596 | 2.1382e-05 | 9419
BAHIA 1104997506 | BAHIA 1104 | 43251104 |  | 0.017519 | 0 |  | 0.83333 | 0.00031861 | 7658 | 0.067105 | 5893 | 2.138e-05 | 9420
PEASE 11031306 | PEASE 1103 | 153751103 |  | 32.3963 | 2.7089 |  | 575.3333 | 0.00028661 | 8270 | 0.075756 | 4276 | 2.1379e-05 | 9421
MARYSVILLE 1108740650 | MARYSVILLE 1108 | 152011108 |  | 8.0154 | 0.19109 |  | 146.5 | 0.00031608 | 7697 | 0.067638 | 5531 | 2.1364e-05 | 9422
ANGIOLA 110241516 | ANGIOLA 1102 | 252151102 |  | 2.825 | 0.011866 |  | 47 | 0.00030019 | 8014 | 0.072255 | 4751 | 2.1363e-05 | 9423
FRENCH CAMP 11028038 | FRENCH CAMP 1102 | 163291102 |  | 31.2183 | 1.764 |  | 561.5 | 0.00027656 | 8502 | 0.077242 | 3541 | 2.1361e-05 | 9424
WATERLOO 1102CB | WATERLOO 1102 | 163151102 |  | 7.6132 | 0.79437 |  | 141.5 | 0.00027584 | 8515 | 0.0774 | 3397 | 2.135e-05 | 9425
WILSON 1102CB | WILSON 1102 | 254301102 |  | 10.7793 | 0.87305 |  | 178.3333 | 0.0002939 | 8130 | 0.073742 | 4576 | 2.135e-05 | 9426
CLARKSVILLE 210955666 | CLARKSVILLE 2109 | 153612109 |  | 1.8827 | 0.25732 |  | 28.5 | 0.00031863 | 7657 | 0.067 | 6057 | 2.1348e-05 | 9427
TEJON 1103CB | TEJON 1103 | 252931103 |  | 13.1216 | 0.42691 |  | 210.75 | 0.0002885 | 8225 | 0.073712 | 4580 | 2.1348e-05 | 9428
PARLIER 11046800 | PARLIER 1104 | 252291104 |  | 2.4977 | 0.23393 |  | 42.5 | 0.00027577 | 8517 | 0.0774 | 3397 | 2.1345e-05 | 9429
SAN JOAQUIN 1112CB | SAN JOAQUIN 1112 | 252361112 |  | 14.4438 | 0.31355 |  | 253.5 | 0.00028279 | 8357 | 0.075616 | 4307 | 2.1344e-05 | 9430
MC KEE 1107XR010 | MC KEE 1107 | 83531107 |  | 10.5864 | 2.6588 |  | 200.5 | 0.00031771 | 7672 | 0.067344 | 5706 | 2.1333e-05 | 9431
COTATI 110578286 | COTATI 1105 | 42271105 |  | 5.004 | 0.91715 |  | 87.5 | 0.00031829 | 7664 | 0.067 | 6057 | 2.1326e-05 | 9432
MIDDLE RIVER 1102CB | MIDDLE RIVER 1102 | 162091102 |  | 10.5169 | 0.21509 |  | 184.5 | 0.00027683 | 8498 | 0.077136 | 3660 | 2.1325e-05 | 9433
LAKEVIEW 11061632 | LAKEVIEW 1106 | 253411106 |  | 7.2544 | 0.24794 |  | 124.5 | 0.00029368 | 8138 | 0.07239 | 4732 | 2.131e-05 | 9434
VICTOR 110236800 | VICTOR 1102 | 163281102 |  | 9.3527 | 1.2223 |  | 166.5 | 0.00027532 | 8527 | 0.0774 | 3397 | 2.131e-05 | 9435
FULTON 1105921 | FULTON 1105 | 42561105 |  | 3.4083 | 0.55706 |  | 68 | 0.00031784 | 7670 | 0.067165 | 5841 | 2.1306e-05 | 9436
TEVIS 21044401 | TEVIS 2104 | 255322104 |  | 4.239 | 0.08587 |  | 61.3333 | 0.00028469 | 8315 | 0.076636 | 3965 | 2.1303e-05 | 9437
RAINBOW 1106R610 | RAINBOW 1106 | 254441106 |  | 13.6333 | 1.4319 |  | 250 | 0.00028224 | 8371 | 0.075915 | 4222 | 2.1293e-05 | 9438
MORGAN HILL 2110814616 | MORGAN HILL 2110 | 83242110 | TRUE | 2.4064 | 0.21732 | 0.063945 | 53 | 0.00030382 | 7934 | 0.070077 | 5026 | 2.1291e-05 | 9439
BARRY 11032020 | BARRY 1103 | 152111103 |  | 14.2287 | 1.2135 |  | 269.5 | 0.00027533 | 8526 | 0.077341 | 3420 | 2.1289e-05 | 9440
SCHINDLER 11149120 | SCHINDLER 1114 | 252891114 |  | 2.7112 | 0.022935 |  | 57.5 | 0.00031306 | 7752 | 0.067794 | 5476 | 2.1278e-05 | 9441
WHEATLAND 110436326 | WHEATLAND 1104 | 152811104 |  | 12.4731 | 2.2201 |  | 223.5 | 0.00031565 | 7704 | 0.067419 | 5652 | 2.1275e-05 | 9442
CAMDEN 1104CB | CAMDEN 1104 | 252301104 |  | 30.1542 | 2.9999 |  | 512.8333 | 0.00027505 | 8532 | 0.077314 | 3454 | 2.1268e-05 | 9443
CAPAY 110286444 | CAPAY 1102 | 102111102 |  | 22.2021 | 2.6898 |  | 405 | 0.00031145 | 7777 | 0.068659 | 5248 | 2.1251e-05 | 9444
JACINTO 110247800 | JACINTO 1102 | 102851102 |  | 8.9141 | 0.50819 |  | 160 | 0.00028799 | 8235 | 0.073922 | 4563 | 2.1251e-05 | 9445
PRUNEDALE 110736920 | PRUNEDALE 1107 | 182961107 |  | 5.9557 | 0.5665 |  | 111.5 | 0.00031493 | 7715 | 0.067433 | 5648 | 2.1246e-05 | 9446
EL PECO 11026030 | EL PECO 1102 | 253981102 |  | 6.5013 | 0.16103 |  | 109 | 0.00027446 | 8545 | 0.0774 | 3397 | 2.1243e-05 | 9447
SANTA MARIA 1105M42 | SANTA MARIA 1105 | 182671105 |  | 10.3093 | 0.31757 |  | 179.3333 | 0.0003104 | 7799 | 0.068566 | 5270 | 2.1232e-05 | 9448
SAN JOAQUIN 1112874392 | SAN JOAQUIN 1112 | 252361112 |  | 11.407 | 0.7693 |  | 188.5 | 0.00027563 | 8521 | 0.077021 | 3749 | 2.1227e-05 | 9449
TEVIS 2104CB | TEVIS 2104 | 255322104 |  | 13.3793 | 0.04045 |  | 215.1667 | 0.0002908 | 8181 | 0.075968 | 4207 | 2.1214e-05 | 9450
BARRY 1101CB | BARRY 1101 | 152111101 |  | 32.0196 | 2.3349 |  | 559.8333 | 0.00027968 | 8428 | 0.076288 | 4095 | 2.1212e-05 | 9451
IGNACIO 11021240 | IGNACIO 1102 | 42481102 |  | 7.1779 | 1.0607 |  | 137.5 | 0.00034178 | 7277 | 0.063681 | 6584 | 2.1211e-05 | 9452
BOWLES 11046190 | BOWLES 1104 | 253531104 |  | 14.4386 | 3.2286 |  | 278 | 0.00028083 | 8399 | 0.076046 | 4183 | 2.121e-05 | 9453
CARUTHERS 1105553830 | CARUTHERS 1105 | 252371105 |  | 0.083118 | 0 |  | 0.83333 | 0.00027387 | 8553 | 0.0774 | 3396 | 2.1197e-05 | 9454
MORMON 1102344118 | MORMON 1102 | 163211102 |  | 2.0419 | 0.022627 |  | 33.5 | 0.00027694 | 8494 | 0.077037 | 3740 | 2.1192e-05 | 9455
MARICOPA 1101CB | MARICOPA 1101 | 254211101 |  | 11.7772 | 0.077544 |  | 211.5 | 0.00031535 | 7710 | 0.067199 | 5810 | 2.1189e-05 | 9456
CORCORAN 1106176636 | CORCORAN 1106 | 252171106 |  | 18.7283 | 0.51628 |  | 329.3333 | 0.00027946 | 8433 | 0.076616 | 3976 | 2.1186e-05 | 9457
RIVERBANK 17159020 | RIVERBANK 1715 | 163191715 |  | 24.6655 | 2.3435 |  | 438 | 0.00027529 | 8529 | 0.077086 | 3702 | 2.1186e-05 | 9458
KEARNEY 1104D4939 | KEARNEY 1104 | 252701104 |  | 4.0913 | 0.44862 |  | 69.5 | 0.00027372 | 8560 | 0.0774 | 3397 | 2.1186e-05 | 9459
CANAL 110192709 | CANAL 1101 | 252091101 |  | 28.4368 | 1.5254 |  | 497 | 0.00028363 | 8339 | 0.075716 | 4287 | 2.1183e-05 | 9460
CASTROVILLE 2103791564 | CASTROVILLE 2103 | 182352103 |  | 5.3732 | 0.29329 |  | 106 | 0.00031522 | 7711 | 0.067196 | 5815 | 2.1175e-05 | 9461
OLD RIVER 11023310 | OLD RIVER 1102 | 252821102 |  | 17.0938 | 0.73633 |  | 286.5 | 0.00027656 | 8504 | 0.076796 | 3890 | 2.1172e-05 | 9462
SANTA NELLA 11049600 | SANTA NELLA 1104 | 254051104 |  | 15.2719 | 0.8596 |  | 255.5 | 0.00027971 | 8426 | 0.07612 | 4156 | 2.1171e-05 | 9463
CARRIZO PLAINS 1101CB | CARRIZO PLAINS 1101 | 253461101 |  | 0.029534 | 0 |  | 0.5 | 0.00031541 | 7706 | 0.067105 | 5893 | 2.1166e-05 | 9464
MC CALL 1108406358 | MC CALL 1108 | 254121108 |  | 0.15877 | 0 |  | 3 | 0.00037206 | 6805 | 0.057127 | 7419 | 2.1152e-05 | 9465
WATSONVILLE 2101905574 | WATSONVILLE 2101 | 83332101 |  | 1.8227 | 0.13845 |  | 30 | 0.00030691 | 7869 | 0.067693 | 5511 | 2.1149e-05 | 9466
SEMITROPIC 1104CB | SEMITROPIC 1104 | 252901104 |  | 7.9803 | 0.21766 |  | 129.3333 | 0.00027568 | 8518 | 0.076906 | 3827 | 2.1145e-05 | 9467
WRIGHT 1110288242 | WRIGHT 1110 | 254641110 |  | 3.6799 | 0.15836 |  | 59.5 | 0.00027315 | 8580 | 0.0774 | 3397 | 2.1142e-05 | 9468
FRENCH CAMP 11021404 | FRENCH CAMP 1102 | 163291102 |  | 25.3427 | 1.3895 |  | 441.5 | 0.00027342 | 8570 | 0.077347 | 3417 | 2.1141e-05 | 9469
DAVIS 11128902 | DAVIS 1112 | 62041112 |  | 29.805 | 2.3974 |  | 488.5 | 0.00029052 | 8188 | 0.075328 | 4361 | 2.1141e-05 | 9470
PEACHTON 1102181815 | PEACHTON 1102 | 103241102 |  | 3.0631 | 0.27644 |  | 53.5 | 0.00027384 | 8554 | 0.077253 | 3535 | 2.1127e-05 | 9471
SANTA NELLA 110438984 | SANTA NELLA 1104 | 254051104 |  | 8.1368 | 0.31837 |  | 135.5 | 0.00027564 | 8519 | 0.076629 | 3971 | 2.1125e-05 | 9472
MAGUNDEN 11064849 | MAGUNDEN 1106 | 252771106 |  | 1.0441 | 0 |  | 18 | 0.00031473 | 7725 | 0.067102 | 5897 | 2.112e-05 | 9473
DOLAN ROAD 1101CB | DOLAN ROAD 1101 | 182381101 |  | 8.355 | 1.0781 |  | 145.3333 | 0.00031522 | 7712 | 0.067 | 6058 | 2.1119e-05 | 9474
TEMBLOR 2103CUST | TEMBLOR 2103 | 252552103 |  | 0.017148 | 0 |  | 0.25 | 0.0003151 | 7713 | 0.067 | 6057 | 2.1112e-05 | 9475
FIGARDEN 2102752669 | FIGARDEN 2102 | 254552102 |  | 3.2992 | 0.90049 |  | 72 | 0.00028324 | 8345 | 0.074767 | 4448 | 2.1111e-05 | 9476
LAMONT 110280580 | LAMONT 1102 | 253911102 |  | 4.9172 | 0.09503 |  | 84 | 0.00030817 | 7840 | 0.068512 | 5284 | 2.1109e-05 | 9477
GOOSE LAKE 1106CB | GOOSE LAKE 1106 | 254201106 |  | 5.3767 | 0.093935 |  | 89.3333 | 0.00027903 | 8442 | 0.076143 | 4144 | 2.1107e-05 | 9478
VACA DIXON 110355570 | VACA DIXON 1103 | 63591103 |  | 4.0428 | 0.11361 |  | 69 | 0.00027456 | 8540 | 0.076819 | 3876 | 2.11e-05 | 9479
MERCED 11144320 | MERCED 1114 | 252801114 |  | 15.3172 | 0.4881 |  | 252.8333 | 0.00027696 | 8493 | 0.076687 | 3942 | 2.1098e-05 | 9480
KERMAN 1104CB | KERMAN 1104 | 252711104 |  | 17.2459 | 0.83298 |  | 290.2 | 0.00027362 | 8563 | 0.077178 | 3617 | 2.1092e-05 | 9481
KINGSBURG 1113CB | KINGSBURG 1113 | 252241113 |  | 14.7336 | 1.9837 |  | 263.45 | 0.00027246 | 8597 | 0.0774 | 3397 | 2.1088e-05 | 9482
HENRIETTA 1108CB | HENRIETTA 1108 | 252681108 |  | 11.7812 | 0.29489 |  | 208 | 0.00027331 | 8576 | 0.07709 | 3698 | 2.1088e-05 | 9483
TEMPLETON 21085777 | TEMPLETON 2108 | 183052108 |  | 5.7001 | 2.2853 |  | 109.5 | 0.0003209 | 7614 | 0.065761 | 6312 | 2.1084e-05 | 9484
PACIFICA 1101777484 | PACIFICA 1101 | 22811101 | FALSE | 3.5758 | 0.0030983 | 0.74129 | 46.5 | 0.00036499 | 6918 | 0.05535 | 7699 | 2.1079e-05 | 9485
GUSTINE 11019120 | GUSTINE 1101 | 163111101 |  | 11.8248 | 0.63447 |  | 201 | 0.00027383 | 8557 | 0.077158 | 3636 | 2.1075e-05 | 9486
DUNNIGAN 110137552 | DUNNIGAN 1101 | 63811101 |  | 9.7824 | 0.93239 |  | 170 | 0.00029027 | 8192 | 0.074038 | 4552 | 2.1071e-05 | 9487
GERBER 1102585548 | GERBER 1102 | 103391102 |  | 0.67036 | 0 |  | 13.5 | 0.00031431 | 7733 | 0.067017 | 6006 | 2.1065e-05 | 9488
SANTA NELLA 1101594884 | SANTA NELLA 1101 | 254051101 |  | 1.8143 | 0.12003 |  | 29.25 | 0.00027215 | 8602 | 0.0774 | 3397 | 2.1064e-05 | 9489
LAKEVILLE 1101CB | LAKEVILLE 1101 | 43371101 |  | 5.3442 | 0.19572 |  | 111 | 0.00031962 | 7637 | 0.066991 | 6063 | 2.106e-05 | 9490
MC MULLIN 11046310 | MC MULLIN 1104 | 254411104 |  | 8.7703 | 0 |  | 149.5 | 0.00027725 | 8487 | 0.076213 | 4125 | 2.106e-05 | 9491
ARBUCKLE 110237526 | ARBUCKLE 1102 | 62081102 |  | 14.592 | 0.34688 |  | 250 | 0.00027928 | 8440 | 0.075751 | 4277 | 2.1052e-05 | 9492
BOWLES 110136522 | BOWLES 1101 | 253531101 |  | 11.4306 | 1.5609 |  | 203.5 | 0.00027249 | 8594 | 0.077323 | 3438 | 2.1051e-05 | 9493
COPUS 11041447 | COPUS 1104 | 253871104 |  | 9.4354 | 0.036818 |  | 162.8333 | 0.00030478 | 7915 | 0.069363 | 5135 | 2.1048e-05 | 9494
WEEDPATCH 110668866 | WEEDPATCH 1106 | 252971106 |  | 18.3893 | 0.91001 |  | 312.5 | 0.00027373 | 8559 | 0.076889 | 3838 | 2.1045e-05 | 9495
BAKERSFIELD 210447676 | BAKERSFIELD 2104 | 253372104 |  | 0.036609 | 0 |  | 1.5 | 0.00027174 | 8614 | 0.0774 | 3397 | 2.1032e-05 | 9496
WEEDPATCH 1106205044 | WEEDPATCH 1106 | 252971106 |  | 3.7072 | 0.073315 |  | 62 | 0.00027716 | 8491 | 0.075969 | 4205 | 2.1032e-05 | 9497
EAST NICOLAUS 11031258 | EAST NICOLAUS 1103 | 152151103 |  | 24.6205 | 1.2287 |  | 407.5 | 0.00027899 | 8446 | 0.075514 | 4336 | 2.1022e-05 | 9498
SPENCE 1103581602 | SPENCE 1103 | 182201103 |  | 1.0676 | 0.12771 |  | 23.5 | 0.00031359 | 7744 | 0.067 | 6057 | 2.1011e-05 | 9499
RIVERBANK 17127154 | RIVERBANK 1712 | 163191712 |  | 13.3508 | 0.99727 |  | 230.5 | 0.00027142 | 8622 | 0.0774 | 3397 | 2.1008e-05 | 9500
AVENA 170113538 | AVENA 1701 | 163571701 |  | 24.0433 | 1.0951 |  | 411.5 | 0.00027191 | 8610 | 0.077282 | 3501 | 2.1007e-05 | 9501
PANOCHE 1102CB | PANOCHE 1102 | 253671102 |  | 1.4767 | 0 |  | 21.3333 | 0.00028401 | 8330 | 0.074069 | 4545 | 2.1006e-05 | 9502
PEACHTON 110255948 | PEACHTON 1102 | 103241102 |  | 20.7594 | 0.63922 |  | 362.5 | 0.00027202 | 8608 | 0.077222 | 3565 | 2.0998e-05 | 9503
GATES 1101934088 | GATES 1101 | 253931101 |  | 6.3315 | 0.14427 |  | 105 | 0.00031438 | 7731 | 0.067129 | 5875 | 2.0995e-05 | 9504
TUDOR 11027448 | TUDOR 1102 | 153711102 |  | 8.6571 | 0.53049 |  | 155.5 | 0.00027602 | 8512 | 0.076494 | 4020 | 2.0992e-05 | 9505
MC CALL 11076090 | MC CALL 1107 | 254121107 |  | 36.4213 | 6.8547 |  | 693 | 0.00027389 | 8552 | 0.076928 | 3810 | 2.0985e-05 | 9506
LAKEVILLE 1102530 | LAKEVILLE 1102 | 43371102 |  | 4.5895 | 0.32861 |  | 95.5 | 0.00030969 | 7810 | 0.067763 | 5488 | 2.0985e-05 | 9507
KINGSBURG 11166000 | KINGSBURG 1116 | 252241116 |  | 5.3381 | 1.153 |  | 100.5 | 0.00027343 | 8567 | 0.077001 | 3760 | 2.0983e-05 | 9508
SAN MIGUEL 1106N38 | SAN MIGUEL 1106 | 182661106 |  | 2.386 | 0.051584 |  | 38.5 | 0.00032489 | 7538 | 0.064691 | 6472 | 2.0983e-05 | 9509
BONITA 1103974448 | BONITA 1103 | 255391103 |  | 2.3587 | 0.12082 |  | 41.5 | 0.00028758 | 8242 | 0.073296 | 4635 | 2.0981e-05 | 9510
MC MULLIN 11066180 | MC MULLIN 1106 | 254411106 |  | 9.0897 | 1.1946 |  | 163 | 0.00027757 | 8478 | 0.075907 | 4228 | 2.098e-05 | 9511
KINGSBURG 11166340 | KINGSBURG 1116 | 252241116 |  | 30.7315 | 5.6068 |  | 564.5 | 0.00028002 | 8422 | 0.075604 | 4311 | 2.098e-05 | 9512
GLENN 11012010 | GLENN 1101 | 102601101 |  | 15.3587 | 2.7244 |  | 277 | 0.00031179 | 7773 | 0.06728 | 5744 | 2.0966e-05 | 9513
PIT NO 1 11019702 | PIT NO 1 1101 | 103721101 | FALSE | 9.18 | 0.50621 | 0.65432 | 169 | 0.00018025 | 10348 | 0.11153 | 3290 | 2.0959e-05 | 9514
GERBER 110253108 | GERBER 1102 | 103391102 |  | 5.6531 | 0.31723 |  | 90 | 0.0003086 | 7827 | 0.067931 | 5423 | 2.0959e-05 | 9515
SAN BENITO 210163516 | SAN BENITO 2101 | 182742101 |  | 22.8491 | 1.9412 |  | 410.5 | 0.00030922 | 7818 | 0.067857 | 5455 | 2.0937e-05 | 9516
GUERNSEY 11028390 | GUERNSEY 1102 | 252661102 |  | 7.0253 | 0.44461 |  | 118.5 | 0.0002705 | 8637 | 0.0774 | 3397 | 2.0936e-05 | 9517
FIREBAUGH 110383056 | FIREBAUGH 1103 | 253471103 |  | 7.2026 | 0.4715 |  | 124 | 0.00027688 | 8496 | 0.075981 | 4204 | 2.0907e-05 | 9518
RICE 11043034 | RICE 1104 | 62831104 |  | 10.4901 | 0.46221 |  | 189.5 | 0.00028401 | 8331 | 0.074561 | 4479 | 2.0904e-05 | 9519
HONCUT 110294298 | HONCUT 1102 | 103211102 |  | 8.845 | 0.93127 |  | 153 | 0.00028149 | 8388 | 0.075679 | 4292 | 2.0883e-05 | 9520
SANGER 111837420 | SANGER 1118 | 252351118 |  | 11.9429 | 2.2554 |  | 209 | 0.00027031 | 8644 | 0.077283 | 3497 | 2.0878e-05 | 9521
SANTA RITA 1105CB | SANTA RITA 1105 | 253541105 |  | 35.0146 | 2.4095 |  | 624 | 0.00027133 | 8624 | 0.076964 | 3787 | 2.087e-05 | 9522
SHAFTER 11031197 | SHAFTER 1103 | 253651103 |  | 20.3979 | 0.44464 |  | 341 | 0.00027198 | 8609 | 0.076961 | 3789 | 2.0855e-05 | 9523
GRAND ISLAND 22278862 | GRAND ISLAND 2227 | 62462227 |  | 16.4242 | 0.84012 |  | 331.5 | 0.0002763 | 8508 | 0.075808 | 4263 | 2.0854e-05 | 9524
AIRWAYS 1107752346 | AIRWAYS 1107 | 252041107 |  | 0.84175 | 0.018397 |  | 15.5 | 0.00028701 | 8255 | 0.074261 | 4520 | 2.0853e-05 | 9525
HAMILTON A 110175208 | HAMILTON A 1101 | 102121101 |  | 8.6223 | 0.90344 |  | 163.5 | 0.00030549 | 7898 | 0.068783 | 5226 | 2.085e-05 | 9526
RIVERBANK 1714CB | RIVERBANK 1714 | 163191714 |  | 12.0791 | 0.87909 |  | 202 | 0.00027472 | 8536 | 0.076599 | 3983 | 2.0834e-05 | 9527
WELLFIELD 11022842 | WELLFIELD 1102 | 254291102 |  | 5.1813 | 0.10903 |  | 89.5 | 0.00030629 | 7881 | 0.068112 | 5381 | 2.0834e-05 | 9528
MORGAN HILL 2109XR104 | MORGAN HILL 2109 | 83242109 |  | 15.7315 | 2.4608 |  | 315.5 | 0.00031121 | 7782 | 0.066899 | 6091 | 2.0825e-05 | 9529
GATES 1105107640 | GATES 1105 | 253931105 |  | 19.3344 | 1.3407 |  | 327.5 | 0.00028233 | 8368 | 0.073842 | 4567 | 2.0824e-05 | 9530
WILKINS SLOUGH 11011704 | WILKINS SLOUGH 1101 | 62771101 |  | 15.6784 | 1.2654 |  | 289.5 | 0.00027266 | 8588 | 0.076589 | 3987 | 2.0818e-05 | 9531
RIVERBANK 17159030 | RIVERBANK 1715 | 163191715 |  | 25.9721 | 2.2918 |  | 458.5 | 0.00027062 | 8636 | 0.077028 | 3745 | 2.0814e-05 | 9532
SALMON CREEK 1101668 | SALMON CREEK 1101 | 43161101 |  | 3.5613 | 0.37368 |  | 72.5 | 0.00030834 | 7835 | 0.067444 | 5642 | 2.0813e-05 | 9533
MC MULLIN 1106CB | MC MULLIN 1106 | 254411106 |  | 30.5839 | 3.0519 |  | 526.3333 | 0.00027206 | 8606 | 0.076709 | 3930 | 2.0813e-05 | 9534
BARRY 1102CB | BARRY 1102 | 152111102 |  | 17.7129 | 2.7554 |  | 324.3333 | 0.00027027 | 8647 | 0.077141 | 3655 | 2.081e-05 | 9535
KNIGHTS LANDING 11026872 | KNIGHTS LANDING 1102 | 62721102 |  | 21.6746 | 0.64295 |  | 424 | 0.00027003 | 8655 | 0.077133 | 3661 | 2.0805e-05 | 9536
PUTAH CREEK 11052777 | PUTAH CREEK 1105 | 63681105 |  | 3.7619 | 0.4666 |  | 66 | 0.00026866 | 8681 | 0.0774 | 3397 | 2.0795e-05 | 9537
LE GRAND 111212020 | LE GRAND 1112 | 255361112 |  | 44.7638 | 2.4826 |  | 787 | 0.00027117 | 8628 | 0.076842 | 3865 | 2.0793e-05 | 9538
WELLFIELD 1102CB | WELLFIELD 1102 | 254291102 |  | 32.6895 | 1.762 |  | 537.5 | 0.00030132 | 7984 | 0.069286 | 5148 | 2.0792e-05 | 9539
NEWARK 21KV 2104LR562 | NEWARK 21KV 2104 | 12232104 |  | 1.9672 | 0 |  | 35.5 | 0.00029093 | 8180 | 0.071525 | 4827 | 2.0791e-05 | 9540
AIRWAYS 1107R1250 | AIRWAYS 1107 | 252041107 |  | 9.1071 | 0.65258 |  | 155.5 | 0.00026861 | 8682 | 0.0774 | 3397 | 2.079e-05 | 9541
LOGAN CREEK 210175318 | LOGAN CREEK 2101 | 103142101 |  | 8.642 | 0.19809 |  | 141.5 | 0.00030125 | 7987 | 0.069189 | 5164 | 2.0785e-05 | 9542
MIDWAY 1103CB | MIDWAY 1103 | 252611103 |  | 18.8032 | 0.4889 |  | 306.3333 | 0.00027384 | 8555 | 0.076351 | 4068 | 2.0776e-05 | 9543
WHEATLAND 11027378 | WHEATLAND 1102 | 152811102 |  | 7.64 | 0.47852 |  | 154.5 | 0.00027677 | 8500 | 0.076196 | 4129 | 2.077e-05 | 9544
DAIRYLAND 11135450 | DAIRYLAND 1113 | 252421113 |  | 25.8289 | 1.6503 |  | 442.5 | 0.0002704 | 8642 | 0.076924 | 3812 | 2.077e-05 | 9545
COVELO 110196896 | COVELO 1101 | 43061101 |  | 7.4079 | 0.22042 |  | 118 | 0.00021586 | 9762 | 0.091467 | 3336 | 2.0761e-05 | 9546
GOOSE LAKE 2104922100 | GOOSE LAKE 2104 | 254202104 |  | 5.3993 | 0.15686 |  | 99 | 0.00028309 | 8353 | 0.073266 | 4641 | 2.0761e-05 | 9547
EL PECO 1105CB | EL PECO 1105 | 253981105 |  | 17.1244 | 0.65954 |  | 284.5 | 0.00026868 | 8680 | 0.077314 | 3453 | 2.0761e-05 | 9548
WILSON 1103873156 | WILSON 1103 | 254301103 |  | 4.0783 | 0.29702 |  | 75 | 0.00027024 | 8648 | 0.077075 | 3712 | 2.076e-05 | 9549
ORO LOMA 11153400 | ORO LOMA 1115 | 255371115 |  | 34.9943 | 3.1917 |  | 616.5 | 0.00026851 | 8686 | 0.077321 | 3441 | 2.0758e-05 | 9550
WASCO 11011294 | WASCO 1101 | 252961101 |  | 5.812 | 0.073673 |  | 97.5 | 0.00026815 | 8695 | 0.0774 | 3397 | 2.0755e-05 | 9551
VACA DIXON 11036822 | VACA DIXON 1103 | 63591103 |  | 33.7104 | 2.0562 |  | 586.5 | 0.00027564 | 8520 | 0.075627 | 4305 | 2.0754e-05 | 9552
REEDLEY 11127230 | REEDLEY 1112 | 252341112 |  | 1.8838 | 0.44455 |  | 34 | 0.00029766 | 8056 | 0.070365 | 4968 | 2.0752e-05 | 9553
CATLETT 110590956 | CATLETT 1105 | 153761105 |  | 14.6845 | 0.47567 |  | 271.5 | 0.00027205 | 8607 | 0.076806 | 3883 | 2.0749e-05 | 9554
COLUSA 110137640 | COLUSA 1101 | 62021101 |  | 3.3984 | 0.16614 |  | 67.3333 | 0.00028535 | 8299 | 0.074712 | 4456 | 2.0748e-05 | 9555
KEARNEY 110497774 | KEARNEY 1104 | 252701104 |  | 23.5269 | 3.6071 |  | 425 | 0.00026888 | 8677 | 0.077174 | 3622 | 2.074e-05 | 9556
CAMDEN 1103CB | CAMDEN 1103 | 252301103 |  | 24.5306 | 2.8946 |  | 420.3333 | 0.00026909 | 8673 | 0.077296 | 3480 | 2.0737e-05 | 9557
TWISSELMAN 21053264 | TWISSELMAN 2105 | 254402105 |  | 10.1716 | 0.066565 |  | 196 | 0.00028531 | 8301 | 0.073839 | 4568 | 2.0736e-05 | 9558
CLEAR LAKE 110181976 | CLEAR LAKE 1101 | 42141101 |  | 2.6761 | 0.56311 |  | 48 | 0.00030943 | 7815 | 0.067003 | 6040 | 2.0733e-05 | 9559
CHOWCHILLA 110411680 | CHOWCHILLA 1104 | 254101104 |  | 22.803 | 3.2099 |  | 386.8333 | 0.00027124 | 8626 | 0.076548 | 3998 | 2.073e-05 | 9560
DAIRYLAND 1112CB | DAIRYLAND 1112 | 252421112 |  | 46.8132 | 4.3736 |  | 808.75 | 0.00026795 | 8701 | 0.07737 | 3403 | 2.0729e-05 | 9561
WHEELER RIDGE 1102CB | WHEELER RIDGE 1102 | 253481102 |  | 32.0089 | 0.48385 |  | 529.8333 | 0.00026935 | 8669 | 0.077073 | 3715 | 2.0729e-05 | 9562
LOS COCHES 1102CB | LOS COCHES 1102 | 182151102 |  | 9.1412 | 0.1695 |  | 191 | 0.00030837 | 7834 | 0.06719 | 5821 | 2.0728e-05 | 9563
STOREY 11115390 | STOREY 1111 | 254611111 |  | 9.9865 | 1.3829 |  | 163.5 | 0.00031276 | 7755 | 0.06831 | 5331 | 2.0719e-05 | 9564
ORO LOMA 11063650 | ORO LOMA 1106 | 255371106 |  | 21.4013 | 0.96174 |  | 363.3333 | 0.00027327 | 8577 | 0.075607 | 4310 | 2.0705e-05 | 9565
GREEN VALLEY 21016625 | GREEN VALLEY 2101 | 83192101 |  | 4.0788 | 0.61988 |  | 72.3333 | 0.00030762 | 7853 | 0.067144 | 5859 | 2.0703e-05 | 9566
LAMONT 11069848 | LAMONT 1106 | 253911106 |  | 2.3806 | 0.41583 |  | 41 | 0.00027177 | 8613 | 0.076615 | 3978 | 2.0702e-05 | 9567
JACINTO 1101662526 | JACINTO 1101 | 102851101 |  | 0.14966 | 0.029624 |  | 3.5 | 0.00030891 | 7824 | 0.067 | 6057 | 2.0697e-05 | 9568
RICE 11023000 | RICE 1102 | 62831102 |  | 15.6205 | 0.55052 |  | 284.5 | 0.00027339 | 8572 | 0.076049 | 4182 | 2.0697e-05 | 9569
MC MULLIN 11066700 | MC MULLIN 1106 | 254411106 |  | 8.0966 | 0.34174 |  | 135.5 | 0.00026739 | 8711 | 0.0774 | 3397 | 2.0696e-05 | 9570
SISQUOC 1102113874 | SISQUOC 1102 | 182811102 |  | 6.4538 | 0.51636 |  | 111 | 0.00030429 | 7923 | 0.067889 | 5443 | 2.0693e-05 | 9571
MENDOTA 1102CB | MENDOTA 1102 | 252311102 |  | 36.4824 | 2.6942 |  | 612.0833 | 0.00029956 | 8028 | 0.073047 | 4657 | 2.0693e-05 | 9572
WESTLEY 1103434305 | WESTLEY 1103 | 162671103 |  | 4.8808 | 0.87214 |  | 87 | 0.0003075 | 7856 | 0.067635 | 5533 | 2.0692e-05 | 9573
MARICOPA 11023082 | MARICOPA 1102 | 254211102 |  | 7.5432 | 1.2838 |  | 137 | 0.00031009 | 7804 | 0.067211 | 5798 | 2.0691e-05 | 9574
KEARNEY 1106481832 | KEARNEY 1106 | 252701106 |  | 0.01548 | 0 |  | 1 | 0.00026724 | 8715 | 0.0774 | 3397 | 2.0684e-05 | 9575
HARDWICK 1101CB | HARDWICK 1101 | 253711101 |  | 6.5227 | 0.76744 |  | 107 | 0.00026723 | 8716 | 0.0774 | 3397 | 2.0684e-05 | 9576
TWISSELMAN 2105576496 | TWISSELMAN 2105 | 254402105 |  | 0.4791 | 0 |  | 8 | 0.00027832 | 8465 | 0.07545 | 4343 | 2.0682e-05 | 9577
CALFLAX 1104CB | CALFLAX 1104 | 253441104 |  | 18.5513 | 0.50015 |  | 313 | 0.00026942 | 8663 | 0.076806 | 3884 | 2.0682e-05 | 9578
ZAMORA 1106CB | ZAMORA 1106 | 63191106 |  | 25.6918 | 1.1213 |  | 454.3333 | 0.00028545 | 8297 | 0.073144 | 4649 | 2.0681e-05 | 9579
BAHIA 1104CB | BAHIA 1104 | 43251104 |  | 11.0674 | 0.90569 |  | 214.1667 | 0.00031093 | 7789 | 0.067108 | 5890 | 2.0676e-05 | 9580
GONZALES 110422418 | GONZALES 1104 | 182131104 |  | 12.3027 | 0.4296 |  | 249.5 | 0.00023718 | 9337 | 0.16391 | 3190 | 2.0675e-05 | 9581
TEMBLOR 110459326 | TEMBLOR 1104 | 252551104 |  | 4.7928 | 0.013613 |  | 91.8333 | 0.00030855 | 7829 | 0.067001 | 6051 | 2.0673e-05 | 9582
TEMPLETON 2111R38 | TEMPLETON 2111 | 183052111 |  | 2.4107 | 1.5565 |  | 51.5 | 0.000338 | 7337 | 0.062059 | 6756 | 2.0673e-05 | 9583
OLD RIVER 11013570 | OLD RIVER 1101 | 252821101 |  | 7.1163 | 0.097518 |  | 119 | 0.00026802 | 8700 | 0.077199 | 3595 | 2.0666e-05 | 9584
BASALT 11062103 | BASALT 1106 | 42461106 |  | 3.8536 | 0.88673 |  | 79.5 | 0.00030426 | 7925 | 0.067913 | 5433 | 2.0665e-05 | 9585
CHEROKEE 110270772 | CHEROKEE 1102 | 163651102 |  | 22.2566 | 2.6444 |  | 436.5 | 0.0002734 | 8571 | 0.076415 | 4047 | 2.0665e-05 | 9586
BUTTE 11072220 | BUTTE 1107 | 103081107 |  | 4.7041 | 0.35522 |  | 95.5 | 0.00029723 | 8064 | 0.070594 | 4942 | 2.0664e-05 | 9587
GUERNSEY 11028450 | GUERNSEY 1102 | 252661102 |  | 7.2202 | 0.49212 |  | 122 | 0.00027551 | 8523 | 0.075547 | 4330 | 2.065e-05 | 9588
CUYAMA 2101CB | CUYAMA 2101 | 253142101 |  | 4.1751 | 0.0080428 |  | 70.3333 | 0.00030815 | 7842 | 0.067 | 6058 | 2.0646e-05 | 9589
PANOCHE 1103CB | PANOCHE 1103 | 253671103 |  | 18.2345 | 0.30985 |  | 316.8333 | 0.00029686 | 8068 | 0.070368 | 4966 | 2.0639e-05 | 9590
KING CITY 1106666728 | KING CITY 1106 | 182031106 |  | 0.023268 | 0 |  | 0.5 | 0.00030799 | 7847 | 0.067 | 6057 | 2.0635e-05 | 9591
SHAFTER 11031195 | SHAFTER 1103 | 253651103 |  | 11.4831 | 0.47046 |  | 193.5 | 0.0002703 | 8645 | 0.076653 | 3958 | 2.0632e-05 | 9592
MOLINO 110381008 | MOLINO 1103 | 42571103 |  | 7.1864 | 2.6509 |  | 137 | 0.00030986 | 7806 | 0.067301 | 5729 | 2.0631e-05 | 9593
WILLIAMS 110130592 | WILLIAMS 1101 | 62051101 |  | 0.03618 | 0 |  | 1.5 | 0.00038873 | 6592 | 0.053073 | 8251 | 2.0631e-05 | 9594
CATLETT 110577448 | CATLETT 1105 | 153761105 |  | 11.3636 | 0.34402 |  | 202.5 | 0.00026676 | 8724 | 0.07728 | 3505 | 2.0621e-05 | 9595
PLAINFIELD 110620042 | PLAINFIELD 1106 | 63441106 |  | 10.4171 | 0.13442 |  | 182 | 0.00026741 | 8710 | 0.07718 | 3614 | 2.0615e-05 | 9596
UKIAH 1114544 | UKIAH 1114 | 42771114 |  | 6.8571 | 0.22161 |  | 116.5 | 0.00030619 | 7883 | 0.067553 | 5570 | 2.0614e-05 | 9597
AVENA 17025494 | AVENA 1702 | 163571702 |  | 39.4831 | 2.7214 |  | 673 | 0.00027466 | 8537 | 0.075427 | 4346 | 2.0612e-05 | 9598
ECHO SUMMIT 1101507864 | ECHO SUMMIT 1101 | 158031101 |  | 2.389 | 0.41088 |  | 42 | 0.00030634 | 7880 | 0.067267 | 5754 | 2.0598e-05 | 9599
GRAND ISLAND 22238852 | GRAND ISLAND 2223 | 62462223 |  | 13.8319 | 1.4106 |  | 265.3333 | 0.00026852 | 8685 | 0.076859 | 3852 | 2.0587e-05 | 9600
MERCED 1108900772 | MERCED 1108 | 252801108 |  | 14.4115 | 0.44556 |  | 247 | 0.00026815 | 8696 | 0.076879 | 3842 | 2.0584e-05 | 9601
EIGHT MILE 210641522 | EIGHT MILE 2106 | 163912106 |  | 25.0593 | 0.47239 |  | 442 | 0.00026845 | 8690 | 0.076751 | 3908 | 2.058e-05 | 9602
STONE CORRAL 11107320 | STONE CORRAL 1110 | 252921110 |  | 20.871 | 3.2571 |  | 366 | 0.00030349 | 7938 | 0.068293 | 5335 | 2.0576e-05 | 9603
RAINBOW 110694792 | RAINBOW 1106 | 254441106 |  | 1.3671 | 0 |  | 24 | 0.00026958 | 8661 | 0.076745 | 3914 | 2.0575e-05 | 9604
MERIDIAN 110169484 | MERIDIAN 1101 | 62541101 |  | 4.1852 | 0.33802 |  | 81 | 0.0002658 | 8746 | 0.0774 | 3397 | 2.0573e-05 | 9605
PANOCHE 1103724590 | PANOCHE 1103 | 253671103 |  | 4.2705 | 0.10826 |  | 69.5 | 0.00029985 | 8022 | 0.068629 | 5255 | 2.0572e-05 | 9606
SCHINDLER 1112494245 | SCHINDLER 1112 | 252891112 |  | 11.9613 | 0.098969 |  | 184.5 | 0.00026607 | 8743 | 0.077147 | 3651 | 2.0561e-05 | 9607
GONZALES 110436982 | GONZALES 1104 | 182131104 |  | 16.6287 | 1.745 |  | 352 | 0.00030693 | 7868 | 0.067039 | 5960 | 2.0545e-05 | 9608
LAMMERS 110113686 | LAMMERS 1101 | 162771101 |  | 5.0641 | 0.20743 |  | 90.5 | 0.00030451 | 7921 | 0.067561 | 5568 | 2.0539e-05 | 9609
DAIRYLAND 11025570 | DAIRYLAND 1102 | 252421102 |  | 49.733 | 3.725 |  | 856.5 | 0.00026851 | 8687 | 0.07672 | 3923 | 2.0524e-05 | 9610
CALFLAX 1101CB | CALFLAX 1101 | 253441101 |  | 27.3528 | 0.33066 |  | 458 | 0.00027216 | 8601 | 0.075859 | 4243 | 2.0524e-05 | 9611
RALSTON 11022028 | RALSTON 1102 | 24141102 | FALSE | 2.3376 | 1.1547 | 3.0771 | 28.5 | 0.00036337 | 6939 | 0.055082 | 7738 | 2.0515e-05 | 9612
LE GRAND 11124510 | LE GRAND 1112 | 255361112 |  | 9.8066 | 0.50225 |  | 172.8333 | 0.00028039 | 8410 | 0.073387 | 4625 | 2.0495e-05 | 9613
ARVIN 110194892 | ARVIN 1101 | 253801101 | TRUE | 10.1403 | 0.22961 | 0.096659 | 163 | 0.00023884 | 9305 | 0.089969 | 3341 | 2.049e-05 | 9614
KINGSBURG 11136390 | KINGSBURG 1113 | 252241113 |  | 20.5835 | 2.3122 |  | 362 | 0.00027736 | 8483 | 0.075563 | 4324 | 2.0474e-05 | 9615
SALINAS 110678264 | SALINAS 1106 | 182011106 |  | 3.1909 | 0.57557 |  | 67.3333 | 0.00030186 | 7969 | 0.067874 | 5449 | 2.0466e-05 | 9616
ARBUCKLE 110481378 | ARBUCKLE 1104 | 62081104 |  | 0.013521 | 0 |  | 0.5 | 0.00030544 | 7900 | 0.067 | 6057 | 2.0464e-05 | 9617
SCHINDLER 1112935980 | SCHINDLER 1112 | 252891112 |  | 0.056263 | 0 |  | 0.5 | 0.00026431 | 8765 | 0.0774 | 3397 | 2.0458e-05 | 9618
BELLEVUE 110298544 | BELLEVUE 1102 | 43181102 |  | 3.4795 | 0.70686 |  | 60 | 0.00030269 | 7952 | 0.067605 | 5545 | 2.0457e-05 | 9619
EL NIDO 11024110 | EL NIDO 1102 | 252451102 |  | 4.0642 | 0.31435 |  | 77 | 0.00026725 | 8714 | 0.076768 | 3899 | 2.0455e-05 | 9620
CATLETT 11022506 | CATLETT 1102 | 153761102 |  | 17.3586 | 1.1313 |  | 286 | 0.00026639 | 8735 | 0.076932 | 3806 | 2.0455e-05 | 9621
SEMITROPIC 1110804864 | SEMITROPIC 1110 | 252901110 |  | 2.1165 | 0.16505 |  | 38 | 0.00026427 | 8769 | 0.0774 | 3397 | 2.0454e-05 | 9622
SEMITROPIC 11104552 | SEMITROPIC 1110 | 252901110 |  | 9.0313 | 0.6234 |  | 155 | 0.00026423 | 8771 | 0.0774 | 3397 | 2.0452e-05 | 9623
ALPAUGH 11038900 | ALPAUGH 1103 | 254001103 |  | 2.551 | 0.019509 |  | 40.5 | 0.00027869 | 8453 | 0.074396 | 4502 | 2.0449e-05 | 9624
DIXON 1106533554 | DIXON 1106 | 62061106 |  | 8.3414 | 1.0214 |  | 157.5 | 0.00027165 | 8616 | 0.075798 | 4265 | 2.0445e-05 | 9625
ANITA 1102CB | ANITA 1102 | 102841102 |  | 12.9319 | 0.6195 |  | 215 | 0.00029535 | 8098 | 0.070485 | 4952 | 2.044e-05 | 9626
OLIVEHURST 110593288 | OLIVEHURST 1105 | 152901105 |  | 31.7625 | 1.458 |  | 576 | 0.00026594 | 8744 | 0.076888 | 3839 | 2.0437e-05 | 9627
HOLLISTER 210683518 | HOLLISTER 2106 | 182492106 |  | 8.5802 | 0.25824 |  | 103.5 | 0.00030339 | 7942 | 0.06758 | 5566 | 2.0434e-05 | 9628
KINGSBURG 1111941436 | KINGSBURG 1111 | 252241111 |  | 23.6979 | 5.1108 |  | 437.3333 | 0.00026999 | 8656 | 0.076428 | 4045 | 2.0433e-05 | 9629
TUPMAN 1103CB | TUPMAN 1103 | 254561103 |  | 19.8468 | 0.6742 |  | 317.75 | 0.00027838 | 8464 | 0.0752 | 4387 | 2.0431e-05 | 9630
HONCUT 110186530 | HONCUT 1101 | 103211101 |  | 8.2297 | 0.50078 |  | 140.5 | 0.00026389 | 8783 | 0.0774 | 3397 | 2.0425e-05 | 9631
STROUD 1101CB | STROUD 1101 | 253661101 |  | 9.342 | 0.44675 |  | 159.5 | 0.00026429 | 8766 | 0.077248 | 3539 | 2.0422e-05 | 9632
GABILAN 11013034 | GABILAN 1101 | 182331101 | TRUE | 20.4822 | 3.5352 | 0.034341 | 410 | 0.00029586 | 8086 | 0.073165 | 4648 | 2.0412e-05 | 9633
DINUBA 1105510758 | DINUBA 1105 | 254091105 |  | 31.0707 | 5.2386 |  | 557 | 0.0002644 | 8764 | 0.077228 | 3555 | 2.041e-05 | 9634
HORSESHOE 110151538 | HORSESHOE 1101 | 152571101 |  | 10.8218 | 1.659 |  | 189.5 | 0.00030452 | 7920 | 0.067009 | 6024 | 2.0406e-05 | 9635
MIDDLE RIVER 1101CB | MIDDLE RIVER 1101 | 162091101 |  | 1.4423 | 0.045282 |  | 23.5 | 0.00027137 | 8623 | 0.075329 | 4360 | 2.0404e-05 | 9636
CORCORAN 110644316 | CORCORAN 1106 | 252171106 |  | 14.8491 | 0.53248 |  | 256.5 | 0.00027084 | 8631 | 0.075827 | 4254 | 2.0402e-05 | 9637
AVENA 1701CUS7523 | AVENA 1701 | 163571701 |  | 0.0087486 | 0 |  | 1 | 0.00026347 | 8796 | 0.0774 | 3397 | 2.0393e-05 | 9638
OCEANO 1106V32 | OCEANO 1106 | 182601106 |  | 4.0184 | 3.7232 |  | 68.8333 | 0.00032743 | 7496 | 0.057819 | 7323 | 2.0385e-05 | 9639
AVENAL 21019070 | AVENAL 2101 | 255002101 |  | 31.5804 | 0.34803 |  | 583 | 0.00024536 | 9181 | 0.46776 | 2854 | 2.0377e-05 | 9640
ATWATER 11082460 | ATWATER 1108 | 253611108 |  | 11.2749 | 1.107 |  | 209.5 | 0.00027339 | 8573 | 0.075105 | 4400 | 2.0371e-05 | 9641
EAST NICOLAUS 11037613 | EAST NICOLAUS 1103 | 152151103 |  | 2.0397 | 0.069369 |  | 34.5 | 0.0002632 | 8801 | 0.0774 | 3397 | 2.0371e-05 | 9642
COTTLE 17089290 | COTTLE 1708 | 163711708 |  | 19.4517 | 1.3457 |  | 328.5 | 0.00026398 | 8781 | 0.07723 | 3554 | 2.037e-05 | 9643
TUDOR 11011234 | TUDOR 1101 | 153711101 |  | 22.6727 | 2.1676 |  | 423.3333 | 0.00026648 | 8732 | 0.076714 | 3929 | 2.036e-05 | 9644
CARUTHERS 11016900 | CARUTHERS 1101 | 252371101 |  | 35.2829 | 3.3762 |  | 604 | 0.00026397 | 8782 | 0.077185 | 3604 | 2.0356e-05 | 9645
STONE CORRAL 11087310 | STONE CORRAL 1108 | 252921108 |  | 6.1555 | 1.6495 |  | 118.5 | 0.00027975 | 8425 | 0.073716 | 4579 | 2.0352e-05 | 9646
PEACHTON 110286036 | PEACHTON 1102 | 103241102 |  | 0.038555 | 0 |  | 1.8333 | 0.00026293 | 8808 | 0.0774 | 3396 | 2.0351e-05 | 9647
CAMDEN 11036490 | CAMDEN 1103 | 252301103 |  | 7.0488 | 0.51772 |  | 116 | 0.00026278 | 8812 | 0.0774 | 3397 | 2.0339e-05 | 9648
ORO LOMA 111848328 | ORO LOMA 1118 | 255371118 |  | 16.6588 | 0.30064 |  | 273.5 | 0.00026474 | 8758 | 0.076987 | 3769 | 2.0335e-05 | 9649
RIO BRAVO 11034349 | RIO BRAVO 1103 | 252861103 |  | 10.7464 | 0.70586 |  | 193.6667 | 0.00026814 | 8697 | 0.076107 | 4161 | 2.0331e-05 | 9650
PARLIER 11036810 | PARLIER 1103 | 252291103 |  | 22.114 | 3.2865 |  | 407 | 0.00026443 | 8762 | 0.07699 | 3766 | 2.0322e-05 | 9651
KNIGHTS LANDING 11018952 | KNIGHTS LANDING 1101 | 62721101 |  | 9.0605 | 0.29879 |  | 149.5 | 0.00026446 | 8761 | 0.077027 | 3746 | 2.0317e-05 | 9652
LIVE OAK 110448420 | LIVE OAK 1104 | 153771104 |  | 16.0045 | 0.81007 |  | 282 | 0.00026377 | 8784 | 0.076929 | 3809 | 2.0313e-05 | 9653
BORDEN 11016079 | BORDEN 1101 | 255121101 |  | 6.5423 | 0.56001 |  | 109.5 | 0.00026303 | 8804 | 0.077178 | 3618 | 2.0288e-05 | 9654
SCHINDLER 111488632 | SCHINDLER 1114 | 252891114 |  | 9.2047 | 0.38316 |  | 155 | 0.00027741 | 8481 | 0.073126 | 4652 | 2.0287e-05 | 9655
DIVIDE 1102M46 | DIVIDE 1102 | 182571102 |  | 21.1917 | 4.2461 |  | 378 | 0.00030322 | 7944 | 0.067181 | 5827 | 2.0286e-05 | 9656
LIVE OAK 110439602 | LIVE OAK 1104 | 153771104 |  | 0.022343 | 0 |  | 1.5 | 0.00026208 | 8833 | 0.0774 | 3397 | 2.0285e-05 | 9657
TRACY 110266306 | TRACY 1102 | 162881102 |  | 16.6208 | 0.79723 |  | 331.5 | 0.00026307 | 8803 | 0.077184 | 3606 | 2.0285e-05 | 9658
UKIAH 1114911132 | UKIAH 1114 | 42771114 | TRUE | 3.1862 | 0.37646 | 0.26483 | 54 | 0.00022613 | 9578 | 0.087152 | 3357 | 2.0283e-05 | 9659
CALFLAX 1102CB | CALFLAX 1102 | 253441102 |  | 19.8466 | 0.54837 |  | 334 | 0.00026372 | 8789 | 0.076843 | 3860 | 2.0283e-05 | 9660
COLUSA 11013529 | COLUSA 1101 | 62021101 |  | 3.7984 | 0.45438 |  | 72.5 | 0.00026205 | 8836 | 0.0774 | 3397 | 2.0282e-05 | 9661
DAIRYLAND 110565734 | DAIRYLAND 1105 | 252421105 |  | 17.243 | 0.66982 |  | 303 | 0.00026227 | 8826 | 0.07732 | 3446 | 2.0275e-05 | 9662
MOLINO 11043281 | MOLINO 1104 | 42571104 |  | 4.4051 | 0.50731 |  | 78.5 | 0.00030231 | 7959 | 0.067062 | 5935 | 2.0274e-05 | 9663
HOLLISTER 2105CB | HOLLISTER 2105 | 182492105 |  | 21.4304 | 1.3141 |  | 367.8333 | 0.00030249 | 7955 | 0.066998 | 6060 | 2.0267e-05 | 9664
HONCUT 11011956 | HONCUT 1101 | 103211101 |  | 14.9532 | 0.91226 |  | 265 | 0.00027727 | 8485 | 0.073528 | 4608 | 2.0264e-05 | 9665
BUTTE 11032422 | BUTTE 1103 | 103081103 |  | 20.8254 | 2.1375 |  | 394.5 | 0.00029571 | 8090 | 0.069385 | 5130 | 2.0262e-05 | 9666
CATLETT 11052504 | CATLETT 1105 | 153761105 |  | 10.0744 | 0.24924 |  | 164 | 0.00026373 | 8788 | 0.077007 | 3757 | 2.0256e-05 | 9667
CARUTHERS 11029060 | CARUTHERS 1102 | 252371102 |  | 4.6882 | 0.25219 |  | 80 | 0.00026646 | 8733 | 0.076202 | 4127 | 2.0253e-05 | 9668
STOREY 1109CB | STOREY 1109 | 254611109 |  | 16.7932 | 1.3535 |  | 282.6667 | 0.00026353 | 8793 | 0.076954 | 3792 | 2.0252e-05 | 9669
ORO LOMA 11089940 | ORO LOMA 1108 | 255371108 |  | 15.0601 | 0.39976 |  | 293.5 | 0.0002681 | 8698 | 0.075813 | 4261 | 2.0252e-05 | 9670
ZAMORA 110769308 | ZAMORA 1107 | 63191107 |  | 23.6614 | 1.8484 |  | 418.5 | 0.0002907 | 8182 | 0.070145 | 5010 | 2.0251e-05 | 9671
ATWATER 110255354 | ATWATER 1102 | 253611102 |  | 0.030621 | 0 |  | 1.5 | 0.00026159 | 8850 | 0.0774 | 3397 | 2.0247e-05 | 9672
ORTIGA 110611190 | ORTIGA 1106 | 254311106 |  | 9.5904 | 0.42686 |  | 165.5 | 0.00027457 | 8539 | 0.073462 | 4616 | 2.0243e-05 | 9673
MERCED 210247184 | MERCED 2102 | 252802102 |  | 0.30683 | 0 |  | 6.3333 | 0.00026148 | 8854 | 0.0774 | 3397 | 2.0239e-05 | 9674
WEEDPATCH 11064171 | WEEDPATCH 1106 | 252971106 |  | 18.4718 | 1.2448 |  | 321 | 0.00026176 | 8841 | 0.077324 | 3437 | 2.0239e-05 | 9675
ARBUCKLE 11013070 | ARBUCKLE 1101 | 62081101 |  | 17.1549 | 1.087 |  | 308 | 0.00027846 | 8462 | 0.073564 | 4602 | 2.0239e-05 | 9676
WAHTOKE 111033004 | WAHTOKE 1110 | 254531110 |  | 6.9933 | 1.178 |  | 124.3333 | 0.00027326 | 8578 | 0.075516 | 4335 | 2.0238e-05 | 9677
BIG LAGOON 1101314118 | BIG LAGOON 1101 | 192361101 |  | 0.0076504 | 0 |  | 1 | 0.00030191 | 7967 | 0.067035 | 5975 | 2.0238e-05 | 9678
LE GRAND 11045050 | LE GRAND 1104 | 255361104 |  | 5.7782 | 0.30045 |  | 112 | 0.0002629 | 8810 | 0.077183 | 3608 | 2.0237e-05 | 9679
DUNNIGAN 110130002 | DUNNIGAN 1101 | 63811101 |  | 11.114 | 0.69394 |  | 191.5 | 0.00026514 | 8752 | 0.076414 | 4048 | 2.0235e-05 | 9680
WILKINS SLOUGH 110118262 | WILKINS SLOUGH 1101 | 62771101 |  | 22.371 | 0.63961 |  | 392.5 | 0.00026349 | 8795 | 0.07693 | 3808 | 2.0233e-05 | 9681
HENRIETTA 111099242 | HENRIETTA 1110 | 252681110 |  | 14.5027 | 2.462 |  | 270 | 0.00026169 | 8847 | 0.07731 | 3460 | 2.0231e-05 | 9682
CORNING 11031628 | CORNING 1103 | 103331103 |  | 9.9624 | 0.80773 |  | 178 | 0.00029692 | 8065 | 0.068187 | 5362 | 2.0228e-05 | 9683
SKAGGS ISLAND 1101CB | SKAGGS ISLAND 1101 | 43341101 |  | 0.048246 | 0 |  | 2 | 0.00029418 | 8123 | 0.068748 | 5232 | 2.0224e-05 | 9684
NORCO 1102CB | NORCO 1102 | 254691102 |  | 7.5686 | 0.10376 |  | 128.5 | 0.00028068 | 8405 | 0.07258 | 4711 | 2.0219e-05 | 9685
VACA DIXON 11035602 | VACA DIXON 1103 | 63591103 |  | 12.4116 | 0.51663 |  | 209.5 | 0.00026689 | 8722 | 0.07613 | 4153 | 2.0219e-05 | 9686
DINUBA 11057120 | DINUBA 1105 | 254091105 |  | 9.8861 | 1.2256 |  | 182 | 0.00026205 | 8835 | 0.077267 | 3521 | 2.0219e-05 | 9687
DINUBA 11047300 | DINUBA 1104 | 254091104 |  | 28.7909 | 4.0846 |  | 513.25 | 0.00026287 | 8811 | 0.077056 | 3727 | 2.0203e-05 | 9688
LERDO 11127348 | LERDO 1112 | 253491112 |  | 1.9425 | 0.0080303 |  | 29.5 | 0.00026096 | 8867 | 0.0774 | 3397 | 2.0198e-05 | 9689
LOCKEFORD 21022130 | LOCKEFORD 2102 | 163682102 |  | 3.5532 | 0.38241 |  | 69 | 0.00030074 | 8005 | 0.067151 | 5853 | 2.0196e-05 | 9690
LOGAN CREEK 210168978 | LOGAN CREEK 2101 | 103142101 |  | 9.716 | 0.32245 |  | 162.5 | 0.00026209 | 8832 | 0.0771 | 3691 | 2.0195e-05 | 9691
LIVE OAK 1101136102 | LIVE OAK 1101 | 153771101 |  | 19.3722 | 2.1955 |  | 343.5 | 0.00027656 | 8503 | 0.075338 | 4356 | 2.0193e-05 | 9692
SISQUOC 1102CB | SISQUOC 1102 | 182811102 |  | 11.4596 | 1.3303 |  | 214 | 0.000296 | 8082 | 0.068354 | 5316 | 2.0191e-05 | 9693
GABILAN 1101566352 | GABILAN 1101 | 182331101 | TRUE | 0.92168 | 0.037848 | 0.2412 | 18 | 0.0003012 | 7990 | 0.067 | 6057 | 2.018e-05 | 9694
PETALUMA C 110835452 | PETALUMA C 1108 | 42631108 |  | 11.1285 | 3.5888 |  | 195.5 | 0.00027503 | 8533 | 0.070856 | 4909 | 2.0176e-05 | 9695
WEST SACRAMENTO 11048422 | WEST SACRAMENTO 1104 | 63131104 |  | 7.0723 | 0.10608 |  | 136.5 | 0.0002711 | 8629 | 0.077043 | 3738 | 2.0172e-05 | 9696
WRIGHT 1110CB | WRIGHT 1110 | 254641110 |  | 31.796 | 1.7996 |  | 534 | 0.0002737 | 8561 | 0.072571 | 4712 | 2.0163e-05 | 9697
NEWMAN 11011584 | NEWMAN 1101 | 162741101 |  | 32.5551 | 1.7093 |  | 623.5 | 0.00026262 | 8815 | 0.076912 | 3821 | 2.0157e-05 | 9698
BLUE LAKE 110294240 | BLUE LAKE 1102 | 192181102 |  | 3.9771 | 0.45892 |  | 81.5 | 0.00029296 | 8148 | 0.068531 | 5280 | 2.0151e-05 | 9699
WHEATLAND 11042220 | WHEATLAND 1104 | 152811104 |  | 14.409 | 1.2215 |  | 263 | 0.00026088 | 8868 | 0.077341 | 3421 | 2.0149e-05 | 9700
RAWSON 11031486 | RAWSON 1103 | 103531103 |  | 6.2954 | 0.61593 |  | 122.5 | 0.00028565 | 8294 | 0.071895 | 4782 | 2.0144e-05 | 9701
FIREBAUGH 11013290 | FIREBAUGH 1101 | 253471101 |  | 13.1815 | 0.45988 |  | 224 | 0.00026337 | 8798 | 0.076716 | 3925 | 2.0137e-05 | 9702
MIDWAY 1101CB | MIDWAY 1101 | 252611101 |  | 33.9992 | 1.0606 |  | 555.3333 | 0.0002623 | 8823 | 0.076856 | 3855 | 2.0132e-05 | 9703
BELMONT 11028918 | BELMONT 1102 | 24031102 |  | 2.6238 | 0.25904 |  | 38.5 | 0.00035516 | 7052 | 0.054881 | 7773 | 2.013e-05 | 9704
GATES 1104CB | GATES 1104 | 253931104 |  | 13.7194 | 0.42381 |  | 231.6667 | 0.00028319 | 8346 | 0.070623 | 4939 | 2.0128e-05 | 9705
RICE 110197036 | RICE 1101 | 62831101 |  | 6.7 | 0.19816 |  | 113 | 0.00026004 | 8882 | 0.0774 | 3397 | 2.0127e-05 | 9706
CLEAR LAKE 110237580 | CLEAR LAKE 1102 | 42141102 |  | 5.1203 | 0.26699 |  | 89.5 | 0.00029883 | 8040 | 0.067367 | 5690 | 2.0127e-05 | 9707
WHEELER RIDGE 1103CB | WHEELER RIDGE 1103 | 253481103 |  | 16.2096 | 0.19677 |  | 282.8333 | 0.0002753 | 8528 | 0.074306 | 4513 | 2.0125e-05 | 9708
GREEN VALLEY 210397492 | GREEN VALLEY 2103 | 83192103 |  | 4.5952 | 0.20066 |  | 93 | 0.00027596 | 8513 | 0.072424 | 4725 | 2.012e-05 | 9709
BRENTWOOD 2105219013 | BRENTWOOD 2105 | 14592105 |  | 6.8038 | 1.0313 |  | 106.0833 | 0.00029957 | 8027 | 0.067199 | 5811 | 2.0115e-05 | 9710
EL NIDO 11015890 | EL NIDO 1101 | 252451101 |  | 27.1135 | 2.4625 |  | 467.5 | 0.00025984 | 8885 | 0.0774 | 3397 | 2.0112e-05 | 9711
PEASE 11031246 | PEASE 1103 | 153751103 |  | 16.8671 | 1.981 |  | 298.3333 | 0.00026127 | 8857 | 0.077075 | 3714 | 2.0087e-05 | 9712
GUSTINE 11017014 | GUSTINE 1101 | 163111101 |  | 7.3773 | 0.5318 |  | 132 | 0.00026374 | 8786 | 0.076478 | 4024 | 2.0085e-05 | 9713
CHOWCHILLA 110139006 | CHOWCHILLA 1101 | 254101101 |  | 12.7715 | 1.4823 |  | 223 | 0.00026312 | 8802 | 0.076675 | 3946 | 2.0079e-05 | 9714
HONCUT 11011038 | HONCUT 1101 | 103211101 |  | 12.6766 | 0.95856 |  | 222.5 | 0.00026114 | 8860 | 0.077111 | 3683 | 2.0069e-05 | 9715
MERCED 1114777666 | MERCED 1114 | 252801114 |  | 4.9666 | 0.18025 |  | 86.5 | 0.00025917 | 8901 | 0.0774 | 3397 | 2.006e-05 | 9716
PEACHTON 110137470 | PEACHTON 1101 | 103241101 |  | 15.4126 | 0.54704 |  | 277.3333 | 0.00026068 | 8873 | 0.077118 | 3679 | 2.0056e-05 | 9717
CAMDEN 11025547F | CAMDEN 1102 | 252301102 |  | 1.2078 | 1.2373 |  | 16.5 | 0.00031149 | 7776 | 0.066387 | 6207 | 2.0052e-05 | 9718
MENDOTA 11023810 | MENDOTA 1102 | 252311102 |  | 2.5859 | 0 |  | 39.5 | 0.00026166 | 8848 | 0.076784 | 3895 | 2.0047e-05 | 9719
DAIRYLAND 1111967172 | DAIRYLAND 1111 | 252421111 |  | 14.3605 | 0.4897 |  | 205.8333 | 0.00025959 | 8890 | 0.077283 | 3498 | 2.0047e-05 | 9720
HOLLISTER 21044676 | HOLLISTER 2104 | 182492104 |  | 10.486 | 0.68626 |  | 197.1667 | 0.00029328 | 8144 | 0.068681 | 5243 | 2.0045e-05 | 9721
LAKEVIEW 1106CB | LAKEVIEW 1106 | 253411106 |  | 12.0381 | 0.25171 |  | 196.8333 | 0.00027144 | 8621 | 0.074329 | 4507 | 2.0041e-05 | 9722
CORCORAN 11188170 | CORCORAN 1118 | 252171118 |  | 13.7869 | 1.2449 |  | 240 | 0.00026172 | 8842 | 0.076797 | 3888 | 2.0038e-05 | 9723
CARBONA 1101CB | CARBONA 1101 | 163091101 |  | 25.099 | 0.32453 |  | 471.5 | 0.00026735 | 8713 | 0.079489 | 3389 | 2.0028e-05 | 9724
ATWATER 11077080 | ATWATER 1107 | 253611107 |  | 9.2805 | 0.63932 |  | 164 | 0.00026323 | 8799 | 0.076436 | 4041 | 2.0027e-05 | 9725
SISQUOC 1101CB | SISQUOC 1101 | 182811101 |  | 13.6116 | 0.8473 |  | 231 | 0.00029729 | 8063 | 0.067224 | 5786 | 2.0023e-05 | 9726
STOREY 11049300 | STOREY 1104 | 254611104 |  | 28.0913 | 1.5209 |  | 472 | 0.00026633 | 8738 | 0.075816 | 4260 | 2.0008e-05 | 9727
JACINTO 11012062 | JACINTO 1101 | 102851101 |  | 15.3226 | 0.63933 |  | 302 | 0.00028815 | 8233 | 0.070962 | 4896 | 2.0002e-05 | 9728
MC MULLIN 11066770 | MC MULLIN 1106 | 254411106 |  | 26.3925 | 1.8257 |  | 458 | 0.00025867 | 8912 | 0.077347 | 3416 | 2.0001e-05 | 9729
STROUD 11029480 | STROUD 1102 | 253661102 |  | 13.7898 | 0.42329 |  | 232.5 | 0.00026631 | 8739 | 0.075583 | 4317 | 1.9997e-05 | 9730
CORTINA 110137554 | CORTINA 1101 | 63121101 |  | 1.7642 | 0.12927 |  | 30 | 0.00028312 | 8352 | 0.07064 | 4938 | 1.9994e-05 | 9731
REEDLEY 11107470 | REEDLEY 1110 | 252341110 |  | 11.052 | 2.6928 |  | 197 | 0.00026478 | 8757 | 0.076499 | 4018 | 1.9992e-05 | 9732
SONOMA 1107606 | SONOMA 1107 | 42721107 |  | 3.154 | 0.11181 |  | 62.5 | 0.00028442 | 8324 | 0.07027 | 4989 | 1.9961e-05 | 9733
MERCED 11089990 | MERCED 1108 | 252801108 |  | 30.4051 | 0.93906 |  | 502 | 0.00025929 | 8898 | 0.077048 | 3734 | 1.9954e-05 | 9734
CLEAR LAKE 1102626634 | CLEAR LAKE 1102 | 42141102 |  | 10.1394 | 1.4404 |  | 180.5 | 0.00029671 | 8070 | 0.067348 | 5702 | 1.9952e-05 | 9735
WRIGHT 111011942 | WRIGHT 1110 | 254641110 |  | 14.2881 | 0.85034 |  | 238.5 | 0.00025841 | 8917 | 0.077232 | 3550 | 1.995e-05 | 9736
MENLO 110358562 | MENLO 1103 | 24131103 |  | 4.4402 | 0.5321 |  | 91 | 0.00030352 | 7937 | 0.066117 | 6242 | 1.9948e-05 | 9737
MC ARTHUR 11011488 | MC ARTHUR 1101 | 103491101 | FALSE | 33.3523 | 1.3082 | 1.684 | 603 | 0.00015134 | 10688 | 0.12843 | 3250 | 1.9944e-05 | 9738
MAXWELL 110530456 | MAXWELL 1105 | 62881105 |  | 7.926 | 0.26688 |  | 132.5 | 0.00025756 | 8932 | 0.0774 | 3397 | 1.9935e-05 | 9739
CORCORAN 1104149336 | CORCORAN 1104 | 252171104 |  | 8.1656 | 0.43704 |  | 131 | 0.00025751 | 8933 | 0.0774 | 3397 | 1.9932e-05 | 9740
ORO LOMA 11163190 | ORO LOMA 1116 | 255371116 |  | 4.8036 | 0.1911 |  | 82.5 | 0.00026113 | 8861 | 0.075987 | 4203 | 1.993e-05 | 9741
COALINGA NO 2 110541882 | COALINGA NO 2 1105 | 252381105 |  | 2.7294 | 0.22539 |  | 46.5 | 0.00029791 | 8053 | 0.066891 | 6098 | 1.9919e-05 | 9742
MADISON 110323452 | MADISON 1103 | 63171103 |  | 5.537 | 0.15619 |  | 100 | 0.00028778 | 8239 | 0.070762 | 4925 | 1.9916e-05 | 9743
LERDO 1112CB | LERDO 1112 | 253491112 |  | 15.34 | 0.45638 |  | 236.5 | 0.00026244 | 8818 | 0.07575 | 4278 | 1.9915e-05 | 9744
MC ARTHUR 1102CB | MC ARTHUR 1102 | 103491102 |  | 1.4356 | 0.77947 |  | 31.5 | 0.00029379 | 8135 | 0.067218 | 5792 | 1.9912e-05 | 9745
GREEN VALLEY 210211036 | GREEN VALLEY 2102 | 83192102 |  | 12.8567 | 1.1388 |  | 228 | 0.00029411 | 8127 | 0.067764 | 5487 | 1.9909e-05 | 9746
CARUTHERS 11046737 | CARUTHERS 1104 | 252371104 |  | 2.0392 | 0.26281 |  | 38.5 | 0.00025719 | 8942 | 0.0774 | 3397 | 1.9907e-05 | 9747
EL PECO 11055870 | EL PECO 1105 | 253981105 |  | 7.7778 | 0.21504 |  | 135 | 0.00025907 | 8903 | 0.076859 | 3851 | 1.9903e-05 | 9748
WINTERS 110121302 | WINTERS 1101 | 63321101 |  | 7.7903 | 1.0268 |  | 146 | 0.00029192 | 8167 | 0.068925 | 5202 | 1.9902e-05 | 9749
SCHINDLER 110599334 | SCHINDLER 1105 | 252891105 |  | 9.4027 | 0.29258 |  | 160 | 0.0002574 | 8937 | 0.077302 | 3470 | 1.9894e-05 | 9750
COLUMBUS 11054059 | COLUMBUS 1105 | 253951105 |  | 5.6887 | 0.33512 |  | 99 | 0.00029652 | 8074 | 0.067094 | 5908 | 1.9894e-05 | 9751
VACA DIXON 110340832 | VACA DIXON 1103 | 63591103 |  | 34.0767 | 3.8218 |  | 590 | 0.00028712 | 8252 | 0.069313 | 5142 | 1.9892e-05 | 9752
BORDEN 11035210 | BORDEN 1103 | 255121103 |  | 13.23 | 0.96885 |  | 230.5 | 0.00025788 | 8927 | 0.077083 | 3704 | 1.9892e-05 | 9753
HERDLYN 110311754 | HERDLYN 1103 | 163741103 |  | 29.9863 | 0.75355 |  | 539.5 | 0.00025814 | 8921 | 0.077176 | 3620 | 1.9878e-05 | 9754
MC FARLAND 1105128091 | MC FARLAND 1105 | 253181105 |  | 3.1081 | 0.14615 |  | 49.5 | 0.00025744 | 8935 | 0.077154 | 3641 | 1.9869e-05 | 9755
TEMBLOR 11043013 | TEMBLOR 1104 | 252551104 |  | 3.2885 | 0 |  | 57 | 0.00029396 | 8128 | 0.067641 | 5529 | 1.9866e-05 | 9756
MENDOTA 1101CB | MENDOTA 1101 | 252311101 |  | 12.3995 | 2.1192 |  | 202.75 | 0.00025824 | 8920 | 0.07704 | 3739 | 1.9865e-05 | 9757
DINUBA 11047590 | DINUBA 1104 | 254091104 |  | 24.6049 | 3.3112 |  | 437 | 0.00025904 | 8904 | 0.076995 | 3765 | 1.9862e-05 | 9758
MISSION (X) 1128CB | MISSION (X) 1128 | 22011128 |  | 0.15911 | 0.49308 |  | 8.0833 | 0.00037423 | 6776 | 0.053073 | 8252 | 1.9861e-05 | 9759
SISQUOC 1103CB | SISQUOC 1103 | 182811103 |  | 7.5363 | 0.49587 |  | 139.5 | 0.00029418 | 8122 | 0.067599 | 5550 | 1.9858e-05 | 9760
GREEN VALLEY 21036661 | GREEN VALLEY 2103 | 83192103 |  | 1.58 | 0.11683 |  | 32.5 | 0.00029629 | 8078 | 0.067 | 6057 | 1.9852e-05 | 9761
CHOWCHILLA 11015550 | CHOWCHILLA 1101 | 254101101 |  | 19.835 | 1.7991 |  | 348 | 0.00026169 | 8846 | 0.076401 | 4054 | 1.9845e-05 | 9762
EL CAPITAN 110384120 | EL CAPITAN 1103 | 253881103 |  | 0.8868 | 0.28306 |  | 18.5 | 0.00025637 | 8956 | 0.0774 | 3397 | 1.9843e-05 | 9763
LE GRAND 110634924 | LE GRAND 1106 | 255361106 |  | 6.0814 | 0.60786 |  | 102.5 | 0.00025627 | 8960 | 0.0774 | 3397 | 1.9835e-05 | 9764
DOS PALOS 110190170 | DOS PALOS 1101 | 254041101 |  | 36.0476 | 2.3333 |  | 628.5 | 0.00025728 | 8940 | 0.077129 | 3666 | 1.9828e-05 | 9765
SANTA YNEZ 110488746 | SANTA YNEZ 1104 | 182721104 |  | 8.6652 | 0.581 |  | 147 | 0.00026071 | 8872 | 0.075251 | 4377 | 1.9818e-05 | 9766
DUNNIGAN 11013050 | DUNNIGAN 1101 | 63811101 |  | 4.4151 | 0.44623 |  | 80 | 0.00027935 | 8437 | 0.072256 | 4750 | 1.9817e-05 | 9767
KINGSBURG 11116170 | KINGSBURG 1111 | 252241111 |  | 26.0116 | 3.7401 |  | 466.5 | 0.00025794 | 8925 | 0.076953 | 3795 | 1.9815e-05 | 9768
MORMON 110277504 | MORMON 1102 | 163211102 |  | 28.0924 | 1.2462 |  | 494.5 | 0.0002623 | 8822 | 0.07619 | 4132 | 1.9808e-05 | 9769
GANSO 1104CB | GANSO 1104 | 254541104 |  | 15.2842 | 0.33451 |  | 253.5 | 0.00025643 | 8954 | 0.077304 | 3468 | 1.9801e-05 | 9770
NEWHALL 1111CB | NEWHALL 1111 | 254461111 |  | 12.0579 | 0.12444 |  | 200.5 | 0.00025962 | 8889 | 0.076754 | 3906 | 1.98e-05 | 9771
STOREY 11086010 | STOREY 1108 | 254611108 |  | 11.3377 | 0.21058 |  | 183.5 | 0.00025646 | 8953 | 0.077315 | 3452 | 1.9796e-05 | 9772
SAN BERNARD 1101438074 | SAN BERNARD 1101 | 253191101 | TRUE | 1.2556 | 0 | 0.17928 | 21.5 | 0.00014733 | 10722 | 0.15129 | 3202 | 1.9792e-05 | 9773
KINGSBURG 1116794408 | KINGSBURG 1116 | 252241116 |  | 7.6206 | 1.5419 |  | 142.5 | 0.00025571 | 8970 | 0.0774 | 3397 | 1.9792e-05 | 9774
RIO DELL 110192712 | RIO DELL 1101 | 192251101 |  | 9.5247 | 0.8336 |  | 173 | 0.00029581 | 8088 | 0.06692 | 6085 | 1.9784e-05 | 9775
HARDWICK 11025050 | HARDWICK 1102 | 253711102 |  | 17.3024 | 0.87095 |  | 292 | 0.0002556 | 8971 | 0.0774 | 3397 | 1.9784e-05 | 9776
LE GRAND 1110CB | LE GRAND 1110 | 255361110 |  | 18.9575 | 0.79958 |  | 318.5 | 0.00025882 | 8909 | 0.076789 | 3893 | 1.978e-05 | 9777
GUERNSEY 110255746 | GUERNSEY 1102 | 252661102 |  | 21.7331 | 1.1918 |  | 380 | 0.00026236 | 8821 | 0.076003 | 4198 | 1.9777e-05 | 9778
MAXWELL 11053006 | MAXWELL 1105 | 62881105 |  | 10.0307 | 0.2836 |  | 165.5 | 0.00025546 | 8973 | 0.0774 | 3397 | 1.9773e-05 | 9779
AIRWAYS 1107R1426 | AIRWAYS 1107 | 252041107 |  | 8.3489 | 0.62599 |  | 143.5 | 0.00025532 | 8977 | 0.0774 | 3397 | 1.9762e-05 | 9780
NEWBURG 113190644 | NEWBURG 1131 | 192151131 |  | 9.0552 | 2.0091 |  | 160.5 | 0.00029794 | 8052 | 0.066619 | 6162 | 1.9753e-05 | 9781
SANGER 1108R544 | SANGER 1108 | 252351108 |  | 19.6454 | 2.7847 |  | 367 | 0.00025597 | 8962 | 0.077225 | 3560 | 1.9748e-05 | 9782
OROSI 110433456 | OROSI 1104 | 252841104 |  | 29.0469 | 4.0913 |  | 510.5 | 0.00026442 | 8763 | 0.074891 | 4429 | 1.974e-05 | 9783
JACINTO 11022606 | JACINTO 1102 | 102851102 |  | 23.832 | 1.7759 |  | 421 | 0.00026365 | 8790 | 0.075811 | 4262 | 1.9737e-05 | 9784
SALINAS 11043018 | SALINAS 1104 | 182011104 |  | 8.2511 | 0.70658 |  | 169.3333 | 0.00029415 | 8126 | 0.067122 | 5882 | 1.9736e-05 | 9785
BIG RIVER 11012989 | BIG RIVER 1101 | 43081101 |  | 1.0632 | 0 |  | 17.5 | 0.00029443 | 8116 | 0.067026 | 5993 | 1.9733e-05 | 9786
TULARE LAKE 110675538 | TULARE LAKE 1106 | 252951106 |  | 19.9392 | 0.38708 |  | 331.5 | 0.00026156 | 8851 | 0.075422 | 4348 | 1.9732e-05 | 9787
MC CALL 11016779F | MC CALL 1101 | 254121101 |  | 5.2532 | 0.60561 |  | 90.5 | 0.00025688 | 8945 | 0.076862 | 3848 | 1.973e-05 | 9788
TUDOR 11022298 | TUDOR 1102 | 153711102 |  | 8.8231 | 0.77074 |  | 155 | 0.00026078 | 8870 | 0.076366 | 4065 | 1.9729e-05 | 9789
MENDOTA 11023160 | MENDOTA 1102 | 252311102 |  | 12.9885 | 0.64663 |  | 235.5 | 0.0002629 | 8809 | 0.075723 | 4283 | 1.9715e-05 | 9790
MC CALL 11016790 | MC CALL 1101 | 254121101 |  | 12.4504 | 1.7053 |  | 228 | 0.00025457 | 8987 | 0.0774 | 3397 | 1.9704e-05 | 9791
ROB ROY 21058281 | ROB ROY 2105 | 83692105 |  | 1.2368 | 0.27425 |  | 19.5 | 0.00036257 | 6955 | 0.055568 | 7664 | 1.9697e-05 | 9792
EL NIDO 1101889532 | EL NIDO 1101 | 252451101 |  | 5.2582 | 0.1551 |  | 87.5 | 0.00025446 | 8990 | 0.0774 | 3397 | 1.9695e-05 | 9793
ATWATER 11027180 | ATWATER 1102 | 253611102 |  | 10.1505 | 1.0227 |  | 179.5 | 0.00025747 | 8934 | 0.076683 | 3943 | 1.9695e-05 | 9794
GOOSE LAKE 2104210300 | GOOSE LAKE 2104 | 254202104 |  | 8.408 | 0.079091 |  | 141 | 0.00027499 | 8534 | 0.071794 | 4796 | 1.9694e-05 | 9795
HARDWICK 11026350 | HARDWICK 1102 | 253711102 |  | 10.5489 | 0.44977 |  | 186 | 0.0002544 | 8993 | 0.0774 | 3397 | 1.9691e-05 | 9796
CABRILLO 1104765792 | CABRILLO 1104 | 183101104 |  | 0.7446 | 0.08849 |  | 11.5 | 0.00028596 | 8288 | 0.068356 | 5314 | 1.967e-05 | 9797
BAIR 110395364 | BAIR 1103 | 24261103 |  | 0.33437 | 0 |  | 8 | 0.00037061 | 6833 | 0.053073 | 8251 | 1.9669e-05 | 9798
MORMON 110112446 | MORMON 1101 | 163211101 |  | 11.9126 | 1.2395 |  | 202.5 | 0.00025463 | 8986 | 0.07728 | 3505 | 1.9654e-05 | 9799
OLD RIVER 11014577 | OLD RIVER 1101 | 252821101 |  | 14.2457 | 0.17469 |  | 232.5 | 0.00025946 | 8892 | 0.07609 | 4167 | 1.9653e-05 | 9800
MADISON 210120052 | MADISON 2101 | 63172101 |  | 3.8979 | 0.031017 |  | 69.5 | 0.00027343 | 8569 | 0.071489 | 4832 | 1.9653e-05 | 9801
BALFOUR 1101611738 | BALFOUR 1101 | 14321101 |  | 1.85 | 0.067203 |  | 31.5 | 0.00029324 | 8145 | 0.067006 | 6028 | 1.9648e-05 | 9802
CASSIDY 21076090 | CASSIDY 2107 | 254272107 |  | 28.168 | 2.142 |  | 482 | 0.00027859 | 8457 | 0.070854 | 4910 | 1.9642e-05 | 9803
BONITA 1103CB | BONITA 1103 | 255391103 |  | 7.4526 | 0.21607 |  | 125.8333 | 0.00025419 | 8997 | 0.077335 | 3426 | 1.964e-05 | 9804
HONCUT 1102CB | HONCUT 1102 | 103211102 |  | 19.316 | 1.2311 |  | 332 | 0.00026428 | 8767 | 0.075944 | 4215 | 1.9626e-05 | 9805
SOLEDAD 21053720 | SOLEDAD 2105 | 182052105 |  | 13.2934 | 0.70867 |  | 272.8333 | 0.00028633 | 8278 | 0.068772 | 5228 | 1.9615e-05 | 9806
SCHINDLER 111494236 | SCHINDLER 1114 | 252891114 |  | 5.2684 | 0.054547 |  | 104.5 | 0.00028006 | 8420 | 0.070274 | 4988 | 1.9589e-05 | 9807
TEMBLOR 2103642990 | TEMBLOR 2103 | 252552103 |  | 0.073615 | 0 |  | 1.75 | 0.0002923 | 8160 | 0.067 | 6057 | 1.9584e-05 | 9808
ANITA 11062496 | ANITA 1106 | 102841106 |  | 11.4873 | 0.30051 |  | 201 | 0.00029147 | 8175 | 0.067034 | 5978 | 1.9562e-05 | 9809
HONCUT 11015581 | HONCUT 1101 | 103211101 |  | 4.8474 | 0.22546 |  | 87.5 | 0.00027537 | 8525 | 0.071398 | 4844 | 1.9555e-05 | 9810
PLUMAS 11017376 | PLUMAS 1101 | 153731101 |  | 18.346 | 0.71716 |  | 350.5 | 0.0002532 | 9011 | 0.077241 | 3543 | 1.9554e-05 | 9811
CORTINA 110189686 | CORTINA 1101 | 63121101 |  | 15.2477 | 0.68655 |  | 249.8333 | 0.00027516 | 8530 | 0.07119 | 4873 | 1.9553e-05 | 9812
LERDO 11113610 | LERDO 1111 | 253491111 |  | 24.5318 | 1.0123 |  | 413.5 | 0.00025495 | 8982 | 0.076933 | 3805 | 1.9546e-05 | 9813
OAKLAND C 1133CB | OAKLAND C 1133 | 12011133 |  | 0.026857 | 0.10763 |  | 4.5 | 0.00036828 | 6867 | 0.053073 | 8251 | 1.9546e-05 | 9814
CORCORAN 1118281454 | CORCORAN 1118 | 252171118 |  | 8.9901 | 0.93131 |  | 163.5 | 0.00025266 | 9027 | 0.077352 | 3411 | 1.9544e-05 | 9815
EEL RIVER 1103CB | EEL RIVER 1103 | 192381103 | TRUE | 39.9965 | 7.9228 | 0.0097507 | 718.3333 | 0.00029831 | 8046 | 0.066454 | 6195 | 1.9542e-05 | 9816
WEEDPATCH 11014574 | WEEDPATCH 1101 | 252971101 |  | 10.1449 | 0.36379 |  | 171.5 | 0.00025543 | 8974 | 0.076578 | 3990 | 1.9537e-05 | 9817
CANTUA 1105CB | CANTUA 1105 | 253591105 |  | 12.9204 | 0.62284 |  | 220.5 | 0.0002573 | 8939 | 0.076225 | 4121 | 1.9534e-05 | 9818
RIO BRAVO 11021578 | RIO BRAVO 1102 | 252861102 |  | 9.1951 | 0.65768 |  | 146 | 0.00027956 | 8429 | 0.071406 | 4842 | 1.9529e-05 | 9819
GERBER 110185172 | GERBER 1101 | 103391101 |  | 23.168 | 2.214 |  | 410 | 0.00028642 | 8277 | 0.068543 | 5278 | 1.9517e-05 | 9820
PUTAH CREEK 11038362 | PUTAH CREEK 1103 | 63681103 |  | 4.7537 | 0.30796 |  | 91.5 | 0.0002878 | 8238 | 0.068461 | 5294 | 1.9516e-05 | 9821
JACOBS CORNER 1101805158 | JACOBS CORNER 1101 | 254771101 |  | 2.9948 | 0.0098542 |  | 51 | 0.0002521 | 9039 | 0.0774 | 3397 | 1.9512e-05 | 9822
LAMMERS 110714358 | LAMMERS 1107 | 162771107 |  | 3.4037 | 0.22164 |  | 69 | 0.00027748 | 8480 | 0.071832 | 4787 | 1.9512e-05 | 9823
CARUTHERS 110149650 | CARUTHERS 1101 | 252371101 |  | 6.5465 | 0.43648 |  | 120 | 0.00025209 | 9040 | 0.0774 | 3397 | 1.9512e-05 | 9824
CLOVIS 1104CB | CLOVIS 1104 | 254081104 |  | 0.43207 | 0.038873 |  | 11 | 0.00027289 | 8585 | 0.076294 | 4090 | 1.9509e-05 | 9825
STAGG 21049948 | STAGG 2104 | 162422104 |  | 23.0579 | 0.24838 |  | 448 | 0.00025447 | 8989 | 0.076922 | 3814 | 1.9501e-05 | 9826
EL PECO 110290060 | EL PECO 1102 | 253981102 |  | 4.5855 | 0.20547 |  | 80.5 | 0.0002519 | 9043 | 0.0774 | 3397 | 1.9497e-05 | 9827
CANAL 11013040 | CANAL 1101 | 252091101 |  | 28.8626 | 1.296 |  | 530.5 | 0.00025304 | 9017 | 0.077171 | 3628 | 1.9496e-05 | 9828
BRENTWOOD 210519062 | BRENTWOOD 2105 | 14592105 |  | 6.1352 | 0.75412 |  | 103 | 0.00029059 | 8187 | 0.0671 | 5898 | 1.9491e-05 | 9829
BAHIA 11026757 | BAHIA 1102 | 43251102 |  | 8.566 | 0.19665 |  | 170.5 | 0.00027337 | 8574 | 0.071545 | 4823 | 1.9488e-05 | 9830
PRUNEDALE 11073712 | PRUNEDALE 1107 | 182961107 |  | 13.6687 | 3.016 |  | 255 | 0.00029011 | 8194 | 0.067209 | 5800 | 1.9486e-05 | 9831
RICE 110359260 | RICE 1103 | 62831103 |  | 15.3142 | 1.2582 |  | 275.5 | 0.00025322 | 9010 | 0.077166 | 3631 | 1.9486e-05 | 9832
GUSTINE 11029100 | GUSTINE 1102 | 163111102 |  | 71.2386 | 3.7312 |  | 1240 | 0.00025928 | 8899 | 0.075114 | 4399 | 1.9484e-05 | 9833
CORNING 110485182 | CORNING 1104 | 103331104 |  | 9.2598 | 1.3074 |  | 178 | 0.00028851 | 8224 | 0.067604 | 5546 | 1.9481e-05 | 9834
OLEMA 11011686 | OLEMA 1101 | 42291101 |  | 3.185 | 0.25048 |  | 62.5 | 0.00028853 | 8223 | 0.067333 | 5713 | 1.9481e-05 | 9835
ALPAUGH 11048220 | ALPAUGH 1104 | 254001104 |  | 15.9848 | 0.54766 |  | 270.5 | 0.00025199 | 9041 | 0.077355 | 3407 | 1.9468e-05 | 9836
TUPMAN 110616222 | TUPMAN 1106 | 254561106 |  | 1.0049 | 0.054946 |  | 17.5 | 0.00025147 | 9051 | 0.0774 | 3397 | 1.9464e-05 | 9837
MAGUNDEN 2108292736 | MAGUNDEN 2108 | 252772108 |  | 0.044779 | 0 |  | 0.5 | 0.00025146 | 9052 | 0.0774 | 3397 | 1.9463e-05 | 9838
OLD RIVER 1102CB | OLD RIVER 1102 | 252821102 |  | 18.5985 | 0.52189 |  | 316.75 | 0.00025305 | 9016 | 0.077075 | 3713 | 1.9459e-05 | 9839
VALLEY HOME 170413112 | VALLEY HOME 1704 | 162981704 |  | 9.6753 | 0.8694 |  | 172 | 0.0002525 | 9032 | 0.077117 | 3680 | 1.9446e-05 | 9840
CALFLAX 1103CB | CALFLAX 1103 | 253441103 |  | 7.5561 | 0.088807 |  | 126 | 0.00025211 | 9038 | 0.077082 | 3706 | 1.9446e-05 | 9841
COPUS 11034801 | COPUS 1103 | 253871103 |  | 22.1994 | 0.30136 |  | 372.8333 | 0.00027233 | 8600 | 0.071857 | 4784 | 1.9446e-05 | 9842
HERDLYN 1103CB | HERDLYN 1103 | 163741103 |  | 33.4109 | 1.3032 |  | 466.8333 | 0.00025793 | 8926 | 0.075642 | 4301 | 1.944e-05 | 9843
KINGSBURG 1116377589 | KINGSBURG 1116 | 252241116 |  | 9.225 | 1.3617 |  | 167.5 | 0.00025105 | 9057 | 0.0774 | 3397 | 1.9431e-05 | 9844
HOLLISTER 21064050 | HOLLISTER 2106 | 182492106 |  | 1.2393 | 0.13713 |  | 17.3333 | 0.000305 | 7911 | 0.065605 | 6339 | 1.943e-05 | 9845
GATES 111084206 | GATES 1110 | 253931110 |  | 15.6888 | 0.32777 |  | 264.5 | 0.00025254 | 9031 | 0.077124 | 3671 | 1.9425e-05 | 9846
SANTA MARIA 111089336 | SANTA MARIA 1110 | 182671110 |  | 6.5853 | 0.19476 |  | 121.5 | 0.00028916 | 8212 | 0.067171 | 5833 | 1.9416e-05 | 9847
MC MULLIN 11045190 | MC MULLIN 1104 | 254411104 |  | 12.8464 | 0.11686 |  | 220.5 | 0.00025185 | 9044 | 0.077179 | 3615 | 1.9415e-05 | 9848
COTTONWOOD 110331548 | COTTONWOOD 1103 | 102931103 |  | 2.3899 | 0.23022 |  | 37 | 0.00028962 | 8205 | 0.067027 | 5990 | 1.9412e-05 | 9849
WOODWARD 2108R867 | WOODWARD 2108 | 255292108 |  | 1.016 | 0.014361 |  | 16.5 | 0.00028973 | 8203 | 0.067 | 6057 | 1.9412e-05 | 9850
JACOBS CORNER 11018160 | JACOBS CORNER 1101 | 254771101 |  | 35.0569 | 4.303 |  | 597 | 0.00025986 | 8884 | 0.075287 | 4369 | 1.9408e-05 | 9851
DINUBA 1105752984 | DINUBA 1105 | 254091105 |  | 0.21606 | 0 |  | 3.5 | 0.00025071 | 9062 | 0.0774 | 3397 | 1.9405e-05 | 9852
MC MULLIN 1105CB | MC MULLIN 1105 | 254411105 |  | 12.5389 | 0.12475 |  | 204.6667 | 0.00025069 | 9064 | 0.0774 | 3398 | 1.9404e-05 | 9853
MC MULLIN 11046130 | MC MULLIN 1104 | 254411104 |  | 16.6865 | 0.083157 |  | 290 | 0.00025166 | 9048 | 0.077069 | 3718 | 1.9399e-05 | 9854
LOS OSITOS 21037468 | LOS OSITOS 2103 | 182082103 |  | 4.0816 | 0.28363 |  | 86.25 | 0.00028505 | 8307 | 0.068085 | 5388 | 1.9394e-05 | 9855
COVELO 11014678 | COVELO 1101 | 43061101 |  | 4.8572 | 1.5835 |  | 86 | 0.0002721 | 8604 | 0.071639 | 4810 | 1.9392e-05 | 9856
ORO LOMA 1118CB | ORO LOMA 1118 | 255371118 |  | 13.1033 | 0.43954 |  | 208.4167 | 0.00027902 | 8443 | 0.071365 | 4847 | 1.9391e-05 | 9857
LEMOORE 11018010 | LEMOORE 1101 | 253601101 |  | 21.563 | 4.1891 |  | 405.5 | 0.00025051 | 9066 | 0.0774 | 3397 | 1.939e-05 | 9858
TULARE LAKE 1108943184 | TULARE LAKE 1108 | 252951108 |  | 2.6224 | 0 |  | 45.5 | 0.00025308 | 9015 | 0.076709 | 3931 | 1.9388e-05 | 9859
REEDLEY 1110CB | REEDLEY 1110 | 252341110 |  | 20.8261 | 3.4045 |  | 378.8333 | 0.00025665 | 8951 | 0.07637 | 4064 | 1.9383e-05 | 9860
EAST NICOLAUS 11011372 | EAST NICOLAUS 1101 | 152151101 |  | 14.6009 | 1.1358 |  | 280.5 | 0.00025198 | 9042 | 0.076997 | 3763 | 1.9382e-05 | 9861
BUTTE 11072500 | BUTTE 1107 | 103081107 |  | 13.7288 | 1.324 |  | 231.5 | 0.00027652 | 8505 | 0.072638 | 4702 | 1.938e-05 | 9862
MAXWELL 11063036 | MAXWELL 1106 | 62881106 |  | 27.8492 | 0.83885 |  | 478.5 | 0.00025507 | 8981 | 0.076389 | 4057 | 1.9379e-05 | 9863
BIOLA 110397862 | BIOLA 1103 | 252211103 |  | 25.231 | 1.9222 |  | 446.5 | 0.00025071 | 9063 | 0.077275 | 3510 | 1.9378e-05 | 9864
DAIRYLAND 1112977849 | DAIRYLAND 1112 | 252421112 |  | 2.1929 | 0.17081 |  | 39 | 0.00025036 | 9071 | 0.0774 | 3397 | 1.9378e-05 | 9865
EAST NICOLAUS 11021290 | EAST NICOLAUS 1102 | 152151102 |  | 36.1271 | 2.4985 |  | 642.5 | 0.00025582 | 8965 | 0.076308 | 4087 | 1.9374e-05 | 9866
MC ARTHUR 110151398 | MC ARTHUR 1101 | 103491101 |  | 0.86309 | 0.21947 |  | 17.5 | 0.00028827 | 8228 | 0.067297 | 5732 | 1.9364e-05 | 9867
LOCKHEED NO 2 1108CB | LOCKHEED NO 2 1108 | 83001108 |  | 1.2539 | 0 |  | 22.5 | 0.00032113 | 7606 | 0.063252 | 6638 | 1.9363e-05 | 9868
LINDEN 11042458 | LINDEN 1104 | 162071104 |  | 19.0299 | 1.4549 |  | 334.5 | 0.0002501 | 9079 | 0.0774 | 3397 | 1.9358e-05 | 9869
LINCOLN 11011398 | LINCOLN 1101 | 153701101 |  | 3.9939 | 0.34503 |  | 69.5 | 0.00028863 | 8221 | 0.06715 | 5854 | 1.9356e-05 | 9870
LOGAN CREEK 21022442 | LOGAN CREEK 2102 | 103142102 |  | 30.4835 | 0.8479 |  | 522.5 | 0.0002786 | 8456 | 0.070129 | 5014 | 1.9351e-05 | 9871
CAMDEN 11036922F | CAMDEN 1103 | 252301103 |  | 1.3157 | 0.13019 |  | 24.5 | 0.00024982 | 9087 | 0.0774 | 3397 | 1.9336e-05 | 9872
MISSION (X) 1125CB | MISSION (X) 1125 | 22011125 |  | 0.12292 | 0.44482 |  | 10.0095 | 0.00036414 | 6928 | 0.053073 | 8252 | 1.9326e-05 | 9873
LOCKEFORD 210212466 | LOCKEFORD 2102 | 163682102 |  | 15.4801 | 1.7901 |  | 257.8333 | 0.00025156 | 9049 | 0.076714 | 3928 | 1.9325e-05 | 9874
SEMITROPIC 1112CB | SEMITROPIC 1112 | 252901112 |  | 15.2969 | 0.31705 |  | 246.3333 | 0.00024963 | 9090 | 0.0774 | 3396 | 1.9321e-05 | 9875
TEMPLETON 2108CB | TEMPLETON 2108 | 183052108 |  | 5.8759 | 0 |  | 105.5 | 0.00028646 | 8275 | 0.067967 | 5409 | 1.932e-05 | 9876
SCHINDLER 111081340 | SCHINDLER 1110 | 252891110 |  | 18.0393 | 0.57678 |  | 303 | 0.00025404 | 8998 | 0.076224 | 4122 | 1.932e-05 | 9877
DAVIS 110712822 | DAVIS 1107 | 62041107 |  | 31.0237 | 1.5382 |  | 537.3333 | 0.00025023 | 9073 | 0.077287 | 3492 | 1.9317e-05 | 9878
LERDO 1116CB | LERDO 1116 | 253491116 |  | 28.9598 | 0.81563 |  | 484.5 | 0.00025223 | 9037 | 0.077059 | 3726 | 1.9315e-05 | 9879
HOLLISTER 21044068 | HOLLISTER 2104 | 182492104 |  | 30.237 | 3.3022 |  | 553.5 | 0.00028654 | 8273 | 0.067475 | 5618 | 1.9313e-05 | 9880
ARVIN 110153388 | ARVIN 1101 | 253801101 |  | 6.0712 | 0.24653 |  | 107 | 0.00027258 | 8591 | 0.070764 | 4924 | 1.9305e-05 | 9881
PANOCHE 1103735730 | PANOCHE 1103 | 253671103 |  | 6.7052 | 0.070973 |  | 110 | 0.00027945 | 8435 | 0.069268 | 5151 | 1.9304e-05 | 9882
MORMON 1102732178 | MORMON 1102 | 163211102 |  | 6.1574 | 0.61563 |  | 100.6667 | 0.00025177 | 9045 | 0.076916 | 3817 | 1.9298e-05 | 9883
RIVERBANK 171120911 | RIVERBANK 1711 | 163191711 |  | 1.689 | 0.22245 |  | 28.5 | 0.00025943 | 8893 | 0.074714 | 4455 | 1.9296e-05 | 9884
PEACHTON 110135138 | PEACHTON 1101 | 103241101 |  | 10.4349 | 0.32295 |  | 176.3333 | 0.00024971 | 9088 | 0.07737 | 3402 | 1.9295e-05 | 9885
BORDEN 110190050 | BORDEN 1101 | 255121101 |  | 22.6277 | 2.8981 |  | 398.5 | 0.00025862 | 8913 | 0.075221 | 4382 | 1.9284e-05 | 9886
WILLIAMS 110249008 | WILLIAMS 1102 | 62051102 |  | 9.8189 | 0.32625 |  | 185 | 0.00025941 | 8895 | 0.074807 | 4442 | 1.9277e-05 | 9887
TULARE LAKE 11089050 | TULARE LAKE 1108 | 252951108 |  | 6.6047 | 0 |  | 125.5 | 0.00027029 | 8646 | 0.072151 | 4762 | 1.9275e-05 | 9888
GUSTINE 11029628 | GUSTINE 1102 | 163111102 |  | 8.0472 | 0.11166 |  | 142.5 | 0.00012874 | 10893 | 0.16997 | 3185 | 1.9266e-05 | 9889
COLUSA 110130252 | COLUSA 1101 | 62021101 |  | 9.1638 | 0.49187 |  | 161 | 0.00025374 | 9004 | 0.076349 | 4069 | 1.9264e-05 | 9890
ORO LOMA 1115CB | ORO LOMA 1115 | 255371115 |  | 16.9243 | 0.45088 |  | 291.7 | 0.00025318 | 9012 | 0.07628 | 4101 | 1.9253e-05 | 9891
COALINGA NO 2 1107CB | COALINGA NO 2 1107 | 252381107 |  | 15.3242 | 0.25524 |  | 255.5 | 0.00027722 | 8488 | 0.069794 | 5078 | 1.9253e-05 | 9892
LOCKEFORD 210148604 | LOCKEFORD 2101 | 163682101 |  | 6.4963 | 0.56143 |  | 112 | 0.00024875 | 9105 | 0.0774 | 3397 | 1.9253e-05 | 9893
REEDLEY 1106CB | REEDLEY 1106 | 252341106 |  | 39.3316 | 7.9124 |  | 707.6667 | 0.00025772 | 8929 | 0.074686 | 4461 | 1.9248e-05 | 9894
PRUNEDALE 11073062 | PRUNEDALE 1107 | 182961107 |  | 9.0066 | 0.7454 |  | 165.5 | 0.00028722 | 8250 | 0.067002 | 6044 | 1.9244e-05 | 9895
ATWATER 110211810 | ATWATER 1102 | 253611102 |  | 19.7597 | 2.3077 |  | 354.5 | 0.00024901 | 9101 | 0.077263 | 3526 | 1.9239e-05 | 9896
RICE 110261906 | RICE 1102 | 62831102 |  | 0.14457 | 0 |  | 2 | 0.0002485 | 9109 | 0.0774 | 3397 | 1.9234e-05 | 9897
CORNING 110485336 | CORNING 1104 | 103331104 |  | 15.6497 | 2.2997 |  | 282.3333 | 0.00028594 | 8289 | 0.067343 | 5707 | 1.9222e-05 | 9898
ALPAUGH 11048819F | ALPAUGH 1104 | 254001104 |  | 1.7802 | 0.037602 |  | 31.5 | 0.00024822 | 9122 | 0.0774 | 3397 | 1.9212e-05 | 9899
SANTA YNEZ 1104Y28 | SANTA YNEZ 1104 | 182721104 |  | 1.4512 | 0.024979 |  | 29 | 0.00028661 | 8269 | 0.067 | 6057 | 1.9203e-05 | 9900
ORO LOMA 1106CB | ORO LOMA 1106 | 255371106 |  | 25.9463 | 1.4447 |  | 437.5 | 0.00025004 | 9082 | 0.076924 | 3812 | 1.9189e-05 | 9901
ORO LOMA 110876656 | ORO LOMA 1108 | 255371108 |  | 20.1826 | 1.2382 |  | 348.5 | 0.00024985 | 9086 | 0.076881 | 3841 | 1.9189e-05 | 9902
ARVIN 110115909 | ARVIN 1101 | 253801101 |  | 1.6538 | 0 |  | 26.5 | 0.00027765 | 8474 | 0.070817 | 4916 | 1.9188e-05 | 9903
PLUMAS 210650800 | PLUMAS 2106 | 153732106 |  | 11.3365 | 1.119 |  | 210 | 0.00024861 | 9107 | 0.077175 | 3621 | 1.9187e-05 | 9904
KERN OIL 110646960 | KERN OIL 1106 | 252721106 |  | 1.107 | 0.045469 |  | 17 | 0.00026941 | 8664 | 0.07119 | 4872 | 1.9181e-05 | 9905
PARLIER 110349150 | PARLIER 1103 | 252291103 |  | 14.3771 | 2.7995 |  | 263 | 0.00024826 | 9121 | 0.077307 | 3466 | 1.9177e-05 | 9906
OLIVEHURST 11031240 | OLIVEHURST 1103 | 152901103 |  | 15.9089 | 1.1728 |  | 285.5 | 0.00024775 | 9133 | 0.0774 | 3397 | 1.9176e-05 | 9907
CAMDEN 11046200 | CAMDEN 1104 | 252301104 |  | 25.2452 | 2.3177 |  | 441 | 0.00024902 | 9100 | 0.077129 | 3665 | 1.9175e-05 | 9908
ECHO SUMMIT 1101889106 | ECHO SUMMIT 1101 | 158031101 |  | 2.4608 | 0.38318 |  | 53.5 | 0.00026028 | 8878 | 0.077955 | 3391 | 1.9171e-05 | 9909
ATWATER 11037170 | ATWATER 1103 | 253611103 |  | 7.3503 | 0.60598 |  | 126.5 | 0.00024792 | 9126 | 0.077296 | 3481 | 1.9169e-05 | 9910
OLD RIVER 11031647 | OLD RIVER 1103 | 252821103 |  | 14.8054 | 0.16411 |  | 248 | 0.0002551 | 8980 | 0.075006 | 4414 | 1.9167e-05 | 9911
STONE CORRAL 11107481F | STONE CORRAL 1110 | 252921110 |  | 9.0748 | 1.4662 |  | 158 | 0.00028413 | 8327 | 0.067592 | 5556 | 1.916e-05 | 9912
LEMOORE 11048650 | LEMOORE 1104 | 253601104 |  | 3.0027 | 0.52834 |  | 55 | 0.00024716 | 9140 | 0.0774 | 3397 | 1.913e-05 | 9913
ARVIN 110154484 | ARVIN 1101 | 253801101 |  | 6.1168 | 0.091895 |  | 105 | 0.00027448 | 8544 | 0.070278 | 4986 | 1.9127e-05 | 9914
BANTA 1103248582 | BANTA 1103 | 162471103 |  | 6.9777 | 0.41404 |  | 143.5 | 0.00025452 | 8988 | 0.075764 | 4273 | 1.9111e-05 | 9915
LIVINGSTON 11014210 | LIVINGSTON 1101 | 252261101 |  | 14.6279 | 0.88867 |  | 241.5 | 0.00025123 | 9055 | 0.076594 | 3984 | 1.9108e-05 | 9916
GIFFEN 11039325 | GIFFEN 1103 | 253151103 |  | 7.8062 | 0.4635 |  | 124.25 | 0.00024814 | 9124 | 0.077077 | 3710 | 1.9103e-05 | 9917
CAMDEN 11026240 | CAMDEN 1102 | 252301102 |  | 43.6726 | 6.3354 |  | 790 | 0.00024677 | 9149 | 0.0774 | 3397 | 1.91e-05 | 9918
LOGAN CREEK 210268318 | LOGAN CREEK 2102 | 103142102 |  | 20.9099 | 2.4129 |  | 361.5 | 0.00028273 | 8359 | 0.067639 | 5530 | 1.9099e-05 | 9919
BAIR 1103CB | BAIR 1103 | 24261103 |  | 0.19997 | 0 |  | 6 | 0.00035979 | 6986 | 0.053073 | 8251 | 1.9095e-05 | 9920
MCKITTRICK 11013092 | MCKITTRICK 1101 | 252781101 |  | 6.8246 | 0.014917 |  | 131 | 0.00028482 | 8313 | 0.067 | 6057 | 1.9083e-05 | 9921
MIDDLETOWN 1101851636 | MIDDLETOWN 1101 | 43141101 |  | 1.0539 | 0.026646 |  | 21 | 0.00022787 | 9538 | 0.084147 | 3377 | 1.9073e-05 | 9922
GARDNER 0401CB | GARDNER 0401 | 254930401 |  | 0.0087917 | 0 |  | 0.5 | 0.00028454 | 8319 | 0.067 | 6057 | 1.9064e-05 | 9923
LIVE OAK 11041282 | LIVE OAK 1104 | 153771104 |  | 42.7683 | 3.6822 |  | 760.5 | 0.00025528 | 8979 | 0.074443 | 4492 | 1.9062e-05 | 9924
CAMDEN 11056740 | CAMDEN 1105 | 252301105 |  | 46.5855 | 3.5399 |  | 797.5 | 0.00024821 | 9123 | 0.076997 | 3762 | 1.9061e-05 | 9925
DIXON 11035932 | DIXON 1103 | 62061103 |  | 18.6067 | 0.74074 |  | 307.5 | 0.00024672 | 9152 | 0.077273 | 3513 | 1.9056e-05 | 9926
GIFFEN 11039620 | GIFFEN 1103 | 253151103 |  | 0.016789 | 0 |  | 0.5 | 0.00024601 | 9164 | 0.0774 | 3397 | 1.9041e-05 | 9927
COLUSA 110179406 | COLUSA 1101 | 62021101 |  | 22.4282 | 0.99951 |  | 389.5 | 0.00025099 | 9058 | 0.076529 | 4006 | 1.904e-05 | 9928
BRENTWOOD 211221256 | BRENTWOOD 2112 | 14592112 |  | 4.9882 | 0.59284 |  | 82 | 0.00025036 | 9069 | 0.076806 | 3882 | 1.9032e-05 | 9929
SHEPHERD 2111537008 | SHEPHERD 2111 | 252062111 |  | 6.0501 | 0 |  | 108 | 0.00028404 | 8329 | 0.067 | 6057 | 1.9031e-05 | 9930
COLUSA JUNCTION 11013010 | COLUSA JUNCTION 1101 | 62071101 |  | 13.4572 | 0.39188 |  | 235.5 | 0.0002464 | 9157 | 0.077297 | 3478 | 1.9026e-05 | 9931
DIVIDE 1103CB | DIVIDE 1103 | 182571103 |  | 0.16863 | 0 |  | 2.0833 | 0.00028328 | 8344 | 0.067145 | 5857 | 1.9024e-05 | 9932
STROUD 1102CB | STROUD 1102 | 253661102 |  | 20.457 | 0.84962 |  | 340.5 | 0.00025926 | 8900 | 0.075152 | 4393 | 1.9024e-05 | 9933
GANSO 1104312168 | GANSO 1104 | 254541104 |  | 2.4716 | 0.020738 |  | 40.5 | 0.00024575 | 9175 | 0.0774 | 3397 | 1.9021e-05 | 9934
SHAFTER 11121453 | SHAFTER 1112 | 253651112 |  | 26.1893 | 1.2137 |  | 429 | 0.00024555 | 9177 | 0.0774 | 3397 | 1.9005e-05 | 9935
CALFLAX 11039560 | CALFLAX 1103 | 253441103 |  | 21.0408 | 0.32323 |  | 356 | 0.00025633 | 8957 | 0.074156 | 4534 | 1.9001e-05 | 9936
CAYUCOS 11014701 | CAYUCOS 1101 | 182551101 | TRUE | 8.7234 | 0.10734 | 0.45788 | 168.5 | 0.00014173 | 10772 | 0.19907 | 3145 | 1.8999e-05 | 9937
RICE 110348674 | RICE 1103 | 62831103 |  | 0.10833 | 0 |  | 2.5 | 0.00024538 | 9179 | 0.0774 | 3397 | 1.8992e-05 | 9938
ARCATA 11056544 | ARCATA 1105 | 192021105 |  | 21.63 | 2.4227 |  | 382.5 | 0.00028508 | 8306 | 0.066814 | 6118 | 1.8979e-05 | 9939
MENDOTA 1104681764 | MENDOTA 1104 | 252311104 |  | 11.25 | 0.082544 |  | 185.5 | 0.00024616 | 9160 | 0.077184 | 3607 | 1.8976e-05 | 9940
MADERA 1119583476 | MADERA 1119 | 252761119 |  | 5.7014 | 0.27157 |  | 96.5 | 0.00024581 | 9172 | 0.077237 | 3547 | 1.8975e-05 | 9941
ORO LOMA 11069790 | ORO LOMA 1106 | 255371106 |  | 25.8463 | 0.7265 |  | 460 | 0.00024544 | 9178 | 0.077285 | 3496 | 1.8968e-05 | 9942
GANSO 11034885 | GANSO 1103 | 254541103 |  | 6.9372 | 0.11732 |  | 117.5 | 0.00024834 | 9119 | 0.076658 | 3953 | 1.8965e-05 | 9943
SANGER 110892484 | SANGER 1108 | 252351108 |  | 10.6385 | 1.7259 |  | 193 | 0.00024496 | 9187 | 0.0774 | 3397 | 1.896e-05 | 9944
CAMBRIA 1101CB | CAMBRIA 1101 | 182771101 |  | 6.1557 | 0.53199 |  | 123.5 | 0.00028261 | 8361 | 0.067044 | 5954 | 1.8952e-05 | 9945
WAHTOKE 11087500 | WAHTOKE 1108 | 254531108 |  | 25.278 | 4.5676 |  | 473 | 0.00024491 | 9188 | 0.07726 | 3530 | 1.894e-05 | 9946
ANITA 11022088 | ANITA 1102 | 102841102 |  | 22.0141 | 0.91316 |  | 383 | 0.00025884 | 8908 | 0.074 | 4555 | 1.893e-05 | 9947
OLD RIVER 1105684892 | OLD RIVER 1105 | 252821105 |  | 9.7675 | 0.12437 |  | 166.5 | 0.000245 | 9186 | 0.077255 | 3534 | 1.8921e-05 | 9948
CASTROVILLE 21033060 | CASTROVILLE 2103 | 182352103 |  | 15.2336 | 0.52942 |  | 305.5 | 0.00028226 | 8370 | 0.067034 | 5977 | 1.8921e-05 | 9949
TIVY VALLEY 11067150 | TIVY VALLEY 1106 | 252941106 |  | 9.2786 | 1.1393 |  | 178.5 | 0.00028076 | 8401 | 0.067395 | 5672 | 1.8898e-05 | 9950
CASTROVILLE 2103196060 | CASTROVILLE 2103 | 182352103 |  | 3.6631 | 0.32112 |  | 75 | 0.00028179 | 8382 | 0.067112 | 5887 | 1.8895e-05 | 9951
GOOSE LAKE 2104CB | GOOSE LAKE 2104 | 254202104 |  | 8.4543 | 0.20321 |  | 141.1667 | 0.00026228 | 8824 | 0.072292 | 4745 | 1.8894e-05 | 9952
BELRIDGE 1A 1101CB | BELRIDGE 1A 1101 | 254371101 |  | 0.014866 | 0 |  | 2 | 0.00028198 | 8376 | 0.067 | 6057 | 1.8893e-05 | 9953
OLD RIVER 11031653 | OLD RIVER 1103 | 252821103 |  | 7.8751 | 0.14333 |  | 133 | 0.00024469 | 9191 | 0.077217 | 3578 | 1.8891e-05 | 9954
SCHINDLER 1112609842 | SCHINDLER 1112 | 252891112 |  | 6.377 | 0.34255 |  | 107 | 0.00024514 | 9184 | 0.077172 | 3626 | 1.8889e-05 | 9955
MIDWAY 1104CB | MIDWAY 1104 | 252611104 |  | 41.9245 | 5.6062 |  | 736 | 0.00025982 | 8886 | 0.073905 | 4565 | 1.8888e-05 | 9956
CAL WATER 1102135060 | CAL WATER 1102 | 255451102 |  | 4.0203 | 0.13277 |  | 68.5 | 0.00028039 | 8411 | 0.067363 | 5692 | 1.8886e-05 | 9957
VACA DIXON 110365434 | VACA DIXON 1103 | 63591103 |  | 11.4793 | 0.85098 |  | 189.5 | 0.00027721 | 8489 | 0.0684 | 5304 | 1.888e-05 | 9958
WOODWARD 2108D412 | WOODWARD 2108 | 255292108 |  | 2.5053 | 0.086057 |  | 44 | 0.00027934 | 8438 | 0.067473 | 5619 | 1.8873e-05 | 9959
SCHINDLER 1111541614 | SCHINDLER 1111 | 252891111 |  | 3.5629 | 0.098786 |  | 60.5 | 0.00024578 | 9174 | 0.076939 | 3801 | 1.8872e-05 | 9960
VINA 11011572 | VINA 1101 | 103581101 |  | 12.8521 | 0.51033 |  | 244.5 | 0.00027456 | 8541 | 0.068966 | 5197 | 1.8872e-05 | 9961
CARUTHERS 1102803408 | CARUTHERS 1102 | 252371102 |  | 1.6741 | 0.052301 |  | 28.5 | 0.00024381 | 9201 | 0.0774 | 3397 | 1.8871e-05 | 9962
HURON 11169300 | HURON 1116 | 253161116 |  | 6.607 | 0.093651 |  | 103 | 0.00024759 | 9135 | 0.076442 | 4037 | 1.8869e-05 | 9963
MIDWAY 1102CB | MIDWAY 1102 | 252611102 |  | 7.6754 | 0.20875 |  | 131.3333 | 0.00024919 | 9097 | 0.076539 | 4001 | 1.8864e-05 | 9964
PEASE 11041228 | PEASE 1104 | 153751104 |  | 20.0512 | 0.91963 |  | 352 | 0.00025853 | 8916 | 0.072694 | 4695 | 1.8864e-05 | 9965
TEJON 110595130 | TEJON 1105 | 252931105 |  | 12.8872 | 0.27971 |  | 217 | 0.00026938 | 8665 | 0.069956 | 5052 | 1.886e-05 | 9966
BRENTWOOD 2112B542R | BRENTWOOD 2112 | 14592112 |  | 16.1033 | 1.9164 |  | 237.8333 | 0.00025631 | 8959 | 0.075041 | 4409 | 1.8853e-05 | 9967
CARUTHERS 11046550 | CARUTHERS 1104 | 252371104 |  | 7.604 | 0.58403 |  | 135 | 0.00024352 | 9213 | 0.0774 | 3397 | 1.8849e-05 | 9968
CHOWCHILLA 11016108 | CHOWCHILLA 1101 | 254101101 |  | 2.3854 | 0.15145 |  | 39.5 | 0.00024339 | 9218 | 0.0774 | 3397 | 1.8838e-05 | 9969
HENRIETTA 1110CB | HENRIETTA 1110 | 252681110 |  | 30.6479 | 0.5728 |  | 510 | 0.00025018 | 9074 | 0.07629 | 4094 | 1.8835e-05 | 9970
WEBER 11022324 | WEBER 1102 | 163481102 |  | 15.5775 | 1.1319 |  | 276 | 0.00024737 | 9137 | 0.076669 | 3949 | 1.8833e-05 | 9971
GERBER 110241572 | GERBER 1102 | 103391102 |  | 17.1771 | 2.0147 |  | 288.5 | 0.00027854 | 8459 | 0.067587 | 5560 | 1.8821e-05 | 9972
LAKEVIEW 11021009 | LAKEVIEW 1102 | 253411102 |  | 18.1117 | 0.12998 |  | 301.5 | 0.00025313 | 9014 | 0.073761 | 4575 | 1.8817e-05 | 9973
GATES 1110264200 | GATES 1110 | 253931110 |  | 13.3132 | 0.10328 |  | 219 | 0.00024373 | 9205 | 0.077233 | 3548 | 1.8815e-05 | 9974
HOLLISTER 210157338 | HOLLISTER 2101 | 182492101 |  | 0.020963 | 0 |  | 1.5 | 0.00028075 | 8402 | 0.067 | 6057 | 1.881e-05 | 9975
JACINTO 110163962 | JACINTO 1101 | 102851101 |  | 4.5466 | 0.42751 |  | 79 | 0.00027764 | 8475 | 0.067924 | 5426 | 1.8809e-05 | 9976
TUPMAN 11041742 | TUPMAN 1104 | 254561104 |  | 1.6128 | 0.07298 |  | 25 | 0.00024296 | 9224 | 0.0774 | 3397 | 1.8805e-05 | 9977
SALINAS 110997654 | SALINAS 1109 | 182011109 |  | 6.4945 | 0.51362 |  | 139 | 0.00027673 | 8501 | 0.067934 | 5420 | 1.8803e-05 | 9978
DINUBA 1105630598 | DINUBA 1105 | 254091105 |  | 10.6069 | 0.59859 |  | 173 | 0.00024352 | 9214 | 0.077262 | 3528 | 1.8801e-05 | 9979
REEDLEY 11127240 | REEDLEY 1112 | 252341112 | FALSE | 25.4782 | 3.3178 | 0.68836 | 449.5 | 0.00020031 | 10036 | 0.11533 | 3277 | 1.8796e-05 | 9980
TAMARACK 1102482896 | TAMARACK 1102 | 152291102 |  | 6.6463 | 1.3549 |  | 136.5 | 0.00027257 | 8592 | 0.068902 | 5205 | 1.8795e-05 | 9981
CROWS LANDING 110190590 | CROWS LANDING 1101 | 163251101 |  | 10.3701 | 0.38735 |  | 172 | 0.00024598 | 9166 | 0.07634 | 4072 | 1.8794e-05 | 9982
DAIRYLAND 1109735784 | DAIRYLAND 1109 | 252421109 |  | 20.7992 | 0.57875 |  | 341.5 | 0.00024281 | 9227 | 0.0774 | 3397 | 1.8794e-05 | 9983
GLENN 110152954 | GLENN 1101 | 102601101 |  | 1.5097 | 0.15105 |  | 25 | 0.00027948 | 8431 | 0.067267 | 5753 | 1.8791e-05 | 9984
CORNING 110237396 | CORNING 1102 | 103331102 |  | 9.0144 | 1.1474 |  | 163.8333 | 0.00027847 | 8461 | 0.06758 | 5565 | 1.8786e-05 | 9985
LIVINGSTON 1104783470 | LIVINGSTON 1104 | 252261104 |  | 1.7673 | 0.17705 |  | 32 | 0.0002442 | 9196 | 0.076908 | 3823 | 1.8776e-05 | 9986
MESA 1104M08 | MESA 1104 | 182821104 |  | 29.3546 | 0.7889 |  | 576 | 0.00027861 | 8455 | 0.067466 | 5625 | 1.8769e-05 | 9987
PARLIER 11045180 | PARLIER 1104 | 252291104 |  | 29.1359 | 4.8018 |  | 536.5 | 0.00024258 | 9233 | 0.077348 | 3415 | 1.8758e-05 | 9988
CHOLAME 2102CB | CHOLAME 2102 | 182562102 |  | 7.2991 | 0.1887 |  | 119.1667 | 0.00027904 | 8441 | 0.067168 | 5837 | 1.8753e-05 | 9989
GIFFEN 1103CB | GIFFEN 1103 | 253151103 |  | 26.2543 | 0.38284 |  | 417.0833 | 0.00024413 | 9197 | 0.076974 | 3780 | 1.875e-05 | 9990
BOGUE 110696114 | BOGUE 1106 | 153781106 |  | 0.025986 | 0 |  | 0.5 | 0.00024212 | 9246 | 0.0774 | 3397 | 1.874e-05 | 9991
PEACHTON 11031010 | PEACHTON 1103 | 103241103 |  | 27.7622 | 1.684 |  | 475.3333 | 0.00024827 | 9120 | 0.075719 | 4286 | 1.874e-05 | 9992
LIVE OAK 110451586 | LIVE OAK 1104 | 153771104 |  | 9.2638 | 0.94123 |  | 166.5 | 0.00024565 | 9176 | 0.076626 | 3972 | 1.8737e-05 | 9993
SAN JOAQUIN 1106D4628 | SAN JOAQUIN 1106 | 252361106 |  | 5.7441 | 0.32287 |  | 101.5 | 0.00024434 | 9194 | 0.076766 | 3900 | 1.8736e-05 | 9994
EL NIDO 11034940 | EL NIDO 1103 | 252451103 |  | 12.5826 | 0.86793 |  | 212.5 | 0.00024222 | 9242 | 0.077326 | 3434 | 1.8734e-05 | 9995
TEJON 1105CB | TEJON 1105 | 252931105 |  | 18.3987 | 0.48126 |  | 336.5833 | 0.00025013 | 9077 | 0.07521 | 4385 | 1.8731e-05 | 9996
GUERNSEY 11048380 | GUERNSEY 1104 | 252661104 |  | 11.4572 | 1.3981 |  | 196.5 | 0.00024252 | 9235 | 0.077276 | 3509 | 1.872e-05 | 9997
GATES 110437824 | GATES 1104 | 253931104 |  | 7.6628 | 0.20916 |  | 127.5 | 0.00024584 | 9171 | 0.076391 | 4056 | 1.8719e-05 | 9998
LINDEN 11033044 | LINDEN 1103 | 162071103 |  | 14.602 | 1.0072 |  | 263 | 0.00024736 | 9138 | 0.075803 | 4264 | 1.8717e-05 | 9999
GUERNSEY 110147746 | GUERNSEY 1101 | 252661101 |  | 17.5656 | 0.6109 |  | 288 | 0.00024253 | 9234 | 0.077209 | 3585 | 1.8712e-05 | 10000
FREMONT 1104MR339 | FREMONT 1104 | 14351104 |  | 2.5267 | 0.39362 |  | 49.5 | 0.00027475 | 8535 | 0.068215 | 5358 | 1.8703e-05 | 10001
LOGAN CREEK 2102806 | LOGAN CREEK 2102 | 103142102 |  | 9.0691 | 0.90452 |  | 157 | 0.00026634 | 8736 | 0.070358 | 4969 | 1.8702e-05 | 10002
SAN ARDO 1101824808 | SAN ARDO 1101 | 182191101 |  | 1.938 | 0 |  | 40.5 | 0.00027439 | 8547 | 0.068031 | 5399 | 1.8689e-05 | 10003
MC ARTHUR 110137344 | MC ARTHUR 1101 | 103491101 | TRUE | 8.8534 | 1.7241 | 0.058559 | 148 | 0.00020909 | 9890 | 0.086559 | 3359 | 1.8686e-05 | 10004
GATES 11028040 | GATES 1102 | 253931102 |  | 3.0795 | 0.075368 |  | 56 | 0.00024142 | 9259 | 0.0774 | 3397 | 1.8686e-05 | 10005
MC MULLIN 1105CUS9322 | MC MULLIN 1105 | 254411105 |  | 0.038475 | 0 |  | 0.5 | 0.00024134 | 9262 | 0.0774 | 3397 | 1.868e-05 | 10006
EAST NICOLAUS 11011362 | EAST NICOLAUS 1101 | 152151101 |  | 19.8232 | 0.97015 |  | 350 | 0.00024167 | 9254 | 0.07731 | 3459 | 1.8672e-05 | 10007
CARUTHERS 1102188898 | CARUTHERS 1102 | 252371102 |  | 14.2922 | 0.80418 |  | 250 | 0.00024185 | 9249 | 0.077303 | 3469 | 1.8672e-05 | 10008
CASTROVILLE 21033014 | CASTROVILLE 2103 | 182352103 |  | 7.9303 | 0.48831 |  | 118.8333 | 0.00027622 | 8510 | 0.067525 | 5587 | 1.8668e-05 | 10009
HAMILTON A 11022210 | HAMILTON A 1102 | 102121102 |  | 30.3006 | 1.164 |  | 550.5 | 0.00026755 | 8708 | 0.071213 | 4869 | 1.8653e-05 | 10010
ESQUON 11022060 | ESQUON 1102 | 102171102 |  | 32.3527 | 1.1531 |  | 533.5 | 0.00026561 | 8749 | 0.071566 | 4821 | 1.8652e-05 | 10011
GUERNSEY 110668132 | GUERNSEY 1106 | 252661106 |  | 22.3556 | 1.8475 |  | 387 | 0.00024133 | 9263 | 0.077298 | 3473 | 1.8646e-05 | 10012
JACOBS CORNER 11018520 | JACOBS CORNER 1101 | 254771101 |  | 11.5821 | 2.4327 |  | 214 | 0.00024087 | 9272 | 0.0774 | 3397 | 1.8643e-05 | 10013
PIERCY 2111CB | PIERCY 2111 | 83912111 |  | 0.91256 | 0.09346 |  | 29 | 0.00028187 | 8380 | 0.066039 | 6264 | 1.8642e-05 | 10014
KINGSBURG 1113891944 | KINGSBURG 1113 | 252241113 |  | 15.1115 | 0.57689 |  | 257.5 | 0.00024227 | 9241 | 0.077055 | 3729 | 1.8642e-05 | 10015
BORDEN 1101CB | BORDEN 1101 | 255121101 |  | 19.2812 | 0.46972 |  | 320 | 0.00024212 | 9245 | 0.07721 | 3582 | 1.8641e-05 | 10016
ELK CREEK 1101CB | ELK CREEK 1101 | 102781101 | TRUE | 0.099585 | 0 | 0.043023 | 2 | 0.00026706 | 8718 | 0.069797 | 5077 | 1.864e-05 | 10017
WILLIAMS 110241772 | WILLIAMS 1102 | 62051102 |  | 25.8019 | 0.95369 |  | 442.5 | 0.00024363 | 9210 | 0.076697 | 3936 | 1.8627e-05 | 10018
FIREBAUGH 110336942 | FIREBAUGH 1103 | 253471103 |  | 25.3778 | 0.72054 |  | 459.5 | 0.00024331 | 9220 | 0.076786 | 3894 | 1.8621e-05 | 10019
HONCUT 11021380 | HONCUT 1102 | 103211102 |  | 30.3616 | 2.6628 |  | 538 | 0.00024643 | 9156 | 0.076501 | 4017 | 1.8621e-05 | 10020
ARBUCKLE 11023016 | ARBUCKLE 1102 | 62081102 |  | 6.9085 | 0.15934 |  | 117.5 | 0.00024613 | 9161 | 0.0762 | 4128 | 1.8621e-05 | 10021
SISQUOC 1104CB | SISQUOC 1104 | 182811104 |  | 16.8191 | 0.54495 |  | 290.5 | 0.00027548 | 8524 | 0.067607 | 5543 | 1.8611e-05 | 10022
SAN BERNARD 1101830398 | SAN BERNARD 1101 | 253191101 |  | 11.8652 | 0.084953 |  | 198.5 | 0.00027169 | 8615 | 0.068528 | 5282 | 1.8599e-05 | 10023
SCHINDLER 110597252 | SCHINDLER 1105 | 252891105 |  | 16.5855 | 0.36273 |  | 273 | 0.00024078 | 9275 | 0.077222 | 3567 | 1.8575e-05 | 10024
TEMPLETON 2112CB | TEMPLETON 2112 | 183052112 |  | 7.0465 | 0.41305 |  | 124.8333 | 0.00027851 | 8460 | 0.067013 | 6019 | 1.8572e-05 | 10025
NEWMAN 110290410 | NEWMAN 1102 | 162741102 |  | 3.7778 | 0.18927 |  | 63 | 0.00024685 | 9147 | 0.075549 | 4328 | 1.8559e-05 | 10026
RICE 110175402 | RICE 1101 | 62831101 |  | 8.4129 | 0.33213 |  | 145 | 0.00024084 | 9273 | 0.077064 | 3722 | 1.8559e-05 | 10027
CAMDEN 11038920 | CAMDEN 1103 | 252301103 |  | 21.9251 | 3.3155 |  | 390 | 0.00025007 | 9080 | 0.075875 | 4237 | 1.8558e-05 | 10028
HENRIETTA 1106CB | HENRIETTA 1106 | 252681106 |  | 43.4447 | 0.56253 |  | 738.8333 | 0.00024513 | 9185 | 0.076095 | 4163 | 1.8545e-05 | 10029
TEJON 11024525 | TEJON 1102 | 252931102 |  | 14.0452 | 0.011601 |  | 264.5 | 0.00026963 | 8660 | 0.068839 | 5216 | 1.8543e-05 | 10030
ALPAUGH 110396038 | ALPAUGH 1103 | 254001103 |  | 3.7775 | 0.1708 |  | 67.3333 | 0.00024107 | 9267 | 0.077322 | 3439 | 1.8536e-05 | 10031
GOOSE LAKE 21041472 | GOOSE LAKE 2104 | 254202104 |  | 2.3583 | 0.069773 |  | 37 | 0.00024789 | 9129 | 0.075292 | 4368 | 1.8532e-05 | 10032
MAXWELL 1105910362 | MAXWELL 1105 | 62881105 |  | 14.5054 | 0.29715 |  | 245.5 | 0.00026298 | 8805 | 0.070235 | 4996 | 1.8516e-05 | 10033
TUPMAN 1104CB | TUPMAN 1104 | 254561104 |  | 17.2486 | 1.3496 |  | 292.5833 | 0.00024265 | 9230 | 0.076328 | 4077 | 1.851e-05 | 10034
ZAMORA 11066992 | ZAMORA 1106 | 63191106 |  | 18.5616 | 0.83562 |  | 318 | 0.00025912 | 8902 | 0.071313 | 4854 | 1.8507e-05 | 10035
BRENTWOOD 2105B534R | BRENTWOOD 2105 | 14592105 | TRUE | 14.6552 | 2.3301 | 0.0044661 | 251.5 | 0.00026227 | 8825 | 0.071226 | 4866 | 1.8497e-05 | 10036
MADISON 110353322 | MADISON 1103 | 63171103 |  | 29.9057 | 2.6645 |  | 479.5 | 0.00027016 | 8650 | 0.068873 | 5211 | 1.8495e-05 | 10037
CRESSEY 21049880 | CRESSEY 2104 | 254702104 |  | 29.7312 | 0.68574 |  | 506 | 0.00023895 | 9302 | 0.0774 | 3397 | 1.8495e-05 | 10038
DINUBA 11047020 | DINUBA 1104 | 254091104 |  | 15.1008 | 2.9205 |  | 275.5 | 0.00024064 | 9277 | 0.07714 | 3656 | 1.849e-05 | 10039
SANTA RITA 1102177196 | SANTA RITA 1102 | 253541102 |  | 8.0822 | 0.52939 |  | 143.5 | 0.0002395 | 9294 | 0.07723 | 3553 | 1.8486e-05 | 10040
CAPAY 11012256 | CAPAY 1101 | 102111101 |  | 18.9815 | 1.3165 |  | 335.5 | 0.0002742 | 8550 | 0.06746 | 5628 | 1.8468e-05 | 10041
TEMBLOR 2103768638 | TEMBLOR 2103 | 252552103 |  | 24.5139 | 0.19447 |  | 416.25 | 0.00026584 | 8745 | 0.070247 | 4992 | 1.8465e-05 | 10042
CARUTHERS 1105CB | CARUTHERS 1105 | 252371105 |  | 32.731 | 1.0258 |  | 531.0833 | 0.00023897 | 9301 | 0.077308 | 3464 | 1.8463e-05 | 10043
PANORAMA 11019092 | PANORAMA 1101 | 103461101 | TRUE | 9.7661 | 1.0619 | 0.10045 | 182 | 0.00027433 | 8548 | 0.067312 | 5723 | 1.8462e-05 | 10044
CORNING 11011440 | CORNING 1101 | 103331101 |  | 27.4536 | 2.1294 |  | 470.5 | 0.00027246 | 8596 | 0.067817 | 5470 | 1.8448e-05 | 10045
BALFOUR 1101744523 | BALFOUR 1101 | 14321101 |  | 12.86 | 1.3486 |  | 200 | 0.00025494 | 8983 | 0.072679 | 4697 | 1.8434e-05 | 10046
ELK HILLS 1106639540 | ELK HILLS 1106 | 252441106 |  | 10.1545 | 0.030867 |  | 174 | 0.00025015 | 9076 | 0.073529 | 4607 | 1.8427e-05 | 10047
TULARE LAKE 110876864 | TULARE LAKE 1108 | 252951108 |  | 16.8283 | 0.24007 |  | 292 | 0.00026027 | 8879 | 0.071061 | 4890 | 1.8422e-05 | 10048
CANTUA 11019890 | CANTUA 1101 | 253591101 |  | 1.8783 | 0 |  | 30.5 | 0.00026963 | 8659 | 0.070069 | 5029 | 1.8416e-05 | 10049
CABRILLO 1104Y08 | CABRILLO 1104 | 183101104 |  | 13.6445 | 0.85955 |  | 229.5 | 0.00026668 | 8728 | 0.069076 | 5180 | 1.8409e-05 | 10050
SCHINDLER 1112CB | SCHINDLER 1112 | 252891112 |  | 29.9906 | 0.44126 |  | 495.6667 | 0.00024314 | 9221 | 0.076059 | 4179 | 1.8404e-05 | 10051
JACINTO 11012608 | JACINTO 1101 | 102851101 |  | 29.8977 | 1.4042 |  | 515 | 0.0002594 | 8897 | 0.071827 | 4790 | 1.8404e-05 | 10052
EL NIDO 1103661820 | EL NIDO 1103 | 252451103 |  | 25.9916 | 0.82794 |  | 431.5 | 0.00023769 | 9328 | 0.0774 | 3397 | 1.8397e-05 | 10053
HARDWICK 110175900 | HARDWICK 1101 | 253711101 |  | 14.4464 | 1.667 |  | 264 | 0.00023765 | 9330 | 0.0774 | 3397 | 1.8394e-05 | 10054
CAMDEN 11036921F | CAMDEN 1103 | 252301103 |  | 5.2787 | 0.40265 |  | 97.5 | 0.00023865 | 9311 | 0.077239 | 3546 | 1.8394e-05 | 10055
RIVER ROCK 1101CB | RIVER ROCK 1101 | 255251101 |  | 0.020851 | 0 |  | 1.5 | 0.00027448 | 8543 | 0.067 | 6057 | 1.839e-05 | 10056
LERDO 11131550 | LERDO 1113 | 253491113 |  | 16.9755 | 0.32455 |  | 286.5 | 0.00023754 | 9333 | 0.0774 | 3397 | 1.8386e-05 | 10057
CRESSEY 210453374 | CRESSEY 2104 | 254702104 |  | 12.6763 | 0.12354 |  | 219.5 | 0.00023917 | 9298 | 0.077076 | 3711 | 1.8384e-05 | 10058
HARDWICK 1102CB | HARDWICK 1102 | 253711102 |  | 23.181 | 3.3273 |  | 416.5 | 0.00023798 | 9321 | 0.077225 | 3559 | 1.836e-05 | 10059
GERBER 110246628 | GERBER 1102 | 103391102 |  | 17.4581 | 0.56361 |  | 352.5 | 0.00026851 | 8688 | 0.069138 | 5169 | 1.8359e-05 | 10060
HARDWICK 11026050 | HARDWICK 1102 | 253711102 |  | 24.3605 | 3.4478 |  | 456 | 0.00023995 | 9289 | 0.076675 | 3945 | 1.8352e-05 | 10061
PUTAH CREEK 110594238 | PUTAH CREEK 1105 | 63681105 |  | 4.7286 | 0.24443 |  | 80 | 0.00027263 | 8589 | 0.06749 | 5610 | 1.835e-05 | 10062
WHEATLAND 11042218 | WHEATLAND 1104 | 152811104 |  | 37.2423 | 1.5909 |  | 648.5 | 0.00025332 | 9009 | 0.072637 | 4704 | 1.8325e-05 | 10063
ORLAND B 11012216 | ORLAND B 1101 | 102701101 |  | 19.2894 | 2.3111 |  | 334 | 0.00027211 | 8603 | 0.067383 | 5682 | 1.8322e-05 | 10064
BUTTE 11032104 | BUTTE 1103 | 103081103 |  | 9.5356 | 0.22446 |  | 189 | 0.00026698 | 8720 | 0.068596 | 5262 | 1.8317e-05 | 10065
GANSO 1104602388 | GANSO 1104 | 254541104 |  | 0.10198 | 0 |  | 1.5 | 0.00023661 | 9347 | 0.0774 | 3397 | 1.8313e-05 | 10066
ARBUCKLE 110134756 | ARBUCKLE 1101 | 62081101 |  | 6.9062 | 0.40986 |  | 119 | 0.00027049 | 8639 | 0.0686 | 5261 | 1.831e-05 | 10067
STONE CORRAL 1108CB | STONE CORRAL 1108 | 252921108 |  | 12.1991 | 1.3624 |  | 208.3333 | 0.00026213 | 8829 | 0.071042 | 4891 | 1.8308e-05 | 10068
NEW HOPE 11021284 | NEW HOPE 1102 | 162081102 |  | 23.1641 | 1.6187 |  | 424.5 | 0.00023737 | 9336 | 0.077186 | 3602 | 1.8299e-05 | 10069
COTTLE 17073290 | COTTLE 1707 | 163711707 |  | 39.7757 | 2.0513 |  | 697 | 0.0002388 | 9307 | 0.076898 | 3834 | 1.8296e-05 | 10070
LOCKEFORD 21012488 | LOCKEFORD 2101 | 163682101 |  | 15.5501 | 2.9739 |  | 279.5 | 0.00023622 | 9355 | 0.0774 | 3397 | 1.8284e-05 | 10071
LEMOORE 11048310 | LEMOORE 1104 | 253601104 |  | 24.8231 | 4.5063 |  | 463 | 0.00023697 | 9340 | 0.077208 | 3587 | 1.8281e-05 | 10072
TUPMAN 1106CB | TUPMAN 1106 | 254561106 |  | 15.4832 | 0.52714 |  | 260.5833 | 0.00023757 | 9331 | 0.077154 | 3642 | 1.8278e-05 | 10073
BIOLA 1102CB | BIOLA 1102 | 252211102 |  | 11.1439 | 0.67018 |  | 194.1667 | 0.00023656 | 9350 | 0.077275 | 3511 | 1.8272e-05 | 10074
SISQUOC 1104M58 | SISQUOC 1104 | 182811104 |  | 10.1164 | 0.22062 |  | 168.5 | 0.00027269 | 8587 | 0.067 | 6054 | 1.827e-05 | 10075
BORDEN 110110560 | BORDEN 1101 | 255121101 |  | 4.9336 | 0.25622 |  | 88.5 | 0.00026402 | 8780 | 0.071232 | 4865 | 1.8266e-05 | 10076
VALLEY HOME 1703CB | VALLEY HOME 1703 | 162981703 |  | 35.3009 | 0.86611 |  | 627.3333 | 0.00023799 | 9320 | 0.076618 | 3975 | 1.8265e-05 | 10077
LOS MOLINOS 11011308 | LOS MOLINOS 1101 | 103481101 |  | 11.7774 | 0.80999 |  | 216.5 | 0.00027258 | 8590 | 0.067002 | 6043 | 1.8264e-05 | 10078
GREEN VALLEY 2101128618 | GREEN VALLEY 2101 | 83192101 | TRUE | 2.722 | 0.14761 | 0.21443 | 59.5 | 0.00021444 | 9785 | 0.12071 | 3264 | 1.8262e-05 | 10079
LINDEN 11032359 | LINDEN 1103 | 162071103 |  | 1.0729 | 0.12328 |  | 20.5 | 0.00023574 | 9369 | 0.0774 | 3397 | 1.8246e-05 | 10080
DINUBA 11047876F | DINUBA 1104 | 254091104 |  | 4.5346 | 0.67061 |  | 84.5 | 0.00023571 | 9370 | 0.0774 | 3397 | 1.8244e-05 | 10081
ARVIN 110235412 | ARVIN 1102 | 253801102 |  | 7.4149 | 0.043822 |  | 130 | 0.00024309 | 9223 | 0.075436 | 4345 | 1.824e-05 | 10082
PANOCHE 1102892696 | PANOCHE 1102 | 253671102 |  | 4.8294 | 0.041565 |  | 80 | 0.00026207 | 8834 | 0.069577 | 5108 | 1.8234e-05 | 10083
DAVIS 11079382 | DAVIS 1107 | 62041107 |  | 37.9856 | 2.1298 |  | 691.5 | 0.00023663 | 9346 | 0.077178 | 3616 | 1.8231e-05 | 10084
SANTA YNEZ 1101CB | SANTA YNEZ 1101 | 182721101 |  | 17.7655 | 3.3322 |  | 327.8333 | 0.00027242 | 8598 | 0.066925 | 6084 | 1.823e-05 | 10085
WESTLEY 110111734 | WESTLEY 1101 | 162671101 |  | 17.1392 | 0.97526 |  | 306.5 | 0.00026074 | 8871 | 0.070308 | 4978 | 1.8228e-05 | 10086
ATWATER 110255392 | ATWATER 1102 | 253611102 |  | 0.012638 | 0 |  | 0.5 | 0.00023512 | 9386 | 0.0774 | 3397 | 1.8198e-05 | 10087
WOODLAND 11068712 | WOODLAND 1106 | 62031106 |  | 18.333 | 0.65329 |  | 348.5 | 0.00023802 | 9319 | 0.076722 | 3921 | 1.8198e-05 | 10088
LIVINGSTON 1105187702 | LIVINGSTON 1105 | 252261105 |  | 12.6416 | 0.6176 |  | 231 | 0.00023608 | 9358 | 0.077126 | 3670 | 1.8192e-05 | 10089
EEL RIVER 1102680 | EEL RIVER 1102 | 192381102 |  | 16.5289 | 1.2768 |  | 310.5 | 0.00027129 | 8625 | 0.067131 | 5873 | 1.8189e-05 | 10090
CHARCA 1102826046 | CHARCA 1102 | 254501102 |  | 3.8755 | 0.50763 |  | 69 | 0.00024028 | 9282 | 0.076011 | 4196 | 1.8185e-05 | 10091
CASSIDY 2107CB | CASSIDY 2107 | 254272107 |  | 24.9334 | 1.7625 |  | 409.5 | 0.00024464 | 9192 | 0.07568 | 4291 | 1.8185e-05 | 10092
LOS OSITOS 210366936 | LOS OSITOS 2103 | 182082103 |  | 10.3832 | 0.47752 |  | 207.5 | 0.00027021 | 8649 | 0.067252 | 5762 | 1.8172e-05 | 10093
CAPAY 11022086 | CAPAY 1102 | 102111102 |  | 14.1059 | 0.91726 |  | 242.5 | 0.00026503 | 8755 | 0.069063 | 5183 | 1.8169e-05 | 10094
FIGARDEN 21126200 | FIGARDEN 2112 | 254552112 |  | 18.7445 | 0.53185 |  | 326.5 | 0.0002354 | 9382 | 0.077278 | 3507 | 1.8165e-05 | 10095
GRAND ISLAND 22279452 | GRAND ISLAND 2227 | 62462227 |  | 21.7258 | 0.65768 |  | 358.1667 | 0.0002361 | 9357 | 0.077016 | 3752 | 1.8163e-05 | 10096
SANGER 110896048 | SANGER 1108 | 252351108 |  | 23.0623 | 3.3573 |  | 430.5 | 0.00023558 | 9375 | 0.077194 | 3598 | 1.8163e-05 | 10097
CAMDEN 1104548526 | CAMDEN 1104 | 252301104 |  | 3.7576 | 0.30476 |  | 62 | 0.00023438 | 9401 | 0.0774 | 3397 | 1.8141e-05 | 10098
STROUD 11019520 | STROUD 1101 | 253661101 |  | 22.722 | 0.40034 |  | 382 | 0.00023657 | 9349 | 0.076748 | 3912 | 1.814e-05 | 10099
HARDWICK 11026100 | HARDWICK 1102 | 253711102 |  | 4.8387 | 0.34141 |  | 82 | 0.0002343 | 9404 | 0.0774 | 3397 | 1.8135e-05 | 10100
PUTAH CREEK 11058812 | PUTAH CREEK 1105 | 63681105 |  | 62.8242 | 2.2866 |  | 1054.5 | 0.00025482 | 8985 | 0.071554 | 4822 | 1.8131e-05 | 10101
OROSI 1101939642 | OROSI 1101 | 252841101 |  | 3.5023 | 0.52338 |  | 58 | 0.00026101 | 8864 | 0.071175 | 4875 | 1.8117e-05 | 10102
OLIVEHURST 11051242 | OLIVEHURST 1105 | 152901105 |  | 6.4335 | 0.25621 |  | 110 | 0.00023403 | 9407 | 0.0774 | 3397 | 1.8114e-05 | 10103
CAMDEN 1104744839 | CAMDEN 1104 | 252301104 |  | 8.4885 | 0.64997 |  | 152.5 | 0.00023394 | 9412 | 0.0774 | 3397 | 1.8107e-05 | 10104
RIO BRAVO 1106CB | RIO BRAVO 1106 | 252861106 |  | 13.356 | 0.34414 |  | 224 | 0.0002366 | 9348 | 0.077221 | 3568 | 1.8103e-05 | 10105
KINGSBURG 1113312897 | KINGSBURG 1113 | 252241113 |  | 1.2596 | 0.04871 |  | 23.5 | 0.00025577 | 8967 | 0.072741 | 4688 | 1.809e-05 | 10106
LIVINGSTON 110553156 | LIVINGSTON 1105 | 252261105 |  | 11.8808 | 0.43333 |  | 200.5 | 0.000234 | 9408 | 0.077321 | 3440 | 1.809e-05 | 10107
OROSI 1103CB | OROSI 1103 | 252841103 |  | 31.0644 | 7.4894 |  | 587.8333 | 0.00026298 | 8806 | 0.069183 | 5165 | 1.8088e-05 | 10108
MADISON 11057712 | MADISON 1105 | 63171105 |  | 21.8326 | 1.1689 |  | 365 | 0.00026097 | 8866 | 0.069772 | 5079 | 1.8087e-05 | 10109
CANTUA 11019880 | CANTUA 1101 | 253591101 |  | 13.4725 | 0.23914 |  | 213 | 0.00023533 | 9384 | 0.076856 | 3854 | 1.8075e-05 | 10110
KINGSBURG 11116380 | KINGSBURG 1111 | 252241111 |  | 27.2411 | 4.0556 |  | 496 | 0.00023448 | 9398 | 0.077191 | 3600 | 1.8067e-05 | 10111
CAPAY 110289646 | CAPAY 1102 | 102111102 |  | 7.7865 | 0.44276 |  | 130.5 | 0.00026754 | 8709 | 0.067838 | 5462 | 1.8064e-05 | 10112
KERMAN 110649702 | KERMAN 1106 | 252711106 |  | 31.1987 | 0.81585 |  | 522 | 0.00023484 | 9392 | 0.07695 | 3797 | 1.8064e-05 | 10113
RANDOLPH 0401CB | RANDOLPH 0401 | 22590401 |  | 0.0045454 | 0 |  | 1 | 0.00034034 | 7301 | 0.053073 | 8251 | 1.8063e-05 | 10114
OROSI 1102CB | OROSI 1102 | 252841102 |  | 24.6138 | 3.4552 |  | 454.3333 | 0.0002611 | 8862 | 0.069266 | 5152 | 1.8051e-05 | 10115
LOCKEFORD 210257876 | LOCKEFORD 2102 | 163682102 |  | 9.7354 | 0.47661 |  | 167 | 0.00023321 | 9423 | 0.0774 | 3397 | 1.805e-05 | 10116
MC CALL 1107622818 | MC CALL 1107 | 254121107 |  | 11.5385 | 0.81085 |  | 205 | 0.00023397 | 9409 | 0.077164 | 3633 | 1.8044e-05 | 10117
CASTROVILLE 21033693 | CASTROVILLE 2103 | 182352103 |  | 0.88172 | 0.019411 |  | 18.5 | 0.00026929 | 8670 | 0.067 | 6057 | 1.8042e-05 | 10118
SANTA RITA 11029930 | SANTA RITA 1102 | 253541102 |  | 7.6388 | 0.24235 |  | 133 | 0.00023365 | 9415 | 0.077217 | 3578 | 1.8037e-05 | 10119
GATES 110699914 | GATES 1106 | 253931106 |  | 17.8372 | 0.31285 |  | 316 | 0.00025577 | 8968 | 0.071177 | 4874 | 1.8035e-05 | 10120
GATES 1102754356 | GATES 1102 | 253931102 |  | 22.8465 | 0.48349 |  | 387.5 | 0.00023434 | 9402 | 0.076943 | 3800 | 1.8034e-05 | 10121
SF H 1104CB | SF H 1104 | 22101104 |  | 0.64741 | 1.6485 |  | 37.25 | 0.00033967 | 7311 | 0.053073 | 8251 | 1.8027e-05 | 10122
JACOBS CORNER 11018230 | JACOBS CORNER 1101 | 254771101 |  | 35.1104 | 6.6292 |  | 653.5 | 0.00023463 | 9395 | 0.076979 | 3777 | 1.8018e-05 | 10123
CAMDEN 11036570 | CAMDEN 1103 | 252301103 |  | 54.4662 | 12.8408 |  | 1037 | 0.00023395 | 9411 | 0.077139 | 3657 | 1.8015e-05 | 10124
GIFFEN 1102CB | GIFFEN 1102 | 253151102 |  | 20.7707 | 0.49897 |  | 340.3333 | 0.00023792 | 9323 | 0.076164 | 4137 | 1.8015e-05 | 10125
HARDWICK 11016840 | HARDWICK 1101 | 253711101 |  | 21.7349 | 4.8781 |  | 413.5 | 0.00023889 | 9303 | 0.076159 | 4139 | 1.8013e-05 | 10126
GUSTINE 110179806 | GUSTINE 1101 | 163111101 |  | 27.9484 | 2.1854 |  | 538.5 | 0.00023452 | 9397 | 0.076956 | 3790 | 1.801e-05 | 10127
WILKINS SLOUGH 11026272 | WILKINS SLOUGH 1102 | 62771102 |  | 10.4498 | 0.2306 |  | 195 | 0.00023358 | 9417 | 0.07715 | 3648 | 1.8007e-05 | 10128
KERMAN 1106CB | KERMAN 1106 | 252711106 |  | 14.8189 | 0.77559 |  | 253.7 | 0.00024134 | 9261 | 0.075995 | 4200 | 1.7998e-05 | 10129
MERCED 111490220 | MERCED 1114 | 252801114 |  | 8.4466 | 0.43387 |  | 149.5 | 0.00023249 | 9434 | 0.0774 | 3397 | 1.7994e-05 | 10130
GLENN 11012550 | GLENN 1101 | 102601101 |  | 14.7064 | 1.4002 |  | 265 | 0.00026642 | 8734 | 0.067496 | 5603 | 1.7986e-05 | 10131
KINGSBURG 11116960 | KINGSBURG 1111 | 252241111 |  | 5.21 | 0.66657 |  | 91 | 0.00023309 | 9425 | 0.077266 | 3523 | 1.7986e-05 | 10132
REEDLEY 11127013 | REEDLEY 1112 | 252341112 |  | 5.4193 | 0.77342 |  | 96.5 | 0.00026274 | 8814 | 0.069155 | 5167 | 1.7984e-05 | 10133
EL NIDO 11034490 | EL NIDO 1103 | 252451103 |  | 11.4389 | 0.38324 |  | 185.5 | 0.00023232 | 9439 | 0.0774 | 3397 | 1.7982e-05 | 10134
LOGAN CREEK 21012430 | LOGAN CREEK 2101 | 103142101 |  | 10.2832 | 0.33033 |  | 172.5 | 0.00025155 | 9050 | 0.071803 | 4793 | 1.7974e-05 | 10135
BRENTWOOD 210577560 | BRENTWOOD 2105 | 14592105 |  | 0.047137 | 0 |  | 0.5 | 0.00026822 | 8693 | 0.067 | 6057 | 1.7971e-05 | 10136
ANITA 110648098 | ANITA 1106 | 102841106 |  | 10.768 | 0.55812 |  | 184 | 0.00025807 | 8923 | 0.071355 | 4848 | 1.7965e-05 | 10137
COPPERMINE 110496648 | COPPERMINE 1104 | 252411104 |  | 4.6325 | 0.34052 |  | 90.8333 | 0.00025445 | 8992 | 0.070396 | 4960 | 1.7963e-05 | 10138
HARDWICK 11026360 | HARDWICK 1102 | 253711102 |  | 14.51 | 1.2538 |  | 256.5 | 0.00023207 | 9442 | 0.0774 | 3397 | 1.7962e-05 | 10139
CLEAR LAKE 1101444 | CLEAR LAKE 1101 | 42141101 |  | 16.2277 | 2.4511 |  | 288.5 | 0.0002672 | 8717 | 0.06719 | 5820 | 1.7956e-05 | 10140
RICE 11023104 | RICE 1102 | 62831102 |  | 17.6343 | 0.44213 |  | 297.5 | 0.0002336 | 9416 | 0.076938 | 3802 | 1.7954e-05 | 10141
BORDEN 110381648 | BORDEN 1103 | 255121103 |  | 23.4983 | 0.99958 |  | 406.5 | 0.00023328 | 9422 | 0.077066 | 3720 | 1.7953e-05 | 10142
TEJON 11062436 | TEJON 1106 | 252931106 |  | 22.0082 | 0.32095 |  | 371.5 | 0.00025291 | 9022 | 0.071493 | 4831 | 1.7946e-05 | 10143
TERMINOUS 110285346 | TERMINOUS 1102 | 163021102 |  | 10.7626 | 0.12479 |  | 186.5 | 0.00023182 | 9446 | 0.0774 | 3397 | 1.7943e-05 | 10144
LINCOLN 110451756 | LINCOLN 1104 | 153701104 | TRUE | 19.0936 | 0.57581 | 0.27114 | 333.5 | 0.00014685 | 10731 | 0.093011 | 3334 | 1.7942e-05 | 10145
DIVIDE 1101M78 | DIVIDE 1101 | 182571101 |  | 12.9273 | 6.0618 |  | 215.5 | 0.00026678 | 8723 | 0.067302 | 5728 | 1.7929e-05 | 10146
CORCORAN 1104996334 | CORCORAN 1104 | 252171104 |  | 1.2845 | 0.11846 |  | 23 | 0.00023163 | 9449 | 0.0774 | 3397 | 1.7928e-05 | 10147
OCEANO 1106V26 | OCEANO 1106 | 182601106 |  | 8.2189 | 7.9441 |  | 139.3333 | 0.000314 | 7737 | 0.056288 | 7533 | 1.7924e-05 | 10148
COTTLE 17026318 | COTTLE 1702 | 163711702 |  | 15.1732 | 0.73569 |  | 266.3333 | 0.00023878 | 9308 | 0.075238 | 4380 | 1.7913e-05 | 10149
GATES 1106879496 | GATES 1106 | 253931106 |  | 4.7032 | 0.13999 |  | 79 | 0.00026244 | 8819 | 0.068317 | 5327 | 1.7912e-05 | 10150
COTATI 11058459 | COTATI 1105 | 42271105 |  | 3.7956 | 0.66271 |  | 74.5 | 0.000219 | 9720 | 0.074297 | 4515 | 1.7908e-05 | 10151
EAST MARYSVILLE 11051704 | EAST MARYSVILLE 1105 | 152331105 |  | 11.7129 | 1.0325 |  | 214 | 0.00023928 | 9297 | 0.07632 | 4082 | 1.7902e-05 | 10152
VALLEY HOME 1702CB | VALLEY HOME 1702 | 162981702 |  | 23.7726 | 1.4708 |  | 450.3333 | 0.00023494 | 9389 | 0.076736 | 3917 | 1.7897e-05 | 10153
ORO LOMA 11163370 | ORO LOMA 1116 | 255371116 |  | 6.5834 | 0.12605 |  | 111 | 0.00023114 | 9460 | 0.0774 | 3397 | 1.7891e-05 | 10154
WHEATLAND 1104CB | WHEATLAND 1104 | 152811104 |  | 16.7304 | 0.93473 |  | 294.8333 | 0.00025445 | 8991 | 0.071291 | 4859 | 1.7888e-05 | 10155
CORRAL 110112304 | CORRAL 1101 | 162991101 |  | 7.3383 | 0.59782 |  | 135 | 0.00025877 | 8910 | 0.069465 | 5122 | 1.7877e-05 | 10156
SCHINDLER 11119420 | SCHINDLER 1111 | 252891111 |  | 24.5952 | 0.56377 |  | 413.5 | 0.00023106 | 9463 | 0.077282 | 3499 | 1.7871e-05 | 10157
JACINTO 110285076 | JACINTO 1102 | 102851102 |  | 30.3722 | 1.5396 |  | 523 | 0.00024271 | 9228 | 0.074142 | 4538 | 1.787e-05 | 10158
TULARE LAKE 11089910 | TULARE LAKE 1108 | 252951108 |  | 16.324 | 0.022849 |  | 279 | 0.00025542 | 8975 | 0.070946 | 4900 | 1.7868e-05 | 10159
HAMMONDS 110212140 | HAMMONDS 1102 | 253401102 |  | 8.8061 | 0.63071 |  | 142.5 | 0.0002402 | 9285 | 0.074892 | 4428 | 1.7867e-05 | 10160
HOLLISTER 21014792 | HOLLISTER 2101 | 182492101 |  | 9.8034 | 1.9971 |  | 188.5 | 0.00026937 | 8668 | 0.067127 | 5878 | 1.7867e-05 | 10161
GOOSE LAKE 11033244 | GOOSE LAKE 1103 | 254201103 |  | 17.1846 | 0.11483 |  | 304.25 | 0.0002523 | 9036 | 0.071585 | 4815 | 1.7859e-05 | 10162
CANTUA 1103CB | CANTUA 1103 | 253591103 |  | 16.4579 | 0.57512 |  | 277 | 0.00025091 | 9059 | 0.071306 | 4855 | 1.7846e-05 | 10163
GABILAN 11013722 | GABILAN 1101 | 182331101 |  | 14.4275 | 0.85813 |  | 280.5 | 0.00026353 | 8792 | 0.067482 | 5614 | 1.7836e-05 | 10164
CLOVIS 110285140 | CLOVIS 1102 | 254081102 |  | 13.3725 | 0.55872 |  | 220.5 | 0.00023042 | 9476 | 0.0774 | 3397 | 1.7834e-05 | 10165
DIXON 11039732 | DIXON 1103 | 62061103 |  | 25.6092 | 0.98174 |  | 424 | 0.00023063 | 9473 | 0.077342 | 3419 | 1.7834e-05 | 10166
TWISSELMAN 2105CB | TWISSELMAN 2105 | 254402105 |  | 25.94 | 0.38751 |  | 465.75 | 0.00024659 | 9154 | 0.073297 | 4634 | 1.7831e-05 | 10167
TIVY VALLEY 1106R1450 | TIVY VALLEY 1106 | 252941106 |  | 0.03571 | 0 |  | 0.5 | 0.00026614 | 8741 | 0.067 | 6057 | 1.7831e-05 | 10168
CAL WATER 11023802 | CAL WATER 1102 | 255451102 |  | 0.023802 | 0.028535 |  | 1.5 | 0.00025428 | 8995 | 0.074061 | 4547 | 1.7831e-05 | 10169
RIO BRAVO 11022676 | RIO BRAVO 1102 | 252861102 |  | 11.0334 | 1.0062 |  | 191 | 0.0002319 | 9444 | 0.077065 | 3721 | 1.7825e-05 | 10170
PALMER 1101CUSTREC | PALMER 1101 | 183031101 |  | 0.3208 | 0 |  | 4.5 | 0.00026574 | 8747 | 0.06707 | 5926 | 1.7821e-05 | 10171
HONCUT 110275350 | HONCUT 1102 | 103211102 |  | 19.876 | 0.74506 |  | 373.5 | 0.00025011 | 9078 | 0.071268 | 4861 | 1.782e-05 | 10172
PENRYN 110550548 | PENRYN 1105 | 152561105 | TRUE | 4.8553 | 0.51958 | 0.00094326 | 84 | 0.0002657 | 8748 | 0.067042 | 5957 | 1.7818e-05 | 10173
BRENTWOOD 2105502672 | BRENTWOOD 2105 | 14592105 |  | 13.4969 | 0.55946 |  | 245 | 0.00026099 | 8865 | 0.06872 | 5237 | 1.7815e-05 | 10174
CASSIDY 2108186620 | CASSIDY 2108 | 254272108 |  | 6.3815 | 0.067196 |  | 111.5 | 0.00025964 | 8888 | 0.068679 | 5245 | 1.7813e-05 | 10175
WATERLOO 110112970 | WATERLOO 1101 | 163151101 |  | 21.5877 | 1.9042 |  | 372 | 0.00023671 | 9345 | 0.076015 | 4195 | 1.7798e-05 | 10176
LEMOORE 110369392 | LEMOORE 1103 | 253601103 |  | 6.1592 | 1.579 |  | 113.5 | 0.00023234 | 9438 | 0.076833 | 3869 | 1.7795e-05 | 10177
MADISON 11057552 | MADISON 1105 | 63171105 |  | 23.4736 | 0.5098 |  | 414 | 0.00025006 | 9081 | 0.071544 | 4824 | 1.7795e-05 | 10178
CAPAY 1101CB | CAPAY 1101 | 102111101 |  | 9.382 | 1.0166 |  | 165.5 | 0.00026249 | 8817 | 0.068216 | 5357 | 1.779e-05 | 10179
CORNING 110283910 | CORNING 1102 | 103331102 |  | 25.7201 | 2.086 |  | 461.5 | 0.00026341 | 8797 | 0.067587 | 5559 | 1.7788e-05 | 10180
CAL WATER 1102329532 | CAL WATER 1102 | 255451102 |  | 2.5928 | 0 |  | 51 | 0.00027363 | 8562 | 0.066408 | 6205 | 1.7781e-05 | 10181
BURNEY 1102CB | BURNEY 1102 | 103311102 |  | 1.5757 | 0.42645 |  | 25.1667 | 0.00026762 | 8707 | 0.066513 | 6184 | 1.778e-05 | 10182
SISQUOC 1102M26 | SISQUOC 1102 | 182811102 |  | 19.7244 | 1.0104 |  | 347.5 | 0.00026213 | 8830 | 0.067988 | 5407 | 1.7779e-05 | 10183
ORLAND B 11032092 | ORLAND B 1103 | 102701103 |  | 20.9114 | 1.2316 |  | 361.5 | 0.00025769 | 8930 | 0.069478 | 5121 | 1.7778e-05 | 10184
GABILAN 11013090 | GABILAN 1101 | 182331101 |  | 16.4701 | 1.4549 |  | 347 | 0.00026374 | 8787 | 0.06737 | 5688 | 1.7777e-05 | 10185
SANTA RITA 11053520 | SANTA RITA 1105 | 253541105 |  | 26.3675 | 0.72859 |  | 479.5 | 0.00022981 | 9493 | 0.077349 | 3414 | 1.7774e-05 | 10186
ESQUON 1101CB | ESQUON 1101 | 102171101 |  | 6.0788 | 0.11236 |  | 118.3333 | 0.00023648 | 9352 | 0.07592 | 4221 | 1.7773e-05 | 10187
PASO ROBLES 1108P28 | PASO ROBLES 1108 | 182611108 |  | 5.0367 | 0.50024 |  | 93 | 0.00026277 | 8813 | 0.067614 | 5539 | 1.7764e-05 | 10188
LOS OSITOS 21037082 | LOS OSITOS 2103 | 182082103 |  | 17.2896 | 1.188 |  | 366.5 | 0.00026145 | 8855 | 0.068053 | 5394 | 1.7761e-05 | 10189
WESTLEY 11037150 | WESTLEY 1103 | 162671103 |  | 11.8823 | 0.35111 |  | 246.5 | 0.00025259 | 9029 | 0.071076 | 4887 | 1.7757e-05 | 10190
CORNING 1102861542 | CORNING 1102 | 103331102 |  | 0.61416 | 0 |  | 8.5 | 0.00026465 | 8759 | 0.067047 | 5949 | 1.7747e-05 | 10191
REEDLEY 11067913F | REEDLEY 1106 | 252341106 |  | 8.7222 | 2.6437 |  | 180 | 0.00024586 | 9170 | 0.072257 | 4749 | 1.7744e-05 | 10192
DAIRYLAND 110595970 | DAIRYLAND 1105 | 252421105 |  | 6.8524 | 0.22347 |  | 114 | 0.00022955 | 9499 | 0.077262 | 3527 | 1.7743e-05 | 10193
BLACKWELL 11023241 | BLACKWELL 1102 | 254681102 |  | 11.6674 | 0.12394 |  | 203.5 | 0.00025293 | 9021 | 0.070998 | 4894 | 1.774e-05 | 10194
DUNNIGAN 110136956 | DUNNIGAN 1101 | 63811101 |  | 5.2297 | 0.26022 |  | 89 | 0.00022917 | 9510 | 0.0774 | 3397 | 1.7738e-05 | 10195
LAMONT 110217566 | LAMONT 1102 | 253911102 |  | 1.3694 | 0.011702 |  | 22.5 | 0.00026054 | 8874 | 0.068078 | 5391 | 1.7731e-05 | 10196
PUTAH CREEK 110258340 | PUTAH CREEK 1102 | 63681102 |  | 0.034523 | 0 |  | 0.5 | 0.00026423 | 8772 | 0.067105 | 5893 | 1.7731e-05 | 10197
HORSESHOE 11012714 | HORSESHOE 1101 | 152571101 |  | 4.0014 | 0.48676 |  | 70.5 | 0.0002632 | 8800 | 0.067149 | 5855 | 1.7725e-05 | 10198
LIVE OAK 110464196 | LIVE OAK 1104 | 153771104 |  | 2.4199 | 0.54635 |  | 45 | 0.00023112 | 9461 | 0.07713 | 3664 | 1.7722e-05 | 10199
FIGARDEN 2113R1967 | FIGARDEN 2113 | 254552113 |  | 4.1027 | 0.25217 |  | 69.5 | 0.00023027 | 9481 | 0.07705 | 3733 | 1.7708e-05 | 10200
MIDWAY 11011470 | MIDWAY 1101 | 252611101 |  | 13.4957 | 0.28823 |  | 233.5 | 0.00022873 | 9517 | 0.0774 | 3397 | 1.7704e-05 | 10201
LINCOLN 110289506 | LINCOLN 1102 | 153701102 |  | 1.9856 | 0.07121 |  | 37 | 0.00026418 | 8774 | 0.067 | 6057 | 1.77e-05 | 10202
CASSIDY 21089510 | CASSIDY 2108 | 254272108 |  | 23.2843 | 0.8145 |  | 390.8333 | 0.00024348 | 9216 | 0.074591 | 4474 | 1.7689e-05 | 10203
CHOWCHILLA 110311490 | CHOWCHILLA 1103 | 254101103 |  | 11.1632 | 0.11401 |  | 183.3333 | 0.00023589 | 9366 | 0.076233 | 4117 | 1.7689e-05 | 10204
ATWATER 11029650 | ATWATER 1102 | 253611102 |  | 13.5146 | 0.42813 |  | 222.5 | 0.00023128 | 9455 | 0.076898 | 3833 | 1.7689e-05 | 10205
HONCUT 110137324 | HONCUT 1101 | 103211101 |  | 11.8955 | 0.70866 |  | 218 | 0.00022851 | 9527 | 0.0774 | 3397 | 1.7686e-05 | 10206
NEW HOPE 11019796 | NEW HOPE 1101 | 162081101 |  | 16.6457 | 0.43875 |  | 312.5 | 0.00022888 | 9515 | 0.077297 | 3476 | 1.7671e-05 | 10207
TEMBLOR 11049126 | TEMBLOR 1104 | 252551104 |  | 12.0594 | 0.0773 |  | 208.5 | 0.00026353 | 8794 | 0.067014 | 6013 | 1.766e-05 | 10208
ELK HILLS 1106CB | ELK HILLS 1106 | 252441106 |  | 7.5053 | 0.14674 |  | 134.3333 | 0.00026223 | 8827 | 0.067395 | 5673 | 1.7652e-05 | 10209
RAINBOW 1106D4879 | RAINBOW 1106 | 254441106 |  | 6.9419 | 0.89222 |  | 119.5 | 0.00022793 | 9535 | 0.0774 | 3397 | 1.7642e-05 | 10210
WILLIAMS 110230332 | WILLIAMS 1102 | 62051102 |  | 9.7116 | 0.23931 |  | 162 | 0.00023055 | 9474 | 0.076702 | 3935 | 1.7641e-05 | 10211
STROUD 1104342914 | STROUD 1104 | 253661104 |  | 11.0105 | 0.75316 |  | 184.5 | 0.00023648 | 9351 | 0.075864 | 4241 | 1.7639e-05 | 10212
PANORAMA 11021526 | PANORAMA 1102 | 103461102 |  | 2.287 | 0.12177 |  | 47 | 0.0002617 | 8845 | 0.067443 | 5643 | 1.7639e-05 | 10213
MIDDLE RIVER 1103CB | MIDDLE RIVER 1103 | 162091103 |  | 21.7538 | 0.24976 |  | 392.5 | 0.00023129 | 9454 | 0.076431 | 4043 | 1.7637e-05 | 10214
RIVERBANK 171338800 | RIVERBANK 1713 | 163191713 |  | 2.1869 | 0.50803 |  | 41 | 0.00023235 | 9437 | 0.07651 | 4012 | 1.7636e-05 | 10215
RICE 110146616 | RICE 1101 | 62831101 |  | 8.7784 | 0.14875 |  | 151.5 | 0.00022782 | 9540 | 0.0774 | 3397 | 1.7633e-05 | 10216
ORICK 1102CB | ORICK 1102 | 192261102 |  | 6.8531 | 1.603 |  | 129 | 0.00027075 | 8634 | 0.065826 | 6299 | 1.7632e-05 | 10217
MC CALL 11076150 | MC CALL 1107 | 254121107 |  | 9.9768 | 1.7641 |  | 194.5 | 0.00022833 | 9531 | 0.077256 | 3533 | 1.7624e-05 | 10218
LOCKEFORD 2102D6873 | LOCKEFORD 2102 | 163682102 |  | 3.8367 | 0.47475 |  | 63.5 | 0.0002277 | 9544 | 0.0774 | 3397 | 1.7624e-05 | 10219
MARICOPA 1101931236 | MARICOPA 1101 | 254211101 |  | 27.5828 | 0.22627 |  | 467 | 0.00026119 | 8858 | 0.067504 | 5598 | 1.7622e-05 | 10220
TUPMAN 11031190 | TUPMAN 1103 | 254561103 |  | 7.7331 | 0.2978 |  | 129 | 0.00022817 | 9532 | 0.077278 | 3506 | 1.7611e-05 | 10221
CORNING 11031368 | CORNING 1103 | 103331103 |  | 20.1912 | 0.82753 |  | 345 | 0.00026105 | 8863 | 0.067478 | 5616 | 1.7609e-05 | 10222
KETTLEMAN HILLS 1101CB | KETTLEMAN HILLS 1101 | 252731101 |  | 13.4695 | 0.17391 |  | 228.5 | 0.00025941 | 8896 | 0.068093 | 5387 | 1.7608e-05 | 10223
HONCUT 11015013 | HONCUT 1101 | 103211101 |  | 1.4425 | 0.010496 |  | 24.5 | 0.00022749 | 9550 | 0.0774 | 3397 | 1.7607e-05 | 10224
PLAINFIELD 1101603390 | PLAINFIELD 1101 | 63441101 |  | 4.3034 | 0.39619 |  | 73 | 0.00022742 | 9552 | 0.0774 | 3397 | 1.7602e-05 | 10225
VACA DIXON 110339500 | VACA DIXON 1103 | 63591103 |  | 15.9471 | 0.57999 |  | 261 | 0.00023107 | 9462 | 0.076356 | 4066 | 1.7597e-05 | 10226
HENRIETTA 11108210 | HENRIETTA 1110 | 252681110 |  | 23.0568 | 1.6921 |  | 399 | 0.00022735 | 9553 | 0.0774 | 3397 | 1.7597e-05 | 10227
SMYRNA 11061200 | SMYRNA 1106 | 253551106 |  | 29.6756 | 1.3041 |  | 504.5 | 0.00023078 | 9467 | 0.076662 | 3952 | 1.7591e-05 | 10228
TERMINOUS 110311906 | TERMINOUS 1103 | 163021103 |  | 11.2531 | 0.15908 |  | 207 | 0.00022758 | 9548 | 0.077282 | 3500 | 1.759e-05 | 10229
COPPERMINE 1106CB | COPPERMINE 1106 | 252411106 |  | 7.9448 | 1.0495 |  | 144.0833 | 0.00025943 | 8894 | 0.067289 | 5739 | 1.759e-05 | 10230
KINGSBURG 1116605430 | KINGSBURG 1116 | 252241116 |  | 17.5293 | 1.055 |  | 303.5 | 0.00022758 | 9547 | 0.077296 | 3479 | 1.7587e-05 | 10231
WYANDOTTE 11095575 | WYANDOTTE 1109 | 102911109 |  | 6.65 | 0.6869 |  | 124 | 0.00026088 | 8869 | 0.067593 | 5555 | 1.7581e-05 | 10232
GONZALES 110422420 | GONZALES 1104 | 182131104 |  | 7.3445 | 0.35473 |  | 155.5 | 0.00026052 | 8875 | 0.067468 | 5622 | 1.7581e-05 | 10233
SANGER 1114R2960 | SANGER 1114 | 252351114 |  | 12.0074 | 1.073 |  | 220.5 | 0.00022761 | 9546 | 0.077329 | 3433 | 1.758e-05 | 10234
ELK HILLS 110489376 | ELK HILLS 1104 | 252441104 |  | 0.010462 | 0 |  | 1.5 | 0.00022697 | 9564 | 0.0774 | 3397 | 1.7567e-05 | 10235
RICE 110430010 | RICE 1104 | 62831104 |  | 16.9596 | 0.60022 |  | 295 | 0.00022712 | 9561 | 0.077317 | 3450 | 1.7557e-05 | 10236
KING CITY 1106202402 | KING CITY 1106 | 182031106 |  | 1.3988 | 0.025254 |  | 23 | 0.00026204 | 8837 | 0.067 | 6057 | 1.7557e-05 | 10237
SISQUOC 1104301229 | SISQUOC 1104 | 182811104 |  | 0.16832 | 0 |  | 3.5 | 0.00026189 | 8838 | 0.067 | 6057 | 1.7546e-05 | 10238
SEMITROPIC 1108CB | SEMITROPIC 1108 | 252901108 |  | 11.7238 | 0.26393 |  | 200.5 | 0.00022688 | 9569 | 0.077321 | 3440 | 1.754e-05 | 10239
TEMPLETON 2112R28 | TEMPLETON 2112 | 183052112 |  | 1.5914 | 0.020775 |  | 26 | 0.00026171 | 8843 | 0.067 | 6057 | 1.7535e-05 | 10240
CASTROVILLE 210375558 | CASTROVILLE 2103 | 182352103 |  | 12.896 | 0.79116 |  | 244.5 | 0.00026115 | 8859 | 0.067127 | 5877 | 1.7533e-05 | 10241
CHARCA 1102CB | CHARCA 1102 | 254501102 |  | 30.1928 | 0.93605 |  | 504.5 | 0.0002323 | 9440 | 0.076327 | 4078 | 1.7531e-05 | 10242
HENRIETTA 1104CB | HENRIETTA 1104 | 252681104 |  | 11.2773 | 0.068018 |  | 153.3333 | 0.00023009 | 9486 | 0.076641 | 3962 | 1.753e-05 | 10243
PANOCHE 11023490 | PANOCHE 1102 | 253671102 |  | 18.2599 | 0.41737 |  | 298 | 0.00022633 | 9574 | 0.0774 | 3397 | 1.7518e-05 | 10244
DEEPWATER 110720212 | DEEPWATER 1107 | 63621107 |  | 4.78 | 0.34334 |  | 91 | 0.00024031 | 9281 | 0.074413 | 4498 | 1.7517e-05 | 10245
ALPAUGH 110398006 | ALPAUGH 1103 | 254001103 |  | 8.5817 | 0.044171 |  | 144.5 | 0.00022631 | 9575 | 0.0774 | 3397 | 1.7516e-05 | 10246
EEL RIVER 1102530 | EEL RIVER 1102 | 192381102 | TRUE | 26.9008 | 3.4648 | 0.038867 | 482.8333 | 0.00020347 | 9988 | 0.076076 | 4170 | 1.7512e-05 | 10247
PEABODY 210765584 | PEABODY 2107 | 63642107 |  | 0.035416 | 0 |  | 0.5 | 0.00025994 | 8883 | 0.067315 | 5722 | 1.7498e-05 | 10248
CARUTHERS 1102389798 | CARUTHERS 1102 | 252371102 |  | 11.1087 | 0.169 |  | 191.5 | 0.00022604 | 9581 | 0.0774 | 3397 | 1.7495e-05 | 10249
GUERNSEY 110192702 | GUERNSEY 1101 | 252661101 |  | 7.6796 | 0.041281 |  | 127.5 | 0.00023606 | 9359 | 0.074761 | 4449 | 1.7495e-05 | 10250
SAN ARDO 1102CB | SAN ARDO 1102 | 182191102 |  | 1.2076 | 0.035152 |  | 21 | 0.00025676 | 8948 | 0.068981 | 5195 | 1.7479e-05 | 10251
GANSO 11043655 | GANSO 1104 | 254541104 |  | 10.9596 | 0.21241 |  | 188 | 0.00023003 | 9488 | 0.076281 | 4100 | 1.7478e-05 | 10252
MENDOTA 11043630 | MENDOTA 1104 | 252311104 |  | 19.4748 | 0.57316 |  | 328 | 0.00022989 | 9491 | 0.076633 | 3967 | 1.7476e-05 | 10253
COPUS 11043551 | COPUS 1104 | 253871104 |  | 28.7127 | 0.10107 |  | 476 | 0.00025388 | 8999 | 0.068656 | 5249 | 1.7475e-05 | 10254
RIO BRAVO 11062635 | RIO BRAVO 1106 | 252861106 |  | 40.9893 | 2.1224 |  | 697.5 | 0.00022606 | 9580 | 0.077273 | 3514 | 1.7473e-05 | 10255
SHAFTER 1112795622 | SHAFTER 1112 | 253651112 |  | 13.6984 | 0.28794 |  | 232.5 | 0.00022707 | 9562 | 0.077063 | 3723 | 1.7472e-05 | 10256
TULARE LAKE 1106CB | TULARE LAKE 1106 | 252951106 |  | 5.454 | 0.054664 |  | 95.3333 | 0.00023909 | 9300 | 0.073819 | 4569 | 1.7471e-05 | 10257
RED BLUFF 11011334 | RED BLUFF 1101 | 103541101 | FALSE | 15.9009 | 0.74102 | 1.3466 | 293 | 0.00016295 | 10560 | 0.14197 | 3228 | 1.7465e-05 | 10258
GATES 1105661396 | GATES 1105 | 253931105 |  | 11.8278 | 0.13014 |  | 202.5 | 0.00023601 | 9361 | 0.074201 | 4526 | 1.7456e-05 | 10259
PANOCHE 11023450 | PANOCHE 1102 | 253671102 |  | 2.0141 | 0.011415 |  | 36 | 0.00023534 | 9383 | 0.073584 | 4597 | 1.7454e-05 | 10260
WAHTOKE 1111267760 | WAHTOKE 1111 | 254531111 |  | 0.027723 | 0 |  | 0.33333 | 0.00022542 | 9601 | 0.0774 | 3396 | 1.7447e-05 | 10261
DUNNIGAN 110192472 | DUNNIGAN 1101 | 63811101 |  | 8.5912 | 0.59408 |  | 151 | 0.00025233 | 9035 | 0.069644 | 5093 | 1.7447e-05 | 10262
BALFOUR 1101547810 | BALFOUR 1101 | 14321101 |  | 24.4697 | 1.2541 |  | 406.8333 | 0.0002287 | 9521 | 0.07681 | 3881 | 1.7433e-05 | 10263
SANTA YNEZ 1101673618 | SANTA YNEZ 1101 | 182721101 | TRUE | 0.37149 | 0.036148 | 0.0402 | 5.5 | 0.00026014 | 8881 | 0.067 | 6057 | 1.743e-05 | 10264
RICE 110284580 | RICE 1102 | 62831102 |  | 13.6484 | 0.30031 |  | 230 | 0.00022727 | 9558 | 0.076818 | 3877 | 1.7417e-05 | 10265
LOS MOLINOS 11023302 | LOS MOLINOS 1102 | 103481102 |  | 4.8325 | 0.12027 |  | 95 | 0.00025556 | 8972 | 0.068625 | 5256 | 1.7416e-05 | 10266
EL PECO 11025590 | EL PECO 1102 | 253981102 |  | 11.5032 | 0.2495 |  | 192.5 | 0.00022731 | 9554 | 0.076768 | 3899 | 1.7411e-05 | 10267
ARBUCKLE 11023014 | ARBUCKLE 1102 | 62081102 |  | 32.082 | 1.8915 |  | 549 | 0.0002275 | 9549 | 0.076945 | 3798 | 1.7379e-05 | 10268
LIVINGSTON 11053900 | LIVINGSTON 1105 | 252261105 |  | 13.1156 | 1.665 |  | 229 | 0.00022519 | 9605 | 0.077103 | 3690 | 1.7376e-05 | 10269
GANSO 11041120 | GANSO 1104 | 254541104 |  | 13.5834 | 0.66576 |  | 224 | 0.0002249 | 9612 | 0.07733 | 3432 | 1.7374e-05 | 10270
SEMITROPIC 11044549 | SEMITROPIC 1104 | 252901104 |  | 8.0436 | 0.15488 |  | 131.5 | 0.00022519 | 9604 | 0.07728 | 3503 | 1.7373e-05 | 10271
CORNING 11021460 | CORNING 1102 | 103331102 |  | 20.4562 | 2.359 |  | 358.5 | 0.00025835 | 8918 | 0.067204 | 5805 | 1.7358e-05 | 10272
PASO ROBLES 110789148 | PASO ROBLES 1107 | 182611107 |  | 2.0989 | 0.14955 |  | 37 | 0.00025586 | 8964 | 0.067958 | 5412 | 1.7351e-05 | 10273
RIVERBANK 171439736 | RIVERBANK 1714 | 163191714 |  | 0.5207 | 0.013007 |  | 10.5 | 0.00022412 | 9625 | 0.0774 | 3397 | 1.7347e-05 | 10274
OCEANO 1108478286 | OCEANO 1108 | 182601108 |  | 0.9234 | 0.20379 |  | 16 | 0.00030708 | 7863 | 0.061197 | 6869 | 1.7346e-05 | 10275
NEWMAN 11069140 | NEWMAN 1106 | 162741106 |  | 16.2562 | 0.42015 |  | 330 | 0.00022545 | 9600 | 0.076984 | 3772 | 1.7321e-05 | 10276
MC FARLAND 1102CB | MC FARLAND 1102 | 253181102 |  | 22.3028 | 0.62187 |  | 374.25 | 0.00022815 | 9534 | 0.076431 | 4042 | 1.7317e-05 | 10277
SAN LUIS OBISPO 1103486690 | SAN LUIS OBISPO 1103 | 182631103 |  | 0.022766 | 0 |  | 0.5 | 0.00032613 | 7518 | 0.053073 | 8251 | 1.7309e-05 | 10278
HERDLYN 11038048 | HERDLYN 1103 | 163741103 |  | 15.8644 | 0.42256 |  | 307 | 0.0002243 | 9619 | 0.077164 | 3632 | 1.7298e-05 | 10279
HURON 111637370 | HURON 1116 | 253161116 |  | 7.936 | 0.018227 |  | 131.5 | 0.00022326 | 9638 | 0.0774 | 3397 | 1.728e-05 | 10280
CRESSEY 21034350 | CRESSEY 2103 | 254702103 |  | 24.005 | 1.7687 |  | 440.5 | 0.00022699 | 9563 | 0.076046 | 4184 | 1.7276e-05 | 10281
KERN OIL 11062794 | KERN OIL 1106 | 252721106 |  | 1.4615 | 0.021061 |  | 27.5 | 0.00022721 | 9559 | 0.076515 | 4010 | 1.7271e-05 | 10282
MC MULLIN 11065402F | MC MULLIN 1106 | 254411106 |  | 4.0878 | 0.64241 |  | 70 | 0.00022309 | 9642 | 0.0774 | 3397 | 1.7267e-05 | 10283
BANTA 1103406410 | BANTA 1103 | 162471103 |  | 16.446 | 1.2632 |  | 328 | 0.000226 | 9584 | 0.076845 | 3858 | 1.7267e-05 | 10284
PEASE 11037274 | PEASE 1103 | 153751103 |  | 8.4829 | 0.65067 |  | 152.5 | 0.00023568 | 9372 | 0.072859 | 4676 | 1.726e-05 | 10285
LINDEN 110144878 | LINDEN 1101 | 162071101 |  | 0.43084 | 0.024663 |  | 8.5 | 0.00022295 | 9646 | 0.0774 | 3397 | 1.7256e-05 | 10286
WRIGHT 11103800 | WRIGHT 1110 | 254641110 |  | 7.9992 | 0.25603 |  | 150.5 | 0.00023491 | 9390 | 0.07364 | 4589 | 1.7253e-05 | 10287
TUPMAN 11031188 | TUPMAN 1103 | 254561103 |  | 9.2687 | 0.25323 |  | 160.5 | 0.00022377 | 9631 | 0.077106 | 3687 | 1.7252e-05 | 10288
RIVERBANK 1712CB | RIVERBANK 1712 | 163191712 |  | 11.5333 | 1.338 |  | 187.1667 | 0.0002254 | 9602 | 0.076842 | 3864 | 1.7251e-05 | 10289
RIO BRAVO 1106CUS7788 | RIO BRAVO 1106 | 252861106 |  | 0.01117 | 0 |  | 1 | 0.0002228 | 9650 | 0.0774 | 3397 | 1.7245e-05 | 10290
PASO ROBLES 1103CB | PASO ROBLES 1103 | 182611103 |  | 6.3327 | 1.9088 |  | 112.8333 | 0.00026783 | 8703 | 0.065778 | 6307 | 1.7236e-05 | 10291
DEVILS DEN 1101CB | DEVILS DEN 1101 | 253451101 |  | 12.955 | 0 |  | 216 | 0.00025363 | 9005 | 0.068978 | 5196 | 1.7236e-05 | 10292
PLUMAS 210750638 | PLUMAS 2107 | 153732107 |  | 13.7516 | 0.70335 |  | 263 | 0.00022378 | 9630 | 0.077155 | 3639 | 1.7233e-05 | 10293
EL NIDO 11024760 | EL NIDO 1102 | 252451102 |  | 13.4115 | 0.49491 |  | 233 | 0.00022257 | 9655 | 0.0774 | 3397 | 1.7227e-05 | 10294
HUMBOLDT BAY 11024724 | HUMBOLDT BAY 1102 | 192341102 |  | 2.8354 | 0.55707 |  | 55.3333 | 0.00025707 | 8943 | 0.067 | 6057 | 1.7224e-05 | 10295
HAMILTON A 11012036 | HAMILTON A 1101 | 102121101 |  | 19.823 | 0.57728 |  | 352 | 0.00024165 | 9256 | 0.072411 | 4729 | 1.7222e-05 | 10296
ELK HILLS 1104CB | ELK HILLS 1104 | 252441104 |  | 1.3413 | 0 |  | 18.3333 | 0.000257 | 8944 | 0.067 | 6056 | 1.7219e-05 | 10297
EAST NICOLAUS 11031252 | EAST NICOLAUS 1103 | 152151103 |  | 20.1109 | 1.4125 |  | 349.5 | 0.00024578 | 9173 | 0.07005 | 5036 | 1.7219e-05 | 10298
DAIRYLAND 11055170 | DAIRYLAND 1105 | 252421105 |  | 13.9251 | 0.48574 |  | 240.5 | 0.00022421 | 9621 | 0.076995 | 3764 | 1.7218e-05 | 10299
TRES PINOS 1111203126 | TRES PINOS 1111 | 183221111 | TRUE | 6.7701 | 0.66793 | 0.10701 | 138.5 | 0.00013671 | 10823 | 0.28502 | 3036 | 1.7208e-05 | 10300
TUPMAN 11041527 | TUPMAN 1104 | 254561104 |  | 30.5533 | 0.68125 |  | 505.5 | 0.00022373 | 9632 | 0.07697 | 3783 | 1.7202e-05 | 10301
MAXWELL 11053302 | MAXWELL 1105 | 62881105 |  | 10.9252 | 0.42969 |  | 185 | 0.00025031 | 9072 | 0.069382 | 5132 | 1.7198e-05 | 10302
GANSO 1104579706 | GANSO 1104 | 254541104 |  | 0.40662 | 0.021827 |  | 5.5 | 0.00022218 | 9667 | 0.0774 | 3397 | 1.7197e-05 | 10303
CUYAMA 2102CB | CUYAMA 2102 | 253142102 |  | 13.9168 | 0.85585 |  | 242.1667 | 0.00025346 | 9008 | 0.067778 | 5481 | 1.7193e-05 | 10304
LOS OSITOS 2102624200 | LOS OSITOS 2102 | 182082102 |  | 2.2979 | 0.037623 |  | 49.5 | 0.00024412 | 9198 | 0.07038 | 4964 | 1.7191e-05 | 10305
OROSI 1101CB | OROSI 1101 | 252841101 |  | 24.6324 | 4.736 |  | 445.8333 | 0.00023553 | 9377 | 0.073616 | 4594 | 1.7174e-05 | 10306
ANITA 11062074 | ANITA 1106 | 102841106 |  | 19.5999 | 0.70735 |  | 376 | 0.00025141 | 9053 | 0.069236 | 5159 | 1.7174e-05 | 10307
SANTA RITA 11023560 | SANTA RITA 1102 | 253541102 |  | 15.5338 | 0.38777 |  | 277 | 0.00022488 | 9613 | 0.076563 | 3995 | 1.7169e-05 | 10308
DOLAN ROAD 110169466 | DOLAN ROAD 1101 | 182381101 |  | 13.5576 | 1.3121 |  | 258 | 0.00025598 | 8961 | 0.06703 | 5985 | 1.7161e-05 | 10309
RAINBOW 1106D7399 | RAINBOW 1106 | 254441106 |  | 6.8978 | 0.74796 |  | 119.5 | 0.00022228 | 9665 | 0.077139 | 3658 | 1.7148e-05 | 10310
ARBUCKLE 110494886 | ARBUCKLE 1104 | 62081104 |  | 4.2284 | 0.11584 |  | 72 | 0.00023225 | 9441 | 0.074396 | 4504 | 1.7139e-05 | 10311
RICE 1101247272 | RICE 1101 | 62831101 |  | 17.6735 | 0.59196 |  | 309.5 | 0.00022848 | 9529 | 0.075385 | 4351 | 1.7133e-05 | 10312
LINCOLN 11051278 | LINCOLN 1105 | 153701105 |  | 19.1536 | 0.95067 |  | 327 | 0.00025017 | 9075 | 0.068712 | 5241 | 1.7131e-05 | 10313
HOLLISTER 21024908 | HOLLISTER 2102 | 182492102 |  | 46.193 | 2.1247 |  | 950 | 0.00024878 | 9104 | 0.069378 | 5134 | 1.713e-05 | 10314
REEDLEY 11047892F | REEDLEY 1104 | 252341104 |  | 2.2065 | 0.57867 |  | 38.5 | 0.00024841 | 9115 | 0.069701 | 5086 | 1.7129e-05 | 10315
WINTERS 1102CB | WINTERS 1102 | 63321102 |  | 2.4901 | 0.28908 |  | 51.5 | 0.00024856 | 9108 | 0.069625 | 5098 | 1.7126e-05 | 10316
CARRIZO PLAINS 1101384116 | CARRIZO PLAINS 1101 | 253461101 |  | 44.5943 | 0.43656 |  | 790 | 0.00011477 | 10987 | 0.27448 | 3050 | 1.7121e-05 | 10317
ORLAND B 11032252 | ORLAND B 1103 | 102701103 |  | 16.2291 | 0.54976 |  | 275.5 | 0.00024238 | 9239 | 0.07146 | 4836 | 1.7107e-05 | 10318
TEMPLETON 2110CB | TEMPLETON 2110 | 183052110 |  | 6.1533 | 0.29835 |  | 117.8333 | 0.00025536 | 8976 | 0.06697 | 6074 | 1.7103e-05 | 10319
SAN JOAQUIN 110669621 | SAN JOAQUIN 1106 | 252361106 |  | 15.3401 | 0.22435 |  | 267 | 0.00022103 | 9685 | 0.077309 | 3461 | 1.7103e-05 | 10320
SCHINDLER 110590342 | SCHINDLER 1105 | 252891105 |  | 7.9331 | 0.18782 |  | 134.5 | 0.00022149 | 9679 | 0.077219 | 3575 | 1.7091e-05 | 10321
LAKEVILLE 1102272 | LAKEVILLE 1102 | 43371102 |  | 8.7109 | 1.0099 |  | 172.5 | 0.00025426 | 8996 | 0.067222 | 5790 | 1.709e-05 | 10322
SAN JOAQUIN 1112R487 | SAN JOAQUIN 1112 | 252361112 |  | 13.4624 | 0.48591 |  | 249 | 0.0002239 | 9629 | 0.07669 | 3940 | 1.7084e-05 | 10323
MERCED 1116705950 | MERCED 1116 | 252801116 |  | 16.3203 | 1.1066 |  | 283.5 | 0.0002215 | 9678 | 0.07713 | 3662 | 1.7079e-05 | 10324
WYANDOTTE 110613046 | WYANDOTTE 1106 | 102911106 |  | 33.861 | 2.5722 |  | 601.5 | 0.00024916 | 9098 | 0.069272 | 5150 | 1.7076e-05 | 10325
SALMON CREEK 1101571972 | SALMON CREEK 1101 | 43161101 |  | 1.8757 | 0.1045 |  | 38.5 | 0.00025302 | 9019 | 0.067634 | 5534 | 1.7074e-05 | 10326
CORNING 11041498 | CORNING 1104 | 103331104 |  | 26.3361 | 2.0313 |  | 467.5 | 0.00024779 | 9131 | 0.06939 | 5127 | 1.7071e-05 | 10327
LOCKEFORD 21024045 | LOCKEFORD 2102 | 163682102 |  | 1.9444 | 0.22854 |  | 35.5 | 0.00022562 | 9593 | 0.076082 | 4169 | 1.7066e-05 | 10328
KETTLEMAN HILLS 110149656 | KETTLEMAN HILLS 1101 | 252731101 |  | 14.9686 | 0.2538 |  | 250 | 0.00023887 | 9304 | 0.071538 | 4826 | 1.7055e-05 | 10329
SCHINDLER 111638456 | SCHINDLER 1116 | 252891116 |  | 19.4576 | 0.41886 |  | 326.5 | 0.00022307 | 9644 | 0.076403 | 4053 | 1.703e-05 | 10330
SANGER 110864662 | SANGER 1108 | 252351108 |  | 14.6152 | 1.4611 |  | 247.5 | 0.00022197 | 9671 | 0.076706 | 3933 | 1.702e-05 | 10331
MC ARTHUR 1102LR-RC-B | MC ARTHUR 1102 | 103491102 |  | 0.011677 | 0 |  | 0.5 | 0.00021982 | 9701 | 0.0774 | 3397 | 1.7014e-05 | 10332
GIFFEN 11029590 | GIFFEN 1102 | 253151102 |  | 0.017685 | 0 |  | 0.5 | 0.00021968 | 9707 | 0.0774 | 3397 | 1.7003e-05 | 10333
SANGER 1114R2940 | SANGER 1114 | 252351114 |  | 9.4875 | 1.2139 |  | 166.5 | 0.00022501 | 9607 | 0.076238 | 4112 | 1.7e-05 | 10334
KERMAN 1106R421 | KERMAN 1106 | 252711106 |  | 25.9236 | 0.83595 |  | 437 | 0.00022498 | 9608 | 0.076122 | 4155 | 1.6997e-05 | 10335
COLONY 110214022 | COLONY 1102 | 162231102 |  | 10.5727 | 0.71045 |  | 191.5 | 0.00021979 | 9703 | 0.077336 | 3425 | 1.6995e-05 | 10336
ESQUON 1103CB | ESQUON 1103 | 102171103 |  | 20.3494 | 1.5025 |  | 399.6667 | 0.00024041 | 9279 | 0.071802 | 4794 | 1.6992e-05 | 10337
ALPAUGH 110437392 | ALPAUGH 1104 | 254001104 |  | 10.3189 | 1.0646 |  | 189 | 0.00022483 | 9614 | 0.075909 | 4227 | 1.6987e-05 | 10338
TWISSELMAN 2105CUS4824 | TWISSELMAN 2105 | 254402105 |  | 0.0086413 | 0 |  | 0.5 | 0.00021946 | 9711 | 0.0774 | 3397 | 1.6987e-05 | 10339
VACA DIXON 11035187 | VACA DIXON 1103 | 63591103 |  | 6.4195 | 0.35673 |  | 111.5 | 0.00021946 | 9712 | 0.0774 | 3397 | 1.6986e-05 | 10340
LINCOLN 11042306 | LINCOLN 1104 | 153701104 |  | 13.0261 | 0.42229 |  | 230.5 | 0.00025314 | 9013 | 0.06709 | 5911 | 1.6976e-05 | 10341
SHAFTER 11023621 | SHAFTER 1102 | 253651102 |  | 10.8359 | 0.17905 |  | 178.5 | 0.00022548 | 9597 | 0.076093 | 4166 | 1.6972e-05 | 10342
GOOSE LAKE 110356686 | GOOSE LAKE 1103 | 254201103 |  | 21.8111 | 0.41313 |  | 386.5 | 0.00021971 | 9705 | 0.077119 | 3677 | 1.6966e-05 | 10343
LINDEN 1104CB | LINDEN 1104 | 162071104 |  | 7.9836 | 0.82936 |  | 144 | 0.00021914 | 9717 | 0.0774 | 3397 | 1.6961e-05 | 10344
CANAL 11033640 | CANAL 1103 | 252091103 |  | 22.6655 | 0.8541 |  | 420 | 0.00021983 | 9700 | 0.07721 | 3584 | 1.6949e-05 | 10345
ESQUON 11012054 | ESQUON 1101 | 102171101 |  | 45.5081 | 1.6192 |  | 819 | 0.00023766 | 9329 | 0.0711 | 4883 | 1.6948e-05 | 10346
HOLLISTER 21024780 | HOLLISTER 2102 | 182492102 |  | 6.4196 | 1.4828 |  | 129.5 | 0.00025173 | 9046 | 0.067402 | 5667 | 1.6948e-05 | 10347
ALPAUGH 11068470 | ALPAUGH 1106 | 254001106 |  | 27.4437 | 1.2102 |  | 464 | 0.00022044 | 9691 | 0.07686 | 3850 | 1.6943e-05 | 10348
LOGAN CREEK 21012432 | LOGAN CREEK 2101 | 103142101 |  | 12.1008 | 0.6346 |  | 206.5 | 0.00023815 | 9318 | 0.07167 | 4806 | 1.6939e-05 | 10349
CUYAMA 11033539 | CUYAMA 1103 | 253141103 |  | 3.0013 | 2.3829 |  | 58 | 0.00025274 | 9026 | 0.067001 | 6047 | 1.6933e-05 | 10350
CORTINA 11013056 | CORTINA 1101 | 63121101 |  | 3.9261 | 0.10464 |  | 63 | 0.00025115 | 9056 | 0.067825 | 5467 | 1.6932e-05 | 10351
CATLETT 11022502 | CATLETT 1102 | 153761102 |  | 24.1074 | 1.4901 |  | 409.5 | 0.00023416 | 9405 | 0.072527 | 4715 | 1.693e-05 | 10352
CAMDEN 1103453786 | CAMDEN 1103 | 252301103 |  | 1.569 | 0.04515 |  | 29.5 | 0.00021873 | 9724 | 0.0774 | 3397 | 1.6929e-05 | 10353
GONZALES 1101522356 | GONZALES 1101 | 182131101 |  | 0.015982 | 0 |  | 0.5 | 0.00025263 | 9028 | 0.067 | 6057 | 1.6926e-05 | 10354
CANAL 11032990 | CANAL 1103 | 252091103 |  | 13.934 | 0.31327 |  | 250.5 | 0.00022449 | 9617 | 0.075955 | 4214 | 1.6905e-05 | 10355
CORRAL 110175204 | CORRAL 1101 | 162991101 | TRUE | 19.442 | 0.46175 | 0.19826 | 363.5 | 0.00015991 | 10600 | 0.094329 | 3329 | 1.6879e-05 | 10356
COALINGA NO 2 1106CB | COALINGA NO 2 1106 | 252381106 |  | 13.0936 | 0.041755 |  | 224.5 | 0.00025 | 9084 | 0.067445 | 5640 | 1.6877e-05 | 10357
KERMAN 110456116 | KERMAN 1104 | 252711104 |  | 17.8314 | 0.94879 |  | 304.5 | 0.00022306 | 9645 | 0.075962 | 4212 | 1.6871e-05 | 10358
EL NIDO 11014480 | EL NIDO 1101 | 252451101 |  | 7.4287 | 0.48839 |  | 122.5 | 0.00021773 | 9737 | 0.0774 | 3397 | 1.6852e-05 | 10359
LIVINGSTON 11017010 | LIVINGSTON 1101 | 252261101 |  | 11.1508 | 0.31454 |  | 187 | 0.00021762 | 9739 | 0.0774 | 3397 | 1.6844e-05 | 10360
LOCKEFORD 210212686 | LOCKEFORD 2102 | 163682102 |  | 38.1204 | 1.602 |  | 660.5 | 0.00021804 | 9729 | 0.077266 | 3524 | 1.6837e-05 | 10361
FIREBAUGH 11033830 | FIREBAUGH 1103 | 253471103 |  | 37.7512 | 0.93108 |  | 698.5 | 0.00022174 | 9676 | 0.076566 | 3993 | 1.6837e-05 | 10362
CRESSEY 2104551990 | CRESSEY 2104 | 254702104 |  | 11.2812 | 0.19432 |  | 206.5 | 0.00021739 | 9744 | 0.0774 | 3397 | 1.6826e-05 | 10363
WELLFIELD 1104CB | WELLFIELD 1104 | 254291104 |  | 5.2504 | 0.029374 |  | 85 | 0.0002425 | 9236 | 0.068875 | 5210 | 1.6823e-05 | 10364
RIO BRAVO 1103CB | RIO BRAVO 1103 | 252861103 |  | 15.8878 | 0.33145 |  | 245 | 0.00021979 | 9702 | 0.076824 | 3873 | 1.6822e-05 | 10365
CAYUCOS 1102CB | CAYUCOS 1102 | 182551102 |  | 5.2842 | 0.86916 |  | 99.3333 | 0.00025638 | 8955 | 0.066908 | 6087 | 1.6818e-05 | 10366
ARBUCKLE 11043042 | ARBUCKLE 1104 | 62081104 |  | 5.3538 | 0.13907 |  | 91.5 | 0.00024378 | 9202 | 0.070072 | 5028 | 1.6812e-05 | 10367
HIGHWAY 1101738 | HIGHWAY 1101 | 42651101 |  | 6.4218 | 0.43608 |  | 128 | 0.00024929 | 9094 | 0.067384 | 5680 | 1.6783e-05 | 10368
TAFT 11033068 | TAFT 1103 | 252081103 |  | 11.7167 | 0.14578 |  | 198.5 | 0.0002504 | 9067 | 0.067001 | 6048 | 1.6777e-05 | 10369
SAN JOAQUIN 1112R1160 | SAN JOAQUIN 1112 | 252361112 |  | 9.595 | 0.23217 |  | 177.5 | 0.00021669 | 9755 | 0.0774 | 3397 | 1.6771e-05 | 10370
LAKEVIEW 11023548 | LAKEVIEW 1102 | 253411102 |  | 3.0697 | 0.011433 |  | 50 | 0.00024848 | 9111 | 0.067416 | 5655 | 1.6765e-05 | 10371
CAPAY 11012254 | CAPAY 1101 | 102111101 |  | 20.4427 | 1.9238 |  | 357.5 | 0.00024538 | 9180 | 0.068288 | 5336 | 1.6762e-05 | 10372
LAKEVIEW 11034488 | LAKEVIEW 1103 | 253411103 |  | 16.7852 | 0.061386 |  | 287.5 | 0.00024366 | 9209 | 0.069071 | 5182 | 1.6757e-05 | 10373
EEL RIVER 11028416 | EEL RIVER 1102 | 192381102 |  | 16.9146 | 0.95479 |  | 323.8333 | 0.00024987 | 9085 | 0.067048 | 5948 | 1.6749e-05 | 10374
MC MULLIN 11056450 | MC MULLIN 1105 | 254411105 |  | 15.3008 | 0.086489 |  | 251.8333 | 0.00021676 | 9753 | 0.077271 | 3515 | 1.6747e-05 | 10375
COLUSA 11013537 | COLUSA 1101 | 62021101 |  | 5.5007 | 0.084184 |  | 100 | 0.00021632 | 9758 | 0.0774 | 3397 | 1.6743e-05 | 10376
REEDLEY 1104274990 | REEDLEY 1104 | 252341104 |  | 34.4613 | 6.1843 |  | 636 | 0.00024067 | 9276 | 0.070229 | 4999 | 1.6743e-05 | 10377
GERBER 11011444 | GERBER 1101 | 103391101 |  | 15.2848 | 1.277 |  | 278 | 0.0002481 | 9125 | 0.067419 | 5651 | 1.674e-05 | 10378
BONITA 11015940 | BONITA 1101 | 255391101 |  | 7.0435 | 0.34117 |  | 118.5 | 0.00021725 | 9746 | 0.077195 | 3597 | 1.6734e-05 | 10379
DALY CITY 11045437 | DALY CITY 1104 | 22641104 |  | 0.60086 | 0.01635 |  | 8.8333 | 0.00024014 | 9288 | 0.069623 | 5099 | 1.6721e-05 | 10380
PANOCHE 1101752874 | PANOCHE 1101 | 253671101 |  | 9.1099 | 0.11584 |  | 154 | 0.00023569 | 9371 | 0.070886 | 4906 | 1.6718e-05 | 10381
LAKEVIEW 11074490 | LAKEVIEW 1107 | 253411107 |  | 26.2882 | 0.13976 |  | 439.8333 | 0.00024674 | 9151 | 0.068137 | 5372 | 1.6716e-05 | 10382
MCKITTRICK 11013043 | MCKITTRICK 1101 | 252781101 |  | 10.2255 | 0.036087 |  | 184 | 0.00024842 | 9114 | 0.067289 | 5738 | 1.6714e-05 | 10383
CORCORAN 111285080 | CORCORAN 1112 | 252171112 |  | 16.3209 | 2.6023 |  | 269 | 0.00022603 | 9582 | 0.075406 | 4350 | 1.6709e-05 | 10384
PUTAH CREEK 110385768 | PUTAH CREEK 1103 | 63681103 |  | 5.9387 | 0.45564 |  | 123 | 0.00024149 | 9258 | 0.069526 | 5117 | 1.6707e-05 | 10385
CAMDEN 110356058 | CAMDEN 1103 | 252301103 |  | 0.018311 | 0 |  | 0.5 | 0.0002158 | 9763 | 0.0774 | 3397 | 1.6703e-05 | 10386
CARNERAS 1102CB | CARNERAS 1102 | 252321102 |  | 7.6297 | 0 |  | 125.5 | 0.00024346 | 9217 | 0.069639 | 5095 | 1.67e-05 | 10387
EEL RIVER 11024396 | EEL RIVER 1102 | 192381102 |  | 16.3588 | 2.6136 |  | 295.5 | 0.00025067 | 9065 | 0.067176 | 5830 | 1.6681e-05 | 10388
KINGSBURG 1114828488 | KINGSBURG 1114 | 252241114 |  | 24.1255 | 1.6531 |  | 432 | 0.0002155 | 9767 | 0.0774 | 3397 | 1.668e-05 | 10389
MAXWELL 1105429752 | MAXWELL 1105 | 62881105 |  | 9.8843 | 0.029766 |  | 160.6667 | 0.00024676 | 9150 | 0.067791 | 5479 | 1.6679e-05 | 10390
OILFIELDS 11037006 | OILFIELDS 1103 | 182391103 |  | 6.9558 | 0.11716 |  | 130.5 | 0.00018468 | 10282 | 0.086531 | 3360 | 1.6664e-05 | 10391
MORMON 1102773114 | MORMON 1102 | 163211102 |  | 0.23411 | 0 |  | 3 | 0.0002153 | 9769 | 0.0774 | 3397 | 1.6664e-05 | 10392
CARUTHERS 1102426884 | CARUTHERS 1102 | 252371102 |  | 4.4652 | 0.29211 |  | 76.5 | 0.00021518 | 9771 | 0.0774 | 3397 | 1.6655e-05 | 10393
COTTLE 17086229 | COTTLE 1708 | 163711708 |  | 10.1277 | 0.54844 |  | 171 | 0.00021514 | 9772 | 0.0774 | 3397 | 1.6652e-05 | 10394
BUTTE 11042440 | BUTTE 1104 | 103081104 |  | 28.122 | 2.4915 |  | 496.5 | 0.00023597 | 9363 | 0.07165 | 4808 | 1.665e-05 | 10395
EL PECO 110590066 | EL PECO 1105 | 253981105 |  | 25.6385 | 0.80792 |  | 441.5 | 0.00021575 | 9764 | 0.077199 | 3594 | 1.6638e-05 | 10396
STOREY 11096250 | STOREY 1109 | 254611109 |  | 31.23 | 1.6107 |  | 583 | 0.00022128 | 9682 | 0.075292 | 4367 | 1.6638e-05 | 10397
WESTLEY 11018660 | WESTLEY 1101 | 162671101 |  | 19.8184 | 0.60523 |  | 356 | 0.00023341 | 9419 | 0.071568 | 4820 | 1.6635e-05 | 10398
LLAGAS 2101XR264 | LLAGAS 2101 | 83182101 |  | 20.5476 | 2.4289 |  | 398.3333 | 0.0002479 | 9128 | 0.067134 | 5869 | 1.6635e-05 | 10399
WATERLOO 11014437 | WATERLOO 1101 | 163151101 |  | 2.4307 | 0.41143 |  | 50.5 | 0.00022691 | 9566 | 0.075162 | 4390 | 1.6623e-05 | 10400
NORCO 11013965 | NORCO 1101 | 254691101 |  | 12.6508 | 0.13117 |  | 228.8333 | 0.00021475 | 9778 | 0.0774 | 3397 | 1.6621e-05 | 10401
DAVIS 110611072 | DAVIS 1106 | 62041106 |  | 16.901 | 0.37088 |  | 274 | 0.00021637 | 9757 | 0.076882 | 3840 | 1.6619e-05 | 10402
KERMAN 1104R1173 | KERMAN 1104 | 252711104 |  | 10.5338 | 0.41041 |  | 183 | 0.00021468 | 9780 | 0.0774 | 3397 | 1.6616e-05 | 10403
SAN LUIS OBISPO 1104798282 | SAN LUIS OBISPO 1104 | 182631104 |  | 0.035933 | 0 |  | 0.5 | 0.00024646 | 9155 | 0.067385 | 5679 | 1.6607e-05 | 10404
BELLEVUE 1102839 | BELLEVUE 1102 | 43181102 |  | 6.0537 | 0.40533 |  | 122 | 0.00024491 | 9189 | 0.068023 | 5402 | 1.6597e-05 | 10405
TECUYA 1101CB | TECUYA 1101 | 254511101 |  | 0.011572 | 0 |  | 1 | 0.00024099 | 9268 | 0.068853 | 5215 | 1.6593e-05 | 10406
SMYRNA 11064550 | SMYRNA 1106 | 253551106 |  | 12.8308 | 0.15086 |  | 214.5 | 0.00021437 | 9790 | 0.0774 | 3397 | 1.6592e-05 | 10407
SOLEDAD 2105125484 | SOLEDAD 2105 | 182052105 |  | 1.4905 | 0 |  | 27.5 | 0.00023561 | 9374 | 0.070239 | 4995 | 1.6592e-05 | 10408
STONE CORRAL 11107778F | STONE CORRAL 1110 | 252921110 |  | 5.9331 | 1.8849 |  | 117.5 | 0.00023695 | 9341 | 0.070569 | 4947 | 1.659e-05 | 10409
ALPAUGH 110636528 | ALPAUGH 1106 | 254001106 |  | 11.4937 | 2.6529 |  | 201 | 0.00022053 | 9690 | 0.075912 | 4226 | 1.659e-05 | 10410
MC MULLIN 11055200 | MC MULLIN 1105 | 254411105 |  | 17.9496 | 0.87807 |  | 306.3333 | 0.00021453 | 9783 | 0.077297 | 3475 | 1.6577e-05 | 10411
ORLAND B 11032204 | ORLAND B 1103 | 102701103 |  | 30.4512 | 1.8008 |  | 508.5 | 0.0002387 | 9309 | 0.07024 | 4994 | 1.6575e-05 | 10412
LOCKEFORD 210212472 | LOCKEFORD 2102 | 163682102 |  | 21.1191 | 1.4656 |  | 371.8333 | 0.00023491 | 9391 | 0.071923 | 4780 | 1.657e-05 | 10413
SANTA MARIA 1110M76 | SANTA MARIA 1110 | 182671110 |  | 10.8992 | 0.28464 |  | 183 | 0.000246 | 9165 | 0.067222 | 5788 | 1.6564e-05 | 10414
MC FARLAND 11021418 | MC FARLAND 1102 | 253181102 |  | 18.1321 | 0.57567 |  | 314.5 | 0.00021391 | 9799 | 0.0774 | 3397 | 1.6557e-05 | 10415
NORCO 1101CB | NORCO 1101 | 254691101 |  | 13.663 | 0.0065535 |  | 245.8333 | 0.00021617 | 9761 | 0.076742 | 3915 | 1.6555e-05 | 10416
PARLIER 1105740598 | PARLIER 1105 | 252291105 |  | 18.29 | 1.4248 |  | 314 | 0.00021389 | 9801 | 0.0774 | 3397 | 1.6555e-05 | 10417
GUSTINE 11026926 | GUSTINE 1102 | 163111102 |  | 19.9969 | 0.82092 |  | 348 | 0.00023053 | 9475 | 0.071395 | 4845 | 1.6552e-05 | 10418
PEABODY 210515812 | PEABODY 2105 | 63642105 |  | 36.3709 | 2.0417 |  | 614.5 | 0.00022179 | 9675 | 0.074966 | 4418 | 1.6549e-05 | 10419
SCHINDLER 111449248 | SCHINDLER 1114 | 252891114 |  | 6.5065 | 0.12557 |  | 115.5 | 0.00022979 | 9494 | 0.071741 | 4798 | 1.6544e-05 | 10420
TIVY VALLEY 11067210 | TIVY VALLEY 1106 | 252941106 |  | 7.7835 | 0.95677 |  | 145 | 0.00024445 | 9193 | 0.067691 | 5513 | 1.6543e-05 | 10421
MC FARLAND 1104521389 | MC FARLAND 1104 | 253181104 |  | 1.7307 | 0.24861 |  | 27.5 | 0.00021372 | 9806 | 0.0774 | 3397 | 1.6542e-05 | 10422
KERMAN 1101R2875 | KERMAN 1101 | 252711101 |  | 21.9582 | 1.2579 |  | 377 | 0.0002144 | 9788 | 0.077206 | 3589 | 1.6534e-05 | 10423
CHARCA 11021192 | CHARCA 1102 | 254501102 |  | 11.0196 | 0.31995 |  | 188 | 0.00021352 | 9809 | 0.0774 | 3397 | 1.6527e-05 | 10424
LIVINGSTON 110190480 | LIVINGSTON 1101 | 252261101 |  | 15.2058 | 0.44798 |  | 257 | 0.00021964 | 9709 | 0.076242 | 4111 | 1.6512e-05 | 10425
SAN JOAQUIN 1112D3025 | SAN JOAQUIN 1112 | 252361112 |  | 1.7373 | 0.12483 |  | 31 | 0.00021744 | 9743 | 0.07583 | 4252 | 1.6502e-05 | 10426
SCHINDLER 111059862 | SCHINDLER 1110 | 252891110 |  | 3.549 | 0.21066 |  | 60.5 | 0.00021313 | 9820 | 0.0774 | 3397 | 1.6497e-05 | 10427
AVENAL 2101602496 | AVENAL 2101 | 255002101 |  | 3.8099 | 0.055293 |  | 62.8333 | 0.00022963 | 9496 | 0.072161 | 4759 | 1.6496e-05 | 10428
CAMPHORA 110177978 | CAMPHORA 1101 | 182071101 |  | 19.7208 | 0.81697 |  | 411.5 | 0.00024201 | 9247 | 0.068097 | 5384 | 1.6491e-05 | 10429
WILKINS SLOUGH 1102799542 | WILKINS SLOUGH 1102 | 62771102 |  | 3.5731 | 0.072761 |  | 65 | 0.00021473 | 9779 | 0.077026 | 3747 | 1.6489e-05 | 10430
WESTLEY 1103CB | WESTLEY 1103 | 162671103 |  | 12.6347 | 1.8737 |  | 254 | 0.00022558 | 9595 | 0.075087 | 4403 | 1.6488e-05 | 10431
RICE 110230422 | RICE 1102 | 62831102 |  | 9.8403 | 0.25949 |  | 188 | 0.00021331 | 9813 | 0.077316 | 3451 | 1.6481e-05 | 10432
HARDWICK 11016510 | HARDWICK 1101 | 253711101 |  | 29.5341 | 2.9314 |  | 521 | 0.00021418 | 9796 | 0.077107 | 3686 | 1.6472e-05 | 10433
WOODLAND 110120252 | WOODLAND 1101 | 62031101 |  | 3.5303 | 0 |  | 57.5 | 0.00022293 | 9647 | 0.074588 | 4477 | 1.6463e-05 | 10434
RAINBOW 110556456 | RAINBOW 1105 | 254441105 |  | 14.4912 | 1.1408 |  | 257 | 0.00021303 | 9823 | 0.077308 | 3462 | 1.6458e-05 | 10435
HENRIETTA 11048240 | HENRIETTA 1104 | 252681104 |  | 9.1106 | 0.26537 |  | 148.5 | 0.00021786 | 9736 | 0.076133 | 4148 | 1.6454e-05 | 10436
ELK HILLS 11043522 | ELK HILLS 1104 | 252441104 |  | 32.6263 | 1.2273 |  | 574.3333 | 0.00023594 | 9365 | 0.070751 | 4926 | 1.6437e-05 | 10437
CORNING 11011620 | CORNING 1101 | 103331101 |  | 13.3724 | 0.83129 |  | 234.5 | 0.00023957 | 9293 | 0.068796 | 5224 | 1.6434e-05 | 10438
MADERA 11196552 | MADERA 1119 | 252761119 |  | 2.8162 | 0.54317 |  | 56.5 | 0.00021229 | 9837 | 0.0774 | 3397 | 1.6431e-05 | 10439
BLACKWELL 1102CB | BLACKWELL 1102 | 254681102 |  | 9.7719 | 0.48948 |  | 183 | 0.00023307 | 9427 | 0.071123 | 4880 | 1.6426e-05 | 10440
CRESSEY 2103596130 | CRESSEY 2103 | 254702103 |  | 6.9518 | 0.36555 |  | 122.5 | 0.00022533 | 9603 | 0.073316 | 4632 | 1.6422e-05 | 10441
SMYRNA 11021183 | SMYRNA 1102 | 253551102 |  | 12.5699 | 0.38736 |  | 212 | 0.00021214 | 9839 | 0.0774 | 3397 | 1.6419e-05 | 10442
PASO ROBLES 1102R64 | PASO ROBLES 1102 | 182611102 |  | 0.7826 | 0 |  | 18 | 0.00023944 | 9295 | 0.068346 | 5318 | 1.6418e-05 | 10443
AIRWAYS 1107671922 | AIRWAYS 1107 | 252041107 |  | 12.2286 | 0.97418 |  | 219.5 | 0.00021195 | 9843 | 0.0774 | 3397 | 1.6405e-05 | 10444
GLENN 11012552 | GLENN 1101 | 102601101 |  | 17.3075 | 0.79111 |  | 293 | 0.00024091 | 9270 | 0.068317 | 5328 | 1.6402e-05 | 10445
OCEANO 1106Q02 | OCEANO 1106 | 182601106 |  | 3.7467 | 4.7598 |  | 65.5 | 0.00030516 | 7907 | 0.053815 | 7996 | 1.6399e-05 | 10446
GOOSE LAKE 11061162 | GOOSE LAKE 1106 | 254201106 |  | 45.5583 | 1.6605 |  | 762 | 0.00021375 | 9805 | 0.077105 | 3688 | 1.6398e-05 | 10447
EL NIDO 11044470 | EL NIDO 1104 | 252451104 |  | 21.3046 | 0.86242 |  | 385 | 0.00021291 | 9827 | 0.077025 | 3748 | 1.6383e-05 | 10448
GEYSERVILLE 1101975350 | GEYSERVILLE 1101 | 42891101 | TRUE | 0.31713 | 0.021092 | 0.03626 | 6 | 0.00023621 | 9356 | 0.069144 | 5168 | 1.6375e-05 | 10449
MORMON 1101922274 | MORMON 1101 | 163211101 |  | 3.0311 | 0.46834 |  | 52.5 | 0.00021155 | 9852 | 0.0774 | 3397 | 1.6374e-05 | 10450
TRES VIAS 11011982 | TRES VIAS 1101 | 103251101 |  | 12.5623 | 0.37097 |  | 207 | 0.00022928 | 9507 | 0.071663 | 4807 | 1.6371e-05 | 10451
LIVINGSTON 110529612 | LIVINGSTON 1105 | 252261105 |  | 29.1243 | 2.2799 |  | 503 | 0.00021706 | 9749 | 0.076155 | 4142 | 1.637e-05 | 10452
OROSI 110495092 | OROSI 1104 | 252841104 |  | 6.053 | 1.4721 |  | 115.5 | 0.00023601 | 9362 | 0.070242 | 4993 | 1.636e-05 | 10453
LOCKEFORD 2102206884 | LOCKEFORD 2102 | 163682102 |  | 48.2437 | 8.0007 |  | 822.5 | 0.00023084 | 9466 | 0.070449 | 4955 | 1.6349e-05 | 10454
DAIRYLAND 11122060 | DAIRYLAND 1112 | 252421112 |  | 2.8594 | 0.1261 |  | 51 | 0.00021122 | 9858 | 0.0774 | 3397 | 1.6348e-05 | 10455
TRES PINOS 11114032 | TRES PINOS 1111 | 183221111 |  | 11.9736 | 1.1465 |  | 167.8333 | 0.00023931 | 9296 | 0.068311 | 5329 | 1.634e-05 | 10456
SANTA YNEZ 1104685160 | SANTA YNEZ 1104 | 182721104 |  | 1.7047 | 0.032921 |  | 32.5 | 0.00024376 | 9204 | 0.067 | 6057 | 1.6332e-05 | 10457
CORCORAN 11188180 | CORCORAN 1118 | 252171118 |  | 17.5163 | 0.87727 |  | 311.5 | 0.00021117 | 9860 | 0.07735 | 3413 | 1.6327e-05 | 10458
FAMOSO 110797800 | FAMOSO 1107 | 252461107 |  | 13.6594 | 0.32798 |  | 244.5 | 0.00021094 | 9861 | 0.0774 | 3397 | 1.6327e-05 | 10459
STONE CORRAL 11087100 | STONE CORRAL 1108 | 252921108 |  | 4.6746 | 0.57565 |  | 83.5 | 0.00023848 | 9315 | 0.068744 | 5233 | 1.6303e-05 | 10460
COPUS 1102CB | COPUS 1102 | 253871102 |  | 7.2623 | 0.24779 |  | 123 | 0.00024164 | 9257 | 0.06734 | 5709 | 1.6268e-05 | 10461
OILFIELDS 1103441010 | OILFIELDS 1103 | 182391103 | TRUE | 0.78722 | 0.019656 | 0.094308 | 14.5 | 0.00017344 | 10438 | 0.093782 | 3331 | 1.6266e-05 | 10462
GANSO 11033276 | GANSO 1103 | 254541103 |  | 10.2727 | 0.17663 |  | 173 | 0.0002113 | 9855 | 0.07712 | 3676 | 1.626e-05 | 10463
OCEANO 1104337754 | OCEANO 1104 | 182601104 | TRUE | 0.20996 | 0.038317 | 0.03782 | 4.5 | 0.00024261 | 9232 | 0.067 | 6057 | 1.6255e-05 | 10464
GUSTINE 110264140 | GUSTINE 1102 | 163111102 |  | 13.3774 | 0.62094 |  | 228.5 | 0.00022275 | 9651 | 0.07332 | 4631 | 1.6247e-05 | 10465
NEWHALL 11096000 | NEWHALL 1109 | 254461109 |  | 32.16 | 0.69528 |  | 604.8333 | 0.00021031 | 9871 | 0.077266 | 3522 | 1.6247e-05 | 10466
IGNACIO 1104469764 | IGNACIO 1104 | 42481104 |  | 38.0289 | 1.2428 |  | 755 | 0.00023522 | 9385 | 0.069701 | 5085 | 1.6246e-05 | 10467
CARUTHERS 1105749586 | CARUTHERS 1105 | 252371105 |  | 7.873 | 0.39853 |  | 139.5 | 0.00020978 | 9877 | 0.0774 | 3397 | 1.6237e-05 | 10468
ALPAUGH 11038030 | ALPAUGH 1103 | 254001103 |  | 7.2186 | 0.42541 |  | 131.5 | 0.00020978 | 9878 | 0.0774 | 3397 | 1.6237e-05 | 10469
WAHTOKE 11087460 | WAHTOKE 1108 | 254531108 |  | 14.92 | 1.201 |  | 266 | 0.0002109 | 9862 | 0.07722 | 3573 | 1.6232e-05 | 10470
WAHTOKE 11087570 | WAHTOKE 1108 | 254531108 |  | 18.538 | 2.7367 |  | 343 | 0.00023256 | 9432 | 0.069906 | 5063 | 1.6202e-05 | 10471
MC MULLIN 11066780 | MC MULLIN 1106 | 254411106 |  | 6.8705 | 0 |  | 112.5 | 0.00021033 | 9870 | 0.077044 | 3737 | 1.6196e-05 | 10472
GOOSE LAKE 2104573054 | GOOSE LAKE 2104 | 254202104 |  | 4.4965 | 0.011733 |  | 75 | 0.00023283 | 9430 | 0.070026 | 5042 | 1.6183e-05 | 10473
MARYSVILLE 1108150116 | MARYSVILLE 1108 | 152011108 |  | 8.679 | 0.53896 |  | 175 | 0.00021308 | 9822 | 0.076062 | 4175 | 1.6179e-05 | 10474
AVENA 170212876 | AVENA 1702 | 163571702 |  | 2.6944 | 0.32695 |  | 47 | 0.00020901 | 9891 | 0.0774 | 3397 | 1.6178e-05 | 10475
SAN BENITO 210275262 | SAN BENITO 2102 | 182742102 |  | 3.3103 | 0.14764 |  | 59 | 0.00024136 | 9260 | 0.067 | 6057 | 1.6171e-05 | 10476
KINGSBURG 11136070 | KINGSBURG 1113 | 252241113 |  | 22.084 | 1.4009 |  | 388.5 | 0.00020901 | 9892 | 0.077337 | 3424 | 1.6169e-05 | 10477
CHOWCHILLA 110652144 | CHOWCHILLA 1106 | 254101106 |  | 21.8905 | 0.95748 |  | 378 | 0.00021022 | 9872 | 0.076739 | 3916 | 1.6166e-05 | 10478
FIREBAUGH 1101738194 | FIREBAUGH 1101 | 253471101 |  | 15.3734 | 0.61857 |  | 303.5 | 0.0002092 | 9888 | 0.077268 | 3520 | 1.6164e-05 | 10479
SEMITROPIC 111037810 | SEMITROPIC 1110 | 252901110 |  | 14.9388 | 0.36205 |  | 247.5 | 0.00020881 | 9897 | 0.0774 | 3397 | 1.6162e-05 | 10480
WAHTOKE 11087180 | WAHTOKE 1108 | 254531108 |  | 13.8948 | 1.1916 |  | 246 | 0.0002278 | 9541 | 0.071439 | 4838 | 1.6158e-05 | 10481
STONE CORRAL 111075288 | STONE CORRAL 1110 | 252921110 |  | 6.306 | 0.68813 |  | 112.5 | 0.00023989 | 9290 | 0.067286 | 5740 | 1.6153e-05 | 10482
MADISON 11038822 | MADISON 1103 | 63171103 |  | 19.7998 | 1.1366 |  | 352.5 | 0.00023017 | 9483 | 0.070822 | 4915 | 1.6125e-05 | 10483
EL CAPITAN 110311670 | EL CAPITAN 1103 | 253881103 |  | 16.1412 | 0.5482 |  | 287.5 | 0.00023441 | 9400 | 0.06826 | 5345 | 1.6124e-05 | 10484
HARDWICK 11026020 | HARDWICK 1102 | 253711102 |  | 3.4848 | 0.17669 |  | 60 | 0.00020832 | 9905 | 0.0774 | 3397 | 1.6124e-05 | 10485
GIFFEN 1103301980 | GIFFEN 1103 | 253151103 |  | 14.0195 | 0.31076 |  | 234 | 0.00020887 | 9895 | 0.077192 | 3599 | 1.6119e-05 | 10486
LAKEVILLE 1101266 | LAKEVILLE 1101 | 43371101 |  | 14.306 | 0.70357 |  | 287.5 | 0.00023982 | 9291 | 0.067243 | 5770 | 1.6112e-05 | 10487
DALY CITY 110442434 | DALY CITY 1104 | 22641104 |  | 1.3422 | 0 |  | 26 | 0.00023431 | 9403 | 0.069333 | 5141 | 1.611e-05 | 10488
ROUGH AND READY ISLA 110211559 | ROUGH AND READY ISLA 1102 | 163081102 |  | 2.0052 | 0 |  | 34.5 | 0.00020806 | 9910 | 0.0774 | 3397 | 1.6104e-05 | 10489
ANGIOLA 11038123F | ANGIOLA 1103 | 252151103 |  | 1.2863 | 0.10097 |  | 21.5 | 0.00020827 | 9908 | 0.075778 | 4269 | 1.6083e-05 | 10490
CAMDEN 11046030 | CAMDEN 1104 | 252301104 |  | 2.8669 | 0.11848 |  | 53 | 0.00021131 | 9854 | 0.076482 | 4022 | 1.6076e-05 | 10491
MIDWAY 11021482 | MIDWAY 1102 | 252611102 |  | 21.2995 | 0.71655 |  | 354 | 0.00021376 | 9803 | 0.07465 | 4465 | 1.607e-05 | 10492
PANOCHE 11013690 | PANOCHE 1101 | 253671101 |  | 0.18788 | 0 |  | 2.5 | 0.00020742 | 9921 | 0.0774 | 3397 | 1.6054e-05 | 10493
CHOLAME 2102X22 | CHOLAME 2102 | 182562102 |  | 16.1946 | 0.27617 |  | 334.5 | 0.00023071 | 9471 | 0.069587 | 5104 | 1.6049e-05 | 10494
CORNING 11043304 | CORNING 1104 | 103331104 |  | 10.1038 | 0.65212 |  | 164 | 0.00023857 | 9313 | 0.067296 | 5734 | 1.6034e-05 | 10495
MENDOTA 1102514238 | MENDOTA 1102 | 252311102 |  | 47.5564 | 0.92273 |  | 786 | 0.00021229 | 9836 | 0.076112 | 4159 | 1.6023e-05 | 10496
REEDLEY 1104882458 | REEDLEY 1104 | 252341104 |  | 13.301 | 2.0684 |  | 242.5 | 0.00021134 | 9853 | 0.075963 | 4211 | 1.6018e-05 | 10497
CAPAY 11022264 | CAPAY 1102 | 102111102 |  | 11.0399 | 0.65721 |  | 190 | 0.00022852 | 9526 | 0.071638 | 4811 | 1.5995e-05 | 10498
GANSO 1103635704 | GANSO 1103 | 254541103 |  | 0.195 | 0 |  | 3.5 | 0.0002066 | 9939 | 0.0774 | 3397 | 1.5991e-05 | 10499
LLAGAS 2106XR146 | LLAGAS 2106 | 83182106 |  | 15.6387 | 0.80955 |  | 329 | 0.00023404 | 9406 | 0.068707 | 5242 | 1.5987e-05 | 10500
CHARCA 11024769 | CHARCA 1102 | 254501102 |  | 3.3218 | 0.061009 |  | 58 | 0.00022214 | 9668 | 0.073564 | 4601 | 1.5985e-05 | 10501
SMYRNA 1102122328 | SMYRNA 1102 | 253551102 |  | 38.1529 | 0.60101 |  | 640.5 | 0.00021329 | 9814 | 0.073876 | 4566 | 1.5983e-05 | 10502
HAMMONDS 1104CB | HAMMONDS 1104 | 253401104 |  | 4.6677 | 0.166 |  | 79.5 | 0.00020707 | 9929 | 0.077202 | 3592 | 1.5972e-05 | 10503
GANSO 110454276 | GANSO 1104 | 254541104 |  | 6.7278 | 0.16899 |  | 111.5 | 0.00020667 | 9937 | 0.077259 | 3531 | 1.597e-05 | 10504
DELEVAN 1101CB | DELEVAN 1101 | 69551101 |  | 0.37153 | 0 |  | 1.6667 | 0.00023791 | 9324 | 0.067094 | 5906 | 1.5962e-05 | 10505
CAL WATER 1103CB | CAL WATER 1103 | 255451103 |  | 4.4785 | 0.068282 |  | 74 | 0.00023686 | 9343 | 0.067371 | 5687 | 1.596e-05 | 10506
MIDDLE RIVER 110292188 | MIDDLE RIVER 1102 | 162091102 |  | 7.3999 | 0.24847 |  | 150.5 | 0.00020918 | 9889 | 0.076286 | 4099 | 1.5949e-05 | 10507
COALINGA NO 1 11099210 | COALINGA NO 1 1109 | 252161109 |  | 2.7313 | 0.025024 |  | 44.5 | 0.00022905 | 9513 | 0.070042 | 5038 | 1.592e-05 | 10508
SMYRNA 1102CB | SMYRNA 1102 | 253551102 |  | 12.0164 | 0.13363 |  | 207.5333 | 0.00020613 | 9944 | 0.077224 | 3562 | 1.5914e-05 | 10509
LINDEN 110111944 | LINDEN 1101 | 162071101 |  | 22.8481 | 1.7503 |  | 404.5 | 0.00020553 | 9952 | 0.0774 | 3397 | 1.5908e-05 | 10510
PLAINFIELD 110512792 | PLAINFIELD 1105 | 63441105 |  | 18.7449 | 0.40261 |  | 308.8333 | 0.00020551 | 9953 | 0.077374 | 3401 | 1.5894e-05 | 10511
SCHINDLER 1110190384 | SCHINDLER 1110 | 252891110 |  | 1.2226 | 0.033451 |  | 21.5 | 0.00021312 | 9821 | 0.075137 | 4396 | 1.5882e-05 | 10512
COTTLE 17089860 | COTTLE 1708 | 163711708 |  | 22.6434 | 0.74149 |  | 404 | 0.00021048 | 9868 | 0.075012 | 4412 | 1.5879e-05 | 10513
SANTA MARIA 1112M148 | SANTA MARIA 1112 | 182671112 |  | 1.4077 | 0.05063 |  | 23.5 | 0.00023543 | 9380 | 0.067443 | 5643 | 1.5876e-05 | 10514
EIGHT MILE 210614839 | EIGHT MILE 2106 | 163912106 |  | 3.4569 | 0.11673 |  | 64.5 | 0.00020565 | 9950 | 0.077211 | 3581 | 1.5858e-05 | 10515
GRAND ISLAND 222418332 | GRAND ISLAND 2224 | 62462224 |  | 16.1233 | 0.26077 |  | 302.5 | 0.00020833 | 9904 | 0.076641 | 3963 | 1.5852e-05 | 10516
CHOLAME 210249414 | CHOLAME 2102 | 182562102 |  | 5.8367 | 0.074921 |  | 96.5 | 0.00021791 | 9734 | 0.073143 | 4650 | 1.5845e-05 | 10517
MORGAN HILL 2105XR312 | MORGAN HILL 2105 | 83242105 |  | 3.6484 | 0.38945 |  | 69.5 | 0.00021735 | 9745 | 0.084298 | 3375 | 1.584e-05 | 10518
DIVIDE 1101CB | DIVIDE 1101 | 182571101 |  | 2.5534 | 0 |  | 42.0833 | 0.00023547 | 9379 | 0.067213 | 5795 | 1.5837e-05 | 10519
WATERLOO 11011375 | WATERLOO 1101 | 163151101 |  | 6.6986 | 0.63922 |  | 116.5 | 0.000204 | 9976 | 0.0774 | 3397 | 1.5789e-05 | 10520
CHOLAME 2102X24 | CHOLAME 2102 | 182562102 |  | 12.0962 | 0.083812 |  | 223.5 | 0.00023337 | 9421 | 0.067558 | 5569 | 1.5789e-05 | 10521
STONE CORRAL 1110CB | STONE CORRAL 1110 | 252921110 |  | 7.0859 | 0.94329 |  | 121 | 0.00022989 | 9490 | 0.069235 | 5161 | 1.5782e-05 | 10522
COLUMBUS 11054055 | COLUMBUS 1105 | 253951105 |  | 2.1535 | 0.0023304 |  | 37.5 | 0.0002354 | 9381 | 0.067028 | 5989 | 1.5781e-05 | 10523
LOS OSITOS 21027592 | LOS OSITOS 2102 | 182082102 |  | 24.3236 | 0.97184 |  | 487.8333 | 0.00023392 | 9413 | 0.067362 | 5694 | 1.5779e-05 | 10524
WILSON 110348236 | WILSON 1103 | 254301103 |  | 36.1427 | 1.3984 |  | 650.8333 | 0.00022206 | 9670 | 0.07122 | 4867 | 1.5776e-05 | 10525
BUTTE 1107551918 | BUTTE 1107 | 103081107 |  | 12.4934 | 0.90645 |  | 243.5 | 0.00022714 | 9560 | 0.070694 | 4934 | 1.5775e-05 | 10526
TUPMAN 11064890 | TUPMAN 1106 | 254561106 |  | 3.2452 | 0 |  | 52.5 | 0.00020377 | 9985 | 0.0774 | 3397 | 1.5772e-05 | 10527
STONE CORRAL 11087592F | STONE CORRAL 1108 | 252921108 |  | 6.4275 | 1.1107 |  | 123.5 | 0.00022932 | 9506 | 0.068828 | 5218 | 1.5769e-05 | 10528
TUPMAN 110375380 | TUPMAN 1103 | 254561103 |  | 8.1097 | 0.22637 |  | 136 | 0.00020403 | 9975 | 0.077221 | 3569 | 1.5764e-05 | 10529
HOLLISTER 21044782 | HOLLISTER 2104 | 182492104 |  | 27.4647 | 2.8721 |  | 545.5 | 0.00023477 | 9393 | 0.067104 | 5896 | 1.5757e-05 | 10530
BERRENDA C 0401CB | BERRENDA C 0401 | 254480401 |  | 0.0029799 | 0 |  | 0.5 | 0.00023501 | 9388 | 0.067 | 6057 | 1.5746e-05 | 10531
CHARCA 11034333 | CHARCA 1103 | 254501103 |  | 5.8859 | 0.063424 |  | 99 | 0.0002069 | 9935 | 0.076504 | 4016 | 1.5744e-05 | 10532
TUPMAN 11064981 | TUPMAN 1106 | 254561106 |  | 16.8576 | 0.040094 |  | 278.3333 | 0.00020565 | 9947 | 0.077054 | 3730 | 1.5743e-05 | 10533
EL CAPITAN 110354922 | EL CAPITAN 1103 | 253881103 |  | 0.036183 | 0 |  | 2 | 0.00020323 | 9993 | 0.0774 | 3397 | 1.573e-05 | 10534
EDENVALE 210589634 | EDENVALE 2105 | 82952105 |  | 2.3026 | 0.021631 |  | 47 | 0.00023477 | 9394 | 0.067 | 6057 | 1.5729e-05 | 10535
LINDEN 11042456 | LINDEN 1104 | 162071104 |  | 28.9137 | 2.5901 |  | 508 | 0.00020981 | 9876 | 0.073917 | 4564 | 1.5721e-05 | 10536
CORNING 11041706 | CORNING 1104 | 103331104 |  | 32.5799 | 2.5886 |  | 553.5 | 0.00023252 | 9433 | 0.067663 | 5523 | 1.5713e-05 | 10537
EL NIDO 1102840410 | EL NIDO 1102 | 252451102 |  | 12.4075 | 0.27786 |  | 214 | 0.00020259 | 10002 | 0.0774 | 3397 | 1.568e-05 | 10538
HOLLISTER 210228421 | HOLLISTER 2102 | 182492102 |  | 1.2056 | 0.053432 |  | 26.5 | 0.00023123 | 9457 | 0.06857 | 5267 | 1.5679e-05 | 10539
LOGAN CREEK 21022428 | LOGAN CREEK 2102 | 103142102 |  | 41.2594 | 1.2633 |  | 731.5 | 0.00022394 | 9627 | 0.069829 | 5067 | 1.567e-05 | 10540
PRUNEDALE 110725695 | PRUNEDALE 1107 | 182961107 |  | 2.3359 | 0.1457 |  | 48.5 | 0.00023385 | 9414 | 0.067 | 6057 | 1.5668e-05 | 10541
SANTA MARIA 1112M74 | SANTA MARIA 1112 | 182671112 |  | 0.23721 | 0 |  | 4.5 | 0.00023345 | 9418 | 0.067 | 6057 | 1.5641e-05 | 10542
MC ARTHUR 110138998 | MC ARTHUR 1101 | 103491101 | TRUE | 5.8855 | 0.49678 | 0.45139 | 106.5 | 0.00018092 | 10342 | 0.092283 | 3335 | 1.564e-05 | 10543
TEMPLETON 2109R74 | TEMPLETON 2109 | 183052109 |  | 4.9338 | 0.028832 |  | 82 | 0.00023339 | 9420 | 0.067 | 6057 | 1.5637e-05 | 10544
ANGIOLA 11038680 | ANGIOLA 1103 | 252151103 |  | 10.2492 | 0.026656 |  | 165 | 0.00020387 | 9982 | 0.076263 | 4106 | 1.5633e-05 | 10545
EL CAPITAN 1103182416 | EL CAPITAN 1103 | 253881103 |  | 3.8709 | 0.12765 |  | 65.5 | 0.00020191 | 10013 | 0.0774 | 3397 | 1.5628e-05 | 10546
STONE CORRAL 111048350 | STONE CORRAL 1110 | 252921110 |  | 5.9845 | 0.57959 |  | 109 | 0.00021753 | 9741 | 0.072915 | 4670 | 1.5615e-05 | 10547
PLEASANT GROVE 21106128 | PLEASANT GROVE 2110 | 152442110 |  | 12.7838 | 0.47816 |  | 211.5 | 0.00023184 | 9445 | 0.067494 | 5605 | 1.561e-05 | 10548
STOREY 1108191286 | STOREY 1108 | 254611108 |  | 7.0254 | 0.71834 |  | 115.5 | 0.00020167 | 10015 | 0.0774 | 3397 | 1.561e-05 | 10549
ARBUCKLE 11044508 | ARBUCKLE 1104 | 62081104 |  | 50.627 | 2.3889 |  | 857.5 | 0.00022777 | 9542 | 0.069128 | 5173 | 1.5607e-05 | 10550
EL CAPITAN 110311820 | EL CAPITAN 1103 | 253881103 |  | 8.3992 | 0.79597 |  | 149.5 | 0.00021482 | 9776 | 0.07243 | 4723 | 1.5597e-05 | 10551
SAN ARDO 11027066 | SAN ARDO 1102 | 182191102 |  | 6.0458 | 0.079914 |  | 120.5 | 0.00023278 | 9431 | 0.067 | 6057 | 1.5596e-05 | 10552
MADISON 21019512 | MADISON 2101 | 63172101 |  | 12.0043 | 0.326 |  | 205 | 0.00022575 | 9589 | 0.069387 | 5129 | 1.5594e-05 | 10553
FAMOSO 1102CB | FAMOSO 1102 | 252461102 |  | 27.3034 | 0.57439 |  | 441.5 | 0.00020199 | 10011 | 0.077226 | 3557 | 1.5573e-05 | 10554
DUNNIGAN 11014706 | DUNNIGAN 1101 | 63811101 |  | 9.6044 | 0.056132 |  | 172 | 0.00022601 | 9583 | 0.069001 | 5189 | 1.5571e-05 | 10555
ZAMORA 110723472 | ZAMORA 1107 | 63191107 |  | 17.8519 | 0.59834 |  | 312.5 | 0.00022546 | 9599 | 0.069362 | 5136 | 1.5568e-05 | 10556
KERMAN 110447386 | KERMAN 1104 | 252711104 |  | 18.5886 | 0.60698 |  | 309.5 | 0.00020323 | 9994 | 0.07672 | 3922 | 1.5565e-05 | 10557
LOCKEFORD 21024484 | LOCKEFORD 2102 | 163682102 |  | 0.022727 | 0 |  | 0.33333 | 0.00020085 | 10028 | 0.0774 | 3396 | 1.5546e-05 | 10558
ORO LOMA 11089770 | ORO LOMA 1108 | 255371108 |  | 19.3093 | 0.17358 |  | 328 | 0.00020204 | 10010 | 0.07689 | 3837 | 1.552e-05 | 10559
ELK HILLS 11044306 | ELK HILLS 1104 | 252441104 |  | 23.3178 | 4.5412 |  | 421.3333 | 0.00023065 | 9472 | 0.067335 | 5711 | 1.5513e-05 | 10560
PANOCHE 11023460 | PANOCHE 1102 | 253671102 |  | 5.8899 | 0.078546 |  | 97 | 0.00021211 | 9840 | 0.072736 | 4690 | 1.5512e-05 | 10561
DAIRYLAND 111254694 | DAIRYLAND 1112 | 252421112 |  | 23.3523 | 0.43973 |  | 398.5 | 0.00020082 | 10029 | 0.077319 | 3448 | 1.5508e-05 | 10562
STOREY 1108239026 | STOREY 1108 | 254611108 |  | 0.22737 | 0 |  | 4.5 | 0.0002003 | 10037 | 0.0774 | 3397 | 1.5503e-05 | 10563
SAN MIGUEL 1104R58 | SAN MIGUEL 1104 | 182661104 | TRUE | 12.0104 | 0.59792 | 0.58898 | 217 | 0.00016319 | 10558 | 0.11184 | 3289 | 1.5499e-05 | 10564
PANOCHE 1101CB | PANOCHE 1101 | 253671101 |  | 8.6997 | 0.03 |  | 139.8333 | 0.00020529 | 9958 | 0.075639 | 4302 | 1.5494e-05 | 10565
WILSON 1102332156 | WILSON 1102 | 254301102 |  | 15.1562 | 0.46292 |  | 259 | 0.0002052 | 9960 | 0.074067 | 4546 | 1.5477e-05 | 10566
ATWATER 11027160 | ATWATER 1102 | 253611102 |  | 23.1773 | 0.78709 |  | 400 | 0.00020018 | 10039 | 0.0773 | 3472 | 1.5477e-05 | 10567
COTTLE 17033292 | COTTLE 1703 | 163711703 |  | 24.8614 | 0.77316 |  | 416 | 0.00020065 | 10032 | 0.076924 | 3813 | 1.5468e-05 | 10568
PANOCHE 11023700 | PANOCHE 1102 | 253671102 |  | 7.8898 | 0.052414 |  | 133 | 0.00020724 | 9924 | 0.074663 | 4464 | 1.5459e-05 | 10569
LOGAN CREEK 210237316 | LOGAN CREEK 2102 | 103142102 |  | 13.0235 | 0.14105 |  | 224 | 0.00022612 | 9579 | 0.069008 | 5188 | 1.5452e-05 | 10570
CORCORAN 11048150 | CORCORAN 1104 | 252171104 |  | 7.2644 | 0.21919 |  | 123 | 0.00019958 | 10048 | 0.0774 | 3397 | 1.5448e-05 | 10571
TUDOR 11011236 | TUDOR 1101 | 153711101 |  | 8.818 | 0.57513 |  | 153 | 0.00019938 | 10053 | 0.0774 | 3397 | 1.5432e-05 | 10572
GANSO 1103CB | GANSO 1103 | 254541103 |  | 19.1836 | 0.33828 |  | 324.5 | 0.00019986 | 10043 | 0.077204 | 3591 | 1.543e-05 | 10573
NORCO 1101309854 | NORCO 1101 | 254691101 |  | 5.332 | 0.031214 |  | 90 | 0.00020517 | 9961 | 0.075549 | 4329 | 1.5426e-05 | 10574
REEDLEY 11127919F | REEDLEY 1112 | 252341112 |  | 6.1223 | 1.0298 |  | 108.5 | 0.00022548 | 9598 | 0.068917 | 5204 | 1.5421e-05 | 10575
PASO ROBLES 1103P08 | PASO ROBLES 1103 | 182611103 |  | 2.6741 | 0.056521 |  | 47 | 0.00023012 | 9485 | 0.067 | 6057 | 1.5418e-05 | 10576
STOREY 11095140 | STOREY 1109 | 254611109 |  | 23.4329 | 0.77826 |  | 395.5 | 0.00020293 | 9997 | 0.076416 | 4046 | 1.5406e-05 | 10577
TYLER 11041522 | TYLER 1104 | 103571104 |  | 9.8772 | 1.05 |  | 190 | 0.00022848 | 9528 | 0.067404 | 5663 | 1.5394e-05 | 10578
ARBUCKLE 110195678 | ARBUCKLE 1101 | 62081101 |  | 7.6087 | 0.41907 |  | 131 | 0.00022428 | 9620 | 0.069382 | 5133 | 1.5393e-05 | 10579
DELEVAN 1102CB | DELEVAN 1102 | 69551102 |  | 0.41772 | 0 |  | 2.1667 | 0.00022906 | 9512 | 0.067089 | 5912 | 1.5367e-05 | 10580
WHEELER RIDGE 110170228 | WHEELER RIDGE 1101 | 253481101 |  | 6.3059 | 0.17168 |  | 106.5 | 0.00021173 | 9849 | 0.072738 | 4689 | 1.5363e-05 | 10581
ARBUCKLE 1104499738 | ARBUCKLE 1104 | 62081104 |  | 5.961 | 0.29448 |  | 103 | 0.0002026 | 10001 | 0.076517 | 4009 | 1.5359e-05 | 10582
COTATI 1103310 | COTATI 1103 | 42271103 |  | 11.9107 | 0.34465 |  | 227 | 0.00017443 | 10431 | 0.087439 | 3355 | 1.5356e-05 | 10583
KINGSBURG 1110CB | KINGSBURG 1110 | 252241110 |  | 4.6869 | 0.39207 |  | 69.7833 | 0.00019818 | 10074 | 0.0774 | 3397 | 1.5339e-05 | 10584
BUENA VISTA 1102555392 | BUENA VISTA 1102 | 182261102 |  | 2.3516 | 0.13531 |  | 52.5 | 0.00022885 | 9516 | 0.067006 | 6026 | 1.5334e-05 | 10585
CHARCA 11034618 | CHARCA 1103 | 254501103 |  | 17.4992 | 0.18254 |  | 288.5 | 0.00019984 | 10044 | 0.07702 | 3750 | 1.5322e-05 | 10586
PIPER BANK 0401CB | PIPER BANK 0401 | 18120401 |  | 1.5609 | 0.39934 |  | 21.8333 | 0.00020014 | 10040 | 0.076843 | 3861 | 1.5319e-05 | 10587
GERBER 11023771 | GERBER 1102 | 103391102 |  | 11.1815 | 0.2417 |  | 207 | 0.00022598 | 9585 | 0.06769 | 5514 | 1.5309e-05 | 10588
HAMMONDS 1101CB | HAMMONDS 1101 | 253401101 |  | 2.9129 | 0.041812 |  | 46 | 0.00020295 | 9996 | 0.075817 | 4259 | 1.5304e-05 | 10589
SANTA YNEZ 1104564710 | SANTA YNEZ 1104 | 182721104 | TRUE | 0.3179 | 0.16703 | 0.12942 | 9.5 | 0.0002284 | 9530 | 0.067 | 6057 | 1.5303e-05 | 10590
COTTLE 170194082 | COTTLE 1701 | 163711701 |  | 15.977 | 0.75652 |  | 284.5 | 0.00020955 | 9880 | 0.07279 | 4686 | 1.53e-05 | 10591
WEEDPATCH 110613390 | WEEDPATCH 1106 | 252971106 |  | 5.3703 | 0.027646 |  | 91.5 | 0.00019763 | 10080 | 0.0774 | 3397 | 1.5297e-05 | 10592
SMYRNA 1101CB | SMYRNA 1101 | 253551101 |  | 25.0658 | 0.7063 |  | 423.5333 | 0.00020728 | 9923 | 0.073455 | 4617 | 1.5292e-05 | 10593
WESTLEY 11038640 | WESTLEY 1103 | 162671103 |  | 19.6032 | 0.72261 |  | 401.5 | 0.00019836 | 10072 | 0.077098 | 3693 | 1.5279e-05 | 10594
GOOSE LAKE 11063290 | GOOSE LAKE 1106 | 254201106 |  | 16.1596 | 0.18827 |  | 278.5 | 0.00020331 | 9991 | 0.075581 | 4319 | 1.5279e-05 | 10595
DEVILS DEN 1102460850 | DEVILS DEN 1102 | 253451102 |  | 13.7612 | 0.079497 |  | 228.5 | 0.00021299 | 9825 | 0.072416 | 4727 | 1.5275e-05 | 10596
CORCORAN 111677788 | CORCORAN 1116 | 252171116 |  | 17.7639 | 0.24806 |  | 290 | 0.00019899 | 10062 | 0.076609 | 3980 | 1.5268e-05 | 10597
RIVERBANK 171499660 | RIVERBANK 1714 | 163191714 |  | 4.1853 | 0.32278 |  | 74 | 0.00019921 | 10056 | 0.076907 | 3826 | 1.5266e-05 | 10598
ANTELOPE 1101CB | ANTELOPE 1101 | 252021101 |  | 6.1788 | 0.28027 |  | 106.5 | 0.00020818 | 9909 | 0.074183 | 4528 | 1.5261e-05 | 10599
EL PECO 110511700 | EL PECO 1105 | 253981105 |  | 31.7675 | 0.5987 |  | 534 | 0.00019865 | 10067 | 0.076666 | 3950 | 1.5227e-05 | 10600
ORO LOMA 1116CB | ORO LOMA 1116 | 255371116 |  | 8.8939 | 0.40936 |  | 144.7 | 0.00019927 | 10054 | 0.076836 | 3867 | 1.5219e-05 | 10601
PANOCHE 110110480 | PANOCHE 1101 | 253671101 |  | 0.031435 | 0 |  | 1.5 | 0.00022691 | 9567 | 0.067 | 6057 | 1.5203e-05 | 10602
ORO LOMA 111711020 | ORO LOMA 1117 | 255371117 |  | 16.4964 | 0.61224 |  | 296 | 0.00019941 | 10051 | 0.075903 | 4231 | 1.5201e-05 | 10603
REEDLEY 11127917F | REEDLEY 1112 | 252341112 |  | 3.6824 | 0.96968 |  | 76.5 | 0.00022362 | 9634 | 0.068495 | 5288 | 1.52e-05 | 10604
PLAINFIELD 11019323 | PLAINFIELD 1101 | 63441101 |  | 1.9178 | 0.074248 |  | 31.5 | 0.00020229 | 10007 | 0.075356 | 4354 | 1.5198e-05 | 10605
MC MULLIN 11056720 | MC MULLIN 1105 | 254411105 |  | 9.5301 | 0.17347 |  | 160.8333 | 0.00019633 | 10104 | 0.0774 | 3397 | 1.5196e-05 | 10606
TULARE LAKE 1104884818 | TULARE LAKE 1104 | 252951104 |  | 3.8201 | 0 |  | 65.5 | 0.00022665 | 9571 | 0.067043 | 5956 | 1.5194e-05 | 10607
LINDEN 11033042 | LINDEN 1103 | 162071103 |  | 14.9364 | 0.94765 |  | 257 | 0.0001963 | 10110 | 0.0774 | 3397 | 1.5193e-05 | 10608
CORCORAN 1116472331 | CORCORAN 1116 | 252171116 |  | 20.1536 | 0.65481 |  | 341.5 | 0.00019879 | 10064 | 0.076974 | 3781 | 1.5184e-05 | 10609
LINCOLN 11042308 | LINCOLN 1104 | 153701104 |  | 17.0611 | 0.86967 |  | 288.5 | 0.00022652 | 9573 | 0.067 | 6057 | 1.5177e-05 | 10610
KINGSBURG 11117090 | KINGSBURG 1111 | 252241111 |  | 13.4715 | 0.94837 |  | 228.5 | 0.00019743 | 10082 | 0.077225 | 3561 | 1.5173e-05 | 10611
LOS COCHES 110275272 | LOS COCHES 1102 | 182151102 |  | 12.514 | 0.27583 |  | 258.5 | 0.00022231 | 9664 | 0.068278 | 5338 | 1.5158e-05 | 10612
RUSSELL (SMUD) 2101CB | RUSSELL (SMUD) 2101 | 63142101 |  | 0.13516 | 0 |  | 2.3333 | 0.00020054 | 10034 | 0.075914 | 4223 | 1.5157e-05 | 10613
PASO ROBLES 1106CB | PASO ROBLES 1106 | 182611106 |  | 5.469 | 0.27798 |  | 104.5 | 0.00023039 | 9478 | 0.066633 | 6155 | 1.5156e-05 | 10614
GOOSE LAKE 1103CB | GOOSE LAKE 1103 | 254201103 |  | 30.8204 | 0.62298 |  | 517.8333 | 0.000199 | 10061 | 0.076036 | 4188 | 1.5156e-05 | 10615
COLUSA 11013557 | COLUSA 1101 | 62021101 |  | 2.636 | 0.095185 |  | 53.5 | 0.00019579 | 10117 | 0.0774 | 3397 | 1.5154e-05 | 10616
SAN ARDO 110294020 | SAN ARDO 1102 | 182191102 |  | 5.8045 | 0.28645 |  | 125 | 0.00022595 | 9586 | 0.067 | 6057 | 1.5138e-05 | 10617
WOODLAND 11139422 | WOODLAND 1113 | 62031113 |  | 11.0422 | 0.21368 |  | 203.5 | 0.00019542 | 10123 | 0.0774 | 3397 | 1.5125e-05 | 10618
SAN ARDO 110291894 | SAN ARDO 1102 | 182191102 |  | 12.1331 | 1.6144 |  | 240 | 0.00022409 | 9626 | 0.067789 | 5480 | 1.5122e-05 | 10619
LINCOLN 11051276 | LINCOLN 1105 | 153701105 |  | 7.4425 | 0.55061 |  | 129 | 0.00022237 | 9662 | 0.068048 | 5395 | 1.5121e-05 | 10620
CARUTHERS 11056300 | CARUTHERS 1105 | 252371105 |  | 5.7556 | 0.15207 |  | 97 | 0.00019527 | 10126 | 0.0774 | 3397 | 1.5114e-05 | 10621
HOLLISTER 210542224 | HOLLISTER 2105 | 182492105 |  | 5.6979 | 0.66436 |  | 115.8333 | 0.00020878 | 9899 | 0.072672 | 4699 | 1.5113e-05 | 10622
NEWHALL 1111408296 | NEWHALL 1111 | 254461111 |  | 34.0993 | 0.52944 |  | 591 | 0.00019544 | 10122 | 0.077291 | 3486 | 1.5102e-05 | 10623
BUTTE 11072434 | BUTTE 1107 | 103081107 |  | 10.8265 | 0.56119 |  | 184.5 | 0.0002142 | 9795 | 0.071904 | 4781 | 1.5096e-05 | 10624
TUPMAN 1105CB | TUPMAN 1105 | 254561105 |  | 8.3906 | 0.10844 |  | 133.0833 | 0.00019498 | 10131 | 0.0774 | 3396 | 1.5092e-05 | 10625
VALLEY HOME 17031558 | VALLEY HOME 1703 | 162981703 |  | 37.8771 | 1.3559 |  | 660.5 | 0.00021219 | 9838 | 0.070383 | 4962 | 1.5089e-05 | 10626
ANGIOLA 11038530 | ANGIOLA 1103 | 252151103 |  | 8.285 | 0.28234 |  | 144 | 0.00019582 | 10116 | 0.077122 | 3673 | 1.5088e-05 | 10627
DIXON 11038202 | DIXON 1103 | 62061103 |  | 25.1361 | 1.4367 |  | 430.5 | 0.00019564 | 10119 | 0.077137 | 3659 | 1.5079e-05 | 10628
FOOTHILL 1101645910 | FOOTHILL 1101 | 182951101 | TRUE | 2.663 | 0.064183 | 0.13126 | 48.5 | 0.00022504 | 9606 | 0.067 | 6057 | 1.5078e-05 | 10629
CORTINA 110130262 | CORTINA 1101 | 63121101 |  | 20.5322 | 0.43655 |  | 345.5 | 0.00020831 | 9907 | 0.073276 | 4638 | 1.5076e-05 | 10630
VINA 11011570 | VINA 1101 | 103581101 |  | 21.0422 | 0.60755 |  | 400.3333 | 0.00022242 | 9659 | 0.067762 | 5489 | 1.5053e-05 | 10631
COLUMBUS 11093953 | COLUMBUS 1109 | 253951109 |  | 0.0078383 | 0.050331 |  | 4.5 | 0.00025284 | 9023 | 0.063885 | 6559 | 1.504e-05 | 10632
DAIRYLAND 111168650 | DAIRYLAND 1111 | 252421111 |  | 5.1151 | 0.22695 |  | 80.3333 | 0.00019422 | 10142 | 0.0774 | 3396 | 1.5032e-05 | 10633
WYANDOTTE 11021502 | WYANDOTTE 1102 | 102911102 |  | 15.0929 | 0.36428 |  | 288.5 | 0.00022363 | 9633 | 0.067438 | 5646 | 1.5031e-05 | 10634
STOREY 11086460 | STOREY 1108 | 254611108 |  | 19.7713 | 1.7685 |  | 331.5 | 0.00022242 | 9660 | 0.067361 | 5697 | 1.5025e-05 | 10635
CATLETT 110237358 | CATLETT 1102 | 153761102 |  | 21.7698 | 1.453 |  | 367.3333 | 0.00022184 | 9674 | 0.067882 | 5445 | 1.5011e-05 | 10636
NEW HOPE 11021286 | NEW HOPE 1102 | 162081102 |  | 8.7671 | 0.35413 |  | 152.5 | 0.00019479 | 10135 | 0.077081 | 3708 | 1.5006e-05 | 10637
KERN OIL 11043843 | KERN OIL 1104 | 252721104 |  | 8.1173 | 0 |  | 131.3333 | 0.00021254 | 9834 | 0.070408 | 4959 | 1.4989e-05 | 10638
MADISON 1105961978 | MADISON 1105 | 63171105 |  | 7.477 | 0.10767 |  | 128.5 | 0.00022088 | 9686 | 0.068342 | 5319 | 1.4956e-05 | 10639
SEMITROPIC 11064553 | SEMITROPIC 1106 | 252901106 |  | 20.9075 | 0.76247 |  | 358 | 0.0001932 | 10161 | 0.0774 | 3397 | 1.4954e-05 | 10640
MC ARTHUR 110153120 | MC ARTHUR 1101 | 103491101 | TRUE | 7.9999 | 0.77185 | 0.10137 | 136 | 0.00021302 | 9824 | 0.074945 | 4422 | 1.4954e-05 | 10641
HAMMONDS 11043660 | HAMMONDS 1104 | 253401104 |  | 24.7525 | 0.64413 |  | 406.5 | 0.00019363 | 10154 | 0.07728 | 3504 | 1.4949e-05 | 10642
KING CITY 110699446 | KING CITY 1106 | 182031106 |  | 4.9192 | 0.27374 |  | 98 | 0.00022311 | 9641 | 0.067 | 6057 | 1.4948e-05 | 10643
GIFFEN 11029140 | GIFFEN 1102 | 253151102 |  | 17.5981 | 0.079119 |  | 291 | 0.00020779 | 9916 | 0.072357 | 4738 | 1.4939e-05 | 10644
GANSO 11033217 | GANSO 1103 | 254541103 |  | 13.0155 | 0.33114 |  | 216 | 0.00019285 | 10168 | 0.0774 | 3397 | 1.4926e-05 | 10645
EAST MARYSVILLE 1108900690 | EAST MARYSVILLE 1108 | 152331108 |  | 33.7837 | 1.0241 |  | 606.5 | 0.00021708 | 9748 | 0.068552 | 5274 | 1.492e-05 | 10646
WHEATLAND 11041348 | WHEATLAND 1104 | 152811104 |  | 9.4419 | 0.5351 |  | 170.5 | 0.00022074 | 9687 | 0.067488 | 5611 | 1.4916e-05 | 10647
RICE 11033106 | RICE 1103 | 62831103 |  | 35.4256 | 1.2341 |  | 606.5 | 0.00019338 | 10160 | 0.077204 | 3590 | 1.4915e-05 | 10648
VINA 11012681 | VINA 1101 | 103581101 |  | 3.6944 | 0.029146 |  | 67.5 | 0.0002225 | 9658 | 0.067023 | 5997 | 1.4913e-05 | 10649
NEWBURG 11313446 | NEWBURG 1131 | 192151131 | TRUE | 8.3096 | 1.4173 | 0.075452 | 147.5 | 0.00022309 | 9643 | 0.066906 | 6088 | 1.4904e-05 | 10650
RUSSELL (SMUD) 210141212 | RUSSELL (SMUD) 2101 | 63142101 |  | 4.8998 | 0 |  | 69.6667 | 0.00022032 | 9693 | 0.067871 | 5451 | 1.4902e-05 | 10651
KETTLEMAN HILLS 11019180 | KETTLEMAN HILLS 1101 | 252731101 |  | 10.2606 | 0 |  | 169 | 0.00021835 | 9726 | 0.06822 | 5356 | 1.4891e-05 | 10652
HAMMONDS 11043670 | HAMMONDS 1104 | 253401104 |  | 35.2868 | 0.86461 |  | 582.5 | 0.00019511 | 10129 | 0.07675 | 3909 | 1.4873e-05 | 10653
KING CITY 11047092 | KING CITY 1104 | 182031104 |  | 13.5683 | 0.71821 |  | 270.5 | 0.00022037 | 9692 | 0.067534 | 5582 | 1.4868e-05 | 10654
BLACKWELL 11024745 | BLACKWELL 1102 | 254681102 |  | 8.9146 | 0 |  | 144.5 | 0.00020692 | 9933 | 0.073085 | 4654 | 1.4865e-05 | 10655
RAINBOW 1106R1500 | RAINBOW 1106 | 254441106 |  | 15.7221 | 2.2815 |  | 280 | 0.00021062 | 9867 | 0.071626 | 4812 | 1.4864e-05 | 10656
SANTA NELLA 11013680 | SANTA NELLA 1101 | 254051101 |  | 8.0368 | 0.095134 |  | 142.5 | 0.00021807 | 9728 | 0.068137 | 5373 | 1.4859e-05 | 10657
PLAINFIELD 1105907648 | PLAINFIELD 1105 | 63441105 |  | 9.2779 | 0.36749 |  | 161 | 0.00019368 | 10150 | 0.076853 | 3856 | 1.4849e-05 | 10658
GUERNSEY 1106184691 | GUERNSEY 1106 | 252661106 |  | 11.4924 | 0.073964 |  | 180.5 | 0.00019173 | 10184 | 0.0774 | 3397 | 1.484e-05 | 10659
COTTLE 1701246168 | COTTLE 1701 | 163711701 |  | 19.3961 | 1.0814 |  | 346 | 0.0002207 | 9688 | 0.067417 | 5654 | 1.4838e-05 | 10660
KING CITY 11067032 | KING CITY 1106 | 182031106 |  | 26.942 | 0.89755 |  | 539.5 | 0.00022133 | 9681 | 0.067038 | 5964 | 1.4833e-05 | 10661
COPPERMINE 110438474 | COPPERMINE 1104 | 252411104 |  | 13.9941 | 0.7333 |  | 239 | 0.00020565 | 9948 | 0.072097 | 4767 | 1.4833e-05 | 10662
CHOLAME 2102X20 | CHOLAME 2102 | 182562102 |  | 11.364 | 0.52059 |  | 215 | 0.00021467 | 9781 | 0.069599 | 5101 | 1.481e-05 | 10663
WYANDOTTE 1106304014 | WYANDOTTE 1106 | 102911106 |  | 3.8011 | 0.36288 |  | 69.5 | 0.00021764 | 9738 | 0.067898 | 5438 | 1.4797e-05 | 10664
LE GRAND 1106761734 | LE GRAND 1106 | 255361106 |  | 2.7546 | 0.054917 |  | 44 | 0.00019115 | 10194 | 0.0774 | 3397 | 1.4795e-05 | 10665
SAN ARDO 11027000 | SAN ARDO 1102 | 182191102 |  | 10.5461 | 0.87123 |  | 219 | 0.00021959 | 9710 | 0.067378 | 5683 | 1.4794e-05 | 10666
NEWHALL 11119800 | NEWHALL 1111 | 254461111 |  | 17.139 | 0.76674 |  | 307 | 0.00019131 | 10192 | 0.077321 | 3442 | 1.4793e-05 | 10667
SMYRNA 110578536 | SMYRNA 1105 | 253551105 |  | 6.4305 | 0.13612 |  | 110.5 | 0.00019111 | 10195 | 0.0774 | 3397 | 1.4792e-05 | 10668
GRAND ISLAND 222418122 | GRAND ISLAND 2224 | 62462224 |  | 9.5959 | 0.48591 |  | 181 | 0.00019094 | 10197 | 0.0774 | 3397 | 1.4778e-05 | 10669
MOLINO 110313219 | MOLINO 1103 | 42571103 |  | 1.8564 | 0.22948 |  | 30.5 | 0.00021877 | 9723 | 0.067341 | 5708 | 1.4768e-05 | 10670
COALINGA NO 2 11069150 | COALINGA NO 2 1106 | 252381106 |  | 7.9985 | 0.23263 |  | 138 | 0.00022009 | 9696 | 0.06703 | 5986 | 1.4752e-05 | 10671
TULARE LAKE 110693686 | TULARE LAKE 1106 | 252951106 |  | 1.2921 | 0 |  | 21.5 | 0.00020922 | 9884 | 0.070771 | 4923 | 1.4726e-05 | 10672
GUERNSEY 1101491366 | GUERNSEY 1101 | 252661101 |  | 0.95473 | 0 |  | 14 | 0.00019012 | 10212 | 0.0774 | 3397 | 1.4715e-05 | 10673
DAIRYLAND 11129830 | DAIRYLAND 1112 | 252421112 |  | 9.8578 | 0.20029 |  | 158.5 | 0.00019003 | 10213 | 0.0774 | 3397 | 1.4708e-05 | 10674
DEVILS DEN 1102CB | DEVILS DEN 1102 | 253451102 |  | 16.1759 | 0.2048 |  | 286 | 0.00021512 | 9773 | 0.068678 | 5246 | 1.4706e-05 | 10675
BIOLA 1103R2666 | BIOLA 1103 | 252211103 |  | 30.869 | 1.4232 |  | 518.5 | 0.00019443 | 10140 | 0.07607 | 4174 | 1.4692e-05 | 10676
CROWS LANDING 110164846 | CROWS LANDING 1101 | 163251101 |  | 9.3976 | 0.69665 |  | 167 | 0.00021005 | 9873 | 0.070569 | 4946 | 1.4687e-05 | 10677
CARBONA 110446431 | CARBONA 1104 | 163091104 |  | 11.9938 | 0.3933 |  | 210 | 0.00020866 | 9901 | 0.071346 | 4850 | 1.4656e-05 | 10678
WESTLEY 11039010 | WESTLEY 1103 | 162671103 |  | 18.1119 | 0.66966 |  | 325 | 0.00021316 | 9819 | 0.069243 | 5153 | 1.465e-05 | 10679
GUSTINE 11011524 | GUSTINE 1101 | 163111101 |  | 15.8415 | 0.50114 |  | 307.5 | 0.00019623 | 10112 | 0.075511 | 4337 | 1.464e-05 | 10680
GLENN 1101546764 | GLENN 1101 | 102601101 |  | 14.2132 | 0.98381 |  | 259.5 | 0.00021793 | 9732 | 0.067152 | 5850 | 1.4635e-05 | 10681
DUNNIGAN 110130004 | DUNNIGAN 1101 | 63811101 |  | 13.1062 | 0.19988 |  | 227.5 | 0.00018895 | 10226 | 0.0774 | 3397 | 1.4625e-05 | 10682
CAPAY 1102575698 | CAPAY 1102 | 102111102 |  | 2.959 | 0.15878 |  | 56 | 0.00020944 | 9882 | 0.069655 | 5090 | 1.4608e-05 | 10683
MC FARLAND 1104956589 | MC FARLAND 1104 | 253181104 |  | 1.5678 | 0.052009 |  | 27.5 | 0.00018854 | 10230 | 0.0774 | 3397 | 1.4593e-05 | 10684
CANTUA 1102CB | CANTUA 1102 | 253591102 |  | 16.0456 | 0.173 |  | 263.5 | 0.00021209 | 9841 | 0.068951 | 5200 | 1.4582e-05 | 10685
MARINA (F) 1101CB | MARINA (F) 1101 | 22781101 |  | 0.0037892 | 0.71129 |  | 17.3333 | 0.00027462 | 8538 | 0.053073 | 8250 | 1.4575e-05 | 10686
HONCUT 110137322 | HONCUT 1101 | 103211101 |  | 17.3651 | 1.643 |  | 332 | 0.00021277 | 9830 | 0.068442 | 5298 | 1.4559e-05 | 10687
ORO LOMA 11163983 | ORO LOMA 1116 | 255371116 |  | 4.5519 | 0.069653 |  | 81.5 | 0.00018847 | 10231 | 0.077251 | 3537 | 1.4556e-05 | 10688
MC FARLAND 1104950506 | MC FARLAND 1104 | 253181104 |  | 5.1305 | 0.024112 |  | 85 | 0.00019368 | 10149 | 0.075216 | 4383 | 1.4546e-05 | 10689
PASO ROBLES 110355374 | PASO ROBLES 1103 | 182611103 |  | 1.395 | 0.68188 |  | 29 | 0.00022548 | 9596 | 0.064526 | 6483 | 1.4537e-05 | 10690
PANOCHE 110211830 | PANOCHE 1102 | 253671102 |  | 7.2903 | 0.039078 |  | 121 | 0.00021128 | 9856 | 0.069516 | 5119 | 1.4532e-05 | 10691
REEDLEY 11067260 | REEDLEY 1106 | 252341106 |  | 17.0156 | 3.4154 |  | 309.5 | 0.00021389 | 9800 | 0.068126 | 5380 | 1.453e-05 | 10692
LIVINGSTON 110190010 | LIVINGSTON 1101 | 252261101 |  | 4.2533 | 0.21558 |  | 72 | 0.00018876 | 10228 | 0.077062 | 3724 | 1.4521e-05 | 10693
WYANDOTTE 11061512 | WYANDOTTE 1106 | 102911106 |  | 23.6696 | 1.7477 |  | 408 | 0.00021316 | 9818 | 0.068096 | 5386 | 1.4519e-05 | 10694
MC MULLIN 1106498152 | MC MULLIN 1106 | 254411106 |  | 0.021841 | 0 |  | 1.5 | 0.00018738 | 10241 | 0.0774 | 3397 | 1.4503e-05 | 10695
RIO BRAVO 11067273 | RIO BRAVO 1106 | 252861106 |  | 8.4776 | 0.98459 |  | 143.5 | 0.00018762 | 10238 | 0.077182 | 3609 | 1.4468e-05 | 10696
WILLIAMS 110230232 | WILLIAMS 1102 | 62051102 |  | 21.9354 | 0.9947 |  | 379.5 | 0.00020216 | 10009 | 0.072415 | 4728 | 1.4467e-05 | 10697
CORDELIA 110448536 | CORDELIA 1104 | 62701104 |  | 22.3002 | 0.56213 |  | 469.3333 | 0.00021463 | 9782 | 0.067388 | 5678 | 1.446e-05 | 10698
KERN OIL 11063301 | KERN OIL 1106 | 252721106 |  | 28.7048 | 0.98712 |  | 494 | 0.00021428 | 9792 | 0.067634 | 5535 | 1.4449e-05 | 10699
SMYRNA 1105488088 | SMYRNA 1105 | 253551105 |  | 2.1303 | 0.26632 |  | 36 | 0.00019153 | 10187 | 0.075612 | 4308 | 1.4402e-05 | 10700
LIVE OAK 11041300 | LIVE OAK 1104 | 153771104 |  | 35.0677 | 2.0069 |  | 633 | 0.00019924 | 10055 | 0.072243 | 4754 | 1.4381e-05 | 10701
COTATI 1103252 | COTATI 1103 | 42271103 |  | 5.9975 | 1.0056 |  | 109 | 0.00021411 | 9798 | 0.067132 | 5872 | 1.4374e-05 | 10702
FELLOWS 2104274456 | FELLOWS 2104 | 254242104 |  | 17.4702 | 0.02781 |  | 320 | 0.00020161 | 10017 | 0.071342 | 4851 | 1.4362e-05 | 10703
ANGIOLA 11038140 | ANGIOLA 1103 | 252151103 |  | 15.8656 | 0.093278 |  | 282 | 0.00019443 | 10139 | 0.074964 | 4419 | 1.4362e-05 | 10704
LIVINGSTON 110155936 | LIVINGSTON 1101 | 252261101 |  | 3.3982 | 0.076457 |  | 59.5 | 0.00018546 | 10268 | 0.0774 | 3397 | 1.4354e-05 | 10705
HONCUT 11026130 | HONCUT 1102 | 103211102 |  | 18.5499 | 0.53841 |  | 326 | 0.00021376 | 9804 | 0.067064 | 5931 | 1.4342e-05 | 10706
GLENN 110137496 | GLENN 1101 | 102601101 |  | 19.3032 | 0.7468 |  | 374.5 | 0.00021186 | 9846 | 0.067728 | 5501 | 1.4341e-05 | 10707
COTTLE 17028100 | COTTLE 1702 | 163711702 |  | 11.6441 | 0.41739 |  | 203.8333 | 0.00018862 | 10229 | 0.075115 | 4398 | 1.4339e-05 | 10708
SF J 0407CB | SF J 0407 | 22220407 |  | 0.002841 | 0.014686 |  | 1.5 | 0.00027008 | 8651 | 0.053073 | 8251 | 1.4334e-05 | 10709
CORDELIA 11048772 | CORDELIA 1104 | 62701104 |  | 26.901 | 1.0279 |  | 531 | 0.0002128 | 9828 | 0.067444 | 5641 | 1.4331e-05 | 10710
JACINTO 11012460 | JACINTO 1101 | 102851101 |  | 9.6852 | 0.38028 |  | 178.5 | 0.00020536 | 9956 | 0.070909 | 4904 | 1.4329e-05 | 10711
CHOWCHILLA 110483552 | CHOWCHILLA 1104 | 254101104 |  | 12.3502 | 0.46294 |  | 206.5 | 0.00018504 | 10276 | 0.0774 | 3397 | 1.4322e-05 | 10712
CARNERAS 11031584 | CARNERAS 1103 | 252321103 |  | 10.4212 | 0.061679 |  | 172.5 | 0.0002126 | 9831 | 0.067482 | 5613 | 1.4311e-05 | 10713
KINGSBURG 111629517 | KINGSBURG 1116 | 252241116 |  | 22.3402 | 0.80743 |  | 382.5 | 0.00018681 | 10248 | 0.076914 | 3818 | 1.4306e-05 | 10714
CHOWCHILLA 110286280 | CHOWCHILLA 1102 | 254101102 |  | 14.3687 | 0.3333 |  | 245.5 | 0.0001853 | 10270 | 0.077301 | 3471 | 1.4298e-05 | 10715
TWISSELMAN 21051139 | TWISSELMAN 2105 | 254402105 |  | 31.0483 | 0.38386 |  | 530 | 0.00020292 | 9998 | 0.072587 | 4709 | 1.4285e-05 | 10716
DAIRYLAND 1113406044 | DAIRYLAND 1113 | 252421113 |  | 4.3398 | 0.24172 |  | 74.5 | 0.00018425 | 10286 | 0.0774 | 3397 | 1.4261e-05 | 10717
TEVIS 21011007 | TEVIS 2101 | 255322101 |  | 5.4581 | 0.048862 |  | 92 | 0.00018417 | 10288 | 0.0774 | 3397 | 1.4255e-05 | 10718
TULARE LAKE 1106565102 | TULARE LAKE 1106 | 252951106 |  | 4.1389 | 0.028044 |  | 73.5 | 0.00020453 | 9967 | 0.06976 | 5082 | 1.4246e-05 | 10719
EL NIDO 110441394 | EL NIDO 1104 | 252451104 |  | 21.6093 | 0.92359 |  | 371 | 0.00018471 | 10281 | 0.077184 | 3607 | 1.4241e-05 | 10720
OAKLAND J 1112CR274 | OAKLAND J 1112 | 12091112 |  | 0.8969 | 0.50055 |  | 9.5833 | 0.00024176 | 9252 | 0.057021 | 7435 | 1.4236e-05 | 10721
CHOLAME 1101CB | CHOLAME 1101 | 182561101 |  | 12.0769 | 1.939 |  | 217.1667 | 0.00021194 | 9844 | 0.067393 | 5675 | 1.4206e-05 | 10722
MORMON 110296462 | MORMON 1102 | 163211102 |  | 10.6728 | 0.73773 |  | 196.5 | 0.00018408 | 10289 | 0.07732 | 3444 | 1.4205e-05 | 10723
TEMPLETON 2109313404 | TEMPLETON 2109 | 183052109 |  | 6.5556 | 0.12939 |  | 112.5 | 0.00021174 | 9848 | 0.067092 | 5910 | 1.4193e-05 | 10724
SAN MIGUEL 1104CB | SAN MIGUEL 1104 | 182661104 |  | 24.8034 | 0.64712 |  | 431.8333 | 0.000208 | 9913 | 0.06816 | 5365 | 1.4188e-05 | 10725
STONE CORRAL 1109CB | STONE CORRAL 1109 | 252921109 |  | 5.7198 | 0.39051 |  | 98.3333 | 0.00020465 | 9965 | 0.070173 | 5004 | 1.4187e-05 | 10726
WINTERS 110223202 | WINTERS 1102 | 63321102 |  | 11.4859 | 1.1352 |  | 214 | 0.00020798 | 9915 | 0.068453 | 5295 | 1.4165e-05 | 10727
EL NIDO 110196140 | EL NIDO 1101 | 252451101 |  | 6.3189 | 0.13896 |  | 113.5 | 0.00018282 | 10306 | 0.0774 | 3397 | 1.4151e-05 | 10728
BUTTE 11072222 | BUTTE 1107 | 103081107 |  | 10.6046 | 0.74684 |  | 189.5 | 0.00019983 | 10045 | 0.07172 | 4801 | 1.4148e-05 | 10729
LINDEN 1103385228 | LINDEN 1103 | 162071103 |  | 4.6538 | 0.25475 |  | 82 | 0.00018559 | 10267 | 0.076441 | 4038 | 1.4148e-05 | 10730
PEABODY 21079784 | PEABODY 2107 | 63642107 |  | 15.3899 | 0.28047 |  | 289 | 0.00020928 | 9883 | 0.067508 | 5595 | 1.4142e-05 | 10731
COALINGA NO 2 110770250 | COALINGA NO 2 1107 | 252381107 |  | 20.8353 | 0.065353 |  | 359 | 0.00020652 | 9942 | 0.06849 | 5289 | 1.4109e-05 | 10732
CRESSEY 21049410 | CRESSEY 2104 | 254702104 |  | 11.8637 | 0.29339 |  | 210 | 0.00018205 | 10317 | 0.0774 | 3397 | 1.4091e-05 | 10733
LINDEN 11033046 | LINDEN 1103 | 162071103 |  | 9.3331 | 0.42994 |  | 164 | 0.00018656 | 10254 | 0.075336 | 4358 | 1.409e-05 | 10734
STOREY 110890070 | STOREY 1108 | 254611108 |  | 21.4205 | 1.9251 |  | 379.5 | 0.00020695 | 9930 | 0.067671 | 5516 | 1.4082e-05 | 10735
SAN ARDO 11017945 | SAN ARDO 1101 | 182191101 |  | 2.5011 | 0.17862 |  | 43.3333 | 0.00019073 | 10199 | 0.073649 | 4586 | 1.4053e-05 | 10736
LOCKEFORD 21026414 | LOCKEFORD 2102 | 163682102 |  | 13.5231 | 0.30421 |  | 228.3333 | 0.00018144 | 10327 | 0.0774 | 3397 | 1.4044e-05 | 10737
FAMOSO 11033652 | FAMOSO 1103 | 252461103 |  | 25.0692 | 0.48301 |  | 428.5 | 0.00018322 | 10302 | 0.076672 | 3948 | 1.4041e-05 | 10738
CRESSEY 21039390 | CRESSEY 2103 | 254702103 |  | 19.6137 | 0.50629 |  | 370 | 0.00019245 | 10174 | 0.072734 | 4692 | 1.403e-05 | 10739
BUTTE 11072498 | BUTTE 1107 | 103081107 |  | 5.0167 | 0.71596 |  | 89 | 0.00019798 | 10076 | 0.07144 | 4837 | 1.3953e-05 | 10740
SMYRNA 1102793576 | SMYRNA 1102 | 253551102 |  | 3.9923 | 0.067394 |  | 65.5 | 0.00018023 | 10349 | 0.0774 | 3397 | 1.395e-05 | 10741
OROSI 11017839F | OROSI 1101 | 252841101 |  | 4.6347 | 0.633 |  | 90.5 | 0.00019938 | 10052 | 0.070103 | 5022 | 1.3928e-05 | 10742
OAKLAND J 1112CR364 | OAKLAND J 1112 | 12091112 |  | 1.2386 | 0.3356 |  | 12.25 | 0.00026241 | 8820 | 0.053073 | 8251 | 1.3927e-05 | 10743
MIDWAY 11021401 | MIDWAY 1102 | 252611102 |  | 14.322 | 0.59651 |  | 254.5 | 0.00018017 | 10351 | 0.077304 | 3467 | 1.3922e-05 | 10744
TWISSELMAN 1102CB | TWISSELMAN 1102 | 254401102 |  | 38.8561 | 0.38262 |  | 642.75 | 0.00019203 | 10178 | 0.073525 | 4609 | 1.3919e-05 | 10745
SEMITROPIC 11122673 | SEMITROPIC 1112 | 252901112 |  | 11.3712 | 0.29916 |  | 195 | 0.00017982 | 10357 | 0.0774 | 3397 | 1.3918e-05 | 10746
MENDOTA 110196158 | MENDOTA 1101 | 252311101 |  | 22.5466 | 0.58276 |  | 375 | 0.00018393 | 10294 | 0.076155 | 4141 | 1.3915e-05 | 10747
RIO BRAVO 1106702014 | RIO BRAVO 1106 | 252861106 |  | 0.2311 | 0.022403 |  | 4 | 0.00017971 | 10359 | 0.0774 | 3397 | 1.391e-05 | 10748
DEVILS DEN 11029340 | DEVILS DEN 1102 | 253451102 |  | 3.6164 | 0.027909 |  | 64.5 | 0.00020392 | 9981 | 0.068311 | 5330 | 1.3908e-05 | 10749
DUNNIGAN 110199650 | DUNNIGAN 1101 | 63811101 |  | 9.6274 | 0.14414 |  | 163 | 0.00020505 | 9963 | 0.067774 | 5482 | 1.3905e-05 | 10750
ELK HILLS 1106556750 | ELK HILLS 1106 | 252441106 |  | 3.7004 | 0 |  | 73 | 0.00020237 | 10005 | 0.068407 | 5303 | 1.3894e-05 | 10751
CAMDEN 11036500 | CAMDEN 1103 | 252301103 |  | 11.6482 | 0.62346 |  | 200.5 | 0.00017938 | 10362 | 0.0774 | 3397 | 1.3884e-05 | 10752
MAXWELL 11023306 | MAXWELL 1102 | 62881102 |  | 36.9413 | 1.3552 |  | 650.5 | 0.00019631 | 10106 | 0.071083 | 4886 | 1.387e-05 | 10753
ANTELOPE 11013609 | ANTELOPE 1101 | 252021101 |  | 8.8693 | 0.14009 |  | 158.5 | 0.0001905 | 10204 | 0.072813 | 4683 | 1.3867e-05 | 10754
REEDLEY 1104218022 | REEDLEY 1104 | 252341104 |  | 10.8195 | 1.7158 |  | 189.5 | 0.00020113 | 10022 | 0.069443 | 5123 | 1.3866e-05 | 10755
REEDLEY 11067270 | REEDLEY 1106 | 252341106 |  | 41.9859 | 6.1511 |  | 759.5 | 0.00019884 | 10063 | 0.070091 | 5025 | 1.3824e-05 | 10756
BLACKWELL 21013258 | BLACKWELL 2101 | 254682101 |  | 9.4 | 0.084569 |  | 181 | 0.00019771 | 10079 | 0.071196 | 4871 | 1.3815e-05 | 10757
ALPAUGH 1104R8190 | ALPAUGH 1104 | 254001104 |  | 5.9851 | 0.18778 |  | 104 | 0.00017846 | 10371 | 0.0774 | 3397 | 1.3813e-05 | 10758
ARBUCKLE 110194064 | ARBUCKLE 1101 | 62081101 |  | 6.3526 | 0.11592 |  | 111 | 0.00019032 | 10208 | 0.073646 | 4588 | 1.3808e-05 | 10759
NORCO 11011963 | NORCO 1101 | 254691101 |  | 0.98012 | 0 |  | 13 | 0.00017833 | 10373 | 0.0774 | 3397 | 1.3803e-05 | 10760
WEBER 110288470 | WEBER 1102 | 163481102 |  | 0.039783 | 0 |  | 0.5 | 0.00017804 | 10378 | 0.0774 | 3397 | 1.3781e-05 | 10761
CLEAR LAKE 1101699062 | CLEAR LAKE 1101 | 42141101 | TRUE | 1.7355 | 0.032686 | 0.30925 | 29 | 0.0001504 | 10704 | 0.26213 | 3064 | 1.3776e-05 | 10762
HOLLISTER 21044046 | HOLLISTER 2104 | 182492104 |  | 10.0539 | 0.92298 |  | 188.1667 | 0.00020535 | 9957 | 0.067032 | 5982 | 1.3768e-05 | 10763
MC FARLAND 1102499013 | MC FARLAND 1102 | 253181102 |  | 1.827 | 0.032025 |  | 30.5 | 0.00017746 | 10389 | 0.0774 | 3397 | 1.3735e-05 | 10764
CUYAMA 21013039 | CUYAMA 2101 | 253142101 |  | 6.7441 | 0.095107 |  | 139.3333 | 0.00016007 | 10598 | 0.086717 | 3358 | 1.3731e-05 | 10765
KERN OIL 110476778 | KERN OIL 1104 | 252721104 |  | 11.3698 | 0.03312 |  | 190.5 | 0.00020435 | 9968 | 0.067037 | 5966 | 1.37e-05 | 10766
HOLLISTER 2105480430 | HOLLISTER 2105 | 182492105 | TRUE | 5.1046 | 0.26119 | 0.40719 | 96 | 0.00016385 | 10550 | 0.084578 | 3372 | 1.3698e-05 | 10767
BRENTWOOD 21122782 | BRENTWOOD 2112 | 14592112 |  | 23.2492 | 0.78492 |  | 410 | 0.00018487 | 10278 | 0.076324 | 4080 | 1.3691e-05 | 10768
WOODWARD 2108703608 | WOODWARD 2108 | 255292108 |  | 0.10489 | 0 |  | 1.5 | 0.00020419 | 9972 | 0.067035 | 5975 | 1.3688e-05 | 10769
WHEATLAND 11051344 | WHEATLAND 1105 | 152811105 |  | 18.008 | 0.74367 |  | 359 | 0.00019039 | 10205 | 0.072721 | 4694 | 1.3685e-05 | 10770
WESTLEY 110111730 | WESTLEY 1101 | 162671101 |  | 17.3437 | 0.42801 |  | 300 | 0.0001991 | 10058 | 0.069239 | 5155 | 1.3679e-05 | 10771
TOKAY 1101CB | TOKAY 1101 | 168881101 |  | 12.2954 | 0.13951 |  | 173 | 0.00017888 | 10367 | 0.075337 | 4357 | 1.3674e-05 | 10772
SALMON CREEK 110137368 | SALMON CREEK 1101 | 43161101 | FALSE | 6.9937 | 0.32389 | 6.2059 | 138 | 0.00020324 | 9992 | 0.067122 | 5883 | 1.3671e-05 | 10773
CHARCA 11033213 | CHARCA 1103 | 254501103 |  | 8.9863 | 0.0068291 |  | 154.5 | 0.0001766 | 10399 | 0.0774 | 3397 | 1.3669e-05 | 10774
TRES VIAS 11011968 | TRES VIAS 1101 | 103251101 |  | 14.8348 | 0.79707 |  | 251 | 0.0001964 | 10101 | 0.069238 | 5156 | 1.3642e-05 | 10775
WHEELER RIDGE 1101234580 | WHEELER RIDGE 1101 | 253481101 |  | 9.7907 | 0.0044097 |  | 181.5 | 0.0001987 | 10066 | 0.068566 | 5271 | 1.3642e-05 | 10776
ANITA 11062418 | ANITA 1106 | 102841106 |  | 9.4821 | 0.47729 |  | 167 | 0.00020103 | 10024 | 0.067506 | 5597 | 1.3613e-05 | 10777
MERCED FALLS 11024000 | MERCED FALLS 1102 | 252811102 |  | 34.1882 | 0.99184 |  | 624.5 | 0.00019659 | 10098 | 0.069051 | 5184 | 1.359e-05 | 10778
HONCUT 11027380 | HONCUT 1102 | 103211102 |  | 10.9543 | 0.40982 |  | 201 | 0.00017619 | 10408 | 0.077219 | 3576 | 1.3589e-05 | 10779
SO. CAL. EDISON 1001CB | SO. CAL. EDISON 1001 | 258881001 |  | 1.9629 | 0 |  | 32 | 0.00017554 | 10416 | 0.0774 | 3397 | 1.3587e-05 | 10780
SAN ARDO 110193072 | SAN ARDO 1101 | 182191101 |  | 5.7917 | 0.11356 |  | 109.3333 | 0.00020166 | 10016 | 0.067191 | 5818 | 1.3561e-05 | 10781
FAMOSO 11012686 | FAMOSO 1101 | 252461101 |  | 26.0516 | 0.38732 |  | 430 | 0.00017934 | 10363 | 0.075239 | 4379 | 1.355e-05 | 10782
COALINGA NO 1 11099270 | COALINGA NO 1 1109 | 252161109 |  | 7.3884 | 0.012213 |  | 122 | 0.00019645 | 10100 | 0.069813 | 5072 | 1.3546e-05 | 10783
WYANDOTTE 110641650 | WYANDOTTE 1106 | 102911106 | TRUE | 16.2127 | 1.2647 | 0.61852 | 286.5 | 0.00013548 | 10837 | 0.11211 | 3286 | 1.3545e-05 | 10784
GERBER 11021560 | GERBER 1102 | 103391102 |  | 12.6848 | 0.53974 |  | 223 | 0.00020126 | 10020 | 0.067264 | 5756 | 1.3545e-05 | 10785
PEABODY 21078502 | PEABODY 2107 | 63642107 |  | 54.9949 | 1.6374 |  | 990 | 0.0001963 | 10109 | 0.069275 | 5149 | 1.3539e-05 | 10786
PEABODY 210718252 | PEABODY 2107 | 63642107 |  | 51.3831 | 2.2994 |  | 916 | 0.00018258 | 10310 | 0.073809 | 4571 | 1.3535e-05 | 10787
TUPMAN 11042705 | TUPMAN 1104 | 254561104 |  | 8.7254 | 0.1563 |  | 148 | 0.00017486 | 10423 | 0.0774 | 3397 | 1.3534e-05 | 10788
SMYRNA 110484708 | SMYRNA 1104 | 253551104 |  | 19.9904 | 0.083146 |  | 321.5 | 0.00018519 | 10274 | 0.073777 | 4572 | 1.3532e-05 | 10789
GARBERVILLE 1102343364 | GARBERVILLE 1102 | 192221102 |  | 0.0082648 | 0 |  | 0.5 | 0.00020192 | 10012 | 0.067 | 6057 | 1.3529e-05 | 10790
CANTUA 11029310 | CANTUA 1102 | 253591102 |  | 27.5791 | 0.36071 |  | 472 | 0.00019053 | 10203 | 0.071612 | 4813 | 1.3527e-05 | 10791
CAL WATER 11023428 | CAL WATER 1102 | 255451102 |  | 4.8683 | 0.027654 |  | 100.5 | 0.00019974 | 10047 | 0.068002 | 5405 | 1.3522e-05 | 10792
CLAY 110314674 | CLAY 1103 | 163341103 |  | 13.9489 | 0.93298 |  | 269.5 | 0.00020121 | 10021 | 0.067176 | 5829 | 1.3515e-05 | 10793
COPUS 11022399 | COPUS 1102 | 253871102 |  | 23.5379 | 0.075197 |  | 399 | 0.00019461 | 10136 | 0.069341 | 5139 | 1.3508e-05 | 10794
NEWMAN 110590430 | NEWMAN 1105 | 162741105 |  | 31.3424 | 0.96061 |  | 556 | 0.00018398 | 10292 | 0.072735 | 4691 | 1.3453e-05 | 10795
MERIDIAN 11023502 | MERIDIAN 1102 | 62541102 |  | 23.3827 | 0.95676 |  | 422 | 0.0001918 | 10183 | 0.070841 | 4911 | 1.3452e-05 | 10796
ARBUCKLE 110447282 | ARBUCKLE 1104 | 62081104 |  | 6.9548 | 0.40386 |  | 119 | 0.00019954 | 10049 | 0.067348 | 5703 | 1.345e-05 | 10797
HAMMONDS 11017250 | HAMMONDS 1101 | 253401101 |  | 5.0121 | 0.081937 |  | 82 | 0.00019844 | 10070 | 0.068078 | 5390 | 1.343e-05 | 10798
CARNERAS 1103CB | CARNERAS 1103 | 252321103 |  | 15.0247 | 0 |  | 262 | 0.00019036 | 10207 | 0.071843 | 4786 | 1.3424e-05 | 10799
CHOWCHILLA 1106275318 | CHOWCHILLA 1106 | 254101106 |  | 13.7415 | 0.26385 |  | 235 | 0.0001828 | 10307 | 0.074213 | 4524 | 1.3416e-05 | 10800
BORDEN 110121130 | BORDEN 1101 | 255121101 |  | 4.0271 | 0.0879 |  | 66 | 0.00017329 | 10442 | 0.0774 | 3397 | 1.3413e-05 | 10801
CARBONA 110145186 | CARBONA 1101 | 163091101 |  | 12.3564 | 0.28944 |  | 215.5 | 0.00019904 | 10060 | 0.06746 | 5630 | 1.3407e-05 | 10802
LAKEVIEW 11064796 | LAKEVIEW 1106 | 253411106 |  | 23.5797 | 0.16067 |  | 415.5 | 0.00019535 | 10124 | 0.068631 | 5252 | 1.3373e-05 | 10803
CORNING 110137546 | CORNING 1101 | 103331101 |  | 10.4173 | 0.4622 |  | 176 | 0.00019729 | 10083 | 0.067546 | 5576 | 1.3369e-05 | 10804
ANITA 11062462 | ANITA 1106 | 102841106 |  | 13.5605 | 0.39817 |  | 227 | 0.00017641 | 10404 | 0.076254 | 4109 | 1.3368e-05 | 10805
CUYAMA 1103CB | CUYAMA 1103 | 253141103 |  | 13.285 | 0.23154 |  | 232.8333 | 0.00019943 | 10050 | 0.067004 | 6034 | 1.3363e-05 | 10806
GONZALES 110165704 | GONZALES 1101 | 182131101 |  | 6.1401 | 0.24981 |  | 137.3333 | 0.00019708 | 10090 | 0.067759 | 5492 | 1.3358e-05 | 10807
VACA DIXON 110376158 | VACA DIXON 1103 | 63591103 |  | 6.7103 | 0.41548 |  | 119.5 | 0.00019716 | 10088 | 0.067773 | 5483 | 1.3353e-05 | 10808
DAIRYLAND 1105410364 | DAIRYLAND 1105 | 252421105 |  | 0.038398 | 0 |  | 0.5 | 0.00017222 | 10456 | 0.0774 | 3397 | 1.333e-05 | 10809
ARBUCKLE 1104969486 | ARBUCKLE 1104 | 62081104 |  | 10.4542 | 0.39613 |  | 178 | 0.00018898 | 10225 | 0.071269 | 4860 | 1.3325e-05 | 10810
LE GRAND 1104CB | LE GRAND 1104 | 255361104 |  | 11.4756 | 0.26023 |  | 185.3333 | 0.00017208 | 10457 | 0.0774 | 3397 | 1.3319e-05 | 10811
SAN ARDO 110283166 | SAN ARDO 1102 | 182191102 |  | 3.9064 | 0.22866 |  | 81 | 0.00019877 | 10065 | 0.067 | 6057 | 1.3317e-05 | 10812
CORRAL 11012128 | CORRAL 1101 | 162991101 |  | 16.2529 | 0.78311 |  | 296.8333 | 0.00019717 | 10086 | 0.06746 | 5629 | 1.3308e-05 | 10813
RAINBOW 1106R104 | RAINBOW 1106 | 254441106 |  | 16.1565 | 1.0558 |  | 274 | 0.00018143 | 10329 | 0.072162 | 4758 | 1.3304e-05 | 10814
MADISON 210112321 | MADISON 2101 | 63172101 |  | 1.1376 | 0.015578 |  | 21.5 | 0.00013455 | 10844 | 0.098454 | 3318 | 1.3274e-05 | 10815
CUYAMA 21013533 | CUYAMA 2101 | 253142101 |  | 19.2923 | 0.26002 |  | 329.8333 | 0.00019747 | 10081 | 0.067098 | 5900 | 1.3261e-05 | 10816
OCEANO 1105CB | OCEANO 1105 | 182601105 |  | 9.1157 | 5.789 |  | 142.5 | 0.00016885 | 10499 | 0.061932 | 6770 | 1.3259e-05 | 10817
MIDDLE RIVER 11015240 | MIDDLE RIVER 1101 | 162091101 |  | 14.4658 | 0.15927 |  | 289 | 0.00017122 | 10472 | 0.0774 | 3397 | 1.3252e-05 | 10818
TULARE LAKE 110854074 | TULARE LAKE 1108 | 252951108 |  | 15.2301 | 0.23177 |  | 262.5 | 0.00018804 | 10234 | 0.071937 | 4779 | 1.3245e-05 | 10819
NEWHALL 110912150 | NEWHALL 1109 | 254461109 |  | 19.1267 | 0.34944 |  | 319 | 0.00017103 | 10473 | 0.0774 | 3397 | 1.3238e-05 | 10820
LINCOLN 2109924404 | LINCOLN 2109 | 153702109 |  | 0.10719 | 0 |  | 4 | 0.00018454 | 10284 | 0.0722 | 4756 | 1.3233e-05 | 10821
DIXON 11038782 | DIXON 1103 | 62061103 |  | 38.958 | 1.9381 |  | 652 | 0.00017172 | 10465 | 0.077152 | 3645 | 1.3228e-05 | 10822
SAN ARDO 11017054 | SAN ARDO 1101 | 182191101 |  | 9.1921 | 0.1649 |  | 193 | 0.00019459 | 10138 | 0.068293 | 5334 | 1.3222e-05 | 10823
VINA 110135730 | VINA 1101 | 103581101 |  | 5.3883 | 0.056619 |  | 106.8333 | 0.00019529 | 10125 | 0.067463 | 5626 | 1.3189e-05 | 10824
WOODCHUCK 2101R2640 | WOODCHUCK 2101 | 254912101 |  | 1.3294 | 0 |  | 24.5 | 0.00019516 | 10128 | 0.067376 | 5684 | 1.3184e-05 | 10825
PLEASANT GROVE 21101296 | PLEASANT GROVE 2110 | 152442110 |  | 5.7655 | 0.092258 |  | 98 | 0.00018126 | 10335 | 0.073412 | 4622 | 1.3184e-05 | 10826
VALLEY HOME 17023214 | VALLEY HOME 1702 | 162981702 |  | 18.7592 | 0.67184 |  | 329.5 | 0.00017778 | 10384 | 0.074837 | 4436 | 1.3177e-05 | 10827
COALINGA NO 2 110677252 | COALINGA NO 2 1106 | 252381106 |  | 22.0464 | 0.19886 |  | 409 | 0.00019357 | 10157 | 0.067896 | 5439 | 1.3176e-05 | 10828
CARNERAS 1102372456 | CARNERAS 1102 | 252321102 |  | 4.5804 | 0.027198 |  | 77.5 | 0.00018137 | 10330 | 0.073374 | 4627 | 1.3166e-05 | 10829
CALFLAX 1103CUS303 | CALFLAX 1103 | 253441103 |  | 0.0072192 | 0 |  | 1 | 0.00019617 | 10113 | 0.067 | 6057 | 1.3144e-05 | 10830
SCHINDLER 111256574 | SCHINDLER 1112 | 252891112 |  | 1.4146 | 0 |  | 23.5 | 0.0001697 | 10489 | 0.0774 | 3397 | 1.3135e-05 | 10831
SISQUOC 1103M14 | SISQUOC 1103 | 182811103 |  | 10.1309 | 0.22364 |  | 205 | 0.0001925 | 10172 | 0.068144 | 5370 | 1.3099e-05 | 10832
LE GRAND 11107130 | LE GRAND 1110 | 255361110 |  | 30.1446 | 0.85964 |  | 528.5 | 0.00018169 | 10322 | 0.071303 | 4857 | 1.3095e-05 | 10833
ALPAUGH 110499506 | ALPAUGH 1104 | 254001104 |  | 4.6503 | 0.20442 |  | 79 | 0.00017187 | 10460 | 0.076784 | 3895 | 1.3093e-05 | 10834
STONE CORRAL 11097580 | STONE CORRAL 1109 | 252921109 |  | 10.8145 | 1.3298 |  | 192 | 0.0001869 | 10245 | 0.070792 | 4918 | 1.309e-05 | 10835
SANTA RITA 11029920 | SANTA RITA 1102 | 253541102 |  | 29.1901 | 0.74083 |  | 491.5 | 0.00016905 | 10497 | 0.077355 | 3408 | 1.3075e-05 | 10836
RENFRO 21014889 | RENFRO 2101 | 254572101 |  | 3.0286 | 0.11747 |  | 60 | 0.00016875 | 10501 | 0.0774 | 3397 | 1.3062e-05 | 10837
SISQUOC 1101M96 | SISQUOC 1101 | 182811101 |  | 13.5722 | 0.19479 |  | 251 | 0.00019357 | 10156 | 0.06736 | 5698 | 1.3061e-05 | 10838
WOODCHUCK 2101R1790 | WOODCHUCK 2101 | 254912101 |  | 1.1124 | 0.11648 |  | 23.5 | 0.00019215 | 10175 | 0.068556 | 5272 | 1.3051e-05 | 10839
HENRIETTA 110849938 | HENRIETTA 1108 | 252681108 |  | 6.8138 | 3.0276 |  | 177.5 | 0.00017019 | 10483 | 0.0769 | 3832 | 1.3038e-05 | 10840
CORNING 110238162 | CORNING 1102 | 103331102 |  | 29.6987 | 0.65436 |  | 521.5 | 0.00019021 | 10211 | 0.068617 | 5260 | 1.301e-05 | 10841
ELK HILLS 1104334524 | ELK HILLS 1104 | 252441104 |  | 0.03349 | 0 |  | 0.33333 | 0.00019366 | 10151 | 0.067 | 6056 | 1.2975e-05 | 10842
ELK HILLS 1104CUS8676 | ELK HILLS 1104 | 252441104 |  | 0.019902 | 0 |  | 0.33333 | 0.00019366 | 10151 | 0.067 | 6056 | 1.2975e-05 | 10842
SANTA NELLA 11043130 | SANTA NELLA 1104 | 254051104 |  | 7.6923 | 0.091432 |  | 137 | 0.00017726 | 10390 | 0.07491 | 4425 | 1.2969e-05 | 10843
ORO LOMA 11173740 | ORO LOMA 1117 | 255371117 |  | 24.4296 | 0.57819 |  | 419 | 0.00017804 | 10379 | 0.07261 | 4708 | 1.2965e-05 | 10844
KERN OIL 1104CB | KERN OIL 1104 | 252721104 |  | 13.0329 | 0.098382 |  | 219.25 | 0.00019307 | 10163 | 0.067204 | 5804 | 1.2962e-05 | 10845
GUERNSEY 11018260 | GUERNSEY 1101 | 252661101 |  | 6.9911 | 0.050039 |  | 115.5 | 0.00017079 | 10477 | 0.076191 | 4131 | 1.2961e-05 | 10846
SANTA MARIA 1110M44 | SANTA MARIA 1110 | 182671110 |  | 20.7147 | 0.35647 |  | 337.5 | 0.00019374 | 10147 | 0.067014 | 6014 | 1.2954e-05 | 10847
CANTUA 11039250 | CANTUA 1103 | 253591103 |  | 4.9125 | 1.1665 |  | 85.5 | 0.000174 | 10434 | 0.074639 | 4466 | 1.2941e-05 | 10848
HOLLISTER 21054040 | HOLLISTER 2105 | 182492105 |  | 8.2999 | 0.35686 |  | 158 | 0.00018989 | 10215 | 0.067934 | 5421 | 1.2904e-05 | 10849
GATES 11049110 | GATES 1104 | 253931104 |  | 3.3941 | 0.0254 |  | 59 | 0.00019303 | 10164 | 0.066644 | 6154 | 1.2865e-05 | 10850
TEMPLETON 2109R78 | TEMPLETON 2109 | 183052109 |  | 4.4744 | 0.1237 |  | 76.8333 | 0.00019158 | 10186 | 0.067135 | 5867 | 1.2861e-05 | 10851
MIDDLE RIVER 110157494 | MIDDLE RIVER 1101 | 162091101 |  | 9.8329 | 0.11874 |  | 180.5 | 0.00016637 | 10518 | 0.077269 | 3517 | 1.2853e-05 | 10852
LINDEN 110112182 | LINDEN 1101 | 162071101 |  | 4.3619 | 0.14677 |  | 75.5 | 0.00016565 | 10526 | 0.0774 | 3397 | 1.2821e-05 | 10853
MC MULLIN 1105840744 | MC MULLIN 1105 | 254411105 |  | 2.6525 | 0.01808 |  | 46 | 0.00016546 | 10527 | 0.0774 | 3397 | 1.2806e-05 | 10854
KETTLEMAN HILLS 21049020 | KETTLEMAN HILLS 2104 | 252732104 |  | 20.4133 | 0.31967 |  | 362 | 0.00018642 | 10256 | 0.068575 | 5265 | 1.28e-05 | 10855
ESQUON 1101717130 | ESQUON 1101 | 102171101 |  | 0.059968 | 0 |  | 1.5 | 0.00019088 | 10198 | 0.067 | 6057 | 1.2789e-05 | 10856
TIVY VALLEY 1106CB | TIVY VALLEY 1106 | 252941106 |  | 7.6495 | 0.80155 |  | 144.5 | 0.00018972 | 10217 | 0.067239 | 5773 | 1.2772e-05 | 10857
PEASE 11031226 | PEASE 1103 | 153751103 |  | 11.2303 | 0.73186 |  | 213.5 | 0.00017621 | 10407 | 0.075835 | 4250 | 1.2771e-05 | 10858
CANAL 1101459434 | CANAL 1101 | 252091101 |  | 6.3827 | 0.045101 |  | 125.5 | 0.00016509 | 10533 | 0.077275 | 3512 | 1.2757e-05 | 10859
CANTUA 11039900 | CANTUA 1103 | 253591103 |  | 10.3874 | 0.022478 |  | 199.5 | 0.00018341 | 10300 | 0.070164 | 5005 | 1.2754e-05 | 10860
SAN MIGUEL 1107CB | SAN MIGUEL 1107 | 182661107 |  | 5.6878 | 0.84584 |  | 99.8333 | 0.00018953 | 10222 | 0.067292 | 5737 | 1.2746e-05 | 10861
WINTERS 110248002 | WINTERS 1102 | 63321102 |  | 21.5169 | 1.0658 |  | 432 | 0.00017001 | 10485 | 0.075582 | 4318 | 1.2741e-05 | 10862
COPPERMINE 1112CB | COPPERMINE 1112 | 252411112 |  | 15.8559 | 0.90798 |  | 249.5833 | 0.00018953 | 10221 | 0.067 | 6058 | 1.2699e-05 | 10863
WILSON 11034140 | WILSON 1103 | 254301103 |  | 20.4157 | 0.75134 |  | 378.5 | 0.0001858 | 10264 | 0.068044 | 5396 | 1.2685e-05 | 10864
CHOLAME 2102X10 | CHOLAME 2102 | 182562102 |  | 18.5954 | 0.37222 |  | 354 | 0.00018267 | 10309 | 0.069136 | 5171 | 1.2641e-05 | 10865
WRIGHT 111084280 | WRIGHT 1110 | 254641110 |  | 6.7853 | 0.089113 |  | 114 | 0.00018529 | 10271 | 0.067805 | 5474 | 1.2603e-05 | 10866
JACINTO 110194868 | JACINTO 1101 | 102851101 |  | 11.2298 | 0.41445 |  | 203.5 | 0.00017256 | 10450 | 0.074308 | 4511 | 1.2584e-05 | 10867
TEMPLETON 2109P32 | TEMPLETON 2109 | 183052109 |  | 10.8968 | 0.21233 |  | 203.8333 | 0.00018626 | 10259 | 0.067612 | 5540 | 1.2572e-05 | 10868
FIREBAUGH 110212190 | FIREBAUGH 1102 | 253471102 |  | 17.5769 | 0.55665 |  | 322 | 0.00016265 | 10566 | 0.077351 | 3412 | 1.257e-05 | 10869
TEMBLOR 110414233 | TEMBLOR 1104 | 252551104 |  | 6.7634 | 0.078186 |  | 127.5 | 0.00017454 | 10427 | 0.072249 | 4753 | 1.2566e-05 | 10870
LOCKEFORD 210212468 | LOCKEFORD 2102 | 163682102 |  | 39.7305 | 1.0716 |  | 696 | 0.00018663 | 10252 | 0.067225 | 5785 | 1.2551e-05 | 10871
ANTELOPE 1102CB | ANTELOPE 1102 | 252021102 |  | 25.3382 | 0.44494 |  | 435.5 | 0.00016843 | 10503 | 0.074534 | 4484 | 1.252e-05 | 10872
MORRO BAY 1102W22 | MORRO BAY 1102 | 183011102 | FALSE | 6.3007 | 2.7754 | 2.9677 | 99.5 | 3.4614e-05 | 11138 | 0.46187 | 2861 | 1.2512e-05 | 10873
WOODWARD 2108R2860 | WOODWARD 2108 | 255292108 | TRUE | 10.172 | 0.17887 | 0.0020626 | 191.5 | 0.00018628 | 10258 | 0.067095 | 5904 | 1.2501e-05 | 10874
HERDLYN 1102609338 | HERDLYN 1102 | 163741102 |  | 8.191 | 0.017365 |  | 144.8333 | 0.00018227 | 10315 | 0.0683 | 5333 | 1.2495e-05 | 10875
SMYRNA 110496526 | SMYRNA 1104 | 253551104 |  | 5.3431 | 0.0096716 |  | 87.5 | 0.00017981 | 10358 | 0.068554 | 5273 | 1.2483e-05 | 10876
COPPERMINE 1104R3200 | COPPERMINE 1104 | 252411104 |  | 17.2501 | 0.71673 |  | 301 | 0.00017551 | 10417 | 0.070784 | 4921 | 1.246e-05 | 10877
CRESSEY 2103335764 | CRESSEY 2103 | 254702103 |  | 4.4858 | 0.20734 |  | 82 | 0.00016095 | 10590 | 0.0774 | 3397 | 1.2457e-05 | 10878
MADISON 2101845694 | MADISON 2101 | 63172101 |  | 0.3266 | 0.019698 |  | 7.5 | 0.00019688 | 10095 | 0.067035 | 5975 | 1.2442e-05 | 10879
CROWS LANDING 110190600 | CROWS LANDING 1101 | 163251101 |  | 21.7761 | 0.67404 |  | 402 | 0.00017377 | 10435 | 0.071265 | 4862 | 1.2442e-05 | 10880
WESTLEY 110111736 | WESTLEY 1101 | 162671101 |  | 13.3014 | 0.41461 |  | 235.5 | 0.00018188 | 10320 | 0.068531 | 5281 | 1.2441e-05 | 10881
LIVINGSTON 110190490 | LIVINGSTON 1101 | 252261101 |  | 25.6328 | 0.69215 |  | 449 | 0.00016105 | 10587 | 0.077292 | 3485 | 1.2427e-05 | 10882
ATASCADERO 1103A80 | ATASCADERO 1103 | 182541103 |  | 11.0771 | 0.84096 |  | 203.5 | 0.00017833 | 10372 | 0.07242 | 4726 | 1.2423e-05 | 10883
LE GRAND 11107120 | LE GRAND 1110 | 255361110 |  | 26.6161 | 1.3466 |  | 469 | 0.00018009 | 10353 | 0.068634 | 5251 | 1.2422e-05 | 10884
LERDO 11124323 | LERDO 1112 | 253491112 |  | 6.6681 | 0.074437 |  | 96 | 0.00017476 | 10424 | 0.069657 | 5089 | 1.242e-05 | 10885
CARNERAS 11023266 | CARNERAS 1102 | 252321102 |  | 4.6008 | 0 |  | 99 | 0.00018528 | 10273 | 0.067001 | 6052 | 1.2414e-05 | 10886
ORTIGA 11063770 | ORTIGA 1106 | 254311106 |  | 6.7183 | 0.14881 |  | 124 | 0.00018352 | 10298 | 0.067442 | 5644 | 1.2375e-05 | 10887
DAVIS 11128722 | DAVIS 1112 | 62041112 |  | 14.3966 | 0.2798 |  | 256.5 | 0.00015949 | 10604 | 0.0774 | 3397 | 1.2345e-05 | 10888
WESTLEY 1101463982 | WESTLEY 1101 | 162671101 |  | 13.4897 | 0.64674 |  | 234 | 0.00017886 | 10368 | 0.069546 | 5115 | 1.2336e-05 | 10889
DAIRYVILLE 11014679 | DAIRYVILLE 1101 | 103341101 |  | 4.2663 | 0.064197 |  | 85.5 | 0.00018228 | 10314 | 0.06765 | 5526 | 1.2281e-05 | 10890
FITCH MOUNTAIN 1111555644 | FITCH MOUNTAIN 1111 | 42751111 | TRUE | 3.1253 | 0.10178 | 0.034084 | 57.5 | 0.00018074 | 10345 | 0.068364 | 5309 | 1.2279e-05 | 10891
SAN MIGUEL 1106CB | SAN MIGUEL 1106 | 182661106 |  | 14.9091 | 0.19063 |  | 291.3333 | 0.00017994 | 10354 | 0.068355 | 5315 | 1.2258e-05 | 10892
SCHINDLER 1110176099 | SCHINDLER 1110 | 252891110 |  | 4.506 | 0.16291 |  | 77.5 | 0.00015796 | 10617 | 0.0774 | 3397 | 1.2226e-05 | 10893
BERRENDA A 1101CB | BERRENDA A 1101 | 254261101 |  | 0.011413 | 0 |  | 1 | 0.00018236 | 10313 | 0.067 | 6057 | 1.2218e-05 | 10894
CORDELIA 110440922 | CORDELIA 1104 | 62701104 |  | 8.6783 | 0.14904 |  | 181 | 0.0001816 | 10324 | 0.067229 | 5779 | 1.221e-05 | 10895
BIOLA 11026170 | BIOLA 1102 | 252211102 |  | 15.627 | 0.34091 |  | 270.8333 | 0.00015765 | 10623 | 0.0774 | 3396 | 1.2202e-05 | 10896
KERN OIL 11044479 | KERN OIL 1104 | 252721104 |  | 6.6001 | 0.035656 |  | 105 | 0.00018144 | 10328 | 0.067163 | 5843 | 1.219e-05 | 10897
SMYRNA 110538778 | SMYRNA 1105 | 253551105 |  | 25.188 | 0.28559 |  | 420 | 0.00015862 | 10607 | 0.077007 | 3758 | 1.2174e-05 | 10898
TYLER 11051704 | TYLER 1105 | 103571105 |  | 2.7481 | 0.16554 |  | 48 | 0.00018111 | 10336 | 0.067217 | 5793 | 1.2145e-05 | 10899
CHOWCHILLA 11045980 | CHOWCHILLA 1104 | 254101104 |  | 16.4542 | 0.45138 |  | 273.5 | 0.00015701 | 10629 | 0.07721 | 3583 | 1.2137e-05 | 10900
OAKLAND J 1112CR360 | OAKLAND J 1112 | 12091112 |  | 0.66552 | 0.53569 |  | 10.8333 | 0.00022852 | 9525 | 0.054195 | 7906 | 1.2133e-05 | 10901
STOREY 11095580 | STOREY 1109 | 254611109 |  | 31.8195 | 1.1481 |  | 538.5 | 0.00016274 | 10562 | 0.074444 | 4491 | 1.2122e-05 | 10902
GANSO 1104339578 | GANSO 1104 | 254541104 |  | 1.5245 | 0.051066 |  | 26.5 | 0.00015641 | 10637 | 0.0774 | 3397 | 1.2106e-05 | 10903
HENRIETTA 11048550 | HENRIETTA 1104 | 252681104 |  | 15.204 | 0.22135 |  | 227.5 | 0.00016093 | 10591 | 0.075907 | 4229 | 1.2091e-05 | 10904
ORO LOMA 1118848136 | ORO LOMA 1118 | 255371118 |  | 12.9667 | 0.29406 |  | 219.5 | 0.0001577 | 10621 | 0.076505 | 4014 | 1.2075e-05 | 10905
KING CITY 11027024 | KING CITY 1102 | 182031102 |  | 13.6532 | 0.21004 |  | 273 | 0.00017805 | 10377 | 0.067854 | 5456 | 1.2065e-05 | 10906
NORCO 11013938 | NORCO 1101 | 254691101 |  | 6.5863 | 0.036679 |  | 117 | 0.00016037 | 10595 | 0.075749 | 4279 | 1.2061e-05 | 10907
STROUD 1104809407 | STROUD 1104 | 253661104 |  | 4.041 | 0.037712 |  | 83 | 0.0001557 | 10640 | 0.0774 | 3397 | 1.2051e-05 | 10908
LERDO 111689580 | LERDO 1116 | 253491116 |  | 13.8172 | 0.087491 |  | 211 | 0.00016691 | 10515 | 0.070955 | 4898 | 1.2001e-05 | 10909
LAKEVILLE 1101108774 | LAKEVILLE 1101 | 43371101 |  | 0.016989 | 0 |  | 1.5 | 0.00017857 | 10370 | 0.06707 | 5925 | 1.1977e-05 | 10910
TEJON 11032280 | TEJON 1103 | 252931103 |  | 21.5188 | 0.3383 |  | 381.5 | 0.00017091 | 10474 | 0.070094 | 5024 | 1.1954e-05 | 10911
BAHIA 110493908 | BAHIA 1104 | 43251104 |  | 3.7743 | 0.023764 |  | 75.5 | 0.00017771 | 10386 | 0.067235 | 5777 | 1.1949e-05 | 10912
MORRO BAY 1101V68 | MORRO BAY 1101 | 183011101 |  | 1.5877 | 1.1315 |  | 25.5 | 0.00018455 | 10283 | 0.063584 | 6602 | 1.1939e-05 | 10913
BIOLA 1102622058 | BIOLA 1102 | 252211102 |  | 5.6172 | 0.2016 |  | 106.3333 | 0.00015425 | 10655 | 0.0774 | 3397 | 1.1939e-05 | 10914
MADISON 1105489630 | MADISON 1105 | 63171105 |  | 13.9241 | 0.35199 |  | 254.5 | 0.00016773 | 10510 | 0.071714 | 4803 | 1.1926e-05 | 10915
ORLAND B 110396988 | ORLAND B 1103 | 102701103 |  | 0.028313 | 0 |  | 1.5 | 0.00017725 | 10391 | 0.067105 | 5893 | 1.1894e-05 | 10916
CATLETT 110285762 | CATLETT 1102 | 153761102 |  | 13.818 | 0.59012 |  | 229.8333 | 0.0001659 | 10522 | 0.072068 | 4771 | 1.1882e-05 | 10917
MENDOTA 110237442 | MENDOTA 1102 | 252311102 |  | 18.8901 | 0.59255 |  | 327 | 0.00015495 | 10646 | 0.077029 | 3744 | 1.1871e-05 | 10918
VALLEY HOME 170356266 | VALLEY HOME 1703 | 162981703 |  | 0.59814 | 0.012302 |  | 11.5 | 0.00015287 | 10669 | 0.0774 | 3397 | 1.1832e-05 | 10919
SAN MIGUEL 1105765824 | SAN MIGUEL 1105 | 182661105 |  | 9.8628 | 0.34439 |  | 191.5 | 0.00017632 | 10405 | 0.067054 | 5942 | 1.1822e-05 | 10920
TEMPLETON 2109CB | TEMPLETON 2109 | 183052109 |  | 16.1617 | 0.38606 |  | 299 | 0.00017556 | 10415 | 0.067316 | 5719 | 1.1802e-05 | 10921
PASO ROBLES 1107P22 | PASO ROBLES 1107 | 182611107 |  | 6.524 | 0.3001 |  | 109 | 0.00017173 | 10464 | 0.068623 | 5257 | 1.1794e-05 | 10922
CORRAL 1101CUS9215 | CORRAL 1101 | 162991101 |  | 0.0037879 | 0 |  | 0.33333 | 0.00017592 | 10410 | 0.067 | 6056 | 1.1787e-05 | 10923
CORRAL 1101173174 | CORRAL 1101 | 162991101 |  | 0.020873 | 0 |  | 0.33333 | 0.00017592 | 10410 | 0.067 | 6056 | 1.1787e-05 | 10923
LIVERMORE 1104MR192 | LIVERMORE 1104 | 12141104 |  | 0.86429 | 0 |  | 14.5 | 0.00017582 | 10412 | 0.067 | 6057 | 1.178e-05 | 10924
TUPMAN 11054107 | TUPMAN 1105 | 254561105 |  | 9.2575 | 0.044043 |  | 154 | 0.00015227 | 10673 | 0.077298 | 3474 | 1.177e-05 | 10925
TEVIS 21011515 | TEVIS 2101 | 255322101 |  | 8.8753 | 0.14135 |  | 150.5 | 0.00015373 | 10660 | 0.076706 | 3934 | 1.1757e-05 | 10926
SMYRNA 1101317866 | SMYRNA 1101 | 253551101 |  | 20.1316 | 0.15684 |  | 332.5 | 0.00015757 | 10625 | 0.075159 | 4391 | 1.1753e-05 | 10927
PEABODY 21059641 | PEABODY 2105 | 63642105 |  | 9.2999 | 0.962 |  | 174.5 | 0.00017223 | 10455 | 0.068587 | 5263 | 1.1747e-05 | 10928
CAL WATER 1102920714 | CAL WATER 1102 | 255451102 |  | 4.3021 | 0.10652 |  | 87.5 | 0.00017059 | 10478 | 0.068722 | 5236 | 1.173e-05 | 10929
CORTINA 110149858 | CORTINA 1101 | 63121101 |  | 7.9898 | 0.094822 |  | 136 | 0.00016971 | 10488 | 0.069133 | 5172 | 1.1697e-05 | 10930
POSO MOUNTAIN 2103388671 | POSO MOUNTAIN 2103 | 253642103 |  | 2.0131 | 0 |  | 35 | 0.00017088 | 10475 | 0.068477 | 5293 | 1.1695e-05 | 10931
LUCERNE 1103721 | LUCERNE 1103 | 43351103 |  | 1.3936 | 0.46648 |  | 26.5 | 0.00018274 | 10308 | 0.064214 | 6518 | 1.1674e-05 | 10932
DAVIS 11016032 | DAVIS 1101 | 62041101 |  | 16.1629 | 0.4628 |  | 283 | 0.00015079 | 10695 | 0.077258 | 3532 | 1.1645e-05 | 10933
LOCKEFORD 210220355 | LOCKEFORD 2102 | 163682102 |  | 0.20327 | 0.034818 |  | 4.5 | 0.00017362 | 10436 | 0.067 | 6057 | 1.1633e-05 | 10934
MADISON 21016617 | MADISON 2101 | 63172101 |  | 4.0143 | 0.43214 |  | 78 | 0.00017276 | 10447 | 0.067169 | 5835 | 1.1608e-05 | 10935
MC ARTHUR 11011492 | MC ARTHUR 1101 | 103491101 |  | 11.5861 | 0.45447 |  | 198 | 0.00016999 | 10486 | 0.068262 | 5344 | 1.1598e-05 | 10936
ANTELOPE 11011631 | ANTELOPE 1101 | 252021101 |  | 8.7948 | 0.17625 |  | 180 | 0.00016515 | 10532 | 0.069961 | 5051 | 1.156e-05 | 10937
WILLITS 1102CUS8736 | WILLITS 1102 | 42661102 |  | 0.0057022 | 0 |  | 0.5 | 0.00017132 | 10470 | 0.067 | 6057 | 1.1479e-05 | 10938
PANOCHE 11013530 | PANOCHE 1101 | 253671101 |  | 6.283 | 0.073018 |  | 102 | 0.00016126 | 10583 | 0.07045 | 4953 | 1.1475e-05 | 10939
WHEATLAND 11042700 | WHEATLAND 1104 | 152811104 |  | 23.3273 | 1.2079 |  | 395.5 | 0.00017013 | 10484 | 0.067105 | 5892 | 1.1411e-05 | 10940
TIVY VALLEY 1106D8492 | TIVY VALLEY 1106 | 252941106 |  | 1.843 | 0.19034 |  | 35 | 0.00016541 | 10530 | 0.068931 | 5201 | 1.1392e-05 | 10941
DIXON 110315137 | DIXON 1103 | 62061103 |  | 4.0324 | 0.080428 |  | 76.5 | 0.00014716 | 10725 | 0.0774 | 3397 | 1.139e-05 | 10942
HAMMONDS 110212100 | HAMMONDS 1102 | 253401102 |  | 15.7855 | 0.34714 |  | 273 | 0.0001643 | 10543 | 0.069855 | 5066 | 1.1385e-05 | 10943
LOCKEFORD 21022136 | LOCKEFORD 2102 | 163682102 |  | 2.6586 | 0.13393 |  | 46 | 0.00014705 | 10728 | 0.0774 | 3397 | 1.1382e-05 | 10944
JERSEY ISLAND 0401CB | JERSEY ISLAND 0401 | 18320401 |  | 2.8752 | 0.058577 |  | 60 | 0.00014661 | 10733 | 0.0774 | 3397 | 1.1348e-05 | 10945
SANTA NELLA 11017200 | SANTA NELLA 1101 | 254051101 |  | 15.5223 | 0.20626 |  | 279.5 | 0.00016775 | 10509 | 0.067524 | 5589 | 1.1346e-05 | 10946
STOREY 11096230 | STOREY 1109 | 254611109 |  | 6.0741 | 0.18118 |  | 115.5 | 0.00014647 | 10734 | 0.0774 | 3397 | 1.1337e-05 | 10947
ZAMORA 110655084 | ZAMORA 1106 | 63191106 |  | 8.5518 | 0.2571 |  | 159.5 | 0.00016351 | 10555 | 0.069483 | 5120 | 1.1333e-05 | 10948
HERDLYN 110299602 | HERDLYN 1102 | 163741102 |  | 7.7593 | 0.13685 |  | 138.5 | 0.00016579 | 10524 | 0.069035 | 5186 | 1.133e-05 | 10949
EDENVALE 2105696340 | EDENVALE 2105 | 82952105 |  | 0.11941 | 0 |  | 2.5 | 0.00016896 | 10498 | 0.067 | 6057 | 1.132e-05 | 10950
LINDEN 1103542460 | LINDEN 1103 | 162071103 |  | 9.2668 | 0.090976 |  | 152 | 0.00016435 | 10541 | 0.068815 | 5221 | 1.132e-05 | 10951
GERBER 1102190339 | GERBER 1102 | 103391102 |  | 1.6059 | 0 |  | 26.5 | 0.00016873 | 10502 | 0.067035 | 5975 | 1.131e-05 | 10952
PEABODY 21074902 | PEABODY 2107 | 63642107 |  | 55.9064 | 2.7066 |  | 1042.6667 | 0.0001657 | 10525 | 0.068239 | 5351 | 1.1304e-05 | 10953
HONCUT 1101424030 | HONCUT 1101 | 103211101 |  | 12.4749 | 0.58346 |  | 228 | 0.00016321 | 10557 | 0.069203 | 5163 | 1.1297e-05 | 10954
NEWHALL 11115960 | NEWHALL 1111 | 254461111 |  | 7.79 | 0.382 |  | 133 | 0.00014545 | 10744 | 0.0774 | 3397 | 1.1258e-05 | 10955
DEVILS DEN 11019470 | DEVILS DEN 1101 | 253451101 |  | 4.9669 | 0.13276 |  | 101 | 0.00016159 | 10580 | 0.068499 | 5287 | 1.1251e-05 | 10956
GIFFEN 11029320 | GIFFEN 1102 | 253151102 |  | 2.9677 | 0.10703 |  | 46.5 | 0.00014515 | 10745 | 0.0774 | 3397 | 1.1235e-05 | 10957
MIDDLE RIVER 110212902 | MIDDLE RIVER 1102 | 162091102 |  | 13.9556 | 0.40091 |  | 292 | 0.00014557 | 10742 | 0.077151 | 3647 | 1.1233e-05 | 10958
WESTLEY 11039900 | WESTLEY 1103 | 162671103 |  | 12.4606 | 0.43017 |  | 219 | 0.00016238 | 10571 | 0.069409 | 5125 | 1.1233e-05 | 10959
CARUTHERS 110595148 | CARUTHERS 1105 | 252371105 |  | 9.0115 | 0.10369 |  | 152.5 | 0.00014446 | 10752 | 0.0774 | 3397 | 1.1181e-05 | 10960
RAINBOW 1106367670 | RAINBOW 1106 | 254441106 |  | 5.7268 | 0.4557 |  | 98 | 0.00016392 | 10547 | 0.067955 | 5414 | 1.114e-05 | 10961
TULARE LAKE 11069800 | TULARE LAKE 1106 | 252951106 |  | 21.5782 | 0.11947 |  | 349 | 0.00015204 | 10678 | 0.075595 | 4313 | 1.1129e-05 | 10962
CORCORAN 1116630954 | CORCORAN 1116 | 252171116 |  | 0.031653 | 0 |  | 1.5 | 0.00014374 | 10761 | 0.0774 | 3397 | 1.1125e-05 | 10963
TEMPLETON 2109R92 | TEMPLETON 2109 | 183052109 |  | 34.4779 | 0.76648 |  | 621 | 0.00016253 | 10570 | 0.068331 | 5322 | 1.1121e-05 | 10964
GATES 110692202 | GATES 1106 | 253931106 |  | 4.4059 | 0.031825 |  | 74.5 | 0.00015856 | 10610 | 0.06986 | 5065 | 1.1076e-05 | 10965
HAMMONDS 1102CB | HAMMONDS 1102 | 253401102 |  | 19.6499 | 0.36831 |  | 338 | 0.00015142 | 10685 | 0.072984 | 4665 | 1.1072e-05 | 10966
OLEMA 1101334 | OLEMA 1101 | 42291101 |  | 13.8824 | 0.39116 |  | 272.5 | 0.00016488 | 10534 | 0.067192 | 5817 | 1.1068e-05 | 10967
GONZALES 1104415382 | GONZALES 1104 | 182131104 | TRUE | 1.1941 | 0.093602 | 0.0036389 | 27.5 | 0.00015855 | 10611 | 0.068901 | 5206 | 1.1063e-05 | 10968
STOREY 11095680 | STOREY 1109 | 254611109 |  | 26.7621 | 0.79678 |  | 506.5 | 0.00015357 | 10662 | 0.071068 | 4888 | 1.1062e-05 | 10969
CAYUCOS 1101W58 | CAYUCOS 1101 | 182551101 |  | 18.8093 | 1.0002 |  | 383.5 | 0.00016438 | 10540 | 0.067384 | 5681 | 1.105e-05 | 10970
TEMPLETON 2109P14 | TEMPLETON 2109 | 183052109 |  | 27.2718 | 0.76708 |  | 502 | 0.00016474 | 10536 | 0.067035 | 5976 | 1.1042e-05 | 10971
SAN ARDO 110265604 | SAN ARDO 1102 | 182191102 |  | 7.679 | 0.059804 |  | 160 | 0.00016429 | 10544 | 0.06726 | 5758 | 1.1039e-05 | 10972
KERMAN 1104928231 | KERMAN 1104 | 252711104 |  | 1.7681 | 0 |  | 28.5 | 0.00014252 | 10768 | 0.0774 | 3397 | 1.1031e-05 | 10973
CHOLAME 1101X14 | CHOLAME 1101 | 182561101 |  | 28.1973 | 1.4218 |  | 517.5 | 0.00016198 | 10574 | 0.067904 | 5436 | 1.1024e-05 | 10974
OCEANO 1102749231 | OCEANO 1102 | 182601102 | FALSE | 11.4796 | 0.82364 | 5.5473 | 157.5 | 2.5525e-05 | 11146 | 0.60228 | 2733 | 1.0992e-05 | 10975
CUYAMA 1104CB | CUYAMA 1104 | 253141104 |  | 18.0648 | 0.10557 |  | 309.1667 | 0.00015047 | 10702 | 0.074439 | 4495 | 1.097e-05 | 10976
CHOLAME 1101R96 | CHOLAME 1101 | 182561101 |  | 12.7512 | 1.0771 |  | 253 | 0.00016271 | 10564 | 0.067274 | 5748 | 1.0944e-05 | 10977
TWISSELMAN 2105623146 | TWISSELMAN 2105 | 254402105 |  | 14.4179 | 0.057484 |  | 243.5 | 0.00014797 | 10720 | 0.074759 | 4450 | 1.0928e-05 | 10978
OROSI 11037901F | OROSI 1103 | 252841103 |  | 6.6506 | 1.2157 |  | 133.5 | 0.00015691 | 10631 | 0.06981 | 5073 | 1.0915e-05 | 10979
CORNING 110185122 | CORNING 1101 | 103331101 |  | 0.99451 | 0 |  | 16 | 0.00016177 | 10577 | 0.06723 | 5778 | 1.0884e-05 | 10980
LAS POSITAS 2110MR195 | LAS POSITAS 2110 | 14402110 |  | 14.1596 | 0.23407 |  | 275.5 | 0.00015675 | 10634 | 0.069384 | 5131 | 1.0851e-05 | 10981
MORRO BAY 1101424198 | MORRO BAY 1101 | 183011101 |  | 0.81909 | 0.69824 |  | 14 | 0.00018574 | 10266 | 0.056057 | 7573 | 1.0844e-05 | 10982
CORTINA 11013058 | CORTINA 1101 | 63121101 |  | 4.5029 | 0.077319 |  | 73.5 | 0.00015717 | 10626 | 0.069554 | 5111 | 1.0844e-05 | 10983
CORTINA 110130014 | CORTINA 1101 | 63121101 |  | 4.0375 | 0.094138 |  | 66.5 | 0.00015845 | 10613 | 0.068877 | 5208 | 1.0837e-05 | 10984
SMYRNA 110496808 | SMYRNA 1104 | 253551104 |  | 7.4695 | 0.17767 |  | 130.5 | 0.00013982 | 10790 | 0.0774 | 3397 | 1.0822e-05 | 10985
OLD RIVER 1103596200 | OLD RIVER 1103 | 252821103 |  | 0.018753 | 0 |  | 0.5 | 0.00013968 | 10792 | 0.0774 | 3397 | 1.0811e-05 | 10986
HAMMONDS 110448426 | HAMMONDS 1104 | 253401104 |  | 0.028458 | 0 |  | 0.5 | 0.00013921 | 10797 | 0.0774 | 3397 | 1.0775e-05 | 10987
SMYRNA 1105238156 | SMYRNA 1105 | 253551105 |  | 0.03139 | 0 |  | 1.5 | 0.0001389 | 10801 | 0.0774 | 3397 | 1.0751e-05 | 10988
CRESSEY 2104947844 | CRESSEY 2104 | 254702104 |  | 6.6841 | 0.034184 |  | 119 | 0.00013836 | 10807 | 0.077313 | 3455 | 1.0695e-05 | 10989
WOODWARD 210892960 | WOODWARD 2108 | 255292108 |  | 1.0589 | 0.027011 |  | 17.5 | 0.00015777 | 10620 | 0.067594 | 5553 | 1.0658e-05 | 10990
NEWHALL 110911510 | NEWHALL 1109 | 254461109 |  | 7.8352 | 0.11007 |  | 127.5 | 0.00013756 | 10817 | 0.077338 | 3423 | 1.062e-05 | 10991
CARNERAS 1103430670 | CARNERAS 1103 | 252321103 |  | 17.0353 | 0.019714 |  | 282.5 | 0.00015707 | 10628 | 0.067637 | 5532 | 1.0579e-05 | 10992
WHEELER RIDGE 11012878 | WHEELER RIDGE 1101 | 253481101 |  | 5.2681 | 0 |  | 101.5 | 0.00015013 | 10707 | 0.070124 | 5015 | 1.0547e-05 | 10993
PASO ROBLES 1107826368 | PASO ROBLES 1107 | 182611107 |  | 13.7303 | 0.96125 |  | 241.5 | 0.00015519 | 10645 | 0.067608 | 5542 | 1.0499e-05 | 10994
MCKITTRICK 11011639 | MCKITTRICK 1101 | 252781101 |  | 20.4724 | 0.12784 |  | 326.5 | 0.00015154 | 10682 | 0.069628 | 5097 | 1.0494e-05 | 10995
SAN ARDO 11017094 | SAN ARDO 1101 | 182191101 |  | 4.735 | 0.058429 |  | 99 | 0.00015135 | 10687 | 0.069638 | 5096 | 1.0417e-05 | 10996
HOLLISTER 21054724 | HOLLISTER 2105 | 182492105 |  | 15.138 | 0.49374 |  | 286 | 0.00015405 | 10657 | 0.067407 | 5662 | 1.0411e-05 | 10997
HAMMONDS 110449120 | HAMMONDS 1104 | 253401104 |  | 1.5524 | 0.012817 |  | 26 | 0.00013404 | 10848 | 0.0774 | 3397 | 1.0375e-05 | 10998
PASO ROBLES 1108R10 | PASO ROBLES 1108 | 182611108 |  | 3.7108 | 0.086936 |  | 66 | 0.00015473 | 10649 | 0.067 | 6057 | 1.0367e-05 | 10999
COTTLE 170178452 | COTTLE 1701 | 163711701 |  | 18.8299 | 0.52394 |  | 352.5 | 0.00015372 | 10661 | 0.067317 | 5718 | 1.0338e-05 | 11000
CORRAL 110314716 | CORRAL 1103 | 162991103 |  | 17.6745 | 0.42942 |  | 340.5 | 0.00015278 | 10671 | 0.067282 | 5743 | 1.0315e-05 | 11001
DAIRYLAND 1105845552 | DAIRYLAND 1105 | 252421105 |  | 0.026744 | 0 |  | 0.5 | 0.00013259 | 10860 | 0.0774 | 3397 | 1.0263e-05 | 11002
CAYUCOS 1101W14 | CAYUCOS 1101 | 182551101 |  | 13.5536 | 0.35757 |  | 282.5 | 0.00015279 | 10670 | 0.067043 | 5955 | 1.0245e-05 | 11003
PEABODY 210718342 | PEABODY 2107 | 63642107 |  | 8.8262 | 0.15231 |  | 173.5 | 0.00014343 | 10762 | 0.073564 | 4600 | 1.0244e-05 | 11004
LIVINGSTON 11014080 | LIVINGSTON 1101 | 252261101 |  | 19.0451 | 0.56124 |  | 363 | 0.00013247 | 10861 | 0.077333 | 3429 | 1.0243e-05 | 11005
MC ARTHUR 110290546 | MC ARTHUR 1102 | 103491102 |  | 3.0711 | 0.18348 |  | 57.5 | 0.00014962 | 10709 | 0.068176 | 5364 | 1.0242e-05 | 11006
LOGAN CREEK 21022226 | LOGAN CREEK 2102 | 103142102 |  | 11.3097 | 0.27034 |  | 200 | 0.00014411 | 10754 | 0.071484 | 4833 | 1.0234e-05 | 11007
CORNING 11021900 | CORNING 1102 | 103331102 |  | 15.0553 | 0.24885 |  | 267.5 | 0.00015168 | 10680 | 0.067484 | 5612 | 1.0233e-05 | 11008
TEMPLETON 2112R98 | TEMPLETON 2112 | 183052112 |  | 14.7165 | 0.47468 |  | 269 | 0.00015219 | 10675 | 0.06708 | 5920 | 1.0212e-05 | 11009
COPPERMINE 1104R3170 | COPPERMINE 1104 | 252411104 |  | 3.1908 | 0.27664 |  | 60 | 0.0001522 | 10674 | 0.067 | 6057 | 1.0198e-05 | 11010
BORDEN 1101349432 | BORDEN 1101 | 255121101 |  | 3.0132 | 0.043931 |  | 49.5 | 0.00013144 | 10872 | 0.0774 | 3397 | 1.0173e-05 | 11011
DAIRYLAND 1105422500 | DAIRYLAND 1105 | 252421105 |  | 4.5324 | 0.035281 |  | 74.5 | 0.0001313 | 10874 | 0.0774 | 3397 | 1.0163e-05 | 11012
CARUTHERS 1101646366 | CARUTHERS 1101 | 252371101 |  | 0.2448 | 0 |  | 3.5 | 0.00013072 | 10879 | 0.0774 | 3397 | 1.0117e-05 | 11013
MADISON 210163762 | MADISON 2101 | 63172101 |  | 6.4115 | 0.60091 |  | 124 | 0.0001423 | 10770 | 0.071806 | 4792 | 1.0106e-05 | 11014
PANOCHE 11034010 | PANOCHE 1103 | 253671103 |  | 6.9144 | 0.19653 |  | 113.5 | 0.00015078 | 10696 | 0.067005 | 6030 | 1.0103e-05 | 11015
MERCED FALLS 1102889524 | MERCED FALLS 1102 | 252811102 |  | 10.4124 | 0.091951 |  | 222 | 0.00015016 | 10706 | 0.067086 | 5914 | 1.008e-05 | 11016
HOLLISTER 21054042 | HOLLISTER 2105 | 182492105 |  | 17.4518 | 1.1771 |  | 331 | 0.00014895 | 10712 | 0.067584 | 5561 | 1.0071e-05 | 11017
CHOLAME 2102X18 | CHOLAME 2102 | 182562102 |  | 4.781 | 0 |  | 96.5 | 0.0001481 | 10718 | 0.067601 | 5549 | 1.003e-05 | 11018
SAN MIGUEL 1104R54 | SAN MIGUEL 1104 | 182661104 |  | 15.426 | 0.63649 |  | 269.5 | 0.00014706 | 10727 | 0.06781 | 5472 | 9.9805e-06 | 11019
CUYAMA 2101952122 | CUYAMA 2101 | 253142101 |  | 20.4489 | 0.38035 |  | 354.5 | 0.00014604 | 10740 | 0.069646 | 5092 | 9.9264e-06 | 11020
MISSION (X) 1111CB | MISSION (X) 1111 | 22011111 |  | 0 | 0.11312 |  | 4.3333 | 0.00018698 | 10243 | 0.053073 | 8250 | 9.9235e-06 | 11021
GOOSE LAKE 1103559711 | GOOSE LAKE 1103 | 254201103 |  | 4.3188 | 0.10284 |  | 73.5 | 0.00012812 | 10900 | 0.0774 | 3397 | 9.9169e-06 | 11022
COTTLE 1708728510 | COTTLE 1708 | 163711708 |  | 17.9849 | 0 |  | 314.5 | 0.00013951 | 10793 | 0.071145 | 4876 | 9.8922e-06 | 11023
NEWHALL 111111941 | NEWHALL 1111 | 254461111 |  | 4.8545 | 0.2299 |  | 99.5 | 0.00012761 | 10905 | 0.0774 | 3397 | 9.877e-06 | 11024
PENTLAND 1101CB | PENTLAND 1101 | 255311101 |  | 0.0086239 | 0 |  | 1 | 0.00014724 | 10723 | 0.067 | 6057 | 9.8651e-06 | 11025
CUYAMA 11031635 | CUYAMA 1103 | 253141103 |  | 16.4439 | 0.36496 |  | 324.5 | 0.00014386 | 10758 | 0.068551 | 5275 | 9.8475e-06 | 11026
HAMMONDS 11019760 | HAMMONDS 1101 | 253401101 |  | 27.16 | 0.56186 |  | 463.5 | 0.00013886 | 10802 | 0.070669 | 4937 | 9.7806e-06 | 11027
HONCUT 1102478754 | HONCUT 1102 | 103211102 |  | 18.1384 | 0.51821 |  | 333.5 | 0.00014513 | 10746 | 0.067132 | 5871 | 9.7421e-06 | 11028
DIVIDE 110398166 | DIVIDE 1103 | 182571103 |  | 4.5486 | 0.10257 |  | 82.5 | 0.00014439 | 10753 | 0.067202 | 5807 | 9.7063e-06 | 11029
SMYRNA 110598496 | SMYRNA 1105 | 253551105 |  | 6.3294 | 0.06105 |  | 108 | 0.00012606 | 10919 | 0.077109 | 3684 | 9.6894e-06 | 11030
COTTLE 1708968888 | COTTLE 1708 | 163711708 |  | 18.7623 | 0.21829 |  | 355.5 | 0.00014388 | 10757 | 0.067449 | 5637 | 9.6845e-06 | 11031
COTTLE 170139546 | COTTLE 1701 | 163711701 |  | 8.2595 | 0 |  | 147.5 | 0.00014044 | 10784 | 0.068781 | 5227 | 9.64e-06 | 11032
COTATI 1105893 | COTATI 1105 | 42271105 | TRUE | 10.5487 | 0.26874 | 0.069848 | 199.5 | 0.00014377 | 10760 | 0.067038 | 5962 | 9.638e-06 | 11033
DAIRYLAND 1111CUS8188 | DAIRYLAND 1111 | 252421111 |  | 0.011829 | 0 |  | 0.5 | 0.00012439 | 10928 | 0.0774 | 3397 | 9.6279e-06 | 11034
ANTELOPE 11012656 | ANTELOPE 1101 | 252021101 |  | 13.0258 | 0.11735 |  | 227.5 | 0.00013387 | 10849 | 0.072273 | 4747 | 9.5894e-06 | 11035
TIVY VALLEY 1107599142 | TIVY VALLEY 1107 | 252941107 | TRUE | 2.2614 | 0.13268 | 0.022822 | 41 | 0.00013715 | 10819 | 0.069542 | 5116 | 9.5816e-06 | 11036
SAN ARDO 1101CB | SAN ARDO 1101 | 182191101 |  | 8.7248 | 0.023655 |  | 170 | 0.00014119 | 10774 | 0.068149 | 5369 | 9.5803e-06 | 11037
CORRAL 110133616 | CORRAL 1101 | 162991101 |  | 1.018 | 0 |  | 17.5 | 0.0001423 | 10769 | 0.067 | 6057 | 9.5344e-06 | 11038
SMYRNA 11013685 | SMYRNA 1101 | 253551101 |  | 2.4532 | 0 |  | 41.8333 | 0.00012251 | 10938 | 0.0774 | 3396 | 9.482e-06 | 11039
OILFIELDS 110293788 | OILFIELDS 1102 | 182391102 |  | 17.7939 | 0.59539 |  | 361.8333 | 0.00013996 | 10787 | 0.067603 | 5547 | 9.4571e-06 | 11040
CHOWCHILLA 110466907 | CHOWCHILLA 1104 | 254101104 |  | 3.8955 | 0.053986 |  | 67.5 | 0.00012363 | 10935 | 0.076167 | 4136 | 9.4501e-06 | 11041
PUTAH CREEK 1105665952 | PUTAH CREEK 1105 | 63681105 | TRUE | 0.97916 | 0.086832 | 0.060491 | 17.5 | 0.00014012 | 10785 | 0.067409 | 5661 | 9.4436e-06 | 11042
PUTAH CREEK 110546162 | PUTAH CREEK 1105 | 63681105 |  | 1.7593 | 0.071288 |  | 30.5 | 0.00013758 | 10816 | 0.068992 | 5192 | 9.4252e-06 | 11043
TEMPLETON 2109R50 | TEMPLETON 2109 | 183052109 |  | 26.3917 | 1.5874 |  | 451 | 0.00013914 | 10798 | 0.067325 | 5714 | 9.3944e-06 | 11044
WHEATLAND 110591170 | WHEATLAND 1105 | 152811105 |  | 26.9376 | 0.50673 |  | 543 | 0.00013793 | 10813 | 0.067882 | 5446 | 9.3432e-06 | 11045
LE GRAND 1104257152 | LE GRAND 1104 | 255361104 |  | 12.6418 | 0.065752 |  | 208 | 0.00013611 | 10829 | 0.068858 | 5214 | 9.3166e-06 | 11046
MADISON 21011943 | MADISON 2101 | 63172101 |  | 2.899 | 0.098698 |  | 51.5 | 0.00013616 | 10828 | 0.068623 | 5258 | 9.2779e-06 | 11047
PANOCHE 110390540 | PANOCHE 1103 | 253671103 |  | 13.1808 | 0.13785 |  | 250.5 | 0.00012854 | 10894 | 0.072585 | 4710 | 9.2384e-06 | 11048
CLEAR LAKE 1101881362 | CLEAR LAKE 1101 | 42141101 | TRUE | 1.123 | 0.03178 | 0.02134 | 18.5 | 0.00013491 | 10840 | 0.068085 | 5389 | 9.1942e-06 | 11049
MC ARTHUR 11021324 | MC ARTHUR 1102 | 103491102 | TRUE | 24.3493 | 0.83095 | 0.097199 | 424.5 | 0.00013465 | 10842 | 0.068189 | 5361 | 9.1823e-06 | 11050
CHOWCHILLA 110359800 | CHOWCHILLA 1103 | 254101103 |  | 3.2631 | 0.086282 |  | 59.5 | 0.00011846 | 10961 | 0.0774 | 3397 | 9.1691e-06 | 11051
OLEMA 1101512 | OLEMA 1101 | 42291101 |  | 6.5626 | 0.11184 |  | 132 | 0.00013621 | 10827 | 0.067115 | 5885 | 9.1427e-06 | 11052
GUERNSEY 1101700790 | GUERNSEY 1101 | 252661101 |  | 0.053481 | 0 |  | 2 | 0.00011761 | 10971 | 0.0774 | 3397 | 9.1029e-06 | 11053
STOREY 11095270 | STOREY 1109 | 254611109 |  | 32.7253 | 0.32881 |  | 625.5 | 0.00013555 | 10836 | 0.067094 | 5905 | 9.0946e-06 | 11054
CORRAL 1101D1495 | CORRAL 1101 | 162991101 |  | 4.4204 | 0.14294 |  | 81 | 0.00013358 | 10850 | 0.068156 | 5367 | 9.0886e-06 | 11055
GLENN 11012012 | GLENN 1101 | 102601101 | TRUE | 30.0032 | 0.30672 | 0.26324 | 580.5 | 8.7557e-05 | 11088 | 0.1121 | 3287 | 9.0809e-06 | 11056
MESA 1104CB | MESA 1104 | 182821104 |  | 5.4374 | 0.42582 |  | 79.3333 | 0.00013516 | 10838 | 0.066989 | 6064 | 9.0569e-06 | 11057
DAIRYLAND 1112163950 | DAIRYLAND 1112 | 252421112 |  | 21.4704 | 0.51516 |  | 365.5 | 0.00011687 | 10973 | 0.077333 | 3428 | 9.0347e-06 | 11058
MISSION (X) 1104CB | MISSION (X) 1104 | 22011104 |  | 0 | 0.1172 |  | 3 | 0.00016949 | 10492 | 0.053073 | 8251 | 8.9955e-06 | 11059
CORNING 110154906 | CORNING 1101 | 103331101 |  | 21.5264 | 0.20913 |  | 416.5 | 0.0001292 | 10887 | 0.069082 | 5179 | 8.9235e-06 | 11060
WOODWARD 2108935396 | WOODWARD 2108 | 255292108 |  | 0.2794 | 0.01904 |  | 4 | 0.00013232 | 10864 | 0.067258 | 5759 | 8.8991e-06 | 11061
SAN ARDO 1102502 | SAN ARDO 1102 | 182191102 |  | 22.2716 | 0.49886 |  | 407 | 0.00011887 | 10958 | 0.21929 | 3121 | 8.8837e-06 | 11062
BRENTWOOD 2105B569R | BRENTWOOD 2105 | 14592105 |  | 3.5403 | 0 |  | 61.5 | 0.0001319 | 10867 | 0.067003 | 6042 | 8.8373e-06 | 11063
GUERNSEY 110178276 | GUERNSEY 1101 | 252661101 |  | 0.44897 | 0 |  | 8 | 0.00011402 | 10990 | 0.0774 | 3397 | 8.8253e-06 | 11064
ANITA 1106552724 | ANITA 1106 | 102841106 | TRUE | 14.6703 | 0.23153 | 0.47837 | 252.5 | 0.00012415 | 10929 | 0.072002 | 4776 | 8.7973e-06 | 11065
RAINBOW 1106D2116 | RAINBOW 1106 | 254441106 |  | 2.2552 | 0.49977 |  | 42.5 | 0.00012565 | 10922 | 0.070181 | 5003 | 8.7682e-06 | 11066
SALMON CREEK 1101660 | SALMON CREEK 1101 | 43161101 |  | 1.5 | 0.018231 |  | 32.5 | 0.0001314 | 10873 | 0.06696 | 6079 | 8.7271e-06 | 11067
TEMPLETON 2110R90 | TEMPLETON 2110 | 183052110 |  | 3.2515 | 0.17936 |  | 59.5 | 0.0001301 | 10884 | 0.067038 | 5963 | 8.7254e-06 | 11068
VASCO 1103964102 | VASCO 1103 | 13751103 |  | 7.8373 | 0.20646 |  | 140 | 0.00012641 | 10916 | 0.070299 | 4980 | 8.7143e-06 | 11069
TIVY VALLEY 1107CB | TIVY VALLEY 1107 | 252941107 | TRUE | 22.0031 | 0.6299 | 0.01563 | 390.5 | 0.00012893 | 10891 | 0.067457 | 5633 | 8.6844e-06 | 11070
STOREY 110921859 | STOREY 1109 | 254611109 |  | 2.9986 | 0.040667 |  | 46.5 | 0.00011211 | 11005 | 0.0774 | 3397 | 8.677e-06 | 11071
REEDLEY 1112477952 | REEDLEY 1112 | 252341112 | TRUE | 1.6113 | 0.14708 | 0.090712 | 27.5 | 0.00012495 | 10924 | 0.067945 | 5415 | 8.5646e-06 | 11072
DIVIDE 110323614 | DIVIDE 1103 | 182571103 |  | 3.0905 | 0.024026 |  | 56.5 | 0.00012733 | 10907 | 0.067086 | 5916 | 8.5417e-06 | 11073
RUSS RANCH 1101CB | RUSS RANCH 1101 | 192471101 |  | 0.022578 | 0 |  | 1.5 | 0.00012574 | 10921 | 0.067385 | 5679 | 8.4732e-06 | 11074
VALLEY HOME 17031532 | VALLEY HOME 1703 | 162981703 |  | 35.7999 | 0.45929 |  | 617.5 | 0.00012478 | 10927 | 0.067699 | 5509 | 8.4311e-06 | 11075
PASO ROBLES 110764703 | PASO ROBLES 1107 | 182611107 |  | 1.2138 | 0.091846 |  | 24.5 | 0.00012563 | 10923 | 0.067 | 6057 | 8.417e-06 | 11076
CUYAMA 1103934590 | CUYAMA 1103 | 253141103 |  | 8.5676 | 0.10005 |  | 161.5 | 0.00010966 | 11014 | 0.077739 | 3393 | 8.3762e-06 | 11077
DIVIDE 110348160 | DIVIDE 1103 | 182571103 |  | 10.3502 | 0 |  | 202.25 | 0.00012382 | 10931 | 0.067277 | 5747 | 8.3231e-06 | 11078
LE GRAND 11045010 | LE GRAND 1104 | 255361104 |  | 18.7604 | 0.2268 |  | 354.5 | 0.00012025 | 10949 | 0.068719 | 5238 | 8.2875e-06 | 11079
COTTLE 170144183 | COTTLE 1701 | 163711701 |  | 0.080714 | 0 |  | 1 | 0.00011815 | 10967 | 0.070112 | 5019 | 8.2837e-06 | 11080
VALLEY HOME 1703768534 | VALLEY HOME 1703 | 162981703 |  | 0.94412 | 0.012399 |  | 17.5 | 0.00010643 | 11032 | 0.0774 | 3397 | 8.2373e-06 | 11081
CARRIZO PLAINS 11013527 | CARRIZO PLAINS 1101 | 253461101 |  | 55.2389 | 0.94719 |  | 936 | 0.00012199 | 10941 | 0.067437 | 5647 | 8.2276e-06 | 11082
GANSO 1104685998 | GANSO 1104 | 254541104 |  | 0.018635 | 0 |  | 0.5 | 0.00010585 | 11035 | 0.0774 | 3397 | 8.1928e-06 | 11083
HARDWICK 1102249398 | HARDWICK 1102 | 253711102 |  | 0.021021 | 0 |  | 0.5 | 0.00010547 | 11040 | 0.0774 | 3397 | 8.1632e-06 | 11084
EL CERRITO G 1114BR190 | EL CERRITO G 1114 | 12501114 |  | 0.10306 | 0 |  | 1.3333 | 0.00015344 | 10665 | 0.053073 | 8251 | 8.1436e-06 | 11085
RUSS RANCH 110196276 | RUSS RANCH 1101 | 192471101 |  | 0.19413 | 0 |  | 3.5 | 0.00011971 | 10952 | 0.067355 | 5699 | 8.0626e-06 | 11086
REEDLEY 1104243924 | REEDLEY 1104 | 252341104 |  | 0.51895 | 0.096478 |  | 12 | 0.00011799 | 10968 | 0.067867 | 5454 | 8.0153e-06 | 11087
COARSEGOLD 210310300 | COARSEGOLD 2103 | 254432103 |  | 9.0005 | 0.1256 |  | 169 | 0.00011796 | 10969 | 0.067158 | 5844 | 7.9148e-06 | 11088
LE GRAND 1104RUSE | LE GRAND 1104 | 255361104 |  | 0.16441 | 0 |  | 4 | 0.00011729 | 10972 | 0.067 | 6057 | 7.8581e-06 | 11089
POTRERO PP (A) 1112CB | POTRERO PP (A) 1112 | 22031112 |  | 0.032012 | 0.1219 |  | 4.8333 | 0.00014698 | 10729 | 0.053073 | 8251 | 7.8007e-06 | 11090
TEMPLETON 2109P68 | TEMPLETON 2109 | 183052109 |  | 22.0588 | 0.35949 |  | 399.5 | 0.00011604 | 10978 | 0.067 | 6057 | 7.7747e-06 | 11091
TEMPLETON 2109R34 | TEMPLETON 2109 | 183052109 |  | 30.241 | 0.28463 |  | 549.5 | 0.0001137 | 10992 | 0.067492 | 5608 | 7.6856e-06 | 11092
OCEANO 1104Q04 | OCEANO 1104 | 182601104 |  | 2.5965 | 2.8072 |  | 48 | 0.00013908 | 10800 | 0.057298 | 7394 | 7.6642e-06 | 11093
PURISIMA 1101Y40 | PURISIMA 1101 | 182971101 |  | 10.4026 | 0.08321 |  | 192.5 | 0.00011304 | 10995 | 0.067467 | 5624 | 7.6482e-06 | 11094
CHOLAME 1101X12 | CHOLAME 1101 | 182561101 |  | 20.2678 | 0.33996 |  | 393 | 0.00011133 | 11009 | 0.067925 | 5425 | 7.5853e-06 | 11095
DAIRYLAND 110577794 | DAIRYLAND 1105 | 252421105 |  | 10.8568 | 0.076391 |  | 179 | 9.7839e-05 | 11061 | 0.0774 | 3397 | 7.5727e-06 | 11096
VALLEY HOME 170339660 | VALLEY HOME 1703 | 162981703 |  | 17.1667 | 0.16691 |  | 325.5 | 0.00011021 | 11011 | 0.067797 | 5475 | 7.4713e-06 | 11097
COPPERMINE 1104R755 | COPPERMINE 1104 | 252411104 |  | 36.9871 | 1.0964 |  | 707.5 | 0.0001101 | 11013 | 0.06706 | 5936 | 7.393e-06 | 11098
CHOLAME 1101R22 | CHOLAME 1101 | 182561101 |  | 20.76 | 0.30211 |  | 394 | 0.00010891 | 11020 | 0.067541 | 5579 | 7.3926e-06 | 11099
KING CITY 1106500 | KING CITY 1106 | 182031106 |  | 26.0347 | 0.77479 |  | 536 | 0.00010682 | 11029 | 0.068953 | 5199 | 7.3612e-06 | 11100
PIT NO 1 1101LR-RC-A | PIT NO 1 1101 | 103721101 |  | 0.0066415 | 0 |  | 0.5 | 0.00010954 | 11015 | 0.067 | 6057 | 7.3392e-06 | 11101
CORTINA 1101107710 | CORTINA 1101 | 63121101 |  | 0.01854 | 0 |  | 1 | 9.3781e-05 | 11068 | 0.0774 | 3397 | 7.2586e-06 | 11102
PEORIA 17041837 | PEORIA 1704 | 163781704 |  | 8.8612 | 0.086804 |  | 180.5 | 0.00010581 | 11037 | 0.068244 | 5349 | 7.2201e-06 | 11103
EL CAPITAN 1103975920 | EL CAPITAN 1103 | 253881103 |  | 3.3531 | 0 |  | 57 | 0.00010616 | 11033 | 0.067225 | 5783 | 7.1468e-06 | 11104
SAN MIGUEL 1104R88 | SAN MIGUEL 1104 | 182661104 |  | 26.4143 | 0.29027 |  | 469 | 0.000106 | 11034 | 0.067244 | 5767 | 7.1297e-06 | 11105
LOS OSITOS 21031132 | LOS OSITOS 2103 | 182082103 |  | 30.3492 | 0.5138 |  | 585.5 | 0.00010041 | 11046 | 0.070506 | 4951 | 7.0904e-06 | 11106
OCEANO 1103597140 | OCEANO 1103 | 182601103 |  | 1.5598 | 0.38487 |  | 26 | 0.00010744 | 11023 | 0.065319 | 6389 | 7.084e-06 | 11107
TIVY VALLEY 1107248306 | TIVY VALLEY 1107 | 252941107 |  | 8.5779 | 0.21605 |  | 150.5 | 9.9733e-05 | 11052 | 0.069902 | 5064 | 6.9523e-06 | 11108
ANGIOLA 11028280 | ANGIOLA 1102 | 252151102 |  | 23.7559 | 0.11128 |  | 314.5 | 8.8982e-05 | 11085 | 0.076792 | 3891 | 6.8737e-06 | 11109
CORCORAN 1112714124 | CORCORAN 1112 | 252171112 |  | 15.7835 | 0.27052 |  | 215 | 9.1422e-05 | 11079 | 0.076485 | 4021 | 6.8281e-06 | 11110
MISSION (X) 1107CB | MISSION (X) 1107 | 22011107 |  | 0 | 0.045319 |  | 1 | 0.00012811 | 10901 | 0.053073 | 8251 | 6.7989e-06 | 11111
MAINE PRAIRIE 0401CB | MAINE PRAIRIE 0401 | 68670401 |  | 0.06262 | 0 |  | 2 | 8.6925e-05 | 11092 | 0.0774 | 3397 | 6.7279e-06 | 11112
COTTLE 170889662 | COTTLE 1708 | 163711708 |  | 38.4937 | 0.49995 |  | 746.5 | 9.9091e-05 | 11054 | 0.067683 | 5515 | 6.7119e-06 | 11113
MORRO BAY 110187487 | MORRO BAY 1101 | 183011101 |  | 5.0984 | 0.22157 |  | 98 | 9.9575e-05 | 11053 | 0.067015 | 6011 | 6.6725e-06 | 11114
CHOLAME 2102X08 | CHOLAME 2102 | 182562102 |  | 39.5412 | 0.46403 |  | 793.5 | 9.4322e-05 | 11067 | 0.068826 | 5219 | 6.4856e-06 | 11115
TRES PINOS 11114064 | TRES PINOS 1111 | 183221111 |  | 12.9161 | 0.16757 |  | 271 | 9.3725e-05 | 11069 | 0.067753 | 5495 | 6.339e-06 | 11116
WOODWARD 2108979850 | WOODWARD 2108 | 255292108 |  | 23.6447 | 0.34386 |  | 435.5 | 9.3294e-05 | 11072 | 0.067725 | 5504 | 6.3027e-06 | 11117
CHOLAME 11015939 | CHOLAME 1101 | 182561101 |  | 3.2102 | 0 |  | 60.5 | 9.0979e-05 | 11080 | 0.067823 | 5469 | 6.1785e-06 | 11118
TEMPLETON 2109R52 | TEMPLETON 2109 | 183052109 |  | 26.1703 | 0.76248 |  | 449 | 9.0363e-05 | 11083 | 0.067058 | 5937 | 6.0645e-06 | 11119
HIGHWAY 1101200662 | HIGHWAY 1101 | 42651101 |  | 0.056844 | 0 |  | 0.5 | 8.6073e-05 | 11094 | 0.067175 | 5831 | 5.7819e-06 | 11120
MISSION (X) 1120CB | MISSION (X) 1120 | 22011120 |  | 0 | 0.012818 |  | 1 | 0.00010657 | 11030 | 0.053073 | 8251 | 5.6561e-06 | 11121
MORRO BAY 1101W02 | MORRO BAY 1101 | 183011101 |  | 3.2881 | 3.6385 |  | 51.1667 | 0.00010438 | 11042 | 0.053073 | 8251 | 5.5395e-06 | 11122
FULTON 110257686 | FULTON 1102 | 42561102 |  | 0.013598 | 0 |  | 0.5 | 8.0277e-05 | 11103 | 0.068853 | 5215 | 5.5273e-06 | 11123
COPPERMINE 1104CB | COPPERMINE 1104 | 252411104 |  | 0.90206 | 0.092853 |  | 14.8333 | 8.0831e-05 | 11102 | 0.067 | 6057 | 5.4157e-06 | 11124
MESA 1103M70 | MESA 1103 | 182821103 |  | 7.8884 | 1.393 |  | 131 | 7.1708e-05 | 11115 | 0.065927 | 6289 | 4.7842e-06 | 11125
ALPINE 1102CB | ALPINE 1102 | 163561102 |  | 0 | 0.05754 |  | 1 | 0.00011226 | 11003 | 0.053073 | 8251 | 4.4754e-06 | 11126
PURISIMA 1101CUSTREC | PURISIMA 1101 | 182971101 |  | 0.012189 | 0 |  | 0.5 | 6.4891e-05 | 11117 | 0.067 | 6057 | 4.3477e-06 | 11127
OCEANO 1108CB | OCEANO 1108 | 182601108 |  | 4.4908 | 4.3471 |  | 79.5 | 7.9518e-05 | 11108 | 0.053375 | 8145 | 4.2411e-06 | 11128
MORRO BAY 110247584 | MORRO BAY 1102 | 183011102 |  | 0.019648 | 0 |  | 0.5 | 6.0387e-05 | 11120 | 0.067 | 6057 | 4.0459e-06 | 11129
OCEANO 110356012 | OCEANO 1103 | 182601103 |  | 2.6041 | 2.2475 |  | 48 | 6.1402e-05 | 11119 | 0.062574 | 6704 | 3.7564e-06 | 11130
MESA 1103M72 | MESA 1103 | 182821103 |  | 6.6716 | 0.78593 |  | 98.5 | 1.88e-05 | 11151 | 0.25138 | 3080 | 3.697e-06 | 11131
MESA 1102CB | MESA 1102 | 182821102 |  | 3.6067 | 0.53845 |  | 60.8333 | 4.8642e-05 | 11129 | 0.067853 | 5457 | 3.2668e-06 | 11132
MORRO BAY 1102W24 | MORRO BAY 1102 | 183011102 |  | 6.1402 | 5.2604 |  | 91 | 4.9539e-05 | 11127 | 0.063788 | 6570 | 3.161e-06 | 11133
WOODCHUCK 2101R2770 | WOODCHUCK 2101 | 254912101 |  | 1.8129 | 0 |  | 26.5 | 4.4329e-05 | 11132 | 0.067629 | 5537 | 3.0223e-06 | 11134
MORRO BAY 1101W06 | MORRO BAY 1101 | 183011101 |  | 1.6569 | 1.4838 |  | 23 | 5.0138e-05 | 11126 | 0.059734 | 7048 | 2.9968e-06 | 11135
MORRO BAY 1102V84 | MORRO BAY 1102 | 183011102 | TRUE | 9.8692 | 9.1317 | 0.15637 | 149.5 | 5.0783e-05 | 11125 | 0.059053 | 7151 | 2.953e-06 | 11136
MORRO BAY 1101W04 | MORRO BAY 1101 | 183011101 | TRUE | 2.5784 | 2.698 | 0.20346 | 35 | 5.3382e-05 | 11123 | 0.053763 | 8009 | 2.8886e-06 | 11137
MESA 1103M68 | MESA 1103 | 182821103 |  | 2.9429 | 0.36383 |  | 48.5 | 1.7523e-05 | 11154 | 0.11708 | 3272 | 2.8257e-06 | 11138
MORRO BAY 1102V80 | MORRO BAY 1102 | 183011102 | TRUE | 1.9858 | 0.99617 | 0.029711 | 29 | 4.3385e-05 | 11133 | 0.064908 | 6450 | 2.756e-06 | 11139
MESA 1103236053 | MESA 1103 | 182821103 |  | 4.4548 | 0.011092 |  | 68.3333 | 4.0217e-05 | 11134 | 0.067134 | 5868 | 2.6945e-06 | 11140
OCEANO 110856014 | OCEANO 1108 | 182601108 |  | 1.5269 | 1.0821 |  | 24 | 4.8558e-05 | 11130 | 0.053943 | 7971 | 2.63e-06 | 11141
MORRO BAY 1102V86 | MORRO BAY 1102 | 183011102 |  | 8.7848 | 8.7928 |  | 143.5 | 4.6915e-05 | 11131 | 0.055051 | 7745 | 2.5717e-06 | 11142
MESA 1103M92 | MESA 1103 | 182821103 |  | 6.8234 | 1.5562 |  | 115.5 | 3.3448e-05 | 11142 | 0.066516 | 6183 | 2.2245e-06 | 11143
MESA 1103CB | MESA 1103 | 182821103 |  | 5.4902 | 2.5277 |  | 77.3333 | 3.4264e-05 | 11140 | 0.065016 | 6428 | 2.2228e-06 | 11144
OCEANO 1108597614 | OCEANO 1108 | 182601108 |  | 4.2245 | 4.7213 |  | 76.3333 | 3.8396e-05 | 11135 | 0.055761 | 7629 | 2.1095e-06 | 11145
OCEANO 1102M60 | OCEANO 1102 | 182601102 |  | 5.624 | 1.4832 |  | 92.5 | 3.1176e-05 | 11143 | 0.066191 | 6235 | 2.0742e-06 | 11146
MORRO BAY 11013487 | MORRO BAY 1101 | 183011101 |  | 1.8079 | 1.1777 |  | 29 | 3.4337e-05 | 11139 | 0.058474 | 7224 | 1.9307e-06 | 11147
MESA 1103M90 | MESA 1103 | 182821103 |  | 9.4107 | 0.95739 |  | 156 | 2.5646e-05 | 11145 | 0.066631 | 6158 | 1.7037e-06 | 11148
MESA 110346149 | MESA 1103 | 182821103 |  | 6.4073 | 0.135 |  | 94.5 | 2.4613e-05 | 11148 | 0.066774 | 6126 | 1.6439e-06 | 11149
CLARKSVILLE 210951796 | CLARKSVILLE 2109 | 153612109 |  | 0.123 | 0 |  | 3.5 | 2.1691e-05 | 11149 | 0.067 | 6057 | 1.4533e-06 | 11150
MESA 1103Q18 | MESA 1103 | 182821103 |  | 8.9867 | 0.89144 |  | 142.8333 | 2.1406e-05 | 11150 | 0.067136 | 5866 | 1.4354e-06 | 11151
CORCORAN 1116436137 | CORCORAN 1116 | 252171116 |  | 4.6552 | 0.014794 |  | 38 | 1.5521e-05 | 11157 | 0.07676 | 3903 | 1.1789e-06 | 11152
MESA 11038647 | MESA 1103 | 182821103 |  | 0.91252 | 0.033741 |  | 17 | 1.8536e-05 | 11152 | 0.06447 | 6489 | 1.1764e-06 | 11153
MESA 1103M64 | MESA 1103 | 182821103 |  | 3.9719 | 0.24397 |  | 55.8333 | 1.7323e-05 | 11155 | 0.067017 | 6005 | 1.1609e-06 | 11154
MESA 1103M62 | MESA 1103 | 182821103 |  | 1.1558 | 0.06881 |  | 18 | 1.66e-05 | 11156 | 0.06882 | 5220 | 1.1338e-06 | 11155
CORCORAN 1116174691 | CORCORAN 1116 | 252171116 |  | 6.4587 | 0.0093892 |  | 33.5 | 9.9138e-06 | 11158 | 0.076921 | 3816 | 7.6389e-07 | 11156
WOODWARD 2108CUS1164 | WOODWARD 2108 | 255292108 |  | 0.11955 | 0 |  | 2.5 | 8.4671e-06 | 11159 | 0.067 | 6057 | 5.673e-07 | 11157
WOODCHUCK 2101R9223 | WOODCHUCK 2101 | 254912101 |  | 0.01035 | 0 |  | 0.5 | 4.8617e-06 | 11160 | 0.06728 | 5745 | 3.2709e-07 | 11158
CALPINE 1144276-G | CALPINE 1144 | 48011144 | TRUE | 0.014756 | 0.011529 | 0.026285 |  |  | 11161 | 80.9558 | 36 |  | 11159
CALPINE 1146200-G | CALPINE 1146 | 48011146 | TRUE | 0.0085229 | 0 | 0.0085228 |  |  | 11161 | 62.0029 | 104 |  | 11159
CALPINE 1146394G | CALPINE 1146 | 48011146 | TRUE | 0.011289 | 0 | 0.011289 |  |  | 11161 | 62.0029 | 104 |  | 11159
SMUD 15805CB | SMUD 15805 | 158050401 | TRUE | 0.0070409 | 0 | 0.0070409 |  |  | 11161 | 1.2226 | 2099 |  | 11159
GUERNSEY 1104695204 | GUERNSEY 1104 | 252661104 |  | 0.017125 | 0 |  |  |  | 11161 | 0.0774 | 3397 |  | 11159
GRASS VALLEY 1103CB | GRASS VALLEY 1103 | 152031103 | TRUE | 0.11384 | 0.034909 | 0.14874 |  | 0.0016508 | 65 |  | 8256 |  | 11159
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cs_name
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: feeder_name
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: feeder_id
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: hftd_miles_under_1km
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: prioh_length_miles
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: secoh_length_miles
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: hftd_miles
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: composite_for_system_hardening_wildfire_risk_pixel_weight_count
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_composite_for_system_hardening_probability_ignition_mean
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_composite_for_system_hardening_probability_ignition_mean_rank
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_wildfire_consequence_v3_4_backstop_mean
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_wildfire_consequence_v3_4_backstop_mean_rank
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_composite_for_system_hardening_wildfire_risk_mean
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weighted_composite_for_system_hardening_wildfire_risk_mean_rank

## v2_conductor_pz_summary (hidden)
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | device_operating_number | hftd_23_primary_length_under_1km | primary_length_m | primary_length_m_hftd_23 | Miles | pixel_count | mean_ignition_probability | ignition_rank | mean_mavf_core | mavf_consequence_rank | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | kpmg_Consolidated Risk Score | KPMG_rank
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | CUS391 | TRUE | 36.3577 | 36.3577 | 0.022596 | 1 | 0.00039685 | 69 | 7972.4858 | 5 | 3.1639 | 3.1639 | 1 |  | 3570
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 276-G | TRUE | 23.7478 | 23.7478 | 0.014759 | 1 | 0.00025382 | 208 | 7401.5283 | 7 | 1.8786 | 1.8786 | 2 | 0.16 | 1261
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 90130 | TRUE | 151.1499 | 151.1499 | 0.09394 | 1 | 0.00016255 | 619 | 10411.5469 | 1 | 1.6924 | 1.6924 | 3 | 2.44 | 603
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 688294 | TRUE | 24.3604 | 24.3604 | 0.01514 | 1 | 0.00017139 | 553 | 8415.9766 | 3 | 1.4425 | 1.4425 | 4 |  | 3420
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | CB | TRUE | 289.8399 | 85.2366 | 0.052975 | 4 | 0.00035401 | 88 | 3206.0204 | 240 | 1.3006 | 5.2026 | 5 | 0.29 | 1032
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | CB | FALSE | 1791.2622 | 1791.2622 | 1.1133 | 3 | 0.00025111 | 214 | 4819.6954 | 90 | 1.2559 | 3.7676 | 6 | 0.09 | 1534
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 1586 | FALSE | 11983.5348 | 11983.5348 | 7.4478 | 39 | 0.00044628 | 48 | 3225.6011 | 233 | 1.2524 | 48.8434 | 7 | 0.24 | 1102
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 302610 | FALSE | 9188.9357 | 7571.5921 | 4.7058 | 53 | 0.00021011 | 357 | 4327.9371 | 121 | 0.91632 | 48.565 | 8 |  | 3061
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 965078 | FALSE | 11264.1399 | 10089.0761 | 6.2704 | 59 | 0.00026416 | 185 | 3338.3605 | 220 | 0.87629 | 51.7008 | 9 |  | 2774
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 241564 | FALSE | 1774.1526 | 1146.9072 | 0.71281 | 14 | 0.0001265 | 1073 | 6191.5313 | 26 | 0.77248 | 10.8148 | 10 |  | 2961
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | CB | FALSE | 7724.4676 | 7724.4676 | 4.8008 | 13 | 0.00026518 | 181 | 3512.0536 | 200 | 0.73491 | 9.5539 | 11 | 0.13 | 1365
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 378446 | TRUE | 173.2196 | 157.9488 | 0.098166 | 3 | 0.00015629 | 683 | 4122.2296 | 142 | 0.73151 | 2.1945 | 12 |  | 3619
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | CB | TRUE | 1420.4117 | 752.0336 | 0.46739 | 12 | 0.00032056 | 109 | 1676.5244 | 530 | 0.72481 | 8.6977 | 13 | 0.71 | 802
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 830 | FALSE | 62803.2175 | 44622.1036 | 27.7328 | 212 | 0.00015679 | 675 | 4619.5228 | 102 | 0.71618 | 151.8291 | 14 | 0.14 | 1322
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | CB | FALSE | 12231.0905 | 8613.688 | 5.3534 | 38 | 0.00011189 | 1370 | 5318.8037 | 51 | 0.70423 | 26.7607 | 15 | 0.04 | 2163
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 4440 | TRUE | 376.2849 | 376.2849 | 0.23386 | 4 | 0.00015164 | 724 | 3234.1311 | 230 | 0.68656 | 2.7463 | 16 | 1.05 | 722
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | CB | TRUE | 135.534 | 135.534 | 0.084235 | 1 | 9.93e-05 | 1662 | 6756.3685 | 11 | 0.67079 | 0.67079 | 17 | 2.37 | 609
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 14072 | FALSE | 6206.8729 | 5897.3117 | 3.6652 | 30 | 0.0001306 | 999 | 5236.689 | 59 | 0.65331 | 19.5994 | 18 | 0.05 | 2003
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 980662 | TRUE | 366.2635 | 366.2635 | 0.22763 | 3 | 0.00014325 | 821 | 4824.4797 | 89 | 0.64187 | 1.9256 | 19 |  | 3599
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 126774 | FALSE | 1267.3386 | 1267.3386 | 0.78766 | 11 | 9.36e-05 | 1808 | 6310.2508 | 24 | 0.62029 | 6.8232 | 20 |  | 3568
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 442850 | FALSE | 9258.545 | 9258.545 | 5.7542 | 30 | 9.18e-05 | 1852 | 6349.6612 | 21 | 0.61454 | 18.4361 | 21 | 0.08 | 1644
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | CB | FALSE | 3906.143 | 3906.143 | 2.4277 | 27 | 0.00013159 | 989 | 4767.3932 | 95 | 0.59573 | 16.0848 | 22 | 2.54 | 600
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 118494 | FALSE | 1737.509 | 1714.9565 | 1.0659 | 12 | 0.00012542 | 1091 | 4982.7835 | 79 | 0.58092 | 6.971 | 23 |  | 3276
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 784704 | TRUE | 43.8835 | 43.8835 | 0.027274 | 1 | 0.00019096 | 437 | 2953.5029 | 279 | 0.564 | 0.564 | 24 | 1.81 | 641
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 113684 | TRUE | 748.9574 | 590.6521 | 0.36709 | 4 | 9.3e-05 | 1823 | 6848.1417 | 10 | 0.55276 | 2.211 | 25 |  | 3509
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 250154 | TRUE | 458.5489 | 458.5489 | 0.28499 | 4 | 0.0001142 | 1315 | 5210.7292 | 61 | 0.55243 | 2.2097 | 26 |  | 3150
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 628 | FALSE | 22883.905 | 22883.905 | 14.2224 | 51 | 0.00010064 | 1633 | 5903.6105 | 33 | 0.5487 | 27.9838 | 27 | 5.08 | 496
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 3202 | TRUE | 630.3021 | 630.3021 | 0.39174 | 9 | 8.4e-05 | 2093 | 6312.7784 | 23 | 0.53731 | 4.8358 | 28 | 9.63 | 406
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 32586 | FALSE | 2375.6773 | 2158.8587 | 1.3417 | 15 | 0.00014236 | 834 | 3072.9006 | 260 | 0.52987 | 7.9481 | 29 | 1.13 | 712
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | CB | FALSE | 3746.9222 | 3746.9222 | 2.3287 | 10 | 5.42e-05 | 2939 | 9615.8541 | 2 | 0.51619 | 5.1619 | 30 | 0.05 | 1951
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 200-G | TRUE | 13.7161 | 13.7161 | 0.0085246 | 1 | 0.00015982 | 645 | 3189.8253 | 242 | 0.50979 | 0.50979 | 31 | 18.16 | 324
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 394G | TRUE | 18.1683 | 18.1683 | 0.011292 | 1 | 0.00015982 | 646 | 3189.8253 | 243 | 0.50979 | 0.50979 | 32 | 18.15 | 325
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 546650 | FALSE | 1443.177 | 1443.177 | 0.89694 | 6 | 0.00052979 | 27 | 978.3256 | 845 | 0.50291 | 3.0174 | 33 |  | 2920
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 47214 | TRUE | 43.972 | 43.972 | 0.027329 | 1 | 5.84e-05 | 2823 | 8298.4728 | 4 | 0.48427 | 0.48427 | 34 | 2.46 | 602
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | CB | FALSE | 8571.1084 | 8453.5074 | 5.2539 | 31 | 0.00011156 | 1382 | 3466.6155 | 205 | 0.47165 | 14.6212 | 35 | 0.06 | 1807
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 97142 | FALSE | 7406.0615 | 7406.0615 | 4.6029 | 40 | 0.00010428 | 1545 | 5130.9585 | 66 | 0.47122 | 18.8487 | 36 | 0.05 | 1966
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 40092 | FALSE | 68288.9427 | 37272.9556 | 23.1653 | 464 | 0.00010079 | 1627 | 4668.9585 | 100 | 0.46772 | 217.022 | 37 | 5.23 | 493
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 481876 | FALSE | 2559.0375 | 1373.1162 | 0.8534 | 14 | 8.32e-05 | 2127 | 5568.7809 | 46 | 0.46769 | 6.5476 | 38 |  | 2766
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 49742 | FALSE | 5593.8568 | 5593.8568 | 3.4766 | 28 | 5.8e-05 | 2835 | 7932.3948 | 6 | 0.46433 | 13.0013 | 39 | 0.05 | 1993
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 48180 | TRUE | 21.1502 | 21.1502 | 0.013145 | 2 | 8.16e-05 | 2167 | 5130.0926 | 67 | 0.46103 | 0.92206 | 40 | 0.05 | 1938
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 46012 | FALSE | 4834.6736 | 1025.1447 | 0.63713 | 38 | 9.49e-05 | 1768 | 4755.8708 | 96 | 0.45557 | 17.3115 | 41 |  | 3124
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 6542 | FALSE | 23588.1989 | 23588.1989 | 14.6602 | 140 | 0.00010109 | 1623 | 4849.1896 | 86 | 0.44642 | 62.4985 | 42 | 0.1 | 1469
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 64118 | FALSE | 15416.9418 | 2646.9433 | 1.6451 | 101 | 0.00019755 | 406 | 2096.5335 | 427 | 0.44262 | 44.7046 | 43 | 0.02 | 2515
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | CB | TRUE | 20.574 | 20.574 | 0.012787 | 1 | 0.00031529 | 111 | 1402.4592 | 637 | 0.44218 | 0.44218 | 44 | 0.04 | 2165
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 6953 | FALSE | 9187.973 | 9187.973 | 5.7104 | 58 | 0.00011159 | 1378 | 4228.1533 | 135 | 0.4353 | 25.2473 | 45 | 4.2 | 525
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 96324 | TRUE | 775.7684 | 775.7684 | 0.48214 | 6 | 0.00013262 | 970 | 3560.1407 | 193 | 0.4317 | 2.5902 | 46 | 0.03 | 2285
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | CB | FALSE | 2942.9352 | 2836.5864 | 1.7629 | 23 | 0.00018049 | 510 | 2272.276 | 388 | 0.42859 | 9.8576 | 47 | 0.07 | 1708
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 9718 | FALSE | 56853.1165 | 29935.2857 | 18.6049 | 357 | 8.86e-05 | 1967 | 4802.059 | 94 | 0.42526 | 151.8163 | 48 | 0.07 | 1758
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 35002 | FALSE | 91942.988 | 91942.988 | 57.1429 | 641 | 0.00011631 | 1264 | 3934.2214 | 153 | 0.42185 | 270.4028 | 49 | 0.4 | 943
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 440236 | FALSE | 6874.8043 | 6874.8043 | 4.2727 | 38 | 0.00016814 | 575 | 3899.3651 | 157 | 0.4205 | 15.979 | 50 |  | 3110
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 881362 | TRUE | 1747.5089 | 480.0321 | 0.29834 | 10 | 0.00010401 | 1552 | 3804.2183 | 168 | 0.41959 | 4.1959 | 51 |  | 3475
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 1454 | FALSE | 12602.1173 | 12602.1173 | 7.8323 | 31 | 9.31e-05 | 1817 | 5114.2446 | 68 | 0.41883 | 12.9837 | 52 | 0.03 | 2353
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 965390 | FALSE | 2587.1085 | 1209.1092 | 0.75147 | 21 | 9.95e-05 | 1657 | 4819.484 | 91 | 0.41415 | 8.6971 | 53 |  | 3088
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 754718 | FALSE | 4640.5633 | 4640.5633 | 2.8841 | 29 | 0.00013445 | 936 | 2737.1841 | 306 | 0.40712 | 11.8066 | 54 |  | 3456
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | CB | TRUE | 1122.2361 | 221.6704 | 0.13777 | 9 | 0.00036283 | 82 | 802.2368 | 941 | 0.40561 | 3.6505 | 55 | 0.11 | 1412
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | CB | FALSE | 11032.7196 | 11032.7196 | 6.8569 | 54 | 0.00014918 | 748 | 2134.6994 | 416 | 0.40353 | 21.7909 | 56 | 0.11 | 1422
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | CB | FALSE | 4029.4321 | 4029.4321 | 2.5043 | 34 | 0.00017446 | 532 | 2332.9065 | 378 | 0.39837 | 13.5444 | 57 | 0.04 | 2081
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 698 | FALSE | 16605.929 | 11071.0466 | 6.8807 | 97 | 9.42e-05 | 1790 | 4392.8078 | 115 | 0.39723 | 38.5312 | 58 | 0.06 | 1832
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 979830 | TRUE | 696.7531 | 680.7511 | 0.42309 | 7 | 7.12e-05 | 2441 | 5107.124 | 69 | 0.3972 | 2.7804 | 59 |  | 3328
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 95878 | FALSE | 30094.5573 | 9856.7705 | 6.126 | 191 | 0.00017374 | 535 | 2217.9989 | 398 | 0.3965 | 75.7306 | 60 | 0.02 | 2524
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 5310 | FALSE | 45195.5088 | 45195.5088 | 28.0892 | 299 | 6.73e-05 | 2551 | 6694.8526 | 15 | 0.39401 | 117.8076 | 61 | 19.51 | 312
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 361952 | FALSE | 2196.587 | 2196.587 | 1.3652 | 9 | 0.00011545 | 1290 | 3151.4111 | 248 | 0.39288 | 3.536 | 62 | 1.9 | 631
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | CB | FALSE | 29229.2172 | 29229.2172 | 18.1661 | 204 | 8.21e-05 | 2150 | 5306.8686 | 52 | 0.39206 | 79.9801 | 63 | 0.11 | 1431
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 8762 | FALSE | 26274.6884 | 22259.6162 | 13.8344 | 147 | 7.87e-05 | 2244 | 4502.8739 | 108 | 0.39138 | 57.5327 | 64 | 0.12 | 1395
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 1634 | FALSE | 29441.3626 | 29110.7694 | 18.0925 | 192 | 8.49e-05 | 2064 | 4929.5026 | 80 | 0.39094 | 75.0607 | 65 | 0.18 | 1222
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 10335 | FALSE | 9369.0411 | 9369.0411 | 5.8229 | 69 | 9.59e-05 | 1732 | 4247.144 | 133 | 0.39082 | 26.9663 | 66 | 1.53 | 668
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 865502 | TRUE | 4467.1172 | 644.9532 | 0.40084 | 27 | 0.00011299 | 1344 | 3613.4467 | 189 | 0.38957 | 10.5185 | 67 |  | 3119
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | CB | FALSE | 40215.5467 | 40215.5467 | 24.9941 | 262 | 0.00012902 | 1029 | 2606.3425 | 328 | 0.38665 | 101.3032 | 68 | 9.11 | 412
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | N54 | FALSE | 34748.7236 | 32201.1783 | 20.0132 | 221 | 9.3e-05 | 1819 | 4184.3432 | 138 | 0.38568 | 85.2354 | 69 | 3.07 | 564
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 37222 | FALSE | 40893.1758 | 40893.1758 | 25.4153 | 152 | 0.00011309 | 1341 | 3498.721 | 202 | 0.3839 | 58.3523 | 70 | 0.05 | 2044
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 1532 | FALSE | 7926.8978 | 6133.1893 | 3.8118 | 27 | 6.51e-05 | 2606 | 6536.3281 | 17 | 0.38077 | 10.2807 | 71 | 0.01 | 2591
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 75802 | TRUE | 680.0226 | 576.1553 | 0.35808 | 6 | 0.0002061 | 377 | 1316.5155 | 676 | 0.37901 | 2.2741 | 72 | 3.09 | 563
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 2408 | FALSE | 22439.0865 | 18541.2413 | 11.5235 | 76 | 0.00027566 | 167 | 1710.6647 | 521 | 0.37815 | 28.7393 | 73 | 0.15 | 1306
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 623120 | FALSE | 12233.579 | 10535.1094 | 6.5476 | 67 | 0.00013171 | 986 | 3211.1058 | 239 | 0.3774 | 25.2855 | 74 |  | 2966
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 1904 | FALSE | 64429.3728 | 51242.8521 | 31.8476 | 332 | 0.00018483 | 475 | 1914.8501 | 471 | 0.37685 | 125.1141 | 75 | 0.11 | 1439
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | CB | FALSE | 14817.1823 | 14817.1823 | 9.2089 | 80 | 0.00011233 | 1359 | 3549.008 | 194 | 0.37545 | 30.036 | 76 | 0.07 | 1694
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 984788 | TRUE | 5.0644 | 5.0644 | 0.0031475 | 1 | 7.62e-05 | 2303 | 4898.9282 | 84 | 0.37348 | 0.37348 | 77 |  | 3623
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 570682 | FALSE | 3264.3372 | 3264.3372 | 2.0288 | 26 | 9.68e-05 | 1718 | 4471.4183 | 111 | 0.37306 | 9.6995 | 78 | 5.65 | 481
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 11101 | FALSE | 5931.2678 | 5931.2678 | 3.6863 | 37 | 6.65e-05 | 2575 | 6042.3197 | 28 | 0.36793 | 13.6135 | 79 | 5.36 | 488
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 9473 | FALSE | 4735.3386 | 3890.479 | 2.4179 | 27 | 9.09e-05 | 1883 | 3855.297 | 162 | 0.36547 | 9.8678 | 80 | 1.5 | 669
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 445650 | FALSE | 1066.4109 | 1066.4109 | 0.66278 | 5 | 6.03e-05 | 2764 | 6011.651 | 29 | 0.36477 | 1.8239 | 81 |  | 3333
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 414 | FALSE | 18899.455 | 9544.4247 | 5.9319 | 114 | 0.00014586 | 791 | 3081.157 | 259 | 0.36434 | 41.5353 | 82 | 1.22 | 699
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 884904 | FALSE | 18739.6016 | 18723.6816 | 11.6368 | 77 | 0.0001019 | 1605 | 3934.604 | 152 | 0.36326 | 27.9711 | 83 |  | 2842
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 592742 | TRUE | 684.4552 | 546.7453 | 0.3398 | 5 | 6.99e-05 | 2474 | 5228.5371 | 60 | 0.36227 | 1.8113 | 84 |  | 3618
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 1568 | FALSE | 37176.4968 | 37176.4968 | 23.1053 | 136 | 9.09e-05 | 1885 | 3456.9848 | 206 | 0.36191 | 49.2203 | 85 | 0.1 | 1479
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | CB | FALSE | 22365.4615 | 7612.1604 | 4.731 | 146 | 0.00014565 | 795 | 2568.6158 | 335 | 0.36174 | 52.8144 | 86 | 14.97 | 351
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | N02 | TRUE | 70.934 | 70.934 | 0.044086 | 1 | 0.00025248 | 210 | 1429.5746 | 625 | 0.36094 | 0.36094 | 87 | 2.56 | 597
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 5020 | FALSE | 26887.6514 | 26064.8634 | 16.1994 | 159 | 8.57e-05 | 2036 | 4882.5801 | 85 | 0.36009 | 57.2543 | 88 | 0.1 | 1468
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 3105 | FALSE | 9965.2703 | 9659.0441 | 6.0031 | 65 | 6.43e-05 | 2635 | 5852.1243 | 38 | 0.35978 | 23.3856 | 89 | 2.42 | 605
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 389190 | FALSE | 4452.7835 | 3542.8058 | 2.2019 | 18 | 0.00010318 | 1566 | 3658.7668 | 184 | 0.35946 | 6.4703 | 90 |  | 3524
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 799940 | TRUE | 1340.3375 | 954.7701 | 0.59339 | 9 | 9.21e-05 | 1842 | 3744.3748 | 176 | 0.35844 | 3.2259 | 91 |  | 3537
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 67858 | FALSE | 18377.3415 | 18377.3415 | 11.4216 | 107 | 6.8e-05 | 2535 | 5416.4769 | 50 | 0.35702 | 38.201 | 92 | 2.79 | 581
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 945670 | TRUE | 403.0974 | 334.4297 | 0.20785 | 3 | 6.39e-05 | 2648 | 5860.0064 | 36 | 0.35536 | 1.0661 | 93 |  | 3578
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | Y54 | FALSE | 55238.5351 | 54847.9366 | 34.0882 | 296 | 8e-05 | 2204 | 4332.6246 | 120 | 0.35181 | 104.1359 | 94 | 0.39 | 950
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | CB | TRUE | 169.7516 | 136.2242 | 0.084664 | 2 | 0.00017127 | 555 | 1962.7321 | 461 | 0.35138 | 0.70277 | 95 | 2.89 | 573
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 867486 | FALSE | 5219.4397 | 3405.4305 | 2.1165 | 20 | 7.39e-05 | 2361 | 3380.0089 | 213 | 0.35061 | 7.0121 | 96 |  | 3172
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 400 | FALSE | 5057.3021 | 5057.3021 | 3.1431 | 8 | 9.55e-05 | 1743 | 3849.0683 | 163 | 0.34896 | 2.7917 | 97 | 0.31 | 1006
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | CB | FALSE | 27398.7529 | 27398.7529 | 17.0284 | 154 | 6.93e-05 | 2496 | 5271.5559 | 56 | 0.348 | 53.5915 | 98 | 0.07 | 1725
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 49024 | FALSE | 26972.4505 | 26707.9675 | 16.5991 | 209 | 8.48e-05 | 2071 | 4699.5815 | 98 | 0.34786 | 72.7038 | 99 | 9.03 | 415
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 1370 | FALSE | 35764.2 | 21861.3958 | 13.5869 | 272 | 0.00010359 | 1559 | 3756.8301 | 175 | 0.34561 | 94.0068 | 100 | 0.05 | 1954
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 35974 | TRUE | 1338.7863 | 398.8739 | 0.2479 | 11 | 7.68e-05 | 2289 | 4333.8495 | 119 | 0.34404 | 3.7844 | 101 | 0.03 | 2393
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 874798 | TRUE | 662.24 | 662.24 | 0.41158 | 3 | 6.6e-05 | 2587 | 6079.8606 | 27 | 0.33623 | 1.0087 | 102 |  | 3523
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 964 | FALSE | 8651.6925 | 4999.6692 | 3.1073 | 41 | 0.00013223 | 977 | 2706.926 | 309 | 0.33456 | 13.717 | 103 | 0.45 | 917
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5703 | FALSE | 12751.5705 | 8525.0586 | 5.2984 | 96 | 0.00012007 | 1186 | 2775.9092 | 303 | 0.33328 | 31.9947 | 104 | 0.07 | 1684
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 1632 | FALSE | 13751.6318 | 13751.6318 | 8.5467 | 19 | 8.89e-05 | 1954 | 4338.5101 | 118 | 0.33244 | 6.3164 | 105 | 0.05 | 1948
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | CB | FALSE | 6348.7863 | 4804 | 2.9857 | 44 | 0.00014557 | 797 | 1870.2515 | 482 | 0.32751 | 14.4105 | 106 | 0.03 | 2238
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 895760 | FALSE | 19502.5171 | 14756.3663 | 9.1711 | 96 | 9.56e-05 | 1740 | 3633.0115 | 188 | 0.32643 | 31.3373 | 107 |  | 3035
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | Y04 | FALSE | 35997.3396 | 25194.6309 | 15.6586 | 238 | 6.64e-05 | 2580 | 5141.1422 | 64 | 0.32463 | 77.261 | 108 | 2.84 | 576
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | CB | TRUE | 1275.2265 | 525.8096 | 0.32679 | 9 | 0.00013923 | 884 | 1814.5621 | 503 | 0.32442 | 2.9197 | 109 | 0.04 | 2217
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 768 | FALSE | 31882.0115 | 27234.0747 | 16.9261 | 115 | 9.51e-05 | 1764 | 3417.6208 | 210 | 0.32431 | 37.2953 | 110 | 0.05 | 2000
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 478952 | FALSE | 5727.3171 | 1143.6662 | 0.71079 | 39 | 0.00011288 | 1347 | 2674.3103 | 318 | 0.32368 | 12.6234 | 111 |  | 3082
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 1202 | FALSE | 12713.8882 | 12713.8882 | 7.9017 | 41 | 0.00015857 | 657 | 2432.9018 | 355 | 0.32328 | 13.2544 | 112 | 2.4 | 607
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 1566 | FALSE | 24740.5736 | 19451.0946 | 12.0889 | 94 | 8.02e-05 | 2199 | 4262.1109 | 129 | 0.3225 | 30.3149 | 113 | 0.05 | 2042
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 426745 | TRUE | 328.8561 | 328.8561 | 0.20439 | 3 | 0.00020048 | 394 | 1570.5843 | 571 | 0.32224 | 0.96673 | 114 |  | 3365
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 153260 | TRUE | 424.4592 | 424.4592 | 0.2638 | 2 | 9.6e-05 | 1729 | 3917.3903 | 154 | 0.32186 | 0.64373 | 115 |  | 3584
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 9726 | FALSE | 27359.7493 | 25257.4681 | 15.6976 | 197 | 8.95e-05 | 1931 | 4058.7556 | 145 | 0.32131 | 63.2977 | 116 | 3.58 | 541
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 323094 | FALSE | 58176.4815 | 58176.4815 | 36.1569 | 208 | 0.00010508 | 1524 | 3224.7709 | 234 | 0.32037 | 66.6373 | 117 | 0.08 | 1636
4869 | BELL 11082202 | 152701108 | BELL 1108 | 2202 | FALSE | 53635.0932 | 52339.4363 | 32.5292 | 363 | 0.0001269 | 1065 | 2599.5441 | 330 | 0.32016 | 116.2183 | 118 | 0.16 | 1264
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 296804 | FALSE | 5287.5044 | 5287.5044 | 3.2862 | 12 | 0.00014395 | 815 | 2252.1128 | 392 | 0.31954 | 3.8345 | 119 |  | 3361
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | CB | FALSE | 1481.3738 | 1293.943 | 0.80419 | 9 | 0.00018563 | 469 | 1193.2799 | 733 | 0.31824 | 2.8642 | 120 | 0.39 | 953
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | A20 | FALSE | 12666.4228 | 11999.0835 | 7.4575 | 92 | 8.35e-05 | 2117 | 4208.4041 | 137 | 0.3179 | 29.2466 | 121 | 0.09 | 1561
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 38316 | FALSE | 36512.8123 | 25616.7426 | 15.9209 | 232 | 7.26e-05 | 2403 | 4684.5531 | 99 | 0.31672 | 73.4796 | 122 | 3 | 569
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 544790 | FALSE | 27462.4335 | 26342.4042 | 16.3719 | 185 | 8.39e-05 | 2097 | 3941.9662 | 151 | 0.31273 | 57.8548 | 123 |  | 2696
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 5525 | FALSE | 21152.7165 | 21152.7165 | 13.1465 | 175 | 5.97e-05 | 2783 | 5306.8404 | 53 | 0.31171 | 54.5497 | 124 | 0.17 | 1227
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 878 | FALSE | 9206.6572 | 5430.6654 | 3.3752 | 49 | 0.00017681 | 519 | 2682.7456 | 315 | 0.31109 | 15.2435 | 125 | 0.63 | 834
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | CB | FALSE | 36834.5436 | 36834.5436 | 22.8928 | 193 | 0.00011343 | 1334 | 2972.4937 | 272 | 0.31093 | 60.0095 | 126 | 10.25 | 399
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 828 | FALSE | 17153.3338 | 13828.9706 | 8.5948 | 112 | 8.39e-05 | 2094 | 3831.1552 | 164 | 0.31086 | 34.8164 | 127 | 5.94 | 476
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | R308 | FALSE | 6217.3701 | 6217.3701 | 3.8641 | 22 | 6.13e-05 | 2743 | 4314.2777 | 123 | 0.30901 | 6.7983 | 128 | 0.04 | 2136
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | CB | FALSE | 2646.4634 | 2646.4634 | 1.6448 | 13 | 0.00028983 | 139 | 1109.8091 | 772 | 0.30873 | 4.0135 | 129 | 5.34 | 489
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 976428 | FALSE | 16955.2499 | 14081.5812 | 8.7518 | 82 | 0.00013702 | 908 | 2148.1965 | 412 | 0.30752 | 25.2165 | 130 |  | 3305
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 96792 | FALSE | 8212.3137 | 6394.0351 | 3.9739 | 30 | 7.18e-05 | 2425 | 5020.5256 | 72 | 0.30689 | 9.2067 | 131 |  | 3057
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 6210 | FALSE | 17177.2503 | 17177.2503 | 10.6757 | 49 | 4.86e-05 | 3072 | 5877.8631 | 34 | 0.30465 | 14.9278 | 132 | 0.06 | 1874
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | A12 | FALSE | 64854.5144 | 64854.5144 | 40.3073 | 180 | 9.12e-05 | 1867 | 3289.4433 | 226 | 0.30414 | 54.7453 | 133 | 0.11 | 1446
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | CB | FALSE | 16489.2317 | 14163.76 | 8.8028 | 107 | 0.00015725 | 671 | 2292.759 | 385 | 0.30391 | 32.5187 | 134 | 6.82 | 459
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | CB | FALSE | 24190.4571 | 22339.3117 | 13.884 | 147 | 0.00012222 | 1145 | 2373.5412 | 366 | 0.30349 | 44.6134 | 135 | 0.16 | 1273
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | CB | FALSE | 16978.5039 | 16978.5039 | 10.5522 | 33 | 8.56e-05 | 2039 | 4275.4303 | 128 | 0.30244 | 9.9805 | 136 | 0.03 | 2265
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | CB | TRUE | 12832.3568 | 56.5182 | 0.035126 | 105 | 9.1e-05 | 1880 | 3530.2398 | 198 | 0.30185 | 31.6947 | 137 | 0.03 | 2249
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | N50 | FALSE | 3586.1974 | 3586.1974 | 2.2288 | 24 | 0.00020174 | 390 | 1403.0605 | 636 | 0.30039 | 7.2094 | 138 | 6.6 | 465
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 354890 | FALSE | 19596.9379 | 15016.4864 | 9.3328 | 131 | 0.00011262 | 1350 | 1727.5671 | 518 | 0.29712 | 38.9233 | 139 |  | 2675
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 1382 | FALSE | 8797.2782 | 8797.2782 | 5.4675 | 67 | 0.00010202 | 1603 | 2904.98 | 289 | 0.29503 | 19.7671 | 140 | 0.07 | 1732
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | CB | FALSE | 55860.8325 | 55860.8325 | 34.7177 | 368 | 5.12e-05 | 3010 | 6445.9013 | 19 | 0.29173 | 107.3565 | 141 | 0.21 | 1150
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | CB | FALSE | 44193.7 | 42311.3503 | 26.2967 | 280 | 7.47e-05 | 2339 | 3983.5914 | 150 | 0.29054 | 81.3506 | 142 | 18.05 | 326
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 1600 | FALSE | 17254.9785 | 7231.4682 | 4.4944 | 106 | 9.33e-05 | 1813 | 3227.6771 | 231 | 0.2889 | 30.6232 | 143 | 0.04 | 2087
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 10030 | FALSE | 59186.5885 | 54599.1868 | 33.9336 | 227 | 5.2e-05 | 2993 | 5711.1735 | 43 | 0.28655 | 65.0478 | 144 | 0.04 | 2223
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 669720 | FALSE | 7831.1318 | 3612.2461 | 2.245 | 22 | 8.81e-05 | 1979 | 4178.9611 | 140 | 0.28655 | 6.3042 | 145 |  | 3370
3809 | WISE 11022230 | 152271102 | WISE 1102 | 2230 | FALSE | 40267.1112 | 38210.8819 | 23.7482 | 278 | 9.88e-05 | 1674 | 3101.6196 | 254 | 0.28438 | 79.0585 | 146 | 8.79 | 420
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 327814 | FALSE | 23697.2526 | 18621.0587 | 11.5731 | 119 | 5.81e-05 | 2832 | 5439.3493 | 48 | 0.28428 | 33.8288 | 147 |  | 2778
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 280170 | FALSE | 24945.6136 | 20943.3132 | 13.0164 | 102 | 0.00011005 | 1411 | 2725.4901 | 307 | 0.28426 | 28.9943 | 148 |  | 2855
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 2949 | TRUE | 766.5719 | 766.5719 | 0.47643 | 6 | 4.99e-05 | 3039 | 6323.2739 | 22 | 0.28416 | 1.7049 | 149 | 2.67 | 590
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | CB | FALSE | 17940.9873 | 8017.5323 | 4.9829 | 118 | 0.00011905 | 1205 | 2481.2226 | 344 | 0.28403 | 33.5157 | 150 | 0.04 | 2142
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 5300 | FALSE | 89782.9365 | 89782.9365 | 55.8005 | 507 | 6.13e-05 | 2742 | 5197.3797 | 62 | 0.28372 | 143.8456 | 151 | 0.2 | 1159
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 750 | FALSE | 14900.5272 | 7342.9025 | 4.5636 | 93 | 0.00015288 | 720 | 2183.6202 | 404 | 0.28318 | 26.3354 | 152 | 3.16 | 559
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | Y66 | FALSE | 29410.1773 | 27268.3855 | 16.9474 | 138 | 5.92e-05 | 2801 | 4926.5491 | 81 | 0.28279 | 39.0253 | 153 | 8.36 | 431
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 10320 | FALSE | 18962.0898 | 18962.0898 | 11.785 | 133 | 7.35e-05 | 2380 | 3652.1529 | 186 | 0.28179 | 37.4782 | 154 | 0.06 | 1810
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 58990 | TRUE | 971.5045 | 427.9744 | 0.26599 | 6 | 0.00011359 | 1330 | 3017.9754 | 266 | 0.28025 | 1.6815 | 155 |  | 3495
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 277014 | FALSE | 26491.1541 | 8850.8283 | 5.5008 | 149 | 7.49e-05 | 2333 | 3435.5989 | 208 | 0.28002 | 41.7232 | 156 |  | 2840
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 53118 | FALSE | 15490.2628 | 15490.2628 | 9.6273 | 47 | 5.94e-05 | 2792 | 5134.3568 | 65 | 0.27952 | 13.1375 | 157 | 0.08 | 1618
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 654021 | TRUE | 1396.0557 | 329.1954 | 0.2046 | 12 | 6.2e-05 | 2719 | 5297.9521 | 54 | 0.27878 | 3.3454 | 158 |  | 3351
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 35598 | FALSE | 17452.8092 | 17452.8092 | 10.847 | 122 | 0.00012105 | 1163 | 2054.3578 | 443 | 0.27855 | 33.9836 | 159 | 2.42 | 604
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 1574 | FALSE | 30217.612 | 27209.5234 | 16.9108 | 221 | 9.78e-05 | 1698 | 3321.0394 | 222 | 0.27852 | 61.5533 | 160 | 0.1 | 1499
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 4626 | FALSE | 50138.0738 | 43527.4256 | 27.0525 | 238 | 9.74e-05 | 1704 | 2906.275 | 288 | 0.27841 | 66.2609 | 161 | 0.08 | 1626
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 873457 | FALSE | 3228.1461 | 2440.6531 | 1.5169 | 18 | 6.46e-05 | 2620 | 3816.6955 | 166 | 0.27723 | 4.9901 | 162 |  | 3525
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | R2578 | FALSE | 74560.01 | 74560.01 | 46.3393 | 506 | 5.75e-05 | 2848 | 5003.4373 | 77 | 0.27714 | 140.2335 | 163 | 0.12 | 1377
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | CB | FALSE | 61825.449 | 61825.449 | 38.4248 | 420 | 0.00010575 | 1502 | 2969.029 | 273 | 0.27679 | 116.2539 | 164 | 0.1 | 1498
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 9570 | FALSE | 12951.7997 | 12951.7997 | 8.0496 | 59 | 6.93e-05 | 2498 | 4812.6159 | 92 | 0.27669 | 16.3249 | 165 | 0.03 | 2273
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | CB | FALSE | 22596.9807 | 22596.9807 | 14.0441 | 79 | 8.91e-05 | 1941 | 3040.7048 | 264 | 0.2766 | 21.851 | 166 | 0.05 | 2045
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | CB | TRUE | 286.9891 | 286.9891 | 0.17836 | 2 | 0.00034143 | 96 | 952.1877 | 859 | 0.27613 | 0.55227 | 167 |  | 3629
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 64664 | FALSE | 46084.8025 | 44670.3665 | 27.7628 | 263 | 0.00011497 | 1301 | 2595.543 | 331 | 0.27567 | 72.501 | 168 | 7.76 | 441
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 1350 | FALSE | 34999.9271 | 34999.9271 | 21.7526 | 212 | 0.00015371 | 714 | 2128.0484 | 418 | 0.27537 | 58.3793 | 169 | 0.14 | 1328
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | MR765 | FALSE | 3411.7079 | 3330.9197 | 2.0702 | 15 | 0.00016258 | 618 | 1924.3853 | 466 | 0.2736 | 4.104 | 170 |  | 3219
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 8352 | FALSE | 19103.6731 | 10298.4219 | 6.4005 | 133 | 7.71e-05 | 2286 | 3533.4319 | 197 | 0.27308 | 36.3202 | 171 | 0.04 | 2110
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 716 | FALSE | 27459.7262 | 24685.2253 | 15.342 | 109 | 0.00010173 | 1611 | 2445.3377 | 351 | 0.27295 | 29.7514 | 172 | 0.09 | 1540
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 2198 | FALSE | 33673.9837 | 32552.0609 | 20.2312 | 248 | 0.00015745 | 669 | 1901.3176 | 477 | 0.27291 | 67.6807 | 173 | 5.01 | 498
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 400470 | TRUE | 475.2183 | 334.0108 | 0.20759 | 3 | 0.00014321 | 822 | 1757.1387 | 513 | 0.27287 | 0.81862 | 174 |  | 3474
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | R309 | FALSE | 13825.8859 | 13825.8859 | 8.5928 | 92 | 4.47e-05 | 3170 | 5876.5086 | 35 | 0.27286 | 25.1032 | 175 | 0.07 | 1734
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 998 | FALSE | 27408.003 | 23900.855 | 14.8545 | 205 | 0.00011619 | 1266 | 2601.6522 | 329 | 0.27124 | 55.6044 | 176 | 9.39 | 410
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | MR572 | FALSE | 19863.5833 | 13342.8208 | 8.2926 | 80 | 8.35e-05 | 2113 | 3855.5003 | 161 | 0.27121 | 21.6967 | 177 | 0.06 | 1900
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 6552 | FALSE | 20088.9562 | 20088.9562 | 12.4854 | 139 | 0.00023194 | 279 | 1458.479 | 613 | 0.2712 | 37.6964 | 178 | 0.07 | 1674
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 80670 | FALSE | 26435.3887 | 23201.6685 | 14.4199 | 158 | 9.33e-05 | 1814 | 3120.2999 | 252 | 0.27059 | 42.753 | 179 | 0.07 | 1687
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 118944 | FALSE | 8499.846 | 3772.9974 | 2.3449 | 41 | 7.26e-05 | 2402 | 3739.9482 | 177 | 0.27039 | 11.0862 | 180 |  | 3148
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 482 | FALSE | 41604.9679 | 39433.4736 | 24.5081 | 188 | 8.34e-05 | 2120 | 3402.5308 | 212 | 0.26975 | 50.7128 | 181 | 0.11 | 1426
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | CB | FALSE | 37179.8547 | 36440.0989 | 22.6477 | 254 | 0.00012368 | 1127 | 2336.1435 | 377 | 0.26784 | 68.0313 | 182 | 0.11 | 1411
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 636114 | FALSE | 32974.1643 | 32974.1643 | 20.4936 | 153 | 5.04e-05 | 3029 | 5596.4616 | 45 | 0.26702 | 40.8546 | 183 |  | 3171
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 564710 | TRUE | 541.7371 | 273.7323 | 0.17013 | 7 | 4.75e-05 | 3102 | 4812.031 | 93 | 0.26624 | 1.8637 | 184 |  | 3533
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 275986 | TRUE | 934.5883 | 934.5883 | 0.58085 | 5 | 8.3e-05 | 2131 | 2938.8625 | 283 | 0.26526 | 1.3263 | 185 |  | 3473
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 50072 | FALSE | 68212.3657 | 68212.3657 | 42.3943 | 424 | 8.38e-05 | 2099 | 2904.6654 | 290 | 0.26524 | 112.4633 | 186 | 0.17 | 1228
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 10070 | FALSE | 42054.457 | 42054.457 | 26.137 | 249 | 5.93e-05 | 2796 | 3802.6518 | 169 | 0.2644 | 65.835 | 187 | 0.16 | 1265
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 10880 | FALSE | 64212.5757 | 63861.6467 | 39.6903 | 362 | 5.47e-05 | 2925 | 5019.3026 | 74 | 0.2637 | 95.458 | 188 | 0.25 | 1077
1822 | BELL 110750172 | 152701107 | BELL 1107 | 50172 | FALSE | 30233.9103 | 28142.3136 | 17.4906 | 210 | 8.95e-05 | 1930 | 3226.5987 | 232 | 0.2635 | 55.3341 | 189 | 3.07 | 565
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 13652 | FALSE | 6914.8485 | 6914.8485 | 4.2976 | 58 | 0.00011431 | 1311 | 2370.7576 | 367 | 0.26339 | 15.2768 | 190 | 4.89 | 502
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 399855 | FALSE | 4438.9669 | 4409.9199 | 2.7408 | 19 | 0.00012846 | 1040 | 1799.172 | 506 | 0.26331 | 5.0028 | 191 |  | 2826
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 4710 | FALSE | 2414.0516 | 2414.0516 | 1.5003 | 18 | 7.4e-05 | 2359 | 3402.6996 | 211 | 0.26308 | 4.7355 | 192 | 0.06 | 1858
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 1808 | FALSE | 25003.3757 | 25003.3757 | 15.5397 | 171 | 0.00012923 | 1021 | 2096.2914 | 428 | 0.26282 | 44.9426 | 193 | 0.09 | 1564
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 1380 | FALSE | 37070.8959 | 28672.6173 | 17.8201 | 204 | 0.00010398 | 1553 | 2782.7866 | 301 | 0.26207 | 53.462 | 194 | 0.07 | 1696
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 45190 | FALSE | 60483.5997 | 60483.5997 | 37.5908 | 416 | 4.41e-05 | 3190 | 5858.6509 | 37 | 0.26095 | 108.5552 | 195 | 0.15 | 1301
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | B504R | FALSE | 18129.2647 | 14074.6887 | 8.7475 | 97 | 9.87e-05 | 1676 | 3474.2779 | 204 | 0.26071 | 25.289 | 196 | 0.1 | 1494
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 18292 | TRUE | 8145.543 | 73.0344 | 0.045391 | 73 | 0.00010766 | 1460 | 2089.0547 | 431 | 0.26015 | 18.9907 | 197 | 4.97 | 499
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | CB | FALSE | 15377.0316 | 15053.0301 | 9.3555 | 98 | 0.00013609 | 918 | 2689.4423 | 314 | 0.25991 | 25.4708 | 198 | 1.45 | 674
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 10990 | FALSE | 64432.5092 | 64432.5092 | 40.0451 | 390 | 6.28e-05 | 2688 | 4452.3041 | 112 | 0.25971 | 101.2865 | 199 | 0.23 | 1118
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 85162 | FALSE | 9267.4821 | 9267.4821 | 5.7598 | 28 | 4.85e-05 | 3077 | 5246.1165 | 57 | 0.2589 | 7.2492 | 200 | 0.09 | 1512
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36652 | FALSE | 58152.9177 | 58152.9177 | 36.1423 | 357 | 6.91e-05 | 2503 | 3912.9423 | 155 | 0.25884 | 92.4048 | 201 | 2.74 | 586
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 660 | FALSE | 15616.9486 | 9914.559 | 6.1619 | 91 | 0.0001122 | 1361 | 2640.3198 | 322 | 0.25883 | 23.5531 | 202 | 0.02 | 2506
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 696 | FALSE | 15381.4122 | 10464.5667 | 6.5038 | 87 | 0.00011584 | 1275 | 2155.4593 | 411 | 0.25793 | 22.4395 | 203 | 0.04 | 2141
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | CB | FALSE | 109280.4349 | 109280.4349 | 67.9182 | 589 | 7.61e-05 | 2305 | 3828.8466 | 165 | 0.25597 | 150.7655 | 204 | 0.64 | 828
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 534 | FALSE | 33775.8496 | 30432.3399 | 18.9138 | 142 | 8.23e-05 | 2145 | 3212.6445 | 237 | 0.25577 | 36.3189 | 205 | 0.12 | 1397
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 93504 | FALSE | 4036.8011 | 3461.2366 | 2.1512 | 15 | 6.09e-05 | 2750 | 4082.5968 | 144 | 0.25426 | 3.8139 | 206 | 0.06 | 1896
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 873304 | FALSE | 1312.9508 | 1312.9508 | 0.816 | 5 | 6.95e-05 | 2489 | 4833.6394 | 88 | 0.25419 | 1.2709 | 207 |  | 3605
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 59714 | FALSE | 7503.916 | 7503.916 | 4.6637 | 34 | 9.43e-05 | 1786 | 2408.1592 | 360 | 0.25391 | 8.6328 | 208 | 0.04 | 2176
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 990354 | TRUE | 170.3854 | 170.3854 | 0.1059 | 2 | 0.00030725 | 122 | 583.9962 | 1119 | 0.25341 | 0.50682 | 209 | 0.02 | 2532
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 526 | FALSE | 17461.3012 | 16256.6321 | 10.1036 | 100 | 0.00011252 | 1356 | 2700.181 | 312 | 0.25318 | 25.318 | 210 | 0.07 | 1679
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 558 | FALSE | 15006.3638 | 4818.3603 | 2.9946 | 72 | 0.00022789 | 291 | 857.3477 | 909 | 0.25266 | 18.1915 | 211 | 0.01 | 2601
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 568 | FALSE | 14789.9903 | 12940.6184 | 8.0426 | 118 | 0.00012911 | 1024 | 2034.9748 | 449 | 0.25222 | 29.7625 | 212 | 0.1 | 1493
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | R902 | FALSE | 24261.144 | 24261.144 | 15.0784 | 156 | 6.33e-05 | 2666 | 4129.7341 | 141 | 0.25137 | 39.2136 | 213 | 0.07 | 1688
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | MR169 | FALSE | 15006.414 | 4976.4795 | 3.0929 | 96 | 9.46e-05 | 1776 | 2310.912 | 383 | 0.25044 | 24.0426 | 214 | 0.02 | 2435
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 99904 | FALSE | 8949.4853 | 8949.4853 | 5.5621 | 54 | 0.00018177 | 500 | 1184.3918 | 739 | 0.25006 | 13.5032 | 215 | 39.72 | 187
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 37504 | FALSE | 5704.6998 | 1890.9339 | 1.1752 | 41 | 0.00013442 | 938 | 1727.1376 | 519 | 0.24974 | 10.2392 | 216 | 0.02 | 2505
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | CB | FALSE | 6924.1001 | 6924.1001 | 4.3034 | 22 | 5.9e-05 | 2806 | 4006.0392 | 149 | 0.24862 | 5.4697 | 217 | 0.07 | 1691
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 702710 | FALSE | 7335.7671 | 4286.5556 | 2.6641 | 49 | 0.00021702 | 330 | 1323.547 | 672 | 0.24845 | 12.174 | 218 |  | 3072
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 66146 | TRUE | 252.3083 | 252.3083 | 0.15681 | 4 | 0.00010984 | 1414 | 2698.6732 | 313 | 0.24793 | 0.99171 | 219 | 0.12 | 1382
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 346006 | FALSE | 3918.3073 | 3650.4625 | 2.2688 | 5 | 7.76e-05 | 2277 | 3061.2643 | 262 | 0.24765 | 1.2382 | 220 |  | 3479
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 90036 | FALSE | 23187.5221 | 21561.1762 | 13.4004 | 87 | 7.38e-05 | 2364 | 4520.2585 | 105 | 0.24724 | 21.5103 | 221 | 0.1 | 1505
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 5732 | FALSE | 5445.3198 | 5445.3198 | 3.3843 | 37 | 5.33e-05 | 2956 | 4484.9828 | 109 | 0.24719 | 9.1461 | 222 | 0.14 | 1324
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 37282 | FALSE | 96262.893 | 86430.7687 | 53.7171 | 498 | 6.54e-05 | 2602 | 4244.8756 | 134 | 0.24522 | 122.1205 | 223 | 0.36 | 969
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 63334 | FALSE | 27819.9713 | 27819.9713 | 17.2902 | 154 | 5.03e-05 | 3032 | 5273.9392 | 55 | 0.24446 | 37.6467 | 224 | 10.23 | 400
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 31502 | FALSE | 19104.3686 | 19104.3686 | 11.8734 | 102 | 0.00014287 | 828 | 1982.4694 | 459 | 0.24429 | 24.9173 | 225 | 0.08 | 1616
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 35874 | TRUE | 329.4831 | 329.4831 | 0.20478 | 4 | 0.0002322 | 276 | 974.717 | 846 | 0.24298 | 0.97191 | 226 | 0.03 | 2258
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 9372 | FALSE | 28750.7098 | 28750.7098 | 17.8687 | 190 | 0.00012144 | 1159 | 1860.3939 | 487 | 0.24281 | 46.1342 | 227 | 6.15 | 472
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 756 | TRUE | 948.4078 | 948.4078 | 0.58944 | 7 | 0.00037409 | 76 | 1141.7089 | 757 | 0.24238 | 1.6966 | 228 | 0.02 | 2431
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | N60 | FALSE | 14171.0101 | 13316.6581 | 8.2764 | 66 | 6.37e-05 | 2655 | 3875.817 | 160 | 0.24236 | 15.9958 | 229 | 0.04 | 2143
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 685276 | FALSE | 34821.9656 | 10432.3869 | 6.4838 | 216 | 7.81e-05 | 2256 | 3212.4401 | 238 | 0.24208 | 52.2897 | 230 |  | 2761
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 416226 | TRUE | 397.9238 | 186.6616 | 0.11601 | 5 | 8.49e-05 | 2065 | 2680.4211 | 316 | 0.24182 | 1.2091 | 231 |  | 3167
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 17011 | FALSE | 3005.3172 | 3005.3172 | 1.8678 | 22 | 9.74e-05 | 1702 | 2978.7374 | 270 | 0.24153 | 5.3136 | 232 | 0.07 | 1747
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | Y02 | FALSE | 21138.3498 | 16812.4916 | 10.449 | 158 | 6.28e-05 | 2691 | 3729.2174 | 180 | 0.24142 | 38.1442 | 233 | 0.07 | 1717
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 186326 | FALSE | 20743.7329 | 19088.8539 | 11.8638 | 123 | 0.00011431 | 1312 | 2157.6907 | 410 | 0.24114 | 29.6596 | 234 |  | 3066
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | CB | FALSE | 13066.3244 | 13066.3244 | 8.1208 | 67 | 0.00015784 | 665 | 1253.7272 | 700 | 0.24096 | 16.1444 | 235 | 0.13 | 1360
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 117644 | FALSE | 3757.3782 | 1080.3525 | 0.67144 | 12 | 9.3e-05 | 1820 | 2949.3645 | 280 | 0.23987 | 2.8784 | 236 |  | 3416
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 617260 | FALSE | 4545.7003 | 1876.8402 | 1.1665 | 15 | 9.41e-05 | 1791 | 3143.4533 | 249 | 0.2396 | 3.5941 | 237 |  | 3506
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 63389 | TRUE | 391.5938 | 0 | 0 | 2 | 0.00010287 | 1573 | 1639.5129 | 547 | 0.23935 | 0.47871 | 238 |  | 3610
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 904 | FALSE | 5777.0339 | 5445.6493 | 3.3845 | 30 | 9.3e-05 | 1822 | 2564.652 | 336 | 0.23862 | 7.1587 | 239 | 1.48 | 670
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 19522 | FALSE | 16493.1882 | 15565.1755 | 9.6738 | 113 | 8.88e-05 | 1959 | 3187.9029 | 244 | 0.23827 | 26.9251 | 240 | 34.17 | 216
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | MR387 | FALSE | 8072.5307 | 8065.9096 | 5.013 | 24 | 6.29e-05 | 2681 | 3500.2914 | 201 | 0.23776 | 5.7062 | 241 | 0.06 | 1882
109 | WISE 11022054 | 152271102 | WISE 1102 | 2054 | FALSE | 20940.0353 | 20940.0353 | 13.0143 | 147 | 0.00010429 | 1544 | 2815.7078 | 298 | 0.23735 | 34.8898 | 242 | 3.46 | 547
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 318686 | FALSE | 4853.6414 | 2345.6024 | 1.4578 | 7 | 6.51e-05 | 2607 | 3652.241 | 185 | 0.23683 | 1.6578 | 243 |  | 3349
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 1314 | FALSE | 23311.1376 | 9677.7607 | 6.0148 | 161 | 8.22e-05 | 2148 | 3017.906 | 267 | 0.23664 | 38.0983 | 244 | 1.18 | 703
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | R353 | FALSE | 22190.5443 | 22190.5443 | 13.7915 | 53 | 3.71e-05 | 3313 | 6512.8186 | 18 | 0.23576 | 12.4952 | 245 | 0.07 | 1773
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 12608 | FALSE | 27131.1027 | 27131.1027 | 16.8621 | 187 | 6.29e-05 | 2683 | 3772.462 | 174 | 0.23545 | 44.029 | 246 | 11.8 | 381
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 707358 | FALSE | 37001.2559 | 30537.9753 | 18.9795 | 219 | 4.13e-05 | 3238 | 5721.8442 | 41 | 0.23489 | 51.4409 | 247 |  | 2974
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 92888 | TRUE | 765.3621 | 400.6025 | 0.24898 | 4 | 0.00010691 | 1480 | 2347.6932 | 375 | 0.23471 | 0.93885 | 248 | 0.01 | 2581
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 8482 | FALSE | 23390.9929 | 23390.9929 | 14.5376 | 117 | 0.00010252 | 1587 | 2287.3259 | 386 | 0.23437 | 27.4214 | 249 | 0.05 | 2057
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 725408 | FALSE | 2105.6406 | 1530.1897 | 0.95102 | 9 | 9.3e-05 | 1821 | 2838.0743 | 294 | 0.23427 | 2.1085 | 250 |  | 3511
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | R56 | FALSE | 19965.7505 | 18526.1855 | 11.5141 | 117 | 9.9e-05 | 1669 | 2922.3966 | 284 | 0.2342 | 27.401 | 251 | 1.75 | 644
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 1892 | FALSE | 5154.3447 | 5154.3447 | 3.2034 | 12 | 0.00011418 | 1317 | 1393.5299 | 640 | 0.23339 | 2.8006 | 252 | 0.06 | 1887
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 37334 | FALSE | 15392.9848 | 15392.9848 | 9.5668 | 70 | 5.29e-05 | 2973 | 4838.4242 | 87 | 0.23311 | 16.3175 | 253 | 0.07 | 1730
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 3988 | FALSE | 29512.4633 | 27217.7374 | 16.9159 | 68 | 4.01e-05 | 3264 | 5944.554 | 32 | 0.23303 | 15.8463 | 254 | 0.1 | 1471
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | CB | FALSE | 23543.7827 | 17030.244 | 10.5844 | 164 | 0.00014109 | 852 | 1638.3807 | 548 | 0.23182 | 38.0188 | 255 | 0.08 | 1577
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | M84 | FALSE | 39352.9214 | 37718.995 | 23.4425 | 145 | 7.15e-05 | 2434 | 3431.3832 | 209 | 0.23169 | 33.5958 | 256 | 0.05 | 2018
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | N58 | FALSE | 11929.7838 | 7319.6094 | 4.5492 | 91 | 8.97e-05 | 1923 | 2958.7213 | 277 | 0.23099 | 21.0205 | 257 | 1.43 | 676
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5597 | FALSE | 8229.9238 | 8229.9238 | 5.1149 | 22 | 5.73e-05 | 2855 | 4008.4187 | 148 | 0.23009 | 5.062 | 258 | 0.06 | 1847
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 412 | FALSE | 27547.3528 | 16599.9817 | 10.317 | 152 | 9.72e-05 | 1709 | 2705.0187 | 311 | 0.23008 | 34.9724 | 259 | 0.04 | 2122
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 2731 | FALSE | 2630.6286 | 2630.6286 | 1.6349 | 13 | 8.16e-05 | 2166 | 3132.5166 | 251 | 0.2296 | 2.9847 | 260 | 0.25 | 1088
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | CB | FALSE | 9780.4489 | 2376.9126 | 1.4773 | 72 | 0.00018501 | 472 | 1136.289 | 760 | 0.22956 | 16.5281 | 261 | 0.02 | 2474
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 226050 | FALSE | 24153.2004 | 7845.4549 | 4.876 | 160 | 0.00012494 | 1099 | 1958.1377 | 463 | 0.22913 | 36.6601 | 262 |  | 2875
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 10400 | FALSE | 72169.1615 | 68567.3531 | 42.6149 | 539 | 6.32e-05 | 2673 | 4382.9111 | 117 | 0.22826 | 123.0305 | 263 | 0.67 | 815
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 50078 | FALSE | 77925.0016 | 77925.0016 | 48.4307 | 427 | 6.65e-05 | 2573 | 3492.1838 | 203 | 0.22791 | 97.3194 | 264 | 0.18 | 1215
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 37472 | FALSE | 23988.0552 | 14935.9015 | 9.2827 | 157 | 0.00012968 | 1013 | 1878.4311 | 481 | 0.22739 | 35.7007 | 265 | 0.05 | 2001
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 10820 | FALSE | 46507.9226 | 46392.4448 | 28.8331 | 327 | 6.26e-05 | 2698 | 4312.1018 | 124 | 0.2269 | 74.1966 | 266 | 0.19 | 1188
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 96554 | FALSE | 23931.0858 | 12987.3897 | 8.0717 | 172 | 7.04e-05 | 2458 | 3307.1204 | 223 | 0.22645 | 38.9486 | 267 | 1.68 | 653
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | CB | FALSE | 2444.9029 | 1435.1005 | 0.89192 | 20 | 0.0002022 | 389 | 1029.6753 | 809 | 0.22632 | 4.5263 | 268 | 0.01 | 2599
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | Y50 | FALSE | 20651.346 | 17101.0403 | 10.6284 | 147 | 6.64e-05 | 2578 | 3157.5997 | 246 | 0.22624 | 33.2573 | 269 | 4.23 | 523
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 1230 | FALSE | 31242.042 | 27069.5791 | 16.8239 | 136 | 8.44e-05 | 2080 | 2820.2882 | 297 | 0.22608 | 30.7471 | 270 | 0.08 | 1627
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 9026 | FALSE | 39327.0742 | 20154.6992 | 12.5262 | 282 | 7.35e-05 | 2382 | 3010.4191 | 268 | 0.22599 | 63.7295 | 271 | 0.04 | 2131
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 672 | FALSE | 35787.4101 | 35088.8854 | 21.8079 | 140 | 0.00010502 | 1528 | 2485.285 | 343 | 0.22571 | 31.5995 | 272 | 0.66 | 819
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 1630 | FALSE | 22751.2492 | 4020.9242 | 2.499 | 152 | 5.71e-05 | 2858 | 3897.064 | 159 | 0.22562 | 34.2944 | 273 | 0.02 | 2518
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | R2839 | FALSE | 20608.9537 | 20608.9537 | 12.8085 | 121 | 6.37e-05 | 2657 | 3802.0162 | 170 | 0.22501 | 27.2266 | 274 | 0.07 | 1746
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 2582 | FALSE | 33578.71 | 32011.0943 | 19.895 | 186 | 8.33e-05 | 2124 | 2966.3342 | 275 | 0.22449 | 41.7559 | 275 | 0.31 | 999
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 1622 | FALSE | 54701.9644 | 54701.9644 | 33.9975 | 126 | 4.76e-05 | 3098 | 5068.1116 | 70 | 0.22413 | 28.2406 | 276 | 0.15 | 1289
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | R2579 | FALSE | 56162.7607 | 56162.7607 | 34.9054 | 286 | 4.37e-05 | 3195 | 4995.9654 | 78 | 0.22394 | 64.0469 | 277 | 0.05 | 1982
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | R1013 | FALSE | 20054.4307 | 20054.4307 | 12.4639 | 132 | 5.21e-05 | 2991 | 4310.3961 | 125 | 0.22385 | 29.5483 | 278 | 0.08 | 1599
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 726 | FALSE | 56301.3395 | 48875.2274 | 30.3762 | 263 | 0.00010365 | 1558 | 2367.3738 | 368 | 0.22347 | 58.7725 | 279 | 5.19 | 495
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | CB | FALSE | 11342.4728 | 11342.4728 | 7.0494 | 33 | 9.14e-05 | 1864 | 1823.5922 | 499 | 0.22294 | 7.3571 | 280 | 1.24 | 696
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 1664 | FALSE | 47581.2918 | 47581.2918 | 29.572 | 244 | 0.00016153 | 624 | 1257.5627 | 697 | 0.22209 | 54.1896 | 281 | 0.09 | 1544
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | Y72 | FALSE | 10347.4182 | 10265.6354 | 6.3801 | 36 | 7.49e-05 | 2335 | 2941.2416 | 282 | 0.2213 | 7.967 | 282 | 0.05 | 1994
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 508502 | FALSE | 25902.2253 | 18917.893 | 11.7575 | 115 | 8.12e-05 | 2178 | 2793.3826 | 300 | 0.22043 | 25.3491 | 283 |  | 2971
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | CB | FALSE | 26399.8993 | 26026.0287 | 16.1753 | 152 | 0.00012844 | 1042 | 2226.2508 | 395 | 0.21931 | 33.3354 | 284 | 0.08 | 1659
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 9504 | FALSE | 23288.5561 | 23283.8699 | 14.471 | 97 | 5.19e-05 | 2997 | 4524.1542 | 104 | 0.21922 | 21.2645 | 285 | 0.67 | 812
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | CB | FALSE | 13738.3645 | 13738.3645 | 8.5384 | 32 | 4.03e-05 | 3260 | 5713.5203 | 42 | 0.21869 | 6.998 | 286 | 0.06 | 1881
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | CB | FALSE | 25047.8449 | 25047.8449 | 15.5673 | 65 | 0.00013384 | 945 | 2147.2351 | 413 | 0.21823 | 14.185 | 287 | 0.06 | 1867
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 36622 | FALSE | 15095.8174 | 8277.82 | 5.1447 | 42 | 0.00010696 | 1475 | 1906.2139 | 474 | 0.21771 | 9.1438 | 288 | 0.01 | 2620
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 13018 | FALSE | 2657.2717 | 1090.3862 | 0.67768 | 20 | 0.00024176 | 241 | 916.9696 | 877 | 0.21662 | 4.3325 | 289 | 0.04 | 2205
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | CB | FALSE | 4716.8976 | 4354.341 | 2.7062 | 38 | 0.00020157 | 391 | 1548.9969 | 580 | 0.21644 | 8.2246 | 290 | 0.07 | 1689
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | N52 | FALSE | 10571.3698 | 10571.3698 | 6.5701 | 32 | 0.00016961 | 565 | 1370.1644 | 652 | 0.21643 | 6.9258 | 291 | 0.06 | 1851
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 1536 | FALSE | 29066.1076 | 28603.8149 | 17.7774 | 79 | 4.66e-05 | 3124 | 4923.7257 | 83 | 0.21608 | 17.0703 | 292 | 0.07 | 1705
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 665952 | TRUE | 1521.662 | 243.3824 | 0.15126 | 13 | 7.18e-05 | 2427 | 3135.666 | 250 | 0.21591 | 2.8069 | 293 |  | 3252
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 47786 | FALSE | 2915.7036 | 2915.7036 | 1.8121 | 13 | 8.74e-05 | 2003 | 2875.37 | 291 | 0.21513 | 2.7967 | 294 | 0.01 | 2571
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 736078 | TRUE | 432.8669 | 373.6781 | 0.23224 | 3 | 6.84e-05 | 2526 | 3199.3848 | 241 | 0.2146 | 0.64381 | 295 |  | 3522
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 306972 | TRUE | 120.3234 | 83.4407 | 0.051859 | 2 | 0.00015818 | 661 | 1356.3524 | 660 | 0.21455 | 0.4291 | 296 |  | 3576
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | CB | FALSE | 4947.493 | 4947.493 | 3.0749 | 21 | 0.0001327 | 965 | 2090.7818 | 430 | 0.21399 | 4.4937 | 297 | 0.32 | 995
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 11210 | FALSE | 27492.7886 | 27492.7886 | 17.0869 | 139 | 4.9e-05 | 3064 | 4555.1801 | 103 | 0.21387 | 29.7273 | 298 | 0.02 | 2413
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 385838 | FALSE | 2645.3497 | 2006.1588 | 1.2468 | 11 | 9.33e-05 | 1815 | 1869.8054 | 483 | 0.21349 | 2.3484 | 299 |  | 3295
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 2944 | FALSE | 24391.9365 | 24262.4198 | 15.0792 | 148 | 5.61e-05 | 2885 | 4103.8075 | 143 | 0.21331 | 31.5694 | 300 | 0.08 | 1576
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 1582 | FALSE | 24298.6245 | 10265.1395 | 6.3798 | 173 | 8.39e-05 | 2096 | 2774.3491 | 305 | 0.21327 | 36.8955 | 301 | 0.05 | 1927
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 7360 | FALSE | 14342.2552 | 14342.2552 | 8.9138 | 83 | 5.77e-05 | 2844 | 3097.6367 | 256 | 0.21272 | 17.6557 | 302 | 0 | 2643
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 472084 | FALSE | 11718.4795 | 7454.711 | 4.6331 | 66 | 0.00014287 | 829 | 1759.7585 | 512 | 0.21229 | 14.0108 | 303 | 0.03 | 2360
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 11290 | FALSE | 12662.0411 | 12662.0411 | 7.8695 | 75 | 8.8e-05 | 1982 | 2545.3939 | 339 | 0.21224 | 15.9178 | 304 | 0.1 | 1455
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | CB | TRUE | 168.4127 | 168.4127 | 0.10467 | 1 | 9.1e-05 | 1882 | 2332.6265 | 379 | 0.2122 | 0.2122 | 305 | 0.27 | 1058
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 37466 | FALSE | 50978.0825 | 50460.2287 | 31.3612 | 345 | 3.23e-05 | 3395 | 6743.7065 | 13 | 0.21127 | 72.8874 | 306 | 0.08 | 1598
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | CB | FALSE | 22068.3915 | 11401.8921 | 7.0863 | 148 | 5.69e-05 | 2864 | 2830.5359 | 295 | 0.21085 | 31.2055 | 307 | 1.66 | 655
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 77098 | FALSE | 20978.2648 | 19250.5668 | 11.9643 | 112 | 5.05e-05 | 3025 | 4289.2504 | 127 | 0.21042 | 23.5673 | 308 | 2.69 | 589
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 806 | FALSE | 55052.2104 | 33831.6044 | 21.0265 | 229 | 9.18e-05 | 1850 | 2097.6482 | 426 | 0.21008 | 48.1076 | 309 | 0.15 | 1276
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 21210 | FALSE | 26056.9931 | 20686.2377 | 12.8566 | 111 | 5.49e-05 | 2916 | 4309.2408 | 126 | 0.20896 | 23.1943 | 310 | 0.06 | 1808
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 79932 | FALSE | 52854.9374 | 35504.8505 | 22.0664 | 345 | 8.03e-05 | 2196 | 2706.2696 | 310 | 0.20828 | 71.8562 | 311 | 0.1 | 1497
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 454 | FALSE | 8909.2195 | 8909.2195 | 5.5371 | 54 | 6.65e-05 | 2574 | 3069.2553 | 261 | 0.20738 | 11.1984 | 312 | 0.38 | 962
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 90180 | FALSE | 7976.0066 | 7976.0066 | 4.9571 | 49 | 5.45e-05 | 2932 | 3678.4222 | 183 | 0.20688 | 10.1373 | 313 | 0.02 | 2514
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 644756 | FALSE | 31848.1753 | 27875.8932 | 17.325 | 163 | 0.00011577 | 1279 | 1915.4825 | 470 | 0.20636 | 33.6372 | 314 |  | 3049
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 2002 | FALSE | 48391.7593 | 35045.7729 | 21.7811 | 109 | 5.51e-05 | 2908 | 4261.2835 | 130 | 0.20473 | 22.3155 | 315 | 0.05 | 1965
1537 | BELL 11072400 | 152701107 | BELL 1107 | 2400 | FALSE | 44680.5549 | 41414.8349 | 25.7395 | 320 | 0.00010832 | 1445 | 2117.8289 | 423 | 0.20423 | 65.3543 | 316 | 10.83 | 393
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 296 | FALSE | 23764.0701 | 23764.0701 | 14.7695 | 123 | 8.73e-05 | 2004 | 2337.6554 | 376 | 0.20401 | 25.0928 | 317 | 6.9 | 457
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | CB | FALSE | 39932.7775 | 21735.4145 | 13.5086 | 273 | 0.00010469 | 1537 | 2355.7077 | 371 | 0.20316 | 55.4629 | 318 | 0.09 | 1519
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 936897 | TRUE | 1562.7499 | 665.5519 | 0.41364 | 12 | 0.00014733 | 769 | 1798.1732 | 507 | 0.20267 | 2.432 | 319 |  | 3507
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 34338 | FALSE | 16775.5793 | 15726.6133 | 9.7742 | 66 | 6.79e-05 | 2539 | 3085.8385 | 258 | 0.2022 | 13.3455 | 320 | 0.08 | 1669
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | R2850 | FALSE | 42428.4265 | 42428.4265 | 26.3694 | 222 | 3.61e-05 | 3337 | 5548.3018 | 47 | 0.20166 | 44.7693 | 321 | 0.17 | 1244
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | CB | FALSE | 32934.7957 | 25410.3119 | 15.7926 | 114 | 0.00011157 | 1381 | 1859.3886 | 488 | 0.20132 | 22.9503 | 322 | 0.04 | 2202
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | CB | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00012264 | 1138 | 1641.5431 | 545 | 0.20132 | 0.20132 | 323 | 0.02 | 2423
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | MR176 | FALSE | 68684.3236 | 62474.1802 | 38.828 | 256 | 5.58e-05 | 2894 | 3634.7993 | 187 | 0.20121 | 51.5086 | 324 | 0.19 | 1184
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 514987 | FALSE | 21614.682 | 13379.7927 | 8.3156 | 63 | 4.62e-05 | 3132 | 4320.4063 | 122 | 0.20048 | 12.6303 | 325 |  | 3128
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 11158 | FALSE | 47609.4929 | 20499.8935 | 12.7408 | 229 | 9.64e-05 | 1721 | 2379.6196 | 364 | 0.20008 | 45.8175 | 326 | 0.06 | 1777
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | R314 | FALSE | 71701.2396 | 68245.5323 | 42.4149 | 390 | 3.25e-05 | 3393 | 6228.9607 | 25 | 0.20004 | 78.017 | 327 | 0.11 | 1437
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 4646 | FALSE | 29868.2951 | 29868.2951 | 18.5633 | 165 | 0.00010487 | 1531 | 2139.2524 | 415 | 0.19983 | 32.9712 | 328 | 36.87 | 205
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4200 | FALSE | 7940.3444 | 6495.7462 | 4.0371 | 37 | 0.00011057 | 1400 | 2908.2309 | 287 | 0.19927 | 7.3729 | 329 | 0.05 | 1995
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 49122 | FALSE | 6376.3554 | 6376.3554 | 3.9629 | 40 | 4.92e-05 | 3060 | 3584.6164 | 191 | 0.19907 | 7.9627 | 330 | 1.33 | 682
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 96844 | FALSE | 9556.2941 | 9556.2941 | 5.9393 | 63 | 0.00023552 | 260 | 862.5947 | 906 | 0.19881 | 12.5249 | 331 | 46.48 | 142
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 85766 | FALSE | 29746.7523 | 29746.7523 | 18.4877 | 166 | 0.00013073 | 996 | 2062.5576 | 442 | 0.19865 | 32.9759 | 332 | 0.1 | 1495
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 391250 | FALSE | 1481.3226 | 1481.3226 | 0.92065 | 3 | 0.00010172 | 1612 | 1985.1612 | 457 | 0.19841 | 0.59524 | 333 |  | 3356
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | CB | FALSE | 42270.0145 | 42270.0145 | 26.271 | 131 | 0.00014762 | 766 | 1407.8483 | 633 | 0.19817 | 25.9607 | 334 | 0.25 | 1086
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 1276 | FALSE | 20806.9121 | 20806.9121 | 12.9316 | 116 | 9.82e-05 | 1687 | 2220.124 | 397 | 0.19794 | 22.9608 | 335 | 0.05 | 1931
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 796386 | FALSE | 64232.6683 | 57391.9753 | 35.6693 | 159 | 5.75e-05 | 2849 | 3563.2207 | 192 | 0.19792 | 31.4686 | 336 |  | 2815
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | CB | FALSE | 20983.2028 | 20983.2028 | 13.0411 | 77 | 2.8e-05 | 3460 | 6753.7935 | 12 | 0.19768 | 15.2216 | 337 | 0.07 | 1765
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 628 | FALSE | 14091.1105 | 6713.6414 | 4.1726 | 98 | 0.00010294 | 1570 | 2036.6122 | 448 | 0.19686 | 19.2923 | 338 | 0.05 | 2063
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 90550 | FALSE | 12911.2772 | 12911.2772 | 8.0244 | 47 | 5.1e-05 | 3014 | 3547.8361 | 195 | 0.19624 | 9.2235 | 339 | 0.02 | 2486
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 2106 | FALSE | 21303.4581 | 21303.4581 | 13.2402 | 67 | 3.78e-05 | 3302 | 5722.5441 | 40 | 0.1961 | 13.1388 | 340 | 0.03 | 2286
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 7040 | FALSE | 39870.081 | 39870.081 | 24.7794 | 230 | 4.85e-05 | 3079 | 4388.1035 | 116 | 0.19605 | 45.0921 | 341 | 0.07 | 1719
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 500 | FALSE | 47144.6891 | 34375.7452 | 21.3647 | 214 | 0.00018229 | 495 | 1298.6787 | 684 | 0.19576 | 41.8921 | 342 | 2.86 | 574
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 19910 | FALSE | 33304.7006 | 33304.7006 | 20.699 | 226 | 0.00010076 | 1629 | 2072.4287 | 435 | 0.19568 | 44.2238 | 343 | 0.32 | 994
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 555644 | TRUE | 5004.528 | 268.6791 | 0.16699 | 19 | 0.00011733 | 1240 | 1847.862 | 491 | 0.19539 | 3.7125 | 344 |  | 3453
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 708166 | FALSE | 33499.3555 | 18511.1854 | 11.5048 | 162 | 7.99e-05 | 2209 | 2528.2807 | 340 | 0.19539 | 31.6535 | 345 | 9.62 | 407
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 3419 | FALSE | 12848.2917 | 12848.2917 | 7.9853 | 38 | 9.4e-05 | 1794 | 2318.7771 | 381 | 0.19531 | 7.4218 | 346 | 0.08 | 1610
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 41396 | FALSE | 11819.9639 | 10868.1559 | 6.7546 | 75 | 0.00014922 | 747 | 1168.3526 | 746 | 0.19503 | 14.6272 | 347 | 0.08 | 1642
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | CB | FALSE | 34280.1417 | 27168.7986 | 16.8855 | 236 | 7.89e-05 | 2237 | 2954.5395 | 278 | 0.19501 | 46.0213 | 348 | 0.13 | 1353
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 584840 | FALSE | 72531.1064 | 72531.1064 | 45.0784 | 449 | 3.4e-05 | 3370 | 5963.8827 | 31 | 0.19446 | 87.311 | 349 | 0.16 | 1267
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 41356 | FALSE | 52238.1569 | 52238.1569 | 32.4662 | 318 | 8.96e-05 | 1926 | 2383.6073 | 362 | 0.19445 | 61.8351 | 350 | 1.05 | 720
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 1532 | FALSE | 68074.9976 | 62691.3369 | 38.9629 | 465 | 0.00014754 | 767 | 1398.4344 | 638 | 0.19412 | 90.2637 | 351 | 0.07 | 1756
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 1208 | FALSE | 61463.0017 | 53098.4432 | 33.0009 | 334 | 7.32e-05 | 2389 | 2975.7795 | 271 | 0.19404 | 64.811 | 352 | 0.06 | 1784
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | CB | FALSE | 12293.5283 | 12293.5283 | 7.6405 | 36 | 4.95e-05 | 3052 | 3520.3689 | 199 | 0.19398 | 6.9834 | 353 | 0.13 | 1346
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 613086 | FALSE | 14704.7375 | 8243.1424 | 5.1231 | 63 | 2.98e-05 | 3430 | 6359.1487 | 20 | 0.19391 | 12.2166 | 354 |  | 2913
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | CB | FALSE | 34332.3301 | 30178.5623 | 18.7561 | 171 | 0.00012918 | 1023 | 1585.4725 | 565 | 0.19378 | 33.1366 | 355 | 0.08 | 1606
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 745850 | TRUE | 1558.6923 | 771.4701 | 0.47947 | 7 | 5.32e-05 | 2960 | 3897.9708 | 158 | 0.19369 | 1.3558 | 356 |  | 3539
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 793776 | FALSE | 1956.9595 | 1956.9595 | 1.2163 | 6 | 0.00010286 | 1574 | 1821.9134 | 500 | 0.19328 | 1.1597 | 357 |  | 3579
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 604 | FALSE | 42817.3578 | 42516.8793 | 26.4244 | 240 | 0.00012061 | 1176 | 1665.6014 | 537 | 0.19315 | 46.357 | 358 | 8.39 | 428
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 532 | FALSE | 7102.1777 | 7099.179 | 4.4122 | 34 | 0.00016574 | 585 | 1247.6791 | 702 | 0.19264 | 6.5497 | 359 | 0.65 | 824
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 2032 | FALSE | 15248.6713 | 14097.6761 | 8.7618 | 52 | 6.46e-05 | 2618 | 3297.3647 | 225 | 0.19237 | 10.0031 | 360 | 0.06 | 1841
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 13044 | FALSE | 9652.7072 | 7674.8454 | 4.7699 | 51 | 0.00014015 | 867 | 1674.4804 | 533 | 0.19229 | 9.8065 | 361 | 0.05 | 1986
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 7140 | FALSE | 42300.5526 | 42300.5526 | 26.29 | 296 | 2.82e-05 | 3453 | 6738.8921 | 14 | 0.19202 | 56.8394 | 362 | 3.46 | 546
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 82350 | FALSE | 33588.8136 | 31579.2765 | 19.6266 | 230 | 8.9e-05 | 1948 | 2107.591 | 425 | 0.19196 | 44.1515 | 363 | 0.3 | 1019
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 7220 | FALSE | 39952.2483 | 39952.2483 | 24.8305 | 188 | 4.26e-05 | 3217 | 4516.9217 | 107 | 0.19171 | 36.0414 | 364 | 0.06 | 1901
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | CB | TRUE | 25.9334 | 25.9334 | 0.016118 | 1 | 0.00013855 | 888 | 1382.2827 | 648 | 0.19152 | 0.19152 | 365 | 0.05 | 1929
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 645910 | TRUE | 3990.9244 | 774.6277 | 0.48143 | 14 | 0.00012447 | 1110 | 1323.2798 | 673 | 0.19134 | 2.6788 | 366 |  | 3245
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 98478 | FALSE | 9678.6987 | 9678.6987 | 6.0154 | 34 | 6.15e-05 | 2732 | 3101.9251 | 253 | 0.19124 | 6.5022 | 367 | 0.06 | 1824
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 5607 | FALSE | 10708.8001 | 7265.9446 | 4.5158 | 71 | 6.76e-05 | 2544 | 3213.7492 | 235 | 0.19115 | 13.5714 | 368 | 0.05 | 2002
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 524 | TRUE | 4106.6103 | 399.4552 | 0.24826 | 31 | 8.77e-05 | 1992 | 2173.4374 | 408 | 0.19015 | 5.8946 | 369 | 0.71 | 803
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 697216 | FALSE | 21374.2842 | 21374.2842 | 13.2842 | 145 | 8.9e-05 | 1951 | 1998.7247 | 456 | 0.18992 | 27.5378 | 370 | 1.72 | 648
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | CB | FALSE | 32077.0701 | 28146.4256 | 17.4931 | 170 | 9.06e-05 | 1893 | 2204.8048 | 402 | 0.18973 | 32.2538 | 371 | 5.76 | 479
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 6512 | FALSE | 1047.7996 | 1047.7996 | 0.65121 | 5 | 6.06e-05 | 2761 | 1094.509 | 777 | 0.18909 | 0.94545 | 372 | 0.08 | 1593
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 805882 | TRUE | 497.9369 | 477.3024 | 0.29665 | 6 | 0.00016012 | 642 | 1125.8811 | 766 | 0.18904 | 1.1343 | 373 |  | 3553
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 1228 | FALSE | 69440.241 | 17449.9174 | 10.8452 | 368 | 0.00011636 | 1263 | 1613.8231 | 557 | 0.18877 | 69.4681 | 374 | 0.04 | 2078
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 1580 | FALSE | 80785.153 | 76365.8976 | 47.4617 | 383 | 0.00012062 | 1174 | 1821.2183 | 501 | 0.18779 | 71.9249 | 375 | 0.11 | 1451
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 31500 | FALSE | 18887.7142 | 7501.4293 | 4.6622 | 111 | 5.04e-05 | 3030 | 3238.0724 | 229 | 0.18759 | 20.823 | 376 | 0.02 | 2550
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 96224 | FALSE | 31213.3049 | 31213.3049 | 19.3992 | 174 | 6.62e-05 | 2582 | 2944.2439 | 281 | 0.18755 | 32.6329 | 377 | 0.79 | 777
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | CB | FALSE | 47599.3495 | 47599.3495 | 29.5832 | 121 | 0.00014957 | 743 | 1075.8896 | 783 | 0.1873 | 22.6633 | 378 | 0.07 | 1739
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 37288 | FALSE | 137232.3506 | 137232.3506 | 85.2905 | 678 | 4.44e-05 | 3179 | 4408.5685 | 114 | 0.18718 | 126.9051 | 379 | 0.6 | 850
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 885215 | FALSE | 3239.6899 | 3225.5678 | 2.0047 | 23 | 4.6e-05 | 3138 | 3739.8152 | 178 | 0.18705 | 4.3021 | 380 |  | 3435
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 128 | FALSE | 60127.5406 | 56205.3694 | 34.9319 | 269 | 9.71e-05 | 1712 | 2077.9375 | 434 | 0.18687 | 50.2671 | 381 | 0.3 | 1014
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 69722 | FALSE | 10673.4289 | 10673.4289 | 6.6336 | 68 | 0.00014836 | 760 | 1483.0501 | 601 | 0.18675 | 12.6993 | 382 | 0.34 | 983
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 85132 | FALSE | 50093.0189 | 50093.0189 | 31.133 | 217 | 4.26e-05 | 3216 | 4662.7247 | 101 | 0.18633 | 40.4342 | 383 | 0.13 | 1354
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 48952 | FALSE | 17050.5619 | 17050.5619 | 10.597 | 123 | 0.00010175 | 1609 | 2266.9677 | 389 | 0.18561 | 22.8305 | 384 | 0.07 | 1722
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 212772 | FALSE | 1753.1585 | 1609.198 | 1.0001 | 11 | 0.00010227 | 1596 | 1767.7041 | 510 | 0.18554 | 2.041 | 385 |  | 3087
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 79788 | FALSE | 67378.0299 | 63661.5746 | 39.5659 | 157 | 0.00011886 | 1209 | 1546.745 | 582 | 0.18551 | 29.1256 | 386 | 0.12 | 1399
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 13052 | FALSE | 31493.7185 | 31480.1828 | 19.5651 | 213 | 9.53e-05 | 1758 | 2083.3172 | 433 | 0.18514 | 39.4358 | 387 | 0.12 | 1398
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 795010 | FALSE | 6022.8068 | 5964.9276 | 3.7072 | 12 | 3.8e-05 | 3300 | 5006.5635 | 76 | 0.18505 | 2.2206 | 388 |  | 3401
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 1550 | FALSE | 35703.4386 | 31009.474 | 19.2725 | 237 | 9.15e-05 | 1860 | 2378.2716 | 365 | 0.18396 | 43.5983 | 389 | 0.06 | 1796
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 1556 | FALSE | 64601.0138 | 61930.0824 | 38.4898 | 411 | 5.28e-05 | 2977 | 3779.2145 | 173 | 0.18357 | 75.4478 | 390 | 0.18 | 1205
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 365572 | TRUE | 696.8465 | 611.8589 | 0.38027 | 2 | 9.47e-05 | 1772 | 2195.1828 | 403 | 0.18299 | 0.36597 | 391 |  | 3633
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | CB | FALSE | 24813.8274 | 24813.8274 | 15.4219 | 127 | 0.00010514 | 1517 | 1354.0744 | 662 | 0.18254 | 23.1832 | 392 | 0.07 | 1749
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 466348 | FALSE | 48812.3964 | 26039.2723 | 16.1835 | 294 | 9.37e-05 | 1802 | 2063.8243 | 440 | 0.18223 | 53.5743 | 393 |  | 2838
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 35470 | FALSE | 40109.7772 | 33111.192 | 20.5787 | 174 | 8e-05 | 2205 | 2635.2321 | 323 | 0.18214 | 31.6926 | 394 | 1.26 | 692
2265 | BELL 1108CB | 152701108 | BELL 1108 | CB | TRUE | 9628.7582 | 0 | 0 | 83 | 0.00016581 | 584 | 955.774 | 856 | 0.18213 | 15.1167 | 395 | 0.04 | 2098
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 37476 | FALSE | 14076.4929 | 4231.6102 | 2.63 | 82 | 0.0001427 | 830 | 1332.1225 | 666 | 0.18107 | 14.8479 | 396 | 0.03 | 2366
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 12612 | FALSE | 32502.2662 | 31091.451 | 19.3235 | 195 | 7.81e-05 | 2254 | 2667.8797 | 319 | 0.18095 | 35.2855 | 397 | 3.37 | 549
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 1510 | TRUE | 5333.1807 | 613.4018 | 0.38123 | 35 | 9.6e-05 | 1728 | 1460.1171 | 611 | 0.18088 | 6.3309 | 398 | 0.5 | 894
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 641367 | FALSE | 63879.2901 | 63879.2901 | 39.7012 | 278 | 6.98e-05 | 2482 | 2628.7284 | 324 | 0.18079 | 50.2607 | 399 |  | 3081
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | Y504R | FALSE | 18910.1435 | 18838.2347 | 11.708 | 112 | 7.26e-05 | 2404 | 2414.4364 | 358 | 0.18021 | 20.1836 | 400 | 0.36 | 972
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 7060 | FALSE | 28760.1957 | 28760.1957 | 17.8746 | 162 | 4.16e-05 | 3231 | 4251.992 | 132 | 0.18019 | 29.1914 | 401 | 0.05 | 2062
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 48268 | FALSE | 8165.6241 | 8152.5339 | 5.0668 | 30 | 2.81e-05 | 3458 | 6541.9938 | 16 | 0.17977 | 5.3932 | 402 | 0.03 | 2409
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2757 | FALSE | 4222.897 | 4222.897 | 2.6245 | 16 | 7.35e-05 | 2384 | 2563.9177 | 338 | 0.1791 | 2.8656 | 403 | 0.07 | 1748
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | R1817 | FALSE | 31029.2187 | 31029.2187 | 19.2848 | 145 | 3.2e-05 | 3401 | 5976.6981 | 30 | 0.17888 | 25.9373 | 404 | 0.08 | 1648
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 7070 | FALSE | 28250.671 | 28250.671 | 17.5579 | 103 | 3.61e-05 | 3333 | 5058.188 | 71 | 0.17873 | 18.4097 | 405 | 0.06 | 1902
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 890 | FALSE | 39539.8399 | 39211.6931 | 24.3702 | 203 | 0.00013749 | 903 | 1564.6167 | 573 | 0.17857 | 36.2505 | 406 | 0.6 | 852
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | CB | FALSE | 15262.2313 | 6326.3363 | 3.9318 | 97 | 0.0001432 | 823 | 1232.8613 | 712 | 0.1779 | 17.2565 | 407 | 0.04 | 2123
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 90730 | FALSE | 13402.9331 | 13402.9331 | 8.33 | 77 | 0.00022241 | 309 | 801.5027 | 942 | 0.17712 | 13.6383 | 408 | 0.07 | 1738
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | CB | FALSE | 1862.134 | 1862.134 | 1.1573 | 2 | 2.65e-05 | 3479 | 5012.0663 | 75 | 0.17665 | 0.3533 | 409 | 0.11 | 1430
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | CB | FALSE | 3124.8792 | 3111.1631 | 1.9336 | 12 | 0.00016891 | 568 | 1033.5651 | 803 | 0.17607 | 2.1128 | 410 | 0.03 | 2391
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 89934 | FALSE | 8917.9013 | 8917.9013 | 5.5425 | 56 | 0.00022642 | 301 | 791.9341 | 950 | 0.17581 | 9.8455 | 411 | 0.04 | 2125
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 594 | FALSE | 23079.0447 | 23079.0447 | 14.3437 | 155 | 0.00011929 | 1200 | 1640.4713 | 546 | 0.17563 | 27.2219 | 412 | 0.16 | 1253
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 53184 | FALSE | 51204.6527 | 51204.6527 | 31.8239 | 123 | 4.46e-05 | 3174 | 4517.1008 | 106 | 0.17544 | 21.5791 | 413 | 0.06 | 1844
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 208 | FALSE | 20077.9466 | 20077.9466 | 12.4785 | 95 | 9.35e-05 | 1810 | 1783.8562 | 508 | 0.1754 | 16.663 | 414 | 11.75 | 382
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 2026 | FALSE | 10220.4249 | 10220.4249 | 6.352 | 26 | 0.00034659 | 95 | 363.8152 | 1347 | 0.17512 | 4.5532 | 415 | 0.84 | 768
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | CB | FALSE | 17435.9444 | 12032.4791 | 7.4782 | 60 | 6.31e-05 | 2678 | 1838.5396 | 494 | 0.17499 | 10.4995 | 416 | 0.03 | 2401
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 3700 | FALSE | 29156.0449 | 29156.0449 | 18.1206 | 116 | 0.00013347 | 952 | 1560.5823 | 576 | 0.17472 | 20.2673 | 417 | 0.06 | 1905
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 710384 | FALSE | 15468.9282 | 8584.2298 | 5.3351 | 84 | 5.82e-05 | 2830 | 3710.5415 | 182 | 0.17469 | 14.6739 | 418 |  | 2697
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 913400 | TRUE | 1667.834 | 172.3529 | 0.10712 | 14 | 0.00011832 | 1223 | 1563.2661 | 575 | 0.17457 | 2.444 | 419 |  | 3465
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 1690 | FALSE | 26217.8201 | 17377.7027 | 10.8003 | 77 | 0.0001954 | 415 | 901.067 | 883 | 0.17449 | 13.4358 | 420 | 7.44 | 444
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 10090 | FALSE | 70938.5406 | 70938.5406 | 44.0886 | 435 | 5.7e-05 | 2861 | 3810.3636 | 167 | 0.17437 | 75.8506 | 421 | 0.3 | 1021
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | CB | FALSE | 4580.4088 | 3639.3631 | 2.2619 | 17 | 0.00012727 | 1059 | 1563.9973 | 574 | 0.1743 | 2.9631 | 422 |  | 3230
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 323962 | FALSE | 46007.9912 | 33116.5425 | 20.5821 | 282 | 7.39e-05 | 2363 | 2674.5475 | 317 | 0.17389 | 49.0357 | 423 | 22.52 | 293
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 51476 | FALSE | 10437.2128 | 7926.327 | 4.9262 | 74 | 9.43e-05 | 1787 | 2122.2216 | 419 | 0.1736 | 12.8462 | 424 | 14.32 | 355
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | N64 | FALSE | 20207.5385 | 17721.3198 | 11.0139 | 101 | 0.00011489 | 1302 | 1611.5581 | 558 | 0.17314 | 17.4874 | 425 | 0.05 | 2025
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 1217 | FALSE | 27736.9205 | 22843.3853 | 14.1973 | 116 | 5.9e-05 | 2808 | 3212.896 | 236 | 0.17295 | 20.0623 | 426 | 2.25 | 617
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 673618 | TRUE | 533.16 | 171.3788 | 0.10651 | 4 | 5.01e-05 | 3035 | 3451.8103 | 207 | 0.17294 | 0.69175 | 427 |  | 3547
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 35244 | FALSE | 28098.7686 | 28098.7686 | 17.4635 | 146 | 7.61e-05 | 2306 | 1918.8043 | 468 | 0.17286 | 25.237 | 428 | 0.1 | 1464
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 1960 | FALSE | 39696.7204 | 39696.7204 | 24.6717 | 223 | 4.46e-05 | 3171 | 4411.9471 | 113 | 0.17242 | 38.4488 | 429 | 0.42 | 933
7293 | WISE 11022234 | 152271102 | WISE 1102 | 2234 | FALSE | 24349.9914 | 24349.9914 | 15.1336 | 179 | 8.34e-05 | 2123 | 2208.9033 | 401 | 0.17198 | 30.784 | 430 | 1.04 | 723
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 421412 | FALSE | 5653.9032 | 1616.3093 | 1.0045 | 38 | 0.00012063 | 1173 | 1137.8972 | 758 | 0.17127 | 6.5083 | 431 |  | 3003
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 9722 | FALSE | 7647.7388 | 5139.2872 | 3.1941 | 55 | 9.27e-05 | 1828 | 2011.1796 | 454 | 0.17084 | 9.3959 | 432 | 2.06 | 625
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 10570 | FALSE | 15440.8056 | 15440.8056 | 9.5965 | 92 | 5.22e-05 | 2985 | 3374.5233 | 214 | 0.17053 | 15.6885 | 433 | 0.28 | 1043
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | N42 | FALSE | 9607.0794 | 5997.3144 | 3.7274 | 30 | 9.73e-05 | 1705 | 2091.1209 | 429 | 0.17017 | 5.105 | 434 | 0 | 2631
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 221165 | FALSE | 7814.4254 | 7056.9288 | 4.3859 | 39 | 7.13e-05 | 2439 | 2286.9555 | 387 | 0.17016 | 6.6364 | 435 |  | 2797
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 13372 | FALSE | 6191.0561 | 6152.1597 | 3.8236 | 5 | 3.54e-05 | 3342 | 4181.8896 | 139 | 0.17014 | 0.85069 | 436 | 1.32 | 686
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 9072 | FALSE | 46343.9208 | 46343.9208 | 28.8029 | 279 | 4.93e-05 | 3057 | 3602.3143 | 190 | 0.1698 | 47.3736 | 437 | 4.2 | 524
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 334476 | TRUE | 102.0354 | 89.9428 | 0.0559 | 2 | 3.68e-05 | 3318 | 3174.6241 | 245 | 0.16961 | 0.33922 | 438 |  | 3587
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 658 | FALSE | 21722.426 | 4561.1197 | 2.8348 | 136 | 9.62e-05 | 1727 | 1846.2822 | 492 | 0.16943 | 23.042 | 439 | 0.53 | 882
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 520 | FALSE | 75123.246 | 75123.246 | 46.6894 | 437 | 8.24e-05 | 2144 | 2644.041 | 320 | 0.16915 | 73.9165 | 440 | 35.85 | 210
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | CB | FALSE | 33441.4577 | 25226.3338 | 15.6783 | 190 | 6.6e-05 | 2589 | 2246.0111 | 394 | 0.16908 | 32.1248 | 441 | 5.92 | 477
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | X10 | FALSE | 70912.2192 | 34475.596 | 21.4267 | 156 | 7.31e-05 | 2393 | 2615.2408 | 327 | 0.16893 | 26.3532 | 442 | 0 | 2634
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 51794 | FALSE | 6308.4167 | 6303.8446 | 3.9179 | 32 | 0.00021523 | 339 | 651.61 | 1061 | 0.16883 | 5.4026 | 443 | 0.05 | 1924
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | XR564 | FALSE | 11653.8006 | 9126.8572 | 5.6724 | 81 | 0.0001173 | 1241 | 1539.4612 | 583 | 0.16792 | 13.6018 | 444 | 0.06 | 1891
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 6090 | TRUE | 1284.821 | 879.5421 | 0.54664 | 10 | 0.00015776 | 667 | 641.9698 | 1070 | 0.16726 | 1.6726 | 445 | 0.04 | 2133
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 82846 | FALSE | 8140.1207 | 7626.8316 | 4.7401 | 61 | 4.66e-05 | 3125 | 3781.4967 | 171 | 0.16626 | 10.1421 | 446 | 0.09 | 1543
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 2228 | FALSE | 34201.7241 | 33727.1471 | 20.9616 | 199 | 0.0001094 | 1423 | 1826.2902 | 498 | 0.16595 | 33.0243 | 447 | 0.19 | 1187
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 117616 | TRUE | 584.7856 | 298.3487 | 0.18542 | 5 | 0.00010782 | 1453 | 3364.4337 | 215 | 0.16564 | 0.82819 | 448 |  | 3494
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 772792 | FALSE | 4440.4408 | 3782.0495 | 2.3506 | 19 | 0.00011586 | 1274 | 1705.2974 | 522 | 0.16509 | 3.1366 | 449 |  | 3485
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 439572 | FALSE | 2069.8545 | 1977.3978 | 1.229 | 18 | 0.00012277 | 1136 | 1750.9686 | 514 | 0.16479 | 2.9663 | 450 |  | 3004
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | TS1115 | FALSE | 28340.5083 | 28340.5083 | 17.6137 | 147 | 6.61e-05 | 2584 | 2220.2472 | 396 | 0.16462 | 24.1996 | 451 | 0.06 | 1872
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 514412 | FALSE | 1675.5188 | 1659.5168 | 1.0314 | 5 | 8.06e-05 | 2190 | 2318.4458 | 382 | 0.16405 | 0.82024 | 452 |  | 3090
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 226562 | FALSE | 1660.7794 | 1371.9928 | 0.8527 | 7 | 8.61e-05 | 2031 | 1632.6529 | 550 | 0.16403 | 1.1482 | 453 |  | 3116
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 98896 | FALSE | 8090.5275 | 8090.5275 | 5.0283 | 25 | 7.98e-05 | 2213 | 2478.9758 | 348 | 0.16402 | 4.1004 | 454 | 0.04 | 2181
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | CB | FALSE | 19101.7778 | 10648.1095 | 6.6178 | 143 | 0.00016037 | 641 | 1368.6904 | 653 | 0.16378 | 23.42 | 455 | 0.24 | 1101
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 48480 | FALSE | 16927.9852 | 16927.9852 | 10.5208 | 125 | 0.00013445 | 937 | 1828.9756 | 497 | 0.16355 | 20.4433 | 456 | 0.7 | 806
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 915324 | FALSE | 5487.5306 | 3584.8296 | 2.228 | 27 | 4.76e-05 | 3097 | 3729.4821 | 179 | 0.16319 | 4.406 | 457 |  | 3321
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 530 | FALSE | 17644.1656 | 17644.1656 | 10.9659 | 23 | 0.00014892 | 752 | 1687.6433 | 526 | 0.16273 | 3.7427 | 458 | 0.71 | 801
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 561208 | FALSE | 4547.6852 | 1347.5454 | 0.8375 | 15 | 0.0001103 | 1407 | 1867.3968 | 484 | 0.1626 | 2.439 | 459 |  | 3487
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 94006 | FALSE | 24566.5609 | 22341.6897 | 13.8855 | 112 | 0.00010255 | 1585 | 1667.7925 | 536 | 0.1626 | 18.2107 | 460 | 0.05 | 1968
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | CB | FALSE | 19725.7628 | 17048.207 | 10.5955 | 144 | 0.00010337 | 1563 | 1745.3469 | 516 | 0.16238 | 23.3827 | 461 | 0.11 | 1421
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | CB | TRUE | 3.6129 | 3.6129 | 0.0022454 | 1 | 3.29e-05 | 3387 | 4925.3659 | 82 | 0.16185 | 0.16185 | 462 |  | 3620
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 34069 | FALSE | 25331.8473 | 25331.8473 | 15.7438 | 156 | 6.27e-05 | 2694 | 2622.4246 | 326 | 0.16138 | 25.1758 | 463 | 0.09 | 1525
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 98680 | TRUE | 46.5973 | 46.5973 | 0.02896 | 1 | 7.28e-05 | 2397 | 2215.7621 | 399 | 0.16135 | 0.16135 | 464 |  | 3628
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 1752 | FALSE | 16018.6134 | 13551.3973 | 8.4222 | 96 | 9.16e-05 | 1854 | 2012.9288 | 453 | 0.16096 | 15.4521 | 465 | 0.04 | 2161
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 37498 | FALSE | 26197.7415 | 26197.7415 | 16.282 | 129 | 0.00018072 | 507 | 890.6369 | 887 | 0.16073 | 20.7336 | 466 | 0.07 | 1723
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 7203 | FALSE | 30305.2229 | 29904.6733 | 18.5859 | 197 | 9.51e-05 | 1761 | 1859.3118 | 489 | 0.16043 | 31.6051 | 467 | 0.19 | 1194
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 48212 | FALSE | 17385.8137 | 17215.267 | 10.6994 | 110 | 0.00014482 | 804 | 1204.0224 | 729 | 0.1603 | 17.6327 | 468 | 18.57 | 319
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 605393 | FALSE | 40299.6716 | 33375.8865 | 20.7432 | 119 | 6.01e-05 | 2768 | 2777.2648 | 302 | 0.15998 | 19.0373 | 469 |  | 2710
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 1610 | FALSE | 61821.9357 | 61821.9357 | 38.4226 | 295 | 4.34e-05 | 3203 | 3907.4677 | 156 | 0.15996 | 47.1875 | 470 | 0.13 | 1340
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 428314 | FALSE | 29650.5939 | 23673.0872 | 14.7129 | 73 | 6.29e-05 | 2680 | 2640.9062 | 321 | 0.15993 | 11.675 | 471 |  | 2732
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 592404 | FALSE | 2658.3381 | 2642.3361 | 1.6422 | 20 | 0.00017008 | 563 | 1297.0483 | 685 | 0.15963 | 3.1926 | 472 |  | 3024
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 38438 | FALSE | 27128.309 | 27128.309 | 16.8604 | 181 | 9.16e-05 | 1855 | 1679.673 | 529 | 0.15947 | 28.8637 | 473 | 0.08 | 1665
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 548 | FALSE | 45554.629 | 44099.7789 | 27.4082 | 298 | 0.00022053 | 318 | 593.8352 | 1108 | 0.15935 | 47.4878 | 474 | 94.8 | 26
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 8721 | FALSE | 4901.8588 | 4400.8399 | 2.7351 | 29 | 5.09e-05 | 3017 | 2918.1731 | 285 | 0.1593 | 4.6198 | 475 | 0.04 | 2186
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 51238 | FALSE | 63137.7387 | 63137.7387 | 39.2404 | 335 | 5.16e-05 | 3004 | 2984.3431 | 269 | 0.15926 | 53.3509 | 476 | 2.31 | 614
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 84088 | FALSE | 28026.8017 | 25963.7603 | 16.1366 | 127 | 0.00012489 | 1101 | 1457.8018 | 614 | 0.15858 | 20.1391 | 477 |  | 2748
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 428534 | FALSE | 8740.0932 | 7301.7326 | 4.5381 | 18 | 6.06e-05 | 2760 | 3052.7595 | 263 | 0.15819 | 2.8474 | 478 |  | 2880
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 964556 | FALSE | 8160.0956 | 8116.5647 | 5.0445 | 31 | 0.00010503 | 1527 | 1599.6673 | 562 | 0.15803 | 4.8988 | 479 |  | 3279
7447 | BELL 1109CB | 152701109 | BELL 1109 | CB | TRUE | 5601.5402 | 484.8416 | 0.30133 | 53 | 0.00031144 | 116 | 533.425 | 1167 | 0.15794 | 8.3708 | 480 | 0.06 | 1805
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 24918 | FALSE | 8843.8557 | 8843.8557 | 5.4965 | 49 | 0.00017491 | 529 | 1042.2333 | 799 | 0.1575 | 7.7177 | 481 | 40.7 | 183
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 705777 | FALSE | 9890.0744 | 9890.0744 | 6.1467 | 46 | 0.00010551 | 1505 | 1615.1994 | 555 | 0.15746 | 7.2434 | 482 |  | 3062
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 542 | FALSE | 54014.7834 | 53958.2006 | 33.5352 | 311 | 0.00010864 | 1433 | 1525.8914 | 585 | 0.15746 | 48.9707 | 483 | 0.08 | 1662
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | CB | FALSE | 10535.3716 | 10535.3716 | 6.5478 | 40 | 5.82e-05 | 2827 | 2851.4073 | 292 | 0.15705 | 6.2822 | 484 | 0.03 | 2244
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 383183 | FALSE | 23681.1054 | 23566.6207 | 14.6467 | 53 | 0.0001153 | 1293 | 1780.7074 | 509 | 0.15687 | 8.3141 | 485 |  | 3164
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 152632 | FALSE | 3427.183 | 3099.3949 | 1.9263 | 13 | 5.64e-05 | 2875 | 2775.5237 | 304 | 0.15681 | 2.0385 | 486 |  | 3200
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 1456 | FALSE | 6155.4627 | 6155.4627 | 3.8256 | 46 | 0.00024152 | 242 | 701.6004 | 1021 | 0.15596 | 7.1739 | 487 | 25.79 | 270
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 5104 | FALSE | 2898.3737 | 2898.3737 | 1.8014 | 11 | 0.00010952 | 1422 | 1407.1508 | 634 | 0.15579 | 1.7137 | 488 | 0.08 | 1654
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 79306 | FALSE | 13157.0108 | 6087.9659 | 3.7837 | 73 | 0.00011173 | 1374 | 1345.2863 | 664 | 0.15551 | 11.352 | 489 | 5.6 | 482
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | R372 | FALSE | 6703.9319 | 6703.9319 | 4.1665 | 14 | 2.94e-05 | 3432 | 4227.7566 | 136 | 0.15539 | 2.1754 | 490 | 0 | 2626
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 869946 | FALSE | 47850.9 | 47850.9 | 29.7395 | 197 | 2.17e-05 | 3527 | 7360.2383 | 8 | 0.15534 | 30.6024 | 491 | 4.76 | 507
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 946229 | TRUE | 3345.1938 | 352.3912 | 0.21901 | 27 | 9.12e-05 | 1875 | 1903.3963 | 476 | 0.15489 | 4.1819 | 492 |  | 3308
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | CB | TRUE | 33.3215 | 28.7495 | 0.017868 | 2 | 0.00010268 | 1578 | 1672.4211 | 534 | 0.15464 | 0.30929 | 493 |  | 3632
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 19502 | FALSE | 92686.5675 | 72356.9682 | 44.9701 | 672 | 0.00010455 | 1541 | 1716.1429 | 520 | 0.15447 | 103.8019 | 494 | 25.98 | 269
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | CB | FALSE | 15673.7726 | 8550.61 | 5.3142 | 114 | 0.00011244 | 1357 | 1000.9631 | 834 | 0.15412 | 17.5695 | 495 | 0.03 | 2253
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 408 | FALSE | 61335.3992 | 60046.2209 | 37.319 | 280 | 0.00011339 | 1336 | 1624.3846 | 553 | 0.15401 | 43.1236 | 496 | 0.16 | 1258
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 7420 | FALSE | 37320.8645 | 37320.8645 | 23.1951 | 263 | 2.75e-05 | 3465 | 5752.6874 | 39 | 0.15397 | 40.4954 | 497 | 0.11 | 1450
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 88998 | FALSE | 22218.0314 | 12794.9324 | 7.9521 | 116 | 8.75e-05 | 2000 | 1675.3538 | 531 | 0.15352 | 17.8079 | 498 | 12.75 | 368
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 942170 | FALSE | 14564.2628 | 5038.647 | 3.1315 | 99 | 8.04e-05 | 2195 | 1848.528 | 490 | 0.15348 | 15.1945 | 499 |  | 2892
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | CB | FALSE | 19525.0238 | 11777.3852 | 7.3197 | 154 | 0.00010262 | 1582 | 1549.2867 | 579 | 0.15336 | 23.6178 | 500 | 0.1 | 1453
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | Y52 | FALSE | 33466.442 | 31529.2091 | 19.5955 | 141 | 6.22e-05 | 2713 | 2469.9036 | 349 | 0.15332 | 21.6184 | 501 | 0.22 | 1124
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | CB | FALSE | 40316.4241 | 40301.3395 | 25.0474 | 275 | 0.00012984 | 1011 | 1360.5287 | 658 | 0.15318 | 42.1242 | 502 | 0.14 | 1317
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 9480 | FALSE | 19971.3977 | 19971.3977 | 12.4123 | 80 | 7.41e-05 | 2352 | 2457.1272 | 350 | 0.15314 | 12.251 | 503 | 0.05 | 1946
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 1573 | FALSE | 29066.997 | 29066.997 | 18.0653 | 156 | 6.92e-05 | 2500 | 1984.6936 | 458 | 0.15282 | 23.8402 | 504 | 0.09 | 1514
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 2220 | FALSE | 45533.9477 | 44226.4373 | 27.4869 | 266 | 0.00015667 | 676 | 1115.795 | 768 | 0.15235 | 40.5244 | 505 | 0.28 | 1037
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 287172 | FALSE | 42975.8424 | 32888.5181 | 20.4403 | 258 | 0.00014341 | 820 | 1064.6586 | 789 | 0.15216 | 39.2578 | 506 | 0.11 | 1432
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 2012 | FALSE | 16177.0749 | 14813.8509 | 9.2069 | 64 | 7.9e-05 | 2236 | 2049.1767 | 445 | 0.15189 | 9.7211 | 507 | 0.03 | 2261
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | N48 | FALSE | 76703.6711 | 76703.6711 | 47.6716 | 292 | 6e-05 | 2778 | 2624.8703 | 325 | 0.15188 | 44.3489 | 508 | 0.11 | 1419
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 301886 | FALSE | 12466.9499 | 4239.6365 | 2.635 | 90 | 8.83e-05 | 1976 | 1844.2972 | 493 | 0.15165 | 13.6484 | 509 |  | 3073
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | N04 | TRUE | 859.5841 | 859.5841 | 0.53424 | 4 | 0.00013464 | 932 | 1420.9296 | 631 | 0.1516 | 0.60641 | 510 | 10.35 | 398
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 701650 | FALSE | 1191.0562 | 1191.0562 | 0.74025 | 12 | 0.00018462 | 478 | 500.0347 | 1199 | 0.15159 | 1.8191 | 511 |  | 3496
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 1280 | FALSE | 37796.6985 | 12933.8174 | 8.0384 | 238 | 0.00011562 | 1283 | 1326.8732 | 670 | 0.1512 | 35.9845 | 512 | 0.03 | 2282
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 14026 | FALSE | 16308.5205 | 16308.5205 | 10.1358 | 101 | 6.43e-05 | 2633 | 2347.8148 | 374 | 0.15084 | 15.2344 | 513 | 3.03 | 567
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 42344 | FALSE | 17541.9825 | 15185.6709 | 9.438 | 123 | 6e-05 | 2772 | 2518.1117 | 341 | 0.15077 | 18.5441 | 514 | 5.29 | 491
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 748272 | FALSE | 6311.5498 | 1206.1255 | 0.74961 | 26 | 6.92e-05 | 2501 | 2825.842 | 296 | 0.15028 | 3.9074 | 515 |  | 3317
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 618 | FALSE | 17470.7407 | 13890.2601 | 8.6329 | 119 | 8.87e-05 | 1961 | 1646.4565 | 544 | 0.15 | 17.8498 | 516 | 3.18 | 555
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | Y26 | FALSE | 25494.2608 | 24411.1885 | 15.1717 | 133 | 6.23e-05 | 2711 | 2408.6488 | 359 | 0.14946 | 19.8785 | 517 | 0.08 | 1586
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 37374 | FALSE | 3616.7474 | 3616.7474 | 2.2478 | 9 | 0.00024971 | 217 | 652.1813 | 1060 | 0.14938 | 1.3444 | 518 | 10.97 | 392
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 4522 | FALSE | 19482.3353 | 14178.9489 | 8.8123 | 128 | 0.00013265 | 968 | 1211.0142 | 727 | 0.14919 | 19.0963 | 519 | 1.62 | 661
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 51792 | FALSE | 15055.1772 | 15055.1772 | 9.3569 | 99 | 0.00012104 | 1164 | 1431.6373 | 622 | 0.14914 | 14.7646 | 520 | 0.08 | 1632
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | Y48 | FALSE | 19054.6896 | 7064.3192 | 4.3905 | 157 | 6.99e-05 | 2475 | 2423.7326 | 357 | 0.14907 | 23.4041 | 521 | 0.03 | 2278
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 1604 | FALSE | 29168.7634 | 6733.9297 | 4.1852 | 166 | 0.00022087 | 316 | 698.8592 | 1023 | 0.14905 | 24.7419 | 522 | 0.05 | 1969
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 537148 | TRUE | 2468.9992 | 923.0762 | 0.5737 | 14 | 8.97e-05 | 1921 | 711.3098 | 1014 | 0.14902 | 2.0863 | 523 |  | 3541
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 2180 | FALSE | 71112.0664 | 71112.0664 | 44.1964 | 444 | 8.9e-05 | 1947 | 1832.2635 | 495 | 0.1487 | 66.0238 | 524 | 0.31 | 1000
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 2181 | FALSE | 38165.6009 | 27116.6383 | 16.8531 | 120 | 3.7e-05 | 3315 | 4260.274 | 131 | 0.14869 | 17.8426 | 525 | 0.05 | 2017
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 2044 | FALSE | 20271.6961 | 13688.923 | 8.5077 | 67 | 0.00011519 | 1295 | 1533.5317 | 584 | 0.14865 | 9.9595 | 526 | 0.03 | 2330
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 87352 | FALSE | 42830.7404 | 42830.7404 | 26.6195 | 215 | 7.65e-05 | 2294 | 2120.5795 | 420 | 0.14862 | 31.9523 | 527 | 0.03 | 2333
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 307494 | FALSE | 54418.6325 | 49958.7477 | 31.0496 | 279 | 7.05e-05 | 2454 | 2167.8038 | 409 | 0.14841 | 41.4062 | 528 | 3.66 | 537
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 64044 | FALSE | 11992.1979 | 9649.0485 | 5.9969 | 46 | 6.4e-05 | 2645 | 2318.9503 | 380 | 0.14834 | 6.8236 | 529 | 0.92 | 747
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 12249 | FALSE | 3869.5175 | 3869.5175 | 2.4049 | 25 | 0.0001396 | 877 | 1383.6803 | 645 | 0.14826 | 3.7065 | 530 | 0.06 | 1811
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 11206 | FALSE | 28786.4552 | 28782.1678 | 17.8882 | 146 | 5.74e-05 | 2853 | 3353.7714 | 217 | 0.14787 | 21.5893 | 531 | 7.09 | 451
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 80454 | FALSE | 51836.245 | 51220.5161 | 31.8338 | 254 | 8.79e-05 | 1985 | 1652.3048 | 542 | 0.14786 | 37.5574 | 532 | 0.09 | 1550
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 196 | FALSE | 11699.1957 | 9030.0657 | 5.6122 | 36 | 5.85e-05 | 2820 | 2429.7049 | 356 | 0.14755 | 5.3118 | 533 | 1.88 | 635
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 66006 | FALSE | 14550.7056 | 14550.7056 | 9.0433 | 98 | 0.00016119 | 629 | 1078.2399 | 782 | 0.14747 | 14.4519 | 534 | 51.49 | 116
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | CB | FALSE | 14152.8775 | 11300.0596 | 7.023 | 87 | 0.00030831 | 120 | 452.1633 | 1245 | 0.14742 | 12.8257 | 535 | 0.09 | 1511
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 1026 | FALSE | 44906.7347 | 36171.5422 | 22.4808 | 273 | 7.21e-05 | 2414 | 2265.0826 | 390 | 0.14732 | 40.2177 | 536 | 0.08 | 1587
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 10110 | FALSE | 79840.1784 | 79840.1784 | 49.621 | 518 | 7.19e-05 | 2423 | 1946.3474 | 464 | 0.1471 | 76.1986 | 537 | 0.85 | 766
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 1636 | FALSE | 29887.6303 | 29071.18 | 18.0679 | 200 | 0.00012911 | 1025 | 1282.4693 | 688 | 0.14693 | 29.387 | 538 | 0.42 | 935
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | N40 | FALSE | 4749.4542 | 4628.046 | 2.8763 | 23 | 7.22e-05 | 2412 | 1911.8815 | 472 | 0.14681 | 3.3766 | 539 | 0.92 | 746
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 1348 | FALSE | 51267.8367 | 46964.6472 | 29.1887 | 357 | 6.45e-05 | 2628 | 2847.109 | 293 | 0.14666 | 52.3583 | 540 | 0.1 | 1507
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 5490 | FALSE | 40241.3391 | 40241.3391 | 25.0102 | 276 | 5.48e-05 | 2921 | 3287.8025 | 227 | 0.14657 | 40.4521 | 541 | 31.17 | 233
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 239062 | FALSE | 22613.4239 | 19618.6008 | 12.193 | 113 | 7.64e-05 | 2296 | 2401.1977 | 361 | 0.14634 | 16.5367 | 542 |  | 3021
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 68436 | FALSE | 14664.9715 | 14664.9715 | 9.1143 | 45 | 0.00011581 | 1278 | 1690.836 | 525 | 0.14627 | 6.582 | 543 | 3.52 | 544
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 2010 | FALSE | 10727.9171 | 10727.9171 | 6.6674 | 39 | 0.00053737 | 26 | 277.3564 | 1477 | 0.14585 | 5.6882 | 544 | 0.08 | 1579
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 19762 | FALSE | 8713.8007 | 7078.7756 | 4.3995 | 72 | 0.00017135 | 554 | 1134.0874 | 762 | 0.14549 | 10.4755 | 545 | 0.25 | 1082
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 2008 | FALSE | 29196.2282 | 9225.9589 | 5.734 | 154 | 5.6e-05 | 2886 | 2966.3445 | 274 | 0.14517 | 22.3567 | 546 | 2.46 | 601
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | N44 | FALSE | 29207.7388 | 29207.7388 | 18.1527 | 109 | 8.21e-05 | 2149 | 1862.5151 | 486 | 0.14496 | 15.8008 | 547 | 0.19 | 1171
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 1102 | FALSE | 69889.6015 | 69889.6015 | 43.4367 | 431 | 0.00010803 | 1451 | 1375.9559 | 650 | 0.14479 | 62.4048 | 548 | 0.21 | 1154
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 64090 | FALSE | 21993.72 | 21993.72 | 13.6692 | 170 | 4.43e-05 | 3181 | 3248.9701 | 228 | 0.1444 | 24.5486 | 549 | 4.94 | 501
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 1268 | FALSE | 17550.3384 | 17538.5447 | 10.9003 | 106 | 8.58e-05 | 2035 | 1744.856 | 517 | 0.14435 | 15.3013 | 550 | 0.13 | 1351
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 9590 | FALSE | 58387.0707 | 58387.0707 | 36.2878 | 387 | 6.18e-05 | 2727 | 2433.9636 | 353 | 0.144 | 55.7277 | 551 | 0.28 | 1045
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | A60 | FALSE | 14423.3233 | 11709.0953 | 7.2773 | 88 | 8.01e-05 | 2202 | 2043.3402 | 447 | 0.14391 | 12.6644 | 552 | 1.69 | 651
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 429006 | FALSE | 3229.4467 | 3213.4446 | 1.9972 | 23 | 0.00015434 | 701 | 805.9602 | 934 | 0.1436 | 3.3029 | 553 | 0.04 | 2192
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 1578 | FALSE | 56424.6884 | 48498.4276 | 30.142 | 269 | 5.31e-05 | 2963 | 2721.7009 | 308 | 0.14355 | 38.6147 | 554 | 0.07 | 1761
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | CB | FALSE | 20557.4413 | 20557.4413 | 12.7765 | 85 | 0.0001276 | 1055 | 1467.6776 | 609 | 0.14347 | 12.1951 | 555 | 0.15 | 1305
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 1448 | FALSE | 49484.9794 | 49484.9794 | 30.7551 | 232 | 9.54e-05 | 1749 | 1437.1719 | 620 | 0.14347 | 33.2848 | 556 | 0.06 | 1912
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 37384 | FALSE | 15082.1187 | 15082.1187 | 9.3736 | 71 | 6.72e-05 | 2554 | 2257.655 | 391 | 0.14324 | 10.17 | 557 | 0.13 | 1350
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 3990 | FALSE | 8945.4958 | 6963.5326 | 4.3279 | 25 | 3.45e-05 | 3361 | 3780.3852 | 172 | 0.14297 | 3.5744 | 558 | 0.05 | 1957
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 636 | FALSE | 15178.9816 | 15178.9816 | 9.4338 | 108 | 0.00010078 | 1628 | 1486.0094 | 600 | 0.14279 | 15.4213 | 559 | 5.46 | 486
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 65764 | FALSE | 16669.4005 | 16669.4005 | 10.3601 | 34 | 4.78e-05 | 3096 | 3350.0688 | 218 | 0.1423 | 4.8382 | 560 | 0.03 | 2268
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 189488 | FALSE | 1343.2605 | 1327.2585 | 0.8249 | 8 | 2.65e-05 | 3478 | 5673.1262 | 44 | 0.14211 | 1.1369 | 561 |  | 3556
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | Y12 | FALSE | 49636.2362 | 42701.7878 | 26.5393 | 274 | 4.9e-05 | 3063 | 2917.17 | 286 | 0.14205 | 38.9225 | 562 | 31.53 | 230
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 451856 | TRUE | 105.147 | 105.147 | 0.065349 | 2 | 5.05e-05 | 3022 | 2807.0375 | 299 | 0.14172 | 0.28345 | 563 |  | 3442
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 6392 | FALSE | 8838.9848 | 8838.9848 | 5.4935 | 37 | 7.97e-05 | 2215 | 1801.3357 | 505 | 0.14162 | 5.2399 | 564 | 16.9 | 336
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 242919 | FALSE | 2111.493 | 2111.493 | 1.3123 | 15 | 0.00019735 | 407 | 815.191 | 928 | 0.14151 | 2.1226 | 565 |  | 2911
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | CB | FALSE | 14807.5224 | 14807.5224 | 9.2029 | 54 | 0.00019854 | 400 | 804.6312 | 935 | 0.14139 | 7.6353 | 566 | 0.07 | 1742
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | M54 | FALSE | 48740.6445 | 31884.2274 | 19.8162 | 166 | 5.3e-05 | 2966 | 2348.1035 | 373 | 0.14114 | 23.4289 | 567 | 0.02 | 2478
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 2070 | FALSE | 46879.1188 | 28951.6433 | 17.9936 | 303 | 7.92e-05 | 2227 | 1863.8372 | 485 | 0.14111 | 42.7554 | 568 | 2.76 | 584
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | CB | FALSE | 1579.2012 | 1277.3495 | 0.79388 | 11 | 0.0001171 | 1244 | 1362.5146 | 655 | 0.14108 | 1.5519 | 569 | 0.61 | 848
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 746082 | FALSE | 1306.1318 | 1306.1318 | 0.81177 | 6 | 0.00011547 | 1287 | 1442.5612 | 617 | 0.14016 | 0.84097 | 570 | 0.11 | 1442
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 4650 | FALSE | 9890.161 | 6190.488 | 3.8474 | 80 | 0.0001146 | 1305 | 915.7398 | 878 | 0.14007 | 11.2058 | 571 | 0.03 | 2344
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 1616 | FALSE | 79228.8196 | 75536.2374 | 46.9461 | 454 | 5.18e-05 | 2998 | 2965.2949 | 276 | 0.13915 | 63.1735 | 572 | 3.66 | 538
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 4456 | FALSE | 37862.2156 | 37862.2156 | 23.5315 | 102 | 2.78e-05 | 3462 | 5239.6007 | 58 | 0.13881 | 14.1582 | 573 | 0.11 | 1440
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 2502 | FALSE | 28650.0789 | 28650.0789 | 17.8061 | 80 | 0.00011917 | 1201 | 1243.1177 | 705 | 0.13859 | 11.0874 | 574 | 0.04 | 2183
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 4160 | FALSE | 36723.9834 | 36723.9834 | 22.8241 | 192 | 7.1e-05 | 2443 | 2062.9169 | 441 | 0.13839 | 26.57 | 575 | 0.07 | 1759
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 152874 | TRUE | 1306.3422 | 982.3028 | 0.61051 | 10 | 6.49e-05 | 2611 | 2044.3409 | 446 | 0.13803 | 1.3803 | 576 |  | 3483
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 186060 | FALSE | 24068.765 | 17542.5963 | 10.9028 | 161 | 0.00011716 | 1242 | 1235.1524 | 709 | 0.13732 | 22.1085 | 577 |  | 2791
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 2679 | FALSE | 11435.2637 | 11435.2637 | 7.1071 | 70 | 6.46e-05 | 2619 | 2176.5839 | 406 | 0.13732 | 9.6123 | 578 | 23.85 | 281
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 34959 | FALSE | 42625.8356 | 41473.2756 | 25.7758 | 205 | 7.18e-05 | 2428 | 1907.4668 | 473 | 0.13657 | 27.9958 | 579 | 0.46 | 910
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 1516 | FALSE | 41402.7558 | 40856.6045 | 25.3925 | 123 | 9.24e-05 | 1832 | 1638.3577 | 549 | 0.13616 | 16.7471 | 580 | 0.06 | 1821
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 11300 | FALSE | 5912.6947 | 5912.6947 | 3.6748 | 41 | 0.00013924 | 881 | 1480.6406 | 604 | 0.1361 | 5.5803 | 581 | 0.19 | 1177
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 51582 | FALSE | 15330.2671 | 15330.2671 | 9.5278 | 105 | 0.00014185 | 842 | 981.2465 | 843 | 0.13574 | 14.2523 | 582 | 0.04 | 2150
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 732836 | FALSE | 24952.5776 | 18788.6293 | 11.6772 | 154 | 4.13e-05 | 3239 | 3303.5879 | 224 | 0.1353 | 20.8364 | 583 |  | 2673
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 720 | FALSE | 13087.7745 | 10923.6575 | 6.7891 | 70 | 6.34e-05 | 2663 | 2299.4316 | 384 | 0.1353 | 9.4707 | 584 | 2.79 | 580
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 4230 | FALSE | 36923.3874 | 36847.6248 | 22.9009 | 59 | 0.00036561 | 80 | 373.6796 | 1331 | 0.13512 | 7.9721 | 585 | 0.02 | 2536
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 13352 | FALSE | 58907.8743 | 55896.819 | 34.7401 | 409 | 0.00012489 | 1100 | 1100.974 | 774 | 0.13486 | 55.1568 | 586 | 30.41 | 238
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 594143 | TRUE | 6633.044 | 814.5641 | 0.50625 | 60 | 9.58e-05 | 1734 | 729.5737 | 990 | 0.13461 | 8.0769 | 587 |  | 3123
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 406 | FALSE | 53036.2911 | 19984.6537 | 12.4205 | 312 | 8.84e-05 | 1975 | 1508.2873 | 594 | 0.1343 | 41.9011 | 588 | 0.13 | 1362
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 7849F | FALSE | 13949.6344 | 13949.6344 | 8.6698 | 61 | 3.16e-05 | 3406 | 5019.3612 | 73 | 0.13395 | 8.1711 | 589 | 0.04 | 2222
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 348657 | FALSE | 3761.8937 | 3253.8359 | 2.0223 | 29 | 8.36e-05 | 2107 | 2006.4651 | 455 | 0.13388 | 3.8825 | 590 |  | 3007
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 870548 | FALSE | 8185.9487 | 8185.9487 | 5.0876 | 56 | 0.00010519 | 1515 | 1377.0688 | 649 | 0.13326 | 7.4625 | 591 |  | 3309
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 76020 | FALSE | 23407.8426 | 15031.7581 | 9.3423 | 137 | 5.5e-05 | 2910 | 2512.6527 | 342 | 0.13318 | 18.2456 | 592 | 0.45 | 918
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 1306 | FALSE | 19638.9419 | 15260.277 | 9.4843 | 117 | 9.05e-05 | 1898 | 1507.2616 | 595 | 0.13303 | 15.5648 | 593 | 0.07 | 1743
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 2540 | FALSE | 28748.5934 | 26122.3431 | 16.2351 | 135 | 0.00054969 | 24 | 203.3955 | 1636 | 0.13296 | 17.9496 | 594 | 0.02 | 2424
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | CB | TRUE | 1312.9371 | 596.6183 | 0.3708 | 11 | 0.00014984 | 739 | 1023.6412 | 812 | 0.13274 | 1.4601 | 595 | 0.08 | 1591
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 10416 | FALSE | 1110.1976 | 1110.1976 | 0.68999 | 7 | 0.00010788 | 1452 | 1426.8175 | 628 | 0.1325 | 0.92748 | 596 | 0.02 | 2491
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 770 | FALSE | 24751.8286 | 13838.1959 | 8.6005 | 110 | 0.00012303 | 1134 | 1361.4118 | 656 | 0.13217 | 14.5382 | 597 | 0.02 | 2513
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 384582 | FALSE | 7304.3535 | 7304.3535 | 4.5397 | 8 | 5.19e-05 | 2994 | 4044.7807 | 147 | 0.13184 | 1.0547 | 598 |  | 3417
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 96390 | FALSE | 16282.4885 | 13753.525 | 8.5479 | 124 | 0.00016254 | 620 | 924.5376 | 871 | 0.13125 | 16.2749 | 599 | 0.12 | 1378
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | CB | FALSE | 16260.0032 | 8994.5064 | 5.5901 | 86 | 9.36e-05 | 1807 | 1513.1588 | 589 | 0.1308 | 11.2491 | 600 | 0.04 | 2129
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | CB | FALSE | 14117.7933 | 14117.7933 | 8.7743 | 70 | 8.39e-05 | 2095 | 1625.1549 | 551 | 0.13063 | 9.1442 | 601 | 0.03 | 2355
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 9753 | FALSE | 3306.1166 | 3306.1166 | 2.0548 | 23 | 6.15e-05 | 2733 | 2174.098 | 407 | 0.13059 | 3.0036 | 602 | 0.08 | 1584
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 627416 | TRUE | 5034.3822 | 971.5124 | 0.6038 | 14 | 9.45e-05 | 1779 | 1192.7699 | 735 | 0.13024 | 1.8234 | 603 |  | 3590
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 13474 | FALSE | 11606.5963 | 4726.1259 | 2.9373 | 99 | 9.89e-05 | 1672 | 1472.7962 | 605 | 0.13001 | 12.8713 | 604 | 1.54 | 666
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 309438 | FALSE | 13011.7309 | 5938.6322 | 3.6909 | 93 | 0.00010698 | 1474 | 1153.73 | 754 | 0.12966 | 12.0584 | 605 |  | 3000
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 2212 | FALSE | 14695.9754 | 14695.9754 | 9.1336 | 76 | 0.00022108 | 315 | 358.4844 | 1358 | 0.12922 | 9.8207 | 606 | 41.81 | 174
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 1304 | FALSE | 30935.6957 | 30935.6957 | 19.2267 | 175 | 7.33e-05 | 2386 | 1973.0848 | 460 | 0.12902 | 22.578 | 607 | 0.29 | 1031
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 886522 | FALSE | 30828.6552 | 10908.527 | 6.7797 | 154 | 6.15e-05 | 2736 | 2215.6632 | 400 | 0.12899 | 19.8644 | 608 |  | 2965
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 1520 | FALSE | 31725.4009 | 6700.2969 | 4.1643 | 230 | 0.00011878 | 1212 | 1243.3344 | 704 | 0.1287 | 29.6011 | 609 | 0.04 | 2162
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 5391 | FALSE | 1530.1829 | 1530.1829 | 0.95101 | 7 | 4.93e-05 | 3055 | 2595.0683 | 333 | 0.12868 | 0.90075 | 610 | 2.85 | 575
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 19042 | FALSE | 13701.0778 | 10069.7209 | 6.2584 | 89 | 0.00010259 | 1584 | 1548.81 | 581 | 0.12861 | 11.4466 | 611 | 0.17 | 1229
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 356 | FALSE | 24352.0152 | 17245.1485 | 10.7179 | 136 | 0.00012922 | 1022 | 991.1123 | 839 | 0.12847 | 17.4723 | 612 | 8.54 | 423
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 7446 | FALSE | 69991.8942 | 69991.8942 | 43.5002 | 427 | 0.00013367 | 949 | 983.1088 | 842 | 0.12828 | 54.7764 | 613 | 0.18 | 1220
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 35588 | FALSE | 4954.8551 | 4954.8551 | 3.0795 | 18 | 9.28e-05 | 1827 | 1278.0574 | 690 | 0.12786 | 2.3016 | 614 | 0.6 | 851
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 59763 | FALSE | 4532.1933 | 4532.1933 | 2.8168 | 30 | 5.5e-05 | 2912 | 2480.207 | 346 | 0.12716 | 3.8149 | 615 | 2.26 | 616
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 1702 | FALSE | 29294.348 | 26958.2044 | 16.7546 | 177 | 4.22e-05 | 3220 | 3360.288 | 216 | 0.12716 | 22.5069 | 616 | 0.14 | 1332
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 188268 | FALSE | 8709.5262 | 6867.4982 | 4.2682 | 66 | 0.00013545 | 924 | 756.6199 | 968 | 0.1264 | 8.3425 | 617 |  | 2932
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 7823F | FALSE | 7527.4054 | 7527.4054 | 4.6783 | 49 | 2.61e-05 | 3486 | 5142.2922 | 63 | 0.12636 | 6.1917 | 618 | 0.06 | 1848
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 877670 | FALSE | 10595.2996 | 10595.2996 | 6.585 | 28 | 7.93e-05 | 2225 | 1606.4027 | 561 | 0.12626 | 3.5352 | 619 | 0.06 | 1803
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | W80 | FALSE | 30507.2399 | 30491.2345 | 18.9504 | 129 | 0.00012461 | 1105 | 990.5879 | 840 | 0.12598 | 16.2519 | 620 | 0.26 | 1062
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 350030 | FALSE | 14009.015 | 9325.238 | 5.7957 | 107 | 0.00012847 | 1039 | 957.5657 | 855 | 0.12598 | 13.4795 | 621 |  | 3314
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 288980 | TRUE | 1137.5268 | 532.3299 | 0.33085 | 6 | 5.38e-05 | 2947 | 2359.4228 | 370 | 0.12531 | 0.75188 | 622 |  | 3583
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 955138 | FALSE | 4475.7732 | 4227.5124 | 2.6274 | 16 | 6.76e-05 | 2548 | 1883.3994 | 478 | 0.12515 | 2.0024 | 623 |  | 3270
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 1330 | FALSE | 50161.9849 | 49990.913 | 31.0696 | 264 | 0.00011447 | 1308 | 1373.7242 | 651 | 0.12503 | 33.0087 | 624 | 0.19 | 1173
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 5152 | FALSE | 2685.0442 | 2685.0442 | 1.6688 | 17 | 0.00018787 | 456 | 675.7903 | 1038 | 0.1239 | 2.1064 | 625 | 12.52 | 374
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 1282 | FALSE | 26604.6713 | 22934.9277 | 14.2542 | 164 | 7.89e-05 | 2239 | 1748.6654 | 515 | 0.12376 | 20.2971 | 626 | 4.57 | 514
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | CB | FALSE | 14342.9846 | 2348.085 | 1.4593 | 124 | 5.55e-05 | 2900 | 1580.4692 | 569 | 0.12375 | 15.3456 | 627 | 0.03 | 2351
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 1644 | FALSE | 36747.479 | 36747.479 | 22.8387 | 244 | 0.00010131 | 1620 | 1382.8849 | 646 | 0.12375 | 30.1941 | 628 | 0.08 | 1604
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 78448 | FALSE | 47671.1997 | 31387.7639 | 19.5076 | 188 | 3.17e-05 | 3405 | 4051.9056 | 146 | 0.12365 | 23.2453 | 629 | 0.05 | 2059
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 1770 | FALSE | 13849.8333 | 13849.8333 | 8.6077 | 66 | 0.00044353 | 51 | 343.9532 | 1380 | 0.12342 | 8.1457 | 630 | 0.02 | 2504
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | Y06 | FALSE | 63281.543 | 48855.5405 | 30.3639 | 304 | 5.49e-05 | 2917 | 2033.2985 | 450 | 0.12317 | 37.4433 | 631 | 0.14 | 1333
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 10587 | FALSE | 35336.5514 | 35336.5514 | 21.9618 | 212 | 8.41e-05 | 2092 | 1469.4238 | 607 | 0.12297 | 26.0703 | 632 | 0.13 | 1334
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 156 | FALSE | 18958.8699 | 9919.8336 | 6.1652 | 110 | 0.00012453 | 1107 | 875.9596 | 896 | 0.12268 | 13.4944 | 633 | 0.21 | 1144
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 69866 | FALSE | 10571.2356 | 10571.2356 | 6.5701 | 46 | 0.00023172 | 281 | 514.4343 | 1188 | 0.12256 | 5.6379 | 634 | 3.53 | 543
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 705100 | FALSE | 13322.8036 | 11885.1942 | 7.3867 | 78 | 0.00013638 | 915 | 900.0548 | 884 | 0.12223 | 9.5341 | 635 |  | 3106
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 7110 | FALSE | 29983.2616 | 29983.2616 | 18.6347 | 132 | 4.04e-05 | 3258 | 3332.8764 | 221 | 0.12197 | 16.0996 | 636 | 0.03 | 2230
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 604 | FALSE | 28058.6741 | 28058.6741 | 17.4386 | 169 | 0.00010038 | 1638 | 1390.9913 | 641 | 0.12169 | 20.5661 | 637 | 38.24 | 196
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 781445 | TRUE | 577.8877 | 405.5365 | 0.25204 | 6 | 0.00010546 | 1508 | 1075.6001 | 784 | 0.12145 | 0.72871 | 638 |  | 3291
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 153199 | FALSE | 8788.2197 | 4750.5459 | 2.9525 | 53 | 5e-05 | 3037 | 2588.0496 | 334 | 0.1214 | 6.4339 | 639 |  | 3364
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 572 | FALSE | 34429.3225 | 34429.3225 | 21.398 | 155 | 0.00020812 | 372 | 588.4642 | 1115 | 0.12097 | 18.7503 | 640 | 5.06 | 497
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | A16 | FALSE | 32308.0619 | 31835.9088 | 19.7861 | 122 | 9.91e-05 | 1665 | 1262.4628 | 693 | 0.12088 | 14.7476 | 641 | 0.07 | 1702
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 2455 | FALSE | 10165.5764 | 10165.5764 | 6.3179 | 84 | 3.52e-05 | 3348 | 3535.7199 | 196 | 0.12034 | 10.1082 | 642 | 0.08 | 1657
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 3008 | FALSE | 24475.225 | 13636.9493 | 8.4754 | 55 | 6.88e-05 | 2515 | 2119.5029 | 421 | 0.1202 | 6.6112 | 643 | 0.01 | 2614
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | CB | FALSE | 66423.2503 | 66423.2503 | 41.2823 | 448 | 0.00014731 | 770 | 1022.0989 | 813 | 0.12006 | 53.7868 | 644 | 29.66 | 239
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 1504 | FALSE | 23629.2409 | 17735.4007 | 11.0226 | 186 | 0.00021184 | 352 | 618.3499 | 1084 | 0.12006 | 22.3307 | 645 | 0.12 | 1402
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | CB | FALSE | 1831.3319 | 1593.4993 | 0.99037 | 15 | 0.00021275 | 345 | 713.5234 | 1009 | 0.11989 | 1.7983 | 646 | 0.07 | 1726
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 855412 | FALSE | 50683.3516 | 45702.3865 | 28.4042 | 108 | 6.44e-05 | 2629 | 1812.7947 | 504 | 0.11956 | 12.9123 | 647 | 0.05 | 2051
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 3152 | FALSE | 27364.6036 | 26923.3255 | 16.733 | 134 | 8.44e-05 | 2079 | 1552.0849 | 578 | 0.11956 | 16.0208 | 648 | 0.08 | 1624
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 7722 | FALSE | 100229.7186 | 96782.5255 | 60.1507 | 572 | 0.00010462 | 1540 | 1087.3028 | 779 | 0.11928 | 68.2291 | 649 | 0.25 | 1084
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 1264 | FALSE | 56286.9636 | 56286.9636 | 34.9826 | 307 | 0.00011647 | 1260 | 1094.5256 | 776 | 0.11917 | 36.585 | 650 | 0.39 | 957
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | CB | FALSE | 45692.926 | 45174.6839 | 28.0762 | 315 | 0.00014305 | 825 | 1166.4722 | 747 | 0.11916 | 37.536 | 651 | 0.25 | 1090
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 822606 | FALSE | 29230.0954 | 21701.9466 | 13.4878 | 144 | 3.21e-05 | 3400 | 3717.2296 | 181 | 0.11894 | 17.1275 | 652 |  | 2678
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | MR186 | TRUE | 4135.7533 | 818.8837 | 0.50894 | 27 | 8.95e-05 | 1933 | 1490.2334 | 599 | 0.11874 | 3.2061 | 653 | 0.02 | 2461
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 8372 | FALSE | 101264.4904 | 94481.7777 | 58.7208 | 629 | 0.00011802 | 1229 | 985.1922 | 841 | 0.11858 | 74.5861 | 654 | 0.21 | 1139
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 9400 | FALSE | 101537.78 | 101537.78 | 63.1061 | 667 | 6.69e-05 | 2561 | 1882.7942 | 479 | 0.11849 | 79.0304 | 655 | 1.17 | 705
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | N62 | FALSE | 8948.1922 | 8948.1922 | 5.5613 | 39 | 7.05e-05 | 2455 | 1674.5706 | 532 | 0.11842 | 4.6183 | 656 | 0.13 | 1344
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | CB | FALSE | 30610.8387 | 30610.8387 | 19.0248 | 245 | 0.00018342 | 484 | 745.8005 | 978 | 0.11812 | 28.9401 | 657 | 0.61 | 844
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | CB | FALSE | 39248.3153 | 36287.6403 | 22.5529 | 243 | 0.00015786 | 664 | 1177.1526 | 742 | 0.11807 | 28.6917 | 658 | 0.1 | 1491
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 528460 | FALSE | 6121.8319 | 3043.5918 | 1.8916 | 12 | 3.99e-05 | 3271 | 3097.7847 | 255 | 0.11792 | 1.415 | 659 |  | 3454
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 6110 | FALSE | 47929.948 | 17714.3763 | 11.0096 | 179 | 4.19e-05 | 3228 | 2595.4532 | 332 | 0.11737 | 21.0097 | 660 | 0.03 | 2313
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 50140 | FALSE | 10038.7802 | 6357.3386 | 3.9511 | 82 | 0.0001527 | 722 | 724.1364 | 995 | 0.11734 | 9.6215 | 661 | 0.07 | 1721
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 777686 | FALSE | 3079.762 | 2707.2733 | 1.6826 | 17 | 6.2e-05 | 2721 | 2050.5492 | 444 | 0.11731 | 1.9944 | 662 |  | 3452
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 58626 | FALSE | 24491.7338 | 24491.7338 | 15.2217 | 125 | 9.12e-05 | 1869 | 1427.3169 | 627 | 0.117 | 14.6249 | 663 | 33.89 | 218
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 157026 | FALSE | 5200.077 | 5200.077 | 3.2319 | 44 | 6.61e-05 | 2586 | 1923.6933 | 467 | 0.11682 | 5.1403 | 664 | 0.05 | 1989
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 11232 | FALSE | 27747.6591 | 20505.608 | 12.7443 | 222 | 7.77e-05 | 2269 | 1686.0292 | 527 | 0.11656 | 25.8772 | 665 | 3.3 | 550
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 2102 | FALSE | 62912.0633 | 60307.8799 | 37.4816 | 417 | 0.00013035 | 1002 | 1146.8943 | 755 | 0.11621 | 48.4576 | 666 | 0.75 | 787
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | CB | FALSE | 12241.4218 | 6260.0525 | 3.8906 | 90 | 0.00013491 | 927 | 773.6055 | 956 | 0.11609 | 10.4477 | 667 | 0.03 | 2310
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 484 | FALSE | 78528.1935 | 53688.8082 | 33.3678 | 379 | 0.00011833 | 1222 | 896.8187 | 885 | 0.11607 | 43.9888 | 668 | 0.17 | 1225
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | CB | FALSE | 18716.5111 | 18050.1072 | 11.2182 | 124 | 0.00013241 | 974 | 792.6979 | 948 | 0.11592 | 14.3743 | 669 | 0.08 | 1643
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 119949 | FALSE | 3756.7927 | 2221.8702 | 1.3809 | 25 | 7.56e-05 | 2320 | 1497.9784 | 598 | 0.11529 | 2.8822 | 670 |  | 3429
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | CB | FALSE | 21668.4067 | 9680.057 | 6.0162 | 110 | 0.00011397 | 1323 | 734.8074 | 989 | 0.11521 | 12.6729 | 671 | 0.03 | 2334
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 745811 | TRUE | 780.426 | 641.2916 | 0.39857 | 8 | 7.9e-05 | 2235 | 1106.1185 | 773 | 0.11506 | 0.92047 | 672 |  | 3113
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 91900 | FALSE | 22248.6035 | 14519.294 | 9.0238 | 91 | 0.00012885 | 1031 | 1012.5441 | 824 | 0.11491 | 10.4566 | 673 | 1.72 | 650
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 97354 | FALSE | 16339.8299 | 14168.242 | 8.8056 | 59 | 2.35e-05 | 3509 | 5418.3509 | 49 | 0.11488 | 6.7778 | 674 | 0.06 | 1885
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 19642 | FALSE | 2579.2739 | 1246.4399 | 0.77467 | 17 | 0.00024874 | 219 | 453.1258 | 1242 | 0.11477 | 1.9511 | 675 | 0.96 | 739
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 9470 | FALSE | 36749.5976 | 36749.5976 | 22.84 | 277 | 8.87e-05 | 1964 | 1395.4992 | 639 | 0.11474 | 31.7833 | 676 | 0.01 | 2586
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 943820 | FALSE | 3953.9711 | 3039.5845 | 1.8891 | 13 | 9e-05 | 1913 | 1434.295 | 621 | 0.11464 | 1.4903 | 677 |  | 3527
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 1594 | FALSE | 39042.2093 | 39042.2093 | 24.2649 | 160 | 0.00012552 | 1089 | 1126.4421 | 765 | 0.11449 | 18.3178 | 678 | 0.12 | 1390
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 10240 | FALSE | 34689.059 | 34689.059 | 21.5594 | 189 | 7.43e-05 | 2350 | 1439.7612 | 619 | 0.11431 | 21.6045 | 679 | 0.31 | 1009
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 674 | FALSE | 32462.2926 | 27296.9382 | 16.9652 | 122 | 0.00011908 | 1203 | 1499.689 | 597 | 0.11401 | 13.9092 | 680 | 0.15 | 1285
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 61892 | FALSE | 48456.6488 | 48456.6488 | 30.116 | 318 | 8.1e-05 | 2183 | 1584.3018 | 567 | 0.11372 | 36.1635 | 681 | 38.89 | 193
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 55206 | TRUE | 3467.0084 | 0 | 0 | 28 | 0.00010976 | 1415 | 967.1576 | 851 | 0.11351 | 3.1783 | 682 | 0.04 | 2213
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 734 | FALSE | 26724.9411 | 22050.8989 | 13.7047 | 162 | 0.00015037 | 732 | 885.8837 | 889 | 0.11348 | 18.3842 | 683 | 1.06 | 719
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | CB | FALSE | 19422.567 | 19422.567 | 12.0712 | 106 | 0.00011506 | 1297 | 1154.679 | 753 | 0.11341 | 12.0218 | 684 | 5.58 | 484
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 45262 | FALSE | 46333.9347 | 46333.9347 | 28.7967 | 221 | 0.00010272 | 1577 | 1038.3077 | 800 | 0.11334 | 25.0485 | 685 | 0.06 | 1915
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 1344 | FALSE | 20065.0071 | 16285.3354 | 10.1214 | 152 | 6.93e-05 | 2497 | 2362.2491 | 369 | 0.11327 | 17.2178 | 686 | 4.34 | 522
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 699062 | FALSE | 3006.4235 | 1359.6473 | 0.84503 | 20 | 8.65e-05 | 2024 | 1257.9802 | 696 | 0.11322 | 2.2645 | 687 |  | 3300
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 12392 | FALSE | 23572.5391 | 23572.5391 | 14.6504 | 178 | 0.00010936 | 1424 | 1246.8521 | 703 | 0.11309 | 20.1293 | 688 | 55.71 | 101
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 421358 | FALSE | 23870.6711 | 23870.6711 | 14.8357 | 169 | 0.00012254 | 1140 | 802.5537 | 940 | 0.11286 | 19.0733 | 689 |  | 2784
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 722 | FALSE | 12705.3582 | 12705.3582 | 7.8964 | 99 | 0.00026082 | 194 | 569.6012 | 1130 | 0.11274 | 11.1613 | 690 | 46.62 | 140
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 3751 | FALSE | 16451.1737 | 15802.8651 | 9.8215 | 65 | 4.49e-05 | 3163 | 3153.8117 | 247 | 0.11269 | 7.325 | 691 | 0.03 | 2272
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | CB | FALSE | 14665.1565 | 5449.7896 | 3.3871 | 81 | 0.00012146 | 1157 | 1050.3758 | 796 | 0.11258 | 9.1187 | 692 | 0.04 | 2099
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 51756 | FALSE | 56082.3102 | 17440.8058 | 10.8395 | 264 | 8.5e-05 | 2060 | 1131.9939 | 763 | 0.11252 | 29.7041 | 693 | 1.15 | 707
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 501106 | FALSE | 16962.6839 | 16083.896 | 9.9962 | 86 | 2.29e-05 | 3513 | 4753.376 | 97 | 0.11248 | 9.6734 | 694 |  | 2889
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 19772 | FALSE | 29712.1582 | 28840.3765 | 17.9244 | 185 | 0.00010637 | 1489 | 1084.3194 | 780 | 0.11233 | 20.7806 | 695 | 41.36 | 177
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 593454 | FALSE | 65282.8123 | 51502.8241 | 32.0092 | 324 | 8.7e-05 | 2012 | 1565.5344 | 572 | 0.11221 | 36.3549 | 696 |  | 2656
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 1530 | FALSE | 28483.8521 | 18168.0106 | 11.2915 | 167 | 5.61e-05 | 2884 | 2176.9842 | 405 | 0.11218 | 18.7349 | 697 | 0.01 | 2573
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 81296 | FALSE | 24680.7336 | 17571.0511 | 10.9205 | 124 | 0.00010636 | 1490 | 869.9858 | 899 | 0.11218 | 13.9107 | 698 | 0.05 | 2005
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 77546 | FALSE | 69346.9328 | 69346.9328 | 43.0994 | 403 | 9.51e-05 | 1762 | 1309.4241 | 678 | 0.11214 | 45.1922 | 699 | 0.19 | 1189
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 752630 | FALSE | 30558.9663 | 30558.9663 | 18.9925 | 154 | 6.48e-05 | 2614 | 1699.6449 | 523 | 0.11205 | 17.2553 | 700 |  | 2886
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 213984 | FALSE | 11162.845 | 11162.845 | 6.9378 | 47 | 9.45e-05 | 1780 | 1225.6338 | 715 | 0.11198 | 5.263 | 701 |  | 2957
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 38748 | FALSE | 24704.6186 | 24704.6186 | 15.354 | 178 | 7.18e-05 | 2426 | 1618.5371 | 554 | 0.11192 | 19.9215 | 702 | 0.01 | 2604
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 99720 | FALSE | 19787.8115 | 14780.8133 | 9.1863 | 134 | 8.82e-05 | 1977 | 1157.381 | 751 | 0.11177 | 14.9768 | 703 | 7.05 | 453
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | CB | FALSE | 17394.4702 | 14019.0953 | 8.7129 | 134 | 0.00023184 | 280 | 615.3789 | 1088 | 0.11172 | 14.9707 | 704 | 0.06 | 1909
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 75370 | FALSE | 23702.8229 | 17823.7139 | 11.0775 | 133 | 0.0001129 | 1346 | 1122.5953 | 767 | 0.11161 | 14.8441 | 705 | 0.05 | 2009
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 37586 | FALSE | 22457.0278 | 22457.0278 | 13.9571 | 72 | 0.00013606 | 919 | 959.2045 | 854 | 0.11137 | 8.0187 | 706 | 0.07 | 1736
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 7831 | FALSE | 14300.9674 | 14300.9674 | 8.8881 | 86 | 5.82e-05 | 2831 | 1904.4724 | 475 | 0.1113 | 9.5719 | 707 | 0.1 | 1473
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 317796 | FALSE | 11760.0744 | 8148.5566 | 5.0644 | 65 | 7.02e-05 | 2466 | 1382.5193 | 647 | 0.11087 | 7.2063 | 708 |  | 3222
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 585 | FALSE | 22730.6202 | 22730.6202 | 14.1272 | 95 | 6.22e-05 | 2714 | 1313.2645 | 677 | 0.11082 | 10.5283 | 709 | 0.1 | 1490
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 690954 | FALSE | 6889.4894 | 6410.0397 | 3.9839 | 12 | 1.55e-05 | 3583 | 7160.5307 | 9 | 0.11057 | 1.3268 | 710 |  | 3318
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | CB | FALSE | 53866.9528 | 51789.1777 | 32.1872 | 417 | 0.00011056 | 1401 | 1269.855 | 691 | 0.11044 | 46.0525 | 711 | 0.78 | 780
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | CB | TRUE | 7260.7146 | 263.08 | 0.16351 | 61 | 0.00011907 | 1204 | 713.2367 | 1010 | 0.1104 | 6.7341 | 712 | 0.02 | 2463
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 839302 | FALSE | 1806.4039 | 1806.4039 | 1.1227 | 8 | 4.49e-05 | 3164 | 2564.3756 | 337 | 0.11001 | 0.88007 | 713 |  | 3595
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 1204 | FALSE | 47393.9854 | 41374.6655 | 25.7145 | 233 | 8.9e-05 | 1950 | 1305.1155 | 679 | 0.10989 | 25.6033 | 714 | 0.09 | 1553
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 2790 | FALSE | 17696.042 | 16028.2028 | 9.9616 | 115 | 0.00014264 | 831 | 967.5085 | 850 | 0.10954 | 12.5971 | 715 | 0.18 | 1201
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 68190 | FALSE | 40559.778 | 38588.9503 | 23.9832 | 238 | 3.63e-05 | 3328 | 3033.8848 | 265 | 0.10937 | 26.0311 | 716 | 0.06 | 1813
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 664732 | FALSE | 1437.8147 | 1437.8147 | 0.89361 | 6 | 9.09e-05 | 1884 | 1650.3416 | 543 | 0.10842 | 0.65051 | 717 | 1.72 | 649
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 600 | FALSE | 39281.1533 | 30870.3 | 19.186 | 164 | 0.00011588 | 1272 | 1083.2564 | 781 | 0.10818 | 17.7408 | 718 | 0.15 | 1297
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | CB | FALSE | 7158.565 | 3619.1597 | 2.2493 | 59 | 0.00018211 | 497 | 299.7205 | 1447 | 0.10789 | 6.3658 | 719 | 0.1 | 1483
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 229588 | FALSE | 21565.3961 | 15531.0208 | 9.6526 | 149 | 8.87e-05 | 1963 | 1224.4513 | 716 | 0.10786 | 16.0708 | 720 |  | 3033
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 1623 | FALSE | 24554.2111 | 24554.2111 | 15.2605 | 152 | 7.63e-05 | 2301 | 1590.8242 | 564 | 0.1076 | 16.3546 | 721 | 0.2 | 1165
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 551904 | TRUE | 35.7178 | 35.7178 | 0.022199 | 1 | 0.00014066 | 859 | 763.0871 | 960 | 0.10733 | 0.10733 | 722 | 0.87 | 755
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 937710 | FALSE | 2292.7758 | 1372.1379 | 0.85279 | 8 | 9.54e-05 | 1748 | 1144.507 | 756 | 0.10733 | 0.85862 | 723 |  | 3387
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 9472 | FALSE | 11800.3384 | 4934.5741 | 3.0669 | 90 | 8.66e-05 | 2018 | 1503.1801 | 596 | 0.10731 | 9.6577 | 724 | 0.04 | 2109
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 51740 | FALSE | 34181.0044 | 25031.397 | 15.5571 | 129 | 6.5e-05 | 2610 | 1615.1565 | 556 | 0.107 | 13.8028 | 725 | 0.06 | 1828
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 36666 | FALSE | 29026.438 | 27295.7526 | 16.9644 | 207 | 7.01e-05 | 2471 | 1591.1088 | 563 | 0.10683 | 22.1131 | 726 | 0.11 | 1436
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 1704 | FALSE | 4825.0456 | 4825.0456 | 2.9988 | 9 | 0.00018499 | 473 | 1060.4778 | 792 | 0.1065 | 0.95854 | 727 | 1.47 | 671
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 75382 | FALSE | 37601.9152 | 37336.0999 | 23.2045 | 198 | 0.00010957 | 1420 | 1232.3374 | 713 | 0.10636 | 21.0588 | 728 | 11.14 | 387
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 220154 | TRUE | 4466.0624 | 427.7941 | 0.26588 | 30 | 0.00014785 | 765 | 533.1924 | 1168 | 0.10579 | 3.1738 | 729 |  | 3155
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | CB | FALSE | 58448.7228 | 58073.6402 | 36.093 | 382 | 0.00010807 | 1450 | 1111.2712 | 769 | 0.10567 | 40.3677 | 730 | 0.26 | 1065
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 4410 | FALSE | 36702.381 | 36702.381 | 22.8107 | 232 | 6.2e-05 | 2720 | 1654.2525 | 541 | 0.10548 | 24.471 | 731 | 0.16 | 1272
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 630 | FALSE | 31341.2103 | 30113.0467 | 18.7154 | 93 | 5.69e-05 | 2863 | 1625.0866 | 552 | 0.10515 | 9.7794 | 732 | 0.15 | 1293
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 966 | FALSE | 3670.4356 | 1555.849 | 0.96697 | 34 | 0.00012939 | 1020 | 514.9608 | 1186 | 0.10505 | 3.5716 | 733 | 0.33 | 984
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 43008 | FALSE | 20752.8612 | 20697.7732 | 12.8637 | 145 | 0.00024315 | 238 | 866.3217 | 903 | 0.10501 | 15.2269 | 734 |  | 3002
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | XR070 | FALSE | 13972.8614 | 10519.5514 | 6.5379 | 90 | 8.01e-05 | 2203 | 1459.1172 | 612 | 0.10473 | 9.4261 | 735 | 0.15 | 1280
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 2112 | FALSE | 31201.9016 | 31201.9016 | 19.3921 | 222 | 0.00012957 | 1016 | 755.541 | 969 | 0.1046 | 23.2211 | 736 | 9 | 416
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 2216 | FALSE | 93046.0132 | 91192.0768 | 56.6762 | 663 | 0.00017534 | 526 | 744.5838 | 980 | 0.10438 | 69.2068 | 737 | 0.89 | 752
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | CB | TRUE | 64.9169 | 64.9169 | 0.040346 | 2 | 8.26e-05 | 2140 | 1260.6413 | 694 | 0.10413 | 0.20825 | 738 | 0.04 | 2172
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 65516 | FALSE | 18264.4613 | 12394.5836 | 7.7033 | 137 | 9.03e-05 | 1904 | 1198.218 | 730 | 0.104 | 14.2484 | 739 | 1.33 | 685
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 65908 | FALSE | 26966.3027 | 22380.0869 | 13.9093 | 205 | 0.00010013 | 1641 | 1026.2121 | 810 | 0.10393 | 21.3052 | 740 | 0.11 | 1441
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 12606 | FALSE | 36144.366 | 36144.366 | 22.4639 | 216 | 6.31e-05 | 2677 | 1680.4042 | 528 | 0.10392 | 22.4476 | 741 | 3.18 | 556
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 1652 | FALSE | 39344.5137 | 33895.2642 | 21.066 | 170 | 8.67e-05 | 2017 | 1367.2683 | 654 | 0.10352 | 17.5982 | 742 | 0.06 | 1779
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 19572 | TRUE | 4463.6596 | 595.3794 | 0.37003 | 12 | 8.89e-05 | 1956 | 995.992 | 836 | 0.10348 | 1.2418 | 743 | 0.4 | 947
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 13442 | FALSE | 49960.437 | 40749.3903 | 25.3259 | 272 | 6.9e-05 | 2508 | 1672.073 | 535 | 0.10338 | 28.1191 | 744 | 0.16 | 1269
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 284874 | FALSE | 7928.0423 | 3450.771 | 2.1447 | 56 | 0.00016281 | 613 | 825.2112 | 923 | 0.10322 | 5.7804 | 745 |  | 2708
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 9792 | FALSE | 44037.0343 | 1255.3676 | 0.78022 | 329 | 0.00010469 | 1536 | 1266.1791 | 692 | 0.10322 | 33.9591 | 746 | 1.85 | 639
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 62157 | TRUE | 72.1015 | 72.1015 | 0.044811 | 3 | 0.00013141 | 991 | 794.5095 | 944 | 0.10257 | 0.30771 | 747 | 0.04 | 2185
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 91464 | FALSE | 11314.1038 | 11314.1038 | 7.0318 | 81 | 0.00016471 | 590 | 737.1972 | 986 | 0.10229 | 8.2855 | 748 | 0.15 | 1286
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 2212 | FALSE | 54144.6309 | 25107.5196 | 15.6044 | 136 | 5.05e-05 | 3023 | 1941.9065 | 465 | 0.10222 | 13.9025 | 749 | 0.05 | 2020
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 36536 | FALSE | 31849.3061 | 27701.0415 | 17.2163 | 206 | 9e-05 | 1912 | 1240.3355 | 706 | 0.10219 | 21.0515 | 750 | 6.79 | 460
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 2584 | FALSE | 15108.9141 | 14615.3184 | 9.0835 | 83 | 7.57e-05 | 2313 | 1697.4776 | 524 | 0.1019 | 8.4581 | 751 | 0.06 | 1883
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 90356 | FALSE | 27619.1431 | 7749.0513 | 4.8161 | 148 | 4.57e-05 | 3146 | 2250.7696 | 393 | 0.10189 | 15.079 | 752 | 0.02 | 2540
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 345230 | FALSE | 4014.2831 | 1908.1944 | 1.186 | 22 | 0.00013065 | 997 | 832.9519 | 920 | 0.10181 | 2.2398 | 753 |  | 3505
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 4646 | TRUE | 480.2865 | 242.399 | 0.15065 | 8 | 0.00023752 | 255 | 1510.1147 | 591 | 0.10163 | 0.81301 | 754 | 0.12 | 1368
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | CB | TRUE | 993.1092 | 957.3027 | 0.59497 | 10 | 0.00022667 | 299 | 666.0518 | 1045 | 0.10116 | 1.0116 | 755 | 1.11 | 714
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 56048 | FALSE | 8009.5026 | 8009.5026 | 4.9779 | 27 | 0.00051047 | 29 | 201.585 | 1638 | 0.10102 | 2.7275 | 756 | 0.04 | 2118
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 4360 | FALSE | 14899.0043 | 12170.4858 | 7.564 | 76 | 4.83e-05 | 3087 | 2072.1488 | 436 | 0.10101 | 7.6765 | 757 | 0.1 | 1496
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 1202 | FALSE | 73649.8789 | 73649.8789 | 45.7737 | 459 | 9.38e-05 | 1798 | 1469.356 | 608 | 0.10087 | 46.3007 | 758 | 0.24 | 1107
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 38864 | FALSE | 12167.5887 | 2907.107 | 1.8068 | 94 | 9.14e-05 | 1865 | 1176.5294 | 743 | 0.10076 | 9.4715 | 759 | 0.03 | 2406
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 204 | FALSE | 31553.8482 | 31553.8482 | 19.6108 | 107 | 0.00017266 | 545 | 673.9659 | 1039 | 0.10067 | 10.7713 | 760 | 11.03 | 390
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 10019 | FALSE | 3187.4941 | 3187.4941 | 1.981 | 11 | 5.95e-05 | 2788 | 1607.8644 | 559 | 0.10052 | 1.1057 | 761 | 0.01 | 2577
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 42348 | FALSE | 5997.998 | 2160.8096 | 1.343 | 53 | 6.9e-05 | 2511 | 1015.3292 | 819 | 0.10037 | 5.3194 | 762 | 0.49 | 895
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 934355 | TRUE | 1942.6666 | 915.6706 | 0.56909 | 12 | 8.35e-05 | 2118 | 1431.4244 | 623 | 0.10029 | 1.2035 | 763 |  | 3546
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 48484 | FALSE | 67054.8672 | 67054.8672 | 41.6749 | 450 | 0.00013313 | 956 | 878.6779 | 893 | 0.09998 | 44.991 | 764 | 0.43 | 927
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 7559 | FALSE | 7193.5229 | 7193.5229 | 4.4708 | 52 | 6.85e-05 | 2522 | 1663.4994 | 538 | 0.099807 | 5.1899 | 765 | 0.1 | 1474
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 718 | FALSE | 47250.4226 | 43463.4041 | 27.0127 | 247 | 6.31e-05 | 2675 | 1440.3304 | 618 | 0.099744 | 24.6369 | 766 | 0.18 | 1211
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 63500 | TRUE | 5562.1132 | 327.1501 | 0.20333 | 46 | 0.00011792 | 1230 | 448.3626 | 1251 | 0.099652 | 4.584 | 767 | 1.81 | 642
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 1608 | FALSE | 53827.5719 | 53827.5719 | 33.4541 | 252 | 0.00019009 | 441 | 523.0258 | 1180 | 0.099644 | 25.1102 | 768 | 0.06 | 1838
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 248490 | FALSE | 43282.2287 | 17726.6224 | 11.0172 | 228 | 9.84e-05 | 1682 | 1137.7994 | 759 | 0.099611 | 22.7114 | 769 |  | 2654
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 443164 | FALSE | 15151.4475 | 4499.5872 | 2.7965 | 111 | 0.00012907 | 1027 | 720.9883 | 997 | 0.099321 | 11.0246 | 770 |  | 2651
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 92622 | FALSE | 50349.3756 | 50311.0535 | 31.2685 | 257 | 0.00011545 | 1291 | 1017.6191 | 817 | 0.098498 | 25.314 | 771 | 0.07 | 1774
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 154362 | FALSE | 11970.1824 | 3480.2712 | 2.163 | 90 | 0.00011044 | 1403 | 797.5542 | 943 | 0.098415 | 8.8574 | 772 |  | 2686
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | CB | FALSE | 3412.1639 | 2836.6716 | 1.763 | 16 | 0.00010435 | 1543 | 961.0572 | 853 | 0.098349 | 1.5736 | 773 | 0.87 | 758
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 93870 | FALSE | 54990.4582 | 29826.9597 | 18.5376 | 342 | 6.69e-05 | 2559 | 1508.5624 | 593 | 0.098287 | 33.6143 | 774 | 0.09 | 1545
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | CB | TRUE | 859.9008 | 859.9008 | 0.53443 | 5 | 0.00010841 | 1440 | 866.0652 | 904 | 0.098274 | 0.49137 | 775 | 0.05 | 1958
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | A10 | FALSE | 49945.6996 | 49945.6996 | 31.0415 | 264 | 7.36e-05 | 2377 | 1325.7939 | 671 | 0.098002 | 25.8725 | 776 | 7.4 | 446
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 2706 | FALSE | 23999.9081 | 9304.8867 | 5.783 | 190 | 0.0001407 | 858 | 837.755 | 918 | 0.09785 | 18.5915 | 777 | 0.94 | 743
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 934 | FALSE | 49660.3767 | 49660.3767 | 30.8641 | 279 | 9.38e-05 | 1799 | 1233.6573 | 711 | 0.097599 | 27.2301 | 778 | 35.78 | 211
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 13498 | FALSE | 1603.6406 | 1585.9579 | 0.98568 | 13 | 0.00013812 | 892 | 567.2293 | 1131 | 0.097071 | 1.2619 | 779 | 0.06 | 1831
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 90090 | FALSE | 48332.111 | 48332.111 | 30.0386 | 168 | 9.24e-05 | 1833 | 1129.7718 | 764 | 0.09692 | 16.2826 | 780 | 0.05 | 2011
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 83158 | FALSE | 31398.3783 | 28429.994 | 17.6694 | 132 | 6.31e-05 | 2679 | 1552.5213 | 577 | 0.09689 | 12.7894 | 781 | 0.06 | 1781
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 2500 | FALSE | 48136.3959 | 48136.3959 | 29.917 | 143 | 8.52e-05 | 2049 | 1216.4356 | 720 | 0.096773 | 13.8385 | 782 | 0.21 | 1155
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 603392 | FALSE | 5227.4341 | 4685.9835 | 2.9124 | 17 | 5.24e-05 | 2983 | 1917.7994 | 469 | 0.096621 | 1.6426 | 783 |  | 3382
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13312 | FALSE | 28501.0245 | 21155.7388 | 13.1484 | 190 | 0.00021994 | 321 | 408.8559 | 1287 | 0.096554 | 18.3453 | 784 | 0.12 | 1376
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 1958 | FALSE | 54465.3426 | 54465.3426 | 33.8504 | 353 | 0.00011848 | 1218 | 944.1299 | 865 | 0.096142 | 33.9382 | 785 | 0.29 | 1022
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | CB | FALSE | 20899.9329 | 19267.3702 | 11.9747 | 95 | 0.00020717 | 375 | 574.8898 | 1127 | 0.095782 | 9.0993 | 786 | 5.57 | 485
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 35466 | FALSE | 11836.6618 | 11836.6618 | 7.3565 | 82 | 0.00016771 | 578 | 531.3358 | 1171 | 0.095562 | 7.8361 | 787 | 0.06 | 1799
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 9811 | FALSE | 14351.9184 | 5776.4657 | 3.5901 | 92 | 8.29e-05 | 2133 | 845.358 | 914 | 0.095333 | 8.7707 | 788 | 0.03 | 2316
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | CB | TRUE | 7060.6838 | 875.6492 | 0.54422 | 45 | 5.64e-05 | 2879 | 1585.2096 | 566 | 0.095165 | 4.2824 | 789 | 0.89 | 750
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | CB | TRUE | 3890.2841 | 517.8814 | 0.32187 | 37 | 0.00015375 | 712 | 238.7834 | 1569 | 0.095153 | 3.5207 | 790 | 0.1 | 1501
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | CB | FALSE | 9278.0237 | 5281.0095 | 3.2822 | 53 | 6.98e-05 | 2480 | 949.0975 | 862 | 0.095135 | 5.0422 | 791 | 0.02 | 2553
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 632 | FALSE | 29843.7661 | 29492.7895 | 18.3299 | 193 | 0.00011902 | 1207 | 950.7759 | 861 | 0.094959 | 18.327 | 792 | 90.53 | 32
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 1064 | FALSE | 31650.7422 | 31650.7422 | 19.6711 | 179 | 9.3e-05 | 1824 | 1110.3932 | 771 | 0.094905 | 16.9879 | 793 | 64.19 | 79
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 6008 | FALSE | 37504.3181 | 37504.3181 | 23.3091 | 236 | 8.34e-05 | 2122 | 1032.7499 | 806 | 0.094797 | 22.3721 | 794 | 0.31 | 1010
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | CB | FALSE | 8828.3789 | 2269.8172 | 1.4107 | 51 | 8.65e-05 | 2023 | 1197.2249 | 732 | 0.094773 | 4.8334 | 795 | 0.08 | 1602
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10100 | FALSE | 18902.6869 | 16723.3035 | 10.3936 | 142 | 0.0001056 | 1504 | 1406.8011 | 635 | 0.094733 | 13.4521 | 796 | 0.13 | 1337
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | XR524 | FALSE | 17990.142 | 17523.6666 | 10.891 | 59 | 7.36e-05 | 2373 | 1425.9142 | 629 | 0.09443 | 5.5714 | 797 | 0.13 | 1349
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | CB | FALSE | 14024.7064 | 1067.201 | 0.66327 | 93 | 0.00014666 | 778 | 560.4187 | 1134 | 0.094346 | 8.7742 | 798 | 0.02 | 2531
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 854149 | FALSE | 1703.8848 | 1563.4443 | 0.97169 | 12 | 3.92e-05 | 3281 | 2116.0059 | 424 | 0.094333 | 1.132 | 799 |  | 3095
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | CB | FALSE | 14181.9325 | 13470.2412 | 8.3718 | 64 | 8.69e-05 | 2014 | 1158.1157 | 750 | 0.094159 | 6.0262 | 800 | 0.04 | 2092
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 373667 | FALSE | 6861.5817 | 5269.4021 | 3.275 | 45 | 0.00010834 | 1444 | 757.3214 | 967 | 0.09414 | 4.2363 | 801 |  | 2927
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 396 | FALSE | 25908.1895 | 25908.1895 | 16.102 | 182 | 0.00013862 | 887 | 571.5533 | 1129 | 0.093951 | 17.099 | 802 | 46.49 | 141
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | MR182 | FALSE | 11548.6884 | 10768.7759 | 6.6928 | 56 | 6.14e-05 | 2738 | 1819.6137 | 502 | 0.093921 | 5.2596 | 803 | 0.09 | 1515
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 4786 | FALSE | 28973.985 | 28973.985 | 18.0074 | 173 | 9.67e-05 | 1720 | 894.0898 | 886 | 0.09378 | 16.224 | 804 | 0.23 | 1115
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 77578 | FALSE | 51848.8987 | 34427.9014 | 21.3971 | 389 | 0.00014957 | 742 | 862.3434 | 907 | 0.09328 | 36.2858 | 805 | 0.14 | 1325
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 4744 | FALSE | 32972.1771 | 27938.0536 | 17.3636 | 161 | 0.00026417 | 184 | 386.3695 | 1311 | 0.093231 | 15.0101 | 806 | 0.03 | 2396
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 2704 | FALSE | 9132.5937 | 2300.3426 | 1.4297 | 76 | 0.00016088 | 633 | 611.8282 | 1093 | 0.093023 | 7.0698 | 807 | 0.54 | 874
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 826 | FALSE | 12455.7725 | 12455.7725 | 7.7413 | 89 | 0.00010691 | 1478 | 923.3771 | 872 | 0.092902 | 8.2683 | 808 | 15.71 | 347
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 233646 | FALSE | 18091.6284 | 15102.5612 | 9.3863 | 127 | 8.22e-05 | 2147 | 1174.21 | 744 | 0.092653 | 11.7669 | 809 |  | 2976
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 75884 | FALSE | 18035.3275 | 17165.4943 | 10.6684 | 94 | 0.00017444 | 533 | 718.5697 | 1003 | 0.09258 | 8.7025 | 810 | 3.43 | 548
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 1402 | FALSE | 71104.0431 | 71104.0431 | 44.1915 | 541 | 9.14e-05 | 1862 | 1211.8423 | 726 | 0.092281 | 49.924 | 811 | 35.4 | 214
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | CB | FALSE | 9345.3494 | 2462.2686 | 1.5303 | 66 | 0.00012054 | 1177 | 1190.2745 | 738 | 0.092174 | 6.0835 | 812 | 0.04 | 2090
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 660 | FALSE | 31347.0514 | 16353.7146 | 10.1639 | 233 | 0.00011883 | 1211 | 1011.3875 | 826 | 0.092166 | 21.4747 | 813 | 0.63 | 835
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 46960 | FALSE | 3112.6164 | 1465.0556 | 0.91054 | 14 | 5.43e-05 | 2938 | 2071.3937 | 437 | 0.092145 | 1.29 | 814 | 0.02 | 2539
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 666 | FALSE | 21923.7063 | 19462.335 | 12.0959 | 90 | 5.9e-05 | 2805 | 1514.7635 | 588 | 0.092048 | 8.2843 | 815 | 0.87 | 754
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 55612 | FALSE | 35781.5314 | 35781.5314 | 22.2384 | 93 | 0.00015401 | 707 | 611.9681 | 1092 | 0.090895 | 8.4532 | 816 | 0.12 | 1370
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 409622 | FALSE | 20757.639 | 20534.7896 | 12.7625 | 156 | 0.00034981 | 90 | 622.0881 | 1080 | 0.090831 | 14.1696 | 817 |  | 2825
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 13424 | FALSE | 5801.6622 | 2404.2277 | 1.4942 | 43 | 0.00013059 | 1000 | 649.8195 | 1066 | 0.090714 | 3.9007 | 818 | 0.03 | 2394
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 384360 | FALSE | 10034.7798 | 7892.4211 | 4.9052 | 70 | 9.23e-05 | 1835 | 1163.0519 | 748 | 0.090426 | 6.3298 | 819 |  | 2667
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 1598 | FALSE | 53928.0023 | 53928.0023 | 33.5165 | 251 | 9.75e-05 | 1700 | 806.3409 | 933 | 0.09042 | 22.6955 | 820 | 22.35 | 294
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 86816 | FALSE | 7103.5026 | 7103.5026 | 4.4149 | 51 | 0.00023289 | 272 | 393.4562 | 1304 | 0.090319 | 4.6062 | 821 | 6.82 | 458
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | M18 | FALSE | 28757.9291 | 24562.1098 | 15.2655 | 81 | 5.49e-05 | 2918 | 1831.3141 | 496 | 0.090027 | 7.2922 | 822 | 0.57 | 861
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 948 | FALSE | 12598.6878 | 10159.6075 | 6.3142 | 73 | 6.67e-05 | 2564 | 1385.8323 | 644 | 0.089784 | 6.5542 | 823 | 0.06 | 1788
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 212096 | FALSE | 6500.9175 | 4124.0159 | 2.5631 | 42 | 6.32e-05 | 2670 | 1654.3016 | 540 | 0.089733 | 3.7688 | 824 |  | 3265
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 297862 | TRUE | 519.2262 | 503.2242 | 0.31276 | 4 | 7.92e-05 | 2228 | 3345.084 | 219 | 0.089567 | 0.35827 | 825 |  | 3575
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 858898 | FALSE | 31911.4059 | 31551.7735 | 19.6096 | 152 | 4.99e-05 | 3040 | 1510.095 | 592 | 0.089508 | 13.6052 | 826 |  | 3043
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 373772 | TRUE | 28.6691 | 28.6691 | 0.017818 | 2 | 0.00012505 | 1097 | 655.2599 | 1058 | 0.089417 | 0.17883 | 827 | 1.87 | 637
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 570 | FALSE | 34272.8021 | 28557.0384 | 17.7483 | 199 | 0.00010582 | 1500 | 921.351 | 874 | 0.089292 | 17.7691 | 828 | 0.22 | 1129
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 5100 | FALSE | 34326.3844 | 34326.3844 | 21.334 | 204 | 8.91e-05 | 1942 | 1331.1763 | 667 | 0.089218 | 18.2004 | 829 | 0.33 | 989
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 88962 | FALSE | 6442.5415 | 3996.9259 | 2.4841 | 45 | 4.86e-05 | 3070 | 1156.9132 | 752 | 0.089174 | 4.0128 | 830 | 0.04 | 2070
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 56026 | FALSE | 24339.1905 | 24339.1905 | 15.1269 | 158 | 0.00012905 | 1028 | 717.5714 | 1005 | 0.089061 | 14.0716 | 831 | 0.07 | 1750
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 528 | FALSE | 19817.3234 | 6048.4547 | 3.7591 | 110 | 0.00013971 | 873 | 614.5051 | 1089 | 0.08906 | 9.7966 | 832 | 0.03 | 2395
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 736 | FALSE | 55772.0682 | 55772.0682 | 34.6626 | 350 | 0.00013305 | 957 | 690.2141 | 1030 | 0.088841 | 31.0945 | 833 | 98.57 | 21
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | CB | FALSE | 21689.1163 | 18499.2196 | 11.4973 | 14 | 0.00021618 | 336 | 754.1992 | 970 | 0.088539 | 1.2395 | 834 | 0.04 | 2124
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 10580 | FALSE | 18949.2019 | 12416.9837 | 7.7172 | 129 | 0.00010187 | 1606 | 1422.4147 | 630 | 0.088489 | 11.415 | 835 | 0.05 | 1984
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 47872 | FALSE | 6709.5897 | 6709.5897 | 4.17 | 52 | 0.00017337 | 538 | 451.2799 | 1248 | 0.088422 | 4.5979 | 836 | 1.21 | 701
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | A14 | FALSE | 40416.4237 | 40416.4237 | 25.119 | 152 | 7.42e-05 | 2351 | 1301.8625 | 681 | 0.088418 | 13.4395 | 837 | 0.07 | 1686
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 75252 | FALSE | 98047.1457 | 93174.0996 | 57.9081 | 401 | 7.77e-05 | 2271 | 1110.9654 | 770 | 0.088153 | 35.3494 | 838 | 0.18 | 1204
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 1700 | FALSE | 35014.8434 | 34930.2373 | 21.7093 | 255 | 0.00014818 | 762 | 706.0979 | 1016 | 0.087918 | 22.4191 | 839 | 0.15 | 1281
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 339792 | FALSE | 5788.3897 | 4221.2236 | 2.6235 | 43 | 0.00011358 | 1331 | 632.6218 | 1077 | 0.087729 | 3.7723 | 840 |  | 3181
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 984552 | FALSE | 9221.3481 | 7304.6852 | 4.5399 | 53 | 7.87e-05 | 2243 | 1388.9327 | 642 | 0.087511 | 4.6381 | 841 |  | 3254
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 80726 | FALSE | 29692.476 | 12661.4918 | 7.8692 | 217 | 0.00011841 | 1219 | 698.1741 | 1024 | 0.087369 | 18.9591 | 842 | 0.05 | 2014
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 348318 | TRUE | 597.0392 | 597.0392 | 0.37106 | 6 | 4.52e-05 | 3156 | 2033.0031 | 451 | 0.087346 | 0.52408 | 843 |  | 2972
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 76694 | FALSE | 7317.351 | 7317.351 | 4.5478 | 37 | 7.26e-05 | 2401 | 1607.6376 | 560 | 0.087295 | 3.2299 | 844 | 0.06 | 1907
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 9190 | FALSE | 14438.9195 | 14438.9195 | 8.9738 | 104 | 0.00015927 | 649 | 560.2186 | 1135 | 0.087115 | 9.06 | 845 | 0.12 | 1405
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 75970 | FALSE | 11378.8384 | 11378.8384 | 7.072 | 33 | 0.0002301 | 284 | 549.4916 | 1145 | 0.08694 | 2.869 | 846 | 0.07 | 1700
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | CB | FALSE | 4772.9739 | 3724.6766 | 2.3149 | 47 | 0.00012677 | 1067 | 1037.4258 | 802 | 0.086583 | 4.0694 | 847 | 3.02 | 568
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 1590 | FALSE | 10388.8945 | 10388.8945 | 6.4567 | 63 | 0.00013775 | 898 | 828.3749 | 922 | 0.086534 | 5.4516 | 848 | 0.58 | 859
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | CB | FALSE | 45670.4217 | 45670.4217 | 28.3844 | 294 | 9.53e-05 | 1751 | 1012.9872 | 821 | 0.086354 | 25.3881 | 849 | 0.47 | 909
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 7380 | FALSE | 45386.7416 | 20845.5533 | 12.9556 | 240 | 4.45e-05 | 3175 | 2480.8683 | 345 | 0.086218 | 20.6923 | 850 | 0.07 | 1707
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 48950 | FALSE | 20081.7793 | 20081.7793 | 12.4809 | 145 | 0.00013937 | 880 | 612.4235 | 1091 | 0.085979 | 12.467 | 851 | 0.08 | 1608
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 161818 | TRUE | 7658.7384 | 212.3638 | 0.13198 | 59 | 5.71e-05 | 2859 | 1511.2201 | 590 | 0.08588 | 5.0669 | 852 | 0.02 | 2419
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 320270 | FALSE | 27707.7793 | 13648.6048 | 8.4827 | 137 | 5.44e-05 | 2934 | 1519.0093 | 586 | 0.08574 | 11.7464 | 853 | 0.03 | 2384
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | XR176 | FALSE | 44222.2898 | 36252.5852 | 22.5311 | 309 | 8.45e-05 | 2077 | 1005.2282 | 831 | 0.085689 | 26.478 | 854 | 0.3 | 1018
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | CB | FALSE | 10972.0561 | 9142.0744 | 5.6818 | 69 | 0.00014429 | 809 | 861.7339 | 908 | 0.08567 | 5.9113 | 855 | 0.08 | 1609
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 167726 | FALSE | 6114.3744 | 6114.3744 | 3.8001 | 50 | 7.79e-05 | 2262 | 1006.5075 | 830 | 0.08544 | 4.272 | 856 |  | 2859
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 9765 | TRUE | 1507.3257 | 425.4979 | 0.26445 | 16 | 4.04e-05 | 3257 | 1304.4493 | 680 | 0.085394 | 1.3663 | 857 | 1.11 | 715
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 87304 | FALSE | 23764.1584 | 4634.8119 | 2.8806 | 100 | 0.00010497 | 1530 | 1066.2761 | 788 | 0.085339 | 8.5339 | 858 | 0.01 | 2567
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | CB | FALSE | 79932.4071 | 51306.3985 | 31.8871 | 469 | 0.00011158 | 1379 | 802.5661 | 939 | 0.085283 | 39.9976 | 859 | 0.15 | 1300
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 537096 | TRUE | 844.1463 | 775.9765 | 0.48227 | 6 | 0.00013769 | 900 | 635.9861 | 1072 | 0.085228 | 0.51137 | 860 |  | 3492
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | CB | FALSE | 3161.2302 | 1492.4904 | 0.92759 | 19 | 0.00014572 | 793 | 421.9203 | 1271 | 0.085217 | 1.6191 | 861 | 0.04 | 2178
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 2004 | FALSE | 86935.2431 | 40225.06 | 25 | 174 | 5.05e-05 | 3024 | 1960.2216 | 462 | 0.085175 | 14.8204 | 862 | 0.02 | 2549
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | V10 | FALSE | 7811.0705 | 3504.8307 | 2.1783 | 54 | 0.00010776 | 1457 | 473.6801 | 1219 | 0.085103 | 4.5956 | 863 |  | 2796
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | R82 | FALSE | 111857.9563 | 61789.4025 | 38.4024 | 563 | 6.82e-05 | 2530 | 1317.1207 | 675 | 0.084913 | 47.806 | 864 | 0.03 | 2235
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | CB | FALSE | 27411.8293 | 27411.8293 | 17.0366 | 139 | 0.00012426 | 1113 | 619.8955 | 1081 | 0.084888 | 11.7994 | 865 | 0.48 | 900
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | L3141 | FALSE | 22528.5485 | 22255.8256 | 13.8321 | 97 | 7.56e-05 | 2322 | 1221.0879 | 717 | 0.084539 | 8.2002 | 866 | 0.09 | 1535
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | CB | FALSE | 35287.6179 | 28413.1031 | 17.6589 | 111 | 0.00022836 | 290 | 382.0524 | 1317 | 0.084457 | 9.3748 | 867 | 0.06 | 1910
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 104 | FALSE | 34991.65 | 34991.65 | 21.7475 | 235 | 0.00014639 | 782 | 473.3298 | 1220 | 0.084332 | 19.818 | 868 | 67.59 | 72
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 2748 | FALSE | 31538.4076 | 20831.4865 | 12.9469 | 245 | 0.00018393 | 480 | 692.2861 | 1029 | 0.084145 | 20.6156 | 869 | 0.1 | 1477
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 739448 | FALSE | 3763.2993 | 2860.1443 | 1.7776 | 12 | 4.57e-05 | 3149 | 1064.5547 | 790 | 0.084104 | 1.0093 | 870 |  | 3393
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 51658 | FALSE | 14039.3789 | 13140.1209 | 8.1666 | 108 | 0.00011684 | 1253 | 818.1348 | 925 | 0.084002 | 9.0722 | 871 | 1.43 | 677
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 98568 | TRUE | 2444.4926 | 168.1421 | 0.1045 | 7 | 7.02e-05 | 2465 | 834.7615 | 919 | 0.083995 | 0.58797 | 872 |  | 3457
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 637242 | FALSE | 35417.2163 | 27085.716 | 16.8339 | 193 | 7.19e-05 | 2424 | 1184.0184 | 740 | 0.083893 | 16.1913 | 873 |  | 2879
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 507389 | TRUE | 305.6652 | 212.3341 | 0.13197 | 4 | 8.94e-05 | 1934 | 719.0918 | 1002 | 0.083842 | 0.33537 | 874 |  | 3399
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 2228 | FALSE | 16654.619 | 5410.2105 | 3.3625 | 80 | 5.64e-05 | 2878 | 1582.2639 | 568 | 0.082955 | 6.6364 | 875 | 0.03 | 2232
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 91948 | FALSE | 11942.5868 | 11942.5868 | 7.4224 | 69 | 0.00010599 | 1494 | 1019.808 | 815 | 0.082927 | 5.7219 | 876 | 0.99 | 733
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | XR366 | FALSE | 17766.1133 | 13567.8022 | 8.4324 | 129 | 7.13e-05 | 2437 | 1012.8648 | 822 | 0.082848 | 10.6874 | 877 | 0.21 | 1134
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 685160 | TRUE | 2780.4715 | 943.7591 | 0.58655 | 17 | 5.04e-05 | 3028 | 1467.3789 | 610 | 0.082766 | 1.407 | 878 |  | 3392
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 4994 | FALSE | 6920.6464 | 2185.8295 | 1.3585 | 45 | 0.00012652 | 1071 | 520.9041 | 1182 | 0.082765 | 3.7244 | 879 | 0.64 | 830
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 737236 | FALSE | 14223.4405 | 14101.6239 | 8.7642 | 88 | 0.00012645 | 1074 | 720.3446 | 999 | 0.082425 | 7.2534 | 880 |  | 2868
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 79140 | FALSE | 19909.2046 | 15742.3512 | 9.7839 | 154 | 9.38e-05 | 1797 | 973.1017 | 848 | 0.082367 | 12.6845 | 881 | 7.99 | 438
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 454432 | FALSE | 23226.2401 | 23226.2401 | 14.4352 | 112 | 5.57e-05 | 2898 | 1234.8209 | 710 | 0.08233 | 9.221 | 882 |  | 2714
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 51790 | FALSE | 13931.0144 | 12725.5168 | 7.909 | 106 | 0.00015838 | 659 | 660.4485 | 1052 | 0.082229 | 8.7163 | 883 | 0.33 | 990
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 144510 | FALSE | 8266.8346 | 5010.1846 | 3.1138 | 41 | 8.37e-05 | 2104 | 950.8265 | 860 | 0.08218 | 3.3694 | 884 |  | 2896
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 5202 | FALSE | 27474.7329 | 26267.8985 | 16.3256 | 162 | 8.85e-05 | 1973 | 910.6874 | 881 | 0.082155 | 13.3091 | 885 | 0.12 | 1403
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 11236 | FALSE | 31777.9091 | 31777.9091 | 19.7501 | 143 | 0.00011636 | 1262 | 616.8333 | 1086 | 0.081838 | 11.7029 | 886 | 0.05 | 2012
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 3485 | FALSE | 2803.9876 | 2803.9876 | 1.7427 | 23 | 0.00011552 | 1286 | 723.112 | 996 | 0.081749 | 1.8802 | 887 |  | 2910
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 632 | FALSE | 23697.8024 | 23697.8024 | 14.7283 | 81 | 6.8e-05 | 2537 | 1288.5976 | 686 | 0.081559 | 6.6063 | 888 | 0.05 | 2027
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4609 | FALSE | 7321.9227 | 7321.9227 | 4.5506 | 41 | 3.73e-05 | 3310 | 2145.8949 | 414 | 0.081381 | 3.3366 | 889 | 0.06 | 1911
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7004 | FALSE | 31981.9475 | 12745.3246 | 7.9213 | 128 | 5.84e-05 | 2822 | 1357.6846 | 659 | 0.081062 | 10.3759 | 890 | 0.03 | 2338
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | XR398 | FALSE | 63835.5147 | 60665.5292 | 37.7039 | 341 | 8.37e-05 | 2103 | 945.2451 | 864 | 0.080766 | 27.5412 | 891 | 0.67 | 814
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 1821 | FALSE | 6061.921 | 5767.6056 | 3.5846 | 33 | 6.91e-05 | 2504 | 1429.8724 | 624 | 0.080483 | 2.6559 | 892 | 0.08 | 1594
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 95756 | FALSE | 29109.9093 | 11950.3804 | 7.4272 | 200 | 7.02e-05 | 2461 | 1033.0935 | 805 | 0.080379 | 16.0759 | 893 | 0.03 | 2343
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | M82 | FALSE | 23986.1463 | 17447.2632 | 10.8435 | 149 | 4.47e-05 | 3168 | 1573.1869 | 570 | 0.080327 | 11.9687 | 894 | 0.04 | 2147
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 2056 | FALSE | 10443.0868 | 8069.9513 | 5.0155 | 70 | 0.00011546 | 1289 | 677.9317 | 1037 | 0.080308 | 5.6215 | 895 | 3.29 | 551
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 808 | FALSE | 8110.4608 | 4081.7731 | 2.5368 | 39 | 8.08e-05 | 2186 | 1061.2531 | 791 | 0.0803 | 3.1317 | 896 | 0.09 | 1528
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 3290 | FALSE | 21820.8937 | 21820.8937 | 13.5618 | 135 | 0.00032761 | 105 | 278.5419 | 1474 | 0.080281 | 10.8379 | 897 | 0.08 | 1641
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 372132 | TRUE | 2259.794 | 673.2222 | 0.41841 | 13 | 0.00010261 | 1583 | 1099.8675 | 775 | 0.08025 | 1.0433 | 898 |  | 3103
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 807988 | FALSE | 6722.2779 | 6706.2477 | 4.168 | 15 | 0.00010987 | 1413 | 855.2361 | 912 | 0.080023 | 1.2003 | 899 |  | 3415
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 643162 | FALSE | 9798.1377 | 5532.3244 | 3.4384 | 41 | 6.71e-05 | 2555 | 1192.2958 | 736 | 0.079941 | 3.2776 | 900 |  | 3054
10896 | CMC 1102CB | 183111102 | CMC 1102 | CB | TRUE | 581.8342 | 581.8342 | 0.36161 | 5 | 0.00015983 | 644 | 548.9355 | 1146 | 0.079905 | 0.39953 | 901 | 0.03 | 2328
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 4300 | FALSE | 43675.508 | 43384.1036 | 26.9634 | 268 | 0.00011959 | 1194 | 736.9291 | 987 | 0.079811 | 21.3893 | 902 | 28.67 | 249
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 1703 | FALSE | 3959.9015 | 1455.5285 | 0.90462 | 7 | 2.6e-05 | 3487 | 3088.567 | 257 | 0.079525 | 0.55668 | 903 | 0.01 | 2618
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 935216 | FALSE | 33848.7529 | 33848.7529 | 21.0371 | 204 | 0.00011214 | 1365 | 509.4897 | 1191 | 0.079474 | 16.2127 | 904 |  | 3025
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 1510 | FALSE | 41028.1557 | 41028.1557 | 25.4992 | 243 | 8.89e-05 | 1952 | 939.2458 | 866 | 0.079411 | 19.297 | 905 | 0.18 | 1216
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 19632 | FALSE | 14659.9971 | 8997.9268 | 5.5922 | 110 | 0.00013387 | 944 | 1009.1241 | 828 | 0.07935 | 8.7285 | 906 | 23.44 | 286
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | A08 | FALSE | 39406.6597 | 16842.5186 | 10.4677 | 257 | 7.6e-05 | 2308 | 953.5418 | 857 | 0.079335 | 20.3891 | 907 | 0.05 | 2006
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | CB | FALSE | 35256.7174 | 21554.4713 | 13.3962 | 149 | 5.74e-05 | 2852 | 1255.3202 | 698 | 0.079316 | 11.8181 | 908 | 3.17 | 557
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | CB | FALSE | 5135.5453 | 5135.5453 | 3.1918 | 17 | 0.00032833 | 104 | 166.3867 | 1733 | 0.079299 | 1.3481 | 909 | 0.73 | 794
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | Q12 | FALSE | 25798.2458 | 18203.0478 | 11.3133 | 142 | 5.32e-05 | 2958 | 1483.0103 | 602 | 0.079257 | 11.2544 | 910 | 0.12 | 1401
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 188426 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00011833 | 1221 | 665.6862 | 1046 | 0.078773 | 0.078773 | 911 |  | 3613
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 4281 | FALSE | 21439.832 | 21439.832 | 13.3249 | 138 | 8.42e-05 | 2085 | 980.9559 | 844 | 0.078646 | 10.8532 | 912 | 0.09 | 1527
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 7863 | FALSE | 6797.0988 | 6797.0988 | 4.2244 | 42 | 6.12e-05 | 2744 | 1254.5183 | 699 | 0.078616 | 3.3019 | 913 | 0.06 | 1859
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 93384 | FALSE | 27406.0322 | 25967.2198 | 16.1387 | 101 | 6.36e-05 | 2660 | 1407.9794 | 632 | 0.078583 | 7.9369 | 914 | 0.06 | 1857
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 1314 | FALSE | 1489.219 | 1489.219 | 0.92556 | 13 | 0.00014408 | 813 | 554.638 | 1141 | 0.078235 | 1.0171 | 915 | 7.88 | 439
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 2248 | FALSE | 14727.9744 | 14727.9744 | 9.1535 | 28 | 6.58e-05 | 2594 | 1037.9427 | 801 | 0.077859 | 2.18 | 916 | 0.05 | 1922
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | Q10 | FALSE | 38031.0006 | 38031.0006 | 23.6364 | 289 | 6.46e-05 | 2621 | 1216.6013 | 719 | 0.077836 | 22.4946 | 917 | 7.07 | 452
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | CB | FALSE | 18838.7982 | 5515.7018 | 3.428 | 135 | 0.00010957 | 1419 | 752.8216 | 973 | 0.077778 | 10.5 | 918 | 0.02 | 2544
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | XR268 | FALSE | 12802.5937 | 12802.5937 | 7.9569 | 61 | 0.00011557 | 1284 | 557.5427 | 1138 | 0.077596 | 4.7333 | 919 | 0.46 | 913
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 1312 | FALSE | 15822.8795 | 15822.8795 | 9.834 | 120 | 0.00013526 | 925 | 772.6153 | 957 | 0.077577 | 9.3092 | 920 | 0.15 | 1291
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | V38 | FALSE | 27926.3564 | 19405.5321 | 12.0606 | 212 | 7.36e-05 | 2379 | 651.082 | 1062 | 0.077544 | 16.4392 | 921 | 0.17 | 1245
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 307342 | TRUE | 573.1034 | 354.0238 | 0.22003 | 6 | 0.00013565 | 923 | 341.2059 | 1386 | 0.077416 | 0.46449 | 922 |  | 3441
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 24550 | FALSE | 34688.2788 | 17797.4846 | 11.0612 | 203 | 9.39e-05 | 1795 | 616.7423 | 1087 | 0.077338 | 15.6996 | 923 | 0.07 | 1711
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 514 | FALSE | 8494.876 | 5391.2208 | 3.3507 | 71 | 0.00014873 | 755 | 482.2809 | 1214 | 0.077302 | 5.4884 | 924 | 0.09 | 1537
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 49746 | TRUE | 601.9007 | 601.9007 | 0.37408 | 3 | 0.00034014 | 97 | 221.8686 | 1601 | 0.077172 | 0.23152 | 925 | 0.04 | 2076
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 630 | FALSE | 6902.8394 | 2654.0652 | 1.6495 | 55 | 7.79e-05 | 2263 | 873.6447 | 897 | 0.077168 | 4.2442 | 926 | 0.03 | 2363
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 201311 | FALSE | 17668.9636 | 12645.7551 | 7.8594 | 108 | 6.43e-05 | 2634 | 1215.4291 | 722 | 0.077053 | 8.3218 | 927 |  | 3015
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 35706 | FALSE | 16269.027 | 16269.027 | 10.1113 | 97 | 0.00041981 | 62 | 185.2954 | 1670 | 0.076898 | 7.4591 | 928 | 4.82 | 505
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 2410 | FALSE | 12099.1952 | 5248.3008 | 3.2618 | 96 | 0.00011208 | 1366 | 705.3971 | 1019 | 0.076748 | 7.3678 | 929 | 0.05 | 1959
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 87402 | FALSE | 18273.7697 | 18273.7697 | 11.3572 | 42 | 9.19e-05 | 1846 | 973.3911 | 847 | 0.07664 | 3.2189 | 930 | 1.23 | 698
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 3760 | FALSE | 10446.6343 | 10415.8967 | 6.4735 | 6 | 4.62e-05 | 3131 | 4483.9501 | 110 | 0.076506 | 0.45904 | 931 | 0.03 | 2370
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | CB | FALSE | 5307.8327 | 5307.8327 | 3.2988 | 25 | 0.0001265 | 1072 | 430.0286 | 1260 | 0.076253 | 1.9063 | 932 | 12.67 | 370
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 4614 | FALSE | 20206.8972 | 20206.8972 | 12.5587 | 95 | 0.00011071 | 1396 | 701.2564 | 1022 | 0.075773 | 7.1985 | 933 |  | 3306
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 37536 | FALSE | 8687.6907 | 8687.6907 | 5.3994 | 60 | 4e-05 | 3267 | 1761.4133 | 511 | 0.075515 | 4.5309 | 934 | 0.07 | 1729
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 1437 | FALSE | 7854.9148 | 4577.3445 | 2.8448 | 39 | 5.93e-05 | 2795 | 1361.2842 | 657 | 0.075332 | 2.9379 | 935 | 0.03 | 2404
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 583202 | FALSE | 15783.8472 | 7874.8461 | 4.8942 | 106 | 0.00010066 | 1631 | 594.6514 | 1106 | 0.075101 | 7.9607 | 936 | 0.05 | 2004
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 538 | FALSE | 10176.8073 | 10176.8073 | 6.3249 | 48 | 6.41e-05 | 2642 | 1480.7363 | 603 | 0.074937 | 3.597 | 937 | 2.14 | 620
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 854266 | TRUE | 966.2653 | 321.4105 | 0.19976 | 6 | 9.57e-05 | 1736 | 1072.2651 | 785 | 0.074827 | 0.44896 | 938 |  | 3418
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7099 | FALSE | 12439.4387 | 12439.4387 | 7.7312 | 83 | 0.00011588 | 1273 | 664.3931 | 1047 | 0.074794 | 6.2079 | 939 | 0.28 | 1036
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 274 | FALSE | 29743.739 | 10398.2127 | 6.4625 | 173 | 0.00011599 | 1270 | 494.2707 | 1207 | 0.074787 | 12.9382 | 940 | 1.24 | 695
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 1606 | TRUE | 42761.0947 | 254.3531 | 0.15808 | 280 | 7.09e-05 | 2446 | 1248.3017 | 701 | 0.074511 | 20.863 | 941 | 0.02 | 2551
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | CB | FALSE | 3483.5782 | 3483.5782 | 2.1651 | 16 | 0.00013086 | 995 | 558.6934 | 1136 | 0.074456 | 1.1913 | 942 | 21.08 | 302
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | CB | FALSE | 21509.9694 | 15956.2359 | 9.9169 | 121 | 5.19e-05 | 2995 | 1288.0652 | 687 | 0.074106 | 8.9669 | 943 | 0.03 | 2320
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 999 | FALSE | 3715.0604 | 3715.0604 | 2.3089 | 22 | 0.00010639 | 1488 | 1017.494 | 818 | 0.074075 | 1.6297 | 944 | 0.09 | 1529
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 6751 | FALSE | 36483.9202 | 36483.9202 | 22.6749 | 139 | 0.00018185 | 499 | 410.6545 | 1284 | 0.073927 | 10.2759 | 945 | 39.14 | 190
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | CB | FALSE | 15601.4012 | 15601.4012 | 9.6963 | 97 | 0.00011323 | 1340 | 789.9349 | 952 | 0.073848 | 7.1632 | 946 | 0.18 | 1203
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 134232 | FALSE | 11553.3534 | 2618.9112 | 1.6277 | 89 | 0.0001535 | 717 | 426.3987 | 1264 | 0.0737 | 6.5593 | 947 |  | 3092
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | CB | TRUE | 2722.4304 | 952.8122 | 0.59218 | 22 | 0.00019759 | 405 | 236.9089 | 1576 | 0.073682 | 1.621 | 948 | 0.13 | 1352
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | Y24 | FALSE | 31605.3339 | 30845.6135 | 19.1707 | 91 | 6.88e-05 | 2514 | 1387.2959 | 643 | 0.073569 | 6.6947 | 949 | 0.26 | 1061
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | CB | TRUE | 6455.7985 | 567.3027 | 0.35258 | 55 | 0.00018028 | 511 | 272.2112 | 1489 | 0.073561 | 4.0458 | 950 | 0.64 | 831
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 792 | FALSE | 33585.8452 | 31119.1615 | 19.3407 | 180 | 9.91e-05 | 1667 | 711.86 | 1012 | 0.073389 | 13.2101 | 951 | 87.74 | 36
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | V40 | FALSE | 37151.701 | 23652.2282 | 14.7 | 194 | 7.96e-05 | 2220 | 1050.089 | 797 | 0.073389 | 14.2374 | 952 | 0.06 | 1795
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 47488 | FALSE | 33425.2179 | 30588.7641 | 19.011 | 207 | 0.00011402 | 1320 | 706.1851 | 1015 | 0.07338 | 15.1897 | 953 | 0.19 | 1176
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | Y44 | FALSE | 18687.8674 | 16745.9311 | 10.4077 | 45 | 6.01e-05 | 2770 | 1213.3424 | 724 | 0.073295 | 3.2983 | 954 | 0.1 | 1484
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | A70 | FALSE | 107377.7331 | 39764.0285 | 24.7135 | 659 | 6.96e-05 | 2486 | 1197.409 | 731 | 0.073157 | 48.2106 | 955 | 3.57 | 542
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | R322 | FALSE | 12336.4699 | 12336.4699 | 7.6672 | 44 | 3.51e-05 | 3349 | 2118.7775 | 422 | 0.073065 | 3.2149 | 956 | 0.06 | 1886
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 9460 | FALSE | 18052.5321 | 17926.192 | 11.1412 | 91 | 8.36e-05 | 2112 | 856.971 | 910 | 0.073014 | 6.6443 | 957 | 0.01 | 2611
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 84944 | FALSE | 93674.3078 | 93674.3078 | 58.219 | 439 | 7.78e-05 | 2268 | 921.9165 | 873 | 0.072725 | 31.9262 | 958 |  | 2719
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 810594 | TRUE | 1080.6364 | 899.4073 | 0.55899 | 6 | 0.0001145 | 1307 | 459.6008 | 1235 | 0.072684 | 0.4361 | 959 |  | 3228
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | CB | FALSE | 25933.7558 | 8735.2446 | 5.429 | 200 | 0.00014636 | 784 | 521.6714 | 1181 | 0.072647 | 14.5295 | 960 | 0.55 | 869
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 980192 | FALSE | 6178.6453 | 6178.6453 | 3.8401 | 19 | 3.43e-05 | 3362 | 2382.3266 | 363 | 0.072592 | 1.3793 | 961 |  | 3513
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | CB | TRUE | 4213.006 | 696.6837 | 0.43299 | 36 | 6.81e-05 | 2534 | 412.1878 | 1283 | 0.07222 | 2.5999 | 962 | 0.06 | 1816
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | CB | FALSE | 29664.4521 | 21174.1488 | 13.1598 | 91 | 0.00013717 | 905 | 720.7685 | 998 | 0.072102 | 6.5613 | 963 | 0.02 | 2565
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 4086 | FALSE | 18494.2051 | 18494.2051 | 11.4942 | 66 | 0.00012787 | 1052 | 634.8288 | 1073 | 0.072098 | 4.7585 | 964 | 0.12 | 1393
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 132 | FALSE | 40702.0776 | 40702.0776 | 25.2965 | 184 | 7.37e-05 | 2369 | 1030.4196 | 808 | 0.071994 | 13.2468 | 965 | 4.02 | 529
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 1596 | FALSE | 35104.5465 | 35104.5465 | 21.8176 | 132 | 6.04e-05 | 2763 | 1180.3203 | 741 | 0.071922 | 9.4937 | 966 | 0.01 | 2583
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 13490 | FALSE | 8773.504 | 6875.4256 | 4.2731 | 49 | 0.00015838 | 660 | 538.4381 | 1161 | 0.071878 | 3.522 | 967 | 0.05 | 1975
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 49144 | FALSE | 34128.6869 | 29574.1503 | 18.3805 | 169 | 0.00016343 | 606 | 803.7485 | 937 | 0.071512 | 12.0855 | 968 | 0.08 | 1646
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | CB | TRUE | 26588.5909 | 184.0196 | 0.11437 | 188 | 9.79e-05 | 1694 | 539.3221 | 1159 | 0.0715 | 13.442 | 969 | 0.02 | 2564
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 7134 | FALSE | 37777.9012 | 32518.1243 | 20.2101 | 172 | 9.53e-05 | 1759 | 696.6949 | 1025 | 0.071297 | 12.2631 | 970 | 0.09 | 1546
4319 | MESA 11016111 | 182821101 | MESA 1101 | 6111 | FALSE | 41513.5486 | 39023.9015 | 24.2535 | 202 | 4.98e-05 | 3042 | 1337.456 | 665 | 0.071153 | 14.3729 | 971 | 9.09 | 413
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 740076 | TRUE | 14283.4902 | 632.3767 | 0.39302 | 106 | 0.00010531 | 1512 | 793.8066 | 947 | 0.071071 | 7.5335 | 972 |  | 2963
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 799924 | TRUE | 621.6151 | 621.6151 | 0.38634 | 4 | 0.00011059 | 1397 | 1327.4203 | 669 | 0.070818 | 0.28327 | 973 |  | 3334
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 724884 | FALSE | 22726.0215 | 22589.092 | 14.0392 | 167 | 0.00017254 | 546 | 443.793 | 1254 | 0.070791 | 11.822 | 974 |  | 2712
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 469810 | FALSE | 9545.8932 | 3464.1714 | 2.153 | 14 | 8.33e-05 | 2125 | 778.0104 | 955 | 0.070672 | 0.98941 | 975 |  | 3354
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 980944 | FALSE | 26900.3072 | 16783.2453 | 10.4309 | 198 | 0.00019807 | 404 | 366.1605 | 1345 | 0.070566 | 13.9721 | 976 |  | 2798
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 76068 | FALSE | 31093.7701 | 27642.9269 | 17.1802 | 232 | 7.71e-05 | 2284 | 1055.6938 | 794 | 0.070348 | 16.3207 | 977 | 6.25 | 470
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | CB | TRUE | 4411.9174 | 914.1112 | 0.56812 | 33 | 8.04e-05 | 2194 | 401.4638 | 1294 | 0.070136 | 2.3145 | 978 |  | 3048
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 306476 | FALSE | 16292.4669 | 3106.377 | 1.9306 | 49 | 0.00010648 | 1486 | 598.7531 | 1101 | 0.069853 | 3.4228 | 979 |  | 3316
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 65454 | FALSE | 3114.2101 | 2176.3172 | 1.3526 | 23 | 6.08e-05 | 2754 | 1192.0123 | 737 | 0.069594 | 1.6007 | 980 | 2.09 | 622
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 1500 | FALSE | 41880.4686 | 41880.4686 | 26.0289 | 261 | 0.00012847 | 1038 | 750.2992 | 975 | 0.069495 | 18.1383 | 981 | 0.21 | 1153
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 8920 | TRUE | 158.1242 | 158.1242 | 0.098275 | 2 | 0.00017718 | 518 | 499.4912 | 1200 | 0.069477 | 0.13895 | 982 | 0.19 | 1196
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 10000 | FALSE | 53656.1229 | 47097.1904 | 29.2711 | 230 | 6.34e-05 | 2664 | 1330.8242 | 668 | 0.069198 | 15.9156 | 983 | 0.02 | 2464
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | V36 | FALSE | 21377.0625 | 18028.895 | 11.205 | 150 | 6.19e-05 | 2723 | 1033.145 | 804 | 0.069118 | 10.3677 | 984 | 6.65 | 464
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 77086 | FALSE | 6051.2822 | 4371.5846 | 2.717 | 47 | 0.00020917 | 363 | 405.3593 | 1291 | 0.068998 | 3.2429 | 985 |  | 3331
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 85152 | FALSE | 37332.1384 | 37332.1384 | 23.2021 | 279 | 4.41e-05 | 3188 | 1657.8134 | 539 | 0.068983 | 19.2463 | 986 | 8.2 | 433
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 544 | TRUE | 16214.8056 | 786.2676 | 0.48867 | 98 | 8.98e-05 | 1918 | 761.7873 | 963 | 0.068781 | 6.7406 | 987 |  | 2803
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 97188 | FALSE | 10919.7899 | 10919.7899 | 6.7867 | 71 | 0.00011852 | 1217 | 794.0069 | 946 | 0.068613 | 4.8715 | 988 | 0.06 | 1870
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | R2838 | FALSE | 32896.73 | 32896.73 | 20.4455 | 210 | 3.73e-05 | 3308 | 2069.6718 | 438 | 0.068544 | 14.3942 | 989 | 0.21 | 1136
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | CB | TRUE | 46.711 | 46.711 | 0.029031 | 1 | 0.00015165 | 723 | 451.5011 | 1247 | 0.068469 | 0.068469 | 990 | 4.71 | 509
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 835115 | FALSE | 29192.1081 | 29192.1081 | 18.143 | 191 | 7.82e-05 | 2253 | 868.4883 | 902 | 0.068398 | 13.0639 | 991 |  | 2775
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | Y70 | FALSE | 13947.1347 | 10839.1211 | 6.7366 | 61 | 5.11e-05 | 3011 | 1300.1446 | 683 | 0.068291 | 4.1658 | 992 | 0.02 | 2489
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 295566 | TRUE | 3409.6411 | 751.534 | 0.46708 | 18 | 5.22e-05 | 2987 | 1215.0443 | 723 | 0.068263 | 1.2287 | 993 |  | 2864
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 1804 | FALSE | 69024.1301 | 69024.1301 | 42.8988 | 394 | 0.00011734 | 1239 | 495.1119 | 1205 | 0.068197 | 26.8697 | 994 | 0.15 | 1295
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 2260 | FALSE | 36303.3353 | 25414.2279 | 15.795 | 185 | 7.15e-05 | 2433 | 1004.259 | 833 | 0.067786 | 12.5404 | 995 | 0.08 | 1667
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 583708 | FALSE | 1263.0794 | 1011.3641 | 0.62857 | 11 | 9.38e-05 | 1800 | 952.2243 | 858 | 0.067762 | 0.74538 | 996 |  | 3189
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | CB | FALSE | 2698.3212 | 1098.894 | 0.68297 | 23 | 9.85e-05 | 1678 | 430.579 | 1258 | 0.067722 | 1.5576 | 997 | 0.47 | 908
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | Y46 | FALSE | 76660.9296 | 50653.8838 | 31.4816 | 277 | 4.21e-05 | 3223 | 1429.3656 | 626 | 0.067522 | 18.7037 | 998 | 0.13 | 1364
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | CB | FALSE | 21488.1146 | 9459.2642 | 5.879 | 171 | 0.00014623 | 785 | 382.8028 | 1314 | 0.067405 | 11.5263 | 999 | 0.05 | 1971
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 456397 | FALSE | 2239.0721 | 2239.0721 | 1.3916 | 19 | 9.78e-05 | 1696 | 785.4652 | 954 | 0.067328 | 1.2792 | 1000 |  | 3391
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | CB | FALSE | 3697.5337 | 3697.5337 | 2.298 | 32 | 0.00012582 | 1082 | 762.0604 | 962 | 0.067293 | 2.1534 | 1001 | 0.05 | 1960
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 146070 | FALSE | 22680.3921 | 20479.5896 | 12.7281 | 167 | 6.69e-05 | 2560 | 1071.9697 | 786 | 0.067012 | 11.191 | 1002 |  | 2871
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 64908 | FALSE | 10254.7707 | 6238.0239 | 3.877 | 84 | 0.00035803 | 84 | 246.1325 | 1550 | 0.066995 | 5.6276 | 1003 | 0.84 | 767
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 53732 | FALSE | 12542.8 | 12542.8 | 7.7954 | 77 | 9.7e-05 | 1714 | 766.0355 | 959 | 0.066862 | 5.1484 | 1004 | 17.55 | 332
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 43924 | FALSE | 15096.7446 | 12523.7999 | 7.7836 | 107 | 0.00015399 | 708 | 446.2971 | 1252 | 0.066852 | 7.1532 | 1005 | 91.99 | 30
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | P02 | TRUE | 11656.6661 | 515.0322 | 0.32009 | 93 | 5.09e-05 | 3016 | 803.9256 | 936 | 0.06682 | 6.2143 | 1006 | 0.32 | 993
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 172096 | TRUE | 1240.5827 | 425.5098 | 0.26446 | 12 | 0.00013435 | 939 | 425.6324 | 1267 | 0.06657 | 0.79884 | 1007 |  | 3077
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | CB | FALSE | 20191.5411 | 12387.7147 | 7.699 | 131 | 0.00018717 | 460 | 356.2256 | 1362 | 0.06648 | 8.7089 | 1008 | 0.06 | 1904
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 39256 | FALSE | 42581.0612 | 42581.0612 | 26.4643 | 287 | 0.00012638 | 1077 | 694.1209 | 1026 | 0.066296 | 19.0271 | 1009 | 0.26 | 1068
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 49484 | FALSE | 4257.4421 | 4257.4421 | 2.646 | 27 | 0.000124 | 1121 | 880.5018 | 890 | 0.06627 | 1.7893 | 1010 | 0.02 | 2543
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 2664 | FALSE | 17552.7674 | 12910.8902 | 8.0242 | 132 | 0.00019724 | 409 | 283.8161 | 1468 | 0.066185 | 8.7364 | 1011 | 7.85 | 440
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 98998 | TRUE | 20001.4994 | 118.1019 | 0.073401 | 136 | 8.55e-05 | 2044 | 370.2201 | 1337 | 0.066014 | 8.9779 | 1012 | 0.02 | 2466
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | A18 | FALSE | 29115.6622 | 14189.3642 | 8.8187 | 188 | 6.7e-05 | 2556 | 932.8875 | 868 | 0.065994 | 12.4068 | 1013 | 1.58 | 663
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 141073 | FALSE | 3422.9373 | 1996.4523 | 1.2408 | 27 | 0.00018845 | 450 | 208.8541 | 1621 | 0.065722 | 1.7745 | 1014 |  | 3174
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 9220 | FALSE | 18356.5403 | 17704.0281 | 11.0031 | 123 | 0.00012861 | 1036 | 658.7055 | 1055 | 0.065661 | 8.0763 | 1015 | 0.19 | 1191
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 1342 | FALSE | 62297.5033 | 33351.1972 | 20.7279 | 440 | 0.00011151 | 1385 | 593.3765 | 1111 | 0.065366 | 28.7609 | 1016 | 1.74 | 645
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | W531R | FALSE | 17380.2917 | 10443.673 | 6.4908 | 100 | 6.97e-05 | 2483 | 735.723 | 988 | 0.065356 | 6.5356 | 1017 | 0.07 | 1731
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 13322 | FALSE | 66617.6825 | 66617.6825 | 41.4032 | 490 | 6.24e-05 | 2708 | 1047.9717 | 798 | 0.065331 | 32.0124 | 1018 | 0.31 | 1005
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 21160 | FALSE | 38269.4773 | 38269.4773 | 23.7846 | 194 | 4.48e-05 | 3167 | 1259.0438 | 695 | 0.065187 | 12.6462 | 1019 | 0.07 | 1757
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 126697 | FALSE | 1766.1223 | 1641.863 | 1.0204 | 10 | 6.11e-05 | 2745 | 1011.3761 | 827 | 0.065062 | 0.65062 | 1020 |  | 3433
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | CB | FALSE | 2729.0129 | 2729.0129 | 1.6961 | 12 | 0.00018833 | 451 | 298.7993 | 1449 | 0.06474 | 0.77689 | 1021 | 0.03 | 2234
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 124 | FALSE | 29762.4384 | 29762.4384 | 18.4975 | 99 | 0.00011564 | 1282 | 546.7406 | 1151 | 0.064597 | 6.3951 | 1022 | 4.64 | 511
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | Q08 | FALSE | 19981.628 | 19981.628 | 12.4187 | 148 | 5.64e-05 | 2876 | 1236.4827 | 708 | 0.064559 | 9.5547 | 1023 | 4.37 | 521
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 542920 | FALSE | 2484.216 | 2034.8319 | 1.2647 | 10 | 2.94e-05 | 3433 | 2350.3357 | 372 | 0.064427 | 0.64427 | 1024 |  | 3478
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | R12 | FALSE | 64632.5351 | 52796.2686 | 32.8131 | 278 | 5.15e-05 | 3005 | 1212.0624 | 725 | 0.064341 | 17.8868 | 1025 | 0.1 | 1470
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 1993 | FALSE | 4771.9686 | 4470.3512 | 2.7783 | 39 | 6.1e-05 | 2747 | 818.0593 | 926 | 0.064212 | 2.5043 | 1026 | 3.17 | 558
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 66730 | FALSE | 1703.3079 | 1703.3079 | 1.0586 | 6 | 0.00011857 | 1215 | 919.8595 | 875 | 0.064035 | 0.38421 | 1027 | 0.49 | 897
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 87432 | FALSE | 21925.1583 | 15708.5355 | 9.7629 | 81 | 7.14e-05 | 2436 | 994.1805 | 837 | 0.063901 | 5.176 | 1028 | 0.09 | 1521
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 1325 | FALSE | 13829.5499 | 13829.5499 | 8.5951 | 80 | 0.00012793 | 1047 | 449.2232 | 1249 | 0.063613 | 5.0891 | 1029 | 12.01 | 378
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 1216 | FALSE | 30877.2329 | 21628.5531 | 13.4422 | 182 | 0.00012873 | 1035 | 525.6183 | 1178 | 0.063522 | 11.561 | 1030 | 0.07 | 1733
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 18935 | FALSE | 10773.8274 | 10773.8274 | 6.696 | 76 | 0.00011327 | 1337 | 910.0927 | 882 | 0.063224 | 4.805 | 1031 | 8.29 | 432
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | N30 | FALSE | 32768.3238 | 32768.3238 | 20.3656 | 120 | 6.32e-05 | 2674 | 927.1943 | 870 | 0.063152 | 7.5782 | 1032 | 0.09 | 1530
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 2070 | FALSE | 15059.4591 | 14786.6222 | 9.1899 | 72 | 0.00014395 | 814 | 498.0458 | 1203 | 0.063106 | 4.5436 | 1033 | 0.07 | 1760
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 116402 | FALSE | 11255.0357 | 3810.8828 | 2.3685 | 64 | 5.74e-05 | 2850 | 1320.2856 | 674 | 0.062979 | 4.0307 | 1034 |  | 2740
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 186912 | FALSE | 97116.525 | 94273.5723 | 58.5914 | 606 | 9.54e-05 | 1747 | 711.7437 | 1013 | 0.06292 | 38.1293 | 1035 | 0.18 | 1223
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 4170 | FALSE | 15319.6405 | 15319.6405 | 9.5212 | 45 | 4.29e-05 | 3210 | 1356.0496 | 661 | 0.062779 | 2.8251 | 1036 | 0.03 | 2358
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 8189 | FALSE | 1685.4401 | 1685.4401 | 1.0475 | 11 | 0.00035454 | 86 | 166.396 | 1732 | 0.062553 | 0.68809 | 1037 | 0.02 | 2537
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | CB | FALSE | 27174.1674 | 1828.844 | 1.1366 | 175 | 0.0001054 | 1510 | 467.1503 | 1226 | 0.062374 | 10.9155 | 1038 | 0.02 | 2425
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 203380 | TRUE | 3178.2991 | 809.5956 | 0.50317 | 26 | 0.00010239 | 1592 | 687.7534 | 1032 | 0.062335 | 1.6207 | 1039 |  | 3423
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 12342 | TRUE | 1750.136 | 352.0949 | 0.21883 | 16 | 0.00013409 | 942 | 663.7688 | 1049 | 0.062293 | 0.99668 | 1040 | 0.32 | 996
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 13478 | FALSE | 24836.1056 | 19846.6513 | 12.3348 | 169 | 0.0001203 | 1180 | 594.448 | 1107 | 0.062159 | 10.5049 | 1041 | 0.09 | 1570
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 2094 | FALSE | 27452.3558 | 25248.6295 | 15.6921 | 139 | 0.00021404 | 343 | 379.7853 | 1321 | 0.062103 | 8.6323 | 1042 | 3.85 | 533
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 2028 | FALSE | 17437.7183 | 17437.7183 | 10.8376 | 86 | 0.00015423 | 702 | 243.285 | 1559 | 0.062015 | 5.3333 | 1043 | 0.41 | 939
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 12282 | FALSE | 58482.1143 | 58482.1143 | 36.3469 | 261 | 0.00011986 | 1190 | 718.4403 | 1004 | 0.061928 | 16.1631 | 1044 | 0.18 | 1206
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 2537 | FALSE | 8030.1143 | 8030.1143 | 4.9907 | 37 | 9.2e-05 | 1844 | 618.6971 | 1083 | 0.061762 | 2.2852 | 1045 | 0.2 | 1156
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | A46 | TRUE | 13904.7944 | 633.1098 | 0.39348 | 94 | 8.19e-05 | 2157 | 550.2411 | 1144 | 0.06175 | 5.8045 | 1046 | 0.02 | 2447
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 51738 | TRUE | 1844.3225 | 26.6806 | 0.016582 | 19 | 0.00013923 | 882 | 441.8941 | 1255 | 0.061564 | 1.1697 | 1047 | 17.24 | 335
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | V78 | FALSE | 47471.3302 | 47471.3302 | 29.5036 | 164 | 6.88e-05 | 2516 | 918.2768 | 876 | 0.061453 | 10.0783 | 1048 | 0.19 | 1179
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | TRUE | 63.3636 | 63.3636 | 0.039381 | 1 | 0.00010321 | 1565 | 595.1616 | 1105 | 0.061428 | 0.061428 | 1049 | 8.51 | 425
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 127563 | FALSE | 11105.9314 | 11105.9314 | 6.9024 | 63 | 7.22e-05 | 2413 | 803.5682 | 938 | 0.061336 | 3.8642 | 1050 | 23.56 | 283
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 351038 | FALSE | 22506.9662 | 2661.6552 | 1.6542 | 130 | 7.02e-05 | 2462 | 1068.3127 | 787 | 0.061316 | 7.971 | 1051 |  | 3029
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 1496 | FALSE | 26084.969 | 23526.9728 | 14.6221 | 201 | 7.64e-05 | 2297 | 864.7228 | 905 | 0.06121 | 12.3032 | 1052 | 0.06 | 1790
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | CB | TRUE | 56.7484 | 56.7484 | 0.035269 | 1 | 0.0001609 | 632 | 380.3958 | 1320 | 0.061207 | 0.061207 | 1053 |  | 3497
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 2408 | FALSE | 18614.5661 | 18614.5661 | 11.569 | 124 | 0.000106 | 1493 | 623.6203 | 1079 | 0.060864 | 7.5471 | 1054 | 0.34 | 981
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | CB | FALSE | 4357.8457 | 4357.8457 | 2.7084 | 3 | 0.00010885 | 1430 | 808.7175 | 931 | 0.060819 | 0.18246 | 1055 | 0.02 | 2472
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | CB | TRUE | 11952.1608 | 777.7423 | 0.48337 | 85 | 0.00011707 | 1245 | 452.6669 | 1244 | 0.060715 | 5.1608 | 1056 | 0.06 | 1775
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 452 | FALSE | 31530.7427 | 8129.076 | 5.0523 | 207 | 0.00010226 | 1598 | 743.369 | 981 | 0.060708 | 12.5666 | 1057 | 0.67 | 816
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 670 | TRUE | 4937.5444 | 587.1475 | 0.36491 | 43 | 0.00012733 | 1058 | 393.8186 | 1302 | 0.06056 | 2.6041 | 1058 | 0.03 | 2292
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | CB | FALSE | 13703.2012 | 13703.2012 | 8.5166 | 51 | 0.00018978 | 443 | 315.2875 | 1424 | 0.060495 | 3.0852 | 1059 | 2.08 | 624
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 2013 | TRUE | 7412.4545 | 238.9679 | 0.14852 | 51 | 5.22e-05 | 2988 | 888.4761 | 888 | 0.06048 | 3.0845 | 1060 | 0.44 | 923
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | L5407 | FALSE | 29410.8857 | 29410.8857 | 18.279 | 153 | 4.59e-05 | 3142 | 1349.9596 | 663 | 0.060463 | 9.2508 | 1061 | 0.09 | 1522
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 56972 | FALSE | 13791.0471 | 13791.0471 | 8.5712 | 57 | 0.00011753 | 1234 | 612.4545 | 1090 | 0.060186 | 3.4306 | 1062 | 0.04 | 2114
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | CB | FALSE | 3229.2079 | 2904.3184 | 1.805 | 19 | 0.00016629 | 580 | 366.1668 | 1344 | 0.05984 | 1.137 | 1063 | 0.04 | 2199
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 708161 | FALSE | 1824.6356 | 1615.0007 | 1.0037 | 12 | 0.00012306 | 1133 | 461.5277 | 1234 | 0.059606 | 0.71527 | 1064 |  | 3411
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6064 | FALSE | 13322.7276 | 10776.9352 | 6.6979 | 66 | 0.00027944 | 157 | 244.0042 | 1557 | 0.059515 | 3.928 | 1065 | 1.74 | 646
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 36680 | FALSE | 32219.8242 | 15055.3944 | 9.357 | 265 | 8.24e-05 | 2143 | 715.9031 | 1008 | 0.059472 | 15.7601 | 1066 | 2.94 | 572
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 844168 | FALSE | 18710.7045 | 7309.0201 | 4.5426 | 100 | 5.8e-05 | 2836 | 877.0353 | 894 | 0.059437 | 5.9437 | 1067 |  | 3097
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 2110 | FALSE | 32283.1191 | 31798.2221 | 19.7627 | 224 | 0.00013772 | 899 | 464.9832 | 1230 | 0.059423 | 13.3106 | 1068 | 0.21 | 1147
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 696 | FALSE | 11659.1184 | 6037.9333 | 3.7526 | 79 | 7.45e-05 | 2343 | 617.4166 | 1085 | 0.059025 | 4.663 | 1069 | 0.32 | 991
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 1540 | TRUE | 20738.5879 | 256.3874 | 0.15935 | 157 | 0.00010932 | 1426 | 527.982 | 1175 | 0.058865 | 9.2418 | 1070 | 0.04 | 2210
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 2708 | FALSE | 17128.5396 | 15094.9992 | 9.3816 | 124 | 0.00011703 | 1249 | 634.212 | 1074 | 0.058775 | 7.2881 | 1071 | 0.09 | 1533
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 460414 | FALSE | 10774.9077 | 8655.1604 | 5.3792 | 38 | 8.55e-05 | 2043 | 785.6181 | 953 | 0.058719 | 2.2313 | 1072 |  | 2688
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 48750 | FALSE | 28839.2375 | 28839.2375 | 17.9237 | 165 | 9.93e-05 | 1660 | 705.0697 | 1020 | 0.058621 | 9.6724 | 1073 | 19.06 | 315
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 82622 | FALSE | 41703.3815 | 41703.3815 | 25.9188 | 254 | 8.81e-05 | 1980 | 753.4327 | 972 | 0.058508 | 14.8609 | 1074 | 0.2 | 1166
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | CB | FALSE | 38608.5003 | 37939.8486 | 23.5798 | 181 | 6.16e-05 | 2729 | 1004.6328 | 832 | 0.058399 | 10.5701 | 1075 | 0.03 | 2280
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 512912 | FALSE | 3140.8885 | 1435.1217 | 0.89193 | 23 | 6.29e-05 | 2682 | 742.0792 | 982 | 0.058383 | 1.3428 | 1076 |  | 2970
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | CB | FALSE | 63324.3345 | 63324.3345 | 39.3563 | 375 | 0.00014192 | 841 | 477.8627 | 1217 | 0.058367 | 21.8875 | 1077 | 0.76 | 785
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 2562 | FALSE | 55111.7044 | 31122.7322 | 19.3429 | 222 | 5.83e-05 | 2824 | 1193.0263 | 734 | 0.057915 | 12.8572 | 1078 | 0.05 | 1950
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 338 | FALSE | 23338.4107 | 12496.8829 | 7.7669 | 176 | 0.00010195 | 1604 | 593.3845 | 1110 | 0.05791 | 10.1921 | 1079 | 7.05 | 454
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 4523 | FALSE | 4420.7892 | 1471.0588 | 0.91427 | 28 | 9.53e-05 | 1750 | 593.4447 | 1109 | 0.057806 | 1.6186 | 1080 |  | 3449
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 289947 | TRUE | 3212.1673 | 447.6357 | 0.27821 | 21 | 8.52e-05 | 2054 | 855.7073 | 911 | 0.057658 | 1.2108 | 1081 |  | 3472
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1087 | FALSE | 3157.1282 | 3157.1282 | 1.9622 | 22 | 0.00010485 | 1532 | 532.5062 | 1170 | 0.05764 | 1.2681 | 1082 | 7.64 | 443
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 816852 | FALSE | 70141.7467 | 20545.6876 | 12.7692 | 423 | 4.26e-05 | 3214 | 1516.9463 | 587 | 0.057549 | 24.3431 | 1083 |  | 2655
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | CB | FALSE | 20142.5456 | 20085.8093 | 12.4834 | 141 | 0.00015851 | 658 | 382.2019 | 1316 | 0.057543 | 8.1136 | 1084 | 0.64 | 827
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 7070 | FALSE | 26486.1632 | 10307.0829 | 6.4059 | 132 | 5.01e-05 | 3036 | 1217.7073 | 718 | 0.057494 | 7.5892 | 1085 | 0.03 | 2323
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 1654 | FALSE | 28221.2564 | 28221.2564 | 17.5396 | 168 | 8.91e-05 | 1943 | 662.2613 | 1051 | 0.057486 | 9.6576 | 1086 | 0.1 | 1492
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 3745 | FALSE | 7247.2343 | 7247.2343 | 4.5042 | 52 | 0.00018327 | 486 | 535.7815 | 1164 | 0.057415 | 2.9856 | 1087 | 1.01 | 730
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | CB | FALSE | 50985.8349 | 50985.8349 | 31.6879 | 293 | 8.48e-05 | 2072 | 750.5824 | 974 | 0.05741 | 16.8213 | 1088 | 0.1 | 1456
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 751990 | FALSE | 39452.6049 | 39436.6029 | 24.51 | 243 | 0.00013521 | 926 | 355.8632 | 1363 | 0.057382 | 13.9439 | 1089 |  | 2702
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 51584 | FALSE | 35041.5534 | 35041.5534 | 21.7785 | 224 | 7.76e-05 | 2272 | 869.1368 | 901 | 0.057318 | 12.8393 | 1090 | 0.08 | 1655
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1404 | FALSE | 5740.3584 | 2402.8891 | 1.4934 | 47 | 0.0001882 | 452 | 397.9556 | 1298 | 0.057199 | 2.6884 | 1091 | 0.03 | 2347
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | CB | FALSE | 15329.2524 | 14012.7161 | 8.709 | 102 | 8.26e-05 | 2139 | 748.7975 | 976 | 0.057183 | 5.8326 | 1092 | 18.75 | 318
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 89150 | FALSE | 15332.2939 | 15332.2939 | 9.5291 | 88 | 0.00012195 | 1149 | 582.7266 | 1121 | 0.057148 | 5.029 | 1093 | 0.48 | 905
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | CB | FALSE | 2345.4974 | 1187.935 | 0.73831 | 21 | 7.67e-05 | 2290 | 471.5803 | 1223 | 0.057097 | 1.199 | 1094 | 0.67 | 818
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 4756 | FALSE | 18962.2339 | 15139.4165 | 9.4092 | 95 | 0.000145 | 802 | 459.0245 | 1236 | 0.057032 | 5.4181 | 1095 | 0.05 | 1943
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 2124 | FALSE | 5026.2322 | 5026.2322 | 3.1238 | 6 | 0.00058653 | 20 | 170.3508 | 1714 | 0.057006 | 0.34203 | 1096 | 1.87 | 636
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | CB | FALSE | 1058.7166 | 1058.7166 | 0.658 | 7 | 0.00022337 | 306 | 221.0499 | 1604 | 0.057005 | 0.39904 | 1097 | 0.06 | 1873
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 901690 | FALSE | 63574.4496 | 60028.2631 | 37.3078 | 306 | 5.67e-05 | 2868 | 1011.6278 | 825 | 0.056927 | 17.4196 | 1098 | 0.62 | 841
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | CB | FALSE | 36057.8693 | 23579.7024 | 14.6549 | 190 | 0.00011058 | 1399 | 511.8263 | 1189 | 0.056867 | 10.8047 | 1099 | 0.02 | 2512
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 853720 | FALSE | 50276.8108 | 50276.8108 | 31.2472 | 140 | 6.25e-05 | 2705 | 1012.617 | 823 | 0.056625 | 7.9275 | 1100 |  | 2684
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 37368 | FALSE | 9786.5772 | 9786.5772 | 6.0824 | 48 | 7.03e-05 | 2459 | 880.1307 | 892 | 0.056596 | 2.7166 | 1101 | 0.06 | 1898
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | CB | FALSE | 4540.438 | 4454.6417 | 2.7686 | 35 | 0.00019479 | 417 | 248.765 | 1543 | 0.056508 | 1.9778 | 1102 | 0.3 | 1017
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 37410 | FALSE | 8875.6069 | 8413.1179 | 5.2288 | 42 | 0.00021128 | 354 | 348.1422 | 1375 | 0.056472 | 2.3718 | 1103 | 0.04 | 2173
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | CB | FALSE | 15108.5071 | 11908.479 | 7.4012 | 76 | 7.91e-05 | 2231 | 565.89 | 1132 | 0.056447 | 4.29 | 1104 | 0.45 | 919
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | CB | FALSE | 24719.9919 | 16900.9683 | 10.504 | 116 | 0.0002473 | 224 | 245.6875 | 1552 | 0.056321 | 6.5332 | 1105 | 3.13 | 561
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 775992 | FALSE | 5059.1291 | 3381.5311 | 2.1016 | 34 | 0.00012418 | 1115 | 374.1489 | 1330 | 0.056251 | 1.9125 | 1106 |  | 2954
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 461703 | FALSE | 1414.65 | 1414.65 | 0.87921 | 8 | 7.78e-05 | 2265 | 327.199 | 1402 | 0.05614 | 0.44912 | 1107 |  | 3274
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 51800 | FALSE | 15718.5986 | 14796.5287 | 9.1961 | 128 | 0.00016264 | 616 | 342.7814 | 1383 | 0.05603 | 7.1719 | 1108 | 3.81 | 534
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | M80 | FALSE | 93735.5013 | 93735.5013 | 58.257 | 397 | 4.57e-05 | 3147 | 1161.6823 | 749 | 0.055911 | 22.1966 | 1109 | 0.42 | 930
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 1991 | FALSE | 11465.3295 | 11465.3295 | 7.1257 | 51 | 0.00016331 | 608 | 395.6046 | 1299 | 0.055786 | 2.8451 | 1110 | 56.35 | 99
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 6697 | FALSE | 6657.3541 | 6657.3541 | 4.1376 | 46 | 0.00010476 | 1534 | 551.7785 | 1143 | 0.055767 | 2.5653 | 1111 | 0.1 | 1462
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 11270 | FALSE | 20312.1456 | 20312.1456 | 12.6241 | 123 | 0.00012756 | 1056 | 499.3074 | 1201 | 0.055685 | 6.8493 | 1112 | 0.11 | 1443
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 5040 | FALSE | 6507.5662 | 6507.5662 | 4.0445 | 46 | 0.0002406 | 244 | 218.6982 | 1609 | 0.055628 | 2.5589 | 1113 | 20.75 | 304
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 171410 | FALSE | 7035.3214 | 2217.9639 | 1.3785 | 40 | 0.00011961 | 1192 | 536.0514 | 1163 | 0.055603 | 2.2241 | 1114 |  | 3405
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 450 | FALSE | 30451.6805 | 9311.1997 | 5.7869 | 208 | 0.00012825 | 1043 | 484.352 | 1210 | 0.055438 | 11.531 | 1115 | 0.04 | 2211
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | CB | FALSE | 14529.9117 | 11213.2305 | 6.9691 | 99 | 0.00015794 | 663 | 471.1517 | 1224 | 0.05535 | 5.4797 | 1116 | 0.06 | 1842
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 35492 | FALSE | 34847.1678 | 16074.976 | 9.9907 | 219 | 9.73e-05 | 1708 | 426.1888 | 1265 | 0.055239 | 12.0973 | 1117 | 0.03 | 2257
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 829470 | FALSE | 16595.0205 | 16595.0205 | 10.3139 | 93 | 0.00011788 | 1231 | 515.0682 | 1185 | 0.055226 | 5.136 | 1118 |  | 3047
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8110 | FALSE | 13110.3306 | 13110.3306 | 8.1481 | 99 | 0.0001169 | 1252 | 657.3966 | 1057 | 0.055185 | 5.4634 | 1119 | 0.15 | 1283
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 859443 | TRUE | 777.6394 | 475.2837 | 0.29539 | 5 | 4.96e-05 | 3047 | 1445.6352 | 616 | 0.055167 | 0.27584 | 1120 |  | 3268
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | CB | FALSE | 9029.352 | 9029.352 | 5.6118 | 38 | 3.46e-05 | 3359 | 1447.0842 | 615 | 0.055113 | 2.0943 | 1121 | 0 | 2649
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 85002 | FALSE | 57093.5104 | 57093.5104 | 35.4838 | 394 | 7.63e-05 | 2302 | 729.1639 | 992 | 0.055026 | 21.6802 | 1122 | 0.87 | 759
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 13412 | FALSE | 62439.7255 | 62439.7255 | 38.8065 | 333 | 0.00011911 | 1202 | 811.1905 | 930 | 0.055018 | 18.321 | 1123 | 0.87 | 756
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 61736 | FALSE | 26875.6469 | 19558.6498 | 12.1558 | 129 | 6e-05 | 2773 | 726.4231 | 994 | 0.054986 | 7.0932 | 1124 | 0.05 | 1936
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 1576 | FALSE | 12974.577 | 12974.577 | 8.0638 | 51 | 8e-05 | 2206 | 832.2405 | 921 | 0.054922 | 2.801 | 1125 | 0.07 | 1744
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 352 | FALSE | 19238.6019 | 9086.2434 | 5.6471 | 123 | 0.00014867 | 757 | 547.944 | 1149 | 0.054876 | 6.7498 | 1126 | 0.04 | 2196
6906 | IONE 1101CB | 163881101 | IONE 1101 | CB | FALSE | 22613.9915 | 2970.8687 | 1.8464 | 85 | 0.00012529 | 1093 | 646.6464 | 1068 | 0.054859 | 4.663 | 1127 | 0.02 | 2492
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 6807 | FALSE | 7894.5527 | 7894.5527 | 4.9065 | 49 | 0.00014837 | 759 | 586.6523 | 1116 | 0.054517 | 2.6713 | 1128 | 0.08 | 1650
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 75140 | FALSE | 32224.0105 | 13968.9875 | 8.6818 | 238 | 4.95e-05 | 3050 | 824.0667 | 924 | 0.054483 | 12.967 | 1129 | 0.07 | 1713
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 831781 | FALSE | 2564.8738 | 1186.1396 | 0.73719 | 19 | 7.38e-05 | 2367 | 806.9369 | 932 | 0.054336 | 1.0324 | 1130 |  | 3304
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 9722 | FALSE | 62437.5165 | 62437.5165 | 38.8052 | 359 | 0.00010174 | 1610 | 529.226 | 1174 | 0.054308 | 19.4965 | 1131 | 0.52 | 890
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | XR152 | FALSE | 20635.5048 | 14045.9028 | 8.7296 | 156 | 8.08e-05 | 2185 | 646.2065 | 1069 | 0.054285 | 8.4685 | 1132 | 0.08 | 1583
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | CB | TRUE | 830.42 | 224.6189 | 0.1396 | 9 | 0.00020912 | 364 | 241.4035 | 1563 | 0.054215 | 0.48794 | 1133 | 0.02 | 2507
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 135854 | FALSE | 4250.0634 | 2325.1244 | 1.4451 | 34 | 6.06e-05 | 2759 | 1134.6908 | 761 | 0.053974 | 1.8351 | 1134 |  | 3213
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 1588 | FALSE | 13991.4401 | 13991.4401 | 8.6957 | 33 | 0.00018106 | 503 | 584.74 | 1118 | 0.053968 | 1.7809 | 1135 | 0.19 | 1195
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 2642 | FALSE | 7497.8568 | 7497.8568 | 4.6599 | 27 | 9.04e-05 | 1902 | 716.2407 | 1006 | 0.053841 | 1.4537 | 1136 | 0.03 | 2270
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 2014 | FALSE | 35984.1335 | 35984.1335 | 22.3643 | 181 | 0.00010418 | 1548 | 602.3767 | 1097 | 0.053762 | 9.731 | 1137 | 0.2 | 1157
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 63464 | FALSE | 21920.8692 | 21920.8692 | 13.6239 | 70 | 0.00012137 | 1160 | 659.6276 | 1053 | 0.05356 | 3.7492 | 1138 | 0.13 | 1359
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 47966 | FALSE | 27271.3222 | 27271.3222 | 16.9492 | 167 | 0.00020988 | 360 | 215.8045 | 1610 | 0.053445 | 8.9254 | 1139 | 0.13 | 1355
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1564 | FALSE | 17092.5832 | 1891.6003 | 1.1756 | 133 | 7.33e-05 | 2387 | 869.3002 | 900 | 0.053412 | 7.1038 | 1140 | 0.62 | 839
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 814616 | TRUE | 3902.6921 | 157.4015 | 0.097826 | 28 | 8.73e-05 | 2006 | 602.3323 | 1098 | 0.053409 | 1.4955 | 1141 |  | 2683
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 694042 | TRUE | 972.0471 | 972.0471 | 0.60413 | 8 | 0.00011883 | 1210 | 338.8363 | 1389 | 0.053395 | 0.42716 | 1142 |  | 3427
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 7742 | FALSE | 73623.5911 | 73535.6671 | 45.7027 | 475 | 9.92e-05 | 1663 | 595.5649 | 1104 | 0.053392 | 25.3612 | 1143 | 1.43 | 675
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | CB | FALSE | 22863.3142 | 22355.1305 | 13.8938 | 170 | 0.0001075 | 1464 | 527.7867 | 1176 | 0.053282 | 9.058 | 1144 | 0.12 | 1366
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 8974 | FALSE | 21278.6691 | 21278.6691 | 13.2248 | 149 | 0.00020534 | 378 | 324.7416 | 1406 | 0.05299 | 7.8956 | 1145 | 76.03 | 55
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 322 | FALSE | 23201.9813 | 22860.7646 | 14.2081 | 167 | 0.00013802 | 893 | 458.1425 | 1238 | 0.052976 | 8.847 | 1146 | 35.69 | 212
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | M88 | FALSE | 24723.9577 | 4969.351 | 3.0885 | 85 | 4.85e-05 | 3076 | 599.8118 | 1100 | 0.052933 | 4.4993 | 1147 | 0.01 | 2589
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 8884 | FALSE | 12033.5669 | 12033.5669 | 7.4789 | 74 | 0.00017464 | 530 | 305.5705 | 1438 | 0.052785 | 3.9061 | 1148 | 48.31 | 129
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 2500 | FALSE | 25777.1885 | 25777.1885 | 16.0206 | 106 | 0.00032433 | 107 | 205.0308 | 1627 | 0.052654 | 5.5813 | 1149 | 11.96 | 380
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 4500 | FALSE | 132540.1743 | 38902.9544 | 24.1783 | 516 | 4.64e-05 | 3128 | 1229.9776 | 714 | 0.052537 | 27.1089 | 1150 | 0.03 | 2255
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 1302 | FALSE | 23388.5169 | 22389.9711 | 13.9155 | 113 | 5.02e-05 | 3034 | 1215.8532 | 721 | 0.052453 | 5.9272 | 1151 | 0.06 | 1889
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | CB | FALSE | 6175.4075 | 6175.4075 | 3.838 | 9 | 9.26e-05 | 1830 | 515.1474 | 1184 | 0.052345 | 0.4711 | 1152 | 0.01 | 2588
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 244246 | FALSE | 1936.2709 | 1936.2709 | 1.2034 | 11 | 0.00016313 | 610 | 330.8536 | 1396 | 0.052269 | 0.57496 | 1153 |  | 3548
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 51484 | FALSE | 26385.5393 | 24741.7275 | 15.3771 | 195 | 0.0001406 | 862 | 372.49 | 1333 | 0.052212 | 10.1812 | 1154 | 0.17 | 1239
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 975698 | FALSE | 7671.0517 | 1441.7984 | 0.89608 | 44 | 4.36e-05 | 3200 | 962.1828 | 852 | 0.052194 | 2.2966 | 1155 |  | 3170
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 612 | FALSE | 6362.7002 | 6362.7002 | 3.9544 | 25 | 8.49e-05 | 2067 | 719.6048 | 1000 | 0.05213 | 1.3033 | 1156 | 0.42 | 931
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 776244 | TRUE | 783.9385 | 274.5802 | 0.17065 | 5 | 5.5e-05 | 2909 | 540.4117 | 1158 | 0.052117 | 0.26059 | 1157 |  | 3366
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 4947 | FALSE | 16652.8009 | 16652.8009 | 10.3498 | 56 | 0.00016312 | 611 | 298.2938 | 1450 | 0.052018 | 2.913 | 1158 | 9.04 | 414
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 7108 | FALSE | 20715.9427 | 15478.9307 | 9.6202 | 99 | 5.14e-05 | 3007 | 993.4887 | 838 | 0.05186 | 5.1341 | 1159 | 0.06 | 1876
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 72036 | FALSE | 21135.8241 | 20864.4611 | 12.9673 | 105 | 8.15e-05 | 2168 | 844.1543 | 916 | 0.051819 | 5.441 | 1160 | 14.82 | 354
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 37506 | FALSE | 18602.139 | 18602.139 | 11.5613 | 77 | 0.00015655 | 678 | 345.7654 | 1377 | 0.051705 | 3.9812 | 1161 | 4.56 | 516
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | CB | FALSE | 10891.762 | 10891.762 | 6.7693 | 40 | 7.36e-05 | 2374 | 760.2437 | 965 | 0.051564 | 2.0626 | 1162 | 0.19 | 1197
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | CB | FALSE | 4864.6418 | 2361.7078 | 1.4678 | 33 | 0.00010062 | 1634 | 651.0467 | 1063 | 0.051416 | 1.6967 | 1163 | 0.02 | 2516
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 960 | FALSE | 8826.9021 | 6237.2835 | 3.8765 | 33 | 0.00010013 | 1642 | 470.8479 | 1225 | 0.051413 | 1.6966 | 1164 | 0.04 | 2083
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 90970 | FALSE | 6924.4221 | 2317.6472 | 1.4404 | 45 | 0.00014799 | 763 | 359.43 | 1356 | 0.051234 | 2.3055 | 1165 | 0.91 | 749
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | CB | FALSE | 20034.2871 | 12973.5363 | 8.0631 | 159 | 0.00012464 | 1103 | 555.1824 | 1140 | 0.051116 | 8.1275 | 1166 | 0.08 | 1582
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 569005 | FALSE | 3858.1769 | 1152.5978 | 0.71634 | 38 | 7.74e-05 | 2278 | 606.2479 | 1095 | 0.051027 | 1.939 | 1167 |  | 3255
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | CB | FALSE | 10545.3692 | 10545.3692 | 6.554 | 31 | 0.00031506 | 112 | 137.2983 | 1822 | 0.050873 | 1.5771 | 1168 | 0.17 | 1226
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 737698 | TRUE | 340.8251 | 324.8619 | 0.2019 | 3 | 4.55e-05 | 3153 | 1051.0501 | 795 | 0.050749 | 0.15225 | 1169 |  | 3626
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 50548 | TRUE | 7824.3085 | 154.2272 | 0.095853 | 58 | 0.00014087 | 856 | 418.2026 | 1274 | 0.050695 | 2.9403 | 1170 | 1.85 | 638
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 684566 | FALSE | 4872.6951 | 4856.693 | 3.0185 | 4 | 3.35e-05 | 3376 | 2480.1079 | 347 | 0.050626 | 0.20251 | 1171 |  | 3437
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 2424 | FALSE | 30415.1718 | 30186.9031 | 18.7613 | 141 | 6.65e-05 | 2572 | 747.4809 | 977 | 0.050559 | 7.1288 | 1172 | 0.17 | 1231
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 286542 | FALSE | 9381.8687 | 3501.8559 | 2.1764 | 25 | 2.36e-05 | 3508 | 2087.6942 | 432 | 0.050527 | 1.2632 | 1173 |  | 3581
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 148 | FALSE | 24974.2018 | 24850.3478 | 15.4446 | 107 | 5.34e-05 | 2952 | 932.2932 | 869 | 0.050374 | 5.39 | 1174 | 0.13 | 1343
2728 | MESA 1103M72 | 182821103 | MESA 1103 | M72 | FALSE | 24045.3968 | 13551.8371 | 8.4225 | 180 | 6e-05 | 2776 | 772.2065 | 958 | 0.050224 | 9.0403 | 1175 | 0.09 | 1574
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 1508 | FALSE | 43792.5733 | 43792.5733 | 27.2173 | 249 | 0.00022481 | 303 | 269.7872 | 1498 | 0.050062 | 12.4656 | 1176 | 0.5 | 893
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 664 | FALSE | 17972.9054 | 15503.1919 | 9.6353 | 140 | 0.00013278 | 964 | 291.1861 | 1461 | 0.050043 | 7.006 | 1177 | 0.12 | 1389
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 32120 | FALSE | 65924.4872 | 65394.3269 | 40.6428 | 485 | 0.00015495 | 695 | 454.7289 | 1240 | 0.049959 | 24.23 | 1178 | 0.23 | 1120
1827 | BELL 11082226 | 152701108 | BELL 1108 | 2226 | FALSE | 41003.1194 | 38762.6482 | 24.0911 | 329 | 0.00015086 | 729 | 321.4507 | 1412 | 0.049738 | 16.3638 | 1179 | 0.14 | 1330
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 83288 | FALSE | 27936.7507 | 27936.7507 | 17.3628 | 140 | 0.00010218 | 1600 | 523.0336 | 1179 | 0.049736 | 6.9631 | 1180 | 56.24 | 100
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 1490 | FALSE | 24262.143 | 16986.9503 | 10.5575 | 122 | 4.67e-05 | 3120 | 1014.4444 | 820 | 0.0497 | 6.0634 | 1181 | 0.01 | 2607
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | XR258 | FALSE | 42613.4021 | 35307.703 | 21.9439 | 117 | 7.13e-05 | 2438 | 813.0901 | 929 | 0.049692 | 5.814 | 1182 | 0.07 | 1728
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 552 | FALSE | 24092.9744 | 15233.6156 | 9.4678 | 172 | 0.00013239 | 975 | 420.6103 | 1272 | 0.049565 | 8.5251 | 1183 | 2.64 | 591
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 654924 | FALSE | 8067.2123 | 4423.0701 | 2.749 | 61 | 8.02e-05 | 2200 | 663.8303 | 1048 | 0.049343 | 3.0099 | 1184 |  | 2692
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | M52 | FALSE | 56469.342 | 54530.2399 | 33.8908 | 131 | 6.77e-05 | 2540 | 719.2711 | 1001 | 0.04915 | 6.4386 | 1185 | 0.09 | 1551
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 55798 | FALSE | 37886.6196 | 37886.6196 | 23.5467 | 246 | 0.00011154 | 1383 | 632.8382 | 1075 | 0.049086 | 12.0752 | 1186 | 6.76 | 461
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 2243 | FALSE | 3051.2175 | 3051.2175 | 1.8963 | 16 | 0.00019188 | 434 | 257.113 | 1528 | 0.049051 | 0.78482 | 1187 | 4.86 | 503
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 1070 | FALSE | 13188.3135 | 12735.6646 | 7.9153 | 100 | 8.36e-05 | 2108 | 545.0696 | 1153 | 0.048737 | 4.8737 | 1188 | 0.08 | 1639
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 36902 | FALSE | 23754.9885 | 19990.5557 | 12.4242 | 147 | 6.37e-05 | 2656 | 753.8177 | 971 | 0.048735 | 7.1641 | 1189 | 0.05 | 2037
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | MR276 | FALSE | 6265.9535 | 6199.9698 | 3.8533 | 42 | 0.00011011 | 1409 | 507.3387 | 1193 | 0.048684 | 2.0447 | 1190 | 0.45 | 920
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 51676 | FALSE | 18975.7232 | 12910.4516 | 8.0239 | 145 | 0.00015332 | 718 | 372.9974 | 1332 | 0.048603 | 7.0475 | 1191 | 1.53 | 667
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 894956 | FALSE | 2635.3424 | 1243.2231 | 0.77267 | 16 | 4.14e-05 | 3237 | 1280.1289 | 689 | 0.048471 | 0.77554 | 1192 |  | 3371
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 567884 | FALSE | 4535.2993 | 4025.5628 | 2.5019 | 27 | 5.6e-05 | 2887 | 815.5904 | 927 | 0.048164 | 1.3004 | 1193 |  | 2926
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 1602 | FALSE | 36538.7848 | 29307.7542 | 18.2149 | 109 | 0.00014214 | 837 | 344.2493 | 1379 | 0.048111 | 5.244 | 1194 | 0.07 | 1681
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 292 | FALSE | 31568.6739 | 25055.0465 | 15.5718 | 165 | 0.00011528 | 1294 | 534.9666 | 1165 | 0.048057 | 7.9294 | 1195 | 0.1 | 1486
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 1760 | FALSE | 20336.5883 | 15610.272 | 9.7018 | 73 | 0.00026452 | 183 | 220.0765 | 1605 | 0.048043 | 3.5072 | 1196 | 0 | 2647
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 4160 | FALSE | 34990.3559 | 34990.3559 | 21.7466 | 194 | 0.00015367 | 716 | 332.5299 | 1395 | 0.047994 | 9.3109 | 1197 | 0.11 | 1435
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | CB | FALSE | 26803.1335 | 19300.4618 | 11.9953 | 191 | 0.00043617 | 57 | 153.1917 | 1768 | 0.047992 | 9.1665 | 1198 | 0.08 | 1590
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 1216 | FALSE | 8821.9491 | 8821.9491 | 5.4829 | 32 | 4.44e-05 | 3178 | 673.2647 | 1041 | 0.04796 | 1.5347 | 1199 | 0.02 | 2470
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | V76 | FALSE | 30510.6388 | 30510.6388 | 18.9625 | 59 | 6.9e-05 | 2510 | 662.2635 | 1050 | 0.047925 | 2.8276 | 1200 | 0.05 | 2034
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 65606 | FALSE | 20505.679 | 20505.679 | 12.7444 | 145 | 0.00013634 | 916 | 329.1085 | 1398 | 0.047918 | 6.9481 | 1201 | 65.5 | 77
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 753254 | TRUE | 576.081 | 561.1486 | 0.34876 | 2 | 0.0001316 | 988 | 1237.8633 | 707 | 0.047657 | 0.095314 | 1202 |  | 3631
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 59596 | FALSE | 58128.5973 | 33598.813 | 20.8818 | 294 | 6.87e-05 | 2517 | 659.4011 | 1054 | 0.047553 | 13.9806 | 1203 | 0.08 | 1603
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 991285 | TRUE | 2786.1304 | 525.9001 | 0.32685 | 24 | 8.66e-05 | 2019 | 543.9338 | 1154 | 0.047469 | 1.1393 | 1204 |  | 2968
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 2402 | FALSE | 6035.4639 | 2411.6802 | 1.4989 | 18 | 6.51e-05 | 2608 | 759.0384 | 966 | 0.047353 | 0.85235 | 1205 | 0.04 | 2096
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 4788 | FALSE | 111874.9537 | 111874.9537 | 69.5307 | 673 | 7.03e-05 | 2460 | 791.3267 | 951 | 0.047319 | 31.8454 | 1206 | 1.08 | 718
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 19772 | FALSE | 6198.5938 | 6198.5938 | 3.8525 | 41 | 7.72e-05 | 2283 | 525.9561 | 1177 | 0.047283 | 1.9386 | 1207 | 48.67 | 125
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 178 | FALSE | 21896.763 | 19626.441 | 12.1979 | 182 | 0.00014981 | 741 | 376.3772 | 1328 | 0.047227 | 8.5954 | 1208 | 24.56 | 276
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | R2845 | FALSE | 28680.0593 | 28680.0593 | 17.8248 | 172 | 4.09e-05 | 3246 | 1025.9007 | 811 | 0.047182 | 8.1154 | 1209 | 0.19 | 1180
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 68362 | FALSE | 11797.2095 | 8312.3827 | 5.1662 | 96 | 0.00012657 | 1070 | 343.9077 | 1382 | 0.047076 | 4.5193 | 1210 |  | 2751
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 785888 | FALSE | 11268.8078 | 7730.7085 | 4.8047 | 49 | 7.81e-05 | 2258 | 321.3673 | 1413 | 0.047021 | 2.304 | 1211 |  | 2753
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 92474 | FALSE | 25104.6477 | 24305.4181 | 15.1059 | 173 | 0.00013452 | 934 | 428.2739 | 1261 | 0.046937 | 8.12 | 1212 | 0.26 | 1060
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | MR339 | FALSE | 11213.6735 | 1921.2331 | 1.1941 | 73 | 5.9e-05 | 2809 | 692.7863 | 1028 | 0.046887 | 3.4227 | 1213 | 1 | 731
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 88630 | FALSE | 1252.5971 | 1252.5971 | 0.77849 | 6 | 6.54e-05 | 2605 | 876.4135 | 895 | 0.046842 | 0.28105 | 1214 | 0.03 | 2399
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | XR178 | FALSE | 20866.1928 | 9493.9491 | 5.9005 | 138 | 8.78e-05 | 1989 | 483.5128 | 1211 | 0.04683 | 6.4625 | 1215 | 0.94 | 744
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 39190 | FALSE | 2877.2566 | 2877.2566 | 1.7882 | 17 | 6.34e-05 | 2665 | 760.9398 | 964 | 0.046743 | 0.79463 | 1216 | 0 | 2644
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 180193 | FALSE | 3981.725 | 3477.0858 | 2.161 | 23 | 0.00010067 | 1630 | 430.5545 | 1259 | 0.046684 | 1.0737 | 1217 |  | 3467
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 467470 | FALSE | 4805.9002 | 2987.9 | 1.857 | 40 | 0.00023296 | 271 | 103.254 | 1936 | 0.046424 | 1.857 | 1218 |  | 2799
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | XR064 | FALSE | 6026.8923 | 1175.6095 | 0.73065 | 35 | 8.48e-05 | 2070 | 462.9277 | 1232 | 0.046387 | 1.6236 | 1219 |  | 3069
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 37388 | FALSE | 20103.5682 | 13050.4067 | 8.1109 | 56 | 2.11e-05 | 3533 | 2437.488 | 352 | 0.046193 | 2.5868 | 1220 | 0 | 2639
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 817491 | FALSE | 3153.3616 | 2279.4584 | 1.4167 | 24 | 0.00010509 | 1523 | 532.8427 | 1169 | 0.046183 | 1.1084 | 1221 |  | 3191
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | XR082 | FALSE | 32889.5484 | 31674.5025 | 19.6858 | 186 | 6.24e-05 | 2710 | 716.1395 | 1007 | 0.046133 | 8.5807 | 1222 | 0.21 | 1151
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 767280 | TRUE | 1164.558 | 816.4039 | 0.5074 | 11 | 4.39e-05 | 3191 | 579.646 | 1124 | 0.046117 | 0.50728 | 1223 |  | 3440
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 678 | FALSE | 57111.2211 | 56857.8795 | 35.3374 | 325 | 0.00011031 | 1406 | 496.7562 | 1204 | 0.046077 | 14.9751 | 1224 | 2.05 | 626
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 38998 | TRUE | 9317.0359 | 189.4976 | 0.11777 | 61 | 3.5e-05 | 3353 | 912.9133 | 879 | 0.046064 | 2.8099 | 1225 | 0.01 | 2570
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 600112 | FALSE | 2016.2056 | 1283.9759 | 0.798 | 18 | 0.00016569 | 586 | 185.2798 | 1671 | 0.045774 | 0.82393 | 1226 |  | 3379
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 654 | FALSE | 14047.9314 | 13220.1575 | 8.2164 | 71 | 8.69e-05 | 2013 | 576.6406 | 1126 | 0.045547 | 3.2338 | 1227 | 0.06 | 1895
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | XR254 | FALSE | 40510.5344 | 40510.5344 | 25.1775 | 134 | 6.94e-05 | 2490 | 745.0432 | 979 | 0.045544 | 6.1028 | 1228 | 0.31 | 1003
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 658 | FALSE | 17510.52 | 17510.52 | 10.8829 | 107 | 0.00014355 | 818 | 343.9435 | 1381 | 0.045341 | 4.8515 | 1229 | 50.23 | 119
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 7124 | FALSE | 51663.5431 | 17797.9944 | 11.0615 | 286 | 6.29e-05 | 2684 | 727.3308 | 993 | 0.045279 | 12.9498 | 1230 | 0.05 | 2026
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 3606 | FALSE | 26641.1753 | 17219.5096 | 10.702 | 129 | 8.64e-05 | 2025 | 738.4699 | 985 | 0.045178 | 5.828 | 1231 | 0.09 | 1541
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 37550 | TRUE | 5259.0816 | 590.535 | 0.36702 | 33 | 6.58e-05 | 2592 | 741.2586 | 983 | 0.045042 | 1.4864 | 1232 | 1.25 | 693
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 367100 | TRUE | 1041.0726 | 900.8036 | 0.55985 | 6 | 8.14e-05 | 2169 | 654.3693 | 1059 | 0.04493 | 0.26958 | 1233 |  | 3526
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 9330 | FALSE | 66516.2766 | 66516.2766 | 41.3401 | 345 | 4.81e-05 | 3091 | 936.7226 | 867 | 0.044648 | 15.4037 | 1234 | 0.27 | 1056
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 37632 | FALSE | 42770.2942 | 42770.2942 | 26.5819 | 304 | 0.0001591 | 651 | 314.3513 | 1426 | 0.044601 | 13.5588 | 1235 | 2.55 | 599
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 912460 | TRUE | 716.9415 | 226.2188 | 0.1406 | 6 | 0.0002094 | 362 | 319.3069 | 1418 | 0.044495 | 0.26697 | 1236 |  | 3384
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 37054 | FALSE | 14849.4038 | 14394.233 | 8.9461 | 76 | 0.00045585 | 46 | 99.7602 | 1954 | 0.044439 | 3.3774 | 1237 | 0.04 | 2218
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 92012 | FALSE | 29794.6367 | 29794.6367 | 18.5175 | 219 | 0.00021006 | 358 | 266.7744 | 1505 | 0.044304 | 9.7026 | 1238 | 27.19 | 260
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 351084 | FALSE | 14339.9461 | 3813.7275 | 2.3702 | 91 | 6.41e-05 | 2639 | 844.8485 | 915 | 0.044255 | 4.0272 | 1239 |  | 2770
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | CB | FALSE | 44653.7534 | 44000.0643 | 27.3462 | 341 | 0.00012378 | 1124 | 546.8562 | 1150 | 0.044085 | 15.0331 | 1240 | 0.94 | 742
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 1544 | FALSE | 44972.2866 | 27291.0085 | 16.9615 | 135 | 2.49e-05 | 3497 | 2130.6474 | 417 | 0.044056 | 5.9476 | 1241 | 0 | 2640
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 7100 | FALSE | 29355.7922 | 3757.8694 | 2.3355 | 130 | 3.92e-05 | 3282 | 1207.5405 | 728 | 0.04396 | 5.7148 | 1242 | 0.01 | 2576
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 2302 | FALSE | 2152.9343 | 2152.9343 | 1.3381 | 19 | 6.32e-05 | 2671 | 648.1357 | 1067 | 0.043905 | 0.8342 | 1243 | 0.01 | 2616
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 1378 | FALSE | 3084.1467 | 1447.5189 | 0.89964 | 25 | 0.00011131 | 1388 | 372.4728 | 1334 | 0.043839 | 1.096 | 1244 | 0.02 | 2452
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 39524 | FALSE | 24862.4083 | 8232.0089 | 5.1162 | 138 | 0.00038497 | 72 | 130.5694 | 1844 | 0.04372 | 6.0334 | 1245 | 0.03 | 2332
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 180398 | FALSE | 8946.0191 | 8946.0191 | 5.56 | 48 | 0.0002082 | 371 | 244.7887 | 1555 | 0.04366 | 2.0957 | 1246 | 24.5 | 278
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 47860 | TRUE | 6236.9476 | 466.0192 | 0.28963 | 54 | 7.37e-05 | 2372 | 319.7615 | 1416 | 0.043573 | 2.353 | 1247 | 0.02 | 2411
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 982992 | FALSE | 14390.2086 | 14390.2086 | 8.9436 | 52 | 4.61e-05 | 3136 | 911.2189 | 880 | 0.043526 | 2.2633 | 1248 |  | 3292
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 691436 | FALSE | 3576.8147 | 1680.7069 | 1.0446 | 28 | 0.00012089 | 1165 | 323.1464 | 1409 | 0.043449 | 1.2166 | 1249 |  | 3034
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 112804 | FALSE | 30691.3669 | 16512.5111 | 10.2626 | 67 | 9.75e-05 | 1701 | 651.0362 | 1064 | 0.043443 | 2.9107 | 1250 |  | 3111
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 1466 | FALSE | 33154.3349 | 33039.7041 | 20.5343 | 211 | 0.0001572 | 672 | 705.5165 | 1017 | 0.043245 | 9.1248 | 1251 | 0.07 | 1677
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 4814 | FALSE | 44262.9015 | 43433.1499 | 26.9939 | 117 | 0.00018022 | 512 | 271.8858 | 1490 | 0.043216 | 5.0562 | 1252 | 0.83 | 769
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 7902 | FALSE | 26218.9532 | 18823.9554 | 11.6992 | 143 | 0.00018704 | 461 | 146.5682 | 1787 | 0.043162 | 6.1722 | 1253 | 0.06 | 1892
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 78268 | FALSE | 15647.3206 | 15647.3206 | 9.7249 | 114 | 0.00016165 | 623 | 303.7186 | 1445 | 0.043133 | 4.9171 | 1254 | 73.54 | 60
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1212 | FALSE | 3797.0171 | 2977.1941 | 1.8503 | 25 | 0.00010853 | 1436 | 197.8244 | 1646 | 0.043056 | 1.0764 | 1255 | 28.71 | 247
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | CB | FALSE | 32987.4913 | 18947.9362 | 11.7762 | 226 | 0.00012255 | 1139 | 327.7945 | 1401 | 0.043018 | 9.722 | 1256 | 0.04 | 2117
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 98036 | FALSE | 14803.9566 | 14803.9566 | 9.2007 | 64 | 0.00012505 | 1098 | 294.291 | 1456 | 0.042868 | 2.7435 | 1257 | 0.04 | 2216
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 4630 | FALSE | 5558.0773 | 1729.1767 | 1.0747 | 42 | 7.78e-05 | 2266 | 548.6975 | 1148 | 0.042814 | 1.7982 | 1258 | 0.05 | 2061
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 166282 | FALSE | 38601.364 | 38601.364 | 23.9909 | 256 | 0.00012662 | 1069 | 425.8459 | 1266 | 0.042498 | 10.8796 | 1259 |  | 2757
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 1028 | FALSE | 28404.1063 | 28404.1063 | 17.6533 | 208 | 0.00012459 | 1106 | 555.8921 | 1139 | 0.042483 | 8.8364 | 1260 | 8.08 | 437
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 370932 | TRUE | 2172.9579 | 619.9296 | 0.38529 | 6 | 3.05e-05 | 3423 | 729.2934 | 991 | 0.042464 | 0.25478 | 1261 |  | 2828
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | CB | FALSE | 5303.193 | 2471.5392 | 1.5361 | 31 | 0.0001612 | 628 | 200.4454 | 1640 | 0.042406 | 1.3146 | 1262 | 0.01 | 2593
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 3113 | FALSE | 1919.7007 | 1919.7007 | 1.1931 | 9 | 5.18e-05 | 2999 | 970.9306 | 849 | 0.042389 | 0.3815 | 1263 | 12.05 | 376
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 968 | FALSE | 44551.6644 | 42969.09 | 26.7055 | 283 | 0.00010481 | 1533 | 381.6576 | 1318 | 0.042383 | 11.9944 | 1264 | 33.68 | 221
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 31322 | FALSE | 46269.6305 | 9420.014 | 5.8546 | 310 | 0.00011584 | 1276 | 412.2583 | 1282 | 0.04237 | 13.1348 | 1265 | 0.05 | 1992
332 | MESA 1101CB | 182821101 | MESA 1101 | CB | FALSE | 40952.4168 | 22299.6831 | 13.8593 | 230 | 5.12e-05 | 3009 | 603.2532 | 1096 | 0.042367 | 9.7444 | 1266 | 0.03 | 2242
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 1682 | TRUE | 14763.8266 | 326.6132 | 0.20299 | 112 | 0.00012357 | 1130 | 359.4666 | 1355 | 0.042324 | 4.7402 | 1267 | 0.48 | 906
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 12842 | FALSE | 27066.2595 | 25454.1408 | 15.8199 | 209 | 0.00018752 | 457 | 122.8933 | 1862 | 0.042311 | 8.8429 | 1268 | 24.93 | 275
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | MR299 | FALSE | 7955.2462 | 7955.2462 | 4.9442 | 58 | 9e-05 | 1910 | 452.8222 | 1243 | 0.042276 | 2.452 | 1269 | 0.4 | 946
5875 | MESA 11016113 | 182821101 | MESA 1101 | 6113 | FALSE | 15649.5972 | 2800.3205 | 1.7404 | 100 | 5.09e-05 | 3015 | 1017.9876 | 816 | 0.042268 | 4.2268 | 1270 | 0.86 | 762
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 6080 | FALSE | 55307.7628 | 55307.7628 | 34.374 | 322 | 0.00011497 | 1300 | 414.8336 | 1277 | 0.042249 | 13.6042 | 1271 | 0.17 | 1242
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 7124 | FALSE | 1081.3743 | 1081.3743 | 0.67208 | 5 | 0.0002308 | 283 | 190.3883 | 1663 | 0.042229 | 0.21114 | 1272 | 0.05 | 1941
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 641042 | FALSE | 10558.7861 | 2300.7684 | 1.4299 | 22 | 2.76e-05 | 3464 | 1880.7413 | 480 | 0.042194 | 0.92827 | 1273 |  | 3414
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 37132 | FALSE | 9343.2123 | 9343.2123 | 5.8068 | 50 | 0.00010209 | 1601 | 598.7122 | 1102 | 0.042173 | 2.1086 | 1274 |  | 3104
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 204480 | TRUE | 3182.9165 | 807.68 | 0.50198 | 28 | 0.00015459 | 699 | 296.133 | 1455 | 0.04209 | 1.1785 | 1275 |  | 3169
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 80620 | FALSE | 8949.87 | 1997.9252 | 1.2417 | 51 | 7.47e-05 | 2340 | 506.899 | 1194 | 0.04205 | 2.1446 | 1276 | 0.61 | 849
796 | MESA 1101M86 | 182821101 | MESA 1101 | M86 | FALSE | 33517.8054 | 20500.8716 | 12.7414 | 217 | 4.93e-05 | 3053 | 762.6869 | 961 | 0.041844 | 9.0801 | 1277 | 0.04 | 2086
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | Y10 | FALSE | 24460.4132 | 7788.8369 | 4.8408 | 122 | 3.66e-05 | 3322 | 632.6734 | 1076 | 0.041779 | 5.0971 | 1278 | 0.05 | 1949
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 4566 | FALSE | 28160.2778 | 20128.0864 | 12.5097 | 180 | 0.00011406 | 1319 | 393.9766 | 1301 | 0.041761 | 7.5169 | 1279 | 0.11 | 1420
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 1834 | FALSE | 38353.1383 | 37922.7084 | 23.5691 | 217 | 8.11e-05 | 2182 | 531.0758 | 1172 | 0.041581 | 9.0231 | 1280 | 0.17 | 1247
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 502 | FALSE | 65884.6114 | 60591.0346 | 37.6576 | 331 | 9.34e-05 | 1812 | 435.9933 | 1257 | 0.041554 | 13.7543 | 1281 | 0.21 | 1137
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 282 | FALSE | 8222.1189 | 4475.09 | 2.7813 | 62 | 8.35e-05 | 2115 | 543.5705 | 1155 | 0.041526 | 2.5746 | 1282 | 2.35 | 612
3229 | WISE 1102CB | 152271102 | WISE 1102 | CB | FALSE | 23260.435 | 22633.2401 | 14.0667 | 177 | 0.00014209 | 838 | 392.5466 | 1305 | 0.041442 | 7.3353 | 1283 | 0.11 | 1427
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 13512 | FALSE | 49131.7705 | 45791.8869 | 28.4598 | 345 | 0.00019634 | 412 | 199.5912 | 1642 | 0.041392 | 14.2801 | 1284 | 59.2 | 89
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 2586 | FALSE | 17615.5168 | 10070.6101 | 6.2589 | 91 | 4.85e-05 | 3075 | 1089.5717 | 778 | 0.041237 | 3.7526 | 1285 | 0.09 | 1567
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 556430 | FALSE | 26122.847 | 7792.8441 | 4.8433 | 122 | 1.64e-05 | 3574 | 2433.0686 | 354 | 0.041063 | 5.0096 | 1286 |  | 3028
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2236 | FALSE | 4120.4561 | 4120.4561 | 2.5609 | 11 | 0.00027956 | 156 | 116.7508 | 1889 | 0.040994 | 0.45093 | 1287 | 0.26 | 1069
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 1972 | FALSE | 34265.9827 | 34265.9827 | 21.2964 | 177 | 0.00011711 | 1243 | 377.3246 | 1326 | 0.040961 | 7.25 | 1288 | 73.04 | 64
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 99214 | FALSE | 3296.9506 | 2953.539 | 1.8356 | 21 | 0.00014798 | 764 | 541.677 | 1157 | 0.040838 | 0.85759 | 1289 | 0.04 | 2193
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | Y36 | FALSE | 73124.8896 | 60717.9561 | 37.7365 | 283 | 4.31e-05 | 3207 | 946.8115 | 863 | 0.0408 | 11.5464 | 1290 | 0.14 | 1321
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 166 | FALSE | 15936.7517 | 9969.1209 | 6.1958 | 110 | 0.00012238 | 1141 | 339.9187 | 1388 | 0.040759 | 4.4835 | 1291 | 0.03 | 2283
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 2100 | FALSE | 62879.0761 | 62879.0761 | 39.0796 | 403 | 0.00011682 | 1254 | 355.7448 | 1364 | 0.040696 | 16.4004 | 1292 | 0.14 | 1318
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 402 | FALSE | 37926.2925 | 37584.6138 | 23.359 | 151 | 0.0001662 | 581 | 293.7692 | 1458 | 0.040695 | 6.145 | 1293 | 0.07 | 1764
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 440856 | FALSE | 56881.4108 | 56011.6124 | 34.8114 | 349 | 6.32e-05 | 2669 | 673.5389 | 1040 | 0.040647 | 14.1857 | 1294 |  | 3143
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 6054 | FALSE | 11579.672 | 11579.672 | 7.1968 | 58 | 0.00029784 | 132 | 184.0031 | 1677 | 0.040642 | 2.3572 | 1295 | 0.09 | 1573
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 1204 | FALSE | 18353.2445 | 15255.8356 | 9.4816 | 124 | 0.00012563 | 1084 | 378.7617 | 1322 | 0.040535 | 5.0263 | 1296 | 0.06 | 1888
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 214 | FALSE | 18868.3768 | 18868.3768 | 11.7268 | 142 | 0.0001516 | 725 | 205.0666 | 1626 | 0.040503 | 5.7514 | 1297 | 44.57 | 157
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 76030 | FALSE | 10072.8355 | 8222.4339 | 5.1103 | 55 | 9.56e-05 | 1739 | 498.7327 | 1202 | 0.040366 | 2.2201 | 1298 | 0.02 | 2538
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 1976 | FALSE | 38264.4277 | 38264.4277 | 23.7815 | 217 | 7.45e-05 | 2346 | 572.7278 | 1128 | 0.040282 | 8.7412 | 1299 | 81.96 | 47
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | CB | FALSE | 29408.7196 | 16846.5197 | 10.4702 | 203 | 0.00013798 | 894 | 318.5868 | 1420 | 0.040232 | 8.1671 | 1300 | 0.05 | 1952
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 2106 | FALSE | 44861.5543 | 44861.5543 | 27.8816 | 264 | 0.00012115 | 1162 | 368.597 | 1341 | 0.040196 | 10.6117 | 1301 | 51.56 | 115
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 176050 | FALSE | 33994.9384 | 33994.9384 | 21.128 | 168 | 3.5e-05 | 3352 | 1021.4734 | 814 | 0.040157 | 6.7464 | 1302 |  | 2863
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 2053 | FALSE | 9238.0472 | 9238.0472 | 5.7415 | 74 | 7.83e-05 | 2252 | 578.9534 | 1125 | 0.040131 | 2.9697 | 1303 | 18.91 | 317
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | CB | FALSE | 14777.824 | 9580.003 | 5.954 | 90 | 0.00019434 | 422 | 250.1874 | 1539 | 0.040116 | 3.6104 | 1304 | 6.07 | 474
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 168892 | TRUE | 1078.2209 | 264.3207 | 0.16428 | 8 | 7.05e-05 | 2456 | 277.1976 | 1478 | 0.040099 | 0.32079 | 1305 |  | 3240
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 81390 | FALSE | 29957.8137 | 29957.8137 | 18.6189 | 208 | 0.00014065 | 861 | 348.4797 | 1374 | 0.039915 | 8.3022 | 1306 | 0.15 | 1288
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 504 | FALSE | 36253.1832 | 36253.1832 | 22.5315 | 205 | 0.00010544 | 1509 | 471.8115 | 1221 | 0.039748 | 8.1484 | 1307 | 47.4 | 133
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | CB | FALSE | 15315.8587 | 15315.8587 | 9.5189 | 44 | 0.00010811 | 1449 | 444.7581 | 1253 | 0.03956 | 1.7406 | 1308 | 15.25 | 349
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | MR748 | FALSE | 10026.1125 | 10026.1125 | 6.2313 | 86 | 9.59e-05 | 1731 | 353.7631 | 1368 | 0.039516 | 3.3984 | 1309 |  | 2749
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 989608 | FALSE | 3673.9458 | 1209.612 | 0.75178 | 6 | 0.00015502 | 693 | 503.7259 | 1195 | 0.039513 | 0.23708 | 1310 |  | 2877
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | V56 | FALSE | 15985.6627 | 15022.8264 | 9.3367 | 115 | 6.43e-05 | 2636 | 557.9025 | 1137 | 0.039442 | 4.5359 | 1311 | 0.1 | 1460
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 891 | FALSE | 5070.4899 | 5070.4899 | 3.1513 | 41 | 0.00012462 | 1104 | 268.5604 | 1501 | 0.03939 | 1.615 | 1312 | 2.7 | 588
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 116 | FALSE | 17433.6477 | 16625.8809 | 10.3331 | 112 | 0.00017861 | 515 | 262.5016 | 1515 | 0.039363 | 4.4087 | 1313 | 33.71 | 220
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 539938 | FALSE | 4460.237 | 4460.237 | 2.7721 | 26 | 0.00021663 | 334 | 141.7664 | 1805 | 0.039354 | 1.0232 | 1314 |  | 2851
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 37486 | FALSE | 12199.5088 | 11162.2658 | 6.9374 | 85 | 0.00018807 | 454 | 224.247 | 1597 | 0.039237 | 3.3351 | 1315 | 0 | 2623
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | CB | FALSE | 6932.7551 | 2351.3614 | 1.4614 | 47 | 0.00016197 | 622 | 176.7445 | 1692 | 0.039234 | 1.844 | 1316 | 0.02 | 2556
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | V02 | FALSE | 29266.1566 | 29266.1566 | 18.189 | 202 | 6.75e-05 | 2550 | 602.2374 | 1099 | 0.039184 | 7.9151 | 1317 | 0.29 | 1026
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 1656 | FALSE | 51859.3271 | 51859.3271 | 32.2308 | 208 | 0.00010206 | 1602 | 466.1612 | 1228 | 0.039176 | 8.1485 | 1318 | 0.07 | 1727
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 1302 | FALSE | 55353.0299 | 32333.7369 | 20.0955 | 317 | 6.35e-05 | 2662 | 792.5298 | 949 | 0.039053 | 12.3798 | 1319 | 0.08 | 1620
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | CB | FALSE | 30614.8922 | 9216.7854 | 5.7283 | 243 | 0.00023355 | 268 | 176.6871 | 1693 | 0.03873 | 9.4114 | 1320 | 0.04 | 2075
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 158138 | TRUE | 1490.1049 | 829.4376 | 0.5155 | 10 | 2.48e-05 | 3499 | 1008.6051 | 829 | 0.038704 | 0.38704 | 1321 |  | 3560
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | CB | FALSE | 12760.2493 | 12447.7538 | 7.7363 | 22 | 0.00012371 | 1125 | 391.2799 | 1306 | 0.038702 | 0.85144 | 1322 | 6.72 | 462
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 1260 | FALSE | 4901.8674 | 4807.0969 | 2.9876 | 36 | 0.00023996 | 246 | 168.4314 | 1724 | 0.038665 | 1.3919 | 1323 |  | 2682
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 580658 | FALSE | 16767.5085 | 15111.3604 | 9.3918 | 107 | 6.13e-05 | 2739 | 693.004 | 1027 | 0.038518 | 4.1214 | 1324 |  | 2759
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 91960 | FALSE | 11326.1042 | 10487.6883 | 6.5181 | 90 | 7.98e-05 | 2210 | 850.9359 | 913 | 0.038488 | 3.4639 | 1325 | 0.06 | 1880
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 2506 | FALSE | 20286.2385 | 20286.2385 | 12.608 | 89 | 0.00011139 | 1386 | 409.6677 | 1285 | 0.038425 | 3.4198 | 1326 | 0.12 | 1404
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 220 | FALSE | 15438.0154 | 15438.0154 | 9.5948 | 105 | 0.00011441 | 1309 | 311.3432 | 1429 | 0.038284 | 4.0198 | 1327 | 9.46 | 408
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | R90 | FALSE | 56951.1784 | 48580.6781 | 30.1931 | 259 | 6.32e-05 | 2672 | 705.4586 | 1018 | 0.038279 | 9.9144 | 1328 | 0.16 | 1275
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | Q06 | FALSE | 20064.3385 | 20064.3385 | 12.4701 | 154 | 5.95e-05 | 2790 | 680.2301 | 1036 | 0.038111 | 5.8691 | 1329 | 0.24 | 1099
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 68192 | FALSE | 10168.9958 | 4402.6894 | 2.7363 | 72 | 0.00012081 | 1168 | 238.5636 | 1570 | 0.037972 | 2.734 | 1330 | 0.05 | 1932
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 334 | FALSE | 14855.8514 | 9584.4637 | 5.9568 | 84 | 0.00013014 | 1009 | 232.8142 | 1581 | 0.037896 | 3.1833 | 1331 | 0.12 | 1407
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 37454 | FALSE | 19681.6074 | 10482.9729 | 6.5152 | 114 | 0.00010014 | 1640 | 404.6575 | 1292 | 0.037721 | 4.3002 | 1332 | 0.03 | 2377
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | V62 | FALSE | 11154.8311 | 11108.5021 | 6.904 | 50 | 5.6e-05 | 2890 | 671.7711 | 1042 | 0.037409 | 1.8704 | 1333 | 0.29 | 1023
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 78372 | FALSE | 27765.2096 | 26751.8084 | 16.6264 | 198 | 9.64e-05 | 1722 | 422.9319 | 1270 | 0.037304 | 7.3862 | 1334 | 0.18 | 1212
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | D514R | FALSE | 7698.3807 | 5032.0091 | 3.1274 | 73 | 0.00011281 | 1348 | 304.6429 | 1441 | 0.037278 | 2.7213 | 1335 | 0.15 | 1282
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | XR526 | FALSE | 8725.9018 | 3365.6589 | 2.0918 | 64 | 8.95e-05 | 1929 | 366.774 | 1343 | 0.037122 | 2.3758 | 1336 | 0.07 | 1699
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | Y42 | FALSE | 26985.4956 | 5628.4599 | 3.4981 | 127 | 5.22e-05 | 2990 | 480.936 | 1215 | 0.037118 | 4.714 | 1337 | 0.03 | 2346
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 168616 | FALSE | 13634.7639 | 5078.9905 | 3.1566 | 102 | 0.00012703 | 1064 | 319.4815 | 1417 | 0.03705 | 3.7791 | 1338 |  | 3144
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 104102 | FALSE | 5954.6843 | 5329.5584 | 3.3123 | 32 | 7.27e-05 | 2398 | 458.1953 | 1237 | 0.03704 | 1.1853 | 1339 |  | 2769
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | N46 | FALSE | 9360.6261 | 9360.6261 | 5.8177 | 29 | 8.79e-05 | 1983 | 551.9562 | 1142 | 0.036988 | 1.0726 | 1340 | 4.74 | 508
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 2426 | FALSE | 27934.4989 | 13782.7728 | 8.566 | 226 | 0.00017076 | 559 | 240.3744 | 1566 | 0.036874 | 8.3335 | 1341 | 0.09 | 1513
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 474 | FALSE | 29501.1448 | 29501.1448 | 18.3351 | 174 | 9.79e-05 | 1695 | 328.9251 | 1399 | 0.036813 | 6.4055 | 1342 | 75.79 | 56
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 2230 | FALSE | 17863.1589 | 10972.6709 | 6.8196 | 112 | 5.68e-05 | 2866 | 738.5033 | 984 | 0.036587 | 4.0978 | 1343 | 1.14 | 710
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 8902 | FALSE | 29281.8886 | 22787.1296 | 14.1623 | 145 | 9.48e-05 | 1771 | 290.9381 | 1462 | 0.036496 | 5.2919 | 1344 | 0.33 | 986
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 1606 | FALSE | 8892.9459 | 8892.9459 | 5.527 | 40 | 0.00014678 | 776 | 232.8508 | 1580 | 0.036482 | 1.4593 | 1345 | 0.01 | 2612
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 1238 | FALSE | 11344.0767 | 5824.674 | 3.6201 | 81 | 0.00010773 | 1458 | 597.355 | 1103 | 0.036431 | 2.9509 | 1346 | 1.29 | 689
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | CB | FALSE | 18045.0473 | 16189.7881 | 10.062 | 76 | 0.00014573 | 792 | 355.2175 | 1365 | 0.036334 | 2.7614 | 1347 | 0.04 | 2159
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 76498 | FALSE | 23942.9529 | 23942.9529 | 14.8806 | 119 | 0.00014996 | 736 | 219.4832 | 1606 | 0.036331 | 4.3234 | 1348 | 0.07 | 1718
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 870396 | FALSE | 4752.0973 | 1326.4884 | 0.82442 | 40 | 7.8e-05 | 2259 | 529.8735 | 1173 | 0.036327 | 1.4531 | 1349 |  | 3499
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 89606 | FALSE | 19260.5468 | 18716.1946 | 11.6322 | 100 | 0.00018082 | 506 | 280.3009 | 1471 | 0.036226 | 3.6226 | 1350 | 2.6 | 595
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | CB | FALSE | 36887.0266 | 35506.5152 | 22.0674 | 293 | 0.00013284 | 960 | 388.0347 | 1309 | 0.036175 | 10.5993 | 1351 | 0.18 | 1199
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 194 | FALSE | 13676.557 | 10907.7439 | 6.7792 | 62 | 5.77e-05 | 2843 | 536.066 | 1162 | 0.03614 | 2.2407 | 1352 | 0.13 | 1363
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | XR186 | FALSE | 25721.3505 | 4651.2538 | 2.8908 | 191 | 7.06e-05 | 2453 | 451.6726 | 1246 | 0.036035 | 6.8827 | 1353 | 0.23 | 1109
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 2392 | FALSE | 14284.0809 | 9811.7074 | 6.098 | 111 | 0.0001898 | 442 | 159.9243 | 1747 | 0.036 | 3.996 | 1354 |  | 2700
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | R94 | FALSE | 33827.9009 | 22380.6586 | 13.9097 | 179 | 5.53e-05 | 2903 | 687.195 | 1033 | 0.035946 | 6.4343 | 1355 | 0.08 | 1614
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 4701 | FALSE | 14095.9599 | 3388.7478 | 2.1061 | 65 | 6.27e-05 | 2693 | 533.9217 | 1166 | 0.035932 | 2.3356 | 1356 | 0.03 | 2301
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 1346 | FALSE | 49591.6622 | 49591.6622 | 30.8214 | 410 | 0.00012199 | 1148 | 241.2851 | 1564 | 0.035841 | 14.6948 | 1357 | 0.17 | 1232
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | R58 | TRUE | 19359.8744 | 870.4973 | 0.54102 | 130 | 8.61e-05 | 2033 | 466.191 | 1227 | 0.035811 | 4.6554 | 1358 | 0.03 | 2357
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 7062 | FALSE | 19664.1429 | 19664.1429 | 12.2213 | 53 | 5.22e-05 | 2986 | 685.2904 | 1034 | 0.035805 | 1.8977 | 1359 | 0.1 | 1452
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 17430 | FALSE | 2364.8217 | 2364.8217 | 1.4697 | 15 | 0.00011951 | 1195 | 247.4437 | 1547 | 0.035767 | 0.5365 | 1360 | 32.76 | 224
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 658898 | FALSE | 27632.4579 | 27632.4579 | 17.1737 | 151 | 0.00015549 | 689 | 248.309 | 1546 | 0.035763 | 5.4002 | 1361 | 57.88 | 94
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 1358 | FALSE | 15167.5785 | 13566.1241 | 8.4314 | 51 | 5.91e-05 | 2804 | 689.2289 | 1031 | 0.035574 | 1.8143 | 1362 | 0.06 | 1890
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 7522 | FALSE | 108391.3301 | 108391.3301 | 67.3656 | 745 | 0.00012077 | 1170 | 356.6073 | 1360 | 0.035529 | 26.4689 | 1363 | 0.39 | 959
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 97300 | FALSE | 5161.3802 | 5161.3802 | 3.2078 | 32 | 0.00052613 | 28 | 106.2466 | 1924 | 0.035439 | 1.1341 | 1364 | 0 | 2624
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | MR284 | FALSE | 24162.974 | 23633.8874 | 14.6886 | 134 | 7.46e-05 | 2342 | 581.0664 | 1123 | 0.035373 | 4.7399 | 1365 | 0.73 | 795
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 70288 | FALSE | 18879.7984 | 18879.7984 | 11.7339 | 94 | 0.00019389 | 426 | 228.6007 | 1590 | 0.035369 | 3.3247 | 1366 | 36.18 | 207
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | CB | FALSE | 9981.732 | 6230.9216 | 3.8725 | 51 | 2.74e-05 | 3466 | 650.8554 | 1065 | 0.03535 | 1.8029 | 1367 |  | 2870
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 666 | FALSE | 3872.5577 | 3872.5577 | 2.4068 | 12 | 9.29e-05 | 1825 | 378.2419 | 1323 | 0.035311 | 0.42373 | 1368 | 4.95 | 500
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 548420 | FALSE | 8380.7958 | 8369.7684 | 5.2018 | 54 | 8.6e-05 | 2034 | 589.6218 | 1114 | 0.035261 | 1.9041 | 1369 |  | 3251
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 55398 | FALSE | 18355.8501 | 5879.4418 | 3.6541 | 82 | 9.93e-05 | 1661 | 371.6607 | 1336 | 0.035221 | 2.8881 | 1370 | 0.05 | 2019
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 48000 | FALSE | 21345.6496 | 15284.0145 | 9.4991 | 115 | 8.69e-05 | 2015 | 388.2741 | 1308 | 0.035167 | 4.0442 | 1371 | 0.07 | 1767
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | CB | TRUE | 1663.8056 | 978.5043 | 0.60814 | 7 | 0.00029336 | 136 | 117.5975 | 1884 | 0.035133 | 0.24593 | 1372 | 0.22 | 1130
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 41650 | FALSE | 26091.6846 | 1862.3816 | 1.1575 | 152 | 9.01e-05 | 1906 | 368.6652 | 1340 | 0.035126 | 5.3392 | 1373 | 1.15 | 706
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 2052 | FALSE | 7781.6967 | 7781.6967 | 4.8364 | 53 | 0.00010975 | 1416 | 342.2139 | 1385 | 0.034981 | 1.854 | 1374 | 16.17 | 340
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 510 | FALSE | 13083.2788 | 6767.6989 | 4.2062 | 101 | 7.55e-05 | 2323 | 619.5024 | 1082 | 0.03495 | 3.5299 | 1375 | 0.06 | 1875
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 8972 | FALSE | 10000.1577 | 10000.1577 | 6.2151 | 60 | 0.00015146 | 726 | 262.3952 | 1516 | 0.034933 | 2.096 | 1376 | 24.19 | 280
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 8842 | TRUE | 4786.8365 | 241.1115 | 0.14985 | 42 | 6.99e-05 | 2476 | 340.0317 | 1387 | 0.03478 | 1.4608 | 1377 | 1.42 | 678
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 48894 | FALSE | 16156.7591 | 14293.1803 | 8.8833 | 119 | 0.00018242 | 493 | 147.0551 | 1786 | 0.034658 | 4.1244 | 1378 | 4.42 | 518
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 2058 | FALSE | 34315.2065 | 34315.2065 | 21.327 | 256 | 0.00016588 | 583 | 212.3054 | 1613 | 0.034582 | 8.853 | 1379 | 0.1 | 1472
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 523764 | TRUE | 581.2133 | 177.5745 | 0.11036 | 5 | 5.35e-05 | 2949 | 454.5614 | 1241 | 0.034478 | 0.17239 | 1380 |  | 3531
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | MR196 | FALSE | 21187.4678 | 6333.1478 | 3.9361 | 96 | 5.26e-05 | 2979 | 626.9753 | 1078 | 0.034417 | 3.304 | 1381 | 0.62 | 842
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 93062 | FALSE | 13326.2559 | 13326.2559 | 8.2823 | 84 | 5.38e-05 | 2946 | 519.6534 | 1183 | 0.034301 | 2.8813 | 1382 | 47.16 | 137
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 650772 | FALSE | 4368.3364 | 1261.3702 | 0.78395 | 10 | 8.43e-05 | 2083 | 361.8664 | 1350 | 0.03426 | 0.3426 | 1383 |  | 3534
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | CB | FALSE | 36721.9242 | 31128.549 | 19.3465 | 268 | 0.00025192 | 213 | 162.0895 | 1742 | 0.034245 | 9.1777 | 1384 | 0.18 | 1200
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | CB | FALSE | 3490.2509 | 3490.2509 | 2.1692 | 23 | 0.00020948 | 361 | 222.197 | 1600 | 0.034029 | 0.78267 | 1385 | 9.67 | 405
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 94468 | FALSE | 2757.0604 | 2757.0604 | 1.7135 | 21 | 6.66e-05 | 2567 | 514.9233 | 1187 | 0.033993 | 0.71385 | 1386 |  | 3480
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 1552 | FALSE | 42573.1939 | 23841.5992 | 14.8177 | 221 | 3.53e-05 | 3346 | 839.4452 | 917 | 0.033912 | 7.4946 | 1387 | 0.02 | 2427
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | CB | TRUE | 10585.951 | 124.2488 | 0.077221 | 65 | 0.00011177 | 1373 | 315.2576 | 1425 | 0.033863 | 2.2011 | 1388 | 0.02 | 2451
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 477952 | TRUE | 2593.1423 | 282.8465 | 0.17579 | 14 | 3.36e-05 | 3374 | 2064.1113 | 439 | 0.033843 | 0.47381 | 1389 |  | 3390
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 9752 | FALSE | 6185.1828 | 6137.4536 | 3.8145 | 41 | 8.52e-05 | 2053 | 359.3768 | 1357 | 0.033837 | 1.3873 | 1390 | 0.08 | 1592
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6014 | FALSE | 11167.2532 | 11167.2532 | 6.9405 | 73 | 0.00012645 | 1075 | 322.1745 | 1410 | 0.033829 | 2.4695 | 1391 | 0.11 | 1416
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 1451 | FALSE | 14799.0552 | 9963.2757 | 6.1922 | 61 | 7.78e-05 | 2264 | 590.7109 | 1112 | 0.03381 | 2.0624 | 1392 | 0.07 | 1693
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 5076 | FALSE | 14477.3636 | 12059.1468 | 7.4948 | 67 | 0.00010771 | 1459 | 265.797 | 1508 | 0.033758 | 2.2618 | 1393 | 0.04 | 2127
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 102734 | TRUE | 954.1374 | 954.1374 | 0.593 | 7 | 8.98e-05 | 1919 | 197.0875 | 1650 | 0.033754 | 0.23628 | 1394 |  | 3280
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 11790 | TRUE | 22.8988 | 22.8988 | 0.014232 | 1 | 0.00070892 | 7 | 47.5828 | 2227 | 0.033732 | 0.033732 | 1395 | 0.2 | 1164
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 342498 | TRUE | 1151.7336 | 49.0072 | 0.030458 | 9 | 7.99e-05 | 2207 | 500.2762 | 1198 | 0.033722 | 0.3035 | 1396 |  | 3521
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 495270 | TRUE | 13307.7021 | 863.3194 | 0.53656 | 50 | 9.08e-05 | 1888 | 589.9667 | 1113 | 0.033688 | 1.6844 | 1397 |  | 2953
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 600 | FALSE | 11716.5391 | 5966.5276 | 3.7082 | 107 | 8.55e-05 | 2040 | 380.66 | 1319 | 0.033514 | 3.586 | 1398 | 2.36 | 611
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 2414 | FALSE | 23793.415 | 23793.415 | 14.7877 | 168 | 0.00014567 | 794 | 312.3629 | 1427 | 0.033489 | 5.6261 | 1399 | 0.1 | 1503
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 1730 | FALSE | 13645.4759 | 13645.4759 | 8.4807 | 73 | 0.00014065 | 860 | 278.461 | 1475 | 0.033438 | 2.441 | 1400 | 45.96 | 146
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1334 | FALSE | 25612.9912 | 2886.1165 | 1.7937 | 155 | 6.09e-05 | 2753 | 682.7098 | 1035 | 0.033359 | 5.1706 | 1401 | 1.21 | 700
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | H82 | FALSE | 58651.4755 | 52489.3402 | 32.6223 | 262 | 9.34e-05 | 1811 | 388.9088 | 1307 | 0.033242 | 8.7095 | 1402 | 0.77 | 782
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 9012 | FALSE | 25166.2142 | 25166.2142 | 15.6409 | 176 | 0.00013267 | 966 | 372.3651 | 1335 | 0.033219 | 5.8466 | 1403 | 0.42 | 934
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 807000 | FALSE | 1709.8584 | 1354.2941 | 0.8417 | 7 | 3.23e-05 | 3394 | 880.4035 | 891 | 0.033203 | 0.23242 | 1404 |  | 3594
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 14028 | FALSE | 12751.8037 | 6133.5417 | 3.812 | 103 | 0.00010822 | 1447 | 214.1406 | 1611 | 0.033074 | 3.4066 | 1405 | 0.04 | 2224
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 1044 | FALSE | 9889.843 | 9889.843 | 6.1466 | 17 | 0.00010748 | 1465 | 324.5037 | 1407 | 0.033036 | 0.56161 | 1406 | 18.93 | 316
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1040 | FALSE | 9753.1063 | 1682.9824 | 1.046 | 62 | 0.00011564 | 1281 | 448.3969 | 1250 | 0.032999 | 2.0459 | 1407 | 0.73 | 796
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 2310 | FALSE | 4180.455 | 1304.6994 | 0.81088 | 34 | 0.00013671 | 911 | 509.3332 | 1192 | 0.032911 | 1.119 | 1408 | 0.05 | 1962
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | CB | FALSE | 30214.013 | 30214.013 | 18.7781 | 154 | 0.00013214 | 980 | 326.6135 | 1403 | 0.03289 | 5.065 | 1409 | 0.04 | 2085
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 12832 | FALSE | 24421.2649 | 23234.3604 | 14.4402 | 166 | 0.00017093 | 557 | 211.8635 | 1615 | 0.032787 | 5.4427 | 1410 | 28.99 | 245
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 599142 | TRUE | 3668.6338 | 573.3105 | 0.35631 | 19 | 2.29e-05 | 3512 | 2022.5531 | 452 | 0.03274 | 0.62205 | 1411 |  | 3488
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 1812 | FALSE | 30912.6745 | 30912.6745 | 19.2124 | 234 | 0.0001396 | 878 | 157.2117 | 1758 | 0.032657 | 7.6418 | 1412 | 0.91 | 748
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 113634 | FALSE | 13932.988 | 2941.0752 | 1.8279 | 76 | 7.48e-05 | 2338 | 364.1214 | 1346 | 0.032654 | 2.4817 | 1413 |  | 3229
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | CB | FALSE | 4270.3268 | 4270.3268 | 2.654 | 7 | 0.000239 | 249 | 194.5881 | 1655 | 0.032515 | 0.22761 | 1414 | 0.03 | 2354
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 2224 | FALSE | 16910.6519 | 16910.6519 | 10.51 | 123 | 0.00022231 | 310 | 204.3067 | 1631 | 0.032512 | 3.999 | 1415 | 31.55 | 229
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 37462 | FALSE | 7845.6326 | 3795.803 | 2.3591 | 63 | 0.00014083 | 857 | 230.0252 | 1586 | 0.032457 | 2.0448 | 1416 | 0.04 | 2166
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 894006 | TRUE | 1042.8451 | 627.9545 | 0.39028 | 8 | 7.15e-05 | 2432 | 670.4008 | 1043 | 0.03239 | 0.25912 | 1417 |  | 3282
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | V14 | FALSE | 13117.1277 | 13103.4117 | 8.1438 | 69 | 5.32e-05 | 2961 | 462.6018 | 1233 | 0.03238 | 2.2342 | 1418 | 0.07 | 1714
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 8412 | FALSE | 31508.6751 | 31508.6751 | 19.5828 | 201 | 0.00012406 | 1118 | 308.2082 | 1435 | 0.032352 | 6.5027 | 1419 | 0.24 | 1093
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 7002 | FALSE | 29669.7133 | 13447.6997 | 8.3578 | 117 | 6.58e-05 | 2591 | 548.8506 | 1147 | 0.032323 | 3.7818 | 1420 | 0.03 | 2407
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 10254 | FALSE | 3449.8351 | 3449.8351 | 2.1441 | 11 | 0.00025218 | 212 | 138.3979 | 1814 | 0.03232 | 0.35552 | 1421 | 0.29 | 1030
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | CB | FALSE | 6578.3972 | 6578.3972 | 4.0885 | 51 | 0.00035059 | 89 | 89.0767 | 2007 | 0.032289 | 1.6467 | 1422 | 4 | 530
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 907698 | FALSE | 3034.3117 | 2466.4183 | 1.5329 | 14 | 0.00012445 | 1111 | 261.4537 | 1520 | 0.03225 | 0.4515 | 1423 |  | 3140
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 2500 | FALSE | 11167.0911 | 10490.7768 | 6.5201 | 74 | 0.00015128 | 727 | 218.7989 | 1608 | 0.032243 | 2.3859 | 1424 | 57.37 | 96
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 1020 | FALSE | 46299.321 | 46299.321 | 28.7752 | 311 | 9.63e-05 | 1725 | 368.887 | 1339 | 0.032187 | 10.0103 | 1425 | 69 | 71
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 2006 | FALSE | 14941.7424 | 13398.0902 | 8.327 | 75 | 0.00034661 | 94 | 97.9891 | 1968 | 0.03216 | 2.412 | 1426 | 0.09 | 1508
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 760730 | TRUE | 4317.2275 | 964.21 | 0.59926 | 17 | 7.57e-05 | 2318 | 407.7093 | 1289 | 0.032096 | 0.54562 | 1427 |  | 3530
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 5462 | FALSE | 37447.0905 | 37447.0905 | 23.2735 | 248 | 0.00016384 | 602 | 227.1186 | 1593 | 0.032082 | 7.9564 | 1428 | 37.76 | 199
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 63170 | FALSE | 21717.2784 | 20031.3406 | 12.4496 | 86 | 0.00032558 | 106 | 126.7281 | 1853 | 0.031951 | 2.7478 | 1429 | 0.11 | 1410
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6917 | FALSE | 11229.1017 | 11229.1017 | 6.9789 | 58 | 0.00011705 | 1246 | 334.9674 | 1393 | 0.031941 | 1.8526 | 1430 | 28.69 | 248
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 887932 | FALSE | 7830.582 | 2732.0868 | 1.698 | 34 | 3.8e-05 | 3299 | 1172.2774 | 745 | 0.031896 | 1.0845 | 1431 |  | 2945
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 619542 | FALSE | 2424.259 | 2408.2569 | 1.4967 | 21 | 0.00013244 | 972 | 252.7945 | 1536 | 0.031874 | 0.66935 | 1432 |  | 3241
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 1130 | FALSE | 32234.9294 | 32234.9294 | 20.0341 | 231 | 8.12e-05 | 2177 | 401.3828 | 1295 | 0.031834 | 7.3538 | 1433 | 0.19 | 1198
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 37238 | FALSE | 18384.2813 | 18384.2813 | 11.4259 | 79 | 9.08e-05 | 1890 | 274.1817 | 1485 | 0.031693 | 2.5038 | 1434 | 39.57 | 188
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 10610 | FALSE | 2196.7777 | 2196.7777 | 1.3653 | 22 | 7.41e-05 | 2354 | 439.5957 | 1256 | 0.031595 | 0.6951 | 1435 | 0.3 | 1012
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 85870 | FALSE | 27055.9571 | 18409.1169 | 11.4413 | 109 | 5.9e-05 | 2807 | 581.2408 | 1122 | 0.031502 | 3.4337 | 1436 | 0.05 | 1923
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 478 | FALSE | 32233.0286 | 13396.6859 | 8.3261 | 213 | 9.8e-05 | 1693 | 387.6512 | 1310 | 0.031296 | 6.6661 | 1437 | 6.33 | 468
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | CB | TRUE | 9680.979 | 75.4379 | 0.046885 | 69 | 8.45e-05 | 2078 | 195.8633 | 1653 | 0.031266 | 2.1574 | 1438 | 3.69 | 536
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 463260 | TRUE | 886.169 | 873.7132 | 0.54302 | 6 | 9.59e-05 | 1730 | 333.1332 | 1394 | 0.031168 | 0.18701 | 1439 |  | 3601
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | CB | FALSE | 17669.2412 | 14555.9213 | 9.0466 | 119 | 0.00013143 | 990 | 316.505 | 1422 | 0.031137 | 3.7053 | 1440 | 0.06 | 1894
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 2556 | FALSE | 10719.4797 | 10719.4797 | 6.6622 | 41 | 0.00022017 | 320 | 170.5273 | 1713 | 0.031032 | 1.2723 | 1441 | 40.37 | 184
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | CB | FALSE | 7207.9497 | 1811.9234 | 1.1261 | 57 | 3.62e-05 | 3330 | 275.7036 | 1484 | 0.03103 | 1.7687 | 1442 | 0.02 | 2494
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | M98 | FALSE | 15843.0204 | 12614.6664 | 7.8401 | 56 | 2.66e-05 | 3477 | 870.0926 | 898 | 0.030988 | 1.7353 | 1443 | 0.06 | 1829
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 9265 | FALSE | 8915.672 | 8915.672 | 5.5411 | 45 | 9.8e-05 | 1691 | 342.4629 | 1384 | 0.03098 | 1.3941 | 1444 | 0.08 | 1605
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 524356 | FALSE | 4107.6805 | 2088.1166 | 1.2978 | 29 | 0.00010421 | 1547 | 511.0846 | 1190 | 0.030872 | 0.89528 | 1445 |  | 2991
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 806 | FALSE | 18143.3916 | 18143.3916 | 11.2762 | 65 | 0.00012168 | 1154 | 338.7274 | 1390 | 0.030867 | 2.0063 | 1446 | 48.53 | 127
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 1750 | FALSE | 13589.0424 | 13584.4704 | 8.4428 | 62 | 0.00032404 | 108 | 98.8868 | 1959 | 0.030822 | 1.911 | 1447 | 0.13 | 1338
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 5380 | FALSE | 22971.0374 | 22971.0374 | 14.2766 | 143 | 7.83e-05 | 2250 | 414.5903 | 1278 | 0.030806 | 4.4053 | 1448 | 0.46 | 911
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 578 | FALSE | 29556.6676 | 27517.4977 | 17.1022 | 170 | 8.76e-05 | 1997 | 393.466 | 1303 | 0.030756 | 5.2285 | 1449 | 37.08 | 203
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 806 | FALSE | 4898.4533 | 4898.4533 | 3.0444 | 17 | 0.00027974 | 154 | 135.7877 | 1828 | 0.030667 | 0.52134 | 1450 | 0.55 | 868
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 657038 | FALSE | 16275.5331 | 4182.6167 | 2.5995 | 72 | 4.91e-05 | 3062 | 415.5682 | 1276 | 0.030657 | 2.2073 | 1451 |  | 3078
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 467046 | FALSE | 34550.7467 | 24654.328 | 15.3228 | 266 | 0.00018345 | 482 | 166.8005 | 1729 | 0.030581 | 8.1346 | 1452 |  | 2816
4703 | WISE 1101CB | 152271101 | WISE 1101 | CB | FALSE | 14435.5526 | 7662.7202 | 4.7624 | 112 | 0.00015887 | 652 | 243.3221 | 1558 | 0.030561 | 3.4229 | 1453 | 0.05 | 2032
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 13481 | TRUE | 1739.6965 | 0 | 0 | 14 | 0.0001142 | 1314 | 13.6321 | 2559 | 0.0016289 | 0.022805 | 2534 | 0.03 | 2380
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 1646 | FALSE | 38843.3191 | 38535.0265 | 23.9497 | 215 | 6.2e-05 | 2718 | 560.4541 | 1133 | 0.030417 | 6.5396 | 1455 | 13.62 | 364
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | CB | TRUE | 200.8618 | 200.8618 | 0.12484 | 2 | 9.04e-05 | 1899 | 309.1042 | 1433 | 0.030413 | 0.060827 | 1456 | 0.72 | 797
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 11212 | FALSE | 35943.9954 | 35943.9954 | 22.3393 | 155 | 8.85e-05 | 1974 | 349.3135 | 1372 | 0.030264 | 4.691 | 1457 | 0.06 | 1822
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | A02 | FALSE | 41006.5742 | 41006.5742 | 25.4858 | 253 | 5.86e-05 | 2818 | 542.8818 | 1156 | 0.030233 | 7.649 | 1458 | 2.41 | 606
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 60090 | FALSE | 10545.4489 | 10545.4489 | 6.554 | 62 | 0.00016362 | 604 | 206.0102 | 1623 | 0.030171 | 1.8706 | 1459 | 0.06 | 1906
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 713592 | FALSE | 16948.2792 | 16715.2405 | 10.3886 | 152 | 6.25e-05 | 2704 | 490.9201 | 1208 | 0.030005 | 4.5608 | 1460 |  | 2997
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | CB | FALSE | 9227.3447 | 4545.9264 | 2.8253 | 60 | 7.48e-05 | 2336 | 409.6387 | 1286 | 0.029933 | 1.7959 | 1461 | 5.21 | 494
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 19552 | FALSE | 34339.9089 | 34339.9089 | 21.3424 | 238 | 0.0001768 | 520 | 361.0634 | 1351 | 0.029928 | 7.123 | 1462 | 0.45 | 915
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 534019 | FALSE | 1193.5001 | 1147.9573 | 0.71346 | 5 | 0.0001111 | 1391 | 269.5494 | 1499 | 0.029893 | 0.14947 | 1463 |  | 3519
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 3174 | FALSE | 35498.7494 | 29750.1978 | 18.4899 | 162 | 0.00035838 | 83 | 115.2454 | 1894 | 0.029875 | 4.8397 | 1464 | 0.13 | 1336
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 8040 | FALSE | 41434.2849 | 11785.9847 | 7.325 | 145 | 5.91e-05 | 2803 | 495.056 | 1206 | 0.02987 | 4.3312 | 1465 | 0.01 | 2600
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 8971 | FALSE | 12716.2408 | 12716.2408 | 7.9032 | 72 | 0.00010598 | 1496 | 268.1837 | 1504 | 0.029749 | 2.1419 | 1466 |  | 3293
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 936674 | FALSE | 6354.8382 | 1063.5848 | 0.66102 | 56 | 8.26e-05 | 2141 | 408.407 | 1288 | 0.029729 | 1.6648 | 1467 |  | 2866
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 41392 | FALSE | 23588.435 | 7062.7077 | 4.3895 | 171 | 0.00011368 | 1327 | 289.7407 | 1465 | 0.029696 | 5.078 | 1468 | 3.21 | 554
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 3783 | TRUE | 16200.7401 | 142.5109 | 0.088571 | 96 | 9.23e-05 | 1834 | 351.5102 | 1370 | 0.029685 | 2.8498 | 1469 |  | 3259
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 46860 | FALSE | 5362.8484 | 1149.598 | 0.71448 | 15 | 0.0001367 | 912 | 145.8531 | 1790 | 0.029648 | 0.44471 | 1470 | 0.03 | 2247
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 6064 | FALSE | 31643.7207 | 30550.9365 | 18.9875 | 199 | 7.57e-05 | 2315 | 471.6661 | 1222 | 0.029564 | 5.8832 | 1471 | 0.2 | 1167
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | Y18 | FALSE | 12113.6185 | 7856.8971 | 4.8831 | 60 | 4.18e-05 | 3229 | 658.0763 | 1056 | 0.029555 | 1.7733 | 1472 | 0.08 | 1647
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 13450 | FALSE | 7994.7686 | 1509.284 | 0.93803 | 42 | 7.64e-05 | 2295 | 360.8067 | 1352 | 0.029532 | 1.2403 | 1473 |  | 2741
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 2936 | FALSE | 53378.6829 | 53378.6829 | 33.1751 | 249 | 0.00014373 | 817 | 191.382 | 1659 | 0.029513 | 7.3486 | 1474 | 0.15 | 1299
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 688780 | TRUE | 2079.7156 | 922.8958 | 0.57358 | 14 | 0.00019275 | 430 | 228.6665 | 1589 | 0.029456 | 0.41239 | 1475 |  | 2839
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 1510 | FALSE | 21171.8285 | 21171.8285 | 13.1584 | 107 | 0.00046286 | 44 | 80.26 | 2047 | 0.029417 | 3.1476 | 1476 | 0.13 | 1358
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 634 | FALSE | 27022.9414 | 18046.5458 | 11.216 | 178 | 0.00012722 | 1060 | 223.109 | 1599 | 0.029373 | 5.2284 | 1477 | 0.7 | 808
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 522 | FALSE | 17218.2435 | 12875.7792 | 8.0023 | 109 | 8.41e-05 | 2091 | 350.0759 | 1371 | 0.029361 | 3.2003 | 1478 | 0.06 | 1861
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 75686 | FALSE | 8282.1233 | 7450.4021 | 4.6305 | 31 | 0.00011699 | 1250 | 264.1333 | 1511 | 0.029281 | 0.90772 | 1479 | 0.04 | 2067
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | CB | FALSE | 7605.9803 | 7605.9803 | 4.7271 | 37 | 0.00011114 | 1390 | 255.7947 | 1533 | 0.029281 | 1.0834 | 1480 | 0.23 | 1113
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | CB | FALSE | 9497.7631 | 9497.7631 | 5.9029 | 69 | 0.00021208 | 351 | 141.7322 | 1806 | 0.029248 | 2.0181 | 1481 | 0.04 | 2126
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 91810 | FALSE | 47379.4324 | 47379.4324 | 29.4465 | 296 | 0.00010548 | 1507 | 312.0704 | 1428 | 0.029203 | 8.6442 | 1482 | 44.17 | 160
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 331444 | FALSE | 7051.4008 | 3579.9474 | 2.225 | 44 | 0.00010727 | 1466 | 260.3745 | 1523 | 0.029048 | 1.2781 | 1483 |  | 3273
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | CB | FALSE | 31622.6384 | 31622.6384 | 19.6536 | 162 | 0.00011093 | 1392 | 299.4116 | 1448 | 0.029034 | 4.7034 | 1484 | 78.02 | 52
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 899734 | FALSE | 5471.5337 | 5471.5337 | 3.4006 | 36 | 0.00048435 | 35 | 103.6873 | 1931 | 0.028754 | 1.0351 | 1485 |  | 3329
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | CB | FALSE | 10872.4032 | 5779.9667 | 3.5923 | 75 | 4.96e-05 | 3048 | 502.0965 | 1196 | 0.028742 | 2.1556 | 1486 | 0.7 | 805
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 684564 | TRUE | 4176.2924 | 443.3906 | 0.27557 | 28 | 6.66e-05 | 2566 | 311.0083 | 1430 | 0.02858 | 0.80024 | 1487 |  | 3243
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 978364 | FALSE | 4026.4295 | 1557.6573 | 0.96809 | 36 | 4.89e-05 | 3067 | 319.1206 | 1419 | 0.028543 | 1.0276 | 1488 |  | 2850
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | CB | FALSE | 41366.5121 | 1446.4903 | 0.899 | 288 | 7.26e-05 | 2400 | 424.917 | 1268 | 0.028499 | 8.2077 | 1489 | 0.17 | 1224
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 3702 | FALSE | 7962.9538 | 7864.1375 | 4.8876 | 35 | 5.58e-05 | 2896 | 546.4749 | 1152 | 0.028477 | 0.99668 | 1490 | 0.03 | 2383
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | R86 | FALSE | 23197.4547 | 17574.2947 | 10.9225 | 160 | 5.76e-05 | 2847 | 490.6496 | 1209 | 0.028407 | 4.5451 | 1491 | 0.08 | 1637
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 711900 | FALSE | 20250.2667 | 14456.1594 | 8.9846 | 116 | 7.69e-05 | 2288 | 301.111 | 1446 | 0.028347 | 3.2883 | 1492 | 0.24 | 1097
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 289662 | TRUE | 1302.884 | 533.3553 | 0.33148 | 11 | 2.78e-05 | 3461 | 483.4846 | 1212 | 0.028227 | 0.31049 | 1493 |  | 3149
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 648 | FALSE | 26216.5179 | 6117.4965 | 3.802 | 187 | 9.69e-05 | 1716 | 305.0125 | 1439 | 0.028161 | 5.2662 | 1494 | 2.81 | 578
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 1618 | FALSE | 9746.1598 | 9746.1598 | 6.0573 | 15 | 0.00010839 | 1441 | 237.7895 | 1574 | 0.028087 | 0.42131 | 1495 | 0 | 2632
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | CB | TRUE | 1951.9603 | 159.1645 | 0.098921 | 22 | 5.91e-05 | 2802 | 153.2438 | 1767 | 0.028017 | 0.61638 | 1496 | 0.28 | 1038
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 6014 | FALSE | 8043.0218 | 8043.0218 | 4.9988 | 50 | 0.000124 | 1120 | 242.0554 | 1562 | 0.027926 | 1.3963 | 1497 | 0.1 | 1478
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | MR298 | FALSE | 8473.8006 | 8244.1822 | 5.1238 | 39 | 7.07e-05 | 2452 | 586.0273 | 1117 | 0.027925 | 1.0891 | 1498 | 0.26 | 1070
739 | COTATI 1105CB | 42271105 | COTATI 1105 | CB | FALSE | 4309.0759 | 4309.0759 | 2.6781 | 35 | 0.00011326 | 1338 | 266.28 | 1506 | 0.027854 | 0.97488 | 1499 | 11.62 | 384
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | Y22 | FALSE | 40867.3286 | 16721.66 | 10.3926 | 178 | 4.38e-05 | 3193 | 413.6922 | 1281 | 0.027743 | 4.9383 | 1500 | 0.04 | 2132
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 76842 | FALSE | 9156.7064 | 9156.7064 | 5.6909 | 33 | 0.00012448 | 1109 | 276.9184 | 1479 | 0.027724 | 0.91488 | 1501 | 0.08 | 1635
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | A66 | FALSE | 54313.8381 | 54313.8381 | 33.7563 | 429 | 6.15e-05 | 2734 | 473.9679 | 1218 | 0.027639 | 11.8573 | 1502 | 0.27 | 1052
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | CB | TRUE | 10934.0811 | 0 | 0 | 68 | 0.00011128 | 1389 | 204.9489 | 1629 | 0.027594 | 1.8764 | 1503 | 0.03 | 2305
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | V82 | FALSE | 22558.9801 | 14130.1148 | 8.7819 | 174 | 7.49e-05 | 2332 | 326.0495 | 1404 | 0.027572 | 4.7975 | 1504 | 0.06 | 1792
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 7502 | FALSE | 36933.3454 | 36933.3454 | 22.9542 | 267 | 0.00011381 | 1324 | 264.2675 | 1509 | 0.027532 | 7.351 | 1505 | 38.11 | 197
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | V12 | FALSE | 33868.1694 | 33868.1694 | 21.0492 | 127 | 8.41e-05 | 2090 | 399.923 | 1297 | 0.027414 | 3.4815 | 1506 | 0.24 | 1100
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 10986 | FALSE | 31785.0255 | 14988.5933 | 9.3155 | 180 | 9.44e-05 | 1785 | 282.1821 | 1470 | 0.027411 | 4.9339 | 1507 | 0.19 | 1190
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 682 | FALSE | 23844.5349 | 23844.5349 | 14.8195 | 97 | 0.00016349 | 605 | 167.4124 | 1727 | 0.027282 | 2.6464 | 1508 | 2.58 | 596
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 3010 | FALSE | 50085.8598 | 50061.44 | 31.1134 | 229 | 6.26e-05 | 2699 | 457.2691 | 1239 | 0.027281 | 6.2474 | 1509 | 0.11 | 1434
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 556 | TRUE | 12171.5187 | 285.9131 | 0.1777 | 90 | 6.1e-05 | 2748 | 422.9587 | 1269 | 0.027227 | 2.4505 | 1510 | 1.68 | 652
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 6074 | FALSE | 5923.6574 | 5923.6574 | 3.6816 | 34 | 0.00013034 | 1003 | 156.7867 | 1759 | 0.027132 | 0.92248 | 1511 | 1.63 | 660
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 818874 | FALSE | 10865.8424 | 9148.5425 | 5.6859 | 42 | 8.81e-05 | 1981 | 323.2606 | 1408 | 0.02708 | 1.1374 | 1512 |  | 3177
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 869408 | TRUE | 710.7103 | 710.7103 | 0.44171 | 6 | 0.00016423 | 597 | 150.5967 | 1775 | 0.027041 | 0.16225 | 1513 |  | 2977
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 7006 | TRUE | 11204.5058 | 0 | 0 | 42 | 6.19e-05 | 2722 | 240.1753 | 1567 | 0.027015 | 1.1346 | 1514 | 0 | 2622
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 889948 | TRUE | 2120.3673 | 706.8877 | 0.43933 | 8 | 7.96e-05 | 2217 | 479.8183 | 1216 | 0.026886 | 0.21509 | 1515 |  | 3380
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | N34 | FALSE | 22008.9702 | 6041.6356 | 3.7549 | 62 | 9.45e-05 | 1778 | 242.6816 | 1560 | 0.02675 | 1.6585 | 1516 | 0 | 2638
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 120 | FALSE | 10326.1868 | 10326.1868 | 6.4178 | 67 | 0.00021509 | 341 | 93.788 | 1989 | 0.026687 | 1.788 | 1517 | 79.25 | 50
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | CB | FALSE | 11922.4207 | 11922.4207 | 7.4098 | 78 | 6.46e-05 | 2617 | 270.2338 | 1497 | 0.026652 | 2.0789 | 1518 | 0.11 | 1413
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 82542 | FALSE | 24330.9579 | 19513.0606 | 12.1274 | 150 | 0.00024689 | 227 | 125.8806 | 1856 | 0.026646 | 3.9969 | 1519 | 0.25 | 1073
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 904574 | FALSE | 2518.7659 | 2518.7659 | 1.5654 | 25 | 0.0002218 | 312 | 119.8467 | 1870 | 0.026628 | 0.6657 | 1520 |  | 3362
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | CB | FALSE | 10055.4219 | 1899.3733 | 1.1805 | 75 | 5.02e-05 | 3033 | 198.6367 | 1643 | 0.026552 | 1.9914 | 1521 | 0.04 | 2084
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 5973 | TRUE | 3972.7876 | 138.2354 | 0.085914 | 35 | 0.00011259 | 1351 | 248.9959 | 1541 | 0.026544 | 0.92904 | 1522 |  | 2881
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 773926 | TRUE | 3395.2146 | 706.7417 | 0.43924 | 25 | 7.91e-05 | 2232 | 668.6259 | 1044 | 0.026524 | 0.66311 | 1523 |  | 3448
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | CB | TRUE | 8832.9668 | 0 | 0 | 64 | 0.00011152 | 1384 | 254.8686 | 1534 | 0.026458 | 1.6933 | 1524 |  | 3122
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | CB | TRUE | 8317.4057 | 587.3881 | 0.36506 | 40 | 7.02e-05 | 2464 | 270.6989 | 1494 | 0.026426 | 1.057 | 1525 | 2.37 | 608
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | CB | FALSE | 23251.1044 | 23251.1044 | 14.4507 | 153 | 0.00019229 | 432 | 98.7244 | 1962 | 0.026396 | 4.0386 | 1526 | 44.02 | 163
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 3446 | TRUE | 13148.5405 | 475.0126 | 0.29522 | 87 | 0.00014693 | 773 | 117.907 | 1882 | 0.026372 | 2.2944 | 1527 | 0.23 | 1108
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 37326 | FALSE | 8213.253 | 8213.253 | 5.1046 | 31 | 6e-05 | 2777 | 369.1163 | 1338 | 0.026358 | 0.8171 | 1528 | 0.04 | 2195
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 48632 | FALSE | 4391.6286 | 4391.6286 | 2.7294 | 38 | 0.00010681 | 1483 | 115.1661 | 1895 | 0.026323 | 1.0003 | 1529 | 0.07 | 1766
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 36676 | FALSE | 27305.8877 | 27305.8877 | 16.9707 | 173 | 8.13e-05 | 2175 | 346.1968 | 1376 | 0.026145 | 4.5232 | 1530 | 34.1 | 217
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 1902 | FALSE | 7840.3138 | 7840.3138 | 4.8728 | 44 | 0.00013678 | 909 | 253.4699 | 1535 | 0.026064 | 1.1468 | 1531 | 31.9 | 227
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 1100 | FALSE | 10937.7288 | 5979.935 | 3.7166 | 68 | 8.98e-05 | 1920 | 293.7962 | 1457 | 0.026059 | 1.772 | 1532 | 0.03 | 2389
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 676060 | TRUE | 1407.162 | 722.7771 | 0.44921 | 9 | 0.00025905 | 197 | 109.1 | 1913 | 0.026046 | 0.23441 | 1533 |  | 3446
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 11188 | FALSE | 48202.5217 | 48202.5217 | 29.9581 | 294 | 0.00012846 | 1041 | 211.2891 | 1617 | 0.02599 | 7.641 | 1534 | 0.06 | 1852
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 47006 | FALSE | 7194.664 | 7194.664 | 4.4715 | 51 | 0.00041526 | 65 | 106.8362 | 1923 | 0.025936 | 1.3227 | 1535 | 0.13 | 1347
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | CB | FALSE | 10088.6649 | 2844.8661 | 1.7681 | 76 | 0.00011862 | 1213 | 152.4537 | 1770 | 0.025924 | 1.9702 | 1536 | 0.01 | 2606
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 2034 | FALSE | 17672.0047 | 17659.7087 | 10.9756 | 99 | 0.00023619 | 258 | 172.9141 | 1707 | 0.025842 | 2.5583 | 1537 | 0.4 | 942
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 346 | FALSE | 40386.1099 | 22629.4944 | 14.0643 | 309 | 0.00013985 | 869 | 232.58 | 1582 | 0.025706 | 7.9433 | 1538 | 0.07 | 1770
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 2839 | FALSE | 2358.3859 | 2358.3859 | 1.4657 | 20 | 0.00011836 | 1220 | 279.5294 | 1473 | 0.02569 | 0.5138 | 1539 | 0.07 | 1683
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | CB | FALSE | 7803.1232 | 3646.1026 | 2.2661 | 50 | 6.16e-05 | 2731 | 249.9677 | 1540 | 0.025673 | 1.2836 | 1540 | 0.06 | 1893
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 430286 | FALSE | 8696.3655 | 5942.5051 | 3.6933 | 13 | 7.02e-05 | 2468 | 482.818 | 1213 | 0.025652 | 0.33348 | 1541 |  | 3410
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 502672 | FALSE | 30486.2559 | 2285.3291 | 1.4203 | 127 | 5.97e-05 | 2781 | 641.4967 | 1071 | 0.025636 | 3.2558 | 1542 | 0.03 | 2388
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 11054 | FALSE | 41601.4757 | 39167.0021 | 24.3425 | 272 | 0.00015629 | 682 | 157.984 | 1754 | 0.025605 | 6.9646 | 1543 | 1.82 | 640
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | XR188 | TRUE | 5000.7034 | 608.151 | 0.37797 | 43 | 0.00010266 | 1579 | 145.3531 | 1791 | 0.025596 | 1.1006 | 1544 | 0.05 | 1999
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 616 | FALSE | 49320.745 | 4247.523 | 2.6399 | 198 | 8.18e-05 | 2160 | 268.44 | 1503 | 0.025585 | 5.0659 | 1545 | 0.02 | 2449
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 781566 | FALSE | 1246.3402 | 1113.5139 | 0.69205 | 11 | 0.00014318 | 824 | 155.6264 | 1762 | 0.025518 | 0.28069 | 1546 |  | 3459
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 9560 | FALSE | 35435.963 | 35435.963 | 22.0236 | 226 | 5.28e-05 | 2976 | 582.977 | 1120 | 0.025353 | 5.7297 | 1547 | 0.31 | 1001
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 7104 | FALSE | 19430.6652 | 19430.6652 | 12.0762 | 148 | 0.0001151 | 1296 | 163.538 | 1738 | 0.025302 | 3.7447 | 1548 | 13.46 | 365
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 9002 | FALSE | 9863.4451 | 1568.4919 | 0.97482 | 74 | 0.0001072 | 1468 | 178.96 | 1685 | 0.025292 | 1.8716 | 1549 | 0.04 | 2144
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 636 | FALSE | 10208.6635 | 8793.2474 | 5.465 | 81 | 0.00012369 | 1126 | 135.9278 | 1827 | 0.025287 | 2.0483 | 1550 | 0.41 | 940
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 37484 | FALSE | 15938.0756 | 12688.6958 | 7.8861 | 74 | 0.0001949 | 416 | 197.6391 | 1647 | 0.025267 | 1.8698 | 1551 | 3.58 | 540
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 844294 | FALSE | 9847.8884 | 3879.784 | 2.4113 | 55 | 0.0001067 | 1485 | 276.8057 | 1480 | 0.025242 | 1.3883 | 1552 |  | 2882
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 37522 | TRUE | 4999.5672 | 833.6297 | 0.5181 | 43 | 3.73e-05 | 3307 | 997.9464 | 835 | 0.025221 | 1.0845 | 1553 | 0.42 | 937
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 922 | FALSE | 12634.8407 | 12589.4258 | 7.8244 | 84 | 5.92e-05 | 2798 | 352.2884 | 1369 | 0.025187 | 2.1157 | 1554 | 0.06 | 1854
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | V46 | FALSE | 33477.4498 | 32077.3964 | 19.9362 | 206 | 6.54e-05 | 2604 | 359.6086 | 1354 | 0.025184 | 5.1879 | 1555 | 0.58 | 860
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | CB | FALSE | 10840.0956 | 10840.0956 | 6.7372 | 79 | 5.52e-05 | 2906 | 463.403 | 1231 | 0.025156 | 1.9873 | 1556 | 0 | 2629
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 608 | FALSE | 28658.1175 | 28658.1175 | 17.8111 | 74 | 9.53e-05 | 1755 | 248.4816 | 1545 | 0.025135 | 1.86 | 1557 | 0.18 | 1210
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 93234 | FALSE | 18471.7273 | 18471.7273 | 11.4803 | 96 | 0.0002481 | 222 | 135.7036 | 1830 | 0.025062 | 2.4059 | 1558 | 7.72 | 442
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | CB | TRUE | 6358.3504 | 326.8592 | 0.20314 | 48 | 0.00010128 | 1621 | 121.8474 | 1865 | 0.025061 | 1.2029 | 1559 | 0.07 | 1754
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 9732 | FALSE | 33758.8907 | 33758.8907 | 20.9813 | 267 | 0.00010167 | 1613 | 282.8705 | 1469 | 0.025046 | 6.6872 | 1560 | 4.84 | 504
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 524 | FALSE | 20718.9245 | 9871.5042 | 6.1352 | 162 | 9.49e-05 | 1769 | 289.834 | 1464 | 0.02502 | 4.0533 | 1561 | 3.23 | 553
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 63868 | FALSE | 25546.2406 | 25546.2406 | 15.8771 | 171 | 8.86e-05 | 1968 | 190.8082 | 1660 | 0.024964 | 4.2689 | 1562 | 0.04 | 2158
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 578852 | FALSE | 38890.7673 | 33210.6867 | 20.6406 | 173 | 9.17e-05 | 1853 | 190.7466 | 1661 | 0.024946 | 4.3156 | 1563 | 0 | 2630
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 5134 | FALSE | 4886.1695 | 1018.6198 | 0.63308 | 23 | 6.02e-05 | 2767 | 173.1479 | 1703 | 0.024922 | 0.57321 | 1564 | 0.02 | 2554
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 384530 | FALSE | 6144.6716 | 6144.6716 | 3.8189 | 12 | 0.00011661 | 1259 | 223.8048 | 1598 | 0.024779 | 0.29735 | 1565 |  | 3460
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 1034 | FALSE | 17942.0463 | 17942.0463 | 11.1511 | 80 | 8.31e-05 | 2129 | 308.8782 | 1434 | 0.024689 | 1.9751 | 1566 | 37.44 | 201
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 1806 | FALSE | 6482.8365 | 6482.8365 | 4.0291 | 17 | 0.00015564 | 687 | 310.6981 | 1431 | 0.024567 | 0.41764 | 1567 | 0.08 | 1588
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 7040 | FALSE | 36891.8795 | 33515.8907 | 20.8303 | 119 | 0.00010008 | 1645 | 276.795 | 1481 | 0.02433 | 2.8953 | 1568 | 0.03 | 2398
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 8050 | FALSE | 19488.3045 | 19488.3045 | 12.1121 | 137 | 6.46e-05 | 2624 | 296.266 | 1454 | 0.024311 | 3.3307 | 1569 | 82.85 | 41
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 397902 | TRUE | 2608.3236 | 717.5326 | 0.44595 | 9 | 1.9e-05 | 3553 | 1301.6353 | 682 | 0.024302 | 0.21872 | 1570 |  | 3589
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 61816 | FALSE | 37826.9874 | 37826.9874 | 23.5096 | 228 | 9.08e-05 | 1889 | 261.0762 | 1521 | 0.0243 | 5.5405 | 1571 | 0.1 | 1458
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | CB | FALSE | 26239.5079 | 25449.7716 | 15.8171 | 183 | 5.94e-05 | 2793 | 407.261 | 1290 | 0.024236 | 4.4352 | 1572 | 0.24 | 1103
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 472660 | FALSE | 2333.6937 | 2333.6937 | 1.4504 | 18 | 0.00011189 | 1371 | 307.8995 | 1436 | 0.024226 | 0.43606 | 1573 |  | 3221
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | CB | TRUE | 2139.8633 | 621.7387 | 0.38641 | 28 | 0.00025903 | 198 | 63.383 | 2133 | 0.024194 | 0.67743 | 1574 | 1.36 | 681
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 321000 | FALSE | 4053.5114 | 2330.3266 | 1.4483 | 13 | 3.54e-05 | 3341 | 465.5516 | 1229 | 0.024187 | 0.31443 | 1575 |  | 3503
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 734248 | TRUE | 774.6582 | 774.6582 | 0.48145 | 9 | 9.73e-05 | 1706 | 238.3995 | 1571 | 0.024166 | 0.2175 | 1576 |  | 2824
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 42650 | FALSE | 4322.5083 | 1459.6214 | 0.90716 | 37 | 0.00018107 | 502 | 100.7676 | 1951 | 0.024082 | 0.89104 | 1577 | 0.04 | 2229
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 90548 | FALSE | 28870.4925 | 28870.4925 | 17.9431 | 168 | 0.00013973 | 872 | 196.9334 | 1651 | 0.024003 | 4.0325 | 1578 | 0.67 | 811
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 224708 | FALSE | 1049.1603 | 1033.1582 | 0.64211 | 9 | 0.00015636 | 681 | 235.0194 | 1578 | 0.02399 | 0.21591 | 1579 |  | 3374
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 35424 | FALSE | 22308.0719 | 22308.0719 | 13.8646 | 147 | 0.00020736 | 374 | 171.1392 | 1711 | 0.023757 | 3.4923 | 1580 | 74.11 | 58
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 51696 | FALSE | 32551.2584 | 28077.2635 | 17.4501 | 238 | 0.00017871 | 514 | 165.4297 | 1734 | 0.023753 | 5.6532 | 1581 | 0.86 | 763
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 738866 | FALSE | 4335.7412 | 3280.2516 | 2.0387 | 28 | 6.38e-05 | 2653 | 268.4844 | 1502 | 0.023732 | 0.66451 | 1582 | 0.1 | 1506
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 940112 | TRUE | 489.7385 | 455.0253 | 0.2828 | 2 | 5.88e-05 | 2813 | 268.9489 | 1500 | 0.023701 | 0.047401 | 1583 |  | 3616
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 438074 | TRUE | 2039.2275 | 516.2478 | 0.32085 | 6 | 3.23e-05 | 3397 | 1470.0727 | 606 | 0.023646 | 0.14187 | 1584 |  | 3592
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 350 | FALSE | 31334.246 | 8365.2365 | 5.199 | 194 | 8.93e-05 | 1940 | 270.3135 | 1496 | 0.023632 | 4.5846 | 1585 | 0.09 | 1536
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | CB | FALSE | 15763.1114 | 12699.351 | 7.8927 | 97 | 5.95e-05 | 2789 | 274.1428 | 1486 | 0.023627 | 2.2918 | 1586 | 0.1 | 1488
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | L3361 | FALSE | 3015.6838 | 3015.6838 | 1.8743 | 21 | 6.36e-05 | 2658 | 377.9344 | 1325 | 0.023616 | 0.49595 | 1587 | 0.09 | 1563
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 122 | FALSE | 11125.688 | 2112.7276 | 1.3131 | 54 | 6.28e-05 | 2689 | 203.6365 | 1635 | 0.023602 | 1.2745 | 1588 | 0.03 | 2263
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 95294 | FALSE | 43494.7194 | 43494.7194 | 27.0321 | 186 | 0.00012237 | 1142 | 194.7256 | 1654 | 0.023449 | 4.3615 | 1589 | 0.05 | 2049
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 764 | FALSE | 23643.468 | 23643.468 | 14.6945 | 146 | 0.00012366 | 1128 | 171.5032 | 1710 | 0.023389 | 3.4148 | 1590 | 57.88 | 95
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 516510 | FALSE | 13673.0725 | 6073.3479 | 3.7746 | 73 | 9.31e-05 | 1818 | 270.871 | 1493 | 0.02337 | 1.706 | 1591 |  | 3347
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 3172 | FALSE | 60635.9905 | 60635.9905 | 37.6855 | 448 | 0.00020312 | 385 | 59.0594 | 2161 | 0.023346 | 10.4588 | 1592 | 67.49 | 73
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 154256 | TRUE | 446.5228 | 430.6088 | 0.26763 | 2 | 0.00011705 | 1248 | 293.424 | 1459 | 0.023318 | 0.046636 | 1593 |  | 3510
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 307998 | TRUE | 911.4775 | 895.4026 | 0.5565 | 6 | 0.00010251 | 1588 | 237.8428 | 1573 | 0.023314 | 0.13989 | 1594 |  | 3235
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 170 | FALSE | 33470.2158 | 28905.2433 | 17.9647 | 223 | 9.1e-05 | 1881 | 278.3702 | 1476 | 0.023285 | 5.1925 | 1595 | 10.49 | 396
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 347280 | FALSE | 20187.7037 | 12761.9341 | 7.9316 | 99 | 7.6e-05 | 2307 | 290.5041 | 1463 | 0.023256 | 2.3024 | 1596 |  | 3109
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8302 | FALSE | 13154.2224 | 13154.2224 | 8.1754 | 83 | 9.52e-05 | 1760 | 244.7794 | 1556 | 0.023206 | 1.9261 | 1597 | 0.09 | 1552
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 3090 | FALSE | 17393.6531 | 17393.6531 | 10.8102 | 58 | 0.00018901 | 447 | 142.6437 | 1798 | 0.023177 | 1.3443 | 1598 | 0.06 | 1843
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 2040 | FALSE | 14724.8662 | 14724.8662 | 9.1516 | 21 | 0.00015655 | 679 | 141.5532 | 1807 | 0.023168 | 0.48652 | 1599 | 17.99 | 328
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | XR548 | FALSE | 14288.8839 | 2708.1629 | 1.6831 | 95 | 8.79e-05 | 1987 | 271.2652 | 1492 | 0.023159 | 2.2001 | 1600 | 0.04 | 2088
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 10870 | FALSE | 4188.8092 | 3071.5505 | 1.909 | 28 | 0.00010127 | 1622 | 246.1327 | 1549 | 0.023077 | 0.64616 | 1601 | 0.04 | 2108
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 3168 | FALSE | 48228.3961 | 48228.3961 | 29.9741 | 285 | 0.00015583 | 684 | 176.2133 | 1695 | 0.023045 | 6.5678 | 1602 | 0.24 | 1095
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 531594 | FALSE | 4284.5499 | 3998.7287 | 2.4852 | 25 | 5.97e-05 | 2782 | 338.5434 | 1391 | 0.022917 | 0.57293 | 1603 |  | 3558
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 8140 | FALSE | 42456.9039 | 42456.9039 | 26.3871 | 260 | 8.2e-05 | 2153 | 273.2886 | 1487 | 0.022915 | 5.958 | 1604 | 41.27 | 178
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | A22 | TRUE | 21048.1737 | 0 | 0 | 167 | 6.01e-05 | 2769 | 362.8063 | 1349 | 0.022889 | 3.8224 | 1605 | 0.03 | 2288
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 557000 | TRUE | 398.6933 | 335.0317 | 0.20822 | 3 | 0.00012959 | 1015 | 348.9375 | 1373 | 0.022855 | 0.068564 | 1606 |  | 3596
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 2006 | FALSE | 27571.1883 | 27571.1883 | 17.1356 | 151 | 6.09e-05 | 2751 | 384.5024 | 1313 | 0.022834 | 3.4479 | 1607 | 0.22 | 1125
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 641808 | FALSE | 41435.7029 | 41435.7029 | 25.7525 | 234 | 0.00014735 | 768 | 181.2789 | 1681 | 0.022822 | 5.3404 | 1608 | 0.36 | 973
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 7142 | FALSE | 24816.4121 | 6275.5413 | 3.9003 | 100 | 7.72e-05 | 2282 | 356.2375 | 1361 | 0.022773 | 2.2773 | 1609 | 0.03 | 2276
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 58448 | FALSE | 7774.1256 | 7141.1012 | 4.4382 | 22 | 8.86e-05 | 1966 | 261.6309 | 1519 | 0.022766 | 0.50086 | 1610 |  | 3368
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 630456 | FALSE | 8616.6169 | 8616.6169 | 5.3553 | 37 | 0.00023209 | 277 | 84.9164 | 2030 | 0.022761 | 0.84216 | 1611 |  | 2888
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 84278 | FALSE | 2506.1692 | 2490.1671 | 1.5476 | 18 | 7.31e-05 | 2392 | 245.6104 | 1553 | 0.022717 | 0.4089 | 1612 | 2.62 | 594
5345 | ELK 11011300 | 42981101 | ELK 1101 | 1300 | FALSE | 15995.4516 | 5711.2619 | 3.5496 | 64 | 8.52e-05 | 2052 | 259.4524 | 1525 | 0.02261 | 1.447 | 1613 | 0.01 | 2613
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 9712 | FALSE | 29909.7326 | 29909.7326 | 18.589 | 214 | 0.00017251 | 547 | 156.1721 | 1761 | 0.022607 | 4.838 | 1614 | 0.65 | 825
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 1902 | FALSE | 11685.3749 | 10562.7391 | 6.5648 | 43 | 0.00014928 | 746 | 134.194 | 1834 | 0.022585 | 0.97115 | 1615 | 0.08 | 1666
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 895310 | TRUE | 4366.1321 | 592.9592 | 0.36853 | 31 | 6.42e-05 | 2637 | 241.124 | 1565 | 0.022565 | 0.69951 | 1616 |  | 3336
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | MR178 | FALSE | 21546.6859 | 2579.6297 | 1.6033 | 117 | 6.76e-05 | 2547 | 427.86 | 1263 | 0.022562 | 2.6398 | 1617 |  | 2847
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 198 | FALSE | 10335.8179 | 10335.8179 | 6.4238 | 62 | 0.0001183 | 1224 | 193.0004 | 1658 | 0.02256 | 1.3987 | 1618 | 41.1 | 181
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 251688 | FALSE | 12475.4445 | 11233.7101 | 6.9818 | 68 | 7.41e-05 | 2355 | 394.4035 | 1300 | 0.022486 | 1.5291 | 1619 |  | 3207
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 858200 | FALSE | 9571.0308 | 9200.2096 | 5.718 | 31 | 6.6e-05 | 2588 | 330.1244 | 1397 | 0.022446 | 0.69582 | 1620 |  | 3395
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 59128 | FALSE | 11301.2737 | 1201.9482 | 0.74702 | 65 | 0.00010017 | 1639 | 414.1368 | 1279 | 0.022397 | 1.4558 | 1621 |  | 2980
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 85112 | FALSE | 10932.2503 | 10932.2503 | 6.7944 | 54 | 7.2e-05 | 2417 | 306.4662 | 1437 | 0.022386 | 1.2088 | 1622 | 0.07 | 1740
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 518 | FALSE | 36303.8238 | 4840.0159 | 3.0081 | 165 | 0.0001564 | 680 | 133.4232 | 1837 | 0.02237 | 3.6911 | 1623 | 0.31 | 1002
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 769230 | FALSE | 27505.7293 | 17732.852 | 11.021 | 160 | 0.00011179 | 1372 | 159.0323 | 1749 | 0.022338 | 3.574 | 1624 | 0.28 | 1034
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 37350 | FALSE | 39069.9006 | 39069.9006 | 24.2821 | 255 | 7.7e-05 | 2287 | 360.2031 | 1353 | 0.02227 | 5.6788 | 1625 | 13.94 | 359
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 648698 | FALSE | 30462.3699 | 17135.0454 | 10.6495 | 173 | 2.22e-05 | 3516 | 1031.0161 | 807 | 0.022255 | 3.85 | 1626 |  | 2707
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | CB | FALSE | 12882.1278 | 12682.5013 | 7.8822 | 86 | 0.00028932 | 141 | 75.4177 | 2064 | 0.022172 | 1.9068 | 1627 | 0.07 | 1701
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 1514 | FALSE | 23767.6372 | 23767.6372 | 14.7717 | 123 | 0.0005607 | 23 | 46.0416 | 2239 | 0.022168 | 2.7266 | 1628 | 0.07 | 1675
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 512313 | TRUE | 1333.0799 | 785.9125 | 0.48845 | 10 | 3.7e-05 | 3314 | 418.9141 | 1273 | 0.022063 | 0.22063 | 1629 |  | 3136
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 895784 | FALSE | 16727.2163 | 12538.91 | 7.793 | 110 | 8.37e-05 | 2101 | 275.8868 | 1483 | 0.022046 | 2.4251 | 1630 |  | 3006
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 75204 | FALSE | 29879.1855 | 1376.4738 | 0.85548 | 130 | 8.07e-05 | 2187 | 212.0292 | 1614 | 0.021935 | 2.8515 | 1631 | 0.01 | 2584
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 848530 | TRUE | 2567.2359 | 715.3706 | 0.44461 | 17 | 9.01e-05 | 1909 | 263.7059 | 1513 | 0.021849 | 0.37143 | 1632 |  | 3381
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 34416 | FALSE | 16821.5127 | 16821.5127 | 10.4546 | 113 | 8.85e-05 | 1971 | 264.2059 | 1510 | 0.021823 | 2.466 | 1633 | 42.3 | 170
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | CB | FALSE | 28620.471 | 28620.471 | 17.7877 | 195 | 0.00020845 | 368 | 153.8768 | 1765 | 0.02173 | 4.2374 | 1634 | 37.1 | 202
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 144140 | TRUE | 2469.4129 | 417.0111 | 0.25917 | 20 | 0.00015373 | 713 | 178.8701 | 1686 | 0.021719 | 0.43439 | 1635 |  | 3076
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 311906 | FALSE | 1528.1122 | 1112.4459 | 0.69139 | 12 | 0.00010712 | 1471 | 200.1105 | 1641 | 0.021675 | 0.2601 | 1636 |  | 3445
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 8652 | FALSE | 21158.9046 | 21158.9046 | 13.1503 | 114 | 0.0003142 | 113 | 77.6007 | 2059 | 0.021633 | 2.4661 | 1637 | 8.55 | 422
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 2416 | FALSE | 50020.1074 | 46563.0328 | 28.9391 | 360 | 0.00016423 | 598 | 156.2016 | 1760 | 0.021547 | 7.7569 | 1638 | 0.56 | 863
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 630 | FALSE | 21891.4244 | 20012.2615 | 12.4377 | 154 | 9.53e-05 | 1756 | 292.7922 | 1460 | 0.021529 | 3.3154 | 1639 | 0.13 | 1357
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 771258 | TRUE | 308.3578 | 308.3578 | 0.19165 | 4 | 6.81e-05 | 2532 | 427.9894 | 1262 | 0.021484 | 0.085935 | 1640 |  | 3432
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 3902 | FALSE | 8223.6344 | 8223.6344 | 5.111 | 9 | 0.00018188 | 498 | 110.945 | 1907 | 0.021389 | 0.1925 | 1641 | 0.02 | 2480
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | CB | FALSE | 22023.4026 | 21461.232 | 13.3382 | 163 | 0.00013265 | 967 | 170.2363 | 1715 | 0.021383 | 3.4854 | 1642 | 0.14 | 1316
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 609690 | FALSE | 12043.451 | 7774.3071 | 4.8318 | 72 | 7.56e-05 | 2321 | 321.8791 | 1411 | 0.021383 | 1.5396 | 1643 |  | 2744
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 6502 | FALSE | 6145.0425 | 1500.682 | 0.93268 | 52 | 0.00017025 | 561 | 88.4192 | 2012 | 0.021251 | 1.1051 | 1644 | 1.73 | 647
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 59046 | FALSE | 6015.5462 | 5641.1576 | 3.506 | 15 | 0.00010509 | 1522 | 101.9046 | 1945 | 0.021246 | 0.31869 | 1645 | 0.25 | 1078
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 9712 | FALSE | 39765.9579 | 39765.9579 | 24.7147 | 226 | 0.00014908 | 750 | 116.696 | 1890 | 0.021241 | 4.8004 | 1646 | 0.54 | 877
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 2072 | TRUE | 27455.5664 | 501.4668 | 0.31166 | 193 | 9.37e-05 | 1804 | 181.6575 | 1679 | 0.021197 | 4.091 | 1647 | 0.03 | 2308
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 708 | FALSE | 7904.2269 | 6040.8568 | 3.7544 | 61 | 0.00013285 | 959 | 152.2948 | 1771 | 0.02118 | 1.292 | 1648 | 0.54 | 876
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 1010 | FALSE | 71394.2707 | 71394.2707 | 44.3718 | 479 | 0.00011001 | 1412 | 172.5805 | 1708 | 0.021168 | 10.1396 | 1649 | 129.45 | 6
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 5460 | FALSE | 18980.3372 | 18980.3372 | 11.7964 | 91 | 0.000114 | 1322 | 193.3663 | 1657 | 0.021116 | 1.9215 | 1650 | 41.43 | 176
9400 | BELL 110880680 | 152701108 | BELL 1108 | 80680 | FALSE | 2866.5185 | 1030.5857 | 0.64051 | 24 | 0.00023396 | 265 | 175.0191 | 1697 | 0.021095 | 0.50627 | 1651 | 0.04 | 2179
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 80930 | FALSE | 29528.4888 | 29528.4888 | 18.3521 | 180 | 6.82e-05 | 2529 | 304.5139 | 1442 | 0.021019 | 3.7835 | 1652 | 0.22 | 1126
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | CB | TRUE | 11751.5136 | 394.0047 | 0.24488 | 100 | 0.00016594 | 582 | 73.1844 | 2079 | 0.021017 | 2.1017 | 1653 | 0.02 | 2416
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 902 | FALSE | 19453.8935 | 19453.8935 | 12.0907 | 83 | 9.15e-05 | 1858 | 227.244 | 1592 | 0.020905 | 1.7351 | 1654 | 0.72 | 798
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 783467 | FALSE | 16521.4957 | 16448.6096 | 10.2229 | 61 | 8.02e-05 | 2201 | 245.1782 | 1554 | 0.020785 | 1.2679 | 1655 |  | 3145
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 1180 | FALSE | 20847.2086 | 20847.2086 | 12.9566 | 141 | 0.00012525 | 1094 | 118.9045 | 1874 | 0.020771 | 2.9287 | 1656 | 0.11 | 1417
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 814656 | TRUE | 28.1252 | 28.1252 | 0.01748 | 1 | 0.00086571 | 4 | 23.8451 | 2401 | 0.020643 | 0.020643 | 1657 |  | 3634
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | CB | FALSE | 3707.9332 | 3707.9332 | 2.3045 | 31 | 9.4e-05 | 1792 | 320.4886 | 1415 | 0.020623 | 0.63931 | 1658 | 0.11 | 1444
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 812366 | FALSE | 4450.8969 | 4421.1038 | 2.7477 | 28 | 8.51e-05 | 2055 | 149.7437 | 1778 | 0.020596 | 0.57668 | 1659 |  | 2843
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 160 | FALSE | 10761.0163 | 4469.2889 | 2.7777 | 77 | 9.25e-05 | 1831 | 17.9801 | 2481 | 0.0024952 | 0.19213 | 2414 | 0.04 | 2105
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 7144 | FALSE | 7491.0055 | 7491.0055 | 4.6557 | 52 | 8.73e-05 | 2005 | 376.542 | 1327 | 0.020479 | 1.0649 | 1661 | 0.36 | 967
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 752596 | TRUE | 1041.1396 | 395.1334 | 0.24558 | 6 | 0.00010963 | 1418 | 256.5638 | 1530 | 0.020465 | 0.12279 | 1662 |  | 3606
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 851 | FALSE | 2029.0984 | 2029.0984 | 1.2611 | 14 | 0.00014146 | 845 | 190.4229 | 1662 | 0.020416 | 0.28582 | 1663 | 44.15 | 161
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 4790 | FALSE | 52731.0383 | 52731.0383 | 32.7726 | 305 | 0.00011375 | 1325 | 232.2083 | 1584 | 0.020377 | 6.2151 | 1664 | 47.18 | 136
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 60080 | FALSE | 16285.3103 | 15418.9407 | 9.5829 | 64 | 0.00014044 | 864 | 185.0893 | 1672 | 0.020345 | 1.3021 | 1665 | 0.24 | 1091
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 11132 | FALSE | 69633.6958 | 69633.6958 | 43.2776 | 420 | 0.00012774 | 1054 | 197.2748 | 1649 | 0.020262 | 8.5102 | 1666 | 0.54 | 875
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 65932 | FALSE | 7276.7194 | 7276.7194 | 4.5225 | 48 | 0.00012509 | 1096 | 211.5152 | 1616 | 0.020219 | 0.97052 | 1667 | 64.62 | 78
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 83098 | FALSE | 12739.0077 | 12739.0077 | 7.9173 | 104 | 7.58e-05 | 2312 | 344.4746 | 1378 | 0.020137 | 2.0942 | 1668 | 45.66 | 147
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 318 | FALSE | 31114.0365 | 31114.0365 | 19.3375 | 228 | 0.00011669 | 1256 | 178.6742 | 1688 | 0.020097 | 4.5821 | 1669 | 88.23 | 35
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 7068 | FALSE | 6155.1451 | 6139.1207 | 3.8155 | 12 | 7.07e-05 | 2451 | 336.2364 | 1392 | 0.019995 | 0.23993 | 1670 | 0.05 | 1997
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | CB | FALSE | 10025.1577 | 6936.1203 | 4.3108 | 73 | 0.00013127 | 993 | 100.6191 | 1952 | 0.019906 | 1.4531 | 1671 | 0.05 | 1978
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | V60 | FALSE | 25811.5583 | 25811.5583 | 16.042 | 142 | 6.43e-05 | 2632 | 354.0238 | 1367 | 0.0199 | 2.8258 | 1672 | 0.51 | 892
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 368158 | FALSE | 14121.5307 | 4484.8758 | 2.7874 | 105 | 0.0001001 | 1644 | 219.1144 | 1607 | 0.019862 | 2.0855 | 1673 |  | 2756
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 1376 | FALSE | 14477.8455 | 14477.8455 | 8.998 | 70 | 0.00013205 | 982 | 179.7284 | 1683 | 0.019836 | 1.3885 | 1674 | 0.02 | 2535
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 714 | FALSE | 17594.5823 | 5568.6627 | 3.4609 | 121 | 0.0001288 | 1033 | 138.0832 | 1817 | 0.019829 | 2.3993 | 1675 | 0.08 | 1672
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 75340 | FALSE | 7696.0179 | 7696.0179 | 4.7831 | 62 | 0.00022111 | 314 | 112.7853 | 1902 | 0.01968 | 1.2202 | 1676 | 43.45 | 168
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 234 | FALSE | 10290.6171 | 5584.5077 | 3.4708 | 81 | 0.0001531 | 719 | 12.3014 | 2581 | 0.0015051 | 0.12191 | 2556 | 0.04 | 2094
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 951424 | FALSE | 5857.3043 | 1124.2371 | 0.69872 | 49 | 6.66e-05 | 2568 | 260.8969 | 1522 | 0.019501 | 0.95554 | 1678 |  | 3026
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 3304 | FALSE | 27901.6416 | 27901.6416 | 17.341 | 88 | 0.00030684 | 123 | 72.4308 | 2081 | 0.019486 | 1.7148 | 1679 | 0.14 | 1315
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 10342 | FALSE | 2930.8819 | 2930.8819 | 1.8216 | 23 | 0.00012225 | 1143 | 225.3144 | 1595 | 0.019463 | 0.44766 | 1680 | 0.23 | 1111
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 38436 | FALSE | 7699.8876 | 7253.5318 | 4.5081 | 62 | 0.00011304 | 1342 | 129.1673 | 1847 | 0.019424 | 1.2043 | 1681 | 0.17 | 1243
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 540991 | FALSE | 2594.6741 | 2544.5262 | 1.5814 | 16 | 6.99e-05 | 2477 | 260.165 | 1524 | 0.019417 | 0.31068 | 1682 |  | 3290
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 1504 | FALSE | 19432.0474 | 17454.8051 | 10.8482 | 64 | 0.00027686 | 165 | 148.5088 | 1782 | 0.019342 | 1.2379 | 1683 | 0.01 | 2608
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 302 | FALSE | 16561.5527 | 14104.3324 | 8.7659 | 123 | 0.00011341 | 1335 | 134.8667 | 1832 | 0.013839 | 1.7022 | 1826 | 14.9 | 352
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 1546 | FALSE | 37312.9087 | 22193.9329 | 13.7936 | 102 | 2.05e-05 | 3539 | 794.3875 | 945 | 0.019258 | 1.9643 | 1685 | 0.02 | 2496
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 6018 | FALSE | 30239.5339 | 25219.5525 | 15.6741 | 160 | 8.52e-05 | 2048 | 248.6459 | 1544 | 0.019223 | 3.0757 | 1686 | 0.05 | 1942
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 807953 | TRUE | 1013.1517 | 745.8215 | 0.46353 | 11 | 0.00012129 | 1161 | 149.9335 | 1777 | 0.019176 | 0.21093 | 1687 |  | 2915
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 223792 | FALSE | 1426.5673 | 1262.347 | 0.78455 | 10 | 7.65e-05 | 2293 | 237.9603 | 1572 | 0.019106 | 0.19106 | 1688 |  | 2832
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | CB | FALSE | 14256.0927 | 10229.3323 | 6.3576 | 98 | 0.00010673 | 1484 | 150.89 | 1774 | 0.019021 | 1.864 | 1689 | 0.06 | 1871
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 7702 | TRUE | 30606.5708 | 0 | 0 | 168 | 8.52e-05 | 2051 | 328.4397 | 1400 | 0.018893 | 3.174 | 1690 | 0.04 | 2103
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 70960 | FALSE | 18837.8279 | 9297.8122 | 5.7786 | 103 | 0.00023998 | 245 | 91.5029 | 1995 | 0.018609 | 1.9167 | 1691 | 0 | 2636
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 2987 | FALSE | 3171.9583 | 3171.9583 | 1.9714 | 18 | 0.0002636 | 186 | 74.107 | 2072 | 0.018603 | 0.33485 | 1692 | 15.92 | 343
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | CB | FALSE | 24644.898 | 24644.898 | 15.3169 | 123 | 0.00014722 | 772 | 162.3912 | 1740 | 0.0185 | 2.2755 | 1693 | 73.53 | 61
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 928 | FALSE | 24779.274 | 22468.3871 | 13.9642 | 125 | 9.51e-05 | 1765 | 208.5932 | 1622 | 0.018489 | 2.3111 | 1694 | 0.05 | 2054
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | CB | FALSE | 6642.1904 | 4240.0548 | 2.6352 | 54 | 0.00012016 | 1183 | 144.2308 | 1793 | 0.018327 | 0.98966 | 1695 | 0.11 | 1449
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 1305 | FALSE | 18201.3708 | 18201.3708 | 11.3122 | 105 | 0.00010838 | 1442 | 197.4917 | 1648 | 0.01831 | 1.9226 | 1696 | 0.76 | 784
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 575872 | FALSE | 2328.1768 | 1906.857 | 1.1851 | 12 | 0.00010594 | 1497 | 157.6636 | 1757 | 0.018279 | 0.21935 | 1697 |  | 3165
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | H80 | FALSE | 31889.194 | 31889.194 | 19.8193 | 164 | 9.89e-05 | 1673 | 213.2657 | 1612 | 0.018248 | 2.9927 | 1698 |  | 2739
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 9432 | FALSE | 32768.2312 | 28100.4349 | 17.4645 | 251 | 0.0001473 | 771 | 86.1349 | 2022 | 0.018233 | 4.5765 | 1699 | 0.25 | 1080
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | CB | FALSE | 28981.2992 | 28981.2992 | 18.012 | 104 | 0.00012953 | 1019 | 141.7915 | 1804 | 0.018204 | 1.8932 | 1700 | 44.04 | 162
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 343 | FALSE | 7140.9406 | 7140.9406 | 4.4381 | 39 | 0.0001241 | 1116 | 75.0943 | 2067 | 0.0075606 | 0.29486 | 2069 | 38.93 | 192
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 32556 | TRUE | 2113.2756 | 188.0999 | 0.1169 | 19 | 0.00017312 | 540 | 58.9098 | 2162 | 0.018147 | 0.34478 | 1702 | 0.05 | 2039
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 2094 | FALSE | 5517.0419 | 5517.0419 | 3.4289 | 11 | 0.00021985 | 323 | 101.8231 | 1947 | 0.018088 | 0.19897 | 1703 | 0.01 | 2580
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | CB | FALSE | 19055.2866 | 19055.2866 | 11.8429 | 80 | 8.79e-05 | 1984 | 356.7774 | 1359 | 0.018079 | 1.4463 | 1704 | 0.23 | 1117
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 482838 | FALSE | 17714.345 | 14284.261 | 8.8777 | 52 | 6.16e-05 | 2730 | 318.0089 | 1421 | 0.018057 | 0.93898 | 1705 |  | 3180
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 2422 | FALSE | 13951.5772 | 13951.5772 | 8.671 | 81 | 0.00012199 | 1147 | 229.8045 | 1587 | 0.018043 | 1.4615 | 1706 | 0.07 | 1676
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 437194 | FALSE | 1741.9129 | 1702.9792 | 1.0584 | 17 | 9.45e-05 | 1781 | 148.2733 | 1783 | 0.018026 | 0.30645 | 1707 |  | 3303
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 86876 | FALSE | 13761.5335 | 3945.9351 | 2.4524 | 110 | 6.21e-05 | 2715 | 110.516 | 1909 | 0.018007 | 1.9808 | 1708 | 0.03 | 2303
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 711966 | FALSE | 19227.2924 | 6326.045 | 3.9317 | 122 | 9.01e-05 | 1907 | 205.4077 | 1625 | 0.017908 | 2.1848 | 1709 |  | 2982
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 1720 | FALSE | 9489.0848 | 9489.0848 | 5.8975 | 34 | 6.95e-05 | 2488 | 304.935 | 1440 | 0.017864 | 0.60738 | 1710 | 23.51 | 285
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 2766 | FALSE | 5300.562 | 5300.562 | 3.2943 | 31 | 0.00018321 | 487 | 59.8653 | 2154 | 0.017834 | 0.55287 | 1711 | 29.29 | 242
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 416 | FALSE | 5187.8358 | 4249.986 | 2.6414 | 28 | 0.00012384 | 1122 | 177.6431 | 1689 | 0.019316 | 0.54085 | 1684 | 0.35 | 975
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | CB | FALSE | 17908.5118 | 3627.2584 | 2.2544 | 118 | 9.06e-05 | 1894 | 263.1957 | 1514 | 0.017802 | 2.1007 | 1713 | 0.7 | 809
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 432 | FALSE | 12624.3351 | 12624.3351 | 7.8461 | 72 | 0.00017278 | 544 | 132.4511 | 1841 | 0.017729 | 1.2765 | 1714 | 0.96 | 740
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 850102 | TRUE | 3948.9067 | 287.4404 | 0.17865 | 23 | 4.42e-05 | 3186 | 279.8882 | 1472 | 0.01772 | 0.40756 | 1715 |  | 2955
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 90320 | FALSE | 44849.664 | 44849.664 | 27.8742 | 282 | 7.41e-05 | 2356 | 382.5749 | 1315 | 0.017701 | 4.9917 | 1716 | 0.1 | 1463
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 2232 | FALSE | 32508.1294 | 25513.6467 | 15.8568 | 128 | 4.48e-05 | 3165 | 539.0362 | 1160 | 0.017667 | 2.2614 | 1717 | 4.69 | 510
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 750804 | TRUE | 449.416 | 390.0676 | 0.24243 | 5 | 0.00016489 | 588 | 71.3665 | 2087 | 0.017655 | 0.088275 | 1718 |  | 3500
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 1589 | FALSE | 6873.0951 | 6873.0951 | 4.2717 | 52 | 8.5e-05 | 2058 | 184.9596 | 1673 | 0.01765 | 0.91781 | 1719 | 0.08 | 1649
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 36816 | FALSE | 8023.9266 | 8023.9266 | 4.9869 | 60 | 0.00012475 | 1102 | 139.9542 | 1810 | 0.017625 | 1.0575 | 1720 | 0.09 | 1516
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | CB | FALSE | 11789.4236 | 11789.4236 | 7.3272 | 71 | 0.00029554 | 134 | 73.697 | 2075 | 0.017606 | 1.25 | 1721 | 13.84 | 360
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 1378 | FALSE | 40111.5829 | 39490.7149 | 24.5436 | 201 | 0.00013379 | 948 | 148.5755 | 1780 | 0.017574 | 3.5323 | 1722 | 0.05 | 2031
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 117328 | FALSE | 23158.4732 | 9894.6539 | 6.1496 | 44 | 4.09e-05 | 3248 | 400.677 | 1296 | 0.017549 | 0.77216 | 1723 |  | 3271
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 1954 | FALSE | 17187.784 | 4223.5591 | 2.625 | 132 | 0.00016112 | 630 | 102.5688 | 1939 | 0.017468 | 2.3057 | 1724 | 0.07 | 1692
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 6060 | FALSE | 6540.8971 | 6540.8971 | 4.0652 | 50 | 0.00014094 | 855 | 178.7675 | 1687 | 0.01746 | 0.873 | 1725 | 0.1 | 1461
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 5042 | FALSE | 11222.6237 | 9737.3633 | 6.0518 | 90 | 0.0001242 | 1114 | 141.9193 | 1803 | 0.01743 | 1.5687 | 1726 | 6.17 | 471
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 739858 | FALSE | 8002.9028 | 7850.7225 | 4.8793 | 46 | 0.00010369 | 1557 | 204.17 | 1632 | 0.017426 | 0.80161 | 1727 |  | 3225
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 1406 | FALSE | 43882.3619 | 43882.3619 | 27.2731 | 204 | 9.55e-05 | 1742 | 157.7153 | 1755 | 0.017352 | 3.5397 | 1728 | 0.18 | 1217
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 477914 | TRUE | 388.2883 | 307.8291 | 0.19132 | 3 | 0.00012285 | 1135 | 285.164 | 1467 | 0.017329 | 0.051987 | 1729 |  | 3582
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 796050 | TRUE | 5067.2794 | 383.7484 | 0.2385 | 45 | 4.15e-05 | 3233 | 109.4022 | 1911 | 0.017291 | 0.7781 | 1730 |  | 2738
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 1721 | FALSE | 10927.2973 | 10927.2973 | 6.7914 | 52 | 0.00016339 | 607 | 107.9769 | 1918 | 0.01726 | 0.89751 | 1731 | 0.12 | 1367
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 298 | FALSE | 20337.8041 | 20253.8323 | 12.5878 | 123 | 0.00016851 | 572 | 115.628 | 1892 | 0.017238 | 2.1202 | 1732 | 85.76 | 39
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 92870 | TRUE | 25931.8169 | 185.9475 | 0.11557 | 187 | 6.39e-05 | 2649 | 163.1162 | 1739 | 0.017207 | 3.2176 | 1733 | 2.3 | 615
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 597518 | TRUE | 2581.15 | 65.1647 | 0.0405 | 30 | 4.63e-05 | 3129 | 233.218 | 1579 | 0.017175 | 0.51524 | 1734 | 0.07 | 1768
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 3312 | FALSE | 14682.6252 | 12944.3529 | 8.045 | 82 | 3.19e-05 | 3403 | 501.3484 | 1197 | 0.017169 | 1.4079 | 1735 | 0.05 | 1934
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 1488 | FALSE | 53867.328 | 3970.6557 | 2.4678 | 217 | 3.79e-05 | 3301 | 226.8447 | 1594 | 0.01714 | 3.7195 | 1736 | 0.01 | 2597
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | CB | FALSE | 6895.2449 | 6754.5413 | 4.198 | 47 | 0.00021084 | 355 | 102.4575 | 1940 | 0.017137 | 0.80543 | 1737 | 0.07 | 1698
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 60114 | FALSE | 39130.9882 | 39130.9882 | 24.3201 | 220 | 0.00014614 | 787 | 173.2936 | 1702 | 0.016971 | 3.7337 | 1738 | 112.13 | 13
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 184604 | FALSE | 16467.2376 | 3361.2922 | 2.0891 | 106 | 3.71e-05 | 3311 | 169.9457 | 1716 | 0.016935 | 1.7951 | 1739 |  | 2831
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | CB | FALSE | 3204.0009 | 1997.9569 | 1.2417 | 29 | 5.3e-05 | 2969 | 262.0724 | 1517 | 0.016895 | 0.48997 | 1740 | 0.03 | 2250
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 3121 | FALSE | 4501.3904 | 4501.3904 | 2.7976 | 36 | 0.00013779 | 897 | 129.4168 | 1846 | 0.016885 | 0.60788 | 1741 | 54.14 | 108
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 8860 | FALSE | 6108.7785 | 3211.911 | 1.9962 | 34 | 0.0001502 | 733 | 173.1129 | 1705 | 0.016867 | 0.57347 | 1742 | 0.03 | 2306
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 1464 | FALSE | 1371.4854 | 1371.4854 | 0.85238 | 10 | 0.00011205 | 1368 | 126.5814 | 1854 | 0.01686 | 0.1686 | 1743 | 0.09 | 1538
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | CB | FALSE | 6022.6718 | 6022.6718 | 3.7431 | 20 | 0.00011138 | 1387 | 174.7898 | 1698 | 0.016801 | 0.33603 | 1744 | 22.21 | 295
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | N32 | FALSE | 47644.4105 | 47470.9597 | 29.5034 | 251 | 5.7e-05 | 2860 | 298.1993 | 1451 | 0.016765 | 4.208 | 1745 | 0.14 | 1326
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 19582 | FALSE | 11698.5344 | 11698.5344 | 7.2707 | 80 | 0.0001731 | 541 | 110.8991 | 1908 | 0.016762 | 1.341 | 1746 | 0.2 | 1168
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 2166 | FALSE | 6559.0006 | 6559.0006 | 4.0764 | 41 | 0.00012787 | 1051 | 196.1831 | 1652 | 0.016743 | 0.68648 | 1747 | 0.04 | 2069
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | CB | FALSE | 17261.1138 | 17261.1138 | 10.7279 | 77 | 6.64e-05 | 2581 | 354.4682 | 1366 | 0.016728 | 1.2881 | 1748 | 0.09 | 1562
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 95324 | FALSE | 10430.483 | 10430.483 | 6.4826 | 40 | 0.00024711 | 226 | 97.4816 | 1970 | 0.016671 | 0.66685 | 1749 | 0.05 | 1990
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 323694 | FALSE | 10298.1869 | 10298.1869 | 6.4004 | 17 | 0.00023892 | 250 | 89.5148 | 2002 | 0.016661 | 0.28324 | 1750 |  | 3406
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 438596 | FALSE | 17736.2716 | 17736.2716 | 11.0232 | 69 | 0.00028911 | 142 | 66.1845 | 2114 | 0.016624 | 1.1471 | 1751 |  | 3135
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2002 | FALSE | 4546.6103 | 4546.6103 | 2.8257 | 27 | 9.94e-05 | 1659 | 177.0336 | 1690 | 0.01654 | 0.44657 | 1752 | 0.03 | 2271
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 804 | FALSE | 35223.4878 | 35223.4878 | 21.8915 | 163 | 9.11e-05 | 1878 | 209.4933 | 1620 | 0.016525 | 2.6936 | 1753 | 22.85 | 291
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 13496 | FALSE | 8111.7845 | 3211.8845 | 1.9962 | 58 | 8.29e-05 | 2132 | 168.1169 | 1725 | 0.016506 | 0.95734 | 1754 | 0.04 | 2107
249 | RINCON 1103CB | 43321103 | RINCON 1103 | CB | FALSE | 6066.7415 | 3931.2505 | 2.4433 | 41 | 0.00016438 | 593 | 84.7695 | 2033 | 0.016461 | 0.67489 | 1755 | 3.87 | 532
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 439030 | FALSE | 31570.1115 | 31570.1115 | 19.621 | 200 | 4.68e-05 | 3117 | 247.3908 | 1548 | 0.016434 | 3.2868 | 1756 | 0.34 | 978
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2012 | FALSE | 48303.6952 | 3708.2991 | 2.3047 | 73 | 4.25e-05 | 3218 | 610.7432 | 1094 | 0.016401 | 1.1972 | 1757 | 0.01 | 2617
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | FALSE | 6465.1165 | 6465.1165 | 4.0181 | 13 | 0.00010277 | 1576 | 122.9227 | 1861 | 0.01639 | 0.21307 | 1758 | 8.51 | 424
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 430 | FALSE | 11355.5979 | 11355.5979 | 7.0575 | 92 | 0.00013784 | 896 | 143.4477 | 1796 | 0.016311 | 1.5006 | 1759 | 1.14 | 709
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 1067 | FALSE | 1306.3843 | 1306.3843 | 0.81192 | 11 | 0.00037762 | 75 | 25.9963 | 2377 | 0.016 | 0.176 | 1760 | 0.39 | 956
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | CB | FALSE | 17781.8863 | 17449.8743 | 10.8452 | 133 | 0.00028585 | 146 | 98.8838 | 1960 | 0.015996 | 2.1275 | 1761 | 0.03 | 2400
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13430 | FALSE | 21106.6036 | 21106.6036 | 13.1178 | 129 | 3.9e-05 | 3286 | 375.4366 | 1329 | 0.015945 | 2.057 | 1762 | 23.77 | 282
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 772781 | FALSE | 2316.7745 | 2316.7745 | 1.4399 | 12 | 0.00017201 | 551 | 85.3434 | 2027 | 0.015766 | 0.1892 | 1763 |  | 3286
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 3166 | FALSE | 19778.1528 | 19778.1528 | 12.2922 | 147 | 0.00014138 | 848 | 96.7473 | 1974 | 0.015763 | 2.3172 | 1764 | 0.13 | 1348
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | CB | FALSE | 7713.2869 | 7713.2869 | 4.7938 | 20 | 0.0002169 | 332 | 123.6935 | 1859 | 0.015736 | 0.31472 | 1765 | 0.28 | 1044
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 86696 | FALSE | 15512.3886 | 15512.3886 | 9.641 | 86 | 0.00022753 | 293 | 118.1033 | 1879 | 0.015606 | 1.3421 | 1766 | 11.17 | 386
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 416 | FALSE | 26082.6279 | 26031.4486 | 16.1787 | 79 | 0.00016777 | 576 | 81.2878 | 2042 | 0.015542 | 1.2278 | 1767 | 0.36 | 968
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 3170 | FALSE | 64049.8846 | 64049.8846 | 39.8073 | 445 | 0.00014644 | 781 | 151.3568 | 1773 | 0.015534 | 6.9125 | 1768 | 0.47 | 907
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | XR332 | FALSE | 29699.1922 | 29699.1922 | 18.4582 | 83 | 7.38e-05 | 2368 | 296.6239 | 1452 | 0.015532 | 1.2892 | 1769 | 0.12 | 1374
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 8170 | FALSE | 12697.6373 | 12388.5528 | 7.6995 | 109 | 0.00012036 | 1178 | 138.0395 | 1818 | 0.015509 | 1.6904 | 1770 | 0.24 | 1094
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | CB | FALSE | 11971.7401 | 11971.7401 | 7.4405 | 18 | 8.51e-05 | 2056 | 173.0854 | 1706 | 0.015422 | 0.27759 | 1771 | 0.15 | 1279
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 338520 | FALSE | 12890.8329 | 12653.3631 | 7.8641 | 87 | 0.00011206 | 1367 | 151.4662 | 1772 | 0.015412 | 1.3409 | 1772 |  | 2737
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 1584 | FALSE | 20998.6152 | 20998.6152 | 13.0507 | 136 | 0.00015385 | 710 | 117.4189 | 1885 | 0.015387 | 2.0926 | 1773 | 0.14 | 1331
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 152 | FALSE | 16493.2298 | 2668.6977 | 1.6586 | 125 | 0.0001196 | 1193 | 103.0488 | 1937 | 0.015258 | 1.9072 | 1774 | 2.09 | 621
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 13494 | FALSE | 12093.2449 | 4454.735 | 2.7686 | 93 | 8.97e-05 | 1924 | 170.6202 | 1712 | 0.015212 | 1.4148 | 1775 | 2.55 | 598
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 383748 | TRUE | 582.318 | 582.318 | 0.36191 | 4 | 0.00011477 | 1303 | 237.7564 | 1575 | 0.015207 | 0.060827 | 1776 |  | 3542
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 6084 | FALSE | 24635.3535 | 24635.3535 | 15.311 | 120 | 0.00027675 | 166 | 46.9926 | 2233 | 0.015158 | 1.8189 | 1777 | 0.26 | 1064
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 462 | FALSE | 6310.2369 | 4550.7014 | 2.8283 | 40 | 9.83e-05 | 1683 | 125.2992 | 1858 | 0.015132 | 0.6053 | 1778 | 0.04 | 2104
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 7048 | FALSE | 47036.8755 | 18663.2877 | 11.5993 | 173 | 4.46e-05 | 3172 | 271.6147 | 1491 | 0.015069 | 2.607 | 1779 | 0.05 | 2050
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | CB | FALSE | 19625.3536 | 4723.1827 | 2.9355 | 52 | 0.00018739 | 458 | 86.4729 | 2019 | 0.015061 | 0.78316 | 1780 | 0 | 2627
10131 | CMC 1101CB | 183111101 | CMC 1101 | CB | FALSE | 3286.0633 | 3286.0633 | 2.0423 | 16 | 7.41e-05 | 2353 | 272.3255 | 1488 | 0.014989 | 0.23983 | 1781 | 0.06 | 1879
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 1462 | FALSE | 16147.0874 | 16116.0676 | 10.0162 | 51 | 0.00019151 | 435 | 137.3214 | 1821 | 0.01495 | 0.76245 | 1782 | 0.07 | 1710
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 58498 | FALSE | 3648.0777 | 1920.6562 | 1.1937 | 34 | 0.00025665 | 200 | 43.134 | 2259 | 0.01494 | 0.50797 | 1783 | 0.03 | 2375
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 65866 | FALSE | 13028.5462 | 5501.1432 | 3.419 | 65 | 4.66e-05 | 3122 | 158.5163 | 1752 | 0.014918 | 0.9697 | 1784 | 0.04 | 2201
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 549904 | TRUE | 8119.1519 | 250.4434 | 0.15565 | 54 | 6.47e-05 | 2616 | 224.282 | 1596 | 0.014902 | 0.80473 | 1785 | 1.15 | 708
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 909424 | TRUE | 642.3156 | 642.3156 | 0.3992 | 8 | 0.00010292 | 1571 | 136.9205 | 1825 | 0.014888 | 0.1191 | 1786 |  | 3602
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 749231 | FALSE | 18200.1936 | 8940.1081 | 5.5563 | 141 | 6.03e-05 | 2765 | 210.5727 | 1619 | 0.014847 | 2.0934 | 1787 |  | 3055
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 51486 | FALSE | 91205.7549 | 91205.7549 | 56.6847 | 656 | 0.00011965 | 1191 | 123.462 | 1860 | 0.014797 | 9.7068 | 1788 | 90.93 | 31
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 65574 | TRUE | 2814.0897 | 939.5268 | 0.58392 | 23 | 0.00030901 | 119 | 33.131 | 2321 | 0.014793 | 0.34024 | 1789 | 0.01 | 2582
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 37344 | TRUE | 14261.5059 | 181.3406 | 0.1127 | 75 | 2.21e-05 | 3519 | 310.2738 | 1432 | 0.014768 | 1.1076 | 1790 | 0.01 | 2575
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 1612 | FALSE | 14766.2971 | 14766.2971 | 9.1773 | 86 | 0.00012715 | 1062 | 147.1224 | 1785 | 0.014748 | 1.2683 | 1791 | 0.03 | 2352
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 665674 | TRUE | 2469.7606 | 698.7983 | 0.43431 | 20 | 0.00016815 | 574 | 82.7929 | 2037 | 0.014722 | 0.29443 | 1792 |  | 2823
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 70952 | FALSE | 2749.7949 | 2724.6488 | 1.6934 | 29 | 3.99e-05 | 3272 | 320.7855 | 1414 | 0.014692 | 0.42606 | 1793 | 0.06 | 1812
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 47964 | FALSE | 12397.0354 | 10475.6408 | 6.5107 | 68 | 0.00011035 | 1405 | 129.5748 | 1845 | 0.014662 | 0.99704 | 1794 | 0.39 | 958
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 98224 | FALSE | 3847.8762 | 3847.8762 | 2.3915 | 23 | 7.89e-05 | 2238 | 166.5531 | 1730 | 0.014654 | 0.33704 | 1795 |  | 3151
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 61602 | FALSE | 17974.447 | 15796.3436 | 9.8175 | 137 | 0.00027732 | 164 | 142.021 | 1802 | 0.014648 | 2.0068 | 1796 | 0.06 | 1802
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 2905 | FALSE | 15594.3492 | 15594.3492 | 9.692 | 83 | 0.00011324 | 1339 | 142.3421 | 1801 | 0.014648 | 1.2158 | 1797 | 0.04 | 2182
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 1006 | FALSE | 32324.6993 | 17529.4826 | 10.8946 | 266 | 0.00017105 | 556 | 184.0652 | 1676 | 0.014639 | 3.8939 | 1798 | 0.05 | 1920
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 4045 | TRUE | 3179.9108 | 576.108 | 0.35805 | 18 | 0.00013215 | 979 | 114.5305 | 1897 | 0.014618 | 0.26312 | 1799 | 0.03 | 2324
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 861266 | FALSE | 3852.0148 | 2503.894 | 1.5562 | 31 | 0.00018468 | 477 | 101.2826 | 1949 | 0.014616 | 0.45311 | 1800 |  | 3353
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 2084 | FALSE | 29723.3403 | 29723.3403 | 18.4732 | 219 | 0.00012877 | 1034 | 131.3983 | 1843 | 0.014579 | 3.1928 | 1801 | 0.11 | 1414
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 4904 | FALSE | 29337.0631 | 29337.0631 | 18.2331 | 121 | 0.00023865 | 252 | 61.1434 | 2146 | 0.014552 | 1.7608 | 1802 | 0.44 | 925
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 714370 | FALSE | 4274.3031 | 3423.0115 | 2.1274 | 28 | 8.03e-05 | 2198 | 368.3867 | 1342 | 0.014533 | 0.40694 | 1803 |  | 3083
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | XR010 | FALSE | 22011.3924 | 4483.0278 | 2.7862 | 160 | 7.87e-05 | 2242 | 168.0653 | 1726 | 0.014407 | 2.3052 | 1804 | 0.05 | 1996
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 823854 | FALSE | 6899.0553 | 3307.4207 | 2.0556 | 33 | 3.95e-05 | 3276 | 363.6041 | 1348 | 0.01437 | 0.47422 | 1805 |  | 2786
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 88772 | FALSE | 69339.2928 | 39135.7756 | 24.323 | 474 | 6.11e-05 | 2746 | 187.0188 | 1668 | 0.014358 | 6.8057 | 1806 | 0.2 | 1160
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 8852 | FALSE | 7650.5094 | 7473.9899 | 4.6451 | 46 | 0.00028421 | 148 | 54.47 | 2184 | 0.014354 | 0.66027 | 1807 | 0.05 | 1930
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 1386 | FALSE | 11052.9537 | 11052.9537 | 6.8695 | 47 | 6.35e-05 | 2661 | 296.3406 | 1453 | 0.014294 | 0.67181 | 1808 | 0.01 | 2619
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 10170 | FALSE | 26253.3221 | 26253.3221 | 16.3165 | 149 | 4.82e-05 | 3089 | 256.1773 | 1532 | 0.014293 | 2.1297 | 1809 | 83.16 | 40
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 5661 | FALSE | 8173.4897 | 4658.2663 | 2.8951 | 66 | 8.64e-05 | 2026 | 169.0465 | 1721 | 0.014289 | 0.94309 | 1810 | 1.66 | 657
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 4817 | FALSE | 5079.2964 | 5079.2964 | 3.1568 | 42 | 0.00011215 | 1364 | 172.256 | 1709 | 0.019666 | 0.82599 | 1677 | 8.13 | 436
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 2718 | TRUE | 11657.4654 | 495.6422 | 0.30804 | 114 | 0.00022728 | 295 | 102.6178 | 1938 | 0.014276 | 1.6275 | 1812 | 0.04 | 2074
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | V18 | FALSE | 6444.7052 | 4344.0922 | 2.6999 | 41 | 3.61e-05 | 3335 | 204.0579 | 1633 | 0.014215 | 0.5828 | 1813 | 0.08 | 1634
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 7038 | FALSE | 35749.3708 | 29491.4615 | 18.3291 | 186 | 5.65e-05 | 2873 | 250.588 | 1538 | 0.014161 | 2.6339 | 1814 | 0.12 | 1392
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 77204 | FALSE | 11918.386 | 11918.386 | 7.4073 | 68 | 0.00011817 | 1226 | 128.4194 | 1848 | 0.014094 | 0.95841 | 1815 |  | 2893
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | CB | FALSE | 7292.0294 | 7292.0294 | 4.532 | 7 | 0.00010421 | 1546 | 1059.6264 | 793 | 0.01407 | 0.098493 | 1816 | 0.03 | 2309
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | CB | FALSE | 7034.6563 | 7034.6563 | 4.3721 | 40 | 0.00012824 | 1044 | 93.9669 | 1986 | 0.014057 | 0.5623 | 1817 | 38.69 | 195
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 60094 | FALSE | 15867.8414 | 15867.8414 | 9.8619 | 95 | 0.00016876 | 569 | 93.9049 | 1987 | 0.014041 | 1.3339 | 1818 | 55.68 | 102
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 67898 | FALSE | 9738.6344 | 6917.4777 | 4.2992 | 70 | 0.00010226 | 1597 | 138.197 | 1816 | 0.014037 | 0.98259 | 1819 | 0.06 | 1819
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 613456 | FALSE | 38029.4611 | 21637.0644 | 13.4475 | 145 | 5.87e-05 | 2815 | 256.2574 | 1531 | 0.014028 | 2.0341 | 1820 |  | 3187
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 5012 | FALSE | 17904.0624 | 17904.0624 | 11.1274 | 131 | 0.00021567 | 337 | 62.8252 | 2137 | 0.014012 | 1.8356 | 1821 | 0.09 | 1569
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 11244 | FALSE | 34513.2878 | 33294.1457 | 20.6924 | 202 | 0.00014416 | 812 | 70.2755 | 2093 | 0.01399 | 2.826 | 1822 | 0.12 | 1385
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 79086 | FALSE | 11075.7434 | 10954.594 | 6.8083 | 82 | 0.00011015 | 1408 | 169.8424 | 1717 | 0.018179 | 1.4907 | 1701 | 0.08 | 1638
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 337126 | FALSE | 3227.6651 | 1128.521 | 0.70138 | 28 | 3.3e-05 | 3386 | 257.5116 | 1527 | 0.013964 | 0.39101 | 1824 |  | 3051
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 280 | FALSE | 10907.0769 | 1106.406 | 0.68764 | 52 | 6.72e-05 | 2553 | 180.7486 | 1682 | 0.013918 | 0.72376 | 1825 | 0.72 | 800
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | CB | FALSE | 23959.1283 | 5020.5865 | 3.1203 | 191 | 0.00012086 | 1166 | 54.2982 | 2185 | 0.007993 | 1.5267 | 2048 | 0.11 | 1429
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 246 | FALSE | 21497.7557 | 21497.7557 | 13.3609 | 148 | 0.00011216 | 1363 | 98.1055 | 1967 | 0.010561 | 1.563 | 1937 | 6.5 | 466
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 1320 | FALSE | 32275.3239 | 31878.2376 | 19.8125 | 179 | 0.00033316 | 101 | 41.1443 | 2271 | 0.013687 | 2.4499 | 1828 | 0.21 | 1149
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | CB | FALSE | 34051.8134 | 34051.8134 | 21.1633 | 240 | 0.00019472 | 419 | 88.9032 | 2008 | 0.01359 | 3.2616 | 1829 | 21.63 | 299
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 135762 | FALSE | 4515.3768 | 1189.5286 | 0.7393 | 28 | 9.64e-05 | 1723 | 173.1219 | 1704 | 0.013539 | 0.3791 | 1830 |  | 3246
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 1322 | FALSE | 30035.9017 | 25851.0688 | 16.0665 | 81 | 4.47e-05 | 3169 | 378.0361 | 1324 | 0.01351 | 1.0943 | 1831 | 0.03 | 2289
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | CB | FALSE | 5107.0559 | 3866.6599 | 2.4031 | 37 | 0.00013283 | 961 | 86.715 | 2017 | 0.013499 | 0.49946 | 1832 | 0.57 | 862
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 261774 | FALSE | 21761.0718 | 21761.0718 | 13.5246 | 142 | 9.99e-05 | 1650 | 183.8239 | 1678 | 0.01783 | 2.5319 | 1712 |  | 2952
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 510 | FALSE | 11861.6385 | 11861.6385 | 7.3721 | 77 | 0.00017549 | 525 | 112.7525 | 1903 | 0.013466 | 1.0369 | 1834 | 48.83 | 124
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 920 | FALSE | 42024.2659 | 28596.0082 | 17.7725 | 258 | 8.96e-05 | 1925 | 168.9827 | 1722 | 0.013411 | 3.4601 | 1835 | 0.09 | 1572
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 4624 | TRUE | 6101.7647 | 50.6724 | 0.031493 | 42 | 0.00012548 | 1090 | 117.1975 | 1886 | 0.013292 | 0.55825 | 1836 | 0.02 | 2483
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 516 | FALSE | 17602.5759 | 17602.5759 | 10.9401 | 135 | 0.00019441 | 420 | 70.1443 | 2094 | 0.013281 | 1.7929 | 1837 | 1.39 | 679
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 942143 | FALSE | 13604.5625 | 8138.4591 | 5.0581 | 74 | 0.00011237 | 1358 | 105.0805 | 1928 | 0.013216 | 0.97798 | 1838 |  | 3068
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 83354 | FALSE | 8260.8147 | 8260.8147 | 5.1341 | 36 | 5.43e-05 | 2936 | 210.679 | 1618 | 0.013182 | 0.47457 | 1839 | 0.05 | 1967
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 38868 | FALSE | 6917.0796 | 3119.1276 | 1.9386 | 61 | 0.00010371 | 1555 | 103.4846 | 1934 | 0.01315 | 0.80215 | 1840 | 0.02 | 2534
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | CB | TRUE | 26.5151 | 26.5151 | 0.016479 | 1 | 7.89e-05 | 2240 | 166.4117 | 1731 | 0.013124 | 0.013124 | 1841 | 0.04 | 2184
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | CB | FALSE | 10780.8577 | 1904.2009 | 1.1835 | 85 | 9e-05 | 1911 | 158.1087 | 1753 | 0.013117 | 1.115 | 1842 | 0.05 | 2028
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | CB | FALSE | 2138.4101 | 1870.8826 | 1.1628 | 21 | 0.00038645 | 70 | 21.5686 | 2432 | 0.013096 | 0.27501 | 1843 | 20.42 | 305
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 296492 | FALSE | 3708.9492 | 1270.5979 | 0.78968 | 29 | 7.45e-05 | 2344 | 198.5181 | 1644 | 0.013092 | 0.37968 | 1844 |  | 3311
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 858388 | FALSE | 13234.6519 | 7717.2675 | 4.7963 | 72 | 2.67e-05 | 3476 | 315.5206 | 1423 | 0.013047 | 0.93942 | 1845 |  | 2860
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 3383 | FALSE | 3031.9376 | 2267.9133 | 1.4095 | 24 | 0.00010952 | 1421 | 99.0724 | 1957 | 0.012944 | 0.31066 | 1846 | 0.05 | 2040
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 97982 | FALSE | 15545.7354 | 15545.7354 | 9.6617 | 104 | 8.31e-05 | 2130 | 187.9326 | 1666 | 0.012892 | 1.3407 | 1847 | 33.04 | 223
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 371694 | TRUE | 6199.8125 | 365.7311 | 0.2273 | 40 | 6.86e-05 | 2519 | 205.0285 | 1628 | 0.012819 | 0.51277 | 1848 |  | 3089
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 1974 | FALSE | 36068.6353 | 36068.6353 | 22.4168 | 259 | 8.2e-05 | 2154 | 157.702 | 1756 | 0.012814 | 3.3188 | 1849 | 125.77 | 11
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 3052 | FALSE | 25170.0534 | 20257.093 | 12.5899 | 163 | 9.54e-05 | 1745 | 138.2678 | 1815 | 0.012795 | 2.0855 | 1850 | 0.66 | 820
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | LB48 | FALSE | 23668.374 | 23668.374 | 14.71 | 142 | 0.0001412 | 849 | 89.798 | 2000 | 0.012757 | 1.8115 | 1851 | 0.79 | 776
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | MR190 | FALSE | 18265.303 | 1336.9264 | 0.83091 | 130 | 5.63e-05 | 2880 | 303.8443 | 1444 | 0.012744 | 1.6567 | 1852 | 0.03 | 2386
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | CB | FALSE | 17493.6949 | 8660.4867 | 5.3825 | 20 | 9.47e-05 | 1773 | 120.7431 | 1868 | 0.012742 | 0.25483 | 1853 |  | 3269
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 10140 | FALSE | 26724.0842 | 26724.0842 | 16.6091 | 188 | 8.93e-05 | 1937 | 119.5136 | 1871 | 0.012696 | 2.3869 | 1854 | 1.03 | 724
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 10040 | FALSE | 28379.0201 | 28379.0201 | 17.6377 | 213 | 7.35e-05 | 2385 | 189.319 | 1665 | 0.01266 | 2.6967 | 1855 | 0.64 | 829
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 640 | FALSE | 5054.3067 | 1636.7685 | 1.0173 | 43 | 9.15e-05 | 1857 | 103.5522 | 1933 | 0.012658 | 0.54429 | 1856 | 0.06 | 1786
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 5739 | FALSE | 10731.8696 | 10731.8696 | 6.6699 | 74 | 0.00014982 | 740 | 107.9805 | 1917 | 0.012582 | 0.93104 | 1857 | 0.05 | 2052
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | A06 | TRUE | 3295.4951 | 441.6127 | 0.27446 | 27 | 6.13e-05 | 2740 | 154.3644 | 1764 | 0.012566 | 0.33927 | 1858 | 23.54 | 284
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 40666 | TRUE | 2641.929 | 575.1734 | 0.35747 | 18 | 0.00018607 | 467 | 44.5439 | 2250 | 0.012564 | 0.22615 | 1859 | 0.03 | 2374
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 113082 | FALSE | 11746.8209 | 9857.3648 | 6.1264 | 75 | 8.95e-05 | 1932 | 142.6253 | 1799 | 0.012535 | 0.94012 | 1860 |  | 3001
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 2096 | FALSE | 22772.919 | 22772.919 | 14.1535 | 129 | 9.88e-05 | 1675 | 133.1159 | 1838 | 0.012531 | 1.6166 | 1861 | 53.86 | 110
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 663244 | TRUE | 704.8457 | 464.3934 | 0.28862 | 6 | 6.41e-05 | 2640 | 270.589 | 1495 | 0.012526 | 0.075153 | 1862 |  | 3250
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 37202 | FALSE | 46485.9705 | 40065.4374 | 24.9008 | 190 | 0.00062222 | 16 | 17.2008 | 2500 | 0.012512 | 2.3773 | 1863 | 0.05 | 1933
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | LB44 | FALSE | 31139.8726 | 31139.8726 | 19.3536 | 213 | 0.00014639 | 783 | 100.8516 | 1950 | 0.012499 | 2.6623 | 1864 | 1.29 | 690
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 1802 | FALSE | 35771.0229 | 35771.0229 | 22.2318 | 259 | 0.00015681 | 674 | 79.811 | 2049 | 0.012496 | 3.2365 | 1865 | 95.5 | 25
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 465074 | FALSE | 7662.1855 | 7662.1855 | 4.7621 | 57 | 0.00013238 | 976 | 95.1304 | 1981 | 0.012495 | 0.7122 | 1866 |  | 2986
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 200856 | FALSE | 4144.4334 | 4144.4334 | 2.5758 | 31 | 0.00022223 | 311 | 73.6449 | 2076 | 0.012452 | 0.38602 | 1867 |  | 3102
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 7632 | FALSE | 13210.2353 | 3566.1023 | 2.2163 | 35 | 2.9e-05 | 3441 | 263.7953 | 1512 | 0.012428 | 0.43499 | 1868 | 0.01 | 2590
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 526864 | FALSE | 5659.7355 | 5008.6837 | 3.1129 | 18 | 5.26e-05 | 2980 | 261.8161 | 1518 | 0.012408 | 0.22335 | 1869 |  | 2901
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 649874 | TRUE | 608.4651 | 608.4651 | 0.37816 | 5 | 0.00011808 | 1227 | 142.79 | 1797 | 0.012324 | 0.061618 | 1870 |  | 3543
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 5078 | FALSE | 23873.1972 | 23873.1972 | 14.8373 | 154 | 0.00030756 | 121 | 41.9114 | 2267 | 0.012313 | 1.8962 | 1871 | 17.59 | 330
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | CB | FALSE | 37542.2534 | 4224.1485 | 2.6253 | 255 | 0.00013212 | 981 | 102.3882 | 1942 | 0.012302 | 3.1369 | 1872 | 0.03 | 2408
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 3094 | FALSE | 14546.7613 | 6578.8406 | 4.0888 | 63 | 6.41e-05 | 2641 | 239.8109 | 1568 | 0.012298 | 0.77477 | 1873 | 0.06 | 1850
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | CB | FALSE | 26652.3351 | 26652.3351 | 16.5645 | 128 | 0.00011861 | 1214 | 102.4016 | 1941 | 0.012215 | 1.5636 | 1874 | 82.53 | 43
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 976553 | FALSE | 3112.5676 | 1744.6035 | 1.0843 | 20 | 6.7e-05 | 2557 | 174.5173 | 1699 | 0.012197 | 0.24394 | 1875 |  | 3407
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | CB | FALSE | 14175.8367 | 14066.7084 | 8.7425 | 88 | 0.00026507 | 182 | 43.8173 | 2253 | 0.012162 | 1.0703 | 1876 | 27.97 | 254
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 317782 | TRUE | 6689.8142 | 874.1929 | 0.54331 | 53 | 0.00012534 | 1092 | 127.094 | 1852 | 0.012141 | 0.64349 | 1877 |  | 2852
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6014 | FALSE | 19985.2036 | 9962.9662 | 6.192 | 106 | 7.66e-05 | 2291 | 149.4232 | 1779 | 0.012138 | 1.2867 | 1878 | 0.02 | 2473
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 676164 | TRUE | 4417.8948 | 487.5008 | 0.30298 | 26 | 4.55e-05 | 3152 | 245.9244 | 1551 | 0.012062 | 0.3136 | 1879 |  | 3115
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | CB | FALSE | 10098.7974 | 10098.7974 | 6.2764 | 73 | 0.000256 | 203 | 35.5525 | 2306 | 0.01204 | 0.87889 | 1880 | 11.22 | 385
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 411508 | TRUE | 731.3696 | 726.7977 | 0.45171 | 6 | 0.00014592 | 790 | 114.8976 | 1896 | 0.012026 | 0.072157 | 1881 |  | 3464
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 466 | TRUE | 2421.8686 | 622.9644 | 0.38717 | 21 | 0.00011297 | 1345 | 121.2049 | 1867 | 0.01202 | 0.25243 | 1882 |  | 2947
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 329930 | FALSE | 19740.5748 | 10526.1812 | 6.5421 | 137 | 0.00012563 | 1085 | 89.3966 | 2004 | 0.012012 | 1.6456 | 1883 | 0.03 | 2300
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 539450 | FALSE | 3896.0108 | 2403.5482 | 1.4938 | 28 | 9.12e-05 | 1874 | 148.5497 | 1781 | 0.011978 | 0.33537 | 1884 |  | 2917
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 2768 | FALSE | 13051.8561 | 12269.0577 | 7.6253 | 88 | 0.00012814 | 1045 | 88.7266 | 2009 | 0.011963 | 1.0528 | 1885 | 7.41 | 445
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 587857 | TRUE | 3120.9828 | 171.8621 | 0.10681 | 28 | 8.57e-05 | 2038 | 73.8505 | 2073 | 0.011944 | 0.33442 | 1886 |  | 3211
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 11800 | FALSE | 15325.4468 | 15325.4468 | 9.5248 | 116 | 9.12e-05 | 1873 | 242.093 | 1561 | 0.011866 | 1.3764 | 1887 | 49.43 | 123
2749 | ELK 1101900 | 42981101 | ELK 1101 | 900 | FALSE | 34419.9463 | 14125.5477 | 8.7791 | 185 | 5.55e-05 | 2901 | 228.3452 | 1591 | 0.011859 | 2.1939 | 1888 | 0.01 | 2598
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 2646 | FALSE | 28413.9838 | 28413.9838 | 17.6594 | 149 | 0.00010253 | 1586 | 176.2359 | 1694 | 0.01184 | 1.7642 | 1889 |  | 2720
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 386844 | TRUE | 2561.2262 | 615.6019 | 0.3826 | 19 | 4.56e-05 | 3150 | 232.4795 | 1583 | 0.01183 | 0.22478 | 1890 |  | 3226
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | XR264 | TRUE | 33068.0694 | 0 | 0 | 258 | 7.96e-05 | 2219 | 168.5722 | 1723 | 0.011726 | 3.0254 | 1891 | 0.77 | 783
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 968652 | FALSE | 3017.7923 | 1606.1834 | 0.99825 | 25 | 0.00010466 | 1539 | 114.1474 | 1898 | 0.011684 | 0.2921 | 1892 |  | 2946
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 63598 | FALSE | 3076.8023 | 3076.8023 | 1.9122 | 24 | 0.0001935 | 427 | 74.3537 | 2071 | 0.011681 | 0.28035 | 1893 | 50.16 | 120
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 870444 | FALSE | 4770.1261 | 4746.504 | 2.95 | 35 | 0.00012787 | 1050 | 122.3071 | 1864 | 0.011666 | 0.40831 | 1894 |  | 3038
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 716 | FALSE | 14319.9438 | 14319.9438 | 8.8999 | 109 | 0.00010523 | 1513 | 113.9799 | 1900 | 0.01165 | 1.2698 | 1895 | 14.14 | 357
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 350336 | FALSE | 2699.1632 | 1936.9418 | 1.2038 | 13 | 7.76e-05 | 2276 | 139.0255 | 1813 | 0.011629 | 0.15117 | 1896 |  | 3323
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 809986 | FALSE | 3460.671 | 1661.0044 | 1.0323 | 18 | 4.76e-05 | 3100 | 119.23 | 1872 | 0.011626 | 0.20927 | 1897 |  | 3484
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 98374 | FALSE | 6103.4021 | 1330.8093 | 0.8271 | 46 | 0.00011986 | 1189 | 56.1694 | 2175 | 0.011616 | 0.53436 | 1898 | 0.02 | 2442
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 91424 | TRUE | 14089.3649 | 303.1658 | 0.18842 | 95 | 6.4e-05 | 2646 | 160.2049 | 1745 | 0.01155 | 1.0973 | 1899 | 0.02 | 2546
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 262 | FALSE | 9547.2777 | 2067.1657 | 1.2848 | 61 | 0.00010047 | 1637 | 112.2285 | 1905 | 0.011548 | 0.70445 | 1900 | 0.05 | 1983
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 247660 | FALSE | 5200.0544 | 3858.4886 | 2.3981 | 35 | 8.36e-05 | 2111 | 144.077 | 1794 | 0.011541 | 0.40392 | 1901 |  | 2689
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 2210 | FALSE | 36938.5346 | 36938.5346 | 22.9574 | 280 | 9.26e-05 | 1829 | 84.7902 | 2032 | 0.01151 | 3.2229 | 1902 | 105.34 | 19
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 5480 | FALSE | 27352.0687 | 27352.0687 | 16.9994 | 180 | 7.08e-05 | 2447 | 169.2363 | 1720 | 0.011505 | 2.0709 | 1903 | 0.6 | 854
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 1360 | FALSE | 36445.2787 | 36106.6297 | 22.4404 | 92 | 4.89e-05 | 3066 | 304.0594 | 1443 | 0.011504 | 1.0584 | 1904 | 0.01 | 2568
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | XR044 | TRUE | 3013.9349 | 677.8018 | 0.42126 | 18 | 0.00010854 | 1434 | 79.5829 | 2050 | 0.011436 | 0.20585 | 1905 | 0.02 | 2555
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 1419 | FALSE | 24160.9517 | 24160.9517 | 15.0161 | 130 | 6.25e-05 | 2706 | 145.1035 | 1792 | 0.011428 | 1.4856 | 1906 | 0.17 | 1249
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 324510 | FALSE | 20073.6016 | 20073.6016 | 12.4758 | 154 | 6.25e-05 | 2702 | 194.5257 | 1656 | 0.011404 | 1.7562 | 1907 | 0.14 | 1320
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 10050 | FALSE | 11290.6239 | 11290.6239 | 7.0172 | 81 | 9.83e-05 | 1684 | 101.871 | 1946 | 0.01137 | 0.92095 | 1908 | 0.52 | 888
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 93116 | FALSE | 68103.7314 | 68103.7314 | 42.3267 | 453 | 9.12e-05 | 1872 | 118.4962 | 1875 | 0.011348 | 5.1406 | 1909 | 26.17 | 268
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | CB | FALSE | 27455.7877 | 6641.9361 | 4.128 | 121 | 2.94e-05 | 3434 | 158.5842 | 1751 | 0.011318 | 1.3695 | 1910 | 0.05 | 2010
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 51788 | FALSE | 20901.6945 | 8188.5748 | 5.0892 | 153 | 0.00012561 | 1087 | 89.1639 | 2005 | 0.011264 | 1.7234 | 1911 | 0.7 | 807
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 9032 | FALSE | 37853.3581 | 36827.5633 | 22.8885 | 175 | 3.61e-05 | 3334 | 413.8546 | 1280 | 0.011207 | 1.9611 | 1912 | 0.02 | 2552
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 4622 | FALSE | 21650.6648 | 21650.6648 | 13.456 | 109 | 0.00028635 | 145 | 73.5891 | 2077 | 0.011136 | 1.2138 | 1913 | 0.1 | 1454
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | MR243 | FALSE | 8929.805 | 8929.805 | 5.5499 | 72 | 8.9e-05 | 1946 | 128.0484 | 1849 | 0.011084 | 0.79807 | 1914 |  | 2988
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 429574 | FALSE | 15346.7415 | 8004.0474 | 4.9745 | 114 | 0.00019074 | 439 | 99.3413 | 1955 | 0.011083 | 1.2634 | 1915 |  | 2857
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | CB | FALSE | 13124.836 | 11515.5312 | 7.1569 | 82 | 7.37e-05 | 2370 | 185.6036 | 1669 | 0.011075 | 0.90815 | 1916 | 0.07 | 1709
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 8896 | FALSE | 2488.0112 | 1537.9857 | 0.95586 | 14 | 0.00022997 | 285 | 52.1302 | 2200 | 0.011065 | 0.15491 | 1917 | 2.98 | 570
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 42896 | FALSE | 8829.785 | 3686.5968 | 2.2912 | 71 | 0.00019577 | 414 | 80.3834 | 2046 | 0.011029 | 0.78303 | 1918 | 0.04 | 2101
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 304826 | FALSE | 14243.5781 | 8398.3076 | 5.2196 | 61 | 1.86e-05 | 3558 | 384.6024 | 1312 | 0.010995 | 0.6707 | 1919 |  | 2949
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | CB | FALSE | 17461.9206 | 17461.9206 | 10.8527 | 136 | 0.00014936 | 745 | 159.9625 | 1746 | 0.010952 | 1.4895 | 1920 | 17.74 | 329
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 2560 | FALSE | 26913.6158 | 26913.6158 | 16.7269 | 179 | 8.96e-05 | 1928 | 135.7772 | 1829 | 0.010913 | 1.9534 | 1921 | 75.77 | 57
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 613562 | FALSE | 9602.6341 | 5945.3079 | 3.695 | 29 | 4.48e-05 | 3166 | 198.1499 | 1645 | 0.010904 | 0.31622 | 1922 |  | 3204
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 189602 | FALSE | 1011.2208 | 1011.2208 | 0.62848 | 9 | 0.00010514 | 1518 | 134.7619 | 1833 | 0.010902 | 0.098117 | 1923 |  | 3183
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 33542 | FALSE | 4316.4835 | 4316.4835 | 2.6827 | 39 | 0.00031343 | 114 | 29.934 | 2346 | 0.010901 | 0.42515 | 1924 | 20.17 | 307
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 37848 | FALSE | 9580.5994 | 9580.5994 | 5.9544 | 60 | 7.17e-05 | 2430 | 176.9482 | 1691 | 0.010901 | 0.65406 | 1925 | 39.39 | 189
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3891 | FALSE | 5583.0951 | 5583.0951 | 3.4699 | 23 | 0.0002266 | 300 | 68.3151 | 2101 | 0.010887 | 0.2504 | 1926 | 21.8 | 297
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 341542 | FALSE | 10584.332 | 9768.7602 | 6.0713 | 47 | 8.72e-05 | 2009 | 161.0484 | 1744 | 0.010885 | 0.5116 | 1927 |  | 3412
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 7514 | FALSE | 16121.906 | 14595.7178 | 9.0713 | 118 | 0.00025507 | 206 | 51.2832 | 2206 | 0.010882 | 1.2841 | 1928 | 4.42 | 519
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 999 | FALSE | 1412.3755 | 1412.3755 | 0.8778 | 7 | 0.00015392 | 709 | 122.3126 | 1863 | 0.010787 | 0.075506 | 1929 | 28.44 | 250
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 492068 | FALSE | 13334.8935 | 11954.6281 | 7.4298 | 75 | 6.93e-05 | 2495 | 169.7517 | 1718 | 0.010772 | 0.80789 | 1930 |  | 2812
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 84572 | TRUE | 3629.8323 | 844.7995 | 0.52505 | 27 | 6.15e-05 | 2735 | 146.1205 | 1788 | 0.010769 | 0.29075 | 1931 | 0.05 | 2022
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 893 | TRUE | 16957.7992 | 312.2303 | 0.19405 | 91 | 8.78e-05 | 1990 | 114.1416 | 1899 | 0.010724 | 0.9759 | 1932 | 0.02 | 2482
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 1650 | FALSE | 34931.9743 | 34931.9743 | 21.7104 | 154 | 4.74e-05 | 3105 | 252.2302 | 1537 | 0.010701 | 1.6479 | 1933 | 0.12 | 1379
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 97086 | FALSE | 41345.0987 | 41345.0987 | 25.6961 | 301 | 7.76e-05 | 2275 | 132.4839 | 1840 | 0.010689 | 3.2174 | 1934 | 48.08 | 132
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 591122 | TRUE | 748.6821 | 748.6821 | 0.46531 | 7 | 0.00022033 | 319 | 51.0001 | 2207 | 0.010649 | 0.074542 | 1935 |  | 3085
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 91216 | FALSE | 65291.6361 | 65291.6361 | 40.579 | 380 | 8.97e-05 | 1922 | 143.7419 | 1795 | 0.010587 | 4.0231 | 1936 | 0.25 | 1085
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 448 | FALSE | 14554.2556 | 3932.5973 | 2.4441 | 116 | 9.73e-05 | 1707 | 15.8508 | 2519 | 0.001256 | 0.1457 | 2592 |  | 2652
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 3088 | FALSE | 24808.0862 | 24808.0862 | 15.4183 | 175 | 7.2e-05 | 2415 | 135.1128 | 1831 | 0.010503 | 1.8381 | 1938 | 0.12 | 1369
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | CB | FALSE | 37414.4172 | 25753.259 | 16.0058 | 153 | 5.56e-05 | 2899 | 155.1527 | 1763 | 0.010468 | 1.6015 | 1939 | 0.06 | 1833
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 97816 | FALSE | 8457.2763 | 8457.2763 | 5.2562 | 50 | 4.7e-05 | 3114 | 169.4239 | 1719 | 0.010402 | 0.52009 | 1940 | 0.19 | 1193
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 47968 | FALSE | 65100.4862 | 65100.4862 | 40.4602 | 306 | 5.72e-05 | 2856 | 229.0575 | 1588 | 0.010385 | 3.1777 | 1941 | 0.12 | 1380
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 60024 | FALSE | 6398.0407 | 6398.0407 | 3.9764 | 27 | 8.43e-05 | 2081 | 118.0471 | 1880 | 0.010381 | 0.28029 | 1942 | 22.82 | 292
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 94936 | FALSE | 14750.2856 | 14750.2856 | 9.1674 | 82 | 0.00010473 | 1535 | 117.7375 | 1883 | 0.010365 | 0.84992 | 1943 | 0.07 | 1716
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 808 | FALSE | 9941.3745 | 9941.3745 | 6.1786 | 23 | 8.88e-05 | 1958 | 107.5525 | 1920 | 0.010361 | 0.23829 | 1944 | 0.23 | 1116
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 706399 | TRUE | 1848.7276 | 537.9717 | 0.33435 | 16 | 4.87e-05 | 3069 | 204.8708 | 1630 | 0.010338 | 0.1654 | 1945 |  | 3173
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 19752 | FALSE | 58764.7318 | 58764.7318 | 36.5225 | 436 | 0.00017226 | 548 | 104.6256 | 1929 | 0.0103 | 4.4909 | 1946 | 119.92 | 12
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 131568 | FALSE | 7881.7386 | 6658.8017 | 4.1385 | 57 | 0.00013576 | 921 | 77.208 | 2060 | 0.010281 | 0.58604 | 1947 |  | 2951
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 38632 | FALSE | 7538.4158 | 7535.3678 | 4.6833 | 58 | 0.00018341 | 485 | 125.725 | 1857 | 0.010245 | 0.59423 | 1948 | 0.22 | 1128
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 337220 | FALSE | 8725.086 | 7959.8917 | 4.9471 | 28 | 0.00012555 | 1088 | 76.0082 | 2062 | 0.010237 | 0.28665 | 1949 |  | 3451
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | CB | FALSE | 37377.2089 | 37377.2089 | 23.2301 | 171 | 0.00013678 | 910 | 60.8273 | 2149 | 0.010207 | 1.7454 | 1950 | 66.07 | 74
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 70198 | FALSE | 5102.4847 | 3628.2739 | 2.255 | 36 | 9.83e-05 | 1685 | 164.1355 | 1736 | 0.010197 | 0.36709 | 1951 | 0.07 | 1763
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 400 | FALSE | 1650.11 | 1410.4889 | 0.87662 | 14 | 7.97e-05 | 2214 | 97.4469 | 1971 | 0.010195 | 0.14273 | 1952 | 0.05 | 2066
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 37426 | FALSE | 8142.4343 | 1270.4089 | 0.78956 | 65 | 4.65e-05 | 3126 | 164.8689 | 1735 | 0.010169 | 0.66101 | 1953 | 0.25 | 1079
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 4004 | FALSE | 32627.9425 | 14083.7966 | 8.7531 | 180 | 5.37e-05 | 2948 | 159.4123 | 1748 | 0.010124 | 1.8224 | 1954 | 0.05 | 1947
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 1280 | FALSE | 13974.6466 | 13812.836 | 8.5847 | 111 | 0.00015949 | 648 | 83.4065 | 2034 | 0.010109 | 1.1221 | 1955 | 0.14 | 1310
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | L3355 | FALSE | 3618.1853 | 3618.1853 | 2.2487 | 27 | 8.18e-05 | 2161 | 67.8566 | 2102 | 0.010104 | 0.2728 | 1956 | 44.71 | 155
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 95016 | FALSE | 7771.8455 | 1223.0109 | 0.76011 | 69 | 5.71e-05 | 2857 | 109.0983 | 1914 | 0.010066 | 0.69458 | 1957 | 0.02 | 2499
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 2474 | FALSE | 13467.3498 | 13410.8685 | 8.3349 | 83 | 3.62e-05 | 3329 | 276.607 | 1482 | 0.010035 | 0.83287 | 1958 | 10.79 | 394
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 414 | FALSE | 35132.3675 | 2113.8048 | 1.3137 | 260 | 5.6e-05 | 2889 | 105.7924 | 1925 | 0.009991 | 2.5977 | 1959 | 1.9 | 632
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | CB | FALSE | 4118.8768 | 4062.5857 | 2.5249 | 34 | 0.00043164 | 58 | 21.0417 | 2435 | 0.0099584 | 0.33859 | 1960 | 0.39 | 952
10564 | WISE 110163199 | 152271101 | WISE 1101 | 63199 | TRUE | 1501.4082 | 989.41 | 0.61492 | 8 | 0.00018345 | 483 | 115.9454 | 1891 | 0.0099235 | 0.079388 | 1961 | 0.04 | 2215
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | XR292 | FALSE | 19536.8147 | 17975.9221 | 11.1721 | 130 | 6.47e-05 | 2615 | 181.5173 | 1680 | 0.0098996 | 1.287 | 1962 | 0.15 | 1292
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 528 | FALSE | 6520.0631 | 5521.142 | 3.4314 | 50 | 8.13e-05 | 2172 | 173.339 | 1701 | 0.013987 | 0.69934 | 1823 | 0.08 | 1607
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | W26 | FALSE | 4390.419 | 4390.419 | 2.7287 | 18 | 6.75e-05 | 2549 | 162.1198 | 1741 | 0.0098794 | 0.17783 | 1964 | 0.05 | 1956
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 1131 | FALSE | 4424.1224 | 4424.1224 | 2.7496 | 33 | 8.14e-05 | 2171 | 131.8339 | 1842 | 0.0098607 | 0.3254 | 1965 | 3.76 | 535
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 568 | FALSE | 20285.8832 | 20285.8832 | 12.6078 | 129 | 0.00011941 | 1198 | 98.3927 | 1966 | 0.0098399 | 1.2694 | 1966 | 40.01 | 186
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 4008 | FALSE | 56919.5652 | 56919.5652 | 35.3757 | 138 | 4.96e-05 | 3045 | 221.1468 | 1603 | 0.0097859 | 1.3505 | 1967 | 0.04 | 2151
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 5002 | FALSE | 22234.4783 | 21939.7249 | 13.6356 | 161 | 0.00029646 | 133 | 37.2556 | 2295 | 0.0097721 | 1.5733 | 1968 | 18.45 | 322
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 52456 | FALSE | 16414.576 | 16414.576 | 10.2017 | 96 | 0.00013704 | 907 | 96.4288 | 1977 | 0.0097493 | 0.93593 | 1969 | 0.06 | 1899
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 965598 | FALSE | 25622.1563 | 14815.8266 | 9.2081 | 139 | 4.38e-05 | 3194 | 205.6396 | 1624 | 0.0097442 | 1.3544 | 1970 |  | 2894
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 203504 | TRUE | 514.0425 | 226.4943 | 0.14077 | 4 | 0.00021969 | 325 | 71.3633 | 2088 | 0.0097327 | 0.038931 | 1971 |  | 3389
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 742 | FALSE | 2084.4879 | 2084.4879 | 1.2955 | 21 | 0.00010714 | 1469 | 98.5688 | 1964 | 0.009698 | 0.20366 | 1972 | 0.02 | 2502
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 2208 | FALSE | 20533.4109 | 18971.647 | 11.791 | 159 | 0.0001453 | 800 | 55.2252 | 2180 | 0.0096885 | 1.5405 | 1973 | 0.15 | 1278
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 13532 | FALSE | 8576.7798 | 8576.7798 | 5.3305 | 46 | 9.99e-05 | 1652 | 99.3016 | 1956 | 0.0096754 | 0.44507 | 1974 | 0 | 2625
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 5120 | FALSE | 9912.3897 | 9912.3897 | 6.1606 | 19 | 7.76e-05 | 2273 | 140.142 | 1809 | 0.0096488 | 0.18333 | 1975 | 15.79 | 345
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 539980 | TRUE | 697.2903 | 474.6546 | 0.295 | 4 | 0.0001397 | 874 | 59.5974 | 2157 | 0.0096291 | 0.038517 | 1976 |  | 2837
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 617828 | FALSE | 4970.4215 | 2303.2847 | 1.4315 | 28 | 9.45e-05 | 1777 | 105.7723 | 1926 | 0.0096279 | 0.26958 | 1977 |  | 2776
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 380686 | FALSE | 4931.6119 | 3014.5331 | 1.8735 | 34 | 0.00017304 | 543 | 55.7388 | 2176 | 0.0095954 | 0.32624 | 1978 |  | 2938
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 1243 | FALSE | 8319.7013 | 8319.7013 | 5.1707 | 50 | 9.2e-05 | 1845 | 108.0493 | 1916 | 0.0095359 | 0.47679 | 1979 |  | 2768
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 467560 | FALSE | 3279.179 | 3279.179 | 2.038 | 27 | 0.0002791 | 159 | 44.0774 | 2252 | 0.009532 | 0.25736 | 1980 |  | 2891
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 728460 | FALSE | 2312.7117 | 1173.0161 | 0.72903 | 17 | 9.98e-05 | 1653 | 103.6058 | 1932 | 0.0095302 | 0.16201 | 1981 |  | 3014
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 19622 | FALSE | 18790.8494 | 9040.145 | 5.6185 | 165 | 0.00016432 | 596 | 119.9283 | 1869 | 0.0095283 | 1.5722 | 1982 | 0.05 | 1921
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 1250 | FALSE | 5741.9405 | 5741.9405 | 3.5686 | 26 | 0.00015474 | 698 | 75.9474 | 2063 | 0.0094996 | 0.24699 | 1983 | 71.72 | 66
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 5024 | TRUE | 526.6111 | 526.6111 | 0.32729 | 4 | 0.00017161 | 552 | 35.72 | 2305 | 0.0094858 | 0.037943 | 1984 | 11.71 | 383
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | CB | TRUE | 14676.6694 | 318.0802 | 0.19769 | 91 | 4.44e-05 | 3177 | 137.3401 | 1820 | 0.0094639 | 0.86121 | 1985 |  | 2802
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 220608 | FALSE | 3563.3452 | 1678.7883 | 1.0434 | 10 | 2.18e-05 | 3522 | 416.4617 | 1275 | 0.009449 | 0.09449 | 1986 |  | 2941
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 50010 | FALSE | 15036.1048 | 9841.1126 | 6.1163 | 117 | 0.00024302 | 239 | 56.6031 | 2173 | 0.0094406 | 1.1046 | 1987 | 18.42 | 323
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 34008 | FALSE | 36886.2403 | 36886.2403 | 22.9249 | 259 | 0.00010265 | 1580 | 90.3162 | 1998 | 0.0094239 | 2.4408 | 1988 | 82.16 | 46
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 3030 | FALSE | 41820.8596 | 16131.8418 | 10.026 | 186 | 2.91e-05 | 3440 | 203.8088 | 1634 | 0.0094083 | 1.7499 | 1989 | 0.06 | 1801
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 58095 | TRUE | 251.9158 | 251.9158 | 0.15657 | 2 | 0.00013161 | 987 | 71.4359 | 2085 | 0.0094017 | 0.018803 | 1990 | 1.66 | 656
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 2600 | FALSE | 32204.7216 | 32204.7216 | 20.0154 | 114 | 9.8e-05 | 1692 | 92.2082 | 1992 | 0.0093006 | 1.0603 | 1991 | 6.68 | 463
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 642 | FALSE | 14995.9698 | 14995.9698 | 9.3201 | 127 | 0.00012083 | 1167 | 94.1376 | 1984 | 0.0092364 | 1.173 | 1992 | 16.12 | 341
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 474 | FALSE | 14496.4926 | 14496.4926 | 9.0096 | 77 | 9.22e-05 | 1837 | 111.515 | 1906 | 0.0092125 | 0.70936 | 1993 | 0.09 | 1510
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 695270 | FALSE | 1764.2137 | 1116.1992 | 0.69372 | 12 | 6.66e-05 | 2569 | 184.7862 | 1675 | 0.009199 | 0.11039 | 1994 |  | 3425
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | MR525 | TRUE | 98.2491 | 17.8831 | 0.011114 | 2 | 6.22e-05 | 2712 | 142.6154 | 1800 | 0.0091967 | 0.018393 | 1995 |  | 3348
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1324 | FALSE | 38651.4549 | 1638.5898 | 1.0184 | 169 | 2.2e-05 | 3520 | 325.2371 | 1405 | 0.0091756 | 1.5507 | 1996 | 0.02 | 2488
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 610800 | FALSE | 4080.4254 | 3862.9953 | 2.4009 | 33 | 8.55e-05 | 2042 | 102.3732 | 1943 | 0.0091096 | 0.30062 | 1997 |  | 3147
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 910230 | FALSE | 3166.5297 | 1560.5069 | 0.96986 | 27 | 0.00023934 | 248 | 37.0091 | 2298 | 0.0090947 | 0.24556 | 1998 |  | 3058
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 532 | FALSE | 15658.0016 | 15658.0016 | 9.7315 | 124 | 0.00024726 | 225 | 48.9408 | 2215 | 0.0090595 | 1.1234 | 1999 | 47.27 | 135
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 542272 | FALSE | 12585.3616 | 12585.3616 | 7.8219 | 80 | 0.00018486 | 474 | 31.5637 | 2334 | 0.0090446 | 0.72357 | 2000 |  | 2940
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 253331 | TRUE | 639.8394 | 107.6584 | 0.06691 | 5 | 0.0001555 | 688 | 63.3453 | 2134 | 0.0090171 | 0.045085 | 2001 |  | 3284
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 6577 | FALSE | 5581.4139 | 5581.4139 | 3.4689 | 33 | 0.00018059 | 509 | 33.2037 | 2318 | 0.0089943 | 0.29681 | 2002 |  | 3482
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 90242 | FALSE | 7016.5204 | 6652.6427 | 4.1346 | 51 | 0.00013965 | 876 | 54.8847 | 2183 | 0.0089934 | 0.45866 | 2003 | 0.05 | 1980
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 802 | FALSE | 20585.105 | 13782.7792 | 8.5661 | 162 | 0.00013761 | 901 | 59.5964 | 2158 | 0.0089568 | 1.451 | 2004 | 0.09 | 1542
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 481660 | FALSE | 1777.5904 | 1750.3957 | 1.0879 | 21 | 0.00013748 | 904 | 66.8278 | 2109 | 0.0089565 | 0.18809 | 2005 |  | 3360
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 625902 | FALSE | 9066.5477 | 4214.4266 | 2.6193 | 26 | 5.25e-05 | 2981 | 97.9588 | 1969 | 0.0089147 | 0.23178 | 2006 |  | 2735
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 4002 | FALSE | 30655.7932 | 29553.7891 | 18.3678 | 140 | 4.26e-05 | 3215 | 236.2342 | 1577 | 0.0088999 | 1.246 | 2007 | 0.18 | 1202
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | A88 | FALSE | 4298.2003 | 1506.8203 | 0.93649 | 41 | 7.07e-05 | 2450 | 118.2966 | 1877 | 0.008869 | 0.36363 | 2008 | 0.51 | 891
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 1602 | FALSE | 26067.9128 | 26067.9128 | 16.2013 | 121 | 7.2e-05 | 2416 | 103.4039 | 1935 | 0.0088619 | 1.0723 | 2009 | 0.28 | 1033
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | VR816 | FALSE | 6675.8935 | 6675.8935 | 4.1491 | 49 | 0.00021002 | 359 | 34.0265 | 2312 | 0.0088541 | 0.43385 | 2010 | 78.58 | 51
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 35576 | FALSE | 12676.983 | 12676.983 | 7.8788 | 77 | 9.96e-05 | 1656 | 90.2081 | 1999 | 0.0088445 | 0.68102 | 2011 | 51.58 | 114
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 357407 | TRUE | 396.3684 | 382.6506 | 0.23782 | 5 | 5.61e-05 | 2883 | 139.4252 | 1811 | 0.0088377 | 0.044188 | 2012 |  | 3206
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 75274 | TRUE | 5361.6389 | 623.7122 | 0.38764 | 43 | 7.48e-05 | 2337 | 100.4794 | 1953 | 0.0088331 | 0.37982 | 2013 | 2.09 | 623
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 64758 | FALSE | 16840.1197 | 16840.1197 | 10.4662 | 97 | 0.00025463 | 207 | 41.2688 | 2270 | 0.0087918 | 0.8528 | 2014 | 58.76 | 91
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 534548 | TRUE | 825.2513 | 643.683 | 0.40005 | 7 | 8.88e-05 | 1960 | 139.419 | 1812 | 0.008746 | 0.061222 | 2015 |  | 3194
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 504 | FALSE | 10763.1252 | 10763.1252 | 6.6893 | 53 | 0.00011675 | 1255 | 93.9031 | 1988 | 0.0087025 | 0.46123 | 2016 | 0.26 | 1063
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 530 | TRUE | 7365.5043 | 114.9911 | 0.071467 | 55 | 7.76e-05 | 2274 | 96.695 | 1976 | 0.0087005 | 0.47853 | 2017 | 0.03 | 2248
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 37520 | FALSE | 3437.9631 | 3437.9631 | 2.1367 | 20 | 0.0002436 | 236 | 45.2659 | 2244 | 0.0086846 | 0.17369 | 2018 | 30.52 | 237
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 180 | FALSE | 3158.1165 | 3158.1165 | 1.9628 | 28 | 0.00023287 | 273 | 37.4189 | 2293 | 0.0086779 | 0.24298 | 2019 | 48.66 | 126
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 1302 | FALSE | 28390.9957 | 12188.0095 | 7.5749 | 189 | 9.16e-05 | 1856 | 135.9642 | 1826 | 0.0086777 | 1.6401 | 2020 | 0.07 | 1751
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 1303 | FALSE | 25207.4138 | 25207.4138 | 15.6665 | 146 | 8.29e-05 | 2134 | 109.1634 | 1912 | 0.0086648 | 1.2651 | 2021 | 55.45 | 103
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 2232 | FALSE | 16843.7265 | 16843.7265 | 10.4684 | 88 | 0.00014558 | 796 | 81.1031 | 2043 | 0.0086414 | 0.76044 | 2022 | 16.24 | 339
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 725939 | TRUE | 1338.4571 | 150.5355 | 0.093558 | 14 | 0.0001664 | 579 | 36.2434 | 2303 | 0.0086108 | 0.12055 | 2023 |  | 3249
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 6601 | FALSE | 3063.6094 | 3063.6094 | 1.904 | 19 | 0.00011592 | 1271 | 66.3782 | 2113 | 0.0085862 | 0.16314 | 2024 |  | 3470
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 348368 | FALSE | 14957.0247 | 4473.6471 | 2.7804 | 107 | 6.05e-05 | 2762 | 137.0477 | 1824 | 0.0085797 | 0.91803 | 2025 |  | 2865
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 4859 | FALSE | 3008.5895 | 3008.5895 | 1.8699 | 22 | 0.00015733 | 670 | 65.9715 | 2116 | 0.0085572 | 0.18826 | 2026 | 30.63 | 236
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | CB | FALSE | 7381.7293 | 5917.6189 | 3.6778 | 32 | 7.2e-05 | 2418 | 150.0597 | 1776 | 0.0085315 | 0.27301 | 2027 | 0.06 | 1914
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 6852 | FALSE | 40624.2727 | 40624.2727 | 25.2481 | 309 | 0.00015417 | 703 | 140.8238 | 1808 | 0.0085289 | 2.6354 | 2028 | 106.87 | 16
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | CB | FALSE | 5578.7405 | 1480.1268 | 0.9199 | 28 | 6.19e-05 | 2724 | 91.0203 | 1996 | 0.0085282 | 0.23879 | 2029 | 0.25 | 1074
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 4923 | FALSE | 4611.3164 | 4611.3164 | 2.866 | 12 | 0.00010517 | 1516 | 65.4057 | 2122 | 0.008518 | 0.10222 | 2030 | 0.06 | 1877
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 63502 | FALSE | 16836.9835 | 16836.9835 | 10.4643 | 107 | 0.00012514 | 1095 | 60.239 | 2153 | 0.0084952 | 0.90898 | 2031 | 0.16 | 1256
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 2068 | FALSE | 17517.3264 | 17517.3264 | 10.8871 | 90 | 0.00011364 | 1328 | 80.7377 | 2044 | 0.0084897 | 0.76407 | 2032 | 0.32 | 992
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | CB | FALSE | 24321.9127 | 2030.3761 | 1.2619 | 199 | 0.00016447 | 591 | 61.5586 | 2143 | 0.0084763 | 1.6868 | 2033 | 0.03 | 2311
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 8233 | FALSE | 7978.7453 | 7978.7453 | 4.9588 | 51 | 7.99e-05 | 2208 | 109.5763 | 1910 | 0.008467 | 0.43182 | 2034 | 41.72 | 175
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | CB | FALSE | 27644.3486 | 27644.3486 | 17.1811 | 231 | 0.00016053 | 637 | 70.3363 | 2092 | 0.0084422 | 1.9501 | 2035 | 0.21 | 1148
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | CB | FALSE | 15842.0085 | 9046.8091 | 5.6226 | 127 | 0.0002078 | 373 | 65.6703 | 2119 | 0.008393 | 1.0659 | 2036 | 0.19 | 1172
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 19612 | FALSE | 14689.1647 | 14689.1647 | 9.1294 | 102 | 0.00021798 | 328 | 33.636 | 2313 | 0.0083743 | 0.85418 | 2037 | 36 | 208
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1500 | FALSE | 2059.653 | 1869.3575 | 1.1618 | 8 | 8.34e-05 | 2121 | 83.3451 | 2035 | 0.0083473 | 0.066779 | 2038 | 0.06 | 1818
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 11010 | FALSE | 3501.2634 | 3501.2634 | 2.176 | 26 | 0.00023343 | 269 | 31.1531 | 2340 | 0.0083235 | 0.21641 | 2039 | 12.24 | 375
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 237522 | FALSE | 26805.1596 | 1485.982 | 0.92354 | 39 | 3.42e-05 | 3366 | 404.1911 | 1293 | 0.0082937 | 0.32346 | 2040 |  | 3130
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | MR334 | FALSE | 9742.4846 | 9116.5949 | 5.666 | 80 | 8.2e-05 | 2151 | 200.4591 | 1639 | 0.0082358 | 0.65886 | 2041 |  | 2808
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | CB | FALSE | 28877.5917 | 25353.1416 | 15.7571 | 216 | 0.00013825 | 891 | 45.587 | 2242 | 0.008163 | 1.7632 | 2042 | 0.16 | 1262
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 152774 | FALSE | 12406.0754 | 10319.2603 | 6.4135 | 84 | 6.21e-05 | 2716 | 152.7782 | 1769 | 0.0081314 | 0.68304 | 2043 |  | 2709
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 920793 | FALSE | 12855.6086 | 10473.7039 | 6.5094 | 51 | 8.69e-05 | 2016 | 85.5215 | 2025 | 0.008033 | 0.40968 | 2044 |  | 2833
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 1820 | FALSE | 9227.6622 | 9227.6622 | 5.735 | 51 | 7.91e-05 | 2234 | 127.8002 | 1850 | 0.0080276 | 0.40941 | 2045 | 46.68 | 139
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 238990 | TRUE | 9730.7173 | 65.0773 | 0.040446 | 84 | 0.00017934 | 513 | 66.7295 | 2111 | 0.0080184 | 0.67354 | 2046 |  | 2918
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 6663 | FALSE | 3787.49 | 3787.49 | 2.3539 | 17 | 7.51e-05 | 2328 | 97.3101 | 1972 | 0.0079953 | 0.13592 | 2047 | 1.13 | 713
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 694641 | FALSE | 6527.852 | 6527.852 | 4.0571 | 49 | 7.32e-05 | 2390 | 257.8416 | 1526 | 0.020553 | 1.0071 | 1660 |  | 3355
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | CB | FALSE | 63333.9358 | 37375.4287 | 23.229 | 440 | 0.00026939 | 173 | 30.0518 | 2342 | 0.0079104 | 3.4806 | 2049 | 0.19 | 1174
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 11062 | FALSE | 21428.2343 | 21428.2343 | 13.3177 | 88 | 0.00013572 | 922 | 71.1136 | 2090 | 0.007899 | 0.69511 | 2050 | 0.25 | 1075
7844 | ELK 11011260 | 42981101 | ELK 1101 | 1260 | FALSE | 25231.41 | 25226.838 | 15.6786 | 120 | 9.5e-05 | 1767 | 70.6215 | 2091 | 0.0078966 | 0.94759 | 2051 | 0.04 | 2197
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 39104 | FALSE | 49366.035 | 49366.035 | 30.6812 | 346 | 0.00016953 | 566 | 33.5173 | 2314 | 0.007888 | 2.7292 | 2052 | 0.26 | 1066
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | CB | FALSE | 14345.0573 | 13611.4014 | 8.4595 | 92 | 0.00011705 | 1247 | 67.2853 | 2106 | 0.0078811 | 0.72506 | 2053 | 0.43 | 926
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 92172 | TRUE | 5246.1471 | 190.7947 | 0.11858 | 45 | 0.00012597 | 1079 | 55.6458 | 2177 | 0.0078638 | 0.35387 | 2054 | 0.61 | 846
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 69412 | FALSE | 34124.5253 | 25048.7626 | 15.5679 | 150 | 9.92e-05 | 1664 | 96.7198 | 1975 | 0.0078448 | 1.1767 | 2055 | 0.06 | 1862
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | CB | FALSE | 12364.4219 | 3069.8489 | 1.9079 | 111 | 3.28e-05 | 3389 | 173.8407 | 1700 | 0.0077955 | 0.8653 | 2056 | 0.03 | 2405
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 1296 | FALSE | 8913.723 | 5630.7668 | 3.4995 | 37 | 6.54e-05 | 2603 | 134.0606 | 1835 | 0.007772 | 0.28757 | 2057 | 0.02 | 2458
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | CB | FALSE | 14659.7522 | 14659.7522 | 9.1111 | 110 | 0.00023141 | 282 | 46.7348 | 2235 | 0.0077431 | 0.85174 | 2058 | 50.51 | 118
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 1340 | FALSE | 28996.5273 | 28996.5273 | 18.0215 | 144 | 3.48e-05 | 3354 | 286.6355 | 1466 | 0.0077101 | 1.1103 | 2059 | 0.06 | 1820
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 614 | FALSE | 2222.7419 | 2222.7419 | 1.3814 | 18 | 0.00013751 | 902 | 52.9107 | 2196 | 0.0076984 | 0.13857 | 2060 | 47.35 | 134
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 320 | FALSE | 4467.496 | 4467.496 | 2.7766 | 29 | 0.00021698 | 331 | 31.2121 | 2339 | 0.0076924 | 0.22308 | 2061 | 49.68 | 122
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 36514 | FALSE | 11050.0531 | 11050.0531 | 6.8677 | 64 | 0.00015664 | 677 | 62.082 | 2141 | 0.0076624 | 0.4904 | 2062 | 0.67 | 813
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 5156 | FALSE | 16018.9017 | 7784.4976 | 4.8381 | 114 | 9.99e-05 | 1647 | 85.2613 | 2028 | 0.0076261 | 0.86938 | 2063 | 0.53 | 881
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 1308 | FALSE | 51491.5441 | 51491.5441 | 32.0022 | 245 | 8.98e-05 | 1917 | 98.5183 | 1965 | 0.0076242 | 1.8679 | 2064 | 0.09 | 1559
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 1036 | TRUE | 989.4598 | 989.4598 | 0.61495 | 4 | 6.24e-05 | 2709 | 118.9656 | 1873 | 0.0076073 | 0.030429 | 2065 | 0.09 | 1531
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | V06 | FALSE | 10508.9376 | 3602.7995 | 2.2392 | 66 | 4.61e-05 | 3135 | 94.4714 | 1983 | 0.007606 | 0.50199 | 2066 | 0.87 | 757
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 5722 | FALSE | 3182.5999 | 3182.5999 | 1.978 | 23 | 7.54e-05 | 2325 | 108.5957 | 1915 | 0.0076053 | 0.17492 | 2067 | 0.29 | 1024
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | CB | FALSE | 10759.8557 | 10367.8883 | 6.4437 | 54 | 7.93e-05 | 2224 | 98.8454 | 1961 | 0.0075954 | 0.41015 | 2068 | 0.46 | 912
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 861496 | FALSE | 7188.816 | 7188.816 | 4.4679 | 51 | 8.77e-05 | 1993 | 163.8005 | 1737 | 0.013491 | 0.68805 | 1833 |  | 3201
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 96986 | FALSE | 9497.5055 | 9497.5055 | 5.9027 | 63 | 0.00018221 | 496 | 38.932 | 2285 | 0.0075562 | 0.47604 | 2070 | 0.41 | 938
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | CB | FALSE | 14786.8555 | 5089.2485 | 3.163 | 92 | 0.00018939 | 445 | 47.0523 | 2232 | 0.0075338 | 0.69311 | 2071 | 0.06 | 1839
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 695411 | FALSE | 13352.973 | 13352.973 | 8.2989 | 99 | 0.00013199 | 984 | 79.3253 | 2051 | 0.0075292 | 0.74539 | 2072 |  | 3065
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 216324 | FALSE | 4626.1816 | 3681.9233 | 2.2883 | 23 | 0.00013316 | 955 | 50.0452 | 2210 | 0.0075204 | 0.17297 | 2073 |  | 3409
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | CB | TRUE | 5946.2245 | 0 | 0 | 51 | 0.00020302 | 386 | 24.2582 | 2398 | 0.0074949 | 0.38224 | 2074 | 0.05 | 1988
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 36764 | FALSE | 7038.6749 | 5034.5882 | 3.129 | 46 | 4.66e-05 | 3123 | 107.3772 | 1922 | 0.0074941 | 0.34473 | 2075 | 0 | 2633
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 758024 | FALSE | 10378.3257 | 7589.8929 | 4.7171 | 72 | 9.04e-05 | 1901 | 69.6669 | 2097 | 0.007484 | 0.53884 | 2076 |  | 2992
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 930190 | FALSE | 30053.7833 | 27579.5423 | 17.1408 | 207 | 0.00014885 | 753 | 53.3783 | 2192 | 0.0074761 | 1.5476 | 2077 |  | 2690
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 10940 | FALSE | 17097.711 | 13824.9592 | 8.5923 | 138 | 0.0001288 | 1032 | 78.9158 | 2055 | 0.0073788 | 1.0183 | 2078 | 0.13 | 1356
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | CB | TRUE | 31613.0704 | 164.6636 | 0.10234 | 261 | 5.24e-05 | 2982 | 125.9834 | 1855 | 0.0073172 | 1.9098 | 2079 |  | 2718
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 4036 | FALSE | 40366.1816 | 16000.3844 | 9.9443 | 57 | 4.33e-05 | 3204 | 184.9055 | 1674 | 0.0073003 | 0.41612 | 2080 | 0.02 | 2455
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 380922 | FALSE | 4341.3947 | 1588.6005 | 0.98732 | 30 | 5.3e-05 | 2965 | 107.6713 | 1919 | 0.0072901 | 0.2187 | 2081 |  | 3357
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 76850 | FALSE | 5941.1146 | 3458.1261 | 2.1492 | 51 | 0.00012907 | 1026 | 65.4632 | 2120 | 0.0072691 | 0.37072 | 2082 | 0.04 | 2220
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 4018 | FALSE | 85010.3668 | 71470.9964 | 44.4195 | 280 | 6.77e-05 | 2541 | 115.5373 | 1893 | 0.0072679 | 2.035 | 2083 | 0.08 | 1661
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 346 | FALSE | 16160.3417 | 16160.3417 | 10.0437 | 101 | 0.00015809 | 662 | 67.6609 | 2104 | 0.0072159 | 0.72881 | 2084 | 0.97 | 737
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 258878 | FALSE | 7396.9293 | 5357.1763 | 3.3295 | 26 | 4e-05 | 3270 | 107.5084 | 1921 | 0.0072141 | 0.18757 | 2085 |  | 3114
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 137662 | FALSE | 13866.4902 | 13813.2405 | 8.585 | 104 | 0.00014441 | 806 | 94.0043 | 1985 | 0.0071841 | 0.74714 | 2086 | 0.76 | 786
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | CB | FALSE | 54723.5805 | 54723.5805 | 34.0109 | 337 | 0.00011257 | 1353 | 93.6722 | 1990 | 0.0071702 | 2.4164 | 2087 | 71.14 | 67
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 953474 | FALSE | 17115.5789 | 17115.5789 | 10.6374 | 133 | 0.000245 | 233 | 47.063 | 2231 | 0.0071239 | 0.94748 | 2088 |  | 2666
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 722270 | TRUE | 712.8056 | 283.5574 | 0.17623 | 5 | 3.32e-05 | 3380 | 133.0363 | 1839 | 0.0070957 | 0.035479 | 2089 |  | 3434
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 140 | FALSE | 13525.925 | 13525.925 | 8.4064 | 96 | 0.0002562 | 201 | 19.1476 | 2459 | 0.0070376 | 0.67561 | 2090 | 16.37 | 338
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 4914 | FALSE | 22650.1521 | 17097.4476 | 10.6261 | 138 | 0.00016776 | 577 | 39.2521 | 2282 | 0.0070374 | 0.97117 | 2091 | 0.08 | 1621
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 10330 | FALSE | 15550.3229 | 15550.3229 | 9.6646 | 90 | 7.23e-05 | 2408 | 118.1064 | 1878 | 0.0069896 | 0.62906 | 2092 | 0.31 | 1008
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 9702 | FALSE | 14797.576 | 1035.9167 | 0.64383 | 91 | 3.62e-05 | 3331 | 189.6534 | 1664 | 0.006985 | 0.63564 | 2093 | 0.01 | 2605
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 3050 | FALSE | 4223.7094 | 4223.7094 | 2.6251 | 18 | 0.00010688 | 1481 | 71.3502 | 2089 | 0.0069828 | 0.12569 | 2094 | 11.06 | 389
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 581588 | TRUE | 1519.7137 | 313.0143 | 0.19454 | 14 | 0.00011751 | 1235 | 44.2079 | 2251 | 0.0069585 | 0.097419 | 2095 |  | 3376
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 2140 | FALSE | 55629.2693 | 55629.2693 | 34.5738 | 373 | 7.63e-05 | 2300 | 87.1186 | 2015 | 0.0069513 | 2.5928 | 2096 | 99.53 | 20
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 331806 | TRUE | 1086.2067 | 799.0558 | 0.49662 | 5 | 0.00010249 | 1590 | 66.6724 | 2112 | 0.0069274 | 0.034637 | 2097 |  | 3162
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 6175 | FALSE | 4418.4642 | 4418.4642 | 2.7461 | 30 | 7.05e-05 | 2457 | 113.3507 | 1901 | 0.0069045 | 0.20713 | 2098 | 0.08 | 1596
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 803 | FALSE | 15630.8479 | 15630.8479 | 9.7146 | 93 | 8.74e-05 | 2002 | 89.4789 | 2003 | 0.0068944 | 0.64118 | 2099 | 0.14 | 1319
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 228 | FALSE | 15665.2534 | 3403.012 | 2.115 | 123 | 0.00014113 | 851 | 47.1197 | 2230 | 0.0068367 | 0.84091 | 2100 | 1.03 | 725
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 603250 | TRUE | 2274.9057 | 927.3694 | 0.57636 | 21 | 0.00016094 | 631 | 57.7467 | 2167 | 0.0068337 | 0.14351 | 2101 |  | 3184
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 618 | TRUE | 16180.0386 | 742.2572 | 0.46132 | 118 | 9.71e-05 | 1711 | 69.2887 | 2098 | 0.0068234 | 0.80516 | 2102 | 17.57 | 331
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 8601 | TRUE | 961.631 | 961.631 | 0.59766 | 9 | 0.00015446 | 700 | 60.8174 | 2150 | 0.0067792 | 0.061013 | 2103 | 35.86 | 209
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 7240 | FALSE | 41066.7491 | 1553.9231 | 0.96577 | 234 | 4.36e-05 | 3198 | 175.637 | 1696 | 0.0067642 | 1.5828 | 2104 | 0.02 | 2533
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 138 | TRUE | 26504.92 | 104.0479 | 0.064666 | 197 | 6.59e-05 | 2590 | 63.508 | 2131 | 0.0067556 | 1.3309 | 2105 | 0.62 | 838
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 59770 | FALSE | 11687.7507 | 7749.7634 | 4.8165 | 97 | 8.57e-05 | 2037 | 89.7185 | 2001 | 0.0067467 | 0.65443 | 2106 | 0.09 | 1532
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 566352 | TRUE | 1524.3755 | 680.7554 | 0.42309 | 9 | 3.34e-05 | 3378 | 153.3762 | 1766 | 0.0067421 | 0.060679 | 2107 |  | 3079
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 990464 | FALSE | 8550.7923 | 3365.9887 | 2.092 | 53 | 2.96e-05 | 3431 | 166.8203 | 1728 | 0.0067321 | 0.3568 | 2108 |  | 3234
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 37034 | FALSE | 7287.0481 | 7287.0481 | 4.5289 | 16 | 0.00011223 | 1360 | 44.6194 | 2249 | 0.006701 | 0.10722 | 2109 | 0.31 | 1007
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 50550 | TRUE | 16250.0266 | 0 | 0 | 127 | 0.00012612 | 1078 | 64.7345 | 2124 | 0.0066813 | 0.84852 | 2110 | 0.74 | 790
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 39458 | FALSE | 8594.1592 | 1902.6531 | 1.1825 | 72 | 7.63e-05 | 2298 | 85.8335 | 2024 | 0.0066627 | 0.47971 | 2111 | 0.27 | 1048
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 8512 | FALSE | 39804.5313 | 39804.5313 | 24.7387 | 228 | 0.00015985 | 643 | 38.9598 | 2284 | 0.0066372 | 1.5133 | 2112 | 8.94 | 418
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 904 | FALSE | 11554.8525 | 2469.2456 | 1.5346 | 78 | 4.31e-05 | 3208 | 64.1478 | 2127 | 0.0066274 | 0.51694 | 2113 | 0.04 | 2146
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 89714 | TRUE | 11363.665 | 178.2278 | 0.11077 | 71 | 8.76e-05 | 1996 | 68.3169 | 2100 | 0.0066271 | 0.47052 | 2114 | 0.02 | 2528
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 344 | FALSE | 9676.0469 | 2427.2453 | 1.5085 | 77 | 0.00010403 | 1551 | 64.3203 | 2126 | 0.0066172 | 0.50953 | 2115 | 1.32 | 687
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 11092 | FALSE | 36100.2834 | 36100.2834 | 22.4365 | 239 | 0.00011036 | 1404 | 74.4691 | 2070 | 0.0066099 | 1.5798 | 2116 | 0.14 | 1314
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 645 | FALSE | 1626.8938 | 1626.8938 | 1.0111 | 13 | 9.12e-05 | 1870 | 67.7241 | 2103 | 0.0065604 | 0.085285 | 2117 | 60.62 | 88
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 474708 | TRUE | 1392.1284 | 422.046 | 0.2623 | 13 | 0.00016436 | 594 | 18.3674 | 2470 | 0.0065356 | 0.084962 | 2118 |  | 3063
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | A64 | FALSE | 18905.9424 | 3242.5015 | 2.0152 | 150 | 7.6e-05 | 2309 | 88.4837 | 2011 | 0.0065293 | 0.9794 | 2119 | 0.02 | 2493
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 861610 | FALSE | 11222.3603 | 1689.7743 | 1.0502 | 99 | 0.00027833 | 162 | 23.4916 | 2410 | 0.0065286 | 0.64633 | 2120 |  | 2695
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 86326 | FALSE | 1145.996 | 1133.0955 | 0.70422 | 5 | 8.42e-05 | 2088 | 38.1596 | 2289 | 0.0065228 | 0.032614 | 2121 |  | 3481
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 404 | FALSE | 7372.5748 | 3785.8959 | 2.3529 | 63 | 6.9e-05 | 2509 | 86.9459 | 2016 | 0.0065164 | 0.41053 | 2122 | 0.24 | 1106
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | CB | FALSE | 15016.5066 | 13697.3672 | 8.513 | 117 | 0.00025615 | 202 | 34.5981 | 2310 | 0.0065148 | 0.76223 | 2123 | 0.09 | 1568
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 77384 | FALSE | 7595.6346 | 7595.6346 | 4.7207 | 61 | 0.00017011 | 562 | 62.7847 | 2138 | 0.0065145 | 0.39738 | 2124 | 0.65 | 823
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 1504 | FALSE | 13347.4853 | 13347.4853 | 8.2955 | 95 | 5.83e-05 | 2825 | 84.8611 | 2031 | 0.0065125 | 0.61869 | 2125 | 45.39 | 148
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 920400 | FALSE | 7975.407 | 7538.764 | 4.6854 | 66 | 0.00044142 | 53 | 18.0732 | 2478 | 0.0064968 | 0.42879 | 2126 |  | 2964
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | MR297 | FALSE | 9710.6915 | 9531.5764 | 5.9239 | 66 | 6.91e-05 | 2502 | 221.7666 | 1602 | 0.0064881 | 0.42822 | 2127 | 0.06 | 1849
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 354 | FALSE | 12035.3765 | 1010.2026 | 0.62784 | 79 | 9.31e-05 | 1816 | 134.0043 | 1836 | 0.0064828 | 0.51214 | 2128 |  | 2822
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 560 | FALSE | 9061.7878 | 8145.5491 | 5.0625 | 31 | 9.99e-05 | 1648 | 60.8351 | 2148 | 0.0064599 | 0.20026 | 2129 | 0.02 | 2420
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 36880 | FALSE | 13851.9467 | 9899.4771 | 6.1526 | 92 | 8.61e-05 | 2032 | 179.7214 | 1684 | 0.0064477 | 0.59319 | 2130 | 0.08 | 1578
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 1104 | FALSE | 79643.684 | 79643.684 | 49.4989 | 462 | 0.00011856 | 1216 | 56.9205 | 2171 | 0.0064469 | 2.9785 | 2131 | 111.82 | 14
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 10315 | FALSE | 8831.8074 | 8831.8074 | 5.489 | 53 | 0.000107 | 1472 | 59.7801 | 2155 | 0.006431 | 0.34084 | 2132 |  | 3064
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 982462 | FALSE | 2320.5593 | 2320.5593 | 1.4422 | 18 | 9.63e-05 | 1726 | 75.3379 | 2065 | 0.006427 | 0.11569 | 2133 |  | 3100
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | CB | TRUE | 2754.8033 | 5.4992 | 0.0034177 | 26 | 0.00020884 | 366 | 19.5341 | 2454 | 0.0064174 | 0.16685 | 2134 | 0.01 | 2596
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 19712 | FALSE | 20850.3369 | 20776.2868 | 12.9125 | 151 | 0.000145 | 801 | 90.5715 | 1997 | 0.0064118 | 0.96818 | 2135 | 0.12 | 1371
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 13438 | FALSE | 26618.9181 | 26618.9181 | 16.5438 | 172 | 0.00010264 | 1581 | 69.7074 | 2096 | 0.0063999 | 1.1008 | 2136 | 82.17 | 45
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 49756 | FALSE | 9480.1738 | 1727.7805 | 1.0738 | 40 | 7.57e-05 | 2316 | 118.0346 | 1881 | 0.0063622 | 0.25449 | 2137 | 0.01 | 2594
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | CB | FALSE | 4085.1757 | 4085.1757 | 2.539 | 27 | 6.88e-05 | 2513 | 75.2459 | 2066 | 0.0062536 | 0.16885 | 2138 | 0.07 | 1752
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 36870 | TRUE | 3829.3681 | 541.2922 | 0.33642 | 29 | 0.00011992 | 1188 | 41.8373 | 2269 | 0.0062483 | 0.1812 | 2139 | 0.04 | 2157
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 3113 | FALSE | 16133.333 | 16133.333 | 10.0269 | 68 | 8.36e-05 | 2106 | 76.2422 | 2061 | 0.0062347 | 0.42396 | 2140 | 0.05 | 1961
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 2214 | FALSE | 29878.7054 | 24265.0129 | 15.0808 | 233 | 0.00042568 | 61 | 48.0844 | 2221 | 0.0062243 | 1.4503 | 2141 | 51.75 | 113
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 79826 | FALSE | 16584.8842 | 16584.8842 | 10.3076 | 95 | 0.00015691 | 673 | 91.848 | 1994 | 0.0062159 | 0.59051 | 2142 | 0.15 | 1290
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 98174 | FALSE | 19681.5881 | 19681.5881 | 12.2322 | 66 | 7.92e-05 | 2229 | 58.0357 | 2166 | 0.0062048 | 0.40952 | 2143 | 22.16 | 296
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 50070 | FALSE | 28555.3412 | 28555.3412 | 17.7473 | 201 | 0.00011083 | 1394 | 43.6964 | 2255 | 0.0062036 | 1.2469 | 2144 | 128.64 | 7
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 413816 | FALSE | 17928.3843 | 17928.3843 | 11.1426 | 104 | 0.00011948 | 1197 | 65.9071 | 2117 | 0.0061927 | 0.64404 | 2145 | 0.87 | 760
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 483444 | FALSE | 8714.6826 | 3311.0968 | 2.0579 | 67 | 5.46e-05 | 2929 | 67.496 | 2105 | 0.0061552 | 0.4124 | 2146 |  | 2731
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 8582 | FALSE | 19173.6398 | 15254.7771 | 9.4809 | 163 | 0.00018689 | 463 | 41.133 | 2272 | 0.0061345 | 0.99993 | 2147 | 0.05 | 1953
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | LA60 | FALSE | 13957.1729 | 13957.1729 | 8.6744 | 61 | 0.00010054 | 1636 | 81.9054 | 2041 | 0.0061263 | 0.3737 | 2148 | 41.93 | 173
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 1502 | FALSE | 11680.2523 | 11680.2523 | 7.2593 | 80 | 8.09e-05 | 2184 | 65.4099 | 2121 | 0.0061144 | 0.48915 | 2149 | 27.78 | 255
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | CB | FALSE | 8114.1348 | 6042.2888 | 3.7553 | 50 | 0.00011189 | 1369 | 66.0103 | 2115 | 0.0060781 | 0.30391 | 2150 | 0.06 | 1817
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 653758 | TRUE | 582.3673 | 582.3673 | 0.36194 | 5 | 5.58e-05 | 2895 | 104.6024 | 1930 | 0.0060671 | 0.030336 | 2151 |  | 3538
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 38698 | FALSE | 25178.9612 | 25178.9612 | 15.6488 | 103 | 9.2e-05 | 1843 | 61.204 | 2145 | 0.0060349 | 0.62159 | 2152 | 4.1 | 526
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 9112 | FALSE | 8500.5119 | 1386.5143 | 0.86172 | 68 | 4.43e-05 | 3182 | 101.7861 | 1948 | 0.0060009 | 0.40806 | 2153 | 0.04 | 2214
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 821698 | FALSE | 1364.9269 | 1364.9269 | 0.84831 | 9 | 5.53e-05 | 2904 | 187.6587 | 1667 | 0.0060008 | 0.054007 | 2154 |  | 3345
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 409621 | TRUE | 945.4612 | 219.1314 | 0.13619 | 4 | 8.5e-05 | 2059 | 85.5196 | 2026 | 0.0059943 | 0.023977 | 2155 |  | 3567
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 12518 | FALSE | 25177.1399 | 25177.1399 | 15.6477 | 145 | 0.00025023 | 216 | 28.5941 | 2352 | 0.0059295 | 0.85978 | 2156 | 0.8 | 774
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 2104 | FALSE | 15810.2753 | 15810.2753 | 9.8261 | 123 | 0.00020356 | 384 | 19.3883 | 2456 | 0.0059169 | 0.72777 | 2157 | 38.88 | 194
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 5470 | FALSE | 14989.8273 | 14989.8273 | 9.3162 | 104 | 0.00010143 | 1618 | 96.9488 | 1973 | 0.0059093 | 0.61457 | 2158 | 14.88 | 353
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 94892 | TRUE | 15531.7609 | 345.9853 | 0.21503 | 66 | 3.5e-05 | 3351 | 201.9181 | 1637 | 0.0059064 | 0.38983 | 2159 |  | 2790
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 94770 | FALSE | 6459.1608 | 3806.5671 | 2.3658 | 55 | 0.00027047 | 172 | 16.4987 | 2510 | 0.0059058 | 0.32482 | 2160 | 0.27 | 1050
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 328 | FALSE | 22172.9748 | 2414.9476 | 1.5009 | 173 | 9.5e-05 | 1766 | 59.7612 | 2156 | 0.0058817 | 1.0175 | 2161 | 1 | 732
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 47952 | FALSE | 16717.6297 | 16717.6297 | 10.3901 | 88 | 0.00011754 | 1233 | 58.6557 | 2163 | 0.0058506 | 0.51485 | 2162 | 0.09 | 1517
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 825 | TRUE | 3371.6214 | 749.4567 | 0.46579 | 26 | 7e-05 | 2473 | 79.9838 | 2048 | 0.0058122 | 0.15112 | 2163 |  | 2782
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 3026 | FALSE | 36330.5251 | 35201.2582 | 21.8777 | 238 | 5.59e-05 | 2892 | 99.002 | 1958 | 0.0057671 | 1.3726 | 2164 | 2.36 | 610
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | XR494 | TRUE | 11814.5496 | 737.5052 | 0.45836 | 98 | 5.64e-05 | 2877 | 82.0467 | 2040 | 0.0057504 | 0.56354 | 2165 | 0.04 | 2167
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 77670 | FALSE | 10996.9079 | 10874.5833 | 6.7586 | 98 | 0.00011661 | 1258 | 47.4912 | 2228 | 0.0057454 | 0.56305 | 2166 | 19.77 | 309
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 10294 | FALSE | 13501.9938 | 13501.9938 | 8.3915 | 95 | 0.00023536 | 261 | 22.5874 | 2416 | 0.0057046 | 0.54194 | 2167 | 48.18 | 131
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 480 | FALSE | 25809.6606 | 2502.4894 | 1.5553 | 161 | 6.77e-05 | 2543 | 89.1189 | 2006 | 0.0057021 | 0.91803 | 2168 | 0.01 | 2595
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 8912 | FALSE | 6310.9141 | 6268.7877 | 3.8961 | 52 | 0.000205 | 381 | 25.8096 | 2383 | 0.0056974 | 0.29627 | 2169 | 26.71 | 266
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 482 | TRUE | 6000.1069 | 595.0555 | 0.36983 | 38 | 6e-05 | 2775 | 118.3715 | 1876 | 0.0056711 | 0.2155 | 2170 | 0.74 | 789
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 12992 | FALSE | 22915.4569 | 22915.4569 | 14.242 | 160 | 0.00020519 | 379 | 28.593 | 2353 | 0.0056575 | 0.90521 | 2171 | 1.14 | 711
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | CB | FALSE | 1694.4122 | 1694.4122 | 1.0531 | 22 | 5.85e-05 | 2821 | 53.0175 | 2195 | 0.0056462 | 0.12422 | 2172 | 0.02 | 2450
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 47198 | FALSE | 9365.2067 | 4939.462 | 3.0699 | 70 | 0.00010692 | 1477 | 39.3397 | 2280 | 0.0056207 | 0.39345 | 2173 | 0.04 | 2116
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 167360 | FALSE | 15830.4656 | 15413.5909 | 9.5796 | 70 | 0.0001177 | 1232 | 51.7218 | 2203 | 0.0056116 | 0.39281 | 2174 |  | 3176
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 8000 | FALSE | 23055.4602 | 23055.4602 | 14.3291 | 174 | 0.00011159 | 1377 | 95.7818 | 1979 | 0.0056032 | 0.97497 | 2175 | 0.55 | 871
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | CB | TRUE | 4645.037 | 606.8044 | 0.37713 | 37 | 4.64e-05 | 3127 | 105.6404 | 1927 | 0.0055946 | 0.207 | 2176 | 0.05 | 1970
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2028 | FALSE | 3747.9741 | 3373.7724 | 2.0968 | 38 | 7.45e-05 | 2345 | 86.2641 | 2021 | 0.0055851 | 0.21223 | 2177 | 0.08 | 1658
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | A50 | FALSE | 33669.9383 | 31118.7087 | 19.3404 | 269 | 5.6e-05 | 2891 | 116.8319 | 1888 | 0.0055802 | 1.5011 | 2178 | 0.22 | 1131
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 1294 | FALSE | 32661.4744 | 31953.6798 | 19.8593 | 234 | 6.86e-05 | 2518 | 79.062 | 2054 | 0.0055387 | 1.2961 | 2179 | 0.53 | 883
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | P150 | FALSE | 3652.8381 | 3652.8381 | 2.2703 | 18 | 9.51e-05 | 1763 | 45.0393 | 2245 | 0.0055206 | 0.09937 | 2180 | 0.03 | 2243
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 1660 | FALSE | 7855.6793 | 7855.6793 | 4.8823 | 43 | 0.00014039 | 865 | 43.7408 | 2254 | 0.0055185 | 0.23729 | 2181 | 0.02 | 2545
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | CB | FALSE | 7739.8411 | 2580.5041 | 1.6038 | 68 | 0.00014616 | 786 | 21.7605 | 2428 | 0.0054995 | 0.37397 | 2182 | 0.06 | 1798
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 610148 | FALSE | 19896.3037 | 3154.5584 | 1.9606 | 58 | 4.56e-05 | 3151 | 102.3263 | 1944 | 0.0054812 | 0.31791 | 2183 |  | 3231
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 94178 | FALSE | 6646.4632 | 3457.4484 | 2.1488 | 57 | 7.33e-05 | 2388 | 42.0306 | 2265 | 0.0054615 | 0.3113 | 2184 | 0.03 | 2290
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | CB | FALSE | 9963.4073 | 9963.4073 | 6.1923 | 59 | 0.00022265 | 308 | 33.5088 | 2315 | 0.0054141 | 0.31943 | 2185 | 0.49 | 898
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6012 | FALSE | 15479.7977 | 10729.2764 | 6.6683 | 79 | 9.05e-05 | 1896 | 70.018 | 2095 | 0.0054078 | 0.42722 | 2186 | 0.08 | 1585
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 2020 | FALSE | 55275.2572 | 55275.2572 | 34.3538 | 281 | 9.14e-05 | 1861 | 43.1327 | 2260 | 0.005376 | 1.5107 | 2187 | 0.23 | 1114
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | V50 | FALSE | 16840.5394 | 11517.5193 | 7.1582 | 107 | 4.71e-05 | 3112 | 96.3505 | 1978 | 0.005367 | 0.57427 | 2188 | 0.11 | 1428
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 404 | FALSE | 19975.0809 | 19975.0809 | 12.4146 | 152 | 0.00018515 | 471 | 26.3611 | 2372 | 0.0053668 | 0.81576 | 2189 | 92.58 | 29
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 57926 | TRUE | 18926.9724 | 200.7916 | 0.12479 | 97 | 5.5e-05 | 2914 | 62.5543 | 2139 | 0.0053561 | 0.51954 | 2190 |  | 2900
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 5188 | FALSE | 3280.6197 | 3280.6197 | 2.0389 | 19 | 0.00034885 | 92 | 16.3316 | 2511 | 0.0053482 | 0.10162 | 2191 | 7.26 | 449
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 652 | FALSE | 2607.8717 | 2607.8717 | 1.6208 | 25 | 0.00027854 | 161 | 20.0324 | 2448 | 0.0053427 | 0.13357 | 2192 | 55.16 | 104
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 260 | FALSE | 9537.0372 | 4317.1662 | 2.6831 | 68 | 6.29e-05 | 2687 | 71.585 | 2084 | 0.0053405 | 0.36316 | 2193 | 0.78 | 778
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 574315 | FALSE | 12024.0849 | 11904.9852 | 7.399 | 78 | 0.00010886 | 1429 | 65.6711 | 2118 | 0.005318 | 0.4148 | 2194 |  | 2800
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 76952 | FALSE | 18206.8026 | 3648.4496 | 2.2675 | 161 | 0.00026698 | 179 | 39.5343 | 2276 | 0.0052383 | 0.84337 | 2195 | 0.06 | 1785
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 501771 | FALSE | 7891.6601 | 7891.6601 | 4.9047 | 54 | 4.06e-05 | 3256 | 137.8049 | 1819 | 0.0052248 | 0.28214 | 2196 |  | 3217
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 440 | FALSE | 17666.8696 | 13392.7701 | 8.3237 | 107 | 5.29e-05 | 2975 | 95.646 | 1980 | 0.0051543 | 0.5515 | 2197 | 0.05 | 1917
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 75612 | TRUE | 15618.6787 | 0 | 0 | 114 | 6.25e-05 | 2703 | 68.7688 | 2099 | 0.0051135 | 0.58294 | 2198 |  | 2747
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 12122 | FALSE | 12740.7086 | 10570.3766 | 6.5695 | 63 | 0.00010779 | 1455 | 51.4668 | 2205 | 0.0051004 | 0.32133 | 2199 | 0.03 | 2382
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 940 | FALSE | 5636.9672 | 1911.101 | 1.1878 | 46 | 0.00018608 | 466 | 23.9825 | 2400 | 0.005067 | 0.23308 | 2200 | 7.35 | 447
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 32726 | FALSE | 19770.2597 | 19581.5665 | 12.17 | 146 | 0.00014193 | 840 | 48.5752 | 2218 | 0.00506 | 0.73876 | 2201 | 0.1 | 1475
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 2452 | TRUE | 11049.8485 | 228.5177 | 0.14202 | 87 | 5.46e-05 | 2931 | 79.1562 | 2053 | 0.0050248 | 0.43716 | 2202 | 13.72 | 363
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | XR578 | TRUE | 1108.6732 | 261.0602 | 0.16225 | 12 | 5.17e-05 | 3003 | 53.5212 | 2190 | 0.0050174 | 0.060209 | 2203 | 0.02 | 2414
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 528344 | FALSE | 43372.0838 | 43372.0838 | 26.9559 | 171 | 9.69e-05 | 1717 | 60.4469 | 2152 | 0.0049999 | 0.85498 | 2204 |  | 2950
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 148504 | TRUE | 3218.0268 | 275.7602 | 0.17139 | 14 | 6.41e-05 | 2643 | 71.3988 | 2086 | 0.0049963 | 0.069948 | 2205 |  | 3134
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 2293 | FALSE | 2820.5709 | 2820.5709 | 1.753 | 21 | 6.94e-05 | 2492 | 78.9038 | 2056 | 0.0049653 | 0.10427 | 2206 | 0.04 | 2140
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | CB | FALSE | 2574.4725 | 2574.4725 | 1.6 | 18 | 0.00018307 | 488 | 33.0833 | 2322 | 0.0049349 | 0.088829 | 2207 | 0.05 | 1919
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 11533 | FALSE | 4249.6596 | 4249.6596 | 2.6412 | 28 | 9.14e-05 | 1863 | 58.6478 | 2164 | 0.0048855 | 0.13679 | 2208 | 29.27 | 243
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | R324 | FALSE | 17238.3934 | 17238.3934 | 10.7137 | 119 | 3.95e-05 | 3277 | 112.2851 | 1904 | 0.0048731 | 0.5799 | 2209 | 35.54 | 213
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 83716 | FALSE | 4275.4859 | 4027.3677 | 2.503 | 22 | 0.00011418 | 1318 | 54.1847 | 2187 | 0.0048588 | 0.10689 | 2210 | 0.02 | 2436
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 878870 | FALSE | 4057.446 | 4057.446 | 2.5217 | 29 | 0.00048816 | 33 | 4.9842 | 2754 | 0.0048412 | 0.1404 | 2211 |  | 2967
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 1184 | FALSE | 18935.6341 | 18820.6068 | 11.6971 | 136 | 0.00016371 | 603 | 34.7864 | 2309 | 0.0048403 | 0.65828 | 2212 | 54.38 | 107
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 2130 | FALSE | 23180.7639 | 23180.7639 | 14.4069 | 163 | 5.77e-05 | 2845 | 88.5821 | 2010 | 0.0048209 | 0.78581 | 2213 | 63.53 | 81
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | MR273 | FALSE | 1164.6083 | 1164.6083 | 0.72381 | 13 | 7.85e-05 | 2248 | 62.481 | 2140 | 0.0047919 | 0.062294 | 2214 |  | 3564
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 44119 | TRUE | 4510.2451 | 512.7214 | 0.31866 | 35 | 5.3e-05 | 2968 | 87.4332 | 2013 | 0.0047623 | 0.16668 | 2215 | 0.04 | 2190
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1082 | FALSE | 4959.0869 | 2511.2326 | 1.5607 | 36 | 3.82e-05 | 3296 | 64.7708 | 2123 | 0.0047619 | 0.17143 | 2216 | 1.65 | 659
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 8130 | FALSE | 15961.1359 | 15961.1359 | 9.9199 | 123 | 8.12e-05 | 2179 | 72.5007 | 2080 | 0.0047602 | 0.5855 | 2217 | 65.59 | 76
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | CB | TRUE | 5810.1426 | 159.6823 | 0.099243 | 47 | 0.00010848 | 1437 | 74.8868 | 2068 | 0.0047601 | 0.22372 | 2218 | 0.03 | 2307
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 127462 | TRUE | 205.3095 | 189.2737 | 0.11763 | 2 | 0.00015962 | 647 | 47.5976 | 2225 | 0.0047158 | 0.0094316 | 2219 |  | 3622
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 829530 | FALSE | 4171.4477 | 2687.7051 | 1.6704 | 32 | 7.43e-05 | 2348 | 92.7573 | 1991 | 0.0047024 | 0.15048 | 2220 |  | 3320
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 673480 | FALSE | 20487.8392 | 20487.8392 | 12.7333 | 88 | 0.00010713 | 1470 | 66.7652 | 2110 | 0.0046984 | 0.41346 | 2221 |  | 2733
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | CB | FALSE | 6307.2067 | 6307.2067 | 3.92 | 54 | 0.00038312 | 73 | 17.6674 | 2486 | 0.004667 | 0.25202 | 2222 | 0.09 | 1518
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 432 | FALSE | 79373.0607 | 79373.0607 | 49.3307 | 320 | 6.17e-05 | 2728 | 74.7952 | 2069 | 0.0046501 | 1.488 | 2223 | 0.19 | 1170
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | CB | FALSE | 1162.2395 | 1162.2395 | 0.72234 | 10 | 0.00013488 | 929 | 47.6107 | 2224 | 0.0046279 | 0.046279 | 2224 | 0.01 | 2572
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 38514 | FALSE | 17257.2473 | 17257.2473 | 10.7254 | 102 | 0.00021556 | 338 | 24.5363 | 2394 | 0.0046099 | 0.47021 | 2225 | 0.75 | 788
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 1922 | FALSE | 7694.4261 | 7391.7604 | 4.594 | 70 | 0.00019092 | 438 | 30.2755 | 2341 | 0.004588 | 0.32116 | 2226 | 17.29 | 334
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 60118 | FALSE | 44902.9478 | 44902.9478 | 27.9074 | 323 | 0.00017204 | 550 | 26.0465 | 2376 | 0.0045775 | 1.4785 | 2227 | 45.32 | 149
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | MR172 | TRUE | 1779.1253 | 856.8002 | 0.5325 | 26 | 6.27e-05 | 2692 | 64.6297 | 2125 | 0.0045679 | 0.11876 | 2228 | 27.77 | 256
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 681991 | FALSE | 6056.3505 | 2212.0344 | 1.3748 | 50 | 6.86e-05 | 2521 | 61.126 | 2147 | 0.0045171 | 0.22586 | 2229 |  | 2909
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 1232 | FALSE | 3935.7724 | 3637.3088 | 2.2606 | 22 | 9.12e-05 | 1868 | 55.6272 | 2178 | 0.0045024 | 0.099054 | 2230 | 3.14 | 560
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 1212 | TRUE | 6586.9975 | 0 | 0 | 62 | 4.46e-05 | 3173 | 87.4084 | 2014 | 0.0044984 | 0.2789 | 2231 | 0.42 | 928
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | CB | TRUE | 35309.4802 | 290.0531 | 0.18027 | 155 | 3.61e-05 | 3336 | 256.8183 | 1529 | 0.0044835 | 0.69495 | 2232 |  | 3056
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 317156 | FALSE | 18303.2443 | 3816.311 | 2.3719 | 67 | 5.17e-05 | 3000 | 86.4803 | 2018 | 0.0044039 | 0.29506 | 2233 |  | 3166
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 1535 | FALSE | 4933.5895 | 4933.5895 | 3.0662 | 30 | 6.1e-05 | 2749 | 63.4215 | 2132 | 0.0043786 | 0.13136 | 2234 | 52.41 | 112
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | CB | TRUE | 3629.5545 | 353.0082 | 0.2194 | 38 | 5.08e-05 | 3020 | 63.168 | 2135 | 0.0043636 | 0.16582 | 2235 | 0.22 | 1127
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 432198 FM | TRUE | 3829.098 | 907.0096 | 0.56371 | 31 | 7.02e-05 | 2467 | 53.7914 | 2188 | 0.004363 | 0.13525 | 2236 |  | 3344
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 5384 | FALSE | 28128.0957 | 25050.2712 | 15.5688 | 202 | 0.0002103 | 356 | 21.9397 | 2426 | 0.0043604 | 0.88081 | 2237 | 0.18 | 1214
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 332 | FALSE | 9174.8238 | 9174.8238 | 5.7022 | 67 | 0.00022781 | 292 | 15.3212 | 2526 | 0.0043573 | 0.29194 | 2238 | 30.76 | 235
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 1989 | FALSE | 1195.1936 | 1195.1936 | 0.74282 | 9 | 0.00014388 | 816 | 55.5275 | 2179 | 0.0043487 | 0.039138 | 2239 | 44.54 | 158
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 10723 | TRUE | 6.3415 | 6.3415 | 0.0039412 | 1 | 9.05e-05 | 1895 | 47.5921 | 2226 | 0.0043094 | 0.0043094 | 2240 | 48.3 | 130
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 309298 | FALSE | 3091.9426 | 1768.6422 | 1.0992 | 23 | 9.54e-05 | 1744 | 39.3183 | 2281 | 0.0043094 | 0.099116 | 2241 |  | 3197
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 23444 | FALSE | 23380.6907 | 23380.6907 | 14.5312 | 135 | 0.00010219 | 1599 | 47.2338 | 2229 | 0.0042666 | 0.57599 | 2242 | 0.12 | 1396
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 60124 | FALSE | 36140.2282 | 36140.2282 | 22.4613 | 267 | 0.00016531 | 587 | 37.1047 | 2296 | 0.0042657 | 1.1389 | 2243 | 77.48 | 53
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 392 | TRUE | 10922.1116 | 404.9115 | 0.25165 | 68 | 9.42e-05 | 1789 | 58.5408 | 2165 | 0.0042431 | 0.28853 | 2244 | 0.28 | 1035
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | N532R | FALSE | 7429.2796 | 5942.762 | 3.6935 | 65 | 9.03e-05 | 1903 | 44.8885 | 2247 | 0.004228 | 0.27482 | 2245 | 0.09 | 1560
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 2253 | FALSE | 2335.3363 | 2335.3363 | 1.4514 | 12 | 0.00020821 | 370 | 19.8765 | 2451 | 0.0041981 | 0.050377 | 2246 | 0.17 | 1238
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 1341 | FALSE | 15927.2159 | 15927.2159 | 9.8988 | 87 | 5.92e-05 | 2799 | 79.2605 | 2052 | 0.0041901 | 0.36454 | 2247 | 0.52 | 886
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 53120 | TRUE | 12732.032 | 173.1766 | 0.10763 | 92 | 2.98e-05 | 3429 | 159.0093 | 1750 | 0.004183 | 0.38483 | 2248 |  | 2793
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | CB | TRUE | 3345.6946 | 710.3038 | 0.44146 | 26 | 0.00011363 | 1329 | 21.0918 | 2434 | 0.0041416 | 0.10768 | 2249 | 0.02 | 2541
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | CB | FALSE | 11999.4505 | 11999.4505 | 7.4577 | 74 | 0.00013448 | 935 | 29.3004 | 2350 | 0.0041406 | 0.3064 | 2250 | 69.29 | 70
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 1214 | FALSE | 7293.1721 | 5549.8668 | 3.4493 | 45 | 4.79e-05 | 3095 | 64.0131 | 2129 | 0.004132 | 0.18594 | 2251 | 0.05 | 2016
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 26000 | FALSE | 55311.5705 | 55311.5705 | 34.3764 | 339 | 0.00010511 | 1521 | 49.7196 | 2212 | 0.0041222 | 1.3974 | 2252 | 73.15 | 63
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 9110 | FALSE | 15217.7545 | 1491.4373 | 0.92693 | 138 | 0.00014546 | 798 | 26.6167 | 2370 | 0.0040502 | 0.55893 | 2253 | 0.04 | 2097
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 94368 | TRUE | 768.9303 | 596.3821 | 0.37065 | 9 | 0.00048312 | 36 | 49.2875 | 2214 | 0.0040353 | 0.036317 | 2254 | 0.02 | 2527
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 22774 | FALSE | 5970.2453 | 1624.1247 | 1.0094 | 27 | 3.9e-05 | 3287 | 127.212 | 1851 | 0.0040151 | 0.10841 | 2255 | 0.01 | 2610
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 12124 | FALSE | 7217.2962 | 7217.2962 | 4.4856 | 59 | 0.000304 | 126 | 21.0181 | 2436 | 0.0040119 | 0.2367 | 2256 | 0.28 | 1041
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | CB | FALSE | 5575.8129 | 2217.6155 | 1.3783 | 61 | 0.0006536 | 11 | 4.7351 | 2763 | 0.0039747 | 0.24245 | 2257 | 15.11 | 350
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 2740 | FALSE | 30939.0056 | 30939.0056 | 19.2287 | 235 | 0.00018236 | 494 | 38.193 | 2288 | 0.003969 | 0.93271 | 2258 | 0.14 | 1313
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 173014 | FALSE | 5456.0353 | 5290.5313 | 3.2881 | 43 | 0.00018414 | 479 | 19.9675 | 2449 | 0.0039357 | 0.16924 | 2259 |  | 2680
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | L373 | FALSE | 11899.5211 | 11899.5211 | 7.3956 | 93 | 5.97e-05 | 2784 | 62.944 | 2136 | 0.0039044 | 0.36311 | 2260 | 72.86 | 65
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 1048 | FALSE | 8484.8832 | 8484.8832 | 5.2734 | 72 | 0.00016147 | 626 | 26.1474 | 2375 | 0.0039018 | 0.28093 | 2261 | 0.13 | 1345
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 22136 | FALSE | 8542.0356 | 2842.9957 | 1.7669 | 59 | 4.54e-05 | 3155 | 51.6014 | 2204 | 0.0038829 | 0.22909 | 2262 | 0.01 | 2587
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 552724 | FALSE | 23613.9534 | 2363.8176 | 1.4691 | 77 | 7.24e-05 | 2405 | 63.51 | 2130 | 0.0038689 | 0.29791 | 2263 |  | 3158
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 106534 | FALSE | 4199.7803 | 1949.2483 | 1.2115 | 38 | 0.00024793 | 223 | 15.6992 | 2522 | 0.0038425 | 0.14601 | 2264 |  | 3012
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 18396 | TRUE | 1851.7327 | 293.2889 | 0.18228 | 16 | 3.57e-05 | 3339 | 53.4957 | 2191 | 0.0038298 | 0.061277 | 2265 | 4.8 | 506
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 9092 | TRUE | 15725.9351 | 255.1238 | 0.15856 | 113 | 0.0001025 | 1589 | 29.6083 | 2349 | 0.0038237 | 0.43208 | 2266 | 1.99 | 627
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 953336 | FALSE | 19079.6136 | 19079.6136 | 11.8581 | 132 | 9.94e-05 | 1658 | 31.4057 | 2336 | 0.0038167 | 0.50381 | 2267 |  | 2724
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 60120 | FALSE | 6993.663 | 6993.663 | 4.3466 | 42 | 0.0001694 | 567 | 23.8386 | 2403 | 0.0038109 | 0.16006 | 2268 | 27.45 | 257
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 4016 | FALSE | 20664.9565 | 3776.8409 | 2.3473 | 59 | 4.61e-05 | 3134 | 98.5723 | 1963 | 0.0038045 | 0.22447 | 2269 | 0.01 | 2621
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 50486 | FALSE | 18786.575 | 18786.575 | 11.6759 | 163 | 0.00010932 | 1425 | 43.079 | 2261 | 0.0037622 | 0.61325 | 2270 | 86.95 | 38
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 1222 | FALSE | 27771.0153 | 27771.0153 | 17.2598 | 218 | 0.0001881 | 453 | 22.6532 | 2414 | 0.0037571 | 0.81905 | 2271 | 105.89 | 18
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 53477 | FALSE | 3295.7871 | 3295.7871 | 2.0483 | 21 | 0.00016065 | 635 | 22.7228 | 2413 | 0.0037529 | 0.078812 | 2272 | 34.99 | 215
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | CB | FALSE | 5699.8132 | 4772.4685 | 2.9661 | 49 | 0.00014009 | 868 | 39.048 | 2283 | 0.0037209 | 0.18233 | 2273 | 0.11 | 1423
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 98606 | TRUE | 13179.7667 | 138.4782 | 0.086065 | 88 | 8.85e-05 | 1972 | 91.908 | 1993 | 0.0037138 | 0.32681 | 2274 |  | 2931
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 13597 | TRUE | 751.816 | 751.816 | 0.46726 | 6 | 0.00014116 | 850 | 23.8355 | 2404 | 0.0037122 | 0.022273 | 2275 | 8.42 | 427
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | P304 | FALSE | 9851.3779 | 8440.4652 | 5.2458 | 47 | 9.36e-05 | 1809 | 31.6902 | 2333 | 0.0037077 | 0.17426 | 2276 | 0.09 | 1556
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 9042 | FALSE | 5080.7921 | 5080.7921 | 3.1577 | 31 | 4.19e-05 | 3227 | 82.8476 | 2036 | 0.0036996 | 0.11469 | 2277 | 0.11 | 1447
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 52910 | FALSE | 5038.2048 | 3510.8305 | 2.182 | 41 | 5.39e-05 | 2944 | 73.7782 | 2074 | 0.0036877 | 0.1512 | 2278 | 0.81 | 773
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | L3733 | FALSE | 2820.1267 | 2820.1267 | 1.7527 | 22 | 6.61e-05 | 2585 | 57.3124 | 2169 | 0.0036798 | 0.080956 | 2279 | 42.03 | 171
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9742 | FALSE | 14685.6636 | 14685.6636 | 9.1272 | 120 | 4.16e-05 | 3232 | 86.0041 | 2023 | 0.0036718 | 0.44061 | 2280 | 37.7 | 200
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 1268 | FALSE | 7937.7862 | 7937.7862 | 4.9334 | 46 | 4.23e-05 | 3219 | 82.2871 | 2039 | 0.0036642 | 0.16855 | 2281 | 0.09 | 1520
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 270 | FALSE | 12312.4188 | 3397.4138 | 2.1115 | 101 | 2.73e-05 | 3467 | 46.9819 | 2234 | 0.0036568 | 0.36934 | 2282 | 0.04 | 2120
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 383092 | TRUE | 613.1926 | 613.1926 | 0.3811 | 5 | 0.00016062 | 636 | 14.3241 | 2544 | 0.0036345 | 0.018173 | 2283 | 0.2 | 1163
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 413916 | FALSE | 6367.8068 | 2275.8898 | 1.4145 | 24 | 2.84e-05 | 3448 | 60.5803 | 2151 | 0.0036248 | 0.086994 | 2284 |  | 3529
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 338878 | FALSE | 7522.3054 | 3300.0012 | 2.051 | 23 | 6.64e-05 | 2579 | 72.1128 | 2083 | 0.0036203 | 0.083266 | 2285 |  | 3067
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 524 | FALSE | 10078.6837 | 10078.6837 | 6.2639 | 76 | 0.00026116 | 193 | 18.5187 | 2467 | 0.0036171 | 0.2749 | 2286 | 109.05 | 15
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 903030 | FALSE | 2341.4408 | 2341.4408 | 1.4552 | 17 | 0.00011468 | 1304 | 137.2956 | 1823 | 0.014278 | 0.24273 | 1811 |  | 2699
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 1290 | FALSE | 20913.8819 | 6586.7468 | 4.0937 | 126 | 8.62e-05 | 2030 | 27.953 | 2362 | 0.0035797 | 0.45104 | 2288 | 0.02 | 2529
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | CB | FALSE | 35929.6836 | 35929.6836 | 22.3304 | 271 | 0.00017817 | 517 | 43.307 | 2257 | 0.0035789 | 0.96987 | 2289 | 173.81 | 3
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 461338 | FALSE | 2872.7742 | 2872.7742 | 1.7854 | 24 | 9.4e-05 | 1793 | 40.8144 | 2273 | 0.0035591 | 0.085418 | 2290 |  | 2814
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | CB | FALSE | 3780.8041 | 1415.7705 | 0.87991 | 32 | 0.00022566 | 302 | 20.6051 | 2441 | 0.0035509 | 0.11363 | 2291 | 2.79 | 582
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 949522 | TRUE | 726.8328 | 708.2171 | 0.44016 | 2 | 0.00014682 | 775 | 72.2883 | 2082 | 0.0035464 | 0.0070929 | 2292 |  | 3609
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 13444 | FALSE | 27386.8447 | 27386.8447 | 17.021 | 221 | 7.96e-05 | 2218 | 41.9022 | 2268 | 0.0035258 | 0.77919 | 2293 | 73.64 | 59
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | XR162 | TRUE | 14645.8548 | 989.1765 | 0.61478 | 122 | 5.65e-05 | 2874 | 50.8473 | 2208 | 0.0035232 | 0.42983 | 2294 | 0.05 | 1985
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 246084 | TRUE | 830.435 | 385.2443 | 0.23943 | 7 | 7.14e-05 | 2435 | 49.9181 | 2211 | 0.0035033 | 0.024523 | 2295 |  | 3377
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10728 | FALSE | 16852.1183 | 16852.1183 | 10.4737 | 134 | 0.00034915 | 91 | 6.6304 | 2693 | 0.0034865 | 0.46719 | 2296 | 1.09 | 717
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 63124 | FALSE | 9481.8427 | 9481.8427 | 5.893 | 65 | 0.00021667 | 333 | 31.8764 | 2329 | 0.0034764 | 0.22596 | 2297 | 31.64 | 228
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | CB | FALSE | 2376.1029 | 2376.1029 | 1.4768 | 18 | 0.00021932 | 326 | 147.9963 | 1784 | 0.0034725 | 0.062504 | 2298 | 0.24 | 1098
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 1374 | FALSE | 13460.5941 | 12470.1527 | 7.7503 | 117 | 0.00017559 | 523 | 21.2592 | 2433 | 0.0034694 | 0.40592 | 2299 | 0.12 | 1408
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 203126 | TRUE | 10848.7001 | 107.4611 | 0.066788 | 58 | 6.81e-05 | 2533 | 54.2531 | 2186 | 0.0034419 | 0.19963 | 2300 |  | 3261
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 37300 | FALSE | 11208.5925 | 11208.5925 | 6.9662 | 41 | 9.18e-05 | 1851 | 39.4946 | 2278 | 0.0034152 | 0.14002 | 2301 | 37.82 | 198
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 54932 | FALSE | 7042.6654 | 7042.6654 | 4.377 | 46 | 5.46e-05 | 2930 | 80.6481 | 2045 | 0.0034144 | 0.15706 | 2302 | 25.23 | 272
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 741980 | FALSE | 15211.0337 | 9241.1429 | 5.7434 | 81 | 0.00018104 | 504 | 20.6165 | 2440 | 0.0034064 | 0.27592 | 2303 |  | 2729
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 464 | FALSE | 13038.4156 | 3443.5911 | 2.1402 | 103 | 8.87e-05 | 1965 | 37.0346 | 2297 | 0.0034005 | 0.35026 | 2304 | 0.04 | 2168
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 31304 | FALSE | 34880.3162 | 34880.3162 | 21.6783 | 119 | 0.00010968 | 1417 | 25.8228 | 2381 | 0.0033857 | 0.40289 | 2305 | 0.23 | 1121
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 792628 | TRUE | 1482.8091 | 365.6177 | 0.22723 | 13 | 7.2e-05 | 2420 | 145.9054 | 1789 | 0.0033779 | 0.043913 | 2306 |  | 3408
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | P146 | FALSE | 5911.5651 | 5843.5425 | 3.6318 | 36 | 0.00010288 | 1572 | 24.7391 | 2392 | 0.0033674 | 0.12123 | 2307 | 0.05 | 1925
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 304 | TRUE | 74.6067 | 74.6067 | 0.046368 | 2 | 0.00013842 | 890 | 24.2406 | 2399 | 0.0033555 | 0.006711 | 2308 | 0.18 | 1213
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 663641 | FALSE | 1909.334 | 1173.5613 | 0.72937 | 13 | 0.00014217 | 836 | 35.4244 | 2307 | 0.0033545 | 0.043609 | 2309 |  | 3093
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 9230 | FALSE | 5065.9524 | 4064.6381 | 2.5262 | 41 | 0.00012174 | 1152 | 32.1288 | 2327 | 0.0033425 | 0.13704 | 2310 | 0.04 | 2191
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 336664 | FALSE | 2515.571 | 1158.7417 | 0.72016 | 16 | 6.76e-05 | 2546 | 46.5783 | 2238 | 0.0033324 | 0.053319 | 2311 |  | 3098
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 477890 | FALSE | 4846.0499 | 1726.9794 | 1.0733 | 35 | 9.21e-05 | 1839 | 48.2183 | 2219 | 0.0033264 | 0.11642 | 2312 |  | 2995
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 4222 | FALSE | 26146.3036 | 4245.3884 | 2.6385 | 87 | 3.16e-05 | 3407 | 230.387 | 1585 | 0.0033258 | 0.28934 | 2313 | 0.02 | 2510
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 53130 | FALSE | 22213.2961 | 22213.2961 | 13.8057 | 168 | 4.83e-05 | 3088 | 94.8297 | 1982 | 0.0033207 | 0.55788 | 2314 | 57.28 | 97
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 806392 | FALSE | 8744.0051 | 5446.9277 | 3.3853 | 79 | 6.38e-05 | 2652 | 38.9119 | 2286 | 0.0033155 | 0.26192 | 2315 |  | 2691
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 476 | FALSE | 24463.8896 | 4825.127 | 2.9988 | 97 | 4.6e-05 | 3139 | 73.5453 | 2078 | 0.0032902 | 0.31915 | 2316 | 0.02 | 2460
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 258688 | FALSE | 5700.7117 | 1727.2951 | 1.0735 | 17 | 1.3e-05 | 3601 | 51.8497 | 2202 | 0.0032882 | 0.0559 | 2317 |  | 3463
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 183860 | FALSE | 12288.1398 | 7942.1796 | 4.9361 | 92 | 0.00018091 | 505 | 20.123 | 2446 | 0.0032843 | 0.30215 | 2318 |  | 2779
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 52088 | FALSE | 3986.2342 | 3986.2342 | 2.4775 | 28 | 0.00019225 | 433 | 17.8963 | 2482 | 0.0032783 | 0.091793 | 2319 | 0.06 | 1856
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 1482 | FALSE | 19365.2644 | 19365.2644 | 12.0356 | 43 | 0.0001494 | 744 | 53.6934 | 2189 | 0.0032735 | 0.14076 | 2320 | 0.01 | 2603
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 97574 | FALSE | 8779.1351 | 5743.5714 | 3.5697 | 60 | 8.46e-05 | 2073 | 42.7148 | 2264 | 0.0032547 | 0.19528 | 2321 |  | 3327
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | X06 | TRUE | 20798.4951 | 651.9578 | 0.40519 | 40 | 5.11e-05 | 3012 | 121.2254 | 1866 | 0.0032533 | 0.13013 | 2322 | 0.03 | 2295
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 5178 | FALSE | 11550.9267 | 11550.9267 | 7.1789 | 84 | 0.0001826 | 491 | 17.8913 | 2483 | 0.0032408 | 0.27223 | 2323 | 0.58 | 856
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 2762 | FALSE | 17774.3074 | 15060.1277 | 9.3599 | 138 | 9.11e-05 | 1879 | 28.3252 | 2356 | 0.0032245 | 0.44498 | 2324 | 0.08 | 1622
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 9032 | FALSE | 7741.5059 | 3452.7748 | 2.1459 | 72 | 0.00021411 | 342 | 20.493 | 2443 | 0.0032245 | 0.23216 | 2325 | 0.08 | 1581
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | CB | FALSE | 46476.8109 | 7426.5465 | 4.6156 | 214 | 5.81e-05 | 2833 | 45.5892 | 2241 | 0.003207 | 0.6863 | 2326 | 0.02 | 2421
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 733408 | FALSE | 5546.1563 | 5546.1563 | 3.447 | 45 | 0.00017527 | 527 | 18.0229 | 2479 | 0.0032065 | 0.14429 | 2327 |  | 2660
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 786782 | FALSE | 5173.0207 | 3549.2326 | 2.2059 | 46 | 0.00014664 | 779 | 8.3437 | 2661 | 0.0032053 | 0.14745 | 2328 |  | 2734
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 1658 | FALSE | 7306.3402 | 7306.3402 | 4.5409 | 25 | 0.0001398 | 870 | 46.6629 | 2236 | 0.0031839 | 0.079597 | 2329 | 0.02 | 2471
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 7080 | FALSE | 17026.2434 | 17026.2434 | 10.5819 | 67 | 5.63e-05 | 2881 | 33.4031 | 2317 | 0.0031698 | 0.21238 | 2330 | 0 | 2646
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 716954 | FALSE | 18261.1322 | 11115.6995 | 6.9085 | 97 | 0.00020479 | 383 | 15.7424 | 2521 | 0.0031691 | 0.30741 | 2331 |  | 3112
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 44150 | FALSE | 5746.8082 | 5746.8082 | 3.5717 | 13 | 9.8e-05 | 1689 | 54.8965 | 2182 | 0.0031685 | 0.04119 | 2332 | 0 | 2641
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 3583 | FALSE | 4565.0094 | 4565.0094 | 2.8372 | 38 | 0.00013592 | 920 | 25.7125 | 2385 | 0.0031615 | 0.12014 | 2333 | 0.78 | 781
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | CB | FALSE | 6922.9717 | 6922.9717 | 4.3027 | 57 | 0.00036471 | 81 | 15.0767 | 2531 | 0.0031502 | 0.17956 | 2334 | 10.19 | 401
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 37210 | FALSE | 9746.716 | 9746.716 | 6.0576 | 65 | 0.00021978 | 324 | 16.5241 | 2509 | 0.0031442 | 0.20437 | 2335 | 0.45 | 916
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | CB | FALSE | 6249.0561 | 1615.0564 | 1.0038 | 45 | 3.64e-05 | 3327 | 61.4823 | 2144 | 0.003121 | 0.14045 | 2336 | 0.03 | 2317
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 1258 | TRUE | 7855.298 | 501.9247 | 0.31195 | 65 | 3.96e-05 | 3275 | 27.811 | 2365 | 0.0031184 | 0.2027 | 2337 |  | 2726
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | CB | FALSE | 15128.6127 | 8212.888 | 5.1043 | 106 | 3e-05 | 3427 | 117.1254 | 1887 | 0.0031059 | 0.32923 | 2338 | 0.03 | 2246
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | CB | TRUE | 460.8364 | 460.8364 | 0.28641 | 6 | 0.00063458 | 14 | 4.0266 | 2776 | 0.0031037 | 0.018622 | 2339 | 7.35 | 448
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 457900 | FALSE | 26252.3118 | 19380.7293 | 12.0452 | 208 | 0.00047135 | 40 | 18.1285 | 2474 | 0.0030985 | 0.64448 | 2340 |  | 2650
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 1306 | TRUE | 6582.7615 | 393.5916 | 0.24462 | 55 | 0.0001826 | 490 | 20.3553 | 2444 | 0.0030939 | 0.17016 | 2341 | 9.44 | 409
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 2476 | FALSE | 14000.8931 | 13050.7122 | 8.1111 | 75 | 7.36e-05 | 2378 | 31.4311 | 2335 | 0.0030704 | 0.23028 | 2342 | 0.03 | 2379
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | CB | FALSE | 11764.5735 | 5407.5285 | 3.3608 | 91 | 5.04e-05 | 3027 | 32.7091 | 2324 | 0.0030523 | 0.27776 | 2343 | 0.09 | 1557
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 555034 | FALSE | 4077.2208 | 2404.9179 | 1.4947 | 8 | 0.00031076 | 117 | 13.913 | 2553 | 0.0030461 | 0.024368 | 2344 |  | 3508
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 8952 | FALSE | 10739.4056 | 10739.4056 | 6.6746 | 82 | 0.0001072 | 1467 | 39.4973 | 2277 | 0.0030386 | 0.24916 | 2345 | 9.23 | 411
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 10424 | FALSE | 11629.4934 | 9151.9906 | 5.688 | 87 | 0.00013475 | 931 | 22.367 | 2420 | 0.0030267 | 0.26332 | 2346 | 0.25 | 1072
2267 | ELK 11011298 | 42981101 | ELK 1101 | 1298 | FALSE | 25951.4505 | 19969.5788 | 12.4112 | 119 | 7.36e-05 | 2376 | 48.6421 | 2217 | 0.0030233 | 0.35978 | 2347 | 0.03 | 2376
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 9210 | FALSE | 36192.6146 | 36192.6146 | 22.4939 | 124 | 4.5e-05 | 3160 | 67.0376 | 2108 | 0.0030209 | 0.37459 | 2348 | 0.31 | 1004
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | L1697 | FALSE | 9283.5435 | 9283.5435 | 5.7698 | 70 | 8.78e-05 | 1988 | 45.9015 | 2240 | 0.0030208 | 0.21145 | 2349 | 2.74 | 585
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 51744 | FALSE | 2867.8226 | 2099.9047 | 1.3051 | 25 | 0.00013923 | 883 | 25.8185 | 2382 | 0.0030149 | 0.075372 | 2350 | 0.2 | 1162
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 616 | TRUE | 12968.0682 | 798.8754 | 0.4965 | 103 | 0.00011091 | 1393 | 20.2831 | 2445 | 0.0030112 | 0.31016 | 2351 | 0.3 | 1020
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | LB50 | FALSE | 18304.0568 | 18130.2581 | 11.268 | 65 | 0.00012813 | 1046 | 26.2606 | 2373 | 0.0029902 | 0.19436 | 2352 | 0.21 | 1142
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | CB | FALSE | 26145.2982 | 26145.2982 | 16.2494 | 187 | 8.14e-05 | 2170 | 64.1413 | 2128 | 0.0029901 | 0.55914 | 2353 | 197.3 | 2
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 167792 | FALSE | 7540.5809 | 7540.5809 | 4.6865 | 48 | 0.00016417 | 599 | 22.3539 | 2421 | 0.0029842 | 0.14324 | 2354 | 27.41 | 258
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 34426 | FALSE | 11062.821 | 7591.2944 | 4.718 | 81 | 0.0001041 | 1549 | 18.642 | 2465 | 0.0029697 | 0.24054 | 2355 | 0.2 | 1161
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | LA64 | FALSE | 20425.5788 | 20425.5788 | 12.6946 | 152 | 0.00024137 | 243 | 12.4217 | 2580 | 0.0029684 | 0.4512 | 2356 | 0.94 | 741
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 8091 | FALSE | 9678.478 | 9678.478 | 6.0152 | 69 | 0.00018296 | 489 | 17.2834 | 2497 | 0.0029648 | 0.20457 | 2357 | 0.38 | 961
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 12758 | FALSE | 9624.9945 | 9624.9945 | 5.982 | 70 | 0.00033735 | 98 | 10.9337 | 2611 | 0.002947 | 0.20629 | 2358 | 6.96 | 456
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 5066 | FALSE | 22120.764 | 22120.764 | 13.7481 | 121 | 0.00018064 | 508 | 16.1765 | 2514 | 0.0029066 | 0.35169 | 2359 | 0.48 | 902
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 602 | FALSE | 38446.6729 | 26032.3379 | 16.1792 | 115 | 5.78e-05 | 2842 | 48.2008 | 2220 | 0.0028981 | 0.33328 | 2360 | 0.08 | 1633
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 1384 | FALSE | 14709.9253 | 14709.9253 | 9.1423 | 106 | 0.00030207 | 128 | 17.1106 | 2502 | 0.0028857 | 0.30589 | 2361 | 0.08 | 1664
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 10714 | FALSE | 31415.1888 | 22795.5157 | 14.1675 | 212 | 9e-05 | 1915 | 34.8828 | 2308 | 0.002884 | 0.61141 | 2362 | 0.2 | 1158
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | CB | FALSE | 17856.3948 | 7352.5883 | 4.5697 | 146 | 2.58e-05 | 3489 | 57.0849 | 2170 | 0.0028615 | 0.41777 | 2363 | 0.1 | 1489
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 147198 | FALSE | 3096.6231 | 2173.9439 | 1.3511 | 24 | 0.00013298 | 958 | 27.8556 | 2363 | 0.0028527 | 0.068464 | 2364 |  | 3161
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 5206 | FALSE | 11520.3774 | 11520.3774 | 7.16 | 78 | 0.00028525 | 147 | 13.4764 | 2563 | 0.0028386 | 0.22141 | 2365 | 16.08 | 342
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 202 | FALSE | 8481.1425 | 8481.1425 | 5.2711 | 55 | 0.00023689 | 257 | 9.574 | 2632 | 0.0028293 | 0.15561 | 2366 | 77.47 | 54
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 2624 | FALSE | 30794.7643 | 29790.8638 | 18.5151 | 148 | 5.86e-05 | 2819 | 45.0109 | 2246 | 0.0028273 | 0.41844 | 2367 | 0.19 | 1182
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 10590 | FALSE | 26358.3376 | 26358.3376 | 16.3818 | 199 | 7.29e-05 | 2395 | 56.6573 | 2172 | 0.0028226 | 0.56169 | 2368 | 0.28 | 1046
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | CB | FALSE | 14569.4696 | 14569.4696 | 9.055 | 110 | 0.00015914 | 650 | 17.5722 | 2489 | 0.0028161 | 0.30977 | 2369 | 97.72 | 22
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | LC14 | FALSE | 17935.8798 | 15879.1839 | 9.869 | 137 | 0.0001215 | 1156 | 25.9229 | 2378 | 0.0028157 | 0.38575 | 2370 | 0.15 | 1303
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 2046 | FALSE | 14788.0543 | 14724.19 | 9.1511 | 57 | 2.91e-05 | 3438 | 49.5192 | 2213 | 0.0028141 | 0.1604 | 2371 | 3.25 | 552
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 84480 | FALSE | 7615.7819 | 7615.7819 | 4.7332 | 50 | 0.00012015 | 1184 | 18.1285 | 2473 | 0.0028064 | 0.14032 | 2372 | 43.55 | 166
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | V58 | FALSE | 3619.1201 | 1838.4445 | 1.1426 | 25 | 3.68e-05 | 3317 | 42.8997 | 2262 | 0.0027879 | 0.069698 | 2373 | 0.25 | 1081
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 2436 | FALSE | 8535.8961 | 8535.8961 | 5.3051 | 19 | 3.58e-05 | 3338 | 86.4703 | 2020 | 0.0027598 | 0.052436 | 2374 | 0.06 | 1878
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 69550 | FALSE | 28222.9499 | 28222.9499 | 17.5407 | 188 | 0.00019115 | 436 | 15.1137 | 2529 | 0.0027545 | 0.51784 | 2375 | 0.88 | 753
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 294 | TRUE | 13929.6308 | 0 | 0 | 66 | 3.76e-05 | 3303 | 12.2945 | 2582 | 0.002743 | 0.18104 | 2376 | 1.46 | 672
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 7273 | FALSE | 10648.4179 | 10648.4179 | 6.618 | 38 | 0.00010776 | 1456 | 24.4514 | 2395 | 0.0027408 | 0.10415 | 2377 |  | 3023
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 2637 | FALSE | 6500.6025 | 6500.6025 | 4.0402 | 28 | 7.36e-05 | 2375 | 33.1621 | 2319 | 0.0027385 | 0.076678 | 2378 | 0.06 | 1783
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 10912 | FALSE | 7824.9032 | 7824.9032 | 4.8632 | 54 | 0.00030255 | 127 | 14.5938 | 2539 | 0.0027343 | 0.14765 | 2379 | 17.3 | 333
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | CB | TRUE | 830.5012 | 830.5012 | 0.51616 | 7 | 2.83e-05 | 3450 | 82.5251 | 2038 | 0.0027213 | 0.019049 | 2380 | 0 | 2645
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 12824 | FALSE | 19725.4463 | 1410.0846 | 0.87637 | 97 | 5.89e-05 | 2811 | 61.7022 | 2142 | 0.0027199 | 0.26383 | 2381 | 0.19 | 1178
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 4048 | FALSE | 45554.4794 | 29209.8997 | 18.1541 | 157 | 5.52e-05 | 2907 | 56.2888 | 2174 | 0.0027194 | 0.42694 | 2382 | 0.07 | 1678
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 2206 | FALSE | 27876.5924 | 6659.3031 | 4.1388 | 227 | 0.00050121 | 31 | 12.7346 | 2573 | 0.0027 | 0.61291 | 2383 |  | 2664
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 91926 | FALSE | 17004.3113 | 10358.7223 | 6.438 | 48 | 0.00024845 | 221 | 9.7992 | 2628 | 0.0026935 | 0.12929 | 2384 | 0.04 | 2095
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 3010 | TRUE | 14671.2868 | 569.5009 | 0.35395 | 106 | 8.43e-05 | 2082 | 23.6594 | 2409 | 0.0026922 | 0.28537 | 2385 | 0.03 | 2262
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 1888 | FALSE | 30440.0056 | 30440.0056 | 18.9186 | 231 | 9.56e-05 | 1738 | 52.6578 | 2198 | 0.0026855 | 0.62036 | 2386 | 136.25 | 4
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10298 | FALSE | 21540.3253 | 17635.9747 | 10.9608 | 138 | 0.00011425 | 1313 | 23.0219 | 2412 | 0.0026825 | 0.37018 | 2387 | 0.67 | 817
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 10214 | FALSE | 22409.5851 | 22409.5851 | 13.9276 | 149 | 0.00015 | 735 | 18.095 | 2476 | 0.0026769 | 0.39885 | 2388 | 59.12 | 90
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 36674 | FALSE | 15144.1466 | 15144.1466 | 9.4121 | 125 | 0.00010056 | 1635 | 28.0218 | 2361 | 0.0026639 | 0.33299 | 2389 | 88.72 | 34
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 29362 | FALSE | 18377.6603 | 12371.5145 | 7.6889 | 74 | 0.00019405 | 424 | 17.4096 | 2493 | 0.0026559 | 0.19654 | 2390 | 0.15 | 1302
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 37286 | FALSE | 5924.4605 | 4150.8287 | 2.5798 | 25 | 7.38e-05 | 2365 | 26.9712 | 2368 | 0.0026543 | 0.066357 | 2391 | 0.03 | 2256
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 10207 | FALSE | 5731.5328 | 5731.5328 | 3.5622 | 38 | 5.27e-05 | 2978 | 53.21 | 2193 | 0.0026426 | 0.10042 | 2392 | 4.55 | 517
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 437582 | FALSE | 3785.2974 | 1172.6243 | 0.72879 | 31 | 9.37e-05 | 1803 | 36.8732 | 2299 | 0.0026389 | 0.081807 | 2393 |  | 2902
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | MR337 | FALSE | 30458.1324 | 14629.5479 | 9.0923 | 193 | 2.07e-05 | 3536 | 31.7021 | 2331 | 0.0026206 | 0.50578 | 2394 |  | 2704
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 95690 | FALSE | 6226.9882 | 6226.9882 | 3.8701 | 58 | 0.00043813 | 55 | 3.7552 | 2782 | 0.0026164 | 0.15175 | 2395 | 0.66 | 821
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 450582 | FALSE | 6805.9936 | 4807.846 | 2.9881 | 50 | 8.46e-05 | 2074 | 22.3998 | 2418 | 0.0026097 | 0.13049 | 2396 | 0.06 | 1776
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | CB | FALSE | 8801.7452 | 2701.0978 | 1.6787 | 82 | 0.00031315 | 115 | 15.1124 | 2530 | 0.0026094 | 0.21397 | 2397 | 0.1 | 1502
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | CB | FALSE | 7486.7827 | 7486.7827 | 4.6531 | 45 | 0.00027461 | 168 | 11.6886 | 2594 | 0.0025849 | 0.11632 | 2398 | 26.9 | 264
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | CB | FALSE | 8911.8997 | 7279.8498 | 4.5245 | 36 | 3.3e-05 | 3385 | 43.2592 | 2258 | 0.0025798 | 0.092875 | 2399 | 0.04 | 2119
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | CB | TRUE | 2118.6497 | 279.4297 | 0.17367 | 22 | 6.83e-05 | 2527 | 21.6949 | 2429 | 0.0025794 | 0.056746 | 2400 | 0.44 | 921
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 173934 | FALSE | 17611.7153 | 17611.7153 | 10.9458 | 125 | 0.00011938 | 1199 | 28.2053 | 2358 | 0.0025705 | 0.32131 | 2401 |  | 2727
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | V66 | FALSE | 26099.4541 | 5840.07 | 3.6296 | 151 | 5.49e-05 | 2915 | 48.8236 | 2216 | 0.0025703 | 0.38811 | 2402 | 0.03 | 2264
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | CB | TRUE | 9964.9315 | 415.9182 | 0.25849 | 45 | 5.4e-05 | 2942 | 29.9475 | 2345 | 0.0025606 | 0.11523 | 2403 | 0.02 | 2456
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 2784 | FALSE | 24673.5503 | 23592.2379 | 14.6627 | 202 | 0.0002125 | 349 | 16.1455 | 2515 | 0.0025529 | 0.51568 | 2404 | 21.1 | 301
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 247511 | FALSE | 3219.7109 | 1938.4111 | 1.2047 | 26 | 5.87e-05 | 2816 | 39.41 | 2279 | 0.0025357 | 0.065929 | 2405 |  | 2844
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | XR374 | TRUE | 4853.8508 | 763.9032 | 0.47477 | 29 | 5.59e-05 | 2893 | 52.1032 | 2201 | 0.002531 | 0.073398 | 2406 | 0.04 | 2155
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 1520 | FALSE | 14435.9237 | 14435.9237 | 8.972 | 69 | 0.0002442 | 234 | 18.3262 | 2471 | 0.002519 | 0.17381 | 2407 | 0.04 | 2139
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 424048 | FALSE | 1501.8611 | 1068.5882 | 0.66413 | 12 | 6.07e-05 | 2756 | 33.0472 | 2323 | 0.002517 | 0.030204 | 2408 |  | 3298
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | CB | FALSE | 10068.8846 | 2571.5147 | 1.5982 | 80 | 4.13e-05 | 3240 | 78.3943 | 2057 | 0.0025158 | 0.20127 | 2409 | 0.42 | 929
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 477 | FALSE | 2946.6356 | 2946.6356 | 1.8313 | 25 | 0.00015508 | 692 | 16.2294 | 2513 | 0.002515 | 0.062875 | 2410 | 3.59 | 539
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 823548 | FALSE | 31748.5399 | 31748.5399 | 19.7318 | 231 | 6.08e-05 | 2755 | 41.9518 | 2266 | 0.0025098 | 0.57976 | 2411 |  | 2944
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 19742 | FALSE | 12071.9353 | 10549.7356 | 6.5567 | 92 | 0.00023207 | 278 | 8.0743 | 2669 | 0.0025093 | 0.23086 | 2412 | 0.09 | 1571
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 646 | FALSE | 19795.1478 | 13544.3225 | 8.4179 | 154 | 0.00011949 | 1196 | 18.0896 | 2477 | 0.0025033 | 0.3855 | 2413 | 28.71 | 246
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | CB | FALSE | 13834.375 | 12733.914 | 7.9142 | 113 | 0.00013093 | 994 | 85.2135 | 2029 | 0.0098816 | 1.1166 | 1963 | 0.08 | 1671
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | XR028 | FALSE | 16732.9663 | 1226.5796 | 0.76232 | 134 | 6.21e-05 | 2717 | 31.865 | 2330 | 0.0024946 | 0.33428 | 2415 | 0.03 | 2231
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | CB | FALSE | 27553.0792 | 12591.5795 | 7.8257 | 180 | 4.2e-05 | 3225 | 36.6519 | 2300 | 0.0024688 | 0.44438 | 2416 | 0.03 | 2341
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 45268 | FALSE | 12405.1563 | 4400.5557 | 2.735 | 112 | 8.34e-05 | 2119 | 27.4918 | 2366 | 0.0024458 | 0.27393 | 2417 | 0.06 | 1780
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 914376 | TRUE | 11215.1853 | 862.0577 | 0.53577 | 93 | 8.18e-05 | 2159 | 28.2406 | 2357 | 0.0024267 | 0.22569 | 2418 | 0.04 | 2227
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 478699 | FALSE | 1763.8687 | 1328.3865 | 0.8256 | 14 | 8.28e-05 | 2136 | 37.3598 | 2294 | 0.0024262 | 0.033967 | 2419 |  | 3466
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 2022 | FALSE | 25888.9554 | 25888.9554 | 16.0901 | 207 | 0.0001628 | 614 | 14.0752 | 2547 | 0.0024209 | 0.50113 | 2420 | 126.01 | 10
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 772210 | FALSE | 5622.5297 | 1329.7793 | 0.82646 | 32 | 0.0003009 | 129 | 8.4673 | 2658 | 0.0023979 | 0.076733 | 2421 |  | 2876
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | CB | FALSE | 14897.5939 | 14897.5939 | 9.2589 | 116 | 0.00026838 | 176 | 10.7214 | 2615 | 0.0023893 | 0.27716 | 2422 | 0.08 | 1670
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | CB | FALSE | 7077.2532 | 2179.3543 | 1.3545 | 22 | 7.86e-05 | 2246 | 23.8165 | 2407 | 0.0023847 | 0.052462 | 2423 | 0.16 | 1259
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 415382 | TRUE | 1920.3588 | 97.0433 | 0.060313 | 8 | 1.77e-05 | 3562 | 59.385 | 2159 | 0.0023723 | 0.018978 | 2424 |  | 3205
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 76088 | FALSE | 17715.9929 | 17715.9929 | 11.0106 | 124 | 8.45e-05 | 2076 | 27.0945 | 2367 | 0.0023715 | 0.29407 | 2425 | 0.08 | 1589
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 36888 | TRUE | 977.9121 | 977.9121 | 0.60778 | 7 | 0.00011804 | 1228 | 17.0465 | 2504 | 0.0023702 | 0.016592 | 2426 | 28.15 | 253
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 647842 | TRUE | 1016.9284 | 187.7325 | 0.11668 | 6 | 4.43e-05 | 3184 | 47.9751 | 2222 | 0.0023697 | 0.014218 | 2427 |  | 2958
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 3970 | FALSE | 11750.7224 | 11750.7224 | 7.3031 | 87 | 0.00015476 | 697 | 11.2679 | 2601 | 0.0023638 | 0.20565 | 2428 | 0.85 | 765
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 1236 | FALSE | 6557.8129 | 5809.1133 | 3.6104 | 34 | 0.00011532 | 1292 | 31.2219 | 2338 | 0.0023633 | 0.080354 | 2429 | 0.06 | 1825
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 23190 | FALSE | 5918.813 | 5918.813 | 3.6786 | 45 | 0.00031007 | 118 | 11.1572 | 2604 | 0.0023536 | 0.10591 | 2430 | 0.09 | 1566
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 10270 | FALSE | 6119.8962 | 6119.8962 | 3.8035 | 39 | 3.22e-05 | 3398 | 67.2012 | 2107 | 0.002349 | 0.091612 | 2431 | 0.07 | 1697
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 4421 | TRUE | 585.3593 | 585.3593 | 0.3638 | 5 | 8.48e-05 | 2068 | 28.5837 | 2354 | 0.0023217 | 0.011609 | 2432 | 18.46 | 321
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | V74 | FALSE | 8209.0598 | 6901.1378 | 4.2891 | 61 | 4.74e-05 | 3107 | 40.6895 | 2274 | 0.0023119 | 0.14103 | 2433 | 0.09 | 1509
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | CB | FALSE | 7725.5743 | 3167.0883 | 1.9684 | 66 | 5.6e-05 | 2888 | 47.8787 | 2223 | 0.0022934 | 0.15136 | 2434 | 0.04 | 2137
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 10720 | FALSE | 7578.3102 | 7578.3102 | 4.71 | 44 | 0.00059263 | 19 | 5.4692 | 2730 | 0.002283 | 0.10045 | 2435 | 61.7 | 86
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | V88 | FALSE | 5002.7309 | 1732.6065 | 1.0768 | 48 | 3.42e-05 | 3365 | 36.539 | 2301 | 0.002278 | 0.10934 | 2436 | 0.6 | 853
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 32180 | FALSE | 4085.725 | 3970.2131 | 2.4675 | 36 | 0.0001328 | 963 | 9.9964 | 2624 | 0.0022763 | 0.081948 | 2437 | 0.25 | 1076
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 8403 | FALSE | 7867.7292 | 7867.7292 | 4.8898 | 42 | 0.00015778 | 666 | 14.7825 | 2533 | 0.0022738 | 0.095499 | 2438 | 0.41 | 941
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 1415 | FALSE | 1913.2696 | 1280.0188 | 0.79554 | 14 | 0.00015385 | 711 | 13.6482 | 2558 | 0.0022706 | 0.031789 | 2439 | 2.72 | 587
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 2090 | FALSE | 23726.1931 | 23726.1931 | 14.7459 | 183 | 0.00011006 | 1410 | 20.7182 | 2438 | 0.0022675 | 0.41496 | 2440 | 71.03 | 68
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | CB | TRUE | 19915.785 | 875.3178 | 0.54401 | 166 | 8.63e-05 | 2028 | 19.7079 | 2452 | 0.0022645 | 0.37591 | 2441 | 3.46 | 545
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 12840 | FALSE | 6323.0478 | 6323.0478 | 3.9298 | 50 | 0.00014417 | 811 | 15.7468 | 2520 | 0.002258 | 0.1129 | 2442 | 0.4 | 948
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 49394 | FALSE | 14105.1915 | 1836.8422 | 1.1416 | 111 | 2.06e-05 | 3538 | 59.3555 | 2160 | 0.0022509 | 0.24985 | 2443 | 0.03 | 2277
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2760 | FALSE | 4358.9956 | 4358.9956 | 2.7091 | 28 | 8.77e-05 | 1995 | 28.0773 | 2360 | 0.0022393 | 0.062701 | 2444 | 0.65 | 826
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 2327 | FALSE | 2038.9698 | 1914.889 | 1.1901 | 20 | 0.00013326 | 953 | 15.5189 | 2523 | 0.0022381 | 0.044762 | 2445 | 0.08 | 1640
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 445166 | FALSE | 15269.7955 | 12164.2635 | 7.5601 | 71 | 5.97e-05 | 2785 | 28.1893 | 2359 | 0.0022354 | 0.15871 | 2446 | 0.06 | 1845
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 45292 | FALSE | 17350.6047 | 17350.6047 | 10.7835 | 132 | 8.2e-05 | 2156 | 36.0802 | 2304 | 0.002235 | 0.29501 | 2447 | 129.86 | 5
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | CB | FALSE | 2942.811 | 2690.5619 | 1.6722 | 19 | 0.00013353 | 951 | 20.0821 | 2447 | 0.0022279 | 0.042331 | 2448 | 0.05 | 2033
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 438 | FALSE | 9219.1151 | 8226.4088 | 5.1127 | 48 | 7.12e-05 | 2440 | 29.805 | 2347 | 0.0022241 | 0.10675 | 2449 | 0.05 | 2035
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 738 | FALSE | 12990.1187 | 4208.5049 | 2.6156 | 106 | 7.61e-05 | 2304 | 26.5188 | 2371 | 0.0022159 | 0.23488 | 2450 | 0.03 | 2251
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | CB | FALSE | 3376.1921 | 3376.1921 | 2.0983 | 27 | 0.00018738 | 459 | 22.0757 | 2425 | 0.0021922 | 0.059189 | 2451 | 44.75 | 154
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 78672 | FALSE | 14393.4787 | 6078.7898 | 3.778 | 123 | 7.98e-05 | 2211 | 9.5346 | 2635 | 0.0021883 | 0.26916 | 2452 | 0.15 | 1304
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 678 | FALSE | 3004.004 | 3004.004 | 1.867 | 17 | 0.00013325 | 954 | 26.6461 | 2369 | 0.002188 | 0.037196 | 2453 | 48.48 | 128
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 86658 | FALSE | 1081.812 | 1029.0279 | 0.63954 | 7 | 0.00024387 | 235 | 13.6494 | 2557 | 0.0021861 | 0.015303 | 2454 | 0.02 | 2563
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 1021 | FALSE | 6702.9103 | 6702.9103 | 4.1659 | 56 | 6.99e-05 | 2478 | 34.4442 | 2311 | 0.0021716 | 0.12161 | 2455 | 8.36 | 430
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 10296 | FALSE | 23203.5804 | 23203.5804 | 14.4211 | 181 | 0.00028227 | 151 | 8.472 | 2657 | 0.0021702 | 0.3928 | 2456 | 20.94 | 303
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 987714 | FALSE | 1590.9598 | 1218.9668 | 0.75759 | 6 | 0.00013453 | 933 | 18.5736 | 2466 | 0.0021699 | 0.01302 | 2457 |  | 3580
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 2514 | FALSE | 31420.4965 | 17648.4979 | 10.9686 | 212 | 0.00019439 | 421 | 17.5789 | 2488 | 0.0021687 | 0.45975 | 2458 | 0.04 | 2164
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 508410 | FALSE | 8406.5825 | 7530.8771 | 4.6805 | 73 | 0.0002728 | 169 | 8.8564 | 2647 | 0.002162 | 0.15783 | 2459 |  | 2754
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 5074 | FALSE | 4940.828 | 2196.7079 | 1.3653 | 34 | 7.86e-05 | 2245 | 54.9615 | 2181 | 0.0021548 | 0.073264 | 2460 | 0.03 | 2294
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 344250 | FALSE | 1668.1837 | 1299.2708 | 0.8075 | 10 | 4.89e-05 | 3068 | 38.0392 | 2290 | 0.0021484 | 0.021484 | 2461 | 0.03 | 2252
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 355914 | FALSE | 14935.3832 | 13002.7807 | 8.0813 | 104 | 0.0002048 | 382 | 13.3148 | 2566 | 0.0021471 | 0.2233 | 2462 |  | 2817
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | W20 | FALSE | 6313.3606 | 3551.7376 | 2.2074 | 48 | 4.07e-05 | 3252 | 28.7718 | 2351 | 0.0021357 | 0.10251 | 2463 | 0.02 | 2548
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 5020 | FALSE | 24253.1314 | 24253.1314 | 15.0734 | 185 | 0.00021261 | 348 | 14.5867 | 2540 | 0.0021265 | 0.3934 | 2464 | 82.74 | 42
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 857148 | FALSE | 3180.8041 | 1503.7135 | 0.93456 | 31 | 4.6e-05 | 3140 | 22.3402 | 2422 | 0.0021126 | 0.065491 | 2465 |  | 3247
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 554 | TRUE | 17322.4158 | 0 | 0 | 130 | 6.95e-05 | 2487 | 22.3741 | 2419 | 0.0021107 | 0.2744 | 2466 | 0.33 | 985
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 39216 | FALSE | 5158.2623 | 2624.8047 | 1.6313 | 41 | 0.00049128 | 32 | 7.6005 | 2675 | 0.0021 | 0.086098 | 2467 | 0.31 | 998
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 4706 | FALSE | 18429.634 | 18429.634 | 11.4541 | 138 | 8.05e-05 | 2193 | 25.0428 | 2390 | 0.0020959 | 0.28923 | 2468 | 94.56 | 27
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 6645 | FALSE | 6787.3604 | 6787.3604 | 4.2184 | 52 | 9.53e-05 | 1753 | 25.6675 | 2386 | 0.0020868 | 0.10851 | 2469 | 54.01 | 109
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | MR332 | TRUE | 4548.7457 | 520.6629 | 0.32359 | 31 | 7.63e-05 | 2299 | 24.407 | 2396 | 0.0020705 | 0.064186 | 2470 | 0.38 | 963
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 868170 | FALSE | 15451.7071 | 14595.2194 | 9.071 | 59 | 3.81e-05 | 3298 | 52.9097 | 2197 | 0.0020479 | 0.12083 | 2471 |  | 2853
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 3144 | FALSE | 8269.2517 | 7828.9119 | 4.8657 | 58 | 0.00015369 | 715 | 19.1385 | 2460 | 0.0020462 | 0.11868 | 2472 | 0.09 | 1549
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 839669 | TRUE | 1273.7836 | 989.219 | 0.6148 | 12 | 0.00010611 | 1492 | 23.2008 | 2411 | 0.0020383 | 0.02446 | 2473 |  | 3373
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 5096 | FALSE | 32680.7032 | 32680.7032 | 20.3112 | 232 | 0.00019642 | 411 | 13.592 | 2561 | 0.0020379 | 0.4728 | 2474 | 12.58 | 372
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | CB | FALSE | 3445.1403 | 3361.7302 | 2.0893 | 23 | 0.00019412 | 423 | 17.2869 | 2496 | 0.0020369 | 0.046849 | 2475 | 0.54 | 878
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | CB | FALSE | 3448.2579 | 2568.9228 | 1.5966 | 22 | 5.29e-05 | 2970 | 18.4256 | 2469 | 0.0020177 | 0.044389 | 2476 | 0.05 | 1991
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | CB | FALSE | 7286.2366 | 7286.2366 | 4.5284 | 49 | 0.00021269 | 347 | 6.3725 | 2702 | 0.0020136 | 0.098667 | 2477 | 46.29 | 143
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2500 | FALSE | 3521.417 | 3521.417 | 2.1886 | 26 | 4.84e-05 | 3083 | 44.8707 | 2248 | 0.0019811 | 0.05151 | 2478 | 0.16 | 1255
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 169700 | FALSE | 13421.5222 | 13421.5222 | 8.3415 | 63 | 7.4e-05 | 2357 | 25.346 | 2387 | 0.001973 | 0.1243 | 2479 |  | 2693
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | CB | FALSE | 14982.4076 | 8539.83 | 5.3075 | 130 | 9.09e-05 | 1886 | 25.7754 | 2384 | 0.0019722 | 0.25639 | 2480 | 0.62 | 843
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 134 | FALSE | 13416.4816 | 13272.5409 | 8.2489 | 99 | 9.58e-05 | 1735 | 24.5453 | 2393 | 0.0019671 | 0.19475 | 2481 | 0.04 | 2145
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 995672 | FALSE | 9263.8953 | 5928.6387 | 3.6847 | 79 | 0.00018258 | 492 | 13.4013 | 2564 | 0.0019604 | 0.15487 | 2482 | 0.08 | 1645
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 99096 | FALSE | 15944.165 | 15895.8244 | 9.8793 | 56 | 9.38e-05 | 1796 | 20.9972 | 2437 | 0.0019603 | 0.10978 | 2483 | 0.05 | 2008
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 121988 | FALSE | 11219.1712 | 11219.1712 | 6.9728 | 92 | 0.00027094 | 171 | 5.2336 | 2742 | 0.0019488 | 0.17929 | 2484 |  | 2725
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 10960 | FALSE | 45089.9597 | 30132.5386 | 18.7275 | 320 | 9.21e-05 | 1838 | 18.2529 | 2472 | 0.0019454 | 0.62252 | 2485 | 0.12 | 1381
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 453266 | TRUE | 510.1509 | 510.1509 | 0.31706 | 5 | 4.86e-05 | 3071 | 42.8367 | 2263 | 0.0019312 | 0.0096562 | 2486 |  | 3444
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | CB | FALSE | 12268.6539 | 7279.3949 | 4.5242 | 93 | 7.19e-05 | 2421 | 13.0319 | 2569 | 0.0019107 | 0.17769 | 2487 | 1.2 | 702
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 93418 | FALSE | 4145.9232 | 4145.9232 | 2.5767 | 23 | 6.45e-05 | 2627 | 45.5233 | 2243 | 0.0019038 | 0.043787 | 2488 | 0.16 | 1254
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 697500 | FALSE | 10836.6474 | 10836.6474 | 6.735 | 74 | 0.00017368 | 536 | 8.0975 | 2667 | 0.0019029 | 0.14082 | 2489 |  | 3178
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 3127 | FALSE | 15418.4131 | 15054.5806 | 9.3565 | 78 | 0.00010691 | 1479 | 266.083 | 1507 | 0.030422 | 2.3729 | 1454 | 0.62 | 840
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 1158 | FALSE | 8353.2531 | 3588.3989 | 2.2302 | 65 | 5.69e-05 | 2865 | 5.9152 | 2715 | 0.0018981 | 0.12337 | 2491 | 0.17 | 1241
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 576 | FALSE | 13079.4255 | 1582.5592 | 0.98357 | 116 | 0.00012308 | 1132 | 17.5488 | 2490 | 0.0018636 | 0.21618 | 2492 | 0.15 | 1287
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 7008 | FALSE | 29112.5788 | 8088.7008 | 5.0272 | 122 | 2.17e-05 | 3523 | 36.2639 | 2302 | 0.0018473 | 0.22537 | 2493 | 0.03 | 2381
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 648928 | FALSE | 7727.8743 | 6359.2353 | 3.9523 | 44 | 6.13e-05 | 2741 | 57.7042 | 2168 | 0.0018437 | 0.081123 | 2494 | 0.04 | 2170
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 535998 | FALSE | 7941.4498 | 7140.4635 | 4.4378 | 43 | 0.00012358 | 1129 | 19.4088 | 2455 | 0.0018414 | 0.079178 | 2495 |  | 3367
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 12947 | FALSE | 5709.2465 | 5709.2465 | 3.5483 | 49 | 0.00010562 | 1503 | 18.015 | 2480 | 0.0018388 | 0.0901 | 2496 | 10.69 | 395
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 57840 | FALSE | 4238.9331 | 4238.9331 | 2.6345 | 29 | 0.00029837 | 131 | 7.443 | 2678 | 0.0018331 | 0.053161 | 2497 | 0.36 | 971
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | CB | TRUE | 28346.0077 | 787.8623 | 0.48966 | 259 | 8.16e-05 | 2165 | 14.0393 | 2549 | 0.0018283 | 0.47354 | 2498 | 0.05 | 1935
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 954 | FALSE | 13095.0591 | 12372.699 | 7.6897 | 78 | 9.45e-05 | 1782 | 22.5908 | 2415 | 0.0018244 | 0.1423 | 2499 | 0.05 | 1972
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 1704 | FALSE | 21239.3917 | 21231.8185 | 13.1957 | 160 | 0.00012962 | 1014 | 19.3786 | 2457 | 0.001823 | 0.29168 | 2500 | 0.18 | 1207
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 9031 | FALSE | 1741.4201 | 1741.4201 | 1.0823 | 17 | 0.00019853 | 401 | 5.6599 | 2722 | 0.0018195 | 0.030932 | 2501 | 26.99 | 262
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | CB | FALSE | 25157.6923 | 15741.0344 | 9.7831 | 214 | 7.93e-05 | 2226 | 25.8956 | 2379 | 0.0018118 | 0.38772 | 2502 | 0.19 | 1192
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | V28 | FALSE | 14462.1376 | 1958.2873 | 1.2171 | 99 | 2.09e-05 | 3535 | 31.9058 | 2328 | 0.0018053 | 0.17873 | 2503 | 0.03 | 2284
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 6421 | FALSE | 2777.3682 | 2777.3682 | 1.7261 | 20 | 5.77e-05 | 2846 | 26.2004 | 2374 | 0.0018044 | 0.036089 | 2504 | 0.14 | 1307
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 12760 | FALSE | 42462.3954 | 42462.3954 | 26.3906 | 299 | 0.00019594 | 413 | 10.5604 | 2618 | 0.0017903 | 0.53531 | 2505 | 1.92 | 630
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | CB | FALSE | 3500.023 | 3442.3441 | 2.1394 | 26 | 0.00012024 | 1181 | 17.4311 | 2492 | 0.0017811 | 0.04631 | 2506 | 0.23 | 1119
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | BL 1101 | FALSE | 13568.3761 | 13568.3761 | 8.4328 | 101 | 0.00030613 | 124 | 6.186 | 2709 | 0.0017681 | 0.17858 | 2507 | 25.42 | 271
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 10190 | FALSE | 13591.0884 | 13591.0884 | 8.4469 | 61 | 6.36e-05 | 2659 | 28.5039 | 2355 | 0.0017583 | 0.10725 | 2508 | 52.84 | 111
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 272636 | TRUE | 431.3681 | 431.3681 | 0.2681 | 5 | 2.85e-05 | 3445 | 33.4034 | 2316 | 0.0017542 | 0.0087708 | 2509 |  | 3545
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 510055 | TRUE | 1976.5067 | 817.6203 | 0.50815 | 11 | 5.93e-05 | 2794 | 33.1507 | 2320 | 0.0017489 | 0.019238 | 2510 |  | 3426
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 307832 | FALSE | 22986.441 | 2614.1136 | 1.6247 | 133 | 5.41e-05 | 2940 | 52.2996 | 2199 | 0.0017438 | 0.23192 | 2511 |  | 2750
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 19542 | FALSE | 15319.5774 | 15319.5774 | 9.5212 | 111 | 0.00024603 | 231 | 13.9871 | 2550 | 0.0017374 | 0.19285 | 2512 | 87.42 | 37
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 2100 | FALSE | 6391.6672 | 6391.6672 | 3.9724 | 47 | 0.00013966 | 875 | 17.2588 | 2498 | 0.0017366 | 0.081621 | 2513 | 19.6 | 310
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 8299 | FALSE | 1934.2169 | 1934.2169 | 1.2021 | 13 | 0.0001379 | 895 | 14.6935 | 2537 | 0.0017192 | 0.02235 | 2514 | 62.52 | 83
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 108540 | FALSE | 7751.409 | 7751.409 | 4.8175 | 44 | 0.00010534 | 1511 | 10.8681 | 2613 | 0.001717 | 0.075547 | 2515 | 25 | 274
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8120 | FALSE | 14371.6326 | 14371.6326 | 8.932 | 108 | 0.00014141 | 847 | 24.2646 | 2397 | 0.0017068 | 0.18434 | 2516 | 0.12 | 1384
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | E510R | TRUE | 9824.475 | 807.8365 | 0.50207 | 84 | 6.44e-05 | 2631 | 25.303 | 2388 | 0.0017029 | 0.14305 | 2517 | 0.06 | 1864
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 2902 | FALSE | 11242.8228 | 11242.8228 | 6.9875 | 8 | 0.00012146 | 1158 | 50.5933 | 2209 | 0.0016954 | 0.013563 | 2518 | 0.04 | 2100
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 863822 | TRUE | 1030.95 | 168.7519 | 0.10488 | 8 | 3.67e-05 | 3321 | 27.8163 | 2364 | 0.0016933 | 0.013546 | 2519 |  | 2906
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 396264 | FALSE | 10259.9636 | 7704.2 | 4.7882 | 95 | 0.00010348 | 1560 | 21.8184 | 2427 | 0.0016927 | 0.16081 | 2520 |  | 2903
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 2200 | FALSE | 8965.9106 | 8965.9106 | 5.5723 | 64 | 0.00010183 | 1607 | 17.8909 | 2484 | 0.0016888 | 0.10808 | 2521 | 54.83 | 105
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 2406 | TRUE | 6309.8622 | 123.5636 | 0.076795 | 50 | 0.0001488 | 754 | 13.0398 | 2568 | 0.0016854 | 0.084272 | 2522 | 0.98 | 736
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 7611 | FALSE | 7068.0362 | 7068.0362 | 4.3928 | 42 | 8.74e-05 | 2001 | 37.9943 | 2291 | 0.0016834 | 0.070701 | 2523 | 0.49 | 896
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 33050 | FALSE | 6143.4432 | 1793.1664 | 1.1145 | 56 | 0.000194 | 425 | 9.4021 | 2637 | 0.0016799 | 0.094072 | 2524 | 2.96 | 571
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 39424 | FALSE | 3992.9225 | 1481.6598 | 0.92086 | 36 | 9.8e-05 | 1690 | 17.4915 | 2491 | 0.0016754 | 0.060313 | 2525 |  | 3138
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 5082 | FALSE | 33362.418 | 32012.7007 | 19.896 | 215 | 0.00012065 | 1172 | 16.3155 | 2512 | 0.0016672 | 0.35844 | 2526 | 2.33 | 613
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 2768 | FALSE | 12969.9695 | 10109.7249 | 6.2832 | 92 | 7.52e-05 | 2326 | 22.2701 | 2424 | 0.0016647 | 0.15315 | 2527 | 0.05 | 2021
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 85234 | FALSE | 12730.8347 | 12730.8347 | 7.9123 | 92 | 7.74e-05 | 2279 | 30.0376 | 2343 | 0.0016524 | 0.15202 | 2528 | 0.02 | 2526
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 230272 | FALSE | 1833.3676 | 1377.39 | 0.85605 | 18 | 5.04e-05 | 3031 | 15.9138 | 2516 | 0.0016485 | 0.029673 | 2529 |  | 2836
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 557468 | FALSE | 3768.3144 | 1423.6732 | 0.88482 | 28 | 0.0001751 | 528 | 10.813 | 2614 | 0.0016475 | 0.046129 | 2530 |  | 3042
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 1300 | FALSE | 9816.2612 | 5145.088 | 3.1977 | 84 | 0.00010467 | 1538 | 15.4386 | 2525 | 0.0016445 | 0.13814 | 2531 | 0.08 | 1580
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | CB | FALSE | 1947.472 | 1251.1033 | 0.77757 | 19 | 5.35e-05 | 2951 | 32.6064 | 2325 | 0.0016436 | 0.031229 | 2532 | 0.03 | 2359
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 218894 | TRUE | 1856.9722 | 540.1994 | 0.33574 | 14 | 6.94e-05 | 2494 | 15.8967 | 2518 | 0.00163 | 0.022819 | 2533 |  | 2758
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 440 | FALSE | 19525.153 | 3309.7658 | 2.057 | 158 | 8.5e-05 | 2062 | 3.5276 | 2792 | 0.00044177 | 0.0698 | 2753 | 0.17 | 1237
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | D4982 | FALSE | 4312.861 | 4312.861 | 2.6805 | 21 | 3.06e-05 | 3421 | 38.5371 | 2287 | 0.0016248 | 0.034121 | 2535 | 33.37 | 222
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 2038 | FALSE | 21510.9233 | 21510.9233 | 13.3691 | 155 | 0.00018693 | 462 | 18.4659 | 2468 | 0.0016155 | 0.2504 | 2536 | 0.06 | 1908
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 2268 | FALSE | 35117.3516 | 35117.3516 | 21.8256 | 217 | 8.42e-05 | 2087 | 23.7294 | 2408 | 0.0016039 | 0.34805 | 2537 | 69.93 | 69
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 52664 | TRUE | 5174.4008 | 284.4033 | 0.17676 | 44 | 5.82e-05 | 2829 | 25.8938 | 2380 | 0.0016028 | 0.070524 | 2538 |  | 2705
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10726 | FALSE | 16936.721 | 16936.721 | 10.5262 | 124 | 0.00026294 | 188 | 7.1636 | 2683 | 0.0016007 | 0.19849 | 2539 | 15.77 | 346
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 1331 | FALSE | 7064.7733 | 7064.7733 | 4.3908 | 63 | 0.00010598 | 1495 | 12.1416 | 2583 | 0.0015977 | 0.10065 | 2540 | 46.2 | 144
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | P166 | FALSE | 7343.1285 | 7068.5222 | 4.3931 | 27 | 0.00014292 | 827 | 10.6287 | 2617 | 0.0015975 | 0.043133 | 2541 | 0.97 | 738
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 36516 | FALSE | 6699.7019 | 6699.7019 | 4.1639 | 53 | 0.00037131 | 77 | 6.3459 | 2704 | 0.0015908 | 0.08431 | 2542 | 29.13 | 244
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 5304 | FALSE | 8039.9737 | 5763.285 | 3.5819 | 60 | 9.19e-05 | 1848 | 18.674 | 2464 | 0.0015784 | 0.094707 | 2543 | 0.05 | 1963
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 685852 | TRUE | 222.9305 | 104.9331 | 0.065216 | 3 | 0.00011257 | 1352 | 15.9116 | 2517 | 0.0015648 | 0.0046945 | 2544 |  | 3611
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | CB | TRUE | 16165.5618 | 153.7468 | 0.095554 | 111 | 7.02e-05 | 2463 | 11.081 | 2607 | 0.0015644 | 0.17365 | 2545 | 0.1 | 1466
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 60050 | FALSE | 13116.246 | 13116.246 | 8.1518 | 98 | 0.00010761 | 1461 | 16.5517 | 2508 | 0.0015546 | 0.15235 | 2546 | 0.1 | 1480
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 391312 | TRUE | 1866.0468 | 229.6394 | 0.14272 | 13 | 5.89e-05 | 2810 | 14.6684 | 2538 | 0.0015528 | 0.020186 | 2547 |  | 3544
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 322 | FALSE | 11857.5634 | 11550.5948 | 7.1787 | 88 | 0.0001706 | 560 | 11.411 | 2599 | 0.0015474 | 0.13618 | 2548 | 1.05 | 721
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 950688 | FALSE | 5883.5054 | 5883.5054 | 3.6566 | 50 | 0.00010781 | 1454 | 17.1924 | 2501 | 0.0015407 | 0.077034 | 2549 |  | 2854
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 9240 | FALSE | 17656.496 | 17656.496 | 10.9736 | 151 | 8.94e-05 | 1936 | 23.8246 | 2406 | 0.0015394 | 0.23246 | 2550 | 0.09 | 1524
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 80982 | TRUE | 836.5231 | 836.5231 | 0.5199 | 8 | 7.45e-05 | 2347 | 11.9509 | 2588 | 0.0015382 | 0.012305 | 2551 | 41.95 | 172
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 5144 | FALSE | 6368.9288 | 6368.9288 | 3.9583 | 36 | 0.00020138 | 392 | 8.6508 | 2650 | 0.0015295 | 0.055061 | 2552 | 32.7 | 225
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 3019 | TRUE | 1511.5981 | 426.9368 | 0.26534 | 11 | 7.3e-05 | 2394 | 21.6652 | 2431 | 0.0015165 | 0.016682 | 2553 |  | 2928
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 173590 | FALSE | 6901.197 | 6901.197 | 4.2891 | 46 | 9.09e-05 | 1887 | 19.2098 | 2458 | 0.0015131 | 0.069603 | 2554 |  | 2921
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | CB | FALSE | 4176.9151 | 1037.2766 | 0.64467 | 36 | 0.00021226 | 350 | 8.6501 | 2651 | 0.0015072 | 0.054259 | 2555 | 0.03 | 2345
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 534 | FALSE | 27841.2407 | 25519.0889 | 15.8602 | 162 | 9.69e-05 | 1715 | 161.0686 | 1743 | 0.01369 | 2.2178 | 1827 | 36.61 | 206
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | CB | FALSE | 7703.9355 | 4253.8822 | 2.6438 | 61 | 0.00011905 | 1206 | 11.75 | 2592 | 0.0014996 | 0.091479 | 2557 | 1.94 | 628
1710 | ELK 110191336 | 42981101 | ELK 1101 | 91336 | FALSE | 13315.5222 | 12740.7114 | 7.9184 | 78 | 8.28e-05 | 2135 | 14.0784 | 2546 | 0.0014969 | 0.11676 | 2558 | 0.04 | 2153
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 969182 | FALSE | 8578.2654 | 8578.2654 | 5.3314 | 64 | 0.00023272 | 274 | 7.8723 | 2672 | 0.0014937 | 0.095599 | 2559 |  | 2685
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 950 | FALSE | 11853.1557 | 9978.6098 | 6.2017 | 85 | 0.00011166 | 1376 | 9.5946 | 2629 | 0.0014937 | 0.12697 | 2560 | 0.09 | 1575
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | CB | FALSE | 17569.8608 | 1899.4744 | 1.1805 | 140 | 3.36e-05 | 3373 | 17.212 | 2499 | 0.0014894 | 0.20851 | 2561 | 0.55 | 873
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 304 | TRUE | 3131.1603 | 221.043 | 0.13738 | 27 | 7.23e-05 | 2410 | 12.9614 | 2570 | 0.0014797 | 0.039953 | 2562 | 0.03 | 2304
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 4796 | FALSE | 11571.4706 | 11571.4706 | 7.1917 | 114 | 8.33e-05 | 2126 | 15.4981 | 2524 | 0.0014707 | 0.16766 | 2563 | 50.63 | 117
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 3002 | FALSE | 13206.8342 | 11656.2739 | 7.2444 | 76 | 8.53e-05 | 2046 | 10.9995 | 2610 | 0.001464 | 0.11126 | 2564 | 0.15 | 1296
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 201156 | FALSE | 2780.2158 | 2335.0863 | 1.4513 | 26 | 0.000132 | 983 | 11.0364 | 2609 | 0.0014632 | 0.038044 | 2565 |  | 2996
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 315500 | FALSE | 5515.195 | 1783.0288 | 1.1082 | 22 | 2.11e-05 | 3532 | 19.9522 | 2450 | 0.0014578 | 0.032073 | 2566 |  | 3335
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 39156 | FALSE | 7678.6279 | 5580.9258 | 3.4686 | 62 | 0.00036657 | 79 | 5.0499 | 2749 | 0.0014467 | 0.089693 | 2567 | 0.4 | 949
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 533648 | FALSE | 10867.8258 | 10867.8258 | 6.7544 | 93 | 0.00016205 | 621 | 8.4995 | 2655 | 0.0014323 | 0.13321 | 2568 | 0.11 | 1415
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 668674 | FALSE | 15298.6549 | 15298.6549 | 9.5082 | 112 | 0.00024869 | 220 | 8.5559 | 2654 | 0.0014289 | 0.16003 | 2569 |  | 2801
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 12590 | FALSE | 8818.0631 | 8233.9726 | 5.1174 | 69 | 0.00032896 | 102 | 7.9903 | 2671 | 0.0014267 | 0.09844 | 2570 | 0.34 | 980
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 45261 | TRUE | 20192.7526 | 164.9958 | 0.10255 | 10 | 7.39e-05 | 2362 | 8.6022 | 2652 | 0.001423 | 0.01423 | 2571 |  | 3326
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1313 | FALSE | 1996.4298 | 1996.4298 | 1.2408 | 19 | 0.00014421 | 810 | 12.5764 | 2576 | 0.0014057 | 0.026709 | 2572 | 44.58 | 156
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 75972 | FALSE | 7223.394 | 5386.1403 | 3.3475 | 61 | 6.5e-05 | 2609 | 22.3 | 2423 | 0.0013938 | 0.085021 | 2573 | 0.52 | 885
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 8982 | FALSE | 7434.3823 | 7434.3823 | 4.6205 | 50 | 0.00014907 | 751 | 11.9525 | 2587 | 0.0013928 | 0.06964 | 2574 | 0.08 | 1625
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 39154 | FALSE | 1419.8889 | 1419.8889 | 0.88247 | 11 | 0.00019824 | 403 | 21.6746 | 2430 | 0.0013923 | 0.015315 | 2575 | 62.39 | 84
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | CB | FALSE | 6227.6638 | 6227.6638 | 3.8705 | 47 | 0.00010177 | 1608 | 5.1216 | 2747 | 0.0013913 | 0.065391 | 2576 | 0.03 | 2337
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1765 | FALSE | 2336.7952 | 2336.7952 | 1.4523 | 20 | 0.00017078 | 558 | 6.0123 | 2713 | 0.0013887 | 0.027774 | 2577 | 15.71 | 348
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 36596 | FALSE | 20043.7619 | 6572.3951 | 4.0848 | 145 | 1.72e-05 | 3570 | 17.052 | 2503 | 0.0013847 | 0.20079 | 2578 | 0.03 | 2397
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 5000 | FALSE | 3149.0186 | 3149.0186 | 1.9571 | 23 | 0.00041733 | 64 | 2.1336 | 2834 | 0.0013814 | 0.031772 | 2579 | 24.55 | 277
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | CB | TRUE | 244.7023 | 7.571 | 0.0047054 | 6 | 8.87e-05 | 1962 | 31.698 | 2332 | 0.001321 | 0.0079259 | 2580 |  | 3593
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 1316 | FALSE | 22645.6685 | 22101.0688 | 13.7359 | 166 | 7.8e-05 | 2260 | 13.3542 | 2565 | 0.0013124 | 0.21786 | 2581 | 0.12 | 1400
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 35562 | FALSE | 22914.0776 | 22914.0776 | 14.2412 | 147 | 0.00010505 | 1525 | 11.7038 | 2593 | 0.0013006 | 0.19119 | 2582 | 0.16 | 1270
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 1318 | FALSE | 16637.0017 | 13693.4076 | 8.5105 | 113 | 0.00013033 | 1004 | 8.2659 | 2664 | 0.0012974 | 0.14661 | 2583 | 9.77 | 404
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | L491 | FALSE | 3564.5514 | 3564.5514 | 2.2154 | 31 | 0.00010065 | 1632 | 5.4343 | 2732 | 0.0012903 | 0.039999 | 2584 | 33.77 | 219
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | XR244 | TRUE | 22757.8317 | 0 | 0 | 157 | 6.38e-05 | 2654 | 15.2591 | 2527 | 0.0012825 | 0.20135 | 2585 | 0.59 | 855
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | CB | TRUE | 3592.4976 | 971.3906 | 0.60372 | 31 | 0.0002505 | 215 | 3.3852 | 2798 | 0.0012726 | 0.039451 | 2586 | 0.05 | 1979
842 | ELK 11011272 | 42981101 | ELK 1101 | 1272 | FALSE | 36077.8728 | 35548.517 | 22.0935 | 236 | 0.00010152 | 1616 | 17.6496 | 2487 | 0.0012681 | 0.29926 | 2587 | 0.25 | 1089
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | CB | FALSE | 9891.2145 | 4885.2685 | 3.0362 | 66 | 2.82e-05 | 3454 | 23.8416 | 2402 | 0.0012656 | 0.083532 | 2588 | 0.03 | 2371
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 12256 | FALSE | 10425.1159 | 10425.1159 | 6.4793 | 86 | 9.85e-05 | 1679 | 19.6956 | 2453 | 0.0012622 | 0.10855 | 2589 | 60.88 | 87
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | W34 | FALSE | 15456.5208 | 12223.0154 | 7.5967 | 112 | 3.83e-05 | 3294 | 31.2471 | 2337 | 0.0012584 | 0.14094 | 2590 |  | 2657
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 903238 | FALSE | 9893.8007 | 6450.8713 | 4.0092 | 30 | 4.73e-05 | 3108 | 30.0306 | 2344 | 0.001258 | 0.037741 | 2591 |  | 3186
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 725292 | TRUE | 1519.9145 | 339.5862 | 0.21105 | 13 | 8.63e-05 | 2027 | 0.065451 | 3395 | 5.66e-06 | 7.3554e-05 | 3231 |  | 2665
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 81514 | FALSE | 7697.8392 | 4781.286 | 2.9716 | 65 | 8.7e-05 | 2011 | 13.7396 | 2556 | 0.0012525 | 0.08141 | 2593 | 0.04 | 2121
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 2204 | FALSE | 11625.6324 | 11625.6324 | 7.2254 | 84 | 9.46e-05 | 1775 | 11.1006 | 2606 | 0.0012429 | 0.1044 | 2594 | 40.14 | 185
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 11046 | FALSE | 25866.5621 | 25866.5621 | 16.0762 | 194 | 0.00016384 | 601 | 6.3121 | 2705 | 0.0012326 | 0.23912 | 2595 | 1.33 | 683
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 8522 | FALSE | 15153.8377 | 3071.2008 | 1.9088 | 123 | 0.0001684 | 573 | 8.4903 | 2656 | 0.0012059 | 0.14833 | 2596 | 0.11 | 1425
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 959032 | FALSE | 1582.9544 | 1283.5288 | 0.79772 | 11 | 0.00012885 | 1030 | 15.1847 | 2528 | 0.0012034 | 0.013238 | 2597 |  | 3517
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 835658 | TRUE | 1187.2489 | 50.0391 | 0.0311 | 11 | 7.66e-05 | 2292 | 17.3633 | 2494 | 0.0018987 | 0.020885 | 2490 |  | 3337
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 2764 | FALSE | 9871.3778 | 9871.3778 | 6.1351 | 68 | 0.0002671 | 178 | 5.6584 | 2724 | 0.0011906 | 0.080958 | 2599 | 0.05 | 2046
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1943 | FALSE | 1959.963 | 1959.963 | 1.2181 | 17 | 0.00014604 | 788 | 5.6591 | 2723 | 0.0011872 | 0.020183 | 2600 |  | 3220
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 641544 | FALSE | 7956.2573 | 7956.2573 | 4.9448 | 58 | 0.00010868 | 1431 | 9.0793 | 2642 | 0.0011816 | 0.068531 | 2601 |  | 2763
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 64565 | FALSE | 1284.2848 | 1284.2848 | 0.79819 | 13 | 0.00016067 | 634 | 14.7117 | 2534 | 0.001175 | 0.015275 | 2602 | 0.3 | 1013
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | CB | TRUE | 26742.8753 | 940.9991 | 0.58483 | 226 | 4.1e-05 | 3242 | 20.6872 | 2439 | 0.0011724 | 0.26497 | 2603 |  | 2752
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 9500 | FALSE | 10910.9002 | 9168.0738 | 5.698 | 71 | 6.67e-05 | 2565 | 18.8342 | 2462 | 0.0011663 | 0.082807 | 2604 | 1.62 | 662
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 836528 | FALSE | 4695.3621 | 4679.584 | 2.9084 | 39 | 3.02e-05 | 3424 | 39.6633 | 2275 | 0.0011552 | 0.045051 | 2605 |  | 2820
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | CB | FALSE | 25409.8546 | 24616.6476 | 15.2993 | 192 | 0.00012212 | 1146 | 9.4762 | 2636 | 0.0011504 | 0.22088 | 2606 | 0.14 | 1327
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | CB | TRUE | 3504.1175 | 755.1177 | 0.46931 | 25 | 5.93e-05 | 2797 | 9.8829 | 2625 | 0.001149 | 0.028724 | 2607 |  | 2717
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 704542 | TRUE | 487.4963 | 345.9417 | 0.215 | 3 | 0.00010371 | 1556 | 10.6423 | 2616 | 0.0011475 | 0.0034424 | 2608 |  | 3612
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 624200 | FALSE | 3744.0071 | 2491.858 | 1.5487 | 6 | 9.13e-06 | 3614 | 78.1632 | 2058 | 0.0011432 | 0.0068593 | 2609 |  | 3383
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | L5381 | FALSE | 1955.4877 | 1955.4877 | 1.2153 | 15 | 8.62e-05 | 2029 | 11.1601 | 2603 | 0.0011429 | 0.017144 | 2610 | 63.74 | 80
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 218424 | TRUE | 877.6167 | 866.5125 | 0.53854 | 4 | 6.94e-05 | 2493 | 17.8902 | 2485 | 0.0011372 | 0.0045488 | 2611 |  | 3498
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 55402 | FALSE | 14989.6887 | 3994.4825 | 2.4826 | 104 | 6.46e-05 | 2623 | 16.7266 | 2505 | 0.0011234 | 0.11683 | 2612 | 0.02 | 2517
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 503000 | FALSE | 7554.2208 | 7373.131 | 4.5824 | 54 | 0.00017004 | 564 | 3.5877 | 2787 | 0.0011185 | 0.060401 | 2613 |  | 2789
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 240 | FALSE | 4953.3762 | 4953.3762 | 3.0785 | 42 | 0.00020071 | 393 | 8.5626 | 2653 | 0.0011134 | 0.046762 | 2614 | 27.15 | 261
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 10930 | FALSE | 18316.5864 | 1585.2477 | 0.98524 | 149 | 9.21e-05 | 1841 | 11.2167 | 2602 | 0.0011126 | 0.16578 | 2615 | 0.03 | 2315
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 1139 | FALSE | 3291.1128 | 3291.1128 | 2.0454 | 25 | 0.00021661 | 335 | 5.771 | 2718 | 0.0011071 | 0.027677 | 2616 | 19.12 | 313
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 1480 | FALSE | 3913.3341 | 3463.9371 | 2.1529 | 20 | 6.9e-05 | 2506 | 14.3241 | 2543 | 0.0011038 | 0.022077 | 2617 | 0.02 | 2410
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 75622 | FALSE | 9209.8908 | 1956.9061 | 1.2162 | 78 | 8.93e-05 | 1938 | 14.1186 | 2545 | 0.0010989 | 0.085711 | 2618 | 1.24 | 694
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | CB | FALSE | 17419.9506 | 9244.2642 | 5.7453 | 121 | 8.28e-05 | 2137 | 22.4988 | 2417 | 0.001078 | 0.13044 | 2619 | 36.92 | 204
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 97924 | FALSE | 8287.4089 | 8287.4089 | 5.1507 | 49 | 8.42e-05 | 2084 | 16.5614 | 2507 | 0.0010653 | 0.052198 | 2620 | 28.19 | 252
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 842642 | FALSE | 9353.842 | 9353.842 | 5.8135 | 80 | 0.00015044 | 731 | 10.167 | 2622 | 0.0010503 | 0.084021 | 2621 | 0.11 | 1445
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | CB | FALSE | 8798.7393 | 5676.9517 | 3.5282 | 72 | 0.00028651 | 144 | 7.3277 | 2682 | 0.0010502 | 0.075616 | 2622 | 5.26 | 492
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | S1547 | FALSE | 4459.8848 | 4459.8848 | 2.7718 | 39 | 5.31e-05 | 2964 | 14.6954 | 2536 | 0.0010487 | 0.040901 | 2623 | 82.41 | 44
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 1277 | TRUE | 3471.3767 | 0 | 0 | 30 | 4.02e-05 | 3263 | 12.7259 | 2574 | 0.001018 | 0.030539 | 2624 | 0.04 | 2212
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 7290 | FALSE | 1075.4071 | 1075.4071 | 0.66837 | 8 | 2.83e-05 | 3452 | 23.8308 | 2405 | 0.0010126 | 0.0081011 | 2625 | 0 | 2635
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 644462 | TRUE | 2486.8085 | 567.6161 | 0.35278 | 24 | 0.00010098 | 1625 | 12.9287 | 2571 | 0.0010124 | 0.024298 | 2626 |  | 3468
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | LC12 | FALSE | 12044.6481 | 12044.6481 | 7.4858 | 86 | 0.00017659 | 521 | 13.8877 | 2554 | 0.0010097 | 0.086838 | 2627 | 0.56 | 865
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 498932 | FALSE | 6861.4641 | 6024.2456 | 3.7441 | 57 | 0.00014672 | 777 | 8.6826 | 2649 | 0.0010076 | 0.057431 | 2628 | 0.09 | 1548
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 5731 | FALSE | 5029.6194 | 5029.6194 | 3.1259 | 41 | 0.00015547 | 690 | 3.5444 | 2790 | 0.0010067 | 0.041274 | 2629 | 0.05 | 1973
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | CB | FALSE | 28734.8817 | 28123.7558 | 17.479 | 148 | 7.11e-05 | 2442 | 13.9274 | 2552 | 0.0010065 | 0.14896 | 2630 | 0.36 | 966
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | CB | FALSE | 10346.1129 | 2141.3708 | 1.3309 | 82 | 8.17e-05 | 2163 | 6.4364 | 2698 | 0.0010058 | 0.082476 | 2631 | 0.06 | 1846
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 87222 | FALSE | 8479.914 | 8240.0573 | 5.1212 | 57 | 0.00010497 | 1529 | 10.4869 | 2620 | 0.0010031 | 0.057176 | 2632 | 0.1 | 1504
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | CB | FALSE | 14092.576 | 11980.8022 | 7.4461 | 86 | 0.00012586 | 1080 | 5.5912 | 2727 | 0.0010024 | 0.086208 | 2633 | 0.22 | 1132
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 509068 | FALSE | 2868.1374 | 1655.4712 | 1.0289 | 22 | 0.00010648 | 1487 | 17.3491 | 2495 | 0.0010019 | 0.022042 | 2634 |  | 3297
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 975388 | TRUE | 2101.0589 | 775.2264 | 0.48181 | 18 | 4.01e-05 | 3265 | 13.2566 | 2567 | 0.0010016 | 0.018029 | 2635 |  | 3242
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 5394 | FALSE | 24529.1372 | 23340.3938 | 14.5061 | 180 | 0.00013064 | 998 | 7.7218 | 2674 | 0.00099214 | 0.17859 | 2636 | 43.45 | 169
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 887180 | FALSE | 8692.4371 | 8589.4892 | 5.3384 | 61 | 5.57e-05 | 2897 | 12.9178 | 2572 | 0.00098628 | 0.060163 | 2637 | 0.07 | 1715
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 4698 | FALSE | 12883.0061 | 12883.0061 | 8.0068 | 101 | 0.00018389 | 481 | 12.0639 | 2584 | 0.00097756 | 0.098734 | 2638 | 0.05 | 1998
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | L7283 | FALSE | 1053.4945 | 1053.4945 | 0.65475 | 12 | 7.51e-05 | 2329 | 13.9335 | 2551 | 0.00097446 | 0.011693 | 2639 | 29.37 | 241
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 51732 | FALSE | 12971.5884 | 1093.5921 | 0.67967 | 110 | 0.00019845 | 402 | 3.0886 | 2809 | 0.00097323 | 0.10706 | 2640 | 0.02 | 2495
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 96738 | FALSE | 10792.8538 | 10792.8538 | 6.7078 | 84 | 0.00020283 | 387 | 5.4435 | 2731 | 0.00097276 | 0.081712 | 2641 | 21.67 | 298
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 692576 | FALSE | 5517.9962 | 3874.9491 | 2.4083 | 51 | 0.0001303 | 1007 | 7.0569 | 2686 | 0.0009691 | 0.049424 | 2642 |  | 2983
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 8848 | FALSE | 16215.0785 | 6200.2521 | 3.8535 | 117 | 6.7e-05 | 2558 | 11.0461 | 2608 | 0.00096385 | 0.11277 | 2643 | 0.22 | 1123
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 50396 | FALSE | 21037.3757 | 20827.3893 | 12.9443 | 162 | 8.52e-05 | 2050 | 11.5065 | 2597 | 0.00096084 | 0.15566 | 2644 | 20.38 | 306
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 114 | TRUE | 4957.8887 | 17.4908 | 0.010871 | 40 | 8.32e-05 | 2128 | 9.1847 | 2640 | 0.00096055 | 0.038422 | 2645 | 8.42 | 426
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 60116 | FALSE | 19634.1928 | 19634.1928 | 12.2027 | 151 | 0.00020011 | 397 | 4.9468 | 2757 | 0.00095505 | 0.14421 | 2646 | 0.89 | 751
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1703 | FALSE | 2213.9946 | 2213.9946 | 1.376 | 16 | 0.00013016 | 1008 | 6.0137 | 2712 | 0.00095446 | 0.015271 | 2647 | 43.57 | 165
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | CB | FALSE | 21117.9549 | 15035.2163 | 9.3444 | 130 | 6.82e-05 | 2531 | 7.7386 | 2673 | 0.00094726 | 0.12314 | 2648 | 0.52 | 887
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 217974 | FALSE | 6862.6922 | 6593.0651 | 4.0976 | 44 | 0.00013259 | 971 | 7.0882 | 2685 | 0.00093976 | 0.04135 | 2649 |  | 2978
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | A32 | FALSE | 9519.6113 | 2633.3805 | 1.6367 | 76 | 6.26e-05 | 2697 | 14.4505 | 2541 | 0.00093807 | 0.071294 | 2650 | 0.03 | 2314
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 1850 | FALSE | 21661.1812 | 21661.1812 | 13.4625 | 182 | 0.00013942 | 879 | 5.1605 | 2745 | 0.00093342 | 0.16988 | 2651 | 73.2 | 62
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4218 | FALSE | 7931.9123 | 7690.241 | 4.7795 | 27 | 0.00022706 | 297 | 5.3463 | 2735 | 0.00093079 | 0.025131 | 2652 | 0.09 | 1526
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 76752 | FALSE | 4380.3192 | 4380.3192 | 2.7224 | 36 | 0.00025263 | 209 | 5.3491 | 2733 | 0.00091318 | 0.032874 | 2653 | 0.44 | 924
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 1030 | FALSE | 25567.0003 | 25567.0003 | 15.89 | 217 | 0.00014916 | 749 | 5.1044 | 2748 | 0.00090995 | 0.19746 | 2654 | 21.6 | 300
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1808 | FALSE | 2949.8139 | 2949.8139 | 1.8333 | 27 | 9.03e-05 | 1905 | 7.9905 | 2670 | 0.00090929 | 0.024551 | 2655 | 46.07 | 145
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 36720 | FALSE | 12840.8619 | 9577.7665 | 5.9526 | 87 | 5.29e-05 | 2972 | 18.0958 | 2475 | 0.00089535 | 0.077895 | 2656 | 0.12 | 1394
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | MR366 | TRUE | 15876.8969 | 0 | 0 | 134 | 1.49e-05 | 3586 | 46.6158 | 2237 | 0.00088159 | 0.11813 | 2657 |  | 2698
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | CB | FALSE | 23033.3792 | 23033.3792 | 14.3153 | 170 | 0.00010514 | 1519 | 8.871 | 2646 | 0.0008744 | 0.14865 | 2658 | 0.65 | 822
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 3142 | FALSE | 28901.7283 | 28901.7283 | 17.9625 | 256 | 8.75e-05 | 1999 | 11.3039 | 2600 | 0.00086175 | 0.22061 | 2659 | 128.2 | 8
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | CB | FALSE | 12456.8292 | 3768.052 | 2.3419 | 111 | 9.7e-05 | 1713 | 9.3336 | 2638 | 0.00085884 | 0.095332 | 2660 | 0.34 | 979
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | L3151 | FALSE | 1595.4085 | 1595.4085 | 0.99155 | 13 | 0.0001267 | 1068 | 7.3809 | 2679 | 0.00085242 | 0.011082 | 2661 | 25 | 273
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 12838 | FALSE | 3807.4911 | 3807.4911 | 2.3664 | 32 | 0.00058408 | 21 | 1.5522 | 2860 | 0.00085046 | 0.027215 | 2662 | 8.72 | 421
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 403102 | TRUE | 2765.6183 | 788.5735 | 0.4901 | 18 | 0.00014171 | 843 | 5.3389 | 2736 | 0.00084561 | 0.015221 | 2663 |  | 3267
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 2010 | FALSE | 6409.6213 | 6409.6213 | 3.9836 | 43 | 8.86e-05 | 1970 | 8.3553 | 2660 | 0.00084365 | 0.036277 | 2664 | 0.11 | 1409
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 4446 | TRUE | 17302.7635 | 0 | 0 | 124 | 4.93e-05 | 3056 | 12.6776 | 2575 | 0.00084052 | 0.10422 | 2665 | 0.04 | 2135
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 669542 | FALSE | 5668.7589 | 5668.7589 | 3.5232 | 49 | 0.00018473 | 476 | 4.4449 | 2769 | 0.0008334 | 0.040836 | 2666 |  | 2960
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 90120 | FALSE | 8309.1292 | 5041.5999 | 3.1334 | 64 | 0.00010439 | 1542 | 5.6342 | 2725 | 0.00082387 | 0.052727 | 2667 | 0.04 | 2200
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 7948F | FALSE | 13813.6905 | 1712.0139 | 1.064 | 74 | 2.71e-05 | 3472 | 53.0836 | 2194 | 0.00082174 | 0.060809 | 2668 | 0.02 | 2432
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | CB | FALSE | 19644.2096 | 2188.9817 | 1.3605 | 180 | 4.39e-05 | 3192 | 3.8934 | 2779 | 0.0008192 | 0.14746 | 2669 | 0.05 | 1928
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 6028 | FALSE | 13370.3026 | 13370.3026 | 8.3097 | 115 | 0.00011502 | 1298 | 6.888 | 2688 | 0.0008147 | 0.09369 | 2670 | 56.37 | 98
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 432 | FALSE | 18069.9686 | 1802.3639 | 1.1202 | 130 | 5.45e-05 | 2933 | 13.5928 | 2560 | 0.00080536 | 0.1047 | 2671 | 0.03 | 2402
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 10720 | FALSE | 7675.033 | 7675.033 | 4.7701 | 25 | 2.22e-05 | 3517 | 32.3965 | 2326 | 0.00079115 | 0.019779 | 2672 | 23.43 | 287
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | CB | FALSE | 3388.6184 | 3388.6184 | 2.106 | 21 | 6.39e-05 | 2651 | 12.5128 | 2578 | 0.0007907 | 0.016605 | 2673 | 0.04 | 2209
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 76468 | FALSE | 4744.0085 | 1281.0776 | 0.79619 | 35 | 9.82e-05 | 1686 | 6.3972 | 2700 | 0.00078905 | 0.027617 | 2674 | 0.03 | 2373
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | CB | FALSE | 4816.3453 | 4816.3453 | 2.9934 | 40 | 0.00013401 | 943 | 11.9588 | 2585 | 0.0007688 | 0.030752 | 2675 | 31.2 | 232
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | CB | FALSE | 11748.8949 | 6728.9489 | 4.1821 | 92 | 9.29e-05 | 1826 | 6.3592 | 2703 | 0.00076238 | 0.070139 | 2676 | 0.16 | 1251
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | CB | FALSE | 19605.5563 | 19605.5563 | 12.1849 | 151 | 0.00013907 | 885 | 11.5584 | 2596 | 0.00075189 | 0.11354 | 2677 | 0.07 | 1772
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 38218 | FALSE | 17605.0564 | 17605.0564 | 10.9416 | 132 | 9.9e-05 | 1668 | 8.1704 | 2665 | 0.00074696 | 0.098599 | 2678 | 94.05 | 28
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 5090 | FALSE | 34218.6566 | 34218.6566 | 21.267 | 245 | 0.00010692 | 1476 | 6.8561 | 2689 | 0.00074249 | 0.18191 | 2679 | 1.26 | 691
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 824 | TRUE | 12575.4803 | 137.5107 | 0.085463 | 103 | 0.00010133 | 1619 | 3.4457 | 2797 | 0.00072721 | 0.074902 | 2680 |  | 2674
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 9280 | FALSE | 10262.6071 | 10262.6071 | 6.3783 | 80 | 8.39e-05 | 2098 | 8.09 | 2668 | 0.00072124 | 0.057699 | 2681 | 2.82 | 577
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 11056 | FALSE | 6785.5939 | 6717.0632 | 4.1747 | 48 | 0.00016442 | 592 | 4.026 | 2778 | 0.00071991 | 0.034556 | 2682 | 0.3 | 1011
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 530 | TRUE | 43254.3781 | 117.5277 | 0.073044 | 255 | 0.00014869 | 756 | 5.1756 | 2744 | 0.00070447 | 0.17964 | 2683 | 0.02 | 2508
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 1818 | FALSE | 5027.483 | 4942.4923 | 3.0718 | 26 | 4.1e-05 | 3243 | 14.3865 | 2542 | 0.00069935 | 0.018183 | 2684 | 0.72 | 799
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 2796 | FALSE | 31981.5846 | 31981.5846 | 19.8767 | 253 | 0.00012583 | 1081 | 6.8299 | 2691 | 0.00069507 | 0.17585 | 2685 | 44.5 | 159
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 10442 | FALSE | 16579.0287 | 9105.2092 | 5.6589 | 133 | 0.00016483 | 589 | 3.6401 | 2786 | 0.00069444 | 0.092361 | 2686 | 0.29 | 1027
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | CB | FALSE | 5806.4035 | 3043.2971 | 1.8914 | 48 | 0.00014993 | 737 | 3.6937 | 2784 | 0.00069407 | 0.033315 | 2687 | 0.04 | 2177
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 237791 | FALSE | 3420.2949 | 2280.4467 | 1.4173 | 23 | 0.0001987 | 399 | 3.165 | 2804 | 0.00069283 | 0.015935 | 2688 |  | 3489
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 285704 | FALSE | 1923.7717 | 1685.8276 | 1.0477 | 17 | 0.00023237 | 275 | 9.8522 | 2626 | 0.00068515 | 0.011648 | 2689 |  | 3385
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 10600 | FALSE | 21367.0688 | 21367.0688 | 13.2797 | 161 | 7.37e-05 | 2371 | 8.335 | 2662 | 0.000683 | 0.10996 | 2690 | 276.94 | 1
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 428102 | FALSE | 20879.8446 | 19729.9421 | 12.2622 | 158 | 0.0001278 | 1053 | 4.9782 | 2755 | 0.00068264 | 0.10786 | 2691 | 0.55 | 866
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 480430 | FALSE | 8153.37 | 1450.1348 | 0.90126 | 39 | 5.74e-05 | 2851 | 18.7653 | 2463 | 0.00068138 | 0.026574 | 2692 |  | 3372
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 662 | FALSE | 13657.9642 | 10019.7655 | 6.2273 | 104 | 6.06e-05 | 2758 | 8.9744 | 2644 | 0.00067921 | 0.070638 | 2693 | 0.07 | 1724
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 54728 | FALSE | 7898.4984 | 1667.872 | 1.0366 | 37 | 3.38e-05 | 3371 | 43.321 | 2256 | 0.00066262 | 0.024517 | 2694 | 0.79 | 775
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 7347 | FALSE | 1315.3758 | 1315.3758 | 0.81751 | 10 | 0.00013644 | 913 | 4.8202 | 2760 | 0.00065864 | 0.0065864 | 2695 | 43.48 | 167
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 13026 | FALSE | 12912.9615 | 12912.9615 | 8.0255 | 70 | 4.92e-05 | 3058 | 11.6076 | 2595 | 0.00065269 | 0.045688 | 2696 | 8.38 | 429
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 320094 | TRUE | 1539.8883 | 440.0576 | 0.2735 | 11 | 3.46e-05 | 3360 | 25.2958 | 2389 | 0.00064788 | 0.0071266 | 2697 |  | 2907
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 15401 | FALSE | 1388.1732 | 1388.1732 | 0.86276 | 11 | 0.00019479 | 418 | 6.5489 | 2694 | 0.00064146 | 0.0070561 | 2698 | 41.15 | 179
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 256 | FALSE | 2415.6319 | 2415.6319 | 1.5013 | 17 | 0.0002397 | 247 | 1.4646 | 2867 | 0.00063627 | 0.010817 | 2699 | 24.25 | 279
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 758594 | FALSE | 3264.6914 | 1943.4938 | 1.2079 | 21 | 0.00012955 | 1018 | 6.1576 | 2711 | 0.00062774 | 0.013182 | 2700 |  | 3075
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 1779 | TRUE | 677.0293 | 540.9099 | 0.33618 | 5 | 6.66e-05 | 2570 | 9.5735 | 2633 | 0.00062625 | 0.0031313 | 2701 |  | 3516
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | A30 | TRUE | 2568.419 | 401.1046 | 0.24929 | 25 | 5.8e-05 | 2834 | 6.399 | 2699 | 0.00062089 | 0.015522 | 2702 | 0.02 | 2500
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 3100 | FALSE | 23694.1727 | 19636.3272 | 12.2041 | 198 | 6.45e-05 | 2625 | 14.9697 | 2532 | 0.00061511 | 0.12179 | 2703 | 0.06 | 1863
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 90334 | FALSE | 5394.0455 | 5394.0455 | 3.3524 | 44 | 3.23e-05 | 3396 | 20.5875 | 2442 | 0.00061497 | 0.027059 | 2704 | 11.09 | 388
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 2194 | FALSE | 4329.2096 | 2142.6429 | 1.3317 | 36 | 0.00018519 | 470 | 3.3664 | 2801 | 0.00060703 | 0.021853 | 2705 | 1.88 | 634
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | XR602 | TRUE | 1368.2778 | 391.3667 | 0.24324 | 13 | 8.42e-05 | 2086 | 9.8269 | 2627 | 0.00060529 | 0.0078688 | 2706 | 0.03 | 2240
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | CB | FALSE | 7588.8389 | 3330.3293 | 2.0698 | 47 | 0.0003055 | 125 | 1.7499 | 2851 | 0.00059825 | 0.028118 | 2707 | 0.99 | 735
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 50142 | FALSE | 6580.4447 | 3596.2025 | 2.2351 | 55 | 0.00011566 | 1280 | 5.2494 | 2740 | 0.00059558 | 0.032757 | 2708 | 2.21 | 618
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | CB | TRUE | 8192.7885 | 792.3448 | 0.49245 | 70 | 0.00016303 | 612 | 5.4892 | 2729 | 0.00059471 | 0.04163 | 2709 | 0.06 | 1815
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 12041 | FALSE | 10143.7851 | 10143.7851 | 6.3044 | 65 | 0.00013198 | 985 | 5.1866 | 2743 | 0.00059297 | 0.038543 | 2710 | 30.78 | 234
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | C558R | FALSE | 23093.6755 | 1942.5032 | 1.2073 | 180 | 4.74e-05 | 3106 | 10.0864 | 2623 | 0.00059158 | 0.10648 | 2711 | 12.02 | 377
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 1804 | FALSE | 13482.9013 | 13482.9013 | 8.3797 | 118 | 0.00010094 | 1626 | 6.3117 | 2706 | 0.00058985 | 0.069602 | 2712 | 106.77 | 17
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 635040 | TRUE | 340.9559 | 324.181 | 0.20148 | 2 | 9.53e-05 | 1752 | 11.9488 | 2590 | 0.0005888 | 0.0011776 | 2713 |  | 3585
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 776806 | TRUE | 1634.4876 | 412.4097 | 0.25631 | 15 | 4.1e-05 | 3244 | 13.7861 | 2555 | 0.00058477 | 0.0087716 | 2714 |  | 3094
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 3611 | FALSE | 2597.3823 | 2597.3823 | 1.6143 | 23 | 5.23e-05 | 2984 | 11.435 | 2598 | 0.00057745 | 0.013281 | 2715 | 32.3 | 226
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | XR250 | TRUE | 9406.4624 | 0 | 0 | 80 | 6.55e-05 | 2601 | 5.0345 | 2750 | 0.00057262 | 0.04581 | 2716 | 4.1 | 527
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | CB | TRUE | 1304.8232 | 357.3361 | 0.22209 | 16 | 7.35e-05 | 2381 | 5.012 | 2752 | 0.00057058 | 0.0091293 | 2717 |  | 3215
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | CB | TRUE | 5451.3154 | 266.9695 | 0.16592 | 50 | 3.14e-05 | 3410 | 8.3028 | 2663 | 0.0005603 | 0.028015 | 2718 | 0.02 | 2459
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 53038 | FALSE | 10729.3555 | 10729.3555 | 6.6683 | 62 | 6.98e-05 | 2481 | 8.8864 | 2645 | 0.00055181 | 0.034212 | 2719 | 0.63 | 833
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 978 | FALSE | 47571.501 | 22458.2021 | 13.9579 | 130 | 3.64e-05 | 3326 | 24.8644 | 2391 | 0.00055148 | 0.071692 | 2720 | 0.07 | 1680
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 908 | FALSE | 3616.7994 | 1126.3756 | 0.70005 | 42 | 6.14e-05 | 2737 | 3.4612 | 2796 | 0.00055062 | 0.023126 | 2721 |  | 3005
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 719490 | FALSE | 4856.6254 | 4856.6254 | 3.0184 | 44 | 6.77e-05 | 2542 | 6.5472 | 2695 | 0.00054847 | 0.024132 | 2722 |  | 2777
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | CB | FALSE | 5887.1186 | 3755.8808 | 2.3343 | 56 | 5.47e-05 | 2926 | 5.5819 | 2728 | 0.00054657 | 0.030608 | 2723 | 0.07 | 1682
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 418480 | FALSE | 1216.9885 | 1216.9885 | 0.75636 | 13 | 0.00010549 | 1506 | 5.5937 | 2726 | 0.0005464 | 0.0071032 | 2724 |  | 3256
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 8894 | FALSE | 18146.6988 | 18102.2842 | 11.2506 | 110 | 0.00011302 | 1343 | 4.8209 | 2759 | 0.00053494 | 0.058844 | 2725 | 5.41 | 487
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2564 | FALSE | 3603.0114 | 3598.4394 | 2.2364 | 21 | 3.97e-05 | 3274 | 12.5176 | 2577 | 0.00053291 | 0.011191 | 2726 | 0.1 | 1482
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | CB | TRUE | 9060.4473 | 490.8425 | 0.30506 | 88 | 4.36e-05 | 3197 | 6.3791 | 2701 | 0.00052635 | 0.046318 | 2727 |  | 2703
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 1276 | FALSE | 6144.8964 | 6012.4282 | 3.7367 | 56 | 0.00018947 | 444 | 3.4619 | 2795 | 0.00052522 | 0.029412 | 2728 | 0.53 | 884
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 47143 | FALSE | 7882.6346 | 7882.6346 | 4.8991 | 67 | 0.00016052 | 638 | 2.9032 | 2815 | 0.00052216 | 0.034985 | 2729 | 0.63 | 837
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 562376 | FALSE | 12962.1789 | 12746.1039 | 7.9218 | 82 | 6.09e-05 | 2752 | 14.0412 | 2548 | 0.00052151 | 0.042763 | 2730 |  | 2872
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 154 | TRUE | 15159.6857 | 20.5741 | 0.012787 | 108 | 0.00013977 | 871 | 1.0919 | 2887 | 0.00051973 | 0.056131 | 2731 | 0.03 | 2260
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | CB | FALSE | 8918.2943 | 8918.2943 | 5.5428 | 46 | 0.00023568 | 259 | 2.1334 | 2835 | 0.00051722 | 0.023792 | 2732 | 44.97 | 153
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 10718 | FALSE | 13624.5702 | 13624.5702 | 8.4677 | 98 | 0.00029137 | 138 | 2.007 | 2842 | 0.0005122 | 0.050195 | 2733 | 0.58 | 858
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 32536 | FALSE | 17537.3204 | 17537.3204 | 10.8995 | 144 | 0.00010307 | 1568 | 6.8331 | 2690 | 0.00050182 | 0.072262 | 2734 | 126.24 | 9
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 12946 | FALSE | 5267.6978 | 3912.0696 | 2.4314 | 41 | 7.16e-05 | 2431 | 5.8607 | 2717 | 0.00050028 | 0.020511 | 2735 | 0.3 | 1016
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 716 | TRUE | 14760.549 | 161.153 | 0.10016 | 124 | 5.87e-05 | 2814 | 7.5935 | 2676 | 0.00049954 | 0.061943 | 2736 | 0.53 | 880
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | S2247 | FALSE | 2394.0014 | 2394.0014 | 1.4879 | 21 | 7.51e-05 | 2331 | 9.1225 | 2641 | 0.00049228 | 0.010338 | 2737 | 96.94 | 23
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 778286 | FALSE | 4188.0047 | 4188.0047 | 2.6029 | 5 | 3.64e-05 | 3323 | 19.0779 | 2461 | 0.0004909 | 0.0024545 | 2738 | 0 | 2637
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 457174 | TRUE | 1940.6507 | 925.5451 | 0.57523 | 14 | 0.00011583 | 1277 | 1.7636 | 2850 | 0.00048348 | 0.0067687 | 2739 |  | 3313
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 825520 | FALSE | 2407.6531 | 1896.9242 | 1.1789 | 21 | 4.68e-05 | 3116 | 8.3859 | 2659 | 0.00047064 | 0.0098834 | 2740 |  | 3202
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1264 | FALSE | 5420.1776 | 3078.9362 | 1.9136 | 50 | 5.67e-05 | 2869 | 10.5255 | 2619 | 0.00046357 | 0.023178 | 2741 | 0.61 | 847
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 45984 | FALSE | 7772.9197 | 7772.9197 | 4.8309 | 68 | 5.79e-05 | 2840 | 4.9585 | 2756 | 0.00046238 | 0.031442 | 2742 | 0.06 | 1809
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 90374 | FALSE | 7135.3675 | 6578.4615 | 4.0885 | 48 | 9.44e-05 | 1784 | 3.531 | 2791 | 0.0004592 | 0.022042 | 2743 | 0.06 | 1794
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | CB | TRUE | 22820.5615 | 0 | 0 | 197 | 8.41e-05 | 2089 | 3.1167 | 2806 | 0.00045724 | 0.090077 | 2744 | 43.8 | 164
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 9270 | FALSE | 9370.6933 | 9370.6933 | 5.8239 | 68 | 0.00011547 | 1288 | 6.0072 | 2714 | 0.00045602 | 0.03101 | 2745 | 40.93 | 182
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | XR234 | TRUE | 1908.9722 | 4.1246 | 0.0025635 | 26 | 4.19e-05 | 3226 | 7.3799 | 2680 | 0.00045563 | 0.011846 | 2746 | 0.03 | 2236
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 1238 | FALSE | 5923.8162 | 5923.8162 | 3.6817 | 30 | 0.00026272 | 189 | 9.5821 | 2630 | 0.0004533 | 0.013599 | 2747 | 62.35 | 85
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 81146 | FALSE | 9033.4152 | 1226.8593 | 0.7625 | 79 | 7.38e-05 | 2366 | 10.282 | 2621 | 0.00045161 | 0.035677 | 2748 | 0.03 | 2350
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 22412 | FALSE | 24417.5389 | 3680.7169 | 2.2876 | 130 | 3.7e-05 | 3316 | 12.5116 | 2579 | 0.0004496 | 0.058447 | 2749 |  | 2781
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5302 | FALSE | 9546.4932 | 9546.4932 | 5.9332 | 57 | 0.00026232 | 191 | 2.1517 | 2833 | 0.00044854 | 0.025567 | 2750 | 1.02 | 727
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | CB | TRUE | 4340.9857 | 216.2085 | 0.13437 | 38 | 4.69e-05 | 3115 | 6.7721 | 2692 | 0.00044808 | 0.017027 | 2751 | 8.14 | 434
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | CB | FALSE | 9677.833 | 9246.0032 | 5.7464 | 73 | 0.00012956 | 1017 | 4.2973 | 2773 | 0.00044728 | 0.032652 | 2752 | 0.53 | 879
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 872066 | TRUE | 1285.5374 | 856.8881 | 0.53256 | 13 | 8.99e-05 | 1916 | 14.7027 | 2535 | 0.0011906 | 0.015478 | 2598 |  | 3074
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 12596 | FALSE | 17025.8657 | 12925.0786 | 8.033 | 140 | 8.89e-05 | 1955 | 5.6622 | 2721 | 0.00043371 | 0.060719 | 2754 | 0.06 | 1804
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 9759 | FALSE | 4110.5786 | 4110.5786 | 2.5547 | 32 | 0.00015886 | 653 | 4.5245 | 2765 | 0.00043106 | 0.013794 | 2755 |  | 2867
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | CB | FALSE | 6570.8 | 6570.8 | 4.0838 | 11 | 6.96e-05 | 2484 | 248.9538 | 1542 | 0.00042329 | 0.0046561 | 2756 | 0.02 | 2523
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | L2219 | FALSE | 5447.1163 | 5447.1163 | 3.3854 | 41 | 7.22e-05 | 2411 | 7.0237 | 2687 | 0.00042266 | 0.017329 | 2757 | 49.71 | 121
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 12705 | TRUE | 9361.8686 | 0 | 0 | 74 | 2.21e-05 | 3518 | 9.0486 | 2643 | 0.00042265 | 0.031276 | 2758 |  | 2827
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 69032 | FALSE | 13655.5842 | 13655.5842 | 8.487 | 101 | 8.9e-05 | 1949 | 4.7713 | 2762 | 0.00041877 | 0.042296 | 2759 | 0.08 | 1653
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 520832 | FALSE | 12960.7664 | 9719.2853 | 6.0406 | 90 | 0.00014149 | 844 | 3.7624 | 2781 | 0.00040636 | 0.036573 | 2760 |  | 2787
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 903182 | FALSE | 1770.3755 | 1052.7078 | 0.65426 | 15 | 5.47e-05 | 2927 | 4.2832 | 2774 | 0.00040533 | 0.0060799 | 2761 |  | 3258
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 1286 | FALSE | 12241.8563 | 7682.9666 | 4.775 | 92 | 6.67e-05 | 2563 | 5.3157 | 2739 | 0.00040112 | 0.036903 | 2762 | 0.07 | 1737
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 76008 | FALSE | 25670.8015 | 25670.8015 | 15.9545 | 170 | 9.36e-05 | 1806 | 4.261 | 2775 | 0.000401 | 0.068169 | 2763 | 96.79 | 24
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 228906 | TRUE | 2215.3527 | 988.5949 | 0.61442 | 21 | 3.98e-05 | 3273 | 5.3472 | 2734 | 0.00039716 | 0.0083403 | 2764 |  | 3330
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 99432 | FALSE | 13966.781 | 2359.0159 | 1.4661 | 115 | 2.72e-05 | 3470 | 10.878 | 2612 | 0.00039549 | 0.045481 | 2765 | 0.07 | 1745
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 4905 | FALSE | 3704.1382 | 3704.1382 | 2.3021 | 35 | 8.13e-05 | 2174 | 6.1793 | 2710 | 0.00038885 | 0.01361 | 2766 | 65.75 | 75
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 60092 | FALSE | 15629.1336 | 15629.1336 | 9.7136 | 108 | 0.00019731 | 408 | 2.9279 | 2813 | 0.00038814 | 0.041919 | 2767 | 0.39 | 951
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 8442 | FALSE | 19428.9727 | 19428.9727 | 12.0752 | 50 | 6.39e-05 | 2650 | 8.1497 | 2666 | 0.00038233 | 0.019117 | 2768 | 0.11 | 1438
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 1210 | FALSE | 8832.2253 | 5252.6146 | 3.2645 | 73 | 0.00023323 | 270 | 1.6941 | 2853 | 0.00038163 | 0.027859 | 2769 | 0.29 | 1025
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 419634 | TRUE | 1981.0133 | 165.107 | 0.10261 | 14 | 7.81e-05 | 2255 | 6.2924 | 2707 | 0.00037832 | 0.0052965 | 2770 |  | 3436
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | CB | TRUE | 14648.5405 | 486.1753 | 0.30216 | 107 | 1.8e-05 | 3560 | 4.7299 | 2764 | 0.00037788 | 0.040433 | 2771 | 0.25 | 1087
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 418 | FALSE | 19645.0637 | 8262.136 | 5.135 | 130 | 5.79e-05 | 2837 | 5.0022 | 2753 | 0.00037742 | 0.049065 | 2772 | 0.06 | 1897
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 337544 | TRUE | 1419.0103 | 579.0642 | 0.35989 | 13 | 0.00011348 | 1333 | 3.7153 | 2783 | 0.00037689 | 0.0048996 | 2773 |  | 3561
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 7050 | FALSE | 15143.783 | 15143.783 | 9.4119 | 67 | 3.02e-05 | 3425 | 13.5475 | 2562 | 0.00037021 | 0.024804 | 2774 | 0 | 2642
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 8089 | FALSE | 4528.4761 | 4528.4761 | 2.8145 | 29 | 0.00010867 | 1432 | 3.3453 | 2802 | 0.00036614 | 0.010618 | 2775 | 4.59 | 513
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 84166 | FALSE | 13898.1694 | 13231.1785 | 8.2232 | 97 | 0.0002829 | 150 | 1.5368 | 2863 | 0.00036427 | 0.035334 | 2776 |  | 3013
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 1252 | FALSE | 6608.6355 | 6608.6355 | 4.1073 | 50 | 0.00013383 | 946 | 3.8677 | 2780 | 0.00036141 | 0.018071 | 2777 | 11.02 | 391
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | M501R | FALSE | 7503.1067 | 4016.4433 | 2.4962 | 60 | 4.68e-05 | 3118 | 3.6463 | 2785 | 0.00035751 | 0.021451 | 2778 | 0.03 | 2319
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | CB | TRUE | 2357.516 | 24.568 | 0.015269 | 24 | 1.88e-05 | 3556 | 2.0509 | 2838 | 0.00035038 | 0.0084091 | 2779 |  | 3009
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 1052 | FALSE | 6204.8696 | 5356.147 | 3.3289 | 49 | 5.66e-05 | 2870 | 5.2348 | 2741 | 0.00034866 | 0.017084 | 2780 | 0.08 | 1629
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | CB | FALSE | 2115.1186 | 1181.1241 | 0.73407 | 17 | 7.57e-05 | 2317 | 2.8608 | 2817 | 0.00034683 | 0.0058961 | 2781 | 0.04 | 2077
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | CR020 | FALSE | 3932.8974 | 3932.8974 | 2.4443 | 15 | 9.37e-05 | 1801 | 4.8237 | 2758 | 0.00034485 | 0.0051727 | 2782 | 41.15 | 180
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 857972 | FALSE | 2082.0425 | 1672.4824 | 1.0395 | 18 | 4.68e-05 | 3119 | 6.2207 | 2708 | 0.00034064 | 0.0061316 | 2783 |  | 3208
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 143744 | FALSE | 1706.1115 | 1706.1115 | 1.0604 | 13 | 0.00045932 | 45 | 1.8946 | 2847 | 0.00033981 | 0.0044176 | 2784 |  | 3153
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 84318 | FALSE | 16486.0902 | 16486.0902 | 10.2462 | 142 | 8.55e-05 | 2041 | 8.7666 | 2648 | 0.00033804 | 0.048002 | 2785 | 0.05 | 2065
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | L1969 | FALSE | 1768.6139 | 1768.6139 | 1.0992 | 16 | 7.78e-05 | 2267 | 7.4947 | 2677 | 0.00032448 | 0.0051917 | 2786 | 58.12 | 93
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | LB40 | FALSE | 14924.9201 | 13714.1212 | 8.5234 | 131 | 7.57e-05 | 2314 | 4.7844 | 2761 | 0.00032354 | 0.042384 | 2787 | 0.15 | 1298
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 9690 | FALSE | 27916.5832 | 27916.5832 | 17.3503 | 185 | 4.8e-05 | 3093 | 9.3188 | 2639 | 0.00031402 | 0.058094 | 2788 | 45.06 | 151
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 402866 | FALSE | 2560.4032 | 2560.4032 | 1.5913 | 20 | 8.05e-05 | 2192 | 2.4422 | 2826 | 0.0003137 | 0.0062739 | 2789 | 0.02 | 2566
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | CB | TRUE | 2195.0052 | 304.3324 | 0.18914 | 18 | 7.95e-05 | 2222 | 3.5853 | 2789 | 0.00031227 | 0.0056208 | 2790 | 1.29 | 688
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | CB | TRUE | 7402.9758 | 10.2676 | 0.0063814 | 69 | 2.92e-05 | 3436 | 37.685 | 2292 | 0.00031202 | 0.02153 | 2791 | 1.11 | 716
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | BR160 | FALSE | 18386.4832 | 13394.711 | 8.3249 | 132 | 6.92e-05 | 2499 | 3.3682 | 2800 | 0.00031068 | 0.04101 | 2792 | 0.24 | 1104
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 720639 | FALSE | 5844.6694 | 2660.7876 | 1.6537 | 25 | 0.00018595 | 468 | 1.9664 | 2846 | 0.0003062 | 0.0076549 | 2793 |  | 3105
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | W10 | FALSE | 3001.7775 | 2354.9644 | 1.4636 | 29 | 3.43e-05 | 3364 | 7.1616 | 2684 | 0.00030601 | 0.0088744 | 2794 | 0.04 | 2112
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 9096 | FALSE | 10649.9386 | 5304.2381 | 3.2966 | 78 | 3.35e-05 | 3375 | 6.4596 | 2697 | 0.00030601 | 0.023869 | 2795 | 0.04 | 2102
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | CB | FALSE | 11982.8259 | 11982.8259 | 7.4474 | 97 | 5.96e-05 | 2786 | 4.4752 | 2768 | 0.00030421 | 0.029509 | 2796 | 0.19 | 1186
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 420146 | FALSE | 5058.5239 | 4389.3602 | 2.728 | 43 | 0.00013428 | 940 | 3.382 | 2799 | 0.00030412 | 0.013077 | 2797 |  | 3266
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | MR650 | FALSE | 4320.1366 | 2086.6412 | 1.2969 | 30 | 3.12e-05 | 3411 | 6.4702 | 2696 | 0.00029523 | 0.0088568 | 2798 | 0.07 | 1706
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 472 | FALSE | 7739.1551 | 4930.8208 | 3.0645 | 71 | 9.58e-05 | 1733 | 2.7474 | 2818 | 0.00029462 | 0.020918 | 2799 | 0.08 | 1630
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 4690 | FALSE | 23028.3671 | 18710.8643 | 11.6289 | 161 | 8.91e-05 | 1944 | 4.3458 | 2772 | 0.00029439 | 0.047396 | 2800 | 0.16 | 1260
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5166 | FALSE | 8840.5786 | 8840.5786 | 5.4945 | 81 | 9.56e-05 | 1737 | 3.5862 | 2788 | 0.00028991 | 0.023482 | 2801 | 31.21 | 231
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 48868 | TRUE | 3010.868 | 0 | 0 | 21 | 2.4e-05 | 3505 | 3.0775 | 2810 | 0.00028316 | 0.0059463 | 2802 | 0.31 | 997
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 1640 | FALSE | 16804.166 | 16804.166 | 10.4439 | 59 | 7.88e-05 | 2241 | 5.7047 | 2720 | 0.00028287 | 0.016689 | 2803 | 0.01 | 2569
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3032 | FALSE | 15762.9704 | 5799.169 | 3.6042 | 84 | 2.44e-05 | 3503 | 5.9133 | 2716 | 0.00028141 | 0.023638 | 2804 | 0.03 | 2349
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 693441 | FALSE | 6859.835 | 6859.835 | 4.2634 | 59 | 4.96e-05 | 3046 | 4.4985 | 2767 | 0.00027928 | 0.016478 | 2805 | 0.29 | 1029
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2183 | FALSE | 4246.8638 | 4246.8638 | 2.6394 | 33 | 9.47e-05 | 1774 | 4.3864 | 2771 | 0.00027436 | 0.009054 | 2806 | 0.05 | 2047
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 952 | FALSE | 16341.5936 | 16341.5936 | 10.1564 | 130 | 0.00010228 | 1595 | 2.9907 | 2812 | 0.00027431 | 0.03566 | 2807 | 0.36 | 970
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | CB | FALSE | 11616.1021 | 9822.6918 | 6.1048 | 86 | 0.0005458 | 25 | 1.1717 | 2883 | 0.00026897 | 0.023131 | 2808 | 19.78 | 308
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 446423 | FALSE | 2345.7749 | 1135.402 | 0.70566 | 23 | 0.00012326 | 1131 | 2.131 | 2836 | 0.00026534 | 0.0061027 | 2809 |  | 2912
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 37278 | FALSE | 10929.4406 | 10929.4406 | 6.7927 | 99 | 0.00011401 | 1321 | 2.7082 | 2820 | 0.00026318 | 0.026055 | 2810 | 62.81 | 82
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | CB | FALSE | 18604.4746 | 8502.7441 | 5.2845 | 115 | 8.11e-05 | 2181 | 1.4421 | 2868 | 0.00025895 | 0.029779 | 2811 | 0.23 | 1110
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 68920 | FALSE | 11754.4382 | 10341.5361 | 6.4273 | 91 | 9.04e-05 | 1900 | 5.0244 | 2751 | 0.0002577 | 0.02345 | 2812 | 0.16 | 1274
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | CB | FALSE | 7764.6762 | 7472.6669 | 4.6443 | 53 | 0.0005799 | 22 | 0.9633 | 2896 | 0.0002457 | 0.013022 | 2813 | 38.98 | 191
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 410 | FALSE | 3634.5971 | 2502.9293 | 1.5556 | 28 | 2.49e-05 | 3498 | 2.3255 | 2830 | 0.00024476 | 0.0068532 | 2814 | 0.06 | 1826
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | CB | TRUE | 13992.2701 | 885.5612 | 0.55038 | 109 | 0.0002118 | 353 | 2.0247 | 2841 | 0.00024231 | 0.026412 | 2815 | 0.21 | 1152
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | CB | FALSE | 19709.1046 | 14267.6715 | 8.8674 | 60 | 0.0002127 | 346 | 1.2563 | 2877 | 0.00023784 | 0.01427 | 2816 | 0.11 | 1433
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 63100 | FALSE | 6591.8886 | 6591.8886 | 4.0969 | 55 | 0.00023384 | 266 | 1.3628 | 2873 | 0.00023675 | 0.013021 | 2817 | 5.34 | 490
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1701 | FALSE | 2248.9876 | 2248.9876 | 1.3978 | 18 | 9.91e-05 | 1666 | 2.7097 | 2819 | 0.00023556 | 0.0042401 | 2818 | 29.59 | 240
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 5001 | TRUE | 2742.1134 | 0 | 0 | 25 | 3.09e-05 | 3419 | 4.514 | 2766 | 0.00023403 | 0.0058507 | 2819 | 6.31 | 469
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | CB | TRUE | 5657.7233 | 67.4906 | 0.041946 | 43 | 3.14e-05 | 3409 | 11.8961 | 2591 | 0.000232 | 0.0099759 | 2820 | 0.04 | 2072
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | CB | FALSE | 13792.1671 | 9469.8097 | 5.8855 | 102 | 0.00017335 | 539 | 0.99807 | 2891 | 0.00023023 | 0.023483 | 2821 | 0.21 | 1141
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 857172 | TRUE | 1843.2099 | 152.0386 | 0.094493 | 15 | 8.79e-05 | 1986 | 3.2284 | 2803 | 0.00022992 | 0.0034488 | 2822 |  | 3212
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 5060 | TRUE | 1113.3002 | 291.5638 | 0.18121 | 12 | 7.56e-05 | 2319 | 1.3951 | 2871 | 0.00022663 | 0.0027196 | 2823 |  | 3502
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 114284 | TRUE | 893.7863 | 451.7326 | 0.28075 | 11 | 8.37e-05 | 2102 | 4.3909 | 2770 | 0.00022547 | 0.0024802 | 2824 |  | 3236
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 37276 | FALSE | 18746.4684 | 18746.4684 | 11.651 | 168 | 0.00010311 | 1567 | 2.0474 | 2839 | 0.00022047 | 0.037039 | 2825 | 88.82 | 33
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 2026 | FALSE | 16422.8166 | 8438.7955 | 5.2447 | 126 | 4.83e-05 | 3086 | 5.725 | 2719 | 0.00021753 | 0.027409 | 2826 | 0.07 | 1690
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 688590 | FALSE | 3500.4301 | 1691.536 | 1.0513 | 32 | 4.98e-05 | 3041 | 3.0358 | 2811 | 0.00021706 | 0.0069459 | 2827 |  | 2671
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 705 | TRUE | 2028.0775 | 622.3172 | 0.38677 | 20 | 0.00010699 | 1473 | 4.0264 | 2777 | 0.00021298 | 0.0042596 | 2828 |  | 2895
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 8090 | FALSE | 6501.5338 | 6501.5338 | 4.0407 | 53 | 0.00010162 | 1614 | 1.8606 | 2848 | 0.00021162 | 0.011216 | 2829 | 58.21 | 92
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | W50 | TRUE | 5818.6322 | 997.9458 | 0.62023 | 40 | 1.48e-05 | 3587 | 16.6866 | 2506 | 0.00021093 | 0.0084371 | 2830 | 0.03 | 2302
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 79628 | FALSE | 23813.9358 | 23813.9358 | 14.8005 | 156 | 7.91e-05 | 2230 | 2.6556 | 2822 | 0.00021051 | 0.032839 | 2831 | 0.17 | 1233
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 1226 | FALSE | 12605.0062 | 12282.9745 | 7.6339 | 96 | 0.00012073 | 1171 | 0.80895 | 2902 | 0.00020916 | 0.02008 | 2832 | 1.01 | 728
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | CR192 | FALSE | 6810.4625 | 3963.0316 | 2.463 | 54 | 8.07e-05 | 2188 | 1.3873 | 2872 | 0.00020828 | 0.011247 | 2833 | 0.21 | 1135
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | V22 | TRUE | 810.5999 | 50.4916 | 0.031381 | 14 | 2e-05 | 3542 | 3.4621 | 2794 | 0.00020377 | 0.0028528 | 2834 |  | 2885
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 3066 | TRUE | 26.0345 | 26.0345 | 0.016181 | 2 | 5.33e-05 | 2953 | 11.9582 | 2586 | 0.00020359 | 0.00040718 | 2835 | 0.44 | 922
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 8132 | FALSE | 5814.9582 | 4248.014 | 2.6402 | 47 | 9.89e-05 | 1671 | 2.0883 | 2837 | 0.00020337 | 0.0095582 | 2836 | 0.04 | 2079
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 1166 | FALSE | 24234.157 | 20163.1012 | 12.5314 | 213 | 0.00022306 | 307 | 0.8473 | 2900 | 0.00020294 | 0.043227 | 2837 | 1.46 | 673
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | CB | FALSE | 5679.6302 | 5679.6302 | 3.5299 | 43 | 0.00015288 | 721 | 0.6192 | 2911 | 0.00020121 | 0.0086519 | 2838 | 23.03 | 289
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 964592 | TRUE | 1787.6075 | 941.9387 | 0.58542 | 15 | 2.91e-05 | 3439 | 9.5689 | 2634 | 0.00019824 | 0.0029736 | 2839 |  | 3528
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 1200 | FALSE | 4658.8808 | 4658.8808 | 2.8955 | 34 | 8.18e-05 | 2158 | 2.8623 | 2816 | 0.00019566 | 0.0066525 | 2840 | 4.42 | 520
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 53192 | TRUE | 3316.9892 | 889.758 | 0.55299 | 30 | 5.41e-05 | 2941 | 5.3377 | 2737 | 0.0001937 | 0.0058109 | 2841 |  | 3032
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 660408 | TRUE | 3217.4282 | 570.687 | 0.35468 | 26 | 3.1e-05 | 3417 | 7.378 | 2681 | 0.00019086 | 0.0049624 | 2842 |  | 3121
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | CB | FALSE | 3053.2387 | 1333.5262 | 0.82879 | 33 | 7.29e-05 | 2396 | 1.9862 | 2843 | 0.00018865 | 0.0062254 | 2843 | 0.02 | 2444
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 750618 | FALSE | 1583.7149 | 1538.3917 | 0.95612 | 13 | 5.33e-05 | 2955 | 3.1105 | 2807 | 0.00018369 | 0.002388 | 2844 |  | 2755
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | CB | FALSE | 6937.627 | 6745.77 | 4.1925 | 55 | 9.87e-05 | 1677 | 3.0905 | 2808 | 0.00018024 | 0.0099135 | 2845 | 0.1 | 1500
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 402/2 LR | FALSE | 10638.2509 | 10545.4353 | 6.554 | 91 | 0.00012174 | 1151 | 1.633 | 2857 | 0.00017917 | 0.016305 | 2846 |  | 2922
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | S2123 | FALSE | 2988.9855 | 2988.9855 | 1.8577 | 25 | 0.00012986 | 1010 | 1.9671 | 2845 | 0.00017176 | 0.0042941 | 2847 |  | 3018
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 290705 | FALSE | 5314.0636 | 5193.0778 | 3.2275 | 38 | 0.0001966 | 410 | 2.568 | 2823 | 0.00016712 | 0.0063506 | 2848 |  | 2706
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 829194 | FALSE | 18124.3826 | 18124.3826 | 11.2644 | 142 | 0.00022979 | 286 | 0.40121 | 2916 | 0.00016422 | 0.023319 | 2849 |  | 2858
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 12990 | FALSE | 21277.9249 | 21277.9249 | 13.2243 | 161 | 0.00018796 | 455 | 1.0994 | 2886 | 0.00016127 | 0.025964 | 2850 | 0.86 | 764
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 32747 | FALSE | 2820.8108 | 1047.4929 | 0.65102 | 26 | 0.00014649 | 780 | 1.2825 | 2876 | 0.00016086 | 0.0041824 | 2851 | 1.65 | 658
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 76178 | FALSE | 32532.3048 | 32532.3048 | 20.219 | 248 | 0.00012177 | 1150 | 3.133 | 2805 | 0.00015934 | 0.039517 | 2852 | 0.13 | 1361
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 3716 | TRUE | 21171.7372 | 690.7324 | 0.42929 | 157 | 6.49e-05 | 2613 | 1.6769 | 2855 | 0.00015488 | 0.024316 | 2853 | 0.03 | 2321
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 57886 | FALSE | 8466.0843 | 6549.4745 | 4.0705 | 81 | 8.26e-05 | 2138 | 0.94597 | 2899 | 0.00015101 | 0.012232 | 2854 | 0.08 | 1619
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | A40 | FALSE | 20639.8903 | 6084.3101 | 3.7814 | 174 | 4.34e-05 | 3202 | 1.431 | 2870 | 0.00015079 | 0.026237 | 2855 | 0.03 | 2254
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 8918 | FALSE | 3457.885 | 2431.0442 | 1.5109 | 30 | 0.00022692 | 298 | 2.4426 | 2824 | 0.0001494 | 0.0044819 | 2856 | 2.79 | 579
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 56468 | FALSE | 9625.3334 | 8910.5893 | 5.538 | 85 | 0.00022965 | 287 | 1.0912 | 2888 | 0.0001483 | 0.012606 | 2857 | 12.55 | 373
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 419718 | FALSE | 3649.8042 | 3649.8042 | 2.2684 | 25 | 0.00013422 | 941 | 1.0173 | 2890 | 0.0001469 | 0.0036725 | 2858 |  | 3248
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 1278 | FALSE | 12855.1379 | 9099.8598 | 5.6556 | 96 | 9.74e-05 | 1703 | 1.5519 | 2861 | 0.00014529 | 0.013948 | 2859 | 0.05 | 1918
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 1220 | TRUE | 7829.4679 | 0 | 0 | 57 | 2.6e-05 | 3488 | 1.1753 | 2882 | 0.00013353 | 0.0076113 | 2860 | 0.03 | 2239
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | CB | FALSE | 24857.1517 | 22896.4557 | 14.2302 | 209 | 9.11e-05 | 1876 | 1.2034 | 2878 | 0.00012966 | 0.027098 | 2861 | 0.08 | 1613
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 68380 | FALSE | 10711.9675 | 10711.9675 | 6.6575 | 88 | 0.00012793 | 1048 | 2.2263 | 2832 | 0.00012865 | 0.011322 | 2862 | 0.74 | 791
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | MR544 | TRUE | 7120.8066 | 27.9821 | 0.017391 | 62 | 9.02e-06 | 3615 | 1.9811 | 2844 | 0.00012274 | 0.0076101 | 2863 | 0.04 | 2154
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 10954 | FALSE | 11428.7483 | 11428.7483 | 7.103 | 90 | 9.19e-05 | 1847 | 2.4422 | 2825 | 0.00012262 | 0.011036 | 2864 | 0.16 | 1268
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 1282 | TRUE | 5984.1771 | 0 | 0 | 56 | 9.97e-05 | 1654 | 1.1951 | 2881 | 0.00012029 | 0.0067363 | 2865 | 0.03 | 2326
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 15341 | TRUE | 2075.9695 | 391.2765 | 0.24318 | 18 | 3.43e-05 | 3363 | 5.3372 | 2738 | 0.00011859 | 0.0021346 | 2866 | 0.74 | 792
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 303870 | FALSE | 1292.4248 | 1028.4638 | 0.63919 | 7 | 5.32e-05 | 2962 | 2.3249 | 2831 | 0.0001185 | 0.00082948 | 2867 |  | 3080
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 426 | FALSE | 6243.6329 | 3219.5011 | 2.0009 | 52 | 5.74e-05 | 2854 | 1.7424 | 2852 | 0.00011662 | 0.0060642 | 2868 | 0.04 | 2194
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 774760 | FALSE | 5348.863 | 5348.863 | 3.3243 | 37 | 0.00022083 | 317 | 0.70854 | 2908 | 0.00011197 | 0.0041429 | 2869 |  | 3263
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 74648 | TRUE | 7581.2034 | 262.1986 | 0.16296 | 63 | 8.48e-05 | 2069 | 1.0707 | 2889 | 0.00011106 | 0.0069966 | 2870 | 0.42 | 932
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 69124 | FALSE | 4347.2792 | 4347.2792 | 2.7019 | 33 | 8.53e-05 | 2047 | 1.5063 | 2864 | 0.00010917 | 0.0036026 | 2871 | 0.05 | 2055
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 116815 | FALSE | 4074.4873 | 2540.2857 | 1.5788 | 33 | 0.00019069 | 440 | 1.5062 | 2865 | 0.00010723 | 0.0035385 | 2872 |  | 3182
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 93038 | FALSE | 4552.6155 | 2107.4343 | 1.3098 | 39 | 0.00019968 | 398 | 1.284 | 2875 | 0.00010645 | 0.0041517 | 2873 | 0.03 | 2241
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 2032 | TRUE | 14427.8487 | 905.5345 | 0.56279 | 103 | 2.54e-05 | 3492 | 0.98818 | 2894 | 0.0001063 | 0.010949 | 2874 | 0.14 | 1323
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3442 | FALSE | 8430.8944 | 5599.863 | 3.4803 | 68 | 0.00011662 | 1257 | 0.7637 | 2904 | 0.00010619 | 0.0072205 | 2875 | 0.07 | 1685
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 33060 | TRUE | 7941.0149 | 856.2789 | 0.53218 | 64 | 0.00022712 | 296 | 0.31239 | 2924 | 9.95e-05 | 0.00637 | 2876 | 0.02 | 2560
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | P148 | FALSE | 7362.5215 | 1361.9079 | 0.84643 | 54 | 4.59e-05 | 3143 | 1.5547 | 2859 | 9.88e-05 | 0.0053348 | 2877 |  | 2783
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 75348 | FALSE | 8532.4043 | 8532.4043 | 5.3029 | 77 | 8.36e-05 | 2110 | 1.3013 | 2874 | 9.55e-05 | 0.0073521 | 2878 | 79.37 | 49
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 1232 | FALSE | 14610.263 | 12420.8061 | 7.7196 | 64 | 4.28e-05 | 3212 | 1.5493 | 2862 | 9.09e-05 | 0.0058153 | 2879 | 0.05 | 2007
4735 | ELK 11018779 | 42981101 | ELK 1101 | 8779 | FALSE | 6865.4129 | 6865.4129 | 4.2669 | 41 | 0.00012002 | 1187 | 1.8049 | 2849 | 8.98e-05 | 0.0036815 | 2880 | 0.05 | 2060
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 3034 | TRUE | 31905.8871 | 80.3377 | 0.04993 | 193 | 4.58e-05 | 3145 | 2.3733 | 2828 | 8.72e-05 | 0.016822 | 2881 | 0.02 | 2481
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 86032 | FALSE | 4656.0497 | 1615.684 | 1.0042 | 23 | 2.82e-05 | 3455 | 3.5085 | 2793 | 8.54e-05 | 0.0019637 | 2882 | 0.82 | 770
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 922138 | FALSE | 3566.848 | 2524.6386 | 1.5691 | 24 | 4.98e-05 | 3043 | 2.046 | 2840 | 8.42e-05 | 0.00202 | 2883 |  | 3016
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 12106 | TRUE | 19539.3367 | 556.8348 | 0.34608 | 139 | 8.36e-05 | 2105 | 0.75016 | 2905 | 8.09e-05 | 0.011248 | 2884 | 0.06 | 1840
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 56774 | TRUE | 4425.2807 | 385.0871 | 0.23933 | 39 | 1.66e-05 | 3572 | 2.9096 | 2814 | 7.87e-05 | 0.0030702 | 2885 |  | 2668
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | CB | FALSE | 16799.2868 | 16799.2868 | 10.4408 | 132 | 9.67e-05 | 1719 | 1.6868 | 2854 | 7.46e-05 | 0.0098468 | 2886 | 0.13 | 1339
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 37088 | FALSE | 18269.9988 | 11434.4875 | 7.1066 | 135 | 4.84e-05 | 3080 | 2.354 | 2829 | 7.34e-05 | 0.0099063 | 2887 | 0.04 | 2198
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1226 | FALSE | 12686.9371 | 2717.7424 | 1.6891 | 102 | 7.32e-05 | 2391 | 0.9972 | 2892 | 7.04e-05 | 0.0071773 | 2888 | 0.01 | 2602
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 279670 | FALSE | 7840.1687 | 6244.093 | 3.8807 | 54 | 9.36e-05 | 1805 | 0.35903 | 2923 | 7.01e-05 | 0.003785 | 2889 |  | 3141
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 103126 | TRUE | 487.0335 | 487.0335 | 0.30269 | 5 | 0.0010399 | 1 | 0.066432 | 2993 | 6.91e-05 | 0.00034541 | 2890 |  | 3462
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 4639 | FALSE | 5228.1955 | 5228.1955 | 3.2493 | 44 | 0.00013355 | 950 | 1.1467 | 2885 | 6.79e-05 | 0.0029871 | 2891 | 1.36 | 680
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 10141 | FALSE | 4694.7775 | 4694.7775 | 2.9178 | 21 | 5.62e-05 | 2882 | 1.1979 | 2879 | 6.78e-05 | 0.0014246 | 2892 | 4.61 | 512
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 910 | FALSE | 11465.6942 | 2722.6312 | 1.6921 | 89 | 0.00012024 | 1182 | 0.77728 | 2903 | 6.7e-05 | 0.005959 | 2893 | 0.04 | 2206
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 690098 | FALSE | 12079.1397 | 11883.9636 | 7.3859 | 108 | 8.89e-05 | 1957 | 0.94645 | 2898 | 6.67e-05 | 0.0072019 | 2894 |  | 2672
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 36656 | TRUE | 1041.7398 | 220.7989 | 0.13723 | 14 | 0.00098372 | 2 | 0.065517 | 3361 | 6.47e-05 | 0.00090588 | 2895 |  | 3040
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | MR210 | FALSE | 12199.0798 | 1314.2646 | 0.81682 | 103 | 2.38e-05 | 3506 | 0.99149 | 2893 | 6.29e-05 | 0.0064828 | 2896 | 1.94 | 629
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | CR014 | FALSE | 16905.8619 | 16905.8619 | 10.5071 | 137 | 0.00013845 | 889 | 0.41497 | 2915 | 6.24e-05 | 0.0085442 | 2897 | 0.99 | 734
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 65444 | TRUE | 757.2593 | 757.2593 | 0.47064 | 9 | 0.00091179 | 3 | 0.066431 | 3074 | 6.06e-05 | 0.00054514 | 2898 | 12.01 | 379
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 528 | FALSE | 4980.15 | 2865.7848 | 1.7811 | 46 | 4.07e-05 | 3254 | 1.441 | 2869 | 5.41e-05 | 0.002487 | 2899 | 0.21 | 1140
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 189010 | TRUE | 84.167 | 59.0426 | 0.036695 | 4 | 0.000791 | 5 | 0.065792 | 3268 | 5.23e-05 | 0.00020939 | 2900 |  | 3386
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 507513 | FALSE | 8339.9553 | 4803.4 | 2.9853 | 65 | 0.00010329 | 1564 | 1.1629 | 2884 | 4.93e-05 | 0.0032025 | 2901 |  | 2887
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | L503R | FALSE | 6910.8038 | 6910.8038 | 4.2951 | 62 | 0.00010589 | 1498 | 0.83292 | 2901 | 4.87e-05 | 0.0030213 | 2902 | 0.09 | 1547
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 590402 | FALSE | 9614.0154 | 3916.034 | 2.4338 | 78 | 5.92e-05 | 2800 | 0.67392 | 2910 | 4.84e-05 | 0.0037788 | 2903 |  | 3086
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 468200 | TRUE | 531.6801 | 531.6801 | 0.33044 | 4 | 0.00072422 | 6 | 0.066431 | 3033 | 4.81e-05 | 0.00019244 | 2904 |  | 3132
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 5039 | TRUE | 4245.0462 | 0 | 0 | 28 | 7.24e-05 | 2407 | 1.1951 | 2880 | 4.53e-05 | 0.0012694 | 2905 |  | 3275
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 2486 | TRUE | 189.7916 | 146.4228 | 0.091002 | 2 | 0.00067148 | 8 | 0.065791 | 3270 | 4.43e-05 | 8.8537e-05 | 2906 |  | 3565
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 828400 | TRUE | 50.1094 | 50.1094 | 0.031143 | 2 | 0.00066466 | 9 | 0.066431 | 3040 | 4.42e-05 | 8.8308e-05 | 2907 |  | 3627
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 1362 | TRUE | 24.9514 | 24.9514 | 0.015507 | 1 | 0.00065973 | 10 | 0.066431 | 3035 | 4.38e-05 | 4.3827e-05 | 2908 | 0.04 | 2068
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | BR194 | FALSE | 8491.9295 | 6148.6965 | 3.8214 | 74 | 6.64e-05 | 2577 | 0.38709 | 2919 | 4.32e-05 | 0.0031957 | 2909 | 0.12 | 1386
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 1212 | FALSE | 3248.6095 | 3232.6075 | 2.0091 | 33 | 0.00064007 | 12 | 0.066393 | 3123 | 4.25e-05 | 0.0014026 | 2910 |  | 3117
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 10996 | FALSE | 1226.2093 | 1226.2093 | 0.76209 | 8 | 0.00063772 | 13 | 0.066431 | 3070 | 4.24e-05 | 0.00033892 | 2911 | 3.1 | 562
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 99226 | FALSE | 5537.6206 | 1841.8715 | 1.1447 | 42 | 0.00062786 | 15 | 0.065639 | 3326 | 4.12e-05 | 0.0017299 | 2912 |  | 3154
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 956 | FALSE | 19682.0883 | 18278.7267 | 11.3603 | 145 | 8.77e-05 | 1994 | 0.39404 | 2918 | 4.09e-05 | 0.0059316 | 2913 | 0.15 | 1277
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 5300 | FALSE | 15760.3239 | 15760.3239 | 9.7951 | 115 | 0.00020513 | 380 | 0.27315 | 2925 | 3.97e-05 | 0.0045672 | 2914 |  | 2767
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 95050 | TRUE | 223.2117 | 223.2117 | 0.13873 | 5 | 0.00059508 | 17 | 0.066431 | 3081 | 3.95e-05 | 0.00019766 | 2915 | 0.24 | 1092
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 7170 | FALSE | 8726.7127 | 8726.7127 | 5.4237 | 54 | 2.87e-05 | 3442 | 2.7066 | 2821 | 3.95e-05 | 0.0021326 | 2916 | 0 | 2648
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 5400 | TRUE | 731.4241 | 731.4241 | 0.45458 | 4 | 0.00059378 | 18 | 0.066431 | 3083 | 3.94e-05 | 0.00015778 | 2917 | 0.27 | 1057
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 38430 | FALSE | 10237.4777 | 6060.3575 | 3.7665 | 90 | 5.32e-05 | 2959 | 0.59378 | 2912 | 3.78e-05 | 0.0033991 | 2918 | 0.19 | 1175
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | CB | FALSE | 6247.2514 | 1003.198 | 0.62349 | 47 | 4.84e-05 | 3081 | 0.73812 | 2907 | 3.52e-05 | 0.0016536 | 2919 |  | 2772
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 449638 | TRUE | 41.9833 | 41.9833 | 0.026093 | 1 | 0.00016049 | 640 | 0.21903 | 2930 | 3.52e-05 | 3.5151e-05 | 2920 |  | 2904
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 777484 | FALSE | 5712.0142 | 1455.0408 | 0.90431 | 50 | 1.32e-05 | 3597 | 5.1374 | 2746 | 3.51e-05 | 0.0017533 | 2921 |  | 2773
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 2534 | FALSE | 5245.4729 | 5105.9059 | 3.1733 | 49 | 0.00050354 | 30 | 0.066327 | 3143 | 3.34e-05 | 0.0016354 | 2922 | 0.49 | 899
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | CB | TRUE | 6265.5755 | 560.1275 | 0.34812 | 51 | 1.53e-05 | 3585 | 1.6186 | 2858 | 3.25e-05 | 0.0016578 | 2923 | 0.17 | 1234
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 2488 | FALSE | 5690.0714 | 5690.0714 | 3.5364 | 47 | 0.0004856 | 34 | 0.066431 | 3043 | 3.23e-05 | 0.0015162 | 2924 |  | 2916
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 181562 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00048291 | 37 | 0.066432 | 2996 | 3.21e-05 | 3.208e-05 | 2925 |  | 3615
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 283794 | FALSE | 4034.8507 | 3810.7404 | 2.3684 | 37 | 0.00048267 | 38 | 0.066328 | 3142 | 3.2e-05 | 0.0011841 | 2926 |  | 2942
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 35592 | FALSE | 21129.6388 | 21129.6388 | 13.1322 | 149 | 0.00014429 | 808 | 0.38535 | 2920 | 3.2e-05 | 0.0047622 | 2927 | 0.14 | 1329
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 3907 | FALSE | 1437.9091 | 1437.9091 | 0.89367 | 16 | 0.00047789 | 39 | 0.066432 | 3009 | 3.17e-05 | 0.00050795 | 2928 | 0.56 | 864
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 3186 | FALSE | 15806.1877 | 15806.1877 | 9.8236 | 143 | 7.94e-05 | 2223 | 0.39871 | 2917 | 3.16e-05 | 0.0045118 | 2929 | 0.04 | 2226
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 435168 | FALSE | 2902.2955 | 2068.4077 | 1.2855 | 26 | 4.95e-05 | 3049 | 0.97971 | 2895 | 3.11e-05 | 0.00080941 | 2930 |  | 3011
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 244027 | TRUE | 620.9738 | 492.7502 | 0.30625 | 6 | 0.00047101 | 41 | 0.065791 | 3272 | 3.09e-05 | 0.00018558 | 2931 |  | 3214
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 95394 | TRUE | 790.3942 | 790.3942 | 0.49123 | 8 | 0.00046445 | 43 | 0.066431 | 3075 | 3.09e-05 | 0.00024683 | 2932 | 8.99 | 417
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 36042 | FALSE | 14063.6211 | 13184.5103 | 8.1942 | 119 | 0.00046491 | 42 | 0.066335 | 3138 | 3.08e-05 | 0.0036673 | 2933 |  | 2883
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 561686 | TRUE | 147.2029 | 147.2029 | 0.091487 | 1 | 0.00044669 | 47 | 0.066431 | 3105 | 2.97e-05 | 2.9674e-05 | 2934 |  | 3430
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 16010 | FALSE | 2728.9115 | 2728.9115 | 1.696 | 25 | 0.00044502 | 49 | 0.066431 | 3054 | 2.96e-05 | 0.00073909 | 2935 | 0.3 | 1015
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 38404 | FALSE | 9333.1056 | 5730.6143 | 3.5616 | 47 | 0.00010907 | 1427 | 0.73881 | 2906 | 2.95e-05 | 0.0013868 | 2936 | 0.08 | 1611
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 395180 | FALSE | 2394.7505 | 2263.8752 | 1.407 | 20 | 1.62e-05 | 3578 | 2.4421 | 2827 | 2.94e-05 | 0.00058824 | 2937 |  | 3059
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 214052 | TRUE | 1011.6764 | 941.1587 | 0.58493 | 7 | 0.00044429 | 50 | 0.066065 | 3204 | 2.93e-05 | 0.00020531 | 2938 |  | 3447
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 176130 | TRUE | 32.0737 | 32.0737 | 0.019934 | 1 | 0.00044128 | 54 | 0.066432 | 3008 | 2.93e-05 | 2.9315e-05 | 2939 |  | 3388
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | CB | TRUE | 225.7012 | 190.3788 | 0.11832 | 6 | 0.00043795 | 56 | 0.066004 | 3225 | 2.9e-05 | 0.00017429 | 2940 | 0.17 | 1240
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | CB | FALSE | 5993.6916 | 2211.8341 | 1.3747 | 46 | 0.0004418 | 52 | 0.065541 | 3355 | 2.9e-05 | 0.0013348 | 2941 | 4.56 | 515
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 969778 | FALSE | 1070.9786 | 1070.9786 | 0.66562 | 9 | 0.00042983 | 59 | 0.066432 | 3004 | 2.86e-05 | 0.00025699 | 2942 |  | 3193
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 954322 | FALSE | 6923.0973 | 6923.0973 | 4.3027 | 63 | 0.0004268 | 60 | 0.066431 | 3044 | 2.84e-05 | 0.0017862 | 2943 |  | 2742
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 5479 | TRUE | 289.2777 | 289.2777 | 0.17979 | 3 | 0.00041807 | 63 | 0.066431 | 3086 | 2.78e-05 | 8.3318e-05 | 2944 | 2.14 | 619
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | BL 2101 | TRUE | 5.191 | 5.191 | 0.0032262 | 1 | 0.00041248 | 66 | 0.066431 | 3087 | 2.74e-05 | 2.7401e-05 | 2945 | 6.05 | 475
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | CB | FALSE | 2742.3098 | 2742.3098 | 1.7044 | 19 | 0.00040765 | 67 | 0.066431 | 3078 | 2.71e-05 | 0.00051453 | 2946 | 26.67 | 267
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 10722 | TRUE | 937.9448 | 937.9448 | 0.58294 | 9 | 0.00040174 | 68 | 0.066431 | 3060 | 2.67e-05 | 0.00024019 | 2947 | 14.01 | 358
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | L510R | FALSE | 15698.8958 | 15538.9501 | 9.6575 | 136 | 8.24e-05 | 2142 | 0.24129 | 2927 | 2.62e-05 | 0.0035575 | 2948 | 0.21 | 1146
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 781318 | TRUE | 172.1377 | 172.1377 | 0.10698 | 3 | 0.00038201 | 74 | 0.066431 | 3034 | 2.54e-05 | 7.6132e-05 | 2949 |  | 3210
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 53544 | FALSE | 1728.2043 | 1035.1182 | 0.64333 | 19 | 0.00038613 | 71 | 0.06569 | 3314 | 2.53e-05 | 0.00048097 | 2950 |  | 2807
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | CB | TRUE | 10480.8911 | 272.5459 | 0.16939 | 83 | 4.14e-05 | 3235 | 0.25769 | 2926 | 2.52e-05 | 0.0020921 | 2951 | 5.67 | 480
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5146 | FALSE | 9534.7408 | 9534.7408 | 5.9259 | 63 | 0.00036971 | 78 | 0.066431 | 3063 | 2.46e-05 | 0.0015473 | 2952 | 0.55 | 870
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 837904 | FALSE | 3252.9939 | 1669.2171 | 1.0374 | 25 | 3.83e-05 | 3293 | 0.69841 | 2909 | 2.44e-05 | 0.00061089 | 2953 |  | 2930
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 961990 | FALSE | 10972.2602 | 10972.2602 | 6.8193 | 91 | 0.00035642 | 85 | 0.066431 | 3018 | 2.37e-05 | 0.0021547 | 2954 |  | 2984
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 772517 | FALSE | 2777.244 | 2777.244 | 1.7261 | 24 | 0.00035423 | 87 | 0.066378 | 3129 | 2.35e-05 | 0.00056446 | 2955 |  | 3281
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | CB | FALSE | 12509.5528 | 12509.5528 | 7.7747 | 106 | 0.00034662 | 93 | 0.066431 | 3076 | 2.3e-05 | 0.0024408 | 2956 | 1.58 | 665
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 528232 | TRUE | 149.6502 | 149.6502 | 0.093008 | 2 | 0.00033485 | 99 | 0.066432 | 3013 | 2.22e-05 | 4.449e-05 | 2957 |  | 3604
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | CB | TRUE | 149.4178 | 149.4178 | 0.092864 | 2 | 0.00033388 | 100 | 0.066432 | 3002 | 2.22e-05 | 4.436e-05 | 2958 | 0.05 | 1937
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | V84 | TRUE | 15879.9521 | 369.7837 | 0.22982 | 126 | 7.21e-06 | 3627 | 0.37923 | 2921 | 2.18e-05 | 0.0027508 | 2959 |  | 2861
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | CB | FALSE | 2249.8408 | 2245.2688 | 1.3954 | 16 | 0.00032886 | 103 | 0.066351 | 3136 | 2.18e-05 | 0.00034924 | 2960 | 0.1 | 1487
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 39126 | FALSE | 3634.7812 | 3634.7812 | 2.259 | 31 | 0.00031627 | 110 | 0.066431 | 3079 | 2.1e-05 | 0.00065131 | 2961 | 15.84 | 344
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 834583 | TRUE | 981.0329 | 981.0329 | 0.60972 | 7 | 0.00030071 | 130 | 0.066431 | 3073 | 2e-05 | 0.00013984 | 2962 | 4.09 | 528
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 737512 | FALSE | 11180.7592 | 10917.3933 | 6.7852 | 89 | 0.0002931 | 137 | 0.066402 | 3118 | 1.95e-05 | 0.0017324 | 2963 |  | 3008
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 11384 | FALSE | 8402.4777 | 8402.4777 | 5.2222 | 59 | 0.00028937 | 140 | 0.066431 | 3069 | 1.92e-05 | 0.0011342 | 2964 | 13.77 | 362
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 762780 | TRUE | 1282.4551 | 400.767 | 0.24908 | 11 | 0.0002944 | 135 | 0.065383 | 3424 | 1.92e-05 | 0.00021145 | 2965 |  | 3209
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 262343 | FALSE | 1232.8709 | 1232.8709 | 0.76623 | 11 | 0.00028891 | 143 | 0.066432 | 3003 | 1.92e-05 | 0.00021112 | 2966 |  | 3404
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 9741 | FALSE | 1036.4661 | 1036.4661 | 0.64417 | 10 | 0.00028291 | 149 | 0.066431 | 3057 | 1.88e-05 | 0.00018794 | 2967 | 14.27 | 356
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5028 | FALSE | 8087.7219 | 8087.7219 | 5.0266 | 59 | 0.00027873 | 160 | 0.066431 | 3056 | 1.85e-05 | 0.0010925 | 2968 | 0.63 | 832
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 851116 | TRUE | 405.8442 | 316.0008 | 0.1964 | 4 | 0.00027959 | 155 | 0.066111 | 3190 | 1.85e-05 | 7.3835e-05 | 2969 |  | 2981
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 926235 | TRUE | 416.1419 | 305.3669 | 0.18979 | 4 | 0.00027977 | 153 | 0.065791 | 3274 | 1.84e-05 | 7.3487e-05 | 2970 |  | 3532
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 981056 | TRUE | 227.7546 | 132.017 | 0.082049 | 2 | 0.00027805 | 163 | 0.065789 | 3285 | 1.83e-05 | 3.6518e-05 | 2971 |  | 3476
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 99658 | TRUE | 4406.3905 | 0 | 0 | 39 | 0.00027979 | 152 | 0.06515 | 3578 | 1.82e-05 | 0.0007109 | 2972 | 0.05 | 2030
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 78862 | TRUE | 1804.4635 | 123.6088 | 0.076823 | 17 | 0.00027938 | 158 | 0.065225 | 3497 | 1.82e-05 | 0.00030962 | 2973 | 5.76 | 478
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 12584 | FALSE | 41638.8897 | 5651.1648 | 3.5122 | 297 | 5.99e-05 | 2779 | 0.22529 | 2929 | 1.82e-05 | 0.0054019 | 2974 | 0.03 | 2245
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | V72 | FALSE | 14155.2453 | 9610.0836 | 5.9727 | 101 | 2.69e-05 | 3473 | 1.494 | 2866 | 1.81e-05 | 0.0018297 | 2975 | 0.05 | 1974
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 11006 | FALSE | 3281.0215 | 3281.0215 | 2.0392 | 24 | 0.00027097 | 170 | 0.066431 | 3059 | 1.8e-05 | 0.00043202 | 2976 | 0.37 | 965
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 32.8824 | 32.8824 | 0.020437 | 1 | 0.00026849 | 175 | 0.066431 | 3046 | 1.78e-05 | 1.7836e-05 | 2977 |  | 3493
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | CB | TRUE | 221.0797 | 221.0797 | 0.1374 | 2 | 0.0002671 | 177 | 0.066431 | 3047 | 1.77e-05 | 3.5488e-05 | 2978 | 0.03 | 2339
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 710556 | TRUE | 81.8649 | 65.863 | 0.040934 | 2 | 0.00026928 | 174 | 0.065792 | 3269 | 1.77e-05 | 3.5324e-05 | 2979 |  | 3566
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 958726 | FALSE | 1647.4395 | 1605.4653 | 0.9978 | 13 | 0.00026566 | 180 | 0.066333 | 3140 | 1.76e-05 | 0.00022904 | 2980 |  | 2975
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 5401 | FALSE | 4047.5171 | 4047.5171 | 2.5155 | 34 | 0.0002635 | 187 | 0.066431 | 3064 | 1.75e-05 | 0.00059516 | 2981 | 18.02 | 327
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | CB | TRUE | 158.4451 | 158.4451 | 0.098474 | 2 | 0.00026209 | 192 | 0.066431 | 3100 | 1.74e-05 | 3.4822e-05 | 2982 | 0.02 | 2438
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 1064 | FALSE | 7144.3316 | 1005.39 | 0.62485 | 51 | 5.22e-05 | 2989 | 0.37559 | 2922 | 1.74e-05 | 0.00088693 | 2983 | 0.02 | 2426
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 761310 | TRUE | 43.1053 | 43.1053 | 0.02679 | 1 | 0.00026016 | 195 | 0.066432 | 3006 | 1.73e-05 | 1.7283e-05 | 2984 | 9.94 | 403
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 5232 | FALSE | 7264.9547 | 7264.9547 | 4.5152 | 50 | 0.00025977 | 196 | 0.066431 | 3065 | 1.73e-05 | 0.00086284 | 2985 | 0.52 | 889
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 956424 | FALSE | 2618.2583 | 1661.8272 | 1.0328 | 21 | 0.00026235 | 190 | 0.065882 | 3247 | 1.72e-05 | 0.00036171 | 2986 |  | 3301
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 10786 | FALSE | 7392.1952 | 7392.1952 | 4.5943 | 58 | 0.00025715 | 199 | 0.066431 | 3068 | 1.71e-05 | 0.0009908 | 2987 | 23.31 | 288
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 11048 | FALSE | 2138.5875 | 1473.7073 | 0.91592 | 19 | 0.00025575 | 204 | 0.065825 | 3261 | 1.69e-05 | 0.00032099 | 2988 | 0.22 | 1122
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 100040 | FALSE | 1340.2293 | 1324.2274 | 0.82301 | 7 | 0.00025542 | 205 | 0.065698 | 3313 | 1.68e-05 | 0.00011745 | 2989 |  | 3490
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 74170 | FALSE | 5752.9394 | 5752.9394 | 3.5755 | 43 | 0.00025227 | 211 | 0.066431 | 3071 | 1.68e-05 | 0.00072063 | 2990 | 54.65 | 106
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | CB | TRUE | 89.3518 | 89.3518 | 0.055533 | 2 | 0.0002491 | 218 | 0.066431 | 3102 | 1.65e-05 | 3.3096e-05 | 2991 | 0.02 | 2430
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 19732 | FALSE | 14898.6258 | 14898.6258 | 9.2596 | 125 | 0.00024625 | 229 | 0.066432 | 3015 | 1.64e-05 | 0.0020448 | 2992 | 0.39 | 954
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 11044 | FALSE | 19649.9105 | 12291.7272 | 7.6394 | 144 | 0.00024668 | 228 | 0.06589 | 3246 | 1.63e-05 | 0.0023496 | 2993 | 0.26 | 1067
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 357568 | FALSE | 3842.9954 | 1927.7671 | 1.1981 | 35 | 0.00024621 | 230 | 0.065663 | 3320 | 1.62e-05 | 0.0005675 | 2994 |  | 2905
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 2651 | FALSE | 1316.7963 | 1238.5246 | 0.76975 | 10 | 0.00024324 | 237 | 0.066303 | 3149 | 1.61e-05 | 0.00016143 | 2995 | 0.05 | 1964
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 837 | FALSE | 2514.1986 | 1083.651 | 0.67349 | 22 | 0.00024512 | 232 | 0.065733 | 3299 | 1.61e-05 | 0.00035514 | 2996 | 0.03 | 2298
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 7401 | FALSE | 1710.0336 | 1710.0336 | 1.0628 | 12 | 0.00023873 | 251 | 0.066431 | 3026 | 1.59e-05 | 0.00019031 | 2997 | 5.59 | 483
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 9773 | TRUE | 724.8545 | 724.8545 | 0.4505 | 6 | 0.00023796 | 254 | 0.066431 | 3077 | 1.58e-05 | 9.4849e-05 | 2998 | 6.09 | 473
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 95576 | TRUE | 3539.5092 | 0 | 0 | 30 | 0.00024199 | 240 | 0.06515 | 3580 | 1.58e-05 | 0.00047296 | 2999 | 0.02 | 2521
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 234378 | FALSE | 1230.3375 | 1030.7217 | 0.6406 | 13 | 0.00023818 | 253 | 0.065939 | 3237 | 1.57e-05 | 0.00020445 | 3000 |  | 2969
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 11004 | FALSE | 6981.3249 | 6981.3249 | 4.3389 | 60 | 0.000234 | 264 | 0.066431 | 3053 | 1.55e-05 | 0.00093268 | 3001 | 0.81 | 772
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 296428 | FALSE | 5326.8427 | 2768.6124 | 1.7207 | 14 | 0.00023533 | 262 | 0.065703 | 3308 | 1.55e-05 | 0.00021688 | 3002 |  | 3554
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | CB | TRUE | 6762.3674 | 0 | 0 | 59 | 0.00023708 | 256 | 0.065169 | 3547 | 1.54e-05 | 0.00091153 | 3003 |  | 3195
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 50008 | FALSE | 7897.7178 | 1828.8508 | 1.1366 | 64 | 0.00023509 | 263 | 0.06535 | 3436 | 1.54e-05 | 0.0009841 | 3004 | 0.7 | 810
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 910235 | TRUE | 1774.1223 | 851.0444 | 0.52893 | 16 | 0.00023372 | 267 | 0.065631 | 3328 | 1.53e-05 | 0.00024453 | 3005 |  | 2923
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | LC26 | FALSE | 9057.4757 | 9057.4757 | 5.6293 | 74 | 0.00022734 | 294 | 0.066432 | 2991 | 1.51e-05 | 0.0011176 | 3006 | 0.12 | 1372
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | CB | FALSE | 2889.8933 | 1390.1141 | 0.86396 | 28 | 0.0002292 | 288 | 0.065745 | 3295 | 1.5e-05 | 0.00042097 | 3007 | 0.09 | 1554
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | CB | TRUE | 9322.594 | 131.7629 | 0.081891 | 81 | 0.00022849 | 289 | 0.065197 | 3511 | 1.49e-05 | 0.0012064 | 3008 |  | 2874
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 64682 | FALSE | 2835.1135 | 2835.1135 | 1.762 | 22 | 0.00022403 | 304 | 0.066431 | 3092 | 1.49e-05 | 0.00032742 | 3009 | 46.82 | 138
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 841 | FALSE | 1307.0396 | 1307.0396 | 0.81233 | 12 | 0.00022352 | 305 | 0.066431 | 3027 | 1.48e-05 | 0.00017819 | 3010 | 0.34 | 982
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 546438 | FALSE | 1552.7497 | 1541.3848 | 0.95798 | 14 | 0.00022139 | 313 | 0.066248 | 3162 | 1.47e-05 | 0.00020577 | 3011 |  | 3363
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 4913 | FALSE | 6065.3094 | 6065.3094 | 3.7696 | 54 | 1.98e-05 | 3546 | 0.94688 | 2897 | 1.46e-05 | 0.00079082 | 3012 | 0.02 | 2519
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | CR346 | TRUE | 330.9469 | 330.9469 | 0.20568 | 3 | 0.00021988 | 322 | 0.066432 | 2961 | 1.46e-05 | 4.3821e-05 | 3013 | 0.27 | 1053
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 19562 | FALSE | 11663.8965 | 11663.8965 | 7.2492 | 98 | 0.00021832 | 327 | 0.066431 | 3051 | 1.45e-05 | 0.0014213 | 3014 | 80.06 | 48
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | LA42 | FALSE | 4459.4554 | 4459.4554 | 2.7716 | 35 | 0.00021752 | 329 | 0.066431 | 3062 | 1.45e-05 | 0.00050575 | 3015 | 0.48 | 904
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 975350 | TRUE | 405.3394 | 73.1065 | 0.045436 | 3 | 0.00015577 | 686 | 0.090462 | 2933 | 1.43e-05 | 4.2852e-05 | 3016 |  | 3591
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | CB | FALSE | 2054.39 | 1346.787 | 0.83703 | 15 | 0.00021376 | 344 | 0.065919 | 3239 | 1.41e-05 | 0.00021149 | 3017 | 0.16 | 1250
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 920850 | TRUE | 514.6425 | 322.1994 | 0.20025 | 3 | 0.00021514 | 340 | 0.065576 | 3348 | 1.41e-05 | 4.2181e-05 | 3018 |  | 3600
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 8611 | FALSE | 2893.9317 | 2893.9317 | 1.7986 | 22 | 0.00020875 | 367 | 0.066432 | 3005 | 1.39e-05 | 0.00030508 | 3019 | 0.05 | 1987
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 2043 | TRUE | 902.2238 | 902.2238 | 0.56074 | 8 | 0.00020837 | 369 | 0.066431 | 3028 | 1.38e-05 | 0.00011074 | 3020 | 28.28 | 251
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 1247 | TRUE | 443.4693 | 443.4693 | 0.27562 | 3 | 0.00020644 | 376 | 0.066431 | 3039 | 1.37e-05 | 4.1142e-05 | 3021 | 45.01 | 152
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 661309 | TRUE | 2205.0428 | 453.7966 | 0.28204 | 16 | 0.00020886 | 365 | 0.065469 | 3383 | 1.37e-05 | 0.00021867 | 3022 |  | 3369
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 600529 | TRUE | 435.4123 | 422.8048 | 0.26277 | 4 | 0.00020229 | 388 | 0.066112 | 3188 | 1.34e-05 | 5.3422e-05 | 3023 |  | 3471
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 968601 | TRUE | 12.2398 | 12.2398 | 0.0076071 | 1 | 0.00020045 | 395 | 0.066431 | 3041 | 1.33e-05 | 1.3316e-05 | 3024 |  | 3573
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5696 | FALSE | 9835.0739 | 8152.2263 | 5.0666 | 90 | 0.00020042 | 396 | 0.066175 | 3179 | 1.33e-05 | 0.0011939 | 3025 | 0.11 | 1418
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 216442 | TRUE | 327.4361 | 327.4361 | 0.2035 | 4 | 0.00012382 | 1123 | 0.10422 | 2932 | 1.29e-05 | 5.1625e-05 | 3026 |  | 3403
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 7181 | FALSE | 1244.1443 | 1244.1443 | 0.77324 | 11 | 0.00019333 | 428 | 0.066432 | 3010 | 1.28e-05 | 0.00014128 | 3027 | 7.1 | 450
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 7603 | FALSE | 1527.2306 | 1527.2306 | 0.94918 | 11 | 0.00019238 | 431 | 0.066431 | 3055 | 1.28e-05 | 0.00014058 | 3028 | 0.27 | 1054
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | LC24 | FALSE | 18535.4178 | 13258.5886 | 8.2403 | 154 | 0.00019316 | 429 | 0.066006 | 3215 | 1.27e-05 | 0.001963 | 3029 | 0.08 | 1601
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 83424 | FALSE | 2603.9122 | 2600.4486 | 1.6162 | 7 | 0.00018902 | 446 | 0.066249 | 3161 | 1.25e-05 | 8.7822e-05 | 3030 | 8.82 | 419
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 16000 | FALSE | 6212.4721 | 3353.5945 | 2.0843 | 51 | 0.000189 | 448 | 0.065804 | 3266 | 1.25e-05 | 0.0006373 | 3031 | 13.79 | 361
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | CB | TRUE | 26.6683 | 26.6683 | 0.016574 | 1 | 0.00018686 | 464 | 0.066431 | 3104 | 1.24e-05 | 1.2413e-05 | 3032 | 0.2 | 1169
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 344092 | TRUE | 131.1041 | 115.3192 | 0.071671 | 2 | 0.00018617 | 465 | 0.066431 | 3037 | 1.24e-05 | 2.4736e-05 | 3033 |  | 3598
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 208930 | TRUE | 1425.5586 | 187.1265 | 0.1163 | 10 | 0.00018882 | 449 | 11.1381 | 2605 | 1.23e-05 | 0.00012302 | 3034 |  | 2804
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 11172 | FALSE | 3921.2737 | 3218.2333 | 2.0001 | 38 | 0.00018146 | 501 | 0.066162 | 3181 | 1.2e-05 | 0.00045611 | 3035 | 0.11 | 1424
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | CB | TRUE | 408.9065 | 408.9065 | 0.25414 | 4 | 0.0001783 | 516 | 0.066431 | 3029 | 1.18e-05 | 4.7378e-05 | 3036 | 13.33 | 366
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | LA46 | FALSE | 2411.7925 | 2411.7925 | 1.4989 | 20 | 0.00017603 | 522 | 0.066431 | 3058 | 1.17e-05 | 0.00023387 | 3037 | 19.55 | 311
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 463510 | FALSE | 4881.4666 | 4697.8741 | 2.9197 | 41 | 0.0001755 | 524 | 0.066369 | 3132 | 1.16e-05 | 0.00047756 | 3038 |  | 3239
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 8898 | FALSE | 1034.8013 | 1034.8013 | 0.64313 | 9 | 0.00017399 | 534 | 0.066431 | 3061 | 1.16e-05 | 0.00010403 | 3039 | 0.71 | 804
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | MR359 | TRUE | 10891.9524 | 0 | 0 | 90 | 2.53e-05 | 3493 | 0.41659 | 2914 | 1.15e-05 | 0.0010328 | 3040 |  | 2849
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 92868 | TRUE | 1050.3516 | 203.5363 | 0.1265 | 14 | 0.00017449 | 531 | 0.065522 | 3360 | 1.14e-05 | 0.0001602 | 3041 | 0.39 | 955
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 391688 | FALSE | 2071.721 | 2071.721 | 1.2876 | 16 | 0.00017212 | 549 | 0.066431 | 3109 | 1.14e-05 | 0.00018295 | 3042 |  | 2694
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 55638 | FALSE | 5639.9215 | 2949.5648 | 1.8332 | 42 | 0.00017356 | 537 | 0.065698 | 3312 | 1.14e-05 | 0.00047946 | 3043 | 0.27 | 1049
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | W503R | TRUE | 12304.5424 | 121.8736 | 0.075745 | 89 | 2e-05 | 3544 | 0.42059 | 2913 | 1.14e-05 | 0.0010113 | 3044 |  | 2765
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 409224 | TRUE | 353.3451 | 138.7205 | 0.086215 | 4 | 0.0001558 | 685 | 0.071835 | 2942 | 1.13e-05 | 4.524e-05 | 3045 |  | 3518
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 38684 | TRUE | 100.1157 | 38.3974 | 0.023864 | 1 | 0.00017305 | 542 | 0.065149 | 3581 | 1.13e-05 | 1.1274e-05 | 3046 | 0.02 | 2437
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 506 | FALSE | 2021.7882 | 2021.7882 | 1.2565 | 18 | 0.00016864 | 571 | 0.066431 | 3019 | 1.12e-05 | 0.00020165 | 3047 | 19.11 | 314
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 2299 | FALSE | 2927.8178 | 2927.8178 | 1.8197 | 25 | 0.00016866 | 570 | 0.06638 | 3127 | 1.12e-05 | 0.00027996 | 3048 | 3.04 | 566
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 8752 | FALSE | 2987.795 | 2987.795 | 1.8569 | 32 | 0.00016401 | 600 | 0.066391 | 3124 | 1.09e-05 | 0.00034845 | 3049 | 0.14 | 1308
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 10946 | FALSE | 13600.904 | 9098.3132 | 5.6546 | 112 | 0.00016435 | 595 | 0.06595 | 3235 | 1.09e-05 | 0.0012153 | 3050 | 0.4 | 945
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | CR214 | FALSE | 4637.1496 | 4637.1496 | 2.882 | 35 | 0.00016318 | 609 | 0.066431 | 3098 | 1.08e-05 | 0.00037942 | 3051 | 26.71 | 265
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | CR288 | FALSE | 4382.4988 | 4382.4988 | 2.7237 | 46 | 0.00016279 | 615 | 0.066431 | 3090 | 1.08e-05 | 0.00049744 | 3052 | 0.78 | 779
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | CR022 | FALSE | 6467.1642 | 6467.1642 | 4.0194 | 48 | 0.00016153 | 625 | 0.066431 | 3103 | 1.07e-05 | 0.00051505 | 3053 | 12.67 | 369
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 1101/2 | TRUE | 31.1897 | 31.1897 | 0.019385 | 1 | 0.00016141 | 627 | 0.066431 | 3050 | 1.07e-05 | 1.0723e-05 | 3054 |  | 3431
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 496570 | TRUE | 701.3537 | 389.3118 | 0.24196 | 8 | 0.00016262 | 617 | 0.065632 | 3327 | 1.07e-05 | 8.5734e-05 | 3055 |  | 3421
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 250 | FALSE | 1985.3414 | 1985.3414 | 1.2339 | 14 | 0.0001605 | 639 | 0.066431 | 3020 | 1.07e-05 | 0.00014927 | 3056 | 12.63 | 371
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 390720 | TRUE | 218.4469 | 202.4448 | 0.12582 | 2 | 0.00015881 | 655 | 0.066432 | 2955 | 1.05e-05 | 2.11e-05 | 3057 |  | 3617
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 1262 | FALSE | 7115.8815 | 6311.248 | 3.9225 | 57 | 0.00015861 | 656 | 0.066252 | 3160 | 1.05e-05 | 0.00060016 | 3058 | 0.45 | 914
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 250129 | TRUE | 467.9989 | 401.6728 | 0.24964 | 5 | 0.00015745 | 668 | 0.066432 | 2964 | 1.05e-05 | 5.23e-05 | 3059 |  | 3307
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | CB | FALSE | 3786.5637 | 1101.4532 | 0.68456 | 37 | 0.00015882 | 654 | 0.065393 | 3421 | 1.04e-05 | 0.00038468 | 3060 | 0.08 | 1623
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 451760 | TRUE | 98.2563 | 98.2563 | 0.061067 | 2 | 0.000155 | 694 | 0.066432 | 2956 | 1.03e-05 | 2.0595e-05 | 3061 |  | 3571
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 210 | FALSE | 12611.9142 | 10477.8716 | 6.512 | 107 | 0.00015483 | 696 | 0.066181 | 3174 | 1.03e-05 | 0.0010973 | 3062 | 0.61 | 845
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 79118 | TRUE | 31.1564 | 31.1564 | 0.019364 | 2 | 0.00015411 | 704 | 0.066431 | 3084 | 1.02e-05 | 2.0475e-05 | 3063 | 13.07 | 367
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 212 | FALSE | 3618.1725 | 3618.1725 | 2.2487 | 27 | 0.00015405 | 705 | 0.066431 | 3024 | 1.02e-05 | 0.00027631 | 3064 | 26.95 | 263
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 1625 | FALSE | 1400.9701 | 1400.9701 | 0.87071 | 10 | 0.00015401 | 706 | 0.066431 | 3067 | 1.02e-05 | 0.00010231 | 3065 | 45.14 | 150
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 104220 | FALSE | 5237.7249 | 1476.8749 | 0.91788 | 45 | 0.00015541 | 691 | 0.065461 | 3392 | 1.02e-05 | 0.00045796 | 3066 |  | 3107
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | CB | FALSE | 12682.0012 | 7810.3005 | 4.8541 | 107 | 0.00015094 | 728 | 0.065845 | 3256 | 9.99e-06 | 0.0010689 | 3067 | 0.33 | 987
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | CR204 | FALSE | 6639.5298 | 6639.5298 | 4.1265 | 49 | 0.00015005 | 734 | 0.066431 | 3107 | 9.97e-06 | 0.00048842 | 3068 | 0.48 | 901
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | CB | TRUE | 191.1806 | 191.1806 | 0.11882 | 2 | 0.00014987 | 738 | 0.066432 | 3011 | 9.96e-06 | 1.9912e-05 | 3069 | 0.03 | 2348
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | CR178 | TRUE | 529.8862 | 529.8862 | 0.32933 | 7 | 0.00014846 | 758 | 0.066432 | 2953 | 9.86e-06 | 6.9036e-05 | 3070 | 0.29 | 1028
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | CB | TRUE | 14599.8126 | 271.1511 | 0.16852 | 108 | 0.0001338 | 947 | 0.073352 | 2938 | 9.84e-06 | 0.0010632 | 3071 | 0.04 | 2189
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 51474 | TRUE | 7519.049 | 594.1189 | 0.36925 | 68 | 0.00015085 | 730 | 0.065188 | 3526 | 9.84e-06 | 0.00066905 | 3072 | 0.02 | 2433
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 932140 | TRUE | 1542.2382 | 861.7057 | 0.53555 | 15 | 0.00014685 | 774 | 0.065836 | 3258 | 9.67e-06 | 0.00014504 | 3073 |  | 2908
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | CB | TRUE | 11988.7275 | 167.7195 | 0.10424 | 114 | 0.00014824 | 761 | 0.06517 | 3545 | 9.66e-06 | 0.0011016 | 3074 | 0.07 | 1673
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 532 | TRUE | 844.3261 | 844.3261 | 0.52475 | 8 | 0.00014487 | 803 | 0.066431 | 3021 | 9.62e-06 | 7.6993e-05 | 3075 | 27.34 | 259
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | CB | FALSE | 3812.8299 | 1129.2677 | 0.70184 | 32 | 0.000146 | 789 | 0.06551 | 3366 | 9.57e-06 | 0.00030616 | 3076 | 0.04 | 2130
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 6129 | FALSE | 5155.4944 | 5155.4944 | 3.2042 | 39 | 0.0001435 | 819 | 0.066432 | 3007 | 9.53e-06 | 0.00037178 | 3077 | 0.06 | 1793
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | CB | TRUE | 35.3815 | 35.3815 | 0.02199 | 1 | 0.00014293 | 826 | 0.066432 | 2990 | 9.5e-06 | 9.4951e-06 | 3078 | 0.05 | 1945
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | CB | FALSE | 22008.731 | 1759.2867 | 1.0934 | 102 | 0.00014538 | 799 | 0.065157 | 3559 | 9.47e-06 | 0.0009662 | 3079 | 0.03 | 2325
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 5026 | FALSE | 2967.0616 | 2967.0616 | 1.844 | 23 | 0.00014253 | 832 | 0.066431 | 3023 | 9.47e-06 | 0.00021778 | 3080 | 0.35 | 976
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 379946 | FALSE | 2891.0032 | 1211.8313 | 0.75316 | 15 | 0.00014448 | 805 | 0.06515 | 3577 | 9.41e-06 | 0.0001412 | 3081 |  | 3120
8927 | ELK 1101CB | 42981101 | ELK 1101 | CB | TRUE | 39.9198 | 39.9198 | 0.02481 | 1 | 0.0001444 | 807 | 0.065148 | 3597 | 9.41e-06 | 9.4072e-06 | 3082 | 0.01 | 2574
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 296476 | FALSE | 1196.6443 | 1061.0328 | 0.65944 | 11 | 0.00014203 | 839 | 0.065849 | 3254 | 9.4e-06 | 0.00010339 | 3083 |  | 3030
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 297538 | FALSE | 1703.5587 | 1703.5587 | 1.0588 | 15 | 0.000141 | 854 | 0.066432 | 3014 | 9.37e-06 | 0.0001405 | 3084 |  | 3160
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 337226 | TRUE | 1293.8077 | 458.4827 | 0.28495 | 13 | 0.00014222 | 835 | 0.065742 | 3297 | 9.36e-06 | 0.0001217 | 3085 |  | 2998
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | CB | TRUE | 10759.641 | 358.8557 | 0.22303 | 85 | 0.00014251 | 833 | 0.065166 | 3549 | 9.29e-06 | 0.00078931 | 3086 | 0.26 | 1071
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 51478 | TRUE | 90.198 | 81.0541 | 0.050375 | 3 | 0.00014054 | 863 | 0.065577 | 3343 | 9.25e-06 | 2.7745e-05 | 3087 | 1.23 | 697
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | CB | FALSE | 11489.4556 | 2237.7238 | 1.3908 | 99 | 0.00014106 | 853 | 0.065344 | 3440 | 9.23e-06 | 0.00091369 | 3088 | 0.02 | 2562
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | BR166 | TRUE | 61.4345 | 61.4345 | 0.038182 | 2 | 0.00013883 | 886 | 0.066432 | 2952 | 9.22e-06 | 1.8446e-05 | 3089 | 0.05 | 1939
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | CB | TRUE | 10445.4547 | 0 | 0 | 86 | 0.00014143 | 846 | 0.065148 | 3602 | 9.21e-06 | 0.0007924 | 3090 | 0.28 | 1040
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 241646 | TRUE | 2237.0921 | 583.4204 | 0.3626 | 13 | 0.00014029 | 866 | 0.065148 | 3600 | 9.14e-06 | 0.00011881 | 3091 |  | 3536
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 91742 | FALSE | 7594.7858 | 3844.7445 | 2.3895 | 67 | 0.00013708 | 906 | 0.065724 | 3302 | 9.02e-06 | 0.00060425 | 3092 | 0.12 | 1387
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 3820 | TRUE | 23262.4232 | 0 | 0 | 115 | 0.0001364 | 914 | 0.065808 | 3265 | 8.99e-06 | 0.0010334 | 3093 | 0.02 | 2422
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 209146 | FALSE | 9672.039 | 4936.2554 | 3.0679 | 85 | 0.00013627 | 917 | 0.065797 | 3267 | 8.97e-06 | 0.00076238 | 3094 |  | 2810
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 1780 | TRUE | 115.3297 | 115.3297 | 0.071678 | 1 | 0.00013489 | 928 | 0.06643 | 3113 | 8.96e-06 | 8.9608e-06 | 3095 | 0.87 | 761
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 328808 | TRUE | 186.4686 | 186.4686 | 0.11589 | 1 | 0.00013477 | 930 | 0.066432 | 2960 | 8.95e-06 | 8.9528e-06 | 3096 |  | 3574
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 6219 | FALSE | 1488.6262 | 1488.6262 | 0.92519 | 11 | 0.00013222 | 978 | 0.066431 | 3066 | 8.78e-06 | 9.6619e-05 | 3097 | 7 | 455
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 184814 | TRUE | 2352.3551 | 682.245 | 0.42402 | 20 | 0.00013241 | 973 | 0.065475 | 3379 | 8.71e-06 | 0.00017414 | 3098 |  | 2762
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 832694 | TRUE | 477.5655 | 461.5634 | 0.28686 | 5 | 0.0001169 | 1251 | 0.073805 | 2937 | 8.71e-06 | 4.3529e-05 | 3099 |  | 3535
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 35934 | TRUE | 5459.9113 | 78.4109 | 0.048733 | 46 | 0.00013282 | 962 | 0.065203 | 3509 | 8.67e-06 | 0.00039862 | 3100 |  | 2806
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 490728 | FALSE | 1414.5018 | 1044.2482 | 0.649 | 11 | 0.00013128 | 992 | 0.065966 | 3228 | 8.66e-06 | 9.5291e-05 | 3101 |  | 2925
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 798018 | FALSE | 1485.4108 | 1448.3137 | 0.90013 | 13 | 0.0001303 | 1006 | 0.066234 | 3166 | 8.64e-06 | 0.00011235 | 3102 |  | 3340
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | CB | TRUE | 1752.4587 | 342.98 | 0.21316 | 11 | 0.00013264 | 969 | 0.065147 | 3621 | 8.64e-06 | 9.5055e-05 | 3103 |  | 3350
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 894156 | TRUE | 625.3701 | 625.3701 | 0.38867 | 4 | 0.0001303 | 1005 | 0.066111 | 3196 | 8.61e-06 | 3.4444e-05 | 3104 |  | 3450
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 718674 | FALSE | 1848.6771 | 1301.8094 | 0.80908 | 16 | 0.0001305 | 1001 | 0.065951 | 3233 | 8.61e-06 | 0.00013775 | 3105 |  | 3168
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 610322 | TRUE | 220.6867 | 220.6867 | 0.13716 | 3 | 0.00012983 | 1012 | 0.066004 | 3217 | 8.59e-06 | 2.578e-05 | 3106 |  | 3607
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 9658 | TRUE | 156.0125 | 156.0125 | 0.096962 | 3 | 0.00012787 | 1049 | 0.066432 | 2984 | 8.49e-06 | 2.5485e-05 | 3107 | 0.04 | 2071
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | CR206 | FALSE | 2877.1568 | 2877.1568 | 1.7882 | 22 | 0.00012717 | 1061 | 0.066431 | 3108 | 8.45e-06 | 0.00018585 | 3108 | 0.28 | 1042
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 5291 | TRUE | 1596.261 | 50.439 | 0.031348 | 14 | 0.00012858 | 1037 | 0.065239 | 3485 | 8.42e-06 | 0.00011792 | 3109 |  | 3053
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 5404 | FALSE | 7456.6431 | 4377.7978 | 2.7208 | 63 | 0.00012738 | 1057 | 0.065779 | 3291 | 8.41e-06 | 0.00053014 | 3110 | 0.15 | 1284
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 205854 | TRUE | 505.1079 | 505.1079 | 0.31393 | 5 | 0.00012714 | 1063 | 0.065923 | 3238 | 8.37e-06 | 4.1826e-05 | 3111 |  | 3625
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 5402 | FALSE | 10826.3428 | 4595.9767 | 2.8564 | 87 | 0.0001269 | 1066 | 0.065546 | 3353 | 8.32e-06 | 0.00072413 | 3112 | 0.19 | 1181
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 431214 | TRUE | 794.6731 | 500.3272 | 0.31096 | 9 | 0.00012639 | 1076 | 0.065861 | 3253 | 8.31e-06 | 7.4772e-05 | 3113 |  | 3396
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 158468 | FALSE | 1388.9106 | 1120.0792 | 0.69613 | 11 | 0.00012572 | 1083 | 0.066083 | 3201 | 8.31e-06 | 9.1369e-05 | 3114 |  | 3084
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 816 | FALSE | 4123.7572 | 3941.7419 | 2.4498 | 29 | 0.00012427 | 1112 | 0.066299 | 3150 | 8.24e-06 | 0.00023898 | 3115 | 0.05 | 2024
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | N510R | TRUE | 1403.237 | 401.7471 | 0.24969 | 15 | 0.00012562 | 1086 | 0.065412 | 3409 | 8.22e-06 | 0.00012333 | 3116 | 0.19 | 1183
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 798032 | TRUE | 259.8305 | 244.5065 | 0.15196 | 2 | 0.00012449 | 1108 | 0.065789 | 3287 | 8.2e-06 | 1.6394e-05 | 3117 |  | 3569
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 2062 | FALSE | 8420.6852 | 2556.2544 | 1.5887 | 83 | 0.00012402 | 1119 | 0.065581 | 3338 | 8.16e-06 | 0.00067739 | 3118 | 0.04 | 2221
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 1457 | FALSE | 1229.3805 | 1229.3805 | 0.76406 | 9 | 0.00012274 | 1137 | 0.066431 | 3025 | 8.15e-06 | 7.3385e-05 | 3119 | 0.27 | 1047
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 967039 | TRUE | 469.6042 | 292.9124 | 0.18205 | 3 | 0.00012406 | 1117 | 0.065578 | 3342 | 8.14e-06 | 2.4417e-05 | 3120 |  | 3394
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | CR102 | TRUE | 316.3322 | 316.3322 | 0.1966 | 6 | 0.00012168 | 1153 | 0.066431 | 3101 | 8.08e-06 | 4.8501e-05 | 3121 | 0.08 | 1651
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 960240 | TRUE | 816.2732 | 816.2732 | 0.50732 | 5 | 0.00012223 | 1144 | 0.066176 | 3175 | 8.08e-06 | 4.0394e-05 | 3122 |  | 3597
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 531976 | FALSE | 2102.4835 | 2102.4835 | 1.3067 | 17 | 0.00012078 | 1169 | 0.066431 | 3080 | 8.02e-06 | 0.0001364 | 3123 |  | 3322
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 36.9839 | 36.9839 | 0.022986 | 1 | 0.00012061 | 1175 | 0.066431 | 3045 | 8.01e-06 | 8.0126e-06 | 3124 |  | 3540
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 284356 | TRUE | 325.8775 | 218.127 | 0.13557 | 4 | 0.00012158 | 1155 | 0.066111 | 3192 | 7.99e-06 | 3.1961e-05 | 3125 |  | 3341
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | CR101 | TRUE | 28.3921 | 28.3921 | 0.017646 | 1 | 0.00011894 | 1208 | 0.066432 | 2948 | 7.9e-06 | 7.9011e-06 | 3126 | 0.27 | 1055
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | CR224 | TRUE | 1656.0037 | 656.3547 | 0.40793 | 17 | 0.00012032 | 1179 | 0.065676 | 3317 | 7.89e-06 | 0.0001342 | 3127 | 0.04 | 2180
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 441010 | TRUE | 1310.5118 | 592.4873 | 0.36823 | 4 | 6.85e-05 | 2523 | 0.11315 | 2931 | 7.88e-06 | 3.1509e-05 | 3128 |  | 3562
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 535284 | TRUE | 913.1511 | 10.8615 | 0.0067505 | 9 | 0.00012012 | 1185 | 0.065436 | 3401 | 7.86e-06 | 7.0747e-05 | 3129 |  | 2746
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 8746 | TRUE | 832.2162 | 645.6965 | 0.4013 | 8 | 0.00011829 | 1225 | 0.06579 | 3278 | 7.82e-06 | 6.2573e-05 | 3130 | 0.55 | 867
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 60052 | FALSE | 3169.0097 | 3169.0097 | 1.9696 | 28 | 0.00011748 | 1236 | 0.066432 | 3001 | 7.8e-06 | 0.00021853 | 3131 | 0.05 | 1976
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 75210 | TRUE | 618.926 | 618.926 | 0.38467 | 6 | 0.00011638 | 1261 | 0.066432 | 2967 | 7.73e-06 | 4.6387e-05 | 3132 | 0.05 | 2048
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | CR008 | FALSE | 7178.6151 | 7178.6151 | 4.4615 | 65 | 0.00011602 | 1269 | 0.066431 | 3099 | 7.71e-06 | 0.00050098 | 3133 | 0.17 | 1230
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 2213 | TRUE | 689.8513 | 689.8513 | 0.42875 | 6 | 0.00011622 | 1265 | 0.066218 | 3167 | 7.69e-06 | 4.6136e-05 | 3134 | 0.02 | 2454
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 553571 | TRUE | 319.9061 | 174.9029 | 0.1087 | 4 | 0.00011616 | 1267 | 0.065791 | 3271 | 7.66e-06 | 3.0647e-05 | 3135 |  | 3296
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | CB | TRUE | 64360.3141 | 0 | 0 | 374 | 0.00011744 | 1237 | 0.065148 | 3603 | 7.65e-06 | 0.0028614 | 3136 |  | 2721
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 60082 | TRUE | 6614.3058 | 0 | 0 | 57 | 0.00011735 | 1238 | 0.06517 | 3546 | 7.65e-06 | 0.00043592 | 3137 |  | 2780
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 327226 | TRUE | 144.3861 | 79.5833 | 0.049461 | 2 | 0.0001161 | 1268 | 0.065791 | 3273 | 7.65e-06 | 1.5292e-05 | 3138 |  | 3458
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 90846 | TRUE | 149.205 | 149.205 | 0.092731 | 2 | 0.00011453 | 1306 | 0.066431 | 3082 | 7.61e-06 | 1.5217e-05 | 3139 | 0.01 | 2578
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 787007 | TRUE | 354.8281 | 307.1886 | 0.19092 | 5 | 0.00010238 | 1593 | 0.070735 | 2943 | 7.59e-06 | 3.7958e-05 | 3140 |  | 3398
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | CB | FALSE | 2354.3543 | 1281.2412 | 0.7963 | 18 | 0.00011498 | 1299 | 0.065789 | 3286 | 7.59e-06 | 0.00013659 | 3141 | 0.02 | 2484
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | CB | FALSE | 5901.3044 | 5623.7964 | 3.4952 | 45 | 0.00011418 | 1316 | 0.066318 | 3144 | 7.58e-06 | 0.00034092 | 3142 | 0.06 | 1823
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 645092 | FALSE | 2229.6022 | 2229.6022 | 1.3857 | 16 | 0.0001137 | 1326 | 0.066352 | 3135 | 7.55e-06 | 0.00012085 | 3143 |  | 3010
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 84640 | TRUE | 1219.4213 | 660.5476 | 0.41053 | 14 | 0.00011439 | 1310 | 0.06579 | 3276 | 7.53e-06 | 0.00010543 | 3144 | 0.06 | 1834
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | CB | TRUE | 80.9954 | 80.9954 | 0.050339 | 3 | 0.00011256 | 1354 | 0.066431 | 3089 | 7.48e-06 | 2.2433e-05 | 3145 | 0.03 | 2362
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 658899 | TRUE | 987.2682 | 941.3759 | 0.58507 | 8 | 0.00011266 | 1349 | 0.066271 | 3156 | 7.47e-06 | 5.9729e-05 | 3146 |  | 2819
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 814784 | TRUE | 296.0572 | 280.0552 | 0.17406 | 3 | 0.00011354 | 1332 | 0.066004 | 3223 | 7.45e-06 | 2.2342e-05 | 3147 |  | 3559
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | CR266 | FALSE | 1901.6084 | 1901.6084 | 1.1819 | 8 | 0.00011171 | 1375 | 0.066431 | 3110 | 7.42e-06 | 5.9368e-05 | 3148 | 23 | 290
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 6867 | TRUE | 1328.3948 | 985.9493 | 0.61277 | 11 | 0.00011216 | 1362 | 0.066081 | 3202 | 7.41e-06 | 8.155e-05 | 3149 | 0.06 | 1791
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 9052 | FALSE | 8315.3581 | 7722.3255 | 4.7995 | 65 | 0.00011158 | 1380 | 0.066333 | 3139 | 7.41e-06 | 0.00048153 | 3150 | 0.1 | 1459
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 296894 | TRUE | 465.5322 | 278.1636 | 0.17288 | 6 | 0.00011252 | 1355 | 0.065577 | 3344 | 7.4e-06 | 4.4388e-05 | 3151 |  | 3312
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 407286 | TRUE | 98.0196 | 98.0196 | 0.06092 | 1 | 0.00011059 | 1398 | 0.066431 | 3111 | 7.35e-06 | 7.3466e-06 | 3152 |  | 3557
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 705523 | TRUE | 1068.2355 | 321.9298 | 0.20008 | 11 | 0.00011081 | 1395 | 0.065615 | 3332 | 7.29e-06 | 8.0224e-05 | 3153 |  | 3044
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 183888 | FALSE | 4871.8577 | 1898.9745 | 1.1802 | 43 | 0.00011047 | 1402 | 0.065447 | 3396 | 7.23e-06 | 0.00031108 | 3154 |  | 2846
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 892332 | TRUE | 410.223 | 410.223 | 0.25496 | 4 | 0.00010843 | 1438 | 0.066432 | 2994 | 7.2e-06 | 2.8814e-05 | 3155 |  | 3332
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | CR312 | FALSE | 5934.1286 | 5934.1286 | 3.6881 | 42 | 0.00010828 | 1446 | 0.066401 | 3119 | 7.19e-06 | 0.00030194 | 3156 | 0.12 | 1375
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 191725 | TRUE | 766.9235 | 558.1402 | 0.34689 | 8 | 0.00010854 | 1435 | 0.066111 | 3189 | 7.17e-06 | 5.7337e-05 | 3157 |  | 2999
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 394169 | TRUE | 962.9958 | 642.0804 | 0.39906 | 7 | 0.00010894 | 1428 | 0.065699 | 3310 | 7.15e-06 | 5.0037e-05 | 3158 |  | 3287
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 380760 | FALSE | 1136.5362 | 1053.0262 | 0.65446 | 12 | 0.00010812 | 1448 | 0.066113 | 3186 | 7.15e-06 | 8.5741e-05 | 3159 |  | 3461
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | CR188 | FALSE | 5760.2047 | 5760.2047 | 3.58 | 47 | 0.00010753 | 1463 | 0.066431 | 3016 | 7.14e-06 | 0.00033573 | 3160 | 0.38 | 960
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 983580 | FALSE | 4036.4763 | 3958.5011 | 2.4602 | 33 | 0.00010756 | 1462 | 0.066393 | 3122 | 7.14e-06 | 0.00023563 | 3161 |  | 3159
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | CR326 | FALSE | 2098.9601 | 2098.9601 | 1.3045 | 17 | 0.00010686 | 1482 | 0.066431 | 3106 | 7.1e-06 | 0.00012068 | 3162 | 16.75 | 337
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 618957 | TRUE | 394.8447 | 301.119 | 0.18715 | 4 | 0.00010843 | 1439 | 0.065151 | 3574 | 7.06e-06 | 2.8257e-05 | 3163 |  | 3555
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 302192 | TRUE | 22573.2133 | 0 | 0 | 79 | 0.00010836 | 1443 | 0.065152 | 3561 | 7.06e-06 | 0.00055773 | 3164 | 0.74 | 793
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 432850 | FALSE | 1988.3274 | 1988.3274 | 1.2358 | 26 | 0.0001052 | 1514 | 0.066431 | 3017 | 6.99e-06 | 0.0001817 | 3165 |  | 2834
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 2204 | TRUE | 592.6413 | 592.6413 | 0.36833 | 8 | 0.00010504 | 1526 | 0.066432 | 2980 | 6.98e-06 | 5.5825e-05 | 3166 | 0.04 | 2073
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 813976 | TRUE | 328.1808 | 312.2978 | 0.19409 | 4 | 0.00010513 | 1520 | 0.066111 | 3194 | 6.94e-06 | 2.7769e-05 | 3167 |  | 3515
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | CB | TRUE | 17820.8713 | 0 | 0 | 150 | 0.00010626 | 1491 | 0.065148 | 3591 | 6.92e-06 | 0.0010384 | 3168 |  | 2669
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 111666 | TRUE | 1605.5548 | 182.6023 | 0.11349 | 13 | 0.00010584 | 1499 | 0.06525 | 3479 | 6.92e-06 | 8.9978e-05 | 3169 |  | 2676
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 6627 | TRUE | 910.3808 | 910.3808 | 0.56581 | 8 | 0.00010404 | 1550 | 0.066431 | 3048 | 6.91e-06 | 5.5291e-05 | 3170 | 0.03 | 2267
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 68970 | TRUE | 5207.2001 | 75.6257 | 0.047002 | 44 | 0.00010579 | 1501 | 0.065151 | 3565 | 6.89e-06 | 0.00030325 | 3171 | 0.08 | 1617
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 489276 | TRUE | 1058.1278 | 723.7002 | 0.44978 | 9 | 0.00010344 | 1561 | 0.066147 | 3182 | 6.85e-06 | 6.1691e-05 | 3172 |  | 3253
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 71630 | FALSE | 3041.9597 | 2182.1843 | 1.3562 | 26 | 0.00010295 | 1569 | 0.066037 | 3211 | 6.82e-06 | 0.00017743 | 3173 | 0.21 | 1143
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | LC22 | FALSE | 13269.3389 | 12038.7869 | 7.4822 | 114 | 0.0001028 | 1575 | 0.066274 | 3155 | 6.82e-06 | 0.00077774 | 3174 | 0.08 | 1600
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 68694 | TRUE | 3377.3751 | 0 | 0 | 32 | 0.00010397 | 1554 | 0.065151 | 3573 | 6.77e-06 | 0.00021675 | 3175 |  | 2914
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 168368 | TRUE | 1090.7031 | 590.4471 | 0.36697 | 8 | 0.00010339 | 1562 | 0.065308 | 3460 | 6.75e-06 | 5.3993e-05 | 3176 |  | 3294
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 782389 | TRUE | 861.6016 | 585.9597 | 0.36418 | 8 | 0.00010151 | 1617 | 0.065955 | 3232 | 6.72e-06 | 5.3721e-05 | 3177 |  | 3216
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 72990 | FALSE | 5262.4562 | 1175.6663 | 0.73068 | 38 | 0.00010234 | 1594 | 0.065487 | 3374 | 6.71e-06 | 0.00025516 | 3178 | 0.03 | 2293
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | LC16 | FALSE | 8170.2082 | 6889.2884 | 4.2817 | 72 | 0.00010102 | 1624 | 0.066218 | 3168 | 6.71e-06 | 0.00048284 | 3179 | 0.17 | 1248
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 954811 | TRUE | 903.9347 | 282.8935 | 0.17582 | 9 | 0.00010244 | 1591 | 0.065576 | 3345 | 6.71e-06 | 6.035e-05 | 3180 |  | 2805
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 818262 | TRUE | 1433.202 | 292.9133 | 0.18205 | 11 | 0.00010153 | 1615 | 0.0655 | 3368 | 6.66e-06 | 7.3231e-05 | 3181 |  | 2994
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1614 | FALSE | 3000.4112 | 3000.4112 | 1.8648 | 5 | 0.00010012 | 1643 | 9.5753 | 2631 | 6.65e-06 | 3.3257e-05 | 3182 | 0.01 | 2585
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | CB | FALSE | 4270.3121 | 4270.3121 | 2.654 | 36 | 0.00010003 | 1646 | 0.066396 | 3120 | 6.64e-06 | 0.00023916 | 3183 | 0.08 | 1628
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 418 | FALSE | 22746.3302 | 22539.2945 | 14.0083 | 178 | 9.97e-05 | 1655 | 0.066381 | 3126 | 6.62e-06 | 0.0011785 | 3184 | 0.17 | 1236
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | P138 | FALSE | 2470.0232 | 2259.003 | 1.404 | 15 | 9.9e-05 | 1670 | 0.066089 | 3200 | 6.57e-06 | 9.8527e-05 | 3185 | 0.04 | 2093
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | CB | TRUE | 42.5019 | 42.5019 | 0.026415 | 1 | 9.84e-05 | 1681 | 0.066432 | 2999 | 6.54e-06 | 6.536e-06 | 3186 | 0.03 | 2336
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | CB | TRUE | 5967.294 | 629.206 | 0.39105 | 71 | 9.99e-05 | 1649 | 0.065224 | 3498 | 6.53e-06 | 0.00046338 | 3187 | 0.18 | 1209
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 11555 | FALSE | 1379.9837 | 1379.9837 | 0.85767 | 11 | 9.8e-05 | 1688 | 0.066432 | 2976 | 6.51e-06 | 7.165e-05 | 3188 | 0.16 | 1271
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 8888 | TRUE | 2206.3607 | 0 | 0 | 25 | 9.99e-05 | 1651 | 0.065147 | 3614 | 6.51e-06 | 0.0001627 | 3189 |  | 3244
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 801904 | TRUE | 22.3881 | 22.3881 | 0.013914 | 1 | 8.22e-05 | 2146 | 0.079148 | 2934 | 6.51e-06 | 6.5066e-06 | 3190 | 0.06 | 1865
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | MR341 | TRUE | 1045.185 | 417.225 | 0.25931 | 11 | 9.84e-05 | 1680 | 0.065731 | 3300 | 6.5e-06 | 7.1529e-05 | 3191 |  | 3142
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 9973 | TRUE | 921.5182 | 921.5182 | 0.57273 | 7 | 9.78e-05 | 1697 | 0.066431 | 3072 | 6.49e-06 | 4.5461e-05 | 3192 |  | 3027
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 55787 | TRUE | 58.9251 | 58.9251 | 0.036622 | 1 | 9.77e-05 | 1699 | 0.066432 | 2989 | 6.49e-06 | 6.491e-06 | 3193 | 0.05 | 2023
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 3342 | FALSE | 3691.7497 | 3691.7497 | 2.2944 | 30 | 9.64e-05 | 1724 | 0.066431 | 3097 | 6.4e-06 | 0.00019206 | 3194 | 0.04 | 2113
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | CB | FALSE | 16824.5331 | 5560.2483 | 3.4557 | 140 | 9.72e-05 | 1710 | 0.065554 | 3352 | 6.39e-06 | 0.00089393 | 3195 | 0.06 | 1789
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 583284 | TRUE | 404.4133 | 236.5766 | 0.14703 | 4 | 9.55e-05 | 1741 | 0.066111 | 3197 | 6.34e-06 | 2.5347e-05 | 3196 |  | 3325
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 678650 | FALSE | 2024.9152 | 1808.9819 | 1.1243 | 14 | 9.53e-05 | 1757 | 0.066065 | 3203 | 6.28e-06 | 8.7903e-05 | 3197 |  | 3091
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | CR422 | FALSE | 3299.6109 | 3238.2816 | 2.0126 | 24 | 9.44e-05 | 1783 | 0.066378 | 3128 | 6.27e-06 | 0.00015049 | 3198 | 0.06 | 1855
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 2028 | FALSE | 14061.7847 | 14048.0686 | 8.7309 | 107 | 9.42e-05 | 1788 | 0.06642 | 3114 | 6.26e-06 | 0.00066966 | 3199 | 0.05 | 2036
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 4041 | FALSE | 7568.2918 | 2174.4689 | 1.3514 | 54 | 9.54e-05 | 1746 | 0.065458 | 3394 | 6.25e-06 | 0.00033741 | 3200 | 0.04 | 2187
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | CB | FALSE | 7432.6484 | 1011.6246 | 0.62873 | 66 | 9.53e-05 | 1754 | 0.065326 | 3450 | 6.23e-06 | 0.00041127 | 3201 | 0.17 | 1235
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1230 | FALSE | 7038.4432 | 1747.5573 | 1.0861 | 57 | 9.49e-05 | 1770 | 0.065398 | 3418 | 6.22e-06 | 0.00035473 | 3202 | 0.02 | 2465
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 184035 | TRUE | 995.7775 | 905.936 | 0.56304 | 9 | 9.15e-05 | 1859 | 0.066289 | 3152 | 6.07e-06 | 5.4649e-05 | 3203 |  | 3118
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 9048 | TRUE | 24.5909 | 24.5909 | 0.015283 | 1 | 9.12e-05 | 1871 | 0.066432 | 2958 | 6.06e-06 | 6.06e-06 | 3204 | 0.06 | 1869
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1663 | FALSE | 1947.6462 | 1947.6462 | 1.2105 | 17 | 9.11e-05 | 1877 | 0.066432 | 3000 | 6.05e-06 | 0.00010289 | 3205 | 0.08 | 1656
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | MR279 | TRUE | 323.7748 | 4.572 | 0.0028415 | 5 | 9.23e-05 | 1836 | 0.065405 | 3413 | 6.05e-06 | 3.0261e-05 | 3206 |  | 3402
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 534 | FALSE | 2541.7011 | 1569.6662 | 0.97555 | 22 | 9.13e-05 | 1866 | 0.065908 | 3243 | 6.04e-06 | 0.00013285 | 3207 | 0.08 | 1668
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | CB | FALSE | 2551.5911 | 2551.5911 | 1.5858 | 22 | 9.07e-05 | 1892 | 0.066432 | 2986 | 6.02e-06 | 0.0001325 | 3208 | 0.07 | 1703
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 526955 | TRUE | 753.5469 | 713.9611 | 0.44373 | 6 | 9.05e-05 | 1897 | 0.066431 | 3022 | 6.01e-06 | 3.608e-05 | 3209 |  | 3070
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 92582 | TRUE | 4514.9648 | 245.7655 | 0.15274 | 41 | 9.21e-05 | 1840 | 0.065147 | 3619 | 6e-06 | 0.00024599 | 3210 | 0.07 | 1704
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 588020 | TRUE | 2885.7528 | 385.2385 | 0.23943 | 19 | 9.18e-05 | 1849 | 0.065219 | 3500 | 5.99e-06 | 0.00011382 | 3211 |  | 3050
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | LB86 | FALSE | 8620.4875 | 7270.7679 | 4.5188 | 69 | 8.96e-05 | 1927 | 0.066208 | 3169 | 5.95e-06 | 0.00041026 | 3212 | 0.13 | 1335
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | BR164 | TRUE | 91.5845 | 91.5845 | 0.05692 | 2 | 8.94e-05 | 1935 | 0.066432 | 2968 | 5.94e-06 | 1.1874e-05 | 3213 | 0.05 | 1944
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 291744 | TRUE | 231.1314 | 195.7909 | 0.12168 | 3 | 9.01e-05 | 1908 | 0.066004 | 3218 | 5.93e-06 | 1.7783e-05 | 3214 |  | 3455
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 156268 | TRUE | 3622.1133 | 52.7453 | 0.032781 | 31 | 9.07e-05 | 1891 | 0.065189 | 3522 | 5.91e-06 | 0.00018333 | 3215 |  | 3199
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | CB | FALSE | 3450.2108 | 3450.2108 | 2.1443 | 23 | 8.89e-05 | 1953 | 0.066432 | 2985 | 5.91e-06 | 0.00013588 | 3216 | 1.33 | 684
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | LA401R | FALSE | 6369.4185 | 4956.3951 | 3.0804 | 55 | 8.93e-05 | 1939 | 0.066129 | 3184 | 5.91e-06 | 0.00032488 | 3217 | 0.06 | 1827
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 63274 | TRUE | 13077.1161 | 74.3652 | 0.046218 | 119 | 9e-05 | 1914 | 0.06516 | 3555 | 5.86e-06 | 0.00069789 | 3218 | 1.68 | 654
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 964292 | TRUE | 128.1599 | 128.1599 | 0.079652 | 2 | 8.82e-05 | 1978 | 0.066432 | 2995 | 5.86e-06 | 1.1714e-05 | 3219 |  | 3491
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 81770 | TRUE | 2254.8682 | 110.4225 | 0.068628 | 21 | 8.91e-05 | 1945 | 0.065148 | 3588 | 5.8e-06 | 0.00012184 | 3220 |  | 3289
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | P136 | FALSE | 9489.9011 | 7931.4997 | 4.9295 | 43 | 8.05e-05 | 2191 | 0.07255 | 2940 | 5.8e-06 | 0.00024939 | 3221 | 0.03 | 2269
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | CB | FALSE | 1079.0936 | 1079.0936 | 0.67066 | 8 | 8.72e-05 | 2007 | 0.066432 | 3012 | 5.8e-06 | 4.6369e-05 | 3222 | 0.06 | 1836
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 1308 | TRUE | 7407.352 | 244.9631 | 0.15225 | 60 | 8.86e-05 | 1969 | 0.065216 | 3502 | 5.79e-06 | 0.00034724 | 3223 | 8.14 | 435
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 401/2 LR | TRUE | 235.881 | 158.249 | 0.098352 | 4 | 8.76e-05 | 1998 | 0.066112 | 3187 | 5.77e-06 | 2.3092e-05 | 3224 |  | 2987
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 4039 | FALSE | 3724.1919 | 3048.4169 | 1.8946 | 32 | 8.71e-05 | 2010 | 0.066191 | 3171 | 5.76e-06 | 0.00018435 | 3225 | 0.06 | 1903
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 4037 | FALSE | 2780.393 | 1840.2464 | 1.1437 | 22 | 8.77e-05 | 1991 | 0.065616 | 3331 | 5.75e-06 | 0.0001266 | 3226 | 0.04 | 2149
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 10850 | TRUE | 3044.0072 | 994.8842 | 0.61832 | 28 | 8.65e-05 | 2022 | 0.065652 | 3324 | 5.7e-06 | 0.00015971 | 3227 | 0.04 | 2091
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 48636 | TRUE | 4495.7291 | 86.4222 | 0.053712 | 38 | 8.72e-05 | 2008 | 0.065185 | 3527 | 5.69e-06 | 0.00021607 | 3228 | 0.01 | 2615
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 944560 | TRUE | 944.5774 | 282.6401 | 0.17566 | 9 | 8.66e-05 | 2020 | 0.065433 | 3404 | 5.66e-06 | 5.0971e-05 | 3229 |  | 3260
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 162952 | FALSE | 3475.2506 | 2846.7585 | 1.7693 | 25 | 8.54e-05 | 2045 | 0.066175 | 3178 | 5.66e-06 | 0.00014146 | 3230 |  | 2962
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | CB | FALSE | 19272.7585 | 4335.2228 | 2.6944 | 149 | 0.00011557 | 1285 | 29.7426 | 2348 | 0.0036086 | 0.53768 | 2287 | 1.01 | 729
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 42914 | TRUE | 6917.2252 | 665.6425 | 0.4137 | 51 | 8.66e-05 | 2021 | 0.065332 | 3443 | 5.66e-06 | 0.00028854 | 3232 | 0.03 | 2387
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | CR208 | FALSE | 3895.4111 | 3895.4111 | 2.421 | 29 | 8.5e-05 | 2061 | 0.066431 | 3052 | 5.65e-06 | 0.00016371 | 3233 | 0.19 | 1185
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 189400 | FALSE | 5552.3042 | 4446.7436 | 2.7637 | 45 | 8.49e-05 | 2063 | 0.066033 | 3212 | 5.63e-06 | 0.00025337 | 3234 |  | 2728
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 987158 | TRUE | 443.4139 | 397.6831 | 0.24716 | 2 | 8.49e-05 | 2066 | 0.06579 | 3277 | 5.62e-06 | 1.1243e-05 | 3235 |  | 3339
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | CB | FALSE | 7634.7258 | 7634.7258 | 4.745 | 55 | 8.45e-05 | 2075 | 0.066409 | 3116 | 5.62e-06 | 0.00030885 | 3236 | 0.16 | 1263
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | CR170 | FALSE | 2012.9175 | 2012.9175 | 1.251 | 17 | 8.38e-05 | 2100 | 0.066432 | 2973 | 5.57e-06 | 9.4663e-05 | 3237 | 0.21 | 1138
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 189700 | TRUE | 2164.8558 | 306.7254 | 0.19063 | 22 | 8.51e-05 | 2057 | 0.065265 | 3473 | 5.55e-06 | 0.00012213 | 3238 |  | 3343
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 79146 | TRUE | 3115.0804 | 85.6157 | 0.05321 | 28 | 8.35e-05 | 2114 | 0.065194 | 3514 | 5.45e-06 | 0.00015263 | 3239 | 0.02 | 2490
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 634576 | FALSE | 3306.7049 | 2935.0444 | 1.8241 | 29 | 8.2e-05 | 2152 | 0.066255 | 3159 | 5.45e-06 | 0.00015794 | 3240 |  | 2939
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | D520R | TRUE | 5652.8623 | 0 | 0 | 50 | 8.36e-05 | 2109 | 0.065148 | 3583 | 5.45e-06 | 0.00027227 | 3241 |  | 2659
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 69586 | TRUE | 9651.4745 | 688.9218 | 0.42817 | 80 | 8.35e-05 | 2116 | 0.065228 | 3492 | 5.44e-06 | 0.00043538 | 3242 | 0.02 | 2429
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | CB | FALSE | 13332.3504 | 7661.9306 | 4.7619 | 102 | 7.79e-05 | 2261 | 0.072303 | 2941 | 5.43e-06 | 0.00055429 | 3243 | 0.07 | 1735
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 174072 | TRUE | 172.7033 | 172.7033 | 0.10734 | 3 | 8.18e-05 | 2162 | 0.066004 | 3219 | 5.39e-06 | 1.6182e-05 | 3244 |  | 3129
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 834094 | TRUE | 201.2345 | 155.4829 | 0.096633 | 3 | 8.2e-05 | 2155 | 0.065582 | 3337 | 5.39e-06 | 1.6174e-05 | 3245 |  | 3572
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 9024 | FALSE | 6139.1912 | 5646.8015 | 3.5095 | 62 | 8.12e-05 | 2180 | 0.066328 | 3141 | 5.39e-06 | 0.00033401 | 3246 | 0.12 | 1406
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 2235 | TRUE | 1389.3312 | 296.6637 | 0.18438 | 10 | 8.16e-05 | 2164 | 0.065407 | 3411 | 5.35e-06 | 5.3477e-05 | 3247 | 0.03 | 2392
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 264914 | FALSE | 1490.2678 | 1396.6171 | 0.868 | 14 | 8.03e-05 | 2197 | 0.066248 | 3164 | 5.32e-06 | 7.4507e-05 | 3248 |  | 2934
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 310 | TRUE | 5801.4081 | 319.7974 | 0.19876 | 48 | 8.13e-05 | 2173 | 0.065285 | 3466 | 5.31e-06 | 0.00025509 | 3249 | 0.63 | 836
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 6617 | FALSE | 2923.677 | 2923.677 | 1.8171 | 13 | 7.81e-05 | 2257 | 0.068388 | 2946 | 5.3e-06 | 6.8952e-05 | 3250 | 1.03 | 726
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 590690 | TRUE | 383.2694 | 102.0304 | 0.063412 | 4 | 8.12e-05 | 2176 | 0.065148 | 3587 | 5.29e-06 | 2.1169e-05 | 3251 |  | 2919
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 12712 | FALSE | 5357.9341 | 1227.8521 | 0.76312 | 46 | 8.07e-05 | 2189 | 0.065483 | 3376 | 5.28e-06 | 0.00024294 | 3252 | 10.37 | 397
4164 | ELK 11014628 | 42981101 | ELK 1101 | 4628 | FALSE | 6688.9793 | 3975.7324 | 2.4709 | 54 | 7.98e-05 | 2212 | 0.065813 | 3262 | 5.26e-06 | 0.00028378 | 3253 | 0.03 | 2361
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | L522R | FALSE | 6797.2077 | 3031.8636 | 1.8843 | 56 | 7.95e-05 | 2221 | 0.065744 | 3296 | 5.26e-06 | 0.00029428 | 3254 | 1.17 | 704
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 803535 | TRUE | 262.4984 | 262.4984 | 0.16314 | 3 | 7.86e-05 | 2247 | 0.066431 | 3038 | 5.22e-06 | 1.5658e-05 | 3255 |  | 3608
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 2000 | FALSE | 14495.3301 | 14495.3301 | 9.0089 | 101 | 7.84e-05 | 2249 | 0.066432 | 2979 | 5.21e-06 | 0.00052618 | 3256 | 0.12 | 1391
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 434 | TRUE | 1839.9407 | 49.2215 | 0.030591 | 16 | 7.97e-05 | 2216 | 0.065231 | 3489 | 5.2e-06 | 8.3238e-05 | 3257 |  | 2993
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 784032 | TRUE | 974.4826 | 863.751 | 0.53682 | 11 | 7.83e-05 | 2251 | 0.066199 | 3170 | 5.19e-06 | 5.7096e-05 | 3258 |  | 3137
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | CB | FALSE | 7735.7733 | 2937.1415 | 1.8254 | 60 | 7.51e-05 | 2330 | 1.6497 | 2856 | 5.16e-06 | 0.00030957 | 3259 | 0.22 | 1133
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | CR210 | FALSE | 4546.547 | 4546.547 | 2.8257 | 35 | 7.77e-05 | 2270 | 0.066431 | 3091 | 5.16e-06 | 0.00018057 | 3260 | 0.14 | 1309
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 471 | TRUE | 2001.813 | 0 | 0 | 16 | 7.91e-05 | 2233 | 0.06523 | 3491 | 5.15e-06 | 8.2468e-05 | 3261 | 0.33 | 988
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 494 | FALSE | 14793.4066 | 9034.9185 | 5.6152 | 114 | 7.71e-05 | 2285 | 0.06596 | 3230 | 5.11e-06 | 0.00058215 | 3262 | 0.23 | 1112
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 9116 | FALSE | 6878.1556 | 1335.9769 | 0.83032 | 53 | 7.74e-05 | 2280 | 0.065341 | 3442 | 5.05e-06 | 0.00026765 | 3263 | 0.08 | 1597
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 527766 | TRUE | 66.9649 | 66.9649 | 0.041619 | 1 | 7.59e-05 | 2310 | 0.066432 | 2954 | 5.04e-06 | 5.0408e-06 | 3264 |  | 3285
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 648439 | TRUE | 225.8757 | 10.9115 | 0.0067816 | 3 | 7.73e-05 | 2281 | 0.065151 | 3571 | 5.03e-06 | 1.5099e-05 | 3265 |  | 3196
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 8858 | FALSE | 3073.6226 | 3073.6226 | 1.9103 | 27 | 7.52e-05 | 2327 | 0.066432 | 2966 | 4.99e-06 | 0.00013482 | 3266 | 0.08 | 1631
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 5065 | FALSE | 3543.5774 | 3543.5774 | 2.2023 | 27 | 7.49e-05 | 2334 | 0.066432 | 2987 | 4.98e-06 | 0.00013434 | 3267 | 0.1 | 1465
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 2553 | FALSE | 3992.3117 | 1548.3173 | 0.96229 | 32 | 7.54e-05 | 2324 | 0.065669 | 3318 | 4.95e-06 | 0.00015851 | 3268 | 0.05 | 2058
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 305072 | FALSE | 6216.8943 | 5044.0425 | 3.1349 | 45 | 7.47e-05 | 2341 | 0.066118 | 3185 | 4.95e-06 | 0.0002229 | 3269 |  | 2933
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 227862 | TRUE | 2810.7104 | 319.3369 | 0.19847 | 26 | 7.59e-05 | 2311 | 0.065246 | 3481 | 4.95e-06 | 0.00012875 | 3270 |  | 2736
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 885952 | TRUE | 299.4502 | 283.4481 | 0.17616 | 4 | 7.4e-05 | 2360 | 0.066111 | 3195 | 4.91e-06 | 1.963e-05 | 3271 |  | 3397
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 779030 | TRUE | 1061.942 | 827.4759 | 0.51428 | 11 | 7.35e-05 | 2383 | 0.066315 | 3145 | 4.88e-06 | 5.3691e-05 | 3272 |  | 3224
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | CB | TRUE | 5313.0282 | 378.608 | 0.23531 | 52 | 7.43e-05 | 2349 | 0.065199 | 3510 | 4.85e-06 | 0.00025204 | 3273 |  | 2771
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | CB | TRUE | 10978.5428 | 257.3233 | 0.15993 | 91 | 7.4e-05 | 2358 | 0.2391 | 2928 | 4.84e-06 | 0.00044057 | 3274 | 0.04 | 2111
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | CB | FALSE | 3052.0291 | 3052.0291 | 1.8968 | 23 | 7.23e-05 | 2409 | 0.066432 | 2962 | 4.8e-06 | 0.0001105 | 3275 | 0.1 | 1457
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 586832 | FALSE | 6692.9945 | 6145.6408 | 3.8195 | 53 | 7.24e-05 | 2406 | 0.066311 | 3146 | 4.8e-06 | 0.00025437 | 3276 |  | 2711
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 3323 | TRUE | 214.7286 | 214.7286 | 0.13345 | 2 | 7.17e-05 | 2429 | 0.066431 | 3042 | 4.77e-06 | 9.5309e-06 | 3277 | 0.27 | 1051
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 10290 | TRUE | 9277.251 | 4.572 | 0.0028415 | 75 | 7.27e-05 | 2399 | 0.065164 | 3550 | 4.74e-06 | 0.00035541 | 3278 |  | 2841
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 687295 | FALSE | 1495.545 | 1495.545 | 0.92949 | 14 | 7.09e-05 | 2445 | 0.066432 | 2963 | 4.71e-06 | 6.5958e-05 | 3279 |  | 2878
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | CB | TRUE | 6661.6605 | 0 | 0 | 61 | 7.2e-05 | 2419 | 0.065151 | 3564 | 4.69e-06 | 0.00028618 | 3280 | 0.11 | 1448
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | CB | TRUE | 1531.5459 | 0 | 0 | 17 | 7.19e-05 | 2422 | 0.065151 | 3566 | 4.69e-06 | 7.9676e-05 | 3281 | 0.25 | 1083
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 395936 | TRUE | 1081.2511 | 685.7662 | 0.42621 | 6 | 7.08e-05 | 2449 | 0.066004 | 3222 | 4.67e-06 | 2.7994e-05 | 3282 |  | 3422
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 12474 | FALSE | 13789.0355 | 5487.3001 | 3.4104 | 105 | 7.08e-05 | 2448 | 0.065612 | 3333 | 4.65e-06 | 0.00048831 | 3283 | 0.04 | 2152
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 307651 | TRUE | 416.3767 | 169.0436 | 0.10506 | 4 | 7.1e-05 | 2444 | 0.065151 | 3569 | 4.63e-06 | 1.8507e-05 | 3284 |  | 3486
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 262924 | FALSE | 3139.8868 | 3032.2865 | 1.8846 | 30 | 6.96e-05 | 2485 | 0.066389 | 3125 | 4.62e-06 | 0.00013867 | 3285 |  | 3238
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 439 | FALSE | 1501.1745 | 1069.2533 | 0.66455 | 12 | 7.01e-05 | 2470 | 0.066111 | 3191 | 4.62e-06 | 5.5413e-05 | 3286 | 1.58 | 664
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 319320 | TRUE | 221.6252 | 210.6172 | 0.1309 | 3 | 7e-05 | 2472 | 0.065578 | 3340 | 4.61e-06 | 1.3844e-05 | 3287 |  | 3552
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 620294 | TRUE | 312.2722 | 249.6637 | 0.15517 | 4 | 7.01e-05 | 2469 | 0.065468 | 3388 | 4.61e-06 | 1.8443e-05 | 3288 |  | 3315
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 3116 | TRUE | 87.1475 | 87.1475 | 0.054163 | 2 | 6.9e-05 | 2507 | 0.066431 | 3085 | 4.59e-06 | 9.1703e-06 | 3289 |  | 3514
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 782320 | TRUE | 606.8883 | 340.3108 | 0.2115 | 5 | 6.94e-05 | 2491 | 0.065662 | 3321 | 4.55e-06 | 2.2762e-05 | 3290 |  | 3175
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | CB | TRUE | 14121.4272 | 0 | 0 | 124 | 6.98e-05 | 2479 | 0.065151 | 3576 | 4.55e-06 | 0.00056425 | 3291 | 0.02 | 2434
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 4431 | FALSE | 2379.8246 | 2267.622 | 1.4093 | 16 | 6.86e-05 | 2520 | 0.066271 | 3158 | 4.55e-06 | 7.2768e-05 | 3292 | 2.63 | 593
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 186938 | FALSE | 4893.222 | 2672.105 | 1.6607 | 41 | 6.88e-05 | 2512 | 0.0659 | 3245 | 4.55e-06 | 0.00018638 | 3293 |  | 2792
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 602871 | FALSE | 1324.4478 | 1324.4478 | 0.82315 | 14 | 6.84e-05 | 2525 | 0.06634 | 3137 | 4.54e-06 | 6.3511e-05 | 3294 |  | 3232
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 48262 | FALSE | 9974.998 | 9974.998 | 6.1995 | 74 | 6.82e-05 | 2528 | 0.066414 | 3115 | 4.53e-06 | 0.00033533 | 3295 | 0.16 | 1266
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | CR220 | TRUE | 2216.0779 | 325.3992 | 0.20224 | 19 | 6.91e-05 | 2505 | 0.065418 | 3408 | 4.51e-06 | 8.5689e-05 | 3296 | 0.06 | 1884
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 8942 | FALSE | 4451.7025 | 3407.8974 | 2.118 | 35 | 6.8e-05 | 2536 | 0.066102 | 3198 | 4.51e-06 | 0.00015779 | 3297 | 0.07 | 1712
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 404226 | FALSE | 1578.9748 | 1403.5728 | 0.87233 | 15 | 6.76e-05 | 2545 | 0.066004 | 3221 | 4.48e-06 | 6.7166e-05 | 3298 |  | 2985
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 4674 | TRUE | 11266.4783 | 72.8 | 0.045245 | 85 | 6.84e-05 | 2524 | 0.065148 | 3604 | 4.46e-06 | 0.00037897 | 3299 | 0.02 | 2468
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | CB | FALSE | 9310.1865 | 3594.4279 | 2.234 | 73 | 6.79e-05 | 2538 | 0.065429 | 3407 | 4.45e-06 | 0.00032509 | 3300 | 0.03 | 2291
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 617344 | FALSE | 3993.4046 | 2952.1893 | 1.8348 | 34 | 6.68e-05 | 2562 | 0.065865 | 3252 | 4.41e-06 | 0.00014986 | 3301 |  | 3099
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | CB | TRUE | 3983.613 | 901.4332 | 0.56024 | 34 | 5.14e-05 | 3008 | 0.069389 | 2944 | 4.39e-06 | 0.00014935 | 3302 | 0.16 | 1257
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | CB | FALSE | 5468.4733 | 4727.7308 | 2.9383 | 42 | 6.62e-05 | 2583 | 0.066187 | 3172 | 4.39e-06 | 0.00018447 | 3303 | 0.12 | 1373
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 68454 | FALSE | 17728.9798 | 13589.2158 | 8.4458 | 142 | 6.66e-05 | 2571 | 0.066016 | 3214 | 4.39e-06 | 0.00062355 | 3304 | 0.14 | 1311
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 22158 | TRUE | 14506.5343 | 184.8198 | 0.11487 | 119 | 6.73e-05 | 2552 | 0.065158 | 3557 | 4.38e-06 | 0.00052165 | 3305 | 0.04 | 2174
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 12850 | FALSE | 6644.9449 | 1063.4476 | 0.66094 | 52 | 6.65e-05 | 2576 | 0.065295 | 3464 | 4.37e-06 | 0.00022741 | 3306 | 0.02 | 2487
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 498 | FALSE | 4821.7264 | 4596.7491 | 2.8569 | 18 | 6.58e-05 | 2593 | 0.066146 | 3183 | 4.36e-06 | 7.8567e-05 | 3307 | 0.05 | 1926
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 5357 | FALSE | 5401.7845 | 5401.7845 | 3.3572 | 37 | 6.57e-05 | 2599 | 0.066432 | 2965 | 4.36e-06 | 0.0001614 | 3308 | 10.09 | 402
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 9490 | FALSE | 2186.2244 | 2004.014 | 1.2455 | 21 | 6.58e-05 | 2597 | 0.066187 | 3173 | 4.35e-06 | 9.1432e-05 | 3309 | 0.07 | 1753
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 480328 | TRUE | 859.3222 | 472.375 | 0.29358 | 7 | 6.56e-05 | 2600 | 0.065698 | 3311 | 4.33e-06 | 3.0278e-05 | 3310 |  | 2811
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 2654 | FALSE | 2963.5999 | 2963.5999 | 1.8419 | 23 | 6.49e-05 | 2612 | 0.066432 | 2988 | 4.31e-06 | 9.916e-05 | 3311 | 0.09 | 1555
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | CB | TRUE | 1021.9623 | 373.7851 | 0.23231 | 8 | 6.58e-05 | 2595 | 0.065148 | 3585 | 4.29e-06 | 3.4289e-05 | 3312 |  | 3278
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 253312 | TRUE | 698.8026 | 682.8006 | 0.42436 | 2 | 6.58e-05 | 2596 | 713.1431 | 1011 | 4.29e-06 | 8.5718e-06 | 3313 |  | 3438
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 173702 | TRUE | 213.4901 | 86.6803 | 0.053872 | 3 | 6.57e-05 | 2598 | 0.065148 | 3599 | 4.28e-06 | 1.2834e-05 | 3314 |  | 3550
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 65474 | FALSE | 5862.6816 | 3837.7425 | 2.3852 | 47 | 6.44e-05 | 2630 | 0.065968 | 3227 | 4.26e-06 | 0.0002004 | 3315 | 0.05 | 2056
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 218962 | TRUE | 167.2894 | 86.3363 | 0.053658 | 2 | 5.43e-05 | 2937 | 0.078474 | 2935 | 4.26e-06 | 8.5182e-06 | 3316 |  | 3037
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 772224 | TRUE | 126.2491 | 91.9583 | 0.057152 | 2 | 6.4e-05 | 2644 | 0.06579 | 3275 | 4.22e-06 | 8.4316e-06 | 3317 |  | 3588
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 84797 | TRUE | 2211.5607 | 66.6995 | 0.041454 | 21 | 6.45e-05 | 2626 | 0.065331 | 3445 | 4.22e-06 | 8.8525e-05 | 3318 | 0.02 | 2441
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | CB | TRUE | 3818.0634 | 493.1815 | 0.30651 | 38 | 6.46e-05 | 2622 | 0.065215 | 3503 | 4.21e-06 | 0.00016012 | 3319 | 0.01 | 2579
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | CB | TRUE | 8168.5567 | 0 | 0 | 67 | 6.42e-05 | 2638 | 0.065525 | 3359 | 4.21e-06 | 0.00028187 | 3320 |  | 2730
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 1254 | FALSE | 15241.9933 | 9639.5738 | 5.991 | 130 | 6.33e-05 | 2668 | 0.06587 | 3250 | 4.19e-06 | 0.0005443 | 3321 | 0.81 | 771
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 36864 | TRUE | 910.3949 | 889.7222 | 0.55297 | 10 | 6.29e-05 | 2685 | 0.066303 | 3147 | 4.18e-06 | 4.1762e-05 | 3322 | 0.03 | 2369
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 9642 | FALSE | 1925.8934 | 1925.8934 | 1.197 | 18 | 6.28e-05 | 2690 | 0.066432 | 2983 | 4.17e-06 | 7.5077e-05 | 3323 | 0.04 | 2171
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | CB | TRUE | 15331.9124 | 23.5925 | 0.014663 | 121 | 6.4e-05 | 2647 | 0.065159 | 3556 | 4.17e-06 | 0.00050446 | 3324 | 0.02 | 2479
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | CB | TRUE | 49.1761 | 49.1761 | 0.030563 | 1 | 6.27e-05 | 2695 | 0.066431 | 3094 | 4.16e-06 | 4.1622e-06 | 3325 | 0 | 2628
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 267868 | FALSE | 1937.2772 | 1363.5441 | 0.84745 | 13 | 6.31e-05 | 2676 | 0.065839 | 3257 | 4.16e-06 | 5.4041e-05 | 3326 |  | 3346
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 9154 | FALSE | 10556.7719 | 6776.6762 | 4.2117 | 95 | 6.29e-05 | 2686 | 0.065945 | 3236 | 4.15e-06 | 0.00039442 | 3327 | 0.03 | 2237
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 2510 | FALSE | 14243.477 | 12778.5068 | 7.9419 | 22 | 6.25e-05 | 2707 | 0.066023 | 3213 | 4.13e-06 | 9.0933e-05 | 3328 | 0.02 | 2457
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 554 | TRUE | 4453.2978 | 52.9857 | 0.032931 | 35 | 6.33e-05 | 2667 | 0.065188 | 3524 | 4.13e-06 | 0.00014456 | 3329 |  | 2848
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 265211 | TRUE | 282.195 | 238.1693 | 0.14802 | 4 | 6.26e-05 | 2696 | 0.065789 | 3282 | 4.13e-06 | 1.6511e-05 | 3330 |  | 3146
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | CB | FALSE | 8287.0611 | 8183.2875 | 5.0859 | 67 | 6.18e-05 | 2725 | 0.066374 | 3130 | 4.11e-06 | 0.00027516 | 3331 | 0.08 | 1652
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 3012 | TRUE | 22106.1049 | 301.9386 | 0.18766 | 160 | 6.25e-05 | 2701 | 0.065164 | 3551 | 4.07e-06 | 0.00065198 | 3332 | 0.04 | 2138
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | XR248 | TRUE | 2436.8191 | 0 | 0 | 22 | 6.25e-05 | 2700 | 0.065147 | 3632 | 4.07e-06 | 8.9634e-05 | 3333 |  | 3052
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 709451 | TRUE | 302.4738 | 302.4738 | 0.18799 | 5 | 6.07e-05 | 2757 | 0.066432 | 2951 | 4.03e-06 | 2.0151e-05 | 3334 |  | 3439
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | CB | TRUE | 15770.5803 | 273.8424 | 0.17019 | 135 | 6.18e-05 | 2726 | 0.065185 | 3529 | 4.03e-06 | 0.00054404 | 3335 | 0.02 | 2453
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | CB | FALSE | 9896.0278 | 4879.3813 | 3.0326 | 92 | 6.02e-05 | 2766 | 0.065711 | 3305 | 3.97e-06 | 0.00036532 | 3336 | 0.35 | 974
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 189500 | FALSE | 1726.2402 | 1225.686 | 0.76177 | 17 | 6.01e-05 | 2771 | 0.065903 | 3244 | 3.97e-06 | 6.7503e-05 | 3337 |  | 3131
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | CB | FALSE | 2366.505 | 2366.505 | 1.4708 | 17 | 5.95e-05 | 2787 | 0.066432 | 2992 | 3.96e-06 | 6.7244e-05 | 3338 | 0.14 | 1312
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 2606 | FALSE | 4663.4326 | 1279.376 | 0.79514 | 52 | 5.98e-05 | 2780 | 0.065394 | 3420 | 3.92e-06 | 0.00020362 | 3339 | 0.06 | 1806
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 1970 | TRUE | 6915.717 | 0 | 0 | 60 | 6e-05 | 2774 | 0.065151 | 3563 | 3.91e-06 | 0.0002346 | 3340 | 0.06 | 1913
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 145998 | FALSE | 4112.6069 | 4027.966 | 2.5034 | 28 | 5.88e-05 | 2812 | 0.066294 | 3151 | 3.9e-06 | 0.00010919 | 3341 |  | 2898
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 9114 | FALSE | 11036.3123 | 10977.6209 | 6.8226 | 92 | 5.86e-05 | 2817 | 0.066404 | 3117 | 3.89e-06 | 0.00035832 | 3342 | 0.17 | 1246
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 9026 | FALSE | 8105.233 | 1184.1509 | 0.73595 | 71 | 5.95e-05 | 2791 | 0.065382 | 3425 | 3.89e-06 | 0.00027642 | 3343 | 0.03 | 2274
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 9656 | TRUE | 188.9883 | 188.9883 | 0.11746 | 2 | 5.83e-05 | 2826 | 0.066432 | 2981 | 3.87e-06 | 7.7429e-06 | 3344 |  | 3621
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | CR184 | FALSE | 5568.9906 | 5568.9906 | 3.4612 | 43 | 5.79e-05 | 2839 | 0.066432 | 2949 | 3.84e-06 | 0.00016531 | 3345 | 0.05 | 2043
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | P142 | FALSE | 5002.4344 | 1963.5704 | 1.2204 | 41 | 5.82e-05 | 2828 | 0.065555 | 3351 | 3.84e-06 | 0.00015757 | 3346 | 0.02 | 2469
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 643778 | TRUE | 406.3148 | 270.3051 | 0.168 | 4 | 5.78e-05 | 2841 | 0.06547 | 3381 | 3.79e-06 | 1.5168e-05 | 3347 |  | 3549
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 882610 | TRUE | 653.6335 | 228.3158 | 0.1419 | 8 | 5.79e-05 | 2838 | 0.065308 | 3458 | 3.79e-06 | 3.0295e-05 | 3348 |  | 3400
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 526868 | FALSE | 2061.1443 | 1780.5165 | 1.1066 | 20 | 5.68e-05 | 2867 | 0.066239 | 3165 | 3.76e-06 | 7.5227e-05 | 3349 |  | 2663
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 58642 | FALSE | 2892.0319 | 2892.0319 | 1.7974 | 13 | 5.65e-05 | 2871 | 0.066431 | 3049 | 3.75e-06 | 4.8812e-05 | 3350 | 0.02 | 2501
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 2379 | FALSE | 1171.3689 | 1171.3689 | 0.72801 | 11 | 5.65e-05 | 2872 | 0.066432 | 2969 | 3.75e-06 | 4.1301e-05 | 3351 | 0.09 | 1523
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 468158 | TRUE | 1565.7596 | 826.6133 | 0.51374 | 12 | 5.7e-05 | 2862 | 0.065469 | 3384 | 3.74e-06 | 4.4889e-05 | 3352 |  | 2897
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 650808 | TRUE | 998.3572 | 843.3592 | 0.52415 | 8 | 5.33e-05 | 2957 | 0.068808 | 2945 | 3.69e-06 | 2.9515e-05 | 3353 |  | 3257
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 555372 | FALSE | 6684.5288 | 6684.5288 | 4.1545 | 54 | 5.53e-05 | 2905 | 0.066432 | 2978 | 3.67e-06 | 0.00019829 | 3354 | 0.13 | 1342
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 55262 | TRUE | 266.534 | 266.534 | 0.16565 | 4 | 5.5e-05 | 2911 | 0.066431 | 3095 | 3.65e-06 | 1.4612e-05 | 3355 | 0.06 | 1866
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 96874 | FALSE | 1722.0177 | 1345.5157 | 0.83624 | 16 | 5.5e-05 | 2913 | 0.06595 | 3234 | 3.64e-06 | 5.8253e-05 | 3356 |  | 3127
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | CB | FALSE | 4041.5057 | 3727.5543 | 2.3167 | 24 | 5.48e-05 | 2920 | 0.066271 | 3157 | 3.64e-06 | 8.736e-05 | 3357 | 0.04 | 2207
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | CR282 | FALSE | 6573.0208 | 6573.0208 | 4.0852 | 45 | 5.47e-05 | 2924 | 0.066432 | 2977 | 3.64e-06 | 0.00016364 | 3358 | 0.06 | 1916
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | CB | TRUE | 1686.9104 | 61.191 | 0.03803 | 24 | 5.54e-05 | 2902 | 0.065254 | 3478 | 3.61e-06 | 8.6724e-05 | 3359 | 0.03 | 2342
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 9488 | FALSE | 2122.5518 | 1460.401 | 0.90765 | 18 | 5.47e-05 | 2923 | 0.06579 | 3279 | 3.6e-06 | 6.486e-05 | 3360 | 0.02 | 2561
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 558727 | TRUE | 2270.5335 | 217.1494 | 0.13496 | 22 | 5.49e-05 | 2919 | 0.065381 | 3426 | 3.59e-06 | 7.9037e-05 | 3361 |  | 2835
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 42226 | TRUE | 4032.3201 | 940.1806 | 0.58433 | 32 | 5.48e-05 | 2922 | 0.065308 | 3457 | 3.59e-06 | 0.00011482 | 3362 |  | 3126
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 309087 | TRUE | 645.6047 | 302.4969 | 0.188 | 6 | 5.44e-05 | 2935 | 0.065578 | 3341 | 3.58e-06 | 2.145e-05 | 3363 |  | 3096
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 238418 | TRUE | 1291.252 | 331.2384 | 0.20587 | 6 | 5.46e-05 | 2928 | 0.065361 | 3433 | 3.56e-06 | 2.1369e-05 | 3364 |  | 2935
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 428 | TRUE | 2739.6912 | 0 | 0 | 21 | 5.39e-05 | 2943 | 0.065212 | 3505 | 3.52e-06 | 7.3852e-05 | 3365 | 0.37 | 964
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | XR326 | TRUE | 21948.0156 | 0 | 0 | 163 | 5.39e-05 | 2945 | 0.065147 | 3608 | 3.51e-06 | 0.00057196 | 3366 | 0.04 | 2188
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 39786 | TRUE | 5442.5467 | 454.7368 | 0.28262 | 44 | 5.35e-05 | 2950 | 0.065245 | 3482 | 3.5e-06 | 0.00015383 | 3367 | 0.21 | 1145
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 9118 | FALSE | 4822.7839 | 1265.7827 | 0.78669 | 41 | 5.33e-05 | 2954 | 0.065429 | 3406 | 3.49e-06 | 0.00014315 | 3368 | 0.42 | 936
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 991788 | FALSE | 5495.9742 | 1222.0634 | 0.75952 | 43 | 5.29e-05 | 2971 | 0.065395 | 3419 | 3.46e-06 | 0.00014892 | 3369 |  | 2890
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | XR246 | TRUE | 6374.5348 | 71.5932 | 0.044495 | 61 | 5.3e-05 | 2967 | 0.06519 | 3521 | 3.46e-06 | 0.00021081 | 3370 |  | 3218
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 76678 | TRUE | 597.8557 | 88.7522 | 0.05516 | 8 | 5.29e-05 | 2974 | 0.065468 | 3386 | 3.45e-06 | 2.7609e-05 | 3371 | 0.02 | 2467
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 741586 | FALSE | 1137.7952 | 1137.7952 | 0.70714 | 9 | 5.17e-05 | 3002 | 0.066431 | 3093 | 3.43e-06 | 3.09e-05 | 3372 |  | 3342
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 8958 | FALSE | 9585.6333 | 5438.9297 | 3.3803 | 73 | 5.17e-05 | 3001 | 0.065833 | 3259 | 3.41e-06 | 0.00024907 | 3373 | 0.04 | 2204
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 502026 | TRUE | 1729.6385 | 180.5393 | 0.11221 | 17 | 5.2e-05 | 2992 | 0.065374 | 3427 | 3.4e-06 | 5.784e-05 | 3374 |  | 3302
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | LB16 | FALSE | 13211.9515 | 4399.0652 | 2.734 | 97 | 5.15e-05 | 3006 | 0.065597 | 3335 | 3.4e-06 | 0.00032945 | 3375 | 0.03 | 2296
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 951816 | TRUE | 539.1734 | 539.1734 | 0.3351 | 6 | 5.11e-05 | 3013 | 0.066431 | 3112 | 3.39e-06 | 2.0354e-05 | 3376 |  | 3551
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | LC40 | TRUE | 2260.1219 | 26.7728 | 0.016639 | 28 | 5.19e-05 | 2996 | 0.065193 | 3517 | 3.38e-06 | 9.4717e-05 | 3377 | 0.02 | 2440
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | CR182 | FALSE | 7768.8154 | 7768.8154 | 4.8284 | 56 | 5.09e-05 | 3018 | 0.066432 | 2959 | 3.38e-06 | 0.00018928 | 3378 | 0.15 | 1294
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 903036 | TRUE | 576.6112 | 306.6437 | 0.19058 | 5 | 5.08e-05 | 3019 | 0.065404 | 3415 | 3.35e-06 | 1.6737e-05 | 3379 |  | 3419
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | CB | FALSE | 5576.1236 | 3611.6831 | 2.2447 | 46 | 5.05e-05 | 3026 | 0.065847 | 3255 | 3.33e-06 | 0.0001533 | 3380 | 0.18 | 1221
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 66732 | TRUE | 3298.663 | 334.9483 | 0.20817 | 23 | 5.07e-05 | 3021 | 0.065259 | 3476 | 3.31e-06 | 7.6211e-05 | 3381 | 0.04 | 2115
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 2355 | TRUE | 1676.4836 | 644.3598 | 0.40047 | 13 | 5e-05 | 3038 | 0.065643 | 3325 | 3.3e-06 | 4.2852e-05 | 3382 | 0.06 | 1797
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 119798 | TRUE | 129.7041 | 129.7041 | 0.080612 | 2 | 4.95e-05 | 3051 | 0.066432 | 2975 | 3.29e-06 | 6.5735e-06 | 3383 |  | 3428
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 81716 | TRUE | 406.7505 | 406.7505 | 0.2528 | 5 | 4.92e-05 | 3059 | 0.066432 | 2971 | 3.27e-06 | 1.6345e-05 | 3384 |  | 3512
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 950286 | FALSE | 1710.7995 | 1710.7995 | 1.0633 | 17 | 4.91e-05 | 3061 | 0.066432 | 2974 | 3.26e-06 | 5.5462e-05 | 3385 |  | 3046
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | CB | FALSE | 6891.3641 | 1520.1281 | 0.94477 | 66 | 4.96e-05 | 3044 | 0.065478 | 3378 | 3.25e-06 | 0.00021451 | 3386 | 0.05 | 2029
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 107508 | TRUE | 282.9574 | 0 | 0 | 2 | 4.93e-05 | 3054 | 0.065151 | 3568 | 3.21e-06 | 6.4279e-06 | 3387 |  | 3203
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | CR172 | TRUE | 3350.0951 | 904.9661 | 0.56244 | 30 | 4.89e-05 | 3065 | 0.065361 | 3434 | 3.21e-06 | 9.6271e-05 | 3388 | 0.05 | 2015
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 11074 | FALSE | 4972.7567 | 4718.31 | 2.9324 | 41 | 4.84e-05 | 3082 | 0.066275 | 3154 | 3.19e-06 | 0.00013081 | 3389 | 0.48 | 903
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | MR441 | TRUE | 350.4949 | 40.2016 | 0.024985 | 8 | 4.86e-05 | 3074 | 0.065309 | 3456 | 3.19e-06 | 2.5513e-05 | 3390 |  | 3190
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 764698 | TRUE | 357.0375 | 133.4071 | 0.082913 | 5 | 4.86e-05 | 3073 | 0.065407 | 3412 | 3.19e-06 | 1.5933e-05 | 3391 |  | 3156
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | P126 | FALSE | 3297.3508 | 1680.8363 | 1.0446 | 25 | 4.83e-05 | 3085 | 0.065713 | 3304 | 3.18e-06 | 7.9621e-05 | 3392 | 0.03 | 2259
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 7315 | TRUE | 3607.614 | 0 | 0 | 32 | 4.85e-05 | 3078 | 0.065151 | 3567 | 3.16e-06 | 0.00010108 | 3393 |  | 2795
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 33064 | TRUE | 5902.0297 | 0 | 0 | 49 | 4.84e-05 | 3084 | 0.065148 | 3593 | 3.15e-06 | 0.00015435 | 3394 |  | 3017
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | CR100 | FALSE | 5399.0675 | 5399.0675 | 3.3555 | 40 | 4.72e-05 | 3109 | 0.066432 | 2972 | 3.14e-06 | 0.00012547 | 3395 | 0.04 | 2134
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | CB | TRUE | 3679.779 | 47.6524 | 0.029616 | 34 | 4.81e-05 | 3090 | 0.065185 | 3530 | 3.14e-06 | 0.00010664 | 3396 | 0.03 | 2233
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | BR178 | TRUE | 10667.1601 | 48.2003 | 0.029957 | 93 | 4.8e-05 | 3092 | 0.065161 | 3553 | 3.13e-06 | 0.00029117 | 3397 | 0.24 | 1105
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | L534R | FALSE | 3066.0904 | 1291.9266 | 0.80294 | 34 | 4.76e-05 | 3099 | 0.065526 | 3358 | 3.13e-06 | 0.00010636 | 3398 | 0.06 | 1853
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | P176 | TRUE | 5384.4602 | 354.4687 | 0.2203 | 44 | 4.74e-05 | 3104 | 0.066098 | 3199 | 3.13e-06 | 0.00013758 | 3399 | 0.06 | 1778
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 92792 | TRUE | 2338.4551 | 0 | 0 | 21 | 4.79e-05 | 3094 | 0.065148 | 3598 | 3.12e-06 | 6.5595e-05 | 3400 | 0.04 | 2169
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 504524 | TRUE | 2446.524 | 610.0991 | 0.37918 | 15 | 4.75e-05 | 3101 | 0.065322 | 3452 | 3.12e-06 | 4.6823e-05 | 3401 |  | 3262
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 747522 | TRUE | 1686.5664 | 412.9409 | 0.25664 | 16 | 4.75e-05 | 3103 | 0.065468 | 3390 | 3.11e-06 | 4.9813e-05 | 3402 |  | 3378
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 121588 | FALSE | 3050.4627 | 1356.1967 | 0.84288 | 27 | 4.71e-05 | 3111 | 0.065623 | 3330 | 3.1e-06 | 8.3654e-05 | 3403 |  | 2743
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 1256 | FALSE | 12257.9124 | 12003.1718 | 7.46 | 88 | 4.67e-05 | 3121 | 0.066359 | 3134 | 3.1e-06 | 0.00027263 | 3404 | 0.07 | 1720
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 595689 | TRUE | 356.3825 | 44.7654 | 0.027822 | 4 | 4.7e-05 | 3113 | 0.065468 | 3387 | 3.08e-06 | 1.233e-05 | 3405 |  | 3152
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 640 | TRUE | 6850.9553 | 0 | 0 | 56 | 4.71e-05 | 3110 | 0.065185 | 3528 | 3.07e-06 | 0.00017204 | 3406 | 0.02 | 2509
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 9089 | FALSE | 2700.0603 | 2319.95 | 1.4419 | 20 | 4.63e-05 | 3130 | 0.066175 | 3177 | 3.07e-06 | 6.1368e-05 | 3407 | 0.03 | 2365
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 968736 | FALSE | 1533.9821 | 1132.2658 | 0.70371 | 9 | 4.62e-05 | 3133 | 0.065575 | 3349 | 3.04e-06 | 2.7334e-05 | 3408 |  | 2899
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 37284 | TRUE | 823.8475 | 303.068 | 0.18836 | 15 | 4.59e-05 | 3141 | 0.065918 | 3241 | 3.02e-06 | 4.5299e-05 | 3409 |  | 2937
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 48752 | TRUE | 3375.7798 | 23.2085 | 0.014424 | 28 | 4.6e-05 | 3137 | 0.065151 | 3572 | 3e-06 | 8.3928e-05 | 3410 | 0.02 | 2446
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | CB | FALSE | 3860.7171 | 2930.2271 | 1.8211 | 31 | 4.51e-05 | 3157 | 0.066059 | 3208 | 2.99e-06 | 9.2772e-05 | 3411 | 0.06 | 1837
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 1218 | TRUE | 3546.1366 | 106.7452 | 0.066343 | 28 | 4.58e-05 | 3144 | 0.065197 | 3512 | 2.99e-06 | 8.3731e-05 | 3412 | 0.03 | 2368
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 84764 | TRUE | 4092.9318 | 339.9136 | 0.21126 | 33 | 4.57e-05 | 3148 | 0.065268 | 3472 | 2.98e-06 | 9.8398e-05 | 3413 |  | 2990
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 12828 | FALSE | 7906.6719 | 1834.1595 | 1.1399 | 66 | 4.5e-05 | 3161 | 0.065458 | 3393 | 2.97e-06 | 0.0001957 | 3414 |  | 2662
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | CB | TRUE | 2059.8957 | 523.3275 | 0.32525 | 23 | 4.49e-05 | 3162 | 0.065538 | 3356 | 2.96e-06 | 6.8153e-05 | 3415 |  | 2989
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 395498 | TRUE | 792.3855 | 171.0291 | 0.1063 | 8 | 4.54e-05 | 3154 | 0.065308 | 3459 | 2.96e-06 | 2.3698e-05 | 3416 |  | 3227
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 683542 | TRUE | 222.9115 | 222.9115 | 0.13854 | 2 | 4.44e-05 | 3180 | 0.066431 | 3030 | 2.95e-06 | 5.8935e-06 | 3417 |  | 3237
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 405812 | TRUE | 695.3753 | 295.2493 | 0.1835 | 7 | 4.5e-05 | 3158 | 0.065517 | 3362 | 2.94e-06 | 2.0611e-05 | 3418 |  | 3019
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | L541R | TRUE | 978.5878 | 0 | 0 | 11 | 4.5e-05 | 3159 | 0.065148 | 3586 | 2.93e-06 | 3.2256e-05 | 3419 |  | 3233
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | CB | TRUE | 3805.7329 | 538.4598 | 0.33465 | 40 | 4.42e-05 | 3185 | 0.065436 | 3400 | 2.92e-06 | 0.00011674 | 3420 | 0.04 | 2228
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | CR256 | FALSE | 2967.1612 | 1965.4224 | 1.2215 | 27 | 4.42e-05 | 3187 | 0.065813 | 3263 | 2.92e-06 | 7.879e-05 | 3421 | 0.05 | 2053
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 144690 | TRUE | 900.0003 | 418.942 | 0.26037 | 10 | 3.53e-05 | 3344 | 0.075693 | 2936 | 2.9e-06 | 2.905e-05 | 3422 |  | 3264
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | MR233 | TRUE | 1023.3374 | 370.9448 | 0.23054 | 7 | 4.44e-05 | 3176 | 0.065331 | 3447 | 2.9e-06 | 2.0325e-05 | 3423 |  | 3504
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 318 | FALSE | 18622.6335 | 2887.2825 | 1.7945 | 150 | 4.43e-05 | 3183 | 0.065347 | 3439 | 2.9e-06 | 0.00043547 | 3424 |  | 2830
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 87784 | FALSE | 2328.7215 | 2328.7215 | 1.4473 | 23 | 4.36e-05 | 3199 | 0.066432 | 2997 | 2.9e-06 | 6.6598e-05 | 3425 | 0.12 | 1383
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | CB | TRUE | 22.2055 | 22.2055 | 0.013801 | 1 | 4.35e-05 | 3201 | 0.066431 | 3088 | 2.89e-06 | 2.8911e-06 | 3426 | 1.9 | 633
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 4456 | TRUE | 8052.7827 | 0 | 0 | 62 | 4.41e-05 | 3189 | 0.065151 | 3562 | 2.87e-06 | 0.00017803 | 3427 | 0.03 | 2297
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 785521 | TRUE | 292.996 | 109.0213 | 0.067757 | 3 | 4.37e-05 | 3196 | 0.065575 | 3350 | 2.87e-06 | 8.5962e-06 | 3428 |  | 3223
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 2246 | FALSE | 2937.4924 | 2937.4924 | 1.8257 | 23 | 4.3e-05 | 3209 | 0.066432 | 2998 | 2.86e-06 | 6.5676e-05 | 3429 | 0.1 | 1481
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 8922 | FALSE | 1940.3902 | 1940.3902 | 1.206 | 11 | 4.29e-05 | 3211 | 0.066431 | 3096 | 2.85e-06 | 3.1372e-05 | 3430 | 0.18 | 1208
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | CB | FALSE | 4044.2651 | 2195.0074 | 1.3642 | 37 | 4.31e-05 | 3206 | 0.065703 | 3309 | 2.85e-06 | 0.0001053 | 3431 | 0.02 | 2448
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 35388 | TRUE | 727.2974 | 517.0139 | 0.32133 | 8 | 4.27e-05 | 3213 | 0.066111 | 3193 | 2.83e-06 | 2.2675e-05 | 3432 | 0.94 | 745
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | CB | TRUE | 3068.5523 | 350.3296 | 0.21773 | 34 | 4.32e-05 | 3205 | 0.065226 | 3495 | 2.82e-06 | 9.5817e-05 | 3433 |  | 2943
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 733078 | TRUE | 567.873 | 551.871 | 0.34299 | 7 | 4.22e-05 | 3221 | 0.066065 | 3206 | 2.78e-06 | 1.9439e-05 | 3434 |  | 3310
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | CB | TRUE | 7954.9462 | 769.1621 | 0.47804 | 66 | 4.2e-05 | 3224 | 0.065264 | 3474 | 2.76e-06 | 0.00018203 | 3435 | 0.02 | 2428
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 420730 | FALSE | 2651.706 | 1292.6324 | 0.80338 | 21 | 4.17e-05 | 3230 | 0.065759 | 3293 | 2.75e-06 | 5.7777e-05 | 3436 |  | 2760
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 880795 | TRUE | 506.0077 | 163.9752 | 0.10191 | 6 | 4.21e-05 | 3222 | 0.065147 | 3611 | 2.74e-06 | 1.6447e-05 | 3437 |  | 3277
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 947314 | TRUE | 2331.8511 | 461.4011 | 0.28676 | 22 | 4.14e-05 | 3236 | 0.065323 | 3451 | 2.72e-06 | 5.976e-05 | 3438 |  | 3163
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 37074 | TRUE | 506.0081 | 21.9456 | 0.013639 | 6 | 4.14e-05 | 3234 | 0.065361 | 3435 | 2.71e-06 | 1.628e-05 | 3439 | 0.03 | 2372
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 79774 | FALSE | 2604.0952 | 1435.8821 | 0.89241 | 24 | 4.09e-05 | 3247 | 0.065682 | 3315 | 2.7e-06 | 6.4753e-05 | 3440 | 0.05 | 2041
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 12586 | FALSE | 10478.2506 | 3041.3304 | 1.8902 | 85 | 4.11e-05 | 3241 | 0.065464 | 3391 | 2.7e-06 | 0.00022925 | 3441 | 0.05 | 2013
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | CR254 | FALSE | 2477.3187 | 1687.0283 | 1.0485 | 20 | 4.07e-05 | 3253 | 0.065918 | 3242 | 2.69e-06 | 5.3882e-05 | 3442 | 0.03 | 2367
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 36922 | TRUE | 8825.2123 | 0 | 0 | 37 | 4.1e-05 | 3245 | 0.065148 | 3595 | 2.67e-06 | 9.8808e-05 | 3443 |  | 2948
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 798137 | TRUE | 581.8228 | 68.0149 | 0.042272 | 5 | 4.08e-05 | 3250 | 0.065404 | 3417 | 2.66e-06 | 1.3319e-05 | 3444 |  | 3045
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 2016 | TRUE | 6829.6992 | 150.9724 | 0.09383 | 65 | 4.08e-05 | 3249 | 0.065188 | 3525 | 2.66e-06 | 0.00017299 | 3445 | 0.04 | 2208
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 317890 | TRUE | 125.8315 | 125.8315 | 0.078205 | 2 | 4e-05 | 3269 | 0.066431 | 3031 | 2.66e-06 | 5.3133e-06 | 3446 |  | 3501
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | CB | TRUE | 3469.4672 | 0 | 0 | 28 | 4.08e-05 | 3251 | 0.065151 | 3570 | 2.66e-06 | 7.4348e-05 | 3447 | 0.09 | 1558
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | CB | TRUE | 1170.6003 | 164.2523 | 0.10208 | 11 | 4.03e-05 | 3259 | 0.065497 | 3371 | 2.65e-06 | 2.9161e-05 | 3448 | 0.27 | 1059
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 65894 | TRUE | 1441.6391 | 0 | 0 | 12 | 4.06e-05 | 3255 | 0.065148 | 3601 | 2.65e-06 | 3.1761e-05 | 3449 |  | 3031
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 931192 | FALSE | 11415.5971 | 3615.6701 | 2.2472 | 87 | 4.02e-05 | 3262 | 0.065487 | 3375 | 2.65e-06 | 0.00023026 | 3450 |  | 3020
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 2142 | TRUE | 2588.0177 | 151.8851 | 0.094397 | 26 | 4.03e-05 | 3261 | 0.065246 | 3480 | 2.63e-06 | 6.8383e-05 | 3451 | 0.08 | 1615
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | CB | FALSE | 4654.0755 | 1041.2537 | 0.64714 | 39 | 4.01e-05 | 3266 | 0.065411 | 3410 | 2.62e-06 | 0.0001023 | 3452 | 0.04 | 2160
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | CB | TRUE | 9581.6812 | 369.0017 | 0.22934 | 76 | 4e-05 | 3268 | 0.065241 | 3484 | 2.62e-06 | 0.00019889 | 3453 | 0.16 | 1252
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 680537 | TRUE | 1060.8184 | 362.7293 | 0.22544 | 9 | 3.94e-05 | 3278 | 0.065433 | 3403 | 2.6e-06 | 2.3381e-05 | 3454 |  | 3424
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 512070 | TRUE | 481.613 | 279.6247 | 0.17379 | 5 | 3.91e-05 | 3285 | 0.065661 | 3322 | 2.59e-06 | 1.293e-05 | 3455 |  | 3413
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | CB | FALSE | 9084.5965 | 2733.348 | 1.6988 | 81 | 3.93e-05 | 3280 | 0.065515 | 3364 | 2.58e-06 | 0.00020929 | 3456 | 0.24 | 1096
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | MR204 | TRUE | 4739.0907 | 326.5252 | 0.20294 | 46 | 3.94e-05 | 3279 | 0.065259 | 3475 | 2.58e-06 | 0.00011849 | 3457 |  | 2785
885 | EDES 1112CR308 | 13681112 | EDES 1112 | CR308 | FALSE | 5698.3231 | 5168.8003 | 3.2124 | 53 | 3.84e-05 | 3292 | 0.066287 | 3153 | 2.55e-06 | 0.00013527 | 3458 | 0.07 | 1769
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 12494 | TRUE | 4190.5486 | 220.1167 | 0.1368 | 35 | 3.91e-05 | 3283 | 0.065184 | 3532 | 2.55e-06 | 8.9268e-05 | 3459 |  | 3101
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | CB | TRUE | 8504.0553 | 0 | 0 | 41 | 3.91e-05 | 3284 | 0.065147 | 3625 | 2.55e-06 | 0.00010442 | 3460 | 0.18 | 1219
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 206248 | TRUE | 893.3087 | 83.0039 | 0.051587 | 10 | 3.89e-05 | 3288 | 0.065404 | 3414 | 2.54e-06 | 2.5435e-05 | 3461 |  | 3179
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 37436 | FALSE | 3311.0305 | 1208.0743 | 0.75082 | 33 | 3.87e-05 | 3289 | 0.065576 | 3347 | 2.54e-06 | 8.3735e-05 | 3462 | 0.1 | 1485
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 9120 | FALSE | 11903.5243 | 2858.0041 | 1.7763 | 112 | 3.87e-05 | 3290 | 0.065446 | 3397 | 2.54e-06 | 0.00028404 | 3463 | 0.07 | 1741
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 398620 | TRUE | 770.3641 | 758.0837 | 0.47115 | 7 | 3.82e-05 | 3297 | 0.066248 | 3163 | 2.53e-06 | 1.7717e-05 | 3464 |  | 3477
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 184672 | FALSE | 5259.1473 | 2666.0437 | 1.657 | 46 | 3.82e-05 | 3295 | 0.065706 | 3307 | 2.53e-06 | 0.00011617 | 3465 |  | 2869
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | CB | TRUE | 8128.5867 | 387.1496 | 0.24062 | 57 | 3.84e-05 | 3291 | 0.065193 | 3515 | 2.51e-06 | 0.00014314 | 3466 | 0.03 | 2279
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 2064 | FALSE | 1409.3976 | 1409.3976 | 0.87595 | 15 | 3.74e-05 | 3305 | 0.066432 | 2982 | 2.49e-06 | 3.729e-05 | 3467 | 0.08 | 1660
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 42542 | TRUE | 5717.1489 | 862.3483 | 0.53595 | 52 | 3.75e-05 | 3304 | 0.065348 | 3438 | 2.47e-06 | 0.00012818 | 3468 | 0.03 | 2335
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 34438 | FALSE | 8258.6725 | 3709.6211 | 2.3055 | 67 | 3.73e-05 | 3309 | 0.065492 | 3373 | 2.45e-06 | 0.00016445 | 3469 | 0.06 | 1800
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 97318 | TRUE | 1594.8254 | 294.9732 | 0.18333 | 18 | 3.74e-05 | 3306 | 0.065576 | 3346 | 2.45e-06 | 4.4019e-05 | 3470 | 0.03 | 2327
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 3049 | FALSE | 2682.1998 | 1650.9947 | 1.0261 | 23 | 3.71e-05 | 3312 | 0.065874 | 3249 | 2.44e-06 | 5.6224e-05 | 3471 | 2.64 | 592
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 965060 | TRUE | 112.5171 | 99.6543 | 0.061936 | 1 | 3.67e-05 | 3320 | 0.066431 | 3036 | 2.44e-06 | 2.4396e-06 | 3472 |  | 3624
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 758798 | TRUE | 68.038 | 53.2652 | 0.033105 | 2 | 3.64e-05 | 3325 | 0.065789 | 3289 | 2.42e-06 | 4.8318e-06 | 3473 |  | 3603
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | CB | TRUE | 18410.6369 | 20.7388 | 0.012889 | 171 | 3.67e-05 | 3319 | 0.065155 | 3560 | 2.39e-06 | 0.00040951 | 3474 | 0.28 | 1039
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | P160 | TRUE | 10321.2013 | 0 | 0 | 96 | 3.64e-05 | 3324 | 0.065148 | 3582 | 2.37e-06 | 0.00022785 | 3475 | 2.76 | 583
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 116034 | TRUE | 4982.0059 | 539.5091 | 0.33531 | 41 | 3.62e-05 | 3332 | 0.065278 | 3469 | 2.36e-06 | 9.6928e-05 | 3476 |  | 2713
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 75844 | TRUE | 864.7167 | 272.6844 | 0.16947 | 10 | 3.57e-05 | 3340 | 0.065275 | 3470 | 2.33e-06 | 2.3271e-05 | 3477 | 0.02 | 2485
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 8846 | FALSE | 7060.9911 | 3588.6165 | 2.2303 | 61 | 3.52e-05 | 3347 | 0.065737 | 3298 | 2.32e-06 | 0.00014163 | 3478 | 0.04 | 2219
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | CB | TRUE | 1584.8668 | 745.3166 | 0.46322 | 19 | 3.53e-05 | 3345 | 0.06535 | 3437 | 2.31e-06 | 4.3942e-05 | 3479 | 0.02 | 2415
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 936988 | FALSE | 10891.0554 | 10891.0554 | 6.7688 | 86 | 3.47e-05 | 3356 | 0.066432 | 2957 | 2.31e-06 | 0.00019824 | 3480 |  | 2818
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 1270 | TRUE | 2454.7077 | 0 | 0 | 21 | 3.53e-05 | 3343 | 0.06515 | 3579 | 2.3e-06 | 4.8357e-05 | 3481 |  | 3133
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 258792 | FALSE | 4808.6867 | 4793.9751 | 2.9795 | 36 | 3.47e-05 | 3358 | 0.066396 | 3121 | 2.3e-06 | 8.287e-05 | 3482 |  | 2788
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 902998 | FALSE | 9746.2747 | 1732.2882 | 1.0766 | 81 | 3.51e-05 | 3350 | 0.065372 | 3428 | 2.3e-06 | 0.00018615 | 3483 |  | 2809
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 48936 | FALSE | 9703.0008 | 7437.214 | 4.6223 | 86 | 3.47e-05 | 3355 | 0.066043 | 3210 | 2.29e-06 | 0.00019731 | 3484 | 0.08 | 1663
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | P128 | TRUE | 4067.7934 | 190.9091 | 0.11865 | 31 | 3.47e-05 | 3357 | 0.065272 | 3471 | 2.27e-06 | 7.0301e-05 | 3485 | 0.03 | 2403
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 206332 | TRUE | 973.8303 | 488.8653 | 0.30383 | 7 | 3.19e-05 | 3402 | 0.072747 | 2939 | 2.26e-06 | 1.5798e-05 | 3486 |  | 3039
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | BR304 | FALSE | 5760.7882 | 2392.7287 | 1.4871 | 53 | 3.42e-05 | 3368 | 0.06568 | 3316 | 2.25e-06 | 0.00011921 | 3487 | 0.08 | 1595
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 685656 | FALSE | 5880.2294 | 1923.4165 | 1.1954 | 43 | 3.41e-05 | 3369 | 0.06533 | 3449 | 2.23e-06 | 9.5997e-05 | 3488 |  | 2845
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 60136 | TRUE | 6522.6172 | 0 | 0 | 57 | 3.42e-05 | 3367 | 0.065147 | 3622 | 2.23e-06 | 0.00012684 | 3489 |  | 2829
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 8872 | FALSE | 9042.2667 | 7244.0552 | 4.5022 | 77 | 3.32e-05 | 3382 | 0.066165 | 3180 | 2.2e-06 | 0.00016952 | 3490 | 0.09 | 1565
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 68070 | TRUE | 3445.6939 | 373.7094 | 0.23226 | 30 | 3.36e-05 | 3372 | 0.065233 | 3488 | 2.2e-06 | 6.5858e-05 | 3491 | 0.02 | 2503
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 504941 | TRUE | 1025.616 | 663.24 | 0.41221 | 6 | 3.32e-05 | 3381 | 0.065578 | 3339 | 2.19e-06 | 1.3164e-05 | 3492 |  | 3375
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 9704 | TRUE | 4114.9938 | 786.5986 | 0.48887 | 29 | 3.34e-05 | 3377 | 0.065369 | 3429 | 2.19e-06 | 6.3429e-05 | 3493 | 0.4 | 944
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 9030 | FALSE | 4149.4333 | 3272.4558 | 2.0338 | 37 | 3.31e-05 | 3384 | 0.06605 | 3209 | 2.19e-06 | 8.0902e-05 | 3494 | 0.1 | 1476
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 2070 | TRUE | 3077.1707 | 843.4628 | 0.52422 | 26 | 3.32e-05 | 3383 | 0.065444 | 3398 | 2.18e-06 | 5.6595e-05 | 3495 | 0.04 | 2156
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 972264 | TRUE | 337.1983 | 0 | 0 | 4 | 3.34e-05 | 3379 | 0.065151 | 3575 | 2.17e-06 | 8.6927e-06 | 3496 |  | 3520
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 2082 | FALSE | 4925.5933 | 2445.1965 | 1.5197 | 46 | 3.28e-05 | 3390 | 0.065762 | 3292 | 2.16e-06 | 9.9139e-05 | 3497 | 0.08 | 1612
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 203897 | TRUE | 1017.3713 | 367.9073 | 0.22866 | 9 | 3.28e-05 | 3388 | 0.065433 | 3405 | 2.15e-06 | 1.9358e-05 | 3498 |  | 3108
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 656108 | TRUE | 1195.0984 | 838.7097 | 0.52126 | 10 | 3.26e-05 | 3392 | 0.065918 | 3240 | 2.15e-06 | 2.1478e-05 | 3499 |  | 2956
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | BR196 | TRUE | 5817.7228 | 0 | 0 | 51 | 3.26e-05 | 3391 | 0.065172 | 3540 | 2.13e-06 | 0.00010848 | 3500 | 0.05 | 1940
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | CB | FALSE | 15907.2746 | 5284.9861 | 3.2846 | 136 | 3.21e-05 | 3399 | 0.065515 | 3363 | 2.12e-06 | 0.00028825 | 3501 | 0.06 | 1835
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 9104 | FALSE | 9586.0766 | 9148.567 | 5.6859 | 79 | 3.18e-05 | 3404 | 0.066367 | 3133 | 2.11e-06 | 0.00016692 | 3502 | 0.18 | 1218
617 | OAK 0401CB | 12600401 | OAK 0401 | CB | FALSE | 8716.4726 | 5585.5806 | 3.4715 | 68 | 3.15e-05 | 3408 | 0.06596 | 3231 | 2.09e-06 | 0.00014192 | 3503 | 0.09 | 1539
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 9698 | TRUE | 1062.5186 | 929.6624 | 0.57779 | 10 | 3.11e-05 | 3415 | 0.066303 | 3148 | 2.06e-06 | 2.0607e-05 | 3504 | 0.07 | 1771
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | BR316 | FALSE | 6608.6922 | 6608.6922 | 4.1073 | 56 | 3.1e-05 | 3416 | 0.066432 | 2970 | 2.06e-06 | 0.00011529 | 3505 | 0.12 | 1388
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 57953 | TRUE | 1217.1907 | 353.2769 | 0.21956 | 11 | 3.12e-05 | 3413 | 0.065497 | 3370 | 2.05e-06 | 2.2566e-05 | 3506 | 0.34 | 977
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | CB | TRUE | 8361.6686 | 466.2641 | 0.28979 | 63 | 3.11e-05 | 3414 | 0.065209 | 3507 | 2.04e-06 | 0.00012831 | 3507 | 0.03 | 2390
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | CB | TRUE | 1166.6657 | 0 | 0 | 15 | 3.12e-05 | 3412 | 0.065147 | 3617 | 2.03e-06 | 3.0501e-05 | 3508 |  | 3022
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | CB | TRUE | 7506.165 | 0 | 0 | 70 | 3.09e-05 | 3418 | 0.065147 | 3616 | 2.02e-06 | 0.00014108 | 3509 | 0.05 | 2064
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | CB | TRUE | 7799.5565 | 109.5296 | 0.068073 | 62 | 3.07e-05 | 3420 | 0.065188 | 3523 | 2e-06 | 0.00012428 | 3510 | 0.02 | 2475
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 781759 | TRUE | 264.5561 | 210.4887 | 0.13082 | 4 | 3.06e-05 | 3422 | 0.065789 | 3288 | 2e-06 | 8.0105e-06 | 3511 |  | 3469
254 | HICKS 1116CB | 83431116 | HICKS 1116 | CB | TRUE | 22837.5991 | 336.1648 | 0.20893 | 165 | 3e-05 | 3426 | 0.065178 | 3539 | 1.96e-06 | 0.00032262 | 3512 | 0.04 | 2128
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 1019 | TRUE | 1173.8689 | 432.0709 | 0.26853 | 10 | 2.98e-05 | 3428 | 0.065279 | 3468 | 1.95e-06 | 1.946e-05 | 3513 | 0.07 | 1695
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 546744 | TRUE | 633.1716 | 428.8696 | 0.26654 | 7 | 2.92e-05 | 3435 | 0.065882 | 3248 | 1.93e-06 | 1.3538e-05 | 3514 |  | 3577
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 994213 | TRUE | 860.1534 | 198.7798 | 0.12354 | 8 | 2.92e-05 | 3437 | 0.065311 | 3455 | 1.91e-06 | 1.5241e-05 | 3515 |  | 3071
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 849701 | TRUE | 220.6039 | 213.7724 | 0.13286 | 2 | 2.84e-05 | 3447 | 0.065789 | 3283 | 1.89e-06 | 3.7788e-06 | 3516 |  | 3358
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 9540 | FALSE | 3592.089 | 2319.7097 | 1.4417 | 32 | 2.85e-05 | 3444 | 0.06587 | 3251 | 1.89e-06 | 6.0431e-05 | 3517 | 0.02 | 2557
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 884949 | TRUE | 693.01 | 312.7335 | 0.19437 | 5 | 2.86e-05 | 3443 | 0.065663 | 3319 | 1.88e-06 | 9.3841e-06 | 3518 |  | 3352
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 965216 | FALSE | 2651.8859 | 2642.7419 | 1.6425 | 21 | 2.81e-05 | 3457 | 0.066371 | 3131 | 1.87e-06 | 3.9227e-05 | 3519 |  | 3185
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 104588 | TRUE | 1238.8359 | 581.4114 | 0.36135 | 11 | 2.83e-05 | 3451 | 0.065731 | 3301 | 1.87e-06 | 2.0518e-05 | 3520 |  | 2924
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 31512 | TRUE | 3255.9931 | 0 | 0 | 29 | 2.85e-05 | 3446 | 0.065148 | 3589 | 1.86e-06 | 5.3819e-05 | 3521 | 6.49 | 467
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 344 | FALSE | 12052.7047 | 1314.7551 | 0.81713 | 97 | 2.83e-05 | 3449 | 0.065283 | 3467 | 1.86e-06 | 0.00017996 | 3522 | 0.06 | 1814
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | W52 | FALSE | 6677.88 | 5033.3373 | 3.1282 | 51 | 2.81e-05 | 3459 | 0.066004 | 3224 | 1.85e-06 | 9.4548e-05 | 3523 | 0.05 | 1977
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | BR180 | TRUE | 3108.6276 | 675.0712 | 0.41956 | 25 | 2.81e-05 | 3456 | 0.065507 | 3367 | 1.85e-06 | 4.6282e-05 | 3524 | 3.92 | 531
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | CR306 | FALSE | 1619.5833 | 1619.5833 | 1.0066 | 16 | 2.77e-05 | 3463 | 0.066432 | 2950 | 1.84e-06 | 2.9404e-05 | 3525 | 0.04 | 2175
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | CB | TRUE | 9244.1392 | 431.1151 | 0.26794 | 75 | 2.73e-05 | 3468 | 0.065217 | 3501 | 1.78e-06 | 0.00013376 | 3526 | 0.02 | 2558
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | CB | TRUE | 4463.0648 | 40.2966 | 0.025045 | 38 | 2.72e-05 | 3469 | 0.065182 | 3535 | 1.78e-06 | 6.751e-05 | 3527 | 0.04 | 2082
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 8862 | TRUE | 4562.4649 | 0 | 0 | 38 | 2.71e-05 | 3471 | 0.065147 | 3615 | 1.77e-06 | 6.7125e-05 | 3528 | 0.02 | 2559
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 57046 | TRUE | 1135.0639 | 48.9091 | 0.030397 | 12 | 2.69e-05 | 3474 | 0.065362 | 3431 | 1.76e-06 | 2.1104e-05 | 3529 |  | 2873
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | MR205 | TRUE | 8740.8692 | 0 | 0 | 73 | 2.68e-05 | 3475 | 0.065182 | 3534 | 1.75e-06 | 0.00012759 | 3530 |  | 2764
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 9112 | FALSE | 5302.286 | 1359.4094 | 0.84488 | 43 | 2.65e-05 | 3480 | 0.065387 | 3422 | 1.74e-06 | 7.4909e-05 | 3531 | 0.55 | 872
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | BR236 | TRUE | 850.4173 | 819.8964 | 0.50957 | 7 | 2.62e-05 | 3484 | 0.066065 | 3207 | 1.74e-06 | 1.2161e-05 | 3532 | 0.06 | 1860
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 820379 | TRUE | 298.2228 | 245.2911 | 0.15245 | 2 | 2.61e-05 | 3485 | 0.066431 | 3032 | 1.74e-06 | 3.4725e-06 | 3533 |  | 3139
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 573610 | TRUE | 5029.4735 | 0 | 0 | 41 | 2.65e-05 | 3481 | 0.065179 | 3538 | 1.73e-06 | 7.0764e-05 | 3534 |  | 2722
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 9148 | TRUE | 6634.7635 | 0 | 0 | 51 | 2.64e-05 | 3482 | 0.065147 | 3618 | 1.72e-06 | 8.7791e-05 | 3535 | 0.07 | 1762
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 9094 | TRUE | 4020.7215 | 160.2742 | 0.099611 | 32 | 2.63e-05 | 3483 | 0.065228 | 3493 | 1.71e-06 | 5.4823e-05 | 3536 | 0.02 | 2542
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 2634 | TRUE | 2692.6366 | 0 | 0 | 23 | 2.57e-05 | 3490 | 0.065148 | 3596 | 1.67e-06 | 3.8458e-05 | 3537 | 0.02 | 2497
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | CR150 | TRUE | 755.1885 | 348.5421 | 0.21662 | 6 | 2.52e-05 | 3494 | 0.065789 | 3290 | 1.67e-06 | 1.0002e-05 | 3538 | 0.05 | 1981
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | CB | TRUE | 3993.2278 | 151.4693 | 0.094139 | 40 | 2.55e-05 | 3491 | 0.06518 | 3537 | 1.66e-06 | 6.6534e-05 | 3539 |  | 3157
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 375239 | TRUE | 343.55 | 145.1624 | 0.090219 | 4 | 2.51e-05 | 3495 | 0.065468 | 3385 | 1.65e-06 | 6.5821e-06 | 3540 |  | 3299
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 345099 | TRUE | 497.3995 | 293.3262 | 0.1823 | 5 | 2.49e-05 | 3496 | 0.065404 | 3416 | 1.63e-06 | 8.156e-06 | 3541 |  | 3324
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 3116 | FALSE | 1685.1043 | 1250.9687 | 0.77748 | 10 | 2.45e-05 | 3500 | 0.066175 | 3176 | 1.63e-06 | 1.6267e-05 | 3542 | 0.01 | 2592
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 502466 | TRUE | 854.2839 | 226.0238 | 0.14047 | 10 | 2.44e-05 | 3501 | 0.065532 | 3357 | 1.62e-06 | 1.6151e-05 | 3543 |  | 2745
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | CB | FALSE | 12969.6446 | 1669.1452 | 1.0374 | 103 | 2.44e-05 | 3504 | 0.065322 | 3453 | 1.6e-06 | 0.00016514 | 3544 | 0.03 | 2287
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | BR346 | TRUE | 11386.6089 | 0 | 0 | 102 | 2.44e-05 | 3502 | 0.065147 | 3620 | 1.59e-06 | 0.00016212 | 3545 | 0.02 | 2439
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | CB | FALSE | 8520.938 | 4604.9325 | 2.862 | 70 | 2.37e-05 | 3507 | 0.065808 | 3264 | 1.56e-06 | 0.00010933 | 3546 | 0.05 | 2038
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 850884 | FALSE | 2534.335 | 1368.1711 | 0.85032 | 19 | 2.35e-05 | 3510 | 0.065756 | 3294 | 1.56e-06 | 2.9549e-05 | 3547 |  | 3036
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 915474 | TRUE | 13475.5148 | 697.4237 | 0.43345 | 98 | 2.31e-05 | 3511 | 0.065213 | 3504 | 1.51e-06 | 0.00014771 | 3548 |  | 2723
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 83200 | TRUE | 4654.5591 | 0 | 0 | 48 | 2.26e-05 | 3514 | 0.065158 | 3558 | 1.47e-06 | 7.0606e-05 | 3549 |  | 2716
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 48338 | TRUE | 1760.6636 | 181.1517 | 0.11259 | 17 | 2.24e-05 | 3515 | 0.065147 | 3613 | 1.46e-06 | 2.4768e-05 | 3550 | 0.03 | 2329
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 9126 | FALSE | 3038.2902 | 1621.4045 | 1.0077 | 25 | 2.17e-05 | 3526 | 0.065969 | 3226 | 1.43e-06 | 3.5823e-05 | 3551 | 0.04 | 2080
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 2614 | FALSE | 3446.6772 | 1037.2147 | 0.64463 | 28 | 2.19e-05 | 3521 | 0.065331 | 3444 | 1.43e-06 | 4.0087e-05 | 3552 | 0.03 | 2331
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 86496 | FALSE | 10364.0845 | 1600.54 | 0.99474 | 94 | 2.17e-05 | 3525 | 0.065366 | 3430 | 1.43e-06 | 0.00013413 | 3553 | 0.02 | 2498
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 888954 | TRUE | 504.7129 | 0 | 0 | 6 | 2.17e-05 | 3524 | 0.065147 | 3623 | 1.42e-06 | 8.4914e-06 | 3554 |  | 3272
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | CR164 | FALSE | 10563.0436 | 2405.3877 | 1.495 | 85 | 2.14e-05 | 3530 | 0.065434 | 3402 | 1.41e-06 | 0.00011967 | 3555 | 0.03 | 2312
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 209865 | TRUE | 1489.582 | 423.0102 | 0.2629 | 11 | 2.14e-05 | 3529 | 0.065497 | 3369 | 1.41e-06 | 1.5482e-05 | 3556 |  | 3125
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 153228 | TRUE | 6680.4391 | 463.496 | 0.28806 | 54 | 2.15e-05 | 3528 | 0.065195 | 3513 | 1.4e-06 | 7.5821e-05 | 3557 | 0.02 | 2445
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | XR300 | TRUE | 1391.3933 | 526.7556 | 0.32738 | 14 | 2.12e-05 | 3531 | 0.065331 | 3446 | 1.4e-06 | 1.9531e-05 | 3558 | 0.04 | 2106
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 173396 | TRUE | 265.7346 | 265.7346 | 0.16516 | 3 | 2.1e-05 | 3534 | 0.066004 | 3220 | 1.39e-06 | 4.1666e-06 | 3559 |  | 3563
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 313472 | TRUE | 1178.1951 | 43.1608 | 0.026825 | 9 | 2.07e-05 | 3537 | 0.06529 | 3465 | 1.35e-06 | 1.2158e-05 | 3560 |  | 3319
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 151462 | TRUE | 247.7748 | 247.7748 | 0.15399 | 3 | 2.05e-05 | 3540 | 0.066005 | 3216 | 1.34e-06 | 4.025e-06 | 3561 |  | 3443
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 472928 | TRUE | 1622.1027 | 124.8253 | 0.077579 | 14 | 2.04e-05 | 3541 | 0.065331 | 3448 | 1.33e-06 | 1.8663e-05 | 3562 |  | 3192
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | CR252 | FALSE | 9962.669 | 1765.2604 | 1.0971 | 92 | 2e-05 | 3543 | 0.065384 | 3423 | 1.32e-06 | 0.0001213 | 3563 | 0.03 | 2364
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | MR379 | FALSE | 2535.6763 | 1749.5827 | 1.0874 | 22 | 1.99e-05 | 3545 | 0.065965 | 3229 | 1.31e-06 | 2.8794e-05 | 3564 |  | 2658
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 3487 | TRUE | 2909.578 | 0 | 0 | 20 | 1.94e-05 | 3547 | 0.065147 | 3626 | 1.26e-06 | 2.5244e-05 | 3565 |  | 3359
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | CB | TRUE | 4613.0306 | 118.7443 | 0.0738 | 41 | 1.93e-05 | 3548 | 0.065148 | 3592 | 1.26e-06 | 5.1642e-05 | 3566 | 0.02 | 2443
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 246034 | TRUE | 413.5355 | 202.2758 | 0.12572 | 4 | 1.92e-05 | 3549 | 0.065471 | 3380 | 1.26e-06 | 5.0314e-06 | 3567 |  | 3188
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | V44 | FALSE | 1767.9988 | 1259.7645 | 0.78295 | 17 | 1.9e-05 | 3551 | 0.065827 | 3260 | 1.26e-06 | 2.1378e-05 | 3568 | 0.03 | 2281
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | CR330 | FALSE | 3874.576 | 1155.5838 | 0.7182 | 31 | 1.9e-05 | 3552 | 0.065438 | 3399 | 1.25e-06 | 3.8635e-05 | 3569 | 0.03 | 2322
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | CR328 | TRUE | 7907.5061 | 956.1241 | 0.59424 | 68 | 1.9e-05 | 3550 | 0.065298 | 3462 | 1.25e-06 | 8.4712e-05 | 3570 |  | 2687
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 85904 | FALSE | 3179.0036 | 1684.9898 | 1.0472 | 24 | 1.88e-05 | 3555 | 0.065629 | 3329 | 1.24e-06 | 2.9864e-05 | 3571 | 0.03 | 2340
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 13333 | TRUE | 480.3389 | 70.7861 | 0.043994 | 4 | 1.89e-05 | 3554 | 0.065469 | 3382 | 1.24e-06 | 4.9594e-06 | 3572 | 0.02 | 2476
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | V80 | TRUE | 3197.8948 | 222.7519 | 0.13844 | 28 | 1.86e-05 | 3557 | 0.065193 | 3516 | 1.21e-06 | 3.3939e-05 | 3573 |  | 2973
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 9090 | TRUE | 4202.8057 | 0 | 0 | 38 | 1.85e-05 | 3559 | 0.065147 | 3627 | 1.2e-06 | 4.5748e-05 | 3574 |  | 2679
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | CB | TRUE | 9405.5468 | 893.6462 | 0.5554 | 84 | 1.78e-05 | 3561 | 0.065258 | 3477 | 1.16e-06 | 9.7839e-05 | 3575 | 0.03 | 2356
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 8956 | TRUE | 2231.1917 | 474.6132 | 0.29497 | 18 | 1.76e-05 | 3564 | 0.065361 | 3432 | 1.15e-06 | 2.0752e-05 | 3576 |  | 2884
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 751 | TRUE | 4384.8994 | 264.612 | 0.16446 | 31 | 1.77e-05 | 3563 | 0.065234 | 3487 | 1.15e-06 | 3.5714e-05 | 3577 | 0.02 | 2530
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | CB | TRUE | 8238.1953 | 128.9588 | 0.080148 | 69 | 1.76e-05 | 3565 | 0.065167 | 3548 | 1.15e-06 | 7.9022e-05 | 3578 | 0.04 | 2203
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | BR110 | TRUE | 5064.9775 | 0 | 0 | 45 | 1.75e-05 | 3566 | 0.065147 | 3628 | 1.14e-06 | 5.1366e-05 | 3579 | 18.55 | 320
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 2644 | FALSE | 2922.7748 | 1828.1218 | 1.1362 | 23 | 1.73e-05 | 3567 | 0.065706 | 3306 | 1.14e-06 | 2.6115e-05 | 3580 | 0.03 | 2385
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | CB | TRUE | 16910.3925 | 74.5132 | 0.04631 | 140 | 1.69e-05 | 3571 | 0.065612 | 3334 | 1.13e-06 | 0.0001576 | 3581 |  | 2813
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 38582 | TRUE | 8624.1276 | 853.8778 | 0.53069 | 53 | 1.72e-05 | 3569 | 0.065245 | 3483 | 1.12e-06 | 5.9598e-05 | 3582 |  | 2701
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 6783 | TRUE | 6579.5365 | 0 | 0 | 50 | 1.72e-05 | 3568 | 0.065147 | 3629 | 1.12e-06 | 5.6147e-05 | 3583 | 1.8 | 643
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | W12 | FALSE | 10251.7677 | 6046.1264 | 3.7577 | 70 | 1.56e-05 | 3581 | 0.06699 | 2947 | 1.08e-06 | 7.5829e-05 | 3584 | 0.07 | 1755
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 500 | TRUE | 5066.4275 | 426.2211 | 0.2649 | 39 | 1.65e-05 | 3573 | 0.065312 | 3454 | 1.08e-06 | 4.203e-05 | 3585 |  | 2856
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | MR218 | FALSE | 18150.1664 | 10386.8132 | 6.4554 | 134 | 1.62e-05 | 3577 | 0.065722 | 3303 | 1.07e-06 | 0.00014329 | 3586 | 0.06 | 1868
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | CB | FALSE | 18622.3449 | 1675.1277 | 1.0411 | 153 | 1.61e-05 | 3579 | 0.065231 | 3490 | 1.06e-06 | 0.00016184 | 3587 | 0.03 | 2299
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | CB | TRUE | 2575.0657 | 47.0231 | 0.029225 | 21 | 1.62e-05 | 3575 | 0.065147 | 3630 | 1.06e-06 | 2.2159e-05 | 3588 | 0.03 | 2266
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | P190 | TRUE | 3318.5959 | 0 | 0 | 28 | 1.62e-05 | 3576 | 0.065148 | 3590 | 1.05e-06 | 2.951e-05 | 3589 | 0.06 | 1830
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | CB | TRUE | 11158.113 | 159.3502 | 0.099037 | 95 | 1.59e-05 | 3580 | 0.065161 | 3554 | 1.04e-06 | 9.8546e-05 | 3590 |  | 2653
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | CB | TRUE | 7478.2552 | 0 | 0 | 59 | 1.56e-05 | 3582 | 0.06517 | 3542 | 1.02e-06 | 5.9995e-05 | 3591 | 0.04 | 2225
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | CR198 | TRUE | 8475.9687 | 515.4771 | 0.32037 | 70 | 1.54e-05 | 3584 | 0.065239 | 3486 | 1.01e-06 | 7.0418e-05 | 3592 | 0.02 | 2547
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 760530 | TRUE | 2038.4891 | 342.5788 | 0.21291 | 13 | 1.47e-05 | 3588 | 0.065542 | 3354 | 9.62e-07 | 1.2511e-05 | 3593 |  | 3041
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | W22 | FALSE | 10106.4598 | 4174.2289 | 2.5943 | 85 | 1.45e-05 | 3590 | 0.065661 | 3323 | 9.59e-07 | 8.1495e-05 | 3594 | 0.1 | 1467
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | MR201 | FALSE | 13962.3911 | 2014.3888 | 1.252 | 112 | 1.46e-05 | 3589 | 0.065296 | 3463 | 9.57e-07 | 0.00010718 | 3595 |  | 2794
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 1224 | TRUE | 3249.7676 | 17.2769 | 0.010738 | 29 | 1.44e-05 | 3591 | 0.065191 | 3519 | 9.35e-07 | 2.7124e-05 | 3596 | 0.02 | 2522
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | CB | TRUE | 6943.4772 | 158.1749 | 0.098306 | 63 | 1.41e-05 | 3592 | 0.065208 | 3508 | 9.18e-07 | 5.7843e-05 | 3597 | 0.06 | 1787
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | CB | TRUE | 11783.4703 | 4.3429 | 0.0026991 | 99 | 1.39e-05 | 3593 | 0.065147 | 3631 | 9.08e-07 | 8.9911e-05 | 3598 | 0.02 | 2417
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | P124 | TRUE | 5089.5347 | 0 | 0 | 43 | 1.39e-05 | 3594 | 0.065148 | 3584 | 9.04e-07 | 3.8877e-05 | 3599 | 0.02 | 2525
3672 | EDES 1112CB | 13681112 | EDES 1112 | CB | TRUE | 911.838 | 70.4619 | 0.043792 | 16 | 1.37e-05 | 3595 | 0.065227 | 3494 | 8.99e-07 | 1.4384e-05 | 3600 | 0.03 | 2275
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 9110 | TRUE | 6943.3735 | 472.9116 | 0.29392 | 58 | 1.35e-05 | 3596 | 0.06517 | 3544 | 8.79e-07 | 5.0965e-05 | 3601 | 0.03 | 2318
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 88190 | TRUE | 4658.7637 | 163.0348 | 0.10133 | 34 | 1.31e-05 | 3598 | 0.065223 | 3499 | 8.58e-07 | 2.9159e-05 | 3602 | 0.01 | 2609
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 9440 | TRUE | 5507.5 | 123.7395 | 0.076905 | 55 | 1.31e-05 | 3599 | 0.065171 | 3541 | 8.54e-07 | 4.6991e-05 | 3603 |  | 2959
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 125484 | FALSE | 2451.828 | 1202.5462 | 0.74739 | 4 | 1.3e-05 | 3600 | 11.9509 | 2589 | 8.49e-07 | 3.3971e-06 | 3604 |  | 3614
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 793774 | TRUE | 378.8633 | 111.8888 | 0.069539 | 3 | 1.29e-05 | 3602 | 0.065147 | 3633 | 8.4e-07 | 2.5199e-06 | 3605 |  | 3586
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | CB | TRUE | 4157.1829 | 423.1153 | 0.26297 | 35 | 1.26e-05 | 3603 | 0.065184 | 3531 | 8.23e-07 | 2.8818e-05 | 3606 | 0.04 | 2089
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 714759 | TRUE | 1469.7626 | 361.9191 | 0.22493 | 11 | 1.23e-05 | 3605 | 0.065497 | 3372 | 8.11e-07 | 8.9178e-06 | 3607 |  | 2936
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | CR242 | TRUE | 7351.3672 | 499.489 | 0.31043 | 59 | 1.24e-05 | 3604 | 0.065191 | 3520 | 8.05e-07 | 4.7517e-05 | 3608 | 0.02 | 2462
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | MR236 | FALSE | 13624.1451 | 2212.8784 | 1.3753 | 112 | 1.22e-05 | 3607 | 0.065342 | 3441 | 8.02e-07 | 8.9816e-05 | 3609 |  | 2670
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | CB | TRUE | 3472.0335 | 0 | 0 | 28 | 1.23e-05 | 3606 | 0.065147 | 3624 | 8.01e-07 | 2.2429e-05 | 3610 | 0.02 | 2412
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | CB | TRUE | 30164.8941 | 0 | 0 | 253 | 1.21e-05 | 3608 | 0.065147 | 3612 | 7.9e-07 | 0.00019978 | 3611 |  | 2681
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 2642 | TRUE | 3637.2616 | 0 | 0 | 28 | 1.21e-05 | 3609 | 0.065148 | 3594 | 7.88e-07 | 2.2062e-05 | 3612 | 0.02 | 2511
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | MR545 | FALSE | 7246.1985 | 3496.0754 | 2.1728 | 66 | 1.17e-05 | 3610 | 0.065789 | 3280 | 7.69e-07 | 5.0766e-05 | 3613 | 0.06 | 1782
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 191498 | TRUE | 267.6915 | 189.8568 | 0.118 | 2 | 1.1e-05 | 3611 | 0.065789 | 3281 | 7.28e-07 | 1.4559e-06 | 3614 |  | 3198
749 | WALDO 0401CB | 13350401 | WALDO 0401 | CB | TRUE | 6516.7767 | 0 | 0 | 56 | 1.05e-05 | 3612 | 0.06517 | 3543 | 6.85e-07 | 3.8386e-05 | 3615 | 0.03 | 2378
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 337754 | TRUE | 259.7315 | 97.7177 | 0.060732 | 3 | 9.37e-06 | 3613 | 0.065147 | 3606 | 6.11e-07 | 1.8316e-06 | 3616 |  | 3283
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 404754 | FALSE | 1404.0353 | 1388.0334 | 0.86267 | 2 | 8.76e-06 | 3616 | 0.065789 | 3284 | 5.7e-07 | 1.141e-06 | 3617 |  | 3630
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 9060 | FALSE | 14415.2582 | 1524.9134 | 0.94774 | 98 | 8.45e-06 | 3617 | 0.065226 | 3496 | 5.54e-07 | 5.4254e-05 | 3618 | 0.58 | 857
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 501762 | TRUE | 2438.6275 | 775.0508 | 0.4817 | 23 | 8.42e-06 | 3618 | 0.065482 | 3377 | 5.51e-07 | 1.2672e-05 | 3619 |  | 2821
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 934870 | TRUE | 804.8523 | 147.5524 | 0.091704 | 7 | 8.4e-06 | 3619 | 0.065514 | 3365 | 5.5e-07 | 3.8472e-06 | 3620 |  | 3338
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | CR284 | FALSE | 1550.6574 | 1235.8311 | 0.76807 | 14 | 7.77e-06 | 3623 | 0.066065 | 3205 | 5.14e-07 | 7.191e-06 | 3621 | 0.04 | 2148
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | CR002 | TRUE | 1715.8521 | 269.8408 | 0.16771 | 16 | 7.83e-06 | 3620 | 0.065308 | 3461 | 5.14e-07 | 8.2173e-06 | 3622 | 0.13 | 1341
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 330790 | TRUE | 714.0791 | 199.5624 | 0.12403 | 8 | 7.79e-06 | 3621 | 0.065468 | 3389 | 5.1e-07 | 4.0799e-06 | 3623 |  | 2979
915 | WALDO 0402CB | 13350402 | WALDO 0402 | CB | TRUE | 3475.548 | 0 | 0 | 27 | 7.77e-06 | 3622 | 0.065147 | 3610 | 5.06e-07 | 1.3673e-05 | 3624 | 0.05 | 1955
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | CB | TRUE | 13277.3465 | 69.3073 | 0.043075 | 103 | 7.67e-06 | 3624 | 0.065147 | 3609 | 5e-07 | 5.1467e-05 | 3625 |  | 2677
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | CB | TRUE | 1942.0349 | 0 | 0 | 20 | 7.52e-06 | 3625 | 0.065211 | 3506 | 4.91e-07 | 9.8213e-06 | 3626 |  | 2929
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 52715 | TRUE | 6122.4469 | 0 | 0 | 60 | 7.37e-06 | 3626 | 0.065147 | 3605 | 4.8e-07 | 2.8824e-05 | 3627 |  | 2661
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | V48 | TRUE | 4125.7287 | 198.7298 | 0.12351 | 39 | 7.08e-06 | 3628 | 0.06518 | 3536 | 4.62e-07 | 1.8e-05 | 3628 | 0.02 | 2477
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 458451 | FALSE | 3952.1728 | 1967.4653 | 1.2228 | 29 | 6.9e-06 | 3629 | 0.06559 | 3336 | 4.53e-07 | 1.3134e-05 | 3629 |  | 2862
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | CB | TRUE | 7369.6348 | 597.2084 | 0.37117 | 58 | 6.66e-06 | 3630 | 0.065191 | 3518 | 4.35e-07 | 2.5211e-05 | 3630 | 0.02 | 2520
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 36948 | TRUE | 13534.0061 | 809.6273 | 0.50319 | 109 | 6.11e-06 | 3631 | 0.065183 | 3533 | 3.98e-07 | 4.34e-05 | 3631 |  | 2715
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 132304 | TRUE | 1491.8996 | 118.6631 | 0.07375 | 13 | 5.81e-06 | 3632 | 0.065147 | 3607 | 3.78e-07 | 4.9205e-06 | 3632 |  | 3288
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 36526 | TRUE | 10589.2357 | 72.2645 | 0.044913 | 84 | 5.56e-06 | 3633 | 0.065163 | 3552 | 3.64e-07 | 3.0574e-05 | 3633 | 0.02 | 2418
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | W04 | TRUE | 3941.4804 | 437.2441 | 0.27175 | 26 | 3.6e-06 | 3634 | 0.065147 | 3634 | 2.34e-07 | 6.0945e-06 | 3634 |  | 3060
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | CB | TRUE | 0 | 0 | 0 |  |  | 3635 |  | 3635 |  | 0 | 3635 |  | 3635