## CA Weather Stations
Region | ST | District | Circuit | Project Name | Trans Pole/Facility Point | Type | Order | Equipment Title in System | Status | In-Service Date | ID | Lat | Long | Sap Order #
SW | CA | Happy Camp | 5G16 | 5G16 Happy Camp FP: 07116007.0028100 | 07116007.0028100 | 4G Cellular Microstation | 10068518 6688664 | Happy Camp HAPPY CAMP WEA STA 5G16 028100 | Completed | 2019-07-08 | PAC-3210 | 41.8022 | -123.3673 | 427969
SW | CA | Happy Camp | 5G39 | 5G39 Seiad FP: 06246012.0112003 | 06246012.0112003 | Satellite Microstation | 10068519 | West Seiad SEIAD WEA STA 5G39 112003 | Completed | 2019-07-11 | PAC-3209 | 41.8387 | -123.2089 | 427970
SW | CA | Mt. Shasta | 5G83 | 5G83 Weed FP: 06242005.0306900 | 06242005.0306900 | 4G Cellular Microstation | 10068582 | West Weed WEED WEA STA 5G83 0306900 | Completed | 2019-06-25 | PAC-3207 | 41.4648 | -122.4657 | 427966
SW | CA | Mt. Shasta | 5G83 | 5G83 Weed FP: 06241005.0167701 | 06241005.0167701 | 4G Cellular Microstation | 10068582 | SW Weed WEED WEA STA 5G83 167701 | Completed | 2019-06-19 | PAC-3206 | 41.4036 | -122.4259 | 427967
SW | CA | Mt. Shasta | 5G83 | 5G83 Weed FP: 06242005.0236000 | 06242005.0236000 | 4G Cellular Microstation | 10068582 | North Weed WEED WEA STA 5G83 236000 | Completed | 2019-06-21 | PAC-3208 | 41.4668 | -122.3882 | 427968
SW | CA | Mt. Shasta |  | 688002 007/071 Line 2 Weather Station | 668002 007/071 | 4G Cellular Microstation | 6688768 | Pollard Flat COPCO 2-DELTA 115KV LN #14 WEA STA 7/071 | Completed | 2019-08-06 | PAC-3204 | 41.0099 | -122.4134 | 428268
SW | CA | Mt. Shasta |  | Mt. Shasta 668002 0016/057 | 668002 0016/057 | 4G Cellular Microstation | 10068520 | Dunsmuir COPCO 2-DELTA 69KV #2 WEA STA 16/057 | Completed | 2019-07-01 | PAC-3201 | 41.1918 | -122.287 | 427984
SW | CA | YREKA | 6G101 | 6G101 Snowbrush FP: 06240003.0305800 | 06240003.0305800 | 4G Cellular Microstation | 10068517 | Snowbrush SNOWBRUSH WEA STA 6G101 305800 | Completed | 2019-06-28 | PAC-3203 | 41.2881 | -122.2406 | 427965
SW | CA | Snowbrush |  | Dunsmuir Shasta - 668002 0702/002 | 668002 0702/002 | 4G Cellular Microstation | 10068516 | COPCO 2-DELTA 69KV #2 WEA STA 2/002 | Completed | 2019-06-26 | PAC-3202 | 41.2803 | -122.3166 | 427985
SW | CA | Weed | 5G77 | 5G77 Shasta FP: 06240004.0094801 | 06240004.0094801 | 4G Cellular Microstation | 10068581 | North Mt Shasta MOUNT SHASTA WEA STA 5G77 094801 | Completed | 2019-06-26 | PAC-3205 | 41.3315 | -122.3157 | 427964
SW | CA | CRESCENT CITY | 5R106 | 5R106 Cave Junction FP:07119004.0349301 | 07119004.0349301 | 4G Cellular Microstation | 10071967 | Ca Inspection Station | Completed | 2020-12-08 | PAC-3260 | 41.995 | -123.7209 | 437178
SW | CA | CRESCENT CITY |  | Crescent City 668038 02/053 | 668038 02/053 | Satellite Microstation | 10071967 | Patrick's Creek | Completed | 2020-11-02 | PAC-3261 | 41.8814 | -123.8647 | 437192
SW | CA | ALTURAS | 5L86 | 5L86 Alturas FP: 06143012.0360401 | 06143012.0360401 | 4G Cellular Microstation | 10071967 | Alturas | Completed | 2021-03-16 | PAC-3246 | 41.523 | -120.5429 | 437177
SW | CA | CRESCENT CITY |  | Crescent City 668087/00 5/026 | 668087/00 5/026 | RAWS | 10071967 | Yurok RAWS | Completed | 2021-01-18 |  | 41.5435 | -124.0504 | 437201
SW | CA | CRESCENT CITY |  | Crescent City 668085/00 4/002 | 668085/00 4/002 | RAWS | 10071967 | Smith River RAWS | Completed | 2021-01-19 |  | 41.8855 | -124.1407 | 437202
SW | CA | YREKA | 5g149 | Hawkinsville FP: 668018/00 3/2 | 668018/00 3/2 | 4G Cellular Microstation | 10075769 | Hawkinsville | Completed | 2021-12-21 | PAC-3385 | 41.7796 | -122.6018 | 445155
SW | CA | YREKA | 5G19 | 5G19 Hornbrook FP: 06247006.0288861 | 06247006.0288861 | 4G Cellular Microstation | 10071967 | 5G19 Hornbrook FP: 06247006.0288861 | Completed | 2021-04-05 | PAC-3257 | 41.8993 | -122.5395 | 437181
SW | CA | Yreka | 5G41 | Etna FP: 06242009.0336501 | 06242009.0336501 | 4G Cellular Microstation | 10075769 | Etna | Completed | 2021-12-04 | PAC-3378 | 41.447 | -122.885 | 445144
SW | CA | YREKA | 5G41 | Quartz Valley Rd FP: 06243010.0249700 | 06243010.0249700 | 4G Cellular Microstation | 10075769 | Quartz Valley Rd | Completed | 2021-12-20 | PAC-3384 | 41.5664 | -122.937 | 445154
SW | CA | Yreka | 5G7 | Gunsight Peak FP: 06245008.0215701 | 06245008.0215701 | 4G Cellular Microstation | 10075769 | Gunsight Peak | Completed | 2021-12-06 | PAC-3379 | 41.7382 | -122.7767 | 445145
SW | CA | YREKA | 5G79 | Yreka FP: 06241003.0329100 | 06241003.0329100 | 4G Cellular Microstation | 10071967 | Ski Bowl | Completed | 2021-06-16 | PAC-3255 | 41.3513 | -122.2103 | 437180
SW | CA | YREKA | 5G93 | 5G93 Yreka FP: 06240002.0316300 | 06240002.0316300 | 4G Cellular Microstation | 10071967 | McCloud | Completed | 2021-04-13 | PAC-3253 | 41.2667 | -122.1226 | 437179
SW | CA | YREKA |  | Yreka 668047/00 6/029 | 668047/00 6/29 | 4G Cellular Microstation | 10071967 | Fort Jones | Completed | 2021-05-07 | PAC-3254 | 41.6315 | -122.8222 | 437193
SW | CA | YREKA |  | Yreka 668014/00 4/23 | 668014/00 4/23 | 4G Cellular Microstation | 10071967 | Harry Cash | Completed | 2021-04-06 | PAC-3256 | 41.6541 | -122.3634 | 437194
SW | CA | YREKA |  | Yreka 668033/00 5/011 | 668033/00 5/011 | Satellite Microstation | 10071967 | Scott's Bar | Completed | 2021-05-05 | PAC-3262 | 41.7479 | -122.9998 | 437195
SW | CA | Yreka |  | Castella FP: 668014 3/61 | 668014 3/61 | 4G Cellular Microstation | 10075769 | Castella | Completed | 2021-12-01 | PAC-3374 | 41.1407 | -122.3247 | 445146
SW | CA | Yreka |  | Slate Creek FP: 668014 3/75 | 668014 3/75 | 4G Cellular Microstation | 10075769 | Slate Creek | Completed | 2021-11-30 | PAC-3373 | 40.9675 | -122.4445 | 445147
SW | CA | Yreka |  | Dunsmuir NE FP: 668014 10/53 | 668014 10/53 | 4G Cellular Microstation | 10075769 | Dunsmuir NE | Completed | 2021-12-02 | PAC-3375 | 41.2282 | -122.2559 | 445148
SW | CA | Yreka |  | Black Butte Saddle FP: 668014 9/42 | 668014 9/42 | 4G Cellular Microstation | 10075769 | Black Butte Saddle | Completed | 2021-12-02 | PAC-3376 | 41.3748 | -122.3301 | 445149
SW | CA | Yreka |  | Weed SE FP: 668014 8/40 | 668014 8/40 | 4G Cellular Microstation | 10075769 | Weed SE | Completed | 2021-12-03 | PAC-3377 | 41.404 | -122.3453 | 448150
SW | CA | Yreka |  | Johns Road FP: 668067 1/15 | 668067 1/15 | 4G Cellular Microstation | 10075769 | Johns Road | Completed | 2021-12-10 | PAC-3383 | 41.8261 | -122.5012 | 445151
SW | CA | Yreka |  | Little Grayback FP: 668033 5/47 | 668033 5/47 | 4G Cellular Microstation | 10075769 | Little Grayback | Completed | 2021-12-07 | PAC-3380 | 41.9705 | -123.5371 | 445152
SW | CA | Yreka |  | Indian Creek Canyon* FP: 668033 7/37 | 668033 7/37 | 4G Cellular Microstation | 10075769 | Indian Creek Canyon* | Completed | 2021-12-08 | PAC-3381 | 41.872 | -123.4085 | 445153
SW | CA | Alturas | 5L87 | Thomas Creek FP: 06143014.0234800 | 06143014.0234800 | 4G Cellular Microstation | 10077761 | Thomas Creek FP: 06143014.0234800 | Completed | 2022-05-18 | PAC-3440 | 41.556 | -120.3221 | 448960
SW | CA | Alturas | 5G97 | Cedar Creek FP: 06142015.0032900 | 06142015.0032900 | Satellite Microstation | 10077761 | Cedar Creek FP: 06142015.0032900 | Completed | 2022-05-18 | PAC-3417 | 41.5391 | -120.2307 | 448961
SW | CA | CRESCENT CITY | 5R96 | Darlingtonia 668038/00 1/58 | 668038/00 1/58 | Satellite Microstation | 10075824 | Darlingtonia 668038/00 1/58 | Completed | 2022-05-26 | PAC-3419 | 41.8475 | -123.9367 | 448962
SW | CA | CRESCENT CITY | 6R3 | Dead Horse FP: 07117003.0096301 | 07117003.0096301 | Satellite Microstation | 10075824 | Dead Horse FP: 07117003.0096301 | Completed | 2022-05-25 | PAC-3420 | 41.8806 | -123.837 | 448963
SW | CA | Mt. Shasta | 5G76 | Deetz FP: 06241005.0250002 | 06241005.0250002 | 4G Cellular Microstation | 10075770 | Deetz FP: 06241005.0250002 | Completed | 2022-04-19 | PAC-3407 | 41.3641 | -122.3824 | 447459
SW | CA | Mt. Shasta | 5G76 | Upton FP: 06240004.0050004 | 06240004.0050004 | 4G Cellular Microstation | 10075770 | Upton FP: 06240004.0050004 | Completed | 2022-01-31 | PAC-3391 | 41.3354 | -122.3432 | 446717
SW | CA | Mt. Shasta | 5G93 | Middle Falls FP: 06239001.0051600 | 06239001.0051600 | 4G Cellular Microstation | 10075770 | Middle Falls FP: 06239001.0051600 | Completed | 2022-04-11 | PAC-3386 | 41.2582 | -121.9972 | 447460
SW | CA | Mt. Shasta | 5G93 | Squaw Valley Creek FP: 06239003.0242000 | 06239003.0242000 | 4G Cellular Microstation | 10075770 | Squaw Valley Creek FP: 06239003.0242000 | Completed | 2022-07-19 | PAC-3520 | 41.204 | -122.1487 | 449452
SW | CA | Mt. Shasta | 6G101 | Snowman FP: 06240003.0319460 | 06240003.0319460 | 4G Cellular Microstation | 10075770 | Snowman FP: 06240003.0319460 | Completed | 2022-04-25 | PAC-3415 | 41.2683 | -122.2318 | 447461
SW | CA | Tulelake | 4L3 | Tennant Rd FP:06244002.0231501 | 06244002.0231501 | 4G Cellular Microstation | 10077761 | Tennant Rd FP:06244002.0231501 | Completed | 2022-02-02 | PAC-3388 | 41.6478 | -122.0581 | 446719
SW | CA | Tulelake | 4L3 | Tickner Road FP: 06144006.0232401 | 06144006.0232401 | 4G Cellular Microstation | 10077761 | Tickner Road FP: 06144006.0232401 | Complete | 2022-07-27 | PAC-3511 | 41.6393 | -121.2527 | 449453
SW | CA | Tulelake | 5L62 | Big Tableland FP: 06146002.0102900 | 06146002.0102900 | 4G Cellular Microstation | 10077761 | Big Tableland FP: 06146002.0102900 | Completed | 2022-05-04 | PAC-3439 | 41.8495 | -121.7397 | 447493
SW | CA | Tulelake | 5L62 | Big Tableland 2 FP: 06147002.0274061 | 06147002.0274061 | 4G Cellular Microstation | 10077761 | Big Tableland 2 FP: 06147002.0274061 | Completed | 2022-05-04 | PAC-3441 | 41.8801 | -121.7353 | 447494
SW | CA | CRESCENT CITY | 5R371 | Smith River FP: 07218001.0288402 | 07218001.0288402 | 4G Cellular Microstation | 10077761 | Smith River FP: 07218001.0288402 | Completed | 2022-07-25 | PAC-3510 | 41.9218 | -124.1785 | 448964
SW | CA | Tulelake | 5L62 | D Hill 668041/00 15/3 | 06147001.0041560 | 4G Cellular Microstation | 10077761 | D Hill 668041/00 15/3 | Completed | 2022-07-18 | PAC-3521 | 41.9458 | -121.8797 | 449454
SW | CA | Tulelake | 5L64 | Dorris FP: 668004/00 7/25 | 668004/00 7/25 | 4G Cellular Microstation | 10077761 | Dorris FP: 668004/00 7/25 | Completed | 2022-05-05 | PAC-3437 | 41.9712 | -121.9065 | 449455
SW | CA | Tulelake | 5L73 | Horseshoe Trail FP: 06248001.0272900 | 06248001.0272900 | 4G Cellular Microstation | 10077761 | Horseshoe Trail FP: 06248001.0272900 | Completed | 2022-05-02 | PAC-3442 | 41.9804 | -121.9716 | 447495
SW | CA | Tulelake | 5L73 | Sheepy Saddle FP: 06147003.0123262 | 06147003.0123262 | 4G Cellular Microstation | 10077761 | Sheepy Saddle FP: 06147003.0123262 | Completed | 2022-05-03 | PAC-3438 | 41.9249 | -121.5776 | 447496
SW | CA | Tulelake | 5L78 | Loverland Trail FP: 06247002.0147801 | 06247002.0147801 | 4G Cellular Microstation | 10077761 | Loverland Trail FP: 06247002.0147801 | Completed | 2022-07-07 | PAC-3508 | 41.9205 | -122.0586 | 449456
SW | CA | Tulelake | 4L3 | Long Prairie FP: 06145001.0268900 | 06145001.0268900 | Satellite Microstation | 10077761 | Long Prairie FP: 06145001.0268900 | Completed | 2022-05-23 | PAC-3436 | 41.7207 | -121.8208 | 449457
SW | CA | Yreka | 5G16 | Slater Butte FP: 07117007.0136101 | 07117007.0136101 | 4G Cellular Microstation | 10075770 | Slater Butte FP: 07117007.0136101 | Completed | 2021-12-09 | PAC-3382 | 41.8581 | -123.3534 | 447462
SW | CA | Yreka |  | Sims FP: 668014 4/66 | 668014 4/66 | 4G Cellular Microstation | 10075770 | Sims FP: 668014 4/66 | Completed | 2022-07-15 | PAC-3516 | 41.0723 | -122.3659 | 448932
SW | CA | Yreka |  | Copco FP: 668019 2/2 | 668019 2/2 | Satellite Microstation | 10075770 | Copco FP: 668019 2/2 | Completed | 2022-05-19 | PAC-3387 | 41.9846 | -122.3725 | 448935
SW | CA | Yreka |  | West Branch Indian Creek FP: 668033 7/43 | 668033 7/43 | 4G Cellular Microstation | 10075770 | West Branch Indian Creek FP: 668033 7/43 | Completed | 2022-07-08 | PAC-3507 | 41.8623 | -123.4003 | 448936
SW | CA | Yreka | 5G1 | Piney Ridge FP: 06243008.0023002 | 06243008.0023002 | 4G Cellular Microstation | 10075770 | Piney Ridge FP: 06243008.0023002 | Completed | 2022-02-03 | PAC-3390 | 41.598 | -122.7423 | 446716
SW | CA | Yreka | 5G1 | Fort Jones W FP: 06243009.0022360 | 06243009.0022360 | 4G Cellular Microstation | 10075770 | Fort Jones W FP: 06243009.0022360 | Completed | 2022-07-06 | PAC-3518 | 41.6039 | -122.8532 | 448937
SW | CA | Yreka | 5G149 | Butcher Hill FP: 06245007.0262701 | 06245007.0262701 | 4G Cellular Microstation | 10075770 | Butcher Hill FP: 06245007.0262701 | Completed | 2022-04-13 | PAC-3400 | 41.7249 | -122.6288 | 447463
SW | CA | Yreka | 5G35 | Palomino FP: 06247005.0316800 | 06247005.0316800 | 4G Cellular Microstation | 10075770 | Palonino FP: 06247005.0316800 | Completed | 2022-07-20 | PAC-3513 | 41.9018 | -122.4347 | 448938
SW | CA | Yreka | 5G19 | Hilt South FP: 06248007.0365300 | 06248007.0365300 | 4G Cellular Microstation | 10075770 | Hilt South FP: 06248007.0365300 | Completed | 2022-04-22 | PAC-3408 | 41.9643 | -122.6042 | 447465
SW | CA | Yreka | 5G19 | Hornbrook West FP: 06247006.0200700 | 06247006.0200700 | 4G Cellular Microstation | 10075770 | Hornbrook West FP: 06247006.0200700 | Completed | 2022-07-05 | PAC-3519 | 41.911 | -122.5733 | 448939
SW | CA | Yreka | 5G2 | Oro Fino Creek FP: 06243009.0054000 | 06243009.0054000 | 4G Cellular Microstation | 10075770 | Oro Fino Creek FP: 06243009.0054000 | Completed | 2022-04-18 | PAC-3404 | 41.5997 | -122.9082 | 447466
SW | CA | Yreka | 5G2 | Quartz Valley FP: 06243010.0036500 | 06243010.0036500 | 4G Cellular Microstation | 10075770 | Quartz Valley FP: 06243010.0036500 | Completed | 2022-04-14 | PAC-3401 | 41.6072 | -122.9816 | 447467
SW | CA | Yreka | 5G2 | Costa Gulch 668047/00 1/26 | 668047/00 1/26 | 4G Cellular Microstation | 10075770 | Costa Gulch 668047/00 1/26 | Completed | 2022-04-25 | PAC-3414 | 41.6403 | -122.7612 | 447468
SW | CA | Yreka | 5G21 | Gazelle FP: 06243006.0274040 | 06243006.0274040 | 4G Cellular Microstation | 10075770 | Gazelle FP: 06243006.0274040 | Completed | 2022-04-22 | PAC-3413 | 41.5381 | -122.5275 | 447469
SW | CA | Yreka | 5G23 | Pluto's Cove FP: 06243004.0156901 | 06243004.0156901 | 4G Cellular Microstation | 10075770 | Pluto's Cove FP: 06243004.0156901 | Completed | 2022-04-22 | PAC-3412 | 41.5796 | -122.2878 | 447497
SW | CA | Yreka | 5G31 | Grenada FP: 06244006.0154901 | 06244006.0154901 | 4G Cellular Microstation | 10075770 | Grenada FP: 06244006.0154901 | Completed | 2022-07-06 | PAC-3515 | 41.6681 | -122.526 | 448940
SW | CA | Yreka | 5G31 | Montague FP: 06245006.0289360 | 06245006.0289360 | 4G Cellular Microstation | 10075770 | Montague FP: 06245006.0289360 | Completed | 2022-04-20 | PAC-3409 | 41.7179 | -122.5359 | 447471
SW | CA | Yreka | 5G35 | Montague-Siskiyou AP FP: 06246005.0327401 | 06246005.0327401 | 4G Cellular Microstation | 10075770 | Montague-Siskiyou AP FP: 06246005.0327401 | Completed | 2022-04-29 | PAC-3444 | 41.7937 | -122.4457 | 447472
SW | CA | Yreka | 5G41 | Kidder Creek FP: 06243009.0323901 | 06243009.0323901 | 4G Cellular Microstation | 10075770 | Kidder Creek FP: 06243009.0323901 | Completed | 2022-04-19 | PAC-3405 | 41.5404 | -122.9092 | 447473
SW | CA | Yreka | 5G41 | Eastside Rd FP: 06243009.0357100 | 06243009.0357100 | 4G Cellular Microstation | 10075770 | Eastside Rd FP: 06243009.0357100 | Completed | 2022-04-27 | PAC-3445 | 41.5292 | -122.843 | 447474
SW | CA | Yreka | 5G41 | Oro Fino Creek 2 FP: 06243009.0173602 | 06243009.0173602 | 4G Cellular Microstation | 10075770 | Oro Fino Creek 2 FP: 06243009.0173602 | Completed | 2022-04-27 | PAC-3446 | 41.5804 | -122.9104 | 447475
SW | CA | Yreka | 5G63 | French Creek FP: 06241009.0156500 | 06241009.0156500 | 4G Cellular Microstation | 10075770 | French Creek FP: 06241009.0156500 | Completed | 2022-04-21 | PAC-3410 | 41.4034 | -122.8654 | 447476
SW | CA | Yreka | 5G7 | Guy's Gulch Ridge FP: 06243006.0064502 | 06243006.0064502 | 4G Cellular Microstation | 10075770 | Guy's Gulch Ridge FP: 06243006.0064502 | Completed | 2022-08-01 | PAC-3509 | 41.6048 | -122.5862 | 448941
SW | CA | Yreka | 5G7 | Yreka South FP: 06245007.00353100 | 06245007.00353100 | 4G Cellular Microstation | 10075770 | Yreka South FP: 06245007.00353100 | Completed | 2022-04-21 | PAC-3411 | 41.7007 | -122.6241 | 447477
SW | CA | Yreka | 6G25 | Camelback CA 668075 11/1 | 668075 11/1 | 4G Cellular Microstation | 10075770 | Camelback CA 668075 11/1 | Completed | 2022-02-01 | PAC-3389 | 41.7113 | -122.3716 | 446715
SW | CA | Yreka | 5G63 | Denny Point FP: 06242008.0319101 | 06242008.0319101 | 4G Cellular Microstation | 10075770 | Denny Point FP: 06242008.0319101 | Completed | 2022-04-18 | PAC-3403 | 41.441 | -122.8052 | 447478
SW | CA | Yreka | 5G63 | Schoolhouse FP: 06241008.0241102 | 06241008.0241102 | Satellite Microstation | 10075770 | Schoolhouse FP: 06241008.0241102 | Completed | 2022-04-26 | PAC-3418 | 41.3827 | -122.7275 | 447479
SW | CA | Yreka | 5G40 | Horse Creek FP: 06246010.0095100 | 06246010.0095100 | Satellite Microstation | 10075770 | Horse Creek FP: 06246010.0095100 | Completed | 2022-08-24 | PAC-3453 | 41.8388 | -123.0129 | 448942
SW | CA | Yreka | 5G40 | Dogget FP: 06246009.0107500 | 06246009.0107500 | Satellite Microstation | 10075770 | Dogget FP: 06246009.0107500 | Completed | 2022-08-25 | PAC-3449 | 41.8435 | -122.8788 | 448943
SW | CA | Yreka | 5G63 | Callahan FP: 06240008.0176800 | 06240008.0176800 | Satellite Microstation | 10075770 | Callahan FP: 06240008.0176800 | Completed | 2022-05-20 | PAC-3416 | 41.3204 | -122.8087 | 448944
SW | CA | Tulelake | 4L3 | Tenant South | 06243001.0149603 | Satellite Microstation | 10083635 | Tenant South FP:06243001.0149603 | Complete | 2023-07-11 | PAC-3588 | 41.575 | -121.9243
SW | CA | Tulelake | 5L82 | Kowolowski Rd | 06148006.0349201 | Satellite Microstation | 10083635 | Kowolowski Rd FP:06148006.0349201 | Complete | 2023-07-12 | PAC-3587 | 41.9535 | -121.2619
SW | CA | Tulelake | 5L77 | Meiss Lake Rd | 06246002.0144003 | Satellite Microstation | 10083635 | Meiss Lake Rd FP:06246002.0144003 | Complete | 2023-07-11 | PAC-3584 | 41-822528 | -122.0647
SW | CA | Tulelake | 5L68 | Tucker Lake Rd | 06147006.0280101 | Satellite Microstation | 10083635 | Tucker Lake Rd FP:06147006.0280101 | Complete | 2023-07-12 | PAC-3585 | 41.8813 | -121.3
SW | CA | Tulelake | 5L20 | Malin | 06148006.0073060 | Satellite Microstation | 10083635 | Malin FP:06148006.0073060 | Complete | 2023-07-13 | PAC-3589 | 41.9951 | -121.332
SW | CA | Crescent City | 5R195 | Elk Valley Rd | 07216001.0143760 | 4G Cellular Microstation | 10083636 | Elk Valley Rd FP:07216001.0143760 | Complete | 2023-06-27 | PAC-3562 | 43.6142 | -118.9684 | 450241
SW | CA | Crescent City | 5R171 | Andy McBeth | 07113001.0137200 | Satellite Microstation | 10083636 | Andy McBeth FP:07113001.0137200 | Complete | 2023-06-27 | PAC-3576 | 41.5151 | -123.9978 | 450240
SW | CA | Tulelake | 4L3 | Deer Mountain | 06243003.0042601 | Satellite Microstation | 10083635 | Deer Mountain FP:06243003.0042601 | Complete | 2023-07-11 | PAC-3591 | 41.605 | -122.201
SW | CA | Yreka | 4G1 | Stags Leap Ranch | 06243005.0025020 | 4G Cellular Microstation | 10083634 | Stags Leap Ranch FP:06243005.0025020 | Complete | 2023-06-29 | PAC-3555 | 41.5963 | -122.3884
SW | CA | Yreka | 5G23 | E Louie Rd | 06243005.0184100 | 4G Cellular Microstation | 10083634 | E Louie Rd FP:06243005.0184100 | Complete | 2023-06-28 | PAC-3552 | 41.5687 | -122.4683 | 450245
SW | CA | Yreka | 4G1 | E Lake Shastina | 06242005.0018761 | 4G Cellular Microstation | 10083634 | E Lake Shastina FP:06242005.0018761 | Complete | 2023-06-29 | PAC-3546 | 41.5112 | -122.3645
SW | CA | Yreka | 5G41 | Doe Run | 06243010.0253101 | Satellite Microstation | 10083634 | Doe Run FP:06243010.0253101 | Complete | 2023-05-31 | PAC-3594 | 41.5435 | -122.9464 | 450193
SW | CA | Yreka | 5G2 | Scott River | 06244010.0270801 |  | 10083634 | Scott River FP:06244010.0270801 | Completed | 2023-05-31 | PAC-3593 | 41.6403 | -122.9923 | 450179
SW | CA | Yreka | 5G19 | Klamath River Canyon FP: 06246007.0221921 | 06246007.0221921 | Satellite Microstation | 10083634 | Klamath River Canyon FP: 06246007.0221921 FP:06246007.0221921 | Completed | 2023-05-31 | PAC-3592 | 41.8306 | -122.6586
SW | CA | Yreka | 5G163 | Yreka West | 06245007.0215560 | 4G Cellular Microstation | 10083634 | Yreka West FP:06245007.0215560 | Complete | 2023-06-28 | PAC-3459 | 41.7359 | -122.6605 | 450244