## Attach OEIS 4.7
GhID | Circuit or circuit segment ID | HFTD Tier (Non-HFTD, Tier 2, or Tier 3) | Associated circuit risk score (WRRM) | Associated circuit risk ranking (WRRM) | Associated circuit risk score (LRAM) | Associated circuit risk ranking (LRAM) | Length of project in miles | Current project status (engineering, design, construction, etc.) | Expected year of completion | Initial planned year of completion, if project was delayed | Reason for project delay, if applicable
07047081a | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 | 0.3 | Complete | 2023 | 2022 | Permitting - Cal Trans
07047081b | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 |  | Complete | 2023 | 2022 | Permitting - Cal Trans
07047081c | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 |  | Complete | 2023 | 2022 | Permitting - Cal Trans
8003679a | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 | 4.4 | Complete | 2023 | 2022 | Permitting - Cal Trans
8003679b | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 |  | Complete | 2023 | 2022 | Permitting - Cal Trans
8003679c | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 |  | Complete | 2023 | 2022 | Permitting - Cal Trans
8304727a | 5G16 | Tier 2 | 0.24231 | 254 | 0.78985 | 24 | 0.4 | Complete | 2023 | 2022 | Permitting - FAA
8077832a | 5G76 | Tier 2 | 0.24231 | 336 | 0.81769 | 16 | 1.3 | Complete | 2023
8077832b | 5G76 | Tier 2 | 0.24231 | 336 | 0.81769 | 16 |  | Complete | 2023
8077844a | 5G76 | Tier 3,Tier 2 | 0.24231 | 336 | 0.81769 | 16 | 3 | Complete | 2023
6811768c | 5G76/5G79 | Tier 2 |  |  |  |  | 1 | permitting | 2023 |  | Permitting - CPUC/Wetland
8286040q | 5G79 | Tier 2 | 0.1969 | 315 | 0.8308 | 13 | 1.5 | Complete | 2023
8077835a | 5G79 | Tier 3 | 0.1969 | 315 | 0.8308 | 13 | 3.6 | Complete | 2023
8077837a | 5G79 | Tier 3,Tier 2 | 0.1969 | 315 | 0.8308 | 13 | 2.1 | Construction | 2023
8077837b | 5G79 | Tier 3,Tier 2 | 0.1969 | 315 | 0.8308 | 13 |  | Construction | 2023
8077846a | 5G79 | Tier 2 | 0.1969 | 315 | 0.8308 | 13 | 1.3 | Complete | 2023
8077661 | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 0.5 | Materials | 2023
8077664 | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 5 | Construction | 2023
8077666 | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 4.6 | Construction | 2023
8077667 | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 4.4 | Complete | 2023
8003684a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 5.8 | Complete | 2023
8003684b | 5G83 | Tier 3 | 0.23987 | 258 | 0.65465 | 146 |  | Complete | 2023
8003684c | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Complete | 2023
8003685a | 5G83 | Tier 3,Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 5.6 | Complete | 2023
8003685b | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Complete | 2023
8003692a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 5.3 | Complete | 2023
8003692b | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Complete | 2023
8077663a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 1.7 | Construction | 2023
8077663b | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Construction | 2023
8077663c | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Construction | 2023
8077679a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 0.8 | Complete | 2023
8077680a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 5.9 | Complete | 2023
8077680b | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 |  | Complete | 2023
8281692a | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 0.3 | Complete | 2023
6993791 | 5R106 | Tier 2 | 0.19499 | 318 | 0.83849 | 11 | 1.3 | Complete | 2023
6810408a | 7G75 | Tier 2 | 0.22393 | 280 | 0.8767 | 5 | 0.2 | Complete | 2023
6810408b | 7G75 | Tier 2 | 0.22393 | 280 | 0.8767 | 5 |  | Complete | 2023
7011415 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 2.2 | Construction | 2023
7011422 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 2.3 | Design | 2023
7011426 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 4.5 | permitting | 2023
7011428 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 2.9 | permitting | 2023
7011435 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 3.8 | permitting | 2023
7011438 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 3.7 | permitting | 2023
7055586 | 5G40 | Tier 2 | 0.18287 | 337 | 0.61717 | 185 | 5.4 | Construction | 2023
8077672 | 8G95 | Tier 2 | 0.17195 | 366 | 0.87775 | 4 | 2.6 | Materials | 2023
8077673 | 8G95 | Tier 2 | 0.17195 | 366 | 0.87775 | 4 | 3 | Construction | 2023
8077674 | 8G95 | Tier 2 | 0.17195 | 366 | 0.87775 | 4 | 2.5 | Construction | 2023
8077675 | 5G39 | Tier 2 | 0.27166 | 224 | 0.77982 | 27 | 1.4 | Construction | 2023
8077678 | 5G39 | Tier 2 | 0.27166 | 224 | 0.77982 | 27 | 2.7 | Construction | 2023
8236604 | 5G39 | Tier 2 | 0.27166 | 224 | 0.77982 | 27 | 3.9 | Construction | 2023
8236605 | 5G39 | Tier 2 | 0.27166 | 224 | 0.77982 | 27 | 1.8 | Construction | 2023
8215499 | 7G81 | Tier 2 | 0.42244 | 140 | 0.67219 | 119 | 1 | Materials | 2023
8222503 | 5G76 | Tier 2 | 0.18364 | 336 | 0.81769 | 16 | 2.9 | Construction | 2023
8196598 | 5G83 | Tier 2 | 0.23987 | 258 | 0.65465 | 146 | 3.2 | Materials | 2023
8231406 | 5G79 | Tier 2 | 0.1969 | 315 | 0.8308 | 13 | 2.1 | Design | 2023
112.2
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See scores for separate circuits.
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See scores for separate circuits.