## Sheet1
(1) Circuit Name | (2) Mileage of Project | (3) Location of Project (City) | (4) 2023-2025 WMP Risk Score | (5) 2023-2025 WMP Risk Ranking | (6) 2025 WMP Risk Score | (7) 2025 WMP Risk Ranking | (8) Reasons for Delay (Constraint Type) | (10) Current Expected Date of Completion
ACOSTA | 0.54 | RANCHO CUCAMONGA |  | NA |  | NA | Pending Environmental | 2025-02-28
ACRES | 2.4 | SADDLEBACK |  | NA |  | NA | Pending Permit | 2025-08-01
ACRES | 0.23 | LAGUNA BEACH |  | NA |  | NA | Pending Environmental | 2025-09-15
ACROBAT | 0.42 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-09-15
ACROBAT | 0.21 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-09-15
ACROBAT | 0.37 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-06-01
ACROBAT | 0.14 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-09-15
AGATE | 0.94 | LAGUNA BEACH |  | NA |  | NA | Pending Environmental | 2025-09-15
ARBORETUM | 1.67 | MONROVIA |  | NA |  | NA | Pending Environmental | 2025-02-28
ARMOUR | 0.42 | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-02-28
ARMOUR | 0.62 | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-09-15
ARMOUR | 0.35 | SANTA BARBARA |  | NA |  | NA | Pending Rights Check | 2025-02-28
ARMOUR | 0.07 | SANTA BARBARA |  | NA |  | NA | Pending Permit | 2025-02-28
ARMOUR | 0.62 | SANTA BARBARA |  | NA |  | NA | Pending Permit | 2025-02-28
ARMOUR | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-03-30
ARMOUR | 2.96 |  |  | NA |  | NA | Pending Environmental | 2025-03-30
AUTUMN | 0.39 | MAMMOTH LAKES |  | NA |  | NA | Pending Environmental | 2025-03-30
AUTUMN | 0.24 | MAMMOTH LAKES |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-03-30
AUTUMN | 0.53 | MAMMOTH LAKES |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-03-30
AVENIDA | NA | SAN DIMAS |  | NA |  | NA | Pending Environmental | 2025-03-30
BABYLON | NA | WILDOMAR |  | NA |  | NA | Pending Environmental | 2025-03-30
BABYLON | 0.17 | WILDOMAR |  | NA |  | NA | Pending Environmental | 2025-03-30
BALCOM | NA | FILLMORE |  | NA |  | NA | Pending Environmental | 2025-01-02
BANANA | 0.15 | GLENDORA |  | NA |  | NA | Pending Environmental | 2025-01-02
BANANA | NA | GLENDORA |  | NA |  | NA | Pending Easement | 2025-02-28
BANTA | 0.71 | LEE VINING |  | NA |  | NA | Pending Rights Check | 2025-03-30
BAYLINER | 0.26 | CANYON LAKE |  | NA |  | NA | Pending Environmental | 2025-03-01
BAYLINER | 0.43 | CANYON LAKE |  | NA |  | NA | Pending Environmental | 2025-03-01
BAYLINER | 0.21 | CANYON LAKE |  | NA |  | NA | Pending Environmental | 2025-09-15
BAYLINER | 0.14 | CANYON LAKE |  | NA |  | NA | Pending Permit | 2025-01-01
BAYLINER | NA | CANYON LAKE |  | NA |  | NA | Pending Environmental | 2025-09-15
BEAR VALLEY | 1.33 | MENTONE |  | NA |  | NA | Pending Environmental | 2025-09-15
BIDDER | 0.27 | GOLETA |  | NA |  | NA | Pending Environmental | 2025-09-15
BIDDER | 0.2 | GOLETA |  | NA |  | NA | Pending Easement | 2025-03-28
BIDDER | 0.84 | GOLETA |  | NA |  | NA | Pending Environmental | 2025-09-15
BIDDER | NA | GOLETA |  | NA |  | NA | Pending Environmental | 2025-03-01
BIRCHIM | 1.04 | ROUND VALLEY |  | NA |  | NA | Pending Environmental | 2025-03-01
BIRCHIM | 0.75 | ROUND VALLEY |  | NA |  | NA | Pending Environmental | 2025-03-01
BIRCHIM | 0.06 | ROUND VALLEY |  | NA |  | NA | Pending Easement | 2025-06-15
BLACKBIRD | 0.3 | VALENCIA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-09-15
BLEDSOE | 2.2 | LANCASTER |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-09-15
BLEDSOE | 0.08 | LANCASTER |  | NA |  | NA | Pending Environmental | 2025-09-15
BLUE RIDGE | 0.54 | WRIGHTWOOD |  | NA |  | NA | Pending Environmental | 2025-09-15
BLUE RIDGE | 1.15 | WRIGHTWOOD |  | NA |  | NA | Pending Environmental | 2025-09-15
BOHEMIA | 0.13 | TUJUNGA |  | NA |  | NA | Pending Environmental | 2025-09-15
BOLLERO | 1.54 | NORCO |  | NA |  | NA | Pending Environmental | 2025-09-15
BONNEVILLE | 2.39 | MENIFEE |  | NA |  | NA | Pending Environmental | 2025-09-15
BOULDER | 0.34 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-03-16
BOULDER | 0.47 | HIGHLAND |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-05
BOULDER | 0.28 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-09-15
BOULDER | 0.31 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-03-01
BOULDER | 0.25 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-02-03
BOULDER | 0.49 | HIGHLAND |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-03
BOULDER | 0.39 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-09-15
BOULDER | 0.39 | HIGHLAND |  | NA |  | NA | Pending Redesign | 2025-09-15
BOULDER | 0.43 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-04-30
BOULDER | 0.41 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-02-03
BOULDER | 0.38 | HIGHLAND |  | NA |  | NA | Pending Environmental | 2025-04-30
BOULDER | 0.65 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-04-30
BRYN MAWR | 1.2 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-09-15
BRYN MAWR | 0.86 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-09-15
BUCKHORN | 0.5 | FILLMORE |  | NA |  | NA | Pending Environmental | 2025-06-15
BUCKTHORN | 0.57 | HESPERIA |  | NA |  | NA | Pending Environmental | 2025-08-01
BURGUNDY | 0.18 | RIALTO |  | NA |  | NA | Pending Environmental | 2025-08-01
BURGUNDY | 0.35 | RIALTO |  | NA |  | NA | Pending Environmental | 2025-08-01
BURGUNDY | 0.16 | RIALTO |  | NA |  | NA | Pending Environmental | 2025-08-01
BUTTERFIELD | 2.29 | CHINO HILLS |  | NA |  | NA | Pending Environmental | 2025-08-01
BUTTERFIELD | 0.32 | CHINO |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-01
BUTTERFIELD | 0.54 | CHINO |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-01-05
BUTTERFIELD | 0.29 | CHINO |  | NA |  | NA | Pending Environmental | 2025-09-15
CAL POLY | 0.96 | LA VERNE |  | NA |  | NA | Pending Environmental | 2025-09-15
CALGROVE | 0.12 | SANTA CLARITA |  | NA |  | NA | Pending Environmental | 2025-09-15
CALIBER | 0.16 | LITTLE ROCK |  | NA |  | NA | Pending Environmental | 2025-09-15
CALIBER | 0.67 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-04-30
CALIBER | 0.38 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-09-15
CALIBER | 0.5 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-09-15
CAMPBELL | 0.47 | PORTERVILLE |  | NA |  | NA | Pending Environmental | 2025-09-15
CAMPROCK | 0.3 | LUCERNE VALLEY |  | NA |  | NA | Pending Environmental | 2025-09-15
CAMPROCK | 0.13 | LUCERNE VALLEY |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | 1.4 | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | 1.8 | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | 0.77 | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | 2.43 | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | 12 | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANEBRAKE | NA | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-15
CANET | 0.09 | VENTURA |  | NA |  | NA | Pending Environmental | 2025-09-15
CANET | NA | VENTURA |  | NA |  | NA | Pending Environmental | 2025-09-15
CANTINA | 0.43 | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
CARANCHO | 3.07 | WILDOMAR |  | NA |  | NA | Pending Environmental | 2025-09-15
CARRIAGE | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
CARRIAGE | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
CARVER | 1.27 | DELANO |  | NA |  | NA | Pending Environmental | 2025-09-15
CARVER | 1.06 | DELANO |  | NA |  | NA | Pending Environmental | 2025-09-15
CASE | 0.38 | LAKE ELSINORE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-01
CASE | 0.33 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CATARACT | 0.57 | GLENDORA |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 0.17 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 0.27 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.32 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 0.52 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.27 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.04 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.18 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 0.99 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.6 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CEREAL | 1.32 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
CHARLIE | 0.32 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-09-15
CHARLIE | 0.66 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-09-15
CHARLIE | 0.31 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | 4.28 | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Rights Check | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COACHELLA | NA | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
COJO | 0.85 | GOLETA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-01
COJO | 0.79 | GOLETA |  | NA |  | NA | Pending Permit | 2025-02-01
COJO | 0.76 | GOLETA |  | NA |  | NA | Pending Environmental | 2025-03-01
COJO | 0.92 | GOLETA |  | NA |  | NA | Pending Environmental | 2025-09-15
COJO | NA | GOLETA |  | NA |  | NA | Pending Environmental | 2025-02-01
COLLIER | 0.35 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-09-15
COLT | 1.64 | MURRIETA |  | NA |  | NA | Pending Environmental | 2025-09-15
COLT | NA | MURRIETA |  | NA |  | NA | Pending Environmental | 2025-09-15
COLT | NA | MURRIETA |  | NA |  | NA | Pending Environmental | 2025-09-15
COLT | NA | MURRIETA |  | NA |  | NA | Pending Environmental | 2025-02-03
CONCEPCION | 0.77 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 0.49 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 0.81 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 0.11 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 0.11 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 1.31 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 0.14 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 1.52 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONCEPCION | 1.34 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.62 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.65 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.56 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.21 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.64 | BRIDGEPORT |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-09-15
CONWAY | 0.72 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.19 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
CONWAY | 0.27 | BRIDGEPORT |  | NA |  | NA | Pending Environmental | 2025-09-15
COOLER | 0.735 | TRABUCO CANYON |  | NA |  | NA | Pending Environmental | 2025-09-15
CORNELL | 1.2 | MENIFEE |  | NA |  | NA | Pending Environmental | 2025-09-15
COVE | 0.14 | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-09-15
CRABTREE | NA | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-09-15
CRUMNER | 4.95 | AGOURA HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
CRUZ | 0.04 | TEMECULA |  | NA |  | NA | Pending Environmental | 2025-09-15
CUSHENBURY | 0.63 | BIG BEAR |  | NA |  | NA | Pending Environmental | 2025-09-15
CUSHENBURY | 0.42 | BIG BEAR |  | NA |  | NA | Pending Environmental | 2025-03-30
CUSHENBURY | 0.86 | VICTORVILLE |  | NA |  | NA | Pending Environmental | 2025-03-30
CUTHBERT | 0.94 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-09-15
CUTHBERT | 0.71 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-02-01
CUTHBERT | 0.73 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-06-01
CUYAMA | NA | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-06-01
CUYAMA | 0.6 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-06-01
CUYAMA | NA | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-12-15
CUYAMA | 0.69 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-12-15
CUYAMA | 0.336 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-01-15
CUYAMA | 0.15 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-12-15
CUYAMA | 1.29 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-12-15
CUYAMA | NA | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-07-15
CUYAMA | 1.06 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-05-30
CUYAMA | 0.97 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-05-30
CUYAMA | 0.253 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-05-30
CUYAMA | 0.342 | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-05-30
DARTMOUTH | 2.52 | HEMET |  | NA |  | NA | Pending Rights Check | 2025-09-15
DEACON | 0.06 | PERRIS |  | NA |  | NA | Pending Environmental | 2025-05-30
DEALER | 0.45 | PINON HILLS |  | NA |  | NA | Pending Rights Check | 2025-06-30
DEL CARBON | 0.86 | CHINO HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
DEL CARBON | 1.32 | CHINO HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
DEL CARBON | 0.7 | CHINO HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
DEL CARBON | NA | CHINO HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
DEVINE | NA | THOUSAND OAKS |  | NA |  | NA | Pending Environmental | 2025-01-27
DEVINE | NA | THOUSAND OAKS |  | NA |  | NA | Pending Environmental | 2025-03-15
DEVINE | NA | THOUSAND OAKS |  | NA |  | NA | Pending Environmental | 2025-03-15
DOLORES | NA | ALTADENA |  | NA |  | NA | Pending Environmental | 2025-08-01
DONNER | 0.25 | CORONA |  | NA |  | NA | Pending Environmental | 2025-06-12
DONNER | 0.22 | CORONA |  | NA |  | NA | Pending Environmental | 2025-06-01
DONNER | 0.25 | CORONA |  | NA |  | NA | Pending Environmental | 2025-06-01
DRISKILL | 5.64 | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-06-01
DRISKILL | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-03-15
EBERT | 0.28 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-01-15
EGMONT | 0.29 | SAN DIMAS |  | NA |  | NA | Pending Environmental | 2025-01-15
EL MIRADOR | 1.98 | STRATHMORE |  | NA |  | NA | Pending Environmental | 2025-06-30
EL MIRADOR | 0.55 | STRATHMORE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 1.14 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 0.95 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 0.81 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 0.37 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 1.3 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ELSTER | 0.73 | SPRINGVILLE |  | NA |  | NA | Pending Environmental | 2025-11-30
ENCANTO | 0.64 | GOLETA |  | NA |  | NA | Pending Environmental | 2025-11-30
ENCANTO | NA | GOLETA |  | NA |  | NA | Pending Environmental | 2025-11-30
FAIRLANE | 0.95 | RIALTO |  | NA |  | NA | Pending Environmental | 2025-11-30
FANO | 1.01 | UPLAND |  | NA |  | NA | Pending Environmental | 2025-11-30
FARMINGTON | 0.09 | MENIFEE |  | NA |  | NA | Pending Environmental | 2025-11-30
FAYE | 2.18 | WELDON |  | NA |  | NA | Pending Environmental | 2025-11-30
FAYE | 2.76 | WELDON |  | NA |  | NA | Pending Environmental | 2025-11-30
FAYE | 1.66 | WELDON |  | NA |  | NA | Pending Environmental | 2025-11-30
FLYCATCHER | 0.17 | ISABELLA |  | NA |  | NA | Pending Environmental | 2025-11-30
FLYCATCHER | NA | MOUNTAIN MESA |  | NA |  | NA | Pending Environmental | 2025-11-30
FLYCATCHER | NA | MOUNTAIN MESA |  | NA |  | NA | Pending Permit | 2025-03-31
FLYING D | 0.37 | HAVILAH |  | NA |  | NA | Pending Environmental | 2025-04-15
FRISBIE | 0.35 | RIALTO |  | NA |  | NA | Pending Pause for TUG | 2025-04-07
GALENA | 0.84 | JURUPA VALLEY |  | NA |  | NA | Pending Permit | 2025-08-01
GREEN RIVER | 0.22 | YORBA LINDA |  | NA |  | NA | Pending Environmental | 2025-02-01
GRIDLOCK | 0.393 | WALNUT |  | NA |  | NA | Pending Permit | 2025-02-01
HARNAGE | 0.08 | MENIFEE |  | NA |  | NA | Pending Environmental | 2025-11-01
HASS | 0.13 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-09-15
HIGHBALL | 1.33 | JURUPA VALLEY |  | NA |  | NA | Pending Environmental | 2025-02-28
HOPE | 0.38 | RANCHO CUCAMONGA |  | NA |  | NA | Pending Environmental | 2025-02-28
HORIZON | NA | HIDDEN HILLS |  | NA |  | NA | Pending Environmental | 2025-03-30
HORIZON | NA | HIDDEN HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
HORIZON | NA | HIDDEN HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
HORIZON | NA | HIDDEN HILLS |  | NA |  | NA | Pending Permit | 2025-03-03
HORIZON | NA | HIDDEN HILLS |  | NA |  | NA | Pending Redesign | 2025-06-30
HOSPAT | 0.6 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-03-30
HOVATTER | 0.76 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-03-30
INVADER | 5.41 | PALM SPRINGS |  | NA |  | NA | Pending Environmental | 2025-12-15
INVADER | 1.34 | WHITEWATER |  | NA |  | NA | Pending Environmental | 2025-12-15
KEENE | 0.71 | TEHACHAPI |  | NA |  | NA | Pending Rights Check | 2025-06-30
KEENE | 15.1 | TEHACHAPI |  | NA |  | NA | Pending Rights Check | 2025-06-30
KEENE | NA | TEHACHAPI |  | NA |  | NA | Pending Environmental | 2025-06-01
KEENE | NA | TEHACHAPI |  | NA |  | NA | Pending Rights Check | 2025-07-30
KENO | 0.19 | PHELAN |  | NA |  | NA | Pending Rights Check | 2025-08-30
KEWAMEE | 1.47 | SADDLEBACK |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
KICKAPOO TRAIL | NA | YUCCA VALLEY |  | NA |  | NA | Pending Rights Check | 2025-04-01
KILTS | 0.24 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-04-30
KILTS | 0.38 | REDLANDS |  | NA |  | NA | Pending Rights Check | 2025-04-30
KILTS | 0.14 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-06-28
KINSEY | 0.86 | QUARTZ HILL |  | NA |  | NA | Pending Rights Check | 2025-06-30
KINSEY | 0.98 | QUARTZ HILL |  | NA |  | NA | Pending Rights Check | 2025-06-28
KINSEY | 1.07 | QUARTZ HILL |  | NA |  | NA | Pending Rights Check | 2025-07-31
KINSEY | 0.51 | QUARTZ HILL |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-01
KINSEY | 0.88 | QUARTZ HILL |  | NA |  | NA | Pending Environmental | 2025-05-01
KINSEY | 0.05 | QUARTZ HILL |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-05
KINSEY | 1.24 | QUARTZ HILL |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-01
KINSEY | 1.04 | QUARTZ HILL |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-05
KINSEY | 0.74 | QUARTZ HILL |  | NA |  | NA | Pending Environmental | 2025-06-01
KINSEY | 0.86 | QUARTZ HILL |  | NA |  | NA | Pending Environmental | 2025-06-01
KINSEY | 0.064 | QUARTZ HILL |  | NA |  | NA | Pending Environmental | 2025-06-01
KINSEY | NA | QUARTZ HILL |  | NA |  | NA | Pending Rights Check | 2025-01-15
KIRBY | 0.34 |  |  | NA |  | NA | Pending Environmental | 2025-06-01
LAKELAND | 0.59 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-06-01
LAKELAND | 0.38 | LAKE ELSINORE |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
LAKELAND | 0.28 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-06-01
LAKELAND | 0.21 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-06-01
LAKELAND | 0.27 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-06-01
LAKELAND | 0.17 | LAKE ELSINORE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-03-01
LAKELAND | 1.15 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-05-01
LAKELAND | 1.25 | LAKE ELSINORE |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
LAKELAND | 1.08 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-05-01
LAKELAND | 2.14 | LAKE ELSINORE |  | NA |  | NA | Pending Environmental | 2025-04-01
LARCH | 0.12 | RIALTO |  | NA |  | NA | Pending Environmental | 2025-04-01
LASKER | 0.05 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-04-01
LASKER | 0.06 | PALMDALE |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | 4.62 |  |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | NA | COLTON |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | NA | COLTON |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | 0.35 | COLTON |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | NA | COLTON |  | NA |  | NA | Pending Environmental | 2025-04-01
LIMONITE | NA | COLTON |  | NA |  | NA | Pending Rights Check | 2025-04-01
LUISENO | 1.1 | TEMECULA |  | NA |  | NA | Pending Permit | 2025-03-01
LYONS | 0.26 | VARIOUS |  | NA |  | NA | Pending Permit | 2025-03-01
MAGOO | 0.51 | RANCHO CUCAMONGA |  | NA |  | NA | Pending Permit | 2025-04-01
MAHOGANY | 6.91 | CAMP NELSON |  | NA |  | NA | Pending Easement | 2025-04-01
MC ALLISTER | 0.21 | RIVERSIDE |  | NA |  | NA | Pending Easement | 2025-04-01
MCBEAN | 0.05 | NEWHALL |  | NA |  | NA | Pending Permit | 2025-03-31
MCBEAN | NA | NEWHALL |  | NA |  | NA | Pending Environmental | 2025-04-01
MCBEAN | NA | NEWHALL |  | NA |  | NA | Pending Environmental | 2025-06-01
MCBEAN | NA | NEWHALL |  | NA |  | NA | Pending Environmental | 2025-07-01
MCBEAN | NA | NEWHALL |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-05-05
MCGEE | 1.4 | BISHOP |  | NA |  | NA | Pending Permit | 2025-05-31
MCGEE | 1.3 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-05-31
MCGEE | 0.26 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-05-31
MCGEE | 1.14 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-05-05
MCGEE | 0.63 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-05-31
MEDUSA | 0.22 | SAN BERNARDINO |  | NA |  | NA | Pending Permit | 2025-03-31
MEDUSA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-07-01
MEDUSA | 0.37 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-08-01
MEDUSA | 0.26 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-05-01
MEDUSA | 0.1 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-05-01
MEDUSA | 0.16 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-05-01
MEDUSA | 0.06 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-05-01
MEDUSA | 0.1 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-12-15
MEMPHIS | NA | YUCAIPA |  | NA |  | NA | Pending Environmental | 2025-12-15
MINT CANYON | 0.05 | SAUGUS |  | NA |  | NA | Pending Environmental | 2025-05-01
MOCCASIN | 0.15 | SAUGUS |  | NA |  | NA | Pending Environmental | 2025-05-01
MONACHE | 0.279 | PORTERVILLE |  | NA |  | NA | Pending Environmental | 2025-03-01
MORONGO | 0.51 | MORONGO VALLEY |  | NA |  | NA | Pending Environmental | 2025-03-01
MORONGO | 1.13 | MORONGO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-04-30
MOSQUITO | 0.63 | CHINO |  | NA |  | NA | Pending Environmental | 2025-04-01
MUSTANG | 1.39 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Rights Check | 2025-01-30
MUSTANG | 1.43 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Permit | 2025-02-28
MUSTANG | NA | WOFFORD HEIGHTS |  | NA |  | NA | Pending Permit | 2025-02-28
MUSTANG | 0.94 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Associated Project | 2025-09-30
MUSTANG | 1.76 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Rights Check | 2025-03-30
MUSTANG | 1.96 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Associated Project | 2025-09-30
MUSTANG | 1.1 | WOFFORD HEIGHTS |  | NA |  | NA | Pending Environmental | 2025-03-30
NA | 13.7 | BISHOP |  | NA |  | NA | Pending Associated Project | 2025-09-30
NA | NA | VARIOUS |  | NA |  | NA | Pending Associated Project | 2025-09-30
NA | NA | GOLETA |  | NA |  | NA | Pending Environmental | 2025-09-30
NA | NA | GOLETA |  | NA |  | NA | Pending Environmental | 2025-09-30
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Easement | 2025-02-01
NA | 2.73 | VENTURA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | CARPINTERIA |  | NA |  | NA | Pending Environmental | 2025-06-15
NA | NA | PALM SPRINGS |  | NA |  | NA | Pending Rights Check | 2025-06-01
NA | 3.5 | LOS ANGELES |  | NA |  | NA | Pending Environmental | 2025-06-15
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-06-01
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-06-01
NA | NA | RIALTO |  | NA |  | NA | Pending Environmental | 2025-06-01
NA | NA | RIALTO |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | NA | RIALTO |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | NA | RIALTO |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | NA | VARIOUS |  | NA |  | NA | Pending Environmental | 2025-06-01
NA | 5.42 | LANCASTER |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | COLTON |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | SAUGUS |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | SAUGUS |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | VARIOUS |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-07-01
NA | NA | THOUSAND OAKS |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-02
NA | NA | THOUSAND OAKS |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-07-07
NA | 1.62 | SAN FERNANDO |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-09
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-09
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-09
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-02
NA | 0.37 | RIVERSIDE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | 0.54 | SANTA BARBARA |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | NA | VENTURA |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | 0.48 | COTO DE CAZA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | 1.4 | RIVERSIDE |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | 1.02 | LEONA VALLEY |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | NA | WELDON |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | NA | WELDON |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | NA | WELDON |  | NA |  | NA | Pending Pause for TUG | 2025-12-15
NA | NA | WELDON |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | WELDON |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | WELDON |  | NA |  | NA | Pending Environmental | 2025-10-01
NA | NA | WELDON |  | NA |  | NA | Pending Environmental | 2025-12-15
NA | NA | WELDON |  | NA |  | NA | Pending Environmental | 2025-09-01
NA | NA | WELDON |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | 0.76 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | 0.76 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-05-01
NA | 0.76 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-06-01
NA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-03-30
NA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-10-01
NA | NA | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | 0.69 | THOUSAND OAKS |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | 1.13 | AGOURA HILLS |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | 0.94 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-10-06
NA | 2.43 |  |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-08-04
NA | 1.55 | ALTADENA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-07-07
NA | 0.32 | LEBEC |  | NA |  | NA | Pending Environmental | 2025-09-01
NA | 0.95 | TORRANCE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | ALTADENA |  | NA |  | NA | Pending Environmental | 2025-07-01
NA | NA | ALTADENA |  | NA |  | NA | Pending Environmental | 2025-10-01
NA | NA | ALTADENA |  | NA |  | NA | Pending Environmental | 2025-11-30
NA | NA | VENTURA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-08-04
NA | NA | VENTURA |  | NA |  | NA | Pending Permit | 2025-09-01
NA | NA | VENTURA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-04-01
NA | NA | VENTURA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | VENTURA |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | VENTURA |  | NA |  | NA | Pending Environmental | 2025-07-15
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-07-15
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-12-15
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-12-15
NA | NA |  |  | NA |  | NA | Pending Environmental | 2025-09-01
NA | NA | TORRANCE |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | NA | TORRANCE |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | 2.79 | CAMARILLO |  | NA |  | NA | Pending Easement | 2025-04-01
NA | 2.79 | CAMARILLO |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | 2.79 | CAMARILLO |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-11-15
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | 1.76 | VENTURA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | 1.76 | VENTURA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | 14.5 | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-04-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Easement | 2025-10-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Easement | 2025-10-01
NA | 14.5 | LA CONCHITA |  | NA |  | NA | Pending Easement | 2025-10-01
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-08-31
NA | NA | LA CONCHITA |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | 0.45 | THOUSAND OAKS |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | 1.13 | AGOURA HILLS |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-15
NA | NA | WHITTIER |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-09-01
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-04-30
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-08-15
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-01
NA | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | 0.16 | SOMIS |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | 2.96 | SANTA BARBARA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
NA | NA | GRAND TERRACE |  | NA |  | NA | Pending Environmental | 2025-10-31
NA | NA | GRAND TERRACE |  | NA |  | NA | Pending Environmental | 2025-11-30
NA | NA | GRAND TERRACE |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | GRAND TERRACE |  | NA |  | NA | Pending Environmental | 2025-08-01
NA | NA | SANTA BARBARA |  | NA |  | NA | Pending Environmental | 2025-10-31
NICHOLAS | 0.34 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-08-04
NICHOLAS | 0.11 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-09-01
NICHOLAS | 0.18 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-09-01
NICHOLAS | 0.15 | MALIBU |  | NA |  | NA | Pending Environmental | 2025-09-01
NICKLIN | 0.2 | FONTANA |  | NA |  | NA | Pending Environmental | 2025-09-01
NORTHPARK | 1.4 | SAN BERNARDINO |  | NA |  | NA | Pending Environmental | 2025-09-01
OAKDALE | 3.79 | MENIFEE |  | NA |  | NA | Pending Environmental | 2025-09-01
OLIVER | 0.32 | MORENO VALLEY |  | NA |  | NA | Pending Environmental | 2025-09-01
OLIVER | 3.79 | PERRIS |  | NA |  | NA | Pending Environmental | 2025-09-01
O'TOOLE | 0.6 | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-01
O'TOOLE | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-01
O'TOOLE | NA | WHITTIER |  | NA |  | NA | Pending Environmental | 2025-09-01
OWENS | 0.76 | CORONA |  | NA |  | NA | Pending Environmental | 2025-09-01
OWENS | 0.12 | CORONA |  | NA |  | NA | Pending Environmental | 2025-09-01
OWENS | NA | CORONA |  | NA |  | NA | Pending Environmental | 2025-09-01
OWENS | 1.77 | CORONA |  | NA |  | NA | Pending Associated Project | 2025-09-30
OWENS | 1.58 | CORONA |  | NA |  | NA | Pending Environmental | 2025-07-01
PALMER | 0.23 | LA VERNE |  | NA |  | NA | Pending Environmental | 2025-09-15
PARCO | 0.15 | JURUPA VALLEY |  | NA |  | NA | Pending Environmental | 2025-10-01
PASCAL | 4.15 | HEMET |  | NA |  | NA | Pending Environmental | 2025-12-31
PASCAL | 2.33 | HEMET |  | NA |  | NA | Pending Environmental | 2025-12-15
PASCAL | NA | HEMET |  | NA |  | NA | Pending Environmental | 2025-11-30
PAWLEY | 48.4 | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-11-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-11-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-11-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-11-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-12-15
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Permit | 2025-09-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Permit | 2025-09-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-09-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Permit | 2025-09-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-09-30
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-11-29
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-15
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-11-04
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-11-04
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-10-01
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-10-31
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-03-31
PAWLEY | NA | THREE RIVERS |  | NA |  | NA | Pending Environmental | 2025-09-15
PEARCE | 0.37 | VENTURA |  | NA |  | NA | Pending Environmental | 2025-10-15
PERIMETER | 16 | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-06-01
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-09-15
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-11-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-12-31
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-03-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-10-31
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-12-31
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-10-31
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-03
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-09-01
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-06-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-06-01
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-06-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-06-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Rights Check | 2025-06-01
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Associated Project | 2025-09-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Associated Project | 2025-09-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Associated Project | 2025-09-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Associated Project | 2025-09-30
PERIMETER | NA | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-03-01
PERIMETER | 16 | SHAVER LAKE |  | NA |  | NA | Pending Environmental | 2025-03-01
PERRIS | 0.02 | PERRIS |  | NA |  | NA | Pending Pause for TUG | 2025-09-30
PETIT | 6.68 | SANTA PAULA |  | NA |  | NA | Pending Pause for TUG | 2025-09-30
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Environmental | 2025-04-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Environmental | 2025-04-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-01-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-01-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Rights Check | 2025-09-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Easement | 2025-09-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-04-01
PETIT | NA | SANTA PAULA |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-08-01
PHOTON | 1.43 | WINCHESTER |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-01
PHOTON | NA | WINCHESTER |  | NA |  | NA | Pending Easement | 2025-09-15
PICKLE MEADOWS | 2.58 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-06-01
PICKLE MEADOWS | 3.3 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-01
PICKLE MEADOWS | 0.4 | BISHOP |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-02-01
PICKLE MEADOWS,STROSNIDER | 2.01 | BRIDGEPORT |  | NA |  | NA | Pending Redesign | 2025-06-30
PINTO | 10 | YUCCA VALLEY |  | NA |  | NA | Pending Redesign | 2025-06-30
PINTO | NA | YUCCA VALLEY |  | NA |  | NA | Pending Environmental | 2025-06-30
PLATEAU | 0.22 | CALABASAS |  | NA |  | NA | Pending Rights Check | 2025-02-01
POULTRY | 2.92 | MENTONE |  | NA |  | NA | Pending Rights Check | 2025-08-31
POULTRY | 1.5 | REDLANDS |  | NA |  | NA | Pending Environmental | 2025-11-30
PRONGHORN | 0.62 | LANCASTER |  | NA |  | NA | Pending Environmental | 2025-11-30
PYLE | 0.07 | SANTA PAULA |  | NA |  | NA | Pending Rights Check | 2025-07-01
QUARRY | NA | NORCO |  | NA |  | NA | Pending Rights Check | 2025-07-01
QUARRY | NA | NORCO |  | NA |  | NA | Pending Environmental | 2025-09-30
QUARRY | NA | NORCO |  | NA |  | NA | Pending Environmental | 2025-09-30
QUARRY | NA | NORCO |  | NA |  | NA | Pending Environmental | 2025-04-15
RAMAC | 1.13 | VARIOUS |  | NA |  | NA | Pending Rights Check | 2025-11-30
RAMAC | 0.919 | VARIOUS |  | NA |  | NA | Pending Rights Check | 2025-01-15
RAMAC | 0.6 | VARIOUS |  | NA |  | NA | Pending Rights Check | 2025-01-15
RAYBURN | 0.05 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-01-15
RAYBURN | 0.28 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-12-15
RED MOUNTAIN | 0.17 | VENTURA |  | NA |  | NA | Pending Rights Check | 2025-05-01
RED MOUNTAIN | 0.18 | VENTURA |  | NA |  | NA | Pending Rights Check | 2025-06-01
RESORT | 4.39 | MOUNTAIN CENTER |  | NA |  | NA | Pending Rights Check | 2025-08-31
RESORT | 0.92 | MOUNTAIN CENTER |  | NA |  | NA | Pending Rights Check | 2025-07-31
RESORT | 0.48 | MOUNTAIN CENTER |  | NA |  | NA | Pending Rights Check | 2025-05-30
RESORT | NA | MOUNTAIN CENTER |  | NA |  | NA | Pending Rights Check | 2025-06-15
RESORT | 1.98 | HEMET |  | NA |  | NA | Pending Rights Check | 2025-05-30
RESORT | 0.96 | HEMET |  | NA |  | NA | Pending Rights Check | 2025-05-30
RESORT | 0.44 | HEMET |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | 0.68 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | 0.24 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | 0.25 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | 0.3 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-05-30
REVERSE PEAK | 0.46 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | 0.11 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | 0.41 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.06 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.07 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-04-01
REVERSE PEAK | 0.29 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-04-01
REVERSE PEAK | 0.07 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-31
REVERSE PEAK | 0.05 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.4 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.45 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.33 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-08-30
REVERSE PEAK | 0.07 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-16
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-04-30
REVERSE PEAK | 0.94 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-07-31
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-07-31
REVERSE PEAK | 0.18 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-31
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-31
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-30
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-07-31
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-04-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-04-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Easement | 2025-04-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Easement | 2025-04-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-06-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-06-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-06-01
REVERSE PEAK | 0.6 | BISHOP |  | NA |  | NA | Pending Environmental | 2025-04-01
REVERSE PEAK | 0.6 | BISHOP |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
REVERSE PEAK | NA | BISHOP |  | NA |  | NA | Pending Environmental | 2025-06-01
RHODA | 0.75 | AGOURA HILLS |  | NA |  | NA | Pending Environmental | 2025-06-01
RIDGE | NA | LEBEC |  | NA |  | NA | Pending Rights Check | 2025-04-15
RIDGE | 0.75 | LEBEC |  | NA |  | NA | Pending Rights Check | 2025-04-15
RIDGEMOOR | 1.22 | MENIFEE |  | NA |  | NA | Pending Rights Check | 2025-04-15
RIVIERA | 1.04 | SANTA BARBARA |  | NA |  | NA | Pending Rights Check | 2025-04-15
RMV 1243 | 1.26 | LAKE ELSINORE |  | NA |  | NA | Pending Rights Check | 2025-04-15
ROBIN | 1.66 | WRIGHTWOOD |  | NA |  | NA | Pending Rights Check | 2025-04-01
ROBIN | 0.63 | WRIGHTWOOD |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
ROBINSON CREEK | 1.24 | BISHOP MAMMOTH LAKE |  | NA |  | NA | Pending Rights Check | 2025-05-30
ROBINSON CREEK | 0.78 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-05-30
ROBINSON CREEK | 0.7 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-07-01
ROBINSON CREEK | 0.81 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-05-01
ROBINSON CREEK | 0.7 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-05-01
ROBINSON CREEK | 0.49 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-03-15
ROBINSON CREEK | 0.5 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-15
ROBINSON CREEK | 0.42 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-07-01
ROCKCREEK | 1.12 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-07-01
ROCKCREEK | 0.86 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-07-01
ROCKRIDGE | 0.78 | LAKE ELSINORE |  | NA |  | NA | Pending Rights Check | 2025-07-01
ROI-TAN | 0.42 | REDLANDS |  | NA |  | NA | Pending Rights Check | 2025-08-31
ROI-TAN | 0.93 | FOOTHILL RANCH |  | NA |  | NA | Pending Rights Check | 2025-08-31
ROI-TAN | 0.94 | SAN BERNARDINO |  | NA |  | NA | Pending Rights Check | 2025-08-31
ROI-TAN | 0.94 | SAN BERNARDINO |  | NA |  | NA | Pending Rights Check | 2025-08-31
ROS | 0.51 | APPLE VALLEY |  | NA |  | NA | Pending Rights Check | 2025-08-31
SABRINA | 0.86 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-06-01
SABRINA | 0.86 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-06-01
SAGEHEN | 1.83 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-08-31
SAGEHEN | 0.155 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-30
SAGEHEN | 0.923 | BENTON |  | NA |  | NA | Pending Permit | 2025-08-04
SAGEHEN | 0.94 | BENTON |  | NA |  | NA | Pending Permit | 2025-08-04
SAGEHEN | 0.43 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-08-30
SAGEHEN | 0.049 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-01
SAGEHEN | 0.48 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-04
SAGEHEN | 0.519 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-04
SAGEHEN | 0.07 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-04
SAGEHEN | 0.619 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-05-01
SAGEHEN | 0.633 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-12-15
SAGEHEN | 0.44 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-08-01
SAGEHEN | 1.19 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-08-01
SAGEHEN | 0.71 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-01
SAGEHEN | 0.58 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-01
SAGEHEN | 1.05 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-09-01
SAGEHEN | 1.18 | BENTON |  | NA |  | NA | Pending Environmental | 2025-09-01
SAGEHEN | 1.19 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-10-01
SAGEHEN | 0.94 | BENTON |  | NA |  | NA | Pending Rights Check | 2025-10-01
SALT CREEK | 1.92 | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-09-04
SALT CREEK | 2.78 | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-09-04
SALT CREEK | 1.96 | THREE RIVERS |  | NA |  | NA | Pending Rights Check | 2025-09-04
SEACLIFF | 15 | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-01
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-30
SEACLIFF | 0.52 | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-30
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-05-05
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-04
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-04
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-04
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-09-01
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-07-07
SEACLIFF | 0.97 | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
SEACLIFF | NA | CARPINTERIA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEACLIFF | 14.5 | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEACLIFF | NA | LA CONCHITA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SEMINARY | 0.16 | SOMIS |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
SERRA | 0.52 | MALIBU |  | NA |  | NA | Pending Pause for TUG | 2025-04-01
SERRA | 0.68 | MALIBU |  | NA |  | NA | Pending Rights Check | 2025-10-30
SHASTA | 0.21 | YUCAIPA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SHASTA | 0.21 | YUCAIPA |  | NA |  | NA | Pending Rights Check | 2025-10-30
SHASTA | 0.24 | YUCAIPA |  | NA |  | NA | Pending Environmental | 2025-08-01
SHASTA | 0.15 | YUCAIPA |  | NA |  | NA | Pending Rights Check | 2025-12-01
SHEFFIELD | 0.32 | MONTECITO |  | NA |  | NA | Pending Rights Check | 2025-07-01
SHEFFIELD | 0.2 | MONTECITO |  | NA |  | NA | Pending Rights Check | 2025-07-01
SHEFFIELD | 0.69 | MONTECITO |  | NA |  | NA | Pending Rights Check | 2025-07-07
SHEFFIELD | 0.28 | MONTECITO |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHERATON | 0.16 | PALM SPRINGS |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHETLAND | 2.03 | MURRIETA |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHETLAND | NA | MURRIETA |  | NA |  | NA | Pending Rights Check | 2025-12-15
SHETLAND | NA | MURRIETA |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHIRAZ | 0.29 | SAN BERNARDINO |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHIRAZ | 0.36 | SAN BERNARDINO |  | NA |  | NA | Pending Rights Check | 2025-09-01
SHIRAZ | 0.22 | SAN BERNARDINO |  | NA |  | NA | Pending Rights Check | 2025-09-01
SIMS | 0.69 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-09-01
SIMS | 0.55 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-09-01
SINKER | 0.97 | BISHOP |  | NA |  | NA | Pending Rights Check | 2025-09-01
SKI | 0.46 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-09-01
SKI | 0.52 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-07-01
SKI | 0.45 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-10-30
SKI | 0.49 | MAMMOTH LAKES |  | NA |  | NA | Pending Public/Government Lands Clearance | 2025-08-01
SKI | 0.48 | MAMMOTH LAKES |  | NA |  | NA | Pending Environmental | 2025-09-15
SKI | 0.42 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-09-30
SKI | 0.34 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-09-30
SKI | 0.02 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-09-30
SLOPE | 1.06 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-11-15
SNOW VALLEY | 0.15 | RUNNING SPRINGS |  | NA |  | NA | Pending Rights Check | 2025-08-01
SNOWCREEK | 0.68 | WHITEWATER |  | NA |  | NA | Pending Rights Check | 2025-11-30
SODA SPRINGS | NA | SPRINGVILLE |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | 7.32 | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-11-09
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-08-01
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-01
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-01
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-07-01
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-08-01
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SOPHIE | NA | PERRIS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SPARLING | 0.11 | REDLANDS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SPLENDOR | 0.25 | THOUSAND OAKS |  | NA |  | NA | Pending Rights Check | 2025-12-30
SPRAGUE | 2.22 | HEMET |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | 8.7 | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STATLER | NA | ROLLING HILLS |  | NA |  | NA | Pending Rights Check | 2025-12-30
STEEL | 0.62 | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-12-30
STEEL | 0.45 | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-08-01
STEEL | 0.35 | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-09-30
STEEL | NA | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-01
STEEL | 0.28 | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-01
STEEL | NA | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-01
STEEL | NA | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-15
STEEL | 0.41 | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-15
STEEL | NA | MORENO VALLEY |  | NA |  | NA | Pending Rights Check | 2025-11-04
STROSNIDER | 0.54 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-10-01
STROSNIDER | 0.57 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-10-01
STROSNIDER | 0.53 | BRIDGEPORT |  | NA |  | NA | Pending Rights Check | 2025-10-01
STUTZ | 3.08 | WHITTIER |  | NA |  | NA | Pending Rights Check | 2025-10-01
SUCCESS | 1.38 |  |  | NA |  | NA | Pending Rights Check | 2025-10-01
SUCCESS | NA | PORTERVILLE |  | NA |  | NA | Pending Rights Check | 2025-12-31
SUCCESS | NA | PORTERVILLE |  | NA |  | NA | Pending Rights Check | 2025-07-30
SUN VILLAGE | 0.3 | PALMDALE |  | NA |  | NA | Pending Rights Check | 2025-07-30
SUSAN | 0.35 | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-07-30
SUSAN | 0.42 | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-07-30
SUSAN | 0.41 | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-12-01
SUSAN | 0.19 | RIALTO |  | NA |  | NA | Pending Pause for TUG | 2025-12-31
SUSAN | 0.12 | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-12-01
SUSAN | NA | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-12-01
SUSAN | NA | RIALTO |  | NA |  | NA | Pending Rights Check | 2025-12-01
SWIFT | 0.72 | MONTECITO |  | NA |  | NA | Pending Rights Check | 2025-12-01
TAHQUITZ | 2.7 | IDYLLWILD |  | NA |  | NA | Pending Rights Check | 2025-12-01
TAHQUITZ | 0.81 | IDYLLWILD |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.49 | LAKE HUGHE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.58 | LAKE HUGHE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.1 | LAKE HUGHE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.04 | LAKE HUGHE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.08 | LAKE HUGHE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 1.43 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.096 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.3 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.17 | LANCASTER |  | NA |  | NA | Pending Permit | 2025-10-01
TEJON | 1.26 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | 0.11 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-11-30
TEJON | 0.59 | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TEJON | NA | LANCASTER |  | NA |  | NA | Pending Rights Check | 2025-12-01
TERMINUS | 0.93 | LEMON COVE |  | NA |  | NA | Pending Rights Check | 2025-12-01
THORNTON | 0.21 | VALLE VISTA |  | NA |  | NA | Pending Rights Check | 2025-12-01
TIMBER CANYON | 0.39 | FILLMORE |  | NA |  | NA | Pending Rights Check | 2025-12-01
TITAN | 0.61 | LITTLEROCK |  | NA |  | NA | Pending Rights Check | 2025-12-01
TITAN | 0.315 | LITTLEROCK |  | NA |  | NA | Pending Rights Check | 2025-09-30
TITAN | 0.487 | LITTLEROCK |  | NA |  | NA | Pending Permit | 2025-09-30
TITAN | 0.104 | LITTLEROCK |  | NA |  | NA | Pending Permit | 2025-09-30
TONNER | 0.493 | BREA |  | NA |  | NA | Pending Permit | 2025-09-30
TORONTO | 0.2 | LAKE ARROWHEAD |  | NA |  | NA | Pending Permit | 2025-09-30
TORONTO | 0.96 | LAKE ARROWHEAD |  | NA |  | NA | Pending Permit | 2025-09-30
TRAM | 2.97 | PALM SPRINGS |  | NA |  | NA | Pending Permit | 2025-09-30
TRAUTWEIN | 0.45 | WOODCREST |  | NA |  | NA | Pending Permit | 2025-09-30
TROUT | 0.3 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.01 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.42 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.31 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.43 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.39 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | 0.19 | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TROUT | NA | MAMMOTH LAKES |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUBA | 0.32 | CASTAIC |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUBA | 1.88 | CASTAIC |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUBA | 2.17 | CASTAIC |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUFA | 0.39 | LEE VINING |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUNA | 0.28 | MALIBU |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUNA | 0.68 | MALIBU |  | NA |  | NA | Pending Rights Check | 2025-12-01
TUNA | 0.29 | MALIBU |  | NA |  | NA | Pending Rights Check | 2025-12-01
TYPHOON | 0.15 | YORBA LINDA |  | NA |  | NA | Pending Rights Check | 2025-12-01
UTE | 0.85 | VICTORVILLE |  | NA |  | NA | Pending Rights Check | 2025-11-01
VANDERLIP | 1.09 |  |  | NA |  | NA | Pending Rights Check | 2025-11-01
VANDERLIP | 0.54 | RANCHO PALOS VERDES |  | NA |  | NA | Pending Rights Check | 2025-12-29
VERA CRUZ | 0.61 | BREA |  | NA |  | NA | Pending Rights Check | 2025-12-01
VERDUGO | 3.12 | LOS ANGELES |  | NA |  | NA | Pending Rights Check | 2025-10-06
VERDUGO | NA | LOS ANGELES |  | NA |  | NA | Pending Environmental | 2025-10-06
VERDUGO | NA | LOS ANGELES |  | NA |  | NA | Pending Environmental | 2025-10-06
WAHOO | 0.56 | DIAMOND BAR |  | NA |  | NA | Pending Permit | 2025-10-01
WINNEBAGO | NA | JURUPA VALLEY |  | NA |  | NA | Pending Permit | 2025-12-01
ZIRCON | 0.73 | ROLLING HILLS ESTATES |  | NA |  | NA | Pending Pause for TUG | 2025-12-15