## 2025 Risk Reduction Estimate
Future Year Planning | (All) | Step 0: All 2025 System Hardening Workplan (Miles and Est. Risk Reduction) Reference existing workplan with all projects and associated miles and risk reduction in 2025.
MAT | (Multiple Items)
Values
SAP Status | 2025 Forecast OH Miles | 2025 V3 OH Risk Reduction | 2025 Forecast UG Miles | 2025 V3 UG Risk Reduction | 2025 Forecast Removal Miles | 2025 V3 Removal Risk Reduction | 2025 Total Miles | 2025 Total V3 Risk Reduction
UNSE | 133.6817 | 1.181% | 448.762 | 4.872% | 31.8212 | 0.1914% | 614.2649 | 6.244%
ESTS | 27.2428 | 0.2059% | 178.5085 | 2.11% | 2.5388 | 0.04728% | 208.2902 | 2.363%
ADER | 4.2598 | 0.03908% | 7.59 | 0.07972% | 0 | 0% | 11.8498 | 0.1188%
APPR | 1.4 | 0.0001863% | 0 | 0% | 0 | 0% | 1.4 | 0.0001863%
PEND | 75.577 | 0.3522% | 69.8731 | 0.5822% | 5.7773 | 0.0618% | 151.2273 | 0.9961%
UNSC | 43.4164 | 0.1042% | 3.1443 | 0.04621% | 0.10909 | 0.001045% | 46.6698 | 0.1515%
CONS | 4.8712 | 0.0258% | 0.30417 | 0.0001349% | 0 | 0% | 5.1754 | 0.02594%
DOCC | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
DCNL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
MAPP | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
FICL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
PROD | 0 | 0% | 0.057 | 0.0006405% | 0 | 0% | 0.057 | 0.0006405%
PREC | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
CLSD | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
CNCL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
DEFR | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Grand Total | 290.449 | 1.908% | 708.2391 | 7.69% | 40.2464 | 0.3015% | 1038.9345 | 9.9%
Future Year Planning | (All) | Step 1: Beyond Scoping Status (UNSE) Includes work beyond "Scoping" status in SAP, which includes all miles considered to calculate projects that have been scoped and moved into later project status including Estimating, Permitting, Ready for Construction, Construction, Post-construction
MAT | (Multiple Items)
Values
SAP Status | 2025 Forecast OH Miles | 2025 V3 OH Risk Reduction | 2025 Forecast UG Miles | 2025 V3 UG Risk Reduction | 2025 Forecast Removal Miles | 2025 V3 Removal Risk Reduction | 2025 Forecast Total System Hardening (GH-01) Miles | 2025 Forecast Total System Hardening (GH-01) Risk Reduction
ESTS | 27.2428 | 0.2059% | 178.5085 | 2.11% | 2.5388 | 0.04728% | 208.2902 | 2.363%
ADER | 4.2598 | 0.03908% | 7.59 | 0.07972% | 0 | 0% | 11.8498 | 0.1188%
APPR | 1.4 | 0.0001863% | 0 | 0% | 0 | 0% | 1.4 | 0.0001863%
PEND | 75.577 | 0.3522% | 69.8731 | 0.5822% | 5.7773 | 0.0618% | 151.2273 | 0.9961%
UNSC | 43.4164 | 0.1042% | 3.1443 | 0.04621% | 0.10909 | 0.001045% | 46.6698 | 0.1515%
CONS | 4.8712 | 0.0258% | 0.30417 | 0.0001349% | 0 | 0% | 5.1754 | 0.02594%
DOCC | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
DCNL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
MAPP | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
FICL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
PROD | 0 | 0% | 0.057 | 0.0006405% | 0 | 0% | 0.057 | 0.0006405%
PREC | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
CLSD | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
CNCL | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
DEFR | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Grand Total | 156.7673 | 0.7274% | 259.4771 | 2.818% | 8.4252 | 0.1101% | 424.6696 | 3.656%
Future Year Planning | Proceed | Step 2: In Scoping Status (UNSE) & marked for "Proceed" Includes work in "Scoping" status in SAP (i.e., all statuses in UNSE) AND marked for "Proceed." This includes those projects that were in Scoping/Scoped (UNSE) status that remained in the workplan after 2023 GRC Decision. This was used to make up the difference to reach the mileage target.
MAT | (Multiple Items)
Values
SAP Status | 2025 Forecast OH Miles | 2025 V3 OH Risk Reduction | 2025 Forecast UG Miles | 2025 V3 UG Risk Reduction | 2025 Forecast Removal Miles | 2025 V3 Removal Risk Reduction | 2025 Total Miles | 2025 Total V3 Risk Reduction
UNSE | 0.36489 | 0.003944% | 182.7153 | 2.267% | 24.1714 | 0.1429% | 207.2516 | 2.414%
Grand Total | 0.36489 | 0.003944% | 182.7153 | 2.267% | 24.1714 | 0.1429% | 207.2516 | 2.414%
Future Year Planning | Proceed - RESCOPE | Step 3: Beyond Scoping Status & Marked for Rescope Includes work in "Scoping" status in SAP (i.e., all statuses in UNSE) AND marked for "Proceed - Rescope." This includes overhead projects that were in Scoping/Scoped (UNSE) status that remained in the workplan, but changed their scope of work/mitigation type after 2023 GRC Decision. This was only used if miles from STEP 2 did not meet mileage targets; which were overhead miles.
MAT | (Multiple Items)
Values
SAP Status | 2025 Forecast OH Miles | 2025 V3 OH Risk Reduction | 2025 Forecast UG Miles | 2025 V3 UG Risk Reduction | 2025 Forecast Removal Miles | 2025 V3 Removal Risk Reduction | 2025 Total Miles | 2025 Total V3 Risk Reduction
UNSE | 133.3168 | 1.177% | N/A | N/A | N/A | N/A | 133.3168 | 1.177%
Grand Total | 133.3168 | 1.177% | N/A | N/A | N/A | N/A | 133.3168 | 1.177%
Step 4: 2025 System Hardening Target Miles and Target Adjusted Risk Reduction Risk reduction forecasts adjusted to be proportionate to mileage target by mitigaton type (200 OH miles, 310 UG miles, 10 Line Removal miles for a total of 520 System Hardening Miles)
| 2025 Forecast OH Miles | 2025 V3 OH Risk Reduction | 2025 Forecast UG Miles | 2025 V3 UG Risk Reduction | 2025 Forecast Removal Miles | 2025 V3 Removal Risk Reduction | 2025 Total System Hardening Miles | 2025 Total V3 Risk Reduction
| 200 | 1.11% | 310 | 3.445% | 10 | 0.1194% | 520 | 4.675%

## 2025 GH-01 Workplan
Source: | Distribution Operations Toolset (DOT)
Stamp: | 2024-02-22
[13 empty] | 1038.9345 | 290.449 | 708.2391 | 40.2464 | 1.908% | 7.69% | 0.3015%
Order | Order Description | Hardening Method | SAP Status | MAT | Program | Div | Region | City | County | HFTD Tier | Circuit Protection Zone | Future Year Planning | 2025 Forecast Total Miles | 2025 Forecast OH Miles | 2025 Forecast UG Miles | 2025 Forecast Removal Miles | 2025 V3 OH Risk Reduction | 2025 V3 UG Risk Reduction | 2025 V3 Removal Risk Reduction
35392113 | FRRB FORESTHILL 1101-37238 UG TL4 | UG | PEND | 08W | FRRB | SI | Region 2 - North East | Foresthill | PLACER | Tier 3 | FORESTHILL 110137238 | Proceed | 1.928 | 0 | 1.928 | 0 | 0% | 0.01185% | 0%
35374682 | FRRB - MARIPOSA 210110240 ML-1 | UG | PEND | 08W | FRRB | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 21019400 | Proceed | 3.1559 | 0 | 3.1559 | 0 | 0% | 0.01235% | 0%
35342335 | FRRB - BIG BASIN 1102 UG3 HWY 236 | UG | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | Tier 3 | BIG BASIN 11025066 | Proceed | 2.1941 | 0 | 2.1941 | 0 | 0% | 0.0019% | 0%
35342336 | FRRB - BIG BASIN 1102 UG2 CAMPGROUND | UG | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | Tier 3 | BIG BASIN 11025066 | Proceed | 2.9763 | 0 | 2.9763 | 0 | 0% | 0.002578% | 0%
35342337 | FRRB - BIG BASIN 1102 UG4 BBSP PUMPSTN | UG | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | Tier 3 | BIG BASIN 11025066 | Proceed | 0.52008 | 0 | 0.52008 | 0 | 0% | 0.0004504% | 0%
35321894 | FRRB - PT MORETTI 1101 12122 PH1 SM4 | UG | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | Tier 2 | POINT MORETTI 110112122 | Proceed | 0.10985 | 0 | 0.10985 | 0 | 0% | 2.83e-05% | 0%
35334404 | FRRB - PT MORETTI 1101 P1S2 310SWAN | OH | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | Tier 2 | POINT MORETTI 110135874 | Proceed | 0.44602 | 0.44602 | 0 | 0 | 1.877e-05% | 0% | 0%
35297464 | FRRB -PT MORETTI 1101 12122 P1S3 460SWAN | UG | PEND | 08W | FRRB | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | Tier 2 | POINT MORETTI 110112122 | Proceed | 1.0021 | 0 | 1.0021 | 0 | 0% | 0.0002581% | 0%
35297984 | REMG 368 - STILLWATER 1101,OLD OREGON TR | Removal | UNSE | 08W | FRRB | NV | Region 2 - North East | Redding | SHASTA | Tier 2 | STILLWATER 110148950 | Proceed | 1.1201 | 0 | 0 | 1.1201 | 0% | 0% | 0.0003909%
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | Removal | UNSC | 08W | FRRB | NV | Region 2 - North East | Oroville | BUTTE | Tier 3 | KANAKA 1101CB | Proceed | 0.10909 | 0 | 0 | 0.10909 | 0% | 0% | 0.001045%
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | UG | PEND | 08W | FRRB | NV | Region 2 - North East | Oroville | BUTTE | Tier 3 | KANAKA 1101CB | Proceed | 2.0655 | 0 | 2.0655 | 0 | 0% | 0.01355% | 0%
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Removal | UNSE | 08W | FRRB | NV | Region 2 - North East | Berry Creek | BUTTE | Tier 3 | WYANDOTTE 11031976 | Proceed | 0.066288 | 0 | 0 | 0.066288
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Removal | UNSE | 08W | FRRB | NV | Region 2 - North East | Berry Creek | BUTTE | Tier 3 | WYANDOTTE 11031976 | Proceed | 0.075758 | 0 | 0 | 0.075758
35284810 | FRRB - HMB 1103 SM CO LR6012 PUMP HOUSE | UG | ESTS | 08W | FRRB | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | Tier 2 | HALF MOON BAY 11036012 | Proceed | 0.89602 | 0.037879 | 0.85814 | 0 | 7.154e-06% | 0.0001815% | 0%
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | UG | PEND | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | CRESCENT MILLS 21012056 | Proceed | 0.82008 | 0 | 0.82008 | 0 | 0% | 0.001251% | 0%
35285594 | FRRB - ECHO SUMMIT 1101 - UG-10 (DC07) | UG | UNSE | 08W | FRRB | SI | Region 2 - North East | Twin Bridges | EL DORADO | Tier 2 | ECHO SUMMIT 1101481660 | Proceed | 0.21989 | 0 | 0.21989 | 0 | 0% | 5.439e-05% | 0%
35290545 | FRRB -BIG MEADOWS 21012260 REMOVE ML 1.4 | Removal | PEND | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | BIG MEADOWS 21012260 | Proceed | 0.66932 | 0 | 0 | 0.66932 | 0% | 0% | 0.0002496%
35292758 | FRRB BIG MEADOWS 2101 CB PH1 | OH | CONS | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | BIG MEADOWS 21012248 | Proceed | 0.018939 | 0.018939 | 0 | 0 | 4.259e-05% | 0% | 0%
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | UG | UNSC | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 3.1443 | 0 | 3.1443 | 0 | 0% | 0.04621% | 0%
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | OH | PEND | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | BIG MEADOWS 21012476 | Proceed | 0.16004 | 0.16004 | 0 | 0 | 0.0001146% | 0% | 0%
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | UG | ESTS | 08W | FRRB | NV | Region 2 - North East | Greenville | PLUMAS | Tier 2 | BIG MEADOWS 21012476 | Proceed | 1.1 | 0 | 1.1 | 0 | 0% | 0.0008717% | 0%
35284366 | REMG 512 - STANISLAUS 1702, FOREBAY | Removal | ESTS | 08W | SH | YO | Region 5 - Central Valley | MI Wuk Village | TUOLUMNE | Tier 2 & 3 | STANISLAUS 1702CB | Proceed | 0.60871 | 0 | 0 | 0.60871 | 0% | 0% | 0.009293%
35290295 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.2 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.1953 | 1.1953 | 0 | 0 | 0.00327% | 0% | 0%
35290296 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.3 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.93598 | 0.93598 | 0 | 0 | 0.002561% | 0% | 0%
35290297 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.4 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.94508 | 0.94508 | 0 | 0 | 0.002586% | 0% | 0%
35290501 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.2 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.64 | 1.64 | 0 | 0 | 0.004487% | 0% | 0%
35290502 | REMG 436 - POTTER VALLEY 1105, CCA-SCP | Removal | ESTS | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed - RESCOPE | 1.6299 | 1.6299 | 0 | 0 | 0.004459% | 0% | 0%
35290503 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.1157 | 1.1157 | 0 | 0 | 0.003053% | 0% | 0%
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.0436 | 0 | 1.0436 | 0 | 0% | 0.00318% | 0%
35290506 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.6 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 2.09 | 2.09 | 0 | 0 | 0.005718% | 0% | 0%
35290507 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.7 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.77992 | 0.77992 | 0 | 0 | 0.002134% | 0% | 0%
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.62008 | 0 | 0.62008 | 0 | 0% | 0.00189% | 0%
35290509 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.2 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Upper Lake | LAKE | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.09 | 1.09 | 0 | 0 | 0.002982% | 0% | 0%
35290510 | CWSP PTR VLY PH 1105 LR1904 PH4.3 VER 3 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Upper Lake | LAKE | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.55303 | 0 | 0.55303 | 0 | 0% | 0.001685% | 0%
35290511 | CWSP - HIGHLANDS 1102 LR623120 PH1.2 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 | HIGHLANDS 1102623120 | Proceed | 1.2799 | 1.2799 | 0 | 0 | 0.001121% | 0% | 0%
35290512 | CWSP - HIGHLANDS 1102 LR623120 PH1.3 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 | HIGHLANDS 1102623120 | Proceed | 2.06 | 2.06 | 0 | 0 | 0.001805% | 0% | 0%
35290513 | CWSP - HIGHLANDS 1102 LR623120 PH1.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 | HIGHLANDS 1102623120 | Proceed | 2.0201 | 2.0201 | 0 | 0 | 0.00177% | 0% | 0%
35290514 | CWSP - HIGHLANDS 1102 LR623120 PH1.5 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 | HIGHLANDS 1102623120 | Proceed | 0.060038 | 0.060038 | 0 | 0 | 5.259e-05% | 0% | 0%
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 | POTTER VALLEY P H 110537476 | Proceed | 0.25133 | 0.25133 | 0 | 0 | 7.989e-05% | 0% | 0%
35285245 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 | POTTER VALLEY P H 110537476 | Proceed | 0.38333 | 0.38333 | 0 | 0 | 0.0001219% | 0% | 0%
35285247 | CWSP - UPPER LAKE 1101 1276 PH 2.2 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Upper Lake | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 0.30379 | 0.30379 | 0 | 0 | 0.00442% | 0% | 0%
35285248 | CWSP - UPPER LAKE 1101 1276 PH 2.3 | OH | ESTS | 08W | SH | HB | Region 1 - North Coast | Upper Lake | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 1.461 | 1.461 | 0 | 0 | 0.02126% | 0% | 0%
35285250 | CWSP - UPPER LAKE 1101 1276 PH 2.5 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 0.51705 | 0.51705 | 0 | 0 | 0.007523% | 0% | 0%
35290807 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.8 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Ukiah | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.3699 | 1.3699 | 0 | 0 | 0.003748% | 0% | 0%
35293664 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.4 | OH | PEND | 08W | SH | SI | Region 2 - North East | Greenwood | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.8 | 0.8 | 0 | 0 | 0.003618% | 0% | 0%
35293666 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.6 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.22992 | 0.22992 | 0 | 0 | 0.00104% | 0% | 0%
35293667 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.7 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.65 | 1.65 | 0 | 0 | 0.007461% | 0% | 0%
35293668 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.8 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.44 | 1.44 | 0 | 0 | 0.006512% | 0% | 0%
35293669 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.9 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.6299 | 1.6299 | 0 | 0 | 0.007371% | 0% | 0%
35293774 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.3 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 & 3 | POTTER VALLEY P H 11051904 | Proceed | 1.2699 | 1.2699 | 0 | 0 | 0.003474% | 0% | 0%
35293841 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.5 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 & 3 | POTTER VALLEY P H 11051904 | Proceed | 1.5 | 1.5 | 0 | 0 | 0.004104% | 0% | 0%
35293843 | CWSP POTTER VALLEY PH 1105 LR1904 PH1.6 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 & 3 | POTTER VALLEY P H 11051904 | Proceed | 1.3095 | 1.3095 | 0 | 0 | 0.003583% | 0% | 0%
35283344 | CWSP UPPER LAKE 1101 1276 PH 1.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 1.6561 | 1.6561 | 0 | 0 | 0.0241% | 0% | 0%
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 1.4144 | 1.4144 | 0 | 0 | 0.02058% | 0% | 0%
35283348 | CWSP UPPER LAKE 1101 1276 PH 1.7 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 0.95379 | 0.95379 | 0 | 0 | 0.01388% | 0% | 0%
35283349 | CWSP UPPER LAKE 1101 1276 PH 1.8 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 0.49602 | 0.49602 | 0 | 0 | 0.007217% | 0% | 0%
35278890 | CWSP AUBERRY 1101 R2578 PH 5.2 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 1.6765 | 1.5542 | 0.12235 | 0 | 0.003847% | 0.0003332% | 0%
35274591 | CWSP MARIPOSA 2101 LR 35244 PH1.3 | OH | PEND | 08W | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 210135244 | Proceed | 1.022 | 1.022 | 0 | 0
35274592 | CWSP MARIPOSA 2101 LR 35244 PH 2.2 | OH | PEND | 08W | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 | MARIPOSA 210135244 | Proceed | 1.963 | 1.963 | 0 | 0
35277921 | CWSP AUBERRY 1101 R2578 PH 1.2 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 2.5078 | 2.5078 | 0 | 0 | 0.006208% | 0% | 0%
35277922 | CWSP AUBERRY 1101 R2578 PH 1.3 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 1.6256 | 1.6256 | 0 | 0 | 0.004024% | 0% | 0%
35277923 | CWSP AUBERRY 1101 R2578 PH 1.4 | OH | UNSC | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 3.1534 | 3.1534 | 0 | 0 | 0.007806% | 0% | 0%
35277937 | CWSP AUBERRY 1101 R2578 PH 2.3 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 2.9004 | 2.9004 | 0 | 0 | 0.00718% | 0% | 0%
35278091 | CWSP AUBERRY 1101 R2578 PH 3.2 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 2.839 | 2.839 | 0 | 0 | 0.007028% | 0% | 0%
35278092 | CWSP AUBERRY 1101 R2578 PH 3.3 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 3.8369 | 3.8369 | 0 | 0 | 0.009498% | 0% | 0%
35278093 | CWSP AUBERRY 1101 R2578 PH 3.4 | UG | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 0.41496 | 0 | 0.41496 | 0 | 0% | 0.00113% | 0%
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 | OH | PEND | 08W | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 210135244 | Proceed | 2.4009 | 2.4009 | 0 | 0
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 | OH | UNSC | 08W | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 | MARIPOSA 210135244 | Proceed | 4.595 | 4.595 | 0 | 0
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | UG | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 2101CB | Proceed | 0.58011 | 0 | 0.58011 | 0 | 0% | 2.083e-05% | 0%
35254070 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.1 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.95701 | 0.95701 | 0 | 0 | 0.004328% | 0% | 0%
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.1 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 2.65 | 2.65 | 0 | 0 | 0.01198% | 0% | 0%
35254072 | CWSP - HIGHLANDS 1102 LR 623120 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 | HIGHLANDS 1102623120 | Proceed | 0.77008 | 0.77008 | 0 | 0 | 0.0006746% | 0% | 0%
35254073 | CWSP POTTER VALLEY PH 1105 LR1904 PH1 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 & 3 | POTTER VALLEY P H 11051904 | Proceed | 1.0233 | 1.0233 | 0 | 0 | 0.0028% | 0% | 0%
35254074 | CWSP POTTER VALLEY PH 1105 LR1904 PH2 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.39792 | 0.39792 | 0 | 0 | 0.001089% | 0% | 0%
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 1.8 | 1.8 | 0 | 0 | 0.004925% | 0% | 0%
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | Tier 2 | POTTER VALLEY P H 11051904 | Proceed | 0.92992 | 0.92992 | 0 | 0 | 0.002544% | 0% | 0%
35254243 | CWSP AUBERRY 1101 LR R2578 PH 1 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 2.9432 | 2.9432 | 0 | 0 | 0.007286% | 0% | 0%
35254245 | CWSP AUBERRY 1101 LR R2578 PH 3 | OH | ESTS | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 3.2072 | 3.2072 | 0 | 0 | 0.007939% | 0% | 0%
35254247 | CWSP AUBERRY 1101 LR R2578 PH 5 | OH | PEND | 08W | SH | FR | Region 5 - Central Valley | Tollhouse | FRESNO | Tier 2 | AUBERRY 1101R2578 | Proceed | 2.0326 | 2.0326 | 0 | 0 | 0.005032% | 0% | 0%
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 2.6782 | 0 | 2.6782 | 0 | 0% | 0.03599% | 0%
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 2.8943 | 0 | 2.8943 | 0 | 0% | 0.03889% | 0%
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | OH | ESTS | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 0.8 | 0.8 | 0 | 0 | 0.00958% | 0% | 0%
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 0.39867 | 0.39867 | 0 | 0 | 0.004774% | 0% | 0%
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 1.2165 | 1.2165 | 0 | 0 | 0.01457% | 0% | 0%
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 2.782 | 0 | 2.782 | 0 | 0% | 0.03734% | 0%
35428406 | CWSP - SILVERADO 2104 LR 515946 PH 1.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed - RESCOPE | 3.1701 | 0 | 3.1701 | 0 | 0% | 0.05196% | 0%
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed | 0.87841 | 0.87841 | 0 | 0 | 0.01633% | 0% | 0%
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed | 1.2953 | 1.2953 | 0 | 0 | 0.02408% | 0% | 0%
35226625 | REMG 670 - ELK CREEK 1101, VALLEY VIEW | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Elk Creek | GLENN | Tier 2 | ELK CREEK 11012106 | Proceed | 8.9 | 0 | 0 | 8.9 | 0% | 0% | 0.07395%
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | OH | ESTS | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 2 | MIDDLETOWN 1102302610 | Proceed | 1.3085 | 1.3085 | 0 | 0 | 0.005633% | 0% | 0%
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 1.1449 | 0 | 1.1449 | 0 | 0% | 0.01537% | 0%
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 0.36 | 0.36 | 0 | 0 | 0.004293% | 0% | 0%
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 0.87992 | 0.87992 | 0 | 0 | 0.01049% | 0% | 0%
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 0.17746 | 0.17746 | 0 | 0 | 0.002116% | 0% | 0%
35226873 | REMG 749-MIDDLETOWN 1101,ANDRESON SPRNGS | Removal | UNSE | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 1.0394 | 0 | 0 | 1.0394 | 0% | 0% | 0.01641%
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 2.8756 | 0 | 2.8756 | 0 | 0% | 0.0386% | 0%
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | OH | CONS | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 0.79375 | 0.79375 | 0 | 0 | 0.009466% | 0% | 0%
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed | 0.97576 | 0.97576 | 0 | 0 | 0.01814% | 0% | 0%
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 2 | MIDDLETOWN 1102302610 | Proceed | 1.689 | 0.10019 | 1.5888 | 0 | 0.0004313% | 0.007803% | 0%
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 2 | MIDDLETOWN 1102302610 | Proceed | 0.73068 | 0.73068 | 0 | 0 | 0.003146% | 0% | 0%
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | OH | ESTS | 08W | SH | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA | Tier 2 | KIRKER 2104442850 | Proceed | 3.2598 | 3.2598 | 0 | 0 | 0.01264% | 0% | 0%
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | UG | PEND | 08W | SH | SO | Region 1 - North Coast | Santa Rosa | SONOMA | Tier 2 | DUNBAR 1101CB | Proceed | 1.0708 | 0 | 1.0708 | 0 | 0% | 6.827e-05% | 0%
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE | Tier 2 & 3 | HIGHLANDS 1102628 | Proceed | 2.7275 | 2.7275 | 0 | 0 | 0.03266% | 0% | 0%
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | UG | UNSE | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed | 2.04 | 0 | 2.04 | 0 | 0% | 0.04215% | 0%
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 1.04 | 0 | 1.04 | 0 | 0% | 0.01396% | 0%
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH.2.1 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 0.71307 | 0.71307 | 0 | 0 | 0.008504% | 0% | 0%
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 1101548 | Proceed | 3.8303 | 0 | 3.8303 | 0 | 0% | 0.05142% | 0%
35428408 | CWSP - SILVERADO 2104 LR 515946 PH 1.4 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed - RESCOPE | 2.56 | 0 | 2.56 | 0 | 0% | 0.04196% | 0%
35409203 | CWSP - MIDDLETOWN 1101433160 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 2 & 3 | Middletown 1101433160 | Proceed - RESCOPE | 1.39 | 0 | 1.39 | 0 | 0% | 0.01935% | 0%
35523540 | REMG 728 UG - HIGHLANDS 1102, BUCKSKIN W | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Clearlake | LAKE |  | HIGHLANDS 1102628 | Proceed - RESCOPE | 0.77992 | 0 | 0.77992 | 0 | 0% | 0.01048% | 0%
35436100 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.3 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 2.15 | 0 | 2.15 | 0 | 0% | 0.02783% | 0%
35435899 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.2 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 0.78996 | 0 | 0.78996 | 0 | 0% | 0.01023% | 0%
35433371 | CWSP - CLAYTON 2212 LR 96224 PH 1.3 | UG | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 3 | CLAYTON 221296224 | Proceed - RESCOPE | 2.096 | 0 | 2.096 | 0 | 0% | 0.02694% | 0%
35433366 | CWSP - CLAYTON 2212 LR 96224 PH 1.2 | UG | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 3 | CLAYTON 221296224 | Proceed - RESCOPE | 2.396 | 0.010038 | 2.386 | 0 | 0.0001179% | 0.03066% | 0%
35418361 | CWSP - SHADY GLEN 110248894 PH1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Colfax | PLACER | Tier 2 & 3 | SHADY GLEN 110248894 | Proceed - RESCOPE | 7.4201 | 0 | 7.4201 | 0 | 0% | 0.09467% | 0%
35526461 | CWSP - SHADY GLEN 110132726 PH 1 | Hybrid | UNSE | 08W | SH | SI | Region 2 - North East | Colfax | PLACER |  | SHADY GLEN 110132726 | Proceed - RESCOPE | 11.74 | 1.6 | 10.14 | 0 | 0.01829% | 0.1311% | 0%
35417110 | CWSP - FORESTHILL 1102 2106 PH 1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Foresthill | PLACER | Tier 3 | FORESTHILL 11022106 | Proceed - RESCOPE | 9.5701 | 0 | 9.5701 | 0 | 0% | 0.1161% | 0%
35422749 | CWSP - SHADY GLEN 11022232 PH 1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Colfax | PLACER | Tier 2 | SHADY GLEN 11022232 | Proceed - RESCOPE | 7.94 | 0 | 7.94 | 0 | 0% | 0.09562% | 0%
35422750 | CWSP - SHADY GLEN 11022232 PH 2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Colfax | PLACER | Tier 3 | SHADY GLEN 11022232 | Proceed - RESCOPE | 8.35 | 0 | 8.35 | 0 | 0% | 0.1006% | 0%
35422751 | CWSP - SHADY GLEN 11022232 PH 3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Colfax | PLACER | Tier 3 | SHADY GLEN 11022232 | Proceed - RESCOPE | 10.74 | 0 | 10.74 | 0 | 0% | 0.1293% | 0%
35430872 | CWSP - SILVERADO 2105658898 PH 1.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 2.038 | 0 | 2.038 | 0 | 0% | 0.02433% | 0%
35430875 | CWSP - SILVERADO 2105658898 PH 1.5 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 0.511 | 0 | 0.511 | 0 | 0% | 0.0061% | 0%
35430876 | CWSP - SILVERADO 2105658898 PH 2.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Santa Rosa | SONOMA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 0.56818 | 0 | 0.56818 | 0 | 0% | 0.006782% | 0%
35430877 | CWSP - SILVERADO 2105658898 PH 2.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 0.56818 | 0 | 0.56818 | 0 | 0% | 0.006782% | 0%
35430873 | CWSP - SILVERADO 2105658898 PH 1.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 2.577 | 0 | 2.577 | 0 | 0% | 0.03076% | 0%
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | OH | CONS | 08W | SH | SO | Region 1 - North Coast | Forestville | SONOMA | Tier 3 | MONTE RIO 1113652 | Proceed | 0.01572 | 0.01572 | 0 | 0 | 1.089e-05% | 0% | 0%
35510467 | CWSP - BONNIE NOOK 1101CB PH 2.4 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Dutch Flat | PLACER |  | BONNIE NOOK 1101CB | Proceed | 1 | 0 | 1 | 0 | 0% | 0.01458% | 0%
35523358 | PSPS - PIT NO 3 2101CB PH 1.2 | UG | PEND | 3UG | SH | NV | Region 2 - North East | Montgomery Creek | SHASTA | Tier 2 | PIT NO 3 2101CB | Proceed - RESCOPE | 3.311 | 0 | 3.311 | 0 | 0% | 0.02173% | 0%
35523400 | PSPS - PIT NO 3 2101CB PH 1.3 | UG | PEND | 3UG | SH | NV | Region 2 - North East | Montgomery Creek | SHASTA | Tier 2 | PIT NO 3 2101CB | Proceed - RESCOPE | 0.52898 | 0 | 0.52898 | 0 | 0% | 0.003472% | 0%
35430874 | CWSP - SILVERADO 2105658898 PH 1.4 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 2.286 | 0 | 2.286 | 0 | 0% | 0.02729% | 0%
35526464 | CWSP - FORESTHILL 11022106 PH 2 | UG | UNSE | 08W | SH | SI | Region 2 - North East | Foresthill | PLACER |  | FORESTHILL 11022106 | Proceed - RESCOPE | 7.96 | 0.68996 | 7.2701 | 0 | 0.007431% | 0.08822% | 0%
35409217 | CWSP - OREGON TRAIL 11021584 PH 2 | Hybrid | UNSE | 3UG | SH | NV | Region 2 - North East | Shasta Lake | SHASTA | Tier 2 | OREGON TRAIL 11021584 | Proceed - RESCOPE | 9.8701 | 4.66 | 5.21 | 0 | 0.05699% | 0.07094% | 0%
35526462 | CWSP - SHADY GLEN 110248894 PH 2 | Hybrid | UNSE | 08W | SH | SI | Region 2 - North East | Grass Valley | NEVADA |  | SHADY GLEN 110248894 | Proceed - RESCOPE | 4.66 | 1.9201 | 2.74 | 0 | 0.02148% | 0.03496% | 0%
35526466 | CWSP - FORESTHILL 11022106 PH 4 | Hybrid | UNSE | 08W | SH | SI | Region 2 - North East | Foresthill | PLACER |  | FORESTHILL 11022106 | Proceed - RESCOPE | 8.19 | 2.3799 | 5.81 | 0 | 0.02563% | 0.0705% | 0%
35418379 | CWSP - STANISLAUS 170237278 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Arnold | CALAVERAS | Tier 3 | STANISLAUS 170237278 | Proceed - RESCOPE | 7.5 | 0 | 7.5 | 0 | 0% | 0.08015% | 0%
35523401 | CWSP - REDBUD 1101 LR323962 PH 1.1 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  | REDBUD 1101323962 | Proceed - RESCOPE | 1.54 | 0 | 1.54 | 0 | 0% | 0.01636% | 0%
35523402 | CWSP - REDBUD 1101 LR323962 PH 1.2 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  | REDBUD 1101323962 | Proceed - RESCOPE | 3.1299 | 0 | 3.1299 | 0 | 0% | 0.03324% | 0%
35523410 | CWSP - REDBUD 1101 LR323962 PH 1.3 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  | REDBUD 1101323962 | Proceed - RESCOPE | 2.86 | 0 | 2.86 | 0 | 0% | 0.03037% | 0%
35372258 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.1 | Hybrid | UNSE | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 8.3301 | 5.06 | 3.2701 | 0 | 0.05876% | 0.04233% | 0%
35526465 | CWSP - FORESTHILL 11022106 PH 3 | Hybrid | UNSE | 08W | SH | SI | Region 2 - North East | Foresthill | PLACER |  | FORESTHILL 11022106 | Proceed - RESCOPE | 9.8299 | 4.39 | 5.44 | 0 | 0.04728% | 0.06601% | 0%
35409215 | CWSP - OREGON TRAIL 11021584 PH 1 | Hybrid | UNSE | 3UG | SH | NV | Region 2 - North East | Shasta Lake | SHASTA | Tier 2 | OREGON TRAIL 11021584 | Proceed - RESCOPE | 4.3701 | 3.8201 | 0.55 | 0 | 0.04672% | 0.007489% | 0%
35524040 | CWSP - PIT NO 3 2101CB PH 1.1 | UG | PEND | 3UG | SH | NV | Region 2 - North East | Montgomery Creek | SHASTA | Tier 2 | PIT NO 3 2101CB | Proceed - RESCOPE | 1.9271 | 0 | 1.9271 | 0 | 0% | 0.01265% | 0%
35487141 | CWSP FLINT 1101 750 PH 1.5 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | FLINT 1101750 | Proceed | 0.71155 | 0.71155 | 0 | 0 | 0.0005933% | 0% | 0%
35488067 | CWSP - ORO FINO 110276008 PH 1.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 1.09 | 0 | 1.09 | 0 | 0% | 0.01294% | 0%
35488068 | CWSP - ORO FINO 110276008 PH 2.2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 5.8292 | 0 | 5.8292 | 0 | 0% | 0.06923% | 0%
35488069 | CWSP - ORO FINO 110276008 PH 2.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 1.4809 | 0 | 1.4809 | 0 | 0% | 0.01759% | 0%
35488560 | CWSP - ORO FINO 110276008 PH 1.2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 7.18 | 0 | 7.18 | 0 | 0% | 0.08527% | 0%
35454650 | CWSP - NOTRE DAME 1104 2028 PH2.2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 0.514 | 0 | 0.514 | 0 | 0% | 0.007771% | 0%
35454651 | CWSP - NOTRE DAME 1104 2028 PH2.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 1.471 | 0.085 | 1.386 | 0 | 0.001133% | 0.02095% | 0%
35454652 | CWSP - NOTRE DAME 1104 2028 PH2.4 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 2.695 | 0 | 2.695 | 0 | 0% | 0.04074% | 0%
35485344 | CWSP - STANISLAUS 17026028 PH1.2 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Arnold | CALAVERAS | Tier 3 | STANISLAUS 17026028 | Proceed | 4.11 | 0 | 4.11 | 0 | 0% | 0.0478% | 0%
35485345 | CWSP - STANISLAUS 17026028 PH 1.3 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Arnold | CALAVERAS | Tier 3 | STANISLAUS 17026028 | Proceed | 3.23 | 0 | 3.23 | 0 | 0% | 0.03757% | 0%
35485580 | PSPS - VACAVILLE 1108 LR8762 PH 1.6 BRAZ | UG | ESTS | 08W | SH | SA | Region 2 - North East | Vacaville | SOLANO | Tier 2 | VACAVILLE 11088762 | Proceed | 0.056818 | 0 | 0.056818 | 0 | 0% | 0.0001852% | 0%
35448807 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Alleghany | SIERRA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.21 | 0 | 2.21 | 0 | 0% | 0.02251% | 0%
35448810 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Alleghany | SIERRA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.56 | 0 | 2.56 | 0 | 0% | 0.02607% | 0%
35301110 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.6 | OH | PEND | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed | 0.40322 | 0.40322 | 0 | 0 | 0.007496% | 0% | 0%
35299134 | CWSP HARTLEY 1101 LR789752 PH 1.3 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | HARTLEY 1101980662 | Proceed | 0.40303 | 0.40303 | 0 | 0
35299135 | CWSP HARTLEY 1101 LR789752 PH 1.4 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | HARTLEY 1101980662 | Proceed | 0.92102 | 0.92102 | 0 | 0
35299136 | CWSP HARTLEY 1101 LR789752 PH 1.5 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | HARTLEY 1101980662 | Proceed | 0.86004 | 0.86004 | 0 | 0
35299137 | CWSP HARTLEY 1101 LR789752 PH 1.6 | OH | UNSC | 08W | SH | HB | Region 1 - North Coast | Lakeport | LAKE | Tier 2 | HARTLEY 1101980662 | Proceed | 0.5 | 0.5 | 0 | 0
35317480 | CWSP - JESSUP 1102 LR1550 PH 2.1 | OH | UNSC | 08W | SH | NV | Region 2 - North East | Anderson | SHASTA | Tier 2 | JESSUP 11021550 | Proceed - RESCOPE | 1.7701 | 1.7701 | 0 | 0 | 0.0007041% | 0% | 0%
35314416 | CWSP - BELL 1108 LR2202 PH 3.1 | Hybrid | ESTS | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.6002 | 0.31004 | 1.1201 | 0.17008 | 4.125e-05% | 0.0001667% | 3.348e-05%
35320443 | CWSP - JAMESON 1102865502 | OH | PEND | 08W | SH | SA | Region 2 - North East | Fairfield | SOLANO | Tier 2 | JAMESON 1102865502 | Proceed | 0.5 | 0.5 | 0 | 0 | 0.0002597% | 0% | 0%
35312542 | PSPS - DUNBAR 1101 440 PH 1.1 | UG | PEND | 08W | SH | SO | Region 1 - North Coast | Glen Ellen | SONOMA | Tier 2 & 3 | DUNBAR 1103534 | Proceed | 0.67386 | 0 | 0.67386 | 0
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | UG | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.1206 | 0 | 1.1206 | 0 | 0% | 0.005667% | 0%
35305304 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.3 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.99205 | 0.99205 | 0 | 0 | 0.004486% | 0% | 0%
35305305 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.4 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.522 | 1.522 | 0 | 0 | 0.006882% | 0% | 0%
35305306 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.5 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.65398 | 0.65398 | 0 | 0 | 0.002957% | 0% | 0%
35305307 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.6 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.0741 | 1.0741 | 0 | 0 | 0.004857% | 0% | 0%
35305309 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.8 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.9229 | 1.9229 | 0 | 0 | 0.008695% | 0% | 0%
35305310 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.9 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.0771 | 1.0771 | 0 | 0 | 0.004871% | 0% | 0%
35305311 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.10 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Greenwood | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.73201 | 0.73201 | 0 | 0 | 0.00331% | 0% | 0%
35305312 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.11 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 0.14792 | 0.14792 | 0 | 0 | 0.0006689% | 0% | 0%
35310704 | CWSP MOUNTAIN QUARRIES 2101 LR1350PH1.12 | OH | PEND | 08W | SH | SI | Region 2 - North East | Cool | EL DORADO | Tier 2 | MOUNTAIN QUARRIES 21011350 | Proceed | 1.196 | 1.196 | 0 | 0 | 0.005408% | 0% | 0%
35311894 | CWSP ANDERSON 1103 LR1600 PH2.1 | OH | PEND | 08W | SH | NV | Region 2 - North East | Anderson | SHASTA | Tier 2 | ANDERSON 11031600 | Proceed | 0.67633 | 0.67633 | 0 | 0 | 5.488e-05% | 0% | 0%
35311896 | CWSP - BELL 1108 LR2202 PH 1.1 | UG | ESTS | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 2.76 | 0 | 2.76 | 0 | 0% | 0.0004108% | 0%
35332863 | PSPS - JESSUP 1103 LR348657 PH 1.2 | OH | UNSC | 08W | SH | NV | Region 2 - North East | Redding | SHASTA | Tier 2 | JESSUP 1103348657 | Proceed | 0.22633 | 0.22633 | 0 | 0
35332864 | PSPS - JESSUP 1103 LR348657 PH 1.3 | OH | UNSC | 08W | SH | NV | Region 2 - North East | Palo Cedro | SHASTA | Tier 2 | JESSUP 1103348657 | Proceed | 1.2585 | 1.2585 | 0 | 0
35332361 | REMG 255 - ELK CREEK 1101, BRAVO | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Elk Creek | GLENN | Tier 2 | ELK CREEK 11012002 | Proceed | 2.2 | 0 | 0 | 2.2 | 0% | 0% | 0.004192%
35330243 | CWSP - REDBUD 1101 LR323962 PH1.5 | Removal | PEND | 08W | SH | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | Tier 3 | REDBUD 1101323962 | Proceed | 4.1479 | 0 | 0 | 4.1479 | 0% | 0% | 0.06153%
35331303 | CWSP ANDERSON 1103 LR1600 PH2.2 | OH | PEND | 08W | SH | NV | Region 2 - North East | Anderson | SHASTA | Tier 2 | ANDERSON 11031600 | Proceed | 1.2837 | 1.1837 | 0 | 0.1 | 9.605e-05% | 0% | 1.064e-05%
35331304 | CWSP ANDERSON 1103 LR1600 PH2.3 | OH | PEND | 08W | SH | NV | Region 2 - North East | Anderson | SHASTA | Tier 2 | ANDERSON 11031600 | Proceed | 1.1201 | 1.1201 | 0 | 0 | 9.089e-05% | 0% | 0%
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | UG | CONS | 08W | SH | NV | Region 2 - North East | Anderson | SHASTA | Tier 2 | JESSUP 11021550 | Proceed | 0.30417 | 0 | 0.30417 | 0 | 0% | 0.0001349% | 0%
35335286 | PSPS - TEJON 1102 LR2455 PH 1.2 | UG | ESTS | 08W | SH | KE | Region 5 - Central Valley | Lebec | KERN | Tier 2 | TEJON 11022455 | Proceed | 5.2104 | 0 | 5.2104 | 0 | 0% | 0.0595% | 0%
35333500 | CWSP - BELL 1108 LR2202 PH 2.2 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.71 | 1.71 | 0 | 0 | 0.0002275% | 0% | 0%
35333502 | CWSP - BELL 1108 LR2202 PH 2.4 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.74 | 1.74 | 0 | 0 | 0.0002315% | 0% | 0%
35333505 | CWSP - BELL 1108 LR2202 PH 2.7 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 0.85 | 0.85 | 0 | 0 | 0.0001131% | 0% | 0%
35333506 | CWSP - BELL 1108 LR2202 PH 3.2 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.76 | 1.76 | 0 | 0 | 0.0002342% | 0% | 0%
35333507 | CWSP - BELL 1108 LR2202 PH 3.3 | OH | APPR | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.4 | 1.4 | 0 | 0 | 0.0001863% | 0% | 0%
35333508 | CWSP - BELL 1108 LR2202 PH 3.4 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.51 | 1.51 | 0 | 0 | 0.0002009% | 0% | 0%
35333509 | CWSP - BELL 1108 LR2202 PH 3.5 | OH | ESTS | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.41 | 1.41 | 0 | 0 | 0.0001876% | 0% | 0%
35333510 | CWSP - BELL 1108 LR2202 PH 3.6 | OH | UNSC | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 0.63996 | 0.63996 | 0 | 0 | 8.515e-05% | 0% | 0%
35334230 | REMG 817 - CORNING 1102 PH 1.4 | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Covelo | TEHAMA | Tier 2 | CORNING 110253184 | Proceed | 3.6701 | 0 | 0 | 3.6701 | 0% | 0% | 0.01244%
35334231 | CWSP - BELL 1108 LR2202 PH 1.2 | OH | ESTS | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.3 | 1.3 | 0 | 0 | 0.000173% | 0% | 0%
35334232 | CWSP - BELL 1108 LR2202 PH 1.3 | UG | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.01 | 0 | 1.01 | 0 | 0% | 0.0001503% | 0%
35334233 | CWSP - BELL 1108 LR2202 PH 1.4 | OH | PEND | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 1.49 | 1.49 | 0 | 0 | 0.0001982% | 0% | 0%
35334234 | CWSP - BELL 1108 LR2202 PH 1.5 | UG | ESTS | 08W | SH | SI | Region 2 - North East | Auburn | PLACER | Tier 2 | BELL 11082202 | Proceed | 2.3 | 0 | 2.3 | 0 | 0% | 0.0003424% | 0%
35337164 | CWSP LINCOLN 1104 51756 & 275986 PH 1.3 | Hybrid | PEND | 08W | SH | SI | Region 2 - North East | Lincoln | PLACER | Tier 2 | LINCOLN 1104275986 | Proceed | 2.8301 | 1.9701 | 0 | 0.86004 | 1.835e-05% | 0% | 1.142e-05%
35349642 | CWSP - UPPER LAKE 1101 1276 PH 2.7 | UG | PEND | 08W | SH | HB | Region 1 - North Coast | Upper Lake | LAKE | Tier 2 | UPPER LAKE 11011276 | Proceed | 0.035985 | 0.035985 | 0 | 0 | 0.0005236% | 0% | 0%
35343741 | PSPS - DUNBAR 1101 440 PH 1.3 | UG | PEND | 08W | SH | SO | Region 1 - North Coast | Sonoma | SONOMA | Tier 2 & 3 | DUNBAR 1103534 | Proceed | 0.70795 | 0 | 0.70795 | 0
35342315 | PSPS - TEJON 1102 LR732836 PH 2.2 | UG | ESTS | 08W | SH | KE | Region 5 - Central Valley | Lebec | KERN | Tier 2 | TEJON 1102732836 | Proceed - RESCOPE | 1.723 | 0 | 1.723 | 0 | 0% | 0.01167% | 0%
35367414 | CWSP - APPLE HILL 21027502 PH 1.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | APPLE HILL 21027502 | Proceed | 6.415 | 0 | 6.415 | 0 | 0% | 0.07656% | 0%
35367464 | CWSP - CALISTOGA 110143924 PH 1.1 | Hybrid | ADER | 3UG | SH | NB | Region 1 - North Coast | Calistoga | NAPA | Tier 3 | CALISTOGA 110143924 | Proceed - RESCOPE | 4.84 | 4.24 | 0.6 | 0 | 0.03889% | 0.006128% | 0%
35367504 | CWSP - ORO FINO 110276008 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 4.37 | 0 | 4.37 | 0 | 0% | 0.0519% | 0%
35367507 | CWSP - ORO FINO 1102CB | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Magalia | BUTTE | Tier 3 | ORO FINO 1102CB | Proceed | 0.897 | 0.021 | 0.876 | 0 | 0.0002992% | 0.01398% | 0%
35367516 | CWSP - SILVERADO 210478268 PH 1.1 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 1.358 | 0 | 1.358 | 0 | 0% | 0.0147% | 0%
35526460 | CWSP - SHADY GLEN 110132726 PH 2 | Hybrid | UNSE | 08W | SH | SI | Region 2 - North East | Colfax | PLACER |  | SHADY GLEN 110132726 | Proceed - RESCOPE | 1.7 | 1.1799 | 0.52008 | 0 | 0.01349% | 0.006726% | 0%
35367524 | CWSP WEST POINT 1101 LR4706 PH1.1 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 1.4 | 0 | 1.4 | 0 | 0% | 0.0154% | 0%
35362666 | CWSP - CLAYTON 2212614950 | UG | PEND | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 2 & 3 | CLAYTON 2212614950 | Proceed | 0.66989 | 0.019886 | 0.65 | 0 | 0.0002713% | 0.009586% | 0%
35363559 | CWSP - SYCAMORE CREEK 11112268 PH 1 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 3.26 | 0 | 3.26 | 0 | 0% | 0.0388% | 0%
35363720 | CWSP - SYCAMORE CREEK 11112268 PH 2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 2.7699 | 0 | 2.7699 | 0 | 0% | 0.03297% | 0%
35364784 | CWSP - SYCAMORE CREEK 11112268 PH 3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 3.0098 | 0 | 3.0098 | 0 | 0% | 0.03582% | 0%
35365064 | CWSP - BONNIE NOOK 1101CB PH 2.1 | UG | PEND | 3UG | SH | SI | Region 2 - North East | Dutch Flat | PLACER | Tier 3 | BONNIE NOOK 1101CB | Proceed | 4.21 | 0 | 4.21 | 0 | 0% | 0.06138% | 0%
35353435 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.4 | Removal | UNSE | 08W | SH | SI | Region 2 - North East | Georgetown | EL DORADO | Tier 3 | PLACERVILLE 21067522 | Proceed | 0.7 | 0 | 0 | 0.7 | 0% | 0% | 0.006031%
35372257 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.1 | OH | ESTS | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 9.0699 | 8.9299 | 0.13996 | 0 | 0.1037% | 0.001812% | 0%
35385802 | CWSP - CLAYTON 2212 LR 96224 PH1.1 | Hybrid | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 3 | CLAYTON 221296224 | Proceed - RESCOPE | 5.7199 | 4.6799 | 0.78996 | 0.25 | 0.05496% | 0.01015% | 0.004648%
35372259 | CWSP - PINE GROVE 1101CB | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | PINE GROVE 1101CB | Proceed | 2.84 | 0 | 2.84 | 0 | 0% | 0.05355% | 0%
35372461 | CWSP - TIGER CREEK 201 CB & 320746 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 2 & 3 | TIGER CREEK 0201CB | Proceed | 4.42 | 0 | 4.42 | 0 | 0% | 0.009378% | 0%
35372462 | CWSP - ELECTRA 1101 LR7104 PH 1.1 | UG | ADER | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | ELECTRA 11017104 | Proceed | 4.8699 | 0.019886 | 4.85 | 0 | 0.0001866% | 0.0518% | 0%
35372465 | CWSP - ANTLER 11011384 PH 1 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011384 | Proceed | 4.695 | 0 | 4.695 | 0 | 0% | 0.06095% | 0%
35373532 | CWSP - APPLE HILL 21027502 PH 3.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Pollock Pines | EL DORADO | Tier 3 | APPLE HILL 21027502 | Proceed | 2.57 | 0 | 2.57 | 0 | 0% | 0.03067% | 0%
35373597 | CWSP - CALISTOGA 110143924 PH 2 | Hybrid | PEND | 3UG | SH | NB | Region 1 - North Coast | Calistoga | NAPA | Tier 3 | CALISTOGA 110143924 | Proceed - RESCOPE | 4.25 | 0.93996 | 3.31 | 0 | 0.008621% | 0.03381% | 0%
35373628 | CWSP - ORO FINO 110276008 PH 2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | ORO FINO 110276008 | Proceed | 0.70019 | 0 | 0.70019 | 0 | 0% | 0.008315% | 0%
35373704 | CWSP - SILVERADO 210478268 PH 2.1 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 3.648 | 0 | 3.648 | 0 | 0% | 0.03948% | 0%
35373708 | CWSP - ANTLER 11011384 PH 2 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011384 | Proceed | 3.73 | 0 | 3.73 | 0 | 0% | 0.04842% | 0%
35374059 | CWSP - ELECTRA 1101L1697 PH 1.1 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | ELECTRA 1101L1697 | Proceed | 2.11 | 0 | 2.11 | 0 | 0% | 0.02357% | 0%
35376558 | CWSP - SILVERADO 2105658898 PH 1.1 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 7.4201 | 0.5 | 6.9201 | 0 | 0.005342% | 0.0826% | 0%
35376559 | CWSP - SILVERADO 2105658898 PH 2.1 | Hybrid | ESTS | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105658898 | Proceed - RESCOPE | 1.55 | 1.11 | 0.43996 | 0 | 0.01186% | 0.005252% | 0%
35433202 | CWSP - MIDDLETOWN 1101171414 PH1.3 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Kelseyville | LAKE | Tier 3 | MIDDLETOWN 1101171414 | Proceed - RESCOPE | 0.72992 | 0.72992 | 0 | 0 | 0.008872% | 0% | 0%
35433201 | CWSP - MIDDLETOWN 1101171414 PH1.2 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Kelseyville | LAKE | Tier 3 | MIDDLETOWN 1101171414 | Proceed - RESCOPE | 1.3299 | 1.3299 | 0 | 0 | 0.01617% | 0% | 0%
35375452 | CWSP - PIKE CITY 11011720 PH 1.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camptonville | YUBA | Tier 3 | PIKE CITY 11011720 | Proceed | 3.1 | 0 | 3.1 | 0 | 0% | 0.04543% | 0%
35374563 | CWSP - BUCKS CREEK 1102 CB PH1.1 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 3.7383 | 0 | 3.7383 | 0 | 0% | 0.05494% | 0%
35374564 | CWSP - BUCKS CREEK 1102 CB PH2.1 | Hybrid | ESTS | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 3.9362 | 0.28883 | 1.8873 | 1.76 | 0.003811% | 0.02774% | 0.03796%
35374569 | CWSP - BUCKS CREEK 1102CB - BELDEN | UG | PEND | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 & 3 | BUCKS CREEK 1102CB | Proceed | 2.1807 | 0 | 2.1807 | 0 | 0% | 0.03205% | 0%
35375449 | CWSP - PIKE CITY 1101CB PH 1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | North San Juan | SIERRA | Tier 3 | PIKE CITY 1101CB | Proceed - RESCOPE | 10.86 | 0 | 10.86 | 0 | 0% | 0.1041% | 0%
35374200 | CWSP - NOTRE DAME 11042028 PH 1 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 2.884 | 0 | 2.884 | 0 | 0% | 0.0436% | 0%
35374202 | CWSP - NOTRE DAME 11042028 PH 2.1 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 1.072 | 0 | 1.072 | 0 | 0% | 0.01621% | 0%
35374204 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Alleghany | SIERRA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.9799 | 0 | 2.9799 | 0 | 0% | 0.03035% | 0%
35374205 | CWSP - ALLEGHANY 1102CB SIERRA PH 2.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Alleghany | SIERRA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.01 | 0 | 2.01 | 0 | 0% | 0.02047% | 0%
35374206 | CWSP - ALLEGHANY 1102CB PH 3.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 4.08 | 0 | 4.08 | 0 | 0% | 0.04155% | 0%
35374208 | CWSP - ALLEGHANY 1102CB NEVADA PH 4.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.28 | 0 | 2.28 | 0 | 0% | 0.02322% | 0%
35374443 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.458 | 0 | 2.458 | 0 | 0% | 0.02503% | 0%
35404726 | CWSP - SILVERADO 210478268 PH 2.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 3.88 | 0 | 3.88 | 0 | 0% | 0.04199% | 0%
35409202 | CWSP - MIDDLETOWN 11011314 PH1 | UG | UNSE | 3UG | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 2 & 3 | MIDDLETOWN 11011314 | Proceed | 1.05 | 0 | 1.05 | 0 | 0% | 0.01629% | 0%
35375450 | CWSP - PIKE CITY 1101CB PH 2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camptonville | YUBA | Tier 3 | PIKE CITY 1101CB | Proceed - RESCOPE | 10.66 | 0 | 10.66 | 0 | 0% | 0.1021% | 0%
35409213 | CWSP - APPLE HILL 1104 CB PH 1.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camino | EL DORADO | Tier 2 | APPLE HILL 1104CB | Proceed | 3.14 | 0.11 | 3.03 | 0 | 0.001136% | 0.03549% | 0%
35377525 | CWSP - PIKE CITY 1101CB PH 3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camptonville | YUBA | Tier 3 | PIKE CITY 1101CB | Proceed - RESCOPE | 6.9701 | 0 | 6.9701 | 0 | 0% | 0.06679% | 0%
35524567 | REMG 729 - HIGHLANDS 1102, WATERTROUGH | OH | UNSE | 08W | SH | HB | Region 1 - North Coast | Clearlake Oaks | LAKE |  | HIGHLANDS 1102628 | Proceed - RESCOPE | 2.66 | 2.66 | 0 | 0 | 0.03185% | 0% | 0%
35524568 | REMG 728 OH - HIGHLANDS 1102, BUCKSKIN W | OH | UNSE | 08W | SH | HB | Region 1 - North Coast | Clearlake | LAKE |  | HIGHLANDS 1102628 | Proceed - RESCOPE | 3.95 | 3.95 | 0 | 0 | 0.0473% | 0% | 0%
35434254 | CWSP - CLAYTON 2212681608 PH 1.3 | UG | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 2 & 3 | CLAYTON 2212681608 | Proceed - RESCOPE | 3.15 | 0 | 3.15 | 0 | 0% | 0.02661% | 0%
35434255 | CWSP - CLAYTON 2212681608 PH 1.4 | UG | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 2 & 3 | CLAYTON 2212681608 | Proceed - RESCOPE | 0.97008 | 0 | 0.97008 | 0 | 0% | 0.008194% | 0%
35434253 | CWSP - CLAYTON 2212681608 PH 1.2 | UG | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 2 & 3 | CLAYTON 2212681608 | Proceed - RESCOPE | 4.2299 | 0 | 4.2299 | 0 | 0% | 0.03573% | 0%
35526463 | CWSP - ANTLER 1101CB | Hybrid | UNSE | 08W | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 1101CB | Proceed - RESCOPE | 1.6299 | 0.68996 | 0.93996 | 0 | 0.005874% | 0.008958% | 0%
35526199 | CWSP - STANISLAUS 1701CB PH 6 | OH | UNSE | 08W | SH | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  | STANISLAUS 1701CB | Proceed - RESCOPE | 7.84 | 7.8 | 0 | 0.039962 | 0.07956% | 0% | 0.00063%
35420111 | CWSP - PLACERVILLE 210611132 PH 2.2 | UG | PEND | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 3.2799 | 0 | 3.2799 | 0 | 0% | 0.02461% | 0%
35526197 | CWSP - STANISLAUS 1701CB PH 4 | OH | UNSE | 08W | SH | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  | STANISLAUS 1701CB | Proceed - RESCOPE | 5.85 | 5.85 | 0 | 0 | 0.05967% | 0% | 0%
35526195 | CWSP - STANISLAUS 1701CB PH 2 | OH | UNSE | 08W | SH | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  | STANISLAUS 1701CB | Proceed - RESCOPE | 6.86 | 6.86 | 0 | 0 | 0.06997% | 0% | 0%
35420747 | CWSP - WOODSIDE 1101 FS 775939 PH 1.2 | UG | UNSE | 08W | SH | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | Tier 3 | WOODSIDE 11018974 | Proceed | 0.8 | 0 | 0.8 | 0 | 0% | 0.001169% | 0%
35526198 | CWSP - STANISLAUS 1701CB PH 5 | OH | UNSE | 08W | SH | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  | STANISLAUS 1701CB | Proceed - RESCOPE | 7.35 | 7.35 | 0 | 0 | 0.07497% | 0% | 0%
35526196 | CWSP - STANISLAUS 1701CB PH 3 | OH | UNSE | 08W | SH | ST | Region 5 - Central Valley | Murphys | CALAVERAS |  | STANISLAUS 1701CB | Proceed - RESCOPE | 1.69 | 1.69 | 0 | 0 | 0.01724% | 0% | 0%
35457108 | CWSP - NARROWS 2102CB 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Penn Valley | NEVADA | Tier 2 | NARROWS 2102CB | Proceed - RESCOPE | 3.85 | 0.01 | 3.84 | 0 | 6.999e-05% | 0.03052% | 0%
35396566 | REMG 24 - BIG BEND 1101, RIM RD | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Oroville | BUTTE | Tier 3 | BIG BEND 1101641808 | Proceed | 1.7799 | 0 | 0 | 1.7799 | 0% | 0% | 0.01383%
35404349 | CWSP - ELECTRA 1101 LR7104 PH 1.2 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | ELECTRA 11017104 | Proceed | 4.47 | 0 | 4.47 | 0 | 0% | 0.04774% | 0%
35404351 | CWSP - SILVERADO 210478268 PH 1.2 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 1.632 | 0 | 1.632 | 0 | 0% | 0.01766% | 0%
35404352 | CWSP - SILVERADO 210478268 PH 1.3 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 2.029 | 0 | 2.029 | 0 | 0% | 0.02196% | 0%
35404353 | CWSP - SILVERADO 210478268 PH 1.4 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 2.096 | 0 | 2.096 | 0 | 0% | 0.02268% | 0%
35404354 | CWSP - SILVERADO 210478268 PH 1.5 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 0.862 | 0 | 0.862 | 0 | 0% | 0.009329% | 0%
35404355 | CWSP - SILVERADO 210478268 PH 1.6 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 210478268 | Proceed | 1.113 | 0 | 1.113 | 0 | 0% | 0.01205% | 0%
35524566 | CWSP REDBUD 1101 LR323962 PH1.4 | OH | UNSE | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE |  | REDBUD 1101323962 | Proceed - RESCOPE | 0.68996 | 0.68996 | 0 | 0 | 0.006656% | 0% | 0%
35420105 | CWSP - PLACERVILLE 210611132 PH 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.4299 | 0 | 2.4299 | 0 | 0% | 0.01823% | 0%
35423082 | CWSP - PLACERVILLE 2106-11132 PH 3.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.9 | 0 | 2.9 | 0 | 0% | 0.02176% | 0%
35424356 | CWSP - PLACERVILLE 2106-11132 PH 4.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.5799 | 0 | 2.5799 | 0 | 0% | 0.01936% | 0%
35403558 | CWSP - CALISTOGA 110143924 PH 1.2 | UG | PEND | 3UG | SH | NB | Region 1 - North Coast | Calistoga | NAPA | Tier 3 | CALISTOGA 110143924 | Proceed - RESCOPE | 1.7299 | 0 | 1.7299 | 0 | 0% | 0.01767% | 0%
35376891 | CWSP - SILVERADO 2104646776 PH 1.1 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104646776 | Proceed | 2.235 | 0 | 2.235 | 0 | 0% | 0.0484% | 0%
35377520 | CWSP - MIDDLETOWN 1101171414 PH 1.1 | UG | ESTS | 3UG | SH | HB | Region 1 - North Coast | Kelseyville | LAKE | Tier 3 | MIDDLETOWN 1101171414 | Proceed | 2.43 | 0 | 2.4299 | 0 | 0% | 0.03294% | 0%
35420106 | CWSP - PLACERVILLE 210611132 PH 1.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 1.2299 | 0 | 1.2299 | 0 | 0% | 0.009229% | 0%
35383758 | CWSP - WEST POINT 11021341 PH1.1 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 2.4598 | 0 | 2.4598 | 0 | 0% | 0.02751% | 0%
35420108 | CWSP - PLACERVILLE 210611132 PH 1.5 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 1.34 | 0 | 1.34 | 0 | 0% | 0.01005% | 0%
35385803 | CWSP - SILVERADO 2104 LR 632 PH 1.1 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 2.198 | 0 | 2.198 | 0 | 0% | 0.03294% | 0%
35385804 | CWSP - SILVERADO 2104 LR 632 PH 2.1 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 2.65 | 0 | 2.65 | 0 | 0% | 0.03972% | 0%
35385805 | CWSP - SILVERADO 2104 LR 515946 PH 1.1 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed | 3.124 | 0 | 3.1241 | 0 | 0% | 0.0512% | 0%
35385806 | CWSP - SILVERADO 2104 LR 515946 PH 2.1 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed | 2.936 | 0 | 2.936 | 0 | 0% | 0.04812% | 0%
35420109 | CWSP - PLACERVILLE 210611132 PH 1.6 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 1.51 | 0 | 1.51 | 0 | 0% | 0.01133% | 0%
35420110 | CWSP - PLACERVILLE 210611132 PH 1.7 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 1 | 0 | 1 | 0 | 0% | 0.007504% | 0%
35380374 | REMG 818 - CORNING 1102 PH 1.13 | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Covelo | TEHAMA | Tier 2 | CORNING 110253184 | Proceed | 2.5299 | 0 | 0 | 2.5299 | 0% | 0% | 0.008574%
35380377 | REMG 301 - CORNING 1102, NEWVILLE | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Corning | TEHAMA | Tier 2 | CORNING 110253184 | Proceed | 2.09 | 0 | 0 | 2.09 | 0% | 0% | 0.007083%
35420113 | CWSP - PLACERVILLE 210611132 PH 2.4 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 0.51004 | 0 | 0.51004 | 0 | 0% | 0.003827% | 0%
35383305 | CWSP - WEST POINT 11014706 PH 2.1 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 0.57 | 0 | 0.57 | 0 | 0% | 0.006271% | 0%
35420107 | CWSP - PLACERVILLE 210611132 PH 1.4 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.4201 | 0 | 2.4201 | 0 | 0% | 0.01816% | 0%
35423081 | CWSP - PLACERVILLE 2106-11132 PH 3.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | PLACERVILLE 210611132 | Proceed - RESCOPE | 3.01 | 0 | 3.01 | 0 | 0% | 0.02259% | 0%
35423083 | CWSP - PLACERVILLE 2106-11132 PH 3.4 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | PLACERVILLE 210611132 | Proceed - RESCOPE | 1.75 | 0 | 1.75 | 0 | 0% | 0.01313% | 0%
35391472 | CWSP - PLACERVILLE 210611132 PH 2.1 | Hybrid | PEND | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 9.1701 | 5.1701 | 4 | 0 | 0.03423% | 0.03001% | 0%
35424358 | CWSP - PLACERVILLE 2106-11132 PH 4.4 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.16 | 0 | 2.16 | 0 | 0% | 0.01621% | 0%
35424580 | CWSP - PLACERVILLE 210611132 PH 5.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 4.01 | 0 | 4.01 | 0 | 0% | 0.03009% | 0%
35424581 | CWSP - PLACERVILLE 210611132 PH 5.4 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Garden Valley | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 2.2799 | 0 | 2.2799 | 0 | 0% | 0.01711% | 0%
35395929 | CWSP - ANTLER 11011520 PH 1.3 | UG | PROD | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011520 | Proceed | 0.057 | 0 | 0.057 | 0 | 0% | 0.0006405% | 0%
35460286 | CWSP - ORO FINO 1102CB PH 1.2 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Magalia | BUTTE | Tier 3 | ORO FINO 1102CB | Proceed | 2.069 | 0 | 2.069 | 0 | 0% | 0.03302% | 0%
35460292 | CWSP - ORO FINO 1102CB PH 1.3 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Magalia | BUTTE | Tier 3 | ORO FINO 1102CB | Proceed | 0.19801 | 0.006 | 0.19201 | 0 | 8.549e-05% | 0.003064% | 0%
35464320 | CWSP - SYCAMORE CREEK 11112268 PH 2.2 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 4.34 | 0 | 4.34 | 0 | 0% | 0.05166% | 0%
35464321 | CWSP - SYCAMORE CREEK 11112268 PH 2.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 1.79 | 0 | 1.79 | 0 | 0% | 0.02131% | 0%
35464322 | CWSP - SYCAMORE CREEK 11112268 PH 3.2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 1.67 | 0 | 1.67 | 0 | 0% | 0.01988% | 0%
35464323 | CWSP - SYCAMORE CREEK 11112268 PH 3.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 1.55 | 0 | 1.55 | 0 | 0% | 0.01845% | 0%
35458434 | CWSP - ALLEGHANY 1102CB NEVADA PH 4.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.39 | 0 | 2.39 | 0 | 0% | 0.02434% | 0%
35460160 | CWSP - SYCAMORE CREEK 11112268 PH 1.2 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 4.37 | 0 | 4.37 | 0 | 0% | 0.05201% | 0%
35460162 | CWSP - SYCAMORE CREEK 11112268 PH 1.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Chico | BUTTE | Tier 3 | SYCAMORE CREEK 11112268 | Proceed | 5.03 | 0 | 5.03 | 0 | 0% | 0.05987% | 0%
35420112 | CWSP - PLACERVILLE 210611132 PH 2.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 4.15 | 0.020076 | 4.1299 | 0 | 0.0001329% | 0.03099% | 0%
35457280 | CWSP - ALLEGHANY 1102CB PH 3.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 3.77 | 0 | 3.77 | 0 | 0% | 0.03839% | 0%
35457281 | CWSP - ALLEGHANY 1102CB PH 3.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.31 | 0 | 2.31 | 0 | 0% | 0.02352% | 0%
35457800 | CWSP - ALLEGHANY 1102CB SIERRA PH 2.3 | UG | ADER | 3UG | SH | SI | Region 2 - North East | Camptonville | SIERRA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.14 | 0 | 2.14 | 0 | 0% | 0.02179% | 0%
35451492 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.2 | UG | ESTS | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 3.3299 | 0 | 3.3299 | 0 | 0% | 0.0431% | 0%
35451493 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.3 | UG | ESTS | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 1.96 | 0 | 1.96 | 0 | 0% | 0.02537% | 0%
35451494 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.4 | UG | ESTS | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 3.5299 | 0 | 3.5299 | 0 | 0% | 0.04569% | 0%
35451495 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.5 | UG | ESTS | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed - RESCOPE | 0.82992 | 0 | 0.82992 | 0 | 0% | 0.01074% | 0%
35452898 | CWSP - PIKE CITY 11011720 PH 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camptonville | YUBA | Tier 3 | PIKE CITY 11011720 | Proceed | 4.42 | 0 | 4.42 | 0 | 0% | 0.06477% | 0%
35450186 | CWSP - BONNIE NOOK 1101CB PH 1.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Alta | PLACER | Tier 3 | BONNIE NOOK 1101CB | Proceed | 0.78996 | 0 | 0.78996 | 0 | 0% | 0.01152% | 0%
35447662 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.197 | 0 | 2.197 | 0 | 0% | 0.02237% | 0%
35447663 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.3 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Nevada City | NEVADA | Tier 3 | ALLEGHANY 1102CB | Proceed | 2.97 | 0 | 2.97 | 0 | 0% | 0.03025% | 0%
35448085 | CWSP - NOTRE DAME 11042028 PH 1.3 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 2.338 | 0 | 2.338 | 0 | 0% | 0.03535% | 0%
35448086 | CWSP - NOTRE DAME 11042028 PH 1.4 | UG | UNSE | 3UG | SH | NV | Region 2 - North East | Forest Ranch | BUTTE | Tier 3 | NOTRE DAME 11042028 | Proceed | 1.986 | 0 | 1.986 | 0 | 0% | 0.03003% | 0%
35439898 | CWSP - ANTLER 11011384 PH 1.2 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011384 | Proceed | 4.939 | 0 | 4.939 | 0 | 0% | 0.06411% | 0%
35439899 | CWSP - ANTLER 11011384 PH 1.3 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011384 | Proceed | 1.334 | 0 | 1.334 | 0 | 0% | 0.01732% | 0%
35523412 | PSPS - TEJON 1102 LR732836 PH 1.4 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 1102732836 | Proceed - RESCOPE | 2.9021 | 0 | 2.9021 | 0 | 0% | 0.01966% | 0%
35436101 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.4 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | El Portal | MARIPOSA | Tier 2 | INDIAN FLAT 1104CB | Proceed | 3.45 | 0 | 3.45 | 0 | 0% | 0.04466% | 0%
35436513 | CWSP - APPLE HILL 1104 CB PH 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Camino | EL DORADO | Tier 2 | APPLE HILL 1104CB | Proceed | 2.36 | 0 | 2.36 | 0 | 0% | 0.02764% | 0%
35436514 | CWSP - APPLE HILL 21026552 PH 1.2 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | APPLE HILL 21026552 | Proceed | 3.56 | 0 | 3.56 | 0 | 0% | 0.0486% | 0%
35436515 | CWSP - APPLE HILL 21026552 PH 2.2 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | APPLE HILL 21026552 | Proceed | 3.53 | 0.03 | 3.5 | 0 | 0.0003594% | 0.04778% | 0%
35436516 | CWSP - APPLE HILL 21026552 PH 2.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | APPLE HILL 21026552 | Proceed | 2.26 | 0 | 2.26 | 0 | 0% | 0.03085% | 0%
35523414 | PSPS - TEJON 1102 LR732836 PH 2.3 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 1102732836 | Proceed - RESCOPE | 2.443 | 0 | 2.443 | 0 | 0% | 0.01655% | 0%
35523415 | PSPS - TEJON 1102 LR732836 PH 2.4 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 1102732836 | Proceed - RESCOPE | 1.954 | 0 | 1.954 | 0 | 0% | 0.01324% | 0%
35523413 | PSPS - TEJON 1102 LR732836 PH 2.1 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 1102732836 | Proceed - RESCOPE | 2.8131 | 0 | 2.8131 | 0 | 0% | 0.01906% | 0%
35433421 | CWSP - ANTLER 11011520 PH 1.6 | UG | PEND | 3UG | SH | NV | Region 2 - North East | Lakehead | SHASTA | Tier 2 | ANTLER 11011520 | Proceed | 2.841 | 0 | 2.841 | 0 | 0% | 0.03192% | 0%
35391721 | CWSP - PLACERVILLE 2106-11132 PH 4.1 | Hybrid | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 9.4799 | 2.6799 | 6.8 | 0 | 0.01774% | 0.05103% | 0%
35391722 | CWSP - PLACERVILLE 210611132 PH 5.1 | Hybrid | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 8.7201 | 3.25 | 5.4701 | 0 | 0.02152% | 0.04105% | 0%
35526467 | CWSP - NOTRE DAME 1104176446 | OH | UNSE | 08W | SH | NV | Region 2 - North East | Chico | BUTTE |  | NOTRE DAME 1104176446 | Proceed - RESCOPE | 8.46 | 8.46 | 0 | 0 | 0.06795% | 0% | 0%
35379381 | CWSP - CLAYTON 2212681608 PH 1.1 | OH | UNSE | 3UG | SH | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | Tier 2 & 3 | CLAYTON 2212681608 | Proceed - RESCOPE | 8.0799 | 8.0799 | 0 | 0 | 0.06215% | 0% | 0%
35391471 | CWSP - PLACERVILLE 210611132 PH 1.1 | Hybrid | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | PLACERVILLE 210611132 | Proceed - RESCOPE | 9.21 | 6.31 | 2.9 | 0 | 0.04178% | 0.02176% | 0%
35425877 | CWSP - SILVERADO 2104646776 PH 1.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 1.225 | 0 | 1.225 | 0 | 0% | 0.01836% | 0%
35425878 | CWSP - SILVERADO 2104646776 PH 1.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 1.684 | 0 | 1.684 | 0 | 0% | 0.02524% | 0%
35425643 | CWSP - SILVERADO 2104 LR 632 PH 1.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 2.508 | 0 | 2.508 | 0 | 0% | 0.03759% | 0%
35425644 | CWSP - SILVERADO 2104 LR 632 PH 1.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Pope Valley | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 4.114 | 0 | 4.114 | 0 | 0% | 0.06166% | 0%
35425645 | CWSP - SILVERADO 2104 LR 632 PH 1.4 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 3.212 | 0 | 3.212 | 0 | 0% | 0.04814% | 0%
35425646 | CWSP - WEST POINT 11014706 PH 2.2 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 2.917 | 0 | 2.917 | 0 | 0% | 0.03209% | 0%
35425647 | CWSP - WEST POINT 11014706 PH 2.3 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 1.86 | 0 | 1.86 | 0 | 0% | 0.02046% | 0%
35411026 | CWSP WEST POINT 1101 LR4706 PH1.2 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 3.36 | 0 | 3.36 | 0 | 0% | 0.03696% | 0%
35411027 | CWSP WEST POINT 1101 LR4706 PH1.3 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 3.51 | 0 | 3.51 | 0 | 0% | 0.03862% | 0%
35411028 | CWSP WEST POINT 1101 LR4706 PH1.4 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 11014706 | Proceed | 1.69 | 0 | 1.69 | 0 | 0% | 0.01859% | 0%
35429499 | CWSP - WEST POINT 11021341 PH1.2 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 1.1799 | 0 | 1.1799 | 0 | 0% | 0.0132% | 0%
35429560 | CWSP - WEST POINT 11021341 PH1.3 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 2.5 | 0 | 2.5 | 0 | 0% | 0.02796% | 0%
35429561 | CWSP - WEST POINT 11021341 PH1.4 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 2.0699 | 0 | 2.0699 | 0 | 0% | 0.02315% | 0%
35429562 | CWSP - WEST POINT 11021341 PH1.5 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 2.05 | 0 | 2.05 | 0 | 0% | 0.02293% | 0%
35429563 | CWSP - WEST POINT 11021341 PH1.6 | Hybrid | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | Tier 3 | WEST POINT 11021341 | Proceed | 0.33977 | 0.16989 | 0.16989 | 0 | 0.001676% | 0.0019% | 0%
35429566 | CWSP - SILVERADO 2104 LR 515946 PH 2.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed | 3.795 | 0 | 3.795 | 0 | 0% | 0.0622% | 0%
35523416 | PSPS - TEJON 11023751 PH 2.1 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 11023751 | Proceed - RESCOPE | 2.958 | 0 | 2.958 | 0 | 0% | 0.01715% | 0%
35523417 | PSPS - TEJON 11023751 PH 2.2 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 11023751 | Proceed - RESCOPE | 2.2521 | 0 | 2.2521 | 0 | 0% | 0.01306% | 0%
35523418 | PSPS - TEJON 11023751 PH 2.3 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 11023751 | Proceed - RESCOPE | 2.997 | 0 | 2.997 | 0 | 0% | 0.01738% | 0%
35523419 | PSPS - TEJON 11023751 PH 2.4 | UG | UNSE | 3UG | SH | KE | Region 5 - Central Valley | Lebec | KERN |  | TEJON 11023751 | Proceed - RESCOPE | 1.357 | 0 | 1.357 | 0 | 0% | 0.007869% | 0%
35401011 | CWSP MARIPOSA 210110240 PH 1.2 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - Rescope | 2.46 | 0 | 2.46 | 0 | 0% | 0.0141% | 0%
35401013 | CWSP MARIPOSA 210110240 PH 1.4 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - Rescope | 3.15 | 0 | 3.15 | 0 | 0% | 0.01806% | 0%
35430878 | CWSP - BUCKS CREEK 1102 CB PH1.2 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 3.4676 | 0 | 3.4676 | 0 | 0% | 0.05096% | 0%
35430879 | CWSP - BUCKS CREEK 1102 CB PH2.2 | OH | ESTS | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 0.79451 | 0.73769 | 0.056818 | 0 | 0.009733% | 0.000835% | 0%
35430880 | CWSP - BUCKS CREEK 1102 CB PH2.3 | UG | ESTS | 3UG | SH | NV | Region 2 - North East | Twain | PLUMAS | Tier 2 | BUCKS CREEK 1102CB | Proceed | 2.5 | 0 | 2.5 | 0 | 0% | 0.03674% | 0%
35431074 | CWSP - ELECTRA 1101L1697 PH 1.2 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | ELECTRA 1101L1697 | Proceed | 2.05 | 0 | 2.05 | 0 | 0% | 0.0229% | 0%
35431075 | CWSP - ELECTRA 1101L1697 PH 1.3 | Hybrid | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pine Grove | AMADOR | Tier 2 | ELECTRA 1101L1697 | Proceed | 2.3799 | 0.87992 | 1.5 | 0 | 0.008713% | 0.01675% | 0%
35428391 | CWSP - APPLE HILL 21027502 PH 1.2 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | APPLE HILL 21027502 | Proceed | 3.9123 | 0 | 3.9123 | 0 | 0% | 0.04669% | 0%
35428392 | CWSP - APPLE HILL 21027502 PH 1.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 & 3 | APPLE HILL 21027502 | Proceed | 4.1402 | 0 | 4.1402 | 0 | 0% | 0.04941% | 0%
35428397 | CWSP - APPLE HILL 21027502 PH 3.2 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Pollock Pines | EL DORADO | Tier 3 | APPLE HILL 21027502 | Proceed | 2.45 | 0 | 2.45 | 0 | 0% | 0.02924% | 0%
35428401 | CWSP - APPLE HILL 21027502 PH 3.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Pollock Pines | EL DORADO | Tier 3 | APPLE HILL 21027502 | Proceed | 3.69 | 0 | 3.69 | 0 | 0% | 0.04404% | 0%
35428403 | CWSP - SILVERADO 2104 LR 515946 PH 1.2 | UG | ESTS | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104515946 | Proceed | 2.739 | 0 | 2.739 | 0 | 0% | 0.04489% | 0%
35397962 | CWSP MARIPOSA 210110240 PH 2.2 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Midpines | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - Rescope | 4.2 | 0 | 4.2 | 0 | 0% | 0.02407% | 0%
35397963 | CWSP MARIPOSA 210110240 PH 2.3 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Midpines | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - RESCOPE | 3.8799 | 0 | 3.8799 | 0 | 0% | 0.02224% | 0%
35428425 | CWSP - SILVERADO 2104 LR 632 PH 2.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Angwin | NAPA | Tier 3 | SILVERADO 2104632 | Proceed | 2.57 | 0 | 2.57 | 0 | 0% | 0.03852% | 0%
35401012 | CWSP MARIPOSA 210110240 PH 1.3 | UG | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Midpines | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - Rescope | 3.11 | 0 | 3.11 | 0 | 0% | 0.01783% | 0%
35391473 | CWSP - PLACERVILLE 2106-11132 PH 3.1 | Hybrid | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | PLACERVILLE 210611132 | Proceed - RESCOPE | 9.3801 | 7.81 | 1.5701 | 0 | 0.05171% | 0.01178% | 0%
35374570 | CWSP - NARROWS 2102CB 1.1 | OH | UNSE | 3UG | SH | SI | Region 2 - North East | Smartsville | NEVADA | Tier 2 | NARROWS 2102CB | Proceed - RESCOPE | 4.99 | 4.99 | 0 | 0 | 0.03493% | 0% | 0%
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Hybrid | UNSE | 08W | SH | HB | Region 1 - North Coast | Middletown | LAKE | Tier 3 | MIDDLETOWN 110148212 | Proceed - RESCOPE | 2.107 | 0.55701 | 1.55 | 0 | 0.01036% | 0.03203% | 0%
35379383 | CWSP MARIPOSA 210110240 PH 1.1 | Hybrid | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - RESCOPE | 10.06 | 7.3201 | 1.6 | 1.14 | 0.03754% | 0.009171% | 0.008975%
35524571 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Removal | UNSE | 08W | SH | FR | Region 5 - Central Valley | Woodlake | TULARE |  | DUNLAP 11027050 | Proceed - RESCOPE | 2.6 | 0 | 0 | 2.6 | 0% | 0% | 0.01441%
35423400 | CWSP - BONNIE NOOK 1101CB PH 1.2 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Alta | PLACER | Tier 3 | BONNIE NOOK 1101CB | Proceed | 5.655 | 0 | 5.655 | 0 | 0% | 0.08245% | 0%
35424354 | CWSP - BONNIE NOOK 1101CB PH 2.2 | UG | PEND | 3UG | SH | SI | Region 2 - North East | Dutch Flat | PLACER | Tier 3 | BONNIE NOOK 1101CB | Proceed | 0.381 | 0 | 0.381 | 0 | 0% | 0.005555% | 0%
35424355 | CWSP - BONNIE NOOK 1101CB PH 2.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Dutch Flat | PLACER | Tier 3 | BONNIE NOOK 1101CB | Proceed | 6.817 | 0 | 6.817 | 0 | 0% | 0.09939% | 0%
35382932 | CWSP MARIPOSA 210110240 PH 2.1 | Hybrid | UNSE | 3UG | SH | YO | Region 5 - Central Valley | Midpines | MARIPOSA | Tier 2 & 3 | MARIPOSA 210110240 | Proceed - RESCOPE | 9.66 | 8.5201 | 0.22992 | 0.91004 | 0.0437% | 0.001318% | 0.007165%
35403554 | CWSP-SILVERADO 2105 167360&990552 PH1.5 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105167360 | Proceed - RESCOPE | 2.95 | 0 | 2.95 | 0 | 0% | 0.01103% | 0%
35403551 | CWSP-SILVERADO 2105 167360&990552 PH1.2 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105167360 | Proceed - RESCOPE | 1.25 | 0 | 1.25 | 0 | 0% | 0.004675% | 0%
35403552 | CWSP-SILVERADO 2105 167360&990552 PH1.3 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105167360 | Proceed - RESCOPE | 2.31 | 0 | 2.31 | 0 | 0% | 0.008639% | 0%
35424589 | CWSP - PLACERVILLE 210611132 PH 6.2 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed | 0.727 | 0.015 | 0.712 | 0 | 9.931e-05% | 0.005343% | 0%
35424590 | CWSP - PLACERVILLE 210611132 PH 6.3 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 210611132 | Proceed | 1.885 | 0 | 1.885 | 0 | 0% | 0.01414% | 0%
35421185 | CWSP - APPLE HILL 21026552 PH 1.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | APPLE HILL 21026552 | Proceed | 3.74 | 0 | 3.74 | 0 | 0% | 0.05105% | 0%
35421186 | CWSP - APPLE HILL 21026552 PH 2.1 | UG | ESTS | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 2 | APPLE HILL 21026552 | Proceed | 3.63 | 0 | 3.63 | 0 | 0% | 0.04955% | 0%
35421187 | CWSP - WEST POINT 1101 CB & 12256 PH 2.2 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 1101CB | Proceed | 3.6598 | 0 | 3.6598 | 0 | 0% | 0.03326% | 0%
35421188 | CWSP - WEST POINT 1101 CB & 12256 PH 2.3 | UG | ESTS | 3UG | SH | ST | Region 5 - Central Valley | Pioneer | AMADOR | Tier 3 | WEST POINT 1101CB | Proceed | 1.6 | 0 | 1.6 | 0 | 0% | 0.01454% | 0%
35403553 | CWSP-SILVERADO 2105 167360&990552 PH1.4 | UG | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105167360 | Proceed - RESCOPE | 1.5299 | 0 | 1.5299 | 0 | 0% | 0.005722% | 0%
35417127 | CWSP - PLACERVILLE 2106-935216 PH 1.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 2106935216 | Proceed | 6.67 | 0 | 6.67 | 0 | 0% | 0.07217% | 0%
35418255 | CWSP - PLACERVILLE 2106-935216 PH 2.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 2106935216 | Proceed | 5.23 | 0 | 5.23 | 0 | 0% | 0.05659% | 0%
35418305 | CWSP - PLACERVILLE 2106-935216 PH 3.1 | UG | UNSE | 3UG | SH | SI | Region 2 - North East | Placerville | EL DORADO | Tier 3 | PLACERVILLE 2106935216 | Proceed | 5.13 | 0 | 5.13 | 0 | 0% | 0.05551% | 0%
35524570 | REMG 499 - PIT NO 7 1101 | Removal | UNSE | 08W | SH | NV | Region 2 - North East | Montgomery Creek | SHASTA |  | PIT NO 7 1101CB | Proceed - RESCOPE | 2.7098 | 0 | 0 | 2.7098 | 0% | 0% | 0.01263%
35418356 | CWSP - SILVERADO 2105900104 | OH | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 2 & 3 | SILVERADO 2105900104 | Proceed - RESCOPE | 0.18996 | 0.18996 | 0 | 0 | 0.000867% | 0% | 0%
35418375 | CWSP - STANISLAUS 17026028 PH 1.1 | UG | UNSE | 3UG | SH | ST | Region 5 - Central Valley | Arnold | CALAVERAS | Tier 3 | STANISLAUS 17026028 | Proceed | 1.94 | 0 | 1.94 | 0 | 0% | 0.02256% | 0%
35367518 | CWSP-SILVERADO 2105 167360&990552 PH1.1 | Hybrid | UNSE | 3UG | SH | NB | Region 1 - North Coast | Saint Helena | NAPA | Tier 3 | SILVERADO 2105167360 | Proceed - RESCOPE | 7 | 5.1299 | 1.8701 | 0 | 0.01733% | 0.006994% | 0%

## SAP Status Key
SAP Status and Status
SAP Status | Status | Description
UNSE | Scoping/Scoped | Project is being scoped for appropriate hardening method and general route alignment.
ESTS | Estimating | Detailed engineering drawing and estimate is created.
ADER | Estimating | Project drawing and estimates being reviewed and approved by senior engineer/estimator.
APPR | Estimating | Project drawing and estimates being reviewed and approved by supervisor.
PEND | Permitting/Dependency | Project obtains all necessary permits and land rights for execution/construction.
UNSC | Ready for Construction | Project is ready to be scheduled for start of construction.
CONS | In-Construction | Construction is underway (can occur across different phases throughout the legnth of the project).
DOCC | Post-Construction | Construction is complete, "as-built" documents are being collected/finalized.
DCNL | Post-Construction | Final labor charges posted, order not ready to be mapped.
MAPP | Post-Construction | Completed project is being added to PG&E GIS system of record.
POST | Post-Construction | Completed project requiring post-estimate.
FICL | Post-Construction | Project is financially closed out (no additional labor charges).
PROD | Post-Construction | With Utility Operations Production Specialist for special handling prior to completion/closure
PREC | Post-Construction | Final project closeout checklist is completed.
CLSD | Closed | Project is completely closed in system of record.