## 2024
*Log Begins July 8, 2024*
Horizon West Transmission
2025 WMP Update Data Request Log
As of August 29, 2024
Count | Party Name | DR Set # | Data Request | Question No. | Question ID | Question | Response | Requestor | Date Received | Final Due Date | Date Sent | Links | No. of Attachments | NDA Required | WMP Section | Category | Subcategory | Confidential
1 | OEIS | 1 | OEIS-P-WMP_2024-HWT-001 | 1 | Q01 | Regarding Changes to Community Outreach and Engagement Expenditures: a.On page 8 of its 2025 WMP Update, Horizon West discusses 2025 expenditures for a new Community Outreach and Engagement initiative under its “Best Practices [sic] Sharing with Other Utilities” initiative activity. Horizon West states that it anticipates joining two industry groups in 2025 as part of this initiative and forecasts total expenditures for participation to be approximately $80,000. However, Horizon West does not list any new programs under Section 4 “New or Discontinued Programs” in its WMP Update. i. Does Horizon West consider its new Community Outreach and Engagement initiative a new program? 1. If so, why was the program not discussed under Section 4 of its WMP Update? 2. If not, explain why Horizon West does not consider this new initiative and associated expenditures a new program. | HWT does not consider its anticipated involvement with the two industry groups in 2025 as a new program. At the time HWT submitted its 2025 WMP update, it only had information regarding the costs of participation in the industry groups and minimal details regarding the activities of the industry groups. As such there is insufficient information for HWT to determine the specifics of its involvement in the industry groups at the present time. Additionally, HWT considers the anticipated participation in the industry group as an initiative specifically aimed at supporting its 2026-2028 WMP requirement to document instances of sharing of best practices amongst utilities. | Jessica McHale | 2024-08-08 | 2024-08-13 | 2024-08-13 | N/A | N/A | N/A | 2025 WMP Update | Section 4 | New or Discontinued Programs | N/A
2 | OEIS | 1 | OEIS-P-WMP_2024-HWT-001 | 1 | Q02 | Regarding Asset and Vegetation Management Inspections Targets: a. On page 9 of its 2025 WMP Update, Horizon West shows 2025 asset inspection completion targets of 6 by the end Q2, 9 by the end of Q3, and 12 by end-of-year. These targets are not reflected in Table 8-4 “Asset Inspections Targets by Year” of the Redlined Base WMP. Are the 2025 quarterly asset inspection targets provided in the 2025 WMP Update accurate? b. On page 10 of its 2025 WMP Update, Horizon West shows 2025 vegetation management inspection completion targets of 3 by the end of Q2, 4 by the end of Q3, and 6 by end-of-year. These targets are not reflected in Table 8-15 “Vegetation Inspections Targets by Year” of the Redlined Base WMP. Are the 2025 quarterly vegetation inspection targets provided in the 2025 WMP Update accurate? | a. The 2025 quarterly asset inspection targets provided in the 2025 WMP Update are accurate. There was an error in the version of the Table 8-4 that was submitted which did not capture the revisions. HWT will submit a revised Redlined Base WMP with the intended Table 8-4. Below is a representation of the intended Table 8-4. b. The 2025 quarterly vegetation management inspection targets provided in the 2025 WMP Update are accurate. There was an error in the version of the Table 8-15 that was submitted which did not capture the revisions. HWT will submit a revised Redlined Base WMP with the intended Table 8-15. Below is a representation of the intended Table 8-15. | Jessica McHale | 2024-08-08 | 2024-08-13 | 2024-08-13 | N/A | N/A | N/A | 8.1 | Grid Design, Operations, and Maintenance | Table 8-4 Table 8-15 | N/A