## Intro - Table
Segments Contributing to Top 5% of Risk | 41
--> Already Hardened or Included in other SH Programs | 4
--> Will be Undergrounded in 2023-2025 | 16
--> Planned for 2026 or later SH | 19
--> Privately Owned Lines | 2
Circuit Segment ID | Already Hardened or in other SH programs | To be UG 2023-2025 | Planned for SH 2026 or later | Privately Owned Lines | Rationale
INDIAN FLAT 1104CB |  |  | TRUE |  | In Table 7-4: 2026 UG |  | already hardened | ug in 2023-2025 | SH 26 or later | pirvately owned
BONNIE NOOK 1101CB |  | TRUE |  |  | In Table 7-4: 2025 UG | old | 7 | 13 | 19 | 2
ALLEGHANY 1102CB |  | TRUE |  |  | In Table 7-4: 2025 UG Line Removal in 2023 | new | 4 | 16 | 19 | 2
OAK HURST 110310140 |  |  | TRUE |  | Long Term Undergrounding Plan
SILVERADO 2104515946 |  |  | TRUE |  | In Table 7-4: 2026 UG
HIGHLANDS 1102628 |  | TRUE |  |  | In Table 7-4: 2023 UG
UPPER LAKE 11011276 |  | TRUE |  |  | In Table 7-4: 2023 UG
MIDDLETOWN 110148212 |  | TRUE |  |  | In Table 7-4: 2023 UG
APPLE HILL 21026552 |  | TRUE |  |  | In Table 7-4: 2024 UG
NOTRE DAME 11042028 |  |  | TRUE |  | In Table 7-4: 2026 UG
CLAYTON 221296224 |  | TRUE |  |  | In Table 7-4: 2023 UG
ANTLER 11011384 |  |  | TRUE |  | In Table 7-4: 2026 UG
MONTICELLO 1101654 |  |  | TRUE |  | Long Term Undergrounding Plan
BALCH NO 1 1101105414 |  |  | TRUE |  | Long Term Undergrounding Plan
CURTIS 170356972 |  |  | TRUE |  | In Table 7-4: 2026 UG
MONTICELLO 1101630 |  |  | TRUE |  | Long Term Undergrounding Plan
PINE GROVE 1101CB |  |  | TRUE |  | In Table 7-4: 2026 UG
BUCKS CREEK 1101CB |  | TRUE |  |  | In Table 7-4: 2023 UG
SILVERADO 2104646776 |  |  | TRUE |  | In Table 7-4: 2026 UG
CALISTOGA 1102131531 | TRUE |  |  |  | In Table 7-4: Existing REFCL Circuit
APPLE HILL 1104CB |  | TRUE |  |  | In Table 7-4: 2024 UG
MIDDLETOWN 1101171414 |  |  | TRUE |  | In Table 7-4: 2026 UG
ELECTRA 1102CB |  |  | TRUE |  | Long Term Undergrounding Plan
ORO FINO 1102CB |  |  | TRUE |  | In Table 7-4: 2026 UG
FRENCH GULCH 1101CB |  |  | TRUE |  | Long Term Undergrounding Plan
PARADISE 1103283794 |  | TRUE |  |  | In Table 7-4: 2024 UG
PARADISE 11061212 |  | TRUE |  |  | In Table 7-4: 2024 UG
CRESTA 1101103126 | TRUE |  |  |  | In Table 7-4: Existing OH Hardened Circuit
CRESTA 1101546650 | TRUE |  |  |  | In Table 7-4: Existing OH Hardened Circuit
MONTICELLO 1101CB |  |  | TRUE |  | Long Term Undergrounding Plan
TIGER CREEK 0201CB |  | TRUE |  |  | In Table 7-4: 2024 UG
INDIAN FLAT 11044440 |  |  | TRUE |  | In Table 7-4: 2026 UG
CALPINE 1144304 |  |  |  | TRUE | In Table 7-4: "Privately Owned Lines"
APPLE HILL 2102CB |  | TRUE |  |  | In Table 7-4: 2024 UG
MIDDLETOWN 1103CB |  | TRUE |  |  | In Table 7-4: 2023 UG
PLACERVILLE 210658118 |  | TRUE |  |  | In Table 7-4: 2024 UG
BALCH NO 1 1101CB |  |  | TRUE |  | Long Term Undergrounding Plan
ALLEGHANY 11021101/2 |  | TRUE |  |  | In Table 7-4: 2025 UG
CALPINE 1144962 |  |  |  | TRUE | In Table 7-4: "Privately Owned Lines"
CAMP EVERS 2105BL 2101 |  |  | TRUE |  | Long Term Undergrounding Plan
MARIPOSA 2101929360 | TRUE |  |  |  | In Table 7-4: Previously OH Hardened Circuit

## a(i) - Table
Segments in 2022 WMP RN Undergrounding Workplan | 332
--> Also included in 2023-2026 Undergrounding Workplan | 193
--> NOT also included in 2023-2026 Undergrounding Workplan | 139
----> In Long Term UG Workplan (work will begin after 2026) | 131
----> NOT in Long Term UG Workplan (work will begin after 2026) | 8
--> Segment was renamed | 5
--> Scheduled for other SH mitigations (OH Hardening or Line Removal) | 3
CPZ | 2022 WMP RN Workplan? | 2023-2026 Undergrounding Workplan? | Long Term Undergrounding Plan? | CPZ | Reason the Circuit Segment does not Appear on 2023-2025 WMP Undergrounding Workplan | Category
PLACERVILLE 210658118 | TRUE | FALSE | TRUE | DUNBAR 1101440 | Circuit segment name changed to DUNBAR 110534. Included in the 2023-2025 WMP Undergrounding Workplan. | Renamed Segment
APPLE HILL 2102CB | TRUE | FALSE | TRUE | DUNBAR 1103234 | Circuit segment name changed to DUNBAR 1101CB. Included in the 2023-2025 WMP Undergrounding Workplan. | Renamed Segment
CALPINE 1144304 | TRUE | FALSE | TRUE | DUNBAR 1103839384 | Circuit segment name changed to DUNBAR 1101CB. Included in the 2023-2025 WMP Undergrounding Workplan. | Renamed Segment
ALLEGHANY 11021101/2 | TRUE | FALSE | TRUE | HALF MOON BAY 11036018 | Circuit segment name changed to HALF MOON BAY 11036012. Included in the 2023-2025 WMP Undergrounding Workplan. | Renamed Segment
PINE GROVE 1101CB | TRUE | TRUE | TRUE | WYANDOTTE 11031504 | Circuit segment name changed to WYANDOTTE 1110980944. Included in 2023-2025 WMP Undergrounding Workplan. | Renamed Segment
TIGER CREEK 0201CB | TRUE | TRUE | TRUE | VOLTA 110111568 | Scheduled for Line Removal. | Other SH Mitigations
INDIAN FLAT 1104CB | TRUE | TRUE | TRUE | BUELLTON 1102CB | Scheduled for Overhead Hardening (Covered Conductor). | Other SH Mitigations
ANTLER 11011384 | TRUE | TRUE | TRUE | POINT MORETTI 1101415734 | Scheduled for Overhead Hardening (Covered Conductor). | Other SH Mitigations
INDIAN FLAT 11044440 | TRUE | FALSE | TRUE
MIDDLETOWN 110148212 | TRUE | TRUE | TRUE
SILVERADO 2104646776 | TRUE | TRUE | TRUE
CLAYTON 221296224 | TRUE | TRUE | TRUE
ORO FINO 1102CB | TRUE | TRUE | TRUE
BONNIE NOOK 1101CB | TRUE | TRUE | TRUE
BUCKS CREEK 1101CB | TRUE | TRUE | TRUE
CALISTOGA 1102131531 | TRUE | FALSE | TRUE
PARADISE 11061212 | TRUE | FALSE | TRUE
HIGHLANDS 1102628 | TRUE | TRUE | TRUE
APPLE HILL 1104CB | TRUE | TRUE | TRUE
CRESTA 1101546650 | TRUE | FALSE | TRUE
APPLE HILL 21026552 | TRUE | TRUE | TRUE
SILVERADO 2104515946 | TRUE | TRUE | TRUE
UPPER LAKE 11011276 | TRUE | TRUE | TRUE
NOTRE DAME 11042028 | TRUE | TRUE | TRUE
MIDDLETOWN 1101171414 | TRUE | TRUE | TRUE
CRESTA 1101103126 | TRUE | FALSE | TRUE
ALLEGHANY 1102CB | TRUE | TRUE | TRUE
KESWICK 11019712 | TRUE | TRUE | TRUE
REDBUD 1101454 | TRUE | TRUE | TRUE
BUCKS CREEK 1102CB | TRUE | TRUE | TRUE
NARROWS 2102CB | TRUE | TRUE | TRUE
CLARK ROAD 110247006 | TRUE | TRUE | TRUE
PIKE CITY 11011720 | TRUE | TRUE | TRUE
STANISLAUS 1702CB | TRUE | TRUE | TRUE
MIDDLETOWN 11011314 | TRUE | TRUE | TRUE
SYCAMORE CREEK 11112268 | TRUE | TRUE | TRUE
PLACERVILLE 2106935216 | TRUE | TRUE | TRUE
SILVERADO 2104632 | TRUE | TRUE | TRUE
STANISLAUS 17026028 | TRUE | TRUE | TRUE
ORO FINO 110276008 | TRUE | TRUE | TRUE
ELECTRA 11017104 | TRUE | TRUE | TRUE
APPLE HILL 21027502 | TRUE | TRUE | TRUE
OREGON TRAIL 11021584 | TRUE | TRUE | TRUE
STANISLAUS 17011812 | TRUE | TRUE | TRUE
PLACERVILLE 210611132 | TRUE | TRUE | TRUE
PARADISE 11032534 | TRUE | TRUE | TRUE
SHADY GLEN 110132726 | TRUE | TRUE | TRUE
TEJON 11022455 | TRUE | TRUE | TRUE
MARIPOSA 2102CB | TRUE | FALSE | TRUE
CALISTOGA 1102141073 | TRUE | FALSE | TRUE
CALPINE 1146CB | TRUE | FALSE | TRUE
WEST POINT 11021341 | TRUE | TRUE | TRUE
WILDWOOD 11011454 | TRUE | FALSE | TRUE
SILVERADO 2105658898 | TRUE | TRUE | TRUE
SHADY GLEN 110248894 | TRUE | TRUE | TRUE
SILVERADO 2105900104 | TRUE | TRUE | TRUE
ANTLER 11011520 | TRUE | TRUE | TRUE
SHADY GLEN 11022232 | TRUE | TRUE | TRUE
ANTLER 1101CB | TRUE | TRUE | TRUE
STANISLAUS 1701CB | TRUE | TRUE | TRUE
FORESTHILL 11022106 | TRUE | TRUE | TRUE
STANISLAUS 170237278 | TRUE | TRUE | TRUE
MIDDLETOWN 1101433160 | TRUE | TRUE | TRUE
CLAYTON 2212614950 | TRUE | TRUE | TRUE
SILVERADO 210478268 | TRUE | TRUE | TRUE
MIDDLETOWN 1101548 | TRUE | TRUE | TRUE
DRUM 1101CB | TRUE | FALSE | TRUE
CALISTOGA 110143924 | TRUE | TRUE | TRUE
MOUNTAIN QUARRIES 2101CB | TRUE | TRUE | TRUE
WEST POINT 11014706 | TRUE | TRUE | TRUE
WILDWOOD 110198896 | TRUE | FALSE | TRUE
WILDWOOD 1101384582 | TRUE | FALSE | TRUE
FORESTHILL 110150486 | TRUE | TRUE | TRUE
CLAYTON 2212681608 | TRUE | TRUE | TRUE
PIKE CITY 1101CB | TRUE | TRUE | TRUE
SILVERADO 2105990552 | TRUE | FALSE | TRUE
ELECTRA 1101L1697 | TRUE | TRUE | TRUE
SHADY GLEN 11012768 | TRUE | FALSE | TRUE
EL DORADO PH 2102542272 | TRUE | FALSE | TRUE
APPLE HILL 110413512 | TRUE | TRUE | TRUE
MARIPOSA 210110240 | TRUE | TRUE | TRUE
REDBUD 1101323962 | TRUE | TRUE | TRUE
ALLEGHANY 1101VR816 | TRUE | FALSE | TRUE
ORO FINO 11022236 | TRUE | FALSE | TRUE
PINE GROVE 11026080 | TRUE | TRUE | TRUE
APPLE HILL 2102836878 | TRUE | TRUE | TRUE
SALT SPRINGS 210297924 | TRUE | TRUE | TRUE
CALISTOGA 1101122350 | TRUE | FALSE | TRUE
NARROWS 2104CB | TRUE | FALSE | TRUE
PINE GROVE 11023172 | TRUE | FALSE | TRUE
ORO FINO 110265932 | TRUE | FALSE | TRUE
WEIMAR 11012084 | TRUE | FALSE | TRUE
ANTLER 11011612 | TRUE | FALSE | TRUE
HIGHLANDS 1103726580 | TRUE | FALSE | TRUE
MIDDLETOWN 1101932140 | TRUE | FALSE | TRUE
PINE GROVE 11013166 | TRUE | TRUE | TRUE
PLACERVILLE 111219712 | TRUE | FALSE | TRUE
ORO FINO 11022090 | TRUE | FALSE | TRUE
TIGER CREEK 0201320746 | TRUE | FALSE | TRUE
NOTRE DAME 1104176446 | TRUE | TRUE | TRUE
HIGHLANDS 1103287766 | TRUE | FALSE | TRUE
ORO FINO 1101CB | TRUE | TRUE | TRUE
PARADISE 1105829194 | TRUE | TRUE | TRUE
MIDDLETOWN 1101959140 | TRUE | FALSE | TRUE
PINE GROVE 1102CB | TRUE | FALSE | TRUE
HIGHLANDS 1101CB | TRUE | FALSE | TRUE
WEST POINT 11024788 | TRUE | TRUE | TRUE
MOUNTAIN QUARRIES 21012422 | TRUE | FALSE | TRUE
WEIMAR 11012058 | TRUE | FALSE | TRUE
CALPINE 1144CB | TRUE | FALSE | TRUE
OAKHURST 11015490 | TRUE | FALSE | TRUE
MIDDLETOWN 1101439572 | TRUE | FALSE | TRUE
MIDDLETOWN 1101352182 | TRUE | FALSE | TRUE
EL DORADO PH 210219542 | TRUE | TRUE | TRUE
MOUNTAIN QUARRIES 210192474 | TRUE | FALSE | TRUE
LOS OSITOS 21033010 | TRUE | TRUE | TRUE
FORESTHILL 11011802 | TRUE | TRUE | TRUE
SHADY GLEN 1102CB | TRUE | FALSE | TRUE
ORO FINO 11022556 | TRUE | FALSE | TRUE
MIDDLETOWN 11014646 | TRUE | TRUE | TRUE
MIDDLETOWN 1101644756 | TRUE | FALSE | TRUE
STANISLAUS 17011331 | TRUE | FALSE | TRUE
BIG BEND 1102CB | TRUE | FALSE | TRUE
WILDWOOD 11011576 | TRUE | FALSE | TRUE
BONNIE NOOK 1102CB | TRUE | TRUE | TRUE
LOS OSITOS 21037014 | TRUE | TRUE | TRUE
CORNING 110185152 | TRUE | FALSE | TRUE
EL DORADO PH 210219562 | TRUE | FALSE | TRUE
APPLE HILL 110497086 | TRUE | FALSE | TRUE
MARIPOSA 2101752630 | TRUE | TRUE | TRUE
CLEAR LAKE 1102904 | TRUE | FALSE | TRUE
SILVERADO 2104726 | TRUE | FALSE | TRUE
PINE GROVE 110213438 | TRUE | TRUE | TRUE
SHADY GLEN 110151696 | TRUE | FALSE | TRUE
ANTLER 11011376 | TRUE | FALSE | TRUE
MIDDLETOWN 1101614 | TRUE | TRUE | TRUE
WEIMAR 1101CB | TRUE | FALSE | TRUE
WEST POINT 1101CB | TRUE | TRUE | TRUE
TEJON 1102732836 | TRUE | TRUE | TRUE
CLAYTON 2212204416 | TRUE | FALSE | TRUE
PLACERVILLE 2106CB | TRUE | FALSE | TRUE
STANISLAUS 170179826 | TRUE | TRUE | TRUE
FORESTHILL 1101CB | TRUE | FALSE | TRUE
PINE GROVE 110245292 | TRUE | TRUE | TRUE
BRUNSWICK 11021010 | TRUE | TRUE | TRUE
PLACERVILLE 21069712 | TRUE | FALSE | TRUE
CALPINE 1144960 | TRUE | FALSE | TRUE
PINE GROVE 110194936 | TRUE | FALSE | TRUE
ANTLER 11011378 | TRUE | FALSE | TRUE
MARIPOSA 2101151918 | TRUE | TRUE | TRUE
WYANDOTTE 1103640652 | TRUE | TRUE | TRUE
ELECTRA 1101CB | TRUE | FALSE | TRUE
PUEBLO 2103678 | TRUE | TRUE | TRUE
WEST POINT 110113444 | TRUE | TRUE | TRUE
MIDDLETOWN 1101128648 | TRUE | FALSE | TRUE
PUEBLO 2103355186 | TRUE | FALSE | TRUE
BRUNSWICK 110651484 | TRUE | TRUE | TRUE
BIG BEND 1102884340 | TRUE | TRUE | TRUE
WEIMAR 11012764 | TRUE | FALSE | TRUE
STANISLAUS 17017144 | TRUE | FALSE | TRUE
HIGHLANDS 1103917328 | TRUE | FALSE | TRUE
WEIMAR 11012740 | TRUE | FALSE | TRUE
ORO FINO 110239154 | TRUE | TRUE | TRUE
MOUNTAIN QUARRIES 21011184 | TRUE | FALSE | TRUE
EL DORADO PH 2102CB | TRUE | TRUE | TRUE
ELECTRA 110136816 | TRUE | FALSE | TRUE
NOTRE DAME 11042537 | TRUE | TRUE | TRUE
SILVERADO 2105247660 | TRUE | FALSE | TRUE
CALISTOGA 11015934 | TRUE | FALSE | TRUE
PIKE CITY 11011730 | TRUE | TRUE | TRUE
PARADISE 1105121988 | TRUE | TRUE | TRUE
PINE GROVE 11023168 | TRUE | FALSE | TRUE
UPPER LAKE 110175370 | TRUE | TRUE | TRUE
PINE GROVE 11011021 | TRUE | FALSE | TRUE
MARIPOSA 2102594143 | TRUE | FALSE | TRUE
JAMESON 110265516 | TRUE | TRUE | TRUE
BRUNSWICK 110651486 | TRUE | TRUE | TRUE
FORESTHILL 110137238 | TRUE | TRUE | TRUE
PIT NO 3 2101CB | TRUE | TRUE | TRUE
UPPER LAKE 1101412 | TRUE | FALSE | TRUE
SPRING GAP 1702188426 | TRUE | FALSE | TRUE
WEST POINT 110112256 | TRUE | FALSE | TRUE
ELECTRA 110161816 | TRUE | FALSE | TRUE
PARADISE 11042034 | TRUE | TRUE | TRUE
TEJON 11023751 | TRUE | TRUE | TRUE
EL DORADO PH 210163464 | TRUE | TRUE | TRUE
REDBUD 1101754544 | TRUE | TRUE | TRUE
STANISLAUS 17021888 | TRUE | TRUE | TRUE
CALISTOGA 1102177784 | TRUE | FALSE | TRUE
APPLE HILL 1104814656 | TRUE | FALSE | TRUE
CALISTOGA 110135588 | TRUE | FALSE | TRUE
MIDDLETOWN 1102302610 | TRUE | TRUE | TRUE
PIT NO 3 21011482 | TRUE | TRUE | TRUE
REDBUD 1101CB | TRUE | FALSE | TRUE
SILVERADO 2105167360 | TRUE | TRUE | TRUE
MARIPOSA 2102440236 | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 21011350 | TRUE | TRUE | TRUE
PARADISE 110343008 | TRUE | TRUE | TRUE
REDBUD 1102523244 | TRUE | FALSE | TRUE
PINE GROVE 11013170 | TRUE | FALSE | TRUE
CALISTOGA 1101886282 | TRUE | FALSE | TRUE
SILVERADO 2105337226 | TRUE | FALSE | TRUE
SILVERADO 21051306 | TRUE | FALSE | TRUE
CALISTOGA 1101257964 | TRUE | FALSE | TRUE
BRUNSWICK 11062104 | TRUE | TRUE | TRUE
SYCAMORE CREEK 11112014 | TRUE | TRUE | TRUE
SILVERADO 2104722 | TRUE | FALSE | TRUE
DUNBAR 1101534 | TRUE | TRUE | TRUE
MIDDLETOWN 1103830 | TRUE | TRUE | TRUE
LOS COCHES 1101625902 | TRUE | TRUE | TRUE
MARIPOSA 2102527766 | TRUE | FALSE | TRUE
CLAYTON 2212158138 | TRUE | FALSE | TRUE
CALISTOGA 1101242919 | TRUE | FALSE | TRUE
HARTLEY 1101698 | TRUE | TRUE | TRUE
VACAVILLE 110838316 | TRUE | TRUE | TRUE
PARADISE 11032486 | TRUE | TRUE | TRUE
PARADISE 1103CB | TRUE | TRUE | TRUE
MARIPOSA 2102241564 | TRUE | FALSE | TRUE
LOS OSITOS 21037062 | TRUE | TRUE | TRUE
WYANDOTTE 11031508 | TRUE | TRUE | TRUE
CALISTOGA 1102769230 | TRUE | FALSE | TRUE
SHADY GLEN 1101585766 | TRUE | FALSE | TRUE
CALPINE 1146400 | TRUE | FALSE | TRUE
SILVERADO 2105131568 | TRUE | FALSE | TRUE
AUBERRY 1101R2578 | TRUE | TRUE | FALSE
POTTER VALLEY P H 11051904 | TRUE | TRUE | TRUE
HIGHLANDS 11031282 | TRUE | FALSE | TRUE
UPPER LAKE 1101CB | TRUE | FALSE | TRUE
CALISTOGA 1101843761 | TRUE | FALSE | TRUE
SILVERADO 2105309298 | TRUE | FALSE | TRUE
AUBERRY 1101R2839 | TRUE | TRUE | FALSE
CORNING 110164090 | TRUE | FALSE | TRUE
SILVERADO 2104708 | TRUE | TRUE | TRUE
PARADISE 1104961990 | TRUE | FALSE | TRUE
ORO FINO 11012022 | TRUE | TRUE | TRUE
MIDDLETOWN 1101481876 | TRUE | FALSE | TRUE
REDBUD 1101708166 | TRUE | TRUE | TRUE
WEST POINT 1101L1969 | TRUE | FALSE | TRUE
CORNING 110253184 | TRUE | TRUE | FALSE
VOLTA 11011516 | TRUE | TRUE | FALSE
CLARK ROAD 11022070 | TRUE | TRUE | FALSE
JAMESON 1105466348 | TRUE | TRUE | TRUE
DUNBAR 1103416 | TRUE | TRUE | TRUE
PARADISE 11052214 | TRUE | FALSE | TRUE
VACAVILLE 11088762 | TRUE | TRUE | FALSE
CALISTOGA 1102634 | TRUE | FALSE | TRUE
EL DORADO PH 21026645 | TRUE | TRUE | TRUE
SILVERADO 21051308 | TRUE | FALSE | TRUE
SILVERADO 2104806 | TRUE | FALSE | TRUE
PARADISE 110636042 | TRUE | TRUE | FALSE
CALISTOGA 1102184814 | TRUE | FALSE | TRUE
SHADY GLEN 1101898212 | TRUE | FALSE | TRUE
SILVERADO 2104324994 | TRUE | FALSE | TRUE
CALISTOGA 1102100335 | TRUE | FALSE | TRUE
PARADISE 110353544 | TRUE | TRUE | TRUE
NOTRE DAME 11042408 | TRUE | FALSE | TRUE
CLARK ROAD 1102514690 | TRUE | TRUE | FALSE
MIDDLETOWN 1101829164 | TRUE | FALSE | TRUE
BIG BASIN 11022253 | TRUE | TRUE | TRUE
WILLOW CREEK 11032936 | TRUE | TRUE | FALSE
BIG MEADOWS 21012510 | TRUE | TRUE | FALSE
JAMESON 1105913400 | TRUE | TRUE | FALSE
PUEBLO 210378504 | TRUE | FALSE | TRUE
CURTIS 1701CB | TRUE | TRUE | FALSE
WOODSIDE 11018974 | TRUE | TRUE | FALSE
CLARK ROAD 110281296 | TRUE | TRUE | TRUE
ELK CREEK 11012002 | TRUE | TRUE | FALSE
DUNBAR 1101440 | TRUE | FALSE | FALSE
DUNBAR 1103234 | TRUE | FALSE | FALSE
PARADISE 1105878870 | TRUE | TRUE | FALSE
PARADISE 110439216 | TRUE | TRUE | FALSE
DIAMOND SPRINGS 11071402 | TRUE | TRUE | FALSE
OAKHURST 1101CB | TRUE | FALSE | TRUE
DUNBAR 1103160 | TRUE | FALSE | TRUE
BIG BASIN 11025066 | TRUE | TRUE | FALSE
SAN RAMON 2103MR279 | TRUE | FALSE | TRUE
ELK CREEK 110193504 | TRUE | TRUE | FALSE
GEYSERVILLE 1101482 | TRUE | TRUE | TRUE
SILVERADO 2105764650 | TRUE | FALSE | TRUE
FLINT 1101750 | TRUE | TRUE | FALSE
BIG MEADOWS 21012476 | TRUE | TRUE | FALSE
PARADISE 1106CB | TRUE | TRUE | FALSE
HIGHLANDS 1104CB | TRUE | TRUE | FALSE
PARADISE 110439214 | TRUE | TRUE | FALSE
DUNBAR 1103839384 | TRUE | FALSE | FALSE
PARADISE 1104920400 | TRUE | TRUE | FALSE
PARADISE 1105CB | TRUE | TRUE | FALSE
CALISTOGA 1101CB | TRUE | FALSE | TRUE
CLAYTON 2212CB | TRUE | FALSE | TRUE
COTTONWOOD 1102544790 | TRUE | TRUE | FALSE
MOLINO 110266006 | TRUE | TRUE | FALSE
WYANDOTTE 1110980944 | TRUE | TRUE | FALSE
JESSUP 11021550 | TRUE | TRUE | FALSE
GOLDTREE 1105CB | TRUE | TRUE | FALSE
JAMESON 11059472 | TRUE | TRUE | FALSE
WYANDOTTE 11031504 | TRUE | FALSE | FALSE
SHINGLE SPRINGS 210551738 | TRUE | FALSE | TRUE
PLACERVILLE 1112CB | TRUE | TRUE | FALSE
VACAVILLE 1111CB | TRUE | TRUE | FALSE
FLINT 1101958726 | TRUE | TRUE | FALSE
AUBERRY 1101CB | TRUE | TRUE | FALSE
BIG MEADOWS 21012260 | TRUE | TRUE | FALSE
HALF MOON BAY 11036018 | TRUE | FALSE | FALSE
PARADISE 11042206 | TRUE | TRUE | FALSE
VOLTA 1101CB | TRUE | TRUE | FALSE
POINT MORETTI 110112122 | TRUE | TRUE | FALSE
STILLWATER 110148950 | TRUE | TRUE | FALSE
ECHO SUMMIT 1101481660 | TRUE | TRUE | FALSE
POTTER VALLEY P H 110537476 | TRUE | TRUE | FALSE
VOLTA 11011568 | TRUE | FALSE | FALSE
POINT MORETTI 1101415734 | TRUE | FALSE | FALSE
CLARK ROAD 1102CB | TRUE | TRUE | FALSE
PARADISE 1104CB | TRUE | TRUE | FALSE
HORSESHOE 110150140 | TRUE | TRUE | FALSE
BUELLTON 1102Y50 | TRUE | TRUE | FALSE
EL CERRITO G 1105BR160 | TRUE | TRUE | FALSE
BELL 11082202 | TRUE | TRUE | FALSE
COTTONWOOD 11029026 | TRUE | TRUE | FALSE
BUELLTON 1102CB | TRUE | FALSE | FALSE
JESSUP 1103770356 | TRUE | TRUE | FALSE
CORNING 1102915324 | TRUE | TRUE | FALSE
LINCOLN 1104275986 | TRUE | TRUE | FALSE
LINCOLN 11042070 | TRUE | TRUE | FALSE
ANDERSON 11031600 | TRUE | TRUE | FALSE
ANDERSON 1103226050 | TRUE | TRUE | FALSE
PANORAMA 1101CB | TRUE | TRUE | FALSE
LINCOLN 1104685276 | TRUE | TRUE | FALSE
SAN RAFAEL 1109535284 | TRUE | FALSE | TRUE
JAMESON 1105371694 | TRUE | TRUE | FALSE
CALPINE 1144276-G | TRUE | FALSE | TRUE
CALPINE 1146200-G | TRUE | FALSE | TRUE
CALPINE 1146394G | TRUE | FALSE | TRUE

## a(i) - Other Mitigations
CPZ | v3 Risk Rank | 2023 Mitigation | 2024 Mitigation | 2025 Mitigation
PLACERVILLE 210658118 | 1 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
APPLE HILL 2102CB | 2 | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALPINE 1144304 | 3 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
ALLEGHANY 11021101/2 | 4 | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
INDIAN FLAT 11044440 | 12 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102131531 | 24 | EPSS Expulsion Fuse Replacement Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PARADISE 11061212 | 26 | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CRESTA 1101546650 | 31 | EPSS Aerial Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
CRESTA 1101103126 | 40 | EPSS Aerial Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
MARIPOSA 2102CB | 77 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102141073 | 78 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALPINE 1146CB | 79 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
WILDWOOD 11011454 | 86 | EPSS Overhead Hardening Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
DRUM 1101CB | 103 | EPSS Aerial Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WILDWOOD 110198896 | 109 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WILDWOOD 1101384582 | 111 | EPSS Aerial Inspection Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105990552 | 117 | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
SHADY GLEN 11012768 | 120 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
EL DORADO PH 2102542272 | 121 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
ALLEGHANY 1101VR816 | 128 | EPSS Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Surge Arrestor Replacement Ground Inspection Veg Mgmt. (Annual & Second Patrol)
ORO FINO 11022236 | 129 | EPSS Aerial Inspection Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101122350 | 134 | EPSS Expulsion Fuse Replacement Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Tree Removal Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
NARROWS 2104CB | 136 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 11023172 | 139 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ORO FINO 110265932 | 140 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WEIMAR 11012084 | 142 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Line Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ANTLER 11011612 | 143 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
HIGHLANDS 1103726580 | 144 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Tree Removal Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101932140 | 146 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PLACERVILLE 111219712 | 148 | EPSS Expulsion Fuse Replacement Surge Arrestor Replacement Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ORO FINO 11022090 | 150 | EPSS Expulsion Fuse Replacement Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
TIGER CREEK 0201320746 | 151 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
HIGHLANDS 1103287766 | 156 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101959140 | 160 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 1102CB | 161 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
HIGHLANDS 1101CB | 163 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MOUNTAIN QUARRIES 21012422 | 165 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WEIMAR 11012058 | 166 | EPSS Expulsion Fuse Replacement Surge Arrestor Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALPINE 1144CB | 169 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
OAKHURST 11015490 | 172 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101439572 | 174 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101352182 | 175 | EPSS Aerial Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
MOUNTAIN QUARRIES 210192474 | 177 | EPSS Surge Arrestor Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
SHADY GLEN 1102CB | 180 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ORO FINO 11022556 | 181 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101644756 | 185 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol)
STANISLAUS 17011331 | 186 | EPSS Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
BIG BEND 1102CB | 187 | EPSS Overhead Hardening Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Overhead Hardening Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WILDWOOD 11011576 | 191 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CORNING 110185152 | 194 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
EL DORADO PH 210219562 | 195 | EPSS Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
APPLE HILL 110497086 | 197 | EPSS Expulsion Fuse Replacement Surge Arrestor Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CLEAR LAKE 1102904 | 200 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2104726 | 203 | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Tree Removal Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
SHADY GLEN 110151696 | 208 | EPSS Ground Inspection Non-Pole Backlog Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
ANTLER 11011376 | 210 | EPSS Surge Arrestor Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
WEIMAR 1101CB | 214 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CLAYTON 2212204416 | 223 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Line Sensors Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PLACERVILLE 2106CB | 230 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
FORESTHILL 1101CB | 232 | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PLACERVILLE 21069712 | 236 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALPINE 1144960 | 238 | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 110194936 | 240 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
ANTLER 11011378 | 247 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Line Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ELECTRA 1101CB | 251 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101128648 | 258 | EPSS Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
PUEBLO 2103355186 | 264 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
WEIMAR 11012764 | 268 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
STANISLAUS 17017144 | 269 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
HIGHLANDS 1103917328 | 270 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
WEIMAR 11012740 | 272 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MOUNTAIN QUARRIES 21011184 | 275 | EPSS Expulsion Fuse Replacement Surge Arrestor Replacement Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ELECTRA 110136816 | 288 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105247660 | 291 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 11015934 | 299 | EPSS Expulsion Fuse Replacement Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 11023168 | 303 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 11011021 | 310 | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MARIPOSA 2102594143 | 312 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
UPPER LAKE 1101412 | 327 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Removal Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
SPRING GAP 1702188426 | 335 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol)
WEST POINT 110112256 | 352 | EPSS Aerial Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
ELECTRA 110161816 | 355 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102177784 | 382 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
APPLE HILL 1104814656 | 386 | EPSS Down Conductor Detection (DCD) Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 110135588 | 389 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
REDBUD 1101CB | 395 | EPSS Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
REDBUD 1102523244 | 407 | EPSS Surge Arrestor Replacement Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PINE GROVE 11013170 | 410 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101886282 | 411 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Tree Removal Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105337226 | 416 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 21051306 | 419 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101257964 | 428 | EPSS Expulsion Fuse Replacement Surge Arrestor Replacement Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Tree Removal Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2104722 | 435 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol)
MARIPOSA 2102527766 | 464 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CLAYTON 2212158138 | 471 | EPSS Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101242919 | 480 | EPSS Expulsion Fuse Replacement Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
MARIPOSA 2102241564 | 515 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102769230 | 534 | EPSS Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Tree Removal Pole Backlog Veg Mgmt. (Annual & Second Patrol)
SHADY GLEN 1101585766 | 542 | EPSS Ground Inspection Non-Pole Backlog Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
CALPINE 1146400 | 543 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105131568 | 556 | EPSS Expulsion Fuse Replacement Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
HIGHLANDS 11031282 | 582 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Line Removal Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
UPPER LAKE 1101CB | 588 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101843761 | 589 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105309298 | 594 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CORNING 110164090 | 615 | EPSS Ground Inspection Non-Pole Backlog Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol)
PARADISE 1104961990 | 622 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Undergrounding Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101481876 | 673 | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
WEST POINT 1101L1969 | 681 | EPSS Down Conductor Detection (DCD) Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
PARADISE 11052214 | 755 | EPSS Undergrounding Expulsion Fuse Replacement Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Undergrounding Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102634 | 769 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 21051308 | 793 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2104806 | 805 | EPSS Expulsion Fuse Replacement Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Pole Backlog Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102184814 | 843 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SHADY GLEN 1101898212 | 869 | EPSS Non-Pole Backlog Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2104324994 | 873 | EPSS Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1102100335 | 874 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
NOTRE DAME 11042408 | 926 | EPSS Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
MIDDLETOWN 1101829164 | 935 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
PUEBLO 210378504 | 1000 | EPSS Expulsion Fuse Replacement Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
OAKHURST 1101CB | 1208 | EPSS Ground Inspection Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
DUNBAR 1103160 | 1232 | EPSS Ground Inspection Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol)
SAN RAMON 2103MR279 | 1337 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SILVERADO 2105764650 | 1407 | EPSS Ground Inspection Non-Pole Backlog Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALISTOGA 1101CB | 1636 | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CLAYTON 2212CB | 1654 | EPSS Aerial Inspection Ground Inspection Non-Pole Backlog Line Sensors Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SHINGLE SPRINGS 210551738 | 1953 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
SAN RAFAEL 1109535284 | 5065 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Ground Inspection Down Conductor Detection (DCD) Veg Mgmt. (Annual & Second Patrol) | EPSS Aerial Inspection Ground Inspection Veg Mgmt. (Annual & Second Patrol)
CALPINE 1144276-G | 11159 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALPINE 1146200-G | 11159 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)
CALPINE 1146394G | 11159 | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol) | EPSS Veg Mgmt. (Annual & Second Patrol)

## a(ii) - Table
Segments in Top 20% of Risk Ranked Segments | 720
--> Also included in 2023-2026 Undergrounding Workplan | 153
--> NOT also included in 2023-2026 Undergrounding Workplan | 567
----> In Long Term UG Workplan (work will begin after 2026) | 477
----> NOT in Long Term UG Workplan (work will begin after 2026) | 90
----> Have already been hardened | 11
----> Have NOT already been hardened or are scheduled for SH | 79
CPZ | Top 20% of Risk Ranked Segments? | 2023-2026 Undergrounding Workplan? | Long Term Undergrounding Workplan? | Already Hardened ?
PLACERVILLE 210658118 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 2102CB | TRUE | FALSE | TRUE | FALSE
CALPINE 1144304 | TRUE | FALSE | TRUE | FALSE
ALLEGHANY 11021101/2 | TRUE | FALSE | TRUE | FALSE
BALCH NO 1 1101CB | TRUE | FALSE | TRUE | FALSE
PINE GROVE 1101CB | TRUE | TRUE | TRUE | FALSE
CAMP EVERS 2105BL 2101 | TRUE | FALSE | TRUE | FALSE
TIGER CREEK 0201CB | TRUE | TRUE | TRUE | FALSE
MONTICELLO 1101630 | TRUE | FALSE | TRUE | FALSE
INDIAN FLAT 1104CB | TRUE | TRUE | TRUE | FALSE
ANTLER 11011384 | TRUE | TRUE | TRUE | FALSE
INDIAN FLAT 11044440 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 110148212 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2104646776 | TRUE | TRUE | TRUE | FALSE
CLAYTON 221296224 | TRUE | TRUE | TRUE | FALSE
MARIPOSA 2101929360 | TRUE | FALSE | TRUE | FALSE
ORO FINO 1102CB | TRUE | TRUE | TRUE | FALSE
BALCH NO 1 1101105414 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101CB | TRUE | FALSE | TRUE | FALSE
BONNIE NOOK 1101CB | TRUE | TRUE | TRUE | FALSE
BUCKS CREEK 1101CB | TRUE | TRUE | TRUE | FALSE
OAKHURST 110310140 | TRUE | FALSE | TRUE | FALSE
PARADISE 1103283794 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1102131531 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1103CB | TRUE | FALSE | TRUE | FALSE
PARADISE 11061212 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101654 | TRUE | FALSE | TRUE | FALSE
ELECTRA 1102CB | TRUE | FALSE | TRUE | FALSE
HIGHLANDS 1102628 | TRUE | TRUE | TRUE | FALSE
APPLE HILL 1104CB | TRUE | TRUE | TRUE | FALSE
CRESTA 1101546650 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 21026552 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2104515946 | TRUE | TRUE | TRUE | FALSE
CURTIS 170356972 | TRUE | FALSE | TRUE | FALSE
UPPER LAKE 11011276 | TRUE | TRUE | TRUE | FALSE
FRENCH GULCH 1101CB | TRUE | FALSE | TRUE | FALSE
NOTRE DAME 11042028 | TRUE | TRUE | TRUE | FALSE
MIDDLETOWN 1101171414 | TRUE | TRUE | TRUE | FALSE
CALPINE 1144962 | TRUE | FALSE | TRUE | FALSE
CRESTA 1101103126 | TRUE | FALSE | TRUE | FALSE
ALLEGHANY 1102CB | TRUE | TRUE | TRUE | FALSE
FRENCH GULCH 1102CB | TRUE | FALSE | TRUE | FALSE
KESWICK 11019712 | TRUE | TRUE | TRUE | FALSE
REDBUD 1101454 | TRUE | TRUE | TRUE | FALSE
BUCKS CREEK 1102CB | TRUE | TRUE | TRUE | FALSE
NARROWS 2102CB | TRUE | TRUE | TRUE | FALSE
CLARK ROAD 110247006 | TRUE | TRUE | TRUE | FALSE
KESWICK 11011586 | TRUE | TRUE | TRUE | FALSE
EL DORADO PH 210119752 | TRUE | TRUE | TRUE | FALSE
MIWUK 170236888 | TRUE | FALSE | TRUE | FALSE
KONOCTI 11022293 | TRUE | FALSE | TRUE | FALSE
PIKE CITY 11011720 | TRUE | TRUE | TRUE | FALSE
BEAR VALLEY 2105CB | TRUE | FALSE | TRUE | FALSE
STANISLAUS 1702CB | TRUE | TRUE | TRUE | FALSE
APPLE HILL 210289934 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 11011314 | TRUE | TRUE | TRUE | FALSE
SYCAMORE CREEK 11112268 | TRUE | TRUE | TRUE | FALSE
PLACERVILLE 2106935216 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2104632 | TRUE | TRUE | TRUE | FALSE
STANISLAUS 17026028 | TRUE | TRUE | TRUE | FALSE
ORO FINO 110276008 | TRUE | TRUE | TRUE | FALSE
ELECTRA 11017104 | TRUE | TRUE | TRUE | FALSE
APPLE HILL 21027502 | TRUE | TRUE | TRUE | FALSE
OREGON TRAIL 11021584 | TRUE | TRUE | TRUE | FALSE
MARIPOSA REMOTE 0001CB | TRUE | FALSE | TRUE | FALSE
STANISLAUS 17011812 | TRUE | TRUE | TRUE | FALSE
CURTIS 17039240 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 210611132 | TRUE | TRUE | TRUE | FALSE
PARADISE 11032534 | TRUE | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 210135466 | TRUE | FALSE | TRUE | FALSE
SHADY GLEN 110132726 | TRUE | TRUE | TRUE | FALSE
TEJON 11022455 | TRUE | TRUE | TRUE | FALSE
GIRVAN 11029012 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 1103639148 | TRUE | FALSE | TRUE | FALSE
COLUMBIA HILL 110190730 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 210576694 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2102CB | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1102141073 | TRUE | FALSE | TRUE | FALSE
CALPINE 1146CB | TRUE | FALSE | TRUE | FALSE
WEST POINT 11021341 | TRUE | TRUE | TRUE | FALSE
EL DORADO PH 2101CB | TRUE | TRUE | TRUE | FALSE
MARIPOSA 2101CB | TRUE | FALSE | TRUE | FALSE
KESWICK 11011588 | TRUE | FALSE | TRUE | FALSE
BALCH NO 1 1101406582 | TRUE | FALSE | TRUE | FALSE
ELK CREEK 11012032 | TRUE | FALSE | TRUE | FALSE
WILDWOOD 11011454 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2105658898 | TRUE | TRUE | TRUE | FALSE
FRENCH GULCH 11011464 | TRUE | FALSE | TRUE | FALSE
SHADY GLEN 110248894 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2105900104 | TRUE | TRUE | TRUE | FALSE
ANTLER 11011520 | TRUE | TRUE | TRUE | FALSE
MIWUK 170111800 | TRUE | FALSE | TRUE | FALSE
SHADY GLEN 11022232 | TRUE | TRUE | TRUE | FALSE
ANTLER 1101CB | TRUE | TRUE | TRUE | FALSE
STANISLAUS 1701CB | TRUE | TRUE | TRUE | FALSE
PLACERVILLE 210692012 | TRUE | FALSE | TRUE | FALSE
FORESTHILL 11022106 | TRUE | TRUE | TRUE | FALSE
STANISLAUS 170237278 | TRUE | TRUE | TRUE | FALSE
MIDDLETOWN 1101433160 | TRUE | TRUE | TRUE | FALSE
CLAYTON 2212614950 | TRUE | TRUE | TRUE | FALSE
SILVERADO 210478268 | TRUE | TRUE | TRUE | FALSE
MIDDLETOWN 1101548 | TRUE | TRUE | TRUE | FALSE
DRUM 1101CB | TRUE | FALSE | TRUE | FALSE
PIT NO 5 1101CB | TRUE | FALSE | TRUE | FALSE
CALISTOGA 110143924 | TRUE | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 2101CB | TRUE | TRUE | TRUE | FALSE
WEST POINT 11014706 | TRUE | TRUE | TRUE | FALSE
BIG BEND 1101180398 | TRUE | FALSE | TRUE | FALSE
WILDWOOD 110198896 | TRUE | FALSE | TRUE | FALSE
WEST POINT 110277204 | TRUE | FALSE | TRUE | FALSE
WILDWOOD 1101384582 | TRUE | FALSE | TRUE | FALSE
COLUMBIA HILL 110135424 | TRUE | FALSE | TRUE | FALSE
SO. CAL. EDISON #3 1101CB | TRUE | FALSE | TRUE | FALSE
FORESTHILL 110150486 | TRUE | TRUE | TRUE | FALSE
CLAYTON 2212681608 | TRUE | TRUE | TRUE | FALSE
PIKE CITY 1101CB | TRUE | TRUE | TRUE | FALSE
SILVERADO 2105990552 | TRUE | FALSE | TRUE | FALSE
ELECTRA 1101L1697 | TRUE | TRUE | TRUE | FALSE
KESWICK 110148480 | TRUE | FALSE | TRUE | FALSE
SHADY GLEN 11012768 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 2102542272 | TRUE | FALSE | TRUE | FALSE
PEORIA 170190090 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 1702815616 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 110413512 | TRUE | TRUE | TRUE | FALSE
BEAR VALLEY 21059570 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 210110240 | TRUE | TRUE | TRUE | FALSE
REDBUD 1101323962 | TRUE | TRUE | TRUE | FALSE
ALLEGHANY 1101VR816 | TRUE | FALSE | TRUE | FALSE
ORO FINO 11022236 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 11011780 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 11026080 | TRUE | TRUE | TRUE | FALSE
APPLE HILL 2102836878 | TRUE | TRUE | TRUE | FALSE
SALT SPRINGS 210297924 | TRUE | TRUE | TRUE | FALSE
CALISTOGA 1101122350 | TRUE | FALSE | TRUE | FALSE
KESWICK 11011590 | TRUE | FALSE | TRUE | FALSE
NARROWS 2104CB | TRUE | FALSE | TRUE | FALSE
MARIPOSA 210110170 | TRUE | TRUE | TRUE | FALSE
COLUMBIA HILL 1101CB | TRUE | FALSE | TRUE | FALSE
PINE GROVE 11023172 | TRUE | FALSE | TRUE | FALSE
ORO FINO 110265932 | TRUE | FALSE | TRUE | FALSE
COLUMBIA HILL 11012212 | TRUE | FALSE | TRUE | FALSE
WEIMAR 11012084 | TRUE | FALSE | TRUE | FALSE
ANTLER 11011612 | TRUE | FALSE | TRUE | FALSE
HIGHLANDS 1103726580 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 21029722 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101932140 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 11013166 | TRUE | TRUE | TRUE | FALSE
PLACERVILLE 111219712 | TRUE | FALSE | TRUE | FALSE
COLUMBIA HILL 1101764 | TRUE | FALSE | TRUE | FALSE
ORO FINO 11022090 | TRUE | FALSE | TRUE | FALSE
TIGER CREEK 0201320746 | TRUE | FALSE | TRUE | FALSE
KONOCTI 1102806668 | TRUE | FALSE | TRUE | FALSE
KESWICK 1101CB | TRUE | FALSE | TRUE | FALSE
WEST POINT 110236676 | TRUE | FALSE | TRUE | FALSE
NOTRE DAME 1104176446 | TRUE | TRUE | TRUE | FALSE
HIGHLANDS 1103287766 | TRUE | FALSE | TRUE | FALSE
KANAKA 1101859138 | TRUE | FALSE | TRUE | FALSE
ORO FINO 1101CB | TRUE | TRUE | TRUE | FALSE
PARADISE 1105829194 | TRUE | TRUE | TRUE | FALSE
MIDDLETOWN 1101959140 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 1102CB | TRUE | FALSE | TRUE | FALSE
PIKE CITY 1102CB | TRUE | FALSE | TRUE | FALSE
HIGHLANDS 1101CB | TRUE | FALSE | TRUE | FALSE
WEST POINT 11024788 | TRUE | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 21012422 | TRUE | FALSE | TRUE | FALSE
WEIMAR 11012058 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 210251792 | TRUE | FALSE | TRUE | FALSE
HARTLEY 11014710 | TRUE | FALSE | TRUE | FALSE
CALPINE 1144CB | TRUE | FALSE | TRUE | FALSE
ALLEGHANY 1101CB | TRUE | FALSE | TRUE | FALSE
TULE POWER HOUSE 1101CB | TRUE | FALSE | TRUE | FALSE
OAKHURST 11015490 | TRUE | FALSE | TRUE | FALSE
NARROWS PH 1151CB | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101439572 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101352182 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 210219542 | TRUE | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 210192474 | TRUE | FALSE | TRUE | FALSE
LOS OSITOS 21033010 | TRUE | TRUE | TRUE | FALSE
FORESTHILL 11011802 | TRUE | TRUE | TRUE | FALSE
SHADY GLEN 1102CB | TRUE | FALSE | TRUE | FALSE
ORO FINO 11022556 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 11014646 | TRUE | TRUE | TRUE | FALSE
OAKHURST 110310723 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 11014786 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101644756 | TRUE | FALSE | TRUE | FALSE
STANISLAUS 17011331 | TRUE | FALSE | TRUE | FALSE
BIG BEND 1102CB | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101720 | TRUE | FALSE | TRUE | FALSE
HARTLEY 1101336932 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 11038412 | TRUE | FALSE | TRUE | FALSE
WILDWOOD 11011576 | TRUE | FALSE | TRUE | FALSE
BONNIE NOOK 1102CB | TRUE | TRUE | TRUE | FALSE
LOS OSITOS 21037014 | TRUE | TRUE | TRUE | FALSE
CORNING 110185152 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 210219562 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 2108CB | TRUE | FALSE | TRUE | FALSE
APPLE HILL 110497086 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 11011419 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2101752630 | TRUE | TRUE | TRUE | FALSE
CLEAR LAKE 1102904 | TRUE | FALSE | TRUE | FALSE
PARADISE 1104954322 | TRUE | TRUE | TRUE | FALSE
TASSAJARA 2112791386 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2104726 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 110213438 | TRUE | TRUE | TRUE | FALSE
BEAR VALLEY 2101CB | TRUE | FALSE | TRUE | FALSE
WEST POINT 11021305 | TRUE | FALSE | TRUE | FALSE
WISHON 1101CB | TRUE | FALSE | TRUE | FALSE
SHADY GLEN 110151696 | TRUE | FALSE | TRUE | FALSE
GIRVAN 11019732 | TRUE | FALSE | TRUE | FALSE
ANTLER 11011376 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101614 | TRUE | TRUE | TRUE | FALSE
KANAKA 1101CB | TRUE | TRUE | TRUE | FALSE
WEST POINT 11024790 | TRUE | FALSE | TRUE | FALSE
WEIMAR 1101CB | TRUE | FALSE | TRUE | FALSE
MOUNTAIN QUARRIES 21011180 | TRUE | FALSE | TRUE | FALSE
MIWUK 17021808 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 11012646 | TRUE | FALSE | TRUE | FALSE
WEST POINT 1101CB | TRUE | TRUE | TRUE | FALSE
TEJON 1102732836 | TRUE | TRUE | TRUE | FALSE
STILLWATER 11021466 | TRUE | FALSE | TRUE | FALSE
BUTTE 1105398234 | TRUE | FALSE | TRUE | FALSE
LUCERNE 1103245134 | TRUE | FALSE | TRUE | FALSE
CLAYTON 2212204416 | TRUE | FALSE | TRUE | FALSE
PIT NO 5 110190846 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 21099372 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 170113412 | TRUE | FALSE | TRUE | FALSE
FRENCH GULCH 11012905 | TRUE | FALSE | TRUE | FALSE
TEMPLETON 2113A10 | TRUE | FALSE | TRUE | FALSE
UKIAH 1113968652 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 2106CB | TRUE | FALSE | TRUE | FALSE
STANISLAUS 170179826 | TRUE | TRUE | TRUE | FALSE
FORESTHILL 1101CB | TRUE | FALSE | TRUE | FALSE
PINE GROVE 110245292 | TRUE | TRUE | TRUE | FALSE
BRUNSWICK 11021010 | TRUE | TRUE | TRUE | FALSE
BALCH NO 1 1101R372 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 21069712 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 210911092 | TRUE | FALSE | TRUE | FALSE
CALPINE 1144960 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 2105293732 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 110194936 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 210935598 | TRUE | TRUE | TRUE | FALSE
MARIPOSA 2101439030 | TRUE | FALSE | TRUE | FALSE
WEST POINT 110272036 | TRUE | FALSE | TRUE | FALSE
BIG BEND 1101CB | TRUE | FALSE | TRUE | FALSE
BANGOR 1101626862 | TRUE | FALSE | TRUE | FALSE
TASSAJARA 21123202 | TRUE | FALSE | TRUE | FALSE
ANTLER 11011378 | TRUE | FALSE | TRUE | FALSE
GRASS VALLEY 11012208 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2101151918 | TRUE | TRUE | TRUE | FALSE
WYANDOTTE 1103640652 | TRUE | TRUE | TRUE | FALSE
ELECTRA 1101CB | TRUE | FALSE | TRUE | FALSE
PUTAH CREEK 110264044 | TRUE | FALSE | TRUE | FALSE
PEORIA 170169124 | TRUE | FALSE | TRUE | FALSE
ALLEGHANY 1101806 | TRUE | FALSE | TRUE | FALSE
PUEBLO 2103678 | TRUE | TRUE | TRUE | FALSE
WEST POINT 110113444 | TRUE | TRUE | TRUE | FALSE
RINCON 11035152 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101128648 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 110165454 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 110147968 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 11011589 | TRUE | FALSE | TRUE | FALSE
FRENCH GULCH 11022902 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 21054170 | TRUE | FALSE | TRUE | FALSE
PUEBLO 2103355186 | TRUE | FALSE | TRUE | FALSE
TEMPLETON 2113A12 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 110651484 | TRUE | TRUE | TRUE | FALSE
BIG BEND 1102884340 | TRUE | TRUE | TRUE | FALSE
WEIMAR 11012764 | TRUE | FALSE | TRUE | FALSE
STANISLAUS 17017144 | TRUE | FALSE | TRUE | FALSE
HIGHLANDS 1103917328 | TRUE | FALSE | TRUE | FALSE
FRENCH GULCH 11011892 | TRUE | FALSE | TRUE | FALSE
WEIMAR 11012740 | TRUE | FALSE | TRUE | FALSE
ORO FINO 110239154 | TRUE | TRUE | TRUE | FALSE
SISQUOC 1102M52 | TRUE | FALSE | TRUE | FALSE
MOUNTAIN QUARRIES 21011184 | TRUE | FALSE | TRUE | FALSE
SWIFT 2110XR332 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 21067522 | TRUE | TRUE | TRUE | FALSE
EL DORADO PH 2102CB | TRUE | TRUE | TRUE | FALSE
MARTELL 110191216 | TRUE | FALSE | TRUE | FALSE
VOLTA 110153118 | TRUE | FALSE | TRUE | FALSE
VOLTA 11011596 | TRUE | TRUE | TRUE | FALSE
DOBBINS 110169722 | TRUE | FALSE | TRUE | FALSE
MIWUK 170193062 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 1103CB | TRUE | FALSE | TRUE | FALSE
SCE VEGAS 1701CB | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 11052130 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 210119612 | TRUE | TRUE | TRUE | FALSE
ELECTRA 110136816 | TRUE | FALSE | TRUE | FALSE
TEMPLETON 2113641367 | TRUE | FALSE | TRUE | FALSE
NOTRE DAME 11042537 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2105247660 | TRUE | FALSE | TRUE | FALSE
WYANDOTTE 1107829470 | TRUE | FALSE | TRUE | FALSE
PEORIA 1701169700 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 1105875388 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 110180930 | TRUE | FALSE | TRUE | FALSE
CURTIS 170390320 | TRUE | FALSE | TRUE | FALSE
KONOCTI 110264664 | TRUE | FALSE | TRUE | FALSE
STELLING 1110396595 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 11015934 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 21021532 | TRUE | FALSE | TRUE | FALSE
PIKE CITY 11011730 | TRUE | TRUE | TRUE | FALSE
PARADISE 1105121988 | TRUE | TRUE | TRUE | FALSE
PINE GROVE 11023168 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 21062224 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 210619552 | TRUE | FALSE | TRUE | FALSE
WEST POINT 1102CB | TRUE | FALSE | TRUE | FALSE
WEST POINT 110234416 | TRUE | FALSE | TRUE | FALSE
ELK CREEK 11012106 | TRUE | FALSE | TRUE | FALSE
UPPER LAKE 110175370 | TRUE | TRUE | TRUE | FALSE
PINE GROVE 11011021 | TRUE | FALSE | TRUE | FALSE
PASO ROBLES 1103N52 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2102594143 | TRUE | FALSE | TRUE | FALSE
JAMESON 110265516 | TRUE | TRUE | TRUE | FALSE
CALISTOGA 1101267806 | TRUE | FALSE | FALSE | TRUE
BRUNSWICK 110651486 | TRUE | TRUE | TRUE | FALSE
PIT NO 5 11011614 | TRUE | FALSE | TRUE | FALSE
SPAULDING 1101CB | TRUE | FALSE | FALSE | FALSE
BIG BEND 1101641808 | TRUE | FALSE | TRUE | FALSE
HIGGINS 1110166282 | TRUE | FALSE | TRUE | FALSE
COVELO 1101516510 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 1101502 | TRUE | FALSE | TRUE | FALSE
FORESTHILL 110137238 | TRUE | TRUE | TRUE | FALSE
AUBERRY 110137536 | TRUE | FALSE | TRUE | FALSE
COVELO 1101536 | TRUE | FALSE | TRUE | FALSE
CURTIS 170411290 | TRUE | FALSE | FALSE | FALSE
PIT NO 3 2101CB | TRUE | TRUE | TRUE | FALSE
UPPER LAKE 1101412 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 1109868678 | TRUE | FALSE | TRUE | FALSE
MIWUK 1701767890 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101256640 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 1101544800 | TRUE | FALSE | TRUE | FALSE
KONOCTI 1102714370 | TRUE | FALSE | TRUE | FALSE
COARSEGOLD 210410110 | TRUE | FALSE | TRUE | FALSE
SALT SPRINGS 210110416 | TRUE | FALSE | TRUE | FALSE
SPRING GAP 1702188426 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 210985766 | TRUE | FALSE | TRUE | FALSE
SANTA YNEZ 1101980192 | TRUE | FALSE | TRUE | FALSE
PUEBLO 2102378860 | TRUE | FALSE | TRUE | FALSE
HIGGINS 11044281 | TRUE | FALSE | TRUE | FALSE
GIRVAN 11011636 | TRUE | FALSE | TRUE | FALSE
HALSEY 1102CB | TRUE | FALSE | TRUE | FALSE
STELLING 1110733294 | TRUE | FALSE | TRUE | FALSE
DOBBINS 11011264 | TRUE | FALSE | TRUE | FALSE
DOBBINS 1101CB | TRUE | FALSE | TRUE | FALSE
GIRVAN 11011330 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2103920793 | TRUE | FALSE | TRUE | FALSE
CALPELLA 1101908688 | TRUE | FALSE | TRUE | FALSE
AUBERRY 1101R324 | TRUE | FALSE | TRUE | FALSE
FRENCH GULCH 11021462 | TRUE | FALSE | FALSE | TRUE
STELLING 111060090 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 210113532 | TRUE | FALSE | TRUE | FALSE
WEST POINT 110112256 | TRUE | FALSE | TRUE | FALSE
UKIAH 1113548420 | TRUE | FALSE | TRUE | FALSE
ARBUCKLE 1101932352 | TRUE | FALSE | TRUE | FALSE
ELECTRA 110161816 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101718 | TRUE | FALSE | TRUE | FALSE
UKIAH 1113691436 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 110152910 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210595394 | TRUE | FALSE | TRUE | FALSE
BUTTE 1105612016 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101666 | TRUE | FALSE | TRUE | FALSE
PARADISE 11042034 | TRUE | TRUE | TRUE | FALSE
MIWUK 170238218 | TRUE | FALSE | TRUE | FALSE
PUEBLO 2102769868 | TRUE | FALSE | TRUE | FALSE
ARBUCKLE 1104669720 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 110193384 | TRUE | FALSE | TRUE | FALSE
ELECTRA 11024756 | TRUE | FALSE | TRUE | FALSE
TEJON 11023751 | TRUE | TRUE | TRUE | FALSE
CUYAMA 1103684566 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 210163464 | TRUE | TRUE | TRUE | FALSE
SAN JOAQUIN #3 1101CB | TRUE | FALSE | FALSE | FALSE
PLACERVILLE 1110953474 | TRUE | FALSE | TRUE | FALSE
RACETRACK 170311270 | TRUE | FALSE | TRUE | FALSE
CLOVERDALE 1102672 | TRUE | FALSE | TRUE | FALSE
REDBUD 1101754544 | TRUE | TRUE | TRUE | FALSE
DIAMOND SPRINGS 11057722 | TRUE | FALSE | TRUE | FALSE
PEORIA 1704877670 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 11062790 | TRUE | FALSE | TRUE | FALSE
STANISLAUS 17021888 | TRUE | TRUE | TRUE | FALSE
MOUNTAIN QUARRIES 21011130 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 210961892 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1102177784 | TRUE | FALSE | TRUE | FALSE
VACAVILLE 11046542 | TRUE | TRUE | TRUE | FALSE
WEST POINT 110293116 | TRUE | FALSE | TRUE | FALSE
RINCON 1103925054 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 1104814656 | TRUE | FALSE | TRUE | FALSE
TEJON 11023760 | TRUE | FALSE | FALSE | FALSE
HIGGINS 110432747 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 110135588 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 1109CB | TRUE | FALSE | TRUE | FALSE
DUNBAR 1102694641 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1102302610 | TRUE | TRUE | TRUE | FALSE
LOYOLA 1102550291 | TRUE | FALSE | TRUE | FALSE
PIT NO 3 21011482 | TRUE | TRUE | TRUE | FALSE
REDBUD 1101CB | TRUE | FALSE | TRUE | FALSE
OAKHURST 11035480 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 21061104 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2105167360 | TRUE | TRUE | TRUE | FALSE
CURTIS 17039210 | TRUE | FALSE | FALSE | FALSE
MARIPOSA 2102440236 | TRUE | TRUE | FALSE | FALSE
MOUNTAIN QUARRIES 21011350 | TRUE | TRUE | TRUE | FALSE
PIT NO 5 11011658 | TRUE | FALSE | TRUE | FALSE
CURTIS 170234426 | TRUE | FALSE | TRUE | FALSE
BUCKS CREEK 1103CB | TRUE | FALSE | TRUE | FALSE
JOLON 11027040 | TRUE | FALSE | TRUE | FALSE
PARADISE 110343008 | TRUE | TRUE | TRUE | FALSE
REDBUD 1102523244 | TRUE | FALSE | TRUE | FALSE
CHALLENGE 11025462 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 210513430 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 11013170 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1101886282 | TRUE | FALSE | TRUE | FALSE
DIAMOND SPRINGS 110676088 | TRUE | FALSE | TRUE | FALSE
PLACERVILLE 210623190 | TRUE | FALSE | TRUE | FALSE
BUTTE 1105235788 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 110137384 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2105337226 | TRUE | FALSE | TRUE | FALSE
LOS GATOS 1106697500 | TRUE | FALSE | TRUE | FALSE
CURTIS 17048140 | TRUE | FALSE | TRUE | FALSE
SILVERADO 21051306 | TRUE | FALSE | TRUE | FALSE
PIT NO 3 21011480 | TRUE | FALSE | TRUE | FALSE
DIAMOND SPRINGS 110656026 | TRUE | FALSE | TRUE | FALSE
PASO ROBLES 1103N02 | TRUE | FALSE | TRUE | FALSE
PUTAH CREEK 110267858 | TRUE | FALSE | TRUE | FALSE
STELLING 11109265 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 11014360 | TRUE | FALSE | TRUE | FALSE
RINCON 1103655192 | TRUE | FALSE | TRUE | FALSE
SWIFT 2110853720 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1101257964 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 11062104 | TRUE | TRUE | TRUE | FALSE
LUCERNE 11034200 | TRUE | FALSE | TRUE | FALSE
KONOCTI 110275382 | TRUE | FALSE | TRUE | FALSE
CALPELLA 1101619542 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 210521160 | TRUE | FALSE | FALSE | FALSE
SYCAMORE CREEK 11112014 | TRUE | TRUE | TRUE | FALSE
SILVERADO 2104722 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 2102186912 | TRUE | FALSE | TRUE | FALSE
MARTELL 110111244 | TRUE | FALSE | TRUE | FALSE
KONOCTI 1102948 | TRUE | FALSE | TRUE | FALSE
COARSEGOLD 210210050 | TRUE | FALSE | TRUE | FALSE
DUNBAR 1101534 | TRUE | TRUE | TRUE | FALSE
BEAR VALLEY 21014160 | TRUE | FALSE | FALSE | FALSE
RACETRACK 1703CB | TRUE | FALSE | FALSE | TRUE
MIDDLETOWN 1103830 | TRUE | TRUE | TRUE | FALSE
ATASCADERO 1103A14 | TRUE | FALSE | TRUE | FALSE
CURTIS 17028000 | TRUE | FALSE | FALSE | FALSE
LOW GAP 1101449990 | TRUE | FALSE | TRUE | FALSE
COALINGA NO 2 11059260 | TRUE | FALSE | TRUE | FALSE
TIDEWATER 210614072 | TRUE | TRUE | TRUE | FALSE
RACETRACK 170310870 | TRUE | FALSE | FALSE | FALSE
DIAMOND SPRINGS 110519910 | TRUE | FALSE | TRUE | FALSE
COVELO 1101112804 | TRUE | FALSE | TRUE | FALSE
CHALLENGE 11015460 | TRUE | FALSE | TRUE | FALSE
OAKHURST 110377384 | TRUE | FALSE | TRUE | FALSE
RINCON 1103474 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210511010 | TRUE | FALSE | TRUE | FALSE
TEMPLETON 2110N30 | TRUE | FALSE | TRUE | FALSE
KERCKHOFF 1101R308 | TRUE | FALSE | FALSE | FALSE
CURTIS 170510590 | TRUE | FALSE | TRUE | FALSE
LOS OSITOS 2102258878 | TRUE | FALSE | TRUE | FALSE
RINCON 1103568 | TRUE | FALSE | TRUE | FALSE
RACETRACK 170455798 | TRUE | FALSE | FALSE | FALSE
LOS COCHES 1101625902 | TRUE | TRUE | TRUE | FALSE
APPLE HILL 21028372 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2102527766 | TRUE | FALSE | TRUE | FALSE
CHALLENGE 1102CB | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1102963232 | TRUE | FALSE | FALSE | TRUE
CURTIS 17039330 | TRUE | FALSE | TRUE | FALSE
DUNLAP 11037170 | TRUE | FALSE | FALSE | FALSE
BRUNSWICK 11062416 | TRUE | FALSE | TRUE | FALSE
POTTER VALLEY P H 1105640888 | TRUE | FALSE | TRUE | FALSE
CLAYTON 2212158138 | TRUE | FALSE | TRUE | FALSE
MOUNTAIN QUARRIES 21011102 | TRUE | FALSE | FALSE | FALSE
GIRVAN 1101323094 | TRUE | FALSE | TRUE | FALSE
MOUNTAIN QUARRIES 21011346 | TRUE | FALSE | TRUE | FALSE
ALHAMBRA 1105295792 | TRUE | FALSE | TRUE | FALSE
LOS GATOS 1107914254 | TRUE | FALSE | TRUE | FALSE
CLARK ROAD 110290548 | TRUE | FALSE | TRUE | FALSE
KONOCTI 1102532 | TRUE | FALSE | TRUE | FALSE
JESSUP 110141356 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1101242919 | TRUE | FALSE | TRUE | FALSE
HALSEY 110239104 | TRUE | FALSE | TRUE | FALSE
DUNLAP 11027050 | TRUE | FALSE | FALSE | FALSE
SILVERADO 210234959 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 210237282 | TRUE | FALSE | FALSE | FALSE
SAN JOAQUIN #3 110110060 | TRUE | FALSE | TRUE | FALSE
HARTLEY 1101698 | TRUE | TRUE | TRUE | FALSE
MARIPOSA 210190180 | TRUE | FALSE | TRUE | FALSE
LAURELES 11116617 | TRUE | FALSE | FALSE | FALSE
HIGGINS 11041374 | TRUE | FALSE | TRUE | FALSE
PARADISE 1104457900 | TRUE | TRUE | TRUE | FALSE
VACAVILLE 110838316 | TRUE | TRUE | TRUE | FALSE
SAN JOAQUIN #3 11035100 | TRUE | FALSE | FALSE | TRUE
KANAKA 110183288 | TRUE | FALSE | FALSE | FALSE
COALINGA NO 1 110878186 | TRUE | FALSE | TRUE | FALSE
SANTA YNEZ 1101Y52 | TRUE | FALSE | TRUE | FALSE
SAN JOAQUIN #3 110210342 | TRUE | FALSE | TRUE | FALSE
PARADISE 11032486 | TRUE | TRUE | TRUE | FALSE
DIAMOND SPRINGS 11062100 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 17011623 | TRUE | FALSE | TRUE | FALSE
DUNBAR 1102528 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210510996 | TRUE | FALSE | TRUE | FALSE
CLEAR LAKE 1101406 | TRUE | FALSE | TRUE | FALSE
PARADISE 1103CB | TRUE | TRUE | TRUE | FALSE
MARIPOSA 21019400 | TRUE | TRUE | TRUE | FALSE
SAN JOAQUIN #2 1103157026 | TRUE | FALSE | FALSE | FALSE
CALAVERAS CEMENT 110111188 | TRUE | FALSE | FALSE | FALSE
DUNLAP 1102CB | TRUE | FALSE | FALSE | FALSE
LOS GATOS 1107CB | TRUE | FALSE | TRUE | FALSE
JOLON 1103CB | TRUE | FALSE | TRUE | FALSE
LAYTONVILLE 11022502 | TRUE | FALSE | TRUE | FALSE
POSO MOUNTAIN 2101CB | TRUE | FALSE | TRUE | FALSE
CORNING 11021622 | TRUE | FALSE | TRUE | FALSE
PEORIA 17051834 | TRUE | FALSE | FALSE | FALSE
KONOCTI 1108950 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 2102241564 | TRUE | FALSE | TRUE | FALSE
LOS OSITOS 21037062 | TRUE | TRUE | TRUE | FALSE
DUNLAP 11037220 | TRUE | FALSE | FALSE | FALSE
GRASS VALLEY 11032110 | TRUE | FALSE | TRUE | FALSE
HOPLAND 1101768 | TRUE | FALSE | TRUE | FALSE
MORGAN HILL 2111123422 | TRUE | FALSE | TRUE | FALSE
GRAYS FLAT 0401CB | TRUE | TRUE | TRUE | FALSE
HOPLAND 11014626 | TRUE | FALSE | TRUE | FALSE
ELECTRA 11026014 | TRUE | FALSE | FALSE | FALSE
BRUNSWICK 11041020 | TRUE | FALSE | FALSE | FALSE
CLARK ROAD 11022068 | TRUE | FALSE | FALSE | FALSE
WYANDOTTE 11031508 | TRUE | TRUE | TRUE | FALSE
GIRVAN 1101CB | TRUE | FALSE | TRUE | FALSE
PASO ROBLES 1104R56 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210510214 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 110235576 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 210110070 | TRUE | TRUE | TRUE | FALSE
LUCERNE 110638632 | TRUE | FALSE | TRUE | FALSE
HIGGINS 1104324510 | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1102769230 | TRUE | FALSE | TRUE | FALSE
DIAMOND SPRINGS 1106930190 | TRUE | FALSE | TRUE | FALSE
RACETRACK 1704CB | TRUE | FALSE | FALSE | FALSE
CLOVERDALE 1102429006 | TRUE | FALSE | TRUE | FALSE
MOUNTAIN QUARRIES 210151584 | TRUE | FALSE | TRUE | FALSE
PIT NO 5 11011618 | TRUE | FALSE | TRUE | FALSE
PUEBLO 2102943820 | TRUE | FALSE | TRUE | FALSE
MARIPOSA 21021960 | TRUE | FALSE | FALSE | FALSE
SHADY GLEN 1101585766 | TRUE | FALSE | TRUE | FALSE
CALPINE 1146400 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210660120 | TRUE | FALSE | TRUE | FALSE
GIRVAN 11021028 | TRUE | FALSE | FALSE | TRUE
CAMP EVERS 210510294 | TRUE | FALSE | TRUE | FALSE
SAN ARDO 1102896438 | TRUE | FALSE | TRUE | FALSE
PINE GROVE 1102269286 | TRUE | FALSE | TRUE | FALSE
PIT NO 7 1101CB | TRUE | FALSE | FALSE | FALSE
BEAR VALLEY 2105454432 | TRUE | FALSE | FALSE | FALSE
TEMPLETON 2111A66 | TRUE | FALSE | TRUE | FALSE
TASSAJARA 2112676362 | TRUE | FALSE | TRUE | FALSE
UKIAH 1114408 | TRUE | FALSE | TRUE | FALSE
UKIAH 1111807988 | TRUE | FALSE | TRUE | FALSE
IGNACIO 1105775176 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2105131568 | TRUE | FALSE | TRUE | FALSE
CURTIS 170384944 | TRUE | FALSE | FALSE | FALSE
PINE GROVE 11021222 | TRUE | TRUE | FALSE | FALSE
SISQUOC 110245261 | TRUE | FALSE | TRUE | FALSE
HIGGINS 11032194 | TRUE | FALSE | TRUE | FALSE
POTTER VALLEY P H 110576498 | TRUE | FALSE | TRUE | FALSE
SHINGLE SPRINGS 2108449638 | TRUE | FALSE | FALSE | FALSE
ALLEGHANY 1101183068 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 1702592404 | TRUE | FALSE | FALSE | FALSE
MARIPOSA 2101309438 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 1101CB | TRUE | FALSE | FALSE | FALSE
SARATOGA 1107LC12 | TRUE | FALSE | TRUE | FALSE
CHOLAME 21025597 | TRUE | FALSE | TRUE | FALSE
AUBERRY 1101R2578 | TRUE | TRUE | FALSE | FALSE
OAKHURST 110310190 | TRUE | FALSE | TRUE | FALSE
KIRKER 2104442850 | TRUE | TRUE | TRUE | FALSE
IGNACIO 11051943 | TRUE | FALSE | TRUE | FALSE
POTTER VALLEY P H 11051904 | TRUE | TRUE | TRUE | FALSE
OAKHURST 1103719490 | TRUE | FALSE | FALSE | FALSE
BIG MEADOWS 21012248 | TRUE | TRUE | TRUE | FALSE
PINE GROVE 110283098 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2103507513 | TRUE | FALSE | TRUE | FALSE
MORGAN HILL 2111919856 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 17027134 | TRUE | FALSE | FALSE | FALSE
AUBERRY 1101R2838 | TRUE | FALSE | FALSE | FALSE
DOBBINS 110191464 | TRUE | FALSE | FALSE | FALSE
HIGHLANDS 11031282 | TRUE | FALSE | TRUE | FALSE
CEDAR CREEK 1101CB | TRUE | FALSE | TRUE | FALSE
CEDAR CREEK 11011664 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 210190550 | TRUE | FALSE | TRUE | FALSE
PUEBLO 1105637242 | TRUE | FALSE | TRUE | FALSE
ORO FINO 11022096 | TRUE | FALSE | FALSE | FALSE
UPPER LAKE 1101CB | TRUE | FALSE | TRUE | FALSE
CALISTOGA 1101843761 | TRUE | FALSE | TRUE | FALSE
DUNLAP 11027360 | TRUE | FALSE | FALSE | FALSE
OAKHURST 1102683678 | TRUE | FALSE | FALSE | FALSE
CLOVERDALE 1102674 | TRUE | FALSE | TRUE | FALSE
DUNLAP 1103CB | TRUE | FALSE | FALSE | FALSE
SILVERADO 2105309298 | TRUE | FALSE | TRUE | FALSE
HARTLEY 1101789752 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 1702307998 | TRUE | FALSE | FALSE | FALSE
ELK CREEK 110137334 | TRUE | FALSE | FALSE | FALSE
PIT NO 3 21011386 | TRUE | FALSE | TRUE | FALSE
CHALLENGE 1101CB | TRUE | FALSE | TRUE | FALSE
CLOVERDALE 1102801904 | TRUE | FALSE | FALSE | FALSE
CAMP EVERS 2105426822 | TRUE | FALSE | TRUE | FALSE
WEIMAR 1102CB | TRUE | FALSE | TRUE | FALSE
SILVERADO 2103403102 | TRUE | FALSE | TRUE | FALSE
SAN JOAQUIN #3 1101673480 | TRUE | FALSE | FALSE | FALSE
CLARKSVILLE 210419772 | TRUE | FALSE | TRUE | FALSE
MILPITAS 110962157 | TRUE | FALSE | TRUE | FALSE
DUNBAR 1103681238 | TRUE | FALSE | TRUE | FALSE
FROGTOWN 17016807 | TRUE | FALSE | TRUE | FALSE
PANOCHE 11034008 | TRUE | FALSE | TRUE | FALSE
CURTIS 170411300 | TRUE | FALSE | FALSE | FALSE
LOS GATOS 1108LB86 | TRUE | FALSE | TRUE | FALSE
OILFIELDS 1103N48 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 1101585 | TRUE | FALSE | FALSE | FALSE
AUBERRY 1101R2839 | TRUE | TRUE | FALSE | FALSE
CORNING 110164090 | TRUE | FALSE | TRUE | FALSE
MONTICELLO 1101130412 | TRUE | FALSE | FALSE | TRUE
ALTO 11243121 | TRUE | FALSE | TRUE | FALSE
OAKHURST 1101636114 | TRUE | FALSE | FALSE | FALSE
SILVERADO 2104708 | TRUE | TRUE | TRUE | FALSE
ALTO 1124430 | TRUE | FALSE | TRUE | FALSE
RED BLUFF 11041302 | TRUE | FALSE | TRUE | FALSE
PARADISE 1104961990 | TRUE | FALSE | TRUE | FALSE
SARATOGA 1105LC14 | TRUE | FALSE | TRUE | FALSE
CLOVERDALE 110247214 | TRUE | FALSE | TRUE | FALSE
EL DORADO PH 21016852 | TRUE | TRUE | TRUE | FALSE
OREGON TRAIL 11031448 | TRUE | FALSE | FALSE | FALSE
STAFFORD 11021048 | TRUE | FALSE | TRUE | FALSE
CAMP EVERS 210595050 | TRUE | FALSE | TRUE | FALSE
SARATOGA 1107LC26 | TRUE | FALSE | TRUE | FALSE
MENLO 11028896 | TRUE | FALSE | TRUE | FALSE
WILLITS 11032500 | TRUE | FALSE | TRUE | FALSE
DUNBAR 110347964 | TRUE | FALSE | TRUE | FALSE
HIGGINS 1103995672 | TRUE | FALSE | TRUE | FALSE
BEAR VALLEY 210110019 | TRUE | FALSE | FALSE | FALSE
SAN LUIS OBISPO 1101V12 | TRUE | FALSE | TRUE | FALSE
PIT NO 1 1101CB | TRUE | FALSE | FALSE | FALSE
PUEBLO 1104580658 | TRUE | FALSE | TRUE | FALSE
LAYTONVILLE 1101518 | TRUE | FALSE | TRUE | FALSE
HICKS 2101XR250 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 11052210 | TRUE | FALSE | TRUE | FALSE
MORGAN HILL 2111XR398 | TRUE | FALSE | TRUE | FALSE
ATASCADERO 1101A02 | TRUE | FALSE | TRUE | FALSE
JESSUP 1102158468 | TRUE | FALSE | TRUE | FALSE
CALAVERAS CEMENT 110111236 | TRUE | FALSE | FALSE | FALSE
CHOLAME 2102867686 | TRUE | FALSE | TRUE | FALSE
OILFIELDS 1103N62 | TRUE | FALSE | TRUE | FALSE
LOS GATOS 110160052 | TRUE | FALSE | TRUE | FALSE
WOODACRE 1102851 | TRUE | FALSE | TRUE | FALSE
OTTER 110263868 | TRUE | FALSE | TRUE | FALSE
SCE REFUGIO 1701CB | TRUE | FALSE | TRUE | FALSE
OAKHURST 110310570 | TRUE | FALSE | FALSE | FALSE
ALLEGHANY 1101804 | TRUE | FALSE | FALSE | FALSE
CURTIS 170247488 | TRUE | FALSE | FALSE | FALSE
OILFIELDS 1103N04 | TRUE | FALSE | FALSE | FALSE
OILFIELDS 1103451760 | TRUE | FALSE | FALSE | FALSE
CAMP EVERS 210533542 | TRUE | FALSE | TRUE | FALSE
ORO FINO 11012022 | TRUE | TRUE | TRUE | FALSE
CURTIS 170210940 | TRUE | FALSE | FALSE | FALSE
SUNOL 1101MR299 | TRUE | FALSE | TRUE | FALSE
VOLTA 1102CB | TRUE | FALSE | TRUE | FALSE
OILFIELDS 11032757 | TRUE | FALSE | FALSE | FALSE
BRUNSWICK 110350070 | TRUE | FALSE | FALSE | TRUE
CURTIS 170349746 | TRUE | FALSE | FALSE | FALSE
HIGGINS 11041006 | TRUE | FALSE | TRUE | FALSE
JARVIS 1111907698 | TRUE | FALSE | TRUE | FALSE
SWIFT 2110XR254 | TRUE | FALSE | TRUE | FALSE
DUNBAR 110379086 | TRUE | FALSE | TRUE | FALSE
APPLE HILL 210297982 | TRUE | FALSE | FALSE | FALSE
ATASCADERO 1101A50 | TRUE | FALSE | TRUE | FALSE
WYANDOTTE 11071510 | TRUE | FALSE | FALSE | FALSE
DUNLAP 110239190 | TRUE | FALSE | FALSE | FALSE
CHOLAME 2102796386 | TRUE | FALSE | TRUE | FALSE
MIDDLETOWN 1101481876 | TRUE | FALSE | TRUE | FALSE
FULTON 1107145720 | TRUE | FALSE | TRUE | FALSE
KING CITY 11037038 | TRUE | FALSE | TRUE | FALSE
CURTIS 170539256 | TRUE | FALSE | FALSE | FALSE
AUBERRY 1101233716 | TRUE | FALSE | FALSE | TRUE
CALPELLA 1101542 | TRUE | FALSE | TRUE | FALSE
REDBUD 1101708166 | TRUE | TRUE | TRUE | FALSE
ALTO 1124432 | TRUE | FALSE | TRUE | FALSE
WEST POINT 1101L1969 | TRUE | FALSE | TRUE | FALSE
CLOVERDALE 1101964556 | TRUE | FALSE | TRUE | FALSE
SILVERADO 2102808 | TRUE | FALSE | FALSE | FALSE
FROGTOWN 170232556 | TRUE | FALSE | TRUE | FALSE
OAKHURST 1102333062 | TRUE | FALSE | TRUE | FALSE
COVELO 1101664688 | TRUE | FALSE | TRUE | FALSE
JESSUP 11012839 | TRUE | FALSE | FALSE | FALSE
BRUNSWICK 1103173934 | TRUE | FALSE | FALSE | TRUE
LOS GATOS 1106LA42 | TRUE | FALSE | TRUE | FALSE
NARROWS 210248484 | TRUE | FALSE | FALSE | FALSE
HIGHLANDS 1103520 | TRUE | FALSE | FALSE | FALSE
AUBERRY 1101R2845 | TRUE | FALSE | FALSE | TRUE
WILDWOOD 110185112 | TRUE | FALSE | FALSE | FALSE
CORNING 110253184 | TRUE | TRUE | FALSE | FALSE
CLAYTON 2212334476 | TRUE | FALSE | FALSE | FALSE
CLARK ROAD 11022582 | TRUE | FALSE | TRUE | FALSE
LOS GATOS 1106LA46 | TRUE | FALSE | TRUE | FALSE
HIGHLANDS 1102CB | TRUE | FALSE | FALSE | FALSE
CLOVERDALE 110184088 | TRUE | FALSE | TRUE | FALSE
SARATOGA 1106340986 | TRUE | FALSE | TRUE | FALSE
OAKHURST 1103CB | TRUE | FALSE | FALSE | FALSE
SALT SPRINGS 21011216 | TRUE | FALSE | FALSE | FALSE
ATASCADERO 1103492068 | TRUE | FALSE | FALSE | FALSE
VOLTA 11011516 | TRUE | TRUE | FALSE | FALSE
LOS GATOS 1106LA64 | TRUE | FALSE | TRUE | FALSE
BIG BASIN 1101391980 | TRUE | FALSE | TRUE | FALSE
ALTO 11243745 | TRUE | FALSE | TRUE | FALSE
BRUNSWICK 110532536 | TRUE | FALSE | TRUE | FALSE
MENLO 11028952 | TRUE | FALSE | TRUE | FALSE
DIAMOND SPRINGS 1106176130 | TRUE | FALSE | TRUE | FALSE
CLARK ROAD 11022070 | TRUE | TRUE | FALSE | FALSE
PUTAH CREEK 11028352 | TRUE | FALSE | TRUE | FALSE
MIWUK 17029270 | TRUE | FALSE | FALSE | FALSE
MARIPOSA 21029590 | TRUE | FALSE | FALSE | FALSE
HIGGINS 110332120 | TRUE | FALSE | FALSE | FALSE
HOPLAND 110194006 | TRUE | FALSE | TRUE | FALSE
LAURELES 1111432 | TRUE | FALSE | FALSE | FALSE
BRUNSWICK 11052140 | TRUE | FALSE | TRUE | FALSE
NARROWS 21022220 | TRUE | FALSE | FALSE | FALSE
CLOVERDALE 1102172096 | TRUE | FALSE | TRUE | FALSE