## All New & Modified Tables
The table below provides a list of new or revised tables in the WMP as a result of the changes in the Revision Notice and the Supplemental Revision Notice.
If a table is added to the Base WMP, "NEW" is indicated in the corresponding filing. If a table is modified, "MOD" is indicated. If the table in the Revision Notice has been removed as a result of the supplemental filing, "REMOVED" is indicated.
NEW OR REVISED TABLES | NEW OR MODIFIED FOR RNR_R0 Submission | NEW OR MODIFIED FOR SRNR_R1 Submission
TABLE 8-21 (REVISED) | MOD | MOD
TABLE 8-22 (REVISED) | MOD | MOD
TABLE 8-23 (REVISED) | MOD | MOD
TABLE 8-33 (REVISED) | MOD | MOD
TABLE 8-34 (REVISED) | MOD | MOD
TABLE 8-53 (REVISED) | MOD | MOD
TABLE 8-54 (REVISED) | MOD | MOD
TABLE 9-3 (REVISED) | MOD | MOD
TABLE 9-4 (REVISED) | MOD | MOD
TABLE 8-7-1 (REVISED) | MOD | MOD
TABLE RN-PG&E-23-02-1 | NEW | MOD
TABLE 8-18-1 (REVISED) | MOD | MOD
TABLE RN-PG&E-23-02-2 | NEW | MOD
TABLE RN-PG&E-23-03-1 | NEW
TABLE RN-PG&E-23-03-2 | NEW
TABLE RN-PG&E-23-04-1 | NEW
TABLE RN-PG&E-23-04-2 | NEW | MOD
TABLE RN-PG&E-23-04-3 | NEW
TABLE RN-PG&E-23-04-4 | NEW
TABLE RN-PG&E-23-04-5 | NEW
TABLE RN-PG&E-23-04-6 | NEW
TABLE RN-PG&E-23-04-7 | NEW
TABLE PG&E-8.1.7-2 (REVISED) | MOD
TABLE RN-PG&E-23-04-8 | NEW
TABLE RN-PG&E-23-05-1 | NEW | MOD
TABLE RN-PG&E-23-05-2 | NEW
TABLE RN-PG&E-23-05-3 | NEW
TABLE RN-PG&E-23-06-1 | NEW | REMOVED
TABLE RN-PG&E-23-06-2 | NEW | REMOVED
TABLE RN-PG&E-23-07-1 | NEW | MOD
TABLE RN-PG&E-23-07-2 | NEW | MOD
TABLE RN-PG&E-23-07-3 | NEW
TABLE RN-PG&E-23-07-4 | NEW
TABLE RN-PG&E-23-07-5 | NEW | MOD
TABLE 7-3-1 (REVISED) | MOD | MOD
TABLE 7-3-2 (REVISED) | MOD | MOD
TABLE 8-1 (REVISED) | MOD | MOD
TABLE 8-2 (REVISED) | MOD | MOD
TABLE 8-3 (REVISED) | MOD | MOD
TABLE 8-12 (REVISED) | MOD | MOD
TABLE 8-13 (REVISED) | MOD | MOD
TABLE 8-14 (REVISED) | MOD | MOD
TABLE 8-15 (REVISED) | MOD | MOD
TABLE 8-17 (REVISED) | MOD | MOD
TABLE PG&E-E-1 (REVISED) | MOD | MOD
TABLE PG&E-G-1 (REVISED) | MOD | MOD
TABLE PG&E-H-1 (REVISED) | MOD | MOD
TABLE 8-7-2 (REVISED) |  | MOD
TABLE 8-18-2 (REVISED) |  | MOD
TABLE SRN-PG&E-23-04-1 |  | NEW
TABLE SRN-PG&E-23-05-2 |  | NEW
Table SRN-PG&E-23-05-4 |  | NEW
TABLE SRN-PG&E-23-07-4 |  | NEW

## TABLE SRN-PG&E-23-04-1
TABLE SRN‑PG&E‑23‑04‑1:
COMPARISON OF TARGETED RISK REDUCTION FOR BUNDLING PLAN
Risk Reduction Category | 2023‑2025 WMP R1 Target(c) | 2023‑2025 WMP R2 Target (Revision Notice) | 2023‑2024 Workplan Current Estimate
2023 – 2024 Backlog Tags(a)(b) | 102.7 risk points | 102.7 risk points | ~130 risk points
_______________ (a) Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations. (b) Risk points represented in the table are the cumulative risk points, target and estimate, for the years 2023 and 2024 in the Wildfire Distribution Risk Model version 3 (WDRM v3) (c) Note: The 102.7 risk points outlined in the 2023‑2025 R1 WMP Target directly aligns with the risk point reduction approved in the 2022 WMP Revision Notice.

## TABLE SRN-PG&E-23-05-2
TABLE SRN‑PG&E‑23‑05‑2:
COMPARING A 10,000 MILE PORTFOLIO SELECTED BASED ON RISK AND A PORTFOLIO INCORPORATING FEASIBILITY
Portfolio Selection Method | Overlapping miles* | Miles exclusively based on this method | Total miles and risk reduction
Feasibility‑Adjusted (WFE) | 8,894 underground miles (~90% overlap) | 1,230 underground miles | 10,124 underground miles
76% risk reduction
Pure Risk‑Ranked (WDRM only) |  | 1,201 underground miles | 10,095 underground miles
77% risk reduction

## TABLE SRN-PG&E-23-05-4
TABLE SRN‑PG&E‑23‑05‑4:
RESULTS OF ALTERNATIVE MITIGATION ANALYSIS
2023‑2024 UNDERGROUNDING PROJECTS SELECTED USING WDRM V3
| 2023 |  |  | 2024
| Total | Underground | Overhead Harden | Total | Underground | Overhead Harden
Projects | 23 | 23 | 0 | 76 | 73 | 3
Miles | 39.71 | 39.71 | 0 | 361.88 | 345.29 | 16.59

## TABLE SRN-PG&E-23-07-4
TABLE RN‑PG&E‑23‑07‑4:
TRI RESIDUAL RISK
Line No. | Description | No. of Units(a),(b) | MAVF Risk Points | Percent of Vegetation Risk
1 | All Removal Trees | 384930 | 686 | 7%
_______________ (a) This figure is as of February 2023. It represents the best estimate of the trees marked during the EVM Program that may remain in the field. (b) This estimate will continue to be refined each year as the trees are visited to check if the trees have been removed by other programs or no longer pose a risk to PG&E facilities.

## TABLE 7-3-1 REVISED
TABLE 7-3-1 (REVISED):
PG&E'S WMP OBJECTIVES
WMP Category | Objective Name | Initiative Tracking ID | Objective Description | 3‑Year/10‑Year Outlook | Completion Date | Location in WMP
Grid Design, Operations and Maintenance | Evaluate Covered Conductor Effectiveness | GH‑02 | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | Within 3 years | 3/29/2024 (2023 data) 3/31/2025 (2024 data) | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | GH‑03 | Evaluate the output of the Phase 1 and Phase 2 covered conductor effectiveness study to: (1) determine the impacts of the study on the maintenance and inspections standards for deployed covered conductor assets; and (2) update TD‑2305M‑JA02 (overhead inspections job aid), as needed. | Within 3 years | 2023-12-31 | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Retainment of Inspectors and Internal Workforce Development | AI‑01 | 1. Develop a plan to increase retention over time for trained and qualified inspectors. 2. Develop a plan to focus on increasing and sustaining a consistent, year‑over‑year internal workforce that builds on existing experience and mentors new employees for asset inspections. | Within 3 years | 2025-12-31 | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Develop Distribution Aerial Inspections program | AI‑03 | Evaluate the continued use of aerial inspections for distribution overhead equipment. | Within 3 years | 2023-12-31 | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Filling Asset Inventory Data Gaps | AI‑11 | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. | Within 3 years | 2025-12-31 | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Updates on EPSS Reliability Study | GM‑07 | Provide annually an updated EPSS reliability impact study per ACI PG&E‑22‑32 | Within 3 years | 2/15/2024 (For 2023 data) 2/15/2025 (For 2024 data) 2/15/2026 (For 2025 data) | Section 8.1.1.1 Objectives, pp. 369 to 374
Grid Design, Operations and Maintenance | Eliminate HFTD/HFRA distribution backlog | GM‑08 | Eliminate PG&E’s HFTD/HFRA EC notifications distribution backlog* by 2029 and have all HFTD/HFRA EC notifications in compliance with GO 95 Rule 18 barring External Factors. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations. | Within 3 years | 2026-02-15 | Section 8.1.1.1 Objectives, pp. 369 to 374
Vegetation Management and Inspection | Constraint Resolution Procedural Guideline | VM‑09 | 1. Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). PG&E will consider creating a “right tree‑right place” program, as part of the centralize Constraints Resolution process. 2. For each major constraint category build a process for addressing each constraint type, implement the new process, and create metrics to track each constraint type. Reporting will track total constraints by type and the time it takes to resolve a constraint after it has been identified. | Within 3 years | 1. 12/31/2023 2. 12/31/2025 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | Inspection in HFTD and HFRA supporting key vegetation management initiatives | VM‑10 | Continue multiple inspection activities supporting key vegetation management initiatives | Within 10 years | 2032-12-31 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | VM‑11 | Enhance and refine Focus Tree Inspection ‑ Areas of Concern (AOC) development criteria and application of the AOCs to vegetation management programs | Within 10 years | 2032-12-31 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | Evaluate emerging technologies | VM‑12 | Evaluate emerging technologies to enhance focus of and streamline execution of vegetation management inspections | Within 10 years | 2032-12-31 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | VM‑19 | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | Within 3 years | 2024-01-31 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | Record Keeping Enhancement (VMOM, TRI) | VM‑20 | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) ‑ VMPI2 ‑ and Tree Removal Inventory (TRI) ‑ Field Maps ‑ program to include capability to capture factors for prescribing trees for removal | Within 3 years | 2024-11-15 | Section 8.2.1.1 Objectives, pp. 596 to 603
Vegetation Management and Inspection | FTI Record Keeping Enhancement | VM‑21 | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form | Within 3 years | 2024-03-31 | Section 8.2.1.1 Objectives, pp. 596 to 603
Situational Awareness and Forecasting | AI in Wildfire Cameras | SA‑01 | Enable Artificial Intelligence processing of Wildfire Camera Data to provide automated wildfire notifications in the internal PG&E monitoring tool (Wildfire Incident Viewer). | Within 3 years | 2023-06-30 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | EFD and DFA Reporting | SA‑03 | Develop scalable processes to: (a) analyze alarms and alerts from Early Fault Detection (EFD) and DFA sensors; (b) conduct field investigation and reporting; (c) track identified mitigations to completion; and (d) track effectiveness of issue identification and remediation using EFD/DFA technologies. | Within 3 years | 2023-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | FPI and IPW Modeling – Revision Evaluation | SA‑04 | Evaluate enhancements to the FPI model and the Ignition Probability Weather model. This involves testing new features and types of model configurations that could improve model skill. At present we do not know if model skills can be improved but we will attempt to do so. | Within 3 years | 2023-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | Evaluate FPI and IPW Modeling enhancements in 2023‑2025(a) | SA‑05 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. At present we do not know if model skill can be improved but we will attempt to do so in 2023. If model skill can be improved and is approved, we plan to operationalize the new models in 2024 and continue operations in 2025. We do not know if any new models developed will be approved for operations by PG&E’s Wildfire risk governance committee. | Within 3 years | 2025-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | Evaluate FPI and IPW Modeling enhancements in 2026 – 2032 | SA‑06 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in the 2026‑2033 period. This work involves testing new features and types of model configurations that could improve model forecasting ability. | Within 10 years | 2032-12-31 | SSection 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | Monitor and evaluate the Cameras AI system’s performance | SA‑07 | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. | Within 3 years | 2025-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | Evaluate the Cameras AI system functionalities and technologies | SA‑08 | In partnership with Digital Path and its collaboration with other camera sponsors, evaluate the AI system for opportunities to test new functionalities and newly developed break‑through technologies. We will also explore new best practices to ensure the ongoing effectiveness of the system. | Within 10 years | 2032-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | EFD and DFA Reporting | SA‑09 | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. | Within 3 years | 2025-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Situational Awareness and Forecasting | Evaluate the use and effectiveness of real‑time monitoring tools | SA‑12 | Each year, we will evaluate and discuss our situational awareness tools internally, as well as with other IOUs. These evaluative discussions will include reviewing observations of our various situational awareness tools and identifying potential areas for improvement. We will also discuss best practices and lessons learned. These discussions will help inform potential changes to what situational awareness tools we incorporate, as well as how they are incorporated. This may include equipment upgrades, new tech integrations, model improvements, and enhanced data initiatives. | Within 10 years | 2032-12-31 | Section 8.3.1.1 Objectives, pp. 715 to 721
Emergency Preparedness Plan | Complete PSPS and Wildfire Tabletop and Functional Exercises | EP‑01 | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP). | Within 3 years | 2025-12-31 | Section 8.4.1.1 Objectives, pp. 776 to 782
Emergency Preparedness Plan | Maintain all hazards planning and preparedness program in 2023‑2025 | EP‑02 | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. | Within 3 years | 2025-12-31 | SSection 8.4.1.1 Objectives, pp. 776 to 782
Emergency Preparedness Plan | Expand all hazards planning to include additional threats and scenarios in 2023‑2025 | EP‑04 | Expand the All Hazards Planning and Preparedness Program to include additional threats and scenarios. | Within 3 years | 2025-12-31 | Section 8.4.1.1 Objectives, pp. 776 to 782
Emergency Preparedness Plan | Common Operating Picture Technology | EP‑07 | Design and deploy a common operating picture.(b) | Within 10 years | 2032-12-31 | Section 8.4.1.1 Objectives, pp. 776 to 782
Emergency Preparedness Plan | Threats and Hazards Identification and Risk Assessment (THIRA) updates executive briefings. | EP‑08 | Execute a Threats and Hazards Identification and Risk Assessment (THIRA)(c) update every three years to address changes in hazard landscape. Use information from THIRA to inform changes to the CERP and hazard annexes. | Within 10 years | 2032-12-31 | Section 8.4.1.1 Objectives, pp. 776 to 782
Emergency Preparedness Plan | County Execute Briefings | EP‑09 | Hold briefings with 47 counties within PG&E’s service territory after every THIRA update to support integrated planning discussions. | Within 10 years | 2032-12-31 | Section 8.4.1.1 Objectives, pp. 776 to 782
Community Outreach and Engagement | Community Outreach and Engagement – Meetings | CO‑01 | For 2023‑2025, PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | Within 3 years | 9/30/2023 9/30/2024 9/30/2025 | Section 8.5.1.1 Objectives, pp. 872 to 876
Community Outreach and Engagement | Community Engagement – Outreach to HFRA Infrastructure Customers | CO‑04 | PG&E will perform outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the CWSP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. | Within 10 years | 2032-12-31 | Section 8.5.1.1 Objectives, pp. 872 to 876
Community Outreach and Engagement | Community Engagement – Outage Preparedness Campaign | CO‑05 | PG&E will also conduct at least one direct‑to‑customer outage preparedness campaign annually via email and/or direct mail targeting residential customers in the PSPS more likely or EPSS program scope. | Within 10 years | 2032-12-31 | Section 8.5.1.1 Objectives, pp. 872 to 876
PSPS | Evaluate enhancements for the PSPS Transmission guidance | PS‑01 | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. | Within 3 years | 2025-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | PS‑02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. | Within 3 years | 2025-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Evaluate the transition of the Portable Battery Program to permanent battery solutions. | PS‑05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions for PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self‑identified vulnerable populations. | Within 10 years | 2032-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Evaluate emerging technologies to reduce PSPS customer impact. | PS‑08 | Evaluate emerging technologies for transmission and distribution that may further reduce scale, scope, or frequency of PSPS. | Within 10 years | 2032-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Reduce PSPS size, duration, or frequency as part of 10,000‑mile undergrounding program | PS‑09 | Reduce PSPS size, duration, or frequency over the next ten years as part of our 10,000‑mile undergrounding program. | Within 10 years | 2032-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Continue sharing PSPS lessons learned | PS‑10 | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. | Within 3 years | 2025-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
PSPS | Pilot using drones for PSPS restoration | PS‑11 | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | Within 3 years | 2025-12-31 | Section 9.1.3 Objectives, pp. 911 to 914
_______________
(a) In response to the Revision Notice, PG&E has modified SA‑05 to include “EPSS” in the objective and method of verification descriptions. Details on this change are included in the response to Critical Issue RN‑PG&E‑23‑08.
(b) A common operation picture (COP) is a continuously updated overview of an incident compiled throughout an incident's life cycle from data shared between integrated communication, information management, and intelligence and information sharing systems. The goal of a COP is real‑time situational awareness across all levels of incident management and across jurisdictions. https://www.dhs.gov/publication/common‑operating‑picture‑emergency‑responders.
(c) According to FEMA https://www.fema.gov/emergency‑managers/national‑preparedness/goal/risk‑capability‑assessment#:~:text=The%20Threat%20and%20Hazard%20Identification,hazards%20can%20affect%20our%20community%3F. The THIRA is a three‑step risk assessment process that helps communities understand their risks and what they need to do to address those risks.

## TABLE 7-3-2 REVISED
TABLE 7-3-2 (REVISED):
PG&E'S WMP TARGETS
Category | Target Name | Initiative Activity Tracking ID | 2023 Target & Unit | 2024 Target & Unit | 2025 Target & Unit | Location in WMP (Section)
Grid Design, operations and maintenance | System Hardening – Distribution | GH‑01 | Complete 420 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas, except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | Complete 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas, except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | Complete 580 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | Section 8.1.1.2 Targets, pp. 375 to 391
| 10K Undergrounding | GH‑04 | Complete 350 circuit miles of undergrounding work. The 350‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | Complete 450 circuit miles of undergrounding work. The 450‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | Complete 550 circuit miles of undergrounding work. The 550‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | Section 8.1.1.2 Targets, pp. 375 to 391
| System Hardening – Transmission | GH‑05 | Remove or replace 43 circuit miles of transmission conductor on lines. | N/A | Remove or replace 5 circuit miles of transmission conductor. | Section 8.1.1.2 Targets, pp. 375 to 391
| System Hardening – Transmission Shunt Splices | GH‑06 | Install shunt splice(s) on 20 transmission lines. | Install shunt splice(s) on 22 transmission lines. | Install shunt splice(s) on 25 transmission lines. | Section 8.1.1.2 Targets, pp. 375 to 391
| Distribution Protective Devices | GH‑07 | Install and SCADA commission 75 new SCADA protective devices (Line Recloser, Fuse Saver, or Interrupter). | N/A | N/A | Section 8.1.1.2 Targets, pp. 375 to 391
| Surge Arrestor – Removals | GH‑08 | Remove 663 non‑exempt surge arrestors (based on the known population as of 01/12/2023) where known grounding issues exist. If no non‑exempt surge arrestor is identified at a location during pre‑field work, the unit will be resolved, and the notification will be canceled. Canceled notifications will count towards this target. | N/A | N/A | Section 8.1.1.2 Targets, pp. 375 to 391
| Distribution Line MSO – Replacements | GH‑09 | Replace or remove 20 MSOs (from the 47 identified as of January 26, 2023). | Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. | N/A | Section 8.1.1.2 Targets, pp. 375 to 391
| Non‑Exempt Expulsion Fuse – Removal | GH‑10 | Remove non‑exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. | Remove non‑exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. | Remove non‑exempt expulsion fuses/ cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. | Section 8.1.1.2 Targets, pp. 375 to 391
| Detailed Inspection Transmission – Ground | AI‑02 | Complete detailed ground inspections on 27,000 transmission structures in PG&E’s asset registry as of January 1, 2023. | Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | Complete detailed ground inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | Section 8.1.1.2 Targets, pp. 375 to 391
| Detailed Inspection Transmission – Aerial | AI‑04 | Complete detailed aerial inspections on 24,000 transmission structures in PG&E’s asset registry as of January 1, 2023. | Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | Section 8.1.1.2 Targets, pp. 375 to 391
| Detailed Inspection Transmission – Climbing | AI‑05 | Complete detailed climbing inspections of 1,700 transmission structures in PG&E’s asset registry as of January 1, 2023. | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | Section 8.1.1.2 Targets, pp. 375 to 391
| Perform transmission IR inspections | AI‑06 | Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. | Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | Infrared patrols will be performed on 3,500 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | Section 8.1.1.2 Targets, pp. 375 to 391
| Detailed Ground Inspections – Distribution | AI‑07 | Complete detailed ground inspections on 234,648 distribution poles, which were identified in PG&E’s asset registry as of December 27, 2022. As part of the target number above, detailed ground inspections will be completed on a 42,470 pole subset of distribution poles in Severe, Extreme, or High plat maps by July 31, 2023, which were identified in PG&E’s asset registry as of December 27, 2022. Similarly, detailed ground inspections will be completed on a 30,062 pole subset of distribution poles in Medium plat maps by September 30, 2023, which were identified in PG&E’s asset registry as of December 27, 2022. Lastly, detailed ground inspections will be completed on a 162,116 pole subset of distribution poles in Low plat maps by December 31, 2023, which were identified in PG&E’s asset registry as of December 27, 2022. | Complete detailed inspections on approximately 233,501 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update.. | Section 8.1.1.2 Targets, pp. 375 to 391
| Supplemental Inspections – Substation Distribution | AI‑08 | Complete supplemental inspections on 52 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 76 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 78 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.1.1.2 Targets, pp. 375 to 391
| Supplemental Inspections – Substation Transmission | AI‑09 | Complete supplemental inspections on 34 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 36 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 41 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.1.1.2 Targets, pp. 375 to 391
| Supplemental Inspections – Hydroelectric Substations and Powerhouses | AI‑10 | Complete supplemental inspections on 41 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.1.1.2 Targets, pp. 375 to 391
| Asset Inspections – Quality Assurance | GM‑01 | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 92% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 82% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 94% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 95% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Section 8.1.1.2 Targets, pp. 375 to 391
| HFTD/HFRA Open Tag Reduction – Transmission | GM‑02 | PG&E will eliminate the known 16,831 HFTD and HFRA transmission Ignition Risk tags (tags found prior to January 1, 2023, with required end dates in 2023 or earlier). | N/A | N/A | Section 8.1.1.2 Targets, pp. 375 to 391
| HFTD/HFRA Open Tag Reduction – Distribution Backlog | GM‑03 | Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog(a) ignition risk EC notifications. This work will reduce 48 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations from 151.1 (risk units as of January 1, 2023) by 72.5 (48 percent) risk units. | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 68 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 2‑year period (2023 to 2024), from 151.1 risk units—as of January 1, 2023—by 102.7 risk units (68 percent). | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications. Of these EC notifications, we expect to close out 55,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 77 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 3‑year period (2023 to 2025), from 151.1 risk units—as of January 1, 2023—by 116.3 risk units (77 percent). | Section 8.1.1.2 Targets, pp. 375 to 391
| EPSS – Down Conductor Detection (DCD) | GM‑06 | Make capable for DCD 500 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | Make capable for DCD 400 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | Section 8.1.1.2 Targets, pp. 375 to 391
| Asset Inspection – Quality Control | GM‑09 | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 20,000 audit locations*; 90% pass rate System Inspection Transmission – HFTD (Field): 1,800 audit locations*; 90% pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 80% pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 80% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 15,000 audit locations*; 92% pass rate System Inspection Transmission – HFTD (Field): 1,300 audit locations*; 92% pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 88% pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 88% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 16,000 audit locations*; 95% pass rate System Inspection Transmission – HFTD (Field): 1,450 audit locations*; 95% pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 95% pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Section 8.1.1.2 Targets, pp. 375 to 391
Vegetation Management and Inspection | LiDAR Data Collection – Transmission(b) | VM‑01 | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non‑HTFD Transmission circuit miles. | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non‑HFTD Transmission circuit miles. | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non‑HFTD Transmission circuit miles. | Section 8.2.1.2 Targets, pp. 604 to 614
| Pole Clearing Program | VM‑02 | Inspect, clear, and maintain, where clearing is necessary, 77,503 poles per Vegetation Control Standard TD‑7112S. | 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD‑7112S will be inspected, cleared, and maintained where clearing is necessary. | 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD‑7112S will be inspected, cleared, and maintained where clearing is necessary. | Section 8.2.1.2 Targets, pp. 604 to 614
| Focused Tree Inspection (FTI) | VM‑03 | Complete focus tree inspections of 250 Circuit Miles in defined Areas of Concern (AOC) locations.(c) | Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. | Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. | Section 8.2.1.2 Targets, pp. 604 to 614
| Tree Removal Inventory (TRI) | VM‑04 | Mitigate(d)15,000 trees identified from the legacy EVM program. | Mitigate(d) 20,000 trees identified from the legacy EVM program. | Mitigate(d) 25,000 trees identified from the legacy EVM program. | Section 8.2.1.2 Targets, pp. 604 to 614
| Defensible Space Inspections – Distribution Substation(e) | VM‑05 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 131 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 131 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 131 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.2.1.2 Targets, pp. 604 to 614
| Defensible Space Inspections – Transmission Substation(e) | VM‑06 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 55 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 55 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P 01 at 55 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.2.1.2 Targets, pp. 604 to 614
| Defensible Space Inspections – Hydroelectric Substations and Powerhouses | VM‑07 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P 01 at 61 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P 01 at 61 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P 01 at 61 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | Section 8.2.1.2 Targets, pp. 604 to 614
| Vegetation Management – Quality Assurance | VM‑08 | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,500 audit locations*; 95% pass rate Transmission VM – HFTD: 1,200 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,800 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,675 audit locations*; 95% pass rate Transmission VM – HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,926 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,862 audit locations*; 95% pass rate Transmission VM – HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Section 8.2.1.2 Targets, pp. 604 to 614
| Routine Ground ‑Transmission | VM‑13 | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | Section 8.2.1.2 Targets, pp. 604 to 614
| Second Patrol – Transmission | VM‑14 | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | Section 8.2.1.2 Targets, pp. 604 to 614
| Integrated Vegetation Management – Transmission | VM‑15 | Complete Integrated Vegetation Management and Fee Inspections of 11,194 acres ROW across the Transmission systemwide | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | Section 8.2.1.2 Targets, pp. 604 to 614
| Routine Patrol – Distribution(f) | VM‑16 | Complete Distribution Routine Annual Patrol Inspection of 79,000 overhead circuit miles system wide | Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide | Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide | Section 8.2.1.2 Targets, pp. 604 to 614
| Second Patrol – Distribution(f) | VM‑17 | Complete Distribution Second Patrol Inspection of 43,600 circuit miles that are in the following map layers FHSZ, WUI, SRA, FRA, HFTD, and HFRA locations. | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | Section 8.2.1.2 Targets, pp. 604 to 614
| VM for Operational Mitigations (VMOM) | VM‑18 | N/A | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry‑over work and prescriptions resulting from pro‑active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry‑over work and prescriptions resulting from pro‑active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | Section 8.2.1.2 Targets, pp. 604 to 614
| Vegetation Management ‑ Quality Control | VM‑22 | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 75,000 audit locations*; 80% pass rate Transmission VM – HFTD: 12,500 audit locations*; 88% pass rate Vegetation Control Pole Clearing – HFTD: 10,500 audit locations*; 80% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 80,000 audit locations*; 88% pass rate Transmission VM – HFTD: 13,500 audit locations*; 92% pass rate Vegetation Control Pole Clearing – HFTD: 11,500 audit locations*; 88% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 85,000 audit locations*; 95% pass rate Transmission VM – HFTD: 14,500 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 12,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Section 8.2.1.2 Targets, pp. 604 to 614
Situational Awareness and Forecasting | Line Sensor – Installations | SA‑02 | Install Line Sensor devices on 40 circuits. | Install Line Sensor devices on 40 circuits. | Install Line Sensor devices on 40 circuits. | Section 8.3.1.2 Targets, pp. 722 to 724
| Distribution Fault Anticipation (DFA) – Installations | SA‑10 | Install 5 Distribution Fault Anticipation (DFA) sensors on circuits.(g) One sensor will be installed per circuit at the initiating substation. | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. | Section 8.3.1.2 Targets, pp. 722 to 724
| Early Fault Detection (EFD) ‑ Installations | SA‑11 | Install Early Fault Detection (EFD) sensors on 2 circuits.(h) | Install Early Fault Detection (EFD) sensors on 2 circuits. | Install Early Fault Detection (EFD) sensors on 4 circuits. | Section 8.3.1.2 Targets, pp. 722 to 724
Emergency Preparedness | Annually review, and revise if appropriate, the Company Emergency Response Plan (CERP) and the two wildfire‑related annexes (the Wildfire Annex and the PSPS Annex) | EP‑06 | 3 documents (1 CERP and 2 wildfire‑related annexes) | 3 documents (1 CERP and 2 wildfire‑related annexes) | 3 documents (1 CERP and 2 wildfire‑related annexes) | Section 8.4.1.2 Targets, pp. 783 to 785
Community Outreach and Engagement | Community Engagement – Surveys | CO‑02 | PG&E will complete two PSPS education and outreach surveys. | PG&E will complete two PSPS education and outreach surveys. | PG&E will complete two PSPS education and outreach surveys. | Section 8.5.1.2 Targets, pp.877 to 881
PSPS | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self‑identified vulnerable populations | PS‑06 | Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. | Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. | Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. | Section 9.1.4 Targets, pp. 915 to 917
PSPS | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023‑2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | PS‑07 | 15,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023. | 33,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023‑2024. | 55,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023‑2025. | Section 9.1.4 Targets, pp. 915 to 917 ACI PG&E‑22‑35 pp. 1130 to 1132
_______________
(a) Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations.
(b) VM‑01 LiDAR is flown in late summer and early fall in the prior year to enable ground inspection's next cycle to begin in November that then allows tree work to commence on January 1 of the following year.
(c) See PG&E’s response to Critical Issue RN‑PG&E‑23‑07, Remedy (b) and (c).
(d) We note that for purposes of Target VM‑04, the term “Mitigate” is intended to refer to a tree identified from the legacy EVM program that is either: (1) removed by the TRI program; (2) removed by another PG&E VM program and no longer present; or (3) no longer poses a threat to PG&E facilities because the facilities have been relocated
(e) VM‑05 and VM‑06 Defensible Space inspections begin in late November to enable work mitigation to be completed before fire season begins in the following year.
(f) The Distribution Routine VM – HFTD includes audit locations and associated pass rates for distribution second patrols. The second patrol is now managed as part of the overall Distribution Routine VM program.
(g) A total of 5 DFA sensors were installed in 2023 from 2022 carry‑over workplans. These installs were not counted or credited toward work in 2022.
(h) A total of 2 circuits were instrumented with EFD sensors in 2023 from 2022 carry‑over workplans. These installs were not counted or credited toward work in 2022.

## TABLE 8-1 REVISED
TABLE 8-1 (REVISED):
GRID DESIGN, OPERATIONS, AND MAINTENANCE OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | GH‑02 | GO95, GO165, ACI PG&E 22‑11 | Whitepaper showing the updated covered conductor effectiveness calculation using 2023 outage data. Whitepaper showing the updated covered conductor effectiveness calculation using 2024 outage data. | 3/29/2024 (2023 data) 3/31/2025 (2024 data) | Section 8.1.2.1 Page 396
Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | Evaluate the output of the Phase 1 and Phase 2 covered conductor effectiveness study to: (1) determine the impacts of the study on the maintenance and inspections standards for deployed covered conductor assets; and (2) update TD‑2305M‑JA02 (overhead inspections job aid), as needed. | GH‑03 | GO95, GO165, TD‑2305M‑JA02 | Report outlining the impacts of the methodology and any proposed changes. Updated TD 2305M JA02 document for inspections and maintenance to include references to covered conductor asset inspection and maintenance, as needed | 2023-12-31 | Section 8.1.2.1 Page 396
Retainment of Inspectors and Internal Workforce Development | Develop a plan to increase retention over time for trained and qualified inspectors. Develop a plan to focus on increasing and sustaining a consistent, year‑over‑year internal workforce that builds on existing experience and mentors new employees for asset inspections. | AI‑01 | N/A | Multiyear resource plans. | 2025-12-31 | Section 8.1.9.1 Page 581
Develop Distribution Aerial Inspections program | Evaluate the continued use of aerial inspections for distribution overhead equipment. | AI‑03 | N/A | Report summarizing the results of the 2023 Aerial Inspections. | 2023-12-31 | Section 8.1.3.2.7 Page 488
Filling Asset Inventory Data Gaps | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. | AI‑11 | TD‑9212S – Asset Registry Standard | List of targeted distribution and transmission equipment types. Baseline and actual rate of completeness for the “Installation Date” data element for each targeted distribution and transmission equipment type. | 2025-12-31 | Section 8.1.5 Page 515
Updates on EPSS Reliability Study | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study per Areas for Continued Improvement (ACI) PG&E‑22‑32 | GM‑07 | D‑16‑01‑008 and Revision Notice 22‑12 from 2022 WMP | Annual EPSS Reliability Study | 2/15/2024 for 2023 data 2/15/2025 for 2024 data 2/15/2026 for 2025 data | Section 8.1.8.1.1 Page 561

## TABLE 8-2 REVISED
TABLE 8-2 (REVISED):
GRID DESIGN, OPERATIONS, AND MAINTENANCE OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., Program) | Completion Date | Reference (Section and Page #)
Eliminate HFTD/HFRA distribution backlog | Eliminate PG&E’s HFTD/HFRA EC notifications distribution backlog[1] by 2029 and have all HFTD/HFRA EC notifications in compliance with GO 95 Rule 18. | GM‑08 | GO 95 Rule 18 | Report showing closed/canceled work orders compared against the distribution HFTD/HFRA backlog. | 2029-12-31 | Section 8.1.7.2 p. 531
Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations.

## TABLE 8-3 REVISED
TABLE 8-3 (REVISED):
GRID DESIGN, OPERATIONS, AND MAINTENANCE TARGETS BY YEAR
Target Name | Initiative Activity Tracking ID | Reference Section | 2023 Target & Unit | x% Risk Impact 2023 | 2024 Target & Unit | x% Risk Impact 2024 | 2025 Target & Unit | x% Risk Impact 2025 | Method of Verification
System Hardening – Distribution | GH‑01 | 8.1.2.1 | Complete 420 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | 2% | Complete 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | 4% | Complete 580 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | 5% | For post construction projects, as built job package and Fire Safe Spans Inspection report. For partially completed/ in construction projects, design construction drawing and Fire Safe Spans Inspection report.
10K Undergrounding | GH‑04 | 8.1.2.2 | Complete 350 circuit miles of undergrounding work. The 350‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | 2% | Complete 450 circuit miles of undergrounding work. The 450‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | 3% | Complete 550 circuit miles of undergrounding work. The 550‑circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | 5% | For post construction projects, as built job package and Fire Safe Spans Inspection report. For partially completed/ in construction projects, design construction drawing and Fire Safe Spans Inspection report.
System Hardening – Transmission | GH‑05 | 8.1.2.5.1 | Remove or replace 43 circuit miles of transmission conductor on lines. | <1% | N/A | N/A | Remove or replace 5 circuit miles of transmission conductor. | <1% | As‑built job package.
System Hardening – Transmission Shunt Splices | GH‑06 | 8.1.2.5.1 | Install shunt splice(s) on 20 transmission lines. | <1% | Install shunt splice(s) on 22 transmission lines. | TBD | Install shunt splice(s) on 25 transmission lines. | TBD | As‑built job package
Distribution Protective Devices | GH‑07 | 8.1.2.8.1 | Install and SCADA commission 75 new SCADA protective devices (Line Recloser, Fuse Saver, or Interrupter). | 0% | N/A | 0% | N/A | 0% | As‑built job package or SCADA Release Letters
Surge Arrestor – Removals | GH‑08 | 8.1.2.10.4 | Remove 663 non‑exempt surge arrestors (based on the known population as of 01/12/2023) where known grounding issues exist. If no non‑exempt surge arrestor is identified at a location during pre‑field work, the unit will be resolved, and the notification will be canceled. Canceled notifications will count towards this target. | <1% | N/A | N/A | N/A | N/A | Closed work orders
Distribution Line Motor Switch Operator (MSO) – Replacements | GH‑09 | 8.1.2.10.3 | Replace or remove 20 MSOs (from the 47 identified as of January 26, 2023). | <1% | Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. | <1% | N/A | N/A | As‑built job package or (SCADA) Release Letters
Non‑Exempt Expulsion Fuse – Removal | GH‑10 | 8.1.2.10.5 | Remove non‑exempt expulsion fuses/cutouts from 3,000 fuse locations identified on distribution poles. | <1% | Remove non‑exempt expulsion fuses/cutouts from 3,000 fuse locations identified on distribution poles. | <1% | Remove non‑exempt expulsion fuses/cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. | <1% | Closed work orders
Detailed Inspection Transmission – Ground | AI‑02 | 8.1.3.1.1 | Complete detailed ground inspections on 27,000 transmission structures in PG&E’s asset registry as of January 1, 2023. | 69% (Eyes‑on‑Risk) | Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023‑2025 WMP Process and Evaluation Guidelines. | TBD | Complete detailed ground inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | TBD | Attainment report
Detailed Inspection Transmission – Aerial | AI‑04 | 8.1.3.1.2 | Complete detailed aerial inspections on 24,000 transmission structures in PG&E’s asset registry as of January 1, 2023. | 66% (Eyes‑on‑Risk) | Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023‑2025 WMP Process and Evaluation Guidelines. | TBD | Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | TBD | Attainment report
Detailed Inspection Transmission – Climbing | AI‑05 | 8.1.3.1.3 | Complete detailed climbing inspections of 1,700 transmission structures in PG&E’s asset registry as of January 1, 2023. | <1% (Eyes‑on‑Risk) | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023‑2025 WMP Process and Evaluation Guidelines. | TBD | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | TBD | Attainment report
Perform transmission infrared (IR) inspections | AI‑06 | 8.1.3.1.4 | IR patrols will be performed on 4,000 circuit miles of energized transmission line. | 56% (Eyes‑on‑Risk) | IR patrols will be performed on 4,000 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023‑2025 WMP Process and Evaluation Guidelines. | TBD | IR patrols will be performed on 3,500 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | TBD | Attainment report
Detailed Ground Inspections – Distribution | AI‑07 | 8.1.3.2.1 | Complete detailed ground inspections on 234,648 distribution poles, which were identified in PG&E’s asset registry as of December 27, 2022. As part of the target number above, detailed ground inspections will be completed on a 42,470 pole subset of distribution poles in Severe, Extreme, or High plat maps by July 31, 2023, which were identified in PG&E’s asset registry as of December 27, 2022. Similarly, detailed ground inspections will be completed on a 30,062 pole subset of distribution poles in Medium plat maps by September 30, 2023, which were identified in PG&E’s asset registry as of December 27, 2022 Lastly, detailed ground inspections will be completed on a 162,116 pole subset of distribution poles in Low plat maps by December 31, 2023, which were identified in PG&E’s asset registry as of December 27, 2022.. | 40% (Eyes‑on‑Risk) | Complete detailed inspections on approximately 233,501 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with section 12.3 of the 2023 2025 WMP Process and Evaluation Guidelines. | 47% (Eyes‑on‑Risk) | Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. | 45% (Eyes‑on‑Risk) | Attainment report
Supplemental Inspections – Substation Distribution | AI‑08 | 8.1.3.3.1 | Complete supplemental inspections on 52 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 28% (Eyes‑on‑Risk) | Complete supplemental inspections on 76 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Complete supplemental inspections on 78 distribution substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Pronto report
Supplemental Inspections – Substation Transmission | AI‑09 | 8.1.3.3.1 | Complete supplemental inspections on 34 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 36% (Eyes‑on‑Risk) | Complete supplemental inspections on 36 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Complete supplemental inspections on 41 transmission substations. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Pronto report
Supplemental Inspections – Hydroelectric Substations and Powerhouses | AI‑10 | 8.1.3.3.1 | Complete supplemental inspections on 41 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 35% (Eyes‑on‑Risk) | Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. Co located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | TBD | Pronto report
Asset Inspections ‑ Quality Assurance | GM‑01 | 8.1.6.1 | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 92% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 82% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 94% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 95% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Final reports and field guides for all audits.
HFTD/HFRA Open Tag Reduction – Transmission | GM‑02 | 8.1.7.1 | PG&E will eliminate the known 16,831 HFTD and HFRA transmission Ignition Risk tags (tags found prior to January 1, 2023, with required end dates in 2023 or earlier). | <1% | N/A | TBD | N/A | TBD | Closed work orders
HFTD/HFRA Open Tag Reduction – Distribution Backlog | GM‑03 | 8.1.7.2 | Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog(a) ignition risk EC notifications. This work will reduce 48 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations from 151.1 (risk units as of January 1, 2023) by 72.5 (48 percent) risk units. | 2.4%(b) | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 68 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 2 year period (2023 to 2024), from 151.1 risk units—as of January 1, 2023—by 102.7 risk units (68 percent). | <1%(b) | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications. Of these EC notifications, we expect to close out 55,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 77 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 3 year period (2023 to 2025), from 151.1 risk units—as of January 1, 2023—by 116.3 risk units (77 percent).. | <1%(b) | Closed work orders
EPSS – Down Conductor Detection (DCD) | GM‑06 | 8.1.2.10.1 | Make capable for DCD 500 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | <2% | Make capable for DCD 400 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | <1% | Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | <1% | Report with the number of protective device controllers or relays that are DCD capable
Asset Inspection – Quality Control | GM-09 | 8.1.6.2 | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 20,000 audit locations*; 90 percent pass rate System Inspection Transmission – HFTD (Field): 1,800 audit locations*; 90 percent pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 80 percent pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 80 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 15,000 audit locations*; 92 percent pass rate System Inspection Transmission – HFTD (Field): 1,300 audit locations*; 92 percent pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 88 percent pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 88 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 16,000 audit locations*; 95 percent pass rate System Inspection Transmission – HFTD (Field): 1,450 audit locations*; 95 percent pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 95 percent pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 95 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Final reports and field guides for all audits
a) Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations.
(b) x% Risk Impact has a non‑substantive update to show risk reduction from pole and non‑pole notifications combined

## TABLE 8.1.7-2 REVISED
TABLE 8.1.7-2 (REVISED):
REVISED ADDRESSING INFRACTIONS FOUND DURING INSPECTIONS
Ignition‑Risk HFTD/HFRA Notifications
| Non‑Pole | Pole | Total(a) | Non‑Ignition Risk HFTD/HFRA | Total Notifications(a)
| (A) | (B) | (C) = (A)+ (B) | (D) | (E) = (C) + (D)
Backlog as of July 24, 2023 | 91400 | 92000 | 183400 | 47,000(b) | 230400
Year 1: 2024 | -35000 | -31200 | -66200 | 0 | -66200
Year 2: 2025 | -29400 | -29600 | -59000 | 0 | -59000
Total Notifications Closed | -64400 | -60800 | -125200 | 0 | -125200
Total Notifications Remaining at the end of the 2023‑2025 WMP cycle | 27000 | 31200 | 58200 | 47000 | 105200
Year 3: 2026 | -12400 | -21300 | -33700 | -6400 | -40100
Year 4: 2027 | -14600 | -9900 | -24500 | -40600 | -65100
Total Notification Remaining | 0 | 0 | 0 | 0 | 0
______________
(a) Differences due to rounding.
(b) Non‑ignition risk notifications will be incorporated into the isolation zone bundles from 2023‑2027.

## TABLE 8-7-1 REVISED
REVISED TABLE 8-7-1:
REVISED GRID DESIGN AND MAINTENANCE SYSTEM INSPECTION QA PROGRAM
Inspection Type | Type of Audit | 2022 Audit Results (as of 12/1/22) | 2023 – 2025 Minimum Sample Size 2023‑25 (locations) | Yearly Target Pass Rate for 2023‑2025
Transmission | Field | N/A. This work was not performed in 2022. | 2023: 500 2024: 500 2025: 500 | 2023: 92% 2024: 94% 2025: 95%
Distribution | Field | N/A. This work was not performed in 2022. | 2023: 1,500 2024: 1,500 2025: 1,500 | 2023: 82% 2024: 90% 2025: 95%

## TABLE 8-7-2 REVISED
TABLE 8‑7‑2 (REVISED):
REVISED GRID DESIGN AND MAINTENANCE SYSTEM INSPECTION QC PROGRAM
Inspection Program | Type of Audit | 2022 Audit Pass Rate Results (as of 12/1/22)(a) | 2023‑‑2025 Minimum Sample Size (locations)(b) | Yearly Target Pass Rate for 2023 – 2025
System Inspection Transmission ‑ HFTD | Desktop | 92.1% | 2023: 20,000 | 2023: 90%
|  |  | 2024: 15,000 | 2024: 92%
|  |  | 2025: 16,000 | 2025: 95%
System Inspection Transmission – HFTD | Field | 80.9% | 2023: 1,800 | 2023: 90%
|  |  | 2024: 1,300 | 2024: 92%
|  |  | 2025: 1,450 | 2025: 95%
System Inspection Distribution – HFTD | Desktop | 85.5% | 2023: 140,000 | 2023: 80%
|  |  | 2024: 140,000 | 2024: 88%
|  |  | 2025: 140,000 | 2025: 95%
System Inspection Distribution ‑ HFTD | Field | 79.3% | 2023: 30,000 | 2023: 80%
|  |  | 2024: 30,000 | 2024: 88%
|  |  | 2025: 30,000 | 2025: 95%
______________ (a) Asset Inspection QC pass rates in 2022 were not specific to HFTD locations, while the 2023 – 2025 target pass rates and associated audit locations are specific to HFTD areas. (b) 2023 – 2025 Minimum Sample Size (locations) are subject to change and dependent on completed execution work and constraints.

## TABLE 8-12 REVISED
REVISED TABLE 8-12:
VEGETATION MANAGEMENT IMPLEMENTATION OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description(a) | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Constraint Resolution Procedural Guideline | Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). For each major constraint category build a process for addressing each constraint type, implement the new process, and create metrics to track each constraint type. Reporting will track total constraints by type and the time it takes to resolve a constraint after it has been identified. PG&E will consider creating a “right tree‑right place” program, as part of the centralize Constraints Resolution process. | VM‑09 | GO 95, Rule 35 GO 95, Rule 35 Appendix E GO 95, Rule 18 PRC 4293 and 4295.5 CCR Title 14 Sections 1250, 1251, 1252, 1253, 1256, 1257 and 1258 ANSI A300 | 1. Procedural guideline and evaluation of a “right tree‑right place” program. 2. Reports from VM system of record demonstrating added constraints tracking functionality. | 1. 12/31/2023 2. 12/31/2025 | Section 8.2.6 Page 705 ACI PG&E 22‑25 Page 1096
_______________ (a) While not a defined objective, PG&E will continue to address risk through our compliance work as well as other mitigation measures including operational mitigations, Public Safety Power Shutoff (PSPS), and Enhanced Powerline Safety Settings (EPSS).

## TABLE 8-13 REVISED
REVISED TABLE 8-13:
VEGETATION MANAGEMENT IMPLEMENTATION OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description(a) | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes,Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Inspection in HFTD and HFRA supporting key vegetation management initiatives | Continue multiple inspection activities in HFTD and HFRA supporting key vegetation management initiatives | VM‑10 | GO 95, Rule 35 GO 95, Rule 35 Appendix E GO 95, Rule 18 PRC 4293 and 4295.5 CCR Title 14 Sections 1250, 1251, 1252, 1253, 1256, 1257 and 1258 ANSI A300 | VM Database | 2032-12-31 | Section 8.2.2 Page 621
Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Enhance and refine Focus Tree Inspection ‑ Areas of Concern (AOC) development criteria and application of the AOCs to vegetation management programs | VM‑11 | GO 95, Rule 35 GO 95, Rule 35 Appendix E GO 95, Rule 18 PRC 4293 and 4295.5 CCR Title 14 Sections 1250, 1251, 1252, 1253, 1256, 1257 and 1258 ANSI A300 | Documentation describing our efforts to enhance and refine the program | 2032-12-31 | Section 8.2.2.2.5 Page 673
Evaluate emerging technologies | Evaluate emerging technologies to enhance focus of and streamline execution of vegetation management inspections | VM‑12 | GO 95, Rule 35 GO 95, Rule 35 GO 95, Rule 18 PRC 4293 and 4295.5 CCR Title 14 Sections 1250, 1251, 1252, 1253, 1256, 1257 and 1258 ANSI A300 | Documentation describing our evaluation of emerging technologies | 2032-12-31 | Sections 8.2.4 Page 691
One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | VM-19 | Record Keeping: Enterprise Records and Information Management Standard (GOV 7101S) Routine: GO 95 Rule 35 and Rule 18 PRC 4292 PRC 4293 Distribution Inspection Procedure (DIP) (TD 7102P 01) Distribution Vegetation Management Standard (TD 7102S) Second Patrol: GO 95 Rule 35 and Rule 18 PRC 4292 PRC 4293 ESRB 4 Distribution Inspection Procedure (DIP) (TD 7102P 01) | Field in One VM capturing reason for removal for Routine, Second Patrol. | 2024-01-31 | Sections 8.2.4 Page 691
Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) ‑ VMPI2 ‑ and Tree Removal Inventory (TRI) ‑ Field Maps ‑ program to include capability to capture factors for prescribing trees for removal | VM-20 | Record Keeping: Enterprise Records and Information Management Standard (GOV 7101S) VMOM: GO 95 Rule 35 PRC 4293 Distribution Inspection Procedure (DIP) (TD 7102P 01) TRI: GO 95 Rule 35 PRC 4293 PUC 8386 Distribution Inspection Procedure (DIP) (TD 7102P 01) | Field capturing reason for removal for VMOM – VMPI2 ‑ and TRI – Field Maps. | 2024-11-15 | Sections 8.2.4 Page 691
FTI Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form | VM-21 | Record Keeping: Enterprise Records and Information Management Standard (GOV 7101S) FTI: GO 95 Rule 35 PRC 4293 Distribution Inspection Procedure (DIP) (TD 7102P 01) | Digitization of Tree Risk Assessment Form Reasons for Tree Abatement | 2024-03-31 | Section 8.2.2.2.5 Page 673
_______________
(a) While not a defined objective, PG&E will continue to address risk through our compliance work as well as other mitigation measures including operational mitigations, Public Safety Power Shutoff (PSPS), and Enhanced Powerline Safety Settings (EPSS).

## TABLE 8-14 REVISED
REVISEDTABLE 8‑14
REVISED PG&E VM TARGETS
Target Name | Initiative Activity Tracking ID | Reference Section | 2023 Target & Unit | X% Risk Impact 2023 | 2024 Target & Unit | X% Risk Impact 2024 | 2025 Target & Unit | X% Risk Impact 2025 | Method of Verification
LiDAR Data Collection –Transmission(a) | VM‑01 | 8.2.2.1.1 | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD/HFRA and non‑HFTD Transmission circuit miles. | N/A | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non‑HFTD Transmission circuit miles. | N/A | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non‑HFTD Transmission circuit miles. | N/A | LiDAR Contractor Work Complete Attestation
Pole Clearing Program | VM‑02 | 8.2.3.1 | Inspect, clear, and maintain, where clearing is necessary 77,503 poles per Vegetation Control Standard TD‑7112S. | <1% | 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD‑7112S will be inspected, cleared, and maintained where clearing is necessary. | <1% | 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD‑7112S will be inspected, cleared, and maintained where clearing is necessary. | <1% | List of all poles in VM database as of October 1, 2022, with work status
Focused Tree Inspections (FTI) | VM‑03 | 8.2.2.2.5 | Complete focus tree inspections of 250 Circuit Miles in defined Areas of Concern (AOC) locations.(b) | <1% | Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. | <1% | Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. | <1% | Documentation of pilot program inspections in VM system of record.
Tree Removal Inventory (TRI) | VM‑04 | 8.2.2.2.4 | Mitigate(c) 15,000 trees identified from the legacy EVM Program. | <1% | Mitigate(c) 20,000 trees identified from the legacy EVM Program. | <1% | Mitigate(c) 25,000 trees identified from the legacy EVM Program. | <1% | Report from VM database reflecting hazard no longer present.
Defensible Space Inspections – Distribution Substation(d) | VM‑05 | 8.2.2.3.1 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 131 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 53% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 131 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 53% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 131 distribution substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 53% (Eyes‑on‑Risk) | Closed notifications
Defensible Space Inspections – Transmission Substation(d) | VM‑06 | 8.2.2.3.1 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 55 transmission substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 22% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 55 transmission substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 22% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P‑01 at 55 transmission substations. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 22% (Eyes‑on‑Risk) | Closed notifications
Defensible Space Inspections – Hydroelectric Substations and Powerhouses | VM‑07 | 8.2.2.3.1 | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P‑01 at 61 Hydroelectric Generation Substations and Powerhouses. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 25% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P‑01 at 61 Hydroelectric Generation Substations and Powerhouses. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 25% (Eyes‑on‑Risk) | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P‑01 at 61 Hydroelectric Generation Substations and Powerhouses. Co‑located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | 25% (Eyes‑on‑Risk) | Closed notifications
Vegetation Management – Quality Verification | VM‑08 | 8.2.5 | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,500 audit locations*; 95% pass rate Transmission VM – HFTD: 1,200 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,800 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,675 audit locations*; 95% pass rate Transmission VM – HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,926 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,862 audit locations*; 95% pass rate Transmission VM – HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | N/A | Final reports and field guides for all audits
Routine Ground ‑Transmission | VM‑13 | 8.2.2.1.1 | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | 100% (Eyes‑on‑Risk) PG&E system | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | 100% (Eyes‑on‑Risk) PG&E system | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | 100% (Eyes‑on‑Risk) PG&E system | Report from VM database reflecting completed work.
Second Patrol – Transmission | VM‑14 | 8.2.2.1.2 | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | 100% (Eyes‑on‑Risk) HFTD / HFRA | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | 100% (Eyes‑on‑Risk) HFTD / HFRA | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | 100% (Eyes‑on‑Risk) HFTD / HFRA | Report from VM database reflecting completed work.
Integrated Vegetation Management – Transmission | VM‑15 | 8.2.2.1.3 | Complete Integrated Vegetation Management and Fee Inspections of 11,194 acres ROW across the Transmission systemwide | <1% | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | TBD | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | TBD | Report from VM database reflecting completed work.
Routine Patrol – Distribution(e) | VM‑16 | 8.2.2.2.1 | Complete Distribution Routine Annual Patrol Inspection of 79,000 overhead circuit miles system wide | <1% | Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide | <1% | Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide | <1% | Report from VM database reflecting completed work.
Second Patrol – Distribution(e) | VM‑17 | 8.2.2.2.2 | Complete Distribution Second Patrol Inspection of 43,000 circuit miles that are in the following map layers FHSZ, WUI, SRA, FRA, HFTD, and HFRA locations. | <1% | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | <1% | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | <1% | Report from VM database reflecting completed work.
VM for Operational Mitigations (VMOM)(f) | VM‑18 | 8.2.2.2.3 | N/A | N/A | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry‑over work and prescriptions resulting from pro‑active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | TBD | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry‑over work and prescriptions resulting from pro‑active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | TBD | Report from VM database reflecting completed work.
Vegetation Management - Quality Control | VM-22 | 8.2.5.2 | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 75,000 audit locations*; 80 percent pass rate Transmission VM – HFTD: 12,500 audit locations*; 88 percent pass rate Vegetation Control Pole Clearing – HFTD: 10,500 audit locations*; 80 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 80,000 audit locations*; 88 percent pass rate Transmission VM – HFTD: 13,500 audit locations*; 92 percent pass rate Vegetation Control Pole Clearing – HFTD: 11,500 audit locations*; 88 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 85,000 audit locations*; 95 percent pass rate Transmission VM – HFTD: 14,500 audit locations*; 95 percent pass rate Vegetation Control Pole Clearing – HFTD: 12,500 audit locations*; 95 perecnt pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | N/A | Final reports and field guides for all audits
_______________
(a) VM‑01 LiDAR is flown in late summer and early fall in the prior year to enable ground inspection's next cycle to begin in November that then allows tree work to commence on January 1 of the following year.
(b) See PG&E’s response to Critical Issue RN‑PG&E‑23‑07, Remedy (b) and (c).
(c) We note that for purposes of Target VM‑04, the term “Mitigate” is intended to refer to a tree identified from the legacy EVM Program that is either: (1) removed by the TRI program; (2) removed by another PG&E VM program and no longer present; or (3) no longer poses a threat to PG&E facilities because the facilities have been relocated.
(d) VM‑05 and VM‑06 Defensible Space inspections begin in late November to enable work mitigation to be completed before fire season begins in the following year.
(e) The Distribution Routine VM – HFTD includes audit locations and associated pass rates for distribution second patrols. The second patrol is now managed as part of the overall Distribution Routine VM program.
(f)PG&E has not included a 2023 target for the VMOM Program. This is a new program for 2023 stemming from the conclusion of the EVM Program. This program will help reduce outages and potential ignitions using a risk informed, targeted plan to mitigate potential vegetation contacts based on historic vegetation outages on EPSS enabled circuits. Currently, PG&E only has one full year of EPSS outage data, and we are still developing our VMOM inspection process. Accordingly, the extent of work necessary for this program in 2023 has not yet been fully determined. We anticipate, however, that the operational lessons learned from 2023 execution of the VMOM Program, combined with another full year of EPSS outage data, will support our conservative target estimate of mitigating 6,500 trees as part of this program in both 2024 and 2025. In 2023, we will also work to establish a process to avoid any double counting of trees worked as part of the VMOM Program in 2024 and 2025 that may also be identified for work in connection with our TRI Program. No double counting will take place in 2023 because VMOM does not have an annual target.

## TABLE 8-15 REVISED
REVISED TABLE 8-15:
REVISED PG&E VEGETATION INSPECTIONS TARGETS BY YEAR
Target Name | Initiative Activity Tracking ID | Reference Section | Target End of Q2 2023 & Unit | Target End of Q3 2023 & Unit | End of Year Target 2023 & Unit | Target End of Q2 2024 & Unit | Target End of Q3 2024 & Unit | End of Year Target 2024 & Unit | End of Year Target 2025 & Unit
LiDAR Data Collection – Transmission(a) | VM‑01 | 8.2.2.1.1 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500
|  |  | Circuit Miles | Circuit Miles | Circuit Miles | Circuit Miles | Circuit Miles | Circuit Miles | Circuit Miles
Pole Clearing Program | VM‑02 | 8.2.3.1 | 57,750 Distribution poles | 77,503 Distribution poles | 77,503 Distribution poles | 47,250 Distribution poles | 63,000 Distribution poles | 63,000 Distribution poles | 52,000 Distribution poles
Focused Tree Inspections (FTI)(b) | VM‑03 | 8.2.2.2.5 | 0 Circuit Miles | 0 Circuit Miles | 250 Circuit Miles | 500 Circuit Miles | 1,250 Circuit Miles | 1,500 Circuit Miles | 1,500 Circuit Miles
Tree Removal Inventory (TRI)(c) | VM‑04 | 8.2.2.2.4 | 0 Trees | 0 Trees | 15,000 Trees | 6,200 Trees | 14,000 Trees | 20,000 Trees | 25,000 Trees
Defensible Space Inspections – | VM‑05 | 8.2.2.3.1 | 130 Distribution Substations | 131 Distribution Substations | 131 Distribution Substations | 130 Distribution Substations | 131 Distribution Substations | 131 Distribution Substations | 131 Distribution Substations
Distribution Substation(d)
Defensible Space Inspections – | VM‑06 | 8.2.2.3.1 | 55 Transmission Substations | 55 Transmission Substations | 55 Transmission Substations | 55 Transmission Substations | 55 Transmission Substations | 55 Transmission Substations | 55 Transmission Substations
Transmission Substation(d)
Defensible Space Inspections – | VM‑07 | 8.2.2.3.1 | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses | 61 Hydroelectric Substations and Powerhouses
Hydroelectric Substations and Powerhouses
Routine Ground –Transmission | VM‑13 | 8.2.2.1.1 | 16,396 Circuit Miles | 17,738 Circuit Miles | 17,740 Circuit Miles | 16,396 Circuit Miles | 17,738 Circuit Miles | 17,740 Circuit Miles | 17,740 Circuit Miles
Second Patrol – Transmission(e) | VM‑14 | 8.2.2.1.2 | 0 Circuit Miles | 0 Circuit Miles | 5,625 Circuit Miles | 0 Circuit Miles | 0 Circuit Miles | 5,625 Circuit Miles | 5,625 Circuit Miles
Integrated Vegetation Management – Transmission | VM‑15 | 8.2.2.1.3 | 11,151 Acres | 11,194 Acres | 11,194 Acres | 2,590 Acres | 5,690 Acres | 6,504 Acres | 6,504 Acres
Routine Patrol – Distribution(f) | VM‑16 | 8.2.2.2.1 | 41,761 Circuit Miles | 61,806 Circuit Miles | 79,000 Circuit Miles | 39,325 Circuit Miles | 58,988 Circuit Miles | 78,650 Circuit Miles | 78,200 Circuit Miles
Second Patrol – Distribution(f) | VM‑17 | 8.2.2.2.2 | 18,904 Circuit Miles | 30,952 Circuit Miles | 43,000 Circuit Miles | 11,831 Circuit Miles | 17,947 Circuit Miles | 25,685 Circuit Miles | 25,685 Circuit Miles
VM for Operational Mitigations(g) | VM‑18 | 8.2.2.2.3 | 0 Trees | 0 Trees | 0 Trees | 3,000 Trees | 5,000 Trees | 6,500 Trees | 6,500 Trees
_______________
(a) VM‑01 LiDAR is flown in late summer and early fall in the prior year to enable ground inspection's next cycle to begin in November that then allows tree work to commence on January 1 of the following year.
(b) The FTI Program is a new pilot that began in Q2 2023 and stems from the conclusion of the EVM Program. In response to this Revision Notice, we have modified our 2023‑2025 WMP to include a target associated with this pilot program. Given the program’s late start in the year, as well as our limited operational experience executing this program, we have only provided an annual target ending in quarter four for this new program. As shown above, conservative estimates for rolling, quarterly targets in 2024 and an annual target in 2025 have been provided. See PG&E’s response to Critical Issue RN‑PG&E‑23‑07, Remedy (b) and (c).
(c) The TRI Program is a new program stemming from the conclusion of the EVM Program. As indicated in the 2023‑2025 WMP, we are still developing our inspection process. Given our limited operational experience executing this program, we have only provided an annual target ending in quarter four for this new program. As shown above, conservative estimates for rolling, quarterly targets in 2024 and an annual target in 2025 have been provided.
(d) VM‑05 and VM‑06 Defensible Space inspections begin in late November to enable work mitigation to be completed before fire season begins in the following year.
(e) The Second Patrol – Transmission target is all included in quarter four because that is when the LiDAR work takes place in the HFTD each year.
(f) The Distribution Routine VM – HFTD includes audit locations and associated pass rates for distribution second patrols. The second patrol is now managed as part of the overall Distribution Routine VM program.
(g) As noted in Revised Table 8‑14, PG&E has not included a 2023 target for the VMOM Program. Please see footnote (c) in that table for additional information. As shown above, conservative, estimated rolling quarterly targets have been provided for 2024 and an annual target for 2025.

## TABLE 8-17 REVISED
REVISED TABLE 8-17:
VM INSPECTION FREQUENCY, METHOD, AND CRITERIA
Type(1),(2) | Inspection Program Name | Frequency or Trigger | Method of Inspection | Governing Standards and Operating Procedures
Transmission | Routine | Recurring Annual Cycle | LiDAR with follow up ground patrol | NERC Standard Federal Agency Code (FAC) 003 04 NERC GO 95 Rule 35 PRC 4292 PRC 4293 Transmission Non Orchard Routine Patrol Procedure (TD 7103P 01) Transmission Orchard Routine Patrol Procedure (TD 7103P 02) Transmission Vegetation Management Standard (TD 7103S)
Transmission | Second Patrol | Recurring Cycle | LiDAR with follow up ground patrol | NERC Standard FAC 003 04 GO 95 Rule 35 PRC 4292 PRC 4293 ESRB 4 Transmission Non Orchard Routine Patrol Procedure (TD 7103P 01)
Transmission | Integrated Vegetation Management | Prioritization is based on aging work cycles and evaluation of vegetation re‑growth | LiDAR with follow up ground patrol | Transmission Integrated Vegetation Management (TIVM) Procedure (TD‑7103P‑04).
Distribution | Routine | Recurring Annual Cycle | Ground Based Patrol | GO 95 Rule 35 and Rule 18 PRC 4292 PRC 4293 Distribution Inspection Procedure (DIP) (TD 7102P 01) Distribution Vegetation Management Standard (TD 7102S)
Distribution | Second Patrol | Approximately 6 months offset from Routine Patrol | Ground Based Patrol | GO 95 Rule 35 and Rule 18 PRC 4292 PRC 4293 ESRB 4 DIP (TD 7102P 01)
Distribution | VM for Operational Mitigations | Workplan to Reduce Customer Impacts due to Vegetation Outages on EPSS ‑ If at any point PG&E determines this program does not effectively support efforts to reduce customer impacts due to Vegetation Outages on EPSS when compared to other viable approaches, PG&E will pause or discontinue the VMOM efforts. | Ground Based Patrol | GO 95 Rule 35 PRC 4293
Distribution | Tree Removal Inventory | Workplan to Remove or Re‑Evaluate Trees previously identified by EVM ‑ If at any point PG&E determines this program does not effectively support efforts to remove or re‑evaluate trees identified to EVM when compared to other viable approaches, PG&E will pause or discontinue the TRI efforts. | Ground Based Patrol | GO 95 Rule 35 PRC 4293 PUC 8386
Distribution | Focused Tree Inspections | Q2 2023 – Pilot | Ground Based Patrol | GO 95 Rule 35 PRC 4293
Substation | Defensible Space Inspection | Annually | Ground Inspection of substation | TD 3328S, LAND 4001P 01, LAND 5201P 01 Rule 18
_______________
Note 1
· Transmission: Detailed planning for the Routine Line Clearance Program is done in the fourth quarter of each year for the following year. The detailed planning process includes forecasting the number of units to be worked on each transmission line and setting the following years’ schedule; and
· Distribution: Detailed planning is conducted in the third and fourth quarter of each year for the following year. The detailed planning process includes forecasting the number of units that will be worked on each distribution circuit or project and setting the following years’ schedule.
Note 2
· Transmission: Transmission programs include Routine NERC and Routine Non‑NERC. These programs recur annually, with the IVM Program recurring based on vegetation growth response. See Section 8.2.2.1. See Table 8‑17 for mode of inspection; and
· Distribution: Distribution programs include Routine patrols which occur annually, and Second Patrol which occurs with an approximate six‑month offset from Routine patrols. See Section 8.2.2.2. See Table 8‑17 for mode of inspection.
· Substation: PG&E assesses the area around ET and Distribution Substations (including power houses and switching stations) in HFTD and HFRA areas to identify potential flammable fuels and vegetation for removal, minimizing the potential for ignition spread outside of facilities and providing improved structure defense capability for firefighting purposes. See Section 8.2.2.3. See Table 8‑17 for mode of inspection.

## TABLE 8-18-1 REVISED
REVISED TABLE 8-18-1:
REVISED VEGETATION MANAGEMENT QA PERFORMANCE (FORMERLY QV) PROGRAM 21
Inspection Program | Type of Audit | 2022 Sample Size(a) | 2022 Audit Pass Rate Results(c) | 2023‑2025 Minimum Sample Size (locations)(d) | Yearly Target Pass Rate for 2023 – 2025
Distribution | Field | 28,516 Locations | 91.3%(b) | N/A | 2023: N/A 2024: N/A 2025: N/A
Distribution VM ‑HFTD | Field | N/A | N/A | 2023: 2,500 2024: 2,675 2025: 2,862 | 2023: 95% 2024: 95% 2025: 95%
Distribution VM – Non‑HFTD | Field | N/A | N/A | N/A | 2023: N/A 2024: N/A 2025: N/A
Transmission | Field | 5,896 Locations | 94.2% | N/A | 2023: N/A 2024: N/A 2025: N/A
Transmission VM – HFTD | Field | N/A | N/A | 2023: 1,200 2024: 1,284 2025: 1,374 | 2023: 95% 2024: 95% 2025: 95%
Transmission VM – Non‑HFTD | Field | N/A | N/A | N/A | 2023: N/A 2024: N/A 2025: N/A
Vegetation Control Pole Clearing | Field | 3,469 Poles | 90.3% | N/A | 2023: N/A 2024: N/A 2025: N/A
Vegetation Control Pole Clearing – HFTD | Field | N/A | N/A | 2023: 1,800 2024: 1,926 2025: 2,061 | 2023: 95% 2024: 95% 2025: 95%
Second Patrol | Field | 12,952 Locations | N/A(b) | N/A | 2023: N/A 2024: N/A 2025: N/A
Second Patrol – HFTD | Field | N/A | N/A | N/A | 2023: N/A 2024: N/A 2025: N/A
_______________ (a) Sample calculations were done at the location level for QVVM Programs. Locations vary in geographic size and can have multiple trees within one location. Not all trees in a single location may be exclusively HFTD or Non‑HFTD. For this reason, it is not possible to break out HFTD and Non‑HFTD sample sizes for Distribution and Transmission. (b) In 2022, the distribution score of 91.34 percent reflected both Maintenance Pre‑Inspection/Tree Trimming (PI/TT) and Second Patrol (PI/TT). (c) “N/A” in 2022 indicates that PG&E did not conduct an audit of the program. (d) “N/A” in 2023‑2025 indicates that PG&E does not plan to conduct an audit of the program during this time.

## TABLE 8-18-2 REVISED
TABLE: 8‑18‑2 (REVISED):
VEGETATION MANAGEMENT QC PERFORMANCE
Inspection Program | Type of Audit | 2022 Sample Size(a) | 2022 Audit Pass Rate Results(a) | 2023‑2025 Minimum Sample Size (locations)(a)(b) | Yearly Target Pass Rate for 2023 – 2025(a)
EVM(d) | Field | 100% (1,924 miles) | 80.64% First Pass Rate | N/A | N/A
Distribution Routine VM – HFTD(c) | Field | N/A | N/A | 2023: 75,000 2024: 80,000 2025: 85,000 | 2023: 80% 2024: 88% 2025: 95%
Distribution Routine VM – Non‑HFTD | Field | N/A | N/A | N/A | N/A
Vegetation Control Pole Clearing – HFTD | Field | N/A | N/A | 2023: 10,500 2024: 11,500 2025: 12,500 | 2023: 80% 2024: 88% 2025: 95%
Distribution Second Patrol(c) | Field | N/A | N/A | N/A | N/A
Transmission VM – HFTD | Field | N/A | N/A | 2023: 12,500 2024: 13,500 2025: 14,500 | 2023: 88% 2024: 92% 2025: 95%
Transmission VM – Non‑HFTD | Field | N/A | N/A | N/A | N/A
______________ (a) “N/A” indicates that PG&E did not conduct an audit of the program or does not plan to conduct an audit of the program. (b) 2023 – 2025 Minimum Sample Size (locations) are subject to change and dependent on completed execution work and external factors. (c) The Distribution Routine VM – HFTD includes audit locations and associated pass rates for distribution second patrols. The second patrol is now managed as part of the overall Distribution Routine VM program. (d) The EVM program was discontinued in 2023.

## TABLE 8-21 REVISED
REVISED TABLE 8-21:
SITUATIONAL AWARENESS INITIATIVE OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes,Standards, and Best Practices (See Note) | Method of Verification (i.e., Program) | Completion Date | Reference (Section and Page #)
Artificial Intelligence (AI) in Wildfire Cameras | Enable AI processing of Wildfire Camera Data to provide automated wildfire notifications in the internal PG&E monitoring tool (Wildfire Incident Viewer (WIV)). | SA‑01 | Early detection of new ignitions can help reduce the overall impact of the ignition through increased awareness and more rapid response. | Report from vendor outlining the deployment of the AI solution and incorporation of PG&E data feeds. Successful user testing for notification push to WIV. | 2023-06-30 | Section 8.3.2.3 Page 736
EFD and DFA Reporting | Develop scalable processes to: (a) analyze alarms and alerts from Early Fault Detection (EFD) and Distribution Fault Anticipation (DFA) sensors; (b) conduct field investigation and reporting; (c) track identified mitigations to completion; and (d) track effectiveness of issue identification and remediation using EFD/DFA technologies. | SA‑03 | EFD and DFA are emerging technologies. Standards and best practices are to be developed as PG&E gains expertise operating these technologies | a) Specification document – Analysis Methodology for identified EFD/DFA Use Cases b) Procedures detailing field processes for EFD/DFA field investigations c) Report for EFD/DFA Investigation Results and Remediations | 2023-12-31 | Section 8.3.3.1 Page 738
FPI and IPW Modeling – Revision Evaluation | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model. This involves testing new features and types of model configurations that could improve model skill. At present we do not know if model skills can be improved, but we will attempt to do so. | SA‑04 | Industry best practice across California (CA) utilities is to run and improve their own FPI. | Documentation that demonstrates evaluation of enhancements to the FPI model. | 2023-12-31 | Section 8.3.6.3 Page 773
Evaluate FPI and IPW Modeling enhancements in 2023 ‑ 2025(a) | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. At present we do not know if model skill can be improved but we will attempt to do so in 2023. If model skill can be improved and is approved, we plan to operationalize the new models in 2024 and continue operations in 2025. We do not know if any new models developed will be approved for operations by PG&E’s Wildfire risk governance committee. | SA‑05 | Industry best practice across California (CA) utilities is to run and improve their own FPI. | Documentation that demonstrates evaluation of enhancements to the FPI and IPW model. | 2025-12-31 | Section 8.3.6.3 Page 773
Monitor and evaluate the Cameras AI system’s performance | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. | SA‑07 | Early detection of new ignitions can help reduce the overall impact of the ignition through increased awareness and more rapid response. | Documentation that demonstrates evaluation of enhancements to the Camera AI system. | 2025-12-31 | Section 8.3.2.3 Page 736
EFD and DFA Reporting | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. | SA‑09 | EFD and DFA are emerging technologies. Standards and best practices are to be developed as PG&E gains expertise operating these technologies. | A feasibility proposal to the Wildfire Risk Governance Steering Committee (WRGSC) for integrating sensor findings into the inspection program. | 2025-12-31 | Section 8.3.3.1 Page 738
_______________
(a) In response to Critical Issues RN‑PG&E‑23‑01, PG&E has modified SA‑05 to include “EPSS” in the objective and method of verification descriptions. Details on this change are included in RN‑PG&E‑23‑08 in Section 9.2.1.

## TABLE 8-22 REVISED
REVISED TABLE 8-22:
SITUATIONAL AWARENESS INITIATIVE OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., Program) | Completion Date | Reference (Section and Page #)
Evaluate FPI and IPW Modeling enhancements in 2026‑2032 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in the 2026‑2033 period. This work involves testing new features and types of model configurations that could improve model forecasting ability. | SA‑06 | Industry best practice across California (CA) utilities is to run and improve their own FPI. | Documentation that demonstrates evaluation of enhancements to the FPI model. | 2032-12-31 | Section 8.3.6.3 Page 773
Evaluate the Cameras AI system functionalities and technologies | In partnership with Digital Path and its collaboration with other camera sponsors, evaluate the AI system for opportunities to test new functionalities and newly developed break‑through technologies. We will explore new best practices to ensure the ongoing effectiveness of the system. | SA‑08 | Early detection of new ignitions can help reduce the overall impact of the ignition through increased awareness and more rapid response. | Documentation that demonstrates evaluation of newly developed break‑through technologies and new best practices to the Camera AI system. | 2032-12-31 | Section 8.3.2.3 Page 736
Evaluate the use and effectiveness of real‑time monitoring tools | Each year, we will evaluate and discuss our situational awareness tools internally, as well as with other IOUs. These evaluative discussions will include reviewing observations of our various situational awareness tools and identifying potential areas for improvement. We will also discuss best practices and lessons learned. These discussions will help inform potential changes to what situational awareness tools we incorporate, as well as how they are incorporated. This may include equipment upgrades, new tech integrations, model improvements, and enhanced data initiatives. | SA‑12 | For emerging technologies, standards and best practices are to be developed as PG&E gains expertise operating these technologies. Early detection of new ignitions can help reduce the overall impact of the ignition through increased awareness and more rapid response. | An annual feasibility proposal to the Wildfire Risk Governance Steering Committee (WRGSC) for integration discussion. | 2032-12-31 | Section 8.3.2.3 Page 736

## TABLE 8-23 REVISED
TABLE 8-23 (REVISED):
REVISED SITUATIONAL AWARENESS INITIATIVE TARGETS BY YEAR
Target Name | Initiative Activity Tracking ID | Reference Section | 2023 Target & Unit | x% Risk Impact 2023 | 2024 Target & Unit | x% Risk Impact 2024 | 2025 Target & Unit | x% Risk Impact 2025 | Method of Verification
Line Sensor – Installations | SA‑02 | Section 8.3.3.1 | Install Line Sensor devices on 40 circuits. | 8% (Eyes‑on‑Risk) | Install Line Sensor devices on 40 circuits. | TBD | Install Line Sensor devices on 40 circuits. | TBD | Completed job packages
Distribution Fault Anticipation (DFA) ‑ Installations | SA‑10 | Section 8.3.3.1 | Install 5 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation.(a) | < 1% (Eyes‑on‑Risk) | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation. | 5.1% (Eyes‑on‑Risk) | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation. | 5.1% (Eyes‑on‑Risk) | Report demonstrating the first communication between the sensor and the Headend software.
Early Fault Detection (EFD) ‑ Installations | SA‑11 | Section 8.3.3.1 | Install Early Fault Detection (EFD) sensors on 2 circuits.(b) | < 1% (Eyes‑on‑Risk) | Install Early Fault Detection (EFD) sensors on 2 circuits. | < 1% (Eyes‑on‑Risk)) | Install Early Fault Detection (EFD) sensors on 4 circuits. | 2.8% (Eyes‑on‑Risk)) | SAP report with notification completion date, circuit name, and location.
(a) A total of 5 DFA sensors were installed in 2023 from 2022 carry‑over workplans. These installs were not counted or credited toward work in 2022.
(b) A total of 2 circuits were instrumented with EFD sensors in 2023 from 2022 carry‑over workplans. These installs were not counted or credited toward work in 2022.

## TABLE 8-33 REVISED
TABLE 8-33 (REVISED):
EMERGENCY PREPAREDNESS INITIATIVE OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP) | EP‑01 | PSPS exercise requirements: • Phase 1: Decision (D.) 19 05 042 • PSPS OII: D.21 06 014 • PSPS Phase 2 D.20 05 051 • PSPS Phase 3 D.21 06 034 Wildfire exercise: 1) Rulemaking (R.) 18 12 005 Appendix A (b) De energization Exercises | Check‑in/check‑out records or After‑Action Review (AAR) items | 11/30/2023 11/30/2024 11/30/2025 | Section 8.4.2.3.1 Page 821
Maintain all hazards planning and preparedness program in 2023‑2025 | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. | EP‑02 | GO 166 Standard 1 and Standard 1.J ISO 45001 and 14001 | Check‑in/check‑out records or After‑Action Review (AAR) items | 2025-12-31 | Section 8.4.3.1 Page 837
Expand All Hazards planning to include additional threats and scenarios | Expand the All Hazards planning program to include additional threats and scenarios. | EP‑04 | GO 166 in entirety | Check‑in/check‑out records or After‑Action Review (AAR) items | 2025-12-31 | Section 8.4.3.1 Page 837

## TABLE 8-34 REVISED
TABLE 8-34 (REVISED):
EMERGENCY PREPAREDNESS INITIATIVE OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Common Operating Picture Technology | Design and deploy a common operating picture(a) | EP‑07 | N/A | 1. Common Operating Picture tool. 2. Guidance Document that defines the use of common operating picture | 2028-12-31 | Section 8.4.3.1 Page 837
Threats and Hazards Identification and Risk Assessment (THIRA) updates | Execute a Threats and Hazards Identification and Risk Assessment (THIRA)(b) update every three years to address changes in hazard landscape. Use information from THIRA to inform changes to the CERP and hazard annexes. | EP‑08 | GO‑166 | Published Company Emergency Response Plan (CERP) and Annexes. | 12/31/2023 12/31/2026 12/31/2029 12/31/2032 | Section 8.4.3.1 Page 837
County Execute Briefings | Hold briefings with 47 counties within PG&E’s service territory after every THIRA update to support integrated planning discussions. | EP‑09 | Best Practice | Documentation of meeting materials, and records of attendance. | 2032-12-31 | Section 8.4.3.1 Page 837
_______________
(a) A common operation picture (COP) is a continuously updated overview of an incident compiled throughout an incident's life cycle from data shared between integrated communication, information management, and intelligence and information sharing systems. The goal of a COP is real‑time situational awareness across all levels of incident management and across jurisdictions. https://www.dhs.gov/publication/common‑operating‑picture‑emergency‑responders
(b) According to FEMA https://www.fema.gov/emergency‑managers/national‑preparedness/goal/risk‑capability‑assessment#:~:text=The%20Threat%20and%20Hazard%20Identification,hazards%20can%20affect%20our%20community%3F The Threat and Hazard Identification and Risk Assessment (THIRA) is a three‑step risk assessment process that helps communities understand their risks and what they need to do to address those risks.

## TABLE 8-53 REVISED
TABLE 8-53 (REVISED):
COMMUNITY OUTREACH AND ENGAGEMENT INITIATIVE OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices | Method of Verification (i.e., Program) | Completion Date | Reference (Section and Page #)
Community Engagement – Meetings | For 2023‑2025, PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | CO‑01 | Continued from 2022 WMP – Investigation 19‑06‑015: 2017 North Bay Fires/ 2018 Camp Fire OII | 1) Meeting summary for In‑Person meetings 2) Recording of session for Virtual meetings | 9/30/2023 9/30/2024 9/30/2025 | Section 8.5.2 Page 884

## TABLE 8-54 REVISED
TABLE 8-54 (REVISED):
COMMUNITY OUTREACH AND ENGAGEMENT INITIATIVE OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices | Method of Verification (i.e., Program) | Completion Date | Reference (Section and Page #)
Community Engagement – Outreach to HFRA Infrastructure Customers | PG&E will perform outreach via e‑mail and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the CWSP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. | CO‑04 | Ongoing lessons learned from the WMP and proceedings pertaining to stakeholder engagement and wildfire safety. | 1) Report of assignments and completed tasks 2) List of critical infrastructure customers | 2032-12-31 | Section 8.5.2 Page 884
Community Engagement – Outage Preparedness Campaign | PG&E will also conduct at least one direct‑to‑customer outage preparedness campaign annually via email and/or direct mail targeting residential customers in the PSPS more likely or EPSS Program scope. | CO‑05 | Ongoing lessons learned from the WMP and proceedings pertaining to stakeholder engagement and wildfire safety. | 1) Letter content (sample letter) 2) Customer lists for distribution | 2032-12-31 | Section 8.5.2 Page 884

## TABLE 9-3 REVISED
TABLE 9-3 (REVISED):
PSPS INITIATIVE OBJECTIVES (3-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Evaluate enhancements for the PSPS Transmission guidance | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. | PS‑01 | Industry best practice across California utilities is to run and improve their own models. | Documentation on evaluation of update to PSPS guidance | 2025-12-31 | Section 9.2.1 Page 921
Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. | PS‑02 | D.19‑05‑042 and OIR 18‑12‑005 and Revision Notice 22‑12 from 2022 WMP, industry best practice across California utilities is to run and improve their own models. | Documentation on evaluation of update to PSPS guidance | 2025-12-31 | Section 9.2.1 Page 921
Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. | PS‑10 | Industry best practice across California utilities is to run and improve their own models. I.19 06 015 (Wildfire OII Settlement) D.20 06 017 (PSPS OII) D.21 06 014 (PSPS OII) | Monthly meeting notes submitted to CPUC by utility hosting joint IOU meeting | 2025-12-31 | Section 9.1.2 Page 906
Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | PS‑11 | All flight operations will be conducted under FAA Part 107 and Part 91 rules. | Documentation presented to the Wildfire Risk Governance Steering Committee (WRGSC) to show results of the pilot program effectiveness. | 2024-12-31 | Section 9.1.2 Page 906

## TABLE 9-4 REVISED
TABLE 9-4 (REVISED):
PSPS INITIATIVE OBJECTIVES (10-YEAR PLAN)
Objective Name | Objective Description | Applicable Initiative(s), Tracking ID(s) | Applicable Regulations, Codes, Standards, and Best Practices (See Note) | Method of Verification (i.e., program) | Completion Date | Reference (Section and Page #)
Evaluate the transition of the Portable Battery Program to permanent battery solutions | Evaluate the transition of the Portable Battery Program to permanent battery solutions for PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self‑identified vulnerable populations. | PS‑05 | CPUC R.12‑11‑005, D.19‑09‑027, CPUC R.12‑11‑005, D.20‑01‑021 | Documentation of the assessment for transitioning to permanent battery solutions | 2032-12-31 | Section 8.5.3 Page 892
Evaluate emerging technologies to reduce PSPS customer impact | Evaluate emerging technologies for transmission and distribution that may further reduce scale, scope, or frequency of PSPS. | PS‑08 | N/A | Documentation of recommendations made to the Wildfire Risk Governance Steering Committee (WRGSC). | 2032-12-31 | Section 9.1.2 Page 906
Reduce PSPS impacts via Undergrounding | Reduce PSPS size, duration, or frequency over the next ten years as part of our 10,000‑mile undergrounding program. | PS‑09 | N/A | Using the static 5 years (2018‑2022) back cast analysis under the 2022 PSPS protocols, generate a report of the impact of undergrounding to reducing size, duration, or frequency of PSPS. | 2032-12-31 | Section 9.1.2 Page 906

## TABLE RN-PG&E-23-03-1
TABLE RN-PG&E-23-03-1:
COMPARING EPSS RESOURCES TO OTHER MITIGATION PROGRAMS
Program Type | Internal Resource Hours |  |  | 2023 Projected Spend
| Other PG&E Wildfire Mitigations | EPSS Reliability Mitigation | EPSS Compared to Other Hours | Other PG&E Wildfire Mitigations | EPSS Reliability Mitigation | EPSS Compared to Other Spend
Vegetation Management | 4169621 | 76,757 (VMOM) | 1.8% | $1,272M | $23M (VMOM) | 1.9%
Asset Repair and Replacement | 2757498 | 111,058 (COE for EPSS) | 4% | $1,277M | $75M (COE for EPSS) | 5.9%
Additional Asset Inspections | 472151 | N/A | 0% | $161M | N/A | 0%
Undergrounding | 1477930 | 21301 | 1.4% | $1,253M | $10M(a) | 0.8%
_______________
(a) The EPSS reliability mitigation related to undergrounding represents a single reliability focused project that will include undergrounding as a component of its scope.

## TABLE RN-PG&E-23-03-2
TABLE RN-PG&E-23-03-2:
MITIGATION PRIORITIZATION CONSIDERING EPSS RISK
Program | EPSS Outage Profile | Existing Program Prioritization | EPSS Risk Consideration
Vegetation management | High frequency vegetation‑caused 2022 EPSS outages | Applicable wildfire risk and compliance driven maintenance cycles. | EPSS risk is not a primary driver of existing vegetation management programs. Accordingly, a dedicated and targeted vegetation management program, VMOM, was created by our EPSS program to address this outage profile on highly‑impacted circuit zones and represents a small percentage of overall vegetation spend.
Asset repair and replacement | High frequency equipment‑caused 2022 EPSS outages | PG&E’s open work orders (tag or notifications) program uses a risk‑informed prioritization approach to address the highest risk issues on its system.(a) | Open work orders (tags or notifications) on EPSS circuits are generally not prioritized over tags on non‑EPSS circuits except for EPSS devices on PG&E’s Critical Operating Equipment (COE) list.
Additional asset inspections | N/A | Applicable wildfire risk and compliance driven maintenance cycles. | EPSS risk is not a driver of existing asset inspection maintenance plans.
Undergrounding | N/A | The 2023‑2026 undergrounding portfolio is focused on undergrounding lines in the highest risk areas, which include the following: (1) Top Ranked Circuit Segments based on WDRMs; (2) Fire Rebuilds; (3) PSPS Mitigation Projects; and (4) PG&E's PSS Identification.(b) | PG&E currently does not use EPSS risk as a part of our decision‑making framework for scoping of locations for undergrounding work. However, EPSS may be a factor for consideration in future underground project scoping.
_______________
(a) 2023‑2025 WMP, R1, p. 447.
(b) 2023‑2025 WMP, R1, p. 344.

## TABLE RN-PG&E-23-02-1
TABLE RN-PG&E-23-02-1:
GRID DESIGN AND MAINTENANCE SYSTEM INSPECITON QC PROGRAM PERFORMANCE
Inspection Type | Type of Audit | 2023 YTD # of Locations Audited (as of 9/14/2023) | 2023 YTD Pass Rate Results (Data as of 9/14/2023)
Transmission – HFTD | Field | 2720 | 99.1%
Transmission – HFTD | Desktop | 27098 | 99%
Distribution – HFTD | Field | 31239 | 86.33%
Distribution – HFTD | Desktop | 118534 | 94%

## TABLE RN-PG&E-23-02-2
TABLE RN-PG&E-23-02-2:
VEGETATION MANAGEMENT QC PROGRAM
Inspection Program | Type of Audit | 2023 YTD # of Locations Audited (as of 9/14/2023) | 2023 YTD Pass Rate Results(a) (As of 9/14/2023)
Distribution VM ‑ HFTD | Field | 45143 | 85%
Transmission VM – HFTD | Field | 15194 | 94%
Vegetation Control Pole Clearing – HFTD | Field | 9564 | 86%

## TABLE RN-PG&E-23-04-1
TABLE RN-PG&E-23-04-1:
2023-2029 MAINTENANCE EXECUTIN PLAN IN THE HFTD/HFRA
Plan Year | Total Inspections(b) | New Tags Created | New Tags Executed(c) | Backlog within Year(d) (New Tags Backlog) | New Tags Backlog Cumulative | Aged Backlog(f) Units Executed | Aged Backlog(f) Units Remaining
2023 | 272000 | 85000 | 23000 | 62000 | 62000 | 29000 | 230000
2024 | 329000 | 64000 | 37000 | 27000 | 89000 | 66000 | 164000
2025 | 339000 | 66000 | 46000 | 20000 | 109000 | 59000 | 105000
2026 | 335000 | 74000 | 72000 | 2000 | 111000 | 40000 | 65000
2027 | 329000 | 64000 | 38000 | 26000 | 137000 | 65000 | 0
2028 | 272000 | 71000 | 110000 | -39000 | 98000 | 0 | 0
2029 | 272000 | 71000 | 110000 | -39000 | 59000 | 0 | 0
_______________
(a) The number of tags in our execution plan exceeds our targets to account for unforeseen delays or other mitigating factors.
(b) The total inspections per year and new tags created come from Table RN‑PG&E‑23‑04‑7, 2023‑2029 Forecast Find Rates by Inspection Rate in response to Remedy d(iii) below. Excludes (due to low impact) patrol and infrared inspections in the HFTD/HFRA.
(c) Refers to the number of tags created and closed in the same calendar year.
(d) Refers to the number of tags opened but not closed in a calendar year.
(e) Differences due to rounding.
(f) Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations.

## TABLE RN-PG&E-23-04-2
TABLE RN-PG&E-23-04-2:
REVISED DISTRIBUTION OPEN TAG REDUCTION TARGETS BY YEAR
Target Name | Initiative Activity Tracking ID | Reference Section | 2023 Target & Unit | x% Risk Impact 2023(b) | 2024 Target & Unit | x% Risk Impact 2024(b) | 2025 Target & Unit | x% Risk Impact 2025(b) | Method of Verification
HFTD/HFRA Open Tag Reduction – Distribution Backlog | GM‑03 | 8.1.7.2 | Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog(a) ignition risk EC notifications. This work will reduce 48 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations from 151.1 (risk units as of January 1, 2023) by 72.5 (48 percent) risk units. | 2.4% | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 68 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 2 year period (2023 to 2024), from 151.1 risk units—as of January 1, 2023—by 102.7 risk units (68 percent). | <1% | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications. Of these EC notifications, we expect to close out 55,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 77 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 3 year period (2023 to 2025), from 151.1 risk units—as of January 1, 2023—by 116.3 risk units (77 percent). | <1% | Closed work orders
_______________
(a) Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations.
(b) x% Risk Impact has a non‑substantive update to show risk reduction from pole and non‑pole notifications combined.

## TABLE RN-PG&E-23-04-3
TABLE RN-PG&E-23-04-3:
EXAMPLES OF FDA IGNITION RISK MAPPING
Facility | Damage | Action | Mapping to Risk Model(a)
High Sign | Missing | Install | Out of Scope
Pole | Decayed/Rotten | Replace | Support Structure Equipment Cause
Connector | Incorrectly Installed | Replace | Conductor Composite
Pole | Broken/Damaged | Replace | Support Structure Equipment Cause
Guy | Overgrown | Trim | Out of Scope
_______________
(a) Items mapped to a risk model can create an ignition risk. Items mapped “out of scope” do not create an ignition risk.

## TABLE RN-PG&E-23-04-4
TABLE RN-PG&E-23-04-4:
TAG FIND RATES, GROUND DETAILED INSPECTIONS (DATA AS OF 6/30/23)
Tier | 2022 | [5 empty] | 2023
| A Find Rate | B Find Rate | E Find Rate | F Find Rate | Inspection Count | Find Rate by Tier | A Find Rate | B Find Rate | E Find Rate | F Find Rate | Inspection Count | Find Rate by Tier
Non‑HFTD/HFRA | 0.28% | 1.1% | 17.23% | 3.36% | 3633 | 21.77% | 0.65% | 1.63% | 21.67% | 5.92% | 2146 | 31.55%
Tier 2 | 0.22% | 1.29% | 22.66% | 4.13% | 190121 | 28.13% | 0.5% | 2.17% | 23.61% | 4.41% | 68425 | 30.51%
Tier 3 | 0.16% | 0.91% | 13.56% | 2,80% | 206177 | 17.34% | 0.67% | 1.21% | 14.7% | 3.16% | 7122 | 19.6%
Zone 1 | 0.7% | 0.7% | 16.2% | 4.23% | 426 | 21.6% | N/A | N/A | N/A | N/A | N/A | N/A
Total | 0.19% | 1.09% | 17.93% | 1.44% | 199357 | 22.66% | 0.52% | 2.07% | 22.79% | 4.34% | 77691 | 29.83%
_______________
The tag find rates in Table RN‑PG&E‑23‑04‑4 do not include cancelled tags. Find rate is the percent of EC notifications created per pole inspected. There have been no EC notifications created in Zone 1 in 2023 to date.

## TABLE RN-PG&E-23-04-5
TABLE RN-PG&E-23-04-5:
DRIVERS OF INCREASED FIND RATES, E TAGS IN THE HFTD
F‑D‑A | 2023 Tags | Delta Find Rate | Guidance Change | Highlighted by QA/QC in 2022 | 2023 Training Emphasis | Notes
Pole Decayed/Rotten Replace | 3736 | 155 | X |  | X | Job Aid to 2305M JA02 was updated in 2023 with examples and more pictures on how to identify rotten poles. The topic was also highlighted as part of 2023 training. Refer to page 162‑164 of TD 2305M JA02 Rev. 11 for more details.(a)
Pole Woodpecker Damage Assessment | 2830 | 114 | X |  | X | Job Aid to 2305M JA02 was updated in 2023 with examples and more pictures on how to identify woodpecker damage on poles. The topic was also highlighted as part of 2023 training. Refer to page 168 of TD 2305M JA02 Rev. 11 for more details.
Hardware/Framing Loose Adjust | 2907 | 608 | X |  | X | Job Aid to 2305M JA02 was updated in 2023 with new guidance on identifying Cotter Key partially backed out. This condition was also tagged with Hardware/Loose/Adjust PDA. Refer to page 122 of TD 2305M JA 02 Rev. 11 for more details.
Pole Woodpecker Damage Replace | 1904 | New FDA | X |  | X | This was a new FDA added in 2023 in SAP. Job Aid TD 2305M JA02 was updated in 2023 with new guidance to directly create a Woodpecker Damage/replace tag if the damage is sufficient or if the woodpecker holes are near the framing hardware. Refer to page 168 and 169 of TD 2305M JA02 Rev. 11 for more details.
Pole Woodpecker Damage Repair | 1288 | New FDA | X |  | X | This was a new FDA added in 2023 in SAP. This allows inspectors to directly create a Woodpecker Damage/Replace tag and they determine if the damage can be repaired or needs to be replaced.
Guy Loose Adjust | 1208 | 212 | X | X | X | Job Aid TD 2305M JA02 was updated in 2023 to provide further clarification that any guy that is 2” from taut should be tagged as Guy/Loose/Adjust in addition this condition highlighted as part of the QA/QC findings in 2022.
_______________
(a) See Appendix E for Job Aid to 2305M JA02, Rev. 11.

## TABLE RN-PG&E-23-04-6
TABLE RN-PG&E-23-04-6:
2023-2025 FORECAST TAGS CREATED
2023 Actual and Forecasted Tags Creation(c)
Priority Level | Q1 (actual) | Q2 (actual) | Q3 | Q4 | Total
L2(a) | 1200 | 23000 | 34500 | 11500 | 70200
L3(b) | 100 | 4000 | 8000 | 2700 | 14800
2024 Forecasted Tags Creation(c)
Priority Level | Q1 | Q2 | Q3 | Q4 | Total
L2(a) | 800 | 17200 | 27000 | 9000 | 54000
L3(b) | 200 | 3300 | 5200 | 1700 | 10400
2025 Forecasted Tags Creation(c)
Priority Level | Q1 | Q2 | Q3 | Q4 | Total
L2(a) | 800 | 17700 | 27900 | 9300 | 55700
L3(b) | 200 | 3400 | 5400 | 1800 | 10800
______________
(a) A Level 2 (L2) tag is a GO95, Rule 18 priority level that aligns to PG&E priority Level B or Level E. Level B or E tags presents a risk of at least moderate potential impact to safety or reliability.
(b) A Level 3 (L3) tag is a GO95, Rule 18 priority level that aligns to PG&E priority Level F. Level F tags present a risk of low potential impact to safety or reliability.
(c) PG&E has not included a forecast for A tags in this analysis because the focus of this Critical Issues is how PG&E is addressing its backlog of maintenance tags. Since PG&E immediately addresses all A tags, we do not have an A tag backlog.

## TABLE RN-PG&E-23-04-7
TABLE RN-PG&E-23-04-7:
2023-2029 FORECAST FINDS BY INSPECTION TYPE
Inspection Type | Tier | Priority(c) | Find | Annual Inspections 2023 |  | Annual Inspections 2024 |  | Annual Inspections 2025 |  | Annual Inspections 2026 |  | Annual Inspections 2027 |  | Annual Inspections 2028 |  | Annual Inspections 2029
|  |  | Rate | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find | Planned by Tier | F’cst Tag Find
Aerial(a) | Non‑HFTD/HFRA | B | #N/A(d) | 700 | 0 | 900 | 0 | 900 | 0 | 900 | 0 | 900 | 0 | 700 | 0 | 700 | 0
Aerial(a) | Non‑HFTD/HFRA | E | #N/A |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Aerial(a) | Non‑HFTD/HFRA | F | #N/A |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Aerial(a) | Tier 2 | B | 2.58% | 30000 | 774 | 30000 | 774 | 30000 | 774 | 30000 | 774 | 30000 | 774 | 30000 | 774 | 30000 | 774
Aerial(a) | Tier 2 | E | 1.57% |  | 471 |  | 471 |  | 471 |  | 471 |  | 471 |  | 471 |  | 471
Aerial(a) | Tier 2 | F | 0.49% |  | 147 |  | 147 |  | 147 |  | 147 |  | 147 |  | 147 |  | 147
Aerial(a) | Tier 3 | B | 2.42% | 7300 | 177 | 7300 | 177 | 7300 | 177 | 7300 | 177 | 7300 | 177 | 7300 | 177 | 7300 | 177
Aerial(a) | Tier 3 | E | 0.82% |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60
Aerial(a) | Tier 3 | F | 0.22% |  | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  | 16
Ground b) | Non‑HFTD/HFRA | B | #N/A | 4800 | 0 | 4400 | 0 | 2200 | 0 | 3900 | 0 | 4400 | 0 | 4800 | 0 | 4800 | 0
Ground(b) | Non‑HFTD/HFRA | E | #N/A |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ground(b) | Non‑HFTD/HFRA | F | #N/A |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ground(b) | Tier 2 | B | 2.21% | 209600 | 6762 | 127400 | 2815 | 121500 | 2684 | 199000 | 4396 | 127400 | 2815 | 209600 | 4631 | 209600 | 4631
Ground(b) | Tier 2 | E | 24.37% |  | 60158 |  | 31039 |  | 29600 |  | 48479 |  | 31039 |  | 51072 |  | 51072
Ground(b) | Tier 2 | F | 5.42% |  | 14362 |  | 6903 |  | 6583 |  | 10782 |  | 6903 |  | 11359 |  | 11359
Ground(b) | Tier 3 | B | 1.79% | 6300 | 90 | 89500 | 1601 | 108200 | 1938 | 24300 | 435 | 89500 | 1601 | 6300 | 113 | 6300 | 113
Ground(b) | Tier 3 | E | 15.44% |  | 1079 |  | 13811 |  | 16713 |  | 3752 |  | 13811 |  | 978 |  | 978
Ground(b) | Tier 3 | F | 3.74% |  | 276 |  | 3346 |  | 4048 |  | 909 |  | 3346 |  | 237 |  | 237
Ground(b) | Zone 1 | B | 2.34% | 200 | 0 | 100 | 1 | 200 | 4 | 200 | 4 | 100 | 1 | 200 | 4 | 200 | 4
Ground(b) | Zone 1 | E | 17.76% |  | 0 |  | 10 |  | 33 |  | 33 |  | 10 |  | 33 |  | 33
Ground(b) | Zone 1 | F | 5.14% |  | 0 |  | 3 |  | 9 |  | 10 |  | 3 |  | 10 |  | 10
PTT | Tier 2 | E | 4.89% | 8700 | 427 | 46000 | 2249 | 46000 | 2249 | 46000 | 2249 | 46000 | 2249 | 8700 | 427 | 8700 | 427
PTT | Tier 3 | E | 4.35% | 4400 | 190 | 23000 | 1001 | 23000 | 1001 | 23000 | 1001 | 23000 | 1001 | 4400 | 190 | 4400 | 190
|  | Total(e)(f)(g) |  | 272000 | 84989 | 328600 | 64424 | 339300 | 66506 | 334600 | 73695 | 328600 | 64424 | 272000 | 70699 | 272000 | 70699
______________
(a) Aerial find rates based off 2023 actuals, matches future planned aerial inspection process.
(b) 2024 and beyond ground find rates based on 2022 actuals, predicted to most align with future inspection processes.
(c) PG&E has not included a forecast for A tags in this analysis because the focus of this Critical Issues is how PG&E is addressing its backlog of maintenance tags. Since PG&E immediately addresses all A tags, we do not have an A tag backlog.
(d) "N/A” indicates that we are not forecasting any finds in that combination of inspection type and tier.
(e) Planned inspections and inspection find rates are projections based on current information
(f) Excludes Patrols and Infrared inspections in the HFTD/HFRA because they account for less than 1 percent of the finds.
(g) Differences due to rounding.

## TABLE RN-PG&E-23-04-8
TABLE RN-PG&E-23-04-8:
2023-2029 RESOURCE ESTIMATES
Year | Total Crew Hours (000s) | Estimated Capital Costs ($Millions) | Estimated Expense Amounts ($Millions)
2023 | 1400 | 575 | 65
2024 | 2000 | 950 | 120
2025 | 2000 | 950 | 120
2026 | 2000 | 950 | 120
2027 | 1800 | 900 | 100
2028 | 1800 | 900 | 100
2029 | 1800 | 900 | 100

## TABLE RN-PG&E-23-05-1
TABLE RN-PG&E-23-05-1:
CIRCUIT SEGMENTS IN THE 2022 WMP UNDERGROUNDING WORKPLAN BUT NOT LISTED IN THE 2023-2026 UNDERGROUNDING WORKPLAN
Line No. | Circuit Segment | Reason the Circuit Segment does not Appear on 2023‑2025 WMP Undergrounding Workplan
1 | DUNBAR 1101440 | Circuit segment name changed to DUNBAR 110534. Included in the 2023‑2025 WMP Undergrounding Workplan.(a)
2 | DUNBAR 1103234 | Circuit segment name changed to DUNBAR 1101CB. Included in the 2023‑2025 WMP Undergrounding Workplan.(a)
3 | DUNBAR 1103839384 | Circuit segment name changed to DUNBAR 1101CB. Included in the 2023‑2025 WMP Undergrounding Workplan.(a)
4 | HALF MOON BAY 11036018 | Circuit segment name changed to HALF MOON BAY 11036012. Included in the 2023‑2025 WMP Undergrounding Workplan.(a)
5 | WYANDOTTE 11031504 | Circuit segment name changed to WYANDOTTE 1110980944. Included in 2023‑2025 WMP Undergrounding Workplan.(a)
6 | VOLTA 110111568 | Scheduled for Line Removal.
7 | BUELLTON 1102CB | Scheduled for Overhead Hardening (Covered Conductor).
8 | POINT MORETTI 1101415734 | Scheduled for Overhead Hardening (Covered Conductor).
_______________
(a) PG&E often changes circuit segment names when additional segmenting devices are placed on the grid or other grid design changes such as switching occur.

## TABLE RN-PG&E-23-05-2
TABLE RN-PG&E-23-05-2:
PG&E'S UNDERGROUNDING WORKPLAN FOR THE TOP 20 PERCENT WFE COMPARED TO RISK MODEL OUTPUT
Line No. | Year | Mileage in Top 20% WFE(a) | Percent of Portfolio in Top 20% WFE(a) | Mileage in Top 20% WDRM v3(b) | Percent of Portfolio in Top 20% WDRM v3(b) | Mileage in Top 20% WDRM v2(c) | Percent of Portfolio in Top 20% WDRM v2(c) | Mileage in Top 20% WDRM v2 and V3 | Percent of Portfolio in Top 20% WDRM v2 and v3
|  | A | B | C | D | E | F | G = C+E | H = D+F
1 | 2023 | 361 | 68% | 40 | 7% | 321 | 60% | 361 | 67%
2 | 2024 | 458 | 78% | 362 | 62% | 97 | 16% | 459 | 78%
3 | 2025 | 647 | 95% | 614 | 90% | 33 | 5% | 647 | 95%
4 | 2026 | 879 | 100% | 860 | 98% | 19 | 2.1% | 879 | 100%
5 | Total(d) | 2346 | 87% | 1876 | 70% | 470 | 17% | 2346 | 87%
_______________
(a) 2023‑2025 WMP, R1, Table 8.1.2‑3.
(b) WMP‑Discovery2023_DR_OEIS_008‑Q002Atch01_Redacted, Row 39.
(c) WMP‑Discovery2023_DR_OEIS_008‑Q002Atch01_Redacted, Row 24.
(d) Differences due to rounding.

## TABLE RN-PG&E-23-05-3
TABLE RN-PG&E-23-05-3:
EXAMPLE WCBA OUTPUT (MILLIONS OF DOLLARS)
Line No. | Mitigation Alternative | PVRR Cap. Invest. | Lifetime O&M Costs | Monetized Risk Value | [5 empty] | Risk Avoidance over Lifetime Benefit | Residual Risk over Lifetime | Lifetime – Benefit‑Cost
|  |  |  | Wildfire | Public Safety | Normal Reliability | PSPS | EPSS | Total Risk
|  | A | B | [6 empty] | C |  | D = C‑(A+B)
1 | Circuit Segment 1
2 | Covered Conductor Rebuild with EPSS and DCD | 30.96 | 18.91 | 2531.09 | 0.47 | 4.36 | 0 | 8.05 | 2543.97 | 1899.69 | 644.27 | 1849.82
3 | UG Primary, OH Secondaries and Services | 126.11 | 5.58 | 2531.09 | 0.47 | 4.36 | 0 | 8.05 | 2543.97 | 2315.42 | 228.55 | 2183.73
4 | Circuit Segment 2
5 | Covered Conductor Rebuild with EPSS and DCD | 46.19 | 26.12 | 55.02 | 0.81 | 73.43 | 3.57 | 74.97 | 207.8 | 116.18 | 91.62 | 43.86
6 | UG Primary, OH Secondaries and Services | 252.33 | 7.7 | 55.02 | 0.81 | 73.43 | 3.57 | 74.97 | 207.8 | 182.17 | 25.62 | -77.86

## TABLE RN-PG&E-23-07-1
TABLE RN-PG&E-23-07-1:
PLANNED FTI SCHEDULE OF ACTIVITIES 2023‑2025
Schedule | Activity
Q2 2023 | Implement pilot program in 4 AOCs(a) covering approximately 250 circuit segment miles(b) (in progress). As of June 30, we have completed 201 miles, which are pending validation.
Q3 and Q4 2023 | Evaluate learnings from pilot program and incorporate into 2024 FTI Program. Activities including updating the FTI procedure and incorporating improved functionality into VM system of record.
2024 | Within the Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees, barring external factors.
2024 | Re‑evaluate AOCs based on emerging data. Update to incorporate new data where appropriate.
Q1 2024 | Create record of all trees inspected, including those not requiring work, using Tree Risk Assessment form.
Q3 and Q4 2024 | Evaluate learnings from 2024 program and incorporate into 2025 FTI plans.
2025 | Within the Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees, barring external factors.
Q3 and Q4 2025 | Re‑evaluate AOCs based on emerging data. Update to incorporate new data where appropriate.
2025 | Evaluate learnings from FTI program and incorporate into 2026 FTI plans.
_______________
(a) The 2023 pilot program will take place in four AOCs: 1) North Coast Napa_AOC_03; 2) Sierra El Dorado_AOC_02; 3) North Valley Butte_AOC_02; and 4) Central Valley Calaveras_AOC_04.
(b) PG&E’s target for the 2023 FTI pilot program is 250 miles (VM‑03). To the extent that there are opportunities to do additional miles in 2023, PG&E will do so.

## TABLE RN-PG&E-23-07-2
TABLE RN-PG&E-23-07-2:
FTI PROGRAM TARGET 2023-2025
Target Name | Initiative Activity Tracking ID | Reference Section | 2023 Target & Unit | X% Risk Impact 2023 | 2024 Target & Unit | X% Risk Impact 2024 | 2025 Target & Unit | X% Risk Impact 2025 | Method of Verification
FTI | VM‑03, VM‑11 | 8.2.2.2.5 | 250 miles | <1% | 1,500 miles | <1% | 1,500 miles | <1% | Completed inspections in AOC

## TABLE RN-PG&E-23-07-3
TABLE RN-PG&E-23-07-3:
PROGRAM STRUCTURE PG&E, SCE, AND SDG&E
System | PG&E |  | SCE |  | SDG&E
| Program | Description | Program | Description | Program | Description
Distribution | Routine | Annual compliance inspections and trimming. Identify dead, dying, and declining trees that may fail. | Routine | Annual compliance inspections and trimming. | Detailed Inspection | Annual compliance inspections and trimming.
| Second Patrol | Patrols six months offset from routine patrol to maintain clearances and to identify dead, dying, and declining trees in the HFTD. | Cycle Buster | Patrol that occurs on a 6‑month cycle to identify vegetation that will not remain in compliance until the next annual inspection and identify hazard trees in HFRA. | Off‑Cycle Patrol | Second annual inspection activity in the HFTD. Similar to Detailed Inspection Program but focused on HFTD. Additional, off‑cycle patrols are also performed for Century plant and bamboo.
| Focused Tree Inventory | Focused inspections in Areas of Concern to address areas that have experienced higher volumes of vegetation damage. | Dead and Dying Tree Program | Patrol and identify dead and dying trees for removal.
| Vegetation Management for Operational Mitigations | Reduce outages and ignitions based on historic outage information. | Hazard Tree Program | Asses live trees posing a fall‑in risk.
| Tree Removal Inventory | Work down trees identified by the legacy Enhanced VM Program.
Transmission | Routine | Routine NERC and Non‑NERC inspection cycle including LiDAR inspection and ground patrol. | Same as Distribution programs |  | Same as Distribution programs
| Second Patrol | Aerial LiDAR inspection to assess tree growth.

## TABLE RN-PG&E-23-07-4
TABLE RN-PG&E-23-07-4:
TRI RESIDUAL RISK
Line No. | Description | No. of Units(a),(b) | MAVF Risk Points | Percent of Vegetation Risk
1 | All Removal Trees | 384930 | 686 | 7%
_______________
(a) This figure is as of February 2023. It represents the best estimate of the trees marked during the EVM Program that may remain in the field.
(b) This estimate will continue to be refined each year as the trees are visited to check if the trees have been removed by other programs or no longer pose a risk to PG&E facilities.

## TABLE RN-PG&E-23-07-5
TABLE RN-PG&E-23-07-5:
RISK REDUCTION OF EVM COMPARED TO FTI AND VMOM
Line No. | Scenario | Risk Points Reduced(a) | Annual Exposure | Annual Cost ($M) | $/Risk Point Reduced ($M) | Vegetation Risk Reduced
1 | EVM | 178 | 1,800 miles | 793.5 | 4.5 | 1.9%
2 | Total New VM Programs | 187 | 1,535 miles | 222.6 | 1.2 | 2%
3 | Focused Tree Inspections | 162 | 1,085 miles avg. | 198.3 | 1.2 | 1.7%
4 | VM Operational Mitigations | 26 | 450 miles avg.(b) | 24.3 | 1 | 0.3%
_______________
(a) Does not include the incremental risk reduction benefit from the improved Routine Inspection or Second Patrol procedures. PG&E estimates the improved procedures are 3 percent more effective at reducing risk than the legacy procedures.
(b) For the purposes of the risk calculation PG&E represented the annual VMOM work in number of miles. The average number of miles of exposure is based on the number of miles associated with EPSS outages that were patrolled and an estimated number of trees per mile. The 450 miles of average annual exposure does not represent a specific target or commitment for this program.

## TABLE E-1 REVISED
REVISED TABLE PG&E‑E‑1:
LIST OF REFERENCED CODES, REGULATIONS, STANDARDS, AND
OTHER REFERENCED DOCUMENTS
Category | Name of Regulation, Code or Standard | Brief Description | Link (if available)
California Legislation: | Assembly Bill 56 (Hill, 2011) | Gas corporations: rate recovery and expenditure: intrastate pipeline safety. | Bill Search (ca.gov)
California Code of Regulations (CCR): | Title 14, § 29300 | State regulation requiring regulated entities to notify the Office of a fault, outage, or other anomaly occurring within the vicinity of a fire or a wildfire threat that poses a danger to infrastructure. | California Code of Regulations
| Title 14, §§ 1250‑1258 | Provides specific exemptions from: electric pole and tower firebreak clearance and electric conductor clearance standards and to specify when the standards apply.
California Public Resources Code (PRC) Sections: | § 4291 | Forests, Forestry and Range and Forage Lands > Protection of Forest Range and Forage Lands > Mountainous, Forest‑, Brush‑ And Grass‑Covered Lands. | Codes: Codes Tree ‑ Public Resources Code ‑ PRC (ca.gov)
§ 4292
§ 4293
§ 4295.5
| § 4221 – 446 | Forests, Forestry and Range and Forage Lands > Protection of Forest Range and Forage Lands > Mountainous, Forest‑, Brush‑ And Grass‑Covered Lands > State Responsibility Area Fire Prevention Fees > Appeals Process
Applications before the California Public Utilities Commission (CPUC or Commission): | Application (A.) 20 06 012 | PG&E’s 2020 Risk Assessment and Mitigation Phase (RAMP) Report. | CPUC Proceeding Information (ca.gov)
| A.21‑06‑021 | PG&E’s Test Year 2023 General Rate Case (GRC) Application.
California Public Utilities (PUC) Code Sections: | § 768.6 | Requires that the Commission establish standards for disaster and emergency preparedness plans and for California electrical corporations to develop and update an emergency and disaster preparedness plan | Codes: Codes Tree ‑ Public Utilities Code ‑ PUC (ca.gov)
| § 8386 | Requires an electrical corporation to construct, maintain, and operate its electrical lines and equipment in a manner that will minimize the risk of catastrophic wildfire. Each electrical corporation shall submit a wildfire mitigation plan (WMP) to the Wildfire Safety Division for review and approval.
§ 8386(c)(18)
| § 956.5 | Owners and operators of intrastate transmission and distribution lines shall meet with local fire departments to discuss and review emergency plans.
CPUC Decisions | Decision (D.) 02‑04‑026 | Interim Opinion Regarding Phase 1 Issues – rulemaking on electric and gas baseline allowances. | Decision Search Form (ca.gov)
| D.05‑10‑044 | Interim Opinion Approving Various Emergency Program Changes Re: Anticipated High Natural Gas Prices In Winter 2005‑2006.
| D.06‑04‑055 | Decision Granting the Request of the Joint Utilities to Modify Requirements for Reporting Incidents Involving Trees or Other Vegetation in the Vicinity of Power Lines.
| D.09‑08‑029 | Decision in Phase 1 – Measures to Reduce Fire Hazards in California Before the 2009 Fall Fire Season.
| D.21‑06‑014 | Decision Addressing the Late 2019 Public Safety Power Shutoffs by PG&E, SCE, and SDG&E to Mitigate the Risk of Wildfire Caused by Utility Infrastructure.
| D.14‑02‑015 | Decision Adopting Regulations to Reduce the Fire Hazards Associated with Overhead (OH) Electric Utility Facilities and Aerial Communications Facilities.
| D.14‑12‑025 | Decision Incorporating a Risk‑Based Decision‑Making Framework into the Rate Case Plan and Modifying Appendix A of D.07‑07‑004.
| D.16‑01‑008 | Decision Updating the Annual Electric Reliability Reporting Requirements for California Electric Utilities.
| D.17‑01‑009 | Decision Adopting a Work Plan for the Development of Fire Map 2.
| D.17‑12‑024 | Decision Adopting Regulations to Enhance Fire Safety in The High Fire‑Threat District.
| D.18‑12‑014 | Phase Two Decision Adopting Safety Model Assessment Proceeding (S‑Map) Settlement Agreement with Modifications.
| D.19‑05‑042 | Adopting De‑Energization (Public Safety Power Shutoff (PSPS)) Guidelines(Ph. 1 Guidelines).
| D.19‑05‑037 | Decision on PG&E’s 2019 WMP Pursuant to Senate Bill (SB) 901.
| D.19‑05‑042 | Decision Adopting De‑Energization (PSPS) Guidelines (Phase 1 Guidelines).
| D.19‑07‑015 | Decision Adopting an Emergency Disaster Relief Program for Electric, Natural Gas, Water and Sewer Utility Customers.
| D.19‑09‑027 | Decision Establishing a Self‑Generating Incentive Program to Support the San Joaquin Valley Disadvantaged Community Pilot Projects
| D.20‑01‑021 | Self‑Generation Incentive Program Revisions Pursuant to Senate Bill 700 and Other Program Changes
| D.20‑03‑004 | Decision on Community Awareness and Public Outreach Before, During and After a Wildfire, and Explaining Next Steps for Other Phase 2 Issues.
| D.20‑05‑051 | Decision Adopting Phase 2 Guidelines For De‑Energization of Electric Facilities to Mitigate Wildfire Risk.
| D.20‑06‑003 | Phase I Decision Adopting Rules and Policy Changes to Reduce Residential Customer Disconnections for the Larger California‑Jurisdictional Energy Utilities.
| D.20‑06‑017 | Decision adopting short‑term actions to accelerate microgrid deployment and related resiliency solutions.
| D.20‑12‑030 | Direction Regarding Marketing and Outreach of the Disadvantaged Communities – Single‑Family Solar Homes.
| D.21‑05‑019 | Decision Addressing Phase II Issues Relating to Emergency and Disaster Preparedness Plans.
| D.21‑06‑014 | Decision Addressing the Late 2019 PSPS to Mitigate the Risk of Wildfire Caused by Utility Infrastructure.
| D.21‑06‑034 | Decision adopting Phase 3 revised and additional guidelines and rules for PSPS.
| D.21‑11‑009 | In the matter of the Application of Ting Telecom California for a Certificate of Public Convenience and Necessity to Provide Full Facilities‑Based and Resold Competitive Local Exchange Services Throughout the State of California.
| D.22‑10‑002 | Decision Resolving Litigated Issues for Southern California Edison Company’s Phase 2 GRC.
| D.22‑12‑027 | Phase II Decision Adopting Modifications to the Risk‑Based Decision‑Making Framework and Directing Environmental and Social Justice Pilots.
| D.22‑03‑008 | Decision Closing RAMP Proceeding.
| D.22‑10‑002 | Decision Addressing Phase I Tracks 3 And 4 Issues –OIR to Further Develop a Risk‑Based Decision‑Making Framework for Electric and Gas Utilities.
| D.22‑11‑033 | Decision Modifying D.02‑04‑026 Regarding Requirements to Remain Enrolled in Medical Baseline Program.
| Res. E‑5162 | Behind‑The‑Meter Microgrid Tariff Pursuant to D.21‑01‑018.
| Res. E‑5242 | Allows PG&E to offer Remote Grids as a sole standard service offering under certain conditions.
| GO 165 | Inspection cycles for electric distribution facilities
CPUC General Orders (GO): | GO 166 | Standards for Operation, Reliability, and Safety During Emergencies and Disasters. | CPUC General Orders (ca.gov)
| GO 174 | Rules for Electric Utility Substations.
| GO 95 | OH Electric Line Construction.
| Investigation (I.) 19‑06‑015 | OII on the Commission’s Motion into the Maintenance, Operations and Practices of PG&E with Respect to its Electric Facilities. Includes Envista Forensics Root Cause Analysis of 2017‑2018 Wildfires.
CPUC Investigations and Rulemakings: | R.08‑11‑005 | OIR to Revise and Clarify Commission Regulations Relating to the Safety of Electric Utility and Communications Infrastructure Provider Facilities. | Root Cause Analysis of the wildfires of 2017 and the Camp fire of 2018 (I.19‑06‑015)
| R.12‑11‑005 | Order Instituting Rulemaking Regarding Policies, Procedures and Rules for the California Solar Initiative, and Self‑Generation Initiative and Other Distributed Generation Issues. | Rulings Search Form (ca.gov)
| R.15‑06‑009 | OIR Regarding Policies, Procedures and Rules for Regulation of Physical Security for the Electric Supply Facilities and to Establish Standards for Disaster and Emergency Preparedness Plans.
| R.18‑12‑005 | Decision adopting phase 3 guidelines and rules for PSPS to mitigate wildfire risk caused by utility infrastructure. Includes Access and Functional Needs (AFN) quarterly progress reports.
| R.19‑09‑009 | OIR Regarding Microgrids Pursuant to SB 1339 and Resiliency Strategies.
| R.20‑07‑013 | OIR to Further Develop a Risk‑Based Decision‑Making Framework for Electric and Gas Utilities.
| ESRB‑4 (Agenda 13027) | Directs Investor‑Owned Electric Utilities to take remedial measures to reduce the likelihood of fires started by or threatening utility facilities.
CPUC Resolutions: | ESRB‑8 | Resolution extending de‑energizing reasonableness, notification, mitigation, and reporting requirements. | ESRB‑4
| Comprehensive Preparedness Guide (CPG) 101 | Developing and Maintaining Emergency Operations Plans (September 2021, V.3). | ESRB‑8
Federal Aviation Administration Rules | FAA Part 107 Rules | Airspace Authorizations rules for Drone pilots flying under the small Unmanned Aircraft Systems (UAS) Rule. | www.faa.gov
| FAA Part 91 Rules | General Operations regarding operations of private aircrafts.
Federal Emergency Management Agency Resources: | AL 4014G/5378 E | To revise Electric Rule 12 to allow customers to reestablish service under a prior rate schedule as part of our Emergency Consumer Protection Plan | CPG 101 Link
| AL 4145‑G/5643‑E | Revision to the Emergency Consumer Protection Plan under Gas and Electric Rule 1 | AL are available at: Advice Letters (pge.com)
PG&E Advice Letters (AL): | AL 4249 G/5827 E2 (PG&E ID U 39 M) | Budget AL
| AL 5918 E | Implementation Plan for Community Microgrid Enablement Program in Compliance with D.20‑06‑017
| AL 6623‑E | Remote Grids as Sole Standard Service Offering
| 2022 PG&E Community Resource Center Plan | 2022 PG&E Community Resource Center Plan
PG&E Communications, Comments, and Documents: | Company Emergency Response Plan (CERP) Annex Maintenance and Deadlines | CERP Annex Maintenance and Deadlines | Wildfire Mitigation Plan (pge.com)
| 2020 CERP Change Record | 2020 CERP Change Record
| EMER‑3001M | CERP (1/1/2023)
| EMER‑3002M | Electric Annex
| EMER‑3008M | Emergency Communication Annex to the CERP
| EMER‑3105M | Wildfire Annex
| EMER‑3106M | PSPS Annex
| 2022 Safety Outage Decision‑Making Guide | 2022 Safety Outage Decision‑Making Guide (Power Off for Safety)
| PSPS Event Notifications (October 2022) | PSPS Event Notifications (October 2022)
| PG&E GO 166 2020‑2021 Annual Compliance Report | Emergency Response Plan – GO 166 Compliance for the period July 1, 2020, through December 31, 2021.
| PG&E PSPS Report to the CPUC | Report to the CPUC, October 22‑24, 2022 (Weather Event Nov. 7, 2022) | PG&E GO 166 2020‑2021 Annual Compliance Report
| PG&E PSPS Policies and Procedures (Emergency Managers) | PG&E PSPS Policies and Procedures (Emergency Managers) | PSPS Report to CPUC
| PG&E (U 39 E) 2022 AFN Plan for PSPS Support | (1/31/2022) R.18‑12‑005, Filed 12/13‑2018 | Public Safety Power Shutoff Policies And Procedures Emergency Managers (pge.com)
| PG&E Independent Safety Monitor (ISM) Status Update Report | Outlines a scope of work that includes Filsinger Energy Partners, Inc. monitoring certain safety and risk aspects of PG&E’s electric and natural gas operations and infrastructure | PG&E’S Access and Functional Needs Plan for Public Safety Power Shutoff Support
| PG&E Removal Plan for Permanently Abandoned Transmission Facilities | Reports on PG&E’s plan to resolve the remedial actions and the resulting Administrative Consent Order regarding the 2019 Kinkade Fire. | PG&E Independent Safety Monitor Report (ca.gov)
| PG&E Multi Year Training and Exercise Plan 2023 2025 (MYTEP) | PG&E Multi Year Training and Exercise Plan 2023 2025 (MYTEP) | Wildfire Mitigation Plan (pge.com)
| PG&E 2020 RAMP Report | RAMP (Risk Assessment and Mitigation Phase) Report. | Wildfire Mitigation Plan (pge.com)
| PG&E 2022 WMP (Includes Revision Notice and Maturity Survey documents) | WMP (Wildfire Mitigation Plan) | 2020 RAMP Report
| PG&E 2023 GRC | General Rate Case: a state‑mandated process for investor‑owned electric and gas companies to request funding for distribution and generation costs. | PG&E 2022 WMP
| OH: Conductors 015073 | Vibration Damper Requirements for Various Types of OH Conductors | PG&E 2023 GRC
PG&E Utility Bulletins, Job Aids, Manuals, and Best Practices: | OH: Transmission 068177 | OH Transmission Line Design Criteria | Wildfire Mitigation Plan (pge.com)
| TD‑076253‑B005 | De Energized Operation of Inertia SCADA MSO
| TD‑1001M | Electric Transmission Preventive Maintenance Manual
| TD‑2305M‑JA02 | Job Aid: OH Assessment
| TD‑2700P‑06‑B001 | No Load Line Segment De‑Energization Process
| TD‑7102P‑01‑B026 | Enhanced Vegetation Management (VM) Transition to Distribution Routine Patrol
| TD‑7102P‑01‑JA01 | General Best Management Practices for All VM Activities
| TD‑7101M‑11 | Chainsaw Operation for VM
| TD‑7112P‑01‑JA01 | Fire Risk Assessment: Vegetation Control Pole Clearing
| TD‑7112P‑01‑JA02 | Pole Work Status Report Types
| TD‑8123M | Electric Distribution Preventive Maintenance Manual
| GOV‑6101P‑08 | Enterprise Corrective Action Program Procedure
PG&E Utility Procedures: | GOV‑6102P‑06 | Cause Evaluation Procedure | Wildfire Mitigation Plan (pge.com)
| GOV-7101S | Enterprise Records and Information Management Standard
| LAND‑4001P‑01 | Substation Fire Hardening
| LAND‑5201P‑01 | Power Generation Powerhouse and Switchyard Defensible Space
| PSPS‑1000P‑01 | PSPS for Transmission and Distribution
| RISK‑6305P‑01 | Electric Incident Reporting On‑Call Representative Procedure
| RISK‑6306P‑01 | Fire Incident Data Collection Plan and Reporting Procedure
| TD‑1001P‑13 | Enhanced Inspection and Maintenance Requirements for Diablo Canyon and Morro Bay Power Plants OH Transmission Facilities
| TD‑1001P‑14 | Infrared (IR) Inspection Procedures
| TD‑1003P‑01 | Management of Idle Electric Transmission Line Facilities Procedure
| TD‑1006P‑02 | Switch Maintenance and Inspection Program for Electric Transmission
| TD‑1470P‑01 | Attachment 1, Application Guide Device Profile Settings (Enhanced Powerline Safety Settings (EPSS)); Fast‑Tripping Scheme mode of device)
| TD‑2022P‑01 | Infrared (IR) Inspections of Electric Distribution Facilities
| TD‑2202P‑1 | EPSS‑Electric Operations (EO) Restoration Dispatch Requirements
| TD‑2302P‑05 | Electric Distribution Maintenance Requirements for Miscellaneous OH and Underground Equipment
| TD‑2325P‑01 | Intrusively Inspecting, Reinforcing, and Reusing Wood Poles
| TD‑2459P‑01 | Idle Facility Program
| TD‑3320P‑12 | Substation SAP Work Management System Process
| TD‑3328P‑01 | Development of the Annual Substation Supplemental Inspection Plan
| TD‑3350P‑10 | Substation Animal Abatement Measures
| TD‑2700P‑26 | EPSS and Patrol Process
| TD‑7103P‑02 | Transmission Orchard Patrol Procedure
| TD‑7103P‑04 | Transmission Integrated Vegetation Management Procedure
| TD‑7103P‑09 | VM Hazard Notification Procedure
| TD‑7102P‑01 | Distribution Routine Patrol Procedure (DRPP)Distribution Inspection Procedure (DIP)
| TD‑7102P‑17 | VM Priority Tag Procedure
| TD‑7102P‑23 | VM Second Patrol Procedure
| TD‑7103P‑01 | Transmission Non‑Orchard Routine Patrol Procedure
| TD‑7102P‑26 | Wood Management
| TD‑7112P‑01 | Vegetation Control Procedure
| TD‑8123P‑100 | Transmission Patrols and Enhanced Inspection Frequency Guidelines
| TD‑8123P‑101 | Transmission Line Corrective Notification Maintenance Strategy
| TD‑8123P‑103 | Electric Transmission Line Guidance for Setting Priority Codes
| TD‑1001S | Electric Transmission Line Inspection and Preventative Maintenance Program
PG&E Utility Standards: | TD‑7103S | Transmission Vegetation Management (TVM) Standard | Wildfire Mitigation Plan (pge.com)
| ENV‑10002S | Environmental Release to Construction for Environmental Evaluations
| TD‑1464S | Preventing and Mitigating Fires While Performing PG&E Work
| TD‑1470S | EPSS
| TD‑2305S | Electric Distribution Maintenance Requirements
| TD‑2321S | Guidance Document Analysis Avian Protection Plan
| TD‑2325S | Inspecting, Testing, and Maintaining Wood Poles
| TD‑3322S | Substation Equipment Maintenance Requirements
| TD‑3322S, Attachment 7 | Substation Equipment Maintenance Requirements; Circuit Breaker Maintenance Template
| TD‑3328S | Substation Supplemental Inspection Program
| TD‑7112S | Vegetation Control Program
| TD‑8124S | Detailed System Inspections Framework
| TD‑9212S | EO Asset Registry Governance
| EMER‑2001S | Company Emergency Response Plans Standard
| EMER‑7001S | Enhanced Customer and Community Support During All Hazards Standard
| TD‑7102‑01 | Vegetation Management Distribution Inspection Procedure
| TD‑7102P‑Att01 | Strategies to Manage and Reduce Palms
| TD‑7102P‑Att02 | EVM WMP Commitments
| TD‑7102P‑Att03 | Identifying Major Woody Stems
| TD‑7102P‑Att04 | Handling Stump Resprouts
| TD‑7102P‑Att05 | Bi‑Annual Tree Management and Reduction Strategy
| TD‑7102P‑Att06 | Tree Removal Inventory Program
| TD‑7102P‑Att07 | Focused Tree Inspection Procedures
| TD‑7102P‑Att08 | Vegetation Management Operational Mitigation Procedure
| TD‑7102S | Vegetation Management Program
| TD‑7114S | Vegetation Management Post Wildfire Standard
| ANSI A300 | American National Standards Institute A300 – Generally accepted industry standards for tree care practices
Third Party/Other Cited Materials: | Effectiveness of Covered Conductors: Failure Mode Identification and Literature Review | Covered Conductors Phase 1 Exponent Report (12/22/21) | ansi.org
| Effectiveness and Implementation Considerations of Covered Conductors: Testing and Analysis | Exponent: Joint‑IOU Covered Conductor Testing Cumulative Report (12/22/22) | Effectiveness of Covered Conductors: Failure Mode ID and Lit Review
| SFAC‑003‑4 TVM/ Federal Energy Regulatory Commission (FERC) Order# 777 | Standard Federal Agency Code: TVM to manage vegetation located on transmission rights of way (FERC). | Wildfire Mitigation Plan (pge.com)
| Intl. Organization for Standardization (ISO) 55001 | An asset management system standard, the main objective of which is to help organizations manage the lifecycle of assets more effectively | ferc.gov
| ISO 45001 and 14001 | ISO 14001 is the international standard for implementing an Environmental Management System. ISO 45001 focuses on managing Occupational Health and Safety concerns.
| Web Content Accessibility Guidelines (WCAG) 2.0 AA | WCAG 2.0 AA accessibility standards | ISO.org
| WCAG 2.1 AA | WCAG 2.1 AA accessibility standards | w3.org

## TABLE G-1 REVISED
TABLE G-1 (REVISED):
OTHER SUPPORTING DOCUMENTATION
Attachment Name | Brief Description
2023‑03-27_PGE_2023_WMP_R1_Section 6.4.2_Atch01 | Circuit Segment Level Workpaper
2023‑03‑27_PGE_2023_WMP_R0_Section 6.6.1_Atch01 | E3 Review of PG&E’s Wildfire Risk Model Version 3
2023‑03‑27_PGE_2023_WMP_R0_Section 8.2.3_Atch01_CONF | Targeted Tree Study (Confidential)
2023‑03‑27_PGE_2023_WMP_R0_Section 8.3.3_Atch01 | Location of Early Fault Detection, Distribution Fault Anticipation, and Line Sensor enabled circuits.
2023‑03‑27_PGE_2023_WMP_R0_Section 10_Atch01 | Relevant portions of Wildfire Risk Governance Committee Presentation, March 2, 2022
2023‑03‑27_PGE_2023_WMP_R0_Section 10_Atch02_CONF | Relevant portions of Wildfire Risk Governance Committee Presentation, June 6th, 2022 (Confidential)
2023‑03-27_PGE_2023_WMP_R1_Appendix C_Atch01 | Geospatial Database (zip file) of Map Layers referenced in Sections 5, 6, and 9
2023‑03‑27_PGE_2023_WMP_R0_Appendix D ACI PG&E‑22‑11_Atch01 | Joint IOU Covered Conductor Working Group Report
2023‑03‑27_PGE_2023_WMP_R0_Appendix D ACI PG&E‑22‑11_Atch02 | PG&E Covered Conductor Testing: Phase 2 Report
2023‑03-27_PGE_2023_WMP_R1_Appendix D ACI PG&E‑22‑16_Atch01_CONF | PG&E’s 2023‑2026 Undergrounding Workplan (Confidential)
2023‑03‑27_PGE_2023_WMP_R0_Appendix D ACI PG&E‑22‑32_Atch01_CONF | 2022 Reliability Study (Confidential)
2023‑08‑07_PGE_23‑04_RNR_R0_Atch01 | Status update on the number of backlog work orders since the start of 2023.
2023‑08‑07_PGE_23‑05_RNR_R0_Atch01 | Addressing circuit segments not included in PG&E’s 2023‑2026 Undergrounding workplan.
2023‑08‑07_PGE_23‑07_RNR_R0_Atch01 | List of information that will be digitally recorded in OneVM.
2023-09-27_PGE_23-05_SRNR_R0_Atch01_CONF | Comparative Analysis between Risk and Feasibility for Undergrounding
2023-09-27_PGE_23-05_SRNR_R0_Atch02 | Economic Analysis Software Package (EASOP) model
2023-09-27_PGE_23-05_SRNR_R0_Atch03_CONF | Mitigation Alternatives Analysis for 2023 and 2024 Projects

## TABLE H-1 REVISED
TABLE H-1 (REVISED):
LIST OF ACRONYMS
Acronym | Term/Definition
°F | degrees Fahrenheit
A. | Application
AAR | After Action Review
AB | Assembly Bill
ACE | Apparent Cause Evaluation
ACI | Areas for Continued Improvement
ACS | American Community Survey
ACSR | Aluminum Conductor Steel Reinforced
ADS | Atmospheric Data Solutions
AFL | Asset Feature List
AFN | Access and Functional Needs
AGA | American Gas Association
AGL | Above Ground Level
AI | Artificial Intelligence
AIC | Asset Information Collection
AKM | Asset Knowledge Management
AL | Advice Letter
ALJ | Administrative Law Judge
ALM | Application Life Cycle Management
ALP | Apprenticeship Line Program
AMP | Asset Management Plans
AMPS | Asset Management Platform and Services
ANSI | American National Standards Institute
AOC | Area of Concern
API | Application Programming Interface
AQL | Acceptable Quality Levels
ARC | Annual Report on Compliance
ARDQ | Asset Registry Data Quality
ASL | American Sign Language
ATLAS | Application Technology Lifecycle and Systems
ATS | Applied Technology Services
ATSDR | Agency for Toxic Substances and Disease Registry
AUC | Area Under the Curve
AWRR | Accelerated Wildfire Risk Reduction
AWS | Amazon Web Services
BLM | Bureau of Land Management
BMP | Best Management Practice
BPTM | Backup Power Transfer Meter
BTM | Behind‑The‑Meter
BTU | British Thermal Unit
BVLOS | Beyond Visual Line of Sight
CAIDI | Customer Average Interruption Duration Index
CAL FIRE | California Department of Forestry and Fire Protection
Cal OES | California Governor’s Office of Emergency Services
CALVEG | Classification and Assessment with Landsat of Visible Ecological Groupings
CAP | Corrective Action Program
CARE | California Alternate Rate for Energy
CBO | Community‑Based Organization
CC | Covered Conductor
CCA | Community Choice Aggregators
CCE | Common Cause Evaluation
CCR | California Code of Regulations
CDAO | Chief Data and Analytics Officer
CDC | Centers for Disease Control and Prevention
CDE | Critical Data Element
CDEC | California Data Exchange Center
CEMI | Customers Experiencing Multiple Interruptions
CERP | Company Emergency Response Plan
CESO | Customers Experiencing a Sustained Outage
CFB | Catastrophic Fire Behavior
cFCI | Communicating Faulted Circuit Indicator
CFI | Critical Facility and Infrastructure
CFP | Catastrophic Fire Probability
CGS | California Geological Survey
CHSC | Chaparral and Serotinous Conifers
CIL | Critical Infrastructure Lead
CL | Confidence Level
CMDB | Configuration Management Database
CMEP | Community Microgrid Enablement Program
CMI | Customer Minutes Interrupted
COL | Conclusion of Law
CoRE | Consequence of Risk Event
COSC | Coastal Sage Scrub
COVID‑19 | Coronavirus disease of 2019
CPG | Comprehensive Preparedness Guide
CPUC or Commission | California Public Utilities Commission
CPZ | Circuit Protection Zone
CRC | Community Resource Centers
CRESS | Corporate Real Estate Strategy and Services
CRT | Constraints Resolution Team
CSM | Clean Substation Microgrid
CSU | California State University
CUEA | California Utilities Emergency Association
CWSP | Community Wildfire Safety Program
D. | Decision
DAC‑AG | Disadvantaged Communities Advisory Group
DAHS | Distribution Asset Health Specialist
DASH | Dynamic Automated Seismic Hazard
DCC | Distribution Control Center
DCD | Downed Conductor Detection
DDAR | Disability Disaster Access and Resources
DEM | Digital Elevation Mode
DER | Distributed Energy Resource
DFA | Distribution Fault Anticipation
DFM | Dead Fuel Moisture
DIP | Distribution Inspection Procedure
DMCO | Dry Mixed Conifer
DMS | Distribution Management System
DOI | Department of the Interior
DTS‑FAST | Distribution, Transmission, and Substation: Fire Action Schemes and Technology
DX | Distribution
EASOP | Economic Analysis Software Package
EBMUD | East Bay Municipal Utility District
EC | Electric Corrective
EC | Emergency Operations Center Commander
ECCVM | Event Classification Through Current and Voltage Monitoring Sensors
EDEC | Electric Distribution Emergency Center
EDGIS | Electric Distribution Geographic Information System
EDMP | Enterprise Data Management Program
EDPM | Electric Distribution Preventive Maintenance
EDPM | Electric Distribution Procedure Manual
EEI | Edison Electric Institute
EF | Equivalent Fatalities
EFD | Early Fault Detection
EIA | Enhanced Ignition Analysis
EII | Electrical Incident Investigation
EIR | Electric Incident Reports
EN | European Norm
EO | Electric Operations
EOC | Emergency Operations Center
EORM | Enterprise and Operational Risk Management
EOY | End of Year
EP&R | Emergency Preparedness and Response
EPC | Engineering, Procurement, and Construction
EPIC | Electric Program Investment Charge
EPRI | Electric Power Research Institute
EPSS | Enhanced Powerline Safety Settings
ERM | Enterprise Risk Model
ERTC | Environmental Release to Construction
ESA | Energy Savings Assistance
ESGIS | Electric Substation Geographic Information System
ESJ | Environmental and Social Justice
ESRB | Electric Safety and Reliability Branch
ET | Electric Transmission
ETEC | Electric Transmission Emergency Center
ETGIS | Electric Transmission Geographic Information System
ETL | Electric Transmission Line
ETOR | Estimated Time of Restoration
ETPM | Electric Transmission Preventive Maintenance
EV | Expected Value
EVEG | Existing Vegetation Geodatabase (USFS geodatabase)
EVM | Enhanced Vegetation Management
F&A | Finance and Administration
FAA | Federal Aviation Administration
FAC | Federal Agency Code
FAN | Field Area Network
FBI | Fire Behavior Index
FDA | Facility Damage Action
FE | Functional Exercise
FEA | Finite Element Analysis
FEMA | Federal Emergency Management Agency
FERA | Family Electric Rate Assistance
FERC | Federal Energy Regulatory Commission
FGDB | File Geodatabase
FIA | Fire Index Area
FIRESCOPE | Firefighting Resources of California Organized for Potential Emergencies
FMEA | Failure Modes and Effects Analysis
FORCE | Field Operations Resource Calculation of Estimated Time of Restoration
FPI | Fire Potential Index
FPS | Fixed Power Solutions
FQC | Field Quality Control
FQCPM | Field Quality Control Program Manager
FRI | Fire Return Interval
FRID | Fire Return Interval Departure
FSE | Full‑Scale Exercise
FSR | Field Safety Reassessment
ft. | foot/feet
FTE | Full‑Time Employee
FTE | Full‑Time Equivalent
GC | General Construction
GE | General Electric Company
GEC | Gas Emergency Center
GED | General Educational Development Test
GHG | Greenhouse Gases
GIS | Geographic Information System
GO | General Order
GRC | General Rate Case
GRFO | Grasses and Forbes
HAT | Hazard Awareness Tool
HAWC | Hazard Awareness and Warning Center
HCP | Habitat Conservation Plan
HFRA | High Fire Risk Area
HFTD | High Fire Threat District
HR | Human Resources
HSEEP | Homeland Security Exercise Evaluation Program
HUD | Housing and Urban Development
HWW | High Wind Warning
I&I | Intelligence and Investigation
IAP | Incident Action Plan
IBEW | International Brotherhood of Electrical Workers
IC | Incident Commander
ICEA | Insulated Cable Engineers Association
ICS | Incident Command System
IFIR | Insufficient Fire Regime Information
IHSS | In‑Home Support Services
ILC | Independent Living Centers
IM | Instruction Memorandum
IMT | Incident Management Teams
iOS | IDevice Operating System
IOU | Investor‑Owned Utility
IPW | Ignition Probability Weather
IQA | Image Quality Assurance
IR | Infrared
ISA | International Society of Arboriculture
ISO | International Organization for Standardization
IT | Information Technology
IVM | Integrated Vegetation Management
IVR | Interactive Voice Recording
JATC | Joint Apprentice and Training Committee
JIS | Joint Information Systems
JIT | Just‑in‑Time
Km. | Kilometer
kV | Kilovolt
kV/in | kilovolts per inch
LBGIS | Landbase Geographic Information System
LEP | Limited English Proficiency
LFM | Live Fuel Moisture
LiDAR | Light Detection and Ranging
LIMA | Limited Area
LNO | Liaison Officers
LOB | Line of Business
LoRE | Likelihood of a Risk Event
LR | Line Reclosers
LRQA | Lloyd’s Register
M&C | Maintenance and Construction
m. | meter
MAA | Mutual Assistance Agreement
MADIS | Meteorological Assimilation Data Ingest System
MAVF | Multi‑Attribute Value Function
MBA | Master of Business Administration
MBL | Medical Baseline
MCMI | Million Customer Minutes Interrupted
MDR | Minimum Distance Requirement
MEA | MyElectronicAccess
MED | Major Event Days
MIEV | Mixed Evergreen
MIP | Microgrid Incentive Program
ML | Machine Learning
MMCO | Moist Mixed Conifer
MOA | Memorandum of Agreement
MOCH | Montane Chaparral
MOR | Multi Outage Review
MSO | Motorized Switch Operator
MYNN | Mellor Yamada Nakanishi‑Niino
MYTEP | Multi‑Year Training and Exercise Plan
NECA | National Electrical Contractors Association
NERC | North American Electric Reliability Corporation
NIMS | National Incident Management System
NMAP | Not Mapped by Existing Vegetation Geodatabase
NOAA | National Oceanic and Atmospheric Administration
NOD | Notice of Defect
NOV | Notice of Violation
NPFR | No Pre‑Euro‑American Settlement Fire Regime
NPS | National Park Service
NRM | Natural Resource Management
NTP | Near‑Term Process
NWS | National Weather Service
O&M | Operations and Maintenance
O2 | Oxygen Molecules
O3 | Ozone
OA | Operability Assessment
OAKW | Oak Woodland
OCM | Overhead Circuit Mile
OEC | Operations Emergency Center
OEIS or Energy Safety | Office of Energy Infrastructure Safety
OES | Office of Emergency Services
OH | Overhead
OIC | Officer‑in‑Charge
OII | Order Instituting Investigation
OIR | Order Instituting Rulemaking
OP | Ordering Paragraph
OPW | Outage Producing Wind
OSHA | Occupational Safety and Health Administration
Pf | Probability of Failure
PFR | Pre‑Euro‑American Settlement Fire Regime
PG | Power Generation
PG&E or the Company | Pacific Gas and Electric Company
PI | Pre‑Inspection
PI/TT | Pre‑Inspection/Tree Trimming
PIC | Potentially‑Impacted Customers
PIH | Pre‑installed Interconnection Hub
PIM | Pre‑Inspection Manager
PIO | Public Information Officer
PMD | Project Management Database
PMO | Project Management Office
PMP | Project Management Professional
POL | Privately Owned Lines
POMMS | PG&E Operational Mesoscale Modeling System
PRC | Public Resources Code
PSDR | Post Season Data Report
PSIP | PSPS Situational Intelligence Platform
PSPS | Public Safety Power Shutoff
PSS | Public Safety Specialist
PT&T | Pole Test and Treat
Pub. Util. Code or PUC | Public Utilities Code
PV | Partial Voltage
PWDAAC | People with Disabilities and Aging Advisory Council
QA | Quality Assurance
QA/QC | Quality Assurance/Quality Control
QA/WV | Quality Control/Work Verification
QAVM | Quality Assurance Vegetation Management
QC | Quality Control
QCR | Qualified Company Representative
QDR | Quarterly Data Report
QEW | Qualified Electrical Worker
QN | Quarterly Notification
QV | Quality Verification
QVVM | Quality Verification Vegetation Management
R&D | Research and Development
R. | Rulemaking
RAMP | Risk Assessment and Mitigation Phase
RAWS | Remote Automatic Weather Station
RBDF | Risk‑Based Decision‑Making Framework
RCA | Root Cause Analyses
RCAM | Redwood Coast Airport Microgrid
RCC | Risk and Compliance Committee
RCE | Root Cause Evaluations
REACH | Relief for Energy Assistance through Community Help
REC | Regional Emergency Center
REDW | Redwood
REFCL | Rapid Earth Fault Current Limiter
Res. | Resolution
RF | Radio Frequency
RFI | Request for Information
RFIR | Red Fir
RFP | Request for Proposal
RFW | Red Flag Warning
RFW OH | Red Flag Warning Overhead
RH | Relative humidity
RMWG | Risk Model Working Group
RN | Revision Notice
ROW | Right‑of‑Way
RPF | Registered Professional Forester
RSE | Risk Spend Efficiency
RT | Radiographic Testing
RW | Request for Work
SAP | Systems, Applications and Products
SCADA | Supervisory Control and Data Acquisition
SCE | Southern California Edison Company
SDG&E | San Diego Gas & Electric Company
SE | Strategy and Execution
SEB | State Executive Briefing
SED | Safety and Enforcement Division
SEMS | Standardized Emergency Management System
SFPE | Society of Fire Protection Engineers
SGIP | Self‑Generation Incentive Program
SI | System Inspection
SIPOC | Suppliers, Inputs, Processes, Outputs by Section and Customers
SIPT | Safety and Infrastructure Protection Teams
SIV | Self‑Identified Vulnerable
S‑MAP | Safety Model and Assessment Proceeding
SMB | Small and Medium Business
SME | Subject‑Matter Expert
SNO | Safety and Nuclear Oversight
SOPP | Storm Outage Prediction Model
SPS | Standalone Power System
sq. mi. | square miles
SQL | Structured Query Language
SRA | State Responsibility Area
SUP | NPS Special Use Permits
SVI | Social Vulnerability Index
SWRSE | Simplified Wildfire Risk Spend Efficiency
T&D | Transmission and Distribution
TAHS | Transmission Asset Health Specialist
TCCI | Tree‑Caused Circuit Interruption
TCM | Transmission Composite Model
THIRA | Threats and Hazards Identification and Risk Assessment
TIVM | Transmission Integrated Vegetation Management
TP | Time Places
TT | Tree Trimming
TTD | Telecommunications Device for the Deaf
TTS | Targeted Tree Species
TTX | Tabletop Exercises
TTY | Teletypewriter
TVM | Transmission Vegetation Management
TX | Transmission
U.S. | United States
UAT | User Acceptance Training
UCLA | University of California Los Angeles
UDS | Utility Defensible Space
UG | Underground
USFS | United States Forest Service
USGS | United States Geological Survey
VCT | Vegetation Control Technician
VGI | Vehicle Grid Integration
VIIRS | Visible Infrared Imaging Radiometer Suite
VM | Vegetation Management
VMARS | Vegetation Management Reporting and Analytic Server
VMD | Vegetation Management Database
VMI | Vegetation Management Inspector
VP | Vice President
WBT | Web Based Training
WCAG | Web Content Accessibility Guidelines
WDRM | Wildfire Distribution Risk Model
WECC | Western Electricity Coordinating Council
WEI | Western Energy Institute
WFC | Wildfire Consequence
WFE | Wildfire Feasibility Efficiency
WGE | Work Group Evaluations
WIV | Wildfire Incident Viewer
WMP | Wildfire Mitigation Plan
WMS | Work Management System
WOR | Weekly Operating Review
WRGSC | Wildfire Risk Governance Steering Committee
WRMAA | Western Regional Mutual Assistance Agreement
WRMAG | Western Region Mutual Assistance Group
WRO | Work Requested by Others
WRRM | Wildfire Risk Reduction Model
WS | Wind Speed
WSD | Wildfire Safety Division
WSIP | Wildfire Safety Inspection Program
WTRM | Wildfire Transmission Risk Model
WUI | Wildland‑Urban Interface
WV | Work Verification
YPIN | Yellow Pine