## 2023-2024 Summary
Based on 2023-04-06 Workplan
Final Recommendation based on Primary + Secondary Filter | 2023 |  |  | 2024
| Total | Underground | Overhead Harden | Total | Underground | Overhead Harden
Projects | 23 | 15 | 0 | 76 | 3 | 0
Miles | 39.7097 | 16.0148 | 0 | 361.878 | 1.34 | 0

## v3 Mitigation Alternatives
note: aligns with the Decision Framework shown in the prior EASOP Analysis
[30 empty] | Overhead Analysis | [5 empty] | Underground Analysis | [5 empty] | Primary Filter |  |  |  | Secondary Filter - Additional Considerations
Order | Category | MAT Code | SAP Status | Status | WMP GH-05 10k UG (Y/N) | Division | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (CPZ) (V2) | Risk Rank (V2) | Mean Risk (V2) | Circuit Protection Zone (CPZ) (V3) | Risk Rank (V3) | Mean Risk (V3) | HFTD Tier | Feasibility Score by CPZ | Total Planned UG Miles | UG - 2022 Complete | UG - 2023 Forecast | UG - 2024 Forecast | UG - 2025 Forecast | UG - 2026 Forecast | Mitigation Alternatives Analysis --> | Primary OH CPZ HF Miles | WDRM Total Risk Score | Overhead - Wildfire Risk Reduction | Overhead - Initial CapEx | Overhead - Capital Annual | Overhead - Expense Annual | Overhead - NPV | Overhead - $ per unit of risk (RSE) | Underground - Wildfire Risk Reduction | Underground - Initial CapEx | Underground - Capital Annual | Underground - Expense Annual | Underground - NPV | Underground - $ per unit of risk (RSE) | Primary Filter - Mitigation Recommendation | (1) PSPS Event Count (10 year) | (2) PSS Total Score Notes | (2) PSS Total Score | (3) Tree Strike Max Population | (3) Tree Strike Review for UG | (3) Tree Strike Review Notes | (3) Tree Strike UG Criteria T/F | 100% Buffer Trigger | Final Recommendation based on Primary + Secondary Filter
35374057 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 |  | 2170 | 0.0056711 |  | 1375 | 0.0011879 | Tier 2 | 1.7566 | 0.33996 | 0 | 0 | 0 | 0 | 0.33996 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 90 | 90 | 59 | N/A | 25/26 project not evaluated | FALSE | FALSE | #N/A
35367472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 |  | 780 | 0.0031904 | Tier 3 | 1.0202 | 4.29 | 0 | 0 | 0 | 4.29 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373630 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 8.5 | 0 | 0 | 0 | 0 | 8.5 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373629 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 5.76 | 0 | 0 | 0 | 0 | 5.76 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367501 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 4.54 | 0 | 0 | 0 | 0 | 4.54 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373626 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2701 | 0 | 0 | 0 | 0 | 6.2701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 134 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373625 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2201 | 0 | 0 | 0 | 0 | 6.2201 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 134 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373624 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 11.9201 | 0 | 0 | 0 | 11.9201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 134 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 7.2701 | 0 | 0 | 0 | 7.2701 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 134 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35390389 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 |  | 187 | 0.2644 |  | 531 | 0.0051015 | Tier 2 | 1.291 | 5.51 | 0 | 0 | 0 | 5.51 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35375091 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.6799 | 0 | 0 | 0 | 0 | 7.6799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | N/A | 25/26 project not evaluated | FALSE | FALSE | #N/A
35364020 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.5 | 0 | 0 | 0 | 0 | 7.5 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | N/A | 25/26 project not evaluated | FALSE | FALSE | #N/A
35376306 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35376304 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.45 | 0 | 0 | 0.45 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35376303 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374866 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374865 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374864 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374862 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374687 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 | 1.7655 | 0.45 | 0 | 0.45 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374686 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.59 | 0 | 1.59 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374685 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374684 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374683 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374682 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 2.45 | 0 | 2.45 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35374559 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.7 | 0 | 1.7 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35364022 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 |  | 2006 | 0.0089147 |  | 462 | 0.0060529 | Tier 2 | 1 | 2.4 | 0 | 0 | 0 | 2.4 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | N/A | 25/26 project not evaluated | FALSE | FALSE | #N/A
35374455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 & 3 | 1.1563 | 10 | 0 | 0 | 0 | 0 | 10 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 374 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35374454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1563 | 10 | 0 | 0 | 0 | 10 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 374 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35374444 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1563 | 8.66 | 0 | 0 | 0 | 8.66 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 374 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35396304 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 2.24 | 0 | 0 | 2.24 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 3.07 | 0 | 0 | 0 | 3.07 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.48 | 0 | 0 | 0 | 1.48 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373585 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.44 | 0 | 1.44 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367418 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 4.02 | 0 | 0 | 0 | 4.02 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35403554 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 2.95 | 0 | 0 | 0 | 0 | 2.95 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 168 | FALSE |  | FALSE | FALSE | #N/A
35403553 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 1.5299 | 0 | 0 | 0 | 0 | 1.5299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 168 | FALSE |  | FALSE | FALSE | #N/A
35403552 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 2.31 | 0 | 0 | 0 | 0 | 2.31 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 168 | FALSE |  | FALSE | FALSE | #N/A
35403551 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 1.25 | 0 | 0 | 0 | 0 | 1.25 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 168 | FALSE |  | FALSE | FALSE | #N/A
35367518 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 8.2201 | 0 | 0 | 8.2201 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 168 | FALSE |  | FALSE | FALSE | #N/A
35392114 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 |  | 2131 | 0.0064469 |  | 397 | 0.0070659 | Tier 3 | 1.2997 | 0.84905 | 0 | 0 | 0 | 0 | 0.84905 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 36 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35355173 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.52917 | 0 | 0 | 0.52917 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 85 | 85 | 341 | TRUE |  | TRUE | TRUE | #N/A
35355171 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.55814 | 0 | 0 | 0 | 0.55814 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 85 | 85 | 341 | TRUE |  | TRUE | TRUE | #N/A
35404753 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 3.74 | 0 | 0 | 3.74 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35385890 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.383 | 0 | 1.383 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35385889 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.453 | 0 | 0 | 2.453 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35385888 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35376888 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 7.2701 | 0 | 0 | 0 | 0 | 7.2701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373705 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 5.517 | 0 | 0 | 5.517 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367520 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373599 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 & 3 | 2.289 | 8.44 | 0 | 0 | 0 | 8.44 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 224 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367467 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 | 2.289 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 224 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35392113 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 3 | 1.5426 | 1.2197 | 0 | 0 | 0 | 1.2197 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35387916 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 2 & 3 | 1.5426 | 7.21 | 0 | 0 | 0 | 7.21 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35397456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.529 | 0 | 0 | 0 | 3.529 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35397455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.312 | 0 | 0 | 0 | 1.312 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35397454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.778 | 0 | 0 | 2.778 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35397453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 4.302 | 0 | 0 | 4.302 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35397452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.074 | 0 | 0 | 2.074 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396863 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.487 | 0 | 0 | 0 | 2.487 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396862 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.798 | 0 | 0 | 0 | 1.798 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396861 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.134 | 0 | 0 | 0 | 2.134 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396860 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.6 | 0 | 0 | 2.6 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.01 | 0 | 0 | 2.01 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.41 | 0 | 0 | 1.41 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396776 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.79 | 0 | 0 | 2.79 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35396775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.71 | 0 | 0 | 0 | 1.71 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35390288 | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 0.12973 | 0 | 0 | 0 | 0 | 0.12973 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373596 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.09 | 0 | 0 | 0 | 0 | 8.09 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373595 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.061 | 0 | 0 | 0 | 3.061 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373594 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 10.76 | 0 | 10.76 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373593 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.081 | 0 | 3.081 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373592 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 5.642 | 0 | 0 | 5.642 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373590 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.268 | 0 | 0 | 2.268 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35373589 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.1201 | 0 | 0 | 8.1201 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35367462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 4.653 | 0 | 0 | 4.653 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 29 | TRUE |  | TRUE | TRUE | #N/A
35382936 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 & 3 | 1.1825 | 5.26 | 0 | 0 | 0 | 5.26 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 120 | 120 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35382934 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 | 1.1825 | 6.04 | 0 | 0 | 0 | 6.04 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 120 | 120 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35379289 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 6.74 | 0 | 0 | 0 | 0 | 6.74 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35375453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 10.5875 | 0 | 0 | 0 | 10.5875 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35385801 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 |  | 1045 | 0.061762 |  | 290 | 0.0096296 | Tier 2 & 3 | 1.2149 | 6.1 | 0 | 0 | 0 | 0 | 6.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 120 | 120 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35401222 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.3201 | 0 | 0 | 0 | 0 | 4.3201 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35401221 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 3.1201 | 0 | 0 | 0 | 3.1201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35401220 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 2.64 | 0 | 0 | 0 | 2.64 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373598 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 9.91 | 0 | 0 | 0 | 0 | 9.91 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367466 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.1 | 0 | 0 | 0 | 0 | 4.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367475 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 |  | 2732 | 0.00051722 |  | 278 | 0.0099516 | Tier 3 | 1.1506 | 6.8875 | 0 | 0 | 0 | 0 | 6.8875 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 189 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35374562 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35374561 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35374459 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35374458 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 & 3 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35374457 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 8.75 | 0 | 0 | 8.75 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35374456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 10.19 | 0 | 0 | 10.19 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 117 | TRUE |  | TRUE | TRUE | #N/A
35350039 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 |  | 1288 | 0.040961 |  | 267 | 0.010152 | Tier 3 | 2.0187 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 135 | 135 | 0 | Fire Rebuild |  | TRUE | TRUE | Underground
35373588 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 9.31 | 0 | 0 | 0 | 0 | 9.31 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373587 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 9.7799 | 0 | 0 | 0 | 9.7799 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 12.41 | 0 | 0 | 0 | 0 | 12.41 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 153 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373706 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.45 | 0 | 0 | 0 | 0 | 12.45 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 477 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367522 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.09 | 0 | 0 | 0 | 12.09 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 477 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35397961 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.161 | 0 | 0 | 1.161 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35397960 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.222 | 0 | 0 | 2.222 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396905 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.481 | 0 | 0 | 0 | 0.481 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396904 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.848 | 0 | 0 | 0 | 0.848 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396903 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.957 | 0 | 0 | 0 | 1.957 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396902 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.575 | 0 | 0 | 0 | 2.575 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396900 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.418 | 0 | 0 | 0 | 1.418 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396878 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.74 | 0 | 0 | 0 | 1.74 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396877 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 4.262 | 0 | 0 | 0 | 4.262 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396876 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.725 | 0 | 0 | 0 | 1.725 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396875 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.705 | 0 | 0 | 2.705 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396874 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.965 | 0 | 0 | 2.965 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396871 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.703 | 0 | 0 | 0.703 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396870 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.619 | 0 | 0 | 1.619 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396869 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 3.618 | 0 | 0 | 3.618 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392777 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2611 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392776 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.76 | 0 | 0 | 0 | 1.76 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392774 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.59 | 0 | 0 | 0 | 1.59 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35392773 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2611 | 4.9 | 0 | 0 | 0 | 4.9 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373703 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.4 | 0 | 0 | 2.4 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373637 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.87 | 0 | 0 | 0 | 1.87 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373636 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.616 | 0 | 0 | 0.616 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 | 1.2611 | 2.27 | 0 | 0 | 0 | 2.27 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373581 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 6.7299 | 0 | 0 | 6.7299 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35373580 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.3799 | 0 | 0 | 0 | 0 | 8.3799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35373539 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.31 | 0 | 0 | 0 | 0 | 9.31 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35373538 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.24 | 0 | 0 | 0 | 8.24 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35373537 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.7 | 0 | 0 | 0 | 9.7 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35373536 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 10.3 | 0 | 0 | 10.3 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35367415 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 7.01 | 0 | 0 | 7.01 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 135 | 135 | 32 | TRUE |  | TRUE | TRUE | #N/A
35396760 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 0.92992 | 0 | 0 | 0 | 0 | 0.92992 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 180 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35396699 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.3701 | 0 | 0 | 0 | 0 | 3.3701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 180 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35396698 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.64 | 0 | 0 | 0 | 3.64 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 180 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 2 & 3 | 1.1915 | 12.7701 | 0 | 0 | 0 | 12.7701 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 180 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35418371 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 |  | 2142 | 0.0062159 |  | 231 | 0.011425 | Tier 2 | 1.4689 | 12.675 | 0 | 0 | 12.675 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35376889 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.7 | 0 | 0 | 0 | 13.7 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 1 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35367526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.5701 | 0 | 0 | 0 | 0 | 13.5701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 1 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35373051 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 |  | 1480 | 0.029281 |  | 212 | 0.01209 | Tier 3 | 2.6514 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 150 | 150 | 622 | Fire Rebuild |  | TRUE | TRUE | Underground
35367500 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 |  | 2060 | 0.0076984 |  | 211 | 0.01209 | Tier 3 | 1.137 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35404267 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 6.192 | 0 | 0 | 0 | 6.192 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 127 | TRUE |  | TRUE | TRUE | #N/A
35402641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.914 | 0 | 0 | 4.914 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 127 | TRUE |  | TRUE | TRUE | #N/A
35373635 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.888 | 0 | 0 | 4.888 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 127 | TRUE |  | TRUE | TRUE | #N/A
35367510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 9 | 0 | 0 | 9 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 127 | TRUE |  | TRUE | TRUE | #N/A
35403850 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.13 | 0 | 0 | 0 | 0 | 3.13 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35403849 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.31 | 0 | 0 | 0 | 0 | 4.31 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35403848 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.81 | 0 | 0 | 0 | 3.81 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35403847 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.39 | 0 | 0 | 0 | 4.39 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35382933 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.24 | 0 | 0 | 0 | 0 | 5.24 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35379382 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.28 | 0 | 0 | 0 | 5.28 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | N/A | 25/26 project not evaluated | FALSE | TRUE | #N/A
35375184 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375183 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375182 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375181 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375180 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 12.71 | 0 | 0 | 12.71 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35376642 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.06 | 0 | 0 | 0 | 0 | 9.06 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 597 | TRUE |  | TRUE | TRUE | #N/A
35376641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 8.2 | 0 | 0 | 0 | 8.2 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 597 | TRUE |  | TRUE | TRUE | #N/A
35376640 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.5 | 0 | 0 | 0 | 9.5 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 597 | TRUE |  | TRUE | TRUE | #N/A
35376556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 4.7 | 0 | 0 | 4.7 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 597 | TRUE |  | TRUE | TRUE | #N/A
35378690 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 4.46 | 0 | 0 | 0 | 0 | 4.46 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 198 | N/A |  | FALSE | TRUE | #N/A
35378688 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 10.89 | 0 | 0 | 0 | 0 | 10.89 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 198 | N/A |  | FALSE | TRUE | #N/A
35378687 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 8.84 | 0 | 0 | 0 | 8.84 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 198 | N/A |  | FALSE | TRUE | #N/A
35377437 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 7.19 | 0 | 0 | 0 | 7.19 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 198 | N/A |  | FALSE | TRUE | #N/A
35403556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.55 | 0 | 0 | 2.55 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35403555 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.172 | 0 | 0 | 3.172 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35399836 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 5.387 | 0 | 0 | 0 | 0 | 5.387 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35399835 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.342 | 0 | 0 | 0 | 0 | 2.342 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35399834 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.952 | 0 | 0 | 3.952 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35373526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.785 | 0 | 0 | 2.785 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35373525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.84 | 0 | 0 | 0 | 0 | 2.84 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35367476 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 4.52 | 0 | 0 | 4.52 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 1 | TRUE |  | TRUE | TRUE | #N/A
35382858 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 7.9701 | 0 | 0 | 7.9701 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375099 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375096 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 0 | 8.75 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375095 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35375094 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.9799 | 0 | 0 | 0 | 8.9799 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | NOT PSS REVIEWED | 0 | 0 | FALSE |  | FALSE | FALSE | #N/A
35373621 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 7.31 | 0 | 0 | 0 | 0 | 7.31 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35367470 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 6.71 | 0 | 0 | 0 | 0 | 6.71 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35383757 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 57 | N/A |  | FALSE | TRUE | #N/A
35383756 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 57 | N/A |  | FALSE | TRUE | #N/A
35383755 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 57 | N/A |  | FALSE | TRUE | #N/A
35383754 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 57 | N/A |  | FALSE | TRUE | #N/A
35383753 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 57 | N/A |  | FALSE | TRUE | #N/A
35373535 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 6.04 | 0 | 0 | 0 | 0 | 6.04 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 45 | N/A |  | FALSE | TRUE | #N/A
35373534 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 5.5701 | 0 | 0 | 0 | 5.5701 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 45 | N/A |  | FALSE | TRUE | #N/A
35367503 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 7.75 | 0 | 0 | 0 | 7.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 45 | N/A |  | FALSE | TRUE | #N/A
35374203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 |  | 73 | 0.37815 |  | 155 | 0.015172 | Tier 2 & 3 | 1.131 | 10.6299 | 0 | 0 | 0 | 10.6299 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35402643 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 2.4561 | 0 | 0 | 0 | 0 | 2.4561 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 29 | N/A |  | FALSE | TRUE | #N/A
35396761 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 4.64 | 0 | 0 | 0 | 0 | 4.64 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 29 | N/A |  | FALSE | TRUE | #N/A
35373707 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.3299 | 0 | 0 | 0 | 7.3299 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 29 | N/A |  | FALSE | TRUE | #N/A
35372460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.4299 | 0 | 0 | 0 | 0 | 7.4299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 29 | N/A |  | FALSE | TRUE | #N/A
35376305 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 3 | 1.6325 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild | FRRB does not use tree strike model for decision making. | TRUE | TRUE | Underground
35374863 | Fire Rebuild | 08W | ADER | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 2 | 1.6325 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 0 | Fire Rebuild | FRRB does not use tree strike model for decision making. | TRUE | TRUE | Underground
35367515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 |  | 2620 | 0.0010653 |  | 133 | 0.016045 | Tier 3 | 1.7779 | 6.6799 | 0 | 0 | 0 | 0 | 6.6799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 120 | 120 | 10 | N/A |  | FALSE | TRUE | #N/A
35375515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375514 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375512 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35375509 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 6.04 | 0 | 0 | 0 | 6.04 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 686 | TRUE |  | TRUE | TRUE | #N/A
35404716 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 6.96 | 0 | 0 | 6.96 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | FALSE |  | FALSE | TRUE | #N/A
35404715 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 8.65 | 0 | 0 | 8.65 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | FALSE |  | FALSE | TRUE | #N/A
35401013 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.15 | 0 | 0 | 0 | 3.15 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35401012 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.11 | 0 | 0 | 0 | 3.11 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35401011 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 2.46 | 0 | 0 | 0 | 2.46 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35397963 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.88 | 0 | 0 | 3.88 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35397962 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.2 | 0 | 0 | 4.2 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35382932 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4 | 0 | 0 | 0 | 4 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35379383 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.74 | 0 | 0 | 4.74 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35375721 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 3 | 1.1652 | 0.71004 | 0 | 0 | 0.71004 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35374681 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 150 | 150 | 219 | FALSE |  | FALSE | TRUE | #N/A
35373529 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.086 | 8.75 | 0 | 0 | 0 | 8.75 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 498 | TRUE |  | TRUE | TRUE | #N/A
35373528 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.086 | 8.75 | 0 | 0 | 8.75 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 498 | TRUE |  | TRUE | TRUE | #N/A
35373527 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.086 | 8.75 | 0 | 0 | 8.75 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 498 | TRUE |  | TRUE | TRUE | #N/A
35367412 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.086 | 8.19 | 0 | 0 | 0 | 8.19 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 498 | TRUE |  | TRUE | TRUE | #N/A
35374059 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 |  | 2349 | 0.0030208 |  | 118 | 0.016781 | Tier 2 | 1.2034 | 5.6701 | 0 | 0 | 0 | 5.6701 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 135 | 135 | 1 | N/A |  | FALSE | TRUE | #N/A
35377525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 6.9701 | 0 | 0 | 0 | 0 | 6.9701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 0 | N/A |  | FALSE | TRUE | #N/A
35375450 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.66 | 0 | 0 | 0 | 0 | 10.66 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 0 | N/A |  | FALSE | TRUE | #N/A
35375449 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.85 | 0 | 0 | 0 | 0 | 10.85 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 0 | N/A |  | FALSE | TRUE | #N/A
35379381 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 |  | 400 | 0.18021 |  | 115 | 0.016899 | Tier 2 & 3 | 1.4865 | 10.4 | 0 | 0 | 0 | 0 | 10.4 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 120 | 120 | 437 | N/A |  | FALSE | TRUE | #N/A
35396911 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.13 | 0 | 0 | 3.13 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396910 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.97 | 0 | 0 | 2.97 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396909 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.01 | 0 | 0 | 3.01 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396908 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.32 | 0 | 0 | 2.32 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373533 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.24 | 0 | 2.24 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367478 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.04 | 0 | 0 | 2.04 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 135 | 135 | 0 | TRUE |  | TRUE | TRUE | #N/A
35383305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 4.99 | 0 | 0 | 0 | 0 | 4.99 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35367524 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 14.3201 | 0 | 0 | 0 | 0 | 14.3201 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35373597 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.2339 | 5.0201 | 0 | 0 | 0 | 0 | 5.0201 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 105 | 105 | 76 | N/A |  | FALSE | TRUE | #N/A
35367464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.2339 | 9.0299 | 0 | 0 | 0 | 0 | 9.0299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 105 | 105 | 76 | N/A |  | FALSE | TRUE | #N/A
35404726 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.88 | 0 | 0 | 3.88 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404355 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.113 | 0 | 0 | 0 | 1.113 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404354 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 0.862 | 0 | 0 | 0 | 0.862 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404353 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.096 | 0 | 0 | 0 | 2.096 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404352 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.029 | 0 | 0 | 2.029 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404351 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.632 | 0 | 0 | 1.632 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373704 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.648 | 0 | 0 | 3.648 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367516 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.358 | 0 | 0 | 0 | 1.358 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35362666 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 |  | 2561 | 0.0014894 |  | 100 | 0.018211 | Tier 2 & 3 | 1.0129 | 0.67992 | 0 | 0 | 0 | 0 | 0.67992 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 120 | 120 | 237 | N/A |  | FALSE | TRUE | #N/A
35409203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 |  | 314 | 0.20636 |  | 99 | 0.018456 | Tier 2 & 3 | 1.0197 | 1.4 | 0 | 0 | 0 | 0 | 1.4 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35418379 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 |  | 2810 | 0.00026318 |  | 98 | 0.01848 | Tier 3 | 1.0041 | 8.4875 | 0 | 0 | 0 | 8.4875 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 25 | N/A |  | FALSE | TRUE | #N/A
35417148 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 8.56 | 0 | 0 | 0 | 0 | 8.56 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 59 | N/A |  | FALSE | TRUE | #N/A
35417144 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 10.7 | 0 | 0 | 0 | 0 | 10.7 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 59 | N/A |  | FALSE | TRUE | #N/A
35417117 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 6.04 | 0 | 0 | 0 | 6.04 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 59 | N/A |  | FALSE | TRUE | #N/A
35417110 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 9.57 | 0 | 0 | 0 | 9.57 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 59 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 2 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 8.975 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 2 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 8.975 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 2 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 2 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 2 | N/A |  | FALSE | TRUE | #N/A
35372463 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 |  | 2207 | 0.0049349 |  | 94 | 0.0187 | Tier 2 | 1.4879 | 1.99 | 0 | 0 | 0 | 0 | 1.99 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.3437 | 10.9 | 0 | 0 | 0 | 10.9 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 11 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.3437 | 15 | 0 | 0 | 0 | 0 | 15 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15 | 120 | 120 | 11 | N/A |  | FALSE | TRUE | #N/A
35395930 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.369 | 0 | 0 | 0 | 0 | 0.369 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35395929 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.057 | 0 | 0 | 0 | 0 | 0.057 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35395928 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 1.937 | 0 | 0 | 0 | 0 | 1.937 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35372464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 6.553 | 0 | 0 | 0 | 0 | 6.553 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35418356 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 |  | 2351 | 0.0030112 |  | 90 | 0.018786 | Tier 3 | 1.5 | 0.4 | 0 | 0 | 0.4 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 50 | 50 | 2 | FALSE |  | FALSE | FALSE | #N/A
35418366 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1253 | 6.062 | 0 | 0 | 0 | 6.062 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 6 | N/A |  | FALSE | TRUE | #N/A
35418361 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1253 | 6.601 | 0 | 0 | 0 | 0 | 6.601 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 120 | 120 | 6 | N/A |  | FALSE | TRUE | #N/A
35376559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 1.21 | 0 | 0 | 0 | 0 | 1.21 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 0 | N/A |  | FALSE | FALSE | #N/A
35376558 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 10.25 | 0 | 0 | 0 | 0 | 10.25 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 50 | 50 | 0 | N/A |  | FALSE | FALSE | #N/A
35373620 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 4.41 | 0 | 0 | 4.41 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 124 | TRUE |  | TRUE | TRUE | #N/A
35367468 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 6.65 | 0 | 0 | 6.65 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 135 | 135 | 124 | TRUE |  | TRUE | TRUE | #N/A
35383758 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 |  | 2247 | 0.0041901 |  | 80 | 0.019265 | Tier 3 | 1.5 | 10.8 | 0 | 0 | 0 | 10.8 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 20 | N/A |  | FALSE | TRUE | #N/A
35409211 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4743 | 3.3 | 0 | 0 | 3.3 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 105 | 105 | 0 | TRUE |  | TRUE | TRUE | #N/A
35409205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4743 | 15.2 | 0 | 0 | 0 | 0 | 15.2 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 105 | 105 | 0 | TRUE |  | TRUE | TRUE | #N/A
35391723 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
35391722 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
35391721 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
35391473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
35391472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.0799 | 0 | 0 | 10.0799 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
35391471 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.7201 | 0 | 0 | 10.7201 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 9 | TRUE |  | TRUE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.9152 | 8.788 | 0 | 0 | 0 | 8.788 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 43 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.9152 | 15 | 0 | 0 | 0 | 0 | 15 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 43 | N/A |  | FALSE | TRUE | #N/A
35409217 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 9.7 | 0 | 0 | 0 | 0 | 9.7 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 185 | N/A |  | FALSE | TRUE | #N/A
35409215 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 5.1 | 0 | 0 | 0 | 0 | 5.1 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 105 | 105 | 185 | N/A |  | FALSE | TRUE | #N/A
35373532 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 8.4701 | 0 | 0 | 8.4701 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35373530 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 15.51 | 0 | 0 | 0 | 0 | 15.51 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35367414 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 2 & 3 | 1.09 | 9.75 | 0 | 0 | 9.75 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | TRUE |  | TRUE | TRUE | #N/A
35404349 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.47 | 0 | 0 | 0 | 0 | 4.47 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 135 | 135 | 105 | N/A |  | FALSE | TRUE | #N/A
35376890 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 7.09 | 0 | 0 | 0 | 0 | 7.09 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 135 | 135 | 105 | N/A |  | FALSE | TRUE | #N/A
35372462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.85 | 0 | 0 | 0 | 0 | 4.85 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 135 | 135 | 105 | N/A |  | FALSE | TRUE | #N/A
35373628 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 8.7299 | 0 | 0 | 0 | 0 | 8.7299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35367504 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 9.35 | 0 | 0 | 0 | 0 | 9.35 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35418375 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 |  | 2670 | 0.0008147 |  | 60 | 0.021109 | Tier 3 | 1.0358 | 10.3875 | 0 | 0 | 0 | 10.3875 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 150 | 150 | 4 | N/A |  | FALSE | TRUE | #N/A
35385804 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 0 | 11.29 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35385803 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 11.29 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35418305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 0 | 8.65 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35418255 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 8.65 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35417127 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 4.9 | 0 | 0 | 0 | 4.9 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35364784 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 7.1701 | 0 | 0 | 0 | 0 | 7.1701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 361 | N/A |  | FALSE | TRUE | #N/A
35363720 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 9.59 | 0 | 0 | 0 | 9.59 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 361 | N/A |  | FALSE | TRUE | #N/A
35363559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 10.34 | 0 | 0 | 0 | 10.34 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 150 | 150 | 361 | N/A |  | FALSE | TRUE | #N/A
35409202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 |  | 915 | 0.078235 |  | 56 | 0.021686 | Tier 2 & 3 | 1.3284 | 1.2 | 0 | 0 | 0 | 0 | 1.2 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3333 | 150 | 150 | 107 | N/A |  | FALSE | TRUE | #N/A
35375452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 |  | 1710 | 0.017864 |  | 52 | 0.02211 | Tier 3 | 1.4588 | 6.9201 | 0 | 0 | 0 | 6.9201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.3333 | 105 | 105 | 98 | N/A |  | FALSE | TRUE | #N/A
35374570 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 |  | 658 | 0.11807 |  | 46 | 0.022999 | Tier 2 | 2.1181 | 7.2799 | 0 | 0 | 0 | 0 | 7.2799 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 30 | 30 | 0 | N/A |  | FALSE | FALSE | #N/A
35374569 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.51004 | 0 | 0 | 0 | 0 | 0.51004 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 120 | 120 | 183 | N/A |  | FALSE | TRUE | #N/A
35374567 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.43996 | 0 | 0 | 0 | 0 | 0.43996 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 120 | 120 | 183 | N/A |  | FALSE | TRUE | #N/A
35374566 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 0.11004 | 0 | 0 | 0 | 0 | 0.11004 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 120 | 120 | 183 | N/A |  | FALSE | TRUE | #N/A
35374564 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 6.79 | 0 | 0 | 0 | 0 | 6.79 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 120 | 120 | 183 | N/A |  | FALSE | TRUE | #N/A
35374563 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 7.21 | 0 | 0 | 0 | 0 | 7.21 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.6667 | 120 | 120 | 183 | N/A |  | FALSE | TRUE | #N/A
35374443 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7701 | 0 | 0 | 0 | 0 | 6.7701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35374208 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 4.89 | 0 | 0 | 0 | 0 | 4.89 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35374206 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 9.69 | 0 | 0 | 0 | 9.69 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35374205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.24 | 0 | 0 | 0 | 0 | 6.24 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35374204 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7201 | 0 | 0 | 0 | 0 | 6.7201 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 0 | N/A |  | FALSE | TRUE | #N/A
35377520 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 |  | 328 | 0.19983 |  | 38 | 0.024501 | Tier 3 | 1.0078 | 3.9701 | 0 | 0 | 0 | 0 | 3.9701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 150 | 150 | 54 | N/A |  | FALSE | TRUE | #N/A
35374202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 4.6701 | 0 | 0 | 0 | 0 | 4.6701 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 120 | 120 | 40 | N/A |  | FALSE | TRUE | #N/A
35374200 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 8.04 | 0 | 0 | 0 | 0 | 8.04 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 120 | 120 | 40 | N/A |  | FALSE | TRUE | #N/A
35385806 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 6.69 | 0 | 0 | 0 | 0 | 6.69 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35385805 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 10.74 | 0 | 0 | 0 | 0 | 10.74 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 |  | 178 | 0.2712 |  | 32 | 0.025831 | Tier 3 | 1.5506 | 15.1375 | 0 | 0 | 15.1375 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 150 | 150 | 0 | FALSE |  | FALSE | TRUE | #N/A
35409213 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 |  | 1422 | 0.032289 |  | 30 | 0.025967 | Tier 2 | 1.0982 | 4.7299 | 0 | 0 | 4.7299 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3333 | 150 | 150 | 90 | TRUE |  | TRUE | TRUE | #N/A
35367335 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 9.7201 | 0 | 0 | 0 | 9.7201 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 148 | N/A |  | FALSE | TRUE | #N/A
35365064 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 10.34 | 0 | 0 | 0 | 0 | 10.34 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 120 | 120 | 148 | N/A |  | FALSE | TRUE | #N/A
35373634 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 4.4299 | 0 | 0 | 0 | 0 | 4.4299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35373632 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 10.2299 | 0 | 0 | 0 | 0 | 10.2299 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35367508 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 5.94 | 0 | 0 | 0 | 0 | 5.94 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35367507 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 3.04 | 0 | 0 | 0 | 0 | 3.04 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.3333 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35385802 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 |  | 377 | 0.18755 |  | 15 | 0.034099 | Tier 3 | 1.3819 | 9.6 | 0 | 0 | 0 | 0 | 9.6 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 120 | 120 | 484 | N/A |  | FALSE | TRUE | #N/A
35376891 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 |  | 1235 | 0.044601 |  | 14 | 0.034265 | Tier 3 | 1.3391 | 4.4 | 0 | 0 | 0 | 0 | 4.4 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.6667 | 150 | 150 | 297 | N/A |  | FALSE | TRUE | #N/A
35373708 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4721 | 3.73 | 0 | 0 | 0 | 0 | 3.73 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35372465 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4721 | 11.84 | 0 | 0 | 0 | 0 | 11.84 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35372258 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 8.892 | 0 | 0 | 0 | 0 | 8.892 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35372257 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 9.808 | 0 | 0 | 0 | 0 | 9.808 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.6667 | 150 | 150 | 0 | N/A |  | FALSE | TRUE | #N/A
35372461 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 |  | 1744 | 0.016801 |  | 8 | 0.040941 | Tier 2 & 3 | 1.5 | 4.42 | 0 | 0 | 4.42 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.6667 | 120 | 120 | 0 | TRUE |  | TRUE | TRUE | #N/A
35396763 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 0.88 | 0 | 0 | 0 | 0 | 0.88 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 75 | N/A |  | FALSE | TRUE | #N/A
35396762 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.91 | 0 | 0 | 0 | 0 | 2.91 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 75 | N/A |  | FALSE | TRUE | #N/A
35372259 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.84 | 0 | 0 | 0 | 0 | 2.84 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | 105 | 105 | 75 | N/A |  | FALSE | TRUE | #N/A
#N/A
#N/A
#N/A

## PG&E UG Workplan 2023-26_ERRATA
PG&E 2023-2026 Undergrounding Workplan
Data as of January 3, 2023
[21 empty] | 2697.1635 | 10.6458 | 534.3408 | 588.2466 | 682.9839 | 880.9464
Order | Category | MAT Code | SAP Status | Status | WMP GH-05 10k UG (Y/N) | Division | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (CPZ) (V2) | Risk Rank (V2) | Mean Risk (V2) | Circuit Protection Zone (CPZ) (V3) | Risk Rank (V3) | Mean Risk (V3) | HFTD Tier | Feasibility Score by CPZ | Total Planned UG Miles | UG - 2022 Complete | UG - 2023 Forecast | UG - 2024 Forecast | UG - 2025 Forecast | UG - 2026 Forecast
35311627 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 2.05 | 0 | 0 | 0 | 2.05 | 0
35374057 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 |  | 2170 | 0.0056711 |  | 1375 | 0.0011879 | Tier 2 | 1.7566 | 0.33996 | 0 | 0 | 0 | 0 | 0.33996
35367472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 |  | 780 | 0.0031904 | Tier 3 | 1.0202 | 4.29 | 0 | 0 | 0 | 4.29 | 0
35373630 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 8.5 | 0 | 0 | 0 | 0 | 8.5
35373629 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 5.76 | 0 | 0 | 0 | 0 | 5.76
35367501 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 4.54 | 0 | 0 | 0 | 0 | 4.54
35373626 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2701 | 0 | 0 | 0 | 0 | 6.2701
35373625 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2201 | 0 | 0 | 0 | 0 | 6.2201
35311626 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3.64 | 0 | 0 | 0 | 3.64 | 0
35311596 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3 | 0 | 0 | 0 | 3 | 0
35286103 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3.0701 | 0 | 0 | 0 | 3.0701 | 0
35373624 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 11.9201 | 0 | 0 | 0 | 11.9201 | 0
35367473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 7.2701 | 0 | 0 | 0 | 7.2701 | 0
35390389 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 |  | 187 | 0.2644 |  | 531 | 0.0051015 | Tier 2 | 1.291 | 5.51 | 0 | 0 | 0 | 5.51 | 0
35375091 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.6799 | 0 | 0 | 0 | 0 | 7.6799
35364020 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35376306 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0
35376304 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.45 | 0 | 0 | 0.45 | 0 | 0
35376303 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0
35374866 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35374865 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0
35374864 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0
35374862 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0
35374687 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 | 1.7655 | 0.45 | 0 | 0.45 | 0 | 0 | 0
35374686 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.59 | 0 | 1.59 | 0 | 0 | 0
35374685 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35374684 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0
35374683 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35374682 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 2.45 | 0 | 2.45 | 0 | 0 | 0
35374559 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.7 | 0 | 1.7 | 0 | 0 | 0
35364022 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 |  | 2006 | 0.0089147 |  | 462 | 0.0060529 | Tier 2 | 1 | 2.4 | 0 | 0 | 0 | 2.4 | 0
35374455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 & 3 | 1.1563 | 10 | 0 | 0 | 0 | 0 | 10
35329471 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 |  | 3243 | 5.43e-06 |  | 1561 | 0.00090896 | Tier 2 | 1.0955 | 1.55 | 0 | 1.55 | 0 | 0 | 0
35374454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1563 | 10 | 0 | 0 | 0 | 10 | 0
35374444 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1563 | 8.66 | 0 | 0 | 0 | 8.66 | 0
35396304 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 2.24 | 0 | 0 | 2.24 | 0 | 0
35392779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 3.07 | 0 | 0 | 0 | 3.07 | 0
35392778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.48 | 0 | 0 | 0 | 1.48 | 0
35373585 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.44 | 0 | 1.44 | 0 | 0 | 0
35367418 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 4.02 | 0 | 0 | 0 | 4.02 | 0
35403554 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 2.95 | 0 | 0 | 0 | 0 | 2.95
35403553 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 1.5299 | 0 | 0 | 0 | 0 | 1.5299
35403552 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 2.31 | 0 | 0 | 0 | 0 | 2.31
35403551 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 1.25 | 0 | 0 | 0 | 0 | 1.25
35367518 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1971 | 8.2201 | 0 | 0 | 8.2201 | 0 | 0
35392114 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 |  | 2131 | 0.0064469 |  | 397 | 0.0070659 | Tier 3 | 1.2997 | 0.84905 | 0 | 0 | 0 | 0 | 0.84905
35355173 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.52917 | 0 | 0 | 0.52917 | 0 | 0
35355171 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.55814 | 0 | 0 | 0 | 0.55814 | 0
35404753 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 3.74 | 0 | 0 | 3.74 | 0 | 0
35385890 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.383 | 0 | 1.383 | 0 | 0 | 0
35385889 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.453 | 0 | 0 | 2.453 | 0 | 0
35385888 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0
35376888 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 7.2701 | 0 | 0 | 0 | 0 | 7.2701
35373705 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 5.517 | 0 | 0 | 5.517 | 0 | 0
35367520 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0
35373599 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 & 3 | 2.289 | 8.44 | 0 | 0 | 0 | 8.44 | 0
35367467 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 | 2.289 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35392113 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 3 | 1.5426 | 1.2197 | 0 | 0 | 0 | 1.2197 | 0
35387916 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 2 & 3 | 1.5426 | 7.21 | 0 | 0 | 0 | 7.21 | 0
35397456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.529 | 0 | 0 | 0 | 3.529 | 0
35397455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.312 | 0 | 0 | 0 | 1.312 | 0
35397454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.778 | 0 | 0 | 2.778 | 0 | 0
35397453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 4.302 | 0 | 0 | 4.302 | 0 | 0
35397452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.074 | 0 | 0 | 2.074 | 0 | 0
35326790 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0.00050684 | Tier 2 | 1.5 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0
35396863 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.487 | 0 | 0 | 0 | 2.487 | 0
35396862 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.798 | 0 | 0 | 0 | 1.798 | 0
35396861 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.134 | 0 | 0 | 0 | 2.134 | 0
35396860 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.6 | 0 | 0 | 2.6 | 0 | 0
35396779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.01 | 0 | 0 | 2.01 | 0 | 0
35396778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.41 | 0 | 0 | 1.41 | 0 | 0
35396776 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.79 | 0 | 0 | 2.79 | 0 | 0
35396775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.71 | 0 | 0 | 0 | 1.71 | 0
35390288 | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 0.12973 | 0 | 0 | 0 | 0 | 0.12973
35373596 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.09 | 0 | 0 | 0 | 0 | 8.09
35373595 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.061 | 0 | 0 | 0 | 3.061 | 0
35373594 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 10.76 | 0 | 10.76 | 0 | 0 | 0
35373593 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.081 | 0 | 3.081 | 0 | 0 | 0
35373592 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 5.642 | 0 | 0 | 5.642 | 0 | 0
35373590 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.268 | 0 | 0 | 2.268 | 0 | 0
35373589 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.1201 | 0 | 0 | 8.1201 | 0 | 0
35367462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 4.653 | 0 | 0 | 4.653 | 0 | 0
35382936 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 & 3 | 1.1825 | 5.26 | 0 | 0 | 0 | 5.26 | 0
35382934 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 | 1.1825 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35379289 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 6.74 | 0 | 0 | 0 | 0 | 6.74
35375453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 10.5875 | 0 | 0 | 0 | 10.5875 | 0
35385801 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 |  | 1045 | 0.061762 |  | 290 | 0.0096296 | Tier 2 & 3 | 1.2149 | 6.1 | 0 | 0 | 0 | 0 | 6.1
35401222 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.3201 | 0 | 0 | 0 | 0 | 4.3201
35401221 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 3.1201 | 0 | 0 | 0 | 3.1201 | 0
35401220 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 2.64 | 0 | 0 | 0 | 2.64 | 0
35373598 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 9.91 | 0 | 0 | 0 | 0 | 9.91
35367466 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.1 | 0 | 0 | 0 | 0 | 4.1
35367475 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 |  | 2732 | 0.00051722 |  | 278 | 0.0099516 | Tier 3 | 1.1506 | 6.8875 | 0 | 0 | 0 | 0 | 6.8875
35374562 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35374561 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35374459 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35374458 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 & 3 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35374457 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35374456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 10.19 | 0 | 0 | 10.19 | 0 | 0
35350039 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 |  | 1288 | 0.040961 |  | 267 | 0.010152 | Tier 3 | 2.0187 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0
35373588 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 9.31 | 0 | 0 | 0 | 0 | 9.31
35373587 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 9.7799 | 0 | 0 | 0 | 9.7799 | 0
35367460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3287 | 12.41 | 0 | 0 | 0 | 0 | 12.41
35373706 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.45 | 0 | 0 | 0 | 0 | 12.45
35367522 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.09 | 0 | 0 | 0 | 12.09 | 0
35397961 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.161 | 0 | 0 | 1.161 | 0 | 0
35397960 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.222 | 0 | 0 | 2.222 | 0 | 0
35396905 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.481 | 0 | 0 | 0 | 0.481 | 0
35396904 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.848 | 0 | 0 | 0 | 0.848 | 0
35396903 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.957 | 0 | 0 | 0 | 1.957 | 0
35396902 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.575 | 0 | 0 | 0 | 2.575 | 0
35396900 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.418 | 0 | 0 | 0 | 1.418 | 0
35396878 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.74 | 0 | 0 | 0 | 1.74 | 0
35396877 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 4.262 | 0 | 0 | 0 | 4.262 | 0
35396876 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.725 | 0 | 0 | 0 | 1.725 | 0
35396875 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.705 | 0 | 0 | 2.705 | 0 | 0
35396874 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.965 | 0 | 0 | 2.965 | 0 | 0
35396871 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.703 | 0 | 0 | 0.703 | 0 | 0
35396870 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.619 | 0 | 0 | 1.619 | 0 | 0
35396869 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 3.618 | 0 | 0 | 3.618 | 0 | 0
35392777 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2611 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0
35392776 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0
35392775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.76 | 0 | 0 | 0 | 1.76 | 0
35392774 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.59 | 0 | 0 | 0 | 1.59 | 0
35392773 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2611 | 4.9 | 0 | 0 | 0 | 4.9 | 0
35373703 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 2.4 | 0 | 0 | 2.4 | 0 | 0
35373637 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 1.87 | 0 | 0 | 0 | 1.87 | 0
35373636 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2611 | 0.616 | 0 | 0 | 0.616 | 0 | 0
35367513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 | 1.2611 | 2.27 | 0 | 0 | 0 | 2.27 | 0
35373581 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 6.7299 | 0 | 0 | 6.7299 | 0 | 0
35373580 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.3799 | 0 | 0 | 0 | 0 | 8.3799
35373539 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.31 | 0 | 0 | 0 | 0 | 9.31
35373538 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.24 | 0 | 0 | 0 | 8.24 | 0
35373537 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.7 | 0 | 0 | 0 | 9.7 | 0
35373536 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 10.3 | 0 | 0 | 10.3 | 0 | 0
35367415 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 7.01 | 0 | 0 | 7.01 | 0 | 0
35396760 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 0.92992 | 0 | 0 | 0 | 0 | 0.92992
35396699 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.3701 | 0 | 0 | 0 | 0 | 3.3701
35396698 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.64 | 0 | 0 | 0 | 3.64 | 0
35367511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 2 & 3 | 1.1915 | 12.7701 | 0 | 0 | 0 | 12.7701 | 0
35418371 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 |  | 2142 | 0.0062159 |  | 231 | 0.011425 | Tier 2 | 1.4689 | 12.675 | 0 | 0 | 12.675 | 0 | 0
35376889 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.7 | 0 | 0 | 0 | 13.7 | 0
35367526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.5701 | 0 | 0 | 0 | 0 | 13.5701
35312546 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8933 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0.00050684 | Tier 2 | 1.5 | 1.0131 | 0 | 0 | 1.0131 | 0 | 0
35373051 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 |  | 1480 | 0.029281 |  | 212 | 0.01209 | Tier 3 | 2.6514 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0
35367500 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 |  | 2060 | 0.0076984 |  | 211 | 0.01209 | Tier 3 | 1.137 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299
35404267 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 6.192 | 0 | 0 | 0 | 6.192 | 0
35402641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.914 | 0 | 0 | 4.914 | 0 | 0
35373635 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.888 | 0 | 0 | 4.888 | 0 | 0
35367510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 9 | 0 | 0 | 9 | 0 | 0
35403850 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.13 | 0 | 0 | 0 | 0 | 3.13
35403849 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.31 | 0 | 0 | 0 | 0 | 4.31
35403848 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.81 | 0 | 0 | 0 | 3.81 | 0
35403847 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.39 | 0 | 0 | 0 | 4.39 | 0
74001486 | Other | 30A | PEND | Permitting/Dependency | Y | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | WDRM v2 |  | 2792 | 0.00031068 |  | 2633 | 0.00025777 | Tier 2 & 3 | 1.3014 | 1.4576 | 0 | 0 | 1.4576 | 0 | 0
35094513 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 |  | 2712 | 0.00058985 |  | 1583 | 0.00088659 | Tier 3 | 1.2428 | 0.053977 | 0.053977 | 0 | 0 | 0 | 0
35237937 | Other | 2BP | UNSC | Ready for Construction | Y | CC | Region 4 - Central Coast | Soquel | Santa Cruz | 37.0341 | -121.9738 | WDRM v2 |  | 2595 | 0.0012326 |  | 1319 | 0.0013011 | Tier 3 | 1.1955 | 0.015341 | 0 | 0 | 0 | 0.015341 | 0
35342333 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0.0018854 | Tier 3 | 2.023 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0
35382933 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.24 | 0 | 0 | 0 | 0 | 5.24
35379382 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.28 | 0 | 0 | 0 | 5.28 | 0
35375184 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375183 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375182 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375181 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375180 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.162 | 12.71 | 0 | 0 | 12.71 | 0 | 0
35376642 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.06 | 0 | 0 | 0 | 0 | 9.06
35378609 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.7 | 0 | 0.7 | 0 | 0 | 0
35376641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 8.2 | 0 | 0 | 0 | 8.2 | 0
35376640 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.5 | 0 | 0 | 0 | 9.5 | 0
35376556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 4.7 | 0 | 0 | 4.7 | 0 | 0
35378690 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 4.46 | 0 | 0 | 0 | 0 | 4.46
35378688 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 10.89 | 0 | 0 | 0 | 0 | 10.89
35378687 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 8.84 | 0 | 0 | 0 | 8.84 | 0
35377437 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 7.19 | 0 | 0 | 0 | 7.19 | 0
35403556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.55 | 0 | 0 | 2.55 | 0 | 0
35403555 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.172 | 0 | 0 | 3.172 | 0 | 0
35399836 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 5.387 | 0 | 0 | 0 | 0 | 5.387
35399835 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.342 | 0 | 0 | 0 | 0 | 2.342
35399834 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.952 | 0 | 0 | 3.952 | 0 | 0
35373526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.785 | 0 | 0 | 2.785 | 0 | 0
35373525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.84 | 0 | 0 | 0 | 0 | 2.84
35367476 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 4.52 | 0 | 0 | 4.52 | 0 | 0
35382858 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 7.9701 | 0 | 0 | 7.9701 | 0 | 0
35375099 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375096 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375095 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375094 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1341 | 8.9799 | 0 | 0 | 0 | 8.9799 | 0
35373621 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 7.31 | 0 | 0 | 0 | 0 | 7.31
35367470 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 6.71 | 0 | 0 | 0 | 0 | 6.71
35383757 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35383756 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35383755 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0
35383754 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0
35383753 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35373535 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 6.04 | 0 | 0 | 0 | 0 | 6.04
35373534 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 5.5701 | 0 | 0 | 0 | 5.5701 | 0
35367503 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 7.75 | 0 | 0 | 0 | 7.75 | 0
35374203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 |  | 73 | 0.37815 |  | 155 | 0.015172 | Tier 2 & 3 | 1.131 | 10.6299 | 0 | 0 | 0 | 10.6299 | 0
35402643 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 2.4561 | 0 | 0 | 0 | 0 | 2.4561
35396761 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 4.64 | 0 | 0 | 0 | 0 | 4.64
35373707 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.3299 | 0 | 0 | 0 | 7.3299 | 0
35372460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.4299 | 0 | 0 | 0 | 0 | 7.4299
35376305 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 3 | 1.6325 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0
35374863 | Fire Rebuild | 08W | ADER | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 2 | 1.6325 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0
35367515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 |  | 2620 | 0.0010653 |  | 133 | 0.016045 | Tier 3 | 1.7779 | 6.6799 | 0 | 0 | 0 | 0 | 6.6799
35375515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35375514 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35375513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0
35375512 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0
35375511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0
35375510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0
35375509 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35404716 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 6.96 | 0 | 0 | 6.96 | 0 | 0
35404715 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 8.65 | 0 | 0 | 8.65 | 0 | 0
35401013 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.15 | 0 | 0 | 0 | 3.15 | 0
35401012 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.11 | 0 | 0 | 0 | 3.11 | 0
35401011 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 2.46 | 0 | 0 | 0 | 2.46 | 0
35397963 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.88 | 0 | 0 | 3.88 | 0 | 0
35397962 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.2 | 0 | 0 | 4.2 | 0 | 0
35382932 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4 | 0 | 0 | 0 | 4 | 0
35379383 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.74 | 0 | 0 | 4.74 | 0 | 0
35375721 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 3 | 1.1652 | 0.71004 | 0 | 0 | 0.71004 | 0 | 0
35374681 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0
35373529 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.086 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35373528 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.086 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35373527 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.086 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35367412 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.086 | 8.19 | 0 | 0 | 0 | 8.19 | 0
35374059 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 |  | 2349 | 0.0030208 |  | 118 | 0.016781 | Tier 2 | 1.2034 | 5.6701 | 0 | 0 | 0 | 5.6701 | 0
35377525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 6.9701 | 0 | 0 | 0 | 0 | 6.9701
35375450 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.66 | 0 | 0 | 0 | 0 | 10.66
35375449 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.85 | 0 | 0 | 0 | 0 | 10.85
35379381 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 |  | 400 | 0.18021 |  | 115 | 0.016899 | Tier 2 & 3 | 1.4865 | 10.4 | 0 | 0 | 0 | 0 | 10.4
35396911 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.13 | 0 | 0 | 3.13 | 0 | 0
35396910 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.97 | 0 | 0 | 2.97 | 0 | 0
35396909 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.01 | 0 | 0 | 3.01 | 0 | 0
35396908 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.32 | 0 | 0 | 2.32 | 0 | 0
35373533 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35367478 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.04 | 0 | 0 | 2.04 | 0 | 0
35383305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 4.99 | 0 | 0 | 0 | 0 | 4.99
35367524 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 14.3201 | 0 | 0 | 0 | 0 | 14.3201
35373597 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.2339 | 5.0201 | 0 | 0 | 0 | 0 | 5.0201
35367464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.2339 | 9.0299 | 0 | 0 | 0 | 0 | 9.0299
35404726 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.88 | 0 | 0 | 3.88 | 0 | 0
35404355 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.113 | 0 | 0 | 0 | 1.113 | 0
35404354 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 0.862 | 0 | 0 | 0 | 0.862 | 0
35404353 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.096 | 0 | 0 | 0 | 2.096 | 0
35404352 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.029 | 0 | 0 | 2.029 | 0 | 0
35404351 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.632 | 0 | 0 | 1.632 | 0 | 0
35373704 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.648 | 0 | 0 | 3.648 | 0 | 0
35367516 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.358 | 0 | 0 | 0 | 1.358 | 0
35362666 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 |  | 2561 | 0.0014894 |  | 100 | 0.018211 | Tier 2 & 3 | 1.0129 | 0.67992 | 0 | 0 | 0 | 0 | 0.67992
35409203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 |  | 314 | 0.20636 |  | 99 | 0.018456 | Tier 2 & 3 | 1.0197 | 1.4 | 0 | 0 | 0 | 0 | 1.4
35418379 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 |  | 2810 | 0.00026318 |  | 98 | 0.01848 | Tier 3 | 1.0041 | 8.4875 | 0 | 0 | 0 | 8.4875 | 0
35417148 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 8.56 | 0 | 0 | 0 | 0 | 8.56
35417144 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 10.7 | 0 | 0 | 0 | 0 | 10.7
35417117 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35417110 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 9.57 | 0 | 0 | 0 | 9.57 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 8.975 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 8.975 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 8.975 | 0 | 0 | 0 | 0 | 8.975
35372463 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 |  | 2207 | 0.0049349 |  | 94 | 0.0187 | Tier 2 | 1.4879 | 1.99 | 0 | 0 | 0 | 0 | 1.99
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.3437 | 10.9 | 0 | 0 | 0 | 10.9 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.3437 | 15 | 0 | 0 | 0 | 0 | 15
35395930 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.369 | 0 | 0 | 0 | 0 | 0.369
35395929 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.057 | 0 | 0 | 0 | 0 | 0.057
35395928 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 1.937 | 0 | 0 | 0 | 0 | 1.937
35372464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 6.553 | 0 | 0 | 0 | 0 | 6.553
35418356 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 |  | 2351 | 0.0030112 |  | 90 | 0.018786 | Tier 3 | 1.5 | 0.4 | 0 | 0 | 0.4 | 0 | 0
35418366 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1253 | 6.062 | 0 | 0 | 0 | 6.062 | 0
35418361 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1253 | 6.601 | 0 | 0 | 0 | 0 | 6.601
35376559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 1.21 | 0 | 0 | 0 | 0 | 1.21
35376558 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 10.25 | 0 | 0 | 0 | 0 | 10.25
35373620 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 4.41 | 0 | 0 | 4.41 | 0 | 0
35367468 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 6.65 | 0 | 0 | 6.65 | 0 | 0
35383758 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 |  | 2247 | 0.0041901 |  | 80 | 0.019265 | Tier 3 | 1.5 | 10.8 | 0 | 0 | 0 | 10.8 | 0
35409211 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4743 | 3.3 | 0 | 0 | 3.3 | 0 | 0
35409205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4743 | 15.2 | 0 | 0 | 0 | 0 | 15.2
35391723 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799
35391722 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799
35391721 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0
35391473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0
35391472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.0799 | 0 | 0 | 10.0799 | 0 | 0
35391471 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.7201 | 0 | 0 | 10.7201 | 0 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.9152 | 8.788 | 0 | 0 | 0 | 8.788 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.9152 | 15 | 0 | 0 | 0 | 0 | 15
35409217 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 9.7 | 0 | 0 | 0 | 0 | 9.7
35409215 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 5.1 | 0 | 0 | 0 | 0 | 5.1
35373532 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 8.4701 | 0 | 0 | 8.4701 | 0 | 0
35373530 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 15.51 | 0 | 0 | 0 | 0 | 15.51
35367414 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 2 & 3 | 1.09 | 9.75 | 0 | 0 | 9.75 | 0 | 0
35404349 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.47 | 0 | 0 | 0 | 0 | 4.47
35376890 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 7.09 | 0 | 0 | 0 | 0 | 7.09
35372462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.85 | 0 | 0 | 0 | 0 | 4.85
35373628 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 8.7299 | 0 | 0 | 0 | 0 | 8.7299
35367504 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 9.35 | 0 | 0 | 0 | 0 | 9.35
35418375 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 |  | 2670 | 0.0008147 |  | 60 | 0.021109 | Tier 3 | 1.0358 | 10.3875 | 0 | 0 | 0 | 10.3875 | 0
35385804 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 0 | 11.29
35385803 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 11.29 | 0
35418305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 0 | 8.65
35418255 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 8.65 | 0
35417127 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 4.9 | 0 | 0 | 0 | 4.9 | 0
35364784 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 7.1701 | 0 | 0 | 0 | 0 | 7.1701
35363720 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 9.59 | 0 | 0 | 0 | 9.59 | 0
35363559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0445 | 10.34 | 0 | 0 | 0 | 10.34 | 0
35409202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 |  | 915 | 0.078235 |  | 56 | 0.021686 | Tier 2 & 3 | 1.3284 | 1.2 | 0 | 0 | 0 | 0 | 1.2
35375452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 |  | 1710 | 0.017864 |  | 52 | 0.02211 | Tier 3 | 1.4588 | 6.9201 | 0 | 0 | 0 | 6.9201 | 0
35374570 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 |  | 658 | 0.11807 |  | 46 | 0.022999 | Tier 2 | 2.1181 | 7.2799 | 0 | 0 | 0 | 0 | 7.2799
35374569 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.51004 | 0 | 0 | 0 | 0 | 0.51004
35374567 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.43996 | 0 | 0 | 0 | 0 | 0.43996
35374566 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 0.11004 | 0 | 0 | 0 | 0 | 0.11004
35374564 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 6.79 | 0 | 0 | 0 | 0 | 6.79
35374563 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 7.21 | 0 | 0 | 0 | 0 | 7.21
35374443 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7701 | 0 | 0 | 0 | 0 | 6.7701
35374208 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 4.89 | 0 | 0 | 0 | 0 | 4.89
35374206 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 9.69 | 0 | 0 | 0 | 9.69 | 0
35374205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.24 | 0 | 0 | 0 | 0 | 6.24
35374204 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7201 | 0 | 0 | 0 | 0 | 6.7201
35377520 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 |  | 328 | 0.19983 |  | 38 | 0.024501 | Tier 3 | 1.0078 | 3.9701 | 0 | 0 | 0 | 0 | 3.9701
35374202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 4.6701 | 0 | 0 | 0 | 0 | 4.6701
35374200 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 8.04 | 0 | 0 | 0 | 0 | 8.04
35385806 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 6.69 | 0 | 0 | 0 | 0 | 6.69
35385805 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 10.74 | 0 | 0 | 0 | 0 | 10.74
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 |  | 178 | 0.2712 |  | 32 | 0.025831 | Tier 3 | 1.5506 | 15.1375 | 0 | 0 | 15.1375 | 0 | 0
35409213 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 |  | 1422 | 0.032289 |  | 30 | 0.025967 | Tier 2 | 1.0982 | 4.7299 | 0 | 0 | 4.7299 | 0 | 0
35367335 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 9.7201 | 0 | 0 | 0 | 9.7201 | 0
35365064 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 10.34 | 0 | 0 | 0 | 0 | 10.34
35373634 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 4.4299 | 0 | 0 | 0 | 0 | 4.4299
35373632 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 10.2299 | 0 | 0 | 0 | 0 | 10.2299
35367508 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 5.94 | 0 | 0 | 0 | 0 | 5.94
35367507 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 3.04 | 0 | 0 | 0 | 0 | 3.04
35318072 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 |  | 2435 | 0.002283 |  | 1105 | 0.0019396 | Tier 3 | 1.6206 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0
35385802 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 |  | 377 | 0.18755 |  | 15 | 0.034099 | Tier 3 | 1.3819 | 9.6 | 0 | 0 | 0 | 0 | 9.6
35376891 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 |  | 1235 | 0.044601 |  | 14 | 0.034265 | Tier 3 | 1.3391 | 4.4 | 0 | 0 | 0 | 0 | 4.4
35373708 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4721 | 3.73 | 0 | 0 | 0 | 0 | 3.73
35372465 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4721 | 11.84 | 0 | 0 | 0 | 0 | 11.84
35372258 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 8.892 | 0 | 0 | 0 | 0 | 8.892
35372257 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 9.808 | 0 | 0 | 0 | 0 | 9.808
35372461 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 |  | 1744 | 0.016801 |  | 8 | 0.040941 | Tier 2 & 3 | 1.5 | 4.42 | 0 | 0 | 4.42 | 0 | 0
35396763 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 0.88 | 0 | 0 | 0 | 0 | 0.88
35353527 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8221 | -121.5955 | N/A |  | N/A | N/A |  | 1124 | N/A | Tier 3 | N/A | 1.2 | 0 | 0 | 1.2 | 0 | 0
35353525 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8243 | -121.5994 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | 1.0039 | 2.8 | 0 | 0 | 2.8 | 0 | 0
35353479 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8211 | -121.6013 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | 1.0039 | 2.5 | 0 | 0 | 2.5 | 0 | 0
35353477 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8192 | -121.6024 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | 1.0039 | 2.2 | 0 | 0 | 2.2 | 0 | 0
35353470 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8146 | -121.6066 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 3.5 | 0 | 0 | 3.5 | 0 | 0
35353468 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8167 | -121.598 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | 1.0039 | 2.5 | 0 | 0 | 2.5 | 0 | 0
35353467 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8182 | -121.5952 | N/A |  | N/A | N/A |  | 1124 | N/A | Tier 3 | N/A | 2.4 | 0 | 2.4 | 0 | 0 | 0
35353466 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8091 | -121.5998 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | 1.0039 | 2.4 | 0 | 2.4 | 0 | 0 | 0
35353463 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8121 | -121.5914 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | 1.2048 | 2.6 | 0 | 0 | 2.6 | 0 | 0
35342338 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.163 | -122.1902 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.24 | 0 | 0 | 0 | 1.24 | 0
35353399 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.5973 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | 1.2048 | 2.3 | 0 | 0 | 2.3 | 0 | 0
35352075 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7777 | -121.6077 | N/A |  | N/A | N/A |  | 809 | N/A | Tier 3 | N/A | 6.1 | 0 | 6.1 | 0 | 0 | 0
35350874 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7637 | -121.5732 | N/A |  | N/A | N/A |  | 1617 | N/A | Tier 3 | N/A | 2.5 | 0 | 2.5 | 0 | 0 | 0
35350582 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.37879 | 0 | 0.37879 | 0 | 0 | 0
35350519 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.47348 | 0 | 0.47348 | 0 | 0 | 0
35396762 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.91 | 0 | 0 | 0 | 0 | 2.91
35342337 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1657 | -122.2231 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 0.52008 | 0 | 0 | 0 | 0.52008 | 0
35342336 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1699 | -122.2026 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0
35342335 | Fire Rebuild | 08W | ESTS | Estimating | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1672 | -122.2131 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.5299 | 0 | 0 | 1.5299 | 0 | 0
35334541 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 0.0026407 | Tier 3 | 1.0799 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0
35292789 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | Tier 2 | 1.0393 | 0.1 | 0 | 0.1 | 0 | 0 | 0
35292788 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | Tier 2 | 1.0393 | 1.1 | 0 | 1.1 | 0 | 0 | 0
35372259 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.84 | 0 | 0 | 0 | 0 | 2.84
35325226 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9868 | -121.8481 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.5241 | 0 | 0 | 0 | 3.5241 | 0
35325225 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9729 | -121.7814 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.6396 | 0 | 0 | 0 | 3.6396 | 0
35325224 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 41.0088 | -121.7129 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.284 | 0 | 0 | 0 | 3.284 | 0
35294730 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9685 | -121.8246 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 2.9066 | 0 | 0 | 2.9066 | 0 | 0
35294729 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7479 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.1407 | 0 | 0 | 0 | 3.1407 | 0
35114040 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 |  | 2271 | 0.0037571 |  | 558 | 0.0048336 | Tier 3 | 2.0641 | 0.093561 | 0.04072 | 0.052841 | 0 | 0 | 0
35318074 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 |  | 2246 | 0.0041981 |  | 936 | 0.002497 | Tier 2 | 1.0031 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0
35321894 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | Tier 2 | 1.0744 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0
35297464 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | Tier 2 | 1.0744 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0
35284810 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2086 | -122.3251 | WDRM v2 |  | 2186 | 0.0054078 |  | 2434 | 0.00033154 | Tier 2 | 1.134 | 0.85814 | 0 | 0 | 0.85814 | 0 | 0
35219543 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 |  | 2123 | 0.0065148 |  | 1979 | 0.00055552 | Tier 2 | 1.5 | 0.24 | 0 | 0.24 | 0 | 0 | 0
35342339 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 |  | 2070 | 0.0075562 |  | 1413 | 0.0011281 | Tier 3 | 1.1797 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0
35217275 | Fire Rebuild | 08W | CONS | In-Construction | Y | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0.0002898 | Tier 2 | 1.1062 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0
35217274 | Fire Rebuild | 08W | CONS | In-Construction | Y | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0.0002898 | Tier 2 | 1.1062 | 2.5239 | 1.6411 | 0 | 0.88277 | 0 | 0
35228775 | Base SH | 08W | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 0.90341 | 0 | 0 | 0.90341 | 0 | 0
35228774 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 1.0008 | 0 | 0 | 1.0008 | 0 | 0
35223063 | Base SH | 08W | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0
35285594 | Fire Rebuild | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8075 | -120.0935 | WDRM v2 |  | 2005 | 0.0089565 |  | 2299 | 0.00038767 | Tier 2 | 2.7059 | 0.21989 | 0 | 0 | 0.21989 | 0 | 0
35109546 | Base SH | 08W | DOCC | In-Construction | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.44621 | 0.44621 | 0 | 0 | 0 | 0
35109541 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.37955 | 0.04072 | 0.33883 | 0 | 0 | 0
35057010 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 2.2513 | 0 | 2.2513 | 0 | 0 | 0
35056733 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.57576 | 0 | 0 | 0.57576 | 0 | 0
35320462 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2642 | -122.1295 | WDRM v2 |  | 1848 | 0.012819 |  | 8953 |  | Tier 2 | 1.4976 | 0.34508 | 0 | 0 | 0.34508 | 0 | 0
35343741 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3371 | -122.4929 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | Tier 2 & 3 | 1.2572 | 0.58 | 0 | 0 | 0.58 | 0 | 0
35312542 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Glen Ellen | Sonoma | 38.3791 | -122.5192 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | Tier 2 & 3 | 1.2572 | 0.77 | 0 | 0 | 0.77 | 0 | 0
35294728 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7478 | WDRM v2 |  | 1816 | 0.01407 |  | 326 | 0.0086689 | Tier 2 | 1.5 | 1.893 | 0 | 0 | 0 | 1.893 | 0
35281758 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 |  | 1748 | 0.016728 |  | 521 | 0.0051671 | Tier 2 | 1.5247 | 1.4 | 0 | 1.4 | 0 | 0 | 0
35145001 | Base SH | 08W | CONS | In-Construction | Y | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.931 | -121.9736 | WDRM v2 |  | 1739 | 0.016935 |  | 1812 | 0.0006705 | Tier 2 & 3 | 1.08 | 1.8845 | 0 | 0 | 1.8845 | 0 | 0
35329013 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | Tier 2 | 1.9074 | 1.85 | 0 | 1.85 | 0 | 0 | 0
35329012 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0.0022353 | Tier 2 | 1.5526 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0
35299633 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0.0022353 | Tier 2 | 1.5526 | 2.14 | 0 | 2.14 | 0 | 0 | 0
35284023 | Fire Rebuild | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 | WDRM v2 |  | 1684 | 0.019316 |  | 732 | 0.0035071 | Tier 3 | 1.7086 | 1.1699 | 0 | 0 | 1.1699 | 0 | 0
35335235 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5192 | -122.4719 | WDRM v2 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | Tier 3 | 1.0815 | 3.5799 | 0 | 0 | 3.5799 | 0 | 0
35280505 | Other | 30A | ESTS | Estimating | Y | NV | Region 2 - North East | Shasta | Shasta | 40.5923 | -122.4836 | WDRM v2 |  | 1614 | 0.022607 |  | 43 | 0.023649 | Tier 3 | 2.6214 | 0.37879 | 0 | 0 | 0 | 0 | 0.37879
35224856 | Other | 10K | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | WDRM v2 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | Tier 2 & 3 | 1.036 | 2.4956 | 0 | 0 | 2.4956 | 0 | 0
35329016 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 0.022808 | Tier 2 | 1.0016 | 3.54 | 0 | 3.54 | 0 | 0 | 0
35299635 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 0.022808 | Tier 2 | 1.0016 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35236985 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 0.01209 | Tier 3 | 2.6514 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0
35334407 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0
35320466 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Salyer | Trinity | 40.8669 | -123.5148 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 2 | 0 | 0 | 0 | 2 | 0
35297699 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0
35297697 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0
35297696 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0
35297695 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35297694 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.95 | 0 | 0.95 | 0 | 0 | 0
35297693 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 1 | 0 | 1 | 0 | 0 | 0
35297692 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0
35281815 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0
35233996 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 0.0099544 | Tier 3 | 1.2536 | 0.84962 | 0 | 0.84962 | 0 | 0 | 0
35233995 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 0.0099544 | Tier 3 | 1.2536 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0
35290517 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0.0020497 | Tier 2 | 1.7495 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0
35282166 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0.0020497 | Tier 2 | 1.7495 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0
35145540 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 |  | 1316 | 0.039234 |  | 1205 | 0.0016222 | Tier 3 | 2.9322 | 0.53447 | 0 | 0.53447 | 0 | 0 | 0
35241077 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0
35241076 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0
35241075 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0
35237889 | Fire Rebuild | 08W | DOCC | In-Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 |  | 1299 | 0.040282 |  | 250 | 0.010796 | Tier 3 | 2.7309 | 1.8256 | 1.8193 | 0.00625 | 0 | 0 | 0
35236997 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0
35235675 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0
35235672 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0
35292791 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 1285 | 0.041237 |  | 2987 | 0.00013567 | Tier 2 | 1.3648 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0
35279307 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 |  | 1172 | 0.050559 |  | 785 | 0.0031715 | Tier 2 & 3 | 1.4657 | 2.25 | 0 | 2.25 | 0 | 0 | 0
35332870 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0
35332868 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0
35312541 | Base SH | 08W | ADER | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0
35283938 | Base SH | 08W | PEND | Permitting/Dependency | Y | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3845 | -122.2937 | WDRM v2 |  | 1145 | 0.05299 |  | 1026 | 0.0021738 | Tier 3 | 1.1831 | 1.1939 | 0 | 0 | 1.1939 | 0 | 0
35320444 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2683 | -120.6383 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0.00059698 | Tier 2 | 1.0458 | 0.48 | 0 | 0 | 0.48 | 0 | 0
35338402 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | Tier 2 | 1.4741 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0
35320464 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | Tier 2 | 1.4741 | 0.15 | 0 | 0.15 | 0 | 0 | 0
35384087 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Oroville | Butte | 39.6578 | -121.5657 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0
35329014 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0
35299634 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0
35234526 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | WDRM v2 |  | 999 | 0.067405 |  | 2578 | 0.0002828 | Tier 2 | 1.4721 | 1.225 | 0 | 0 | 1.225 | 0 | 0
35292784 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0
35292780 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0
35290944 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0
35290544 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0
35290542 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0
35343397 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5082 | -121.5038 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 0.84 | 0 | 0 | 0.84 | 0 | 0
35343396 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0
35343395 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.76 | 0 | 1.76 | 0 | 0 | 0
35343394 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.17 | 0 | 1.17 | 0 | 0 | 0
35331308 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 0.82 | 0 | 0.82 | 0 | 0 | 0
35331307 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 2.55 | 0 | 2.55 | 0 | 0 | 0
35331306 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5178 | -121.4854 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 2.67 | 0 | 0 | 2.67 | 0 | 0
35312560 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 3.61 | 0 | 3.61 | 0 | 0 | 0
35254947 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 0.0099219 | Tier 2 | 1.0655 | 0.263 | 0 | 0.263 | 0 | 0 | 0
35254945 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 0.0099219 | Tier 2 | 1.0655 | 0.51 | 0 | 0.51 | 0 | 0 | 0
35292756 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0
35292755 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0
35292754 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0
35290540 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 1.2858 | 0 | 1.2858 | 0 | 0 | 0
35280493 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 0.35 | 0 | 0.35 | 0 | 0 | 0
35279985 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 3.115 | 0 | 3.115 | 0 | 0 | 0
35280496 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 0.0028532 | Tier 2 | 1.2887 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0
35297984 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 | WDRM v2 |  | 851 | 0.085979 |  | 2266 | 0.00040165 | Tier 2 | 2.7366 | 1.1201 | 0 | 0 | 0 | 0 | 1.1201
74010582 | Other | 30A | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | WDRM v2 |  | 811 | 0.092281 |  | 1184 | 0.0016787 | Tier 2 | 2.0901 | 1.3299 | 0 | 0 | 1.3299 | 0 | 0
35342151 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0
35342148 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 1.19 | 0 | 1.19 | 0 | 0 | 0
35342147 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0
35342146 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 2.397 | 0 | 2.397 | 0 | 0 | 0
35342145 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0
35342144 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 1.617 | 0 | 1.617 | 0 | 0 | 0
35342143 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0
35320442 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.3858 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0
35337015 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | Tier 2 | 1.4988 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0
35337014 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | Tier 2 | 1.4988 | 0.020076 | 0 | 0.020076 | 0 | 0 | 0
35329011 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1445 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0
35329010 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1445 | 2.814 | 0 | 2.814 | 0 | 0 | 0
35329009 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1445 | 0.94091 | 0 | 0.94091 | 0 | 0 | 0
35299631 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1445 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0
35342310 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 1.357 | 0 | 0 | 0 | 0 | 1.357
35342308 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8868 | -118.9361 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 2.997 | 0 | 0 | 0 | 0 | 2.997
35342307 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8833 | -118.9271 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 2.252 | 0 | 0 | 0 | 0 | 2.252
35335289 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 1.5775 | 0 | 0 | 0 | 0 | 1.5775
35335288 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.9158 | -118.9258 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 3.6 | 0 | 0 | 0 | 3.6 | 0
35321445 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 2.958 | 0 | 0 | 0 | 2.958 | 0
35312554 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.9321 | -118.9283 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6754 | 1.6 | 0 | 0 | 0 | 1.6 | 0
35339665 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0
35339664 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.17008 | 0 | 0.17008 | 0 | 0 | 0
35320447 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.83996 | 0 | 0.83996 | 0 | 0 | 0
35335287 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8466 | -118.8987 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 2.1799 | 0 | 0 | 2.1799 | 0 | 0
35335286 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8542 | -118.893 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 5.21 | 0 | 0 | 5.21 | 0 | 0
35312553 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8837 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 2.39 | 0 | 0 | 2.39 | 0 | 0
35332866 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 |  | 590 | 0.13388 |  | 2153 | 0.00046034 | Tier 2 | 1.4456 | 1.01 | 0 | 1.01 | 0 | 0 | 0
35312549 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | Tier 2 | 1.0306 | 0.98 | 0 | 0.98 | 0 | 0 | 0
35342318 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8363 | -118.8637 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 4.508 | 0 | 0 | 0 | 4.508 | 0
35342317 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8295 | -118.8723 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.604 | 0 | 0 | 0 | 2.604 | 0
35342316 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.837 | -118.8663 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.443 | 0 | 0 | 0 | 2.443 | 0
35342315 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8407 | -118.8677 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.723 | 0 | 0 | 0 | 1.723 | 0
35342314 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8594 | -118.8797 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 0.421 | 0 | 0 | 0 | 0.421 | 0
35342313 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8835 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.902 | 0 | 0 | 2.902 | 0 | 0
35342312 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8726 | -118.8905 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.591 | 0 | 0 | 1.591 | 0 | 0
35342311 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8765 | -118.8926 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.174 | 0 | 0 | 2.174 | 0 | 0
35320607 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.846 | -118.872 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.8129 | 0 | 0 | 2.8129 | 0 | 0
35312555 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.979 | 0 | 0 | 1.979 | 0 | 0
35364448 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 3.2201 | 0 | 0 | 0 | 3.2201 | 0
35364446 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.5381 | 0 | 0 | 0 | 0 | 2.5381
35364442 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 4.621 | 0 | 0 | 4.621 | 0 | 0
35364440 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.8689 | 0 | 0 | 0 | 0 | 2.8689
35364339 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.746 | 0 | 0 | 2.746 | 0 | 0
35364337 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.5091 | 0 | 0 | 2.5091 | 0 | 0
35364336 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 1.8561 | 0 | 0 | 0 | 0 | 1.8561
35364334 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.1591 | 0 | 0 | 2.1591 | 0 | 0
35364333 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.8131 | 0 | 0 | 0 | 0 | 2.8131
35364332 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.4159 | 0 | 0 | 0 | 2.4159 | 0
35316201 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1397 | -120.9389 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.68314 | 0 | 0.68314 | 0 | 0 | 0
35316200 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1413 | -120.957 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.0417 | 0 | 1.0417 | 0 | 0 | 0
35316019 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1435 | -120.9581 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.017 | 0 | 1.017 | 0 | 0 | 0
35316018 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.7197 | 0 | 0.7197 | 0 | 0 | 0
35334467 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 40.3305 | -122.0971 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.014 | 0 | 0 | 2.014 | 0 | 0
35334466 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 40.3386 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 1.5951 | 0 | 0 | 1.5951 | 0 | 0
35313249 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.2871 | 0 | 1.2871 | 0 | 0 | 0
35332958 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | Tier 2 | 2.3771 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0
35320312 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | Tier 2 | 2.3771 | 2.04 | 0 | 2.04 | 0 | 0 | 0
35056808 | Other | 30A | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | WDRM v2 |  | 534 | 0.14747 |  | 1720 | 0.00074971 | Tier 3 | 1.0903 | 1.5138 | 0 | 0 | 1.5138 | 0 | 0
35335293 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 2.41 | 0 | 2.41 | 0 | 0 | 0
35335292 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0
35335291 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0
35320440 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3783 | -122.0044 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 2.2 | 0 | 0 | 2.2 | 0 | 0
35236439 | Base SH | 08W | DOCC | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.2508 | 1.2034 | 0.047348 | 0 | 0 | 0
35234865 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0
35234862 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0
35234758 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0
35234756 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 2.782 | 0 | 2.782 | 0 | 0 | 0
35227025 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0
35227007 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0
35227002 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 0.41894 | 0 | 0 | 0.41894 | 0 | 0
35227001 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0
35226878 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0
35226873 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0
35226857 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0
35174501 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0
35174478 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.1929 | 1.04 | 0 | 1.04 | 0 | 0 | 0
35227031 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1868 | 1.55 | 0 | 1.55 | 0 | 0 | 0
35227030 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1868 | 1.3765 | 0 | 1.3765 | 0 | 0 | 0
35226621 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1868 | 1.55 | 0 | 0 | 1.55 | 0 | 0
35192282 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7241 | -122.619 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1868 | 2.04 | 0 | 0 | 2.04 | 0 | 0
35340270 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | Tier 2 | 1.0421 | 2.34 | 0 | 2.34 | 0 | 0 | 0
35311898 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | Tier 2 | 1.0421 | 2 | 0 | 2 | 0 | 0 | 0
35274593 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0.010861 | Tier 2 | 1.3062 | 2.756 | 0 | 2.756 | 0 | 0 | 0
35274589 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0.010861 | Tier 2 & 3 | 1.3062 | 2.132 | 0 | 2.132 | 0 | 0 | 0
35330241 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1508 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0
35330219 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1508 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0
35330217 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0
35330216 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35330215 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 3.54 | 0 | 3.54 | 0 | 0 | 0
35330213 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.5887 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 5.26 | 0 | 0 | 5.26 | 0 | 0
35330211 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0
35317399 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1508 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35312550 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1508 | 1.54 | 0 | 1.54 | 0 | 0 | 0
35320463 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 |  | 419 | 0.17457 |  | 987 | 0.0022992 | Tier 2 | 1.5 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0
35380376 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0
35380373 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 1.79 | 0 | 1.79 | 0 | 0 | 0
35380372 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 1.74 | 0 | 1.74 | 0 | 0 | 0
35380371 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0
35380370 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0
35380369 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0
35380368 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0
35380365 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.04 | 0 | 3.04 | 0 | 0 | 0
35334229 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.04 | 0 | 3.04 | 0 | 0 | 0
35311897 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 4.84 | 0 | 4.84 | 0 | 0 | 0
35285065 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | Tier 2 | 1.381 | 0.25398 | 0 | 0.25398 | 0 | 0 | 0
35285064 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | Tier 2 | 1.381 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0
35339293 | Base SH | 08W | ESTS | Estimating | Y | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35338410 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 2.21 | 0 | 2.21 | 0 | 0 | 0
35338409 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35338408 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0
35338407 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0
35338406 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 1.14 | 0 | 1.14 | 0 | 0 | 0
35338405 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35338404 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0
35320461 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 3.56 | 0 | 3.56 | 0 | 0 | 0
35320460 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.2475 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0
35339289 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.82 | 0 | 1.82 | 0 | 0 | 0
35339288 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.25 | 0 | 2.25 | 0 | 0 | 0
35339287 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.2 | 0 | 1.2 | 0 | 0 | 0
35339286 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.54 | 0 | 2.54 | 0 | 0 | 0
35339285 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.32 | 0 | 2.32 | 0 | 0 | 0
35339283 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.96 | 0 | 2.96 | 0 | 0 | 0
35339282 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 0.51 | 0 | 0.51 | 0 | 0 | 0
35337012 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.443 | -122.3663 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 4.92 | 0 | 0 | 0 | 4.92 | 0
35337011 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.89 | 0 | 2.89 | 0 | 0 | 0
35337010 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 3.82 | 0 | 3.82 | 0 | 0 | 0
35337008 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35317887 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 0.8 | 0 | 0.8 | 0 | 0 | 0
35317480 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.06 | 0 | 2.06 | 0 | 0 | 0
35312548 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.2 | 0 | 1.2 | 0 | 0 | 0
35280560 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 2.64 | 0 | 2.64 | 0 | 0 | 0
35280499 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.85 | 0 | 0.85 | 0 | 0 | 0
35279182 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0
35279181 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 5.589 | 0 | 5.589 | 0 | 0 | 0
35192280 | Base SH | 08W | PEND | Permitting/Dependency | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 0.034099 | Tier 3 | 1.3819 | 1.34 | 0 | 1.34 | 0 | 0 | 0
35223030 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 |  | 355 | 0.19378 |  | 2768 | 0.00020951 | Tier 2 | 1.5959 | 1.1968 | 1.1364 | 0.060417 | 0 | 0 | 0
35330249 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 4 | 0 | 4 | 0 | 0 | 0
35330248 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0296 | -122.6802 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 2.4 | 0 | 0 | 2.4 | 0 | 0
35330247 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 0.75 | 0 | 0.75 | 0 | 0 | 0
35330246 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0
35330245 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0
35330244 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0
35329474 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 0.007396 | Tier 2 & 3 | 1.0644 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0
35317398 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0581 | -122.693 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 0.007396 | Tier 2 & 3 | 1.0644 | 3.5201 | 0 | 0 | 3.5201 | 0 | 0
35312552 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.1247 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0
35349642 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1699 | -123.006 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.035985 | 0 | 0 | 0 | 0.035985 | 0
35285251 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0
35286270 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7583 | -121.6291 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 1.2 | 0 | 0 | 1.2 | 0 | 0
35285249 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0
35283346 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0
35283343 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.72614 | 0 | 0.72614 | 0 | 0 | 0
35256083 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 1.847 | 0 | 1.847 | 0 | 0 | 0
35134959 | Other | 06A | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Valley Springs | Calaveras | 38.2131 | -120.7638 | WDRM v2 |  | 322 | 0.20132 |  | 1048 | 0.0020877 | Tier 2 | 1.3568 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0
35332364 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0
35332363 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0
35332362 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0
35332360 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 5.46 | 0 | 5.46 | 0 | 0 | 0
35330812 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 2.49 | 0 | 2.49 | 0 | 0 | 0
35316278 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35312543 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 3.71 | 0 | 3.71 | 0 | 0 | 0
35329473 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0654 | -122.6333 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 4.761 | 0 | 0 | 4.761 | 0 | 0
35329472 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0
35312551 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0
35277935 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0.0043344 | Tier 2 | 2.2546 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0
35332217 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 3.0299 | 0 | 3.0299 | 0 | 0 | 0
35332216 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35332215 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 2.26 | 0 | 2.26 | 0 | 0 | 0
35332214 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.04 | 0 | 4.04 | 0 | 0 | 0
35316569 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.81 | 0 | 4.81 | 0 | 0 | 0
35316567 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0
35312540 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0
35349649 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | Tier 2 | 1.0227 | 0.25019 | 0 | 0 | 0.25019 | 0 | 0
35349648 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | Tier 2 | 1.0227 | 0.25625 | 0 | 0 | 0.25625 | 0 | 0
35329008 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | Tier 2 | 1 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0
35299629 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.654 | -121.6323 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | Tier 2 | 1 | 0.89091 | 0 | 0 | 0.89091 | 0 | 0
35330815 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | Tier 2 | 1.0974 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0
35311895 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | Tier 2 | 1.0974 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0
35337306 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 2.2667 | 0 | 2.2667 | 0 | 0 | 0
35284365 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 2.7547 | 0 | 2.7547 | 0 | 0 | 0
35284364 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 0.91742 | 0 | 0.91742 | 0 | 0 | 0
35349244 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | Tier 2 | 1.6327 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0
35320450 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | Tier 2 | 1.6327 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0
35223039 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WDRM v2 |  | 218 | 0.24845 |  | 2461 | 0.00032066 | Tier 2 | 1.256 | 0.53561 | 0.40985 | 0 | 0.12576 | 0 | 0
35223615 | Base SH | 08W | PEND | Permitting/Dependency | Y | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 |  | 215 | 0.25006 |  | 1267 | 0.0014262 | Tier 3 | 1.2195 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0
35312544 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0.0012407 | Tier 2 | 1.4822 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0
35335290 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0.00074783 | Tier 2 | 1.0225 | 2.61 | 0 | 2.61 | 0 | 0 | 0
35320441 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0.00074783 | Tier 2 | 1.0225 | 2.14 | 0 | 2.14 | 0 | 0 | 0
35337163 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | Tier 2 | 1.5614 | 1.39 | 0 | 1.39 | 0 | 0 | 0
35320449 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | Tier 2 | 1.5614 | 3.2375 | 0 | 3.2375 | 0 | 0 | 0
35305308 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8944 | -120.9647 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.66799 | 0 | 0 | 0.66799 | 0 | 0
35305303 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 1.065 | 0 | 1.065 | 0 | 0 | 0
35293670 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0
35293665 | Base SH | 08W | UNSC | Ready for Construction | Y | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0
35293663 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.98996 | 0 | 0 | 0.98996 | 0 | 0
35293662 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0
35278093 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.41496 | 0 | 0 | 0 | 0 | 0.41496
35254346 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6087 | N/A |  | N/A | N/A |  | 1178 | N/A | Non-HFTD | N/A | 0.056818 | 0 | 0 | 0.056818 | 0 | 0
35254345 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7874 | -121.601 | N/A |  | N/A | N/A |  | 809 | N/A | Tier 3 | N/A | 0.066288 | 0 | 0 | 0.066288 | 0 | 0
35254344 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7414 | -121.6432 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 3 | 1.0005 | 0.12027 | 0 | 0 | 0.12027 | 0 | 0
35254275 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7704 | -121.6012 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 0.066288 | 0 | 0 | 0.066288 | 0 | 0
35254274 | Community Rebuild | 95F | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7598 | -121.6341 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 0.088447 | 0 | 0 | 0.088447 | 0 | 0
35277938 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.42822 | 0 | 0.42822 | 0 | 0 | 0
35277924 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0
35062376 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 0.011098 | Tier 3 | 2.2454 | 5.0311 | 0.97178 | 4.0593 | 0 | 0 | 0
35254650 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 0.0099281 | Tier 2 | 1.1169 | 0.30436 | 0.30436 | 0 | 0 | 0 | 0
35325590 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 2.06 | 0 | 2.06 | 0 | 0 | 0
35325589 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 1.21 | 0 | 1.21 | 0 | 0 | 0
35312545 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0
35331305 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | Tier 2 | 1.1362 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0
35298571 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | Tier 2 | 1.1362 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0
35332218 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 3.26 | 0 | 3.26 | 0 | 0 | 0
35332213 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0
35316561 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 4.41 | 0 | 4.41 | 0 | 0 | 0
35311899 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 3.44 | 0 | 3.44 | 0 | 0 | 0
35404729 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4295 | -122.0489 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 0.95 | 0 | 0 | 0 | 0.95 | 0
35404728 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4201 | -122.0443 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 0.85 | 0 | 0 | 0 | 0.85 | 0
35404727 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4267 | -122.0475 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 1.1 | 0 | 0 | 0 | 1.1 | 0
35334755 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 1.47 | 0 | 1.47 | 0 | 0 | 0
35334754 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 3.93 | 0 | 3.93 | 0 | 0 | 0
35334753 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 1.26 | 0 | 1.26 | 0 | 0 | 0
35246598 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8149 | -121.5802 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 3.5 | 0 | 0 | 3.5 | 0 | 0
35246595 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7842 | -121.5991 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 5.9 | 0 | 0 | 5.9 | 0 | 0
35246594 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7382 | -121.6208 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | 1.0011 | 3.7 | 0 | 0 | 3.7 | 0 | 0
35246592 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7367 | -121.6125 | N/A |  | N/A | N/A |  | 362 | N/A | Tier 3 | 1.036 | 6.2 | 0 | 0 | 6.2 | 0 | 0
35246591 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7485 | -121.6086 | N/A |  | N/A | N/A |  | 1563 | N/A | Tier 3 | N/A | 4.3 | 0 | 0 | 4.3 | 0 | 0
35246590 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7696 | -121.579 | N/A |  | N/A | N/A |  | 2198 | N/A | Tier 3 | N/A | 3.3 | 0 | 0 | 3.3 | 0 | 0
35246589 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.764 | -121.5986 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 0.5 | 0 | 0 | 0.5 | 0 | 0
35320339 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 2.2 | 0 | 2.2 | 0 | 0 | 0
35246316 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7265 | -121.6374 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | 1.0011 | 3.6 | 0 | 0 | 3.6 | 0 | 0
35246309 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7752 | -121.6093 | N/A |  | N/A | N/A |  | 1546 | N/A | Non-HFTD | N/A | 1.3 | 0 | 0 | 1.3 | 0 | 0
35246308 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7572 | -121.5722 | N/A |  | N/A | N/A |  | 1617 | N/A | Tier 3 | N/A | 3.2 | 0 | 0 | 3.2 | 0 | 0
35320336 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4365 | -122.0527 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.231 | 2.3 | 0 | 0 | 2.3 | 0 | 0
35334234 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1088 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.3 | 0 | 0 | 2.3 | 0 | 0
35334232 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9855 | -121.1087 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 1.01 | 0 | 0 | 1.01 | 0 | 0
35244220 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7717 | -121.6118 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 2.5 | 0 | 0 | 2.5 | 0 | 0
35244027 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7285 | -121.6363 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 5.5 | 0 | 0 | 5.5 | 0 | 0
35333504 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 0.45 | 0 | 0.45 | 0 | 0 | 0
35333503 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 0.3 | 0 | 0.3 | 0 | 0 | 0
35333501 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9851 | -121.1296 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.96 | 0 | 0 | 2.96 | 0 | 0
35314416 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9981 | -121.1168 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0
35314415 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.05 | 0 | 0 | 2.05 | 0 | 0
35311896 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1091 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.76 | 0 | 0 | 2.76 | 0 | 0
35259512 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0.00022756 | Tier 2 | 1.2336 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0
35254259 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | Tier 2 & 3 | 1.323 | 0.275 | 0 | 0.275 | 0 | 0 | 0
35240166 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | Tier 2 & 3 | 1.323 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0
35293846 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 & 3 | 1.1318 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0
35290808 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.1318 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0
35290508 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.1318 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0
35290504 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.1318 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0
35301112 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.52576 | 0 | 0.52576 | 0 | 0 | 0
35300933 | Base SH | 08W | UNSC | Ready for Construction | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0
35227481 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7392 | -121.5724 | N/A |  | N/A | N/A |  | 201 | N/A | Tier 3 | 1.0013 | 4.2 | 0 | 4.2 | 0 | 0 | 0
35227417 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7323 | -121.6513 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 2 | 1.0005 | 2.8 | 0 | 0 | 2.8 | 0 | 0
35227415 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7389 | -121.6402 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 3 | 1.0005 | 5.2 | 0 | 5.2 | 0 | 0 | 0
35227413 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7423 | -121.6423 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 2 | 1.0005 | 5.6 | 0 | 0 | 5.6 | 0 | 0
35227412 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.769 | -121.5786 | N/A |  | N/A | N/A |  | 490 | N/A | Tier 3 | 1.0028 | 2 | 0 | 0 | 2 | 0 | 0
35227411 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7595 | -121.6024 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 2.7 | 0 | 0 | 2.7 | 0 | 0
35227409 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7501 | -121.6242 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | 1.0011 | 3.6 | 0 | 0 | 3.6 | 0 | 0
35227408 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7524 | -121.6126 | N/A |  | N/A | N/A |  | 2530 | N/A | Non-HFTD | N/A | 2.1 | 0 | 2.1 | 0 | 0 | 0
35227406 | Community Rebuild | 95F O | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7523 | -121.6185 | N/A |  | N/A | N/A |  | 2530 | N/A | Tier 3 | N/A | 4.5 | 0 | 4.5 | 0 | 0 | 0
35227405 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7578 | -121.6071 | N/A |  | N/A | N/A |  | 503 | N/A | Non-HFTD | 1.006 | 0.3 | 0 | 0.3 | 0 | 0 | 0
35227404 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7538 | -121.6172 | N/A |  | N/A | N/A |  | 2530 | N/A | Non-HFTD | N/A | 3.3 | 0 | 3.3 | 0 | 0 | 0
35227403 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7616 | -121.6079 | N/A |  | N/A | N/A |  | 503 | N/A | Non-HFTD | 1.006 | 2.2 | 0 | 2.2 | 0 | 0 | 0
35227402 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7703 | -121.6071 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 1.9 | 0 | 1.9 | 0 | 0 | 0
35227401 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7628 | -121.6233 | N/A |  | N/A | N/A |  | 69 | N/A | Tier 3 | 1.0005 | 1.2 | 0 | 1.2 | 0 | 0 | 0
35227400 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7712 | -121.6031 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 1.9 | 0 | 0 | 1.9 | 0 | 0
35293508 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0
35254067 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35223032 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0
35334752 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 1.81 | 0 | 1.81 | 0 | 0 | 0
35334750 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 1.49 | 0 | 1.49 | 0 | 0 | 0
35320334 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 2.5 | 0 | 2.5 | 0 | 0 | 0
35320333 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 2.95 | 0 | 2.95 | 0 | 0 | 0
35277925 | Base SH | 08W | CONS | In-Construction | Y | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0.00047477 | Tier 2 | 1.7695 | 0.14148 | 0 | 0.14148 | 0 | 0 | 0
35283198 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 0.0056859 | Tier 2 | 1.226 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0
35338384 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 1.6 | 0 | 1.6 | 0 | 0 | 0
35279120 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 1.004 | 0 | 1.004 | 0 | 0 | 0
35278899 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4365 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0
35280362 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0.0069412 | Tier 2 & 3 | 2.4692 | 0.13258 | 0 | 0.13258 | 0 | 0 | 0
35316537 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Redding | Shasta | 40.624 | -122.3049 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 0.20152 | 0 | 0 | 0.20152 | 0 | 0
35234399 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 0.55985 | 0 | 0 | 0.55985 | 0 | 0
35233950 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 4.5701 | 0 | 0 | 4.5701 | 0 | 0
35233948 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 4.6722 | 0 | 0 | 4.6722 | 0 | 0
35219289 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 6.7973 | 0 | 0 | 6.7973 | 0 | 0
35227652 | Base SH | 08W | CONS | In-Construction | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 0.0073117 | Tier 3 | 1.4991 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0
35219276 | Base SH | 08W | PEND | Permitting/Dependency | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 0.0073117 | Tier 3 | 1.4991 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0
35226700 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0.0002242 | Tier 2 | 1.4877 | 0.4214 | 0.41477 | 0.0066288 | 0 | 0 | 0
35189987 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7404 | -121.5939 | N/A |  | N/A | N/A |  | 490 | N/A | Tier 3 | 1.0028 | 2.7 | 0 | 2.7 | 0 | 0 | 0
35189984 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7471 | -121.6129 | N/A |  | N/A | N/A |  | 1178 | N/A | Non-HFTD | N/A | 3.3 | 0 | 3.3 | 0 | 0 | 0
35189983 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6266 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | 1.0011 | 2.1 | 0 | 0 | 2.1 | 0 | 0
35189853 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7681 | -121.5891 | N/A |  | N/A | N/A |  | 2198 | N/A | Non-HFTD | N/A | 1.4 | 0 | 1.4 | 0 | 0 | 0
35189792 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.784 | -121.5864 | N/A |  | N/A | N/A |  | 1618 | N/A | Non-HFTD | N/A | 3.9 | 0 | 3.9 | 0 | 0 | 0
35189791 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5873 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 2 | 0 | 2 | 0 | 0 | 0
35175548 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7619 | -121.6125 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 3.2 | 0 | 3.2 | 0 | 0 | 0
35175547 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5797 | N/A |  | N/A | N/A |  | 1618 | N/A | Non-HFTD | N/A | 4.8 | 0 | 4.8 | 0 | 0 | 0
35231621 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 0.026126 | Tier 2 & 3 | 1.2678 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0
35231620 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 0.026126 | Tier 2 & 3 | 1.2678 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0
35219096 | Base SH | 08W | CONS | In-Construction | Y | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 0.00471 | Tier 2 | 1.0994 | 1.8303 | 1.8019 | 0.028409 | 0 | 0 | 0
35144480 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8116 | -121.5956 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | 1.2048 | 2.6 | 0 | 2.6 | 0 | 0 | 0
35219093 | Base SH | 08W | PEND | Permitting/Dependency | Y | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 |  | 18 | 0.65331 |  | 448 | 0.0062529 | Tier 2 | 1.0412 | 1.14 | 0 | 1.14 | 0 | 0 | 0
35127550 | Community Rebuild | 95F CEMA | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7858 | -121.6004 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 2.9 | 0 | 0 | 2.9 | 0 | 0
35127360 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7461 | -121.6435 | N/A |  | N/A | N/A |  | 875 | N/A | Tier 2 | 1 | 1.3 | 0 | 0 | 1.3 | 0 | 0
35126752 | Community Rebuild | 95F O | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7333 | -121.6353 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | 1.0011 | 1.9 | 0 | 0 | 1.9 | 0 | 0
35126750 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7741 | -121.5895 | N/A |  | N/A | N/A |  | 2198 | N/A | Tier 3 | N/A | 2.4 | 0 | 2.4 | 0 | 0 | 0
35126645 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7612 | -121.6342 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | 1.006 | 2.2 | 0 | 2.2 | 0 | 0 | 0
35228186 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4139 | 1.49 | 0 | 1.49 | 0 | 0 | 0
35118676 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7551 | -121.6455 | N/A |  | N/A | N/A |  | 69 | N/A | Tier 3 | 1.0005 | 3.2 | 0 | 3.2 | 0 | 0 | 0
35118674 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.6017 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | 1.2048 | 2.1 | 0 | 0 | 2.1 | 0 | 0
35118673 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8005 | -121.6047 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | 1.2048 | 3.1 | 0 | 0 | 3.1 | 0 | 0
35117455 | Community Rebuild | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7813 | -121.594 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 1.4 | 0 | 1.4 | 0 | 0 | 0
35227864 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4139 | 1.3212 | 0.36136 | 0.95985 | 0 | 0 | 0
35220895 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4139 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0
35112126 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.78 | -121.6092 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 2.1 | 0 | 0 | 2.1 | 0 | 0
35224713 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0.029234 | Tier 2 & 3 | 3 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0
35224712 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0.029234 | Tier 2 & 3 | 3 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0
35227160 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 0.007089 | Tier 2 | 1.4876 | 1.3201 | 0 | 0 | 1.3201 | 0 | 0
35226629 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 0.022602 | Tier 3 | 2.481 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0
35226628 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 0.022602 | Tier 3 | 2.481 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Idle Facilities | Removal of Primary Conductor in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
MAT Code
MAT Code | Description
06A | Feeder Projects Associated with Substation Capacity
08W | System Hardening Wildfire Resiliency Projects
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
95F | Electric Distribution Major Emergency
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Division
Division Acronym | Division Name
CC | Central Coast
CV | Central Valley
DA | De Anza
DI | Diablo
EB | East Bay
FR | Fresno
HB | Humboldt
KE | Kern
LP | Los Padres
NB | North Bay
NV | North Valley
PN | Peninsula
SA | Sacramento
SF | San Francisco
SI | Sierra
SJ | San Jose
SO | Sonoma
ST | Stockton
YO | Yosemite
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Mean Risk | Summation of the total risk of all pixels (100-meter x 100-meter cell) linked to a circuit segment, divided by the total number of pixels.
Feasibility score by CPZ | Cost multiplier indicating the difficulty of undergrounding the circuit segment (Circuit Protection Zone (CPZ)) based on presence of hard rock, water crossing, and gradient. The scale ranges from 1 to 3, with 3 being most challenging.

## Cost_Data
Installation Capital Costs
| UG Primary | OH+EPSS/DCD | OH to UG Conversion Factor | 1.25
Capital Total | 3 | 1.125
O&M Annual Costs |  |  | Risk Parameters | Rate
Standard Costs per Mile ($K) | UG Primary | OH | Study Period (years) | 45
Expense Total | 2.9 | 22.8107 | Generic Capital PVRR Multiplier | 1.3891
Ongoing Capital Total | 4.965 | 8.789 | nominal discount rate | 6.8%
O&M Total ($K) | 7.865 | 31.5997 | real discount rate | 4.195%
|  |  | inflation rate | 2.5%

## WF_Data
Circuit Segment | Primary Overhead HFTD Mileage | weighted_composite_for_system_hardening_wildfire_risk_total | MAVF WDRM v3 Risk | PSPS MAVF Risk
| 0.053018 | 0.087256 | 0.99559 | 0
| 0.063133 | 0.13518 | 1.5424 | 0
| 0.046358 | 0.17111 | 1.9523 | 0
| 0.014692 | 0.033039 | 0.37697 | 0
| 0.0137 | 0.079975 | 0.91252 | 0
| 4.2753 | 3.4028 | 38.8262 | 0
| 0.0032255 | 0.0089715 | 0.10236 | 0
| 0.23574 | 0.22518 | 2.5693 | 0
| 4.3236 | 3.8404 | 43.8186 | 0
| 15.8169 | 11.9266 | 136.0829 | 0
| 8.8384 | 5.772 | 65.8588 | 0
| 0.23656 | 0.17387 | 1.9839 | 0
| 8.7009 | 5.7643 | 65.7703 | 0
| 3.5161 | 2.4842 | 28.3445 | 0
| 7.6836 | 4.7056 | 53.6914 | 0
| 0.067118 | 0.0083518 | 0.095294 | 0
| 2.157 | 1.3156 | 15.0114 | 0
| 6.9964 | 4.0645 | 46.3754 | 0
| 0.53696 | 0.30464 | 3.476 | 0
| 14.4436 | 8.3015 | 94.7207 | 0
| 4.8133 | 2.8016 | 31.9666 | 0
| 16.6046 | 9.0145 | 102.8552 | 0
| 2.0337 | 1.0282 | 11.7314 | 0
| 4.8415 | 2.4772 | 28.2648 | 0
| 0.052964 | 0.085541 | 0.97603 | 0
| 1.572 | 0.56647 | 6.4634 | 0
| 7.9965 | 4.0715 | 46.456 | 0
| 2.6041 | 1.3965 | 15.9346 | 0
| 14.7135 | 7.276 | 83.0191 | 0
| 4.0817 | 1.8567 | 21.1847 | 0
| 0.89675 | 0.42811 | 4.8847 | 0
| 12.1088 | 5.7862 | 66.0208 | 0
| 16.2603 | 7.9091 | 90.2423 | 0
| 8.0994 | 4.0241 | 45.915 | 0
| 12.7917 | 6.4674 | 73.7934 | 0
| 2.3629 | 1.1858 | 13.5302 | 0
| 10.8392 | 4.9411 | 56.3775 | 0
| 3.5119 | 1.6171 | 18.4509 | 0
| 0.039372 | 0.020374 | 0.23247 | 0
| 0.80751 | 0.37145 | 4.2382 | 0
| 17.7806 | 8.3828 | 95.6481 | 0
| 1.8226 | 0.73111 | 8.342 | 0
| 18.5915 | 8.0408 | 91.745 | 0
| 5.5314 | 2.5066 | 28.6006 | 0
| 29.4281 | 13.4627 | 153.6092 | 0
| 5.08 | 1.9223 | 21.9334 | 0
| 4.4768 | 1.5699 | 17.913 | 0
| 7.4823 | 3.1416 | 35.8458 | 0
| 38.5694 | 15.3213 | 174.8164 | 0
| 0.60339 | 0.19954 | 2.2767 | 0
| 1.7304 | 0.69693 | 7.9519 | 0
| 5.8943 | 2.4874 | 28.3808 | 0
| 16.0285 | 7.1274 | 81.3241 | 0
| 8.1019 | 2.8854 | 32.9227 | 0
| 5.4273 | 1.9545 | 22.3014 | 0
| 0.92536 | 0.41204 | 4.7014 | 0
| 21.6868 | 8.4684 | 96.6249 | 0
| 20.7464 | 8.4164 | 96.0313 | 0
| 18.0741 | 7.1206 | 81.2465 | 0
| 8.3079 | 2.7653 | 31.5517 | 0
| 16.1491 | 5.8121 | 66.3157 | 0
| 12.074 | 4.3703 | 49.865 | 0
| 22.8335 | 8.7516 | 99.8555 | 0
| 13.1714 | 5.2 | 59.332 | 0
| 0 | 0.082841 | 0.94522 | 0
| 19.2034 | 7.1619 | 81.7175 | 0
| 10.8962 | 4.0927 | 46.6978 | 0
| 42.7003 | 16.1566 | 184.3466 | 0
| 2.1932 | 0.99955 | 11.4048 | 0
| 7.2944 | 2.5439 | 29.0258 | 0
| 12.1474 | 4.5113 | 51.4738 | 0
| 6.319 | 2.3484 | 26.7956 | 0
| 15.5575 | 5.5179 | 62.959 | 0
| 8.9938 | 3.3068 | 37.7308 | 0
| 8.3716 | 3.1353 | 35.7737 | 0
| 4.5851 | 1.6917 | 19.3028 | 0
| 5.4987 | 2.1267 | 24.2658 | 0
| 1.0899 | 0.76169 | 8.6909 | 0
| 2.9685 | 1.0545 | 12.0317 | 0
| 9.7907 | 3.3233 | 37.9184 | 0
| 7.2822 | 2.2121 | 25.2404 | 0
| 2.4592 | 0.84682 | 9.6622 | 0
| 8.6529 | 3.2678 | 37.2853 | 0
| 3.6869 | 1.3876 | 15.833 | 0
| 8.4872 | 3.3892 | 38.6706 | 0
| 7.7772 | 2.9044 | 33.1397 | 0
| 16.8969 | 6.1774 | 70.4843 | 0
| 0.86422 | 0.32112 | 3.6639 | 0
| 10.1348 | 4.0016 | 45.6588 | 0
| 0.10477 | 0.028179 | 0.32152 | 0
| 8.9409 | 3.1742 | 36.2179 | 0
| 9.5064 | 2.972 | 33.9106 | 0
| 19.7285 | 7.0586 | 80.5388 | 0
| 1.5904 | 0.47686 | 5.441 | 0
| 36.2198 | 12.2141 | 139.3626 | 0
| 18.4325 | 6.2898 | 71.7661 | 0
| 27.8704 | 9.8393 | 112.2661 | 0
| 6.7927 | 1.9589 | 22.3506 | 0
| 1.1188 | 0.60598 | 6.9142 | 0
| 0.63982 | 0.44617 | 5.0908 | 0
| 11.4486 | 3.9906 | 45.5326 | 0
| 26.732 | 9.4271 | 107.5638 | 0
| 2.1646 | 0.69692 | 7.9518 | 0
| 0.744 | 0.25621 | 2.9234 | 0
| 7.5055 | 3.1179 | 35.5755 | 0
| 0.016109 | 0.026347 | 0.30062 | 0
| 11.4709 | 3.7702 | 43.0184 | 0
| 5.3451 | 1.6192 | 18.4751 | 0
| 5.0272 | 1.7355 | 19.8022 | 0
| 7.4433 | 2.4292 | 27.7167 | 0
| 4.5387 | 1.5072 | 17.1975 | 0
| 13.8934 | 4.5149 | 51.5151 | 0
| 8.1186 | 2.6537 | 30.2783 | 0
| 11.6351 | 3.8647 | 44.0963 | 0
| 26.596 | 8.669 | 98.913 | 0
| 19.6699 | 6.3025 | 71.9114 | 0
| 0.61239 | 0.21863 | 2.4946 | 0
| 5.7665 | 1.9047 | 21.7321 | 0
| 10.5204 | 2.8989 | 33.0763 | 0
| 7.1775 | 2.4427 | 27.8707 | 0
| 7.7436 | 2.2948 | 26.1833 | 0
| 29.4365 | 9.5205 | 108.6292 | 0
| 0.99205 | 0.30259 | 3.4525 | 0
| 27.7276 | 8.9772 | 102.4304 | 0
| 7.9707 | 2.6418 | 30.1434 | 0
| 19.8721 | 6.2842 | 71.7029 | 0
| 19.7637 | 8.9972 | 102.6582 | 0
| 4.0965 | 1.2 | 13.6923 | 0
| 2.5364 | 0.72907 | 8.3186 | 0
| 0.071662 | 0.0053773 | 0.061355 | 0
| 34.3485 | 9.9885 | 113.9693 | 0
| 40.8368 | 12.0608 | 137.6141 | 0
| 5.2013 | 1.4896 | 16.9958 | 0
| 13.4533 | 4.0369 | 46.0608 | 0
| 6.2972 | 1.8707 | 21.3442 | 0
| 0.0028409 | 0.0039948 | 0.04558 | 0
| 16.137 | 4.8694 | 55.5597 | 0
| 44.1612 | 13.4663 | 153.6506 | 0
| 9.4624 | 2.5746 | 29.3765 | 0
| 11.2245 | 3.1622 | 36.0811 | 0
| 8.4346 | 2.6094 | 29.7729 | 0
| 18.5775 | 5.4469 | 62.1493 | 0
| 7.6712 | 2.4998 | 28.5232 | 0
| 7.8699 | 2.5116 | 28.6568 | 0
| 38.1953 | 11.3689 | 129.7191 | 0
| 0.52179 | 0.32613 | 3.7211 | 0
| 12.1496 | 3.4781 | 39.6849 | 0
| 12.8614 | 3.6691 | 41.8641 | 0
| 14.691 | 4.4522 | 50.7999 | 0
| 14.8409 | 3.9916 | 45.5437 | 0
| 3.5158 | 1.1343 | 12.9425 | 0
| 2.0853 | 0.52242 | 5.9608 | 0
| 0.016571 | 0.0076797 | 0.087626 | 0
| 16.6363 | 4.652 | 53.0794 | 0
| 8.505 | 2.5262 | 28.8238 | 0
| 16.9385 | 5.0054 | 57.1115 | 0
| 6.192 | 1.7547 | 20.0213 | 0
| 22.6501 | 5.5081 | 62.8471 | 0
| 11.3666 | 2.8043 | 31.9975 | 0
| 3.9356 | 1.1385 | 12.9899 | 0
| 10.8157 | 2.8563 | 32.59 | 0
| 9.5167 | 2.6533 | 30.274 | 0
| 0.029873 | 0.0085653 | 0.09773 | 0
| 72.2382 | 19.7827 | 225.7203 | 0
| 8.5438 | 2.2919 | 26.1509 | 0
| 24.5192 | 6.5973 | 75.2752 | 0
| 9.2557 | 2.4178 | 27.5868 | 0
| 1.5223 | 0.36642 | 4.1808 | 0
| 26.7649 | 6.8896 | 78.6101 | 0
| 4.3611 | 1.3002 | 14.8354 | 0
| 4.0705 | 1.1727 | 13.3803 | 0
| 24.6358 | 6.4517 | 73.6137 | 0
| 0.19775 | 0.032593 | 0.37189 | 0
| 1.1684 | 0.33161 | 3.7837 | 0
| 2.0574 | 0.57005 | 6.5043 | 0
| 9.4781 | 2.2502 | 25.6752 | 0
| 14.6161 | 3.8608 | 44.0523 | 0
| 29.9421 | 8.5102 | 97.1014 | 0
| 22.1876 | 5.7413 | 65.5083 | 0
| 20.6065 | 5.3554 | 61.1052 | 0
| 6.6456 | 1.8797 | 21.4477 | 0
| 23.5711 | 6.1582 | 70.2646 | 0
| 0.0039404 | 0.0045037 | 0.051387 | 0
| 17.7888 | 4.6987 | 53.6123 | 0
| 14.8656 | 4.6566 | 53.132 | 0
| 4.389 | 0.90731 | 10.3524 | 0
| 17.1088 | 4.0417 | 46.1161 | 0
| 6.7554 | 2.1303 | 24.3071 | 0
| 8.2448 | 2.0859 | 23.7997 | 0
| 19.6177 | 4.8656 | 55.516 | 0
| 8.062 | 2.1188 | 24.175 | 0
| 34.0025 | 8.4066 | 95.9191 | 0
| 0 | 10.4801 | 119.5775 | 0
| 23.0709 | 5.6966 | 64.9982 | 0
| 2.8622 | 0.55093 | 6.2862 | 0
| 1.4215 | 0.31862 | 3.6354 | 0
| 25.5647 | 6.1639 | 70.3301 | 0
| 14.8875 | 3.6329 | 41.4516 | 0
| 18.7527 | 4.5301 | 51.688 | 0
| 2.9289 | 0.80315 | 9.1639 | 0
| 2.8215 | 0.66951 | 7.6391 | 0
| 2.4112 | 0.58773 | 6.706 | 0
| 27.1674 | 8.0999 | 92.4201 | 0
| 16.5261 | 3.5723 | 40.7604 | 0
| 18.1114 | 4.3275 | 49.3765 | 0
| 11.3098 | 2.6234 | 29.9326 | 0
| 7.553 | 1.806 | 20.6066 | 0
| 16.2171 | 4.0376 | 46.0691 | 0
| 20.9965 | 4.6466 | 53.0173 | 0
| 9.175 | 2.2313 | 25.4595 | 0
| 1.3822 | 0.30225 | 3.4487 | 0
| 40.5539 | 8.3902 | 95.7324 | 0
| 32.5358 | 7.2955 | 83.2412 | 0
| 9.2257 | 1.8944 | 21.6152 | 0
| 12.9561 | 2.7505 | 31.3837 | 0
| 1.8076 | 0.40387 | 4.6081 | 0
| 17.5628 | 3.9291 | 44.8315 | 0
| 4.7928 | 1.1303 | 12.8972 | 0
| 15.5795 | 3.5396 | 40.3873 | 0
| 20.306 | 4.5093 | 51.4513 | 0
| 15.0802 | 3.1381 | 35.8054 | 0
| 4.4649 | 1.0774 | 12.2927 | 0
| 11.7586 | 2.6982 | 30.7867 | 0
| 0.088249 | 0.017436 | 0.19895 | 0
| 18.0519 | 3.7394 | 42.6666 | 0
| 38.8026 | 8.4201 | 96.0729 | 0
| 9.5145 | 2.0527 | 23.4215 | 0
| 30.7751 | 6.7402 | 76.9061 | 0
| 0.9895 | 0.33945 | 3.8732 | 0
| 6.1972 | 1.2865 | 14.6786 | 0
| 10.192 | 2.1651 | 24.7039 | 0
| 9.0779 | 1.9478 | 22.2243 | 0
| 10.7857 | 2.1846 | 24.9266 | 0
| 44.5227 | 9.1483 | 104.3827 | 0
| 3.8991 | 0.91716 | 10.4648 | 0
| 24.6861 | 5.499 | 62.7434 | 0
| 22.0882 | 4.5439 | 51.8464 | 0
| 4.0614 | 0.74233 | 8.47 | 0
| 26.0604 | 5.6481 | 64.4445 | 0
| 9.1551 | 1.8767 | 21.4133 | 0
| 11.3804 | 2.2752 | 25.9598 | 0
| 19.5831 | 3.9784 | 45.3932 | 0
| 12.6514 | 2.6968 | 30.7707 | 0
| 23.1433 | 4.707 | 53.7071 | 0
| 11.2782 | 2.2747 | 25.9549 | 0
| 0.39411 | 0.092936 | 1.0604 | 0
| 24.2446 | 5.168 | 58.9674 | 0
| 11.8855 | 2.5155 | 28.7016 | 0
| 16.5871 | 3.603 | 41.1103 | 0
| 34.4732 | 6.8284 | 77.9121 | 0
| 23.2605 | 4.6905 | 53.5181 | 0
| 5.5208 | 1.5214 | 17.3591 | 0
| 2.6937 | 0.52951 | 6.0417 | 0
| 11.3077 | 2.4553 | 28.0151 | 0
| 32.9798 | 6.6617 | 76.0094 | 0
| 27.7557 | 5.5702 | 63.5559 | 0
| 1.6684 | 0.3405 | 3.8851 | 0
| 0.61466 | 0.099344 | 1.1335 | 0
| 0.92301 | 0.40035 | 4.568 | 0
| 17.2109 | 3.4528 | 39.396 | 0
| 4.2251 | 0.72736 | 8.2992 | 0
| 7.023 | 1.454 | 16.5898 | 0
| 9.3206 | 1.7933 | 20.4621 | 0
| 1.8362 | 0.39784 | 4.5393 | 0
| 40.8008 | 8.1347 | 92.8172 | 0
| 22.5363 | 4.3672 | 49.8299 | 0
| 20.922 | 4.1676 | 47.5523 | 0
| 6.2202 | 1.1004 | 12.5552 | 0
| 4.6389 | 0.883 | 10.075 | 0
| 7.2684 | 1.6882 | 19.2625 | 0
| 3.0199 | 0.61899 | 7.0627 | 0
| 15.6695 | 2.8082 | 32.042 | 0
| 42.1728 | 8.2978 | 94.6777 | 0
| 33.2034 | 6.9264 | 79.0305 | 0
| 11.196 | 2.0444 | 23.3264 | 0
| 18.4629 | 3.4436 | 39.2912 | 0
| 67.3977 | 12.3186 | 140.5547 | 0
| 5.5262 | 0.77456 | 8.8378 | 0
| 40.268 | 7.3703 | 84.095 | 0
| 9.6029 | 1.9757 | 22.5428 | 0
| 21.6978 | 3.9191 | 44.7174 | 0
| 6.5279 | 1.1933 | 13.615 | 0
| 7.8055 | 1.4071 | 16.0548 | 0
| 18.6941 | 4.0058 | 45.706 | 0
| 0.10465 | 0.039316 | 0.4486 | 0
| 11.5892 | 2.0895 | 23.8415 | 0
| 8.6815 | 1.5936 | 18.1825 | 0
| 4.9856 | 0.85756 | 9.7847 | 0
| 39.0254 | 7.2273 | 82.4633 | 0
| 4.8784 | 0.94852 | 10.8226 | 0
| 2.2233 | 0.58663 | 6.6934 | 0
| 10.3312 | 1.8269 | 20.8446 | 0
| 8.3152 | 1.5526 | 17.715 | 0
| 2.9513 | 0.57446 | 6.5546 | 0
| 17.8564 | 3.2182 | 36.7194 | 0
| 27.8853 | 4.8836 | 55.7214 | 0
| 25.0232 | 4.6572 | 53.1392 | 0
| 0 | 0.070764 | 0.80741 | 0
| 25.7752 | 4.6454 | 53.0037 | 0
| 37.8058 | 7.1842 | 81.9722 | 0
| 8.4704 | 1.5815 | 18.0444 | 0
| 6.7157 | 1.0615 | 12.1117 | 0
| 29.9752 | 5.2773 | 60.2145 | 0
| 10.3969 | 1.7281 | 19.7178 | 0
| 21.3779 | 3.5001 | 39.9359 | 0
| 22.4116 | 3.7097 | 42.3271 | 0
| 25.7663 | 4.4306 | 50.5527 | 0
| 13.1577 | 2.3194 | 26.4639 | 0
| 12.7357 | 2.9989 | 34.2174 | 0
| 4.165 | 0.68401 | 7.8046 | 0
| 6.569 | 1.1531 | 13.1571 | 0
| 0.54018 | 0.70912 | 8.091 | 0
| 7.4973 | 1.7973 | 20.5071 | 0
| 0 | 0.0029731 | 0.033923 | 0
| 56.7518 | 9.1862 | 104.815 | 0
| 1.8419 | 0.30164 | 3.4417 | 0
| 0.044275 | 0.004434 | 0.050592 | 0
| 28.6377 | 4.7198 | 53.8534 | 0
| 23.6132 | 3.7414 | 42.6893 | 0
| 3.7017 | 1.374 | 15.6773 | 0
| 37.0433 | 6.6596 | 75.9861 | 0
| 11.4277 | 1.9522 | 22.2741 | 0
| 3.39 | 0.55914 | 6.3798 | 0
| 0 | 0.56788 | 6.4795 | 0
| 7.8564 | 1.3252 | 15.121 | 0
| 4.5495 | 0.79754 | 9.0999 | 0
| 9.501 | 2.8863 | 32.9322 | 0
| 10.7568 | 1.8222 | 20.7918 | 0
| 11.8267 | 1.8969 | 21.6431 | 0
| 8.9988 | 1.6429 | 18.7452 | 0
| 22.9909 | 3.7702 | 43.0177 | 0
| 2.4103 | 0.40181 | 4.5847 | 0
| 49.2752 | 7.8646 | 89.7355 | 0
| 0.68994 | 0.14052 | 1.6034 | 0
| 0.0028409 | 0.0042469 | 0.048457 | 0
| 18.5169 | 3.0122 | 34.3695 | 0
| 3.8797 | 0.61665 | 7.036 | 0
| 18.5411 | 3.3166 | 37.8418 | 0
| 13.3552 | 2.1236 | 24.2297 | 0
| 15.5924 | 2.79 | 31.8337 | 0
| 14.1556 | 2.1718 | 24.7803 | 0
| 0 | 0.10793 | 1.2315 | 0
| 27.4895 | 4.2348 | 48.3194 | 0
| 0.69202 | 0.090924 | 1.0374 | 0
| 30.4763 | 4.6291 | 52.8178 | 0
| 6.4061 | 1.3196 | 15.0563 | 0
| 8.4518 | 1.3936 | 15.9014 | 0
| 24.3799 | 3.6385 | 41.515 | 0
| 9.7875 | 1.458 | 16.6357 | 0
| 6.2789 | 0.95872 | 10.939 | 0
| 5.4199 | 0.87564 | 9.9911 | 0
| 6.5391 | 0.88667 | 10.1169 | 0
| 5.0707 | 0.73461 | 8.3819 | 0
| 0 | 0.098398 | 1.1227 | 0
| 23.4846 | 3.5048 | 39.9897 | 0
| 25.8212 | 4.3468 | 49.5966 | 0
| 0.95563 | 0.30856 | 3.5207 | 0
| 2.1931 | 0.47474 | 5.4167 | 0
| 0.48966 | 0.031202 | 0.35601 | 0
| 5.4167 | 0.83217 | 9.4951 | 0
| 10.7057 | 1.9436 | 22.177 | 0
| 10.9472 | 1.5153 | 17.2898 | 0
| 14.4338 | 1.8935 | 21.6054 | 0
| 0.35198 | 0.33636 | 3.8379 | 0
| 1.9232 | 0.69827 | 7.9673 | 0
| 15.3439 | 2.4979 | 28.5007 | 0
| 9.1539 | 1.4733 | 16.81 | 0
| 8.4592 | 1.351 | 15.4146 | 0
| 2.5774 | 0.49264 | 5.621 | 0
| 13.7502 | 2.0445 | 23.3273 | 0
| 5.1632 | 0.75527 | 8.6176 | 0
| 10.7892 | 1.419 | 16.1907 | 0
| 12.4632 | 1.6896 | 19.2781 | 0
| 21.7253 | 3.26 | 37.197 | 0
| 4.1597 | 1.3091 | 14.9367 | 0
| 58.5893 | 8.3015 | 94.7205 | 0
| 6.3579 | 0.9419 | 10.747 | 0
| 8.0409 | 1.2898 | 14.7161 | 0
| 18.9786 | 2.3859 | 27.2227 | 0
| 19.9124 | 2.8022 | 31.9736 | 0
| 30.0461 | 3.8876 | 44.3575 | 0
| 0.090317 | 0.018318 | 0.20901 | 0
| 15.3394 | 1.9083 | 21.7743 | 0
| 42.2883 | 5.6908 | 64.9319 | 0
| 11.9402 | 1.6639 | 18.9846 | 0
| 0.017476 | 0.0036317 | 0.041437 | 0
| 6.4769 | 1.0286 | 11.736 | 0
| 0.55916 | 0.21647 | 2.4699 | 0
| 3.0901 | 0.41642 | 4.7514 | 0
| 0.0088181 | 0.017803 | 0.20313 | 0
| 3.9951 | 0.52893 | 6.0351 | 0
| 4.5264 | 0.75852 | 8.6548 | 0
| 0.015735 | 0.74782 | 8.5326 | 0
| 12.1398 | 1.6721 | 19.0792 | 0
| 3.2441 | 0.76041 | 8.6763 | 0
| 16.8067 | 2.2849 | 26.0712 | 0
| 49.234 | 6.4724 | 73.85 | 0
| 9.4733 | 1.2847 | 14.6587 | 0
| 21.7807 | 3.0276 | 34.5453 | 0
| 42.84 | 5.6397 | 64.3494 | 0
| 21.7138 | 2.6799 | 30.5778 | 0
| 4.5563 | 0.59511 | 6.7902 | 0
| 4.3071 | 0.78476 | 8.9541 | 0
| 2.1814 | 0.3893 | 4.4419 | 0
| 19.7056 | 3.0694 | 35.0219 | 0
| 12.9647 | 1.6294 | 18.5912 | 0
| 15.4386 | 2.4068 | 27.4616 | 0
| 23.2453 | 2.8812 | 32.8747 | 0
| 12.8151 | 1.6664 | 19.0139 | 0
| 39.8103 | 4.9366 | 56.3263 | 0
| 10.8617 | 1.448 | 16.5215 | 0
| 32.3938 | 4.0421 | 46.1205 | 0
| 3.5347 | 0.39809 | 4.5422 | 0
| 7.9849 | 0.9628 | 10.9856 | 0
| 9.3362 | 1.1007 | 12.5595 | 0
| 0.30776 | 0.094496 | 1.0782 | 0
| 6.6197 | 0.80167 | 9.147 | 0
| 35.6795 | 4.4607 | 50.8968 | 0
| 0.57064 | 0.51168 | 5.8383 | 0
| 2.134 | 0.33168 | 3.7845 | 0
| 14.6745 | 1.6855 | 19.2318 | 0
| 0.032736 | 0.0033439 | 0.038154 | 0
| 11.2878 | 1.3404 | 15.2934 | 0
| 5.4912 | 0.69174 | 7.8927 | 0
| 7.0338 | 1.184 | 13.5097 | 0
| 3.9474 | 0.47636 | 5.4352 | 0
| 30.4123 | 3.9444 | 45.0057 | 0
| 12.9075 | 2.0814 | 23.7484 | 0
| 9.6082 | 1.1454 | 13.0685 | 0
| 3.9587 | 0.60866 | 6.9448 | 0
| 22.5045 | 2.9322 | 33.4569 | 0
| 1.4275 | 0.18799 | 2.145 | 0
| 22.9631 | 2.8396 | 32.4 | 0
| 22.1968 | 2.823 | 32.2103 | 0
| 7.7922 | 0.88227 | 10.0667 | 0
| 58.0531 | 7.3153 | 83.4673 | 0
| 20.5311 | 2.6087 | 29.7655 | 0
| 6.2161 | 0.92756 | 10.5834 | 0
| 7.061 | 0.82689 | 9.4349 | 0
| 15.6243 | 1.97 | 22.4781 | 0
| 22.8171 | 2.8422 | 32.4295 | 0
| 15.6144 | 1.9143 | 21.8416 | 0
| 23.2445 | 4.9208 | 56.1464 | 0
| 25.2459 | 3.1761 | 36.2391 | 0
| 14.1863 | 1.6489 | 18.8144 | 0
| 3.9248 | 0.49186 | 5.6121 | 0
| 0 | 2.4089 | 27.485 | 0
| 3.6398 | 0.48148 | 5.4936 | 0
| 1.8246 | 0.2907 | 3.3169 | 0
| 20.5939 | 2.2461 | 25.6278 | 0
| 8.5355 | 2.2239 | 25.3751 | 0
| 31.8408 | 3.8274 | 43.6708 | 0
| 4.7055 | 0.56237 | 6.4167 | 0
| 6.4052 | 0.77683 | 8.8637 | 0
| 2.1786 | 0.18998 | 2.1676 | 0
| 19.7775 | 2.3444 | 26.75 | 0
| 3.7523 | 0.42157 | 4.8101 | 0
| 16.1136 | 1.699 | 19.3858 | 0
| 2.48 | 0.55565 | 6.3399 | 0
| 8.6721 | 0.99117 | 11.3092 | 0
| 22.9732 | 2.5845 | 29.4893 | 0
| 2.2947 | 0.66279 | 7.5625 | 0
| 56.3478 | 6.9934 | 79.7946 | 0
| 0.056359 | 0.0089361 | 0.10196 | 0
| 15.3136 | 1.702 | 19.4196 | 0
| 0 | 0.0089051 | 0.10161 | 0
| 40.7468 | 4.5255 | 51.6364 | 0
| 5.0284 | 0.60937 | 6.9529 | 0
| 32.1085 | 3.6988 | 42.2036 | 0
| 8.5868 | 1.0091 | 11.5134 | 0
| 0.47121 | 0.10008 | 1.142 | 0
| 43.1507 | 4.6374 | 52.913 | 0
| 34.5864 | 3.9253 | 44.7874 | 0
| 30.8506 | 3.2992 | 37.6443 | 0
| 2.8805 | 0.31202 | 3.5601 | 0
| 1.172 | 0.11348 | 1.2948 | 0
| 17.8016 | 1.8758 | 21.4024 | 0
| 7.4909 | 0.77894 | 8.8877 | 0
| 32.4204 | 3.3868 | 38.6439 | 0
| 1.312 | 0.17079 | 1.9487 | 0
| 30.673 | 3.2715 | 37.3273 | 0
| 12.66 | 1.4884 | 16.9823 | 0
| 24.7972 | 2.9718 | 33.9084 | 0
| 50.5334 | 6.2306 | 71.0913 | 0
| 6.5479 | 0.72762 | 8.3022 | 0
| 6.3614 | 1.1884 | 13.5592 | 0
| 4.8788 | 0.52753 | 6.0191 | 0
| 1.7797 | 0.22292 | 2.5435 | 0
| 7.5312 | 0.84105 | 9.5964 | 0
| 9.7743 | 1.3505 | 15.4095 | 0
| 15.178 | 2.3544 | 26.864 | 0
| 25.856 | 2.7427 | 31.2941 | 0
| 17.3082 | 1.8352 | 20.9393 | 0
| 0 | 3.9475 | 45.0412 | 0
| 20.0606 | 2.1761 | 24.8296 | 0
| 1.7906 | 0.17322 | 1.9765 | 0
| 12.0281 | 1.1838 | 13.5074 | 0
| 38.1845 | 3.737 | 42.6392 | 0
| 15.2038 | 1.6075 | 18.342 | 0
| 3.0198 | 0.41242 | 4.7057 | 0
| 0.75301 | 0.03513 | 0.40083 | 0
| 11.1325 | 3.3152 | 37.8264 | 0
| 4.2094 | 0.67207 | 7.6683 | 0
| 62.309 | 6.1299 | 69.9417 | 0
| 3.1855 | 0.30459 | 3.4754 | 0
| 29.9322 | 2.9179 | 33.2938 | 0
| 6.6295 | 0.72013 | 8.2167 | 0
| 13.4094 | 1.2557 | 14.3278 | 0
| 12.417 | 1.8656 | 21.2864 | 0
| 17.579 | 1.8301 | 20.8812 | 0
| 4.3358 | 0.37734 | 4.3054 | 0
| 33.6774 | 3.5156 | 40.1127 | 0
| 22.878 | 2.2695 | 25.8953 | 0
| 5.6679 | 0.679 | 7.7474 | 0
| 0.68367 | 0.11709 | 1.336 | 0
| 12.1456 | 1.2731 | 14.5265 | 0
| 25.1559 | 2.6218 | 29.9146 | 0
| 19.2145 | 1.8003 | 20.5414 | 0
| 16.3125 | 1.9787 | 22.5768 | 0
| 1.3237 | 0.11115 | 1.2682 | 0
| 10.6401 | 1.1058 | 12.6168 | 0
| 25.5192 | 3.0756 | 35.0928 | 0
| 5.0942 | 0.4505 | 5.1402 | 0
| 28.7063 | 2.6869 | 30.6577 | 0
| 10.8056 | 1.0326 | 11.7817 | 0
| 26.9663 | 2.4841 | 28.344 | 0
| 1.2333 | 0.29162 | 3.3274 | 0
| 10.9115 | 1.1147 | 12.7185 | 0
| 2.2219 | 0.18151 | 2.071 | 0
| 7.8751 | 0.76545 | 8.7338 | 0
| 25.7416 | 2.4997 | 28.5218 | 0
| 4.4959 | 0.36644 | 4.1811 | 0
| 12.4416 | 1.1896 | 13.5728 | 0
| 9.711 | 1.5715 | 17.9313 | 0
| 16.8985 | 1.6368 | 18.6764 | 0
| 22.4309 | 2.1025 | 23.9891 | 0
| 1.9282 | 0.18459 | 2.1062 | 0
| 21.8671 | 2.0124 | 22.9612 | 0
| 6.1596 | 0.62103 | 7.0859 | 0
| 1.8021 | 0.27276 | 3.1122 | 0
| 24.1641 | 2.3269 | 26.5504 | 0
| 0.7888 | 0.064762 | 0.73894 | 0
| 1.8423 | 0.18677 | 2.131 | 0
| 4.2802 | 0.38345 | 4.3751 | 0
| 17.7529 | 1.5919 | 18.1635 | 0
| 8.3678 | 0.62264 | 7.1044 | 0
| 0 | 2.5119 | 28.6611 | 0
| 28.1463 | 2.4367 | 27.8028 | 0
| 2.8406 | 0.28083 | 3.2042 | 0
| 13.9807 | 1.3577 | 15.4915 | 0
| 34.0518 | 3.1805 | 36.2891 | 0
| 3.0421 | 0.30781 | 3.5121 | 0
| 37.1096 | 3.6726 | 41.904 | 0
| 3.6961 | 0.34403 | 3.9253 | 0
| 0.41471 | 0.038987 | 0.44484 | 0
| 3.8443 | 0.4337 | 4.9485 | 0
| 57.3548 | 5.3137 | 60.6295 | 0
| 17.0252 | 1.4187 | 16.187 | 0
| 0.072712 | 0.5907 | 6.7399 | 0
| 1.3195 | 0.22171 | 2.5297 | 0
| 6.2878 | 0.60958 | 6.9553 | 0
| 0.032317 | 0.0024055 | 0.027447 | 0
| 3.3692 | 0.31235 | 3.5639 | 0
| 0.19546 | 0.022418 | 0.25579 | 0
| 3.1243 | 0.70437 | 8.0368 | 0
| 10.0507 | 1.5705 | 17.9189 | 0
| 7.3435 | 0.6491 | 7.4062 | 0
| 4.8632 | 0.46069 | 5.2565 | 0
| 44.8681 | 3.8105 | 43.4783 | 0
| 8.3751 | 0.72591 | 8.2826 | 0
| 5.6891 | 0.52281 | 5.9652 | 0
| 1.2084 | 0.11007 | 1.2559 | 0
| 30.1651 | 3.5307 | 40.2852 | 0
| 2.9793 | 0.30076 | 3.4317 | 0
| 9.2087 | 0.81552 | 9.3051 | 0
| 7.9156 | 0.72193 | 8.2372 | 0
| 2.7245 | 0.48316 | 5.5128 | 0
| 9.3769 | 0.8593 | 9.8047 | 0
| 19.1149 | 1.7074 | 19.4814 | 0
| 20.5037 | 1.7325 | 19.768 | 0
| 6.9909 | 0.57499 | 6.5607 | 0
| 6.0828 | 0.69087 | 7.8828 | 0
| 48.5241 | 4.2611 | 48.6192 | 0
| 29.3636 | 2.5079 | 28.6148 | 0
| 8.0911 | 0.69236 | 7.8998 | 0
| 15.1524 | 1.818 | 20.7437 | 0
| 13.9689 | 1.1553 | 13.1824 | 0
| 1.0869 | 0.092658 | 1.0572 | 0
| 3.6144 | 0.38832 | 4.4307 | 0
| 8.9415 | 0.73046 | 8.3345 | 0
| 7.5044 | 0.68558 | 7.8225 | 0
| 16.2413 | 1.7341 | 19.7858 | 0
| 5.5101 | 0.45572 | 5.1998 | 0
| 0.8654 | 0.15858 | 1.8094 | 0
| 2.8007 | 0.34523 | 3.939 | 0
| 0.43655 | 0.042305 | 0.4827 | 0
| 9.4194 | 0.8233 | 9.3939 | 0
| 6.4816 | 0.55981 | 6.3874 | 0
| 16.4398 | 1.4182 | 16.1821 | 0
| 0.032241 | 0.0044269 | 0.050511 | 0
| 1.1372 | 0.092652 | 1.0572 | 0
| 14.9282 | 1.2139 | 13.8511 | 0
| 0.4876 | 0.16045 | 1.8308 | 0
| 12.5404 | 1.1033 | 12.5881 | 0
| 17.2538 | 1.4061 | 16.0431 | 0
| 0.060309 | 0.0043865 | 0.05005 | 0
| 0.4879 | 0.041647 | 0.47519 | 0
| 4.9863 | 0.39189 | 4.4714 | 0
| 35.16 | 3.0505 | 34.806 | 0
| 3.5255 | 0.26875 | 3.0664 | 0
| 4.4179 | 0.38876 | 4.4358 | 0
| 47.5255 | 3.9242 | 44.7746 | 0
| 14.1242 | 1.1784 | 13.445 | 0
| 12.5464 | 1.0402 | 11.8692 | 0
| 13.6416 | 1.1117 | 12.6845 | 0
| 3.7796 | 0.29636 | 3.3814 | 0
| 2.7541 | 0.19172 | 2.1875 | 0
| 20.5594 | 1.7216 | 19.6431 | 0
| 3.6066 | 0.37431 | 4.2709 | 0
| 7.0398 | 0.51502 | 5.8764 | 0
| 13.4764 | 1.1808 | 13.4728 | 0
| 5.0355 | 0.43499 | 4.9633 | 0
| 9.7839 | 0.87153 | 9.9441 | 0
| 0.019382 | 0.0021247 | 0.024242 | 0
| 25.0604 | 1.8213 | 20.7809 | 0
| 30.6011 | 2.4655 | 28.1313 | 0
| 5.2084 | 0.42223 | 4.8176 | 0
| 0.14266 | 0.0094707 | 0.10806 | 0
| 5.644 | 0.46087 | 5.2585 | 0
| 0.6657 | 0.091819 | 1.0477 | 0
| 29.6769 | 2.1395 | 24.4116 | 0
| 6.4128 | 0.64014 | 7.304 | 0
| 3.3377 | 0.42851 | 4.8892 | 0
| 1.933 | 0.15431 | 1.7607 | 0
| 20.4569 | 1.6284 | 18.5804 | 0
| 6.6314 | 0.52243 | 5.9609 | 0
| 9.164 | 0.78468 | 8.9533 | 0
| 2.1018 | 1.7174 | 19.5958 | 0
| 7.2439 | 1.0389 | 11.8538 | 0
| 24.6511 | 1.8913 | 21.5794 | 0
| 26.6671 | 2.2309 | 25.4544 | 0
| 25.261 | 2.0315 | 23.1795 | 0
| 0.67213 | 0.059675 | 0.68089 | 0
| 19.5865 | 1.5609 | 17.81 | 0
| 20.2812 | 2.0614 | 23.5206 | 0
| 5.6723 | 0.42457 | 4.8443 | 0
| 1.9052 | 0.14328 | 1.6348 | 0
| 1.2608 | 0.10018 | 1.143 | 0
| 15.7815 | 1.3065 | 14.907 | 0
| 0.0022449 | 0.0020372 | 0.023244 | 0
| 9.5969 | 0.76421 | 8.7197 | 0
| 18.4885 | 1.4142 | 16.1356 | 0
| 18.7461 | 1.4715 | 16.7893 | 0
| 0.37741 | 0.035477 | 0.40479 | 0
| 0.061054 | 0.0053447 | 0.060983 | 0
| 2.6586 | 0.16471 | 1.8794 | 0
| 16.1465 | 1.1006 | 12.558 | 0
| 8.4394 | 0.76764 | 8.7588 | 0
| 4.9394 | 0.38121 | 4.3496 | 0
| 3.3373 | 0.24669 | 2.8148 | 0
| 2.4949 | 0.20015 | 2.2837 | 0
| 8.0109 | 0.55825 | 6.3696 | 0
| 0.31098 | 0.025443 | 0.2903 | 0
| 10.5312 | 1.389 | 15.8486 | 0
| 0.9386 | 0.13498 | 1.5401 | 0
| 24.8051 | 1.8864 | 21.5242 | 0
| 6.4334 | 0.51975 | 5.9303 | 0
| 9.6784 | 0.71884 | 8.202 | 0
| 20.0726 | 1.5483 | 17.6665 | 0
| 25.3115 | 1.8366 | 20.9555 | 0
| 1.7106 | 0.1248 | 1.4239 | 0
| 33.7199 | 2.9612 | 33.7875 | 0
| 0.83906 | 0.11878 | 1.3553 | 0
| 10.2572 | 0.74556 | 8.5069 | 0
| 17.7758 | 1.6618 | 18.9617 | 0
| 26.17 | 1.8871 | 21.5323 | 0
| 3.1838 | 0.24138 | 2.7541 | 0
| 33.1518 | 2.382 | 27.1787 | 0
| 5.3899 | 0.80868 | 9.2271 | 0
| 7.7169 | 0.50513 | 5.7635 | 0
| 1.099 | 0.078881 | 0.90003 | 0
| 5.1559 | 0.40747 | 4.6492 | 0
| 2.8294 | 0.39356 | 4.4905 | 0
| 0.011895 | 0.072692 | 0.82941 | 0
| 0.13067 | 0.022108 | 0.25226 | 0
| 0 | 0.058696 | 0.66973 | 0
| 1.4938 | 0.10761 | 1.2278 | 0
| 10.9398 | 0.73735 | 8.4132 | 0
| 2.743 | 0.16757 | 1.912 | 0
| 41.8421 | 2.9234 | 33.3556 | 0
| 43.6095 | 3.0095 | 34.3384 | 0
| 17.6671 | 1.2604 | 14.381 | 0
| 6.793 | 0.45956 | 5.2436 | 0
| 31.8905 | 2.3541 | 26.8601 | 0
| 0.031767 | 0.0056179 | 0.064101 | 0
| 19.7418 | 1.436 | 16.3849 | 0
| 1.4934 | 0.0835 | 0.95273 | 0
| 7.4911 | 0.37291 | 4.2549 | 0
| 15.8794 | 1.2323 | 14.0604 | 0
| 7.3858 | 0.55677 | 6.3528 | 0
| 31.663 | 2.1392 | 24.4088 | 0
| 5.4808 | 0.41619 | 4.7487 | 0
| 5.6643 | 0.40492 | 4.6202 | 0
| 24.5117 | 1.7297 | 19.7356 | 0
| 12.6486 | 0.86779 | 9.9014 | 0
| 5.0525 | 0.36784 | 4.1971 | 0
| 4.4768 | 0.27831 | 3.1755 | 0
| 10.9898 | 0.73644 | 8.4028 | 0
| 3.3532 | 0.23075 | 2.6329 | 0
| 0.019568 | 0.0036302 | 0.041421 | 0
| 0.17109 | 0.0036217 | 0.041324 | 0
| 5.5502 | 0.77455 | 8.8376 | 0
| 5.7379 | 0.35348 | 4.0333 | 0
| 36.0397 | 2.4054 | 27.446 | 0
| 39.4357 | 2.5643 | 29.2585 | 0
| 12.3959 | 1.0556 | 12.0445 | 0
| 48.9583 | 3.3665 | 38.4123 | 0
| 34.2805 | 2.2859 | 26.082 | 0
| 27.183 | 1.8608 | 21.2314 | 0
| 0.071759 | 0.040454 | 0.46158 | 0
| 40.9123 | 2.6578 | 30.3254 | 0
| 0.32009 | 0.040997 | 0.46777 | 0
| 0 | 0.048084 | 0.54864 | 0
| 10.8614 | 0.78785 | 8.9894 | 0
| 4.7411 | 0.24832 | 2.8333 | 0
| 1.0286 | 0.18894 | 2.1558 | 0
| 18.1219 | 1.2101 | 13.8067 | 0
| 13.9602 | 2.0078 | 22.9094 | 0
| 9.5996 | 0.69415 | 7.9202 | 0
| 0.83099 | 0.19901 | 2.2707 | 0
| 3.7458 | 0.28087 | 3.2047 | 0
| 2.0955 | 0.17185 | 1.9608 | 0
| 2.0742 | 0.12791 | 1.4594 | 0
| 11.3874 | 0.77873 | 8.8853 | 0
| 5.7746 | 0.4679 | 5.3387 | 0
| 0.63001 | 0.14482 | 1.6524 | 0
| 25.0617 | 1.5574 | 17.7704 | 0
| 34.5964 | 2.2856 | 26.0792 | 0
| 0.39955 | 0.10835 | 1.2363 | 0
| 5.3571 | 0.36446 | 4.1585 | 0
| 0 | 2.3431 | 26.7344 | 0
| 1.8588 | 0.13539 | 1.5448 | 0
| 8.4829 | 0.56284 | 6.422 | 0
| 13.1144 | 1.2599 | 14.3758 | 0
| 20.5246 | 1.291 | 14.7299 | 0
| 34.2671 | 2.1858 | 24.9398 | 0
| 6.9057 | 1.106 | 12.6196 | 0
| 4.8983 | 0.32883 | 3.752 | 0
| 2.6699 | 0.19149 | 2.1849 | 0
| 2.0969 | 0.15221 | 1.7367 | 0
| 0 | 0.50125 | 5.7192 | 0
| 5.5818 | 0.36613 | 4.1775 | 0
| 10.7416 | 0.75027 | 8.5606 | 0
| 0.9809 | 0.10228 | 1.167 | 0
| 14.3169 | 1.0034 | 11.4487 | 0
| 17.2538 | 1.2503 | 14.2662 | 0
| 4.6775 | 0.26172 | 2.9862 | 0
| 17.1506 | 1.0114 | 11.5397 | 0
| 0.57686 | 0.32449 | 3.7024 | 0
| 2.3577 | 0.15814 | 1.8044 | 0
| 6.9025 | 0.39158 | 4.4679 | 0
| 7.3225 | 0.44031 | 5.0239 | 0
| 9.5222 | 0.8627 | 9.8434 | 0
| 38.2398 | 2.6673 | 30.4334 | 0
| 6.3232 | 0.4025 | 4.5925 | 0
| 4.0007 | 0.24384 | 2.7823 | 0
| 4.2927 | 0.23442 | 2.6748 | 0
| 14.2279 | 1.2513 | 14.2772 | 0
| 5.856 | 0.71296 | 8.1349 | 0
| 27.204 | 1.9967 | 22.7818 | 0
| 7.3199 | 0.56488 | 6.4453 | 0
| 2.7983 | 0.18075 | 2.0624 | 0
| 26.1821 | 1.6141 | 18.4165 | 0
| 7.4685 | 0.43394 | 4.9513 | 0
| 36.7614 | 2.2732 | 25.9376 | 0
| 1.6265 | 0.10746 | 1.2262 | 0
| 4.6558 | 0.25959 | 2.9619 | 0
| 4.4966 | 0.24032 | 2.742 | 0
| 16.8402 | 1.0956 | 12.5009 | 0
| 4.0873 | 0.23928 | 2.7302 | 0
| 2.8669 | 0.18492 | 2.11 | 0
| 19.2731 | 1.2001 | 13.6929 | 0
| 0.14381 | 0.017483 | 0.19948 | 0
| 0.039035 | 0.0015889 | 0.018129 | 0
| 18.4694 | 1.1306 | 12.9007 | 0
| 19.5836 | 1.128 | 12.8707 | 0
| 9.7643 | 0.56693 | 6.4687 | 0
| 6.9806 | 0.45562 | 5.1987 | 0
| 3.5962 | 0.1781 | 2.0321 | 0
| 6.4695 | 0.37768 | 4.3094 | 0
| 17.0865 | 1.0316 | 11.7701 | 0
| 0.45402 | 0.012049 | 0.13747 | 0
| 0.16783 | 0.275 | 3.1378 | 0
| 4.0307 | 0.23086 | 2.6341 | 0
| 13.0525 | 0.98962 | 11.2916 | 0
| 4.8506 | 0.39472 | 4.5037 | 0
| 11.9072 | 0.64949 | 7.4107 | 0
| 11.2076 | 0.72056 | 8.2216 | 0
| 12.3794 | 0.86558 | 9.8763 | 0
| 21.7811 | 1.2983 | 14.8141 | 0
| 3.8551 | 1.0125 | 11.5524 | 0
| 0 | 1.5334 | 17.4961 | 0
| 7.0953 | 0.42814 | 4.885 | 0
| 10.6784 | 0.81284 | 9.2745 | 0
| 18.3909 | 2.1321 | 24.3272 | 0
| 5.7585 | 0.31165 | 3.5559 | 0
| 4.2985 | 0.29283 | 3.3412 | 0
| 4.7211 | 0.52506 | 5.9909 | 0
| 7.4825 | 0.43562 | 4.9704 | 0
| 0.58281 | 0.033192 | 0.37872 | 0
| 28.2995 | 1.6683 | 19.0348 | 0
| 3.4896 | 0.37494 | 4.2781 | 0
| 11.1491 | 0.57553 | 6.5668 | 0
| 0.34934 | 0.022724 | 0.25928 | 0
| 8.4313 | 0.48772 | 5.5649 | 0
| 9.3645 | 0.63652 | 7.2626 | 0
| 12.1344 | 0.61936 | 7.0669 | 0
| 3.95 | 0.21464 | 2.4491 | 0
| 13.8949 | 0.83297 | 9.5041 | 0
| 6.9165 | 0.41133 | 4.6933 | 0
| 0.01394 | 0.001492 | 0.017024 | 0
| 4.9842 | 0.2745 | 3.1321 | 0
| 7.575 | 0.39629 | 4.5216 | 0
| 67.8274 | 3.8322 | 43.7254 | 0
| 4.7512 | 0.27134 | 3.096 | 0
| 7.5557 | 0.45246 | 5.1626 | 0
| 8.682 | 0.47864 | 5.4613 | 0
| 2.0597 | 0.20661 | 2.3574 | 0
| 0.038172 | 0.0029581 | 0.033752 | 0
| 4.8408 | 0.26586 | 3.0334 | 0
| 0.84238 | 0.12062 | 1.3763 | 0
| 0.23697 | 0.010266 | 0.11714 | 0
| 11.5881 | 0.63175 | 7.2083 | 0
| 16.2867 | 0.9918 | 11.3164 | 0
| 7.3322 | 0.44189 | 5.042 | 0
| 9.7943 | 0.45194 | 5.1566 | 0
| 1.0965 | 0.068731 | 0.78422 | 0
| 19.4256 | 1.1071 | 12.6316 | 0
| 0.32165 | 0.0065696 | 0.074959 | 0
| 32.6577 | 1.8513 | 21.1238 | 0
| 2.5925 | 0.11491 | 1.3111 | 0
| 7.7217 | 0.70754 | 8.073 | 0
| 0.58504 | 0.11025 | 1.258 | 0
| 44.6552 | 3.1066 | 35.4458 | 0
| 0.54687 | 0.092186 | 1.0518 | 0
| 5.8128 | 0.31808 | 3.6293 | 0
| 7.6765 | 0.45976 | 5.2458 | 0
| 11.1212 | 0.62271 | 7.1051 | 0
| 11.9433 | 0.94568 | 10.7902 | 0
| 4.3091 | 0.20752 | 2.3678 | 0
| 1.8041 | 0.11761 | 1.3419 | 0
| 19.6562 | 1.5225 | 17.3717 | 0
| 7.4045 | 0.37589 | 4.2889 | 0
| 3.6028 | 0.34238 | 3.9065 | 0
| 7.3727 | 0.37084 | 4.2313 | 0
| 1.4555 | 0.066805 | 0.76225 | 0
| 8.453 | 0.39349 | 4.4898 | 0
| 2.2107 | 0.062463 | 0.7127 | 0
| 19.0404 | 1.3598 | 15.5151 | 0
| 10.5504 | 0.54832 | 6.2563 | 0
| 25.1102 | 1.2833 | 14.6429 | 0
| 12.2965 | 0.60183 | 6.8669 | 0
| 6.9143 | 0.4462 | 5.0912 | 0
| 5.8779 | 0.32534 | 3.7121 | 0
| 8.1279 | 0.55855 | 6.373 | 0
| 11.6452 | 0.58223 | 6.6432 | 0
| 10.2621 | 0.56862 | 6.488 | 0
| 14.7043 | 0.76244 | 8.6994 | 0
| 0.26241 | 0.047097 | 0.53737 | 0
| 38.8077 | 2.2679 | 25.8766 | 0
| 0.42602 | 0.89955 | 10.2639 | 0
| 38.8217 | 2.024 | 23.0939 | 0
| 0.63916 | 0.032616 | 0.37215 | 0
| 0.01856 | 0.0068874 | 0.078585 | 0
| 0.61763 | 0.061821 | 0.70538 | 0
| 26.3778 | 1.367 | 15.5979 | 0
| 2.4649 | 0.076264 | 0.87017 | 0
| 6.2338 | 0.31891 | 3.6387 | 0
| 10.5256 | 0.65667 | 7.4927 | 0
| 0 | 0.30239 | 3.4503 | 0
| 25.441 | 1.27 | 14.4908 | 0
| 18.4356 | 0.9569 | 10.9182 | 0
| 9.8612 | 0.58851 | 6.7149 | 0
| 6.4338 | 0.37119 | 4.2353 | 0
| 4.5346 | 0.22541 | 2.5719 | 0
| 4.251 | 0.31371 | 3.5795 | 0
| 0 | 0.0017889 | 0.020412 | 0
| 4.4699 | 0.22312 | 2.5458 | 0
| 31.9505 | 1.5954 | 18.2036 | 0
| 12.7484 | 0.66144 | 7.547 | 0
| 11.3387 | 0.67132 | 7.6597 | 0
| 3.1338 | 0.29235 | 3.3357 | 0
| 5.0384 | 0.34682 | 3.9573 | 0
| 5.403 | 0.28827 | 3.2892 | 0
| 4.7418 | 0.22925 | 2.6158 | 0
| 2.8069 | 0.14042 | 1.6022 | 0
| 5.8734 | 0.25615 | 2.9227 | 0
| 1.7275 | 0.091064 | 1.039 | 0
| 4.4406 | 0.17273 | 1.9709 | 0
| 2.51 | 0.1318 | 1.5039 | 0
| 0 | 0.14848 | 1.6942 | 0
| 2.745 | 0.28471 | 3.2485 | 0
| 10.4869 | 0.48021 | 5.4792 | 0
| 4.0824 | 0.20735 | 2.3659 | 0
| 18.9503 | 0.8818 | 10.0614 | 0
| 17.9681 | 0.92904 | 10.6004 | 0
| 4.903 | 0.2275 | 2.5958 | 0
| 2.4874 | 0.12344 | 1.4084 | 0
| 4.3204 | 0.28292 | 3.2281 | 0
| 3.3198 | 0.25386 | 2.8966 | 0
| 14.4877 | 0.73388 | 8.3735 | 0
| 0.58546 | 0.072012 | 0.82166 | 0
| 43.8356 | 2.0679 | 23.5949 | 0
| 0.61974 | 0.028355 | 0.32353 | 0
| 7.7092 | 0.31229 | 3.5632 | 0
| 24.2953 | 1.398 | 15.9514 | 0
| 15.5274 | 0.71597 | 8.1692 | 0
| 21.6866 | 1.0186 | 11.6228 | 0
| 1.8845 | 0.077634 | 0.8858 | 0
| 8.6216 | 0.47508 | 5.4206 | 0
| 2.3414 | 0.25061 | 2.8595 | 0
| 16.6921 | 0.7152 | 8.1604 | 0
| 0.64087 | 0.040601 | 0.46326 | 0
| 3.0401 | 0.14572 | 1.6626 | 0
| 2.559 | 0.13392 | 1.528 | 0
| 3.0742 | 0.28044 | 3.1999 | 0
| 1.5243 | 0.063101 | 0.71998 | 0
| 0.14877 | 0.015985 | 0.18239 | 0
| 18.654 | 0.87258 | 9.9561 | 0
| 29.587 | 1.6548 | 18.8812 | 0
| 16.2341 | 0.80562 | 9.1921 | 0
| 8.3427 | 0.36585 | 4.1743 | 0
| 3.4101 | 0.086813 | 0.99054 | 0
| 3.7509 | 0.19123 | 2.1819 | 0
| 1.5704 | 0.43548 | 4.9688 | 0
| 0.64585 | 0.030796 | 0.35138 | 0
| 3.9186 | 0.18015 | 2.0555 | 0
| 32.6023 | 1.5441 | 17.6179 | 0
| 18.5817 | 0.9283 | 10.5919 | 0
| 21.2106 | 0.99973 | 11.4069 | 0
| 7.9737 | 0.50068 | 5.7128 | 0
| 10.8299 | 0.52428 | 5.982 | 0
| 0.12481 | 0.0036984 | 0.042199 | 0
| 4.6599 | 0.33278 | 3.797 | 0
| 0 | 1.7366 | 19.8147 | 0
| 8.8877 | 0.48677 | 5.554 | 0
| 8.2393 | 0.38881 | 4.4363 | 0
| 0.52464 | 0.018443 | 0.21043 | 0
| 26.189 | 1.1693 | 13.3417 | 0
| 5.5274 | 0.25489 | 2.9083 | 0
| 4.6157 | 0.33638 | 3.8381 | 0
| 2.7521 | 0.26244 | 2.9944 | 0
| 6.1773 | 0.30456 | 3.475 | 0
| 35.2696 | 1.5712 | 17.9275 | 0
| 0.4654 | 0.021512 | 0.24545 | 0
| 6.3346 | 0.73977 | 8.4407 | 0
| 25.9269 | 1.1326 | 12.9231 | 0
| 9.669 | 0.394 | 4.4955 | 0
| 3.9875 | 0.3616 | 4.1259 | 0
| 14.0764 | 0.59859 | 6.8299 | 0
| 0.13735 | 0.0024071 | 0.027465 | 0
| 31.6476 | 2.3561 | 26.8832 | 0
| 19.8392 | 0.86354 | 9.8529 | 0
| 9.7198 | 0.4268 | 4.8698 | 0
| 1.6882 | 0.069899 | 0.79755 | 0
| 5.9262 | 0.22667 | 2.5863 | 0
| 1.7722 | 0.065796 | 0.75073 | 0
| 0.031136 | 0.0035799 | 0.040846 | 0
| 8.6382 | 0.41245 | 4.7061 | 0
| 1.3302 | 0.13833 | 1.5784 | 0
| 0 | 0.0021837 | 0.024916 | 0
| 33.9288 | 1.5398 | 17.5692 | 0
| 0 | 0.14507 | 1.6552 | 0
| 0.88507 | 0.036137 | 0.41232 | 0
| 2.6245 | 0.1025 | 1.1696 | 0
| 12.4742 | 0.51822 | 5.9128 | 0
| 6.9611 | 0.29667 | 3.385 | 0
| 1.0346 | 0.040933 | 0.46705 | 0
| 23.1079 | 0.96095 | 10.9644 | 0
| 15.4829 | 0.71907 | 8.2046 | 0
| 0.45068 | 0.022047 | 0.25156 | 0
| 8.5263 | 0.33374 | 3.8079 | 0
| 1.1708 | 0.060184 | 0.6867 | 0
| 7.2001 | 0.24814 | 2.8312 | 0
| 5.9329 | 0.27176 | 3.1008 | 0
| 6.8662 | 0.29823 | 3.4028 | 0
| 0.040017 | 0.044834 | 0.51156 | 0
| 8.1294 | 0.31606 | 3.6062 | 0
| 9.3192 | 0.45831 | 5.2293 | 0
| 11.5446 | 0.39268 | 4.4805 | 0
| 10.7588 | 0.48669 | 5.5532 | 0
| 22.8849 | 1.0454 | 11.9284 | 0
| 6.7297 | 0.28875 | 3.2946 | 0
| 1.7982 | 0.065019 | 0.74187 | 0
| 3.7686 | 0.22237 | 2.5372 | 0
| 4.865 | 0.19301 | 2.2023 | 0
| 3.7366 | 0.16279 | 1.8574 | 0
| 17.1146 | 0.70012 | 7.9884 | 0
| 1.666 | 0.060874 | 0.69458 | 0
| 7.505 | 0.50347 | 5.7446 | 0
| 10.8191 | 0.42991 | 4.9052 | 0
| 8.188 | 0.35845 | 4.09 | 0
| 14.5035 | 0.60226 | 6.8718 | 0
| 0 | 0.057584 | 0.65703 | 0
| 0.19667 | 0.010158 | 0.1159 | 0
| 6.1226 | 0.36468 | 4.161 | 0
| 10.3294 | 0.45826 | 5.2288 | 0
| 0 | 0.018691 | 0.21326 | 0
| 8.9731 | 0.31406 | 3.5834 | 0
| 21.7084 | 1.0076 | 11.4966 | 0
| 17.9533 | 0.76141 | 8.6877 | 0
| 1.3476 | 0.085121 | 0.97123 | 0
| 3.3899 | 0.13594 | 1.5511 | 0
| 10.3569 | 1.4077 | 16.0615 | 0
| 2.3734 | 0.0824 | 0.94019 | 0
| 17.3849 | 0.75578 | 8.6234 | 0
| 2.7382 | 0.17573 | 2.0051 | 0
| 7.4388 | 0.4746 | 5.4152 | 0
| 16.6898 | 0.67933 | 7.7512 | 0
| 4.0913 | 0.15686 | 1.7898 | 0
| 14.8481 | 0.5967 | 6.8083 | 0
| 42.3316 | 1.7459 | 19.9206 | 0
| 11.076 | 0.6648 | 7.5854 | 0
| 16.6394 | 0.62441 | 7.1245 | 0
| 4.3425 | 0.28978 | 3.3064 | 0
| 13.1151 | 0.53258 | 6.0768 | 0
| 56.8031 | 2.2801 | 26.0156 | 0
| 9.44 | 0.61025 | 6.9629 | 0
| 2.8225 | 0.12006 | 1.3699 | 0
| 15.4984 | 0.62915 | 7.1786 | 0
| 3.3596 | 0.29215 | 3.3334 | 0
| 4.0651 | 0.1467 | 1.6739 | 0
| 8.2589 | 0.69781 | 7.962 | 0
| 4.2384 | 0.1747 | 1.9933 | 0
| 10.48 | 0.43278 | 4.938 | 0
| 10.4054 | 0.39337 | 4.4883 | 0
| 25.706 | 1.034 | 11.7979 | 0
| 0.56568 | 0.022221 | 0.25354 | 0
| 17.9184 | 0.69482 | 7.9279 | 0
| 13.5292 | 0.65442 | 7.4669 | 0
| 7.6073 | 0.32397 | 3.6965 | 0
| 3.6612 | 0.12759 | 1.4558 | 0
| 9.7221 | 0.37287 | 4.2544 | 0
| 15.2206 | 1.2027 | 13.7226 | 0
| 3.4553 | 0.20489 | 2.3378 | 0
| 15.843 | 0.63953 | 7.297 | 0
| 10.2833 | 0.46321 | 5.2852 | 0
| 14.9079 | 0.77662 | 8.8612 | 0
| 3.0388 | 0.20692 | 2.361 | 0
| 43.1394 | 1.5749 | 17.9699 | 0
| 1.7808 | 0.2128 | 2.428 | 0
| 20.9803 | 1.0762 | 12.2793 | 0
| 11.6832 | 0.45421 | 5.1826 | 0
| 9.4318 | 0.51829 | 5.9137 | 0
| 7.3709 | 0.31767 | 3.6246 | 0
| 8.6068 | 0.3617 | 4.127 | 0
| 18.356 | 0.81054 | 9.2483 | 0
| 6.6742 | 0.24545 | 2.8006 | 0
| 2.0079 | 0.075258 | 0.85869 | 0
| 2.2014 | 0.08932 | 1.0191 | 0
| 26.5575 | 1.0312 | 11.766 | 0
| 6.957 | 0.2523 | 2.8787 | 0
| 3.089 | 0.12417 | 1.4168 | 0
| 6.5341 | 0.23879 | 2.7246 | 0
| 3.0762 | 0.20291 | 2.3152 | 0
| 0.052525 | 0.0030678 | 0.035003 | 0
| 3.5251 | 0.11733 | 1.3387 | 0
| 12.0078 | 0.50772 | 5.793 | 0
| 0.43206 | 0.10682 | 1.2188 | 0
| 10.4277 | 0.64305 | 7.3372 | 0
| 1.2682 | 0.046037 | 0.52528 | 0
| 1.8265 | 0.056836 | 0.6485 | 0
| 0 | 0.14715 | 1.679 | 0
| 2.6932 | 0.093269 | 1.0642 | 0
| 2.4863 | 0.097265 | 1.1098 | 0
| 24.0015 | 0.91584 | 10.4498 | 0
| 3.57 | 0.16364 | 1.8671 | 0
| 0.57048 | 0.032321 | 0.36878 | 0
| 6.4576 | 0.24187 | 2.7598 | 0
| 10.7329 | 0.56381 | 6.4331 | 0
| 4.5589 | 0.27685 | 3.1588 | 0
| 10.4571 | 0.46106 | 5.2607 | 0
| 11.6396 | 0.40371 | 4.6063 | 0
| 0.13851 | 0.014002 | 0.15977 | 0
| 9.246 | 0.32137 | 3.6669 | 0
| 12.539 | 0.61164 | 6.9788 | 0
| 18.7139 | 0.77757 | 8.8721 | 0
| 2.0384 | 0.16964 | 1.9356 | 0
| 0.75417 | 0.026557 | 0.30301 | 0
| 1.3127 | 0.35751 | 4.0791 | 0
| 7.0035 | 0.46694 | 5.3278 | 0
| 2.6327 | 0.14343 | 1.6365 | 0
| 8.7115 | 0.31203 | 3.5603 | 0
| 9.5798 | 0.348 | 3.9706 | 0
| 0.43286 | 0.016635 | 0.18981 | 0
| 3.1626 | 0.1037 | 1.1832 | 0
| 17.9634 | 0.66761 | 7.6175 | 0
| 26.149 | 1.4425 | 16.4584 | 0
| 5.7823 | 0.26528 | 3.0269 | 0
| 6.3704 | 0.25325 | 2.8895 | 0
| 9.2175 | 0.34959 | 3.9888 | 0
| 5.5999 | 0.17586 | 2.0066 | 0
| 4.8702 | 0.18103 | 2.0656 | 0
| 13.485 | 0.48706 | 5.5574 | 0
| 4.5212 | 0.15711 | 1.7926 | 0
| 0.053047 | 0.0074157 | 0.084614 | 0
| 1.452 | 0.052154 | 0.59508 | 0
| 0.2536 | 0.076147 | 0.86884 | 0
| 20.6426 | 0.94673 | 10.8022 | 0
| 7.0662 | 0.26458 | 3.0188 | 0
| 9.7027 | 0.30149 | 3.44 | 0
| 14.9919 | 0.48982 | 5.5889 | 0
| 14.4156 | 0.46401 | 5.2944 | 0
| 7.2872 | 0.36192 | 4.1295 | 0
| 18.0342 | 0.65205 | 7.4399 | 0
| 4.2767 | 0.16396 | 1.8708 | 0
| 3.7096 | 0.12448 | 1.4203 | 0
| 0.054151 | 0.0018886 | 0.021549 | 0
| 1.1106 | 0.075478 | 0.8612 | 0
| 1.6885 | 0.053421 | 0.60953 | 0
| 4.1633 | 0.15642 | 1.7847 | 0
| 4.4638 | 0.14303 | 1.632 | 0
| 2.6056 | 0.12323 | 1.406 | 0
| 2.712 | 0.083582 | 0.95367 | 0
| 18.7155 | 0.747 | 8.5233 | 0
| 2.0452 | 0.058928 | 0.67236 | 0
| 0.32078 | 0.0081042 | 0.092468 | 0
| 0.86011 | 0.028013 | 0.31963 | 0
| 26.1012 | 1.1634 | 13.2742 | 0
| 21.9765 | 0.69729 | 7.9561 | 0
| 6.1602 | 0.24336 | 2.7767 | 0
| 5.532 | 0.18813 | 2.1466 | 0
| 23.9382 | 0.83609 | 9.5398 | 0
| 22.2352 | 0.76788 | 8.7616 | 0
| 1.6049 | 0.059392 | 0.67767 | 0
| 6.6769 | 0.23825 | 2.7185 | 0
| 4.9411 | 0.2595 | 2.9609 | 0
| 0.25501 | 0.0041669 | 0.047544 | 0
| 8.4304 | 0.2933 | 3.3465 | 0
| 3.8589 | 0.14179 | 1.6179 | 0
| 0.93104 | 0.036648 | 0.41815 | 0
| 1.1972 | 0.030129 | 0.34378 | 0
| 22.5348 | 0.74746 | 8.5285 | 0
| 4.4671 | 0.13815 | 1.5763 | 0
| 3.8103 | 0.13054 | 1.4895 | 0
| 6.0217 | 0.21988 | 2.5088 | 0
| 10.2577 | 0.59244 | 6.7597 | 0
| 6.836 | 0.23391 | 2.6689 | 0
| 3.2413 | 0.090193 | 1.0291 | 0
| 2.0764 | 0.074575 | 0.8509 | 0
| 1.5379 | 0.042229 | 0.48183 | 0
| 27.7186 | 1.1386 | 12.9915 | 0
| 2.0549 | 0.070888 | 0.80883 | 0
| 0.25389 | 0.24227 | 2.7643 | 0
| 0.6874 | 0.082959 | 0.94656 | 0
| 14.4015 | 0.69371 | 7.9152 | 0
| 3.2642 | 0.43648 | 4.9803 | 0
| 3.9148 | 0.12331 | 1.4069 | 0
| 2.3945 | 0.072202 | 0.82383 | 0
| 6.4597 | 0.2342 | 2.6722 | 0
| 5.1848 | 0.14646 | 1.6711 | 0
| 0 | 0.0026495 | 0.030231 | 0
| 16.697 | 0.72319 | 8.2516 | 0
| 11.4001 | 0.3744 | 4.2719 | 0
| 0.93369 | 0.18235 | 2.0806 | 0
| 1.2404 | 0.040311 | 0.45995 | 0
| 2.1247 | 0.075141 | 0.85736 | 0
| 19.3919 | 0.60202 | 6.8691 | 0
| 38.2589 | 1.2404 | 14.1529 | 0
| 4.8112 | 0.15687 | 1.7899 | 0
| 6.5367 | 0.23532 | 2.685 | 0
| 0.015504 | 0.00085672 | 0.0097752 | 0
| 10.671 | 0.35959 | 4.103 | 0
| 7.5199 | 0.24571 | 2.8036 | 0
| 20.0272 | 0.57628 | 6.5753 | 0
| 0.33211 | 0.009966 | 0.11371 | 0
| 0.21009 | 0.004835 | 0.055168 | 0
| 1.5741 | 0.092027 | 1.05 | 0
| 0.56062 | 0.017893 | 0.20416 | 0
| 15.5316 | 0.94965 | 10.8355 | 0
| 2.3735 | 0.10158 | 1.1591 | 0
| 12.1671 | 0.39026 | 4.4528 | 0
| 23.0747 | 0.7015 | 8.0041 | 0
| 44.4338 | 1.3497 | 15.3998 | 0
| 7.9643 | 0.26745 | 3.0516 | 0
| 2.3068 | 0.080046 | 0.91333 | 0
| 3.8639 | 0.11419 | 1.3029 | 0
| 10.5408 | 0.3444 | 3.9296 | 0
| 12.1743 | 0.38767 | 4.4233 | 0
| 0.054774 | 0.0016581 | 0.018919 | 0
| 0.28791 | 0.0055262 | 0.063054 | 0
| 7.8016 | 0.38958 | 4.4451 | 0
| 8.3225 | 0.27985 | 3.1931 | 0
| 6.7064 | 0.20034 | 2.2859 | 0
| 14.985 | 0.49409 | 5.6376 | 0
| 2.2624 | 0.078315 | 0.89358 | 0
| 7.0754 | 0.20834 | 2.3772 | 0
| 27.2025 | 0.80114 | 9.141 | 0
| 0 | 0.34908 | 3.983 | 0
| 10.8315 | 0.31888 | 3.6384 | 0
| 31.0207 | 0.96294 | 10.9872 | 0
| 8.0946 | 0.68326 | 7.7959 | 0
| 4.4625 | 0.15099 | 1.7228 | 0
| 38.0599 | 1.1397 | 13.0037 | 0
| 2.1668 | 0.11329 | 1.2926 | 0
| 0 | 0.0997 | 1.1376 | 0
| 24.9707 | 0.56993 | 6.5029 | 0
| 0.10163 | 0.031406 | 0.35835 | 0
| 0.68708 | 0.069904 | 0.7976 | 0
| 5.8684 | 0.34178 | 3.8997 | 0
| 31.5917 | 0.96464 | 11.0065 | 0
| 6.6523 | 0.21512 | 2.4545 | 0
| 0.80279 | 0.088713 | 1.0122 | 0
| 1.5205 | 0.047644 | 0.54361 | 0
| 7.9531 | 0.22812 | 2.6028 | 0
| 5.056 | 0.15153 | 1.7289 | 0
| 2.3603 | 0.055754 | 0.63615 | 0
| 9.4937 | 0.28356 | 3.2354 | 0
| 9.3395 | 0.25322 | 2.8892 | 0
| 5.7251 | 0.1789 | 2.0413 | 0
| 5.6369 | 0.15973 | 1.8226 | 0
| 4.9961 | 0.12182 | 1.3899 | 0
| 34.2023 | 0.98338 | 11.2203 | 0
| 2.2003 | 0.058458 | 0.667 | 0
| 21.1858 | 0.60787 | 6.9358 | 0
| 23.9732 | 0.73399 | 8.3748 | 0
| 0.77844 | 0.022287 | 0.2543 | 0
| 9.1591 | 0.28161 | 3.2132 | 0
| 37.3917 | 1.9964 | 22.7787 | 0
| 7.1548 | 0.24357 | 2.7791 | 0
| 36.9234 | 1.1597 | 13.2319 | 0
| 0.19181 | 0.10086 | 1.1508 | 0
| 3.8509 | 0.12408 | 1.4158 | 0
| 6.0719 | 0.18014 | 2.0554 | 0
| 0.74058 | 0.1299 | 1.4822 | 0
| 8.2284 | 0.50596 | 5.773 | 0
| 4.4695 | 0.12513 | 1.4278 | 0
| 7.4647 | 0.18743 | 2.1385 | 0
| 3.4084 | 0.085353 | 0.97388 | 0
| 8.5294 | 0.63626 | 7.2598 | 0
| 0.39063 | 0.0050128 | 0.057196 | 0
| 1.4941 | 0.086782 | 0.99018 | 0
| 2.3174 | 0.061063 | 0.69673 | 0
| 2.4171 | 0.072381 | 0.82587 | 0
| 1.2874 | 0.054448 | 0.62125 | 0
| 1.4188 | 0.058902 | 0.67207 | 0
| 6.3593 | 0.1853 | 2.1142 | 0
| 19.4027 | 0.54574 | 6.2269 | 0
| 15.9098 | 0.45972 | 5.2454 | 0
| 1.8328 | 0.11723 | 1.3376 | 0
| 3.2391 | 0.089228 | 1.0181 | 0
| 15.6191 | 0.41306 | 4.713 | 0
| 1.0084 | 0.072778 | 0.83039 | 0
| 0.24923 | 0.074895 | 0.85455 | 0
| 43.9951 | 1.1764 | 13.4232 | 0
| 5.8544 | 0.18907 | 2.1573 | 0
| 16.7391 | 0.43325 | 4.9433 | 0
| 2.73 | 0.075856 | 0.86551 | 0
| 0.70417 | 0.027466 | 0.31339 | 0
| 4.7474 | 0.13194 | 1.5054 | 0
| 0.17644 | 0.022572 | 0.25754 | 0
| 2.0229 | 0.055217 | 0.63003 | 0
| 1.0081 | 0.40575 | 4.6296 | 0
| 0.23322 | 0.0026419 | 0.030144 | 0
| 1.8185 | 0.040749 | 0.46494 | 0
| 37.5223 | 1.0103 | 11.5271 | 0
| 5.3935 | 0.15046 | 1.7168 | 0
| 17.5746 | 0.49996 | 5.7046 | 0
| 13.9574 | 0.39182 | 4.4707 | 0
| 0.48408 | 0.064098 | 0.73136 | 0
| 0.16658 | 0.0040059 | 0.045708 | 0
| 85.0016 | 2.2539 | 25.7171 | 0
| 1.7679 | 0.031466 | 0.35903 | 0
| 10.289 | 0.27598 | 3.1489 | 0
| 0.098254 | 0.0028088 | 0.032049 | 0
| 0.0028409 | 0.00070203 | 0.0080102 | 0
| 9.293 | 0.23522 | 2.6839 | 0
| 8.6811 | 0.23582 | 2.6907 | 0
| 10.7387 | 0.30347 | 3.4626 | 0
| 14.8827 | 0.43839 | 5.0021 | 0
| 31.0216 | 0.79175 | 9.0339 | 0
| 2.0442 | 0.15906 | 1.8149 | 0
| 0.013798 | 0.00045871 | 0.0052339 | 0
| 0.002841 | 0.00045859 | 0.0052325 | 0
| 16.1706 | 0.44108 | 5.0327 | 0
| 58.135 | 1.5392 | 17.5624 | 0
| 11.2959 | 0.47543 | 5.4246 | 0
| 0.44609 | 0.038669 | 0.44122 | 0
| 35.6862 | 1.1644 | 13.2854 | 0
| 4.4862 | 0.0954 | 1.0885 | 0
| 4.5687 | 0.10433 | 1.1904 | 0
| 2.1493 | 0.91764 | 10.4702 | 0
| 0.46241 | 0.046951 | 0.53571 | 0
| 0.098744 | 0.019535 | 0.2229 | 0
| 0.52118 | 0.011428 | 0.1304 | 0
| 9.3826 | 0.2284 | 2.606 | 0
| 0.015137 | 0.00066866 | 0.0076294 | 0
| 7.0571 | 0.34462 | 3.9321 | 0
| 18.938 | 0.50954 | 5.8138 | 0
| 2.3183 | 0.06869 | 0.78375 | 0
| 4.1448 | 0.098581 | 1.1248 | 0
| 0 | 1.1766 | 13.4246 | 0
| 26.2216 | 0.62543 | 7.1361 | 0
| 7.9562 | 0.1858 | 2.12 | 0
| 0.098836 | 0.01253 | 0.14297 | 0
| 2.7379 | 0.062587 | 0.71412 | 0
| 7.3937 | 0.1867 | 2.1302 | 0
| 23.0424 | 0.58171 | 6.6373 | 0
| 27.8483 | 0.60674 | 6.9229 | 0
| 13.7426 | 0.35409 | 4.0402 | 0
| 21.6475 | 1.3477 | 15.377 | 0
| 4.4405 | 0.29014 | 3.3105 | 0
| 0.73188 | 0.078895 | 0.90019 | 0
| 9.5221 | 0.23797 | 2.7153 | 0
| 4.8099 | 0.11482 | 1.3101 | 0
| 5.3544 | 0.13001 | 1.4834 | 0
| 1.3292 | 0.074923 | 0.85488 | 0
| 0.1767 | 0.006512 | 0.074302 | 0
| 16.0708 | 0.39034 | 4.4538 | 0
| 0.057962 | 0.0010803 | 0.012326 | 0
| 20.4521 | 0.6258 | 7.1404 | 0
| 8.5701 | 0.18944 | 2.1615 | 0
| 0 | 0.32829 | 3.7458 | 0
| 8.5834 | 0.21708 | 2.4769 | 0
| 26.1897 | 0.77669 | 8.8621 | 0
| 0.88681 | 0.017174 | 0.19595 | 0
| 2.9395 | 0.057003 | 0.6504 | 0
| 0.60802 | 0.075643 | 0.86309 | 0
| 8.1237 | 0.19275 | 2.1993 | 0
| 1.4427 | 0.041156 | 0.46959 | 0
| 16.2339 | 0.41944 | 4.7858 | 0
| 5.9505 | 0.13848 | 1.58 | 0
| 14.7536 | 0.37933 | 4.3281 | 0
| 8.898 | 0.2046 | 2.3345 | 0
| 0.6359 | 0.013227 | 0.15092 | 0
| 8.123 | 0.48037 | 5.481 | 0
| 0.0028409 | 0.0048241 | 0.055043 | 0
| 8.5069 | 0.20608 | 2.3514 | 0
| 13.1801 | 0.30265 | 3.4532 | 0
| 9.7718 | 0.21447 | 2.4471 | 0
| 0.0076054 | 0.0012526 | 0.014292 | 0
| 7.1266 | 0.17654 | 2.0143 | 0
| 7.4004 | 0.26352 | 3.0068 | 0
| 5.8135 | 0.17119 | 1.9532 | 0
| 0.81175 | 0.020407 | 0.23284 | 0
| 0.74449 | 0.021759 | 0.24827 | 0
| 1.413 | 0.096483 | 1.1009 | 0
| 1.9635 | 0.042829 | 0.48867 | 0
| 0.75442 | 0.029173 | 0.33286 | 0
| 1.9565 | 0.044666 | 0.50964 | 0
| 6.215 | 0.1475 | 1.683 | 0
| 0.26301 | 0.075568 | 0.86224 | 0
| 9.1136 | 0.19998 | 2.2817 | 0
| 1.3866 | 0.029053 | 0.3315 | 0
| 0.23321 | 0.0092652 | 0.10572 | 0
| 3.5628 | 0.08695 | 0.9921 | 0
| 15.325 | 0.34363 | 3.9208 | 0
| 4.3275 | 0.091757 | 1.0469 | 0
| 0.18282 | 0.018462 | 0.21065 | 0
| 8.7047 | 0.28241 | 3.2223 | 0
| 5.4334 | 0.11892 | 1.3569 | 0
| 29.359 | 0.69377 | 7.9159 | 0
| 7.4483 | 0.23586 | 2.6911 | 0
| 0.050742 | 0.0036543 | 0.041696 | 0
| 22.5955 | 0.49508 | 5.6488 | 0
| 0.058358 | 0.00091144 | 0.0104 | 0
| 0.018482 | 0.0088715 | 0.10122 | 0
| 2.8385 | 0.058051 | 0.66236 | 0
| 14.8079 | 0.33829 | 3.8599 | 0
| 0.27972 | 0.0066305 | 0.075653 | 0
| 5.6124 | 0.13957 | 1.5925 | 0
| 0 | 0.33355 | 3.8058 | 0
| 0 | 0.0053597 | 0.061154 | 0
| 3.6396 | 0.10457 | 1.1931 | 0
| 0.20457 | 0.083748 | 0.95556 | 0
| 9.617 | 0.2106 | 2.4029 | 0
| 5.799 | 0.11606 | 1.3242 | 0
| 8.7586 | 0.19347 | 2.2075 | 0
| 8.7308 | 0.32666 | 3.7271 | 0
| 10.7055 | 0.27031 | 3.0842 | 0
| 4.4519 | 0.10448 | 1.1921 | 0
| 7.9913 | 0.21686 | 2.4743 | 0
| 1.5908 | 0.035726 | 0.40764 | 0
| 4.685 | 0.10948 | 1.2492 | 0
| 7.181 | 0.24682 | 2.8162 | 0
| 4.6845 | 0.10164 | 1.1597 | 0
| 2.1375 | 0.047485 | 0.54181 | 0
| 4.6629 | 0.11574 | 1.3206 | 0
| 2.5117 | 0.055796 | 0.63663 | 0
| 4.9565 | 0.10746 | 1.2261 | 0
| 6.6246 | 0.13194 | 1.5054 | 0
| 25.3216 | 0.56154 | 6.4072 | 0
| 5.0711 | 0.11333 | 1.2931 | 0
| 1.6213 | 0.079214 | 0.90383 | 0
| 4.008 | 0.070096 | 0.79979 | 0
| 0.2787 | 0.01855 | 0.21165 | 0
| 2.8628 | 0.23085 | 2.634 | 0
| 1.5159 | 0.08054 | 0.91896 | 0
| 3.8237 | 0.092528 | 1.0557 | 0
| 14.6669 | 0.36136 | 4.1231 | 0
| 3.1084 | 0.076539 | 0.87331 | 0
| 1.9901 | 0.26615 | 3.0368 | 0
| 1.1151 | 0.023491 | 0.26804 | 0
| 3.829 | 0.086509 | 0.98706 | 0
| 0.45596 | 0.01029 | 0.11741 | 0
| 5.2699 | 0.11425 | 1.3036 | 0
| 0 | 0.014281 | 0.16294 | 0
| 6.0782 | 0.17169 | 1.959 | 0
| 22.7596 | 0.48287 | 5.5096 | 0
| 11.3351 | 0.26811 | 3.0591 | 0
| 16.2031 | 0.37871 | 4.3211 | 0
| 7.2549 | 0.16676 | 1.9027 | 0
| 4.9192 | 0.10153 | 1.1584 | 0
| 2.1015 | 0.044523 | 0.50801 | 0
| 23.5828 | 0.5441 | 6.2082 | 0
| 27.8333 | 0.57371 | 6.5461 | 0
| 16.2632 | 0.40124 | 4.5781 | 0
| 4.8555 | 0.082907 | 0.94596 | 0
| 20.4229 | 0.44182 | 5.0411 | 0
| 0 | 0.020708 | 0.23627 | 0
| 4.6373 | 0.12867 | 1.4682 | 0
| 0.80266 | 0.045117 | 0.51479 | 0
| 8.3247 | 0.15466 | 1.7646 | 0
| 7.8669 | 0.15774 | 1.7999 | 0
| 2.235 | 0.077667 | 0.88619 | 0
| 3.7451 | 0.076303 | 0.87062 | 0
| 1.0675 | 0.024941 | 0.28458 | 0
| 3.8235 | 0.083689 | 0.95489 | 0
| 1.7381 | 0.032142 | 0.36675 | 0
| 11.3636 | 0.23203 | 2.6474 | 0
| 13.0058 | 0.36696 | 4.187 | 0
| 13.3363 | 0.25471 | 2.9062 | 0
| 9.4329 | 0.32601 | 3.7198 | 0
| 4.4582 | 0.1011 | 1.1536 | 0
| 3.3832 | 0.16089 | 1.8358 | 0
| 16.8331 | 0.40577 | 4.6298 | 0
| 0.19745 | 0.019179 | 0.21883 | 0
| 29.297 | 0.56003 | 6.3899 | 0
| 6.3452 | 0.1143 | 1.3041 | 0
| 0 | 0.06717 | 0.76641 | 0
| 1.2405 | 0.028331 | 0.32326 | 0
| 1.2193 | 0.027723 | 0.31632 | 0
| 0 | 0.061135 | 0.69755 | 0
| 1.5408 | 0.034053 | 0.38854 | 0
| 3.9601 | 0.070229 | 0.80132 | 0
| 14.6138 | 0.25644 | 2.926 | 0
| 1.2563 | 0.023539 | 0.26858 | 0
| 5.2758 | 0.11732 | 1.3386 | 0
| 3.0319 | 0.053124 | 0.60615 | 0
| 9.6079 | 0.17525 | 1.9997 | 0
| 4.9804 | 0.2004 | 2.2865 | 0
| 20.1881 | 0.39318 | 4.4862 | 0
| 5.3687 | 0.13209 | 1.5071 | 0
| 2.3352 | 0.048175 | 0.54968 | 0
| 12.5223 | 0.24576 | 2.8041 | 0
| 3.9479 | 0.079707 | 0.90946 | 0
| 0.94898 | 0.017414 | 0.1987 | 0
| 18.5568 | 0.35668 | 4.0697 | 0
| 45.4733 | 1.0006 | 11.4166 | 0
| 6.536 | 0.13448 | 1.5344 | 0
| 8.582 | 0.17965 | 2.0498 | 0
| 27.9454 | 0.5404 | 6.1659 | 0
| 16.4021 | 0.49306 | 5.6259 | 0
| 10.7044 | 0.25817 | 2.9457 | 0
| 0.18121 | 0.0052348 | 0.059729 | 0
| 3.1261 | 0.11926 | 1.3607 | 0
| 5.4376 | 0.16885 | 1.9266 | 0
| 1.8696 | 0.039508 | 0.45078 | 0
| 1.4823 | 0.018102 | 0.20655 | 0
| 6.25 | 0.11005 | 1.2557 | 0
| 1.8749 | 0.028007 | 0.31956 | 0
| 0.084825 | 0.062027 | 0.70773 | 0
| 0.014229 | 0.00051738 | 0.0059033 | 0
| 10.0728 | 0.31651 | 3.6114 | 0
| 0.017428 | 0.0046406 | 0.052949 | 0
| 2.1051 | 0.055102 | 0.62872 | 0
| 4.5056 | 0.089064 | 1.0162 | 0
| 7.2893 | 0.13498 | 1.5402 | 0
| 1.8143 | 0.033859 | 0.38633 | 0
| 0.11526 | 0.0046047 | 0.05254 | 0
| 0.047363 | 0.00025566 | 0.0029171 | 0
| 9.8902 | 0.1885 | 2.1508 | 0
| 0 | 0.044927 | 0.51262 | 0
| 28.6595 | 0.55886 | 6.3766 | 0
| 1.0817 | 0.033144 | 0.37817 | 0
| 0.45329 | 0.009007 | 0.10277 | 0
| 8.2897 | 0.33562 | 3.8295 | 0
| 3.136 | 0.12777 | 1.4578 | 0
| 14.8587 | 0.30081 | 3.4323 | 0
| 1.0582 | 0.023806 | 0.27162 | 0
| 19.9735 | 0.36331 | 4.1453 | 0
| 30.9607 | 0.58071 | 6.6259 | 0
| 5.9254 | 0.16988 | 1.9384 | 0
| 4.2372 | 0.076222 | 0.86969 | 0
| 14.7318 | 0.27229 | 3.1068 | 0
| 0.11575 | 0.0013316 | 0.015194 | 0
| 4.6501 | 0.082557 | 0.94198 | 0
| 2.3529 | 0.075266 | 0.85879 | 0
| 0.66159 | 0.013874 | 0.1583 | 0
| 1.3488 | 0.028737 | 0.32789 | 0
| 15.3763 | 0.41255 | 4.7072 | 0
| 18.0538 | 0.3153 | 3.5975 | 0
| 4.8638 | 0.096223 | 1.0979 | 0
| 10.3912 | 0.18501 | 2.111 | 0
| 9.0609 | 0.18086 | 2.0637 | 0
| 4.8787 | 0.086748 | 0.98979 | 0
| 5.5082 | 0.15182 | 1.7322 | 0
| 4.5743 | 0.15374 | 1.7542 | 0
| 3.0156 | 0.08956 | 1.0219 | 0
| 0.35707 | 0.0083179 | 0.094907 | 0
| 19.9304 | 0.34292 | 3.9127 | 0
| 3.2266 | 0.21852 | 2.4934 | 0
| 2.1436 | 0.037381 | 0.42651 | 0
| 12.9461 | 0.24137 | 2.754 | 0
| 4.4094 | 0.10899 | 1.2435 | 0
| 6.4026 | 0.11643 | 1.3284 | 0
| 2.0597 | 0.060664 | 0.69218 | 0
| 1.701 | 0.027813 | 0.31735 | 0
| 8.0127 | 0.18233 | 2.0804 | 0
| 0.01528 | 0.0003191 | 0.0036409 | 0
| 0.027848 | 0.0038277 | 0.043674 | 0
| 9.029 | 0.23412 | 2.6713 | 0
| 2.4125 | 0.07607 | 0.86796 | 0
| 5.9389 | 0.14594 | 1.6651 | 0
| 0.50915 | 0.0094999 | 0.10839 | 0
| 4.9323 | 0.095466 | 1.0893 | 0
| 0.01936 | 0.0014242 | 0.01625 | 0
| 2.8586 | 0.045798 | 0.52256 | 0
| 7.8013 | 0.13584 | 1.5499 | 0
| 0.40227 | 0.0089566 | 0.10219 | 0
| 8.6084 | 0.13657 | 1.5583 | 0
| 0.51138 | 0.016412 | 0.18726 | 0
| 7.9582 | 0.15782 | 1.8008 | 0
| 0.86986 | 0.015467 | 0.17648 | 0
| 3.943 | 0.056237 | 0.64166 | 0
| 33.021 | 0.58105 | 6.6298 | 0
| 0.029025 | 0.00046744 | 0.0053335 | 0
| 0.027927 | 0.0014012 | 0.015988 | 0
| 6.8314 | 0.13277 | 1.5149 | 0
| 0.15554 | 0.03362 | 0.38361 | 0
| 3.7144 | 0.074648 | 0.85174 | 0
| 0.52045 | 0.045658 | 0.52096 | 0
| 7.7735 | 0.14173 | 1.6172 | 0
| 10.9396 | 0.20842 | 2.3781 | 0
| 0.022194 | 0.00046302 | 0.0052831 | 0
| 4.6297 | 0.066221 | 0.75558 | 0
| 0.15648 | 0.017055 | 0.19459 | 0
| 1.1873 | 0.06772 | 0.77269 | 0
| 0.81239 | 0.01746 | 0.19921 | 0
| 1.4241 | 0.057845 | 0.66001 | 0
| 0.39747 | 0.0038209 | 0.043596 | 0
| 3.7307 | 0.066916 | 0.76351 | 0
| 1.245 | 0.015728 | 0.17946 | 0
| 22.532 | 0.6814 | 7.7747 | 0
| 7.5157 | 0.14251 | 1.626 | 0
| 0.14307 | 0.0091245 | 0.10411 | 0
| 10.2951 | 0.18501 | 2.111 | 0
| 42.0641 | 0.74174 | 8.4633 | 0
| 14.227 | 0.24168 | 2.7576 | 0
| 10.4386 | 0.15318 | 1.7478 | 0
| 4.6718 | 0.11142 | 1.2713 | 0
| 1.2101 | 0.040443 | 0.46146 | 0
| 0.00042227 | 0.016779 | 0.19145 | 0
| 0.36514 | 0.0075514 | 0.086161 | 0
| 2.7892 | 0.033062 | 0.37724 | 0
| 2.0371 | 0.052685 | 0.60113 | 0
| 2.2276 | 0.18374 | 2.0965 | 0
| 17.2625 | 0.29882 | 3.4095 | 0
| 6.5729 | 0.4314 | 4.9223 | 0
| 11.7467 | 0.52895 | 6.0353 | 0
| 1.7371 | 0.033398 | 0.38107 | 0
| 8.3032 | 0.1442 | 1.6453 | 0
| 18.2796 | 0.3072 | 3.5052 | 0
| 12.3762 | 0.19743 | 2.2527 | 0
| 2.6053 | 0.046828 | 0.53431 | 0
| 1.1066 | 0.060207 | 0.68696 | 0
| 9.5427 | 0.14885 | 1.6984 | 0
| 7.3382 | 0.11924 | 1.3606 | 0
| 5.2061 | 0.15981 | 1.8234 | 0
| 5.2241 | 0.29683 | 3.3868 | 0
| 0.61163 | 0.043062 | 0.49134 | 0
| 5.8232 | 0.099307 | 1.1331 | 0
| 8.3786 | 0.12841 | 1.4651 | 0
| 0.30666 | 0.0094457 | 0.10778 | 0
| 3.7761 | 0.061906 | 0.70635 | 0
| 10.5796 | 0.18571 | 2.1189 | 0
| 0.29648 | 0.0083981 | 0.095822 | 0
| 0 | 0.00044116 | 0.0050337 | 0
| 1.8473 | 0.029082 | 0.33182 | 0
| 3.9324 | 0.062518 | 0.71333 | 0
| 12.4543 | 0.30487 | 3.4786 | 0
| 3.1442 | 0.073779 | 0.84182 | 0
| 4.1605 | 0.066454 | 0.75824 | 0
| 2.4965 | 0.059264 | 0.6762 | 0
| 3.5356 | 0.050784 | 0.57944 | 0
| 12.3716 | 0.20884 | 2.3829 | 0
| 1.2526 | 0.027931 | 0.31869 | 0
| 7.257 | 0.1439 | 1.6419 | 0
| 0.85271 | 0.14619 | 1.668 | 0
| 0.046655 | 0.0047994 | 0.054761 | 0
| 3.5751 | 0.062349 | 0.7114 | 0
| 0.89525 | 0.017126 | 0.19541 | 0
| 14.3045 | 0.23231 | 2.6507 | 0
| 5.5805 | 0.090919 | 1.0374 | 0
| 17.594 | 0.36798 | 4.1987 | 0
| 7.1081 | 0.43584 | 4.973 | 0
| 0.24202 | 0.0051585 | 0.058859 | 0
| 2.1797 | 0.18148 | 2.0707 | 0
| 0.58309 | 0.0103 | 0.11752 | 0
| 14.101 | 0.25606 | 2.9217 | 0
| 5.3151 | 0.11612 | 1.3249 | 0
| 9.6659 | 0.1567 | 1.7879 | 0
| 1.7018 | 0.027683 | 0.31586 | 0
| 1.8807 | 0.028681 | 0.32725 | 0
| 0.30073 | 0.0055611 | 0.063453 | 0
| 14.7535 | 0.22074 | 2.5187 | 0
| 3.4241 | 0.059457 | 0.6784 | 0
| 5.8595 | 0.10309 | 1.1763 | 0
| 1.8209 | 0.034632 | 0.39516 | 0
| 31.3932 | 0.49704 | 5.6712 | 0
| 2.2473 | 0.033755 | 0.38515 | 0
| 1.8028 | 0.069701 | 0.79529 | 0
| 0.3041 | 0.0053333 | 0.060853 | 0
| 0.18597 | 0.011169 | 0.12744 | 0
| 22.113 | 0.37134 | 4.237 | 0
| 2.6457 | 0.035125 | 0.40078 | 0
| 13.7144 | 0.21317 | 2.4323 | 0
| 2.3557 | 0.11421 | 1.3032 | 0
| 14.0855 | 0.20444 | 2.3327 | 0
| 0.6023 | 0.010371 | 0.11833 | 0
| 10.1072 | 0.16245 | 1.8536 | 0
| 9.308 | 0.15505 | 1.7692 | 0
| 23.8662 | 1.0074 | 11.4946 | 0
| 2.4398 | 0.041146 | 0.46948 | 0
| 9.8081 | 0.1624 | 1.853 | 0
| 0.086752 | 0.0093016 | 0.10613 | 0
| 0.72524 | 0.016132 | 0.18406 | 0
| 20.9488 | 0.29099 | 3.3202 | 0
| 5.4039 | 0.10806 | 1.233 | 0
| 24.2069 | 0.36322 | 4.1443 | 0
| 4.8719 | 0.07837 | 0.8942 | 0
| 0.13272 | 0.020019 | 0.22842 | 0
| 5.2327 | 0.20134 | 2.2973 | 0
| 1.6383 | 0.024056 | 0.27448 | 0
| 0.029925 | 0.00040767 | 0.0046515 | 0
| 11.6066 | 0.15724 | 1.7942 | 0
| 4.5877 | 0.070854 | 0.80844 | 0
| 4.3244 | 0.066928 | 0.76365 | 0
| 0.54484 | 0.020728 | 0.23651 | 0
| 2.1905 | 0.05796 | 0.66132 | 0
| 0.098331 | 0.001759 | 0.020071 | 0
| 5.6268 | 0.13308 | 1.5185 | 0
| 12.1413 | 0.19415 | 2.2152 | 0
| 0.30393 | 0.12252 | 1.3979 | 0
| 1.8596 | 0.056062 | 0.63967 | 0
| 3.3466 | 0.036236 | 0.41345 | 0
| 29.1242 | 0.45434 | 5.184 | 0
| 0.54468 | 0.012065 | 0.13766 | 0
| 0.016177 | 0.00046912 | 0.0053526 | 0
| 1.8914 | 0.026743 | 0.30514 | 0
| 2.1012 | 0.034879 | 0.39797 | 0
| 4.9405 | 0.078475 | 0.8954 | 0
| 9.3863 | 0.15076 | 1.7202 | 0
| 0.15233 | 0.0097031 | 0.11071 | 0
| 10.7791 | 0.16222 | 1.8509 | 0
| 1.2606 | 0.01486 | 0.16955 | 0
| 2.8927 | 0.033671 | 0.38418 | 0
| 13.3177 | 0.19959 | 2.2773 | 0
| 2.3791 | 0.026624 | 0.30378 | 0
| 0 | 0.12947 | 1.4772 | 0
| 0.6932 | 0.01151 | 0.13133 | 0
| 19.3984 | 0.36447 | 4.1586 | 0
| 9.9691 | 0.14386 | 1.6415 | 0
| 5.4694 | 0.076797 | 0.87626 | 0
| 16.261 | 0.23353 | 2.6646 | 0
| 0.44078 | 0.0065862 | 0.075149 | 0
| 8.6721 | 0.35267 | 4.0239 | 0
| 5.5761 | 0.16897 | 1.928 | 0
| 10.1999 | 0.14425 | 1.6459 | 0
| 0.61022 | 0.010974 | 0.12522 | 0
| 5.6507 | 0.074838 | 0.8539 | 0
| 1.9205 | 0.045309 | 0.51697 | 0
| 4.3979 | 0.19679 | 2.2454 | 0
| 2.3077 | 0.031791 | 0.36274 | 0
| 5.6018 | 0.096533 | 1.1014 | 0
| 7.3627 | 0.10786 | 1.2307 | 0
| 17.7548 | 0.25999 | 2.9664 | 0
| 0.74266 | 0.012008 | 0.13702 | 0
| 6.1089 | 0.073883 | 0.843 | 0
| 3.4324 | 0.047566 | 0.54273 | 0
| 2.4893 | 0.10161 | 1.1594 | 0
| 3.9292 | 0.053608 | 0.61167 | 0
| 18.7137 | 0.27109 | 3.0932 | 0
| 0.026351 | 0.12298 | 1.4032 | 0
| 1.9908 | 0.02736 | 0.31217 | 0
| 0.81558 | 0.014118 | 0.16108 | 0
| 4.1846 | 0.094235 | 1.0752 | 0
| 3.995 | 0.05568 | 0.63531 | 0
| 19.7166 | 0.28646 | 3.2685 | 0
| 11.1953 | 0.17083 | 1.9492 | 0
| 0.12306 | 0.0019124 | 0.02182 | 0
| 0.37823 | 0.010193 | 0.1163 | 0
| 2.7843 | 0.031338 | 0.35757 | 0
| 1.4912 | 0.021372 | 0.24386 | 0
| 1.2182 | 0.016788 | 0.19155 | 0
| 16.4488 | 0.26026 | 2.9696 | 0
| 25.9295 | 0.36374 | 4.1503 | 0
| 15.6495 | 0.20534 | 2.3429 | 0
| 37.586 | 0.5585 | 6.3724 | 0
| 2.7225 | 0.041166 | 0.4697 | 0
| 0.4469 | 0.018938 | 0.21608 | 0
| 0 | 0.0208 | 0.23733 | 0
| 0.97544 | 0.0166 | 0.1894 | 0
| 0.029406 | 0.00050281 | 0.005737 | 0
| 0.011497 | 0.0028903 | 0.032978 | 0
| 5.9903 | 0.078658 | 0.89749 | 0
| 22.6963 | 0.30297 | 3.4569 | 0
| 1.5057 | 0.024398 | 0.27838 | 0
| 0.38122 | 0.017128 | 0.19543 | 0
| 8.9373 | 0.13232 | 1.5098 | 0
| 12.0573 | 0.18925 | 2.1593 | 0
| 4.2811 | 0.058331 | 0.66556 | 0
| 5.3015 | 0.067441 | 0.7695 | 0
| 18.3065 | 0.41678 | 4.7554 | 0
| 2.1881 | 0.067844 | 0.7741 | 0
| 2.2052 | 0.11704 | 1.3355 | 0
| 4.8759 | 0.063524 | 0.7248 | 0
| 2.1196 | 0.029331 | 0.33467 | 0
| 1.3263 | 0.015832 | 0.18065 | 0
| 15.165 | 0.20835 | 2.3773 | 0
| 8.8102 | 0.13157 | 1.5012 | 0
| 3.0705 | 0.042903 | 0.48953 | 0
| 1.1724 | 0.12127 | 1.3837 | 0
| 58.2265 | 0.86372 | 9.8551 | 0
| 3.4135 | 0.061411 | 0.7007 | 0
| 1.9874 | 0.058398 | 0.66632 | 0
| 2.6782 | 0.038782 | 0.4425 | 0
| 0.79641 | 0.038391 | 0.43804 | 0
| 21.3385 | 0.30148 | 3.4399 | 0
| 0.31093 | 0.0036558 | 0.041713 | 0
| 25.2133 | 0.33269 | 3.796 | 0
| 5.4123 | 0.094914 | 1.083 | 0
| 7.0073 | 0.088187 | 1.0062 | 0
| 9.0026 | 0.18687 | 2.1322 | 0
| 2.9247 | 0.11651 | 1.3294 | 0
| 0.13611 | 0.0014524 | 0.016571 | 0
| 0.46497 | 0.0071361 | 0.081423 | 0
| 0.025185 | 0.00024179 | 0.0027588 | 0
| 0 | 0.1495 | 1.7058 | 0
| 2.683 | 0.045885 | 0.52355 | 0
| 14.4698 | 0.2055 | 2.3447 | 0
| 31.1451 | 0.4295 | 4.9006 | 0
| 3.2574 | 0.041988 | 0.47908 | 0
| 3.0874 | 0.11222 | 1.2805 | 0
| 1.7117 | 0.024046 | 0.27436 | 0
| 7.3794 | 0.095152 | 1.0857 | 0
| 0 | 0.011094 | 0.12659 | 0
| 0.12861 | 0.017641 | 0.20129 | 0
| 0.090862 | 0.002145 | 0.024474 | 0
| 20.2719 | 0.26786 | 3.0562 | 0
| 2.4186 | 0.029937 | 0.34158 | 0
| 1.3462 | 0.012822 | 0.1463 | 0
| 0.87367 | 0.018505 | 0.21114 | 0
| 10.6353 | 0.16667 | 1.9017 | 0
| 2.956 | 0.029842 | 0.3405 | 0
| 13.284 | 0.163 | 1.8598 | 0
| 0.48095 | 0.0039048 | 0.044554 | 0
| 25.0714 | 0.31272 | 3.5681 | 0
| 13.0685 | 0.17714 | 2.0212 | 0
| 11.5727 | 0.16074 | 1.8341 | 0
| 2.5319 | 0.030024 | 0.34258 | 0
| 5.7539 | 0.14362 | 1.6387 | 0
| 1.3004 | 0.017634 | 0.2012 | 0
| 3.2897 | 0.04443 | 0.50695 | 0
| 1.8577 | 0.016197 | 0.18481 | 0
| 9.7511 | 0.12003 | 1.3695 | 0
| 0 | 0.0138 | 0.15746 | 0
| 6.6241 | 0.14728 | 1.6804 | 0
| 10.115 | 0.19564 | 2.2323 | 0
| 1.6439 | 0.038206 | 0.43593 | 0
| 42.0207 | 0.58006 | 6.6185 | 0
| 22.4368 | 0.32021 | 3.6536 | 0
| 9.0414 | 0.22245 | 2.5382 | 0
| 0.80692 | 0.016306 | 0.18605 | 0
| 5.6512 | 0.081709 | 0.9323 | 0
| 0.20411 | 0.0024207 | 0.02762 | 0
| 9.6545 | 0.11883 | 1.3558 | 0
| 6.9691 | 0.094014 | 1.0727 | 0
| 11.3418 | 0.099305 | 1.1331 | 0
| 0.70956 | 0.0092994 | 0.10611 | 0
| 2.1537 | 0.026364 | 0.30082 | 0
| 0.71437 | 0.0093937 | 0.10718 | 0
| 4.4698 | 0.06185 | 0.70571 | 0
| 0.095548 | 0.0018295 | 0.020874 | 0
| 0.73097 | 0.0070259 | 0.080165 | 0
| 0 | 0.018844 | 0.21501 | 0
| 0.77413 | 0.0099223 | 0.11321 | 0
| 3.7869 | 0.049603 | 0.56597 | 0
| 6.4271 | 0.084984 | 0.96967 | 0
| 9.2003 | 0.12354 | 1.4096 | 0
| 4.8437 | 0.088746 | 1.0126 | 0
| 4.1577 | 0.0453 | 0.51688 | 0
| 6.0498 | 0.079781 | 0.9103 | 0
| 11.9179 | 0.22861 | 2.6085 | 0
| 3.448 | 0.060005 | 0.68466 | 0
| 5.7337 | 0.11898 | 1.3576 | 0
| 0.80074 | 0.0096348 | 0.10993 | 0
| 0.68933 | 0.0087222 | 0.09952 | 0
| 13.9147 | 0.19087 | 2.1778 | 0
| 1.0674 | 0.029519 | 0.33681 | 0
| 0.53095 | 0.0043585 | 0.049731 | 0
| 2.0728 | 0.10728 | 1.2241 | 0
| 3.5412 | 0.045217 | 0.51592 | 0
| 6.8012 | 0.086007 | 0.98134 | 0
| 0.8788 | 0.013827 | 0.15777 | 0
| 0.67903 | 0.01204 | 0.13737 | 0
| 0.54407 | 0.011034 | 0.1259 | 0
| 0.78715 | 0.0096817 | 0.11047 | 0
| 1.8517 | 0.026697 | 0.30462 | 0
| 0.0046756 | 0.01014 | 0.1157 | 0
| 0 | 0.00033334 | 0.0038034 | 0
| 2.695 | 0.029694 | 0.33881 | 0
| 0.99134 | 0.0163 | 0.18599 | 0
| 5.5797 | 0.063503 | 0.72457 | 0
| 0.0077088 | 0.00033114 | 0.0037783 | 0
| 9.5888 | 0.23398 | 2.6697 | 0
| 1.1606 | 0.01488 | 0.16979 | 0
| 5.9263 | 0.10482 | 1.196 | 0
| 8.2294 | 0.10737 | 1.2251 | 0
| 1.51 | 0.029061 | 0.33159 | 0
| 6.5571 | 0.089399 | 1.02 | 0
| 25.5064 | 0.30729 | 3.5062 | 0
| 3.4289 | 0.036729 | 0.41908 | 0
| 3.3413 | 0.042232 | 0.48187 | 0
| 30.5888 | 0.44845 | 5.1168 | 0
| 1.9162 | 0.022719 | 0.25922 | 0
| 2.3016 | 0.025884 | 0.29534 | 0
| 17.4486 | 0.2746 | 3.1332 | 0
| 2.6244 | 0.034039 | 0.38839 | 0
| 0.73585 | 0.0073462 | 0.08382 | 0
| 8.3188 | 0.10458 | 1.1932 | 0
| 2.8495 | 0.044012 | 0.50217 | 0
| 15.9229 | 0.19826 | 2.2621 | 0
| 0.876 | 0.015628 | 0.17832 | 0
| 0.72613 | 0.0096974 | 0.11065 | 0
| 3.6622 | 0.049064 | 0.55982 | 0
| 29.9393 | 0.50792 | 5.7954 | 0
| 2.0132 | 0.022908 | 0.26138 | 0
| 6.8562 | 0.083792 | 0.95607 | 0
| 0.35023 | 0.20258 | 2.3115 | 0
| 11.6636 | 0.13827 | 1.5777 | 0
| 4.9629 | 0.14823 | 1.6913 | 0
| 23.564 | 0.32063 | 3.6584 | 0
| 0.17757 | 0.0035197 | 0.04016 | 0
| 3.6077 | 0.038806 | 0.44278 | 0
| 6.4841 | 0.077884 | 0.88866 | 0
| 18.6295 | 0.23201 | 2.6472 | 0
| 4.9554 | 0.050358 | 0.57458 | 0
| 19.967 | 0.35818 | 4.0868 | 0
| 1.1233 | 0.018763 | 0.21408 | 0
| 8.3997 | 0.10987 | 1.2537 | 0
| 1.4558 | 0.018094 | 0.20646 | 0
| 3.1635 | 0.038596 | 0.44038 | 0
| 3.2643 | 0.06023 | 0.68723 | 0
| 8.066 | 0.13862 | 1.5816 | 0
| 4.125 | 0.046086 | 0.52584 | 0
| 2.6034 | 0.036554 | 0.41708 | 0
| 2.4953 | 0.045672 | 0.52112 | 0
| 3.9864 | 0.048502 | 0.55341 | 0
| 12.2805 | 0.29549 | 3.3715 | 0
| 0.085433 | 0.0027235 | 0.031075 | 0
| 2.8956 | 0.029835 | 0.34042 | 0
| 5.6099 | 0.07389 | 0.84308 | 0
| 3.8976 | 0.18434 | 2.1034 | 0
| 5.2644 | 0.078376 | 0.89427 | 0
| 2.6859 | 0.030086 | 0.34328 | 0
| 3.1154 | 0.036142 | 0.41238 | 0
| 6.1722 | 0.13892 | 1.5851 | 0
| 0.55683 | 0.018365 | 0.20955 | 0
| 0.57868 | 0.0089221 | 0.1018 | 0
| 0 | 0.0012428 | 0.01418 | 0
| 2.5936 | 0.058401 | 0.66635 | 0
| 0.39912 | 0.0052523 | 0.059929 | 0
| 4.3894 | 0.081283 | 0.92744 | 0
| 7.9659 | 0.10268 | 1.1716 | 0
| 18.6943 | 0.21777 | 2.4847 | 0
| 0.57093 | 0.018856 | 0.21514 | 0
| 0 | 0.0087907 | 0.1003 | 0
| 4.9897 | 0.061204 | 0.69834 | 0
| 0.77287 | 0.011321 | 0.12918 | 0
| 27.0613 | 0.30008 | 3.4239 | 0
| 0.15661 | 0.0091294 | 0.10417 | 0
| 2.2373 | 0.023927 | 0.273 | 0
| 24.028 | 0.33782 | 3.8546 | 0
| 1.8597 | 0.020673 | 0.23587 | 0
| 3.9221 | 0.045339 | 0.51732 | 0
| 0.4446 | 0.016291 | 0.18588 | 0
| 0.46929 | 0.0068261 | 0.077886 | 0
| 12.3249 | 0.15897 | 1.8138 | 0
| 0.56787 | 0.051354 | 0.58595 | 0
| 0.93128 | 0.018896 | 0.2156 | 0
| 6.2693 | 0.070606 | 0.80562 | 0
| 6.8675 | 0.10726 | 1.2238 | 0
| 6.2533 | 0.07964 | 0.9087 | 0
| 0.52069 | 0.0083332 | 0.095082 | 0
| 4.2664 | 0.043014 | 0.49079 | 0
| 3.0001 | 0.1292 | 1.4742 | 0
| 6.3915 | 0.1991 | 2.2717 | 0
| 0.333 | 0.003557 | 0.040586 | 0
| 0.29166 | 0.0037471 | 0.042754 | 0
| 0.6452 | 0.0079819 | 0.091073 | 0
| 13.3137 | 0.1525 | 1.74 | 0
| 12.1031 | 0.1197 | 1.3658 | 0
| 2.9117 | 0.076875 | 0.87715 | 0
| 6.5038 | 0.070464 | 0.804 | 0
| 0.46327 | 0.0047157 | 0.053807 | 0
| 1.8001 | 0.018549 | 0.21164 | 0
| 1.3758 | 0.009123 | 0.10409 | 0
| 38.3804 | 0.41774 | 4.7664 | 0
| 0.88798 | 0.0061604 | 0.07029 | 0
| 1.0087 | 0.011145 | 0.12716 | 0
| 2.1334 | 0.030075 | 0.34316 | 0
| 0.28957 | 0.036061 | 0.41145 | 0
| 1.2197 | 0.040219 | 0.45889 | 0
| 19.621 | 0.22814 | 2.603 | 0
| 55.5154 | 0.58079 | 6.6268 | 0
| 0.037809 | 0.0139 | 0.1586 | 0
| 2.1877 | 0.078954 | 0.90086 | 0
| 15.413 | 0.38036 | 4.3399 | 0
| 0.036725 | 0.001154 | 0.013167 | 0
| 9.234 | 0.15842 | 1.8076 | 0
| 6.9913 | 0.1268 | 1.4468 | 0
| 6.083 | 0.071695 | 0.81804 | 0
| 1.7765 | 0.018958 | 0.21631 | 0
| 0.17627 | 0.0025825 | 0.029466 | 0
| 0.25274 | 0.0030593 | 0.034907 | 0
| 2.1066 | 0.044751 | 0.51061 | 0
| 4.371 | 0.15991 | 1.8246 | 0
| 0.21013 | 0.0034224 | 0.03905 | 0
| 10.8 | 0.1179 | 1.3452 | 0
| 1.3758 | 0.040144 | 0.45805 | 0
| 6.6631 | 0.087683 | 1.0005 | 0
| 2.2203 | 0.027038 | 0.3085 | 0
| 0.063881 | 0.0019916 | 0.022724 | 0
| 10.2114 | 0.14535 | 1.6585 | 0
| 1.337 | 0.01445 | 0.16487 | 0
| 16.4629 | 0.22627 | 2.5818 | 0
| 15.8629 | 0.17785 | 2.0292 | 0
| 8.7542 | 0.10353 | 1.1812 | 0
| 1.7189 | 0.018966 | 0.21641 | 0
| 20.3246 | 0.20551 | 2.3449 | 0
| 5.8088 | 0.06188 | 0.70605 | 0
| 0.016579 | 0.010726 | 0.12239 | 0
| 16.6965 | 0.1993 | 2.274 | 0
| 0.016114 | 0.00028117 | 0.0032082 | 0
| 17.2978 | 0.20777 | 2.3706 | 0
| 3.939 | 0.040996 | 0.46777 | 0
| 4.947 | 0.054959 | 0.62708 | 0
| 4.7863 | 0.10282 | 1.1732 | 0
| 17.248 | 0.18554 | 2.1171 | 0
| 0.019395 | 0.013722 | 0.15657 | 0
| 0 | 0.10219 | 1.166 | 0
| 13.6519 | 0.15366 | 1.7533 | 0
| 9.132 | 0.097116 | 1.1081 | 0
| 2.7103 | 0.027142 | 0.3097 | 0
| 5.5843 | 0.05651 | 0.64477 | 0
| 1.4422 | 0.017048 | 0.19452 | 0
| 44.6471 | 0.46018 | 5.2506 | 0
| 11.2832 | 0.12231 | 1.3956 | 0
| 22.6693 | 0.23245 | 2.6523 | 0
| 7.4795 | 0.082528 | 0.94165 | 0
| 0.21526 | 0.026207 | 0.29902 | 0
| 1.0663 | 0.01254 | 0.14308 | 0
| 1.5884 | 0.041234 | 0.47048 | 0
| 4.8955 | 0.052374 | 0.59759 | 0
| 0 | 9.2793e-05 | 0.0010588 | 0
| 10.9084 | 0.3089 | 3.5246 | 0
| 21.1159 | 0.23065 | 2.6317 | 0
| 0.81836 | 0.0090735 | 0.10353 | 0
| 2.2021 | 0.033513 | 0.38239 | 0
| 1.5618 | 0.015252 | 0.17403 | 0
| 10.762 | 0.10448 | 1.1921 | 0
| 0.1415 | 0.077034 | 0.87896 | 0
| 4.2417 | 0.049006 | 0.55916 | 0
| 5.2366 | 0.066025 | 0.75335 | 0
| 9.0769 | 0.096691 | 1.1032 | 0
| 2.389 | 0.18823 | 2.1477 | 0
| 4.372 | 0.050197 | 0.57275 | 0
| 3.493 | 0.031372 | 0.35795 | 0
| 4.765 | 0.047696 | 0.54421 | 0
| 17.4522 | 0.19063 | 2.1751 | 0
| 1.3221 | 0.17423 | 1.988 | 0
| 4.4104 | 0.18081 | 2.063 | 0
| 6.838 | 0.072151 | 0.82324 | 0
| 16.559 | 0.16541 | 1.8874 | 0
| 0.39175 | 0.0050933 | 0.058115 | 0
| 0.82419 | 0.012537 | 0.14305 | 0
| 1.0558 | 0.015259 | 0.1741 | 0
| 4.7662 | 0.055004 | 0.62759 | 0
| 3.046 | 0.034946 | 0.39874 | 0
| 3.2148 | 0.037663 | 0.42973 | 0
| 9.0497 | 0.093185 | 1.0632 | 0
| 3.3793 | 0.060908 | 0.69496 | 0
| 7.5664 | 0.068873 | 0.78585 | 0
| 6.3629 | 0.084986 | 0.96969 | 0
| 0.56079 | 0.012041 | 0.13738 | 0
| 6.8396 | 0.071658 | 0.81762 | 0
| 5.7814 | 0.078569 | 0.89648 | 0
| 0.16628 | 0.025816 | 0.29456 | 0
| 0.94661 | 0.024168 | 0.27575 | 0
| 0.84478 | 0.016889 | 0.19271 | 0
| 1.6614 | 0.016595 | 0.18935 | 0
| 8.4361 | 0.1038 | 1.1843 | 0
| 10.9751 | 0.11046 | 1.2604 | 0
| 28.2864 | 0.28901 | 3.2976 | 0
| 3.4788 | 0.030632 | 0.34951 | 0
| 5.9474 | 0.1098 | 1.2528 | 0
| 3.9606 | 0.092249 | 1.0526 | 0
| 2.4763 | 0.023566 | 0.26889 | 0
| 6.5747 | 0.067443 | 0.76952 | 0
| 1.2131 | 0.010262 | 0.11709 | 0
| 8.0562 | 0.11846 | 1.3516 | 0
| 2.0341 | 0.098682 | 1.126 | 0
| 0.71914 | 0.023217 | 0.2649 | 0
| 7.5438 | 0.070966 | 0.80972 | 0
| 0 | 0.019248 | 0.21962 | 0
| 2.4077 | 0.025559 | 0.29163 | 0
| 18.2975 | 0.19097 | 2.179 | 0
| 0.37255 | 0.0050477 | 0.057594 | 0
| 3.6117 | 0.040242 | 0.45916 | 0
| 0.46627 | 0.027614 | 0.31507 | 0
| 1.7138 | 0.018028 | 0.2057 | 0
| 9.8836 | 0.10069 | 1.1489 | 0
| 0 | 0.00017455 | 0.0019917 | 0
| 18.4131 | 0.18017 | 2.0557 | 0
| 3.5772 | 0.037599 | 0.429 | 0
| 7.2877 | 0.068636 | 0.78314 | 0
| 2.4908 | 0.061441 | 0.70105 | 0
| 1.7919 | 0.020237 | 0.2309 | 0
| 3.0241 | 0.021143 | 0.24125 | 0
| 4.0531 | 0.17045 | 1.9449 | 0
| 3.4139 | 0.092337 | 1.0536 | 0
| 14.0013 | 0.13177 | 1.5035 | 0
| 15.5972 | 0.1429 | 1.6305 | 0
| 19.1851 | 0.21225 | 2.4218 | 0
| 1.9912 | 0.028284 | 0.32272 | 0
| 16.7608 | 0.1793 | 2.0458 | 0
| 5.4418 | 0.04238 | 0.48356 | 0
| 0.13739 | 0.0020711 | 0.023631 | 0
| 5.1044 | 0.056154 | 0.64072 | 0
| 9.686 | 0.15232 | 1.738 | 0
| 6.5681 | 0.086679 | 0.989 | 0
| 0.32287 | 0.0027545 | 0.031429 | 0
| 0.24772 | 0.0033507 | 0.038231 | 0
| 9.084 | 0.088233 | 1.0067 | 0
| 2.3952 | 0.026235 | 0.29934 | 0
| 8.2889 | 0.094101 | 1.0737 | 0
| 2.5178 | 0.032098 | 0.36624 | 0
| 2.3019 | 0.021287 | 0.24289 | 0
| 4.6533 | 0.080765 | 0.92152 | 0
| 1.3978 | 0.017775 | 0.20282 | 0
| 1.3838 | 0.019223 | 0.21934 | 0
| 0.83458 | 0.012446 | 0.14201 | 0
| 1.3241 | 0.053958 | 0.61567 | 0
| 3.521 | 0.042328 | 0.48297 | 0
| 23.6643 | 0.22706 | 2.5907 | 0
| 1.533 | 0.023927 | 0.27301 | 0
| 1.8112 | 0.017817 | 0.20329 | 0
| 5.2488 | 0.049595 | 0.56588 | 0
| 0.95121 | 0.0099141 | 0.11312 | 0
| 0.96482 | 0.0093765 | 0.10699 | 0
| 17.5094 | 0.16261 | 1.8554 | 0
| 1.2536 | 0.012649 | 0.14432 | 0
| 8.4244 | 0.12316 | 1.4053 | 0
| 0.91306 | 0.029324 | 0.33459 | 0
| 8.9039 | 0.080175 | 0.9148 | 0
| 0 | 0.022456 | 0.25622 | 0
| 0.41344 | 0.01502 | 0.17138 | 0
| 1.5034 | 0.015854 | 0.18089 | 0
| 1.9372 | 0.060748 | 0.69313 | 0
| 5.8567 | 0.058464 | 0.66708 | 0
| 5.7828 | 0.051291 | 0.58524 | 0
| 1.2413 | 0.051416 | 0.58666 | 0
| 13.9138 | 0.13199 | 1.5061 | 0
| 14.9346 | 0.19206 | 2.1914 | 0
| 6.3695 | 0.092616 | 1.0567 | 0
| 12.7826 | 0.19636 | 2.2405 | 0
| 16.6863 | 0.1585 | 1.8084 | 0
| 37.6702 | 0.38363 | 4.3772 | 0
| 1.1962 | 0.073877 | 0.84293 | 0
| 45.5565 | 0.40087 | 4.5739 | 0
| 10.7204 | 0.14496 | 1.654 | 0
| 35.2624 | 0.33076 | 3.7739 | 0
| 0.64336 | 0.034746 | 0.39645 | 0
| 0.85753 | 0.0095943 | 0.10947 | 0
| 0.043348 | 0.0034439 | 0.039295 | 0
| 3.727 | 0.031154 | 0.35547 | 0
| 3.4487 | 0.034307 | 0.39145 | 0
| 0 | 0.0066272 | 0.075616 | 0
| 0.89903 | 0.024761 | 0.28252 | 0
| 0.45975 | 0.012702 | 0.14492 | 0
| 2.8445 | 0.025718 | 0.29345 | 0
| 0.78632 | 0.010095 | 0.11518 | 0
| 8.2414 | 0.076637 | 0.87442 | 0
| 0.21004 | 0.02465 | 0.28126 | 0
| 8.3223 | 0.14488 | 1.6531 | 0
| 10.9525 | 0.17221 | 1.9649 | 0
| 2.24 | 0.065955 | 0.75255 | 0
| 19.6722 | 0.19312 | 2.2035 | 0
| 10.067 | 0.09534 | 1.0878 | 0
| 1.1894 | 0.021489 | 0.24519 | 0
| 1.4298 | 0.013036 | 0.14874 | 0
| 13.7665 | 0.12446 | 1.4201 | 0
| 21.4528 | 0.23404 | 2.6704 | 0
| 12.6501 | 0.17421 | 1.9877 | 0
| 20.692 | 0.18862 | 2.1522 | 0
| 4.7527 | 0.041077 | 0.46869 | 0
| 15.205 | 0.15636 | 1.7841 | 0
| 55.6001 | 0.48336 | 5.5151 | 0
| 10.8373 | 0.10294 | 1.1746 | 0
| 0 | 0.047342 | 0.54018 | 0
| 12.5693 | 0.11824 | 1.3491 | 0
| 0.76793 | 0.0087199 | 0.099495 | 0
| 0.39264 | 0.013314 | 0.15191 | 0
| 5.3709 | 0.11187 | 1.2765 | 0
| 18.1452 | 0.16403 | 1.8716 | 0
| 1.9982 | 0.021364 | 0.24376 | 0
| 1.4595 | 0.041535 | 0.47392 | 0
| 4.1155 | 0.03627 | 0.41384 | 0
| 4.0682 | 0.028269 | 0.32254 | 0
| 6.3495 | 0.061289 | 0.69931 | 0
| 0.078744 | 0.010389 | 0.11854 | 0
| 11.629 | 0.092704 | 1.0578 | 0
| 0.094001 | 0.00070559 | 0.0080507 | 0
| 10.3799 | 0.13429 | 1.5322 | 0
| 2.2087 | 0.025144 | 0.28689 | 0
| 0.31793 | 0.0028177 | 0.03215 | 0
| 2.283 | 0.10024 | 1.1438 | 0
| 1.2395 | 0.01338 | 0.15267 | 0
| 13.5717 | 0.11677 | 1.3324 | 0
| 4.127 | 0.057046 | 0.65089 | 0
| 0.60048 | 0.006073 | 0.069293 | 0
| 0.013142 | 0.00069902 | 0.0079759 | 0
| 28.3613 | 0.24894 | 2.8404 | 0
| 11.3509 | 0.11451 | 1.3065 | 0
| 1.8158 | 0.031299 | 0.35712 | 0
| 8.0225 | 0.070871 | 0.80864 | 0
| 2.4217 | 0.020841 | 0.2378 | 0
| 7.9829 | 0.068743 | 0.78436 | 0
| 7.3243 | 0.093951 | 1.072 | 0
| 6.4622 | 0.086972 | 0.99236 | 0
| 7.1309 | 0.092959 | 1.0607 | 0
| 0.6091 | 0.011508 | 0.13131 | 0
| 0.95277 | 0.0087774 | 0.10015 | 0
| 1.1789 | 0.010093 | 0.11516 | 0
| 10.3043 | 0.088665 | 1.0117 | 0
| 10.3655 | 0.084169 | 0.96037 | 0
| 5.3541 | 0.044493 | 0.50767 | 0
| 1.4725 | 0.036931 | 0.42139 | 0
| 4.8762 | 0.038401 | 0.43815 | 0
| 9.7094 | 0.087418 | 0.99744 | 0
| 4.8359 | 0.036118 | 0.41211 | 0
| 4.3788 | 0.040714 | 0.46455 | 0
| 8.1722 | 0.078585 | 0.89666 | 0
| 0.81657 | 0.0074997 | 0.085572 | 0
| 1.3304 | 0.022197 | 0.25327 | 0
| 14.129 | 0.15792 | 1.8019 | 0
| 7.4489 | 0.066628 | 0.76022 | 0
| 16.7162 | 0.15429 | 1.7605 | 0
| 14.758 | 0.12203 | 1.3924 | 0
| 2.2879 | 0.019699 | 0.22477 | 0
| 4.8062 | 0.045353 | 0.51748 | 0
| 2.3874 | 0.023634 | 0.26967 | 0
| 14.8067 | 0.1526 | 1.7412 | 0
| 3.0778 | 0.038721 | 0.44181 | 0
| 0.30394 | 0.0037825 | 0.043158 | 0
| 0.36093 | 0.0071159 | 0.081192 | 0
| 5.3115 | 0.061312 | 0.69957 | 0
| 5.7134 | 0.12103 | 1.3809 | 0
| 1.4802 | 0.014414 | 0.16447 | 0
| 18.8368 | 0.1787 | 2.0389 | 0
| 23.2586 | 0.20035 | 2.286 | 0
| 34.7673 | 0.26413 | 3.0137 | 0
| 6.9283 | 0.051121 | 0.58329 | 0
| 7.7413 | 0.068737 | 0.78429 | 0
| 0.56737 | 0.0083799 | 0.095614 | 0
| 0.79566 | 0.0066019 | 0.075328 | 0
| 1.4554 | 0.012468 | 0.14226 | 0
| 3.2613 | 0.025519 | 0.29118 | 0
| 5.5656 | 0.082229 | 0.93823 | 0
| 0.20066 | 0.0024148 | 0.027552 | 0
| 8.793 | 0.12596 | 1.4372 | 0
| 1.0572 | 0.0076626 | 0.08743 | 0
| 4.4328 | 0.040681 | 0.46417 | 0
| 0.29687 | 0.0026238 | 0.029937 | 0
| 0.11384 | 0.0088736 | 0.10125 | 0
| 2.9382 | 0.020681 | 0.23597 | 0
| 1.1388 | 0.058702 | 0.66979 | 0
| 1.1411 | 0.028912 | 0.32988 | 0
| 5.1487 | 0.042662 | 0.48677 | 0
| 4.6074 | 0.051464 | 0.58721 | 0
| 9.0089 | 0.066226 | 0.75564 | 0
| 1.4439 | 0.010602 | 0.12097 | 0
| 7.3421 | 0.062697 | 0.71537 | 0
| 8.1458 | 0.061875 | 0.706 | 0
| 0.61554 | 0.0096949 | 0.11062 | 0
| 0.62875 | 0.0075255 | 0.085866 | 0
| 0.42746 | 0.0049393 | 0.056358 | 0
| 1.8107 | 0.029905 | 0.34122 | 0
| 10.0801 | 0.1714 | 1.9556 | 0
| 0.11569 | 0.013296 | 0.15171 | 0
| 0.075062 | 0.0077181 | 0.088064 | 0
| 0.94365 | 0.011772 | 0.13432 | 0
| 0 | 0.00010686 | 0.0012193 | 0
| 0 | 0.0013433 | 0.015327 | 0
| 6.5507 | 0.071659 | 0.81763 | 0
| 3.4777 | 0.19842 | 2.264 | 0
| 0.022592 | 0.00021288 | 0.002429 | 0
| 15.2058 | 0.11027 | 1.2582 | 0
| 11.427 | 0.093806 | 1.0703 | 0
| 3.2468 | 0.025942 | 0.296 | 0
| 0.80916 | 0.0074262 | 0.084733 | 0
| 3.6583 | 0.035418 | 0.40412 | 0
| 1.7141 | 0.030103 | 0.34348 | 0
| 0 | 0.015444 | 0.17622 | 0
| 5.5871 | 0.045626 | 0.52059 | 0
| 9.5866 | 0.10873 | 1.2406 | 0
| 14.3504 | 0.11527 | 1.3152 | 0
| 22.0862 | 0.19544 | 2.2299 | 0
| 0.80937 | 0.012011 | 0.13704 | 0
| 6.9131 | 0.049855 | 0.56885 | 0
| 10.5497 | 0.07844 | 0.895 | 0
| 4.3843 | 0.033695 | 0.38445 | 0
| 1.5264 | 0.040244 | 0.45919 | 0
| 17.9281 | 0.14822 | 1.6912 | 0
| 13.9976 | 0.10593 | 1.2087 | 0
| 3.7689 | 0.027302 | 0.31152 | 0
| 18.5596 | 0.15693 | 1.7906 | 0
| 7.6838 | 0.094092 | 1.0736 | 0
| 23.8772 | 0.20255 | 2.3111 | 0
| 2.3674 | 0.029902 | 0.34118 | 0
| 0.67675 | 0.035176 | 0.40136 | 0
| 6.1618 | 0.08926 | 1.0185 | 0
| 1.9982 | 0.010302 | 0.11754 | 0
| 0.81695 | 0.014887 | 0.16986 | 0
| 7.2555 | 0.090527 | 1.0329 | 0
| 3.4393 | 0.033517 | 0.38243 | 0
| 1.8748 | 0.036807 | 0.41997 | 0
| 3.6336 | 0.042532 | 0.48529 | 0
| 2.3497 | 0.022718 | 0.25921 | 0
| 16.012 | 0.12271 | 1.4001 | 0
| 2.0766 | 0.011817 | 0.13484 | 0
| 0.1163 | 0.00061111 | 0.0069728 | 0
| 8.2565 | 0.081891 | 0.93438 | 0
| 4.8486 | 0.059173 | 0.67516 | 0
| 0.92129 | 0.0058281 | 0.066499 | 0
| 4.4525 | 0.041153 | 0.46955 | 0
| 12.0926 | 0.10172 | 1.1606 | 0
| 8.6033 | 0.065519 | 0.74757 | 0
| 0.6268 | 0.0028385 | 0.032387 | 0
| 5.9956 | 0.03323 | 0.37916 | 0
| 0.11882 | 0.0012154 | 0.013868 | 0
| 8.6773 | 0.06675 | 0.76161 | 0
| 15.278 | 0.17744 | 2.0246 | 0
| 1.3654 | 0.061302 | 0.69945 | 0
| 12.3703 | 0.091577 | 1.0449 | 0
| 27.0343 | 0.20717 | 2.3638 | 0
| 0.49928 | 0.016445 | 0.18764 | 0
| 8.9619 | 0.080971 | 0.92388 | 0
| 10.3423 | 0.10095 | 1.1518 | 0
| 3.8025 | 0.03651 | 0.41658 | 0
| 18.517 | 0.14881 | 1.6979 | 0
| 0.81139 | 0.035878 | 0.40937 | 0
| 0.52714 | 0.0028393 | 0.032396 | 0
| 19.6109 | 0.15145 | 1.7281 | 0
| 17.8955 | 0.13322 | 1.52 | 0
| 4.1555 | 0.068188 | 0.77803 | 0
| 0.64089 | 0.0049297 | 0.056248 | 0
| 5.4669 | 0.063851 | 0.72854 | 0
| 12.6474 | 0.18489 | 2.1096 | 0
| 1.0646 | 0.01336 | 0.15244 | 0
| 0.05237 | 0.00052376 | 0.0059761 | 0
| 3.2458 | 0.026504 | 0.30242 | 0
| 2.4208 | 0.017055 | 0.19459 | 0
| 2.119 | 0.027919 | 0.31856 | 0
| 7.9195 | 0.12583 | 1.4357 | 0
| 15.8992 | 0.11695 | 1.3344 | 0
| 10.0105 | 0.074821 | 0.85371 | 0
| 5.8548 | 0.095663 | 1.0915 | 0
| 0.48703 | 0.0037099 | 0.042331 | 0
| 22.281 | 0.17394 | 1.9847 | 0
| 1.7182 | 0.017957 | 0.20489 | 0
| 7.0969 | 0.072331 | 0.8253 | 0
| 5.4382 | 0.12269 | 1.3999 | 0
| 20.5499 | 0.15038 | 1.7158 | 0
| 0.33943 | 0.0033053 | 0.037713 | 0
| 0 | 0.00019417 | 0.0022155 | 0
| 1.9879 | 0.021066 | 0.24036 | 0
| 1.0487 | 0.0085287 | 0.097313 | 0
| 0.65852 | 0.010465 | 0.1194 | 0
| 9.5558 | 0.072642 | 0.82885 | 0
| 13.8446 | 0.10279 | 1.1728 | 0
| 4.5639 | 0.037497 | 0.42784 | 0
| 5.5249 | 0.041694 | 0.47573 | 0
| 8.506 | 0.06403 | 0.73058 | 0
| 14.6743 | 0.10707 | 1.2216 | 0
| 3.2989 | 0.044373 | 0.5063 | 0
| 3.5686 | 0.055509 | 0.63336 | 0
| 28.6376 | 0.21679 | 2.4736 | 0
| 2.9201 | 0.023064 | 0.26316 | 0
| 12.0336 | 0.10651 | 1.2153 | 0
| 0.16317 | 0.0036142 | 0.041238 | 0
| 12.8088 | 0.091594 | 1.0451 | 0
| 3.4871 | 0.036516 | 0.41664 | 0
| 1.9685 | 0.015882 | 0.18121 | 0
| 20.0559 | 0.15259 | 1.7411 | 0
| 7.3737 | 0.064493 | 0.73586 | 0
| 9.5458 | 0.08499 | 0.96974 | 0
| 12.4405 | 0.098369 | 1.1224 | 0
| 1.3574 | 0.0089003 | 0.10155 | 0
| 1.8772 | 0.059211 | 0.6756 | 0
| 0.30472 | 0.0098003 | 0.11182 | 0
| 9.0645 | 0.10212 | 1.1652 | 0
| 6.0651 | 0.059864 | 0.68305 | 0
| 1.5555 | 0.067931 | 0.77509 | 0
| 46.5716 | 0.3375 | 3.8508 | 0
| 9.6134 | 0.070101 | 0.79986 | 0
| 0.92326 | 0.037189 | 0.42432 | 0
| 2.1935 | 0.022235 | 0.2537 | 0
| 4.5422 | 0.042346 | 0.48316 | 0
| 3.0069 | 0.030451 | 0.34745 | 0
| 2.4871 | 0.016614 | 0.18956 | 0
| 0.017864 | 0.00037317 | 0.0042579 | 0
| 18.0353 | 0.13398 | 1.5287 | 0
| 3.3429 | 0.042076 | 0.48009 | 0
| 2.5574 | 0.016119 | 0.18392 | 0
| 10.3058 | 0.069733 | 0.79566 | 0
| 3.2895 | 0.041343 | 0.47173 | 0
| 4.5366 | 0.036051 | 0.41135 | 0
| 5.5619 | 0.041519 | 0.47373 | 0
| 5.5655 | 0.057043 | 0.65086 | 0
| 7.5511 | 0.057384 | 0.65475 | 0
| 2.0531 | 0.021581 | 0.24624 | 0
| 1.2542 | 0.013273 | 0.15145 | 0
| 12.3893 | 0.087148 | 0.99436 | 0
| 0.984 | 0.030696 | 0.35024 | 0
| 9.2836 | 0.067072 | 0.76529 | 0
| 5.1012 | 0.1182 | 1.3487 | 0
| 0.21148 | 0.0070899 | 0.080896 | 0
| 0.23156 | 0.0036608 | 0.04177 | 0
| 2.1759 | 0.027899 | 0.31833 | 0
| 2.9333 | 0.023936 | 0.27311 | 0
| 17.537 | 0.19657 | 2.2429 | 0
| 12.081 | 0.095734 | 1.0923 | 0
| 2.1578 | 0.033657 | 0.38403 | 0
| 26.8537 | 0.18781 | 2.1429 | 0
| 0.47405 | 0.0065318 | 0.074528 | 0
| 5.7826 | 0.061976 | 0.70715 | 0
| 2.3787 | 0.019751 | 0.22536 | 0
| 7.7103 | 0.081538 | 0.93035 | 0
| 2.9986 | 0.076475 | 0.87258 | 0
| 0.10612 | 0.0037955 | 0.043307 | 0
| 6.0014 | 0.1253 | 1.4297 | 0
| 7.843 | 0.059266 | 0.67623 | 0
| 13.5612 | 0.092222 | 1.0522 | 0
| 0.11382 | 0.0023397 | 0.026696 | 0
| 7.7868 | 0.074935 | 0.85501 | 0
| 0.17687 | 0.023988 | 0.27371 | 0
| 0.76886 | 0.0082481 | 0.094111 | 0
| 0.80666 | 0.0090847 | 0.10366 | 0
| 2.8192 | 0.06399 | 0.73013 | 0
| 8.5118 | 0.13507 | 1.5411 | 0
| 2.3343 | 0.01744 | 0.19899 | 0
| 0.29698 | 0.0090563 | 0.10333 | 0
| 2.6244 | 0.033452 | 0.38169 | 0
| 6.2138 | 0.05147 | 0.58727 | 0
| 13.0144 | 0.08811 | 1.0053 | 0
| 1.3787 | 0.0080229 | 0.091541 | 0
| 0.70069 | 0.021241 | 0.24236 | 0
| 26.4574 | 0.17866 | 2.0385 | 0
| 0.55813 | 0.0056759 | 0.064762 | 0
| 7.0669 | 0.18582 | 2.1202 | 0
| 21.666 | 0.1483 | 1.6921 | 0
| 3.3909 | 0.030175 | 0.3443 | 0
| 0.31128 | 0.012176 | 0.13893 | 0
| 2.5947 | 0.022388 | 0.25544 | 0
| 13.5823 | 0.12972 | 1.4801 | 0
| 7.329 | 0.086796 | 0.99034 | 0
| 23.5186 | 0.16343 | 1.8647 | 0
| 0.69921 | 0.0070187 | 0.080083 | 0
| 8.3341 | 0.077172 | 0.88053 | 0
| 5.3369 | 0.03844 | 0.4386 | 0
| 0.98012 | 0.013908 | 0.1587 | 0
| 11.8821 | 0.19085 | 2.1776 | 0
| 0.81682 | 0.010746 | 0.12261 | 0
| 0.19874 | 0.014732 | 0.16809 | 0
| 4.6367 | 0.031147 | 0.35539 | 0
| 1.5755 | 0.11515 | 1.3139 | 0
| 7.4195 | 0.1199 | 1.368 | 0
| 23.3983 | 0.15565 | 1.776 | 0
| 0.78169 | 0.0079643 | 0.090873 | 0
| 1.5552 | 0.010801 | 0.12323 | 0
| 6.7467 | 0.048649 | 0.55508 | 0
| 23.1334 | 0.14962 | 1.7072 | 0
| 57.1253 | 0.34216 | 3.9041 | 0
| 1.077 | 0.013127 | 0.14978 | 0
| 17.1005 | 0.15184 | 1.7325 | 0
| 1.9328 | 0.016335 | 0.18638 | 0
| 5.5597 | 0.035008 | 0.39944 | 0
| 0.2606 | 0.018342 | 0.20928 | 0
| 1.0718 | 0.02007 | 0.22899 | 0
| 0.89174 | 0.010674 | 0.12179 | 0
| 2.6882 | 0.024037 | 0.27426 | 0
| 14.7065 | 0.097771 | 1.1156 | 0
| 0.16959 | 0.0038866 | 0.044346 | 0
| 4.5527 | 0.028216 | 0.32195 | 0
| 0.54808 | 0.0072035 | 0.082192 | 0
| 5.8545 | 0.041671 | 0.47547 | 0
| 0.23531 | 0.015145 | 0.17281 | 0
| 2.5211 | 0.03634 | 0.41464 | 0
| 0.19223 | 0.0051575 | 0.058847 | 0
| 0.5445 | 0.0074956 | 0.085525 | 0
| 2.9914 | 0.12049 | 1.3748 | 0
| 0.34527 | 0.0038469 | 0.043893 | 0
| 1.681 | 0.013366 | 0.1525 | 0
| 0.45837 | 0.0031736 | 0.03621 | 0
| 6.1702 | 0.1207 | 1.3772 | 0
| 23.4195 | 0.15752 | 1.7973 | 0
| 15.519 | 0.10007 | 1.1418 | 0
| 17.6967 | 0.1881 | 2.1462 | 0
| 4.0536 | 0.022736 | 0.25942 | 0
| 4.2022 | 0.033182 | 0.3786 | 0
| 3.1535 | 0.018085 | 0.20635 | 0
| 7.2183 | 0.082057 | 0.93627 | 0
| 2.0226 | 0.018715 | 0.21354 | 0
| 0.83969 | 0.0056734 | 0.064734 | 0
| 8.836 | 0.056732 | 0.64731 | 0
| 20.2424 | 0.15278 | 1.7432 | 0
| 12.5478 | 0.077289 | 0.88187 | 0
| 4.1937 | 0.029119 | 0.33225 | 0
| 8.9834 | 0.057445 | 0.65545 | 0
| 2.4123 | 0.018789 | 0.21438 | 0
| 3.649 | 0.031977 | 0.36485 | 0
| 24.9502 | 0.18403 | 2.0997 | 0
| 0.18074 | 0.0021202 | 0.024191 | 0
| 0.43793 | 0.005055 | 0.057677 | 0
| 3.0013 | 0.022326 | 0.25474 | 0
| 5.1224 | 0.042601 | 0.48608 | 0
| 1.3593 | 0.0068316 | 0.077948 | 0
| 0.19111 | 0.014526 | 0.16574 | 0
| 0.52046 | 0.013333 | 0.15212 | 0
| 0.11683 | 0.092177 | 1.0517 | 0
| 13.5287 | 0.096672 | 1.103 | 0
| 19.3839 | 0.18531 | 2.1144 | 0
| 4.0556 | 0.029297 | 0.33428 | 0
| 4.5604 | 0.045601 | 0.52031 | 0
| 13.7496 | 0.091989 | 1.0496 | 0
| 3.0163 | 0.020859 | 0.238 | 0
| 2.2754 | 0.080614 | 0.9198 | 0
| 0.88152 | 0.045961 | 0.52442 | 0
| 0.45936 | 0.011063 | 0.12623 | 0
| 23.6023 | 0.15642 | 1.7848 | 0
| 0.73831 | 0.010082 | 0.11504 | 0
| 0.44543 | 0.0046336 | 0.05287 | 0
| 4.8692 | 0.029167 | 0.33279 | 0
| 16.8248 | 0.10516 | 1.1999 | 0
| 32.6795 | 0.21965 | 2.5062 | 0
| 0.38791 | 0.014118 | 0.16109 | 0
| 0.61081 | 0.0055724 | 0.063581 | 0
| 0.10416 | 0.0050869 | 0.058042 | 0
| 5.1507 | 0.051976 | 0.59305 | 0
| 3.0138 | 0.039659 | 0.45251 | 0
| 0.18788 | 0.016665 | 0.19014 | 0
| 0.9134 | 0.0099955 | 0.11405 | 0
| 1.1054 | 0.011414 | 0.13024 | 0
| 2.0731 | 0.027311 | 0.31162 | 0
| 10.9407 | 0.093654 | 1.0686 | 0
| 17.6135 | 0.096947 | 1.1062 | 0
| 0 | 0.031873 | 0.36367 | 0
| 7.9071 | 0.048281 | 0.55089 | 0
| 16.2763 | 0.091436 | 1.0433 | 0
| 1.9348 | 0.012579 | 0.14352 | 0
| 0.77308 | 0.0072248 | 0.082435 | 0
| 0.27645 | 0.0095588 | 0.10907 | 0
| 5.5751 | 0.050293 | 0.57384 | 0
| 0.028959 | 0.0029744 | 0.033938 | 0
| 11.9545 | 0.073554 | 0.83925 | 0
| 0.24831 | 0.0019775 | 0.022563 | 0
| 1.2645 | 0.016077 | 0.18344 | 0
| 1.1637 | 0.030323 | 0.34599 | 0
| 0.64149 | 0.0080788 | 0.09218 | 0
| 3.1361 | 0.036197 | 0.41301 | 0
| 33.6263 | 0.18259 | 2.0834 | 0
| 4.7691 | 0.026857 | 0.30643 | 0
| 7.838 | 0.052153 | 0.59507 | 0
| 3.7205 | 0.020634 | 0.23543 | 0
| 4.0987 | 0.022005 | 0.25108 | 0
| 6.8292 | 0.035303 | 0.4028 | 0
| 10.0646 | 0.075817 | 0.86507 | 0
| 1.3615 | 0.032735 | 0.3735 | 0
| 27.68 | 0.22954 | 2.6191 | 0
| 4.1285 | 0.028594 | 0.32626 | 0
| 1.8083 | 0.0118 | 0.13464 | 0
| 5.7399 | 0.045541 | 0.51963 | 0
| 3.5557 | 0.020719 | 0.23641 | 0
| 2.5747 | 0.0155 | 0.17686 | 0
| 5.0824 | 0.057154 | 0.65213 | 0
| 2.3081 | 0.08464 | 0.96574 | 0
| 0.077711 | 0.0030485 | 0.034784 | 0
| 2.8143 | 0.021765 | 0.24834 | 0
| 2.6002 | 0.016873 | 0.19252 | 0
| 1.9707 | 0.040626 | 0.46355 | 0
| 2.2086 | 0.019089 | 0.2178 | 0
| 1.0905 | 0.012563 | 0.14335 | 0
| 0.80371 | 0.0080204 | 0.091513 | 0
| 1.6776 | 0.012179 | 0.13896 | 0
| 8.4702 | 0.043691 | 0.49851 | 0
| 8.5535 | 0.045048 | 0.514 | 0
| 1.1984 | 0.01466 | 0.16727 | 0
| 0.69119 | 0.0061871 | 0.070595 | 0
| 0.73764 | 0.0060348 | 0.068857 | 0
| 21.115 | 0.21885 | 2.4971 | 0
| 0.27008 | 0.042804 | 0.4884 | 0
| 12.8746 | 0.070311 | 0.80224 | 0
| 3.2876 | 0.043144 | 0.49227 | 0
| 11.245 | 0.091146 | 1.04 | 0
| 15.5324 | 0.094011 | 1.0727 | 0
| 0.4512 | 0.0055052 | 0.062814 | 0
| 24.989 | 0.15155 | 1.7292 | 0
| 1.106 | 0.019236 | 0.21948 | 0
| 0.27542 | 0.0057905 | 0.06607 | 0
| 6.9872 | 0.044074 | 0.50289 | 0
| 9.5854 | 0.081253 | 0.9271 | 0
| 11.6694 | 0.064908 | 0.7406 | 0
| 4.7577 | 0.026635 | 0.3039 | 0
| 2.5892 | 0.022591 | 0.25776 | 0
| 10.8624 | 0.089279 | 1.0187 | 0
| 3.2816 | 0.017241 | 0.19672 | 0
| 0.30569 | 0.062329 | 0.71118 | 0
| 16.2687 | 0.094396 | 1.0771 | 0
| 0.37619 | 0.0083884 | 0.095712 | 0
| 7.3543 | 0.062828 | 0.71687 | 0
| 1.1805 | 0.012792 | 0.14596 | 0
| 8.6456 | 0.057602 | 0.65724 | 0
| 0.99431 | 0.021944 | 0.25038 | 0
| 3.3289 | 0.027426 | 0.31293 | 0
| 1.2514 | 0.011967 | 0.13655 | 0
| 8.5462 | 0.071899 | 0.82036 | 0
| 0.70443 | 0.0193 | 0.22022 | 0
| 17.3445 | 0.10095 | 1.1518 | 0
| 2.0232 | 0.0104 | 0.11866 | 0
| 16.6815 | 0.11933 | 1.3616 | 0
| 13.2516 | 0.11245 | 1.283 | 0
| 13.9295 | 0.12432 | 1.4185 | 0
| 1.6859 | 0.013883 | 0.15841 | 0
| 3.6645 | 0.031531 | 0.35977 | 0
| 1.9888 | 0.016212 | 0.18498 | 0
| 0.77688 | 0.015459 | 0.17639 | 0
| 2.0055 | 0.014403 | 0.16433 | 0
| 7.1759 | 0.046539 | 0.53101 | 0
| 4.2351 | 0.034191 | 0.39012 | 0
| 1.1816 | 0.0058389 | 0.066622 | 0
| 0.48363 | 0.010178 | 0.11613 | 0
| 3.608 | 0.024501 | 0.27956 | 0
| 0 | 0.0065871 | 0.075159 | 0
| 1.2128 | 0.077166 | 0.88046 | 0
| 3.4297 | 0.017446 | 0.19906 | 0
| 1.3301 | 0.0098463 | 0.11235 | 0
| 0 | 0.10887 | 1.2422 | 0
| 6.8439 | 0.062511 | 0.71325 | 0
| 0.85741 | 0.012855 | 0.14668 | 0
| 5.8903 | 0.03301 | 0.37664 | 0
| 14.6339 | 0.080783 | 0.92173 | 0
| 10.3278 | 0.054323 | 0.61982 | 0
| 1.2356 | 0.009833 | 0.11219 | 0
| 48.9306 | 0.25832 | 2.9475 | 0
| 7.2042 | 0.076243 | 0.86994 | 0
| 1.0995 | 0.036292 | 0.41409 | 0
| 0.19017 | 0.0012693 | 0.014483 | 0
| 4.1672 | 0.040297 | 0.45979 | 0
| 14.8027 | 0.083476 | 0.95246 | 0
| 12.5081 | 0.066128 | 0.75452 | 0
| 0.92021 | 0.0048986 | 0.055893 | 0
| 1.9632 | 0.060716 | 0.69277 | 0
| 32.3248 | 0.17246 | 1.9678 | 0
| 5.0081 | 0.066002 | 0.75308 | 0
| 0 | 0.0088328 | 0.10078 | 0
| 16.1426 | 0.11113 | 1.268 | 0
| 0.51664 | 0.017959 | 0.20491 | 0
| 0.13033 | 0.010622 | 0.12119 | 0
| 2.7642 | 0.021793 | 0.24866 | 0
| 18.6519 | 0.18801 | 2.1452 | 0
| 0.74281 | 0.0039941 | 0.045572 | 0
| 0.98794 | 0.0074284 | 0.084758 | 0
| 1.1163 | 0.0092985 | 0.1061 | 0
| 22.156 | 0.11939 | 1.3623 | 0
| 7.117 | 0.038173 | 0.43556 | 0
| 8.6988 | 0.048504 | 0.55343 | 0
| 3.9502 | 0.028367 | 0.32367 | 0
| 0.1348 | 0.0050592 | 0.057726 | 0
| 11.7197 | 0.085408 | 0.9745 | 0
| 0.76984 | 0.0074309 | 0.084786 | 0
| 0.055728 | 0.0043478 | 0.049608 | 0
| 13.4765 | 0.10801 | 1.2324 | 0
| 6.8476 | 0.040232 | 0.45905 | 0
| 8.872 | 0.053695 | 0.61266 | 0
| 10.322 | 0.06089 | 0.69476 | 0
| 19.3933 | 0.10126 | 1.1554 | 0
| 1.8096 | 0.012635 | 0.14416 | 0
| 4.8125 | 0.055682 | 0.63533 | 0
| 0.35355 | 0.0108 | 0.12323 | 0
| 2.7251 | 0.021359 | 0.24371 | 0
| 0.81841 | 0.045343 | 0.51736 | 0
| 11.487 | 0.070577 | 0.80528 | 0
| 12.8245 | 0.11398 | 1.3005 | 0
| 1.8635 | 0.014731 | 0.16808 | 0
| 0 | 0.071422 | 0.81493 | 0
| 1.524 | 0.0076944 | 0.087793 | 0
| 5.5183 | 0.030529 | 0.34833 | 0
| 25.9342 | 0.12791 | 1.4595 | 0
| 3.5507 | 0.018784 | 0.21432 | 0
| 4.911 | 0.028733 | 0.32784 | 0
| 0.65358 | 0.014019 | 0.15996 | 0
| 1.87 | 0.067022 | 0.76472 | 0
| 6.5198 | 0.062194 | 0.70963 | 0
| 6.1128 | 0.050169 | 0.57243 | 0
| 0.39325 | 0.0057607 | 0.065729 | 0
| 2.6195 | 0.064298 | 0.73364 | 0
| 0 | 6.4743e-05 | 0.00073872 | 0
| 0.60799 | 0.0022407 | 0.025567 | 0
| 13.4673 | 0.065242 | 0.74441 | 0
| 4.0426 | 0.034724 | 0.3962 | 0
| 7.989 | 0.050823 | 0.57989 | 0
| 1.629 | 0.012485 | 0.14245 | 0
| 0.66136 | 0.011938 | 0.13622 | 0
| 0.073028 | 0.012572 | 0.14344 | 0
| 1.2016 | 0.010882 | 0.12416 | 0
| 0.27146 | 0.0090813 | 0.10362 | 0
| 9.617 | 0.055748 | 0.63609 | 0
| 2.2242 | 0.012065 | 0.13767 | 0
| 1.3728 | 0.0057138 | 0.065194 | 0
| 0.67603 | 0.012179 | 0.13896 | 0
| 25.3127 | 0.11718 | 1.337 | 0
| 0.02272 | 0.0039304 | 0.044846 | 0
| 27.0734 | 0.14955 | 1.7063 | 0
| 1.686 | 0.02757 | 0.31458 | 0
| 0.87319 | 0.011398 | 0.13005 | 0
| 0 | 0.002109 | 0.024063 | 0
| 0.13028 | 0.006616 | 0.075488 | 0
| 4.0204 | 0.039229 | 0.4476 | 0
| 9.2803 | 0.045124 | 0.51487 | 0
| 3.7449 | 0.061075 | 0.69687 | 0
| 1.3698 | 0.023909 | 0.27281 | 0
| 0.58372 | 0.0061621 | 0.07031 | 0
| 7.3769 | 0.038682 | 0.44136 | 0
| 0.10936 | 0.020189 | 0.23035 | 0
| 4.2648 | 0.020721 | 0.23642 | 0
| 0.12061 | 0.0030051 | 0.034289 | 0
| 0.31302 | 0.007128 | 0.081331 | 0
| 22.2399 | 0.19655 | 2.2427 | 0
| 8.7506 | 0.044851 | 0.51175 | 0
| 0.012784 | 0.00012387 | 0.0014133 | 0
| 0.60909 | 0.0032175 | 0.036712 | 0
| 1.8419 | 0.0086375 | 0.098554 | 0
| 10.1897 | 0.074 | 0.84434 | 0
| 7.3421 | 0.053626 | 0.61187 | 0
| 7.634 | 0.063895 | 0.72904 | 0
| 19.9228 | 0.17629 | 2.0115 | 0
| 3.2435 | 0.02557 | 0.29176 | 0
| 0.83975 | 0.0063495 | 0.072448 | 0
| 7.8441 | 0.034595 | 0.39473 | 0
| 10.8804 | 0.048402 | 0.55226 | 0
| 1.8624 | 0.034236 | 0.39063 | 0
| 0 | 0.081456 | 0.92942 | 0
| 6.6468 | 0.073555 | 0.83927 | 0
| 11.4951 | 0.074308 | 0.84786 | 0
| 1.2072 | 0.015752 | 0.17972 | 0
| 1.4598 | 0.016908 | 0.19292 | 0
| 0.15574 | 0.0078492 | 0.089559 | 0
| 4.1606 | 0.03142 | 0.3585 | 0
| 1.8186 | 0.01396 | 0.15928 | 0
| 1.9742 | 0.017745 | 0.20247 | 0
| 0.2262 | 0.0017827 | 0.02034 | 0
| 0.14872 | 0.00071114 | 0.0081141 | 0
| 25.9217 | 0.11159 | 1.2733 | 0
| 5.3615 | 0.028286 | 0.32274 | 0
| 0.48671 | 0.0089521 | 0.10214 | 0
| 0 | 0.0002743 | 0.0031298 | 0
| 0.74529 | 0.03951 | 0.45081 | 0
| 0.18296 | 0.011955 | 0.1364 | 0
| 11.2012 | 0.052952 | 0.60419 | 0
| 0.32207 | 0.0037391 | 0.042663 | 0
| 0.83452 | 0.014596 | 0.16654 | 0
| 0.48734 | 0.0024502 | 0.027957 | 0
| 12.4726 | 0.056737 | 0.64737 | 0
| 2.2748 | 0.021626 | 0.24676 | 0
| 1.1366 | 0.019769 | 0.22557 | 0
| 0.21228 | 0.0045854 | 0.052319 | 0
| 0.34939 | 0.070376 | 0.80299 | 0
| 7.3656 | 0.18535 | 2.1148 | 0
| 9.9779 | 0.053479 | 0.6102 | 0
| 0.10377 | 0.0021709 | 0.02477 | 0
| 30.2676 | 0.21878 | 2.4962 | 0
| 11.5924 | 0.087837 | 1.0022 | 0
| 4.6954 | 0.013766 | 0.15708 | 0
| 1.5385 | 0.010447 | 0.1192 | 0
| 8.5738 | 0.048682 | 0.55546 | 0
| 0 | 0.0078198 | 0.089223 | 0
| 0.69544 | 0.015437 | 0.17614 | 0
| 0.79977 | 0.0097953 | 0.11176 | 0
| 2.909 | 0.023654 | 0.2699 | 0
| 4.7294 | 0.041208 | 0.47018 | 0
| 13.3295 | 0.052773 | 0.60213 | 0
| 2.1435 | 0.015275 | 0.17429 | 0
| 0.36317 | 0.0023921 | 0.027294 | 0
| 3.3606 | 0.05438 | 0.62048 | 0
| 0.77971 | 0.0034752 | 0.039652 | 0
| 3.0922 | 0.019793 | 0.22584 | 0
| 17.3911 | 0.074382 | 0.8487 | 0
| 9.8307 | 0.049875 | 0.56908 | 0
| 0.47648 | 0.0063185 | 0.072094 | 0
| 0.055419 | 0.0062207 | 0.070978 | 0
| 11.8088 | 0.092851 | 1.0594 | 0
| 0.99233 | 0.011298 | 0.12891 | 0
| 0.98653 | 0.0077489 | 0.088414 | 0
| 1.3611 | 0.011712 | 0.13364 | 0
| 3.4645 | 0.031106 | 0.35492 | 0
| 0.73387 | 0.0038397 | 0.043811 | 0
| 7.6693 | 0.042574 | 0.48576 | 0
| 3.3976 | 0.0232 | 0.26471 | 0
| 5.0757 | 0.036432 | 0.41569 | 0
| 0.91823 | 0.013888 | 0.15846 | 0
| 6.4566 | 0.032297 | 0.36851 | 0
| 3.0429 | 0.016359 | 0.18666 | 0
| 1.7397 | 0.020823 | 0.23759 | 0
| 10.325 | 0.045015 | 0.51362 | 0
| 8.5227 | 0.05983 | 0.68266 | 0
| 0.028954 | 0.00010872 | 0.0012405 | 0
| 3.0809 | 0.027857 | 0.31785 | 0
| 3.0897 | 0.016119 | 0.18392 | 0
| 9.2425 | 0.044507 | 0.50782 | 0
| 2.0724 | 0.013791 | 0.15736 | 0
| 2.3469 | 0.0090102 | 0.10281 | 0
| 8.3089 | 0.038137 | 0.43514 | 0
| 2.3374 | 0.017401 | 0.19855 | 0
| 2.8752 | 0.023931 | 0.27306 | 0
| 0.75314 | 0.0027868 | 0.031797 | 0
| 1.7442 | 0.020079 | 0.2291 | 0
| 0 | 0.018741 | 0.21383 | 0
| 1.3066 | 0.010914 | 0.12453 | 0
| 1.8394 | 0.006133 | 0.069978 | 0
| 30.546 | 0.13294 | 1.5168 | 0
| 3.6779 | 0.036275 | 0.4139 | 0
| 5.3139 | 0.048075 | 0.54854 | 0
| 0.88258 | 0.0060729 | 0.069292 | 0
| 0.59007 | 0.0021121 | 0.024099 | 0
| 5.2547 | 0.021375 | 0.24389 | 0
| 0.25268 | 0.010875 | 0.12408 | 0
| 1.5846 | 0.0080745 | 0.09213 | 0
| 0.20473 | 0.00063602 | 0.007257 | 0
| 5.7198 | 0.040885 | 0.4665 | 0
| 3.2777 | 0.015862 | 0.18099 | 0
| 3.7853 | 0.045779 | 0.52234 | 0
| 14.759 | 0.070308 | 0.80221 | 0
| 1.9975 | 0.0076924 | 0.08777 | 0
| 0.81159 | 0.0027325 | 0.031178 | 0
| 8.9257 | 0.084663 | 0.96601 | 0
| 17.5785 | 0.079824 | 0.91079 | 0
| 14.5924 | 0.076482 | 0.87266 | 0
| 4.5315 | 0.035522 | 0.40531 | 0
| 0.58753 | 0.0096666 | 0.1103 | 0
| 0.18324 | 0.0077878 | 0.088858 | 0
| 14.1089 | 0.064838 | 0.7398 | 0
| 1.801 | 0.0078623 | 0.089709 | 0
| 0.37339 | 0.0064981 | 0.074144 | 0
| 2.2056 | 0.033864 | 0.38639 | 0
| 0.16558 | 0.020184 | 0.2303 | 0
| 0.36276 | 0.0015368 | 0.017534 | 0
| 0.78585 | 0.0072481 | 0.082701 | 0
| 4.538 | 0.036019 | 0.41098 | 0
| 0.53198 | 0.0075117 | 0.085709 | 0
| 0.090594 | 0.0039568 | 0.045147 | 0
| 0.70268 | 0.0030762 | 0.035099 | 0
| 3.9637 | 0.038649 | 0.44099 | 0
| 15.6314 | 0.070603 | 0.80558 | 0
| 0.95239 | 0.014966 | 0.17076 | 0
| 33.3704 | 0.13697 | 1.5628 | 0
| 0.17411 | 0.00050528 | 0.0057652 | 0
| 9.7471 | 0.069784 | 0.79624 | 0
| 0.43465 | 0.017854 | 0.20371 | 0
| 2.3588 | 0.014601 | 0.1666 | 0
| 0.35551 | 0.0036869 | 0.042068 | 0
| 2.2646 | 0.0249 | 0.28411 | 0
| 0.69259 | 0.011394 | 0.13001 | 0
| 0 | 0.030857 | 0.35208 | 0
| 0.058295 | 0.0079923 | 0.091192 | 0
| 0 | 0.002063 | 0.023539 | 0
| 2.7886 | 0.020387 | 0.23262 | 0
| 8.139 | 0.050991 | 0.58181 | 0
| 5.4575 | 0.047244 | 0.53905 | 0
| 1.0261 | 0.0044517 | 0.050794 | 0
| 0.97496 | 0.0082049 | 0.093618 | 0
| 0.00079843 | 0.0077956 | 0.088947 | 0
| 0 | 4.3998 | 50.2012 | 0
| 1.5152 | 0.010278 | 0.11727 | 0
| 0.56096 | 0.0026536 | 0.030277 | 0
| 2.668 | 0.010019 | 0.11431 | 0
| 0.12309 | 0.014214 | 0.16219 | 0
| 3.7983 | 0.041361 | 0.47193 | 0
| 0.19379 | 0.0027352 | 0.031209 | 0
| 4.533 | 0.017206 | 0.19632 | 0
| 21.3632 | 0.11459 | 1.3074 | 0
| 0 | 0.0001458 | 0.0016636 | 0
| 7.7633 | 0.073442 | 0.83797 | 0
| 23.3383 | 0.087645 | 1 | 0
| 2.6453 | 0.017476 | 0.1994 | 0
| 1.9939 | 0.032958 | 0.37605 | 0
| 4.9267 | 0.036422 | 0.41557 | 0
| 0 | 0.027328 | 0.31181 | 0
| 0.44822 | 0.016548 | 0.18882 | 0
| 0.34488 | 0.0074986 | 0.085559 | 0
| 0 | 0.015177 | 0.17316 | 0
| 1.9147 | 0.025664 | 0.29283 | 0
| 0.061501 | 0.0024105 | 0.027504 | 0
| 0.28341 | 0.0022926 | 0.026159 | 0
| 25.6659 | 0.17335 | 1.9779 | 0
| 1.0692 | 0.013624 | 0.15546 | 0
| 5.6332 | 0.036101 | 0.41192 | 0
| 0.19888 | 0.0080715 | 0.092096 | 0
| 19.0862 | 0.066464 | 0.75835 | 0
| 0.82873 | 0.0030997 | 0.035367 | 0
| 0.47494 | 0.0081578 | 0.09308 | 0
| 0 | 0.0085982 | 0.098105 | 0
| 2.0398 | 0.0099062 | 0.11303 | 0
| 2.5929 | 0.020189 | 0.23036 | 0
| 31.7043 | 0.10748 | 1.2263 | 0
| 0.46511 | 0.0029116 | 0.033222 | 0
| 1.7083 | 0.027804 | 0.31725 | 0
| 0 | 0.00017044 | 0.0019447 | 0
| 9.002 | 0.027838 | 0.31763 | 0
| 3.4539 | 0.04833 | 0.55145 | 0
| 0.90228 | 0.032676 | 0.37284 | 0
| 0.59155 | 0.010882 | 0.12416 | 0
| 6.9006 | 0.048172 | 0.54965 | 0
| 0.24615 | 0.00027424 | 0.0031291 | 0
| 2.0551 | 0.025836 | 0.29479 | 0
| 5.7988 | 0.048553 | 0.55399 | 0
| 0.26375 | 0.0011845 | 0.013516 | 0
| 0.37047 | 0.0010816 | 0.012342 | 0
| 22.2674 | 0.07217 | 0.82346 | 0
| 1.7664 | 0.058315 | 0.66537 | 0
| 3.2176 | 0.012999 | 0.14832 | 0
| 6.661 | 0.022147 | 0.2527 | 0
| 0.8654 | 0.0028273 | 0.03226 | 0
| 0.73967 | 0.0051255 | 0.058482 | 0
| 0.46963 | 0.0055651 | 0.063498 | 0
| 16.4894 | 0.050672 | 0.57817 | 0
| 1.1813 | 0.014434 | 0.16469 | 0
| 36.1949 | 0.11228 | 1.2811 | 0
| 0.90298 | 0.0046886 | 0.053497 | 0
| 0.35428 | 0.0060662 | 0.069216 | 0
| 0.64548 | 0.0053881 | 0.061478 | 0
| 2.696 | 0.011364 | 0.12966 | 0
| 0.80271 | 0.0066186 | 0.075518 | 0
| 1.0411 | 0.0050525 | 0.057649 | 0
| 5.9046 | 0.033649 | 0.38393 | 0
| 0.1314 | 0.0041338 | 0.047167 | 0
| 0.67032 | 0.015638 | 0.17843 | 0
| 6.2203 | 0.049151 | 0.56081 | 0
| 0 | 0.00014568 | 0.0016622 | 0
| 4.8203 | 0.025108 | 0.28648 | 0
| 1.0554 | 0.004954 | 0.056525 | 0
| 24.9631 | 0.094859 | 1.0823 | 0
| 2.3803 | 0.027892 | 0.31825 | 0
| 25.5693 | 0.081637 | 0.93147 | 0
| 5.903 | 0.054103 | 0.61731 | 0
| 2.7741 | 0.0092714 | 0.10579 | 0
| 0 | 0.0039595 | 0.045178 | 0
| 0.5059 | 0.0096984 | 0.11066 | 0
| 1.8786 | 0.016615 | 0.18958 | 0
| 0.54117 | 0.0086893 | 0.099145 | 0
| 1.8766 | 0.012131 | 0.13841 | 0
| 1.9 | 0.0074265 | 0.084736 | 0
| 0.42429 | 0.0034531 | 0.0394 | 0
| 0.37425 | 0.0096632 | 0.11026 | 0
| 0 | 0.0022633 | 0.025825 | 0
| 1.6434 | 0.007511 | 0.085701 | 0
| 14.3783 | 0.0639 | 0.72909 | 0
| 2.6767 | 0.016489 | 0.18814 | 0
| 4.1465 | 0.022278 | 0.25419 | 0
| 0.45917 | 0.0064493 | 0.073586 | 0
| 12.7462 | 0.073715 | 0.84109 | 0
| 6.4136 | 0.042889 | 0.48937 | 0
| 0.86184 | 0.025273 | 0.28836 | 0
| 0.27567 | 0.0023125 | 0.026386 | 0
| 1.3143 | 0.017222 | 0.1965 | 0
| 8.1095 | 0.032963 | 0.3761 | 0
| 0.52907 | 0.0018253 | 0.020827 | 0
| 1.9177 | 0.012469 | 0.14227 | 0
| 0.21522 | 0.0049634 | 0.056632 | 0
| 1.7364 | 0.013694 | 0.15624 | 0
| 0.37592 | 0.016257 | 0.18549 | 0
| 4.9183 | 0.016038 | 0.183 | 0
| 0 | 0.0093837 | 0.10707 | 0
| 1.8755 | 0.010255 | 0.11701 | 0
| 0.73898 | 0.0098512 | 0.1124 | 0
| 2.2351 | 0.0066948 | 0.076387 | 0
| 0.007725 | 0.0085729 | 0.097817 | 0
| 15.5546 | 0.045784 | 0.5224 | 0
| 0 | 0.00045224 | 0.0051601 | 0
| 0.10144 | 0.007181 | 0.081936 | 0
| 1.1862 | 0.010166 | 0.11599 | 0
| 3.598 | 0.040253 | 0.45928 | 0
| 4.2949 | 0.037701 | 0.43017 | 0
| 2.7997 | 0.019639 | 0.22408 | 0
| 2.5169 | 0.016547 | 0.1888 | 0
| 0.95643 | 0.0056944 | 0.064973 | 0
| 14.581 | 0.044093 | 0.5031 | 0
| 1.7829 | 0.017942 | 0.20471 | 0
| 0.7097 | 0.0093948 | 0.10719 | 0
| 1.767 | 0.028579 | 0.32609 | 0
| 0 | 0.0023129 | 0.02639 | 0
| 8.7931 | 0.048253 | 0.55057 | 0
| 0.61052 | 0.0027575 | 0.031463 | 0
| 3.9045 | 0.018418 | 0.21015 | 0
| 4.251 | 0.039577 | 0.45157 | 0
| 8.9275 | 0.039338 | 0.44885 | 0
| 18.5957 | 0.054857 | 0.62592 | 0
| 0.29747 | 0.0023544 | 0.026864 | 0
| 6.0538 | 0.045744 | 0.52194 | 0
| 10.8269 | 0.052366 | 0.5975 | 0
| 0.52532 | 0.0015134 | 0.017268 | 0
| 0.20056 | 0.0029183 | 0.033298 | 0
| 3.7954 | 0.031391 | 0.35817 | 0
| 0 | 0.0037715 | 0.043033 | 0
| 2.3511 | 0.022393 | 0.25551 | 0
| 1.4099 | 0.015635 | 0.17839 | 0
| 8.4096 | 0.04334 | 0.49451 | 0
| 0 | 0.0042029 | 0.047955 | 0
| 4.0301 | 0.016664 | 0.19013 | 0
| 2.918 | 0.007381 | 0.084217 | 0
| 10.3418 | 0.027675 | 0.31577 | 0
| 0.65641 | 0.0053369 | 0.060895 | 0
| 0.71821 | 0.01206 | 0.13761 | 0
| 1.4138 | 0.0076042 | 0.086764 | 0
| 11.0692 | 0.046251 | 0.52772 | 0
| 1.1988 | 0.030332 | 0.34609 | 0
| 0.15672 | 0.0023961 | 0.02734 | 0
| 0 | 0.007519 | 0.085791 | 0
| 0 | 0.0010923 | 0.012463 | 0
| 1.6705 | 0.027638 | 0.31535 | 0
| 4.0984 | 0.038202 | 0.43589 | 0
| 0.015292 | 0.0057899 | 0.066063 | 0
| 0.33925 | 0.001953 | 0.022283 | 0
| 3.6407 | 0.019018 | 0.21699 | 0
| 0.51935 | 0.0053806 | 0.061392 | 0
| 0.95791 | 0.0036088 | 0.041177 | 0
| 0.84841 | 0.0047421 | 0.054107 | 0
| 0.15662 | 0.001646 | 0.018781 | 0
| 2.8214 | 0.014379 | 0.16406 | 0
| 0.92315 | 0.0093218 | 0.10636 | 0
| 0 | 0.010977 | 0.12524 | 0
| 0.46478 | 0.028704 | 0.32751 | 0
| 0.55787 | 0.0022748 | 0.025955 | 0
| 0.059012 | 0.00071072 | 0.0081093 | 0
| 0.21934 | 0.0038593 | 0.044035 | 0
| 0.55057 | 0.0034781 | 0.039686 | 0
| 2.312 | 0.0089316 | 0.10191 | 0
| 5.9663 | 0.044378 | 0.50636 | 0
| 1.866 | 0.012005 | 0.13698 | 0
| 0.59634 | 0.0017487 | 0.019953 | 0
| 0.27463 | 0.0046755 | 0.053347 | 0
| 3.8305 | 0.02906 | 0.33157 | 0
| 0.025591 | 0.007724 | 0.088131 | 0
| 0.0028409 | 0.0025035 | 0.028565 | 0
| 5.2855 | 0.01436 | 0.16385 | 0
| 0.42587 | 0.016907 | 0.19291 | 0
| 2.1731 | 0.013818 | 0.15767 | 0
| 8.8639 | 0.039208 | 0.44737 | 0
| 16.5629 | 0.069581 | 0.79392 | 0
| 0.0038148 | 0.0033618 | 0.038359 | 0
| 3.6901 | 0.022559 | 0.2574 | 0
| 1.6845 | 0.022109 | 0.25227 | 0
| 2.1799 | 0.025445 | 0.29032 | 0
| 0.17911 | 0.0020394 | 0.023269 | 0
| 0.12626 | 0.011329 | 0.12927 | 0
| 5.5632 | 0.025438 | 0.29024 | 0
| 7.8973 | 0.025279 | 0.28843 | 0
| 0.65941 | 0.0070083 | 0.079965 | 0
| 0.51513 | 0.0037767 | 0.043092 | 0
| 0.63455 | 0.0093487 | 0.10667 | 0
| 13.4671 | 0.069817 | 0.79661 | 0
| 0 | 0.0022648 | 0.025842 | 0
| 12.8859 | 0.051756 | 0.59054 | 0
| 1.5675 | 0.018926 | 0.21595 | 0
| 0.039088 | 0.00026833 | 0.0030617 | 0
| 3.557 | 0.026534 | 0.30275 | 0
| 0 | 0.005533 | 0.063131 | 0
| 1.3617 | 0.018704 | 0.21342 | 0
| 0.20496 | 0.018001 | 0.2054 | 0
| 0 | 0.0062733 | 0.071578 | 0
| 3.983 | 0.03814 | 0.43518 | 0
| 0.14722 | 0.0021724 | 0.024787 | 0
| 0.022511 | 6.638e-05 | 0.00075739 | 0
| 0.33636 | 0.0077236 | 0.088126 | 0
| 0.67599 | 0.0079137 | 0.090295 | 0
| 0.34071 | 0.0042806 | 0.048842 | 0
| 0.23293 | 0.0078162 | 0.089183 | 0
| 6.7258 | 0.015088 | 0.17216 | 0
| 3.5634 | 0.027903 | 0.31837 | 0
| 0.46811 | 0.0050164 | 0.057237 | 0
| 0.68573 | 0.015008 | 0.17124 | 0
| 0.47012 | 0.004934 | 0.056297 | 0
| 0.4365 | 0.0029774 | 0.033972 | 0
| 14.362 | 0.062505 | 0.71319 | 0
| 1.567 | 0.025774 | 0.29408 | 0
| 0.73606 | 0.02292 | 0.26151 | 0
| 0.66655 | 0.008818 | 0.10061 | 0
| 0 | 0.0036337 | 0.041461 | 0
| 0 | 0.0057226 | 0.065295 | 0
| 0 | 0.0026789 | 0.030566 | 0
| 1.0146 | 0.0075804 | 0.086493 | 0
| 4.7021 | 0.044635 | 0.50928 | 0
| 0 | 0.0048545 | 0.05539 | 0
| 1.0224 | 0.002478 | 0.028274 | 0
| 2.4375 | 0.012513 | 0.14278 | 0
| 2.9538 | 0.02696 | 0.30762 | 0
| 0.50721 | 0.0013923 | 0.015886 | 0
| 0 | 0.00014726 | 0.0016803 | 0
| 0.49769 | 0.015903 | 0.18146 | 0
| 0.35911 | 0.0027045 | 0.030858 | 0
| 0 | 0.00012547 | 0.0014316 | 0
| 0.045359 | 0.0048238 | 0.05504 | 0
| 0.30879 | 0.0070656 | 0.080618 | 0
| 1.4295 | 0.0082107 | 0.093684 | 0
| 0.21178 | 0.02318 | 0.26448 | 0
| 1.1266 | 0.013773 | 0.15715 | 0
| 3.2797 | 0.036874 | 0.42073 | 0
| 0 | 0.0023964 | 0.027343 | 0
| 0.94907 | 0.0085464 | 0.097514 | 0
| 0 | 0.0041609 | 0.047476 | 0
| 0.40458 | 0.011807 | 0.13472 | 0
| 8.8644 | 0.057449 | 0.6555 | 0
| 2.2293 | 0.012081 | 0.13784 | 0
| 7.8174 | 0.043586 | 0.49732 | 0
| 0.12469 | 0.0060397 | 0.068913 | 0
| 0.81281 | 0.0067173 | 0.076644 | 0
| 9.4842 | 0.02207 | 0.25182 | 0
| 0.17403 | 0.0022289 | 0.025432 | 0
| 5.146 | 0.018659 | 0.2129 | 0
| 3.8896 | 0.022732 | 0.25937 | 0
| 0.12922 | 0.011668 | 0.13313 | 0
| 0.24716 | 0.0048324 | 0.055138 | 0
| 1.2711 | 0.012517 | 0.14282 | 0
| 17.4973 | 0.063484 | 0.72435 | 0
| 1.5668 | 0.0096339 | 0.10992 | 0
| 0.0077706 | 0.0011287 | 0.012879 | 0
| 3.3222 | 0.02419 | 0.27601 | 0
| 0.1408 | 0.010908 | 0.12446 | 0
| 0.58198 | 0.0054516 | 0.062203 | 0
| 0.094851 | 0.0056489 | 0.064454 | 0
| 0.1182 | 0.006873 | 0.07842 | 0
| 0.24167 | 0.0077215 | 0.088102 | 0
| 1.0808 | 0.012025 | 0.1372 | 0
| 14.687 | 0.070526 | 0.8047 | 0
| 10.8148 | 0.044917 | 0.51251 | 0
| 0.98856 | 0.013267 | 0.15138 | 0
| 0 | 0.0080747 | 0.092132 | 0
| 0.40102 | 0.0047266 | 0.053931 | 0
| 0.067996 | 0.0019155 | 0.021856 | 0
| 0.91038 | 0.012228 | 0.13952 | 0
| 3.391 | 0.037619 | 0.42923 | 0
| 5.2162 | 0.021828 | 0.24906 | 0
| 0.26156 | 0.029337 | 0.33474 | 0
| 2.1651 | 0.021757 | 0.24825 | 0
| 1.5253 | 0.0043514 | 0.04965 | 0
| 1.6803 | 0.025943 | 0.29601 | 0
| 0 | 5.6949e-05 | 0.00064978 | 0
| 0 | 0.0030115 | 0.034361 | 0
| 1.6525 | 0.021415 | 0.24434 | 0
| 2.6342 | 0.028817 | 0.3288 | 0
| 0.82556 | 0.012396 | 0.14144 | 0
| 3.1951 | 0.018038 | 0.20582 | 0
| 1.0608 | 0.011583 | 0.13217 | 0
| 0.42436 | 0.0051927 | 0.059248 | 0
| 0.026667 | 0.0044311 | 0.050559 | 0
| 0.76229 | 0.012571 | 0.14344 | 0
| 1.8898 | 0.011623 | 0.13261 | 0
| 0 | 0.0063129 | 0.072031 | 0
| 11.3145 | 0.033603 | 0.38341 | 0
| 0 | 0.0024501 | 0.027956 | 0
| 0 | 3.7118e-05 | 0.00042352 | 0
| 0.25975 | 0.0039464 | 0.045029 | 0
| 0.57384 | 0.0015543 | 0.017735 | 0
| 0 | 3.6757e-05 | 0.0004194 | 0
| 0.53936 | 0.0059905 | 0.068351 | 0
| 0.23738 | 0.0053814 | 0.061402 | 0
| 9.6946 | 0.032217 | 0.3676 | 0
| 1.6287 | 0.012574 | 0.14347 | 0
| 0.20271 | 0.0041391 | 0.047227 | 0
| 5.2566 | 0.029318 | 0.33452 | 0
| 0.052245 | 0.0046967 | 0.053589 | 0
| 0.72455 | 0.0043069 | 0.049141 | 0
| 11.306 | 0.083962 | 0.958 | 0
| 0.79374 | 0.0062401 | 0.071199 | 0
| 4.0305 | 0.02107 | 0.24041 | 0
| 0 | 0.0075675 | 0.086345 | 0
| 0.060322 | 0.0014561 | 0.016614 | 0
| 2.9637 | 0.011483 | 0.13102 | 0
| 0 | 0.0029501 | 0.033661 | 0
| 0.2564 | 0.0082454 | 0.09408 | 0
| 1.0225 | 0.0063331 | 0.072261 | 0
| 2.8668 | 0.016504 | 0.18831 | 0
| 1.1186 | 0.023416 | 0.26717 | 0
| 0 | 0.0012651 | 0.014435 | 0
| 0.91761 | 0.0092545 | 0.10559 | 0
| 0.9619 | 0.0066307 | 0.075657 | 0
| 0.079266 | 0.0016812 | 0.019183 | 0
| 7.3582 | 0.040515 | 0.46228 | 0
| 0 | 0.0028775 | 0.032832 | 0
| 1.9876 | 0.023465 | 0.26774 | 0
| 19.6333 | 0.066789 | 0.76206 | 0
| 3.669 | 0.024104 | 0.27503 | 0
| 0 | 0.00010347 | 0.0011806 | 0
| 11.4002 | 0.044588 | 0.50875 | 0
| 3.2912 | 0.049055 | 0.55972 | 0
| 4.8617 | 0.026157 | 0.29846 | 0
| 0 | 4.2458e-05 | 0.00048444 | 0
| 0 | 5.0934e-05 | 0.00058116 | 0
| 0.03003 | 0.0046175 | 0.052685 | 0
| 1.1496 | 0.0038052 | 0.043418 | 0
| 0 | 5.0567e-05 | 0.00057697 | 0
| 0.028173 | 0.006191 | 0.07064 | 0
| 0.26858 | 0.0059113 | 0.067448 | 0
| 1.3234 | 0.0067193 | 0.076667 | 0
| 0.7437 | 0.0053943 | 0.061549 | 0
| 1.4129 | 0.0065085 | 0.074262 | 0
| 0.47579 | 0.0090855 | 0.10367 | 0
| 0 | 0.0032584 | 0.037179 | 0
| 1.2922 | 0.0077932 | 0.08892 | 0
| 0.56398 | 0.0056448 | 0.064407 | 0
| 0 | 0.0009461 | 0.010795 | 0
| 1.6476 | 0.0071212 | 0.081253 | 0
| 2.3783 | 0.015961 | 0.18211 | 0
| 0.049113 | 0.0071309 | 0.081363 | 0
| 0.32034 | 0.0054314 | 0.061972 | 0
| 1.3059 | 0.015662 | 0.1787 | 0
| 0 | 4.9169e-05 | 0.00056102 | 0
| 2.4566 | 0.0079737 | 0.09098 | 0
| 1.0761 | 0.0048397 | 0.055221 | 0
| 0 | 0.0046368 | 0.052906 | 0
| 0.23477 | 0.0054033 | 0.061652 | 0
| 0.34248 | 0.0030751 | 0.035087 | 0
| 0 | 0.0004386 | 0.0050045 | 0
| 1.1814 | 0.0070793 | 0.080775 | 0
| 0 | 0.0095933 | 0.10946 | 0
| 0.72622 | 0.0062392 | 0.07119 | 0
| 3.137 | 0.027106 | 0.30928 | 0
| 0 | 0.0022256 | 0.025395 | 0
| 0.92867 | 0.019779 | 0.22567 | 0
| 4.3448 | 0.010085 | 0.11507 | 0
| 0 | 0.0040049 | 0.045696 | 0
| 0.052133 | 0.0027779 | 0.031695 | 0
| 0 | 0.0010395 | 0.01186 | 0
| 5.1183 | 0.015114 | 0.17245 | 0
| 7.1059 | 0.015992 | 0.18246 | 0
| 0 | 0.0015663 | 0.017871 | 0
| 2.0874 | 0.0092915 | 0.10602 | 0
| 1.0154 | 0.0023448 | 0.026754 | 0
| 0.14739 | 0.0086935 | 0.099193 | 0
| 0.018498 | 0.004221 | 0.048162 | 0
| 3.3389 | 0.027336 | 0.3119 | 0
| 0 | 0.000703 | 0.0080212 | 0
| 0 | 0.00018293 | 0.0020872 | 0
| 12.121 | 0.041555 | 0.47414 | 0
| 0 | 4.5559e-05 | 0.00051983 | 0
| 0.14357 | 0.010149 | 0.1158 | 0
| 0 | 0.0011374 | 0.012977 | 0
| 0.32941 | 0.0044383 | 0.050641 | 0
| 1.5219 | 0.0042113 | 0.048051 | 0
| 2.1614 | 0.015633 | 0.17837 | 0
| 0 | 2.2584e-05 | 0.00025768 | 0
| 0 | 0.0004053 | 0.0046245 | 0
| 0 | 0.002115 | 0.024132 | 0
| 0.49829 | 0.0039137 | 0.044655 | 0
| 0 | 5.9939e-05 | 0.00068391 | 0
| 0.79557 | 0.014474 | 0.16515 | 0
| 10.2586 | 0.032997 | 0.37649 | 0
| 0.34068 | 0.035228 | 0.40195 | 0
| 0 | 0.00026618 | 0.0030371 | 0
| 0.31015 | 0.0090496 | 0.10326 | 0
| 0 | 0.001047 | 0.011947 | 0
| 0 | 4.3963e-05 | 0.00050162 | 0
| 0 | 7.3141e-05 | 0.00083454 | 0
| 0.49338 | 0.005752 | 0.06563 | 0
| 0 | 0.00030548 | 0.0034855 | 0
| 0 | 5.0894e-05 | 0.0005807 | 0
| 0 | 0.00010177 | 0.0011612 | 0
| 0.068243 | 0.010463 | 0.11938 | 0
| 0 | 0.0015692 | 0.017905 | 0
| 0 | 0.0070702 | 0.080671 | 0
| 4.7133 | 0.044599 | 0.50887 | 0
| 0.35006 | 0.012402 | 0.1415 | 0
| 0 | 5.7918e-05 | 0.00066084 | 0
| 0.057981 | 0.00099725 | 0.011379 | 0
| 0 | 0.0011544 | 0.013172 | 0
| 0.91022 | 0.015384 | 0.17553 | 0
| 0 | 2.8818e-05 | 0.00032881 | 0
| 0 | 0.0057824 | 0.065978 | 0
| 0.098947 | 0.00034428 | 0.0039282 | 0
| 0 | 0.00060205 | 0.0068694 | 0
| 0 | 0.0042945 | 0.049 | 0
| 0 | 4.2884e-05 | 0.00048931 | 0
| 0 | 0.0011804 | 0.013468 | 0
| 0.13489 | 0.0074101 | 0.084549 | 0
| 1.9028 | 0.014084 | 0.1607 | 0
| 0.15445 | 0.015884 | 0.18124 | 0
| 0 | 0.00034025 | 0.0038823 | 0
| 0 | 6.8859e-05 | 0.00078568 | 0
| 0.90331 | 0.0010484 | 0.011962 | 0
| 0 | 0.00012749 | 0.0014547 | 0
| 0 | 0.0010194 | 0.011631 | 0
| 0.64611 | 0.0084497 | 0.096411 | 0
| 0 | 0.001694 | 0.019328 | 0
| 0.63078 | 0.0059281 | 0.06764 | 0
| 0 | 0.0015187 | 0.017329 | 0
| 0.10274 | 0.0010966 | 0.012512 | 0
| 0.27708 | 0.011781 | 0.13443 | 0
| 4.1034 | 0.0055587 | 0.063424 | 0
| 0 | 0.0039082 | 0.044593 | 0
| 0 | 0.00033585 | 0.003832 | 0
| 0 | 0.0064248 | 0.073307 | 0
| 0 | 0.006963 | 0.079448 | 0
| 1.0533 | 0.0047281 | 0.053948 | 0
| 0 | 0.00099715 | 0.011377 | 0
| 0 | 2.765e-05 | 0.00031548 | 0
| 0 | 0.0036809 | 0.041999 | 0
| 0.35401 | 0.0054582 | 0.062278 | 0
| 0 | 4.1298e-05 | 0.00047121 | 0
| 0 | 0.00052277 | 0.0059648 | 0
| 1.0365 | 0.0095596 | 0.10908 | 0
| 8.5863 | 0.047251 | 0.53914 | 0
| 0.4523 | 0.0016811 | 0.019182 | 0
| 0 | 0.00034139 | 0.0038953 | 0
| 0 | 0.0024148 | 0.027553 | 0
| 4.4754 | 0.024512 | 0.27969 | 0
| 0 | 4.0892e-05 | 0.00046658 | 0
| 0 | 0.00024494 | 0.0027947 | 0
| 0 | 0.0012201 | 0.013921 | 0
| 0.031963 | 0.0042474 | 0.048463 | 0
| 0 | 0.0076813 | 0.087643 | 0
| 0.17126 | 0.0049895 | 0.05693 | 0
| 0 | 0.011533 | 0.13159 | 0
| 0.59196 | 0.0045797 | 0.052255 | 0
| 0 | 0.00015527 | 0.0017717 | 0
| 0.68625 | 0.027856 | 0.31784 | 0
| 0 | 0.008122 | 0.092672 | 0
| 0 | 0.0040979 | 0.046757 | 0
| 0 | 0.00056429 | 0.0064386 | 0
| 3.0548 | 0.014263 | 0.16274 | 0
| 0 | 4.0277e-05 | 0.00045956 | 0
| 0 | 0.0010873 | 0.012406 | 0
| 3.82 | 0.022014 | 0.25118 | 0
| 0 | 0.00010692 | 0.0012199 | 0
| 2.7736 | 0.0055717 | 0.063573 | 0
| 0 | 0.0056561 | 0.064537 | 0
| 0 | 0.0033599 | 0.038336 | 0
| 0.96992 | 0.0040757 | 0.046504 | 0
| 0 | 0.00085236 | 0.0097254 | 0
| 0 | 0.00036868 | 0.0042066 | 0
| 0 | 4.2583e-05 | 0.00048588 | 0
| 0.54758 | 0.0091244 | 0.10411 | 0
| 0 | 0.0027627 | 0.031523 | 0
| 0 | 0.001035 | 0.01181 | 0
| 0 | 3.9793e-05 | 0.00045404 | 0
| 2.1193 | 0.014897 | 0.16997 | 0
| 0 | 0.00062102 | 0.0070859 | 0
| 0 | 0.0009863 | 0.011254 | 0
| 0 | 0.0010511 | 0.011993 | 0
| 0 | 0.0034974 | 0.039906 | 0
| 0 | 0.007334 | 0.083681 | 0
| 0 | 0.00074437 | 0.0084933 | 0
| 0 | 0.0034038 | 0.038837 | 0
| 0 | 0.00010426 | 0.0011896 | 0
| 0 | 0.0026841 | 0.030626 | 0
| 0.61932 | 0.0034781 | 0.039685 | 0
| 0 | 0.00076822 | 0.0087654 | 0
| 1.443 | 0.0081045 | 0.092472 | 0
| 0.39693 | 0.0020886 | 0.023831 | 0
| 0 | 0.0031414 | 0.035844 | 0
| 0 | 0.00052949 | 0.0060415 | 0
| 0 | 0.0024165 | 0.027572 | 0
| 0.90839 | 0.004948 | 0.056457 | 0
| 0 | 0.00020584 | 0.0023487 | 0
| 0 | 0.0013245 | 0.015113 | 0
| 0 | 0.00067871 | 0.0077441 | 0
| 0 | 0.00049839 | 0.0056866 | 0
| 7.1758 | 0.03027 | 0.34538 | 0
| 0.047569 | 1.9144e-05 | 0.00021843 | 0
| 0.98882 | 0.0083749 | 0.095558 | 0
| 0 | 0.00056024 | 0.0063923 | 0
| 0.028065 | 0.0083614 | 0.095404 | 0
| 0 | 0.0001905 | 0.0021736 | 0
| 0.38902 | 0.023237 | 0.26514 | 0
| 0 | 0.001572 | 0.017936 | 0
| 0 | 0.00089985 | 0.010267 | 0
| 0.88984 | 0.0057752 | 0.065895 | 0
| 0 | 0.0026466 | 0.030197 | 0
| 1.0221 | 0.012101 | 0.13808 | 0
| 0 | 1.8941e-05 | 0.00021611 | 0
| 0 | 2.5253e-05 | 0.00028814 | 0
| 0 | 0.00066867 | 0.0076295 | 0
| 0 | 0.0003531 | 0.0040288 | 0
| 0 | 1.8789e-05 | 0.00021438 | 0
| 0 | 0.00099579 | 0.011362 | 0
| 0.032408 | 0.00063881 | 0.0072888 | 0
| 0.34951 | 0.0019021 | 0.021702 | 0
| 0 | 1.4997e-05 | 0.00017111 | 0
| 0 | 3.7474e-05 | 0.00042758 | 0
| 0 | 3.7473e-05 | 0.00042756 | 0
| 0.015789 | 0.00016235 | 0.0018525 | 0
| 0.29431 | 0.003068 | 0.035006 | 0
| 0.20701 | 0.00063549 | 0.0072509 | 0
| 0 | 7.4666e-05 | 0.00085193 | 0
| 0 | 0.0017155 | 0.019573 | 0
| 0 | 0.00018633 | 0.002126 | 0
| 2.7823 | 0.0056235 | 0.064164 | 0
| 0 | 0.0030032 | 0.034266 | 0
| 0 | 3.7224e-05 | 0.00042473 | 0
| 0 | 0.0021623 | 0.024672 | 0
| 0 | 4.9496e-05 | 0.00056475 | 0
| 0 | 0.00024724 | 0.002821 | 0
| 0 | 9.8805e-05 | 0.0011274 | 0
| 0 | 7.4091e-05 | 0.00084537 | 0
| 0 | 0.00051815 | 0.0059121 | 0
| 0.0053059 | 0.0024301 | 0.027727 | 0
| 0.84656 | 0.0075807 | 0.086495 | 0
| 0.038174 | 3.696e-05 | 0.00042172 | 0
| 0 | 0.0098138 | 0.11198 | 0
| 0 | 3.6847e-05 | 0.00042042 | 0
| 0 | 9.8186e-05 | 0.0011203 | 0
| 0 | 7.3563e-05 | 0.00083935 | 0
| 0 | 0.0018006 | 0.020545 | 0
| 0 | 0.0011085 | 0.012648 | 0
| 0 | 0.0024372 | 0.027809 | 0
| 0 | 0.0002568 | 0.00293 | 0
| 0 | 0.00037905 | 0.004325 | 0
| 0.47515 | 0.0046857 | 0.053463 | 0
| 0 | 3.6586e-05 | 0.00041745 | 0
| 0.24782 | 0.0080315 | 0.09164 | 0
| 0 | 0.00068049 | 0.0077644 | 0
| 0.63159 | 0.0055775 | 0.063639 | 0
| 0 | 0.0030066 | 0.034306 | 0
| 0 | 0.00087868 | 0.010026 | 0
| 0 | 0.0012948 | 0.014773 | 0
| 2.9214 | 0.0082036 | 0.093603 | 0
| 0 | 0.001006 | 0.011479 | 0
| 0 | 0.000253 | 0.0028868 | 0
| 0 | 0.00026434 | 0.0030161 | 0
| 0 | 0.007924 | 0.090412 | 0
| 0.24984 | 0.0090323 | 0.10306 | 0
| 0 | 0.0055756 | 0.063618 | 0
| 0 | 0.00068797 | 0.0078497 | 0
| 0 | 7.1885e-05 | 0.00082021 | 0
| 0.047229 | 0.0037719 | 0.043038 | 0
| 0 | 2.3932e-05 | 0.00027306 | 0
| 0.65824 | 0.0081189 | 0.092637 | 0
| 0.81718 | 0.012346 | 0.14087 | 0
| 0 | 3.5746e-05 | 0.00040786 | 0
| 0.17919 | 0.0040263 | 0.04594 | 0
| 0 | 0.00050007 | 0.0057058 | 0
| 8.4169 | 0.016269 | 0.18563 | 0
| 0 | 0.003245 | 0.037026 | 0
| 0 | 0.00092632 | 0.010569 | 0
| 0 | 0.00026121 | 0.0029804 | 0
| 0.70196 | 0.0040839 | 0.046598 | 0
| 0 | 0.0056165 | 0.064084 | 0
| 0 | 0.0023631 | 0.026962 | 0
| 0 | 0.0017497 | 0.019964 | 0
| 0 | 0.00067579 | 0.0077107 | 0
| 0 | 1.7766e-05 | 0.00020271 | 0
| 2.0198 | 0.0075297 | 0.085914 | 0
| 0 | 0.0014201 | 0.016204 | 0
| 0 | 0.003998 | 0.045617 | 0
| 0 | 9.4592e-05 | 0.0010793 | 0
| 0 | 0.0052727 | 0.060161 | 0
| 0.0056485 | 0.00046073 | 0.0052569 | 0
| 0 | 0.00024767 | 0.0028259 | 0
| 0 | 0.00023564 | 0.0026887 | 0
| 0 | 0.0011518 | 0.013142 | 0
| 0.092284 | 2.3495e-05 | 0.00026807 | 0
| 0 | 0.00313 | 0.035713 | 0
| 0 | 0.00014067 | 0.0016051 | 0
| 0 | 0.00031633 | 0.0036093 | 0
| 0 | 2.3408e-05 | 0.00026708 | 0
| 0 | 2.3394e-05 | 0.00026693 | 0
| 0.0019007 | 0.0045917 | 0.052391 | 0
| 0 | 0.00054899 | 0.006264 | 0
| 0 | 0.00027965 | 0.0031908 | 0
| 0 | 0.00020966 | 0.0023922 | 0
| 0 | 0.0017143 | 0.01956 | 0
| 0 | 0.0015252 | 0.017403 | 0
| 0.18657 | 9.3108e-05 | 0.0010624 | 0
| 0 | 0.0032083 | 0.036607 | 0
| 0 | 0.00024406 | 0.0027847 | 0
| 0.00068285 | 0.0020986 | 0.023945 | 0
| 0 | 0.0019588 | 0.02235 | 0
| 0 | 3.4746e-05 | 0.00039645 | 0
| 0 | 0.0013091 | 0.014937 | 0
| 0 | 0.0018029 | 0.020571 | 0
| 0 | 0.00065874 | 0.0075162 | 0
| 1.5314 | 0.0089431 | 0.10204 | 0
| 0.51636 | 0.0099774 | 0.11384 | 0
| 0 | 0.0020665 | 0.023579 | 0
| 0 | 0.00087703 | 0.010007 | 0
| 0 | 3.4619e-05 | 0.000395 | 0
| 0 | 0.00099222 | 0.011321 | 0
| 0 | 0.0043442 | 0.049568 | 0
| 0 | 0.0087795 | 0.10017 | 0
| 0.031087 | 0.011481 | 0.131 | 0
| 3.5485 | 0.024127 | 0.27529 | 0
| 0 | 3.4495e-05 | 0.00039359 | 0
| 0 | 0.0026882 | 0.030673 | 0
| 0 | 3.443e-05 | 0.00039285 | 0
| 0 | 0.00010323 | 0.0011778 | 0
| 2.0558 | 0.0098628 | 0.11253 | 0
| 0 | 0.0039241 | 0.044774 | 0
| 0 | 0.0012004 | 0.013697 | 0
| 0 | 0.0018513 | 0.021123 | 0
| 0 | 0.00074183 | 0.0084642 | 0
| 0 | 0.00021664 | 0.0024719 | 0
| 0 | 0.0088811 | 0.10133 | 0
| 0 | 0.0046052 | 0.052546 | 0
| 0 | 0.0018337 | 0.020923 | 0
| 0.5024 | 0.0016957 | 0.019348 | 0
| 0 | 0.0018887 | 0.02155 | 0
| 0 | 0.0046364 | 0.052901 | 0
| 0.38691 | 0.016801 | 0.19169 | 0
| 0.076182 | 0.0018376 | 0.020967 | 0
| 0 | 0.005206 | 0.059401 | 0
| 0 | 0.001733 | 0.019773 | 0
| 0 | 0.00039612 | 0.0045198 | 0
| 0 | 6.7855e-05 | 0.00077422 | 0
| 0 | 0.0002713 | 0.0030955 | 0
| 0 | 0.0046566 | 0.053132 | 0
| 0 | 0.007643 | 0.087207 | 0
| 3.215 | 0.023007 | 0.26251 | 0
| 0 | 0.0017589 | 0.020069 | 0
| 0 | 0.00016909 | 0.0019293 | 0
| 0 | 0.0002592 | 0.0029575 | 0
| 0 | 0.0029916 | 0.034134 | 0
| 0 | 0.00068661 | 0.0078342 | 0
| 0 | 3.3759e-05 | 0.00038519 | 0
| 0 | 0.00084287 | 0.0096171 | 0
| 0 | 0.0013652 | 0.015577 | 0
| 0.5191 | 0.0024557 | 0.028019 | 0
| 0 | 2.2421e-05 | 0.00025582 | 0
| 0.78822 | 0.0020066 | 0.022896 | 0
| 0 | 0.0024476 | 0.027928 | 0
| 0 | 0.00094068 | 0.010733 | 0
| 0 | 0.00032699 | 0.003731 | 0
| 0 | 0.0046488 | 0.053043 | 0
| 0.016758 | 0.00097239 | 0.011095 | 0
| 0 | 0.00016758 | 0.0019121 | 0
| 0 | 0.00053493 | 0.0061035 | 0
| 0 | 0.00052912 | 0.0060373 | 0
| 0 | 0.00026716 | 0.0030483 | 0
| 2.3743 | 0.017494 | 0.19961 | 0
| 0.22955 | 0.0048049 | 0.054824 | 0
| 0 | 0.00032204 | 0.0036745 | 0
| 0 | 0.00074379 | 0.0084867 | 0
| 0 | 0.0047831 | 0.054575 | 0
| 0 | 0.0028499 | 0.032517 | 0
| 0 | 3.3267e-05 | 0.00037957 | 0
| 0 | 0.00077865 | 0.0088844 | 0
| 0 | 0.0018646 | 0.021275 | 0
| 0 | 0.00081812 | 0.0093348 | 0
| 0.067379 | 0.013634 | 0.15557 | 0
| 0 | 0.00016533 | 0.0018864 | 0
| 0 | 0.0043881 | 0.050068 | 0
| 0 | 0.00019807 | 0.00226 | 0
| 0 | 0.0021787 | 0.024859 | 0
| 0 | 0.0016833 | 0.019207 | 0
| 0.36294 | 0.0028055 | 0.032011 | 0
| 0.51334 | 0.0048168 | 0.054959 | 0
| 0 | 0.0017742 | 0.020243 | 0
| 0 | 0.0053046 | 0.060526 | 0
| 0 | 0.0072843 | 0.083114 | 0
| 0.10021 | 0.00055867 | 0.0063744 | 0
| 0 | 0.00032859 | 0.0037492 | 0
| 0 | 3.2847e-05 | 0.00037478 | 0
| 0 | 3.2811e-05 | 0.00037437 | 0
| 0 | 3.2796e-05 | 0.0003742 | 0
| 0 | 0.0009181 | 0.010476 | 0
| 0 | 0.0016063 | 0.018327 | 0
| 0 | 0.0014255 | 0.016265 | 0
| 0 | 0.00026198 | 0.0029891 | 0
| 0 | 0.00091616 | 0.010453 | 0
| 0 | 0.0014451 | 0.016489 | 0
| 0 | 0.0020919 | 0.023869 | 0
| 0 | 0.00023967 | 0.0027346 | 0
| 0 | 3.268e-05 | 0.00037288 | 0
| 0 | 6.532e-05 | 0.0007453 | 0
| 0 | 0.00025032 | 0.0028562 | 0
| 0 | 0.0016652 | 0.019 | 0
| 0.34773 | 0.0021544 | 0.024581 | 0
| 0 | 0.0022503 | 0.025676 | 0
| 0.90936 | 0.0086375 | 0.098554 | 0
| 0 | 0.0037802 | 0.043132 | 0
| 0 | 0.00077108 | 0.008798 | 0
| 0 | 0.001151 | 0.013133 | 0
| 0 | 0.0042281 | 0.048243 | 0
| 0 | 0.0014679 | 0.016749 | 0
| 0.090717 | 0.0047327 | 0.054 | 0
| 0.25036 | 0.0031391 | 0.035817 | 0
| 0 | 0.00068169 | 0.0077781 | 0
| 0 | 0.0063009 | 0.071893 | 0
| 0 | 0.00058401 | 0.0066635 | 0
| 0 | 3.2389e-05 | 0.00036956 | 0
| 0.11572 | 0.0048079 | 0.054859 | 0
| 0 | 0.0037877 | 0.043217 | 0
| 0 | 0.0060319 | 0.068824 | 0
| 0 | 0.002697 | 0.030773 | 0
| 0 | 0.0052366 | 0.05975 | 0
| 0.030745 | 0.0068775 | 0.078472 | 0
| 0 | 0.0016159 | 0.018437 | 0
| 0 | 0.0018528 | 0.021141 | 0
| 0 | 0.0077135 | 0.088012 | 0
| 0 | 1.0762e-05 | 0.0001228 | 0
| 0 | 0.0019471 | 0.022216 | 0
| 0 | 0.0036242 | 0.041352 | 0
| 0 | 0.0018649 | 0.021278 | 0
| 0 | 0.00028998 | 0.0033086 | 0
| 0 | 0.00091236 | 0.01041 | 0
| 0 | 0.0024459 | 0.027908 | 0
| 2.1525 | 0.0027882 | 0.031813 | 0
| 0 | 0.0010509 | 0.011991 | 0
| 0 | 0.0042969 | 0.049028 | 0
| 0 | 0.00079274 | 0.0090452 | 0
| 0 | 0.0011767 | 0.013426 | 0
| 0 | 0.0035178 | 0.040138 | 0
| 0 | 0.0037809 | 0.04314 | 0
| 0 | 0.0024367 | 0.027802 | 0
| 0.14133 | 0.022966 | 0.26204 | 0
| 0 | 0.00016013 | 0.0018271 | 0
| 0 | 0.00012794 | 0.0014598 | 0
| 0 | 0.0022705 | 0.025906 | 0
| 0 | 6.3835e-05 | 0.00072835 | 0
| 0 | 0.0018085 | 0.020635 | 0
| 2.3002 | 0.0083878 | 0.095705 | 0
| 0 | 9.5674e-05 | 0.0010916 | 0
| 0 | 0.00010098 | 0.0011522 | 0
| 0 | 0.0005421 | 0.0061854 | 0
| 0 | 0.0033143 | 0.037816 | 0
| 0 | 0.0015636 | 0.017841 | 0
| 0 | 0.00012742 | 0.0014539 | 0
| 0 | 0.00086934 | 0.0099192 | 0
| 0 | 9.532e-05 | 0.0010876 | 0
| 0 | 0.0044455 | 0.050723 | 0
| 0 | 0.0033757 | 0.038517 | 0
| 0 | 3.1745e-05 | 0.00036221 | 0
| 0 | 0.0036712 | 0.041888 | 0
| 0 | 0.00079329 | 0.0090514 | 0
| 0 | 0.00019032 | 0.0021715 | 0
| 0 | 0.0010462 | 0.011937 | 0
| 0 | 0.0030241 | 0.034505 | 0
| 0 | 0.0023347 | 0.026639 | 0
| 0 | 0.00092953 | 0.010606 | 0
| 0 | 0.00034856 | 0.0039771 | 0
| 0 | 0.0036336 | 0.041459 | 0
| 0 | 0.00035879 | 0.0040938 | 0
| 1.1944 | 0.0077737 | 0.088697 | 0
| 0 | 0.0028452 | 0.032464 | 0
| 0 | 3.1613e-05 | 0.00036071 | 0
| 0 | 0.0015693 | 0.017906 | 0
| 0.028155 | 0.0015055 | 0.017178 | 0
| 0 | 0.0042306 | 0.048271 | 0
| 0 | 1.5785e-05 | 0.00018011 | 0
| 0 | 0.0072368 | 0.082572 | 0
| 0 | 0.0001156 | 0.001319 | 0
| 0 | 5.2543e-05 | 0.00059952 | 0
| 0 | 0.00097711 | 0.011149 | 0
| 0 | 0.0031927 | 0.036428 | 0
| 0 | 9.446e-05 | 0.0010778 | 0
| 0 | 0.003544 | 0.040437 | 0
| 0 | 0.00012582 | 0.0014356 | 0
| 0 | 0.007472 | 0.085255 | 0
| 0 | 3.1416e-05 | 0.00035845 | 0
| 0 | 0.0010362 | 0.011823 | 0
| 0 | 0.0004082 | 0.0046576 | 0
| 0 | 0.0024801 | 0.028298 | 0
| 0.1698 | 0.0078886 | 0.090009 | 0
| 0 | 0.0036865 | 0.042062 | 0
| 0 | 0.00094815 | 0.010818 | 0
| 0 | 0.00083555 | 0.0095336 | 0
| 0 | 0.007049 | 0.08043 | 0
| 0 | 0.00079614 | 0.009084 | 0
| 0 | 0.0011289 | 0.01288 | 0
| 0.083051 | 3.6387e-05 | 0.00041518 | 0
| 0 | 0.0017751 | 0.020254 | 0
| 0 | 0.0042146 | 0.048089 | 0
| 0 | 6.2253e-05 | 0.0007103 | 0
| 0 | 0.0025099 | 0.028638 | 0
| 0 | 0.0022853 | 0.026076 | 0
| 0 | 0.0014189 | 0.01619 | 0
| 0 | 0.0025451 | 0.02904 | 0
| 0 | 0.0039986 | 0.045624 | 0
| 0 | 6.205e-05 | 0.00070799 | 0
| 0 | 0.0045495 | 0.051909 | 0
| 0 | 0.00066132 | 0.0075457 | 0
| 0 | 5.1662e-05 | 0.00058947 | 0
| 0 | 0.0023298 | 0.026583 | 0
| 0 | 0.0039692 | 0.045288 | 0
| 0 | 0.0028787 | 0.032846 | 0
| 0 | 1.5475e-05 | 0.00017658 | 0
| 0 | 6.1826e-05 | 0.00070543 | 0
| 0 | 0.0034454 | 0.039313 | 0
| 0 | 0.0012974 | 0.014803 | 0
| 1.1838 | 0.015839 | 0.18073 | 0
| 0 | 0.0032305 | 0.03686 | 0
| 0 | 0.001255 | 0.014319 | 0
| 0 | 0.00035492 | 0.0040496 | 0
| 0 | 0.00061695 | 0.0070394 | 0
| 0 | 0.0050726 | 0.057879 | 0
| 0.020045 | 0.0069688 | 0.079514 | 0
| 0 | 0.0018498 | 0.021106 | 0
| 0 | 0.0015053 | 0.017176 | 0
| 0 | 0.006142 | 0.07008 | 0
| 0 | 0.0027449 | 0.031319 | 0
| 0 | 0.00061563 | 0.0070243 | 0
| 0 | 0.0022462 | 0.025629 | 0
| 0 | 4.1022e-05 | 0.00046806 | 0
| 0.51018 | 0.0036274 | 0.041389 | 0
| 0 | 3.0741e-05 | 0.00035075 | 0
| 0 | 0.0016599 | 0.018939 | 0
| 0.040126 | 0.0024482 | 0.027934 | 0
| 0 | 0.00036046 | 0.0041129 | 0
| 0 | 0.0059266 | 0.067623 | 0
| 7.4319 | 0.0074503 | 0.085008 | 0
| 0 | 0.00020433 | 0.0023314 | 0
| 0 | 1.5315e-05 | 0.00017475 | 0
| 0 | 0.0066007 | 0.075314 | 0
| 0 | 3.5719e-05 | 0.00040756 | 0
| 3.6365 | 0.0089324 | 0.10192 | 0
| 1.4198 | 0.014956 | 0.17065 | 0
| 0 | 0.0041724 | 0.047607 | 0
| 0.39537 | 0.0054706 | 0.062419 | 0
| 0 | 0.0017113 | 0.019525 | 0
| 0 | 0.0006722 | 0.0076697 | 0
| 0 | 0.00094674 | 0.010802 | 0
| 0 | 6.1028e-05 | 0.00069632 | 0
| 0 | 1.2201e-05 | 0.00013921 | 0
| 0 | 1.2201e-05 | 0.00013921 | 0
| 0 | 0.0013316 | 0.015194 | 0
| 0 | 0.0012502 | 0.014265 | 0
| 0 | 0.0022232 | 0.025366 | 0
| 0 | 0.0050447 | 0.05756 | 0
| 0 | 0.00011155 | 0.0012728 | 0
| 0 | 0.0014894 | 0.016994 | 0
| 0 | 0.0004153 | 0.0047386 | 0
| 0 | 0.0020509 | 0.023401 | 0
| 0 | 0.0020494 | 0.023383 | 0
| 0.4644 | 0.0067089 | 0.076549 | 0
| 0 | 0.00063731 | 0.0072717 | 0
| 0 | 0.0040761 | 0.046508 | 0
| 0 | 0.0026141 | 0.029827 | 0
| 0 | 0.001805 | 0.020595 | 0
| 0 | 3.031e-05 | 0.00034584 | 0
| 0 | 3.031e-05 | 0.00034583 | 0
| 0 | 0.00038389 | 0.0043802 | 0
| 0 | 0.0024549 | 0.02801 | 0
| 0 | 3.0294e-05 | 0.00034566 | 0
| 0 | 0.00063086 | 0.0071981 | 0
| 0 | 0.001029 | 0.01174 | 0
| 0 | 0.0017848 | 0.020365 | 0
| 0 | 0.0032369 | 0.036933 | 0
| 0 | 2.0167e-05 | 0.0002301 | 0
| 0 | 3.0238e-05 | 0.00034502 | 0
| 0 | 0.00041014 | 0.0046797 | 0
| 0 | 2.0154e-05 | 0.00022996 | 0
| 0 | 0.0032343 | 0.036903 | 0
| 0 | 3.5261e-05 | 0.00040233 | 0
| 0 | 0.0025279 | 0.028843 | 0
| 0 | 0.0015099 | 0.017228 | 0
| 0.17125 | 0.0014793 | 0.016879 | 0
| 0 | 0.0016151 | 0.018428 | 0
| 0 | 0.0028575 | 0.032604 | 0
| 0 | 0.0011671 | 0.013316 | 0
| 0 | 0.0010206 | 0.011645 | 0
| 0 | 3.0151e-05 | 0.00034402 | 0
| 0 | 0.0007033 | 0.0080246 | 0
| 0 | 0.0042443 | 0.048428 | 0
| 0 | 9.0275e-05 | 0.00103 | 0
| 0.051927 | 0.0041518 | 0.047372 | 0
| 0 | 0.0002607 | 0.0029746 | 0
| 0 | 2.0052e-05 | 0.00022879 | 0
| 0 | 0.00044114 | 0.0050334 | 0
| 0 | 0.0011626 | 0.013265 | 0
| 0 | 6.0124e-05 | 0.00068601 | 0
| 0 | 0.0047951 | 0.054713 | 0
| 0 | 0.0044768 | 0.05108 | 0
| 0 | 0.00094067 | 0.010733 | 0
| 0 | 0.00045026 | 0.0051375 | 0
| 0 | 0.0020669 | 0.023583 | 0
| 0 | 0.0047993 | 0.05476 | 0
| 0 | 0.00053974 | 0.0061584 | 0
| 0 | 0.0011789 | 0.013451 | 0
| 0 | 0.0014754 | 0.016835 | 0
| 0 | 0.00031451 | 0.0035885 | 0
| 0 | 0.01202 | 0.13715 | 0
| 0 | 0.0015373 | 0.01754 | 0
| 0 | 0.00014971 | 0.0017082 | 0
| 0 | 0.0039736 | 0.045338 | 0
| 0.019876 | 0.0034616 | 0.039497 | 0
| 0 | 0.0020841 | 0.02378 | 0
| 0 | 8.9681e-05 | 0.0010233 | 0
| 0.059208 | 0.0023414 | 0.026715 | 0
| 0.031341 | 0.0013151 | 0.015005 | 0
| 0.55224 | 0.0018228 | 0.020798 | 0
| 0 | 0.0012763 | 0.014562 | 0
| 0 | 0.0022696 | 0.025896 | 0
| 0 | 1.9899e-05 | 0.00022705 | 0
| 0 | 0.0017907 | 0.020432 | 0
| 0 | 0.0011638 | 0.013279 | 0
| 0 | 0.0022078 | 0.025191 | 0
| 0 | 0.00098927 | 0.011288 | 0
| 0 | 0.00050667 | 0.0057811 | 0
| 0 | 0.00064562 | 0.0073666 | 0
| 0 | 0.001132 | 0.012916 | 0
| 0 | 0.001658 | 0.018918 | 0
| 0 | 0.0055476 | 0.063298 | 0
| 0 | 0.0019294 | 0.022015 | 0
| 0 | 0.00089216 | 0.01018 | 0
| 0 | 0.00044588 | 0.0050875 | 0
| 0 | 0.0014657 | 0.016724 | 0
| 0 | 0.00091598 | 0.010451 | 0
| 0 | 0.00041572 | 0.0047434 | 0
| 2.753 | 0.020143 | 0.22984 | 0
| 0 | 0.0023143 | 0.026406 | 0
| 0 | 0.00065267 | 0.007447 | 0
| 0 | 0.00017793 | 0.0020302 | 0
| 0 | 0.00093383 | 0.010655 | 0
| 0 | 0.0011561 | 0.013191 | 0
| 0 | 0.0010375 | 0.011838 | 0
| 0 | 0.0007059 | 0.0080543 | 0
| 0 | 0.00075004 | 0.008558 | 0
| 0 | 0.0018823 | 0.021477 | 0
| 0 | 8.8693e-05 | 0.001012 | 0
| 0 | 0.00022665 | 0.002586 | 0
| 0 | 0.0045958 | 0.052438 | 0
| 0 | 0.0058341 | 0.066567 | 0
| 0 | 0.0017409 | 0.019864 | 0
| 0 | 0.0012093 | 0.013799 | 0
| 0 | 0.00027525 | 0.0031406 | 0
| 0 | 7.37e-05 | 0.00084091 | 0
| 0.014002 | 0.00062375 | 0.0071169 | 0
| 0 | 0.00064795 | 0.0073931 | 0
| 0.063145 | 0.0015362 | 0.017528 | 0
| 0 | 0.0014916 | 0.017019 | 0
| 0 | 0.0040468 | 0.046174 | 0
| 1.9621 | 0.016771 | 0.19136 | 0
| 0 | 0.00010784 | 0.0012304 | 0
| 0 | 0.0022836 | 0.026056 | 0
| 0 | 1.96e-05 | 0.00022364 | 0
| 0 | 0.0038405 | 0.04382 | 0
| 0 | 0.0041427 | 0.047268 | 0
| 0 | 0.0013417 | 0.015309 | 0
| 0 | 0.0025723 | 0.02935 | 0
| 0 | 0.0016632 | 0.018977 | 0
| 0 | 0.0015646 | 0.017852 | 0
| 0.5494 | 0.005543 | 0.063245 | 0
| 0.032027 | 0.0011134 | 0.012704 | 0
| 0 | 0.0021298 | 0.024301 | 0
| 0 | 0.00064357 | 0.0073432 | 0
| 0 | 0.00044853 | 0.0051177 | 0
| 0.062172 | 0.0026904 | 0.030697 | 0
| 0 | 0.0010033 | 0.011448 | 0
| 0 | 2.9216e-05 | 0.00033336 | 0
| 0 | 0.00063787 | 0.0072781 | 0
| 0 | 0.0012964 | 0.014792 | 0
| 0 | 0.0051658 | 0.058942 | 0
| 0 | 0.0020816 | 0.023751 | 0
| 0 | 0.00040849 | 0.0046609 | 0
| 1.5689 | 0.015552 | 0.17744 | 0
| 0 | 0.00080681 | 0.0092058 | 0
| 0 | 2.9157e-05 | 0.00033269 | 0
| 0 | 0.0036139 | 0.041234 | 0
| 0.39984 | 0.0044579 | 0.050864 | 0
| 0 | 0.0053498 | 0.061041 | 0
| 0.074086 | 0.0008738 | 0.00997 | 0
| 0.13862 | 0.0013974 | 0.015944 | 0
| 0 | 0.007932 | 0.090504 | 0
| 0 | 0.00064023 | 0.007305 | 0
| 0 | 0.0010766 | 0.012284 | 0
| 0 | 0.0016653 | 0.019001 | 0
| 0 | 0.0068487 | 0.078143 | 0
| 0 | 0.00036806 | 0.0041995 | 0
| 0 | 0.00069734 | 0.0079567 | 0
| 0 | 0.00013067 | 0.0014909 | 0
| 0 | 0.00077405 | 0.0088319 | 0
| 0 | 0.0011028 | 0.012583 | 0
| 0 | 0.00098661 | 0.011257 | 0
| 0 | 0.00066726 | 0.0076134 | 0
| 0 | 0.0040415 | 0.046113 | 0
| 0 | 0.0028906 | 0.032981 | 0
| 0 | 0.0021717 | 0.02478 | 0
| 0 | 0.00072485 | 0.0082705 | 0
| 0 | 0.00075313 | 0.0085933 | 0
| 0.046244 | 0.001071 | 0.01222 | 0
| 0 | 0.00054025 | 0.0061643 | 0
| 0 | 0.0022332 | 0.02548 | 0
| 0 | 0.0036944 | 0.042153 | 0
| 0 | 0.002872 | 0.03277 | 0
| 0 | 0.00028907 | 0.0032983 | 0
| 0 | 0.00051999 | 0.0059331 | 0
| 0.008958 | 0.0018869 | 0.021529 | 0
| 0 | 0.0021081 | 0.024054 | 0
| 0 | 3.8482e-05 | 0.00043908 | 0
| 0.73365 | 0.00092344 | 0.010536 | 0
| 0.30974 | 0.0046824 | 0.053426 | 0
| 0 | 0.0069077 | 0.078816 | 0
| 0 | 2.8823e-05 | 0.00032887 | 0
| 0.93706 | 0.0090665 | 0.10345 | 0
| 0 | 0.00086417 | 0.0098602 | 0
| 0 | 0.00043205 | 0.0049297 | 0
| 0 | 0.00065274 | 0.0074477 | 0
| 0 | 0.001987 | 0.022671 | 0
| 0 | 0.0011326 | 0.012923 | 0
| 0 | 0.00028786 | 0.0032845 | 0
| 0 | 0.0040924 | 0.046695 | 0
| 0 | 0.0018409 | 0.021004 | 0
| 0 | 0.0018611 | 0.021235 | 0
| 0 | 0.00065143 | 0.0074328 | 0
| 0 | 0.0037072 | 0.042299 | 0
| 0 | 0.0021262 | 0.02426 | 0
| 0 | 0.00091795 | 0.010474 | 0
| 0 | 0.0012333 | 0.014072 | 0
| 0 | 0.00030575 | 0.0034886 | 0
| 0 | 0.0070412 | 0.08034 | 0
| 0 | 0.00080246 | 0.0091561 | 0
| 0 | 2.8657e-05 | 0.00032698 | 0
| 0 | 0.0039895 | 0.045521 | 0
| 0 | 0.0012981 | 0.014811 | 0
| 0 | 0.0017627 | 0.020113 | 0
| 0 | 0.0052487 | 0.059887 | 0
| 0 | 0.00042934 | 0.0048988 | 0
| 0 | 0.002413 | 0.027533 | 0
| 0 | 9.5339e-05 | 0.0010878 | 0
| 0 | 0.0015058 | 0.017181 | 0
| 0 | 0.00084781 | 0.0096735 | 0
| 0 | 0.0031911 | 0.036411 | 0
| 0.1191 | 0.0035334 | 0.040316 | 0
| 0 | 0.0021705 | 0.024765 | 0
| 0 | 0.0013898 | 0.015857 | 0
| 0 | 0.00013325 | 0.0015204 | 0
| 0 | 0.00087527 | 0.0099868 | 0
| 0 | 0.00029476 | 0.0033632 | 0
| 0 | 0.0032606 | 0.037203 | 0
| 0 | 0.00085536 | 0.0097597 | 0
| 0 | 0.0018671 | 0.021304 | 0
| 0 | 0.0003658 | 0.0041738 | 0
| 0 | 0.0011861 | 0.013533 | 0
| 0 | 0.0012998 | 0.014831 | 0
| 0 | 0.00093878 | 0.010711 | 0
| 0 | 0.00093869 | 0.010711 | 0
| 0 | 2.8444e-05 | 0.00032454 | 0
| 1.0149 | 0.01388 | 0.15838 | 0
| 0 | 0.0031279 | 0.035689 | 0
| 0 | 0.00015159 | 0.0017297 | 0
| 0 | 0.0012679 | 0.014467 | 0
| 0 | 0.0010703 | 0.012213 | 0
| 0 | 0.0012493 | 0.014254 | 0
| 0 | 0.0013241 | 0.015108 | 0
| 0 | 0.00076847 | 0.0087682 | 0
| 0 | 0.00042535 | 0.0048533 | 0
| 0 | 0.0017486 | 0.019952 | 0
| 0.098051 | 0.0019185 | 0.02189 | 0
| 0 | 2.8349e-05 | 0.00032346 | 0
| 0 | 0.00038738 | 0.00442 | 0
| 0 | 0.0014919 | 0.017023 | 0
| 0 | 4.7197e-05 | 0.00053851 | 0
| 0 | 1.8875e-05 | 0.00021536 | 0
| 0 | 0.00020762 | 0.0023689 | 0
| 0 | 1.8872e-05 | 0.00021533 | 0
| 0 | 0.0003113 | 0.003552 | 0
| 0 | 0.00099965 | 0.011406 | 0
| 0 | 0.00065026 | 0.0074194 | 0
| 0 | 0.00027315 | 0.0031166 | 0
| 0.12958 | 0.0081545 | 0.093043 | 0
| 0 | 0.00084924 | 0.0096898 | 0
| 2.5483 | 0.020015 | 0.22837 | 0
| 0 | 0.002962 | 0.033797 | 0
| 0 | 0.0030227 | 0.03449 | 0
| 0 | 0.0020966 | 0.023923 | 0
| 0 | 0.00078452 | 0.0089514 | 0
| 0 | 0.00080325 | 0.0091651 | 0
| 0 | 0.00044151 | 0.0050377 | 0
| 0 | 0.00019726 | 0.0022508 | 0
| 0 | 0.0020562 | 0.023461 | 0
| 0 | 0.00084457 | 0.0096366 | 0
| 0 | 0.00019678 | 0.0022453 | 0
| 0 | 0.0006465 | 0.0073765 | 0
| 0 | 0.0029038 | 0.033132 | 0
| 0 | 0.00030026 | 0.003426 | 0
| 0 | 0.0021536 | 0.024572 | 0
| 0 | 0.0029183 | 0.033298 | 0
| 0 | 0.0042135 | 0.048076 | 0
| 0 | 0.002745 | 0.03132 | 0
| 10.4692 | 0.031046 | 0.35423 | 0
| 0 | 0.0021867 | 0.02495 | 0
| 0 | 0.0048487 | 0.055323 | 0
| 0 | 0.0035779 | 0.040823 | 0
| 0 | 0.002653 | 0.03027 | 0
| 0 | 0.0030997 | 0.035368 | 0
| 0 | 1.8673e-05 | 0.00021306 | 0
| 0 | 0.0010661 | 0.012164 | 0
| 0 | 0.00018668 | 0.00213 | 0
| 0 | 0.00063648 | 0.0072622 | 0
| 0 | 0.0002704 | 0.0030853 | 0
| 0 | 0.00048484 | 0.005532 | 0
| 0 | 8.3847e-05 | 0.00095669 | 0
| 0 | 0.0036236 | 0.041345 | 0
| 0 | 0.0012482 | 0.014242 | 0
| 0 | 0.0034557 | 0.03943 | 0
| 0 | 0.0019372 | 0.022104 | 0
| 0 | 0.0017693 | 0.020188 | 0
| 0 | 0.0041625 | 0.047494 | 0
| 0 | 0.00024211 | 0.0027625 | 0
| 0 | 0.0025878 | 0.029527 | 0
| 0 | 0.00094943 | 0.010833 | 0
| 0 | 0.010713 | 0.12223 | 0
| 0 | 0.00013959 | 0.0015927 | 0
| 0 | 0.00069767 | 0.0079604 | 0
| 0 | 0.0011996 | 0.013688 | 0
| 0.14347 | 0.0019712 | 0.022491 | 0
| 0 | 0.0017013 | 0.019412 | 0
| 0 | 1.8593e-05 | 0.00021214 | 0
| 0 | 0.016967 | 0.19359 | 0
| 0 | 0.0024772 | 0.028265 | 0
| 0 | 0.0024493 | 0.027946 | 0
| 0 | 0.0003802 | 0.004338 | 0
| 0 | 0.00079737 | 0.009098 | 0
| 0 | 0.0095399 | 0.10885 | 0
| 0.82033 | 0.0062297 | 0.071081 | 0
| 0 | 0.0015709 | 0.017924 | 0
| 0 | 0.0021236 | 0.02423 | 0
| 0.23509 | 0.0043349 | 0.049461 | 0
| 0 | 6.481e-05 | 0.00073949 | 0
| 0 | 0.0010457 | 0.011932 | 0
| 0 | 0.0009622 | 0.010979 | 0
| 0 | 0.00063835 | 0.0072836 | 0
| 0 | 0.0093185 | 0.10632 | 0
| 0 | 0.00058719 | 0.0066998 | 0
| 0 | 0.0050949 | 0.058133 | 0
| 0 | 0.0041598 | 0.047463 | 0
| 0 | 0.0017026 | 0.019427 | 0
| 0 | 0.0016911 | 0.019296 | 0
| 0 | 1.3861e-05 | 0.00015815 | 0
| 0 | 0.0044307 | 0.050554 | 0
| 0 | 0.0044298 | 0.050544 | 0
| 0 | 0.0067393 | 0.076895 | 0
| 0 | 9.2255e-06 | 0.00010526 | 0
| 0 | 0.0029051 | 0.033147 | 0
| 0 | 0.0044379 | 0.050636 | 0
| 0 | 0.00066399 | 0.0075761 | 0
| 0 | 0.0016478 | 0.018801 | 0
| 0 | 0.0032999 | 0.037652 | 0
| 0 | 0.0053968 | 0.061577 | 0
| 0 | 5.2523e-05 | 0.00059929 | 0
| 0 | 0.0016374 | 0.018683 | 0
| 0 | 2.7643e-05 | 0.0003154 | 0
| 0 | 0.00037776 | 0.0043102 | 0
| 0 | 0.00058035 | 0.0066218 | 0
| 0 | 0.0044155 | 0.050381 | 0
| 0 | 0.00095729 | 0.010923 | 0
| 0 | 0.0019323 | 0.022048 | 0
| 0 | 0.0025396 | 0.028976 | 0
| 0 | 0.0020115 | 0.022952 | 0
| 0 | 0.0020894 | 0.02384 | 0
| 0 | 0.0012396 | 0.014144 | 0
| 0 | 0.022639 | 0.25832 | 0
| 0 | 0.00060587 | 0.006913 | 0
| 0 | 0.0010784 | 0.012304 | 0
| 0 | 0.0045237 | 0.051615 | 0
| 0 | 0.005817 | 0.066372 | 0
| 0 | 0.0016967 | 0.01936 | 0
| 0 | 0.0001926 | 0.0021975 | 0
| 0 | 0.00074282 | 0.0084756 | 0
| 0 | 0.003519 | 0.040152 | 0
| 0 | 0.0028398 | 0.032402 | 0
| 0 | 0.0033253 | 0.037942 | 0
| 0 | 0.0002565 | 0.0029266 | 0
| 0 | 0.00048549 | 0.0055394 | 0
| 0 | 0.0032793 | 0.037416 | 0
| 0 | 0.00016483 | 0.0018808 | 0
| 0 | 0.0019797 | 0.022589 | 0
| 0 | 0.0032049 | 0.036568 | 0
| 0 | 0.0035251 | 0.040222 | 0
| 0 | 0.0092871 | 0.10597 | 0
| 0 | 0.0002837 | 0.003237 | 0
| 0 | 7.3201e-05 | 0.00083523 | 0
| 0 | 0.00027419 | 0.0031285 | 0
| 0 | 0.00027414 | 0.003128 | 0
| 0 | 0.0039107 | 0.044622 | 0
| 0 | 0.0094473 | 0.10779 | 0
| 0.22652 | 0.0016989 | 0.019384 | 0
| 0 | 0.00026488 | 0.0030222 | 0
| 0 | 0.0027949 | 0.031889 | 0
| 0 | 0.0044255 | 0.050495 | 0
| 0 | 0.0040435 | 0.046136 | 0
| 0 | 0.0015196 | 0.017339 | 0
| 0 | 5.4748e-05 | 0.00062468 | 0
| 0.12383 | 0.004123 | 0.047043 | 0
| 0 | 0.0015278 | 0.017433 | 0
| 0.21293 | 0.0039586 | 0.045167 | 0
| 0 | 0.0011765 | 0.013423 | 0
| 0 | 0.014154 | 0.16149 | 0
| 0 | 0.0026348 | 0.030063 | 0
| 0 | 0.00061969 | 0.0070706 | 0
| 0 | 0.0049294 | 0.056245 | 0
| 0 | 0.00013662 | 0.0015589 | 0
| 0 | 0.00016389 | 0.0018699 | 0
| 0 | 7.7381e-05 | 0.00088292 | 0
| 0 | 0.0012197 | 0.013917 | 0
| 0 | 0.010331 | 0.11787 | 0
| 0 | 0.004183 | 0.047728 | 0
| 0 | 0.00050964 | 0.005815 | 0
| 0 | 0.00171 | 0.019511 | 0
| 0 | 8.1832e-05 | 0.0009337 | 0
| 0 | 0.00059101 | 0.0067434 | 0
| 0 | 0.0025094 | 0.028632 | 0
| 0 | 0.00035367 | 0.0040354 | 0
| 0 | 0.0029099 | 0.033202 | 0
| 0 | 0.0015909 | 0.018152 | 0
| 0.06612 | 0.00040767 | 0.0046515 | 0
| 0 | 2.7177e-05 | 0.00031009 | 0
| 0 | 0.00031706 | 0.0036176 | 0
| 0 | 0.0021187 | 0.024175 | 0
| 0 | 0.0062548 | 0.071367 | 0
| 0 | 0.0038551 | 0.043987 | 0
| 0 | 0.0014474 | 0.016514 | 0
| 0 | 4.07e-05 | 0.00046439 | 0
| 0 | 4.07e-05 | 0.00046439 | 0
| 0 | 0.0034184 | 0.039004 | 0
| 0.18038 | 0.0095741 | 0.10924 | 0
| 0 | 0.0042036 | 0.047963 | 0
| 0 | 0.0009989 | 0.011397 | 0
| 0 | 0.0044589 | 0.050876 | 0
| 0 | 0.0044912 | 0.051245 | 0
| 0 | 0.0022765 | 0.025975 | 0
| 0 | 0.00090332 | 0.010307 | 0
| 0 | 0.0020579 | 0.023481 | 0
| 0 | 0.0065298 | 0.074505 | 0
| 0 | 0.0038915 | 0.044402 | 0
| 0 | 0.0010196 | 0.011633 | 0
| 0 | 0.026659 | 0.30418 | 0
| 0 | 0.0018642 | 0.021271 | 0
| 0 | 0.0018121 | 0.020677 | 0
| 0 | 0.00029743 | 0.0033937 | 0
| 0 | 0.0037296 | 0.042554 | 0
| 0 | 0.00036934 | 0.0042142 | 0
| 0 | 2.7023e-05 | 0.00030833 | 0
| 0 | 0.0025666 | 0.029285 | 0
| 0 | 0.0024926 | 0.02844 | 0
| 0 | 9.897e-05 | 0.0011292 | 0
| 0 | 0.0011335 | 0.012933 | 0
| 0 | 0.0004785 | 0.0054597 | 0
| 0 | 0.0070328 | 0.080244 | 0
| 0 | 0.0044571 | 0.050855 | 0
| 0 | 0.0022628 | 0.025819 | 0
| 0 | 0.0021841 | 0.024921 | 0
| 0 | 2.6957e-05 | 0.00030758 | 0
| 0 | 0.0015095 | 0.017224 | 0
| 0 | 0.004514 | 0.051504 | 0
| 0 | 0.0038429 | 0.043847 | 0
| 0 | 0.0011223 | 0.012805 | 0
| 0 | 7.1821e-05 | 0.00081948 | 0
| 1.4768 | 0.0091002 | 0.10383 | 0
| 0 | 0.0054645 | 0.06235 | 0
| 0 | 0.00046645 | 0.0053222 | 0
| 3.0497 | 0.01951 | 0.22261 | 0
| 0 | 0.0012722 | 0.014516 | 0
| 0 | 0.0033307 | 0.038003 | 0
| 0 | 0.0052281 | 0.059653 | 0
| 0 | 0.00064901 | 0.0074051 | 0
| 0 | 0.00025952 | 0.0029611 | 0
| 0 | 0.0016102 | 0.018372 | 0
| 0 | 0.0020379 | 0.023252 | 0
| 0 | 0.0021178 | 0.024164 | 0
| 0 | 0.00072374 | 0.0082579 | 0
| 0 | 0.0045255 | 0.051636 | 0
| 0.13922 | 0.001918 | 0.021884 | 0
| 0 | 0.00045486 | 0.0051899 | 0
| 0 | 0.0021403 | 0.024421 | 0
| 0 | 0.0020663 | 0.023576 | 0
| 0 | 0.0017902 | 0.020426 | 0
| 0 | 0.003446 | 0.039319 | 0
| 0 | 0.00081872 | 0.0093416 | 0
| 0 | 0.0052937 | 0.060401 | 0
| 0 | 0.0024819 | 0.028319 | 0
| 0 | 0.0017968 | 0.020502 | 0
| 0 | 0.0021763 | 0.024832 | 0
| 0 | 0.0014935 | 0.017041 | 0
| 0 | 3.1113e-05 | 0.000355 | 0
| 0 | 0.0022483 | 0.025654 | 0
| 0 | 0.0010039 | 0.011455 | 0
| 0 | 0.00029314 | 0.0033448 | 0
| 0 | 0.0022413 | 0.025573 | 0
| 0 | 0.00043032 | 0.00491 | 0
| 0 | 0.0039655 | 0.045246 | 0
| 0 | 0.00082679 | 0.0094337 | 0
| 0 | 0.0020618 | 0.023525 | 0
| 0 | 0.001543 | 0.017605 | 0
| 0 | 0.0015288 | 0.017443 | 0
| 0 | 0.0022642 | 0.025835 | 0
| 0 | 0.0005405 | 0.0061671 | 0
| 0 | 0.0017587 | 0.020067 | 0
| 0 | 0.0010096 | 0.011519 | 0
| 0 | 0.00034535 | 0.0039404 | 0
| 0 | 0.00039845 | 0.0045463 | 0
| 0 | 0.0012129 | 0.013839 | 0
| 0 | 0.00025663 | 0.0029282 | 0
| 0.33708 | 0.0011149 | 0.012721 | 0
| 0 | 0.0026278 | 0.029983 | 0
| 0 | 0.0012298 | 0.014032 | 0
| 0 | 0.00019021 | 0.0021703 | 0
| 0 | 3.5381e-05 | 0.0004037 | 0
| 0 | 0.0014328 | 0.016349 | 0
| 0 | 0.0024755 | 0.028246 | 0
| 0 | 0.0056715 | 0.064712 | 0
| 0 | 0.00074702 | 0.0085235 | 0
| 0.096994 | 0.0070271 | 0.08018 | 0
| 0 | 0.00031813 | 0.0036299 | 0
| 0 | 0.0039942 | 0.045574 | 0
| 0 | 0.0016698 | 0.019053 | 0
| 0 | 0.00052999 | 0.0060471 | 0
| 0 | 0.00068886 | 0.0078599 | 0
| 0 | 0.00030904 | 0.0035262 | 0
| 0.52322 | 0.007307 | 0.083373 | 0
| 0.18216 | 0.0061989 | 0.07073 | 0
| 0 | 7.9401e-05 | 0.00090596 | 0
| 1.091 | 0.0064843 | 0.073986 | 0
| 0 | 0.0013012 | 0.014847 | 0
| 0 | 1.058e-05 | 0.00012072 | 0
| 0 | 0.0018774 | 0.021421 | 0
| 0 | 0.00078324 | 0.0089367 | 0
| 0 | 0.001938 | 0.022112 | 0
| 0 | 0.001506 | 0.017184 | 0
| 5.3312 | 0.02074 | 0.23665 | 0
| 0 | 0.0028181 | 0.032154 | 0
| 0 | 0.0051957 | 0.059283 | 0
| 0 | 0.0027294 | 0.031143 | 0
| 0 | 0.0018651 | 0.021281 | 0
| 0 | 0.0011583 | 0.013216 | 0
| 0 | 0.0012497 | 0.014259 | 0
| 0 | 0.0026663 | 0.030423 | 0
| 0 | 0.0013463 | 0.015362 | 0
| 0 | 0.002672 | 0.030487 | 0
| 0 | 0.0037635 | 0.042942 | 0
| 0 | 0.00081746 | 0.0093272 | 0
| 0 | 0.0038175 | 0.043558 | 0
| 0 | 0.0016607 | 0.018948 | 0
| 0 | 0.00092862 | 0.010596 | 0
| 0 | 0.0025736 | 0.029365 | 0
| 0 | 0.003399 | 0.038783 | 0
| 0 | 0.0071437 | 0.08151 | 0
| 0 | 0.00013597 | 0.0015514 | 0
| 0 | 0.0020601 | 0.023506 | 0
| 0 | 0.0018492 | 0.021099 | 0
| 0 | 0.0012529 | 0.014296 | 0
| 0 | 4.3798e-05 | 0.00049974 | 0
| 0 | 0.0048821 | 0.055704 | 0
| 0 | 0.0043746 | 0.049915 | 0
| 0 | 0.0043314 | 0.049421 | 0
| 0 | 1.7499e-05 | 0.00019966 | 0
| 0 | 0.0061232 | 0.069866 | 0
| 0 | 2.6228e-05 | 0.00029926 | 0
| 2.1058 | 0.014443 | 0.1648 | 0
| 0 | 0.00081203 | 0.0092652 | 0
| 0 | 0.005963 | 0.068038 | 0
| 0 | 0.0012743 | 0.014539 | 0
| 20.5427 | 0.085307 | 0.97335 | 0
| 0 | 0.0083659 | 0.095454 | 0
| 0 | 0.00062742 | 0.0071589 | 0
| 0 | 0.0022345 | 0.025496 | 0
| 0 | 0.003667 | 0.04184 | 0
| 0 | 0.00096655 | 0.011028 | 0
| 0 | 0.00091414 | 0.01043 | 0
| 0 | 0.00057195 | 0.006526 | 0
| 0 | 0.00041782 | 0.0047674 | 0
| 0 | 0.0030988 | 0.035358 | 0
| 0 | 0.0041073 | 0.046864 | 0
| 0 | 0.00045249 | 0.0051629 | 0
| 0 | 5.2207e-05 | 0.00059568 | 0
| 0 | 0.0022709 | 0.025911 | 0
| 0.57373 | 0.0071736 | 0.081851 | 0
| 0 | 2.6084e-05 | 0.00029762 | 0
| 0 | 0.00044338 | 0.005059 | 0
| 0 | 0.0043077 | 0.04915 | 0
| 0 | 0.00013037 | 0.0014876 | 0
| 0 | 1.7383e-05 | 0.00019834 | 0
| 0 | 0.0016339 | 0.018643 | 0
| 0.43266 | 0.0060742 | 0.069307 | 0
| 0 | 0.00077325 | 0.0088227 | 0
| 0 | 0.00078189 | 0.0089213 | 0
| 0 | 0.00023456 | 0.0026763 | 0
| 0 | 0.0044584 | 0.050871 | 0
| 0 | 0.00083365 | 0.0095119 | 0
| 0 | 0.00087699 | 0.010007 | 0
| 0 | 0.0016929 | 0.019316 | 0
| 0.11841 | 0.0030124 | 0.034371 | 0
| 0 | 0.00065709 | 0.0074974 | 0
| 0 | 0.0033114 | 0.037783 | 0
| 0.65955 | 0.0031498 | 0.035939 | 0
| 0 | 5.2045e-05 | 0.00059383 | 0
| 0.030661 | 0.0045513 | 0.051931 | 0
| 0 | 0.0031382 | 0.035807 | 0
| 0 | 0.0052876 | 0.060332 | 0
| 0.14519 | 0.00067596 | 0.0077127 | 0
| 0 | 0.003015 | 0.034401 | 0
| 0 | 0.0080118 | 0.091414 | 0
| 0 | 0.0018015 | 0.020556 | 0
| 0 | 0.0021435 | 0.024457 | 0
| 0 | 0.0012119 | 0.013828 | 0
| 0 | 1.7312e-05 | 0.00019753 | 0
| 2.0802 | 0.015054 | 0.17176 | 0
| 0 | 0.00054482 | 0.0062164 | 0
| 0 | 0.0032082 | 0.036606 | 0
| 0 | 0.0010419 | 0.011888 | 0
| 0 | 0.0091127 | 0.10398 | 0
| 0 | 0.00061805 | 0.007052 | 0
| 0 | 0.0014781 | 0.016865 | 0
| 0 | 0.0013958 | 0.015926 | 0
| 0 | 2.5927e-05 | 0.00029582 | 0
| 0 | 0.00069996 | 0.0079865 | 0
| 0 | 7.7754e-05 | 0.00088718 | 0
| 0.0027521 | 2.5918e-05 | 0.00029572 | 0
| 0 | 0.00068553 | 0.0078219 | 0
| 0 | 0.0010875 | 0.012409 | 0
| 0 | 0.0045916 | 0.052391 | 0
| 0 | 0.00041427 | 0.0047268 | 0
| 0 | 0.003452 | 0.039388 | 0
| 0 | 0.0022352 | 0.025503 | 0
| 0 | 0.0034251 | 0.039081 | 0
| 0 | 0.00053469 | 0.0061008 | 0
| 0 | 0.0039488 | 0.045056 | 0
| 0 | 0.0013967 | 0.015936 | 0
| 0 | 0.0010256 | 0.011702 | 0
| 0 | 0.0045484 | 0.051897 | 0
| 0 | 2.5841e-05 | 0.00029485 | 0
| 0 | 0.0052612 | 0.06003 | 0
| 0 | 0.0031941 | 0.036445 | 0
| 0 | 0.00027546 | 0.0031429 | 0
| 0 | 0.00043893 | 0.0050082 | 0
| 0 | 0.0052644 | 0.060067 | 0
| 0 | 2.5817e-05 | 0.00029457 | 0
| 0 | 0.0027709 | 0.031616 | 0
| 0 | 0.0003872 | 0.004418 | 0
| 0 | 0.0048779 | 0.055656 | 0
| 0.14021 | 0.0088764 | 0.10128 | 0
| 0 | 0.0023648 | 0.026982 | 0
| 0 | 0.0033964 | 0.038753 | 0
| 0 | 0.0078518 | 0.089589 | 0
| 0 | 0.00074799 | 0.0085345 | 0
| 0 | 0.0038162 | 0.043542 | 0
| 0 | 0.0019416 | 0.022154 | 0
| 0 | 0.0041745 | 0.047631 | 0
| 0 | 0.0063637 | 0.072609 | 0
| 0 | 0.0021983 | 0.025083 | 0
| 0 | 0.00062661 | 0.0071497 | 0
| 1.1502 | 0.010092 | 0.11515 | 0
| 0 | 0.0012442 | 0.014196 | 0
| 0 | 0.00073782 | 0.0084185 | 0
| 0 | 0.0023076 | 0.02633 | 0
| 0 | 0.001025 | 0.011696 | 0
| 0 | 0.000463 | 0.0052828 | 0
| 0 | 0.0046917 | 0.053532 | 0
| 0 | 0.0011187 | 0.012765 | 0
| 0 | 0.00091707 | 0.010464 | 0
| 0 | 0.00012852 | 0.0014665 | 0
| 0 | 0.006066 | 0.069213 | 0
| 0 | 0.00080535 | 0.0091891 | 0
| 0 | 0.0023814 | 0.027172 | 0
| 0 | 0.00023128 | 0.0026389 | 0
| 0 | 0.00052673 | 0.00601 | 0
| 0 | 0.00038541 | 0.0043975 | 0
| 0 | 0.001062 | 0.012117 | 0
| 0 | 0.0029409 | 0.033556 | 0
| 0 | 0.002313 | 0.026392 | 0
| 0 | 0.00097606 | 0.011137 | 0
| 0 | 0.0014039 | 0.016018 | 0
| 0 | 0.0013567 | 0.01548 | 0
| 10.5645 | 0.024646 | 0.28121 | 0
| 0 | 0.0016771 | 0.019135 | 0
| 0 | 0.0024624 | 0.028096 | 0
| 0 | 0.005854 | 0.066794 | 0
| 0 | 0.0024524 | 0.027982 | 0
| 0 | 0.017749 | 0.20252 | 0
| 0 | 2.5619e-05 | 0.00029231 | 0
| 0 | 5.1233e-05 | 0.00058457 | 0
| 0 | 0.0018946 | 0.021618 | 0
| 0 | 0.00046931 | 0.0053548 | 0
| 0 | 0.0004179 | 0.0047682 | 0
| 0 | 0.0025669 | 0.029288 | 0
| 0 | 0.00021319 | 0.0024325 | 0
| 0 | 0.0035406 | 0.040398 | 0
| 0 | 2.5582e-05 | 0.00029189 | 0
| 0 | 0.003555 | 0.040562 | 0
| 0 | 0.00074982 | 0.0085555 | 0
| 0 | 0.0008051 | 0.0091862 | 0
| 0.042027 | 7.6676e-05 | 0.00087488 | 0
| 0 | 7.6639e-05 | 0.00087445 | 0
| 0 | 0.00061303 | 0.0069947 | 0
| 0 | 0.0088987 | 0.10153 | 0
| 0 | 0.0014484 | 0.016526 | 0
| 0 | 0.0066654 | 0.076053 | 0
| 0 | 0.00017865 | 0.0020384 | 0
| 0 | 0.0011059 | 0.012618 | 0
| 0 | 0.00076551 | 0.0087345 | 0
| 0 | 0.00067617 | 0.0077151 | 0
| 0 | 0.0072206 | 0.082387 | 0
| 0 | 0.0019134 | 0.021832 | 0
| 0 | 0.00020408 | 0.0023286 | 0
| 0 | 1.7005e-05 | 0.00019402 | 0
| 0 | 0.0025762 | 0.029395 | 0
| 0 | 0.0013347 | 0.015229 | 0
| 0 | 2.5503e-05 | 0.00029098 | 0
| 0 | 0.00099439 | 0.011346 | 0
| 0.094658 | 0.0006328 | 0.0072203 | 0
| 0 | 0.0010956 | 0.012501 | 0
| 0 | 0.0013847 | 0.015799 | 0
| 0 | 0.00011035 | 0.0012591 | 0
| 0 | 0.00010184 | 0.001162 | 0
| 0 | 0.0012048 | 0.013746 | 0
| 0 | 0.0026639 | 0.030395 | 0
| 0 | 0.0092021 | 0.105 | 0
| 0 | 0.00335 | 0.038223 | 0
| 0 | 0.00071237 | 0.0081281 | 0
| 0 | 0.0051114 | 0.058322 | 0
| 0 | 0.00057606 | 0.0065728 | 0
| 0 | 0.00037274 | 0.004253 | 0
| 0 | 0.0055144 | 0.062919 | 0
| 0 | 0.00027105 | 0.0030927 | 0
| 0 | 0.0009985 | 0.011393 | 0
| 0 | 0.000525 | 0.0059903 | 0
| 0 | 0.0035358 | 0.040344 | 0
| 0 | 0.00085513 | 0.0097571 | 0
| 0 | 0.0007112 | 0.0081147 | 0
| 0 | 0.00058408 | 0.0066644 | 0
| 0.54044 | 0.010681 | 0.12187 | 0
| 0 | 0.009874 | 0.11266 | 0
| 0 | 0.0028172 | 0.032145 | 0
| 0 | 0.0013196 | 0.015057 | 0
| 0 | 0.0020357 | 0.023227 | 0
| 0 | 0.00078653 | 0.0089743 | 0
| 0 | 5.9189e-05 | 0.00067535 | 0
| 0 | 0.00073555 | 0.0083926 | 0
| 0 | 0.0006085 | 0.006943 | 0
| 0 | 0.0011406 | 0.013015 | 0
| 0 | 0.00010136 | 0.0011565 | 0
| 0 | 0.00053205 | 0.0060706 | 0
| 0 | 0.00076849 | 0.0087684 | 0
| 0 | 0.0068632 | 0.078309 | 0
| 0 | 0.0012915 | 0.014736 | 0
| 0 | 0.0012323 | 0.014061 | 0
| 0 | 5.0637e-05 | 0.00057777 | 0
| 0 | 0.0028184 | 0.032158 | 0
| 0 | 0.00016033 | 0.0018293 | 0
| 0.034299 | 0.0047674 | 0.054396 | 0
| 0 | 0.0020397 | 0.023273 | 0
| 0 | 0.0055499 | 0.063324 | 0
| 0 | 0.0012973 | 0.014802 | 0
| 0 | 0.0016589 | 0.018928 | 0
| 0 | 4.2103e-05 | 0.00048039 | 0
| 0 | 0.00035356 | 0.0040341 | 0
| 0.062035 | 0.0045958 | 0.052438 | 0
| 0 | 0.0007068 | 0.0080646 | 0
| 0 | 0.00092554 | 0.01056 | 0
| 0 | 0.0029948 | 0.034171 | 0
| 0 | 1.6825e-05 | 0.00019197 | 0
| 0 | 0.0015308 | 0.017466 | 0
| 0 | 0.00079057 | 0.0090205 | 0
| 0 | 0.0016399 | 0.018711 | 0
| 0 | 0.0033611 | 0.038351 | 0
| 0 | 0.0011301 | 0.012894 | 0
| 0 | 0.00042836 | 0.0048876 | 0
| 0.17108 | 0.0080436 | 0.091777 | 0
| 0 | 0.0021158 | 0.024142 | 0
| 0 | 0.0036924 | 0.04213 | 0
| 0 | 4.1943e-05 | 0.00047857 | 0
| 0 | 0.0050869 | 0.058041 | 0
| 0 | 0.00052831 | 0.006028 | 0
| 0 | 0.00044441 | 0.0050707 | 0
| 0 | 0.0016853 | 0.019229 | 0
| 0 | 0.0036614 | 0.041777 | 0
| 0.47791 | 0.0037952 | 0.043303 | 0
| 0 | 2.5131e-05 | 0.00028675 | 0
| 0 | 0.0018341 | 0.020927 | 0
| 0 | 0.00012558 | 0.0014329 | 0
| 0 | 0.00051468 | 0.0058725 | 0
| 0.089785 | 0.00086968 | 0.009923 | 0
| 0 | 0.0087246 | 0.099548 | 0
| 0 | 0.0001354 | 0.0015449 | 0
| 0 | 0.0025149 | 0.028695 | 0
| 0 | 0.0015455 | 0.017634 | 0
| 0 | 0.00069071 | 0.007881 | 0
| 0 | 0.00082685 | 0.0094343 | 0
| 0 | 0.0012026 | 0.013722 | 0
| 0 | 0.0010511 | 0.011993 | 0
| 0 | 2.5039e-05 | 0.0002857 | 0
| 0 | 0.0018936 | 0.021606 | 0
| 0 | 0.0036913 | 0.042118 | 0
| 0 | 0.00049216 | 0.0056155 | 0
| 0 | 0.0037369 | 0.042638 | 0
| 0 | 0.0050797 | 0.057959 | 0
| 0 | 5.0013e-05 | 0.00057065 | 0
| 0 | 7.5012e-05 | 0.00085588 | 0
| 0 | 0.0029085 | 0.033186 | 0
| 0 | 0.001 | 0.01141 | 0
| 0 | 0.0072751 | 0.083008 | 0
| 0 | 0.003239 | 0.036957 | 0
| 0 | 0.0022315 | 0.025461 | 0
| 0 | 0.0039134 | 0.044652 | 0
| 0 | 0.0034629 | 0.039512 | 0
| 0 | 7.491e-05 | 0.00085472 | 0
| 3.3709 | 0.028835 | 0.329 | 0
| 0 | 0.0013967 | 0.015937 | 0
| 0 | 0.00076469 | 0.0087252 | 0
| 0 | 0.00059843 | 0.0068281 | 0
| 0 | 0.0011252 | 0.012838 | 0
| 0 | 0.0012953 | 0.01478 | 0
| 0 | 0.00014945 | 0.0017053 | 0
| 0 | 0.0014446 | 0.016483 | 0
| 0 | 1.6603e-05 | 0.00018944 | 0
| 0 | 0.004632 | 0.052851 | 0
| 0 | 0.0040536 | 0.046252 | 0
| 0 | 2.4869e-05 | 0.00028375 | 0
| 0 | 0.0018897 | 0.021561 | 0
| 0 | 0.0031864 | 0.036357 | 0
| 0 | 0.0014119 | 0.016109 | 0
| 0 | 0.0045203 | 0.051577 | 0
| 0 | 0.0015645 | 0.017851 | 0
| 0 | 0.0013406 | 0.015297 | 0
| 0 | 0.0011046 | 0.012603 | 0
| 0 | 0.00073621 | 0.0084002 | 0
| 0 | 0.0032894 | 0.037532 | 0
| 0 | 0.00017367 | 0.0019815 | 0
| 0 | 4.1343e-05 | 0.00047173 | 0
| 0 | 0.0024225 | 0.02764 | 0
| 0 | 0.0017609 | 0.020092 | 0
| 0 | 0.00084304 | 0.0096191 | 0
| 0 | 0.0004627 | 0.0052795 | 0
| 0 | 0.0023053 | 0.026303 | 0
| 0 | 0.0016029 | 0.018289 | 0
| 0 | 0.00061935 | 0.0070667 | 0
| 0 | 0.0023946 | 0.027323 | 0
| 0 | 0.0021716 | 0.024778 | 0
| 0 | 0.0009656 | 0.011018 | 0
| 0 | 1.2377e-05 | 0.00014122 | 0
| 0 | 0.00099427 | 0.011345 | 0
| 0 | 0.013193 | 0.15053 | 0
| 0 | 0.0052676 | 0.060104 | 0
| 0 | 0.0021858 | 0.024939 | 0
| 0 | 0.0042675 | 0.048693 | 0
| 0 | 0.0011875 | 0.013549 | 0
| 0 | 0.0014635 | 0.016698 | 0
| 0 | 0.00086543 | 0.0098745 | 0
| 0 | 0.0031895 | 0.036392 | 0
| 0 | 0.0042028 | 0.047954 | 0
| 0 | 0.00028826 | 0.003289 | 0
| 0 | 0.0055262 | 0.063054 | 0
| 0 | 0.00018939 | 0.0021609 | 0
| 0 | 0.0035321 | 0.040301 | 0
| 0.51905 | 0.0052852 | 0.060304 | 0
| 0 | 0.0062234 | 0.071009 | 0
| 0 | 0.00064179 | 0.0073228 | 0
| 0 | 0.0058734 | 0.067016 | 0
| 0 | 0.00070729 | 0.0080701 | 0
| 0 | 0.0018008 | 0.020547 | 0
| 0 | 0.0021105 | 0.024081 | 0
| 0 | 0.0083315 | 0.095063 | 0
| 0 | 0.002111 | 0.024087 | 0
| 0 | 0.00031212 | 0.0035613 | 0
| 0 | 0.0073498 | 0.083861 | 0
| 0 | 0.0001478 | 0.0016864 | 0
| 0 | 2.4628e-05 | 0.00028101 | 0
| 0 | 0.00037352 | 0.0042619 | 0
| 0 | 0.00022163 | 0.0025288 | 0
| 0 | 0.0002495 | 0.0028468 | 0
| 0 | 0.0015263 | 0.017415 | 0
| 0 | 0.0020102 | 0.022936 | 0
| 0 | 0.001046 | 0.011935 | 0
| 1.6881 | 0.0046512 | 0.05307 | 0
| 0 | 0.0010088 | 0.01151 | 0
| 0 | 0.0022348 | 0.025499 | 0
| 0 | 0.0010698 | 0.012207 | 0
| 0 | 0.00041805 | 0.0047699 | 0
| 0 | 0.005633 | 0.064273 | 0
| 0 | 2.4583e-05 | 0.00028049 | 0
| 0 | 0.0011874 | 0.013549 | 0
| 0.020012 | 0.0052894 | 0.060353 | 0
| 0 | 0.00084738 | 0.0096686 | 0
| 0 | 2.4553e-05 | 0.00028015 | 0
| 0 | 0.00022096 | 0.0025211 | 0
| 0 | 0.0023323 | 0.026611 | 0
| 0 | 0.0014727 | 0.016804 | 0
| 0 | 0.00056044 | 0.0063946 | 0
| 0 | 0.00043115 | 0.0049194 | 0
| 0 | 0.0018162 | 0.020723 | 0
| 0 | 0.00039254 | 0.0044788 | 0
| 0 | 0.0020483 | 0.023372 | 0
| 0 | 0.0034792 | 0.039698 | 0
| 0 | 0.0026896 | 0.030688 | 0
| 0 | 0.0014057 | 0.016039 | 0
| 0 | 0.0013974 | 0.015944 | 0
| 0 | 0.0033243 | 0.037931 | 0
| 0 | 0.0026953 | 0.030754 | 0
| 0 | 0.0021844 | 0.024924 | 0
| 0 | 0.0019029 | 0.021712 | 0
| 0 | 0.0027768 | 0.031683 | 0
| 0 | 0.0019346 | 0.022074 | 0
| 0 | 0.0002857 | 0.0032598 | 0
| 0 | 0.0055885 | 0.063764 | 0
| 0 | 0.0028594 | 0.032626 | 0
| 0 | 0.00019583 | 0.0022344 | 0
| 0 | 0.0021949 | 0.025044 | 0
| 0 | 0.0014111 | 0.016101 | 0
| 0 | 0.00048926 | 0.0055825 | 0
| 0 | 0.005106 | 0.05826 | 0
| 0 | 0.00033413 | 0.0038124 | 0
| 0 | 0.00099388 | 0.01134 | 0
| 1.9839 | 0.0020773 | 0.023702 | 0
| 0 | 0.0010426 | 0.011896 | 0
| 0 | 0.00046179 | 0.005269 | 0
| 0 | 0.0010095 | 0.011518 | 0
| 0 | 0.0010172 | 0.011606 | 0
| 0 | 0.0029861 | 0.034072 | 0
| 0 | 0.0037668 | 0.042979 | 0
| 0 | 0.0009272 | 0.010579 | 0
| 0 | 0.00024396 | 0.0027835 | 0
| 0 | 0.00059359 | 0.0067729 | 0
| 0 | 0.0012438 | 0.014192 | 0
| 0 | 0.00014633 | 0.0016696 | 0
| 0 | 0.0039163 | 0.044685 | 0
| 0 | 0.0007758 | 0.0088519 | 0
| 0 | 0.00090975 | 0.01038 | 0
| 0 | 0.00519 | 0.059218 | 0
| 0.23271 | 0.0081513 | 0.093007 | 0
| 0 | 0.001583 | 0.018062 | 0
| 0 | 0.0005356 | 0.0061112 | 0
| 0 | 3.246e-05 | 0.00037037 | 0
| 0 | 0.010289 | 0.11739 | 0
| 0 | 0.0018741 | 0.021384 | 0
| 0 | 0.0073502 | 0.083866 | 0
| 0 | 0.00059203 | 0.0067551 | 0
| 0 | 0.0030073 | 0.034313 | 0
| 0 | 0.0012482 | 0.014242 | 0
| 0 | 4.0514e-05 | 0.00046227 | 0
| 0 | 0.0012672 | 0.014459 | 0
| 0 | 0.0014867 | 0.016963 | 0
| 0 | 0.0014978 | 0.01709 | 0
| 0.014771 | 0.0031171 | 0.035566 | 0
| 0 | 0.0035698 | 0.040731 | 0
| 0 | 0.0011871 | 0.013545 | 0
| 0 | 0.0034391 | 0.03924 | 0
| 0 | 0.00031154 | 0.0035546 | 0
| 0 | 0.0021471 | 0.024499 | 0
| 0 | 0.0003073 | 0.0035063 | 0
| 0 | 0.004255 | 0.04855 | 0
| 0 | 0.00080029 | 0.0091313 | 0
| 0 | 0.00071132 | 0.0081161 | 0
| 0 | 0.0019925 | 0.022734 | 0
| 0 | 0.0027738 | 0.031649 | 0
| 0 | 0.0022546 | 0.025725 | 0
| 0.71269 | 0.0062287 | 0.07107 | 0
| 0 | 0.0047257 | 0.053921 | 0
| 0 | 0.00056547 | 0.006452 | 0
| 0 | 0.0010021 | 0.011434 | 0
| 0 | 0.0023719 | 0.027064 | 0
| 0.074218 | 0.0015248 | 0.017398 | 0
| 0 | 0.0032399 | 0.036968 | 0
| 0.14469 | 0.00019341 | 0.0022068 | 0
| 0 | 0.0010395 | 0.01186 | 0
| 0 | 0.00066872 | 0.00763 | 0
| 0 | 0.0014743 | 0.016822 | 0
| 0 | 0.0061881 | 0.070606 | 0
| 0 | 0.00094246 | 0.010753 | 0
| 0 | 0.0033003 | 0.037657 | 0
| 0 | 0.00086142 | 0.0098289 | 0
| 0 | 0.00022944 | 0.0026179 | 0
| 0 | 0.0076465 | 0.087247 | 0
| 0 | 0.00067594 | 0.0077125 | 0
| 0 | 0.007041 | 0.080338 | 0
| 0 | 0.0068397 | 0.07804 | 0
| 0 | 0.00017862 | 0.002038 | 0
| 0 | 0.0012389 | 0.014136 | 0
| 0 | 0.0035773 | 0.040818 | 0
| 0 | 0.0028472 | 0.032486 | 0
| 0.017444 | 0.0031159 | 0.035552 | 0
| 0 | 0.00032559 | 0.003715 | 0
| 0 | 0.0015589 | 0.017787 | 0
| 0.6531 | 0.0014703 | 0.016776 | 0
| 0 | 0.0033656 | 0.038401 | 0
| 0 | 0.0028833 | 0.032898 | 0
| 0 | 0.0013732 | 0.015668 | 0
| 0 | 0.00072262 | 0.0082451 | 0
| 0 | 0.0037576 | 0.042874 | 0
| 0 | 0.00016861 | 0.0019238 | 0
| 0 | 0.0011962 | 0.013648 | 0
| 0 | 0.0024083 | 0.027479 | 0
| 0 | 2.4079e-05 | 0.00027475 | 0
| 0 | 0.0028107 | 0.03207 | 0
| 0 | 0.00012842 | 0.0014652 | 0
| 0.065647 | 0.0046804 | 0.053404 | 0
| 0 | 0.0057503 | 0.065611 | 0
| 0 | 0.00061749 | 0.0070455 | 0
| 0.14542 | 0.00012429 | 0.0014181 | 0
| 0 | 4.0071e-05 | 0.00045721 | 0
| 0 | 0.0010454 | 0.011928 | 0
| 0 | 0.0042894 | 0.048942 | 0
| 0 | 0.0022828 | 0.026047 | 0
| 0 | 0.0013012 | 0.014847 | 0
| 0 | 1.2009e-05 | 0.00013702 | 0
| 0 | 7.2035e-05 | 0.00082192 | 0
| 0 | 0.0054484 | 0.062166 | 0
| 0 | 0.0027596 | 0.031487 | 0
| 0 | 0.0026301 | 0.03001 | 0
| 0 | 0.000967 | 0.011034 | 0
| 0 | 0.0094733 | 0.10809 | 0
| 0 | 0.00021564 | 0.0024605 | 0
| 0 | 0.001166 | 0.013304 | 0
| 0 | 0.0029708 | 0.033897 | 0
| 0 | 0.00023952 | 0.0027329 | 0
| 0 | 0.0028296 | 0.032285 | 0
| 0 | 0.0021387 | 0.024402 | 0
| 0 | 0.0015717 | 0.017933 | 0
| 0 | 0.00080139 | 0.0091438 | 0
| 0 | 0.0045689 | 0.052131 | 0
| 0 | 0.0029741 | 0.033934 | 0
| 0 | 0.0018811 | 0.021464 | 0
| 0 | 0.0015941 | 0.018189 | 0
| 0 | 2.3905e-05 | 0.00027276 | 0
| 0 | 0.0008446 | 0.0096369 | 0
| 0 | 0.0018963 | 0.021637 | 0
| 0 | 0.0014262 | 0.016273 | 0
| 0 | 0.001423 | 0.016236 | 0
| 0 | 0.0017916 | 0.020442 | 0
| 0 | 0.0078538 | 0.089612 | 0
| 0 | 0.0015843 | 0.018077 | 0
| 0.16709 | 0.00074037 | 0.0084477 | 0
| 0 | 0.00042192 | 0.0048141 | 0
| 0 | 0.0040553 | 0.046271 | 0
| 0 | 0.0037325 | 0.042588 | 0
| 0 | 0.00063662 | 0.0072638 | 0
| 0 | 0.00023074 | 0.0026327 | 0
| 0 | 0.0044078 | 0.050293 | 0
| 0 | 0.0021716 | 0.024778 | 0
| 0 | 2.3862e-05 | 0.00027227 | 0
| 0 | 0.00028628 | 0.0032665 | 0
| 0 | 0.0010773 | 0.012292 | 0
| 0 | 0.0018405 | 0.021 | 0
| 0 | 0.0028142 | 0.03211 | 0
| 0 | 0.003434 | 0.039182 | 0
| 0 | 0.0056858 | 0.064875 | 0
| 0 | 0.0056017 | 0.063916 | 0
| 0 | 0.00028601 | 0.0032633 | 0
| 0 | 0.0025417 | 0.029001 | 0
| 0 | 0.00045263 | 0.0051645 | 0
| 0 | 0.0077334 | 0.088238 | 0
| 0 | 4.128e-05 | 0.00047101 | 0
| 0 | 0.0063663 | 0.072639 | 0
| 0 | 0.0092389 | 0.10542 | 0
| 0 | 0.00099214 | 0.01132 | 0
| 0 | 0.0034419 | 0.039272 | 0
| 0 | 0.0024443 | 0.02789 | 0
| 0 | 0.0017181 | 0.019604 | 0
| 0 | 0.00035709 | 0.0040744 | 0
| 1.0843 | 0.0038803 | 0.044274 | 0
| 0 | 6.3462e-05 | 0.0007241 | 0
| 0 | 0.00063451 | 0.0072398 | 0
| 0 | 0.0028509 | 0.032528 | 0
| 0 | 0.0016173 | 0.018453 | 0
| 0 | 0.0028455 | 0.032467 | 0
| 0 | 0.00090352 | 0.010309 | 0
| 0 | 0.00035651 | 0.0040678 | 0
| 0 | 8.3185e-05 | 0.00094914 | 0
| 0 | 4.7532e-05 | 0.00054234 | 0
| 0 | 0.0034894 | 0.039814 | 0
| 0 | 0.00087132 | 0.0099417 | 0
| 0 | 0.00087921 | 0.010032 | 0
| 0 | 0.0018213 | 0.020781 | 0
| 0 | 0.00021378 | 0.0024392 | 0
| 0 | 0.0029612 | 0.033787 | 0
| 0 | 0.0021771 | 0.024841 | 0
| 0 | 0.008138 | 0.092855 | 0
| 0 | 0.0014407 | 0.016438 | 0
| 0 | 0.00011871 | 0.0013545 | 0
| 0 | 2.3736e-05 | 0.00027083 | 0
| 0 | 0.0025944 | 0.029602 | 0
| 0 | 0.00040332 | 0.0046019 | 0
| 0.55253 | 0.0018187 | 0.020751 | 0
| 0 | 0.0022765 | 0.025974 | 0
| 0 | 0.0024178 | 0.027588 | 0
| 0 | 0.00011852 | 0.0013523 | 0
| 0 | 0.00063204 | 0.0072115 | 0
| 0 | 0.0033798 | 0.038563 | 0
| 0 | 0.0031996 | 0.036507 | 0
| 0 | 0.00040278 | 0.0045957 | 0
| 0 | 4.7385e-05 | 0.00054066 | 0
| 0 | 0.00085279 | 0.0097304 | 0
| 0 | 0.0029058 | 0.033155 | 0
| 0 | 0.0010422 | 0.011891 | 0
| 0 | 0.0010458 | 0.011932 | 0
| 0 | 4.7349e-05 | 0.00054026 | 0
| 0 | 0.0022062 | 0.025173 | 0
| 0 | 0.0086245 | 0.098406 | 0
| 0 | 4.733e-05 | 0.00054003 | 0
| 0 | 0.00070177 | 0.0080072 | 0
| 0 | 0.0053064 | 0.060546 | 0
| 0 | 0.0010052 | 0.011469 | 0
| 0 | 0.00040201 | 0.004587 | 0
| 0.026607 | 0.0034524 | 0.039392 | 0
| 0 | 0.0026357 | 0.030074 | 0
| 0 | 0.0029861 | 0.034071 | 0
| 0 | 0.0006381 | 0.0072807 | 0
| 0 | 0.0028121 | 0.032086 | 0
| 0 | 0.0022133 | 0.025254 | 0
| 0 | 0.00051198 | 0.0058417 | 0
| 0 | 0.00088985 | 0.010153 | 0
| 0 | 9.4489e-05 | 0.0010781 | 0
| 0 | 0.0018059 | 0.020605 | 0
| 0 | 7.0829e-05 | 0.00080816 | 0
| 0 | 0.0046194 | 0.052707 | 0
| 0 | 0.0015734 | 0.017953 | 0
| 0.049297 | 0.0038707 | 0.044164 | 0
| 0 | 0.0016757 | 0.01912 | 0
| 0 | 0.0062501 | 0.071314 | 0
| 0 | 0.00049548 | 0.0056534 | 0
| 0 | 0.00051881 | 0.0059196 | 0
| 0 | 0.000723 | 0.0082495 | 0
| 0 | 0.00095525 | 0.010899 | 0
| 0 | 0.001791 | 0.020435 | 0
| 0 | 0.0031577 | 0.036029 | 0
| 0 | 2.3565e-05 | 0.00026888 | 0
| 0 | 0.00014138 | 0.0016131 | 0
| 0 | 0.0010916 | 0.012455 | 0
| 0 | 0.0019549 | 0.022306 | 0
| 0 | 2.3553e-05 | 0.00026874 | 0
| 0 | 0.00044748 | 0.0051057 | 0
| 0 | 0.0015465 | 0.017646 | 0
| 0 | 0.0011854 | 0.013525 | 0
| 0 | 0.0012167 | 0.013883 | 0
| 0 | 0.0016165 | 0.018444 | 0
| 0 | 0.00069814 | 0.0079658 | 0
| 0 | 0.0035218 | 0.040183 | 0
| 0 | 0.00054113 | 0.0061743 | 0
| 0 | 2.3514e-05 | 0.0002683 | 0
| 0 | 0.00047025 | 0.0053656 | 0
| 0 | 0.0022606 | 0.025794 | 0
| 0 | 0.0021389 | 0.024405 | 0
| 0 | 0.00065025 | 0.0074194 | 0
| 0 | 0.001222 | 0.013943 | 0
| 0 | 0.00025849 | 0.0029494 | 0
| 1.1148 | 0.0034774 | 0.039677 | 0
| 0 | 0.00093355 | 0.010652 | 0
| 0 | 0.0010492 | 0.011971 | 0
| 0 | 0.0043141 | 0.049224 | 0
| 0 | 0.0028519 | 0.03254 | 0
| 0.83488 | 0.0072439 | 0.082653 | 0
| 0 | 0.0005319 | 0.0060689 | 0
| 0 | 0.0010872 | 0.012405 | 0
| 0 | 0.0026195 | 0.029888 | 0
| 0 | 0.00064895 | 0.0074046 | 0
| 0 | 1.1725e-05 | 0.00013378 | 0
| 0.3252 | 0.0003048 | 0.0034777 | 0
| 0 | 0.0073073 | 0.083376 | 0
| 0 | 0.0016919 | 0.019305 | 0
| 0 | 0.0053839 | 0.061431 | 0
| 0 | 0.0023126 | 0.026387 | 0
| 0.024911 | 0.00021094 | 0.0024069 | 0
| 0 | 0.002531 | 0.028878 | 0
| 0 | 0.00043737 | 0.0049904 | 0
| 0 | 0.002054 | 0.023436 | 0
| 0 | 0.006021 | 0.0687 | 0
| 0 | 0.0012625 | 0.014405 | 0
| 0 | 0.001093 | 0.012471 | 0
| 0 | 0.0046749 | 0.053341 | 0
| 1.0528 | 0.0077967 | 0.08896 | 0
| 0 | 2.3413e-05 | 0.00026714 | 0
| 0 | 2.3408e-05 | 0.00026709 | 0
| 0 | 0.00042106 | 0.0048043 | 0
| 0 | 0.0014659 | 0.016726 | 0
| 0 | 0.0020815 | 0.02375 | 0
| 0 | 0.0029688 | 0.033875 | 0
| 0 | 0.0021039 | 0.024005 | 0
| 0 | 2.3374e-05 | 0.0002667 | 0
| 0 | 0.0023834 | 0.027195 | 0
| 0 | 0.0052371 | 0.059756 | 0
| 0 | 0.0017989 | 0.020526 | 0
| 0 | 0.006765 | 0.077188 | 0
| 0 | 3.8926e-05 | 0.00044414 | 0
| 0 | 0.0034098 | 0.038906 | 0
| 0 | 0.00077843 | 0.0088819 | 0
| 0 | 0.0088576 | 0.10106 | 0
| 0 | 0.00022959 | 0.0026197 | 0
| 0 | 2.7237e-05 | 0.00031077 | 0
| 0 | 0.00025677 | 0.0029297 | 0
| 0 | 0.00025675 | 0.0029295 | 0
| 1.1795 | 0.0010269 | 0.011717 | 0
| 0 | 0.0079177 | 0.09034 | 0
| 0 | 0.00011668 | 0.0013313 | 0
| 0 | 0.01136 | 0.12962 | 0
| 0 | 0.0012438 | 0.014191 | 0
| 0 | 0.0022386 | 0.025543 | 0
| 0 | 0.0035561 | 0.040575 | 0
| 0 | 0.0036843 | 0.042038 | 0
| 0 | 0.0026572 | 0.030319 | 0
| 0 | 0.0016388 | 0.018699 | 0
| 0 | 0.0011182 | 0.012759 | 0
| 0 | 0.00090835 | 0.010364 | 0
| 0 | 0.0016303 | 0.018602 | 0
| 0.031374 | 0.00046572 | 0.0053139 | 0
| 0 | 3.4923e-05 | 0.00039847 | 0
| 0 | 0.0067583 | 0.077112 | 0
| 0 | 0.00090772 | 0.010357 | 0
| 0 | 0.0012568 | 0.01434 | 0
| 0 | 2.327e-05 | 0.00026551 | 0
| 0 | 0.00090875 | 0.010369 | 0
| 0 | 0.0056457 | 0.064417 | 0
| 0 | 0.00022483 | 0.0025653 | 0
| 0 | 0.00055043 | 0.0062804 | 0
| 0 | 5.426e-05 | 0.0006191 | 0
| 0 | 0.0060685 | 0.069241 | 0
| 0 | 0.0053166 | 0.060663 | 0
| 0 | 0.00049567 | 0.0056556 | 0
| 0.10233 | 0.0006738 | 0.0076881 | 0
| 0 | 0.0034774 | 0.039677 | 0
| 0 | 0.00010065 | 0.0011485 | 0
| 0 | 0.0022608 | 0.025796 | 0
| 0 | 0.0014865 | 0.01696 | 0
| 0 | 0.0022721 | 0.025925 | 0
| 0 | 0.00080484 | 0.0091833 | 0
| 0 | 0.0019957 | 0.022771 | 0
| 0 | 0.0007424 | 0.0084708 | 0
| 0 | 0.0066631 | 0.076025 | 0
| 0 | 0.0022261 | 0.0254 | 0
| 0 | 0.006956 | 0.079368 | 0
| 0 | 0.00024728 | 0.0028214 | 0
| 0 | 2.3178e-05 | 0.00026446 | 0
| 0 | 0.00091931 | 0.010489 | 0
| 0 | 0.0008575 | 0.0097841 | 0
| 0 | 0.00076463 | 0.0087244 | 0
| 0 | 0.0074276 | 0.084749 | 0
| 0 | 0.0023396 | 0.026695 | 0
| 0 | 0.0011031 | 0.012586 | 0
| 0 | 0.0019442 | 0.022183 | 0
| 0 | 0.00030087 | 0.0034329 | 0
| 0 | 2.3138e-05 | 0.000264 | 0
| 0 | 0.00033158 | 0.0037833 | 0
| 0 | 0.0016847 | 0.019222 | 0
| 0 | 0.0017116 | 0.019529 | 0
| 0 | 0.0036574 | 0.041731 | 0
| 0 | 0.00064742 | 0.007387 | 0
| 0 | 0.00047773 | 0.0054509 | 0
| 0 | 0.0026583 | 0.030331 | 0
| 0 | 0.0018236 | 0.020807 | 0
| 0 | 0.00013865 | 0.001582 | 0
| 0 | 0.0019176 | 0.021879 | 0
| 0 | 0.00065446 | 0.0074673 | 0
| 0 | 0.00036956 | 0.0042166 | 0
| 0 | 1.5397e-05 | 0.00017568 | 0
| 0 | 0.0010776 | 0.012296 | 0
| 0 | 0.00071572 | 0.0081664 | 0
| 0 | 0.0033931 | 0.038716 | 0
| 0 | 0.0016195 | 0.018479 | 0
| 0 | 0.00034616 | 0.0039497 | 0
| 0 | 0.0002769 | 0.0031594 | 0
| 0 | 0.0043149 | 0.049233 | 0
| 0 | 0.0058839 | 0.067136 | 0
| 0 | 0.00094597 | 0.010794 | 0
| 0 | 0.00019994 | 0.0022813 | 0
| 0 | 0.003508 | 0.040026 | 0
| 0 | 0.003014 | 0.03439 | 0
| 0 | 0.0011069 | 0.01263 | 0
| 0 | 0.00059953 | 0.0068406 | 0
| 0 | 0.00029205 | 0.0033323 | 0
| 0 | 2.3053e-05 | 0.00026303 | 0
| 0 | 0.0058014 | 0.066194 | 0
| 0 | 0.0021514 | 0.024547 | 0
| 0 | 0.0041178 | 0.046984 | 0
| 0 | 0.0045187 | 0.051559 | 0
| 0 | 2.3033e-05 | 0.00026281 | 0
| 0 | 0.00033007 | 0.0037661 | 0
| 0 | 0.0012969 | 0.014797 | 0
| 0 | 0.0016345 | 0.01865 | 0
| 0 | 0.0014425 | 0.016459 | 0
| 0 | 0.0086133 | 0.098277 | 0
| 0 | 0.0046257 | 0.05278 | 0
| 0 | 0.0016639 | 0.018985 | 0
| 0 | 0.0024765 | 0.028257 | 0
| 0 | 0.00033726 | 0.0038481 | 0
| 0 | 1.5329e-05 | 0.00017491 | 0
| 0 | 0.0062467 | 0.071274 | 0
| 0 | 0.00074002 | 0.0084436 | 0
| 0 | 0.0013258 | 0.015127 | 0
| 1.5512 | 0.0076784 | 0.08761 | 0
| 0 | 0.0010305 | 0.011758 | 0
| 0 | 0.0046723 | 0.053311 | 0
| 0 | 0.00033699 | 0.0038451 | 0
| 0 | 0.00096471 | 0.011007 | 0
| 0 | 0.0016926 | 0.019312 | 0
| 0 | 0.0010406 | 0.011873 | 0
| 0 | 0.0037565 | 0.042862 | 0
| 0 | 0.00086454 | 0.0098644 | 0
| 0 | 0.0030526 | 0.03483 | 0
| 0 | 0.0024938 | 0.028454 | 0
| 0 | 0.00082222 | 0.0093816 | 0
| 0 | 0.0076494 | 0.08728 | 0
| 0 | 0.0027758 | 0.031672 | 0
| 0 | 0.0013763 | 0.015703 | 0
| 0 | 0.0019727 | 0.022508 | 0
| 0 | 0.0023564 | 0.026887 | 0
| 0 | 0.0020642 | 0.023553 | 0
| 0 | 0.0015899 | 0.018141 | 0
| 0 | 0.0049143 | 0.056073 | 0
| 0 | 0.0034838 | 0.03975 | 0
| 0 | 0.00029795 | 0.0033996 | 0
| 0 | 6.1101e-05 | 0.00069716 | 0
| 0 | 0.0058722 | 0.067002 | 0
| 0 | 0.0012485 | 0.014245 | 0
| 0 | 0.0013553 | 0.015464 | 0
| 0 | 0.0014505 | 0.01655 | 0
| 0 | 0.0022557 | 0.025738 | 0
| 0 | 0.0031518 | 0.035962 | 0
| 0 | 0.0013049 | 0.014889 | 0
| 0 | 0.0029148 | 0.033258 | 0
| 0 | 0.0025861 | 0.029507 | 0
| 0 | 0.00089245 | 0.010183 | 0
| 0 | 2.2881e-05 | 0.00026108 | 0
| 0 | 0.00052245 | 0.0059612 | 0
| 0 | 0.0016089 | 0.018358 | 0
| 0 | 0.00084632 | 0.0096565 | 0
| 0 | 0.0069762 | 0.079598 | 0
| 0 | 0.0015706 | 0.01792 | 0
| 0 | 0.0019593 | 0.022355 | 0
| 0 | 6.8612e-05 | 0.00078286 | 0
| 0 | 0.0047494 | 0.054191 | 0
| 0 | 0.0016158 | 0.018436 | 0
| 0 | 0.0025303 | 0.028871 | 0
| 0.036797 | 0.0017072 | 0.019479 | 0
| 0 | 0.0021035 | 0.024 | 0
| 0 | 0.00063252 | 0.0072171 | 0
| 0 | 0.00041145 | 0.0046946 | 0
| 0 | 0.00077695 | 0.0088651 | 0
| 0 | 0.0012832 | 0.014641 | 0
| 0 | 0.00088297 | 0.010075 | 0
| 0 | 0.00207 | 0.023618 | 0
| 0 | 0.0004678 | 0.0053376 | 0
| 0 | 0.0035826 | 0.040877 | 0
| 0 | 0.0018938 | 0.021608 | 0
| 0 | 6.843e-05 | 0.00078078 | 0
| 0 | 0.00063868 | 0.0072873 | 0
| 0 | 0.0016493 | 0.018819 | 0
| 0 | 2.2798e-05 | 0.00026012 | 0
| 0 | 0.001831 | 0.020892 | 0
| 0 | 0.00045579 | 0.0052005 | 0
| 0 | 0.0001823 | 0.00208 | 0
| 0 | 0.0012609 | 0.014387 | 0
| 0 | 0.00014429 | 0.0016463 | 0
| 0 | 0.0028666 | 0.032708 | 0
| 0 | 0.0017536 | 0.020009 | 0
| 0 | 0.002539 | 0.02897 | 0
| 0 | 0.00047061 | 0.0053696 | 0
| 0 | 0.0020266 | 0.023123 | 0
| 0 | 0.0014092 | 0.016079 | 0
| 0 | 2.2764e-05 | 0.00025974 | 0
| 0 | 0.0023595 | 0.026922 | 0
| 0 | 0.0040892 | 0.046658 | 0
| 0 | 0.0029472 | 0.033627 | 0
| 0 | 0.0019341 | 0.022069 | 0
| 0 | 0.0030185 | 0.034441 | 0
| 0 | 0.001676 | 0.019123 | 0
| 0 | 0.00051556 | 0.0058825 | 0
| 0 | 8.7189e-05 | 0.00099483 | 0
| 0 | 0.0015693 | 0.017906 | 0
| 0 | 0.00092486 | 0.010553 | 0
| 0 | 0.0025546 | 0.029148 | 0
| 0 | 0.0020397 | 0.023273 | 0
| 0 | 2.2735e-05 | 0.00025941 | 0
| 0 | 0.0060624 | 0.069172 | 0
| 0 | 0.0044757 | 0.051068 | 0
| 0 | 0.0024926 | 0.028441 | 0
| 0 | 0.0021819 | 0.024896 | 0
| 0 | 0.00017419 | 0.0019875 | 0
| 0 | 0.00099208 | 0.01132 | 0
| 0.17268 | 0.0024989 | 0.028513 | 0
| 0 | 0.0022035 | 0.025141 | 0
| 0 | 0.002139 | 0.024406 | 0
| 0 | 0.0013323 | 0.015201 | 0
| 6.9092 | 0.0078558 | 0.089634 | 0
| 0 | 0.00011352 | 0.0012953 | 0
| 0 | 0.0033519 | 0.038245 | 0
| 0 | 0.0018158 | 0.020718 | 0
| 0 | 0.00061283 | 0.0069924 | 0
| 0 | 0.00034803 | 0.003971 | 0
| 0 | 0.0044256 | 0.050496 | 0
| 0 | 0.0019441 | 0.022182 | 0
| 0 | 0.0026092 | 0.029771 | 0
| 0 | 0.00083948 | 0.0095784 | 0
| 0 | 0.00031384 | 0.003581 | 0
| 0 | 0.0017975 | 0.02051 | 0
| 0 | 0.0022303 | 0.025447 | 0
| 0 | 2.268e-05 | 0.00025877 | 0
| 0 | 0.00022674 | 0.0025871 | 0
| 0 | 0.0019816 | 0.02261 | 0
| 0 | 0.0025125 | 0.028667 | 0
| 0 | 6.7982e-05 | 0.00077568 | 0
| 0 | 0.0010648 | 0.012149 | 0
| 0 | 0.0011479 | 0.013097 | 0
| 0 | 0.0092441 | 0.10548 | 0
| 0 | 0.0029487 | 0.033644 | 0
| 0 | 0.0046629 | 0.053204 | 0
| 0 | 0.0034344 | 0.039187 | 0
| 0 | 0.00034716 | 0.0039611 | 0
| 0 | 0.0022413 | 0.025573 | 0
| 0 | 0.00092808 | 0.010589 | 0
| 0 | 0.0027159 | 0.030989 | 0
| 0 | 0.0015654 | 0.017861 | 0
| 0 | 0.0049782 | 0.056802 | 0
| 0 | 0.0019172 | 0.021875 | 0
| 0 | 0.00033939 | 0.0038724 | 0
| 0 | 0.0014796 | 0.016883 | 0
| 0 | 0.0019456 | 0.022199 | 0
| 0 | 0.0011312 | 0.012907 | 0
| 0 | 0.00015833 | 0.0018065 | 0
| 0 | 0.0025935 | 0.029592 | 0
| 0 | 0.0036977 | 0.042191 | 0
| 0 | 0.0017337 | 0.019781 | 0
| 0 | 0.0017223 | 0.019651 | 0
| 0 | 0.0042129 | 0.048069 | 0
| 0 | 0.00067202 | 0.0076677 | 0
| 0 | 0.00031638 | 0.0036098 | 0
| 0 | 0.00035398 | 0.0040389 | 0
| 0 | 0.00015061 | 0.0017184 | 0
| 0 | 0.0046535 | 0.053096 | 0
| 0 | 0.00067744 | 0.0077296 | 0
| 0 | 0.0014036 | 0.016015 | 0
| 0 | 0.004 | 0.04564 | 0
| 0 | 0.00074504 | 0.0085009 | 0
| 0 | 0.00039117 | 0.0044633 | 0
| 0 | 0.001843 | 0.021029 | 0
| 0 | 0.0049258 | 0.056203 | 0
| 0 | 0.00051415 | 0.0058664 | 0
| 0 | 0.0014908 | 0.01701 | 0
| 0 | 0.0048918 | 0.055816 | 0
| 0 | 0.0022761 | 0.02597 | 0
| 0 | 0.0011943 | 0.013627 | 0
| 0 | 2.253e-05 | 0.00025706 | 0
| 0 | 0.00095741 | 0.010924 | 0
| 0 | 0.0018245 | 0.020817 | 0
| 0 | 9.0096e-06 | 0.0001028 | 0
| 0 | 0.0028217 | 0.032196 | 0
| 0 | 0.002117 | 0.024155 | 0
| 0 | 0.001629 | 0.018587 | 0
| 0 | 0.0035653 | 0.04068 | 0
| 0 | 0.0018948 | 0.02162 | 0
| 0 | 0.0016283 | 0.018579 | 0
| 2.9457e-05 | 0.00053996 | 0.0061609 | 0
| 0 | 0.0038919 | 0.044407 | 0
| 0 | 0.0021135 | 0.024115 | 0
| 0 | 2.2483e-05 | 0.00025653 | 0
| 0 | 0.0052366 | 0.05975 | 0
| 0.90658 | 0.0071542 | 0.08163 | 0
| 0 | 0.000964 | 0.010999 | 0
| 0 | 0.00040069 | 0.0045719 | 0
| 0 | 0.0027933 | 0.031872 | 0
| 0 | 0.0006739 | 0.0076892 | 0
| 0 | 0.0058026 | 0.066208 | 0
| 0 | 0.00074856 | 0.008541 | 0
| 0 | 0.0011675 | 0.013321 | 0
| 0 | 7.4838e-05 | 0.0008539 | 0
| 0 | 0.00087509 | 0.0099848 | 0
| 0 | 2.2437e-05 | 0.00025601 | 0
| 0.73051 | 0.0020417 | 0.023296 | 0
| 0 | 0.00089739 | 0.010239 | 0
| 0 | 0.0016524 | 0.018854 | 0
| 0 | 0.0041193 | 0.047001 | 0
| 0 | 0.00096413 | 0.011001 | 0
| 0 | 0.00063508 | 0.0072463 | 0
| 0 | 0.00073966 | 0.0084395 | 0
| 0 | 0.00087378 | 0.0099698 | 0
| 0 | 0.0010119 | 0.011546 | 0
| 0 | 0.0023971 | 0.02735 | 0
| 0 | 0.0027106 | 0.030928 | 0
| 0 | 0.0038527 | 0.04396 | 0
| 0 | 0.0021041 | 0.024008 | 0
| 0 | 0.00027593 | 0.0031484 | 0
| 0 | 0.001484 | 0.016933 | 0
| 0 | 0.0017449 | 0.019909 | 0
| 0 | 0.00064863 | 0.0074009 | 0
| 0 | 0.0033549 | 0.03828 | 0
| 0 | 0.0012041 | 0.013739 | 0
| 0 | 0.0015134 | 0.017268 | 0
| 0 | 0.00013419 | 0.0015311 | 0
| 0 | 0.00054791 | 0.0062516 | 0
| 0 | 0.0023928 | 0.027302 | 0
| 0 | 0.00032798 | 0.0037422 | 0
| 0 | 0.0060153 | 0.068635 | 0
| 0 | 0.00022357 | 0.002551 | 0
| 0 | 0.0011625 | 0.013264 | 0
| 0 | 0.0044036 | 0.050245 | 0
| 0 | 0.004204 | 0.047967 | 0
| 0 | 0.0021142 | 0.024123 | 0
| 0 | 0.0040567 | 0.046287 | 0
| 0 | 0.0070409 | 0.080336 | 0
| 0 | 0.00033489 | 0.0038211 | 0
| 0 | 0.0017414 | 0.019869 | 0
| 0 | 0.0029767 | 0.033964 | 0
| 0 | 0.0071129 | 0.081158 | 0
| 0 | 0.0026784 | 0.03056 | 0
| 0 | 0.0034968 | 0.039899 | 0
| 0 | 0.0080839 | 0.092237 | 0
| 0 | 0.00071379 | 0.0081444 | 0
| 0 | 0.0012187 | 0.013905 | 0
| 0 | 0.0006352 | 0.0072476 | 0
| 0 | 0.0029118 | 0.033224 | 0
| 0 | 0.0037175 | 0.042417 | 0
| 0 | 0.0012585 | 0.014359 | 0
| 0 | 0.0015069 | 0.017194 | 0
| 0 | 0.0021148 | 0.02413 | 0
| 0 | 0.0012651 | 0.014435 | 0
| 0 | 0.0016727 | 0.019085 | 0
| 0 | 3.7081e-05 | 0.00042309 | 0
| 0 | 0.0016659 | 0.019008 | 0
| 0 | 0.00073386 | 0.0083733 | 0
| 0 | 0.00048888 | 0.0055781 | 0
| 0 | 0.0059769 | 0.068196 | 0
| 0 | 0.0026511 | 0.03025 | 0
| 0 | 0.00054044 | 0.0061664 | 0
| 0 | 0.00075497 | 0.0086143 | 0
| 0.095885 | 4.8106e-05 | 0.00054889 | 0
| 0 | 2.22e-05 | 0.0002533 | 0
| 0 | 0.0028563 | 0.03259 | 0
| 0 | 0.0013921 | 0.015884 | 0
| 0 | 0.0028616 | 0.032651 | 0
| 0 | 0.0028319 | 0.032312 | 0
| 0 | 0.0015304 | 0.017461 | 0
| 0 | 0.0017936 | 0.020465 | 0
| 0 | 0.0010863 | 0.012395 | 0
| 0 | 0.0044588 | 0.050875 | 0
| 0 | 0.00068722 | 0.0078412 | 0
| 0 | 0.00083494 | 0.0095267 | 0
| 0 | 0.0026539 | 0.030282 | 0
| 0 | 0.001411 | 0.0161 | 0
| 0 | 0.0014474 | 0.016514 | 0
| 0 | 0.012693 | 0.14482 | 0
| 0 | 0.00019193 | 0.0021899 | 0
| 0 | 0.0010149 | 0.01158 | 0
| 0 | 8.8555e-05 | 0.0010104 | 0
| 0 | 0.0015803 | 0.018031 | 0
| 0 | 0.0016599 | 0.01894 | 0
| 0 | 0.0010843 | 0.012372 | 0
| 0 | 0.00014014 | 0.001599 | 0
| 0 | 0.001652 | 0.018849 | 0
| 0 | 0.0019593 | 0.022356 | 0
| 0 | 0.0014121 | 0.016112 | 0
| 0 | 0.0044569 | 0.050853 | 0
| 0 | 0.0051375 | 0.058618 | 0
| 0 | 0.0013929 | 0.015893 | 0
| 0 | 0.0020008 | 0.022829 | 0
| 0 | 0.0021222 | 0.024215 | 0
| 0 | 0.0018126 | 0.020681 | 0
| 0 | 0.0038458 | 0.043881 | 0
| 0 | 0.00044203 | 0.0050436 | 0
| 0 | 0.0054586 | 0.062283 | 0
| 0 | 0.0019813 | 0.022606 | 0
| 0 | 0.0038775 | 0.044243 | 0
| 0.052233 | 0.0034832 | 0.039743 | 0
| 0 | 0.0019411 | 0.022148 | 0
| 0 | 0.0012877 | 0.014692 | 0
| 0 | 0.00033097 | 0.0037763 | 0
| 0 | 0.00082188 | 0.0093776 | 0
| 0 | 0.0016547 | 0.01888 | 0
| 0 | 0.0024924 | 0.028438 | 0
| 0 | 0.00067635 | 0.0077172 | 0
| 0 | 0.003087 | 0.035222 | 0
| 0 | 0.0018409 | 0.021005 | 0
| 0 | 0.00078627 | 0.0089713 | 0
| 0 | 0.00030862 | 0.0035214 | 0
| 0 | 0.00040412 | 0.0046111 | 0
| 0 | 0.0033871 | 0.038647 | 0
| 0 | 0.00067952 | 0.0077533 | 0
| 0 | 0.00013222 | 0.0015086 | 0
| 0 | 0.00039659 | 0.0045251 | 0
| 0 | 0.001858 | 0.0212 | 0
| 0 | 0.00015422 | 0.0017597 | 0
| 0 | 0.00059475 | 0.0067862 | 0
| 0 | 0.0011687 | 0.013335 | 0
| 0 | 0.0028631 | 0.032668 | 0
| 0 | 0.0031236 | 0.03564 | 0
| 0 | 0.0094027 | 0.10729 | 0
| 0 | 0.0032846 | 0.037478 | 0
| 0 | 0.00022018 | 0.0025123 | 0
| 0 | 0.00011009 | 0.0012561 | 0
| 0 | 0.0037062 | 0.042288 | 0
| 0 | 2.3473e-05 | 0.00026783 | 0
| 0 | 0.0034989 | 0.039922 | 0
| 0 | 0.0036234 | 0.041343 | 0
| 0 | 0.00065275 | 0.0074478 | 0
| 0 | 0.001078 | 0.0123 | 0
| 0 | 0.0045905 | 0.052378 | 0
| 0 | 0.00076996 | 0.0087852 | 0
| 0 | 0.0010266 | 0.011713 | 0
| 0 | 0.00074789 | 0.0085334 | 0
| 0 | 0.00067454 | 0.0076965 | 0
| 0 | 0.0044707 | 0.05101 | 0
| 0 | 0.001802 | 0.02056 | 0
| 0 | 0.0011285 | 0.012876 | 0
| 0 | 0.0030555 | 0.034863 | 0
| 0 | 0.0019123 | 0.021819 | 0
| 0 | 0.0015165 | 0.017304 | 0
| 0 | 0.0026988 | 0.030794 | 0
| 0 | 0.0019706 | 0.022484 | 0
| 0 | 0.0023953 | 0.02733 | 0
| 0 | 0.001267 | 0.014457 | 0
| 0 | 0.0019958 | 0.022772 | 0
| 0 | 0.0075566 | 0.086221 | 0
| 1.0122 | 0.0042496 | 0.048488 | 0
| 0 | 0.00065883 | 0.0075173 | 0
| 0 | 0.0021226 | 0.024219 | 0
| 0 | 0.0015587 | 0.017785 | 0
| 0 | 0.0038631 | 0.044079 | 0
| 0 | 0.003172 | 0.036193 | 0
| 0 | 0.0016005 | 0.018262 | 0
| 0 | 0.0026815 | 0.030595 | 0
| 0 | 0.00084343 | 0.0096235 | 0
| 0 | 0.003651 | 0.041658 | 0
| 0 | 0.0014019 | 0.015996 | 0
| 0 | 0.0013386 | 0.015273 | 0
| 0 | 0.0022485 | 0.025655 | 0
| 0.42782 | 0.000438 | 0.0049976 | 0
| 0 | 0.0033607 | 0.038346 | 0
| 0.49141 | 0.0043124 | 0.049205 | 0
| 0 | 0.0011528 | 0.013154 | 0
| 0 | 0.0015541 | 0.017732 | 0
| 0 | 0.00028453 | 0.0032465 | 0
| 0 | 0.00075868 | 0.0086565 | 0
| 0 | 0.00056882 | 0.0064903 | 0
| 0 | 0.0020272 | 0.023131 | 0
| 0 | 0.0057097 | 0.065148 | 0
| 0 | 0.0026244 | 0.029944 | 0
| 0 | 0.0023181 | 0.02645 | 0
| 0 | 0.002063 | 0.023539 | 0
| 0 | 0.0047158 | 0.053807 | 0
| 0 | 0.0015015 | 0.017132 | 0
| 0 | 0.0017055 | 0.01946 | 0
| 0 | 0.0017774 | 0.020281 | 0
| 0 | 0.0007095 | 0.0080954 | 0
| 0 | 0.00061917 | 0.0070647 | 0
| 0 | 0.002622 | 0.029917 | 0
| 0 | 0.0004807 | 0.0054848 | 0
| 0 | 0.0049231 | 0.056173 | 0
| 0 | 2.1839e-05 | 0.00024918 | 0
| 0.46803 | 0.0044185 | 0.050415 | 0
| 0 | 0.00084066 | 0.0095919 | 0
| 0 | 0.0025072 | 0.028607 | 0
| 0 | 2.183e-05 | 0.00024908 | 0
| 0 | 0.0018628 | 0.021255 | 0
| 1.2154 | 0.003078 | 0.03512 | 0
| 0 | 0.0025866 | 0.029513 | 0
| 0 | 0.0012293 | 0.014026 | 0
| 0 | 0.0016 | 0.018256 | 0
| 0 | 0.001643 | 0.018747 | 0
| 0 | 0.0031077 | 0.035459 | 0
| 0 | 0.0036707 | 0.041883 | 0
| 1.4195 | 0.012272 | 0.14003 | 0
| 0 | 0.0015694 | 0.017907 | 0
| 0 | 0.0019014 | 0.021695 | 0
| 0 | 0.00040678 | 0.0046414 | 0
| 0 | 0.002506 | 0.028594 | 0
| 0 | 0.0025494 | 0.029089 | 0
| 1.759 | 0.0096088 | 0.10964 | 0
| 0 | 0.00093685 | 0.010689 | 0
| 0 | 0.0028539 | 0.032563 | 0
| 0 | 0.0027229 | 0.031069 | 0
| 0.089426 | 0.00050085 | 0.0057147 | 0
| 0 | 2.1769e-05 | 0.00024838 | 0
| 0 | 0.0017632 | 0.020118 | 0
| 0 | 0.0016027 | 0.018287 | 0
| 0 | 0.0015587 | 0.017785 | 0
| 0 | 0.0037184 | 0.042426 | 0
| 0 | 0.0052836 | 0.060285 | 0
| 0 | 0.00078255 | 0.0089289 | 0
| 0 | 0.0059465 | 0.06785 | 0
| 0 | 0.010492 | 0.11971 | 0
| 0 | 0.0011729 | 0.013383 | 0
| 0 | 0.0043886 | 0.050074 | 0
| 0 | 0.0030752 | 0.035088 | 0
| 0 | 0.001295 | 0.014776 | 0
| 0.13818 | 0.0034292 | 0.039128 | 0
| 0 | 0.0022427 | 0.02559 | 0
| 0 | 0.0016565 | 0.018901 | 0
| 0 | 0.0011608 | 0.013245 | 0
| 0 | 0.0040503 | 0.046213 | 0
| 0 | 0.002571 | 0.029335 | 0
| 0 | 0.0012692 | 0.014482 | 0
| 0 | 0.00084608 | 0.0096538 | 0
| 0 | 9.4006e-05 | 0.0010726 | 0
| 0.44735 | 0.0016342 | 0.018647 | 0
| 0 | 0.0016047 | 0.01831 | 0
| 0 | 0.0041563 | 0.047423 | 0
| 0 | 0.0025042 | 0.028573 | 0
| 0 | 0.00012278 | 0.001401 | 0
| 0 | 0.0016106 | 0.018376 | 0
| 0 | 0.0046142 | 0.052648 | 0
| 0 | 0.0055239 | 0.063028 | 0
| 0 | 0.0032698 | 0.037309 | 0
| 0 | 0.0011909 | 0.013588 | 0
| 0 | 0.0046401 | 0.052943 | 0
| 0 | 0.00080094 | 0.0091387 | 0
| 0 | 0.0029041 | 0.033136 | 0
| 0 | 0.0017026 | 0.019426 | 0
| 0 | 0.0032677 | 0.037285 | 0
| 0 | 0.0042406 | 0.048385 | 0
| 0 | 0.0013846 | 0.015799 | 0
| 4.427 | 0.013348 | 0.1523 | 0
| 0 | 0.0011177 | 0.012753 | 0
| 0 | 0.0036921 | 0.042127 | 0
| 0 | 0.00094441 | 0.010776 | 0
| 0 | 0.0012685 | 0.014474 | 0
| 0.015054 | 0.0011243 | 0.012829 | 0
| 0 | 0.00052611 | 0.0060029 | 0
| 0 | 0.0011639 | 0.01328 | 0
| 0 | 0.00095129 | 0.010854 | 0
| 0 | 0.0021043 | 0.02401 | 0
| 0 | 0.004021 | 0.045879 | 0
| 0 | 0.0006484 | 0.0073982 | 0
| 0 | 0.0013181 | 0.015039 | 0
| 0 | 0.0017176 | 0.019598 | 0
| 0 | 0.0041248 | 0.047064 | 0
| 0 | 0.00051109 | 0.0058315 | 0
| 0 | 0.0012739 | 0.014535 | 0
| 0 | 0.0012811 | 0.014617 | 0
| 0 | 0.0035977 | 0.04105 | 0
| 0 | 0.0013167 | 0.015024 | 0
| 0 | 0.0017914 | 0.02044 | 0
| 0 | 0.0051726 | 0.059019 | 0
| 0 | 0.00023735 | 0.0027081 | 0
| 0 | 0.0011218 | 0.0128 | 0
| 0 | 0.00084851 | 0.0096815 | 0
| 0 | 0.00084851 | 0.0096815 | 0
| 0 | 0.00094911 | 0.010829 | 0
| 0 | 0.0002876 | 0.0032815 | 0
| 0 | 2.157e-05 | 0.00024611 | 0
| 0 | 0.0015023 | 0.017142 | 0
| 0 | 0.011422 | 0.13032 | 0
| 0 | 0.00039678 | 0.0045272 | 0
| 0 | 0.0021347 | 0.024357 | 0
| 0 | 0.0015055 | 0.017178 | 0
| 0 | 2.1551e-05 | 0.0002459 | 0
| 0 | 0.00064652 | 0.0073768 | 0
| 0 | 0.00017239 | 0.0019669 | 0
| 0 | 0.00013646 | 0.001557 | 0
| 0 | 0.0022408 | 0.025568 | 0
| 0 | 0.00035906 | 0.0040969 | 0
| 0 | 0.00068218 | 0.0077837 | 0
| 0 | 0.0013856 | 0.01581 | 0
| 0 | 0.0068623 | 0.078298 | 0
| 0 | 0.0060075 | 0.068546 | 0
| 0 | 0.0028077 | 0.032036 | 0
| 0 | 0.0013254 | 0.015123 | 0
| 0 | 0.0037375 | 0.042645 | 0
| 0 | 0.0003084 | 0.0035188 | 0
| 0 | 0.0011045 | 0.012602 | 0
| 0 | 0.00062396 | 0.0071194 | 0
| 0 | 0.00021508 | 0.0024541 | 0
| 0 | 0.0010391 | 0.011856 | 0
| 0.32729 | 0.0047149 | 0.053796 | 0
| 0 | 0.0030093 | 0.034336 | 0
| 0 | 0.0032921 | 0.037563 | 0
| 0 | 0.0044119 | 0.05034 | 0
| 0 | 0.0009383 | 0.010706 | 0
| 0 | 0.0016257 | 0.01855 | 0
| 0 | 5.7295e-05 | 0.00065373 | 0
| 0 | 0.0011817 | 0.013483 | 0
| 0 | 0.00047265 | 0.0053929 | 0
| 0 | 0.0019679 | 0.022454 | 0
| 0.79743 | 0.00057243 | 0.0065315 | 0
| 0 | 0.0012879 | 0.014695 | 0
| 0 | 0.0038177 | 0.04356 | 0
| 0 | 0.0030258 | 0.034525 | 0
| 0 | 0.0036695 | 0.041869 | 0
| 0 | 0.0066302 | 0.07565 | 0
| 0 | 0.007942 | 0.090618 | 0
| 0 | 0.0013336 | 0.015217 | 0
| 0 | 0.00022879 | 0.0026105 | 0
| 0 | 0.00051827 | 0.0059134 | 0
| 0 | 0.0024805 | 0.028302 | 0
| 0 | 0.00095064 | 0.010847 | 0
| 0 | 0.0031086 | 0.035469 | 0
| 0 | 0.0016435 | 0.018752 | 0
| 0 | 0.0045656 | 0.052093 | 0
| 0 | 0.0043866 | 0.050051 | 0
| 0 | 0.00081429 | 0.009291 | 0
| 0 | 0.0030636 | 0.034956 | 0
| 0 | 0.0032202 | 0.036743 | 0
| 0 | 0.00047125 | 0.005377 | 0
| 0 | 0.0024275 | 0.027697 | 0
| 0 | 0.0013063 | 0.014905 | 0
| 0 | 0.0010101 | 0.011525 | 0
| 0 | 0.0030014 | 0.034246 | 0
| 0 | 0.0026908 | 0.030702 | 0
| 0 | 0.0048174 | 0.054967 | 0
| 0 | 0.0013558 | 0.01547 | 0
| 0 | 0.0015199 | 0.017342 | 0
| 0 | 0.00089553 | 0.010218 | 0
| 0 | 0.0035876 | 0.040935 | 0
| 0 | 0.0020717 | 0.023638 | 0
| 0 | 0.0020893 | 0.023839 | 0
| 0 | 0.00064172 | 0.0073221 | 0
| 0 | 0.00027805 | 0.0031726 | 0
| 0 | 0.002595 | 0.029609 | 0
| 0 | 0.00067365 | 0.0076863 | 0
| 0 | 0.005875 | 0.067033 | 0
| 0 | 0.00089807 | 0.010247 | 0
| 0 | 0.0055484 | 0.063307 | 0
| 0 | 0.0013469 | 0.015369 | 0
| 0 | 0.0018172 | 0.020735 | 0
| 0 | 0.0018811 | 0.021464 | 0
| 0 | 0.0086902 | 0.099155 | 0
| 0 | 0.0014106 | 0.016095 | 0
| 0 | 0.00059126 | 0.0067462 | 0
| 0 | 0.0011754 | 0.013411 | 0
| 0 | 0.00033475 | 0.0038195 | 0
| 0 | 0.0031157 | 0.03555 | 0
| 0 | 0.0080412 | 0.091751 | 0
| 0 | 0.0029247 | 0.033371 | 0
| 0 | 0.00014944 | 0.0017051 | 0
| 0 | 0.0015228 | 0.017375 | 0
| 0 | 0.006496 | 0.074119 | 0
| 0 | 0.0017497 | 0.019964 | 0
| 0 | 0.0017636 | 0.020122 | 0
| 0 | 0.0021614 | 0.024662 | 0
| 0 | 0.0023639 | 0.026972 | 0
| 0 | 0.0013503 | 0.015407 | 0
| 0 | 0.00059671 | 0.0068084 | 0
| 0 | 0.0023117 | 0.026377 | 0
| 0 | 0.0043816 | 0.049994 | 0
| 0 | 0.00027693 | 0.0031598 | 0
| 0 | 0.0011432 | 0.013044 | 0
| 0 | 0.0023572 | 0.026896 | 0
| 0 | 0.0032578 | 0.037172 | 0
| 0 | 0.0035341 | 0.040325 | 0
| 0 | 0.0019584 | 0.022346 | 0
| 0 | 0.0014049 | 0.01603 | 0
| 0.006119 | 0.0066196 | 0.07553 | 0
| 0 | 0.0033622 | 0.038363 | 0
| 0 | 0.0010851 | 0.012381 | 0
| 0 | 0.001331 | 0.015187 | 0
| 0 | 0.0028718 | 0.032768 | 0
| 0 | 0.002672 | 0.030487 | 0
| 0 | 0.0050602 | 0.057737 | 0
| 0 | 0.00023739 | 0.0027086 | 0
| 0 | 0.0017623 | 0.020108 | 0
| 0 | 0.0031462 | 0.035898 | 0
| 0 | 0.00097779 | 0.011157 | 0
| 0 | 0.0026837 | 0.030621 | 0
| 0 | 0.00063707 | 0.007269 | 0
| 0 | 0.0020859 | 0.0238 | 0
| 0 | 0.00012738 | 0.0014534 | 0
| 0 | 0.00029367 | 0.0033508 | 0
| 0 | 0.0017487 | 0.019953 | 0
| 0 | 0.0050814 | 0.057979 | 0
| 0 | 0.0010608 | 0.012104 | 0
| 0 | 0.0022484 | 0.025655 | 0
| 0 | 0.0019936 | 0.022747 | 0
| 0 | 0.00085534 | 0.0097594 | 0
| 0 | 0.002983 | 0.034036 | 0
| 0 | 0.00072098 | 0.0082264 | 0
| 0 | 0.003308 | 0.037744 | 0
| 0 | 0.00057247 | 0.0065319 | 0
| 0 | 0.001159 | 0.013225 | 0
| 0 | 0.002834 | 0.032336 | 0
| 0 | 0.006077 | 0.069338 | 0
| 0 | 0.0047058 | 0.053693 | 0
| 0 | 0.001399 | 0.015962 | 0
| 0 | 0.0030734 | 0.035067 | 0
| 0 | 0.0016037 | 0.018298 | 0
| 0 | 0.0014406 | 0.016438 | 0
| 0 | 0.0012502 | 0.014265 | 0
| 0 | 0.00097607 | 0.011137 | 0
| 0 | 0.0029719 | 0.033909 | 0
| 0 | 0.0010902 | 0.012439 | 0
| 0 | 0.00081848 | 0.0093389 | 0
| 0 | 0.00064197 | 0.0073249 | 0
| 0.15747 | 0.0048021 | 0.054792 | 0
| 0 | 0.0029334 | 0.03347 | 0
| 0 | 0.0015229 | 0.017376 | 0
| 0 | 0.0019562 | 0.02232 | 0
| 0 | 0.0010573 | 0.012064 | 0
| 0 | 0.0011204 | 0.012784 | 0
| 0 | 0.006102 | 0.069624 | 0
| 0 | 0.0014303 | 0.01632 | 0
| 0 | 0.0028666 | 0.032708 | 0
| 0 | 0.00044352 | 0.0050606 | 0
| 0 | 0.00029137 | 0.0033245 | 0
| 0 | 0.001499 | 0.017103 | 0
| 0 | 0.001247 | 0.014228 | 0
| 0 | 0.0024628 | 0.028101 | 0
| 0 | 0.00033774 | 0.0038536 | 0
| 0 | 0.0010074 | 0.011494 | 0
| 0 | 2.1102e-05 | 0.00024078 | 0
| 0 | 0.0020539 | 0.023435 | 0
| 0 | 0.0042413 | 0.048393 | 0
| 0 | 0.00085811 | 0.009791 | 0
| 0 | 0.0025776 | 0.02941 | 0
| 0 | 0.0013429 | 0.015323 | 0
| 0 | 0.0014482 | 0.016524 | 0
| 0 | 0.00022494 | 0.0025666 | 0
| 0.78434 | 0.00050259 | 0.0057345 | 0
| 0 | 0.0010262 | 0.011709 | 0
| 0 | 0.0039551 | 0.045127 | 0
| 0 | 0.00015455 | 0.0017634 | 0
| 0 | 0.0041354 | 0.047185 | 0
| 0 | 0.0043968 | 0.050168 | 0
| 0 | 0.0031254 | 0.035661 | 0
| 0.48648 | 0.00017909 | 0.0020435 | 0
| 0 | 0.00085678 | 0.0097759 | 0
| 0 | 0.0038335 | 0.04374 | 0
| 0 | 0.0012424 | 0.014176 | 0
| 0 | 0.00038249 | 0.0043643 | 0
| 0 | 0.00052625 | 0.0060045 | 0
| 0 | 2.1046e-05 | 0.00024014 | 0
| 0 | 0.0065306 | 0.074514 | 0
| 0 | 0.0029668 | 0.033851 | 0
| 0 | 0.0016307 | 0.018606 | 0
| 0.18929 | 0.00031559 | 0.0036009 | 0
| 0 | 0.0009045 | 0.01032 | 0
| 0 | 0.004138 | 0.047215 | 0
| 0 | 0.0030273 | 0.034541 | 0
| 0 | 0.0017237 | 0.019667 | 0
| 0 | 0.0026415 | 0.03014 | 0
| 0 | 0.0016745 | 0.019106 | 0
| 0 | 0.0035167 | 0.040126 | 0
| 0 | 0.0022764 | 0.025974 | 0
| 0 | 0.0042016 | 0.04794 | 0
| 0 | 0.0033187 | 0.037867 | 0
| 0 | 0.0010712 | 0.012222 | 0
| 0 | 0.00064058 | 0.007309 | 0
| 0 | 0.002604 | 0.029711 | 0
| 0 | 0.0015079 | 0.017206 | 0
| 0 | 0.0024349 | 0.027782 | 0
| 0 | 0.0031834 | 0.036322 | 0
| 0 | 0.003105 | 0.035429 | 0
| 0 | 0.0038208 | 0.043595 | 0
| 0 | 0.0012305 | 0.01404 | 0
| 0 | 0.0010557 | 0.012045 | 0
| 0 | 6.2906e-05 | 0.00071776 | 0
| 0 | 0.0019639 | 0.022409 | 0
| 0 | 0.0020009 | 0.022831 | 0
| 0 | 0.0033072 | 0.037735 | 0
| 0 | 0.0031835 | 0.036324 | 0
| 0 | 0.00084823 | 0.0096783 | 0
| 0 | 0.0011584 | 0.013217 | 0
| 0 | 0.0074766 | 0.085308 | 0
| 0 | 0.0014546 | 0.016597 | 0
| 0 | 0.00089939 | 0.010262 | 0
| 0 | 0.009396 | 0.10721 | 0
| 0 | 0.00258 | 0.029438 | 0
| 0 | 0.0038256 | 0.04365 | 0
| 0 | 0.0058934 | 0.067243 | 0
| 0 | 0.0024416 | 0.027858 | 0
| 0 | 0.0021089 | 0.024062 | 0
| 0 | 0.0017274 | 0.019709 | 0
| 0 | 0.0010028 | 0.011442 | 0
| 0 | 0.0024336 | 0.027767 | 0
| 0 | 0.002067 | 0.023584 | 0
| 0 | 0.0036529 | 0.04168 | 0
| 0.19268 | 0.00041745 | 0.0047632 | 0
| 0 | 0.00012522 | 0.0014287 | 0
| 0 | 0.001746 | 0.019922 | 0
| 0 | 0.0019545 | 0.0223 | 0
| 0 | 0.0027125 | 0.03095 | 0
| 0 | 0.0023174 | 0.026442 | 0
| 0 | 0.0013102 | 0.014949 | 0
| 0 | 0.00063631 | 0.0072603 | 0
| 0 | 0.0026704 | 0.030469 | 0
| 0 | 0.0084699 | 0.096641 | 0
| 0 | 0.0017939 | 0.020468 | 0
| 0 | 0.0025587 | 0.029195 | 0
| 0 | 0.0021901 | 0.024989 | 0
| 0 | 0.0025235 | 0.028794 | 0
| 0 | 0.0014389 | 0.016418 | 0
| 0 | 0.00096272 | 0.010985 | 0
| 0 | 0.0038054 | 0.04342 | 0
| 0 | 0.0042953 | 0.04901 | 0
| 0 | 0.0016957 | 0.019348 | 0
| 0 | 2.0847e-05 | 0.00023787 | 0
| 0 | 0.0020256 | 0.023112 | 0
| 0 | 0.0026257 | 0.029959 | 0
| 0 | 0.0014586 | 0.016643 | 0
| 0 | 0.0018128 | 0.020685 | 0
| 0 | 0.0027713 | 0.03162 | 0
| 0 | 0.0030003 | 0.034233 | 0
| 0 | 0.00142 | 0.016202 | 0
| 0 | 0.0021386 | 0.024401 | 0
| 0 | 0.0027218 | 0.031056 | 0
| 0 | 0.0012078 | 0.013781 | 0
| 0 | 0.0043423 | 0.049546 | 0
| 0 | 5.2037e-05 | 0.00059374 | 0
| 0 | 0.0016163 | 0.018442 | 0
| 0 | 0.0039607 | 0.045191 | 0
| 0 | 0.0014289 | 0.016303 | 0
| 0 | 0.001262 | 0.014399 | 0
| 0 | 0.00076963 | 0.0087814 | 0
| 0 | 0.0030365 | 0.034647 | 0
| 0 | 0.0015524 | 0.017713 | 0
| 0 | 0.0019071 | 0.02176 | 0
| 0 | 8.3149e-05 | 0.00094873 | 0
| 0 | 0.0015798 | 0.018025 | 0
| 0 | 0.00050222 | 0.0057304 | 0
| 0 | 0.0013437 | 0.015332 | 0
| 0 | 2.0778e-05 | 0.00023708 | 0
| 0 | 0.0024931 | 0.028446 | 0
| 0 | 0.00083584 | 0.009537 | 0
| 0 | 0.0023059 | 0.02631 | 0
| 0 | 0.0013294 | 0.015169 | 0
| 0 | 0.0028457 | 0.03247 | 0
| 0 | 0.00090693 | 0.010348 | 0
| 0 | 0.0013915 | 0.015877 | 0
| 0 | 0.0020628 | 0.023536 | 0
| 0 | 0.0025504 | 0.0291 | 0
| 0 | 0.00040837 | 0.0046594 | 0
| 0 | 0.0029199 | 0.033316 | 0
| 0 | 0.0006642 | 0.0075785 | 0
| 0 | 0.0036322 | 0.041443 | 0
| 0 | 0.0022001 | 0.025103 | 0
| 0 | 0.0015082 | 0.017209 | 0
| 0 | 0.00081766 | 0.0093295 | 0
| 0 | 0.0041006 | 0.046788 | 0
| 0 | 0.0022608 | 0.025796 | 0
| 0 | 0.0007674 | 0.008756 | 0
| 0 | 0.0027285 | 0.031132 | 0
| 0 | 0.0015485 | 0.017668 | 0
| 0 | 0.0029861 | 0.034071 | 0
| 0 | 0.0031092 | 0.035476 | 0
| 0 | 2.7634e-05 | 0.0003153 | 0
| 0 | 0.0027183 | 0.031016 | 0
| 0 | 0.00045582 | 0.0052009 | 0
| 0 | 0.00037292 | 0.004255 | 0
| 0 | 4.1432e-05 | 0.00047274 | 0
| 0 | 0.0043808 | 0.049985 | 0
| 0 | 0.0012461 | 0.014218 | 0
| 0 | 0.0022574 | 0.025757 | 0
| 0.086784 | 0.01389 | 0.15849 | 0
| 0 | 0.0012491 | 0.014252 | 0
| 0 | 0.00037264 | 0.0042519 | 0
| 0 | 0.00066039 | 0.0075351 | 0
| 0 | 0.0065201 | 0.074395 | 0
| 0 | 0.00018972 | 0.0021647 | 0
| 0 | 0.0021247 | 0.024243 | 0
| 0 | 0.0041538 | 0.047395 | 0
| 0 | 0.0025448 | 0.029036 | 0
| 0 | 0.0017652 | 0.020141 | 0
| 0 | 0.0025718 | 0.029344 | 0
| 0 | 0.00088942 | 0.010148 | 0
| 0 | 0.0025127 | 0.02867 | 0
| 0 | 0.0016958 | 0.019349 | 0
| 0.10069 | 0.0011304 | 0.012898 | 0
| 0 | 0.0015232 | 0.01738 | 0
| 0.40498 | 0.0011372 | 0.012975 | 0
| 0 | 0.0008269 | 0.0094349 | 0
| 0 | 0.0015298 | 0.017455 | 0
| 0 | 0.0019223 | 0.021933 | 0
| 0 | 0.0019494 | 0.022243 | 0
| 0 | 0.0038226 | 0.043616 | 0
| 0 | 0.0029683 | 0.033868 | 0
| 0 | 0.0022174 | 0.0253 | 0
| 0 | 0.0015012 | 0.017129 | 0
| 0 | 0.0013152 | 0.015007 | 0
| 0 | 5.5088e-05 | 0.00062856 | 0
| 0 | 0.0014873 | 0.01697 | 0
| 0 | 0.001563 | 0.017834 | 0
| 0.071104 | 0.0019864 | 0.022665 | 0
| 0 | 0.0072708 | 0.08296 | 0
| 0.021417 | 0.00055767 | 0.006363 | 0
| 0 | 0.006359 | 0.072557 | 0
| 0 | 0.0032973 | 0.037622 | 0
| 0 | 0.0013353 | 0.015236 | 0
| 0 | 2.0649e-05 | 0.00023561 | 0
| 0 | 0.00044737 | 0.0051045 | 0
| 0 | 0.0017757 | 0.020261 | 0
| 0 | 0.0013625 | 0.015546 | 0
| 0 | 0.0017958 | 0.020491 | 0
| 0 | 0.0011043 | 0.0126 | 0
| 0 | 0.0063158 | 0.072063 | 0
| 0 | 0.0019538 | 0.022293 | 0
| 0 | 0.0011833 | 0.013501 | 0
| 0 | 0.00055722 | 0.0063578 | 0
| 0 | 0.00035078 | 0.0040023 | 0
| 0 | 0.0034738 | 0.039636 | 0
| 0 | 0.00024066 | 0.0027459 | 0
| 0 | 0.0026606 | 0.030357 | 0
| 0 | 0.0014229 | 0.016235 | 0
| 0 | 1.3746e-05 | 0.00015684 | 0
| 0 | 0.0024531 | 0.02799 | 0
| 0 | 0.0016215 | 0.018501 | 0
| 0 | 0.0026965 | 0.030767 | 0
| 0 | 0.00026791 | 0.0030568 | 0
| 0 | 0.0021149 | 0.024131 | 0
| 0 | 0.0040673 | 0.046408 | 0
| 0 | 0.00053533 | 0.0061081 | 0
| 0 | 0.0010224 | 0.011666 | 0
| 0 | 0.005393 | 0.061534 | 0
| 0 | 0.0051037 | 0.058234 | 0
| 0 | 0.00050077 | 0.0057138 | 0
| 0 | 0.0024486 | 0.027938 | 0
| 0 | 0.00079538 | 0.0090753 | 0
| 0 | 0.0015085 | 0.017212 | 0
| 0 | 0.0037845 | 0.043182 | 0
| 0 | 0.0013127 | 0.014978 | 0
| 0 | 0.0046677 | 0.053259 | 0
| 0 | 0.0032078 | 0.036601 | 0
| 0 | 0.0045712 | 0.052157 | 0
| 0 | 0.0021995 | 0.025096 | 0
| 0 | 0.0021823 | 0.0249 | 0
| 0 | 0.00074819 | 0.0085368 | 0
| 0 | 0.0080295 | 0.091617 | 0
| 0 | 0.0020957 | 0.023912 | 0
| 0 | 0.001862 | 0.021245 | 0
| 0 | 0.0038022 | 0.043383 | 0
| 0 | 0.0017041 | 0.019444 | 0
| 0 | 0.0014404 | 0.016436 | 0
| 0 | 0.0011496 | 0.013117 | 0
| 0 | 0.0013686 | 0.015615 | 0
| 0 | 0.0021713 | 0.024774 | 0
| 0 | 0.0033654 | 0.038399 | 0
| 0 | 8.2071e-06 | 9.3643e-05 | 0
| 0 | 0.0048696 | 0.055562 | 0
| 1.629 | 0.0074888 | 0.085447 | 0
| 0 | 0.0012446 | 0.014201 | 0
| 0 | 0.0013539 | 0.015448 | 0
| 0 | 0.0012716 | 0.014509 | 0
| 0 | 0.0006563 | 0.0074883 | 0
| 0 | 0.0039088 | 0.044599 | 0
| 0 | 0.0036556 | 0.041711 | 0
| 0 | 0.0040512 | 0.046225 | 0
| 0 | 0.00017079 | 0.0019487 | 0
| 0 | 0.0029641 | 0.033821 | 0
| 0 | 0.0043543 | 0.049683 | 0
| 0 | 6.1455e-05 | 0.0007012 | 0
| 0.077659 | 0.0019665 | 0.022438 | 0
| 0 | 0.00028676 | 0.003272 | 0
| 0 | 0.00065526 | 0.0074765 | 0
| 0 | 0.00081214 | 0.0092665 | 0
| 0 | 0.00081894 | 0.0093441 | 0
| 0 | 0.0027543 | 0.031426 | 0
| 0 | 0.0023734 | 0.02708 | 0
| 0 | 0.0028516 | 0.032536 | 0
| 0 | 0.00085899 | 0.0098011 | 0
| 0 | 0.0023721 | 0.027066 | 0
| 0 | 0.0047851 | 0.054598 | 0
| 0 | 0.0010019 | 0.011432 | 0
| 0 | 0.0054536 | 0.062226 | 0
| 0 | 0.0014311 | 0.016328 | 0
| 0 | 0.00034071 | 0.0038876 | 0
| 0 | 0.0033559 | 0.038291 | 0
| 0 | 0.00073577 | 0.0083951 | 0
| 0 | 0.00015668 | 0.0017878 | 0
| 0 | 0.00077644 | 0.0088592 | 0
| 0 | 0.0017365 | 0.019813 | 0
| 0 | 0.00014298 | 0.0016314 | 0
| 0 | 5.4466e-05 | 0.00062146 | 0
| 0 | 0.0047791 | 0.05453 | 0
| 0 | 0.00016815 | 0.0019186 | 0
| 0 | 0.00044927 | 0.0051261 | 0
| 0 | 0.00023483 | 0.0026794 | 0
| 0 | 2.0417e-05 | 0.00023296 | 0
| 0 | 0.0002586 | 0.0029506 | 0
| 0 | 0.0013134 | 0.014985 | 0
| 0 | 0.002157 | 0.024612 | 0
| 0 | 0.0015171 | 0.01731 | 0
| 0 | 0.00087072 | 0.009935 | 0
| 0 | 0.0024489 | 0.027942 | 0
| 0.034381 | 0.0011632 | 0.013272 | 0
| 0 | 0.0029045 | 0.03314 | 0
| 0 | 0.0012786 | 0.014589 | 0
| 0 | 0.0021627 | 0.024676 | 0
| 0 | 0.0011765 | 0.013424 | 0
| 0 | 0.0024481 | 0.027932 | 0
| 0 | 8.1571e-05 | 0.00093073 | 0
| 0 | 0.0012231 | 0.013956 | 0
| 0 | 0.0016376 | 0.018686 | 0
| 0 | 0.00059116 | 0.0067452 | 0
| 0 | 0.0047334 | 0.054008 | 0
| 0 | 0.00097764 | 0.011155 | 0
| 0 | 0.00011541 | 0.0013169 | 0
| 0 | 0.0010587 | 0.01208 | 0
| 0 | 0.0017509 | 0.019977 | 0
| 0 | 0.0020698 | 0.023616 | 0
| 0 | 0.0060803 | 0.069376 | 0
| 0.0080205 | 0.0032767 | 0.037388 | 0
| 0 | 0.00050877 | 0.005805 | 0
| 0 | 0.00077999 | 0.0088997 | 0
| 0 | 0.00084235 | 0.0096112 | 0
| 0 | 0.0016749 | 0.019111 | 0
| 0 | 0.0024369 | 0.027805 | 0
| 0 | 0.0033691 | 0.038441 | 0
| 0 | 0.0063898 | 0.072907 | 0
| 0 | 0.00056939 | 0.0064968 | 0
| 0 | 0.0037105 | 0.042337 | 0
| 0.33335 | 0.0020331 | 0.023198 | 0
| 0 | 0.001484 | 0.016933 | 0
| 0 | 0.00011519 | 0.0013144 | 0
| 0 | 0.00016261 | 0.0018553 | 0
| 0 | 0.00096003 | 0.010954 | 0
| 0 | 0.00041324 | 0.004715 | 0
| 0 | 0.00062312 | 0.0071098 | 0
| 0 | 0.00020993 | 0.0023954 | 0
| 0 | 0.002614 | 0.029826 | 0
| 0 | 0.0040696 | 0.046434 | 0
| 0 | 0.00058234 | 0.0066445 | 0
| 0 | 0.001185 | 0.013521 | 0
| 0 | 0.0012795 | 0.014599 | 0
| 0 | 0.0016045 | 0.018307 | 0
| 0 | 0.0044004 | 0.050208 | 0
| 0 | 0.0025386 | 0.028966 | 0
| 0 | 0.0013912 | 0.015873 | 0
| 0 | 0.00042645 | 0.0048657 | 0
| 0 | 0.0013601 | 0.015519 | 0
| 0.036812 | 0.00094039 | 0.01073 | 0
| 0 | 0.00077936 | 0.0088925 | 0
| 0 | 0.0012042 | 0.01374 | 0
| 0 | 0.0035447 | 0.040444 | 0
| 0 | 0.0024728 | 0.028214 | 0
| 0 | 0.00022992 | 0.0026234 | 0
| 0.046115 | 0.0070321 | 0.080236 | 0
| 0 | 0.0015612 | 0.017813 | 0
| 0 | 1.3513e-05 | 0.00015418 | 0
| 0 | 0.00078374 | 0.0089424 | 0
| 0 | 0.0040266 | 0.045943 | 0
| 0 | 0.0012768 | 0.014568 | 0
| 0 | 0.0012767 | 0.014567 | 0
| 0 | 0.00038504 | 0.0043933 | 0
| 0 | 0.0021074 | 0.024046 | 0
| 0 | 0.0056059 | 0.063963 | 0
| 0 | 0.0036732 | 0.041911 | 0
| 0 | 0.0031802 | 0.036286 | 0
| 0 | 3.3759e-05 | 0.00038519 | 0
| 0 | 0.00024305 | 0.0027732 | 0
| 0 | 0.0020452 | 0.023336 | 0
| 0 | 0.001701 | 0.019408 | 0
| 0 | 0.0092306 | 0.10532 | 0
| 0 | 0.0014642 | 0.016706 | 0
| 0 | 0.0014506 | 0.016552 | 0
| 0 | 0.0024085 | 0.027482 | 0
| 0 | 0.001467 | 0.016739 | 0
| 0 | 0.0019289 | 0.022009 | 0
| 0 | 0.0056721 | 0.064719 | 0
| 0 | 0.003817 | 0.043552 | 0
| 0 | 0.0013351 | 0.015234 | 0
| 0 | 0.0075697 | 0.08637 | 0
| 0 | 0.0020968 | 0.023924 | 0
| 0 | 0.0011528 | 0.013154 | 0
| 0.055521 | 5.0559e-05 | 0.00057687 | 0
| 0 | 0.0021368 | 0.024381 | 0
| 0 | 0.00043802 | 0.0049978 | 0
| 0 | 0.00058556 | 0.0066813 | 0
| 0 | 0.00091625 | 0.010454 | 0
| 0 | 0.0055849 | 0.063723 | 0
| 0 | 0.00016166 | 0.0018445 | 0
| 0 | 0.00099005 | 0.011296 | 0
| 2.0812 | 0.0015288 | 0.017444 | 0
| 0 | 0.0018588 | 0.021209 | 0
| 0 | 0.0015556 | 0.017749 | 0
| 0 | 0.0035955 | 0.041025 | 0
| 0 | 0.0030097 | 0.03434 | 0
| 0 | 0.00097627 | 0.011139 | 0
| 0 | 0.0016492 | 0.018818 | 0
| 0 | 0.0024704 | 0.028188 | 0
| 0.19141 | 0.0018642 | 0.021271 | 0
| 0 | 7.7385e-05 | 0.00088296 | 0
| 0 | 0.0024628 | 0.028101 | 0
| 0 | 0.00042728 | 0.0048753 | 0
| 0 | 0.00022195 | 0.0025324 | 0
| 0 | 0.0051246 | 0.058472 | 0
| 0 | 2.0174e-05 | 0.00023019 | 0
| 0 | 0.0024106 | 0.027505 | 0
| 0 | 0.0033419 | 0.038131 | 0
| 0 | 0.0017078 | 0.019486 | 0
| 0 | 0.0023398 | 0.026698 | 0
| 0 | 0.0063803 | 0.072799 | 0
| 0 | 0.0028708 | 0.032755 | 0
| 0 | 0.0015933 | 0.018179 | 0
| 0 | 0.0021607 | 0.024653 | 0
| 0 | 0.0036601 | 0.041762 | 0
| 0 | 0.0034816 | 0.039725 | 0
| 0 | 0.00075945 | 0.0086653 | 0
| 0 | 0.0013508 | 0.015413 | 0
| 0 | 0.0010886 | 0.012421 | 0
| 0 | 0.0083656 | 0.095451 | 0
| 0 | 0.00039627 | 0.0045214 | 0
| 0 | 0.0020349 | 0.023218 | 0
| 0 | 0.0036042 | 0.041124 | 0
| 0 | 0.0033824 | 0.038593 | 0
| 0 | 0.0040161 | 0.045823 | 0
| 0 | 0.0040394 | 0.04609 | 0
| 0 | 0.0026737 | 0.030507 | 0
| 0 | 0.0011672 | 0.013318 | 0
| 0 | 0.00050299 | 0.0057392 | 0
| 0 | 0.0019918 | 0.022726 | 0
| 0.23725 | 0.0007578 | 0.0086465 | 0
| 0 | 0.0023606 | 0.026934 | 0
| 0 | 0.0033925 | 0.038709 | 0
| 0 | 0.0005698 | 0.0065014 | 0
| 0 | 0.0028755 | 0.03281 | 0
| 0 | 0.00091151 | 0.0104 | 0
| 0 | 0.0026937 | 0.030735 | 0
| 0 | 0.0021708 | 0.024769 | 0
| 0 | 0.0023307 | 0.026594 | 0
| 0 | 0.0016073 | 0.018339 | 0
| 0 | 0.0017511 | 0.01998 | 0
| 0 | 0.0042991 | 0.049052 | 0
| 0 | 0.00060262 | 0.0068759 | 0
| 0 | 0.0017744 | 0.020245 | 0
| 0 | 0.00041512 | 0.0047366 | 0
| 0 | 0.0017601 | 0.020083 | 0
| 0 | 6.0231e-05 | 0.00068723 | 0
| 0 | 0.0035867 | 0.040924 | 0
| 0 | 0.0025286 | 0.028852 | 0
| 0 | 0.00096304 | 0.010988 | 0
| 0 | 0.0033504 | 0.038228 | 0
| 0 | 0.00061519 | 0.0070193 | 0
| 0 | 0.0017787 | 0.020295 | 0
| 0 | 0.0016583 | 0.018921 | 0
| 0 | 0.0019787 | 0.022577 | 0
| 0 | 0.00059485 | 0.0067873 | 0
| 0 | 0.0034219 | 0.039044 | 0
| 0 | 0.0011161 | 0.012735 | 0
| 0 | 0.0029272 | 0.033399 | 0
| 0 | 0.00043435 | 0.0049559 | 0
| 0 | 0.00096221 | 0.010979 | 0
| 0 | 0.00092535 | 0.010558 | 0
| 0 | 0.00014029 | 0.0016007 | 0
| 0 | 0.0020775 | 0.023704 | 0
| 0 | 0.001229 | 0.014023 | 0
| 0 | 0.0019033 | 0.021717 | 0
| 0 | 0.0027513 | 0.031392 | 0
| 0 | 0.0010831 | 0.012358 | 0
| 0 | 0.0032584 | 0.037179 | 0
| 0 | 0.0015925 | 0.01817 | 0
| 0 | 0.0050411 | 0.057518 | 0
| 0 | 0.0027575 | 0.031464 | 0
| 0 | 0.0034646 | 0.039532 | 0
| 0 | 1.3351e-05 | 0.00015234 | 0
| 0 | 0.00079432 | 0.0090632 | 0
| 0 | 0.00062396 | 0.0071193 | 0
| 0 | 0.0033221 | 0.037906 | 0
| 0 | 0.00028012 | 0.0031962 | 0
| 0 | 4.0017e-05 | 0.00045659 | 0
| 0 | 0.0047818 | 0.054561 | 0
| 0 | 0.0015538 | 0.017729 | 0
| 0 | 0.00079356 | 0.0090545 | 0
| 0 | 0.00011336 | 0.0012935 | 0
| 0 | 0.0025397 | 0.028978 | 0
| 0 | 0.002519 | 0.028742 | 0
| 0 | 0.0011427 | 0.013038 | 0
| 0 | 0.0013891 | 0.01585 | 0
| 0 | 0.001499 | 0.017103 | 0
| 0 | 0.00031972 | 0.0036481 | 0
| 0 | 0.0063839 | 0.07284 | 0
| 0 | 0.0029165 | 0.033277 | 0
| 0 | 0.00053932 | 0.0061537 | 0
| 0 | 6.6575e-06 | 7.5962e-05 | 0
| 0 | 0.0073644 | 0.084028 | 0
| 0.30133 | 0.0021193 | 0.024182 | 0
| 0 | 0.0011411 | 0.01302 | 0
| 0 | 0.00069864 | 0.0079714 | 0
| 0 | 0.0039056 | 0.044562 | 0
| 0 | 0.005402 | 0.061637 | 0
| 0 | 0.0016759 | 0.019122 | 0
| 0 | 0.0026597 | 0.030347 | 0
| 0 | 0.0012634 | 0.014415 | 0
| 0 | 0.0033311 | 0.038007 | 0
| 0 | 0.0022696 | 0.025896 | 0
| 0 | 9.9687e-05 | 0.0011374 | 0
| 0 | 0.0018272 | 0.020848 | 0
| 0 | 0.00023253 | 0.0026532 | 0
| 0 | 3.9855e-05 | 0.00045475 | 0
| 0 | 0.0090636 | 0.10342 | 0
| 0 | 0.00242 | 0.027613 | 0
| 0 | 0.0038896 | 0.044381 | 0
| 0 | 0.00066328 | 0.007568 | 0
| 0 | 0.00037142 | 0.0042379 | 0
| 0 | 0.005319 | 0.06069 | 0
| 0 | 0.00056369 | 0.0064317 | 0
| 0 | 0.0017938 | 0.020467 | 0
| 0 | 0.000557 | 0.0063554 | 0
| 0 | 0.0074465 | 0.084965 | 0
| 0 | 0.00067694 | 0.0077239 | 0
| 0 | 0.00019227 | 0.0021938 | 0
| 0 | 0.00081537 | 0.0093034 | 0
| 0 | 0.00043751 | 0.004992 | 0
| 0 | 0.0030422 | 0.034711 | 0
| 0 | 0.0020578 | 0.023479 | 0
| 0 | 0.00058971 | 0.0067286 | 0
| 0 | 0.00025837 | 0.002948 | 0
| 0 | 0.0019475 | 0.022221 | 0
| 0 | 0.0023844 | 0.027206 | 0
| 0 | 0.0035572 | 0.040588 | 0
| 0 | 0.0017415 | 0.019871 | 0
| 0 | 0.0016752 | 0.019114 | 0
| 0 | 0.0010658 | 0.012161 | 0
| 0 | 0.0010721 | 0.012233 | 0
| 0 | 0.0010256 | 0.011702 | 0
| 0 | 0.0020247 | 0.023101 | 0
| 0 | 0.0024477 | 0.027928 | 0
| 0 | 0.00042668 | 0.0048684 | 0
| 0 | 0.0043594 | 0.049741 | 0
| 0 | 0.0047989 | 0.054755 | 0
| 0.031092 | 0.0025794 | 0.029431 | 0
| 0 | 0.0012401 | 0.014149 | 0
| 0 | 0.001607 | 0.018336 | 0
| 0 | 7.9333e-05 | 0.00090519 | 0
| 0 | 0.0034112 | 0.038922 | 0
| 0 | 0.00045612 | 0.0052043 | 0
| 0 | 0.0028487 | 0.032504 | 0
| 0 | 1.9828e-05 | 0.00022624 | 0
| 0 | 0.0044249 | 0.050489 | 0
| 0 | 0.0044541 | 0.050821 | 0
| 0 | 0.00056498 | 0.0064464 | 0
| 0 | 0.0009448 | 0.01078 | 0
| 0 | 0.0020215 | 0.023065 | 0
| 0 | 9.9093e-05 | 0.0011307 | 0
| 0 | 0.0013011 | 0.014845 | 0
| 0 | 0.0045365 | 0.051762 | 0
| 0 | 0.0032454 | 0.03703 | 0
| 0 | 0.00043577 | 0.0049721 | 0
| 0 | 0.00062059 | 0.0070809 | 0
| 0 | 0.00052814 | 0.0060261 | 0
| 0 | 0.0028255 | 0.032239 | 0
| 0 | 0.0024655 | 0.028132 | 0
| 0 | 0.0056342 | 0.064286 | 0
| 0 | 0.00029025 | 0.0033117 | 0
| 0.037398 | 0.0011854 | 0.013525 | 0
| 0 | 0.0024268 | 0.02769 | 0
| 0 | 0.00013846 | 0.0015799 | 0
| 0 | 0.0052161 | 0.059515 | 0
| 0 | 0.00148 | 0.016887 | 0
| 0 | 0.00054718 | 0.0062433 | 0
| 0 | 0.0014239 | 0.016247 | 0
| 0 | 0.00013842 | 0.0015794 | 0
| 0 | 0.0025013 | 0.02854 | 0
| 0 | 0.00017795 | 0.0020304 | 0
| 0 | 0.0010017 | 0.011429 | 0
| 0 | 0.002659 | 0.030339 | 0
| 0 | 0.0015353 | 0.017518 | 0
| 0 | 9.8842e-05 | 0.0011278 | 0
| 0 | 1.9763e-05 | 0.0002255 | 0
| 0 | 0.0020947 | 0.023901 | 0
| 0 | 0.0014228 | 0.016234 | 0
| 0 | 0.0012449 | 0.014204 | 0
| 0 | 0.0016201 | 0.018486 | 0
| 0 | 0.00056632 | 0.0064617 | 0
| 0 | 0.002443 | 0.027875 | 0
| 0 | 0.009837 | 0.11224 | 0
| 0 | 0.0055944 | 0.063832 | 0
| 0 | 7.8978e-05 | 0.00090114 | 0
| 0 | 0.0027772 | 0.031687 | 0
| 0 | 0.0042246 | 0.048203 | 0
| 0 | 0.00088817 | 0.010134 | 0
| 0 | 0.00070724 | 0.0080696 | 0
| 0 | 0.0034795 | 0.039701 | 0
| 0 | 0.0066004 | 0.075311 | 0
| 0 | 0.0017956 | 0.020487 | 0
| 0 | 0.0024126 | 0.027528 | 0
| 0 | 0.0015973 | 0.018225 | 0
| 0 | 0.0028177 | 0.03215 | 0
| 0 | 0.0013859 | 0.015813 | 0
| 0 | 0.0052852 | 0.060304 | 0
| 0 | 0.0012347 | 0.014088 | 0
| 0 | 0.0011493 | 0.013114 | 0
| 0 | 0.0067512 | 0.077031 | 0
| 0 | 0.0047388 | 0.05407 | 0
| 0 | 0.0038916 | 0.044404 | 0
| 0 | 1.968e-05 | 0.00022455 | 0
| 0 | 0.0017317 | 0.019758 | 0
| 4.6273 | 0.012791 | 0.14594 | 0
| 0 | 0.00033449 | 0.0038165 | 0
| 0 | 0.0017048 | 0.019451 | 0
| 0 | 0.0011946 | 0.01363 | 0
| 0 | 0.0015834 | 0.018067 | 0
| 0 | 0.0083617 | 0.095407 | 0
| 0 | 0.0049816 | 0.05684 | 0
| 0 | 0.0017627 | 0.020112 | 0
| 0 | 0.0035053 | 0.039995 | 0
| 0 | 0.00070908 | 0.0080906 | 0
| 0.078732 | 0.0033136 | 0.037808 | 0
| 0 | 0.0022785 | 0.025998 | 0
| 0 | 0.00031753 | 0.003623 | 0
| 0 | 0.0017805 | 0.020316 | 0
| 0 | 0.0042643 | 0.048655 | 0
| 0 | 0.0011779 | 0.01344 | 0
| 0 | 0.0022113 | 0.025231 | 0
| 0 | 0.0028197 | 0.032173 | 0
| 0 | 0.0010107 | 0.011533 | 0
| 0 | 0.0036404 | 0.041537 | 0
| 0 | 9.8122e-05 | 0.0011196 | 0
| 0 | 0.001269 | 0.01448 | 0
| 0 | 0.00061811 | 0.0070526 | 0
| 0 | 1.9622e-05 | 0.00022388 | 0
| 0 | 0.00057536 | 0.0065649 | 0
| 0 | 0.0028504 | 0.032523 | 0
| 0 | 0.00023534 | 0.0026852 | 0
| 0 | 0.00037258 | 0.0042512 | 0
| 0 | 0.0059417 | 0.067794 | 0
| 0 | 0.0012124 | 0.013834 | 0
| 0 | 0.0017613 | 0.020097 | 0
| 0 | 0.0015096 | 0.017224 | 0
| 0 | 7.1881e-05 | 0.00082016 | 0
| 0 | 0.00017641 | 0.0020128 | 0
| 0 | 0.0027504 | 0.031382 | 0
| 0 | 0.0013849 | 0.015802 | 0
| 0 | 0.00038539 | 0.0043973 | 0
| 0 | 0.00034942 | 0.0039869 | 0
| 0 | 0.0020703 | 0.023622 | 0
| 0 | 0.00033306 | 0.0038002 | 0
| 0 | 0.001071 | 0.01222 | 0
| 0 | 0.0052807 | 0.060253 | 0
| 0 | 0.0020503 | 0.023394 | 0
| 0 | 1.9588e-05 | 0.00022349 | 0
| 0 | 0.0015996 | 0.018251 | 0
| 0 | 0.00015668 | 0.0017877 | 0
| 0 | 0.0050852 | 0.058022 | 0
| 0 | 1.9576e-05 | 0.00022336 | 0
| 0 | 0.0009394 | 0.010719 | 0
| 0 | 0.0029877 | 0.03409 | 0
| 0 | 0.0025702 | 0.029326 | 0
| 0 | 0.00036528 | 0.0041678 | 0
| 0 | 0.0014057 | 0.016039 | 0
| 0 | 0.0015218 | 0.017364 | 0
| 0 | 3.9136e-05 | 0.00044654 | 0
| 0 | 5.8667e-05 | 0.00066939 | 0
| 0 | 0.0043345 | 0.049457 | 0
| 0 | 0.0030302 | 0.034575 | 0
| 0 | 0.0010849 | 0.012378 | 0
| 0 | 0.0067562 | 0.077088 | 0
| 0 | 0.0017729 | 0.020229 | 0
| 0 | 0.0021754 | 0.024822 | 0
| 0 | 0.0011007 | 0.012559 | 0
| 0 | 0.00085318 | 0.0097348 | 0
| 0 | 0.0030206 | 0.034465 | 0
| 0 | 0.0017704 | 0.0202 | 0
| 0 | 0.0051606 | 0.058883 | 0
| 0.014067 | 3.9042e-05 | 0.00044547 | 0
| 0 | 0.0020788 | 0.023719 | 0
| 0 | 0.0037293 | 0.042551 | 0
| 0 | 0.00011711 | 0.0013362 | 0
| 0 | 0.0046053 | 0.052547 | 0
| 0 | 0.0033596 | 0.038333 | 0
| 0 | 0.00062425 | 0.0071227 | 0
| 0 | 0.00091686 | 0.010461 | 0
| 0 | 0.0022628 | 0.025818 | 0
| 0 | 0.0019017 | 0.021698 | 0
| 0 | 0.0019113 | 0.021808 | 0
| 0 | 0.0018753 | 0.021398 | 0
| 0 | 0.00017865 | 0.0020383 | 0
| 0 | 0.00048363 | 0.0055183 | 0
| 0 | 0.0031429 | 0.035861 | 0
| 0 | 0.0047508 | 0.054207 | 0
| 0 | 0.00095643 | 0.010913 | 0
| 0 | 0.00015572 | 0.0017767 | 0
| 0 | 9.7308e-06 | 0.00011103 | 0
| 0 | 0.00090814 | 0.010362 | 0
| 0 | 0.0013355 | 0.015238 | 0
| 0 | 0.0015559 | 0.017753 | 0
| 0 | 9.7242e-06 | 0.00011095 | 0
| 0 | 9.7242e-06 | 0.00011095 | 0
| 0 | 0.0018667 | 0.021299 | 0
| 0 | 0.00011666 | 0.0013311 | 0
| 0 | 0.0032457 | 0.037034 | 0
| 0 | 0.00089379 | 0.010198 | 0
| 0 | 0.0018782 | 0.02143 | 0
| 0 | 0.010174 | 0.11608 | 0
| 0 | 0.00038521 | 0.0043953 | 0
| 0 | 0.00017478 | 0.0019942 | 0
| 0 | 0.0010485 | 0.011963 | 0
| 0 | 0.00076366 | 0.0087133 | 0
| 0 | 0.0080169 | 0.091473 | 0
| 0 | 0.0022808 | 0.026024 | 0
| 0 | 0.0011451 | 0.013066 | 0
| 0 | 0.00078925 | 0.0090054 | 0
| 0 | 0.00045606 | 0.0052036 | 0
| 0 | 0.001863 | 0.021256 | 0
| 0 | 0.00023286 | 0.0026569 | 0
| 0 | 3.2342e-05 | 0.00036902 | 0
| 0 | 0.0058466 | 0.066709 | 0
| 0 | 0.0033435 | 0.038149 | 0
| 0 | 0.00077592 | 0.0088533 | 0
| 0 | 0.0012027 | 0.013722 | 0
| 0 | 0.00077587 | 0.0088527 | 0
| 0 | 0.0081778 | 0.093309 | 0
| 0 | 0.0072508 | 0.082732 | 0
| 0 | 0.001273 | 0.014525 | 0
| 0 | 0.0011081 | 0.012644 | 0
| 0 | 0.0030105 | 0.03435 | 0
| 0 | 0.0018359 | 0.020948 | 0
| 0 | 0.0020442 | 0.023324 | 0
| 0 | 0.0043789 | 0.049964 | 0
| 0 | 0.0023246 | 0.026524 | 0
| 0 | 0.001046 | 0.011935 | 0
| 0 | 0.00081194 | 0.0092642 | 0
| 0 | 0.0024336 | 0.027767 | 0
| 0 | 0.0035632 | 0.040656 | 0
| 0 | 0.0018976 | 0.021652 | 0
| 0 | 0.0021881 | 0.024966 | 0
| 0 | 0.0005228 | 0.0059651 | 0
| 0 | 0.0016103 | 0.018374 | 0
| 0 | 1.9363e-05 | 0.00022093 | 0
| 0 | 0.0014115 | 0.016105 | 0
| 0 | 0.0029783 | 0.033982 | 0
| 0 | 0.00099055 | 0.011302 | 0
| 0 | 0.0015054 | 0.017176 | 0
| 0 | 0.0048694 | 0.055559 | 0
| 0 | 0.0017668 | 0.02016 | 0
| 0 | 0.0035658 | 0.040686 | 0
| 0 | 0.00092853 | 0.010595 | 0
| 0 | 0.0027271 | 0.031117 | 0
| 0 | 0.0020693 | 0.023611 | 0
| 0 | 0.0026882 | 0.030672 | 0
| 0 | 0.00058661 | 0.0066932 | 0
| 0 | 0.0026204 | 0.029898 | 0
| 0 | 0.0002256 | 0.0025741 | 0
| 0 | 0.0013276 | 0.015148 | 0
| 0 | 0.00093431 | 0.01066 | 0
| 0 | 0.0011145 | 0.012717 | 0
| 0 | 0.0013979 | 0.01595 | 0
| 0 | 0.0035555 | 0.040569 | 0
| 0 | 0.00068826 | 0.007853 | 0
| 0 | 0.0014104 | 0.016093 | 0
| 0 | 0.00051506 | 0.0058769 | 0
| 0 | 0.0046738 | 0.053328 | 0
| 0 | 0.0019054 | 0.02174 | 0
| 0 | 0.0036305 | 0.041424 | 0
| 0 | 0.0015384 | 0.017553 | 0
| 0 | 0.0013515 | 0.015421 | 0
| 0 | 0.0027778 | 0.031695 | 0
| 0 | 0.0024838 | 0.02834 | 0
| 0 | 0.0018976 | 0.021652 | 0
| 0 | 0.0015856 | 0.018092 | 0
| 0 | 0.0012734 | 0.01453 | 0
| 0 | 0.0018327 | 0.020912 | 0
| 0 | 0.00041472 | 0.004732 | 0
| 0 | 0.0021988 | 0.025089 | 0
| 0 | 0.00019288 | 0.0022007 | 0
| 0 | 9.6423e-05 | 0.0011002 | 0
| 0 | 0.0031626 | 0.036086 | 0
| 0 | 0.0030853 | 0.035203 | 0
| 0 | 0.0013305 | 0.015181 | 0
| 0 | 0.0010702 | 0.012211 | 0
| 0 | 0.0035286 | 0.040262 | 0
| 0 | 0.0065283 | 0.074488 | 0
| 0.58098 | 0.0053005 | 0.060479 | 0
| 0 | 0.00040473 | 0.004618 | 0
| 0 | 0.00075162 | 0.008576 | 0
| 0 | 0.0019413 | 0.02215 | 0
| 0 | 0.00041752 | 0.0047639 | 0
| 0 | 0.0010212 | 0.011652 | 0
| 0 | 1.9264e-05 | 0.00021981 | 0
| 0 | 0.0010981 | 0.012529 | 0
| 0 | 0.0010402 | 0.011869 | 0
| 0 | 0.0034481 | 0.039343 | 0
| 0 | 0.0021382 | 0.024397 | 0
| 0 | 0.0024656 | 0.028132 | 0
| 0 | 0.0014531 | 0.01658 | 0
| 0 | 0.003671 | 0.041886 | 0
| 0.0072987 | 0.004303 | 0.049097 | 0
| 0 | 0.0027622 | 0.031517 | 0
| 0 | 0.00078276 | 0.0089312 | 0
| 0 | 9.6234e-05 | 0.001098 | 0
| 0 | 0.0024182 | 0.027592 | 0
| 0 | 0.0065356 | 0.074571 | 0
| 0 | 0.0029809 | 0.034012 | 0
| 0 | 0.0038395 | 0.043809 | 0
| 0 | 0.00045186 | 0.0051558 | 0
| 0 | 0.0037301 | 0.042561 | 0
| 0 | 0.0019283 | 0.022002 | 0
| 0 | 0.0021396 | 0.024413 | 0
| 0 | 0.00058294 | 0.0066514 | 0
| 0 | 0.0020877 | 0.02382 | 0
| 0 | 0.00051227 | 0.005845 | 0
| 0 | 0.0020938 | 0.023891 | 0
| 0 | 0.0019154 | 0.021855 | 0
| 0 | 0.00066896 | 0.0076329 | 0
| 0 | 0.00074888 | 0.0085447 | 0
| 0 | 0.00088314 | 0.010077 | 0
| 0 | 0.0021693 | 0.024752 | 0
| 0 | 0.0034299 | 0.039135 | 0
| 0 | 0.00030061 | 0.00343 | 0
| 0 | 0.0028268 | 0.032254 | 0
| 0 | 0.0022379 | 0.025534 | 0
| 0 | 0.0011893 | 0.013569 | 0
| 0 | 0.00067582 | 0.0077111 | 0
| 0 | 0.00036441 | 0.004158 | 0
| 0 | 0.0001854 | 0.0021154 | 0
| 0 | 0.005191 | 0.05923 | 0
| 2.6559 | 0.0015214 | 0.01736 | 0
| 0.14579 | 0.0057531 | 0.065643 | 0
| 0 | 0.0044289 | 0.050534 | 0
| 0 | 0.0031943 | 0.036447 | 0
| 0 | 0.002331 | 0.026597 | 0
| 0 | 0.0039054 | 0.04456 | 0
| 0 | 0.0011891 | 0.013568 | 0
| 0 | 0.0043604 | 0.049752 | 0
| 0 | 0.012169 | 0.13884 | 0
| 0 | 0.0010722 | 0.012233 | 0
| 0 | 0.0025588 | 0.029196 | 0
| 0 | 0.00096662 | 0.011029 | 0
| 0 | 0.0058889 | 0.067192 | 0
| 0 | 0.0016459 | 0.01878 | 0
| 0 | 0.00026794 | 0.0030572 | 0
| 0 | 0.0024876 | 0.028383 | 0
| 0 | 0.0022324 | 0.025472 | 0
| 0 | 5.1024e-05 | 0.00058218 | 0
| 0 | 0.0015876 | 0.018114 | 0
| 0 | 0.001396 | 0.015928 | 0
| 0 | 0.0083342 | 0.095093 | 0
| 0.011482 | 0.0030583 | 0.034895 | 0
| 0 | 0.0025167 | 0.028715 | 0
| 0 | 0.0021415 | 0.024434 | 0
| 0 | 0.00064968 | 0.0074128 | 0
| 0 | 0.0010316 | 0.01177 | 0
| 0 | 0.0077744 | 0.088706 | 0
| 0 | 0.0021772 | 0.024842 | 0
| 0 | 0.0022468 | 0.025635 | 0
| 0 | 0.0032585 | 0.037179 | 0
| 0 | 0.0039075 | 0.044584 | 0
| 0 | 0.0038181 | 0.043564 | 0
| 0 | 0.001928 | 0.021998 | 0
| 0 | 0.0035683 | 0.040715 | 0
| 0 | 0.00063932 | 0.0072947 | 0
| 0 | 0.00032443 | 0.0037018 | 0
| 0 | 0.0040644 | 0.046375 | 0
| 0 | 0.00073739 | 0.0084136 | 0
| 0 | 0.00045769 | 0.0052222 | 0
| 0.2904 | 0.0017926 | 0.020453 | 0
| 0 | 0.0013984 | 0.015956 | 0
| 0 | 0.0012459 | 0.014215 | 0
| 0 | 0.0010181 | 0.011617 | 0
| 0 | 0.0027645 | 0.031543 | 0
| 0 | 0.00028593 | 0.0032625 | 0
| 0 | 0.0051848 | 0.059159 | 0
| 0 | 0.00037806 | 0.0043136 | 0
| 0 | 0.0016202 | 0.018487 | 0
| 0 | 0.001477 | 0.016853 | 0
| 0 | 0.0033097 | 0.037764 | 0
| 0 | 0.0017652 | 0.020141 | 0
| 0 | 0.0016509 | 0.018837 | 0
| 0 | 0.0017715 | 0.020212 | 0
| 0 | 0.0033841 | 0.038613 | 0
| 0 | 0.00035555 | 0.0040568 | 0
| 0 | 0.0064848 | 0.073991 | 0
| 0.10157 | 0.00033644 | 0.0038388 | 0
| 0 | 0.0062146 | 0.070909 | 0
| 0 | 0.00079663 | 0.0090895 | 0
| 0 | 0.0014218 | 0.016223 | 0
| 0 | 1.9042e-05 | 0.00021727 | 0
| 0 | 0.0024497 | 0.027951 | 0
| 0 | 0.0020178 | 0.023023 | 0
| 0 | 1.9035e-05 | 0.00021719 | 0
| 0 | 0.0010785 | 0.012306 | 0
| 0.38027 | 0.0008754 | 0.0099883 | 0
| 0 | 0.0022264 | 0.025403 | 0
| 0 | 0.0069632 | 0.07945 | 0
| 0 | 0.0024666 | 0.028144 | 0
| 0 | 0.0012745 | 0.014542 | 0
| 0 | 0.0021443 | 0.024467 | 0
| 0 | 0.0021114 | 0.024091 | 0
| 0 | 0.0034618 | 0.039499 | 0
| 0 | 0.0024727 | 0.028213 | 0
| 0 | 0.00086345 | 0.0098519 | 0
| 0 | 0.0021775 | 0.024845 | 0
| 0 | 0.00036131 | 0.0041225 | 0
| 0 | 3.1693e-05 | 0.00036162 | 0
| 0 | 0.00025987 | 0.0029651 | 0
| 0 | 0.00077325 | 0.0088228 | 0
| 0 | 0.0025589 | 0.029197 | 0
| 0 | 0.0010448 | 0.011921 | 0
| 0 | 0.0016398 | 0.018711 | 0
| 0 | 0.0036272 | 0.041387 | 0
| 0 | 0.00049369 | 0.005633 | 0
| 0 | 0.0010772 | 0.012291 | 0
| 0 | 5.6955e-05 | 0.00064985 | 0
| 0 | 0.0096183 | 0.10974 | 0
| 0 | 0.0076245 | 0.086995 | 0
| 0 | 0.00041127 | 0.0046925 | 0
| 0 | 0.0016005 | 0.018262 | 0
| 0 | 0.0029603 | 0.033777 | 0
| 0 | 0.00047745 | 0.0054478 | 0
| 0 | 0.0032635 | 0.037236 | 0
| 0 | 0.00043616 | 0.0049766 | 0
| 0 | 0.0007332 | 0.0083658 | 0
| 0 | 0.0003413 | 0.0038942 | 0
| 0 | 0.00017064 | 0.001947 | 0
| 0 | 0.0087356 | 0.099673 | 0
| 0 | 0.0043598 | 0.049745 | 0
| 0 | 0.0036515 | 0.041663 | 0
| 0 | 0.0017371 | 0.01982 | 0
| 0 | 0.0040043 | 0.045689 | 0
| 0 | 0.0010198 | 0.011636 | 0
| 0 | 0.0025381 | 0.028959 | 0
| 0 | 0.0021588 | 0.024632 | 0
| 0 | 0.00296 | 0.033774 | 0
| 0 | 0.00082045 | 0.0093613 | 0
| 0 | 0.0039379 | 0.044932 | 0
| 0 | 0.0018868 | 0.021529 | 0
| 0 | 5.6782e-05 | 0.00064789 | 0
| 0 | 0.00048893 | 0.0055787 | 0
| 0 | 0.00049209 | 0.0056147 | 0
| 0 | 0.001022 | 0.011661 | 0
| 0 | 0.0010787 | 0.012308 | 0
| 0 | 0.000246 | 0.0028068 | 0
| 0 | 0.0015579 | 0.017776 | 0
| 0 | 0.0040365 | 0.046057 | 0
| 0 | 2.837e-05 | 0.0003237 | 0
| 0 | 1.8913e-05 | 0.00021579 | 0
| 0 | 0.0012418 | 0.014169 | 0
| 0 | 0.00099582 | 0.011362 | 0
| 0 | 0.0022122 | 0.025241 | 0
| 0 | 0.0045184 | 0.051555 | 0
| 0 | 0.0046176 | 0.052686 | 0
| 0 | 0.00082523 | 0.0094159 | 0
| 0 | 0.0082293 | 0.093896 | 0
| 0 | 0.0015494 | 0.017679 | 0
| 0 | 0.0013258 | 0.015128 | 0
| 0 | 0.00017004 | 0.0019401 | 0
| 0 | 0.001269 | 0.014479 | 0
| 0 | 0.0002141 | 0.0024429 | 0
| 0 | 0.0009067 | 0.010345 | 0
| 0 | 0.00060442 | 0.0068964 | 0
| 0.49773 | 0.00035886 | 0.0040946 | 0
| 0 | 0.0054189 | 0.061829 | 0
| 1.0508 | 0.0087227 | 0.099526 | 0
| 0 | 6.2931e-05 | 0.00071804 | 0
| 0 | 0.00047174 | 0.0053825 | 0
| 0 | 0.0036606 | 0.041767 | 0
| 0 | 0.00079247 | 0.0090421 | 0
| 0 | 0.0012262 | 0.013991 | 0
| 0 | 0.0070989 | 0.080999 | 0
| 0 | 1.8863e-05 | 0.00021522 | 0
| 0 | 0.0011976 | 0.013664 | 0
| 0 | 0.0016216 | 0.018502 | 0
| 0 | 0.0032977 | 0.037627 | 0
| 0 | 0.00032053 | 0.0036572 | 0
| 0 | 0.0020236 | 0.023089 | 0
| 0 | 0.0038187 | 0.043571 | 0
| 0 | 0.0031076 | 0.035458 | 0
| 0 | 0.00034835 | 0.0039747 | 0
| 0 | 0.0037628 | 0.042934 | 0
| 0 | 1.8819e-05 | 0.00021472 | 0
| 0 | 0.004619 | 0.052703 | 0
| 0 | 0.0044461 | 0.05073 | 0
| 0 | 0.0034737 | 0.039635 | 0
| 0 | 0.0029533 | 0.033697 | 0
| 0 | 0.0039124 | 0.04464 | 0
| 0 | 0.00041378 | 0.0047212 | 0
| 0 | 0.00092583 | 0.010564 | 0
| 0 | 0.0021118 | 0.024096 | 0
| 0 | 0.0010369 | 0.011831 | 0
| 0 | 0.0013029 | 0.014866 | 0
| 0 | 0.00071095 | 0.008112 | 0
| 0 | 0.00030065 | 0.0034304 | 0
| 0 | 0.0024989 | 0.028513 | 0
| 0 | 0.00015031 | 0.0017151 | 0
| 0 | 0.00086412 | 0.0098597 | 0
| 0 | 0.0022039 | 0.025146 | 0
| 0 | 0.00052275 | 0.0059646 | 0
| 0 | 0.0038126 | 0.043501 | 0
| 0 | 0.0020157 | 0.022999 | 0
| 0 | 0.001909 | 0.021781 | 0
| 0 | 3.7553e-05 | 0.00042848 | 0
| 0 | 0.0012111 | 0.013818 | 0
| 0 | 0.0048866 | 0.055756 | 0
| 0 | 0.0021397 | 0.024414 | 0
| 0 | 0.0035661 | 0.040689 | 0
| 0 | 0.00058491 | 0.0066738 | 0
| 0 | 0.00045041 | 0.0051391 | 0
| 0 | 0.003371 | 0.038464 | 0
| 0 | 5.6259e-05 | 0.00064192 | 0
| 0 | 0.0021441 | 0.024464 | 0
| 0 | 0.0022877 | 0.026102 | 0
| 0 | 0.0025687 | 0.029309 | 0
| 0 | 0.00011248 | 0.0012834 | 0
| 0 | 0.00047485 | 0.0054181 | 0
| 0 | 0.003167 | 0.036136 | 0
| 0 | 0.0019364 | 0.022094 | 0
| 0 | 0.0021174 | 0.024159 | 0
| 0 | 0.0048717 | 0.055586 | 0
| 0 | 0.0012366 | 0.014109 | 0
| 0 | 0.0061581 | 0.070263 | 0
| 0 | 0.00019168 | 0.0021871 | 0
| 0 | 0.003068 | 0.035005 | 0
| 0 | 3.745e-05 | 0.00042731 | 0
| 0 | 0.0012107 | 0.013814 | 0
| 0 | 0.0026271 | 0.029975 | 0
| 0 | 0.0046292 | 0.052819 | 0
| 0 | 1.8712e-05 | 0.0002135 | 0
| 0 | 0.00023388 | 0.0026686 | 0
| 0 | 0.0018211 | 0.020779 | 0
| 0 | 0.0033676 | 0.038425 | 0
| 0 | 0.0018357 | 0.020945 | 0
| 0 | 0.00069185 | 0.007894 | 0
| 0 | 0.0015017 | 0.017135 | 0
| 0 | 0.00019618 | 0.0022384 | 0
| 0 | 1.8679e-05 | 0.00021313 | 0
| 0 | 0.0031814 | 0.0363 | 0
| 0 | 0.0052479 | 0.059878 | 0
| 0 | 0.0011578 | 0.01321 | 0
| 0 | 0.00016805 | 0.0019174 | 0
| 0 | 0.0013257 | 0.015126 | 0
| 1.7626 | 0.0012105 | 0.013812 | 0
| 0 | 0.00061615 | 0.0070302 | 0
| 0 | 0.0044552 | 0.050834 | 0
| 0 | 0.00011199 | 0.0012779 | 0
| 0 | 0.00017727 | 0.0020226 | 0
| 0 | 0.0066843 | 0.076267 | 0
| 0 | 0.0041214 | 0.047025 | 0
| 0 | 0.0018648 | 0.021277 | 0
| 0 | 0.0031202 | 0.035602 | 0
| 0 | 0.0015724 | 0.017941 | 0
| 0 | 0.0025568 | 0.029173 | 0
| 0 | 0.002252 | 0.025695 | 0
| 0 | 0.00023605 | 0.0026933 | 0
| 0 | 0.0016213 | 0.018499 | 0
| 0 | 0.0016893 | 0.019275 | 0
| 0 | 0.0010184 | 0.01162 | 0
| 0 | 0.0041662 | 0.047536 | 0
| 0 | 1.8623e-05 | 0.00021249 | 0
| 0 | 0.00076346 | 0.0087111 | 0
| 0 | 0.0001117 | 0.0012745 | 0
| 0 | 0.0031892 | 0.036389 | 0
| 0.027442 | 0.00044052 | 0.0050263 | 0
| 0 | 0.001104 | 0.012597 | 0
| 0 | 0.00063256 | 0.0072175 | 0
| 0 | 0.0016496 | 0.018822 | 0
| 0 | 0.00073788 | 0.0084192 | 0
| 0 | 0.0020084 | 0.022916 | 0
| 0 | 0.007159 | 0.081685 | 0
| 0.45032 | 0.0029875 | 0.034088 | 0
| 0 | 1.8592e-05 | 0.00021213 | 0
| 0 | 0.00066917 | 0.0076352 | 0
| 0 | 0.00105 | 0.011981 | 0
| 0 | 5.5727e-05 | 0.00063584 | 0
| 0 | 0.0046438 | 0.052986 | 0
| 0 | 0.001071 | 0.01222 | 0
| 0 | 0.0016095 | 0.018365 | 0
| 0 | 0.0048781 | 0.055659 | 0
| 0 | 0.0005385 | 0.0061443 | 0
| 0 | 0.0022375 | 0.02553 | 0
| 0 | 0.0013368 | 0.015252 | 0
| 0 | 0.00070529 | 0.0080474 | 0
| 0 | 0.010366 | 0.11827 | 0
| 0 | 0.0017382 | 0.019833 | 0
| 0 | 0.0011134 | 0.012704 | 0
| 0 | 0.0009834 | 0.011221 | 0
| 0 | 0.00081638 | 0.0093148 | 0
| 2.2651 | 0.017414 | 0.19869 | 0
| 0 | 0.0052934 | 0.060398 | 0
| 0 | 0.0014097 | 0.016085 | 0
| 0 | 0.00089023 | 0.010157 | 0
| 0 | 0.0031277 | 0.035687 | 0
| 0.42649 | 0.00011126 | 0.0012694 | 0
| 0 | 0.0017861 | 0.02038 | 0
| 0 | 0.0035589 | 0.040607 | 0
| 0 | 0.0030027 | 0.034261 | 0
| 0 | 0.0030842 | 0.035191 | 0
| 0 | 0.00015445 | 0.0017623 | 0
| 0 | 0.0027427 | 0.031294 | 0
| 0 | 0.0011644 | 0.013286 | 0
| 0 | 0.0062263 | 0.071042 | 0
| 0 | 0.0046043 | 0.052535 | 0
| 0 | 0.00027792 | 0.003171 | 0
| 0 | 0.00067923 | 0.00775 | 0
| 0 | 0.0025192 | 0.028744 | 0
| 0 | 0.0007718 | 0.0088062 | 0
| 0 | 0.00050001 | 0.0057051 | 0
| 0 | 0.0041231 | 0.047044 | 0
| 0 | 0.0046229 | 0.052748 | 0
| 0 | 0.002302 | 0.026266 | 0
| 0 | 0.0018742 | 0.021385 | 0
| 0 | 0.0011231 | 0.012814 | 0
| 0 | 0.0025607 | 0.029218 | 0
| 0 | 0.0022026 | 0.025132 | 0
| 0 | 0.00092542 | 0.010559 | 0
| 0 | 0.0018076 | 0.020625 | 0
| 0 | 0.00025293 | 0.002886 | 0
| 0 | 0.0021777 | 0.024847 | 0
| 0 | 0.0011962 | 0.013649 | 0
| 0 | 0.0016215 | 0.018502 | 0
| 0 | 0.00062272 | 0.0071052 | 0
| 0 | 0.0052639 | 0.060061 | 0
| 0 | 0.0020833 | 0.02377 | 0
| 0 | 0.0058427 | 0.066665 | 0
| 0 | 0.00035738 | 0.0040777 | 0
| 0 | 0.0031357 | 0.035779 | 0
| 0 | 0.0011572 | 0.013203 | 0
| 0 | 0.00054165 | 0.0061803 | 0
| 0 | 0.005958 | 0.067981 | 0
| 0 | 0.0030402 | 0.034688 | 0
| 0 | 0.00011076 | 0.0012638 | 0
| 0 | 0.00020918 | 0.0023867 | 0
| 0 | 0.0010518 | 0.012001 | 0
| 0 | 0.0013654 | 0.01558 | 0
| 0 | 0.0045081 | 0.051437 | 0
| 0 | 0.0015127 | 0.01726 | 0
| 0 | 0.002269 | 0.025889 | 0
| 0 | 0.0046836 | 0.053439 | 0
| 0 | 0.0011221 | 0.012803 | 0
| 0 | 0.0044694 | 0.050996 | 0
| 0 | 0.00064545 | 0.0073646 | 0
| 0 | 0.00025809 | 0.0029448 | 0
| 0 | 0.0022518 | 0.025693 | 0
| 0 | 0.00054351 | 0.0062014 | 0
| 0 | 0.0013204 | 0.015065 | 0
| 0 | 0.0017502 | 0.019969 | 0
| 0 | 0.0025852 | 0.029497 | 0
| 0 | 0.0021061 | 0.024031 | 0
| 0 | 0.0025904 | 0.029557 | 0
| 0 | 0.00080409 | 0.0091746 | 0
| 0 | 0.00036827 | 0.004202 | 0
| 0 | 0.00023934 | 0.0027309 | 0
| 0.22109 | 0.0030591 | 0.034905 | 0
| 0 | 0.0014358 | 0.016382 | 0
| 0 | 0.00060114 | 0.0068591 | 0
| 0 | 0.0051339 | 0.058577 | 0
| 0 | 0.0013371 | 0.015256 | 0
| 0 | 0.0018522 | 0.021133 | 0
| 0 | 0.00036792 | 0.004198 | 0
| 0 | 0.0014162 | 0.016159 | 0
| 0 | 0.0014468 | 0.016508 | 0
| 0 | 0.0038002 | 0.043361 | 0
| 0 | 0.0011431 | 0.013043 | 0
| 0 | 0.0026416 | 0.030141 | 0
| 0 | 0.00016546 | 0.0018879 | 0
| 0 | 0.00018382 | 0.0020973 | 0
| 0 | 0.0042521 | 0.048517 | 0
| 0 | 0.00029712 | 0.0033901 | 0
| 0 | 0.00049304 | 0.0056256 | 0
| 0 | 0.0040153 | 0.045815 | 0
| 0 | 0.0019104 | 0.021797 | 0
| 0 | 0.00017756 | 0.0020259 | 0
| 0 | 1.8365e-05 | 0.00020955 | 0
| 0 | 0.00078965 | 0.0090099 | 0
| 0 | 0.00049582 | 0.0056573 | 0
| 0 | 0.0015975 | 0.018227 | 0
| 0 | 0.0035682 | 0.040713 | 0
| 0 | 0.00051403 | 0.0058651 | 0
| 0 | 0.0035381 | 0.040369 | 0
| 0 | 0.0005813 | 0.0066326 | 0
| 0 | 0.0012115 | 0.013823 | 0
| 0 | 0.0017376 | 0.019826 | 0
| 0 | 0.0032947 | 0.037593 | 0
| 0 | 0.0020219 | 0.02307 | 0
| 0 | 0.0021945 | 0.025039 | 0
| 0 | 0.00091765 | 0.01047 | 0
| 0 | 0.0019269 | 0.021986 | 0
| 0 | 0.002879 | 0.032849 | 0
| 0 | 0.0013209 | 0.015071 | 0
| 0 | 0.00049224 | 0.0056165 | 0
| 0 | 0.0016876 | 0.019255 | 0
| 0 | 0.0026594 | 0.030344 | 0
| 0 | 0.0034051 | 0.038852 | 0
| 0 | 0.0020715 | 0.023635 | 0
| 0 | 0.0027979 | 0.031924 | 0
| 0 | 0.0031886 | 0.036382 | 0
| 0 | 0.0018079 | 0.020628 | 0
| 0 | 0.00055575 | 0.0063411 | 0
| 0 | 0.00087303 | 0.0099612 | 0
| 0 | 0.0024481 | 0.027933 | 0
| 0.42959 | 0.0030086 | 0.034328 | 0
| 0 | 0.0024651 | 0.028127 | 0
| 0 | 0.0021172 | 0.024157 | 0
| 0 | 0.0038195 | 0.04358 | 0
| 0 | 0.00080536 | 0.0091891 | 0
| 0 | 0.0037699 | 0.043015 | 0
| 0 | 5.4899e-05 | 0.0006264 | 0
| 0 | 0.00029279 | 0.0033407 | 0
| 0 | 3.659e-05 | 0.00041749 | 0
| 0 | 0.0038418 | 0.043835 | 0
| 0 | 0.0052499 | 0.059901 | 0
| 0 | 0.00072851 | 0.0083123 | 0
| 0 | 0.00084116 | 0.0095976 | 0
| 0 | 0.0021024 | 0.023989 | 0
| 0.552 | 0.00062159 | 0.0070923 | 0
| 0 | 0.00059698 | 0.0068115 | 0
| 0 | 0.00015838 | 0.0018071 | 0
| 0 | 0.00015837 | 0.001807 | 0
| 0 | 0.00031065 | 0.0035445 | 0
| 0 | 0.0011219 | 0.012801 | 0
| 0 | 0.0035072 | 0.040017 | 0
| 0 | 0.0080374 | 0.091707 | 0
| 0 | 0.0038898 | 0.044382 | 0
| 0 | 0.00095886 | 0.010941 | 0
| 0 | 0.00094318 | 0.010762 | 0
| 0 | 0.0001582 | 0.0018051 | 0
| 0 | 0.0020382 | 0.023256 | 0
| 0 | 0.00020078 | 0.0022909 | 0
| 0 | 0.00094103 | 0.010737 | 0
| 0 | 0.0020986 | 0.023945 | 0
| 0 | 0.00034064 | 0.0038867 | 0
| 0 | 0.0043268 | 0.049369 | 0
| 0 | 0.0013498 | 0.015401 | 0
| 0 | 0.00063234 | 0.007215 | 0
| 0 | 0.0058539 | 0.066793 | 0
| 0 | 0.0087381 | 0.099702 | 0
| 0 | 0.0015681 | 0.017892 | 0
| 0 | 0.0016409 | 0.018723 | 0
| 0 | 1.8231e-05 | 0.00020802 | 0
| 0 | 0.00035236 | 0.0040205 | 0
| 0 | 0.0035903 | 0.040965 | 0
| 0 | 0.00036448 | 0.0041588 | 0
| 0 | 0.0013667 | 0.015594 | 0
| 0 | 0.0014092 | 0.016079 | 0
| 0 | 0.0070118 | 0.080005 | 0
| 0 | 0.0018035 | 0.020578 | 0
| 0 | 0.00016819 | 0.001919 | 0
| 0 | 0.00027018 | 0.0030828 | 0
| 0 | 0.00061608 | 0.0070295 | 0
| 0 | 0.00058264 | 0.0066479 | 0
| 0 | 0.0034591 | 0.039468 | 0
| 0 | 0.00094668 | 0.010802 | 0
| 0 | 0.0029307 | 0.033439 | 0
| 0 | 0.0031241 | 0.035646 | 0
| 0 | 0.00018189 | 0.0020754 | 0
| 0 | 0.0035939 | 0.041006 | 0
| 0 | 0.000706 | 0.0080554 | 0
| 0 | 0.00078147 | 0.0089165 | 0
| 0 | 0.0037071 | 0.042298 | 0
| 0 | 0.0021133 | 0.024113 | 0
| 0 | 0.0027396 | 0.031258 | 0
| 0 | 0.0024277 | 0.0277 | 0
| 0 | 7.2635e-05 | 0.00082876 | 0
| 0 | 0.0023969 | 0.027348 | 0
| 0 | 0.00079895 | 0.009116 | 0
| 0 | 0.0023598 | 0.026926 | 0
| 0 | 7.2586e-05 | 0.00082821 | 0
| 0 | 0.0015658 | 0.017866 | 0
| 0 | 0.0030469 | 0.034766 | 0
| 0 | 0.0025084 | 0.028621 | 0
| 0 | 0.0038744 | 0.044207 | 0
| 0 | 0.0017981 | 0.020516 | 0
| 0 | 0.0013567 | 0.01548 | 0
| 0 | 0.00018129 | 0.0020685 | 0
| 0 | 0.0012327 | 0.014065 | 0
| 0 | 0.0030756 | 0.035093 | 0
| 0 | 0.00062841 | 0.0071702 | 0
| 0.060777 | 0.0021448 | 0.024472 | 0
| 0 | 0.0011054 | 0.012613 | 0
| 0 | 0.0006113 | 0.0069749 | 0
| 0 | 0.0026336 | 0.030049 | 0
| 0 | 0.0040166 | 0.045829 | 0
| 0 | 0.0019084 | 0.021775 | 0
| 0.065099 | 0.0096744 | 0.11039 | 0
| 0 | 0.0034058 | 0.03886 | 0
| 0 | 0.0032903 | 0.037542 | 0
| 0 | 0.0015934 | 0.018181 | 0
| 0 | 0.0016834 | 0.019208 | 0
| 0 | 0.0022533 | 0.025711 | 0
| 0 | 0.0036076 | 0.041163 | 0
| 0 | 0.0010798 | 0.012321 | 0
| 0 | 0.0042647 | 0.04866 | 0
| 0 | 1.8095e-05 | 0.00020646 | 0
| 0 | 0.004306 | 0.049131 | 0
| 0 | 0.00049148 | 0.0056077 | 0
| 0 | 0.00048846 | 0.0055733 | 0
| 0 | 0.0044763 | 0.051074 | 0
| 0 | 0.00053648 | 0.0061213 | 0
| 0 | 0.00093728 | 0.010694 | 0
| 0 | 0.0032991 | 0.037643 | 0
| 0 | 0.0076285 | 0.087041 | 0
| 0 | 0.0010665 | 0.012168 | 0
| 0.96251 | 0.0005241 | 0.00598 | 0
| 0 | 0.0018704 | 0.021341 | 0
| 0 | 0.0022191 | 0.02532 | 0
| 0 | 0.0013005 | 0.014839 | 0
| 0 | 0.0055748 | 0.063608 | 0
| 0 | 0.002781 | 0.031731 | 0
| 0 | 0.0028049 | 0.032004 | 0
| 0 | 0.00046948 | 0.0053568 | 0
| 0 | 0.0019196 | 0.021903 | 0
| 0 | 0.0004873 | 0.0055601 | 0
| 0 | 0.0023322 | 0.026611 | 0
| 0 | 4.8104e-05 | 0.00054887 | 0
| 0 | 0.000992 | 0.011319 | 0
| 0 | 0.0015269 | 0.017422 | 0
| 0 | 0.0020858 | 0.023799 | 0
| 0 | 0.0007693 | 0.0087777 | 0
| 0 | 0.0007733 | 0.0088233 | 0
| 0 | 0.0015442 | 0.017619 | 0
| 0 | 0.0028298 | 0.032288 | 0
| 0 | 0.0021505 | 0.024537 | 0
| 0 | 0.00045052 | 0.0051405 | 0
| 0 | 0.0020714 | 0.023635 | 0
| 0 | 0.0046395 | 0.052937 | 0
| 0 | 0.00025208 | 0.0028762 | 0
| 0 | 0.0022832 | 0.026051 | 0
| 0 | 0.0052675 | 0.060102 | 0
| 0 | 0.0016346 | 0.018651 | 0
| 0 | 0.00047987 | 0.0054753 | 0
| 0 | 0.0051451 | 0.058706 | 0
| 0 | 0.00098944 | 0.011289 | 0
| 0 | 0.0035917 | 0.040981 | 0
| 0 | 0.00065048 | 0.007422 | 0
| 0 | 0.0043511 | 0.049646 | 0
| 0 | 0.0027686 | 0.03159 | 0
| 0 | 0.0004253 | 0.0048527 | 0
| 0 | 0.0012759 | 0.014558 | 0
| 0 | 0.00025151 | 0.0028697 | 0
| 0 | 0.0041664 | 0.047539 | 0
| 0 | 0.0021191 | 0.024178 | 0
| 0 | 0.00035915 | 0.0040979 | 0
| 0 | 0.0005386 | 0.0061454 | 0
| 0 | 0.0055144 | 0.06292 | 0
| 0.12243 | 0.00037698 | 0.0043013 | 0
| 0 | 0.0015977 | 0.018229 | 0
| 0 | 0.00078985 | 0.0090122 | 0
| 0 | 0.0047741 | 0.054473 | 0
| 0.015232 | 0.0058848 | 0.067146 | 0
| 0 | 0.0033735 | 0.038492 | 0
| 0 | 0.0018952 | 0.021624 | 0
| 0 | 0.006265 | 0.071484 | 0
| 0 | 0.0030483 | 0.034782 | 0
| 0 | 4.7814e-05 | 0.00054556 | 0
| 0.0034134 | 0.003889 | 0.044374 | 0
| 0 | 0.001506 | 0.017184 | 0
| 0 | 0.0010577 | 0.012068 | 0
| 0 | 0.0014519 | 0.016567 | 0
| 0 | 0.0013174 | 0.015031 | 0
| 0 | 0.0013992 | 0.015964 | 0
| 0 | 0.0099494 | 0.11352 | 0
| 0 | 0.0052265 | 0.059634 | 0
| 0 | 0.0011763 | 0.013421 | 0
| 0 | 0.0010508 | 0.01199 | 0
| 0 | 0.0031597 | 0.036052 | 0
| 0 | 0.0038447 | 0.043867 | 0
| 0 | 0.0055161 | 0.062939 | 0
| 0 | 0.0029249 | 0.033373 | 0
| 0 | 0.0012832 | 0.014641 | 0
| 0 | 0.010169 | 0.11602 | 0
| 0.033761 | 0.0018078 | 0.020628 | 0
| 0.014771 | 0.0014853 | 0.016947 | 0
| 0 | 0.0011154 | 0.012726 | 0
| 0 | 0.0043628 | 0.04978 | 0
| 0 | 0.0036791 | 0.041978 | 0
| 0 | 0.000316 | 0.0036056 | 0
| 0.11218 | 0.00022654 | 0.0025848 | 0
| 0 | 0.00019076 | 0.0021766 | 0
| 0 | 0.0015201 | 0.017345 | 0
| 0 | 0.0010662 | 0.012165 | 0
| 0.19598 | 0.00059006 | 0.0067326 | 0
| 0 | 0.00046485 | 0.0053039 | 0
| 0 | 0.0043025 | 0.049092 | 0
| 0 | 0.00062552 | 0.0071372 | 0
| 0 | 0.000982 | 0.011205 | 0
| 0 | 0.0012683 | 0.014471 | 0
| 0 | 0.00010718 | 0.0012229 | 0
| 0 | 0.0012234 | 0.013959 | 0
| 0 | 0.00035701 | 0.0040734 | 0
| 0 | 0.0063602 | 0.07257 | 0
| 0 | 2.9746e-05 | 0.0003394 | 0
| 0 | 0.0010708 | 0.012218 | 0
| 0.12149 | 0.00041041 | 0.0046828 | 0
| 0 | 0.004157 | 0.047431 | 0
| 0 | 0.00057982 | 0.0066158 | 0
| 0 | 0.0061722 | 0.070425 | 0
| 0 | 0.0043343 | 0.049455 | 0
| 0 | 0.00076697 | 0.0087511 | 0
| 0 | 0.00089173 | 0.010175 | 0
| 0 | 0.0015396 | 0.017567 | 0
| 0 | 0.000428 | 0.0048835 | 0
| 0 | 0.00567 | 0.064694 | 0
| 0 | 0.00293 | 0.033431 | 0
| 0 | 0.0044394 | 0.050654 | 0
| 0 | 0.0027921 | 0.031858 | 0
| 0.46323 | 0.0044548 | 0.050829 | 0
| 0 | 0.0020967 | 0.023923 | 0
| 0 | 0.0018645 | 0.021274 | 0
| 0 | 0.0034435 | 0.039291 | 0
| 0 | 1.7804e-05 | 0.00020314 | 0
| 0 | 0.0029642 | 0.033822 | 0
| 0 | 0.00099083 | 0.011305 | 0
| 0 | 0.0026281 | 0.029986 | 0
| 0 | 0.00025797 | 0.0029434 | 0
| 0 | 0.004999 | 0.057038 | 0
| 0 | 0.0055959 | 0.063849 | 0
| 0 | 0.0010936 | 0.012479 | 0
| 0 | 0.00025192 | 0.0028744 | 0
| 0 | 0.0031472 | 0.035909 | 0
| 0 | 0.002898 | 0.033067 | 0
| 0 | 0.0015644 | 0.017849 | 0
| 0 | 0.0028631 | 0.032669 | 0
| 0 | 0.0036531 | 0.041682 | 0
| 0 | 0.00012442 | 0.0014197 | 0
| 0 | 0.0010605 | 0.012101 | 0
| 0 | 0.0075731 | 0.086409 | 0
| 0 | 0.0019071 | 0.02176 | 0
| 0 | 0.00012431 | 0.0014184 | 0
| 0 | 0.0009915 | 0.011313 | 0
| 0 | 0.0025907 | 0.02956 | 0
| 0 | 0.00068606 | 0.0078279 | 0
| 0 | 5.3205e-05 | 0.00060707 | 0
| 0 | 5.3194e-05 | 0.00060695 | 0
| 0 | 0.0079602 | 0.090826 | 0
| 0 | 0.00026 | 0.0029666 | 0
| 0 | 0.0059325 | 0.06769 | 0
| 0 | 0.003007 | 0.03431 | 0
| 0 | 0.00060849 | 0.0069429 | 0
| 0 | 0.00021266 | 0.0024264 | 0
| 0 | 0.0001772 | 0.0020218 | 0
| 0 | 0.00099229 | 0.011322 | 0
| 0 | 0.0065915 | 0.075209 | 0
| 0 | 1.7712e-05 | 0.00020209 | 0
| 0 | 0.0025912 | 0.029566 | 0
| 0 | 0.0029908 | 0.034125 | 0
| 0 | 0.0019653 | 0.022424 | 0
| 0 | 3.5409e-05 | 0.00040401 | 0
| 0 | 0.00049565 | 0.0056554 | 0
| 0 | 0.0011505 | 0.013127 | 0
| 0 | 0.0017641 | 0.020128 | 0
| 0 | 0.00061336 | 0.0069984 | 0
| 0.39267 | 0.00026536 | 0.0030277 | 0
| 0 | 0.0054836 | 0.062568 | 0
| 0 | 0.0022165 | 0.02529 | 0
| 0 | 0.00094311 | 0.010761 | 0
| 0.20216 | 0.001806 | 0.020607 | 0
| 0 | 3.5354e-05 | 0.00040339 | 0
| 0 | 0.0028635 | 0.032673 | 0
| 0 | 0.0037295 | 0.042553 | 0
| 0 | 0.0038173 | 0.043556 | 0
| 0 | 0.0038867 | 0.044347 | 0
| 0 | 0.0013955 | 0.015923 | 0
| 0 | 0.00015897 | 0.0018138 | 0
| 0.0089164 | 0.0011315 | 0.01291 | 0
| 0 | 1.7659e-05 | 0.00020149 | 0
| 0 | 0.0016245 | 0.018536 | 0
| 0 | 0.0040078 | 0.045729 | 0
| 0 | 3.531e-05 | 0.00040289 | 0
| 0 | 0.00082977 | 0.0094677 | 0
| 0 | 0.00019419 | 0.0022157 | 0
| 0 | 0.0066895 | 0.076327 | 0
| 0 | 0.0025769 | 0.029402 | 0
| 4.6654 | 0.0036063 | 0.041148 | 0
| 0.17275 | 0.0058689 | 0.066964 | 0
| 0 | 0.00029987 | 0.0034215 | 0
| 0 | 0.00065262 | 0.0074464 | 0
| 0 | 0.0017373 | 0.019823 | 0
| 0 | 0.0043181 | 0.04927 | 0
| 0 | 0.0053087 | 0.060572 | 0
| 0 | 0.00035273 | 0.0040247 | 0
| 0 | 0.0016578 | 0.018916 | 0
| 0 | 0.0049848 | 0.056876 | 0
| 0 | 0.0042147 | 0.04809 | 0
| 0 | 0.0013061 | 0.014902 | 0
| 0 | 0.0033146 | 0.037819 | 0
| 0 | 0.0015867 | 0.018105 | 0
| 0 | 0.00038191 | 0.0043576 | 0
| 0 | 0.0022207 | 0.025338 | 0
| 0 | 0.0030337 | 0.034615 | 0
| 0 | 0.0014634 | 0.016697 | 0
| 0 | 0.0010884 | 0.012418 | 0
| 0 | 0.0044445 | 0.050711 | 0
| 0 | 0.0017225 | 0.019654 | 0
| 0 | 0.0024571 | 0.028035 | 0
| 0 | 0.00010562 | 0.0012051 | 0
| 0 | 0.0040299 | 0.045981 | 0
| 0 | 0.0042237 | 0.048193 | 0
| 0 | 0.0021118 | 0.024096 | 0
| 0 | 0.00010559 | 0.0012048 | 0
| 0 | 0.0041294 | 0.047116 | 0
| 0 | 0.00040467 | 0.0046173 | 0
| 0 | 0.010222 | 0.11663 | 0
| 0 | 0.0013723 | 0.015658 | 0
| 0 | 0.0042567 | 0.048569 | 0
| 0 | 0.00095556 | 0.010903 | 0
| 0 | 0.0039509 | 0.04508 | 0
| 0 | 0.00102 | 0.011638 | 0
| 0.0032458 | 0.0010022 | 0.011436 | 0
| 0 | 1.7583e-05 | 0.00020062 | 0
| 0 | 1.758e-05 | 0.00020059 | 0
| 0 | 0.001289 | 0.014707 | 0
| 0 | 0.0050879 | 0.058053 | 0
| 0 | 0.0023022 | 0.026268 | 0
| 0 | 0.00141 | 0.016088 | 0
| 0 | 0.00080839 | 0.0092237 | 0
| 0 | 0.0016517 | 0.018846 | 0
| 0 | 0.0010718 | 0.012229 | 0
| 0 | 0.001282 | 0.014628 | 0
| 0 | 0.0012819 | 0.014627 | 0
| 0 | 0.0035235 | 0.040203 | 0
| 0 | 0.00082522 | 0.0094157 | 0
| 0.014793 | 0.001618 | 0.018461 | 0
| 0 | 6.4359e-05 | 0.00073434 | 0
| 0 | 0.0019297 | 0.022018 | 0
| 0 | 0.00024553 | 0.0028015 | 0
| 0 | 0.00052028 | 0.0059363 | 0
| 0 | 0.0020867 | 0.02381 | 0
| 0 | 0.0032966 | 0.037614 | 0
| 0 | 0.00091182 | 0.010404 | 0
| 0 | 0.0019169 | 0.021872 | 0
| 0 | 0.0027525 | 0.031406 | 0
| 0 | 0.0033661 | 0.038407 | 0
| 0 | 0.0011389 | 0.012995 | 0
| 0 | 0.0023068 | 0.026321 | 0
| 0 | 0.0031708 | 0.036179 | 0
| 0 | 0.0020727 | 0.023649 | 0
| 0 | 0.00054291 | 0.0061946 | 0
| 0 | 0.00064781 | 0.0073915 | 0
| 0 | 0.00092778 | 0.010586 | 0
| 0.028955 | 3.5007e-05 | 0.00039943 | 0
| 0 | 0.00078752 | 0.0089856 | 0
| 0 | 0.0015571 | 0.017767 | 0
| 0 | 4.9561e-05 | 0.00056549 | 0
| 0 | 0.00044894 | 0.0051224 | 0
| 0 | 0.0079669 | 0.090902 | 0
| 2.9394 | 0.0027396 | 0.031258 | 0
| 0 | 0.0011074 | 0.012635 | 0
| 0 | 0.00031466 | 0.0035903 | 0
| 0 | 0.0045621 | 0.052054 | 0
| 0 | 0.0012585 | 0.014359 | 0
| 0 | 0.0018523 | 0.021135 | 0
| 0 | 0.0021259 | 0.024256 | 0
| 0 | 0.0029462 | 0.033616 | 0
| 0 | 0.0030882 | 0.035236 | 0
| 0 | 0.0067178 | 0.07665 | 0
| 0 | 0.0030208 | 0.034468 | 0
| 0 | 0.0031078 | 0.03546 | 0
| 0 | 0.0017864 | 0.020383 | 0
| 0 | 0.00034908 | 0.003983 | 0
| 0 | 0.0030892 | 0.035247 | 0
| 0.60976 | 0.00059919 | 0.0068367 | 0
| 0 | 0.0010354 | 0.011814 | 0
| 0 | 0.0028835 | 0.0329 | 0
| 0 | 0.00077547 | 0.0088482 | 0
| 0 | 0.0006277 | 0.007162 | 0
| 0 | 0.0017843 | 0.020359 | 0
| 0 | 0.00069162 | 0.0078914 | 0
| 0 | 0.0013424 | 0.015316 | 0
| 0 | 0.00080192 | 0.0091499 | 0
| 0 | 0.0023883 | 0.02725 | 0
| 0 | 0.00319 | 0.036398 | 0
| 0 | 0.00014817 | 0.0016906 | 0
| 0 | 0.00060996 | 0.0069596 | 0
| 0 | 0.00041935 | 0.0047847 | 0
| 0 | 0.0072476 | 0.082695 | 0
| 0 | 0.0022823 | 0.026041 | 0
| 0 | 0.00060976 | 0.0069574 | 0
| 0 | 0.00031353 | 0.0035774 | 0
| 0 | 0.0016371 | 0.01868 | 0
| 0 | 0.0055156 | 0.062933 | 0
| 0 | 0.0010795 | 0.012318 | 0
| 0 | 0.0021704 | 0.024764 | 0
| 0 | 0.0010271 | 0.011719 | 0
| 0 | 0.00079607 | 0.0090832 | 0
| 0 | 0.0013518 | 0.015424 | 0
| 0 | 0.0039275 | 0.044812 | 0
| 0 | 0.0040365 | 0.046056 | 0
| 0 | 0.0037865 | 0.043204 | 0
| 0 | 0.0020756 | 0.023683 | 0
| 0 | 0.0050874 | 0.058047 | 0
| 0 | 0.0008116 | 0.0092604 | 0
| 0 | 0.0033792 | 0.038557 | 0
| 0 | 0.0020461 | 0.023345 | 0
| 0 | 0.0017037 | 0.019439 | 0
| 0 | 0.00097341 | 0.011107 | 0
| 0 | 0.0027955 | 0.031897 | 0
| 0 | 0.00011581 | 0.0013214 | 0
| 0 | 0.0010075 | 0.011495 | 0
| 0 | 0.0044815 | 0.051134 | 0
| 0 | 0.0011869 | 0.013543 | 0
| 0.24884 | 0.0071211 | 0.081252 | 0
| 0 | 0.0039365 | 0.044916 | 0
| 0 | 0.00088532 | 0.010101 | 0
| 0 | 0.0015224 | 0.01737 | 0
| 0 | 0.0010415 | 0.011884 | 0
| 0 | 0.0064457 | 0.073546 | 0
| 0 | 0.00015622 | 0.0017825 | 0
| 0 | 0.0013539 | 0.015448 | 0
| 0 | 0.0010761 | 0.012278 | 0
| 0 | 0.0016661 | 0.019011 | 0
| 0 | 0.0023078 | 0.026332 | 0
| 0 | 0.001278 | 0.014582 | 0
| 0 | 0.00074015 | 0.0084451 | 0
| 0 | 0.0011043 | 0.0126 | 0
| 0 | 0.0016244 | 0.018534 | 0
| 0.58774 | 0.0052775 | 0.060216 | 0
| 0 | 0.00072832 | 0.0083101 | 0
| 0 | 0.0019971 | 0.022787 | 0
| 0 | 0.0028663 | 0.032704 | 0
| 0 | 0.00099973 | 0.011407 | 0
| 0 | 0.0029698 | 0.033885 | 0
| 0 | 0.001161 | 0.013247 | 0
| 0 | 0.0011262 | 0.01285 | 0
| 0 | 0.0058208 | 0.066416 | 0
| 0 | 0.00041579 | 0.0047442 | 0
| 0 | 0.00071313 | 0.0081368 | 0
| 0 | 0.00042152 | 0.0048096 | 0
| 0 | 0.0023209 | 0.026482 | 0
| 0 | 0.001472 | 0.016795 | 0
| 0 | 0.0063959 | 0.072977 | 0
| 0 | 0.00035776 | 0.004082 | 0
| 0 | 0.0015 | 0.017115 | 0
| 0 | 0.0029245 | 0.033369 | 0
| 0 | 0.0013671 | 0.015598 | 0
| 0 | 0.0035821 | 0.040872 | 0
| 0 | 0.0015048 | 0.01717 | 0
| 0 | 0.0018217 | 0.020786 | 0
| 0 | 0.00012102 | 0.0013808 | 0
| 0 | 0.00025932 | 0.0029589 | 0
| 0 | 0.0023338 | 0.026628 | 0
| 0 | 0.001296 | 0.014787 | 0
| 0 | 1.1517e-05 | 0.00013141 | 0
| 0 | 0.0019348 | 0.022076 | 0
| 0 | 0.0034718 | 0.039613 | 0
| 0.6355 | 0.00063315 | 0.0072243 | 0
| 0 | 0.0034189 | 0.03901 | 0
| 0 | 0.012156 | 0.1387 | 0
| 0 | 0.0001036 | 0.0011821 | 0
| 0 | 0.0017093 | 0.019503 | 0
| 0 | 0.0048958 | 0.055861 | 0
| 0 | 0.0011941 | 0.013625 | 0
| 0 | 0.0021748 | 0.024815 | 0
| 0 | 0.00094907 | 0.010829 | 0
| 0 | 0.0047452 | 0.054143 | 0
| 0 | 0.0068323 | 0.077956 | 0
| 0 | 0.0013053 | 0.014893 | 0
| 0 | 0.0012733 | 0.014528 | 0
| 0 | 0.00021375 | 0.0024389 | 0
| 0 | 0.0019476 | 0.022222 | 0
| 0 | 0.00059749 | 0.0068174 | 0
| 0 | 0.0066983 | 0.076428 | 0
| 0 | 0.0017519 | 0.019989 | 0
| 0 | 0.0017745 | 0.020247 | 0
| 0 | 0.0014523 | 0.016571 | 0
| 0 | 0.00067127 | 0.0076592 | 0
| 0 | 0.0013911 | 0.015872 | 0
| 0 | 0.0011357 | 0.012958 | 0
| 0 | 0.0015482 | 0.017665 | 0
| 0 | 0.00073397 | 0.0083746 | 0
| 0 | 0.0030789 | 0.03513 | 0
| 0 | 0.0031097 | 0.035481 | 0
| 0 | 0.0011349 | 0.012949 | 0
| 0 | 0.0019429 | 0.022169 | 0
| 0 | 0.0032296 | 0.036849 | 0
| 0 | 0.0010543 | 0.01203 | 0
| 0 | 0.00085092 | 0.009709 | 0
| 0 | 0.0034894 | 0.039814 | 0
| 0 | 0.00042397 | 0.0048375 | 0
| 0 | 0.0016785 | 0.019152 | 0
| 0 | 0.0013347 | 0.015229 | 0
| 0 | 0.0025079 | 0.028615 | 0
| 0 | 0.00061821 | 0.0070538 | 0
| 0 | 0.0033943 | 0.038729 | 0
| 0 | 0.00026616 | 0.0030369 | 0
| 0 | 0.0028637 | 0.032675 | 0
| 0 | 0.0026261 | 0.029963 | 0
| 0 | 0.0029262 | 0.033388 | 0
| 0 | 0.002551 | 0.029107 | 0
| 0 | 0.0016585 | 0.018924 | 0
| 0 | 1.7149e-05 | 0.00019566 | 0
| 0 | 0.0028119 | 0.032084 | 0
| 0 | 0.00077715 | 0.0088673 | 0
| 0 | 0.00051817 | 0.0059123 | 0
| 0 | 2.2842e-05 | 0.00026063 | 0
| 0 | 0.0010333 | 0.01179 | 0
| 0 | 0.00044528 | 0.0050806 | 0
| 0 | 0.00070174 | 0.0080068 | 0
| 0.25934 | 0.0016602 | 0.018943 | 0
| 0 | 0.0043575 | 0.049719 | 0
| 0 | 0.0045057 | 0.051411 | 0
| 0 | 8.5531e-05 | 0.00097591 | 0
| 0 | 0.0050131 | 0.057199 | 0
| 0 | 0.0023148 | 0.026411 | 0
| 0 | 0.0015678 | 0.017889 | 0
| 0 | 0.0015278 | 0.017432 | 0
| 0 | 0.0020549 | 0.023447 | 0
| 0 | 0.0039593 | 0.045176 | 0
| 0.16734 | 0.0023239 | 0.026516 | 0
| 0 | 0.002269 | 0.025889 | 0
| 0 | 0.0070693 | 0.08066 | 0
| 0 | 0.0026973 | 0.030776 | 0
| 0 | 0.0002998 | 0.0034207 | 0
| 0 | 0.0017233 | 0.019663 | 0
| 0.16284 | 0.0038558 | 0.043995 | 0
| 0 | 0.0010918 | 0.012457 | 0
| 0 | 0.00411 | 0.046896 | 0
| 0 | 0.00067644 | 0.0077182 | 0
| 0 | 0.0011479 | 0.013098 | 0
| 0 | 0.0051768 | 0.059067 | 0
| 0 | 0.0050205 | 0.057284 | 0
| 0 | 8.5225e-05 | 0.00097242 | 0
| 0 | 0.0011505 | 0.013127 | 0
| 0 | 0.0044415 | 0.050677 | 0
| 0 | 0.0068866 | 0.078576 | 0
| 0 | 0.0066098 | 0.075418 | 0
| 0 | 0.0036397 | 0.041529 | 0
| 0 | 0.0080051 | 0.091338 | 0
| 0 | 0.0052861 | 0.060314 | 0
| 0 | 0.0033706 | 0.038458 | 0
| 0 | 0.0009305 | 0.010617 | 0
| 0 | 0.0024678 | 0.028157 | 0
| 0 | 0.0012763 | 0.014563 | 0
| 0 | 0.0025864 | 0.029511 | 0
| 0 | 0.0029154 | 0.033264 | 0
| 0 | 0.00169 | 0.019283 | 0
| 0 | 0.00039117 | 0.0044632 | 0
| 0 | 0.00059511 | 0.0067902 | 0
| 0 | 0.0029693 | 0.033879 | 0
| 0 | 0.00074792 | 0.0085337 | 0
| 0 | 0.0022204 | 0.025335 | 0
| 0 | 0.003907 | 0.044579 | 0
| 0 | 0.00033401 | 0.003811 | 0
| 0 | 0.0015511 | 0.017698 | 0
| 0 | 0.0010586 | 0.012078 | 0
| 0 | 0.0011886 | 0.013562 | 0
| 0 | 0.00082615 | 0.0094264 | 0
| 0 | 0.0040739 | 0.046484 | 0
| 0 | 0.0072645 | 0.082888 | 0
| 0 | 0.0015388 | 0.017558 | 0
| 0 | 0.0022573 | 0.025756 | 0
| 0 | 0.0025907 | 0.029559 | 0
| 0 | 3.3936e-05 | 0.00038721 | 0
| 0 | 0.0017758 | 0.020262 | 0
| 0 | 0.0016625 | 0.018969 | 0
| 0 | 0.0014533 | 0.016582 | 0
| 0 | 0.00018657 | 0.0021288 | 0
| 0 | 0.00089873 | 0.010255 | 0
| 0 | 0.001537 | 0.017537 | 0
| 0 | 0.0032538 | 0.037125 | 0
| 0 | 0.0041122 | 0.04692 | 0
| 0 | 0.002067 | 0.023585 | 0
| 0 | 0.00050262 | 0.0057348 | 0
| 0 | 0.0024451 | 0.027898 | 0
| 0 | 0.00044041 | 0.0050251 | 0
| 0 | 0.001914 | 0.021839 | 0
| 0 | 6.2091e-05 | 0.00070846 | 0
| 0 | 0.0063049 | 0.071938 | 0
| 0 | 0.0012954 | 0.01478 | 0
| 0 | 0.0020545 | 0.023442 | 0
| 0 | 0.0075498 | 0.086143 | 0
| 0 | 0.0010155 | 0.011587 | 0
| 0 | 0.00090544 | 0.010331 | 0
| 0 | 0.0018615 | 0.02124 | 0
| 0 | 0.0039704 | 0.045302 | 0
| 0.0059716 | 0.00055814 | 0.0063683 | 0
| 0 | 0.0013924 | 0.015888 | 0
| 0 | 0.0021647 | 0.0247 | 0
| 0 | 0.00027612 | 0.0031505 | 0
| 0 | 0.003479 | 0.039695 | 0
| 0.83283 | 0.0033973 | 0.038763 | 0
| 0 | 0.0015223 | 0.017369 | 0
| 0.48183 | 0.0011098 | 0.012662 | 0
| 0 | 5.0689e-05 | 0.00057836 | 0
| 0 | 0.0020076 | 0.022907 | 0
| 0 | 0.0019231 | 0.021943 | 0
| 0 | 5.0681e-05 | 0.00057827 | 0
| 0 | 0.00098546 | 0.011244 | 0
| 0 | 0.0010809 | 0.012333 | 0
| 0 | 0.0006361 | 0.0072579 | 0
| 0 | 0.0040351 | 0.046041 | 0
| 0 | 0.0010467 | 0.011942 | 0
| 0 | 0.00063565 | 0.0072528 | 0
| 0 | 0.00021929 | 0.0025021 | 0
| 0 | 0.00080963 | 0.0092379 | 0
| 0 | 0.00099481 | 0.011351 | 0
| 0.069111 | 0.0087674 | 0.10004 | 0
| 0 | 0.0014661 | 0.016729 | 0
| 0 | 0.0011341 | 0.012941 | 0
| 0 | 0.00019088 | 0.002178 | 0
| 0 | 0.00073545 | 0.0083915 | 0
| 0 | 0.00089258 | 0.010184 | 0
| 0 | 0.00078029 | 0.0089031 | 0
| 0 | 0.0010214 | 0.011655 | 0
| 0 | 0.0039061 | 0.044568 | 0
| 0 | 0.0031371 | 0.035794 | 0
| 0 | 0.0037205 | 0.042451 | 0
| 0 | 0.0016438 | 0.018756 | 0
| 0 | 0.0054362 | 0.062027 | 0
| 0 | 0.0023673 | 0.027011 | 0
| 0 | 0.00084145 | 0.0096009 | 0
| 0 | 0.0014976 | 0.017088 | 0
| 0 | 0.001336 | 0.015244 | 0
| 0 | 0.0021702 | 0.024762 | 0
| 0 | 0.00031963 | 0.0036469 | 0
| 0 | 0.0039008 | 0.044508 | 0
| 0 | 0.0024204 | 0.027617 | 0
| 0 | 0.0003359 | 0.0038327 | 0
| 0 | 0.00015116 | 0.0017247 | 0
| 0 | 0.0013436 | 0.01533 | 0
| 0 | 0.00082291 | 0.0093894 | 0
| 0 | 0.0087974 | 0.10038 | 0
| 0 | 0.0010966 | 0.012512 | 0
| 0 | 2.7971e-05 | 0.00031915 | 0
| 0 | 0.00024163 | 0.002757 | 0
| 0 | 0.0029695 | 0.033882 | 0
| 0 | 0.0035697 | 0.04073 | 0
| 0 | 0.00085527 | 0.0097587 | 0
| 0 | 0.0011907 | 0.013586 | 0
| 0 | 0.00058132 | 0.0066329 | 0
| 0 | 0.0014868 | 0.016964 | 0
| 0 | 0.0085882 | 0.097992 | 0
| 0 | 0.0041762 | 0.047651 | 0
| 0 | 0.0020649 | 0.02356 | 0
| 0 | 0.00028479 | 0.0032495 | 0
| 0 | 0.0034286 | 0.039121 | 0
| 0 | 0.0027967 | 0.03191 | 0
| 0 | 0.00027909 | 0.0031844 | 0
| 0 | 0.0020597 | 0.023501 | 0
| 0 | 0.0013675 | 0.015603 | 0
| 0 | 0.0031756 | 0.036234 | 0
| 0 | 0.0029575 | 0.033746 | 0
| 0 | 0.0014619 | 0.01668 | 0
| 0 | 0.008319 | 0.09492 | 0
| 0 | 0.00022874 | 0.0026099 | 0
| 0 | 0.0035136 | 0.04009 | 0
| 0 | 0.0037198 | 0.042442 | 0
| 0 | 5.019e-05 | 0.00057267 | 0
| 0 | 0.0021303 | 0.024306 | 0
| 0 | 0.0013884 | 0.015842 | 0
| 0 | 0.0013297 | 0.015172 | 0
| 0 | 0.0030886 | 0.035241 | 0
| 0 | 0.00046829 | 0.0053432 | 0
| 0 | 0.00099779 | 0.011385 | 0
| 0 | 0.0019061 | 0.021748 | 0
| 0 | 0.00093628 | 0.010683 | 0
| 0 | 0.004698 | 0.053604 | 0
| 0 | 0.0014322 | 0.016341 | 0
| 0 | 0.0066518 | 0.075897 | 0
| 0 | 2.7855e-05 | 0.00031783 | 0
| 0.06002 | 0.0004178 | 0.0047671 | 0
| 0 | 0.00084669 | 0.0096608 | 0
| 0 | 0.0025897 | 0.029549 | 0
| 0 | 0.0001782 | 0.0020333 | 0
| 0 | 0.0031237 | 0.035642 | 0
| 0 | 0.0006263 | 0.0071461 | 0
| 0.46434 | 0.00031729 | 0.0036203 | 0
| 0 | 0.0014638 | 0.016702 | 0
| 0 | 0.00075119 | 0.0085711 | 0
| 0 | 0.0010683 | 0.012189 | 0
| 0 | 0.0035049 | 0.039991 | 0
| 0 | 0.00062306 | 0.0071091 | 0
| 0 | 0.0026811 | 0.030591 | 0
| 0 | 0.0014349 | 0.016373 | 0
| 0 | 0.0075195 | 0.085797 | 0
| 0 | 0.0035145 | 0.040101 | 0
| 0 | 0.0055746 | 0.063606 | 0
| 0 | 0.000784 | 0.0089454 | 0
| 0 | 0.0016125 | 0.018398 | 0
| 0 | 0.00071159 | 0.0081193 | 0
| 0 | 1.6677e-05 | 0.00019028 | 0
| 0 | 0.0010701 | 0.012209 | 0
| 0 | 0.0033462 | 0.038181 | 0
| 0 | 0.0026283 | 0.029989 | 0
| 0 | 0.0025672 | 0.029292 | 0
| 0 | 0.00033327 | 0.0038026 | 0
| 0 | 0.0012163 | 0.013878 | 0
| 0 | 0.0015828 | 0.01806 | 0
| 0 | 0.00090524 | 0.010329 | 0
| 0 | 0.0028655 | 0.032696 | 0
| 0 | 0.00084966 | 0.0096946 | 0
| 0.096217 | 0.0017961 | 0.020494 | 0
| 0 | 0.00034975 | 0.0039907 | 0
| 0 | 0.0014154 | 0.01615 | 0
| 0 | 0.00040514 | 0.0046227 | 0
| 0 | 0.00093237 | 0.010638 | 0
| 0 | 0.0021809 | 0.024884 | 0
| 0 | 0.00061032 | 0.0069637 | 0
| 0 | 0.0014812 | 0.016901 | 0
| 0 | 0.00042712 | 0.0048734 | 0
| 0 | 0.00068764 | 0.0078459 | 0
| 0 | 0.0024614 | 0.028084 | 0
| 0 | 0.002771 | 0.031617 | 0
| 0 | 0.0032915 | 0.037556 | 0
| 0 | 0.0020391 | 0.023266 | 0
| 0 | 0.00098071 | 0.01119 | 0
| 0 | 0.00028254 | 0.0032238 | 0
| 0 | 1.661e-05 | 0.00018953 | 0
| 0 | 0.0074965 | 0.085535 | 0
| 0 | 0.0029728 | 0.03392 | 0
| 0 | 0.00089126 | 0.010169 | 0
| 0 | 0.0036479 | 0.041622 | 0
| 0 | 0.0024388 | 0.027826 | 0
| 0.05102 | 0.0015659 | 0.017867 | 0
| 0 | 0.001162 | 0.013258 | 0
| 0 | 0.0021909 | 0.024999 | 0
| 0 | 0.0020966 | 0.023922 | 0
| 0 | 0.0010341 | 0.011799 | 0
| 0 | 0.0048271 | 0.055077 | 0
| 0.18369 | 0.0016422 | 0.018737 | 0
| 0 | 0.0017468 | 0.019932 | 0
| 0 | 0.0020228 | 0.02308 | 0
| 0 | 0.0017796 | 0.020305 | 0
| 0 | 0.0028628 | 0.032664 | 0
| 0 | 0.0056039 | 0.063941 | 0
| 0 | 0.006363 | 0.072602 | 0
| 0.19487 | 0.0018783 | 0.021431 | 0
| 0 | 0.0006132 | 0.0069966 | 0
| 0 | 0.0010605 | 0.012101 | 0
| 0 | 0.0022868 | 0.026092 | 0
| 0 | 0.0014581 | 0.016637 | 0
| 0 | 0.0023528 | 0.026846 | 0
| 0 | 0.0059646 | 0.068057 | 0
| 0 | 0.002284 | 0.026061 | 0
| 0 | 0.00066156 | 0.0075484 | 0
| 0 | 0.003909 | 0.044602 | 0
| 0 | 0.0028108 | 0.032071 | 0
| 0 | 0.0018517 | 0.021128 | 0
| 0 | 0.00090358 | 0.01031 | 0
| 0.58369 | 0.002165 | 0.024703 | 0
| 0 | 0.0011018 | 0.012571 | 0
| 0 | 0.0028584 | 0.032614 | 0
| 0 | 0.0014704 | 0.016777 | 0
| 0 | 0.0020673 | 0.023588 | 0
| 0 | 0.0025429 | 0.029014 | 0
| 0 | 0.00035772 | 0.0040816 | 0
| 0 | 0.0067604 | 0.077137 | 0
| 0 | 0.0017659 | 0.020149 | 0
| 0 | 0.0021235 | 0.024229 | 0
| 0 | 0.000132 | 0.0015062 | 0
| 0 | 0.0011325 | 0.012922 | 0
| 0 | 0.00054423 | 0.0062096 | 0
| 0 | 0.004873 | 0.0556 | 0
| 0.0026986 | 0.0030233 | 0.034495 | 0
| 0 | 0.00077283 | 0.008818 | 0
| 0 | 0.00050525 | 0.0057649 | 0
| 0 | 0.0075561 | 0.086215 | 0
| 0 | 0.0028331 | 0.032326 | 0
| 0 | 0.000185 | 0.0021109 | 0
| 0 | 0.000185 | 0.0021109 | 0
| 0 | 0.002371 | 0.027053 | 0
| 0 | 0.0020494 | 0.023384 | 0
| 0 | 0.0044579 | 0.050864 | 0
| 1.8585 | 0.010448 | 0.11921 | 0
| 0 | 0.004947 | 0.056445 | 0
| 0 | 0.0048514 | 0.055354 | 0
| 0 | 0.0056233 | 0.064162 | 0
| 0.61876 | 0.0030231 | 0.034493 | 0
| 0 | 0.0074402 | 0.084892 | 0
| 0 | 0.0055628 | 0.063472 | 0
| 0 | 0.00018062 | 0.0020609 | 0
| 0 | 0.0010836 | 0.012364 | 0
| 0 | 0.0028568 | 0.032596 | 0
| 0 | 0.00073865 | 0.008428 | 0
| 0 | 0.00059082 | 0.0067413 | 0
| 0 | 0.0029805 | 0.034007 | 0
| 0 | 0.0025429 | 0.029015 | 0
| 0 | 0.0024113 | 0.027513 | 0
| 0 | 0.0015582 | 0.017779 | 0
| 0 | 0.00041001 | 0.0046782 | 0
| 0 | 0.0036087 | 0.041175 | 0
| 0 | 0.0006995 | 0.0079813 | 0
| 0 | 0.0016968 | 0.01936 | 0
| 0 | 0.0074618 | 0.085139 | 0
| 0 | 1.6392e-05 | 0.00018704 | 0
| 0 | 0.002616 | 0.029849 | 0
| 0 | 0.0068648 | 0.078327 | 0
| 0 | 0.0014172 | 0.01617 | 0
| 0 | 0.0034157 | 0.038973 | 0
| 0 | 0.00047503 | 0.0054201 | 0
| 0 | 0.00031121 | 0.0035509 | 0
| 0 | 0.0017753 | 0.020256 | 0
| 0.10415 | 0.0093377 | 0.10654 | 0
| 0 | 0.0013807 | 0.015754 | 0
| 0 | 1.6369e-05 | 0.00018676 | 0
| 0 | 0.00086177 | 0.0098328 | 0
| 0 | 0.0014834 | 0.016926 | 0
| 0 | 0.0026334 | 0.030047 | 0
| 0 | 0.00069787 | 0.0079627 | 0
| 0 | 0.00020718 | 0.0023639 | 0
| 0 | 0.0021097 | 0.024072 | 0
| 0 | 0.0043267 | 0.049368 | 0
| 0 | 0.00051217 | 0.0058439 | 0
| 0 | 0.0018302 | 0.020883 | 0
| 0 | 0.0036387 | 0.041517 | 0
| 0 | 0.00055832 | 0.0063704 | 0
| 0 | 0.0050812 | 0.057976 | 0
| 0 | 0.002246 | 0.025627 | 0
| 0 | 0.0039077 | 0.044587 | 0
| 0 | 0.0040319 | 0.046004 | 0
| 0 | 0.0029539 | 0.033704 | 0
| 0 | 0.0011859 | 0.013531 | 0
| 0 | 0.0016754 | 0.019117 | 0
| 0 | 0.0014847 | 0.016941 | 0
| 0 | 0.0020876 | 0.023819 | 0
| 0 | 0.0013047 | 0.014886 | 0
| 0 | 0.0018536 | 0.02115 | 0
| 0 | 0.001647 | 0.018793 | 0
| 0 | 0.001519 | 0.017332 | 0
| 0 | 0.00119 | 0.013577 | 0
| 0 | 0.0019368 | 0.022099 | 0
| 0 | 0.0036426 | 0.041562 | 0
| 0 | 0.0035997 | 0.041073 | 0
| 0 | 0.0019436 | 0.022177 | 0
| 0 | 0.010292 | 0.11743 | 0
| 0 | 0.0014275 | 0.016288 | 0
| 0 | 0.0026541 | 0.030284 | 0
| 0 | 0.0051617 | 0.058895 | 0
| 0 | 0.0014328 | 0.016348 | 0
| 0 | 0.00084119 | 0.009598 | 0
| 0 | 0.00075959 | 0.0086669 | 0
| 0 | 0.0069975 | 0.079842 | 0
| 0 | 0.0027905 | 0.031839 | 0
| 0 | 0.0025191 | 0.028743 | 0
| 0.42596 | 0.0051249 | 0.058475 | 0
| 0 | 0.0010519 | 0.012002 | 0
| 0 | 0.00094317 | 0.010762 | 0
| 0 | 0.00053118 | 0.0060607 | 0
| 0 | 0.0031814 | 0.0363 | 0
| 0 | 0.00020051 | 0.0022878 | 0
| 0 | 4.877e-05 | 0.00055646 | 0
| 0 | 0.007071 | 0.080681 | 0
| 0 | 0.00067177 | 0.0076649 | 0
| 0 | 0.0034066 | 0.038869 | 0
| 0 | 0.001581 | 0.018039 | 0
| 0 | 0.0045611 | 0.052042 | 0
| 0 | 0.0029293 | 0.033424 | 0
| 0 | 0.00058663 | 0.0066934 | 0
| 0 | 0.0012758 | 0.014557 | 0
| 2.0052 | 0.010194 | 0.11631 | 0
| 0 | 0.00076167 | 0.0086906 | 0
| 0 | 0.0026245 | 0.029946 | 0
| 0 | 0.00087472 | 0.0099806 | 0
| 0 | 0.00086902 | 0.0099155 | 0
| 0 | 0.0034758 | 0.039659 | 0
| 0 | 0.0049539 | 0.056524 | 0
| 0 | 0.0011599 | 0.013235 | 0
| 0 | 0.0031237 | 0.035642 | 0
| 0 | 0.0015752 | 0.017973 | 0
| 0 | 0.00067964 | 0.0077547 | 0
| 0 | 0.0012621 | 0.014401 | 0
| 0 | 0.0026202 | 0.029897 | 0
| 0 | 0.0010675 | 0.01218 | 0
| 0 | 0.001229 | 0.014023 | 0
| 0 | 0.0024193 | 0.027605 | 0
| 0 | 0.0013576 | 0.015491 | 0
| 0 | 0.0039375 | 0.044927 | 0
| 0 | 0.00080782 | 0.0092173 | 0
| 0 | 0.0007378 | 0.0084183 | 0
| 0 | 0.0051861 | 0.059173 | 0
| 0 | 0.0039842 | 0.04546 | 0
| 0 | 0.00099601 | 0.011365 | 0
| 0 | 0.0055552 | 0.063385 | 0
| 0 | 0.0065165 | 0.074353 | 0
| 0 | 1.614e-05 | 0.00018415 | 0
| 0 | 0.0015851 | 0.018086 | 0
| 0 | 0.0036783 | 0.041969 | 0
| 0 | 0.0042532 | 0.048529 | 0
| 0 | 3.225e-05 | 0.00036797 | 0
| 0 | 0.0015586 | 0.017784 | 0
| 0 | 0.0015478 | 0.01766 | 0
| 0 | 0.0056936 | 0.064964 | 0
| 0 | 0.0018645 | 0.021274 | 0
| 0 | 0.0046365 | 0.052902 | 0
| 0 | 0.0041201 | 0.047011 | 0
| 0 | 0.0020412 | 0.02329 | 0
| 0 | 0.003094 | 0.035303 | 0
| 0 | 0.00041892 | 0.0047799 | 0
| 0 | 0.0017936 | 0.020465 | 0
| 0 | 0.002695 | 0.03075 | 0
| 0 | 0.0027809 | 0.03173 | 0
| 0 | 0.00028828 | 0.0032892 | 0
| 0 | 0.0038165 | 0.043546 | 0
| 0 | 0.00017708 | 0.0020205 | 0
| 0 | 0.0012019 | 0.013713 | 0
| 0 | 0.0040717 | 0.046458 | 0
| 0 | 0.00096549 | 0.011016 | 0
| 0 | 0.00073459 | 0.0083817 | 0
| 0 | 0.0012546 | 0.014315 | 0
| 0 | 0.0013401 | 0.015291 | 0
| 0.18475 | 0.0013506 | 0.01541 | 0
| 0 | 0.0063691 | 0.072672 | 0
| 0 | 0.00049826 | 0.0056852 | 0
| 0 | 0.0014946 | 0.017054 | 0
| 0 | 0.0012374 | 0.014118 | 0
| 0 | 0.0062296 | 0.07108 | 0
| 0 | 0.000257 | 0.0029324 | 0
| 0 | 0.0035764 | 0.040807 | 0
| 0 | 0.002104 | 0.024006 | 0
| 0 | 0.0034792 | 0.039698 | 0
| 0 | 0.0030021 | 0.034254 | 0
| 0 | 0.0021885 | 0.024971 | 0
| 0 | 0.0011875 | 0.01355 | 0
| 0 | 1.6047e-05 | 0.00018309 | 0
| 0 | 0.0025351 | 0.028926 | 0
| 0 | 0.0037592 | 0.042893 | 0
| 0 | 0.0011173 | 0.012749 | 0
| 0 | 0.0028227 | 0.032207 | 0
| 0 | 0.0021328 | 0.024335 | 0
| 0 | 0.0040356 | 0.046046 | 0
| 0 | 0.00092927 | 0.010603 | 0
| 0 | 0.0042938 | 0.048993 | 0
| 0 | 0.0028785 | 0.032844 | 0
| 0 | 0.0046244 | 0.052765 | 0
| 0 | 1.0679e-05 | 0.00012185 | 0
| 0 | 0.0069431 | 0.079221 | 0
| 0 | 0.00014408 | 0.0016439 | 0
| 0 | 0.0082192 | 0.093781 | 0
| 0 | 6.3996e-05 | 0.00073019 | 0
| 0 | 0.0038815 | 0.044287 | 0
| 0 | 0.0023619 | 0.026949 | 0
| 0 | 1.5992e-05 | 0.00018247 | 0
| 0 | 0.0023187 | 0.026456 | 0
| 0 | 0.0016523 | 0.018852 | 0
| 0 | 0.00084742 | 0.0096691 | 0
| 0 | 0.0013696 | 0.015627 | 0
| 0 | 0.0017585 | 0.020065 | 0
| 0 | 0.0012789 | 0.014592 | 0
| 0 | 0.00075109 | 0.00857 | 0
| 0 | 0.0026527 | 0.030268 | 0
| 0.13688 | 0.0016458 | 0.018779 | 0
| 0 | 0.0023808 | 0.027165 | 0
| 0 | 0.0027483 | 0.031358 | 0
| 0 | 0.00049532 | 0.0056516 | 0
| 0 | 0.00072935 | 0.0083218 | 0
| 0 | 0.001324 | 0.015107 | 0
| 0 | 0.002201 | 0.025113 | 0
| 0 | 0.0056235 | 0.064164 | 0
| 0 | 0.0028541 | 0.032566 | 0
| 0 | 0.0022375 | 0.02553 | 0
| 0 | 0.0013871 | 0.015827 | 0
| 0 | 0.0063642 | 0.072616 | 0
| 0 | 0.0010788 | 0.01231 | 0
| 0 | 0.0040628 | 0.046356 | 0
| 8.0667 | 0.0046068 | 0.052564 | 0
| 0 | 0.0028647 | 0.032687 | 0
| 0 | 0.0016523 | 0.018853 | 0
| 0 | 0.00102 | 0.011639 | 0
| 0 | 0.00066235 | 0.0075574 | 0
| 0 | 0.0050145 | 0.057215 | 0
| 0 | 1.5917e-05 | 0.00018161 | 0
| 0 | 0.0015067 | 0.017192 | 0
| 0 | 0.0010928 | 0.012469 | 0
| 0 | 0.0038352 | 0.04376 | 0
| 0 | 0.0046618 | 0.053191 | 0
| 0.80398 | 0.010134 | 0.11563 | 0
| 0 | 3.1818e-05 | 0.00036304 | 0
| 0 | 1.5908e-05 | 0.00018151 | 0
| 0 | 1.0605e-05 | 0.00012101 | 0
| 0 | 0.00067863 | 0.0077432 | 0
| 0 | 0.0057731 | 0.065871 | 0
| 0 | 0.0012563 | 0.014335 | 0
| 0 | 0.0049117 | 0.056043 | 0
| 7.381 | 0.025478 | 0.29071 | 0
| 0 | 0.00029658 | 0.003384 | 0
| 0 | 0.00066722 | 0.0076129 | 0
| 0 | 0.00092135 | 0.010513 | 0
| 0 | 0.0008895 | 0.010149 | 0
| 0 | 0.00075157 | 0.0085754 | 0
| 0 | 0.0035185 | 0.040146 | 0
| 0 | 0.0010396 | 0.011862 | 0
| 0 | 0.0039143 | 0.044662 | 0
| 0 | 0.00093616 | 0.010682 | 0
| 0 | 0.0019938 | 0.022749 | 0
| 0 | 0.0011264 | 0.012852 | 0
| 0 | 0.0013148 | 0.015002 | 0
| 0 | 0.00061853 | 0.0070574 | 0
| 0 | 3.1718e-05 | 0.00036191 | 0
| 0 | 0.00016123 | 0.0018396 | 0
| 0 | 0.00042814 | 0.0048851 | 0
| 0 | 1.5855e-05 | 0.0001809 | 0
| 0 | 0.0020818 | 0.023753 | 0
| 0 | 0.0051199 | 0.058418 | 0
| 0 | 0.0016217 | 0.018504 | 0
| 0 | 0.0030901 | 0.035258 | 0
| 0 | 0.00078704 | 0.0089801 | 0
| 0 | 1.5838e-05 | 0.00018071 | 0
| 0 | 4.7509e-05 | 0.00054208 | 0
| 0 | 0.0003906 | 0.0044567 | 0
| 0 | 0.0066977 | 0.076421 | 0
| 0 | 0.00042749 | 0.0048777 | 0
| 0 | 0.000707 | 0.0080669 | 0
| 0 | 0.0046826 | 0.053428 | 0
| 0 | 0.006016 | 0.068643 | 0
| 0 | 0.0010386 | 0.01185 | 0
| 0.018728 | 0.0043483 | 0.049614 | 0
| 0 | 0.0048842 | 0.055728 | 0
| 0 | 0.00024763 | 0.0028255 | 0
| 0 | 0.00076644 | 0.0087451 | 0
| 0 | 0.0001422 | 0.0016225 | 0
| 0 | 0.0024801 | 0.028298 | 0
| 0 | 0.00020004 | 0.0022824 | 0
| 0 | 0.0011629 | 0.013269 | 0
| 0 | 0.0013773 | 0.015716 | 0
| 0 | 1.0512e-05 | 0.00011994 | 0
| 0 | 0.0012608 | 0.014385 | 0
| 0 | 0.0048657 | 0.055518 | 0
| 0 | 0.00083447 | 0.0095213 | 0
| 0 | 0.0013907 | 0.015868 | 0
| 0 | 0.00039337 | 0.0044883 | 0
| 0 | 0.001623 | 0.018518 | 0
| 0 | 0.00044044 | 0.0050254 | 0
| 0 | 0.0003146 | 0.0035895 | 0
| 0 | 0.00030919 | 0.0035279 | 0
| 0 | 0.004605 | 0.052543 | 0
| 0 | 0.0018855 | 0.021514 | 0
| 0 | 0.0063423 | 0.072366 | 0
| 0 | 0.0043465 | 0.049593 | 0
| 0 | 0.0009111 | 0.010396 | 0
| 0 | 0.0027514 | 0.031394 | 0
| 0 | 1.0471e-05 | 0.00011948 | 0
| 0 | 0.0015233 | 0.017381 | 0
| 0 | 0.00458 | 0.052258 | 0
| 0 | 0.003438 | 0.039228 | 0
| 0 | 0.0015592 | 0.017791 | 0
| 0 | 0.0025204 | 0.028758 | 0
| 0 | 0.00029797 | 0.0033999 | 0
| 0 | 0.002807 | 0.032028 | 0
| 0 | 0.0046363 | 0.0529 | 0
| 0 | 0.0019281 | 0.021999 | 0
| 0 | 0.0031814 | 0.0363 | 0
| 0 | 0.0019737 | 0.02252 | 0
| 0 | 0.008801 | 0.10042 | 0
| 0.014383 | 0.0058554 | 0.06681 | 0
| 0 | 0.0012994 | 0.014826 | 0
| 0 | 0.00040702 | 0.0046441 | 0
| 0 | 0.0049351 | 0.05631 | 0
| 0 | 1.5639e-05 | 0.00017844 | 0
| 0 | 0.001032 | 0.011775 | 0
| 0 | 0.0029015 | 0.033106 | 0
| 0.14114 | 0.00035956 | 0.0041026 | 0
| 0 | 0.0028131 | 0.032097 | 0
| 0 | 0.0010887 | 0.012422 | 0
| 0 | 0.0087088 | 0.099367 | 0
| 0 | 0.0045105 | 0.051465 | 0
| 0 | 0.0031091 | 0.035475 | 0
| 0 | 0.00041661 | 0.0047536 | 0
| 0 | 0.003577 | 0.040813 | 0
| 0 | 4.6836e-05 | 0.0005344 | 0
| 0 | 0.0061649 | 0.070342 | 0
| 0 | 0.012205 | 0.13926 | 0
| 0 | 0.001893 | 0.021599 | 0
| 0 | 0.0020601 | 0.023505 | 0
| 0 | 0.0021524 | 0.024559 | 0
| 0 | 0.0028175 | 0.032147 | 0
| 0 | 0.005988 | 0.068324 | 0
| 0 | 0.00029468 | 0.0033624 | 0
| 0 | 0.0011355 | 0.012957 | 0
| 0 | 0.00072744 | 0.0083001 | 0
| 3.6658 | 0.0026341 | 0.030056 | 0
| 2.0341 | 0.011409 | 0.13018 | 0
| 0 | 0.0046125 | 0.052628 | 0
| 0 | 0.00038948 | 0.004444 | 0
| 0 | 0.0014486 | 0.016529 | 0
| 0 | 0.00545 | 0.062184 | 0
| 0 | 0.0066325 | 0.075677 | 0
| 0 | 0.0067623 | 0.077158 | 0
| 0 | 0.0056876 | 0.064895 | 0
| 0 | 0.00045104 | 0.0051463 | 0
| 0 | 4.6631e-05 | 0.00053206 | 0
| 0 | 4.6631e-05 | 0.00053206 | 0
| 0 | 0.00026409 | 0.0030133 | 0
| 0 | 0.00048156 | 0.0054946 | 0
| 0 | 0.0035417 | 0.040411 | 0
| 0 | 0.0015326 | 0.017487 | 0
| 0 | 0.01276 | 0.1456 | 0
| 0 | 0.0012425 | 0.014177 | 0
| 0 | 0.0043012 | 0.049077 | 0
| 0 | 0.00052791 | 0.0060235 | 0
| 0 | 0.0019482 | 0.022229 | 0
| 0 | 0.00078583 | 0.0089663 | 0
| 0 | 0.00041874 | 0.0047778 | 0
| 0 | 0.0047139 | 0.053786 | 0
| 0 | 0.0043361 | 0.049475 | 0
| 0 | 0.00083204 | 0.0094936 | 0
| 0 | 0.0035038 | 0.039979 | 0
| 0 | 0.00052134 | 0.0059484 | 0
| 0 | 0.0065867 | 0.075154 | 0
| 0 | 0.0020765 | 0.023693 | 0
| 0 | 0.0045963 | 0.052444 | 0
| 0 | 4.647e-05 | 0.00053022 | 0
| 0 | 0.00066605 | 0.0075997 | 0
| 0 | 0.00071213 | 0.0081254 | 0
| 0 | 0.00097515 | 0.011126 | 0
| 0 | 0.0028476 | 0.032492 | 0
| 0 | 2.6817e-05 | 0.00030599 | 0
| 0 | 0.0026138 | 0.029823 | 0
| 0 | 0.0021523 | 0.024558 | 0
| 0 | 0.00038663 | 0.0044114 | 0
| 0 | 0.00074215 | 0.0084679 | 0
| 0 | 0.00091189 | 0.010405 | 0
| 0 | 0.00153 | 0.017458 | 0
| 0 | 0.0037702 | 0.043018 | 0
| 0 | 0.0010043 | 0.011459 | 0
| 0 | 0.0035674 | 0.040704 | 0
| 0 | 0.0081849 | 0.09339 | 0
| 0 | 0.00092656 | 0.010572 | 0
| 0 | 0.0021301 | 0.024305 | 0
| 0 | 0.00024695 | 0.0028177 | 0
| 0 | 0.0055291 | 0.063087 | 0
| 0 | 0.0018093 | 0.020645 | 0
| 0 | 0.0045437 | 0.051844 | 0
| 0 | 0.0011716 | 0.013368 | 0
| 0 | 0.00032882 | 0.0037518 | 0
| 0 | 0.0012791 | 0.014594 | 0
| 0 | 0.0010166 | 0.011599 | 0
| 0 | 0.0010576 | 0.012068 | 0
| 0 | 0.0017405 | 0.019859 | 0
| 0 | 0.00090357 | 0.01031 | 0
| 0 | 0.0024844 | 0.028348 | 0
| 0 | 0.0013499 | 0.015402 | 0
| 0 | 0.0025714 | 0.02934 | 0
| 0 | 0.0045261 | 0.051643 | 0
| 0 | 0.0086903 | 0.099156 | 0
| 0 | 0.0014561 | 0.016614 | 0
| 0 | 0.0024351 | 0.027785 | 0
| 0 | 0.0059457 | 0.067841 | 0
| 0 | 0.003116 | 0.035554 | 0
| 0 | 0.002757 | 0.031457 | 0
| 0 | 0.00055337 | 0.0063139 | 0
| 0 | 0.0076229 | 0.086977 | 0
| 0.24664 | 0.0067544 | 0.077067 | 0
| 0 | 0.0034202 | 0.039025 | 0
| 0 | 1.5354e-05 | 0.00017519 | 0
| 0 | 0.0018524 | 0.021136 | 0
| 0 | 0.0033005 | 0.037659 | 0
| 0 | 0.0045263 | 0.051645 | 0
| 0 | 0.0019739 | 0.022522 | 0
| 0 | 0.0058446 | 0.066687 | 0
| 0 | 1.0226e-05 | 0.00011668 | 0
| 0 | 0.0036196 | 0.041299 | 0
| 0 | 0.0028326 | 0.03232 | 0
| 0 | 0.00044463 | 0.0050732 | 0
| 0 | 0.00070006 | 0.0079876 | 0
| 0 | 0.002453 | 0.027989 | 0
| 0 | 0.0001686 | 0.0019237 | 0
| 0 | 0.0020692 | 0.023609 | 0
| 0.14177 | 0.00062831 | 0.007169 | 0
| 0 | 0.0018079 | 0.020628 | 0
| 0 | 0.0018767 | 0.021413 | 0
| 0 | 0.002972 | 0.033911 | 0
| 0 | 0.0043499 | 0.049633 | 0
| 0 | 0.0045028 | 0.051377 | 0
| 0 | 0.00067896 | 0.0077469 | 0
| 0 | 0.0062451 | 0.071256 | 0
| 0 | 0.0038416 | 0.043832 | 0
| 0 | 0.00029074 | 0.0033173 | 0
| 0 | 0.0013158 | 0.015014 | 0
| 0 | 0.00053544 | 0.0061093 | 0
| 0 | 0.0053954 | 0.061562 | 0
| 0 | 0.0042157 | 0.048101 | 0
| 0 | 0.0031728 | 0.036201 | 0
| 0 | 0.00067221 | 0.0076699 | 0
| 0 | 0.0031595 | 0.03605 | 0
| 0 | 0.0002444 | 0.0027886 | 0
| 0 | 0.0041319 | 0.047145 | 0
| 0 | 0.00099213 | 0.01132 | 0
| 0.018237 | 0.00203 | 0.023163 | 0
| 0 | 0.0012744 | 0.01454 | 0
| 0 | 0.00042728 | 0.0048753 | 0
| 0 | 1.5256e-05 | 0.00017407 | 0
| 0 | 0.0019168 | 0.021871 | 0
| 0 | 0.0034874 | 0.039791 | 0
| 0 | 0.0052761 | 0.0602 | 0
| 0 | 0.00088659 | 0.010116 | 0
| 0 | 0.0066976 | 0.07642 | 0
| 0 | 0.0029208 | 0.033326 | 0
| 0 | 3.0469e-05 | 0.00034765 | 0
| 0 | 0.0044938 | 0.051275 | 0
| 0 | 0.002102 | 0.023983 | 0
| 0 | 0.00166 | 0.018941 | 0
| 0 | 0.00013197 | 0.0015058 | 0
| 0 | 0.0066996 | 0.076443 | 0
| 0 | 0.0014642 | 0.016707 | 0
| 0 | 0.0020089 | 0.022922 | 0
| 0 | 6.0852e-05 | 0.00069432 | 0
| 0 | 0.0032856 | 0.037488 | 0
| 0.091505 | 0.010205 | 0.11644 | 0
| 0 | 0.00039032 | 0.0044536 | 0
| 0 | 0.00084903 | 0.0096874 | 0
| 0 | 0.0038622 | 0.044068 | 0
| 0 | 0.0018241 | 0.020814 | 0
| 0 | 0.0013069 | 0.014911 | 0
| 0 | 9.1145e-05 | 0.00104 | 0
| 0 | 0.0015341 | 0.017504 | 0
| 0 | 0.001549 | 0.017674 | 0
| 0 | 0.00048568 | 0.0055417 | 0
| 0 | 0.0026862 | 0.03065 | 0
| 0 | 0.0047039 | 0.053672 | 0
| 0 | 0.0016613 | 0.018956 | 0
| 0 | 0.0006321 | 0.0072123 | 0
| 0 | 0.010586 | 0.12078 | 0
| 0 | 0.0067181 | 0.076654 | 0
| 0 | 4.5492e-05 | 0.00051906 | 0
| 0 | 0.00039414 | 0.0044972 | 0
| 0 | 1.515e-05 | 0.00017286 | 0
| 0 | 0.00069688 | 0.0079514 | 0
| 0 | 0.0011804 | 0.013469 | 0
| 0 | 0.0008222 | 0.0093813 | 0
| 0 | 0.0033724 | 0.038479 | 0
| 0 | 0.0010432 | 0.011903 | 0
| 0 | 0.0010834 | 0.012362 | 0
| 0 | 1.5113e-05 | 0.00017244 | 0
| 0 | 0.01135 | 0.12951 | 0
| 0 | 0.0010729 | 0.012242 | 0
| 0 | 0.00028712 | 0.003276 | 0
| 0 | 1.5107e-05 | 0.00017237 | 0
| 0.26402 | 0.00028702 | 0.0032749 | 0
| 0 | 0.0010932 | 0.012474 | 0
| 0 | 0.0048914 | 0.055811 | 0
| 0 | 0.0032304 | 0.036859 | 0
| 0 | 0.0078157 | 0.089177 | 0
| 0 | 0.0048683 | 0.055547 | 0
| 0 | 0.0022329 | 0.025477 | 0
| 0 | 0.0034095 | 0.038903 | 0
| 0 | 0.00028663 | 0.0032705 | 0
| 0 | 0.00027143 | 0.0030971 | 0
| 0 | 0.00069356 | 0.0079136 | 0
| 0 | 0.00084397 | 0.0096297 | 0
| 0.10537 | 0.00044206 | 0.0050439 | 0
| 0 | 0.0030232 | 0.034495 | 0
| 0 | 0.0016872 | 0.019251 | 0
| 0 | 0.0013405 | 0.015295 | 0
| 1.1092 | 0.0071199 | 0.081238 | 0
| 0 | 0.0075251 | 0.085862 | 0
| 0 | 0.0023779 | 0.027132 | 0
| 0 | 0.004003 | 0.045674 | 0
| 0 | 0.0027111 | 0.030934 | 0
| 0.24447 | 0.0037469 | 0.042752 | 0
| 0 | 0.0029585 | 0.033756 | 0
| 0 | 0.0086637 | 0.098852 | 0
| 0 | 0.0048724 | 0.055594 | 0
| 0 | 0.0031 | 0.035371 | 0
| 0 | 0.00096131 | 0.010969 | 0
| 0 | 0.0054065 | 0.061688 | 0
| 0 | 0.0023584 | 0.026909 | 0
| 0 | 3.0023e-05 | 0.00034257 | 0
| 0.24195 | 0.0075503 | 0.086149 | 0
| 0 | 0.0023715 | 0.027058 | 0
| 0 | 0.00047023 | 0.0053653 | 0
| 0 | 0.0015004 | 0.01712 | 0
| 0 | 0.0017328 | 0.019771 | 0
| 0 | 0.0044453 | 0.050721 | 0
| 0 | 0.0040595 | 0.046319 | 0
| 0 | 0.0045105 | 0.051465 | 0
| 0 | 0.0024773 | 0.028266 | 0
| 0.16643 | 6.9856e-05 | 0.00079706 | 0
| 0 | 0.0033958 | 0.038746 | 0
| 0 | 0.00026936 | 0.0030734 | 0
| 0 | 0.0038154 | 0.043534 | 0
| 0 | 0.0052218 | 0.059581 | 0
| 0 | 2.9913e-05 | 0.0003413 | 0
| 0 | 0.012124 | 0.13834 | 0
| 0 | 0.0014731 | 0.016808 | 0
| 0 | 0.003544 | 0.040437 | 0
| 0 | 0.0081193 | 0.092641 | 0
| 0 | 9.9643e-05 | 0.0011369 | 0
| 0 | 0.004375 | 0.049919 | 0
| 0 | 0.0037953 | 0.043305 | 0
| 0 | 0.0077104 | 0.087976 | 0
| 0 | 0.00082152 | 0.0093736 | 0
| 0 | 0.00067198 | 0.0076673 | 0
| 0 | 0.0028363 | 0.032362 | 0
| 0 | 0.00012688 | 0.0014477 | 0
| 0 | 4.478e-05 | 0.00051094 | 0
| 0 | 0.0055162 | 0.06294 | 0
| 0 | 0.0025963 | 0.029623 | 0
| 0 | 0.0012976 | 0.014806 | 0
| 0 | 0.0022057 | 0.025167 | 0
| 0 | 0.0012167 | 0.013883 | 0
| 0 | 0.00077458 | 0.0088379 | 0
| 0 | 0.0036787 | 0.041975 | 0
| 0 | 0.0015777 | 0.018001 | 0
| 0 | 0.00029767 | 0.0033965 | 0
| 0 | 0.0037596 | 0.042897 | 0
| 0 | 0.0053567 | 0.06112 | 0
| 0 | 0.00014876 | 0.0016974 | 0
| 0 | 2.9752e-05 | 0.00033947 | 0
| 0 | 0.0075975 | 0.086688 | 0
| 0 | 0.0015865 | 0.018102 | 0
| 0 | 0.00042633 | 0.0048644 | 0
| 0 | 0.0013653 | 0.015578 | 0
| 0 | 0.00050042 | 0.0057097 | 0
| 1.4646 | 0.0012163 | 0.013878 | 0
| 0 | 0.0013672 | 0.0156 | 0
| 0 | 0.00030712 | 0.0035042 | 0
| 0.0087403 | 0.0015007 | 0.017123 | 0
| 0 | 0.0019932 | 0.022742 | 0
| 0 | 0.00090106 | 0.010281 | 0
| 0 | 0.0039353 | 0.044902 | 0
| 0 | 0.00094538 | 0.010787 | 0
| 0 | 0.0047301 | 0.053971 | 0
| 0 | 0.00053422 | 0.0060955 | 0
| 0 | 0.0040192 | 0.045859 | 0
| 0 | 0.0065092 | 0.07427 | 0
| 0 | 0.00018773 | 0.002142 | 0
| 0.23228 | 0.0016298 | 0.018596 | 0
| 0 | 0.0032594 | 0.03719 | 0
| 0 | 0.0003259 | 0.0037186 | 0
| 0 | 0.0023252 | 0.026531 | 0
| 0 | 0.00048375 | 0.0055196 | 0
| 0 | 0.0016236 | 0.018525 | 0
| 0 | 0.0047471 | 0.054165 | 0
| 0 | 9.8691e-06 | 0.00011261 | 0
| 2.9651 | 0.0014433 | 0.016468 | 0
| 0 | 0.0035617 | 0.040639 | 0
| 0 | 0.00021704 | 0.0024764 | 0
| 0 | 0.0020566 | 0.023466 | 0
| 0 | 0.00063065 | 0.0071957 | 0
| 0 | 0.0024187 | 0.027597 | 0
| 0 | 0.0052892 | 0.06035 | 0
| 0 | 0.0017162 | 0.019582 | 0
| 0 | 0.0013293 | 0.015167 | 0
| 0 | 0.001152 | 0.013145 | 0
| 0.26838 | 0.00026579 | 0.0030327 | 0
| 0 | 0.0028885 | 0.032958 | 0
| 0 | 0.0011808 | 0.013473 | 0
| 0 | 0.0010332 | 0.011789 | 0
| 0 | 0.0033943 | 0.038729 | 0
| 0 | 0.00053113 | 0.0060602 | 0
| 0 | 0.00038359 | 0.0043767 | 0
| 0 | 0.0054123 | 0.061755 | 0
| 0 | 0.00075202 | 0.0085805 | 0
| 0 | 0.0004816 | 0.005495 | 0
| 0 | 0.00033908 | 0.0038689 | 0
| 0 | 0.0015332 | 0.017494 | 0
| 0 | 0.0067062 | 0.076518 | 0
| 0 | 0.006755 | 0.077074 | 0
| 0 | 0.0024604 | 0.028073 | 0
| 0 | 0.0039478 | 0.045044 | 0
| 0 | 0.0022586 | 0.02577 | 0
| 0 | 0.00077555 | 0.008849 | 0
| 0 | 0.0039757 | 0.045362 | 0
| 0.091564 | 0.00036811 | 0.0042002 | 0
| 0 | 0.0062567 | 0.071389 | 0
| 0 | 0.00069677 | 0.0079501 | 0
| 0 | 0.005682 | 0.064831 | 0
| 0 | 2.9426e-05 | 0.00033575 | 0
| 0 | 0.006458 | 0.073686 | 0
| 0 | 0.001216 | 0.013875 | 0
| 0 | 0.00051411 | 0.005866 | 0
| 0 | 0.0033528 | 0.038256 | 0
| 0 | 9.788e-06 | 0.00011168 | 0
| 0 | 0.0033765 | 0.038526 | 0
| 0 | 1.4676e-05 | 0.00016746 | 0
| 0 | 0.0027362 | 0.03122 | 0
| 0 | 0.0016277 | 0.018572 | 0
| 0 | 0.0010263 | 0.01171 | 0
| 0 | 0.0039007 | 0.044507 | 0
| 0 | 0.00071832 | 0.008196 | 0
| 0 | 0.0038981 | 0.044478 | 0
| 0 | 0.0029456 | 0.033609 | 0
| 0 | 0.0017415 | 0.019871 | 0
| 0 | 0.0001122 | 0.0012802 | 0
| 0 | 0.0012438 | 0.014192 | 0
| 0 | 0.0024232 | 0.027648 | 0
| 0 | 4.388e-05 | 0.00050067 | 0
| 0 | 0.0020618 | 0.023525 | 0
| 0 | 0.00074575 | 0.008509 | 0
| 0 | 0.0022508 | 0.025681 | 0
| 0 | 1.461e-05 | 0.0001667 | 0
| 0 | 0.0012222 | 0.013946 | 0
| 0 | 1.4608e-05 | 0.00016668 | 0
| 0 | 0.0064706 | 0.07383 | 0
| 0 | 0.00089052 | 0.010161 | 0
| 0 | 0.0014014 | 0.015989 | 0
| 0 | 2.9176e-05 | 0.00033289 | 0
| 0 | 0.0024212 | 0.027625 | 0
| 0 | 0.0063581 | 0.072546 | 0
| 0 | 0.0060854 | 0.069435 | 0
| 0 | 0.012273 | 0.14003 | 0
| 0 | 0.0015291 | 0.017447 | 0
| 0.48418 | 0.001907 | 0.021759 | 0
| 0 | 0.0027066 | 0.030883 | 0
| 0 | 0.0023521 | 0.026838 | 0
| 0 | 0.0026477 | 0.030211 | 0
| 0 | 0.0026764 | 0.030538 | 0
| 0 | 0.0011198 | 0.012777 | 0
| 0 | 0.0001938 | 0.0022112 | 0
| 0.0079332 | 0.00030031 | 0.0034266 | 0
| 0 | 0.00011139 | 0.0012709 | 0
| 0 | 1.4526e-05 | 0.00016574 | 0
| 0 | 0.00045227 | 0.0051604 | 0
| 0 | 0.0036548 | 0.041702 | 0
| 0 | 0.0050181 | 0.057256 | 0
| 0 | 0.0060121 | 0.068598 | 0
| 0 | 0.0039557 | 0.045134 | 0
| 0 | 0.0061137 | 0.069757 | 0
| 0 | 0.00026077 | 0.0029753 | 0
| 0 | 0.0029245 | 0.033368 | 0
| 0 | 0.00010131 | 0.0011559 | 0
| 0 | 0.0021467 | 0.024494 | 0
| 0 | 0.0040758 | 0.046505 | 0
| 0 | 4.3402e-05 | 0.00049521 | 0
| 0 | 0.005684 | 0.064855 | 0
| 0.49351 | 0.00039026 | 0.0044528 | 0
| 0 | 0.0003709 | 0.004232 | 0
| 0 | 0.00018785 | 0.0021434 | 0
| 0 | 0.0051626 | 0.058905 | 0
| 0 | 0.0011271 | 0.01286 | 0
| 0 | 0.003922 | 0.04475 | 0
| 0 | 0.002713 | 0.030955 | 0
| 0 | 0.00095657 | 0.010914 | 0
| 0 | 0.0013555 | 0.015466 | 0
| 0 | 0.0016672 | 0.019023 | 0
| 0 | 0.0014558 | 0.016611 | 0
| 0 | 0.0020275 | 0.023134 | 0
| 0 | 0.0047993 | 0.05476 | 0
| 0 | 0.0020386 | 0.02326 | 0
| 0 | 0.00019206 | 0.0021914 | 0
| 0 | 0.0062075 | 0.070828 | 0
| 0 | 0.00070563 | 0.0080513 | 0
| 0 | 0.0047376 | 0.054056 | 0
| 0.24194 | 0.0013289 | 0.015163 | 0
| 0 | 0.0074937 | 0.085504 | 0
| 0 | 0.00031149 | 0.0035541 | 0
| 0 | 0.0012507 | 0.01427 | 0
| 0.2423 | 0.00080481 | 0.0091829 | 0
| 0 | 0.0003018 | 0.0034435 | 0
| 0 | 0.001154 | 0.013167 | 0
| 0 | 0.00021546 | 0.0024584 | 0
| 0 | 0.0037203 | 0.042448 | 0
| 0 | 0.00038776 | 0.0044244 | 0
| 0 | 0.00048346 | 0.0055163 | 0
| 0 | 0.0035182 | 0.040143 | 0
| 0 | 0.00034463 | 0.0039323 | 0
| 0 | 0.00020818 | 0.0023754 | 0
| 0 | 0.0089865 | 0.10254 | 0
| 0 | 0.0025692 | 0.029315 | 0
| 0 | 0.00072693 | 0.0082943 | 0
| 0 | 0.0020658 | 0.02357 | 0
| 0 | 0.00053077 | 0.0060561 | 0
| 0 | 0.0017644 | 0.020132 | 0
| 0 | 0.0012573 | 0.014346 | 0
| 0 | 0.0029536 | 0.033701 | 0
| 0 | 0.0027088 | 0.030907 | 0
| 0 | 0.0062469 | 0.071277 | 0
| 0 | 0.00071151 | 0.0081183 | 0
| 0 | 0.0019714 | 0.022494 | 0
| 0 | 0.0019523 | 0.022276 | 0
| 0 | 0.0041811 | 0.047706 | 0
| 0 | 0.0048114 | 0.054898 | 0
| 0 | 0.0032159 | 0.036693 | 0
| 0 | 1.2881e-05 | 0.00014698 | 0
| 0 | 0.0015981 | 0.018234 | 0
| 0 | 0.0011445 | 0.013059 | 0
| 0 | 0.0001382 | 0.0015769 | 0
| 0 | 0.0026017 | 0.029686 | 0
| 0 | 0.0023667 | 0.027005 | 0
| 1.566 | 0.0038001 | 0.043359 | 0
| 0 | 0.0011998 | 0.013689 | 0
| 0 | 0.0047654 | 0.054374 | 0
| 0 | 0.00045692 | 0.0052134 | 0
| 0 | 0.00073754 | 0.0084153 | 0
| 0 | 0.0054387 | 0.062055 | 0
| 0 | 0.0014836 | 0.016928 | 0
| 0 | 0.00045173 | 0.0051543 | 0
| 0 | 0.00079834 | 0.009109 | 0
| 0 | 0.0017413 | 0.019868 | 0
| 0 | 0.0027221 | 0.031059 | 0
| 0 | 0.0012681 | 0.01447 | 0
| 0 | 0.00081206 | 0.0092656 | 0
| 0 | 0.00025639 | 0.0029254 | 0
| 0 | 8.5409e-05 | 0.00097451 | 0
| 0 | 0.00035347 | 0.0040331 | 0
| 0 | 0.016531 | 0.18861 | 0
| 0 | 5.6892e-05 | 0.00064914 | 0
| 0 | 0.00054758 | 0.0062479 | 0
| 0 | 0.00059729 | 0.0068151 | 0
| 0 | 0.0024458 | 0.027906 | 0
| 0 | 0.00096635 | 0.011026 | 0
| 0 | 0.0096938 | 0.11061 | 0
| 0 | 0.0030399 | 0.034685 | 0
| 0 | 0.0013068 | 0.014911 | 0
| 0 | 0.0047724 | 0.054453 | 0
| 0 | 0.0017893 | 0.020416 | 0
| 0 | 0.0011074 | 0.012635 | 0
| 0 | 0.0067616 | 0.07715 | 0
| 0 | 0.0024915 | 0.028429 | 0
| 0 | 1.6541e-05 | 0.00018873 | 0
| 0 | 0.00045367 | 0.0051764 | 0
| 0 | 0.0039206 | 0.044734 | 0
| 0 | 0.00044416 | 0.0050679 | 0
| 0 | 0.00053862 | 0.0061457 | 0
| 0 | 0.0010016 | 0.011428 | 0
| 0 | 0.0021827 | 0.024904 | 0
| 0 | 0.0049743 | 0.056757 | 0
| 0 | 1.4169e-05 | 0.00016167 | 0
| 0 | 0.0026339 | 0.030053 | 0
| 0 | 0.0018543 | 0.021157 | 0
| 0 | 0.0006227 | 0.007105 | 0
| 0 | 0.0069055 | 0.078792 | 0
| 0 | 0.0013015 | 0.01485 | 0
| 0 | 0.0058426 | 0.066664 | 0
| 0 | 0.015085 | 0.17212 | 0
| 0 | 0.0018174 | 0.020736 | 0
| 0 | 0.004994 | 0.056982 | 0
| 0 | 0.0014356 | 0.01638 | 0
| 0 | 0.0044567 | 0.050851 | 0
| 0 | 0.0042942 | 0.048997 | 0
| 0 | 0.010958 | 0.12503 | 0
| 0 | 0.0031306 | 0.03572 | 0
| 0 | 0.0067098 | 0.076559 | 0
| 0 | 0.0048731 | 0.055602 | 0
| 0 | 0.0017759 | 0.020263 | 0
| 0 | 0.0014937 | 0.017043 | 0
| 0 | 0.013232 | 0.15098 | 0
| 0 | 0.005208 | 0.059423 | 0
| 0 | 0.0015211 | 0.017356 | 0
| 0 | 1.4083e-05 | 0.00016069 | 0
| 0 | 0.00015486 | 0.001767 | 0
| 0.9991 | 0.0009709 | 0.011078 | 0
| 0 | 0.0045491 | 0.051905 | 0
| 0 | 0.00022511 | 0.0025685 | 0
| 0 | 0.0013646 | 0.015571 | 0
| 0 | 0.0016882 | 0.019262 | 0
| 0 | 0.0059911 | 0.068359 | 0
| 0 | 0.0030375 | 0.034657 | 0
| 0 | 0.0065237 | 0.074436 | 0
| 0 | 0.00073105 | 0.0083413 | 0
| 0 | 0.010397 | 0.11864 | 0
| 0 | 0.0016432 | 0.018749 | 0
| 0 | 0.00033001 | 0.0037654 | 0
| 0 | 0.0029896 | 0.034111 | 0
| 0.055732 | 0.0076608 | 0.087409 | 0
| 0 | 0.00055885 | 0.0063764 | 0
| 0 | 0.013309 | 0.15186 | 0
| 0 | 0.0025514 | 0.029111 | 0
| 0 | 9.8119e-05 | 0.0011195 | 0
| 0 | 0.0013312 | 0.015189 | 0
| 0 | 0.0008243 | 0.0094052 | 0
| 0 | 0.0040997 | 0.046777 | 0
| 0 | 0.0013579 | 0.015494 | 0
| 0 | 1.3998e-05 | 0.00015972 | 0
| 0 | 0.0014695 | 0.016767 | 0
| 0 | 0.0065715 | 0.074981 | 0
| 0 | 1.3982e-05 | 0.00015953 | 0
| 0 | 0.0012022 | 0.013717 | 0
| 0 | 0.0079664 | 0.090897 | 0
| 0 | 0.00063819 | 0.0072818 | 0
| 0 | 0.00081951 | 0.0093506 | 0
| 0 | 0.0010896 | 0.012432 | 0
| 0 | 0.00057258 | 0.0065331 | 0
| 0 | 0.00061442 | 0.0070105 | 0
| 0 | 0.0029789 | 0.033989 | 0
| 0 | 0.0035039 | 0.039979 | 0
| 0 | 0.0036566 | 0.041722 | 0
| 0 | 0.0051728 | 0.059022 | 0
| 0 | 2.3252e-05 | 0.00026531 | 0
| 0 | 1.395e-05 | 0.00015917 | 0
| 0 | 0.0027663 | 0.031564 | 0
| 0 | 0.0024404 | 0.027845 | 0
| 0 | 0.0015338 | 0.017501 | 0
| 0 | 0.0015958 | 0.018208 | 0
| 0 | 0.0024674 | 0.028153 | 0
| 0 | 0.00012539 | 0.0014307 | 0
| 0 | 0.00019964 | 0.0022779 | 0
| 0 | 0.0044411 | 0.050673 | 0
| 0 | 0.0034525 | 0.039393 | 0
| 0 | 0.0010276 | 0.011725 | 0
| 0 | 0.00095564 | 0.010904 | 0
| 0 | 0.002848 | 0.032495 | 0
| 0 | 0.0038498 | 0.043927 | 0
| 0 | 0.0011546 | 0.013174 | 0
| 0 | 0.0034829 | 0.03974 | 0
| 0 | 1.3905e-05 | 0.00015865 | 0
| 0 | 0.00093093 | 0.010622 | 0
| 0 | 0.0038621 | 0.044067 | 0
| 0 | 0.0027986 | 0.031931 | 0
| 0 | 0.00097212 | 0.011092 | 0
| 0 | 0.0076975 | 0.087829 | 0
| 0 | 0.001583 | 0.018062 | 0
| 0 | 0.00034703 | 0.0039596 | 0
| 0 | 5.5475e-05 | 0.00063297 | 0
| 0 | 0.0056004 | 0.063901 | 0
| 0 | 0.0024533 | 0.027992 | 0
| 0 | 0.0011226 | 0.012809 | 0
| 0 | 0.0043234 | 0.04933 | 0
| 0 | 0.00212 | 0.024189 | 0
| 0 | 0.00020781 | 0.0023711 | 0
| 0 | 0.0061927 | 0.070659 | 0
| 0 | 1.3852e-05 | 0.00015805 | 0
| 0 | 1.3851e-05 | 0.00015804 | 0
| 0 | 0.0026591 | 0.03034 | 0
| 0 | 0.00026307 | 0.0030016 | 0
| 0 | 0.001975 | 0.022534 | 0
| 0 | 0.010783 | 0.12303 | 0
| 0 | 0.00082575 | 0.0094218 | 0
| 0 | 0.0026568 | 0.030314 | 0
| 0 | 0.0068077 | 0.077675 | 0
| 0 | 0.0033753 | 0.038512 | 0
| 0 | 0.00099595 | 0.011364 | 0
| 0 | 1.3828e-05 | 0.00015778 | 0
| 0 | 0.0022538 | 0.025716 | 0
| 0 | 0.0074661 | 0.085188 | 0
| 0 | 0.0047276 | 0.053942 | 0
| 0 | 0.00055289 | 0.0063085 | 0
| 0 | 0.0098131 | 0.11197 | 0
| 0 | 1.3812e-05 | 0.00015759 | 0
| 0.28184 | 0.0011464 | 0.01308 | 0
| 0 | 0.0039499 | 0.045068 | 0
| 0 | 0.003604 | 0.041121 | 0
| 0 | 0.0050732 | 0.057885 | 0
| 0 | 0.0064537 | 0.073637 | 0
| 0 | 0.00015176 | 0.0017316 | 0
| 0.037946 | 0.008179 | 0.093322 | 0
| 0 | 0.0018882 | 0.021544 | 0
| 0 | 2.756e-05 | 0.00031446 | 0
| 0 | 0.0012262 | 0.01399 | 0
| 0 | 0.0018874 | 0.021536 | 0
| 0 | 0.0013203 | 0.015064 | 0
| 0 | 0.001749 | 0.019957 | 0
| 0 | 6.8832e-05 | 0.00078537 | 0
| 0 | 0.0059445 | 0.067827 | 0
| 0 | 0.0031921 | 0.036422 | 0
| 0 | 0.00068767 | 0.0078464 | 0
| 0 | 0.0055329 | 0.063131 | 0
| 0 | 0.0040277 | 0.045956 | 0
| 0 | 0.011521 | 0.13145 | 0
| 0 | 0.0033599 | 0.038336 | 0
| 0 | 1.3729e-05 | 0.00015665 | 0
| 0 | 0.0049557 | 0.056545 | 0
| 0 | 0.00037744 | 0.0043066 | 0
| 0 | 0.0041581 | 0.047443 | 0
| 0 | 0.002085 | 0.02379 | 0
| 0 | 0.00077714 | 0.0088672 | 0
| 0 | 0.0067681 | 0.077224 | 0
| 0 | 0.0031623 | 0.036082 | 0
| 0 | 0.017809 | 0.2032 | 0
| 0 | 0.0025635 | 0.029249 | 0
| 0 | 0.0035635 | 0.04066 | 0
| 0 | 0.003277 | 0.037391 | 0
| 0 | 0.004664 | 0.053216 | 0
| 0 | 0.00050193 | 0.005727 | 0
| 0 | 0.0051456 | 0.058711 | 0
| 0 | 0.0035385 | 0.040374 | 0
| 0 | 0.0044012 | 0.050218 | 0
| 0 | 0.0011026 | 0.01258 | 0
| 0 | 0.0010249 | 0.011694 | 0
| 0 | 0.010235 | 0.11678 | 0
| 0 | 0.0015449 | 0.017628 | 0
| 0 | 0.00099664 | 0.011372 | 0
| 0 | 0.0036127 | 0.041221 | 0
| 0 | 4.0943e-05 | 0.00046716 | 0
| 0 | 0.0039168 | 0.04469 | 0
| 0 | 0.0018045 | 0.020589 | 0
| 0 | 0.00014989 | 0.0017103 | 0
| 0 | 0.0022074 | 0.025186 | 0
| 0 | 0.0023049 | 0.026299 | 0
| 0 | 0.0015532 | 0.017722 | 0
| 0 | 0.00088556 | 0.010104 | 0
| 0 | 0.0041809 | 0.047704 | 0
| 0 | 0.0042214 | 0.048166 | 0
| 0.013828 | 0.0017974 | 0.020508 | 0
| 0 | 0.0054687 | 0.062398 | 0
| 0 | 0.0047279 | 0.053945 | 0
| 0 | 0.0022004 | 0.025106 | 0
| 0 | 0.003959 | 0.045173 | 0
| 0 | 0.00039454 | 0.0045017 | 0
| 0 | 0.0066929 | 0.076366 | 0
| 0 | 0.00029924 | 0.0034144 | 0
| 0 | 2.7198e-05 | 0.00031033 | 0
| 0 | 0.00040758 | 0.0046505 | 0
| 0 | 0.0015077 | 0.017203 | 0
| 0 | 1.3583e-05 | 0.00015498 | 0
| 0 | 0.0047379 | 0.054059 | 0
| 0 | 0.0029049 | 0.033145 | 0
| 0 | 0.0029701 | 0.033889 | 0
| 0 | 1.357e-05 | 0.00015483 | 0
| 0 | 4.0699e-05 | 0.00046438 | 0
| 0 | 0.017177 | 0.19599 | 0
| 0 | 0.00070461 | 0.0080396 | 0
| 0 | 0.0021799 | 0.024873 | 0
| 0 | 0.0085897 | 0.098008 | 0
| 0 | 0.0048327 | 0.055142 | 0
| 0 | 0.010261 | 0.11707 | 0
| 0 | 1.3529e-05 | 0.00015437 | 0
| 0 | 2.7047e-05 | 0.00030861 | 0
| 0 | 0.0048127 | 0.054913 | 0
| 0 | 0.0096791 | 0.11044 | 0
| 0.15989 | 0.0042036 | 0.047963 | 0
| 0 | 0.00093251 | 0.01064 | 0
| 0 | 0.0020767 | 0.023695 | 0
| 0 | 0.0044717 | 0.051022 | 0
| 0 | 0.00079653 | 0.0090884 | 0
| 0 | 0.0016995 | 0.019391 | 0
| 0 | 0.0033159 | 0.037834 | 0
| 0.014081 | 0.0045013 | 0.05136 | 0
| 0 | 0.0027071 | 0.030888 | 0
| 0 | 0.00036355 | 0.0041481 | 0
| 0 | 0.00039938 | 0.0045569 | 0
| 0 | 0.0011129 | 0.012698 | 0
| 0 | 0.005223 | 0.059595 | 0
| 0 | 0.0059657 | 0.068069 | 0
| 0 | 0.0019586 | 0.022348 | 0
| 0 | 0.0059552 | 0.067948 | 0
| 0 | 0.0022579 | 0.025763 | 0
| 0 | 0.0015946 | 0.018195 | 0
| 0 | 0.00064941 | 0.0074097 | 0
| 0 | 0.0046778 | 0.053374 | 0
| 0 | 0.0039493 | 0.045062 | 0
| 0 | 0.002082 | 0.023756 | 0
| 0 | 0.00085963 | 0.0098084 | 0
| 0 | 0.0047806 | 0.054547 | 0
| 0 | 0.00024171 | 0.0027579 | 0
| 0.67137 | 0.00084596 | 0.0096524 | 0
| 0.15188 | 0.00038926 | 0.0044414 | 0
| 0 | 0.0055389 | 0.063199 | 0
| 0 | 0.0083077 | 0.094791 | 0
| 0 | 0.0039203 | 0.044731 | 0
| 0 | 0.0061093 | 0.069707 | 0
| 0 | 0.00095703 | 0.01092 | 0
| 0 | 0.0062169 | 0.070935 | 0
| 0 | 0.00095212 | 0.010864 | 0
| 0 | 0.0052031 | 0.059368 | 0
| 0 | 0.0028295 | 0.032284 | 0
| 0 | 0.0029609 | 0.033784 | 0
| 0.37809 | 0.00013392 | 0.0015281 | 0
| 0 | 0.0066677 | 0.076078 | 0
| 0 | 0.0038826 | 0.044301 | 0
| 0 | 0.001553 | 0.01772 | 0
| 0 | 0.00096375 | 0.010996 | 0
| 0 | 0.0063303 | 0.072228 | 0
| 0 | 0.0015747 | 0.017967 | 0
| 0 | 0.0046704 | 0.053289 | 0
| 0 | 0.00033447 | 0.0038163 | 0
| 0 | 0.0019532 | 0.022286 | 0
| 0 | 0.002916 | 0.033272 | 0
| 1.0029 | 0.00095793 | 0.01093 | 0
| 0 | 0.0015102 | 0.017232 | 0
| 0 | 0.0040675 | 0.046411 | 0
| 0 | 0.0021774 | 0.024844 | 0
| 0 | 0.0099361 | 0.11337 | 0
| 0 | 0.0021929 | 0.025021 | 0
| 0 | 0.0022147 | 0.02527 | 0
| 0 | 0.00076028 | 0.0086748 | 0
| 0 | 0.0013024 | 0.014861 | 0
| 0 | 0.0034528 | 0.039396 | 0
| 0 | 0.0027372 | 0.031232 | 0
| 0 | 0.0029182 | 0.033297 | 0
| 0 | 0.0058231 | 0.066441 | 0
| 0 | 0.0052473 | 0.059871 | 0
| 0 | 0.0068529 | 0.078191 | 0
| 0 | 0.0031134 | 0.035524 | 0
| 0 | 1.3301e-05 | 0.00015177 | 0
| 0 | 0.00050515 | 0.0057637 | 0
| 0 | 0.004586 | 0.052326 | 0
| 0 | 0.011098 | 0.12663 | 0
| 0 | 0.00039863 | 0.0045484 | 0
| 0 | 0.00027893 | 0.0031826 | 0
| 0 | 0.0013763 | 0.015703 | 0
| 0 | 0.0068763 | 0.078459 | 0
| 0 | 0.0013536 | 0.015445 | 0
| 0 | 0.00041129 | 0.0046928 | 0
| 0 | 0.0013485 | 0.015387 | 0
| 0 | 6.1892e-05 | 0.00070618 | 0
| 0 | 0.0047214 | 0.053871 | 0
| 1.9579 | 0.001083 | 0.012357 | 0
| 0 | 0.0073402 | 0.083751 | 0
| 0 | 0.0023538 | 0.026857 | 0
| 0 | 0.0010076 | 0.011497 | 0
| 0 | 0.0006761 | 0.0077144 | 0
| 0 | 0.00034458 | 0.0039317 | 0
| 0 | 0.0019875 | 0.022678 | 0
| 0 | 0.0024773 | 0.028266 | 0
| 0 | 0.0036296 | 0.041414 | 0
| 0 | 0.0030982 | 0.03535 | 0
| 0 | 0.002131 | 0.024315 | 0
| 0 | 0.0073834 | 0.084245 | 0
| 0 | 0.0049223 | 0.056163 | 0
| 0 | 0.0045637 | 0.052072 | 0
| 0.072871 | 0.01211 | 0.13818 | 0
| 0 | 0.0043901 | 0.050091 | 0
| 0 | 0.0093476 | 0.10666 | 0
| 0 | 0.0035825 | 0.040876 | 0
| 0 | 0.0029455 | 0.033608 | 0
| 0 | 0.0068921 | 0.078639 | 0
| 0 | 0.0017559 | 0.020034 | 0
| 0 | 0.0030889 | 0.035245 | 0
| 0 | 0.002428 | 0.027703 | 0
| 0 | 0.0050217 | 0.057297 | 0
| 0 | 0.0031395 | 0.035822 | 0
| 0 | 0.0010023 | 0.011437 | 0
| 0 | 0.0027157 | 0.030986 | 0
| 0 | 6.1498e-05 | 0.0007017 | 0
| 0 | 0.0017259 | 0.019693 | 0
| 0 | 0.0058099 | 0.066291 | 0
| 0 | 0.0032475 | 0.037054 | 0
| 0 | 0.003695 | 0.042161 | 0
| 0 | 0.00061854 | 0.0070576 | 0
| 1.6 | 0.00078304 | 0.0089345 | 0
| 0 | 0.0019295 | 0.022016 | 0
| 0 | 0.0018147 | 0.020706 | 0
| 0 | 0.0013411 | 0.015301 | 0
| 0 | 0.0021581 | 0.024624 | 0
| 0 | 0.028578 | 0.32607 | 0
| 0 | 0.0028898 | 0.032972 | 0
| 0 | 0.00055165 | 0.0062943 | 0
| 0 | 9.1865e-05 | 0.0010482 | 0
| 0 | 0.0030838 | 0.035186 | 0
| 0 | 0.0011856 | 0.013527 | 0
| 0 | 0.0024305 | 0.027732 | 0
| 0 | 0.00054636 | 0.006234 | 0
| 0 | 0.00012457 | 0.0014213 | 0
| 0 | 0.0077191 | 0.088075 | 0
| 0 | 0.0017554 | 0.020029 | 0
| 0 | 0.00014409 | 0.0016441 | 0
| 0 | 0.0055063 | 0.062827 | 0
| 0 | 0.0029319 | 0.033453 | 0
| 0 | 0.001121 | 0.012791 | 0
| 0 | 0.0051153 | 0.058366 | 0
| 0 | 0.00057549 | 0.0065663 | 0
| 0 | 0.0026288 | 0.029994 | 0
| 0 | 0.0069293 | 0.079063 | 0
| 0 | 0.0028445 | 0.032455 | 0
| 0 | 0.0017777 | 0.020284 | 0
| 0 | 0.0047529 | 0.05423 | 0
| 0 | 0.00061407 | 0.0070065 | 0
| 0 | 0.00079695 | 0.0090932 | 0
| 0 | 0.0060114 | 0.06859 | 0
| 0 | 0.0020489 | 0.023378 | 0
| 0 | 0.0046966 | 0.053589 | 0
| 0 | 0.0099543 | 0.11358 | 0
| 0 | 0.00058705 | 0.0066982 | 0
| 0 | 0.00019564 | 0.0022323 | 0
| 0 | 0.001708 | 0.019488 | 0
| 0 | 0.0089114 | 0.10168 | 0
| 0 | 0.0012466 | 0.014224 | 0
| 0 | 0.010393 | 0.11858 | 0
| 0 | 0.0008202 | 0.0093585 | 0
| 0 | 0.0065077 | 0.074253 | 0
| 0 | 0.0013403 | 0.015292 | 0
| 0 | 0.001483 | 0.016921 | 0
| 0 | 0.0050842 | 0.058011 | 0
| 0 | 0.00078581 | 0.0089661 | 0
| 0 | 0.0057749 | 0.065891 | 0
| 0 | 0.00044116 | 0.0050337 | 0
| 0 | 0.0073891 | 0.08431 | 0
| 0 | 0.0052804 | 0.06025 | 0
| 0 | 0.0031499 | 0.03594 | 0
| 0 | 0.0015031 | 0.01715 | 0
| 0 | 0.0080192 | 0.091499 | 0
| 0 | 0.0036656 | 0.041825 | 0
| 0 | 0.0059108 | 0.067442 | 0
| 0 | 0.0041834 | 0.047733 | 0
| 0 | 0.0030973 | 0.03534 | 0
| 0 | 1.2941e-05 | 0.00014766 | 0
| 0 | 0.007195 | 0.082095 | 0
| 0 | 0.0019497 | 0.022246 | 0
| 0 | 0.00042698 | 0.0048719 | 0
| 0 | 0.007219 | 0.082368 | 0
| 0 | 0.00076288 | 0.0087044 | 0
| 0 | 0.0010276 | 0.011725 | 0
| 0 | 0.0012618 | 0.014397 | 0
| 0 | 0.00024544 | 0.0028005 | 0
| 0 | 0.0045725 | 0.052172 | 0
| 0 | 0.011119 | 0.12686 | 0
| 0 | 0.0011297 | 0.01289 | 0
| 0 | 0.0017558 | 0.020034 | 0
| 0 | 0.0034728 | 0.039624 | 0
| 0 | 0.00043875 | 0.0050061 | 0
| 0 | 0.00028383 | 0.0032386 | 0
| 0 | 0.010174 | 0.11608 | 0
| 0 | 0.0015091 | 0.017219 | 0
| 0 | 0.0051587 | 0.058861 | 0
| 0 | 0.0027077 | 0.030895 | 0
| 0 | 0.0021001 | 0.023963 | 0
| 0 | 0.0099715 | 0.11377 | 0
| 0 | 0.011178 | 0.12754 | 0
| 0 | 0.006683 | 0.076254 | 0
| 0.01553 | 0.00082409 | 0.0094028 | 0
| 0 | 0.0055471 | 0.063293 | 0
| 0 | 0.0020461 | 0.023345 | 0
| 0 | 0.0032556 | 0.037146 | 0
| 0 | 0.0010421 | 0.01189 | 0
| 0 | 0.0040086 | 0.045738 | 0
| 0 | 0.0020964 | 0.02392 | 0
| 0 | 0.0015834 | 0.018067 | 0
| 0 | 0.0017741 | 0.020243 | 0
| 0 | 0.0021533 | 0.024569 | 0
| 0 | 0.0059975 | 0.068432 | 0
| 0 | 0.0059375 | 0.067747 | 0
| 0 | 0.0029692 | 0.033879 | 0
| 0 | 0.0029683 | 0.033868 | 0
| 0 | 0.0053173 | 0.060671 | 0
| 0 | 0.0019778 | 0.022567 | 0
| 0 | 0.0041568 | 0.047429 | 0
| 0 | 0.0047219 | 0.053876 | 0
| 0 | 0.012015 | 0.13709 | 0
| 0 | 0.00075707 | 0.0086381 | 0
| 0 | 0.0055813 | 0.063683 | 0
| 0 | 0.001176 | 0.013418 | 0
| 0 | 0.0050942 | 0.058124 | 0
| 0 | 0.0091507 | 0.10441 | 0
| 0 | 0.0062811 | 0.071668 | 0
| 0 | 0.0023971 | 0.02735 | 0
| 0 | 0.005486 | 0.062595 | 0
| 0 | 0.0025108 | 0.028648 | 0
| 0 | 0.0039967 | 0.045602 | 0
| 0 | 0.00049949 | 0.0056992 | 0
| 0 | 0.00030732 | 0.0035065 | 0
| 0 | 3.8413e-05 | 0.00043829 | 0
| 0.20487 | 0.0047497 | 0.054194 | 0
| 0 | 0.0054282 | 0.061936 | 0
| 0 | 0.0071009 | 0.081021 | 0
| 0.28801 | 0.0024238 | 0.027656 | 0
| 0 | 0.001278 | 0.014582 | 0
| 0 | 0.0050564 | 0.057694 | 0
| 0 | 0.0015741 | 0.017961 | 0
| 0 | 0.00078056 | 0.0089061 | 0
| 0 | 0.00080177 | 0.0091482 | 0
| 0 | 0.0022593 | 0.025778 | 0
| 0 | 0.00024292 | 0.0027718 | 0
| 0 | 0.0058804 | 0.067095 | 0
| 0 | 0.0025344 | 0.028917 | 0
| 0 | 0.00095809 | 0.010932 | 0
| 0 | 0.0046621 | 0.053194 | 0
| 0 | 0.00067229 | 0.0076709 | 0
| 0 | 0.00066375 | 0.0075734 | 0
| 0 | 0.0032416 | 0.036986 | 0
| 0 | 0.0016841 | 0.019216 | 0
| 0 | 2.5501e-05 | 0.00029097 | 0
| 0 | 0.0064006 | 0.073031 | 0
| 0 | 0.00072636 | 0.0082878 | 0
| 0 | 0.0044854 | 0.051179 | 0
| 0 | 0.0031219 | 0.035621 | 0
| 0 | 0.0018816 | 0.021469 | 0
| 0 | 0.0061257 | 0.069894 | 0
| 0 | 0.00039055 | 0.0044562 | 0
| 0 | 0.0025079 | 0.028615 | 0
| 0 | 0.0097017 | 0.1107 | 0
| 0 | 0.005686 | 0.064877 | 0
| 0 | 0.00073348 | 0.008369 | 0
| 0 | 0.00087735 | 0.010011 | 0
| 1.3299 | 0.00061661 | 0.0070355 | 0
| 0 | 3.3878e-05 | 0.00038655 | 0
| 0 | 0.0014991 | 0.017105 | 0
| 0 | 0.0090071 | 0.10277 | 0
| 0 | 0.00076282 | 0.0087038 | 0
| 0 | 0.0072783 | 0.083045 | 0
| 0 | 0.0052398 | 0.059786 | 0
| 0 | 0.0048248 | 0.055051 | 0
| 0 | 1.2697e-05 | 0.00014487 | 0
| 0 | 0.0044417 | 0.050679 | 0
| 0 | 0.00011412 | 0.0013021 | 0
| 0 | 0.0088871 | 0.1014 | 0
| 0 | 0.0053074 | 0.060558 | 0
| 0 | 0.0018859 | 0.021518 | 0
| 0 | 0.0055529 | 0.063359 | 0
| 0 | 0.0014544 | 0.016595 | 0
| 0 | 0.0055397 | 0.063208 | 0
| 0 | 0.010873 | 0.12406 | 0
| 0 | 0.0023262 | 0.026542 | 0
| 0 | 0.00099868 | 0.011395 | 0
| 0 | 0.0026842 | 0.030627 | 0
| 0 | 0.0039049 | 0.044555 | 0
| 0 | 0.0013772 | 0.015713 | 0
| 0 | 0.0010983 | 0.012532 | 0
| 0 | 0.0049813 | 0.056837 | 0
| 0 | 0.0023852 | 0.027216 | 0
| 0 | 0.00099681 | 0.011374 | 0
| 0 | 6.7236e-05 | 0.00076716 | 0
| 0 | 0.003076 | 0.035097 | 0
| 0 | 0.0087671 | 0.10003 | 0
| 0 | 0.0060883 | 0.069467 | 0
| 0.23129 | 0.00036541 | 0.0041693 | 0
| 0 | 0.0011842 | 0.013511 | 0
| 0 | 0.0043898 | 0.050088 | 0
| 0 | 0.00062976 | 0.0071856 | 0
| 0 | 0.00062974 | 0.0071853 | 0
| 0 | 0.0082404 | 0.094023 | 0
| 0 | 0.022427 | 0.2559 | 0
| 0 | 0.0070253 | 0.080159 | 0
| 0 | 0.0037515 | 0.042804 | 0
| 0 | 0.00054128 | 0.006176 | 0
| 0.12474 | 0.0015479 | 0.017662 | 0
| 0 | 0.019216 | 0.21926 | 0
| 0 | 0.0012829 | 0.014638 | 0
| 0 | 0.00074186 | 0.0084647 | 0
| 0 | 0.0045642 | 0.052077 | 0
| 0 | 0.003818 | 0.043564 | 0
| 0 | 0.0014829 | 0.01692 | 0
| 0 | 0.0060316 | 0.068821 | 0
| 0 | 0.0010805 | 0.012329 | 0
| 0 | 0.0030612 | 0.034928 | 0
| 0 | 0.0053265 | 0.060775 | 0
| 0 | 0.0018078 | 0.020627 | 0
| 0 | 0.0058866 | 0.067166 | 0
| 0 | 0.0091823 | 0.10477 | 0
| 0 | 0.0074379 | 0.084866 | 0
| 0 | 0.0019065 | 0.021753 | 0
| 0 | 0.0012917 | 0.014738 | 0
| 0 | 0.0019061 | 0.021749 | 0
| 0 | 0.00071474 | 0.0081552 | 0
| 0 | 0.0040376 | 0.046069 | 0
| 0 | 0.003791 | 0.043256 | 0
| 0 | 0.0001961 | 0.0022375 | 0
| 0 | 1.2516e-05 | 0.00014281 | 0
| 0 | 0.0018274 | 0.02085 | 0
| 0 | 0.0024281 | 0.027704 | 0
| 0 | 0.0054924 | 0.062668 | 0
| 0 | 0.0076911 | 0.087755 | 0
| 0 | 0.0023632 | 0.026964 | 0
| 0 | 0.0053462 | 0.061 | 0
| 0 | 0.00018735 | 0.0021377 | 0
| 0 | 0.00043298 | 0.0049403 | 0
| 0 | 0.0013488 | 0.01539 | 0
| 0 | 0.00013321 | 0.0015199 | 0
| 0 | 0.0057021 | 0.065061 | 0
| 0 | 0.003933 | 0.044876 | 0
| 0 | 0.00432 | 0.049291 | 0
| 0 | 0.0018226 | 0.020796 | 0
| 0 | 0.0026586 | 0.030335 | 0
| 0 | 0.0052989 | 0.060461 | 0
| 0 | 0.0041067 | 0.046857 | 0
| 0 | 0.0019079 | 0.021769 | 0
| 0 | 0.0054691 | 0.062402 | 0
| 0 | 0.0035875 | 0.040933 | 0
| 0 | 1.6606e-05 | 0.00018947 | 0
| 0 | 0.0078274 | 0.08931 | 0
| 0 | 0.0006595 | 0.0075249 | 0
| 0 | 2.4863e-05 | 0.00028368 | 0
| 0 | 0.0018974 | 0.02165 | 0
| 0 | 0.0024917 | 0.028431 | 0
| 0 | 2.4845e-05 | 0.00028348 | 0
| 0 | 0.00011384 | 0.0012989 | 0
| 0 | 0.0012833 | 0.014642 | 0
| 0 | 0.004628 | 0.052806 | 0
| 0 | 0.0063415 | 0.072357 | 0
| 0 | 0.0017383 | 0.019834 | 0
| 0 | 0.0061913 | 0.070643 | 0
| 0 | 0.0030404 | 0.034691 | 0
| 0 | 0.0060146 | 0.068627 | 0
| 0 | 0.0044716 | 0.051022 | 0
| 0 | 1.2398e-05 | 0.00014146 | 0
| 0 | 0.0010908 | 0.012446 | 0
| 0 | 0.0081557 | 0.093057 | 0
| 0 | 0.012232 | 0.13957 | 0
| 0 | 0.00066503 | 0.007588 | 0
| 0 | 0.00020651 | 0.0023563 | 0
| 0 | 0.0068644 | 0.078323 | 0
| 0 | 0.0022303 | 0.025448 | 0
| 0 | 0.0045949 | 0.052428 | 0
| 0 | 0.0066938 | 0.076377 | 0
| 0 | 0.0034413 | 0.039266 | 0
| 0 | 0.0033292 | 0.037987 | 0
| 0 | 0.0033762 | 0.038523 | 0
| 0 | 0.0058698 | 0.066974 | 0
| 0 | 0.0051892 | 0.059209 | 0
| 0 | 0.003597 | 0.041042 | 0
| 0 | 0.0056994 | 0.065031 | 0
| 0 | 0.00063 | 0.0071884 | 0
| 0 | 0.0065333 | 0.074545 | 0
| 0 | 0.0021686 | 0.024743 | 0
| 0 | 0.001987 | 0.022671 | 0
| 0 | 0.0031826 | 0.036313 | 0
| 0 | 0.011147 | 0.12718 | 0
| 0 | 0.0018253 | 0.020826 | 0
| 0 | 0.00053016 | 0.0060491 | 0
| 0 | 0.0021204 | 0.024193 | 0
| 0 | 0.0012944 | 0.014769 | 0
| 0 | 0.002802 | 0.031971 | 0
| 0 | 7.3952e-05 | 0.00084379 | 0
| 0 | 0.0071111 | 0.081137 | 0
| 0 | 3.2859e-05 | 0.00037492 | 0
| 0 | 0.0028337 | 0.032333 | 0
| 0 | 0.0072444 | 0.082659 | 0
| 0 | 0.0089566 | 0.10219 | 0
| 0 | 0.0032888 | 0.037525 | 0
| 0 | 0.0070562 | 0.080512 | 0
| 0 | 0.00013542 | 0.0015451 | 0
| 0.19818 | 0.00044921 | 0.0051255 | 0
| 0 | 0.00074655 | 0.0085181 | 0
| 0 | 0.00093521 | 0.010671 | 0
| 0 | 0.0023009 | 0.026254 | 0
| 0 | 0.003406 | 0.038862 | 0
| 0 | 3.6886e-05 | 0.00042087 | 0
| 0 | 0.0035962 | 0.041033 | 0
| 0 | 0.009823 | 0.11208 | 0
| 0 | 0.0028152 | 0.032122 | 0
| 0 | 0.0054153 | 0.061788 | 0
| 0 | 0.0095055 | 0.10846 | 0
| 0 | 0.0005283 | 0.0060279 | 0
| 0 | 0.0016094 | 0.018364 | 0
| 0 | 0.0040295 | 0.045976 | 0
| 0 | 0.0048016 | 0.054787 | 0
| 0 | 0.0040012 | 0.045654 | 0
| 0 | 0.00099401 | 0.011342 | 0
| 0 | 0.0091085 | 0.10393 | 0
| 0 | 0.0060691 | 0.069248 | 0
| 0 | 0.000184 | 0.0020994 | 0
| 0.12257 | 8.5829e-05 | 0.0009793 | 0
| 0 | 0.0022311 | 0.025457 | 0
| 0 | 0.0013606 | 0.015524 | 0
| 0 | 0.017969 | 0.20503 | 0
| 0 | 0.00038814 | 0.0044287 | 0
| 0 | 0.0046821 | 0.053422 | 0
| 0 | 0.0063813 | 0.072811 | 0
| 0 | 0.0046077 | 0.052574 | 0
| 0 | 0.00015926 | 0.0018171 | 0
| 0 | 0.0095551 | 0.10902 | 0
| 0 | 0.0047364 | 0.054043 | 0
| 0 | 3.6747e-05 | 0.00041928 | 0
| 0 | 0.00368 | 0.041989 | 0
| 0 | 0.0036351 | 0.041476 | 0
| 0 | 0.00081959 | 0.0093516 | 0
| 0 | 0.0045621 | 0.052053 | 0
| 0.57786 | 0.0088306 | 0.10076 | 0
| 0 | 0.0010599 | 0.012093 | 0
| 0 | 0.0025875 | 0.029524 | 0
| 0 | 0.0032129 | 0.03666 | 0
| 0 | 0.002687 | 0.030659 | 0
| 0 | 0.0071445 | 0.081519 | 0
| 0 | 0.0013433 | 0.015327 | 0
| 0 | 0.0016808 | 0.019178 | 0
| 0 | 0.0088879 | 0.10141 | 0
| 0 | 0.0031989 | 0.0365 | 0
| 0 | 0.0091538 | 0.10444 | 0
| 0 | 0.003461 | 0.03949 | 0
| 0 | 0.0084655 | 0.096592 | 0
| 0 | 0.005666 | 0.064649 | 0
| 0 | 0.0045966 | 0.052447 | 0
| 0.84658 | 0.011582 | 0.13215 | 0
| 0 | 0.0030903 | 0.035261 | 0
| 0 | 8.5321e-05 | 0.00097351 | 0
| 0 | 0.0018524 | 0.021136 | 0
| 0 | 0.0064666 | 0.073784 | 0
| 0 | 0.0011327 | 0.012924 | 0
| 0 | 0.0081358 | 0.092829 | 0
| 0 | 0.0023817 | 0.027176 | 0
| 0 | 0.0073003 | 0.083297 | 0
| 0 | 0.0023964 | 0.027343 | 0
| 0 | 0.0087584 | 0.099933 | 0
| 0 | 0.0051576 | 0.058849 | 0
| 0 | 0.0032431 | 0.037004 | 0
| 0 | 0.0086348 | 0.098523 | 0
| 0 | 0.0051077 | 0.058279 | 0
| 0 | 0.014578 | 0.16634 | 0
| 0 | 0.0033523 | 0.03825 | 0
| 0 | 0.013563 | 0.15475 | 0
| 0 | 0.0022429 | 0.025592 | 0
| 0 | 0.0011416 | 0.013025 | 0
| 0 | 0.010662 | 0.12165 | 0
| 0 | 0.012715 | 0.14508 | 0
| 0 | 0.0021825 | 0.024902 | 0
| 0 | 0.0016499 | 0.018826 | 0
| 0 | 0.0017062 | 0.019468 | 0
| 0 | 0.0035289 | 0.040265 | 0
| 0 | 0.0002425 | 0.002767 | 0
| 2.4536 | 0.014051 | 0.16032 | 0
| 0 | 0.0060965 | 0.069561 | 0
| 0 | 0.005375 | 0.061328 | 0
| 0 | 0.0019107 | 0.021801 | 0
| 0 | 0.00010876 | 0.001241 | 0
| 0 | 0.005763 | 0.065756 | 0
| 0 | 1.2075e-05 | 0.00013778 | 0
| 0 | 0.00012477 | 0.0014236 | 0
| 0 | 0.0046848 | 0.053453 | 0
| 0 | 0.00045875 | 0.0052343 | 0
| 0 | 0.0069779 | 0.079618 | 0
| 0 | 0.0021359 | 0.024371 | 0
| 0 | 0.0017803 | 0.020313 | 0
| 0 | 0.0081977 | 0.093536 | 0
| 0 | 0.0036936 | 0.042144 | 0
| 0 | 0.0037455 | 0.042736 | 0
| 0 | 0.0038654 | 0.044105 | 0
| 0 | 0.010452 | 0.11926 | 0
| 0 | 0.0089347 | 0.10194 | 0
| 0 | 0.0036724 | 0.041902 | 0
| 0 | 0.00021667 | 0.0024722 | 0
| 0 | 0.0024429 | 0.027873 | 0
| 0 | 0.0073166 | 0.083482 | 0
| 0 | 0.0090358 | 0.1031 | 0
| 0 | 0.0098399 | 0.11227 | 0
| 0 | 0.0037891 | 0.043234 | 0
| 0 | 0.005786 | 0.066018 | 0
| 0 | 0.0066392 | 0.075753 | 0
| 0 | 0.0047735 | 0.054466 | 0
| 0 | 0.0027523 | 0.031403 | 0
| 0 | 0.0060558 | 0.069097 | 0
| 0 | 0.0077137 | 0.088013 | 0
| 0 | 0.0041206 | 0.047016 | 0
| 0 | 1.2011e-05 | 0.00013705 | 0
| 0 | 8.0037e-06 | 9.1322e-05 | 0
| 0 | 0.0072383 | 0.082589 | 0
| 0 | 0.0042371 | 0.048345 | 0
| 0 | 0.0050372 | 0.057475 | 0
| 0 | 0.0038856 | 0.044335 | 0
| 0 | 0.0028777 | 0.032835 | 0
| 0 | 0.00012788 | 0.0014591 | 0
| 0 | 0.0042435 | 0.048418 | 0
| 0 | 1.9979e-05 | 0.00022796 | 0
| 0 | 1.9976e-05 | 0.00022793 | 0
| 0 | 0.0030798 | 0.035141 | 0
| 0 | 0.0011983 | 0.013673 | 0
| 0 | 2.3966e-05 | 0.00027345 | 0
| 0 | 0.002648 | 0.030214 | 0
| 0 | 0.0040458 | 0.046162 | 0
| 0.78039 | 0.0026239 | 0.029938 | 0
| 0 | 0.0036539 | 0.041691 | 0
| 0 | 0.0072472 | 0.082691 | 0
| 0 | 0.011946 | 0.13631 | 0
| 0 | 0.00080214 | 0.0091525 | 0
| 0 | 0.0041768 | 0.047657 | 0
| 0 | 3.5881e-05 | 0.0004094 | 0
| 0 | 0.0061218 | 0.06985 | 0
| 0 | 0.0041958 | 0.047874 | 0
| 0 | 0.0057134 | 0.06519 | 0
| 0 | 0.0023984 | 0.027366 | 0
| 0 | 0.0090108 | 0.10281 | 0
| 0 | 0.0012905 | 0.014725 | 0
| 0 | 0.00076455 | 0.0087235 | 0
| 0 | 0.00041809 | 0.0047704 | 0
| 0 | 0.004167 | 0.047546 | 0
| 0 | 0.0024831 | 0.028332 | 0
| 0 | 0.0067564 | 0.07709 | 0
| 0 | 0.0019325 | 0.02205 | 0
| 0 | 0.0010337 | 0.011794 | 0
| 0 | 0.0069951 | 0.079814 | 0
| 0 | 0.005288 | 0.060336 | 0
| 0 | 5.9626e-05 | 0.00068033 | 0
| 0 | 0.0062465 | 0.071273 | 0
| 0 | 0.010275 | 0.11724 | 0
| 0 | 0.0025375 | 0.028953 | 0
| 0 | 0.0068769 | 0.078465 | 0
| 0 | 0.0031387 | 0.035813 | 0
| 0 | 0.0041417 | 0.047257 | 0
| 0 | 0.0080668 | 0.092043 | 0
| 0 | 5.1557e-05 | 0.00058827 | 0
| 0 | 0.0090508 | 0.10327 | 0
| 0 | 0.00065409 | 0.0074632 | 0
| 0 | 0.017399 | 0.19853 | 0
| 0 | 0.0056054 | 0.063957 | 0
| 0 | 0.00067727 | 0.0077276 | 0
| 0 | 0.0021857 | 0.024939 | 0
| 0 | 0.010828 | 0.12355 | 0
| 0 | 0.0037282 | 0.042539 | 0
| 0 | 0.00085465 | 0.0097516 | 0
| 0 | 0.00036793 | 0.0041981 | 0
| 0 | 0.00108 | 0.012323 | 0
| 0 | 0.0033349 | 0.038052 | 0
| 0 | 0.0047225 | 0.053884 | 0
| 0 | 0.00036782 | 0.0041968 | 0
| 0 | 0.0049446 | 0.056418 | 0
| 0 | 0.0051099 | 0.058304 | 0
| 0 | 0.0080969 | 0.092385 | 0
| 0 | 0.004002 | 0.045663 | 0
| 0 | 0.0029148 | 0.033258 | 0
| 0 | 0.0031988 | 0.036499 | 0
| 0 | 0.0010307 | 0.01176 | 0
| 0 | 0.00341 | 0.038908 | 0
| 0 | 0.0093245 | 0.10639 | 0
| 0 | 0.005578 | 0.063645 | 0
| 0 | 0.0040114 | 0.045771 | 0
| 0 | 0.0019406 | 0.022142 | 0
| 0 | 0.0017982 | 0.020518 | 0
| 0 | 0.018006 | 0.20544 | 0
| 0 | 0.0043641 | 0.049794 | 0
| 0 | 0.0036053 | 0.041137 | 0
| 0.02337 | 0.0017142 | 0.019559 | 0
| 0 | 0.0027069 | 0.030886 | 0
| 0 | 0.0077177 | 0.088058 | 0
| 0 | 0.0044437 | 0.050703 | 0
| 0 | 0.0023273 | 0.026555 | 0
| 0 | 0.0023509 | 0.026823 | 0
| 0 | 0.001701 | 0.019408 | 0
| 0 | 0.0067681 | 0.077224 | 0
| 0 | 1.1809e-05 | 0.00013474 | 0
| 0 | 0.0031282 | 0.035693 | 0
| 0 | 0.0037276 | 0.042532 | 0
| 0 | 0.0035799 | 0.040846 | 0
| 0 | 1.1796e-05 | 0.00013459 | 0
| 0 | 0.0067811 | 0.077372 | 0
| 0 | 0.004587 | 0.052338 | 0
| 0 | 0.0038182 | 0.043565 | 0
| 0 | 0.0080947 | 0.092361 | 0
| 0 | 0.0078571 | 0.089649 | 0
| 0 | 0.0021045 | 0.024012 | 0
| 0 | 0.0035609 | 0.04063 | 0
| 0 | 0.0094449 | 0.10777 | 0
| 0 | 7.8507e-06 | 8.9577e-05 | 0
| 0 | 0.0049094 | 0.056017 | 0
| 0 | 0.0075926 | 0.086632 | 0
| 0 | 0.0082032 | 0.093599 | 0
| 0 | 0.0078851 | 0.089969 | 0
| 0 | 0.010144 | 0.11574 | 0
| 0 | 0.0024157 | 0.027563 | 0
| 0 | 0.00079942 | 0.0091214 | 0
| 0 | 0.0035733 | 0.040771 | 0
| 0 | 0.0051011 | 0.058204 | 0
| 0 | 2.3506e-05 | 0.0002682 | 0
| 0 | 0.011017 | 0.1257 | 0
| 0 | 0.003073 | 0.035063 | 0
| 0 | 0.0036115 | 0.041207 | 0
| 0 | 0.0032981 | 0.037632 | 0
| 0 | 0.0025346 | 0.02892 | 0
| 0 | 0.0014312 | 0.01633 | 0
| 0 | 0.0043398 | 0.049518 | 0
| 0 | 0.0055122 | 0.062894 | 0
| 0 | 0.00073866 | 0.0084281 | 0
| 0 | 0.0037383 | 0.042654 | 0
| 0 | 0.0072465 | 0.082683 | 0
| 0 | 0.00062041 | 0.0070789 | 0
| 0 | 0.0038027 | 0.043389 | 0
| 0 | 0.0061747 | 0.070453 | 0
| 0.069549 | 0.0021088 | 0.024062 | 0
| 0 | 0.0020098 | 0.022932 | 0
| 0 | 0.00555 | 0.063326 | 0
| 0 | 0.0050354 | 0.057454 | 0
| 0 | 0.0059107 | 0.067441 | 0
| 0 | 0.0052682 | 0.06011 | 0
| 0 | 0.0044616 | 0.050906 | 0
| 0 | 0.00327 | 0.03731 | 0
| 0 | 0.001505 | 0.017173 | 0
| 0 | 0.0013658 | 0.015584 | 0
| 0 | 0.0026014 | 0.029682 | 0
| 0 | 0.0023211 | 0.026484 | 0
| 0 | 0.0015141 | 0.017275 | 0
| 0 | 0.0030194 | 0.034451 | 0
| 0 | 0.0098693 | 0.11261 | 0
| 0 | 1.1657e-05 | 0.000133 | 0
| 0 | 7.7707e-06 | 8.8664e-05 | 0
| 0 | 0.0078551 | 0.089627 | 0
| 0 | 0.007557 | 0.086226 | 0
| 0 | 1.1646e-05 | 0.00013288 | 0
| 0 | 0.00085774 | 0.0097869 | 0
| 0 | 4.6572e-05 | 0.00053139 | 0
| 0 | 0.0035039 | 0.03998 | 0
| 0 | 0.0058783 | 0.067071 | 0
| 0 | 0.0033819 | 0.038588 | 0
| 0 | 0.0029086 | 0.033187 | 0
| 0 | 0.013868 | 0.15823 | 0
| 0 | 0.007467 | 0.085198 | 0
| 0 | 0.00074047 | 0.0084488 | 0
| 0 | 0.0042562 | 0.048563 | 0
| 0 | 0.00024417 | 0.002786 | 0
| 0 | 0.0032306 | 0.036861 | 0
| 0 | 0.00019754 | 0.002254 | 0
| 0 | 0.012793 | 0.14597 | 0
| 0 | 0.0023122 | 0.026383 | 0
| 0 | 0.00017425 | 0.0019882 | 0
| 0 | 0.0011035 | 0.012591 | 0
| 0 | 0.00031363 | 0.0035785 | 0
| 1.4239 | 0.0045765 | 0.052218 | 0
| 0 | 0.0002206 | 0.0025171 | 0
| 0 | 0.0029684 | 0.033869 | 0
| 0 | 0.0017531 | 0.020003 | 0
| 0 | 0.0039 | 0.044499 | 0
| 0 | 0.001472 | 0.016796 | 0
| 0 | 0.0022093 | 0.025208 | 0
| 0 | 0.0097575 | 0.11133 | 0
| 0 | 0.0097116 | 0.11081 | 0
| 0 | 0.0020603 | 0.023509 | 0
| 0 | 0.00019675 | 0.0022449 | 0
| 0 | 0.010692 | 0.12199 | 0
| 0 | 0.00056668 | 0.0064658 | 0
| 0 | 0.0068808 | 0.07851 | 0
| 0 | 0.0041474 | 0.047322 | 0
| 0 | 0.011957 | 0.13642 | 0
| 0 | 0.0021256 | 0.024253 | 0
| 0 | 0.0092059 | 0.10504 | 0
| 0 | 0.0016273 | 0.018568 | 0
| 0 | 0.0054011 | 0.061626 | 0
| 0 | 0.0080004 | 0.091284 | 0
| 0 | 0.0049106 | 0.05603 | 0
| 0 | 0.0024899 | 0.028409 | 0
| 0 | 0.0039536 | 0.045111 | 0
| 0 | 0.0044815 | 0.051133 | 0
| 0 | 0.0050261 | 0.057348 | 0
| 0 | 0.0073497 | 0.08386 | 0
| 0 | 0.0034198 | 0.03902 | 0
| 0 | 0.00077135 | 0.0088012 | 0
| 0 | 0.0019913 | 0.022721 | 0
| 0 | 0.0038329 | 0.043733 | 0
| 0 | 0.0042701 | 0.048722 | 0
| 0 | 0.0089982 | 0.10267 | 0
| 0 | 0.0033132 | 0.037803 | 0
| 0 | 0.0089342 | 0.10194 | 0
| 0 | 0.0050258 | 0.057345 | 0
| 0 | 0.0099979 | 0.11408 | 0
| 0 | 0.0046652 | 0.05323 | 0
| 0 | 5.7451e-05 | 0.00065552 | 0
| 0 | 0.0023432 | 0.026736 | 0
| 0 | 0.0081618 | 0.093126 | 0
| 0 | 0.0066454 | 0.075824 | 0
| 0 | 0.0021111 | 0.024088 | 0
| 0 | 0.0049098 | 0.056021 | 0
| 0 | 3.4399e-05 | 0.0003925 | 0
| 0 | 0.00064188 | 0.0073239 | 0
| 0 | 0.0029797 | 0.033998 | 0
| 0 | 0.0035411 | 0.040404 | 0
| 0 | 0.0023598 | 0.026926 | 0
| 0 | 0.0012864 | 0.014677 | 0
| 0 | 0.0061769 | 0.070478 | 0
| 0 | 0.0038685 | 0.044139 | 0
| 0 | 1.1444e-05 | 0.00013058 | 0
| 0 | 0.0067279 | 0.076766 | 0
| 0 | 0.0020481 | 0.023369 | 0
| 0 | 0.0018526 | 0.021139 | 0
| 0 | 0.0076764 | 0.087588 | 0
| 0.29601 | 0.0069628 | 0.079445 | 0
| 0 | 0.0018635 | 0.021263 | 0
| 0 | 0.0048928 | 0.055827 | 0
| 0 | 0.0065123 | 0.074306 | 0
| 0 | 0.0094184 | 0.10746 | 0
| 0 | 0.0046122 | 0.052625 | 0
| 0 | 0.012458 | 0.14214 | 0
| 0 | 0.0042611 | 0.048619 | 0
| 0 | 0.0036148 | 0.041245 | 0
| 0 | 0.0047889 | 0.054641 | 0
| 0 | 0.0072493 | 0.082715 | 0
| 0 | 0.0022188 | 0.025317 | 0
| 0 | 0.0016523 | 0.018853 | 0
| 0 | 0.0034369 | 0.039215 | 0
| 1.3894 | 0.0041124 | 0.046922 | 0
| 0 | 0.0074158 | 0.084614 | 0
| 0 | 0.0061853 | 0.070575 | 0
| 0 | 0.0011125 | 0.012694 | 0
| 0 | 0.0094424 | 0.10774 | 0
| 0 | 0.00036443 | 0.0041581 | 0
| 0.10971 | 0.0005806 | 0.0066246 | 0
| 0 | 0.0043557 | 0.049699 | 0
| 0 | 0.0048046 | 0.05482 | 0
| 0 | 0.00042081 | 0.0048014 | 0
| 0 | 0.0055045 | 0.062806 | 0
| 0 | 0.0041511 | 0.047364 | 0
| 0 | 0.0080573 | 0.091933 | 0
| 0 | 0.0033772 | 0.038534 | 0
| 0 | 0.014167 | 0.16164 | 0
| 0 | 0.0041702 | 0.047582 | 0
| 0 | 0.004227 | 0.04823 | 0
| 0 | 1.1359e-05 | 0.0001296 | 0
| 0 | 0.0042251 | 0.048209 | 0
| 0 | 1.1354e-05 | 0.00012955 | 0
| 0 | 0.0031336 | 0.035754 | 0
| 0 | 0.011813 | 0.13479 | 0
| 0 | 0.0017246 | 0.019678 | 0
| 0 | 0.005427 | 0.061922 | 0
| 0 | 0.0031193 | 0.035591 | 0
| 0 | 0.0034736 | 0.039634 | 0
| 0 | 0.0014482 | 0.016524 | 0
| 0 | 0.00023753 | 0.0027102 | 0
| 0 | 0.0036516 | 0.041665 | 0
| 0 | 0.0016014 | 0.018272 | 0
| 0 | 0.0079337 | 0.090524 | 0
| 0 | 0.011201 | 0.1278 | 0
| 0 | 0.00071129 | 0.0081158 | 0
| 0 | 0.0091391 | 0.10428 | 0
| 0.10022 | 0.0001016 | 0.0011593 | 0
| 0 | 0.0070076 | 0.079956 | 0
| 0 | 0.0098228 | 0.11208 | 0
| 0 | 0.0005601 | 0.0063908 | 0
| 0 | 0.0036763 | 0.041946 | 0
| 0 | 0.0036419 | 0.041554 | 0
| 0 | 0.0014205 | 0.016208 | 0
| 0 | 0.020796 | 0.23728 | 0
| 0 | 0.0030964 | 0.03533 | 0
| 0 | 0.0021192 | 0.02418 | 0
| 0 | 0.0030197 | 0.034455 | 0
| 0 | 0.0040218 | 0.045889 | 0
| 0 | 0.0028386 | 0.032388 | 0
| 0 | 0.0021623 | 0.024671 | 0
| 0 | 0.0062726 | 0.071571 | 0
| 0 | 0.004038 | 0.046074 | 0
| 0 | 0.0096766 | 0.11041 | 0
| 0 | 0.0038717 | 0.044176 | 0
| 0 | 0.0025659 | 0.029277 | 0
| 0 | 0.0060994 | 0.069595 | 0
| 0 | 0.0014059 | 0.016042 | 0
| 0 | 0.0026727 | 0.030496 | 0
| 0 | 1.1244e-05 | 0.00012829 | 0
| 0 | 0.0078802 | 0.089913 | 0
| 0 | 0.0048782 | 0.05566 | 0
| 0 | 0.0041231 | 0.047045 | 0
| 0 | 0.0048084 | 0.054864 | 0
| 0 | 0.0068639 | 0.078318 | 0
| 0 | 0.0044373 | 0.05063 | 0
| 0 | 0.0037403 | 0.042677 | 0
| 0 | 0.0060183 | 0.068669 | 0
| 0 | 0.00010104 | 0.0011529 | 0
| 0 | 0.0051585 | 0.058858 | 0
| 0 | 0.0017171 | 0.019592 | 0
| 0 | 0.00086396 | 0.0098578 | 0
| 0 | 0.0031409 | 0.035838 | 0
| 0 | 0.0025346 | 0.02892 | 0
| 0 | 0.01277 | 0.1457 | 0
| 0 | 0.0023437 | 0.026741 | 0
| 0 | 0.0043265 | 0.049365 | 0
| 0 | 0.00095242 | 0.010867 | 0
| 0 | 0.0082869 | 0.094553 | 0
| 0 | 0.00078411 | 0.0089467 | 0
| 0 | 0.0028446 | 0.032457 | 0
| 0 | 0.0053721 | 0.061296 | 0
| 0 | 0.0067485 | 0.077 | 0
| 0 | 0.0035365 | 0.040352 | 0
| 0 | 0.00029094 | 0.0033196 | 0
| 0 | 0.0061879 | 0.070604 | 0
| 0 | 0.0076063 | 0.086788 | 0
| 0 | 0.0043946 | 0.050142 | 0
| 0 | 0.006494 | 0.074097 | 0
| 0 | 0.0043991 | 0.050194 | 0
| 0 | 0.0065032 | 0.074202 | 0
| 0 | 0.0013071 | 0.014914 | 0
| 0 | 0.00083787 | 0.0095601 | 0
| 0 | 0.00048026 | 0.0054798 | 0
| 0 | 0.0089114 | 0.10168 | 0
| 0 | 0.0070612 | 0.080568 | 0
| 0 | 0.0012163 | 0.013878 | 0
| 0 | 0.0027282 | 0.031129 | 0
| 0 | 2.2307e-05 | 0.00025453 | 0
| 0 | 0.00020064 | 0.0022893 | 0
| 0 | 0.0016047 | 0.01831 | 0
| 0 | 0.005045 | 0.057563 | 0
| 0 | 0.0045656 | 0.052094 | 0
| 0 | 0.0087173 | 0.099465 | 0
| 0 | 0.0015363 | 0.017529 | 0
| 0 | 0.0040295 | 0.045976 | 0
| 0 | 0.000345 | 0.0039364 | 0
| 0 | 0.014577 | 0.16633 | 0
| 0 | 0.0016577 | 0.018915 | 0
| 0 | 0.0056808 | 0.064818 | 0
| 0.21961 | 0.0012235 | 0.01396 | 0
| 0 | 0.0046602 | 0.053173 | 0
| 0 | 0.016757 | 0.1912 | 0
| 0 | 0.0005893 | 0.0067239 | 0
| 0 | 0.0051584 | 0.058857 | 0
| 0 | 0.0015599 | 0.017799 | 0
| 0 | 0.0011855 | 0.013526 | 0
| 0 | 0.011701 | 0.13351 | 0
| 0 | 0.0023991 | 0.027373 | 0
| 0 | 0.0037759 | 0.043083 | 0
| 0 | 0.0029205 | 0.033323 | 0
| 0 | 0.00014063 | 0.0016046 | 0
| 0 | 0.0028385 | 0.032388 | 0
| 0 | 0.0041956 | 0.047872 | 0
| 0 | 0.0036518 | 0.041667 | 0
| 0 | 0.0048506 | 0.055346 | 0
| 0 | 0.0038549 | 0.043984 | 0
| 0 | 0.0062479 | 0.071289 | 0
| 0 | 0.0023503 | 0.026817 | 0
| 0 | 0.0030257 | 0.034524 | 0
| 0 | 0.0037086 | 0.042316 | 0
| 0 | 0.0077548 | 0.088482 | 0
| 0 | 0.0047076 | 0.053714 | 0
| 0 | 0.0039264 | 0.0448 | 0
| 0 | 0.0011961 | 0.013648 | 0
| 0 | 0.0043192 | 0.049282 | 0
| 0 | 0.00034331 | 0.0039172 | 0
| 0 | 0.011512 | 0.13136 | 0
| 0 | 0.0022026 | 0.025132 | 0
| 0 | 0.0059769 | 0.068197 | 0
| 0 | 0.0038619 | 0.044065 | 0
| 0 | 0.0033331 | 0.038031 | 0
| 0 | 0.0013277 | 0.015149 | 0
| 0 | 0.0084852 | 0.096817 | 0
| 0 | 0.0068364 | 0.078003 | 0
| 0 | 0.008046 | 0.091805 | 0
| 0 | 0.00077403 | 0.0088317 | 0
| 0 | 2.7643e-05 | 0.0003154 | 0
| 0 | 0.0028968 | 0.033052 | 0
| 0 | 0.0084422 | 0.096326 | 0
| 0 | 0.0034102 | 0.03891 | 0
| 0 | 0.0087811 | 0.10019 | 0
| 0.32535 | 0.0011265 | 0.012854 | 0
| 0 | 0.0037302 | 0.042562 | 0
| 0 | 0.0031668 | 0.036134 | 0
| 0 | 0.0013644 | 0.015568 | 0
| 0 | 0.0083615 | 0.095404 | 0
| 0 | 0.0011137 | 0.012708 | 0
| 0 | 0.0032526 | 0.037113 | 0
| 0 | 0.0079488 | 0.090696 | 0
| 0 | 0.0047066 | 0.053702 | 0
| 0 | 0.0031006 | 0.035378 | 0
| 0 | 0.0018402 | 0.020996 | 0
| 0 | 0.0014433 | 0.016468 | 0
| 0 | 0.0013658 | 0.015584 | 0
| 0.87066 | 0.0034145 | 0.038959 | 0
| 0 | 0.0028406 | 0.032411 | 0
| 0 | 0.0092808 | 0.10589 | 0
| 0 | 0.0015522 | 0.01771 | 0
| 0 | 0.00051728 | 0.0059022 | 0
| 0 | 0.0044847 | 0.05117 | 0
| 0 | 0.0043728 | 0.049894 | 0
| 0 | 0.0026463 | 0.030195 | 0
| 0 | 0.0011655 | 0.013298 | 0
| 0 | 0.0062231 | 0.071005 | 0
| 0 | 0.00025654 | 0.0029272 | 0
| 0 | 0.0015716 | 0.017932 | 0
| 0 | 0.0066049 | 0.075362 | 0
| 0 | 0.0045277 | 0.051661 | 0
| 0 | 0.0019667 | 0.02244 | 0
| 0 | 0.0010547 | 0.012035 | 0
| 0 | 2.197e-05 | 0.00025067 | 0
| 0 | 0.0087649 | 0.10001 | 0
| 0 | 0.0030457 | 0.034752 | 0
| 0 | 0.0043489 | 0.049621 | 0
| 0 | 0.0034585 | 0.039461 | 0
| 0 | 0.0066812 | 0.076232 | 0
| 0 | 0.0045277 | 0.051661 | 0
| 0 | 0.00016464 | 0.0018786 | 0
| 0 | 0.0043968 | 0.050167 | 0
| 0 | 0.0022161 | 0.025286 | 0
| 0 | 0.005112 | 0.058328 | 0
| 0 | 2.1937e-05 | 0.0002503 | 0
| 0 | 0.00065442 | 0.0074669 | 0
| 0 | 0.0019851 | 0.022649 | 0
| 0 | 0.0075451 | 0.08609 | 0
| 0 | 0.0019555 | 0.022312 | 0
| 0 | 0.0023124 | 0.026384 | 0
| 0 | 0.0028055 | 0.032011 | 0
| 0 | 0.010726 | 0.12238 | 0
| 0 | 2.191e-05 | 0.00024999 | 0
| 0 | 0.0048847 | 0.055735 | 0
| 0 | 0.01083 | 0.12357 | 0
| 0 | 0.0057145 | 0.065202 | 0
| 0 | 0.00087561 | 0.0099907 | 0
| 0 | 0.0035297 | 0.040274 | 0
| 0 | 0.00072227 | 0.0082411 | 0
| 0 | 0.0044977 | 0.051319 | 0
| 0 | 0.01301 | 0.14844 | 0
| 0 | 0.00033919 | 0.0038701 | 0
| 0 | 0.0050343 | 0.057441 | 0
| 0 | 0.003935 | 0.044898 | 0
| 0 | 0.0035634 | 0.040658 | 0
| 0 | 0.0035275 | 0.040249 | 0
| 0 | 0.0021615 | 0.024663 | 0
| 0 | 0.0080006 | 0.091287 | 0
| 0 | 0.0067739 | 0.077291 | 0
| 0 | 0.0026281 | 0.029987 | 0
| 0 | 0.0027914 | 0.03185 | 0
| 0 | 0.015163 | 0.17301 | 0
| 0 | 0.0035 | 0.039935 | 0
| 0 | 0.0050482 | 0.0576 | 0
| 0 | 0.008155 | 0.093049 | 0
| 0 | 0.0012097 | 0.013803 | 0
| 9.121 | 0.003331 | 0.038007 | 0
| 0 | 0.00075078 | 0.0085664 | 0
| 0 | 0.0014432 | 0.016467 | 0
| 0 | 0.00089193 | 0.010177 | 0
| 0 | 0.00092455 | 0.010549 | 0
| 0 | 0.0048072 | 0.05485 | 0
| 0 | 0.0055137 | 0.062912 | 0
| 0 | 0.0069916 | 0.079774 | 0
| 0 | 0.0032392 | 0.036959 | 0
| 0 | 0.00046716 | 0.0053303 | 0
| 0 | 2.1728e-05 | 0.00024792 | 0
| 0.047804 | 0.00019551 | 0.0022308 | 0
| 0 | 0.0018208 | 0.020776 | 0
| 0 | 0.006991 | 0.079768 | 0
| 0 | 0.0022573 | 0.025755 | 0
| 0.016462 | 0.0029807 | 0.03401 | 0
| 0 | 0.0049594 | 0.056586 | 0
| 0 | 0.0035546 | 0.040558 | 0
| 0 | 0.0020936 | 0.023888 | 0
| 0 | 0.0025961 | 0.029621 | 0
| 0 | 0.0042588 | 0.048592 | 0
| 0 | 0.0037721 | 0.04304 | 0
| 0 | 0.0014956 | 0.017065 | 0
| 0 | 0.00053102 | 0.006059 | 0
| 0 | 0.0082572 | 0.094215 | 0
| 0 | 0.0039199 | 0.044726 | 0
| 0 | 0.00073631 | 0.0084013 | 0
| 0 | 0.0095602 | 0.10908 | 0
| 0 | 0.014506 | 0.16551 | 0
| 0 | 0.0036371 | 0.0415 | 0
| 0 | 0.013357 | 0.1524 | 0
| 0 | 0.00197 | 0.022477 | 0
| 0 | 6.4931e-05 | 0.00074087 | 0
| 0 | 0.010075 | 0.11496 | 0
| 0 | 0.0047608 | 0.05432 | 0
| 0 | 0.0001605 | 0.0018313 | 0
| 0 | 0.0037544 | 0.042838 | 0
| 0 | 0.0022394 | 0.025551 | 0
| 0 | 0.0075831 | 0.086524 | 0
| 0 | 0.0030609 | 0.034925 | 0
| 0 | 0.0044407 | 0.050669 | 0
| 0 | 7.2028e-06 | 8.2185e-05 | 0
| 0 | 0.0028291 | 0.03228 | 0
| 0 | 0.0049672 | 0.056676 | 0
| 0 | 0.0034228 | 0.039054 | 0
| 0 | 0.0095663 | 0.10915 | 0
| 0 | 0.0025877 | 0.029526 | 0
| 0 | 0.017059 | 0.19464 | 0
| 0 | 0.0030736 | 0.03507 | 0
| 0 | 0.0008731 | 0.0099621 | 0
| 0 | 0.0091032 | 0.10387 | 0
| 0 | 0.0022513 | 0.025687 | 0
| 0 | 0.0036296 | 0.041414 | 0
| 0 | 0.0050836 | 0.058003 | 0
| 0 | 0.006354 | 0.0725 | 0
| 0 | 0.0052436 | 0.05983 | 0
| 0 | 0.0036062 | 0.041146 | 0
| 0 | 0.0091822 | 0.10477 | 0
| 0 | 0.0013562 | 0.015474 | 0
| 0 | 0.00358 | 0.040847 | 0
| 0 | 0.0039601 | 0.045185 | 0
| 0 | 0.0015563 | 0.017758 | 0
| 0 | 0.0086466 | 0.098658 | 0
| 0 | 0.0050723 | 0.057875 | 0
| 0 | 0.0055563 | 0.063397 | 0
| 0 | 0.0089991 | 0.10268 | 0
| 0 | 0.007057 | 0.08052 | 0
| 0 | 0.0041703 | 0.047583 | 0
| 0 | 0.0037711 | 0.043028 | 0
| 0 | 0.0028359 | 0.032358 | 0
| 0 | 0.0018796 | 0.021446 | 0
| 0 | 0.0072062 | 0.082223 | 0
| 0 | 0.0051762 | 0.059061 | 0
| 0 | 0.0076227 | 0.086975 | 0
| 0 | 0.0043371 | 0.049487 | 0
| 0 | 0.0060325 | 0.068831 | 0
| 0 | 0.0055947 | 0.063835 | 0
| 0 | 0.0019493 | 0.022241 | 0
| 0 | 0.00024678 | 0.0028158 | 0
| 0 | 0.003808 | 0.04345 | 0
| 0 | 6.4351e-05 | 0.00073425 | 0
| 0 | 0.0028743 | 0.032796 | 0
| 0 | 0.0050271 | 0.057359 | 0
| 0 | 0.0020792 | 0.023724 | 0
| 0 | 0.010155 | 0.11587 | 0
| 0 | 0.0018709 | 0.021347 | 0
| 0 | 0.0029544 | 0.033709 | 0
| 0 | 0.0080652 | 0.092024 | 0
| 0 | 0.00014613 | 0.0016674 | 0
| 0 | 0.0080825 | 0.092222 | 0
| 0 | 0.0015288 | 0.017444 | 0
| 0 | 1.7817e-05 | 0.00020329 | 0
| 0 | 0.0123 | 0.14034 | 0
| 0 | 0.0031298 | 0.035711 | 0
| 0 | 0.0010041 | 0.011456 | 0
| 0 | 0.011994 | 0.13685 | 0
| 0 | 0.003021 | 0.03447 | 0
| 0 | 0.0038074 | 0.043442 | 0
| 0 | 0.00060842 | 0.006942 | 0
| 0 | 0.004499 | 0.051333 | 0
| 0 | 0.00090715 | 0.010351 | 0
| 0 | 0.0054108 | 0.061737 | 0
| 0 | 0.0042772 | 0.048803 | 0
| 0 | 0.001866 | 0.021291 | 0
| 0 | 0.0039345 | 0.044893 | 0
| 0 | 0.0026531 | 0.030272 | 0
| 0 | 0.003548 | 0.040483 | 0
| 0 | 0.0014488 | 0.016531 | 0
| 0 | 0.0013066 | 0.014908 | 0
| 0 | 0.0053234 | 0.060739 | 0
| 0.042072 | 0.0011284 | 0.012875 | 0
| 0 | 0.0057373 | 0.065463 | 0
| 0 | 0.0012235 | 0.01396 | 0
| 0 | 0.0047549 | 0.054253 | 0
| 0 | 0.010907 | 0.12445 | 0
| 0 | 0.0086067 | 0.098202 | 0
| 0 | 0.0034001 | 0.038795 | 0
| 0 | 0.0023689 | 0.02703 | 0
| 0 | 0.0023155 | 0.026419 | 0
| 0 | 0.0038076 | 0.043445 | 0
| 0 | 0.0040013 | 0.045655 | 0
| 0 | 0.0045645 | 0.052081 | 0
| 0 | 0.011875 | 0.1355 | 0
| 0 | 0.0029165 | 0.033277 | 0
| 0 | 0.0058963 | 0.067277 | 0
| 0 | 1.7664e-05 | 0.00020155 | 0
| 0 | 0.00070994 | 0.0081004 | 0
| 0 | 0.0044815 | 0.051133 | 0
| 0 | 0.0069773 | 0.07961 | 0
| 0 | 0.0092794 | 0.10588 | 0
| 0 | 0.0014724 | 0.0168 | 0
| 0 | 0.010528 | 0.12013 | 0
| 0 | 0.0022446 | 0.02561 | 0
| 0 | 0.0060657 | 0.06921 | 0
| 0 | 0.0054092 | 0.061719 | 0
| 0 | 1.0583e-05 | 0.00012075 | 0
| 0 | 6.3456e-05 | 0.00072403 | 0
| 0 | 0.00063448 | 0.0072394 | 0
| 0 | 0.0027348 | 0.031204 | 0
| 0 | 0.0012579 | 0.014353 | 0
| 0 | 0.0093339 | 0.1065 | 0
| 0 | 0.010327 | 0.11783 | 0
| 0 | 0.0011303 | 0.012897 | 0
| 0 | 0.0028624 | 0.03266 | 0
| 0 | 0.00038016 | 0.0043377 | 0
| 0 | 0.0030694 | 0.035021 | 0
| 0 | 5.2779e-06 | 6.0221e-05 | 0
| 0 | 0.00152 | 0.017343 | 0
| 0 | 0.0017732 | 0.020232 | 0
| 0 | 0.0018855 | 0.021514 | 0
| 0 | 0.0014559 | 0.016612 | 0
| 0 | 0.0053342 | 0.060863 | 0
| 0 | 0.0061208 | 0.069838 | 0
| 0 | 0.0055556 | 0.06339 | 0
| 0 | 0.0043863 | 0.050047 | 0
| 0 | 0.0023087 | 0.026342 | 0
| 0.74129 | 0.00098017 | 0.011184 | 0
| 0 | 0.004236 | 0.048333 | 0
| 0 | 0.0035821 | 0.040871 | 0
| 0 | 0.00028437 | 0.0032447 | 0
| 0 | 0.00061613 | 0.00703 | 0
| 0 | 0.0023377 | 0.026673 | 0
| 0 | 0.0031484 | 0.035924 | 0
| 0 | 0.005263 | 0.060051 | 0
| 0 | 0.004284 | 0.04888 | 0
| 0 | 0.0034273 | 0.039106 | 0
| 0 | 0.0065767 | 0.07504 | 0
| 0 | 3.1548e-05 | 0.00035997 | 0
| 0 | 0.001304 | 0.014879 | 0
| 0 | 0.0085666 | 0.097745 | 0
| 0 | 0.00049375 | 0.0056337 | 0
| 0 | 0.0048423 | 0.05525 | 0
| 0 | 0.0086443 | 0.098631 | 0
| 0 | 0.00044812 | 0.0051131 | 0
| 0 | 0.0076119 | 0.086852 | 0
| 0 | 0.0022044 | 0.025153 | 0
| 0 | 0.0032643 | 0.037246 | 0
| 0 | 0.014543 | 0.16593 | 0
| 0 | 0.002004 | 0.022866 | 0
| 0 | 0.0021088 | 0.024062 | 0
| 0 | 0.00080784 | 0.0092174 | 0
| 0 | 0.00087071 | 0.0099348 | 0
| 0 | 0.0034198 | 0.03902 | 0
| 0 | 0.011843 | 0.13513 | 0
| 0 | 0.0058076 | 0.066265 | 0
| 0.61113 | 0.003542 | 0.040415 | 0
| 0 | 0.0018863 | 0.021523 | 0
| 0 | 0.0085945 | 0.098063 | 0
| 0 | 0.002481 | 0.028308 | 0
| 0 | 0.0025925 | 0.029581 | 0
| 0 | 0.0039614 | 0.0452 | 0
| 0 | 0.0031951 | 0.036457 | 0
| 0 | 0.0043634 | 0.049787 | 0
| 0 | 0.013023 | 0.14859 | 0
| 0 | 0.0071114 | 0.081141 | 0
| 0 | 0.006913 | 0.078877 | 0
| 0 | 0.00032322 | 0.0036879 | 0
| 0 | 0.0034089 | 0.038896 | 0
| 0 | 0.0042085 | 0.048019 | 0
| 0 | 0.0018646 | 0.021275 | 0
| 0 | 0.0065703 | 0.074968 | 0
| 0 | 0.0068198 | 0.077814 | 0
| 0 | 0.0060267 | 0.068765 | 0
| 0 | 0.009543 | 0.10889 | 0
| 0 | 0.001509 | 0.017217 | 0
| 0 | 0.010955 | 0.12499 | 0
| 0 | 0.0067494 | 0.07701 | 0
| 0 | 0.0088211 | 0.10065 | 0
| 0 | 0.0013724 | 0.01566 | 0
| 0 | 0.016364 | 0.18671 | 0
| 0 | 0.011176 | 0.12752 | 0
| 0 | 0.00073808 | 0.0084214 | 0
| 0 | 0.0032328 | 0.036887 | 0
| 0 | 0.0029411 | 0.033558 | 0
| 0 | 0.0063644 | 0.072618 | 0
| 0 | 0.003209 | 0.036615 | 0
| 0 | 0.0091908 | 0.10487 | 0
| 0 | 0.0024499 | 0.027953 | 0
| 0 | 0.0020553 | 0.023451 | 0
| 0 | 0.0059064 | 0.067392 | 0
| 0 | 0.001557 | 0.017766 | 0
| 0 | 0.012797 | 0.14601 | 0
| 0 | 0.0020236 | 0.023089 | 0
| 0 | 0.012172 | 0.13888 | 0
| 0 | 0.00070556 | 0.0080505 | 0
| 0 | 0.0056333 | 0.064276 | 0
| 0 | 0.0013971 | 0.01594 | 0
| 0 | 0.0088145 | 0.10057 | 0
| 0 | 0.0087164 | 0.099454 | 0
| 0 | 0.0040642 | 0.046372 | 0
| 0 | 0.00099519 | 0.011355 | 0
| 0 | 0.0080192 | 0.091499 | 0
| 0 | 0.016765 | 0.19129 | 0
| 0 | 0.010983 | 0.12532 | 0
| 0 | 0.0039591 | 0.045173 | 0
| 0 | 0.0033876 | 0.038652 | 0
| 0 | 0.0075228 | 0.085835 | 0
| 0 | 0.0014976 | 0.017087 | 0
| 0 | 0.00084879 | 0.0096847 | 0
| 0 | 7.2441e-05 | 0.00082655 | 0
| 0 | 0.0058882 | 0.067184 | 0
| 0 | 0.0028043 | 0.031997 | 0
| 0 | 0.0022969 | 0.026208 | 0
| 0 | 0.012666 | 0.14452 | 0
| 0 | 0.0018002 | 0.02054 | 0
| 0 | 0.0028347 | 0.032344 | 0
| 0 | 2.0684e-05 | 0.00023601 | 0
| 0 | 0.0022132 | 0.025252 | 0
| 0 | 0.00016546 | 0.0018879 | 0
| 0 | 0.0064733 | 0.073861 | 0
| 0 | 0.0093959 | 0.10721 | 0
| 0 | 0.0044281 | 0.050524 | 0
| 0.73862 | 0.0051583 | 0.058857 | 0
| 0 | 0.0018985 | 0.021661 | 0
| 0 | 0.0010646 | 0.012148 | 0
| 0 | 0.0024592 | 0.02806 | 0
| 0 | 0.0016429 | 0.018746 | 0
| 0 | 0.0090202 | 0.10292 | 0
| 0 | 0.0019734 | 0.022516 | 0
| 0 | 0.0025192 | 0.028745 | 0
| 0 | 0.0014521 | 0.016568 | 0
| 0 | 0.0065391 | 0.074611 | 0
| 0 | 1.0318e-05 | 0.00011772 | 0
| 0 | 0.0039924 | 0.045553 | 0
| 0 | 0.0028265 | 0.032251 | 0
| 0 | 3.0946e-05 | 0.0003531 | 0
| 0 | 0.0041758 | 0.047646 | 0
| 0 | 0.0037519 | 0.042809 | 0
| 0 | 0.0024016 | 0.027402 | 0
| 0 | 0.013872 | 0.15828 | 0
| 0 | 0.00086511 | 0.0098709 | 0
| 0 | 0.0054624 | 0.062326 | 0
| 0 | 0.0050842 | 0.058011 | 0
| 0 | 0.0090963 | 0.10379 | 0
| 0 | 0.0075308 | 0.085927 | 0
| 0 | 0.0004938 | 0.0056342 | 0
| 0 | 0.0016664 | 0.019014 | 0
| 0 | 0.0014297 | 0.016313 | 0
| 0 | 0.0037935 | 0.043284 | 0
| 0 | 0.0072317 | 0.082513 | 0
| 0 | 0.0018588 | 0.021209 | 0
| 0 | 0.017579 | 0.20058 | 0
| 0 | 0.0094001 | 0.10726 | 0
| 1.9225 | 0.00058467 | 0.0066711 | 0
| 0 | 0.0035423 | 0.040417 | 0
| 0.096659 | 0.0033399 | 0.038108 | 0
| 0 | 0.0074116 | 0.084566 | 0
| 0 | 0.0013781 | 0.015724 | 0
| 0 | 1.0232e-05 | 0.00011675 | 0
| 0 | 1.0229e-05 | 0.00011671 | 0
| 0 | 0.0012274 | 0.014005 | 0
| 0 | 0.0015751 | 0.017972 | 0
| 0 | 0.0058501 | 0.066749 | 0
| 0 | 0.00077726 | 0.0088685 | 0
| 0 | 0.00317 | 0.03617 | 0
| 0 | 0.00082818 | 0.0094495 | 0
| 0 | 0.0032201 | 0.036742 | 0
| 0 | 0.0043946 | 0.050143 | 0
| 0 | 0.011772 | 0.13432 | 0
| 0 | 0.0021149 | 0.024131 | 0
| 0 | 0.008936 | 0.10196 | 0
| 0 | 0.0064919 | 0.074072 | 0
| 0 | 0.0028698 | 0.032744 | 0
| 0 | 0.0032573 | 0.037166 | 0
| 0.034341 | 0.0083688 | 0.095488 | 0
| 0 | 0.011369 | 0.12972 | 0
| 0 | 0.0038669 | 0.044121 | 0
| 0 | 0.0004795 | 0.0054711 | 0
| 0 | 0.0052331 | 0.05971 | 0
| 0 | 2.0393e-05 | 0.00023268 | 0
| 0 | 0.0014032 | 0.01601 | 0
| 0 | 0.01188 | 0.13555 | 0
| 0 | 0.0042678 | 0.048696 | 0
| 0 | 0.00070281 | 0.0080191 | 0
| 0 | 0.0066915 | 0.07635 | 0
| 0 | 0.0086193 | 0.098346 | 0
| 0 | 0.012295 | 0.14028 | 0
| 0 | 0.0024117 | 0.027518 | 0
| 0 | 3.7309e-05 | 0.0004257 | 0
| 0 | 0.0023593 | 0.02692 | 0
| 0 | 0.0055615 | 0.063457 | 0
| 0 | 0.0039375 | 0.044926 | 0
| 0 | 0.0082711 | 0.094374 | 0
| 0 | 0.0030375 | 0.034657 | 0
| 0 | 0.0057283 | 0.06536 | 0
| 0 | 0.0022216 | 0.025348 | 0
| 0 | 0.0031445 | 0.035879 | 0
| 0 | 0.007668 | 0.087492 | 0
| 0 | 3.0427e-05 | 0.00034717 | 0
| 0 | 0.0067244 | 0.076726 | 0
| 0.19514 | 0.0010953 | 0.012497 | 0
| 0 | 0.0067744 | 0.077296 | 0
| 0 | 0.0014705 | 0.016778 | 0
| 0 | 0.0061433 | 0.070095 | 0
| 0 | 0.0015915 | 0.018159 | 0
| 0 | 0.0074548 | 0.085059 | 0
| 0 | 0.0053701 | 0.061272 | 0
| 0 | 0.0079935 | 0.091206 | 0
| 0 | 0.0033221 | 0.037905 | 0
| 0 | 0.0016203 | 0.018487 | 0
| 0 | 0.0057247 | 0.065319 | 0
| 0 | 0.0059438 | 0.067819 | 0
| 0 | 0.0084749 | 0.096699 | 0
| 0 | 3.037e-05 | 0.00034652 | 0
| 0 | 0.0033502 | 0.038226 | 0
| 0 | 0.00012818 | 0.0014625 | 0
| 0 | 0.0064966 | 0.074126 | 0
| 0 | 0.0062335 | 0.071124 | 0
| 0 | 0.0025163 | 0.028711 | 0
| 0 | 2.0238e-05 | 0.00023092 | 0
| 0 | 0.0022665 | 0.025861 | 0
| 0 | 0.003875 | 0.044213 | 0
| 0 | 0.0079415 | 0.090612 | 0
| 0 | 0.0054623 | 0.062325 | 0
| 0 | 0.0036005 | 0.041082 | 0
| 0 | 4.0448e-05 | 0.00046152 | 0
| 0 | 0.0025981 | 0.029645 | 0
| 0 | 0.0042358 | 0.048331 | 0
| 0 | 0.0036798 | 0.041986 | 0
| 0 | 0.010369 | 0.11831 | 0
| 0 | 0.00059585 | 0.0067986 | 0
| 0 | 0.0013936 | 0.0159 | 0
| 0 | 0.0032817 | 0.037444 | 0
| 0 | 0.0069361 | 0.079141 | 0
| 0 | 0.0043209 | 0.049301 | 0
| 0.2412 | 0.00036324 | 0.0041446 | 0
| 0 | 0.0039445 | 0.045007 | 0
| 0 | 0.0027535 | 0.031417 | 0
| 0 | 0.010767 | 0.12285 | 0
| 0 | 0.012568 | 0.1434 | 0
| 0 | 0.0016423 | 0.018738 | 0
| 0 | 0.0052991 | 0.060463 | 0
| 0 | 0.0024677 | 0.028156 | 0
| 0 | 0.0045108 | 0.051468 | 0
| 0 | 0.01118 | 0.12756 | 0
| 0 | 0.00077501 | 0.0088428 | 0
| 0 | 0.0046629 | 0.053204 | 0
| 0 | 0.0022743 | 0.02595 | 0
| 0 | 0.0018014 | 0.020553 | 0
| 0 | 0.0056921 | 0.064946 | 0
| 0 | 0.0018711 | 0.021349 | 0
| 0 | 0.0021339 | 0.024348 | 0
| 0 | 0.0094023 | 0.10728 | 0
| 0 | 0.0059926 | 0.068375 | 0
| 0 | 0.0026512 | 0.030251 | 0
| 0 | 0.0044775 | 0.051089 | 0
| 0 | 0.0044654 | 0.05095 | 0
| 0 | 0.0017352 | 0.019798 | 0
| 0 | 0.0055622 | 0.063464 | 0
| 0 | 0.00033085 | 0.003775 | 0
| 0 | 0.00079185 | 0.0090351 | 0
| 0 | 0.0041263 | 0.047081 | 0
| 0 | 0.0039522 | 0.045095 | 0
| 0 | 0.0039447 | 0.045009 | 0
| 0 | 0.0048091 | 0.054872 | 0
| 0 | 0.0094434 | 0.10775 | 0
| 0 | 0.0032844 | 0.037475 | 0
| 0 | 0.0046253 | 0.052775 | 0
| 0 | 0.0094437 | 0.10775 | 0
| 0 | 0.0060405 | 0.068922 | 0
| 0 | 0.0091603 | 0.10452 | 0
| 0 | 0.0046492 | 0.053048 | 0
| 0 | 0.00059982 | 0.006844 | 0
| 0 | 0.0039383 | 0.044936 | 0
| 0 | 0.0012476 | 0.014235 | 0
| 0 | 0.010017 | 0.11429 | 0
| 0 | 0.0036014 | 0.041092 | 0
| 0 | 0.0047582 | 0.054291 | 0
| 0 | 0.0018153 | 0.020712 | 0
| 1.6257 | 0.012026 | 0.13722 | 0
| 0 | 0.0026414 | 0.030138 | 0
| 0 | 0.002611 | 0.029792 | 0
| 0 | 0.0016442 | 0.01876 | 0
| 0 | 0.00092623 | 0.010568 | 0
| 0 | 0.0019916 | 0.022724 | 0
| 0 | 0.0047099 | 0.05374 | 0
| 0 | 0.00062723 | 0.0071567 | 0
| 0 | 0.0045391 | 0.051792 | 0
| 0 | 0.00076641 | 0.0087447 | 0
| 0 | 0.0026869 | 0.030657 | 0
| 0 | 0.0029057 | 0.033154 | 0
| 0 | 0.0031831 | 0.036319 | 0
| 0 | 0.0019695 | 0.022472 | 0
| 0 | 0.011737 | 0.13391 | 0
| 0 | 0.004585 | 0.052315 | 0
| 0 | 0.010724 | 0.12236 | 0
| 0 | 0.00098353 | 0.011222 | 0
| 0 | 0.0011323 | 0.01292 | 0
| 0 | 0.0040276 | 0.045955 | 0
| 0 | 0.0086798 | 0.099037 | 0
| 0 | 0.00016054 | 0.0018318 | 0
| 0 | 0.0027702 | 0.031608 | 0
| 0 | 0.00064518 | 0.0073615 | 0
| 0 | 0.0069061 | 0.078799 | 0
| 0 | 0.00036709 | 0.0041886 | 0
| 0 | 0.0020331 | 0.023198 | 0
| 0 | 0.012462 | 0.14219 | 0
| 0 | 0.0029133 | 0.033241 | 0
| 0 | 0.0015853 | 0.018089 | 0
| 0 | 0.0092437 | 0.10547 | 0
| 0 | 0.0097949 | 0.11176 | 0
| 0 | 0.0050194 | 0.057272 | 0
| 0 | 0.00397 | 0.045298 | 0
| 0 | 0.0036327 | 0.041449 | 0
| 0.17928 | 0.00042553 | 0.0048553 | 0
| 0 | 0.0028204 | 0.03218 | 0
| 0 | 0.0034227 | 0.039053 | 0
| 0 | 0.0057769 | 0.065914 | 0
| 0 | 0.0062999 | 0.071882 | 0
| 0 | 0.0075154 | 0.085751 | 0
| 0 | 0.0032724 | 0.037338 | 0
| 0 | 0.0028358 | 0.032357 | 0
| 0 | 0.0031704 | 0.036174 | 0
| 0 | 0.0072477 | 0.082696 | 0
| 0 | 0.010077 | 0.11498 | 0
| 0 | 0.0083095 | 0.094811 | 0
| 0 | 0.003342 | 0.038132 | 0
| 0 | 0.00034533 | 0.0039402 | 0
| 0 | 0.0065413 | 0.074636 | 0
| 0 | 0.0017856 | 0.020374 | 0
| 0 | 0.003058 | 0.034892 | 0
| 0 | 0.004643 | 0.052976 | 0
| 0 | 0.0044925 | 0.05126 | 0
| 0 | 0.00038409 | 0.0043824 | 0
| 0 | 0.0017234 | 0.019663 | 0
| 0 | 0.0035353 | 0.040337 | 0
| 0 | 0.0027769 | 0.031685 | 0
| 0 | 0.0036625 | 0.041789 | 0
| 0 | 0.00022621 | 0.002581 | 0
| 0 | 0.00015735 | 0.0017954 | 0
| 0 | 0.00398 | 0.045411 | 0
| 0 | 0.0045694 | 0.052137 | 0
| 0 | 0.0013659 | 0.015585 | 0
| 0 | 0.00061892 | 0.0070619 | 0
| 0 | 0.0094676 | 0.10803 | 0
| 0 | 0.0024714 | 0.028198 | 0
| 0 | 0.0065158 | 0.074345 | 0
| 0 | 0.0053517 | 0.061063 | 0
| 0 | 0.0020471 | 0.023357 | 0
| 0 | 3.4272e-05 | 0.00039104 | 0
| 0 | 0.003932 | 0.044864 | 0
| 0 | 0.001711 | 0.019523 | 0
| 0 | 0.0068537 | 0.078201 | 0
| 0 | 0.0048849 | 0.055737 | 0
| 0 | 0.0080822 | 0.092218 | 0
| 0 | 8.7955e-05 | 0.0010036 | 0
| 0 | 0.0031955 | 0.03646 | 0
| 0 | 0.014038 | 0.16017 | 0
| 0 | 0.0033506 | 0.03823 | 0
| 0 | 0.0043072 | 0.049145 | 0
| 0 | 0.0028512 | 0.032533 | 0
| 0 | 0.0080022 | 0.091305 | 0
| 0 | 0.0017857 | 0.020375 | 0
| 0 | 0.00099512 | 0.011354 | 0
| 0 | 0.0013463 | 0.015361 | 0
| 0 | 0.0023414 | 0.026715 | 0
| 0 | 0.0002146 | 0.0024486 | 0
| 0 | 0.0087364 | 0.099682 | 0
| 0 | 0.0015695 | 0.017908 | 0
| 0 | 0.010343 | 0.11801 | 0
| 0 | 0.0020076 | 0.022906 | 0
| 0 | 0.0033228 | 0.037913 | 0
| 0 | 0.0049689 | 0.056696 | 0
| 0 | 0.0053683 | 0.061252 | 0
| 0 | 0.02416 | 0.27567 | 0
| 0 | 0.0034676 | 0.039566 | 0
| 0 | 0.0012176 | 0.013892 | 0
| 0 | 0.0052661 | 0.060087 | 0
| 0 | 0.00034062 | 0.0038865 | 0
| 0 | 9.7314e-06 | 0.00011104 | 0
| 0 | 0.0061637 | 0.070328 | 0
| 0 | 0.0033447 | 0.038163 | 0
| 0 | 0.0024502 | 0.027957 | 0
| 0 | 0.00725 | 0.082723 | 0
| 0 | 0.0090751 | 0.10355 | 0
| 0 | 0.0032547 | 0.037136 | 0
| 0 | 0.00033679 | 0.0038428 | 0
| 0 | 0.005138 | 0.058625 | 0
| 0 | 0.002359 | 0.026916 | 0
| 0 | 0.0042809 | 0.048845 | 0
| 0 | 0.00071824 | 0.0081951 | 0
| 0 | 0.00032029 | 0.0036546 | 0
| 0 | 0.011586 | 0.1322 | 0
| 0 | 6.7918e-05 | 0.00077495 | 0
| 0 | 0.0039713 | 0.045312 | 0
| 0 | 0.0056256 | 0.064188 | 0
| 0 | 0.0016727 | 0.019086 | 0
| 0 | 0.0016677 | 0.019029 | 0
| 0 | 0.0040414 | 0.046112 | 0
| 0 | 0.0078625 | 0.089712 | 0
| 0 | 0.00088217 | 0.010066 | 0
| 0 | 0.0073428 | 0.083781 | 0
| 0 | 0.0054366 | 0.062031 | 0
| 0 | 0.0044864 | 0.05119 | 0
| 0 | 0.009273 | 0.10581 | 0
| 0 | 0.0086524 | 0.098724 | 0
| 0 | 0.00075574 | 0.008623 | 0
| 0 | 0.012448 | 0.14203 | 0
| 0 | 0.00033887 | 0.0038665 | 0
| 0 | 0.00043567 | 0.004971 | 0
| 0 | 0.0064752 | 0.073882 | 0
| 0 | 0.0013452 | 0.015349 | 0
| 0 | 0.010111 | 0.11537 | 0
| 0 | 0.00047374 | 0.0054053 | 0
| 0 | 0.00019344 | 0.0022072 | 0
| 0 | 0.0049826 | 0.056851 | 0
| 0 | 0.0047595 | 0.054306 | 0
| 0 | 0.0020383 | 0.023257 | 0
| 0 | 0.005854 | 0.066794 | 0
| 0 | 0.01038 | 0.11843 | 0
| 0 | 0.0093582 | 0.10678 | 0
| 0 | 0.01069 | 0.12197 | 0
| 0 | 0.0020656 | 0.023568 | 0
| 0 | 0.0021234 | 0.024228 | 0
| 0 | 0.0019427 | 0.022166 | 0
| 0 | 0.00054994 | 0.0062749 | 0
| 0 | 0.0034023 | 0.038821 | 0
| 0 | 0.0076848 | 0.087684 | 0
| 0 | 0.0035663 | 0.040691 | 0
| 0 | 0.002419 | 0.027601 | 0
| 0 | 0.0027454 | 0.031325 | 0
| 0 | 0.0031015 | 0.035388 | 0
| 0 | 0.0056162 | 0.064081 | 0
| 0 | 0.0049192 | 0.056128 | 0
| 0 | 0.0021563 | 0.024604 | 0
| 0 | 0.013621 | 0.15541 | 0
| 0 | 0.0031849 | 0.03634 | 0
| 0 | 0.0068202 | 0.077819 | 0
| 0 | 3.8468e-05 | 0.00043891 | 0
| 0 | 0.0054269 | 0.061921 | 0
| 0 | 0.00060518 | 0.0069052 | 0
| 0 | 0.00055689 | 0.0063541 | 0
| 0 | 0.0083954 | 0.095792 | 0
| 0 | 0.0066875 | 0.076305 | 0
| 0 | 0.00050848 | 0.0058018 | 0
| 0 | 0.0040292 | 0.045973 | 0
| 0 | 0.00032608 | 0.0037205 | 0
| 0 | 0.0050435 | 0.057546 | 0
| 0 | 0.0054747 | 0.062467 | 0
| 0 | 0.0084563 | 0.096487 | 0
| 0 | 0.0010256 | 0.011702 | 0
| 0 | 0.0024248 | 0.027667 | 0
| 0 | 0.0047533 | 0.054235 | 0
| 0 | 0.0030272 | 0.034541 | 0
| 0 | 0.0010521 | 0.012005 | 0
| 0 | 0.0020084 | 0.022916 | 0
| 0 | 0.0027425 | 0.031292 | 0
| 0 | 0.0046145 | 0.052651 | 0
| 0 | 0.0023736 | 0.027083 | 0
| 0 | 0.015089 | 0.17216 | 0
| 0 | 0.0069044 | 0.07878 | 0
| 0 | 0.00011457 | 0.0013072 | 0
| 0 | 0.0024999 | 0.028524 | 0
| 0 | 0.00040054 | 0.0045701 | 0
| 0 | 9.532e-06 | 0.00010876 | 0
| 0 | 0.014497 | 0.16541 | 0
| 0 | 0.015201 | 0.17345 | 0
| 0 | 0.0058597 | 0.066859 | 0
| 0 | 9.5205e-06 | 0.00010863 | 0
| 0 | 0.0074162 | 0.084619 | 0
| 0 | 0.0015606 | 0.017807 | 0
| 0 | 0.0020553 | 0.023451 | 0
| 0 | 0.0044806 | 0.051123 | 0
| 0 | 3.9634e-05 | 0.00045222 | 0
| 0 | 0.0064776 | 0.073909 | 0
| 0 | 0.00077036 | 0.0087898 | 0
| 0 | 0.0081534 | 0.09303 | 0
| 0 | 0.0067642 | 0.07718 | 0
| 0.45788 | 0.0032014 | 0.036528 | 0
| 0 | 4.7481e-05 | 0.00054176 | 0
| 0 | 0.0072596 | 0.082833 | 0
| 0 | 0.0035201 | 0.040164 | 0
| 0 | 0.0018311 | 0.020892 | 0
| 0 | 0.0087252 | 0.099554 | 0
| 0 | 0.0022284 | 0.025426 | 0
| 0 | 0.0036593 | 0.041753 | 0
| 0 | 0.0023406 | 0.026706 | 0
| 0 | 0.0089585 | 0.10222 | 0
| 0 | 0.0072502 | 0.082725 | 0
| 0 | 0.0031504 | 0.035945 | 0
| 0 | 0.0057804 | 0.065954 | 0
| 0 | 0.0033733 | 0.03849 | 0
| 0 | 0.0014172 | 0.01617 | 0
| 0 | 0.0026672 | 0.030433 | 0
| 0 | 3.7786e-05 | 0.00043114 | 0
| 0 | 0.0025125 | 0.028668 | 0
| 0 | 0.0020211 | 0.023061 | 0
| 0 | 0.013902 | 0.15862 | 0
| 0 | 0.0012937 | 0.014761 | 0
| 0 | 0.0035777 | 0.040822 | 0
| 0 | 0.00083041 | 0.009475 | 0
| 0 | 0.0011417 | 0.013027 | 0
| 0 | 0.0046141 | 0.052647 | 0
| 0 | 0.00053782 | 0.0061366 | 0
| 0 | 0.0019435 | 0.022175 | 0
| 0 | 0.0024775 | 0.028268 | 0
| 0 | 0.0066401 | 0.075764 | 0
| 0 | 0.0040927 | 0.046698 | 0
| 0 | 0.0044838 | 0.05116 | 0
| 0 | 0.0025446 | 0.029034 | 0
| 0 | 0.00074411 | 0.0084903 | 0
| 0 | 0.0096059 | 0.1096 | 0
| 0 | 0.0051978 | 0.059307 | 0
| 0 | 0.0054299 | 0.061955 | 0
| 0 | 0.0056732 | 0.064732 | 0
| 0 | 0.0041205 | 0.047015 | 0
| 0 | 2.8215e-05 | 0.00032193 | 0
| 0 | 0.0014859 | 0.016954 | 0
| 0 | 0.00047012 | 0.0053641 | 0
| 0 | 0.0026136 | 0.029821 | 0
| 0 | 0.0032525 | 0.037111 | 0
| 0.68836 | 0.008449 | 0.096403 | 0
| 0 | 0.0025656 | 0.029273 | 0
| 0 | 0.0032326 | 0.036883 | 0
| 0 | 0.006418 | 0.073229 | 0
| 0 | 0.00046979 | 0.0053603 | 0
| 0 | 0.0030778 | 0.035118 | 0
| 0 | 0.00060083 | 0.0068555 | 0
| 0 | 0.010811 | 0.12335 | 0
| 0 | 0.010064 | 0.11483 | 0
| 0 | 0.0022347 | 0.025498 | 0
| 0 | 0.0078205 | 0.089231 | 0
| 0 | 9.37e-06 | 0.00010691 | 0
| 0 | 0.0089075 | 0.10163 | 0
| 0 | 0.0031197 | 0.035596 | 0
| 0 | 0.0019017 | 0.021698 | 0
| 0 | 0.003981 | 0.045423 | 0
| 0 | 0.0063044 | 0.071933 | 0
| 0 | 0.0036785 | 0.041972 | 0
| 0 | 0.0023867 | 0.027232 | 0
| 0 | 0.0049226 | 0.056166 | 0
| 0 | 0.005389 | 0.061489 | 0
| 0 | 0.00092578 | 0.010563 | 0
| 0 | 0.0029363 | 0.033503 | 0
| 0 | 0.0007569 | 0.0086363 | 0
| 0.058559 | 0.0027655 | 0.031554 | 0
| 0 | 0.0010464 | 0.011939 | 0
| 0 | 9.3399e-06 | 0.00010657 | 0
| 0 | 0.0065352 | 0.074567 | 0
| 0 | 0.004668 | 0.053262 | 0
| 0 | 0.0022183 | 0.025311 | 0
| 0 | 0.010268 | 0.11716 | 0
| 0 | 0.009951 | 0.11354 | 0
| 0 | 0.0072162 | 0.082337 | 0
| 0 | 0.0039896 | 0.045521 | 0
| 0 | 0.00054061 | 0.0061684 | 0
| 0 | 0.0048003 | 0.054771 | 0
| 0 | 0.005965 | 0.06806 | 0
| 0.043023 | 3.728e-05 | 0.00042536 | 0
| 0 | 0.0082423 | 0.094044 | 0
| 0 | 0.0085565 | 0.09763 | 0
| 0 | 0.010018 | 0.11431 | 0
| 0 | 0.0021879 | 0.024964 | 0
| 0 | 0.0054064 | 0.061687 | 0
| 0 | 0.0036918 | 0.042123 | 0
| 0 | 0.005071 | 0.05786 | 0
| 0 | 0.0023184 | 0.026453 | 0
| 0 | 0.0011692 | 0.013341 | 0
| 0 | 0.0026911 | 0.030705 | 0
| 0 | 0.0072375 | 0.08258 | 0
| 0 | 0.013702 | 0.15633 | 0
| 0 | 0.0049046 | 0.055961 | 0
| 0 | 0.0012481 | 0.014241 | 0
| 0 | 0.00068568 | 0.0078236 | 0
| 0 | 0.0045458 | 0.051867 | 0
| 0 | 0.0054158 | 0.061794 | 0
| 0 | 0.0058851 | 0.067149 | 0
| 0.0044661 | 0.004652 | 0.05308 | 0
| 0 | 0.0088683 | 0.10119 | 0
| 0 | 0.0093583 | 0.10678 | 0
| 0 | 0.0050939 | 0.058122 | 0
| 0 | 0.0026528 | 0.030268 | 0
| 0 | 0.0061959 | 0.070695 | 0
| 0 | 0.0076863 | 0.0877 | 0
| 0 | 0.0098052 | 0.11188 | 0
| 0.10045 | 0.0033602 | 0.03834 | 0
| 0 | 0.0086796 | 0.099034 | 0
| 0 | 0.0036868 | 0.042066 | 0
| 0 | 0.0032063 | 0.036584 | 0
| 0 | 0.0053793 | 0.061378 | 0
| 0 | 0.00056169 | 0.0064088 | 0
| 0 | 0.0042249 | 0.048206 | 0
| 0 | 0.0091224 | 0.10409 | 0
| 0 | 0.0094779 | 0.10814 | 0
| 0 | 0.0079384 | 0.090577 | 0
| 0 | 0.004856 | 0.055407 | 0
| 0 | 0.0017934 | 0.020462 | 0
| 0 | 2.7585e-05 | 0.00031475 | 0
| 0 | 0.0052675 | 0.060102 | 0
| 0 | 0.0040352 | 0.046042 | 0
| 0 | 0.007647 | 0.087253 | 0
| 0 | 0.0064715 | 0.073839 | 0
| 0 | 0.0083687 | 0.095487 | 0
| 0 | 0.001468 | 0.01675 | 0
| 0 | 0.011884 | 0.13559 | 0
| 0 | 0.0061194 | 0.069822 | 0
| 0 | 0.0034619 | 0.0395 | 0
| 0 | 2.747e-05 | 0.00031343 | 0
| 0 | 0.0021789 | 0.024862 | 0
| 0 | 0.0038142 | 0.04352 | 0
| 0 | 0.0077681 | 0.088634 | 0
| 0 | 0.012752 | 0.1455 | 0
| 0 | 0.0051103 | 0.058308 | 0
| 0 | 0.008464 | 0.096575 | 0
| 0 | 0.004763 | 0.054346 | 0
| 0 | 0.0035478 | 0.040481 | 0
| 0 | 0.0030785 | 0.035126 | 0
| 0 | 0.0016166 | 0.018445 | 0
| 0 | 0.011458 | 0.13074 | 0
| 0 | 0.0039543 | 0.045118 | 0
| 0.21443 | 0.0010866 | 0.012398 | 0
| 0 | 0.00037405 | 0.0042679 | 0
| 0 | 0.0015416 | 0.01759 | 0
| 0 | 0.0023712 | 0.027056 | 0
| 0 | 0.0014587 | 0.016644 | 0
| 0 | 0.012607 | 0.14384 | 0
| 0 | 0.0059765 | 0.068191 | 0
| 0 | 0.005587 | 0.063748 | 0
| 0 | 9.0992e-06 | 0.00010382 | 0
| 0 | 0.0063419 | 0.072362 | 0
| 0 | 0.0042023 | 0.047948 | 0
| 0 | 0.0056476 | 0.064439 | 0
| 0 | 0.0012548 | 0.014317 | 0
| 0 | 0.0074467 | 0.084966 | 0
| 0 | 0.0037707 | 0.043024 | 0
| 0 | 0.004406 | 0.050272 | 0
| 0 | 0.0059308 | 0.06767 | 0
| 0 | 0.0065055 | 0.074227 | 0
| 0 | 0.007819 | 0.089215 | 0
| 0 | 0.0011248 | 0.012834 | 0
| 0 | 0.0069295 | 0.079066 | 0
| 0 | 0.001487 | 0.016967 | 0
| 0 | 0.01912 | 0.21815 | 0
| 0 | 0.0010508 | 0.011989 | 0
| 0 | 0.0019925 | 0.022735 | 0
| 0 | 0.0027614 | 0.031507 | 0
| 0 | 0.004055 | 0.046267 | 0
| 0 | 0.00042511 | 0.0048505 | 0
| 0 | 0.003627 | 0.041384 | 0
| 0 | 0.010632 | 0.12132 | 0
| 0 | 0.0066018 | 0.075327 | 0
| 0 | 0.00385 | 0.043929 | 0
| 0 | 0.0089613 | 0.10225 | 0
| 0 | 0.0023573 | 0.026897 | 0
| 0 | 0.0094292 | 0.10759 | 0
| 0 | 1.8063e-05 | 0.0002061 | 0
| 0 | 0.0082014 | 0.093578 | 0
| 0 | 0.0030144 | 0.034394 | 0
| 0 | 0.003699 | 0.042206 | 0
| 0 | 0.00033378 | 0.0038085 | 0
| 0 | 0.002399 | 0.027372 | 0
| 0 | 0.005699 | 0.065025 | 0
| 0 | 0.0069883 | 0.079736 | 0
| 0 | 0.00067151 | 0.0076619 | 0
| 0 | 0.011775 | 0.13435 | 0
| 0 | 0.018682 | 0.21316 | 0
| 0 | 0.006131 | 0.069955 | 0
| 0 | 0.0074483 | 0.084985 | 0
| 0 | 0.0096984 | 0.11066 | 0
| 0 | 0.0035113 | 0.040064 | 0
| 0 | 0.0045661 | 0.052099 | 0
| 0 | 0.0026902 | 0.030695 | 0
| 0 | 0.0047663 | 0.054383 | 0
| 0 | 0.0016367 | 0.018675 | 0
| 0 | 0.0017354 | 0.019801 | 0
| 0 | 0.0033356 | 0.038059 | 0
| 0 | 0.0031005 | 0.035377 | 0
| 0 | 8.9855e-06 | 0.00010252 | 0
| 0 | 0.0033056 | 0.037717 | 0
| 0 | 0.0016316 | 0.018617 | 0
| 0 | 0.0046073 | 0.052569 | 0
| 0 | 0.0051802 | 0.059106 | 0
| 0 | 0.0053412 | 0.060943 | 0
| 0 | 0.0072977 | 0.083267 | 0
| 0 | 0.006667 | 0.076071 | 0
| 0 | 0.0033464 | 0.038182 | 0
| 0.27114 | 0.0059838 | 0.068275 | 0
| 0 | 0.0038637 | 0.044084 | 0
| 0 | 0.00041235 | 0.004705 | 0
| 0 | 0.0024975 | 0.028496 | 0
| 0 | 0.0047708 | 0.054435 | 0
| 0 | 0.0014151 | 0.016146 | 0
| 0 | 0.0013342 | 0.015223 | 0
| 0 | 0.003831 | 0.043711 | 0
| 0 | 0.0080594 | 0.091958 | 0
| 0 | 0.0019859 | 0.022659 | 0
| 0 | 0.0052741 | 0.060177 | 0
| 0 | 0.0024134 | 0.027537 | 0
| 0 | 0.0073897 | 0.084316 | 0
| 0 | 0.0093458 | 0.10664 | 0
| 0 | 0.0049853 | 0.056882 | 0
| 0 | 0.002546 | 0.02905 | 0
| 0 | 0.0033678 | 0.038427 | 0
| 0 | 0.0054335 | 0.061996 | 0
| 0 | 0.0049433 | 0.056403 | 0
| 0 | 0.005003 | 0.057084 | 0
| 0 | 0.0039324 | 0.044869 | 0
| 0 | 0.0075616 | 0.086278 | 0
| 0 | 0.008305 | 0.09476 | 0
| 0 | 8.9156e-06 | 0.00010173 | 0
| 0 | 2.6746e-05 | 0.00030517 | 0
| 0 | 0.0034046 | 0.038846 | 0
| 0 | 8.0193e-05 | 0.000915 | 0
| 0 | 0.0066559 | 0.075944 | 0
| 0.00094326 | 0.0014967 | 0.017077 | 0
| 0 | 0.0043647 | 0.049801 | 0
| 0 | 0.0019862 | 0.022662 | 0
| 0 | 0.0066207 | 0.075542 | 0
| 0 | 0.0020198 | 0.023046 | 0
| 0 | 0.0073669 | 0.084057 | 0
| 0 | 0.0029443 | 0.033594 | 0
| 0 | 0.0082094 | 0.093669 | 0
| 0 | 0.00090682 | 0.010347 | 0
| 0 | 0.00044747 | 0.0051056 | 0
| 0 | 0.0061782 | 0.070493 | 0
| 0 | 0.0064269 | 0.073331 | 0
| 0 | 0.0061685 | 0.070383 | 0
| 0 | 0.0085226 | 0.097243 | 0
| 0 | 0.0021032 | 0.023997 | 0
| 0 | 0.0016521 | 0.01885 | 0
| 0 | 0.0065095 | 0.074274 | 0
| 0 | 0.0043771 | 0.049943 | 0
| 0 | 0.00015085 | 0.0017212 | 0
| 0 | 0.0031939 | 0.036442 | 0
| 0 | 0.0020227 | 0.02308 | 0
| 0 | 0.0036102 | 0.041192 | 0
| 0 | 0.0015787 | 0.018013 | 0
| 0 | 0.00039895 | 0.004552 | 0
| 0 | 8.8655e-06 | 0.00010116 | 0
| 0 | 0.0012496 | 0.014258 | 0
| 0 | 0.00079749 | 0.0090993 | 0
| 0 | 0.0012307 | 0.014042 | 0
| 0 | 0.0041338 | 0.047167 | 0
| 0 | 0.00065491 | 0.0074725 | 0
| 0 | 0.0069135 | 0.078883 | 0
| 0 | 0.0032429 | 0.037002 | 0
| 0 | 0.0039357 | 0.044906 | 0
| 0 | 0.0038556 | 0.043993 | 0
| 0 | 0.0055223 | 0.063009 | 0
| 0 | 0.0036821 | 0.042012 | 0
| 0 | 0.0023713 | 0.027056 | 0
| 0 | 0.0021082 | 0.024054 | 0
| 0 | 0.0028578 | 0.032608 | 0
| 0 | 0.0032544 | 0.037132 | 0
| 0 | 0.00082901 | 0.009459 | 0
| 0 | 0.0069225 | 0.078986 | 0
| 0 | 0.00072306 | 0.0082501 | 0
| 0 | 0.0026714 | 0.030481 | 0
| 0 | 0.0022745 | 0.025952 | 0
| 0 | 0.0034278 | 0.039111 | 0
| 0 | 0.0011191 | 0.012769 | 0
| 0 | 0.0082294 | 0.093898 | 0
| 0 | 0.0022718 | 0.025922 | 0
| 0 | 0.0060751 | 0.069317 | 0
| 0 | 0.0040235 | 0.045908 | 0
| 0 | 0.00043138 | 0.004922 | 0
| 0 | 0.001285 | 0.014661 | 0
| 0 | 0.0045928 | 0.052404 | 0
| 0 | 0.007021 | 0.08011 | 0
| 0 | 0.0088748 | 0.10126 | 0
| 0 | 0.0036412 | 0.041546 | 0
| 0 | 0.0025344 | 0.028917 | 0
| 0 | 0.0053378 | 0.060904 | 0
| 0 | 0.00218 | 0.024874 | 0
| 0 | 0.0027338 | 0.031193 | 0
| 0 | 0.0038763 | 0.044229 | 0
| 0 | 2.6351e-05 | 0.00030067 | 0
| 0 | 0.0051794 | 0.059097 | 0
| 0 | 0.00040381 | 0.0046075 | 0
| 0 | 6.1412e-05 | 0.00070071 | 0
| 0 | 0.0035167 | 0.040126 | 0
| 0 | 0.0004559 | 0.0052018 | 0
| 0 | 0.0042867 | 0.048911 | 0
| 0 | 0.0088444 | 0.10092 | 0
| 0 | 0.0026879 | 0.030669 | 0
| 0 | 0.0052203 | 0.059564 | 0
| 0 | 0.0015941 | 0.018188 | 0
| 0 | 0.0025311 | 0.02888 | 0
| 0.038867 | 0.0084555 | 0.096478 | 0
| 0 | 8.7489e-06 | 9.9824e-05 | 0
| 0 | 0.0033503 | 0.038227 | 0
| 0 | 0.0022306 | 0.025451 | 0
| 0 | 0.00036705 | 0.0041881 | 0
| 0 | 0.0032859 | 0.037492 | 0
| 0 | 0.0057323 | 0.065405 | 0
| 0 | 0.0083183 | 0.094912 | 0
| 0 | 0.012187 | 0.13906 | 0
| 0 | 0.0040623 | 0.046351 | 0
| 0 | 0.0016656 | 0.019004 | 0
| 1.3081 | 0.0051171 | 0.058386 | 0
| 0 | 0.0035348 | 0.040332 | 0
| 0 | 0.00062833 | 0.0071692 | 0
| 0 | 5.8158e-06 | 6.6359e-05 | 0
| 0 | 0.0026345 | 0.03006 | 0
| 0 | 0.0070923 | 0.080923 | 0
| 0.036162 | 9.5863e-05 | 0.0010938 | 0
| 0 | 0.0040059 | 0.045707 | 0
| 0 | 0.0016546 | 0.018878 | 0
| 0 | 0.0033515 | 0.038241 | 0
| 0 | 0.0095413 | 0.10887 | 0
| 0 | 0.0039792 | 0.045402 | 0
| 0 | 0.0038919 | 0.044406 | 0
| 0 | 0.0022845 | 0.026067 | 0
| 0 | 0.0062229 | 0.071003 | 0
| 0 | 0.00064198 | 0.007325 | 0
| 0 | 0.00018214 | 0.0020782 | 0
| 0 | 0.00027753 | 0.0031666 | 0
| 0 | 0.005716 | 0.06522 | 0
| 0 | 0.0064809 | 0.073947 | 0
| 0 | 8.6543e-06 | 9.8746e-05 | 0
| 0 | 0.0053104 | 0.060592 | 0
| 0 | 0.0022724 | 0.025928 | 0
| 0 | 0.00761 | 0.08683 | 0
| 0 | 0.00047496 | 0.0054192 | 0
| 0 | 0.0012087 | 0.013791 | 0
| 0 | 0.0056634 | 0.06462 | 0
| 0 | 0.0026322 | 0.030033 | 0
| 0 | 0.00014668 | 0.0016736 | 0
| 0 | 0.0025966 | 0.029627 | 0
| 0 | 0.0027689 | 0.031593 | 0
| 0 | 0.0032288 | 0.03684 | 0
| 0 | 1.7245e-05 | 0.00019676 | 0
| 0 | 0.0019448 | 0.022191 | 0
| 0 | 0.0037229 | 0.042478 | 0
| 0 | 0.0045323 | 0.051713 | 0
| 0 | 0.0040139 | 0.045798 | 0
| 0 | 0.00095304 | 0.010874 | 0
| 0 | 0.0060622 | 0.06917 | 0
| 0 | 0.00031568 | 0.0036019 | 0
| 0 | 0.0060179 | 0.068664 | 0
| 0 | 0.0041408 | 0.047247 | 0
| 0.10701 | 0.0023833 | 0.027193 | 0
| 0 | 0.0086955 | 0.099215 | 0
| 0 | 0.0031816 | 0.036302 | 0
| 0 | 9.4581e-05 | 0.0010792 | 0
| 0 | 0.0041636 | 0.047507 | 0
| 0 | 0.00085094 | 0.0097092 | 0
| 0 | 0.0076569 | 0.087365 | 0
| 0 | 0.0064573 | 0.073678 | 0
| 0 | 0.0047559 | 0.054265 | 0
| 0 | 0.0044275 | 0.050518 | 0
| 0 | 0.0020491 | 0.023381 | 0
| 0 | 0.001234 | 0.01408 | 0
| 0 | 0.0053028 | 0.060505 | 0
| 0 | 0.0056018 | 0.063917 | 0
| 0 | 0.016274 | 0.18568 | 0
| 0 | 0.00065947 | 0.0075246 | 0
| 0 | 0.00088197 | 0.010063 | 0
| 0 | 0.013526 | 0.15433 | 0
| 0 | 0.004713 | 0.053775 | 0
| 0 | 0.0020154 | 0.022995 | 0
| 0 | 0.0045666 | 0.052105 | 0
| 0 | 0.0022987 | 0.026228 | 0
| 0 | 0.002948 | 0.033637 | 0
| 0 | 0.004254 | 0.048538 | 0
| 0 | 0.004842 | 0.055247 | 0
| 0 | 0.010271 | 0.1172 | 0
| 0 | 0.00065734 | 0.0075003 | 0
| 0 | 0.0079808 | 0.091061 | 0
| 0 | 0.00060584 | 0.0069127 | 0
| 0 | 0.0042639 | 0.048651 | 0
| 0 | 0.0055603 | 0.063444 | 0
| 0 | 0.0042124 | 0.048064 | 0
| 0 | 8.5071e-06 | 9.7066e-05 | 0
| 0 | 8.5015e-06 | 9.7002e-05 | 0
| 0 | 0.0028305 | 0.032296 | 0
| 0 | 0.0074279 | 0.084752 | 0
| 0 | 0.0032545 | 0.037134 | 0
| 0 | 0.006791 | 0.077485 | 0
| 0 | 0.0032106 | 0.036633 | 0
| 0 | 8.4933e-06 | 9.6908e-05 | 0
| 0 | 0.001894 | 0.02161 | 0
| 0 | 0.0039129 | 0.044646 | 0
| 0 | 0.0030295 | 0.034567 | 0
| 0 | 0.0065572 | 0.074818 | 0
| 0 | 0.0024424 | 0.027868 | 0
| 0 | 0.0071185 | 0.081222 | 0
| 0 | 0.01388 | 0.15837 | 0
| 0 | 0.0021947 | 0.025042 | 0
| 0 | 0.0078616 | 0.0897 | 0
| 0 | 0.003498 | 0.039912 | 0
| 0 | 0.00098214 | 0.011206 | 0
| 0 | 0.0010667 | 0.012171 | 0
| 0 | 0.0069329 | 0.079104 | 0
| 0 | 0.00049942 | 0.0056984 | 0
| 0 | 8.4632e-06 | 9.6565e-05 | 0
| 0 | 0.0042346 | 0.048317 | 0
| 0.16964 | 0.0061355 | 0.070006 | 0
| 0 | 0.003789 | 0.043232 | 0
| 0 | 0.0051372 | 0.058615 | 0
| 0 | 0.0020644 | 0.023555 | 0
| 0 | 0.0031498 | 0.035939 | 0
| 0 | 0.011121 | 0.12689 | 0
| 0 | 0.01176 | 0.13419 | 0
| 0 | 0.0034745 | 0.039644 | 0
| 0 | 0.00143 | 0.016316 | 0
| 0 | 0.0041215 | 0.047026 | 0
| 0 | 0.0016706 | 0.019062 | 0
| 0 | 0.0015383 | 0.017552 | 0
| 0 | 0.0021482 | 0.024511 | 0
| 0 | 0.0033303 | 0.037999 | 0
| 0 | 0.0029769 | 0.033967 | 0
| 0 | 0.00083825 | 0.0095644 | 0
| 0 | 0.0059923 | 0.068372 | 0
| 0 | 0.0048176 | 0.054969 | 0
| 0 | 0.0054238 | 0.061886 | 0
| 0 | 0.0042174 | 0.04812 | 0
| 0 | 0.0016743 | 0.019104 | 0
| 0 | 0.010649 | 0.1215 | 0
| 0 | 0.0046538 | 0.0531 | 0
| 0 | 0.0019829 | 0.022625 | 0
| 0 | 0.00014771 | 0.0016853 | 0
| 0 | 0.0025746 | 0.029376 | 0
| 0 | 0.0073521 | 0.083888 | 0
| 0 | 0.0030753 | 0.03509 | 0
| 0 | 0.0044947 | 0.051284 | 0
| 0 | 0.002055 | 0.023447 | 0
| 0 | 8.3513e-06 | 9.5288e-05 | 0
| 0 | 0.0020959 | 0.023914 | 0
| 0 | 0.0049294 | 0.056244 | 0
| 0 | 0.0072056 | 0.082215 | 0
| 0 | 0.0026798 | 0.030576 | 0
| 0 | 0.0021747 | 0.024813 | 0
| 0 | 4.9992e-05 | 0.00057041 | 0
| 0 | 0.0012741 | 0.014537 | 0
| 0 | 0.0028474 | 0.032489 | 0
| 0 | 0.0082669 | 0.094325 | 0
| 0 | 0.0073458 | 0.083816 | 0
| 0 | 0.0097 | 0.11068 | 0
| 0 | 0.0059222 | 0.067573 | 0
| 0 | 0.0066263 | 0.075606 | 0
| 0 | 0.00083945 | 0.0095782 | 0
| 0 | 0.0038035 | 0.043398 | 0
| 0 | 0.0045535 | 0.051956 | 0
| 0 | 0.0030408 | 0.034695 | 0
| 0 | 8.3037e-06 | 9.4745e-05 | 0
| 0 | 0.0020249 | 0.023104 | 0
| 0 | 1.6593e-05 | 0.00018932 | 0
| 0 | 0.003559 | 0.040608 | 0
| 0 | 0.00045628 | 0.0052061 | 0
| 0 | 0.0019493 | 0.022242 | 0
| 0 | 0.0033345 | 0.038047 | 0
| 0 | 0.005078 | 0.05794 | 0
| 0 | 0.0084284 | 0.096168 | 0
| 0 | 0.0061611 | 0.070299 | 0
| 0 | 0.0030312 | 0.034586 | 0
| 0 | 0.005207 | 0.059412 | 0
| 0 | 0.0040699 | 0.046437 | 0
| 0 | 0.0051983 | 0.059313 | 0
| 0 | 0.0057602 | 0.065724 | 0
| 0 | 0.010169 | 0.11603 | 0
| 0 | 0.0019108 | 0.021803 | 0
| 0 | 0.0023987 | 0.027369 | 0
| 0 | 0.0004549 | 0.0051904 | 0
| 0 | 0.0062335 | 0.071124 | 0
| 0 | 0.003107 | 0.035451 | 0
| 0 | 0.0042437 | 0.04842 | 0
| 0 | 0.00051157 | 0.005837 | 0
| 0 | 0.00099804 | 0.011388 | 0
| 0 | 0.0010365 | 0.011826 | 0
| 0 | 0.0067862 | 0.07743 | 0
| 0 | 0.0010718 | 0.012229 | 0
| 0 | 0.004188 | 0.047785 | 0
| 0 | 0.0030985 | 0.035354 | 0
| 0 | 0.0085817 | 0.097918 | 0
| 0 | 0.00094663 | 0.010801 | 0
| 0 | 0.0042297 | 0.048261 | 0
| 0 | 0.0024435 | 0.02788 | 0
| 0 | 0.0094405 | 0.10772 | 0
| 0 | 0.0038538 | 0.043972 | 0
| 0 | 0.00092836 | 0.010593 | 0
| 0 | 0.0030059 | 0.034297 | 0
| 0 | 0.0020117 | 0.022954 | 0
| 0 | 0.0034809 | 0.039717 | 0
| 0 | 0.00029552 | 0.0033719 | 0
| 0 | 0.0036009 | 0.041086 | 0
| 0 | 0.0048058 | 0.054835 | 0
| 0 | 0.0010741 | 0.012256 | 0
| 0 | 0.012495 | 0.14257 | 0
| 0 | 0.0063073 | 0.071966 | 0
| 0.015168 | 9.8248e-05 | 0.001121 | 0
| 0 | 0.00085962 | 0.0098083 | 0
| 0 | 0.0033889 | 0.038667 | 0
| 0 | 0.0082339 | 0.093948 | 0
| 0 | 0.0018895 | 0.02156 | 0
| 0 | 0.013447 | 0.15343 | 0
| 0 | 0.00083376 | 0.0095132 | 0
| 0 | 0.0027423 | 0.03129 | 0
| 0 | 0.00053079 | 0.0060563 | 0
| 0 | 0.0050859 | 0.05803 | 0
| 0 | 0.0039919 | 0.045547 | 0
| 0 | 0.0013613 | 0.015533 | 0
| 0 | 0.0020009 | 0.022831 | 0
| 0.074653 | 0.00023585 | 0.0026911 | 0
| 0 | 0.002813 | 0.032096 | 0
| 0.03782 | 7.3145e-05 | 0.00083459 | 0
| 0 | 0.0037125 | 0.04236 | 0
| 0 | 0.0098266 | 0.11212 | 0
| 0 | 0.012266 | 0.13995 | 0
| 0 | 0.0022651 | 0.025845 | 0
| 0 | 0.0021351 | 0.024362 | 0
| 0 | 0.0043178 | 0.049266 | 0
| 0 | 0.0055572 | 0.063408 | 0
| 0 | 0.001822 | 0.020789 | 0
| 0 | 0.0012137 | 0.013849 | 0
| 0 | 0.0028314 | 0.032306 | 0
| 0 | 0.00076035 | 0.0086755 | 0
| 0 | 0.0009541 | 0.010886 | 0
| 0 | 0.0062815 | 0.071672 | 0
| 0 | 0.0061109 | 0.069725 | 0
| 0 | 0.0049057 | 0.055974 | 0
| 0 | 0.004 | 0.04564 | 0
| 0 | 0.0039749 | 0.045354 | 0
| 0 | 0.0018172 | 0.020734 | 0
| 0 | 0.0056841 | 0.064855 | 0
| 0 | 0.0046358 | 0.052894 | 0
| 0 | 0.00096744 | 0.011039 | 0
| 0 | 0.0037719 | 0.043037 | 0
| 0 | 0.0046323 | 0.052854 | 0
| 0 | 0.00041886 | 0.0047792 | 0
| 0 | 0.00055559 | 0.0063393 | 0
| 0 | 0.00034577 | 0.0039453 | 0
| 0 | 0.00085201 | 0.0097214 | 0
| 0 | 0.0056887 | 0.064908 | 0
| 0 | 4.0136e-05 | 0.00045795 | 0
| 0 | 0.0053685 | 0.061255 | 0
| 0 | 0.0026296 | 0.030004 | 0
| 0 | 0.012594 | 0.1437 | 0
| 0 | 0.0038844 | 0.044321 | 0
| 0 | 0.003039 | 0.034675 | 0
| 0 | 5.5969e-05 | 0.0006386 | 0
| 0 | 0.0052598 | 0.060014 | 0
| 0 | 0.00092711 | 0.010578 | 0
| 0 | 0.010237 | 0.1168 | 0
| 0 | 0.0012697 | 0.014488 | 0
| 0 | 0.0017807 | 0.020318 | 0
| 0 | 2.6603e-05 | 0.00030353 | 0
| 0 | 0.0011811 | 0.013476 | 0
| 0 | 0.0024003 | 0.027387 | 0
| 0 | 0.00070844 | 0.0080833 | 0
| 0 | 0.0033027 | 0.037684 | 0
| 0 | 0.0064349 | 0.073423 | 0
| 0 | 0.0049086 | 0.056007 | 0
| 0 | 0.00034147 | 0.0038961 | 0
| 0 | 0.0064149 | 0.073194 | 0
| 0 | 0.00037308 | 0.0042569 | 0
| 0 | 0.0010228 | 0.01167 | 0
| 0 | 0.0047954 | 0.054715 | 0
| 0 | 0.0015291 | 0.017447 | 0
| 0 | 0.0011009 | 0.012561 | 0
| 0 | 0.00066646 | 0.0076043 | 0
| 0 | 0.0018394 | 0.020988 | 0
| 0 | 0.0035288 | 0.040264 | 0
| 0 | 0.0019096 | 0.021788 | 0
| 0 | 0.00059178 | 0.0067522 | 0
| 0 | 0.0076974 | 0.087827 | 0
| 0 | 0.010267 | 0.11715 | 0
| 0 | 0.0038412 | 0.043828 | 0
| 0 | 0.00082802 | 0.0094478 | 0
| 0 | 0.0019475 | 0.022221 | 0
| 0 | 0.0021439 | 0.024462 | 0
| 0 | 0.0085956 | 0.098076 | 0
| 0 | 7.873e-06 | 8.9831e-05 | 0
| 0 | 0.0015587 | 0.017784 | 0
| 0 | 0.0043818 | 0.049996 | 0
| 0 | 3.146e-05 | 0.00035896 | 0
| 0 | 0.00073928 | 0.0084352 | 0
| 0 | 0.0079863 | 0.091124 | 0
| 0 | 0.0086972 | 0.099235 | 0
| 0 | 0.0033556 | 0.038287 | 0
| 0 | 0.00041551 | 0.0047409 | 0
| 0 | 0.011463 | 0.13079 | 0
| 0 | 0.00075989 | 0.0086703 | 0
| 0 | 7.0386e-05 | 0.0008031 | 0
| 0.40292 | 0.0016657 | 0.019005 | 0
| 0 | 0.0012822 | 0.01463 | 0
| 0 | 0.0025795 | 0.029432 | 0
| 0 | 0.0010236 | 0.01168 | 0
| 0 | 0.001702 | 0.01942 | 0
| 0 | 0.0033014 | 0.03767 | 0
| 0 | 0.0018029 | 0.020571 | 0
| 0 | 0.013383 | 0.1527 | 0
| 0 | 0.0023317 | 0.026605 | 0
| 0 | 0.0018793 | 0.021443 | 0
| 0 | 0.0031968 | 0.036475 | 0
| 0 | 0.0068757 | 0.078452 | 0
| 0 | 0.0026782 | 0.030558 | 0
| 0 | 0.004865 | 0.05551 | 0
| 0 | 0.0048172 | 0.054964 | 0
| 0 | 5.1819e-06 | 5.9125e-05 | 0
| 0 | 0.0050906 | 0.058084 | 0
| 0 | 0.0065361 | 0.074577 | 0
| 0 | 0.0015047 | 0.017168 | 0
| 0 | 0.0061798 | 0.070511 | 0
| 0 | 6.9765e-05 | 0.00079602 | 0
| 0.57596 | 0.0033632 | 0.038375 | 0
| 0 | 0.0021666 | 0.024721 | 0
| 0 | 0.0040086 | 0.045739 | 0
| 0 | 0.0061909 | 0.070638 | 0
| 0 | 0.0064345 | 0.073418 | 0
| 0 | 0.002056 | 0.023459 | 0
| 0 | 0.0034612 | 0.039492 | 0
| 0 | 0.0019001 | 0.02168 | 0
| 0 | 0.0023611 | 0.02694 | 0
| 0 | 0.0050071 | 0.057131 | 0
| 0 | 0.0013883 | 0.015841 | 0
| 0 | 0.0016732 | 0.019091 | 0
| 0 | 0.00072466 | 0.0082683 | 0
| 0 | 0.006093 | 0.069521 | 0
| 0 | 0.0029248 | 0.033372 | 0
| 0 | 0.0020164 | 0.023007 | 0
| 0 | 3.3294e-05 | 0.00037989 | 0
| 0 | 0.0016362 | 0.018669 | 0
| 0 | 0.0015819 | 0.01805 | 0
| 0 | 0.0034859 | 0.039774 | 0
| 0 | 0.0010704 | 0.012214 | 0
| 0 | 0.00080503 | 0.0091854 | 0
| 0 | 0.0044204 | 0.050437 | 0
| 0 | 0.00033446 | 0.0038161 | 0
| 0 | 0.0031689 | 0.036157 | 0
| 0 | 0.00070398 | 0.0080324 | 0
| 0.12942 | 0.00014538 | 0.0016587 | 0
| 0 | 0.0043528 | 0.049665 | 0
| 0 | 0.0013997 | 0.01597 | 0
| 0 | 0.0064766 | 0.073898 | 0
| 0 | 0.0061346 | 0.069996 | 0
| 0 | 0.0042552 | 0.048552 | 0
| 0 | 0.0034903 | 0.039824 | 0
| 0 | 0.0044278 | 0.050521 | 0
| 0 | 0.0011297 | 0.012889 | 0
| 0 | 0.0016253 | 0.018545 | 0
| 0 | 0.0081312 | 0.092777 | 0
| 0 | 0.0022022 | 0.025127 | 0
| 0 | 2.2804e-05 | 0.0002602 | 0
| 0 | 0.0044996 | 0.05134 | 0
| 0 | 0.0011628 | 0.013268 | 0
| 0 | 0.00047873 | 0.0054623 | 0
| 0 | 0.002444 | 0.027886 | 0
| 0 | 0.00099523 | 0.011356 | 0
| 0 | 0.0039047 | 0.044553 | 0
| 0 | 0.0051854 | 0.059165 | 0
| 0 | 0.0043786 | 0.04996 | 0
| 0 | 0.0034669 | 0.039558 | 0
| 0 | 0.0039182 | 0.044707 | 0
| 0 | 3.5366e-05 | 0.00040353 | 0
| 0 | 0.0015838 | 0.018071 | 0
| 0 | 0.0078483 | 0.089549 | 0
| 0 | 0.00081075 | 0.0092507 | 0
| 0 | 0.0018923 | 0.021591 | 0
| 0 | 0.003078 | 0.03512 | 0
| 0 | 0.0036293 | 0.04141 | 0
| 0 | 0.0019506 | 0.022257 | 0
| 0 | 0.0014661 | 0.016728 | 0
| 0 | 0.0017506 | 0.019975 | 0
| 0 | 0.008925 | 0.10183 | 0
| 0 | 0.0027852 | 0.031779 | 0
| 0 | 0.0020084 | 0.022916 | 0
| 0 | 0.009966 | 0.11371 | 0
| 0 | 0.0021727 | 0.02479 | 0
| 0 | 0.0064915 | 0.074068 | 0
| 0.081639 | 0.00073128 | 0.0083439 | 0
| 0 | 0.0052088 | 0.059433 | 0
| 0 | 0.0060263 | 0.06876 | 0
| 0 | 6.768e-05 | 0.00077223 | 0
| 0 | 0.0012076 | 0.013779 | 0
| 0 | 0.0043365 | 0.04948 | 0
| 0 | 0.0049808 | 0.056831 | 0
| 0 | 0.0055139 | 0.062914 | 0
| 0 | 0.0022884 | 0.02611 | 0
| 0 | 0.0019685 | 0.022461 | 0
| 0 | 0.0019218 | 0.021928 | 0
| 0 | 0.0053535 | 0.061084 | 0
| 0.10137 | 0.0020337 | 0.023205 | 0
| 0 | 0.0060766 | 0.069334 | 0
| 0 | 0.0014649 | 0.016715 | 0
| 0 | 0.0043473 | 0.049602 | 0
| 0 | 0.0032241 | 0.036787 | 0
| 0 | 0.0090492 | 0.10325 | 0
| 0 | 0.0025432 | 0.029018 | 0
| 0 | 0.0090459 | 0.10321 | 0
| 0 | 0.0010066 | 0.011486 | 0
| 0.024504 | 0.0021983 | 0.025083 | 0
| 0 | 0.0010382 | 0.011846 | 0
| 0 | 0.0025166 | 0.028714 | 0
| 0 | 0.0086636 | 0.098852 | 0
| 0 | 0.0040218 | 0.045889 | 0
| 0 | 0.0021481 | 0.024509 | 0
| 0 | 0.004162 | 0.047488 | 0
| 0 | 0.0021174 | 0.024159 | 0
| 0 | 0.0023907 | 0.027278 | 0
| 0 | 0.0026786 | 0.030563 | 0
| 0 | 0.0051338 | 0.058577 | 0
| 0 | 0.0080025 | 0.091309 | 0
| 0 | 0.0035451 | 0.04045 | 0
| 0 | 0.0031841 | 0.03633 | 0
| 0 | 0.0010284 | 0.011734 | 0
| 0 | 0.00065098 | 0.0074276 | 0
| 0 | 0.0032398 | 0.036967 | 0
| 0 | 0.0045415 | 0.051819 | 0
| 0 | 0.0016345 | 0.01865 | 0
| 0 | 0.0026749 | 0.030521 | 0
| 0 | 0.00045042 | 0.0051393 | 0
| 0 | 0.0020358 | 0.023228 | 0
| 0 | 0.00031661 | 0.0036125 | 0
| 0 | 0.00020601 | 0.0023506 | 0
| 0 | 0.0023312 | 0.026599 | 0
| 0 | 0.0042059 | 0.04799 | 0
| 0 | 0.007618 | 0.086922 | 0
| 0 | 0.0024528 | 0.027986 | 0
| 0 | 0.0030778 | 0.035118 | 0
| 0 | 0.0047613 | 0.054327 | 0
| 0 | 0.0045018 | 0.051366 | 0
| 0 | 0.0037979 | 0.043334 | 0
| 0 | 0.0033272 | 0.037963 | 0
| 0 | 0.00081803 | 0.0093337 | 0
| 0 | 0.0004013 | 0.0045789 | 0
| 0 | 0.0038424 | 0.043842 | 0
| 0 | 0.00025263 | 0.0028825 | 0
| 0 | 0.0048336 | 0.055152 | 0
| 0 | 0.0011863 | 0.013536 | 0
| 0 | 0.0012364 | 0.014108 | 0
| 0 | 0.00042157 | 0.0048102 | 0
| 0 | 0.0017584 | 0.020063 | 0
| 0 | 0.0044971 | 0.051311 | 0
| 0 | 0.0010455 | 0.011929 | 0
| 0 | 0.0059236 | 0.067588 | 0
| 0 | 2.1755e-05 | 0.00024822 | 0
| 0 | 0.0020762 | 0.023689 | 0
| 0 | 0.0054903 | 0.062644 | 0
| 0 | 0.0067864 | 0.077433 | 0
| 0 | 0.0071378 | 0.081442 | 0
| 0 | 0.00051847 | 0.0059157 | 0
| 0 | 0.0091029 | 0.10386 | 0
| 0 | 0.0015668 | 0.017877 | 0
| 0 | 0.0045959 | 0.052439 | 0
| 0 | 0.00405 | 0.04621 | 0
| 0 | 0.00085409 | 0.0097452 | 0
| 0 | 0.0046754 | 0.053347 | 0
| 0 | 0.0053706 | 0.061279 | 0
| 0 | 0.0029228 | 0.033349 | 0
| 0 | 2.1501e-05 | 0.00024533 | 0
| 0 | 0.0076099 | 0.086829 | 0
| 0 | 0.0025577 | 0.029183 | 0
| 0 | 0.0029574 | 0.033744 | 0
| 0 | 0.0024687 | 0.028167 | 0
| 0 | 0.0054719 | 0.062434 | 0
| 0 | 0.0035101 | 0.040051 | 0
| 0 | 0.0075711 | 0.086386 | 0
| 0 | 0.0010625 | 0.012123 | 0
| 0 | 0.0013115 | 0.014964 | 0
| 0 | 0.0010471 | 0.011947 | 0
| 0 | 0.0052833 | 0.060283 | 0
| 0 | 0.00013643 | 0.0015567 | 0
| 0 | 0.0030851 | 0.0352 | 0
| 0 | 0.0027913 | 0.031849 | 0
| 0 | 0.0015967 | 0.018218 | 0
| 0 | 0.0061267 | 0.069905 | 0
| 0 | 0.0013951 | 0.015918 | 0
| 0 | 0.0030313 | 0.034587 | 0
| 0 | 0.0016061 | 0.018325 | 0
| 0 | 0.0026811 | 0.030591 | 0
| 0 | 0.0011601 | 0.013237 | 0
| 0 | 0.0040871 | 0.046633 | 0
| 0 | 0.0050651 | 0.057793 | 0
| 0 | 0.002959 | 0.033762 | 0
| 0 | 0.0023108 | 0.026366 | 0
| 0 | 0.0053443 | 0.060978 | 0
| 0 | 0.00060898 | 0.0069485 | 0
| 0 | 0.0032066 | 0.036588 | 0
| 0 | 0.0060166 | 0.06865 | 0
| 0 | 0.0051912 | 0.059231 | 0
| 0 | 0.0012418 | 0.014169 | 0
| 0 | 0.00091372 | 0.010426 | 0
| 0 | 0.0012605 | 0.014382 | 0
| 0 | 0.0001706 | 0.0019465 | 0
| 0 | 0.0035432 | 0.040427 | 0
| 0 | 0.0089465 | 0.10208 | 0
| 0 | 0.002714 | 0.030966 | 0
| 0 | 0.005218 | 0.059538 | 0
| 0 | 5.5639e-05 | 0.00063484 | 0
| 0 | 0.00089704 | 0.010235 | 0
| 0 | 0.0022666 | 0.025861 | 0
| 0 | 0.0010143 | 0.011573 | 0
| 0 | 0.0027837 | 0.031762 | 0
| 0 | 0.0090223 | 0.10294 | 0
| 0 | 0.0021979 | 0.025077 | 0
| 0 | 0.0026276 | 0.029981 | 0
| 0 | 0.010499 | 0.11979 | 0
| 0 | 0.0025006 | 0.028532 | 0
| 0 | 0.0014366 | 0.016391 | 0
| 0 | 0.0015327 | 0.017488 | 0
| 0 | 0.00017943 | 0.0020473 | 0
| 0 | 6.8903e-06 | 7.8619e-05 | 0
| 0.30925 | 0.00039949 | 0.0045582 | 0
| 0 | 0.0025906 | 0.029559 | 0
| 0 | 0.00041892 | 0.0047799 | 0
| 0 | 0.0019131 | 0.021829 | 0
| 0 | 0.0026098 | 0.029778 | 0
| 0.37383 | 0.001315 | 0.015004 | 0
| 0 | 0.0056135 | 0.06405 | 0
| 0 | 2.0532e-05 | 0.00023427 | 0
| 0 | 0.0049131 | 0.056058 | 0
| 0 | 0.0041036 | 0.046823 | 0
| 0 | 0.0023656 | 0.026992 | 0
| 6.9937 | 0.0018866 | 0.021527 | 0
| 0 | 0.0021118 | 0.024096 | 0
| 0 | 0.0034241 | 0.039069 | 0
| 0 | 0.002476 | 0.028251 | 0
| 0 | 0.0022733 | 0.025939 | 0
| 0 | 0.008487 | 0.096836 | 0
| 0 | 0.0027314 | 0.031165 | 0
| 0 | 0.00043478 | 0.0049608 | 0
| 0 | 0.0014827 | 0.016917 | 0
| 0 | 0.0058266 | 0.066481 | 0
| 0 | 0.0016526 | 0.018856 | 0
| 0.55007 | 0.0038807 | 0.044279 | 0
| 0 | 0.0030206 | 0.034465 | 0
| 0 | 0.013403 | 0.15293 | 0
| 0 | 0.012398 | 0.14146 | 0
| 0 | 0.0020031 | 0.022855 | 0
| 0 | 0.0043505 | 0.049639 | 0
| 0 | 6.7643e-06 | 7.718e-05 | 0
| 0 | 0.0063847 | 0.07285 | 0
| 0 | 0.0013589 | 0.015505 | 0
| 0 | 0.0036422 | 0.041557 | 0
| 0 | 0.0053896 | 0.061495 | 0
| 0 | 0.00748 | 0.085347 | 0
| 0 | 0.0056767 | 0.064771 | 0
| 0 | 0.0016006 | 0.018262 | 0
| 0 | 0.0011012 | 0.012565 | 0
| 0 | 0.0035171 | 0.04013 | 0
| 0 | 0.0031528 | 0.035973 | 0
| 0 | 0.00088523 | 0.0101 | 0
| 0 | 0.0028892 | 0.032966 | 0
| 0 | 0.0055565 | 0.063399 | 0
| 0 | 0.002353 | 0.026848 | 0
| 0 | 0.0030345 | 0.034624 | 0
| 0 | 0.0031113 | 0.0355 | 0
| 0 | 0.0018345 | 0.020931 | 0
| 0 | 0.0015957 | 0.018207 | 0
| 0 | 6.665e-06 | 7.6048e-05 | 0
| 0 | 0.0023719 | 0.027063 | 0
| 0 | 0.0024684 | 0.028164 | 0
| 0 | 0.0010787 | 0.012308 | 0
| 0 | 0.0039503 | 0.045073 | 0
| 0 | 0.0036453 | 0.041592 | 0
| 0 | 0.00028539 | 0.0032563 | 0
| 0 | 0.004374 | 0.049907 | 0
| 0 | 0.0018894 | 0.021558 | 0
| 0 | 0.0038299 | 0.043699 | 0
| 0 | 0.0034767 | 0.039669 | 0
| 0 | 0.0042229 | 0.048184 | 0
| 0 | 5.2934e-05 | 0.00060397 | 0
| 0 | 0.0086247 | 0.098407 | 0
| 0 | 0.0025519 | 0.029117 | 0
| 0 | 0.001409 | 0.016077 | 0
| 0 | 0.00032301 | 0.0036855 | 0
| 0 | 0.001292 | 0.014742 | 0
| 0 | 0.0043418 | 0.04954 | 0
| 0 | 0.0053888 | 0.061487 | 0
| 0 | 0.0010204 | 0.011642 | 0
| 0 | 1.3144e-05 | 0.00014997 | 0
| 0 | 0.00030867 | 0.0035219 | 0
| 0 | 0.0026854 | 0.03064 | 0
| 0 | 0.0069207 | 0.078966 | 0
| 0 | 0.0010343 | 0.011802 | 0
| 0 | 0.0025134 | 0.028677 | 0
| 0 | 0.0064263 | 0.073324 | 0
| 0 | 0.00078369 | 0.0089419 | 0
| 0 | 0.0032784 | 0.037407 | 0
| 0 | 0.0003067 | 0.0034994 | 0
| 0 | 0.0023142 | 0.026405 | 0
| 0 | 0.0067847 | 0.077413 | 0
| 0 | 4.3251e-06 | 4.935e-05 | 0
| 0 | 4.3251e-06 | 4.935e-05 | 0
| 0 | 0.0017767 | 0.020272 | 0
| 0 | 0.0054325 | 0.061985 | 0
| 0 | 0.0028419 | 0.032426 | 0
| 0 | 0.001497 | 0.01708 | 0
| 0 | 0.0043719 | 0.049883 | 0
| 0 | 0.0011064 | 0.012624 | 0
| 0 | 0.0020388 | 0.023262 | 0
| 0 | 0.00075904 | 0.0086606 | 0
| 0 | 0.00098816 | 0.011275 | 0
| 0 | 0.00232 | 0.026472 | 0
| 0 | 0.000968 | 0.011045 | 0
| 0 | 0.00058909 | 0.0067215 | 0
| 0 | 0.0046336 | 0.052869 | 0
| 0 | 1.9183e-05 | 0.00021888 | 0
| 0 | 0.0018456 | 0.021058 | 0
| 0 | 0.0027266 | 0.031111 | 0
| 0 | 0.0016011 | 0.018268 | 0
| 0 | 0.0025443 | 0.029031 | 0
| 0 | 0.0012725 | 0.014519 | 0
| 0 | 0.005504 | 0.062801 | 0
| 0 | 0.0031694 | 0.036163 | 0
| 0 | 0.0048014 | 0.054784 | 0
| 0 | 0.0044751 | 0.051061 | 0
| 0 | 0.0014368 | 0.016393 | 0
| 0 | 0.0025608 | 0.029219 | 0
| 0 | 0.0025625 | 0.029239 | 0
| 0 | 0.0040476 | 0.046183 | 0
| 0 | 0.0016022 | 0.018281 | 0
| 0 | 0.0087352 | 0.099669 | 0
| 0 | 0.0054523 | 0.062211 | 0
| 2.3251 | 0.001245 | 0.014205 | 0
| 0.0020626 | 0.0023939 | 0.027315 | 0
| 0 | 0.0018098 | 0.020649 | 0
| 0 | 0.0010922 | 0.012463 | 0
| 0 | 0.0037504 | 0.042792 | 0
| 0 | 0.0010215 | 0.011655 | 0
| 0 | 9.3315e-05 | 0.0010647 | 0
| 0 | 0.0050016 | 0.057069 | 0
| 0 | 0.0029298 | 0.033429 | 0
| 0 | 0.0055797 | 0.063664 | 0
| 0 | 0.0025282 | 0.028846 | 0
| 0 | 0.0058261 | 0.066476 | 0
| 0 | 0.0011924 | 0.013605 | 0
| 0 | 0.001229 | 0.014023 | 0
| 0 | 0.0015345 | 0.017508 | 0
| 0 | 0.0031665 | 0.036129 | 0
| 0 | 0.0028865 | 0.032935 | 0
| 0 | 0.00105 | 0.011981 | 0
| 0.034084 | 0.00070606 | 0.0080561 | 0
| 0 | 0.0035712 | 0.040748 | 0
| 0 | 0.00094753 | 0.010811 | 0
| 0 | 1.2218e-05 | 0.00013941 | 0
| 0 | 0.00221 | 0.025216 | 0
| 0 | 0.0033048 | 0.037708 | 0
| 0 | 0.00128 | 0.014604 | 0
| 0 | 0.0051131 | 0.05834 | 0
| 0 | 0.00058295 | 0.0066514 | 0
| 0 | 0.0033196 | 0.037876 | 0
| 0 | 0.00013144 | 0.0014997 | 0
| 0 | 0.0065275 | 0.074479 | 0
| 0 | 0.00032082 | 0.0036606 | 0
| 0 | 0.0027506 | 0.031384 | 0
| 0 | 0.0026504 | 0.030241 | 0
| 0 | 0.0032938 | 0.037582 | 0
| 0 | 0.0014112 | 0.016102 | 0
| 0 | 0.0010002 | 0.011413 | 0
| 0 | 0.0025323 | 0.028893 | 0
| 0 | 1.7965e-05 | 0.00020498 | 0
| 0 | 0.0045604 | 0.052034 | 0
| 0 | 0.00090218 | 0.010294 | 0
| 0 | 0.00030445 | 0.0034738 | 0
| 0 | 0.0012695 | 0.014485 | 0
| 0 | 0.0030352 | 0.034631 | 0
| 0 | 1.7842e-05 | 0.00020357 | 0
| 0 | 0.0027309 | 0.03116 | 0
| 0 | 0.0038818 | 0.044291 | 0
| 0 | 0.00013607 | 0.0015526 | 0
| 0 | 0.002264 | 0.025832 | 0
| 0 | 0.0035287 | 0.040263 | 0
| 0 | 0.0012855 | 0.014668 | 0
| 0 | 3.9289e-06 | 4.4829e-05 | 0
| 0 | 3.9289e-06 | 4.4829e-05 | 0
| 0 | 0.00017081 | 0.0019489 | 0
| 0 | 0.0018125 | 0.020681 | 0
| 0 | 0.0017694 | 0.020189 | 0
| 0 | 0.0039078 | 0.044589 | 0
| 0 | 0.0020498 | 0.023389 | 0
| 0 | 0.0010264 | 0.011711 | 0
| 0 | 0.0015908 | 0.018151 | 0
| 0 | 0.00040933 | 0.0046704 | 0
| 0 | 0.00030936 | 0.0035298 | 0
| 0 | 0.0032954 | 0.037601 | 0
| 0 | 5.2347e-05 | 0.00059728 | 0
| 0 | 0.00090544 | 0.010331 | 0
| 0 | 0.0022964 | 0.026202 | 0
| 0 | 0.0020808 | 0.023742 | 0
| 0 | 5.7393e-06 | 6.5485e-05 | 0
| 0 | 0.0011705 | 0.013355 | 0
| 0 | 0.0045132 | 0.051496 | 0
| 0 | 0.00039873 | 0.0045495 | 0
| 0 | 0.00087134 | 0.009942 | 0
| 0 | 0.0031081 | 0.035463 | 0
| 0 | 0.00052356 | 0.0059738 | 0
| 0 | 0.00068086 | 0.0077686 | 0
| 0 | 0.0031712 | 0.036183 | 0
| 0 | 0.0013094 | 0.01494 | 0
| 0 | 0.0018076 | 0.020625 | 0
| 0 | 0.0015692 | 0.017905 | 0
| 0 | 2.83e-05 | 0.0003229 | 0
| 0 | 0.0017206 | 0.019633 | 0
| 0 | 0.00029973 | 0.0034199 | 0
| 0 | 0.011786 | 0.13448 | 0
| 0 | 0.0025758 | 0.02939 | 0
| 0 | 0.0014973 | 0.017084 | 0
| 0 | 0.0011364 | 0.012966 | 0
| 0 | 0.00052241 | 0.0059607 | 0
| 0 | 0.0032802 | 0.037427 | 0
| 0 | 0.0024599 | 0.028068 | 0
| 0 | 0.0017051 | 0.019455 | 0
| 0 | 0.0010917 | 0.012456 | 0
| 0 | 0.003884 | 0.044317 | 0
| 0 | 1.6688e-05 | 0.00019041 | 0
| 0 | 0.0069058 | 0.078796 | 0
| 0 | 0.00082515 | 0.0094149 | 0
| 0 | 0.0037422 | 0.042698 | 0
| 0 | 0.0030161 | 0.034413 | 0
| 0.0036389 | 0.00030424 | 0.0034713 | 0
| 0 | 0.0056029 | 0.06393 | 0
| 0 | 0.0042376 | 0.048351 | 0
| 0 | 0.0055433 | 0.063249 | 0
| 0 | 0.0017662 | 0.020153 | 0
| 0 | 0.00031439 | 0.0035872 | 0
| 0 | 0.0057052 | 0.065096 | 0
| 5.4173 | 0.0017312 | 0.019753 | 0
| 0 | 0.0033915 | 0.038697 | 0
| 0 | 0.0027688 | 0.031592 | 0
| 0 | 0.002661 | 0.030362 | 0
| 0 | 0.0014572 | 0.016627 | 0
| 0 | 0.00017414 | 0.001987 | 0
| 0 | 0.0029894 | 0.034109 | 0
| 0 | 0.00015181 | 0.0017322 | 0
| 0 | 0.000797 | 0.0090937 | 0
| 0 | 0.00072067 | 0.0082229 | 0
| 0 | 0.0014122 | 0.016114 | 0
| 0 | 5.4056e-06 | 6.1678e-05 | 0
| 0 | 5.3876e-06 | 6.1472e-05 | 0
| 0 | 1.6126e-05 | 0.000184 | 0
| 0 | 0.0012727 | 0.014522 | 0
| 0 | 0.00018652 | 0.0021282 | 0
| 0 | 0.001354 | 0.01545 | 0
| 0 | 0.0029887 | 0.034101 | 0
| 0 | 0.0010705 | 0.012214 | 0
| 0 | 0.0025356 | 0.028931 | 0
| 0 | 0.0034261 | 0.039092 | 0
| 0 | 0.0010313 | 0.011767 | 0
| 0 | 0.0029776 | 0.033975 | 0
| 0 | 0.00026974 | 0.0030778 | 0
| 0 | 0.00068421 | 0.0078068 | 0
| 0 | 0.0036442 | 0.04158 | 0
| 0 | 0.0035124 | 0.040077 | 0
| 0 | 5.1314e-06 | 5.8549e-05 | 0
| 0 | 0.0028942 | 0.033023 | 0
| 0 | 0.0017773 | 0.020279 | 0
| 0 | 0.0037183 | 0.042426 | 0
| 0 | 0.0005889 | 0.0067194 | 0
| 0 | 0.0020468 | 0.023354 | 0
| 0 | 0.0027373 | 0.031232 | 0
| 0 | 0.0027471 | 0.031344 | 0
| 0 | 0.00061185 | 0.0069813 | 0
| 0 | 0.00050358 | 0.0057458 | 0
| 0 | 0.00075711 | 0.0086386 | 0
| 0 | 3.5411e-05 | 0.00040404 | 0
| 0 | 0.0012532 | 0.014299 | 0
| 0 | 0.0011467 | 0.013084 | 0
| 0 | 0.0022377 | 0.025532 | 0
| 0 | 0.0033335 | 0.038036 | 0
| 0 | 0.00096791 | 0.011044 | 0
| 0 | 0.0026898 | 0.03069 | 0
| 0 | 0.0035189 | 0.040151 | 0
| 0 | 4.3002e-05 | 0.00049065 | 0
| 0 | 0.00072889 | 0.0083166 | 0
| 0 | 0.0031111 | 0.035497 | 0
| 0 | 0.00098276 | 0.011213 | 0
| 0 | 9.8651e-06 | 0.00011256 | 0
| 0 | 0.0031955 | 0.036461 | 0
| 0 | 0.0045333 | 0.051725 | 0
| 0 | 0.003249 | 0.037071 | 0
| 0 | 0.00080077 | 0.0091367 | 0
| 0 | 0.0010465 | 0.01194 | 0
| 0 | 0.0034428 | 0.039283 | 0
| 0 | 0.0014219 | 0.016224 | 0
| 0.069848 | 0.0019228 | 0.021939 | 0
| 0 | 4.814e-06 | 5.4927e-05 | 0
| 0 | 0.0021816 | 0.024892 | 0
| 0.022822 | 0.00039285 | 0.0044824 | 0
| 0 | 0.0016286 | 0.018583 | 0
| 0 | 0.00016685 | 0.0019038 | 0
| 0 | 0.00039667 | 0.004526 | 0
| 0 | 0.0034219 | 0.039044 | 0
| 0 | 0.00063788 | 0.0072782 | 0
| 0.060491 | 0.00016526 | 0.0018857 | 0
| 0 | 0.00028747 | 0.00328 | 0
| 0 | 0.0042369 | 0.048343 | 0
| 0 | 0.0050734 | 0.057887 | 0
| 0 | 0.0019379 | 0.022111 | 0
| 0 | 0.00047781 | 0.0054518 | 0
| 0 | 0.0023142 | 0.026405 | 0
| 0.02134 | 0.00017009 | 0.0019408 | 0
| 0.097199 | 0.0038979 | 0.044475 | 0
| 0 | 0.00054556 | 0.0062248 | 0
| 0 | 0.0012068 | 0.01377 | 0
| 0 | 1.8206e-05 | 0.00020773 | 0
| 0 | 0.0056887 | 0.064908 | 0
| 0 | 0.00073618 | 0.0083998 | 0
| 0.26324 | 0.0052715 | 0.060148 | 0
| 0 | 0.00071852 | 0.0081983 | 0
| 0 | 0.0033022 | 0.037678 | 0
| 0 | 2.6986e-05 | 0.00030792 | 0
| 0 | 0.0037166 | 0.042407 | 0
| 0 | 3.5596e-05 | 0.00040615 | 0
| 0 | 0.0036157 | 0.041255 | 0
| 0 | 0.0005435 | 0.0062013 | 0
| 0 | 7.0602e-05 | 0.00080557 | 0
| 0.47837 | 0.0022213 | 0.025345 | 0
| 0 | 0.00037265 | 0.0042519 | 0
| 0 | 0.00028363 | 0.0032362 | 0
| 0 | 0.00051916 | 0.0059237 | 0
| 0 | 0.00122 | 0.01392 | 0
| 0 | 0.0033913 | 0.038694 | 0
| 0 | 0.00040348 | 0.0046037 | 0
| 0.090712 | 0.00023553 | 0.0026874 | 0
| 0 | 0.00048261 | 0.0055066 | 0
| 0 | 1.271e-05 | 0.00014502 | 0
| 0 | 0.0052062 | 0.059403 | 0
| 0 | 0.00020622 | 0.0023529 | 0
| 0 | 0.0013528 | 0.015435 | 0
| 0 | 0.0016833 | 0.019207 | 0
| 0 | 0.0029379 | 0.033522 | 0
| 0 | 8.2837e-06 | 9.4517e-05 | 0
| 0 | 0.00014415 | 0.0016448 | 0
| 0 | 0.007701 | 0.087869 | 0
| 0 | 4.0964e-06 | 4.674e-05 | 0
| 0 | 4.0816e-06 | 4.6571e-05 | 0
| 0 | 1.0858e-05 | 0.00012389 | 0
| 0 | 2.8219e-05 | 0.00032198 | 0
| 0 | 9.6183e-05 | 0.0010974 | 0
| 0 | 0.0013376 | 0.015262 | 0
| 0 | 3.1432e-05 | 0.00035864 | 0
| 0 | 3.7703e-05 | 0.0004302 | 0
| 0 | 0.003106 | 0.035439 | 0
| 0 | 0.0042232 | 0.048187 | 0
| 0 | 0.00036788 | 0.0041975 | 0
| 0 | 0.0014723 | 0.016799 | 0
| 0 | 0.002981 | 0.034014 | 0
| 0 | 0.0013555 | 0.015466 | 0
| 0 | 0.0024319 | 0.027748 | 0
| 0 | 0.0052305 | 0.059681 | 0
| 0 | 0.0029127 | 0.033234 | 0
| 0 | 0.0039456 | 0.04502 | 0
| 0 | 3.6696e-06 | 4.187e-05 | 0
| 0 | 7.2586e-06 | 8.2821e-05 | 0
| 0 | 0.0013032 | 0.01487 | 0
| 0 | 0.00040737 | 0.0046481 | 0
| 0 | 0.0033438 | 0.038153 | 0
| 0 | 0.0041515 | 0.047368 | 0
| 0 | 0.00018418 | 0.0021015 | 0
| 0 | 0.0010463 | 0.011939 | 0
| 0 | 0.0021618 | 0.024666 | 0
| 0 | 0.001468 | 0.01675 | 0
| 0 | 6.7989e-06 | 7.7575e-05 | 0
| 0 | 1.3456e-05 | 0.00015353 | 0
| 0 | 0.0050105 | 0.057169 | 0
| 0 | 0.0006539 | 0.007461 | 0
| 0 | 0.0051463 | 0.058719 | 0
| 0 | 0.0017179 | 0.019601 | 0
| 0 | 0.0027448 | 0.031318 | 0
| 0 | 0.0003738 | 0.0042651 | 0
| 0 | 0.002723 | 0.031069 | 0
| 0 | 2.891e-06 | 3.2986e-05 | 0
| 0 | 5.6561e-06 | 6.4537e-05 | 0
| 0 | 0.00028344 | 0.003234 | 0
| 0 | 2.7636e-06 | 3.1533e-05 | 0
| 0 | 8.0333e-05 | 0.00091659 | 0
| 0 | 0.00062672 | 0.0071509 | 0
| 0 | 4.4754e-06 | 5.1064e-05 | 0
| 0 | 2.1739e-06 | 2.4804e-05 | 0
| 0 | 0.00033717 | 0.0038471 | 0
| 0 | 2.0229e-06 | 2.3082e-05 | 0
| 0 | 0.00018031 | 0.0020573 | 0
| 0.9458 | 0.00036416 | 0.0041551 | 0
| 0 | 0.00019873 | 0.0022675 | 0
| 0 | 0.00028765 | 0.0032821 | 0
| 0 | 8.009e-05 | 0.00091383 | 0
| 0 | 6.8927e-05 | 0.00078646 | 0
| 0.12746 | 0.00044147 | 0.0050372 | 0
| 0.085313 | 0.0001011 | 0.0011536 | 0
| 0 | 0.00013705 | 0.0015637 | 0
| 0.029711 | 7.9924e-05 | 0.00091194 | 0
| 0 | 0.00018413 | 0.0021009 | 0
| 0 | 6.312e-05 | 0.0007202 | 0
| 0 | 0.00036904 | 0.0042108 | 0
| 0 | 0.00025693 | 0.0029316 | 0
| 0 | 0.0001719 | 0.0019613 | 0
| 0 | 0.00016102 | 0.0018373 | 0
| 0 | 0.00019186 | 0.0021892 | 0
| 0 | 5.5991e-05 | 0.00063885 | 0
| 0 | 0.00026578 | 0.0030325 | 0
| 0 | 0.00015535 | 0.0017725 | 0
| 0 | 5.0866e-06 | 5.8038e-05 | 0
| 0 | 0.00020502 | 0.0023393 | 0
| 0 | 4.4798e-05 | 0.00051115 | 0
| 0 | 1.9998e-05 | 0.00022818 | 0
| 0 | 6.4816e-05 | 0.00073955 | 0
| 0 | 2.0408e-05 | 0.00023285 | 0
| 0 | 2.559e-05 | 0.00029199 | 0
| 0 | 1.4182e-06 | 1.6182e-05 | 0
| 0 | 1.6355e-07 | 1.8661e-06 | 0
| 0.014756 |  | 0 | 0
| 0.0085228 |  | 0 | 0
| 0.011289 |  | 0 | 0
| 0.0070409 |  | 0 | 0
| 0 |  | 0 | 0
| 0.11384 |  | 0 | 0

## PSPS_Data
circuit_name | circuit_segment | psps_risk[ann] | dx_risk[ann] | tx_risk[ann] | TxDx_risk[ann] | event_count[ann] | cust_count[ann] | Tot_Dur[ann] | psps_conseq
|  | 18.8693 | 9.4774 | 0 | 9.3919 | 1.6667 | 3257.1667 | 151103.9416 | 11.3216
|  | 18.1809 | 6.204 | 5.7714 | 6.2055 | 2.1667 | 4070.3333 | 178273.5878 | 8.3912
|  | 15.7304 | 7.8765 | 0.0099098 | 7.844 | 1.6667 | 2638 | 121971.7252 | 9.4382
|  | 14.0205 | 7.0337 | 0.0072309 | 6.9795 | 0.66667 | 2332 | 106686.3498 | 21.0307
|  | 13.0847 | 4.4318 | 4.2366 | 4.4164 | 2 | 2642.6667 | 115836.4988 | 6.5424
|  | 12.5802 | 4.2638 | 4.0479 | 4.2684 | 2 | 2396.1667 | 105724.4056 | 6.2901
|  | 12.0173 | 4.033 | 3.9471 | 4.0372 | 2 | 2363.3333 | 103605.163 | 6.0087
|  | 11.9355 | 4.0428 | 3.8578 | 4.035 | 0.66667 | 2011.1667 | 102501.8577 | 17.9033
|  | 10.4169 | 0.081756 | 5.1447 | 5.1905 | 1.3333 | 2446.1667 | 97544.3179 | 7.8127
|  | 10.0072 | 5.0121 | 0 | 4.9951 | 1.6667 | 1825.8333 | 84654.2351 | 6.0043
|  | 9.9833 | 5.0004 | 0 | 4.9829 | 1.8333 | 2969 | 99602.0685 | 5.4454
|  | 9.1295 | 3.0869 | 2.9712 | 3.0715 | 0.66667 | 1579.3333 | 80500.9753 | 13.6943
|  | 8.9649 | 0.16146 | 4.3487 | 4.4547 | 1.3333 | 1955 | 83285.9914 | 6.7237
|  | 8.7174 | 4.3612 | 0.011695 | 4.3445 | 2.1667 | 1954.8333 | 80543.579 | 4.0234
|  | 8.4952 | 4.2502 | 0.0064617 | 4.2385 | 1.6667 | 1589 | 71623.4988 | 5.0971
|  | 8.0634 | 2.731 | 2.6045 | 2.728 | 2 | 1822.3333 | 78510.663 | 4.0317
|  | 7.8341 | 2.6188 | 2.5989 | 2.6164 | 1 | 1769.3333 | 80501.4161 | 7.8341
|  | 7.7386 | 3.8798 | 0 | 3.8588 | 0.83333 | 1944.5 | 68097.0378 | 9.2863
|  | 7.6975 | 0.27593 | 3.5884 | 3.8332 | 1.3333 | 1736 | 69227.9049 | 5.7731
|  | 7.6588 | 3.831 | 0.0013463 | 3.8264 | 1.8333 | 1399.6667 | 59608.0031 | 4.1775
|  | 7.5542 | 2.5357 | 2.4864 | 2.532 | 1 | 3152.3333 | 101929.0827 | 7.5542
|  | 7.5102 | 7.5102 | 0 | 0 | 1.1667 | 1297 | 60718.6687 | 6.4373
|  | 7.4151 | 2.9491 | 1.5098 | 2.9563 | 1.8333 | 1634 | 73374.7377 | 4.0446
|  | 7.1549 | 3.5721 | 0.0088214 | 3.574 | 2 | 1816.5 | 59661.7339 | 3.5774
|  | 6.9592 | 3.4791 | 0.00044878 | 3.4796 | 1.8333 | 1019.6667 | 45143.0827 | 3.7959
|  | 6.8975 | 3.448 | 0 | 3.4495 | 2.5 | 2259.3333 | 71910.8234 | 2.759
|  | 6.8636 | 3.4404 | 0.0058519 | 3.4173 | 1.1667 | 1327.8333 | 50503.3721 | 5.8831
|  | 6.8262 | 3.4154 | 0 | 3.4109 | 1.8333 | 1565.1667 | 74942.4901 | 3.7234
|  | 6.5747 | 3.292 | 0.0065783 | 3.2761 | 2.6667 | 1344.5 | 62325.5827 | 2.4655
|  | 6.5477 | 3.2739 | 0 | 3.2739 | 1.8333 | 417.3333 | 18524 | 3.5715
|  | 6.5355 | 0.0020717 | 3.2359 | 3.2976 | 0.66667 | 1138.8333 | 55222.4179 | 9.8033
|  | 6.4888 | 3.2474 | 0 | 3.2414 | 1.5 | 1833.3333 | 59881.2351 | 4.3259
|  | 6.3395 | 3.1697 | 0 | 3.1698 | 0.83333 | 1692.3333 | 59239.7153 | 7.6074
|  | 6.2543 | 3.0673 | 0.12048 | 3.0665 | 1.1667 | 1539.5 | 56208.9014 | 5.3608
|  | 6.1644 | 3.0788 | 0.006781 | 3.0788 | 2.6667 | 1110.5 | 50066.5 | 2.3117
|  | 6.1405 | 2.0959 | 1.9449 | 2.0997 | 2 | 1532.8333 | 67644.0741 | 3.0702
|  | 6.1357 | 3.0689 | 0.00089757 | 3.0659 | 1.6667 | 1068.5 | 42377.0827 | 3.6814
|  | 6.0531 | 3.0384 | 0.00044878 | 3.0142 | 1.3333 | 1131.1667 | 55565.8278 | 4.5398
|  | 5.9321 | 2.9615 | 0.0044878 | 2.9662 | 0.66667 | 1232.3333 | 50529.4136 | 8.8982
|  | 5.9045 | 2.9523 | 0 | 2.9523 | 2.3333 | 1717.3333 | 75194.6667 | 2.5305
|  | 5.8403 | 2.9334 | 0.00044878 | 2.9065 | 2 | 1177 | 45665.0043 | 2.9202
|  | 5.7583 | 2.8843 | 0.0061192 | 2.8678 | 0.83333 | 1592.6667 | 56389.0629 | 6.9099
|  | 5.7329 | 1.9435 | 1.8441 | 1.9453 | 2 | 1154.6667 | 50625.6642 | 2.8665
|  | 5.7243 | 2.8648 | 0.0061529 | 2.8533 | 1.8333 | 1379.3333 | 47697.2469 | 3.1223
|  | 5.7215 | 0.14989 | 2.741 | 2.8306 | 1.3333 | 1172.6667 | 46840.2395 | 4.2911
|  | 5.7003 | 2.8565 | 0.0013463 | 2.8425 | 2.6667 | 1238 | 55786.1654 | 2.1376
|  | 5.6847 | 2.8435 | 0.00044878 | 2.8407 | 1.6667 | 1454.3333 | 56412.2494 | 3.4108
|  | 5.4301 | 1.8208 | 1.7881 | 1.8212 | 0.66667 | 1065.6667 | 54353.9117 | 8.1452
|  | 5.419 | 2.718 | 0.00044878 | 2.7005 | 0.83333 | 1140.1667 | 40370.5629 | 6.5028
|  | 5.4154 | 2.711 | 0 | 2.7044 | 1.8333 | 1199.3333 | 49172.5 | 2.9539
|  | 5.394 | 2.6952 | 0.0022001 | 2.6966 | 0.66667 | 1315.6667 | 53942.0827 | 8.0909
|  | 5.3864 | 1.8089 | 1.7715 | 1.806 | 0.83333 | 1658.8333 | 58726.8278 | 6.4636
|  | 5.3358 | 1.8283 | 1.6787 | 1.8288 | 1.6667 | 1207 | 52987.0827 | 3.2015
|  | 5.2958 | 0.73147 | 3.1059 | 1.4584 | 1.8333 | 1166.5 | 51259.8265 | 2.8886
|  | 5.1928 | 2.5938 | 0 | 2.599 | 1.1667 | 904.1667 | 44691.1568 | 4.4509
|  | 5.1111 | 0.084319 | 2.4958 | 2.531 | 1.3333 | 1226.3333 | 50435.0815 | 3.8333
|  | 5.0826 | 1.7158 | 1.6482 | 1.7186 | 1.6667 | 1120.3333 | 49181.3297 | 3.0495
|  | 5.0136 | 2.507 | 0.0050519 | 2.5015 | 2 | 1525.3333 | 51533.4049 | 2.5068
|  | 4.9889 | 2.4743 | 0.022372 | 2.4922 | 1.5 | 1339.5 | 62361.1667 | 3.3259
|  | 4.9668 | 1.8041 | 1.3571 | 1.8056 | 1.8333 | 1223.5 | 54945.1654 | 2.7092
|  | 4.9485 | 1.7215 | 1.5054 | 1.7216 | 1 | 840 | 42048.6698 | 4.9485
|  | 4.9385 | 1.6513 | 1.6342 | 1.6531 | 0.66667 | 807.6667 | 41148.9752 | 7.4078
|  | 4.8911 | 2.4551 | 0.00044878 | 2.4355 | 1.3333 | 978 | 48040.7395 | 3.6683
|  | 4.8747 | 4.8747 | 0 | 0 | 1.1667 | 919 | 44365.465 | 4.1783
|  | 4.6446 | 1.5618 | 1.5304 | 1.5524 | 2.1667 | 1237.1667 | 41855.6667 | 2.1437
|  | 4.6404 | 4.6404 | 0 | 0 | 2 | 566.6667 | 20690.0123 | 2.3202
|  | 4.6326 | 2.3192 | 0.0013463 | 2.3121 | 1.3333 | 1213.6667 | 50214.6301 | 3.4745
|  | 4.621 | 0.82602 | 1.4935 | 2.3015 | 1.5 | 953.5 | 39512.2438 | 3.0807
|  | 4.5567 | 4.5567 | 0 | 0 | 1.1667 | 902.3333 | 43564.3457 | 3.9057
|  | 4.5174 | 2.2604 | 0.0039404 | 2.253 | 1.8333 | 867.3333 | 29295.5784 | 2.464
|  | 4.5143 | 2.2622 | 0.0018047 | 2.2502 | 0.66667 | 1098.8333 | 46117.3721 | 6.7714
|  | 4.4883 | 1.5071 | 1.4597 | 1.5215 | 2 | 1018.6667 | 44234.492 | 2.2442
|  | 4.4794 | 0.091345 | 2.1536 | 2.2344 | 1.3333 | 1201.3333 | 49404.8333 | 3.3596
|  | 4.4086 | 1.5071 | 1.3974 | 1.5041 | 2.1667 | 1457.5 | 49011.4988 | 2.0347
|  | 4.3983 | 0.19375 | 2.0151 | 2.1894 | 1.3333 | 961.3333 | 40377.6642 | 3.2987
|  | 4.3874 | 2.1963 | 0.0023389 | 2.1888 | 0.83333 | 1009 | 35724.2395 | 5.2649
|  | 4.3224 | 2.175 | 0 | 2.1474 | 2 | 974.3333 | 43520.1568 | 2.1612
|  | 4.2923 | 1.5578 | 1.1724 | 1.5621 | 2 | 1083 | 47019.7445 | 2.1461
|  | 4.2688 | 2.1369 | 0.00044878 | 2.1315 | 2 | 472.6667 | 21495.3377 | 2.1344
|  | 4.2583 | 1.3751 | 1.4323 | 1.4509 | 1.6667 | 708.5 | 31908.5 | 2.555
|  | 4.2405 | 1.9041 | 2.2553 | 0.08104 | 0.83333 | 1101.3333 | 44248.6869 | 5.0886
|  | 4.1491 | 2.0746 | 0 | 2.0746 | 1.8333 | 722.3333 | 30666.3333 | 2.2632
|  | 4.1266 | 2.074 | 0 | 2.0525 | 1.8333 | 604.8333 | 28253.745 | 2.2509
|  | 4.1028 | 2.0524 | 0.0013463 | 2.0491 | 2.1667 | 371.3333 | 16793.0815 | 1.8936
|  | 4.0673 | 1.3673 | 1.3415 | 1.3585 | 1 | 906.1667 | 41230.0043 | 4.0673
|  | 4.0636 | 4.0636 | 0 | 0 | 1 | 1060.3333 | 36586.2387 | 4.0636
|  | 4.0522 | 2.0238 | 0.00089757 | 2.0274 | 2 | 1204 | 49101.8278 | 2.0261
|  | 4.0463 | 0.071536 | 1.963 | 2.0117 | 1.3333 | 1130 | 45061.4061 | 3.0347
|  | 3.9965 | 1.9911 | 0.0049231 | 2.0005 | 1.5 | 682.8333 | 31788.5827 | 2.6644
|  | 3.9384 | 1.3415 | 1.2601 | 1.3368 | 0.66667 | 888.1667 | 45277.8364 | 5.9076
|  | 3.9077 | 1.9553 | 0.00089757 | 1.9515 | 1.6667 | 752.3333 | 33928.9988 | 2.3446
|  | 3.8444 | 1.9174 | 0.0048498 | 1.9222 | 0.66667 | 917.3333 | 38765.0604 | 5.7667
|  | 3.8203 | 1.9102 | 0 | 1.9102 | 2 | 1100 | 36116.6667 | 1.9102
|  | 3.7628 | 1.8793 | 0.00044878 | 1.8831 | 1.8333 | 829.5 | 34099.9845 | 2.0525
|  | 3.7604 | 0.041914 | 1.8421 | 1.8763 | 1.1667 | 1702 | 38212.992 | 3.2232
|  | 3.7204 | 1.8624 | 0.0013463 | 1.8567 | 2 | 524.3333 | 24950.0914 | 1.8602
|  | 3.7185 | 3.7185 | 0 | 0 | 1 | 867.5 | 30038.644 | 3.7185
|  | 3.7152 | 1.8659 | 0 | 1.8493 | 1.1667 | 782.1667 | 38658.9018 | 3.1845
|  | 3.6988 | 1.8463 | 0.0017951 | 1.8506 | 1.8333 | 926.1667 | 41590.7228 | 2.0175
|  | 3.6924 | 1.8656 | 0 | 1.8268 | 2.3333 | 837.8333 | 36685.245 | 1.5825
|  | 3.6831 | 1.84 | 0.00073683 | 1.8424 | 1.1667 | 1109.1667 | 41696.6369 | 3.157
|  | 3.6547 | 3.6547 | 0 | 0 | 1 | 975.1667 | 36731.2263 | 3.6547
|  | 3.5954 | 1.7977 | 0 | 1.7977 | 2.3333 | 1289.3333 | 41471.3333 | 1.5409
|  | 3.5849 | 0.063239 | 1.7466 | 1.7752 | 1.3333 | 941.8333 | 38734.1611 | 2.6887
|  | 3.5539 | 1.7812 | 0 | 1.7727 | 2.3333 | 574.3333 | 18300.8234 | 1.5231
|  | 3.5388 | 1.772 | 0 | 1.7668 | 1.8333 | 1098.8333 | 37464.4018 | 1.9303
|  | 3.5284 | 1.7673 | 0.00044878 | 1.7607 | 0.83333 | 882.1667 | 31232.8278 | 4.234
|  | 3.4931 | 1.7466 | 0 | 1.7466 | 1.1667 | 487 | 24070.3333 | 2.9941
|  | 3.4742 | 1.7451 | 0.011725 | 1.7174 | 0.66667 | 636 | 29093.5586 | 5.2113
|  | 3.4409 | 1.7223 | 0.00089757 | 1.7177 | 0.83333 | 748.5 | 26503.9701 | 4.129
|  | 3.3942 | 1.7041 | 0 | 1.6901 | 1.6667 | 891.1667 | 30397.745 | 2.0365
|  | 3.3833 | 0.059726 | 1.6477 | 1.6758 | 1.3333 | 684 | 28129.5 | 2.5375
|  | 3.381 | 1.1291 | 1.1228 | 1.1291 | 1 | 1425 | 46075 | 3.381
|  | 3.3279 | 3.3279 | 0 | 0 | 0.16667 | 729.8333 | 32781.364 | 19.9674
|  | 3.3183 | 0.55375 | 1.3708 | 1.3937 | 1 | 697 | 32674.7494 | 3.3183
|  | 3.2926 | 3.2926 | 0 | 0 | 2 | 1094.1667 | 37508.893 | 1.6463
|  | 3.292 | 3.292 | 0 | 0 | 0 | 1139.6667 | 42575.6673 | #DIV/0!
|  | 3.2835 | 1.1171 | 1.0623 | 1.104 | 0.66667 | 522.1667 | 26620.9963 | 4.9252
|  | 3.2812 | 1.0961 | 1.0896 | 1.0954 | 1 | 753.6667 | 34284.4161 | 3.2812
|  | 3.2359 | 3.2359 | 0 | 0 | 1 | 979.8333 | 33806.6317 | 3.2359
|  | 3.2265 | 1.6183 | 0 | 1.6082 | 1.1667 | 596.3333 | 29475.0784 | 2.7656
|  | 3.2165 | 1.6142 | 0.00089757 | 1.6014 | 0.83333 | 795.3333 | 28164.5672 | 3.8598
|  | 3.1946 | 0.071889 | 1.5379 | 1.5849 | 0.66667 | 668 | 31224.7382 | 4.792
|  | 3.1898 | 0.96811 | 1.0967 | 1.125 | 2 | 591 | 25591.6618 | 1.5949
|  | 3.1549 | 1.5805 | 0.0022108 | 1.5722 | 0.5 | 509.8333 | 28036.9161 | 6.3097
|  | 3.1491 | 1.0497 | 1.0497 | 1.0497 | 1.8333 | 962.5 | 33862.5 | 1.7177
|  | 3.1287 | 0.035133 | 1.5358 | 1.5578 | 1.3333 | 909.8333 | 37418.1611 | 2.3465
|  | 3.1266 | 1.5654 | 0 | 1.5612 | 1.3333 | 654.6667 | 32160.5 | 2.3449
|  | 3.1077 | 1.5524 | 0.0027871 | 1.5525 | 0.83333 | 604 | 31523.6468 | 3.7293
|  | 3.0966 | 0.058359 | 0 | 3.0383 | 1.6667 | 460.8333 | 21444.8333 | 1.858
|  | 3.0765 | 3.0765 | 0 | 0 | 1 | 763.5 | 27868.179 | 3.0765
|  | 3.0715 | 0.23364 | 1.3229 | 1.515 | 0.66667 | 554.1667 | 25904.5771 | 4.6072
|  | 3.0621 | 3.0621 | 0 | 0 | 1 | 748.3333 | 27314.4527 | 3.0621
|  | 3.0445 | 1.4761 | 0.00044878 | 1.5679 | 0.66667 | 619 | 30907.0827 | 4.5667
|  | 3.036 | 1.0169 | 1.0022 | 1.0169 | 0.83333 | 831.8333 | 29448.0043 | 3.6432
|  | 3.0334 | 1.5186 | 0 | 1.5149 | 1.1667 | 542.5 | 26815 | 2.6001
|  | 3.0305 | 1.5168 | 0.0036201 | 1.51 | 1.6667 | 815.1667 | 27635.9117 | 1.8183
|  | 3.0303 | 3.0303 | 0 | 0 | 0 | 1013.3333 | 37856.1066 | #DIV/0!
|  | 3.0254 | 0.024593 | 1.4967 | 1.5042 | 1.3333 | 770.8333 | 31701.0784 | 2.2691
|  | 3.0224 | 0 | 3.0224 | 0 | 0.5 | 710.5 | 30077.2188 | 6.0449
|  | 3.0168 | 1.5101 | 0 | 1.5067 | 1.6667 | 458.3333 | 18376.5784 | 1.8101
|  | 3.0001 | 1.0196 | 0.95904 | 1.0215 | 1.5 | 896.6667 | 33980.1599 | 2.0001
|  | 2.9622 | 1.481 | 0 | 1.4812 | 1 | 876 | 31149.745 | 2.9622
|  | 2.9598 | 1.4072 | 0.078468 | 1.4741 | 1.5 | 577.8333 | 29598.9148 | 1.9732
|  | 2.9512 | 0.0082867 | 1.4662 | 1.4767 | 0.66667 | 493.6667 | 24327.8321 | 4.4268
|  | 2.9487 | 0 | 1.4593 | 1.4894 | 0.66667 | 569 | 27591.6555 | 4.4231
|  | 2.936 | 1.4668 | 0 | 1.4692 | 2 | 816.1667 | 26662.3919 | 1.468
|  | 2.9195 | 1.4611 | 0 | 1.4585 | 1.6667 | 836 | 34442.5498 | 1.7517
|  | 2.918 | 1.4666 | 0.00044878 | 1.4509 | 1.8333 | 585.5 | 24099.9845 | 1.5916
|  | 2.9116 | 1.4565 | 0.0013458 | 1.4537 | 0.83333 | 591 | 29283.0043 | 3.4939
|  | 2.9073 | 0.060356 | 1.3991 | 1.4478 | 1.1667 | 1049.1667 | 23538.2494 | 2.492
|  | 2.8709 | 1.4323 | 0.0035026 | 1.4351 | 1.3333 | 703.6667 | 28607.1281 | 2.1531
|  | 2.8707 | 1.4405 | 0 | 1.4301 | 1.8333 | 601.3333 | 26622.6667 | 1.5658
|  | 2.8596 | 1.4296 | 0.0018688 | 1.4281 | 0.83333 | 724.3333 | 25356.3234 | 3.4315
|  | 2.8369 | 0.95852 | 0.92065 | 0.95776 | 0.66667 | 631.6667 | 32207.2482 | 4.2554
|  | 2.8259 | 1.4155 | 0.00089757 | 1.4095 | 1.6667 | 750.8333 | 26061.2438 | 1.6955
|  | 2.8179 | 1.411 | 0 | 1.4069 | 1.1667 | 835.1667 | 29001.745 | 2.4153
|  | 2.8002 | 0.9375 | 0.92661 | 0.93609 | 0.83333 | 837 | 29632.4161 | 3.3602
|  | 2.7965 | 0.032292 | 1.3711 | 1.3931 | 1.3333 | 503.1667 | 21133.8278 | 2.0974
|  | 2.7949 | 0.96611 | 0.86258 | 0.96619 | 1.6667 | 582 | 25548.8047 | 1.6769
|  | 2.7909 | 2.7909 | 0 | 0 | 1.6667 | 700.1667 | 24891.2263 | 1.6746
|  | 2.7734 | 0.9625 | 0.84701 | 0.96393 | 2 | 619 | 26874.7482 | 1.3867
|  | 2.7512 | 0.023322 | 1.6688 | 1.059 | 0.33333 | 461.3333 | 23956.0211 | 8.2535
|  | 2.7468 | 1.3753 | 0 | 1.3716 | 1.1667 | 267.5 | 13230.3333 | 2.3544
|  | 2.7454 | 1.372 | 0 | 1.3734 | 2.3333 | 700.5 | 29222.2351 | 1.1766
|  | 2.7313 | 0.060356 | 1.3187 | 1.3523 | 1 | 411.3333 | 21523.4161 | 2.7313
|  | 2.7261 | 1.3647 | 0 | 1.3614 | 2.1667 | 825.5 | 19367.5 | 1.2582
|  | 2.7261 | 1.3505 | 0.00089757 | 1.3747 | 1.8333 | 687.8333 | 30888.2042 | 1.4869
|  | 2.7246 | 1.3633 | 0.00089757 | 1.3604 | 0.83333 | 726 | 25304.0827 | 3.2695
|  | 2.723 | 1.3656 | 0.0039084 | 1.3535 | 0.66667 | 497.5 | 22759.0685 | 4.0845
|  | 2.7135 | 2.7135 | 0 | 0 | 1.8333 | 676 | 23813.6193 | 1.4801
|  | 2.6978 | 0.02596 | 1.3279 | 1.3439 | 0.66667 | 441.3333 | 20632.3333 | 4.0467
|  | 2.6972 | 1.3427 | 0.01085 | 1.3436 | 0.66667 | 651.8333 | 27547.4105 | 4.0458
|  | 2.694 | 1.3523 | 0 | 1.3417 | 1.1667 | 559 | 27629.745 | 2.3091
|  | 2.6827 | 1.3435 | 0 | 1.3393 | 2.3333 | 931.5 | 29680.0498 | 1.1497
|  | 2.6758 | 1.0329 | 0.0044862 | 1.6385 | 0.5 | 592.3333 | 29595.3265 | 5.3517
|  | 2.6721 | 1.3377 | 0 | 1.3345 | 1.6667 | 805.1667 | 27940.9117 | 1.6033
|  | 2.6681 | 1.3341 | 0.0025949 | 1.3315 | 1.1667 | 761 | 26414.6667 | 2.287
|  | 2.6537 | 1.3288 | 0 | 1.325 | 0.83333 | 646.6667 | 22892 | 3.1845
|  | 2.6499 | 1.3358 | 0 | 1.3141 | 1.5 | 549.1667 | 26962.0784 | 1.7666
|  | 2.6365 | 0.52017 | 0.76069 | 1.3556 | 0.5 | 664.8333 | 28275.4197 | 5.2729
|  | 2.6348 | 0.0056383 | 1.2946 | 1.3345 | 0.33333 | 334.6667 | 22027.3284 | 7.9043
|  | 2.6205 | 2.6205 | 0 | 0 | 1 | 702.5 | 25641.679 | 2.6205
|  | 2.609 | 0.87189 | 0.86606 | 0.87105 | 0.33333 | 680.1667 | 28567.4204 | 7.827
|  | 2.604 | 1.3022 | 0.0026059 | 1.2992 | 0.5 | 593.1667 | 27681.1512 | 5.208
|  | 2.5916 | 2.5916 | 0 | 0 | 1 | 718.5 | 20937.5957 | 2.5916
|  | 2.5766 | 1.2942 | 0 | 1.2824 | 2 | 411.1667 | 19380.0784 | 1.2883
|  | 2.576 | 2.576 | 0 | 0 | 1 | 702.3333 | 25635.4527 | 2.576
|  | 2.5669 | 0.079695 | 1.2095 | 1.2777 | 1.6667 | 584.8333 | 25666.7457 | 1.5401
|  | 2.5646 | 1.2833 | 0.00089757 | 1.2805 | 2 | 850.5 | 27930.1611 | 1.2823
|  | 2.5641 | 0.01243 | 1.2639 | 1.2878 | 0.66667 | 448.5 | 21982.663 | 3.8461
|  | 2.5378 | 0.045542 | 1.1947 | 1.2976 | 1.5 | 205.6667 | 9573.393 | 1.6918
|  | 2.5343 | 1.2675 | 0.00089757 | 1.2658 | 1.1667 | 630 | 27737.6654 | 2.1722
|  | 2.5302 | 0.86727 | 0.80209 | 0.8608 | 1.6667 | 456.3333 | 20033.3863 | 1.5181
|  | 2.5291 | 2.5291 | 0 | 0 | 1.1667 | 768 | 31843.353 | 2.1678
|  | 2.5211 | 0.57705 | 0.0017727 | 1.9423 | 0.66667 | 537.8333 | 25405.9901 | 3.7816
|  | 2.5107 | 1.2543 | 0.0006514 | 1.2557 | 1 | 653.5 | 23633.1667 | 2.5107
|  | 2.4848 | 1.2445 | 0 | 1.2403 | 1.8333 | 537.6667 | 25594.5 | 1.3553
|  | 2.4821 | 1.0304 | 0 | 1.4516 | 1.6667 | 565.8333 | 25371.6667 | 1.4892
|  | 2.4723 | 2.4723 | 0 | 0 | 1 | 579.1667 | 21139.7263 | 2.4723
|  | 2.4618 | 1.2372 | 0 | 1.2246 | 2.3333 | 742.1667 | 32496.4117 | 1.055
|  | 2.4276 | 1.2133 | 0.0017946 | 1.2125 | 0.83333 | 373.8333 | 18458.3321 | 2.9132
|  | 2.4233 | 2.4233 | 0 | 0 | 1.6667 | 641.8333 | 22400.393 | 1.454
|  | 2.4199 | 0.072092 | 1.1544 | 1.1935 | 1.1667 | 1196.6667 | 26857.0771 | 2.0742
|  | 2.4098 | 0 | 1.2023 | 1.2076 | 0.33333 | 348 | 22945.2482 | 7.2295
|  | 2.4083 | 0.031951 | 1.1802 | 1.1962 | 0.66667 | 556 | 25993 | 3.6124
|  | 2.4065 | 0.83296 | 0.74676 | 0.82673 | 1.8333 | 736.8333 | 24786.0784 | 1.3126
|  | 2.395 | 1.1975 | 0 | 1.1975 | 1.8333 | 535.3333 | 24041.3333 | 1.3063
|  | 2.3756 | 1.185 | 0.0046455 | 1.186 | 1.3333 | 525.5 | 25842.6611 | 1.7817
|  | 2.3653 | 2.3653 | 0 | 0 | 0 | 810.3333 | 30272.4326 | #DIV/0!
|  | 2.3637 | 1.1784 | 0 | 1.1853 | 2.1667 | 539.5 | 23371.9018 | 1.0909
|  | 2.3603 | 0.018645 | 1.1648 | 1.1769 | 0.66667 | 395.3333 | 19492.7469 | 3.5405
|  | 2.3528 | 1.1801 | 0 | 1.1727 | 1.1667 | 531.6667 | 20781.1568 | 2.0166
|  | 2.3521 | 2.3521 | 0 | 0 | 0 | 710.8333 | 26555.3116 | #DIV/0!
|  | 2.3496 | 0.099952 | 0.0035903 | 2.2461 | 0.33333 | 438.3333 | 22775.8297 | 7.0488
|  | 2.3343 | 1.043 | 0.24891 | 1.0424 | 1 | 511.8333 | 27210.0685 | 2.3343
|  | 2.3329 | 1.1655 | 0.0013669 | 1.166 | 0.66667 | 618 | 19777.245 | 3.4993
|  | 2.3207 | 1.1604 | 0.0043577 | 1.156 | 0.66667 | 428.8333 | 19612.4889 | 3.4811
|  | 2.3198 | 2.3198 | 0 | 0 | 0.83333 | 665.6667 | 21038.8457 | 2.7838
|  | 2.3173 | 1.1623 | 0 | 1.1549 | 1.3333 | 565.8333 | 28043 | 1.738
|  | 2.316 | 2.316 | 0 | 0 | 1.1667 | 419.1667 | 20236.1193 | 1.9852
|  | 2.3086 | 1.1599 | 0 | 1.1486 | 0.66667 | 659 | 24550.1568 | 3.4628
|  | 2.3056 | 1.1565 | 0.0036948 | 1.1454 | 1.1667 | 445.6667 | 22028.6667 | 1.9762
|  | 2.2916 | 1.1474 | 0 | 1.1441 | 1.3333 | 505.3333 | 19392.1667 | 1.7187
|  | 2.2903 | 0.78447 | 0.72506 | 0.7808 | 2 | 511 | 22185.7482 | 1.1452
|  | 2.2875 | 0.78837 | 0.71481 | 0.78431 | 1.6667 | 634.6667 | 27859.8122 | 1.3725
|  | 2.2832 | 1.1465 | 0 | 1.1367 | 2.1667 | 483.1667 | 11335.8333 | 1.0538
|  | 2.282 | 2.282 | 0 | 0 | 1 | 597.5 | 20617.072 | 2.282
|  | 2.2812 | 1.1427 | 0 | 1.1385 | 1.6667 | 478 | 23048.1667 | 1.3687
|  | 2.2757 | 2.2757 | 0 | 0 | 1.6667 | 656.6667 | 23077.0123 | 1.3654
|  | 2.2507 | 1.1295 | 0.00044878 | 1.1208 | 1 | 693.3333 | 22420.5043 | 2.2507
|  | 2.2418 | 1.1207 | 0 | 1.1211 | 1.1667 | 137.5 | 6796.0784 | 1.9215
|  | 2.2341 | 1.1206 | 0 | 1.1135 | 0.66667 | 1005.6667 | 28427.5486 | 3.3512
|  | 2.2322 | 0.75038 | 0.73526 | 0.7466 | 0.83333 | 743.3333 | 26314 | 2.6787
|  | 2.2298 | 2.2298 | 0 | 0 | 0.16667 | 494.3333 | 22239.9053 | 13.3787
|  | 2.2297 | 1.1146 | 0 | 1.1151 | 0.83333 | 610.5 | 21601.0784 | 2.6756
|  | 2.2151 | 1.1077 | 0.00044878 | 1.1069 | 0.33333 | 364.5 | 18403.8278 | 6.6452
|  | 2.1863 | 2.1863 | 0 | 0 | 0.83333 | 658.6667 | 23439.436 | 2.6235
|  | 2.1817 | 1.0932 | 0.00044878 | 1.088 | 1 | 607.5 | 21390.2494 | 2.1817
|  | 2.1806 | 0.72829 | 0.71453 | 0.73783 | 0.16667 | 503.5 | 22153.4523 | 13.0839
|  | 2.1732 | 1.0882 | 0.00044878 | 1.0846 | 0.83333 | 472 | 18220.7494 | 2.6078
|  | 2.1376 | 2.1376 | 0 | 0 | 2.6667 | 354.3333 | 15126.9053 | 0.80162
|  | 2.1292 | 1.0665 | 0 | 1.0627 | 0.16667 | 577.6667 | 23684.8831 | 12.7751
|  | 2.1257 | 0.7112 | 0.7033 | 0.7112 | 1.6667 | 271.6667 | 10051.6667 | 1.2754
|  | 2.1246 | 1.0602 | 0.0017951 | 1.0626 | 0.5 | 621.1667 | 20923.9932 | 4.2492
|  | 2.1115 | 2.1115 | 0 | 0 | 2.1667 | 663 | 30651 | 0.97453
|  | 2.1107 | 1.0576 | 0.00044878 | 1.0527 | 1.1667 | 607.3333 | 21771.3377 | 1.8092
|  | 2.0801 | 1.0433 | 0 | 1.0367 | 1.1667 | 635 | 22789.0685 | 1.7829
|  | 2.0669 | 1.0372 | 0 | 1.0297 | 0.83333 | 484.1667 | 16945.8333 | 2.4802
|  | 2.0543 | 1.0272 | 0 | 1.0272 | 0.66667 | 549.3333 | 23758.6667 | 3.0815
|  | 2.0495 | 2.0495 | 0 | 0 | 2.6667 | 295.8333 | 12322 | 0.76858
|  | 2.0481 | 1.0233 | 0.00044878 | 1.0243 | 2.3333 | 652.1667 | 24783.1611 | 0.87775
|  | 2.0397 | 1.0149 | 0.0049231 | 1.0199 | 1.6667 | 426.6667 | 18780.7494 | 1.2238
|  | 2.0273 | 2.0273 | 0 | 0 | 0.33333 | 674.3333 | 24274.7263 | 6.082
|  | 2.0206 | 1.0035 | 0 | 1.017 | 0.83333 | 473.6667 | 16652.517 | 2.4247
|  | 2.0164 | 1.0082 | 0 | 1.0082 | 2.1667 | 476.3333 | 21192.3333 | 0.93064
|  | 2.0104 | 0 | 1.0022 | 1.0083 | 0.33333 | 258.1667 | 17033.8278 | 6.0313
|  | 2.0089 | 1.0084 | 0 | 1.0005 | 1.5 | 438.5 | 20346.4117 | 1.3393
|  | 2.0054 | 2.0054 | 0 | 0 | 1.8333 | 544 | 18897.1193 | 1.0938
|  | 2.0041 | 2.0041 | 0 | 0 | 0.33333 | 345.5 | 17911.8353 | 6.0122
|  | 2.0027 | 0 | 0.9752 | 1.0275 | 0.66667 | 391.1667 | 18958.7457 | 3.0041
|  | 2.0008 | 0.67856 | 0.64402 | 0.67824 | 0.33333 | 504.8333 | 21203.1555 | 6.0024
|  | 1.9903 | 1.9903 | 0 | 0 | 1.1667 | 511.8333 | 20026.393 | 1.706
|  | 1.9885 | 0.024593 | 0.97318 | 0.99075 | 1.3333 | 502.6667 | 20672.1667 | 1.4914
|  | 1.985 | 0.10995 | 1.7655 | 0.10959 | 0.16667 | 431.8333 | 17980.2088 | 11.9103
|  | 1.979 | 0.98854 | 0.0018901 | 0.98854 | 0.83333 | 520.8333 | 18437.5 | 2.3748
|  | 1.9646 | 1.9646 | 0 | 0 | 1.6667 | 547.5 | 19170.5597 | 1.1788
|  | 1.9619 | 0.4956 | 0.72666 | 0.73963 | 0.33333 | 743.6667 | 24920.0704 | 5.8857
|  | 1.9606 | 1.9606 | 0 | 0 | 1.1667 | 557.3333 | 20042.4527 | 1.6805
|  | 1.957 | 1.957 | 0 | 0 | 2 | 530.8333 | 19374 | 0.97848
|  | 1.9523 | 0.96963 | 0.0082681 | 0.97438 | 0.83333 | 474.8333 | 16814.3321 | 2.3427
|  | 1.9505 | 0.97784 | 0.0013463 | 0.97134 | 1.3333 | 382.1667 | 18769.2438 | 1.4629
|  | 1.94 | 1.94 | 0 | 0 | 0.16667 | 660.6667 | 22476.0987 | 11.6403
|  | 1.9357 | 0.97169 | 0 | 0.96405 | 1.1667 | 511 | 19107.245 | 1.6592
|  | 1.9289 | 0 | 1.9289 | 0 | 0 | 496 | 20844.9238 | #DIV/0!
|  | 1.9284 | 1.9284 | 0 | 0 | 0.16667 | 586.6667 | 26332.4957 | 11.5705
|  | 1.9217 | 0.00085429 | 0.9519 | 0.96896 | 0.33333 | 499.3333 | 19984.9753 | 5.7652
|  | 1.8936 | 0.10158 | 0.84588 | 0.94618 | 0.66667 | 534.1667 | 21901.4117 | 2.8405
|  | 1.8813 | 0.94066 | 0 | 0.94068 | 0.33333 | 512 | 22528.3135 | 5.644
|  | 1.8801 | 0.94036 | 0.00089757 | 0.9388 | 0.5 | 431.8333 | 20149.5771 | 3.7601
|  | 1.88 | 0.63448 | 0.61108 | 0.63448 | 1.1667 | 794.8333 | 25732 | 1.6115
|  | 1.8766 | 0.9416 | 0 | 0.93503 | 0.33333 | 415.6667 | 18289.3333 | 5.6299
|  | 1.8623 | 0.6229 | 0.6164 | 0.62305 | 0.16667 | 448 | 19709.0342 | 11.1741
|  | 1.8595 | 0.93746 | 0.00044878 | 0.92156 | 0.66667 | 446 | 20401.8962 | 2.7892
|  | 1.8554 | 0.010049 | 0.9181 | 0.92722 | 1.3333 | 341.8333 | 15049.1611 | 1.3915
|  | 1.852 | 0.9274 | 0.00044878 | 0.92418 | 0.66667 | 593.6667 | 25676.0827 | 2.778
|  | 1.8439 | 0.89784 | 0 | 0.94601 | 1.1667 | 351.5 | 17308.8584 | 1.5804
|  | 1.8373 | 1.8373 | 0 | 0 | 0.16667 | 472.1667 | 21243.679 | 11.0241
|  | 1.8371 | 0.003588 | 0.91495 | 0.91854 | 1.3333 | 450.6667 | 18928 | 1.3778
|  | 1.827 | 0.91292 | 0 | 0.91412 | 0.33333 | 569 | 20424.4516 | 5.4811
|  | 1.8215 | 1.8215 | 0 | 0 | 1 | 543.6667 | 18764.1193 | 1.8215
|  | 1.8138 | 0.90902 | 0 | 0.90478 | 1 | 512.8333 | 18543.8333 | 1.8138
|  | 1.8013 | 0.61404 | 0.57407 | 0.61319 | 0.16667 | 393.1667 | 17297.1455 | 10.8078
|  | 1.8008 | 0.60965 | 0.58152 | 0.60965 | 1.6667 | 440.5 | 19326 | 1.0805
|  | 1.7941 | 0.89703 | 0.0041433 | 0.89289 | 1 | 612 | 19788 | 1.7941
|  | 1.7914 | 1.7914 | 0 | 0 | 0.83333 | 421.8333 | 15721.1193 | 2.1496
|  | 1.7735 | 0.88767 | 0 | 0.8858 | 0.83333 | 490.8333 | 17179.1667 | 2.1282
|  | 1.7525 | 0.58686 | 0.57973 | 0.58595 | 0.16667 | 437.8333 | 19264.0716 | 10.5152
|  | 1.7449 | 0.87103 | 0.0035034 | 0.87038 | 0.66667 | 429.8333 | 15217.7195 | 2.6174
|  | 1.7413 | 0 | 1.7413 | 0 | 0 | 440.8333 | 18526.4864 | #DIV/0!
|  | 1.7394 | 0.58873 | 0.56153 | 0.58919 | 0.66667 | 452.8333 | 18988.5 | 2.6092
|  | 1.733 | 0.86622 | 0 | 0.86676 | 0.66667 | 445.3333 | 14259.6468 | 2.5995
|  | 1.7314 | 0 | 1.7314 | 0 | 0 | 483 | 20298.5851 | #DIV/0!
|  | 1.7313 | 0.071077 | 0.0047008 | 1.6555 | 0.33333 | 377.8333 | 19623.1475 | 5.194
|  | 1.7265 | 0 | 1.7265 | 0 | 0 | 425.8333 | 17896.0955 | #DIV/0!
|  | 1.7263 | 0.86314 | 0.00044878 | 0.86272 | 1 | 610.8333 | 19822.4944 | 1.7263
|  | 1.7203 | 0.8596 | 0.0017951 | 0.85888 | 0.33333 | 280.8333 | 14175.9247 | 5.1608
|  | 1.7199 | 0.51509 | 0.5896 | 0.61526 | 0.5 | 297 | 17436.0827 | 3.4399
|  | 1.718 | 0.85865 | 0.00044878 | 0.85893 | 1.6667 | 353.5 | 15452.0827 | 1.0308
|  | 1.7055 | 0.57947 | 0.54468 | 0.58137 | 0.66667 | 272.1667 | 13873.8364 | 2.5583
|  | 1.7014 | 0.85372 | 0 | 0.84771 | 2.1667 | 444.1667 | 19235.8333 | 0.78527
|  | 1.6959 | 0.84981 | 0.0036948 | 0.84242 | 1.1667 | 290.5 | 14359 | 1.4536
|  | 1.6957 | 0.043313 | 0.0022439 | 1.6502 | 0.33333 | 333.1667 | 17312.15 | 5.0871
|  | 1.6946 | 0 | 1.6946 | 0 | 0 | 434.1667 | 18246.3127 | #DIV/0!
|  | 1.6705 | 0.83565 | 0 | 0.83485 | 1.5 | 478 | 19062.4901 | 1.1137
|  | 1.6677 | 0.029954 | 0.80965 | 0.82815 | 0.66667 | 452.1667 | 21136.0771 | 2.5016
|  | 1.6659 | 1.6659 | 0 | 0 | 1 | 460.6667 | 15894.9053 | 1.6659
|  | 1.6612 | 0.83079 | 0 | 0.83041 | 0.5 | 423.5 | 16661.6182 | 3.3224
|  | 1.6533 | 0.096621 | 0.0015594 | 1.5551 | 0.33333 | 292.3333 | 15195.9061 | 4.9599
|  | 1.6503 | 1.6503 | 0 | 0 | 1.8333 | 426.5 | 14833.786 | 0.90015
|  | 1.6501 | 0.82573 | 0 | 0.82437 | 0.5 | 412.1667 | 16257.3234 | 3.3002
|  | 1.6479 | 1.6479 | 0 | 0 | 1.1667 | 499.3333 | 12996.8107 | 1.4125
|  | 1.6457 | 0 | 1.6457 | 0 | 0 | 379.8333 | 15962.8969 | #DIV/0!
|  | 1.6449 | 0.82245 | 0 | 0.82245 | 1 | 556 | 17977.3333 | 1.6449
|  | 1.6437 | 0.0015957 | 0 | 1.6421 | 0 | 420 | 18673.9537 | #DIV/0!
|  | 1.6285 | 0.81471 | 0 | 0.81381 | 0.66667 | 534.3333 | 23110.3234 | 2.4428
|  | 1.6263 | 0.54485 | 0.53656 | 0.54485 | 1 | 393 | 12707 | 1.6263
|  | 1.6242 | 0.54892 | 0.52593 | 0.54939 | 1.6667 | 364.1667 | 15974.7494 | 0.97454
|  | 1.6229 | 0.14993 | 0.0038033 | 1.4691 | 0.33333 | 269 | 13973.821 | 4.8686
|  | 1.6151 | 0.80999 | 0 | 0.80507 | 0.5 | 499.6667 | 16823.9117 | 3.2301
|  | 1.5868 | 1.5868 | 0 | 0 | 2.5 | 330.3333 | 14968.823 | 0.63473
|  | 1.5809 | 1.5809 | 0 | 0 | 1 | 414 | 15111 | 1.5809
|  | 1.5746 | 0.7873 | 0 | 0.7873 | 1.6667 | 547 | 21439.3333 | 0.94476
|  | 1.5741 | 0 | 0.78565 | 0.78847 | 0.33333 | 102.3333 | 6748 | 4.7224
|  | 1.5704 | 0.78708 | 0.0024249 | 0.7809 | 0.33333 | 277 | 12973.9701 | 4.7112
|  | 1.5653 | 0.52573 | 0.51388 | 0.52573 | 2 | 150.8333 | 5067.6667 | 0.78267
|  | 1.5607 | 1.5607 | 0 | 0 | 0.66667 | 526.3333 | 18553.9527 | 2.341
|  | 1.5596 | 0.79619 | 0 | 0.76337 | 1.8333 | 427.3333 | 17884.6667 | 0.85067
|  | 1.5573 | 0 | 0.75664 | 0.80062 | 0.66667 | 247.8333 | 12018.1667 | 2.3359
|  | 1.5568 | 0.051087 | 0.0086716 | 1.4971 | 0.33333 | 275.3333 | 14306.4789 | 4.6704
|  | 1.5555 | 0.7799 | 0 | 0.77565 | 1.3333 | 338.6667 | 8424.3333 | 1.1667
|  | 1.5485 | 0.77306 | 0 | 0.77544 | 0.83333 | 411.8333 | 14580.4117 | 1.8582
|  | 1.5475 | 0.017972 | 0.76127 | 0.76824 | 0.66667 | 280.6667 | 13119.2395 | 2.3212
|  | 1.5356 | 1.5356 | 0 | 0 | 1.1667 | 367.3333 | 13608 | 1.3162
|  | 1.534 | 0.76702 | 0 | 0.76702 | 1.5 | 489 | 11790.3333 | 1.0227
|  | 1.5299 | 0.76672 | 0 | 0.76318 | 2 | 521 | 21317.1667 | 0.76495
|  | 1.5271 | 1.5271 | 0 | 0 | 0 | 489.8333 | 18299.1936 | #DIV/0!
|  | 1.5271 | 0.7631 | 0.003332 | 0.76062 | 0.16667 | 286.3333 | 12883.7097 | 9.1623
|  | 1.5056 | 0.75237 | 0.00089757 | 0.75237 | 1.3333 | 432.3333 | 17582.0087 | 1.1292
|  | 1.5039 | 1.5039 | 0 | 0 | 1.6667 | 415.5 | 14501.286 | 0.90232
|  | 1.4886 | 1.4886 | 0 | 0 | 1 | 349.5 | 12757.179 | 1.4886
|  | 1.4868 | 0.74179 | 0.0013463 | 0.7437 | 0.5 | 152.8333 | 8396.3321 | 2.9737
|  | 1.4855 | 0 | 1.4855 | 0 | 0 | 432.5 | 18176.2692 | #DIV/0!
|  | 1.4843 | 0 | 1.0156 | 0.46871 | 0 | 423 | 18122.4694 | #DIV/0!
|  | 1.4716 | 0.49159 | 0.48795 | 0.49207 | 1.5 | 394.6667 | 14954.5784 | 0.98107
|  | 1.4675 | 0.003588 | 0.73196 | 0.73196 | 1.3333 | 252 | 10584 | 1.1006
|  | 1.4664 | 1.4664 | 0 | 0 | 0.5 | 332.6667 | 12589.5267 | 2.9327
|  | 1.4615 | 0.014053 | 0.72022 | 0.72725 | 1.3333 | 346.6667 | 14256.6667 | 1.0961
|  | 1.4588 | 0.7294 | 0 | 0.7294 | 1.8333 | 445 | 17962.6667 | 0.79571
|  | 1.4574 | 0.7291 | 0.00089757 | 0.72742 | 0.33333 | 280.5 | 14161.4204 | 4.3722
|  | 1.457 | 0.50252 | 0.4661 | 0.48843 | 1.5 | 132.1667 | 5008.745 | 0.97136
|  | 1.4511 | 0.0050297 | 0.72137 | 0.72475 | 1.1667 | 706.1667 | 15845.2494 | 1.2438
|  | 1.4483 | 0.72392 | 0 | 0.72439 | 0.83333 | 393.5 | 13931.4117 | 1.738
|  | 1.4473 | 1.4473 | 0 | 0 | 0 | 406.5 | 15186.027 | #DIV/0!
|  | 1.446 | 0 | 1.446 | 0 | 0 | 325.6667 | 13686.4856 | #DIV/0!
|  | 1.4365 | 1.4365 | 0 | 0 | 0.33333 | 430 | 17181.113 | 4.3095
|  | 1.4358 | 0.49815 | 0.43876 | 0.49893 | 1.6667 | 509.1667 | 19432.9105 | 0.8615
|  | 1.4338 | 1.4338 | 0 | 0 | 0 | 468.3333 | 17495.9966 | #DIV/0!
|  | 1.428 | 0.014352 | 0.69967 | 0.71402 | 1.3333 | 341.3333 | 14336 | 1.071
|  | 1.4273 | 0.714 | 0 | 0.71327 | 0.33333 | 243 | 12269.4901 | 4.2818
|  | 1.4224 | 0.48963 | 0.45057 | 0.4822 | 1.6667 | 341.5 | 12641.5827 | 0.85344
|  | 1.4096 | 0.70458 | 0 | 0.705 | 2.1667 | 468.8333 | 18753.1667 | 0.65057
|  | 1.4094 | 0.042191 | 0.66453 | 0.70267 | 1.1667 | 511.3333 | 11478.0871 | 1.2081
|  | 1.4089 | 1.4089 | 0 | 0 | 0.16667 | 456.1667 | 17226.72 | 8.4533
|  | 1.3969 | 0.016915 | 0.6766 | 0.70338 | 0.33333 | 128 | 8448 | 4.1907
|  | 1.3964 | 1.3964 | 0 | 0 | 0.33333 | 298.1667 | 15169.3457 | 4.1891
|  | 1.3927 | 0.6975 | 0 | 0.69518 | 1.5 | 382.5 | 9222.5 | 0.92845
|  | 1.3886 | 0.69545 | 0.0017951 | 0.69131 | 2 | 390.8333 | 16968.3364 | 0.69428
|  | 1.3845 | 0 | 1.3845 | 0 | 0 | 342.6667 | 14400.9285 | #DIV/0!
|  | 1.3836 | 0 | 1.3836 | 0 | 0 | 269 | 11305.0091 | #DIV/0!
|  | 1.3767 | 0.69023 | 0 | 0.68648 | 0.16667 | 315.6667 | 13889.5685 | 8.2603
|  | 1.3707 | 0.010059 | 0.6761 | 0.68451 | 1.1667 | 512.5 | 11501.5827 | 1.1749
|  | 1.366 | 0.68235 | 0.0014099 | 0.68224 | 0.5 | 308.8333 | 15093.0827 | 2.732
|  | 1.3656 | 1.3656 | 0 | 0 | 0.33333 | 334.8333 | 14727.1317 | 4.0969
|  | 1.3643 | 0 | 1.3643 | 0 | 0 | 386.3333 | 16236.0663 | #DIV/0!
|  | 1.3546 | 0.00039893 | 0.0022439 | 1.352 | 0 | 349.6667 | 15547.3606 | #DIV/0!
|  | 1.3543 | 1.3543 | 0 | 0 | 1.1667 | 246.5 | 11898.786 | 1.1608
|  | 1.3506 | 0.46191 | 0.42676 | 0.4619 | 0.83333 | 312.8333 | 13030.2438 | 1.6207
|  | 1.3501 | 0.00041647 | 0.72463 | 0.6251 | 0.16667 | 266.3333 | 10400.5592 | 8.1009
|  | 1.3475 | 0.6761 | 0 | 0.67141 | 1 | 376.8333 | 14978.745 | 1.3475
|  | 1.3392 | 1.3392 | 0 | 0 | 1 | 480.8333 | 17009.7263 | 1.3392
|  | 1.3377 | 0 | 0.66532 | 0.67237 | 0.33333 | 173 | 11418 | 4.0131
|  | 1.3375 | 1.3375 | 0 | 0 | 2.1667 | 299.3333 | 11422.2263 | 0.61729
|  | 1.3363 | 1.3363 | 0 | 0 | 1.1667 | 280.3333 | 13532.4527 | 1.1454
|  | 1.3349 | 0.00039511 | 0.64408 | 0.69042 | 0.16667 | 334.6667 | 12385.9944 | 8.0094
|  | 1.3292 | 0.046943 | 0.63754 | 0.64475 | 1 | 236.5 | 12372.4944 | 1.3292
|  | 1.3248 | 0 | 1.3248 | 0 | 0 | 270.1667 | 11354.0395 | #DIV/0!
|  | 1.3227 | 0.66133 | 0 | 0.66133 | 2.1667 | 264.3333 | 11447.6667 | 0.61046
|  | 1.3225 | 0.19609 | 0.0056181 | 1.1208 | 0.5 | 279.5 | 13766.2979 | 2.645
|  | 1.3155 | 1.3155 | 0 | 0 | 1.6667 | 118.5 | 5196.286 | 0.7893
|  | 1.3154 | 0.036649 | 0.006496 | 1.2722 | 0.33333 | 193.5 | 10046.1586 | 3.9461
|  | 1.3106 | 0.014352 | 0.6463 | 0.64991 | 1.3333 | 324.3333 | 13622.4161 | 0.98292
|  | 1.3091 | 0.00039893 | 0.0017951 | 1.3069 | 0 | 348.8333 | 15509.8947 | #DIV/0!
|  | 1.3051 | 0.65343 | 0 | 0.65163 | 0.66667 | 291 | 10556.9703 | 1.9576
|  | 1.3019 | 1.3019 | 0 | 0 | 1 | 370.5 | 13523.679 | 1.3019
|  | 1.2987 | 0.00039893 | 0 | 1.2983 | 0 | 166 | 7380.878 | #DIV/0!
|  | 1.2961 | 0.43615 | 0.42578 | 0.43421 | 0.66667 | 143.1667 | 7011.3091 | 1.9442
|  | 1.2741 | 0.63548 | 0.00089757 | 0.63771 | 1.6667 | 434.8333 | 17828.4988 | 0.76445
|  | 1.2729 | 0.63619 | 0 | 0.63667 | 0.33333 | 304.8333 | 13412.745 | 3.8186
|  | 1.2721 | 0.63508 | 0.0018901 | 0.63508 | 0.83333 | 340.8333 | 12065.5 | 1.5265
|  | 1.269 | 1.269 | 0 | 0 | 0 | 443.5 | 16568.273 | #DIV/0!
|  | 1.2648 | 0.0070266 | 0.62536 | 0.63239 | 1.3333 | 354.6667 | 14585.6667 | 0.94859
|  | 1.2643 | 0.42053 | 0.42185 | 0.42196 | 0.16667 | 327.3333 | 14401.9148 | 7.586
|  | 1.2612 | 0.00039893 | 0.00044878 | 1.2603 | 0 | 320.6667 | 14258.5378 | #DIV/0!
|  | 1.2596 | 0.010059 | 0.62228 | 0.62731 | 1.1667 | 638.5 | 14321.8333 | 1.0797
|  | 1.2589 | 0.63079 | 0 | 0.62806 | 0.33333 | 334.5 | 14209.5586 | 3.7766
|  | 1.2584 | 0.62771 | 0.0031182 | 0.6276 | 0.33333 | 237 | 11966.6667 | 3.7753
|  | 1.2572 | 0 | 0.62368 | 0.63349 | 1.1667 | 318.8333 | 7158.3234 | 1.0776
|  | 1.2521 | 0.4695 | 0.31169 | 0.47092 | 1.8333 | 398.5 | 17895.5728 | 0.68297
|  | 1.2476 | 0 | 1.2476 | 0 | 0 | 298.5 | 12544.7777 | #DIV/0!
|  | 1.2322 | 1.2322 | 0 | 0 | 1 | 272.3333 | 12025.786 | 1.2322
|  | 1.2296 | 0.41348 | 0.40361 | 0.41254 | 0.16667 | 299 | 13156 | 7.3778
|  | 1.2291 | 1.2291 | 0 | 0 | 0 | 385.3333 | 14395.2826 | #DIV/0!
|  | 1.2251 | 0.61221 | 0 | 0.6129 | 1 | 353.6667 | 12382.4117 | 1.2251
|  | 1.2251 | 1.2251 | 0 | 0 | 2.1667 | 239.6667 | 5738.2263 | 0.56543
|  | 1.2243 | 0.024433 | 0 | 1.1999 | 0.33333 | 263.8333 | 13718.0784 | 3.673
|  | 1.2124 | 0 | 0.77505 | 0.43737 | 0 | 315.3333 | 13520.2642 | #DIV/0!
|  | 1.209 | 0.60424 | 0 | 0.60473 | 0.33333 | 268 | 11792.1568 | 3.6269
|  | 1.2072 | 0 | 0 | 1.2072 | 0 | 262 | 11651.2085 | #DIV/0!
|  | 1.207 | 0.025373 | 0.57319 | 0.60843 | 0.33333 | 208.6667 | 13778 | 3.621
|  | 1.2069 | 1.2069 | 0 | 0 | 0.5 | 279 | 10173.5123 | 2.4139
|  | 1.2068 | 0.021795 | 0.58389 | 0.60116 | 1.1667 | 624.6667 | 14020.9944 | 1.0344
|  | 1.2053 | 0.44184 | 0.32529 | 0.4382 | 0.83333 | 197.5 | 10266.4988 | 1.4464
|  | 1.2031 | 0.60201 | 0.00087565 | 0.60026 | 0.16667 | 338 | 13858 | 7.2189
|  | 1.1984 | 1.1984 | 0 | 0 | 1.3333 | 231.3333 | 11274.1667 | 0.89877
|  | 1.1933 | 0 | 1.1933 | 0 | 0 | 301.8333 | 12684.8646 | #DIV/0!
|  | 1.1828 | 1.1828 | 0 | 0 | 0.16667 | 317 | 14259.9053 | 7.0966
|  | 1.1808 | 0.59042 | 0 | 0.59042 | 1 | 128 | 4138.6667 | 1.1808
|  | 1.1778 | 1.1778 | 0 | 0 | 1.1667 | 287.8333 | 10474.465 | 1.0096
|  | 1.1747 | 0.58733 | 0 | 0.58733 | 2.3333 | 37.3333 | 1333.3333 | 0.50342
|  | 1.1742 | 1.1742 | 0 | 0 | 0.16667 | 420.1667 | 14295.181 | 7.0453
|  | 1.1644 | 0 | 1.1644 | 0 | 0.33333 | 228.6667 | 9831.6927 | 3.4933
|  | 1.159 | 0.5795 | 0 | 0.5795 | 0.66667 | 336 | 9128 | 1.7385
|  | 1.153 | 0.57745 | 0 | 0.57558 | 0.83333 | 370.8333 | 12979.1667 | 1.3836
|  | 1.1468 | 0.57379 | 0 | 0.57305 | 0.5 | 366.3333 | 12336.8234 | 2.2937
|  | 1.1455 | 0.0014096 | 0.50226 | 0.64184 | 0.33333 | 112 | 7384.4161 | 3.4365
|  | 1.1422 | 0 | 1.1422 | 0 | 0 | 323.8333 | 13609.4378 | #DIV/0!
|  | 1.1417 | 1.1417 | 0 | 0 | 0 | 346.6667 | 12950.7733 | #DIV/0!
|  | 1.1395 | 1.1395 | 0 | 0 | 1.6667 | 187.3333 | 8473 | 0.68369
|  | 1.1378 | 0.018168 | 0.0017951 | 1.1179 | 0.33333 | 200.5 | 10409.3806 | 3.4135
|  | 1.1349 | 0.40696 | 0.32399 | 0.4039 | 1.6667 | 370.3333 | 13703.9117 | 0.68092
|  | 1.1347 | 0.11482 | 0.45254 | 0.56738 | 1.3333 | 251 | 10542.4161 | 0.85106
|  | 1.1344 | 1.1344 | 0 | 0 | 0.83333 | 330 | 11639.5 | 1.3612
|  | 1.1321 | 1.1321 | 0 | 0 | 1.6667 | 301.1667 | 10927.7263 | 0.67928
|  | 1.1318 | 1.1318 | 0 | 0 | 0 | 362.5 | 13542.275 | #DIV/0!
|  | 1.1246 | 0 | 1.1246 | 0 | 0 | 296.3333 | 12453.7213 | #DIV/0!
|  | 1.1236 | 1.1236 | 0 | 0 | 1.3333 | 267.3333 | 9597.3333 | 0.84273
|  | 1.1217 | 0 | 0.5598 | 0.5619 | 0.66667 | 186.3333 | 9035.4161 | 1.6825
|  | 1.121 | 0.55993 | 0 | 0.56107 | 0.16667 | 263.8333 | 11608.3434 | 6.726
|  | 1.1183 | 0.0027925 | 0.53854 | 0.57698 | 0 | 270.8333 | 11714.5422 | #DIV/0!
|  | 1.1179 | 1.1179 | 0 | 0 | 0.66667 | 347 | 12358.8457 | 1.6768
|  | 1.1176 | 1.1176 | 0 | 0 | 1.1667 | 345.6667 | 11349.5 | 0.95795
|  | 1.1139 | 0.020439 | 0.54163 | 0.55185 | 1.3333 | 260 | 10367.5 | 0.83544
|  | 1.1102 | 1.1102 | 0 | 0 | 0 | 330.1667 | 12334.3663 | #DIV/0!
|  | 1.1056 | 0.55365 | 0.00044878 | 0.55152 | 1.8333 | 151.1667 | 3749.5043 | 0.60306
|  | 1.1044 | 0.11252 | 0.47638 | 0.51549 | 0.83333 | 375.5 | 15172.0784 | 1.3253
|  | 1.1022 | 1.1022 | 0 | 0 | 0.83333 | 426.1667 | 11119.5 | 1.3226
|  | 1.0934 | 0.54665 | 0 | 0.54672 | 0.83333 | 313.6667 | 11105.638 | 1.312
|  | 1.0906 | 1.0906 | 0 | 0 | 1 | 253.1667 | 9240.7263 | 1.0906
|  | 1.0842 | 0.54349 | 0 | 0.5407 | 0.83333 | 212.5 | 11092.5 | 1.301
|  | 1.0823 | 1.0823 | 0 | 0 | 0 | 286 | 10684.388 | #DIV/0!
|  | 1.0805 | 0.54419 | 0 | 0.53633 | 0.33333 | 255.5 | 8305.745 | 3.2415
|  | 1.0778 | 0.5368 | 0.0018901 | 0.53916 | 0.83333 | 190.1667 | 6733.4117 | 1.2934
|  | 1.0747 | 0.011736 | 0.52811 | 0.53482 | 1.1667 | 596.1667 | 13371.1667 | 0.92115
|  | 1.0746 | 0.36273 | 0.35285 | 0.35898 | 0.16667 | 233.8333 | 10288.4161 | 6.4473
|  | 1.0714 | 1.0714 | 0 | 0 | 0.16667 | 207.5 | 9334.9527 | 6.4282
|  | 1.0709 | 0.49436 | 0.081678 | 0.49489 | 0.16667 | 335.8333 | 13805.8189 | 6.4256
|  | 1.0655 | 0.53477 | 0 | 0.53076 | 1 | 311.3333 | 11775.1667 | 1.0655
|  | 1.0582 | 0.39796 | 0.27764 | 0.38261 | 1.8333 | 271.5 | 12097.9161 | 0.5772
|  | 1.0537 | 0.52523 | 0.00089757 | 0.52757 | 0.16667 | 187.3333 | 8428.4789 | 6.3222
|  | 1.0535 | 0.5277 | 0 | 0.52584 | 0.5 | 350.5 | 10164.5 | 2.1071
|  | 1.0529 | 0.52879 | 0 | 0.52416 | 0.5 | 230.6667 | 9882.8234 | 2.1059
|  | 1.0523 | 0 | 0.00044878 | 1.0519 | 0 | 266.1667 | 11836.0939 | #DIV/0!
|  | 1.0506 | 1.0506 | 0 | 0 | 0.5 | 81.8333 | 3467.9053 | 2.1012
|  | 1.0473 | 0.52363 | 0 | 0.52363 | 1.8333 | 22 | 934 | 0.57123
|  | 1.0429 | 0.36598 | 0.31126 | 0.36561 | 0.33333 | 319.5 | 13420.2351 | 3.1286
|  | 1.0428 | 0 | 0 | 1.0428 | 0 | 293.1667 | 13037.1983 | #DIV/0!
|  | 1.037 | 0 | 0.16605 | 0.87094 | 0 | 277.1667 | 12214.4628 | #DIV/0!
|  | 1.0353 | 0.51761 | 0.00096108 | 0.51675 | 0.66667 | 212.8333 | 8972.1568 | 1.553
|  | 1.0345 | 0.021101 | 0.0013463 | 1.0121 | 0.33333 | 217 | 11275.2482 | 3.1035
|  | 1.0345 | 1.0345 | 0 | 0 | 0.16667 | 515.5 | 10836.4053 | 6.207
|  | 1.0313 | 0.34394 | 0.34298 | 0.34442 | 0.16667 | 253.1667 | 11139.1611 | 6.188
|  | 1.0311 | 0.44026 | 0 | 0.59082 | 0.33333 | 277.8333 | 12191.8015 | 3.0932
|  | 1.0252 | 0 | 0.52481 | 0.5004 | 0.33333 | 102.8333 | 6783.0043 | 3.0757
|  | 1.0247 | 0.51283 | 0 | 0.5119 | 0.33333 | 224.3333 | 9758.5 | 3.0742
|  | 1.0239 | 0.34855 | 0.32895 | 0.34637 | 0.66667 | 188 | 9588 | 1.5358
|  | 1.0223 | 0 | 1.0223 | 0 | 0 | 269.1667 | 11312.0134 | #DIV/0!
|  | 1.0158 | 1.0158 | 0 | 0 | 1 | 317.3333 | 11582.9527 | 1.0158
|  | 1.0156 | 0 | 1.0156 | 0 | 0 | 263 | 11052.8527 | #DIV/0!
|  | 1.0139 | 0.01999 | 0.0024569 | 0.99143 | 0.33333 | 209.5 | 10883.9932 | 3.0416
|  | 1.0097 | 0.5067 | 0.00044878 | 0.50258 | 1.1667 | 299.1667 | 11514.6314 | 0.86548
|  | 1.0085 | 1.0085 | 0 | 0 | 0 | 21.3333 | 796.9707 | #DIV/0!
|  | 1.0048 | 0 | 0.95591 | 0.048913 | 0 | 249.5 | 10518.0904 | #DIV/0!
|  | 1.0036 | 0.33584 | 0.33189 | 0.33584 | 1.6667 | 348.3333 | 12888.3333 | 0.60215
|  | 1.0032 | 0.33642 | 0.32937 | 0.33737 | 0.16667 | 246.5 | 10846.1568 | 6.019
|  | 1.0016 | 1.0016 | 0 | 0 | 1 | 195.5 | 7303.7387 | 1.0016
|  | 0.99351 | 0.042565 | 0.46808 | 0.48287 | 1.3333 | 202.6667 | 8318.1568 | 0.74513
|  | 0.99304 | 0.3348 | 0.32345 | 0.3348 | 0.83333 | 205.1667 | 10432.8333 | 1.1917
|  | 0.98957 | 0 | 0.98957 | 0 | 0 | 222 | 9329.7844 | #DIV/0!
|  | 0.9876 | 0.33141 | 0.32476 | 0.33142 | 0.33333 | 169.5 | 6896.6611 | 2.9628
|  | 0.98537 | 0.98537 | 0 | 0 | 0 | 291.3333 | 10883.6306 | #DIV/0!
|  | 0.9822 | 0.16881 | 0.39618 | 0.41721 | 0.33333 | 188.8333 | 9084.8395 | 2.9466
|  | 0.98124 | 0.98124 | 0 | 0 | 1 | 267.3333 | 9247.7817 | 0.98124
|  | 0.97798 | 0.97798 | 0 | 0 | 0.5 | 255.6667 | 10207.893 | 1.956
|  | 0.97736 | 0.49054 | 0 | 0.48682 | 0.33333 | 179.3333 | 7801 | 2.9321
|  | 0.9746 | 0.9746 | 0 | 0 | 0 | 291.6667 | 10896.0833 | #DIV/0!
|  | 0.97161 | 0 | 0.97161 | 0 | 0 | 197.1667 | 8286.1374 | #DIV/0!
|  | 0.96444 | 0 | 0.00089757 | 0.96354 | 0 | 263.3333 | 11709.6875 | #DIV/0!
|  | 0.96185 | 0.96185 | 0 | 0 | 0.16667 | 242.8333 | 10679.1317 | 5.7711
|  | 0.96052 | 0.96052 | 0 | 0 | 0.66667 | 333.3333 | 11916.6667 | 1.4408
|  | 0.9595 | 0.4799 | 0.00044878 | 0.47916 | 0.5 | 262.6667 | 9628.7494 | 1.919
|  | 0.95794 | 0 | 0.47535 | 0.48258 | 0.33333 | 57.6667 | 3752.9124 | 2.8738
|  | 0.95704 | 0.95704 | 0 | 0 | 0 | 280.1667 | 10466.4663 | #DIV/0!
|  | 0.95665 | 0.47885 | 0 | 0.4778 | 1.5 | 282.6667 | 10086.245 | 0.63777
|  | 0.95619 | 0 | 0.82037 | 0.13582 | 0 | 234 | 9911.497 | #DIV/0!
|  | 0.95538 | 0.47769 | 0 | 0.47769 | 0.16667 | 6 | 222 | 5.7323
|  | 0.95314 | 0.95314 | 0 | 0 | 0.83333 | 329 | 12828.537 | 1.1438
|  | 0.95212 | 0 | 0.00044878 | 0.95167 | 0 | 293.1667 | 13036.791 | #DIV/0!
|  | 0.95171 | 0.47565 | 0.0026059 | 0.47346 | 0.33333 | 183 | 8289.1512 | 2.8551
|  | 0.9513 | 0.9513 | 0 | 0 | 1.1667 | 278.8333 | 10369.0123 | 0.8154
|  | 0.95052 | 0 | 0.95052 | 0 | 0 | 254.5 | 10695.6313 | #DIV/0!
|  | 0.94952 | 0.039362 | 0.45107 | 0.45909 | 0.66667 | 177.5 | 8600.6686 | 1.4243
|  | 0.94547 | 0 | 0.93122 | 0.014247 | 0 | 267.6667 | 11257.529 | #DIV/0!
|  | 0.94546 | 0.94546 | 0 | 0 | 0.83333 | 348.5 | 12337.2263 | 1.1346
|  | 0.94521 | 0.94521 | 0 | 0 | 0.5 | 203.5 | 8105.1227 | 1.8904
|  | 0.94502 | 0.94502 | 0 | 0 | 0.33333 | 185.1667 | 9442.679 | 2.8351
|  | 0.94483 | 0.94483 | 0 | 0 | 1.5 | 250 | 10467.7263 | 0.62989
|  | 0.94348 | 0.94348 | 0 | 0 | 0 | 231.1667 | 8635.9243 | #DIV/0!
|  | 0.94312 | 0.47132 | 0 | 0.4718 | 1.6667 | 226.8333 | 9912.745 | 0.56587
|  | 0.94294 | 0 | 0.93392 | 0.0090228 | 0 | 120.5 | 5069.4355 | #DIV/0!
|  | 0.94017 | 0.00039893 | 0.00044878 | 0.93932 | 0 | 170.6667 | 7587.9986 | #DIV/0!
|  | 0.9351 | 0.9351 | 0 | 0 | 0 | 280.6667 | 10485.1453 | #DIV/0!
|  | 0.93492 | 0.46815 | 0 | 0.46677 | 0.83333 | 263.1667 | 6998.3333 | 1.1219
|  | 0.93437 | 0 | 0.93437 | 0 | 0 | 245.3333 | 10310.3924 | #DIV/0!
|  | 0.93424 | 0.93424 | 0 | 0 | 1.6667 | 311.8333 | 12224.0597 | 0.56054
|  | 0.93271 | 0.93271 | 0 | 0 | 0 | 244.6667 | 9140.2573 | #DIV/0!
|  | 0.93155 | 0.46701 | 0.00089757 | 0.46365 | 0.33333 | 150.6667 | 7603.8321 | 2.7947
|  | 0.93082 | 0.31122 | 0.30838 | 0.31122 | 0.33333 | 226.5 | 9973.7494 | 2.7925
|  | 0.92616 | 0.30998 | 0.30809 | 0.30809 | 0.83333 | 273.3333 | 9676 | 1.1114
|  | 0.92305 | 0.0052539 | 0.45626 | 0.46154 | 0.66667 | 273.3333 | 11030.4161 | 1.3846
|  | 0.92261 | 0.4654 | 0.0016445 | 0.45557 | 0.66667 | 158.3333 | 6097.8234 | 1.3839
|  | 0.92234 | 0.92234 | 0 | 0 | 0 | 305.5 | 11412.869 | #DIV/0!
|  | 0.92172 | 0 | 0 | 0.92172 | 1.5 | 9 | 419 | 0.61448
|  | 0.92123 | 0 | 0.85807 | 0.06316 | 0 | 200.5 | 8462.0726 | #DIV/0!
|  | 0.91952 | 0.45999 | 0 | 0.45953 | 0.16667 | 196.5 | 8646.0784 | 5.5171
|  | 0.91908 | 0.91908 | 0 | 0 | 1.1667 | 232 | 8467.965 | 0.78778
|  | 0.91865 | 0.016338 | 0.87647 | 0.025836 | 0.16667 | 216.5 | 9129.3579 | 5.5119
|  | 0.91821 | 0 | 0.91821 | 0 | 0 | 253.6667 | 10660.6095 | #DIV/0!
|  | 0.91686 | 0 | 0.91686 | 0 | 0 | 223.8333 | 9406.8322 | #DIV/0!
|  | 0.91282 | 0 | 0.91282 | 0 | 0 | 166.5 | 6997.3383 | #DIV/0!
|  | 0.91156 | 0.91156 | 0 | 0 | 0 | 237.3333 | 8866.2987 | #DIV/0!
|  | 0.90879 | 0 | 0.90879 | 0 | 0 | 214.1667 | 9000.5803 | #DIV/0!
|  | 0.9079 | 0.9079 | 0 | 0 | 0.16667 | 269.3333 | 9160.6913 | 5.4474
|  | 0.90767 | 0.90767 | 0 | 0 | 0.33333 | 250.3333 | 10512.4527 | 2.723
|  | 0.90688 | 0.40932 | 0.00089757 | 0.49665 | 0.5 | 165.8333 | 7204.2494 | 1.8138
|  | 0.90502 | 0.90502 | 0 | 0 | 1 | 244 | 9190.6667 | 0.90502
|  | 0.90354 | 0.012686 | 0.43979 | 0.45107 | 0.33333 | 106.3333 | 7018 | 2.7106
|  | 0.90205 | 0 | 0.90205 | 0 | 0 | 223 | 9371.8105 | #DIV/0!
|  | 0.90093 | 0.45576 | 0 | 0.44517 | 1.1667 | 325.1667 | 12982.4901 | 0.77222
|  | 0.90031 | 0.016766 | 0.43423 | 0.44932 | 1.1667 | 432.8333 | 9707.8333 | 0.77169
|  | 0.89981 | 0 | 0.89981 | 0 | 0 | 286.3333 | 12033.4607 | #DIV/0!
|  | 0.89846 | 0 | 0.89846 | 0 | 0 | 217.1667 | 9126.6585 | #DIV/0!
|  | 0.89834 | 0.89834 | 0 | 0 | 1.1667 | 243.1667 | 9071 | 0.77001
|  | 0.8968 | 0.4484 | 0 | 0.4484 | 0.83333 | 206.6667 | 10209.3333 | 1.0762
|  | 0.89667 | 0 | 0.89667 | 0 | 0 | 211.8333 | 8902.5195 | #DIV/0!
|  | 0.89281 | 0.89281 | 0 | 0 | 0 | 229.3333 | 8567.4347 | #DIV/0!
|  | 0.89207 | 0.89207 | 0 | 0 | 0.16667 | 280.5 | 9542.037 | 5.3524
|  | 0.89148 | 0.44545 | 0 | 0.44603 | 0.33333 | 95.8333 | 4140.7252 | 2.6744
|  | 0.8909 | 0.8909 | 0 | 0 | 1.5 | 119 | 5193.179 | 0.59393
|  | 0.89036 | 0.038159 | 0.0024569 | 0.84975 | 0.33333 | 176.1667 | 9146.9646 | 2.6711
|  | 0.88983 | 0.88983 | 0 | 0 | 1 | 212 | 7914.6667 | 0.88983
|  | 0.88869 | 0.29766 | 0.29338 | 0.29766 | 0.33333 | 138.3333 | 5805 | 2.6661
|  | 0.88806 | 0.44439 | 0 | 0.44367 | 0.16667 | 226.8333 | 9301.9018 | 5.3284
|  | 0.88598 | 0.44485 | 0 | 0.44113 | 1.3333 | 180.1667 | 8849.9117 | 0.66449
|  | 0.88563 | 0 | 0.00044878 | 0.88518 | 0 | 260.1667 | 11569.2723 | #DIV/0!
|  | 0.88284 | 0.44134 | 0 | 0.4415 | 0.16667 | 35.6667 | 1322.1568 | 5.297
|  | 0.88236 | 0.88236 | 0 | 0 | 0.16667 | 266.8333 | 10566.983 | 5.2942
|  | 0.88186 | 0 | 0.88186 | 0 | 0 | 212.3333 | 8923.5326 | #DIV/0!
|  | 0.87438 | 0 | 0.43505 | 0.43933 | 0.33333 | 150.3333 | 9906.8321 | 2.6231
|  | 0.87205 | 0.87205 | 0 | 0 | 0.5 | 144 | 7824 | 1.7441
|  | 0.87109 | 0 | 0.87109 | 0 | 0 | 205.8333 | 8650.3632 | #DIV/0!
|  | 0.87087 | 0.87087 | 0 | 0 | 0 | 253 | 9451.574 | #DIV/0!
|  | 0.86989 | 0.43814 | 0 | 0.43175 | 1.3333 | 293.8333 | 11816.745 | 0.65242
|  | 0.86654 | 0.86654 | 0 | 0 | 0.83333 | 267.3333 | 8558.179 | 1.0398
|  | 0.86609 | 0.43281 | 0 | 0.43328 | 2.5 | 245.1667 | 9464.4117 | 0.34644
|  | 0.86529 | 0.86529 | 0 | 0 | 0 | 246.8333 | 9221.1997 | #DIV/0!
|  | 0.86529 | 0.86529 | 0 | 0 | 0 | 269.1667 | 10055.5283 | #DIV/0!
|  | 0.8648 | 0 | 0.8648 | 0 | 0 | 229.6667 | 9651.9842 | #DIV/0!
|  | 0.86417 | 0 | 0.65522 | 0.20895 | 0 | 237.1667 | 10084.9089 | #DIV/0!
|  | 0.86346 | 0 | 0.86346 | 0 | 0 | 184 | 7732.7943 | #DIV/0!
|  | 0.86286 | 0 | 0 | 0.86286 | 0 | 230.8333 | 10265.2187 | #DIV/0!
|  | 0.86144 | 0.43076 | 0 | 0.43068 | 1 | 236.5 | 7390.8333 | 0.86144
|  | 0.86121 | 0 | 0.86121 | 0 | 0 | 182 | 7648.7422 | #DIV/0!
|  | 0.85922 | 0.0033317 | 0.42736 | 0.42852 | 0.33333 | 163.3333 | 8490.4161 | 2.5777
|  | 0.85688 | 0.4289 | 0 | 0.42798 | 0.16667 | 249.6667 | 8502.0013 | 5.1413
|  | 0.85583 | 0 | 0.85583 | 0 | 0 | 186.5 | 7837.8594 | #DIV/0!
|  | 0.85538 | 0 | 0.85538 | 0 | 0 | 207.3333 | 8713.4023 | #DIV/0!
|  | 0.85403 | 0 | 0.85403 | 0 | 0 | 259.3333 | 10898.7572 | #DIV/0!
|  | 0.85135 | 0.0017086 | 0.41092 | 0.43873 | 0.33333 | 226.1667 | 9047.4117 | 2.5541
|  | 0.84934 | 0.42321 | 0.0030547 | 0.42308 | 0.5 | 177.6667 | 8963.4988 | 1.6987
|  | 0.84831 | 0.84831 | 0 | 0 | 0.66667 | 291.6667 | 10427.6193 | 1.2725
|  | 0.84621 | 0.33969 | 0.16425 | 0.34227 | 0.66667 | 219.5 | 7971.6976 | 1.2693
|  | 0.84506 | 0 | 0.84506 | 0 | 0 | 206.5 | 8678.3806 | #DIV/0!
|  | 0.84259 | 0.84259 | 0 | 0 | 1 | 184.1667 | 6354.2263 | 0.84259
|  | 0.84057 | 0 | 0.84057 | 0 | 0 | 175.1667 | 7361.5641 | #DIV/0!
|  | 0.84015 | 0.023322 | 0.0013463 | 0.81548 | 0.33333 | 163.6667 | 8501.9148 | 2.5205
|  | 0.83896 | 0.83896 | 0 | 0 | 0 | 304.6667 | 11381.7373 | #DIV/0!
|  | 0.83821 | 0.83821 | 0 | 0 | 1.8333 | 181.8333 | 8553.6193 | 0.45721
|  | 0.8381 | 0.41796 | 0 | 0.42014 | 0.33333 | 398 | 7578.9802 | 2.5143
|  | 0.83503 | 0.41752 | 0 | 0.41752 | 1.1667 | 207.6667 | 10264.6667 | 0.71574
|  | 0.83355 | 0.41583 | 0.0018901 | 0.41583 | 0.83333 | 164.1667 | 5811.5 | 1.0003
|  | 0.83298 | 0.83298 | 0 | 0 | 0.16667 | 195.3333 | 8760.7057 | 4.9979
|  | 0.83191 | 0.83191 | 0 | 0 | 0.33333 | 222.8333 | 9801.3457 | 2.4957
|  | 0.83178 | 0.83178 | 0 | 0 | 0 | 264.5 | 9881.191 | #DIV/0!
|  | 0.83098 | 0.41528 | 0 | 0.4157 | 1.6667 | 400.1667 | 10446.5 | 0.49859
|  | 0.82899 | 0.82899 | 0 | 0 | 0 | 278.6667 | 10410.4293 | #DIV/0!
|  | 0.82865 | 0.82865 | 0 | 0 | 0.83333 | 272.8333 | 10931.4527 | 0.99438
|  | 0.82832 | 0.41416 | 0 | 0.41416 | 0.5 | 189 | 6363 | 1.6566
|  | 0.82712 | 0.82712 | 0 | 0 | 1 | 258.1667 | 8907.2263 | 0.82712
|  | 0.82666 | 0 | 0.40578 | 0.42088 | 0.16667 | 237.6667 | 8799.8919 | 4.9599
|  | 0.826 | 0 | 0.826 | 0 | 0.33333 | 187.5 | 8061.6884 | 2.478
|  | 0.82513 | 0.41164 | 0.00089757 | 0.41259 | 1.5 | 174.3333 | 8115.0827 | 0.55009
|  | 0.82452 | 0.3439 | 0.13673 | 0.3439 | 1 | 179 | 5787.6667 | 0.82452
|  | 0.82349 | 0.82349 | 0 | 0 | 0.16667 | 252.3333 | 8582.1317 | 4.9409
|  | 0.8218 | 0.41066 | 0 | 0.41114 | 0.16667 | 198.6667 | 8741.4901 | 4.9308
|  | 0.81599 | 0.81599 | 0 | 0 | 1.1667 | 268.8333 | 6996.2387 | 0.69942
|  | 0.81596 | 0.0043883 | 0 | 0.81158 | 0 | 208.8333 | 9283.3168 | #DIV/0!
|  | 0.815 | 0.27679 | 0.26141 | 0.27679 | 0.83333 | 345 | 11040 | 0.978
|  | 0.81362 | 0.40726 | 0.0013885 | 0.40497 | 0.66667 | 157.6667 | 8698.4757 | 1.2204
|  | 0.81045 | 0.28053 | 0.24892 | 0.281 | 1.8333 | 251.3333 | 8455.745 | 0.44207
|  | 0.81044 | 0.40553 | 0.00044878 | 0.40445 | 0.5 | 243.6667 | 8204.8377 | 1.6209
|  | 0.81005 | 0 | 0.81005 | 0 | 0 | 217.6667 | 9147.6715 | #DIV/0!
|  | 0.80735 | 0.016766 | 0.38773 | 0.40285 | 1.1667 | 384.1667 | 8623.2494 | 0.69201
|  | 0.80467 | 0 | 0.80467 | 0 | 0 | 195 | 8195.0809 | #DIV/0!
|  | 0.80257 | 0.40216 | 0.0017409 | 0.39867 | 0.16667 | 301 | 10932.6413 | 4.8154
|  | 0.80088 | 0.40044 | 0 | 0.40044 | 1.8333 | 179.6667 | 7954.3333 | 0.43684
|  | 0.7994 | 0.7994 | 0 | 0 | 0.5 | 184 | 7717.5597 | 1.5988
|  | 0.79882 | 0.024433 | 0 | 0.77439 | 0.33333 | 179.5 | 9330.2351 | 2.3965
|  | 0.7982 | 0.7982 | 0 | 0 | 1.1667 | 123.1667 | 5686.5 | 0.68417
|  | 0.7941 | 0.39738 | 0 | 0.39673 | 0.66667 | 309.8333 | 8798.9117 | 1.1912
|  | 0.79398 | 0 | 0.00044878 | 0.79353 | 0 | 197.6667 | 8789.881 | #DIV/0!
|  | 0.79255 | 0 | 0.79255 | 0 | 0 | 238.5 | 10023.2144 | #DIV/0!
|  | 0.79245 | 0.39757 | 0 | 0.39489 | 0.16667 | 248.3333 | 8445.0784 | 4.7547
|  | 0.78989 | 0.13117 | 0.29628 | 0.36244 | 1.5 | 280.6667 | 11557.7494 | 0.52659
|  | 0.78855 | 0.78855 | 0 | 0 | 0.33333 | 212.6667 | 7762.9053 | 2.3657
|  | 0.78831 | 0.39392 | 0 | 0.39439 | 0.33333 | 142.8333 | 6213.4117 | 2.3649
|  | 0.78805 | 0.26382 | 0.25994 | 0.26429 | 2 | 352.3333 | 11894.4161 | 0.39402
|  | 0.78681 | 0.39404 | 0 | 0.39277 | 0.66667 | 235.5 | 9656.0784 | 1.1802
|  | 0.78627 | 0 | 0.78627 | 0 | 0 | 210.1667 | 8832.4761 | #DIV/0!
|  | 0.78272 | 0.78272 | 0 | 0 | 0.16667 | 190.6667 | 8388.2263 | 4.6963
|  | 0.78191 | 0.78191 | 0 | 0 | 0 | 204.8333 | 7652.1637 | #DIV/0!
|  | 0.78178 | 0 | 0.78178 | 0 | 0 | 191.3333 | 8040.9854 | #DIV/0!
|  | 0.77916 | 0.77916 | 0 | 0 | 1 | 200.1667 | 7306.2263 | 0.77916
|  | 0.77916 | 0.38997 | 0 | 0.38919 | 0.16667 | 256.8333 | 9509.0586 | 4.675
|  | 0.77786 | 0 | 0 | 0.77786 | 0 | 93.8333 | 4172.7929 | #DIV/0!
|  | 0.77684 | 0 | 0.77684 | 0 | 0 | 190.1667 | 7991.955 | #DIV/0!
|  | 0.77668 | 0.011277 | 0.37777 | 0.38764 | 0.33333 | 129.6667 | 8558 | 2.33
|  | 0.77643 | 0 | 0 | 0.77643 | 0 | 194.3333 | 8642.0542 | #DIV/0!
|  | 0.77593 | 0 | 0.00044878 | 0.77549 | 0 | 138.5 | 6158.7239 | #DIV/0!
|  | 0.77186 | 0.77186 | 0 | 0 | 0.33333 | 285.6667 | 10282.7263 | 2.3156
|  | 0.76787 | 0 | 0.76787 | 0 | 0 | 162.3333 | 6822.2298 | #DIV/0!
|  | 0.76554 | 0.76554 | 0 | 0 | 0.16667 | 166 | 6346.2393 | 4.5932
|  | 0.76437 | 0.38329 | 0 | 0.38108 | 1 | 205.1667 | 8583.245 | 0.76437
|  | 0.76211 | 0.00039893 | 0 | 0.76171 | 0 | 209.3333 | 9307.9227 | #DIV/0!
|  | 0.76077 | 0.76077 | 0 | 0 | 0 | 225.8333 | 8436.6817 | #DIV/0!
|  | 0.75996 | 0.25332 | 0.25332 | 0.25332 | 1.8333 | 262.5 | 9362.5 | 0.41452
|  | 0.75941 | 0.75941 | 0 | 0 | 0.16667 | 234 | 10524.9053 | 4.5564
|  | 0.75558 | 0.75558 | 0 | 0 | 0 | 238.1667 | 8897.4303 | #DIV/0!
|  | 0.75454 | 0 | 0.00089757 | 0.75364 | 0 | 211.8333 | 9419.469 | #DIV/0!
|  | 0.75005 | 0.37502 | 0.0018474 | 0.37318 | 0.66667 | 121.3333 | 5247.6667 | 1.1251
|  | 0.7499 | 0.7499 | 0 | 0 | 2.1667 | 250.1667 | 8934.893 | 0.34611
|  | 0.74966 | 0.74966 | 0 | 0 | 1.3333 | 126.5 | 3877.786 | 0.56225
|  | 0.7492 | 0.7492 | 0 | 0 | 0 | 231.5 | 8648.377 | #DIV/0!
|  | 0.74879 | 0.37529 | 0 | 0.37349 | 0.83333 | 257.3333 | 9798.9603 | 0.89854
|  | 0.74777 | 0.35201 | 0.047905 | 0.34786 | 0.5 | 250.6667 | 8455.5244 | 1.4955
|  | 0.74633 | 0.74633 | 0 | 0 | 0.16667 | 194 | 6603.2757 | 4.478
|  | 0.74561 | 0.74561 | 0 | 0 | 0 | 213.1667 | 7963.4803 | #DIV/0!
|  | 0.74145 | 0.74145 | 0 | 0 | 0.33333 | 219.3333 | 8595.4387 | 2.2244
|  | 0.74042 | 0.74042 | 0 | 0 | 0 | 213.8333 | 7988.3857 | #DIV/0!
|  | 0.73926 | 0.36918 | 0.00089757 | 0.36918 | 1.1667 | 156.5 | 5769.0043 | 0.63366
|  | 0.73892 | 0 | 0 | 0.73892 | 0 | 200.5 | 8916.2874 | #DIV/0!
|  | 0.7378 | 0 | 0.7378 | 0 | 0 | 169.8333 | 7137.4252 | #DIV/0!
|  | 0.73722 | 0.73722 | 0 | 0 | 0.16667 | 204.3333 | 9188.6317 | 4.4233
|  | 0.73691 | 0.36846 | 0 | 0.36846 | 1 | 204 | 7718 | 0.73691
|  | 0.73656 | 0.36872 | 0 | 0.36784 | 0.16667 | 160.3333 | 6894.8234 | 4.4194
|  | 0.73404 | 0.73404 | 0 | 0 | 0 | 168 | 6276.144 | #DIV/0!
|  | 0.73352 | 0.36676 | 0 | 0.36676 | 0.66667 | 221.3333 | 8256.3333 | 1.1003
|  | 0.73341 | 0.36671 | 0 | 0.36671 | 0.5 | 40 | 1346.6667 | 1.4668
|  | 0.73239 | 0.053308 | 0.0051269 | 0.67396 | 0.33333 | 175.3333 | 9100.6444 | 2.1972
|  | 0.72882 | 0 | 0.72882 | 0 | 0 | 157.3333 | 6612.0995 | #DIV/0!
|  | 0.72513 | 0.31993 | 0.083922 | 0.32128 | 0.83333 | 213.6667 | 7056.8009 | 0.87016
|  | 0.72367 | 0.72367 | 0 | 0 | 0 | 211 | 7882.538 | #DIV/0!
|  | 0.72344 | 0 | 0.72344 | 0 | 0 | 223.5 | 9392.8235 | #DIV/0!
|  | 0.72304 | 0.72304 | 0 | 0 | 1 | 130.1667 | 4751.2263 | 0.72304
|  | 0.72145 | 0.72145 | 0 | 0 | 0.83333 | 189.3333 | 6900.9053 | 0.86574
|  | 0.72075 | 0 | 0.72075 | 0 | 0 | 153 | 6429.9866 | #DIV/0!
|  | 0.71775 | 0.017769 | 0 | 0.69998 | 0.33333 | 156.1667 | 8116.9018 | 2.1533
|  | 0.71765 | 0.71765 | 0 | 0 | 0.33333 | 238.3333 | 8804.6847 | 2.1529
|  | 0.71472 | 0.3581 | 0 | 0.35663 | 0.33333 | 242.6667 | 8372 | 2.1442
|  | 0.71299 | 0.23766 | 0.23766 | 0.23766 | 1.1667 | 17.5 | 535 | 0.61114
|  | 0.7121 | 0.7121 | 0 | 0 | 0 | 213.5 | 7975.933 | #DIV/0!
|  | 0.71135 | 0 | 0.00044878 | 0.7109 | 0 | 179.6667 | 7989.4163 | #DIV/0!
|  | 0.70966 | 0.70966 | 0 | 0 | 0.83333 | 43.3333 | 2028 | 0.85159
|  | 0.70867 | 0.049389 | 0.6099 | 0.049389 | 0.5 | 169.3333 | 7107.4274 | 1.4173
|  | 0.70851 | 0.36837 | 0 | 0.34014 | 1.6667 | 166.8333 | 7474.0784 | 0.42511
|  | 0.70623 | 0.35288 | 0 | 0.35335 | 0.5 | 232.8333 | 7858.4117 | 1.4125
|  | 0.70607 | 0.35304 | 0 | 0.35304 | 0.5 | 160 | 7733.3333 | 1.4121
|  | 0.70555 | 0.70555 | 0 | 0 | 2.3333 | 228.6667 | 8212.0247 | 0.30238
|  | 0.70532 | 0.70532 | 0 | 0 | 0 | 195.1667 | 7291.0363 | #DIV/0!
|  | 0.70267 | 0 | 0.0026927 | 0.69998 | 0 | 147.1667 | 6542.096 | #DIV/0!
|  | 0.69972 | 0 | 0.64131 | 0.058411 | 0 | 182.3333 | 7700.6361 | #DIV/0!
|  | 0.69841 | 0.34892 | 0 | 0.34949 | 0.16667 | 206.3333 | 6400.8234 | 4.1904
|  | 0.69803 | 0 | 0.59688 | 0.10115 | 0 | 200.8333 | 8517.2254 | #DIV/0!
|  | 0.69694 | 0.69694 | 0 | 0 | 0 | 215.5 | 8050.649 | #DIV/0!
|  | 0.69666 | 0.34833 | 0 | 0.34833 | 1.3333 | 125.3333 | 6157 | 0.52249
|  | 0.69632 | 0.23312 | 0.22961 | 0.23359 | 1.6667 | 233.6667 | 8647.7494 | 0.41779
|  | 0.69516 | 0 | 0.69516 | 0 | 0 | 156.6667 | 6584.0821 | #DIV/0!
|  | 0.69478 | 0 | 0.67721 | 0.017571 | 0 | 148.5 | 6251.0535 | #DIV/0!
|  | 0.69444 | 0.34736 | 0 | 0.34709 | 0.33333 | 362.3333 | 6892.8234 | 2.0833
|  | 0.69382 | 0 | 0.69382 | 0 | 0 | 128.3333 | 5393.3439 | #DIV/0!
|  | 0.69363 | 0.69363 | 0 | 0 | 0.33333 | 171.6667 | 7548.9053 | 2.0809
|  | 0.69286 | 0 | 0 | 0.69286 | 0 | 179.3333 | 7975.0002 | #DIV/0!
|  | 0.69157 | 0 | 0.69157 | 0 | 0 | 225 | 9455.8626 | #DIV/0!
|  | 0.68977 | 0 | 0.63278 | 0.056986 | 0 | 167.6667 | 7084.2539 | #DIV/0!
|  | 0.68559 | 0 | 0.45148 | 0.23412 | 0 | 169.8333 | 7250.266 | #DIV/0!
|  | 0.68537 | 0.68537 | 0 | 0 | 0 | 188.6667 | 7048.2093 | #DIV/0!
|  | 0.68425 | 0.68425 | 0 | 0 | 0.16667 | 228.6667 | 7778.0247 | 4.1055
|  | 0.68388 | 0.34373 | 0 | 0.34015 | 0.5 | 395.3333 | 6861.4901 | 1.3678
|  | 0.68316 | 0.68316 | 0 | 0 | 1 | 215 | 8733 | 0.68316
|  | 0.68174 | 0 | 0.28902 | 0.39273 | 0 | 140.6667 | 6112.4974 | #DIV/0!
|  | 0.6804 | 0.016766 | 0.32402 | 0.33961 | 1.1667 | 323.6667 | 7269.9944 | 0.5832
|  | 0.6803 | 0.6803 | 0 | 0 | 2.1667 | 15.1667 | 701.1667 | 0.31398
|  | 0.67811 | 0 | 0.67811 | 0 | 0 | 150.8333 | 6338.9301 | #DIV/0!
|  | 0.67779 | 0.67779 | 0 | 0 | 0 | 219.8333 | 8212.5337 | #DIV/0!
|  | 0.67645 | 0.011106 | 0.00089757 | 0.66444 | 0.33333 | 145.8333 | 7576.2438 | 2.0293
|  | 0.67558 | 0.34096 | 0 | 0.33462 | 1.1667 | 94.6667 | 3635.7351 | 0.57907
|  | 0.67457 | 0.33704 | 0 | 0.33753 | 0.16667 | 197.5 | 8492.9901 | 4.0474
|  | 0.67407 | 0 | 0.67407 | 0 | 0 | 204 | 8573.3154 | #DIV/0!
|  | 0.67276 | 0.00041647 | 0.33382 | 0.33852 | 0.16667 | 184.6667 | 7209.5846 | 4.0365
|  | 0.67235 | 0.33566 | 0 | 0.33669 | 0.16667 | 145.5 | 6256.9901 | 4.0341
|  | 0.67196 | 0 | 0 | 0.67196 | 0 | 95.6667 | 4254.3217 | #DIV/0!
|  | 0.67196 | 0.33527 | 0 | 0.33669 | 0.66667 | 84.3333 | 3521.8234 | 1.0079
|  | 0.67024 | 0 | 0.32357 | 0.34667 | 0 | 87.8333 | 3800.0557 | #DIV/0!
|  | 0.66869 | 0 | 0.66869 | 0 | 0 | 187.5 | 7879.8855 | #DIV/0!
|  | 0.66853 | 0.66853 | 0 | 0 | 0.16667 | 204 | 7548 | 4.0112
|  | 0.6683 | 0.33452 | 0 | 0.33378 | 0.33333 | 210.3333 | 7256.5 | 2.0049
|  | 0.66808 | 0.31908 | 0.033305 | 0.31569 | 0.16667 | 154.1667 | 6905.5131 | 4.0085
|  | 0.66571 | 0.00039893 | 0 | 0.66531 | 0 | 189.3333 | 8418.5175 | #DIV/0!
|  | 0.66517 | 0.3345 | 0 | 0.33067 | 0.66667 | 199.8333 | 8194.9018 | 0.99775
|  | 0.66502 | 0.66502 | 0 | 0 | 0 | 184.5 | 6892.551 | #DIV/0!
|  | 0.66436 | 0 | 0 | 0.66436 | 0 | 116.3333 | 5173.3738 | #DIV/0!
|  | 0.66409 | 0.66409 | 0 | 0 | 0.33333 | 123.6667 | 5192.4527 | 1.9923
|  | 0.66285 | 0 | 0.66285 | 0 | 0 | 176 | 7396.5859 | #DIV/0!
|  | 0.6624 | 0 | 0.6624 | 0 | 0 | 92.5 | 3887.4102 | #DIV/0!
|  | 0.66223 | 0.66223 | 0 | 0 | 0 | 200.8333 | 7502.7317 | #DIV/0!
|  | 0.66195 | 0 | 0.66195 | 0 | 0 | 192 | 8069.0028 | #DIV/0!
|  | 0.66142 | 0.66142 | 0 | 0 | 0.33333 | 169.3333 | 7448.4527 | 1.9843
|  | 0.65971 | 0 | 0.65971 | 0 | 0 | 142 | 5967.7 | #DIV/0!
|  | 0.65952 | 0.22383 | 0.21187 | 0.22383 | 0.83333 | 289.1667 | 9253.3333 | 0.79142
|  | 0.65926 | 0 | 0.65926 | 0 | 0 | 140.3333 | 5897.6565 | #DIV/0!
|  | 0.65868 | 0.19514 | 0.26792 | 0.19562 | 0.83333 | 178.8333 | 6669.9284 | 0.79042
|  | 0.65777 | 0.18023 | 0.22968 | 0.24786 | 0.5 | 102.3333 | 6010.7494 | 1.3155
|  | 0.65672 | 0.006215 | 0.32318 | 0.32732 | 0.66667 | 144.6667 | 7016.3333 | 0.98508
|  | 0.65631 | 0.22033 | 0.21565 | 0.22033 | 1.6667 | 93.3333 | 4097.3333 | 0.39379
|  | 0.65468 | 0.089957 | 0.0013463 | 0.56338 | 0.33333 | 139 | 7222.1654 | 1.964
|  | 0.65264 | 0.0014096 | 0.3228 | 0.32843 | 0.33333 | 18 | 1188 | 1.9579
|  | 0.65245 | 0.65245 | 0 | 0 | 0.66667 | 203 | 6501.2983 | 0.97868
|  | 0.64907 | 0.64907 | 0 | 0 | 0 | 209.3333 | 7820.2747 | #DIV/0!
|  | 0.64723 | 0.32625 | 0.32098 | 0 | 0.16667 | 195.8333 | 7441.5597 | 3.8834
|  | 0.64703 | 0.32332 | 0 | 0.32371 | 0.66667 | 208.6667 | 7323.0685 | 0.97054
|  | 0.64627 | 0.64627 | 0 | 0 | 0 | 178.6667 | 6674.6293 | #DIV/0!
|  | 0.64625 | 0.24516 | 0.087042 | 0.31404 | 2.5 | 224.6667 | 8832.245 | 0.2585
|  | 0.64587 | 0.64587 | 0 | 0 | 0 | 220.8333 | 8249.8917 | #DIV/0!
|  | 0.64548 | 0.64548 | 0 | 0 | 0 | 220.5 | 8237.439 | #DIV/0!
|  | 0.64266 | 0 | 0.64266 | 0 | 0 | 162.5 | 6829.2341 | #DIV/0!
|  | 0.63903 | 0 | 0.58252 | 0.056511 | 0 | 149.5 | 6314.2627 | #DIV/0!
|  | 0.63843 | 0.63843 | 0 | 0 | 0.16667 | 211 | 7175.679 | 3.8306
|  | 0.63691 | 0.26637 | 0.10322 | 0.26732 | 1.1667 | 195 | 6817.0761 | 0.54592
|  | 0.63255 | 0 | 0 | 0.63255 | 0 | 160.1667 | 7122.6536 | #DIV/0!
|  | 0.63206 | 0.016766 | 0.3001 | 0.31519 | 1.1667 | 320.8333 | 7195.8333 | 0.54177
|  | 0.63032 | 0.63032 | 0 | 0 | 0 | 204.5 | 7639.711 | #DIV/0!
|  | 0.62912 | 0.00039893 | 0.00044878 | 0.62827 | 0 | 134 | 5957.4223 | #DIV/0!
|  | 0.62845 | 0.62845 | 0 | 0 | 1 | 185.3333 | 6393.0597 | 0.62845
|  | 0.6283 | 0.6283 | 0 | 0 | 0.16667 | 190.8333 | 6490.572 | 3.7698
|  | 0.62685 | 0 | 0 | 0.62685 | 0 | 127.8333 | 5684.7818 | #DIV/0!
|  | 0.62597 | 0.31188 | 0.00044878 | 0.31364 | 0.16667 | 174.3333 | 5935.6512 | 3.7558
|  | 0.6256 | 0 | 0.6256 | 0 | 0 | 137.3333 | 5771.5784 | #DIV/0!
|  | 0.62449 | 0 | 0.3112 | 0.3133 | 0.66667 | 110.3333 | 5349.4161 | 0.93674
|  | 0.62314 | 0.62314 | 0 | 0 | 0 | 190.1667 | 7104.2463 | #DIV/0!
|  | 0.62067 | 0 | 0.62067 | 0 | 0 | 199.6667 | 8391.2025 | #DIV/0!
|  | 0.62067 | 0 | 0.62067 | 0 | 0 | 151.1667 | 6352.9388 | #DIV/0!
|  | 0.61581 | 0.61581 | 0 | 0 | 0.66667 | 119.6667 | 5875.1193 | 0.92371
|  | 0.61536 | 0.0088847 | 0.0020081 | 0.60447 | 0.33333 | 110.1667 | 5724.4944 | 1.8461
|  | 0.61037 | 0.61037 | 0 | 0 | 0 | 129.3333 | 4831.6347 | #DIV/0!
|  | 0.60965 | 0.30482 | 0 | 0.30482 | 0.66667 | 196 | 8477 | 0.91447
|  | 0.60855 | 0 | 0.60855 | 0 | 0 | 143.5 | 6030.739 | #DIV/0!
|  | 0.60846 | 0.60846 | 0 | 0 | 0.83333 | 170 | 4193 | 0.73015
|  | 0.6082 | 0.00039893 | 0.00089757 | 0.6069 | 0 | 170 | 7558.3517 | #DIV/0!
|  | 0.60678 | 0.60678 | 0 | 0 | 0 | 189.1667 | 7066.8883 | #DIV/0!
|  | 0.60675 | 0 | 0.60675 | 0 | 0 | 74.8333 | 3144.9499 | #DIV/0!
|  | 0.60591 | 0.60591 | 0 | 0 | 0.16667 | 342.5 | 7225.216 | 3.6355
|  | 0.60451 | 0 | 0.60451 | 0 | 0 | 117 | 4917.0486 | #DIV/0!
|  | 0.60382 | 0.60382 | 0 | 0 | 0.33333 | 140.1667 | 6161.7983 | 1.8115
|  | 0.60319 | 0.60319 | 0 | 0 | 0 | 217.1667 | 8112.9123 | #DIV/0!
|  | 0.60237 | 0.0084575 | 0.29037 | 0.30354 | 0.33333 | 58.1667 | 3835.4117 | 1.8071
|  | 0.60234 | 0.60234 | 0 | 0 | 2 | 6 | 276.5 | 0.30117
|  | 0.60122 | 0.60122 | 0 | 0 | 2 | 193.3333 | 7083.537 | 0.30061
|  | 0.60088 | 0.30113 | 0 | 0.29976 | 0.66667 | 178.1667 | 7705.9117 | 0.90133
|  | 0.6006 | 0.010764 | 0.29108 | 0.29876 | 1.3333 | 172.5 | 7245.8278 | 0.45045
|  | 0.59973 | 0.30135 | 0 | 0.29837 | 1.6667 | 140.3333 | 4883.8333 | 0.35984
|  | 0.59883 | 0 | 0 | 0.59883 | 0 | 124.1667 | 5521.7241 | #DIV/0!
|  | 0.59767 | 0.00079787 | 0.00089757 | 0.59598 | 0 | 176.5 | 7845.8157 | #DIV/0!
|  | 0.59731 | 0.2989 | 0 | 0.29841 | 0.16667 | 125.8333 | 5662.4117 | 3.5838
|  | 0.59477 | 0.29691 | 0 | 0.29786 | 0.33333 | 103.6667 | 4354.8234 | 1.7843
|  | 0.59441 | 0.59441 | 0 | 0 | 0 | 194.5 | 7266.131 | #DIV/0!
|  | 0.58962 | 0.58962 | 0 | 0 | 0 | 189.8333 | 7091.7937 | #DIV/0!
|  | 0.58847 | 0.58847 | 0 | 0 | 1.1667 | 128.1667 | 4724.358 | 0.5044
|  | 0.58814 | 0.58814 | 0 | 0 | 1.5 | 117.1667 | 5453.2263 | 0.39209
|  | 0.58791 | 0 | 0.58791 | 0 | 0 | 139.1667 | 5848.6261 | #DIV/0!
|  | 0.58746 | 0 | 0.58746 | 0 | 0 | 164.3333 | 6906.2819 | #DIV/0!
|  | 0.58717 | 0.29663 | 0.29055 | 0 | 0.16667 | 210 | 7979.893 | 3.523
|  | 0.58707 | 0.29543 | 0.0023923 | 0.28925 | 0.66667 | 179.1667 | 5999.3377 | 0.88061
|  | 0.58656 | 0 | 0.58656 | 0 | 0 | 132.6667 | 5575.4568 | #DIV/0!
|  | 0.58615 | 0.29376 | 0.00036308 | 0.29202 | 0.16667 | 125 | 4252.3047 | 3.5169
|  | 0.586 | 0 | 0.21831 | 0.36769 | 1 | 148 | 6635.3333 | 0.586
|  | 0.58404 | 0.58404 | 0 | 0 | 0 | 177.1667 | 6618.5923 | #DIV/0!
|  | 0.58395 | 0.00039893 | 0.0013463 | 0.58221 | 0 | 152.5 | 6779.7148 | #DIV/0!
|  | 0.57936 | 0 | 0 | 0.57936 | 0 | 163 | 7248.6526 | #DIV/0!
|  | 0.57811 | 0.018068 | 0.26231 | 0.29773 | 0.33333 | 138.1667 | 6184.3321 | 1.7343
|  | 0.57738 | 0.57738 | 0 | 0 | 0.5 | 113.5 | 5572.2983 | 1.1548
|  | 0.57323 | 0 | 0.28448 | 0.28875 | 0.33333 | 169 | 6760 | 1.7197
|  | 0.57323 | 0.57323 | 0 | 0 | 0.33333 | 102.6667 | 4517.3333 | 1.7197
|  | 0.5731 | 0 | 0.5731 | 0 | 0 | 132.3333 | 5561.4481 | #DIV/0!
|  | 0.57194 | 0.00079022 | 0.17548 | 0.39567 | 0.16667 | 186.1667 | 6891.4944 | 3.4316
|  | 0.57149 | 0.57149 | 0 | 0 | 0.16667 | 279.6667 | 6669.0893 | 3.429
|  | 0.57097 | 0.57097 | 0 | 0 | 0.16667 | 151 | 5137.358 | 3.4258
|  | 0.569 | 0.19217 | 0.18607 | 0.19076 | 0.16667 | 138 | 6072 | 3.414
|  | 0.56883 | 0.00039893 | 0 | 0.56844 | 0 | 136.8333 | 6083.8287 | #DIV/0!
|  | 0.56836 | 0.00039893 | 0 | 0.56796 | 0 | 105.3333 | 4683.0155 | #DIV/0!
|  | 0.56581 | 0.28243 | 0 | 0.28338 | 0.33333 | 267.6667 | 5094.1568 | 1.6974
|  | 0.56516 | 0.28258 | 0 | 0.28258 | 0.33333 | 104.6667 | 5285.6667 | 1.6955
|  | 0.56461 | 0 | 0.00044878 | 0.56416 | 0 | 158.3333 | 7040.7174 | #DIV/0!
|  | 0.56412 | 0 | 0.56412 | 0 | 0 | 119.3333 | 5015.1094 | #DIV/0!
|  | 0.56397 | 0.56397 | 0 | 0 | 0.83333 | 178.8333 | 6258.4527 | 0.67677
|  | 0.56319 | 0.28191 | 0.00030968 | 0.28097 | 0.5 | 138.3333 | 5446.5784 | 1.1264
|  | 0.56211 | 0.00079787 | 0 | 0.56131 | 0 | 139.5 | 6201.2307 | #DIV/0!
|  | 0.56208 | 0.56208 | 0 | 0 | 0.33333 | 105.8333 | 4598.6317 | 1.6862
|  | 0.56143 | 0 | 0.56143 | 0 | 0 | 105.8333 | 4447.7576 | #DIV/0!
|  | 0.5612 | 0.28073 | 0 | 0.28047 | 0.33333 | 182.5 | 6297.9117 | 1.6836
|  | 0.56119 | 0.28059 | 0 | 0.28059 | 1.3333 | 236 | 6766 | 0.42089
|  | 0.56081 | 0 | 0.00044878 | 0.56036 | 0 | 159 | 7070.3642 | #DIV/0!
|  | 0.56049 | 0.27737 | 0 | 0.28313 | 0.16667 | 133.6667 | 5217.5586 | 3.363
|  | 0.55751 | 0 | 0 | 0.55751 | 0 | 142.1667 | 6322.1888 | #DIV/0!
|  | 0.55649 | 0 | 0.55649 | 0 | 0 | 120.8333 | 5078.1484 | #DIV/0!
|  | 0.55532 | 0.55532 | 0 | 0 | 0 | 187.5 | 7004.625 | #DIV/0!
|  | 0.55335 | 0 | 0.55335 | 0 | 0 | 149.5 | 6282.8954 | #DIV/0!
|  | 0.55309 | 0.27738 | 0.00044878 | 0.27526 | 0.33333 | 126.5 | 6338.2494 | 1.6593
|  | 0.55238 | 0.55238 | 0 | 0 | 0.16667 | 156.3333 | 5784.572 | 3.3143
|  | 0.55201 | 0.13435 | 0.054751 | 0.36292 | 0.16667 | 185.1667 | 7459.217 | 3.3121
|  | 0.55154 | 0.014502 | 0.26517 | 0.27186 | 0.66667 | 106.1667 | 5148.4117 | 0.82731
|  | 0.55101 | 0.55101 | 0 | 0 | 0.16667 | 157.6667 | 7084.8107 | 3.306
|  | 0.55036 | 0 | 0.00044878 | 0.54992 | 0 | 146.5 | 6514.4859 | #DIV/0!
|  | 0.55032 | 0.05791 | 0.00044878 | 0.49196 | 1.3333 | 134 | 5345.9061 | 0.41274
|  | 0.55021 | 0 | 0.55021 | 0 | 0 | 137 | 5757.5697 | #DIV/0!
|  | 0.55013 | 0.55013 | 0 | 0 | 0 | 181.5 | 6780.477 | #DIV/0!
|  | 0.54897 | 0 | 0 | 0.54897 | 0 | 118.6667 | 5277.1377 | #DIV/0!
|  | 0.54736 | 0 | 0.28845 | 0.2589 | 0.33333 | 90.6667 | 5976.4161 | 1.6421
|  | 0.54694 | 0.54694 | 0 | 0 | 0 | 176.8333 | 6606.1397 | #DIV/0!
|  | 0.54595 | 0.54595 | 0 | 0 | 0.33333 | 107.1667 | 4709.7983 | 1.6379
|  | 0.54534 | 0.54534 | 0 | 0 | 0 | 154.6667 | 5778.0373 | #DIV/0!
|  | 0.54378 | 0.27263 | 0 | 0.27115 | 0.33333 | 137.3333 | 4738 | 1.6313
|  | 0.54324 | 0.27046 | 0.00089757 | 0.27188 | 0.16667 | 142.3333 | 6120.4988 | 3.2594
|  | 0.54221 | 0.54221 | 0 | 0 | 0.33333 | 308.1667 | 6581.858 | 1.6266
|  | 0.54085 | 0.54085 | 0 | 0 | 0.33333 | 112.3333 | 5841.3333 | 1.6226
|  | 0.53889 | 0.26904 | 0 | 0.26985 | 0.16667 | 157.8333 | 5373.3135 | 3.2333
|  | 0.53856 | 0.53856 | 0 | 0 | 0 | 171.1667 | 6394.4443 | #DIV/0!
|  | 0.53854 | 0 | 0.53854 | 0 | 0 | 169 | 7102.4035 | #DIV/0!
|  | 0.53802 | 0 | 0.00044878 | 0.53757 | 0 | 151.1667 | 6722.0138 | #DIV/0!
|  | 0.53778 | 0 | 0.26362 | 0.27415 | 0.16667 | 31.1667 | 1216.4117 | 3.2267
|  | 0.53741 | 0.53741 | 0 | 0 | 1.1667 | 97.6667 | 3755.679 | 0.46063
|  | 0.53719 | 0 | 0.53719 | 0 | 0 | 132.1667 | 5554.4437 | #DIV/0!
|  | 0.53616 | 0.2691 | 0 | 0.26705 | 0.16667 | 130 | 6240 | 3.2169
|  | 0.53613 | 0.26735 | 0 | 0.26878 | 0.16667 | 149.5 | 6578.2351 | 3.2168
|  | 0.53611 | 0.27116 | 0.00044878 | 0.26449 | 1.6667 | 160.6667 | 6093.2395 | 0.32166
|  | 0.53475 | 0.26692 | 0.00089757 | 0.26692 | 0.66667 | 163.1667 | 5724.671 | 0.80212
|  | 0.5344 | 0.5344 | 0 | 0 | 0.5 | 147.1667 | 5249.2263 | 1.0688
|  | 0.53103 | 0.53103 | 0 | 0 | 0.16667 | 147.1667 | 5006.465 | 3.1862
|  | 0.53053 | 0 | 0.52104 | 0.0094977 | 0 | 113.5 | 4775.6605 | #DIV/0!
|  | 0.53049 | 0.53049 | 0 | 0 | 0.16667 | 163.3333 | 5639.522 | 3.1829
|  | 0.53013 | 0 | 0.0053854 | 0.52475 | 0 | 118.3333 | 5257.4259 | #DIV/0!
|  | 0.52915 | 0.21571 | 0 | 0.31344 | 0.66667 | 123 | 6186.6667 | 0.79372
|  | 0.5286 | 0.26517 | 0 | 0.26343 | 0.83333 | 162.3333 | 4889.9018 | 0.63432
|  | 0.52779 | 0.52779 | 0 | 0 | 0 | 140 | 5230.12 | #DIV/0!
|  | 0.52633 | 0.26317 | 0 | 0.26317 | 0.33333 | 97.3333 | 4915.3333 | 1.579
|  | 0.52619 | 0.52619 | 0 | 0 | 0 | 147.8333 | 5522.7577 | #DIV/0!
|  | 0.52579 | 0.52579 | 0 | 0 | 0.5 | 163.1667 | 5854.1667 | 1.0516
|  | 0.52531 | 0.015548 | 0.2521 | 0.25766 | 0.33333 | 111.6667 | 5806.6667 | 1.5759
|  | 0.52508 | 0 | 0.52508 | 0 | 0 | 110.6667 | 4650.8835 | #DIV/0!
|  | 0.52431 | 0.52431 | 0 | 0 | 0.83333 | 167.3333 | 6405.5217 | 0.62918
|  | 0.523 | 0.523 | 0 | 0 | 0 | 134 | 5005.972 | #DIV/0!
|  | 0.51859 | 0.51859 | 0 | 0 | 0.16667 | 128.1667 | 4870.1193 | 3.1115
|  | 0.51762 | 0 | 0 | 0.51762 | 0 | 130.5 | 5803.3691 | #DIV/0!
|  | 0.51586 | 0.51586 | 0 | 0 | 0.33333 | 72.1667 | 4354.5123 | 1.5476
|  | 0.51572 | 0 | 0 | 0.51572 | 0 | 123.6667 | 5499.489 | #DIV/0!
|  | 0.51517 | 0.00039893 | 0 | 0.51477 | 0 | 136.3333 | 6061.5936 | #DIV/0!
|  | 0.51251 | 0 | 0.51251 | 0 | 0 | 85 | 3572.2148 | #DIV/0!
|  | 0.51223 | 0.51223 | 0 | 0 | 0 | 162 | 6051.996 | #DIV/0!
|  | 0.51193 | 0.25589 | 0 | 0.25604 | 0.16667 | 227.3333 | 7049.5784 | 3.0716
|  | 0.50984 | 0.50984 | 0 | 0 | 0 | 171.6667 | 6413.1233 | #DIV/0!
|  | 0.50955 | 0 | 0 | 0.50955 | 0 | 102.3333 | 4550.7901 | #DIV/0!
|  | 0.50954 | 0.25556 | 0 | 0.25398 | 0.83333 | 169.3333 | 6537.245 | 0.61145
|  | 0.5087 | 0.5087 | 0 | 0 | 0.16667 | 102.8333 | 3500.8107 | 3.0522
|  | 0.50832 | 0.50832 | 0 | 0 | 0.83333 | 115.8333 | 2849.5 | 0.60998
|  | 0.507 | 0.25139 | 0.004229 | 0.25139 | 0.83333 | 143.5 | 5081.0043 | 0.6084
|  | 0.50661 | 0.50661 | 0 | 0 | 1.1667 | 178.6667 | 6838.9527 | 0.43424
|  | 0.50623 | 0 | 0.50623 | 0 | 0 | 70.6667 | 2969.8413 | #DIV/0!
|  | 0.5054 | 0.2527 | 0 | 0.2527 | 0.33333 | 120.6667 | 5249 | 1.5162
|  | 0.50528 | 0.010924 | 0 | 0.49436 | 0.16667 | 105.6667 | 4591.2622 | 3.0317
|  | 0.50467 | 0 | 0.24839 | 0.25629 | 0.33333 | 138.5 | 5955.9932 | 1.514
|  | 0.5026 | 0.25132 | 0.00044878 | 0.25083 | 0.16667 | 102.3333 | 4604.3278 | 3.0156
|  | 0.50247 | 0.25101 | 0.00044878 | 0.25101 | 0.5 | 167.1667 | 5761.0043 | 1.0049
|  | 0.50185 | 0.50185 | 0 | 0 | 0.33333 | 159.8333 | 5474.967 | 1.5055
|  | 0.50146 | 0.50146 | 0 | 0 | 0 | 140.5 | 5248.799 | #DIV/0!
|  | 0.50145 | 0 | 0.00044878 | 0.501 | 0 | 152.5 | 6781.3075 | #DIV/0!
|  | 0.50106 | 0.50106 | 0 | 0 | 0 | 131 | 4893.898 | #DIV/0!
|  | 0.50053 | 0 | 0 | 0.50053 | 0 | 120.8333 | 5373.4899 | #DIV/0!
|  | 0.49878 | 0.49878 | 0 | 0 | 1.1667 | 54.8333 | 2136.9527 | 0.42752
|  | 0.49852 | 0.00039893 | 0.12297 | 0.37516 | 0 | 146.6667 | 6431.4988 | #DIV/0!
|  | 0.49747 | 0.49747 | 0 | 0 | 0 | 171.3333 | 6400.6707 | #DIV/0!
|  | 0.49743 | 0 | 0.32267 | 0.17476 | 0 | 106.5 | 4595.9484 | #DIV/0!
|  | 0.49716 | 0.49716 | 0 | 0 | 1 | 134 | 5047.3333 | 0.49716
|  | 0.49665 | 0.022372 | 0 | 0.47428 | 1.5 | 118.5 | 5516.8333 | 0.3311
|  | 0.49653 | 0 | 0.47706 | 0.01947 | 0 | 167.1667 | 7041.6504 | #DIV/0!
|  | 0.49627 | 0.012216 | 0.23878 | 0.24528 | 0.33333 | 106.8333 | 5554.0784 | 1.4888
|  | 0.49607 | 0.24798 | 0 | 0.24809 | 0.16667 | 128.6667 | 4376.4117 | 2.9764
|  | 0.49561 | 0.24794 | 0 | 0.24767 | 0.33333 | 273.3333 | 5201.8234 | 1.4868
|  | 0.49518 | 0.24789 | 0 | 0.24729 | 0.83333 | 172.8333 | 5051.8234 | 0.59422
|  | 0.49439 | 0.20973 | 0.074452 | 0.2102 | 0.5 | 144.8333 | 6080.745 | 0.98877
|  | 0.49424 | 0.16492 | 0.16345 | 0.16587 | 0.16667 | 132.3333 | 5821.8364 | 2.9654
|  | 0.49423 | 0.49423 | 0 | 0 | 0.16667 | 167.5 | 5930.305 | 2.9654
|  | 0.49338 | 0 | 0.00044878 | 0.49293 | 0 | 113.3333 | 5039.5556 | #DIV/0!
|  | 0.49158 | 0.49158 | 0 | 0 | 1.6667 | 223.8333 | 6317.5597 | 0.29495
|  | 0.49098 | 0 | 0.30351 | 0.18747 | 0.33333 | 78.5 | 5177.0043 | 1.473
|  | 0.49067 | 0.2451 | 0 | 0.24557 | 0.33333 | 111.5 | 4238.0784 | 1.472
|  | 0.49055 | 0 | 0 | 0.49055 | 0 | 131.3333 | 5840.4277 | #DIV/0!
|  | 0.49052 | 0 | 0.49052 | 0 | 0 | 154.5 | 6493.0257 | #DIV/0!
|  | 0.49027 | 0 | 0.26613 | 0.22415 | 0 | 112.6667 | 4854.7017 | #DIV/0!
|  | 0.48995 | 0 | 0.12476 | 0.36519 | 0 | 107.1667 | 4686.7004 | #DIV/0!
|  | 0.48937 | 0.24326 | 0 | 0.24611 | 0.16667 | 132.8333 | 4525.0586 | 2.9362
|  | 0.48917 | 0 | 0.48917 | 0 | 0 | 131.5 | 5526.4264 | #DIV/0!
|  | 0.48872 | 0 | 0.48872 | 0 | 0 | 108.8333 | 4573.8358 | #DIV/0!
|  | 0.48861 | 0.24431 | 0 | 0.24431 | 1.8333 | 179.6667 | 6027 | 0.26652
|  | 0.48765 | 0.24383 | 0 | 0.24383 | 0.83333 | 146.6667 | 5192 | 0.58518
|  | 0.4875 | 0.4875 | 0 | 0 | 1 | 140 | 5273.3333 | 0.4875
|  | 0.48738 | 0 | 0.48738 | 0 | 0 | 127.8333 | 5372.3308 | #DIV/0!
|  | 0.48738 | 0 | 0.48738 | 0 | 0 | 101.8333 | 4279.6534 | #DIV/0!
|  | 0.4871 | 0.4871 | 0 | 0 | 0 | 161.6667 | 6039.5433 | #DIV/0!
|  | 0.4871 | 0.4871 | 0 | 0 | 0 | 136.8333 | 5111.8197 | #DIV/0!
|  | 0.48678 | 0.24315 | 0 | 0.24363 | 0.33333 | 116.8333 | 4032.4117 | 1.4603
|  | 0.48533 | 0 | 0 | 0.48533 | 0 | 114 | 5069.6098 | #DIV/0!
|  | 0.4851 | 0.4851 | 0 | 0 | 0 | 144.5 | 5398.231 | #DIV/0!
|  | 0.48469 | 0 | 0.48469 | 0 | 0 | 109 | 4580.8401 | #DIV/0!
|  | 0.48431 | 0.48431 | 0 | 0 | 0.66667 | 177 | 6326.1193 | 0.72646
|  | 0.48424 | 0 | 0.48424 | 0 | 0 | 130.6667 | 5491.4047 | #DIV/0!
|  | 0.48255 | 0.1621 | 0.15787 | 0.16258 | 0.16667 | 126.8333 | 5580.745 | 2.8953
|  | 0.48154 | 0 | 0.48154 | 0 | 0 | 112.6667 | 4734.9356 | #DIV/0!
|  | 0.48151 | 0.48151 | 0 | 0 | 0 | 148.8333 | 5560.1157 | #DIV/0!
|  | 0.48134 | 0.24021 | 0.00044878 | 0.24068 | 0.33333 | 107.6667 | 3717.4161 | 1.444
|  | 0.4805 | 0.16142 | 0.15813 | 0.16095 | 0.33333 | 123.6667 | 5569.3333 | 1.4415
|  | 0.48032 | 0.48032 | 0 | 0 | 0 | 145.1667 | 5423.1363 | #DIV/0!
|  | 0.47955 | 0.47955 | 0 | 0 | 1.3333 | 140.6667 | 5528.864 | 0.35967
|  | 0.47951 | 0 | 0.23067 | 0.24884 | 0 | 115 | 4975.5751 | #DIV/0!
|  | 0.4793 | 0 | 0.4793 | 0 | 0 | 132.8333 | 5582.4611 | #DIV/0!
|  | 0.47912 | 0.47912 | 0 | 0 | 0 | 123.3333 | 4607.4867 | #DIV/0!
|  | 0.47885 | 0 | 0.47885 | 0 | 0 | 124.3333 | 5225.2396 | #DIV/0!
|  | 0.47764 | 0 | 0.31998 | 0.15766 | 0 | 104.5 | 4500.0826 | #DIV/0!
|  | 0.47764 | 0.47764 | 0 | 0 | 0.33333 | 112.3333 | 4939.3457 | 1.4329
|  | 0.47713 | 0.47713 | 0 | 0 | 0 | 156 | 5827.848 | #DIV/0!
|  | 0.47706 | 0 | 0.47706 | 0 | 0 | 96.3333 | 4048.5101 | #DIV/0!
|  | 0.47678 | 0 | 0 | 0.47678 | 0 | 110.8333 | 4928.7873 | #DIV/0!
|  | 0.47673 | 0.47673 | 0 | 0 | 0 | 142.8333 | 5335.9677 | #DIV/0!
|  | 0.47635 | 0.0070052 | 0.23292 | 0.23643 | 0.66667 | 148 | 6068 | 0.71453
|  | 0.47616 | 0 | 0.47616 | 0 | 0 | 106.3333 | 4468.7706 | #DIV/0!
|  | 0.47388 | 0.04374 | 0.3864 | 0.04374 | 0.16667 | 106.5 | 4754.1116 | 2.8433
|  | 0.47304 | 0.47304 | 0 | 0 | 1 | 138 | 4761 | 0.47304
|  | 0.47257 | 0 | 0.47257 | 0 | 0 | 113.8333 | 4783.966 | #DIV/0!
|  | 0.47238 | 0.237 | 0 | 0.23538 | 0.5 | 233.6667 | 4384.6667 | 0.94476
|  | 0.47229 | 0.47229 | 0 | 0 | 0.16667 | 123.6667 | 5563.7263 | 2.8337
|  | 0.47203 | 0 | 0 | 0.47203 | 0 | 134.6667 | 5988.6619 | #DIV/0!
|  | 0.47154 | 0.47154 | 0 | 0 | 0 | 142.5 | 5323.515 | #DIV/0!
|  | 0.47052 | 0.47052 | 0 | 0 | 0.33333 | 122.3333 | 5378.2387 | 1.4116
|  | 0.46989 | 0.46989 | 0 | 0 | 0.33333 | 118.1667 | 4402.0857 | 1.4097
|  | 0.46961 | 0.23457 | 0 | 0.23504 | 0.33333 | 93.5 | 3275.745 | 1.4088
|  | 0.46943 | 0 | 0.46943 | 0 | 0 | 133.1667 | 5596.4698 | #DIV/0!
|  | 0.46915 | 0.46915 | 0 | 0 | 0 | 132.8333 | 4962.3877 | #DIV/0!
|  | 0.46884 | 0.46884 | 0 | 0 | 0.16667 | 143.8333 | 4526.652 | 2.8131
|  | 0.46835 | 0.46835 | 0 | 0 | 0 | 147.3333 | 5504.0787 | #DIV/0!
|  | 0.46834 | 0.46834 | 0 | 0 | 0.66667 | 89.3333 | 4332.2933 | 0.70252
|  | 0.46808 | 0 | 0.46808 | 0 | 0 | 112 | 4706.9183 | #DIV/0!
|  | 0.46763 | 0 | 0.46763 | 0 | 0 | 125.3333 | 5267.2657 | #DIV/0!
|  | 0.46673 | 0 | 0.46673 | 0 | 0 | 96.8333 | 4069.5231 | #DIV/0!
|  | 0.46663 | 0.46663 | 0 | 0 | 0.33333 | 130.3333 | 4623 | 1.3999
|  | 0.466 | 0.23276 | 0 | 0.23324 | 1.5 | 181.5 | 7150.745 | 0.31067
|  | 0.46547 | 0.23226 | 0 | 0.23321 | 0.5 | 131.3333 | 5473.1568 | 0.93094
|  | 0.46396 | 0.46396 | 0 | 0 | 0 | 146.5 | 5472.947 | #DIV/0!
|  | 0.46315 | 0 | 0.013912 | 0.44924 | 0 | 80.3333 | 3562.6675 | #DIV/0!
|  | 0.46276 | 0.46276 | 0 | 0 | 0 | 144.8333 | 5410.6837 | #DIV/0!
|  | 0.46276 | 0.46276 | 0 | 0 | 0 | 134.6667 | 5030.8773 | #DIV/0!
|  | 0.46267 | 0 | 0.23083 | 0.23184 | 0.16667 | 239.6667 | 5519.0827 | 2.776
|  | 0.46077 | 0.46077 | 0 | 0 | 0 | 132.6667 | 4956.1613 | #DIV/0!
|  | 0.46072 | 0.46072 | 0 | 0 | 0.33333 | 99.8333 | 4389.3457 | 1.3822
|  | 0.45917 | 0.45917 | 0 | 0 | 0 | 92.6667 | 3461.8413 | #DIV/0!
|  | 0.45826 | 0 | 0 | 0.45826 | 0 | 119.1667 | 5299.3728 | #DIV/0!
|  | 0.45725 | 0.45725 | 0 | 0 | 0.33333 | 72.5 | 3767.5597 | 1.3717
|  | 0.45718 | 0.00039893 | 0.00089757 | 0.45589 | 0 | 102.3333 | 4548.79 | #DIV/0!
|  | 0.45686 | 0.45686 | 0 | 0 | 0.16667 | 140.3333 | 4773.0123 | 2.7411
|  | 0.45684 | 0 | 0 | 0.45684 | 0 | 131.1667 | 5833.016 | #DIV/0!
|  | 0.45641 | 0 | 0.45641 | 0 | 0 | 136.6667 | 5743.561 | #DIV/0!
|  | 0.45602 | 0.45602 | 0 | 0 | 0.16667 | 122.1667 | 4153.6667 | 2.7361
|  | 0.45541 | 0 | 0 | 0.45541 | 0 | 83.8333 | 3728.0903 | #DIV/0!
|  | 0.45459 | 0.2273 | 0 | 0.2273 | 2 | 136 | 5610 | 0.2273
|  | 0.45417 | 0 | 0.45417 | 0 | 0 | 86.1667 | 3621.2452 | #DIV/0!
|  | 0.45363 | 0.22682 | 0 | 0.22682 | 0.83333 | 116.6667 | 4130 | 0.54436
|  | 0.45359 | 0.45359 | 0 | 0 | 0 | 122.8333 | 4588.8077 | #DIV/0!
|  | 0.45339 | 0.00039893 | 0.00089757 | 0.45209 | 0 | 103.3333 | 4593.2602 | #DIV/0!
|  | 0.45263 | 0.020183 | 0.40705 | 0.025401 | 0.16667 | 103.8333 | 4407.7508 | 2.7158
|  | 0.45184 | 0.45184 | 0 | 0 | 1.1667 | 158.6667 | 5848 | 0.38729
|  | 0.45159 | 0.45159 | 0 | 0 | 0 | 104.1667 | 3891.4583 | #DIV/0!
|  | 0.4504 | 0.4504 | 0 | 0 | 0 | 148.3333 | 5541.4367 | #DIV/0!
|  | 0.45035 | 0.0016232 | 0 | 0.44873 | 0.33333 | 194 | 3719.9603 | 1.351
|  | 0.45019 | 0 | 0 | 0.45019 | 0 | 105.5 | 4691.6126 | #DIV/0!
|  | 0.45002 | 0.22561 | 0 | 0.22441 | 0.33333 | 54.1667 | 1946.6667 | 1.3501
|  | 0.44923 | 0 | 0.44923 | 0 | 0 | 115.6667 | 4861.0138 | #DIV/0!
|  | 0.4484 | 0.4484 | 0 | 0 | 0 | 132.5 | 4949.935 | #DIV/0!
|  | 0.44833 | 0 | 0.44833 | 0 | 0 | 116.1667 | 4882.0268 | #DIV/0!
|  | 0.44811 | 0 | 0.21795 | 0.23016 | 1.1667 | 57.3333 | 1289.5784 | 0.3841
|  | 0.44719 | 0.015548 | 0.00089757 | 0.43075 | 0.33333 | 92.6667 | 4812.8321 | 1.3416
|  | 0.44698 | 0.22551 | 0 | 0.22147 | 2.3333 | 177 | 6723.5 | 0.19156
|  | 0.44625 | 0.44625 | 0 | 0 | 0.16667 | 169.5 | 5774.753 | 2.6775
|  | 0.44541 | 0 | 0.00044878 | 0.44497 | 0 | 115.6667 | 5143.3195 | #DIV/0!
|  | 0.44482 | 0.44482 | 0 | 0 | 0.66667 | 134.1667 | 5165.2263 | 0.66723
|  | 0.44409 | 0.22295 | 0 | 0.22114 | 0.83333 | 177 | 5172.5784 | 0.53291
|  | 0.44402 | 0 | 0 | 0.44402 | 0 | 124.3333 | 5529.1359 | #DIV/0!
|  | 0.44361 | 0.44361 | 0 | 0 | 0 | 134.1667 | 5012.1983 | #DIV/0!
|  | 0.44354 | 0 | 0 | 0.44354 | 0 | 78.8333 | 3505.739 | #DIV/0!
|  | 0.44322 | 0.44322 | 0 | 0 | 0 | 146.1667 | 5460.4943 | #DIV/0!
|  | 0.4425 | 0.22125 | 0 | 0.22125 | 2.1667 | 91.3333 | 4246.3333 | 0.20423
|  | 0.44225 | 0.22089 | 0 | 0.22136 | 0.66667 | 135.1667 | 5003.0784 | 0.66338
|  | 0.44202 | 0.44202 | 0 | 0 | 0 | 151.3333 | 5653.5107 | #DIV/0!
|  | 0.4416 | 0 | 0.4416 | 0 | 0 | 134.3333 | 5645.5002 | #DIV/0!
|  | 0.44148 | 0.44148 | 0 | 0 | 0.16667 | 166.8333 | 5175.0123 | 2.6489
|  | 0.44082 | 0.44082 | 0 | 0 | 0 | 109.5 | 4090.701 | #DIV/0!
|  | 0.44042 | 0.44042 | 0 | 0 | 0 | 152.6667 | 5703.3213 | #DIV/0!
|  | 0.44013 | 0.44013 | 0 | 0 | 1 | 122 | 4554.6667 | 0.44013
|  | 0.44002 | 0.44002 | 0 | 0 | 0 | 98.5 | 3679.763 | #DIV/0!
|  | 0.43997 | 0.2193 | 0.14168 | 0.078983 | 0.16667 | 131.6667 | 4483.2395 | 2.6398
|  | 0.4399 | 0.4399 | 0 | 0 | 1.5 | 211.6667 | 6327.7263 | 0.29327
|  | 0.4396 | 0.21929 | 0 | 0.22032 | 0.16667 | 127.6667 | 4727.4018 | 2.6376
|  | 0.43939 | 0.43939 | 0 | 0 | 0.16667 | 136.8333 | 4653.4527 | 2.6364
|  | 0.43936 | 0.0033317 | 0.37828 | 0.05775 | 0.33333 | 78.6667 | 4084.0174 | 1.3181
|  | 0.43927 | 0 | 0 | 0.43927 | 0 | 129.6667 | 5766.3106 | #DIV/0!
|  | 0.43803 | 0.43803 | 0 | 0 | 0 | 147.5 | 5510.305 | #DIV/0!
|  | 0.43803 | 0.43803 | 0 | 0 | 0 | 106.5 | 3978.627 | #DIV/0!
|  | 0.43774 | 0.21887 | 0 | 0.21887 | 0.66667 | 100 | 4575 | 0.65661
|  | 0.43684 | 0.43684 | 0 | 0 | 1.5 | 66.5 | 2952.893 | 0.29122
|  | 0.43603 | 0.43603 | 0 | 0 | 0 | 141.5 | 5286.157 | #DIV/0!
|  | 0.43462 | 0.21889 | 0 | 0.21573 | 0.16667 | 160 | 5920 | 2.6077
|  | 0.43424 | 0.0088847 | 0 | 0.42535 | 0.33333 | 88.6667 | 4610.6667 | 1.3027
|  | 0.43397 | 0 | 0.43397 | 0 | 0 | 117.3333 | 4931.0572 | #DIV/0!
|  | 0.43352 | 0 | 0.43352 | 0 | 0 | 116.6667 | 4903.0399 | #DIV/0!
|  | 0.433 | 0.19324 | 0.046516 | 0.19324 | 2.1667 | 125 | 4041 | 0.19985
|  | 0.43205 | 0.43205 | 0 | 0 | 0 | 90.3333 | 3374.6727 | #DIV/0!
|  | 0.43173 | 0 | 0.43173 | 0 | 0 | 120.1667 | 5050.1311 | #DIV/0!
|  | 0.43128 | 0 | 0.43128 | 0 | 0 | 111.3333 | 4678.9009 | #DIV/0!
|  | 0.43085 | 0.43085 | 0 | 0 | 0 | 146.1667 | 5460.4943 | #DIV/0!
|  | 0.43005 | 0.43005 | 0 | 0 | 0 | 124.6667 | 4657.2973 | #DIV/0!
|  | 0.42946 | 0.21418 | 0 | 0.21528 | 0.16667 | 138.6667 | 4305.4018 | 2.5767
|  | 0.42859 | 0 | 0.42859 | 0 | 0 | 134.5 | 5652.5045 | #DIV/0!
|  | 0.42831 | 0.21368 | 0 | 0.21463 | 0.33333 | 131.5 | 5720.4117 | 1.2849
|  | 0.4282 | 0.21323 | 0 | 0.21497 | 0.66667 | 151.1667 | 4842.3234 | 0.64231
|  | 0.42819 | 0.2141 | 0 | 0.2141 | 0.5 | 133 | 5453 | 0.85639
|  | 0.42782 | 0 | 0.00089757 | 0.42692 | 0 | 103.6667 | 4609.269 | #DIV/0!
|  | 0.42606 | 0.42606 | 0 | 0 | 0 | 128.8333 | 4812.9557 | #DIV/0!
|  | 0.42584 | 0.00039893 | 0.00089757 | 0.42455 | 0 | 72.5 | 3222.5012 | #DIV/0!
|  | 0.42545 | 0 | 0.42545 | 0 | 0 | 105.3333 | 4426.7446 | #DIV/0!
|  | 0.42502 | 0 | 0 | 0.42502 | 0 | 82.6667 | 3676.2083 | #DIV/0!
|  | 0.42455 | 0 | 0.42455 | 0 | 0 | 125.3333 | 5267.2657 | #DIV/0!
|  | 0.42409 | 0.42409 | 0 | 0 | 0.33333 | 111 | 4051.786 | 1.2723
|  | 0.42331 | 0.14064 | 0.14719 | 0.13548 | 1.6667 | 79 | 3468 | 0.25399
|  | 0.42275 | 0 | 0.42275 | 0 | 0 | 116.3333 | 4889.0312 | #DIV/0!
|  | 0.42241 | 0.12571 | 0.17099 | 0.12571 | 0.66667 | 119.8333 | 4306.0813 | 0.63361
|  | 0.42159 | 0.2108 | 0 | 0.2108 | 1.8333 | 102.6667 | 4386.6667 | 0.22996
|  | 0.42127 | 0.42127 | 0 | 0 | 0 | 124.1667 | 4638.6183 | #DIV/0!
|  | 0.4205 | 0 | 0.061483 | 0.35901 | 0 | 86 | 3772.7068 | #DIV/0!
|  | 0.4179 | 0 | 0 | 0.4179 | 0 | 109.3333 | 4862.0819 | #DIV/0!
|  | 0.41766 | 0.41766 | 0 | 0 | 1.3333 | 141.1667 | 5607.4527 | 0.31325
|  | 0.41552 | 0.20788 | 0.00044878 | 0.20719 | 1.1667 | 98.8333 | 3537.4061 | 0.35616
|  | 0.41454 | 0.012985 | 0.00089757 | 0.40066 | 0.33333 | 206 | 3938.6555 | 1.2436
|  | 0.41401 | 0 | 0.2043 | 0.2097 | 0.16667 | 247.8333 | 5714.0728 | 2.484
|  | 0.41376 | 0.20688 | 0 | 0.20688 | 1.8333 | 148 | 5802.6667 | 0.22569
|  | 0.4133 | 0.4133 | 0 | 0 | 0 | 128.5 | 4800.503 | #DIV/0!
|  | 0.41315 | 0.41315 | 0 | 0 | 0.16667 | 137.8333 | 4277.072 | 2.4789
|  | 0.41252 | 0.13739 | 0.13502 | 0.1401 | 1.3333 | 156 | 6086.6667 | 0.30939
|  | 0.4121 | 0.4121 | 0 | 0 | 0 | 109 | 4072.022 | #DIV/0!
|  | 0.4117 | 0 | 0.00044878 | 0.41125 | 0 | 99.5 | 4424.3837 | #DIV/0!
|  | 0.4116 | 0 | 0.20298 | 0.20862 | 0.33333 | 68.6667 | 4532 | 1.2348
|  | 0.41125 | 0 | 0 | 0.41125 | 0 | 100.3333 | 4461.8496 | #DIV/0!
|  | 0.4112 | 0.4112 | 0 | 0 | 0.16667 | 104.6667 | 3862.006 | 2.4672
|  | 0.41056 | 0.41056 | 0 | 0 | 0.83333 | 142.6667 | 5050.7263 | 0.49267
|  | 0.4105 | 0.4105 | 0 | 0 | 0 | 129.1667 | 4825.4083 | #DIV/0!
|  | 0.4101 | 0.4101 | 0 | 0 | 0 | 119.5 | 4464.281 | #DIV/0!
|  | 0.40991 | 0.20623 | 0 | 0.20369 | 0.16667 | 118.6667 | 4034.6667 | 2.4595
|  | 0.40983 | 0.20468 | 0 | 0.20515 | 0.66667 | 140.5 | 5240.0784 | 0.61475
|  | 0.40981 | 0.20512 | 0 | 0.20469 | 0.66667 | 143.3333 | 3930.0784 | 0.61472
|  | 0.40971 | 0.40971 | 0 | 0 | 0 | 91 | 3399.578 | #DIV/0!
|  | 0.40929 | 0 | 0.40929 | 0 | 0 | 117.1667 | 4924.0529 | #DIV/0!
|  | 0.40746 | 0 | 0.19869 | 0.20877 | 0.16667 | 106.6667 | 4162.3278 | 2.4447
|  | 0.40603 | 0 | 0 | 0.40603 | 0 | 68.6667 | 3053.6246 | #DIV/0!
|  | 0.40518 | 0.19951 | 0.0030651 | 0.2026 | 0.83333 | 82.6667 | 3821.0827 | 0.48621
|  | 0.40508 | 0 | 0 | 0.40508 | 0 | 70.8333 | 3149.9769 | #DIV/0!
|  | 0.40462 | 0.40462 | 0 | 0 | 0.16667 | 96.6667 | 4350 | 2.4277
|  | 0.40385 | 0 | 0.19253 | 0.21132 | 0 | 105.8333 | 4580.1521 | #DIV/0!
|  | 0.40355 | 0.00039893 | 0.00044878 | 0.4027 | 0 | 109.5 | 4867.9009 | #DIV/0!
|  | 0.40332 | 0.40332 | 0 | 0 | 0 | 146.5 | 5472.947 | #DIV/0!
|  | 0.40256 | 0 | 0.40256 | 0 | 0 | 90.1667 | 3789.3494 | #DIV/0!
|  | 0.40231 | 0.20115 | 0 | 0.20115 | 0.66667 | 116 | 4669 | 0.60346
|  | 0.40173 | 0.40173 | 0 | 0 | 0 | 102 | 3810.516 | #DIV/0!
|  | 0.40166 | 0.0033317 | 0.19747 | 0.20085 | 0.33333 | 93.3333 | 4847.4988 | 1.205
|  | 0.40126 | 0.20063 | 0 | 0.20063 | 0.5 | 48 | 2378 | 0.80252
|  | 0.39973 | 0 | 0.149 | 0.25074 | 0 | 115.5 | 5027.1407 | #DIV/0!
|  | 0.3996 | 0.3996 | 0 | 0 | 0.16667 | 124.6667 | 4241.465 | 2.3976
|  | 0.39852 | 0 | 0.39852 | 0 | 0 | 98.1667 | 4125.5578 | #DIV/0!
|  | 0.3975 | 0.3975 | 0 | 0 | 0.33333 | 104.6667 | 4605.3333 | 1.1925
|  | 0.39748 | 0 | 0 | 0.39748 | 0 | 91.1667 | 4054.2055 | #DIV/0!
|  | 0.39738 | 0.19845 | 0 | 0.19893 | 0.33333 | 78.8333 | 3980.0784 | 1.1921
|  | 0.3959 | 0.3959 | 0 | 0 | 0.16667 | 82.1667 | 3287.7397 | 2.3754
|  | 0.39583 | 0 | 0.39583 | 0 | 0 | 109.6667 | 4608.8575 | #DIV/0!
|  | 0.39538 | 0 | 0.39538 | 0 | 0 | 100.5 | 4223.6186 | #DIV/0!
|  | 0.39494 | 0.39494 | 0 | 0 | 0 | 132.5 | 4949.935 | #DIV/0!
|  | 0.39455 | 0.39455 | 0 | 0 | 0 | 126.6667 | 4732.0133 | #DIV/0!
|  | 0.39445 | 0.39445 | 0 | 0 | 2.1667 | 159.8333 | 3939 | 0.18205
|  | 0.39368 | 0 | 0 | 0.39368 | 0 | 96.1667 | 4276.5568 | #DIV/0!
|  | 0.39342 | 0.39342 | 0 | 0 | 1.1667 | 56 | 2704 | 0.33722
|  | 0.39331 | 0.39331 | 0 | 0 | 0.16667 | 221.8333 | 4672.1317 | 2.3599
|  | 0.39295 | 0.39295 | 0 | 0 | 0 | 101.5 | 3791.837 | #DIV/0!
|  | 0.39215 | 0.39215 | 0 | 0 | 0 | 92.6667 | 3461.8413 | #DIV/0!
|  | 0.39183 | 0.39183 | 0 | 0 | 0.16667 | 121.3333 | 4126.4527 | 2.351
|  | 0.39141 | 0.19499 | 0 | 0.19642 | 0.16667 | 109 | 4796.1568 | 2.3485
|  | 0.39135 | 0.39135 | 0 | 0 | 0 | 125.5 | 4688.429 | #DIV/0!
|  | 0.39044 | 0 | 0.39044 | 0 | 0 | 110.1667 | 4629.8705 | #DIV/0!
|  | 0.38976 | 0.38976 | 0 | 0 | 0 | 133.5 | 4987.293 | #DIV/0!
|  | 0.38954 | 0 | 0.38954 | 0 | 0 | 94.3333 | 3964.458 | #DIV/0!
|  | 0.3894 | 0 | 0 | 0.3894 | 0 | 83.5 | 3713.2668 | #DIV/0!
|  | 0.38876 | 0.38876 | 0 | 0 | 1.1667 | 138.1667 | 3598.0123 | 0.33322
|  | 0.38843 | 0 | 0.00044878 | 0.38798 | 0 | 73.5 | 3268.1569 | #DIV/0!
|  | 0.3882 | 0 | 0.3882 | 0 | 0 | 82.6667 | 3474.154 | #DIV/0!
|  | 0.38776 | 0.38776 | 0 | 0 | 0 | 120.6667 | 4507.8653 | #DIV/0!
|  | 0.38751 | 0.19375 | 0 | 0.19375 | 0.66667 | 112 | 4704 | 0.58126
|  | 0.38713 | 0.38713 | 0 | 0 | 0.16667 | 123 | 4596.3077 | 2.3228
|  | 0.38574 | 0.38574 | 0 | 0 | 0.16667 | 86 | 3358.912 | 2.3144
|  | 0.3855 | 0 | 0.3855 | 0 | 0 | 111.8333 | 4699.9139 | #DIV/0!
|  | 0.38544 | 0.38544 | 0 | 0 | 1.5 | 119 | 4739.286 | 0.25696
|  | 0.38475 | 0.38475 | 0 | 0 | 0.33333 | 97.3333 | 4281.5597 | 1.1542
|  | 0.38457 | 0.38457 | 0 | 0 | 0 | 103.6667 | 3872.7793 | #DIV/0!
|  | 0.38421 | 0.38421 | 0 | 0 | 1.5 | 156.5 | 4771.5 | 0.25614
|  | 0.38401 | 0.19255 | 0 | 0.19146 | 0.33333 | 62.1667 | 2270.4117 | 1.152
|  | 0.38371 | 0 | 0 | 0.38371 | 0 | 99.8333 | 4439.6144 | #DIV/0!
|  | 0.38347 | 0.38347 | 0 | 0 | 0.83333 | 120 | 4560 | 0.46017
|  | 0.38258 | 0.38258 | 0 | 0 | 0 | 98 | 3661.084 | #DIV/0!
|  | 0.38232 | 0.38232 | 0 | 0 | 0.16667 | 172.6667 | 3305.144 | 2.2939
|  | 0.38218 | 0.38218 | 0 | 0 | 0 | 105.6667 | 3947.4953 | #DIV/0!
|  | 0.38133 | 0 | 0 | 0.38133 | 0 | 101.1667 | 4498.9081 | #DIV/0!
|  | 0.3808 | 0 | 0.00089757 | 0.37991 | 0 | 85 | 3779.5649 | #DIV/0!
|  | 0.38055 | 0.18928 | 0 | 0.19126 | 0.16667 | 98.8333 | 4347.9516 | 2.2833
|  | 0.38038 | 0 | 0 | 0.38038 | 0 | 98.6667 | 4387.7325 | #DIV/0!
|  | 0.38018 | 0.38018 | 0 | 0 | 0 | 108.8333 | 4065.7957 | #DIV/0!
|  | 0.38012 | 0 | 0.38012 | 0 | 0 | 102.8333 | 4321.6794 | #DIV/0!
|  | 0.38012 | 0 | 0.38012 | 0 | 0 | 83.8333 | 3523.1844 | #DIV/0!
|  | 0.38012 | 0 | 0.38012 | 0 | 0 | 65.1667 | 2738.698 | #DIV/0!
|  | 0.37965 | 0.18982 | 0 | 0.18982 | 0.33333 | 92 | 4646 | 1.1389
|  | 0.37839 | 0.37839 | 0 | 0 | 0.16667 | 140.6667 | 2675.7263 | 2.2703
|  | 0.37739 | 0.37739 | 0 | 0 | 0 | 124.1667 | 4638.6183 | #DIV/0!
|  | 0.37666 | 0.37666 | 0 | 0 | 0.16667 | 104.8333 | 4716.2263 | 2.26
|  | 0.37611 | 0.37611 | 0 | 0 | 0.16667 | 125 | 4522.5577 | 2.2567
|  | 0.37611 | 0 | 0 | 0.37611 | 0 | 80.5 | 3579.8561 | #DIV/0!
|  | 0.37608 | 0 | 0.37608 | 0 | 0 | 106 | 4454.7619 | #DIV/0!
|  | 0.37477 | 0.37477 | 0 | 0 | 0.16667 | 95.8333 | 3259.4527 | 2.2486
|  | 0.37473 | 0 | 0.37473 | 0 | 0 | 71 | 2983.85 | #DIV/0!
|  | 0.3746 | 0.3746 | 0 | 0 | 0 | 74.6667 | 2789.3973 | #DIV/0!
|  | 0.37339 | 0 | 0.37339 | 0 | 0 | 109 | 4580.8401 | #DIV/0!
|  | 0.37314 | 0.37314 | 0 | 0 | 0.16667 | 106 | 4766.179 | 2.2388
|  | 0.37312 | 0.016766 | 0.17146 | 0.1849 | 1.1667 | 215 | 4829.0827 | 0.31982
|  | 0.37237 | 0 | 0.35005 | 0.02232 | 0 | 116.8333 | 4924.3021 | #DIV/0!
|  | 0.37186 | 0.01999 | 0.0026699 | 0.3492 | 0.33333 | 90 | 4677.0827 | 1.1156
|  | 0.37184 | 0.18568 | 0 | 0.18616 | 0.33333 | 94.1667 | 3955.4117 | 1.1155
|  | 0.37136 | 0 | 0 | 0.37136 | 0 | 81.3333 | 3616.9146 | #DIV/0!
|  | 0.37134 | 0.37134 | 0 | 0 | 1.3333 | 86.6667 | 3768.8333 | 0.27851
|  | 0.37114 | 0 | 0.37114 | 0 | 0 | 104.5 | 4391.7229 | #DIV/0!
|  | 0.37101 | 0.37101 | 0 | 0 | 0 | 89.5 | 3343.541 | #DIV/0!
|  | 0.37021 | 0.37021 | 0 | 0 | 0 | 120.3333 | 4495.4127 | #DIV/0!
|  | 0.36934 | 0.18504 | 0 | 0.1843 | 0.33333 | 144.5 | 2749.745 | 1.108
|  | 0.36862 | 0.36862 | 0 | 0 | 0 | 107 | 3997.306 | #DIV/0!
|  | 0.36862 | 0.36862 | 0 | 0 | 0 | 95.3333 | 3561.4627 | #DIV/0!
|  | 0.368 | 0 | 0.368 | 0 | 0 | 76 | 3193.9803 | #DIV/0!
|  | 0.36793 | 0.36793 | 0 | 0 | 0.16667 | 91.5 | 4114.9527 | 2.2076
|  | 0.36715 | 0.36715 | 0 | 0 | 0.16667 | 221.8333 | 4680.3107 | 2.2029
|  | 0.36661 | 0 | 0 | 0.36661 | 0 | 75.8333 | 3372.3282 | #DIV/0!
|  | 0.36538 | 0.0055529 | 0.17769 | 0.18214 | 0.33333 | 87 | 4524 | 1.0961
|  | 0.36536 | 0 | 0.17866 | 0.18669 | 0.16667 | 62.8333 | 2451.4117 | 2.1922
|  | 0.36502 | 0.36502 | 0 | 0 | 0 | 123 | 4595.034 | #DIV/0!
|  | 0.364 | 0.039949 | 0.28363 | 0.040424 | 0.16667 | 113 | 4774.0249 | 2.184
|  | 0.36316 | 0.0033317 | 0.17769 | 0.18214 | 0.33333 | 31.6667 | 1646.6667 | 1.0895
|  | 0.36289 | 0.36289 | 0 | 0 | 1 | 89.1667 | 3254.786 | 0.36289
|  | 0.36288 | 0.36288 | 0 | 0 | 0.16667 | 86 | 3864.9053 | 2.1773
|  | 0.36263 | 0.36263 | 0 | 0 | 0 | 126.6667 | 4732.0133 | #DIV/0!
|  | 0.36236 | 0.183 | 0 | 0.17936 | 0.16667 | 131.1667 | 4984.2263 | 2.1742
|  | 0.36223 | 0.18392 | 0 | 0.17831 | 1.5 | 135.3333 | 5396.0784 | 0.24148
|  | 0.36209 | 0.36209 | 0 | 0 | 1 | 101.8333 | 3716.8333 | 0.36209
|  | 0.36104 | 0.36104 | 0 | 0 | 0 | 89.3333 | 3337.3147 | #DIV/0!
|  | 0.36024 | 0.36024 | 0 | 0 | 0 | 102.3333 | 3822.9687 | #DIV/0!
|  | 0.3591 | 0.17908 | 0 | 0.18002 | 0.16667 | 92 | 3956.245 | 2.1546
|  | 0.35886 | 0 | 0.17413 | 0.18473 | 0 | 96.5 | 4173.651 | #DIV/0!
|  | 0.3581 | 0.18038 | 0.00041647 | 0.1773 | 0.66667 | 101.6667 | 4167.6667 | 0.53715
|  | 0.35704 | 0.00039893 | 0 | 0.35664 | 0 | 99.5 | 4423.6056 | #DIV/0!
|  | 0.35628 | 0.17855 | 0 | 0.17774 | 0.33333 | 96.3333 | 3660.6667 | 1.0689
|  | 0.35625 | 0.35625 | 0 | 0 | 0 | 121.3333 | 4532.7707 | #DIV/0!
|  | 0.35567 | 0.35567 | 0 | 0 | 0.16667 | 195.5 | 4119.1317 | 2.134
|  | 0.35494 | 0.17747 | 0 | 0.17747 | 0.83333 | 23 | 764 | 0.42593
|  | 0.35454 | 0 | 0.35454 | 0 | 0 | 84.1667 | 3537.193 | #DIV/0!
|  | 0.35376 | 0.17688 | 0 | 0.17688 | 0.5 | 109 | 3669.6667 | 0.70753
|  | 0.35346 | 0.35346 | 0 | 0 | 0 | 85 | 3175.43 | #DIV/0!
|  | 0.35317 | 0.011106 | 0.0011106 | 0.34095 | 0.33333 | 72.3333 | 3761.3333 | 1.0595
|  | 0.3531 | 0.032196 | 0.13912 | 0.18178 | 0.16667 | 65 | 2830.4145 | 2.1186
|  | 0.35303 | 0.041914 | 0.13412 | 0.17699 | 1.1667 | 168.3333 | 3782.8234 | 0.30259
|  | 0.35266 | 0.35266 | 0 | 0 | 0 | 121.3333 | 4532.7707 | #DIV/0!
|  | 0.35237 | 0.35237 | 0 | 0 | 0.33333 | 89.5 | 3934.679 | 1.0571
|  | 0.35229 | 0 | 0.35229 | 0 | 0 | 82.6667 | 3474.154 | #DIV/0!
|  | 0.35189 | 0 | 0 | 0.35189 | 0 | 83.5 | 3713.2668 | #DIV/0!
|  | 0.35156 | 0.17578 | 0 | 0.17578 | 0.83333 | 108.3333 | 3835 | 0.42188
|  | 0.35147 | 0.17526 | 0 | 0.17621 | 0.16667 | 81 | 3564.2351 | 2.1088
|  | 0.3514 | 0 | 0.3514 | 0 | 0 | 91.8333 | 3859.3928 | #DIV/0!
|  | 0.35066 | 0.35066 | 0 | 0 | 0 | 82 | 3063.356 | #DIV/0!
|  | 0.3506 | 0.00039893 | 0.21676 | 0.13344 | 0 | 69.3333 | 2999.3905 | #DIV/0!
|  | 0.35029 | 0.17558 | 0 | 0.17471 | 0.5 | 95.3333 | 3615.745 | 0.70057
|  | 0.3501 | 0.0088847 | 0.0020081 | 0.3392 | 0.33333 | 72.5 | 3765.4204 | 1.0503
|  | 0.34987 | 0.34987 | 0 | 0 | 0 | 98.8333 | 3692.2157 | #DIV/0!
|  | 0.34985 | 0.17493 | 0 | 0.17493 | 1.1667 | 105.3333 | 4142.6667 | 0.29988
|  | 0.34983 | 0.34983 | 0 | 0 | 0.5 | 78.5 | 3140 | 0.69967
|  | 0.34981 | 0.17463 | 0 | 0.17518 | 0.33333 | 132.8333 | 4581.3333 | 1.0494
|  | 0.3496 | 0 | 0.3496 | 0 | 0 | 108 | 4538.8141 | #DIV/0!
|  | 0.34938 | 0 | 0.15752 | 0.19185 | 0 | 75.1667 | 3258.3562 | #DIV/0!
|  | 0.3491 | 0.3491 | 0 | 0 | 0.16667 | 174 | 3336.5967 | 2.0946
|  | 0.34817 | 0.0056383 | 0.16774 | 0.17479 | 0.33333 | 53 | 3498 | 1.0445
|  | 0.34776 | 0.17408 | 0.00040579 | 0.17327 | 0.33333 | 192.3333 | 3654.3333 | 1.0433
|  | 0.34747 | 0.34747 | 0 | 0 | 0 | 102 | 3810.516 | #DIV/0!
|  | 0.34746 | 0.051097 | 0 | 0.29637 | 1.3333 | 72 | 2871 | 0.2606
|  | 0.34691 | 0.1172 | 0.11251 | 0.1172 | 1.6667 | 73.3333 | 3219.3333 | 0.20814
|  | 0.34614 | 0 | 0.00089757 | 0.34524 | 0 | 81.8333 | 3638.7424 | #DIV/0!
|  | 0.34601 | 0 | 0.34601 | 0 | 0 | 69.8333 | 2934.8196 | #DIV/0!
|  | 0.34548 | 0.34548 | 0 | 0 | 0 | 101.5 | 3791.837 | #DIV/0!
|  | 0.34521 | 0 | 0.00044878 | 0.34477 | 0 | 91.5 | 4068.6216 | #DIV/0!
|  | 0.34493 | 0.34493 | 0 | 0 | 0.16667 | 58.6667 | 2428.6333 | 2.0696
|  | 0.34407 | 0.34407 | 0 | 0 | 0.16667 | 85.1667 | 3832.5 | 2.0644
|  | 0.34377 | 0 | 0.34377 | 0 | 0 | 107.6667 | 4524.8054 | #DIV/0!
|  | 0.34314 | 0.12189 | 0.098896 | 0.12236 | 1.6667 | 105.3333 | 4623.9161 | 0.20589
|  | 0.34287 | 0 | 0 | 0.34287 | 0 | 88.6667 | 3943.0299 | #DIV/0!
|  | 0.34264 | 0 | 0.10995 | 0.23269 | 0 | 103.6667 | 4522.9071 | #DIV/0!
|  | 0.34206 | 0.17103 | 0 | 0.17103 | 0.66667 | 14.6667 | 524.3333 | 0.51309
|  | 0.34197 | 0 | 0.34197 | 0 | 0 | 79.5 | 3341.0715 | #DIV/0!
|  | 0.34097 | 0 | 0 | 0.34097 | 0 | 91.5 | 4069.0289 | #DIV/0!
|  | 0.33978 | 0.16373 | 0.0099525 | 0.1661 | 1.8333 | 101.8333 | 4223.4117 | 0.18533
|  | 0.33973 | 0 | 0.33973 | 0 | 0 | 97 | 4076.5274 | #DIV/0!
|  | 0.33949 | 0.33949 | 0 | 0 | 0 | 104.6667 | 3910.1373 | #DIV/0!
|  | 0.33924 | 0.33924 | 0 | 0 | 0.33333 | 88.6667 | 3901.3333 | 1.0177
|  | 0.33909 | 0 | 0.16291 | 0.17618 | 0 | 84 | 3634.4748 | #DIV/0!
|  | 0.33907 | 0 | 0 | 0.33907 | 0 | 65.5 | 2912.8021 | #DIV/0!
|  | 0.3387 | 0.3387 | 0 | 0 | 0 | 126.3333 | 4719.5607 | #DIV/0!
|  | 0.33859 | 0 | 0 | 0.33859 | 0 | 96.5 | 4291.3802 | #DIV/0!
|  | 0.33849 | 0.00039893 | 0.00044878 | 0.33764 | 0 | 96.1667 | 4274.9641 | #DIV/0!
|  | 0.33793 | 0 | 0.33793 | 0 | 0 | 76.3333 | 3207.9889 | #DIV/0!
|  | 0.33659 | 0 | 0.33659 | 0 | 0 | 101.8333 | 4279.6534 | #DIV/0!
|  | 0.3363 | 0.3363 | 0 | 0 | 0 | 82 | 3063.356 | #DIV/0!
|  | 0.3363 | 0.16791 | 0 | 0.16839 | 0.5 | 134.8333 | 2552.745 | 0.6726
|  | 0.33623 | 0.33623 | 0 | 0 | 0.83333 | 138.3333 | 4314.679 | 0.40348
|  | 0.33596 | 0.16821 | 0 | 0.16775 | 0.16667 | 69.8333 | 3072.745 | 2.0157
|  | 0.33556 | 0.00039893 | 0.0017951 | 0.33337 | 0 | 75 | 3333.2695 | #DIV/0!
|  | 0.33523 | 0.33523 | 0 | 0 | 0.5 | 93 | 3871.0247 | 0.67045
|  | 0.335 | 0.1652 | 0 | 0.16981 | 1 | 115.6667 | 4593.8919 | 0.335
|  | 0.33433 | 0.11909 | 0.0026281 | 0.21261 | 0.83333 | 119.5 | 3598.0815 | 0.40119
|  | 0.33432 | 0 | 0 | 0.33432 | 0 | 59.5 | 2645.9806 | #DIV/0!
|  | 0.33431 | 0.33431 | 0 | 0 | 0 | 7 | 261.506 | #DIV/0!
|  | 0.33424 | 0.00039893 | 0 | 0.33384 | 0 | 82.8333 | 3682.4346 | #DIV/0!
|  | 0.33391 | 0.33391 | 0 | 0 | 0 | 119.6667 | 4470.5073 | #DIV/0!
|  | 0.33391 | 0.33391 | 0 | 0 | 0 | 105.5 | 3941.269 | #DIV/0!
|  | 0.33391 | 0.33391 | 0 | 0 | 0 | 91.5 | 3418.257 | #DIV/0!
|  | 0.33384 | 0 | 0 | 0.33384 | 0 | 86.5 | 3846.6776 | #DIV/0!
|  | 0.33337 | 0 | 0 | 0.33337 | 0 | 71.8333 | 3194.4471 | #DIV/0!
|  | 0.33174 | 0.16539 | 0 | 0.16635 | 0.16667 | 93 | 4092.2351 | 1.9904
|  | 0.33152 | 0.33152 | 0 | 0 | 0.16667 | 108.6667 | 3695.2263 | 1.9891
|  | 0.3312 | 0 | 0.3312 | 0 | 0 | 90.8333 | 3817.3668 | #DIV/0!
|  | 0.33112 | 0 | 0.16454 | 0.16659 | 0.16667 | 89.5 | 3491.0043 | 1.9867
|  | 0.33053 | 0.33053 | 0 | 0 | 1.8333 | 9.1667 | 243.3333 | 0.18029
|  | 0.3303 | 0 | 0.3303 | 0 | 0 | 96.8333 | 4069.5231 | #DIV/0!
|  | 0.32941 | 0 | 0.32941 | 0 | 0 | 103.8333 | 4363.7055 | #DIV/0!
|  | 0.32936 | 0.32936 | 0 | 0 | 1 | 113 | 3898.5 | 0.32936
|  | 0.32854 | 0 | 0.32806 | 0.00047488 | 0 | 88.3333 | 3712.709 | #DIV/0!
|  | 0.32851 | 0 | 0.32851 | 0 | 0 | 96.3333 | 4048.5101 | #DIV/0!
|  | 0.32795 | 0.014203 | 0 | 0.31374 | 0.33333 | 151.1667 | 2876.4117 | 0.98384
|  | 0.32771 | 0.32771 | 0 | 0 | 1 | 103 | 3845.3333 | 0.32771
|  | 0.32767 | 0 | 0 | 0.32767 | 0 | 82.6667 | 3676.2083 | #DIV/0!
|  | 0.32677 | 0.16386 | 0 | 0.1629 | 0.16667 | 10.3333 | 465 | 1.9606
|  | 0.32629 | 0.051845 | 0.1959 | 0.078542 | 0.33333 | 119.6667 | 3128.8507 | 0.97887
|  | 0.32626 | 0.16313 | 0 | 0.16313 | 1.5 | 149.6667 | 4555.3333 | 0.2175
|  | 0.32568 | 0.32568 | 0 | 0 | 0.16667 | 91 | 3094 | 1.9541
|  | 0.32485 | 0.16242 | 0 | 0.16242 | 0.33333 | 110.6667 | 3596.6667 | 0.97454
|  | 0.32474 | 0.00039893 | 0 | 0.32435 | 0 | 93.6667 | 4164.1958 | #DIV/0!
|  | 0.32473 | 0.32473 | 0 | 0 | 0 | 111.1667 | 4152.9643 | #DIV/0!
|  | 0.32426 | 0.32426 | 0 | 0 | 0.16667 | 104.5 | 3553.5597 | 1.9456
|  | 0.32393 | 0.32393 | 0 | 0 | 0 | 59.6667 | 2229.0273 | #DIV/0!
|  | 0.32392 | 0.012216 | 0.00089757 | 0.3108 | 0.33333 | 65.6667 | 3408.8321 | 0.97175
|  | 0.32318 | 0.01888 | 0 | 0.3043 | 0.33333 | 69.6667 | 3622.6667 | 0.96954
|  | 0.32314 | 0.32314 | 0 | 0 | 0 | 100.1667 | 3742.0263 | #DIV/0!
|  | 0.32314 | 0.32314 | 0 | 0 | 0 | 96.5 | 3605.047 | #DIV/0!
|  | 0.32312 | 0.32312 | 0 | 0 | 0.16667 | 85.3333 | 3752.4527 | 1.9387
|  | 0.32312 | 0.16156 | 0 | 0.16156 | 0.5 | 22 | 902 | 0.64623
|  | 0.32283 | 0.00041647 | 0.15874 | 0.16367 | 0.16667 | 90.5 | 3530.5087 | 1.937
|  | 0.32277 | 0.00079787 | 0 | 0.32197 | 0 | 91.8333 | 4081.4816 | #DIV/0!
|  | 0.32273 | 0.32273 | 0 | 0 | 2 | 94 | 3431 | 0.16137
|  | 0.32223 | 0 | 0.32223 | 0 | 0 | 79.3333 | 3334.0671 | #DIV/0!
|  | 0.32172 | 0.32172 | 0 | 0 | 0.16667 | 89.1667 | 3032.2263 | 1.9303
|  | 0.32154 | 0.32154 | 0 | 0 | 0 | 84.8333 | 3169.2037 | #DIV/0!
|  | 0.32133 | 0.32133 | 0 | 0 | 0.33333 | 76.8333 | 2899.476 | 0.96399
|  | 0.32133 | 0 | 0.32133 | 0 | 0 | 80.5 | 3383.0975 | #DIV/0!
|  | 0.32074 | 0.32074 | 0 | 0 | 0 | 81.8333 | 3057.1297 | #DIV/0!
|  | 0.32043 | 0 | 0.32043 | 0 | 0 | 62.3333 | 2619.6242 | #DIV/0!
|  | 0.32036 | 0.16018 | 0 | 0.16018 | 0.5 | 93 | 3875 | 0.64072
|  | 0.31998 | 0 | 0.31998 | 0 | 0 | 70 | 2941.8239 | #DIV/0!
|  | 0.31955 | 0.31955 | 0 | 0 | 0 | 111.6667 | 4171.6433 | #DIV/0!
|  | 0.31953 | 0 | 0.31953 | 0 | 0 | 103.5 | 4349.6968 | #DIV/0!
|  | 0.31953 | 0 | 0.31953 | 0 | 0 | 2.3333 | 98.0608 | #DIV/0!
|  | 0.31948 | 0.022105 | 0 | 0.29737 | 0.16667 | 79 | 3281.6265 | 1.9169
|  | 0.31912 | 0 | 0 | 0.31912 | 0 | 71 | 3157.3886 | #DIV/0!
|  | 0.31846 | 0.31846 | 0 | 0 | 0.5 | 115.1667 | 4247.7507 | 0.63691
|  | 0.31844 | 0.31844 | 0 | 0 | 0.16667 | 85.6667 | 3852.4527 | 1.9106
|  | 0.31805 | 0.15903 | 0 | 0.15903 | 0.66667 | 84 | 3066 | 0.47708
|  | 0.31778 | 0 | 0.15889 | 0.15889 | 0.66667 | 66 | 3198.6667 | 0.47666
|  | 0.31767 | 0 | 0.00044878 | 0.31722 | 0 | 55.6667 | 2475.1039 | #DIV/0!
|  | 0.31755 | 0.31755 | 0 | 0 | 0 | 63.3333 | 2366.0067 | #DIV/0!
|  | 0.31729 | 0 | 0.31729 | 0 | 0 | 74 | 3109.9281 | #DIV/0!
|  | 0.31729 | 0 | 0.31729 | 0 | 0 | 47.1667 | 1982.229 | #DIV/0!
|  | 0.31715 | 0.00039893 | 0 | 0.31675 | 0 | 83.6667 | 3719.4932 | #DIV/0!
|  | 0.31611 | 0.31611 | 0 | 0 | 0.33333 | 100.1667 | 3656.2263 | 0.94834
|  | 0.31489 | 0.15745 | 0 | 0.15745 | 0.66667 | 142.6667 | 3999.3333 | 0.47234
|  | 0.31488 | 0.31488 | 0 | 0 | 0.66667 | 136.6667 | 3670.393 | 0.47231
|  | 0.31437 | 0 | 0 | 0.31437 | 0 | 80.3333 | 3572.4443 | #DIV/0!
|  | 0.31385 | 0 | 0.00089757 | 0.31295 | 0 | 62.5 | 2778.984 | #DIV/0!
|  | 0.31356 | 0.31356 | 0 | 0 | 0 | 111.3333 | 4159.1907 | #DIV/0!
|  | 0.31352 | 0.0033531 | 0.15424 | 0.15592 | 1.1667 | 176.1667 | 3951.1667 | 0.26873
|  | 0.31342 | 0 | 0 | 0.31342 | 0 | 67.6667 | 3009.1544 | #DIV/0!
|  | 0.31331 | 0.15698 | 0 | 0.15633 | 0.66667 | 150.1667 | 4021.9117 | 0.46996
|  | 0.31295 | 0 | 0 | 0.31295 | 0 | 101.1667 | 4498.9081 | #DIV/0!
|  | 0.31276 | 0.31276 | 0 | 0 | 0 | 88.3333 | 3299.9567 | #DIV/0!
|  | 0.31197 | 0.31197 | 0 | 0 | 0 | 64 | 2390.912 | #DIV/0!
|  | 0.31187 | 0.31187 | 0 | 0 | 0.83333 | 116.6667 | 4130 | 0.37425
|  | 0.31157 | 0.31157 | 0 | 0 | 0 | 82.5 | 3082.035 | #DIV/0!
|  | 0.31152 | 0 | 0 | 0.31152 | 0 | 84.8333 | 3772.5605 | #DIV/0!
|  | 0.31101 | 0 | 0.31101 | 0 | 0 | 75.3333 | 3165.9629 | #DIV/0!
|  | 0.31021 | 0 | 0.30831 | 0.0018995 | 0 | 75.3333 | 3167.5924 | #DIV/0!
|  | 0.30962 | 0 | 0 | 0.30962 | 0 | 100.6667 | 4476.673 | #DIV/0!
|  | 0.3094 | 0.10313 | 0.10313 | 0.10313 | 1.6667 | 105 | 4609.5 | 0.18564
|  | 0.30884 | 0.037119 | 0 | 0.27172 | 0.16667 | 84.5 | 3748.2535 | 1.853
|  | 0.30876 | 0 | 0.30876 | 0 | 0 | 81.1667 | 3411.1149 | #DIV/0!
|  | 0.3087 | 0.3087 | 0 | 0 | 1 | 104 | 3796 | 0.3087
|  | 0.30867 | 0 | 0 | 0.30867 | 0 | 62.6667 | 2786.8031 | #DIV/0!
|  | 0.30867 | 0 | 0 | 0.30867 | 0 | 59.3333 | 2638.5689 | #DIV/0!
|  | 0.30838 | 0.30838 | 0 | 0 | 0 | 81 | 3025.998 | #DIV/0!
|  | 0.30831 | 0 | 0.30831 | 0 | 0 | 92.5 | 3887.4102 | #DIV/0!
|  | 0.3082 | 0 | 0 | 0.3082 | 0 | 84 | 3735.502 | #DIV/0!
|  | 0.30806 | 0.15429 | 0 | 0.15377 | 0.16667 | 39.5 | 1896 | 1.8484
|  | 0.30763 | 0 | 0 | 0.30763 | 0.33333 | 62.6667 | 3258.6667 | 0.92289
|  | 0.30742 | 0 | 0.30742 | 0 | 0 | 59.1667 | 2486.5416 | #DIV/0!
|  | 0.30691 | 0.30691 | 0 | 0 | 0.16667 | 129.6667 | 2478.965 | 1.8415
|  | 0.30644 | 0.15322 | 0 | 0.15322 | 0.16667 | 85.6667 | 2912.6667 | 1.8386
|  | 0.30562 | 0 | 0.30562 | 0 | 0 | 72.5 | 3046.8891 | #DIV/0!
|  | 0.30532 | 0 | 0.00044878 | 0.30488 | 0 | 74 | 3290.392 | #DIV/0!
|  | 0.30532 | 0 | 0.00044878 | 0.30488 | 0 | 69.8333 | 3105.0992 | #DIV/0!
|  | 0.30441 | 0.10149 | 0.10143 | 0.10149 | 0.16667 | 43 | 1891.342 | 1.8264
|  | 0.30383 | 0 | 0.30383 | 0 | 0 | 96 | 4034.5014 | #DIV/0!
|  | 0.30356 | 0.15132 | 0.00044878 | 0.15179 | 0.66667 | 76.6667 | 3632.7494 | 0.45534
|  | 0.30285 | 0.30285 | 0 | 0 | 0.16667 | 65 | 2023.4773 | 1.8171
|  | 0.30239 | 0.30239 | 0 | 0 | 0 | 95.8333 | 3580.1417 | #DIV/0!
|  | 0.30239 | 0.30239 | 0 | 0 | 0 | 50.1667 | 1874.1263 | #DIV/0!
|  | 0.3021 | 0.15105 | 0 | 0.15105 | 0.33333 | 90 | 3105 | 0.9063
|  | 0.3012 | 0.3012 | 0 | 0 | 0 | 77.8333 | 2907.6977 | #DIV/0!
|  | 0.30099 | 0.30099 | 0 | 0 | 0.16667 | 137.3333 | 3165.8457 | 1.806
|  | 0.3006 | 0 | 0 | 0.3006 | 0 | 78.8333 | 3505.739 | #DIV/0!
|  | 0.30035 | 0 | 0.27376 | 0.026593 | 0 | 68.3333 | 2884.8163 | #DIV/0!
|  | 0.30001 | 0.30001 | 0 | 0 | 0.16667 | 87.1667 | 3262.7407 | 1.8
|  | 0.29973 | 0.29973 | 0 | 0 | 0.16667 | 101.6667 | 3153.786 | 1.7984
|  | 0.29965 | 0 | 0 | 0.29965 | 0 | 49.8333 | 2216.1014 | #DIV/0!
|  | 0.29935 | 0 | 0.14406 | 0.15529 | 0 | 71 | 3071.0266 | #DIV/0!
|  | 0.2986 | 0.021795 | 0.12832 | 0.14849 | 1.1667 | 167.5 | 3770.6654 | 0.25594
|  | 0.29829 | 0.15014 | 0.00044878 | 0.14771 | 0.16667 | 98.8333 | 3756.2307 | 1.7897
|  | 0.2976 | 0.2976 | 0 | 0 | 0 | 109.3333 | 4084.4747 | #DIV/0!
|  | 0.29747 | 0.29747 | 0 | 0 | 0.16667 | 95 | 3231.1193 | 1.7848
|  | 0.29728 | 0 | 0 | 0.29728 | 0 | 64.1667 | 2853.5084 | #DIV/0!
|  | 0.29681 | 0.29681 | 0 | 0 | 0 | 90.6667 | 3387.1253 | #DIV/0!
|  | 0.29627 | 0.29627 | 0 | 0 | 0.16667 | 70.8333 | 3113.3457 | 1.7776
|  | 0.2962 | 0 | 0.2962 | 0 | 0 | 67.8333 | 2850.7675 | #DIV/0!
|  | 0.29582 | 0.29582 | 0 | 0 | 0.33333 | 54.6667 | 2369.5597 | 0.88747
|  | 0.29575 | 0 | 0.29575 | 0 | 0 | 75 | 3151.9542 | #DIV/0!
|  | 0.29535 | 0 | 0.00044878 | 0.2949 | 0 | 57.8333 | 2571.4561 | #DIV/0!
|  | 0.29504 | 0.29504 | 0 | 0 | 0.16667 | 78 | 3507.4527 | 1.7703
|  | 0.2946 | 0.2946 | 0 | 0 | 0.16667 | 94.5 | 3215.2387 | 1.7676
|  | 0.2944 | 0 | 0.2944 | 0 | 0 | 67.1667 | 2822.7501 | #DIV/0!
|  | 0.29439 | 0.29439 | 0 | 0 | 1 | 89.1667 | 3076.7263 | 0.29439
|  | 0.29401 | 0.29401 | 0 | 0 | 0 | 102.5 | 3829.195 | #DIV/0!
|  | 0.29395 | 0 | 0 | 0.29395 | 0 | 63.5 | 2823.8616 | #DIV/0!
|  | 0.29395 | 0 | 0.29395 | 0 | 0 | 76.8333 | 3229.002 | #DIV/0!
|  | 0.29393 | 0 | 0.00044878 | 0.29348 | 0 | 84.5 | 3757.3297 | #DIV/0!
|  | 0.29392 | 0.14606 | 0.0017951 | 0.14606 | 0.66667 | 73 | 3026.6754 | 0.44088
|  | 0.2935 | 0 | 0.2935 | 0 | 0 | 88.5 | 3719.306 | #DIV/0!
|  | 0.29326 | 0.14663 | 0 | 0.14663 | 1.3333 | 117.3333 | 2918.6667 | 0.21994
|  | 0.29319 | 0 | 0.29319 | 0 | 0.33333 | 39.3333 | 2596 | 0.87958
|  | 0.29242 | 0.29242 | 0 | 0 | 0 | 103 | 3847.874 | #DIV/0!
|  | 0.29242 | 0.29242 | 0 | 0 | 0 | 101.3333 | 3785.6107 | #DIV/0!
|  | 0.29208 | 0.146 | 0 | 0.14608 | 0.5 | 83.3333 | 2807.9714 | 0.58416
|  | 0.29193 | 0.29193 | 0 | 0 | 0.16667 | 94.8333 | 3691.3563 | 1.7516
|  | 0.29162 | 0.29162 | 0 | 0 | 0 | 87.8333 | 3281.2777 | #DIV/0!
|  | 0.29082 | 0.29082 | 0 | 0 | 0 | 91.8333 | 3430.7097 | #DIV/0!
|  | 0.29008 | 0.29008 | 0 | 0 | 0.16667 | 86 | 3867.4527 | 1.7405
|  | 0.29003 | 0.29003 | 0 | 0 | 0 | 99.6667 | 3723.3473 | #DIV/0!
|  | 0.28873 | 0 | 0 | 0.28873 | 0 | 61.6667 | 2742.3328 | #DIV/0!
|  | 0.28821 | 0.28821 | 0 | 0 | 0.5 | 54 | 3049.1293 | 0.57641
|  | 0.28803 | 0.28803 | 0 | 0 | 0 | 79.3333 | 2963.7347 | #DIV/0!
|  | 0.28784 | 0 | 0.1391 | 0.14874 | 0.16667 | 75.6667 | 2951.9117 | 1.727
|  | 0.28767 | 0 | 0.28767 | 0 | 0 | 74 | 3109.9281 | #DIV/0!
|  | 0.28723 | 0.28723 | 0 | 0 | 0 | 83 | 3100.714 | #DIV/0!
|  | 0.28693 | 0.28693 | 0 | 0 | 2.5 | 70.1667 | 2918.2263 | 0.11477
|  | 0.28659 | 0 | 0.28659 | 0 | 0.33333 | 59.1667 | 3901.0043 | 0.85978
|  | 0.28651 | 0.14302 | 0 | 0.14349 | 1 | 90.1667 | 3412.4117 | 0.28651
|  | 0.28635 | 0 | 0 | 0.28635 | 0 | 64.6667 | 2875.7436 | #DIV/0!
|  | 0.28634 | 0.14317 | 0 | 0.14317 | 0.5 | 94.6667 | 3930 | 0.57268
|  | 0.28607 | 0.014683 | 0.2567 | 0.014683 | 0.5 | 89.1667 | 3743.37 | 0.57214
|  | 0.28604 | 0.28604 | 0 | 0 | 0 | 69.3333 | 2590.1547 | #DIV/0!
|  | 0.28583 | 0 | 0.00089757 | 0.28493 | 0 | 41.8333 | 1859.5245 | #DIV/0!
|  | 0.28524 | 0.28524 | 0 | 0 | 0 | 99.6667 | 3723.3473 | #DIV/0!
|  | 0.28505 | 0.14123 | 0 | 0.14383 | 0.16667 | 155.1667 | 3590.3036 | 1.7103
|  | 0.28491 | 0.28491 | 0 | 0 | 0.5 | 84.3333 | 2980.393 | 0.56982
|  | 0.28485 | 0.00039893 | 0 | 0.28446 | 0 | 76.6667 | 3408.2013 | #DIV/0!
|  | 0.28412 | 0.28412 | 0 | 0 | 0.16667 | 57.1667 | 2513.1193 | 1.7047
|  | 0.2841 | 0 | 0.063278 | 0.22082 | 0 | 85.3333 | 3745.5042 | #DIV/0!
|  | 0.28405 | 0.28405 | 0 | 0 | 0.16667 | 152.8333 | 3223.1317 | 1.7043
|  | 0.28404 | 0.28404 | 0 | 0 | 0 | 93.6667 | 3499.1993 | #DIV/0!
|  | 0.28351 | 0 | 0 | 0.28351 | 0 | 69.8333 | 3105.5066 | #DIV/0!
|  | 0.28324 | 0.28324 | 0 | 0 | 0 | 97.1667 | 3629.9523 | #DIV/0!
|  | 0.2832 | 0.1416 | 0 | 0.1416 | 0.33333 | 10 | 300 | 0.8496
|  | 0.28294 | 0.14147 | 0 | 0.14147 | 1.5 | 72 | 3312 | 0.18863
|  | 0.28294 | 0.14147 | 0 | 0.14147 | 1 | 138 | 3174 | 0.28294
|  | 0.28265 | 0.28265 | 0 | 0 | 0.5 | 83.6667 | 2956.5597 | 0.5653
|  | 0.28196 | 0.0052539 | 0.1366 | 0.1401 | 0.66667 | 92.6667 | 3799.3333 | 0.42294
|  | 0.28178 | 0 | 0.15214 | 0.12964 | 0 | 68.5 | 2954.5552 | #DIV/0!
|  | 0.28119 | 0.28119 | 0 | 0 | 0.16667 | 106 | 3288.1193 | 1.6871
|  | 0.28106 | 0.28106 | 0 | 0 | 1 | 109 | 3415.3333 | 0.28106
|  | 0.28098 | 0.28098 | 0 | 0 | 0.33333 | 71.6667 | 3153.3333 | 0.84293
|  | 0.28094 | 0 | 0.28094 | 0 | 0 | 86 | 3614.2408 | #DIV/0!
|  | 0.28086 | 0.14036 | 0 | 0.1405 | 0.16667 | 118 | 3660.245 | 1.6852
|  | 0.28078 | 0.010956 | 0.0044878 | 0.26533 | 0.33333 | 152.5 | 2942.1586 | 0.84234
|  | 0.28049 | 0 | 0.28049 | 0 | 0 | 77.5 | 3257.0193 | #DIV/0!
|  | 0.28006 | 0 | 0.13913 | 0.14093 | 0.16667 | 150.5 | 3474.9988 | 1.6804
|  | 0.27965 | 0.27965 | 0 | 0 | 0 | 111.3333 | 4159.1907 | #DIV/0!
|  | 0.27965 | 0.27965 | 0 | 0 | 0 | 64.6667 | 2415.8173 | #DIV/0!
|  | 0.27785 | 0.13987 | 0 | 0.13798 | 0.83333 | 85.8333 | 3038.5 | 0.33342
|  | 0.2778 | 0 | 0.2778 | 0 | 0 | 81.8333 | 3439.1323 | #DIV/0!
|  | 0.27765 | 0.13904 | 0 | 0.13861 | 0.33333 | 77.8333 | 3269.4117 | 0.83295
|  | 0.27765 | 0.13882 | 0 | 0.13882 | 0.83333 | 87 | 3684 | 0.33317
|  | 0.27709 | 0.27709 | 0 | 0 | 0.16667 | 150.1667 | 2868.465 | 1.6626
|  | 0.27613 | 0.13806 | 0 | 0.13806 | 1.8333 | 101.6667 | 3541.3333 | 0.15062
|  | 0.27581 | 0.27581 | 0 | 0 | 0.16667 | 67.8333 | 2984.6667 | 1.6549
|  | 0.27555 | 0 | 0.27555 | 0 | 0 | 62.1667 | 2612.6198 | #DIV/0!
|  | 0.27534 | 0.13743 | 0 | 0.13791 | 0.16667 | 22.5 | 1012.4117 | 1.6521
|  | 0.2751 | 0 | 0.2751 | 0 | 0 | 67.1667 | 2822.7501 | #DIV/0!
|  | 0.27484 | 0.13852 | 0 | 0.13631 | 0.33333 | 87 | 3001.5 | 0.82451
|  | 0.2748 | 0.2748 | 0 | 0 | 0.33333 | 71.8333 | 3159.5597 | 0.82439
|  | 0.27466 | 0 | 0.27466 | 0 | 0 | 87 | 3656.2669 | #DIV/0!
|  | 0.27376 | 0 | 0.27376 | 0 | 0 | 74.8333 | 3144.9499 | #DIV/0!
|  | 0.27353 | 0 | 0 | 0.27353 | 0 | 42.1667 | 1875.1627 | #DIV/0!
|  | 0.27303 | 0 | 0.13104 | 0.14199 | 0 | 69 | 2985.3451 | #DIV/0!
|  | 0.27298 | 0.00039893 | 0 | 0.27258 | 0 | 62.5 | 2778.206 | #DIV/0!
|  | 0.27277 | 0 | 0.0049366 | 0.26783 | 0 | 59.8333 | 2657.1377 | #DIV/0!
|  | 0.27258 | 0 | 0 | 0.27258 | 0 | 64.6667 | 2875.7436 | #DIV/0!
|  | 0.27203 | 0.27203 | 0 | 0 | 0.16667 | 71.1667 | 2804.396 | 1.6322
|  | 0.27158 | 0.0039938 | 0.13379 | 0.13379 | 0.66667 | 62.6667 | 2929.6667 | 0.40737
|  | 0.27157 | 0.27157 | 0 | 0 | 0.16667 | 76.6667 | 2791.3567 | 1.6294
|  | 0.27124 | 0 | 0.13202 | 0.13922 | 0.16667 | 78.3333 | 3055.9117 | 1.6274
|  | 0.27076 | 0.27076 | 0 | 0 | 0.83333 | 60.5 | 1623.8333 | 0.32491
|  | 0.27068 | 0 | 0 | 0.27068 | 0 | 64.3333 | 2860.9202 | #DIV/0!
|  | 0.27066 | 0 | 0.00044878 | 0.27021 | 0 | 63.6667 | 2830.866 | #DIV/0!
|  | 0.2705 | 0 | 0.13496 | 0.13554 | 0.16667 | 130.1667 | 3010.5031 | 1.623
|  | 0.27021 | 0 | 0 | 0.27021 | 0 | 80 | 3557.6209 | #DIV/0!
|  | 0.27018 | 0 | 0.00044878 | 0.26973 | 0 | 68.5 | 3045.8055 | #DIV/0!
|  | 0.27017 | 0 | 0.27017 | 0 | 0 | 62 | 2605.6155 | #DIV/0!
|  | 0.27016 | 0.13385 | 0.0028832 | 0.13343 | 0.66667 | 74.8333 | 3279.8333 | 0.40524
|  | 0.26987 | 0.26987 | 0 | 0 | 0.33333 | 51.3333 | 2669.3333 | 0.80961
|  | 0.26968 | 0.26968 | 0 | 0 | 0 | 83 | 3100.714 | #DIV/0!
|  | 0.26957 | 0.13551 | 0 | 0.13406 | 0.16667 | 44.3333 | 1994.8234 | 1.6174
|  | 0.2692 | 0.13632 | 0.00044878 | 0.13243 | 0.16667 | 93.6667 | 3561.8401 | 1.6152
|  | 0.26907 | 0.26907 | 0 | 0 | 0.16667 | 61.3333 | 2085.893 | 1.6144
|  | 0.26894 | 0.26894 | 0 | 0 | 0.33333 | 100.6667 | 2727.02 | 0.80683
|  | 0.26831 | 0 | 0 | 0.26831 | 0 | 68.1667 | 3031.3895 | #DIV/0!
|  | 0.26816 | 0.13564 | 0 | 0.13252 | 0.83333 | 100 | 2920 | 0.3218
|  | 0.2679 | 0.2679 | 0 | 0 | 0.5 | 82.3333 | 3248.4527 | 0.53581
|  | 0.26768 | 0.26768 | 0 | 0 | 0 | 89.8333 | 3355.9937 | #DIV/0!
|  | 0.26768 | 0.26768 | 0 | 0 | 0 | 86.5 | 3231.467 | #DIV/0!
|  | 0.26755 | 0.038272 | 0.19101 | 0.038272 | 0.66667 | 70.5 | 2681.235 | 0.40133
|  | 0.26743 | 0.13543 | 0 | 0.132 | 0.5 | 78.8333 | 2968.5784 | 0.53486
|  | 0.26736 | 0 | 0 | 0.26736 | 0 | 62.3333 | 2771.9796 | #DIV/0!
|  | 0.26729 | 0.26729 | 0 | 0 | 0 | 64.1667 | 2397.1383 | #DIV/0!
|  | 0.26726 | 0.00039893 | 0.00044878 | 0.26641 | 0 | 45.3333 | 2014.3924 | #DIV/0!
|  | 0.26686 | 0 | 0.24431 | 0.022553 | 0.33333 | 46.8333 | 3087.0043 | 0.80058
|  | 0.2668 | 0.1334 | 0 | 0.1334 | 0.83333 | 100.6667 | 2939.3333 | 0.32016
|  | 0.26658 | 0 | 0.26658 | 0 | 0 | 79.6667 | 3348.0758 | #DIV/0!
|  | 0.26649 | 0.26649 | 0 | 0 | 0 | 57.3333 | 2141.8587 | #DIV/0!
|  | 0.26532 | 0.13266 | 0 | 0.13266 | 0.5 | 86 | 2895.3333 | 0.53064
|  | 0.26478 | 0 | 0.26478 | 0 | 0 | 77 | 3236.0063 | #DIV/0!
|  | 0.2647 | 0.2647 | 0 | 0 | 0.16667 | 58.8333 | 1825.9527 | 1.5882
|  | 0.26433 | 0 | 0.26433 | 0 | 0 | 47.6667 | 2003.242 | #DIV/0!
|  | 0.26409 | 0.26409 | 0 | 0 | 0 | 85.8333 | 3206.5617 | #DIV/0!
|  | 0.26409 | 0.26409 | 0 | 0 | 0 | 64.8333 | 2422.0437 | #DIV/0!
|  | 0.26359 | 0.26359 | 0 | 0 | 0.66667 | 80.6667 | 2662 | 0.39539
|  | 0.26344 | 0 | 0.26344 | 0 | 0 | 70.5 | 2962.8369 | #DIV/0!
|  | 0.2633 | 0.2633 | 0 | 0 | 0 | 83.8333 | 3131.8457 | #DIV/0!
|  | 0.26321 | 0.13091 | 0 | 0.1323 | 0.16667 | 142.8333 | 3303.0586 | 1.5793
|  | 0.26318 | 0.13224 | 0 | 0.13093 | 0.66667 | 87 | 2672.5 | 0.39476
|  | 0.2631 | 0.2631 | 0 | 0 | 0.16667 | 88.3333 | 3305.5987 | 1.5786
|  | 0.26276 | 0.26276 | 0 | 0 | 0.33333 | 80 | 3371 | 0.78828
|  | 0.26273 | 0.00083294 | 0.12667 | 0.13523 | 0.16667 | 80.6667 | 3151.5672 | 1.5764
|  | 0.26261 | 0 | 0 | 0.26261 | 0 | 51.1667 | 2275.395 | #DIV/0!
|  | 0.26211 | 0 | 0.00044878 | 0.26166 | 0 | 60.1667 | 2675.22 | #DIV/0!
|  | 0.26164 | 0 | 0.26164 | 0 | 0 | 54.3333 | 2283.4157 | #DIV/0!
|  | 0.26164 | 0 | 0.26164 | 0 | 0 | 56 | 2353.4591 | #DIV/0!
|  | 0.26163 | 0 | 0.00044878 | 0.26119 | 0 | 62.5 | 2778.984 | #DIV/0!
|  | 0.26099 | 0.0011106 | 0.12994 | 0.12994 | 0.33333 | 61 | 3172 | 0.78296
|  | 0.2609 | 0.2609 | 0 | 0 | 0 | 79.5 | 2969.961 | #DIV/0!
|  | 0.2609 | 0.2609 | 0 | 0 | 0 | 45.8333 | 1712.2417 | #DIV/0!
|  | 0.26074 | 0 | 0.26074 | 0 | 0 | 49.1667 | 2066.2811 | #DIV/0!
|  | 0.2605 | 0.2605 | 0 | 0 | 0 | 79.5 | 2969.961 | #DIV/0!
|  | 0.26008 | 0.088548 | 0.082984 | 0.088548 | 2.1667 | 57.5 | 2507.1667 | 0.12004
|  | 0.25989 | 0.25989 | 0 | 0 | 0.16667 | 63 | 2833.7263 | 1.5593
|  | 0.25985 | 0 | 0.25985 | 0 | 0 | 64.8333 | 2724.6893 | #DIV/0!
|  | 0.25971 | 0.25971 | 0 | 0 | 0 | 99.3333 | 3710.8947 | #DIV/0!
|  | 0.25971 | 0.25971 | 0 | 0 | 0 | 80.1667 | 2994.8663 | #DIV/0!
|  | 0.25965 | 0.25965 | 0 | 0 | 0.33333 | 70 | 2799.1193 | 0.77895
|  | 0.25931 | 0.25931 | 0 | 0 | 0 | 80.6667 | 3013.5453 | #DIV/0!
|  | 0.25891 | 0.25891 | 0 | 0 | 0 | 74.8333 | 2795.6237 | #DIV/0!
|  | 0.25881 | 0 | 0 | 0.25881 | 0 | 71.8333 | 3194.4471 | #DIV/0!
|  | 0.2585 | 0 | 0.2585 | 0 | 0 | 66.6667 | 2801.7371 | #DIV/0!
|  | 0.25834 | 0 | 0 | 0.25834 | 0 | 73.8333 | 3283.3876 | #DIV/0!
|  | 0.25808 | 0.12904 | 0 | 0.12904 | 1.3333 | 50 | 2307 | 0.19356
|  | 0.25774 | 0.12673 | 0 | 0.13101 | 0.16667 | 50.6667 | 2179.6468 | 1.5465
|  | 0.25771 | 0.25771 | 0 | 0 | 0 | 75.6667 | 2826.7553 | #DIV/0!
|  | 0.25688 | 0.12821 | 0 | 0.12867 | 0.16667 | 116.3333 | 2682.8234 | 1.5413
|  | 0.2567 | 0 | 0.2567 | 0 | 0 | 80.3333 | 3376.0932 | #DIV/0!
|  | 0.25651 | 0.25651 | 0 | 0 | 0 | 73.1667 | 2733.3603 | #DIV/0!
|  | 0.25638 | 0.035816 | 0 | 0.22056 | 0.16667 | 69.6667 | 3064.5239 | 1.5383
|  | 0.25625 | 0 | 0.25625 | 0 | 0 | 63.1667 | 2654.6459 | #DIV/0!
|  | 0.25612 | 0.25612 | 0 | 0 | 0 | 80 | 2988.64 | #DIV/0!
|  | 0.25565 | 0.12823 | 0 | 0.12742 | 0.33333 | 82.3333 | 3128.6667 | 0.76694
|  | 0.25564 | 0.25564 | 0 | 0 | 0.16667 | 86.1667 | 3188.2263 | 1.5338
|  | 0.2556 | 0.1278 | 0 | 0.1278 | 0.33333 | 63.3333 | 2786.6667 | 0.76681
|  | 0.25549 | 0 | 0 | 0.25549 | 0 | 52.6667 | 2342.1004 | #DIV/0!
|  | 0.25532 | 0.25532 | 0 | 0 | 0 | 51.5 | 1923.937 | #DIV/0!
|  | 0.2552 | 0.2552 | 0 | 0 | 0.66667 | 90.3333 | 2858 | 0.3828
|  | 0.25515 | 0.12686 | 0 | 0.12829 | 0.16667 | 16.6667 | 749.8234 | 1.5309
|  | 0.25491 | 0 | 0.25491 | 0 | 0 | 68.8333 | 2892.7935 | #DIV/0!
|  | 0.25486 | 0 | 0.22305 | 0.031817 | 0 | 68.8333 | 2911.5324 | #DIV/0!
|  | 0.25478 | 0.25478 | 0 | 0 | 0.33333 | 104.3333 | 3029 | 0.76435
|  | 0.25471 | 0.25471 | 0 | 0 | 0.16667 | 71.3333 | 2214.5123 | 1.5283
|  | 0.25459 | 0.25459 | 0 | 0 | 0.16667 | 66.6667 | 2932.2263 | 1.5276
|  | 0.25452 | 0.25452 | 0 | 0 | 0 | 78 | 2913.924 | #DIV/0!
|  | 0.25406 | 0 | 0 | 0.25406 | 0 | 72 | 3201.8588 | #DIV/0!
|  | 0.25401 | 0.25401 | 0 | 0 | 1.5 | 113.5 | 2823 | 0.16934
|  | 0.25401 | 0 | 0.25401 | 0 | 0 | 45.5 | 1912.1855 | #DIV/0!
|  | 0.25372 | 0.25372 | 0 | 0 | 0 | 73.5 | 2745.813 | #DIV/0!
|  | 0.25363 | 0.12821 | 0 | 0.12542 | 1.6667 | 121.6667 | 3175.5 | 0.15218
|  | 0.25344 | 0 | 0.14137 | 0.11207 | 0 | 63 | 2720.153 | #DIV/0!
|  | 0.25332 | 0.25332 | 0 | 0 | 0 | 73 | 2727.134 | #DIV/0!
|  | 0.2533 | 0.12727 | 0.00044878 | 0.12559 | 0.5 | 84.3333 | 2842.4161 | 0.50661
|  | 0.25306 | 0.11869 | 0 | 0.13436 | 0.16667 | 66.1667 | 2601.4693 | 1.5183
|  | 0.2527 | 0.12559 | 0.0049366 | 0.12217 | 0.66667 | 76.1667 | 3110.0304 | 0.37905
|  | 0.25264 | 0 | 0 | 0.25264 | 0 | 61.5 | 2734.9211 | #DIV/0!
|  | 0.25257 | 0 | 0.25257 | 0 | 0.33333 | 33.3333 | 1800 | 0.75772
|  | 0.25219 | 0.25219 | 0 | 0 | 0.33333 | 85.1667 | 3108.7263 | 0.75657
|  | 0.25217 | 0.25217 | 0 | 0 | 1 | 49.5 | 2864.3333 | 0.25217
|  | 0.25216 | 0 | 0 | 0.25216 | 0 | 74.1667 | 3298.2111 | #DIV/0!
|  | 0.25185 | 0.12565 | 0 | 0.1262 | 0.16667 | 64.1667 | 2376.7761 | 1.5111
|  | 0.25185 | 0 | 0.25042 | 0.0014247 | 0 | 78 | 3279.2545 | #DIV/0!
|  | 0.2518 | 0.2518 | 0 | 0 | 0.16667 | 63.3333 | 2338.7433 | 1.5108
|  | 0.25173 | 0.25173 | 0 | 0 | 0 | 64.8333 | 2422.0437 | #DIV/0!
|  | 0.25079 | 0.12498 | 0 | 0.1258 | 0.33333 | 148 | 2820.4901 | 0.75236
|  | 0.25071 | 0 | 0.00044878 | 0.25026 | 0 | 62.1667 | 2764.1606 | #DIV/0!
|  | 0.2502 | 0.2502 | 0 | 0 | 0.16667 | 79.8333 | 3589.9527 | 1.5012
|  | 0.24973 | 0.24973 | 0 | 0 | 0 | 88.5 | 3306.183 | #DIV/0!
|  | 0.24952 | 0 | 0.24952 | 0 | 0 | 79.5 | 3341.0715 | #DIV/0!
|  | 0.24952 | 0 | 0.24952 | 0 | 0 | 80.3333 | 3376.0932 | #DIV/0!
|  | 0.24929 | 0 | 0.00044878 | 0.24884 | 0 | 55.6667 | 2475.1039 | #DIV/0!
|  | 0.2492 | 0.12354 | 0 | 0.12565 | 0.16667 | 124.3333 | 2877.5586 | 1.4952
|  | 0.24889 | 0.025558 | 0 | 0.22333 | 0.16667 | 57.3333 | 2335.1638 | 1.4933
|  | 0.24884 | 0.24884 | 0 | 0 | 0.16667 | 39.6667 | 1783.7263 | 1.493
|  | 0.24844 | 0.12446 | 0 | 0.12398 | 0.16667 | 66.5 | 2992.5 | 1.4906
|  | 0.24806 | 0.24806 | 0 | 0 | 0.33333 | 52.1667 | 2710.2263 | 0.74418
|  | 0.24802 | 0.24802 | 0 | 0 | 0.16667 | 61.6667 | 2712.2263 | 1.4881
|  | 0.2476 | 0.2476 | 0 | 0 | 0.5 | 99.6667 | 1762.5843 | 0.4952
|  | 0.24694 | 0.24694 | 0 | 0 | 0 | 77.1667 | 2882.7923 | #DIV/0!
|  | 0.24694 | 0.24694 | 0 | 0 | 0 | 65.1667 | 2434.4963 | #DIV/0!
|  | 0.24683 | 0 | 0.24683 | 0 | 0 | 67.5 | 2836.7588 | #DIV/0!
|  | 0.24668 | 0 | 0.24668 | 0 | 0.33333 | 20.6667 | 1364 | 0.74003
|  | 0.24628 | 0.24628 | 0 | 0 | 0.66667 | 100.1667 | 2835.786 | 0.36942
|  | 0.24591 | 0.12295 | 0 | 0.12295 | 0.33333 | 45.3333 | 2289.3333 | 0.73773
|  | 0.24549 | 0 | 0.00044878 | 0.24504 | 0 | 60.3333 | 2682.6317 | #DIV/0!
|  | 0.24506 | 0.0077741 | 0.00089757 | 0.23639 | 0.33333 | 49.3333 | 2562.4161 | 0.73519
|  | 0.24504 | 0 | 0 | 0.24504 | 0 | 44.3333 | 1971.5149 | #DIV/0!
|  | 0.24504 | 0 | 0.24504 | 0 | 0 | 76.6667 | 3221.9976 | #DIV/0!
|  | 0.24495 | 0 | 0.23023 | 0.014721 | 0 | 58.5 | 2467.4864 | #DIV/0!
|  | 0.24459 | 0 | 0.24459 | 0 | 0 | 59.8333 | 2514.559 | #DIV/0!
|  | 0.24414 | 0 | 0.24414 | 0 | 0 | 70.6667 | 2969.8413 | #DIV/0!
|  | 0.24386 | 0.12193 | 0 | 0.12193 | 0.66667 | 74.6667 | 3229.3333 | 0.36579
|  | 0.24375 | 0.24375 | 0 | 0 | 0 | 66 | 2465.628 | #DIV/0!
|  | 0.24374 | 0.24374 | 0 | 0 | 0.5 | 72.8333 | 3033.286 | 0.48748
|  | 0.24348 | 0 | 0.20644 | 0.037041 | 0 | 77.6667 | 3290.9099 | #DIV/0!
|  | 0.24335 | 0.24335 | 0 | 0 | 0 | 54.3333 | 2029.7847 | #DIV/0!
|  | 0.24324 | 0 | 0.24324 | 0 | 0 | 57.8333 | 2430.5069 | #DIV/0!
|  | 0.24255 | 0.24255 | 0 | 0 | 0 | 65.8333 | 2459.4017 | #DIV/0!
|  | 0.24255 | 0.24255 | 0 | 0 | 0 | 60.3333 | 2253.9327 | #DIV/0!
|  | 0.24253 | 0 | 0.12127 | 0.12127 | 0.66667 | 47.6667 | 2313 | 0.3638
|  | 0.24219 | 0.24219 | 0 | 0 | 0.16667 | 70 | 2172.1193 | 1.4532
|  | 0.24189 | 0 | 0.24189 | 0 | 0 | 60.1667 | 2528.5677 | #DIV/0!
|  | 0.24172 | 0 | 0 | 0.24172 | 0 | 47.8333 | 2127.1608 | #DIV/0!
|  | 0.24164 | 0 | 0.0013463 | 0.24029 | 0 | 71.3333 | 3170.9899 | #DIV/0!
|  | 0.24119 | 0.12054 | 0 | 0.12065 | 0.16667 | 72.3333 | 2461.0784 | 1.4472
|  | 0.241 | 0 | 0.241 | 0 | 0 | 74 | 3109.9281 | #DIV/0!
|  | 0.24077 | 0 | 0 | 0.24077 | 0 | 62.1667 | 2764.5679 | #DIV/0!
|  | 0.24055 | 0 | 0.24055 | 0 | 0 | 72.5 | 3046.8891 | #DIV/0!
|  | 0.24042 | 0.24042 | 0 | 0 | 0.16667 | 59.8333 | 2233.1343 | 1.4425
|  | 0.24016 | 0.24016 | 0 | 0 | 0 | 83.3333 | 3113.1667 | #DIV/0!
|  | 0.2401 | 0 | 0.2401 | 0 | 0 | 54.3333 | 2283.4157 | #DIV/0!
|  | 0.23981 | 0.23981 | 0 | 0 | 0.5 | 65.1667 | 2562.893 | 0.47963
|  | 0.23969 | 0.11985 | 0 | 0.11985 | 0.33333 | 58 | 2523 | 0.71908
|  | 0.23957 | 0.11978 | 0 | 0.11978 | 0.66667 | 82.6667 | 3242.6667 | 0.35935
|  | 0.23938 | 0.23938 | 0 | 0 | 0.16667 | 109.8333 | 2096.0123 | 1.4363
|  | 0.23909 | 0 | 0.184 | 0.055087 | 0 | 45.1667 | 1935.2473 | #DIV/0!
|  | 0.23908 | 0.23908 | 0 | 0 | 0.5 | 43.1667 | 1638.8333 | 0.47817
|  | 0.23881 | 0.23881 | 0 | 0 | 0.5 | 4.5 | 160.5 | 0.47761
|  | 0.23838 | 0.23838 | 0 | 0 | 0.5 | 79.8333 | 2874.4527 | 0.47675
|  | 0.23822 | 0 | 0.23822 | 0 | 0.33333 | 39.6667 | 2618 | 0.71466
|  | 0.23816 | 0.23816 | 0 | 0 | 0 | 75.6667 | 2826.7553 | #DIV/0!
|  | 0.23816 | 0.23816 | 0 | 0 | 0 | 70.3333 | 2627.5127 | #DIV/0!
|  | 0.23809 | 0 | 0.19298 | 0.045114 | 0 | 62.8333 | 2668.7456 | #DIV/0!
|  | 0.23775 | 0.23775 | 0 | 0 | 0.33333 | 46 | 2783 | 0.71325
|  | 0.23766 | 0.11883 | 0 | 0.11883 | 0.5 | 5 | 178.3333 | 0.47533
|  | 0.23739 | 0.23739 | 0 | 0 | 0.16667 | 54.5 | 2452.5 | 1.4243
|  | 0.23728 | 0.11864 | 0 | 0.11864 | 0.33333 | 60.6667 | 3063.6667 | 0.71184
|  | 0.23726 | 0.11863 | 0 | 0.11863 | 0.66667 | 77.3333 | 3112.6667 | 0.35589
|  | 0.23682 | 0 | 0.010771 | 0.22604 | 0 | 67.3333 | 2984.9615 | #DIV/0!
|  | 0.23657 | 0.23657 | 0 | 0 | 0 | 73.6667 | 2752.0393 | #DIV/0!
|  | 0.23642 | 0.00039893 | 0 | 0.23602 | 0 | 50 | 2222.3277 | #DIV/0!
|  | 0.23638 | 0.23638 | 0 | 0 | 0.33333 | 50.3333 | 2356 | 0.70915
|  | 0.23628 | 0.11814 | 0 | 0.11814 | 0.33333 | 49.6667 | 1871.6667 | 0.70883
|  | 0.23575 | 0.1174 | 0 | 0.11835 | 0.16667 | 91.6667 | 2115.4901 | 1.4145
|  | 0.23574 | 0.23574 | 0 | 0 | 0.16667 | 55.5 | 1953.4103 | 1.4144
|  | 0.23554 | 0 | 0 | 0.23554 | 0 | 67.3333 | 2994.3309 | #DIV/0!
|  | 0.23537 | 0.23537 | 0 | 0 | 0 | 55.6667 | 2079.5953 | #DIV/0!
|  | 0.23529 | 0.11725 | 0 | 0.11804 | 0.33333 | 86.8333 | 2612.2351 | 0.70586
|  | 0.23516 | 0 | 0.23516 | 0 | 0 | 66.1667 | 2780.724 | #DIV/0!
|  | 0.23497 | 0.23497 | 0 | 0 | 0 | 59 | 2204.122 | #DIV/0!
|  | 0.23459 | 0 | 0 | 0.23459 | 0 | 69 | 3068.448 | #DIV/0!
|  | 0.23431 | 0.23431 | 0 | 0 | 1 | 83 | 2863.5 | 0.23431
|  | 0.23417 | 0.23417 | 0 | 0 | 0 | 70 | 2615.06 | #DIV/0!
|  | 0.23412 | 0 | 0 | 0.23412 | 0 | 67.6667 | 3009.1544 | #DIV/0!
|  | 0.23402 | 0.23402 | 0 | 0 | 0.5 | 100.3333 | 2812.4527 | 0.46804
|  | 0.23341 | 0.23341 | 0 | 0 | 1 | 77.3333 | 2450 | 0.23341
|  | 0.23318 | 0.12319 | 0 | 0.10999 | 1.6667 | 55 | 2266 | 0.13991
|  | 0.23308 | 0.23308 | 0 | 0 | 0.33333 | 52.3333 | 1910.1667 | 0.69925
|  | 0.23298 | 0 | 0.11623 | 0.11675 | 0.16667 | 34.8333 | 1566.2438 | 1.3979
|  | 0.23273 | 0.11727 | 0 | 0.11546 | 0.16667 | 71 | 2414 | 1.3964
|  | 0.23261 | 0.119 | 0.0020503 | 0.11156 | 1.6667 | 72 | 3630.5 | 0.13957
|  | 0.23258 | 0.23258 | 0 | 0 | 0 | 76.3333 | 2851.6607 | #DIV/0!
|  | 0.23258 | 0.23258 | 0 | 0 | 0 | 67.1667 | 2509.2123 | #DIV/0!
|  | 0.23222 | 0 | 0 | 0.23222 | 0 | 40.6667 | 1808.4573 | #DIV/0!
|  | 0.23222 | 0 | 0 | 0.23222 | 0 | 62.6667 | 2786.8031 | #DIV/0!
|  | 0.23208 | 0.11593 | 0 | 0.11616 | 0.16667 | 113.3333 | 2610.245 | 1.3925
|  | 0.23184 | 0.078424 | 0.074516 | 0.078899 | 0.66667 | 63 | 3210.4161 | 0.34776
|  | 0.23102 | 0.11525 | 0 | 0.11576 | 0.16667 | 73.5 | 3161.2351 | 1.3861
|  | 0.23087 | 0.23087 | 0 | 0 | 1 | 59.3333 | 2219.3457 | 0.23087
|  | 0.2307 | 0.2307 | 0 | 0 | 0.16667 | 55.1667 | 2427.3333 | 1.3842
|  | 0.23058 | 0.23058 | 0 | 0 | 0 | 62.5 | 2334.875 | #DIV/0!
|  | 0.22976 | 0 | 0.11418 | 0.11559 | 0.33333 | 43 | 2838 | 0.68929
|  | 0.22971 | 0.079695 | 0.070319 | 0.079695 | 1.6667 | 46.6667 | 2048.6667 | 0.13783
|  | 0.22934 | 0 | 0.00044878 | 0.22889 | 0 | 50 | 2223.1057 | #DIV/0!
|  | 0.22934 | 0.22934 | 0 | 0 | 0.16667 | 138.6667 | 2928.358 | 1.376
|  | 0.22899 | 0.22899 | 0 | 0 | 0.16667 | 147.8333 | 3115.4053 | 1.3739
|  | 0.22889 | 0 | 0 | 0.22889 | 0 | 57.5 | 2557.04 | #DIV/0!
|  | 0.22868 | 0.22868 | 0 | 0 | 0.16667 | 55.5 | 2439.786 | 1.3721
|  | 0.22845 | 0.22845 | 0 | 0 | 0.16667 | 68.8333 | 2341.4527 | 1.3707
|  | 0.22794 | 0 | 0 | 0.22794 | 0 | 67.3333 | 2994.3309 | #DIV/0!
|  | 0.22779 | 0.22779 | 0 | 0 | 0 | 68.6667 | 2565.2493 | #DIV/0!
|  | 0.22765 | 0.11687 | 0.00040579 | 0.11037 | 0.16667 | 64.6667 | 2457.3333 | 1.3659
|  | 0.22753 | 0 | 0.22753 | 0 | 0 | 56.6667 | 2381.4765 | #DIV/0!
|  | 0.22718 | 0.22718 | 0 | 0 | 0.16667 | 49.6667 | 1875.1943 | 1.3631
|  | 0.22708 | 0 | 0.21901 | 0.008073 | 0 | 55.8333 | 2351.3432 | #DIV/0!
|  | 0.227 | 0.056889 | 0.1122 | 0.057915 | 0.16667 | 85.8333 | 2529.5374 | 1.362
|  | 0.22687 | 0.22687 | 0 | 0 | 0.16667 | 52 | 2286.893 | 1.3612
|  | 0.22638 | 0.033403 | 0.12611 | 0.066874 | 0.16667 | 79.5 | 2675.3676 | 1.3583
|  | 0.22604 | 0 | 0 | 0.22604 | 0 | 28.1667 | 1252.579 | #DIV/0!
|  | 0.22604 | 0 | 0 | 0.22604 | 0 | 45.8333 | 2038.2203 | #DIV/0!
|  | 0.22582 | 0.097475 | 0 | 0.12834 | 0.16667 | 36.6667 | 1964.9387 | 1.3549
|  | 0.22558 | 0.22558 | 0 | 0 | 0.16667 | 121.5 | 2581.4897 | 1.3535
|  | 0.22549 | 0.22549 | 0 | 0 | 0.33333 | 48.3333 | 2028.8457 | 0.67648
|  | 0.22502 | 0.00039893 | 0 | 0.22462 | 0 | 32.6667 | 1451.5098 | #DIV/0!
|  | 0.22481 | 0.11322 | 0 | 0.11159 | 0.16667 | 80.6667 | 3065.3333 | 1.3488
|  | 0.22462 | 0 | 0 | 0.22462 | 0 | 55 | 2445.8644 | #DIV/0!
|  | 0.22439 | 0 | 0.22439 | 0 | 0 | 70.6667 | 2969.8413 | #DIV/0!
|  | 0.22438 | 0.22438 | 0 | 0 | 0.16667 | 66.3333 | 2255.3333 | 1.3463
|  | 0.22435 | 0.22435 | 0 | 0 | 1 | 50 | 1175 | 0.22435
|  | 0.2242 | 0.2242 | 0 | 0 | 0 | 70.6667 | 2639.9653 | #DIV/0!
|  | 0.22415 | 0 | 0 | 0.22415 | 0 | 53.6667 | 2386.5707 | #DIV/0!
|  | 0.22408 | 0 | 0.10726 | 0.11682 | 0 | 32.8333 | 1421.407 | #DIV/0!
|  | 0.22367 | 0 | 0 | 0.22367 | 0 | 61.8333 | 2749.7445 | #DIV/0!
|  | 0.22306 | 0 | 0.075844 | 0.14721 | 0 | 50.1667 | 2186.9291 | #DIV/0!
|  | 0.22301 | 0 | 0.17458 | 0.048438 | 0 | 66.6667 | 2837.9928 | #DIV/0!
|  | 0.223 | 0.223 | 0 | 0 | 0 | 64 | 2390.912 | #DIV/0!
|  | 0.22261 | 0.22261 | 0 | 0 | 0 | 59.6667 | 2229.0273 | #DIV/0!
|  | 0.22225 | 0 | 0 | 0.22225 | 0 | 40.3333 | 1793.6339 | #DIV/0!
|  | 0.22221 | 0.22221 | 0 | 0 | 0.16667 | 124.6667 | 2628.9053 | 1.3333
|  | 0.22221 | 0.22221 | 0 | 0 | 0 | 54.8333 | 2048.4637 | #DIV/0!
|  | 0.22177 | 0 | 0 | 0.22177 | 0 | 47.3333 | 2104.9257 | #DIV/0!
|  | 0.22125 | 0 | 0.22125 | 0 | 0 | 61.1667 | 2570.5938 | #DIV/0!
|  | 0.22105 | 0.018421 | 0.18445 | 0.018175 | 0.16667 | 67.1667 | 2489.7941 | 1.3263
|  | 0.22061 | 0.22061 | 0 | 0 | 0 | 76.8333 | 2870.3397 | #DIV/0!
|  | 0.22035 | 0 | 0 | 0.22035 | 0 | 66.5 | 2957.2724 | #DIV/0!
|  | 0.22002 | 0.10954 | 0 | 0.11048 | 0.16667 | 111.6667 | 2579.0685 | 1.3201
|  | 0.2199 | 0 | 0.2199 | 0 | 0 | 55.3333 | 2325.4418 | #DIV/0!
|  | 0.21974 | 0.11049 | 0 | 0.10924 | 0.33333 | 51.5 | 2012.5 | 0.65921
|  | 0.21941 | 0.21941 | 0 | 0 | 0 | 61.6667 | 2303.7433 | #DIV/0!
|  | 0.21941 | 0.21941 | 0 | 0 | 0 | 57.3333 | 2141.8587 | #DIV/0!
|  | 0.21937 | 0 | 0.00044878 | 0.21892 | 0 | 70.1667 | 3119.9227 | #DIV/0!
|  | 0.21896 | 0.10948 | 0 | 0.10948 | 0.16667 | 62.3333 | 2742.6667 | 1.3137
|  | 0.21893 | 0.21893 | 0 | 0 | 0.33333 | 56.8333 | 2492.9177 | 0.65679
|  | 0.21862 | 0.21862 | 0 | 0 | 0 | 70.5 | 2633.739 | #DIV/0!
|  | 0.21861 | 0.21861 | 0 | 0 | 0.66667 | 60.5 | 2535.5 | 0.32792
|  | 0.21845 | 0 | 0 | 0.21845 | 0 | 46.6667 | 2075.2789 | #DIV/0!
|  | 0.21837 | 0.00039893 | 0 | 0.21797 | 0 | 51.8333 | 2303.8565 | #DIV/0!
|  | 0.21822 | 0.21822 | 0 | 0 | 0 | 72.3333 | 2702.2287 | #DIV/0!
|  | 0.21797 | 0 | 0 | 0.21797 | 0 | 47.5 | 2112.3374 | #DIV/0!
|  | 0.21797 | 0.10858 | 0 | 0.10939 | 0.16667 | 75.3333 | 2337.5784 | 1.3078
|  | 0.2179 | 0.00039893 | 0 | 0.2175 | 0 | 56.1667 | 2496.561 | #DIV/0!
|  | 0.21782 | 0.21782 | 0 | 0 | 0 | 68 | 2540.344 | #DIV/0!
|  | 0.21772 | 0.11249 | 0 | 0.10523 | 1.6667 | 83 | 3145.3333 | 0.13063
|  | 0.21748 | 0.21748 | 0 | 0 | 0.16667 | 62.8333 | 2136.3333 | 1.3049
|  | 0.21742 | 0.21742 | 0 | 0 | 0 | 65.8333 | 2459.4017 | #DIV/0!
|  | 0.2174 | 0.1087 | 0 | 0.1087 | 0.16667 | 55.6667 | 2171 | 1.3044
|  | 0.21739 | 0.00039893 | 0.00044878 | 0.21655 | 0 | 44.8333 | 1992.1573 | #DIV/0!
|  | 0.21737 | 0.21737 | 0 | 0 | 0.5 | 59.3333 | 2506.716 | 0.43474
|  | 0.21702 | 0 | 0 | 0.21702 | 0 | 56.3333 | 2505.1581 | #DIV/0!
|  | 0.21676 | 0 | 0.21676 | 0 | 0 | 54.1667 | 2276.4114 | #DIV/0!
|  | 0.21644 | 0.10798 | 0 | 0.10846 | 0.66667 | 81.5 | 2610.0784 | 0.32466
|  | 0.21631 | 0 | 0.21631 | 0 | 0 | 37 | 1554.9641 | #DIV/0!
|  | 0.21622 | 0.21622 | 0 | 0 | 0 | 65.3333 | 2440.7227 | #DIV/0!
|  | 0.21607 | 0 | 0 | 0.21607 | 0 | 61 | 2712.686 | #DIV/0!
|  | 0.2159 | 0.2159 | 0 | 0 | 1.5 | 86.6667 | 2761.6667 | 0.14393
|  | 0.21586 | 0 | 0.21586 | 0 | 0 | 61.5 | 2584.6024 | #DIV/0!
|  | 0.21574 | 0.0044423 | 0.00044878 | 0.21085 | 0.33333 | 42.5 | 2205.8278 | 0.64722
|  | 0.2156 | 0 | 0.1068 | 0.10881 | 0.16667 | 119.6667 | 2755.5043 | 1.2936
|  | 0.21515 | 0.10758 | 0 | 0.10758 | 0.33333 | 20.6667 | 713 | 0.64546
|  | 0.21495 | 0.21495 | 0 | 0 | 0.33333 | 59.8333 | 2156.572 | 0.64485
|  | 0.21423 | 0.21423 | 0 | 0 | 0 | 73.5 | 2745.813 | #DIV/0!
|  | 0.21362 | 0 | 0.21362 | 0 | 0 | 70.8333 | 2976.8456 | #DIV/0!
|  | 0.21362 | 0.020855 | 0 | 0.19276 | 0.16667 | 72.5 | 2977.1392 | 1.2817
|  | 0.21357 | 0.21357 | 0 | 0 | 0.16667 | 61.5 | 2433.8653 | 1.2814
|  | 0.2134 | 0.10635 | 0 | 0.10705 | 0.16667 | 120 | 2763.5784 | 1.2804
|  | 0.21317 | 0 | 0.21317 | 0 | 0 | 68.5 | 2878.7848 | #DIV/0!
|  | 0.2127 | 0.10672 | 0 | 0.10598 | 0.33333 | 114.6667 | 2185.9714 | 0.63809
|  | 0.21259 | 0 | 0.0026927 | 0.2099 | 0 | 47.6667 | 2117.7123 | #DIV/0!
|  | 0.21239 | 0.1062 | 0 | 0.10619 | 0.16667 | 41.6667 | 1874.9117 | 1.2744
|  | 0.2118 | 0 | 0 | 0.2118 | 0 | 56 | 2490.3346 | #DIV/0!
|  | 0.21132 | 0 | 0 | 0.21132 | 0 | 61.6667 | 2742.3328 | #DIV/0!
|  | 0.21093 | 0 | 0.21093 | 0 | 0 | 66 | 2773.7197 | #DIV/0!
|  | 0.21048 | 0.21048 | 0 | 0 | 1 | 68 | 2482 | 0.21048
|  | 0.21024 | 0.21024 | 0 | 0 | 0 | 40.6667 | 1519.2253 | #DIV/0!
|  | 0.2099 | 0 | 0 | 0.2099 | 0 | 46.6667 | 2075.2789 | #DIV/0!
|  | 0.2097 | 0 | 0.10142 | 0.10827 | 0 | 51 | 2206.0635 | #DIV/0!
|  | 0.20958 | 0 | 0.20958 | 0 | 0 | 52.5 | 2206.3679 | #DIV/0!
|  | 0.20958 | 0 | 0.20958 | 0 | 0 | 64.3333 | 2703.6763 | #DIV/0!
|  | 0.20948 | 0.10405 | 0.00089757 | 0.10453 | 0.33333 | 57.8333 | 2429.4204 | 0.62844
|  | 0.20947 | 0.10438 | 0 | 0.10509 | 0.16667 | 111.1667 | 2563.9901 | 1.2568
|  | 0.20862 | 0.20862 | 0 | 0 | 0.16667 | 67.5 | 2296.1193 | 1.2517
|  | 0.20845 | 0 | 0.10422 | 0.10422 | 0.33333 | 12.6667 | 506.6667 | 0.62534
|  | 0.20824 | 0 | 0.20824 | 0 | 0 | 43.8333 | 1842.1421 | #DIV/0!
|  | 0.20821 | 0.20821 | 0 | 0 | 1 | 74.1667 | 2753.1667 | 0.20821
|  | 0.20783 | 0.20783 | 0 | 0 | 0.16667 | 121.1667 | 2547.2263 | 1.247
|  | 0.20752 | 0 | 0 | 0.20752 | 0 | 50 | 2223.5131 | #DIV/0!
|  | 0.20705 | 0.20705 | 0 | 0 | 0 | 72 | 2689.776 | #DIV/0!
|  | 0.20659 | 0.20659 | 0 | 0 | 0.16667 | 63.8333 | 2170.3333 | 1.2395
|  | 0.20625 | 0.20625 | 0 | 0 | 0 | 42.8333 | 1600.1677 | #DIV/0!
|  | 0.2062 | 0.2062 | 0 | 0 | 0.16667 | 33.6667 | 2451.7263 | 1.2372
|  | 0.2061 | 0 | 0 | 0.2061 | 0 | 52.5 | 2334.6887 | #DIV/0!
|  | 0.2061 | 0 | 0 | 0.2061 | 0 | 61.1667 | 2720.0977 | #DIV/0!
|  | 0.20594 | 0.20594 | 0 | 0 | 0.16667 | 73 | 2483.1193 | 1.2356
|  | 0.20546 | 0.20546 | 0 | 0 | 0.5 | 43.5 | 2146 | 0.41092
|  | 0.20545 | 0.20545 | 0 | 0 | 0 | 69.3333 | 2590.1547 | #DIV/0!
|  | 0.20515 | 0 | 0 | 0.20515 | 0 | 46.6667 | 2075.2789 | #DIV/0!
|  | 0.20509 | 0 | 0.20509 | 0 | 0 | 45.6667 | 1919.1899 | #DIV/0!
|  | 0.20472 | 0.20472 | 0 | 0 | 0.16667 | 114.6667 | 2418.9053 | 1.2283
|  | 0.20465 | 0.20465 | 0 | 0 | 0 | 41.6667 | 1556.5833 | #DIV/0!
|  | 0.20425 | 0.20425 | 0 | 0 | 0 | 61.3333 | 2291.2907 | #DIV/0!
|  | 0.2042 | 0 | 0 | 0.2042 | 0 | 43.6667 | 1941.8681 | #DIV/0!
|  | 0.20408 | 0.10223 | 0 | 0.10186 | 0.5 | 71.5 | 2989.2351 | 0.40817
|  | 0.20386 | 0.20386 | 0 | 0 | 0 | 61.8333 | 2309.9697 | #DIV/0!
|  | 0.20379 | 0.016766 | 0.08763 | 0.099391 | 1.1667 | 97.1667 | 2186.2494 | 0.17467
|  | 0.20373 | 0 | 0 | 0.20373 | 0 | 38.1667 | 1697.2816 | #DIV/0!
|  | 0.20306 | 0.20306 | 0 | 0 | 0 | 64.3333 | 2403.3647 | #DIV/0!
|  | 0.20279 | 0.10139 | 0 | 0.10139 | 0.16667 | 52.3333 | 2355 | 1.2167
|  | 0.20266 | 0.20266 | 0 | 0 | 0 | 72 | 2689.776 | #DIV/0!
|  | 0.20221 | 0.10179 | 0 | 0.10042 | 0.16667 | 49.1667 | 2210.9615 | 1.2133
|  | 0.20186 | 0.20186 | 0 | 0 | 0 | 68.3333 | 2552.7967 | #DIV/0!
|  | 0.20186 | 0.20186 | 0 | 0 | 0 | 65 | 2428.27 | #DIV/0!
|  | 0.20183 | 0 | 0 | 0.20183 | 0 | 52.3333 | 2327.277 | #DIV/0!
|  | 0.2015 | 0.2015 | 0 | 0 | 0.33333 | 54.5 | 2396.893 | 0.6045
|  | 0.20146 | 0.20146 | 0 | 0 | 0 | 65.8333 | 2459.4017 | #DIV/0!
|  | 0.20088 | 0 | 0 | 0.20088 | 0 | 38 | 1689.8699 | #DIV/0!
|  | 0.20088 | 0 | 0 | 0.20088 | 0 | 42.8333 | 1904.8095 | #DIV/0!
|  | 0.20028 | 0 | 0.14092 | 0.05936 | 0 | 62.6667 | 2678.8506 | #DIV/0!
|  | 0.20026 | 0.20026 | 0 | 0 | 0 | 62.5 | 2334.875 | #DIV/0!
|  | 0.19987 | 0.19987 | 0 | 0 | 0.16667 | 59.8333 | 2034.893 | 1.1992
|  | 0.19907 | 0.19907 | 0 | 0 | 0 | 65.3333 | 2440.7227 | #DIV/0!
|  | 0.19898 | 0 | 0 | 0.19898 | 0 | 41.6667 | 1852.9276 | #DIV/0!
|  | 0.19895 | 0.099013 | 0.00044878 | 0.099488 | 0.5 | 46.3333 | 2345.0827 | 0.3979
|  | 0.19881 | 0 | 0.19881 | 0 | 0 | 25 | 1050.6514 | #DIV/0!
|  | 0.19867 | 0.19867 | 0 | 0 | 0 | 69.1667 | 2583.9283 | #DIV/0!
|  | 0.1985 | 0 | 0 | 0.1985 | 0 | 54.1667 | 2408.8058 | #DIV/0!
|  | 0.19848 | 0 | 0.00044878 | 0.19803 | 0 | 50 | 2223.1057 | #DIV/0!
|  | 0.19803 | 0.0032463 | 0 | 0.19478 | 0.16667 | 59.8333 | 2273.6667 | 1.1882
|  | 0.19783 | 0 | 0.088857 | 0.10898 | 1.1667 | 105 | 2355 | 0.16957
|  | 0.19731 | 0.0011106 | 0.00089757 | 0.1953 | 0.33333 | 37.3333 | 1938.4161 | 0.59193
|  | 0.19721 | 0.099013 | 0.055187 | 0.043014 | 0.16667 | 65 | 2470 | 1.1833
|  | 0.19708 | 0 | 0 | 0.19708 | 0 | 48.3333 | 2149.396 | #DIV/0!
|  | 0.19667 | 0.19667 | 0 | 0 | 0 | 60.1667 | 2247.7063 | #DIV/0!
|  | 0.19637 | 0.079118 | 0 | 0.11725 | 0.16667 | 62.6667 | 2070.6342 | 1.1782
|  | 0.19628 | 0.19628 | 0 | 0 | 0 | 51.8333 | 1936.3897 | #DIV/0!
|  | 0.19567 | 0 | 0.19567 | 0 | 0 | 57.3333 | 2409.4939 | #DIV/0!
|  | 0.19565 | 0 | 0 | 0.19565 | 0 | 26.1667 | 1163.6385 | #DIV/0!
|  | 0.19546 | 0.065311 | 0.064841 | 0.065311 | 0.16667 | 14.8333 | 652.6667 | 1.1728
|  | 0.19533 | 0.19533 | 0 | 0 | 0.16667 | 67.8333 | 2316.967 | 1.172
|  | 0.19522 | 0 | 0.19522 | 0 | 0 | 46.3333 | 1947.2073 | #DIV/0!
|  | 0.19505 | 0.19505 | 0 | 0 | 0.33333 | 52.3333 | 2340.3333 | 0.58514
|  | 0.19427 | 0.097133 | 0 | 0.097133 | 1.6667 | 80 | 3032 | 0.11656
|  | 0.19388 | 0.19388 | 0 | 0 | 0 | 60.8333 | 2272.6117 | #DIV/0!
|  | 0.19388 | 0.19388 | 0 | 0 | 0 | 63.5 | 2372.233 | #DIV/0!
|  | 0.19373 | 0.0050297 | 0.092659 | 0.096038 | 1.1667 | 111.1667 | 2500.2494 | 0.16605
|  | 0.19366 | 0.19366 | 0 | 0 | 0.16667 | 47.1667 | 1605.3457 | 1.162
|  | 0.19328 | 0 | 0 | 0.19328 | 0 | 57.5 | 2557.04 | #DIV/0!
|  | 0.19326 | 0.012814 | 0 | 0.18045 | 0.16667 | 52.5 | 2199.633 | 1.1596
|  | 0.19279 | 0.19279 | 0 | 0 | 0.16667 | 58 | 1977.037 | 1.1567
|  | 0.19269 | 0.19269 | 0 | 0 | 0 | 63.8333 | 2384.6857 | #DIV/0!
|  | 0.19266 | 0.041017 | 0.00044878 | 0.15119 | 0.16667 | 70.3333 | 2196.9564 | 1.1559
|  | 0.19261 | 0.013455 | 0.00044878 | 0.17871 | 0.16667 | 44.3333 | 1974.0211 | 1.1557
|  | 0.19258 | 0 | 0.093289 | 0.099295 | 0.16667 | 56.5 | 2206.2351 | 1.1555
|  | 0.19233 | 0 | 0 | 0.19233 | 0 | 47.5 | 2112.3374 | #DIV/0!
|  | 0.19229 | 0.19229 | 0 | 0 | 0 | 51.8333 | 1936.3897 | #DIV/0!
|  | 0.19229 | 0.19229 | 0 | 0 | 0 | 56.6667 | 2116.9533 | #DIV/0!
|  | 0.19194 | 0.097795 | 0 | 0.094143 | 0.16667 | 68.1667 | 2590.3333 | 1.1516
|  | 0.19189 | 0.19189 | 0 | 0 | 0 | 55.1667 | 2060.9163 | #DIV/0!
|  | 0.19176 | 0 | 0.10771 | 0.084054 | 0 | 59.1667 | 2541.5363 | #DIV/0!
|  | 0.1916 | 0.095766 | 0 | 0.095835 | 0.33333 | 107.1667 | 2040.4117 | 0.57481
|  | 0.19125 | 0.19125 | 0 | 0 | 0.33333 | 44.1667 | 1733.557 | 0.57376
|  | 0.1909 | 0 | 0 | 0.1909 | 0 | 47 | 2090.1023 | #DIV/0!
|  | 0.19066 | 0.19066 | 0 | 0 | 1 | 62 | 2335.3333 | 0.19066
|  | 0.19043 | 0 | 0 | 0.19043 | 0 | 39.1667 | 1741.7519 | #DIV/0!
|  | 0.19032 | 0.19032 | 0 | 0 | 0.66667 | 47 | 1809.1193 | 0.28547
|  | 0.19017 | 0.043249 | 0.078986 | 0.067931 | 0.16667 | 53 | 2308.9259 | 1.141
|  | 0.18961 | 0.096866 | 0 | 0.092744 | 0.83333 | 71.6667 | 2766.3333 | 0.22753
|  | 0.18949 | 0.18949 | 0 | 0 | 0 | 63.3333 | 2366.0067 | #DIV/0!
|  | 0.18943 | 0 | 0.00089757 | 0.18853 | 0 | 41.3333 | 1837.6968 | #DIV/0!
|  | 0.18919 | 0.18919 | 0 | 0 | 0.66667 | 32 | 937.8333 | 0.28379
|  | 0.18913 | 0.18913 | 0 | 0 | 0.16667 | 90.6667 | 2381.1083 | 1.1348
|  | 0.18907 | 0.18907 | 0 | 0 | 0.16667 | 112 | 2362.9053 | 1.1344
|  | 0.189 | 0 | 0 | 0.189 | 0 | 25.6667 | 1141.4034 | #DIV/0!
|  | 0.18874 | 0.18874 | 0 | 0 | 1 | 57 | 2130.0233 | 0.18874
|  | 0.1887 | 0.1887 | 0 | 0 | 0 | 56.8333 | 2123.1797 | #DIV/0!
|  | 0.18849 | 0.093737 | 0 | 0.094756 | 0.33333 | 128.1667 | 2447.9018 | 0.56548
|  | 0.18844 | 0.094218 | 0 | 0.094218 | 0.66667 | 61.3333 | 2652.6667 | 0.28265
|  | 0.18836 | 0.094015 | 0 | 0.094346 | 0.16667 | 87.1667 | 2702.1667 | 1.1302
|  | 0.18804 | 0 | 0.18804 | 0 | 0 | 3.3333 | 140.0869 | #DIV/0!
|  | 0.1876 | 0 | 0.16291 | 0.024694 | 0 | 43.8333 | 1858.4368 | #DIV/0!
|  | 0.18759 | 0 | 0.18759 | 0 | 0 | 56 | 2353.4591 | #DIV/0!
|  | 0.1875 | 0.1875 | 0 | 0 | 0 | 60.8333 | 2272.6117 | #DIV/0!
|  | 0.1875 | 0.1875 | 0 | 0 | 0 | 54.1667 | 2023.5583 | #DIV/0!
|  | 0.1871 | 0 | 0 | 0.1871 | 0 | 50.8333 | 2260.5716 | #DIV/0!
|  | 0.1867 | 0.1867 | 0 | 0 | 0 | 65.5 | 2446.949 | #DIV/0!
|  | 0.1867 | 0.1867 | 0 | 0 | 0 | 55 | 2054.69 | #DIV/0!
|  | 0.18624 | 0 | 0.18624 | 0 | 0 | 48.8333 | 2052.2724 | #DIV/0!
|  | 0.1859 | 0.1859 | 0 | 0 | 0 | 64 | 2390.912 | #DIV/0!
|  | 0.18589 | 0.092947 | 0 | 0.092947 | 0.16667 | 58.6667 | 1994.6667 | 1.1154
|  | 0.18586 | 0.092691 | 0 | 0.093166 | 0.16667 | 50.5 | 1567.745 | 1.1151
|  | 0.1856 | 0.092798 | 0 | 0.092798 | 2.5 | 39.6667 | 1541 | 0.074238
|  | 0.18535 | 0 | 0.18535 | 0 | 0 | 57.3333 | 2409.4939 | #DIV/0!
|  | 0.18473 | 0 | 0 | 0.18473 | 0 | 43.3333 | 1927.0447 | #DIV/0!
|  | 0.18471 | 0.18471 | 0 | 0 | 0 | 53.6667 | 2004.8793 | #DIV/0!
|  | 0.1846 | 0.092061 | 0 | 0.092536 | 0.16667 | 63.8333 | 2363.0784 | 1.1076
|  | 0.18431 | 0.18431 | 0 | 0 | 0 | 53.5 | 1998.653 | #DIV/0!
|  | 0.18423 | 0.092114 | 0 | 0.092114 | 0.33333 | 88.6667 | 1684.6667 | 0.55269
|  | 0.18395 | 0.091975 | 0 | 0.091975 | 1.6667 | 90 | 2349 | 0.11037
|  | 0.18391 | 0.18391 | 0 | 0 | 0 | 36.8333 | 1376.0197 | #DIV/0!
|  | 0.18385 | 0.18385 | 0 | 0 | 0.5 | 54.6667 | 2328.331 | 0.36771
|  | 0.18378 | 0 | 0 | 0.18378 | 0 | 51.8333 | 2305.0419 | #DIV/0!
|  | 0.18355 | 0 | 0.18355 | 0 | 0 | 56.1667 | 2360.4635 | #DIV/0!
|  | 0.18351 | 0.18351 | 0 | 0 | 0 | 61.3333 | 2291.2907 | #DIV/0!
|  | 0.18346 | 0 | 0.16874 | 0.014721 | 0 | 57 | 2407.7062 | #DIV/0!
|  | 0.18311 | 0.18311 | 0 | 0 | 0 | 60.3333 | 2253.9327 | #DIV/0!
|  | 0.18283 | 0 | 0 | 0.18283 | 0 | 54.8333 | 2438.4527 | #DIV/0!
|  | 0.18271 | 0.18271 | 0 | 0 | 0 | 40.6667 | 1519.2253 | #DIV/0!
|  | 0.18265 | 0 | 0.18265 | 0 | 0 | 52.8333 | 2220.3766 | #DIV/0!
|  | 0.18179 | 0.090897 | 0 | 0.090897 | 0.66667 | 69.3333 | 2634.6667 | 0.27269
|  | 0.18159 | 0.18159 | 0 | 0 | 0.16667 | 73.5 | 1546.2263 | 1.0896
|  | 0.18152 | 0.18152 | 0 | 0 | 0 | 48.6667 | 1818.0893 | #DIV/0!
|  | 0.18125 | 0.18125 | 0 | 0 | 0.66667 | 17.8333 | 555.5597 | 0.27188
|  | 0.18093 | 0 | 0 | 0.18093 | 0 | 39.8333 | 1771.3988 | #DIV/0!
|  | 0.18092 | 0.090459 | 0.00045918 | 0.09 | 0.16667 | 54.6667 | 2350.6667 | 1.0855
|  | 0.18052 | 0.18052 | 0 | 0 | 0.16667 | 91.3333 | 1918 | 1.0831
|  | 0.18043 | 0 | 0.00044878 | 0.17998 | 0 | 41.8333 | 1859.9319 | #DIV/0!
|  | 0.18043 | 0 | 0.18043 | 0 | 0.33333 | 36.3333 | 2398 | 0.54128
|  | 0.18043 | 0.18043 | 0 | 0 | 0.83333 | 35.8333 | 1376 | 0.21651
|  | 0.18041 | 0 | 0.18041 | 0 | 0 | 51.5 | 2164.3419 | #DIV/0!
|  | 0.18032 | 0.18032 | 0 | 0 | 0 | 29.5 | 1102.061 | #DIV/0!
|  | 0.17998 | 0.17998 | 0 | 0 | 0.16667 | 94 | 1979.4527 | 1.0799
|  | 0.17952 | 0.17952 | 0 | 0 | 0 | 56.1667 | 2098.2743 | #DIV/0!
|  | 0.17952 | 0.17952 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.17951 | 0 | 0 | 0.17951 | 0 | 45.5 | 2023.3969 | #DIV/0!
|  | 0.17903 | 0 | 0 | 0.17903 | 0 | 54 | 2401.3941 | #DIV/0!
|  | 0.17863 | 0.17863 | 0 | 0 | 0.16667 | 51 | 1734 | 1.0718
|  | 0.17862 | 0.089541 | 0 | 0.089082 | 0.16667 | 55.1667 | 2372.1667 | 1.0717
|  | 0.17862 | 0 | 0.17862 | 0 | 0 | 46.8333 | 1968.2203 | #DIV/0!
|  | 0.17862 | 0 | 0.17862 | 0 | 0 | 42.3333 | 1779.103 | #DIV/0!
|  | 0.17832 | 0.17832 | 0 | 0 | 0 | 44.8333 | 1674.8837 | #DIV/0!
|  | 0.17808 | 0 | 0 | 0.17808 | 0 | 33.6667 | 1497.1655 | #DIV/0!
|  | 0.17808 | 0 | 0 | 0.17808 | 0 | 57.3333 | 2549.6283 | #DIV/0!
|  | 0.1778 | 0.0889 | 0 | 0.0889 | 1.3333 | 47.6667 | 2145 | 0.13335
|  | 0.17772 | 0 | 0.17772 | 0 | 0 | 47.3333 | 1989.2333 | #DIV/0!
|  | 0.17753 | 0 | 0.083025 | 0.094502 | 0 | 47.1667 | 2041.7046 | #DIV/0!
|  | 0.17753 | 0.17753 | 0 | 0 | 0 | 68.6667 | 2565.2493 | #DIV/0!
|  | 0.17746 | 0.17746 | 0 | 0 | 0.16667 | 96 | 2021.4527 | 1.0648
|  | 0.17735 | 0.088676 | 0 | 0.088676 | 0.66667 | 49.3333 | 2133.6667 | 0.26603
|  | 0.17727 | 0 | 0.17727 | 0 | 0 | 38.3333 | 1610.9988 | #DIV/0!
|  | 0.17711 | 0.17711 | 0 | 0 | 0.16667 | 84 | 1766.7263 | 1.0627
|  | 0.17708 | 0.06335 | 0.00044878 | 0.11328 | 0.16667 | 39.8333 | 1784.5504 | 1.0625
|  | 0.17696 | 0.17696 | 0 | 0 | 0.16667 | 111.8333 | 2356.679 | 1.0618
|  | 0.17692 | 0.17692 | 0 | 0 | 1 | 54.5 | 2043.072 | 0.17692
|  | 0.17666 | 0 | 0 | 0.17666 | 0 | 46.6667 | 2075.2789 | #DIV/0!
|  | 0.17637 | 0 | 0.17637 | 0 | 0 | 54.5 | 2290.4201 | #DIV/0!
|  | 0.17633 | 0.17633 | 0 | 0 | 0 | 59 | 2204.122 | #DIV/0!
|  | 0.1762 | 0 | 0.1029 | 0.073298 | 0.33333 | 37.6667 | 2486 | 0.52859
|  | 0.17592 | 0 | 0.17592 | 0 | 0 | 52 | 2185.3549 | #DIV/0!
|  | 0.17553 | 0.17553 | 0 | 0 | 0 | 53.6667 | 2004.8793 | #DIV/0!
|  | 0.17497 | 0.08701 | 0 | 0.08796 | 0.33333 | 49 | 2058.8234 | 0.52491
|  | 0.17458 | 0 | 0.17458 | 0 | 0 | 48.3333 | 2031.2594 | #DIV/0!
|  | 0.17433 | 0.17433 | 0 | 0 | 0 | 60.1667 | 2247.7063 | #DIV/0!
|  | 0.17428 | 0 | 0 | 0.17428 | 0 | 41.5 | 1845.5159 | #DIV/0!
|  | 0.17428 | 0 | 0 | 0.17428 | 0 | 48.3333 | 2149.396 | #DIV/0!
|  | 0.17428 | 0.087138 | 0 | 0.087138 | 0.33333 | 1.3333 | 53.3333 | 0.52283
|  | 0.17426 | 0 | 0.00044878 | 0.17381 | 0 | 39.1667 | 1741.3445 | #DIV/0!
|  | 0.17396 | 0 | 0.086497 | 0.087458 | 0.16667 | 18.8333 | 847.5 | 1.0437
|  | 0.17381 | 0 | 0 | 0.17381 | 0 | 46 | 2045.632 | #DIV/0!
|  | 0.17366 | 0.17366 | 0 | 0 | 0.16667 | 50.8333 | 2057.0077 | 1.042
|  | 0.17338 | 0.08669 | 0 | 0.08669 | 1.6667 | 26.6667 | 1202.6667 | 0.10403
|  | 0.17333 | 0 | 0 | 0.17333 | 0 | 42.8333 | 1904.8095 | #DIV/0!
|  | 0.1733 | 0.1733 | 0 | 0 | 0.16667 | 97.6667 | 2053.7263 | 1.0398
|  | 0.17302 | 0.17302 | 0 | 0 | 0.16667 | 101.3333 | 2133.4527 | 1.0381
|  | 0.17283 | 0 | 0.085184 | 0.08765 | 0.16667 | 101.8333 | 2352.4944 | 1.037
|  | 0.17278 | 0 | 0.17278 | 0 | 0 | 50.5 | 2122.3158 | #DIV/0!
|  | 0.17219 | 0.086326 | 0 | 0.085867 | 0.16667 | 40.1667 | 1727.1667 | 1.0332
|  | 0.17195 | 0.086497 | 0 | 0.085451 | 0.5 | 54.5 | 1897.6667 | 0.3439
|  | 0.17191 | 0 | 0 | 0.17191 | 0 | 44.6667 | 1986.3383 | #DIV/0!
|  | 0.17188 | 0 | 0.00044878 | 0.17143 | 0 | 47 | 2089.6949 | #DIV/0!
|  | 0.17155 | 0.17155 | 0 | 0 | 0.16667 | 46 | 2070 | 1.0293
|  | 0.17144 | 0 | 0.17144 | 0 | 0 | 44.8333 | 1884.1682 | #DIV/0!
|  | 0.17136 | 0.00039893 | 0 | 0.17096 | 0 | 28.5 | 1266.2171 | #DIV/0!
|  | 0.17096 | 0 | 0 | 0.17096 | 0 | 46.6667 | 2075.2789 | #DIV/0!
|  | 0.17048 | 0 | 0 | 0.17048 | 0 | 31.1667 | 1385.9898 | #DIV/0!
|  | 0.17034 | 0.17034 | 0 | 0 | 0 | 27.6667 | 1033.5713 | #DIV/0!
|  | 0.16992 | 0.0011106 | 0 | 0.16881 | 0.33333 | 12 | 624 | 0.50976
|  | 0.16953 | 0 | 0 | 0.16953 | 0 | 40.5 | 1801.0456 | #DIV/0!
|  | 0.16919 | 0 | 0.16919 | 0 | 0 | 45.1667 | 1898.1769 | #DIV/0!
|  | 0.16898 | 0.00039893 | 0 | 0.16858 | 0 | 47.1667 | 2096.3286 | #DIV/0!
|  | 0.16875 | 0.16875 | 0 | 0 | 0 | 49 | 1830.542 | #DIV/0!
|  | 0.16858 | 0 | 0 | 0.16858 | 0 | 50 | 2223.5131 | #DIV/0!
|  | 0.16847 | 0.083998 | 0 | 0.084473 | 0.33333 | 60.8333 | 2100.4117 | 0.50542
|  | 0.16845 | 0.085504 | 0 | 0.082941 | 1.1667 | 66 | 2629 | 0.14438
|  | 0.16834 | 0.058263 | 0.051396 | 0.058679 | 1.5 | 64.8333 | 2456.8333 | 0.11223
|  | 0.16811 | 0 | 0 | 0.16811 | 0 | 47.1667 | 2097.514 | #DIV/0!
|  | 0.168 | 0.168 | 0 | 0 | 0.5 | 30 | 920 | 0.33599
|  | 0.16795 | 0.16795 | 0 | 0 | 0 | 56 | 2092.048 | #DIV/0!
|  | 0.16785 | 0.083924 | 0 | 0.083924 | 1.8333 | 49 | 2187 | 0.091553
|  | 0.16763 | 0 | 0 | 0.16763 | 0 | 7.6667 | 340.9387 | #DIV/0!
|  | 0.16751 | 0.16751 | 0 | 0 | 0.83333 | 68 | 2136.2263 | 0.20101
|  | 0.16747 | 0.16747 | 0 | 0 | 0.16667 | 82.1667 | 1747.3107 | 1.0048
|  | 0.16708 | 0.00039893 | 0 | 0.16668 | 0 | 50.8333 | 2259.3863 | #DIV/0!
|  | 0.16675 | 0.16675 | 0 | 0 | 0 | 59.1667 | 2210.3483 | #DIV/0!
|  | 0.16668 | 0 | 0.083422 | 0.083262 | 0.16667 | 80.5 | 1857.842 | 1.0001
|  | 0.16573 | 0 | 0 | 0.16573 | 0 | 43.8333 | 1949.2798 | #DIV/0!
|  | 0.16573 | 0 | 0 | 0.16573 | 0 | 47 | 2090.1023 | #DIV/0!
|  | 0.16522 | 0.16522 | 0 | 0 | 0.16667 | 47 | 2113.7263 | 0.99135
|  | 0.165 | 0.165 | 0 | 0 | 0.16667 | 40.1667 | 846.2263 | 0.99
|  | 0.16476 | 0.16476 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.16456 | 0.00024561 | 0.08056 | 0.083753 | 0.16667 | 92.3333 | 2123.6667 | 0.98735
|  | 0.16436 | 0.16436 | 0 | 0 | 0 | 51 | 1905.258 | #DIV/0!
|  | 0.16431 | 0 | 0 | 0.16431 | 0 | 44.8333 | 1993.7501 | #DIV/0!
|  | 0.16431 | 0 | 0 | 0.16431 | 0 | 50 | 2223.5131 | #DIV/0!
|  | 0.16426 | 0 | 0.00089757 | 0.16336 | 0 | 40.3333 | 1792.8191 | #DIV/0!
|  | 0.16394 | 0.08197 | 0 | 0.08197 | 0.5 | 50 | 1683.3333 | 0.32788
|  | 0.16383 | 0 | 0 | 0.16383 | 0 | 39.8333 | 1771.3988 | #DIV/0!
|  | 0.16381 | 0 | 0.16381 | 0 | 0 | 50 | 2101.3028 | #DIV/0!
|  | 0.16378 | 0.16378 | 0 | 0 | 0.33333 | 20.8333 | 884.5597 | 0.49135
|  | 0.16356 | 0.16356 | 0 | 0 | 0 | 56.5 | 2110.727 | #DIV/0!
|  | 0.16351 | 0 | 0.16066 | 0.0028493 | 0 | 47 | 1976.8541 | #DIV/0!
|  | 0.16336 | 0 | 0 | 0.16336 | 0 | 32.8333 | 1460.1069 | #DIV/0!
|  | 0.16316 | 0.16316 | 0 | 0 | 0 | 56.5 | 2110.727 | #DIV/0!
|  | 0.16316 | 0.16316 | 0 | 0 | 0 | 50.8333 | 1899.0317 | #DIV/0!
|  | 0.16289 | 0 | 0 | 0.16289 | 0 | 37.5 | 1667.6348 | #DIV/0!
|  | 0.16274 | 0.16274 | 0 | 0 | 0.33333 | 24.8333 | 1753.3457 | 0.48823
|  | 0.16257 | 0.16257 | 0 | 0 | 0.16667 | 45.3333 | 1994.6667 | 0.97543
|  | 0.16241 | 0 | 0 | 0.16241 | 0 | 28.5 | 1267.4025 | #DIV/0!
|  | 0.16241 | 0 | 0 | 0.16241 | 0 | 45.5 | 2023.3969 | #DIV/0!
|  | 0.16204 | 0.16204 | 0 | 0 | 0.16667 | 95.6667 | 2014.4527 | 0.97221
|  | 0.16194 | 0 | 0 | 0.16194 | 0 | 56.5 | 2512.5698 | #DIV/0!
|  | 0.16157 | 0 | 0.16157 | 0 | 0.16667 | 35.6667 | 823.5043 | 0.96941
|  | 0.16146 | 0 | 0.080304 | 0.081158 | 0.33333 | 39 | 1560 | 0.48438
|  | 0.16123 | 0.080613 | 0 | 0.080613 | 1.5 | 61 | 2385 | 0.10748
|  | 0.16099 | 0 | 0 | 0.16099 | 0 | 38 | 1689.8699 | #DIV/0!
|  | 0.16099 | 0 | 0 | 0.16099 | 0 | 48 | 2134.5726 | #DIV/0!
|  | 0.16069 | 0.080346 | 0 | 0.080346 | 0.33333 | 78.6667 | 1494.6667 | 0.48208
|  | 0.16037 | 0.16037 | 0 | 0 | 0 | 56.6667 | 2116.9533 | #DIV/0!
|  | 0.16037 | 0.16037 | 0 | 0 | 0 | 51.3333 | 1917.7107 | #DIV/0!
|  | 0.15997 | 0.15997 | 0 | 0 | 0 | 51.6667 | 1930.1633 | #DIV/0!
|  | 0.1598 | 0.079898 | 0 | 0.079898 | 0.16667 | 40.6667 | 1748.6667 | 0.95877
|  | 0.15957 | 0.15957 | 0 | 0 | 0 | 49.3333 | 1842.9947 | #DIV/0!
|  | 0.15954 | 0.15954 | 0 | 0 | 0.16667 | 40.6667 | 1830 | 0.95724
|  | 0.15947 | 0.15947 | 0 | 0 | 0.16667 | 77.3333 | 1472.393 | 0.95681
|  | 0.15917 | 0.15917 | 0 | 0 | 0 | 27.1667 | 1014.8923 | #DIV/0!
|  | 0.15909 | 0 | 0 | 0.15909 | 0 | 48.6667 | 2164.2194 | #DIV/0!
|  | 0.15896 | 0.079585 | 0 | 0.079374 | 0.16667 | 57.8333 | 1968.638 | 0.95375
|  | 0.15878 | 0.15878 | 0 | 0 | 0 | 44.5 | 1662.431 | #DIV/0!
|  | 0.15854 | 0.079485 | 0 | 0.079054 | 0.16667 | 82 | 1895.5498 | 0.95123
|  | 0.15842 | 0 | 0.15842 | 0 | 0 | 51.5 | 2164.3419 | #DIV/0!
|  | 0.15838 | 0.15838 | 0 | 0 | 0 | 49 | 1830.542 | #DIV/0!
|  | 0.15814 | 0 | 0 | 0.15814 | 0 | 43 | 1912.2212 | #DIV/0!
|  | 0.15805 | 0.078787 | 0 | 0.079262 | 1 | 60.1667 | 2177.4117 | 0.15805
|  | 0.15804 | 0.15804 | 0 | 0 | 0.83333 | 45.8333 | 1833.3333 | 0.18965
|  | 0.15797 | 0 | 0.15797 | 0 | 0 | 44.5 | 1870.1595 | #DIV/0!
|  | 0.15787 | 0.15787 | 0 | 0 | 0.33333 | 45.6667 | 1918 | 0.47362
|  | 0.15758 | 0.15758 | 0 | 0 | 0 | 54 | 2017.332 | #DIV/0!
|  | 0.15758 | 0.15758 | 0 | 0 | 0 | 54 | 2017.332 | #DIV/0!
|  | 0.15752 | 0 | 0.15752 | 0 | 0 | 28.8333 | 1211.7513 | #DIV/0!
|  | 0.15752 | 0 | 0.077495 | 0.08002 | 0.16667 | 40 | 1561.4161 | 0.94509
|  | 0.15719 | 0 | 0 | 0.15719 | 0 | 39.6667 | 1763.987 | #DIV/0!
|  | 0.15707 | 0 | 0.15707 | 0 | 0 | 42.1667 | 1772.0987 | #DIV/0!
|  | 0.15678 | 0 | 0.15393 | 0.0028493 | 0 | 17.5 | 737.9002 | #DIV/0!
|  | 0.15638 | 0.15638 | 0 | 0 | 0 | 54.1667 | 2023.5583 | #DIV/0!
|  | 0.15638 | 0.15638 | 0 | 0 | 0 | 54 | 2017.332 | #DIV/0!
|  | 0.15638 | 0.15638 | 0 | 0 | 0 | 49.8333 | 1861.6737 | #DIV/0!
|  | 0.15618 | 0 | 0.15618 | 0 | 0 | 45.1667 | 1898.1769 | #DIV/0!
|  | 0.15576 | 0 | 0 | 0.15576 | 0 | 42.6667 | 1897.3978 | #DIV/0!
|  | 0.15574 | 0 | 0.077442 | 0.078296 | 0.66667 | 54.3333 | 2190.6667 | 0.23361
|  | 0.15558 | 0.15558 | 0 | 0 | 0 | 54.8333 | 2048.4637 | #DIV/0!
|  | 0.15558 | 0.15558 | 0 | 0 | 0 | 52.1667 | 1948.8423 | #DIV/0!
|  | 0.15538 | 0.15538 | 0 | 0 | 0.16667 | 28.8333 | 1266.4527 | 0.93229
|  | 0.155 | 0.155 | 0 | 0 | 0.83333 | 46.1667 | 1846.5 | 0.186
|  | 0.15434 | 0 | 0 | 0.15434 | 0 | 40 | 1778.8105 | #DIV/0!
|  | 0.15426 | 0.15426 | 0 | 0 | 0.16667 | 29.5 | 914.5 | 0.92559
|  | 0.1542 | 0.1542 | 0 | 0 | 0.16667 | 48.1667 | 1673.31 | 0.92521
|  | 0.15419 | 0.15419 | 0 | 0 | 0.16667 | 75.1667 | 1583.9527 | 0.92512
|  | 0.15399 | 0.15399 | 0 | 0 | 0 | 50.6667 | 1892.8053 | #DIV/0!
|  | 0.15399 | 0.15399 | 0 | 0 | 0 | 47 | 1755.826 | #DIV/0!
|  | 0.15399 | 0.077741 | 0 | 0.076246 | 0.5 | 44.5 | 2076.6667 | 0.30797
|  | 0.15397 | 0 | 0.075797 | 0.078172 | 0.16667 | 42.1667 | 1645.4117 | 0.92381
|  | 0.15386 | 0 | 0 | 0.15386 | 0 | 23.8333 | 1059.8746 | #DIV/0!
|  | 0.15386 | 0 | 0 | 0.15386 | 0 | 34.6667 | 1541.6357 | #DIV/0!
|  | 0.15386 | 0 | 0 | 0.15386 | 0 | 44 | 1956.6915 | #DIV/0!
|  | 0.15348 | 0 | 0.15348 | 0 | 0 | 56.8333 | 2388.4809 | #DIV/0!
|  | 0.15348 | 0 | 0.15348 | 0 | 0 | 36.6667 | 1540.9554 | #DIV/0!
|  | 0.15338 | 0 | 0.0736 | 0.07978 | 0 | 39.8333 | 1723.3294 | #DIV/0!
|  | 0.15331 | 0.00039893 | 0 | 0.15291 | 0 | 45 | 1999.9764 | #DIV/0!
|  | 0.15297 | 0.15297 | 0 | 0 | 0.5 | 46.8333 | 1949.9527 | 0.30594
|  | 0.15253 | 0.076086 | 0 | 0.076448 | 0.33333 | 61.5 | 1694.9117 | 0.4576
|  | 0.15244 | 0 | 0 | 0.15244 | 0 | 24.6667 | 1096.9331 | #DIV/0!
|  | 0.15201 | 0.15201 | 0 | 0 | 1 | 41 | 1496.5 | 0.15201
|  | 0.15196 | 0 | 0 | 0.15196 | 0 | 44.3333 | 1971.5149 | #DIV/0!
|  | 0.15184 | 0.15184 | 0 | 0 | 0.16667 | 44.8333 | 1646.9003 | 0.91105
|  | 0.15169 | 0 | 0.15169 | 0 | 0 | 38.6667 | 1625.0075 | #DIV/0!
|  | 0.1515 | 0.1515 | 0 | 0 | 0.16667 | 79.3333 | 1671.4527 | 0.90897
|  | 0.15121 | 0.061595 | 0 | 0.089613 | 1.6667 | 37.5 | 1569.527 | 0.090724
|  | 0.1512 | 0.1512 | 0 | 0 | 0 | 24.8333 | 927.7237 | #DIV/0!
|  | 0.15108 | 0.15108 | 0 | 0 | 0.16667 | 44.3333 | 1507.893 | 0.90645
|  | 0.15099 | 0 | 0.00044878 | 0.15054 | 0 | 40.3333 | 1793.2265 | #DIV/0!
|  | 0.15036 | 0.075178 | 0 | 0.075178 | 0.16667 | 36 | 1584 | 0.90213
|  | 0.15036 | 0.15036 | 0 | 0 | 0.33333 | 34.6667 | 1525.3333 | 0.45107
|  | 0.15015 | 0.075306 | 0 | 0.074847 | 0.16667 | 38.5 | 1655.5 | 0.90092
|  | 0.15006 | 0 | 0 | 0.15006 | 0 | 42.3333 | 1882.5744 | #DIV/0!
|  | 0.15 | 0.15 | 0 | 0 | 0 | 52.6667 | 1967.5213 | #DIV/0!
|  | 0.15 | 0.15 | 0 | 0 | 0 | 43.3333 | 1618.8467 | #DIV/0!
|  | 0.14989 | 0 | 0.14989 | 0 | 0 | 25 | 1050.6514 | #DIV/0!
|  | 0.14977 | 0.074658 | 0.00044878 | 0.074665 | 0.16667 | 53 | 2014.564 | 0.89864
|  | 0.14971 | 0.14971 | 0 | 0 | 0.16667 | 73.5 | 1405.679 | 0.89825
|  | 0.1496 | 0.1496 | 0 | 0 | 0 | 54.5 | 2036.011 | #DIV/0!
|  | 0.14959 | 0 | 0 | 0.14959 | 0 | 14.5 | 644.8188 | #DIV/0!
|  | 0.14944 | 0 | 0.14944 | 0 | 0 | 40.3333 | 1695.0509 | #DIV/0!
|  | 0.14937 | 0.14937 | 0 | 0 | 1.5 | 70.5 | 2107.1667 | 0.099582
|  | 0.14911 | 0 | 0 | 0.14911 | 0 | 42.8333 | 1904.8095 | #DIV/0!
|  | 0.14903 | 0.0067596 | 0.060068 | 0.082204 | 0.33333 | 39.1667 | 1748.5 | 0.44709
|  | 0.14883 | 0 | 0.072498 | 0.076331 | 0.16667 | 40.8333 | 1594.8278 | 0.89297
|  | 0.1488 | 0.1488 | 0 | 0 | 0 | 46.8333 | 1749.5997 | #DIV/0!
|  | 0.14802 | 0.14802 | 0 | 0 | 0.16667 | 42.6667 | 1452.3457 | 0.88814
|  | 0.14801 | 0 | 0.0026927 | 0.14531 | 0 | 41 | 1822.466 | #DIV/0!
|  | 0.14769 | 0 | 0 | 0.14769 | 0 | 37 | 1645.3997 | #DIV/0!
|  | 0.14769 | 0 | 0 | 0.14769 | 0 | 43.1667 | 1919.633 | #DIV/0!
|  | 0.14764 | 0.074153 | 0 | 0.073491 | 0.16667 | 68 | 2108 | 0.88586
|  | 0.14759 | 0.0089205 | 0.00089757 | 0.13777 | 0.33333 | 61.3333 | 1180.7208 | 0.44276
|  | 0.14731 | 0.00041647 | 0.070448 | 0.076447 | 0.16667 | 42 | 1642.6555 | 0.88387
|  | 0.14721 | 0.14721 | 0 | 0 | 0 | 46.5 | 1737.147 | #DIV/0!
|  | 0.14721 | 0.14721 | 0 | 0 | 0 | 31.5 | 1176.777 | #DIV/0!
|  | 0.14714 | 0.065108 | 0.016445 | 0.065583 | 0.5 | 25.6667 | 1339.4117 | 0.29427
|  | 0.14672 | 0.14672 | 0 | 0 | 0.16667 | 18.8333 | 584.893 | 0.88031
|  | 0.14656 | 0.14656 | 0 | 0 | 0.16667 | 68.6667 | 1447.4527 | 0.87937
|  | 0.14644 | 0 | 0.070459 | 0.075981 | 0 | 36.5 | 1579.1688 | #DIV/0!
|  | 0.14601 | 0.14601 | 0 | 0 | 0 | 45.6667 | 1706.0153 | #DIV/0!
|  | 0.14601 | 0.14601 | 0 | 0 | 0 | 20.8333 | 778.2917 | #DIV/0!
|  | 0.14601 | 0.14601 | 0 | 0 | 0 | 28.6667 | 1070.9293 | #DIV/0!
|  | 0.14597 | 0 | 0.070459 | 0.075507 | 0 | 38.3333 | 1658.2535 | #DIV/0!
|  | 0.14585 | 0 | 0.14585 | 0 | 0 | 44.6667 | 1877.1638 | #DIV/0!
|  | 0.14579 | 0 | 0 | 0.14579 | 0 | 33.5 | 1489.7538 | #DIV/0!
|  | 0.14579 | 0 | 0 | 0.14579 | 0 | 40.6667 | 1808.4573 | #DIV/0!
|  | 0.14566 | 0.072829 | 0 | 0.072829 | 0.16667 | 39.3333 | 1730.6667 | 0.87394
|  | 0.14498 | 0.072017 | 0 | 0.072967 | 1 | 37.5 | 1628.0784 | 0.14498
|  | 0.14496 | 0 | 0.14496 | 0 | 0 | 28.3333 | 1190.7383 | #DIV/0!
|  | 0.14484 | 0 | 0 | 0.14484 | 0 | 45.6667 | 2030.8086 | #DIV/0!
|  | 0.14481 | 0.14481 | 0 | 0 | 0 | 43.8333 | 1637.5257 | #DIV/0!
|  | 0.14467 | 0 | 0.070843 | 0.073832 | 0.16667 | 52 | 1312.1654 | 0.86805
|  | 0.14436 | 0 | 0 | 0.14436 | 0 | 42.8333 | 1904.8095 | #DIV/0!
|  | 0.14425 | 0.14425 | 0 | 0 | 0.16667 | 70.8333 | 1348.893 | 0.86551
|  | 0.14425 | 0.14425 | 0 | 0 | 0.16667 | 31.6667 | 1393.3333 | 0.86549
|  | 0.14389 | 0 | 0 | 0.14389 | 0 | 40 | 1778.8105 | #DIV/0!
|  | 0.14362 | 0.14362 | 0 | 0 | 0 | 46.6667 | 1743.3733 | #DIV/0!
|  | 0.14362 | 0.14362 | 0 | 0 | 0 | 42.3333 | 1581.4887 | #DIV/0!
|  | 0.1432 | 0.071601 | 0 | 0.071601 | 0.16667 | 14.6667 | 660 | 0.85921
|  | 0.14293 | 0.046666 | 0.049366 | 0.046895 | 0.16667 | 61.1667 | 1686.2895 | 0.85756
|  | 0.14284 | 0 | 0.09963 | 0.043214 | 0 | 46.6667 | 1991.7685 | #DIV/0!
|  | 0.14278 | 0.023749 | 0.04862 | 0.070415 | 1.1667 | 71.3333 | 1600.5 | 0.12239
|  | 0.14221 | 0 | 0.094244 | 0.047963 | 0 | 31.3333 | 1352.6648 | #DIV/0!
|  | 0.14215 | 0.14215 | 0 | 0 | 0.5 | 43.8333 | 1822.7983 | 0.2843
|  | 0.14202 | 0.14202 | 0 | 0 | 0 | 41.5 | 1550.357 | #DIV/0!
|  | 0.14193 | 0.14193 | 0 | 0 | 1 | 57.1667 | 2177 | 0.14193
|  | 0.14157 | 0.066622 | 0.074947 | 0 | 0 | 17.3333 | 687.9952 | #DIV/0!
|  | 0.14143 | 0.14143 | 0 | 0 | 0.16667 | 34.1667 | 1469.1667 | 0.84857
|  | 0.14106 | 0.14106 | 0 | 0 | 0.16667 | 47.8333 | 1769.893 | 0.84635
|  | 0.14104 | 0 | 0 | 0.14104 | 0 | 34.5 | 1534.224 | #DIV/0!
|  | 0.14042 | 0.14042 | 0 | 0 | 0 | 45.8333 | 1712.2417 | #DIV/0!
|  | 0.14032 | 0.02077 | 0 | 0.11955 | 0.5 | 40 | 1660.9907 | 0.28063
|  | 0.14023 | 0.069839 | 0 | 0.070393 | 0.33333 | 50.5 | 1749.6568 | 0.4207
|  | 0.14016 | 0.14016 | 0 | 0 | 0.66667 | 58.6667 | 1540 | 0.21024
|  | 0.14003 | 0.14003 | 0 | 0 | 0 | 37.5 | 1400.925 | #DIV/0!
|  | 0.14002 | 0 | 0.14002 | 0 | 0 | 32.3333 | 1358.8425 | #DIV/0!
|  | 0.13993 | 0.13993 | 0 | 0 | 0.83333 | 37.5 | 1755 | 0.16792
|  | 0.13963 | 0.13963 | 0 | 0 | 0 | 41 | 1531.678 | #DIV/0!
|  | 0.13963 | 0.13963 | 0 | 0 | 0 | 39 | 1456.962 | #DIV/0!
|  | 0.13957 | 0 | 0.13957 | 0 | 0 | 33 | 1386.8598 | #DIV/0!
|  | 0.1394 | 0.1394 | 0 | 0 | 0.5 | 50 | 2033.3333 | 0.2788
|  | 0.1393 | 0.1393 | 0 | 0 | 0.5 | 58.1667 | 1888.4393 | 0.2786
|  | 0.1392 | 0.049335 | 0.042288 | 0.047574 | 0.33333 | 56.6667 | 1558.3333 | 0.41759
|  | 0.13914 | 0 | 0 | 0.13914 | 0 | 29.5 | 1311.8727 | #DIV/0!
|  | 0.13883 | 0.13883 | 0 | 0 | 0 | 49.8333 | 1861.6737 | #DIV/0!
|  | 0.13883 | 0.13883 | 0 | 0 | 0 | 34 | 1270.172 | #DIV/0!
|  | 0.13823 | 0 | 0.13823 | 0 | 0 | 41.1667 | 1730.0726 | #DIV/0!
|  | 0.13819 | 0 | 0 | 0.13819 | 0 | 39.3333 | 1749.1636 | #DIV/0!
|  | 0.13814 | 0.06907 | 0 | 0.06907 | 0.5 | 52 | 1698.6667 | 0.27628
|  | 0.13809 | 0.13809 | 0 | 0 | 0.83333 | 61.3333 | 1842.8553 | 0.16571
|  | 0.13803 | 0.13803 | 0 | 0 | 0 | 44.3333 | 1656.2047 | #DIV/0!
|  | 0.13772 | 0 | 0 | 0.13772 | 0 | 29.6667 | 1319.2844 | #DIV/0!
|  | 0.13771 | 0.0044423 | 0 | 0.13327 | 0.33333 | 32.6667 | 1698.6667 | 0.41314
|  | 0.13771 | 0.0033317 | 0 | 0.13438 | 0.33333 | 26.3333 | 1369.3333 | 0.41314
|  | 0.13752 | 0.13752 | 0 | 0 | 0.33333 | 42.1667 | 1454.3457 | 0.41256
|  | 0.13736 | 0.13736 | 0 | 0 | 0.16667 | 69.3333 | 1317.3333 | 0.82416
|  | 0.13733 | 0 | 0.13733 | 0 | 0 | 43.5 | 1828.1334 | #DIV/0!
|  | 0.13726 | 0 | 0.067116 | 0.070142 | 0.16667 | 40.5 | 1581.8278 | 0.82355
|  | 0.13724 | 0 | 0 | 0.13724 | 0 | 13.8333 | 615.172 | #DIV/0!
|  | 0.13724 | 0 | 0 | 0.13724 | 0 | 38.5 | 1712.1051 | #DIV/0!
|  | 0.13717 | 0 | 0.13717 | 0 | 0.16667 | 61.8333 | 1431.6797 | 0.82301
|  | 0.13708 | 0.0033317 | 0 | 0.13374 | 0.33333 | 32.8333 | 1706.0784 | 0.41123
|  | 0.13688 | 0 | 0.13688 | 0 | 0 | 37.8333 | 1589.9858 | #DIV/0!
|  | 0.13688 | 0 | 0.13688 | 0 | 0 | 28.5 | 1197.7426 | #DIV/0!
|  | 0.13683 | 0.13683 | 0 | 0 | 0 | 42.6667 | 1593.9413 | #DIV/0!
|  | 0.13677 | 0 | 0 | 0.13677 | 0 | 10 | 444.7026 | #DIV/0!
|  | 0.13675 | 0.13675 | 0 | 0 | 0.16667 | 78.6667 | 1668.358 | 0.82048
|  | 0.13662 | 0 | 0.067766 | 0.068858 | 0 | 32.5 | 1407.8057 | #DIV/0!
|  | 0.13643 | 0 | 0.13643 | 0 | 0 | 44.1667 | 1856.1508 | #DIV/0!
|  | 0.13642 | 0.068159 | 0.068259 | 0 | 0.16667 | 52 | 1977.128 | 0.81851
|  | 0.13629 | 0 | 0 | 0.13629 | 0 | 35.6667 | 1586.106 | #DIV/0!
|  | 0.13615 | 0.13615 | 0 | 0 | 0.16667 | 28.8333 | 980.3333 | 0.81692
|  | 0.13604 | 0.13604 | 0 | 0 | 0 | 28.5 | 1064.703 | #DIV/0!
|  | 0.13593 | 0.13593 | 0 | 0 | 0.16667 | 69.5 | 1323.5597 | 0.8156
|  | 0.13564 | 0.13564 | 0 | 0 | 0 | 50.6667 | 1892.8053 | #DIV/0!
|  | 0.13564 | 0.13564 | 0 | 0 | 0 | 44.6667 | 1668.6573 | #DIV/0!
|  | 0.13564 | 0.13564 | 0 | 0 | 0 | 38.8333 | 1450.7357 | #DIV/0!
|  | 0.13553 | 0 | 0.13553 | 0 | 0 | 43.3333 | 1821.1291 | #DIV/0!
|  | 0.13543 | 0 | 0.067938 | 0.067489 | 0.33333 | 45.5 | 1820.3377 | 0.40628
|  | 0.13524 | 0.13524 | 0 | 0 | 0 | 16.6667 | 622.6333 | #DIV/0!
|  | 0.135 | 0.0675 | 0 | 0.0675 | 0.16667 | 44.3333 | 1906.3333 | 0.81
|  | 0.13497 | 0.13497 | 0 | 0 | 0.16667 | 33.8333 | 1487.5597 | 0.80979
|  | 0.13491 | 0.13491 | 0 | 0 | 0.16667 | 69.1667 | 1320.286 | 0.80947
|  | 0.13484 | 0.13484 | 0 | 0 | 0 | 40.3333 | 1506.7727 | #DIV/0!
|  | 0.13484 | 0.13484 | 0 | 0 | 0 | 44.3333 | 1656.2047 | #DIV/0!
|  | 0.13444 | 0.13444 | 0 | 0 | 0 | 36.5 | 1363.567 | #DIV/0!
|  | 0.1344 | 0.1344 | 0 | 0 | 0.16667 | 46.5 | 1441.5 | 0.80641
|  | 0.13439 | 0 | 0 | 0.13439 | 0 | 41.6667 | 1852.9276 | #DIV/0!
|  | 0.13404 | 0.13404 | 0 | 0 | 0 | 44.3333 | 1656.2047 | #DIV/0!
|  | 0.13373 | 0.13373 | 0 | 0 | 0.16667 | 67.6667 | 1426.4527 | 0.80238
|  | 0.13364 | 0.13364 | 0 | 0 | 0 | 49.8333 | 1861.6737 | #DIV/0!
|  | 0.13361 | 0.13361 | 0 | 0 | 0.33333 | 24.3333 | 1119.3333 | 0.40083
|  | 0.13355 | 0.13355 | 0 | 0 | 0.16667 | 41.5 | 1567.283 | 0.80132
|  | 0.13348 | 0.13348 | 0 | 0 | 0.5 | 0.5 | 20.8333 | 0.26697
|  | 0.13329 | 0 | 0.13329 | 0 | 0 | 35.3333 | 1484.9206 | #DIV/0!
|  | 0.13324 | 0.13324 | 0 | 0 | 0 | 41.3333 | 1544.1307 | #DIV/0!
|  | 0.13324 | 0.13324 | 0 | 0 | 0 | 30.6667 | 1145.6453 | #DIV/0!
|  | 0.13323 | 0.13323 | 0 | 0 | 0.16667 | 84.3333 | 1781.9053 | 0.79939
|  | 0.13249 | 0 | 0 | 0.13249 | 0 | 25.1667 | 1119.1682 | #DIV/0!
|  | 0.13249 | 0 | 0 | 0.13249 | 0 | 37.1667 | 1652.8114 | #DIV/0!
|  | 0.13249 | 0 | 0 | 0.13249 | 0 | 36.5 | 1623.1645 | #DIV/0!
|  | 0.13245 | 0.13245 | 0 | 0 | 0 | 41.8333 | 1562.8097 | #DIV/0!
|  | 0.13235 | 0.015014 | 0.10232 | 0.015014 | 0.16667 | 46.3333 | 1890.2453 | 0.79411
|  | 0.13205 | 0.13205 | 0 | 0 | 0 | 48.6667 | 1818.0893 | #DIV/0!
|  | 0.13194 | 0 | 0.13194 | 0 | 0 | 36.1667 | 1519.9424 | #DIV/0!
|  | 0.13194 | 0 | 0.13194 | 0 | 0 | 27.8333 | 1169.7252 | #DIV/0!
|  | 0.13189 | 0.13189 | 0 | 0 | 0.33333 | 21.3333 | 736 | 0.39568
|  | 0.13154 | 0 | 0 | 0.13154 | 0 | 22.6667 | 1007.9926 | #DIV/0!
|  | 0.13154 | 0 | 0 | 0.13154 | 0 | 26.5 | 1178.4619 | #DIV/0!
|  | 0.13152 | 0 | 0.00044878 | 0.13107 | 0 | 32.8333 | 1459.6996 | #DIV/0!
|  | 0.1314 | 0 | 0.1314 | 0 | 0.16667 | 19.1667 | 440.8333 | 0.78841
|  | 0.13102 | 0.13102 | 0 | 0 | 0.16667 | 33.8333 | 1519.9527 | 0.78615
|  | 0.13087 | 0.13087 | 0 | 0 | 0.16667 | 66.8333 | 1269.8333 | 0.7852
|  | 0.13059 | 0 | 0 | 0.13059 | 0 | 34.3333 | 1526.8123 | #DIV/0!
|  | 0.13045 | 0.13045 | 0 | 0 | 0 | 48 | 1793.184 | #DIV/0!
|  | 0.13042 | 0.065332 | 0 | 0.065087 | 0.16667 | 65.8333 | 1514.1667 | 0.78251
|  | 0.13012 | 0 | 0 | 0.13012 | 0 | 37.3333 | 1660.2231 | #DIV/0!
|  | 0.13012 | 0 | 0 | 0.13012 | 0 | 37.3333 | 1660.2231 | #DIV/0!
|  | 0.13012 | 0 | 0 | 0.13012 | 0 | 38.8333 | 1726.9285 | #DIV/0!
|  | 0.13009 | 0 | 0.00044878 | 0.12964 | 0 | 10.3333 | 459.1187 | #DIV/0!
|  | 0.12994 | 0.043313 | 0.043313 | 0.043313 | 1.3333 | 52 | 2028 | 0.097454
|  | 0.1297 | 0 | 0.1297 | 0 | 0 | 38.8333 | 1632.0118 | #DIV/0!
|  | 0.12966 | 0.12966 | 0 | 0 | 0.16667 | 36.6667 | 1436.557 | 0.77794
|  | 0.12944 | 0.12944 | 0 | 0 | 0.16667 | 12.3333 | 382.3333 | 0.77662
|  | 0.12924 | 0.028736 | 0 | 0.1005 | 0.16667 | 41.6667 | 1746.2575 | 0.77543
|  | 0.12917 | 0 | 0 | 0.12917 | 0 | 24 | 1067.2863 | #DIV/0!
|  | 0.12917 | 0 | 0 | 0.12917 | 0 | 36.6667 | 1630.5763 | #DIV/0!
|  | 0.12835 | 0 | 0.12835 | 0 | 0 | 37.5 | 1575.9771 | #DIV/0!
|  | 0.12814 | 0.00039893 | 0 | 0.12774 | 0 | 32.5 | 1444.0981 | #DIV/0!
|  | 0.12793 | 0.063079 | 0 | 0.064855 | 0.66667 | 61.8333 | 1753.3919 | 0.1919
|  | 0.12767 | 0.00039893 | 0 | 0.12727 | 0 | 32.3333 | 1436.6864 | #DIV/0!
|  | 0.12766 | 0.12766 | 0 | 0 | 0 | 37.5 | 1400.925 | #DIV/0!
|  | 0.12756 | 0.063303 | 0 | 0.064253 | 0.5 | 71.3333 | 1245.4901 | 0.25511
|  | 0.12755 | 0.12755 | 0 | 0 | 0.16667 | 41 | 1558.9477 | 0.76533
|  | 0.1275 | 0.1275 | 0 | 0 | 0.16667 | 44.8333 | 1672.676 | 0.76499
|  | 0.12745 | 0 | 0.12745 | 0 | 0 | 36.8333 | 1547.9597 | #DIV/0!
|  | 0.12742 | 0.0016766 | 0.062032 | 0.063709 | 1.1667 | 60.6667 | 1360.6667 | 0.10922
|  | 0.12686 | 0.12686 | 0 | 0 | 0.16667 | 31.3333 | 1378.6667 | 0.76118
|  | 0.12677 | 0 | 0.00044878 | 0.12632 | 0 | 38.5 | 1711.6977 | #DIV/0!
|  | 0.12673 | 0.063367 | 0 | 0.063367 | 0.16667 | 37 | 1591 | 0.76041
|  | 0.12633 | 0.063164 | 0 | 0.063164 | 0.33333 | 48 | 1560 | 0.37899
|  | 0.12632 | 0 | 0 | 0.12632 | 0 | 31.8333 | 1415.6367 | #DIV/0!
|  | 0.12632 | 0 | 0 | 0.12632 | 0 | 35.1667 | 1563.8709 | #DIV/0!
|  | 0.1261 | 0.1261 | 0 | 0 | 0.66667 | 27.6667 | 988.7117 | 0.18914
|  | 0.12607 | 0.063495 | 0 | 0.062577 | 0.33333 | 39.3333 | 1453.3333 | 0.37822
|  | 0.12566 | 0 | 0.12566 | 0 | 0 | 26 | 1092.6775 | #DIV/0!
|  | 0.12566 | 0 | 0.12566 | 0 | 0 | 37.6667 | 1582.9814 | #DIV/0!
|  | 0.12566 | 0 | 0.12566 | 0 | 0 | 32.1667 | 1351.8381 | #DIV/0!
|  | 0.12521 | 0 | 0.12521 | 0 | 0 | 28.5 | 1197.7426 | #DIV/0!
|  | 0.12519 | 0 | 0.052059 | 0.073132 | 0 | 21 | 928.9871 | #DIV/0!
|  | 0.12507 | 0 | 0.021542 | 0.10352 | 0 | 34.5 | 1520.3735 | #DIV/0!
|  | 0.125 | 0.062385 | 0 | 0.062614 | 0.16667 | 64.6667 | 1490.9117 | 0.74999
|  | 0.12468 | 0.12468 | 0 | 0 | 0.16667 | 75.8333 | 1592.5 | 0.74811
|  | 0.12468 | 0.12468 | 0 | 0 | 0.16667 | 40.3333 | 1373.0123 | 0.74807
|  | 0.12447 | 0.12447 | 0 | 0 | 0 | 44.5 | 1662.431 | #DIV/0!
|  | 0.12447 | 0.12447 | 0 | 0 | 0 | 39.8333 | 1488.0937 | #DIV/0!
|  | 0.12407 | 0.12407 | 0 | 0 | 0 | 40.6667 | 1519.2253 | #DIV/0!
|  | 0.12407 | 0.12407 | 0 | 0 | 0 | 26.6667 | 996.2133 | #DIV/0!
|  | 0.12394 | 0 | 0 | 0.12394 | 0 | 30.6667 | 1363.7547 | #DIV/0!
|  | 0.12382 | 0 | 0.059239 | 0.064584 | 0 | 34.6667 | 1500.0842 | #DIV/0!
|  | 0.12371 | 0.00079787 | 0.0013463 | 0.12157 | 0 | 35.3333 | 1568.0971 | #DIV/0!
|  | 0.12349 | 0 | 0.11399 | 0.0094977 | 0 | 34.3333 | 1447.783 | #DIV/0!
|  | 0.12342 | 0 | 0.12342 | 0 | 0 | 35.3333 | 1484.9206 | #DIV/0!
|  | 0.12327 | 0.0088847 | 0 | 0.11439 | 0.33333 | 25.6667 | 1334.6667 | 0.36982
|  | 0.1231 | 0.1231 | 0 | 0 | 0.16667 | 34.1667 | 1503.3333 | 0.73862
|  | 0.1231 | 0.061552 | 0 | 0.061552 | 0.16667 | 9 | 396 | 0.73862
|  | 0.12297 | 0 | 0.12297 | 0 | 0 | 30.3333 | 1274.7904 | #DIV/0!
|  | 0.12294 | 0.12294 | 0 | 0 | 0.16667 | 32.8333 | 1476.2263 | 0.73762
|  | 0.12292 | 0.061221 | 0 | 0.061696 | 0.16667 | 45.8333 | 1788.4117 | 0.7375
|  | 0.12287 | 0.12287 | 0 | 0 | 0 | 46 | 1718.468 | #DIV/0!
|  | 0.12247 | 0.12247 | 0 | 0 | 0 | 41 | 1531.678 | #DIV/0!
|  | 0.12207 | 0.12207 | 0 | 0 | 0 | 39.3333 | 1469.4147 | #DIV/0!
|  | 0.12207 | 0.12207 | 0 | 0 | 0 | 37.1667 | 1388.4723 | #DIV/0!
|  | 0.12207 | 0.12207 | 0 | 0 | 0 | 37.3333 | 1394.6987 | #DIV/0!
|  | 0.12199 | 0.062374 | 0 | 0.059613 | 1.3333 | 44.8333 | 1715.245 | 0.091491
|  | 0.12169 | 0.12169 | 0 | 0 | 0.33333 | 17.5 | 624.2323 | 0.36507
|  | 0.12162 | 0 | 0.12162 | 0 | 0 | 29.8333 | 1253.7773 | #DIV/0!
|  | 0.12128 | 0.12128 | 0 | 0 | 0 | 26.5 | 989.987 | #DIV/0!
|  | 0.12117 | 0 | 0.12117 | 0 | 0 | 37.5 | 1575.9771 | #DIV/0!
|  | 0.1211 | 0 | 0 | 0.1211 | 0 | 20.1667 | 896.8169 | #DIV/0!
|  | 0.12088 | 0.12088 | 0 | 0 | 0 | 35.1667 | 1313.7563 | #DIV/0!
|  | 0.12077 | 0.12077 | 0 | 0 | 0.33333 | 27.5 | 1400.8333 | 0.3623
|  | 0.12071 | 0.060548 | 0 | 0.060164 | 0.16667 | 55.6667 | 1002 | 0.72427
|  | 0.12054 | 0.12054 | 0 | 0 | 0.16667 | 31.1667 | 1059.6667 | 0.72325
|  | 0.12018 | 0.0052753 | 0 | 0.11491 | 0.33333 | 61.1667 | 1166.4117 | 0.36055
|  | 0.12015 | 0 | 0 | 0.12015 | 0 | 22.3333 | 993.1692 | #DIV/0!
|  | 0.12015 | 0 | 0 | 0.12015 | 0 | 33 | 1467.5186 | #DIV/0!
|  | 0.12003 | 0.060014 | 0 | 0.060014 | 1.3333 | 33 | 1628.6667 | 0.090021
|  | 0.11994 | 0.0066635 | 0 | 0.11328 | 0.33333 | 29.6667 | 1542.6667 | 0.35983
|  | 0.11984 | 0.059929 | 0 | 0.059912 | 0.16667 | 62.1667 | 1433.4117 | 0.71905
|  | 0.11968 | 0.11968 | 0 | 0 | 0 | 36.5 | 1363.567 | #DIV/0!
|  | 0.11968 | 0.11968 | 0 | 0 | 0 | 24.3333 | 909.0447 | #DIV/0!
|  | 0.11967 | 0 | 0 | 0.11967 | 0 | 39.3333 | 1749.1636 | #DIV/0!
|  | 0.11928 | 0.11928 | 0 | 0 | 0 | 43.6667 | 1631.2993 | #DIV/0!
|  | 0.11893 | 0 | 0.11893 | 0 | 0 | 39 | 1639.0162 | #DIV/0!
|  | 0.11893 | 0 | 0.11893 | 0 | 0 | 36.3333 | 1526.9467 | #DIV/0!
|  | 0.11888 | 0.11888 | 0 | 0 | 0 | 41 | 1531.678 | #DIV/0!
|  | 0.1188 | 0.1188 | 0 | 0 | 0.16667 | 38.1667 | 1298.786 | 0.71278
|  | 0.1186 | 0.1186 | 0 | 0 | 0.5 | 35.5 | 1210.2263 | 0.2372
|  | 0.11825 | 0 | 0 | 0.11825 | 0 | 29.8333 | 1326.6961 | #DIV/0!
|  | 0.11825 | 0 | 0 | 0.11825 | 0 | 35.8333 | 1593.5177 | #DIV/0!
|  | 0.11823 | 0.062812 | 0 | 0.055422 | 1.1667 | 23.3333 | 1153.3333 | 0.10134
|  | 0.11808 | 0.11808 | 0 | 0 | 0 | 37.5 | 1400.925 | #DIV/0!
|  | 0.11803 | 0 | 0.11803 | 0 | 0 | 35 | 1470.912 | #DIV/0!
|  | 0.11803 | 0 | 0.11803 | 0 | 0 | 36.6667 | 1540.9554 | #DIV/0!
|  | 0.11803 | 0 | 0.11803 | 0 | 0 | 32.6667 | 1372.8512 | #DIV/0!
|  | 0.11794 | 0.058968 | 0 | 0.058968 | 1 | 36 | 1506 | 0.11794
|  | 0.11777 | 0 | 0 | 0.11777 | 0 | 29.1667 | 1297.0493 | #DIV/0!
|  | 0.11768 | 0.11768 | 0 | 0 | 0.16667 | 66.1667 | 1392.2263 | 0.7061
|  | 0.11758 | 0 | 0.11758 | 0 | 0 | 29.6667 | 1246.773 | #DIV/0!
|  | 0.11758 | 0 | 0.11758 | 0 | 0 | 26.8333 | 1127.6992 | #DIV/0!
|  | 0.11742 | 0.11742 | 0 | 0 | 0.16667 | 40.3333 | 1493.5267 | 0.70455
|  | 0.11729 | 0.11729 | 0 | 0 | 0 | 33.1667 | 1239.0403 | #DIV/0!
|  | 0.1172 | 0.042191 | 0.032816 | 0.042191 | 1.6667 | 38.3333 | 1682.8333 | 0.070319
|  | 0.11702 | 0.058274 | 0 | 0.058748 | 0.33333 | 56.8333 | 1080.0784 | 0.35107
|  | 0.11689 | 0.11689 | 0 | 0 | 0 | 31.5 | 1176.777 | #DIV/0!
|  | 0.11668 | 0 | 0.11668 | 0 | 0 | 32.5 | 1365.8468 | #DIV/0!
|  | 0.11668 | 0 | 0.11668 | 0 | 0 | 32 | 1344.8338 | #DIV/0!
|  | 0.11655 | 0.11655 | 0 | 0 | 1 | 41 | 1462.3333 | 0.11655
|  | 0.11635 | 0 | 0 | 0.11635 | 0 | 33.1667 | 1474.9303 | #DIV/0!
|  | 0.11627 | 0.057665 | 0 | 0.058609 | 0.16667 | 36.3333 | 1634.7351 | 0.69764
|  | 0.11609 | 0.11609 | 0 | 0 | 0 | 34.6667 | 1295.0773 | #DIV/0!
|  | 0.11587 | 0 | 0 | 0.11587 | 0 | 29.8333 | 1326.6961 | #DIV/0!
|  | 0.11571 | 0 | 0.057857 | 0.057857 | 0.33333 | 28 | 1204 | 0.34714
|  | 0.11569 | 0.11569 | 0 | 0 | 0 | 34.8333 | 1301.3037 | #DIV/0!
|  | 0.1155 | 0.1155 | 0 | 0 | 0.16667 | 58.3333 | 1346.4527 | 0.69299
|  | 0.1154 | 0 | 0 | 0.1154 | 0 | 16 | 711.5242 | #DIV/0!
|  | 0.1154 | 0 | 0 | 0.1154 | 0 | 29.8333 | 1326.6961 | #DIV/0!
|  | 0.11537 | 0.041882 | 0.033189 | 0.040301 | 0.33333 | 35 | 1295 | 0.34612
|  | 0.11492 | 0 | 0 | 0.11492 | 0 | 32.5 | 1445.2835 | #DIV/0!
|  | 0.11469 | 0.11469 | 0 | 0 | 0.16667 | 5.5 | 246.2263 | 0.68812
|  | 0.11445 | 0 | 0 | 0.11445 | 0 | 35.5 | 1578.6943 | #DIV/0!
|  | 0.1142 | 0.057024 | 0 | 0.057179 | 0.16667 | 41.3333 | 1242.4117 | 0.68522
|  | 0.11414 | 0.0024347 | 0.00044878 | 0.11126 | 0.33333 | 61.3333 | 1173.4161 | 0.34242
|  | 0.1141 | 0.1141 | 0 | 0 | 0 | 42.8333 | 1600.1677 | #DIV/0!
|  | 0.11383 | 0.11383 | 0 | 0 | 0.16667 | 18.6667 | 1350.786 | 0.68299
|  | 0.1135 | 0 | 0 | 0.1135 | 0 | 29.5 | 1311.8727 | #DIV/0!
|  | 0.11347 | 0.056736 | 0 | 0.056736 | 0.16667 | 58 | 1334 | 0.68083
|  | 0.11277 | 0.0014096 | 0.053564 | 0.057793 | 0.33333 | 19.6667 | 1298 | 0.3383
|  | 0.11264 | 0 | 0.10457 | 0.008073 | 0 | 32 | 1350.9443 | #DIV/0!
|  | 0.11257 | 0.11257 | 0 | 0 | 0.16667 | 39.6667 | 756.7263 | 0.67543
|  | 0.11255 | 0 | 0 | 0.11255 | 0 | 24.8333 | 1104.3448 | #DIV/0!
|  | 0.1125 | 0.1125 | 0 | 0 | 0 | 35.5 | 1326.209 | #DIV/0!
|  | 0.1125 | 0.1125 | 0 | 0 | 0 | 28.6667 | 1070.9293 | #DIV/0!
|  | 0.1125 | 0.1125 | 0 | 0 | 0 | 34.1667 | 1276.3983 | #DIV/0!
|  | 0.1119 | 0 | 0.055711 | 0.056186 | 0.16667 | 39.5 | 1462.745 | 0.67138
|  | 0.1117 | 0.1117 | 0 | 0 | 0 | 23.8333 | 890.3657 | #DIV/0!
|  | 0.11146 | 0 | 0.11146 | 0 | 0.16667 | 24 | 555.171 | 0.66879
|  | 0.11112 | 0 | 0 | 0.11112 | 0 | 15.5 | 689.2891 | #DIV/0!
|  | 0.11065 | 0 | 0 | 0.11065 | 0 | 35.1667 | 1563.8709 | #DIV/0!
|  | 0.11065 | 0 | 0 | 0.11065 | 0 | 34.8333 | 1549.0474 | #DIV/0!
|  | 0.11011 | 0.11011 | 0 | 0 | 0 | 35.1667 | 1313.7563 | #DIV/0!
|  | 0.10995 | 0.0011106 | 0 | 0.10884 | 0.33333 | 19.3333 | 1005.3333 | 0.32984
|  | 0.10969 | 0.036564 | 0.036564 | 0.036564 | 1 | 38.5 | 1244 | 0.10969
|  | 0.10969 | 0.10969 | 0 | 0 | 1 | 28 | 998.6667 | 0.10969
|  | 0.10946 | 0.054728 | 0 | 0.054728 | 0.5 | 34 | 1416.6667 | 0.21891
|  | 0.10931 | 0.10931 | 0 | 0 | 0 | 33.1667 | 1239.0403 | #DIV/0!
|  | 0.10922 | 0 | 0 | 0.10922 | 0 | 24.8333 | 1104.3448 | #DIV/0!
|  | 0.10922 | 0 | 0 | 0.10922 | 0 | 30.3333 | 1348.9313 | #DIV/0!
|  | 0.10875 | 0.10875 | 0 | 0 | 0.16667 | 37.5 | 1493.0777 | 0.65253
|  | 0.10875 | 0 | 0 | 0.10875 | 0 | 25.5 | 1133.9917 | #DIV/0!
|  | 0.10872 | 0 | 0.00044878 | 0.10827 | 0 | 25.5 | 1133.5843 | #DIV/0!
|  | 0.1086 | 0.054301 | 0 | 0.054301 | 0.16667 | 3 | 135 | 0.65161
|  | 0.10844 | 0.10844 | 0 | 0 | 0.16667 | 64.6667 | 1363.4527 | 0.65063
|  | 0.10842 | 0.054824 | 0 | 0.053596 | 0.16667 | 34.1667 | 1163.4117 | 0.65052
|  | 0.10811 | 0.10811 | 0 | 0 | 0 | 34.5 | 1288.851 | #DIV/0!
|  | 0.10809 | 0.10809 | 0 | 0 | 2 | 28 | 1124.6667 | 0.054045
|  | 0.10789 | 0.054023 | 0 | 0.053868 | 0.33333 | 37.6667 | 1372.8234 | 0.32367
|  | 0.10785 | 0.10785 | 0 | 0 | 0.66667 | 1.3333 | 33.3333 | 0.16178
|  | 0.10777 | 0 | 0.00044878 | 0.10732 | 0 | 25.3333 | 1126.1726 | #DIV/0!
|  | 0.10771 | 0.10771 | 0 | 0 | 0 | 36.3333 | 1357.3407 | #DIV/0!
|  | 0.10771 | 0 | 0.10771 | 0 | 0 | 35.1667 | 1477.9163 | #DIV/0!
|  | 0.10771 | 0 | 0.10771 | 0 | 0 | 33.5 | 1407.8729 | #DIV/0!
|  | 0.10758 | 0.054525 | 0 | 0.053052 | 0.33333 | 38 | 1311 | 0.32273
|  | 0.10738 | 0.053692 | 0 | 0.053692 | 1.5 | 24 | 1117.3333 | 0.07159
|  | 0.10731 | 0.10731 | 0 | 0 | 0 | 26.6667 | 996.2133 | #DIV/0!
|  | 0.10717 | 0.10717 | 0 | 0 | 0.16667 | 36.6667 | 1402.705 | 0.64303
|  | 0.10717 | 0 | 0.05161 | 0.055561 | 0 | 30.6667 | 1326.6842 | #DIV/0!
|  | 0.10716 | 0.0065781 | 0.00044878 | 0.10013 | 0.5 | 30.3333 | 1244.2122 | 0.21431
|  | 0.10685 | 0 | 0 | 0.10685 | 0 | 28.1667 | 1252.579 | #DIV/0!
|  | 0.10672 | 0.05397 | 0 | 0.052753 | 0.16667 | 33.5 | 1273 | 0.64034
|  | 0.10652 | 0.10652 | 0 | 0 | 0 | 31.8333 | 1189.2297 | #DIV/0!
|  | 0.10637 | 0 | 0 | 0.10637 | 0 | 24.3333 | 1082.1097 | #DIV/0!
|  | 0.10609 | 0.10609 | 0 | 0 | 0.16667 | 32.8333 | 1116.893 | 0.63654
|  | 0.1059 | 0 | 0 | 0.1059 | 0 | 27.8333 | 1237.7556 | #DIV/0!
|  | 0.10549 | 0.10549 | 0 | 0 | 0.16667 | 33.6667 | 1245.6667 | 0.63297
|  | 0.10549 | 0 | 0.051707 | 0.053783 | 0.16667 | 31.6667 | 1236.4161 | 0.63294
|  | 0.10532 | 0.10532 | 0 | 0 | 0 | 30.6667 | 1145.6453 | #DIV/0!
|  | 0.10512 | 0 | 0.051824 | 0.053297 | 0.16667 | 54.6667 | 1257.3333 | 0.63073
|  | 0.10495 | 0 | 0 | 0.10495 | 0 | 13.1667 | 585.5251 | #DIV/0!
|  | 0.10495 | 0 | 0 | 0.10495 | 0 | 17 | 755.9944 | #DIV/0!
|  | 0.10495 | 0 | 0 | 0.10495 | 0 | 27.3333 | 1215.5205 | #DIV/0!
|  | 0.10495 | 0 | 0 | 0.10495 | 0 | 26.5 | 1178.4619 | #DIV/0!
|  | 0.10492 | 0.10492 | 0 | 0 | 0 | 28.8333 | 1077.1557 | #DIV/0!
|  | 0.10475 | 0.052379 | 0 | 0.052373 | 0.16667 | 32.6667 | 1469.9117 | 0.62851
|  | 0.10469 | 0.10469 | 0 | 0 | 0.16667 | 31.1667 | 1340.1667 | 0.62816
|  | 0.10463 | 0.0087565 | 0.044199 | 0.051679 | 0.66667 | 39.8333 | 1633.0784 | 0.15695
|  | 0.10447 | 0 | 0 | 0.10447 | 0 | 26.5 | 1178.4619 | #DIV/0!
|  | 0.10427 | 0 | 0.046677 | 0.057589 | 0.16667 | 29 | 1133.3278 | 0.6256
|  | 0.10425 | 0.051888 | 0 | 0.052363 | 0.16667 | 27.1667 | 1168.4117 | 0.6255
|  | 0.10412 | 0.10412 | 0 | 0 | 0 | 36.5 | 1363.567 | #DIV/0!
|  | 0.10412 | 0.10412 | 0 | 0 | 0 | 33.5 | 1251.493 | #DIV/0!
|  | 0.10412 | 0.10412 | 0 | 0 | 0 | 31.1667 | 1164.3243 | #DIV/0!
|  | 0.10412 | 0 | 0.10412 | 0 | 0 | 27.3333 | 1148.7122 | #DIV/0!
|  | 0.104 | 0 | 0 | 0.104 | 0 | 25.3333 | 1126.58 | #DIV/0!
|  | 0.10397 | 0 | 0.00044878 | 0.10352 | 0 | 27.1667 | 1207.7014 | #DIV/0!
|  | 0.10352 | 0 | 0 | 0.10352 | 0 | 23.8333 | 1059.8746 | #DIV/0!
|  | 0.10346 | 0.051728 | 0 | 0.051728 | 1.1667 | 25.6667 | 1268.6667 | 0.088676
|  | 0.10332 | 0.10332 | 0 | 0 | 0 | 40.5 | 1512.999 | #DIV/0!
|  | 0.10332 | 0.10332 | 0 | 0 | 0 | 32.8333 | 1226.5877 | #DIV/0!
|  | 0.10332 | 0.10332 | 0 | 0 | 0 | 18.1667 | 678.6703 | #DIV/0!
|  | 0.10322 | 0 | 0.10322 | 0 | 0 | 29 | 1218.7556 | #DIV/0!
|  | 0.10322 | 0 | 0.10322 | 0 | 0 | 21 | 882.5472 | #DIV/0!
|  | 0.1031 | 0.1031 | 0 | 0 | 1 | 24.5 | 895.8333 | 0.1031
|  | 0.10292 | 0.10292 | 0 | 0 | 0 | 21.1667 | 790.7443 | #DIV/0!
|  | 0.1029 | 0.1029 | 0 | 0 | 0.16667 | 25.3333 | 1114.6667 | 0.6174
|  | 0.1029 | 0.019574 | 0 | 0.083325 | 0.16667 | 30.8333 | 1292.7593 | 0.6174
|  | 0.10284 | 0.051418 | 0 | 0.051418 | 0.16667 | 27.6667 | 1245 | 0.61701
|  | 0.10257 | 0 | 0 | 0.10257 | 0 | 21.1667 | 941.2872 | #DIV/0!
|  | 0.10253 | 0 | 0.049815 | 0.052712 | 0 | 21 | 908.2113 | #DIV/0!
|  | 0.10245 | 0 | 0.049976 | 0.052475 | 0.16667 | 30.1667 | 1176.5 | 0.61471
|  | 0.10232 | 0 | 0.10232 | 0 | 0 | 27.6667 | 1162.7209 | #DIV/0!
|  | 0.10232 | 0 | 0.10232 | 0 | 0 | 13 | 546.3387 | #DIV/0!
|  | 0.10225 | 0.10225 | 0 | 0 | 0.16667 | 54.1667 | 1032.2263 | 0.61351
|  | 0.10213 | 0.10213 | 0 | 0 | 0 | 30.3333 | 1133.1927 | #DIV/0!
|  | 0.10213 | 0.10213 | 0 | 0 | 0 | 33.3333 | 1245.2667 | #DIV/0!
|  | 0.1021 | 0 | 0 | 0.1021 | 0 | 14.5 | 644.8188 | #DIV/0!
|  | 0.1021 | 0 | 0 | 0.1021 | 0 | 24 | 1067.2863 | #DIV/0!
|  | 0.10207 | 0 | 0.00044878 | 0.10163 | 0 | 27.3333 | 1215.1131 | #DIV/0!
|  | 0.10187 | 0 | 0.004039 | 0.097826 | 0 | 22.6667 | 1005.141 | #DIV/0!
|  | 0.10185 | 0.0024347 | 0 | 0.099419 | 0.33333 | 39.3333 | 747.3333 | 0.30556
|  | 0.10174 | 0.10174 | 0 | 0 | 0.16667 | 31 | 1149.3867 | 0.61045
|  | 0.10173 | 0.10173 | 0 | 0 | 0 | 37.6667 | 1407.1513 | #DIV/0!
|  | 0.10173 | 0.10173 | 0 | 0 | 0 | 30.8333 | 1151.8717 | #DIV/0!
|  | 0.10163 | 0 | 0 | 0.10163 | 0 | 15.8333 | 704.1125 | #DIV/0!
|  | 0.10142 | 0 | 0.10142 | 0 | 0 | 29.5 | 1239.7687 | #DIV/0!
|  | 0.10142 | 0 | 0.10142 | 0 | 0 | 29.8333 | 1253.7773 | #DIV/0!
|  | 0.10137 | 0.10137 | 0 | 0 | 0.16667 | 37.8333 | 1173.893 | 0.6082
|  | 0.10093 | 0.10093 | 0 | 0 | 0 | 34 | 1270.172 | #DIV/0!
|  | 0.10093 | 0.10093 | 0 | 0 | 0 | 32 | 1195.456 | #DIV/0!
|  | 0.10093 | 0.10093 | 0 | 0 | 0 | 17.3333 | 647.5387 | #DIV/0!
|  | 0.10067 | 0.0031609 | 0.05161 | 0.0459 | 0.16667 | 31.6667 | 1348.0207 | 0.60403
|  | 0.10053 | 0.10053 | 0 | 0 | 0 | 32.6667 | 1220.3613 | #DIV/0!
|  | 0.10036 | 0.050179 | 0 | 0.050179 | 0.16667 | 31 | 1147 | 0.60215
|  | 0.10017 | 0 | 0.00044878 | 0.099726 | 0 | 14.3333 | 636.9997 | #DIV/0!
|  | 0.10013 | 0.10013 | 0 | 0 | 0 | 38 | 1419.604 | #DIV/0!
|  | 0.10002 | 0.10002 | 0 | 0 | 0.16667 | 50.8333 | 1067.5 | 0.6001
|  | 0.099734 | 0.099734 | 0 | 0 | 0 | 38 | 1419.604 | #DIV/0!
|  | 0.099643 | 0.05098 | 0 | 0.048663 | 1.5 | 49.5 | 1193.5 | 0.066429
|  | 0.09963 | 0 | 0.09963 | 0 | 0 | 12.6667 | 532.33 | #DIV/0!
|  | 0.099335 | 0.099335 | 0 | 0 | 0 | 35.1667 | 1313.7563 | #DIV/0!
|  | 0.099335 | 0.099335 | 0 | 0 | 0 | 26.1667 | 977.5343 | #DIV/0!
|  | 0.099251 | 0 | 0 | 0.099251 | 0 | 23.3333 | 1037.6394 | #DIV/0!
|  | 0.099184 | 0 | 0.099184 | 0 | 0.16667 | 42.8333 | 988.3377 | 0.5951
|  | 0.099181 | 0 | 0.099181 | 0 | 0 | 28.3333 | 1190.7383 | #DIV/0!
|  | 0.099181 | 0 | 0.099181 | 0 | 0 | 23 | 966.5993 | #DIV/0!
|  | 0.098936 | 0.098936 | 0 | 0 | 0 | 32 | 1195.456 | #DIV/0!
|  | 0.098776 | 0 | 0 | 0.098776 | 0 | 26.3333 | 1171.0502 | #DIV/0!
|  | 0.098767 | 0.098767 | 0 | 0 | 1.1667 | 33.3333 | 1230.6667 | 0.084658
|  | 0.098671 | 0 | 0.098671 | 0 | 0.33333 | 17.3333 | 1144 | 0.29601
|  | 0.098537 | 0.098537 | 0 | 0 | 0 | 29.3333 | 1095.8347 | #DIV/0!
|  | 0.098465 | 0.036258 | 0 | 0.062207 | 0.16667 | 40.8333 | 1088.2731 | 0.59079
|  | 0.098374 | 0.098374 | 0 | 0 | 0.16667 | 48.6667 | 1270.0963 | 0.59024
|  | 0.098345 | 0 | 0.048727 | 0.049618 | 0.16667 | 18.6667 | 728.9117 | 0.59007
|  | 0.098265 | 0.098265 | 0 | 0 | 0.33333 | 30.6667 | 1318.6667 | 0.2948
|  | 0.098201 | 0.049101 | 0 | 0.049101 | 0.33333 | 62.6667 | 1190.6667 | 0.2946
|  | 0.098147 | 0.040526 | 0 | 0.057621 | 0.16667 | 20 | 574.5081 | 0.58888
|  | 0.098142 | 0.049133 | 0 | 0.049009 | 0.33333 | 25 | 1262.4117 | 0.29443
|  | 0.098138 | 0.098138 | 0 | 0 | 0 | 27.6667 | 1033.5713 | #DIV/0!
|  | 0.097739 | 0.097739 | 0 | 0 | 0 | 31.6667 | 1183.0033 | #DIV/0!
|  | 0.097739 | 0.097739 | 0 | 0 | 0 | 28.3333 | 1058.4767 | #DIV/0!
|  | 0.097386 | 0 | 0.097386 | 0 | 0 | 23 | 966.5993 | #DIV/0!
|  | 0.097386 | 0 | 0.097386 | 0 | 0 | 3.1667 | 133.0825 | #DIV/0!
|  | 0.097351 | 0 | 0 | 0.097351 | 0 | 21 | 933.8755 | #DIV/0!
|  | 0.097351 | 0 | 0 | 0.097351 | 0 | 27.1667 | 1208.1088 | #DIV/0!
|  | 0.097322 | 0.097322 | 0 | 0 | 0.33333 | 38.3333 | 1323.4527 | 0.29197
|  | 0.096941 | 0.096941 | 0 | 0 | 0.83333 | 26.6667 | 1166.3333 | 0.11633
|  | 0.096941 | 0.096941 | 0 | 0 | 0 | 38.8333 | 1450.7357 | #DIV/0!
|  | 0.096941 | 0.096941 | 0 | 0 | 0 | 31.1667 | 1164.3243 | #DIV/0!
|  | 0.096941 | 0.096941 | 0 | 0 | 0 | 30 | 1120.74 | #DIV/0!
|  | 0.096941 | 0.096941 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.096876 | 0 | 0 | 0.096876 | 0 | 0.83333 | 37.0586 | #DIV/0!
|  | 0.0968 | 0.00039893 | 0 | 0.096401 | 0 | 23.5 | 1043.8658 | #DIV/0!
|  | 0.096557 | 0.048278 | 0 | 0.048278 | 0.83333 | 36.3333 | 1273.6667 | 0.11587
|  | 0.096401 | 0 | 0 | 0.096401 | 0 | 0.83333 | 37.0586 | #DIV/0!
|  | 0.096401 | 0 | 0 | 0.096401 | 0 | 29.5 | 1311.8727 | #DIV/0!
|  | 0.096375 | 0 | 0.00044878 | 0.095927 | 0 | 20.5 | 911.233 | #DIV/0!
|  | 0.096251 | 0.096251 | 0 | 0 | 0.16667 | 23.8333 | 1047.5597 | 0.5775
|  | 0.096143 | 0.096143 | 0 | 0 | 0 | 36.5 | 1363.567 | #DIV/0!
|  | 0.096143 | 0.096143 | 0 | 0 | 0 | 23.1667 | 865.4603 | #DIV/0!
|  | 0.095927 | 0 | 0 | 0.095927 | 0 | 0.66667 | 29.6468 | #DIV/0!
|  | 0.095927 | 0 | 0 | 0.095927 | 0 | 28 | 1245.1673 | #DIV/0!
|  | 0.095884 | 0.095884 | 0 | 0 | 1 | 23 | 839.5 | 0.095884
|  | 0.095852 | 0.095852 | 0 | 0 | 0.16667 | 25.6667 | 1129.3333 | 0.57511
|  | 0.095852 | 0 | 0.047926 | 0.047926 | 0.33333 | 20 | 1320 | 0.28756
|  | 0.09583 | 0.00039511 | 0.047072 | 0.048363 | 0.16667 | 31.3333 | 1162.6611 | 0.57498
|  | 0.095744 | 0.095744 | 0 | 0 | 0 | 28.8333 | 1077.1557 | #DIV/0!
|  | 0.095744 | 0.095744 | 0 | 0 | 0 | 18.3333 | 684.8967 | #DIV/0!
|  | 0.095628 | 0.095628 | 0 | 0 | 0.16667 | 25.3333 | 1140 | 0.57377
|  | 0.09561 | 0.09561 | 0 | 0 | 0.5 | 32 | 1043.0597 | 0.19122
|  | 0.095531 | 0.095531 | 0 | 0 | 0.16667 | 55.1667 | 1158.5 | 0.57319
|  | 0.095525 | 0.095525 | 0 | 0 | 0.16667 | 29.8333 | 1003.2487 | 0.57315
|  | 0.095222 | 0 | 0.046623 | 0.048599 | 0.16667 | 36.1667 | 1338.1667 | 0.57133
|  | 0.094912 | 0.094912 | 0 | 0 | 0.16667 | 22.1667 | 975.3333 | 0.56947
|  | 0.094693 | 0 | 0.094693 | 0 | 0 | 23.1667 | 973.6036 | #DIV/0!
|  | 0.0943 | 0.0943 | 0 | 0 | 0.16667 | 23 | 1009.786 | 0.5658
|  | 0.094244 | 0 | 0.094244 | 0 | 0 | 22.3333 | 938.5819 | #DIV/0!
|  | 0.094027 | 0 | 0 | 0.094027 | 0 | 26.8333 | 1193.2854 | #DIV/0!
|  | 0.093959 | 0.013455 | 0 | 0.080504 | 0.16667 | 26.5 | 1114.935 | 0.56376
|  | 0.093796 | 0 | 0.093796 | 0 | 0 | 31.6667 | 1330.8251 | #DIV/0!
|  | 0.093796 | 0 | 0.093796 | 0 | 0 | 29.3333 | 1232.7643 | #DIV/0!
|  | 0.093796 | 0 | 0.093796 | 0 | 0 | 24.6667 | 1036.6427 | #DIV/0!
|  | 0.093796 | 0 | 0.093796 | 0 | 0 | 25.1667 | 1057.6557 | #DIV/0!
|  | 0.09375 | 0.09375 | 0 | 0 | 0 | 31.3333 | 1170.5507 | #DIV/0!
|  | 0.093737 | 0.093737 | 0 | 0 | 0.66667 | 24.6667 | 949.6667 | 0.14061
|  | 0.093638 | 0.093638 | 0 | 0 | 0.16667 | 58.1667 | 1226.9527 | 0.56183
|  | 0.093351 | 0.093351 | 0 | 0 | 0 | 17.1667 | 641.3123 | #DIV/0!
|  | 0.09319 | 0.09319 | 0 | 0 | 0.16667 | 40.5 | 855.9527 | 0.55914
|  | 0.093077 | 0 | 0 | 0.093077 | 0 | 19 | 844.935 | #DIV/0!
|  | 0.093077 | 0 | 0 | 0.093077 | 0 | 27 | 1200.6971 | #DIV/0!
|  | 0.093077 | 0 | 0 | 0.093077 | 0 | 30.3333 | 1348.9313 | #DIV/0!
|  | 0.092962 | 0.092962 | 0 | 0 | 0.16667 | 24.6667 | 1084.2263 | 0.55777
|  | 0.092952 | 0.092952 | 0 | 0 | 0 | 28 | 1046.024 | #DIV/0!
|  | 0.092898 | 0 | 0.092898 | 0 | 0 | 24 | 1008.6253 | #DIV/0!
|  | 0.092684 | 0 | 0.08841 | 0.004274 | 0 | 22 | 927.8322 | #DIV/0!
|  | 0.09267 | 0.046335 | 0 | 0.046335 | 1 | 55 | 1378.3333 | 0.09267
|  | 0.092553 | 0.092553 | 0 | 0 | 0 | 17.1667 | 641.3123 | #DIV/0!
|  | 0.092514 | 0 | 0.044562 | 0.047952 | 0.16667 | 28.3333 | 1105.9117 | 0.55509
|  | 0.092324 | 0.092324 | 0 | 0 | 0.16667 | 24.3333 | 887.2177 | 0.55394
|  | 0.092154 | 0.092154 | 0 | 0 | 0 | 21.6667 | 809.4233 | #DIV/0!
|  | 0.092127 | 0 | 0 | 0.092127 | 0 | 27.3333 | 1215.5205 | #DIV/0!
|  | 0.092127 | 0 | 0 | 0.092127 | 0 | 27 | 1200.6971 | #DIV/0!
|  | 0.092069 | 0.092069 | 0 | 0 | 0.16667 | 55.8333 | 1177.9527 | 0.55241
|  | 0.091996 | 0.046452 | 0 | 0.045544 | 0.5 | 37.3333 | 1087.8234 | 0.18399
|  | 0.091653 | 0 | 0 | 0.091653 | 0 | 25.1667 | 1119.1682 | #DIV/0!
|  | 0.091612 | 0 | 0.044947 | 0.046666 | 0.16667 | 48.5 | 1115.5 | 0.54967
|  | 0.091393 | 0.045459 | 0 | 0.045934 | 0.16667 | 27.8333 | 1197.0784 | 0.54836
|  | 0.091178 | 0 | 0 | 0.091178 | 0 | 22.6667 | 1007.9926 | #DIV/0!
|  | 0.090703 | 0 | 0 | 0.090703 | 0 | 24.1667 | 1074.698 | #DIV/0!
|  | 0.090703 | 0 | 0 | 0.090703 | 0 | 27.5 | 1222.9322 | #DIV/0!
|  | 0.090483 | 0.0032143 | 0 | 0.087269 | 0.16667 | 28.3333 | 1256.5601 | 0.5429
|  | 0.090342 | 0.090342 | 0 | 0 | 0.16667 | 24.3333 | 1095 | 0.54205
|  | 0.090246 | 0.090246 | 0 | 0 | 0.16667 | 30.1667 | 937.286 | 0.54148
|  | 0.090228 | 0 | 0 | 0.090228 | 0 | 23.5 | 1045.0511 | #DIV/0!
|  | 0.090205 | 0 | 0.090205 | 0 | 0 | 29.3333 | 1232.7643 | #DIV/0!
|  | 0.090205 | 0 | 0.090205 | 0 | 0 | 26.8333 | 1127.6992 | #DIV/0!
|  | 0.089809 | 0 | 0.088859 | 0.00094977 | 0 | 26.1667 | 1100.0892 | #DIV/0!
|  | 0.089802 | 0.00073683 | 0 | 0.089065 | 0.16667 | 12.6667 | 541.8197 | 0.53881
|  | 0.089779 | 0.089779 | 0 | 0 | 0.16667 | 31.6667 | 982.7263 | 0.53868
|  | 0.089779 | 0.089779 | 0 | 0 | 0.16667 | 23.3333 | 1048.7263 | 0.53868
|  | 0.089361 | 0.089361 | 0 | 0 | 0 | 30.6667 | 1145.6453 | #DIV/0!
|  | 0.088922 | 0.088922 | 0 | 0 | 0.16667 | 30 | 932.1193 | 0.53353
|  | 0.088803 | 0 | 0 | 0.088803 | 0 | 24.6667 | 1096.9331 | #DIV/0!
|  | 0.088803 | 0 | 0 | 0.088803 | 0 | 26.3333 | 1171.0502 | #DIV/0!
|  | 0.088462 | 0.088462 | 0 | 0 | 0.16667 | 15.8333 | 601.6667 | 0.53077
|  | 0.08841 | 0 | 0.08841 | 0 | 0 | 24.6667 | 1036.6427 | #DIV/0!
|  | 0.088328 | 0 | 0 | 0.088328 | 0 | 7.6667 | 340.9387 | #DIV/0!
|  | 0.088164 | 0.088164 | 0 | 0 | 0 | 27 | 1008.666 | #DIV/0!
|  | 0.08811 | 0.0017513 | 0.043378 | 0.042981 | 0.66667 | 25.5 | 1047.1698 | 0.13216
|  | 0.08795 | 0.043975 | 0 | 0.043975 | 0.66667 | 24 | 852 | 0.13192
|  | 0.087853 | 0 | 0 | 0.087853 | 0 | 26.3333 | 1171.0502 | #DIV/0!
|  | 0.087766 | 0.087766 | 0 | 0 | 0 | 30.6667 | 1145.6453 | #DIV/0!
|  | 0.087513 | 0 | 0.087513 | 0 | 0 | 23 | 966.5993 | #DIV/0!
|  | 0.087513 | 0 | 0.087513 | 0 | 0 | 23.5 | 987.6123 | #DIV/0!
|  | 0.087427 | 0.087427 | 0 | 0 | 0.16667 | 50.6667 | 971.8457 | 0.52456
|  | 0.087379 | 0 | 0 | 0.087379 | 0 | 23.6667 | 1052.4629 | #DIV/0!
|  | 0.087367 | 0.087367 | 0 | 0 | 0 | 24.6667 | 921.4973 | #DIV/0!
|  | 0.087352 | 0 | 0.00044878 | 0.086904 | 0 | 25.3333 | 1126.1726 | #DIV/0!
|  | 0.08705 | 0.08705 | 0 | 0 | 0.16667 | 27.3333 | 1163.7693 | 0.5223
|  | 0.087049 | 0 | 0.02199 | 0.065059 | 0 | 23.6667 | 1036.1682 | #DIV/0!
|  | 0.086968 | 0.086968 | 0 | 0 | 0 | 19.5 | 728.481 | #DIV/0!
|  | 0.086904 | 0 | 0 | 0.086904 | 0 | 10 | 444.7026 | #DIV/0!
|  | 0.086904 | 0 | 0 | 0.086904 | 0 | 24.6667 | 1096.9331 | #DIV/0!
|  | 0.086615 | 0 | 0.086615 | 0 | 0 | 28.1667 | 1183.7339 | #DIV/0!
|  | 0.086569 | 0.086569 | 0 | 0 | 0 | 27 | 1008.666 | #DIV/0!
|  | 0.086569 | 0.086569 | 0 | 0 | 0 | 21.3333 | 796.9707 | #DIV/0!
|  | 0.086429 | 0 | 0 | 0.086429 | 0 | 22.1667 | 985.7575 | #DIV/0!
|  | 0.086337 | 0.086337 | 0 | 0 | 0.66667 | 39.3333 | 1032.5 | 0.12951
|  | 0.085771 | 0.085771 | 0 | 0 | 0 | 25.5 | 952.629 | #DIV/0!
|  | 0.085479 | 0 | 0 | 0.085479 | 0 | 26.3333 | 1171.0502 | #DIV/0!
|  | 0.085341 | 0.085341 | 0 | 0 | 0.16667 | 49 | 1034.4527 | 0.51205
|  | 0.085004 | 0 | 0 | 0.085004 | 0 | 19.3333 | 859.7584 | #DIV/0!
|  | 0.084973 | 0.084973 | 0 | 0 | 0 | 26.1667 | 977.5343 | #DIV/0!
|  | 0.08496 | 0 | 0.04248 | 0.04248 | 0.16667 | 1 | 39 | 0.50976
|  | 0.084918 | 0.084918 | 0 | 0 | 0.16667 | 50.3333 | 1070.6317 | 0.50951
|  | 0.08482 | 0 | 0.08482 | 0 | 0 | 20.8333 | 875.5428 | #DIV/0!
|  | 0.084574 | 0.084574 | 0 | 0 | 0 | 25.3333 | 946.4027 | #DIV/0!
|  | 0.084574 | 0.084574 | 0 | 0 | 0 | 24.3333 | 909.0447 | #DIV/0!
|  | 0.084554 | 0.042277 | 0 | 0.042277 | 0.16667 | 1.6667 | 61.6667 | 0.50732
|  | 0.084529 | 0 | 0 | 0.084529 | 0 | 23.5 | 1045.0511 | #DIV/0!
|  | 0.084175 | 0.084175 | 0 | 0 | 0 | 29.6667 | 1108.2873 | #DIV/0!
|  | 0.084063 | 0.084063 | 0 | 0 | 0.83333 | 43.3333 | 1066 | 0.10088
|  | 0.084054 | 0 | 0 | 0.084054 | 0 | 20.1667 | 896.8169 | #DIV/0!
|  | 0.084028 | 0 | 0.00044878 | 0.08358 | 0 | 22.8333 | 1014.9969 | #DIV/0!
|  | 0.083978 | 0.00039893 | 0 | 0.08358 | 0 | 25.6667 | 1140.218 | #DIV/0!
|  | 0.083922 | 0 | 0.083922 | 0 | 0 | 12 | 504.3127 | #DIV/0!
|  | 0.083922 | 0 | 0.083922 | 0 | 0 | 20.3333 | 854.5298 | #DIV/0!
|  | 0.083828 | 0.011736 | 0.031855 | 0.040237 | 1.1667 | 53.6667 | 1203.6667 | 0.071852
|  | 0.083797 | 0.083797 | 0 | 0 | 0.16667 | 51.8333 | 1093.9527 | 0.50278
|  | 0.08358 | 0 | 0 | 0.08358 | 0 | 8.8333 | 392.8206 | #DIV/0!
|  | 0.083297 | 0.0081692 | 0 | 0.075128 | 0.16667 | 27.6667 | 1233.3458 | 0.49978
|  | 0.083025 | 0 | 0.083025 | 0 | 0 | 20 | 840.5211 | #DIV/0!
|  | 0.083016 | 0.083016 | 0 | 0 | 0.16667 | 33.5 | 1079.734 | 0.4981
|  | 0.082781 | 0.082781 | 0 | 0 | 0.16667 | 26 | 884 | 0.49669
|  | 0.08263 | 0 | 0 | 0.08263 | 0 | 17.6667 | 785.6413 | #DIV/0!
|  | 0.08263 | 0 | 0 | 0.08263 | 0 | 18.6667 | 830.1115 | #DIV/0!
|  | 0.08263 | 0 | 0 | 0.08263 | 0 | 23.5 | 1045.0511 | #DIV/0!
|  | 0.082579 | 0.082579 | 0 | 0 | 0 | 1.1667 | 43.5843 | #DIV/0!
|  | 0.08218 | 0.08218 | 0 | 0 | 0 | 23.6667 | 884.1393 | #DIV/0!
|  | 0.082155 | 0 | 0 | 0.082155 | 0 | 25 | 1111.7565 | #DIV/0!
|  | 0.082155 | 0 | 0 | 0.082155 | 0 | 23 | 1022.816 | #DIV/0!
|  | 0.082127 | 0 | 0.082127 | 0 | 0 | 24.5 | 1029.6384 | #DIV/0!
|  | 0.082098 | 0.082098 | 0 | 0 | 0.66667 | 36.8333 | 1101.3333 | 0.12315
|  | 0.082034 | 0.041017 | 0 | 0.041017 | 0.66667 | 16 | 668 | 0.12305
|  | 0.08184 | 0.023824 | 0 | 0.058016 | 0.16667 | 36.6667 | 1072.3495 | 0.49104
|  | 0.08168 | 0 | 0 | 0.08168 | 0 | 10 | 444.7026 | #DIV/0!
|  | 0.081393 | 0.081393 | 0 | 0 | 0.16667 | 28.3333 | 1048.3333 | 0.48836
|  | 0.081205 | 0 | 0 | 0.081205 | 0 | 20.3333 | 904.2287 | #DIV/0!
|  | 0.08113 | 0.08113 | 0 | 0 | 0.66667 | 51.5 | 1084.2263 | 0.12169
|  | 0.081073 | 0.040536 | 0 | 0.040536 | 0.83333 | 41.6667 | 1216.6667 | 0.097287
|  | 0.080984 | 0.080984 | 0 | 0 | 0 | 25 | 933.95 | #DIV/0!
|  | 0.080984 | 0.080984 | 0 | 0 | 0 | 23.5 | 877.913 | #DIV/0!
|  | 0.080955 | 0.080955 | 0 | 0 | 0.16667 | 34 | 646 | 0.48573
|  | 0.080918 | 0 | 0.0049366 | 0.075981 | 0 | 25.5 | 1129.5106 | #DIV/0!
|  | 0.080905 | 0.080905 | 0 | 0 | 0.16667 | 34 | 716.7263 | 0.48543
|  | 0.080886 | 0 | 0.038147 | 0.04274 | 0 | 19 | 822.5298 | #DIV/0!
|  | 0.080818 | 0.029388 | 0.021093 | 0.030337 | 0.16667 | 24.3333 | 1040.0058 | 0.48491
|  | 0.080585 | 0.080585 | 0 | 0 | 0 | 22.5 | 840.555 | #DIV/0!
|  | 0.080585 | 0.080585 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.080517 | 0.040259 | 0 | 0.040259 | 1.1667 | 28 | 1160 | 0.069015
|  | 0.080275 | 0.080275 | 0 | 0 | 0.16667 | 19.1667 | 842.2263 | 0.48165
|  | 0.080255 | 0 | 0 | 0.080255 | 0 | 23.8333 | 1059.8746 | #DIV/0!
|  | 0.080186 | 0.080186 | 0 | 0 | 0 | 25.8333 | 965.0817 | #DIV/0!
|  | 0.079898 | 0.079898 | 0 | 0 | 1.5 | 15.8333 | 697.5 | 0.053265
|  | 0.079898 | 0.079898 | 0 | 0 | 0.16667 | 10.3333 | 444.3333 | 0.47939
|  | 0.079787 | 0.079787 | 0 | 0 | 0 | 19.5 | 728.481 | #DIV/0!
|  | 0.079787 | 0.079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.07978 | 0 | 0 | 0.07978 | 0 | 22.6667 | 1007.9926 | #DIV/0!
|  | 0.079735 | 0.079735 | 0 | 0 | 0.33333 | 20.5 | 900.893 | 0.2392
|  | 0.079483 | 0 | 0.079483 | 0 | 0.16667 | 32.8333 | 829.3464 | 0.4769
|  | 0.079407 | 0.039703 | 0 | 0.039703 | 0.66667 | 25.3333 | 1070.3333 | 0.11911
|  | 0.079306 | 0 | 0 | 0.079306 | 0 | 10.1667 | 452.1143 | #DIV/0!
|  | 0.079306 | 0 | 0 | 0.079306 | 0 | 20 | 889.4052 | #DIV/0!
|  | 0.079306 | 0 | 0 | 0.079306 | 0 | 20.8333 | 926.4638 | #DIV/0!
|  | 0.078989 | 0.078989 | 0 | 0 | 0 | 23.1667 | 865.4603 | #DIV/0!
|  | 0.07898 | 0.039949 | 0 | 0.039031 | 0.16667 | 20.6667 | 888.6667 | 0.47388
|  | 0.078937 | 0.039468 | 0 | 0.039468 | 0.33333 | 25.3333 | 1064 | 0.23681
|  | 0.07859 | 0.07859 | 0 | 0 | 0 | 24.3333 | 909.0447 | #DIV/0!
|  | 0.078317 | 0.078317 | 0 | 0 | 0.16667 | 41.1667 | 782.1667 | 0.4699
|  | 0.078253 | 0.078253 | 0 | 0 | 2.5 | 25 | 763.3333 | 0.031301
|  | 0.077926 | 0.077926 | 0 | 0 | 0.16667 | 23 | 1010.893 | 0.46756
|  | 0.077881 | 0 | 0 | 0.077881 | 0 | 17.6667 | 785.6413 | #DIV/0!
|  | 0.077881 | 0 | 0 | 0.077881 | 0 | 19.5 | 867.1701 | #DIV/0!
|  | 0.077805 | 0.00039893 | 0 | 0.077406 | 0 | 22.1667 | 984.5721 | #DIV/0!
|  | 0.077691 | 0.077691 | 0 | 0 | 0.66667 | 20.8333 | 801.893 | 0.11654
|  | 0.077639 | 0 | 0.077639 | 0 | 0 | 22 | 924.5732 | #DIV/0!
|  | 0.077639 | 0 | 0.077639 | 0 | 0 | 20 | 840.5211 | #DIV/0!
|  | 0.077591 | 0.038796 | 0 | 0.038796 | 0.66667 | 26.6667 | 1153.3333 | 0.11639
|  | 0.077406 | 0 | 0 | 0.077406 | 0 | 21.1667 | 941.2872 | #DIV/0!
|  | 0.077336 | 0.077336 | 0 | 0 | 0.16667 | 40.8333 | 946.3457 | 0.46401
|  | 0.077143 | 0.038571 | 0 | 0.038571 | 1.1667 | 18.6667 | 688 | 0.066122
|  | 0.077122 | 0.011255 | 0 | 0.065867 | 0.16667 | 20.6667 | 820.2702 | 0.46273
|  | 0.077121 | 0.0083828 | 0.030178 | 0.038561 | 1.1667 | 23.3333 | 523.3333 | 0.066104
|  | 0.077004 | 0.0026483 | 0 | 0.074356 | 0.16667 | 21.3333 | 917.2683 | 0.46202
|  | 0.076876 | 0.076876 | 0 | 0 | 0.16667 | 36.3333 | 835.6667 | 0.46125
|  | 0.076855 | 0.00039893 | 0 | 0.076456 | 0 | 19.8333 | 880.8081 | #DIV/0!
|  | 0.076595 | 0.076595 | 0 | 0 | 0 | 29.1667 | 1089.6083 | #DIV/0!
|  | 0.076595 | 0.076595 | 0 | 0 | 0 | 25.3333 | 946.4027 | #DIV/0!
|  | 0.076595 | 0.076595 | 0 | 0 | 0 | 20 | 747.16 | #DIV/0!
|  | 0.076456 | 0 | 0 | 0.076456 | 0 | 7 | 311.2918 | #DIV/0!
|  | 0.076374 | 0.076374 | 0 | 0 | 1.1667 | 33.6667 | 1192 | 0.065463
|  | 0.076331 | 0 | 0.010322 | 0.066009 | 0 | 20.5 | 903.0856 | #DIV/0!
|  | 0.076293 | 0 | 0.076293 | 0 | 0 | 22 | 924.5732 | #DIV/0!
|  | 0.07621 | 0 | 0.028722 | 0.047488 | 0 | 22.8333 | 991.3696 | #DIV/0!
|  | 0.076167 | 0.0043287 | 0 | 0.071838 | 0.16667 | 20.1667 | 816.9073 | 0.457
|  | 0.076022 | 0.076022 | 0 | 0 | 0.16667 | 48 | 1008 | 0.45613
|  | 0.075981 | 0 | 0 | 0.075981 | 0 | 22 | 978.3458 | #DIV/0!
|  | 0.075865 | 0 | 0.067317 | 0.0085479 | 0 | 21.8333 | 922.0499 | #DIV/0!
|  | 0.07566 | 0 | 0.071388 | 0.0042715 | 0.16667 | 33.1667 | 843.355 | 0.45396
|  | 0.075399 | 0.075399 | 0 | 0 | 0 | 26.8333 | 1002.4397 | #DIV/0!
|  | 0.075107 | 0.075107 | 0 | 0 | 1 | 31.1667 | 1101.5597 | 0.075107
|  | 0.075 | 0.075 | 0 | 0 | 0 | 23 | 859.234 | #DIV/0!
|  | 0.074751 | 0.037375 | 0 | 0.037375 | 0.5 | 16 | 666.6667 | 0.1495
|  | 0.074676 | 0.074676 | 0 | 0 | 0.16667 | 25 | 925 | 0.44806
|  | 0.074676 | 0.074676 | 0 | 0 | 0.16667 | 41.8333 | 878.5 | 0.44806
|  | 0.074601 | 0.074601 | 0 | 0 | 0 | 24.1667 | 902.8183 | #DIV/0!
|  | 0.074557 | 0 | 0 | 0.074557 | 0 | 20.3333 | 904.2287 | #DIV/0!
|  | 0.074557 | 0 | 0 | 0.074557 | 0 | 20.3333 | 904.2287 | #DIV/0!
|  | 0.074082 | 0 | 0 | 0.074082 | 0 | 20.8333 | 926.4638 | #DIV/0!
|  | 0.074049 | 0 | 0.074049 | 0 | 0 | 17.8333 | 749.4647 | #DIV/0!
|  | 0.073803 | 0.073803 | 0 | 0 | 0 | 25.6667 | 958.8553 | #DIV/0!
|  | 0.073607 | 0 | 0 | 0.073607 | 0 | 23.6667 | 1052.4629 | #DIV/0!
|  | 0.0736 | 0 | 0.0736 | 0 | 0 | 20 | 840.5211 | #DIV/0!
|  | 0.0736 | 0 | 0.0736 | 0 | 0 | 20.1667 | 847.5255 | #DIV/0!
|  | 0.073441 | 0.073441 | 0 | 0 | 0.16667 | 7.1667 | 321.2263 | 0.44065
|  | 0.073404 | 0.073404 | 0 | 0 | 0 | 25.1667 | 940.1763 | #DIV/0!
|  | 0.073404 | 0.073404 | 0 | 0 | 0 | 24.1667 | 902.8183 | #DIV/0!
|  | 0.073395 | 0.073395 | 0 | 0 | 0.5 | 32 | 928 | 0.14679
|  | 0.073147 | 0.0033317 | 0 | 0.069815 | 0.33333 | 22.8333 | 966.1503 | 0.21944
|  | 0.073128 | 0.073128 | 0 | 0 | 0.5 | 20.5 | 731.1667 | 0.14626
|  | 0.073037 | 0.036521 | 0 | 0.036515 | 0.16667 | 14.6667 | 659.9117 | 0.43822
|  | 0.073005 | 0.073005 | 0 | 0 | 0 | 23.8333 | 890.3657 | #DIV/0!
|  | 0.072786 | 0.035944 | 0.00089757 | 0.035944 | 0.16667 | 24.5 | 834.3377 | 0.43672
|  | 0.072703 | 0 | 0.072703 | 0 | 0 | 21 | 882.5472 | #DIV/0!
|  | 0.072605 | 0 | 0.00089757 | 0.071707 | 0 | 18.1667 | 807.0617 | #DIV/0!
|  | 0.072182 | 0 | 0 | 0.072182 | 0 | 17.8333 | 793.053 | #DIV/0!
|  | 0.071889 | 0.071889 | 0 | 0 | 0.83333 | 25.8333 | 966.1667 | 0.086267
|  | 0.071884 | 0 | 0.02962 | 0.042265 | 0 | 18.5 | 797.8504 | #DIV/0!
|  | 0.071808 | 0.071808 | 0 | 0 | 0 | 28 | 1046.024 | #DIV/0!
|  | 0.071808 | 0.071808 | 0 | 0 | 0 | 25.6667 | 958.8553 | #DIV/0!
|  | 0.071808 | 0.071808 | 0 | 0 | 0 | 22.6667 | 846.7813 | #DIV/0!
|  | 0.071808 | 0.071808 | 0 | 0 | 0 | 10.8333 | 404.7117 | #DIV/0!
|  | 0.071707 | 0 | 0 | 0.071707 | 0 | 18.8333 | 837.5233 | #DIV/0!
|  | 0.071707 | 0 | 0 | 0.071707 | 0 | 20.3333 | 904.2287 | #DIV/0!
|  | 0.071707 | 0 | 0 | 0.071707 | 0 | 22.1667 | 985.7575 | #DIV/0!
|  | 0.071681 | 0 | 0.00044878 | 0.071233 | 0 | 22.5 | 1000.1735 | #DIV/0!
|  | 0.071205 | 0.035603 | 0 | 0.035603 | 0.33333 | 15.6667 | 857 | 0.21362
|  | 0.07112 | 0 | 0.03477 | 0.03635 | 0.16667 | 23.8333 | 881.8333 | 0.42672
|  | 0.07101 | 0.07101 | 0 | 0 | 0 | 23.3333 | 871.6867 | #DIV/0!
|  | 0.071002 | 0.010807 | 0 | 0.060195 | 0.16667 | 26.6667 | 949.7008 | 0.42601
|  | 0.070782 | 0.070782 | 0 | 0 | 0.33333 | 18.6667 | 834.7263 | 0.21235
|  | 0.070758 | 0 | 0 | 0.070758 | 0 | 18.8333 | 837.5233 | #DIV/0!
|  | 0.070758 | 0 | 0 | 0.070758 | 0 | 17.5 | 778.2296 | #DIV/0!
|  | 0.070611 | 0.070611 | 0 | 0 | 0 | 24.5 | 915.271 | #DIV/0!
|  | 0.070463 | 0 | 0.034823 | 0.03564 | 0.16667 | 24.6667 | 914.7494 | 0.42278
|  | 0.070459 | 0 | 0.070459 | 0 | 0 | 21.1667 | 889.5515 | #DIV/0!
|  | 0.070402 | 0 | 0.022439 | 0.047963 | 0 | 20.1667 | 881.7443 | #DIV/0!
|  | 0.070159 | 0.070159 | 0 | 0 | 0.16667 | 19.8333 | 892.5 | 0.42095
|  | 0.070042 | 0 | 0.0368 | 0.033242 | 0 | 21.1667 | 912.7715 | #DIV/0!
|  | 0.07001 | 0 | 0.07001 | 0 | 0 | 21.3333 | 896.5559 | #DIV/0!
|  | 0.069989 | 0.069989 | 0 | 0 | 0.16667 | 19.5 | 782.08 | 0.41994
|  | 0.069813 | 0.069813 | 0 | 0 | 0 | 6.1667 | 230.3743 | #DIV/0!
|  | 0.069742 | 0.069742 | 0 | 0 | 0.16667 | 41.8333 | 878.5 | 0.41845
|  | 0.069678 | 0.069678 | 0 | 0 | 0.5 | 31 | 899 | 0.13936
|  | 0.069518 | 0.069518 | 0 | 0 | 0.16667 | 35.6667 | 749 | 0.41711
|  | 0.069347 | 0.034855 | 0 | 0.034492 | 0.16667 | 21.1667 | 719.6667 | 0.41608
|  | 0.069333 | 0 | 0 | 0.069333 | 0 | 20.5 | 911.6404 | #DIV/0!
|  | 0.06907 | 0.06907 | 0 | 0 | 0.16667 | 19.3333 | 850.6667 | 0.41442
|  | 0.06907 | 0 | 0.06907 | 0 | 0.33333 | 11.3333 | 748 | 0.20721
|  | 0.069016 | 0.069016 | 0 | 0 | 0 | 28 | 1046.024 | #DIV/0!
|  | 0.069016 | 0.069016 | 0 | 0 | 0 | 10.3333 | 386.0327 | #DIV/0!
|  | 0.068664 | 0 | 0.068664 | 0 | 0 | 14.1667 | 595.3691 | #DIV/0!
|  | 0.068617 | 0.068617 | 0 | 0 | 0 | 24 | 896.592 | #DIV/0!
|  | 0.068248 | 0.068248 | 0 | 0 | 0.16667 | 39.1667 | 827.9527 | 0.40949
|  | 0.068218 | 0.068218 | 0 | 0 | 0 | 24.6667 | 921.4973 | #DIV/0!
|  | 0.068215 | 0 | 0.068215 | 0 | 0 | 16.3333 | 686.4256 | #DIV/0!
|  | 0.06797 | 0.06797 | 0 | 0 | 0.16667 | 38.3333 | 728.3333 | 0.40782
|  | 0.067955 | 0 | 0.031864 | 0.036091 | 0 | 15 | 649.5371 | #DIV/0!
|  | 0.067908 | 0 | 0 | 0.067908 | 0 | 16 | 711.5242 | #DIV/0!
|  | 0.067908 | 0 | 0 | 0.067908 | 0 | 19.8333 | 881.9935 | #DIV/0!
|  | 0.067863 | 0.067863 | 0 | 0 | 0.16667 | 28 | 868 | 0.40718
|  | 0.067819 | 0.067819 | 0 | 0 | 0 | 26.3333 | 983.7607 | #DIV/0!
|  | 0.067819 | 0.067819 | 0 | 0 | 0 | 23.3333 | 871.6867 | #DIV/0!
|  | 0.067819 | 0.067819 | 0 | 0 | 0 | 17.3333 | 647.5387 | #DIV/0!
|  | 0.06742 | 0.06742 | 0 | 0 | 0 | 16.6667 | 622.6333 | #DIV/0!
|  | 0.067317 | 0 | 0.067317 | 0 | 0 | 16 | 672.4169 | #DIV/0!
|  | 0.067021 | 0.067021 | 0 | 0 | 0 | 24.6667 | 921.4973 | #DIV/0!
|  | 0.066977 | 0.066977 | 0 | 0 | 1 | 20 | 746.6667 | 0.066977
|  | 0.066959 | 0 | 0 | 0.066959 | 0 | 17.8333 | 793.053 | #DIV/0!
|  | 0.066959 | 0 | 0 | 0.066959 | 0 | 17.1667 | 763.4062 | #DIV/0!
|  | 0.066869 | 0 | 0.066869 | 0 | 0 | 21.1667 | 889.5515 | #DIV/0!
|  | 0.066649 | 0.066649 | 0 | 0 | 0.66667 | 28.5 | 723.5597 | 0.099974
|  | 0.066635 | 0.066635 | 0 | 0 | 0.83333 | 26.6667 | 1040 | 0.079962
|  | 0.066629 | 0.066629 | 0 | 0 | 0.16667 | 38 | 808.9053 | 0.39977
|  | 0.066622 | 0.066622 | 0 | 0 | 0 | 23.3333 | 871.6867 | #DIV/0!
|  | 0.066622 | 0.066622 | 0 | 0 | 0 | 17.5 | 653.765 | #DIV/0!
|  | 0.066484 | 0 | 0 | 0.066484 | 0 | 16.1667 | 718.9359 | #DIV/0!
|  | 0.066484 | 0 | 0 | 0.066484 | 0 | 15.3333 | 681.8773 | #DIV/0!
|  | 0.06642 | 0 | 0.06642 | 0 | 0 | 18.8333 | 791.4907 | #DIV/0!
|  | 0.06642 | 0 | 0.06642 | 0 | 0 | 21.6667 | 910.5645 | #DIV/0!
|  | 0.066223 | 0.066223 | 0 | 0 | 0 | 22.5 | 840.555 | #DIV/0!
|  | 0.066009 | 0 | 0 | 0.066009 | 0 | 18 | 800.4647 | #DIV/0!
|  | 0.065983 | 0 | 0.00044878 | 0.065534 | 0 | 6.5 | 288.6493 | #DIV/0!
|  | 0.065618 | 0.02942 | 0.0058342 | 0.030364 | 1 | 19.8333 | 860.7916 | 0.065618
|  | 0.065425 | 0.065425 | 0 | 0 | 0 | 17.5 | 653.765 | #DIV/0!
|  | 0.065138 | 0.015719 | 0 | 0.049419 | 0.16667 | 28 | 858.7026 | 0.39083
|  | 0.065074 | 0 | 0.065074 | 0 | 0 | 7.1667 | 301.1867 | #DIV/0!
|  | 0.065059 | 0 | 0 | 0.065059 | 0 | 16.6667 | 741.171 | #DIV/0!
|  | 0.065026 | 0.065026 | 0 | 0 | 0 | 9.3333 | 348.6747 | #DIV/0!
|  | 0.065026 | 0.065026 | 0 | 0 | 0 | 16.8333 | 628.8597 | #DIV/0!
|  | 0.064627 | 0.064627 | 0 | 0 | 0 | 16.1667 | 603.9543 | #DIV/0!
|  | 0.064601 | 0.064601 | 0 | 0 | 0.16667 | 19.5 | 798.5327 | 0.3876
|  | 0.064584 | 0 | 0 | 0.064584 | 0 | 18 | 800.4647 | #DIV/0!
|  | 0.064228 | 0.064228 | 0 | 0 | 0 | 21 | 784.518 | #DIV/0!
|  | 0.064176 | 0 | 0.064176 | 0 | 0 | 21.3333 | 896.5559 | #DIV/0!
|  | 0.064109 | 0 | 0 | 0.064109 | 0 | 17.1667 | 763.4062 | #DIV/0!
|  | 0.063962 | 0.063962 | 0 | 0 | 0.16667 | 28 | 866.549 | 0.38377
|  | 0.063901 | 0.063901 | 0 | 0 | 0.33333 | 13 | 572 | 0.1917
|  | 0.063829 | 0.063829 | 0 | 0 | 0 | 22.1667 | 828.1023 | #DIV/0!
|  | 0.063829 | 0.063829 | 0 | 0 | 0 | 18.3333 | 684.8967 | #DIV/0!
|  | 0.063697 | 0.0028832 | 0 | 0.060813 | 0.16667 | 15.8333 | 704.9071 | 0.38218
|  | 0.063634 | 0 | 0 | 0.063634 | 0 | 11.6667 | 518.8197 | #DIV/0!
|  | 0.063634 | 0 | 0 | 0.063634 | 0 | 16.5 | 733.7593 | #DIV/0!
|  | 0.063431 | 0.063431 | 0 | 0 | 0 | 18.1667 | 678.6703 | #DIV/0!
|  | 0.063431 | 0.063431 | 0 | 0 | 0 | 18.8333 | 703.5757 | #DIV/0!
|  | 0.063378 | 0.063378 | 0 | 0 | 0.33333 | 18.5 | 796.6667 | 0.19013
|  | 0.06319 | 0.06319 | 0 | 0 | 0.16667 | 33.5 | 706.2263 | 0.37914
|  | 0.06316 | 0 | 0 | 0.06316 | 0 | 18.8333 | 837.5233 | #DIV/0!
|  | 0.06316 | 0 | 0 | 0.06316 | 0 | 20 | 889.4052 | #DIV/0!
|  | 0.062945 | 0.031235 | 0 | 0.03171 | 0.33333 | 23.5 | 765.745 | 0.18884
|  | 0.062876 | 0 | 0.058209 | 0.0046666 | 0.16667 | 34.8333 | 801.1667 | 0.37726
|  | 0.062812 | 0.062812 | 0 | 0 | 0.16667 | 17.6667 | 600.6667 | 0.37687
|  | 0.062633 | 0.062633 | 0 | 0 | 0 | 20 | 747.16 | #DIV/0!
|  | 0.062492 | 0.062492 | 0 | 0 | 0.16667 | 18.1667 | 799.3333 | 0.37495
|  | 0.06221 | 0 | 0 | 0.06221 | 0 | 14.3333 | 637.4071 | #DIV/0!
|  | 0.062139 | 0.062139 | 0 | 0 | 0.16667 | 31.1667 | 716.8333 | 0.37284
|  | 0.062139 | 0.031192 | 0 | 0.030947 | 0.16667 | 30.8333 | 709.1667 | 0.37284
|  | 0.062086 | 0.062086 | 0 | 0 | 0.16667 | 19 | 646 | 0.37252
|  | 0.061894 | 0 | 0.030947 | 0.030947 | 0.16667 | 7.3333 | 168.6667 | 0.37136
|  | 0.061851 | 0.030925 | 0 | 0.030925 | 1.1667 | 16.3333 | 844.6667 | 0.053015
|  | 0.061709 | 0 | 0.00044878 | 0.06126 | 0 | 18.1667 | 807.4691 | #DIV/0!
|  | 0.061595 | 0.030797 | 0 | 0.030797 | 2.6667 | 16 | 721 | 0.023098
|  | 0.061575 | 0.0075498 | 0.025581 | 0.028445 | 0.33333 | 16.5 | 745.196 | 0.18473
|  | 0.061436 | 0.061436 | 0 | 0 | 0 | 22.1667 | 828.1023 | #DIV/0!
|  | 0.061436 | 0.061436 | 0 | 0 | 0 | 20.1667 | 753.3863 | #DIV/0!
|  | 0.061436 | 0.061436 | 0 | 0 | 0 | 19.3333 | 722.2547 | #DIV/0!
|  | 0.061317 | 0.030658 | 0 | 0.030658 | 0.5 | 23 | 667 | 0.12263
|  | 0.060869 | 0.060869 | 0 | 0 | 0.33333 | 18 | 788.679 | 0.18261
|  | 0.060785 | 0 | 0 | 0.060785 | 0 | 17.1667 | 763.4062 | #DIV/0!
|  | 0.060666 | 0 | 0.060666 | 0 | 0.16667 | 20.6667 | 475.3333 | 0.36399
|  | 0.060649 | 0.03021 | 0 | 0.030439 | 0.16667 | 29.6667 | 685.9117 | 0.3639
|  | 0.060638 | 0.060638 | 0 | 0 | 0 | 20 | 747.16 | #DIV/0!
|  | 0.060638 | 0.060638 | 0 | 0 | 0 | 17.1667 | 641.3123 | #DIV/0!
|  | 0.060463 | 0.0068984 | 0 | 0.053564 | 0.16667 | 19.3333 | 734.6667 | 0.36278
|  | 0.06031 | 0 | 0 | 0.06031 | 0 | 17.3333 | 770.8179 | #DIV/0!
|  | 0.06031 | 0 | 0 | 0.06031 | 0 | 16.5 | 733.7593 | #DIV/0!
|  | 0.06031 | 0 | 0 | 0.06031 | 0 | 18 | 800.4647 | #DIV/0!
|  | 0.060274 | 0.060274 | 0 | 0 | 0.16667 | 39.5 | 832.2263 | 0.36165
|  | 0.0601 | 0.0601 | 0 | 0 | 0.16667 | 37.5 | 787.5 | 0.3606
|  | 0.06004 | 0.026654 | 0.0067317 | 0.026654 | 0.16667 | 16.6667 | 657.0608 | 0.36024
|  | 0.05984 | 0.05984 | 0 | 0 | 0 | 22.1667 | 828.1023 | #DIV/0!
|  | 0.05984 | 0.05984 | 0 | 0 | 0 | 21.8333 | 815.6497 | #DIV/0!
|  | 0.05984 | 0.05984 | 0 | 0 | 0 | 17.1667 | 641.3123 | #DIV/0!
|  | 0.05984 | 0.05984 | 0 | 0 | 0 | 7.1667 | 267.7323 | #DIV/0!
|  | 0.059835 | 0 | 0 | 0.059835 | 0 | 14.6667 | 652.2305 | #DIV/0!
|  | 0.059688 | 0 | 0.059688 | 0 | 0 | 15 | 630.3908 | #DIV/0!
|  | 0.059683 | 0.059683 | 0 | 0 | 0.16667 | 37.5 | 862.5 | 0.3581
|  | 0.059441 | 0.059441 | 0 | 0 | 0 | 17.6667 | 659.9913 | #DIV/0!
|  | 0.059441 | 0.059441 | 0 | 0 | 0 | 15.5 | 579.049 | #DIV/0!
|  | 0.05936 | 0 | 0 | 0.05936 | 0 | 18.6667 | 830.1115 | #DIV/0!
|  | 0.05936 | 0 | 0 | 0.05936 | 0 | 18.6667 | 830.1115 | #DIV/0!
|  | 0.05936 | 0 | 0 | 0.05936 | 0 | 16 | 711.5242 | #DIV/0!
|  | 0.059239 | 0 | 0.059239 | 0 | 0 | 17.1667 | 721.4473 | #DIV/0!
|  | 0.059203 | 0.059203 | 0 | 0 | 0.16667 | 32.6667 | 686 | 0.35522
|  | 0.059176 | 0.001228 | 0 | 0.057948 | 0.16667 | 18.3333 | 425.245 | 0.35505
|  | 0.059087 | 0.059087 | 0 | 0 | 0.16667 | 16.3333 | 621.6293 | 0.35452
|  | 0.059054 | 0.059054 | 0 | 0 | 0.5 | 38.3333 | 813.179 | 0.11811
|  | 0.058989 | 0.058989 | 0 | 0 | 1 | 33.8333 | 771.1667 | 0.058989
|  | 0.058925 | 0.058925 | 0 | 0 | 0.16667 | 26 | 806 | 0.35355
|  | 0.058891 | 0.027925 | 0.030966 | 0 | 0 | 20.5 | 813.2976 | #DIV/0!
|  | 0.058886 | 0 | 0 | 0.058886 | 0 | 3.5 | 155.6459 | #DIV/0!
|  | 0.058886 | 0 | 0 | 0.058886 | 0 | 17 | 755.9944 | #DIV/0!
|  | 0.058861 | 0.0011106 | 0.028875 | 0.028875 | 0.33333 | 12.3333 | 641.3333 | 0.17658
|  | 0.05884 | 0.05884 | 0 | 0 | 0.83333 | 20 | 760 | 0.070607
|  | 0.058722 | 0 | 0.028736 | 0.029986 | 0.16667 | 15.6667 | 611 | 0.35233
|  | 0.058594 | 0.058594 | 0 | 0 | 0.16667 | 25 | 775 | 0.35156
|  | 0.058411 | 0 | 0 | 0.058411 | 0 | 18.8333 | 837.5233 | #DIV/0!
|  | 0.058411 | 0 | 0 | 0.058411 | 0 | 17.8333 | 793.053 | #DIV/0!
|  | 0.058342 | 0 | 0.058342 | 0 | 0 | 17.8333 | 749.4647 | #DIV/0!
|  | 0.058306 | 0 | 0.029153 | 0.029153 | 0.16667 | 16.3333 | 637 | 0.34983
|  | 0.058263 | 0.058263 | 0 | 0 | 0.16667 | 14.3333 | 630.6667 | 0.34958
|  | 0.058263 | 0.058263 | 0 | 0 | 0.16667 | 17.3333 | 537.3333 | 0.34958
|  | 0.05822 | 0.05822 | 0 | 0 | 1 | 28 | 877.3333 | 0.05822
|  | 0.058191 | 0 | 0.028273 | 0.029918 | 0 | 12.6667 | 547.81 | #DIV/0!
|  | 0.057936 | 0 | 0 | 0.057936 | 0 | 17.6667 | 785.6413 | #DIV/0!
|  | 0.057936 | 0 | 0 | 0.057936 | 0 | 18.8333 | 837.5233 | #DIV/0!
|  | 0.057889 | 0 | 0.027903 | 0.029986 | 0.16667 | 19.5 | 760.5 | 0.34733
|  | 0.057845 | 0.057845 | 0 | 0 | 0 | 23.3333 | 871.6867 | #DIV/0!
|  | 0.057845 | 0.057845 | 0 | 0 | 0 | 17.8333 | 666.2177 | #DIV/0!
|  | 0.057761 | 0.057761 | 0 | 0 | 2.1667 | 19.5 | 901.5 | 0.026659
|  | 0.057563 | 0.0011106 | 0.00044878 | 0.056004 | 0.33333 | 15.3333 | 794.4161 | 0.17269
|  | 0.057461 | 0 | 0 | 0.057461 | 0 | 16.5 | 733.7593 | #DIV/0!
|  | 0.057447 | 0.057447 | 0 | 0 | 0 | 22.5 | 840.555 | #DIV/0!
|  | 0.057447 | 0.057447 | 0 | 0 | 0 | 18 | 672.444 | #DIV/0!
|  | 0.057444 | 0 | 0.057444 | 0 | 0 | 3.3333 | 140.0869 | #DIV/0!
|  | 0.057444 | 0 | 0.057444 | 0 | 0 | 16.6667 | 700.4343 | #DIV/0!
|  | 0.057435 | 0 | 0.00044878 | 0.056986 | 0 | 14.3333 | 636.9997 | #DIV/0!
|  | 0.057435 | 0 | 0.00044878 | 0.056986 | 0 | 15.1667 | 674.0583 | #DIV/0!
|  | 0.057135 | 0.057135 | 0 | 0 | 1 | 23.1667 | 891.7263 | 0.057135
|  | 0.056995 | 0 | 0.056995 | 0 | 0 | 15.8333 | 665.4126 | #DIV/0!
|  | 0.05696 | 0 | 0.00044878 | 0.056511 | 0 | 12.8333 | 570.2943 | #DIV/0!
|  | 0.05664 | 0.05664 | 0 | 0 | 0.16667 | 17 | 578 | 0.33984
|  | 0.056608 | 0.056608 | 0 | 0 | 0.16667 | 17.6667 | 547.6667 | 0.33965
|  | 0.056608 | 0.056608 | 0 | 0 | 0.16667 | 21.1667 | 656.1667 | 0.33965
|  | 0.056512 | 0.056512 | 0 | 0 | 0.5 | 25.5 | 714 | 0.11302
|  | 0.056474 | 0.0019649 | 0 | 0.054509 | 0.16667 | 29.3333 | 678.245 | 0.33884
|  | 0.056223 | 0.056223 | 0 | 0 | 0.16667 | 2.3333 | 105 | 0.33734
|  | 0.056098 | 0 | 0.056098 | 0 | 0 | 19.3333 | 812.5037 | #DIV/0!
|  | 0.056081 | 0.056081 | 0 | 0 | 0.16667 | 21 | 652.0597 | 0.33649
|  | 0.056036 | 0 | 0 | 0.056036 | 0 | 14.3333 | 637.4071 | #DIV/0!
|  | 0.056036 | 0 | 0 | 0.056036 | 0 | 14.6667 | 652.2305 | #DIV/0!
|  | 0.055984 | 0 | 0.00089757 | 0.055087 | 0 | 16.1667 | 718.5285 | #DIV/0!
|  | 0.055906 | 0 | 0.0022439 | 0.053662 | 0 | 15.6667 | 694.6639 | #DIV/0!
|  | 0.055851 | 0.055851 | 0 | 0 | 0 | 19.5 | 728.481 | #DIV/0!
|  | 0.055843 | 0.055843 | 0 | 0 | 0.16667 | 14.3333 | 629.5597 | 0.33506
|  | 0.055753 | 0 | 0.055753 | 0 | 0.16667 | 30.3333 | 697.6667 | 0.33452
|  | 0.055743 | 0.027871 | 0 | 0.027871 | 1.1667 | 21 | 870 | 0.047779
|  | 0.055561 | 0 | 0 | 0.055561 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.055561 | 0 | 0 | 0.055561 | 0 | 16 | 711.5242 | #DIV/0!
|  | 0.055551 | 0.027551 | 0.00044878 | 0.027551 | 0.16667 | 19.5 | 838.3377 | 0.3333
|  | 0.055535 | 0 | 0.00044878 | 0.055087 | 0 | 15.6667 | 696.2934 | #DIV/0!
|  | 0.055452 | 0.055452 | 0 | 0 | 0 | 18.5 | 691.123 | #DIV/0!
|  | 0.055452 | 0.055452 | 0 | 0 | 0 | 16.5 | 616.407 | #DIV/0!
|  | 0.055444 | 0.055444 | 0 | 0 | 0.16667 | 11.5 | 506 | 0.33266
|  | 0.05539 | 0 | 0.026654 | 0.028736 | 0.16667 | 14.6667 | 572 | 0.33234
|  | 0.055351 | 0.055351 | 0 | 0 | 0.16667 | 20.1667 | 626.2263 | 0.33211
|  | 0.055209 | 0.055209 | 0 | 0 | 0.33333 | 12.6667 | 595.3333 | 0.16563
|  | 0.0552 | 0 | 0.0552 | 0 | 0 | 14.8333 | 623.3865 | #DIV/0!
|  | 0.055087 | 0 | 0 | 0.055087 | 0 | 15.8333 | 704.1125 | #DIV/0!
|  | 0.055053 | 0.055053 | 0 | 0 | 0 | 17.5 | 653.765 | #DIV/0!
|  | 0.055053 | 0.055053 | 0 | 0 | 0 | 16.3333 | 610.1807 | #DIV/0!
|  | 0.054952 | 0.054952 | 0 | 0 | 0.16667 | 22.5 | 697.5 | 0.32971
|  | 0.054942 | 0.054942 | 0 | 0 | 0.16667 | 33.8333 | 710.5 | 0.32965
|  | 0.054846 | 0.054846 | 0 | 0 | 1 | 12 | 428 | 0.054846
|  | 0.054751 | 0 | 0.054751 | 0 | 0 | 11.6667 | 490.304 | #DIV/0!
|  | 0.054654 | 0.054654 | 0 | 0 | 0 | 19 | 709.802 | #DIV/0!
|  | 0.054184 | 0.054184 | 0 | 0 | 0.16667 | 16.5 | 709.5 | 0.3251
|  | 0.054137 | 0 | 0 | 0.054137 | 0 | 14.1667 | 629.9954 | #DIV/0!
|  | 0.053735 | 0.053735 | 0 | 0 | 0.16667 | 18.8333 | 640.3333 | 0.32241
|  | 0.053662 | 0 | 0 | 0.053662 | 0 | 11.8333 | 526.2314 | #DIV/0!
|  | 0.053662 | 0 | 0 | 0.053662 | 0 | 16.1667 | 718.9359 | #DIV/0!
|  | 0.053557 | 0.053557 | 0 | 0 | 0.83333 | 26 | 683.0597 | 0.064269
|  | 0.053457 | 0.053457 | 0 | 0 | 0 | 22.1667 | 828.1023 | #DIV/0!
|  | 0.053457 | 0.053457 | 0 | 0 | 0 | 21.3333 | 796.9707 | #DIV/0!
|  | 0.053058 | 0.053058 | 0 | 0 | 0 | 14.6667 | 547.9173 | #DIV/0!
|  | 0.053009 | 0.027231 | 0 | 0.025778 | 0.16667 | 23 | 782 | 0.31805
|  | 0.052956 | 0 | 0.052956 | 0 | 0 | 13.5 | 567.3518 | #DIV/0!
|  | 0.052956 | 0 | 0.052956 | 0 | 0 | 18 | 756.469 | #DIV/0!
|  | 0.052712 | 0 | 0 | 0.052712 | 0 | 15.5 | 689.2891 | #DIV/0!
|  | 0.052712 | 0 | 0 | 0.052712 | 0 | 16.8333 | 748.5827 | #DIV/0!
|  | 0.052712 | 0 | 0 | 0.052712 | 0 | 15.1667 | 674.4656 | #DIV/0!
|  | 0.052667 | 0.026334 | 0 | 0.026334 | 1.1667 | 16.3333 | 639.3333 | 0.045143
|  | 0.052659 | 0.052659 | 0 | 0 | 0 | 17.3333 | 647.5387 | #DIV/0!
|  | 0.052636 | 0.00039893 | 0 | 0.052237 | 0 | 12.5 | 554.6929 | #DIV/0!
|  | 0.052625 | 0.052625 | 0 | 0 | 0.16667 | 12 | 528 | 0.31575
|  | 0.052508 | 0 | 0.052508 | 0 | 0 | 14 | 588.3648 | #DIV/0!
|  | 0.05226 | 0.05226 | 0 | 0 | 0 | 17.3333 | 647.5387 | #DIV/0!
|  | 0.052155 | 0.052155 | 0 | 0 | 0.16667 | 13.8333 | 608.6667 | 0.31293
|  | 0.051927 | 0.051927 | 0 | 0 | 0.16667 | 28.6667 | 607.4527 | 0.31156
|  | 0.051762 | 0 | 0 | 0.051762 | 0 | 17 | 755.9944 | #DIV/0!
|  | 0.051628 | 0.051628 | 0 | 0 | 0.16667 | 18.6667 | 635.786 | 0.30977
|  | 0.05161 | 0 | 0.05161 | 0 | 0 | 14.5 | 609.3778 | #DIV/0!
|  | 0.051562 | 0.0011106 | 0 | 0.050451 | 0.33333 | 9.5 | 492.745 | 0.15469
|  | 0.051462 | 0.051462 | 0 | 0 | 0 | 17.6667 | 659.9913 | #DIV/0!
|  | 0.051418 | 0.051418 | 0 | 0 | 0.16667 | 1.3333 | 60 | 0.30851
|  | 0.051277 | 0 | 0.024683 | 0.026593 | 0 | 13.1667 | 569.6378 | #DIV/0!
|  | 0.051271 | 0 | 0.016605 | 0.034667 | 0 | 14.5 | 634.6346 | #DIV/0!
|  | 0.051229 | 0.051229 | 0 | 0 | 0.16667 | 15.8333 | 538.893 | 0.30738
|  | 0.051183 | 0 | 0.0017951 | 0.049388 | 0 | 17 | 754.365 | #DIV/0!
|  | 0.051161 | 0 | 0.051161 | 0 | 0 | 15.1667 | 637.3952 | #DIV/0!
|  | 0.051144 | 0.051144 | 0 | 0 | 0.16667 | 12.5 | 548.893 | 0.30686
|  | 0.051064 | 0.051064 | 0 | 0 | 0 | 18.6667 | 697.3493 | #DIV/0!
|  | 0.051064 | 0.051064 | 0 | 0 | 0 | 16 | 597.728 | #DIV/0!
|  | 0.051064 | 0.051064 | 0 | 0 | 0 | 16 | 597.728 | #DIV/0!
|  | 0.051064 | 0.051064 | 0 | 0 | 0 | 3.8333 | 143.2057 | #DIV/0!
|  | 0.051064 | 0.051064 | 0 | 0 | 0 | 16.3333 | 610.1807 | #DIV/0!
|  | 0.050813 | 0 | 0 | 0.050813 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.050813 | 0 | 0 | 0.050813 | 0 | 15.8333 | 704.1125 | #DIV/0!
|  | 0.050712 | 0 | 0.050712 | 0 | 0 | 14 | 588.3648 | #DIV/0!
|  | 0.050696 | 0.050696 | 0 | 0 | 0.16667 | 33.3333 | 642.5123 | 0.30418
|  | 0.050665 | 0.050665 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.050489 | 0 | 0.050489 | 0 | 0.33333 | 13.8333 | 594.671 | 0.15147
|  | 0.050338 | 0 | 0 | 0.050338 | 0 | 12.8333 | 570.7017 | #DIV/0!
|  | 0.049976 | 0 | 0.049976 | 0 | 0.33333 | 10.3333 | 537.3333 | 0.14993
|  | 0.049912 | 0.049912 | 0 | 0 | 0.16667 | 27 | 513 | 0.29947
|  | 0.049891 | 0.049891 | 0 | 0 | 1.8333 | 18.3333 | 486.6667 | 0.027213
|  | 0.049867 | 0.049867 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.049863 | 0 | 0 | 0.049863 | 0 | 13.8333 | 615.172 | #DIV/0!
|  | 0.049815 | 0 | 0.049815 | 0 | 0 | 16.1667 | 679.4212 | #DIV/0!
|  | 0.049388 | 0 | 0 | 0.049388 | 0 | 11.1667 | 496.5846 | #DIV/0!
|  | 0.049388 | 0 | 0 | 0.049388 | 0 | 12.5 | 555.8783 | #DIV/0!
|  | 0.049094 | 0.049094 | 0 | 0 | 0.16667 | 26.8333 | 512.893 | 0.29456
|  | 0.049074 | 0 | 0.046225 | 0.0028493 | 0 | 12.8333 | 541.7786 | #DIV/0!
|  | 0.049069 | 0.049069 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.049069 | 0.049069 | 0 | 0 | 0 | 15.8333 | 591.5017 | #DIV/0!
|  | 0.049069 | 0.049069 | 0 | 0 | 0 | 15.1667 | 566.5963 | #DIV/0!
|  | 0.048913 | 0 | 0 | 0.048913 | 0 | 13.8333 | 615.172 | #DIV/0!
|  | 0.048727 | 0 | 0.023739 | 0.024988 | 0.16667 | 15.1667 | 591.5 | 0.29236
|  | 0.048695 | 0.048695 | 0 | 0 | 0.16667 | 12.6667 | 481.3333 | 0.29217
|  | 0.04867 | 0.04867 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.048469 | 0 | 0.048469 | 0 | 0 | 1.3333 | 56.0347 | #DIV/0!
|  | 0.048438 | 0 | 0 | 0.048438 | 0 | 10.3333 | 459.526 | #DIV/0!
|  | 0.048438 | 0 | 0 | 0.048438 | 0 | 14.5 | 644.8188 | #DIV/0!
|  | 0.048438 | 0 | 0 | 0.048438 | 0 | 15.6667 | 696.7008 | #DIV/0!
|  | 0.048438 | 0 | 0 | 0.048438 | 0 | 14 | 622.5837 | #DIV/0!
|  | 0.048438 | 0 | 0 | 0.048438 | 0 | 16 | 711.5242 | #DIV/0!
|  | 0.048271 | 0.048271 | 0 | 0 | 0 | 19 | 709.802 | #DIV/0!
|  | 0.048271 | 0.048271 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.048271 | 0.048271 | 0 | 0 | 0 | 3.3333 | 124.5267 | #DIV/0!
|  | 0.04802 | 0 | 0.04802 | 0 | 0 | 15.1667 | 637.3952 | #DIV/0!
|  | 0.047963 | 0 | 0 | 0.047963 | 0 | 13.1667 | 585.5251 | #DIV/0!
|  | 0.047872 | 0.047872 | 0 | 0 | 0 | 13.6667 | 510.5593 | #DIV/0!
|  | 0.047571 | 0 | 0.047571 | 0 | 0 | 15.3333 | 644.3995 | #DIV/0!
|  | 0.047473 | 0.047473 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.047473 | 0.047473 | 0 | 0 | 0 | 10.3333 | 386.0327 | #DIV/0!
|  | 0.047413 | 0.047413 | 0 | 0 | 0.16667 | 15.5 | 573.5 | 0.28448
|  | 0.047413 | 0.047413 | 0 | 0 | 0.83333 | 11.6667 | 431.6667 | 0.056896
|  | 0.047285 | 0 | 0.047285 | 0 | 0.33333 | 12.3333 | 666 | 0.14186
|  | 0.047268 | 0.047268 | 0 | 0 | 0.16667 | 28.6667 | 604.7263 | 0.28361
|  | 0.047122 | 0 | 0.047122 | 0 | 0 | 14.8333 | 623.3865 | #DIV/0!
|  | 0.047119 | 0.024219 | 0 | 0.0229 | 0.33333 | 16.8333 | 707.4117 | 0.14136
|  | 0.047074 | 0.047074 | 0 | 0 | 0 | 14.1667 | 529.2383 | #DIV/0!
|  | 0.047074 | 0.047074 | 0 | 0 | 0 | 17.5 | 653.765 | #DIV/0!
|  | 0.046986 | 0.046986 | 0 | 0 | 0.16667 | 0.16667 | 7.3333 | 0.28192
|  | 0.046673 | 0 | 0.046673 | 0 | 0 | 14.1667 | 595.3691 | #DIV/0!
|  | 0.046666 | 0.046666 | 0 | 0 | 0.16667 | 21.1667 | 402.1667 | 0.27999
|  | 0.046644 | 0.023322 | 0 | 0.023322 | 0.16667 | 17 | 663 | 0.27987
|  | 0.046637 | 0.0052859 | 0.00044878 | 0.040902 | 0.16667 | 15.3333 | 683.4124 | 0.27982
|  | 0.046539 | 0 | 0 | 0.046539 | 0 | 12.5 | 555.8783 | #DIV/0!
|  | 0.046404 | 0.001228 | 0 | 0.045176 | 0.16667 | 25 | 578.5784 | 0.27842
|  | 0.046276 | 0.046276 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.046253 | 0.046253 | 0 | 0 | 0.16667 | 23 | 440.0597 | 0.27752
|  | 0.046228 | 0.0024988 | 0 | 0.043729 | 0.16667 | 15.8333 | 617.5 | 0.27737
|  | 0.046185 | 0.024016 | 0 | 0.022169 | 0.66667 | 11.3333 | 490.1667 | 0.069278
|  | 0.04614 | 0.04614 | 0 | 0 | 0.66667 | 15.3333 | 651.9527 | 0.069209
|  | 0.046064 | 0 | 0 | 0.046064 | 0 | 12.5 | 555.8783 | #DIV/0!
|  | 0.046064 | 0 | 0 | 0.046064 | 0 | 12.8333 | 570.7017 | #DIV/0!
|  | 0.046038 | 0 | 0.00044878 | 0.045589 | 0 | 11.6667 | 518.4124 | #DIV/0!
|  | 0.045922 | 0.045922 | 0 | 0 | 0.16667 | 28.3333 | 597.7263 | 0.27553
|  | 0.045913 | 0.022842 | 0 | 0.023071 | 0.16667 | 24.3333 | 563.245 | 0.27548
|  | 0.045877 | 0.045877 | 0 | 0 | 0 | 16.1667 | 603.9543 | #DIV/0!
|  | 0.045589 | 0 | 0 | 0.045589 | 0 | 8.1667 | 363.1738 | #DIV/0!
|  | 0.045589 | 0 | 0 | 0.045589 | 0 | 12.5 | 555.8783 | #DIV/0!
|  | 0.045589 | 0 | 0 | 0.045589 | 0 | 13.5 | 600.3485 | #DIV/0!
|  | 0.045589 | 0 | 0 | 0.045589 | 0 | 11.5 | 511.408 | #DIV/0!
|  | 0.045506 | 0.045506 | 0 | 0 | 0.16667 | 11 | 482.893 | 0.27303
|  | 0.045478 | 0.045478 | 0 | 0 | 0 | 13.1667 | 491.8803 | #DIV/0!
|  | 0.045478 | 0.045478 | 0 | 0 | 0 | 12.1667 | 454.5223 | #DIV/0!
|  | 0.045327 | 0 | 0.045327 | 0 | 0 | 10.6667 | 448.2779 | #DIV/0!
|  | 0.045114 | 0 | 0 | 0.045114 | 0 | 12 | 533.6431 | #DIV/0!
|  | 0.04508 | 0.04508 | 0 | 0 | 0 | 14 | 523.012 | #DIV/0!
|  | 0.04508 | 0.04508 | 0 | 0 | 0 | 15.5 | 579.049 | #DIV/0!
|  | 0.045043 | 0.022521 | 0 | 0.022521 | 0.5 | 17 | 677 | 0.090085
|  | 0.044979 | 0 | 0.022073 | 0.022906 | 0.16667 | 14.3333 | 559 | 0.26987
|  | 0.04484 | 0.04484 | 0 | 0 | 0.16667 | 31.5 | 598.5 | 0.26904
|  | 0.044816 | 0 | 0.02962 | 0.015196 | 0 | 14.1667 | 605.1459 | #DIV/0!
|  | 0.044801 | 0 | 0.0053854 | 0.039415 | 0 | 11.6667 | 515.1534 | #DIV/0!
|  | 0.044681 | 0.044681 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.044681 | 0.044681 | 0 | 0 | 0 | 14.8333 | 554.1437 | #DIV/0!
|  | 0.044639 | 0 | 0 | 0.044639 | 0 | 12.1667 | 541.0548 | #DIV/0!
|  | 0.044527 | 0.044527 | 0 | 0 | 0.16667 | 23.5 | 498.9527 | 0.26716
|  | 0.044429 | 0 | 0.044429 | 0 | 0 | 13.5 | 567.3518 | #DIV/0!
|  | 0.044429 | 0 | 0.044429 | 0 | 0 | 7.5 | 315.1954 | #DIV/0!
|  | 0.044429 | 0 | 0.044429 | 0 | 0 | 12.8333 | 539.3344 | #DIV/0!
|  | 0.044367 | 0 | 0.029171 | 0.015196 | 0 | 12.8333 | 547.4817 | #DIV/0!
|  | 0.044338 | 0.022169 | 0 | 0.022169 | 1.1667 | 4.6667 | 230.6667 | 0.038004
|  | 0.044282 | 0.044282 | 0 | 0 | 0 | 15.8333 | 591.5017 | #DIV/0!
|  | 0.044282 | 0.044282 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.044282 | 0.044282 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.04421 | 0.00098244 | 0 | 0.043227 | 0.16667 | 26 | 598 | 0.26526
|  | 0.04421 | 0.04421 | 0 | 0 | 0.16667 | 11.8333 | 532.5 | 0.26526
|  | 0.044164 | 0 | 0 | 0.044164 | 0 | 11.6667 | 518.8197 | #DIV/0!
|  | 0.044085 | 0 | 0.042186 | 0.0018995 | 0 | 12.8333 | 540.5565 | #DIV/0!
|  | 0.043981 | 0 | 0.043981 | 0 | 0 | 12.6667 | 532.33 | #DIV/0!
|  | 0.043905 | 0.021614 | 0.00044878 | 0.021843 | 0.16667 | 25.5 | 593.2494 | 0.26343
|  | 0.043883 | 0.043883 | 0 | 0 | 0 | 14.1667 | 529.2383 | #DIV/0!
|  | 0.043689 | 0 | 0 | 0.043689 | 0 | 13.6667 | 607.7602 | #DIV/0!
|  | 0.043532 | 0 | 0.043532 | 0 | 0 | 14.1667 | 595.3691 | #DIV/0!
|  | 0.043484 | 0.043484 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.043214 | 0 | 0 | 0.043214 | 0 | 11.3333 | 503.9963 | #DIV/0!
|  | 0.043147 | 0.013263 | 0 | 0.029884 | 0.33333 | 20 | 590.3513 | 0.12944
|  | 0.043085 | 0.043085 | 0 | 0 | 0 | 14.6667 | 547.9173 | #DIV/0!
|  | 0.043085 | 0.043085 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.043085 | 0.043085 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.043083 | 0 | 0.043083 | 0 | 0 | 15.1667 | 637.3952 | #DIV/0!
|  | 0.043071 | 0.043071 | 0 | 0 | 0.5 | 12.8333 | 492.2263 | 0.086142
|  | 0.043056 | 0.043056 | 0 | 0 | 0.16667 | 24.1667 | 507.5 | 0.25834
|  | 0.04299 | 0 | 0.020195 | 0.022794 | 0 | 11.6667 | 504.9692 | #DIV/0!
|  | 0.04274 | 0 | 0 | 0.04274 | 0 | 9.5 | 422.4675 | #DIV/0!
|  | 0.042686 | 0.042686 | 0 | 0 | 0 | 13.3333 | 498.1067 | #DIV/0!
|  | 0.042686 | 0.042686 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.042686 | 0.042686 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.042666 | 0 | 0.0094244 | 0.033242 | 0 | 12.1667 | 535.3517 | #DIV/0!
|  | 0.042634 | 0 | 0.042634 | 0 | 0 | 9.3333 | 392.2432 | #DIV/0!
|  | 0.042634 | 0 | 0.042634 | 0 | 0 | 11 | 462.2866 | #DIV/0!
|  | 0.042608 | 0.00040579 | 0 | 0.042202 | 0.33333 | 25.3333 | 481.3333 | 0.12782
|  | 0.042373 | 0.042373 | 0 | 0 | 0.16667 | 14.3333 | 444.3333 | 0.25424
|  | 0.042287 | 0.042287 | 0 | 0 | 0 | 15.3333 | 572.8227 | #DIV/0!
|  | 0.042287 | 0.042287 | 0 | 0 | 0 | 13.1667 | 491.8803 | #DIV/0!
|  | 0.042287 | 0.042287 | 0 | 0 | 0 | 14.1667 | 529.2383 | #DIV/0!
|  | 0.042265 | 0 | 0 | 0.042265 | 0 | 7.6667 | 340.9387 | #DIV/0!
|  | 0.042265 | 0 | 0 | 0.042265 | 0 | 12.1667 | 541.0548 | #DIV/0!
|  | 0.042186 | 0 | 0.042186 | 0 | 0 | 11.5 | 483.2996 | #DIV/0!
|  | 0.042186 | 0 | 0.042186 | 0 | 0 | 14.1667 | 595.3691 | #DIV/0!
|  | 0.042186 | 0 | 0.042186 | 0 | 0 | 13 | 546.3387 | #DIV/0!
|  | 0.041888 | 0.041888 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.041784 | 0 | 0.032761 | 0.0090228 | 0 | 11 | 468.8045 | #DIV/0!
|  | 0.041737 | 0 | 0.041737 | 0 | 0 | 14.3333 | 602.3735 | #DIV/0!
|  | 0.041315 | 0 | 0 | 0.041315 | 0 | 9.8333 | 437.2909 | #DIV/0!
|  | 0.041315 | 0 | 0 | 0.041315 | 0 | 11.5 | 511.408 | #DIV/0!
|  | 0.041315 | 0 | 0 | 0.041315 | 0 | 11.5 | 511.408 | #DIV/0!
|  | 0.041262 | 0.020631 | 0 | 0.020631 | 0.83333 | 13 | 417 | 0.049515
|  | 0.04117 | 0.04117 | 0 | 0 | 0.16667 | 19.6667 | 454.7263 | 0.24702
|  | 0.041145 | 0.013455 | 0 | 0.02769 | 0.16667 | 12.3333 | 552.7045 | 0.24687
|  | 0.04109 | 0.04109 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.04109 | 0.04109 | 0 | 0 | 0 | 11.8333 | 442.0697 | #DIV/0!
|  | 0.041038 | 0.041038 | 0 | 0 | 0.16667 | 25.8333 | 542.5 | 0.24623
|  | 0.04084 | 0 | 0 | 0.04084 | 0 | 12.1667 | 541.0548 | #DIV/0!
|  | 0.04084 | 0 | 0 | 0.04084 | 0 | 11.1667 | 496.5846 | #DIV/0!
|  | 0.04084 | 0 | 0 | 0.04084 | 0 | 8.5 | 377.9972 | #DIV/0!
|  | 0.04084 | 0 | 0 | 0.04084 | 0 | 10.6667 | 474.3495 | #DIV/0!
|  | 0.040691 | 0.040691 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.040691 | 0.040691 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.040579 | 0.0036521 | 0 | 0.036927 | 0.33333 | 20.3333 | 386.3333 | 0.12174
|  | 0.04039 | 0 | 0.04039 | 0 | 0 | 13.8333 | 581.3604 | #DIV/0!
|  | 0.040365 | 0 | 0 | 0.040365 | 0 | 10.5 | 466.9377 | #DIV/0!
|  | 0.040292 | 0.040292 | 0 | 0 | 0 | 14.6667 | 547.9173 | #DIV/0!
|  | 0.040045 | 0.020023 | 0 | 0.020023 | 1.6667 | 13.3333 | 500 | 0.024027
|  | 0.039942 | 0 | 0.039942 | 0 | 0 | 11.8333 | 497.3083 | #DIV/0!
|  | 0.039942 | 0 | 0.039942 | 0 | 0 | 13.8333 | 581.3604 | #DIV/0!
|  | 0.039938 | 0.039938 | 0 | 0 | 0.16667 | 12.3333 | 419.3333 | 0.23963
|  | 0.039893 | 0.039893 | 0 | 0 | 0 | 14.1667 | 529.2383 | #DIV/0!
|  | 0.039893 | 0.039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.039893 | 0.039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.039893 | 0.039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.039893 | 0.039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.03989 | 0 | 0 | 0.03989 | 0 | 10.1667 | 452.1143 | #DIV/0!
|  | 0.039778 | 0 | 0.019489 | 0.020289 | 0.16667 | 18 | 450 | 0.23867
|  | 0.039723 | 0 | 0.027376 | 0.012347 | 0 | 12.3333 | 528.5055 | #DIV/0!
|  | 0.039662 | 0.039662 | 0 | 0 | 0.16667 | 11 | 458.895 | 0.23797
|  | 0.039493 | 0 | 0.039493 | 0 | 0 | 10.6667 | 448.2779 | #DIV/0!
|  | 0.039096 | 0.039096 | 0 | 0 | 0 | 12.6667 | 473.2013 | #DIV/0!
|  | 0.039096 | 0.039096 | 0 | 0 | 0 | 13.3333 | 498.1067 | #DIV/0!
|  | 0.039096 | 0.039096 | 0 | 0 | 0 | 14.8333 | 554.1437 | #DIV/0!
|  | 0.039052 | 0.019894 | 0 | 0.019158 | 0.33333 | 17.6667 | 609.5 | 0.11716
|  | 0.03902 | 0.022297 | 0 | 0.016723 | 0.83333 | 6.6667 | 348 | 0.046824
|  | 0.03902 | 0.03902 | 0 | 0 | 0.16667 | 11 | 231 | 0.23412
|  | 0.03894 | 0 | 0 | 0.03894 | 0 | 9.3333 | 415.0558 | #DIV/0!
|  | 0.038697 | 0.038697 | 0 | 0 | 0 | 12.5 | 466.975 | #DIV/0!
|  | 0.038653 | 0 | 0.0049366 | 0.033717 | 0 | 12.5 | 551.8046 | #DIV/0!
|  | 0.038603 | 0.038603 | 0 | 0 | 0.33333 | 11.6667 | 495 | 0.11581
|  | 0.038571 | 0.019286 | 0 | 0.019286 | 1.1667 | 9.3333 | 344 | 0.033061
|  | 0.038466 | 0 | 0 | 0.038466 | 0 | 11.3333 | 503.9963 | #DIV/0!
|  | 0.038458 | 0.038458 | 0 | 0 | 0.33333 | 8.5 | 372.893 | 0.11537
|  | 0.038347 | 0.038347 | 0 | 0 | 0.16667 | 10.1667 | 213.5 | 0.23008
|  | 0.038251 | 0.019126 | 0 | 0.019126 | 1.3333 | 21.3333 | 530.6667 | 0.028688
|  | 0.038147 | 0 | 0.038147 | 0 | 0 | 12.3333 | 518.3214 | #DIV/0!
|  | 0.038059 | 0 | 0.022553 | 0.015505 | 0.33333 | 6 | 396 | 0.11418
|  | 0.037991 | 0 | 0 | 0.037991 | 0 | 7.6667 | 340.9387 | #DIV/0!
|  | 0.037991 | 0 | 0 | 0.037991 | 0 | 10 | 444.7026 | #DIV/0!
|  | 0.037899 | 0.037899 | 0 | 0 | 0 | 14.6667 | 547.9173 | #DIV/0!
|  | 0.037899 | 0.037899 | 0 | 0 | 0 | 12.8333 | 479.4277 | #DIV/0!
|  | 0.037698 | 0 | 0.037698 | 0 | 0 | 11.6667 | 490.304 | #DIV/0!
|  | 0.037698 | 0 | 0.037698 | 0 | 0 | 12.5 | 525.3257 | #DIV/0!
|  | 0.0375 | 0.0375 | 0 | 0 | 0 | 12 | 448.296 | #DIV/0!
|  | 0.037433 | 0.037433 | 0 | 0 | 0.16667 | 11 | 374.5597 | 0.2246
|  | 0.037249 | 0 | 0.037249 | 0 | 0 | 13.6667 | 574.3561 | #DIV/0!
|  | 0.03711 | 0.03711 | 0 | 0 | 0.16667 | 12.5 | 472.0697 | 0.22266
|  | 0.037101 | 0.037101 | 0 | 0 | 0 | 12.8333 | 479.4277 | #DIV/0!
|  | 0.037098 | 0.018549 | 0 | 0.018549 | 0.83333 | 13.3333 | 514.6667 | 0.044517
|  | 0.037002 | 0 | 0.037002 | 0 | 0.16667 | 10.1667 | 457.5 | 0.22201
|  | 0.037002 | 0.037002 | 0 | 0 | 0.16667 | 20 | 420 | 0.22201
|  | 0.036841 | 0.018421 | 0 | 0.018421 | 0.16667 | 24 | 552 | 0.22105
|  | 0.0368 | 0 | 0.0368 | 0 | 0 | 10.8333 | 455.2823 | #DIV/0!
|  | 0.0368 | 0 | 0.0368 | 0 | 0 | 7.3333 | 308.1911 | #DIV/0!
|  | 0.036702 | 0.036702 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.036702 | 0.036702 | 0 | 0 | 0 | 13.8333 | 516.7857 | #DIV/0!
|  | 0.036664 | 0.036664 | 0 | 0 | 0.16667 | 19.6667 | 527.506 | 0.21998
|  | 0.036649 | 0 | 0.017075 | 0.019574 | 0.16667 | 11.6667 | 455 | 0.2199
|  | 0.036566 | 0 | 0 | 0.036566 | 0 | 11.3333 | 503.9963 | #DIV/0!
|  | 0.036566 | 0 | 0 | 0.036566 | 0 | 9.3333 | 415.0558 | #DIV/0!
|  | 0.036566 | 0 | 0 | 0.036566 | 0 | 11.6667 | 518.8197 | #DIV/0!
|  | 0.036515 | 0.00026697 | 0.014683 | 0.021565 | 0.16667 | 17.3333 | 436.5784 | 0.21909
|  | 0.036397 | 0.012975 | 0 | 0.023422 | 0.16667 | 8.5 | 381.1757 | 0.21838
|  | 0.036351 | 0 | 0.036351 | 0 | 0 | 9.6667 | 406.2519 | #DIV/0!
|  | 0.036308 | 0.036308 | 0 | 0 | 0.16667 | 0.16667 | 5.6667 | 0.21785
|  | 0.03619 | 0.03619 | 0 | 0 | 1 | 11.8333 | 471.9463 | 0.03619
|  | 0.036018 | 0 | 0.0094244 | 0.026593 | 0 | 9.6667 | 423.7687 | #DIV/0!
|  | 0.035912 | 0.015121 | 0.0056704 | 0.015121 | 0.83333 | 9.1667 | 324.5 | 0.043095
|  | 0.035859 | 0 | 0.017684 | 0.018175 | 0.16667 | 17.3333 | 398.6667 | 0.21515
|  | 0.03556 | 0.004485 | 0.02659 | 0.004485 | 0.33333 | 11.1667 | 487.5 | 0.10668
|  | 0.035539 | 0.017769 | 0 | 0.017769 | 0.66667 | 14.6667 | 554.6667 | 0.053308
|  | 0.035505 | 0.035505 | 0 | 0 | 0 | 12.5 | 466.975 | #DIV/0!
|  | 0.035505 | 0.035505 | 0 | 0 | 0 | 11.3333 | 423.3907 | #DIV/0!
|  | 0.035505 | 0.035505 | 0 | 0 | 0 | 11.3333 | 423.3907 | #DIV/0!
|  | 0.035453 | 0.035453 | 0 | 0 | 2.5 | 10 | 442.6667 | 0.014181
|  | 0.035357 | 0.035357 | 0 | 0 | 0.16667 | 8.8333 | 379.8333 | 0.21214
|  | 0.03524 | 0.03524 | 0 | 0 | 1.6667 | 18.3333 | 504.1667 | 0.021144
|  | 0.035141 | 0 | 0 | 0.035141 | 0 | 9.1667 | 407.6441 | #DIV/0!
|  | 0.035141 | 0 | 0 | 0.035141 | 0 | 11.3333 | 503.9963 | #DIV/0!
|  | 0.035141 | 0 | 0 | 0.035141 | 0 | 10.6667 | 474.3495 | #DIV/0!
|  | 0.035141 | 0 | 0 | 0.035141 | 0 | 10.6667 | 474.3495 | #DIV/0!
|  | 0.035106 | 0.035106 | 0 | 0 | 0 | 14.5 | 541.691 | #DIV/0!
|  | 0.034983 | 0.034983 | 0 | 0 | 0.16667 | 21.5 | 451.5 | 0.2099
|  | 0.034934 | 0.034934 | 0 | 0 | 0.16667 | 21.3333 | 450.7263 | 0.2096
|  | 0.034667 | 0 | 0 | 0.034667 | 0 | 8 | 355.7621 | #DIV/0!
|  | 0.034556 | 0 | 0.034556 | 0 | 0 | 10.1667 | 427.2649 | #DIV/0!
|  | 0.034556 | 0 | 0.034556 | 0 | 0 | 10.6667 | 448.2779 | #DIV/0!
|  | 0.034417 | 0.034417 | 0 | 0 | 1.1667 | 12.8333 | 537.1667 | 0.029501
|  | 0.034385 | 0.034385 | 0 | 0 | 0.33333 | 7 | 322 | 0.10316
|  | 0.034308 | 0.034308 | 0 | 0 | 0 | 10.8333 | 404.7117 | #DIV/0!
|  | 0.034192 | 0 | 0 | 0.034192 | 0 | 10.1667 | 452.1143 | #DIV/0!
|  | 0.034139 | 0 | 0.00089757 | 0.033242 | 0 | 11 | 488.7655 | #DIV/0!
|  | 0.03383 | 0.016915 | 0 | 0.016915 | 0.16667 | 11 | 528 | 0.20298
|  | 0.033813 | 0.033813 | 0 | 0 | 0.16667 | 19.8333 | 419.2263 | 0.20288
|  | 0.033717 | 0 | 0 | 0.033717 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.033691 | 0 | 0.00044878 | 0.033242 | 0 | 8 | 355.3547 | #DIV/0!
|  | 0.033659 | 0 | 0.033659 | 0 | 0 | 11 | 462.2866 | #DIV/0!
|  | 0.03351 | 0.03351 | 0 | 0 | 0 | 10 | 373.58 | #DIV/0!
|  | 0.03351 | 0.03351 | 0 | 0 | 0 | 11.5 | 429.617 | #DIV/0!
|  | 0.03351 | 0.03351 | 0 | 0 | 0 | 12.5 | 466.975 | #DIV/0!
|  | 0.033242 | 0 | 0 | 0.033242 | 0 | 9.8333 | 437.2909 | #DIV/0!
|  | 0.033242 | 0 | 0 | 0.033242 | 0 | 8.8333 | 392.8206 | #DIV/0!
|  | 0.033189 | 0.033189 | 0 | 0 | 0.16667 | 11.8333 | 437.8333 | 0.19914
|  | 0.033157 | 0.033157 | 0 | 0 | 0.16667 | 9.1667 | 412.5 | 0.19894
|  | 0.03305 | 0.016146 | 0 | 0.016904 | 0.16667 | 21.3333 | 388.4117 | 0.1983
|  | 0.033024 | 0.00041647 | 0.00089757 | 0.03171 | 0.16667 | 9 | 352.4161 | 0.19814
|  | 0.033016 | 0.033016 | 0 | 0 | 0.16667 | 11 | 457.9547 | 0.19809
|  | 0.032713 | 0.032713 | 0 | 0 | 0 | 11.8333 | 442.0697 | #DIV/0!
|  | 0.032713 | 0.032713 | 0 | 0 | 0 | 12.8333 | 479.4277 | #DIV/0!
|  | 0.032677 | 0.032677 | 0 | 0 | 0.16667 | 7.6667 | 260.6667 | 0.19606
|  | 0.032613 | 0.032613 | 0 | 0 | 0.5 | 11.1667 | 382.5 | 0.065225
|  | 0.032602 | 0.032602 | 0 | 0 | 0.16667 | 10.6667 | 458.6667 | 0.19561
|  | 0.032429 | 0.032429 | 0 | 0 | 0.16667 | 17.6667 | 338.7263 | 0.19457
|  | 0.032399 | 0.032399 | 0 | 0 | 0.16667 | 9.5 | 351.5 | 0.19439
|  | 0.032314 | 0.032314 | 0 | 0 | 0 | 12 | 448.296 | #DIV/0!
|  | 0.032292 | 0 | 0 | 0.032292 | 0 | 6.6667 | 296.4684 | #DIV/0!
|  | 0.03216 | 0.03216 | 0 | 0 | 0.16667 | 13.5 | 470.796 | 0.19296
|  | 0.032068 | 0.032068 | 0 | 0 | 0.16667 | 17.5 | 367.5 | 0.19241
|  | 0.032036 | 0.032036 | 0 | 0 | 1 | 16 | 400 | 0.032036
|  | 0.031915 | 0.031915 | 0 | 0 | 0 | 10.5 | 392.259 | #DIV/0!
|  | 0.031848 | 0.031848 | 0 | 0 | 0.16667 | 12.1667 | 378.2263 | 0.19109
|  | 0.031822 | 0.015911 | 0 | 0.015911 | 0.66667 | 6.6667 | 248.3333 | 0.047734
|  | 0.031817 | 0 | 0 | 0.031817 | 0 | 10.5 | 466.9377 | #DIV/0!
|  | 0.031817 | 0 | 0 | 0.031817 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.031716 | 0.031716 | 0 | 0 | 0.16667 | 8.1667 | 367.5 | 0.19029
|  | 0.031415 | 0 | 0.031415 | 0 | 0 | 8.5 | 357.2215 | #DIV/0!
|  | 0.031246 | 0.031246 | 0 | 0 | 0.16667 | 10.8333 | 411.6667 | 0.18747
|  | 0.031235 | 0.031235 | 0 | 0 | 0.16667 | 8 | 360 | 0.18741
|  | 0.031182 | 0.031182 | 0 | 0 | 0.66667 | 10.6667 | 389.3333 | 0.046773
|  | 0.031117 | 0.031117 | 0 | 0 | 0 | 11.1667 | 417.1643 | #DIV/0!
|  | 0.031117 | 0.031117 | 0 | 0 | 0 | 8.8333 | 329.9957 | #DIV/0!
|  | 0.031011 | 0 | 0.031011 | 0 | 0.33333 | 4.3333 | 286 | 0.093033
|  | 0.030966 | 0 | 0.030966 | 0 | 0 | 11.1667 | 469.291 | #DIV/0!
|  | 0.030867 | 0 | 0 | 0.030867 | 0 | 10.3333 | 459.526 | #DIV/0!
|  | 0.030867 | 0 | 0 | 0.030867 | 0 | 8.8333 | 392.8206 | #DIV/0!
|  | 0.030867 | 0 | 0 | 0.030867 | 0 | 8 | 355.7621 | #DIV/0!
|  | 0.030867 | 0 | 0 | 0.030867 | 0 | 8.3333 | 370.5855 | #DIV/0!
|  | 0.030718 | 0.030718 | 0 | 0 | 0 | 11.6667 | 435.8433 | #DIV/0!
|  | 0.030517 | 0 | 0.030517 | 0 | 0 | 11.1667 | 469.291 | #DIV/0!
|  | 0.030507 | 0 | 0.014361 | 0.016146 | 0 | 6.5 | 281.3167 | #DIV/0!
|  | 0.030393 | 0 | 0 | 0.030393 | 0 | 8.6667 | 385.4089 | #DIV/0!
|  | 0.030393 | 0 | 0 | 0.030393 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.030393 | 0 | 0 | 0.030393 | 0 | 7.6667 | 340.9387 | #DIV/0!
|  | 0.030366 | 0 | 0.00044878 | 0.029918 | 0 | 7.5 | 333.1196 | #DIV/0!
|  | 0.030319 | 0.030319 | 0 | 0 | 0 | 11.1667 | 417.1643 | #DIV/0!
|  | 0.030274 | 0.015377 | 0 | 0.014897 | 0.16667 | 10.1667 | 457.5 | 0.18164
|  | 0.030068 | 0 | 0.030068 | 0 | 0 | 9.5 | 399.2475 | #DIV/0!
|  | 0.030068 | 0 | 0.030068 | 0 | 0 | 9.6667 | 406.2519 | #DIV/0!
|  | 0.03005 | 0.03005 | 0 | 0 | 0.16667 | 17.1667 | 360.5 | 0.1803
|  | 0.029719 | 0.029719 | 0 | 0 | 0.16667 | 3.3333 | 76.6667 | 0.17831
|  | 0.029601 | 0.029601 | 0 | 0 | 0.16667 | 15.3333 | 322 | 0.17761
|  | 0.029557 | 0 | 0.014361 | 0.015196 | 0 | 6.6667 | 288.3211 | #DIV/0!
|  | 0.029521 | 0.029521 | 0 | 0 | 0 | 10 | 373.58 | #DIV/0!
|  | 0.029521 | 0.029521 | 0 | 0 | 0 | 11.6667 | 435.8433 | #DIV/0!
|  | 0.029443 | 0 | 0 | 0.029443 | 0 | 8.1667 | 363.1738 | #DIV/0!
|  | 0.029234 | 0 | 0.0035903 | 0.025644 | 0 | 8.3333 | 367.3266 | #DIV/0!
|  | 0.029217 | 0.029217 | 0 | 0 | 0.16667 | 19.3333 | 367.3333 | 0.1753
|  | 0.029171 | 0 | 0.029171 | 0 | 0 | 10.1667 | 427.2649 | #DIV/0!
|  | 0.029171 | 0 | 0.029171 | 0 | 0 | 9.1667 | 385.2388 | #DIV/0!
|  | 0.029171 | 0 | 0.029171 | 0 | 0 | 9 | 378.2345 | #DIV/0!
|  | 0.029131 | 0.029131 | 0 | 0 | 0.16667 | 5.8333 | 256.6667 | 0.17479
|  | 0.028968 | 0 | 0 | 0.028968 | 0 | 9.6667 | 429.8792 | #DIV/0!
|  | 0.028968 | 0 | 0 | 0.028968 | 0 | 9.1667 | 407.6441 | #DIV/0!
|  | 0.028968 | 0 | 0 | 0.028968 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.028929 | 0.028929 | 0 | 0 | 0.16667 | 18.1667 | 381.5 | 0.17357
|  | 0.028875 | 0 | 0 | 0.028875 | 0.33333 | 5.6667 | 294.6667 | 0.086625
|  | 0.028723 | 0.028723 | 0 | 0 | 0 | 10.1667 | 379.8063 | #DIV/0!
|  | 0.028722 | 0 | 0.028722 | 0 | 0 | 10.5 | 441.2736 | #DIV/0!
|  | 0.028722 | 0 | 0.028722 | 0 | 0 | 9.1667 | 385.2388 | #DIV/0!
|  | 0.028701 | 0.028701 | 0 | 0 | 0.16667 | 7 | 380.3127 | 0.1722
|  | 0.028655 | 0.028655 | 0 | 0 | 0.16667 | 15.8333 | 335.2263 | 0.17193
|  | 0.028493 | 0 | 0 | 0.028493 | 0 | 6.3333 | 281.645 | #DIV/0!
|  | 0.028192 | 0 | 0.014096 | 0.014096 | 0.33333 | 5.3333 | 352 | 0.084575
|  | 0.028128 | 0.0093759 | 0.0093759 | 0.0093759 | 1.6667 | 5 | 219.5 | 0.016877
|  | 0.028069 | 0.013797 | 0 | 0.014272 | 0.33333 | 20.1667 | 387.4117 | 0.084206
|  | 0.028018 | 0 | 0 | 0.028018 | 0 | 8.1667 | 363.1738 | #DIV/0!
|  | 0.028018 | 0 | 0 | 0.028018 | 0 | 7 | 311.2918 | #DIV/0!
|  | 0.028018 | 0 | 0 | 0.028018 | 0 | 8.8333 | 392.8206 | #DIV/0!
|  | 0.027925 | 0.027925 | 0 | 0 | 0 | 9.3333 | 348.6747 | #DIV/0!
|  | 0.027925 | 0.027925 | 0 | 0 | 0 | 8.5 | 317.543 | #DIV/0!
|  | 0.027871 | 0.027871 | 0 | 0 | 0.16667 | 9.1667 | 412.5 | 0.16723
|  | 0.027807 | 0.027807 | 0 | 0 | 0.16667 | 15 | 315 | 0.16684
|  | 0.0277 | 0.0277 | 0 | 0 | 1.1667 | 13.6667 | 369.6667 | 0.023743
|  | 0.027551 | 0.027551 | 0 | 0 | 0.16667 | 9.6667 | 415.6667 | 0.16531
|  | 0.027551 | 0 | 0.017449 | 0.010102 | 0.33333 | 9.3333 | 401.3333 | 0.082653
|  | 0.027543 | 0 | 0 | 0.027543 | 0 | 8.1667 | 363.1738 | #DIV/0!
|  | 0.027526 | 0.027526 | 0 | 0 | 0 | 10.5 | 392.259 | #DIV/0!
|  | 0.027526 | 0.027526 | 0 | 0 | 0 | 10.8333 | 404.7117 | #DIV/0!
|  | 0.027491 | 0.027491 | 0 | 0 | 0.16667 | 6 | 257.0597 | 0.16494
|  | 0.027425 | 0.027425 | 0 | 0 | 0.16667 | 11.3333 | 396.1273 | 0.16455
|  | 0.027391 | 0.027391 | 0 | 0 | 0.16667 | 7 | 315 | 0.16434
|  | 0.027376 | 0 | 0.027376 | 0 | 0 | 9.5 | 399.2475 | #DIV/0!
|  | 0.027376 | 0 | 0.027376 | 0 | 0 | 9.3333 | 392.2432 | #DIV/0!
|  | 0.027376 | 0 | 0.027376 | 0 | 0 | 8 | 336.2084 | #DIV/0!
|  | 0.027197 | 0.027197 | 0 | 0 | 0.33333 | 8.5 | 318.4423 | 0.081592
|  | 0.027128 | 0.027128 | 0 | 0 | 0 | 7 | 261.506 | #DIV/0!
|  | 0.027128 | 0.027128 | 0 | 0 | 0 | 10.3333 | 386.0327 | #DIV/0!
|  | 0.027123 | 0.013316 | 0 | 0.013807 | 0.16667 | 6.8333 | 294.3234 | 0.16274
|  | 0.027068 | 0 | 0 | 0.027068 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.026927 | 0 | 0.026927 | 0 | 0 | 9 | 378.2345 | #DIV/0!
|  | 0.02686 | 0 | 0.0035903 | 0.023269 | 0 | 7.1667 | 316.6667 | #DIV/0!
|  | 0.026835 | 0.0012494 | 0.00089757 | 0.024688 | 0.16667 | 9 | 352.4161 | 0.16101
|  | 0.026782 | 0.0089274 | 0.0089274 | 0.0089274 | 0.16667 | 6 | 264 | 0.16069
|  | 0.026745 | 0 | 0.013359 | 0.013385 | 0.16667 | 9.3333 | 365.4161 | 0.16047
|  | 0.026593 | 0 | 0 | 0.026593 | 0 | 8.5 | 377.9972 | #DIV/0!
|  | 0.026593 | 0 | 0 | 0.026593 | 0 | 7 | 311.2918 | #DIV/0!
|  | 0.026526 | 0.013263 | 0 | 0.013263 | 0.33333 | 10 | 345 | 0.079578
|  | 0.02648 | 0.02648 | 0 | 0 | 0.83333 | 11.1667 | 413.286 | 0.031776
|  | 0.026478 | 0 | 0.026478 | 0 | 0 | 8 | 336.2084 | #DIV/0!
|  | 0.02633 | 0.02633 | 0 | 0 | 0 | 10.3333 | 386.0327 | #DIV/0!
|  | 0.026312 | 0.026312 | 0 | 0 | 0.33333 | 6.3333 | 277 | 0.078937
|  | 0.026227 | 0.013113 | 0 | 0.013113 | 1.3333 | 8 | 307 | 0.01967
|  | 0.026173 | 0.013316 | 0 | 0.012857 | 0.16667 | 7.5 | 322.5 | 0.15704
|  | 0.026141 | 0.013071 | 0 | 0.013071 | 0.16667 | 11.6667 | 396.6667 | 0.15685
|  | 0.026119 | 0 | 0 | 0.026119 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.026119 | 0 | 0 | 0.026119 | 0 | 7.8333 | 348.3504 | #DIV/0!
|  | 0.026119 | 0 | 0 | 0.026119 | 0 | 6.3333 | 281.645 | #DIV/0!
|  | 0.026119 | 0 | 0 | 0.026119 | 0 | 6.1667 | 274.2333 | #DIV/0!
|  | 0.026029 | 0 | 0.026029 | 0 | 0 | 8.5 | 357.2215 | #DIV/0!
|  | 0.026029 | 0 | 0.026029 | 0 | 0 | 9.1667 | 385.2388 | #DIV/0!
|  | 0.025931 | 0.025931 | 0 | 0 | 0 | 10 | 373.58 | #DIV/0!
|  | 0.025931 | 0.025931 | 0 | 0 | 0 | 8.6667 | 323.7693 | #DIV/0!
|  | 0.025931 | 0.025931 | 0 | 0 | 0 | 10 | 373.58 | #DIV/0!
|  | 0.025821 | 0 | 0.012911 | 0.012911 | 0.16667 | 8.6667 | 338 | 0.15493
|  | 0.025644 | 0 | 0 | 0.025644 | 0 | 9 | 400.2324 | #DIV/0!
|  | 0.025532 | 0.025532 | 0 | 0 | 0 | 9.1667 | 342.4483 | #DIV/0!
|  | 0.025532 | 0.025532 | 0 | 0 | 0 | 9.3333 | 348.6747 | #DIV/0!
|  | 0.025527 | 0.012526 | 0 | 0.013001 | 0.16667 | 15.5 | 360.0784 | 0.15316
|  | 0.025133 | 0.025133 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.025133 | 0.025133 | 0 | 0 | 0 | 10.1667 | 379.8063 | #DIV/0!
|  | 0.025132 | 0 | 0.025132 | 0 | 0 | 9.1667 | 385.2388 | #DIV/0!
|  | 0.025132 | 0 | 0.025132 | 0 | 0 | 7.3333 | 308.1911 | #DIV/0!
|  | 0.025132 | 0 | 0.025132 | 0 | 0 | 5.6667 | 238.1477 | #DIV/0!
|  | 0.025052 | 0.00049122 | 0 | 0.024561 | 0.16667 | 13.1667 | 302.8333 | 0.15031
|  | 0.024939 | 0 | 0.012117 | 0.012822 | 0 | 5.6667 | 245.0729 | #DIV/0!
|  | 0.024734 | 0.024734 | 0 | 0 | 0 | 7.1667 | 267.7323 | #DIV/0!
|  | 0.024694 | 0 | 0 | 0.024694 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.024694 | 0 | 0 | 0.024694 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.024694 | 0 | 0 | 0.024694 | 0 | 6.1667 | 274.2333 | #DIV/0!
|  | 0.024683 | 0 | 0.024683 | 0 | 0 | 6.1667 | 259.1607 | #DIV/0!
|  | 0.024561 | 0 | 0.01228 | 0.01228 | 0.16667 | 11 | 253 | 0.14737
|  | 0.024518 | 0 | 0.012259 | 0.012259 | 0.66667 | 9.3333 | 382.6667 | 0.036777
|  | 0.024335 | 0.024335 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.024335 | 0.024335 | 0 | 0 | 0 | 8.8333 | 329.9957 | #DIV/0!
|  | 0.024335 | 0.024335 | 0 | 0 | 0 | 7 | 261.506 | #DIV/0!
|  | 0.024315 | 0.024315 | 0 | 0 | 0.33333 | 6.6667 | 230 | 0.072946
|  | 0.024219 | 0 | 0 | 0.024219 | 0 | 6.3333 | 281.645 | #DIV/0!
|  | 0.024219 | 0 | 0 | 0.024219 | 0 | 6.6667 | 296.4684 | #DIV/0!
|  | 0.024219 | 0 | 0 | 0.024219 | 0 | 6 | 266.8216 | #DIV/0!
|  | 0.02407 | 0.02407 | 0 | 0 | 0.66667 | 9.3333 | 375.6667 | 0.036105
|  | 0.02407 | 0.012035 | 0 | 0.012035 | 0.16667 | 11.3333 | 260.6667 | 0.14442
|  | 0.023963 | 0 | 0.011981 | 0.011981 | 0.66667 | 6.6667 | 311.6667 | 0.035944
|  | 0.023936 | 0.023936 | 0 | 0 | 0 | 7.8333 | 292.6377 | #DIV/0!
|  | 0.02392 | 0 | 0.01196 | 0.01196 | 0.33333 | 5.3333 | 213.3333 | 0.071761
|  | 0.023785 | 0 | 0.023785 | 0 | 0 | 6.1667 | 259.1607 | #DIV/0!
|  | 0.023744 | 0 | 0 | 0.023744 | 0 | 5.1667 | 229.763 | #DIV/0!
|  | 0.023744 | 0 | 0 | 0.023744 | 0 | 6.5 | 289.0567 | #DIV/0!
|  | 0.023744 | 0 | 0 | 0.023744 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.023739 | 0.023739 | 0 | 0 | 0.16667 | 16.5 | 313.5 | 0.14243
|  | 0.023668 | 0.00039893 | 0 | 0.023269 | 0 | 8 | 354.5767 | #DIV/0!
|  | 0.023537 | 0.023537 | 0 | 0 | 0 | 9.3333 | 348.6747 | #DIV/0!
|  | 0.023537 | 0.023537 | 0 | 0 | 0 | 8.1667 | 305.0903 | #DIV/0!
|  | 0.023472 | 0.0067062 | 0.0067062 | 0.010059 | 1.1667 | 12.8333 | 287.8333 | 0.020119
|  | 0.023408 | 0.011704 | 0 | 0.011704 | 1.1667 | 7 | 274 | 0.020064
|  | 0.023322 | 0.011661 | 0 | 0.011661 | 0.16667 | 7.3333 | 286 | 0.13993
|  | 0.023269 | 0 | 0 | 0.023269 | 0 | 7.5 | 333.527 | #DIV/0!
|  | 0.023269 | 0 | 0 | 0.023269 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.023269 | 0 | 0 | 0.023269 | 0 | 5.3333 | 237.1747 | #DIV/0!
|  | 0.023269 | 0 | 0 | 0.023269 | 0 | 6 | 266.8216 | #DIV/0!
|  | 0.023138 | 0.023138 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.023138 | 0.023138 | 0 | 0 | 0 | 8.1667 | 305.0903 | #DIV/0!
|  | 0.023066 | 0.023066 | 0 | 0 | 0.16667 | 5.5 | 247.5 | 0.1384
|  | 0.022966 | 0 | 0.021542 | 0.0014247 | 0 | 7.6667 | 323.4219 | #DIV/0!
|  | 0.022936 | 0.022936 | 0 | 0 | 0.16667 | 9.3333 | 345.6317 | 0.13761
|  | 0.022888 | 0 | 0.022888 | 0 | 0 | 8.3333 | 350.2171 | #DIV/0!
|  | 0.022874 | 0.022874 | 0 | 0 | 0.16667 | 13.5 | 283.5 | 0.13724
|  | 0.022821 | 0.0024347 | 0.017951 | 0.0024347 | 0.16667 | 7.5 | 307.1433 | 0.13692
|  | 0.022794 | 0 | 0 | 0.022794 | 0 | 7.3333 | 326.1153 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 8.1667 | 305.0903 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 8.1667 | 305.0903 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.022739 | 0.022739 | 0 | 0 | 0 | 8.3333 | 311.3167 | #DIV/0!
|  | 0.022687 | 0 | 0.011106 | 0.011581 | 0.33333 | 7.5 | 300.745 | 0.06806
|  | 0.022639 | 0.011319 | 0 | 0.011319 | 1.1667 | 9 | 353.3333 | 0.019405
|  | 0.022591 | 0 | 0.011668 | 0.010922 | 0 | 8.1667 | 352.5822 | #DIV/0!
|  | 0.022513 | 0.0019649 | 0.015259 | 0.0052891 | 0.16667 | 9 | 330.3499 | 0.13508
|  | 0.022439 | 0 | 0.022439 | 0 | 0 | 7.8333 | 329.2041 | #DIV/0!
|  | 0.02234 | 0.02234 | 0 | 0 | 0 | 8.5 | 317.543 | #DIV/0!
|  | 0.02234 | 0.02234 | 0 | 0 | 0 | 8.5 | 317.543 | #DIV/0!
|  | 0.02234 | 0.02234 | 0 | 0 | 0 | 7.3333 | 273.9587 | #DIV/0!
|  | 0.02234 | 0.02234 | 0 | 0 | 0 | 8.1667 | 305.0903 | #DIV/0!
|  | 0.02232 | 0 | 0 | 0.02232 | 0 | 6.5 | 289.0567 | #DIV/0!
|  | 0.022173 | 0.0081692 | 0.0058342 | 0.0081692 | 0.16667 | 7.6667 | 339.0521 | 0.13304
|  | 0.022105 | 0.022105 | 0 | 0 | 0.16667 | 6.6667 | 300 | 0.13263
|  | 0.02199 | 0 | 0.02199 | 0 | 0 | 4.8333 | 203.1259 | #DIV/0!
|  | 0.021941 | 0.021941 | 0 | 0 | 0 | 7.1667 | 267.7323 | #DIV/0!
|  | 0.021941 | 0.021941 | 0 | 0 | 0 | 8.5 | 317.543 | #DIV/0!
|  | 0.021849 | 0.0072829 | 0.0072829 | 0.0072829 | 1.5 | 9 | 341 | 0.014566
|  | 0.021845 | 0 | 0 | 0.021845 | 0 | 6.1667 | 274.2333 | #DIV/0!
|  | 0.021656 | 0.0072188 | 0.0072188 | 0.0072188 | 1.3333 | 8 | 338 | 0.016242
|  | 0.021656 | 0.021656 | 0 | 0 | 1.1667 | 3.5 | 169 | 0.018563
|  | 0.021542 | 0.021542 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.021542 | 0.021542 | 0 | 0 | 0 | 8 | 298.864 | #DIV/0!
|  | 0.021528 | 0 | 0.010764 | 0.010764 | 1.3333 | 8 | 336 | 0.016146
|  | 0.021486 | 0.021486 | 0 | 0 | 1 | 9 | 335.3333 | 0.021486
|  | 0.02137 | 0 | 0 | 0.02137 | 0 | 6.6667 | 296.4684 | #DIV/0!
|  | 0.02137 | 0 | 0 | 0.02137 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.02137 | 0 | 0 | 0.02137 | 0 | 6.5 | 289.0567 | #DIV/0!
|  | 0.02137 | 0 | 0 | 0.02137 | 0 | 5.3333 | 237.1747 | #DIV/0!
|  | 0.021344 | 0 | 0.00044878 | 0.020895 | 0 | 6.6667 | 296.061 | #DIV/0!
|  | 0.021254 | 0.021254 | 0 | 0 | 0.16667 | 8.5 | 264.5597 | 0.12753
|  | 0.021244 | 0 | 0.010322 | 0.010922 | 0 | 6.8333 | 294.918 | #DIV/0!
|  | 0.021144 | 0.021144 | 0 | 0 | 0 | 6.3333 | 236.6007 | #DIV/0!
|  | 0.021144 | 0.021144 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.021122 | 0.010561 | 0 | 0.010561 | 0.16667 | 10 | 230 | 0.12673
|  | 0.021122 | 0.010561 | 0 | 0.010561 | 0.16667 | 14 | 322 | 0.12673
|  | 0.021016 | 0 | 0.010508 | 0.010508 | 0.66667 | 8 | 328 | 0.031523
|  | 0.020895 | 0 | 0 | 0.020895 | 0 | 6.8333 | 303.8801 | #DIV/0!
|  | 0.020895 | 0 | 0 | 0.020895 | 0 | 7.1667 | 318.7035 | #DIV/0!
|  | 0.020895 | 0 | 0 | 0.020895 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.020767 | 0.020767 | 0 | 0 | 0.16667 | 6.3333 | 215.893 | 0.1246
|  | 0.020745 | 0.020745 | 0 | 0 | 0 | 8.6667 | 323.7693 | #DIV/0!
|  | 0.020663 | 0.020663 | 0 | 0 | 0.16667 | 7.1667 | 322.5 | 0.12398
|  | 0.020663 | 0.020663 | 0 | 0 | 0.16667 | 6.3333 | 285 | 0.12398
|  | 0.020644 | 0 | 0.020644 | 0 | 0 | 6.1667 | 259.1607 | #DIV/0!
|  | 0.020394 | 0 | 0.00044878 | 0.019945 | 0 | 6.1667 | 273.8259 | #DIV/0!
|  | 0.020346 | 0.020346 | 0 | 0 | 0 | 5.3333 | 199.2427 | #DIV/0!
|  | 0.020346 | 0.020346 | 0 | 0 | 0 | 7 | 261.506 | #DIV/0!
|  | 0.020283 | 0.020283 | 0 | 0 | 0.16667 | 10.8333 | 208.893 | 0.1217
|  | 0.020254 | 0.0056811 | 0.0022439 | 0.012329 | 0.16667 | 7.1667 | 290.7857 | 0.12153
|  | 0.020195 | 0 | 0.020195 | 0 | 0 | 7.1667 | 301.1867 | #DIV/0!
|  | 0.020195 | 0 | 0.020195 | 0 | 0 | 7.3333 | 308.1911 | #DIV/0!
|  | 0.020145 | 0 | 0.01006 | 0.010086 | 0.16667 | 6 | 269.4161 | 0.12087
|  | 0.019947 | 0.019947 | 0 | 0 | 0 | 6.1667 | 230.3743 | #DIV/0!
|  | 0.019734 | 0.019734 | 0 | 0 | 0.33333 | 4.6667 | 205.3333 | 0.059203
|  | 0.019548 | 0.019548 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.019548 | 0.019548 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.01947 | 0 | 0 | 0.01947 | 0 | 6.1667 | 274.2333 | #DIV/0!
|  | 0.01947 | 0 | 0 | 0.01947 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.019403 | 0 | 0 | 0.019403 | 0.16667 | 10.8333 | 249.1667 | 0.11642
|  | 0.019307 | 0.019307 | 0 | 0 | 1 | 8 | 301.3333 | 0.019307
|  | 0.019298 | 0 | 0.019298 | 0 | 0 | 6.8333 | 287.178 | #DIV/0!
|  | 0.019298 | 0 | 0.019298 | 0 | 0 | 4.6667 | 196.1216 | #DIV/0!
|  | 0.019222 | 0.019222 | 0 | 0 | 0.16667 | 6.1667 | 277.5 | 0.11533
|  | 0.019222 | 0.019222 | 0 | 0 | 1.1667 | 10.5 | 270 | 0.016476
|  | 0.019222 | 0.019222 | 0 | 0 | 1 | 12 | 300 | 0.019222
|  | 0.019158 | 0.019158 | 0 | 0 | 0.16667 | 10.6667 | 245.3333 | 0.11495
|  | 0.019149 | 0.019149 | 0 | 0 | 0 | 5.5 | 205.469 | #DIV/0!
|  | 0.019149 | 0.019149 | 0 | 0 | 0 | 7.3333 | 273.9587 | #DIV/0!
|  | 0.019149 | 0.019149 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.018995 | 0 | 0 | 0.018995 | 0 | 5.8333 | 259.4099 | #DIV/0!
|  | 0.018995 | 0 | 0 | 0.018995 | 0 | 5.5 | 244.5864 | #DIV/0!
|  | 0.018969 | 0 | 0.00044878 | 0.01852 | 0 | 6.5 | 288.6493 | #DIV/0!
|  | 0.018849 | 0 | 0.018849 | 0 | 0 | 6.6667 | 280.1737 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 7.1667 | 267.7323 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 5.1667 | 193.0163 | #DIV/0!
|  | 0.01875 | 0.01875 | 0 | 0 | 0 | 7 | 261.506 | #DIV/0!
|  | 0.018666 | 0.0093332 | 0 | 0.0093332 | 0.16667 | 5.6667 | 215.3333 | 0.112
|  | 0.018666 | 0.0093332 | 0 | 0.0093332 | 0.33333 | 14 | 266 | 0.055999
|  | 0.01852 | 0 | 0 | 0.01852 | 0 | 4.8333 | 214.9396 | #DIV/0!
|  | 0.0184 | 0 | 0.0184 | 0 | 0 | 5.5 | 231.1433 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 6.1667 | 230.3743 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 5.6667 | 211.6953 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 4.1667 | 155.6583 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.018351 | 0.018351 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.018325 | 0.0012494 | 0 | 0.017075 | 0.16667 | 6 | 234 | 0.10995
|  | 0.018261 | 0.018261 | 0 | 0 | 0.16667 | 4.3333 | 195 | 0.10956
|  | 0.018201 | 0.0088633 | 0 | 0.0093382 | 0.33333 | 6.8333 | 192.4117 | 0.054604
|  | 0.018154 | 0.018154 | 0 | 0 | 1 | 10 | 283.3333 | 0.018154
|  | 0.018051 | 0.018051 | 0 | 0 | 0.16667 | 9.3333 | 180.393 | 0.1083
|  | 0.018046 | 0 | 0 | 0.018046 | 0 | 6.1667 | 274.2333 | #DIV/0!
|  | 0.018046 | 0 | 0 | 0.018046 | 0 | 5.5 | 244.5864 | #DIV/0!
|  | 0.018046 | 0 | 0 | 0.018046 | 0 | 4.8333 | 214.9396 | #DIV/0!
|  | 0.017952 | 0.017952 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.017952 | 0.017952 | 0 | 0 | 0 | 6.5 | 242.827 | #DIV/0!
|  | 0.017951 | 0 | 0.017951 | 0 | 0 | 6.3333 | 266.165 | #DIV/0!
|  | 0.017951 | 0 | 0.017951 | 0 | 0 | 6.5 | 273.1694 | #DIV/0!
|  | 0.017908 | 0 | 0.0087458 | 0.0091623 | 0.16667 | 4.8333 | 188.5 | 0.10745
|  | 0.01778 | 0.01778 | 0 | 0 | 0.16667 | 5.6667 | 255 | 0.10668
|  | 0.01778 | 0.01778 | 0 | 0 | 0.16667 | 4.8333 | 217.5 | 0.10668
|  | 0.017769 | 0.017769 | 0 | 0 | 0.66667 | 7.5 | 248.6667 | 0.026654
|  | 0.017652 | 0.017652 | 0 | 0 | 0.16667 | 10.1667 | 193.1667 | 0.10591
|  | 0.017605 | 0.0055743 | 0 | 0.01203 | 0.16667 | 10.5 | 241.9405 | 0.10563
|  | 0.017571 | 0 | 0 | 0.017571 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.017571 | 0 | 0 | 0.017571 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.017571 | 0 | 0 | 0.017571 | 0 | 5.8333 | 259.4099 | #DIV/0!
|  | 0.017571 | 0 | 0 | 0.017571 | 0 | 5.8333 | 259.4099 | #DIV/0!
|  | 0.017553 | 0.017553 | 0 | 0 | 0 | 7.1667 | 267.7323 | #DIV/0!
|  | 0.017503 | 0 | 0.017503 | 0 | 0 | 5.8333 | 245.152 | #DIV/0!
|  | 0.017503 | 0 | 0.017503 | 0 | 0 | 4.6667 | 196.1216 | #DIV/0!
|  | 0.017492 | 0 | 0.0087458 | 0.0087458 | 0.16667 | 6.3333 | 247 | 0.10495
|  | 0.017353 | 0.017353 | 0 | 0 | 0.5 | 4 | 166.6667 | 0.034706
|  | 0.017193 | 0.017193 | 0 | 0 | 0.66667 | 6.6667 | 268.3333 | 0.025789
|  | 0.017182 | 0.017182 | 0 | 0 | 0.16667 | 6.8333 | 255.7077 | 0.10309
|  | 0.017154 | 0.017154 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.017154 | 0.017154 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.017154 | 0.017154 | 0 | 0 | 0 | 5 | 186.79 | #DIV/0!
|  | 0.017096 | 0 | 0 | 0.017096 | 0 | 5.6667 | 251.9981 | #DIV/0!
|  | 0.017096 | 0 | 0 | 0.017096 | 0 | 5.8333 | 259.4099 | #DIV/0!
|  | 0.017096 | 0 | 0 | 0.017096 | 0 | 4.8333 | 214.9396 | #DIV/0!
|  | 0.016819 | 0.016819 | 0 | 0 | 0.83333 | 5.8333 | 204.1667 | 0.020183
|  | 0.016755 | 0.016755 | 0 | 0 | 0 | 6.8333 | 255.2797 | #DIV/0!
|  | 0.016755 | 0.016755 | 0 | 0 | 0 | 6.6667 | 249.0533 | #DIV/0!
|  | 0.016755 | 0.016755 | 0 | 0 | 0 | 5 | 186.79 | #DIV/0!
|  | 0.016755 | 0.016755 | 0 | 0 | 0 | 5.1667 | 193.0163 | #DIV/0!
|  | 0.016755 | 0.016755 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.016737 | 0.016737 | 0 | 0 | 0.16667 | 4.3333 | 193.7263 | 0.10042
|  | 0.016659 | 0 | 0.0083294 | 0.0083294 | 0.16667 | 6 | 234 | 0.099952
|  | 0.016621 | 0 | 0 | 0.016621 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.016621 | 0 | 0 | 0.016621 | 0 | 4.8333 | 214.9396 | #DIV/0!
|  | 0.016605 | 0 | 0.016605 | 0 | 0 | 6 | 252.1563 | #DIV/0!
|  | 0.016605 | 0 | 0.016605 | 0 | 0 | 5.8333 | 245.152 | #DIV/0!
|  | 0.016605 | 0 | 0.016605 | 0 | 0 | 6.1667 | 259.1607 | #DIV/0!
|  | 0.016605 | 0 | 0.016605 | 0 | 0 | 5.6667 | 238.1477 | #DIV/0!
|  | 0.016573 | 0.016573 | 0 | 0 | 0.83333 | 4.6667 | 150.6667 | 0.019888
|  | 0.016552 | 0 | 0.016552 | 0 | 0.16667 | 8.6667 | 216.6667 | 0.099312
|  | 0.016356 | 0.016356 | 0 | 0 | 0 | 5.5 | 205.469 | #DIV/0!
|  | 0.016257 | 0.016257 | 0 | 0 | 0.16667 | 5 | 223.7263 | 0.097541
|  | 0.016146 | 0 | 0 | 0.016146 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.016146 | 0 | 0 | 0.016146 | 0 | 4.8333 | 214.9396 | #DIV/0!
|  | 0.016018 | 0.016018 | 0 | 0 | 0.66667 | 10 | 250 | 0.024027
|  | 0.015957 | 0.015957 | 0 | 0 | 0 | 6.3333 | 236.6007 | #DIV/0!
|  | 0.015957 | 0.015957 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.015707 | 0 | 0.015707 | 0 | 0 | 4.8333 | 203.1259 | #DIV/0!
|  | 0.015707 | 0 | 0.015707 | 0 | 0 | 3.6667 | 154.0955 | #DIV/0!
|  | 0.015671 | 0 | 0 | 0.015671 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.015671 | 0 | 0 | 0.015671 | 0 | 4.6667 | 207.5279 | #DIV/0!
|  | 0.015671 | 0 | 0 | 0.015671 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.015623 | 0.015623 | 0 | 0 | 0.16667 | 5.8333 | 110.8333 | 0.093737
|  | 0.015609 | 0.015609 | 0 | 0 | 0.16667 | 7.3333 | 142.393 | 0.093655
|  | 0.015558 | 0.015558 | 0 | 0 | 0 | 5.5 | 205.469 | #DIV/0!
|  | 0.015558 | 0.015558 | 0 | 0 | 0 | 6.3333 | 236.6007 | #DIV/0!
|  | 0.015558 | 0.015558 | 0 | 0 | 0 | 6.1667 | 230.3743 | #DIV/0!
|  | 0.015558 | 0.015558 | 0 | 0 | 0 | 5.1667 | 193.0163 | #DIV/0!
|  | 0.015505 | 0 | 0.0070479 | 0.0084575 | 0.33333 | 2.3333 | 154 | 0.046516
|  | 0.01542 | 0.00771 | 0 | 0.00771 | 0.33333 | 7.3333 | 139.3333 | 0.04626
|  | 0.015377 | 0 | 0.0076886 | 0.0076886 | 0.33333 | 4 | 160 | 0.046132
|  | 0.015217 | 0 | 0.015217 | 0 | 0.16667 | 6.8333 | 170.8333 | 0.091303
|  | 0.015196 | 0 | 0 | 0.015196 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.015159 | 0.015159 | 0 | 0 | 0 | 5.3333 | 199.2427 | #DIV/0!
|  | 0.015159 | 0.015159 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.015159 | 0.015159 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.014876 | 0.014876 | 0 | 0 | 0.16667 | 7.3333 | 162.179 | 0.089257
|  | 0.014822 | 0.007411 | 0.007411 | 0 | 1.1667 | 4.6667 | 231.3333 | 0.012705
|  | 0.01481 | 0 | 0.01481 | 0 | 0 | 5.1667 | 217.1346 | #DIV/0!
|  | 0.01481 | 0 | 0.01481 | 0 | 0 | 5.1667 | 217.1346 | #DIV/0!
|  | 0.014761 | 0.014761 | 0 | 0 | 0 | 6.1667 | 230.3743 | #DIV/0!
|  | 0.014761 | 0.014761 | 0 | 0 | 0 | 5.6667 | 211.6953 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 5 | 222.3513 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 4.6667 | 207.5279 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 3.6667 | 163.0576 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.014721 | 0 | 0 | 0.014721 | 0 | 3.5 | 155.6459 | #DIV/0!
|  | 0.014416 | 0.014416 | 0 | 0 | 0.16667 | 4.1667 | 187.5 | 0.086497
|  | 0.014362 | 0.014362 | 0 | 0 | 0 | 5.8333 | 217.9217 | #DIV/0!
|  | 0.014362 | 0.014362 | 0 | 0 | 0 | 6 | 224.148 | #DIV/0!
|  | 0.014362 | 0.014362 | 0 | 0 | 0 | 5.1667 | 193.0163 | #DIV/0!
|  | 0.014362 | 0.014362 | 0 | 0 | 0 | 5 | 186.79 | #DIV/0!
|  | 0.014362 | 0.014362 | 0 | 0 | 0 | 4.1667 | 155.6583 | #DIV/0!
|  | 0.014361 | 0 | 0.014361 | 0 | 0 | 4.5 | 189.1173 | #DIV/0!
|  | 0.014352 | 0.0071761 | 0 | 0.0071761 | 0.33333 | 4.6667 | 196 | 0.043056
|  | 0.014352 | 0.014352 | 0 | 0 | 0.16667 | 9.3333 | 196 | 0.086113
|  | 0.014341 | 0.0012494 | 0.00089757 | 0.012194 | 0.16667 | 4.6667 | 184.8321 | 0.086048
|  | 0.014247 | 0 | 0 | 0.014247 | 0 | 3.5 | 155.6459 | #DIV/0!
|  | 0.014203 | 0.014203 | 0 | 0 | 0.83333 | 5.8333 | 221.6667 | 0.017043
|  | 0.014064 | 0.014064 | 0 | 0 | 1.6667 | 5 | 219.5 | 0.0084383
|  | 0.01401 | 0 | 0.0070052 | 0.0070052 | 0.66667 | 4 | 164 | 0.021016
|  | 0.013963 | 0.013963 | 0 | 0 | 0 | 5.3333 | 199.2427 | #DIV/0!
|  | 0.013963 | 0.013963 | 0 | 0 | 0 | 5.6667 | 211.6953 | #DIV/0!
|  | 0.013959 | 0 | 0.0049366 | 0.0090228 | 0 | 3 | 131.3739 | #DIV/0!
|  | 0.013912 | 0 | 0.013912 | 0 | 0 | 4.3333 | 182.1129 | #DIV/0!
|  | 0.013861 | 0.013861 | 0 | 0 | 0.33333 | 5 | 216.3333 | 0.041583
|  | 0.013754 | 0.013754 | 0 | 0 | 0.16667 | 7.6667 | 176.3333 | 0.082525
|  | 0.013626 | 0 | 0.006813 | 0.006813 | 1.3333 | 5.3333 | 212.6667 | 0.010219
|  | 0.013599 | 0 | 0.0013463 | 0.012253 | 0.16667 | 4.3333 | 173.2482 | 0.081595
|  | 0.013564 | 0.013564 | 0 | 0 | 0 | 4.6667 | 174.3373 | #DIV/0!
|  | 0.013535 | 0.013535 | 0 | 0 | 0.16667 | 4.6667 | 133.4423 | 0.081213
|  | 0.013463 | 0 | 0.013463 | 0 | 0 | 4.3333 | 182.1129 | #DIV/0!
|  | 0.013463 | 0 | 0.013463 | 0 | 0 | 4.3333 | 182.1129 | #DIV/0!
|  | 0.013463 | 0 | 0.013463 | 0 | 0 | 4.5 | 189.1173 | #DIV/0!
|  | 0.013455 | 0.013455 | 0 | 0 | 0.16667 | 3.8333 | 172.5 | 0.080731
|  | 0.013391 | 0.013391 | 0 | 0 | 0.16667 | 5.1667 | 196.3333 | 0.080346
|  | 0.013327 | 0 | 0.0066635 | 0.0066635 | 0.16667 | 3.3333 | 130 | 0.079962
|  | 0.013297 | 0 | 0 | 0.013297 | 0 | 4.5 | 200.1162 | #DIV/0!
|  | 0.013242 | 0.0066208 | 0 | 0.0066208 | 0.16667 | 6 | 186 | 0.079449
|  | 0.013165 | 0.013165 | 0 | 0 | 0 | 4.6667 | 174.3373 | #DIV/0!
|  | 0.013165 | 0.013165 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.013156 | 0.013156 | 0 | 0 | 0.16667 | 2.5 | 110 | 0.078937
|  | 0.013015 | 0 | 0.013015 | 0 | 0 | 3.8333 | 161.0999 | #DIV/0!
|  | 0.012857 | 0.0064286 | 0 | 0.0064286 | 0.16667 | 3 | 129 | 0.077143
|  | 0.012857 | 0.0064286 | 0 | 0.0064286 | 0.16667 | 4.6667 | 200.6667 | 0.077143
|  | 0.012825 | 0.012825 | 0 | 0 | 0.5 | 3.3333 | 154.1667 | 0.02565
|  | 0.012822 | 0 | 0 | 0.012822 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.012822 | 0 | 0 | 0.012822 | 0 | 3.3333 | 148.2342 | #DIV/0!
|  | 0.012822 | 0 | 0 | 0.012822 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.012796 | 0 | 0.00044878 | 0.012347 | 0 | 3.6667 | 162.6503 | #DIV/0!
|  | 0.012766 | 0.012766 | 0 | 0 | 0 | 5.1667 | 193.0163 | #DIV/0!
|  | 0.012766 | 0.012766 | 0 | 0 | 0 | 5.3333 | 199.2427 | #DIV/0!
|  | 0.012766 | 0.012766 | 0 | 0 | 0 | 4.8333 | 180.5637 | #DIV/0!
|  | 0.012766 | 0.012766 | 0 | 0 | 0 | 3.6667 | 136.9793 | #DIV/0!
|  | 0.012766 | 0.012766 | 0 | 0 | 0 | 4.8333 | 180.5637 | #DIV/0!
|  | 0.012686 | 0.0063431 | 0 | 0.0063431 | 0.16667 | 5.3333 | 96 | 0.076118
|  | 0.012566 | 0 | 0.012566 | 0 | 0 | 4.1667 | 175.1086 | #DIV/0!
|  | 0.012566 | 0 | 0.012566 | 0 | 0 | 3.5 | 147.0912 | #DIV/0!
|  | 0.012404 | 0 | 0.0071805 | 0.0052237 | 0 | 3.3333 | 142.5311 | #DIV/0!
|  | 0.012367 | 0.012367 | 0 | 0 | 0 | 5 | 186.79 | #DIV/0!
|  | 0.012367 | 0.012367 | 0 | 0 | 0 | 4.3333 | 161.8847 | #DIV/0!
|  | 0.012367 | 0.012367 | 0 | 0 | 0 | 4.8333 | 180.5637 | #DIV/0!
|  | 0.012367 | 0.012367 | 0 | 0 | 0 | 3.6667 | 136.9793 | #DIV/0!
|  | 0.012367 | 0.012367 | 0 | 0 | 0 | 4.1667 | 155.6583 | #DIV/0!
|  | 0.012347 | 0 | 0 | 0.012347 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.012347 | 0 | 0 | 0.012347 | 0 | 2.6667 | 118.5874 | #DIV/0!
|  | 0.012347 | 0 | 0 | 0.012347 | 0 | 3.6667 | 163.0576 | #DIV/0!
|  | 0.012334 | 0.012334 | 0 | 0 | 0.16667 | 6.6667 | 140 | 0.074003
|  | 0.012302 | 0.012302 | 0 | 0 | 0.83333 | 6.6667 | 170.6667 | 0.014762
|  | 0.012169 | 0 | 0.01122 | 0.00094977 | 0 | 2.3333 | 98.4682 | #DIV/0!
|  | 0.012034 | 0 | 0.0053854 | 0.0066484 | 0 | 4 | 173.4 | #DIV/0!
|  | 0.012024 | 0.0060121 | 0 | 0.0060121 | 2.1667 | 4.3333 | 187.6667 | 0.0055496
|  | 0.012024 | 0.0060121 | 0 | 0.0060121 | 1 | 5.3333 | 187.6667 | 0.012024
|  | 0.012008 | 0 | 0.0058342 | 0.0061735 | 0 | 3.3333 | 144.1605 | #DIV/0!
|  | 0.011968 | 0.011968 | 0 | 0 | 0 | 4.3333 | 161.8847 | #DIV/0!
|  | 0.011968 | 0.011968 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.011968 | 0.011968 | 0 | 0 | 0 | 3.1667 | 118.3003 | #DIV/0!
|  | 0.011872 | 0 | 0 | 0.011872 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.011872 | 0 | 0 | 0.011872 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.011789 | 0.011789 | 0 | 0 | 0.5 | 5.5 | 168.6667 | 0.023579
|  | 0.011768 | 0.011768 | 0 | 0 | 0.16667 | 3.3333 | 126.6667 | 0.070607
|  | 0.011725 | 0.0059587 | 0 | 0.0057665 | 0.16667 | 7.1667 | 129 | 0.070351
|  | 0.011668 | 0 | 0.011668 | 0 | 0 | 3.8333 | 161.0999 | #DIV/0!
|  | 0.011668 | 0 | 0.011668 | 0 | 0 | 4.3333 | 182.1129 | #DIV/0!
|  | 0.011668 | 0 | 0.011668 | 0 | 0 | 4 | 168.1042 | #DIV/0!
|  | 0.011661 | 0.011661 | 0 | 0 | 0.66667 | 4 | 156 | 0.017492
|  | 0.011569 | 0.011569 | 0 | 0 | 0 | 4.6667 | 174.3373 | #DIV/0!
|  | 0.011569 | 0.011569 | 0 | 0 | 0 | 4.6667 | 174.3373 | #DIV/0!
|  | 0.011569 | 0.011569 | 0 | 0 | 0 | 3.8333 | 143.2057 | #DIV/0!
|  | 0.011569 | 0.011569 | 0 | 0 | 0 | 4.1667 | 155.6583 | #DIV/0!
|  | 0.011559 | 0 | 0.0053854 | 0.0061735 | 0 | 3.5 | 151.5722 | #DIV/0!
|  | 0.01148 | 0 | 0.0056063 | 0.0058733 | 0.16667 | 5.5 | 137.5 | 0.068877
|  | 0.011397 | 0 | 0 | 0.011397 | 0 | 3.8333 | 170.4693 | #DIV/0!
|  | 0.011397 | 0 | 0 | 0.011397 | 0 | 4 | 177.881 | #DIV/0!
|  | 0.011397 | 0 | 0 | 0.011397 | 0 | 3 | 133.4108 | #DIV/0!
|  | 0.011362 | 0.0040579 | 0.0073042 | 0 | 0.16667 | 4.6667 | 177.3333 | 0.068173
|  | 0.011335 | 0.011335 | 0 | 0 | 0.33333 | 4.1667 | 163.5843 | 0.034006
|  | 0.011282 | 0.00073683 | 0 | 0.010545 | 0.16667 | 6.3333 | 149.245 | 0.06769
|  | 0.01122 | 0 | 0.01122 | 0 | 0 | 3.1667 | 133.0825 | #DIV/0!
|  | 0.011213 | 0.0056063 | 0 | 0.0056063 | 0.83333 | 5 | 175 | 0.013455
|  | 0.011106 | 0.011106 | 0 | 0 | 0.33333 | 4.3333 | 173.3333 | 0.033317
|  | 0.011106 | 0.011106 | 0 | 0 | 0.5 | 7 | 121.3333 | 0.022212
|  | 0.011052 | 0.011052 | 0 | 0 | 0.16667 | 6.1667 | 141.8333 | 0.066315
|  | 0.01102 | 0.01102 | 0 | 0 | 0.16667 | 3.1667 | 136.1667 | 0.066122
|  | 0.010956 | 0.010956 | 0 | 0 | 0.16667 | 6.6667 | 126.6667 | 0.065738
|  | 0.010956 | 0.010956 | 0 | 0 | 0.16667 | 3.8333 | 145.6667 | 0.065738
|  | 0.010922 | 0 | 0 | 0.010922 | 0 | 3 | 133.4108 | #DIV/0!
|  | 0.010922 | 0 | 0 | 0.010922 | 0 | 3 | 133.4108 | #DIV/0!
|  | 0.010892 | 0.010892 | 0 | 0 | 0.33333 | 3 | 127.5 | 0.032677
|  | 0.01085 | 0 | 0.01085 | 0 | 0.5 | 4 | 169.3333 | 0.021699
|  | 0.010846 | 0.00039893 | 0 | 0.010447 | 0 | 2.6667 | 117.402 | #DIV/0!
|  | 0.010807 | 0.0054034 | 0 | 0.0054034 | 1.8333 | 3.6667 | 168.6667 | 0.0058946
|  | 0.010771 | 0.010771 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.010771 | 0.010771 | 0 | 0 | 0 | 4.3333 | 161.8847 | #DIV/0!
|  | 0.010508 | 0 | 0.0052539 | 0.0052539 | 0.66667 | 2.6667 | 109.3333 | 0.015762
|  | 0.010447 | 0 | 0 | 0.010447 | 0 | 2.8333 | 125.9991 | #DIV/0!
|  | 0.010372 | 0.010372 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.01033 | 0.01033 | 0 | 0 | 0.16667 | 3.3333 | 104.393 | 0.061981
|  | 0.010322 | 0 | 0.010322 | 0 | 0 | 3.6667 | 154.0955 | #DIV/0!
|  | 0.010316 | 0 | 0.0051578 | 0.0051578 | 0.16667 | 6.3333 | 145.6667 | 0.061894
|  | 0.010316 | 0.0051578 | 0 | 0.0051578 | 0.16667 | 6 | 138 | 0.061894
|  | 0.010252 | 0.010252 | 0 | 0 | 0.66667 | 4 | 120 | 0.015377
|  | 0.010219 | 0.010219 | 0 | 0 | 0.5 | 5.5 | 159.5 | 0.020439
|  | 0.010091 | 0.010091 | 0 | 0 | 1.3333 | 2.6667 | 105 | 0.0075685
|  | 0.01007 | 0.00073683 | 0 | 0.0093332 | 0.16667 | 5.5 | 126.5 | 0.06042
|  | 0.010062 | 0.010062 | 0 | 0 | 0.16667 | 4 | 150.823 | 0.060375
|  | 0.010059 | 0 | 0.0050297 | 0.0050297 | 1.1667 | 7 | 157 | 0.0086223
|  | 0.0099734 | 0.0099734 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0099734 | 0.0099734 | 0 | 0 | 0 | 4 | 149.432 | #DIV/0!
|  | 0.0099734 | 0.0099734 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0099734 | 0.0099734 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0099734 | 0.0099734 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.0099726 | 0 | 0 | 0.0099726 | 0 | 3 | 133.4108 | #DIV/0!
|  | 0.0099726 | 0 | 0 | 0.0099726 | 0 | 2.1667 | 96.3522 | #DIV/0!
|  | 0.0099726 | 0 | 0 | 0.0099726 | 0 | 2.8333 | 125.9991 | #DIV/0!
|  | 0.0098671 | 0.0098671 | 0 | 0 | 1 | 4 | 154 | 0.0098671
|  | 0.0098244 | 0.0049122 | 0 | 0.0049122 | 0.16667 | 5.6667 | 130.3333 | 0.058946
|  | 0.0098244 | 0.0049122 | 0 | 0.0049122 | 0.16667 | 6.3333 | 145.6667 | 0.058946
|  | 0.009739 | 0.009739 | 0 | 0 | 0.33333 | 4.6667 | 88.6667 | 0.029217
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 3.1667 | 118.3003 | #DIV/0!
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 3.6667 | 136.9793 | #DIV/0!
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.0095744 | 0.0095744 | 0 | 0 | 0 | 3.8333 | 143.2057 | #DIV/0!
|  | 0.0094977 | 0 | 0 | 0.0094977 | 0 | 2.8333 | 125.9991 | #DIV/0!
|  | 0.0094476 | 0.0094476 | 0 | 0 | 0.16667 | 2.5 | 109.9527 | 0.056686
|  | 0.0093332 | 0.0048695 | 0 | 0.0044637 | 0.16667 | 2.1667 | 82.3333 | 0.055999
|  | 0.0092905 | 0.0046452 | 0 | 0.0046452 | 0.5 | 3 | 87 | 0.018581
|  | 0.0091755 | 0.0091755 | 0 | 0 | 0 | 3.3333 | 124.5267 | #DIV/0!
|  | 0.0091755 | 0.0091755 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.0091755 | 0.0091755 | 0 | 0 | 0 | 3.5 | 130.753 | #DIV/0!
|  | 0.0091623 | 0 | 0.0045812 | 0.0045812 | 0.16667 | 3.3333 | 130 | 0.054974
|  | 0.0090819 | 0.0043035 | 0 | 0.0047784 | 0.16667 | 4.1667 | 131.4117 | 0.054491
|  | 0.0090228 | 0 | 0 | 0.0090228 | 0 | 3 | 133.4108 | #DIV/0!
|  | 0.0090228 | 0 | 0 | 0.0090228 | 0 | 2.1667 | 96.3522 | #DIV/0!
|  | 0.0090228 | 0 | 0 | 0.0090228 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.0088847 | 0.0022212 | 0 | 0.0066635 | 0.33333 | 2.6667 | 138.6667 | 0.026654
|  | 0.0088419 | 0.004421 | 0 | 0.004421 | 0.33333 | 1.3333 | 46 | 0.026526
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 3.6667 | 136.9793 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 3.6667 | 136.9793 | #DIV/0!
|  | 0.0087766 | 0.0087766 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.0087458 | 0.0087458 | 0 | 0 | 0.5 | 2 | 60.6667 | 0.017492
|  | 0.0086497 | 0.0086497 | 0 | 0 | 0.16667 | 2.6667 | 120 | 0.051898
|  | 0.0086497 | 0.0086497 | 0 | 0 | 0.16667 | 1.6667 | 75 | 0.051898
|  | 0.0086497 | 0 | 0.0043249 | 0.0043249 | 0.16667 | 1.3333 | 60 | 0.051898
|  | 0.0085479 | 0 | 0 | 0.0085479 | 0 | 2.8333 | 125.9991 | #DIV/0!
|  | 0.0085479 | 0 | 0 | 0.0085479 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.0085479 | 0 | 0 | 0.0085479 | 0 | 2.3333 | 103.7639 | #DIV/0!
|  | 0.0085479 | 0 | 0 | 0.0085479 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0085269 | 0 | 0.0085269 | 0 | 0 | 3.1667 | 133.0825 | #DIV/0!
|  | 0.008472 | 0.008472 | 0 | 0 | 0.16667 | 5.5 | 118.2263 | 0.050832
|  | 0.0083776 | 0.0083776 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0083776 | 0.0083776 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0083776 | 0.0083776 | 0 | 0 | 0 | 3.3333 | 124.5267 | #DIV/0!
|  | 0.0083507 | 0.0041754 | 0 | 0.0041754 | 0.16667 | 4.3333 | 99.6667 | 0.050104
|  | 0.0083187 | 0.0083187 | 0 | 0 | 0.16667 | 4.1667 | 79.1667 | 0.049912
|  | 0.008313 | 0 | 0.004039 | 0.004274 | 0 | 2.3333 | 100.9124 | #DIV/0!
|  | 0.0082867 | 0.0082867 | 0 | 0 | 0.5 | 4 | 129.3333 | 0.016573
|  | 0.0082653 | 0 | 0.0082653 | 0 | 0.33333 | 3 | 129 | 0.024796
|  | 0.0080781 | 0 | 0.0080781 | 0 | 0 | 3 | 126.0782 | #DIV/0!
|  | 0.0079787 | 0.0079787 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0079787 | 0.0079787 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.0079787 | 0.0079787 | 0 | 0 | 0 | 3.3333 | 124.5267 | #DIV/0!
|  | 0.0076886 | 0.0076886 | 0 | 0 | 0.16667 | 2.6667 | 120 | 0.046132
|  | 0.0076566 | 0.0076566 | 0 | 0 | 0.33333 | 2.8333 | 119.5 | 0.02297
|  | 0.0076295 | 0.0035904 | 0.004039 | 0 | 0 | 3 | 119.0761 | #DIV/0!
|  | 0.0076293 | 0 | 0.0076293 | 0 | 0 | 2.8333 | 119.0738 | #DIV/0!
|  | 0.0076293 | 0 | 0.0076293 | 0 | 0 | 2.8333 | 119.0738 | #DIV/0!
|  | 0.0076293 | 0 | 0.0076293 | 0 | 0 | 2.3333 | 98.0608 | #DIV/0!
|  | 0.0076246 | 0.0076246 | 0 | 0 | 0.16667 | 4.8333 | 101.5 | 0.045747
|  | 0.0075981 | 0 | 0 | 0.0075981 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.0075981 | 0 | 0 | 0.0075981 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0075981 | 0 | 0 | 0.0075981 | 0 | 2.1667 | 96.3522 | #DIV/0!
|  | 0.0075797 | 0.0075797 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0075797 | 0.0075797 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0075797 | 0.0075797 | 0 | 0 | 0 | 3 | 112.074 | #DIV/0!
|  | 0.0074324 | 0.0037162 | 0 | 0.0037162 | 0.33333 | 2.6667 | 116 | 0.022297
|  | 0.0072401 | 0.0072401 | 0 | 0 | 1 | 3 | 113 | 0.0072401
|  | 0.0072188 | 0.0072188 | 0 | 0 | 1.1667 | 2.3333 | 112.6667 | 0.0061875
|  | 0.0072081 | 0.0072081 | 0 | 0 | 0.16667 | 2 | 90 | 0.043249
|  | 0.0071808 | 0.0071808 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0071808 | 0.0071808 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0071808 | 0.0071808 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0071808 | 0.0071808 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0071805 | 0 | 0.0071805 | 0 | 0 | 2.5 | 105.0651 | #DIV/0!
|  | 0.0071805 | 0 | 0.0071805 | 0 | 0 | 2.6667 | 112.0695 | #DIV/0!
|  | 0.0071805 | 0 | 0.0071805 | 0 | 0 | 1.3333 | 56.0347 | #DIV/0!
|  | 0.0071761 | 0.003588 | 0 | 0.003588 | 0.66667 | 2.6667 | 112 | 0.010764
|  | 0.0071761 | 0.0071761 | 0 | 0 | 0.16667 | 4.1667 | 87.5 | 0.043056
|  | 0.0071233 | 0 | 0 | 0.0071233 | 0 | 2.5 | 111.1757 | #DIV/0!
|  | 0.0071233 | 0 | 0 | 0.0071233 | 0 | 2.1667 | 96.3522 | #DIV/0!
|  | 0.007112 | 0.003556 | 0 | 0.003556 | 0.16667 | 2 | 74 | 0.042672
|  | 0.0070906 | 0.0070906 | 0 | 0 | 2.5 | 2.5 | 110.6667 | 0.0028363
|  | 0.0070052 | 0 | 0.0035026 | 0.0035026 | 0.66667 | 2.6667 | 109.3333 | 0.010508
|  | 0.0069518 | 0.0069518 | 0 | 0 | 0.16667 | 4.5 | 94.5 | 0.041711
|  | 0.0069405 | 0 | 0.0031415 | 0.0037991 | 0 | 2.1667 | 93.908 | #DIV/0!
|  | 0.0068877 | 0.0068877 | 0 | 0 | 0.16667 | 2.3333 | 100.3333 | 0.041326
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2.8333 | 105.8477 | #DIV/0!
|  | 0.0067819 | 0.0067819 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0067317 | 0 | 0.0067317 | 0 | 0 | 2.3333 | 98.0608 | #DIV/0!
|  | 0.0067317 | 0 | 0.0067317 | 0 | 0 | 2 | 84.0521 | #DIV/0!
|  | 0.0066635 | 0.0022212 | 0 | 0.0044423 | 0.33333 | 1 | 52 | 0.01999
|  | 0.0066484 | 0 | 0 | 0.0066484 | 0 | 2.3333 | 103.7639 | #DIV/0!
|  | 0.0066484 | 0 | 0 | 0.0066484 | 0 | 2 | 88.9405 | #DIV/0!
|  | 0.0066484 | 0 | 0 | 0.0066484 | 0 | 1.5 | 66.7054 | #DIV/0!
|  | 0.0066315 | 0.0066315 | 0 | 0 | 1 | 3 | 103.5 | 0.0066315
|  | 0.0064926 | 0.0064926 | 0 | 0 | 0.16667 | 1.6667 | 63.3333 | 0.038956
|  | 0.0064179 | 0.0064179 | 0 | 0 | 2.1667 | 2.1667 | 100.1667 | 0.0029621
|  | 0.0064072 | 0.0064072 | 0 | 0 | 1 | 3 | 75 | 0.0064072
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.3333 | 87.1687 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.0063829 | 0.0063829 | 0 | 0 | 0 | 2.6667 | 99.6213 | #DIV/0!
|  | 0.006283 | 0 | 0.006283 | 0 | 0 | 2.1667 | 91.0565 | #DIV/0!
|  | 0.006283 | 0 | 0.006283 | 0 | 0 | 1.5 | 63.0391 | #DIV/0!
|  | 0.006247 | 0.006247 | 0 | 0 | 0.16667 | 2.1667 | 97.5 | 0.037482
|  | 0.0061735 | 0 | 0 | 0.0061735 | 0 | 2.1667 | 96.3522 | #DIV/0!
|  | 0.0061735 | 0 | 0 | 0.0061735 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0061735 | 0 | 0 | 0.0061735 | 0 | 1.6667 | 74.1171 | #DIV/0!
|  | 0.0061509 | 0.0061509 | 0 | 0 | 0.33333 | 2.3333 | 84 | 0.018453
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 2.3333 | 87.1687 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 2.3333 | 87.1687 | #DIV/0!
|  | 0.005984 | 0.005984 | 0 | 0 | 0 | 2.5 | 93.395 | #DIV/0!
|  | 0.0058946 | 0.0058946 | 0 | 0 | 0.66667 | 3.3333 | 76.6667 | 0.0088419
|  | 0.0058946 | 0.0029473 | 0 | 0.0029473 | 0.33333 | 1.3333 | 46 | 0.017684
|  | 0.0058733 | 0 | 0.0029366 | 0.0029366 | 0.16667 | 2 | 50 | 0.03524
|  | 0.0058342 | 0 | 0.0058342 | 0 | 0 | 1.8333 | 77.0478 | #DIV/0!
|  | 0.0057665 | 0.0057665 | 0 | 0 | 0.16667 | 1.5 | 67.5 | 0.034599
|  | 0.0056986 | 0 | 0 | 0.0056986 | 0 | 2 | 88.9405 | #DIV/0!
|  | 0.0056986 | 0 | 0 | 0.0056986 | 0 | 1.3333 | 59.2937 | #DIV/0!
|  | 0.0056849 | 0.0056849 | 0 | 0 | 0.16667 | 1.3333 | 58.7263 | 0.034109
|  | 0.0056383 | 0 | 0.0028192 | 0.0028192 | 0.33333 | 0.66667 | 44 | 0.016915
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 2.3333 | 87.1687 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0055851 | 0.0055851 | 0 | 0 | 0 | 2.3333 | 87.1687 | #DIV/0!
|  | 0.0055743 | 0.0027871 | 0 | 0.0027871 | 0.83333 | 1.6667 | 87 | 0.0066891
|  | 0.0055529 | 0 | 0 | 0.0055529 | 0.33333 | 1.3333 | 69.3333 | 0.016659
|  | 0.0055102 | 0.0055102 | 0 | 0 | 0.16667 | 2 | 86 | 0.033061
|  | 0.0054995 | 0 | 0.0021998 | 0.0032997 | 0.33333 | 1 | 51.5 | 0.016499
|  | 0.0054898 | 0 | 0.0035903 | 0.0018995 | 0 | 1.1667 | 50.6599 | #DIV/0!
|  | 0.0054141 | 0.0054141 | 0 | 0 | 1 | 3 | 84.5 | 0.0054141
|  | 0.005318 | 0.005318 | 0 | 0 | 0.83333 | 0.83333 | 41.5 | 0.0063816
|  | 0.0052966 | 0.0052966 | 0 | 0 | 0.16667 | 1.8333 | 56.8333 | 0.03178
|  | 0.0052646 | 0.0052646 | 0 | 0 | 0.33333 | 2.8333 | 82.1667 | 0.015794
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.3333 | 59.2937 | #DIV/0!
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.3333 | 59.2937 | #DIV/0!
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.8333 | 81.5288 | #DIV/0!
|  | 0.0052237 | 0 | 0 | 0.0052237 | 0 | 1.6667 | 74.1171 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0051861 | 0.0051861 | 0 | 0 | 0 | 2.1667 | 80.9423 | #DIV/0!
|  | 0.0051471 | 0.0051471 | 0 | 0 | 2 | 2 | 80.3333 | 0.0025736
|  | 0.0049976 | 0.0049976 | 0 | 0 | 0.83333 | 0.83333 | 39 | 0.0059971
|  | 0.0049366 | 0 | 0.0049366 | 0 | 0 | 1.8333 | 77.0478 | #DIV/0!
|  | 0.0049366 | 0 | 0.0049366 | 0 | 0 | 1.1667 | 49.0304 | #DIV/0!
|  | 0.0049122 | 0.0024561 | 0 | 0.0024561 | 1 | 2 | 76.6667 | 0.0049122
|  | 0.0049122 | 0.0024561 | 0 | 0.0024561 | 0.16667 | 3 | 69 | 0.029473
|  | 0.0048695 | 0.0048695 | 0 | 0 | 0.16667 | 1.5 | 57 | 0.029217
|  | 0.0048695 | 0.0048695 | 0 | 0 | 0.16667 | 1.5 | 57 | 0.029217
|  | 0.0048054 | 0.0048054 | 0 | 0 | 0.16667 | 0.83333 | 37.5 | 0.028832
|  | 0.0048054 | 0.0048054 | 0 | 0 | 0.16667 | 1.5 | 67.5 | 0.028832
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.0047872 | 0.0047872 | 0 | 0 | 0 | 2 | 74.716 | #DIV/0!
|  | 0.004784 | 0.002392 | 0 | 0.002392 | 1 | 2 | 74.6667 | 0.004784
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 0.83333 | 37.0586 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.5 | 66.7054 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.6667 | 74.1171 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.5 | 66.7054 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.5 | 66.7054 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.6667 | 74.1171 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.6667 | 74.1171 | #DIV/0!
|  | 0.0047488 | 0 | 0 | 0.0047488 | 0 | 1.5 | 66.7054 | #DIV/0!
|  | 0.00472 | 0.00472 | 0 | 0 | 1 | 1 | 36.8333 | 0.00472
|  | 0.0046773 | 0.0046773 | 0 | 0 | 1 | 1 | 36.5 | 0.0046773
|  | 0.0046666 | 0 | 0.0046666 | 0 | 0.16667 | 2.6667 | 61.3333 | 0.027999
|  | 0.0046345 | 0.0023173 | 0 | 0.0023173 | 1 | 2 | 72.3333 | 0.0046345
|  | 0.0044878 | 0 | 0.0044878 | 0 | 0 | 1.5 | 63.0391 | #DIV/0!
|  | 0.0044878 | 0 | 0.0044878 | 0 | 0 | 1 | 42.0261 | #DIV/0!
|  | 0.0044637 | 0.0044637 | 0 | 0 | 0.5 | 1.6667 | 69.6667 | 0.0089274
|  | 0.0044637 | 0.0044637 | 0 | 0 | 0.16667 | 1.6667 | 63.3333 | 0.026782
|  | 0.0044423 | 0 | 0.0022212 | 0.0022212 | 0.33333 | 1.3333 | 69.3333 | 0.013327
|  | 0.0044423 | 0.0022212 | 0 | 0.0022212 | 0.33333 | 0.66667 | 34.6667 | 0.013327
|  | 0.004421 | 0.004421 | 0 | 0 | 0.16667 | 3 | 69 | 0.026526
|  | 0.004421 | 0.004421 | 0 | 0 | 1 | 1 | 34.5 | 0.004421
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0043883 | 0.0043883 | 0 | 0 | 0 | 1.8333 | 68.4897 | #DIV/0!
|  | 0.0043249 | 0.0043249 | 0 | 0 | 0.16667 | 0.83333 | 37.5 | 0.025949
|  | 0.0043035 | 0.0043035 | 0 | 0 | 0.16667 | 1.1667 | 36.1667 | 0.025821
|  | 0.004274 | 0 | 0 | 0.004274 | 0 | 1.1667 | 51.882 | #DIV/0!
|  | 0.004274 | 0 | 0 | 0.004274 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0042715 | 0.0042715 | 0 | 0 | 0.66667 | 2 | 50 | 0.0064072
|  | 0.0042608 | 0.0042608 | 0 | 0 | 0.16667 | 3.1667 | 66.5 | 0.025565
|  | 0.0042433 | 0.0042433 | 0 | 0 | 0.16667 | 1.5 | 66.2263 | 0.02546
|  | 0.0042288 | 0.0042288 | 0 | 0 | 0.66667 | 2 | 66 | 0.0063431
|  | 0.0041647 | 0 | 0.0020823 | 0.0020823 | 0.16667 | 1.3333 | 52 | 0.024988
|  | 0.0040579 | 0 | 0 | 0.0040579 | 0.33333 | 3 | 57 | 0.012174
|  | 0.004039 | 0 | 0.004039 | 0 | 0 | 1.5 | 63.0391 | #DIV/0!
|  | 0.004039 | 0 | 0.004039 | 0 | 0 | 1.1667 | 49.0304 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0039893 | 0.0039893 | 0 | 0 | 0 | 1.6667 | 62.2633 | #DIV/0!
|  | 0.0038443 | 0.0038443 | 0 | 0 | 0.16667 | 1.3333 | 60 | 0.023066
|  | 0.0038443 | 0 | 0.0019222 | 0.0019222 | 0.16667 | 0.66667 | 30 | 0.023066
|  | 0.0038443 | 0.0019222 | 0 | 0.0019222 | 0.16667 | 2 | 36 | 0.023066
|  | 0.0037991 | 0 | 0 | 0.0037991 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0037991 | 0 | 0 | 0.0037991 | 0 | 1.1667 | 51.882 | #DIV/0!
|  | 0.0037589 | 0.0037589 | 0 | 0 | 0.16667 | 1.1667 | 51.3333 | 0.022553
|  | 0.0036414 | 0.0036414 | 0 | 0 | 0.16667 | 1.5 | 46.5 | 0.021849
|  | 0.0036308 | 0.0036308 | 0 | 0 | 0.16667 | 1.5 | 51 | 0.021785
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.3333 | 49.8107 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.1667 | 43.5843 | #DIV/0!
|  | 0.0035904 | 0.0035904 | 0 | 0 | 0 | 1.5 | 56.037 | #DIV/0!
|  | 0.003588 | 0.003588 | 0 | 0 | 0.16667 | 2 | 42 | 0.021528
|  | 0.003588 | 0.003588 | 0 | 0 | 0.16667 | 1.6667 | 35 | 0.021528
|  | 0.0033638 | 0.0033638 | 0 | 0 | 0.16667 | 0.66667 | 30 | 0.020183
|  | 0.0033638 | 0.0033638 | 0 | 0 | 0.16667 | 1.1667 | 52.5 | 0.020183
|  | 0.0033638 | 0.0033638 | 0 | 0 | 0.16667 | 0.5 | 22.5 | 0.020183
|  | 0.0033531 | 0 | 0.0016766 | 0.0016766 | 1.1667 | 2.3333 | 52.3333 | 0.0028741
|  | 0.0033531 | 0 | 0.0016766 | 0.0016766 | 1.1667 | 2.3333 | 52.3333 | 0.0028741
|  | 0.0033242 | 0 | 0 | 0.0033242 | 0 | 1.1667 | 51.882 | #DIV/0!
|  | 0.0033242 | 0 | 0 | 0.0033242 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0033242 | 0 | 0 | 0.0033242 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0032459 | 0 | 0.0013463 | 0.0018995 | 0 | 1.1667 | 50.6599 | #DIV/0!
|  | 0.0031915 | 0.0031915 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0031915 | 0.0031915 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0031915 | 0.0031915 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0031502 | 0.0031502 | 0 | 0 | 0.33333 | 0.83333 | 34.6667 | 0.0094506
|  | 0.0031415 | 0 | 0.0031415 | 0 | 0 | 1.1667 | 49.0304 | #DIV/0!
|  | 0.0031415 | 0 | 0.0031415 | 0 | 0 | 1.1667 | 49.0304 | #DIV/0!
|  | 0.0031415 | 0 | 0.0031415 | 0 | 0 | 0.83333 | 35.0217 | #DIV/0!
|  | 0.0031415 | 0 | 0.0031415 | 0 | 0 | 0.5 | 21.013 | #DIV/0!
|  | 0.0031415 | 0 | 0.0031415 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.0031395 | 0.0031395 | 0 | 0 | 0.16667 | 2 | 42 | 0.018837
|  | 0.0030755 | 0.0030755 | 0 | 0 | 0.16667 | 0.83333 | 40 | 0.018453
|  | 0.00299 | 0.00299 | 0 | 0 | 0.16667 | 1.1667 | 46.6667 | 0.01794
|  | 0.002926 | 0 | 0.002926 | 0 | 0.66667 | 0.66667 | 22.8333 | 0.0043889
|  | 0.0029153 | 0.0029153 | 0 | 0 | 0.16667 | 2.1667 | 45.5 | 0.017492
|  | 0.0028832 | 0.0028832 | 0 | 0 | 0.16667 | 0.66667 | 30 | 0.017299
|  | 0.0028493 | 0 | 0 | 0.0028493 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0028493 | 0 | 0 | 0.0028493 | 0 | 1 | 44.4703 | #DIV/0!
|  | 0.0028192 | 0.0028192 | 0 | 0 | 0.33333 | 1.3333 | 44 | 0.0084575
|  | 0.0028192 | 0 | 0.0028192 | 0 | 0.33333 | 0.33333 | 22 | 0.0084575
|  | 0.0028192 | 0.0028192 | 0 | 0 | 0.16667 | 0.66667 | 29.3333 | 0.016915
|  | 0.0027925 | 0.0027925 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0027925 | 0.0027925 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.0027925 | 0.0027925 | 0 | 0 | 0 | 1.1667 | 43.5843 | #DIV/0!
|  | 0.0027925 | 0.0027925 | 0 | 0 | 0 | 1.1667 | 43.5843 | #DIV/0!
|  | 0.002771 | 0 | 0.0013463 | 0.0014247 | 0 | 0.66667 | 28.8321 | #DIV/0!
|  | 0.0027551 | 0.0027551 | 0 | 0 | 0.16667 | 0.33333 | 14.3333 | 0.016531
|  | 0.0027017 | 0 | 0 | 0.0027017 | 0.16667 | 1.3333 | 30.6667 | 0.01621
|  | 0.0026927 | 0 | 0.0026927 | 0 | 0 | 1 | 42.0261 | #DIV/0!
|  | 0.0026927 | 0 | 0.0026927 | 0 | 0 | 0.83333 | 35.0217 | #DIV/0!
|  | 0.0026927 | 0 | 0.0026927 | 0 | 0 | 1 | 42.0261 | #DIV/0!
|  | 0.0026927 | 0 | 0.0026927 | 0 | 0 | 0.5 | 21.013 | #DIV/0!
|  | 0.002627 | 0.0013135 | 0 | 0.0013135 | 0.5 | 1 | 41 | 0.0052539
|  | 0.0025308 | 0.0025308 | 0 | 0 | 0.33333 | 0.66667 | 26.3333 | 0.0075925
|  | 0.0024988 | 0.0024988 | 0 | 0 | 0.16667 | 1 | 39 | 0.014993
|  | 0.0024668 | 0.0024668 | 0 | 0 | 0.16667 | 1.8333 | 38.5 | 0.014801
|  | 0.0024347 | 0.0024347 | 0 | 0 | 0.16667 | 0.66667 | 25.3333 | 0.014608
|  | 0.0024347 | 0.0024347 | 0 | 0 | 0.16667 | 1 | 38 | 0.014608
|  | 0.0024347 | 0.0012174 | 0.0012174 | 0 | 0.16667 | 1 | 38 | 0.014608
|  | 0.0024134 | 0.0024134 | 0 | 0 | 1 | 1 | 37.6667 | 0.0024134
|  | 0.0024027 | 0.0024027 | 0 | 0 | 0.16667 | 0.83333 | 37.5 | 0.014416
|  | 0.0024027 | 0.0024027 | 0 | 0 | 0.16667 | 0.66667 | 30 | 0.014416
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0023936 | 0.0023936 | 0 | 0 | 0 | 1 | 37.358 | #DIV/0!
|  | 0.0023852 | 0.0023852 | 0 | 0 | 0.16667 | 1.1667 | 37.2263 | 0.014311
|  | 0.0023744 | 0 | 0 | 0.0023744 | 0 | 0.83333 | 37.0586 | #DIV/0!
|  | 0.0023744 | 0 | 0 | 0.0023744 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0023744 | 0 | 0 | 0.0023744 | 0 | 0.66667 | 29.6468 | #DIV/0!
|  | 0.0023744 | 0 | 0 | 0.0023744 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0023744 | 0 | 0 | 0.0023744 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.0022959 | 0.0022959 | 0 | 0 | 0.16667 | 0.83333 | 35.8333 | 0.013775
|  | 0.0021785 | 0.0010892 | 0 | 0.0010892 | 0.16667 | 0.66667 | 22.6667 | 0.013071
|  | 0.0021571 | 0.0010785 | 0 | 0.0010785 | 0.33333 | 0.66667 | 33.6667 | 0.0064713
|  | 0.0021571 | 0.0010785 | 0 | 0.0010785 | 0.33333 | 0.66667 | 33.6667 | 0.0064713
|  | 0.0020289 | 0 | 0.0020289 | 0 | 0.16667 | 0.16667 | 6.3333 | 0.012174
|  | 0.0019969 | 0.0019969 | 0 | 0 | 0.83333 | 0.83333 | 31.1667 | 0.0023963
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019947 | 0.0019947 | 0 | 0 | 0 | 0.83333 | 31.1317 | #DIV/0!
|  | 0.0019222 | 0.0019222 | 0 | 0 | 0.16667 | 0.33333 | 15 | 0.011533
|  | 0.0019222 | 0.0019222 | 0 | 0 | 0.16667 | 0.33333 | 15 | 0.011533
|  | 0.0019222 | 0.00096108 | 0 | 0.00096108 | 0.16667 | 0.33333 | 15 | 0.011533
|  | 0.0018995 | 0 | 0 | 0.0018995 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0018995 | 0 | 0 | 0.0018995 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.0018995 | 0 | 0 | 0.0018995 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0018794 | 0.0018794 | 0 | 0 | 0.33333 | 0.33333 | 14.6667 | 0.0056383
|  | 0.0018734 | 0 | 0.00044878 | 0.0014247 | 0 | 0.66667 | 29.2395 | #DIV/0!
|  | 0.0018581 | 0.00092905 | 0 | 0.00092905 | 0.33333 | 0.66667 | 29 | 0.0055743
|  | 0.0018473 | 0 | 0.00089757 | 0.00094977 | 0 | 0.33333 | 14.4161 | #DIV/0!
|  | 0.0017951 | 0 | 0.0017951 | 0 | 0 | 0.66667 | 28.0174 | #DIV/0!
|  | 0.0017951 | 0 | 0.0017951 | 0 | 0 | 0.66667 | 28.0174 | #DIV/0!
|  | 0.0017951 | 0 | 0.0017951 | 0 | 0 | 0.66667 | 28.0174 | #DIV/0!
|  | 0.0017951 | 0 | 0.0017951 | 0 | 0 | 0.5 | 21.013 | #DIV/0!
|  | 0.0017951 | 0 | 0.0017951 | 0 | 0 | 0.66667 | 28.0174 | #DIV/0!
|  | 0.001794 | 0.00089701 | 0 | 0.00089701 | 0.33333 | 0.66667 | 28 | 0.0053821
|  | 0.001794 | 0.00089701 | 0 | 0.00089701 | 0.33333 | 0.66667 | 28 | 0.0053821
|  | 0.0017086 | 0 | 0.00085429 | 0.00085429 | 0.33333 | 0.66667 | 26.6667 | 0.0051258
|  | 0.0017086 | 0.0017086 | 0 | 0 | 0.16667 | 0.66667 | 26.6667 | 0.010252
|  | 0.0017086 | 0 | 0.00085429 | 0.00085429 | 0.33333 | 0.66667 | 26.6667 | 0.0051258
|  | 0.0016659 | 0 | 0.00083294 | 0.00083294 | 0.16667 | 0.66667 | 26 | 0.0099952
|  | 0.0016232 | 0.0016232 | 0 | 0 | 0.16667 | 0.66667 | 25.3333 | 0.009739
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.66667 | 24.9053 | #DIV/0!
|  | 0.0015957 | 0.0015957 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.0015377 | 0.00076886 | 0 | 0.00076886 | 0.16667 | 1 | 18 | 0.0092264
|  | 0.0015377 | 0.00076886 | 0 | 0.00076886 | 0.16667 | 1 | 18 | 0.0092264
|  | 0.0015377 | 0.00076886 | 0 | 0.00076886 | 0.16667 | 1.3333 | 24 | 0.0092264
|  | 0.0014523 | 0.0014523 | 0 | 0 | 0.16667 | 0.5 | 17 | 0.0087138
|  | 0.0014416 | 0.0014416 | 0 | 0 | 0.16667 | 0.33333 | 15 | 0.0086497
|  | 0.0014416 | 0.0014416 | 0 | 0 | 0.16667 | 0.33333 | 15 | 0.0086497
|  | 0.0014416 | 0.0014416 | 0 | 0 | 0.16667 | 0.5 | 22.5 | 0.0086497
|  | 0.0014247 | 0 | 0 | 0.0014247 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0014247 | 0 | 0 | 0.0014247 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0014247 | 0 | 0 | 0.0014247 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.0014247 | 0 | 0 | 0.0014247 | 0 | 0.5 | 22.2351 | #DIV/0!
|  | 0.0013882 | 0.00069411 | 0 | 0.00069411 | 0.33333 | 0.66667 | 21.6667 | 0.0041647
|  | 0.0013882 | 0.00069411 | 0 | 0.00069411 | 0.33333 | 0.66667 | 21.6667 | 0.0041647
|  | 0.0013669 | 0.00068344 | 0 | 0.00068344 | 0.16667 | 0.33333 | 21.3333 | 0.0082012
|  | 0.0013463 | 0 | 0.0013463 | 0 | 0 | 0.5 | 21.013 | #DIV/0!
|  | 0.0012814 | 0.0012814 | 0 | 0 | 0.16667 | 0.5 | 20 | 0.0076886
|  | 0.0012174 | 0.0012174 | 0 | 0 | 0.16667 | 1 | 19 | 0.0073042
|  | 0.0012174 | 0.0012174 | 0 | 0 | 0.16667 | 0.33333 | 12.6667 | 0.0073042
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.5 | 18.679 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.0011968 | 0.0011968 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.0011533 | 0.00057665 | 0 | 0.00057665 | 0.16667 | 1 | 18 | 0.0069198
|  | 0.0011213 | 0.0011213 | 0 | 0 | 0.16667 | 0.66667 | 14 | 0.0067276
|  | 0.0011213 | 0.0011213 | 0 | 0 | 0.16667 | 0.66667 | 14 | 0.0067276
|  | 0.0011106 | 0 | 0 | 0.0011106 | 0.33333 | 0.33333 | 17.3333 | 0.0033317
|  | 0.0010892 | 0.0010892 | 0 | 0 | 0.16667 | 0.5 | 17 | 0.0065354
|  | 0.0010679 | 0 | 0 | 0.0010679 | 0.16667 | 0.66667 | 16.6667 | 0.0064072
|  | 0.0010679 | 0 | 0.00053393 | 0.00053393 | 0.16667 | 0.66667 | 16.6667 | 0.0064072
|  | 0.0010679 | 0 | 0.0010679 | 0 | 0.16667 | 0.5 | 12.5 | 0.0064072
|  | 0.00096108 | 0.00096108 | 0 | 0 | 0.16667 | 0.16667 | 7.5 | 0.0057665
|  | 0.00096108 | 0.00048054 | 0 | 0.00048054 | 0.16667 | 0.33333 | 15 | 0.0057665
|  | 0.00096108 | 0.00096108 | 0 | 0 | 0.16667 | 0.33333 | 15 | 0.0057665
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.33333 | 14.8234 | #DIV/0!
|  | 0.00094977 | 0 | 0 | 0.00094977 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00090769 | 0.00090769 | 0 | 0 | 0.33333 | 0.33333 | 14.1667 | 0.0027231
|  | 0.00090769 | 0.00090769 | 0 | 0 | 0.33333 | 0.33333 | 14.1667 | 0.0027231
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00089757 | 0 | 0.00089757 | 0 | 0 | 0.33333 | 14.0087 | #DIV/0!
|  | 0.00083294 | 0.00041647 | 0 | 0.00041647 | 0.16667 | 0.33333 | 13 | 0.0049976
|  | 0.00083294 | 0.00041647 | 0 | 0.00041647 | 0.16667 | 0.33333 | 13 | 0.0049976
|  | 0.00081158 | 0.00081158 | 0 | 0 | 0.16667 | 0.5 | 9.5 | 0.0048695
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.33333 | 12.4527 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00079787 | 0.00079787 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00072615 | 0.00072615 | 0 | 0 | 0.16667 | 0.33333 | 11.3333 | 0.0043569
|  | 0.00072615 | 0.00036308 | 0 | 0.00036308 | 0.16667 | 0.33333 | 11.3333 | 0.0043569
|  | 0.00066208 | 0.00066208 | 0 | 0 | 0.16667 | 0.33333 | 10.3333 | 0.0039725
|  | 0.00060868 | 0.00060868 | 0 | 0 | 0.16667 | 0.33333 | 6.3333 | 0.0036521
|  | 0.00049122 | 0 | 0.00024561 | 0.00024561 | 0.16667 | 0.33333 | 7.6667 | 0.0029473
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00047488 | 0 | 0 | 0.00047488 | 0 | 0.16667 | 7.4117 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.00044878 | 0 | 0.00044878 | 0 | 0 | 0.16667 | 7.0043 | #DIV/0!
|  | 0.0004485 | 0.0004485 | 0 | 0 | 0.16667 | 0.33333 | 7 | 0.002691
|  | 0.0004485 | 0.0004485 | 0 | 0 | 0.16667 | 0.16667 | 3.5 | 0.002691
|  | 0.00042715 | 0.00042715 | 0 | 0 | 0.16667 | 0.16667 | 6.6667 | 0.0025629
|  | 0.00040579 | 0.00040579 | 0 | 0 | 0.16667 | 0.16667 | 6.3333 | 0.0024347
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00039893 | 0.00039893 | 0 | 0 | 0 | 0.16667 | 6.2263 | #DIV/0!
|  | 0.00036308 | 0.00036308 | 0 | 0 | 0.16667 | 0.16667 | 5.6667 | 0.0021785
|  | 0.00024561 | 0 | 0 | 0.00024561 | 0.16667 | 0.16667 | 3.8333 | 0.0014737
|  | 0.00024561 | 0 | 0 | 0.00024561 | 0.16667 | 0.16667 | 3.8333 | 0.0014737
|  | 0.00022425 | 0.00022425 | 0 | 0 | 0.16667 | 0.16667 | 3.5 | 0.0013455
|  | 0.00022425 | 0.00022425 | 0 | 0 | 0.16667 | 0.16667 | 3.5 | 0.0013455
|  | 0.00022425 | 0.00022425 | 0 | 0 | 0.16667 | 0.16667 | 3.5 | 0.0013455