## Sheet1
Utility | SDG&E
Table No. | 12
Date Modified | 2023-12-19
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Covered Conductor Installation | WMP.455 | Quantitative | Miles | 33 | 45 | 60 | 0 17 | 0 30 | 60 40 | Quantitative | Distribution OH Hardening - Covered Conductor
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP.473 | Quantitative | Miles | 12.94 | 63.88 | 84.43 | 0 | 0 | 125 | Quantitative | Strategic Undergrounding
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP.475 | Quantitative | Miles | 1.8 | 1.8 | 1.9 | 0 | 0 | 0 | Quantitative | Distribution OH System Hardening
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP.543 | Quantitative | Miles | 7.8 | 8.8 | 14.1 | 10.2 | 10.2 | 10.2 | Quantitative | Transmission OH Hardening
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP.545 | Quantitative | Miles | 2.7 | 2.7 | 7.1 | 0 | 1 | 1 | Quantitative | Transmission OH Hardening - Distribution Underbuild
Grid Design, Operations, and Maintenance | Microgrids | WMP.462 | Quantitative | Micogrids | 0 | 0 | 0 | 0 | 0 | 3 1 | Quantitative | Microgrids
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP.463 | Quantitative | Circuits | 3 | 4 | 5 | 3 | 6 | 8 | Quantitative | Advanced Protection
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP.1195 | Quantitative | Nodes | 20 | 40 | 60 | 30 | 52 | 60 | Quantitative | Early Fault Detection
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP.549 | Quantitative | Base Stations | 10 | 17 | 35 | 20 5 | 40 10 | 60 15 | Quantitative | Distribution Communications Reliability Improvements
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.453 | Quantitative | Capacitors | 11 | 13 | 20 | 0 | 0 | 0 | Quantitative | Capacitor Maintenance and replacement program (SCADA)
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.459 | Quantitative | Fuses | 20 | 30 | 40 | 0 | 0 | 0 | Quantitative | Expulsion fuse replacement
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.464 | Quantitative | HLCs | 126 | 188 | 250 | 126 | 188 | 250 | Quantitative | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.550 | Quantitative | Arrestors | 1531 | 1715 | 1848 | 1531 | 1715 | 1848 | Quantitative | Lightning arrester removal and replacement
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.972 | Quantitative | Poles | 50 | 150 | 200 | 50 | 150 | 200 | Quantitative | Avian Protection
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.1189 | Quantitative | Poles | 0 | 27 | 60 | 98 64 | 150 131 | 200 267 | Quantitative | Strategic Pole Replacement Program
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP.449 | Quantitative | WFIs | 0 | 0 | 0 | 0 | 300 0 | 300 0 | Quantitative | Wireless Fault Indicators
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP.461 | Quantitative | Switches | 9 | 10 | 10 | 8 | 10 | 10 | Quantitative | PSPS Sectionalizing Enhancements
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP.468 | Quantitative | Generators | 100 | 250 | 300 | 100 29 | 150 44 | 300 58 | Quantitative | Fixed Backup Power
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP.466 | Quantitative | NA | NA | NA | NA | NA | NA | NA | Qualitative | Generator Grant Program
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP.467 | Qualitative | NA | NA | NA | NA | NA | NA | NA | Qualitative | Generator Assistance Program
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.478 | Quantitative | Inspections | 8450 | 9650 | 11100 | 14850 | 15350 | 15450 | Quantitative | Distribution Overhead Detailed Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.479 | Quantitative | Inspections | 850 | 1672 | 2387 | 1121 | 1442 | 1960 | Quantitative | Transmission Overhead Detailed Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.481 | Quantitative | Inspections | 6343 | 8147 | 9578 | 4,766 150 | 7,149 300 | 9,532 300 | Quantitative | Distribution Infrared Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.482 | Quantitative | Inspections | 0 | 0 | 6179 | 0 | 0 | 6179 | Quantitative | Transmission Infrared Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.483 | Quantitative | Inspections | 0 | 50 | 50 | 0 | 0 | 0 | Quantitative | Distribution Wood Pole Intrusive Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.1190 | Quantitative | Inspections | 0 | 0 | 73 | 0 | 0 | 0 | Quantitative | Transmission Wood Pole Intrusive Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.552 | Quantitative | Inspections | 6848 | 10270 | 13692 | 6753 | 10127 | 13500 | Quantitative | Drone Assessments
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.488 | Quantitative | Inspections | 61800 | 86500 | 86880 | 71047 | 83247 | 86197 | Quantitative | Distribution Overhead Patrol Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.489 | Quantitative | Structures | 6008 | 6008 | 6337 | 6008 | 6008 | 6337 | Quantitative | Transmission Overhead Patrol Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.555 | Quantitative | Structures | 0 | 1632 | 1632 | 0 | 1632 | 1632 | Quantitative | Transmission 69kV Tier 3 Visual Inspections
Grid Design, Operations, and Maintenance | Asset Inspections | WMP.492 | Quantitative | Inspections | 192 | 281 | 384 | 192 | 281 | 384 | Quantitative | Substation Patrol inspections
Grid Design, Operations, and Maintenance | Quality assurance / quality control | WMP.1191 | Quantitative | Findings | 100% | 100% | 100% | 100% | 100% | 100% | Quantitative | QA/QC of Transmission Inspections
Grid Design, Operations, and Maintenance | Quality assurance / quality control | WMP.491 | Quantitative | Inspections | 0 | 0 | 160 | 0 | 0 | 77 | Quantitative | QA/QC of Distribution Detailed Inspections
Grid Design, Operations, and Maintenance | Quality assurance / quality control | WMP.1192 | Quantitative | Inspections | 6848 | 10270 | 13692 | 6753 | 10127 | 13500 | Quantitative | QA/QC of Distribution Drone Assessments
Grid Design, Operations, and Maintenance | Quality assurance / quality control | WMP.1193 | Quantitative | Inspections | 0 | 0 | 12 | 0 | 0 | 0 | Quantitative | QA/QC of Wood Pole Intrusive (Transmission & Distribution)
Grid Design, Operations, and Maintenance | Quality assurance / quality control | WMP.1194 | Quantitative | Inspections | 9 | 9 | 18 | 9 | 9 | 18 | Quantitative | QA/QC of Substation Inspections
Situational Awareness and Forecasting | Enviornmental monitoring System | WMP.970 | Quantitative | Sensors | 6 | 6 | 6 | 3 0 | 6 0 | 18 0 | Quantitative | Air Quality Index
Situational Awareness and Forecasting | Enviornmental monitoring System | WMP.1430 | Quantitative | WX Stations |  |  |  | 114 | 171 | 222 |  | Weather Station Maintenance and Calibration
Vegetation Management and Inspection | Vegetation Management Inspection Program | WMP.494 | Quantitative | Inspections | 241800 | 374200 | 485400 | 241800 | 374200 | 485400 | Quantitative | Detailed Inspections
Vegetation Management and Inspection | Vegetation Management Inspection Program | WMP.508 | Quantitative | VMAs | 9 | 106 | 106 | 9 | 106 | 106 | Quantitative | Off-Cycle Patrol
Vegetation Management and Inspection | Fuels management | WMP.497 | Quantitative | Poles | 100 | 200 | 500 | 100 | 200 | 500 | Quantitative | Fuels management
Vegetation Management and Inspection | Pole Clearing | WMP.512 | Quantitative | Poles | 25150 | 27890 | 33010 | 25150 | 27890 | 33010 | Quantitative | Pole Clearing (Brushing)
Vegetation Management and Inspection | Clearance | WMP.501 | Quantitative | Trees Trimmed or Removed | 5890 | 8780 | 11200 | 5890 | 8780 | 11200 | Quantitative | Clearance
Vegetation Management and Inspection | Quality assurance / quality control | WMP.505 | Quantitative | Inspections | 15% | 15% | 15% | 15% | 15% | 15% | Quantitative | QA/QC Vegetation Management