## Workplan Template (2023)
2023 Work Plan | SA-11
2023 Units
Project Name | Circuit Protection Zone (CPZ) (as applicable) | Equipment # or Pole # (as applicable) | Lat | Long | Scheduled Completion date (Per unit completion defintion) | Total Units | Tier 3 HFTD | Tier 2 HFTD | Zone 1 HFTD | HFRA Non-HFTD | Non-HFTD Tier 2/3 Buffer | Non-HFTD / Non- HFRA | MAT
SHINGLE SPRINGS 1104 |  |  |  |  | 2023-06-30 | 1 | x |  | x |  |  |  | 49I
RED BLUFF 1104 |  |  |  |  | 2023-06-30 | 1 | x |  | x |  |  |  | 49I
2

## Workplan Template (2024)
2023 Work Plan | SA-11
2023 Units
Project Name | Circuit Protection Zone (CPZ) (as applicable) | Equipment # or Pole # (as applicable) | Lat | Long | Scheduled Completion date (Per unit completion defintion) | Total Units | Tier 3 HFTD | Tier 2 HFTD | Zone 1 HFTD | HFRA Non-HFTD | Non-HFTD Tier 2/3 Buffer | Non-HFTD / Non- HFRA | MAT
CAMP EVERS 2106 |  |  |  |  | 2024-11-30 | 1 | x | x | x |  |  |  | 49I
MIWUK 1702 |  |  |  |  | 2024-11-30 | 1 | x | x | x |  |  |  | 49I
2

## Workplan Template (2025)
2023 Work Plan | SA-11
2023 Units
Project Name | Circuit Protection Zone (CPZ) (as applicable) | Equipment # or Pole # (as applicable) | Lat | Long | Scheduled Completion date (Per unit completion defintion) | Total Units | Tier 3 HFTD | Tier 2 HFTD | Zone 1 HFTD | HFRA Non-HFTD | Non-HFTD Tier 2/3 Buffer | Non-HFTD / Non- HFRA | MAT
OILFIELDS 1103 |  |  |  |  | 2025-11-30 | 1 | x | x | x |  |  |  | 49I
SHINGLE SPRINGS 2109 |  |  |  |  | 2025-11-30 | 1 | x | x | x |  |  |  | 49I
MARIPOSA 2102 |  |  |  |  | 2025-11-30 | 1 | x | x | x
WEIMAR 1101 |  |  |  |  | 2025-11-30 | 1 | x | x | x
4