## PG&E UG Workplan 2023- 26_Redac
GH-04: PG&E 2023-2026 Undergrounding Workplan
Data as of June 26, 2024
[16 empty] | 1260.4541 | 364.7809 | 265.007 | 468.3682 | 308.0558
Order | Order Description | Category | MAT Code | SAP Status | Status | Division | Region | City | County | Latitude | Longitude | Circuit Protection Zone | Applicable Risk Model | Applicable Risk Model Risk Rank | HFTD Tier | Total 2023-2026 UG Miles | UG - 2023 Complete | UG - 2024 Complete / Forecast | UG - 2025 Forecast | UG - 2026 Forecast
31437447 | GEP 6650 OASIS ROAD REDDING | Other | 10I | DOCC | Post-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6492 | -122.3426 |  | v2 | 968 | Tier 2 | 0.1553 | 0.1553 | 0 | 0 | 0
31533746 | COMP-3285&3231 SAINT HELENA HWY N ST FR | Other | 10I | DOCC | Post-Construction | NB | Region 1 - North Coast | St Helena | NAPA | 38.5336 | -122.5148 |  | v2 | 1901 | Tier 3 | 0.15814 | 0.15814 | 0 | 0 | 0
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.6834 | -120.6389 |  | v2 | 1946 | Tier 3 | 0.57348 | 0.57348 | 0 | 0 | 0
35056808 | R20A - FREESTONE SONOMA COUNTY | Other | 30A | CONS | In-Construction | SO | Region 1 - North Coast | Sebastopol | SONOMA | 38.3734 | -122.918 |  | v2 | 534 | Tier 3 | 1.1309 | 0 | 1.1309 | 0 | 0
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7821 | -120.6094 |  | v2 | 1946 | Tier 3 | 2.2348 | 2.2348 | 0 | 0 | 0
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Shingle Springs | EL DORADO | 38.7686 | -120.9251 |  | v2 | 159 | Tier 3 | 4.0593 | 4.0593 | 0 | 0 | 0
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Placerville | EL DORADO | 38.6839 | -120.6354 |  | v2 | 1946 | Tier 3 | 0.33883 | 0.33883 | 0 | 0 | 0
35114040 | OCGC CWSP - PINE GROVE 1102 - LR1222 | Base SH | 08W | FICL | Post-Construction | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.436 | -120.5559 |  | v2 | 2271 | Tier 3 | 0.057386 | 0.057386 | 0 | 0 | 0
35134959 | VALLEY SPRINGS 1102 FEEDER OUTLET | Other | 06A | CONS | In-Construction | ST | Region 5 - Central Valley | Valley Springs | CALAVERAS | 38.2131 | -120.7638 |  | v2 | 322 | Tier 2 | 0.42386 | 0 | 0.42386 | 0 | 0
35145001 | PSPS - CLAYTON 2215 - CB | Base SH | 08W | FICL | Post-Construction | DI | Region 3 - Bay Area | Concord | CONTRA COSTA | 37.931 | -121.9736 |  | v2 | 1739 | Tier 2 & 3 | 1.875 | 1.875 | 0 | 0 | 0
35145540 | PSPS - FROGTOWN 1702 - CB | Base SH | 08W | CONS | In-Construction | ST | Region 5 - Central Valley | Angels Camp | CALAVERAS | 38.0563 | -120.5345 |  | v2 | 1316 | Tier 3 | 0.4947 | 0 | 0.4947 | 0 | 0
35148392 | ARNOLD - STANISLAUS 1702 PIH | Other | 49M | FICL | Post-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2582 | -120.3481 |  | v2 | 2651 | Tier 3 | 0.34735 | 0.34735 | 0 | 0 | 0
35159243 | EP 38050 HWY 36 E MINERAL | Other | 10H | CLSD | Closed | NV | Region 2 - North East | Mineral | TEHAMA | 40.3457 | -121.6064 |  | v2 | 2528 | Tier 2 | 0.95739 | 0.95739 | 0 | 0 | 0
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | v2 | 474 | Tier 3 | 1.04 | 0 | 0 | 1.04 | 0
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7988 | -122.7044 |  | v2 | 474 | Tier 3 | 3.8303 | 0 | 0 | 3.8303 | 0
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Base SH | 08W | DOCC | Post-Construction | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.8684 | -121.8573 |  | v2 | 377 | Tier 3 | 1.6784 | 1.6784 | 0 | 0 | 0
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Base SH | 08W | ESTS | Estimating | HB | Region 1 - North Coast | Middletown | LAKE | 38.7241 | -122.619 |  | v2 | 468 | Tier 3 | 1.5 | 0 | 0 | 0 | 1.5
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1 | Fire Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9107 | -121.3275 |  | v2 | 11 | Tier 2 & 3 | 0.017803 | 0 | 0.017803 | 0 | 0
35217274 | FRRB-HMB 1103 655644 PH1.1 SM COUNTY | Fire Rebuild | 08W | FICL | Post-Construction | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.1601 | -122.3295 |  | v2 | 2055 | Tier 2 | 0.88277 | 0.88277 | 0 | 0 | 0
35217275 | FRRB-HMB 1103 655644 PH2.1 SC COUNTY | Fire Rebuild | 08W | DOCC | Post-Construction | CC | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.1703 | -122.3044 |  | v2 | 2055 | Tier 2 | 2.7439 | 2.7439 | 0 | 0 | 0
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Base SH | 08W | FICL | Post-Construction | DI | Region 3 - Bay Area | Concord | CONTRA COSTA | 37.9632 | -121.9407 |  | v2 | 18 | Tier 2 | 1.5739 | 1.5739 | 0 | 0 | 0
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Base SH | 08W | FICL | Post-Construction | DI | Region 3 - Bay Area | Pittsburg | CONTRA COSTA | 37.9907 | -121.896 |  | v2 | 21 | Tier 2 | 0.028409 | 0.028409 | 0 | 0 | 0
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | v2 | 42 | Tier 3 | 3.2708 | 1.0816 | 2.1892 | 0 | 0
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | v2 | 49 | Tier 2 | 7.0055 | 0 | 7.0055 | 0 | 0
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7265 | -122.5415 |  | v2 | 14 | Tier 2 & 3 | 2.0684 | 2.0684 | 0 | 0 | 0
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Bangor | BUTTE | 39.3878 | -121.4038 |  | v2 | 355 | Tier 2 | 0.12973 | 0.12973 | 0 | 0 | 0
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Base SH | 08W | DOCC | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8855 | -121.0156 |  | v2 | 68 | Tier 2 | 0.9358 | 0.9358 | 0 | 0 | 0
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Base SH | 08W | CONS | In-Construction | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | v2 | 2048 | Tier 2 | 0.20019 | 0 | 0.20019 | 0 | 0
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9101 | -121.3297 |  | v2 | 11 | Tier 2 & 3 | 2.0761 | 1.4989 | 0.57727 | 0 | 0
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9007 | -121.3594 |  | v2 | 11 | Tier 2 & 3 | 1.8095 | 0 | 1.8095 | 0 | 0
35224856 | BR-12-5A HWY 191 RELOCATION, PARB | Other | 10K | MAPP | Post-Construction | NV | Region 2 - North East | Paradise | BUTTE | 39.7352 | -121.6113 |  | v2 | 1537 | Tier 2 & 3 | 2.4278 | 2.3129 | 0.11496 | 0 | 0
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Base SH | 08W | FICL | Post-Construction | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.8879 | -121.8676 |  | v2 | 377 | Tier 3 | 0.092992 | 0.092992 | 0 | 0 | 0
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | v2 | 7 | Tier 3 | 0.85511 | 0 | 0.85511 | 0 | 0
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6253 | -122.4633 |  | v2 | 7 | Tier 3 | 4.4303 | 0 | 4.4303 | 0 | 0
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.8928 |  | v2 | 52 | Tier 2 | 0.19792 | 0.19792 | 0 | 0 | 0
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 1.1449 | 0 | 0 | 1.1449 | 0
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 0.70511 | 0.70511 | 0 | 0 | 0
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 0.69924 | 0.69924 | 0 | 0 | 0
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 0.43674 | 0.43674 | 0 | 0 | 0
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 2.8756 | 0 | 0 | 2.8756 | 0
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 0.69261 | 0.69261 | 0 | 0 | 0
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | v2 | 468 | Tier 3 | 1.372 | 1.372 | 0 | 0 | 0
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7249 | -122.6186 |  | v2 | 468 | Tier 3 | 1.4125 | 1.4125 | 0 | 0 | 0
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7573 | -122.606 |  | v2 | 8 | Tier 2 | 1.5888 | 0 | 0 | 0 | 1.5888
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3423 | -122.0077 |  | v2 | 42 | Tier 3 | 0.45871 | 0.45871 | 0 | 0 | 0
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | v2 | 14 | Tier 2 & 3 | 1.1049 | 1.1049 | 0 | 0 | 0
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7564 | -122.6056 |  | v2 | 14 | Tier 2 & 3 | 0.95852 | 0.95852 | 0 | 0 | 0
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | Base SH | 08W | CONS | In-Construction | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4438 | -122.602 |  | v2 | 2048 | Tier 2 | 1.1847 | 0 | 1.1847 | 0 | 0
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | v2 | 27 | Tier 2 & 3 | 2.6782 | 0 | 0 | 0 | 2.6782
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9822 | -122.6031 |  | v2 | 27 | Tier 2 & 3 | 2.8943 | 0 | 0 | 0 | 2.8943
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | Base SH | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | v2 | 49 | Tier 2 | 4.7536 | 0 | 4.7536 | 0 | 0
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | Base SH | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | v2 | 49 | Tier 2 | 4.6155 | 0 | 4.6155 | 0 | 0
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Georgetown | EL DORADO | 38.905 | -120.8401 |  | v2 | 1363 | Tier 3 | 0.66042 | 0.66042 | 0 | 0 | 0
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Georgetown | EL DORADO | 38.9063 | -120.837 |  | v2 | 1363 | Tier 3 | 0.64129 | 0.64129 | 0 | 0 | 0
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.6242 | -122.3039 |  | v2 | 49 | Tier 2 | 0.6053 | 0.6053 | 0 | 0 | 0
35234526 | OCGC PSPS - MARTELL 1101 - SUTTER CREEK | Base SH | 08W | FICL | Post-Construction | ST | Region 5 - Central Valley | Sutter Creek | AMADOR | 38.3949 | -120.804 |  | v2 | 999 | Tier 2 | 0.87614 | 0.87614 | 0 | 0 | 0
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | v2 | 474 | Tier 3 | 2.782 | 0 | 0 | 2.782 | 0
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | v2 | 474 | Tier 3 | 0.80208 | 0.80208 | 0 | 0 | 0
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | v2 | 474 | Tier 3 | 0.12311 | 0.12311 | 0 | 0 | 0
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Middletown | LAKE | 38.7576 | -122.6358 |  | v2 | 474 | Tier 3 | 1.0684 | 0 | 1.0684 | 0 | 0
35236439 | OCGC ECOP-MIDDLETWN1101-H12-LR548-PH2.15 | Base SH | 08W | CLSD | Closed | HB | Region 1 - North Coast | Middletown | LAKE | 38.7577 | -122.6359 |  | v2 | 474 | Tier 3 | 0.047348 | 0 | 0.047348 | 0 | 0
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Oroville | BUTTE | 39.5762 | -121.3051 |  | v2 | 1480 | Tier 3 | 2.0655 | 0 | 0 | 2.0655 | 0
35237937 | EQUIP ACCESS ISSUE 1025 HIDDEN VALLEY RD | Other | 2BP | DOCC | Post-Construction | CC | Region 4 - Central Coast | Soquel | SANTA CRUZ | 37.0341 | -121.9738 |  | v2 | 2595 | Tier 3 | 0.015341 | 0.015341 | 0 | 0 | 0
35240166 | CWSP - VOLTA 1101CB PH 1.1 | Base SH | 08W | CLSD | Closed | NV | Region 2 - North East | Manton | SHASTA | 40.4595 | -121.8662 |  | v2 | 76 | Tier 2 & 3 | 0.015341 | 0.015341 | 0 | 0 | 0
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 SM | Fire Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6348 | -121.3915 |  | v2 | 1299 | Tier 3 | 0.33807 | 0.33807 | 0 | 0 | 0
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | Base SH | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Cool | EL DORADO | 38.9141 | -121.0189 |  | v2 | 68 | Tier 2 | 0.58011 | 0 | 0 | 0.58011 | 0
35254259 | CWSP - VOLTA 1101CB PH 1.3 | Base SH | 08W | CLSD | Closed | NV | Region 2 - North East | Manton | SHASTA | 40.4594 | -121.8663 |  | v2 | 76 | Tier 2 & 3 | 0.25455 | 0.25455 | 0 | 0 | 0
35254945 | CWSP - VOLTA 11011596 - PH1.3 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | v2 | 966 | Tier 2 | 0.49148 | 0.49148 | 0 | 0 | 0
35254947 | CWSP - VOLTA 11011596 - PH1.5 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Paynes Creek | TEHAMA | 40.351 | -121.7811 |  | v2 | 966 | Tier 2 | 0.25038 | 0.25038 | 0 | 0 | 0
35256083 | OCGC CWSP - UPPER LAKE 11011276 PH 2 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1434 | -123.0023 |  | v2 | 335 | Tier 2 | 1.8593 | 1.8593 | 0 | 0 | 0
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Bella Vista | SHASTA | 40.6324 | -122.2376 |  | v2 | 100 | Tier 2 | 0.10739 | 0.10739 | 0 | 0 | 0
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5186 | -119.9402 |  | v2 | 428 | Tier 2 & 3 | 2.6763 | 0 | 0 | 0 | 2.6763
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | Base SH | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5165 | -119.9716 |  | v2 | 428 | Tier 2 | 2.9869 | 2.9869 | 0 | 0 | 0
35277924 | CWSP AUBERRY 1101 R2578 PH 1.5 | Base SH | 08W | FICL | Post-Construction | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0071 | -119.4086 |  | v2 | 163 | Tier 2 | 0.12633 | 0.12633 | 0 | 0 | 0
35277925 | CWSP AUBERRY 1101 CB PH 1.2 | Base SH | 08W | FICL | Post-Construction | FR | Region 5 - Central Valley | Auberry | FRESNO | 37.0746 | -119.4845 |  | v2 | 63 | Tier 2 | 0.14148 | 0.14148 | 0 | 0 | 0
35277935 | CWSP AUBERRY 1101 R2839 PH 1.4 | Base SH | 08W | FICL | Post-Construction | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0313 | -119.4396 |  | v2 | 274 | Tier 2 | 0.083333 | 0.083333 | 0 | 0 | 0
35277938 | CWSP AUBERRY 1101 R2578 PH 2.4 | Base SH | 08W | MAPP | Post-Construction | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 37.0125 | -119.4038 |  | v2 | 163 | Tier 2 | 0.42822 | 0.42822 | 0 | 0 | 0
35278093 | CWSP AUBERRY 1101 R2578 PH 3.4 | Base SH | 08W | PEND | Permitting/Dependency | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9797 | -119.3677 |  | v2 | 163 | Tier 2 | 0.41496 | 0 | 0 | 0.41496 | 0
35278890 | CWSP AUBERRY 1101 R2578 PH 5.2 | Base SH | 08W | PEND | Permitting/Dependency | FR | Region 5 - Central Valley | Tollhouse | FRESNO | 36.9737 | -119.3888 |  | v2 | 163 | Tier 2 | 0.12235 | 0 | 0 | 0 | 0.12235
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | Base SH | 08W | CONS | In-Construction | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | v2 | 56 | Tier 2 & 3 | 1.5324 | 1.5324 | 0 | 0 | 0
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | Base SH | 08W | DOCC | Post-Construction | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 |  | v2 | 56 | Tier 2 & 3 | 0.98769 | 0.98769 | 0 | 0 | 0
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.958 | -121.2964 |  | v2 | 378 | Tier 2 & 3 | 6.8367 | 0 | 6.8367 | 0 | 0
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | Fire Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | Belden | PLUMAS | 40.0071 | -121.2415 |  | v2 | 378 | Tier 2 & 3 | 2.4947 | 0 | 2.4947 | 0 | 0
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Quincy | PLUMAS | 40.0399 | -120.9685 |  | v2 | 1172 | Tier 2 & 3 | 3.415 | 0 | 3.415 | 0 | 0
35279985 | FRRB-BIG MEADOW2101 UG RND VLY RES PH1.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Chester | PLUMAS | 40.1203 | -120.9582 |  | v2 | 916 | Tier 2 | 2.7989 | 2.7989 | 0 | 0 | 0
35280362 | CWSP- MARIPOSA 210244036 PH1.4 | Base SH | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.4632 | -119.9482 |  | v2 | 50 | Tier 2 & 3 | 0.13258 | 0 | 0.13258 | 0 | 0
35280493 | FRRB -BIG MEADOWS 21012260 UG TL 1.13 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1423 | -120.9547 |  | v2 | 916 | Tier 2 | 0.44811 | 0.44811 | 0 | 0 | 0
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Greenville | PLUMAS | 40.135 | -120.9275 |  | v2 | 895 | Tier 2 | 0.82008 | 0 | 0 | 0.82008 | 0
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9141 | -121.3272 |  | v2 | 378 | Tier 2 & 3 | 1.3686 | 0 | 1.3686 | 0 | 0
35280505 | HWY 299 SHASTA R20A | Other | 30A | ESTS | Estimating | NV | Region 2 - North East | Shasta | SHASTA | 40.5938 | -122.4857 |  | v2 | 1614 | Tier 3 | 0.37879 | 0 | 0.37879 | 0 | 0
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9955 | -121.2748 |  | v2 | 378 | Tier 2 & 3 | 2.4705 | 0 | 2.4705 | 0 | 0
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Twain | PLUMAS | 40.0222 | -121.0643 |  | v2 | 1748 | Tier 2 | 1.4616 | 0 | 1.4616 | 0 | 0
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7898 | -123.4452 |  | v2 | 1474 | Tier 2 | 0.51799 | 0.51799 | 0 | 0 | 0
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Crescent Mills | PLUMAS | 40.0604 | -120.9643 |  | v2 | 1322 | Tier 2 | 2.5703 | 2.5703 | 0 | 0 | 0
35283198 | CWSP HARTLEY 1101 LR698 1.4 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.108 | -122.9558 |  | v2 | 58 | Tier 2 | 0.29773 | 0 | 0.29773 | 0 | 0
35283343 | OCGC CWSP UPPER LAKE 1101 1276 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1488 | -122.9992 |  | v2 | 335 | Tier 2 | 0.55909 | 0.55909 | 0 | 0 | 0
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.13 | -122.997 |  | v2 | 335 | Tier 2 | 1.4462 | 0.96799 | 0.47822 | 0 | 0
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | Base SH | 08W | UNSC | Ready for Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1253 | -122.9948 |  | v2 | 335 | Tier 2 | 0.038068 | 0 | 0 | 0.038068 | 0
35283938 | CWSP - WOODSIDE 1101 FS 775939 PH 1.1 | Base SH | 08W | CONS | In-Construction | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3781 | -122.2797 |  | v2 | 1145 | Tier 3 | 0.84356 | 0.45341 | 0.39015 | 0 | 0
35284023 | FRRB - DUNBAR 1101 416 | Fire Rebuild | 08W | CONS | In-Construction | SO | Region 1 - North Coast | Santa Rosa | SONOMA | 38.4361 | -122.5779 |  | v2 | 1684 | Tier 3 | 1.3411 | 0.19091 | 1.1502 | 0 | 0
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | Base SH | 08W | DOCC | Post-Construction | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | v2 | 235 | Tier 2 & 3 | 0.80985 | 0.80985 | 0 | 0 | 0
35284365 | +CWSP STANISLAUS 1702 CB PH 1.3 | Base SH | 08W | CONS | In-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2399 | -120.3619 |  | v2 | 235 | Tier 2 & 3 | 2.7129 | 0 | 2.7129 | 0 | 0
35284810 | FRRB-HMB 1103 SM CO LR6012 PUMP HOUSE | Fire Rebuild | 08W | ESTS | Estimating | PN | Region 3 - Bay Area | Pescadero | SAN MATEO | 37.2086 | -122.3251 |  | v2 | 2186 | Tier 2 | 0.85814 | 0 | 0 | 0 | 0.85814
35285064 | OCGCCWSP POTTERVLY PH 1105 LR37476 PH1.2 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3076 | -123.1133 |  | v2 | 396 | Tier 2 | 0.63125 | 0.63125 | 0 | 0 | 0
35285249 | OCGC CWSP - UPPER LAKE 1101 1276 PH 2.4 | Base SH | 08W | APPR | Estimating | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1673 | -123.0087 |  | v2 | 335 | Tier 2 | 2.3348 | 2.1686 | 0.16629 | 0 | 0
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6*GC | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Lakeport | LAKE | 39.1758 | -123.0191 |  | v2 | 335 | Tier 2 | 0.41799 | 0 | 0.41799 | 0 | 0
35285594 | FRRB - ECHO SUMMIT 1101 - UG-10 (DC07) | Fire Rebuild | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Twin Bridges | EL DORADO | 38.8075 | -120.0935 |  | v2 | 2005 | Tier 2 | 0.21989 | 0 | 0 | 0 | 0.21989
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.2145 | -123.0742 |  | v2 | 75 | Tier 2 | 1.0436 | 0 | 0 | 0 | 1.0436
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Ukiah | MENDOCINO | 39.1988 | -123.0496 |  | v2 | 75 | Tier 2 | 0.62008 | 0 | 0 | 0.62008 | 0
35290510 | CWSP PTR VLY PH 1105 LR1904 PH4.3 VER 3 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Upper Lake | LAKE | 39.1887 | -123.0323 |  | v2 | 75 | Tier 2 | 0.55303 | 0 | 0 | 0 | 0.55303
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Crescent Mills | PLUMAS | 40.0553 | -120.9636 |  | v2 | 1322 | Tier 2 | 0.6625 | 0.6625 | 0 | 0 | 0
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1718 | -121.0769 |  | v2 | 916 | Tier 2 | 1.335 | 1.335 | 0 | 0 | 0
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1523 | -120.9417 |  | v2 | 995 | Tier 2 | 1.2955 | 1.2955 | 0 | 0 | 0
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1581 | -121.081 |  | v2 | 995 | Tier 2 | 2.0723 | 2.0521 | 0.020265 | 0 | 0
35290808 | OCGCCWSP POTTER VLY PH 1105 LR1904 PH2.9 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.2815 | -123.1027 |  | v2 | 75 | Tier 2 | 0.20587 | 0.20587 | 0 | 0 | 0
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | Fire Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1672 | -120.9367 |  | v2 | 995 | Tier 2 | 0.48788 | 0.48788 | 0 | 0 | 0
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1719 | -121.0339 |  | v2 | 916 | Tier 2 | 4.0852 | 4.0852 | 0 | 0 | 0
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | Fire Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.175 | -120.9765 |  | v2 | 916 | Tier 2 | 2.6481 | 2.6481 | 0 | 0 | 0
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1601 | -120.9487 |  | v2 | 916 | Tier 2 | 1.2301 | 1.2301 | 0 | 0 | 0
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | Fire Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1576 | -120.9382 |  | v2 | 995 | Tier 2 | 0.24318 | 0.24318 | 0 | 0 | 0
35292784 | FRRB - BUCKS CREEK 1102CB PH5 | Fire Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.011 | -121.1988 |  | v2 | 378 | Tier 2 | 3.1443 | 0 | 0 | 3.1443 | 0
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Greenville | PLUMAS | 40.1774 | -121.0987 |  | v2 | 2342 | Tier 2 | 1.1 | 0 | 0 | 1.1 | 0
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1717 | -121.0715 |  | v2 | 2342 | Tier 2 | 0.23636 | 0.23636 | 0 | 0 | 0
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | Fire Rebuild | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1615 | -120.9334 |  | v2 | 1285 | Tier 2 | 0.11932 | 0.11932 | 0 | 0 | 0
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | Base SH | 08W | DOCC | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8729 | -120.991 |  | v2 | 68 | Tier 2 | 0.46212 | 0.46212 | 0 | 0 | 0
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | Base SH | 08W | DOCC | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8956 | -120.9606 |  | v2 | 169 | Tier 2 | 0.58902 | 0.58902 | 0 | 0 | 0
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8964 | -120.922 |  | v2 | 169 | Tier 2 | 1.0653 | 1.0653 | 0 | 0 | 0
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | Base SH | 08W | CLSD | Closed | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8973 | -120.9098 |  | v2 | 169 | Tier 2 | 0.3017 | 0.3017 | 0 | 0 | 0
35293670 | CWSP-MOUNTAIN QUARRIES 2101 LR1350PH2.10 | Base SH | 08W | DOCC | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8805 | -120.9418 |  | v2 | 169 | Tier 2 | 0.65417 | 0.65417 | 0 | 0 | 0
35293846 | OCGC_CWSP PVPH 1105 LR1904 PH1.9 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3009 | -123.0524 |  | v2 | 75 | Tier 2 & 3 | 0.70133 | 0.70133 | 0 | 0 | 0
35295446 | FRRB - BUCKS CREEK 1103 CB PH2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Quincy | PLUMAS | 39.8957 | -121.2789 |  | v2 | 1658 | Tier 2 & 3 | 0.59848 | 0 | 0.59848 | 0 | 0
35297464 | FRRB-PT MORETTI 1101 12122 P1S3 460SWAN | Fire Rebuild | 08W | PEND | Permitting/Dependency | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0777 | -122.2439 |  | v2 | 2199 | Tier 2 | 1.0021 | 0 | 0 | 1.0021 | 0
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.8422 | -123.485 |  | v2 | 1474 | Tier 2 | 4.5937 | 4.5937 | 0 | 0 | 0
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.8422 | -123.485 |  | v2 | 1474 | Tier 2 | 0.95928 | 0.95928 | 0 | 0 | 0
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.8422 | -123.485 |  | v2 | 1474 | Tier 2 | 0.93371 | 0.93371 | 0 | 0 | 0
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7844 | -123.4236 |  | v2 | 1474 | Tier 2 | 0.45455 | 0.45455 | 0 | 0 | 0
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7967 | -123.3513 |  | v2 | 1474 | Tier 2 | 0.8 | 0.8 | 0 | 0 | 0
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.8422 | -123.485 |  | v2 | 1474 | Tier 2 | 1.0606 | 1.0606 | 0 | 0 | 0
35298571 | CWSP ANDERSON 1103 LR1600 PH1 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.469 | -122.2542 |  | v2 | 143 | Tier 2 | 0.29678 | 0.29678 | 0 | 0 | 0
35299629 | PSPS CLARK ROAD 1102 CB PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Oroville | BUTTE | 39.654 | -121.6323 |  | v2 | 268 | Tier 2 | 0.89091 | 0 | 0.89091 | 0 | 0
35299631 | PSPS CLARK ROAD 1102 LR81296 PH 1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6474 | -121.6306 |  | v2 | 698 | Tier 2 | 3.5237 | 3.5237 | 0 | 0 | 0
35299633 | PSPS CLARK ROAD 1102 LR514690 PH 2.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6766 | -121.5675 |  | v2 | 1703 | Tier 2 | 1.2955 | 0 | 1.2955 | 0 | 0
35299634 | PSPS CLARK ROAD 1102 LR514690 PH 1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6568 | -121.5763 |  | v2 | 1033 | Tier 2 | 2.322 | 2.322 | 0 | 0 | 0
35299635 | PSPS CLARK ROAD 1102 LR47006 PH 1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Paradise | BUTTE | 39.6988 | -121.5743 |  | v2 | 1535 | Tier 2 | 2.3252 | 0.65133 | 1.6739 | 0 | 0
35300933 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.2 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8775 | -120.993 |  | v2 | 68 | Tier 2 | 0.49432 | 0.49432 | 0 | 0 | 0
35301112 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3.4 | Base SH | 08W | DOCC | Post-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8641 | -120.9817 |  | v2 | 68 | Tier 2 | 0.49905 | 0.49905 | 0 | 0 | 0
35305303 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Cool | EL DORADO | 38.8972 | -120.989 |  | v2 | 169 | Tier 2 | 1.1206 | 0 | 0 | 1.1206 | 0
35305308 | CWSP MOUNTAIN QUARRIES 2101 LR1350 PH1.7 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Cool | EL DORADO | 38.8944 | -120.9647 |  | v2 | 169 | Tier 2 | 0.45833 | 0 | 0.45833 | 0 | 0
35311895 | CWSP ANDERSON 1103 LR226050 PH 1.1 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4803 | -122.2646 |  | v2 | 262 | Tier 2 | 2.4659 | 2.4659 | 0 | 0 | 0
35311896 | CWSP - BELL 1108 LR2202 PH 1.1 | Base SH | 08W | ESTS | Estimating | SI | Region 2 - North East | Auburn | PLACER | 38.9961 | -121.1091 |  | v2 | 118 | Tier 2 | 3.6788 | 0 | 0 | 3.6788 | 0
35311897 | PSPS - CORNING 1102 LR53184 PH 1.1 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Corning | TEHAMA | 39.8685 | -122.5663 |  | v2 | 413 | Tier 2 | 4.1133 | 4.1133 | 0 | 0 | 0
35311898 | PSPS - CORNING 1102 LR915324 PH 1.1 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Corning | TEHAMA | 39.9193 | -122.437 |  | v2 | 457 | Tier 2 | 2.0881 | 2.0881 | 0 | 0 | 0
35311899 | PSPS - COTTONWOOD 1102544790 PH 1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | v2 | 123 | Tier 2 | 3.339 | 3.339 | 0 | 0 | 0
35312540 | PSPS - COTTONWOOD 11029026 PH1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | v2 | 271 | Tier 2 | 4.8006 | 4.7561 | 0.044508 | 0 | 0
35312541 | PSPS - CURTIS 1701 CB PH 1.1 | Base SH | 08W | FICL | Post-Construction | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9777 | -120.3274 |  | v2 | 1166 | Tier 2 | 0.46686 | 0.46686 | 0 | 0 | 0
35312542 | PSPS - DUNBAR 1101 440 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | SO | Region 1 - North Coast | Glen Ellen | SONOMA | 38.3791 | -122.5192 |  | v2 | 1827 | Tier 2 & 3 | 0.67386 | 0 | 0 | 0.67386 | 0
35312543 | CWSP - ELK CREEK 1101 LR2002 PH 1.1-DC07 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.5896 | -122.5395 |  | v2 | 315 | Tier 2 | 3.1943 | 2.9263 | 0.26799 | 0 | 0
35312544 | CWSP - ELK CREEK 1101 LR93504 PH1.1-DC07 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.5927 | -122.5431 |  | v2 | 206 | Tier 2 | 0.51913 | 0.51913 | 0 | 0 | 0
35312545 | CWSP FLINT 1101 750 PH 1.1 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.8586 | -121.0805 |  | v2 | 152 | Tier 2 | 1.7595 | 0 | 1.7595 | 0 | 0
35312549 | PSPS - JESSUP 1103 LR348657 PH 1.1 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Redding | SHASTA | 40.4913 | -122.2744 |  | v2 | 590 | Tier 2 | 0.94489 | 0.94489 | 0 | 0 | 0
35312551 | CWSP - REDBUD 1101 LR454 PH 1.1 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0837 | -122.66 |  | v2 | 312 | Tier 3 | 3.3917 | 0 | 3.3917 | 0 | 0
35312552 | CWSP REDBUD 1101 708166 PH 1.1 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.023 | -122.6779 |  | v2 | 345 | Tier 2 & 3 | 0.73409 | 0.73409 | 0 | 0 | 0
35312553 | PSPS - TEJON 1102 LR2455 PH 1.1 | Base SH | 08W | CONS | In-Construction | KE | Region 5 - Central Valley | Lebec | KERN | 34.8582 | -118.8837 |  | v2 | 642 | Tier 2 | 1.7642 | 0 | 1.7642 | 0 | 0
35312560 | PSPS WYANDOTTE 1110 LR980944 PH1.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5054 | -121.4999 |  | v2 | 976 | Tier 2 | 2.1254 | 1.1481 | 0.97727 | 0 | 0
35313249 | PLUCODIXIE-BUSH ST Z1 GREENVILLE | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1415 | -120.9483 |  | N/A | N/A | TBD | 1.1652 | 1.1652 | 0 | 0 | 0
35314415 | CWSP - BELL 1108 LR2202 PH 2.1 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.9962 | -121.1167 |  | v2 | 118 | Tier 2 | 1.9231 | 0 | 1.9231 | 0 | 0
35314416 | CWSP - BELL 1108 LR2202 PH 3.1 | Base SH | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Auburn | PLACER | 38.9981 | -121.1168 |  | v2 | 118 | Tier 2 | 0.95947 | 0 | 0 | 0.95947 | 0
35316018 | PLUCODIXIE-BIDWELL ST Z2 GREENVILLE | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1407 | -120.9513 |  | N/A | N/A | TBD | 0.65814 | 0.57102 | 0.087121 | 0 | 0
35316019 | PLUCODIXIE-FORGAY AVE Z3 GREENVILLE | Community Rebuild | 95F | UNSC | Ready for Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1435 | -120.9581 |  | N/A | N/A | TBD | 1.017 | 0 | 1.017 | 0 | 0
35316200 | PLUCODIXIE-KINDER AVE Z4 GREENVILLE | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1413 | -120.957 |  | N/A | N/A | TBD | 1.6187 | 0 | 1.6187 | 0 | 0
35316201 | PLUCODIXIE-HOT SPRINGS RD Z5 GREENVILLE | Community Rebuild | 95F | ADER | Estimating | NV | Region 2 - North East | Greenville | PLUMAS | 40.1397 | -120.9389 |  | N/A | N/A | TBD | 0.68314 | 0 | 0.68314 | 0 | 0
35316278 | CWSP - ELK CREEK 1101 LR2002 PH 2.1-DC07 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.4868 | -122.5188 |  | v2 | 315 | Tier 2 | 2.5396 | 2.5396 | 0 | 0 | 0
35316561 | PSPS - COTTONWOOD 1102544790 PH 2.1 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3895 | -122.3067 |  | v2 | 123 | Tier 2 | 4.7434 | 0 | 4.7434 | 0 | 0
35316567 | PSPS - COTTONWOOD 11029026 PH2.1 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | v2 | 271 | Tier 2 | 2.6206 | 2.6206 | 0 | 0 | 0
35316569 | PSPS - COTTONWOOD 11029026 PH3.1 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3893 | -122.3434 |  | v2 | 271 | Tier 2 | 4.4525 | 4.4525 | 0 | 0 | 0
35317398 | CWSP REDBUD 1101 754544 PH 1.1 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0584 | -122.6925 |  | v2 | N/A | Tier 2 & 3 | 1.8322 | 1.8322 | 0 | 0 | 0
35317399 | CWSP - REDBUD 1101323962 PH 2.1 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | v2 | 423 | Tier 2 & 3 | 1.0938 | 0 | 0 | 1.0938 | 0
35317887 | CWSP - JESSUP 1102 LR1550 PH 3.1 | Base SH | 08W | ADER | Estimating | NV | Region 2 - North East | Anderson | SHASTA | 40.4377 | -122.3878 |  | v2 | 389 | Tier 2 | 0.8053 | 0.8053 | 0 | 0 | 0
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | Fire Rebuild | 08W | FICL | Post-Construction | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1291 | -122.1378 |  | v2 | 2435 | Tier 3 | 0.1803 | 0.1803 | 0 | 0 | 0
35318074 | FRRB-PT MORETTI 1101 12122 P1S2 640SWANV | Fire Rebuild | 08W | DOCC | Post-Construction | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.072 | -122.2298 |  | v2 | 2246 | Tier 2 | 0.3 | 0.3 | 0 | 0 | 0
35320312 | CWSP LINCOLN 1104 LR2070 PH 2.1 | Base SH | 08W | MAPP | Post-Construction | SI | Region 2 - North East | Lincoln | PLACER | 38.9507 | -121.219 |  | v2 | 568 | Tier 2 | 2.0256 | 2.0256 | 0 | 0 | 0
35320333 | PSPS - VACAVILLE 1108 LR8762 PH 1.1 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.344 | -122.0247 |  | v2 | 64 | Tier 2 | 3.0309 | 0 | 3.0309 | 0 | 0
35320334 | PSPS - VACAVILLE 1108 LR8762 PH 2.0 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3618 | -122.0219 |  | v2 | 64 | Tier 2 | 1.553 | 0 | 1.553 | 0 | 0
35320335 | PSPS - VACAVILLE 1108 LR8762 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | SA | Region 2 - North East | Vacaville | SOLANO | 38.3593 | -122.0012 |  | v2 | 1247 | Tier 2 | 0.44508 | 0 | 0 | 0.44508 | 0
35320336 | PSPS - VACAVILLE 1108 LR38316 PH 1.1 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4365 | -122.0527 |  | v2 | 122 | Tier 2 | 1.4021 | 1.4021 | 0 | 0 | 0
35320339 | PSPS - VACAVILLE 1108 LR38316 PH 2.1 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4168 | -122.0381 |  | v2 | 122 | Tier 2 | 0.77462 | 0.77462 | 0 | 0 | 0
35320440 | PSPS - VACAVILLE 1111 CB PH 1.1 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3783 | -122.0044 |  | v2 | 500 | Tier 2 | 2.5508 | 1.7053 | 0.84545 | 0 | 0
35320441 | PSPS - VACAVILLE 1111 LR13652 PH 1.1 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3933 | -122.0146 |  | v2 | 190 | Tier 2 | 2.3703 | 1.918 | 0.45227 | 0 | 0
35320442 | PSPS - JAMESON 1102 LR65516 1.1 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2515 | -122.161 |  | v2 | 739 | Tier 2 | 0.70909 | 0.058712 | 0.65038 | 0 | 0
35320447 | CWSP - HORSESHOE 1101 LR50140 PH 1.1 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Granite Bay | PLACER | 38.782 | -121.1456 |  | v2 | 661 | Tier 2 | 0.87633 | 0.87633 | 0 | 0 | 0
35320449 | CWSP LINCOLN 1104 51756 & 275986 PH 1.1 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Lincoln | PLACER | 38.9755 | -121.2772 |  | v2 | 185 | Tier 2 | 2.7277 | 2.7277 | 0 | 0 | 0
35320450 | CWSP - LINCOLN 1104 LR685276 PH 1.1 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Lincoln | PLACER | 39.0041 | -121.2605 |  | v2 | 230 | Tier 2 | 2.2078 | 0 | 2.2078 | 0 | 0
35320460 | PSPS - JAMESON 1105 LR466348 PH 1.1 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.3063 | -122.1288 |  | v2 | 393 | Tier 2 | 1.5277 | 1.5277 | 0 | 0 | 0
35320461 | PSPS - JAMESON 1105 LR466348 PH 2.1 | Base SH | 08W | MAPP | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.299 | -122.1519 |  | v2 | 393 | Tier 2 | 1.0729 | 0 | 1.0729 | 0 | 0
35320462 | PSPS - JAMESON 1105371694 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2642 | -122.1295 |  | v2 | 1848 | Tier 2 | 0.28826 | 0.28826 | 0 | 0 | 0
35320463 | PSPS - JAMESON 1105913400 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.284 | -122.1279 |  | v2 | 419 | Tier 2 | 1.5386 | 1.5386 | 0 | 0 | 0
35320464 | PSPS - PANORAMA 1101 CB PH 1.1 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4267 | -122.2656 |  | v2 | 1038 | Tier 2 | 0.22292 | 0.22292 | 0 | 0 | 0
35321894 | FRRB-PT MORETTI 1101 12122 PH1 SM4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | CC | Region 4 - Central Coast | Davenport | SANTA CRUZ | 37.0773 | -122.2434 |  | v2 | 2199 | Tier 2 | 0.10985 | 0 | 0 | 0.10985 | 0
35325589 | CWSP FLINT 1101 750 PH 1.2 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.8537 | -121.0803 |  | v2 | 152 | Tier 2 | 0.57178 | 0 | 0.57178 | 0 | 0
35325590 | CWSP FLINT 1101 750 PH 1.3 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.8575 | -121.0758 |  | v2 | 152 | Tier 2 | 2.296 | 0 | 2.296 | 0 | 0
35326790 | PSPS - FLINT1101 CB & 40666 PH1.2 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.8934 | -121.0677 |  | v2 | 2980 | Tier 2 | 0.1322 | 0.1322 | 0 | 0 | 0
35329008 | PSPS CLARK ROAD 1102 CB PH 1.2 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6413 | -121.6413 |  | v2 | 268 | Tier 2 | 0.39602 | 0.39602 | 0 | 0 | 0
35329009 | PSPS CLARK ROAD 1102 LR81296 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.655 | -121.5839 |  | v2 | 698 | Tier 2 | 0.70795 | 0.70795 | 0 | 0 | 0
35329010 | PSPS CLARK ROAD 1102 LR81296 PH 1.3 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6564 | -121.5838 |  | v2 | 698 | Tier 2 | 2.336 | 2.336 | 0 | 0 | 0
35329011 | PSPS CLARK ROAD 1102 LR81296 PH 1.4 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6668 | -121.5824 |  | v2 | 698 | Tier 2 | 1.5634 | 1.5634 | 0 | 0 | 0
35329012 | URE PSPS CLARK ROAD 1102 LR514690 PH 2.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Paradise | BUTTE | 39.6908 | -121.5733 |  | v2 | 1703 | Tier 2 | 1.55 | 0 | 1.55 | 0 | 0
35329013 | PSPS CLARK ROAD 1102 LR514690 PH 2.3 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Paradise | BUTTE | 39.6805 | -121.5693 |  | v2 | 1703 | Tier 2 | 1.3754 | 1.3754 | 0 | 0 | 0
35329014 | PSPS CLARK ROAD 1102 LR514690 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6666 | -121.5712 |  | v2 | 1033 | Tier 2 | 2.7237 | 2.7237 | 0 | 0 | 0
35329016 | PSPS CLARK ROAD 1102 LR47006 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Paradise | BUTTE | 39.709 | -121.5757 |  | v2 | 1535 | Tier 2 | 3.4301 | 0 | 3.4301 | 0 | 0
35329472 | CWSP - REDBUD 1101 LR454 PH 1.2 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0748 | -122.6503 |  | v2 | 312 | Tier 3 | 2.6585 | 0 | 2.6585 | 0 | 0
35329473 | CWSP - REDBUD 1101 LR454 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0654 | -122.6333 |  | v2 | 312 | Tier 3 | 4.761 | 0 | 4.761 | 0 | 0
35329474 | CWSP REDBUD 1101 754544 PH 1.2 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0932 | -122.6804 |  | v2 | N/A | Tier 2 & 3 | 0.1375 | 0.1375 | 0 | 0 | 0
35330211 | CWSP - REDBUD 1101323962 PH 2.2 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.5858 |  | v2 | 423 | Tier 2 & 3 | 1.8019 | 0 | 1.8019 | 0 | 0
35330213 | CWSP - REDBUD 1101323962 PH 2.3 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.5887 |  | v2 | 423 | Tier 2 & 3 | 5.4256 | 0 | 5.4256 | 0 | 0
35330215 | CWSP - REDBUD 1101323962 PH 2.4 | Base SH | 08W | UNSC | Ready for Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0669 | -122.5993 |  | v2 | 423 | Tier 2 & 3 | 2.7998 | 0 | 2.7998 | 0 | 0
35330216 | CWSP - REDBUD 1101323962 PH 2.5 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0696 | -122.585 |  | v2 | 423 | Tier 2 & 3 | 1.2557 | 0 | 1.2557 | 0 | 0
35330217 | CWSP - REDBUD 1101323962 PH 2.6 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0506 | -122.5833 |  | v2 | 423 | Tier 2 & 3 | 0.30966 | 0 | 0.30966 | 0 | 0
35330244 | CWSP REDBUD 1101 708166 PH 1.2 | Base SH | 08W | MAPP | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0531 | -122.6813 |  | v2 | 345 | Tier 2 & 3 | 0.46723 | 0.46723 | 0 | 0 | 0
35330245 | CWSP REDBUD 1101 708166 PH 1.3 | Base SH | 08W | FICL | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0541 | -122.6767 |  | v2 | 345 | Tier 2 & 3 | 0.077273 | 0.077273 | 0 | 0 | 0
35330246 | CWSP REDBUD 1101 708166 PH 1.4 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0448 | -122.6814 |  | v2 | 345 | Tier 2 & 3 | 0.78504 | 0.78504 | 0 | 0 | 0
35330247 | CWSP REDBUD 1101 708166 PH 1.5 | Base SH | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.04 | -122.6823 |  | v2 | 345 | Tier 2 & 3 | 0.82405 | 0.82405 | 0 | 0 | 0
35330248 | CWSP REDBUD 1101 708166 PH 1.6 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0296 | -122.6802 |  | v2 | 345 | Tier 2 & 3 | 2.5108 | 0 | 2.2108 | 0.3 | 0
35330249 | CWSP REDBUD 1101 708166 PH 1.7 | Base SH | 08W | CONS | In-Construction | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0287 | -122.6799 |  | v2 | 345 | Tier 2 & 3 | 2.6822 | 0 | 2.6822 | 0 | 0
35330812 | CWSP - ELK CREEK 1101 LR2002 PH 1.2-DC07 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.5561 | -122.5414 |  | v2 | 315 | Tier 2 | 2.3237 | 2.3237 | 0 | 0 | 0
35330815 | CWSP ANDERSON 1103 LR226050 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4792 | -122.2645 |  | v2 | 262 | Tier 2 | 0.46913 | 0.46913 | 0 | 0 | 0
35331305 | CWSP ANDERSON 1103 LR1600 PH2.4 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4699 | -122.2473 |  | v2 | 143 | Tier 2 | 0.50417 | 0.50417 | 0 | 0 | 0
35331306 | PSPS WYANDOTTE 1110 LR980944 PH1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5178 | -121.4854 |  | v2 | 976 | Tier 2 | 1.6879 | 0 | 1.6879 | 0 | 0
35331307 | PSPS WYANDOTTE 1110 LR980944 PH1.3 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5261 | -121.4815 |  | v2 | 976 | Tier 2 | 2.1913 | 0 | 2.1913 | 0 | 0
35332213 | PSPS COTTONWOOD 1102 LR544790 PH 2.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3892 | -122.3258 |  | v2 | 123 | Tier 2 | 2.5496 | 0 | 2.5496 | 0 | 0
35332214 | PSPS COTTONWOOD 1102 LR9026 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3899 | -122.3499 |  | v2 | 271 | Tier 2 | 4.307 | 4.307 | 0 | 0 | 0
35332215 | PSPS COTTONWOOD 1102 LR9026 PH 2.2 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4149 | -122.3421 |  | v2 | 271 | Tier 2 | 2.1809 | 2.1809 | 0 | 0 | 0
35332216 | PSPS COTTONWOOD 1102 LR9026 PH 2.3 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.4042 | -122.3264 |  | v2 | 271 | Tier 2 | 1.325 | 1.325 | 0 | 0 | 0
35332217 | PSPS COTTONWOOD 1102 LR9026 PH 3.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3886 | -122.3831 |  | v2 | 271 | Tier 2 | 2.6513 | 2.6513 | 0 | 0 | 0
35332218 | PSPS COTTONWOOD 1102 LR544790 PH 1.2 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Cottonwood | SHASTA | 40.3986 | -122.3143 |  | v2 | 123 | Tier 2 | 3.2642 | 3.2642 | 0 | 0 | 0
35332360 | CWSP - ELK CREEK 1101 LR2002 PH 2.2-DC07 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Willows | GLENN | 39.456 | -122.5138 |  | v2 | 315 | Tier 2 | 2.7987 | 2.2564 | 0.54223 | 0 | 0
35332362 | CWSP - ELK CREEK 1101 LR2002 PH 2.4-DC07 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.4286 | -122.5052 |  | v2 | 315 | Tier 2 | 3.0616 | 3.0616 | 0 | 0 | 0
35332363 | CWSP - ELK CREEK 1101 LR2002 PH 2.5-DC07 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.4073 | -122.5471 |  | v2 | 315 | Tier 2 | 1.2686 | 1.2686 | 0 | 0 | 0
35332364 | CWSP - ELK CREEK 1101 LR2002 PH 2.6-DC07 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Elk Creek | GLENN | 39.3944 | -122.5518 |  | v2 | 315 | Tier 2 | 1.0562 | 1.0562 | 0 | 0 | 0
35332866 | PSPS - JESSUP 1103 LR348657 PH 1.4 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4668 | -122.3357 |  | v2 | 590 | Tier 2 | 0.7411 | 0.7411 | 0 | 0 | 0
35332868 | PSPS - CURTIS 1701 CB PH 1.2 | Base SH | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9803 | -120.337 |  | v2 | 1166 | Tier 2 | 1.8716 | 0 | 1.8716 | 0 | 0
35332870 | PSPS - CURTIS 1701 CB PH 1.3 | Base SH | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9737 | -120.3714 |  | v2 | 1166 | Tier 2 | 0.7411 | 0 | 0.7411 | 0 | 0
35332872 | CWSP - LINCOLN 1104 LR997576 PH 1.3 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Sheridan | PLACER | 39.0337 | -121.3086 |  | v2 | N/A | Tier 2 | 0.20777 | 0.20777 | 0 | 0 | 0
35332958 | CWSP LINCOLN 1104 LR2070 PH 2.2 | Base SH | 08W | APPR | Estimating | SI | Region 2 - North East | Lincoln | PLACER | 38.9431 | -121.219 |  | v2 | 568 | Tier 2 | 2.2254 | 2.2254 | 0 | 0 | 0
35333501 | CWSP - BELL 1108 LR2202 PH 2.3 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.9851 | -121.1296 |  | v2 | 118 | Tier 2 | 1.6025 | 0 | 1.6025 | 0 | 0
35333503 | CWSP - BELL 1108 LR2202 PH 2.5 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.9959 | -121.1355 |  | v2 | 118 | Tier 2 | 0.31326 | 0 | 0.31326 | 0 | 0
35333504 | CWSP - BELL 1108 LR2202 PH 2.6 | Base SH | 08W | CONS | In-Construction | SI | Region 2 - North East | Auburn | PLACER | 38.9992 | -121.1363 |  | v2 | 118 | Tier 2 | 0.56212 | 0 | 0.56212 | 0 | 0
35334229 | PSPS - CORNING 1102 LR53184 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Covelo | TEHAMA | 39.8493 | -122.6179 |  | v2 | 413 | Tier 2 | 2.986 | 2.986 | 0 | 0 | 0
35334232 | CWSP - BELL 1108 LR2202 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Auburn | PLACER | 38.9855 | -121.1087 |  | v2 | 118 | Tier 2 | 1.0227 | 0 | 0 | 1.0227 | 0
35334234 | CWSP - BELL 1108 LR2202 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Auburn | PLACER | 38.9781 | -121.1088 |  | v2 | 118 | Tier 2 | 2.2405 | 0 | 0 | 2.2405 | 0
35334407 | FRRB - WILLOW CREEK 11032936 - UG TL4 | Fire Rebuild | 08W | DOCC | Post-Construction | HB | Region 1 - North Coast | Burnt Ranch | TRINITY | 40.7875 | -123.4468 |  | v2 | 1474 | Tier 2 | 0.22538 | 0.22538 | 0 | 0 | 0
35334541 | FRRB-BIG BASIN 1102 12758 P1S2 CYPRESS | Fire Rebuild | 08W | FICL | Post-Construction | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1443 | -122.1579 |  | v2 | 2358 | Tier 3 | 0.13617 | 0.13617 | 0 | 0 | 0
35334750 | PSPS - VACAVILLE 1108 LR8762 PH 1.2 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3588 | -122.0245 |  | v2 | 64 | Tier 2 | 1.2367 | 1.2367 | 0 | 0 | 0
35334752 | PSPS - VACAVILLE 1108 LR8762 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3655 | -122.0233 |  | v2 | 64 | Tier 2 | 1.8445 | 1.8445 | 0 | 0 | 0
35334753 | PSPS - VACAVILLE 1108 LR38316 PH 1.2 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4313 | -122.05 |  | v2 | 122 | Tier 2 | 1.7612 | 1.7612 | 0 | 0 | 0
35334754 | PSPS - VACAVILLE 1108 LR38316 PH 2.2 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4024 | -122.0318 |  | v2 | 122 | Tier 2 | 3.8655 | 3.8 | 0.06553 | 0 | 0
35334755 | PSPS - VACAVILLE 1108 LR38316 PH 2.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3911 | -122.0367 |  | v2 | 122 | Tier 2 | 1.0534 | 1.0371 | 0.016288 | 0 | 0
35335235 | PSPS - SILVERADO 2104708 | Base SH | 08W | PEND | Permitting/Dependency | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5192 | -122.4719 |  | v2 | 1648 | Tier 3 | 4.8312 | 0 | 0 | 4.8312 | 0
35335286 | PSPS - TEJON 1102 LR2455 PH 1.2 | Base SH | 08W | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.8542 | -118.893 |  | v2 | 642 | Tier 2 | 5.2104 | 0 | 0 | 5.2104 | 0
35335287 | PSPS - TEJON 1102 LR2455 PH 1.3 | Base SH | 08W | CONS | In-Construction | KE | Region 5 - Central Valley | Lebec | KERN | 34.8466 | -118.8987 |  | v2 | 642 | Tier 2 | 2.1282 | 0 | 2.1282 | 0 | 0
35335290 | PSPS - VACAVILLE 1111 LR13652 PH 1.2 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3898 | -122.0001 |  | v2 | 190 | Tier 2 | 2.5305 | 1.4413 | 1.0892 | 0 | 0
35335291 | PSPS - VACAVILLE 1111 CB PH 1.2 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3771 | -121.9968 |  | v2 | 500 | Tier 2 | 1.0614 | 0 | 1.0614 | 0 | 0
35335292 | PSPS - VACAVILLE 1111 CB PH 1.3 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3772 | -121.9918 |  | v2 | 500 | Tier 2 | 1.858 | 0 | 1.858 | 0 | 0
35335293 | PSPS - VACAVILLE 1111 CB PH 1.4 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.3663 | -121.9916 |  | v2 | 500 | Tier 2 | 2.3941 | 0 | 2.3941 | 0 | 0
35337008 | CWSP - JESSUP 1102 LR1550 PH 1.2 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4409 | -122.3061 |  | v2 | 389 | Tier 2 | 1.5167 | 1.2125 | 0.30417 | 0 | 0
35337010 | CWSP - JESSUP 1102 LR1550 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4416 | -122.3258 |  | v2 | 389 | Tier 2 | 3.4553 | 3.4553 | 0 | 0 | 0
35337011 | CWSP - JESSUP 1102 LR1550 PH 1.4 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4406 | -122.3414 |  | v2 | 389 | Tier 2 | 2.9191 | 2.9191 | 0 | 0 | 0
35337012 | CWSP - JESSUP 1102 LR1550 PH 1.5 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.443 | -122.3663 |  | v2 | 389 | Tier 2 | 4.1544 | 4.1544 | 0 | 0 | 0
35337014 | CWSP - JAMESON 1105 LR9472 PH 1.3 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2525 | -122.144 |  | v2 | 724 | Tier 2 | 0.031818 | 0.031818 | 0 | 0 | 0
35337015 | CWSP - JAMESON 1105 LR9472 PH 1.4 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2533 | -122.1356 |  | v2 | 724 | Tier 2 | 0.4572 | 0.4572 | 0 | 0 | 0
35337151 | EP WASSAMA STATE PARK AHWAHNEE | Other | 10J | CLSD | Closed | YO | Region 5 - Central Valley | Ahwahnee | MADERA | 37.3745 | -119.7218 |  | v2 | 421 | Tier 2 | 0.11837 | 0.11837 | 0 | 0 | 0
35337163 | CWSP LINCOLN 1104 51756 & 275986 PH 1.2 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Lincoln | PLACER | 38.97 | -121.2606 |  | v2 | 185 | Tier 2 | 0.89811 | 0.89811 | 0 | 0 | 0
35337306 | CWSP STANISLAUS 1702 CB PH 1.5 | Base SH | 08W | CONS | In-Construction | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1677 | -120.3831 |  | v2 | 235 | Tier 2 & 3 | 2.3008 | 2.3008 | 0 | 0 | 0
35338384 | CWSP - STANISLAUS 1701 CB PH1.6 | Base SH | 08W | CONS | In-Construction | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1735 | -120.3833 |  | v2 | 56 | Tier 2 & 3 | 1.5968 | 1.5968 | 0 | 0 | 0
35338402 | PSPS - PANORAMA 1101 CB PH 1.2 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4214 | -122.2578 |  | v2 | 1038 | Tier 2 | 1.4112 | 1.4112 | 0 | 0 | 0
35338404 | PSPS - JAMESON 1105 LR466348 PH 1.2 | Base SH | 08W | ESTS | Estimating | SA | Region 2 - North East | Fairfield | SOLANO | 38.3141 | -122.1263 |  | v2 | 393 | Tier 2 | 1.5994 | 1.5994 | 0 | 0 | 0
35338405 | PSPS - JAMESON 1105 LR466348 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2972 | -122.1262 |  | v2 | 393 | Tier 2 | 2.147 | 2.147 | 0 | 0 | 0
35338406 | PSPS - JAMESON 1105 LR466348 PH 1.4 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2877 | -122.1043 |  | v2 | 393 | Tier 2 | 1.2985 | 0 | 1.2985 | 0 | 0
35338407 | PSPS - JAMESON 1105 LR466348 PH 1.5 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.3039 | -122.0964 |  | v2 | 393 | Tier 2 | 1.3886 | 0 | 1.3886 | 0 | 0
35338408 | PSPS - JAMESON 1105 LR466348 PH 1.6 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.3148 | -122.0962 |  | v2 | 393 | Tier 2 | 0.90985 | 0 | 0.90985 | 0 | 0
35338409 | PSPS - JAMESON 1105 LR466348 PH 2.2 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2968 | -122.1356 |  | v2 | 393 | Tier 2 | 2.5402 | 2.5402 | 0 | 0 | 0
35338410 | PSPS - JAMESON 1105 LR466348 PH 2.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2925 | -122.1292 |  | v2 | 393 | Tier 2 | 2.0521 | 2.0521 | 0 | 0 | 0
35339282 | CWSP - JESSUP 1102 LR1550 PH 2.2 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4516 | -122.3245 |  | v2 | 389 | Tier 2 | 0.52027 | 0.52027 | 0 | 0 | 0
35339283 | CWSP - JESSUP 1102 LR1550 PH 2.3 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | v2 | 389 | Tier 2 | 2.553 | 2.553 | 0 | 0 | 0
35339285 | CWSP - JESSUP 1102 LR1550 PH 2.4 | Base SH | 08W | FICL | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4359 | -122.3689 |  | v2 | 389 | Tier 2 | 1.3479 | 1.3479 | 0 | 0 | 0
35339286 | CWSP - JESSUP 1102 LR1550 PH 2.5 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4362 | -122.3535 |  | v2 | 389 | Tier 2 | 1.9854 | 1.9854 | 0 | 0 | 0
35339287 | CWSP - JESSUP 1102 LR1550 PH 3.2 | Base SH | 08W | APPR | Estimating | NV | Region 2 - North East | Anderson | SHASTA | 40.4427 | -122.3927 |  | v2 | 389 | Tier 2 | 1.068 | 1.068 | 0 | 0 | 0
35339288 | CWSP - JESSUP 1102 LR1550 PH 3.3 | Base SH | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Anderson | SHASTA | 40.4403 | -122.4075 |  | v2 | 389 | Tier 2 | 2.5028 | 2.5028 | 0 | 0 | 0
35339289 | CWSP - JESSUP 1102 LR1550 PH 3.4 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Anderson | SHASTA | 40.4493 | -122.4078 |  | v2 | 389 | Tier 2 | 1.1839 | 1.1839 | 0 | 0 | 0
35339293 | PSPS - JAMESON 1105 LR466348 PH 1.7 | Base SH | 08W | FICL | Post-Construction | NB | Region 2 - North East | Fairfield | SOLANO | 38.3158 | -122.1039 |  | v2 | 393 | Tier 2 | 1.2508 | 1.2508 | 0 | 0 | 0
35339665 | CWSP - HORSESHOE 1101 LR50140 PH 1.4 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Loomis | PLACER | 38.767 | -121.1634 |  | v2 | 661 | Tier 2 | 0.8072 | 0.8072 | 0 | 0 | 0
35340270 | PSPS - CORNING 1102 LR915324 PH 1.2 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Corning | TEHAMA | 39.918 | -122.4709 |  | v2 | 457 | Tier 2 | 2.3447 | 2.3447 | 0 | 0 | 0
35342143 | PSPS - JAMESON 1102 LR65516 1.2 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2645 | -122.1722 |  | v2 | 739 | Tier 2 | 3.2491 | 0 | 3.2491 | 0 | 0
35342144 | PSPS - JAMESON 1102 LR65516 1.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2553 | -122.1615 |  | v2 | 739 | Tier 2 | 2.2509 | 0 | 2.2509 | 0 | 0
35342145 | PSPS - JAMESON 1102 LR65516 1.4 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2565 | -122.1687 |  | v2 | 739 | Tier 2 | 0.18068 | 0.18068 | 0 | 0 | 0
35342146 | PSPS - JAMESON 1102 LR65516 1.5 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.262 | -122.1635 |  | v2 | 739 | Tier 2 | 1.6994 | 0 | 1.6994 | 0 | 0
35342147 | PSPS - JAMESON 1102 LR65516 1.6 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2706 | -122.167 |  | v2 | 739 | Tier 2 | 1.8259 | 0 | 1.8259 | 0 | 0
35342148 | PSPS - JAMESON 1102 LR65516 1.7 | Base SH | 08W | CONS | In-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2714 | -122.1672 |  | v2 | 739 | Tier 2 | 1.0377 | 0 | 1.0377 | 0 | 0
35342151 | PSPS - JAMESON 1102 LR65516 1.9 | Base SH | 08W | FICL | Post-Construction | SA | Region 2 - North East | Fairfield | SOLANO | 38.2491 | -122.1769 |  | v2 | 739 | Tier 2 | 0.077841 | 0.077841 | 0 | 0 | 0
35342335 | FRRB-BIG BASIN 1102 UG3 HWY 236 | Fire Rebuild | 08W | PEND | Permitting/Dependency | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1672 | -122.2131 |  | v2 | 2359 | Tier 3 | 2.1506 | 0 | 0 | 2.1506 | 0
35342336 | FRRB-BIG BASIN 1102 UG2 CAMPGROUND | Fire Rebuild | 08W | PEND | Permitting/Dependency | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1699 | -122.2026 |  | v2 | 2359 | Tier 3 | 2.9763 | 0 | 0 | 2.9763 | 0
35342337 | FRRB-BIG BASIN 1102 UG4 BBSP PUMPSTN | Fire Rebuild | 08W | PEND | Permitting/Dependency | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1657 | -122.2231 |  | v2 | 2359 | Tier 3 | 0.52008 | 0 | 0 | 0.52008 | 0
35342338 | FRRB-BIG BASIN 1102 UG5 LITTLEBASIN | Fire Rebuild | 08W | DOCC | Post-Construction | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1629 | -122.1903 |  | v2 | 2359 | Tier 3 | 1.447 | 0 | 1.447 | 0 | 0
35342339 | FRRB - BIG BASIN 1102 UG6 BB VINEYARD | Fire Rebuild | 08W | FICL | Post-Construction | CC | Region 4 - Central Coast | Boulder Creek | SANTA CRUZ | 37.1837 | -122.1598 |  | v2 | 2070 | Tier 3 | 0.14489 | 0.14489 | 0 | 0 | 0
35343394 | PSPS - WYANDOTTE 1110 LR980944 PH1.6 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5152 | -121.4932 |  | v2 | 976 | Tier 2 | 1.2506 | 0.97027 | 0.2803 | 0 | 0
35343395 | PSPS - WYANDOTTE 1110 LR980944 PH1.7 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5168 | -121.4943 |  | v2 | 976 | Tier 2 | 1.9903 | 1.9903 | 0 | 0 | 0
35343396 | PSPS - WYANDOTTE 1110 LR980944 PH1.8 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.52 | -121.4943 |  | v2 | 976 | Tier 2 | 1.0896 | 1.0896 | 0 | 0 | 0
35343397 | PSPS - WYANDOTTE 1110 LR980944 PH1.9 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.5082 | -121.5038 |  | v2 | 976 | Tier 2 | 0.64451 | 0.39394 | 0.25057 | 0 | 0
35343741 | PSPS - DUNBAR 1101 440 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | SO | Region 1 - North Coast | Sonoma | SONOMA | 38.3371 | -122.4929 |  | v2 | 1827 | Tier 2 & 3 | 0.70795 | 0 | 0 | 0.70795 | 0
35349244 | CWSP - LINCOLN 1104 LR685276 PH 1.5 | Base SH | 08W | FICL | Post-Construction | SI | Region 2 - North East | Lincoln | PLACER | 38.9873 | -121.2542 |  | v2 | 230 | Tier 2 | 0.62879 | 0.62879 | 0 | 0 | 0
35350039 | FRRB - BIG BEND 1102 884340 - B4 SM2 | Fire Rebuild | 08W | CLSD | Closed | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6626 | -121.4006 |  | v3 | 267 | Tier 3 | 0.096212 | 0.096212 | 0 | 0 | 0
35350519 | PLUCODIXIE-ALTA CAMP Z6 GREENVILLE | Community Rebuild | 95F | PEND | Permitting/Dependency | NV | Region 2 - North East | Greenville | PLUMAS | 40.1415 | -120.9483 |  | N/A | N/A | TBD | 0.47348 | 0 | 0.47348 | 0 | 0
35350582 | PLUCODIXIE-HIDEAWAY Z7 GREENVILLE | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1415 | -120.9483 |  | N/A | N/A | TBD | 0.37879 | 0 | 0.37879 | 0 | 0
35362666 | CWSP - CLAYTON 2212614950 | Targeted UG | 3UG | PEND | Permitting/Dependency | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.9331 | -121.942 |  | v3 | 100 | Tier 2 & 3 | 0.65 | 0 | 0 | 0.65 | 0
35363559 | CWSP - SYCAMORE CREEK 11112268 PH 1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.9035 | -121.742 |  | v3 | 57 | Tier 3 | 3.26 | 0 | 0 | 3.26 | 0
35363720 | CWSP - SYCAMORE CREEK 11112268 PH 2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.9339 | -121.7255 |  | v3 | 57 | Tier 3 | 2.7699 | 0 | 0 | 2.7699 | 0
35364784 | CWSP - SYCAMORE CREEK 11112268 PH 3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.9339 | -121.7255 |  | v3 | 57 | Tier 3 | 3.0098 | 0 | 0 | 3.0098 | 0
35365064 | CWSP - BONNIE NOOK 1101CB PH 2.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Dutch Flat | PLACER | 39.1898 | -120.85 |  | v3 | 20 | Tier 3 | 4.21 | 0 | 0 | 0 | 4.21
35367335 | CWSP - BONNIE NOOK 1101CB PH 1.1 | Targeted UG | 3UG | CONS | In-Construction | SI | Region 2 - North East | Alta | PLACER | 39.2116 | -120.8195 |  | v3 | 20 | Tier 3 | 5.6767 | 0 | 5.6767 | 0 | 0
35367414 | CWSP - APPLE HILL 21027502 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6829 | -120.6626 |  | v3 | 63 | Tier 2 & 3 | 4.1449 | 0 | 0 | 4.1449 | 0
35367468 | CWSP - EL DORADO PH 2101-668674 PH 1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7928 | -120.6194 |  | v3 | 81 | Tier 3 | 2.9 | 0 | 0 | 0 | 2.9
35367478 | CWSP - FORESTHILL 1101-50486 PH 1.1 | Targeted UG | 3UG | CONS | In-Construction | SI | Region 2 - North East | Foresthill | PLACER | 39.0016 | -120.8905 |  | v3 | 114 | Tier 3 | 2.425 | 0 | 2.425 | 0 | 0
35367504 | CWSP - ORO FINO 110276008 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8877 | -121.6655 |  | v3 | 61 | Tier 3 | 4.3701 | 0 | 0 | 4.3701 | 0
35367507 | CWSP - ORO FINO 1102CB | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Magalia | BUTTE | 39.8718 | -121.6107 |  | v3 | 17 | Tier 3 | 0.876 | 0 | 0 | 0.876 | 0
35367516 | CWSP - SILVERADO 210478268 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5613 | -122.4612 |  | v3 | 101 | Tier 3 | 1.358 | 0 | 0 | 0 | 1.358
35367520 | CWSP - STANISLAUS 1702 LR1888 PH1.1 | Targeted UG | 3UG | CONS | In-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2367 | -120.3629 |  | v3 | 379 | Tier 3 | 2.0172 | 2.0172 | 0 | 0 | 0
35367524 | CWSP - WEST POINT 1101 LR4706 PH 1.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4678 | -120.5277 |  | v3 | 107 | Tier 3 | 1.4 | 0 | 0 | 1.4 | 0
35372259 | CWSP - PINE GROVE 1101CB | Targeted UG | 3UG | ADER | Estimating | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.4129 | -120.6605 |  | v3 | 6 | Tier 2 | 2.84 | 0 | 0 | 0 | 2.84
35372461 | CWSP - TIGER CREEK 201 CB & 320746 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4492 | -120.492 |  | v3 | 8 | Tier 2 & 3 | 4.3384 | 0 | 0 | 0 | 4.3384
35372462 | CWSP - ELECTRA 1101 LR7104 PH 1.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.4053 | -120.6461 |  | v3 | 62 | Tier 2 | 4.6718 | 0 | 0 | 4.6718 | 0
35372464 | CWSP - ANTLER 11011520 PH 1.1 | Targeted UG | 3UG | CONS | In-Construction | NV | Region 2 - North East | Lakehead | SHASTA | 40.8994 | -122.3862 |  | v3 | 91 | Tier 2 | 3.712 | 0 | 3.712 | 0 | 0
35372465 | CWSP - ANTLER 11011384 PH 1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Lakehead | SHASTA | 40.8936 | -122.3819 |  | v3 | 11 | Tier 2 | 4.695 | 0 | 0 | 4.695 | 0
35373051 | FRRB KANAKA 1101CB - K2 SM3 (DC07) | Fire Rebuild | 08W | CLSD | Closed | NV | Region 2 - North East | Oroville | BUTTE | 39.574 | -121.3077 |  | v2 | 1480 | Tier 3 | 0.12424 | 0.12424 | 0 | 0 | 0
35373530 | CWSP - APPLE HILL 21027502 PH 2.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7137 | -120.632 |  | v3 | 63 | Tier 3 | 2.0428 | 0 | 0 | 2.0428 | 0
35373532 | CWSP - APPLE HILL 21027502 PH 3.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7137 | -120.632 |  | v3 | 63 | Tier 3 | 3.2233 | 0 | 0 | 3.2233 | 0
35373533 | CWSP - FORESTHILL 1101-50486 PH 2 | Targeted UG | 3UG | CONS | In-Construction | SI | Region 2 - North East | Foresthill | PLACER | 38.9918 | -120.883 |  | v3 | 114 | Tier 3 | 2.6201 | 0 | 2.6201 | 0 | 0
35373597 | CWSP - CALISTOGA 110143924 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5951 | -122.6024 |  | v3 | 105 | Tier 3 | 2.55 | 0 | 0 | 2.55 | 0
35373620 | CWSP - EL DORADO PH 2101-668674 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7646 | -120.5783 |  | v3 | 81 | Tier 3 | 0.65 | 0 | 0 | 0 | 0.65
35373628 | CWSP - ORO FINO 110276008 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8877 | -121.666 |  | v3 | 61 | Tier 3 | 0.9 | 0 | 0 | 0.9 | 0
35373704 | CWSP - SILVERADO 210478268 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5653 | -122.4415 |  | v3 | 101 | Tier 3 | 3.648 | 0 | 0 | 3.648 | 0
35373708 | CWSP - ANTLER 11011384 PH 2 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Lakehead | SHASTA | 40.8928 | -122.3816 |  | v3 | 11 | Tier 2 | 3.73 | 0 | 0 | 3.73 | 0
35374059 | CWSP - ELECTRA 1101L1697 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.3794 | -120.6379 |  | v3 | 118 | Tier 2 | 2.11 | 0 | 0 | 2.11 | 0
35374200 | CWSP - NOTRE DAME 11042028 PH 1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8389 | -121.702 |  | v3 | 37 | Tier 3 | 2.884 | 0 | 0 | 2.884 | 0
35374202 | CWSP - NOTRE DAME 11042028 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.839 | -121.7019 |  | v3 | 37 | Tier 3 | 1.072 | 0 | 0 | 0 | 1.072
35374204 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Alleghany | SIERRA | 39.4653 | -120.8447 |  | v3 | 41 | Tier 3 | 2.9799 | 0 | 0 | 2.9799 | 0
35374205 | CWSP - ALLEGHANY 1102CB SIERRA PH 2.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Alleghany | SIERRA | 39.4569 | -120.837 |  | v3 | 41 | Tier 3 | 2.01 | 0 | 0 | 2.01 | 0
35374206 | CWSP - ALLEGHANY 1102CB PH 3.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Nevada City | NEVADA | 39.4393 | -120.8173 |  | v3 | 41 | Tier 3 | 4.08 | 0 | 0 | 0 | 4.08
35374208 | CWSP - ALLEGHANY 1102CB NEVADA PH 4.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Nevada City | NEVADA | 39.4016 | -120.7873 |  | v3 | 41 | Tier 3 | 2.28 | 0 | 0 | 0 | 2.28
35374443 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Nevada City | NEVADA | 39.3652 | -120.7935 |  | v3 | 41 | Tier 3 | 2.458 | 0 | 0 | 2.458 | 0
35374559 | FRRB - MARIPOSA 21019400 ML-3 | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5087 | -119.8728 |  | v3 | 504 | Tier 2 & 3 | 3.9581 | 3.9581 | 0 | 0 | 0
35374563 | CWSP - BUCKS CREEK 1102 CB PH1.1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0144 | -121.2252 |  | v3 | 45 | Tier 2 | 3.7383 | 0 | 0 | 3.7383 | 0
35374564 | CWSP - BUCKS CREEK 1102 CB PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0721 | -121.1691 |  | v3 | 45 | Tier 2 | 1.8873 | 0 | 0 | 0 | 1.8873
35374566 | CWSP - BUCKS CREEK 1102CB - ROCK CREST | Targeted UG | 3UG | CONS | In-Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9272 | -121.3169 |  | v3 | 45 | Tier 2 | 0.22178 | 0 | 0.22178 | 0 | 0
35374567 | CWSP - BUCKS CREEK 1102CB - RODGERS FLAT | Targeted UG | 3UG | UNSC | Ready for Construction | NV | Region 2 - North East | Twain | PLUMAS | 39.9591 | -121.2804 |  | v3 | 45 | Tier 2 & 3 | 0.43996 | 0 | 0.43996 | 0 | 0
35374569 | CWSP - BUCKS CREEK 1102CB - BELDEN | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Twain | PLUMAS | 40.0055 | -121.249 |  | v3 | 45 | Tier 2 & 3 | 2.1807 | 0 | 0 | 2.1807 | 0
35374681 | FRRB - MARIPOSA 21019400 ML-2 | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5113 | -119.9076 |  | v3 | 126 | Tier 2 & 3 | 5.0826 | 5.0826 | 0 | 0 | 0
35374682 | FRRB - MARIPOSA 210110240 ML-1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.541 | -119.9184 |  | v3 | 504 | Tier 2 & 3 | 3.1559 | 0 | 0 | 3.1559 | 0
35374683 | FRRB - MARIPOSA 21019400 ML-4 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.513 | -119.8444 |  | v3 | 504 | Tier 2 & 3 | 1.3799 | 1.3799 | 0 | 0 | 0
35374684 | FRRB - MARIPOSA 210110170 ML-5 | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.517 | -119.8344 |  | v3 | 504 | Tier 2 & 3 | 1.4767 | 1.4767 | 0 | 0 | 0
35374685 | FRRB - MARIPOSA 210110240 TL-1 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.517 | -119.8344 |  | v3 | 126 | Tier 3 | 2.4203 | 0 | 2.4203 | 0 | 0
35374686 | FRRB - MARIPOSA 21019400 TL-2 | Fire Rebuild | 08W | FICL | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5268 | -119.904 |  | v3 | 504 | Tier 3 | 2.5994 | 2.5994 | 0 | 0 | 0
35374687 | FRRB - MARIPOSA 21019400 TL-3 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5083 | -119.8773 |  | v3 | 504 | Tier 2 | 0.87008 | 0 | 0.87008 | 0 | 0
35374862 | FRRB - MARIPOSA 21029590 TL-1 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5079 | -119.8466 |  | v3 | 714 | Tier 3 | 1.5746 | 1.5746 | 0 | 0 | 0
35374863 | FRRB - MARIPOSA 21019400 TL-4 INSTALL | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5016 | -119.8815 |  | v3 | 504 | Tier 2 | 0.45076 | 0 | 0.45076 | 0 | 0
35374864 | FRRB - MARIPOSA 21019400 TL-5 INSTALL | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5083 | -119.8773 |  | v3 | 137 | Tier 3 | 1.7504 | 1.7504 | 0 | 0 | 0
35374865 | FRRB - MARIPOSA 21019400 TL-6 INSTALL | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5363 | -119.833 |  | v3 | 504 | Tier 3 | 0.78883 | 0.78883 | 0 | 0 | 0
35374866 | FRRB - MARIPOSA 21019400 TL-7 | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5363 | -119.833 |  | v3 | 504 | Tier 3 | 0.44508 | 0.44508 | 0 | 0 | 0
35375449 | CWSP - PIKE CITY 1101CB PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | SIERRA | 39.4381 | -120.996 |  | v3 | 116 | Tier 3 | 10.86 | 0 | 0 | 10.86 | 0
35375450 | CWSP - PIKE CITY 1101CB PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.4544 | -121.0512 |  | v3 | 116 | Tier 3 | 10.66 | 0 | 0 | 10.66 | 0
35375452 | CWSP - PIKE CITY 11011720 PH 1.1 | Targeted UG | 3UG | ADER | Estimating | SI | Region 2 - North East | Camptonville | YUBA | 39.4553 | -121.0529 |  | v3 | 52 | Tier 3 | 3.1 | 0 | 0 | 0 | 3.1
35375721 | FRRB - MARIPOSA 21019400 ML-6 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5139 | -119.8384 |  | v3 | 137 | Tier 3 | 0.95928 | 0.95928 | 0 | 0 | 0
35376303 | FRRB - MARIPOSA 21019400 TL-9 INSTALL | Fire Rebuild | 08W | DOCC | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5268 | -119.904 |  | v3 | 504 | Tier 3 | 0.27348 | 0.27348 | 0 | 0 | 0
35376304 | FRRB - MARIPOSA 21019400 TL-8 INSTALL | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5136 | -119.8722 |  | v3 | 504 | Tier 3 | 0.52822 | 0 | 0.52822 | 0 | 0
35376305 | FRRB - MARIPOSA 210110170 TL-10 | Fire Rebuild | 08W | FICL | Post-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5083 | -119.8773 |  | v3 | 137 | Tier 3 | 0.53068 | 0.53068 | 0 | 0 | 0
35376306 | FRRB - MARIPOSA 21019400 TL-11 | Fire Rebuild | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.5136 | -119.8722 |  | v3 | 504 | Tier 2 & 3 | 0.36023 | 0 | 0.36023 | 0 | 0
35376558 | CWSP - SILVERADO 2105658898 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5208 | -122.539 |  | v3 | 105 | Tier 3 | 2.78 | 0 | 0 | 2.78 | 0
35376559 | CWSP - SILVERADO 2105658898 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5253 | -122.551 |  | v3 | 105 | Tier 3 | 1.42 | 0 | 0 | 1.42 | 0
35376890 | CWSP- ELECTRA 11017104 PH 2.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.364 | -120.6467 |  | v3 | 62 | Tier 2 | 2.875 | 0 | 2.875 | 0 | 0
35376891 | CWSP - SILVERADO 2104646776 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5753 | -122.4443 |  | v3 | 14 | Tier 3 | 2.235 | 0 | 0 | 2.235 | 0
35377520 | CWSP - MIDDLETOWN 1101171414 PH 1.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Kelseyville | LAKE | 38.8481 | -122.7562 |  | v3 | 38 | Tier 3 | 2.4299 | 0 | 0 | 2.4299 | 0
35377525 | CWSP - PIKE CITY 1101CB PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.4756 | -121.0425 |  | v3 | 116 | Tier 3 | 1.6201 | 0 | 0 | 0 | 1.6201
35378609 | PLUCODIXIE-COMMERCIAL-Z2 GREENVILLE | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1407 | -120.9513 |  | N/A | N/A | TBD | 0.58466 | 0.062879 | 0.52178 | 0 | 0
35380365 | PSPS - CORNING 1102 LR53184 PH 1.5 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Corning | TEHAMA | 39.9089 | -122.4786 |  | v2 | 413 | Tier 2 | 2.6271 | 2.6271 | 0 | 0 | 0
35380368 | PSPS - CORNING 1102 LR53184 PH 1.7 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.9108 | -122.493 |  | v2 | 413 | Tier 2 | 2.3733 | 0 | 2.3733 | 0 | 0
35380369 | PSPS - CORNING 1102 LR53184 PH 1.8 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.8928 | -122.5171 |  | v2 | 413 | Tier 2 | 1.9886 | 0 | 1.9886 | 0 | 0
35380370 | PSPS - CORNING 1102 LR53184 PH 1.9 | Base SH | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Red Bluff | TEHAMA | 39.887 | -122.5361 |  | v2 | 413 | Tier 2 | 3.6866 | 0 | 3.6866 | 0 | 0
35380371 | PSPS - CORNING 1102 LR53184 PH 1.10 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Corning | TEHAMA | 39.8773 | -122.5512 |  | v2 | 413 | Tier 2 | 2.0348 | 2.0348 | 0 | 0 | 0
35380372 | PSPS - CORNING 1102 LR53184 PH 1.11 | Base SH | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Covelo | TEHAMA | 39.8634 | -122.5862 |  | v2 | 413 | Tier 2 | 1.5839 | 1.5839 | 0 | 0 | 0
35380373 | PSPS - CORNING 1102 LR53184 PH 1.12 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Covelo | TEHAMA | 39.8466 | -122.59 |  | v2 | 413 | Tier 2 | 1.5989 | 1.5989 | 0 | 0 | 0
35380376 | PSPS - CORNING 1102 LR53184 PH 1.15 | Base SH | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Covelo | TEHAMA | 39.846 | -122.5891 |  | v2 | 413 | Tier 2 | 2.515 | 2.515 | 0 | 0 | 0
35383305 | CWSP - WEST POINT 11014706 PH 2.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4841 | -120.5202 |  | v3 | 107 | Tier 3 | 0.57 | 0 | 0 | 0.57 | 0
35383758 | CWSP - WEST POINT 11021341 PH1.1 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 2.4598 | 0 | 0 | 2.4598 | 0
35384087 | PSPS - CLARK ROAD 1102 LR514690 PH 1.4 | Base SH | 08W | CONS | In-Construction | NV | Region 2 - North East | Oroville | BUTTE | 39.6578 | -121.5657 |  | v2 | 1033 | Tier 2 | 0.43258 | 0.43258 | 0 | 0 | 0
35385803 | CWSP - SILVERADO 2104 LR 632 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5917 | -122.4436 |  | v3 | 59 | Tier 3 | 2.198 | 0 | 0 | 2.198 | 0
35385804 | CWSP - SILVERADO 2104 LR 632 PH 2.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Angwin | NAPA | 38.5934 | -122.4486 |  | v3 | 59 | Tier 3 | 2.65 | 0 | 0 | 0 | 2.65
35385805 | CWSP - SILVERADO 2104 LR 515946 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5633 | -122.4694 |  | v3 | 33 | Tier 3 | 3.1241 | 0 | 0 | 3.1241 | 0
35385806 | CWSP - SILVERADO 2104 LR 515946 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5379 | -122.4767 |  | v3 | 33 | Tier 3 | 2.936 | 0 | 0 | 2.936 | 0
35385888 | CWSP - STANISLAUS 1702 LR1888 PH1.2 | Targeted UG | 3UG | CONS | In-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2367 | -120.3629 |  | v3 | 379 | Tier 3 | 1.51 | 1.51 | 0 | 0 | 0
35385889 | CWSP - STANISLAUS 1702 LR1888 PH1.3 | Targeted UG | 3UG | DOCC | Post-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2367 | -120.3629 |  | v3 | 379 | Tier 3 | 1.9521 | 1.9521 | 0 | 0 | 0
35385890 | CWSP - STANISLAUS 1702 LR1888 PH1.4 | Targeted UG | 3UG | DOCC | Post-Construction | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2367 | -120.3629 |  | v3 | 379 | Tier 3 | 0.81572 | 0.81572 | 0 | 0 | 0
35390288 | CWSP - BRUNSWICK 110651486 - 13993 SEVEN | Targeted UG | 3UG | FICL | Post-Construction | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1766 | -120.9772 |  | v3 | 315 | Tier 3 | 0.10549 | 0.10549 | 0 | 0 | 0
35391471 | CWSP - PLACERVILLE 210611132 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7666 | -120.8222 |  | v3 | 68 | Tier 2 & 3 | 0.75 | 0 | 0 | 0 | 0.75
35391473 | CWSP - PLACERVILLE 2106-11132 PH 3.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7978 | -120.8203 |  | v3 | 68 | Tier 2 | 0.21 | 0 | 0 | 0.21 | 0
35391721 | CWSP - PLACERVILLE 2106-11132 PH 4.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7952 | -120.8123 |  | v3 | 68 | Tier 3 | 0.92708 | 0 | 0 | 0 | 0.92708
35391722 | CWSP - PLACERVILLE 210611132 PH 5.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.8102 | -120.8074 |  | v3 | 68 | Tier 3 | 3.5699 | 0 | 0 | 3.5699 | 0
35391723 | CWSP - PLACERVILLE 210611132 PH 6.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8261 | -120.8117 |  | v3 | 68 | Tier 3 | 3.24 | 0 | 0 | 3.24 | 0
35392113 | +FRRB - FORESTHILL 1101-37238 UG TL4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | SI | Region 2 - North East | Foresthill | PLACER | 39.0444 | -120.7393 |  | v3 | 322 | Tier 3 | 1.928 | 0 | 0 | 1.928 | 0
35392114 | +FRRB - PLACERVILE 21061104 UG TL5(DC07) | Fire Rebuild | 08W | CONS | In-Construction | SI | Region 2 - North East | Georgetown | EL DORADO | 38.9878 | -120.7412 |  | v3 | 397 | Tier 3 | 1.0307 | 0 | 1.0307 | 0 | 0
35395928 | CWSP - ANTLER 11011520 PH 1.2 | Targeted UG | 3UG | CONS | In-Construction | NV | Region 2 - North East | Lakehead | SHASTA | 40.9066 | -122.3834 |  | v3 | 91 | Tier 2 | 1.937 | 0 | 1.937 | 0 | 0
35395930 | CWSP - ANTLER 11011520 PH 1.4 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Lakehead | SHASTA | 40.9052 | -122.3826 |  | v3 | 91 | Tier 2 | 0.369 | 0 | 0.369 | 0 | 0
35396762 | CWSP - PINE GROVE 1101CB PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.4129 | -120.6605 |  | v3 | 6 | Tier 2 | 2.9159 | 0 | 2.9159 | 0 | 0
35396763 | CWSP - PINE GROVE 1101CB PH 1.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.4129 | -120.6605 |  | v3 | 6 | Tier 2 | 0.88 | 0 | 0.88 | 0 | 0
35396908 | CWSP - FORESTHILL 1101-50486 PH 1.2 | Targeted UG | 3UG | CONS | In-Construction | SI | Region 2 - North East | Foresthill | PLACER | 38.9994 | -120.8896 |  | v3 | 114 | Tier 3 | 3.2038 | 0 | 3.2038 | 0 | 0
35396909 | CWSP - FORESTHILL 1101-50486 PH 1.3 | Targeted UG | 3UG | CONS | In-Construction | SI | Region 2 - North East | Foresthill | PLACER | 38.9917 | -120.8912 |  | v3 | 114 | Tier 3 | 2.9786 | 0 | 2.9786 | 0 | 0
35396910 | CWSP - FORESTHILL 1101-50486 PH 1.4 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Foresthill | PLACER | 38.9928 | -120.8828 |  | v3 | 114 | Tier 3 | 3.0699 | 0 | 3.0699 | 0 | 0
35396911 | CWSP - FORESTHILL 1101-50486 PH 1.5 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Foresthill | PLACER | 38.9913 | -120.8827 |  | v3 | 114 | Tier 3 | 3.571 | 0 | 3.571 | 0 | 0
35397962 | CWSP- MARIPOSA 210110240 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Midpines | MARIPOSA | 37.5616 | -119.9349 |  | v3 | 126 | Tier 2 & 3 | 0.45 | 0 | 0 | 0 | 0.45
35398091 | FRRB -BIG MEADOWS 21012260 UG TL 1.15 | Fire Rebuild | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1356 | -120.9468 |  | v2 | 995 | Tier 2 | 0.26818 | 0 | 0.26818 | 0 | 0
35398092 | FRRB -BIG MEADOWS 21012260 UG TL 1.16 | Fire Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1356 | -120.9468 |  | v2 | 995 | Tier 2 | 0.1108 | 0.1108 | 0 | 0 | 0
35398093 | FRRB -BIG MEADOWS 21012260 UG TL 1.17 | Fire Rebuild | 08W | MAPP | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1356 | -120.9468 |  | v2 | 995 | Tier 2 | 0.14508 | 0.14508 | 0 | 0 | 0
35401011 | CWSP MARIPOSA 210110240 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Mariposa | MARIPOSA | 37.541 | -119.9184 |  | v3 | 126 | Tier 2 & 3 | 1.9701 | 0 | 0 | 0 | 1.9701
35401224 | CWSP - EL DORADO PH 2101-668674 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7605 | -120.5747 |  | v3 | 81 | Tier 3 | 0.61 | 0 | 0 | 0 | 0.61
35401226 | CWSP - EL DORADO PH 2101-668674 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7609 | -120.5741 |  | v3 | 81 | Tier 3 | 2.04 | 0 | 0 | 0 | 2.04
35402641 | CWSP - PINE GROVE 1102 13438 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Volcano | AMADOR | 38.4738 | -120.6267 |  | v3 | 204 | Tier 2 & 3 | 4.7756 | 0 | 4.7756 | 0 | 0
35402642 | CWSP - PINE GROVE 1102 13438 PH 1.3 | Targeted UG | 3UG | CONS | In-Construction | ST | Region 5 - Central Valley | Volcano | AMADOR | 38.4738 | -120.6267 |  | v3 | 204 | Tier 2 & 3 | 0.80663 | 0 | 0.80663 | 0 | 0
35402643 | CWSP - PINE GROVE 11013166 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.4069 | -120.6707 |  | v3 | 147 | Tier 2 | 2.456 | 0 | 2.456 | 0 | 0
35404061 | FRRB -BIG MEADOWS 21012260 UG TL 1.18 | Fire Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | Greenville | PLUMAS | 40.1354 | -120.947 |  | v2 | 995 | Tier 2 | 0.071591 | 0.071591 | 0 | 0 | 0
35404349 | CWSP - ELECTRA 1101 LR7104 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.395 | -120.645 |  | v3 | 62 | Tier 2 | 4.8153 | 0 | 0 | 4.8153 | 0
35404351 | CWSP - SILVERADO 210478268 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5575 | -122.452 |  | v3 | 101 | Tier 3 | 1.632 | 0 | 0 | 0 | 1.632
35404352 | CWSP - SILVERADO 210478268 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5578 | -122.4566 |  | v3 | 101 | Tier 3 | 2.029 | 0 | 0 | 0 | 2.029
35404353 | CWSP - SILVERADO 210478268 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5587 | -122.4577 |  | v3 | 101 | Tier 3 | 2.096 | 0 | 0 | 0 | 2.096
35404354 | CWSP - SILVERADO 210478268 PH 1.5 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5582 | -122.4502 |  | v3 | 101 | Tier 3 | 0.862 | 0 | 0 | 0.862 | 0
35404355 | CWSP - SILVERADO 210478268 PH 1.6 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5532 | -122.4564 |  | v3 | 101 | Tier 3 | 1.113 | 0 | 0 | 1.113 | 0
35404726 | CWSP - SILVERADO 210478268 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5572 | -122.4315 |  | v3 | 101 | Tier 3 | 3.88 | 0 | 0 | 3.88 | 0
35404727 | PSPS - VACAVILLE 1108 LR38316 PH 1.3 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4267 | -122.0475 |  | v2 | 122 | Tier 2 | 1.086 | 1.086 | 0 | 0 | 0
35404728 | PSPS - VACAVILLE 1108 LR38316 PH 1.4 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4201 | -122.0443 |  | v2 | 122 | Tier 2 | 0.82462 | 0.82462 | 0 | 0 | 0
35404729 | PSPS - VACAVILLE 1108 LR38316 PH 1.5 | Base SH | 08W | DOCC | Post-Construction | SA | Region 2 - North East | Vacaville | SOLANO | 38.4295 | -122.0489 |  | v2 | 122 | Tier 2 | 0.80644 | 0.80644 | 0 | 0 | 0
35406859 | CWSP - BUCKS CREEK 1102CB - TOBIN | Targeted UG | 3UG | CONS | In-Construction | NV | Region 2 - North East | Twain | PLUMAS | 40.0144 | -121.2252 |  | v3 | 45 | Tier 2 & 3 | 0.22102 | 0 | 0.22102 | 0 | 0
35407303 | FRRB-BIG MEADOWS2101 RND VALLY RES PH1.2 | Fire Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | Twain | PLUMAS | 40.1138 | -120.9705 |  | v2 | 995 | Tier 2 | 0.18958 | 0 | 0.18958 | 0 | 0
35407709 | BUCKS CREEK 1102CB - RED HILL | Base SH | 08W | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0359 | -121.2181 |  | v3 | 45 | Tier 2 | 0.0094697 | 0 | 0 | 0.0094697 | 0
35409202 | CWSP - MIDDLETOWN 11011314 PH1 | Targeted UG | 3UG | ESTS | Estimating | HB | Region 1 - North Coast | Middletown | LAKE | 38.7313 | -122.6233 |  | v3 | 56 | Tier 2 & 3 | 1.05 | 0 | 0 | 0 | 1.05
35409203 | CWSP - MIDDLETOWN 1101433160 | Targeted UG | 3UG | UNSE | Scoping/Scoped | HB | Region 1 - North Coast | Middletown | LAKE | 38.7253 | -122.6191 |  | v3 | 99 | Tier 2 & 3 | 1.39 | 0 | 0 | 1.39 | 0
35409213 | CWSP - APPLE HILL 1104 CB PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Camino | EL DORADO | 38.7395 | -120.6766 |  | v3 | 30 | Tier 2 | 3.03 | 0 | 0 | 3.03 | 0
35411026 | CWSP WEST POINT 1101 LR4706 PH1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4695 | -120.5278 |  | v3 | 107 | Tier 3 | 3.36 | 0 | 0 | 3.36 | 0
35411027 | CWSP WEST POINT 1101 LR4706 PH1.3 | Targeted UG | 3UG | ADER | Estimating | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4725 | -120.5267 |  | v3 | 107 | Tier 3 | 3.51 | 0 | 0 | 3.51 | 0
35411028 | CWSP WEST POINT 1101 LR4706 PH1.4 | Targeted UG | 3UG | APPR | Estimating | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4646 | -120.5292 |  | v3 | 107 | Tier 3 | 1.69 | 0 | 0 | 1.69 | 0
35417110 | CWSP - FORESTHILL 1102 2106 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0198 | -120.8507 |  | v3 | 97 | Tier 3 | 3.61 | 0 | 0 | 0 | 3.61
35417127 | CWSP - PLACERVILLE 2106-935216 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7572 | -120.7681 |  | v3 | 58 | Tier 3 | 3 | 0 | 0 | 0 | 3
35418255 | CWSP - PLACERVILLE 2106-935216 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7907 | -120.7686 |  | v3 | 58 | Tier 3 | 1.8894 | 0 | 0 | 0 | 1.8894
35418305 | CWSP - PLACERVILLE 2106-935216 PH 3.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.797 | -120.7315 |  | v3 | 58 | Tier 3 | 2.5598 | 0 | 0 | 0 | 2.5598
35418361 | CWSP - SHADY GLEN 110248894 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.119 | -120.9512 |  | v3 | 89 | Tier 2 & 3 | 1.5799 | 0 | 0 | 0 | 1.5799
35418375 | CWSP- STANISLAUS 17026028 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.237 | -120.3646 |  | v3 | 60 | Tier 3 | 1.94 | 0 | 0 | 1.94 | 0
35418379 | CWSP - STANISLAUS 170237278 PH1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2507 | -120.3666 |  | v3 | 98 | Tier 3 | 2.59 | 0 | 0 | 0 | 2.59
35419624 | FRRB - WYANDOTTE 1103 - W2 SM3 (DC07) | Fire Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | Berry Creek | BUTTE | 39.6324 | -121.4086 |  | v2 | N/A | Tier 3 | 0.099621 | 0.099621 | 0 | 0 | 0
35420109 | CWSP - PLACERVILLE 210611132 PH 1.6 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7821 | -120.8168 |  | v3 | 68 | Tier 2 & 3 | 0.17992 | 0 | 0 | 0 | 0.17992
35420110 | CWSP - PLACERVILLE 210611132 PH 1.7 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7842 | -120.8157 |  | v3 | 68 | Tier 2 & 3 | 2.15 | 0 | 0 | 0 | 2.15
35420111 | CWSP - PLACERVILLE 210611132 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7939 | -120.8191 |  | v3 | 68 | Tier 2 & 3 | 0.35 | 0 | 0 | 0.35 | 0
35420112 | CWSP - PLACERVILLE 210611132 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.8014 | -120.8185 |  | v3 | 68 | Tier 2 & 3 | 0.58 | 0 | 0 | 0.58 | 0
35420113 | CWSP - PLACERVILLE 210611132 PH 2.4 | Targeted UG | 3UG | ADER | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.8014 | -120.8187 |  | v3 | 68 | Tier 2 & 3 | 2.42 | 0 | 0 | 2.42 | 0
35420747 | CWSP - WOODSIDE 1101 FS 775939 PH 1.2 | Base SH | 08W | ESTS | Estimating | PN | Region 3 - Bay Area | Redwood City | SAN MATEO | 37.3851 | -122.2897 |  | v2 | 1145 | Tier 3 | 0.8 | 0 | 0 | 0.8 | 0
35421185 | CWSP - APPLE HILL 21026552 PH 1.1 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6818 | -120.6631 |  | v3 | 32 | Tier 2 | 3.74 | 0 | 0 | 3.74 | 0
35421186 | CWSP - APPLE HILL 21026552 PH 2.1 | Targeted UG | 3UG | ADER | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6727 | -120.6677 |  | v3 | 32 | Tier 2 | 3.3598 | 0 | 0 | 3.3598 | 0
35421187 | CWSP - WEST POINT 1101 CB & 12256 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4214 | -120.5494 |  | v3 | 218 | Tier 3 | 3.6598 | 0 | 0 | 3.6598 | 0
35421188 | CWSP - WEST POINT 1101 CB & 12256 PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4214 | -120.5494 |  | v3 | 218 | Tier 3 | 1.6 | 0 | 0 | 1.6 | 0
35421339 | CWSP - POTTER VALLEY 110576498 | Targeted UG | 3UG | MAPP | Post-Construction | HB | Region 1 - North Coast | Potter Valley | MENDOCINO | 39.3869 | -123.1132 |  | v2 | 1348 | Tier 2 | 0.37178 | 0.37178 | 0 | 0 | 0
35422751 | CWSP - SHADY GLEN 11022232 PH 3.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.144 | -120.9088 |  | v3 | 93 | Tier 3 | 2.09 | 0 | 0 | 0 | 2.09
35423081 | CWSP - PLACERVILLE 2106-11132 PH 3.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.8024 | -120.845 |  | v3 | 68 | Tier 2 | 1.03 | 0 | 0 | 1.03 | 0
35423082 | CWSP - PLACERVILLE 2106-11132 PH 3.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7983 | -120.836 |  | v3 | 68 | Tier 2 | 0.16 | 0 | 0 | 0.16 | 0
35423083 | CWSP - PLACERVILLE 2106-11132 PH 3.4 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7887 | -120.8368 |  | v3 | 68 | Tier 2 | 0.2 | 0 | 0 | 0.2 | 0
35423400 | CWSP - BONNIE NOOK 1101CB PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Alta | PLACER | 39.2148 | -120.8091 |  | v3 | 20 | Tier 3 | 5.655 | 0 | 0 | 5.655 | 0
35424354 | CWSP - BONNIE NOOK 1101CB PH 2.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Dutch Flat | PLACER | 39.1895 | -120.8347 |  | v3 | 20 | Tier 3 | 0.381 | 0 | 0 | 0.381 | 0
35424355 | CWSP - BONNIE NOOK 1101CB PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Dutch Flat | PLACER | 39.202 | -120.8364 |  | v3 | 20 | Tier 3 | 5.817 | 0 | 0 | 5.817 | 0
35424356 | CWSP - PLACERVILLE 2106-11132 PH 4.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.8026 | -120.805 |  | v3 | 68 | Tier 3 | 0.7 | 0 | 0 | 0 | 0.7
35424357 | CWSP - PLACERVILLE 2106-11132 PH 4.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.8025 | -120.7946 |  | v3 | 68 | Tier 3 | 1.739 | 0 | 0 | 1.739 | 0
35424358 | CWSP - PLACERVILLE 2106-11132 PH 4.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7881 | -120.7965 |  | v3 | 68 | Tier 3 | 0.75208 | 0 | 0 | 0 | 0.75208
35424359 | CWSP - PLACERVILLE 210611132 PH 5.2 | Targeted UG | 3UG | ADER | Estimating | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8235 | -120.8094 |  | v3 | 68 | Tier 3 | 0.85 | 0 | 0 | 0.85 | 0
35424427 | PSPS - CURTIS 1701 CB PH 1.4 | Base SH | 08W | CONS | In-Construction | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 37.9803 | -120.337 |  | v2 | 1166 | Tier 3 | 0.057576 | 0 | 0.057576 | 0 | 0
35424580 | CWSP - PLACERVILLE 210611132 PH 5.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.8123 | -120.8027 |  | v3 | 68 | Tier 3 | 2.0598 | 0 | 0 | 2.0598 | 0
35424581 | CWSP - PLACERVILLE 210611132 PH 5.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8196 | -120.7924 |  | v3 | 68 | Tier 3 | 1.7299 | 0 | 0 | 1.7299 | 0
35424589 | CWSP - PLACERVILLE 210611132 PH 6.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.832 | -120.8169 |  | v3 | 68 | Tier 3 | 0.712 | 0 | 0 | 0.712 | 0
35424590 | CWSP - PLACERVILLE 210611132 PH 6.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.83 | -120.8152 |  | v3 | 68 | Tier 3 | 1.885 | 0 | 0 | 1.885 | 0
35425643 | CWSP - SILVERADO 2104 LR 632 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5933 | -122.4411 |  | v3 | 59 | Tier 3 | 2.508 | 0 | 0 | 0 | 2.508
35425644 | CWSP - SILVERADO 2104 LR 632 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6044 | -122.4357 |  | v3 | 59 | Tier 3 | 4.114 | 0 | 0 | 0 | 4.114
35425645 | CWSP - SILVERADO 2104 LR 632 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5762 | -122.4427 |  | v3 | 59 | Tier 3 | 3.212 | 0 | 0 | 0 | 3.212
35425646 | CWSP - WEST POINT 11014706 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4817 | -120.52 |  | v3 | 107 | Tier 3 | 2.917 | 0 | 0 | 2.917 | 0
35425647 | CWSP - WEST POINT 11014706 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pioneer | AMADOR | 38.4872 | -120.519 |  | v3 | 107 | Tier 3 | 1.86 | 0 | 0 | 1.86 | 0
35425877 | CWSP - SILVERADO 2104646776 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Angwin | NAPA | 38.5809 | -122.451 |  | v3 | 14 | Tier 3 | 1.225 | 0 | 0 | 0 | 1.225
35425878 | CWSP - SILVERADO 2104646776 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Angwin | NAPA | 38.5792 | -122.4492 |  | v3 | 14 | Tier 3 | 1.684 | 0 | 0 | 0 | 1.684
35425879 | CWSP - STANISLAUS 17011812 PH 1.1 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.1831 | -120.3755 |  | v3 | 66 | Tier 3 | 4.14 | 0 | 0 | 0 | 4.14
35425921 | CWSP - STANISLAUS 17011812 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2058 | -120.3693 |  | v3 | 66 | Tier 3 | 4.4299 | 0 | 0 | 0 | 4.4299
35426736 | CWSP- ELECTRA 11017104 PH 2.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.3756 | -120.6406 |  | v3 | 62 | Tier 2 | 3.7756 | 0 | 3.7756 | 0 | 0
35428391 | CWSP - APPLE HILL 21027502 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Placerville | EL DORADO | 38.6869 | -120.641 |  | v3 | 63 | Tier 2 & 3 | 4.4379 | 0 | 0 | 4.4379 | 0
35428392 | CWSP - APPLE HILL 21027502 PH 1.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Placerville | EL DORADO | 38.6929 | -120.6389 |  | v3 | 63 | Tier 2 & 3 | 4.3966 | 0 | 0 | 4.3966 | 0
35428395 | CWSP - APPLE HILL 21027502 PH 2.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7161 | -120.6271 |  | v3 | 63 | Tier 3 | 2.9475 | 0 | 0 | 2.9475 | 0
35428396 | CWSP - APPLE HILL 21027502 PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Placerville | EL DORADO | 38.7062 | -120.6272 |  | v3 | 63 | Tier 3 | 3.9765 | 0 | 0 | 3.9765 | 0
35428397 | CWSP - APPLE HILL 21027502 PH 3.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7336 | -120.6104 |  | v3 | 63 | Tier 3 | 3.1089 | 0 | 0 | 3.1089 | 0
35428401 | CWSP - APPLE HILL 21027502 PH 3.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Pollock Pines | EL DORADO | 38.7247 | -120.6171 |  | v3 | 63 | Tier 3 | 4.4076 | 0 | 0 | 4.4076 | 0
35428403 | CWSP - SILVERADO 2104 LR 515946 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.5736 | -122.4558 |  | v3 | 33 | Tier 3 | 2.739 | 0 | 0 | 2.739 | 0
35428406 | CWSP - SILVERADO 2104 LR 515946 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Angwin | NAPA | 38.5778 | -122.4547 |  | v3 | 33 | Tier 3 | 1.386 | 0 | 0 | 0 | 1.386
35428425 | CWSP - SILVERADO 2104 LR 632 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Angwin | NAPA | 38.5991 | -122.4595 |  | v3 | 59 | Tier 3 | 2.57 | 0 | 0 | 0 | 2.57
35428426 | CWSP - SILVERADO 2104 LR 632 PH 2.3 | Targeted UG | 3UG | CONS | In-Construction | NB | Region 1 - North Coast | Angwin | NAPA | 38.6059 | -122.4586 |  | v3 | 59 | Tier 3 | 3.6413 | 0 | 0 | 3.6413 | 0
35428427 | CWSP - SILVERADO 2104 LR 632 PH 2.4 | Targeted UG | 3UG | ESTS | Estimating | NB | Region 1 - North Coast | Angwin | NAPA | 38.6116 | -122.4584 |  | v3 | 59 | Tier 3 | 3.328 | 0 | 0 | 3.328 | 0
35429499 | CWSP - WEST POINT 11021341 PH1.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 1.1799 | 0 | 0 | 1.1799 | 0
35429560 | CWSP - WEST POINT 11021341 PH1.3 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 2.5 | 0 | 0 | 2.5 | 0
35429561 | CWSP - WEST POINT 11021341 PH1.4 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 2.0699 | 0 | 0 | 2.0699 | 0
35429562 | CWSP - WEST POINT 11021341 PH1.5 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 2.05 | 0 | 0 | 2.05 | 0
35429563 | CWSP - WEST POINT 11021341 PH1.6 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3174 | -120.5211 |  | v3 | 80 | Tier 3 | 0.16989 | 0 | 0 | 0.16989 | 0
35429565 | CWSP - WEST POINT 11024788 PH 1.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3313 | -120.5186 |  | v3 | 164 | Tier 2 | 3.26 | 0 | 0 | 3.26 | 0
35429566 | CWSP - SILVERADO 2104 LR 515946 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5516 | -122.4853 |  | v3 | 33 | Tier 3 | 3.795 | 0 | 0 | 0 | 3.795
35430872 | CWSP - SILVERADO 2105658898 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5215 | -122.5366 |  | v3 | 105 | Tier 3 | 2.04 | 0 | 0 | 2.04 | 0
35430873 | CWSP - SILVERADO 2105658898 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5201 | -122.5433 |  | v3 | 105 | Tier 3 | 2.58 | 0 | 0 | 0 | 2.58
35430874 | CWSP - SILVERADO 2105658898 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5145 | -122.5421 |  | v3 | 105 | Tier 3 | 2.29 | 0 | 0 | 0 | 2.29
35430875 | CWSP - SILVERADO 2105658898 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5272 | -122.5468 |  | v3 | 105 | Tier 3 | 0.51 | 0 | 0 | 0 | 0.51
35430876 | *CANC* SILVERADO 2105658898 PH 2.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Santa Rosa | SONOMA | 38.5217 | -122.5584 |  | v3 | 105 | Tier 3 | 0.93 | 0 | 0 | 0 | 0.93
35430877 | *CANC* SILVERADO 2105658898 PH 2.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Saint Helena | NAPA | 38.5328 | -122.5495 |  | v3 | 105 | Tier 3 | 0.78 | 0 | 0 | 0 | 0.78
35430878 | CWSP - BUCKS CREEK 1102 CB PH1.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0547 | -121.2063 |  | v3 | 45 | Tier 2 | 3.4676 | 0 | 0 | 3.4676 | 0
35430879 | CWSP - BUCKS CREEK 1102 CB PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0785 | -121.1611 |  | v3 | 45 | Tier 2 | 0.056818 | 0 | 0 | 0 | 0.056818
35430880 | CWSP - BUCKS CREEK 1102 CB PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Twain | PLUMAS | 40.0913 | -121.1478 |  | v3 | 45 | Tier 2 | 2.5 | 0 | 0 | 0 | 2.5
35431074 | CWSP - ELECTRA 1101L1697 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.3732 | -120.6317 |  | v3 | 118 | Tier 2 | 2.05 | 0 | 0 | 2.05 | 0
35431075 | CWSP - ELECTRA 1101L1697 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Pine Grove | AMADOR | 38.374 | -120.6333 |  | v3 | 118 | Tier 2 | 1.5 | 0 | 0 | 1.5 | 0
35433366 | CWSP - CLAYTON 2212 LR 96224 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.9038 | -121.8741 |  | v3 | 15 | Tier 3 | 0.78996 | 0 | 0 | 0 | 0.78996
35433421 | CWSP - ANTLER 11011520 PH 1.6 | Targeted UG | 3UG | CONS | In-Construction | NV | Region 2 - North East | Lakehead | SHASTA | 40.9164 | -122.3982 |  | v3 | 91 | Tier 2 | 2.841 | 0 | 0 | 2.841 | 0
35435899 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | YO | Region 5 - Central Valley | El Portal | MARIPOSA | 37.6774 | -119.7745 |  | v3 | 10 | Tier 2 | 1.2 | 0 | 0 | 1.2 | 0
35436100 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | YO | Region 5 - Central Valley | El Portal | MARIPOSA | 37.6775 | -119.7744 |  | v3 | 10 | Tier 2 | 1.5098 | 0 | 0 | 1.5098 | 0
35436513 | CWSP - APPLE HILL 1104 CB PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Camino | EL DORADO | 38.7381 | -120.676 |  | v3 | 30 | Tier 2 | 2.36 | 0 | 0 | 2.36 | 0
35436514 | CWSP - APPLE HILL 21026552 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6762 | -120.6628 |  | v3 | 32 | Tier 2 | 3.6299 | 0 | 0 | 3.6299 | 0
35436515 | CWSP - APPLE HILL 21026552 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6595 | -120.6763 |  | v3 | 32 | Tier 2 | 3.3299 | 0 | 0 | 3.3299 | 0
35436516 | CWSP - APPLE HILL 21026552 PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Placerville | EL DORADO | 38.6727 | -120.6685 |  | v3 | 32 | Tier 2 | 2.1519 | 0 | 0 | 2.1519 | 0
35439661 | CWSP - BUCKS CREEK 1102CB - STORRIE | Targeted UG | 3UG | UNSC | Ready for Construction | NV | Region 2 - North East | Belden | PLUMAS | 39.9118 | -121.3272 |  | v3 | 45 | Tier 2 & 3 | 0.094697 | 0 | 0.094697 | 0 | 0
35439898 | CWSP - ANTLER 11011384 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Lakehead | SHASTA | 40.8876 | -122.389 |  | v3 | 11 | Tier 2 | 4.939 | 0 | 0 | 4.939 | 0
35439899 | CWSP - ANTLER 11011384 PH 1.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Lakehead | SHASTA | 40.8906 | -122.3821 |  | v3 | 11 | Tier 2 | 1.334 | 0 | 0 | 1.334 | 0
35447662 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Nevada City | NEVADA | 39.3582 | -120.8008 |  | v3 | 41 | Tier 3 | 2.197 | 0 | 0 | 2.197 | 0
35447663 | CWSP - ALLEGHANY 1102CB NEVADA PH 5.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Nevada City | NEVADA | 39.3625 | -120.7904 |  | v3 | 41 | Tier 3 | 2.97 | 0 | 0 | 2.97 | 0
35448085 | CWSP - NOTRE DAME 11042028 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.835 | -121.6897 |  | v3 | 37 | Tier 3 | 2.338 | 0 | 0 | 2.338 | 0
35448086 | CWSP - NOTRE DAME 11042028 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8332 | -121.6804 |  | v3 | 37 | Tier 3 | 1.986 | 0 | 0 | 1.986 | 0
35448807 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Alleghany | SIERRA | 39.4646 | -120.8462 |  | v3 | 41 | TBD | 2.21 | 0 | 0 | 2.21 | 0
35448810 | CWSP - ALLEGHANY 1102CB SIERRA PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Alleghany | SIERRA | 39.4632 | -120.8493 |  | v3 | 41 | TBD | 2.56 | 0 | 0 | 0 | 2.56
35450186 | CWSP - BONNIE NOOK 1101CB PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Alta | PLACER | 39.2164 | -120.826 |  | v3 | 20 | Tier 3 | 0.78996 | 0 | 0 | 0.78996 | 0
35451494 | CWSP - INDIAN FLAT 1104 CB & 4440 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | YO | Region 5 - Central Valley | El Portal | MARIPOSA | 37.6699 | -119.8155 |  | v3 | 10 | Tier 2 | 0.35 | 0 | 0 | 0.35 | 0
35452898 | CWSP - PIKE CITY 11011720 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Camptonville | YUBA | 39.4717 | -121.0851 |  | v3 | 52 | Tier 3 | 4.42 | 0 | 0 | 0 | 4.42
35454650 | CWSP - NOTRE DAME 1104 2028 PH2.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8577 | -121.6926 |  | v3 | 37 | Tier 3 | 0.514 | 0 | 0 | 0 | 0.514
35454651 | CWSP - NOTRE DAME 1104 2028 PH2.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8558 | -121.693 |  | v3 | 37 | Tier 3 | 1.386 | 0 | 0 | 0 | 1.386
35454652 | CWSP - NOTRE DAME 1104 2028 PH2.4 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8571 | -121.6918 |  | v3 | 37 | Tier 3 | 2.695 | 0 | 0 | 2.695 | 0
35457280 | CWSP - ALLEGHANY 1102CB PH 3.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Nevada City | NEVADA | 39.4264 | -120.8101 |  | v3 | 41 | Tier 3 | 3.77 | 0 | 0 | 0 | 3.77
35457281 | CWSP - ALLEGHANY 1102CB PH 3.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Nevada City | NEVADA | 39.4171 | -120.8 |  | v3 | 41 | Tier 3 | 2.31 | 0 | 0 | 0 | 2.31
35457712 | CWSP REDBUD 1101 754544 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0932 | -122.6804 |  | v3 | N/A | TBD | 1.5 | 0 | 0 | 1.5 | 0
35457800 | CWSP - ALLEGHANY 1102CB SIERRA PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Camptonville | SIERRA | 39.4482 | -120.8298 |  | v3 | 41 | Tier 3 | 2.14 | 0 | 0 | 2.14 | 0
35458434 | CWSP - ALLEGHANY 1102CB NEVADA PH 4.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Nevada City | NEVADA | 39.3826 | -120.7871 |  | v3 | 41 | Tier 3 | 2.39 | 0 | 0 | 0 | 2.39
35460160 | CWSP - SYCAMORE CREEK 11112268 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.918 | -121.7361 |  | v3 | 57 | Tier 3 | 4.37 | 0 | 0 | 4.37 | 0
35460162 | CWSP - SYCAMORE CREEK 11112268 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.9262 | -121.7321 |  | v3 | 57 | Tier 3 | 5.03 | 0 | 0 | 0 | 5.03
35460286 | CWSP - ORO FINO 1102CB PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Magalia | BUTTE | 39.8645 | -121.6139 |  | v3 | 17 | Tier 3 | 2.069 | 0 | 0 | 2.069 | 0
35460292 | CWSP - ORO FINO 1102CB PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Magalia | BUTTE | 39.8718 | -121.6107 |  | v3 | 17 | Tier 3 | 0.19201 | 0 | 0 | 0.19201 | 0
35464320 | CWSP - SYCAMORE CREEK 11112268 PH 2.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Chico | BUTTE | 39.9339 | -121.7267 |  | v3 | 57 | Tier 3 | 4.34 | 0 | 0 | 4.34 | 0
35464321 | CWSP - SYCAMORE CREEK 11112268 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.943 | -121.729 |  | v3 | 57 | Tier 3 | 1.79 | 0 | 0 | 0 | 1.79
35464322 | CWSP - SYCAMORE CREEK 11112268 PH 3.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.942 | -121.7093 |  | v3 | 57 | Tier 3 | 1.67 | 0 | 0 | 1.67 | 0
35464323 | CWSP - SYCAMORE CREEK 11112268 PH 3.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Chico | BUTTE | 39.9323 | -121.7034 |  | v3 | 57 | Tier 3 | 1.55 | 0 | 0 | 1.55 | 0
35473990 | CWSP - PLACERVILLE 2106-935216 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.794 | -120.7609 |  | v3 | 58 | Tier 3 | 5.3598 | 0 | 0 | 0 | 5.3598
35473991 | CWSP - PLACERVILLE 2106-935216 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7872 | -120.7748 |  | v3 | 58 | Tier 3 | 1.69 | 0 | 0 | 0 | 1.69
35473992 | PSPS - JAMESON 1102 LR65516 1.10 | Base SH | 08W | PEND | Permitting/Dependency | SA | Region 2 - North East | Fairfield | SOLANO | 38.2722 | -122.1725 |  | v2 | 739 | Tier 2 | 0.4786 | 0 | 0.4786 | 0 | 0
35473993 | PSPS - VACAVILLE 1108 LR8762 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | SA | Region 2 - North East | Vacaville | SOLANO | 38.3492 | -122.0247 |  | v2 | 64 | Tier 2 | 0.26174 | 0 | 0.26174 | 0 | 0
35474894 | PSPS - VACAVILLE 1108 LR38316 PH 2.4 | Base SH | 08W | ESTS | Estimating | SA | Region 2 - North East | Vacaville | SOLANO | 38.4097 | -122.0358 |  | v2 | 122 | Tier 2 | 1.2775 | 0 | 1.2775 | 0 | 0
35474978 | CWSP - PLACERVILLE 2106-935216 PH 3.2 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7948 | -120.7319 |  | v3 | 58 | Tier 3 | 3.5199 | 0 | 0 | 0 | 3.5199
35485344 | CWSP- STANISLAUS 17026028 PH1.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2373 | -120.3651 |  | v3 | 60 | Tier 3 | 4.11 | 0 | 0 | 4.11 | 0
35485345 | CWSP- STANISLAUS 17026028 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2385 | -120.3693 |  | v3 | 60 | Tier 3 | 3.23 | 0 | 0 | 3.23 | 0
35485580 | PSPS - VACAVILLE 1108 LR8762 PH 1.6 BRAZ | Base SH | 08W | PEND | Permitting/Dependency | SA | Region 2 - North East | Vacaville | SOLANO | 38.3721 | -122.0251 |  | v2 | 64 | Tier 2 | 0.056818 | 0 | 0 | 0.056818 | 0
35488067 | CWSP - ORO FINO 110276008 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.876 | -121.7077 |  | v3 | 61 | Tier 3 | 1.09 | 0 | 0 | 1.09 | 0
35488068 | CWSP - ORO FINO 110276008 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8728 | -121.6795 |  | v3 | 61 | Tier 3 | 3.7299 | 0 | 0 | 3.7299 | 0
35488069 | CWSP - ORO FINO 110276008 PH 2.3 | Targeted UG | 3UG | ADER | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.876 | -121.6809 |  | v3 | 61 | Tier 3 | 1.45 | 0 | 0 | 1.45 | 0
35488560 | CWSP - ORO FINO 110276008 PH 1.2 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8769 | -121.6831 |  | v3 | 61 | Tier 3 | 2.55 | 0 | 0 | 2.55 | 0
35490375 | PSPS - CORNING 1102 - LR 915324 PH# 1.3 | Base SH | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | Corning | TEHAMA | 39.9193 | -122.437 |  | v2 | 457 | Tier 2 | 0.093182 | 0 | 0.093182 | 0 | 0
35493212 | CWSP - STANISLAUS 17011812 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.1859 | -120.3689 |  | v3 | 66 | Tier 3 | 1.9741 | 0 | 0 | 0 | 1.9741
35493213 | CWSP - STANISLAUS 17011812 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.1921 | -120.3655 |  | v3 | 66 | Tier 3 | 0.9697 | 0 | 0 | 0 | 0.9697
35493214 | CWSP - STANISLAUS 17011812 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.193 | -120.3641 |  | v3 | 66 | Tier 3 | 1.6917 | 0 | 0 | 0 | 1.6917
35493215 | CWSP - STANISLAUS 17011812 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.1964 | -120.3652 |  | v3 | 66 | Tier 3 | 1.658 | 0 | 0 | 0 | 1.658
35493216 | CWSP - STANISLAUS 17011812 PH 1.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.203 | -120.3695 |  | v3 | 66 | Tier 3 | 2.9295 | 0 | 0 | 0 | 2.9295
35493217 | CWSP - STANISLAUS 17011812 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2049 | -120.3696 |  | v3 | 66 | Tier 3 | 3.6299 | 0 | 0 | 0 | 3.6299
35493218 | CWSP - STANISLAUS 17011812 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2057 | -120.3666 |  | v3 | 66 | Tier 3 | 2.35 | 0 | 0 | 0 | 2.35
35493219 | CWSP - STANISLAUS 17011812 PH 2.4 | Targeted UG | 3UG | ESTS | Estimating | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2247 | -120.3693 |  | v3 | 66 | Tier 3 | 2.2201 | 0 | 0 | 0 | 2.2201
35510467 | CWSP - BONNIE NOOK 1101CB PH 2.4 | Targeted UG | 3UG | PEND | Permitting/Dependency | SI | Region 2 - North East | Dutch Flat | PLACER | 39.1913 | -120.8316 |  | v3 | 20 | Tier 3 | 1 | 0 | 0 | 1 | 0
35515535 | CWSP - PLACERVILLE 210611132 PH 2.5 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Garden Valley | EL DORADO | 38.8212 | -120.8271 |  | v3 | 68 | Tier 2 & 3 | 0.33 | 0 | 0 | 0.33 | 0
35519761 | CWSP - OAKHURST 110310140 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3664 | -119.6296 |  | v3 | 22 | Tier 3 | 1.317 | 0 | 0 | 0 | 1.317
35519767 | CWSP - KESWICK 11019712 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Shasta | SHASTA | 40.6167 | -122.4958 |  | v3 | 43 | Tier 3 | 0.66004 | 0 | 0 | 0 | 0.66004
35519768 | CWSP - KONOCTI 11022293 | Base SH | 08W | UNSE | Scoping/Scoped | HB | Region 1 - North Coast | Lower Lake | LAKE | 38.9454 | -122.6672 |  | v3 | 51 | Tier 2 | 0.18996 | 0 | 0 | 0 | 0.18996
35519772 | CWSP - APPLE HILL 210289934 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Somerset | EL DORADO | 38.649 | -120.6765 |  | v3 | 55 | Tier 2 | 0.33996 | 0 | 0 | 0 | 0.33996
35519776 | CWSP - BEAR VALLEY 210576694 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Coulterville | MARIPOSA | 37.7404 | -120.1278 |  | v3 | 76 | Tier 2 | 0.15 | 0 | 0 | 0 | 0.15
35519777 | CWSP - KESWICK 11011588 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.617 | -122.4961 |  | v3 | 83 | Tier 2 & 3 | 1.1701 | 0 | 0 | 0 | 1.1701
35519779 | CWSP - ELK CREEK 11012032 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Stonyford | COLUSA | 39.3759 | -122.5506 |  | v3 | 85 | Tier 2 | 0.48996 | 0 | 0 | 0 | 0.48996
35519784 | CWSP - WILDWOOD 110198896 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Platina | SHASTA | 40.3606 | -122.9513 |  | v3 | 109 | Tier 2 | 2.3 | 0 | 0 | 0 | 2.3
35519786 | CWSP - KESWICK 110148480 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.6237 | -122.4621 |  | v3 | 119 | Tier 3 | 0.27992 | 0 | 0 | 0.27992 | 0
35521812 | CWSP- MIWUK 170236888 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Sonora | TUOLUMNE | 38.0285 | -120.2514 |  | v3 | 50 | Tier 3 | 0.42992 | 0 | 0 | 0 | 0.42992
35521813 | CWSP - MOUNTAIN QUARRIES 210135466 PH1.1 | Base SH | 08W | ESTS | Estimating | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8988 | -120.9105 |  | v3 | 70 | Tier 2 | 0.05 | 0 | 0 | 0 | 0.05
35521818 | CWSP - COLUMBIA HILL 110190730 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | NEVADA | 39.3429 | -121.1211 |  | v3 | 75 | Tier 2 | 1.4193 | 0 | 0 | 0 | 1.4193
35521819 | CWSP - CLAYTON 2212681608 PH2.1 | Base SH | 08W | UNSE | Scoping/Scoped | DI | Region 3 - Bay Area | Clayton | CONTRA COSTA | 37.9245 | -121.9124 |  | v3 | 115 | Tier 2 & 3 | 0.043939 | 0 | 0 | 0 | 0.043939
35522101 | CWSP - SHADY GLEN 11012768 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1023 | -120.9592 |  | v3 | 120 | Tier 2 | 0.5 | 0 | 0 | 0 | 0.5
35522102 | CWSP - ALLEGHANY 1101VR816 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.5572 | -120.8285 |  | v3 | 120 | Tier 3 | 0.8464 | 0 | 0 | 0 | 0.8464
35522104 | CWSP - CALISTOGA 1101122350 PH2.1 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Calistoga | NAPA | 38.6089 | -122.591 |  | v3 | 134 | Tier 3 | 0.48409 | 0 | 0 | 0 | 0.48409
35523358 | PSPS - PIT NO 3 2101CB PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9981 | -121.7481 |  | v3 | 326 | Tier 2 | 3.2841 | 0 | 0 | 3.2841 | 0
35523400 | PSPS - PIT NO 3 2101CB PH 1.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9981 | -121.7481 |  | v3 | 326 | Tier 2 | 0.52898 | 0 | 0 | 0.52898 | 0
35523401 | CWSP - REDBUD 1101 LR323962 PH 1.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | v3 | 127 | Tier 3 | 1.54 | 0 | 0 | 1.54 | 0
35523402 | CWSP - REDBUD 1101 LR323962 PH 1.2 | Targeted UG | 3UG | PEND | Permitting/Dependency | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | v3 | 127 | Tier 3 | 3.1299 | 0 | 0 | 3.1299 | 0
35523410 | CWSP - REDBUD 1101 LR323962 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | HB | Region 1 - North Coast | Clearlake Oaks | LAKE | 39.0662 | -122.6111 |  | v3 | 127 | Tier 3 | 2.86 | 0 | 0 | 2.86 | 0
35523412 | PSPS - TEJON 1102 LR732836 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.8817 | -118.9019 |  | v3 | 219 | Tier 2 | 3.233 | 0 | 0 | 3.233 | 0
35523413 | PSPS - TEJON 1102 LR732836 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.8817 | -118.9019 |  | v3 | 219 | Tier 2 | 2.7701 | 0 | 0 | 2.7701 | 0
35523414 | PSPS - TEJON 1102 LR732836 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.8817 | -118.9019 |  | v3 | 219 | Tier 2 | 1.4201 | 0 | 0 | 1.4201 | 0
35523415 | PSPS - TEJON 1102 LR732836 PH 2.4 | Targeted UG | 3UG | PEND | Permitting/Dependency | KE | Region 5 - Central Valley | Lebec | KERN | 34.8817 | -118.9019 |  | v3 | 219 | Tier 2 | 1.69 | 0 | 0 | 1.69 | 0
35523416 | PSPS - TEJON 11023751 PH 2.1 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | v3 | 368 | Tier 2 | 2.0201 | 0 | 0 | 2.0201 | 0
35523417 | PSPS - TEJON 11023751 PH 2.2 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | v3 | 368 | Tier 2 | 2.2521 | 0 | 0 | 2.2521 | 0
35523418 | PSPS - TEJON 11023751 PH 2.3 | Targeted UG | 3UG | PEND | Permitting/Dependency | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | v3 | 368 | Tier 2 | 2.6201 | 0 | 0 | 2.6201 | 0
35523419 | PSPS - TEJON 11023751 PH 2.4 | Targeted UG | 3UG | ESTS | Estimating | KE | Region 5 - Central Valley | Lebec | KERN | 34.9321 | -118.9283 |  | v3 | 368 | Tier 2 | 1.44 | 0 | 0 | 1.44 | 0
35523540 | CWSP - HIGHLANDS 1102628 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | HB | Region 1 - North Coast | Clearlake | LAKE | 38.9936 | -122.5251 |  | v3 | 29 | Tier 2 | 0.77992 | 0 | 0 | 0.77992 | 0
35524040 | PSPS - PIT NO 3 2101CB PH 1.1 | Targeted UG | 3UG | PEND | Permitting/Dependency | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9983 | -121.7471 |  | v3 | 326 | Tier 2 | 1.893 | 0 | 0 | 1.893 | 0
35524267 | CWSP - VACAVILLE 11046542 PH 1.7 | Base SH | 08W | PEND | Permitting/Dependency | SA | Region 2 - North East | Vacaville | SOLANO | 38.3417 | -122.0095 |  | v2 | 42 | Tier 2 | 0.15 | 0 | 0 | 0.15 | 0
35524564 | CWSP - CURTIS 17039240 PH 2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 | 1.5299 | 0 | 0 | 0 | 1.5299
35524565 | CWSP - CURTIS 17039240 PH 1 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 & 3 | 1.46 | 0 | 0 | 0 | 1.46
35524572 | CWSP - PIT NO 5 1101CB | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Montgomery Creek | SHASTA | 40.9869 | -121.9773 |  | v3 | 104 | Tier 2 | 0.67405 | 0 | 0 | 0 | 0.67405
35526198 | CWSP- STANISLAUS 1701CB PH 5 | Base SH | 08W | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Murphys | CALAVERAS | 38.0906 | -120.4525 |  | v3 | 95 | Tier 2 | 0.32992 | 0 | 0 | 0.32992 | 0
35526461 | CWSP - SHADY GLEN 110132726 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1007 | -120.9598 |  | v3 | 71 | Tier 2 | 0.86402 | 0 | 0 | 0.86402 | 0
35526462 | CWSP - SHADY GLEN 110248894 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1369 | -120.958 |  | v3 | 89 | Tier 2 & 3 | 0.71591 | 0 | 0 | 0 | 0.71591
35526463 | CWSP - ANTLER 1101CB | Base SH | 08W | ESTS | Estimating | NV | Region 2 - North East | Lakehead | SHASTA | 40.8945 | -122.381 |  | v3 | 94 | Tier 2 | 0.42008 | 0 | 0 | 0.42008 | 0
35526464 | CWSP - FORESTHILL 11022106 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0185 | -120.8784 |  | v3 | 97 | Tier 3 | 0.93996 | 0 | 0 | 0 | 0.93996
35526465 | CWSP - FORESTHILL 11022106 PH 3.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0018 | -120.9075 |  | v3 | 97 | Tier 2 & 3 | 1.81 | 0 | 0 | 0 | 1.81
35526466 | CWSP - FORESTHILL 11022106 PH 4.1 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9956 | -120.9194 |  | v3 | 97 | Tier 2 | 1.8299 | 0 | 0 | 0 | 1.8299
35534915 | CWSP - SILVERADO 2104 LR 632 PH 1.5 | Targeted UG | 3UG | CONS | In-Construction | NB | Region 1 - North Coast | Angwin | NAPA | 38.6168 | -122.4252 |  | v3 | 59 | Tier 3 | 0.99886 | 0 | 0 | 0 | 0.99886
35537020 | CWSP - CALISTOGA 1102131531 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5634 | -122.5627 |  | v3 | 24 | Tier 3 | 0.87992 | 0 | 0 | 0 | 0.87992
35537023 | CWSP - CALISTOGA 1102131531 PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5559 | -122.577 |  | v3 | 24 | Tier 3 | 0.82992 | 0 | 0 | 0 | 0.82992
35537077 | CWSP - OREGON TRAIL 11021584 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.6625 | -122.4012 |  | v3 | 64 | Tier 2 | 1.75 | 0 | 0 | 1.75 | 0
35537866 | CWSP - PLACERVILLE 210611132 PH 2.6 | Targeted UG | 3UG | ADER | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.8235 | -120.8278 |  | v3 | 68 | Tier 2 & 3 | 0.73 | 0 | 0 | 0.73 | 0
35538297 | CWSP - FORESTHILL 1102 2106 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0287 | -120.8611 |  | v3 | 97 | Tier 3 | 3.31 | 0 | 0 | 0 | 3.31
35538298 | CWSP - FORESTHILL 1102 2106 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0323 | -120.8638 |  | v3 | 97 | Tier 3 | 0.87992 | 0 | 0 | 0 | 0.87992
35538299 | CWSP - FORESTHILL 1102 2106 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0412 | -120.8651 |  | v3 | 97 | Tier 3 | 1.8 | 0 | 0 | 0 | 1.8
35538520 | CWSP - FORESTHILL 11022106 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0148 | -120.8838 |  | v3 | 97 | Tier 3 | 2.49 | 0 | 0 | 0 | 2.49
35538521 | CWSP - FORESTHILL 11022106 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0096 | -120.895 |  | v3 | 97 | Tier 3 | 1.04 | 0 | 0 | 0 | 1.04
35538522 | CWSP - FORESTHILL 11022106 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 39.0077 | -120.8982 |  | v3 | 97 | Tier 3 | 2.9701 | 0 | 0 | 0 | 2.9701
35538523 | CWSP - FORESTHILL 11022106 PH 3.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9952 | -120.9057 |  | v3 | 97 | Tier 2 & 3 | 3.26 | 0 | 0 | 0 | 3.26
35538524 | CWSP - FORESTHILL 11022106 PH 3.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9861 | -120.9067 |  | v3 | 97 | Tier 2 & 3 | 0.089962 | 0 | 0 | 0 | 0.089962
35538525 | CWSP - FORESTHILL 11022106 PH 3.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9956 | -120.9194 |  | v3 | 97 | Tier 2 & 3 | 0.72008 | 0 | 0 | 0 | 0.72008
35538526 | CWSP - FORESTHILL 11022106 PH 3.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9979 | -120.9213 |  | v3 | 97 | Tier 2 & 3 | 0.31004 | 0 | 0 | 0 | 0.31004
35538527 | CWSP - FORESTHILL 11022106 PH 4.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Foresthill | PLACER | 38.9864 | -120.9328 |  | v3 | 97 | Tier 2 & 3 | 2.84 | 0 | 0 | 0 | 2.84
35539104 | CWSP- STANISLAUS 170237278 PH1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2523 | -120.3681 |  | v3 | 98 | Tier 3 | 1.8201 | 0 | 0 | 0 | 1.8201
35539105 | CWSP- STANISLAUS 170237278 PH1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2521 | -120.3666 |  | v3 | 98 | Tier 3 | 1.34 | 0 | 0 | 0 | 1.34
35539106 | CWSP- STANISLAUS 170237278 PH1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2504 | -120.3612 |  | v3 | 98 | Tier 3 | 3.3201 | 0 | 0 | 0 | 3.3201
35539107 | CWSP- STANISLAUS 170237278 PH1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Arnold | CALAVERAS | 38.2433 | -120.3632 |  | v3 | 98 | Tier 3 | 1.5799 | 0 | 0 | 0 | 1.5799
35539117 | CWSP - PLACERVILLE 2106935216 PH 1.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7941 | -120.775 |  | v3 | N/A | TBD | 1.69 | 0 | 0 | 0 | 1.69
35539118 | CWSP - PLACERVILLE 2106935216 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7944 | -120.7748 |  | v3 | N/A | TBD | 2.03 | 0 | 0 | 0 | 2.03
35539119 | CWSP - PLACERVILLE 2106935216 PH 1.5 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7713 | -120.7704 |  | v3 | N/A | TBD | 0.92 | 0 | 0 | 0 | 0.92
35539160 | CWSP - PLACERVILLE 2106935216 PH 1.6 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7704 | -120.7672 |  | v3 | N/A | TBD | 1.35 | 0 | 0 | 0 | 1.35
35539161 | CWSP - PLACERVILLE 2106935216 PH 2.3 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7907 | -120.7686 |  | v3 | N/A | TBD | 1.0468 | 0 | 0 | 1.0468 | 0
35539162 | CWSP - PLACERVILLE 2106935216 PH 2.4 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.7909 | -120.76 |  | v3 | N/A | TBD | 2.3498 | 0 | 0 | 2.3498 | 0
35539166 | CWSP - CALISTOGA 110143924 PH 1.3 | Targeted UG | 3UG | ADER | Estimating | NB | Region 1 - North Coast | Calistoga | NAPA | 38.576 | -122.5845 |  | v3 | 105 | Tier 3 | 0.41004 | 0 | 0 | 0.41004 | 0
35539167 | CWSP - CALISTOGA 110143924 PH 1.4 | Targeted UG | 3UG | ADER | Estimating | NB | Region 1 - North Coast | Calistoga | NAPA | 38.5813 | -122.5952 |  | v3 | 105 | Tier 3 | 0.0039773 | 0 | 0 | 0.0039773 | 0
35539171 | CWSP - OREGON TRAIL 11021584 PH 1.3 | Base SH | 08W | ESTS | Estimating | NV | Region 2 - North East | Redding | SHASTA | 40.6626 | -122.3966 |  | v3 | 64 | Tier 2 | 0.55 | 0 | 0 | 0.55 | 0
35539172 | CWSP - OREGON TRAIL 11021584 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.6609 | -122.4186 |  | v3 | 64 | Tier 2 | 1.5201 | 0 | 0 | 1.5201 | 0
35539175 | CWSP - OREGON TRAIL 11021584 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.664 | -122.4008 |  | v3 | 64 | Tier 2 | 1.0701 | 0 | 0 | 1.0701 | 0
35539177 | CWSP - OREGON TRAIL 11021584 PH 2.7 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Shasta Lake | SHASTA | 40.6755 | -122.4063 |  | v3 | 64 | Tier 2 | 2.14 | 0 | 0 | 2.14 | 0
35540576 | CWSP - STANISLAUS 1701CB PH 6.3 | Base SH | 08W | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Vallecito | CALAVERAS | 38.0934 | -120.4772 |  | v3 | 95 | Tier 2 | 0.41742 | 0 | 0 | 0.41742 | 0
35540577 | CWSP - STANISLAUS 1701CB PH 6.4 | Base SH | 08W | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Vallecito | CALAVERAS | 38.0934 | -120.4772 |  | v3 | 95 | Tier 2 | 0.41155 | 0 | 0 | 0.41155 | 0
35542495 | CWSP - CALISTOGA 1101122350 PH1.7 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6393 | -122.594 |  | v3 | 134 | Tier 2 & 3 | 0.15 | 0 | 0 | 0 | 0.15
35542603 | CWSP - APPLE HILL 21027502 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | SI | Region 2 - North East | Placerville | EL DORADO | 38.6856 | -120.6476 |  | v3 | N/A | TBD | 2.2699 | 0 | 0 | 2.2699 | 0
35543416 | CWSP - OAKHURST 110310140 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3666 | -119.6298 |  | v3 | 22 | Tier 3 | 0.61004 | 0 | 0 | 0 | 0.61004
35543417 | CWSP - OAKHURST 110310140 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3638 | -119.6243 |  | v3 | 22 | Tier 3 | 0.72008 | 0 | 0 | 0 | 0.72008
35543418 | CWSP - OAKHURST 110310140 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3638 | -119.6243 |  | v3 | 22 | Tier 3 | 0.039962 | 0 | 0 | 0 | 0.039962
35543419 | CWSP - OAKHURST 110310140 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3633 | -119.6194 |  | v3 | 22 | Tier 3 | 0.8 | 0 | 0 | 0 | 0.8
35543440 | CWSP - OAKHURST 110310140 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3673 | -119.6084 |  | v3 | 22 | Tier 3 | 1 | 0 | 0 | 0 | 1
35543441 | CWSP - OAKHURST 110310140 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3664 | -119.6073 |  | v3 | 22 | Tier 3 | 0.41004 | 0 | 0 | 0 | 0.41004
35543443 | CWSP - OAKHURST 110310140 PH 1.8 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3651 | -119.601 |  | v3 | 22 | Tier 3 | 0.45 | 0 | 0 | 0 | 0.45
35543444 | CWSP - OAKHURST 110310140 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3578 | -119.6085 |  | v3 | 22 | Tier 3 | 0.47008 | 0 | 0 | 0 | 0.47008
35543445 | CWSP - OAKHURST 110310140 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Oakhurst | MADERA | 37.3539 | -119.6052 |  | v3 | 22 | Tier 3 | 0.32992 | 0 | 0 | 0 | 0.32992
35543447 | CWSP - OAKHURST 110310140 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Bass Lake | MADERA | 37.343 | -119.5913 |  | v3 | 22 | Tier 3 | 1.35 | 0 | 0 | 0 | 1.35
35543503 | CWSP - SHADY GLEN 110132726 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0955 | -120.9652 |  | v3 | 71 | Tier 2 | 1.229 | 0 | 0 | 1.229 | 0
35543504 | CWSP - SHADY GLEN 110132726 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.088 | -120.9659 |  | v3 | 71 | Tier 2 | 1.358 | 0 | 0 | 1.358 | 0
35543505 | CWSP - SHADY GLEN 110132726 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0973 | -120.975 |  | v3 | 71 | Tier 2 | 1.3811 | 0 | 0 | 1.3811 | 0
35543506 | CWSP - SHADY GLEN 110132726 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0942 | -120.9765 |  | v3 | 71 | Tier 2 | 1.778 | 0 | 0 | 1.778 | 0
35543507 | CWSP - SHADY GLEN 110132726 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0991 | -120.9633 |  | v3 | 71 | Tier 2 | 1.3009 | 0 | 0 | 1.3009 | 0
35543509 | CWSP - SHADY GLEN 110132726 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0927 | -120.9725 |  | v3 | 71 | Tier 2 | 0.95909 | 0 | 0 | 0.95909 | 0
35543511 | CWSP - SHADY GLEN 110132726 PH 1.8 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0914 | -120.9642 |  | v3 | 71 | Tier 2 | 1.272 | 0 | 0 | 1.272 | 0
35543512 | CWSP - SHADY GLEN 110132726 PH 1.9 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.0896 | -120.9694 |  | v3 | 71 | Tier 2 | 0.53598 | 0 | 0 | 0.53598 | 0
35543514 | CWSP - SHADY GLEN 110132726 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Grass Valley | NEVADA | 39.0865 | -120.9923 |  | v3 | 71 | Tier 2 | 0.29602 | 0 | 0 | 0.29602 | 0
35544220 | CWSP - KESWICK 11019712 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Shasta | SHASTA | 40.616 | -122.4958 |  | v3 | 43 | Tier 3 | 0.35 | 0 | 0 | 0 | 0.35
35544224 | CWSP - KESWICK 11019712 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.5899 | -122.4872 |  | v3 | 43 | Tier 3 | 2.7 | 0 | 0 | 0 | 2.7
35544225 | CWSP - KESWICK 11019712 PH 2.6 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.5834 | -122.4871 |  | v3 | 43 | Tier 3 | 1.86 | 0 | 0 | 0 | 1.86
35544229 | CWSP - MOUNTAIN QUARRIES 210135466 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Greenwood | EL DORADO | 38.8989 | -120.9121 |  | v3 | 70 | Tier 2 | 0.28996 | 0 | 0 | 0 | 0.28996
35544230 | CWSP - APPLE HILL 210289934 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Somerset | EL DORADO | 38.6474 | -120.6748 |  | v3 | 55 | Tier 2 | 0.6 | 0 | 0 | 0 | 0.6
35544237 | CWSP- CURTIS 1703258550 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.831 | -120.2426 |  | v3 | 34 | Tier 2 | 0.24508 | 0 | 0 | 0 | 0.24508
35544380 | CWSP - GIRVAN 11029012 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Redding | SHASTA | 40.5901 | -122.4605 |  | v3 | 73 | Tier 2 & 3 | 0.33996 | 0 | 0 | 0 | 0.33996
35544681 | CWSP - CALISTOGA 1101122350 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Calistoga | NAPA | 38.6459 | -122.5925 |  | v3 | 134 | Tier 3 | 0.64602 | 0 | 0 | 0 | 0.64602
35544682 | CWSP - CALISTOGA 1101122350 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Calistoga | NAPA | 38.6487 | -122.5942 |  | v3 | 134 | Tier 3 | 1.796 | 0 | 0 | 0 | 1.796
35544683 | CWSP - CALISTOGA 1101122350 PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6579 | -122.5946 |  | v3 | 134 | Tier 3 | 0.57595 | 0 | 0 | 0 | 0.57595
35544685 | CWSP - CALISTOGA 1101122350 PH2.7 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6657 | -122.5922 |  | v3 | 134 | Tier 3 | 0.60095 | 0 | 0 | 0.60095 | 0
35544687 | CWSP - CALISTOGA 1101122350 PH2.8 | Base SH | 08W | UNSE | Scoping/Scoped | NB | Region 1 - North Coast | Pope Valley | NAPA | 38.6732 | -122.585 |  | v3 | 134 | Tier 3 | 0.80909 | 0 | 0 | 0.80909 | 0
35544699 | CWSP - ALLEGHANY 1101VR816 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.5599 | -120.8293 |  | v3 | 120 | Tier 3 | 0.22216 | 0 | 0 | 0 | 0.22216
35544720 | CWSP - ALLEGHANY 1101VR816 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.561 | -120.8267 |  | v3 | 120 | Tier 3 | 0.3017 | 0 | 0 | 0 | 0.3017
35544721 | CWSP - ALLEGHANY 1101VR816 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.5595 | -120.8277 |  | v3 | 120 | Tier 3 | 0.28939 | 0 | 0 | 0 | 0.28939
35544722 | CWSP - ALLEGHANY 1101VR816 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.562 | -120.8268 |  | v3 | 120 | Tier 3 | 0.29602 | 0 | 0 | 0 | 0.29602
35544723 | CWSP - ALLEGHANY 1101VR816 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.5618 | -120.826 |  | v3 | 120 | Tier 3 | 0.75492 | 0 | 0 | 0 | 0.75492
35544724 | CWSP - ALLEGHANY 1101VR816 PH 1.8 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Downieville | SIERRA | 39.5677 | -120.8244 |  | v3 | 120 | Tier 3 | 1.6953 | 0 | 0 | 0 | 1.6953
35544809 | CWSP - SHADY GLEN 110248894 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Grass Valley | NEVADA | 39.1377 | -120.962 |  | v3 | 89 | Tier 2 & 3 | 1.7521 | 0 | 0 | 1.7521 | 0
35544810 | CWSP - SHADY GLEN 110248894 PH 1.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1233 | -120.9581 |  | v3 | 89 | Tier 2 & 3 | 1.1299 | 0 | 0 | 0 | 1.1299
35544811 | CWSP - SHADY GLEN 110248894 PH 1.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1193 | -120.9516 |  | v3 | 89 | Tier 2 & 3 | 2 | 0 | 0 | 2 | 0
35544812 | CWSP - SHADY GLEN 110248894 PH 1.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1224 | -120.9517 |  | v3 | 89 | Tier 2 & 3 | 1.4 | 0 | 0 | 1.4 | 0
35544813 | CWSP - SHADY GLEN 110248894 PH 1.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1269 | -120.9563 |  | v3 | 89 | Tier 2 & 3 | 0.61004 | 0 | 0 | 0.61004 | 0
35544814 | CWSP - SHADY GLEN 110248894 PH 1.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1333 | -120.9536 |  | v3 | 89 | Tier 2 & 3 | 1.0938 | 0 | 0 | 0 | 1.0938
35544815 | CWSP - ORO FINO 110276008 PH 1.4 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8855 | -121.6771 |  | v3 | 61 | Tier 3 | 1.65 | 0 | 0 | 1.65 | 0
35544816 | CWSP - ORO FINO 110276008 PH 1.5 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8863 | -121.6743 |  | v3 | 61 | Tier 3 | 2.2 | 0 | 0 | 2.2 | 0
35544818 | CWSP - ORO FINO 110276008 PH 1.6 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8877 | -121.6655 |  | v3 | 61 | Tier 3 | 0.15 | 0 | 0 | 0.15 | 0
35545062 | CWSP - SHADY GLEN 11022232 PH 3.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1745 | -120.8594 |  | v3 | 93 | Tier 2 | 1.01 | 0 | 0 | 0 | 1.01
35545064 | CWSP - SHADY GLEN 11022232 PH 3.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1711 | -120.8711 |  | v3 | 93 | Tier 2 | 1.2701 | 0 | 0 | 0 | 1.2701
35545065 | CWSP - SHADY GLEN 11022232 PH 3.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1732 | -120.8578 |  | v3 | 93 | Tier 2 | 1.39 | 0 | 0 | 0 | 1.39
35545066 | CWSP - SHADY GLEN 11022232 PH 3.6 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1631 | -120.8656 |  | v3 | 93 | Tier 2 | 1.4299 | 0 | 0 | 0 | 1.4299
35545067 | CWSP - SHADY GLEN 11022232 PH 3.7 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1685 | -120.8566 |  | v3 | 93 | Tier 2 | 0.8 | 0 | 0 | 0 | 0.8
35545068 | CWSP - SHADY GLEN 11022232 PH 3.8 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1596 | -120.8584 |  | v3 | 93 | Tier 2 | 0.73996 | 0 | 0 | 0 | 0.73996
35545069 | CWSP - SHADY GLEN 11022232 PH 3.9 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Gold Run | PLACER | 39.1555 | -120.8556 |  | v3 | 93 | Tier 2 | 1.0299 | 0 | 0 | 0 | 1.0299
35545294 | CWSP - COLUMBIA HILL 110190730 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | NEVADA | 39.3389 | -121.1333 |  | v3 | 75 | Tier 2 | 0.48428 | 0 | 0 | 0 | 0.48428
35545295 | CWSP - COLUMBIA HILL 110190730 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | NEVADA | 39.3309 | -121.142 |  | v3 | 75 | Tier 2 | 0.64697 | 0 | 0 | 0 | 0.64697
35545296 | CWSP - COLUMBIA HILL 110190730 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | NEVADA | 39.3236 | -121.1499 |  | v3 | 75 | Tier 2 | 0.28523 | 0 | 0 | 0 | 0.28523
35545299 | CWSP - COLUMBIA HILL 110190730 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | North San Juan | NEVADA | 39.306 | -121.1611 |  | v3 | 75 | Tier 2 | 0.09375 | 0 | 0 | 0 | 0.09375
35546442 | CWSP - KESWICK 11011588 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | French Gulch | SHASTA | 40.6029 | -122.5357 |  | v3 | 83 | Tier 2 & 3 | 0.88996 | 0 | 0 | 0 | 0.88996
35546585 | CWSP - WILDWOOD 110198896 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Platina | SHASTA | 40.3615 | -122.9411 |  | v3 | 109 | Tier 2 | 0.47008 | 0 | 0 | 0 | 0.47008
35546586 | CWSP - WILDWOOD 110198896 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Platina | SHASTA | 40.3623 | -122.9136 |  | v3 | 109 | Tier 2 | 1.1799 | 0 | 0 | 0 | 1.1799
35546587 | CWSP - WILDWOOD 110198896 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Platina | SHASTA | 40.3595 | -122.9098 |  | v3 | 109 | Tier 2 | 0.71004 | 0 | 0 | 0 | 0.71004
35546589 | CWSP - ANTLER 11011612 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Lakehead | SHASTA | 40.8744 | -122.3584 |  | v3 | 143 | Tier 2 & 3 | 0.67992 | 0 | 0 | 0 | 0.67992
35546590 | CWSP - ANTLER 11011612 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Lakehead | SHASTA | 40.8593 | -122.3436 |  | v3 | 143 | Tier 2 & 3 | 2.41 | 0 | 0 | 0 | 2.41
35546591 | CWSP - ANTLER 11011612 PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Lakehead | SHASTA | 40.8587 | -122.3485 |  | v3 | 143 | Tier 2 & 3 | 0.95 | 0 | 0 | 0 | 0.95
35546592 | CWSP - ANTLER 11011612 PH1.6 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Lakehead | SHASTA | 40.8537 | -122.3344 |  | v3 | 143 | Tier 2 & 3 | 0.57008 | 0 | 0 | 0 | 0.57008
35547187 | CWSP - CURTIS 17039240 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 & 3 | 1.46 | 0 | 0 | 0 | 1.46
35547188 | CWSP - CURTIS 17039240 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 & 3 | 1.3598 | 0 | 0 | 0 | 1.3598
35547189 | CWSP - CURTIS 17039240 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 & 3 | 1.5799 | 0 | 0 | 0 | 1.5799
35547190 | CWSP - CURTIS 17039240 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 | 1.65 | 0 | 0 | 0 | 1.65
35547191 | CWSP - CURTIS 17039240 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 | 2.11 | 0 | 0 | 0 | 2.11
35547192 | CWSP - CURTIS 17039240 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 | 2.36 | 0 | 0 | 0 | 2.36
35547193 | CWSP - CURTIS 17039240 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Groveland | TUOLUMNE | 37.8307 | -120.2369 |  | v3 | 67 | Tier 2 | 3.26 | 0 | 0 | 0 | 3.26
35547351 | CWSP - BEAR VALLEY 210576694 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | YO | Region 5 - Central Valley | Coulterville | MARIPOSA | 37.7182 | -120.2044 |  | v3 | 76 | Tier 2 | 1.99 | 0 | 0 | 0 | 1.99
35548717 | CWSP - KESWICK 11019712 PH 2.8 | Base SH | 08W | UNSE | Scoping/Scoped | NV | Region 2 - North East | Shasta | SHASTA | 40.5958 | -122.4874 |  | v3 | 43 | Tier 3 | 0.52008 | 0 | 0 | 0 | 0.52008
35548781 | CWSP - SHADY GLEN 11012768 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1055 | -120.9608 |  | v3 | 120 | Tier 2 | 0.66004 | 0 | 0 | 0 | 0.66004
35548782 | CWSP - SHADY GLEN 11012768 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1097 | -120.9646 |  | v3 | 120 | Tier 2 | 0.83996 | 0 | 0 | 0 | 0.83996
35548783 | CWSP - SHADY GLEN 11012768 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.11 | -120.964 |  | v3 | 120 | Tier 2 | 1 | 0 | 0 | 0 | 1
35548784 | CWSP - SHADY GLEN 11012768 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Colfax | PLACER | 39.1109 | -120.9619 |  | v3 | 120 | Tier 2 | 0.65 | 0 | 0 | 0 | 0.65
35548785 | CWSP - DRUM 1101CB PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Alta | PLACER | 39.2571 | -120.7669 |  | v3 | 103 | Tier 3 | 0.27992 | 0 | 0 | 0 | 0.27992
35549058 | CWSP - PLACERVILLE 111219712 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.719 | -120.7819 |  | v3 | 148 | Tier 2 | 0.05 | 0 | 0 | 0 | 0.05
35549059 | CWSP - PLACERVILLE 111219712 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7236 | -120.7683 |  | v3 | 148 | Tier 2 | 0.95 | 0 | 0 | 0 | 0.95
35549201 | CWSP - PLACERVILLE 111219712 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7173 | -120.7674 |  | v3 | 148 | Tier 2 | 0.82008 | 0 | 0 | 0 | 0.82008
35549203 | CWSP - PLACERVILLE 111219712 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7157 | -120.7646 |  | v3 | 148 | Tier 2 | 0.71004 | 0 | 0 | 0 | 0.71004
35549204 | CWSP - PLACERVILLE 111219712 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7151 | -120.7653 |  | v3 | 148 | Tier 2 | 0.56004 | 0 | 0 | 0 | 0.56004
35549206 | CWSP - PLACERVILLE 111219712 PH 2.6 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7182 | -120.757 |  | v3 | 148 | Tier 2 | 0.11004 | 0 | 0 | 0 | 0.11004
35549207 | CWSP - PLACERVILLE 111219712 PH 2.7 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7179 | -120.7562 |  | v3 | 148 | Tier 2 | 1.31 | 0 | 0 | 0 | 1.31
35549208 | CWSP - PLACERVILLE 111219712 PH 2.8 | Base SH | 08W | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7187 | -120.7489 |  | v3 | 148 | Tier 2 | 1.39 | 0 | 0 | 0 | 1.39
35550921 | CWSP - ORO FINO 110276008 PH 2.4 | Targeted UG | 3UG | ESTS | Estimating | NV | Region 2 - North East | Forest Ranch | BUTTE | 39.8713 | -121.6777 |  | v3 | 61 | Tier 3 | 2.1 | 0 | 0 | 2.1 | 0
35552171 | CWSP - PIKE CITY 1101CB PH 3.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.4694 | -121.0331 |  | v3 | 116 | Tier 3 | 1.0299 | 0 | 0 | 0 | 1.0299
35552172 | CWSP - PIKE CITY 1101CB PH 3.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.4758 | -121.0385 |  | v3 | 116 | Tier 3 | 0.97992 | 0 | 0 | 0 | 0.97992
35552173 | CWSP - PIKE CITY 1101CB PH 3.5 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.454 | -121.0327 |  | v3 | 116 | Tier 3 | 1.54 | 0 | 0 | 0 | 1.54
35552175 | CWSP - PIKE CITY 1101CB PH 3.2 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Camptonville | YUBA | 39.4784 | -121.0342 |  | v3 | 116 | Tier 3 | 1.49 | 0 | 0 | 0 | 1.49
35554777 | CWSP - PLACERVILLE 2106935216 PH 3.3 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7897 | -120.7378 |  | v3 | 58 | Tier 3 | 3.1 | 0 | 0 | 0 | 3.1
35554778 | CWSP - PLACERVILLE 2106935216 PH 3.4 | Targeted UG | 3UG | UNSE | Scoping/Scoped | SI | Region 2 - North East | Placerville | EL DORADO | 38.7899 | -120.7198 |  | v3 | 58 | Tier 3 | 2.5701 | 0 | 0 | 2.5701 | 0
35554850 | CWSP - WEST POINT 110277204 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | ST | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS | 38.3442 | -120.583 |  | v3 | 110 | Tier 2 & 3 | 3.46 | 0 | 0 | 0 | 3.46
74001486 | GRIZZLY PEAK BLVD BERKELEY R20A | Other | 30A | CONS | In-Construction | EB | Region 3 - Bay Area | Berkeley | ALAMEDA | 37.8838 | -122.2484 |  | v2 | 2792 | Tier 2 & 3 | 1.7312 | 0 | 0 | 0 | 1.7312
74010582 | * GREEN VALLEY RD EL DORADO CNTY R20A | Other | 30A | PEND | Permitting/Dependency | SI | Region 2 - North East | Placerville | EL DORADO | 38.726 | -120.8396 |  | v2 | 811 | Tier 2 | 1.3299 | 0 | 0 | 1.3299 | 0
35112126 | PARAGALIA | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.78 | -121.6092 |  | N/A | N/A | Non-HFTD |  | 0 | 1.8964 | 0 | 0
35127550 | MYRTLE WAY | Community Rebuild | 95F CEMA | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7904 | -121.5945 |  | N/A | N/A | Non-HFTD |  | 0 | 1.6614 | 0 | 0
35352075 | BILLE WAGSTAFF | Community Rebuild | 08W | MAPP | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7777 | -121.6077 |  | N/A | N/A | Non-HFTD |  | 5.6055 | 0 | 0 | 0
35352072 | OLIVER | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7703 | -121.6265 |  | N/A | N/A | Non-HFTD |  | 0 | 0.70947 | 0 | 0
35246595 | SKYWAY PH5 (Wagstaff to Clark) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7842 | -121.5991 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 5.8848 | 0
35244027 | SKYWAY PH6 (Old Skyway) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.8074 | -121.5789 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 3.5089 | 0
35463723 | SKYWAY PH5.5 (Clark to Pentz) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7842 | -121.5991 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 1.3258 | 0
35486222 | CEMETERY | Community Rebuild | 95F O | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.8092 | -121.5811 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 0.93561 | 0
35189791 | WARREN RD | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7886 | -121.5873 |  | N/A | N/A | Non-HFTD |  | 1.4091 | 0 | 0 | 0
35189792 | CYPRESS LN | Community Rebuild | 95F O | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7796 | -121.5895 |  | N/A | N/A | Non-HFTD |  | 3.6905 | 0 | 0 | 0
35117455 | HERMAN | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7813 | -121.594 |  | N/A | N/A | Non-HFTD |  | 0.81894 | 0.35133 | 0 | 0
35189793 | SEVERNS LN | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7793 | -121.5986 |  | N/A | N/A | Non-HFTD |  | 0 | 0.11799 | 0 | 0
35227400 | OAK WAY | Community Rebuild | 95F O | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7712 | -121.6031 |  | N/A | N/A | Non-HFTD |  | 0 | 2.275 | 0 | 0
35126750 | JERRYS WAY | Community Rebuild | 95F O | MAPP | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7741 | -121.5895 |  | N/A | N/A | Non-HFTD |  | 2.5801 | 0 | 0 | 0
35175547 | WAGSTAFF | Community Rebuild | 95F O | PEND | Permitting/Dependency | NV | Region 2 - North East | N/A | BUTTE | 39.7886 | -121.5797 |  | N/A | N/A | Non-HFTD |  | 1.2951 | 0 | 0 | 0
35424604 | PENTZ PH1 (Wagstaff and North) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7719 | -121.5798 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 3.0303 | 0
35189851 | VALLEY VIEW | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7646 | -121.6344 |  | N/A | N/A | Non-HFTD |  | 0.20095 | 0 | 0 | 0
35227401 | CAMELLIA DR | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7628 | -121.6233 |  | N/A | N/A | Non-HFTD |  | 1.2627 | 0 | 0 | 0
35118676 | REDBUD DR | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7551 | -121.6455 |  | N/A | N/A | Non-HFTD |  | 3.4761 | 0 | 0 | 0
35126645 | CRESTVIEW | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7612 | -121.6342 |  | N/A | N/A | Non-HFTD |  | 2.2104 | 0 | 0 | 0
35246309 | SKYWAY PH4 (Bille to Wagstaff) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7752 | -121.6093 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 0 | 1.2898
35227402 | STINSON LN | Community Rebuild | 95F O | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7703 | -121.6071 |  | N/A | N/A | Non-HFTD |  | 0.9089 | 0.30152 | 0 | 0
35246589 | KLING CT | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.764 | -121.5986 |  | N/A | N/A | Non-HFTD |  | 0 | 0.56288 | 0 | 0
35175548 | HIGH SCHOOL MAXWELL | Community Rebuild | 95F O | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7619 | -121.6125 |  | N/A | N/A | Non-HFTD |  | 3.2771 | 0 | 0 | 0
35227403 | MAPLE PARK | Community Rebuild | 95F O | MAPP | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7616 | -121.6079 |  | N/A | N/A | Non-HFTD |  | 2.1731 | 0 | 0 | 0
35227405 | SHADOWBROOK | Community Rebuild | 95F O | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7578 | -121.6071 |  | N/A | N/A | Non-HFTD |  | 0.25795 | 0 | 0 | 0
35227406 | COLLEGE HILL | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7523 | -121.6185 |  | N/A | N/A | Non-HFTD |  | 2.443 | 0 | 0 | 0
35227404 | ACADEMY | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7538 | -121.6172 |  | N/A | N/A | Non-HFTD |  | 1.5837 | 0 | 0 | 0
35227408 | PEARSON RD | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7524 | -121.6126 |  | N/A | N/A | Non-HFTD |  | 2.021 | 0 | 0 | 0
35475301 | LOGAN | Community Rebuild | 95F O | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7496 | -121.6249 |  | N/A | N/A | Non-HFTD |  | 0 | 1.3055 | 0 | 0
35227411 | COPELAND RD | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7595 | -121.6024 |  | N/A | N/A | Non-HFTD |  | 2.6706 | 0 | 0 | 0
35189853 | HAPPY WOODS | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7681 | -121.5891 |  | N/A | N/A | Non-HFTD |  | 1.4928 | 0 | 0 | 0
35246590 | ALEXANDER CT | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7696 | -121.579 |  | N/A | N/A | Non-HFTD |  | 1.0837 | 0.93504 | 0 | 0
35350874 | NORWOOD | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7637 | -121.5732 |  | N/A | N/A | Non-HFTD |  | 1.66 | 0 | 0 | 0
35246308 | HOSPITAL | Community Rebuild | 95F O | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7572 | -121.5722 |  | N/A | N/A | Non-HFTD |  | 0 | 0.68977 | 0 | 0
35227412 | PENTZ PH2 (Arrowhead to Bille) | Community Rebuild | 95F O | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.769 | -121.5786 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 3.1021 | 0
35244220 | HONEY RUN | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7538 | -121.6327 |  | N/A | N/A | Non-HFTD |  | 0 | 2.2742 | 0 | 0
35286270 | BOQUEST | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7583 | -121.6291 |  | N/A | N/A | Non-HFTD |  | 0.98144 | 0 | 0 | 0
35127360 | PRINCETON WAY | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7461 | -121.6435 |  | N/A | N/A | Non-HFTD |  | 0.71212 | 0 | 0 | 0
35491035 | BLACK OLIVE P2 | Community Rebuild | 95F O | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7528 | -121.6291 |  | N/A | N/A | Non-HFTD |  | 0 | 0.53106 | 0 | 0
35227413 | STARLIGHT CT | Community Rebuild | 95F O | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7423 | -121.6423 |  | N/A | N/A | Non-HFTD |  | 0 | 1.1119 | 0 | 0
35227415 | JARVIS LN | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7389 | -121.6402 |  | N/A | N/A | Non-HFTD |  | 2.879 | 0 | 0 | 0
35227417 | CHAPARRAL | Community Rebuild | 95F O | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7323 | -121.6513 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 1.1364 | 0
35189983 | FOSTER RD | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7484 | -121.6266 |  | N/A | N/A | Non-HFTD |  | 2.0981 | 0 | 0 | 0
35227409 | SCOTTWOOD | Community Rebuild | 95F O | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7501 | -121.6242 |  | N/A | N/A | Non-HFTD |  | 0 | 2.2646 | 0 | 0
35246594 | ROSEHILL | Community Rebuild | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | N/A | BUTTE | 39.7382 | -121.6208 |  | N/A | N/A | Non-HFTD |  | 0 | 1.9519 | 0 | 0
35126752 | APPLE | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7333 | -121.6353 |  | N/A | N/A | Non-HFTD |  | 1.2731 | 0 | 0 | 0
35246316 | WAYLAND | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7265 | -121.6374 |  | N/A | N/A | Non-HFTD |  | 0 | 4.9066 | 0 | 0
35189984 | PALOMA AVE | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7471 | -121.6129 |  | N/A | N/A | Non-HFTD |  | 3.4121 | 0 | 0 | 0
35246591 | OAK KNOLL (Caltrans) | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.7485 | -121.6086 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 3.8648 | 0
35246592 | AMERICAN | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7367 | -121.6125 |  | N/A | N/A | Non-HFTD |  | 0 | 2.2205 | 0 | 0
35189987 | WHATEVER LN | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7426 | -121.5937 |  | N/A | N/A | Non-HFTD |  | 2.8201 | 0 | 0 | 0
35227481 | HILLPARK LN | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7392 | -121.5724 |  | N/A | N/A | Non-HFTD |  | 4.4428 | 0 | 0 | 0
35144480 | SHAW CIR | Community Rebuild | 95F O | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8116 | -121.5956 |  | N/A | N/A | Non-HFTD |  | 2.6464 | 0 | 0 | 0
35353399 | EUREKA DR | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8082 | -121.5973 |  | N/A | N/A | Non-HFTD |  | 2.2892 | 0 | 0 | 0
35353463 | ANDOVER DR | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7978 | -121.6014 |  | N/A | N/A | Non-HFTD |  | 0 | 2.5441 | 0 | 0
35118673 | S PARK DR | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8005 | -121.6047 |  | N/A | N/A | Non-HFTD |  | 0 | 2.9197 | 0 | 0
35118674 | GLENDALE DR | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8082 | -121.6017 |  | N/A | N/A | Non-HFTD |  | 0 | 2.1636 | 0 | 0
35353466 | W PARK DR | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8091 | -121.5998 |  | N/A | N/A | Non-HFTD |  | 2.603 | 0 | 0 | 0
35353467 | DREXEL DR | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8182 | -121.5952 |  | N/A | N/A | Non-HFTD |  | 1.8271 | 0 | 0 | 0
35353468 | PONDEROSA DR | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8167 | -121.598 |  | N/A | N/A | Non-HFTD |  | 0 | 1.7324 | 0 | 0
35353470 | JOPLIN CT | Community Rebuild | 08W | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8146 | -121.6066 |  | N/A | N/A | Non-HFTD |  | 0 | 3.5631 | 0 | 0
35353477 | WYCLIFF WAY | Community Rebuild | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | N/A | BUTTE | 39.8192 | -121.6024 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 2.0114 | 0
35353479 | CRESTON DR | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8211 | -121.6013 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 1.8172 | 0
35353525 | SHERWOOD CIR | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8243 | -121.5994 |  | N/A | N/A | Non-HFTD |  | 0 | 0 | 2.1305 | 0
35353527 | CITADEL WAY | Community Rebuild | 08W | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8221 | -121.5955 |  | N/A | N/A | Non-HFTD |  | 0 | 1.3218 | 0 | 0
35246598 | DOGTOWN | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.8149 | -121.5802 |  | N/A | N/A | Non-HFTD |  | 2.1311 | 0 | 0 | 0
35441211 | MAGALIA DAM | Community Rebuild | 08W | PEND | Permitting/Dependency | NV | Region 2 - North East | N/A | BUTTE | 39.8149 | -121.5802 |  | N/A | N/A | Non-HFTD |  | 0 | 0.45568 | 0 | 0
35179068 | Short_Harmony | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7371 | -121.6464 |  | N/A | N/A | Non-HFTD |  | 0 | 0.077462 | 0 | 0
35226602 | BUCOCAMPUG 5365 CLARK RD | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7427 | -121.61 |  | N/A | N/A | Non-HFTD |  | 0.092992 | 0 | 0 | 0
35246596 | PBS-Malibu | Community Rebuild | 08W | DOCC | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7329 | -121.5738 |  | N/A | N/A | Non-HFTD |  | 0.47178 | 0 | 0 | 0
35254274 | PBS-NOTTONGHAM PARK | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7598 | -121.6341 |  | N/A | N/A | Non-HFTD |  | 0.073864 | 0 | 0 | 0
35254275 | PBS-BURKE LN | Community Rebuild | 95F | PEND | Permitting/Dependency | NV | Region 2 - North East | N/A | BUTTE | 39.7704 | -121.6012 |  | N/A | N/A | Non-HFTD |  | 0 | 0.074432 | 0 | 0
35254342 | PBS-RITA LN | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7538 | -121.6172 |  | N/A | N/A | Non-HFTD |  | 0.045455 | 0 | 0 | 0
35487869 | PBS-360 OAK SPRING RD | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7441 | -121.6412 |  | N/A | N/A | Non-HFTD |  | 0 | 0.21686 | 0 | 0
35254345 | PBS-NUTMEG WAY | Community Rebuild | 95F | UNSC | Ready for Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7874 | -121.601 |  | N/A | N/A | Non-HFTD |  | 0 | 0.00625 | 0 | 0
35333044 | Short_1105 Lanser Dr | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7409 | -121.6076 |  | N/A | N/A | Non-HFTD |  | 0.054924 | 0 | 0 | 0
35345874 | Short_BILLE | Community Rebuild | 08W | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7694 | -121.5812 |  | N/A | N/A | Non-HFTD |  | 0.8072 | 0 | 0 | 0
35399500 | Short_James Drive | Community Rebuild | 95F | FICL | Post-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7583 | -121.6178 |  | N/A | N/A | Non-HFTD |  | 0.15189 | 0 | 0 | 0
35499494 | Short_Moore Rd South | Community Rebuild | 08W | ESTS | Estimating | NV | Region 2 - North East | N/A | BUTTE | 39.771 | -121.6087 |  | N/A | N/A | Non-HFTD |  | 0 | 0.47348 | 0 | 0
35469309 | Short_Academy (service) | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7546 | -121.6168 |  | N/A | N/A | Non-HFTD |  | 0 | 0.073295 | 0 | 0
35483343 | Short_1040 Buschmann | Community Rebuild | 95F | CONS | In-Construction | NV | Region 2 - North East | N/A | BUTTE | 39.7484 | -121.6097 |  | N/A | N/A | Non-HFTD |  | 0 | 0.096023 | 0 | 0

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Idle Facilities | Removal of Primary Conductor in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
MAT Code
MAT Code | Description
06A | Feeder Projects Associated with Substation Capacity
08W | System Hardening Wildfire Resiliency Projects
10H | Work Requested by Others - Rule 20B
10I | Work Requested by Others - Rule 20C
10J | Work Requested by Others - Overhead Relocation
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
49M | Preinstalled Interconnection Hubs / Microgrids: non-gen
95F | Electric Distribution Major Emergency
SAP Status and Status
SAP Status | Status | Description
UNSE | Scoping/Scoped | Project is being scoped for appropriate hardening method and general route alignment.
ESTS | Estimating | Detailed engineering drawing and estimate is created.
ADER | Estimating | Project drawing and estimates being reviewed and approved by senior engineer/estimator.
APPR | Estimating | Project drawing and estimates being reviewed and approved by supervisor.
PEND | Permitting/Dependency | Project obtains all necessary permits and land rights for execution/construction.
UNSC | Ready for Construction | Project is ready to be scheduled for start of construction.
CONS | In-Construction | Construction is underway (can occur across different phases throughout the legnth of the project).
DOCC | Post-Construction | Construction is complete, "as-built" documents are being collected/finalized.
DCNL | Post-Construction | Final labor charges posted, order not ready to be mapped.
MAPP | Post-Construction | Completed project is being added to PG&E GIS system of record.
POST | Post-Construction | Completed project requiring post-estimate.
FICL | Post-Construction | Project is financially closed out (no additional labor charges).
PROD | Post-Construction | With Utility Operations Production Specialist for special handling prior to completion/closure
PREC | Post-Construction | Final project closeout checklist is completed.
CLSD | Closed | Project is completely closed in system of record.
Division
Division Acronym | Division Name
CC | Central Coast
CV | Central Valley
DA | De Anza
DI | Diablo
EB | East Bay
FR | Fresno
HB | Humboldt
KE | Kern
LP | Los Padres
NB | North Bay
NV | North Valley
PN | Peninsula
SA | Sacramento
SF | San Francisco
SI | Sierra
SJ | San Jose
SO | Sonoma
ST | Stockton
YO | Yosemite
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.