## 2023 - 2025 Plan
State | District | Location (Circuit) | Line Miles | Planned Completion Year | Status
CA | Yreka | 5G40 | 1.16 | 2023 | Complete
CA | Yreka | 5G83 | 5.0388 | 2023 | Complete
CA | Mt Shasta | 5G76/5G79 | 1.283 | 2023 | Complete
CA | Mt Shasta | 7G75 | 0.22367 | 2023 | Complete
CA | Yreka | 5G83 | 1.7053 | 2023 | Complete
CA | Yreka | 5G83 | 4.5275 | 2023 | Complete
CA | Yreka | 5G83 | 2.0938 | 2023 | Complete
CA | Yreka | 5G83 | 4.543 | 2023 | Complete
CA | Yreka | 5G83 | 4.4712 | 2023 | Complete
CA | Yreka | 5G83 | 5.1188 | 2023 | Complete
CA | Yreka | 5G83 | 2.5085 | 2023 | Complete
CA | Yreka | 5G83 | 0.42576 | 2023 | Complete
CA | Yreka | 5G83 | 3.9269 | 2023 | Complete
CA | Yreka | 5G83 | 6.2377 | 2023 | Complete
CA | Mt Shasta | 5G79 | 1.3327 | 2023 | Complete
CA | Mt Shasta | 5G76 | 1.3256 | 2023 | Complete
CA | Mt Shasta | 5G76 | 2.9775 | 2023 | Complete
CA | Mt Shasta | 5G79 | 3.6307 | 2023 | Complete
CA | Mt Shasta | 5G79 | 2.0545 | 2023 | Complete
CA | Mt Shasta | 5G79 | 1.7403 | 2023 | Complete
CA | Mt Shasta | 5G79 | 1.45 | 2023 | Complete
CA | Yreka | 5G83 | 5.3701 | 2023 | Complete
CA | Yreka | 5G83 | 5.6945 | 2023 | Complete
CA | Yreka | 5G16 | 0.64508 | 2023 | Complete
CA | Yreka | 5G16 | 1.4485 | 2023 | Complete
CA | Yreka | 5G16 | 4.0818 | 2023 | Complete
CA | Yreka | 5G14 | 0.81155 | 2023 | Complete
CA | Mt Shasta | 5G79 | 2.7996 | 2023 | Complete
CA | Yreka | 5G40 | 0.37879 | 2023 | Complete
CA | Yreka | 5G40 | 1.3682 | 2023 | Complete
CA | Yreka | 5G40 | 4.4011 | 2023 | Complete
CA | Yreka | 5G40 | 1.9106 | 2023 | Complete
CA | Yreka | 5G40 | 3.2212 | 2023 | Complete
CA | Yreka | 5G40 | 3.6165 | 2023 | Complete
CA | Mt Shasta | 7G81 | 0.17992 | 2023 | Complete
CA | Yreka | 5G40 | 1.2064 | 2023 | Complete
CA | Yreka | 5G39 | 2.5972 | 2023 | Complete
CA | Mt Shasta | 8G95 | 0.63542 | 2023 | Complete
CA | Mt Shasta | 8G95 | 1.3305 | 2023 | Complete
CA | Grants Pass | 5R106 | 1.2915 | 2023 | Complete
CA | Mt Shasta | 5G76/5G79 | 0.075947 | 2024 | Construction
CA | Yreka | 5G83 | 0.43409 | 2024 | Construction
CA | Yreka | 5G83 | 0.77909 | 2024 | Construction
CA | Yreka | 5G40 | 0.039394 | 2024 | Complete
CA | Yreka | 5G40 | 0.3483 | 2024 | Complete
CA | Yreka | 5G40 | 2.386 | 2024 | Construction
CA | Yreka | 5G40 | 4.9928 | 2024 | Complete
CA | Mt Shasta | 7G81 | 0.025189 | 2024 | Construction
CA | Mt Shasta | 7G81 | 2.22 | 2024 | Design
CA | Mt Shasta | 8G95 | 2.5398 | 2024 | Complete
CA | Mt Shasta | 8G95 | 2.9498 | 2024 | Construction
CA | Yreka | 5G39 | 3.746 | 2024 | Complete
CA | Yreka | 5G39 | 1.832 | 2024 | Complete
CA | Yreka | 5G39 | 1.6339 | 2024 | Construction
CA | Yreka | 5G39 | 2.73 | 2024 | Complete
CA | Yreka | 5G39 | 0.49678 | 2024 | Permitting
CA | Yreka | 5G83 | 3.2697 | 2024 | Construction
CA | Yreka | 5G83 | 1.3566 | 2024 | Construction
CA | Yreka | 5G83 | 0.76 | 2024 | Permitting
CA | Yreka | 5G45 | 1.2 | 2024 | Construction
CA | Yreka | 5G45 | 0.9 | 2024 | Construction
CA | Mt Shasta | 5G76 | 3.65 | 2024 | Construction
CA | Mt Shasta | 5G76 | 4.5122 | 2024 | Construction
CA | Mt Shasta | 5G76 | 3.23 | 2024 | Construction
CA | Mt Shasta | 5G76 | 2.3036 | 2024 | Complete
CA | Mt Shasta | 5G76 | 3.9 | 2024 | Construction
CA | Mt Shasta | 5G76/5G79 | 3.65 | 2024 | Construction
CA | Mt Shasta | 5G76/5G79 | 3.4136 | 2024 | Complete
CA | Mt Shasta | 5G76/5G79 | 2.9572 | 2024 | Construction
CA | Mt Shasta | 5G76/5G79 | 2.86 | 2024 | Construction
CA | Mt Shasta | 5G76/5G79 | 2.3036 | 2024 | Construction
CA | Mt Shasta | 5G79 | 4.6 | 2024 | Construction
CA | Mt Shasta | 5G79 | 3.2 | 2024 | Construction
CA | Mt Shasta | 5G79 | 4.5 | 2024 | Construction
CA | Yreka | 5G83 | 0.2 | 2024 | Construction
CA | Mt Shasta | 5G79 | 4.2 | 2025 | Permitting
CA | Mt Shasta | 5G79 | 0.5 | 2025 | Permitting
CA | Yreka | 5G40 | 2.3 | 2025 | Design
CA | Yreka | 5G40 | 3.4 | 2025 | Design
CA | Yreka | 5G40 | 4.4 | 2025 | Design
CA | Yreka | 5G40 | 6 | 2025 | Design
CA | Yreka | 5G40 | 6 | 2025 | Design
CA | Yreka | 5G40 | 4.5 | 2025 | Design
CA | Mt Shasta | 7G82 | 1.88 | 2025 | Design
CA | Mt Shasta | 7G82 | 0.11 | 2025 | Design
CA | Yreka | 5G39 | 3.23 | 2025 | Permitting
CA | Yreka | 5G39 | 0.5 | 2025 | Permitting
CA | Yreka | 5G39 | 7.3 | 2025 | Design
CA | Yreka | 5G16 | 0.28 | 2025 | Permitting
CA | Yreka | 5G16 | 0.32 | 2025 | Permitting
CA | Yreka | 5G16 | 2.85 | 2025 | Design
CA | Yreka | 5G16 | 0.17 | 2025 | Design
CA | Yreka | 5G16 | 1.87 | 2025 | Design
CA | Yreka | 5G16 | 3.12 | 2025 | Design
CA | Yreka | 5G16 | 3.48 | 2025 | Design
CA | Yreka | 5G16 | 2.77 | 2025 | Design
CA | Yreka | 5G16 | 2.74 | 2025 | Design
CA | Yreka | 5G16 | 3.85 | 2025 | Design
CA | Mt Shasta | 5G76 | 2.8 | 2025 | Design
CA | Crescent City | 5R165 | 0.83 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.27 | 2025 | Permitting
CA | Crescent City | 5R165 | 2.38 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.01 | 2025 | Permitting
CA | Crescent City | 5R165 | 0.85 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.51 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.9 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.73 | 2025 | Permitting
CA | Crescent City | 5R165 | 1.66 | 2025 | Permitting
CA | Crescent City | 5R165 | 2.28 | 2025 | Permitting
CA | Mt. Shasta | 5G97 | 2.5 | 2025 | Scoping
CA | Mt. Shasta | 5G97 | 3.1 | 2025 | Scoping
CA | Mt. Shasta | 5G97 | 3.1 | 2025 | Scoping
CA | Mt. Shasta | 8G65 | 5.98 | 2025 | Scoping
CA | Mt. Shasta | 5G99 | 4.9 | 2025 | Scoping
CA | Mt. Shasta | 5G99 | 3.2 | 2025 | Scoping
CA | Mt. Shasta | 5G99 | 1.8 | 2025 | Scoping
CA | Mt. Shasta | 5G99 | 4.7 | 2025 | Scoping
CA | Crescent City | 5R96 | 10.19 | 2025 | Scoping
CA | Crescent City | 5R171 | 2 | 2025 | Scoping
CA | Yreka | 8G27 | 5 | 2025 | Scoping
CA | Mt. Shasta | 5G93 | 5 | 2025 | Scoping